## 2021 Exec Status
|  |  | 2021 | [5 empty] | Circuit Name | Division | Miles
|  | Status | Mileage | Projects |  |  |  |  | ALLEGHANY 1101 | Sierra | 1.74
|  | 0. PG&E Responsibility to Design | 31.8 | 1 |  |  |  |  | BANGOR 1101 | Sierra | 0.85
Scope status | Exec Status code | 1. PM Not Created | 0 | 0 |  |  |  |  | BIG BASIN 1101 | Central Coast | 1.4733
Pre-Scope | 2 | 2. PM Created (UNSE) | 11.93 | 2 |  |  |  |  | BIG BEND 1102 | North Valley | 31.9301
Pre-Scope | 3 | 3. Design in Progress | 0 | 0 |  |  |  |  | BRUNSWICK 1103 | Sierra | 9.1785
Pre-Scope | 4 | 4. Preliminary Scope Review | 0 | 0 |  |  |  |  | BRUNSWICK 1110 | Sierra | 0.055871
Pre-Scope | 5 | 5. Return to Engineer | 0.95 | 1 |  |  |  |  | BUCKS CREEK 1101 | North Valley | 5.4104
Pre-Scope | 6 | 6. AA Submitted/Field Desktop Meeting Scheduled | 0 | 0 | Scoped Miles |  |  |  | CALISTOGA 1102 | North Bay | 0.18
In Scoping | 7 | 7. AA Approved/Field Desktop Meeting Scheduled | 9.6634 | 5 | Overhead | Underground | Removal | Remote Grid | CAMP EVERS 2106 | Central Coast | 1.0392
In Scoping | 8 | 8. Estimating Field Verification | 5.42 | 2 | 0 | 5.42 | 0 | 0 | CLAYTON 2212 | Diablo | 2.8186
In Scoping | 9 | 9. Return to Planning | 101.5156 | 53 | 71.1358 | 18.7029 | 11.6769 | 0 | COARSEGOLD 2104 | Yosemite | 8.2815
In Scoping | 10 | 10. Field Review Incorporated | 50.0814 | 41 | 39.85 | 10.2314 | 0 | 0 | COLUMBIA HILL 1101 | Sierra | 5.65
In Scoping | 11 | 11. Grid Design completed review | 18.3011 | 7 | 18.3011 | 0 | 0 | 0 | CORNING 1102 | North Valley | 3.04
In Scoping | 12 | 12. Scheduled for Approval meeting | 0 | 0 | 0 | 0 | 0 | 0 | CRESTA 1101 | North Valley | 0
In Scoping | 13 | 13. Project Scope Approved | 144.9984 | 124 | 61.4425 | 73.1084 | 7.1781 | 3.0494 | DESCHUTES 1104 | North Valley | 18.3011
Scoped | 14 | 14. In Estimating (ESTS) | 96.2609 | 51 | 66.8503 | 28.7956 | 0.61496 | 0 | DIAMOND SPRINGS 1105 | Sierra | 1.6339
Scoped | 15 | 15. ADE Review (ADER) | 1.4799 | 1 | 1.4799 | 0 | 0 | 0 | DIAMOND SPRINGS 1107 | Sierra | 8.465
Scoped | 16 | 16. CMCS Approved (DS73) | 0 | 0 | 0 | 0 | 0 | 0 | DUNBAR 1101 | Sonoma | 2.4614
Scoped | 17 | 17. Estimate Approval (APPR) | 1.11 | 2 | 1.11 | 0 | 0 | 0 | DUNLAP 1102 | Fresno | 2.6
Scoped | 18 | 18. Pending Dependencies (PEND) | 11.2708 | 9 | 6.7267 | 3.7103 | 0.84356 | 0 | ELK CREEK 1101 | North Valley | 7.9
Scoped | 19 | 19. Construction Ready (UNSC) | 61.3982 | 34 | 6.9384 | 54.4563 | 0 | 0 | FITCH MOUNTAIN 1113 | Sonoma | 8.5158
Scoped | 20 | 20. In-Construction (CONS) | 46.2777 | 29 | 50.4221 | 0.4483 | 0 | 0 | FROGTOWN 1701 | Stockton | 0.59
|  |  | 592.4574 | 362 | 324.2569 | 194.8733 | 20.3135 | 3.0494 | FROGTOWN 1702 | Stockton | 1.2739
[9 empty] | FULTON 1107 | Sonoma | 4.015
[9 empty] | HALF MOON BAY 1103 | Peninsula | 6.37
[9 empty] | HIGHLANDS 1102 | Humboldt | 17.3
[9 empty] | KESWICK 1101 | North Valley | 9.1078
[9 empty] | KIRKER 2104 | Diablo | 5.44
[9 empty] | KONOCTI 1102 | Humboldt | 4.2114
[9 empty] | LAS GALLINAS A 1105 | North Bay | 2.7962
[9 empty] | LOS GATOS 1106 | De Anza | 0.84905
[9 empty] | MARIPOSA 2101 | Yosemite | 5.5536
[9 empty] | MARIPOSA 2102 | Yosemite | 14.5083
[9 empty] | MARTELL 1101 |  | 0.87
[9 empty] | MIDDLETOWN 1101 | Humboldt | 48.7783
[9 empty] | MIDDLETOWN 1102 | Humboldt | 6.8034
[9 empty] | MIDDLETOWN 1103 | Humboldt | 23.9445
[9 empty] | MIWUK 1701 | Yosemite | 15.6106
[9 empty] | MIWUK 1702 | Yosemite | 7.4222
[9 empty] | MOUNTAIN QUARRIES 2101 | Sierra | 6.39
[9 empty] | NORTH DUBLIN 2101 | Mission | 0
[9 empty] | OAKHURST 1101 | Yosemite | 2.6721
[9 empty] | OAKHURST 1103 | Yosemite | 3.855
[9 empty] | OLETA 1101 | Stockton | 2.88
[9 empty] | OREGON TRAIL 1103 | North Valley | 62.3756
[9 empty] | PINE GROVE 1102 | Stockton | 4.3156
[9 empty] | PLACERVILLE 1112 | Sierra | 0.38
[9 empty] | PLACERVILLE 2106 | Sierra | 1.83
[9 empty] | POSO MOUNTAIN 2103 | Kern | 0
[9 empty] | POSO MOUNTAIN 2104 | Kern | 0
[9 empty] | POTTER VALLEY P H 1105 | Humboldt | 1.8343
[9 empty] | PUEBLO 2102 | North Bay | 3.3379
[9 empty] | PUTAH CREEK 1102 | Sacramento | 0.52
[9 empty] | RINCON 1103 | Sonoma | 1.5
[9 empty] | RINCON 1104 | Sonoma | 1.78
[9 empty] | RIO DELL 1102 | Humboldt | 2.8937
[9 empty] | ROB ROY 2105 | Central Coast | 1.86
[9 empty] | SHINGLE SPRINGS 2109 | Sierra | 30.1644
[9 empty] | SILVERADO 2102 | North Bay | 3.5445
[9 empty] | SILVERADO 2104 | North Bay | 6.1621
[9 empty] | SILVERADO 2105 | North Bay | 1.2676
[9 empty] | STANISLAUS 1702 | Stockton | 3.6612
[9 empty] | TIDEWATER 2106 | Diablo | 3.64
[9 empty] | TULUCAY 1101 | North Bay | 0
[9 empty] | UPPER LAKE 1101 | North Coast | 1.1055
[9 empty] | VACA DIXON 1101 | Sacramento | 0.39811
[9 empty] | VACA DIXON 1105 | Sacramento | 33.47
[9 empty] | VACAVILLE 1104 | Sacramento | 14.58
[9 empty] | VARIOUS | Various | 31.8
[9 empty] | VOLTA 1101 | North Valley | 3.461
[9 empty] | WILDWOOD 1101 | North Valley | 8.09
[9 empty] | WYANDOTTE 1103 | North Valley | 76.0708
[9 empty] | WYANDOTTE 1109 | North Valley | 1.9093
[9 empty] | SILVERADO 2102 | North Bay | 3.5445
[9 empty] | SILVERADO 2104 | North Bay | 6.1621
[9 empty] | SILVERADO 2105 | North Bay | 1.2676
[9 empty] | STANISLAUS 1702 | Stockton | 3.6612
[9 empty] | TIDEWATER 2106 | Diablo | 3.64
[9 empty] | TULUCAY 1101 | North Bay | 0
[9 empty] | UPPER LAKE 1101 | North Coast | 1.1055
[9 empty] | VACA DIXON 1101 | Sacramento | 0.39811
[9 empty] | VACA DIXON 1105 | Sacramento | 33.47
[9 empty] | VACAVILLE 1104 | Sacramento | 14.58
[9 empty] | VARIOUS | Various | 31.8
[9 empty] | VOLTA 1101 | North Valley | 3.461
[9 empty] | WILDWOOD 1101 | North Valley | 8.09
[9 empty] | WYANDOTTE 1103 | North Valley | 76.0708
[9 empty] | WYANDOTTE 1109 | North Valley | 1.9093

## REDACTED's Review
Order | KEEP | Exec. Status | LTIP Condition 1 | LTIP Condition 2 | Priority | Original OH Miles | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | 2018 KPMG CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notif. | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | EASOP Risk Reduced | EASOP NPV ($000) | EASOP RSE | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost | [REDACTED] Comments | In DOT | Scope status | On MPP Workplan | MPP Project year | Comments
35212495 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.65 | 0 | 2020 |  |  | 7.65 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101233716 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.04 | 119985141 | 35212495 | FRRB - AUBERRY 1101 LR233716 | - | - | - | - | [9 empty] | 0 | 0
35212464 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.48 | 0 | 2020 |  |  | 0.48 | 0 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101886282 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793893 | E.5034566.01.07 | 119983588 | 35212464 | FRRB - CALISTOGA 1101 LR 886282 | - | - | - | - | [9 empty] | 0 | 0
35212487 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.82 | 0 | 2020 |  |  | 1.82 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011034 | 80 | 11.1511 | 1566 | 1.9751 | 0.024689 | 1434 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.06 | 119983959 | 35212487 | FRRB - KANAKA 1101 LR1034 | - | - | - | - | [9 empty] | 0 | 0
35212460 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 17.43 | 3 | 2020 |  |  | 14.43 | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 110114605 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.03 | 119983565 | 35212460 | FRRB - RINCON 1101 LR 14605 | - | - | - | - | [9 empty] | 0 | 0
35212466 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.94 | 0.68 | 2020 |  |  | 8.26 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | 147 | 13.8344 | 64 | 57.5327 | 0.39138 | 108 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.02 | 119984990 | 35212466 | FRRB - VACAVILLE 1108 LR 8762 | - | - | - | - | [9 empty] | 0 | 0
35212490 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.44 | 0.72 | 2020 |  |  | 4.72 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 1101323094 | 208 | 36.1569 | 117 | 66.6373 | 0.32037 | 234 | #VALUE! |  |  | FRRB | IGO | Shasta | North Valley | Northern | 5793919 | E.5034573.01.02 | 119984003 | 35212490 | FRRB - GIRVAN 1101 LR323094 | - | - | - | - | [9 empty] | 0 | 0
35212465 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.34 | 0 | 2020 |  |  | 6.34 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | 232 | 15.9209 | 122 | 73.4796 | 0.31672 | 99 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.01 | 119933526 | 35212465 | FRRB - VACAVILLE 1108 LR 38316 | - | - | - | - | [9 empty] | 0 | 0
35212406 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110137384 | 71 | 9.3736 | 557 | 10.17 | 0.14324 | 391 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.06 | 119983061 | 35212406 | FRRB - MONTICELLO 1101 LR 37384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212408 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.58 | 0 | 2020 |  |  | 1.58 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | 205 | 25.7758 | 579 | 27.9958 | 0.13657 | 473 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.08 | 119983069 | 35212408 | FRRB - SILVERADO 2102 LR 34959 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212489 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.16 | -2.24 | 2020 |  |  | 6.4 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 11011330 | 264 | 31.0696 | 624 | 33.0087 | 0.12503 | 651 | #VALUE! |  |  | FRRB | REDDING | Shasta | North Valley | Northern | 5793919 | E.5034573.01.01 | 119933733 | 35212489 | FRRB - GIRVAN 1101 LR1330 | - | - | - | - | [9 empty] | 0 | 0
35212411 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.17 | 0 | 2020 |  |  | 0.17 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104722 | 99 | 7.8964 | 690 | 11.1613 | 0.11274 | 1130 | #VALUE! |  |  | FRRB | DEER PARK | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.11 | 119983147 | 35212411 | FRRB - SILVERADO 2104 LR 722 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212404 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5 | 0 | 2020 |  |  | 5 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101630 | 93 | 18.7154 | 732 | 9.7794 | 0.10515 | 552 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.04 | 119982981 | 35212404 | FRRB - MONTICELLO 1101 LR 630 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35122401 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.31 | 0 | 2020 |  |  | 7.31 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101CB | 5 | 0.53443 | 775 | 0.49137 | 0.098274 | 904 | #VALUE! |  |  | FRRB | STRAWBERRY VALLEY | Yuba | North Valley | Northern | 5793892 | E.5034565.01.01 | 119933522 | 35122401 | FRRB - MONTICELLO 1101 CB | - | - | - | - |  |  |  | 0 |  | 2019-39360 |  |  |  | 0 | 0
35212402 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.42 | 0 | 2020 |  |  | 2.42 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101666 | 90 | 12.0959 | 815 | 8.2843 | 0.092048 | 588 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.02 | 119982885 | 35212402 | FRRB - MONTICELLO 1101 LR 666 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212491 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | 0 | 2020 |  |  | 0.96 | 0 | UNSE | 252531103 | SAN JOAQUIN #3 | SAN JOAQUIN #3 11035100 | 204 | 21.334 | 829 | 18.2004 | 0.089218 | 667 | #VALUE! |  |  | FRRB | NORTH FORK | Madera | Yosemite | Central Valley | 5793920 | E.5034574.01.01 | 119933734 | 35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | - | - | - | - | [9 empty] | 0 | 0
35212479 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7 | 3.84 | 2020 |  |  | 3.16 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.01 | 119933732 | 35212479 | FRRB - BIG BEND 1102 CB | - | - | - | - | [9 empty] | 0 | 0
35212405 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.9 | 0 | 2020 |  |  | 11.9 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110193384 | 101 | 16.1387 | 914 | 7.9369 | 0.078583 | 632 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.05 | 119982987 | 35212405 | FRRB - MONTICELLO 1101 LR 93384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212494 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | 0 | 2020 |  |  | 1.38 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 110137536 | 60 | 5.3994 | 934 | 4.5309 | 0.075515 | 511 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.03 | 119984007 | 35212494 | FRRB - AUBERRY 1101 LR37536 | - | - | - | - | [9 empty] | 0 | 0
35212418 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 13.7 | 0 | 2020 |  |  | 13.7 | 0 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | #VALUE! |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.01 | 119933523 | 35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | - | - | - | - | [9 empty] | 0 | 0
35212481 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.52 | 0.87 | 2020 |  |  | 10.65 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.03 | 119983951 | 35212481 | FRRB - WYANDOTTE 1103 LR1508 | - | - | - | - | [9 empty] | 0 | 0
35212492 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.05 | 0 | 2020 |  |  | 3.05 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R2845 | 172 | 17.8248 | 1209 | 8.1154 | 0.047182 | 811 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.01 | 119933735 | 35212492 | FRRB - AUBERRY 1101 R2845 | - | - | - | - | [9 empty] | 0 | 0
35212403 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.58 | 0 | 2020 |  |  | 3.58 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101654 | 71 | 8.2164 | 1227 | 3.2338 | 0.045547 | 1126 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.03 | 119982889 | 35212403 | FRRB - MONTICELLO 1101 LR 654 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212412 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.13 | -0.58 | 2020 |  |  | 4.71 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 210437632 | 304 | 26.5819 | 1235 | 13.5588 | 0.044601 | 1426 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.12 | 119983231 | 35212412 | FRRB - SILVERADO 2104 LR 37632 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212480 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.12 | 3.74 | 2020 |  |  | 2.38 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.02 | 119983950 | 35212480 | FRRB - BIG BEND 1102 LR1972 | - | - | - | - | [9 empty] | 0 | 0
35212463 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.5 | 0 | 2020 |  |  | 7.5 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103474 | 174 | 18.3351 | 1342 | 6.4055 | 0.036813 | 1399 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.06 | 119983582 | 35212463 | FRRB - RINCON 1103 LR 474 | - | - | - | - | [9 empty] | 0 | 0
35212413 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | -2.25 | 2020 |  |  | 3.63 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.13 | 119983363 | 35212413 | FRRB - SILVERADO 2105 LR 658898 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212496 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.26 | -0.37 | 2020 |  |  | 2.63 | 0 | UNSE | 192411101 | LOW GAP 1101 | LOW GAP 1101CB | 23 | 2.1692 | 1385 | 0.78267 | 0.034029 | 1600 | #VALUE! |  |  | FRRB | ZENIA | Trinity | Humboldt | Northern | 5793922 | E.5034576.01.01 | 119933736 | 35212496 | FRRB - LOW GAP 1101 | - | - | - | - | [9 empty] | 0 | 0
35212471 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.83 | 0 | 2020 |  |  | 1.83 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 | 1508 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.04 | 119983629 | 35212471 | FRRB - POINT MORETTI 1101 LR5076 | - | - | - | - | [9 empty] | 0 | 0
35212473 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.21 | 0 | 2020 |  |  | 2.21 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110210254 | 11 | 2.1441 | 1421 | 0.35552 | 0.03232 | 1814 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.06 | 119983704 | 35212473 | FRRB - BIG BASIN 1102 LR10254 | - | - | - | - | [9 empty] | 0 | 0
35212416 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.252 | 0 | 2020 |  |  | 1.252 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.16 | 119983454 | 35212416 | FRRB - CALISTOGA 1102 LR 634 | - | - | - | - | [9 empty] | 0 | 0
35212486 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 9.46 | 5.02 | 2020 |  |  | 4.44 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.05 | 119983955 | 35212486 | FRRB - KANAKA 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212407 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | -0.19 | 2020 |  |  | 1.15 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 2102636 | 81 | 5.465 | 1550 | 2.0483 | 0.025287 | 1827 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.07 | 119983066 | 35212407 | FRRB - SILVERADO 2102 LR 636 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212462 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.16 | -0.35 | 2020 |  |  | 12.51 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103198 | 62 | 6.4238 | 1618 | 1.3987 | 0.02256 | 1658 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.05 | 119983580 | 35212462 | FRRB - RINCON 1103 LR 198 | - | - | - | - | [9 empty] | 0 | 0
35212417 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.2 | 0.18 | 2020 |  |  | 4.02 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | 160 | 11.021 | 1624 | 3.574 | 0.022338 | 1749 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.17 | 119983463 | 35212417 | FRRB - CALISTOGA 1102 LR 769230 | - | - | - | - | [9 empty] | 0 | 0
35212410 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.41 | 0 | 2020 |  |  | 0.41 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | 61 | 3.7544 | 1648 | 1.292 | 0.02118 | 1771 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.10 | 119983145 | 35212410 | FRRB - SILVERADO 2104 LR 708 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212419 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | 28 | 2.6414 | 1684 | 0.54085 | 0.019316 | 1689 | #VALUE! |  |  | FRRB | KENWOOD | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.02 | 119983560 | 35212419 | FRRB - DUNBAR 1101 - LR 416 | - | - | - | - | [9 empty] | 0 | 0
35212488 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.74 | 0.34 | 2020 |  |  | 4.4 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011406 | 204 | 27.2731 | 1728 | 3.5397 | 0.017352 | 1755 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.07 | 119984001 | 35212488 | FRRB - KANAKA 1101 LR1406 | - | - | - | - | [9 empty] | 0 | 0
35212478 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.99 | 0 | 2020 |  |  | 7.99 | 0 | UNSE | 83392110 | SWIFT 2110 | SWIFT 2110XR332 | 83 | 18.4582 | 1769 | 1.2892 | 0.015532 | 1452 | #VALUE! |  |  | FRRB | LIVERMORE | Santa Clara | San Jose | Central Coast | 5793897 | E.5034571.01.01 | 119933730 | 35212478 | FRRB - SWIFT 2110 XR332 | - | - | - | - | [9 empty] | 0 | 0
35212483 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.53 | 11 | 2020 |  |  | 1.53 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.04 | 119983953 | 35212483 | FRRB - WYANDOTTE 1103 LR1974 | - | - | - | - | [9 empty] | 0 | 0
35212414 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0.24 | 2020 |  |  | 0.98 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105131568 | 57 | 4.1385 | 1947 | 0.58604 | 0.010281 | 2060 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.14 | 119983432 | 35212414 | FRRB - SILVERADO 2105 LR 131568 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212409 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.97 | 0 | 2020 |  |  | 0.97 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104645 | 13 | 1.0111 | 2117 | 0.085285 | 0.0065604 | 2103 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.09 | 119983129 | 35212409 | FRRB - SILVERADO 2104 LR 645 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212415 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.31 | 0 | 2020 |  |  | 2.31 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | 70 | 9.5796 | 2174 | 0.39281 | 0.0056116 | 2203 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.15 | 119983433 | 35212415 | FRRB - SILVERADO 2105 LR 167360 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212467 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0 | 2020 |  |  | 1.22 | 0 | UNSE | 182371111 | LAURELES 1111 | LAURELES 11112020 | 281 | 34.3538 | 2187 | 1.5107 | 0.005376 | 2260 | #VALUE! |  |  | FRRB | CARMEL VALLEY | Monterey | Central Coast | Central Coast | 5793895 | E.5034568.01.01 | 119933604 | 35212467 | FRRB - LAURELES 1111 LR 2020 | - | - | - | - | [9 empty] | 0 | 0
35212469 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.23 | 2.95 | 2020 |  |  | 2.28 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 63 | 6.5695 | 2199 | 0.32133 | 0.0051004 | 2205 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.02 | 119983626 | 35212469 | FRRB - POINT MORETTI 1101 LR12122 | - | - | - | - | [9 empty] | 0 | 0
35212493 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.92 | 3.6 | 2020 |  |  | 5.32 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R324 | 119 | 10.7137 | 2209 | 0.5799 | 0.0048731 | 1904 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.02 | 119984006 | 35212493 | FRRB - AUBERRY 1101 R324 | - | - | - | - | [9 empty] | 0 | 0
35212470 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.77 | 0 | 2020 |  |  | 0.77 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110183716 | 22 | 2.503 | 2210 | 0.10689 | 0.0048588 | 2187 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.03 | 119983627 | 35212470 | FRRB - POINT MORETTI 1101 LR83716 | - | - | - | - | [9 empty] | 0 | 0
35212461 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 1101663641 | 13 | 0.72937 | 2309 | 0.043609 | 0.0033545 | 2307 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.04 | 119983567 | 35212461 | FRRB - RINCON 1101 LR 663641 | - | - | - | - | [9 empty] | 0 | 0
35212474 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.52 | 0 | 2020 |  |  | 0.52 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 70 | 5.982 | 2358 | 0.20629 | 0.002947 | 2611 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.07 | 119983709 | 35212474 | FRRB - BIG BASIN 1102 LR12758 | - | - | - | - | [9 empty] | 0 | 0
35212472 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.51 | 1.37 | 2020 |  |  | 1.14 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | 121 | 13.7481 | 2359 | 0.35169 | 0.0029066 | 2514 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.05 | 119983702 | 35212472 | FRRB - BIG BASIN 1102 LR5066 | - | - | - | - | [9 empty] | 0 | 0
35212475 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.09 | 0 | 2020 |  |  | 3.09 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 1101CB | 45 | 4.6531 | 2398 | 0.11632 | 0.0025849 | 2594 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.08 | 119983868 | 35212475 | FRRB - BIG BASIN 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212477 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.59 | 0 | 2020 |  |  | 0.59 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | 44 | 4.71 | 2435 | 0.10045 | 0.002283 | 2730 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.10 | 119983869 | 35212477 | FRRB - BIG BASIN 1101 LR10720 | - | - | - | - | [9 empty] | 0 | 0
35212468 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.89 | 0 | 2020 |  |  | 0.89 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136516 | 53 | 4.1639 | 2542 | 0.08431 | 0.0015908 | 2704 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.01 | 119933606 | 35212468 | FRRB - POINT MORETTI 1101 LR36516 | - | - | - | - | [9 empty] | 0 | 0
35212476 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.58 | 0 | 2020 |  |  | 2.58 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 11015000 | 23 | 1.9571 | 2579 | 0.031772 | 0.0013814 | 2834 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.09 | 119985051 | 35212476 | FRRB - BIG BASIN 1101 LR5000 | - | - | - | - | [9 empty] | 0 | 0
35192280 | ECOP - Top 20% | 14 | MEET | MEET | 2022003 |  | 1.643 | 1.643 | 2021 |  |  | 0 | 23348.52 | ESTS | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 2.7362 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5792091 | E.5034400.01 | 119556070 | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 PH1 | 0 | 8675 | 0 | 0 | 2020-77593 | 2020-77594 | 14414.4 | 2.73 | 4538638 | 2021-02769 | 0 | 8675 | 0 | 8675 | 1.643 | 3687300 |  |  | 0 | [16 empty] | • Per [REDACTED] email, there will be a request to move this project to 2022 | TRUE | Scoped | TRUE | 2021
35085847 | In-Construction - 2 | 18 | No | No | 2021030 |  | 0.86 | 0.86 | 2021 |  |  | 0 | 78122.49 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 7.6345e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5530169 | P.12006 | 113255606 | 35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 4555 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | [5 empty] | 2020-66516 | 0 | 0 | 4555 | 4555 | 0.86269 | 2900525 | 5126422 | 636.7783 | [6 empty] | • Currently on MPP plan as 2022 job; no open request in DOT to pull forward to 2021 | TRUE | Scoped | TRUE | 2022
35015704 | In-Construction - 2 | 18 | No | No | 2021031 |  | 1 | 1 | 2021 |  |  | 0 | 59156.34 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 8.8773e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5533644 |  | 113255603 | 35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 5300 | 0 | 0 | 0 |  | 2017-105215 | 5300 | 1.0038 | 502000 |  |  |  |  | 0 | 0 | [20 empty] | • Currently on MPP plan as 2022 job; no open request in DOT to pull forward to 2021 | TRUE | Scoped | TRUE | 2022
35219291 | Top 250 Miles | 14 | MEET | No | 2021200 |  | 0.39811 | 0.39811 | 2021 |  |  | 0 | 9258.02 | ESTS | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | 24 | 2.1382 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5543350 | E.5034693.01.01 | 120141627 | 35219291 | CWSP - VACA DIXON 1101126774 | 2102 | 0 | 0 | 0 |  | 2021-01500 | 2112 | 0.4 | 1561600 | 2021-04312 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | • Currently on MPP plan as 2022 job; no open request in DOT to pull forward to 2021 • Notes from previous DOT requests indicate should be 2021 project, however, request did not note 2021 in proper column for this to be added to plan as 2021 job. New DOT request needed to pull forward to 2021 if desired | TRUE | Scoped | TRUE | 2022
35114040 | In-Construction | 20 | No | No | 2022001 | 5.2 | 1.4847 | 1.4847 | 2020 | 0 |  | 0 | 1168946.77 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.043681 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785991 | E.5014745.02 | 117500499 | 35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7839 | 0 | 0 | 0 |  | 2018-49722 | 27456 | 5.2 | 5674800 | 2019-35977 | 0 | 0 | 7188 | 7188 | 1.3614 | 2613818.1818 |  |  | 0 | 2020-20653 | 2020-39428 | 0 | 0 | 7839 | 7839 | 1.4847 | 3107232 | 4232854 | 396.3812 | [6 empty] | • Currently on MPP plan as 2022 job; no open request in DOT to pull forward to 2021 | TRUE | Scoped | TRUE | 2022
35052737 | DSDD | 18 | No | No | 2022002 | 1.97 | 1.5867 | 1.5867 | 2020 | 0 |  | 0 | 106027.53 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.041798 | 12 | Tier 3 | CWSP | LONG BARN | Tuolumne | Yosemite | Central Valley | 5785238 | E.5014733.01 | 114675474 | 35052737 | CWSP-MIWUK 1701-LR8060-PH 1.1 | 8378 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8605 | 8605 | 1.6297 | 3129090.9091 |  |  | 0 | 2019-63683 | 2020-27366 | 0 | 0 | 8378 | 8378 | 1.5867 | 2060222 | 2768676 | 245.9086 | [6 empty] | • Currently on MPP plan as 2022 job; no open request in DOT to pull forward to 2021 | TRUE | Scoped | TRUE | 2022
31361965 | In-Construction - 2 | 20 | No | MEET | 2021028 |  | 0.45 | 0.45 | 2021 |  |  | 0 | 267453.44 | CONS | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | 1845 | 0.068224 | 1151 | Tier 3 | WDDB | KENWOOD | Sonoma | Sonoma | Northern | 5530175 |  | 113751296 | 31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 0 | 2367 | 0 | 0 |  | 2018-69430 | 2300 | 0.43561 | 345000 | N/A |  |  |  | 0 | 0 | 0 |  |  | 0 | 2019-35371 | 2019-34365 | 0 | 0 | 2367 | 2367 | 0.4483 | 797947 | 1245293 | 337.1132 | [6 empty] | • Not on MPP work plan • Request to add to 2021 MPP work plan is in DOT: In Construction Review status | TRUE | Scoped | FALSE | 0
31334291 | In-Construction - 2 | 18 | No | No | 2021029 |  | 0.51 | 0.51 | 2021 |  |  | 0 | 357850.19 | PEND | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | 2061 | 0.01337 | 2292 | Tier 3 | WDDB | FORT BRAGG | Mendocino | Humboldt | Northern | 5530164 |  | 112994395 | 31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 2710 | 0 | 0 | 0 |  | 2018-10393 | 1920 | 0.36364 | 212000 | N/A | 0 | 0 | 2692.8 | 2692.8 | 0.51 | 979200 |  |  |  |  | 2019-31651 | 0 | 0 | 2710 | 2710 | 0.51326 | 688000 | 1115000 | 253.8745 |  | 2019-19275 |  |  |  |  | • Not on MPP work plan • Request to add to 2021 MPP work plan is in DOT: In Construction Review status | TRUE | Scoped | FALSE | 0
35235320 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021150 |  | 10 | 10 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 3.6389 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.23 | 120582839 | 35235320 | FRRB - WYANDOTTE 1103 - W3 PH 3 | 0 | 52800 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan | FALSE | Scoped | FALSE | 0
35235669 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021151 |  | 10.2 | 10.2 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 3.7117 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.24 | 120594870 | 35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4 | 0 | 53856 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan | TRUE | Scoped | FALSE | 0
35235670 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021152 |  | 3.91 | 3.91 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.7729 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.25 | 120594871 | 35235670 | FRRB - WYANDOTTE 1103 - W5 PH 5 | 0 | 20645 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan• NCF rebuild related ( [REDACTED] should be handling the change request) | TRUE | Scoped | FALSE | 0
35235671 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021153 |  | 4.49 | 4.49 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 2.0358 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.26 | 120594872 | 35235671 | FRRB - WYANDOTTE 1103 - W6 PH 6 | 0 | 23707 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan• NCF rebuild related ( [REDACTED] should be handling the change request) | TRUE | Scoped | FALSE | 0
35235672 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021154 |  | 1.64 | 1.64 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 0.74359 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.27 | 120594873 | 35235672 | FRRB - WYANDOTTE 1103 - W7 PH 7 | 0 | 8659 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan• NCF rebuild related ( [REDACTED] should be handling the change request) | TRUE | Scoped | FALSE | 0
35235673 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021155 |  | 2.14 | 2.14 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 0.97031 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.28 | 120594874 | 35235673 | FRRB - WYANDOTTE 1103 - W8 PH 8 | 0 | 11299 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan• NCF rebuild related ( [REDACTED] should be handling the change request) | TRUE | Scoped | FALSE | 0
35233166 | FRRB - UG - 2021 | 14 | MEET | No | 2021306 |  | 0 |  | 2021 |  |  | 0 |  | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.04 | 120541098 | 35233166 | FRRB - Big Bend 11021972 - B4 | 0 | 0 | 0 | 0 | [31 empty] | • Not on MPP work plan, and no request in DOT to add to work plan | TRUE | Scoped | FALSE | 0
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021113 |  | 2.56 | 2.56 | 2021 |  |  | 0 | -679894.08 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.54034 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 13516.8 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | • Order is on MPP work plan, but under 95A for 2020 • No request in DOT to add to 2021 work plan • FYI, order appears twice on the project list | TRUE | Scoped | FALSE | 0
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021114 |  | 4.8 | 4.8 | 2021 |  |  | 0 | -179287.42 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.6177 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 25344 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | • Order is on MPP work plan, but under 95B for 2020 • No request in DOT to add to 2021 work plan • FYI, order appears twice on the project list | TRUE | Scoped | FALSE | 0
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021115 |  | 6.72 | 6.72 | 2021 |  |  | 0 | -679894.08 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.9082 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 35481.6 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | Duplicate order | TRUE | Scoped | FALSE | 0
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021116 |  | 7.25 | 7.25 | 2021 |  |  | 0 | -179287.42 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 3.2873 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 38280 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | Duplicate order | TRUE | Scoped | FALSE | 0
74022384 | In-Construction | 20 | MEET | No | 2021001 | 5.6 | 5.4458 | 4.4858 | 2020 | 0.96 |  | 0.96 | 7133317.26 | CONS | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | 799 | 4.7409 | 209 | Tier 3 | PRE | GEYSERVILLE | Sonoma | Sonoma | Northern | 5782860 | E.5015487.01 | 114753320 | 74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 28754 | 0 | 0 | 0 |  | 2018-55406 | 29568 | 5.6 | 5959500 | N/A | 0 | 0 | 29040 | 29040 | 5.5 | 10560000 |  |  | 0 | 2019-34744 | 2019-02348 | 0 | 0 | 28754 | 28754 | 5.4458 | [10 empty] | TRUE | Scoped | TRUE | 2021
35157845 | In-Construction | 20 | No | No | 2021002 | 1.27 | 1.2676 | 1.2676 | 2020 | 0 |  | 0 | 431041.62 | CONS | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | 0.24713 | 104 | Tier 2 | WDDB | SAINT HELENA | Napa | North Bay | Bay Area | 5784869 | E.5014317.04 | 116952175 | 35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 6693 | 0 | 0 | 0 |  | N/A |  |  |  | N/A | 0 | 0 | 6705.6 | 6705.6 | 1.27 | 2438400 |  |  | 0 | 2020-03939 | 2020-42595 | 0 | 0 | 6693 | 6693 | 1.2676 | 1404334 | 1800634 | 209.8213 | [7 empty] | TRUE | Scoped | TRUE | 2021
35119965 | In-Construction | 18 | No | No | 2021003 | 0.87 | 0.84905 | 0.84905 | 2020 | 0 |  | 0 | 764949.39 | PEND | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.072413 | 841 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786602 | E.5014534.05 | 117721840 | 35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 4483 | 0 | 0 | 0 |  | 2018-31656 | 8077 | 1.5297 | 903333 | 2018-53540 | 0 | 0 | 1584 | 1584 | 0.3 | 576000 |  |  | 0 | 2019-78779 | 2020-24016 | 4483 | 0 | 4483 | 4483 | 0.84905 | 1435425 | 1924210 | 320.193 | [7 empty] | TRUE | Scoped | TRUE | 2021
35094397 | In-Construction | 20 | No | No | 2021004 | 0.87 | 1.0646 | 1.0646 | 2020 | 0 |  | 0 | 1301754.83 | DOCC | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.076193 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785167 | E.5015029.11 | 117131100 | 35094397 | CWSP-KONOCTI 1102-LR 532-PH10 | 5621 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 |  |  | 0 | 2019-62948 | 2020-36368 | 0 | 0 | 5621 | 5621 | 1.0646 | 1438986 | 1733017 | 256.0018 | [7 empty] | TRUE | Scoped | TRUE | 2021
35061206 | In-Construction | 20 | No | No | 2021005 | 1.966 | 1.7652 | 1.7652 | 2020 | 0 |  | 0 | 2046932.97 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.076892 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783070 | E.5015569.01 | 115106231 | 35061206 | CWSP-BRUNSWICK 1103-LR50070-PH 1.1 | 9320 | 0 | 0 | 0 |  | 2018-85016 | 10380.48 | 1.966 | 2108720 | 2019-76345 | 0 | 0 | 9320 | 9320 | 1.7652 | 3389090.9091 |  |  | 0 | 2020-03978 | 2020-30766 | 0 | 0 | 9320 | 9320 | 1.7652 | 3459498 | 4711641 | 371.1908 | [7 empty] | TRUE | Scoped | TRUE | 2021
35117443 | In-Construction | 20 | No | No | 2021006 | 1.543 | 2.1581 | 2.1581 | 2020 | 0 |  | 0 | 2018722.86 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.094012 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5786518 | E.5015567.06 | 117634567 | 35117443 | CWSP-BRUNSWICK 1103-LR50070-PH 3.6 | 11395 | 0 | 0 | 0 |  | 2018-85051 | 8147.04 | 1.543 | 1630650 | 2019-76353 | 0 | 0 | 11395 | 11395 | 2.1581 | 4143636.3636 |  |  | 0 | 2020-32576 | 2020-42958 | 0 | 0 | 11395 | 11395 | 2.1581 | 4475708 | 5778810 | 392.7782 | [7 empty] | TRUE | Scoped | TRUE | 2021
35061212 | In-Construction | 20 | No | No | 2021007 | 9 | 1.7888 | 1.7888 | 2020 | 0 |  | 0 | 1548567.12 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.077924 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783071 | E.5015568.01 | 115106486 | 35061212 | CWSP-BRUNSWICK 1103-LR50070-PH 2.1 | 9445 | 0 | 0 | 0 |  | 2018-85027 | 47520 | 9 | 9533800 | 2019-76348 | 0 | 0 | 9445 | 9445 | 1.7888 | 3434545.4545 |  |  | 0 | 2020-06702 | 2020-46891 | 0 | 0 | 9445 | 9445 | 1.7888 | 3890031 | 4913095 | 411.8614 |  | 2020-04589 | [5 empty] | TRUE | Scoped | TRUE | 2021
35115151 | In-Construction | 20 | No | No | 2021008 | 2.25 | 1.8964 | 1.8964 | 2020 | 0 |  | 0 | 1293779.94 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.08261 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785721 | E.5015568.02 | 117493857 | 35115151 | CWSP-BRUNSWICK 1103-LR50070-PH 2.2 | 10013 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 | 0 | 0 | 10013 | 10013 | 1.8964 | 3641090.9091 |  |  | 0 | 2020-23454 | 2020-46448 | 0 | 0 | 10013 | 10013 | 1.8964 | 4025667 | 5273989 | 402.044 |  | 2020-38642 | [5 empty] | TRUE | Scoped | TRUE | 2021
35115152 | In-Construction - 2 | 20 | No | No | 2021009 |  | 1.57 | 1.57 | 2021 |  |  | 0 | 444280.95 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.068391 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785722 | E.5015568.03 | 117495855 | 35115152 | CWSP-BRUNSWICK 1103-LR50070-PH 2.3 | 8271 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 |  |  |  | 0 | 0 | 0 |  |  |  | 2020-55781 | 2020-58697 | 0 | 0 | 8271 | 8271 | 1.5665 | 2679486 | 3591121 | 323.9616 | [7 empty] | TRUE | Scoped | TRUE | 2021 | Tagged as "Remove" in DOT
35116383 | In-Construction | 20 | No | No | 2021010 | 1.97 | 1.3862 | 1.3862 | 2020 | 0 |  | 0 | 991398.25 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.036514 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785966 | E.5014733.02 | 117604600 | 35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 7319 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 7080 | 7080 | 1.3409 | 2574545.4545 |  |  | 0 | 2019-60218 | 2020-25651 | 0 | 0 | 7319 | 7319 | 1.3862 | 2547023 | 3758449 | 348.0015 | [7 empty] | TRUE | Scoped | TRUE | 2021 | Tagged as "Remove" in DOT
35116384 | In-Construction | 20 | No | No | 2021011 | 1.97 | 1.8371 | 1.6671 | 2020 | 0.17 |  | 0.17 | 121782.96 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.048393 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785967 | E.5014733.03 | 117604604 | 35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 9700 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 9715 | 9715 | 1.84 | 3532727.2727 |  |  | 0 | 2020-00930 | 2020-48509 | 0 | 0 | 9700 | 9700 | 1.8371 | 3239382 | 4624169 | 333.9569 | [7 empty] | TRUE | Scoped | TRUE | 2021
35114048 | In-Construction | 20 | No | No | 2021012 | 15.9024 | 1.3909 | 1.3909 | 2020 | 0 |  | 0 | 889880.15 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.040923 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785997 | E.5014742.03 | 117499466 | 35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7344 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7382 | 7382 | 1.3981 | 2684363.6364 |  |  | 0 | 2019-73207 | 2020-43723 | 0 | 0 | 7344 | 7344 | 1.3909 | 3133899 | 4178929 | 426.7292 | [7 empty] | TRUE | Scoped | TRUE | 2021
35114051 | In-Construction - 2 | 20 | No | No | 2021013 |  | 1.44 | 1.44 | 2021 |  |  | 0 | 558652.57 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.042367 | 2 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786000 | E.5014742.06 | 117502234 | 35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 7698 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7628 | 7628 | 1.4447 | 2773818.1818 |  |  |  | 2019-72313 | 2020-47316 | 0 | 0 | 7698 | 7698 | 1.458 | 3949678 | 5342998 | 513.0785 | [7 empty] | TRUE | Scoped | TRUE | 2021
35115054 | In-Construction | 20 | No | No | 2021014 | 1.96 | 1.4259 | 1.3959 | 2020 | 0.03 |  | 0.03 | 1016834.07 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.030421 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785986 | E.5015427.02 | 117490035 | 35115054 | CWSP-MIWUK 1701-OCB-PH 2.2 | 7529 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 7255 | 7255 | 1.3741 | 2638181.8182 |  |  | 0 | 2019-53298 | 2020-44293 | 0 | 0 | 7529 | 7529 | 1.4259 | 2482662 | 3789178 | 329.7466 | [7 empty] | TRUE | Scoped | TRUE | 2021
35115050 | In-Construction | 20 | No | No | 2021015 | 2.304 | 1.6121 | 1.6121 | 2020 | 0 |  | 0 | 875800.67 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.034393 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785972 | E.5014771.02 | 117495948 | 35115050 | CWSP-MIWUK 1701–OCB-PH 1.2 | 8512 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 8270 | 8270 | 1.5663 | 3007272.7273 |  |  | 0 | 2019-79491 | 2020-40482 | 0 | 0 | 8512 | 8512 | 1.6121 | 2809593 | 4091239 | 330.0744 | [7 empty] | TRUE | Scoped | TRUE | 2021
35115055 | In-Construction | 20 | No | No | 2021016 | 1.96 | 2.1343 | 2.1343 | 2020 | 0 |  | 0 | 952089.56 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.045533 | 2 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785987 | E.5015427.03 | 117490481 | 35115055 | CWSP-MIWUK 1701-OCB-PH 2.3 | 11269 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 11088 | 11088 | 2.1 | 4032000 |  |  | 0 | 2019-68750 | 2020-34644 | 0 | 0 | 11269 | 11269 | 2.1343 | 2901359 | 3784068 | 257.4638 | [7 empty] | TRUE | Scoped | TRUE | 2021
35115053 | In-Construction | 20 | No | No | 2021017 | 2.304 | 1.7203 | 1.7203 | 2020 | 0 |  | 0 | 634368.78 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.036701 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785975 | E.5014771.05 | 117496041 | 35115053 | CWSP-MIWUK 1701–OCB-PH 1.5 | 9083 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9571 | 9571 | 1.8127 | 3480363.6364 |  |  | 0 | 2020-56266 | 2020-27365 | 0 | 0 | 9083 | 9083 | 1.7203 | 1670418 | 2296559 | 183.906 | [7 empty] | TRUE | Scoped | TRUE | 2021
35052821 | In-Construction | 20 | No | No | 2021018 | 2.304 | 2.0744 | 2.0744 | 2020 | 0 |  | 0 | 611371.23 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.044256 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5784646 | E.5014771.01 | 114593976 | 35052821 | CWSP-MIWUK 1701–OCB-PH 1.1 | 10953 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9750 | 9750 | 1.8466 | 3545454.5455 |  |  | 0 | 2019-52652 | 2020-46847 | 0 | 0 | 10953 | 10953 | 2.0744 | 3322975 | 4765282 | 303.3849 | [7 empty] | TRUE | Scoped | TRUE | 2021
35056746 | In-Construction | 20 | No | No | 2021019 | 1.96 | 2.0335 | 2.0335 | 2020 | 0 |  | 0 | 372655.58 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.043384 | 2 | Tier 3 | PRE | MI WUK VLG | Tuolumne | Yosemite | Central Valley | 5782537 | E.5015427.01 | 114996821 | 35056746 | CWSP-MIWUK 1701-OCB-PH 2.1 | 10737 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 10615 | 10615 | 2.0104 | 3860000 |  |  | 0 | 2019-65579 | 2020-47773 | 0 | 0 | 10737 | 10737 | 2.0335 | 2950902 | 3642331 | 274.8349 | [7 empty] | TRUE | Scoped | TRUE | 2021
35116391 | In-Construction | 20 | No | No | 2021020 | 2.04 | 2.0902 | 0.71015 | 2020 | 1.38 |  | 1.38 | 1688016.64 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.044332 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785976 | E.5014773.02 | 117605551 | 35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 11036 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 10840 | 10840 | 2.053 | 3941818.1818 |  |  | 0 | 2019-64313 | 2020-18345 | 0 | 0 | 11036 | 11036 | 2.0902 | 3920204 | 5835429 | 355.2196 | [7 empty] | TRUE | Scoped | TRUE | 2021
35192284 | ECOP - Top 20% | 13 | MEET | MEET | 2021040 |  | 1.086 | 1.086 | 2021 |  |  | 0 | 15071.45 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.0802 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5792107 | E.5034416.01 | 119556691 | 35192284 | ECOP - SILVERADO 2104 - H05-LR726 PH1 | 0 | 5734 | 0 | 0 |  | 2020-77337 | 5734 | 1.09 | 6664630 | 2021-00327 | 0 | 5734 | 0 | 5734 | 1.086 | 4505396 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35223024 | ECOP - Top 20% | 13 | MEET | MEET | 2021041 |  | 1.2659 | 1.2659 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.4248 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.01 | 120245076 | 35223024 | ECOP - SILVERADO 2104 - H05-LR726 PH2 | 0 | 6684 | 0 | 0 |  | 2020-77337 | 6684 | 1.27 | 0 | 2021-00327 | 0 | 6684 | 0 | 6684 | 1.2659 | 4738320 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35223026 | ECOP - Top 20% | 13 | MEET | No | 2021042 |  | 1.0348 | 1.0348 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.2414 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.02 | 120245190 | 35223026 | ECOP - SILVERADO 2104 - H05-LR726 PH3 | 5464 | 0 | 0 | 0 |  | 2020-77337 | 5464 | 1.03 | 0 | 2021-00327 | 0 | 0 | 5464 | 5464 | 1.0348 | 3702224 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35116395 | In-Construction | 20 | No | No | 2021021 | 2.04 | 1.7106 | 1.7106 | 2020 | 0 |  | 0 | 804930.72 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.036282 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785979 | E.5014773.05 | 117605558 | 35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 9032 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 7500 | 7500 | 1.4205 | 2727272.7273 |  |  | 0 | 2019-57777 | 2020-44284 | 0 | 0 | 9032 | 9032 | 1.7106 | 2479935 | 3714853 | 274.5721 | [7 empty] | TRUE | Scoped | TRUE | 2021
35223028 | ECOP - Top 20% | 13 | MEET | No | 2021044 |  | 1.208 | 1.208 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.4491 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.04 | 120245193 | 35223028 | ECOP - SILVERADO 2104 - H05-LR726 PH5 | 6378 | 0 | 0 | 0 |  | 2020-77337 | 6378 | 1.21 | 0 | 2021-00327 | 0 | 0 | 6378 | 6378 | 1.208 | 1330059 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35116800 | In-Construction | 20 | No | No | 2021022 | 1.78 | 1.4252 | 1.1752 | 2020 | 0.25 |  | 0.25 | 1284948.37 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.025962 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785961 | E.5014730.02 | 117605265 | 35116800 | CWSP-MIWUK 1702-LR 6018-PH1.2 | 7525 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 6695 | 6695 | 1.268 | 2434545.4545 |  |  | 0 | 2020-45856 | 2020-18449 | 0 | 0 | 7525 | 7525 | 1.4252 | 2704457 | 4030625 | 359.3963 | [7 empty] | TRUE | Scoped | TRUE | 2021
35192281 | ECOP - Top 20% | 13 | MEET | No | 2021046 |  | 0.30663 | 0.30663 | 2021 |  |  | 0 | 19203.82 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.3133 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792097 | E.5034406.01 | 119556250 | 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.1 | 1619 | 0 | 0 | 0 | 2020-78060 | 2020-78081 | 31363.2 | 5.94 | 8593932 | 2021-04756 | 0 | 0 | 1619 | 1619 | 0.30663 | 344842 | 14.37 | 51800 | 3604.7321 | [17 empty] | TRUE | In Scoping |  | 2021
35227027 | ECOP - Top 20% | 13 | MEET | No | 2021047 |  | 0.97576 | 0.97576 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.997 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.26 | 120449717 | 35227027 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.2 | 5152 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5152 | 5152 | 0.97576 | 1065537 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227028 | ECOP - Top 20% | 13 | MEET | No | 2021048 |  | 0.61723 | 0.61723 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.63067 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.27 | 120449719 | 35227028 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.3 | 3259 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 3259 | 3259 | 0.61723 | 684026 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227029 | ECOP - Top 20% | 13 | MEET | No | 2021049 |  | 1.0886 | 1.0886 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.1123 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.28 | 120449800 | 35227029 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.4 | 5748 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5748 | 5748 | 1.0886 | 1198801 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35236437 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.34 | 0.34 |  |  |  | 0 |  | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.55472 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.35 | 120617837 | 35236437 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.7 | 0 | 1795.2 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35236438 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.48 | 0.48 |  |  |  | 0 |  | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.78314 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.36 | 120617839 | 35236438 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.8 | 0 | 2534.4 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35226622 | ECOP - Top 20% | 13 | MEET | No | 2021050 |  | 0.87841 | 0.87841 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.89753 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.02 | 120445225 | 35226622 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.3 | 4638 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 4638 | 4638 | 0.87841 | 1129975 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226623 | ECOP - Top 20% | 13 | MEET | No | 2021051 |  | 1.2953 | 1.2953 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.3235 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.03 | 120445227 | 35226623 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.4 | 6839 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 6839 | 6839 | 1.2953 | 1454442 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226624 | ECOP - Top 20% | 13 | MEET | No | 2021052 |  | 0.70795 | 0.70795 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.72337 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.04 | 120445228 | 35226624 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.5 | 3738 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 3738 | 3738 | 0.70795 | 783093 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35225595 | ECOP - Top 20% | 13 | MEET | No | 2021053 |  | 0.87803 | 0.87803 | 2021 |  |  | 0 | 869.34 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.64201 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.02 | 120424186 | 35225595 | ECOP - FULTON 1107 - H02-LR604 Ph 1.3 | 4636 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4636 | 4636 | 0.87803 | 2648900 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35114100 | In-Construction | 20 | No | No | 2021023 | 1.61 | 1.0392 | 1.0392 | 2020 | 0 |  | 0 | 413706 | CONS | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.016816 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5786131 | E.5015489.02 | 117545617 | 35114100 | CWSP-CAMP EVERS 2106-LR5020-PH2.2 | 5487 | 0 | 0 | 0 |  | 2018-64516 | 8500.8 | 1.61 | 1747200 | N/A | 0 | 0 | 5491.2 | 5491.2 | 1.04 | 1996800 |  |  | 0 | 2019-82353 | 2020-34359 | 0 | 0 | 5487 | 5487 | 1.0392 | 2119397 | 2502285 | 386.2579 | [7 empty] | TRUE | Scoped | TRUE | 2021
35116442 | In-Construction | 20 | No | No | 2021024 | 1.85 | 2.3458 | 0.55583 | 2020 | 1.79 |  | 1.79 | 1951346.75 | DOCC | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.013106 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785982 | E.5014776.03 | 117605169 | 35116442 | CWSP-MIWUK 1702-LR38218-PH1.3 | 12386 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 11065 | 11065 | 2.0956 | 4023636.3636 |  |  | 0 | 2020-11921 | 2020-34785 | 0 | 0 | 12386 | 12386 | 2.3458 | 2994831 | 3849738 | 241.7916 | [7 empty] | TRUE | Scoped | TRUE | 2021
35174479 | ECOP - Top 20% | 13 | MEET | No | 2021056 |  | 0.72159 | 0.72159 | 2021 |  |  | 0 | 21891.62 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.77515 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790119 | E.5033918.01 | 118913025 | 35174479 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.1 | 3810 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 48840 | 9.25 | 13481516 | 2021-04464 | 0 | 0 | 3810 | 3810 | 0.72159 | 20851272.7273 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226863 | ECOP - Top 20% | 13 | MEET | No | 2021057 |  | 0.52765 | 0.52765 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.56681 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.06 | 120449205 | 35226863 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.2 | 2786 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2786 | 2786 | 0.52765 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226864 | ECOP - Top 20% | 13 | MEET | No | 2021058 |  | 0.32652 | 0.32652 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.35075 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.07 | 120449207 | 35226864 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.3 | 1724 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1724 | 1724 | 0.32652 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226865 | ECOP - Top 20% | 13 | MEET | No | 2021059 |  | 0.23542 | 0.23542 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.25289 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.08 | 120449208 | 35226865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.4 | 1243 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 |  | 0 | 1243 | 1243 | 0.23542 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226866 | ECOP - Top 20% | 13 | MEET | No | 2021060 |  | 0.51818 | 0.51818 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.55664 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.09 | 120449230 | 35226866 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.5 | 2736 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2736 | 2736 | 0.51818 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226870 | ECOP - Top 20% | 13 | MEET | No | 2021061 |  | 0.41951 | 0.41951 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.45064 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.10 | 120449231 | 35226870 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.6 | 2215 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2215 | 2215 | 0.41951 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226871 | ECOP - Top 20% | 13 | MEET | MEET | 2021062 |  | 1.9117 | 1.9117 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.2398 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.11 | 120449235 | 35226871 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.7 | 420 | 6124 | 3550 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 3205 | 6124 | 420 | 9749 | 1.8464 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226872 | ECOP - Top 20% | 13 | MEET | MEET | 2021063 |  | 1.4881 | 1.4881 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.4242 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.12 | 120449236 | 35226872 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.8 | 1168 | 2552 | 4137 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 2328 | 2552 | 1168 | 6048 | 1.1455 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226873 | ECOP - Top 20% | 13 | MEET | No | 2021064 |  | 1.0394 | 1.0394 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.7829 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.13 | 120449450 | 35226873 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.9 | 0 | 0 | 0 | 5488 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 4734 | 0 | 0 | 4734 | 0.89659 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226878 | ECOP - Top 20% | 13 | MEET | MEET | 2021065 |  | 0.58883 | 0.58883 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.01 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.14 | 120449453 | 35226878 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.10 | 0 | 3109 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3034 | 3034 | 0.57462 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227001 | ECOP - Top 20% | 13 | MEET | MEET | 2021066 |  | 0.7214 | 0.7214 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2374 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.15 | 120449454 | 35227001 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.11 | 0 | 3809 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3591 | 3591 | 0.68011 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227002 | ECOP - Top 20% | 13 | MEET | MEET | 2021067 |  | 0.43295 | 0.43295 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.74264 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.16 | 120449455 | 35227002 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.12 | 0 | 2286 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2286 | 2286 | 0.43295 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227003 | ECOP - Top 20% | 13 | MEET | MEET | 2021068 |  | 0.58087 | 0.58087 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99636 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.17 | 120449456 | 35227003 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.13 | 0 | 3067 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3067 | 3067 | 0.58087 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227004 | ECOP - Top 20% | 13 | MEET | MEET | 2021069 |  | 0.3483 | 0.3483 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.59743 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.18 | 120449457 | 35227004 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.14 | 0 | 1839 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1763 | 1763 | 0.3339 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35236439 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 1.12 | 1.12 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9211 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.37 | 120617881 | 35236439 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.15 | 0 | 5913.6 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35236660 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.48 | 0.48 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.82334 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.38 | 120617882 | 35236660 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.16 | 0 | 2534.4 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35116444 | In-Construction | 20 | No | No | 2021025 | 1.85 | 2.1023 | 2.1023 | 2020 | 0 |  | 0 | 775814.94 | CONS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.011746 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785984 | E.5014776.05 | 117605182 | 35116444 | CWSP-MIWUK 1702-LR38218-PH1.5 | 11100 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 9600 | 9600 | 1.8182 | 3490909.0909 |  |  | 0 | 2019-57736 | 2020-27703 | 0 | 0 | 11100 | 11100 | 2.1023 | 2648178 | 3531134 | 238.5746 | [7 empty] | TRUE | Scoped | TRUE | 2021
35052825 | In-Construction | 20 | No | No | 2021026 | 1.95 | 1.1682 | 1.1682 | 2020 | 0 |  | 0 | 472917.86 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | 2641 | 0.0050323 | 26 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785221 | E.5014722.01 | 114701195 | 35052825 | CWSP-MIWUK 1702-LR 8090-PH 1.1 | 6168 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 5785 | 5785 | 1.0956 | 2103636.3636 |  |  | 0 | 2019-54146 | 2020-43899 | 0 | 0 | 6168 | 6168 | 1.1682 | 2342292 | 3544410 | 379.749 | [7 empty] | TRUE | Scoped | TRUE | 2021
35192290 | ECOP | 13 | No | No | 2021072 |  | 5.0004 | 5.0004 | 2021 |  |  | 0 | 11659.49 | ESTS | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 3.5024 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792092 | E.5034401.01 | 119556075 | 35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 26402 | 0 | 0 | 0 |  | 2020-66261 | 26400 | 5 | 5575214 | 2021-04162 | 0 | 0 | 26402 | 26402 | 5.0004 | 5633062 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35116515 | In-Construction - 2 | 19 | No | No | 2021027 |  | 1.75 | 1.75 | 2021 |  |  | 0 | 152800.55 | UNSC | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.035578 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786036 | E.5015701.02 | 117607998 | 35116515 | CWSP–STANISLAUS 1702-LR1888-PH 1.2 | 9222 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 8765 | 8765 | 1.66 | 3187272.7273 |  |  |  | 2019-69359 | 2020-48497 | 0 | 0 | 9222 | 9222 | 1.7466 | 3203035 | 4438411 | 347.3254 | [7 empty] | TRUE | Scoped | TRUE | 2021
35231544 | Top 50 Miles | 13 | MEET | No | 2021074 | 1.2 | 1.2 | 1.2 | 2021 |  |  | 0 | 0 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 3.9785 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.03 | 120504131 | 35231544 | CWSP - TIDEWATER 210614072 PH 3 | 6336 | 0 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 0 | 6336 | 6336 | 1.2 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226627 | Top 50 Miles | 13 | MEET | No | 2021075 | 0.29 | 0.31231 | 0.31231 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 1.2699 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.02 | 120445375 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 2 | 1649 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226630 | Top 50 Miles | 13 | MEET | No | 2021076 | 1.44 | 1.4061 | 1.4061 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.7171 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.05 | 120445421 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 5 | 7424 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226631 | Top 50 Miles | 13 | MEET | No | 2021077 | 1.54 | 1.5326 | 1.5326 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 6.2315 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.06 | 120445423 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 6 | 8092 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35052731 | DSDD | 19 | No | No | 2021032 | 2.43 | 1.4733 | 1.4733 | 2020 | 0 |  | 0 | 148877.35 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.02488 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5782530 | E.5014542.01 | 114607365 | 35052731 | CWSP-BIG BASIN 1101-LR10296-PH 1.1 | 7779 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2020-46872 | 2020-54946 | 0 | 0 | 7779 | 7779 | 1.4733 | 3391041 | 4994628 | 435.9225 | [7 empty] | TRUE | Scoped | TRUE | 2021
35227860 | Top 50 Miles | 13 | MEET | No | 2021079 |  | 0.19583 | 0.19583 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.66472 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.07 | 120462186 | 35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 1034 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 1034 | 1034 | 0.19583 | 223852 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227861 | Top 50 Miles | 13 | MEET | No | 2021080 |  | 1.5339 | 1.5339 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.2066 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.08 | 120462188 | 35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 8099 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 8099 | 8099 | 1.5339 | 1685035 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227862 | Top 50 Miles | 13 | MEET | No | 2021081 |  | 0.93466 | 0.93466 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.1725 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.09 | 120462232 | 35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 4935 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4935 | 4935 | 0.93466 | 1020657 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227863 | Top 50 Miles | 13 | MEET | No | 2021082 |  | 0.79129 | 0.79129 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.6859 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.10 | 120462233 | 35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 4178 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4178 | 4178 | 0.79129 | 874094 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227866 | Top 50 Miles | 13 | MEET | No | 2021083 |  | 0.52386 | 0.52386 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.12 | 120462238 | 35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 2766 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2766 | 2766 | 0.52386 | 592064 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227867 | Top 50 Miles | 13 | MEET | No | 2021084 |  | 0.99527 | 0.99527 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.3782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.13 | 120462241 | 35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 5255 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 5255 | 5255 | 0.99527 | 1116839 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227868 | Top 50 Miles | 13 | MEET | No | 2021085 |  | 0.51686 | 0.51686 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7544 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.14 | 120462242 | 35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 2729 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2729 | 2729 | 0.51686 | 584412 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35228187 | Top 50 Miles | 13 | MEET | No | 2021086 |  | 0.62879 | 0.62879 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.1343 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.16 | 120475324 | 35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | 3320 | 0 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 0 | 3320 | 3320 | 0.62879 | 733000 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35228188 | Top 50 Miles | 13 | MEET | MEET | 2021087 |  | 3.73 | 3.73 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 20.4207 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.17 | 120475326 | 35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | 0 | 0 | 19694.4 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 19694 | 0 | 0 | 19694 | 3.7299 | 667600 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35236661 | Top 50 Miles | 13 |  |  |  |  | 0.22 | 0.22 |  |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.74675 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.18 | 120617883 | 35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | 1161.6 | 0 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35222045 | Top 50 Miles | 13 | MEET | No | 2021088 |  | 0.88864 | 0.88864 | 2021 |  |  | 0 | 5980.16 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.0163 |  |  | CWSP | MIDDLETOWN | Napa | Humboldt | Northern | 5794898 | E.5034741.01.01 | 120233319 | 35222045 | CWSP - MIDDLETOWN 1103 LR 830 PH4 | 4692 | 0 | 0 | 0 | N/A | 2020-87784 | 3907.2 | 0.74 | 808000 | 2021-03692 | 0 | 0 | 4692 | 4692 | 0.88864 | 970399 | 3.02 | 2500 | 827.8146 | [17 empty] | TRUE | In Scoping |  | 0
35145540 | PSPS - Scoped | 18 | MEET | MEET | 2021033 | 0.5 | 1.2739 | 1.2739 | 2020 | 0 |  | 0 | 217190.06 | PEND | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | 1692 | 1.602 | 3052 | Tier 3 | PSPS | Angels | Calaveras | Stockton | Central Valley | 5788779 | E.5025634 | 118259180 | 35145540 | PSPS – Frogtown 1702 – CB | 0 | 2272 | 4454 | 0 |  | 2019-80603 | 2640 | 0.5 | 3900000 | N/A | 4454 | 2272 | 0 | 6726 | 1.2739 | 2100000 |  |  | 0 | 2020-42690 | [16 empty] | TRUE | Scoped | TRUE | 2021
35094513 | DSDD | 18 | No | No | 2021034 | 1.54 | 1.9112 | 1.9112 | 2020 | 0 |  | 0 | 192432.87 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.0098421 | 19 | Tier 3 | CWSP | ARNOLD | Calaveras | Stockton | Central Valley | 5785245 | E.5014540.01 | 114567769 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10091 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 10091 | 10091 | 1.9112 | 3669454.5455 |  |  | 0 | 2020-43006 | 2021-08435 | [15 empty] | TRUE | Scoped | TRUE | 2021
35145525 | PSPS - Scoped | 18 | MEET | MEET | 2021035 | 1.78 | 1.78 | 1.78 | 2020 | 0 |  | 0 | 156085.26 | PEND | 43321104 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | 2944 | 0.00046978 | 1522 | Tier 2 | PSPS | Santa Rosa | Sonoma | Sonoma | Northern | 5788787 | E.5025638.01 | 118266592 | 35145525 | PSPS - Rincon 1102 and 1104 - CB | 0 | 9398.4 | 0 | 0 |  | 2019-82382 | 9398.4 | 1.78 | 17891818 | N/A | 0 | 9398.4 | 0 | 9398.4 | 1.78 | 7476000 |  |  | 0 | 2020-50683 | [10 empty] | 2020-28718 | [5 empty] | TRUE | Scoped | TRUE | 2021
35231609 | Top 20% MAVF CPZ | 13 | MEET | No | 2021092 | 1.3299 | 1.3301 | 1.3301 | 2021 |  |  | 0 | 0 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.1292 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.13 | 120504096 | 35231609 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 7023 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7022 | 7022 | 1.3299 | 2069042.1649 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35145524 | PSPS - Scoped | 18 | MEET | MEET | 2021036 | 1.5 | 1.5 | 1.5 | 2020 | 0 |  | 0 | 170611.65 | PEND | 43321103 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | 2033 | 0.41019 | 628 | Tier 3 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5788786 | E.5025637 | 118266591 | 35145524 | PSPS - Rincon 1101 and 1103- CB | 0 | 7920 | 0 | 0 |  | 2019-82381 | 7920 | 1.5 | 14953636 | N/A | 0 | 7920 | 0 | 7920 | 1.5 | 6300000 |  |  | 0 | 2020-48279 | [16 empty] | TRUE | Scoped | TRUE | 2021
35137590 | ECOP - Top 20% | 14 | MEET | No | 2021037 | 0.52992 | 0.53485 | 0.53485 | 2021 |  |  | 0 | 32518.21 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | 335 | 3.7019 | 413 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5530164 |  | 118093216 | 35137590 | ECOP-MIDDLETOWN 1101-H02-CB | 2824 | 0 | 0 | 0 |  | 2019-73180 | 2798 | 0.52992 | 564800 | 2020-03-04 | 0 | 0 | 2824 | 2824 | 0.53485 | 1026909.0909 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35137593 | ECOP - Top 20% | 14 | MEET | No | 2021038 | 1.3799 | 1.3775 | 1.3775 | 2021 |  |  | 0 | 31936.06 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.5169 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118125945 | 35137593 | ECOP-MIDDLETOWN 1101-H07-LR4646 | 7273 | 0 | 0 | 0 |  | 2019-73200 | 7286 | 1.3799 | 1454600 | 43894 | 0 | 0 | 7273 | 7273 | 1.3775 | 2644727.2727 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35137596 | ECOP - Top 20% | 14 | MEET | No | 2021039 | 0.96989 | 0.97178 | 0.97178 | 2021 |  |  | 0 | 9431.74 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.0701 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118127757 | 35137596 | ECOP-MIDDLETOWN 1101-H08-LR4646 | 5131 | 0 | 0 | 0 |  | 2019-73285 | 5121 | 0.96989 | 1026000 | 43894 | 0 | 0 | 5131 | 5131 | 0.97178 | 1865818.1818 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35223027 | ECOP - Top 20% | 14 | MEET | No | 2021043 |  | 1.5674 | 1.5674 | 2021 |  |  | 0 | 9687.98 | ESTS | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.8803 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.03 | 120245192 | 35223027 | ECOP - SILVERADO 2104 - H05-LR726 PH4 | 8276 | 0 | 0 | 0 |  | 2020-77337 | 8276 | 1.57 | 0 | 2021-00327 | 0 | 0 | 8276 | 8276 | 1.5674 | 1898194 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225593 | ECOP - Top 20% | 14 | MEET | No | 2021045 |  | 1.1756 | 1.1756 | 2021 |  |  | 0 | 3814.22 | ESTS | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 1.2261 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5544143 | E.5034791.01 | 120424181 | 35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 6207 | 0 | 0 | 0 | 2020-77593 | 2020-77594 | 0 | 0 | 0 | 2021-02769 | 0 | 0 | 6207 | 6207 | 1.1756 | 1283732 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225597 | ECOP - Top 20% | 14 | MEET | No | 2021054 |  | 0.77576 | 0.77576 | 2021 |  |  | 0 | 943.79 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.56723 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.03 | 124024187 | 35225597 | ECOP - FULTON 1107 - H02-LR604 Ph 1.4 | 4096 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4096 | 4096 | 0.77576 | 1917600 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225598 | ECOP - Top 20% | 14 | MEET | No | 2021055 |  | 0.88144 | 0.88144 | 2021 |  |  | 0 | 943.79 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.6445 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.04 | 120424188 | 35225598 | ECOP - FULTON 1107 - H02-LR604 Ph 1.5 | 4654 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4654 | 4654 | 0.88144 | 1766100 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35054184 | Top 20% MAVF CPZ | 10 | MEET | No | 2021101 |  | 0.91 | 0.91 | 2021 |  |  | 0 | 22124.95 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.60664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5530173 | E.5019937.01.01 | 114941996 | 35054184 | CWSP-COLUMBIA HILL 1101-TS8233-PH1 | 4804.8 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 4805 | 0.91004 | 5227500 | 2021-03589 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35226659 | Top 20% MAVF CPZ | 10 | MEET | MEET | 2021102 |  | 1.88 | 1.88 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.5835 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.02 | 120447026 | 35226659 | CWSP-COLUMBIA HILL 1101-TS8233-PH2 | 5544 | 4382.4 | 0 | 0 | 2018-69650 | 2018-72909 | 9926 | 1.8799 |  | 2021-03589 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35226720 | Top 20% MAVF CPZ | 10 | MEET | No | 2021103 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.34665 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.03 | 120447027 | 35226720 | CWSP-COLUMBIA HILL 1101-TS8233-PH3 | 2745.6 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 2746 | 0.52008 |  | 2021-03589 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35226723 | Top 20% MAVF CPZ | 10 | MEET | MEET | 2021104 |  | 1.04 | 1.04 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.99964 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.04 | 120447110 | 35226723 | CWSP-COLUMBIA HILL 1101-TS8233-PH4 | 1425.6 | 4065.6 | 0 | 0 | 2018-69650 | 2018-72909 | 5492 | 1.0402 |  | 2021-03589 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227204 | Top 20% MAVF CPZ | 10 | MEET | No | 2021105 |  | 1.3 | 1.3 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.86664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.05 | 120447111 | 35227204 | CWSP-COLUMBIA HILL 1101-TS8233-PH5 | 6864 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 6864 | 1.3 |  | 2021-03589 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35026643 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2021106 | 1.63 | 1.6339 | 1.6339 | 2021 |  |  | 0 | 59465.39 | UNSE | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | 755 | 1.5795 | 957 | Tier 2 | WDDB | DIAMOND SPRINGS | El Dorado | Sierra | Northern | 5530173 |  | 114258488 | 35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 5727 | 0 | 2900 | 0 | n/a | 2018-38234 | 7400 | 1.4015 | 2100000 | 2021-03592 |  |  |  | 0 | 0 |  | 1.58 | 2900 | 1835.443 | [17 empty] | TRUE | In Scoping |  | 2021
35191318 | ECOP - Top 20% | 14 | MEET | No | 2021070 |  | 2.2159 | 2.2159 | 2021 |  |  | 0 | 17697.86 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 1.32 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541303 | E.5034352.01 | 119518390 | 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 11700 | 0 | 0 | 0 | 2020-76797 | 2020-76801 | 11721.6 | 2.22 | 1685400 | 2021-00256 | 0 | 0 | 11700 | 11700 | 2.2159 | 2027400 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
77799999 | Line Removal | 0 | MEET | MEET | 2021108 |  | 31.8 | 31.8 | 2021 |  |  | 0 | 0 | UNSE | Various | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Various | Various | Various | Various |  |  |  |  | VARIOUS | 0 | 0 | 167904 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [17 empty] | FALSE | 0 |  | 0 | Not valued order
35226625 | FRRB - REMG - 2021 | 2 | MEET | No | 2021109 |  | 7.9 | 7.9 | 2021 |  |  | 0 | 395.6 | UNSE | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 | 40 | 7.7611 |  |  | FRRB | ELK CREEK | Glenn | North Valley | Northern | 5795150 | E.5034795.01.01 | 120445306 | 35226625 | FRRB - ELK CREEK 1101 LR 2106 | 0 | 0 | 0 | 41712 | [9 empty] | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Pre-Scope |  | 0
35217274 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021110 |  | 2.52 | 2.52 | 2021 |  |  | 0 | 14916.89 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.18857 |  |  | FRRB | PESCADERO | San Mateo | Peninsula | Central Coast | 5794202 | E.5034613.01.01 | 120048101 | 35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 0 | 13305.6 | 0 | 0 |  | 2020-84558 | 13305.6 | 2.52 | 4621000 |  |  | 13305.6 | 0 | 13305.6 | 2.52 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217275 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021111 |  | 2.9 | 2.9 | 2021 |  |  | 0 | 15629.41 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.21701 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794201 | E.5034614.01.01 | 120048103 | 35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 0 | 15312 | 0 | 0 |  | 2020-87935 | 15312 | 2.9 | 5352500 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226626 | FRRB - REMG - 2021 | 2 | MEET | No | 2021112 |  | 4.03 | 4.03 | 2021 |  |  | 0 | 6800.87 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | 1.8081 |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5795151 | E.5034796.01.01 | 120445370 | 35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 0 | 0 | 0 | 21278.4 | [9 empty] | 0 |  |  |  |  | 0 | [17 empty] | TRUE | Pre-Scope |  | 0
35191383 | ECOP - Top 20% | 14 | MEET | No | 2021071 |  | 1.3286 | 1.3286 | 2021 |  |  | 0 | 16640.95 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 0.79143 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541309 | E.5034359.01 | 119518528 | 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 7015 | 0 | 0 | 0 |  | 2020-78168 | 7022.4 | 1.33 | 1143750 | 2021-00326 | 0 | 0 | 7015 | 7015 | 1.3286 | 1175890 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021 | MAT 95A ON MPP WP but for 2020
35226845 | ECOP | 14 | No | No | 2021073 |  | 2.3674 | 2.3674 | 2021 |  |  | 0 | 1039.61 | ESTS | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.6582 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5795298 | E.5034803.01.01 | 120448987 | 35226845 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 2 | 12500 | 0 | 0 | 0 |  | 2020-69602 |  |  |  | 2021-04462 | 0 | 0 | 12500 | 12500 | 2.3674 | 2880250 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021 | MAT 95A ON MPP WP but for 2020
35217267 | Top 50 Miles | 14 | MEET | No | 2021078 | 0.71281 | 0.71 | 0.71 | 2021 |  |  | 0 | 46774.47 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | 26 | 6.6788 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794209 | E.5034606.01.01 | 120047657 | 35217267 | CWSP - MARIPOSA 2102 LR 241564 | 3748.8 | 0 | 0 | 0 |  | 2020-83810 | 3748.8 | 0.71 | 804541 |  |  |  | 3748.8 | 3748.8 | 0.71 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021 | Duplicate value
35226846 | Top 20% MAVF CPZ | 14 | MEET | No | 2021089 | 1.54 | 1.5714 | 1.5714 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.5154 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.01 | 120448989 | 35226846 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 8297 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 8131 | 8131 | 1.54 | 2395810.5729 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021 | Duplicate value
35220936 | FRRB - UG - 2021 | 5 | MEET | MEET | 2021117 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 7246.08 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 | 2095 | 0.060255 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794202 | E.5034613.01.02 | 120224375 | 35220936 | FRRB - BUTANO STATE PARK - PN SM | 0 | 5016 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | Pre-Scope |  | 0
35226847 | Top 20% MAVF CPZ | 14 | MEET | No | 2021090 | 1.9299 | 1.9839 | 1.9839 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.1757 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.02 | 120449140 | 35226847 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 10475 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 10190 | 10190 | 1.9299 | 3002497.8155 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35231607 | Top 20% MAVF CPZ | 14 | MEET | No | 2021091 | 1.4799 | 1.646 | 1.646 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.6349 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.11 | 120504093 | 35231607 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 8691 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7814 | 7814 | 1.4799 | 2302406.0776 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35235139 | FRRB - UG - 2021 |  |  |  | 2021120 |  | 0 | [7 empty] | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5794519 | E.5034825.01.22 | 120582960 | 35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH 3 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35229043 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021121 |  | 0.41345 | 0.41345 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.060599 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.01 | 120493696 | 35229043 | FRRB – WYANDOTTE 1103 – BALD ROCK ZONE 1 | 0 | 2183 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35226848 | Top 20% MAVF CPZ | 14 | MEET | No | 2021093 | 2.8701 | 2.4445 | 2.4445 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.913 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.03 | 120449141 | 35226848 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 12907 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 15154 | 15154 | 2.8701 | 4392047.6357 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226850 | Top 20% MAVF CPZ | 14 | MEET | No | 2021094 | 2.29 | 1.5451 | 1.5451 | 2021 |  |  | 0 | 515 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.4733 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.05 | 120449143 | 35226850 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 8158 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 9187 | 9187 | 1.74 | 2662646.2735 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226851 | Top 20% MAVF CPZ | 14 | MEET | No | 2021095 | 2.19 | 1.8784 | 1.8784 | 2021 |  |  | 0 | 297.8 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.0069 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.06 | 120449144 | 35226851 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 9918 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 11563 | 11563 | 2.19 | 3351276.6802 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35232280 | Top 20% MAVF CPZ | 14 | MEET | No | 2021096 | 0.6 | 0.6 | 0.6 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.96045 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.14 | 120527401 | 35232280 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 3168 | 0 | 0 | 0 | [5 empty] | 2021-04169 | 3168 | 0 | 0 | 3168 | 0.6 | 918173.8755 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226852 | Top 20% MAVF CPZ | 14 | MEET | No | 2021097 | 2.93 | 2.4932 | 2.4932 | 2021 |  |  | 0 | 696.05 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 4.8429 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.07 | 120449145 | 35226852 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.2 | 13164 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 15470.4 | 15470.4 | 2.93 | 5502901.5208 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35222234 | Remote Grid Pilot | 7 | MEET | No | 2021127 |  | 2.62 | 2.62 | 2021 |  |  | 0 | 0 | UNSE | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 | 167 | 4.4624 |  |  | REMG | OAKHURST | Mariposa | Yosemite | Central Valley | 5543982 | E.5034752.01.01 | 120237130 | 35222234 | REMG - OAKHURST 110110090 | 0 | 0 | 0 | 13833.6 |  | 2021-00557 | 13833.6 | 2.62 | 4816500 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35226853 | Top 20% MAVF CPZ | 14 | MEET | No | 2021098 | 2.92 | 2.8044 | 2.8044 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 5.4473 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.08 | 120449146 | 35226853 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 14807 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 264 | 15153.6 | 15417.6 | 2.92 | 5484120.2869 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226854 | Top 20% MAVF CPZ | 14 | MEET | No | 2021099 | 1.03 | 1.0299 | 1.0299 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 2.0006 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.09 | 120449147 | 35226854 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 5438 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 5438.4 | 0 | 0 | 5438.4 | 1.03 | 1934467.0875 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226856 | Top 20% MAVF CPZ | 14 | MEET | No | 2021100 | 4.53 | 1.9436 | 1.9436 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 3.7753 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.10 | 120449149 | 35226856 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 10262 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 23918.4 | 23918.4 | 4.53 | 8507898.9383 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35075103 | Top 20% MAVF CPZ | 17 | MEET | No | 2021107 |  | 0.59 | 0.59 | 2021 |  |  | 0 | 73818.65 | APPR | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | 564 | 0.39202 | 1409 | Tier 3 | WDDB | MURPHYS | Calaveras | Stockton | Central Valley | 5530176 |  | 116475141 | 35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 3115.2 | 0 | 0 | 0 |  | 2019-20625 2021-08733 | 3115 | 0.58996 | 623000 | 2021-04261 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35223343 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021118 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 46989.9 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.28647 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.08 | 120255838 | 35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 1 | 0 | 4488 | 0 | 0 |  | 2021-02744 | 4488 | 0.85 | 1338480 | [9 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225821 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021119 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 43823.92 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.32018 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.11 | 120424578 | 35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 2 | 0 | 5016 | 0 | 0 |  | 2021-02748 | 5016 | 0.95 | 1638720 | [9 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35223344 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021122 |  | 4.1617 | 4.1617 | 2021 |  |  | 0 | 182107.54 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.60999 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.09 | 120255980 | 35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | 0 | 21974 | 0 | 0 |  | 2021-02746 | 9081.6 | 1.72 | 3007400 | [9 empty] | 0 |  | 2021-07956 | [15 empty] | TRUE | Scoped | TRUE | 2021
35223345 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021123 |  | 4.454 | 4.454 | 2021 |  |  | 0 | 786926.39 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 1.6208 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.10 | 120255982 | 35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 0 | 23517 | 0 | 0 |  | 2021-02747 | 13147.2 | 2.49 | 4312040 | [9 empty] | 0 | 2021-09321 | 2021-11881 | [15 empty] | TRUE | Scoped | TRUE | 2021
35225822 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021124 |  | 1.8693 | 1.8693 | 2021 |  |  | 0 | 61032.84 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.27399 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.12 | 120424579 | 35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 0 | 9870 | 0 | 0 |  | 2021-02749 | 5755.2 | 1.09 | 1954920 | [9 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225823 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021125 |  | 1.7159 | 1.7159 | 2021 |  |  | 0 | 76747.3 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.6244 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.13 | 120424672 | 35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 0 | 9060 | 0 | 0 |  | 2021-02750 | 9081.6 | 1.72 | 3005800 | [9 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225824 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021126 |  | 2.9364 | 2.9364 | 2021 |  |  | 0 | 550379.42 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.3314 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.14 | 120424703 | 35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 0 | 15504 | 0 | 0 |  | 2021-02751 | 13464 | 2.55 | 4213480 | [9 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35232298 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021128 |  | 0.24 | 0.24 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.035177 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.02 | 120532441 | 35232298 | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | 0 | 1267.2 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233038 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021129 |  | 0.23 | 0.23 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.033711 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.05 | 120542278 | 35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | 0 | 1214.4 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233039 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021130 |  | 0.37 | 0.37 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.06 | 120542500 | 35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 0 | 1953.6 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233300 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021131 |  | 0.32 | 0.32 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.046902 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.07 | 120542502 | 35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 0 | 1689.6 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233301 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021132 |  | 0.36 | 0.36 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.052765 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.08 | 120542503 | 35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | 0 | 1900.8 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233302 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021133 |  | 0.12 | 0.12 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.017588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.09 | 120542504 | 35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 0 | 633.6 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233303 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021134 |  | 0.09 | 0.09 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.013191 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.10 | 120542505 | 35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | 0 | 475.2 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233304 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021135 |  | 0.3 | 0.3 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.043971 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.11 | 120542506 | 35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | 0 | 1584 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233305 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021136 |  | 0.29 | 0.29 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.042505 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.12 | 120542507 | 35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | 0 | 1531.2 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233306 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021137 |  | 0.26 | 0.26 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.038108 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.13 | 120541535 | 35233306 | FRRB - WYANDOTTE 1103 - W1 PH 1.10 | 0 | 1372.8 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233307 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021138 |  | 0.6 | 0.6 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.087942 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.14 | 120541538 | 35233307 | FRRB - WYANDOTTE 1103 - W1 PH 1.11 | 0 | 3168 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35233308 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021139 |  | 0.93 | 0.93 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.13631 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.15 | 120541539 | 35233308 | FRRB - WYANDOTTE 1103 - W1 PH 1.12 | 0 | 4910.4 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | New order
35233309 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021140 |  | 0.37 | 0.37 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.16 | 120541630 | 35233309 | FRRB - WYANDOTTE 1103 - W1 PH 1.13 | 0 | 1953.6 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | NCF - Pulled into DOT on 3/8/21 not on MPP WP and change rquest not yet submitted
35233310 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021141 |  | 0.15 | 0.15 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.021985 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.17 | 120541632 | 35233310 | FRRB - WYANDOTTE 1103 - W1 PH 1.14 | 0 | 792 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | NCF - Pulled into DOT on 3/4/21
35232718 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021142 |  | 1.2 | 1.2 | 2021 |  |  | 0 |  | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.03 | 120538803 | 35232718 | FRRB - WYANDOTTE 1103 - W2 PH 2.1 | 0 | 6336 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | NCF - Pulled into DOT on 3/4/21
35233311 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021143 |  | 1.25 | 1.25 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.18321 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.18 | 120541633 | 35233311 | FRRB - WYANDOTTE 1103 - W2 PH 2.2 | 0 | 6600 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | NCF - Pulled into DOT on 3/4/21
35233312 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021144 |  | 1.1 | 1.1 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.16123 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.19 | 120541634 | 35233312 | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | 0 | 5808 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021 | NCF - Pulled into DOT on 3/4/21
35235674 | FRRB - UG - 2021 |  |  |  | 2021156 |  | 4.3 | 4.3 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 2.9484 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.29 | 120596259 | 35235674 | FRRB - BIG BEND 1102 - B1 PH 1 | 0 | 22704 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235675 | FRRB - UG - 2021 |  |  |  | 2021157 |  | 1 | 1 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 0.68567 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.30 | 120596615 | 35235675 | FRRB - BIG BEND 1102 - B2 PH 2 | 0 | 5280 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235676 | FRRB - UG - 2021 |  |  |  | 2021158 |  | 2.3701 | 2.3701 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.79878 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.31 | 120598345 | 35235676 | FRRB - BIG BEND 1102 - B3 PH 3 | 0 | 12514 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235677 | FRRB - UG - 2021 |  |  |  | 2021159 |  | 4.2 | 4.2 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4155 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.32 | 120598407 | 35235677 | FRRB - BIG BEND 1102 - B4 PH 4 | 0 | 22176 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235678 | FRRB - UG - 2021 |  |  |  | 2021160 |  | 4.4 | 4.4 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4829 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.33 | 120598535 | 35235678 | FRRB - BIG BEND 1102 - B5 PH 5 | 0 | 23232 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235679 | FRRB - UG - 2021 |  |  |  | 2021161 |  | 6.5 | 6.5 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 2.1907 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.34 | 120598623 | 35235679 | FRRB - BIG BEND 1102 - B6 PH 6 | 0 | 34320 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235700 | FRRB - UG - 2021 |  |  |  | 2021162 |  | 5.44 | 5.44 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.2343 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.35 | 120598982 | 35235700 | FRRB - KANAKA 1101 - K1 PH 1 | 0 | 28723 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235701 | FRRB - UG - 2021 |  |  |  | 2021163 |  | 3.49 | 3.49 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.79185 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.36 | 120599070 | 35235701 | FRRB - KANAKA 1101 - K2 PH 2 | 0 | 18427 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235702 | FRRB - UG - 2021 |  |  |  | 2021164 |  | 2.14 | 2.14 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.48554 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.37 | 120599072 | 35235702 | FRRB - KANAKA 1101 - K3 PH3 | 0 | 11299 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235703 | FRRB - UG - 2021 |  |  |  | 2021165 |  | 8.44 | 8.44 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.915 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.38 | 120599073 | 35235703 | FRRB - KANAKA 1101 - K4 PH 4 | 0 | 44563 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
35235704 | FRRB - UG - 2021 |  |  |  | 2021166 |  | 6.1 | 6.1 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.384 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.39 | 120599076 | 35235704 | FRRB - KANAKA 1101 - K5 PH 5 | 0 | 32208 | 0 | 0 | [32 empty] | TRUE | 0 |  | 0
| FRRB - UG - 2021 |  |  |  | 2021167 | [8 empty] | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #DIV/0! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 |  |  |  | FRRB - KANAKA 1101 - K6 PH 6 | 0 |  | 0 | 0 | [32 empty] | FALSE | 0 |  | 0 | Blank Order value
35222236 | Remote Grid Pilot | 7 | MEET | No | 2021168 |  | 0.99 | 0.99 | 2021 |  |  | 0 | 0 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 | 468 | 1.4164 |  |  | REMG | MARIPOSA | Mariposa | Yosemite | Central Valley | 5543983 | E.5034753.01.01 | 120237131 | 35222236 | REMG - MARIPOSA 210135244 | 0 | 0 | 0 | 5227.2 |  | 2020-88214 | 5227.2 | 0.99 | 780759 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35175853 | Remote Grid Pilot | 13 | No | No | 2021169 |  | 0.7 | 0.7 | 2021 |  |  | 0 | 1787.6 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.0417 |  |  | REMG | GEORGETOWN | El Dorado | Sierra | Northern | 5790554 | E.5015422.03 | 118981960 | 35175853 | REMG - PLACERVILLE 21061104 | 0 | 0 | 0 | 3696 |  | 2018-84079 | 45936 | 8.7 | 9322600 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35222235 | Remote Grid Pilot | 7 | No | No | 2021170 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 5790.29 | UNSE | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 | 2461 | 0.0024273 |  |  | REMG | BADGER | Tulare | Fresno | Central Valley | 5794900 | E.5034754.01.01 | 120236988 | 35222235 | REMG - DUNLAP 1102778286 | 0 | 0 | 0 | 13728 |  | 2020-88308 | 13728 | 2.6 | 613214 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35229051 | Remote Grid Pilot | 7 | MEET | No | 2021171 |  | 3.04 | 3.04 | 2021 |  |  | 0 | 395.6 | UNSE | 103331102 | CORNING 1102 | CORNING 110253184 | 123 | 31.8239 | 413 | 21.5791 | 0.17544 | 106 | 2.0407 |  |  | REMG | FLOURNEY | Tehama | North Valley | Northern | 5795612 | E.5034827.01.01 | 120494134 | 35229051 | CORNING 1102 - REMOTE GRID #299 & # 300 | 0 | 0 | 0 | 16051 |  | 2021-09834 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219543 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021172 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 3904.85 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.021274 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.02 | 120135657 | 35219543 | PSPS - West Main St / Reservoir St - PLA PH 1.1 | 0 | 1267.2 | 0 | 0 |  | 2021-01722 | 1267.2 | 0.24 | 850440 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35223036 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021173 |  | 0.055871 | 0.055871 | 2021 |  |  | 0 | 4821.78 | UNSE | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 | 2454 | 2.7003 |  |  | PSPS | GRASS VALLEY | Nevada | Sierra | Northern | 5794983 | E.5034759.01.01 | 120242599 | 35223036 | PSPS - Brunswick 1110CB | 0 | 295 | 0 | 0 |  | 2021-01470 | 264 | 0.05 | 88320 | 2021-08160 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35223030 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021174 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 12822.92 | UNSE | 103191101 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 | 565 | 1.4867 |  |  | PSPS | BANGOR | Butte | Sierra | Northern | 5794981 | E.5034757.01.01 | 120242544 | 35223030 | PSPS - Bangor 1101CB | 0 | 4488 | 0 | 0 |  | 2021-01574 | 3009.6 | 0.57 | 1556240 | 2021-08449 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35223062 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021175 |  | 0.18 | 0.18 | 2021 |  |  | 0 | 6857.1 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | 3379 | 7.3185e-05 |  | Tier 2 | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.01 | 120242676 | 35223062 | PSPS - Calistoga 1102184814 | 0 | 950.4 | 0 | 0 |  | 2021-01578 | 950.4 | 0.18 | 579050 | 2021-07698 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35223038 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021176 |  | 0.87 | 0.87 | 2021 |  |  | 0 | 8921.72 | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | 1.6887 |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.01 | 120242693 | 35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | 0 | 4593.6 | 0 | 0 |  | 2021-01713 | 4593.6 | 0.87 | 911350 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234284 | PSPS - Community Resiliency | 9 | MEET | No | 2021177 |  | 0 | 0 | 2021 |  |  | 0 |  | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | #DIV/0! |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.02 | 120539923 | 35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | In Scoping |  | 0
35234526 | PSPS - Community Resiliency | 9 | MEET | No | 2021178 |  |  |  | 2021 |  |  | 0 |  | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | #DIV/0! |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.03 | 120574717 | 35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | In Scoping |  | 0
35223060 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021179 |  | 1.74 | 1.74 | 2021 |  |  | 0 | 5062.09 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | 0.18012 |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.01 | 120242671 | 35223060 | PSPS-ALLEGHANY 1101-Downieville PH 1.1 | 0 | 9187.2 | 0 | 0 |  | 2021-01568 | 9187.2 | 1.74 | 4040000 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234527 | PSPS - Community Resiliency | 9 | MEET | No | 2021180 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.02 | 120574718 | 35234527 | PSPS-ALLEGHANY 1101-Downieville PH 1.2 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | In Scoping |  | 0
35234528 | PSPS - Community Resiliency | 9 | MEET | No | 2021181 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.03 | 120574870 | 35234528 | PSPS-ALLEGHANY 1101-Downieville PH 1.3 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | In Scoping |  | 0
35234529 | PSPS - Community Resiliency | 9 | MEET | No | 2021182 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.04 | 120574871 | 35234529 | PSPS-ALLEGHANY 1101-Downieville PH 1.4 | 0 | 0 | 0 | 0 | [32 empty] | TRUE | In Scoping |  | 0
35223063 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021183 |  | 0.15114 | 0.15114 | 2021 |  |  | 0 | 4536.46 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.073206 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.01 | 120242673 | 35223063 | PSPS - DUNBAR 1101 - OAKMONT PH 1 | 0 | 798 | 0 | 0 |  | 2021-01566 | 10190.4 | 1.93 | 4690000 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35228774 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021184 |  | 0.97405 | 0.97405 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.47181 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.02 | 120487476 | 35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | 0 | 5143 | 0 | 0 |  | 2021-01566 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35228775 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021185 |  | 0.88617 | 0.88617 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.42924 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.03 | 120487477 | 35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | 0 | 4679 | 0 | 0 |  | 2021-01566 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35223032 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021186 |  | 0.44 | 0.44 | 2021 |  |  | 0 | 9292.7 | UNSE | 152282102 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | 328 | 1.7655 |  | Tier 2 | PSPS | COOL | El Dorado | Sierra | Northern | 5794982 | E.5034758.01.01 | 120242546 | 35223032 | PSPS - Mounatin Quarries 2101CB | 0 | 2323.2 | 0 | 0 |  | 2021-01503 | 2323.2 | 0.44 | 745920 | 2021-10707 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35233314 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021145 |  | 1.6 | 1.6 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.23451 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.20 | 120541635 | 35233314 | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | 0 | 8448 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35224377 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021188 |  | 1.13 | 1.13 | 2021 |  |  | 0 | 4024.98 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.43955 |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.01 | 120360607 | 35224377 | PSPS - PLACERVILLE 21067522 PH 1.1 | 0 | 5966.4 | 0 | 0 |  | 2021-01725 | 5966.4 | 1.13 | 2731920 |  |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35223039 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021189 | 0.63 | 0.60739 | 0.60739 | 2021 |  |  | 0 | 10152.12 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | 672 | 2.522 |  | Tier 2 | PSPS | OROVILLE | Butte | North Valley | Northern | 5794987 | E.5034763.01.01 | 120242691 | 35223039 | PSPS - Wyandotte 1109702710 | 705 | 2502 | 0 | 0 |  | 2021-01576 | 4065.6 | 0.77 | 1517740 | 2021-08443 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35233995 | PSPS - Community Resiliency | 10 | MEET | No | 2021190 |  | 0 | 0 | 2021 |  |  | 0 |  | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | #DIV/0! |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.02 | 120563909 | 35233995 | PSPS - PLACERVILLE 21067522 PH 1.2 | 0 | 0 | 0 | 0 |  | 2021-01725 | [30 empty] | TRUE | In Scoping |  | 0
35233996 | PSPS - Community Resiliency | 10 | MEET | No | 2021191 |  |  |  | 2021 |  |  | 0 |  | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | #DIV/0! |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.03 | 120563933 | 35233996 | PSPS - PLACERVILLE 21067522 PH 1.3 | 0 | 0 | 0 | 0 |  | 2021-01725 | [30 empty] | TRUE | In Scoping |  | 0
35219542 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021192 |  | 0.14 | 0.14 | 2021 |  |  | 0 | 7221.51 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.01241 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.01 | 120135655 | 35219542 | PSPS - Eskaton Village | 0 | 739.2 | 0 | 0 |  | 2021-01718 | 739.2 | 0.14 | 544560 | 2021-11652 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35233315 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021146 |  | 0.96004 | 0.96004 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.14071 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.21 | 120541636 | 35233315 | FRRB - WYANDOTTE 1103 - W2 PH 2.5 | 0 | 5069 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35235705 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021147 |  | 1.3201 | 1.3201 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.19348 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.40 | 120594567 | 35235705 | FRRB - WYANDOTTE 1103 - W2 PH 2.6 | 0 | 6970 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35235706 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021148 |  | 1.16 | 1.16 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17003 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.41 | 120594568 | 35235706 | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | 0 | 6125 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35235707 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021149 |  | 0.95 | 0.95 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.13924 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.42 | 120594569 | 35235707 | FRRB - WYANDOTTE 1103 - W2 PH 2.8 | 0 | 5016 | 0 | 0 |  | 2021-09904 | [30 empty] | TRUE | Scoped | TRUE | 2021
35223037 | PSPS - Community Resiliency | 14 | MEET | MEET | 2021187 |  | 0.052083 | 0.052083 | 2021 |  |  | 0 | 5273.97 | ESTS | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | 802 | 0.090642 |  | Tier 3 | PSPS | OAKHURST | Madera | Yosemite | Central Valley | 5794989 | E.5034765.01.01 | 120242694 | 35223037 | PSPS - Oakhurst 1101CB | 0 | 275 | 0 | 0 |  | 2021-01716 | 580.8 | 0.11 | 181120 | 2021-06095 |  |  |  | 0 |  |  | 0.0891 | 200 | 2244.6689 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219098 | Top 250 Miles | 13 | MEET | No | 2021205 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 13086.55 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 2.9196 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120141805 | 35219098 | CWSP - MIDDLETOWN 1101118494 | 3801.6 | 0 | 0 | 0 |  | 2020-88310 | 7022.4 | 1.33 | 1830000 | 2021-04412 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35229119 | Top 250 Miles | 13 | MEET | MEET | 2021206 |  | 0.61 | 0.61 | 2021 |  |  | 0 | 957.21 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 3.9497 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120496477 | 35229119 | CWSP - MIDDLETOWN 1101118494 PH 2 | 0 | 3220.8 | 0 | 0 |  | 2020-88310 |  |  |  | 2021-04412 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219099 | Top 250 Miles | 10 | MEET | No | 2021207 |  | 17.3 | 17.3 | 2021 |  |  | 0 | 25924.57 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 21.1042 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.01 | 120141849 | 35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | 91344 | 0 | 0 | 0 |  | 2021-00785 | 91344 | 17.3 | 25150000 | 2021-08349 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231620 | Top 250 Miles | 10 | MEET | No | 2021208 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.02 | 120504137 | 35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231621 | Top 250 Miles | 10 | MEET | No | 2021209 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.03 | 120504138 | 35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231622 | Top 250 Miles | 10 | MEET | No | 2021210 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.04 | 120504139 | 35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231623 | Top 250 Miles | 10 | MEET | No | 2021211 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.05 | 120504160 | 35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231624 | Top 250 Miles | 10 | MEET | No | 2021212 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.06 | 120504163 | 35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231625 | Top 250 Miles | 10 | MEET | No | 2021213 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.07 | 120504164 | 35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231626 | Top 250 Miles | 10 | MEET | No | 2021214 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.08 | 120504165 | 35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231627 | Top 250 Miles | 10 | MEET | No | 2021215 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.09 | 120504167 | 35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231628 | Top 250 Miles | 10 | MEET | No | 2021216 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.10 | 120504170 | 35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231629 | Top 250 Miles | 10 | MEET | No | 2021217 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.11 | 120504175 | 35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231630 | Top 250 Miles | 10 | MEET | No | 2021218 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.12 | 120504176 | 35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35231631 | Top 250 Miles | 10 | MEET | No | 2021219 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.13 | 120504177 | 35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219260 | Top 250 Miles | 13 | MEET | No | 2021220 | 0.84 | 0.84432 | 0.84432 | 2021 |  |  | 0 | 11750.94 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 3.1009 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034698.01.01 | 120141880 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1 | 4458 | 0 | 0 | 0 |  | 2021-01235 | 6916.8 | 1.31 | 2194368 | 2021-04349 |  |  |  | 0 | 0 |  | 6.25 | 4000 | 640 | [17 empty] | TRUE | In Scoping |  | 2021
35219097 | Top 250 Miles | 14 | MEET | No | 2021201 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 12094.11 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.01 | 120141762 | 35219097 | CWSP - COARSEGOLD 2104CB PH1.1 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 | 45302.4 | 8.58 | 7867593 | 2021-04771 |  |  |  | 0 | 0 |  | 26.69 | 19300 | 723.1173 | [17 empty] | TRUE | Scoped | TRUE | 2021
35227260 | Top 250 Miles | 14 | MEET | No | 2021202 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 0 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.02 | 120457078 | 35227260 | CWSP - COARSEGOLD 2104CB PH1.2 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35227261 | Top 250 Miles | 14 | MEET | No | 2021203 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 3990.77 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 8.873 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.03 | 120457111 | 35227261 | CWSP - COARSEGOLD 2104CB PH1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35227262 | Top 250 Miles | 14 | MEET | No | 2021204 |  | 1.4015 | 1.4015 | 2021 |  |  | 0 | 3544.16 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 5.7572 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.04 | 120457115 | 35227262 | CWSP - COARSEGOLD 2104CB PH1.4 | 7400 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219266 | Top 250 Miles | 14 | MEET | No | 2021221 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 45633.67 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 4.4861 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.01 | 120141949 | 35219266 | CWSP - MARIPOSA 2102CB PH 1 | 13728 | 0 | 0 | 0 |  | 2021-01236 | 27720 | 5.25 | 8003586 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219269 | Top 250 Miles | 9 | MEET | MEET | 2021226 |  | 32.72 | 32.72 | 2021 |  |  | 0 | 7398.58 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 251.599 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.01 | 120142106 | 35219269 | CWSP - VACA DIXON 110540092 | 80150.4 | 50424 | 42187.2 | 0 |  | 2021-08140 | 130574.4 | 24.73 | 28158240 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227263 | Top 250 Miles | 14 | MEET | No | 2021222 |  | 2.6083 | 2.6083 | 2021 |  |  | 0 | 12113.02 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 4.5005 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.05 | 120457435 | 35227263 | CWSP - MARIPOSA 2102CB PH 2 | 13772 | 0 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219268 | Top 250 Miles | 14 | MEET | No | 2021223 |  | 1.6212 | 1.6212 | 2021 |  |  | 0 | 77148.45 | ESTS | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 4.1161 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.01 | 120142035 | 35219268 | CWSP - MARIPOSA 210197142 PH 1 | 8560 | 0 | 0 | 0 |  | 2021-01027 | 24288 | 4.6 | 7389000 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35226241 | Top 250 Miles | 15 | MEET | No | 2021224 |  | 1.4799 | 1.4799 | 2021 |  |  | 0 | 36185.31 | ADER | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7573 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.02 | 120431331 | 35226241 | CWSP - MARIPOSA 210197142 PH 2 | 7814 | 0 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219276 | Top 250 Miles | 10 | MEET | MEET | 2021230 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 30622.52 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.1163 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.01 | 120142212 | 35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | 0 | 11404.8 | 0 | 0 |  | 2021-01037 | 40444.8 | 7.66 | 11826060 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227651 | Top 250 Miles | 10 | MEET | No | 2021231 |  | 2.31 | 2.31 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 6.1057 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.03 | 120462109 | 35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | 12196.8 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227652 | Top 250 Miles | 10 | MEET | MEET | 2021232 |  | 0.41 | 0.41 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.7304 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.04 | 120462111 | 35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 0 | 2164.8 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227653 | Top 250 Miles | 10 | MEET | No | 2021233 |  | 2 | 2 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.2863 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.05 | 120462112 | 35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | 10560 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227654 | Top 250 Miles | 10 | MEET | No | 2021234 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.9031 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.06 | 120462113 | 35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | 3801.6 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35224378 | Top 250 Miles | 10 | MEET | No | 2021235 |  | 3.6 | 3.6 | 2021 |  |  | 0 | 14637.68 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.5154 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.02 | 120406213 | 35224378 | CWSP - VACAVILLE 11046542 PH 2.1 | 19008 | 0 | 0 | 0 |  | 2021-01589 | 36854.4 | 6.98 | 8840920 | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227870 | Top 250 Miles | 10 | MEET | MEET | 2021236 |  | 1.35 | 1.35 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.6977 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.07 | 120462116 | 35227870 | CWSP - VACAVILLE 11046542 PH 2.2 | 0 | 7128 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227656 | Top 250 Miles | 10 | MEET | MEET | 2021237 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 3.1654 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.08 | 120462117 | 35227656 | CWSP - VACAVILLE 11046542 PH 2.3 | 0 | 3960 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227657 | Top 250 Miles | 10 | MEET | No | 2021238 |  | 1 | 1 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 2.6432 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.09 | 120462180 | 35227657 | CWSP - VACAVILLE 11046542 PH 2.4 | 5280 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227658 | Top 250 Miles | 10 | MEET | No | 2021239 |  | 0.04 | 0.04 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.10573 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.10 | 120462182 | 35227658 | CWSP - VACAVILLE 11046542 PH 2.5 | 211.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35227659 | Top 250 Miles | 10 | MEET | No | 2021240 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.63436 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.11 | 120462184 | 35227659 | CWSP - VACAVILLE 11046542 PH 2.6 | 1267.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219280 | Top 250 Miles | 13 | MEET | MEET | 2021241 |  | 0.15152 | 0.15152 | 2021 |  |  | 0 | 4376.27 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 4.0762 |  | Tier 2 | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.01 | 120142216 | 35219280 | CWSP - POTTER VALLEY P H 110564118 PH 1 | 0 | 800 | 0 | 0 |  | 2020-88312 | 9820.8 | 1.86 | 2340000 | 2021-03822 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226632 | Top 250 Miles | 13 | MEET | No | 2021242 |  | 1.6828 | 1.6828 | 2021 |  |  | 0 | 919.75 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 28.3517 |  |  | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.02 | 120445424 | 35226632 | CWSP - POTTER VALLEY P H 110564118 PH 2 | 8885 | 0 | 0 | 0 |  | 2020-88312 | - | - | - | 2021-03822 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35232651 | Top 250 Miles | 13 | MEET | No | 2021243 |  | 1.74 | 1.74 | 2021 |  |  | 0 |  | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 4.7696 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.03 | 120529255 | 35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 9187 | 0 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219286 | Top 250 Miles | 11 | MEET | No | 2021244 | 2.91 | 3.4547 | 3.4547 | 2021 |  |  | 0 | 17566.79 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.4782 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.01 | 120142352 | 35219286 | CWSP - DESCHUTES 11049718 PH1.1 | 18241 | 0 | 0 | 0 |  | 2021-03394 | 31574.4 | 5.98 | 6757905 | 2021-12071 |  |  | 15365 | 15365 | 2.91 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35232960 | Top 250 Miles | 11 | MEET | No | 2021245 | 2.9299 | 3.0411 | 3.0411 | 2021 |  |  | 0 | 8846.26 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.3856 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.07 | 120537723 | 35232960 | CWSP - DESCHUTES 11049718 PH1.2 | 16057 | 0 | 0 | 0 |  | 2021-03394 |  |  |  | 2021-12071 |  |  | 15470 | 15470 | 2.9299 | [21 empty] | TRUE | In Scoping |  | 0
35225825 | Top 250 Miles | 11 | MEET | No | 2021246 | 1.5299 | 1.5562 | 1.5562 | 2021 |  |  | 0 | 8930.89 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 7.8734 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.02 | 120426401 | 35225825 | CWSP - DESCHUTES 11049718 PH2.1 | 8217 | 0 | 0 | 0 |  | 2021-03395 | 56126.4 | 10.63 | 9724400 | 2021-12064 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35232442 | Top 250 Miles | 11 | MEET | No | 2021247 | 3.1299 | 3.0778 | 3.0778 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.5714 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.03 | 120528704 | 35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | 16251 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35232443 | Top 250 Miles | 11 | MEET | No | 2021248 | 1 | 1.0356 | 1.0356 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 5.2393 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.04 | 120528712 | 35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | 5468 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35232444 | Top 250 Miles | 11 | MEET | No | 2021249 | 3.4701 | 3.5318 | 3.5318 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.8682 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.05 | 120528751 | 35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | 18648 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35232445 | Top 250 Miles | 11 | MEET | No | 2021250 | 2.6 | 2.6038 | 2.6038 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 13.1731 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.06 | 120528752 | 35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | 13748 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219289 | Top 250 Miles | 9 | MEET | MEET | 2021251 | 57.14 | 16.997 | 16.997 | 2021 |  |  | 0 | 7304.58 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 66.499 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.02 | 120142359 | 35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | 40052 | 32488 | 17204 | 0 |  | 2021-05564 | 58396.8 | 11.06 | [5 empty] | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35233947 | Top 250 Miles | 9 | MEET | No | 2021252 |  | 0 | 0 | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.38 | 120564156 | 35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 | 0 | 0 | 0 | 0 |  | 2021-05564 | [30 empty] | TRUE | In Scoping |  | 0
35233948 | Top 250 Miles | 9 | MEET | No | 2021253 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.39 | 120564181 | 35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | 0 | 0 | 0 | 0 |  | 2021-05564 | [30 empty] | TRUE | In Scoping |  | 0
35233949 | Top 250 Miles | 9 | MEET | No | 2021254 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.40 | 120564182 | 35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 | 0 | 0 | 0 | 0 |  | 2021-05564 | [30 empty] | TRUE | In Scoping |  | 0
35233950 | Top 250 Miles | 9 | MEET | No | 2021255 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.41 | 120564183 | 35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | 0 | 0 | 0 | 0 |  | 2021-05564 | [30 empty] | TRUE | In Scoping |  | 0
35233951 | Top 250 Miles | 9 | MEET | No | 2021256 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.42 | 120564184 | 35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 | 0 | 0 | 0 | 0 |  | 2021-05564 | [30 empty] | TRUE | In Scoping |  | 0
35225826 | Top 250 Miles | 9 | MEET | MEET | 2021257 |  | 9.7468 | 9.7468 | 2021 |  |  | 0 | 1990.54 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 29.0085 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.03 | 120426402 | 35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | 50237 | 533 | 693 | 0 |  | 2021-05558 | 51268.8 | 9.71 | [10 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35233952 | Top 250 Miles | 9 | MEET | No | 2021258 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.08 | 120563958 | 35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35233953 | Top 250 Miles | 9 | MEET | No | 2021259 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.09 | 120563959 | 35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35233955 | Top 250 Miles | 9 | MEET | No | 2021260 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.10 | 120564050 | 35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35233957 | Top 250 Miles | 9 | MEET | No | 2021261 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.11 | 120564051 | 35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35233959 | Top 250 Miles | 9 | MEET | No | 2021262 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.12 | 120564052 | 35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35234381 | Top 250 Miles | 9 | MEET | No | 2021263 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.13 | 120564055 | 35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35234382 | Top 250 Miles | 9 | MEET | No | 2021264 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.14 | 120564057 | 35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | 0 | 0 | 0 | 0 |  | 2021-05558 | [30 empty] | TRUE | In Scoping |  | 0
35225827 | Top 250 Miles | 9 | MEET | No | 2021265 |  | 6.5636 | 6.5636 | 2021 |  |  | 0 | 1182.27 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 19.2568 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.04 | 120426404 | 35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | 34656 | 0 | 0 | 0 |  | 2021-05859 | 34636.8 | 6.56 | [10 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35233954 | Top 250 Miles | 9 | MEET | No | 2021266 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.15 | 120564059 | 35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35233956 | Top 250 Miles | 9 | MEET | No | 2021267 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.16 | 120564070 | 35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35233958 | Top 250 Miles | 9 | MEET | No | 2021268 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.17 | 120564071 | 35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35234380 | Top 250 Miles | 9 | MEET | No | 2021269 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.18 | 120564073 | 35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35234383 | Top 250 Miles | 9 | MEET | No | 2021270 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.19 | 120564074 | 35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35234384 | Top 250 Miles | 9 | MEET | No | 2021271 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.20 | 120564075 | 35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35234385 | Top 250 Miles | 9 | MEET | No | 2021272 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.21 | 120564076 | 35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35234386 | Top 250 Miles | 9 | MEET | No | 2021273 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.22 | 120564078 | 35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 | 0 | 0 | 0 | 0 |  | 2021-05859 | [30 empty] | TRUE | In Scoping |  | 0
35225828 | Top 250 Miles | 9 | MEET | MEET | 2021274 |  | 8.4214 | 8.4214 | 2021 |  |  | 0 | 1136.42 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 25.3345 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.05 | 120426405 | 35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | 42608 | 575 | 1282 | 0 |  | 2021-05891 | 48470.4 | 9.18 | [10 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234387 | Top 250 Miles | 9 | MEET | No | 2021275 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.23 | 120564102 | 35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35234388 | Top 250 Miles | 9 | MEET | No | 2021276 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.24 | 120564104 | 35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35234389 | Top 250 Miles | 9 | MEET | No | 2021277 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.25 | 120564107 | 35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35234390 | Top 250 Miles | 9 | MEET | No | 2021278 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.26 | 120564108 | 35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35234391 | Top 250 Miles | 9 | MEET | No | 2021279 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.27 | 120564120 | 35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35234392 | Top 250 Miles | 9 | MEET | No | 2021280 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.28 | 120564121 | 35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 | 0 | 0 | 0 | 0 |  | 2021-05891 | [30 empty] | TRUE | In Scoping |  | 0
35225829 | Top 250 Miles | 9 | MEET | No | 2021281 |  | 11.1205 | 11.1205 | 2021 |  |  | 0 | 709.34 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 32.6259 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.06 | 120426406 | 35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | 58716 | 0 | 0 | 0 |  | 2021-05936 | 58713.6 | 11.12 | [10 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234393 | Top 250 Miles | 9 | MEET | No | 2021282 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.29 | 120564122 | 35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | 0 | 0 | 0 | 0 |  | 2021-05936 | [30 empty] | TRUE | In Scoping |  | 0
35234394 | Top 250 Miles | 9 | MEET | No | 2021283 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.30 | 120564123 | 35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | 0 | 0 | 0 | 0 |  | 2021-05936 | [30 empty] | TRUE | In Scoping |  | 0
35234395 | Top 250 Miles | 9 | MEET | No | 2021284 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.31 | 120564126 | 35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | 0 | 0 | 0 | 0 |  | 2021-05936 | [30 empty] | TRUE | In Scoping |  | 0
35234396 | Top 250 Miles | 9 | MEET | No | 2021285 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.32 | 120564127 | 35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 | 0 | 0 | 0 | 0 |  | 2021-05936 | [30 empty] | TRUE | In Scoping |  | 0
35234397 | Top 250 Miles | 9 | MEET | No | 2021286 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.33 | 120564129 | 35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | 0 | 0 | 0 | 0 |  | 2021-05936 | [30 empty] | TRUE | In Scoping |  | 0
35219287 | Top 250 Miles | 9 | MEET | MEET | 2021287 |  | 9.5263 | 9.5263 | 2021 |  |  | 0 | 9913.45 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 28.047 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.01 | 120142356 | 35219287 | CWSP - OREGON TRAIL 110335002 PH 6.1 | 50011 | 0 | 288 | 0 |  | 2021-06038 | 46992 | 8.9 | [5 empty] | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234398 | Top 250 Miles | 9 | MEET | No | 2021288 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.34 | 120564152 | 35234398 | CWSP - OREGON TRAIL 110335002 PH 6.2 | 0 | 0 | 0 | 0 |  | 2021-06038 | [30 empty] | TRUE | In Scoping |  | 0
35234399 | Top 250 Miles | 9 | MEET | No | 2021289 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.35 | 120564153 | 35234399 | CWSP - OREGON TRAIL 110335002 PH 6.3 | 0 | 0 | 0 | 0 |  | 2021-06038 | [30 empty] | TRUE | In Scoping |  | 0
35234400 | Top 250 Miles | 9 | MEET | No | 2021290 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.36 | 120564154 | 35234400 | CWSP - OREGON TRAIL 110335002 PH 6.4 | 0 | 0 | 0 | 0 |  | 2021-06038 | [30 empty] | TRUE | In Scoping |  | 0
35234401 | Top 250 Miles | 9 | MEET | No | 2021291 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.37 | 120564155 | 35234401 | CWSP - OREGON TRAIL 110335002 PH 6.5 | 0 | 0 | 0 | 0 |  | 2021-06038 | [30 empty] | TRUE | In Scoping |  | 0
35219267 | Top 250 Miles | 10 | MEET | No | 2021292 |  | 4.27 | 4.27 | 2021 |  |  | 0 | 7536.52 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 9.9007 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.02 | 120142033 | 35219267 | CWSP - MARIPOSA 2102440236 PH 1.1 | 22545.6 | 0 | 0 | 0 |  | 2021-01697 | 45302.4 | 8.58 | 950000 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219587 | Top 250 Miles | 10 | MEET | No | 2021293 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 606.27 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.03 | 120165147 | 35219587 | CWSP - MARIPOSA 2102440236 PH 1.2 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219588 | Top 250 Miles | 10 | MEET | No | 2021294 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 305.76 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.04 | 120165148 | 35219588 | CWSP - MARIPOSA 2102440236 PH 1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219589 | Top 250 Miles | 13 | MEET | No | 2021295 |  | 3.03 | 3.03 | 2021 |  |  | 0 | 10742.17 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 3.1142 |  | Tier 2 | CWSP | PLATINA | Shasta | North Valley | Northern | 5794561 | E.5034719.01.01 | 120165231 | 35219589 | CWSP - WILDWOOD 11011454 | 14836.8 | 0 | 0 | 0 |  | 2021-01188 | 15048 | 2.85 | 2940110 | 2021-04308 |  |  | 14837 | 14837 | 2.81 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35224321 | Top 250 Miles | 13 | MEET | No | 2021296 |  | 2.46 | 2.46 | 2021 |  |  | 0 | 4955.21 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 2.5283 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.01 | 120401277 | 35224321 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.1 | 12988.8 | 0 | 0 | 0 |  | 2021-01193 | 26664 | 5.05 | 7710294 | 2021-04257 |  |  | 12989 | 12989 | 2.46 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226798 | Top 250 Miles | 13 | MEET | No | 2021297 |  | 1.72 | 1.72 | 2021 |  |  | 0 | 217.2 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 1.7678 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.02 | 120450942 | 35226798 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.2 | 9081.6 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 9082 | 9082 | 1.7201 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226799 | Top 250 Miles | 13 | MEET | No | 2021298 |  | 0.19 | 0.19 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.19528 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.03 | 120450944 | 35226799 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.3 | 1003.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 1003 | 1003 | 0.18996 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226900 | Top 250 Miles | 13 | MEET | No | 2021299 |  | 0.69 | 0.69 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.70917 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.04 | 120450946 | 35226900 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.4 | 3643.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 3643 | 3643 | 0.68996 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219590 | Top 250 Miles | 9 | MEET | No | 2021300 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 385.66 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | 91 | 5.3817 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.02 | 120165232 | 35219590 | CWSP - VACA DIXON 1105965390 | 3960 | 0 | 0 | 0 |  | 2021-01565 | 3168 | 0.6 | 1047680 | [9 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35219591 | Top 250 Miles | 9 | MEET | No | 2021301 |  | 2.88 | 2.88 | 2021 |  |  | 0 | 152.97 | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | 7.3096 |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.01 | 120173637 | 35219591 | CWSP - OLETA 1101754718 PH 1.1 | 15206.4 | 0 | 0 | 0 |  | 2021-08929 | [12 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 0
35236662 | Top 250 Miles | 9 | MEET | No |  |  | 0 | 0 |  |  |  | 0 |  | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | #DIV/0! |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.02 | 120618060 | 35236662 | CWSP - OLETA 1101754718 PH 1.2 | 0 | 0 | 0 | 0 | [32 empty] | FALSE | In Scoping |  | 0 | New order
35192053 | Storm Rebuild | 20 | No | No | 2021302 |  | 1.97 | 1.97 | 2021 |  |  | 0 | 972832.92 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.036346 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034391.01 | 119554059 | 35192053 | STRM - OAKHURST 1103 - LR 5120 PH 1 | 10401.6 | 0 | 0 | 0 | N/A | 2021-04765 | 21965 | 4.16 | 7671845 | [9 empty] | 0 | 2021-04813 |  |  |  | 10401.6 | 10401.6 | 1.97
35227096 | Storm Rebuild | 20 | No | No | 2021303 |  | 1.0602 | 1.0602 | 2021 |  |  | 0 | 194307.81 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.019561 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.01 | 120457011 | 35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | 5598 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04843 |  |  |  | 5598 | 5598 | 1.0602
35227201 | Storm Rebuild | 19 | No | No | 2021304 |  | 0.82481 | 0.82481 | 2021 |  |  | 0 | 199814.78 | UNSC | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.015218 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.02 | 120457012 | 35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | 4355 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04837 |  |  |  | 4355 | 4355 | 0.82481
35228449 | Storm Rebuild | 19 | MEET | No | 2021305 | 2.89 | 2.8937 | 2.8937 | 2021 |  |  | 0 | 795091.79 | UNSC | 192251102 | RIO DELL 1102 | Rio Dell 11024230 | 59 | 22.9009 | 585 | 7.9721 | 0.13512 | 1331 | 0.62455 | 3088 | Tier 2 | STRM | MYERS FLAT | HUMBOLDT | HUMBOLDT | NORTHERN | 5795392 |  | 120481753 | 35228449 | Rio Dell Storm Rebuild | 15279 | 0 | 0 | 0 | N/A | N/A | 15279 | 2.8937 | 5469187.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0 | 2021-06858 | 2021-11321 | 0 | 0 | 15279 | 15279 | 2.8937 | 9426416 | 12825799 | 616.9524
35226240 | Top 250 Miles | 14 | MEET | No | 2021225 |  | 1.4625 | 1.4625 | 2021 |  |  | 0 | 34659.33 | ESTS | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7131 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.03 | 120431332 | 35226240 | CWSP - MARIPOSA 210197142 PH 3 | 7722 | 0 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021 | Not on MPP WP Change request not yet submitted
35219272 | Top 250 Miles | 14 | MEET | No | 2021227 |  | 0.85436 | 0.85436 | 2021 |  |  | 0 | 8598 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | 46 | 4.0641 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.02 | 120142171 | 35219272 | CWSP - MIDDLETOWN 1101481876 | 4511 | 0 | 0 | 0 |  | 2020-88311 | 4857.6 | 0.92 | 1280000 | 2021-04297 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219273 | Top 250 Miles | 14 | MEET | No | 2021228 | 3.46 | 3.461 | 3.461 | 2021 |  |  | 0 | 9004.69 | ESTS | 102541101 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | 6 | 8.0246 |  | Tier 2 | CWSP | MANTON | Tehama | North Valley | Northern | 5794543 | E.5034705.01.01 | 120142173 | 35219273 | CWSP - VOLTA 110149742 | 18274 | 0 | 0 | 0 |  | 2021-00903 | 18374.4 | 3.48 | 8182317 | 2021-03779 | 0 | 0 | 18744 | 18744 | 3.55 | 6700000 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35219275 | Top 250 Miles | 17 | MEET | No | 2021229 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 5860.46 | APPR | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | 96 | 8.7599 |  | Tier 2 | CWSP | WINTERS | Solano | Sacramento | Northern | 5543347 | E.5034706.01.01 | 120142210 | 35219275 | CWSP - PUTAH CREEK 110246012 | 2745.6 | 0 | 0 | 0 |  | 2020-88233 | 2745.6 | 0.52 | 566066 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225589 | Top 50 Miles | 14 | MEET | No | 2022004 | 1.3852 | 1.0983 | 1.0983 | 2021 |  |  | 0 | 31647.51 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 5.6145 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.02 | 120423768 | 35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 5799 | 0 | 0 | 0 |  | 2020-81645 | [12 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35225591 | Top 50 Miles | 14 | MEET | MEET | 2022005 | 1.857 | 1.4723 | 1.4723 | 2021 |  |  | 0 | 28447.2 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 9.4535 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.03 | 120423769 | 35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 4527 | 0 | 3247 | 0 |  | 2020-81645 | [12 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35217268 | Top 50 Miles | 14 | MEET | MEET | 2022006 |  | 0.25795 | 0.25795 | 2021 |  |  | 0 | 16622.75 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 0.34672 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.01 | 120047659 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 1158 | 204 | 0 | 0 | 2020-81775 | 2020-81782 | 21436.8 | 4.06 | 6144137 | 2021-03744 |  | 9662.4 | 11774.4 | 21436.8 | 4.06 |  |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35224712 | Top 50 Miles | 14 | MEET | MEET | 2022007 |  | 3.2869 | 3.2869 | 2021 |  |  | 0 | 0 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 6.3054 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.02 | 120427328 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 1222 | 16133 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35224713 | Top 50 Miles | 14 | MEET | MEET | 2022008 |  | 1.8655 | 1.8655 | 2021 |  |  | 0 | 0 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 3.6531 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.03 | 120427329 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 160 | 9690 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35062375 | Top 20% MAVF CPZ | 14 | MEET | MEET | 2022009 | 1.11 | 1.0902 | 1.0902 | 2021 |  |  | 0 | 30474.26 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.7865 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783068 | E.5015571.01 | 115323921 | 35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 0 | 5756 | 0 | 0 |  | 2018-89225 | 63518.4 | 12.03 | 13033162 | 2021-04169 | 0 | 5861 | 0 | 5861 | 1.11 | 1698679.6353 |  |  | 0 | [17 empty] | TRUE | Scoped | TRUE | 2021
35191319 | ECOP - Top 20% | 13 | MEET | MEET | 2022010 | 1.04 | 1.1705 | 1.1705 | 2021 |  |  | 0 | 16760.5 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 2.8131 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5541305 | E.5034355.01 | 119518398 | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH1 | 0 | 6180 | 0 | 0 |  | 2020-76901 | 5491.2 | 1.04 | 1673104 | 2021-02773 | 0 | 5985 | 0 | 5985 | 1.1335 | 2201900 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35223615 | ECOP - Top 20% | 13 | MEET | MEET | 2022011 |  | 1.6258 | 1.6258 | 2021 |  |  | 0 | 521.99 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 3.9074 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5795129 | E.5034355.02 | 120401360 | 35223615 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH2 | 0 | 8584 | 0 | 0 |  | 2020-76901 | 0 | 0 | 0 | 2021-02773 | 0 | 8465 | 0 | 8465 | 1.6032 | 3288180 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227030 | ECOP - Top 20% | 13 | MEET | MEET | 2022012 |  | 1.7072 | 1.7072 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 2.5275 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.29 | 120449801 | 35227030 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.5 | 2233 | 6781 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 6781 | 2233 | 9014 | 1.7072 | 2820684 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227031 | ECOP - Top 20% | 13 | MEET | MEET | 2022013 |  | 2.03 | 2.03 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.0193 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.30 | 120449802 | 35227031 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.6 | 2534.4 | 8184 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 7672 | 2834 | 10506 | 1.9898 | 3192728 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35192282 | ECOP - Top 20% | 13 | MEET | MEET | 2022014 |  | 2.2621 | 2.2621 | 2021 |  |  | 0 | 20927.1 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.6907 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792098 | E.5034407.01 | 119556300 | 35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.1 | 0 | 11944 | 0 | 0 | 2020-78129 | 2020-78306 | 40920 | 7.75 | 11896580 | 2021-03830 | 0 | 11944 |  | 11944 | 2.2621 | 4133200 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226621 | ECOP - Top 20% | 13 | MEET | MEET | 2022015 |  | 2.6562 | 2.6562 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.9941 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.01 | 120445224 | 35226621 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.2 | 2941 | 11084 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 11084 | 2941 | 14025 | 2.6562 | 4029758 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35192292 | ECOP - Top 20% | 13 | MEET | MEET | 2022016 |  | 0.95114 | 0.95114 | 2021 |  |  | 0 | 54096.84 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 1.0419 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5792094 | E.5034403.01 | 119556108 | 35192292 | ECOP - FULTON 1107 - H02-LR604 Ph 1.1 | 830 | 4192 | 0 | 0 | 2020-78732 | 2020-78779 | 19800 | 3.75 | 4686150 | 2021-02767 | 0 | 4192 | 830 | 5022 | 0.95114 | 1887200 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35225594 | ECOP - Top 20% | 13 | MEET | MEET | 2022017 |  | 0.5286 | 0.5286 | 2021 |  |  | 0 | 1447.31 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.5956 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.01 | 120424183 | 35225594 | ECOP - FULTON 1107 - H02-LR604 Ph 1.2 | 261 | 2530 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 2530 | 389 | 2919 | 0.55284 | 864959 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35174478 | ECOP - Top 20% | 13 | MEET | MEET | 2022018 |  | 1.79 | 1.79 | 2021 |  |  | 0 | 8194.28 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.0704 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790111 | E.5033917.01 | 118913024 | 35174478 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.1 | 0 | 9451.2 | 0 | 0 | 2020-51635 | 2020-51816 | 21489.6 | 4.07 | 6162189 | 2021-04465 | 0 | 9463 | 518 | 9981 | 1.8903 | 3159460 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226857 | ECOP - Top 20% | 13 | MEET | MEET | 2022019 |  | 1.94 | 1.94 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.3277 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.01 | 120449200 | 35226857 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.2 | 0 | 10243.2 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 10242 | 0 | 10242 | 1.9398 | 3613740 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226858 | ECOP - Top 20% | 13 | MEET | MEET | 2022020 |  | 0.74295 | 0.74295 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0502 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.02 | 120449201 | 35226858 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.3 | 1900.8 | 0 | 2022 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 2022 | 0 | 1889 | 3911 | 0.74072 | 510683 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226859 | ECOP - Top 20% | 13 | MEET | No | 2022021 |  | 0.88 | 0.88 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.94531 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.03 | 120449202 | 35226859 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.4 | 4646.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 0 | 4659 | 4659 | 0.88239 | 1123574 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226861 | ECOP - Top 20% | 13 | MEET | No | 2022022 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.80566 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.04 | 120449203 | 35226861 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.5 | 3960 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3986 | 3986 | 0.75492 | 824385 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226862 | ECOP - Top 20% | 13 | MEET | No | 2022023 |  | 0.58 | 0.58 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.62305 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.05 | 120449204 | 35226862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.6 | 3062.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3073 | 3073 | 0.58201 | 635558 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35174501 | ECOP - Top 20% | 13 | MEET | MEET | 2022024 |  | 1.683 | 1.683 | 2021 |  |  | 0 | 22873.41 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.8867 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790112 | E.5033919.01 | 118913026 | 35174501 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.1 | 0 | 8886 | 0 | 0 | 2020-53723 | 2020-53724 | 50952 | 9.65 | 16768361 | 2021-04463 | 0 | 8886 | 0 | 8886 | 1.683 | 18931272.7273 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227007 | ECOP - Top 20% | 13 | MEET | MEET | 2022025 |  | 1.1288 | 1.1288 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9362 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.19 | 120449533 | 35227007 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.2 | 0 | 5960 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 5960 | 0 | 5960 | 1.1288 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227010 | ECOP - Top 20% | 13 | MEET | No | 2022026 |  | 0.15985 | 0.15985 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.17171 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.20 | 120449536 | 35227010 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.3 | 844 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 844 | 844 | 0.15985 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227013 | ECOP - Top 20% | 13 | MEET | No | 2022027 |  | 0.026894 | 0.026894 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.02889 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.21 | 120449539 | 35227013 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.4 | 142 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 142 | 142 | 0.026894 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227015 | ECOP - Top 20% | 13 | MEET | No | 2022028 |  | 0.95758 | 0.95758 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0286 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.22 | 120449710 | 35227015 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.5 | 5056 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 5056 | 5056 | 0.95758 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227018 | ECOP - Top 20% | 13 | MEET | No | 2022029 |  | 1.2 | 1.2 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2891 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.23 | 120449711 | 35227018 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.6 | 6336 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 6336 | 6336 | 1.2 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227021 | ECOP - Top 20% | 13 | MEET | No | 2022030 |  | 0.21989 | 0.21989 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.23621 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.24 | 120449712 | 35227021 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.7 | 1161 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 1161 | 1161 | 0.21989 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227025 | ECOP - Top 20% | 13 | MEET | MEET | 2022031 |  | 0.7536 | 0.7536 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0184 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.25 | 120449714 | 35227025 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.8 | 2259 | 1720 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 1720 | 2259 | 3979 | 0.7536 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35234756 | ECOP - Top 20% | 13 | MEET | MEET | 2022032 |  | 2.782 | 2.782 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 4.7719 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.31 | 120580906 | 35234756 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.9 | 0 | 14689 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 14689 | 0 | 14689 | 2.782 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234758 | ECOP - Top 20% | 13 | MEET | MEET | 2022033 |  | 0.58201 | 0.58201 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99831 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.32 | 120580957 | 35234758 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.10 | 0 | 3073 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3073 | 0 | 3073 | 0.58201 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234862 | ECOP - Top 20% | 13 | MEET | MEET | 2022034 |  | 0.079924 | 0.079924 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.13709 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.33 | 120580959 | 35234862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.11 | 0 | 422 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 422 | 0 | 422 | 0.079924 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35234865 | ECOP - Top 20% | 13 | MEET | MEET | 2022035 |  | 0.64754 | 0.64754 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.1107 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.34 | 120581001 | 35234865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.12 | 0 | 3419 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3419 | 0 | 3419 | 0.64754 | 0 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 0
35192291 | ECOP | 13 | No | MEET | 2022036 |  | 1.0972 | 1.0972 | 2021 |  |  | 0 | 17752.99 | UNSE | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.1858 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792093 | E.5034402.01 | 119556091 | 35192291 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 1 | 521 | 5272 | 0 | 0 |  | 2020-69602 | 15100.8 | 2.86 | 3208863 | 2021-04462 | 0 | 5272 | 521 | 5793 | 1.0972 | 2442393 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35191937 | ECOP | 13 | No | No | 2022037 |  | 1.4528 | 1.4528 | 2021 |  |  | 0 | 14993.88 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.61524 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5792064 | E.5034372.01 | 119553837 | 35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1 | 7671 | 0 | 0 | 0 | 2020-61147 | 2020-61154 | 17635.2 | 3.34 | 3777700 | 2021-04460 |  | 4540.8 | 13094.4 | 17635.2 | 3.34 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227032 | ECOP | 13 | No | No | 2022038 |  | 0.575 | 0.575 | 2021 |  |  | 0 | 0 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.2435 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.01 | 120449806 | 35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 2 | 3036 | 0 | 0 | 0 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227033 | ECOP | 13 | No | No | 2022039 |  | 1.31 | 1.31 | 2021 |  |  | 0 | 0 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.88583 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.02 | 120449807 | 35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 3 | 0 | 0 | 0 | 6917 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219093 | Top 50 Miles | 13 | MEET | MEET | 2022040 | 1.14 | 1.14 | 1.14 | 2021 |  |  | 0 | 6576.02 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.0351 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.01 | 120141622 | 35219093 | CWSP - TIDEWATER 210614072 PH 1 | 0 | 6019.2 | 0 | 0 |  | 2020-87771 | 25396.8 | 4.81 | 8092656 | 2021-08732 | 0 | 6019.2 | 0 | 6019.2 | 1.14 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35231543 | Top 50 Miles | 13 | MEET | MEET | 2022041 | 1.3 | 1.3 | 1.3 | 2021 |  |  | 0 | 0 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.8821 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.02 | 120504099 | 35231543 | CWSP - TIDEWATER 210614072 PH 2 | 0 | 6864 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 6864 | 0 | 6864 | 1.3 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217273 | Top 50 Miles | 13 | MEET | MEET | 2022042 | 1.1133 | 1.1055 | 1.1055 | 2021 |  |  | 0 | 14756.58 | UNSE | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | 90 | 3.6826 |  | Tier 2 | CWSP | UPPER LAKE | Lake | North Coast | Northern | 5794203 | E.5034612.01.01 | 120048019 | 35217273 | CWSP - UPPER LAKE 1101 CB | 240 | 0 | 5596.8 | 0 | 2020-81991 | 2020-82007 | 211.2 | 0.04 | 970000 |  | 5596.8 |  | 211.2 | 5808 | 1.1 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217272 | Top 50 Miles | 13 | MEET | MEET | 2022043 | 0.3 | 0.34053 | 0.34053 | 2021 |  |  | 0 | 24256.47 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 2.1677 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.01 | 120048018 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1 | 94 | 1704 | 0 | 0 | 2020-81561 | 2020-82753 | 42926.4 | 8.13 | 22711843 | 2021-03825 |  | 34161.6 | 8764.8 | 42926.4 | 8.13 |  | 41.75 | 31200 | 747.3054 | [17 empty] | TRUE | In Scoping |  | 2021
35226628 | Top 50 Miles | 13 | MEET | MEET | 2022044 | 0.82 | 0.81913 | 0.81913 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.3182 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.03 | 120445377 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 3 | 0 | 4325 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226629 | Top 50 Miles | 13 | MEET | MEET | 2022045 | 4.5 | 4.6972 | 4.6972 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 30.4963 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.04 | 120445378 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 4 | 0 | 24801 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217269 | Top 50 Miles | 13 | MEET | MEET | 2022046 | 0.23222 | 0.52083 | 0.52083 | 2021 |  |  | 0 | 15574.94 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.8658 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.01 | 120048011 | 35217269 | SH - MIDDLETOWN 1102 LR 302610 PH 1 | 630 | 2120 | 0 | 0 | 2020-81207 | 2020-81139 | 26294.4 | 4.98 | 6542572 | 2021-04671 |  | 9240 | 17054.4 | 26294.4 | 4.98 |  | 39.7 | 22200 | 559.194 | [17 empty] | TRUE | In Scoping |  | 2021
35226819 | Top 50 Miles | 13 | MEET | No | 2022047 | 0.58899 | 1.321 | 1.321 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 8.4527 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.02 | 120456652 | 35226819 | SH - MIDDLETOWN 1102 LR 302610 PH 2 | 6975 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227160 | Top 50 Miles | 13 | MEET | MEET | 2022048 | 1.2676 | 2.843 | 2.843 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 28.9198 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.03 | 120456653 | 35227160 | SH - MIDDLETOWN 1102 LR 302610 PH 3 | 176 | 14835 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227161 | Top 50 Miles | 13 | MEET | No | 2022049 | 0.32578 | 0.73068 | 0.73068 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.6753 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.04 | 120456654 | 35227161 | SH - MIDDLETOWN 1102 LR 302610 PH 4 | 3858 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227162 | Top 50 Miles | 13 | MEET | MEET | 2022050 | 0.18628 | 0.4178 | 0.4178 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.2687 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.05 | 120456655 | 35227162 | SH - MIDDLETOWN 1102 LR 302610 PH 5 | 0 | 2206 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227163 | Top 50 Miles | 13 | MEET | No | 2022051 | 0.18333 | 0.41117 | 0.41117 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 2.6309 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.06 | 120456657 | 35227163 | SH - MIDDLETOWN 1102 LR 302610 PH 6 | 2171 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227164 | Top 50 Miles | 13 | MEET | No | 2022052 | 0.24919 | 0.5589 | 0.5589 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 3.5762 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.07 | 120456658 | 35227164 | SH - MIDDLETOWN 1102 LR 302610 PH 7 | 2951 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217270 | Top 50 Miles | 13 | MEET | No | 2022053 | 0.72665 | 0.57614 | 0.57614 | 2021 |  |  | 0 | 35945.14 | UNSE | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 2.9452 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.01 | 120048013 | 35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 3042 | 0 | 0 | 0 | 2020-81626 | 2020-81645 | 11035.2 | 2.09 | 2458800 |  |  |  | 11035.2 | 11035.2 | 2.09 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35217271 | Top 50 Miles | 13 | MEET | MEET | 2022054 |  | 2.8496 | 2.8496 | 2021 |  |  | 0 | 47097.09 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 15.4448 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.01 | 120048017 | 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 0 | 15046 | 0 | 0 |  | 2020-87776 | 38016 | 7.2 | 11000000 | 2021-05676 | 0 | 15046 | 0 | 15046 | 2.8496 | 5487320 | 34.46 | 31600 | 917.0052 | [17 empty] | TRUE | In Scoping |  | 2021
35227864 | Top 50 Miles | 13 | MEET | MEET | 2022055 |  | 1.8392 | 1.8392 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.9684 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.11 | 120462234 | 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 0 | 9711 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 9711 | 0 | 9711 | 1.8392 | 3498820 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35220895 | Top 50 Miles | 13 | MEET | MEET | 2022056 |  | 2.1489 | 2.1489 | 2021 |  |  | 0 | 13660.71 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 11.2106 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.02 | 120221891 | 35220895 | CWSP - MIDDLETOWN 1103 LR 830 PH2.1 | 1137 | 10209 | 0 | 0 |  | 2020-87780 | 48681.6 | 9.22 | 7050000 | 2021-06302 | 0 | 10209 | 1137 | 11346 | 2.1489 | 3553334 | 19.39 | 18300 | 943.7855 | [17 empty] | TRUE | In Scoping |  | 2021
35228186 | Top 50 Miles | 13 | MEET | MEET | 2022057 |  | 1.4847 | 1.4847 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.0468 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.15 | 120475322 | 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 0 | 7839 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 7839 | 0 | 7839 | 1.4847 | 2916780 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35220896 | Top 50 Miles | 13 | MEET | MEET | 2022058 |  | 0.2803 | 0.2803 | 2021 |  |  | 0 | 6986.57 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.5192 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.03 | 120222356 | 35220896 | CWSP - MIDDLETOWN 1103 LR 830 PH3.1 | 0 | 1480 | 0 | 0 |  | 2020-87782 | 19219.2 | 3.64 | 3976000 | 2021-04672 | 0 | 1480 | 0 | 1480 | 0.2803 | 653600 | 21.1 | 23300 | 1104.2654 | [17 empty] | TRUE | In Scoping |  | 0
35227165 | Top 50 Miles | 13 | MEET | MEET | 2022059 |  | 1.0112 | 1.0112 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.4805 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.04 | 120456740 | 35227165 | CWSP - MIDDLETOWN 1103 LR 830 PH3.2 | 0 | 5339 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 5339 | 0 | 5339 | 1.0112 | 1743480 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227167 | Top 50 Miles | 13 | MEET | MEET | 2022060 |  | 1.7975 | 1.7975 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.7426 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.05 | 120456741 | 35227167 | CWSP - MIDDLETOWN 1103 LR 830 PH3.3 | 0 | 9491 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 9491 | 0 | 9491 | 1.7975 | 3107120 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227168 | Top 50 Miles | 13 | MEET | MEET | 2022061 |  | 1.5741 | 1.5741 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.5313 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.06 | 120456742 | 35227168 | CWSP - MIDDLETOWN 1103 LR 830 PH3.4 | 0 | 8311 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 8311 | 0 | 8311 | 1.5741 | 2764520 | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35062374 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022062 | 1.56 | 1.5352 | 1.5352 | 2021 |  |  | 0 | 47327.61 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.9241 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783067 | E.5015572.01 | 115323920 | 35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 0 | 8106 | 0 | 0 |  | 2018-89221 | 45038.4 | 8.53 | 9171850 | 2021-04171 | 0 | 8237 | 0 | 8237 | 1.56 | 2427043.6218 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35231608 | Top 20% MAVF CPZ | 13 | MEET | No | 2022063 | 0.32992 | 0.16212 | 0.16212 | 2021 |  |  | 0 | 928.03 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.25951 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.12 | 120504095 | 35231608 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 856 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 1742 | 0 | 1742 | 0.32992 | 513282.7473 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226849 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022064 | 1.7799 | 1.7833 | 1.7833 | 2021 |  |  | 0 | 372.25 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 4.5583 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.04 | 120449142 | 35226849 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 0 | 9416 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 9398 | 0 | 9398 | 1.7799 | 2723799.8997 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35062376 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022065 | 2.53 | 4.3231 | 4.3231 | 2021 |  |  | 0 | 21370.26 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 13.4088 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783069 | E.5015570.01 | 115323922 | 35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 0 | 22826 | 0 | 0 |  | 2018-89227 | 58080 | 11 | 11965840 | 2021-05102 | 0 | 13358.4 | 0 | 13358.4 | 2.53 | 4751652.1664 |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219096 | Top 250 Miles | 13 | MEET | MEET | 2022066 |  | 1.67 | 1.67 | 2021 |  |  | 0 | 6407.72 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 5.297 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.01 | 120141671 | 35219096 | CWSP - KIRKER 2104442850 PH 1 | 0 | 8817.6 | 0 | 0 |  | 2021-01226 | 9240 | 1.75 | 4945020 |  |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35227655 | Top 250 Miles | 13 | MEET | No | 2022067 |  | 3.77 | 3.77 | 2021 |  |  | 0 | 0 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 7.4888 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.02 | 120462115 | 35227655 | CWSP - KIRKER 2104442850 PH 2 | 19905.6 | 0 | 0 | 0 | [14 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35226700 | Top 250 Miles | 13 | MEET | MEET | 2022068 | 0.46 | 0.45758 | 0.45758 | 2021 |  |  | 0 | 0 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 2.6834 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034802.01.02 | 120447112 | 35226700 | CWSP - WYANDOTTE 110932586 PH 2 | 0 | 2416 | 0 | 0 |  | 2021-01235 |  |  |  | 2021-04349 | [6 empty] | 0 | 0 | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35219281 | Top 250 Miles | 13 | MEET | MEET | 2022069 |  | 2.5 | 2.5 | 2021 |  |  | 0 | 18741.89 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 10.9428 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.01 | 120142240 | 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.1 | 0 | 13200 | 0 | 0 |  | 2021-00875 | 30940.8 | 5.86 | 8236794 | 2021-10593 |  |  |  | 0 | 0 |  |  |  | 0 | [17 empty] | TRUE | In Scoping |  | 2021
35232650 | Top 250 Miles | 13 | MEET | MEET | 2022070 |  | 1.71 | 1.71 | 2021 |  |  | 0 |  | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 7.485 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.02 | 120529254 | 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 0 | 9029 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0 | [17 empty] | TRUE | In Scoping |  | 2021

## Project List
Order | KEEP | Exec. Status | LTIP Condition 1 | LTIP Condition 2 | Priority | Original OH Miles | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | 2018 KPMG CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notif. | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | EASOP Risk Reduced | EASOP NPV ($000) | EASOP RSE | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost | In DOT | Scope status | On MPP Workplan | MPP Project year | Comments
35212495 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.65 | 0 | 2020 |  |  | 7.65 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101233716 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.04 | 119985141 | 35212495 | FRRB - AUBERRY 1101 LR233716 | - | - | - | - | [9 empty] | 0 | 0
35212464 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.48 | 0 | 2020 |  |  | 0.48 | 0 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101886282 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793893 | E.5034566.01.07 | 119983588 | 35212464 | FRRB - CALISTOGA 1101 LR 886282 | - | - | - | - | [9 empty] | 0 | 0
35212487 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.82 | 0 | 2020 |  |  | 1.82 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011034 | 80 | 11.1511 | 1566 | 1.9751 | 0.024689 | 1434 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.06 | 119983959 | 35212487 | FRRB - KANAKA 1101 LR1034 | - | - | - | - | [9 empty] | 0 | 0
35212460 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 17.43 | 3 | 2020 |  |  | 14.43 | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 110114605 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.03 | 119983565 | 35212460 | FRRB - RINCON 1101 LR 14605 | - | - | - | - | [9 empty] | 0 | 0
35212466 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.94 | 0.68 | 2020 |  |  | 8.26 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | 147 | 13.8344 | 64 | 57.5327 | 0.39138 | 108 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.02 | 119984990 | 35212466 | FRRB - VACAVILLE 1108 LR 8762 | - | - | - | - | [9 empty] | 0 | 0
35212490 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.44 | 0.72 | 2020 |  |  | 4.72 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 1101323094 | 208 | 36.1569 | 117 | 66.6373 | 0.32037 | 234 | #VALUE! |  |  | FRRB | IGO | Shasta | North Valley | Northern | 5793919 | E.5034573.01.02 | 119984003 | 35212490 | FRRB - GIRVAN 1101 LR323094 | - | - | - | - | [9 empty] | 0 | 0
35212465 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.34 | 0 | 2020 |  |  | 6.34 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | 232 | 15.9209 | 122 | 73.4796 | 0.31672 | 99 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.01 | 119933526 | 35212465 | FRRB - VACAVILLE 1108 LR 38316 | - | - | - | - | [9 empty] | 0 | 0
35212406 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110137384 | 71 | 9.3736 | 557 | 10.17 | 0.14324 | 391 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.06 | 119983061 | 35212406 | FRRB - MONTICELLO 1101 LR 37384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212408 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.58 | 0 | 2020 |  |  | 1.58 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | 205 | 25.7758 | 579 | 27.9958 | 0.13657 | 473 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.08 | 119983069 | 35212408 | FRRB - SILVERADO 2102 LR 34959 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212489 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.16 | -2.24 | 2020 |  |  | 6.4 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 11011330 | 264 | 31.0696 | 624 | 33.0087 | 0.12503 | 651 | #VALUE! |  |  | FRRB | REDDING | Shasta | North Valley | Northern | 5793919 | E.5034573.01.01 | 119933733 | 35212489 | FRRB - GIRVAN 1101 LR1330 | - | - | - | - | [9 empty] | 0 | 0
35212411 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.17 | 0 | 2020 |  |  | 0.17 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104722 | 99 | 7.8964 | 690 | 11.1613 | 0.11274 | 1130 | #VALUE! |  |  | FRRB | DEER PARK | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.11 | 119983147 | 35212411 | FRRB - SILVERADO 2104 LR 722 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212404 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5 | 0 | 2020 |  |  | 5 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101630 | 93 | 18.7154 | 732 | 9.7794 | 0.10515 | 552 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.04 | 119982981 | 35212404 | FRRB - MONTICELLO 1101 LR 630 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35122401 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.31 | 0 | 2020 |  |  | 7.31 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101CB | 5 | 0.53443 | 775 | 0.49137 | 0.098274 | 904 | #VALUE! |  |  | FRRB | STRAWBERRY VALLEY | Yuba | North Valley | Northern | 5793892 | E.5034565.01.01 | 119933522 | 35122401 | FRRB - MONTICELLO 1101 CB | - | - | - | - |  |  |  | 0 |  | 2019-39360 |  |  |  | 0 | 0
35212402 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.42 | 0 | 2020 |  |  | 2.42 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101666 | 90 | 12.0959 | 815 | 8.2843 | 0.092048 | 588 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.02 | 119982885 | 35212402 | FRRB - MONTICELLO 1101 LR 666 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212491 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | 0 | 2020 |  |  | 0.96 | 0 | UNSE | 252531103 | SAN JOAQUIN #3 | SAN JOAQUIN #3 11035100 | 204 | 21.334 | 829 | 18.2004 | 0.089218 | 667 | #VALUE! |  |  | FRRB | NORTH FORK | Madera | Yosemite | Central Valley | 5793920 | E.5034574.01.01 | 119933734 | 35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | - | - | - | - | [9 empty] | 0 | 0
35212479 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7 | 3.84 | 2020 |  |  | 3.16 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.01 | 119933732 | 35212479 | FRRB - BIG BEND 1102 CB | - | - | - | - | [9 empty] | 0 | 0
35212405 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.9 | 0 | 2020 |  |  | 11.9 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110193384 | 101 | 16.1387 | 914 | 7.9369 | 0.078583 | 632 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.05 | 119982987 | 35212405 | FRRB - MONTICELLO 1101 LR 93384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212494 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | 0 | 2020 |  |  | 1.38 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 110137536 | 60 | 5.3994 | 934 | 4.5309 | 0.075515 | 511 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.03 | 119984007 | 35212494 | FRRB - AUBERRY 1101 LR37536 | - | - | - | - | [9 empty] | 0 | 0
35212418 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 13.7 | 0 | 2020 |  |  | 13.7 | 0 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | #VALUE! |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.01 | 119933523 | 35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | - | - | - | - | [9 empty] | 0 | 0
35212481 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.52 | 0.87 | 2020 |  |  | 10.65 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.03 | 119983951 | 35212481 | FRRB - WYANDOTTE 1103 LR1508 | - | - | - | - | [9 empty] | 0 | 0
35212492 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.05 | 0 | 2020 |  |  | 3.05 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R2845 | 172 | 17.8248 | 1209 | 8.1154 | 0.047182 | 811 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.01 | 119933735 | 35212492 | FRRB - AUBERRY 1101 R2845 | - | - | - | - | [9 empty] | 0 | 0
35212403 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.58 | 0 | 2020 |  |  | 3.58 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101654 | 71 | 8.2164 | 1227 | 3.2338 | 0.045547 | 1126 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.03 | 119982889 | 35212403 | FRRB - MONTICELLO 1101 LR 654 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212412 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.13 | -0.58 | 2020 |  |  | 4.71 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 210437632 | 304 | 26.5819 | 1235 | 13.5588 | 0.044601 | 1426 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.12 | 119983231 | 35212412 | FRRB - SILVERADO 2104 LR 37632 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212480 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.12 | 3.74 | 2020 |  |  | 2.38 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.02 | 119983950 | 35212480 | FRRB - BIG BEND 1102 LR1972 | - | - | - | - | [9 empty] | 0 | 0
35212463 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.5 | 0 | 2020 |  |  | 7.5 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103474 | 174 | 18.3351 | 1342 | 6.4055 | 0.036813 | 1399 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.06 | 119983582 | 35212463 | FRRB - RINCON 1103 LR 474 | - | - | - | - | [9 empty] | 0 | 0
35212413 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | -2.25 | 2020 |  |  | 3.63 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.13 | 119983363 | 35212413 | FRRB - SILVERADO 2105 LR 658898 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212496 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.26 | -0.37 | 2020 |  |  | 2.63 | 0 | UNSE | 192411101 | LOW GAP 1101 | LOW GAP 1101CB | 23 | 2.1692 | 1385 | 0.78267 | 0.034029 | 1600 | #VALUE! |  |  | FRRB | ZENIA | Trinity | Humboldt | Northern | 5793922 | E.5034576.01.01 | 119933736 | 35212496 | FRRB - LOW GAP 1101 | - | - | - | - | [9 empty] | 0 | 0
35212471 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.83 | 0 | 2020 |  |  | 1.83 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 | 1508 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.04 | 119983629 | 35212471 | FRRB - POINT MORETTI 1101 LR5076 | - | - | - | - | [9 empty] | 0 | 0
35212473 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.21 | 0 | 2020 |  |  | 2.21 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110210254 | 11 | 2.1441 | 1421 | 0.35552 | 0.03232 | 1814 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.06 | 119983704 | 35212473 | FRRB - BIG BASIN 1102 LR10254 | - | - | - | - | [9 empty] | 0 | 0
35212416 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.252 | 0 | 2020 |  |  | 1.252 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.16 | 119983454 | 35212416 | FRRB - CALISTOGA 1102 LR 634 | - | - | - | - | [9 empty] | 0 | 0
35212486 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 9.46 | 5.02 | 2020 |  |  | 4.44 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.05 | 119983955 | 35212486 | FRRB - KANAKA 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212407 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | -0.19 | 2020 |  |  | 1.15 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 2102636 | 81 | 5.465 | 1550 | 2.0483 | 0.025287 | 1827 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.07 | 119983066 | 35212407 | FRRB - SILVERADO 2102 LR 636 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212462 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.16 | -0.35 | 2020 |  |  | 12.51 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103198 | 62 | 6.4238 | 1618 | 1.3987 | 0.02256 | 1658 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.05 | 119983580 | 35212462 | FRRB - RINCON 1103 LR 198 | - | - | - | - | [9 empty] | 0 | 0
35212417 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.2 | 0.18 | 2020 |  |  | 4.02 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | 160 | 11.021 | 1624 | 3.574 | 0.022338 | 1749 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.17 | 119983463 | 35212417 | FRRB - CALISTOGA 1102 LR 769230 | - | - | - | - | [9 empty] | 0 | 0
35212410 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.41 | 0 | 2020 |  |  | 0.41 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | 61 | 3.7544 | 1648 | 1.292 | 0.02118 | 1771 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.10 | 119983145 | 35212410 | FRRB - SILVERADO 2104 LR 708 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212419 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | 28 | 2.6414 | 1684 | 0.54085 | 0.019316 | 1689 | #VALUE! |  |  | FRRB | KENWOOD | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.02 | 119983560 | 35212419 | FRRB - DUNBAR 1101 - LR 416 | - | - | - | - | [9 empty] | 0 | 0
35212488 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.74 | 0.34 | 2020 |  |  | 4.4 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011406 | 204 | 27.2731 | 1728 | 3.5397 | 0.017352 | 1755 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.07 | 119984001 | 35212488 | FRRB - KANAKA 1101 LR1406 | - | - | - | - | [9 empty] | 0 | 0
35212478 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.99 | 0 | 2020 |  |  | 7.99 | 0 | UNSE | 83392110 | SWIFT 2110 | SWIFT 2110XR332 | 83 | 18.4582 | 1769 | 1.2892 | 0.015532 | 1452 | #VALUE! |  |  | FRRB | LIVERMORE | Santa Clara | San Jose | Central Coast | 5793897 | E.5034571.01.01 | 119933730 | 35212478 | FRRB - SWIFT 2110 XR332 | - | - | - | - | [9 empty] | 0 | 0
35212483 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.53 | 11 | 2020 |  |  | 1.53 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.04 | 119983953 | 35212483 | FRRB - WYANDOTTE 1103 LR1974 | - | - | - | - | [9 empty] | 0 | 0
35212414 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0.24 | 2020 |  |  | 0.98 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105131568 | 57 | 4.1385 | 1947 | 0.58604 | 0.010281 | 2060 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.14 | 119983432 | 35212414 | FRRB - SILVERADO 2105 LR 131568 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212409 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.97 | 0 | 2020 |  |  | 0.97 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104645 | 13 | 1.0111 | 2117 | 0.085285 | 0.0065604 | 2103 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.09 | 119983129 | 35212409 | FRRB - SILVERADO 2104 LR 645 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212415 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.31 | 0 | 2020 |  |  | 2.31 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | 70 | 9.5796 | 2174 | 0.39281 | 0.0056116 | 2203 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.15 | 119983433 | 35212415 | FRRB - SILVERADO 2105 LR 167360 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212467 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0 | 2020 |  |  | 1.22 | 0 | UNSE | 182371111 | LAURELES 1111 | LAURELES 11112020 | 281 | 34.3538 | 2187 | 1.5107 | 0.005376 | 2260 | #VALUE! |  |  | FRRB | CARMEL VALLEY | Monterey | Central Coast | Central Coast | 5793895 | E.5034568.01.01 | 119933604 | 35212467 | FRRB - LAURELES 1111 LR 2020 | - | - | - | - | [9 empty] | 0 | 0
35212469 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.23 | 2.95 | 2020 |  |  | 2.28 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 63 | 6.5695 | 2199 | 0.32133 | 0.0051004 | 2205 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.02 | 119983626 | 35212469 | FRRB - POINT MORETTI 1101 LR12122 | - | - | - | - | [9 empty] | 0 | 0
35212493 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.92 | 3.6 | 2020 |  |  | 5.32 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R324 | 119 | 10.7137 | 2209 | 0.5799 | 0.0048731 | 1904 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.02 | 119984006 | 35212493 | FRRB - AUBERRY 1101 R324 | - | - | - | - | [9 empty] | 0 | 0
35212470 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.77 | 0 | 2020 |  |  | 0.77 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110183716 | 22 | 2.503 | 2210 | 0.10689 | 0.0048588 | 2187 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.03 | 119983627 | 35212470 | FRRB - POINT MORETTI 1101 LR83716 | - | - | - | - | [9 empty] | 0 | 0
35212461 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 1101663641 | 13 | 0.72937 | 2309 | 0.043609 | 0.0033545 | 2307 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.04 | 119983567 | 35212461 | FRRB - RINCON 1101 LR 663641 | - | - | - | - | [9 empty] | 0 | 0
35212474 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.52 | 0 | 2020 |  |  | 0.52 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 70 | 5.982 | 2358 | 0.20629 | 0.002947 | 2611 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.07 | 119983709 | 35212474 | FRRB - BIG BASIN 1102 LR12758 | - | - | - | - | [9 empty] | 0 | 0
35212472 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.51 | 1.37 | 2020 |  |  | 1.14 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | 121 | 13.7481 | 2359 | 0.35169 | 0.0029066 | 2514 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.05 | 119983702 | 35212472 | FRRB - BIG BASIN 1102 LR5066 | - | - | - | - | [9 empty] | 0 | 0
35212475 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.09 | 0 | 2020 |  |  | 3.09 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 1101CB | 45 | 4.6531 | 2398 | 0.11632 | 0.0025849 | 2594 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.08 | 119983868 | 35212475 | FRRB - BIG BASIN 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212477 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.59 | 0 | 2020 |  |  | 0.59 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | 44 | 4.71 | 2435 | 0.10045 | 0.002283 | 2730 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.10 | 119983869 | 35212477 | FRRB - BIG BASIN 1101 LR10720 | - | - | - | - | [9 empty] | 0 | 0
35212468 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.89 | 0 | 2020 |  |  | 0.89 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136516 | 53 | 4.1639 | 2542 | 0.08431 | 0.0015908 | 2704 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.01 | 119933606 | 35212468 | FRRB - POINT MORETTI 1101 LR36516 | - | - | - | - | [9 empty] | 0 | 0
35212476 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.58 | 0 | 2020 |  |  | 2.58 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 11015000 | 23 | 1.9571 | 2579 | 0.031772 | 0.0013814 | 2834 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.09 | 119985051 | 35212476 | FRRB - BIG BASIN 1101 LR5000 | - | - | - | - | [9 empty] | 0 | 0
74022384 | In-Construction | 20 | MEET | No | 2021001 | 5.6 | 5.4458 | 4.4858 | 2020 | 0.96 |  | 0.96 | 7133317.26 | CONS | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | 799 | 4.7409 | 209 | Tier 3 | PRE | GEYSERVILLE | Sonoma | Sonoma | Northern | 5782860 | E.5015487.01 | 114753320 | 74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 28754 | 0 | 0 | 0 |  | 2018-55406 | 29568 | 5.6 | 5959500 | N/A | 0 | 0 | 29040 | 29040 | 5.5 | 10560000 |  |  | 0 | 2019-34744 | 2019-02348 | 0 | 0 | 28754 | 28754 | 5.4458 | [9 empty] | TRUE | Scoped | TRUE | 2021
35157845 | In-Construction | 20 | No | No | 2021002 | 1.27 | 1.2676 | 1.2676 | 2020 | 0 |  | 0 | 431041.62 | CONS | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | 0.24713 | 104 | Tier 2 | WDDB | SAINT HELENA | Napa | North Bay | Bay Area | 5784869 | E.5014317.04 | 116952175 | 35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 6693 | 0 | 0 | 0 |  | N/A |  |  |  | N/A | 0 | 0 | 6705.6 | 6705.6 | 1.27 | 2438400 |  |  | 0 | 2020-03939 | 2020-42595 | 0 | 0 | 6693 | 6693 | 1.2676 | 1404334 | 1800634 | 209.8213 | [6 empty] | TRUE | Scoped | TRUE | 2021
35119965 | In-Construction | 18 | No | No | 2021003 | 0.87 | 0.84905 | 0.84905 | 2020 | 0 |  | 0 | 764949.39 | PEND | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.072413 | 841 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786602 | E.5014534.05 | 117721840 | 35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 4483 | 0 | 0 | 0 |  | 2018-31656 | 8077 | 1.5297 | 903333 | 2018-53540 | 0 | 0 | 1584 | 1584 | 0.3 | 576000 |  |  | 0 | 2019-78779 | 2020-24016 | 4483 | 0 | 4483 | 4483 | 0.84905 | 1435425 | 1924210 | 320.193 | [6 empty] | TRUE | Scoped | TRUE | 2021
35094397 | In-Construction | 20 | No | No | 2021004 | 0.87 | 1.0646 | 1.0646 | 2020 | 0 |  | 0 | 1301754.83 | DOCC | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.076193 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785167 | E.5015029.11 | 117131100 | 35094397 | CWSP-KONOCTI 1102-LR 532-PH10 | 5621 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 |  |  | 0 | 2019-62948 | 2020-36368 | 0 | 0 | 5621 | 5621 | 1.0646 | 1438986 | 1733017 | 256.0018 | [6 empty] | TRUE | Scoped | TRUE | 2021
35061206 | In-Construction | 20 | No | No | 2021005 | 1.966 | 1.7652 | 1.7652 | 2020 | 0 |  | 0 | 2046932.97 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.076892 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783070 | E.5015569.01 | 115106231 | 35061206 | CWSP-BRUNSWICK 1103-LR50070-PH 1.1 | 9320 | 0 | 0 | 0 |  | 2018-85016 | 10380.48 | 1.966 | 2108720 | 2019-76345 | 0 | 0 | 9320 | 9320 | 1.7652 | 3389090.9091 |  |  | 0 | 2020-03978 | 2020-30766 | 0 | 0 | 9320 | 9320 | 1.7652 | 3459498 | 4711641 | 371.1908 | [6 empty] | TRUE | Scoped | TRUE | 2021
35117443 | In-Construction | 20 | No | No | 2021006 | 1.543 | 2.1581 | 2.1581 | 2020 | 0 |  | 0 | 2018722.86 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.094012 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5786518 | E.5015567.06 | 117634567 | 35117443 | CWSP-BRUNSWICK 1103-LR50070-PH 3.6 | 11395 | 0 | 0 | 0 |  | 2018-85051 | 8147.04 | 1.543 | 1630650 | 2019-76353 | 0 | 0 | 11395 | 11395 | 2.1581 | 4143636.3636 |  |  | 0 | 2020-32576 | 2020-42958 | 0 | 0 | 11395 | 11395 | 2.1581 | 4475708 | 5778810 | 392.7782 | [6 empty] | TRUE | Scoped | TRUE | 2021
35061212 | In-Construction | 20 | No | No | 2021007 | 9 | 1.7888 | 1.7888 | 2020 | 0 |  | 0 | 1548567.12 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.077924 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783071 | E.5015568.01 | 115106486 | 35061212 | CWSP-BRUNSWICK 1103-LR50070-PH 2.1 | 9445 | 0 | 0 | 0 |  | 2018-85027 | 47520 | 9 | 9533800 | 2019-76348 | 0 | 0 | 9445 | 9445 | 1.7888 | 3434545.4545 |  |  | 0 | 2020-06702 | 2020-46891 | 0 | 0 | 9445 | 9445 | 1.7888 | 3890031 | 4913095 | 411.8614 |  | 2020-04589 |  |  |  |  | TRUE | Scoped | TRUE | 2021
35115151 | In-Construction | 20 | No | No | 2021008 | 2.25 | 1.8964 | 1.8964 | 2020 | 0 |  | 0 | 1293779.94 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.08261 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785721 | E.5015568.02 | 117493857 | 35115151 | CWSP-BRUNSWICK 1103-LR50070-PH 2.2 | 10013 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 | 0 | 0 | 10013 | 10013 | 1.8964 | 3641090.9091 |  |  | 0 | 2020-23454 | 2020-46448 | 0 | 0 | 10013 | 10013 | 1.8964 | 4025667 | 5273989 | 402.044 |  | 2020-38642 |  |  |  |  | TRUE | Scoped | TRUE | 2021
35115152 | In-Construction - 2 | 20 | No | No | 2021009 |  | 1.57 | 1.57 | 2021 |  |  | 0 | 444280.95 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.068391 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785722 | E.5015568.03 | 117495855 | 35115152 | CWSP-BRUNSWICK 1103-LR50070-PH 2.3 | 8271 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 |  |  |  | 0 | 0 | 0 |  |  |  | 2020-55781 | 2020-58697 | 0 | 0 | 8271 | 8271 | 1.5665 | 2679486 | 3591121 | 323.9616 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116383 | In-Construction | 20 | No | No | 2021010 | 1.97 | 1.3862 | 1.3862 | 2020 | 0 |  | 0 | 991398.25 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.036514 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785966 | E.5014733.02 | 117604600 | 35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 7319 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 7080 | 7080 | 1.3409 | 2574545.4545 |  |  | 0 | 2019-60218 | 2020-25651 | 0 | 0 | 7319 | 7319 | 1.3862 | 2547023 | 3758449 | 348.0015 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116384 | In-Construction | 20 | No | No | 2021011 | 1.97 | 1.8371 | 1.6671 | 2020 | 0.17 |  | 0.17 | 121782.96 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.048393 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785967 | E.5014733.03 | 117604604 | 35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 9700 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 9715 | 9715 | 1.84 | 3532727.2727 |  |  | 0 | 2020-00930 | 2020-48509 | 0 | 0 | 9700 | 9700 | 1.8371 | 3239382 | 4624169 | 333.9569 | [6 empty] | TRUE | Scoped | TRUE | 2021
35114048 | In-Construction | 20 | No | No | 2021012 | 15.9024 | 1.3909 | 1.3909 | 2020 | 0 |  | 0 | 889880.15 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.040923 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785997 | E.5014742.03 | 117499466 | 35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7344 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7382 | 7382 | 1.3981 | 2684363.6364 |  |  | 0 | 2019-73207 | 2020-43723 | 0 | 0 | 7344 | 7344 | 1.3909 | 3133899 | 4178929 | 426.7292 | [6 empty] | TRUE | Scoped | TRUE | 2021
35114051 | In-Construction - 2 | 20 | No | No | 2021013 |  | 1.44 | 1.44 | 2021 |  |  | 0 | 558652.57 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.042367 | 2 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786000 | E.5014742.06 | 117502234 | 35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 7698 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7628 | 7628 | 1.4447 | 2773818.1818 |  |  |  | 2019-72313 | 2020-47316 | 0 | 0 | 7698 | 7698 | 1.458 | 3949678 | 5342998 | 513.0785 | [6 empty] | TRUE | Scoped | TRUE | 2021
35115054 | In-Construction | 20 | No | No | 2021014 | 1.96 | 1.4259 | 1.3959 | 2020 | 0.03 |  | 0.03 | 1016834.07 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.030421 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785986 | E.5015427.02 | 117490035 | 35115054 | CWSP-MIWUK 1701-OCB-PH 2.2 | 7529 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 7255 | 7255 | 1.3741 | 2638181.8182 |  |  | 0 | 2019-53298 | 2020-44293 | 0 | 0 | 7529 | 7529 | 1.4259 | 2482662 | 3789178 | 329.7466 | [6 empty] | TRUE | Scoped | TRUE | 2021
35115050 | In-Construction | 20 | No | No | 2021015 | 2.304 | 1.6121 | 1.6121 | 2020 | 0 |  | 0 | 875800.67 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.034393 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785972 | E.5014771.02 | 117495948 | 35115050 | CWSP-MIWUK 1701–OCB-PH 1.2 | 8512 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 8270 | 8270 | 1.5663 | 3007272.7273 |  |  | 0 | 2019-79491 | 2020-40482 | 0 | 0 | 8512 | 8512 | 1.6121 | 2809593 | 4091239 | 330.0744 | [6 empty] | TRUE | Scoped | TRUE | 2021
35115055 | In-Construction | 20 | No | No | 2021016 | 1.96 | 2.1343 | 2.1343 | 2020 | 0 |  | 0 | 952089.56 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.045533 | 2 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785987 | E.5015427.03 | 117490481 | 35115055 | CWSP-MIWUK 1701-OCB-PH 2.3 | 11269 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 11088 | 11088 | 2.1 | 4032000 |  |  | 0 | 2019-68750 | 2020-34644 | 0 | 0 | 11269 | 11269 | 2.1343 | 2901359 | 3784068 | 257.4638 | [6 empty] | TRUE | Scoped | TRUE | 2021
35115053 | In-Construction | 20 | No | No | 2021017 | 2.304 | 1.7203 | 1.7203 | 2020 | 0 |  | 0 | 634368.78 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.036701 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785975 | E.5014771.05 | 117496041 | 35115053 | CWSP-MIWUK 1701–OCB-PH 1.5 | 9083 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9571 | 9571 | 1.8127 | 3480363.6364 |  |  | 0 | 2020-56266 | 2020-27365 | 0 | 0 | 9083 | 9083 | 1.7203 | 1670418 | 2296559 | 183.906 | [6 empty] | TRUE | Scoped | TRUE | 2021
35052821 | In-Construction | 20 | No | No | 2021018 | 2.304 | 2.0744 | 2.0744 | 2020 | 0 |  | 0 | 611371.23 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.044256 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5784646 | E.5014771.01 | 114593976 | 35052821 | CWSP-MIWUK 1701–OCB-PH 1.1 | 10953 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9750 | 9750 | 1.8466 | 3545454.5455 |  |  | 0 | 2019-52652 | 2020-46847 | 0 | 0 | 10953 | 10953 | 2.0744 | 3322975 | 4765282 | 303.3849 | [6 empty] | TRUE | Scoped | TRUE | 2021
35056746 | In-Construction | 20 | No | No | 2021019 | 1.96 | 2.0335 | 2.0335 | 2020 | 0 |  | 0 | 372655.58 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.043384 | 2 | Tier 3 | PRE | MI WUK VLG | Tuolumne | Yosemite | Central Valley | 5782537 | E.5015427.01 | 114996821 | 35056746 | CWSP-MIWUK 1701-OCB-PH 2.1 | 10737 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 10615 | 10615 | 2.0104 | 3860000 |  |  | 0 | 2019-65579 | 2020-47773 | 0 | 0 | 10737 | 10737 | 2.0335 | 2950902 | 3642331 | 274.8349 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116391 | In-Construction | 20 | No | No | 2021020 | 2.04 | 2.0902 | 0.71015 | 2020 | 1.38 |  | 1.38 | 1688016.64 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.044332 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785976 | E.5014773.02 | 117605551 | 35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 11036 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 10840 | 10840 | 2.053 | 3941818.1818 |  |  | 0 | 2019-64313 | 2020-18345 | 0 | 0 | 11036 | 11036 | 2.0902 | 3920204 | 5835429 | 355.2196 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116395 | In-Construction | 20 | No | No | 2021021 | 2.04 | 1.7106 | 1.7106 | 2020 | 0 |  | 0 | 804930.72 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.036282 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785979 | E.5014773.05 | 117605558 | 35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 9032 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 7500 | 7500 | 1.4205 | 2727272.7273 |  |  | 0 | 2019-57777 | 2020-44284 | 0 | 0 | 9032 | 9032 | 1.7106 | 2479935 | 3714853 | 274.5721 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116800 | In-Construction | 20 | No | No | 2021022 | 1.78 | 1.4252 | 1.1752 | 2020 | 0.25 |  | 0.25 | 1284948.37 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.025962 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785961 | E.5014730.02 | 117605265 | 35116800 | CWSP-MIWUK 1702-LR 6018-PH1.2 | 7525 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 6695 | 6695 | 1.268 | 2434545.4545 |  |  | 0 | 2020-45856 | 2020-18449 | 0 | 0 | 7525 | 7525 | 1.4252 | 2704457 | 4030625 | 359.3963 | [6 empty] | TRUE | Scoped | TRUE | 2021
35114100 | In-Construction | 20 | No | No | 2021023 | 1.61 | 1.0392 | 1.0392 | 2020 | 0 |  | 0 | 413706 | CONS | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.016816 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5786131 | E.5015489.02 | 117545617 | 35114100 | CWSP-CAMP EVERS 2106-LR5020-PH2.2 | 5487 | 0 | 0 | 0 |  | 2018-64516 | 8500.8 | 1.61 | 1747200 | N/A | 0 | 0 | 5491.2 | 5491.2 | 1.04 | 1996800 |  |  | 0 | 2019-82353 | 2020-34359 | 0 | 0 | 5487 | 5487 | 1.0392 | 2119397 | 2502285 | 386.2579 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116442 | In-Construction | 20 | No | No | 2021024 | 1.85 | 2.3458 | 0.55583 | 2020 | 1.79 |  | 1.79 | 1951346.75 | DOCC | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.013106 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785982 | E.5014776.03 | 117605169 | 35116442 | CWSP-MIWUK 1702-LR38218-PH1.3 | 12386 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 11065 | 11065 | 2.0956 | 4023636.3636 |  |  | 0 | 2020-11921 | 2020-34785 | 0 | 0 | 12386 | 12386 | 2.3458 | 2994831 | 3849738 | 241.7916 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116444 | In-Construction | 20 | No | No | 2021025 | 1.85 | 2.1023 | 2.1023 | 2020 | 0 |  | 0 | 775814.94 | CONS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.011746 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785984 | E.5014776.05 | 117605182 | 35116444 | CWSP-MIWUK 1702-LR38218-PH1.5 | 11100 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 9600 | 9600 | 1.8182 | 3490909.0909 |  |  | 0 | 2019-57736 | 2020-27703 | 0 | 0 | 11100 | 11100 | 2.1023 | 2648178 | 3531134 | 238.5746 | [6 empty] | TRUE | Scoped | TRUE | 2021
35052825 | In-Construction | 20 | No | No | 2021026 | 1.95 | 1.1682 | 1.1682 | 2020 | 0 |  | 0 | 472917.86 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | 2641 | 0.0050323 | 26 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785221 | E.5014722.01 | 114701195 | 35052825 | CWSP-MIWUK 1702-LR 8090-PH 1.1 | 6168 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 5785 | 5785 | 1.0956 | 2103636.3636 |  |  | 0 | 2019-54146 | 2020-43899 | 0 | 0 | 6168 | 6168 | 1.1682 | 2342292 | 3544410 | 379.749 | [6 empty] | TRUE | Scoped | TRUE | 2021
35116515 | In-Construction - 2 | 19 | No | No | 2021027 |  | 1.75 | 1.75 | 2021 |  |  | 0 | 152800.55 | UNSC | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.035578 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786036 | E.5015701.02 | 117607998 | 35116515 | CWSP–STANISLAUS 1702-LR1888-PH 1.2 | 9222 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 8765 | 8765 | 1.66 | 3187272.7273 |  |  |  | 2019-69359 | 2020-48497 | 0 | 0 | 9222 | 9222 | 1.7466 | 3203035 | 4438411 | 347.3254 | [6 empty] | TRUE | Scoped | TRUE | 2021
31361965 | In-Construction - 2 | 20 | No | MEET | 2021028 |  | 0.45 | 0.45 | 2021 |  |  | 0 | 267453.44 | CONS | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | 1845 | 0.068224 | 1151 | Tier 3 | WDDB | KENWOOD | Sonoma | Sonoma | Northern | 5530175 |  | 113751296 | 31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 0 | 2367 | 0 | 0 |  | 2018-69430 | 2300 | 0.43561 | 345000 | N/A |  |  |  | 0 | 0 | 0 |  |  | 0 | 2019-35371 | 2019-34365 | 0 | 0 | 2367 | 2367 | 0.4483 | 797947 | 1245293 | 337.1132 | [6 empty] | TRUE | Scoped | FALSE | 0 | Tagged as "Remove" in DOT
31334291 | In-Construction - 2 | 18 | No | No | 2021029 |  | 0.51 | 0.51 | 2021 |  |  | 0 | 357850.19 | PEND | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | 2061 | 0.01337 | 2292 | Tier 3 | WDDB | FORT BRAGG | Mendocino | Humboldt | Northern | 5530164 |  | 112994395 | 31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 2710 | 0 | 0 | 0 |  | 2018-10393 | 1920 | 0.36364 | 212000 | N/A | 0 | 0 | 2692.8 | 2692.8 | 0.51 | 979200 |  |  |  |  | 2019-31651 | 0 | 0 | 2710 | 2710 | 0.51326 | 688000 | 1115000 | 253.8745 |  | 2019-19275 |  |  |  |  | TRUE | Scoped | FALSE | 0 | Tagged as "Remove" in DOT
35085847 | In-Construction - 2 | 18 | No | No | 2021030 |  | 0.86 | 0.86 | 2021 |  |  | 0 | 78122.49 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 7.6345e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5530169 | P.12006 | 113255606 | 35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 4555 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | [5 empty] | 2020-66516 | 0 | 0 | 4555 | 4555 | 0.86269 | 2900525 | 5126422 | 636.7783 | [6 empty] | TRUE | Scoped | TRUE | 2022
35015704 | In-Construction - 2 | 18 | No | No | 2021031 |  | 1 | 1 | 2021 |  |  | 0 | 59156.34 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 8.8773e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5533644 |  | 113255603 | 35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 5300 | 0 | 0 | 0 |  | 2017-105215 | 5300 | 1.0038 | 502000 |  |  |  |  | 0 | 0 | [20 empty] | TRUE | Scoped | TRUE | 2022
35052731 | DSDD | 19 | No | No | 2021032 | 2.43 | 1.4733 | 1.4733 | 2020 | 0 |  | 0 | 148877.35 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.02488 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5782530 | E.5014542.01 | 114607365 | 35052731 | CWSP-BIG BASIN 1101-LR10296-PH 1.1 | 7779 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2020-46872 | 2020-54946 | 0 | 0 | 7779 | 7779 | 1.4733 | 3391041 | 4994628 | 435.9225 | [6 empty] | TRUE | Scoped | TRUE | 2021
35145540 | PSPS - Scoped | 18 | MEET | MEET | 2021033 | 0.5 | 1.2739 | 1.2739 | 2020 | 0 |  | 0 | 217190.06 | PEND | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | 1692 | 1.602 | 3052 | Tier 3 | PSPS | Angels | Calaveras | Stockton | Central Valley | 5788779 | E.5025634 | 118259180 | 35145540 | PSPS – Frogtown 1702 – CB | 0 | 2272 | 4454 | 0 |  | 2019-80603 | 2640 | 0.5 | 3900000 | N/A | 4454 | 2272 | 0 | 6726 | 1.2739 | 2100000 |  |  | 0 | 2020-42690 | [15 empty] | TRUE | Scoped | TRUE | 2021
35094513 | DSDD | 18 | No | No | 2021034 | 1.54 | 1.9112 | 1.9112 | 2020 | 0 |  | 0 | 192432.87 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.0098421 | 19 | Tier 3 | CWSP | ARNOLD | Calaveras | Stockton | Central Valley | 5785245 | E.5014540.01 | 114567769 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10091 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 10091 | 10091 | 1.9112 | 3669454.5455 |  |  | 0 | 2020-43006 | 2021-08435 | [14 empty] | TRUE | Scoped | TRUE | 2021
35145525 | PSPS - Scoped | 18 | MEET | MEET | 2021035 | 1.78 | 1.78 | 1.78 | 2020 | 0 |  | 0 | 156085.26 | PEND | 43321104 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | 2944 | 0.00046978 | 1522 | Tier 2 | PSPS | Santa Rosa | Sonoma | Sonoma | Northern | 5788787 | E.5025638.01 | 118266592 | 35145525 | PSPS - Rincon 1102 and 1104 - CB | 0 | 9398.4 | 0 | 0 |  | 2019-82382 | 9398.4 | 1.78 | 17891818 | N/A | 0 | 9398.4 | 0 | 9398.4 | 1.78 | 7476000 |  |  | 0 | 2020-50683 | [10 empty] | 2020-28718 |  |  |  |  | TRUE | Scoped | TRUE | 2021
35145524 | PSPS - Scoped | 18 | MEET | MEET | 2021036 | 1.5 | 1.5 | 1.5 | 2020 | 0 |  | 0 | 170611.65 | PEND | 43321103 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | 2033 | 0.41019 | 628 | Tier 3 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5788786 | E.5025637 | 118266591 | 35145524 | PSPS - Rincon 1101 and 1103- CB | 0 | 7920 | 0 | 0 |  | 2019-82381 | 7920 | 1.5 | 14953636 | N/A | 0 | 7920 | 0 | 7920 | 1.5 | 6300000 |  |  | 0 | 2020-48279 | [15 empty] | TRUE | Scoped | TRUE | 2021
35137590 | ECOP - Top 20% | 14 | MEET | No | 2021037 | 0.52992 | 0.53485 | 0.53485 | 2021 |  |  | 0 | 32518.21 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | 335 | 3.7019 | 413 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5530164 |  | 118093216 | 35137590 | ECOP-MIDDLETOWN 1101-H02-CB | 2824 | 0 | 0 | 0 |  | 2019-73180 | 2798 | 0.52992 | 564800 | 2020-03-04 | 0 | 0 | 2824 | 2824 | 0.53485 | 1026909.0909 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35137593 | ECOP - Top 20% | 14 | MEET | No | 2021038 | 1.3799 | 1.3775 | 1.3775 | 2021 |  |  | 0 | 31936.06 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.5169 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118125945 | 35137593 | ECOP-MIDDLETOWN 1101-H07-LR4646 | 7273 | 0 | 0 | 0 |  | 2019-73200 | 7286 | 1.3799 | 1454600 | 2020-03-04 | 0 | 0 | 7273 | 7273 | 1.3775 | 2644727.2727 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35137596 | ECOP - Top 20% | 14 | MEET | No | 2021039 | 0.96989 | 0.97178 | 0.97178 | 2021 |  |  | 0 | 9431.74 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.0701 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118127757 | 35137596 | ECOP-MIDDLETOWN 1101-H08-LR4646 | 5131 | 0 | 0 | 0 |  | 2019-73285 | 5121 | 0.96989 | 1026000 | 2020-03-04 | 0 | 0 | 5131 | 5131 | 0.97178 | 1865818.1818 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35192284 | ECOP - Top 20% | 13 | MEET | MEET | 2021040 |  | 1.086 | 1.086 | 2021 |  |  | 0 | 15071.45 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.0802 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5792107 | E.5034416.01 | 119556691 | 35192284 | ECOP - SILVERADO 2104 - H05-LR726 PH1 | 0 | 5734 | 0 | 0 |  | 2020-77337 | 5734 | 1.09 | 6664630 | 2021-00327 | 0 | 5734 | 0 | 5734 | 1.086 | 4505396 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223024 | ECOP - Top 20% | 13 | MEET | MEET | 2021041 |  | 1.2659 | 1.2659 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.4248 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.01 | 120245076 | 35223024 | ECOP - SILVERADO 2104 - H05-LR726 PH2 | 0 | 6684 | 0 | 0 |  | 2020-77337 | 6684 | 1.27 | 0 | 2021-00327 | 0 | 6684 | 0 | 6684 | 1.2659 | 4738320 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223026 | ECOP - Top 20% | 13 | MEET | No | 2021042 |  | 1.0348 | 1.0348 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.2414 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.02 | 120245190 | 35223026 | ECOP - SILVERADO 2104 - H05-LR726 PH3 | 5464 | 0 | 0 | 0 |  | 2020-77337 | 5464 | 1.03 | 0 | 2021-00327 | 0 | 0 | 5464 | 5464 | 1.0348 | 3702224 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223027 | ECOP - Top 20% | 14 | MEET | No | 2021043 |  | 1.5674 | 1.5674 | 2021 |  |  | 0 | 9687.98 | ESTS | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.8803 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.03 | 120245192 | 35223027 | ECOP - SILVERADO 2104 - H05-LR726 PH4 | 8276 | 0 | 0 | 0 |  | 2020-77337 | 8276 | 1.57 | 0 | 2021-00327 | 0 | 0 | 8276 | 8276 | 1.5674 | 1898194 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35223028 | ECOP - Top 20% | 13 | MEET | No | 2021044 |  | 1.208 | 1.208 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.4491 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.04 | 120245193 | 35223028 | ECOP - SILVERADO 2104 - H05-LR726 PH5 | 6378 | 0 | 0 | 0 |  | 2020-77337 | 6378 | 1.21 | 0 | 2021-00327 | 0 | 0 | 6378 | 6378 | 1.208 | 1330059 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35225593 | ECOP - Top 20% | 14 | MEET | No | 2021045 |  | 1.1756 | 1.1756 | 2021 |  |  | 0 | 3814.22 | ESTS | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 1.2261 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5544143 | E.5034791.01 | 120424181 | 35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 6207 | 0 | 0 | 0 | 2020-77593 | 2020-77594 | 0 | 0 | 0 | 2021-02769 | 0 | 0 | 6207 | 6207 | 1.1756 | 1283732 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35192281 | ECOP - Top 20% | 13 | MEET | No | 2021046 |  | 0.30663 | 0.30663 | 2021 |  |  | 0 | 19203.82 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.3133 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792097 | E.5034406.01 | 119556250 | 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.1 | 1619 | 0 | 0 | 0 | 2020-78060 | 2020-78081 | 31363.2 | 5.94 | 8593932 | 2021-04756 | 0 | 0 | 1619 | 1619 | 0.30663 | 344842 | 14.37 | 51800 | 3604.7321 | [16 empty] | TRUE | In Scoping |  | 2021
35227027 | ECOP - Top 20% | 13 | MEET | No | 2021047 |  | 0.97576 | 0.97576 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.997 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.26 | 120449717 | 35227027 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.2 | 5152 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5152 | 5152 | 0.97576 | 1065537 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227028 | ECOP - Top 20% | 13 | MEET | No | 2021048 |  | 0.61723 | 0.61723 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.63067 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.27 | 120449719 | 35227028 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.3 | 3259 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 3259 | 3259 | 0.61723 | 684026 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227029 | ECOP - Top 20% | 13 | MEET | No | 2021049 |  | 1.0886 | 1.0886 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.1123 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.28 | 120449800 | 35227029 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.4 | 5748 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5748 | 5748 | 1.0886 | 1198801 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35236437 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.34 | 0.34 |  |  |  | 0 |  | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.55472 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.35 | 120617837 | 35236437 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.7 | 0 | 1795.2 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35236438 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.48 | 0.48 |  |  |  | 0 |  | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.78314 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.36 | 120617839 | 35236438 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.8 | 0 | 2534.4 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35226622 | ECOP - Top 20% | 13 | MEET | No | 2021050 |  | 0.87841 | 0.87841 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.89753 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.02 | 120445225 | 35226622 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.3 | 4638 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 4638 | 4638 | 0.87841 | 1129975 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226623 | ECOP - Top 20% | 13 | MEET | No | 2021051 |  | 1.2953 | 1.2953 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.3235 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.03 | 120445227 | 35226623 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.4 | 6839 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 6839 | 6839 | 1.2953 | 1454442 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226624 | ECOP - Top 20% | 13 | MEET | No | 2021052 |  | 0.70795 | 0.70795 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.72337 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.04 | 120445228 | 35226624 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.5 | 3738 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 3738 | 3738 | 0.70795 | 783093 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35225595 | ECOP - Top 20% | 13 | MEET | No | 2021053 |  | 0.87803 | 0.87803 | 2021 |  |  | 0 | 869.34 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.64201 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.02 | 120424186 | 35225595 | ECOP - FULTON 1107 - H02-LR604 Ph 1.3 | 4636 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4636 | 4636 | 0.87803 | 2648900 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35225597 | ECOP - Top 20% | 14 | MEET | No | 2021054 |  | 0.77576 | 0.77576 | 2021 |  |  | 0 | 943.79 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.56723 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.03 | 124024187 | 35225597 | ECOP - FULTON 1107 - H02-LR604 Ph 1.4 | 4096 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4096 | 4096 | 0.77576 | 1917600 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225598 | ECOP - Top 20% | 14 | MEET | No | 2021055 |  | 0.88144 | 0.88144 | 2021 |  |  | 0 | 943.79 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.6445 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.04 | 120424188 | 35225598 | ECOP - FULTON 1107 - H02-LR604 Ph 1.5 | 4654 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4654 | 4654 | 0.88144 | 1766100 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35174479 | ECOP - Top 20% | 13 | MEET | No | 2021056 |  | 0.72159 | 0.72159 | 2021 |  |  | 0 | 21891.62 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.77515 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790119 | E.5033918.01 | 118913025 | 35174479 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.1 | 3810 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 48840 | 9.25 | 13481516 | 2021-04464 | 0 | 0 | 3810 | 3810 | 0.72159 | 20851272.7273 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226863 | ECOP - Top 20% | 13 | MEET | No | 2021057 |  | 0.52765 | 0.52765 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.56681 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.06 | 120449205 | 35226863 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.2 | 2786 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2786 | 2786 | 0.52765 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226864 | ECOP - Top 20% | 13 | MEET | No | 2021058 |  | 0.32652 | 0.32652 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.35075 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.07 | 120449207 | 35226864 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.3 | 1724 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1724 | 1724 | 0.32652 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226865 | ECOP - Top 20% | 13 | MEET | No | 2021059 |  | 0.23542 | 0.23542 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.25289 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.08 | 120449208 | 35226865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.4 | 1243 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 |  | 0 | 1243 | 1243 | 0.23542 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226866 | ECOP - Top 20% | 13 | MEET | No | 2021060 |  | 0.51818 | 0.51818 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.55664 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.09 | 120449230 | 35226866 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.5 | 2736 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2736 | 2736 | 0.51818 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226870 | ECOP - Top 20% | 13 | MEET | No | 2021061 |  | 0.41951 | 0.41951 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.45064 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.10 | 120449231 | 35226870 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.6 | 2215 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2215 | 2215 | 0.41951 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226871 | ECOP - Top 20% | 13 | MEET | MEET | 2021062 |  | 1.9117 | 1.9117 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.2398 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.11 | 120449235 | 35226871 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.7 | 420 | 6124 | 3550 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 3205 | 6124 | 420 | 9749 | 1.8464 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226872 | ECOP - Top 20% | 13 | MEET | MEET | 2021063 |  | 1.4881 | 1.4881 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.4242 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.12 | 120449236 | 35226872 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.8 | 1168 | 2552 | 4137 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 2328 | 2552 | 1168 | 6048 | 1.1455 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226873 | ECOP - Top 20% | 13 | MEET | No | 2021064 |  | 1.0394 | 1.0394 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.7829 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.13 | 120449450 | 35226873 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.9 | 0 | 0 | 0 | 5488 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 4734 | 0 | 0 | 4734 | 0.89659 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226878 | ECOP - Top 20% | 13 | MEET | MEET | 2021065 |  | 0.58883 | 0.58883 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.01 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.14 | 120449453 | 35226878 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.10 | 0 | 3109 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3034 | 3034 | 0.57462 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227001 | ECOP - Top 20% | 13 | MEET | MEET | 2021066 |  | 0.7214 | 0.7214 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2374 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.15 | 120449454 | 35227001 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.11 | 0 | 3809 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3591 | 3591 | 0.68011 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227002 | ECOP - Top 20% | 13 | MEET | MEET | 2021067 |  | 0.43295 | 0.43295 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.74264 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.16 | 120449455 | 35227002 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.12 | 0 | 2286 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2286 | 2286 | 0.43295 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227003 | ECOP - Top 20% | 13 | MEET | MEET | 2021068 |  | 0.58087 | 0.58087 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99636 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.17 | 120449456 | 35227003 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.13 | 0 | 3067 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3067 | 3067 | 0.58087 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227004 | ECOP - Top 20% | 13 | MEET | MEET | 2021069 |  | 0.3483 | 0.3483 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.59743 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.18 | 120449457 | 35227004 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.14 | 0 | 1839 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1763 | 1763 | 0.3339 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35236439 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 1.12 | 1.12 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9211 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.37 | 120617881 | 35236439 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.15 | 0 | 5913.6 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35236660 | ECOP - Top 20% | 13 | MEET | MEET |  |  | 0.48 | 0.48 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.82334 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.38 | 120617882 | 35236660 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH2.16 | 0 | 2534.4 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35191318 | ECOP - Top 20% | 14 | MEET | No | 2021070 |  | 2.2159 | 2.2159 | 2021 |  |  | 0 | 17697.86 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 1.32 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541303 | E.5034352.01 | 119518390 | 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 11700 | 0 | 0 | 0 | 2020-76797 | 2020-76801 | 11721.6 | 2.22 | 1685400 | 2021-00256 | 0 | 0 | 11700 | 11700 | 2.2159 | 2027400 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35191383 | ECOP - Top 20% | 14 | MEET | No | 2021071 |  | 1.3286 | 1.3286 | 2021 |  |  | 0 | 16640.95 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 0.79143 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541309 | E.5034359.01 | 119518528 | 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 7015 | 0 | 0 | 0 |  | 2020-78168 | 7022.4 | 1.33 | 1143750 | 2021-00326 | 0 | 0 | 7015 | 7015 | 1.3286 | 1175890 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35192290 | ECOP | 13 | No | No | 2021072 |  | 5.0004 | 5.0004 | 2021 |  |  | 0 | 11659.49 | ESTS | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 3.5024 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792092 | E.5034401.01 | 119556075 | 35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 26402 | 0 | 0 | 0 |  | 2020-66261 | 26400 | 5 | 5575214 | 2021-04162 | 0 | 0 | 26402 | 26402 | 5.0004 | 5633062 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226845 | ECOP | 14 | No | No | 2021073 |  | 2.3674 | 2.3674 | 2021 |  |  | 0 | 1039.61 | ESTS | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.6582 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5795298 | E.5034803.01.01 | 120448987 | 35226845 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 2 | 12500 | 0 | 0 | 0 |  | 2020-69602 |  |  |  | 2021-04462 | 0 | 0 | 12500 | 12500 | 2.3674 | 2880250 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35231544 | Top 50 Miles | 13 | MEET | No | 2021074 | 1.2 | 1.2 | 1.2 | 2021 |  |  | 0 | 0 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 3.9785 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.03 | 120504131 | 35231544 | CWSP - TIDEWATER 210614072 PH 3 | 6336 | 0 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 0 | 6336 | 6336 | 1.2 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226627 | Top 50 Miles | 13 | MEET | No | 2021075 | 0.29 | 0.31231 | 0.31231 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 1.2699 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.02 | 120445375 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 2 | 1649 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226630 | Top 50 Miles | 13 | MEET | No | 2021076 | 1.44 | 1.4061 | 1.4061 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.7171 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.05 | 120445421 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 5 | 7424 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226631 | Top 50 Miles | 13 | MEET | No | 2021077 | 1.54 | 1.5326 | 1.5326 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 6.2315 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.06 | 120445423 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 6 | 8092 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217267 | Top 50 Miles | 14 | MEET | No | 2021078 | 0.71281 | 0.71 | 0.71 | 2021 |  |  | 0 | 46774.47 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | 26 | 6.6788 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794209 | E.5034606.01.01 | 120047657 | 35217267 | CWSP - MARIPOSA 2102 LR 241564 | 3748.8 | 0 | 0 | 0 |  | 2020-83810 | 3748.8 | 0.71 | 804541 |  |  |  | 3748.8 | 3748.8 | 0.71 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35227860 | Top 50 Miles | 13 | MEET | No | 2021079 |  | 0.19583 | 0.19583 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.66472 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.07 | 120462186 | 35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 1034 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 1034 | 1034 | 0.19583 | 223852 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227861 | Top 50 Miles | 13 | MEET | No | 2021080 |  | 1.5339 | 1.5339 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.2066 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.08 | 120462188 | 35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 8099 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 8099 | 8099 | 1.5339 | 1685035 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227862 | Top 50 Miles | 13 | MEET | No | 2021081 |  | 0.93466 | 0.93466 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.1725 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.09 | 120462232 | 35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 4935 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4935 | 4935 | 0.93466 | 1020657 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227863 | Top 50 Miles | 13 | MEET | No | 2021082 |  | 0.79129 | 0.79129 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.6859 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.10 | 120462233 | 35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 4178 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4178 | 4178 | 0.79129 | 874094 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227866 | Top 50 Miles | 13 | MEET | No | 2021083 |  | 0.52386 | 0.52386 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.12 | 120462238 | 35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 2766 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2766 | 2766 | 0.52386 | 592064 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227867 | Top 50 Miles | 13 | MEET | No | 2021084 |  | 0.99527 | 0.99527 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.3782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.13 | 120462241 | 35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 5255 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 5255 | 5255 | 0.99527 | 1116839 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227868 | Top 50 Miles | 13 | MEET | No | 2021085 |  | 0.51686 | 0.51686 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7544 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.14 | 120462242 | 35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 2729 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2729 | 2729 | 0.51686 | 584412 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35228187 | Top 50 Miles | 13 | MEET | No | 2021086 |  | 0.62879 | 0.62879 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.1343 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.16 | 120475324 | 35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | 3320 | 0 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 0 | 3320 | 3320 | 0.62879 | 733000 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35228188 | Top 50 Miles | 13 | MEET | MEET | 2021087 |  | 3.73 | 3.73 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 20.4207 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.17 | 120475326 | 35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | 0 | 0 | 19694.4 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 19694 | 0 | 0 | 19694 | 3.7299 | 667600 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35236661 | Top 50 Miles | 13 |  |  |  |  | 0.22 | 0.22 |  |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.74675 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.18 | 120617883 | 35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | 1161.6 | 0 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35222045 | Top 50 Miles | 13 | MEET | No | 2021088 |  | 0.88864 | 0.88864 | 2021 |  |  | 0 | 5980.16 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.0163 |  |  | CWSP | MIDDLETOWN | Napa | Humboldt | Northern | 5794898 | E.5034741.01.01 | 120233319 | 35222045 | CWSP - MIDDLETOWN 1103 LR 830 PH4 | 4692 | 0 | 0 | 0 | N/A | 2020-87784 | 3907.2 | 0.74 | 808000 | 2021-03692 | 0 | 0 | 4692 | 4692 | 0.88864 | 970399 | 3.02 | 2500 | 827.8146 | [16 empty] | TRUE | In Scoping |  | 0
35226846 | Top 20% MAVF CPZ | 14 | MEET | No | 2021089 | 1.54 | 1.5714 | 1.5714 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.5154 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.01 | 120448989 | 35226846 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 8297 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 8131 | 8131 | 1.54 | 2395810.5729 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226847 | Top 20% MAVF CPZ | 14 | MEET | No | 2021090 | 1.9299 | 1.9839 | 1.9839 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.1757 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.02 | 120449140 | 35226847 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 10475 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 10190 | 10190 | 1.9299 | 3002497.8155 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35231607 | Top 20% MAVF CPZ | 14 | MEET | No | 2021091 | 1.4799 | 1.646 | 1.646 | 2021 |  |  | 0 | 928.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.6349 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.11 | 120504093 | 35231607 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 8691 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7814 | 7814 | 1.4799 | 2302406.0776 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35231609 | Top 20% MAVF CPZ | 13 | MEET | No | 2021092 | 1.3299 | 1.3301 | 1.3301 | 2021 |  |  | 0 | 0 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.1292 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.13 | 120504096 | 35231609 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 7023 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7022 | 7022 | 1.3299 | 2069042.1649 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226848 | Top 20% MAVF CPZ | 14 | MEET | No | 2021093 | 2.8701 | 2.4445 | 2.4445 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.913 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.03 | 120449141 | 35226848 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 12907 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 15154 | 15154 | 2.8701 | 4392047.6357 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226850 | Top 20% MAVF CPZ | 14 | MEET | No | 2021094 | 2.29 | 1.5451 | 1.5451 | 2021 |  |  | 0 | 515 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.4733 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.05 | 120449143 | 35226850 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 8158 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 9187 | 9187 | 1.74 | 2662646.2735 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226851 | Top 20% MAVF CPZ | 14 | MEET | No | 2021095 | 2.19 | 1.8784 | 1.8784 | 2021 |  |  | 0 | 297.8 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.0069 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.06 | 120449144 | 35226851 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 9918 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 11563 | 11563 | 2.19 | 3351276.6802 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35232280 | Top 20% MAVF CPZ | 14 | MEET | No | 2021096 | 0.6 | 0.6 | 0.6 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.96045 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.14 | 120527401 | 35232280 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 3168 | 0 | 0 | 0 | [5 empty] | 2021-04169 | 3168 | 0 | 0 | 3168 | 0.6 | 918173.8755 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226852 | Top 20% MAVF CPZ | 14 | MEET | No | 2021097 | 2.93 | 2.4932 | 2.4932 | 2021 |  |  | 0 | 696.05 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 4.8429 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.07 | 120449145 | 35226852 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.2 | 13164 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 15470.4 | 15470.4 | 2.93 | 5502901.5208 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226853 | Top 20% MAVF CPZ | 14 | MEET | No | 2021098 | 2.92 | 2.8044 | 2.8044 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 5.4473 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.08 | 120449146 | 35226853 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 14807 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 264 | 15153.6 | 15417.6 | 2.92 | 5484120.2869 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226854 | Top 20% MAVF CPZ | 14 | MEET | No | 2021099 | 1.03 | 1.0299 | 1.0299 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 2.0006 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.09 | 120449147 | 35226854 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 5438 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 5438.4 | 0 | 0 | 5438.4 | 1.03 | 1934467.0875 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226856 | Top 20% MAVF CPZ | 14 | MEET | No | 2021100 | 4.53 | 1.9436 | 1.9436 | 2021 |  |  | 0 | 0 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 3.7753 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.10 | 120449149 | 35226856 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 10262 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 23918.4 | 23918.4 | 4.53 | 8507898.9383 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35054184 | Top 20% MAVF CPZ | 10 | MEET | No | 2021101 |  | 0.91 | 0.91 | 2021 |  |  | 0 | 22124.95 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.60664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5530173 | E.5019937.01.01 | 114941996 | 35054184 | CWSP-COLUMBIA HILL 1101-TS8233-PH1 | 4804.8 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 4805 | 0.91004 | 5227500 | 2021-03589 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35226659 | Top 20% MAVF CPZ | 10 | MEET | MEET | 2021102 |  | 1.88 | 1.88 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.5835 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.02 | 120447026 | 35226659 | CWSP-COLUMBIA HILL 1101-TS8233-PH2 | 5544 | 4382.4 | 0 | 0 | 2018-69650 | 2018-72909 | 9926 | 1.8799 |  | 2021-03589 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35226720 | Top 20% MAVF CPZ | 10 | MEET | No | 2021103 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.34665 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.03 | 120447027 | 35226720 | CWSP-COLUMBIA HILL 1101-TS8233-PH3 | 2745.6 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 2746 | 0.52008 |  | 2021-03589 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35226723 | Top 20% MAVF CPZ | 10 | MEET | MEET | 2021104 |  | 1.04 | 1.04 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.99964 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.04 | 120447110 | 35226723 | CWSP-COLUMBIA HILL 1101-TS8233-PH4 | 1425.6 | 4065.6 | 0 | 0 | 2018-69650 | 2018-72909 | 5492 | 1.0402 |  | 2021-03589 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227204 | Top 20% MAVF CPZ | 10 | MEET | No | 2021105 |  | 1.3 | 1.3 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.86664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.05 | 120447111 | 35227204 | CWSP-COLUMBIA HILL 1101-TS8233-PH5 | 6864 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 6864 | 1.3 |  | 2021-03589 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35026643 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2021106 | 1.63 | 1.6339 | 1.6339 | 2021 |  |  | 0 | 59465.39 | UNSE | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | 755 | 1.5795 | 957 | Tier 2 | WDDB | DIAMOND SPRINGS | El Dorado | Sierra | Northern | 5530173 |  | 114258488 | 35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 5727 | 0 | 2900 | 0 | n/a | 2018-38234 | 7400 | 1.4015 | 2100000 | 2021-03592 |  |  |  | 0 | 0 |  | 1.58 | 2900 | 1835.443 | [16 empty] | TRUE | In Scoping |  | 2021
35075103 | Top 20% MAVF CPZ | 17 | MEET | No | 2021107 |  | 0.59 | 0.59 | 2021 |  |  | 0 | 73818.65 | APPR | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | 564 | 0.39202 | 1409 | Tier 3 | WDDB | MURPHYS | Calaveras | Stockton | Central Valley | 5530176 |  | 116475141 | 35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 3115.2 | 0 | 0 | 0 |  | 2019-20625 2021-08733 | 3115 | 0.58996 | 623000 | 2021-04261 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
77799999 | Line Removal | 0 | MEET | MEET | 2021108 |  | 31.8 | 31.8 | 2021 |  |  | 0 | 0 | UNSE | Various | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Various | Various | Various | Various |  |  |  |  | VARIOUS | 0 | 0 | 167904 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | FALSE | 0 |  | 0 | Not valued order
35226625 | FRRB - REMG - 2021 | 2 | MEET | No | 2021109 |  | 7.9 | 7.9 | 2021 |  |  | 0 | 395.6 | UNSE | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 | 40 | 7.7611 |  |  | FRRB | ELK CREEK | Glenn | North Valley | Northern | 5795150 | E.5034795.01.01 | 120445306 | 35226625 | FRRB - ELK CREEK 1101 LR 2106 | 0 | 0 | 0 | 41712 | [9 empty] | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Pre-Scope |  | 0
35217274 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021110 |  | 2.52 | 2.52 | 2021 |  |  | 0 | 14916.89 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.18857 |  |  | FRRB | PESCADERO | San Mateo | Peninsula | Central Coast | 5794202 | E.5034613.01.01 | 120048101 | 35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 0 | 13305.6 | 0 | 0 |  | 2020-84558 | 13305.6 | 2.52 | 4621000 |  |  | 13305.6 | 0 | 13305.6 | 2.52 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217275 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021111 |  | 2.9 | 2.9 | 2021 |  |  | 0 | 15629.41 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.21701 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794201 | E.5034614.01.01 | 120048103 | 35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 0 | 15312 | 0 | 0 |  | 2020-87935 | 15312 | 2.9 | 5352500 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226626 | FRRB - REMG - 2021 | 2 | MEET | No | 2021112 |  | 4.03 | 4.03 | 2021 |  |  | 0 | 6800.87 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | 1.8081 |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5795151 | E.5034796.01.01 | 120445370 | 35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 0 | 0 | 0 | 21278.4 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | TRUE | Pre-Scope |  | 0
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021113 |  | 2.56 | 2.56 | 2021 |  |  | 0 | -679894.08 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.54034 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 13516.8 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | TRUE | Scoped | FALSE | 0 | MAT 95A ON MPP WP but for 2020
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021114 |  | 4.8 | 4.8 | 2021 |  |  | 0 | -179287.42 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.6177 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 25344 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | TRUE | Scoped | FALSE | 0 | MAT 95A ON MPP WP but for 2020
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021115 |  | 6.72 | 6.72 | 2021 |  |  | 0 | -679894.08 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.9082 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 35481.6 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | TRUE | Scoped | FALSE | 0 | Duplicate value
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021116 |  | 7.25 | 7.25 | 2021 |  |  | 0 | -179287.42 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 3.2873 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 38280 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0 | [16 empty] | TRUE | Scoped | FALSE | 0 | Duplicate value
35220936 | FRRB - UG - 2021 | 5 | MEET | MEET | 2021117 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 7246.08 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 | 2095 | 0.060255 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794202 | E.5034613.01.02 | 120224375 | 35220936 | FRRB - BUTANO STATE PARK - PN SM | 0 | 5016 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | Pre-Scope |  | 0
35223343 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021118 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 46989.9 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.28647 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.08 | 120255838 | 35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 1 | 0 | 4488 | 0 | 0 |  | 2021-02744 | 4488 | 0.85 | 1338480 | [9 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225821 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021119 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 43823.92 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.32018 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.11 | 120424578 | 35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 2 | 0 | 5016 | 0 | 0 |  | 2021-02748 | 5016 | 0.95 | 1638720 | [9 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35235139 | FRRB - UG - 2021 |  |  |  | 2021120 |  | 0 | [7 empty] | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5794519 | E.5034825.01.22 | 120582960 | 35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH 3 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35229043 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021121 |  | 0.41345 | 0.41345 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.060599 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.01 | 120493696 | 35229043 | FRRB – WYANDOTTE 1103 – BALD ROCK ZONE 1 | 0 | 2183 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223344 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021122 |  | 4.1617 | 4.1617 | 2021 |  |  | 0 | 182107.54 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.60999 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.09 | 120255980 | 35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | 0 | 21974 | 0 | 0 |  | 2021-02746 | 9081.6 | 1.72 | 3007400 | [9 empty] | 0 |  | 2021-07956 | [14 empty] | TRUE | Scoped | TRUE | 2021
35223345 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021123 |  | 4.454 | 4.454 | 2021 |  |  | 0 | 786926.39 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 1.6208 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.10 | 120255982 | 35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 0 | 23517 | 0 | 0 |  | 2021-02747 | 13147.2 | 2.49 | 4312040 | [9 empty] | 0 | 2021-09321 | 2021-11881 | [14 empty] | TRUE | Scoped | TRUE | 2021
35225822 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021124 |  | 1.8693 | 1.8693 | 2021 |  |  | 0 | 61032.84 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.27399 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.12 | 120424579 | 35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 0 | 9870 | 0 | 0 |  | 2021-02749 | 5755.2 | 1.09 | 1954920 | [9 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225823 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021125 |  | 1.7159 | 1.7159 | 2021 |  |  | 0 | 76747.3 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.6244 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.13 | 120424672 | 35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 0 | 9060 | 0 | 0 |  | 2021-02750 | 9081.6 | 1.72 | 3005800 | [9 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225824 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021126 |  | 2.9364 | 2.9364 | 2021 |  |  | 0 | 550379.42 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.3314 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.14 | 120424703 | 35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 0 | 15504 | 0 | 0 |  | 2021-02751 | 13464 | 2.55 | 4213480 | [9 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35222234 | Remote Grid Pilot | 7 | MEET | No | 2021127 |  | 2.62 | 2.62 | 2021 |  |  | 0 | 0 | UNSE | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 | 167 | 4.4624 |  |  | REMG | OAKHURST | Mariposa | Yosemite | Central Valley | 5543982 | E.5034752.01.01 | 120237130 | 35222234 | REMG - OAKHURST 110110090 | 0 | 0 | 0 | 13833.6 |  | 2021-00557 | 13833.6 | 2.62 | 4816500 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232298 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021128 |  | 0.24 | 0.24 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.035177 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.02 | 120532441 | 35232298 | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | 0 | 1267.2 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233038 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021129 |  | 0.23 | 0.23 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.033711 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.05 | 120542278 | 35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | 0 | 1214.4 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233039 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021130 |  | 0.37 | 0.37 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.06 | 120542500 | 35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 0 | 1953.6 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233300 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021131 |  | 0.32 | 0.32 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.046902 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.07 | 120542502 | 35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 0 | 1689.6 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233301 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021132 |  | 0.36 | 0.36 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.052765 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.08 | 120542503 | 35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | 0 | 1900.8 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233302 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021133 |  | 0.12 | 0.12 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.017588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.09 | 120542504 | 35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 0 | 633.6 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233303 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021134 |  | 0.09 | 0.09 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.013191 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.10 | 120542505 | 35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | 0 | 475.2 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233304 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021135 |  | 0.3 | 0.3 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.043971 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.11 | 120542506 | 35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | 0 | 1584 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233305 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021136 |  | 0.29 | 0.29 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.042505 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.12 | 120542507 | 35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | 0 | 1531.2 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233306 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021137 |  | 0.26 | 0.26 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.038108 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.13 | 120541535 | 35233306 | FRRB - WYANDOTTE 1103 - W1 PH 1.10 | 0 | 1372.8 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233307 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021138 |  | 0.6 | 0.6 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.087942 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.14 | 120541538 | 35233307 | FRRB - WYANDOTTE 1103 - W1 PH 1.11 | 0 | 3168 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233308 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021139 |  | 0.93 | 0.93 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.13631 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.15 | 120541539 | 35233308 | FRRB - WYANDOTTE 1103 - W1 PH 1.12 | 0 | 4910.4 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233309 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021140 |  | 0.37 | 0.37 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.16 | 120541630 | 35233309 | FRRB - WYANDOTTE 1103 - W1 PH 1.13 | 0 | 1953.6 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233310 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021141 |  | 0.15 | 0.15 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.021985 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.17 | 120541632 | 35233310 | FRRB - WYANDOTTE 1103 - W1 PH 1.14 | 0 | 792 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35232718 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021142 |  | 1.2 | 1.2 | 2021 |  |  | 0 |  | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.03 | 120538803 | 35232718 | FRRB - WYANDOTTE 1103 - W2 PH 2.1 | 0 | 6336 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233311 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021143 |  | 1.25 | 1.25 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.18321 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.18 | 120541633 | 35233311 | FRRB - WYANDOTTE 1103 - W2 PH 2.2 | 0 | 6600 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233312 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021144 |  | 1.1 | 1.1 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.16123 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.19 | 120541634 | 35233312 | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | 0 | 5808 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233314 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021145 |  | 1.6 | 1.6 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.23451 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.20 | 120541635 | 35233314 | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | 0 | 8448 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35233315 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021146 |  | 0.96004 | 0.96004 | 2021 |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.14071 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.21 | 120541636 | 35233315 | FRRB - WYANDOTTE 1103 - W2 PH 2.5 | 0 | 5069 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35235705 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021147 |  | 1.3201 | 1.3201 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.19348 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.40 | 120594567 | 35235705 | FRRB - WYANDOTTE 1103 - W2 PH 2.6 | 0 | 6970 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35235706 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021148 |  | 1.16 | 1.16 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17003 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.41 | 120594568 | 35235706 | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | 0 | 6125 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35235707 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021149 |  | 0.95 | 0.95 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.13924 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.42 | 120594569 | 35235707 | FRRB - WYANDOTTE 1103 - W2 PH 2.8 | 0 | 5016 | 0 | 0 |  | 2021-09904 | [29 empty] | TRUE | Scoped | TRUE | 2021
35235320 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021150 |  | 10 | 10 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 3.6389 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.23 | 120582839 | 35235320 | FRRB - WYANDOTTE 1103 - W3 PH 3 | 0 | 52800 | 0 | 0 | [31 empty] | FALSE | Scoped | FALSE | 0 | New order
35235669 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021151 |  | 10.2 | 10.2 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 3.7117 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.24 | 120594870 | 35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4 | 0 | 53856 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | NCF - Pulled into DOT on 3/8/21 not on MPP WP and change rquest not yet submitted
35235670 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021152 |  | 3.91 | 3.91 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.7729 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.25 | 120594871 | 35235670 | FRRB - WYANDOTTE 1103 - W5 PH 5 | 0 | 20645 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | NCF - Pulled into DOT on 3/4/21
35235671 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021153 |  | 4.49 | 4.49 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 2.0358 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.26 | 120594872 | 35235671 | FRRB - WYANDOTTE 1103 - W6 PH 6 | 0 | 23707 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | NCF - Pulled into DOT on 3/4/21
35235672 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021154 |  | 1.64 | 1.64 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 0.74359 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.27 | 120594873 | 35235672 | FRRB - WYANDOTTE 1103 - W7 PH 7 | 0 | 8659 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | NCF - Pulled into DOT on 3/4/21
35235673 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021155 |  | 2.14 | 2.14 |  |  |  | 0 |  | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 0.97031 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.28 | 120594874 | 35235673 | FRRB - WYANDOTTE 1103 - W8 PH 8 | 0 | 11299 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | NCF - Pulled into DOT on 3/4/21
35235674 | FRRB - UG - 2021 |  |  |  | 2021156 |  | 4.3 | 4.3 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 2.9484 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.29 | 120596259 | 35235674 | FRRB - BIG BEND 1102 - B1 PH 1 | 0 | 22704 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235675 | FRRB - UG - 2021 |  |  |  | 2021157 |  | 1 | 1 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 0.68567 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.30 | 120596615 | 35235675 | FRRB - BIG BEND 1102 - B2 PH 2 | 0 | 5280 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235676 | FRRB - UG - 2021 |  |  |  | 2021158 |  | 2.3701 | 2.3701 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.79878 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.31 | 120598345 | 35235676 | FRRB - BIG BEND 1102 - B3 PH 3 | 0 | 12514 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235677 | FRRB - UG - 2021 |  |  |  | 2021159 |  | 4.2 | 4.2 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4155 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.32 | 120598407 | 35235677 | FRRB - BIG BEND 1102 - B4 PH 4 | 0 | 22176 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235678 | FRRB - UG - 2021 |  |  |  | 2021160 |  | 4.4 | 4.4 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4829 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.33 | 120598535 | 35235678 | FRRB - BIG BEND 1102 - B5 PH 5 | 0 | 23232 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235679 | FRRB - UG - 2021 |  |  |  | 2021161 |  | 6.5 | 6.5 |  |  |  | 0 |  | UNSC | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 2.1907 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.34 | 120598623 | 35235679 | FRRB - BIG BEND 1102 - B6 PH 6 | 0 | 34320 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235700 | FRRB - UG - 2021 |  |  |  | 2021162 |  | 5.44 | 5.44 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.2343 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.35 | 120598982 | 35235700 | FRRB - KANAKA 1101 - K1 PH 1 | 0 | 28723 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235701 | FRRB - UG - 2021 |  |  |  | 2021163 |  | 3.49 | 3.49 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.79185 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.36 | 120599070 | 35235701 | FRRB - KANAKA 1101 - K2 PH 2 | 0 | 18427 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235702 | FRRB - UG - 2021 |  |  |  | 2021164 |  | 2.14 | 2.14 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.48554 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.37 | 120599072 | 35235702 | FRRB - KANAKA 1101 - K3 PH3 | 0 | 11299 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235703 | FRRB - UG - 2021 |  |  |  | 2021165 |  | 8.44 | 8.44 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.915 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.38 | 120599073 | 35235703 | FRRB - KANAKA 1101 - K4 PH 4 | 0 | 44563 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
35235704 | FRRB - UG - 2021 |  |  |  | 2021166 |  | 6.1 | 6.1 |  |  |  | 0 |  | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.384 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.39 | 120599076 | 35235704 | FRRB - KANAKA 1101 - K5 PH 5 | 0 | 32208 | 0 | 0 | [31 empty] | TRUE | 0 |  | 0
| FRRB - UG - 2021 |  |  |  | 2021167 | [8 empty] | UNSC | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #DIV/0! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 |  |  |  | FRRB - KANAKA 1101 - K6 PH 6 | 0 |  | 0 | 0 | [31 empty] | FALSE | 0 |  | 0 | Blank Order value
35222236 | Remote Grid Pilot | 7 | MEET | No | 2021168 |  | 0.99 | 0.99 | 2021 |  |  | 0 | 0 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 | 468 | 1.4164 |  |  | REMG | MARIPOSA | Mariposa | Yosemite | Central Valley | 5543983 | E.5034753.01.01 | 120237131 | 35222236 | REMG - MARIPOSA 210135244 | 0 | 0 | 0 | 5227.2 |  | 2020-88214 | 5227.2 | 0.99 | 780759 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35175853 | Remote Grid Pilot | 13 | No | No | 2021169 |  | 0.7 | 0.7 | 2021 |  |  | 0 | 1787.6 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.0417 |  |  | REMG | GEORGETOWN | El Dorado | Sierra | Northern | 5790554 | E.5015422.03 | 118981960 | 35175853 | REMG - PLACERVILLE 21061104 | 0 | 0 | 0 | 3696 |  | 2018-84079 | 45936 | 8.7 | 9322600 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35222235 | Remote Grid Pilot | 7 | No | No | 2021170 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 5790.29 | UNSE | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 | 2461 | 0.0024273 |  |  | REMG | BADGER | Tulare | Fresno | Central Valley | 5794900 | E.5034754.01.01 | 120236988 | 35222235 | REMG - DUNLAP 1102778286 | 0 | 0 | 0 | 13728 |  | 2020-88308 | 13728 | 2.6 | 613214 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35229051 | Remote Grid Pilot | 7 | MEET | No | 2021171 |  | 3.04 | 3.04 | 2021 |  |  | 0 | 395.6 | UNSE | 103331102 | CORNING 1102 | CORNING 110253184 | 123 | 31.8239 | 413 | 21.5791 | 0.17544 | 106 | 2.0407 |  |  | REMG | FLOURNEY | Tehama | North Valley | Northern | 5795612 | E.5034827.01.01 | 120494134 | 35229051 | CORNING 1102 - REMOTE GRID #299 & # 300 | 0 | 0 | 0 | 16051 |  | 2021-09834 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219543 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021172 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 3904.85 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.021274 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.02 | 120135657 | 35219543 | PSPS - West Main St / Reservoir St - PLA PH 1.1 | 0 | 1267.2 | 0 | 0 |  | 2021-01722 | 1267.2 | 0.24 | 850440 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223036 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021173 |  | 0.055871 | 0.055871 | 2021 |  |  | 0 | 4821.78 | UNSE | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 | 2454 | 2.7003 |  |  | PSPS | GRASS VALLEY | Nevada | Sierra | Northern | 5794983 | E.5034759.01.01 | 120242599 | 35223036 | PSPS - Brunswick 1110CB | 0 | 295 | 0 | 0 |  | 2021-01470 | 264 | 0.05 | 88320 | 2021-08160 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223030 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021174 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 12822.92 | UNSE | 103191101 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 | 565 | 1.4867 |  |  | PSPS | BANGOR | Butte | Sierra | Northern | 5794981 | E.5034757.01.01 | 120242544 | 35223030 | PSPS - Bangor 1101CB | 0 | 4488 | 0 | 0 |  | 2021-01574 | 3009.6 | 0.57 | 1556240 | 2021-08449 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223062 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021175 |  | 0.18 | 0.18 | 2021 |  |  | 0 | 6857.1 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | 3379 | 7.3185e-05 |  | Tier 2 | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.01 | 120242676 | 35223062 | PSPS - Calistoga 1102184814 | 0 | 950.4 | 0 | 0 |  | 2021-01578 | 950.4 | 0.18 | 579050 | 2021-07698 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223038 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021176 |  | 0.87 | 0.87 | 2021 |  |  | 0 | 8921.72 | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | 1.6887 |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.01 | 120242693 | 35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | 0 | 4593.6 | 0 | 0 |  | 2021-01713 | 4593.6 | 0.87 | 911350 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234284 | PSPS - Community Resiliency | 9 | MEET | No | 2021177 |  | 0 | 0 | 2021 |  |  | 0 |  | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | #DIV/0! |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.02 | 120539923 | 35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | In Scoping |  | 0
35234526 | PSPS - Community Resiliency | 9 | MEET | No | 2021178 |  |  |  | 2021 |  |  | 0 |  | ESTS | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | #DIV/0! |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.03 | 120574717 | 35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | In Scoping |  | 0
35223060 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021179 |  | 1.74 | 1.74 | 2021 |  |  | 0 | 5062.09 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | 0.18012 |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.01 | 120242671 | 35223060 | PSPS-ALLEGHANY 1101-Downieville PH 1.1 | 0 | 9187.2 | 0 | 0 |  | 2021-01568 | 9187.2 | 1.74 | 4040000 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234527 | PSPS - Community Resiliency | 9 | MEET | No | 2021180 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.02 | 120574718 | 35234527 | PSPS-ALLEGHANY 1101-Downieville PH 1.2 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | In Scoping |  | 0
35234528 | PSPS - Community Resiliency | 9 | MEET | No | 2021181 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.03 | 120574870 | 35234528 | PSPS-ALLEGHANY 1101-Downieville PH 1.3 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | In Scoping |  | 0
35234529 | PSPS - Community Resiliency | 9 | MEET | No | 2021182 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.04 | 120574871 | 35234529 | PSPS-ALLEGHANY 1101-Downieville PH 1.4 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | In Scoping |  | 0
35223063 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021183 |  | 0.15114 | 0.15114 | 2021 |  |  | 0 | 4536.46 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.073206 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.01 | 120242673 | 35223063 | PSPS - DUNBAR 1101 - OAKMONT PH 1 | 0 | 798 | 0 | 0 |  | 2021-01566 | 10190.4 | 1.93 | 4690000 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35228774 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021184 |  | 0.97405 | 0.97405 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.47181 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.02 | 120487476 | 35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | 0 | 5143 | 0 | 0 |  | 2021-01566 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35228775 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021185 |  | 0.88617 | 0.88617 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.42924 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.03 | 120487477 | 35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | 0 | 4679 | 0 | 0 |  | 2021-01566 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223032 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021186 |  | 0.44 | 0.44 | 2021 |  |  | 0 | 9292.7 | UNSE | 152282102 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | 328 | 1.7655 |  | Tier 2 | PSPS | COOL | El Dorado | Sierra | Northern | 5794982 | E.5034758.01.01 | 120242546 | 35223032 | PSPS - Mounatin Quarries 2101CB | 0 | 2323.2 | 0 | 0 |  | 2021-01503 | 2323.2 | 0.44 | 745920 | 2021-10707 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223037 | PSPS - Community Resiliency | 14 | MEET | MEET | 2021187 |  | 0.052083 | 0.052083 | 2021 |  |  | 0 | 5273.97 | ESTS | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | 802 | 0.090642 |  | Tier 3 | PSPS | OAKHURST | Madera | Yosemite | Central Valley | 5794989 | E.5034765.01.01 | 120242694 | 35223037 | PSPS - Oakhurst 1101CB | 0 | 275 | 0 | 0 |  | 2021-01716 | 580.8 | 0.11 | 181120 | 2021-06095 |  |  |  | 0 |  |  | 0.0891 | 200 | 2244.6689 | [16 empty] | TRUE | Scoped | TRUE | 2021
35224377 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021188 |  | 1.13 | 1.13 | 2021 |  |  | 0 | 4024.98 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.43955 |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.01 | 120360607 | 35224377 | PSPS - PLACERVILLE 21067522 PH 1.1 | 0 | 5966.4 | 0 | 0 |  | 2021-01725 | 5966.4 | 1.13 | 2731920 |  |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35223039 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021189 | 0.63 | 0.60739 | 0.60739 | 2021 |  |  | 0 | 10152.12 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | 672 | 2.522 |  | Tier 2 | PSPS | OROVILLE | Butte | North Valley | Northern | 5794987 | E.5034763.01.01 | 120242691 | 35223039 | PSPS - Wyandotte 1109702710 | 705 | 2502 | 0 | 0 |  | 2021-01576 | 4065.6 | 0.77 | 1517740 | 2021-08443 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35233995 | PSPS - Community Resiliency | 10 | MEET | No | 2021190 |  | 0 | 0 | 2021 |  |  | 0 |  | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | #DIV/0! |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.02 | 120563909 | 35233995 | PSPS - PLACERVILLE 21067522 PH 1.2 | 0 | 0 | 0 | 0 |  | 2021-01725 | [29 empty] | TRUE | In Scoping |  | 0
35233996 | PSPS - Community Resiliency | 10 | MEET | No | 2021191 |  |  |  | 2021 |  |  | 0 |  | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | #DIV/0! |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.03 | 120563933 | 35233996 | PSPS - PLACERVILLE 21067522 PH 1.3 | 0 | 0 | 0 | 0 |  | 2021-01725 | [29 empty] | TRUE | In Scoping |  | 0
35219542 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021192 |  | 0.14 | 0.14 | 2021 |  |  | 0 | 7221.51 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.01241 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.01 | 120135655 | 35219542 | PSPS - Eskaton Village | 0 | 739.2 | 0 | 0 |  | 2021-01718 | 739.2 | 0.14 | 544560 | 2021-11652 |  |  |  | 0 |  |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219291 | Top 250 Miles | 14 | MEET | No | 2021200 |  | 0.39811 | 0.39811 | 2021 |  |  | 0 | 9258.02 | ESTS | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | 24 | 2.1382 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5543350 | E.5034693.01.01 | 120141627 | 35219291 | CWSP - VACA DIXON 1101126774 | 2102 | 0 | 0 | 0 |  | 2021-01500 | 2112 | 0.4 | 1561600 | 2021-04312 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2022
35219097 | Top 250 Miles | 14 | MEET | No | 2021201 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 12094.11 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.01 | 120141762 | 35219097 | CWSP - COARSEGOLD 2104CB PH1.1 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 | 45302.4 | 8.58 | 7867593 | 2021-04771 |  |  |  | 0 | 0 |  | 26.69 | 19300 | 723.1173 | [16 empty] | TRUE | Scoped | TRUE | 2021
35227260 | Top 250 Miles | 14 | MEET | No | 2021202 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 0 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.02 | 120457078 | 35227260 | CWSP - COARSEGOLD 2104CB PH1.2 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35227261 | Top 250 Miles | 14 | MEET | No | 2021203 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 3990.77 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 8.873 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.03 | 120457111 | 35227261 | CWSP - COARSEGOLD 2104CB PH1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35227262 | Top 250 Miles | 14 | MEET | No | 2021204 |  | 1.4015 | 1.4015 | 2021 |  |  | 0 | 3544.16 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 5.7572 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.04 | 120457115 | 35227262 | CWSP - COARSEGOLD 2104CB PH1.4 | 7400 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219098 | Top 250 Miles | 13 | MEET | No | 2021205 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 13086.55 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 2.9196 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120141805 | 35219098 | CWSP - MIDDLETOWN 1101118494 | 3801.6 | 0 | 0 | 0 |  | 2020-88310 | 7022.4 | 1.33 | 1830000 | 2021-04412 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35229119 | Top 250 Miles | 13 | MEET | MEET | 2021206 |  | 0.61 | 0.61 | 2021 |  |  | 0 | 957.21 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 3.9497 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120496477 | 35229119 | CWSP - MIDDLETOWN 1101118494 PH 2 | 0 | 3220.8 | 0 | 0 |  | 2020-88310 |  |  |  | 2021-04412 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219099 | Top 250 Miles | 10 | MEET | No | 2021207 |  | 17.3 | 17.3 | 2021 |  |  | 0 | 25924.57 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 21.1042 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.01 | 120141849 | 35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | 91344 | 0 | 0 | 0 |  | 2021-00785 | 91344 | 17.3 | 25150000 | 2021-08349 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231620 | Top 250 Miles | 10 | MEET | No | 2021208 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.02 | 120504137 | 35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231621 | Top 250 Miles | 10 | MEET | No | 2021209 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.03 | 120504138 | 35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231622 | Top 250 Miles | 10 | MEET | No | 2021210 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.04 | 120504139 | 35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231623 | Top 250 Miles | 10 | MEET | No | 2021211 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.05 | 120504160 | 35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231624 | Top 250 Miles | 10 | MEET | No | 2021212 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.06 | 120504163 | 35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231625 | Top 250 Miles | 10 | MEET | No | 2021213 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.07 | 120504164 | 35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231626 | Top 250 Miles | 10 | MEET | No | 2021214 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.08 | 120504165 | 35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231627 | Top 250 Miles | 10 | MEET | No | 2021215 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.09 | 120504167 | 35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231628 | Top 250 Miles | 10 | MEET | No | 2021216 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.10 | 120504170 | 35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231629 | Top 250 Miles | 10 | MEET | No | 2021217 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.11 | 120504175 | 35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231630 | Top 250 Miles | 10 | MEET | No | 2021218 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.12 | 120504176 | 35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35231631 | Top 250 Miles | 10 | MEET | No | 2021219 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | #DIV/0! |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.13 | 120504177 | 35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | 0 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219260 | Top 250 Miles | 13 | MEET | No | 2021220 | 0.84 | 0.84432 | 0.84432 | 2021 |  |  | 0 | 11750.94 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 3.1009 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034698.01.01 | 120141880 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1 | 4458 | 0 | 0 | 0 |  | 2021-01235 | 6916.8 | 1.31 | 2194368 | 2021-04349 |  |  |  | 0 | 0 |  | 6.25 | 4000 | 640 | [16 empty] | TRUE | In Scoping |  | 2021
35219266 | Top 250 Miles | 14 | MEET | No | 2021221 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 45633.67 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 4.4861 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.01 | 120141949 | 35219266 | CWSP - MARIPOSA 2102CB PH 1 | 13728 | 0 | 0 | 0 |  | 2021-01236 | 27720 | 5.25 | 8003586 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35227263 | Top 250 Miles | 14 | MEET | No | 2021222 |  | 2.6083 | 2.6083 | 2021 |  |  | 0 | 12113.02 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 4.5005 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.05 | 120457435 | 35227263 | CWSP - MARIPOSA 2102CB PH 2 | 13772 | 0 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219268 | Top 250 Miles | 14 | MEET | No | 2021223 |  | 1.6212 | 1.6212 | 2021 |  |  | 0 | 77148.45 | ESTS | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 4.1161 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.01 | 120142035 | 35219268 | CWSP - MARIPOSA 210197142 PH 1 | 8560 | 0 | 0 | 0 |  | 2021-01027 | 24288 | 4.6 | 7389000 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226241 | Top 250 Miles | 15 | MEET | No | 2021224 |  | 1.4799 | 1.4799 | 2021 |  |  | 0 | 36185.31 | ADER | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7573 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.02 | 120431331 | 35226241 | CWSP - MARIPOSA 210197142 PH 2 | 7814 | 0 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35226240 | Top 250 Miles | 14 | MEET | No | 2021225 |  | 1.4625 | 1.4625 | 2021 |  |  | 0 | 34659.33 | ESTS | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7131 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.03 | 120431332 | 35226240 | CWSP - MARIPOSA 210197142 PH 3 | 7722 | 0 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219269 | Top 250 Miles | 9 | MEET | MEET | 2021226 |  | 32.72 | 32.72 | 2021 |  |  | 0 | 7398.58 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 251.599 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.01 | 120142106 | 35219269 | CWSP - VACA DIXON 110540092 | 80150.4 | 50424 | 42187.2 | 0 |  | 2021-08140 | 130574.4 | 24.73 | 28158240 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219272 | Top 250 Miles | 14 | MEET | No | 2021227 |  | 0.85436 | 0.85436 | 2021 |  |  | 0 | 8598 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | 46 | 4.0641 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.02 | 120142171 | 35219272 | CWSP - MIDDLETOWN 1101481876 | 4511 | 0 | 0 | 0 |  | 2020-88311 | 4857.6 | 0.92 | 1280000 | 2021-04297 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219273 | Top 250 Miles | 14 | MEET | No | 2021228 | 3.46 | 3.461 | 3.461 | 2021 |  |  | 0 | 9004.69 | ESTS | 102541101 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | 6 | 8.0246 |  | Tier 2 | CWSP | MANTON | Tehama | North Valley | Northern | 5794543 | E.5034705.01.01 | 120142173 | 35219273 | CWSP - VOLTA 110149742 | 18274 | 0 | 0 | 0 |  | 2021-00903 | 18374.4 | 3.48 | 8182317 | 2021-03779 | 0 | 0 | 18744 | 18744 | 3.55 | 6700000 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219275 | Top 250 Miles | 17 | MEET | No | 2021229 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 5860.46 | APPR | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | 96 | 8.7599 |  | Tier 2 | CWSP | WINTERS | Solano | Sacramento | Northern | 5543347 | E.5034706.01.01 | 120142210 | 35219275 | CWSP - PUTAH CREEK 110246012 | 2745.6 | 0 | 0 | 0 |  | 2020-88233 | 2745.6 | 0.52 | 566066 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35219276 | Top 250 Miles | 10 | MEET | MEET | 2021230 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 30622.52 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.1163 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.01 | 120142212 | 35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | 0 | 11404.8 | 0 | 0 |  | 2021-01037 | 40444.8 | 7.66 | 11826060 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227651 | Top 250 Miles | 10 | MEET | No | 2021231 |  | 2.31 | 2.31 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 6.1057 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.03 | 120462109 | 35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | 12196.8 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227652 | Top 250 Miles | 10 | MEET | MEET | 2021232 |  | 0.41 | 0.41 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.7304 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.04 | 120462111 | 35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 0 | 2164.8 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227653 | Top 250 Miles | 10 | MEET | No | 2021233 |  | 2 | 2 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.2863 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.05 | 120462112 | 35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | 10560 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227654 | Top 250 Miles | 10 | MEET | No | 2021234 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.9031 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.06 | 120462113 | 35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | 3801.6 | 0 | 0 | 0 |  | 2021-01037 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35224378 | Top 250 Miles | 10 | MEET | No | 2021235 |  | 3.6 | 3.6 | 2021 |  |  | 0 | 14637.68 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.5154 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.02 | 120406213 | 35224378 | CWSP - VACAVILLE 11046542 PH 2.1 | 19008 | 0 | 0 | 0 |  | 2021-01589 | 36854.4 | 6.98 | 8840920 | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227870 | Top 250 Miles | 10 | MEET | MEET | 2021236 |  | 1.35 | 1.35 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.6977 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.07 | 120462116 | 35227870 | CWSP - VACAVILLE 11046542 PH 2.2 | 0 | 7128 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227656 | Top 250 Miles | 10 | MEET | MEET | 2021237 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 3.1654 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.08 | 120462117 | 35227656 | CWSP - VACAVILLE 11046542 PH 2.3 | 0 | 3960 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227657 | Top 250 Miles | 10 | MEET | No | 2021238 |  | 1 | 1 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 2.6432 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.09 | 120462180 | 35227657 | CWSP - VACAVILLE 11046542 PH 2.4 | 5280 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227658 | Top 250 Miles | 10 | MEET | No | 2021239 |  | 0.04 | 0.04 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.10573 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.10 | 120462182 | 35227658 | CWSP - VACAVILLE 11046542 PH 2.5 | 211.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35227659 | Top 250 Miles | 10 | MEET | No | 2021240 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.63436 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.11 | 120462184 | 35227659 | CWSP - VACAVILLE 11046542 PH 2.6 | 1267.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219280 | Top 250 Miles | 13 | MEET | MEET | 2021241 |  | 0.15152 | 0.15152 | 2021 |  |  | 0 | 4376.27 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 4.0762 |  | Tier 2 | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.01 | 120142216 | 35219280 | CWSP - POTTER VALLEY P H 110564118 PH 1 | 0 | 800 | 0 | 0 |  | 2020-88312 | 9820.8 | 1.86 | 2340000 | 2021-03822 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226632 | Top 250 Miles | 13 | MEET | No | 2021242 |  | 1.6828 | 1.6828 | 2021 |  |  | 0 | 919.75 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 28.3517 |  |  | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.02 | 120445424 | 35226632 | CWSP - POTTER VALLEY P H 110564118 PH 2 | 8885 | 0 | 0 | 0 |  | 2020-88312 | - | - | - | 2021-03822 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35232651 | Top 250 Miles | 13 | MEET | No | 2021243 |  | 1.74 | 1.74 | 2021 |  |  | 0 |  | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 4.7696 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.03 | 120529255 | 35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 9187 | 0 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219286 | Top 250 Miles | 11 | MEET | No | 2021244 | 2.91 | 3.4547 | 3.4547 | 2021 |  |  | 0 | 17566.79 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.4782 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.01 | 120142352 | 35219286 | CWSP - DESCHUTES 11049718 PH1.1 | 18241 | 0 | 0 | 0 |  | 2021-03394 | 31574.4 | 5.98 | 6757905 | 2021-12071 |  |  | 15365 | 15365 | 2.91 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232960 | Top 250 Miles | 11 | MEET | No | 2021245 | 2.9299 | 3.0411 | 3.0411 | 2021 |  |  | 0 | 8846.26 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.3856 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.07 | 120537723 | 35232960 | CWSP - DESCHUTES 11049718 PH1.2 | 16057 | 0 | 0 | 0 |  | 2021-03394 |  |  |  | 2021-12071 |  |  | 15470 | 15470 | 2.9299 | [20 empty] | TRUE | In Scoping |  | 0
35225825 | Top 250 Miles | 11 | MEET | No | 2021246 | 1.5299 | 1.5562 | 1.5562 | 2021 |  |  | 0 | 8930.89 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 7.8734 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.02 | 120426401 | 35225825 | CWSP - DESCHUTES 11049718 PH2.1 | 8217 | 0 | 0 | 0 |  | 2021-03395 | 56126.4 | 10.63 | 9724400 | 2021-12064 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232442 | Top 250 Miles | 11 | MEET | No | 2021247 | 3.1299 | 3.0778 | 3.0778 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.5714 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.03 | 120528704 | 35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | 16251 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232443 | Top 250 Miles | 11 | MEET | No | 2021248 | 1 | 1.0356 | 1.0356 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 5.2393 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.04 | 120528712 | 35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | 5468 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232444 | Top 250 Miles | 11 | MEET | No | 2021249 | 3.4701 | 3.5318 | 3.5318 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.8682 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.05 | 120528751 | 35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | 18648 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35232445 | Top 250 Miles | 11 | MEET | No | 2021250 | 2.6 | 2.6038 | 2.6038 | 2021 |  |  | 0 | 3064.15 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 13.1731 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.06 | 120528752 | 35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | 13748 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219289 | Top 250 Miles | 9 | MEET | MEET | 2021251 | 57.14 | 16.997 | 16.997 | 2021 |  |  | 0 | 7304.58 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 66.499 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.02 | 120142359 | 35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | 40052 | 32488 | 17204 | 0 |  | 2021-05564 | 58396.8 | 11.06 | [5 empty] | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35233947 | Top 250 Miles | 9 | MEET | No | 2021252 |  | 0 | 0 | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.38 | 120564156 | 35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 | 0 | 0 | 0 | 0 |  | 2021-05564 | [29 empty] | TRUE | In Scoping |  | 0
35233948 | Top 250 Miles | 9 | MEET | No | 2021253 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.39 | 120564181 | 35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | 0 | 0 | 0 | 0 |  | 2021-05564 | [29 empty] | TRUE | In Scoping |  | 0
35233949 | Top 250 Miles | 9 | MEET | No | 2021254 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.40 | 120564182 | 35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 | 0 | 0 | 0 | 0 |  | 2021-05564 | [29 empty] | TRUE | In Scoping |  | 0
35233950 | Top 250 Miles | 9 | MEET | No | 2021255 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.41 | 120564183 | 35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | 0 | 0 | 0 | 0 |  | 2021-05564 | [29 empty] | TRUE | In Scoping |  | 0
35233951 | Top 250 Miles | 9 | MEET | No | 2021256 |  |  |  | 2021 |  |  | 0 |  | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.42 | 120564184 | 35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 | 0 | 0 | 0 | 0 |  | 2021-05564 | [29 empty] | TRUE | In Scoping |  | 0
35225826 | Top 250 Miles | 9 | MEET | MEET | 2021257 |  | 9.7468 | 9.7468 | 2021 |  |  | 0 | 1990.54 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 29.0085 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.03 | 120426402 | 35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | 50237 | 533 | 693 | 0 |  | 2021-05558 | 51268.8 | 9.71 | [10 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35233952 | Top 250 Miles | 9 | MEET | No | 2021258 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.08 | 120563958 | 35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35233953 | Top 250 Miles | 9 | MEET | No | 2021259 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.09 | 120563959 | 35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35233955 | Top 250 Miles | 9 | MEET | No | 2021260 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.10 | 120564050 | 35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35233957 | Top 250 Miles | 9 | MEET | No | 2021261 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.11 | 120564051 | 35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35233959 | Top 250 Miles | 9 | MEET | No | 2021262 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.12 | 120564052 | 35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35234381 | Top 250 Miles | 9 | MEET | No | 2021263 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.13 | 120564055 | 35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35234382 | Top 250 Miles | 9 | MEET | No | 2021264 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.14 | 120564057 | 35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | 0 | 0 | 0 | 0 |  | 2021-05558 | [29 empty] | TRUE | In Scoping |  | 0
35225827 | Top 250 Miles | 9 | MEET | No | 2021265 |  | 6.5636 | 6.5636 | 2021 |  |  | 0 | 1182.27 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 19.2568 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.04 | 120426404 | 35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | 34656 | 0 | 0 | 0 |  | 2021-05859 | 34636.8 | 6.56 | [10 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35233954 | Top 250 Miles | 9 | MEET | No | 2021266 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.15 | 120564059 | 35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35233956 | Top 250 Miles | 9 | MEET | No | 2021267 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.16 | 120564070 | 35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35233958 | Top 250 Miles | 9 | MEET | No | 2021268 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.17 | 120564071 | 35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35234380 | Top 250 Miles | 9 | MEET | No | 2021269 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.18 | 120564073 | 35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35234383 | Top 250 Miles | 9 | MEET | No | 2021270 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.19 | 120564074 | 35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35234384 | Top 250 Miles | 9 | MEET | No | 2021271 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.20 | 120564075 | 35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35234385 | Top 250 Miles | 9 | MEET | No | 2021272 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.21 | 120564076 | 35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35234386 | Top 250 Miles | 9 | MEET | No | 2021273 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.22 | 120564078 | 35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 | 0 | 0 | 0 | 0 |  | 2021-05859 | [29 empty] | TRUE | In Scoping |  | 0
35225828 | Top 250 Miles | 9 | MEET | MEET | 2021274 |  | 8.4214 | 8.4214 | 2021 |  |  | 0 | 1136.42 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 25.3345 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.05 | 120426405 | 35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | 42608 | 575 | 1282 | 0 |  | 2021-05891 | 48470.4 | 9.18 | [10 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234387 | Top 250 Miles | 9 | MEET | No | 2021275 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.23 | 120564102 | 35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35234388 | Top 250 Miles | 9 | MEET | No | 2021276 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.24 | 120564104 | 35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35234389 | Top 250 Miles | 9 | MEET | No | 2021277 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.25 | 120564107 | 35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35234390 | Top 250 Miles | 9 | MEET | No | 2021278 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.26 | 120564108 | 35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35234391 | Top 250 Miles | 9 | MEET | No | 2021279 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.27 | 120564120 | 35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35234392 | Top 250 Miles | 9 | MEET | No | 2021280 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.28 | 120564121 | 35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 | 0 | 0 | 0 | 0 |  | 2021-05891 | [29 empty] | TRUE | In Scoping |  | 0
35225829 | Top 250 Miles | 9 | MEET | No | 2021281 |  | 11.1205 | 11.1205 | 2021 |  |  | 0 | 709.34 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 32.6259 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.06 | 120426406 | 35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | 58716 | 0 | 0 | 0 |  | 2021-05936 | 58713.6 | 11.12 | [10 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234393 | Top 250 Miles | 9 | MEET | No | 2021282 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.29 | 120564122 | 35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | 0 | 0 | 0 | 0 |  | 2021-05936 | [29 empty] | TRUE | In Scoping |  | 0
35234394 | Top 250 Miles | 9 | MEET | No | 2021283 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.30 | 120564123 | 35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | 0 | 0 | 0 | 0 |  | 2021-05936 | [29 empty] | TRUE | In Scoping |  | 0
35234395 | Top 250 Miles | 9 | MEET | No | 2021284 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.31 | 120564126 | 35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | 0 | 0 | 0 | 0 |  | 2021-05936 | [29 empty] | TRUE | In Scoping |  | 0
35234396 | Top 250 Miles | 9 | MEET | No | 2021285 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.32 | 120564127 | 35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 | 0 | 0 | 0 | 0 |  | 2021-05936 | [29 empty] | TRUE | In Scoping |  | 0
35234397 | Top 250 Miles | 9 | MEET | No | 2021286 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.33 | 120564129 | 35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | 0 | 0 | 0 | 0 |  | 2021-05936 | [29 empty] | TRUE | In Scoping |  | 0
35219287 | Top 250 Miles | 9 | MEET | MEET | 2021287 |  | 9.5263 | 9.5263 | 2021 |  |  | 0 | 9913.45 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 28.047 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.01 | 120142356 | 35219287 | CWSP - OREGON TRAIL 110335002 PH 6.1 | 50011 | 0 | 288 | 0 |  | 2021-06038 | 46992 | 8.9 | [5 empty] | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234398 | Top 250 Miles | 9 | MEET | No | 2021288 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.34 | 120564152 | 35234398 | CWSP - OREGON TRAIL 110335002 PH 6.2 | 0 | 0 | 0 | 0 |  | 2021-06038 | [29 empty] | TRUE | In Scoping |  | 0
35234399 | Top 250 Miles | 9 | MEET | No | 2021289 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.35 | 120564153 | 35234399 | CWSP - OREGON TRAIL 110335002 PH 6.3 | 0 | 0 | 0 | 0 |  | 2021-06038 | [29 empty] | TRUE | In Scoping |  | 0
35234400 | Top 250 Miles | 9 | MEET | No | 2021290 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.36 | 120564154 | 35234400 | CWSP - OREGON TRAIL 110335002 PH 6.4 | 0 | 0 | 0 | 0 |  | 2021-06038 | [29 empty] | TRUE | In Scoping |  | 0
35234401 | Top 250 Miles | 9 | MEET | No | 2021291 |  |  |  | 2021 |  |  | 0 | 3219.64 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | #DIV/0! |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.37 | 120564155 | 35234401 | CWSP - OREGON TRAIL 110335002 PH 6.5 | 0 | 0 | 0 | 0 |  | 2021-06038 | [29 empty] | TRUE | In Scoping |  | 0
35219267 | Top 250 Miles | 10 | MEET | No | 2021292 |  | 4.27 | 4.27 | 2021 |  |  | 0 | 7536.52 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 9.9007 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.02 | 120142033 | 35219267 | CWSP - MARIPOSA 2102440236 PH 1.1 | 22545.6 | 0 | 0 | 0 |  | 2021-01697 | 45302.4 | 8.58 | 950000 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219587 | Top 250 Miles | 10 | MEET | No | 2021293 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 606.27 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.03 | 120165147 | 35219587 | CWSP - MARIPOSA 2102440236 PH 1.2 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219588 | Top 250 Miles | 10 | MEET | No | 2021294 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 305.76 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.04 | 120165148 | 35219588 | CWSP - MARIPOSA 2102440236 PH 1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219589 | Top 250 Miles | 13 | MEET | No | 2021295 |  | 3.03 | 3.03 | 2021 |  |  | 0 | 10742.17 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 3.1142 |  | Tier 2 | CWSP | PLATINA | Shasta | North Valley | Northern | 5794561 | E.5034719.01.01 | 120165231 | 35219589 | CWSP - WILDWOOD 11011454 | 14836.8 | 0 | 0 | 0 |  | 2021-01188 | 15048 | 2.85 | 2940110 | 2021-04308 |  |  | 14837 | 14837 | 2.81 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35224321 | Top 250 Miles | 13 | MEET | No | 2021296 |  | 2.46 | 2.46 | 2021 |  |  | 0 | 4955.21 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 2.5283 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.01 | 120401277 | 35224321 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.1 | 12988.8 | 0 | 0 | 0 |  | 2021-01193 | 26664 | 5.05 | 7710294 | 2021-04257 |  |  | 12989 | 12989 | 2.46 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226798 | Top 250 Miles | 13 | MEET | No | 2021297 |  | 1.72 | 1.72 | 2021 |  |  | 0 | 217.2 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 1.7678 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.02 | 120450942 | 35226798 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.2 | 9081.6 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 9082 | 9082 | 1.7201 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226799 | Top 250 Miles | 13 | MEET | No | 2021298 |  | 0.19 | 0.19 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.19528 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.03 | 120450944 | 35226799 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.3 | 1003.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 1003 | 1003 | 0.18996 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226900 | Top 250 Miles | 13 | MEET | No | 2021299 |  | 0.69 | 0.69 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.70917 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.04 | 120450946 | 35226900 | CWSP - WILDWOOD 11011454 TEHAMA CO PH1.4 | 3643.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 3643 | 3643 | 0.68996 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219590 | Top 250 Miles | 9 | MEET | No | 2021300 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 385.66 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | 91 | 5.3817 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.02 | 120165232 | 35219590 | CWSP - VACA DIXON 1105965390 | 3960 | 0 | 0 | 0 |  | 2021-01565 | 3168 | 0.6 | 1047680 | [9 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35219591 | Top 250 Miles | 9 | MEET | No | 2021301 |  | 2.88 | 2.88 | 2021 |  |  | 0 | 152.97 | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | 7.3096 |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.01 | 120173637 | 35219591 | CWSP - OLETA 1101754718 PH 1.1 | 15206.4 | 0 | 0 | 0 |  | 2021-08929 | [12 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 0
35236662 | Top 250 Miles | 9 | MEET | No |  |  | 0 | 0 |  |  |  | 0 |  | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | #DIV/0! |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.02 | 120618060 | 35236662 | CWSP - OLETA 1101754718 PH 1.2 | 0 | 0 | 0 | 0 | [31 empty] | FALSE | In Scoping |  | 0 | New order
35192053 | Storm Rebuild | 20 | No | No | 2021302 |  | 1.97 | 1.97 | 2021 |  |  | 0 | 972832.92 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.036346 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034391.01 | 119554059 | 35192053 | STRM - OAKHURST 1103 - LR 5120 PH 1 | 10401.6 | 0 | 0 | 0 | N/A | 2021-04765 | 21965 | 4.16 | 7671845 | [9 empty] | 0 | 2021-04813 |  |  |  | 10401.6 | 10401.6 | 1.97
35227096 | Storm Rebuild | 20 | No | No | 2021303 |  | 1.0602 | 1.0602 | 2021 |  |  | 0 | 194307.81 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.019561 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.01 | 120457011 | 35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | 5598 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04843 |  |  |  | 5598 | 5598 | 1.0602
35227201 | Storm Rebuild | 19 | No | No | 2021304 |  | 0.82481 | 0.82481 | 2021 |  |  | 0 | 199814.78 | UNSC | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.015218 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.02 | 120457012 | 35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | 4355 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04837 |  |  |  | 4355 | 4355 | 0.82481
35228449 | Storm Rebuild | 19 | MEET | No | 2021305 | 2.89 | 2.8937 | 2.8937 | 2021 |  |  | 0 | 795091.79 | UNSC | 192251102 | RIO DELL 1102 | Rio Dell 11024230 | 59 | 22.9009 | 585 | 7.9721 | 0.13512 | 1331 | 0.62455 | 3088 | Tier 2 | STRM | MYERS FLAT | HUMBOLDT | HUMBOLDT | NORTHERN | 5795392 |  | 120481753 | 35228449 | Rio Dell Storm Rebuild | 15279 | 0 | 0 | 0 | N/A | N/A | 15279 | 2.8937 | 5469187.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0 | 2021-06858 | 2021-11321 | 0 | 0 | 15279 | 15279 | 2.8937 | 9426416 | 12825799 | 616.9524
35233166 | FRRB - UG - 2021 | 14 | MEET | No | 2021306 |  | 0 |  | 2021 |  |  | 0 |  | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.04 | 120541098 | 35233166 | FRRB - Big Bend 11021972 - B4 | 0 | 0 | 0 | 0 | [31 empty] | TRUE | Scoped | FALSE | 0 | Not on MPP WP Change request not yet submitted
35114040 | In-Construction | 20 | No | No | 2022001 | 5.2 | 1.4847 | 1.4847 | 2020 | 0 |  | 0 | 1168946.77 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.043681 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785991 | E.5014745.02 | 117500499 | 35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7839 | 0 | 0 | 0 |  | 2018-49722 | 27456 | 5.2 | 5674800 | 2019-35977 | 0 | 0 | 7188 | 7188 | 1.3614 | 2613818.1818 |  |  | 0 | 2020-20653 | 2020-39428 | 0 | 0 | 7839 | 7839 | 1.4847 | 3107232 | 4232854 | 396.3812 | [6 empty] | TRUE | Scoped | TRUE | 2022
35052737 | DSDD | 18 | No | No | 2022002 | 1.97 | 1.5867 | 1.5867 | 2020 | 0 |  | 0 | 106027.53 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.041798 | 12 | Tier 3 | CWSP | LONG BARN | Tuolumne | Yosemite | Central Valley | 5785238 | E.5014733.01 | 114675474 | 35052737 | CWSP-MIWUK 1701-LR8060-PH 1.1 | 8378 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8605 | 8605 | 1.6297 | 3129090.9091 |  |  | 0 | 2019-63683 | 2020-27366 | 0 | 0 | 8378 | 8378 | 1.5867 | 2060222 | 2768676 | 245.9086 | [6 empty] | TRUE | Scoped | TRUE | 2022
35192280 | ECOP - Top 20% | 14 | MEET | MEET | 2022003 |  | 1.643 | 1.643 | 2021 |  |  | 0 | 23348.52 | ESTS | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 2.7362 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5792091 | E.5034400.01 | 119556070 | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 PH1 | 0 | 8675 | 0 | 0 | 2020-77593 | 2020-77594 | 14414.4 | 2.73 | 4538638 | 2021-02769 | 0 | 8675 | 0 | 8675 | 1.643 | 3687300 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225589 | Top 50 Miles | 14 | MEET | No | 2022004 | 1.056 | 1.0983 | 1.0983 | 2021 |  |  | 0 | 31647.51 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 5.6145 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.02 | 120423768 | 35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 5799 | 0 | 0 | 0 |  | 2020-81645 | [12 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35225591 | Top 50 Miles | 14 | MEET | MEET | 2022005 | 1.4156 | 1.4723 | 1.4723 | 2021 |  |  | 0 | 28447.2 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 9.4535 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.03 | 120423769 | 35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 4527 | 0 | 3247 | 0 |  | 2020-81645 | [12 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35217268 | Top 50 Miles | 14 | MEET | MEET | 2022006 |  | 0.25795 | 0.25795 | 2021 |  |  | 0 | 16622.75 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 0.34672 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.01 | 120047659 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 1158 | 204 | 0 | 0 | 2020-81775 | 2020-81782 | 21436.8 | 4.06 | 6144137 | 2021-03744 |  | 9662.4 | 11774.4 | 21436.8 | 4.06 |  |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35224712 | Top 50 Miles | 14 | MEET | MEET | 2022007 |  | 3.2869 | 3.2869 | 2021 |  |  | 0 | 0 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 6.3054 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.02 | 120427328 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 1222 | 16133 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35224713 | Top 50 Miles | 14 | MEET | MEET | 2022008 |  | 1.8655 | 1.8655 | 2021 |  |  | 0 | 0 | ESTS | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 3.6531 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.03 | 120427329 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 160 | 9690 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35062375 | Top 20% MAVF CPZ | 14 | MEET | MEET | 2022009 | 1.11 | 1.0902 | 1.0902 | 2021 |  |  | 0 | 30474.26 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.7865 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783068 | E.5015571.01 | 115323921 | 35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 0 | 5756 | 0 | 0 |  | 2018-89225 | 63518.4 | 12.03 | 13033162 | 2021-04169 | 0 | 5861 | 0 | 5861 | 1.11 | 1698679.6353 |  |  | 0 | [16 empty] | TRUE | Scoped | TRUE | 2021
35191319 | ECOP - Top 20% | 13 | MEET | MEET | 2022010 | 1.04 | 1.1705 | 1.1705 | 2021 |  |  | 0 | 16760.5 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 2.8131 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5541305 | E.5034355.01 | 119518398 | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH1 | 0 | 6180 | 0 | 0 |  | 2020-76901 | 5491.2 | 1.04 | 1673104 | 2021-02773 | 0 | 5985 | 0 | 5985 | 1.1335 | 2201900 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35223615 | ECOP - Top 20% | 13 | MEET | MEET | 2022011 |  | 1.6258 | 1.6258 | 2021 |  |  | 0 | 521.99 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 3.9074 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5795129 | E.5034355.02 | 120401360 | 35223615 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH2 | 0 | 8584 | 0 | 0 |  | 2020-76901 | 0 | 0 | 0 | 2021-02773 | 0 | 8465 | 0 | 8465 | 1.6032 | 3288180 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227030 | ECOP - Top 20% | 13 | MEET | MEET | 2022012 |  | 1.7072 | 1.7072 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 2.5275 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.29 | 120449801 | 35227030 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.5 | 2233 | 6781 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 6781 | 2233 | 9014 | 1.7072 | 2820684 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227031 | ECOP - Top 20% | 13 | MEET | MEET | 2022013 |  | 2.03 | 2.03 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.0193 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.30 | 120449802 | 35227031 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.6 | 2534.4 | 8184 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 7672 | 2834 | 10506 | 1.9898 | 3192728 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35192282 | ECOP - Top 20% | 13 | MEET | MEET | 2022014 |  | 2.2621 | 2.2621 | 2021 |  |  | 0 | 20927.1 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.6907 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792098 | E.5034407.01 | 119556300 | 35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.1 | 0 | 11944 | 0 | 0 | 2020-78129 | 2020-78306 | 40920 | 7.75 | 11896580 | 2021-03830 | 0 | 11944 |  | 11944 | 2.2621 | 4133200 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226621 | ECOP - Top 20% | 13 | MEET | MEET | 2022015 |  | 2.6562 | 2.6562 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.9941 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.01 | 120445224 | 35226621 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.2 | 2941 | 11084 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 11084 | 2941 | 14025 | 2.6562 | 4029758 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35192292 | ECOP - Top 20% | 13 | MEET | MEET | 2022016 |  | 0.95114 | 0.95114 | 2021 |  |  | 0 | 54096.84 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 1.0419 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5792094 | E.5034403.01 | 119556108 | 35192292 | ECOP - FULTON 1107 - H02-LR604 Ph 1.1 | 830 | 4192 | 0 | 0 | 2020-78732 | 2020-78779 | 19800 | 3.75 | 4686150 | 2021-02767 | 0 | 4192 | 830 | 5022 | 0.95114 | 1887200 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35225594 | ECOP - Top 20% | 13 | MEET | MEET | 2022017 |  | 0.5286 | 0.5286 | 2021 |  |  | 0 | 1447.31 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.5956 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.01 | 120424183 | 35225594 | ECOP - FULTON 1107 - H02-LR604 Ph 1.2 | 261 | 2530 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 2530 | 389 | 2919 | 0.55284 | 864959 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35174478 | ECOP - Top 20% | 13 | MEET | MEET | 2022018 |  | 1.79 | 1.79 | 2021 |  |  | 0 | 8194.28 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.0704 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790111 | E.5033917.01 | 118913024 | 35174478 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.1 | 0 | 9451.2 | 0 | 0 | 2020-51635 | 2020-51816 | 21489.6 | 4.07 | 6162189 | 2021-04465 | 0 | 9463 | 518 | 9981 | 1.8903 | 3159460 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226857 | ECOP - Top 20% | 13 | MEET | MEET | 2022019 |  | 1.94 | 1.94 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.3277 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.01 | 120449200 | 35226857 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.2 | 0 | 10243.2 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 10242 | 0 | 10242 | 1.9398 | 3613740 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226858 | ECOP - Top 20% | 13 | MEET | MEET | 2022020 |  | 0.74295 | 0.74295 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0502 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.02 | 120449201 | 35226858 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.3 | 1900.8 | 0 | 2022 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 2022 | 0 | 1889 | 3911 | 0.74072 | 510683 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226859 | ECOP - Top 20% | 13 | MEET | No | 2022021 |  | 0.88 | 0.88 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.94531 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.03 | 120449202 | 35226859 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.4 | 4646.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 0 | 4659 | 4659 | 0.88239 | 1123574 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226861 | ECOP - Top 20% | 13 | MEET | No | 2022022 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.80566 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.04 | 120449203 | 35226861 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.5 | 3960 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3986 | 3986 | 0.75492 | 824385 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226862 | ECOP - Top 20% | 13 | MEET | No | 2022023 |  | 0.58 | 0.58 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.62305 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.05 | 120449204 | 35226862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH1.6 | 3062.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3073 | 3073 | 0.58201 | 635558 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35174501 | ECOP - Top 20% | 13 | MEET | MEET | 2022024 |  | 1.683 | 1.683 | 2021 |  |  | 0 | 22873.41 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.8867 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790112 | E.5033919.01 | 118913026 | 35174501 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.1 | 0 | 8886 | 0 | 0 | 2020-53723 | 2020-53724 | 50952 | 9.65 | 16768361 | 2021-04463 | 0 | 8886 | 0 | 8886 | 1.683 | 18931272.7273 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227007 | ECOP - Top 20% | 13 | MEET | MEET | 2022025 |  | 1.1288 | 1.1288 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9362 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.19 | 120449533 | 35227007 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.2 | 0 | 5960 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 5960 | 0 | 5960 | 1.1288 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227010 | ECOP - Top 20% | 13 | MEET | No | 2022026 |  | 0.15985 | 0.15985 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.17171 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.20 | 120449536 | 35227010 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.3 | 844 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 844 | 844 | 0.15985 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227013 | ECOP - Top 20% | 13 | MEET | No | 2022027 |  | 0.026894 | 0.026894 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.02889 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.21 | 120449539 | 35227013 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.4 | 142 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 142 | 142 | 0.026894 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227015 | ECOP - Top 20% | 13 | MEET | No | 2022028 |  | 0.95758 | 0.95758 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0286 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.22 | 120449710 | 35227015 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.5 | 5056 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 5056 | 5056 | 0.95758 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227018 | ECOP - Top 20% | 13 | MEET | No | 2022029 |  | 1.2 | 1.2 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2891 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.23 | 120449711 | 35227018 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.6 | 6336 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 6336 | 6336 | 1.2 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227021 | ECOP - Top 20% | 13 | MEET | No | 2022030 |  | 0.21989 | 0.21989 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.23621 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.24 | 120449712 | 35227021 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.7 | 1161 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 1161 | 1161 | 0.21989 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227025 | ECOP - Top 20% | 13 | MEET | MEET | 2022031 |  | 0.7536 | 0.7536 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0184 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.25 | 120449714 | 35227025 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.8 | 2259 | 1720 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 1720 | 2259 | 3979 | 0.7536 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35234756 | ECOP - Top 20% | 13 | MEET | MEET | 2022032 |  | 2.782 | 2.782 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 4.7719 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.31 | 120580906 | 35234756 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.9 | 0 | 14689 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 14689 | 0 | 14689 | 2.782 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234758 | ECOP - Top 20% | 13 | MEET | MEET | 2022033 |  | 0.58201 | 0.58201 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99831 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.32 | 120580957 | 35234758 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.10 | 0 | 3073 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3073 | 0 | 3073 | 0.58201 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234862 | ECOP - Top 20% | 13 | MEET | MEET | 2022034 |  | 0.079924 | 0.079924 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.13709 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.33 | 120580959 | 35234862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.11 | 0 | 422 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 422 | 0 | 422 | 0.079924 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35234865 | ECOP - Top 20% | 13 | MEET | MEET | 2022035 |  | 0.64754 | 0.64754 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.1107 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.34 | 120581001 | 35234865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH3.12 | 0 | 3419 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3419 | 0 | 3419 | 0.64754 | 0 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 0
35192291 | ECOP | 13 | No | MEET | 2022036 |  | 1.0972 | 1.0972 | 2021 |  |  | 0 | 17752.99 | UNSE | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.1858 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792093 | E.5034402.01 | 119556091 | 35192291 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 1 | 521 | 5272 | 0 | 0 |  | 2020-69602 | 15100.8 | 2.86 | 3208863 | 2021-04462 | 0 | 5272 | 521 | 5793 | 1.0972 | 2442393 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35191937 | ECOP | 13 | No | No | 2022037 |  | 1.4528 | 1.4528 | 2021 |  |  | 0 | 14993.88 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.61524 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5792064 | E.5034372.01 | 119553837 | 35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1 | 7671 | 0 | 0 | 0 | 2020-61147 | 2020-61154 | 17635.2 | 3.34 | 3777700 | 2021-04460 |  | 4540.8 | 13094.4 | 17635.2 | 3.34 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227032 | ECOP | 13 | No | No | 2022038 |  | 0.575 | 0.575 | 2021 |  |  | 0 | 0 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.2435 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.01 | 120449806 | 35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 2 | 3036 | 0 | 0 | 0 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227033 | ECOP | 13 | No | No | 2022039 |  | 1.31 | 1.31 | 2021 |  |  | 0 | 0 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.88583 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.02 | 120449807 | 35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 3 | 0 | 0 | 0 | 6917 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219093 | Top 50 Miles | 13 | MEET | MEET | 2022040 | 1.14 | 1.14 | 1.14 | 2021 |  |  | 0 | 6576.02 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.0351 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.01 | 120141622 | 35219093 | CWSP - TIDEWATER 210614072 PH 1 | 0 | 6019.2 | 0 | 0 |  | 2020-87771 | 25396.8 | 4.81 | 8092656 | 2021-08732 | 0 | 6019.2 | 0 | 6019.2 | 1.14 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35231543 | Top 50 Miles | 13 | MEET | MEET | 2022041 | 1.3 | 1.3 | 1.3 | 2021 |  |  | 0 | 0 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.8821 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.02 | 120504099 | 35231543 | CWSP - TIDEWATER 210614072 PH 2 | 0 | 6864 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 6864 | 0 | 6864 | 1.3 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217273 | Top 50 Miles | 13 | MEET | MEET | 2022042 | 1.1133 | 1.1055 | 1.1055 | 2021 |  |  | 0 | 14756.58 | UNSE | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | 90 | 3.6826 |  | Tier 2 | CWSP | UPPER LAKE | Lake | North Coast | Northern | 5794203 | E.5034612.01.01 | 120048019 | 35217273 | CWSP - UPPER LAKE 1101 CB | 240 | 0 | 5596.8 | 0 | 2020-81991 | 2020-82007 | 211.2 | 0.04 | 970000 |  | 5596.8 |  | 211.2 | 5808 | 1.1 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217272 | Top 50 Miles | 13 | MEET | MEET | 2022043 | 0.3 | 0.34053 | 0.34053 | 2021 |  |  | 0 | 24256.47 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 2.1677 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.01 | 120048018 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1 | 94 | 1704 | 0 | 0 | 2020-81561 | 2020-82753 | 42926.4 | 8.13 | 22711843 | 2021-03825 |  | 34161.6 | 8764.8 | 42926.4 | 8.13 |  | 41.75 | 31200 | 747.3054 | [16 empty] | TRUE | In Scoping |  | 2021
35226628 | Top 50 Miles | 13 | MEET | MEET | 2022044 | 0.82 | 0.81913 | 0.81913 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.3182 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.03 | 120445377 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 3 | 0 | 4325 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226629 | Top 50 Miles | 13 | MEET | MEET | 2022045 | 4.5 | 4.6972 | 4.6972 | 2021 |  |  | 0 | 0 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 30.4963 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.04 | 120445378 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 4 | 0 | 24801 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217269 | Top 50 Miles | 13 | MEET | MEET | 2022046 | 0.1288 | 0.52083 | 0.52083 | 2021 |  |  | 0 | 15574.94 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.8658 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.01 | 120048011 | 35217269 | SH - MIDDLETOWN 1102 LR 302610 PH 1 | 630 | 2120 | 0 | 0 | 2020-81207 | 2020-81139 | 26294.4 | 4.98 | 6542572 | 2021-04671 |  | 9240 | 17054.4 | 26294.4 | 4.98 |  | 39.7 | 22200 | 559.194 | [16 empty] | TRUE | In Scoping |  | 2021
35226819 | Top 50 Miles | 13 | MEET | No | 2022047 | 0.32668 | 1.321 | 1.321 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 8.4527 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.02 | 120456652 | 35226819 | SH - MIDDLETOWN 1102 LR 302610 PH 2 | 6975 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227160 | Top 50 Miles | 13 | MEET | MEET | 2022048 | 0.70305 | 2.843 | 2.843 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 28.9198 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.03 | 120456653 | 35227160 | SH - MIDDLETOWN 1102 LR 302610 PH 3 | 176 | 14835 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227161 | Top 50 Miles | 13 | MEET | No | 2022049 | 0.18069 | 0.73068 | 0.73068 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.6753 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.04 | 120456654 | 35227161 | SH - MIDDLETOWN 1102 LR 302610 PH 4 | 3858 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227162 | Top 50 Miles | 13 | MEET | MEET | 2022050 | 0.10332 | 0.4178 | 0.4178 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.2687 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.05 | 120456655 | 35227162 | SH - MIDDLETOWN 1102 LR 302610 PH 5 | 0 | 2206 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227163 | Top 50 Miles | 13 | MEET | No | 2022051 | 0.10168 | 0.41117 | 0.41117 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 2.6309 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.06 | 120456657 | 35227163 | SH - MIDDLETOWN 1102 LR 302610 PH 6 | 2171 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227164 | Top 50 Miles | 13 | MEET | No | 2022052 | 0.13821 | 0.5589 | 0.5589 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 3.5762 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.07 | 120456658 | 35227164 | SH - MIDDLETOWN 1102 LR 302610 PH 7 | 2951 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217270 | Top 50 Miles | 13 | MEET | No | 2022053 | 0.55395 | 0.57614 | 0.57614 | 2021 |  |  | 0 | 35945.14 | UNSE | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 2.9452 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.01 | 120048013 | 35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 3042 | 0 | 0 | 0 | 2020-81626 | 2020-81645 | 11035.2 | 2.09 | 2458800 |  |  |  | 11035.2 | 11035.2 | 2.09 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35217271 | Top 50 Miles | 13 | MEET | MEET | 2022054 |  | 2.8496 | 2.8496 | 2021 |  |  | 0 | 47097.09 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 15.4448 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.01 | 120048017 | 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 0 | 15046 | 0 | 0 |  | 2020-87776 | 38016 | 7.2 | 11000000 | 2021-05676 | 0 | 15046 | 0 | 15046 | 2.8496 | 5487320 | 34.46 | 31600 | 917.0052 | [16 empty] | TRUE | In Scoping |  | 2021
35227864 | Top 50 Miles | 13 | MEET | MEET | 2022055 |  | 1.8392 | 1.8392 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.9684 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.11 | 120462234 | 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 0 | 9711 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 9711 | 0 | 9711 | 1.8392 | 3498820 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35220895 | Top 50 Miles | 13 | MEET | MEET | 2022056 |  | 2.1489 | 2.1489 | 2021 |  |  | 0 | 13660.71 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 11.2106 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.02 | 120221891 | 35220895 | CWSP - MIDDLETOWN 1103 LR 830 PH2.1 | 1137 | 10209 | 0 | 0 |  | 2020-87780 | 48681.6 | 9.22 | 7050000 | 2021-06302 | 0 | 10209 | 1137 | 11346 | 2.1489 | 3553334 | 19.39 | 18300 | 943.7855 | [16 empty] | TRUE | In Scoping |  | 2021
35228186 | Top 50 Miles | 13 | MEET | MEET | 2022057 |  | 1.4847 | 1.4847 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.0468 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.15 | 120475322 | 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 0 | 7839 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 7839 | 0 | 7839 | 1.4847 | 2916780 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35220896 | Top 50 Miles | 13 | MEET | MEET | 2022058 |  | 0.2803 | 0.2803 | 2021 |  |  | 0 | 6986.57 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.5192 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.03 | 120222356 | 35220896 | CWSP - MIDDLETOWN 1103 LR 830 PH3.1 | 0 | 1480 | 0 | 0 |  | 2020-87782 | 19219.2 | 3.64 | 3976000 | 2021-04672 | 0 | 1480 | 0 | 1480 | 0.2803 | 653600 | 21.1 | 23300 | 1104.2654 | [16 empty] | TRUE | In Scoping |  | 0
35227165 | Top 50 Miles | 13 | MEET | MEET | 2022059 |  | 1.0112 | 1.0112 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.4805 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.04 | 120456740 | 35227165 | CWSP - MIDDLETOWN 1103 LR 830 PH3.2 | 0 | 5339 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 5339 | 0 | 5339 | 1.0112 | 1743480 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227167 | Top 50 Miles | 13 | MEET | MEET | 2022060 |  | 1.7975 | 1.7975 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.7426 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.05 | 120456741 | 35227167 | CWSP - MIDDLETOWN 1103 LR 830 PH3.3 | 0 | 9491 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 9491 | 0 | 9491 | 1.7975 | 3107120 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227168 | Top 50 Miles | 13 | MEET | MEET | 2022061 |  | 1.5741 | 1.5741 | 2021 |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.5313 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.06 | 120456742 | 35227168 | CWSP - MIDDLETOWN 1103 LR 830 PH3.4 | 0 | 8311 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 8311 | 0 | 8311 | 1.5741 | 2764520 | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35062374 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022062 | 1.56 | 1.5352 | 1.5352 | 2021 |  |  | 0 | 47327.61 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.9241 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783067 | E.5015572.01 | 115323920 | 35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 0 | 8106 | 0 | 0 |  | 2018-89221 | 45038.4 | 8.53 | 9171850 | 2021-04171 | 0 | 8237 | 0 | 8237 | 1.56 | 2427043.6218 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35231608 | Top 20% MAVF CPZ | 13 | MEET | No | 2022063 | 0.32992 | 0.16212 | 0.16212 | 2021 |  |  | 0 | 928.03 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.25951 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.12 | 120504095 | 35231608 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 856 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 1742 | 0 | 1742 | 0.32992 | 513282.7473 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226849 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022064 | 1.7799 | 1.7833 | 1.7833 | 2021 |  |  | 0 | 372.25 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 4.5583 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.04 | 120449142 | 35226849 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 0 | 9416 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 9398 | 0 | 9398 | 1.7799 | 2723799.8997 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35062376 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022065 | 2.53 | 4.3231 | 4.3231 | 2021 |  |  | 0 | 21370.26 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 13.4088 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783069 | E.5015570.01 | 115323922 | 35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 0 | 22826 | 0 | 0 |  | 2018-89227 | 58080 | 11 | 11965840 | 2021-05102 | 0 | 13358.4 | 0 | 13358.4 | 2.53 | 4751652.1664 |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219096 | Top 250 Miles | 13 | MEET | MEET | 2022066 |  | 1.67 | 1.67 | 2021 |  |  | 0 | 6407.72 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 5.297 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.01 | 120141671 | 35219096 | CWSP - KIRKER 2104442850 PH 1 | 0 | 8817.6 | 0 | 0 |  | 2021-01226 | 9240 | 1.75 | 4945020 |  |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35227655 | Top 250 Miles | 13 | MEET | No | 2022067 |  | 3.77 | 3.77 | 2021 |  |  | 0 | 0 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 7.4888 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.02 | 120462115 | 35227655 | CWSP - KIRKER 2104442850 PH 2 | 19905.6 | 0 | 0 | 0 | [14 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35226700 | Top 250 Miles | 13 | MEET | MEET | 2022068 | 0.46 | 0.45758 | 0.45758 | 2021 |  |  | 0 | 0 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 2.6834 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034802.01.02 | 120447112 | 35226700 | CWSP - WYANDOTTE 110932586 PH 2 | 0 | 2416 | 0 | 0 |  | 2021-01235 |  |  |  | 2021-04349 | [6 empty] | 0 | 0 | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35219281 | Top 250 Miles | 13 | MEET | MEET | 2022069 |  | 2.5 | 2.5 | 2021 |  |  | 0 | 18741.89 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 10.9428 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.01 | 120142240 | 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.1 | 0 | 13200 | 0 | 0 |  | 2021-00875 | 30940.8 | 5.86 | 8236794 | 2021-10593 |  |  |  | 0 | 0 |  |  |  | 0 | [16 empty] | TRUE | In Scoping |  | 2021
35232650 | Top 250 Miles | 13 | MEET | MEET | 2022070 |  | 1.71 | 1.71 | 2021 |  |  | 0 |  | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 7.485 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.02 | 120529254 | 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 0 | 9029 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0 | [16 empty] | TRUE | In Scoping |  | 2021

## WSHP Extract 3-11
Order | Job Owner Name | Project Reporting Year | Sub-Category | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | 2023 Forecast Feet | 2023 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Program | Ready to Break Ground | Pre-Eng. Mtg Date | Pre-Eng. Complete | EOD Forecast | SAP Est Out Date | Previous EOD Forecast | Prelim Dwg Forecast | Previous Prelim Dwg Forecast | Prelim Dwg Out | PEND IN Date | Estimating Comments | Estimating Team | Estimating Manager | ADE | Priority | Status | T-Line Conflict | Composite Poles | Wood Poles | Comp Poles | --1 | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Base Map Status | Expected Base Map Complete | Base Map Vendor | Surveyor | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | Land Planner | Envrionmental Lead PGE Contact | Notes | L and ERTC Complete | --2 | Expected Permit Date | Permits Complete | Permit Expire Date | Permit Coordinator | Permitting Notes | --3 | Veg Complete | Veg Completed | Veg Start | ERTC Call Date | Veg Management | Veg Notes | --4 | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | 2021 Feet Installed | 2021 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | P6 Operative Date | P6 Operative Actualized | P6 Forecast In Service | UNSC In Date | CLICK Construction Start | CLICK Construction End | CN24 Out Date | Materials Ready Date | Materials Ready | Readiness Notes | --5 | Auth Amt without Contingency (Expected Case) | Total EAC | MPP Approved Budget (2021) | Auth Amt with Contingency (High Case) | Remaining Contingency | Expected - (Actuals + Committed) | Total EAC / Expected Case | ITD Actual | Open Commitments | Total Act + Com | Credits and Reimbursements | Expected Unit Cost | --6 | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Blended IDs | Project Managed | Circuit Protection Zone | Risk Rank | Segmentation ID# | Project Type | Last Edited By | Last Edited Date
30748101 |  | 2020 | 220 Mile Plan | OCGC R7 EP ED WRO - HWY 29 - KELSEYVILLE |  |  | FICL |  | 0 | 17499 | 17499 | 3.3142 | 17499 | 3.3142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 10L | SH | 2019-07-18 | [21 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | [5 empty] | Y | [11 empty] | 0 | 0 | 17499 | 3.3142 | 0 | 0 | 3.3142 | 0 | 3.3142 | 0 | 3.3142 | 0 | 0 | 3.3142 |  |  | 2019-07-18 | Yes | N/A | 2019-10-07 | 2020-04-22 | Yes | 2020-04-30 17:00 |  | 2019-03-27 | 2020-04-30 | 2020-06-08 |  | Yes | Shovel Ready |  | 2414558.4 |  |  | 5340502 | 2925943.6 |  |  | 2340375.7 |  |  | -3348.795 | [14 empty] | 0 | 0 |  |  |  |  | 2020 | [5 empty] | Y | [5 empty] | 2021-02-24 13:41
30962842 |  |  |  | REM OH FAC -408 MILL RD. FEATHER FA |  |  | FICL |  | 0 | 7000 | 7000 | 1.3258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 7000 | 1.3258 | 0 | 0 | 0 | 0 | 1.3258 | 0 | 1.3258 | 0 | 1.3258 | 0 | 0 | 1.3258 |  |  |  |  | N/A | [7 empty] | 2019-06-06 | [27 empty] | Feather Falls | Butte | 39.3567 | -121.1428
30977613 |  |  |  | WDDB OTTER 1102 PHASE 3 |  |  | PEND | 3700 | 0 | 3637 | 3637 | 0.68883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68883 |  |  | CC | 08W | SH | 2020-02-26 |  |  | 2019-02-28 |  | 2019-02-28 |  |  | Yes | 2019-02-28 | [6 empty] | No | [5 empty] | Yes |  |  |  | 2020-02-26 | 2020-02-26 |  |  |  |  | Full | 2020-02-26 | 2020-02-26 | Partial |  |  | Issued a PERTC3/30/2020 - ; 4/30/2020- date is at risk due to property owner backing out of TCE for power generation; the Plan "B" TCE will require State Park and County approval/ possible Coastal Development Permit | Partial |  |  | Yes |  |  | No permit needed. Work done on private and state property. |  | 1980-01-01 | Y |  |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68883 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  | Yes | INPR | [9 empty] | Yes | Reauth |  | 355200 | 1242530.5 |  | 355200 | 0 |  | 349.8% | 312710.5 |  |  |  | 1803838.6142 |  | 16 | [7 empty] | Remove |  | Big Sur | Monterey | 36.3507 | -121.8806 | P.06570 | ML |  | 2020-088 | 2022 | Q3 | 2019-02-28 | 2020-05-01 | 2020-05-25 |  | Y | OTTER 1102CB | 1425
30977614 |  |  |  | WDDB OTTER 1102 PHASE 4 |  |  | UNSC | 3400 | 0 | 3681 | 3681 | 0.69716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69716 |  |  | CC | 08W | SH | 2019-02-28 |  |  | 2019-02-28 |  | 2019-02-28 |  |  | Yes | 2019-02-28 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Forest Svs & Land | Full |  |  | Yes |  |  | No permit needed. Work done on private and state property. |  | 1980-01-01 | Y |  |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69716 | 0 | 0 | 0.69735 | 0.69735 | 0 | 0 |  | Remove |  | Yes | N/A |  |  |  |  | 2019-12-05 |  |  |  |  | yes | Shovel Ready |  | 326400 | 1136914.4 |  | 326400 | 0 |  | 348.3% | 279877.3 |  |  |  | 1630781.8615 |  | 15 | [7 empty] | Remove |  | Big Sur | Monterey | 36.3507 | -121.8806 | P.06571 | ML |  | 2020-089 | 2022 | Q3 | 2019-02-28 | 2020-05-01 | 2020-05-24 |  | Y | OTTER 1102CB | 1425
30977615 |  |  |  | WDDB OTTER 1102 PHASE 5 |  |  | UNSC | 3000 | 0 | 2664 | 2664 | 0.50455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50455 |  |  | CC | 08W | SH | 2019-02-20 |  |  | 2019-02-20 | 2021-09-30 | 2019-02-20 |  |  | Yes | 2019-12-06 | 2/20: Approved |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Forest Svs & Land | Full |  |  | Yes |  |  | No permit needed. Work done on private property. |  | 1980-01-01 | Y |  |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50455 | 0 | 0 | 0.50455 | 0.50455 | 0 | 0 |  | Remove |  | Yes | N/A |  |  |  |  | 2019-12-06 |  |  |  |  | yes | Shovel Ready |  | 240000 | 1040318.1 |  | 245198 | 5198 | 11434.1 | 433.5% | 226469.9 | 2096 | 228565.9 |  | 2061891.7297 |  | 15 | [7 empty] | Remove |  | Big Sur | Monterey | 36.3662 | -121.8921 | P.06572 | ML |  | 2020-090 | 2022 | Q3 | 2019-02-20 | 2020-05-01 | 2020-05-23 |  | Y | OTTER 1102CB | 1425
31048050 |  |  |  | STS-OFAC_IDLE_REMV-WENTWORTH SPRINGS |  |  | CLSD |  | 0 | 1185 | 1185 | 0.22443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 1185 | 0.22443 | 0 | 0 | 0 | 0 | 0.22443 | 0 | 0.22443 | 0 | 0.22443 | 0 | 0 | 0.22443 |  |  |  |  | N/A | [7 empty] | 2018-06-16 | [29 empty] | 38.9288 | -120.77
31048480 |  |  |  | STS-POLE_IDLE_REMV-S/O 21604 DONNER P |  |  | CLSD |  | 0 | 230 | 230 | 0.043561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 230 | 0.043561 | 0 | 0 | 0 | 0 | 0.043561 | 0 | 0.043561 | 0 | 0.043561 | 0 | 0 | 0.043561 |  |  |  |  | N/A | [7 empty] | 2018-06-07 | [29 empty] | 39.3233 | -120.3816
31081464 |  |  |  | STS-REMV IDLE FAC 8110 DICK COOK RD |  |  | CLSD |  | 0 | 819 | 819 | 0.15511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 819 | 0.15511 | 0 | 0 | 0 | 0 | 0.15511 | 0 | 0.15511 | 0 | 0.15511 | 0 | 0 | 0.15511 |  |  |  |  | N/A | [7 empty] | 2018-03-24 | [29 empty] | 38.7924 | -121.1522
31082393 |  |  |  | RECON THREE SPANS CHERRY RIDGE RD |  |  | DOCC | 686.4 | 0 | 1345 | 1345 | 0.25473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-03-15 17:00 |  |  | 2019-02-21 |  | 2019-02-21 |  |  | Yes | 2019-02-21 | [6 empty] | No | 15/50 | 50 | 15 | [12 empty] | Full |  |  | Full |  |  | Need laydown | Full | [5 empty] | Annual see long text 3/12 |  | 1980-01-01 | Y | [11 empty] | 1345 | 0.25473 | 0 | 0 | 0 | 0 | 0.25473 | 0 | 0.25473 | 0 | 0.25473 | 0 | 4.3063e-17 | 0.25473 |  |  | 2019-03-15 17:00 |  | N/A | 2019-08-05 | 2019-08-06 | Yes | 2019-08-06 | 2019-03-21 |  |  | 2019-08-06 | [17 empty] | 8 | [9 empty] | Sebastopol | Sonoma | 38.4061 | -122.8917 | 31082393 |  |  |  | 2019 | Q2 | [5 empty] | MOLINO 1102178 | 321 |  |  |  | 2021-03-01 13:32
31088475 |  |  |  | CCM REM IDLE LINE^ 17171 SFD BVD INVERV |  |  | CLSD |  | 0 | 3673 | 3673 | 0.69564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 2AF | IF | [60 empty] | 3673 | 0.69564 | 0 | 0 | 0 | 0 | 0.69564 | 0 | 0.69564 | 0 | 0.69564 | 0 | 0 | 0.69564 |  |  |  |  | N/A | [7 empty] | 2018-08-29 | [29 empty] | 38.0493 | -122.5592
31089263 |  |  |  | MOVE FUSE 1179/RECON WITH TREE WIRE |  |  | UNSE |  | 0 | 400 | 400 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 |  |  | DI | 08W | SH | 2023-12-25 |  |  |  | 2020-10-31 |  |  |  |  | 2016-08-03 | [23 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  | No | INPR |  |  |  |  | 2016-11-09 | [23 empty] | Not Required | [6 empty] | Walnut Creek | Contra Costa | 0 | 0 | 31089263 |  |  | 2021-167 | 2021 |  |  |  | 2020-09-01 |  |  | SOBRANTE 1102L510R | 1384
31098626 |  | 2020 | 220 Mile Plan | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 |  |  | FICL | 3400 | 0 | 8052 | 8052 | 1.525 | 8052 | 1.525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2018-07-03 | [8 empty] | 2018-06-24 | [12 empty] | Yes |  |  |  | 2018-05-16 | 2018-05-16 |  |  |  |  | Full | 2018-05-03 | 2018-05-03 | Full |  |  |  | Full |  |  | Yes | [5 empty] | Y | [11 empty] | 0 | 0 | 8052 | 1.525 | 0 | 0 | 1.525 | 0 | 1.525 | 0 | 1.525 | 0 | -1.7225e-16 | 1.525 |  | Keep | 2018-07-03 | Yes | COMP | 2018-07-16 | 2020-06-26 | Yes | 2020-12-01 | 2018-09-18 | 2020-11-30 | 2020-11-30 | 2020-11-10 |  | Yes | Shovel Ready |  | 1301220 |  |  | 1543425 | 242205 |  |  | 1273909.1 |  |  | -32.478 | [12 empty] | El Dorado Hills | El Dorado | 38.6997 | -121.0284 | P.11129 |  |  |  | 2020 | Q3 |  |  |  |  | Y | CLARKSVILLE 210413352 | 274
31102666 |  |  |  | REMV IDLE FAC 6 LOCS WO C/O5095 NAP+++++ |  |  | PEND |  | 0 | 1245 | 1245 | 0.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 2AF | IF | [60 empty] | 1245 | 0.2358 | 0 | 0 | 0 | 0 | 0.2358 | 0 | 0.2358 | 0 | 0.2358 | 0 | 0 | 0.2358 |  |  |  |  | N/A | [35 empty] | Napa | Napa | 38.2542 | -122.3808
31153500 |  |  |  | STS-COND_IDLE_REMV-27534 GRANDVIEW |  |  | CLSD |  | 0 | 1365 | 1365 | 0.25852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | MI | 2AF | IF |  |  |  |  | 2018-11-26 | [55 empty] | 1365 | 0.25852 | 0 | 0 | 0 | 0 | 0.25852 | 0 | 0.25852 | 0 | 0.25852 | 0 | 0 | 0.25852 |  |  |  |  | N/A | [7 empty] | 2019-05-29 | [27 empty] | Hayward | Alameda | 37.6511 | -122.0462
31159701 |  |  |  | +TRAN_IDLE_REMV-KLAU MINE RD |  |  | CLSD |  | 0 | 710 | 710 | 0.13447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF |  |  |  |  | 2019-06-19 | [55 empty] | 710 | 0.13447 | 0 | 0 | 0 | 0 | 0.13447 | 0 | 0.13447 | 0 | 0.13447 | 0 | 0 | 0.13447 |  |  |  |  | N/A | [7 empty] | 2019-05-28 | [29 empty] | 35.6253 | 120.6945
31159702 |  |  |  | TRAN_IDLE_REMV-CHIMNEY ROCK RD |  |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF |  |  |  |  | 2019-06-19 | [55 empty] | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0 | 0.07197 |  |  |  |  | N/A | [7 empty] | 2019-05-07 | [29 empty] | 35.659 | 120.9226
31207090 |  | 2020 | 220 Mile Plan | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  |  | DOCC | 6861 | 0 | 9487 | 9487 | 1.7968 | 9487 | 1.7968 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1006e-15 |  |  | NB | 08W | SH | 2019-06-13 |  |  | 2019-06-13 |  | 2019-06-13 |  |  | Yes | 2019-06-13 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Need plans - No land constraints at high level review | Full |  |  | Yes |  |  | Expires 9/13/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 9487 | 1.7968 | 0 | 0 | 1.7968 | 3.1006e-15 | 1.7968 | 0 | 1.7968 | 0 | -3.1006e-15 | 1.7968 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-06-19 | 2020-03-09 | 2020-05-04 | 2020-05-08 |  | Yes | Shovel Ready |  | 3466319 |  | 36635 | 3466319 | 0 |  |  | 3482680.1 | [5 empty] | 50 | [9 empty] | Mill Valley | Marin | 0 | 0 | P.11104 |  |  |  | 2020 | Q2 | 2019-06-07 | 2020-04-15 | 2020-06-28 |  | Y | ALTO 1125935 | 634
31209950 |  |  |  | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) |  |  | DOCC | 3000 | 0 | 3008 | 3008 | 0.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-04-19 |  |  | 2019-04-19 | 2019-03-17 | 2019-04-19 |  |  | Yes | 2019-04-19 | 1/14: Job moved back to ESTS to update per standard - Updated submittal for 1/181/23: Job has been resubmitted - waiting for 1st [REDACTED] /28: Resubmitted for ADE review 1/182/3 & 2/11: Pending ADE -ReReview [REDACTED] asked for update on 1/30.2/11: 1st Corrections sent back2/13/4: 2nd ADE submittal and recieved feedback from ADE. Additional poles may need to be added due to 200' interset poles2/18: Pending if additional work is necessary2/20: Scope changed. Pending Easements and Land to move forward2/25: 2nd review on track to be submitted on 2/272/27: follow up with LAND to see if easment is need for interset pole - follow up next week3/4: Pending response from LAND3/6: Land confirmed. QUES in process of fielding3/11: Onsite today, should have by 3/153/13: pending 2nd Submittal shoul be on 3/153/20: 2nd submittal on 3/223/21: 2nd ADE submittal3/27: waiting second corrections4/3: waiting second corrections4/8: Minor corrections and EDRS for approval when complete - [REDACTED] /11: from ADE Change was not made to joint pole intent for location 23, Also it appears FAA process was not completed for the new interset poles4/17: APPR Status |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Bald Eagel - Need laydown yard location, equipment to be used and durations. If construction will start after August then environmental can be released. | Full | [5 empty] | Annual |  | 1980-01-01 | Y | [11 empty] | 3008 | 0.5697 | 0 | 0 | 0 | 0 | 0.5697 | 0 | 0.5697 | 0 | 0.5697 | 0 | 0 | 0.5697 |  |  |  |  | N/A |  |  |  |  | 2019-06-11 |  |  | 2019-08-21 |  |  |  |  | 1216917.9 |  |  | 273660 | -943257.9 |  |  | 1212818 |  |  | -71.537 |  |  | 13 | [9 empty] | Potter Valley | Mendocino | 39.3808 | -123.1149 | P.11913 |  |  |  | 2019 | Q3 |  |  |  |  | Y | POTTER VALLEY P H 110576498 | 2098
31211614 |  |  |  | IDLE OH 4004 BONES RD SEBASTOPOL*OCLH |  |  | CLSD |  | 0 | 170 | 170 | 0.032197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022727 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 158 | 0.029924 | 0 | 0 | 0.029924 | 0.0022727 | 0.032197 | 0 | 0.032197 | 0 | -0.0022727 | 0 |  |  |  |  | N/A | [7 empty] | 2020-02-03 | [27 empty] | Sebastopol | Sonoma | 38.4361 | -122.9103
31215474 |  |  |  | RECONDUCTOR ROB ROY 2104-MCDONALD RD |  |  | CLSD | 2719 | 0 | 2719 | 2719 | 0.51496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-02-08 |  |  | 2019-02-08 |  | 2019-02-08 |  |  | Yes | 2019-03-28 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | In Construction, ERTC issued | Full | [5 empty] | Annual permit uploaded 2/22 |  | 1980-01-01 | Y | [11 empty] | 2719 | 0.51496 | 0 | 0 | 0 | 0 | 0.51496 | 0 | 0.51496 | 0 | 0.51496 | 0 | 8.6126e-17 | 0.51496 |  |  |  |  | N/A |  |  |  |  | 2019-03-28 |  |  | 2019-05-16 |  |  |  |  | 543773 |  |  | 625339 | 81566 |  |  | 541456.9 | [5 empty] | 19 | [9 empty] | Aptos | Santa Cruz | 36.9875 | -121.8608 | P.11413 |  |  |  | 2019 | Q2 |  |  |  |  | Y | ROB ROY 210410954 | 1532 |  |  |  | 2021-03-01 20:30
31232280 |  |  |  | ZACA 1102 LONG CYN RD, SANTA YNEZ |  |  | FICL | 5851 | 0 | 5851 | 5851 | 1.1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-05-22 |  |  | 2019-04-01 |  | 2019-04-01 |  |  | Yes | 2019-04-01 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | ERTC released | Full | [7 empty] | 1980-01-01 | Y | [11 empty] | 5851 | 1.1081 | 0 | 0 | 0 | 0 | 1.1081 | 0 | 1.1081 | 0 | 1.1081 | 0 | 0 | 1.1081 |  |  | 2019-05-22 |  | N/A | 2019-05-23 08:00 | 2019-06-30 17:00 | Yes | 2019-06-30 17:00 | 2019-04-17 |  |  | 2019-08-06 | [17 empty] | 24 | [9 empty] | Santa Ynez | Santa Barbara | 34.6544 | -120.074 | P.11690 |  |  |  | 2019 | Q2 | [5 empty] | ZACA 1102Y54 | 1154
31248532 |  | 2020 | 220 Mile Plan | CWSP HALF MOON BAY 1101 LS CO4063 |  |  | CLSD | 1900 | 0 | 3926 | 3926 | 0.74356 | 3896 | 0.73788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | SH | 2020-06-01 |  |  | 2019-07-09 | 2019-07-09 | 2019-07-09 |  |  | Yes | 2019-07-09 | 4/17 Corrections sent to QUES5/1: job being refielded. Next submittal 5/105/8: added additional locaitons + refield - next submittal will be 5/105/15: job had to be refielded again. Waiting on PE Stamps. Sent in by 5/175/21: submitted for 2nd submittal5/29: waiting for 2nd corrections - ADE pulled for B-Tags5/31: [REDACTED] on vacation. [REDACTED] to take on review6/5: waiting for 2nd corrections. [REDACTED]back from vacation6/7: [REDACTED] sent a note for renumbering alignment issue6/12: QUES to follow with [REDACTED] and provide update6/18: 2nd submittal sent6/26: waiting for corrections back7/3: 3rd submittal sent7/9: Approved and in PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes |  |  |  | 2020-04-06 | 2020-04-06 |  |  |  |  | Full | 2020-04-06 | 2020-04-06 | Full |  |  | Coastal exemption process applies as per San Mateo County on 2/11/2020 - waiting for confirmation of Caltrans permit extension | Full |  | 2020-03-31 | Yes |  |  | Waiting on ERTC |  | 2020-07-17 | Y | 2020-06-01 | [10 empty] | 0 | 0 | 3926 | 0.74356 | 0 | 0 | 0.74356 | 0 | 0.74356 | 0 | 0.74356 | 0 | 0 | 0.74356 |  | Keep |  | Yes | COMP |  |  |  |  | 2020-04-22 | 2020-07-21 | 2020-08-15 | 2020-08-06 |  | Yes | Shovel Ready | [14 empty] | 17 | [9 empty] | Half Moon Bay | San Mateo | 37.4891 | -122.3917 | P.12008.01 |  |  | 2020-086 | 2020 | Q3 | 2019-07-09 | 2022-01-19 |  |  | Y | HALF MOON BAY 11018902 | 1203
31252335 |  |  |  | 0611POLE_IDLE_REMV-12398 SHALE RIDGE LN |  |  | CLSD |  | 0 | 499 | 499 | 0.094508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 499 | 0.094508 | 0 | 0 | 0 | 0 | 0.094508 | 0 | 0.094508 | 0 | 0.094508 | 0 | 0 | 0.094508 |  |  |  |  | N/A | [7 empty] | 2017-08-11 | [27 empty] | Auburn | Placer | 38.953 | -121.0896
31252580 |  |  |  | 3/1/18 REMV IF IRO COURTNEY DR KENW*OCLH |  |  | CLSD |  | 0 | 171 | 171 | 0.032386 | 171 | 0.032386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 171 | 0.032386 | 0 | 0 | 0.032386 | 0 | 0.032386 | 0 | 0.032386 | 0 | 0 | 0.032386 |  |  |  |  | N/A | [7 empty] | 2018-02-26 | [27 empty] | Kenwood | Sonoma | 38.4225 | -122.5301
31254545 |  |  |  | POLE_IDLE_REMV-SEWER TREATMENT PLANT |  |  | CLSD |  | 0 | 857 | 857 | 0.16231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 857 | 0.16231 | 0 | 0 | 0 | 0 | 0.16231 | 0 | 0.16231 | 0 | 0.16231 | 0 | 0 | 0.16231 |  |  |  |  | N/A | [7 empty] | 2018-06-28 | [29 empty] | 40.649 | -122.6135
31254690 |  |  |  | CCM COND_IDLE_REMV+-3640 HWY 128 |  |  | CLSD |  | 0 | 300 | 300 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 2AF | IF | [60 empty] | 300 | 0.056818 | 0 | 0 | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0.056818 |  |  |  |  | N/A | [7 empty] | 2018-04-04 | [29 empty] | 38.6063 | -122.6299
31254945 |  |  |  | 4/30/18 REMV IF -750 CHILENO VALLEY*OCLH |  |  | CLSD |  | 0 | 270 | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0.051136 |  |  |  |  | N/A | [7 empty] | 2018-04-02 | [27 empty] | Petaluma | Sonoma | 38.2092 | -122.6767
31257161 |  |  |  | STS-POLE_IDLE_REMV-R/O 7652 WARREN RD |  |  | CLSD |  | 0 | 490 | 490 | 0.092803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF |  |  |  |  | 2019-03-12 | [55 empty] | 490 | 0.092803 | 0 | 0 | 0 | 0 | 0.092803 | 0 | 0.092803 | 0 | 0.092803 | 0 | 0 | 0.092803 |  |  |  |  | N/A | [7 empty] | 2019-09-06 | [29 empty] | 38.1373 | -120.9225
31269259 |  |  |  | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  |  | FICL | 6336 | 0 | 6386 | 6386 | 1.2095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-06-20 17:00 |  |  | 2019-04-01 |  | 2019-04-01 |  |  | Yes | 2019-04-01 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | ERTC released | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 6386 | 1.2095 | 0 | 0 | 0 | 0 | 1.2095 | 0 | 1.2095 | 0 | 1.2095 | 0 | 0 | 1.2095 |  |  | 2019-06-20 17:00 |  | N/A | 2019-03-11 08:00 | 2019-09-26 | Yes | 2019-09-26 17:00 | 2019-04-12 |  |  | 2019-08-08 | [17 empty] | 22 | [9 empty] | Los Olivos | Santa Barbara | 34.6997 | -120.1495 | P.11693 |  |  |  | 2019 | Q2 | [5 empty] | ZACA 1101CB | 2754
31272374 |  |  |  | CWSP PT. MORETTI FROM 5043 TO 5955 |  |  | DOCC | 8500 | 0 | 8500 | 8500 | 1.6098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6098 | 8573 | 1.6237 | CC | 08W |  | 2021-11-19 |  |  | 2019-02-15 |  | 2019-02-15 |  |  | Yes | 2021-02-08 | [5 empty] | COMPLETED | No | No |  | 0 | [6 empty] | 2021-11-19 | 2021-11-19 | [5 empty] | 2021-11-19 | 2021-11-19 |  |  |  | Emergency ERTC was issued 9/4. Coastal & Veg - 11/19/2021 - [REDACTED] sent application week of 2/24/20 |  |  |  | Yes |  |  | Annual uploaded 3/13/19 |  | 2020-10-31 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6098 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2021-03-26 17:00 |  | COMP | 2020-08-31 | 2020-12-18 | Yes | 2020-12-18 | 2021-02-06 |  |  | 2020-09-26 |  |  |  |  | 55000 | 2305462.1 |  | 55000 | 0 |  | 4192% | 2295721.5 |  |  |  | 1432098.8104 |  | 52 | [7 empty] | Remove |  | Davenport | Santa Cruz | 37.0684 | -122.2302 | P.11381 |  |  | 2020-098 | 2022 |  | 2019-02-15 | 2022-01-02 |  |  | Y | POINT MORETTI 11015076 | 2568
31272375 |  |  |  | CWSP PT. MORETTI BEYOND 5995 |  |  | DOCC | 5150 | 0 | 5150 | 5150 | 0.97538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97538 |  |  | CC | 08W |  | 2021-11-19 |  |  | 2019-02-15 |  | 2019-02-15 |  |  | Yes | 2019-02-15 | [5 empty] | COMPLETED | No | No |  | 0 | [6 empty] | 2021-11-19 | 2021-11-19 | [5 empty] | 2021-11-19 | 2021-11-19 |  |  |  | Emergency ERTC was issued 9/4. Coastal & Veg - 11/19/2021 - [REDACTED] sent application week of 2/24/20 |  |  |  | Yes |  |  | Annual uploaded 3/1/19 |  | 2020-10-31 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97538 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | COMP | [12 empty] | 55000 |  |  | 55000 | 0 |  |  | 82551 | [5 empty] | 33 | [7 empty] | Remove |  | Davenport | Santa Cruz | 37.0854 | -122.2453 | P.11379 |  |  | 2020-099 | 2022 |  | 2019-02-15 | 2022-01-22 |  |  | Y | POINT MORETTI 110112122 | 2707
31275658 |  |  |  | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  |  | DOCC | 1700 | 0 | 2580 | 2580 | 0.48864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-09-27 |  |  | 2019-02-28 |  | 2019-02-28 |  |  | Yes | 2019-02-28 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Need laydown. | Full |  |  | Yes |  |  | Private property. No tasks are activated. |  | 1980-01-01 | Y | [11 empty] | 2580 | 0.48864 | 0 | 0 | 0 | 0 | 0.48864 | 0 | 0.48864 | 0 | 0.48864 | 0 | 0 | 0.48864 |  |  | 2019-09-27 |  | N/A | 2019-08-06 | 2019-08-30 | Yes | 2019-08-30 | 2019-04-25 |  |  | 2019-08-30 |  |  |  |  | 775316.6 |  |  | 1092540 | 317223.4 |  |  | 652020.6 |  |  | -1.494 |  |  | 11 | [9 empty] | Sonoma | Sonoma | 38.3327 | -122.5266 | 31275658 |  |  |  | 2019 | Q2 |  |  |  |  | Y | DUNBAR 11021285 | 449
31278200 |  |  |  | +OCEANO 1102 S HALCYON & PINE RDGE |  |  | CLSD | 2081 | 0 | 2059.2 | 2059.2 | 0.39 | 21.8 | 0.0041288 | 0 | 0 | 0 | 0 | 0 | 0 | -8.6126e-17 |  |  | LP | 08W | SH | 2019-02-08 |  |  | 2019-02-08 |  | 2019-02-08 |  |  | Yes | 2019-02-08 | 2/3: Approved on 1/17 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 2059.2 | 0.39 | 0 | 0 | 0 | 0 | 0.39 | -8.6126e-17 | 0.39 | 0 | 0.39 | 0 | 0 | 0.39 |  |  |  |  | N/A |  |  |  |  | 2019-02-22 |  |  | 2019-03-21 |  |  |  |  | 476629 |  |  | 496629 | 20000 |  |  | 455075 | [5 empty] | 12 | [9 empty] | Arroyo Grande | San Luis Obispo | 35.0696 | -120.5679 | P.11685 |  |  |  | 2019 | Q2 |  |  |  |  | Y | OCEANO 1102V56 | 1779
31286573 |  |  |  | APPLE HILL 2102 HIGH SPLICE AREA |  |  | CLSD | 3700 | 0 | 3492 | 3492 | 0.66136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-01-30 |  |  | 2019-01-30 |  | 2019-01-30 |  |  | Yes | 2019-01-30 | 1/30: job was approved and EDRS |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 3492 | 0.66136 | 0 | 0 | 0 | 0 | 0.66136 | 0 | 0.66136 | 0 | 0.66136 | 0 | 0 | 0.66136 |  |  |  |  | N/A |  |  |  |  | 2019-03-18 |  |  | 2019-05-06 |  |  |  |  | 574040 |  |  | 900307 | 326267 |  |  | 543235.6 | [5 empty] | 14 | [9 empty] | Somerset | El Dorado | 0 | 0 | 31286573 |  |  |  | 2019 | Q2 |  |  |  |  | Y | APPLE HILL 2102186912 | 1461
31289238 |  |  |  | FRUITLAND 1142 INS TREE WIRE LR 6064 |  |  | DOCC | 6200 | 0 | 6271 | 6271 | 1.1877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-03-13 |  |  | 2019-03-13 | 2019-04-14 | 2019-03-13 |  |  | Yes | 2019-07-24 | 3/11: Pending review of the Ocalc stamp |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | need future ERTC call | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 6271 | 1.1877 | 0 | 0 | 0 | 0 | 1.1877 | 0 | 1.1877 | 0 | 1.1877 | 0 | 0 | 1.1877 |  |  | 2018-06-12 08:00 |  | N/A | 2019-07-15 | 2019-07-26 | Yes | 2019-07-26 | 2019-07-26 |  |  | 2019-07-26 | [17 empty] | 27 | [9 empty] | Myers Flat | Humboldt | 40.2734 | -123.7722 | P.11908 |  |  |  | 2019 | Q2 | [5 empty] | FRUITLAND 11426064 | 786
31290145 |  |  |  | R7 SAN RAFAEL 1107 COND REPLACEMENT |  |  | FICL | 370 | 0 | 801 | 801 | 0.1517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-04-19 |  |  | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-03-11 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Need laydown | Full |  |  | Yes |  |  | Extended on 3/20/19 |  | 1980-01-01 | Y | [11 empty] | 801 | 0.1517 | 0 | 0 | 0 | 0 | 0.1517 | 0 | 0.1517 | 0 | 0.1517 | 0 | 0 | 0.1517 |  |  | 2019-04-19 |  | N/A | 2019-08-07 | 2019-08-12 | Yes | 2019-08-12 | 2019-04-09 |  |  | 2019-08-12 | [17 empty] | 6 | [9 empty] | Greenbrae | Marin | 37.9468 | -122.5599 | 31290145 |  |  |  | 2019 | Q2 | [5 empty] | SAN RAFAEL 11071166 | 818
31290147 |  |  |  | OCCCR7 OLEMA 1101 REPLACE COND VISION RD |  |  | CLSD | 3280 | 0 | 3174 | 3174 | 0.60114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8.6126e-17 |  |  | NB | 08W | SH | 2019-02-20 |  |  | 2019-02-20 |  | 2019-02-20 |  |  | Yes | 2019-05-14 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Coastal Commission / No Heli work before August | Full |  |  | Yes |  |  | Not a county maintainted road |  | 1980-01-01 | Y | [11 empty] | 3174 | 0.60114 | 0 | 0 | 0 | 0 | 0.60114 | -8.6126e-17 | 0.60114 | 0 | 0.60114 | 0 | 8.6126e-17 | 0.60114 |  |  |  |  | N/A |  |  |  |  | 2019-05-14 |  |  | 2019-09-20 | [17 empty] | 14 | [9 empty] | Inverness | Marin | 38.0994 | -122.8752 | P.11781 |  |  |  | 2019 | Q3 |  |  |  |  | Y | OLEMA 110150396 | 357
31291071 |  |  |  | OCGC 14043533 WRO - HWY 175 MIDDLETOWN |  |  | CLSD |  | 0 | 6583 | 6583 | 1.2468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 10J |  | 2019-03-28 | [59 empty] | 6583 | 1.2468 | 0 | 0 | 0 | 0 | 1.2468 | 0 | 1.2468 | 0 | 1.2468 | 0 | 0 | 1.2468 |  |  | 2019-03-28 |  | N/A | 2019-05-31 08:00 | 2019-09-16 | Yes | 2019-09-16 |  |  |  | 2019-09-16 | [29 empty] | 39.5848 | -123.4602 |  |  |  |  | 2019 | [5 empty] | Y
31291639 |  |  |  | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  |  | ESTS | 2745 | 0 | 3100 | 3100 | 0.58712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58712 |  |  | LP | 08W |  | 2022-09-26 17:00 | [7 empty] | Yes | 2020-07-14 | [6 empty] | Yes | [15 empty] | Full |  |  | Full |  |  | High level review constraints unlikely | Full | [7 empty] | 2022-02-01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58712 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-09-26 17:00 |  | INPR | 2022-11-09 11:00 | 2022-12-05 11:00 |  | 2022-12-26 11:00 | 2020-07-01 | [7 empty] | 150000 | 2284449.4 |  | 150000 | 0 |  | 1523% | 122229.3 |  |  |  | 3890933.1716 |  | 12 |  | Transmission [REDACTED] to follow up with prelim date | [5 empty] | Remove |  | San Luis Obispo | San Luis Obispo | 35.2924 | -120.7159 | 31291639 |  |  |  | 2022 | [5 empty] | Y | FOOTHILL 1101CB | 668
31297994 |  |  |  | 12/31/18-T2-PLE_IDL_REM-1E/O 16N/O C/O P |  |  | CLSD |  | 0 | 895 | 895 | 0.16951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 895 | 0.16951 | 0 | 0 | 0 | 0 | 0.16951 | 0 | 0.16951 | 0 | 0.16951 | 0 | 0 | 0.16951 |  |  |  |  | N/A | [7 empty] | 2018-10-02 | [29 empty] | 41.3249 | -123.5155
31298793 |  |  |  | OFAC_IDLE_REMV - 2 S/O 5 W/O 5245 HWY 49 |  |  | CLSD |  | 0 | 285 | 285 | 0.053977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 285 | 0.053977 | 0 | 0 | 0 | 0 | 0.053977 | 0 | 0.053977 | 0 | 0.053977 | 0 | 0 | 0.053977 |  |  |  |  | N/A | [7 empty] | 2018-08-22 | [27 empty] | Auburn | Placer | 38.9816 | -121.1133
31319444 |  |  |  | RECON 5-SPANS PORTER CRK RD-RINCON 1103 |  |  | CLSD | 1100 | 0 | 1279 | 1279 | 0.24223 | 5 | 0.00094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-19 |  |  | 2019-02-19 |  | 2019-02-19 |  |  | Yes | 2019-02-19 | 2/20: Approved |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Need laydown | Full |  |  | Yes |  |  | Using Annual |  | 1980-01-01 | Y | [11 empty] | 1279 | 0.24223 | 0 | 0 | 0 | 0 | 0.24223 | 0 | 0.24223 | 0 | 0.24223 | 0 | 0 | 0.24223 |  |  |  |  | N/A |  |  |  |  | 2019-06-17 |  |  | 2019-12-14 | [17 empty] | 6 | [9 empty] | Santa Rosa | Sonoma | 38.5541 | -122.6551 | 31319444 |  |  |  | 2019 | Q3 |  |  |  |  | Y | RINCON 11035152 | 440
31323810 |  |  |  | T3-COND_IDLE_REMV-2042 HIDDEN VALL*OCLH |  |  | CLSD |  | 0 | 180 | 180 | 0.034091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034091 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.034091 | 0 | 0 | 0.034091 | 0.034091 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2019-12-13 | [29 empty] | 38.4597 | -122.7023
31326034 |  |  |  | STS-POLE_IDLE_REMV - 27218 FAIRVIEW AVE |  |  | CLSD |  | 0 | 134 | 134 | 0.025379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | MI | 2AF | IF | [60 empty] | 134 | 0.025379 | 0 | 0 | 0 | 0 | 0.025379 | 0 | 0.025379 | 0 | 0.025379 | 0 | 0 | 0.025379 |  |  |  |  | N/A | [7 empty] | 2019-04-24 | [29 empty] | 37.6665 | -122.0274
31326119 |  |  |  | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR |  |  | CLSD | 2813 | 0 | 2990 | 2990 | 0.56629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-24 |  |  | 2019-06-24 | 2019-04-11 | 2019-06-24 |  |  | Yes | 2019-06-24 | 4/8: Still Pending response from transmission - QUES to send a follow up email cc'ing myself and [REDACTED] . [REDACTED] to follow up with Transmission4/17 - 5/1: still waiting for transmission5/8: On Hold - Transmission underbuild5/21: submitted for 1st ADE for review5/29: waiting for 1st corrections - ADE was pulled to review B-Tags5/30: Need review from [REDACTED] by 6/6 to try and make EOD of 6/146/4: Are preliminary drawings good to go? Or should we wait for transmission response6/5: waiting on 1st corrections, corrections should be completd by 6/76/11: 1st corrections sent6/12: QUES needs clarification between engineer and ADE - pushed EOD to 6/216/18: EDRS routed6/24: APPROVED |  |  |  | Completed | COMPLETED | Yes |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Need laydown. Updated estimation being reviewed | Full |  |  | Yes |  |  | Private - [REDACTED] to note in SAP |  | 1980-01-01 | Y | [11 empty] | 2990 | 0.56629 | 0 | 0 | 0 | 0 | 0.56629 | 0 | 0.56629 | 0 | 0.56629 | 0 | 0 | 0.56629 |  |  |  |  | N/A |  |  |  |  | 2019-06-27 |  |  | 2019-11-15 |  |  |  |  | 1074304.5 |  |  | 1325896 | 251591.5 |  |  | 997479.3 | [5 empty] | 17 | [9 empty] | Colfax | Placer | 39.0375 | -120.9882 | P.11895 |  |  |  | 2019 | Q4 |  |  |  |  | Y | WEIMAR 1101CB | 1889
31334291 |  |  |  | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  |  | PEND | 1920 | 0 | 2710 | 2710 | 0.51326 | 0 | 0 | 0 | 0 | 2710 | 0.51326 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-03-15 |  |  | 2019-02-20 | 2020-09-30 | 2019-02-20 |  |  | Yes | 2019-04-12 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full | 2021-03-15 | 2021-03-15 |  |  |  | Submitted second permit package to Mendocino County LCP in July. County is agreeing to process under CEQA exemption with additional measures included for biological resources. Driving for February 2021 approval hearing. |  |  |  | Yes | 2021-12-31 |  | Not required - private property - see long text 10/25/18 | [6 empty] | Waiting on ERTC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51326 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2019-03-29 08:00 | Yes | COMP | 2022-04-29 08:00 | 2022-05-17 17:00 |  | 2022-05-18 08:00 | 2019-04-11 |  |  |  | 2020-07-30 | Yes |  |  | 337210 | 1118242 |  | 1115282 | 778072 |  | 331.6% | 358769.9 |  |  |  | 2178715.0406 |  | 10 |  |  | Complete |  |  |  |  | Remove |  | Fort Bragg | Mendocino | 39.5022 | -123.7717 | 31334291 |  |  | 2021-123 | 2021 | 2020 Reserve | 2019-02-20 | 2020-10-30 | 2020-11-18 |  | Y | FORT BRAGG A 11013113 | 2140 |  | WDDB |  | 2021-03-08 13:45
31334292 |  |  |  | RECON 9-SPANS, AUSTIN CREEK RD |  |  | CLSD | 2550 | 0 | 2493 | 2493 | 0.47216 | 20 | 0.0037879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-25 |  |  | 2019-02-25 |  | 2019-02-25 |  |  | Yes | 2019-02-25 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Need laydown | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 2493 | 0.47216 | 0 | 0 | 0 | 0 | 0.47216 | 0 | 0.47216 | 0 | 0.47216 | 0 | 0 | 0.47216 |  |  |  |  | N/A |  |  |  |  | 2019-03-20 |  |  | 2019-09-20 | [17 empty] | 13 | [9 empty] | Cazadero | Sonoma | 38.49 | -123.0599 | 31334292 |  |  |  | 2019 | Q3 | [5 empty] | MONTE RIO 111123916 | 312
31343500 |  | 2020 | 220 Mile Plan | CWSP ORINDA 401 HIGH SPLICE COUNT |  |  | FICL | 8023 | 0 | 7959 | 7959 | 1.5074 | 7959 | 1.5074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2020-03-31 |  |  | 2019-12-16 | 2019-12-16 | 2019-12-16 |  |  | Yes | 2020-03-10 | 12/11: Can EDRS meet 12/12 EOD?12/05 EEI submitted for 6th ADE Rvw - ADE rtn 6th corrections to contractor (change top/side tiers per UB Td-015195-B001) - EEI submitted changes - ADE approved for EDRS12/04: EEI submitted for 5th ADE rvw - ADE rtn 5th corrections to contractor12/02: On Track for 4th sub11/27: EOD pushed to apply corrections and route11/23: ADE rtn 4th corrections to contractor11/20: EOD pushed 1 wk - EEI to update on progress11/13: Push 1wk - Finalize review and processing EDRS11/12: EEI submitted for 4th ADE rvw11/08: ADE returned 3rd corrections to contractor11/07: EEI submitted for 3rd ADE rvw11/06: Contractor working with ADE on clarifying information, Voltage drops/updates11/01: ADE returned corrections to Contractor10/30: In rvw with [REDACTED] /29: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]10/23: On track (EOW)10/18: ADE rtn 1st corrections to contractor10/16: Check with ADE - ADE finalizing other projects10/09: ADE on target for 1st review completion (finding alot of errors)10/04: Rvw initiated - EEI uploaded revised OCalcs per ADE request10/02: In review9/26: ADE assigned ( [REDACTED] ) (2nd rvw set at 2wks)9/23: Scope update submitted for ADE rvw; Change order approved9/18: Additional Change Order [B] in process9/11 - 9/18: On Target for 1st submittal 9/23--> [RCC Issue]9/04: Missing Scope in change - Change Order [A] to be submitted by EEI - On Track for 9/238/22: NTP issued - EEI Est target completion date set at 9/237/29: Scope change initiated*Original ADE for pre-redesign - [REDACTED] /2: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Scope change due to veg conflicts - needs to be reestimated. 7/23 | Full |  |  | Yes |  |  | Received 7/11 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7959 | 1.5074 | 0 | 0 | 1.5074 | 0 | 1.5074 | 0 | 1.5074 | 0 | 0 | 1.5074 |  | Keep | 2020-03-31 | Yes | COMP | 2020-02-24 08:00 | 2020-05-13 | Yes | 2020-05-13 | 2020-03-10 | 2020-02-24 | 2020-05-12 | 2020-05-13 |  | Yes | Shovel Ready |  | 2998329.3 |  |  | 4611914 | 1613584.7 |  |  | 2743432.3 | [5 empty] | 77 | [9 empty] | Orinda | Contra Costa | 37.8861 | -122.1985 | 31343500 |  |  |  | 2020 | Q1 | 2019-12-16 | 2020-02-17 | 2020-05-17 |  | Y | ORINDA 0401N545R | 1632
31354988 |  |  |  | TULUCAY 1101 RECOND WITH TREE WIRE |  | In Scoping | UNSE |  | 7180.8 | 316.8 | 7497.6 | 1.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.42 |  |  | NB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.42 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.2124 | -122.2111
31360766 |  |  |  | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW |  |  | CLSD | 31360766 | 0 | 1153 | 1153 | 0.21837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2019-03-18 |  |  | 2019-03-18 |  | 2019-03-18 |  |  | Yes | 2019-03-18 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Released in march | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 1153 | 0.21837 | 0 | 0 | 0 | 0 | 0.21837 | 0 | 0.21837 | 0 | 0.21837 | 0 | 0 | 0.21837 |  |  |  |  | COMP |  |  |  |  | 2019-04-29 |  |  | 2019-05-20 |  |  |  |  | 416838 |  |  | 474763 | 57925 |  |  | 400124.9 | [5 empty] | 31360766 | [9 empty] | Murphys | Calaveras | 38.1373 | -120.4594 | 31360766 |  |  |  | 2019 | Q2 |  |  |  |  | Y | FROGTOWN 170113412 | 921 |  |  |  | 2021-03-01 20:30
31361965 |  |  |  | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  |  | CONS | 2300 | 0 | 2367 | 2367 | 0.4483 | 0 | 0 | 0 | 0 | 2367 | 0.4483 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2020-11-16 |  |  | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-06-19 | 3/6: approved will be routed today |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-11-16 | 2020-11-16 | Full |  |  | 1602 permit conditions apply. Have approval of the amended agreement and mitigation plan by CDFW as of 11/5/20 | Full |  |  | Yes | 2021-12-31 |  | Received and under review 7/23 |  | 2020-11-30 | Y | 2020-11-16 |  |  | Waiting on CDFW permitting | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4483 | 0 | 0 | 0.4483 | 0.4483 | 0 | 0 |  | Remove | 2019-06-21 | Yes | COMP | 2021-03-29 08:00 | 2021-05-14 08:00 |  | 2021-06-14 17:00 | 2020-07-24 |  |  |  |  | Yes |  |  | 747947 | 1452193.7 |  | 1245293 | 497346 | -1420541.7 | 194.2% | 320694.5 | 1847794.2 | 2168488.7 |  | 3239367.4423 |  | 10 | [7 empty] | Remove |  | Kenwood | Sonoma | 38.3919 | -122.53 | 31361965 |  |  |  | 2020 | Q3 | 2019-03-06 | 2020-07-15 | 2020-08-04 |  | Y | DUNBAR 110147964 | 1794 |  | WDDB |  | 2021-03-04 09:47
31364361 |  |  |  | 0428OFAC_IDLE_REMV 12310 OLD AUBURN 4TA |  |  | FICL |  | 0 | 394 | 394 | 0.074621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 394 | 0.074621 | 0 | 0 | 0 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0.074621 | 0 | 0 | 0.074621 |  |  |  |  | N/A | [7 empty] | 2018-06-22 | [29 empty] | 39.193 | -121.079
31366453 |  |  |  | STS-COND_BROK_REPL - LANDERGEN RD HONEYD |  |  | CLSD |  | 0 | 205 | 205 | 0.038826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 205 | 0.038826 | 0 | 0 | 0 | 0 | 0.038826 | 0 | 0.038826 | 0 | 0.038826 | 0 | 0 | 0.038826 |  |  |  |  | N/A | [37 empty] | 40.2264 | -124.1108
31389447 |  |  |  | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  |  | DOCC | 6740 | 0 | 6705.6 | 6705.6 | 1.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-01 |  |  | 2019-01-01 |  | 2019-01-01 |  |  | Yes | [7 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 6705.6 | 1.27 | 0 | 0 | 0 | 0 | 1.27 | 0 | 1.27 | 0 | 1.27 | 0 | 0 | 1.27 |  |  |  |  | N/A | [7 empty] | 2019-03-29 |  |  |  |  | 3937382 |  |  | 3937382 | 0 |  |  | 3918024.7 | [5 empty] | 36 | [9 empty] | Napa | Napa | 38.3812 | -122.2913 | P.11939 |  |  |  | 2019 | Q2 |  |  |  |  | Y | PUEBLO 1105696 | 1210
31401029 |  | 2020 | T1 A Tag | NO-NV-SHASTA CO-07/23/18 CARR FIRE |  |  | POST | 16868 | 0 | 16389.09 | 16389.09 | 3.104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | [61 empty] | 16389.09 | 3.104 | 0 | 0 | 0 | 0 | 3.104 | 0 | 3.104 | 0 | 3.104 | 0 | -4.8149e-08 | 3.104 |  |  |  |  | N/A | 2019-01-02 08:00 | 2019-08-30 17:00 | Yes | 2019-08-30 17:00 |  | 2021-09-20 07:00 | 2021-09-24 16:00 | [18 empty] | 88 | [11 empty] | 40.6866 | -122.6412 |  |  |  |  | 2019
31406815 |  |  |  | POD REMV IDLE FAC 4800 MUNIZ RANCH*W |  |  | FICL |  | 0 | 381 | 381 | 0.072159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF |  |  |  |  | 2019-10-14 | [55 empty] | 381 | 0.072159 | 0 | 0 | 0 | 0 | 0.072159 | 0 | 0.072159 | 0 | 0.072159 | 0 | 0 | 0.072159 |  |  |  |  | N/A | [35 empty] | Cazadero | Sonoma | 38.5104 | -123.14
31415330 |  |  |  | NO-NV-BUTTE-11/08/18 CAMP FIRE |  |  | ESTS |  | 0 | 24356.2 | 24356.2 | 4.6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | [61 empty] | 24356.2 | 4.6129 | 0 | 0 | 0 | 0 | 4.6129 | 0 | 4.6129 | 0 | 4.6129 | 0 | 0 | 4.6129 |  |  |  |  | N/A | 2019-01-02 | 2019-12-31 17:00 | Yes | 2019-12-31 17:00 | [33 empty] | 0 | 0 |  |  |  |  | 2019
31420416 |  |  |  | BUCOCAMP - 675 SUNSET DR PARADISE |  |  | CLSD |  | 0 | 883 | 883 | 0.16723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 883 | 0.16723 | 0 | 0 | 0 | 0 | 0.16723 | 0 | 0.16723 | 0 | 0.16723 | 0 | 0 | 0.16723 |  |  |  |  | N/A | [7 empty] | 2019-03-08 | [27 empty] | Paradise | Butte | 39.7688 | -121.6265 |  |  |  |  | 2019
31420810 |  |  |  | BUCOCAMP-6160 FORTY OAKS LN PARADISE |  |  | CLSD |  | 0 | 827 | 827 | 0.15663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 827 | 0.15663 | 0 | 0 | 0 | 0 | 0.15663 | 0 | 0.15663 | 0 | 0.15663 | 0 | -2.1532e-17 | 0.15663 |  |  |  |  | N/A | [7 empty] | 2019-01-12 | [27 empty] | Paradise | Butte | 39.7705 | -121.6338 |  |  |  |  | 2019
31422565 |  |  |  | BUCOCAMP -6250 MOUNTAIN VIEW DR PARADISE |  |  | CLSD |  | 0 | 356 | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0.067424 | 0 | 0.13902 | 0 | 0.13902 | 0 | -0.071591 | 0.13902 |  |  |  |  | N/A | [7 empty] | 2019-02-09 | [29 empty] | 39.7743 | -121.57 |  |  |  |  | 2019
31422566 |  |  |  | BUCOCAMP -6250 MOUNTAIN VIEW DR PARADISE |  |  | CLSD |  | 0 | 356 | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 356 | 0.067424 | 0 | 0 | 0 | 0 | 0.067424 | 0 | 0 | 0 |  | 0 | 0.067424 | 0 |  |  |  |  | N/A | [7 empty] | 2019-02-09 | [29 empty] | 39.7724 | -121.5689 |  |  |  |  | 2019
31422838 |  |  |  | BUCOCAMP -7057 MOLOKAI DR PARADISE |  |  | CLSD |  | 0 | 83.5 | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0.015814 | 0 | 0.031629 | 0 | 0.031629 | 0 | -0.015814 | 0.031629 |  |  |  |  | N/A | [7 empty] | 2019-02-07 | [27 empty] | Paradise | Butte | 39.7836 | -121.6044 |  |  |  |  | 2019
31422901 |  |  |  | BUCOCAMP -7057 MOLOKAI DR PARADISE |  |  | CLSD |  | 0 | 83.5 | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95B | BUCOCAMP | [60 empty] | 83.5 | 0.015814 | 0 | 0 | 0 | 0 | 0.015814 | 0 | 0 | 0 |  | 0 | 0.015814 | 0 |  |  |  |  | N/A | [7 empty] | 2019-02-07 | [29 empty] | 39.7836 | -121.6048 |  |  |  |  | 2019
31422902 |  |  |  | BUCOCAMP -5295 S LIBBY RD PARADISE |  |  | CLSD |  | 0 | 255 | 255 | 0.048295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 255 | 0.048295 | 0 | 0 | 0 | 0 | 0.048295 | 0 | 0.045644 | 0 | 0.045644 | 0 | 0.0026515 | 0.045644 |  |  |  |  | N/A | [7 empty] | 2019-02-23 | [29 empty] | 39.7405 | -121.5938 |  |  |  |  | 2019
31422909 |  |  |  | BUCOCAMP - 874 BUSCHMANN RD PARADISE |  |  | FICL |  | 0 | 905 | 905 | 0.1714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 905 | 0.1714 | 0 | 0 | 0 | 0 | 0.1714 | 0 | 0.1714 | 0 | 0.1714 | 0 | -2.1532e-17 | 0.1714 |  |  |  |  | N/A | [7 empty] | 2020-02-13 | [29 empty] | 39.7466 | -121.6137 |  |  |  |  | 2019
31423331 |  |  |  | BUCOCAMP - 6168 TWIN LN PARADISE |  |  | CLSD |  | 0 | 420 | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0 | 0.079545 |  |  |  |  | N/A | [7 empty] | 2019-03-22 | [29 empty] | 39.7703 | -121.6074 |  |  |  |  | 2019
31425506 |  |  |  | BUCOCAMP - 5541 VISTA WAY PARADISE |  |  | CLSD |  | 0 | 264 | 264 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 264 | 0.05 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0.05 | 0 | 0.05 | 0 | 0 | 0.05 |  |  |  |  | N/A | 2019-01-02 17:00 | 2019-03-15 | Yes | 2019-03-15 |  |  |  | 2019-03-07 | [29 empty] | 39.7482 | -121.636 |  |  |  |  | 2019
31425508 |  |  |  | BUCOCAMP - 6097 LAUREL DR PARADISE |  |  | CLSD |  | 0 | 422 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 422 | 0.079924 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0.08 | 0 | 0.08 | 0 | -7.5758e-05 | 0.08 |  |  |  |  | N/A | 2019-01-02 08:00 | 2019-03-15 17:00 | Yes | 2019-03-15 17:00 |  |  |  | 2019-03-06 | [29 empty] | 39.7672 | -121.6339 |  |  |  |  | 2019
31425894 |  |  |  | BUCOCAMP - REBUILD CHAPARRAL DR PARADISE |  |  | CLSD |  | 0 | 2017 | 2017 | 0.38201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 2017 | 0.38201 | 0 | 0 | 0 | 0 | 0.38201 | 0 | 0.38314 | 0 | 0.38314 | 0 | -0.0011364 | 0.38314 |  |  |  |  | N/A | [7 empty] | 2019-03-12 | [29 empty] | 39.7324 | -121.6496 |  |  |  |  | 2019
31426083 |  |  |  | BUCOCAMP 5720 ACADEMY DR PARADISE |  |  | CLSD |  | 0 | 174 | 174 | 0.032955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 174 | 0.032955 | 0 | 0 | 0 | 0 | 0.032955 | 0 | 0.032955 | 0 | 0.032955 | 0 | -5.3829e-18 | 0.032955 |  |  |  |  | N/A | [7 empty] | 2019-03-21 | [27 empty] | Paradise | Butte | 39.7546 | -121.6173 |  |  |  |  | 2019
31426086 |  |  |  | BUCOCAMP - 5250 FOSTER RD PARADISE |  |  | CLSD |  | 0 | 50 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0.0094697 |  |  |  |  | N/A | [7 empty] | 2019-04-01 | [29 empty] | 39.7386 | -121.6299 |  |  |  |  | 2019
31426416 |  |  |  | BUCOCAMP - 6452 RIX LN PARADISE |  |  | CLSD |  | 0 | 578 | 578 | 0.10947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 578 | 0.10947 | 0 | 0 | 0 | 0 | 0.10947 | 0 | 0.10076 | 0 | 0.10076 | 0 | 0.0087121 | 0.10076 |  |  |  |  | N/A | [7 empty] | 2019-04-26 | [29 empty] | 39.7777 | -121.5924 |  |  |  |  | 2019
31426417 |  |  |  | BUCOCAMP - 13797 SUGAR PINE DR MAGALIA |  |  | CLSD |  | 0 | 756 | 756 | 0.14318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 756 | 0.14318 | 0 | 0 | 0 | 0 | 0.14318 | 0 | 0.14318 | 0 | 0.14318 | 0 | 0 | 0.14318 |  |  |  |  | N/A | [7 empty] | 2019-05-02 | [29 empty] | 39.8095 | -121.5816 |  |  |  |  | 2019
31426519 |  |  |  | BUCOCAMP - 5250 CALIFORNIA WAY PARADISE |  |  | CLSD |  | 0 | 742 | 742 | 0.14053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 742 | 0.14053 | 0 | 0 | 0 | 0 | 0.14053 | 0 | 0.14053 | 0 | 0.14053 | 0 | 0 | 0.14053 |  |  |  |  | N/A | [7 empty] | 2019-05-07 | [29 empty] | 39.7376 | -121.5957 |  |  |  |  | 2019
31427127 |  |  |  | BUCOCAMP-COMCAST-FOREST SERVICE RD PARAD |  |  | CLSD |  | 0 | 792 | 792 | 0.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | BUCOCAMP | [60 empty] | 792 | 0.15 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0.15 | 0 | 0.15 | 0 | 0 | 0.15 |  |  |  |  | N/A | [7 empty] | 2019-03-13 | [29 empty] | 39.7849 | -121.5889 |  |  |  |  | 2019
31429487 |  |  |  | OTTER-1101 S030CC121 - TRANS POLES |  |  | PEND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2023-12-25 | [8 empty] | 2019-10-17 | [12 empty] | Yes |  |  |  | 2021-12-21 | 2021-12-21 | [5 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A |  |  |  |  | 2019-10-09 |  |  |  |  | Yes |  |  | 163000 | 508877.3 |  | 163000 | 0 |  | 312.2% | 101314.8 | [8 empty] | Complete | [11 empty] | MX |  | 2021-146 | 2022 | [5 empty] | Y | OTTER 11017611 | 1092
31433961 |  |  |  | BUCOCAMP 1700 SONOMA CT PARADISE |  |  | CLSD |  | 0 | 263 | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95B | BUCOCAMP | [60 empty] | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0.049811 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0.0092803 | 0.04053 |  |  |  |  | N/A | [7 empty] | 2019-04-26 | [29 empty] | 39.7805 | -121.5804 |  |  |  |  | 2019
31434881 |  |  |  | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE |  |  | PEND |  | 17735 | 0 | 17735 | 3.3589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [9 empty] | 2019-06-11 | [22 empty] | Full |  |  | Full |  |  | Project is pre-DOT, and is complete | Full | [20 empty] | 17735 | 3.3589 | 0 | 0 | 0 | 0 | 3.3589 | 0 | 3.3589 | 0 | 3.3589 | 0 | 0 | 3.3589 |  |  |  |  | N/A | [37 empty] | 0 | 0 |  |  |  |  | 2019 | [11 empty] | 2021-03-04 11:54
31475979 |  |  |  | NC-SO-SONOMA 10/23/19 KINCADE FIRE UG CA |  |  | POST |  | 0 | 5276 | 5276 | 0.99924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 95B | [61 empty] | 5276 | 0.99924 | 0 | 0 | 0 | 0 | 0.99924 | 0 | 0.99924 | 0 | 0.99924 | 0 | 0 | 0.99924 |  |  |  |  | N/A | [7 empty] | 2020-05-04 | [29 empty] | 0 | 0 |  |  |  |  | 2019
35008479 |  |  |  | R2 2019 AUBERRY 1101 RECONDUCTOR |  |  | CLSD | 1800 | 0 | 1636.8 | 1636.8 | 0.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | SH | 2019-03-12 |  |  | 2019-03-04 |  | 2019-03-04 |  |  | Yes | 2019-03-04 | 3/4: Pending EDRS Approval |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | ERTC released | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 1636.8 | 0.31 | 0 | 0 | 0 | 0 | 0.31 | 0 | 0 | 0 | 0.3142 | 0.3142 | 0.31 | 0 |  |  | 2019-03-12 |  | N/A | 2019-06-03 08:00 | 2019-06-07 17:00 | Yes | 2019-06-07 17:00 | 2019-04-24 |  |  | 2019-06-10 | [17 empty] | 5 | [9 empty] | Tollhouse | Fresno | 37.006 | -119.4065 | P.11678 |  |  |  | 2019 | Q2 | [5 empty] | AUBERRY 1101R2578 | 1685
35009046 |  |  |  | CCM POLE_IDLE+_REMV-2E/O 8S/O 4890 CHILE |  |  | CONS |  | 0 | 891 | 891 | 0.16875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 2AF | IF | [60 empty] | 891 | 0.16875 | 0 | 0 | 0 | 0 | 0.16875 | 0 | 0.16875 | 0 | 0.16875 | 0 | 0 | 0.16875 |  |  |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5783 | -122.3939
35010118 |  |  |  | STS-COND_IDLE_REMV - 695 ORCHARD AVE SON |  |  | CLSD |  | 0 | 150 | 150 | 0.028409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 150 | 0.028409 | 0 | 0 | 0 | 0 | 0.028409 | 0 | 0.028409 | 0 | 0.028409 | 0 | 0 | 0.028409 |  |  |  |  | N/A | [7 empty] | 2018-04-19 | [29 empty] | 37.9942 | -120.3876
35010356 |  |  |  | X*FT-OFAC_IDLE_REMV-OLD ADOBE RD 13 POLE |  |  | CLSD |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF | [60 empty] | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0 | 0.063826 |  |  |  |  | N/A | [7 empty] | 2018-07-02 | [29 empty] | 36.9511 | -121.8189
35010358 |  |  |  | X STS-COND_IDLE_REMV-OLD GIRL SCOUT |  |  | CLSD |  | 0 | 516 | 516 | 0.097727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF | [60 empty] | 516 | 0.097727 | 0 | 0 | 0 | 0 | 0.097727 | 0 | 0.097727 | 0 | 0.097727 | 0 | 0 | 0.097727 |  |  |  |  | N/A | [7 empty] | 2018-05-30 | [29 empty] | 37.1219 | -122.1673
35011247 |  |  |  | STS-COND_IDLE_REMV-3054 CALAVERITAS RD ( |  |  | CLSD |  | 0 | 1090 | 1090 | 0.20644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 1090 | 0.20644 | 0 | 0 | 0 | 0 | 0.20644 | 0 | 0.20644 | 0 | 0.20644 | 0 | 0 | 0.20644 |  |  |  |  | N/A | [7 empty] | 2019-10-23 | [27 empty] | San Andreas | Calaveras | 38.1713 | -120.6326
35011253 |  |  |  | STS-POLE_IDLE_REMV-OPP 5865 POOLE STATIO |  |  | CLSD |  | 0 | 800 | 800 | 0.15152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 800 | 0.15152 | 0 | 0 | 0 | 0 | 0.15152 | 0 | 0.15152 | 0 | 0.15152 | 0 | 0 | 0.15152 |  |  |  |  | N/A | [7 empty] | 2019-09-16 | [29 empty] | 38.1415 | -120.6643
35011254 |  |  |  | STS-TRAN_IDLE_REMV-OLD BULK OIL PLANT 1/ |  |  | CLSD |  | 0 | 350 | 350 | 0.066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 350 | 0.066288 | 0 | 0 | 0 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0.066288 | 0 | 0 | 0.066288 |  |  |  |  | N/A | [7 empty] | 2019-09-12 | [27 empty] | San Andreas | Calaveras | 38.1675 | -120.6727
35011264 |  |  |  | STS-POLE_IDLE_REMV-11700 WHISKEY SLIDE R |  |  | CLSD |  | 0 | 223 | 223 | 0.042235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022727 |  |  | ST | 2AF | IF | [60 empty] | 0 | 0 | 211 | 0.039962 | 0 | 0 | 0.039962 | 0.0022727 | 0.042235 | 0 | 0.042235 | 0 | -0.0022727 | 0.042235 |  |  |  |  | N/A | [7 empty] | 2019-09-19 | [27 empty] | Amador City | Amador | 38.2673 | -120.5861
35011276 |  |  |  | STS-COND_IDLE_REMV-#2E CO#9975 W/O SHIRL |  |  | CLSD |  | 0 | 300 | 300 | 0.056818 | 300 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 0 | 0 | 300 | 0.056818 | 0 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0.056818 | 0 | 0 | 0.056818 |  | Keep |  |  | N/A | [7 empty] | 2020-01-23 | [29 empty] | 38.3431 | -120.7165
35011295 |  |  |  | *FT-OFAC_IDLE_REMV-6301 ECHO LN |  |  | CLSD |  | 0 | 1583 | 1583 | 0.29981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 1583 | 0.29981 | 0 | 0 | 0 | 0 | 0.29981 | 0 | 0.29981 | 0 | 0.29981 | 0 | 0 | 0.29981 |  |  |  |  | N/A | [7 empty] | 2018-06-22 | [29 empty] | 38.7048 | -120.8618
35012324 |  |  |  | STS-TRAN_IDLE_REMV-2 POLES EAST OF C/O'S |  |  | CLSD |  | 0 | 263 | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 263 | 0.049811 | 0 | 0 | 0 | 0 | 0.049811 | 0 | 0.049811 | 0 | 0.049811 | 0 | 0 | 0.049811 |  |  |  |  | N/A | [7 empty] | 2018-05-31 | [29 empty] | 40.6316 | -122.2544
35012964 |  |  |  | 7/9-STS-COND_IDLE_REMV-CRN ELM DR |  |  | CLSD |  | 0 | 1234 | 1234 | 0.23371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 1234 | 0.23371 | 0 | 0 | 0 | 0 | 0.23371 | 0 | 0.23371 | 0 | 0.23371 | 0 | 0 | 0.23371 |  |  |  |  | N/A | [7 empty] | 2018-06-15 | [27 empty] | Clearlake | Lake | 39.0076 | -122.6699
35014742 |  |  |  | 0628 IDLE FACIREPL - 1S/O 16823 COLEMAN |  |  | FICL |  | 0 | 803 | 803 | 0.15208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF |  |  |  |  | 2018-11-20 | [55 empty] | 803 | 0.15208 | 0 | 0 | 0 | 0 | 0.15208 | 0 | 0.15208 | 0 | 0.15208 | 0 | 0 | 0.15208 |  |  |  |  | N/A | [7 empty] | 2018-08-03 | [27 empty] | Grass Valley | Nevada | 39.1269 | -121.1702
35014889 |  |  |  | STS-POLE_DECA_REPL - #1E ON LINE @ R/O 2 |  |  | CLSD |  | 0 | 552 | 552 | 0.10455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 552 | 0.10455 | 0 | 0 | 0 | 0 | 0.10455 | 0 | 0.10455 | 0 | 0.10455 | 0 | 0 | 0.10455 |  |  |  |  | N/A | [7 empty] | 2018-07-06 | [27 empty] | North San Juan | Nevada | 39.3722 | -121.1011
35015704 |  | 2022 |  | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  |  | PEND | 5300 | 0 | 5300 | 5300 | 1.0038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 |  |  | CC | 08W |  | 2021-11-22 |  |  | 2019-04-11 |  | 2019-04-11 |  |  | Yes | 2019-04-11 | [6 empty] | No | [9 empty] | 2021-11-22 | 2021-11-22 | [5 empty] | 2021-11-22 | 2021-11-22 |  |  |  | ** Caltrans Dist. 5 - 5/28/20- CT D5 Permit Loc 1-4 crossing requested/ CDFW and Coastal Zone permitting required - Caltrans permit received on 8/24 | [6 empty] | [REDACTED] instructs not to permit until 7/2020. Env constraint | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0038 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [12 empty] | 99000 | 1081994.8 | 1196.1 | 99000 | 0 |  | 1093% | 59185.3 |  |  |  | 1077911.8008 |  | 23.5556 | [7 empty] | Remove |  | Aptos | Santa Cruz | 36.9746 | -121.8838 | 35015704 |  |  | 2020-096 | 2022 |  | 2019-04-11 | 2022-01-02 |  |  | Y | ROB ROY 210512474 | 3283 |  | WDDB |  | 2021-03-09 17:04
35016357 |  |  |  | STS-COND_IDLE_REMV-LCO 2961 DENNY RD |  |  | CLSD |  | 0 | 647 | 647 | 0.12254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 647 | 0.12254 | 0 | 0 | 0 | 0 | 0.12254 | 0 | 0.12254 | 0 | 0.12254 | 0 | 0 | 0.12254 |  |  |  |  | N/A | [7 empty] | 2018-03-26 | [29 empty] | 40.8705 | -123.5211
35016714 |  |  |  | 12/31-ST-CON_IDL_RMV-2 S/O TX-WHEEL BARR |  |  | CLSD |  | 0 | 856 | 856 | 0.16212 | 856 | 0.16212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 0 | 0 | 856 | 0.16212 | 0 | 0 | 0.16212 | 0 | 0.16212 | 0 | 0.16212 | 0 | 0 | 0.16212 |  |  |  |  | N/A | [7 empty] | 2018-11-13 | [29 empty] | 39.4983 | -123.3362
35016855 |  |  |  | 10/31-ST-POLE_IDLE_REMV-43451 EUREKA HIL |  |  | CLSD |  | 0 | 214 | 214 | 0.04053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 214 | 0.04053 | 0 | 0 | 0 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0.04053 | 0 | 0 | 0.04053 |  |  |  |  | N/A | [7 empty] | 2018-06-12 | [29 empty] | 38.9098 | -123.6856
35018047 |  |  |  | +STS-POLE_IDLE_REMV - TABLE MTNSAN MIGUE |  |  | CLSD |  | 0 | 839 | 839 | 0.1589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF | [60 empty] | 839 | 0.1589 | 0 | 0 | 0 | 0 | 0.1589 | 0 | 0.1589 | 0 | 0.1589 | 0 | 0 | 0.1589 |  |  |  |  | N/A | [7 empty] | 2018-10-20 | [29 empty] | 35.9272 | -120.3825
35018537 |  |  |  | STS-COND_IDLE_REMV - 17059 VAN ARSDALE R |  |  | CLSD |  | 0 | 3891 | 3891 | 0.73693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-04-08 | [55 empty] | 0 | 0 | 3891 | 0.73693 | 0 | 0 | 0.73693 | 0 | 0.73693 | 0 | 0.73693 | 0 | 0 | 0.73693 |  |  |  |  | N/A | [7 empty] | 2019-01-07 | [29 empty] | 39.3751 | -123.1217
35018539 |  |  |  | 6/30-STS-POLE_IDLE_REMV-#1S/O 3000GUIDIV |  |  | CLSD |  | 0 | 252 | 252 | 0.047727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 252 | 0.047727 | 0 | 0 | 0 | 0 | 0.047727 | 0 | 0.047727 | 0 | 0.047727 | 0 | 0 | 0.047727 |  |  |  |  | N/A | [7 empty] | 2018-04-24 | [29 empty] | 39.139 | -123.1476
35018787 |  |  |  | HALSEY 1101 - S039NO112 HIGH SPLICE 08J |  |  | CLSD | 1621 | 0 | 2854 | 2854 | 0.54053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-26 |  |  | 2019-06-26 | 2019-03-13 | 2019-06-26 |  |  | Yes | 2019-06-26 | 4/17: 2nd submittal to ED by 4/254/19: 4th ADE submittal5/15: waiting on 1st corrections from [REDACTED] /22: waiting on 1st corrections from [REDACTED] /29: 2nd submittal (7th total) due to renumbering by 6/5 with EOD by 6/75/31: 2nd submittal sent6/5: EDRS soon6/12: EDRS will be ready tomorrow6/19: ADE on vacation - updated EOD to 6/286/26: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | ERTC is Complete | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 2854 | 0.54053 | 0 | 0 | 0 | 0 | 0.54053 | 0 | 0.54053 | 0 | 0.54053 | 0 | 0 | 0.54053 |  |  |  |  | N/A |  |  |  |  | 2019-07-16 |  |  | 2019-09-09 |  |  |  |  | 866575 |  |  | 873318 | 6743 |  |  | 782303.1 | [5 empty] | 16 | [9 empty] | Meadow Vista | Placer | 0 | 0 | 35018787 |  |  |  | 2019 | Q3 |  |  |  |  | Y | HALSEY 110176178 | 1629
35018788 |  |  |  | APPLE HILL 1104 - S049NO119 HIGH SPLICE |  |  | CLSD | 3769 | 0 | 6121 | 6121 | 1.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-05-28 |  |  | 2019-05-28 | 2019-03-17 | 2019-05-28 |  |  | Yes | 2019-05-28 | 5/28: Complete |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Contractor nootified to obtain their own no-fee permit 6/28/19 |  | 1980-01-01 | Y | [11 empty] | 6121 | 1.1593 | 0 | 0 | 0 | 0 | 1.1593 | 0 | 1.1593 | 0 | 1.1593 | 0 | -1.7225e-16 | 1.1593 |  |  |  |  | N/A |  |  |  |  | 2019-06-17 |  |  | 2019-09-22 |  |  |  |  | 1681167 |  |  | 1995745 | 314578 |  |  | 1502307 | [5 empty] | 38 | [9 empty] | Camino | El Dorado | 0 | 0 | 35018788 |  |  |  | 2019 | Q3 |  |  |  |  | Y | APPLE HILL 110412842 | 320
35019006 |  |  |  | ROB ROY 2104 CO11865 REPLACE OH LINE |  |  | CLSD | 9680 | 0 | 9525 | 9525 | 1.804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-06-20 |  |  | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | walkdown 7/24 - Potental for 1 pole to require an easement & 1 guy connect confirmation | Full |  |  | Yes |  |  | County states that work may be completed under Annual permit. |  | 1980-01-01 | Y | [11 empty] | 9525 | 1.804 | 0 | 0 | 0 | 0 | 1.804 | 0 | 1.804 | 0 | 1.804 | 0 | 0 | 1.804 |  |  |  |  | N/A |  |  |  |  | 2019-08-22 |  |  | 2019-12-11 |  |  |  |  | 1159532 |  |  | 1485645.6 | 326113.6 |  |  | 1016957.3 | [5 empty] | 35 | [9 empty] | Watsonville | Santa Cruz | 37.0261 | -121.7749 | 35019006 |  |  |  | 2019 | Q3 |  |  |  |  | Y | GREEN VALLEY 210111054 | 778
35022707 |  |  |  | XSTS-COND_IDLE_REMV-HWY 1 (AREA 3 SPANS |  |  | FICL |  | 0 | 395 | 395 | 0.074811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF | [60 empty] | 395 | 0.074811 | 0 | 0 | 0 | 0 | 0.074811 | 0 | 0.074811 | 0 | 0.074811 | 0 | 0 | 0.074811 |  |  |  |  | N/A | [7 empty] | 2018-07-23 | [29 empty] | 36.4215 | -121.9117
35022860 |  |  |  | STS-POLE_IDLE_REMV-END OF CALDERWOOD RD |  |  | CLSD |  | 0 | 368 | 368 | 0.069697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 368 | 0.069697 | 0 | 0 | 0 | 0 | 0.069697 | 0 | 0.069697 | 0 | 0.069697 | 0 | 0 | 0.069697 |  |  |  |  | N/A | [7 empty] | 2019-09-11 | [29 empty] | 38.6675 | -120.9541
35022861 |  |  |  | STS-POLE_IDLE_REMV-CHURCH MINE RD |  |  | CLSD |  | 0 | 2168 | 2168 | 0.41061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF |  |  |  |  | 2019-01-03 | [55 empty] | 2168 | 0.41061 | 0 | 0 | 0 | 0 | 0.41061 | 0 | 0.41061 | 0 | 0.41061 | 0 | 0 | 0.41061 |  |  |  |  | N/A | [7 empty] | 2019-09-17 | [29 empty] | 38.6537 | -120.8271
35023234 |  |  |  | STS-OFAC_IDLE_REMV-34039 HIGHWAY 44 |  |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2018-11-10 | [55 empty] | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0.07197 | 0 | 0 | 0.07197 |  |  |  |  | N/A | [7 empty] | 2019-04-26 | [27 empty] | Shingletown | Shasta | 40.5129 | -121.772
35023526 |  |  |  | 1/6/19-STS-POLE_IDLE_REMV-7050 BOGGS KEL |  |  | CLSD |  | 0 | 410 | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0.077652 | 0 | 0.077652 | 0 | 0.077652 | 0 | 0 | 0.077652 |  |  |  |  | N/A | [7 empty] | 2018-10-23 | [29 empty] | 38.9498 | -122.879
35023687 |  |  |  | R2RPL OH WIRE ON B LOMND 0401 17-0095503 |  |  | DOCC | 7590 | 0 | 7044 | 7044 | 1.3341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-10-15 |  |  | 2019-10-15 |  | 2019-10-15 |  |  | Yes | 2019-06-13 | 4/8: On track for 1st submittal 4/304/17: On track for 4/30 submittal4/29: Submitted 1st ADE submittal5/8: 1st correction received today5/14: 2nd submittal sent5/21: 3rd submittal sent5/29: ADE on vacation - job on 3rd review6/4: 3rd Review submitted6/5: approved by [REDACTED] , EDRS shortly. Uploading issues with SAP, but IT has been contacted6/12: Approved and in PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Additional issues found on job walk that delayed ERTC - Partial release scheduled for 8/30/19 | Full |  |  | Yes |  |  | Annual will cover work - no road closers longer than 15 minutes |  | 1980-01-01 | Y | [11 empty] | 7044 | 1.3341 | 0 | 0 | 0 | 0 | 1.3341 | 0 | 1.3341 | 0 | 1.3341 | 0 | -1.7225e-16 | 1.3341 |  |  |  |  | N/A |  |  |  |  | 2019-08-30 |  |  | 2019-12-19 |  |  |  |  | 4004352 |  |  | 4004352 | 0 | 89286.3 |  | 3907306.6 | 7759.1 | 3915065.7 |  |  |  | 58 | [9 empty] | Ben Lomond | Santa Cruz | 37.0955 | -122.0857 | P.11844 |  |  |  | 2019 | Q4 |  |  |  |  | Y | BEN LOMOND 04015206 | 401
35024926 |  |  |  | MARTELL 1101 RECONDCUTOR 3,700FT |  |  | FICL | 686.4 | 0 | 686.4 | 686.4 | 0.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2019-02-21 |  |  | 2019-02-21 |  | 2019-02-21 |  |  | Yes | 2019-02-21 | 2/20: Pending EDRS approval - SAP is now showing ESTS |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 686.4 | 0.13 | 0 | 0 | 0 | 0 | 0.13 | 0 | 0.13 | 0 | 0.13 | 0 | 0 | 0.13 |  |  |  |  | COMP |  |  |  |  | 2019-03-07 |  |  | 2019-03-30 |  |  |  |  | 703057 |  |  | 824970 | 121913 |  |  | 537779.5 | [5 empty] | 20 | [9 empty] | Sutter Creek | Amador | 38.3951 | -120.8017 | 35024926 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MARTELL 1101CB | 2357
35025977 |  |  |  | REMV 4 IDLE POLES 12099 HWY 12 KEN*OCLH |  |  | CLSD |  | 0 | 712 | 712 | 0.13485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 712 | 0.13485 | 0 | 0 | 0 | 0 | 0.13485 | 0 | 0.13485 | 0 | 0.13485 | 0 | 0 | 0.13485 |  |  |  |  | N/A | [7 empty] | 2018-07-19 | [27 empty] | Kenwood | Sonoma | 38.3948 | -122.5147
35026643 |  | 2021 |  | DIAMOND SPRINGS 1105 - LR 2102 |  | Scoped | DCNL | 7400 | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2022-06-10 17:00 | 2021-03-23 | N | [13 empty] | Yes | [11 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-06-10 17:00 |  | INPR | 2022-06-29 11:00 | 2022-07-28 11:00 |  | 2022-10-21 11:00 | [8 empty] | 100000 | 1882335.5 |  | 100000 | 0 |  | 1882% | 58947.7 |  |  |  | 1161935.4938 |  | 22 |  | Still need to be scoped / table topped | [7 empty] | El Dorado | El Dorado | 0 | 0 | 35026643 | MX | OH |  | 999 | [5 empty] | Y | DIAMOND SPRINGS 11052102 | 666 |  | WDDB |  | 2021-03-11 17:02
35026735 |  |  |  | X STS-COND_BROK_REPA - NEAR 19145 BIG |  |  | CLSD |  | 0 | 420 | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF | [60 empty] | 420 | 0.079545 | 0 | 0 | 0 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0.079545 | 0 | 0 | 0.079545 |  |  |  |  | N/A | [7 empty] | 2018-07-31 | [29 empty] | 37.1717 | -122.1761
35026994 |  |  |  | STS-POLE_IDLE_REMV - 7140 KELSEY CREEK D |  |  | CLSD |  | 0 | 390 | 390 | 0.073864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF | [60 empty] | 390 | 0.073864 | 0 | 0 | 0 | 0 | 0.073864 | 0 | 0.073864 | 0 | 0.073864 | 0 | 0 | 0.073864 |  |  |  |  | N/A | [7 empty] | 2018-10-22 | [29 empty] | 38.9517 | -122.8384
35028500 |  |  |  | *FT-REPL POLE:17SW/O C/O 7943 TO KATE H. |  |  | FICL |  | 0 | 3671 | 3671 | 0.69527 | 0 | 0 | 3671 | 0.69527 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 3671 | 0.69527 | 0.69527 | 0 | 0.69527 | 0 | 0.69527 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-05-26 | [27 empty] | Camptonville | Yuba | 39.4788 | -120.8891
35030568 |  |  |  | CWSP HALF MOON BAY 1101 FUCO 4141 |  |  | PEND | 4690 | 838 | 3852 | 4690 | 0.88826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88826 |  |  | PN | 08W |  | 2022-06-01 |  |  | 2020-01-15 |  | 2020-01-15 | 2019-08-06 | 2019-08-06 | Yes | 2019-12-31 | 12/31: Corrections finalized - Put in PEND12/17: Estimator working ADE corrections, submit by EOD - preparing to route12/09: Fixbug voltage drop issues.12/06: EN submitted for ADE - updated sketch and the VDVF sheet12/04: ADE rtn 4th (minor) corrections to contractor - fix and route12/03: Check in with ADE - EOD EOW11/25 EN Submitted for 4th ADE rvw11/19: ADE rtn 3rd corrections to contractor11/12: Push 2wk - ADE priority assignments (2 to finalize)11/05 <-- 10/29: ADE completing El Dorado 2101 PH2.2 (priority) - out on vacation; IT ticket submitted for USER STATUS, target completion no later than Thurs 10/3110/22: EN submit ticket to update USER STATUS10/21: EN submitted for (3rd Rvw?) ADE Rvw - Project USER STATUS DCNL10/16: ADE returned revisions 2 corrections to contractor10/15: push - finalize corrections, Est out sick10/08: ADE returned corrections to contractor - Minor request for info/Est getting info. (Page 2 missing property lines)10/03 EN submitted for 3rd ADE rvw10/01: Minor corrections, received Pull Calc spreadsheet - target to turn around no later than the end of the week9/30: ADE returned corrections to contractor9/27: EN submitted for 3rd ADE rvw (sketches for UG portion)9/24: Submitting for 3rd rvw 9/259/10 - 9/17: Working with ADE- [REDACTED] for resolution regarding transformer details - Finalizing, target set for submittal 9/24.8/27: Not the needed details flagged by ADE in order to proceed - checked resources ID'd and ACAD, etc.. - will forward specifics - [REDACTED] to assist8/23: Flagged on priority list email (ADDED)8/20: Vendor to obtain UG box pad mount detail - for CAD information...check Green Book; (TIL); EN to follow up with GB - anticipate quick turn around if issue resolved8/13: EN/PGE ADE resolving issue with 'box' information - [REDACTED] to assist in follow up.8/01: EN submitted for 2nd ADE rvw - [PRELIM DWG ready] |  |  |  | Completed | COMPLETED | No | No | 29 | 0 | [6 empty] | 2021-06-01 | 2021-06-01 | [5 empty] | 2022-06-01 | 2022-06-01 |  |  |  | Update: PM sent email saying this is 2022 - San Mateo County Coastal Development Permit - [REDACTED]has not received updates since early September, but has been following up. Vegetation scope being revised as of week of November 9 which drives permit determination by the County. | [6 empty] | Late 2020 early 2021 project - Delay permit application accordingly |  | 2022-02-01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88826 | 0 | 0 | 0.83712 | 0.83712 | 0 | 0 |  |  | 2021-12-15 17:00 |  | INPR | 2022-04-07 08:00 | 2022-07-04 17:00 |  | 2022-08-03 17:00 | [8 empty] | 100000 | 868236.8 |  | 100000 | 0 |  | 868.2% | 75285.3 |  |  |  | 977460.6192 |  | 25 |  | [REDACTED] needs confidence level of prelim drawing given slippage | [5 empty] | Remove |  | Half Moon Bay | San Mateo | 0 | 0 | 35030568 |  |  | 2020-085 | 2022 |  | 2019-12-31 | 2021-09-17 |  |  | Y | HALF MOON BAY 1101CB | 1132
35030654 |  |  |  | TW ON WOODSIDE1101 N/O 7573 |  |  | CLSD | 5271 | 0 | 5271 | 5271 | 0.9983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | SH | 2019-03-06 |  |  | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/4: ADE approved pending EDRS approval |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 5271 | 0.9983 | 0 | 0 | 0 | 0 | 0.9983 | 0 | 0.9983 | 0 | 0.9983 | 0 | 0 | 0.9983 |  |  |  |  | N/A |  |  |  |  | 2019-05-09 |  |  | 2019-12-06 | [17 empty] | 26 | [9 empty] | Redwood City | San Mateo | 37.3792 | -122.2831 | 35030654 |  |  |  | 2019 | Q3 |  |  |  |  | Y | WOODSIDE 11018974 | 59
35030877 |  |  |  | 12/31 REMV IDLE 5 PLS 25050 HWY 1 C*OCLH |  |  | CLSD |  | 0 | 796 | 796 | 0.15076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 796 | 0.15076 | 0 | 0 | 0 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0.15076 | 0 | 0 | 0.15076 |  |  |  |  | N/A | [7 empty] | 2018-08-06 | [27 empty] | Jenner | Sonoma | 38.6005 | -123.3488
35031139 |  |  |  | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 |  |  | CLSD | 7900 | 0 | 8016 | 8016 | 1.5182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-07-11 |  |  | 2019-07-11 | 2020-10-31 | 2019-07-11 |  |  | Yes | 2019-07-11 | 4/8: Working Job Packages4/10: Updated Scope for QUES to review4/17: waiting for Updated Scope4/24: waiting for updated change order5/15: QUES to follow up. Waiting on UG inspection ( [REDACTED] to follow up)5/22: [REDACTED] to provide map and explaination for why not to UG. QUES to provide 1st ADE submittal timeframe 6/115/29: [REDACTED] to follow up with [REDACTED] /5: 1st submittal by 6/186/12: on track for 6/18 submittal6/19:1st ADE submittal sent - assigned to [REDACTED] /25: corrections back from [REDACTED] /1: got clarification7/3: 7/12 2nd submittal7/9: 2nd submittal send7/11: APPROVED |  |  |  | Completed | COMPLETED | No | 4/8: Working Job Packages4/10: Updated Scope for QUES to review4/17: waiting for Updated Scope4/24: waiting for updated change order5/15: QUES to follow up. Waiting on UG inspection ( [REDACTED] to follow up)5/22: [REDACTED] to provide map and explaination for why not to UG. QUES to provide 1st ADE submittal timeframe 6/115/29: [REDACTED] to follow up with [REDACTED] /5: 1st submittal by 6/186/12: on track for 6/18 submittal6/19:1st ADE submittal sent - assigned to [REDACTED] /25: corrections back from [REDACTED] /1: got clarification7/3: 7/12 2nd submittal7/9: 2nd submittal send7/11: APPROVED | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Placer County Annual |  | 2019-12-19 | [12 empty] | 8016 | 1.5182 | 0 | 0 | 0 | 0 | 1.5182 | 0 | 1.5182 | 0 | 1.5182 | 0 | -3.4451e-16 | 1.5182 |  |  |  |  | N/A |  |  |  |  | 2019-07-31 |  |  | 2019-12-30 |  |  |  |  | 2511202 |  |  | 2668456 | 157254 |  |  | 2416634.1 | [5 empty] | 29 | [9 empty] | Colfax | Placer | 39.1479 | -120.9087 | 35031139 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SHADY GLEN 1102CB | 349
35031662 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 |  |  | FICL | 2978 | 511 | 2467 | 2978 | 0.56402 | 2978 | 0.56402 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1676e-16 |  |  | DA | 08W | SH | 2020-02-18 17:00 |  |  | 2019-10-07 |  | 2019-10-07 |  |  | Yes | 2019-10-07 | waiting on GC review |  |  |  |  | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | [REDACTED] to check on CIF - EOD 7/30/19; [REDACTED] (notification only); Midpeninsula Open Space | Full |  |  | Yes |  |  | Santa Clara County |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 2978 | 0.56402 | 0 | 0 | 0.56402 | 5.1676e-16 | 0.56402 | 0 | 0.56402 | 0 | -5.1676e-16 | 0.56402 |  | Keep | 2020-02-18 17:00 | Yes | N/A | 2020-02-12 | 2020-03-25 | Yes | 2020-03-25 17:00 | 2020-01-13 | 2020-02-10 | 2020-03-27 | 2020-03-25 |  | Yes | Shovel Ready |  | 1109989 | 1032916.3 | 19394.1 | 1363100.7 | 253111.7 | 77302.5 | 93.05% | 1026578.3 | 6108.2 | 1032686.5 |  | 1831362.681 |  | 13 |  | 6/21 - next week will have additional PM numbers to add tohe list for new segments | [7 empty] | Los Gatos | Santa Clara | 37.1933 | -122.0204 | E.0000130.01 |  |  | 2020-079 | 2020 | Q1 | 2019-10-04 | 2020-02-02 | 2020-03-23 |  | Y | LOS GATOS 1106LB44 | 841
35031663 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  |  | ESTS | 1587 | 3643 | 0 | 3643 | 0.68996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68996 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [5 empty] | No | [16 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Santa Clara Parks & Rec (local permitting desk) | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68996 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 60000 | 3500108.3 |  | 10000 | -50000 |  | 5834% | 45155.7 |  |  |  | 5072899.2105 |  | 18 |  | 6/21 - next week will have additional PM numbers to add tohe list for new segments | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.0000131.01 | ML |  | 2021-140 | 2021 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35032266 |  |  |  | APPLE HILL 1104 RECONDUCTOR |  |  | CLSD | 1060 | 0 | 877 | 877 | 0.1661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-13 |  |  | 2019-06-13 |  | 2019-06-13 |  |  | Yes | 2019-07-08 | 5/22: on track for 6/3 submittal 6/3: 1st ADE submitted 6/5: 1st corrections 6/12: EEI to follow up with 2nd submittal 6/13: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Received on 6/17 No contraints identified | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 877 | 0.1661 | 0 | 0 | 0 | 0 | 0.1661 | 0 | 0.1661 | 0 | 0.1661 | 0 | 0 | 0.1661 |  |  |  |  | N/A |  |  |  |  | 2019-07-15 |  |  | 2019-08-01 |  |  |  |  | 351206.2 |  |  | 368711 | 17504.8 |  |  | 284268.5 | [5 empty] | 7 | [9 empty] | Pollock Pines | El Dorado | 38.7632 | -120.5756 | 35032266 |  |  |  | 2019 | Q3 |  |  |  |  | Y | APPLE HILL 110413512 | 99
35037345 |  |  |  | STS-OFAC_IDLE_REMV-6645 E. HWY 246 |  |  | CLSD |  | 0 | 250 | 250 | 0.047348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF |  |  |  |  | 2019-04-28 | [55 empty] | 250 | 0.047348 | 0 | 0 | 0 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0.047348 | 0 | 0 | 0.047348 |  |  |  |  | N/A | [7 empty] | 2019-08-12 | [27 empty] | Los Osos | San Luis Obispo | 34.6385 | -120.2903
35037374 |  |  |  | COND_IDLE_REMV-15587 38TH AVE CLK * KS |  |  | FICL |  | 0 | 100 | 100 | 0.018939 | 100 | 0.018939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-09-12 | [55 empty] | 0 | 0 | 100 | 0.018939 | 0 | 0 | 0.018939 | 0 | 0.018939 | 0 | 0.018939 | 0 | 0 | 0.018939 |  | Keep |  |  | N/A | [7 empty] | 2020-02-28 | [29 empty] | 38.9493 | -122.6192
35037395 |  |  |  | POD T2 REMV IDLE -21335 PINE ST |  |  | CLSD |  | 0 | 35 | 35 | 0.0066288 | 35 | 0.0066288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-08-09 | [55 empty] | 0 | 0 | 35 | 0.0066288 | 0 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0.0066288 | 0 | 0 | 0.0066288 |  | Keep |  |  | N/A | [7 empty] | 2020-01-07 | [29 empty] | 38.7488 | -122.6191
35037594 |  |  |  | COND_IDLE_REMV-JUNCTION @ HWY 36 & R |  |  | FICL |  | 0 | 497 | 497 | 0.094129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-07-06 | [55 empty] | 497 | 0.094129 | 0 | 0 | 0 | 0 | 0.094129 | 0 | 0.094129 | 0 | 0.094129 | 0 | 0 | 0.094129 |  |  |  |  | N/A | [7 empty] | 2019-11-14 | [29 empty] | 40.3012 | 123.5944
35037596 |  |  |  | TRAN_IDLE_REMV-OLD LIGHTHOUSE RD E.O |  |  | CLSD |  | 0 | 1160 | 1160 | 0.2197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2197 |  |  | HB | 2AF | IF |  |  |  |  | 2019-07-09 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2197 | 0 | 0 | 0.2197 | 0.2197 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-02-10 | [29 empty] | 40.4392 | -124.4076
35037647 |  |  |  | STS-POLE_IDLE_REMV-44141 LITTLE LAKE RD |  |  | FICL |  | 0 | 527 | 527 | 0.099811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-06-12 | [55 empty] | 527 | 0.099811 | 0 | 0 | 0 | 0 | 0.099811 | 0 | 0.099811 | 0 | 0.099811 | 0 | 0 | 0.099811 |  |  |  |  | N/A | [7 empty] | 2019-08-09 | [29 empty] | 39.3122 | -123.783
35037701 |  |  |  | TRAN_IDLE_REMV-M.P. 4.39 AVE OF THE |  |  | FICL |  | 0 | 793 | 793 | 0.15019 | 793 | 0.15019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-09-08 | [55 empty] | 0 | 0 | 793 | 0.15019 | 0 | 0 | 0.15019 | 0 | 0.05928 | 0 | 0.05928 | 0 | 0.090909 | 0.05928 |  |  |  |  | N/A | [7 empty] | 2020-01-29 | [29 empty] | 40.1335 | -123.4831
35037728 |  |  |  | REMV IF 3 LOCS-STEWARTS PT SKAGGS *OCLH |  |  | FICL |  | 0 | 520 | 520 | 0.098485 | 520 | 0.098485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF |  |  |  |  | 2019-10-29 | [55 empty] | 0 | 0 | 520 | 0.098485 | 0 | 0 | 0.098485 | 0 | 0.097538 | 0 | 0.097538 | 0 | 0.00094697 | 0.097538 |  |  |  |  | N/A | [7 empty] | 2020-03-16 | [27 empty] | Geyserville | Sonoma | 38.669 | -123.0984
35037854 |  |  |  | X STS-TRAN_IDLE_REMV-16 POLES FROM E.O. |  |  | CLSD |  | 0 | 457 | 457 | 0.086553 | 0 | 0 | 457 | 0.086553 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF |  |  |  |  | 2018-12-05 | [55 empty] | 0 | 0 | 0 | 0 | 457 | 0.086553 | 0.086553 | 0 | 0.086553 | 0 | 0.086553 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2019-03-15 | [29 empty] | 36.1328 | -121.2304
35038058 |  |  |  | STS-COND_IDLE_REMV-LA PORTE RD 1 PL E/O |  |  | CLSD |  | 0 | 115 | 115 | 0.02178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0017045 |  |  | NV | 2AF | IF |  |  |  |  | 2019-05-11 | [55 empty] | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0.020076 | 0.0017045 | 0.02178 | 0 | 0.02178 | 0 | -0.0017045 | 0.02178 |  |  |  |  | N/A | [7 empty] | 2019-12-30 | [27 empty] | Clipper Mills | Butte | 39.5311 | -121.1651
35038059 |  |  |  | STS-COND_IDLE_REMV-11648 LA PORTE ROAD |  |  | CLSD |  | 0 | 115 | 115 | 0.02178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-06-30 | [55 empty] | 115 | 0.02178 | 0 | 0 | 0 | 0 | 0.02178 | 0 | 0.02178 | 0 | 0.02178 | 0 | 0 | 0.02178 |  |  |  |  | N/A | [7 empty] | 2019-06-19 | [29 empty] | 39.5224 | -121.1819
35038067 |  |  |  | STS-COND_IDLE_REMV-202 OBERT DRIVE ( MAP |  |  | CLSD |  | 0 | 184 | 184 | 0.034848 | 184 | 0.034848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-05-11 | [55 empty] | 0 | 0 | 184 | 0.034848 | 0 | 0 | 0.034848 | 0 | 0.034848 | 0 | 0.034848 | 0 | 0 | 0.034848 |  | Keep |  |  | N/A | [7 empty] | 2020-01-01 | [29 empty] | 39.4408 | -121.371
35038136 |  |  |  | STS-COND_IDLE_REMV-7660 PONDEROSA WAY |  |  | FICL |  | 0 | 188 | 188 | 0.035606 | 188 | 0.035606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-06-19 | [55 empty] | 0 | 0 | 188 | 0.035606 | 0 | 0 | 0.035606 | 0 | 0.035606 | 0 | 0.035606 | 0 | 0 | 0.035606 |  | Keep |  |  | N/A | [7 empty] | 2020-03-03 | [29 empty] | 40.5115 | -121.9378
35038141 |  |  |  | STS-COND_IDLE_REMV-BRUSH CREEL LANE |  |  | CLSD |  | 0 | 323 | 323 | 0.061174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-06-19 | [55 empty] | 323 | 0.061174 | 0 | 0 | 0 | 0 | 0.061174 | 0 | 0.061174 | 0 | 0.061174 | 0 | 0 | 0.061174 |  |  |  |  | N/A | [7 empty] | 2019-07-27 | [27 empty] | Shingletown | Shasta | 40.4947 | 121.8665
35038190 |  |  |  | X-STS-TRAN_IDLE_REMV-A/O 30445 CHUALAR |  |  | FICL |  | 0 | 515 | 515 | 0.097538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 2AF | IF |  |  |  |  | 2019-02-21 | [55 empty] | 515 | 0.097538 | 0 | 0 | 0 | 0 | 0.097538 | 0 | 0.097538 | 0 | 0.097538 | 0 | 0 | 0.097538 |  |  |  |  | N/A | [7 empty] | 2019-04-12 | [29 empty] | 36.603 | -121.429
35038312 |  |  |  | +STS-COND_IDLE_REMV-S OF 7100 FOXEN CYN |  |  | CLSD |  | 0 | 320 | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF |  |  |  |  | 2019-04-24 | [55 empty] | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0 | 0.060606 |  |  |  |  | N/A | [7 empty] | 2019-08-22 | [29 empty] | 34.8318 | -120.2326
35038382 |  | 2021 | E/F Capital - OH | STS-TRAN_IDLE_REMV-BEHIND 4052 CLARK DR |  |  | MAPP |  | 0 | 1220 | 1220 | 0.23106 | 0 | 0 | 1220 | 0.23106 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF |  |  |  |  | 2018-12-06 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23106 | 0 | 0 | 0.23106 | 0.23106 | 0 | 0 |  | keep |  |  | N/A | [5 empty] | 2020-01-21 | 2020-01-21 | 2020-01-21 | [29 empty] | 37.9214 | -121.2204
35038502 |  |  |  | STS-TRAN_IDLE_REMV-CHOLAME VALLEY RD |  |  | CLSD |  | 0 | 866 | 866 | 0.16402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF |  |  |  |  | 2019-05-26 | [55 empty] | 866 | 0.16402 | 0 | 0 | 0 | 0 | 0.16402 | 0 | 0.16402 | 0 | 0.16402 | 0 | 0 | 0.16402 |  |  |  |  | N/A | [7 empty] | 2019-06-05 | [29 empty] | 35.8493 | -120.3944
35038571 |  |  |  | POLE_IDLE_REMV-NEXT TO BUSCH CR |  |  | CLSD |  | 0 | 273 | 273 | 0.051705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2019-07-20 | [55 empty] | 273 | 0.051705 | 0 | 0 | 0 | 0 | 0.051705 | 0 | 0.051705 | 0 | 0.051705 | 0 | 0 | 0.051705 |  |  |  |  | N/A | [7 empty] | 2019-09-08 | [29 empty] | 39.2075 | -123.0845
35038608 |  |  |  | STS-COND_IDLE_REMV-8100 PLEASANTS VALLEY |  |  | CLSD |  | 0 | 1140 | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SA | 2AF | IF |  |  |  |  | 2019-04-24 | [55 empty] | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0.21591 | 0 | 0.21591 | 0 | 0.21591 | 0 | 0 | 0.21591 |  |  |  |  | N/A | [7 empty] | 2019-09-10 | [29 empty] | 38.4603 | -122.0547
35038669 |  |  |  | ANCH_SOIL_ADJU-2701 BLACKHAWK RI*DIV |  |  | FICL |  | 0 | 398 | 398 | 0.075379 | 398 | 0.075379 | 0 | 0 | 0 | 0 | 0 | 0 | -0.014583 |  |  | HB | 2AF | IF |  |  |  |  | 2020-01-03 | [55 empty] | 0 | 0 | 475 | 0.089962 | 0 | 0 | 0.089962 | -0.014583 | 0.092803 | 0 | 0.092803 | 0 | -0.0028409 | 0.092803 |  |  |  |  | N/A | [7 empty] | 2020-07-21 | [29 empty] | 39.3451 | -123.3446
35038685 |  |  |  | REMV IDLE TAP-X ST FROM 2997 RD. 30 |  |  | CLSD |  | 0 | 624 | 624 | 0.11818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-05-11 | [55 empty] | 624 | 0.11818 | 0 | 0 | 0 | 0 | 0.11818 | 0 | 0.11818 | 0 | 0.11818 | 0 | 0 | 0.11818 |  |  |  |  | N/A | [7 empty] | 2019-10-16 | [27 empty] | Elk Creek | Glenn | 39.587 | -122.5887
35039002 |  |  |  | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO |  |  | CLSD | 6336 | 0 | 6019.2 | 6019.2 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-01 |  |  | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2018-08-29 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 6019.2 | 1.14 | 0 | 0 | 0 | 0 | 1.14 | 0 | 1.14 | 0 | 1.14 | 0 | 0 | 1.14 |  |  |  |  | N/A |  |  |  |  | 2018-09-12 |  |  | 2019-03-29 | [17 empty] | 22 | [9 empty] | Calistoga | Napa | 0 | 0 | 35039002 |  |  |  | 2019 | Q2 | [5 empty] | CALISTOGA 1101736 | 24 |  |  |  | 2021-03-01 20:30
35040225 |  |  |  | HIGGINS 1110 RECONDUCTOR |  |  | CLSD | 7400 | 0 | 8584 | 8584 | 1.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-07-01 |  |  | 2019-07-01 |  | 2019-07-01 |  |  | Yes | 2019-07-01 | 5/22: on track for 6/3 submittal6/5: 1st submittal by 6/76/7: 1st ADE submittal - assigned to [REDACTED] /13: 1st correction received6/19: EEI to follow up on 2nd submittal6/20: 2nd submittal sent6/21: 2nd corrections sent6/26: ADE on vacation6/28: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | ERTC COmpleted | Full |  |  | Yes |  |  | Private Property - No Permit Needed |  | 1980-01-01 | Y | [11 empty] | 8584 | 1.6258 | 0 | 0 | 0 | 0 | 1.6258 | 0 | 1.6258 | 0 | 1.6258 | 0 | 0 | 1.6258 |  |  |  |  | N/A |  |  |  |  | 2019-08-01 |  |  | 2019-09-30 |  |  |  |  | 2449837 |  |  | 2449837 | 0 |  |  | 2412478.7 | [5 empty] | 29 | [9 empty] | Grass Valley | Nevada | 0 | 0 | 35040225 |  |  |  | 2019 | Q3 |  |  |  |  | Y | HIGGINS 11102408 | 1188
35040742 |  |  |  | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO |  |  | CLSD | 2710 | 2798.4 | 0 | 2798.4 | 0.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-01-01 |  |  | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2018-09-04 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 2798.4 | 0.53 | 0 | 0 | 0 | 0 | 0.53 | 0 | 0.53 | 0 | 0.53 | 0 | 0 | 0.53 |  |  |  |  | N/A |  |  |  |  | 2018-10-10 |  |  | 2019-04-05 | [17 empty] | 12.0444 | [9 empty] | Occidental | Sonoma | 38.4146 | -122.9514 | 35040742 |  |  |  | 2019 | Q2 | [5 empty] | MONTE RIO 1112120 | 54 |  |  |  | 2021-03-04 11:49
35042365 |  |  |  | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57
35042366 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57
35042368 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57
35042369 |  |  |  | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Los Gatos | Santa Clara | 37.0639 | -121.797 | [11 empty] | CAMP EVERS 210660124 | 57
35042670 |  |  |  | STS-POLE_DECA_REPL - 4300 SOFAR RD PLACE |  |  | CLSD |  | 0 | 467 | 467 | 0.088447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 467 | 0.088447 | 0 | 0 | 0 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0.088447 | 0 | 0 | 0.088447 |  |  |  |  | N/A | [7 empty] | 2018-09-10 | [29 empty] | 38.7026 | -120.7902
35042719 |  |  |  | CWSP-AMGWIN STEEL POLE & TW DEMO PH |  |  | CLSD | 2112 | 0 | 1275 | 1275 | 0.24148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-15 |  |  | 2019-01-15 |  | 2019-01-15 |  |  | Yes | 2018-10-17 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | total mess | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 1275 | 0.24148 | 0 | 0 | 0 | 0 | 0.24148 | 0 | 0.24148 | 0 | 0.24148 | 0 | 0 | 0.24148 |  |  |  |  | N/A |  |  |  |  | 2019-01-15 |  |  | 2019-10-09 | [17 empty] | 9.3867 | [9 empty] | Angwin | Napa | 0 | 0 | 35042719 |  |  |  | 2019 | Q2 | [5 empty] | SILVERADO 210478268 | 64
35043291 |  | 2020 | 220 Mile Plan | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  |  | CLSD | 15523 | 0 | 15172 | 15172 | 2.8735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2019-09-20 |  |  | 2019-09-20 |  | 2019-09-20 |  |  | Yes | 2019-09-20 | 5/29: 1st ADE submittal on 6/14 6/11: on track for 6/14 submittal 7/8: partial 2nd corrections received 7/16: Directed to work Version 9 - seeking confirmation, or still waiting for remaining corrections,ETA requested 7/16 7/22: Approved for Version 9; Change Order to be Submitted 7/23, w/ New 1st ADE Submittal date (apprx 8/13) 7/24: Via Email - Change Order defined; confirmed 1st ADE submittal date of 8/9 7/30 - 8/6: on track for 8/9 8/9: BCF submitted for 1st ADE Rvw 8/13: In Review - Adding/Add field notes 8/15: In Review - going to keep Loc 1 as is, redlining to have you show this is an existing 55'-H1 pole. The calc will need to be corrected 8/20: 1st ADE Rvw completion scheduled for 8/23 8/26: 1st ADE corrections returned to contractor 9/03: Correction submittal targeted for 9/05 (Thurs) --> [RCC Issue] 9/05: BCF submitted for 2nd ADE Rvw [PRELIM DWG ready] 9/10: In Review 9/14: 2nd ADE corrections rtn to contractor 9/17: Finishing ADE coordination - firmed up target for corrections 9/18 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Scenic Hwy - Dwg received - Need to consider partial release | Full |  |  | Yes |  |  | Revised DWG week of 9/3/19. TCP Requested |  | 1980-01-01 | Y | [11 empty] | 15172 | 2.8735 | 0 | 0 | 0 | 0 | 2.8735 | 0 | 2.8735 | 0 | 2.8735 | 0 | 0 | 2.8735 |  | Keep |  | Yes | COMP |  |  |  |  | 2019-10-11 | 2019-12-03 | 2019-12-27 | 2019-12-20 |  | Yes | Shovel Ready | [14 empty] | 93 | [9 empty] | Pine Grove | Amador | 38.4082 | -120.6204 | E.5014680.01 |  |  |  | 2019 | Q1 |  |  |  |  | Y | PINE GROVE 11029145 | 156 |  |  |  | 2021-03-01 20:30
35043296 |  |  |  | WDDB - WILLOW CRK 1103 LR 3090 |  |  | UNSC | 6300 | 0 | 6698 | 6698 | 1.2686 | 0 | 0 | 0 | 0 | 6698 | 1.2686 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-03-26 17:00 |  |  | 2020-05-22 | 2020-05-31 | 2020-05-22 | 2019-10-31 | 2019-10-31 | Yes | 2020-05-22 | 5/22: APPROVED - INTO PEND 05/20: EEI applying corrections and routing05/20: ADE rtn corrections to CO; apply and route05/06: EST completed internal rvw, applying changes; Target EOW sub04/29: Site visited - fielded loc 10; EST to provide status update on Loc 7 - EST information to be uploaded04/22: Refielding04/08: Field meet sched; Veg to adjust to use of Loc 7.04/01: Push 1mth (Schd Mtg, Apply Change, ADE Rvw); [REDACTED] to reachout to JO - JO needs to pull parties together and seek resolution. EST ready to go as-is or work on new approach(es).- 12/12: Push for resolution - bumped for resolution status12/20: Holding: Three issues at this location, 1] planner doesn't like location of switch on a slight bend and requested more pictures. 2] EEI will need a change order to visit the site itself and expending fielding resources will affect our other priority commitments.3] Veg also has an issue with the poles that are being designed OH since there is a common issue with vegetation.The third issue, these locations are only being designed OH due to a land issue which won't allow us to go UG.12/18 <-- 12/11: Planner/Veg - land issues; still addressing scope 12/04 <-- 11/20: Pending pictures and planner feedback11/13: Push 2wk - Veg feedback - OH back to UG, based on land/veg issue/customer11/06 |  |  |  | 2020 - Q1- M3 [R303] | COMPLETED | No | Wood | 9 | 0 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-01 | 2020-09-01 | Full |  |  | Requires a Caltrans permit | Full |  |  | Yes | 2021-12-31 |  | Permit expires on 12/31/19 | [6 empty] | Eed response from [REDACTED] | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2686 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-03-26 17:00 |  | INPR | 2022-02-16 08:00 | 2022-04-04 08:00 |  | 2022-04-04 08:00 | 2020-09-02 |  |  |  |  | Yes |  |  | 100000 | 779794.4 |  | 776346.19 | 676346.19 |  | 779.8% | 153587.7 |  |  |  | 614708.037 |  | 19 | [7 empty] | Remove |  | Willow Creek | Humboldt | 0 | 0 | 35043296 |  |  |  | 2021 |  | 2020-03-31 | 2021-01-02 |  |  | Y | WILLOW CREEK 11033090 | 2204
35043299 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 |  |  | ESTS | 6500 | 0 | 6376 | 6376 | 1.2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-11 |  |  | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2020-04-16 | 4/8: Working Job Packages - 4/30 1st ADE submittal target4/17: On track for 4/304/24: 1st ADE submitted5/8: waiting for 1st corrections5/15: waiting for 1st corrections5/22: 1st corrections will be submitted today 5/225/29: waiting for 2nd submittal6/3: 2nd submittal 6/5: waiting for 2nd corrections6/12: ready to route - need to clear DCNL Status6/14: routed, [REDACTED] cannot see approvers on EES6/20: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Prelim drawings provided to ENV - ERTC Received and uploaded | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 6376 | 1.2076 | 0 | 0 | 0 | 0 | 1.2076 | 0 | 1.2076 | 0 | 1.2076 | 0 | 0 | 1.2076 |  |  | 2019-07-11 |  | N/A | 2019-09-09 | 2019-11-27 | Yes | 2019-11-27 | 2019-07-26 |  |  | 2019-11-27 |  |  |  |  | 1224410.6 |  |  | 1224411 | 0.4 |  |  | 1211548.4 | [5 empty] | 9 | [9 empty] | Ferndale | Humboldt | 0 | 0 | 35043299 |  |  |  | 2019 | Q3 |  |  |  |  | Y | EEL RIVER 11024814 | 936
35043303 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 |  |  | DOCC | 8500 | 0 | 8140 | 8140 | 1.5417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-02 |  |  | 2019-06-04 |  | 2019-06-04 |  |  | Yes | 2019-06-06 | 6/3: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Design sent to enviro in June | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 8140 | 1.5417 | 0 | 0 | 0 | 0 | 1.5417 | 0 | 1.5417 | 0 | 1.5417 | 0 | 0 | 1.5417 |  |  | 2019-08-02 |  | N/A | 2019-08-12 | 2019-09-19 | Yes | 2019-09-19 | 2019-06-26 |  |  | 2019-09-19 | [17 empty] | 34 | [9 empty] | Ferndale | Humboldt | 40.5118 | -124.1573 | 35043303 |  |  |  | 2019 | Q3 | [5 empty] | EEL RIVER 1102530 | 2931
35043421 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  |  | ESTS | 11665.4 | 0 | 11665.4 | 11665.4 | 2.2094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2094 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-01-31 | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | 11/04 - 10/07: No updates, can't field due to access issues. EEI in contact with Veg Mgmnt 10/01: Proj Mgr - coordinating w/ stakeholders and Vendor to progress efforts for access to conduct the estimate 09/30 - 08/12: EST scheduled to recheck field conditions for approach to complete estimate 07/22- 06/03: Working toward resolution 06/03- 03/25: JO was in contact - working with Maintenance toward solution - Unable to field - project manager contacting maintenance to see how they access poles 02/27: Flagged COMPOSITE to WOOD [2] 03/25: JO was in contact - working with Maintenance toward solution 02/18: Unable to Field (Cliff side/Access Road washed out - helicopter sets per ADE); EST waiting on JO response - To review and firm up 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/20/20 11/27: EEI advise +3wk Push (will send details) 11/20 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/12 |  |  |  | 2021 - Q1- M1 [R2022(+)_168] | Iss_R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Need to clear veg for estimating - Will involve BLM | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2094 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-31 17:00 |  | INPR | 2022-08-02 08:00 | 2022-10-24 17:00 |  | 2022-11-23 17:00 | [5 empty] | Yes |  |  | 750000 | 3425495.8 |  | 40000 | -710000 |  | 456.7% | 37158.5 |  |  |  | 1550449.8623 |  | 59 | [7 empty] | Remove |  | Pioneer | Amador | 38.4438 | -120.5087 | E.5014728.01 | ML |  | 2020-168 | 2021 |  | 2020-12-31 | 2021-06-29 |  |  | Y | WEST POINT 110112256 | 96
35043422 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  |  | ESTS | 11037 | 0 | 11037 | 11037 | 2.0903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0903 | 11926 | 2.2587 | ST | 08W |  | 2022-01-11 17:00 |  |  | 2020-11-30 | 2021-01-31 | 2020-11-30 | 2020-09-17 | 2020-09-17 |  |  | 11/04: ADE in rvw 11/03: EEI submitted corrections for 4th ADE rvw 11/02: ADE rtn 3rd rvw to CO 10/28 - 10/14: ADE in rvw 10/12: EEI submitted for 3rd ADE rvw 10/07: EST Submittal by 10/12 10/05: ADE rtn 2nd corrections to CO 09/30 - 09/23: ADE in rvw; priority based 09/17: EEI submitted for 2nd ADE rvw - PRELIM DWG ready 09/14: ADE rtn 1st corrections to CO 09/02: ADE in rvw; priority based 08/28: EEI submitted for 1st ADE rvw [2] - renumbered 08/26: EST target sub (TBD); Est working 2 Comp to Wood conversions 08/20: ADE rtn 1st corrections to CO; EST to renumber locations 08/19: ADE assigned (Terry) 08/12 - 04/22: ADE to be assigned 04/21: EEI submitted for 1st ADE rvw 04/15 - 03/25: EST firmed up 1st sub 02/27: Flagged COMPOSITE to WOOD [2] 02/26: On Track 02/19: Est priority alignment shift 02/12: In review; Push to next week 01/29: Access issues - field conditions (road washed out) 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/3/20 11/27: EEI advise +3wk Push (will send details) 11/20 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q4- M11 [R2022(+)_318] | R4.2 - ADE Review in Progress |  | Wood | 63 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0903 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-11 17:00 |  | INPR | 2022-03-03 08:00 | 2022-04-15 17:00 |  | 2022-05-17 17:00 | [8 empty] | 300000 | 2002149.4 |  | 500000 | 200000 |  | 667.4% | 47887.3 |  |  |  | 957809.9875 |  | 56 | [7 empty] | Remove |  | Pioneer | Amador | 38.487 | -120.5231 | E.5014727.01 |  |  |  | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | WEST POINT 1101L2219 | 137
35043423 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  |  | PEND | 5885 | 0 | 5885 | 5885 | 1.1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1146 |  |  | ST | 08W | SH | 2021-12-28 17:00 |  |  | 2020-10-05 | 2020-10-31 | 2020-10-05 | 2020-07-01 | 2020-07-01 | Yes | 2020-11-16 | [Composite to Wood - Sept List]10/05: APPROVED - INTO PEND10/01: Routed to [REDACTED] on Vacation09/23: Conversion Complete - data issues; seeking approval to add cost09/16 - 08/05: EST - Waiting on site survey; : Conversion 1st sub (9/18)07/30: lack of radio and L-band signals in the area will delay the project until Telecomm addresses the signal issue. cannot proceed with ordering the exact antenna required to operate the SCADA equipment. 07/22 - 07/15: EST - Waiting on site survey07/08: ADE rtn 2nd corrections to CO; apply and route07/01: QUES submitted for 2nd ADE rvw; ADE rvw - priority based06/24: Waiting on GC; can submit same day06/17: On Track - RISK GC rvw delay06/10: EST submitted for GC cost; ready to submit upon response06/03: EST target sub (6/8) 05/28: ADE rtn 1st corrections to CO05/27 - 05/20: ADE rvw - priority based05/14: ADE assigned ( [REDACTED] DB)05/06 - 1/29: ADE to be assigned [Q3.9]01/22: QUES resubmitted for 1st ADE rvw - redesigned to reduce the overall cost of the work (material and labor). 12/13: EST advised, will be resubmitting; TBD12/03 QUEs submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/27 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2021 - Q1- M1 [R2022(+)_312] | COMPLETED |  | Comp | 9 | 32 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full | [5 empty] | TCP requested | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1146 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-28 17:00 |  | INPR | 2022-02-11 08:00 | 2022-04-04 17:00 |  | 2022-04-08 17:00 | 2020-11-13 | [7 empty] | 250000 | 1621977.9 |  | 1561814.97 | 1311814.97 |  | 648.8% | 68123.2 |  |  |  | 1455232.5084 |  | 30 | [7 empty] | Remove |  | Volcano | Amador | 38.487 | -120.5231 | E.5014726.01 | ML |  |  | 2021 | Reserve | 2020-09-30 | 2020-10-30 | 2020-12-06 |  | Y | WEST POINT 110113444 | 63
35046211 |  |  |  | CWSP - GARBERVILLE 1102 HENDRIX PILOT |  |  | UNSE | 4000 | 0 | 4000 | 4000 | 0.75758 | 0 | 0 | 0 | 0 | 4000 | 0.75758 | 0 | 0 | 0 |  |  | HB | 08W | [17 empty] | No | [25 empty] | Yes | 2022-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75758 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 95000 |  |  | 95000 | 0 |  |  | 23788.8 | [5 empty] | 17 | [7 empty] | Remove |  | Redway | Humboldt | 40.118 | -123.8285 | 35046211 |  |  | 2020-093 | 999 | [5 empty] | Y | GARBERVILLE 11021510 | 1630
35046371 |  |  |  | ECOP - STANISLAUS 1702 LR 37276 |  |  | PROD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W |  | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Arnold | Calaveras | 0 | 0 | [11 empty] | STANISLAUS 170237276 | 37
35047429 |  |  |  | CWSP - WILLITS 1104 - LR 34008 PH 1 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Willits | Mendocino | 39.3986 | -123.342 | [11 empty] | WILLITS 110434008 | 50
35047601 |  |  |  | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 |  |  | UNSE |  | 0 | 46358.4 | 46358.4 | 8.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.78 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | waiting for Field Scoping checklist | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.78 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 500000 | 16776600.9 |  | 500000 | 0 |  | 3355% | 19712.7 |  |  |  | 1910774.59 |  |  |  |  | Complete | Scoping meeting on 7/23/20 |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-047 | 2021 | [5 empty] | Y | BRUNSWICK 110532536 | 9
35048678 |  |  |  | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 |  |  | UNSE |  | 0 | 36960 | 36960 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | waiting for Field Scoping checklist | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 500000 | 13400928 |  | 500000 | 0 |  | 2680% | 15606.5 |  |  |  | 1914418.2857 |  |  |  |  | Complete | Scoping meeting on 7/23/20 |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-048 | 2021 | [5 empty] | Y | BRUNSWICK 110532536 | 9
35049537 |  |  |  | CWSP - BIG BASIN 1102 - 9741 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Boulder Creek | Santa Cruz | 0 | 0 | [11 empty] | BIG BASIN 11029741 | 419
35050942 |  |  |  | CWSP: GARBERVILLE 1101 HENDRIX PILOT |  |  | UNSE | 9000 | 0 | 9000 | 9000 | 1.7045 | 0 | 0 | 0 | 0 | 9000 | 1.7045 | 0 | 0 | 0 |  |  | HB | 08W | [17 empty] | No | [25 empty] | Yes | 2022-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7045 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 95000 |  |  | 95000 | 0 |  |  | 13257.7 | [5 empty] | 36 | [7 empty] | Remove |  | Garberville | Humboldt | 40.0228 | -123.7936 | 35050942 |  |  | 2020-095 | 999 | [5 empty] | Y | GARBERVILLE 11011514 | 2062
35050951 |  |  |  | CWSP: MONTE RIO 1113 HENDRIX CABLE |  |  | UNSE | 7400 | 0 | 7400 | 7400 | 1.4015 | 0 | 0 | 0 | 0 | 7400 | 1.4015 | 0 | 0 | 3.4451e-16 |  |  | SO | 08W |  | 2021-09-03 17:00 | [15 empty] | No | [21 empty] | High level review indicates only caltrans (non-scenic) but multiple poles. |  |  |  |  | 2022-12-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4015 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2021-09-03 17:00 |  | INPR | 2022-02-01 08:00 | 2022-03-16 17:00 |  | 2022-03-16 17:00 | [8 empty] | 95000 |  |  | 95000 | 0 |  |  | 24866.8 | [5 empty] | 49 | [7 empty] | Remove |  | Guerneville | Sonoma | 38.4945 | -123.0109 | 35050951 |  |  | 2020-068 | 999 | [5 empty] | Y | MONTE RIO 1113CB | 163
35051268 |  |  |  | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Willits | Mendocino | 39.437 | -123.3898 | [11 empty] | WILLITS 110434008 | 50
35051472 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 |  |  | ESTS |  | 0 | 38438.4 | 38438.4 | 7.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.28 |  |  | CC | 08W | SH | 2023-12-25 |  |  |  | 2021-09-30 | [5 empty] | waiting for Field Scoping checklist | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.28 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [28 empty] | Complete | Scoping meeting on 7/14/20 |  |  |  | Remove |  | Scotts Valley | Santa Cruz | 37.0639 | -122.0055 |  |  |  | 2021-113 | 2022 | [6 empty] | CAMP EVERS 21065020 | 46
35051827 |  |  |  | STS-POLE_DECA_REMV - 44243 ROAD 619AHWAH |  |  | CLSD |  | 0 | 634 | 634 | 0.12008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF |  |  |  |  | 2019-01-01 | [55 empty] | 634 | 0.12008 | 0 | 0 | 0 | 0 | 0.12008 | 0 | 0.12008 | 0 | 0.12008 | 0 | 0 | 0.12008 |  |  |  |  | N/A | [7 empty] | 2019-07-01 | [29 empty] | 37.3614 | -119.7348
35052718 |  |  |  | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 |  |  | CLSD | 0 | 2265 | 0 | 2265 | 0.42898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-01-11 |  |  | 2019-01-11 |  | 2019-01-11 |  |  | Yes | 2018-11-07 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 2265 | 0.42898 | 0 | 0 | 0 | 0 | 0.42898 | 0 | 0.42898 | 0 | 0.42898 | 0 | 0 | 0.42898 |  |  |  |  | N/A |  |  |  |  | 2019-01-11 |  |  | 2019-07-24 | [17 empty] | 0 | [9 empty] | Angwin | Napa | 38.5653 | -122.4416 | 35052718 |  |  |  | 2019 | Q2 | [5 empty] | SILVERADO 210478268 | 64 |  |  |  | 2021-03-04 11:50
35052731 |  | 2021 | 220 Mile Plan | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Scoped | PEND | 8120 | 0 | 7779 | 7779 | 1.4733 | 0 | 0 | 7779 | 1.4733 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2021-04-15 |  | Y | 2020-08-04 | 2020-08-31 | 2020-08-04 | 2020-05-01 | 2020-05-01 | Yes | 2021-03-04 | [2020 Const. Sched]08/04: APPROVED - INTO PEND08/03: ADE rtn 4th corrections CO; EST submitted for 5th ADE rvw07/31: EEI submitted for 4th ADE rvw07/29: EEI target sub (7/31)07/28: ADE rtn 3rd corrections to CO; Final Corrections07/22 - 07/15: ADE in review07/13: EEI submitted for 3rd ADE rvw (new standards)07/08: On Track07/01: EST target sub (7/10); - issues with Caltrans still need to be worked out - redoing OCalcs per ADE06/24: EST target pushed (7/2); applying standards change06/10: EOD Pushed - Est target sub (6/15) - anticipated 1-2 week push; update via standards version; this is an old job and when we started work on it, HFTD was not in OCalc - EST instructed to continue designing to old standard; Per the direction from [REDACTED] , the poles designed under the old standard must still pass in the current HFTD Load Case06/04: ADE return 2nd corrections to CO - Ocalcs and ZPole06/03: Impact resolution forecast??05/27 - 05/20: ADE/EST Status; at risk, anticipating sub date changes, TBD upon rvw; Per PMgr 'sounds like on hold til issues with CALTRANS resolved'05/19: GC Review returned and the Caltrans rejection/comments. From our estimating meeting a couple of weeks ago, it sounded like this was on hold until we have the issue with Caltrans resolved05/17: GC rvw received; PMgr Q&A sched for Mon (5/25)05/13 - 05/06: ADE in rvw; EOD progress risk (+ CAL TRAN ties)05/01: EEI submitted for 2nd ADE rvw04/29: EST impact - keep est. moving through; address CAL Trans impact through process; 04/28: PMgr-is it possible to have estimating make these changes Caltrans is requiring, especially if we have not had any forward progress with a Caltrans meeting?; New requirement is going to slow down the process immensely - CAL TRANS permits taking 60Days - new standard that has been issued for all Aerial pole work within Caltrans Right of Way called a Design Standard Decision Document that will need to be completed and submitted with all aerial encroachment permits in order to be considered for review4/22 - 04/08: Est sub date; JO sched job walk; pending feedback to apply adjustments and align standards (due to age of estimate) (4/24 sub)04/01: EST firm up sub date03/25: ADE rtn 1st corrections to CO03/24: ADE status update?? (DUE - RISK)03/11 - 03/04: ADE (sick) will be done be EOW (3/11)02/26: EST advised, will be impacted by computer crash, upon recpt of corrections02/19: ADE advised (1 to 2 week Push)02/12 - 01/29: ADE Status?? Prelim coming due1/08: ADE prioritized on UG cable replacement 35063021 (for [REDACTED] ) - will switch to next, target is to be on BB early next week.12/18 <-- 11/27: ADE priority shift - 56B rtn job & [REDACTED] - then Big Basin11/20 <-- 11/13: Completing another higher priority review (final)10/29 <-- 10/16: Checked in with ADE: Push 3wk - Finalizing 2 other 2019 projects & review duration (large review anticipated)10/09 <-- 9/17: In Review ( [REDACTED] report it is a large job, require more time)9/11: In Review - EES issue being resolved9/04 <-- 8/14: In Review8/6: [REDACTED] que'd as ADE ; requesting prioritization order of current projects8/2: EEI submitted for 1st ADE Review7/31 <-- 7/24: On Track7/18: 3 PMs confirmed; 1st ADE Submittal Projected for 8/167/16: Send Segment Maps to EEI, EEI to provide Dates7/5: received sub orders6/14: [REDACTED] sent direction to move forward with PM split6/12: on track for 6/14 submittal [REDACTED] is working on printing issues6/12: on track for 6/14 submittal - [REDACTED] e is working on printing issues5/29: [REDACTED] (PG&E EES expert) advised us on methods and steps to take that may fix the issues with the Big Basin estimate.though it did not seem that [REDACTED] was 100% sure that the recommendations will work. The Big Basin PM is a priority for all estimators involved and this may impact other 08W work being developed. EEI expects this effort to take two weeks with 6 estimators to re-enter all the Big Basin EES entries. 1st submittal updated to 6/145/22: still waiting on IT to resolve issues. [REDACTED] to follow up.5/15: still waiting on IT to resolve issues. [REDACTED] to follow up.5/8: waiting to submit on IT issue with EES - assigned [REDACTED] V8) |  |  |  | 2020 - Q3- M7 [R2020_74] | COMPLETED | No | Comp | 13 | 29 |  | 2020-08-15 | Yes |  |  |  | 2020-08-04 | 2020-08-04 |  |  |  |  | Partial | 2020-08-04 | 2020-08-04 | Partial |  |  | ** Caltrans DSDD - Pilot Project- district 5 permit issue pushing this to 6/30/20 - PERTC (excluding CT) expected 8/1. Followed up with PM on status of DSDD on 12/1 - [REDACTED] | Partial |  |  | Yes |  |  | Need start date for Santa Cruz county to issue permit |  |  |  | 2021-04-15 | 2020-08-15 |  | Caltrans delay - Restricted area. ERTC Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4733 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-08-18 17:00 | Yes | INPR | 2021-04-16 08:00 | 2021-12-24 17:00 |  | 2021-12-25 08:00 | 2020-08-18 |  |  |  | 2020-08-28 | Yes |  |  | 3391041.4 | 1916116.1 | 1805936 | 4994628 | 1603586.6 | 2874189.6 | 56.5% | 154530 | 362321.8 | 516851.8 |  | 1300564.7266 |  | 36.0889 |  | Nothing underway | [7 empty] | Boulder Creek | Santa Cruz | 37.1332 | -122.1258 | E.5014542.01 | MX |  | 2020-074 | 2020 | Q3 | 2020-02-29 | 2020-08-14 | 2020-09-12 |  | Y | BIG BASIN 110110296 | 2456 |  | CWSP |  | 2021-03-09 08:31
35052735 |  |  |  | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  |  | UNSC | 10296 | 0 | 10641 | 10641 | 2.0153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0153 |  |  | YO | 08W | SH | 2022-01-03 17:00 |  |  | 2020-07-14 | 2020-12-31 | 2020-07-14 | 2020-07-08 | 2020-07-08 | Yes | 2020-09-05 | 07/14: APPROVED - INTO PEND07/13: EES applied final corrections07/10: ADE provided final corrections to CO07/09: EEI submitted for 3rd ADE rvw; ADE approved07/08: ADE rtn 2nd corrections to CO; Minor corrections07/08: EEI Submitted for 2nd ADE rvw - [PRELIM DWG ready]07/06: ADE rtn 1st corrections (Sheet 4); Complete07/03: ADE rtn 1st corrections (Sheet 3)07/02: ADE rtn 1st corrections (Sheet 2)07/01: ADE rtn 1st corrections (Sheet 1); EST wrking corrections06/30: ADE rtn 1st corrections to CO {pt.1} - sending corrections daily to break it up, as to not give them to you all at once06/30: ADE assigned ( [REDACTED] )06/24 - 04/08: ADE to be assigned04/03: EEI submitted for 1st ADE rvw [2]03/24- 03/03: EST to assess impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2] - Pulled back02/25: EEI submitted for ADE rvw02/19: Internal rvw finialized - EOW02/12: Back from Internal Rvw, took longer than anticipated - EOW/early next week02/05: On track for EOW (early next wk)01/22: Push 2/7 Scope01/08: On Track 1st sub12/18: Push 1st sub: EST Priority shifts12/11 <-- 11/13: On Track 12/3011/06: Push - PSPS/Fielding Impacts10/29 <-- 10/16: On Track 1st ADE Sub 11/2810/09: Push - 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/22 |  |  |  | 2020 - Q4- M12 [R115] | COMPLETED | No | Wood | 68 | 9 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-07 | 2020-09-07 | Full |  |  | Forest Svs no longer a constraint | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-12-07 |  | 2020-11-16 | 2020-10-13 |  | Preinspection stage as of 10/20/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0153 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-03 17:00 |  | COMP | 2022-02-22 08:00 | 2022-05-26 17:00 |  | 2022-08-11 17:00 | 2020-10-21 |  |  |  |  | Yes |  |  | 250000 | 3063066.3 |  | 250000 | 0 |  | 1225% | 172335.1 |  |  |  | 1519875.0178 |  | 75 |  |  | Complete |  |  |  |  | Remove |  | Mi Wuk Village | Tuolumne | 0 | 0 | E.5014723.01 | ML |  | 2021-001 | 2021 |  | 2020-12-31 | 2021-04-15 |  |  | Y | MIWUK 170110600 | 1
35052737 |  | 2022 | 2021 Rsrv | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Scoped | PEND | 8605 | 0 | 8605 | 8605 | 1.6297 | 0 | 0 | 0 | 0 | 8605 | 1.6297 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-04-15 |  | Y | 2020-06-29 | 2021-09-30 | 2020-06-29 | 2019-11-15 | 2019-11-15 | Yes | 2020-06-29 | IN PEND12/18: EST Awaiting Ocalc stamping12/11: EOD Push12/06: OCalcs uploaded - Final correction request sent to contractor12/04 - ADE req - Add stamped OCalcs; EST to submit target 12/0611/27: routed on 11/20 - waiting for approval, ADE on vaca11/19: ADE rtn 2nd corrections to contractor - small fixes, when complete 'ok to route for approval'11/13: On Track - ADE requesting 'corrected' pkg; sent 11/1411/04: EEI submitted for 2nd ADE rvw10/31: ADE returned corrections to contractor10/29: with ADE for rvw10/23: EEI submitted for 1st ADE rvw - ADE assigned ( [REDACTED] )10/16: On Track 1st sub 10/14 (EOW)10/09: EEI update - pulled in.10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) |  |  |  | Priority Q1 | COMPLETED | No | Comp | 7 | 48 |  |  | yes |  |  |  | 2021-04-15 | 2021-04-15 | [5 empty] | 2021-04-15 | 2021-04-15 |  |  |  | ** Caltrans DSDD - Pilot Project - 5/22/2020 delayed - will match Land Clear Date - Caltrans permit rejected as of 4/27/20. Partial not desired. Preliminary Enviro reviews complete. |  |  |  | Yes | 2020-12-31 |  | [REDACTED] sending prelim on 12/10/19 |  |  |  | 2021-03-01 |  |  | DSDD - Cal Trans Delay/BC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6297 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-06-10 | Yes | INPR | 2022-03-02 08:00 | 2022-04-27 17:00 |  | 2022-05-26 17:00 |  | 2021-11-09 07:00 | 2021-12-30 16:00 |  |  | No |  |  | 2060220.2 | 1955791.3 | 2738.2 | 2768676 | 708455.8 | 1951740.1 | 94.93% | 108280.1 | 200 | 108480.1 |  | 1200067.1777 |  | 40 | [9 empty] | Long Barn | Tuolumne | 0 | 0 | E.5014733.01 | ML |  | 2020-016 | 2022 | Q3 | 2020-01-03 | 2020-06-13 | 2020-08-06 |  | Y | MIWUK 17018060 | 2267 |  | CWSP |  | 2021-03-04 21:58
35052739 |  |  |  | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  |  | CONS | 9900 | 0 | 11546 | 11546 | 2.1867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1867 |  |  | YO | 08W | SH | 2020-04-13 |  |  | 2020-04-13 | 2020-04-13 | 2020-04-13 | 2020-02-03 | 2020-02-03 | Yes | 2020-05-13 | 04/13: INTO PEND 04/09: ADE rtn minor corrections; approve for routing 04/08: EST firm up sub date (4/10) - finalizing stamping 04/03: ADE rtn 3rd corrections to CO 04/01: ADE Status (3/30); Rvw in progress, Target 4/2 per ADE 03/24: QUES submitted for 3rd ADE rvw 03/25 - 03/18: EST will have his corrections on the second review back 04/01: ADE target date (3/30)?? to me on 3/27 - In stamping 03/12: Est to review corrections/firm up submittal date - churn in correction cycles; maybe out 1-2 wks 03/12: GC partners need our help to get this out of estimating and into their hands so that we can keep our crews busy 03/05: ADE rtn 2nd corrections to CO 3/04: ADE to submit by Thurday (3/12) 02/26: ADE status, due EOW? 02/19: ADE PTO, finishing review - target EOW next week 02/03: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready] 01/29: Stamping 70 out of 100 complete; EOW 01/22: Waiting on stamps; completed priority PMs; part of current batch 01/08: Est corrections applied, in stamping (Stamping working through backlog and renewing old stamps[700] (4.5wks wrk)- 3rd PE in training)) 12/26: ADE rtn 1st corrections to ECO 12/18<-- 11/20: in review; Pole impact? Status check with ADE. 11/19: Composite Pole impact (availabilities) -45 locs; ADE Bandwidth 11/13:QUES submitted for 1st ADE rvw 11/13: Push - Target 11/13 submittal - Stamping 11/06: On Target 10/30: ADE/EST working through design discussions/Q&A - Target 1st submittal 11/08 10/23: Push 1wk - T-line changes; Target next week 10/16 <-- 10/02: On Track; RISK- Resource availability (Stamping 1 PE) 9/25: On Track 1st ADE submittal 10/22 |  |  |  | 2020 - Q1- M2 [R51] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2019-11-22 | 2019-11-22 |  |  |  |  | Full | 2019-12-10 | 2019-12-10 | Full |  |  | CIF submitted on 10/23/19 | Full |  |  | Yes | 2020-12-31 |  | [REDACTED] sending prelim on 12/10/19 |  | 2020-04-21 | Y | 2020-04-01 | 2020-04-01 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1867 | 0 | 0 | 1.9125 | 1.9125 | 0 | 0 |  | Remove | 2020-04-01 | Yes | COMP | 2022-01-18 08:00 | 2022-03-21 17:00 |  | 2022-04-01 17:00 | 2020-05-13 |  |  |  |  | Yes | Shovel Ready |  | 4023890.8 | 1888372.2 |  | 5180025 | 1156134.2 | 3268357.3 | 46.92% | 638482.5 | 117051 | 755533.5 |  | 863554.9295 |  | 99 | [9 empty] | Twain Harte | Tuolumne | 38.0486 | -120.2438 | E.5014776.01 | ML |  | 2020-051 | 2020 | Q2 | 2020-02-29 | 2020-03-15 | 2020-05-12 |  | Y | MIWUK 17021808 | 165
35052820 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.1 |  |  | FICL | 10715 | 0 | 10619 | 10619 | 2.0112 | 10619 | 2.0112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10392 | 1.9682 | YO | 08W | SH | 2020-04-15 |  |  | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-01-10 | 2020-01-10 | Yes | 2020-03-19 | 03/19: ADE rvw - OK TO CONCUR- INTO PEND03/18: QUES submitted for 9th ADE rvw03/13: QUES submitted for 8th ADE rvw; ADE rtn 8th corrections to CO03/11: ADE rtn 8th correction to CO (Standard change, req to move to new standard)03/04: QUES to review for next submittal - coordinating on corrections03/03: QUES submitted for 7th ADE rvw; ADE rtn 7th corrections to CO02/26: ADE/EST checking with JO to change to Recloser or stay with SW. OCalc software made slight changes (89.7% to 89.6%) so stamped PDF will not match PPLX files (Change Order to revise and restamp); This is the one with Older version Ocalcs, need instructions from [REDACTED] on how to go back to old version02/26: ADE rtn 6th corrections to CO02/19: Impacted by OCalc upload issue; (numbers being changed in background)02/13: QUES submitted for 6th ADE rvw; ADE request stamped OCALCs to compare02/12: QUES submitted for 5th rvw; ADE return 5th corrections to CO02/08: ADE rtn corrections to CO 02/04: QUES submitted for 4th rvw01/30: ADE rtn 3rd corrections to CO01/28: |  |  |  | 2020 - Q1- M2 [R44] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted on 10/21/19 | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 10619 | 2.0112 | 0 | 0 | 2.0112 | 0 | 2.0112 | 0 | 2.015 | 0.0037879 | 0 | 2.0112 |  | Keep | 2020-04-15 | Yes | N/A | 2020-04-24 | 2020-06-11 | Yes | 2020-06-11 | 2020-04-08 | 2020-07-10 | 2020-07-10 | 2020-08-04 |  | Yes | Shovel Ready |  | 7032493.2 | 3381266.9 | 91962 | 3585097 | -3447396.2 | 3652108.8 | 48.08% | 3285070.8 | 95313.6 | 3380384.4 |  | 1681240.1575 |  | 54 |  | Estimatros computer crashed | [7 empty] | Twain Harte | Tuolumne | 38.0528 | -120.2183 | E.5014773.01 |  |  | 2020-044 | 2020 | Q2 | 2020-02-29 | 2020-06-29 | 2020-08-12 |  | Y | MIWUK 1702CB | 25
35052821 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 - OCB - PH 1.1 |  | Scoped | CONS | 9750 | 0 | 9083 | 9083 | 1.7203 | 0 | 0 | 9083 | 1.7203 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-08-10 |  | Y | 2020-01-15 | 2019-12-20 | 2020-01-15 | 2019-11-04 | 2019-11-04 | Yes | 2020-08-13 | 12/20: IN PEND 12/18: EEI submitted for final rvw 12/17: Approval rejected for final corrections 12/16: ADE approved for routing 12/16: EEI submtted for review 12/13: ADE rtn correctons to contractor 12/10: EEI submitted for review; Ticket answered - rerouted the job in EES 12/07: ADE Rtn corrections to contractor 11/27: System validation issue - ticket submitted 11/22: EEI reported as routed as of 11/22 11/20: Composite pole impact (32 hrs) new 3rd sub date?; 11/16: ADE rtn 2nd corrections to contractor 11/07: Experiencing 'High Validation Error' w/ linked OCalc/PIBID; submitted ticket [11/08] 11/04: EEI submitted for 2nd ADE rvw 10/30: ADE rtn 1st corrections to contractor 10/17: ADE Assigned (Carlos) 10/29 <-- 10/16: ADE to be assigned (waiting for 2020 priority list) 10/09: ADE to be assigned 9/24: EEI Submitted for 1st ADE rvw 9/04: EEI to supply new target dates (push) |  |  |  | Priority Q2 | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-05-22 | 2020-05-22 |  |  |  |  | Full | 2020-05-22 | 2020-05-22 | Full |  |  | 5/1/2020 - REVISE to 5/22 - Project Manager responses are still needed to submit this to USFS as of 4/27 | Full |  |  | Yes | 2020-12-31 |  | Will submit to US Forest on 1/27 |  | 2020-08-31 | Y | 2020-08-10 |  |  | Work at 75% as of 8/25/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7203 | 0 | 0 | 2.1303 | 2.1303 | 0 | 0 |  | Keep | 2020-07-27 | Yes | COMP | 2020-08-31 08:00 | 2021-07-20 17:00 |  | 2021-08-31 17:00 | 2020-08-13 | 2020-06-22 07:00 | 2021-04-23 16:00 |  | 2020-08-05 | Yes | Shovel Ready |  | 3322975.4 | 946780.7 | 1325532.5 | 4765282 | 1442306.6 | 1950140.5 | 28.49% | 660338.7 | 712496.2 | 1372834.9 |  | 550369.0516 |  | 49 | [9 empty] | Twain Harte | Tuolumne | 38.0571 | -120.2065 | E.5014771.01 | ML |  | 2020-005 | 2020 | Q3 | 2019-12-20 | 2020-05-31 | 2020-07-27 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35052822 |  |  |  | CWSP - MIWUK 1701 - LR 8050 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Twain Harte | Tuolumne | 38.0569 | -120.203 | [11 empty] | MIWUK 17018050 | 45
35052823 |  |  |  | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  |  | UNSC | 7835 | 0 | 8100 | 8100 | 1.5341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5341 |  |  | YO | 08W | SH | 2020-11-06 |  |  | 2020-07-03 | 2019-12-18 | 2020-07-03 | 2020-06-05 | 2020-06-05 | yes | 2020-07-31 | 07/01: Order unable to be approved until NEW PM/WBS - planning reached out to [REDACTED] 06/29: ADE - ready for approval06/24: In ADE rvw; date push 6/26; New PM needing to be created to transfer cost; 'do not execute' set locking out Order06/19: planning order 5530178 got linked to PM order: 35052823 when created . Later on 05.03.2019 it has been changed to 5785220 by LANID: RJA3. Unable to process.06/18: Pre-Final rvw provided to ADE; to include in ADE rvw06/16: EEI submitted for 3rd ADE rvw06/11: ADE rtn 2nd corrections to CO06/10: ADE soft target (6/12) 06/05: EEI submitted for 2nd ADE rvw06/0 |  |  |  | 2020 - Q2- M5 [R38] | COMPLETED |  | Comp | 2 | 40 |  |  | Yes |  |  |  | 2020-07-28 | 2020-07-28 |  |  |  |  | Full | 2020-07-28 | 2020-07-28 | Full |  |  | CIF submitted 6/15 | Full |  | 2020-07-31 | Yes | 2021-07-29 |  |  |  | 2020-09-30 | Y | 2020-09-15 | 2020-08-21 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5341 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-05 | Yes | COMP | 2022-02-25 08:00 | 2022-04-07 17:00 |  | 2022-04-25 17:00 | 2020-10-25 |  |  |  | 2020-11-06 | Yes |  |  | 6133206 | 2631951.4 |  | 6133206 | 0 | 5329444.7 | 42.91% | 108943.7 | 694817.6 | 803761.3 |  | 1715642.3941 |  | 52 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.01 | ML |  | 2020-038 | 2021 | Reserve | 2020-05-31 | 2020-07-14 | 2020-08-19 |  | Y | MIWUK 17028130 | 83
35052824 |  |  |  | CWSP - MIWUK 1702 - LR6018 - PH 2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Twain Harte | Tuolumne | 38.0594 | -120.268 | [11 empty] | MIWUK 17026018 | 23
35052825 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Scoped | CONS | 5785 | 0 | 6168 | 6168 | 1.1682 | 0 | 0 | 6168 | 1.1682 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-08-24 |  | Y | 2020-04-29 | 2020-04-29 | 2020-04-29 | 2019-12-09 | 2019-12-09 | Yes | 2020-05-21 | 04/29: APPROVED - INTO PEND 04/28: EST route (4/29) 04/27: ADE rtn 5th corrections to CO - ok to route 4/24: EEI submitted for 5th ADE rvw 4/22: EST set sub (4/27) 04/21: ADE rtn 4th corrrections to CO 04/15: ADE soft target 4/17 04/10: EEI submitted for 4th ADE rvw 04/08: Determined that transmission will need to increase their pole size - Estimator having hard drive issues03/25: Push sub to 4/8 - Job walk rescheduled 04/01 - 03/11: EST - dependent on job walk; problem with one location that we will need to underground to get under transmission. 02/19: Push to 2/24: Couple locations required refielding 02/10: ADE rtn 3rd corrections to CO 1/29: ADE status?? 1/13: EEI submitted for 3rd ADE rvw 01/08: push 3rd sub 1/17 - Est Bandwith 1/03: ADE rtn 2nd corrections to contractor 12/18: Push 2nd rvw; ADE bandwith 12/02: EEi submitted for 2nd ADE rvw 11/27: On Track 2nd Sub 12/06 11/25: ADE rtn 1st corrections to contractor 11/20 <-- 11/13: In rvw 11/07: Assigned to ADE 10/29 <-- 10/16: ADE to be assigned (waiting for 2020 priority list) 10/15: EEI submitted for 1st ADE rvw 10/09:Target dates shifted (resources finishing El Dorado & Volta) 1wk 10/02 <-- 9/11: On Track 09/04: On Track for 1st Submittal 10/01 |  |  |  | 2020 - Q1- M3 [R176] | COMPLETED | yes | Wood | 39 | 14 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Sent | Full |  |  | Yes | 2021-01-09 |  | Annual Permit |  | 2020-11-02 | Y | 2020-08-12 | 2020-07-29 |  | 90% complete as of 10/6/20. Need line covers | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1682 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-07-14 | Yes | COMP | 2021-04-06 08:00 | 2021-05-13 17:00 |  | 2021-06-01 17:00 | 2020-05-27 |  |  |  | 2020-08-24 | Yes |  |  | 2342291 | 1587633.3 | 1048628 | 3544410 | 1202119 | 1113971.7 | 67.78% | 549771.4 | 678547.9 | 1228319.3 |  | 1359063.5253 |  | 75 | [9 empty] | Twain Harte | Tuolumne | 38.0489 | -120.2345 | E.5014722.01 | MX |  | 2020-176 | 2020 | Q3 | 2020-03-31 | 2020-03-30 | 2020-04-29 |  | Y | MIWUK 1702S2247 | 2737 |  | PRE
35053033 |  | 2020 | 220 Mile Plan | CWSP - TASSAJARA 2112 - FUSE 18053 |  |  | MAPP | 37377 | 0 | 31174 | 31174 | 5.9042 | 31154 | 5.9004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2019-12-11 |  |  | 2019-05-22 | 2021-02-28 | 2019-05-22 |  |  | Yes | 2019-12-02 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | State Park Permit Delay - Critical Habbitat | Full |  |  | Yes |  |  | Received message from CCC that this is a private road so no permit is needed. |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 31174 | 5.9042 | 0 | 0 | 5.9042 | 0 | 5.9042 | 0 | 5.9042 | 0 | 0 | 5.9042 |  | Keep | 2019-12-11 | Yes | N/A | 2019-12-03 | 2020-06-04 | Yes | 2020-06-04 | 2019-12-02 | 2021-01-13 | 2021-01-13 | 2021-01-13 |  | Yes | Shovel Ready |  | 9709000 | 9399329.7 | 368855 | 9709000 | 0 | 303090 | 96.81% | 9396515.3 | 9394.7 | 9405910 |  | 1591982.4474 |  | 113 | [9 empty] | Danville | Contra Costa | 37.8359 | -121.9505 | E.5014753.01 |  |  | 2020-091 | 2020 | Q1 | 2019-05-22 | 2020-12-18 | 2021-06-30 |  | Y | TASSAJARA 2112D514R | 1556
35053429 |  |  |  | CWSP HALF MOON BAY 1102 FUCO 12457 |  |  | UNSC | 5742 | 0 | 5597 | 5597 | 1.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.06 |  |  | PN | 08W | SH | 2022-04-14 17:00 |  |  | 2019-06-13 | 2020-10-31 | 2019-06-13 |  |  | Yes | 2020-11-24 | 2/25: QUES working on Job, fielding this week3/4: Fielding completed last week3/11: Still working on Job package3/12: CO submitted pending approval3/20-4/3: 4/18 1st ADE submittal date - on track4/8: On track for 1st ADE submittal on 4/184/17: QUES to follow up4/23: Ocalc Completed along with EES - [REDACTED] 5/1: updated submittal 5/35/8: submitted for 1st reivew today 5/8 - assigned to [REDACTED] 5/14: 1st correction received5/15: QUES to follow up with 2nd submittal date5/22: 2nd by 5/245/29: 3rd ADE review submitted - ADE was pulled for B-Tags |  |  |  | Completed | COMPLETED | No | No | 34 | 0 |  |  | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-10-01 | 2020-10-01 | Full |  |  | 9/1/2020- Have discussed with GGNRA. GGNRA has resumed reviews as of 5/19. | Full |  |  | Yes |  |  | GGNRA and private property |  | 2020-12-18 |  | 2020-11-30 | 2020-10-21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.06 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-14 17:00 |  | COMP | 2022-05-27 08:00 | 2022-07-05 08:00 |  | 2022-07-25 17:00 | 2020-11-30 |  |  |  |  | Yes |  |  | 190000 | 1482295.2 |  | 190000 | 0 |  | 780.1% | 110175 |  |  |  | 1398341.7288 |  | 34 |  |  | Complete |  |  |  |  | Remove |  | Half Moon Bay | San Mateo | 37.5235 | -122.4875 | 35053429 | TL |  | 2021-122 | 2021 | 2020 Reserve | 2019-06-13 | 2020-09-15 | 2020-10-26 |  | Y | HALF MOON BAY 11022032 | 1589
35054184 |  |  |  | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | In Scoping | UNSE |  | 0 | 4804.8 | 4804.8 | 0.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Nevada City | Nevada | 39.3056 | -121.0288 | [12 empty] | 606 | 35054184 | PRE |  | 2021-03-11 16:48
35054959 |  |  |  | STS-POLE_IDLE_REMV - 4215 HOLLIS LN FIDD |  |  | CLSD |  | 0 | 406 | 406 | 0.076894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 406 | 0.076894 | 0 | 0 | 0 | 0 | 0.076894 | 0 | 0.076894 | 0 | 0.076894 | 0 | 0 | 0.076894 |  |  |  |  | N/A | [7 empty] | 2019-01-12 | [29 empty] | 38.5424 | -120.693
35055289 |  |  |  | STS-POLE_DECA_REPL - 6999 ARROYO RDLIVER |  |  | CONS |  | 0 | 314 | 314 | 0.05947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | MI | 2AF | IF |  |  |  |  | 2019-04-13 | [55 empty] | 314 | 0.05947 | 0 | 0 | 0 | 0 | 0.05947 | 0 | 0.05947 | 0 | 0.05947 | 0 | 0 | 0.05947 |  |  |  |  | N/A | [35 empty] | Livermore | Alameda | 37.6057 | -121.7497
35055474 |  |  |  | OCGC REDBUD 1101 RECONDUCTOR FOR NB LOAD |  |  | CLSD | 7186 | 0 | 7555 | 7555 | 1.4309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 06H | SH | 2019-06-20 |  |  | 2019-06-20 |  | 2019-06-20 |  |  | Yes | [7 empty] | No | [15 empty] | Full |  |  | Full |  |  | Enviro fielding week of 7/15 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 7555 | 1.4309 | 0 | 0 | 0 | 0 | 1.4309 | 0 | 1.4309 | 0 | 1.4309 | 0 | 0 | 1.4309 |  |  |  |  | N/A | [7 empty] | 2019-12-13 |  | Yes |  |  | 1653532.7 |  |  | 1653533 | 0.3 |  |  | 1566533.4 | [5 empty] | 25 | [9 empty] | Clearlake Oaks | Lake | 39.024 | -122.6783 | 35055474 |  |  |  | 2019 | Q3 |  |  |  |  | Y
35056298 |  |  |  | STS-COND_IDLE_REMV-45828 AUBERRY RD |  |  | DOCC |  | 0 | 326 | 326 | 0.061742 | 326 | 0.061742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 2AF | IF | [60 empty] | 0 | 0 | 326 | 0.061742 | 0 | 0 | 0.061742 | 0 | 0.061742 | 0 | 0.061742 | 0 | 0 | 0.061742 |  | Keep |  |  | N/A | [37 empty] | 37.0604 | -119.3671
35056387 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  |  | ESTS |  | 0 | 5981 | 5981 | 1.1328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1328 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: EST to review if 12/12 Desired EOD can be met - 1st sub target in OCT; expired (No) 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1328 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-28 17:00 |  | N/A | 2022-07-20 08:00 | 2022-11-30 17:00 |  | 2023-01-31 17:00 | [5 empty] | Yes |  |  | 166667 | 27286 |  | 166667 | 0 |  | 16.37% | 26032.1 |  |  |  | 24087.9585 |  |  |  |  | Complete |  |  |  |  | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 |  | ML |  | 2021-148 | 2021 | [5 empty] | Y | PLACERVILLE 21061104 | 16
35056433 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [15 empty] | 1 |  |  |  | 21158.7 | [13 empty] | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 | [10 empty] | Y | PLACERVILLE 21061104 | 16
35056434 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16
35056435 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16
35056438 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16
35056439 |  |  |  | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.8989 | -120.7975 | [11 empty] | PLACERVILLE 21061104 | 16
35056733 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  |  | PEND | 11252.4 | 1930 | 9322 | 11252 | 2.1311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1311 | 8064 | 1.5273 | SI | 08W | SH | 2022-02-28 17:00 |  |  | 2020-08-27 | 2020-10-31 | 2020-08-27 | 2019-10-16 | 2019-10-16 |  | 2020-08-31 | 08/27: QUES rtn for final rvw; APPROVED - INTO PEND08/26: ADE - OK to concur this job; Final corrections communicated08/25: EST to route today08/22: ADE rtn 6th corrections to CO08/20: QUES submitted for 6th ADE rvw08/19: EST target sub (08/21)08/15: ADE rtn 5th corrections to CO08/13: EEI submitted for 5th ADE rvw08/12: On Track08/05: EST target sub (8/13)08/01: ADE rtn 4th corrections to CO; job scope change07/29: ADE in rvw - soft target 8/707/22: QUES submitted for 4th ADE rvw07/22: EST finishing stamping - sub by (7/24); ADE on vacation, rtn Monday 7/2707/15: EST target sub (7/21); finalizing stamping and changes07/08: On Track07/01: EST - ADE requesting change to reduce cost - Chng Ordr to be submitted; Removing PMI-9 from design.06/24: EST push (7/6) - UG design to be changes being applied06/17: EST target sub (6/29)06/12: ADE rtn corrections to CO; 3 locs. could not be opened in SAP for review. EST/ADE coordinated; locs. rvw completed06/03: ADE soft target (6/12)06/01: QUES submitted for ADE rvw05/27: Redesign- full review anticipated with scale of change - firm up ADE rvw duration05/20: EST status (6/1); UG portion going through rvw/stamping05/13: Pending stamps - target sub (5/15)05/06: On Track05/01: Very near ready to turn in for ADE review. But still need stamps04/29: EST close to submittal04/15: Rcv'd response from county; Change Order to be submitted. Going to proceed, should finish quick.04/08: Required survey (rcv'd Mon 4/6); submitting change order04/01: Applying changes;03/18: Rcving Maps - Going to Google earth/overlays - Meeting; more update coming next week03/04: xxx02/20 - 02/19: EST - Check in on base maps; [REDACTED] - just finished going through it, Coordination with EST to take a look and talk if you have any questions. 01/29: Confirm Target date EOD...01/23: Per [REDACTED] - The balance of all five PM's below should, per our bi-monthly meetings, reflect a revised EOD date of 5/31/2020; Can this date be met, w/remaining est required??01/09: EOD push pending resolutions - In talks with PGE Surveying (Unscheduled); Survey needs to sched/Complete; T+30 for Est/Refielding. RISK - additional push based on survey.12/18 <-- 12/11: UG Surveying (Internal actions item); Easement issue - Customer declined access/redesign required (Construction May? confirm - Q2/Q3)12/04 |  |  |  | 2020 - Q3- M8 [R2021_79] | COMPLETED | No | Wood | 57 | 0 |  | 2020-09-18 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-05-01 | 2020-05-01 | Full |  |  | Waiting on Finalized Drawings | Full |  | 2020-12-31 |  |  |  | 10/13/20 - waiting on TCP plans |  | 2020-07-03 | Y | 2020-06-15 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1311 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-28 17:00 |  | INPR | 2022-03-30 08:00 | 2022-08-10 17:00 |  | 2022-10-11 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  | 725000 | 588483.9 |  | 725000 | 0 |  | 81.17% | 585657.8 |  |  |  | 276146.0178 |  | 57 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015417.01 | MX |  | 2021-079 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-10-31 |  | Y | EL DORADO PH 210119752 | 13
35056746 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Scoped | CONS | 10615 | 0 | 10615 | 10615 | 2.0104 | 0 | 0 | 10615 | 2.0104 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-08-20 |  | Y | 2020-03-30 | 2020-06-22 | 2020-03-30 | 2020-03-04 | 2020-03-04 | Yes | 2020-06-22 | 03/30: APPROVED - INTO PEND 03/30: ADE rtn 3rd correctionts to CO; correct and route - EEI routed - ADE rtn for final corrections - EEI submitted final corrections; routed 03/27: EEI submitted for 3rd ADE rvw 03/25: Est target sub 03/27 03/23: ADE rtn 2nd corrections to CO 03/11: ADE - On Vacation; rtn Friday (push 1wk) 02/26: ADE - On Vacation; to start Monday 02/19: EEI submitted for 2nd ADE rvw - applied alternate approach to renumbering to, w/ req for ADE advise if acceptable 02/19: Push to complete - ADE request renumbering/formatting & Change Order 02/05 <-- 01/22: Push to xx; Work other Miwuk/PSPS priorities 01/15: EST target?? 01/08: ADE return 1st corrections to contractor; cut the review short so some of the issues could be addressed before the reviewing the JP intent and EES 12/30: ADE provided PARTIAL corrections to contractor 12/18: ADE status? Due next week 11/27 <-- 11/06: ADE to be assigned; 11/27 Push 1st rvw 1 mth 10/29 <-- 10/16: ADE to be assigned (waiting for 2020 priority list) 10/10: EEI submitted for 1st ADE rvw 10/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs. 10/02: EEI 1st submittal target update to 10/07 9/04: EEI to supply new target dates (push) |  |  |  | 2020 - Q1- M3 [R120] | COMPLETED |  | Wood | 47 | 0 |  |  | Yes |  |  |  | 2020-06-05 | 2020-06-05 |  |  |  |  | Full | 2020-07-24 | 2020-07-24 | Full |  |  | Re-desing dwg sent to Charlotte on 6/22, moved ERTC date up to 7/24 | Full |  | 2020-05-22 | Yes | 2021-01-09 |  | Submitted dwg on 6/28 |  | 2020-09-17 | Y | 2020-08-20 | 2020-08-20 |  | 90% complete as of 9/8/20 - PSPS event |  | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0104 | 0 | 0 | 2.0242 | 2.0242 | 0 | 0 |  | Keep | 2020-07-23 | Yes | COMP | 2020-09-14 08:00 | 2020-09-24 17:00 | Yes | 2021-05-12 17:00 | 2020-07-24 | 2020-09-14 07:00 | 2021-05-28 16:00 |  |  | Yes |  |  | 2950902 | 1003609.6 | 975015.3 | 3642331 | 691429 | 1875758.6 | 34.01% | 388838.9 | 686304.5 | 1075143.4 |  | 499204.7751 |  | 54 | [9 empty] | Mi Wuk Village | Tuolumne | 0 | 0 | E.5015427.01 | TL |  | 2020-120 | 2020 | Q3 | 2020-03-31 | 2020-08-13 | 2020-10-12 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35057010 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  |  | APPR | 6914 | 3135 | 3779 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3095 |  |  | SI | 08W | SH | 2022-04-28 17:00 |  |  | 2021-01-31 | 2020-09-30 | 2021-01-31 | 2019-10-11 | 2019-10-11 | Yes | 2020-07-22 | [Composite to Wood - Sept List]11/10: EST status TBD - mtg cancelled (Holiday)11/04: EST sub (11/05)10/28: EST sub (10/29); in final QC10/21: EST target sub (TBD); Estimator out of office till 10/22; Walkdown schedule for next Wed.10/16: Final rvw - rtn to CO; Con DWG and OCALC need some updating/QC rvw; not seeing how tied together with UG service. 10/14: ADE working with EST on pushing routing through. EST will route 10/1510/07 - 09/23: ADE target sub (10/02)09/08: CAL submitted for 4th ADE rvw/approval09/04: EST Conversion Complete08/12 - 07/29: EST working with county (details below)07/22: USER STATUS, should be back to ESTS - [REDACTED] ooking into07/22 - 07/15: EST - working with County on more specifics of rejection; working on details with LIDAR to be applied; County request(s) will require another contractor to be brought on (Piggy back with QUES - 30-60 day. Geo Tech dependancies (avg 60-90 day impact); EOD ??07/10: County rejected the plans earlier this week. Needs to go back to Estimating to have the OH-UG scope revised.**********06/15: Per [REDACTED] approved; APPROVED - PEND06/08: Routed for approval; APPROVED - INTO PEND06/05: ADE in review06/04: CAL submitted for 3rd rvw06/03: EST Target sub (6/8);Changes were requested; applying changes05/27: On Track for (5/29); more changes than anticipated05/20: EST on track (5/22)05/13: EST status - Target sub (5/22)05/06 - 04/29: Est to proceed; foregoing V-Jobwalk; proceeding with current information with ADE [REDACTED] ; reviewing to establish timeline03/23: Virtual walkdown to be rescheduled03/17: Cal Engineering build a kmz file with simple R/W and Center Line of road, that we could overlay into Google Earth for our ‘virtual’ walkdown? Information would be beneficial in placing sub-structures/pad-mount structures in the best possible location with R/W, existing ditches, trees, and slopes in mind.01/29: Confirm Target date EOD...01/23: Per [REDACTED] - The balance of all five PM’s below should, per our bi-monthly meetings, reflect a revised EOD date of 5/31/2020; Can this date be met, w/remaining est required??01/22: |  |  |  | 2021 - Q1- M1 [R2021_81] | EDRS - EST Routing for approval | No | Wood | 55 | 0 |  | 2020-07-17 | Yes | [12 empty] | Full |  |  | CIF submitted 9/19/19. OH to UG for permitting only |  |  | 2021-02-28 |  |  |  | Permit request sent 9/19/19. Will need to submit permits in early June. |  | 2020-07-15 | Y | 2020-06-22 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3095 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-28 17:00 |  | INPR | 2022-06-20 08:00 | 2022-10-31 17:00 |  | 2022-12-30 17:00 | [5 empty] | No |  |  | 600000 | 319080.3 |  | 600000 | 0 |  | 53.18% | 316745.2 |  |  |  | 243671.3891 |  | 35 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015416.01 | ML |  | 2021-081 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-11-30 |  | Y | EL DORADO PH 210119752 | 13
35057017 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 3.1 |  |  | DOCC | 8569 | 0 | 9006 | 9006 | 1.7057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-18 |  |  | 2019-08-27 | 2020-10-31 | 2019-08-27 |  |  | Yes | 2019-08-27 | 8/6: [REDACTED] - I have it in to me for approval, but there is an issue with the JP credits in EES , call into estimating support to resolve. When resolved it will be put through.8/20: No response from support entities to-date8/22: 16 LOCs exhibiting errors/ OCALC/ Est. issues - to be corrected and PE stamped8/26: BCF submitted for 2nd ADE rvw [PRELIM DWG ready]8/27:APPROVED - PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF Submitted 8/1/19. Expedite if OH | Full |  |  | Yes | 2019-12-30 |  | Permit Request sent 8/1/19 |  | 1980-01-01 | Y | [11 empty] | 9006 | 1.7057 | 0 | 0 | 0 | 0 | 1.7057 | 0 | 1.7057 | 0 | 1.7057 | 0 | 0 | 1.7057 |  |  | 2019-09-18 |  | N/A | 2019-09-19 | 2019-12-03 | Yes | 2019-12-03 | 2019-09-24 |  |  | 2019-12-03 |  |  |  |  | 3201494.4 |  |  | 3201494 | -0.4 | 307603.4 |  | 2706369.9 | 187521.1 | 2893891 | 0 |  |  | 43 | [9 empty] | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015415.01 | ML |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13 |  |  |  | 2021-03-01 13:05
35057018 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  |  | PEND | 10624 | 10624 | 0 | 10624 | 2.0121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0121 |  |  | SI | 08W | SH | 2022-02-24 17:00 |  |  | 2020-11-29 |  | 2020-11-29 | 2019-09-23 | 2019-09-23 |  | 2020-07-17 | 11/04: EST submitted10/28: RD EOD (11/29); retaining walls 2 wks out; met with county; conflict with land survey (distances from street - 2 sources)10/21: Meeting Monday with county and JO in person for job walk07/17: APPROVED - INTO PEND07/17: ADER final corrections to CO; QUES submitted for final rvw07/15: Subcontractor - to conduct some fielding items; Contracts needing to be developed/issued for 3rd party surveying. To be added post approval (approx 1.5 month); RISK - Permitting 6wks out, El Dorado Review07/14: QUES submitted for 4th ADE rvw; ADE approved for routing07/13: ADE rtn [final pt] 3rd corrections to CO; through loc 229, sheet 11; complete07/09: [REDACTED] rvw provided to CO; provided some insight on potential County rvw catch points.07/09: ADE rtn [partial] 3rd corrections to CO; through loc 117, sheet 707/08: ADE in rvw; QUES provided most up to date estimate file on sharepoint07/07: ADE rtn [partial] 3rd corrections to CO; through sheet 3 loc 2007/06: QUES submitted for 3rd ADE rvw07/01: EST Target sub (7/3) - in final rvw; structural usually works from their design 1st - EST trying to get sub-contractor to work from QUES design (structural small piece)06/24: EST On Track06/17: EST to submit (On Track) - w/ ref to civil design points, civil design to be added upon completion.06/16: EST reached out to 2 ENGR firms; waiting on response6/15: [REDACTED] advised - encourage EST to reach out to REY Engineering in Folsom, believe they are versed in working with El Dorado County regarding civil projects and should be able to assist in a job-package to avoid refusal via our future permit submission06/12: EST - this one needs civil engineering for large retaining walls. Rcv'd the locations from [REDACTED] and am contacting the firms today. DO NOT anticipate a quick turn around from civil.6/10: ADE status check - only have 2 pages of the construction map updated since CAD just started working on it today. Hoping the rest of the pages will be done by this Friday, but until then, only have the redlines ADE drew up for them. |  |  |  | 2020 - RD- M11 [R2021_83] | Iss_RD1.2_Rdsn - ADE Redesign Rvw in Progress | No | Wood | 21 | 7 |  |  | Yes | [9 empty] | Full | 2020-05-03 | 2020-05-03 | Full |  |  | Received approval from USFS on package. Finalizing our 299 land rights. | Full |  | 2020-12-31 |  |  |  | Permit Request sent 9/3/19 | [6 empty] | Waiting to initiate until county permit resolved | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0121 | 0 | 0 | 2.4557 | 2.4557 | 0 | 0 |  | Remove | 2022-02-24 17:00 |  | INPR | 2022-03-29 08:00 | 2022-08-09 17:00 |  | 2022-10-10 17:00 | 2020-07-17 |  |  |  |  | Yes |  |  | 725000 | 303291 |  | 725000 | 0 | 442044 | 41.83% | 260115.3 | 22840.7 | 282956 |  | 150731.9729 |  | 54 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015414.01 | ML |  | 2021-083 | 2021 |  | 2020-05-31 | 2020-09-01 |  |  | Y | EL DORADO PH 210119752 | 13
35058026 |  |  |  | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  |  | ESTS | 3309 | 3309 | 0 | 3309 | 0.6267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6267 |  |  | SI | 08W | SH | 2023-12-25 |  |  |  | 2021-09-30 | [5 empty] | External Estimating - CRGN | [5 empty] | No | [9 empty] | 2021-01-30 | 2021-01-30 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Will require a USFS Class 3 approval for undergrounding, access route, Caltrans permit, etc. Potholing ERTC for USFS land released 10/12/20. Full Class 3 submittal to be sent to USFS on 12/7/20 and then will set up a meeting with USFS El Dorado to discuss any questions they may have re. the submittal. | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6267 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-30 17:00 |  | INPR | 2022-01-24 08:00 | 2022-07-04 17:00 |  | 2022-09-02 17:00 | [8 empty] | 245000 | 5885636.4 |  | 245000 | 0 | 122252.9 | 2402% | 117447.5 | 5299.6 | 122747.1 |  | 9391405.3164 |  | 2 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7593 | -120.5087 | 35058026 | ML | UG | 2021-124 | 2022 | [5 empty] | Y | EL DORADO PH 210163464 | 1639
35058267 |  |  |  | IDLE FACILITY-R/O15140 GOLD DUST VOLCANO |  |  | CLSD |  | 0 | 610 | 610 | 0.11553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 610 | 0.11553 | 0 | 0 | 0 | 0 | 0.11553 | 0 | 0.11553 | 0 | 0.11553 | 0 | 0 | 0.11553 |  |  |  |  | N/A | [7 empty] | 2018-10-24 | [27 empty] | Kit Carson | Amador | 38.4252 | -120.611
35058273 |  |  |  | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  |  | DOCC | 6215 | 0 | 6215 | 6215 | 1.1771 | 6215 | 1.1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-04-09 |  |  | 2019-09-17 | 2019-09-21 | 2019-09-17 |  |  | Yes | 2019-09-17 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: ADE TBD 9/10: ADE review returned to contractor 9/12: EEI submitted for 2nd ADE review [PRELIM DWG ready] 9/12: ADE approved |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Submitted to forest service week of 12/10 | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y |  |  |  | Complete | [7 empty] | 0 | 0 | 6215 | 1.1771 | 0 | 0 | 1.1771 | 0 | 1.1771 | 0 | 1.1771 | 0 | 0 | 1.1771 |  | Keep | 2020-04-09 | Yes | N/A | 2020-03-09 08:00 | 2020-06-26 08:00 | Yes | 2020-07-20 17:00 | 2019-12-31 |  |  | 2020-07-20 |  | Yes | Shovel Ready |  | 3559342.7 |  |  | 4515047 | 955704.3 | 468096.7 |  | 3379570.7 | -288324.7 | 3091246 |  |  |  | 32 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.01 |  |  |  | 2020 | Q2 | 2019-09-17 | 2020-03-16 | 2020-06-20 |  | Y | EL DORADO PH 2101CB | 76
35058905 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  |  | DOCC | 11306 | 0 | 11145 | 11145 | 2.1108 | 3971 | 0.75208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-10 17:00 |  |  | 2019-08-30 | 2019-09-14 | 2019-08-30 |  |  | Yes | 2019-08-30 | (Moved into 2019)7/3 - 7/24: On track for 8/98/9: EEI Submitted fr 1st ADE Review - ADE [REDACTED] /14: ADE assigned - [REDACTED] /19: 1st ADE corrections rtn to contractor8/21: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]8/26: 2nd ADE corrections rtn to contractor - (minor corrections) |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/16/19. Caltrans Permit | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 7174 | 1.3587 | 3971 | 0.75208 | 0 | 0 | 2.1108 | 0 | 2.1108 | 0 | 2.1108 | 0 | 0 | 2.1108 |  | Keep | 2020-03-10 17:00 | Yes | N/A | 2019-11-05 | 2020-01-16 | Yes | 2020-01-16 | 2019-10-14 | 2019-10-15 | 2020-01-16 | 2020-01-16 |  | Yes | Shovel Ready |  | 5085298 |  |  | 5418545 | 333247 |  |  | 4717522.4 | [5 empty] | 57 | [9 empty] | Shingletown | Shasta | 40.518 | -121.7552 | E.5015428.01 |  |  | 2020-186 | 2020 | Q1 | 2019-08-30 | 2019-11-19 | 2020-01-16 |  | Y | VOLTA 11029742 | 229
35060229 |  |  |  | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 |  |  | CLSD | 8300 | 0 | 6529 | 6529 | 1.2366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-03-06 |  |  | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/4: Pending Ocals to be signed then will route for EDRS approval |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 6529 | 1.2366 | 0 | 0 | 0 | 0 | 1.2366 | 0 | 1.2366 | 0 | 1.2366 | 0 | 0 | 1.2366 |  |  |  |  | N/A |  |  |  |  | 2019-03-11 |  |  | 2019-07-30 | [17 empty] | 38 | [9 empty] | Miranda | Humboldt | 0 | 0 | 35060229 |  |  |  | 2019 | Q2 | [5 empty] | FRUITLAND 11422006 | 1841
35060582 |  |  |  | SLO 1107 RECOD 3884 FT WITH 2CU TW |  |  | FICL | 3836 | 0 | 3884 | 3884 | 0.73561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-03-06 |  |  | 2019-03-06 |  | 2019-03-06 |  |  | Yes | 2019-03-06 | 3/6: 3rd ADE Submitted |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | ERTC released | Full |  |  | Yes |  |  | [REDACTED] to confirm that annual should cover this work |  | 1980-01-01 | Y | [11 empty] | 3884 | 0.73561 | 0 | 0 | 0 | 0 | 0.73561 | 0 | 0.73561 | 0 | 0.73561 | 0 | 0 | 0.73561 |  |  |  |  | N/A |  |  |  |  | 2019-04-08 |  |  | 2019-10-09 | [17 empty] | 13 | [9 empty] | Oceano | San Luis Obispo | 35.1938 | -120.6781 | 35060582 |  |  |  | 2019 | Q3 | [5 empty] | SAN LUIS OBISPO 1107V02 | 1250
35060584 |  |  |  | RPL OH WIRE ON OTTER-1101 S030CC121 |  |  | PEND | 23884 | 0 | 24027 | 24027 | 4.5506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5506 | 24381 | 4.6176 | CC | 08W | SH | 2023-12-25 |  |  | 2020-02-27 | 2021-09-30 | 2020-02-27 | 2020-12-20 | 2020-12-20 | Yes | 2020-02-27 | 02/27: INTO PEND02/26: EST sub corrections; seeking 1 clarification to finalize ( EOD RISK; targeting EOM approval)02/21: Final corrections rtn to CO for final approval - Potential 1 wk push02/19: EST resaved the poles as proposed designs02/14: EST/ADE unable to finish rvw untill all FAAs recv'd; 90 FAA screenings are required and we only have 73 results. Please contact estimating support.02/12: ADE/EST coordination - rvw-corrections; current - PLC and FAA need to be updated before approving for EES02/10: QUES submitted for 4th ADE rvw02/08: ADE rtn 3rd Corrections to contractor1/31: QUES submitted for 3rd ADE rvw1/28: Finalizing stamping; EOW01/17: ADE rtn 2nd corrections to CO01/15: ADE/EST coordination of correction and routing 01/08: Push 2nd rvw12/20: QUES Submitted for 2nd ADE Rvw - [PRELIM DWGs ready] - ADE will start when rtn from vacation (1/6)12/18: Stamping on hold - PGE rvwing state of CA standards vs. PGE req.12/11: EST prioritizing to Finishing Stamping12/04: On Track if no refielding needed (RISK) - Constructability meeting results go to go with est.11/27: T-line came back; Adding more locations11/1 [REDACTED] - spoke with [REDACTED] Field Engineer, after the call. He stated the terrain is too steep to insert poles and to proceed with the estimate.11-13 <-- 10/25: ADE requesting confirmation from GC; 11/13 Push 2 wk GC10/23: Checking in with ADE10/16: GC review provided. - request ADE confirmation rvw can proceed.10/16: [REDACTED] working on followup - push 2wk10/10: Per [REDACTED] - planning on going out on Monday, the PSPS event this week delaying. I will followup with them Monday for an ETA10/09: Checking on status10/02: In constructablilty rvw (apprx 2wk process), at tail end, following up for a status update. - GC is going to take a look at this for us and get back to us in a couple of weeks. They have the most knowledge of this area and will be the best to build it in 2020. |  |  |  | 2020 - Q1- M2 [R84] | COMPLETED | Yes | Wood | 85 | 0 | [6 empty] | 2021-12-21 | 2021-12-21 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF sent 10/24 | [6 empty] | ERTC Delay - holding of on permit app Can start permit process. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5506 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [9 empty] | Yes |  |  | 176000 | 9290108.9 |  | 176000 | 0 |  | 5278% | 89713 |  |  |  | 2041527.2399 |  | 106.1511 |  | Tline | Complete |  |  |  |  | Remove |  | Carmel | Monterey | 36.3855 | -121.8678 | P.0000106.01 | MX |  | 2021-147 | 2022 |  | 2020-02-29 | 2022-01-20 |  |  | Y | OTTER 11017611 | 1092
35060990 |  |  |  | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  |  | UNSE | 4562 | 0 | 4562 | 4562 | 0.86402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86402 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86402 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35060991 |  |  |  | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  |  | UNSE | 2465 | 0 | 2465 | 2465 | 0.46686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46686 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46686 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35060992 |  |  |  | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  |  | UNSE | 2534 | 0 | 2534 | 2534 | 0.47992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47992 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35060993 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  |  | ESTS | 5545 | 5545 | 0 | 5545 | 1.0502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0502 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/14: Transfered to SCARDA; 09/16: EST approved for conducting surveying (6wk turn-around) 08/26: SCOPE CHANGE - UG removal and OH added 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_160] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0502 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-02-20 17:00 |  |  | 2023-03-15 08:00 | 2023-07-26 17:00 |  | 2023-09-26 17:00 | [5 empty] | Yes |  |  | 71432 | 13501.7 |  | 71432 | 0 |  | 18.9% | 13103 |  |  |  | 12856.4429 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 | E.5015550.01 | TL | MX | 2021-160 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35060994 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  |  | ESTS | 5780 | 2698 | 3009 | 5707 | 1.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0809 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 11/04: EST sub (11/4); CNCS still pending 10/28: PMgr Request for 'Desired EOD' - 11/06 (Nov); 1st sub dependency expired (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M1 [R2021_151] | R0.0 - Estimating |  | Wood | 18 | 2 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0809 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 250000 | 2160565.3 |  | 250000 | 0 |  | 864.2% | 125230.8 |  |  |  | 1998910.9487 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-151 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35061206 |  | 2021 | 220 Mile Plan | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Scoped | CONS | 10380.48 | 0 | 9320 | 9320 | 1.7652 | 0 | 0 | 9320 | 1.7652 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-29 |  | Y | 2020-03-26 | 2020-05-20 | 2020-03-26 | 2019-11-15 | 2019-11-15 | Yes | 2020-05-27 | 03/26: INTO PEND 03/25: PIKE All changes applied , documents updated in SAP and Sharepoint. Routed 03/24: EST Routing status- in progress; work final items/approv - target 3/25 03/20: ADE req route for approv 03/19: PIKE submitted for 6th ADE rvw; ADE rtn rvw, req correct and route 03/17: EST confirm sub date (03/18) 03/13: ADE rtn 5th corrections to CO - Flagged: Planner needs to clear DS73 03/12: PIKE submitted for 5th ADE rvw 03/10: Target 3/11 confirmed - EST pending some O-Calcs for stamping and just finishing that one location 03/03: EST to confirm 5th sub date (set at 3/11 - depends on level of corrections) 03/02: ADE req go through all the OCalcs and choose the worse case load - ADE advised target completion of 4th rvw EOW 02/28: PIKE submitted for 4th ADE rvw 02/25: EST On Track 02/18: AT RISK EOD - EST firm up sub date? 02/14: ADE rtn 3rd corrections to CO 02/11: ADE Status - Rvw Due EOW?? 1/27: ADE in progress 1/24: PIKE submitted for 3rd ADE Rvw 01/21: EST push to EOW - 1/24; Fielding and changes bigger impact than anticipated. Addressing ADE request to replace all services. ADE/EST coordinated. 01/14: Est On Track 01/07: Push 3rd sub 1/17- Waiting on planner - 'Replace all services', 'Apply new 2020 standards' - seeking clarification and needing refielding. - Stay with old standard due to 'in progress' 12/17: Planner prioritized Stanus Laus - working now. 12/09: Mtg scheduled 12/03: Working to connect with OE to address changes; unavailable last week 11/26: ADE changes being requested 11/19: Corrections need to be rvw'd with JO/ADE/Etc on approach 11/15: ADE rtn corrections to contractor 11/13: PIKE submitted for 2nd ADE rvw 11/12: Pending CMCS Approval for UG (OH or UG) - PSPS event impacts 11/08: Corrections have been made; OCALCS ready next week - submitted? 11/05: Applying 'Service" changes and corrections - finalizing today 10/29: Pike working through corrections and final direction on open items. ADE - working fires; Risk for push depending availabilities. On target, unless directed on redesign needs. 10/22: PIKE - Documentation is provided; responding and clarifying discrepancies. 10/21: ADE Rejected submittal - No construction sketch included; CMCS not clear what work is being done where: SAP processing codes need updated, OCalc location needs to be rechecked and Stamped 10/16: ADE assigned to Brad Rice 10/15: ADE to be assigned - holding for 2020 priority list 10/09: ADE to be reassigned, due to UG change/delays 10/08 <-- 10/01: In Review; Estimating working with ADE on access issues; potential UG change still undefined. 9/24: ... Catch up on status next week 9/20: Availability of documents in SAP in question by ADE (rejected?!) 9/20: ADE assigned (Walter) 9/17: PIKE advised - Communication initiated for scope change to partial UG 9/10: Pending ADE assignment (Reviewing Resource loading) - Target dates subject to push 9/03: PIKE submitted for 1st ADE rvw - ADE TBD 9/03: In by EOD 8/27: All information submitting, except JPA (target Monday of next week) 8/13: Confirmed date swaps - moved to 8/23 Target. 8/06 <-- 7/23: On Track for 8/16 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] |  |  |  | 2020 - Q1- M2 [R136] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-05-29 | 2020-05-29 |  |  |  |  | Full | 2020-05-29 | 2020-05-29 | Full |  |  | PERTC by 5/22 | Full |  |  | Yes | 2020-12-31 |  | [REDACTED] submitted request for extention 9/29/2020 |  | 2020-07-10 | y | 2020-05-20 |  |  | 22 Units remaining | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7652 | 0 | 0 | 1.7652 | 1.7652 | 0 | 0 |  | Keep | 2020-05-20 | Yes | N/A | 2020-06-15 | 2020-12-03 | Yes | 2021-09-01 17:00 | 2020-05-27 | 2020-06-14 06:00 | 2021-05-22 15:00 |  |  | Yes | Shovel Ready |  | 3459498 |  | 1419181 | 4711641 | 1252143 | 1244278.7 |  | 2092874.5 | 122344.8 | 2215219.3 |  |  |  | 52 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.01 |  |  | 2020-136 | 2020 | Q3 | 2020-02-29 | 2020-08-20 | 2020-09-30 |  | Y | BRUNSWICK 110350070 | 2144 |  | PRE
35061212 |  | 2021 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Scoped | CONS | 9973 | 0 | 9445 | 9445 | 1.7888 | 0 | 0 | 9445 | 1.7888 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-10-30 |  | Y | 2020-10-30 | 2020-07-31 | 2020-10-30 | 2020-05-29 | 2020-05-29 | Yes | 2020-09-11 | [2020 Const. Sched] 09/09: ADE rtn 2nd RD corrections to CO; BCF submitted for RD 3rd rvw; ADE rtn 3rd RD corrections to CO; EST - intents status are "SENT TO CONSTRUCTION" in JPA Software, proceed with edit? 09/08: BCF submitted REDESIGN for 2nd ADE rvw 09/03: ADE rtn corrections to CO 09/01: BCF submittited REDESIGN for ADE rvw; revised design 08/31: Land had already met with the property owner, and now that we are removing the two intercept poles there is no need to revisit this issue - move forward with the approval of the re-design 08/31: GC limited resouces for anchor placement with customer.08/27: eliminate Location 157 and 158 08/25: [Redesign] Designing around tree interference;pole on the property will require heavy angle guying; EST scope change requested, **************** 06/26: APPROVED - INTO PEND 06/23: Status - Waiting on Planner for approvals (trgt - 6/26); Final corrections provided to CO for pre-completion- EST applied corrections 06/19: ADE - Concur rejected - missing docs in SAP; EST uploaded Calcs, Zip file 109 EST could not see in SAP after several attempts (seeking guidence); Per ADE - Do not Concur this job until the Dist. Eng. approves the CMCS; EST - Loc 109 zip now in SAP 06/18: REJECTED - Correction still not made on JP Intent. Phone Co. will not accept; EST/ADE coordinating on standards & applying corrections; EST submitted for 5th ADE rvw [2]; ADE approved for routing; EST routed; 06/17: ADe rtn 4th corrections to CO; EST submitted 5th ADE rvw (final) 06/16: Est Target sub (6/16) - EST submitted for 4th ADE rvw 06/13: ADE rtn 3rd corrections to CO 06/12: BCF submitted for 3rd ADE rvw 06/09: EST status (6/12) - 06/06: EST redesign; ADE redlines/EST advised redesign necessary, ADE advised for redesign to happen, Land will need to obtain easement for the redesign of the Pri. OH 06/03: ADE rtn 2rd correctionst to CO 06/02: ADE soft target (6/05) 05/29: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready] 05/26: On Track 05/19 - 05/05: Pending clarifications from PGE on standards 04/28:EST Status (5/8); Clarifying pole height and framing informations; EST/ADE coordinating; To be reviewed on PGE side. 04/23: EOD shift - progress RISK 04/21: On Track - WebEx sched with ADE to address comments 04/14: EST to firm sub date (4/24); EST/ADE working on directions for various items 03/31: EST firm up date (4/04)??; BCF unable to join/Tech issues. 03/25: ADE rtn 1st [3] corrections to CO 03/24 - 03/17 ADE Status?? (Due) 03/03: BCF submitted for 1st rvw [3] 03/03: EST implementing Export program for formatting; Sub this week 02/24 ADE Rejected 1st submittal - Push (~1wk) all information for the field note guideline are not provided and DO-Field Note incomplete. 02/21: BCF submitted for 1st ADE rvw [2] 02/18: EST working on export means to put into requested format; review final w/ Shaylin (target this week) 02/11: EST to review and firm up target. PGE offline rvw of ADE request and format implementation. 02/10: ADE Rejected 1st submittal - field note guideline are not followed and DO-Field Note not use. Cannot review this job with the filed notes provided 02/05: ADE assigned (Walter) 1/17: BCF submitted for 1st ADE rvw 01/07: On Track 12/17: Anticipate Weather impacts. -Visited sight, Fielding scheduled to start in following weeks 12/10: Prioritize for Q2 Const. 12/02: Veg scheduled to be completed 2nd wk Dec 11/12 <-- 10/17: Push 2mnth - Jeff Kringler spoke with James. He's going to review the locations mid November and provide a timeframe to complete the veg work. vegetation team is tentatively scheduled to being patrol and trimming on the Brunswick tap line so Estimating can access our facilities for the Reconductoring design on 11/18/19 10/15: Status quo 10/08: Veg management issues (no line of site/access issues) - need line cleared for Estimating to proceed - Est team to initiate communication with Veg Mgmnt; (initial 4wk push) to address/coordinate resolution 10/01 <-- 9/24: LIDAR - meeting to be scheduled w/ contractor, 'pilot' utilization 9/17: Need to push - reviewing LIDAR opportunity - meeting scheduled. 9/10 <-- 9/03: No Change at this time - Based on fielding hardships, reviewing for reprioritization 8/21: Condition summary provided by BCF - RISK identified potential need to push & shift another project forward 8/20: Pre-field inspections - BCF to provide list of issues impacting ability to field through normal conventions 8/6 <-- 7/30: Est Fielding planned to start wk of 9/5 - for prelim assessment of conditions and scheduling impacts 7/25: Approved - Vendor provided 1st Submittal 'Tentative' Target dates - RISK, anticipated Fielding difficulties will lead to date push 7/23: RFI - Alternate Vendor, to bring in dates 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued |  |  |  | 2020 - RD- M10 [R2020_137] | Iss_RD1.3_Rdsn - EST Implementing Redesign Corrections | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-20 | 2020-04-20 | Full |  |  | CIF Submitted 3/6/2020 | Full |  |  | Yes | 2020-12-20 |  |  |  | 2020-08-19 | Y | 2020-07-13 |  |  | Starting 6/1/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7888 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-07-19 | Yes | COMP | 2020-08-20 | 2021-04-28 08:00 |  | 2021-07-20 17:00 | 2020-07-06 | 2020-08-15 06:00 | 2021-03-19 16:00 |  | 2020-07-28 | Yes | Shovel Ready |  | 3890027.8 | 3486942.7 | 2161081.9 | 4913095 | 1023067.2 | 1888364.7 | 89.63% | 1614926.5 | 386736.6 | 2001663.1 |  | 1949291.4194 |  | 50 |  | Will be underway | [7 empty] | Nevada City | Nevada | 0 | 0 | E.5015568.01 |  |  | 2020-137 | 2020 | Q3 | 2020-03-31 | 2020-06-14 | 2020-07-26 |  | Y | BRUNSWICK 110350070 | 2144 |  | PRE |  | 2021-02-25 13:06
35061213 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  |  | FICL | 10043 | 0 | 7099 | 7099 | 1.3445 | 7099 | 1.3445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 |  |  | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-11-04 | 2019-11-04 | Yes | 2020-05-11 | 03/02: INTO PEND02/13: still shows a high validation error in EES that prevents me from routing for approval; submitted a mapping correction to ED WebViewer; told they cannot correct issues related to PLDBIDs 02/05: PIKE submitted final corrections02/03: Final corrections rtn to CO01/30: EES validation error resolved01/28: Another ticket submitted 1/24 - reappearance of error01/21: EN to forward communications to for assistance. IT shifting back and forth between grps for support.01/14: Push 1wk EOD: EST SPPT in progress01/06: EES validations issues - escalating to EST support to resolve.12/17: QC - inconsistencies with sequences - Coordinated with ADE, refielding: Routing by EOD 12/1812/06: ADE rtn 4th corrections to contractor - apply and route.12/05: PIKE submitted for 4th ADE rvw12/05:ADE rtn 3rd corrections to contractor11/20: PIKE submitted for 3rd ADE rvw11/19: On Track (or earlier) - ADE heading to vaca11/15: ADE rtn 2nd corrections to contractor11/12: Follow up with ADE on target11/04: PIKE submitted for 2nd ADE rvw10/29: On Track for 11/01; clearing up comment (Pole/High wind load...) w/ .10/22: Push 1 week - Est workload/prioritization10/18: ADE returned 1st corrections to contractor10/09: ADE assigned () - push 1wk for rvw duration (2wk)10/08: ADE to be assigned10/01: PIKE to forward submittal to - To confirm ADE and availabilities9/23: PIKE submitted for 1st ADE rvw8/27 - 9/17: On track8/20: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities8/13: PIKE communicated potential pressures on 1st ADE submittal targets, due to computer availabilities and technical issues: (IE: Token malfunctions; SAP Access issues) - working through issues with TSC on case by case basis 7/23 - 8/6: On Track for 9/67/19: Vendor Provided 1st ADE Sub dates7/16: Vendor Request for 1st ADE Submittal7/15: Sub Order issued[Version 8] |  |  |  | 2020 - Q1- M2 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes |  |  | Drawings submitted 1/7/2020 & 1/14/2020 |  | 2020-06-17 | Y | 2020-05-01 |  |  | Started | [7 empty] | 0 | 0 | 7099 | 1.3445 | 0 | 0 | 1.3445 | 0 | 1.3445 | 0 | 1.4511 | 0.10663 | 0 | 1.3445 |  | Keep | 2020-05-01 | Yes | N/A | 2020-05-18 | 2020-08-14 | Yes | 2020-08-14 | 2020-05-16 | 2020-07-24 | 2020-07-24 | 2020-08-14 |  | Yes | Shovel Ready |  | 4177343.8 | 2136212 | -212915 | 6076529 | 1899185.2 |  | 51.13% | 2349127 |  |  |  | 1588843.4089 |  | 51 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.01 |  |  | 2020-138 | 2020 | Q3 | 2020-02-29 | 2020-06-01 | 2020-07-24 |  | Y | BRUNSWICK 110350070 | 7
35061709 |  |  |  | SILVERADO 2104 RECONDUCTOR PROJECT |  |  | DOCC | 8800 | 0 | 8003 | 8003 | 1.5157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-15 |  |  | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-03-27 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Undergrounding redesign in process. Once completed will provide to ENV team / Need laydown | Full |  |  | Yes |  |  | Approved through May 2020 |  | 1980-01-01 | Y | [11 empty] | 8003 | 1.5157 | 0 | 0 | 0 | 0 | 1.5157 | 0 | 1.5157 | 0 | 1.6388 | 0.12311 | 0 | 1.5157 |  |  | 2019-08-15 |  | N/A | 2019-10-23 | 2019-12-14 | Yes | 2019-12-14 | 2019-06-01 |  |  | 2019-08-22 | [17 empty] | 35 | [9 empty] | Angwin | Napa | 38.5567 | -122.4932 | 35061709 |  |  |  | 2019 | Q2 | [5 empty] | SILVERADO 2104563322 | 295
35061811 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 100000 |  |  | 100000 | 0 |  |  | 7209 | [13 empty] | Remove |  |  |  | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y | EL DORADO PH 210219542 | 41
35062127 |  |  |  | *FT-OFAC_IDLE_REMV - 5000 HWY 49COOL |  |  | FICL |  | 0 | 6011 | 6011 | 1.1384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 6011 | 1.1384 | 0 | 0 | 0 | 0 | 1.1384 | 0 | 1.1384 | 0 | 1.1384 | 0 | 0 | 1.1384 |  |  |  |  | N/A | [7 empty] | 2019-09-15 | [29 empty] | 38.85 | -120.9828
35062374 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Scoped | UNSE |  | 8106 | 0 | 8106 | 1.5352 | 0 | 0 | 0 | 0 | 8106 | 1.5352 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-31 | 2021-04-14 | N | 2021-05-31 | [6 empty] | [Basemap; UG] 02/24: [EOD PUSH] UG – pending basemaps (4/12 bm) |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-04-12 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5352 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 220000 | 4904599.4 | 153434.85 | 220000 | 0 |  | 2229% | 52793 |  |  |  | 3194705.7528 |  |  |  | Site survey requested 3/9/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-11 16:34
35062375 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Scoped | UNSE |  | 5860 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-10-21 17:00 | 2021-02-22 | Y | 2021-05-31 | [6 empty] | [Basemap; UG] 02/24: [EOD PUSH] UG – pending basemaps (4/12 bm) |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-04-12 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-21 17:00 |  | INPR | 2022-01-17 08:00 | 2022-04-25 17:00 |  | 2022-06-24 17:00 |  | 2021-05-21 07:00 | 2021-05-21 16:00 | [8 empty] | 1 |  |  |  | 32460.3 | [15 empty] | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-11 16:26
35062376 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Scoped | UNSE |  | 22892 | 0 | 22892 | 4.3356 | 0 | 0 | 0 | 0 | 22892 | 4.3356 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-04-21 | N | [25 empty] | In Progress | 2021-04-19 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 220000 | 8027019.4 | 364360.62 | 220000 | 0 |  | 3649% | 23689.6 |  |  |  | 1851418.0688 |  |  |  | Site survey requested 2/25/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | Y |  | 159 | 35062376 | PRE |  | 2021-03-11 10:00
35064793 |  |  |  | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  |  | FICL | 17020 | 0 | 12142 | 12142 | 2.2996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 08W | SH | 2019-06-25 |  |  | 2019-02-25 |  | 2019-02-25 |  |  | Yes | 2019-08-20 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | ERTC released, need land task completion. Need ERTC call | Full |  |  | Yes |  |  | Permit expires 10/12 |  | 1980-01-01 | Y | [11 empty] | 12142 | 2.2996 | 0 | 0 | 0 | 0 | 2.2996 | 0 | 2.2996 | 0 | 2.2996 | 0 | 0 | 2.2996 |  |  | 2019-06-25 |  | N/A | 2019-07-12 08:00 | 2019-08-26 | Yes | 2019-08-26 17:00 | 2019-08-20 |  |  | 2019-08-26 | [17 empty] | 75.6444 | [9 empty] | Lompoc | Santa Barbara | 34.6451 | -120.5194 | E.5015545.01 |  |  |  | 2019 | Q2 | [5 empty] | CABRILLO 1104Y22 | 2531
35065058 |  |  |  | STS-POLE_IDLE_REMV - BETWEEN 1860 & 1850 |  |  | CLSD |  | 0 | 530 | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF |  |  |  |  | 2019-05-10 | [55 empty] | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0 | 0.10038 |  |  |  |  | N/A | [7 empty] | 2019-08-23 | [29 empty] | 38.6055 | -120.8122
35066622 |  |  |  | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  |  | UNSE | 10900 | 0 | 10900 | 10900 | 2.0644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0644 |  |  | LP | 08W |  | 2022-09-06 17:00 | [15 empty] | Yes | [21 empty] | L&EM needs drawing | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0644 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-09-06 17:00 |  | INPR | 2022-10-20 08:00 | 2022-12-15 17:00 |  | 2022-12-29 17:00 | [21 empty] | 48.4444 |  | Tline on PM 31429487 | [5 empty] | Remove |  | San Luis Obispo | San Luis Obispo | 35.2869 | -120.7197 | E.5015594.01 |  |  |  | 999 | [6 empty] | FOOTHILL 1101CB | 668
35066689 |  |  |  | OCLH STS-OFAC_IDLE_REMV-16275 HWY 88 |  |  | CLSD |  | 0 | 103 | 103 | 0.019508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF |  |  |  |  | 2019-01-17 | [55 empty] | 103 | 0.019508 | 0 | 0 | 0 | 0 | 0.019508 | 0 | 0.019508 | 0 | 0.019508 | 0 | 0 | 0.019508 |  |  |  |  | N/A | [7 empty] | 2019-04-29 | [29 empty] | 38.3643 | -120.7245
35066745 |  |  |  | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 |  |  | CLSD | 9160 | 0 | 8900 | 8900 | 1.6856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-05-25 |  |  | 2019-05-25 | 2019-04-12 | 2019-05-25 |  |  | Yes | 2019-06-05 | 5/25: COMPLETED6/5: minor corrections needed to be made after approval. moved back into ESTS for CAL to complete by 6/5. Job was in PEND, and will be in PEND again by 6/76/12: Approved and in PEND Status |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Poles 1 - 17 are in DWR. SSSP provided. Partial ERTC released 7/17/19 | Full |  |  | Yes |  |  | Not required - See long text 2/20 |  | 1980-01-01 | Y | [11 empty] | 8900 | 1.6856 | 0 | 0 | 0 | 0 | 1.6856 | 0 | 1.6856 | 0 | 1.6856 | 0 | 0 | 1.6856 |  |  |  |  | N/A |  |  |  |  | 2019-07-16 |  |  | 2019-11-21 |  |  |  |  | 2769654 |  |  | 3916190 | 1146536 |  |  | 3167514.9 | [5 empty] | 36 | [9 empty] | Corning | Tehama | 0 | 0 | 35066745 |  |  |  | 2019 | Q4 |  |  |  |  | Y | BIG BEND 1102CB | 1094
35067619 |  |  |  | CWSP - MONTE RIO 1112 - LR 120 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Monte Rio | Sonoma | 0 | 0 | [11 empty] | MONTE RIO 1112120 | 54
35072146 |  |  |  | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  |  | DOCC | 3654 | 0 | 3684 | 3684 | 0.69773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-26 |  |  | 2019-06-12 |  | 2019-06-12 |  |  | Yes | 2019-08-16 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | estimation received. Currently under review | Full |  |  | Yes | 2020-12-31 |  | Submitted Permit Req & Dwg on 6/25. Permit App sent on 7/9/2019 Napa Co approved, St. Helena pending as of 7/23 |  | 1980-01-01 | Y | [11 empty] | 3684 | 0.69773 | 0 | 0 | 0 | 0 | 0.69773 | 0 | 0.69773 | 0 | 0.69773 | 0 | 0 | 0.69773 |  |  | 2019-06-26 |  | N/A | 2019-11-15 08:00 | 2019-12-17 | Yes | 2019-12-17 | 2019-08-28 |  |  | 2019-12-17 |  |  |  |  | 2410000.1 | 2228422.6 |  | 2410000 | -0.1 |  | 92.46% | 2112523 |  |  |  | 3193830.4365 |  | 18 | [9 empty] | Saint Helena | Napa | 38.5229 | -122.5312 | E.5014317.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2105658898 | 104
35072147 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  |  | ESTS | 7868 | 7868 | 0 | 7868 | 1.4902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4902 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [5 empty] | No | [16 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4902 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 350000 |  |  | 350000 | 0 | 132076.3 |  | 217281.6 | 642.1 | 217923.7 |  |  |  | 40 |  | 6/21 - next week will have additional PM numbers to add tohe list for new segments | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 37.2159 | -121.9884 | E.5014319.01 | ML |  | 2021-139 | 2021 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35072360 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  |  | CONS | 5305 | 0 | 5541 | 5541 | 1.0494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0494 |  |  | ST | 08W | SH | 2020-10-13 |  |  | 2020-05-19 | 2020-06-30 | 2020-05-19 | 2020-02-21 | 2020-02-21 | Yes | 2020-05-19 | 05/19: APPROVED - INTO PEND05/12: EST routed - waiting for approval05/06: Est Status??04/29 EST target sub (5/5)04/27: CAL submitted for 6th ADE rvw; ADE rtn 6th corrections to CO04/24: ADE rtn 5th corrections to CO - request EST to complete and send for concur04/16: CAL submitted for 5th ADE rvw04/08: EST firm up sub date (04/22)04/06: ADE rtn 4th corrections to CO04/01: ADE target date (4/5)??03/31: CAL submitted for 4th ADE rvw03/25: EST to firm up sub??03/24: ADE rtn 3rd corrections to CO03/18: CAL submitted for 3rd ADE rvw03/18: With PE for rvw - sub target today; upload of docs03/11: Firmed up sub date to 3/1703/04: Walk down scheduled (03/05) - EST req Change Order (03/03)03/02: ADE rtn 2nd corrections to CO02/26: ADE to firm up date??02/21: CAL submitted for 1st ADE rwv02/19: Push 1/wk - In PE review; Couple ADE changes rcv'd this week, designer applied02/12: Field driven changes - Pushed to 2/1402/05 <-- 01/29: Advise EST rvw inflight; firmed 2nd sub target01/22: ADE rtn 1st corrections to CO12/20: ADE assigned ( [REDACTED] )12/04 <-- 10/16: ADE to be assigned (waiting on 2020 priority list); 11/20 ADE assignment 1mnth push10/04: CAL submitted for 1st ADE rvw9/25: Target 1st Submittal 11/01 ON TRACK8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q2- M5 [R139] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  | 2020-07-17 | Yes |  |  |  | 2020-05-01 | 2020-05-01 |  |  |  |  | Full | 2020-05-01 | 2020-05-01 | Full |  |  | CIF submitted 3/17/2020 | Full |  | 2020-10-13 | Yes |  |  | Check received - Waiting on precon |  | 2020-08-14 | Y | 2020-07-02 | 2020-08-25 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0494 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-23 17:00 | Yes | COMP | 2022-01-11 11:00 | 2022-02-25 11:00 |  | 2022-03-29 11:00 | 2020-07-17 |  |  |  | 2020-08-10 | Yes | Shovel Ready |  | 1932058.6 | 1727735.6 |  | 2583069 | 651010.4 |  | 89.42% | 736038.5 |  |  |  | 1646353.36 |  | 26 |  | Veg Complete Work not started | [5 empty] | Remove |  | Arnold | Calaveras | 38.3018 | -120.277 | E.5015236.01 | TL |  | 2020-139 | 2020 | Q3 | 2020-05-31 | 2020-08-14 | 2020-09-12 |  | Y | SALT SPRINGS 21023142 | 2659 |  | PRE |  | 2021-03-01 20:30
35072361 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  |  | ADER | 7703 | 0 | 7703 | 7703 | 1.4589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4589 | 7709 | 1.46 | ST | 08W | SH | 2022-01-24 17:00 |  |  | 2020-12-31 | 2020-10-31 | 2020-12-31 | 2020-04-19 | 2020-04-19 | Yes |  | [Composite to Wood - Sept List]11/10 - 10/14: ADE in rvw10/13: CAL submitted for 4th ADE rvw [2] - Conversions09/23: In review - Sub target (9/25)09/09: Conversion Target (9/18)09/03: ADE rtn 4th corrections to CO09/02: Conversion 1st sub TBD08/26:ADE in rvw; Priority based08/21: Rescheduled permitting - submit when finalized/approved08/19: PUSH - ADE advised approx 2wk required due to condition of estimate, to complete rvw; CAL permit will need to be resubmitted.08/12 - 08/05: ADE in rvw - priority based {AUG EOD} - ADE vaca??08/04: ADE in rvw; EST/ADE working on some rvw specifics07/29: CAL submitted for 4th ADE rvw7/29: EST target sub 7/24; (7/31); Change Order request from CAL07/15: ADE in rvw; should incorporate land changes as well.07/13: EST/ADE working through some Q&A; Land changes07/08 - 06/24: ADE rvw soft target (6/29) - priority based (push) (7/17),(7/24)06/23: CAL submitted for 3rd ADE rvw06/17: EST target sub (6/19)06/10 - 06/03: EST target sub (6/12)05/27: ADE rtn 2nd corrections to CO; very difficult estimate to check. Lots of issues05/20- 04/29: ADE working priority PMs04/19: CAL submitted for 2nd ADE rvw04/15 - 04/18: EST sub date set (4/22)04/01: On Track 4/1703/24: Push - OCalc Versions - Per [REDACTED] .; will have a solution very soon for the O’calc issue as I’m awaiting the resolution from our 06/17: EST push Target sub (06/19)06/19O’calc Team. I’m hoping we can send you the old version of O’calc so the Stamped version and the uploaded version will match in SAP03/23: ADE rtn 1st corrections to CO - This is a very low level review. I have concentrated on the sketches and a few other thing; have not gone through job instructions, JP form, OCalc or field notes because I want these items below corrected before we move forward03/19: ADE assigned (Donald)03/12 - 11/04: ADE assignment push10/23: CAL update uploaded UG payment schedule10/09: ADE to be assigned10/01: CAL submitted for 1st ADE rvw9/25: Target 1st submittal pulled into 9/278/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q4- M12 [R2021_36] | R4.2 - ADE Review in Progress | No | Comp | 25 | 50 | [6 empty] | 2020-12-03 | 2020-12-03 | [5 empty] | 2020-12-03 | 2020-12-03 |  |  |  | ** Caltrans DSDD - Pilot Project - Caltrans permit required due 12/2/2020, can do PERTC by 9/15 (assuming EOD of 8/30), if requested. Preliminary environmental Reviews complete. |  |  | 2020-09-16 |  |  |  | TCP Requested 7/8 |  | 2021-02-13 |  | 2021-01-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4589 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-24 17:00 |  | INPR | 2022-06-06 11:00 | 2022-08-15 11:00 |  | 2022-09-14 11:00 | [8 empty] | 500000 | 2712758.3 |  | 500000 | 0 |  | 542.6% | 180453.1 |  |  |  | 1859452.6579 |  | 40 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3018 | -120.277 | E.5015235.01 | ML |  | 2021-036 | 2021 | 2020 Reserve | 2020-07-31 | 2020-11-13 | 2020-12-18 |  | Y | SALT SPRINGS 21023142 | 8
35072362 |  |  |  | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 |  |  | CLSD | 15000 | 0 | 14292 | 14292 | 2.7068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-30 |  |  | 2019-08-30 | 2019-08-20 | 2019-08-30 |  |  | Yes | 2019-08-30 | 5/22: 1st ADE submittal by 6/146/12: majority of the work have been completed for 1st submittal. A small portion of the job is inaccessible due to river depth and flow - will push 1st submittal6/19: still access issue with the river - may delay to late fall7/3: QUES to follow up on access issues7/16: QUES Fielded - Submittal planned for 7/197/22: 1st ADE Submitted for review7/31: Awaiting ADE Review/corrections - [REDACTED] ; 7/29 1st ADE review completed and returned to Vendor8/6: Contractor working through correction items with ADE8/7: Corrections returned to contractor8/20: 2nd ADE Submitted for review [PRELIM DWG ready]8/20: 2nd ADE corrections rtn to contractor8/23 QUES submitted for 3rd ADE rvw9/04: IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Annual |  | 1980-01-01 | Y | [11 empty] | 14292 | 2.7068 | 0 | 0 | 0 | 0 | 2.7068 | 0 | 2.7068 | 0 | 2.7068 | 0 | 3.4451e-16 | 2.7068 |  |  |  |  | N/A |  |  |  |  | 2019-09-05 |  |  | 2019-12-21 | [17 empty] | 45 | [9 empty] | Ferndale | Humboldt | 40.4516 | -124.2697 | E.5014735.01 |  |  |  | 2019 | Q4 | [5 empty] | EEL RIVER 11024814 | 936
35072720 |  |  |  | RPL OH WIRE ON GABILN 1101 17-0077248 |  |  | CLSD | 11795 | 0 | 11745 | 11745 | 2.2244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-06-20 |  |  | 2019-06-20 |  | 2019-06-20 |  |  | Yes | 2019-06-20 | 2/25: QUES working on Job, fielding this week3/4: Fielding completed last week3/7: ADE assigned3/11: QUES working on Job package3/20 - 4/3: 4/11 1st ADE submittal date - on track4/8: On track for 1st ADE submittal on 4/114/11: 1st ADE submitted - [REDACTED] to review5/1: [REDACTED] to send corrections any day5/8: waiting on 1st corrections- 1st corrections estimated by 5/105/15: 1st correction 5/10. Job needs to be refielded due 200' interset spec. QUES to follow up on 2nd submittal5/22: QUES to follow up on 2nd submittal - waiting for [REDACTED] to approve locations for interset5/29: Recevied answer on refield on 5/24, estimator will start working on today5/31: submitted6/4: 2nd corrections sent by [REDACTED] /5: EDRS ready6/10: Rerouted6/19: [REDACTED] to approve EDRS reroute6/20: APPROVED |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | Bio review of 4 poles in water way. [REDACTED] will be talking to [REDACTED] to review. Walkdown 7/23/19. [REDACTED] to review | Full |  |  | Yes |  |  | Annual permit |  | 1980-01-01 | Y | [11 empty] | 11745 | 2.2244 | 0 | 0 | 0 | 0 | 2.2244 | 0 | 2.2244 | 0 | 2.2244 | 0 | 0 | 2.2244 |  |  |  |  | N/A |  |  |  |  | 2019-08-30 |  |  | 2020-01-14 |  |  |  |  | 1547724 |  |  | 1869000 | 321276 |  |  | 1076838.7 | [5 empty] | 61 | [9 empty] | Salinas | Monterey | 36.6615 | -121.5473 | E.5015593.01 |  |  |  | 2019 | Q4 |  |  |  |  | Y | GABILAN 11013090 | 747
35073525 |  | 2020 |  | BUCOCAMP - 6265 AZALEA LN PARADISE |  |  | CLSD |  | 0 | 2027 | 2027 | 0.3839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 2027 | 0.3839 | 0 | 0 | 0 | 0 | 0.3839 | 0 | 0.40284 | 0 | 0.40284 | 0 | -0.018939 | 0.40284 |  |  |  |  | N/A | [7 empty] | 2019-03-14 | [29 empty] | 39.7719 | -121.6019 |  |  |  |  | 2019
35075103 |  | 2021 |  | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 |  | Scoped | DCNL |  | 0 | 3115.2 | 3115.2 | 0.59 | 0 | 0 | 3362 | 0.63674 | 0 | 0 | 0 | 0 | -0.046742 | 3362 | 0.63674 | ST | 08W | SH | 2021-04-13 | 2021-02-08 | Y | 2021-02-28 | 2021-02-28 | 2021-02-28 | [20 empty] | 2021-04-12 | 2021-04-12 | N/A |  |  |  | Full | 2021-04-12 | 2021-04-12 | [12 empty] | 2021-05-15 |  | 2021-04-13 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-29 17:00 |  | INPR | 2021-05-19 08:00 | 2021-06-29 17:00 |  | 2021-08-10 17:00 | [8 empty] | 299999.6 | 513283.3 | 490994.6 | 50000 | -249999.6 |  | 171.1% | 100556.7 |  |  |  | 869971.6949 | [5 empty] | Prioritized | [5 empty] | Murphys | Calaveras | 0 | 0 |  | TL | OH | [7 empty] | Y |  | 721 |  | WDDB |  | 2021-03-11 15:55
35076188 |  | 2020 |  | BUCOCAMP - 5275 SKYWAY PARADISE |  |  | CLSD |  | 0 | 229 | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0.043371 | 0 | 0.039205 | 0 | 0.039205 | 0 | 0.0041667 | 0.039205 |  |  |  |  | N/A | [7 empty] | 2019-05-27 | [29 empty] | 39.7477 | -121.6375 |  |  |  |  | 2019
35077252 |  | 2020 |  | BUCOCAMP - 1658 HUCKA LN PARADISE |  |  | CLSD |  | 0 | 563 | 563 | 0.10663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 563 | 0.10663 | 0 | 0 | 0 | 0 | 0.10663 | 0 | 0.10663 | 0 | 0.10663 | 0 | 0 | 0.10663 |  |  |  |  | N/A | [7 empty] | 2019-04-11 | [29 empty] | 39.7916 | -121.5854 |  |  |  |  | 2019
35077480 |  | 2020 |  | BUCOCAMP - 5220 FOSTER RD PARADISE |  |  | CLSD |  | 0 | 1165 | 1165 | 0.22064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1165 | 0.22064 | 0 | 0 | 0 | 0 | 0.22064 | 0 | 0.22064 | 0 | 0.22064 | 0 | 0 | 0.22064 |  |  |  |  | N/A | [7 empty] | 2019-03-30 | [29 empty] | 39.738 | -121.6306 |  |  |  |  | 2019
35077549 |  | 2020 |  | BUCOCAMP - 1797 STARK LN PARADISE |  |  | CLSD |  | 0 | 270 | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0.051136 | 0 | 0 | 0.051136 |  |  |  |  | N/A | [7 empty] | 2019-04-11 | [29 empty] | 39.7742 | -121.5764 |  |  |  |  | 2019
35078144 |  |  |  | STS-TRAN_IDLE_REMV - SIERRA NATIONAL FOR |  |  | CLSD |  | 0 | 450 | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 2AF | IF | [60 empty] | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0 | 0.085227 |  |  |  |  | N/A | [7 empty] | 2019-09-16 | [29 empty] | 37.0566 | -119.3751
35078217 |  |  |  | STS-COND_IDLE_REMV-2290 BANDERILLA DR |  |  | CLSD |  | 0 | 1211 | 1211 | 0.22936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.030682 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 1373 | 0.26004 | 0 | 0 | 0.26004 | -0.030682 | 0.26061 | 0 | 0.26061 | 0 | -0.00056818 | 0.26061 |  |  |  |  | N/A | [7 empty] | 2019-10-21 | [29 empty] | 37.6758 | -120.3562
35078728 |  |  |  | COND_IDLE_REMV-17351 TRINITY MOUNTAI |  |  | CLSD |  | 0 | 193 | 193 | 0.036553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 193 | 0.036553 | 0 | 0 | 0 | 0 | 0.036553 | 0 | 0.036553 | 0 | 0.036553 | 0 | 0 | 0.036553 |  |  |  |  | N/A | [7 empty] | 2019-08-30 | [29 empty] | 40.7906 | -122.6151
35078734 |  |  |  | COND_IDLE_REMV-16333 TRINITY MOUNTAI |  |  | CLSD |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0 | 0.063826 |  |  |  |  | N/A | [7 empty] | 2019-08-30 | [29 empty] | 40.7634 | -122.6102
35078758 |  |  |  | COND_IDLE_REMV-20508 HIGHWAY 116 *OCLH |  |  | FICL |  | 0 | 50 | 50 | 0.0094697 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00037879 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 52 | 0.0098485 | 0 | 0 | 0.0098485 | -0.00037879 | 0.0098485 | 0 | 0.0098485 | 0 | -1.3457e-18 | 0.0098485 |  | Keep |  |  | N/A | [7 empty] | 2020-02-11 | [27 empty] | Monte Rio | Sonoma | 38.4681 | -123.0125
35078820 |  | 2020 |  | BUCOCAMP - 820 COLLEGE HILL RD PARADISE |  |  | CLSD |  | 0 | 462 | 462 | 0.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 462 | 0.0875 | 0 | 0 | 0 | 0 | 0.0875 | 0 | 0.0875 | 0 | 0.0875 | 0 | -1.0766e-17 | 0.0875 |  |  |  |  | N/A | [7 empty] | 2019-04-10 | [29 empty] | 39.7509 | -121.6182 |  |  |  |  | 2019
35079380 |  |  |  | STS-POLE_IDLE_REMV-17425 BAKER RILEY |  |  | FICL |  | 0 | 1159 | 1159 | 0.21951 | 0 | 0 | 1159 | 0.21951 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF |  |  |  |  | 2019-10-07 | [55 empty] | 0 | 0 | 0 | 0 | 1159 | 0.21951 | 0.21951 | 0 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-07-29 | [29 empty] | 38.2738 | -120.562
35079416 |  |  |  | STS-COND_IDLE_REMV-3/P/N/3/P/E/O ROCKY C |  |  | FICL |  | 0 | 279 | 279 | 0.052841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.052841 |  |  | LP | 2AF | IF |  |  |  |  | 2020-05-08 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.052841 | 0 | 0 | 0.052841 | 0.052841 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-02-19 | [29 empty] | 35.4896 | -120.539
35079972 |  |  |  | STS-COND_IDLE_REMV-12655 RATTLESNAKE GUL |  |  | CLSD |  | 0 | 92 | 92 | 0.017424 | 92 | 0.017424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 92 | 0.017424 | 0 | 0 | 0.017424 | 0 | 0.017424 | 0 | 0.017424 | 0 | 0 | 0.017424 |  | Keep |  |  | N/A | [7 empty] | 2020-01-15 | [29 empty] | 38.0334 | -120.367
35080227 |  |  |  | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  |  | ADER |  | 0 | 1876 | 1876 | 0.3553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | [60 empty] | 1876 | 0.3553 | 0 | 0 | 0 | 0 | 0.3553 | 0 | 0.3553 | 0 | 0.3553 | 0 | 0 | 0.3553 |  |  |  |  | N/A |  |  |  |  | 2019-11-20 | [10 empty] | 178900 |  |  |  | 601811.5 | [15 empty] | Calistoga | Napa | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | CALISTOGA 1101734 | 882
35080391 |  | 2020 |  | BUCOCAMP - 6650 PENTZ RD PARADISE |  |  | CLSD |  | 0 | 1159 | 1159 | 0.21951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1159 | 0.21951 | 0 | 0 | 0 | 0 | 0.21951 | 0 | 0.21951 | 0 | 0.21951 | 0 | 0 | 0.21951 |  |  |  |  | N/A | [7 empty] | 2019-05-14 | [29 empty] | 39.7778 | -121.5799 |  |  |  |  | 2019
35081535 |  | 2020 |  | BUCOCAMP - 785 SECLUDED LN PARADIS*COMP* |  |  | CLSD |  | 0 | 556 | 556 | 0.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 556 | 0.1053 | 0 | 0 | 0 | 0 | 0.1053 | 0 | 0.074242 | 0 | 0.074242 | 0 | 0.031061 | 0.074242 |  |  |  |  | N/A | [5 empty] | 2019-09-30 | 2019-10-04 | 2019-09-23 | [29 empty] | 39.7755 | -121.6221 |  |  |  |  | 2019
35081665 |  | 2020 |  | BUCOCAMP - 732 WILLOW ST PARADISE |  |  | CLSD |  | 0 | 137 | 137 | 0.025947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 137 | 0.025947 | 0 | 0 | 0 | 0 | 0.025947 | 0 | 0.025947 | 0 | 0.025947 | 0 | 0 | 0.025947 |  |  |  |  | N/A | [7 empty] | 2019-04-23 | [29 empty] | 39.7572 | -121.6223 |  |  |  |  | 2019
35081674 |  | 2020 |  | BUCOCAMPT 5615 NEWLAND RD PARADISE*ILB |  |  | MAPP |  | 0 | 254 | 254 | 0.048106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 254 | 0.048106 | 0 | 0 | 0 | 0 | 0.048106 | 0 | 0.076136 | 0 | 0.076136 | 0 | -0.02803 | 0.076136 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-12-07 | [29 empty] | 39.7523 | -121.6026 |  |  |  |  | 2019
35081676 |  | 2020 |  | BUCOCAMP 5708 ROUND TREE DR PARADISE |  |  | CLSD |  | 0 | 504 | 504 | 0.095455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 504 | 0.095455 | 0 | 0 | 0 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0.095455 | 0 | 0 | 0.095455 |  |  |  |  | N/A | [7 empty] | 2019-06-18 | [27 empty] | Paradise | Butte | 39.7544 | -121.5962 |  |  |  |  | 2019
35081748 |  | 2020 | 220 Mile Plan | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 |  |  | CLSD | 1617 | 0 | 850 | 850 | 0.16098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2019-03-20 |  |  | 2019-03-20 |  | 2019-03-20 |  |  | Yes | 2019-05-28 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Partial ERTC released. Redwood tree conflict | Full |  |  | Yes |  |  | Sent follow up to PF re permit status. Site specific TCP requested. Caltrans - No Encroachment needed |  | 1980-01-01 | Y | [11 empty] | 850 | 0.16098 | 0 | 0 | 0 | 0 | 0.16098 | 0 | 0.16098 | 0 | 0.16098 | 0 | 0 | 0.16098 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-08-23 | 2020-02-18 | 2020-02-18 | 2020-02-19 |  | Yes | Shovel Ready |  | 632820 |  |  | 713114 | 80294 |  |  | 608138.6 | [5 empty] | 9 | [9 empty] | Aptos | Santa Cruz | 36.9734 | -121.9038 | 35081748 |  |  |  | 2020 | Q1 | 2019-03-20 | 2020-02-10 | 2020-02-28 |  | Y | ROB ROY 210538430 | 1439
35082172 |  | 2020 |  | BUCOCAMP 5150 S LIBBY RD PARADISE |  |  | CLSD |  | 0 | 860 | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0.16288 | 0 | 0.16288 | 0 | 0.16288 | 0 | 0 | 0.16288 |  |  |  |  | N/A | [7 empty] | 2019-04-22 | [27 empty] | Paradise | Butte | 39.7372 | -121.5938 |  |  |  |  | 2019
35083670 |  |  |  | STS-TRAN_IDLE_REMV-LOC 1-3/P/E & 1/P S/O |  |  | CLSD |  | 0 | 334 | 334 | 0.063258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05322 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 53 | 0.010038 | 0 | 0 | 0.010038 | 0.05322 | 0.0094697 | 0 | 0.0094697 | 0 | 0.00056818 | 0.0094697 |  |  |  |  | N/A | [7 empty] | 2020-02-06 | [29 empty] | 37.4453 | -120.0998
35083680 |  |  |  | STS-TRAN_IDLE_REMV-LOC #1, RADIAL TAP 4 |  |  | FICL |  | 0 | 391 | 391 | 0.074053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.015909 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 475 | 0.089962 | 0 | 0 | 0.089962 | -0.015909 | 0.086742 | 0 | 0.086742 | 0 | 0.0032197 | 0.086742 |  |  |  |  | N/A | [7 empty] | 2020-02-05 | [29 empty] | 37.9008 | -120.4153
35083685 |  |  |  | STS-POLE_IDLE_REMV-MERCED FALLS RD 1/P/S |  |  | CLSD |  | 0 | 1046 | 1046 | 0.19811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0081439 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 1003 | 0.18996 | 0 | 0 | 0.18996 | 0.0081439 | 0.19394 | 0 | 0.19394 | 0 | -0.0039773 | 0.19394 |  |  |  |  | N/A | [7 empty] | 2020-02-07 | [29 empty] | 37.6857 | 120.3246
35083689 |  |  |  | STS-TRAN_IDLE_REMV-LOC #8 8655 HUNTERS V |  |  | FICL |  | 0 | 354 | 354 | 0.067045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0011364 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 348 | 0.065909 | 0 | 0 | 0.065909 | 0.0011364 | 0.065909 | 0 | 0.065909 | 0 | -1.0766e-17 | 0.065909 |  |  |  |  | N/A | [7 empty] | 2020-03-13 | [29 empty] | 37.6153 | -120.2408
35083704 |  |  |  | STS-COND_IDLE_REMV-17715 HARVARD MINE RD |  |  | CLSD |  | 0 | 63 | 63 | 0.011932 | 63 | 0.011932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 63 | 0.011932 | 0 | 0 | 0.011932 | 0 | 0.011932 | 0 | 0.011932 | 0 | 0 | 0.011932 |  | Keep |  |  | N/A | [7 empty] | 2020-02-19 | [29 empty] | 37.9459 | -120.4305
35083721 |  |  |  | STS-COND_IDLE_REMV-8/10MI N/O BEAR TRAP |  |  | FICL |  | 0 | 80 | 80 | 0.015152 | 80 | 0.015152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 2AF | IF | [60 empty] | 0 | 0 | 80 | 0.015152 | 0 | 0 | 0.015152 | 0 | 0.015152 | 0 | 0.015152 | 0 | 0 | 0.015152 |  | Keep |  |  | N/A | [7 empty] | 2020-04-20 | [29 empty] | 34.8483 | -118.8649
35083727 |  |  |  | STS-POLE_IDLE_REMV-INDIAN PEAK RD |  |  | DOCC |  | 0 | 145 | 145 | 0.027462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 145 | 0.027462 | 0 | 0 | 0.027462 | 0 | 0.027462 | 0 | 0.027462 | 0 | 0 | 0.027462 |  |  |  |  | N/A | [37 empty] | 37.4414 | -119.8918
35083741 |  |  |  | STS-COND_IDLE_REMV-2120 S. HWY 49 |  |  | DOCC |  | 0 | 155 | 155 | 0.029356 | 155 | 0.029356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 155 | 0.029356 | 0 | 0 | 0.029356 | 0 | 0 | 0 | 0.029356 | 0.029356 | 0.029356 | 0 |  | Keep |  |  | N/A | [37 empty] | 37.4499 | -119.7492
35083742 |  |  |  | STS-COND_IDLE_REMV-56060 NORTH FORK RD ( |  |  | FICL |  | 0 | 155 | 155 | 0.029356 | 155 | 0.029356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 155 | 0.029356 | 0 | 0 | 0.029356 | 0 | 0 | 0 | 0.029356 | 0.029356 | 0.029356 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-02-28 | [29 empty] | 37.1789 | -119.6281
35083747 |  |  |  | STS-COND_IDLE_REMV-23736 SKY HARBOUR RD |  |  | CLSD |  | 0 | 50 | 50 | 0.0094697 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 2AF | IF | [60 empty] | 0 | 0 | 50 | 0.0094697 | 0 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0.0094697 |  | Keep |  |  | N/A | [7 empty] | 2020-02-12 | [29 empty] | 36.9907 | -119.6293
35083751 |  |  |  | STS-COND_IDLE_REMV-1355 TULE RD/FAMOSO L |  |  | UNSE |  | 0 | 600 | 600 | 0.11364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 2AF | IF | [60 empty] | 600 | 0.11364 | 0 | 0 | 0 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0.11364 | 0 | 0 | 0.11364 |  |  |  |  | N/A | [37 empty] | 35.6211 | -118.9583
35083765 |  |  |  | STS-COND_IDLE_REMV - 9711 DUBLIN CANYON |  |  | FICL |  | 0 | 60 | 60 | 0.011364 | 60 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0018939 |  |  | MI | 2AF | IF | [60 empty] | 0 | 0 | 50 | 0.0094697 | 0 | 0 | 0.0094697 | 0.0018939 | 0.0094697 | 0 | 0.0094697 | 0 | 0 | 0.0094697 |  | Keep |  |  | N/A | [7 empty] | 2020-03-13 | [27 empty] | Castro Valley | Alameda | 37.6984 | -121.9821
35083780 |  |  |  | STS-COND_IDLE_REMV-5088 TIPTOP RD |  |  | CLSD |  | 0 | 180 | 180 | 0.034091 | 180 | 0.034091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 180 | 0.034091 | 0 | 0 | 0.034091 | 0 | 0 | 0 | 0.034091 | 0.034091 | 0.034091 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-02-05 | [29 empty] | 37.4561 | -119.823
35083784 |  |  |  | STS-COND_IDLE_REMV-5811 E. WHITLOCK RD |  |  | FICL |  | 0 | 252 | 252 | 0.047727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022727 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 240 | 0.045455 | 0 | 0 | 0.045455 | 0.0022727 | 0.045455 | 0 | 0.045455 | 0 | 0 | 0.045455 |  |  |  |  | N/A | [7 empty] | 2020-02-25 | [29 empty] | 37.5441 | -119.9961
35083823 |  |  |  | OCLH STS-COND_IDLE_RMV-1 PLE S/OF D89103 |  |  | CLSD |  | 0 | 60 | 60 | 0.011364 | 60 | 0.011364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 2AF | IF | [60 empty] | 0 | 0 | 60 | 0.011364 | 0 | 0 | 0.011364 | 0 | 0.011364 | 0 | 0.011364 | 0 | 0 | 0.011364 |  | Keep |  |  | N/A | [7 empty] | 2020-02-15 | [29 empty] | 36.7245 | -119.2394
35083840 |  |  |  | OLCH STS-COND_IDLE_RMV-41524 ACORN |  |  | CLSD |  | 0 | 609 | 609 | 0.11534 | 609 | 0.11534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 2AF | IF | [60 empty] | 0 | 0 | 609 | 0.11534 | 0 | 0 | 0.11534 | 0 | 0.11534 | 0 | 0.11534 | 0 | 0 | 0.11534 |  | Keep |  |  | N/A | [7 empty] | 2020-02-06 | [29 empty] | 37.0943 | -119.4284
35083885 |  |  |  | STS-COND_IDLE_REMV-6/P/E OF C/OUTS 38296 |  |  | FICL |  | 0 | 238 | 238 | 0.045076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0013258 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 245 | 0.046402 | 0 | 0 | 0.046402 | -0.0013258 | 0.046402 | 0 | 0.046402 | 0 | 0 | 0.046402 |  |  |  |  | N/A | [7 empty] | 2020-08-03 | [29 empty] | 37.5252 | -120.3128
35083897 |  |  |  | STS-COND_IDLE_REMV-14403 LAS MORAS ST |  |  | DOCC |  | 0 | 276 | 276 | 0.052273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0022727 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 264 | 0.05 | 0 | 0 | 0.05 | 0.0022727 | 0.051136 | 0 | 0.051136 | 0 | -0.0011364 | 0.051136 |  |  |  |  | N/A | [7 empty] | 2020-06-12 | [29 empty] | 37.6847 | -120.3289
35083905 |  |  |  | STS-COND_IDLE_REMV-MARKER 1000 USONA RD |  |  | CLSD |  | 0 | 95 | 95 | 0.017992 | 95 | 0.017992 | 0 | 0 | 0 | 0 | 0 | 0 | -2.6914e-18 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 95 | 0.017992 | 0 | 0 | 0.017992 | -2.6914e-18 | 0 | 0 | 0.017992 | 0.017992 | 0.017992 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-02-11 | [29 empty] | 37.3921 | -119.8313
35085362 |  |  |  | ASAP REMV IDLE R/O 17020 ARMSTRON*AE |  |  | FICL |  | 0 | 264 | 264 | 0.05 | 264 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 264 | 0.05 | 0 | 0 | 0.05 | 0 | 0 | 0 |  | 0 | 0.05 | 0 |  |  |  |  | N/A | [7 empty] | 2020-07-17 | [27 empty] | Guerneville | Sonoma | 38.5542 | -123.0043
35085393 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1B |  |  | FICL | 2150 | 0 | 1871 | 1871 | 0.35436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-25 |  |  | 2019-06-25 |  | 2019-06-25 |  |  | Yes | 2019-06-25 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | estimation released last week 7/12 | Full |  |  | Yes | 2020-12-31 |  | expires 7/15/20 |  | 1980-01-01 | Y | [11 empty] | 1871 | 0.35436 | 0 | 0 | 0 | 0 | 0.35436 | 0 | 0.35436 | 0 | 0.35436 | 0 | 0 | 0.35436 |  |  |  |  | N/A |  |  |  |  | 2019-08-07 |  |  | 2019-10-17 |  |  |  |  | 1299999.5 |  |  | 1300000 | 0.5 |  |  | 1239931.9 | [5 empty] | 11 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.02 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2104722 | 160
35085532 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1C |  |  | FICL | 6000 | 0 | 5948 | 5948 | 1.1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-06-24 |  |  | 2019-06-10 |  | 2019-06-10 |  |  | Yes | 2019-07-17 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | ERTC released | Full |  |  | Yes | 2020-12-31 |  | expires 7/15/20 |  | 1980-01-01 | Y | [11 empty] | 5948 | 1.1265 | 0 | 0 | 0 | 0 | 1.1265 | 0 | 1.1265 | 0 | 1.1265 | 0 | 0 | 1.1265 |  |  | 2019-06-24 |  | N/A | 2019-09-13 | 2020-01-15 | Yes | 2020-01-15 17:00 | 2019-07-27 |  |  | 2020-01-15 |  |  |  |  | 2099999.8 |  |  | 2100000 | 0.2 |  |  | 2033156.3 | [5 empty] | 30 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.03 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2104722 | 160
35085533 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1D |  |  | FICL | 4400 | 0 | 5365 | 5365 | 1.0161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-09-10 |  |  | 2019-09-10 |  | 2019-09-10 |  |  | Yes | 2019-09-06 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Drawing received | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 5365 | 1.0161 | 0 | 0 | 0 | 0 | 1.0161 | 0 | 1.0161 | 0 | 1.0161 | 0 | 0 | 1.0161 |  |  | 2019-08-21 |  | N/A | 2019-09-23 | 2019-10-08 | Yes | 2019-10-08 | 2019-09-10 |  |  | 2019-10-08 |  |  |  |  | 2100000 |  |  | 2100000 | 0 |  |  | 2014171.4 | [5 empty] | 22 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.04 |  |  |  | 2019 | Q4 |  |  |  |  | Y | SILVERADO 2104722 | 160
35085534 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1E |  |  | DOCC | 4048 | 0 | 4191 | 4191 | 0.79375 | 3823 | 0.72405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-16 |  |  | 2019-08-16 |  | 2019-08-16 |  |  | Yes | 2019-08-16 | [5 empty] | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Drawings received 8/12 | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 368 | 0.069697 | 3823 | 0.72405 | 0 | 0 | 0.79375 | 0 | 0.79375 | 0 | 0.79375 | 0 | 0 | 0.79375 |  | Keep | 2019-08-14 | Yes | N/A | 2019-11-20 | 2020-05-01 | Yes | 2020-05-01 | 2019-09-27 | 2019-11-20 | 2020-02-20 | 2020-05-01 |  | Yes | Shovel Ready |  | 2118489.8 |  |  | 2126590 | 8100.2 |  |  | 1679560.4 | [5 empty] | 21 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.05 |  |  |  | 2020 | Q1 | 2019-08-16 | 2020-01-02 | 2020-01-26 |  | Y | SILVERADO 2104722 | 160
35085535 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1F |  |  | DOCC | 8793 | 0 | 8793 | 8793 | 1.6653 | 8793 | 1.6653 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-01 |  |  | 2019-08-01 |  | 2019-08-01 |  |  | Yes | 2019-08-01 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Drawing to be sent on 7/30/19 | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 8793 | 1.6653 | 0 | 0 | 1.6653 | 0 | 1.6653 | 0 | 1.6653 | 0 | 0 | 1.6653 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-10-04 | 2020-04-30 | 2020-04-30 | 2020-05-01 |  | Yes | Shovel Ready |  | 2963631.1 |  |  | 2979682 | 16050.9 |  |  | 2503031.7 | [5 empty] | 44 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.06 |  |  |  | 2020 | Q1 | 2019-08-01 | 2020-01-02 | 2020-02-09 |  | Y | SILVERADO 2104722 | 160
35085536 |  |  |  | CWSP - SILVERADO 2104 - LR722 PH 1G |  |  | DOCC | 4850 | 0 | 7010 | 7010 | 1.3277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-09-02 |  |  | 2019-08-13 |  | 2019-08-13 |  |  | Yes | 2019-08-13 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  | was submitted to Napa County on 8/12/19, should be approved by 9/12/19 |  | 1980-01-01 | Y | [11 empty] | 7010 | 1.3277 | 0 | 0 | 0 | 0 | 1.3277 | 0 | 1.3277 | 0 | 1.3277 | 0 | 0 | 1.3277 |  |  | 2019-09-02 |  | N/A | 2019-10-14 | 2019-12-09 | Yes | 2019-12-09 | 2019-09-20 |  |  | 2019-12-09 |  |  |  |  | 1949999.6 |  |  | 1950000 | 0.4 |  |  | 1863426.2 | [5 empty] | 25 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.07 |  |  |  | 2019 | Q4 |  |  |  |  | Y | SILVERADO 2104722 | 160
35085537 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104 - LR722 PH 1H |  |  | DOCC | 4053 | 0 | 3752 | 3752 | 0.71061 | 628 | 0.11894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-09-02 |  |  | 2019-07-09 |  | 2019-07-09 |  |  | Yes | 2019-09-05 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 7/23 - Dwg received currently being reviewed - [REDACTED] to complete land task | Full |  |  | Yes | 2020-12-31 |  | expires 7/15/20 |  | 1980-01-01 | Y | [11 empty] | 3124 | 0.59167 | 628 | 0.11894 | 0 | 0 | 0.71061 | 0 | 0.71061 | 0 | 0.71061 | 0 | 0 | 0.71061 |  | Keep | 2019-09-02 | Yes | N/A | 2019-10-07 | 2020-01-17 | Yes | 2020-01-17 | 2019-09-09 | 2020-06-05 | 2020-06-05 | 2020-01-17 |  | Yes | Shovel Ready |  | 1350000.2 |  |  | 1350000 | -0.2 | 69604.3 |  | 1280395.9 | 0 | 1280395.9 |  |  |  | 21 | [9 empty] | Deer Park | Napa | 0 | 0 | E.5014772.08 |  |  |  | 2020 | Q1 | 2019-06-30 | 2020-01-02 | 2020-01-17 |  | Y | SILVERADO 2104722 | 160
35085538 |  | 2020 | 220 Mile Plan | SILVERADO 2105 WIRE DOWN - PH 1 |  |  | FICL | 10194 | 0 | 10413 | 10413 | 1.9722 | 5327 | 1.0089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-19 |  |  | 2019-08-01 |  | 2019-08-01 |  |  | Yes | 2019-09-05 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  |  |  | 1980-01-01 | Y | [11 empty] | 5086 | 0.96326 | 5327 | 1.0089 | 0 | 0 | 1.9722 | 0 | 1.9722 | 0 | 1.9722 | 0 | 0 | 1.9722 |  | Keep | 2019-08-19 | Yes | N/A | 2019-10-07 | 2020-05-18 | Yes | 2020-05-18 | 2019-09-09 | 2020-04-29 | 2020-04-29 | 2020-02-01 |  | Yes | Shovel Ready |  | 2950000.4 |  |  | 2950000 | -0.4 |  |  | 2775454.4 | [5 empty] | 26 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.02 |  |  |  | 2020 | Q1 | 2019-07-26 | 2020-01-02 | 2020-01-31 |  | Y | SILVERADO 2105658898 | 104
35085539 |  | 2020 | 220 Mile Plan | SILVERADO 2105 WIRE DOWN - PH 2 |  |  | DOCC | 10424 | 0 | 10260 | 10260 | 1.9432 | 4405 | 0.83428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-21 |  |  | 2019-08-09 |  | 2019-08-09 |  |  | Yes | 2019-09-04 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 5855 | 1.1089 | 4405 | 0.83428 | 0 | 0 | 1.9432 | 0 | 1.9432 | 0 | 1.9432 | 0 | 0 | 1.9432 |  | Keep | 2019-08-21 | Yes | N/A | 2019-11-08 | 2020-05-21 | Yes | 2020-05-21 | 2019-09-09 | 2019-11-08 | 2020-02-21 | 2020-05-19 |  | Yes | Shovel Ready |  | 2569999.8 |  |  | 2570000 | 0.2 |  |  | 2450650.7 | [5 empty] | 28 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.03 |  |  |  | 2020 | Q1 | 2019-08-02 | 2020-01-02 | 2020-01-31 |  | Y | SILVERADO 2105658898 | 104
35085680 |  |  |  | SILVERADO 2105 WIRE DOWN - PH 3 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | [10 empty] | 2019-07-23 | [33 empty] | 2020-12-31 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6538 | 1.6538 | 0 | 0 |  |  |  |  | N/A | [12 empty] | 10000 |  |  | 2298281.08 | 2288281.08 |  |  | 84743.6 | [15 empty] | Saint Helena | Napa | 0 | 0 | [10 empty] | Y
35085681 |  |  |  | SILVERADO 2105 WIRE DOWN - PH 4 |  |  | DOCC | 2947 | 0 | 2934 | 2934 | 0.55568 | 13 | 0.0024621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-19 |  |  | 2019-06-07 |  | 2019-06-07 |  |  | Yes | 2019-08-28 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Envro review starting 6/25/19. CIF Sent on 6/28/2019 | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 2934 | 0.55568 | 0 | 0 | 0 | 0 | 0.55568 | 0 | 0.55568 | 0 | 0.55568 | 0 | 0 | 0.55568 |  |  | 2019-08-19 |  | N/A | 2019-09-06 | 2019-09-24 | Yes | 2019-09-24 | 2019-08-30 |  |  | 2019-09-30 |  |  |  |  | 500000.5 |  |  | 500000 | -0.5 |  |  | 480452.5 | [5 empty] | 15 | [9 empty] | Saint Helena | Napa | 0 | 0 | E.5014317.05 |  |  |  | 2019 | Q3 |  |  |  |  | Y | SILVERADO 2105658898 | 104
35085847 |  | 2022 |  | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  |  | PEND | 4470 | 0 | 4470 | 4470 | 0.84659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84659 |  |  | CC | 08W |  | 2022-11-22 |  |  | 2019-06-25 |  | 2019-06-25 |  |  | Yes | 2019-06-25 | [6 empty] | No | [9 empty] | 2022-11-22 | 2022-11-22 | [5 empty] | 2022-11-22 | 2022-11-22 |  |  |  | ** Caltrans District 5 - 5/28/20- CT D5 Permit requested DUE 8/28/20 | [6 empty] | [REDACTED] instructs not to permit until 7/2020. Env constraint | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84659 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [12 empty] | 2900526 | 1520908.4 | 1353842.8 | 5136422 | 2235896 |  | 52.43% | 78122.6 |  |  |  | 1796509.251 |  | 19.8667 | [7 empty] | Remove |  | Aptos | Santa Cruz | 36.9746 | -121.8838 | 35085847 |  |  | 2020-097 | 999 |  | 2019-06-25 | 2023-01-02 |  |  | Y | ROB ROY 210512474 | 3283 |  | WDDB |  | 2021-03-09 17:04
35087207 |  |  |  | STS-REPL POLE 16E/O 2S/O CO 19161 BLA |  |  | CLSD |  | 0 | 1065 | 1065 | 0.2017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 2AF | IF | [60 empty] | 1065 | 0.2017 | 0 | 0 | 0 | 0 | 0.2017 | 0 | 0.2017 | 0 | 0.2017 | 0 | 0 | 0.2017 |  |  |  |  | N/A | [7 empty] | 2019-06-28 | [29 empty] | 37.9397 | -121.911
35087462 |  |  |  | STS-OFAC_IDLE_DEEN - 6 N/O 2 W/O R/O 930 |  |  | CLSD |  | 0 | 1538 | 1538 | 0.29129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 1538 | 0.29129 | 0 | 0 | 0 | 0 | 0.29129 | 0 | 0.29129 | 0 | 0.29129 | 0 | 0 | 0.29129 |  |  |  |  | N/A | [7 empty] | 2019-06-26 | [29 empty] | 39.0461 | -121.3037
35087685 |  | 2020 |  | BUCOCAMP 5000 BLUE BALATON LN PARADISE |  |  | CLSD |  | 0 | 272 | 272 | 0.051515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 272 | 0.051515 | 0 | 0 | 0 | 0 | 0.051515 | 0 | 0.051515 | 0 | 0.051515 | 0 | 0 | 0.051515 |  |  |  |  | N/A | [5 empty] | 2019-06-28 | 2019-06-28 | 2019-05-14 | [29 empty] | 39.727 | -121.5755 |  |  |  |  | 2019
35087693 |  | 2020 | (blank) | BUCOCAMP 13524 HOG RANCH RD ORO COMP |  |  | UNSC |  | 0 | 666 | 666 | 0.12614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 666 | 0.12614 | 0 | 0 | 0 | 0 | 0.12614 | 0 | 0.12614 | 0 | 0.12614 | 0 | 0 | 0.12614 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-20 | [28 empty] | Paradise | Butte | 39.7882 | -121.5303 |  |  |  |  | 2019 | [5 empty] | Y
35088308 |  | 2020 |  | BUCOCAMP 1445 KELLER LANE PARADISE |  |  | CLSD |  | 0 | 486 | 486 | 0.092045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 486 | 0.092045 | 0 | 0 | 0 | 0 | 0.092045 | 0 | 0.092045 | 0 | 0.092045 | 0 | 0 | 0.092045 |  |  |  |  | N/A | [7 empty] | 2019-05-25 | [27 empty] | Paradise | Butte | 39.7413 | -121.5938 |  |  |  |  | 2019
35088309 |  | 2020 |  | BUCOCAMP 1426 W DOTTIE LANE PARADISE |  |  | CLSD |  | 0 | 530 | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 530 | 0.10038 | 0 | 0 | 0 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0.10038 | 0 | 0 | 0.10038 |  |  |  |  | N/A | [7 empty] | 2019-05-22 | [29 empty] | 39.7449 | -121.5937 |  |  |  |  | 2019
35089880 |  |  |  | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 |  |  | CLSD |  | 2117 | 0 | 2117 | 0.40095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | [9 empty] | 2019-08-12 | [50 empty] | 2117 | 0.40095 | 0 | 0 | 0 | 0 | 0.40095 | 0 | 0.40095 | 0 | 0.40095 | 0 | 0 | 0.40095 |  |  |  |  | N/A |  |  |  |  | 2019-09-23 |  |  | 2019-10-09 | [27 empty] | Angwin | Napa | 0 | 0 |  |  |  |  | 2019 | [6 empty] | SILVERADO 210437632 | 720 |  |  |  | 2021-03-04 11:48
35091861 |  | 2020 |  | BUCOCAMP 628 MORRIS LANE PARADISE |  |  | CLSD |  | 0 | 238 | 238 | 0.045076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 238 | 0.045076 | 0 | 0 | 0 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0.045076 | 0 | 0 | 0.045076 |  |  |  |  | N/A | [7 empty] | 2019-05-03 | [29 empty] | 39.7437 | -121.6267 |  |  |  |  | 2019
35092061 |  |  |  | STS-COND_IDLE_REMV - 19501 OLD CAZ *OCLH |  |  | FICL |  | 0 | 120 | 120 | 0.022727 | 120 | 0.022727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 2AF | IF | [60 empty] | 0 | 0 | 120 | 0.022727 | 0 | 0 | 0.022727 | 0 | 0.022727 | 0 | 0.022727 | 0 | 0 | 0.022727 |  | Keep |  |  | N/A | [7 empty] | 2020-02-27 | [27 empty] | Guerneville | Sonoma | 38.5304 | -123.0511
35094082 |  |  |  | STS-POLE_IDLE_REMV - 5549 GLEN DR#1PNPAR |  |  | CLSD |  | 0 | 566 | 566 | 0.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 566 | 0.1072 | 0 | 0 | 0 | 0 | 0.1072 | 0 | 0.1072 | 0 | 0.1072 | 0 | 0 | 0.1072 |  |  |  |  | N/A | [7 empty] | 2019-08-31 | [29 empty] | 39.7491 | -121.6026
35094321 |  |  |  | XSTS-POLE_IDLE-REMOV - 6PSE1PSW 6700 CRO |  |  | CLSD |  | 0 | 545 | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 2AF | IF | [60 empty] | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0.10322 |  |  |  |  | N/A | [7 empty] | 2019-06-13 | [29 empty] | 37.0834 | -121.7524
35094363 |  | 2020 |  | BUCOCAMP 13764 CANYON RD MAGALIA |  |  | CLSD |  | 0 | 555 | 555 | 0.10511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 555 | 0.10511 | 0 | 0 | 0 | 0 | 0.10511 | 0 | 0.10511 | 0 | 0.10511 | 0 | 0 | 0.10511 |  |  |  |  | N/A | [5 empty] | 2019-08-10 | 2019-08-10 | 2019-06-20 | [29 empty] | 39.8088 | -121.5822 |  |  |  |  | 2019
35094388 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 1 |  |  | FICL | 2741 | 0 | 2241 | 2241 | 0.42443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-19 |  |  | 2019-07-03 |  | 2019-07-03 |  |  | Yes | 2019-08-28 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Caltrans encroachment permit submitted on 8/13 | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 1980-01-01 | Y | [11 empty] | 2241 | 0.42443 | 0 | 0 | 0 | 0 | 0.42443 | 0 | 0.42443 | 0 | 0.42443 | 0 | 0 | 0.42443 |  |  | 2019-07-19 |  | N/A | 2019-09-16 | 2019-09-23 | Yes | 2019-09-23 | 2019-09-16 |  |  | 2019-09-23 |  |  |  |  | 400000.2 |  |  | 400000 | -0.2 |  |  | 390843.6 | [5 empty] | 14 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.02 |  |  |  | 2019 | Q3 |  |  |  |  | Y | KONOCTI 1102532 | 153
35094389 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 2 |  |  | ESTS | 2741 | 3000 | 200 | 3200 | 0.60606 | 0 | 0 | 0 | 0 | 3200 | 0.60606 | 0 | 0 | 0 | 2741 | 0.51913 | HB | 08W | SH | 2022-06-27 17:00 |  |  | 2021-01-31 | 2021-01-31 | 2021-01-31 | 2020-12-15 | 2020-12-15 |  |  | 5.2.2020-Caltrans scope on project is moveing the PEND date out. | [5 empty] | No | [21 empty] | ** Caltrans DSDD likely |  |  |  | Yes | 2020-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.60606 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-06-27 17:00 |  | INPR | 2022-11-17 08:00 | 2022-12-16 08:00 |  | 2023-02-15 17:00 | [8 empty] | 85000 |  |  | 85000 | 0 |  |  | 74198 | [5 empty] | 14 |  | Have not been assigned in Estimating & EODs are undetermined. As soon as we get a copy of the 2020 work plan with a priority list, we will start to have a better idea of when these will be started. A rough base map for each of these is completed, which will help to expedite the substructure design. Both of these will require CalTrans permits. PM35094389 will need to be built in order for PM74022385 to become fully operational. | Complete |  |  |  |  | Remove |  | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.03 |  |  | 2021-074 | 2022 |  | 2020-04-30 | 2020-10-01 | 2020-11-05 |  | Y | KONOCTI 1102532 | 153
35094390 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 3 |  |  | DOCC | 2237 | 0 | 2881 | 2881 | 0.54564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-27 |  |  | 2019-07-31 |  | 2019-07-31 |  |  | Yes | 2019-08-09 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Drawing received 7/29 - Potential forest conflicts | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 1980-01-01 | Y | [11 empty] | 2881 | 0.54564 | 0 | 0 | 0 | 0 | 0.54564 | 0 | 0.54564 | 0 | 0.54564 | 0 | 0 | 0.54564 |  |  | 2019-08-27 |  | N/A | 2019-11-21 | 2019-12-16 | Yes | 2018-12-16 | 2019-09-13 |  |  | 2019-12-16 |  |  |  |  | 900000.3 |  |  | 900000 | -0.3 |  |  | 879982.2 | [5 empty] | 12 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.04 |  |  | 2020-060 | 2019 | Q4 |  |  |  |  | Y | KONOCTI 1102532 | 153
35094391 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 4 |  |  | UNSC | 2237 | 0 | 3625 | 3625 | 0.68655 | 0 | 0 | 0 | 0 | 3625 | 0.68655 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-03-08 17:00 |  |  | 2020-01-10 |  | 2020-01-10 |  |  | Yes | 2020-01-17 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68655 | 0 | 0 | 0.77973 | 0.77973 | 0 | 0 |  | Remove | 2021-03-08 17:00 |  | N/A | 2022-04-19 08:00 | 2022-05-02 08:00 |  | 2022-06-30 17:00 | 2020-02-14 | [7 empty] | 45454 | 30137.3 |  | 470100.69 | 424646.69 |  | 66.3% | 30050.9 |  |  |  | 43896.5363 |  | 12 |  |  | complete |  |  |  |  | Remove |  | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.05 |  |  | 2021-075 | 2022 |  | 2019-01-10 | 2021-04-03 |  |  | Y | KONOCTI 1102532 | 153
35094392 |  |  |  | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 |  |  | FICL | 3625 | 0 | 1956 | 1956 | 0.37045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-08-29 |  |  | 2019-08-29 |  | 2019-08-29 |  |  | Yes | 2019-08-29 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | CIF Submitted on 9/5/19 | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 1980-01-01 | Y | [11 empty] | 1956 | 0.37045 | 0 | 0 | 0 | 0 | 0.37045 | 0 | 0.37045 | 0 | 0.37045 | 0 | 0 | 0.37045 |  |  | 2019-08-16 |  | N/A | 2019-10-28 | 2019-12-04 | Yes | 2019-12-04 | 2019-10-22 |  |  | 2019-12-04 |  |  |  |  | 270000 |  |  | 270000 | 0 |  |  | 260347.4 | [5 empty] | 19 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.06 |  |  | 2020-062 | 2019 | Q4 |  |  |  |  | Y | KONOCTI 1102532 | 153
35094393 |  | 2020 | 220 Mile Plan | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  |  | FICL | 10459 | 0 | 10641 | 10641 | 2.0153 | 10641 | 2.0153 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4451e-16 |  |  | HB | 08W | SH | 2020-05-25 |  |  | 2019-12-19 |  | 2019-12-19 |  |  | Yes | 2019-12-19 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted on 12/17/19 | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 2020-06-09 | Y | 2020-05-01 |  |  | Started | [7 empty] | 0 | 0 | 10641 | 2.0153 | 0 | 0 | 2.0153 | 3.4451e-16 | 2.0153 | 0 | 2.0153 | 0 | -3.4451e-16 | 2.0153 |  | Keep | 2020-02-11 | Yes | N/A | 2020-06-01 08:00 | 2020-08-20 | Yes | 2020-08-20 | 2020-02-14 | 2020-05-04 | 2020-08-05 | 2020-08-05 | 2020-05-25 | Yes | Shovel Ready |  | 2815032.1 |  |  | 3335231 | 520198.9 |  |  | 1763244.6 | [5 empty] | 53 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.07 |  |  | 2020-063 | 2020 | Q2 | 2019-12-13 | 2020-05-02 | 2020-06-14 |  | Y | KONOCTI 1102532 | 153
35094394 |  | 2020 | 220 Mile Plan | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  |  | MAPP | 7765 | 0 | 7765 | 7765 | 1.4706 | 7765 | 1.4706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-12-11 |  |  | 2019-12-11 |  | 2019-12-11 |  |  | Yes | 2019-12-11 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7765 | 1.4706 | 0 | 0 | 1.4706 | 0 | 1.4706 | 0 | 1.4706 | 0 | 0 | 1.4706 |  | Keep | 2019-11-05 | Yes | N/A | 2020-03-09 | 2020-11-19 | Yes | 2020-11-19 | 2020-02-04 | 2020-11-19 | 2020-11-19 | 2020-11-19 |  | Yes | Shovel Ready |  | 1670654.3 |  | 8937.4 | 1708101 | 37446.7 |  |  | 1480080.8 | [5 empty] | 39 | [9 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.08 |  |  | 2020-064 | 2020 | Q1 | 2019-11-05 | 2020-02-28 | 2020-05-01 |  | Y | KONOCTI 1102532 | 153
35094395 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 8 |  |  | ESTS | 7300 | 6245 | 1055 | 7300 | 1.3826 | 0 | 0 | 0 | 0 | 7300 | 1.3826 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-03-03 17:00 |  |  | 2021-02-28 |  | 2021-02-28 | 2020-12-15 | 2020-12-15 |  |  | 5.2.2020-Caltrans scope on project is moveing the PEND date out. | [5 empty] | No | [21 empty] | ** Caltrans DSDD likely |  |  |  | Yes | 2020-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3826 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-03 17:00 |  | INPR | 2022-04-14 08:00 | 2022-07-06 08:00 |  | 2022-09-05 17:00 | [8 empty] | 75000 | 57453.4 |  | 75000 | 0 |  | 76.6% | 57287.1 |  |  |  | 41555.3359 |  | 37 |  | CalTrans required Have not been assigned in Estimating & EODs are undetermined. As soon as we get a copy of the 2020 work plan with a priority list, we will start to have a better idea of when these will be started. A rough base map for each of these is completed, which will help to expedite the substructure design. Both of these will require CalTrans permits. PM35094389 will need to be built in order for PM74022385 to become fully operational. | Complete |  |  |  |  | Remove |  | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.09 |  |  | 2021-076 | 2022 |  | 2020-04-30 | 2021-01-02 |  |  | Y | KONOCTI 1102532 | 153
35094396 |  |  |  | CWSP-KONOCTI 1102-LR 532 PH 9 |  |  | UNSC | 4961 | 0 | 4961 | 4961 | 0.93958 | 0 | 0 | 0 | 0 | 4961 | 0.93958 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-03-12 17:00 |  |  | 2020-02-21 |  | 2020-02-21 |  |  | Yes | 2020-02-21 | With estimator for final edits due back 1/31. |  |  |  |  | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 1/13/20 | Full |  |  | Yes | 2020-12-31 |  | Annual | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.93958 | 0 | 0 | 0.82405 | 0.82405 | 0 | 0 |  | Remove | 2021-03-12 17:00 |  | N/A | 2022-04-11 08:00 | 2022-05-09 08:00 |  | 2022-07-07 17:00 | 2020-03-20 | [7 empty] | 45454 | 433248.9 |  | 687082.4 | 641628.4 |  | 953.1% | 33461.8 |  |  |  | 461107.4767 |  | 25 |  | completed, ADE approved. There are (4) very minor edits to the estimate that still need to be made. My estimator has been sick this week. I will come in tomorrow to make these edits if not later today. I expect this to be in PEND by COB on Tuesday. | complete |  |  |  |  | Remove |  | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.10 |  |  | 2021-077 | 2022 |  | 2020-01-31 | 2021-04-03 |  |  | Y | KONOCTI 1102532 | 153
35094397 |  | 2021 | 220 Mile Plan | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Scoped | MAPP | 4347 | 0 | 5621 | 5621 | 1.0646 | 0 | 0 | 5621 | 1.0646 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2020-06-08 |  | Y | 2019-12-26 |  | 2019-12-26 |  |  | Yes | 2019-12-26 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2020-12-31 |  | Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 0 | 0 | 5605.9 | 1.0617 | 1.0617 | 0.0028598 | 1.0617 | 0 | 1.0617 | 0 | 1.7225e-16 | 0 |  | Keep | 2020-05-29 17:00 | Yes | N/A | 2020-06-02 08:00 | 2020-11-09 | Yes | 2021-01-15 | 2020-02-14 | 2020-06-08 | 2021-01-13 | 2021-01-14 | 2020-06-08 | Yes | Shovel Ready |  | 1438986.6 |  | 280532.1 | 1733017 | 294030.4 | 126847.1 |  | 1305301.5 | 6838 | 1312139.5 |  |  |  | 22 |  | 100% complete | [7 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.11 |  |  | 2020-067 | 2020 | Q2 | 2019-12-17 | 2020-06-10 | 2020-06-30 |  | Y | KONOCTI 1102532 | 1999 |  | PRE
35094513 |  | 2021 |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Scoped | PEND | 10091 | 428 | 9423 | 9851 | 1.8657 | 0 | 0 | 10124 | 1.9174 | 0 | 0 | 0 | 0 | -0.051705 |  |  | ST | 08W | SH | 2021-05-03 |  | Y | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-05-15 | 2020-05-15 | Yes | 2020-06-29 | 06/23: EST target sub (6/26)06/16: ADE soft target (6/20) - ADE rtn 3rd correctionst to CO06/15: BCF submitted for 3rd ADE rvw06/09 - 05/26: EST target sub (6/05); (6/09); (6/12)05/24: ADE rtn 2nd corrections to CO5/18: ADE target (5/22); ok'd EST to sched constructability rvw05/15: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready]05/12: On Track05/05 - 04/28: EST to firm up Sub date (5/15)04/07: ADE rtn 1st corrrections to CO04/03: BCF updated DO Field Notes in SAP for review 03/26: In ADE rvw - request CO provide detail field notes per the attached ADE/Contractor guidelines03/23: ADE assigned ( [REDACTED] ) - firm up rvw date (4/11)??03/17 <-- 10/29: ADE to be assigned10/22: PUSH 1 month - ADE resourcing10/15: Pending ADE assignment - waiting for 2020 Priority list10/11: BCF submitted for 1st ADE rvw10/08: On Track; (EES changes adding additional activities to processing)10/01: Push to 10/11 completing 9/24 task9/24: Push to 10/08 1st submittal |  |  |  | 2020 - Q3- M7 [R153] | R3.3 - EST Implementing Corrections |  | Comp | 27 | 61 |  |  | Yes |  |  |  | 2021-04-15 | 2021-04-15 | Complete |  |  |  |  | 2021-04-15 | 2021-04-15 |  |  |  | ** Caltrans DSDD - Pilot Project. USFS locations in Stanislaus NF- package submitted to USFS 10/28 and follow up sent on 11/10. Stanislaus NF concerns with veg delaying approval. Partial ERTC requested 2/9/21. |  |  | 2021-04-17 |  |  |  | County requires Caltans permit before County approval. Submitted to calaveras on 6/30/20 |  | 2021-06-18 |  | 2021-05-03 |  |  | DSDD | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8657 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-17 17:00 |  | INPR | 2021-07-20 08:00 | 2021-09-27 08:00 |  | 2021-11-25 17:00 |  | 2021-09-06 20:53 | 2021-09-30 01:30 | [5 empty] | 250000 | 3681203.2 | 4178901 | 3142865.56 | 2892865.56 |  | 1472% | 201595.5 |  |  |  | 1973074.0936 |  | 92 |  |  | Complete | [6 empty] | Arnold | Calaveras | 0 | 0 | E.5014540.01 | ML | MX | 2021-084 | 2021 |  | 2020-07-31 | 2021-02-26 |  |  | Y | STANISLAUS 17021804 | 2712 |  | CWSP |  | 2021-03-11 16:58
35094514 |  |  |  | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  |  | PEND | 6756 | 0 | 6756 | 6756 | 1.2795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2795 |  |  | NV | 08W | SH | 2021-12-02 08:00 |  |  | 2020-08-04 | 2021-09-30 | 2020-08-04 | 2020-07-07 | 2020-07-07 | Yes | 2020-09-29 | 08/04: APPROVED - INTO PEND08/03: EST advised job with estimating support for 2wks07/29: ADE rtn 3rd corrections to CO; complete JP Credits and route.07/28: QUES submitted for 3rd ADE rvw07/22: EST target sub (7/31)07/16: ADE rtn 2nd corrections to CO07/15 - 07/08: ADE in rvw - priority based07/07: QUES submitted for 2nd ADE rvw07/01: EST On Track for QUES piece; GC rvw - may take 3wk based on avg turnaround06/24: EST target sub (7/7); holiday, refielding needed; re stamping06/17: EST target sub (7/1)06/08: ADE rtn 1st corrections to CO06/03- 05/27: ADE rvw - priority based05/21: ADE assigned ( [REDACTED] )05/20 - 05/06: ADE to be assigned04/14: QUES resubmitted for 1st ADE rvw04/08: Finalizing conversion; rvw/stamping03/25 - 03/23: 1st sub updated 4/1502/27: Flagged COMPOSITE to WOOD [2] - Pulled back02/24: QUES resubmitted for 1st ADE rvw - job scope changed according to the 2-19-2020 design meeting02/17: QUES submitted for 1st ADE rvw02/12: On Track02/04: EST (Design Approach email) - in internal review and stamping needed. Riser pole - design approach pending.01/08: No Change12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M10 [R2021_49] | COMPLETED |  | Wood | 55 | 10 |  | 2020-09-11 | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-14 | 2020-09-14 | Full |  |  |  | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-07-16 |  | 2021-06-25 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2795 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-02 08:00 |  | INPR | 2022-01-13 08:00 | 2022-05-02 17:00 |  | 2022-07-01 17:00 | 2020-09-28 | [7 empty] | 262500 | 2498087.6 |  | 262500 | 0 |  | 951.7% | 65459.2 |  |  |  | 1952324.2345 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.01 | ML | OH | 2021-049 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35094515 |  |  |  | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  |  | ESTS | 8723 | 0 | 8723 | 8723 | 1.6521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6521 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-12-31 | 2020-11-30 | 2020-12-31 | 2020-12-01 | 2020-12-01 |  |  | 11/04 - 10/28: EST target sub (TBD); design in rvw for alternative approach (walkdown pending)10/22: ADE rtn 1st rvw to CO10/20: ADE/EST coordinating on some ADE Q&A; finishing up rvw; Target sub (10/21); conflict in approach to barricades for equip - working with planner on solution, at RISK of dragging out estimate.10/14 - 09/16: ADE In rvw; priority based09/10: ADE Assigned ( [REDACTED] )09/09: QUES submitted for 1st ADE rvw [2] - redesign incorporated09/02: EST target sub (9/4);Waiting for Planning Eng for scope change08/26: EST target Sub (??) Met - moving forward; installing pad mount w/ recloser08/19: On Track - meeting08/12: Meeting next Wens ; pole path rise - reviewing approach to go UG as potential better option.08/05: Meeting sched next coming week(s) with PID to iron out details07/29 - 05/01: Pending PID rvw - Redesign; 6/24 waiting on change order (part of 6 job Chng requests being submitted)04/30: EST - Based on the PID job walk, we will need to reinterpret and redesign04/21: |  |  |  | 2020 - Q4- M12 [R2021_52] | R1.3 - EST Implementing Corrections |  | Wood | 2 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-06-04 |  | 2021-05-13 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6521 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-09-09 17:00 |  | INPR | 2022-10-18 08:00 | 2022-11-25 17:00 |  | 2023-02-17 17:00 | [5 empty] | Yes |  |  | 271429 | 5788519.8 |  | 271429 | 0 |  | 2133% | 11040.2 |  |  |  | 3503769.8663 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014755.01 | ML | OH | 2021-052 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35094516 |  |  |  | CWSP-ORO FINO 1101 OCB PH 1.1 |  |  | PEND | 10300 | 0 | 10300 | 10300 | 1.9508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9508 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-10-31 | 2020-09-30 | 2020-10-31 | 2020-07-22 | 2020-07-22 | yes | 2020-10-29 | [Composite to Wood - Sept List][OCT EOD at RISK]10/28: Final rvw communicated for corrections, Planner to complete [REDACTED] ; Routing upon update completion to SAP10/26: EST Routed for approval10/23: ADE rtn rvw for 2nd corrections to CO; couple items, apply and send for approval10/21 EN submitted corrections for 3rd ADE rvw10/20: EST ready to submit - SCADA equip issue; mtg scheduled today on how to proceed.10/13: EST target sub (10/16)10/07: ADE rtn 2nd corrections to CO10/05: ADE reaffirmed confidence in OCT EOD10/02: Pulled in per PMGR request (2021 Project)09/28 - 09/22: Conversion Target sub (9/29); 9/27 routed09/15 - 09/08: EST target sub TBD; Conversion09/01 - 08/04: ADE in rvw - priority based07/22: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]07/21 - 07/14: EST target sub (7/24)07/10: ADE rtn 1st corrections to CO07/07 - 05/28: ADE working priority PM - targeting starting next week (6/5);(06/12)05/27: EN submitted for 1st ADE rvw [2] - revision applied05/26: Per EN - ADE hasn’t returned the corrections yet. Job scope changed on the underground and the estimator is working on that. The ADE is still reviewing the overhead part of the job04/20: ADE provided some input on your UG design before moving forward on the revisions04/17: ADE - Estimator has requested job be put on HOLD do to somerevisions required to the design. MSO Switches and UG routing04/07: ADE assigned ( [REDACTED] )03/31 - 02/25: ADE to be assigned02/21: EN submitted for 1st ADE rvw02/19: 2nd scope change from the system planner ; taken over the UG crossing and two other pole locations that were not in our original or 1st scope change. Sub 2/2102/18: On Track02/11: Est Push to 2/19 1wk: 6 Engr out doing 'staking' (priority req).02/04: On Track 1st sub01/17 <-- 01/14: Push 2 wk; System Planner request: Est rcv'd Job scope change - refielding required, new proposed undergrounding for portions of the mainline.12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q4- M10 [R2021_6] | EDRS - EST Routing for approval |  | Comp | 0 | 82 |  | 2020-11-06 | Yes |  |  |  | 2020-11-30 | 2020-11-30 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Locations on FERC identified in high level review. May push out ERTC date. | [8 empty] | 2021-04-02 |  | 2021-03-17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9508 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-11 17:00 |  | INPR | 2022-08-29 08:00 | 2022-10-04 17:00 |  | 2022-12-27 17:00 | [8 empty] | 250000 | 3760743.1 |  | 250000 | 0 |  | 1504% | 54804.3 |  |  |  | 1927837.2396 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.01 | ML | MX | 2021-006 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35094517 |  |  |  | CWSP-ORO FINO 1101 OCB PH 2.1 |  |  | PEND | 7634 | 0 | 7634 | 7634 | 1.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4458 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-10-31 | 2020-09-30 | 2020-10-31 | 2020-10-07 | 2020-10-07 |  | 2020-10-29 | [OCT EOD at RISK] 10/28: EST routed; ADE final rvw communicated 10/27: EST routing today; DS73 request for completion sent; EST repackaging. 10/23: EN submitted corrections for 3rd ADE rvw; ADE rtn rvw for 3rd corrections to CO; apply and sub for approval 10/20: EST target sub (10/24) 10/19: ADE rtn 2nd corrections to CO 10/13: ADE target sub (10/16); ADE assisting with Fire response 10/7: 2nd Corrections Received 10/5: Anticipated submittal of 10/6 09/28 - 09/08: EST target sub (10/1) 09/03: ADE rtn 1st corrections to CO; going to remove most of the 4/0AWAC and 4/0ASCR secondary from this job 09/01 - 07/21: ADE in rvw - priority based 07/10: ADE assigned (Steve) 07/07 - 04/04: ADE to be assigned 03/24 EN submitted for 1st ADE rvw 03/17 - 03/03: EST to review impact and sched 1st sub 02/27: Flagged COMPOSITE to WOOD [2] 02/04<-- 12/10: In Progress/No Changes to date 12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q4- M10 [R2021_13] | EDRS - ADE Approved for Routing |  | Wood | 25 | 20 |  | 2020-11-06 | Yes |  |  |  | 2020-12-14 | 2020-12-14 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | No environmental constraints identified, potential for easements pending feedback from LOB on design changes requested. Since estimating is not working on this project, and easements are triggered if no redesign is possible, we have moved date to Jan 2021 pending further guidance from estimating. | [8 empty] | 2021-04-02 |  | 2021-03-17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4458 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 17:00 |  | INPR | 2022-08-10 08:00 | 2022-08-24 17:00 |  | 2022-08-26 17:00 | [8 empty] | 333333 | 2841900.2 |  | 333333 | 0 |  | 852.6% | 79901.9 |  |  |  | 1965579.389 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.01 | ML | OH | 2021-013 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35094518 |  |  |  | CWSP-ORO FINO 1101 OCB PH 3.1 |  |  | ADER | 8931 | 0 | 8931 | 8931 | 1.6915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6915 | 11132 | 2.1083 | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-10-31 | 2020-11-30 | 2020-10-30 | 2020-10-30 |  |  | 11/10: EST target sub (11/13) 11/05: ADE rtn 2nd rvw to CO10/30: BCF submitted corrections for 2nd ADE rvw10/27 - 10/20: EST target sub (10/30)10/19: ADE rtn corrections to CO10/13: NOV EOD AT RISK (Driver - Durations & FC 4th iteration); ADE advised, Large job 142 location, Target sub (10/23)10/7: BCF submited for 1st ADE review [2] - redesign applied11/03: ADE in rvw10/6: Estimate was completely wiped out of EES on 10/2. Submittal back to the ADE by 10/7, job has been renumbered.09/28 - 09/21: Target Sub (10/2); Finishing Oro Fino 3.409/15 - 08/25: Sched impact - Target Sub 9/2508/24: EST - requested to remove AWAC. The ADE for this project is [REDACTED] . There are 23 total affected poles. 08/18 - 07/26: ADE Renumbering required (Start locs from '1'); EST target Sub (8/28)07/21: ADE rvw - priority based07/15: ADE assigned ( [REDACTED] )07/14- 03/24: ADE to be assigned03/20: BCF submitted for 1st ADE rvw03/17 - 03/10: EST No impact/ On Track; Low Risk w/ Transition to Offsite work method03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/11 - 02/04: No changes at this time; Low RISK for adjustments01/07: BCF to profide 1st sub FC update - Brunswick move up in priority12/17: Needs Traffic control (50 mph/No shoulder)/ BCF finalizing new 1st submittal dates.12/10: Reprioritizing to Brunswick12/06: BCF 1st ADE Submittal target set 1/2211-26 <-- 11/19: In Rvw for WST 1st submittal target date; [REDACTED] target - Jan Submittal |  |  |  | 2020 - Q4- M11 [R2021_19] | R2.3 - EST Implementing Corrections |  | Wood | 71 | 29 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-04-23 |  | 2021-04-02 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6915 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-29 17:00 |  | INPR | 2022-04-15 08:00 | 2022-05-06 17:00 |  | 2022-07-29 17:00 | [8 empty] | 250000 | 3278814.8 |  | 250000 | 0 |  | 1312% | 63603.9 |  |  |  | 1938432.6664 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014746.01 | ML | MX | 2021-019 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 1101CB | 3
35094519 |  |  |  | CWSP-ORO FINO 1102 LR-2560 PH 1 |  |  | ADER | 9589 | 1027 | 8562 | 9589 | 1.8161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8161 | 9589 | 1.8161 | NV | 08W | SH | 2022-03-25 17:00 |  |  | 2021-01-31 | 2021-09-30 | 2021-01-31 | 2020-10-09 | 2020-10-09 | Yes |  | [Composite to Wood - Sept List]11/10 10/14: ADE in rvw; priority based10/09: CAL Submitted for 2nd ADE rvw09/23: ADE rtn corrections to CO (per CAL); EST recv'd Corrections (9/29)09/16: Estimator confirmed that its 28 composite, and 37 wood; is along the highway which may count as the ones needing to stay composite.09/11: CAL submitted for 1st ADE rvw [2]; Conversion Complete09/09: Conversion On Track09/03: ADE assigned ( [REDACTED] )09/02: Conversion 1st sub (9/11)08/26 - 01/22: ADE to be assigned01/17: CAL submitted for 1st ADE rvw12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2021 - Q1- M1 [R2021_114] | R2.2 - ADE Review in Progress |  | Wood | 37 | 28 | [6 empty] | 2021-03-15 | 2021-03-15 | [5 empty] | 2021-03-15 | 2021-03-15 |  |  |  | ** Caltrans DSDD - Waiting on Final drawings to submit to Caltrans. Waiting for CT Permit. Due 5/27. Partial not desired. Enviro information provided to Caltrans to facilitate veg work starting. Sent follow up on DSDD status on 12/1/20 - [REDACTED] |  |  | 2020-07-06 | Yes |  |  | [REDACTED] to send plans to [REDACTED] on 6/23 | [6 empty] | PI complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8161 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-25 17:00 |  | INPR | 2022-07-04 08:00 | 2022-10-17 17:00 |  | 2022-11-16 17:00 |  |  |  |  | 2020-12-25 |  |  |  | 300000 | 177399.1 |  | 300000 | 0 |  | 59.13% | 173661.3 |  |  |  | 97681.4316 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014721.01 |  |  | 2021-114 | 2022 | 2020 Reserve | 2020-08-31 | 2020-11-14 | 2020-12-25 |  | Y | ORO FINO 11022560 | 61
35095160 |  |  |  | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  |  | ADER | 8398 | 0 | 8398 | 8398 | 1.5905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5905 |  |  | NV | 08W | SH | 2022-04-28 17:00 |  |  | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2020-09-24 | 2020-09-24 |  |  | [Composite to Wood - Sept List]11/10 - 11/04: EST sub (11/13); making adjustments base on 2.6 & 2.210/28: EST sub (11/09)10/27: ADE rtn 2nd rvw to CO10/22: PMgr request to pull in (Dec)10/21 - 09/30: ADE in rvw; priority based09/24: CAL submitted for 2nd ADE rvw09/23: Current Status Sub'd or in Rvw ??09/16: EST Conversion Complete09/09: CAL submitted for 1st ADE Rvw [3]; Conversions09/02: ADE rtn 1st corrections to CO; EST converting09/02: Conversion 1st sub (9/11) soft target08/26 - 07/29: ADE in rvw - priority based07/17: ADE assigned (Ed)07/15: ADE to be assigned07/13: Reassigning ADE - [REDACTED] workload increased07/08: ADE assigned ( [REDACTED] )07/01 - 05/06: ADE to be assigned05/03: CAL submitted for 1st ADE rvw [2] QC04/15: QC Rereview/Resubmit02/05: CAL submitted for 1st ADE rvw12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q4- M12 [R2021_119] | R2.3 - EST Implementing Corrections |  | Wood | 35 | 7 | [18 empty] | ** Caltrans DSDD | [8 empty] | 2021-02-01 |  | 2021-01-19 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5905 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-28 17:00 |  | INPR | 2022-06-03 08:00 | 2022-09-02 17:00 |  | 2022-09-09 17:00 | [8 empty] | 100000 | 63936.1 |  | 100000 | 0 |  | 63.93% | 63602.4 |  |  |  | 40197.9767 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014720.01 | ML |  | 2021-119 | 2021 |  | 2020-12-31 | 2021-03-16 |  |  | Y | ORO FINO 11022560 | 61
35095161 |  |  |  | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  |  | PEND | 3757 | 132 | 3625 | 3757 | 0.71155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71155 |  |  | NV | 08W | SH | 2022-04-07 17:00 |  |  | 2020-08-01 | 2020-11-30 | 2020-08-01 | 2020-07-14 | 2020-07-14 |  | 2020-08-01 | 08/01: APPROVED - INTO PEND07/29: ADE approved for routing07/24: QUES submitted for 3rd ADE rvw07/18: ADE rtn 2nd corrections to CO07/14: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready]07/14: EST working priority job through approval; target sub (7/17)07/07: Risk - Mon sub; stamping/office closure06/30: On Track06/23: EST target sub (7/10)06/16: ADE rtn 1st corrections to CO - EST target TBD06/09: ADE Rvw - priority based06/04: ADE assigned ( [REDACTED] )06/02: ADE to be assigned05/29: PIKE submitted for 1st ADE rvw05/26: ON Track05/12: EST set 1st sub date05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June.04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week03/17: Applied new Est 1st sub03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06])02/27: Flagged COMPOSITE to WOOD [2]02/11 -On Track |  |  |  | 2020 - Q3- M9 [R2021_103] | COMPLETED |  | Comp/Wood | 24 | 20 |  |  | Yes |  |  |  | 2021-02-15 | 2021-02-15 | [5 empty] | 2021-02-15 | 2021-02-15 |  |  |  | ** Caltrans DSDD - Caltrans encroachment needed for 13% of project - Basemap being created (no DSDD required). Enviro reviews are complete. |  |  | 2020-11-20 | [5 empty] | 2021-02-16 |  | 2021-02-02 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71155 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-07 17:00 |  | INPR | 2022-07-18 08:00 | 2022-08-26 17:00 |  | 2022-09-20 17:00 | [8 empty] | 250000 | 104223.1 |  | 250000 | 0 |  | 41.68% | 104069 |  |  |  | 146472.7091 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014719.01 | ML |  | 2021-103 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35095162 |  |  |  | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  |  | PEND | 6398 | 0 | 6398 | 6398 | 1.2117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2117 | 6960 | 1.3182 | NV | 08W | SH | 2022-04-21 17:00 |  |  | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2020-11-28 | 2020-11-28 |  | 2020-12-22 | [NOV EOD at RISK] - PIKE11/10: ADE target this week11/03: ADE in rvw; rtn from RDO Tues; target this week/next10/27: ADE RDO; long weekend; target mid next week10/20 - 10/13: ADE follow-up; Next PM to jump back on after 56A routed.10/6: Submitted to ADE at the end of Week 10/2.09/21 - 08/18: ADE in rvw; priority based - @RISK EOD PUSH08/11: ADE assigned ( [REDACTED] )08/10: PIKE submitted for 1st ADE rvw08/04: On Track07/27: Est Target date (8/7) - qued for stamping)07/21: On track07/14: Target Sub (7/24); Estimator working priority work07/07 - 06/30: EST target sub (7/15) ; Design - UG conversions/ design/ complex06/16: EST target sub (07/02); Estimator working high priority PMs06/09 - 05/19: On Track; Some UG items to work through ADE with approach & crossroad pieces - At Risk05/12: EST set 1st sub date05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June.04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week03/17: Applied new Est 1st sub03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06])02/27: Flagged COMPOSITE to WOOD [2]02/25: Move from 3/13 to 3/27: Brunswick prioritization02/11 -On Track |  |  |  | 2020 - Q4- M11 [R2021_108] | R1.2 - ADE Review in Progress |  | Wood | 37 | 21 | [18 empty] | ** Caltrans DSDD | [8 empty] | 2021-03-03 |  | 2021-02-17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2117 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-21 17:00 |  | INPR | 2022-07-18 08:00 | 2022-10-06 17:00 |  | 2022-10-11 17:00 | [8 empty] | 250000 | 148855.7 |  | 1563870.91 | 1313870.91 |  | 59.54% | 147769.5 |  |  |  | 122844.3414 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014718.01 | ML |  | 2021-108 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35095163 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  |  | ADER | 6559 | 953 | 5606 | 6559 | 1.2422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2422 |  |  | ST | 08W | SH | 2022-02-18 17:00 |  |  | 2020-12-31 | 2020-10-31 | 2020-12-31 | 2020-10-23 | 2020-10-23 |  |  | [Composite to Wood - Sept List]11/10 - 11/03: ADE in rvw; priority based; Targeting next week to get back to rvw10/23: EN submitted for ADE rvw: conversions10/20: EST target sub (10/22); wrapping up corrections10/13: EST target sub (10/16)09/28 - 09/21: Conversion Sub (10/09)09/15 - 09/01: EST target sub TBD; Conversion08/18: Spoke with JO; JO still working to get someone with Gas - in progress.08/11: EST - reached out to JO; still awaiting feedback; will attempt to discuss during another scheduled meeting07/27: Still in process w/ JO for feedback07/21 - 07/14: Waiting on JO for feed back; in discussions07/07 - 06/30: EST seeking approval to proceed - Change Order submitted; Target EOD - TBD06/23 - 06/02: EST in progress - meeting being set up to review and approve with stakeholders05/21: 2nd sub push (2 mnth)/EOD Push; per PMGR ( [REDACTED] ) will take us more time to reach the preliminary drawing milestone; Project involves hardening OH sections, undergrounding crossings on Highway 88, and relocation of about 1000’ of electric distribution line that will be installed running parallel to Highway 88.05/19: EST - applying outside work adjustments |  |  |  | 2020 - Q4- M12 [R2022(+)_30] | R2.2 - ADE Review in Progress |  | Comp | 0 | 36 | [18 empty] | ** Caltrans DSDD - Pilot Project - | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2422 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-18 17:00 |  | INPR | 2022-03-16 08:00 | 2022-05-02 17:00 |  | 2022-05-05 17:00 | [8 empty] | 625000 | 2804370.5 |  | 1 | -624999 |  | 448.7% | 108941.9 |  |  |  | 2257520.3903 |  | 33 | [7 empty] | Remove |  | Pioneer | Amador | 38.436 | -120.5561 | E.5014742.01 | ML |  | 2020-030 | 2021 | Reserve | 2020-04-30 | 2020-07-29 | 2020-09-06 |  | Y | PINE GROVE 11021222 | 20
35095164 |  |  |  | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  |  | UNSC | 10157 | 610 | 9619 | 10229 | 1.9373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9373 |  |  | NV | 08W | SH | 2021-12-22 17:00 |  |  | 2020-08-13 | 2021-09-30 | 2020-08-13 | 2020-07-17 | 2020-07-17 | yes | 2020-08-13 | 08/13: APPROVED INTO PEND08/12: ADE in rvw; soft target (8/21)08/11: EEI submitted for 5th ADE rvw08/08: ADE provide some additional corrections to CO08/07: EEI submitted for 4th ADE rvw; [REDACTED] inquiry on readiness - to submit for environmental08/05: ADE rtn 3rd corrections to CO07/29: EEI submitted for 3rd ADE rvw07/26: ADE rtn 2nd corrections to CO07/22: ADE in rvw - priority based07/17: EEI submitted for 2nd ADE rvw07/15: EST target sub (7/17)07/10: ADE rtn 1st correctionst to CO07/08 - 06/24: ADE in rvw; numbering to be applied in future jobs06/19: ADE assigned ( [REDACTED] ) - ADE rejected; Number sequense should start at "1"06/17 - 06/10: ADE to be assigned06/05: EEI submitted for 1st ADE rvw06/03: On Track05/27: Push 3wk - EST internal rvw/OCalcs05/20: Push 1wk - EST internal rvw/OCalcs05/13 - 04/22: EST firmed up sub (5/15)04/15 - 03/25: On Track02/27: Flagged COMPOSITE to WOOD [2]02/26: EST push 1st Sub02/18: EEI to review schedule01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M11 [R2021_50] | COMPLETED |  | Wood | 54 | 30 |  | 2020-09-18 | Yes |  |  |  | 2020-10-06 | 2020-10-06 |  |  |  |  | Full | 2020-10-06 | 2020-10-06 | Full |  |  | CIF Submitted 8/21/20 | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-08-06 |  | 2021-07-16 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9373 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-01-31 08:00 | 2022-05-23 17:00 |  | 2022-06-22 17:00 | 2020-10-06 | [7 empty] | 250000 | 3875283.5 |  | 250000 | 0 |  | 1550% | 188550 |  |  |  | 2000341.8594 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5015030.01 | ML | MX | 2021-050 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35095165 |  |  |  | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  |  | FICL | 3825 | 0 | 3666 | 3666 | 0.69432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-09-12 |  |  | 2019-07-22 | 2019-12-29 | 2019-07-22 |  |  | Yes | 2019-07-22 | 7/3 - 7/16: On track for 8/2 Submitted 7/10, ADE Assigned 7/15 7/22: Moved into PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF Submitted 7/22/19 | Full |  |  | Yes |  |  | permit request submitted 7/22/19 |  | 1980-01-01 | Y | [11 empty] | 3666 | 0.69432 | 0 | 0 | 0 | 0 | 0.69432 | 0 | 0.69432 | 0 | 0.69432 | 0 | 0 | 0.69432 |  |  | 2019-09-12 |  | N/A | 2019-09-17 | 2019-11-25 | Yes | 2019-11-25 | 2019-08-19 |  |  | 2019-11-25 |  |  |  |  | 3352028.5 |  |  | 3514354 | 162325.5 | 252187.8 |  | 3093747.3 | 6093.4 | 3099840.7 |  |  |  | 20 | [9 empty] | Shingletown | Shasta | 40.5069 | -121.8183 | E.5015704.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | VOLTA 11021648 | 283
35095166 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  |  | CLSD | 7329 | 0 | 7412 | 7412 | 1.4038 | 7412 | 1.4038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 |  |  | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-12-16 | 2020-12-16 | Yes | 2020-03-10 | 03/09: INTO PEND 03/04: QUES routed for Approval 02/26: ADE Status? EOD RISK 02/22 QUES submitted for 3rd ADE rvw 02/19 - 01/29: 2nd round stamping; High volume of stamping (restamping); Finalizing stamping 01/22: EST on track if restamping is at a minimum 01/18 QUES submitted for another (3rd?) ADE rvw 01/13: ADE Status- ADE unexpected time off - on track for this week (1/17) 12/16: QUES submitted for 2nd ADE rvw - [PRELIM DWGs ready] 12/11 <-- 12/04: On Track 11/27: Ocalcs changing (85%); additional changes (+3wk) - EEI to review implementation 11/20: ADE rtn 1st corrections for ADE rvw 11/13: On Target 11/06:Estimator on vacation - ADE on partial vacation - Rvw expected to be done next week. 10/29: Checking in with ADE (1st 08W rvw, working with new laptop/issues) 10/23: Rvw Inprogress 10/14 QUES submitted for 1st Rvw 10/09: Originally went off straight pole count - Larger amount of poles - require additional time to complete 10/02: 1st Submittal push to 10/07; Estimator bandwith - volume of work - Resource impacts (down to 1 PE for stamping) 9/25: 1st Submittal on target 9/30 9/18: Push to 9/30 - Training/New Hire ramp up 9/11: 1st Submittal push to 9/20 - --> [RCC Issue] 9/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift 7/16 - 8/21: On track 7/3: QUES to review to provide review on 1st ADE Submital |  |  |  | 2020 - Q1- M2 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 12/18/19 | Full |  |  | Yes |  |  | Drawings submitted 12/18/19 |  | 2020-05-22 | Y | 2020-05-01 |  |  | Started | [7 empty] | 0 | 0 | 7412 | 1.4038 | 0 | 0 | 1.4038 | 0 | 1.4038 | 0 | 1.4038 | 0 | 0 | 1.4038 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-04-27 | 2020-05-01 | 2020-08-14 | 2020-08-21 |  | Yes | Shovel Ready |  |  |  | 75000 | [10 empty] | 37 | [9 empty] | Pollock Pines | El Dorado | 38.7717 | -120.5878 | E.5015687.01 |  |  |  | 2020 | Q2 | 2020-02-29 | 2020-05-18 | 2020-08-06 |  | Y | EL DORADO PH 210219562 | 52
35095167 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 |  |  | PEND | 5833 | 0 | 5899 | 5899 | 1.1172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1172 | 5899 | 1.1172 | ST | 08W | SH | 2020-11-30 |  |  | 2020-07-07 | 2020-09-30 | 2020-07-07 | 2020-04-10 | 2020-04-10 | Yes | 2020-07-07 | 07/07: Final corrections applied and routed. APPROVED - INTO PEND 06/29: ADE working to get in for final approval 6/30. - working priority projects 06/23: EST will follow up w/ ADE to check on route situation 06/09: EST status - routed. 06/02: EST target sub (6/5) 5/29-05/28: ADE rtn 3rd corrections to CO; ADE/EST coordinated on walkdown dwg changes 05/26: ON Track; ADE targeting early this week 05/19: EST to submitt (5/19) with applied changes for ADE to conclude review, 05/12: EST - appling changes and stamping for ADE to proceed with rvw 05/05: Construction walk today; ADE advised - will include adjustments 04/28: PIKE submitted for 3rd ADE rvw 04/21: ADE rtn 2nd corrections to CO 04/14: ADE status; corrections update (4/18) (??); pushed 04/10: PIKE submitted for 2nd ADE rvw 04/07: EST firm up date (04/13) 04/03: ADE rtn 1st corrections to CO 03/17: ADE rvw target (3/31)?? 03/12: ADE assigned (Ed) 12/13: PIKE submitted for 1st ADE rvw 11/19 <-- 10/29: Completing Fielding - PSPS Impacts 10/22: On Track (12/15) 10/15: PIKE pulled in 1st ADE Submittal Target (2wk) - Sched to start UG Fielding 9/24 - 10/01: Review 1st submittal target/capabilities - goal is to meet 2019 EOY EOD |  |  |  | 2020 - Q3- M7 [R131] | COMPLETED |  | Comp | 5 | 34 |  | 2020-07-21 | Yes |  |  |  | 2020-05-27 | 2020-05-27 |  |  |  |  | Full | 2020-07-17 | 2020-07-17 | Full |  |  | CIF submitted 5/18/20; waiting on final estimation to finalize reviews/ prelim enviro reviews to be completed 7/10/2020 | Full |  | 2020-11-30 |  |  |  | County Pre-Veg meeting complete 9/23/2020. |  | 2020-11-28 |  | 2020-11-05 | 2020-08-18 |  | 90% complete as of 12/9. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1172 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-13 | Yes | INPR | 2022-03-14 08:00 | 2022-05-03 17:00 |  | 2022-05-09 17:00 | [5 empty] | No |  |  | 2365953.1 | 1453780 |  | 1059112.65 | -1306840.45 | 1672210.8 | 61.44% | 132019.1 | 561723.2 | 693742.3 |  | 1301230.4458 |  | 39 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015394.01 | ML | OH | 2021-029 | 2021 | 2020 Reserve | 2020-07-31 | 2020-11-13 | 2020-12-29 |  | Y | STANISLAUS 17021888 | 4
35095168 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 |  |  | PEND | 6461 | 0 | 6718 | 6718 | 1.2723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2723 |  |  | ST | 08W | SH | 2022-02-07 17:00 |  |  | 2020-08-11 | 2020-10-31 | 2020-08-11 | 2020-05-22 | 2020-05-22 | Yes | 2020-08-24 | {AUG EOD}08/11: ADE applied final corrections; APPROVED - INTO PEND08/10: Final corrections communicated to ADE 08/06: PIKE applied corrections; uploaded docs to SAP08/05: ADE rtn 4th corrections to CO; apply for routing08/04: PIKE submitted for 4th ADE rvw07/27: On Track - in que for stamping 07/21: EST target sub (7/31); 07/16: ADE rtn 3rd corrections to CO07/14 - 07/07: ADE in rvw - start 7/306/24: PIKE submitted for 3rd ADE rvw06/23: EST finishing up 8 Ocalcs06/16: EST status; Working with ADE on applying corrections06/09: EST target sub (6/12)06/04: ADE rtn 2nd corrections to CO; 06/02:ADE advised that JP form 2 missing section of locations; EST updated form 2 in [REDACTED] /26: ADE soft target (5/29)05/22: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready]05/19: Finalizing estimating; 75% stamped; EST internal QC05/15: EST target sub (05/15); EST finalized stamping, completing NB work;05/05 - 04/28: Working corrections; ADE reqs vs standards; stamping, construtability walk impacts04/21: On Track04/14: Construction walk (3/31); Applying changes (push 1-2 days)04/07: EST set sub date (4/17)03/31: |  |  |  | 2020 - Q3- M8 [R2021_23] | COMPLETED |  | Comp | 18 | 41 |  | 2020-08-24 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-15 | 2020-09-15 | Full |  |  | Waiting on Finalized Drawings. CIF Submitted on 4/20/20, reviews complete based on prelim drawings, waiting on final estimate | Full |  | 2020-11-30 |  |  |  | County Pre-Veg meeting scheduled on 10/14. Check requested on 9/29/20 |  | 2020-11-28 |  | 2020-10-23 | 2020-09-17 |  | 65% Complete as of 12/9/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2723 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-07 17:00 |  | INPR | 2022-03-02 08:00 | 2022-05-05 17:00 |  | 2022-08-05 17:00 | 2020-08-22 |  |  |  |  | No |  |  | 250000 | 1952399.7 |  | 1296538.52 | 1046538.52 |  | 781% | 127115.8 |  |  |  | 1534485.0277 |  | 59 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.01 | ML | OH | 2021-023 | 2021 | 2020 Reserve | 2020-05-31 | 2020-08-14 | 2020-09-30 |  | Y | STANISLAUS 17021888 | 4
35096604 |  | 2020 |  | BUCOCAMPT 678 MEMORIAL WAY PARADISE |  |  | CLSD |  | 0 | 218 | 218 | 0.041288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 218 | 0.041288 | 0 | 0 | 0 | 0 | 0.041288 | 0 | 0.13011 | 0 | 0.13011 | 0 | -0.088826 | 0.13011 |  |  |  |  | N/A | [5 empty] | 2019-09-23 | 2019-09-27 | 2019-09-27 | [7 empty] | 67539.78 |  |  |  | 77958.6 | [17 empty] | 39.7611 | -121.6241 |  |  |  |  | 2019 | [5 empty] | Y
35098264 |  |  |  | FT-POLE_IDLE_REMV - NE/O ENTR. 5756 RAI |  |  | CLSD |  | 0 | 545 | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 2AF | IF | [60 empty] | 545 | 0.10322 | 0 | 0 | 0 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0.10322 | 0 | 0 | 0.10322 |  |  |  |  | N/A | [7 empty] | 2019-06-26 | [29 empty] | 38.2657 | -120.5096
35098578 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 |  |  | CLSD | 10112 | 0 | 9480 | 9480 | 1.7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-16 |  |  | 2019-09-16 |  | 2019-09-16 |  |  | Yes | 2019-09-16 | Section 21st ADE Submittal - 7/30/197/3 - 7/24: on track 7/307/31: Friday Submittal8/5: QUES submitted for 1st ADE Review8/7: [REDACTED] assigned & OCalc uploaded to SAP8/21: 1st ADE review scheduled to complete by 8/238/22: Corrections returned to contractors (Prt1, Prt 2, Prt3)8/23: 2nd ADE review communicated to contractor - Need the OU attachment height to be shown on the DWG8/23: Moved into AUG 8/30 priority list (Gap Fill)8/27: QUES submitted for 2nd ADE Rvw8/28: Corrections done - review for ready to route - Routed in EES PRELIM DWG (Done)9/04 - 9/11: [RCC Issues] 9/27 EOD push |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 7/15/19 | Full |  |  | Yes |  |  | Request sent - No permit required |  | 1980-01-01 | Y | [11 empty] | 9480 | 1.7955 | 0 | 0 | 0 | 0 | 1.7955 | 0 | 1.7955 | 0 | 1.7955 | 0 | 0 | 1.7955 |  |  |  |  | N/A |  |  |  |  | 2019-09-30 |  |  | 2019-12-03 |  |  |  |  | 3550707.7 |  |  | 3550706 | -1.7 |  |  | 3490905 | [5 empty] | 50.56 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.02 |  |  |  | 2019 | Q4 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198
35098579 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 |  |  | CLSD | 7417 | 0 | 7573 | 7573 | 1.4343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-08-12 |  |  | 2019-08-12 | 2019-07-30 | 2019-08-12 |  |  | Yes | 2019-08-30 | Section 3 1st ADE Submittal - 6/30/19. Refielded needed. Submittal 7/12 for 1st ADE submittal 7/16: 7/10 Submitted 7/24 - 7/31: Waiting for PGE review completion; ADE Carlos 8/5: 1st ADE review complete, returned to contractor. 8/6: ADE returned corrections to vendor [Prelim DWG ready] 8/12: Approved into PEND 7417' of 1/OAR tree wire. Again, lots of errors showing in EES, which might be due to the SAP issues IT is working on |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 6/27/19. KMZ received. Currently reviewing | Full |  |  | Yes |  |  | Request sent to SIDIVPGEPERMITS 8/6/19 - Private Property No permit required |  | 1980-01-01 | Y | [11 empty] | 7573 | 1.4343 | 0 | 0 | 0 | 0 | 1.4343 | 0 | 1.4343 | 0 | 1.4343 | 0 | 0 | 1.4343 |  |  |  |  | N/A |  |  |  |  | 2019-09-03 |  |  | 2019-10-07 |  |  |  |  | 2022516.3 |  |  | 2438915 | 416398.7 |  |  | 1956173 | [5 empty] | 37.085 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.03 |  |  |  | 2019 | Q3 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198
35098621 |  | 2020 | 220 Mile Plan | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Scoped | DOCC | 6128 | 3761 | 2387 | 6148 | 1.1644 | 5642 | 1.0686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-20 |  | Y | 2019-10-24 | 2019-10-24 | 2019-10-24 |  |  | Yes | 2020-04-24 | Section 41st ADE Submittal - 6/30/19 (assuming we can start immediately without easement/land approval). Submitted 6/287/16: Waiting on Review7/24: QUES received 1st ADE corrections7/31: Need some additional fielding - scheduled for next week - limited on Fld Engrs.7/31: JOB PLACED ON HOLD; per [REDACTED] new job owner, land department has denied to acquire easements to underground along Old Mill Rd. as originally desigm0 [REDACTED] to talk with all parties involved and come up with a solution. 8/7: Construction push out 6month to a year8/29: Confirmed EST still progressing - ADE Corrections targeted for submittal 8/309/04: Pending submittal - Target 9/06 - Additional locations had to be staked9/04: QUES submitted for 2nd ADE rvw [PRELIM DWG ready]9/11 - 09/24: In Review9/25: ADE status update - interruptions for high priority requests, anticipates minimal issues, should be in approval early next week |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes |  |  |  | 2020-07-20 | 2020-07-20 | Complete |  |  |  | Full | 2020-06-08 | 2020-06-08 | Full |  |  | PERTC to be issued by 3/31, [REDACTED] to spoke with [REDACTED] (with BLM) about process on 2/11/20 and they said a more realistic time frame is 7/20/2020. BLM easement needed. Waiting on BLM to reply to docs sent on 1/21. Easment for School property needed as well. 2 easements on Private Property needed. CIF submitted 6/25/19. KMZ received. Offers out to owners. Board meeting is on 12/10. Board asked for staking and will review at Feb. board meeting. Update 4/24/20 - very close to receiving BLM approval - BLM SMEs have all approved and are now finalizing easements. | Full |  |  | Yes |  |  | Project is located on private property and doesn't require county/city permit |  | 2020-06-08 | Y | 2020-05-25 | [10 empty] | 0 | 0 | 6148 | 1.1644 | 0 | 0 | 1.1644 | 0 | 1.1644 | 0 | 1.7326 | 0.56818 | 0 | 0.33523 |  | Keep | 2020-05-05 | Yes | N/A | 2020-06-01 | 2020-12-03 | Yes | 2020-12-03 17:00 | 2020-05-04 |  |  | 2020-12-03 |  | Yes | Shovel Ready |  | 2185499.2 | 1984763.1 | -20298 | 2927538 | 742038.8 |  | 90.81% | 2005061.1 |  |  |  | 1704546.0586 |  | 30.64 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.04 |  |  |  | 2020 | Q3 | 2019-10-24 | 2020-04-30 | 2020-05-27 |  | Y | COLUMBIA HILL 11012212 | 606 |  | PRE |  | 2021-03-09 12:44
35098622 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  |  | FICL | 12854 | 0 | 13101 | 13101 | 2.4813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-08-08 |  |  | 2019-08-08 | 2019-08-20 | 2019-08-08 |  |  | Yes | 2019-08-08 | Section 51st ADE Submittal - 7/15/19. 7/3: On track for 7/157/16: 1st ADE Submitted on 7/157/24 - 7/31: QUES waiting for ADE corrections; ADE [REDACTED] /31: Review completed, corrections being applied8/6: * Correct Location 11 Ocalc, used existing pole load case.* All Zip file Ocalcs should match signed PE calculations. Correction in progress[PRELIM DWG ready]8/8: JOB APPROVED and into PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 6/27/19 - Will try to expedite ERTC | Full |  |  | Yes |  |  | Nevada Co. - Sub permit acquired but only last 30 days (9/30) |  | 1980-01-01 | Y | [11 empty] | 13101 | 2.4813 | 0 | 0 | 0 | 0 | 2.4813 | 0 | 2.4813 | 0 | 2.4813 | 0 | 3.4451e-16 | 2.4813 |  |  |  |  | N/A |  |  |  |  | 2019-08-23 |  |  | 2019-12-09 |  |  |  |  | 4154524.4 | 3905204.8 |  | 4936253 | 781728.6 |  | 93.99% | 4031793.8 |  |  |  | 1573886.0655 |  | 64.27 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.05 |  |  |  | 2019 | Q3 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198
35099113 |  | 2020 |  | BUCOCAMP 1793 EL TORO CT PARADISE |  |  | CLSD |  | 0 | 282 | 282 | 0.053409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 282 | 0.053409 | 0 | 0 | 0 | 0 | 0.053409 | 0 | 0.053409 | 0 | 0.053409 | 0 | 0 | 0.053409 |  |  |  |  | N/A | [7 empty] | 2019-06-05 | [27 empty] | Paradise | Butte | 39.7854 | -121.5758 |  |  |  |  | 2019
35099740 |  | 2020 |  | BUCOCAMPT 1361 PEACEFUL OAKS LN PARADISE |  |  | CLSD |  | 0 | 1929 | 1929 | 0.36534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1929 | 0.36534 | 0 | 0 | 0 | 0 | 0.36534 | 0 | 0.042803 | 0 | 0.042803 | 0 | 0.32254 | 0.042803 |  |  |  |  | N/A | [5 empty] | 2019-09-09 | 2019-09-09 | 2019-09-10 | [29 empty] | 39.7423 | -121.5937 |  |  |  |  | 2019
35100238 |  |  |  | STS-COND_IDLE_REMV-3750 SUNRISE RIDGE |  |  | CLSD |  | 0 | 665 | 665 | 0.12595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF | [60 empty] | 665 | 0.12595 | 0 | 0 | 0 | 0 | 0.12595 | 0 | 0.12595 | 0 | 0.12595 | 0 | 0 | 0.12595 |  |  |  |  | N/A | [7 empty] | 2019-08-02 | [29 empty] | 35.5212 | -120.7973
35100240 |  | 2020 |  | BUCOCAMPT 6285 OAK WAY PARADISE |  |  | FICL |  | 0 | 96 | 96 | 0.018182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 96 | 0.018182 | 0 | 0 | 0 | 0 | 0.018182 | 0 | 0.21231 | 0 | 0.21231 | 0 | -0.19413 | 0.21231 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-20 | 2019-09-06 | [27 empty] | Paradise | Butte | 39.7726 | -121.6031 |  |  |  |  | 2019 | [5 empty] | Y
35100244 |  | 2020 |  | BUCOCAMPT 1411 RAMADA LN PARADISE |  |  | CLSD |  | 0 | 380 | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 380 | 0.07197 | 0 | 0 | 0 | 0 | 0.07197 | 0 | 0.055303 | 0 | 0.055303 | 0 | 0.016667 | 0.055303 |  |  |  |  | N/A | [5 empty] | 2019-09-09 | 2019-09-09 | 2019-09-13 | [29 empty] | 39.7539 | -121.5925 |  |  |  |  | 2019
35100245 |  | 2020 |  | BUCOCAMP 5706 PARADISE AVE PARADISE |  |  | CLSD |  | 0 | 412 | 412 | 0.07803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 412 | 0.07803 | 0 | 0 | 0 | 0 | 0.07803 | 0 | 0.07803 | 0 | 0.07803 | 0 | 0 | 0.07803 |  |  |  |  | N/A | [5 empty] | 2019-08-02 | 2019-08-02 | 2019-07-19 | [27 empty] | Paradise | Butte | 39.7536 | -121.5971 |  |  |  |  | 2019
35100980 |  | 2020 |  | BUCOCAMPT 1736 PINEY RIDGE DR PARADISE |  |  | DOCC |  | 0 | 510 | 510 | 0.096591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 510 | 0.096591 | 0 | 0 | 0 | 0 | 0.096591 | 0 | 0.16799 | 0 | 0.16799 | 0 | -0.071402 | 0.16799 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-18 | [27 empty] | Paradise | Butte | 39.7951 | -121.5797 |  |  |  |  | 2019 | [5 empty] | Y
35100982 |  | 2020 |  | BUCOCAMPT 1428 JUNIPER LN PARADISE |  |  | CLSD |  | 0 | 853 | 853 | 0.16155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 853 | 0.16155 | 0 | 0 | 0 | 0 | 0.16155 | 0 | 0.043371 | 0 | 0.043371 | 0 | 0.11818 | 0.043371 |  |  |  |  | N/A | [5 empty] | 2019-08-28 | 2019-08-28 | 2019-08-28 | [7 empty] | 23678.41 |  |  |  | 30774.1 | [15 empty] | Paradise | Butte | 39.7744 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y
35101036 |  | 2020 |  | BUCOCAMP POLE_BURN - BARDEES BAR RD OROV |  |  | UNSC |  | 0 | 21684 | 21684 | 4.1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 21684 | 4.1068 | 0 | 0 | 0 | 0 | 4.1068 | 0 | 4.1068 | 0 | 4.1068 | 0 | 0 | 4.1068 |  |  |  |  | N/A | [35 empty] | Paradise | Butte | 39.7378 | -121.4774 |  |  |  |  | 2019
35101860 |  | 2020 |  | BUCOCAMP POLE_BURN HWY 70 OROVILLE |  |  | FICL |  | 0 | 25058 | 25058 | 4.7458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 25058 | 4.7458 | 0 | 0 | 0 | 0 | 4.7458 | 0 | 4.7458 | 0 | 4.7458 | 0 | 0 | 4.7458 |  |  |  |  | N/A | [7 empty] | 2019-06-21 | [27 empty] | Paradise | Butte | 39.7839 | -121.4494 |  |  |  |  | 2019
35101861 |  | 2020 |  | BUCOCAMP POLE BURN -CAMP CRK RD OROVILLE |  |  | UNSC |  | 0 | 22283 | 22283 | 4.2203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 22283 | 4.2203 | 0 | 0 | 0 | 0 | 4.2203 | 0 | 4.2203 | 0 | 4.2203 | 0 | 6.8901e-16 | 4.2203 |  |  |  |  | N/A | [37 empty] | 39.8741 | -121.3788 |  |  |  |  | 2019
35102732 |  | 2020 |  | BUCOCAMPT 2543 HONEY RUN RD CHICO |  |  | CLSD |  | 0 | 5147 | 5147 | 0.97481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 5147 | 0.97481 | 0 | 0 | 0 | 0 | 0.97481 | 0 | 0.97481 | 0 | 0.97481 | 0 | 0 | 0.97481 |  |  |  |  | N/A | [5 empty] | 2019-07-15 | 2019-07-15 | 2019-07-16 | [7 empty] | 187168.5 |  |  |  | 480388.7 | [17 empty] | 39.7482 | -121.6698 |  |  |  |  | 2019 | [5 empty] | Y
35103065 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR 108540 PH 1 |  |  | FICL | 12588 | 0 | 12599 | 12599 | 2.3862 | 369 | 0.069886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2019-07-26 |  |  | 2019-07-26 |  | 2019-07-26 |  |  | Yes | 2019-08-01 | [5 empty] | COMPLETED | No | No |  |  |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Just received as of 8/2 | Full |  |  | Yes |  |  | 43830 |  | 1980-01-01 | Y | [11 empty] | 12230 | 2.3163 | 369 | 0.069886 | 0 | 0 | 2.3862 | 0 | 2.3862 | 0 | 2.3862 | 0 | 0 | 2.3862 |  | Keep |  | Yes | COMP |  |  |  |  | 2019-09-12 | 2019-09-30 | 2019-12-21 | 2019-12-18 |  | Yes | Shovel Ready |  | 5151556.1 |  | -37865.9 | 5151555 | -1.1 |  |  | 5084914.2 | [5 empty] | 78 | [9 empty] | Orinda | Contra Costa | 37.852 | -122.1681 | E.5014544.01 |  |  |  | 2020 | Q1 | 2019-07-26 | 2020-01-02 | 2020-01-17 |  | Y | MORAGA 1101108540 | 319
35103110 |  |  |  | STS-COND_IDLE_REMV-2920 HOLLOWAY DR |  |  | CLSD |  | 0 | 105 | 105 | 0.019886 | 105 | 0.019886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 105 | 0.019886 | 0 | 0 | 0.019886 | 0 | 0.019886 | 0 | 0.019886 | 0 | 0 | 0.019886 |  | Keep |  |  | N/A | [7 empty] | 2020-01-15 | [29 empty] | 38.8989 | -120.8611
35103323 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  |  | DOCC | 6489 | 0 | 5875 | 5875 | 1.1127 | 5875 | 1.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2019-11-05 |  |  | 2019-11-05 |  | 2019-11-05 |  |  | Yes | 2020-01-24 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Bio AMMs for Alameda Whipsnake required | Full |  |  | Yes |  |  | Need extention of programatic permit |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 5875 | 1.1127 | 0 | 0 | 1.1127 | 0 | 1.1127 | 0 | 1.1127 | 0 | 1.7225e-16 | 1.1127 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-01-23 | 2020-03-21 | 2020-04-09 | 2020-02-25 |  | Yes | Shovel Ready |  | 3798645.9 |  |  | 4408478 | 609832.1 |  |  | 3437722.9 | [5 empty] | 48 | [9 empty] | Orinda | Contra Costa | 0 | 0 | E.5014544.02 |  |  |  | 2020 | Q1 | 2019-11-05 | 2020-01-02 | 2020-04-01 |  | Y | MORAGA 1101108540 | 319
35103324 |  | 2020 | 220 Mile Plan | CWSP - ROSSMOOR 1102 - OCB |  |  | CLSD | 4046 | 0 | 4046 | 4046 | 0.76629 | 1639 | 0.31042 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3063e-17 |  |  | DI | 08W | SH | 2019-08-02 |  |  | 2019-08-02 |  | 2019-08-02 |  |  | Yes | 2019-08-02 | [6 empty] | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Trying to release early | Full |  |  | Yes |  |  | On private property - no encroachment permit needed. |  | 1980-01-01 | Y | [11 empty] | 2407 | 0.45587 | 1639 | 0.31042 | 0 | 0 | 0.76629 | 4.3063e-17 | 0.76629 | 0 | 0.76629 | 0 | 0 | 0.76629 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-09-26 | 2019-10-15 | 2020-03-17 | 2020-03-17 |  | Yes | Shovel Ready |  | 2510809 |  |  | 2510809 | 0 |  |  | 2486089.7 | [5 empty] | 21 | [9 empty] | Lafayette | Contra Costa | 0 | 0 | E.5014544.03 |  |  |  | 2020 | Q1 | 2019-08-02 | 2020-04-01 | 2020-04-19 |  | Y | ROSSMOOR 1102CB | 560
35103325 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1102 & 1104 - OCB |  |  | CLSD | 6506 | 3755 | 3159 | 6914 | 1.3095 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7225e-16 |  |  | DI | 08W | SH | 2019-09-04 |  |  | 2019-09-04 |  | 2019-09-04 |  |  | Yes | 2019-09-04 | [5 empty] | COMPLETED | No | YES |  |  |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | [REDACTED] to coordinate with [REDACTED] | Full |  |  | Yes |  |  | Submitted on 8/1 to [REDACTED]. Need SSSP |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 6914 | 1.3095 | 0 | 0 | 1.3095 | -1.7225e-16 | 1.3095 | 0 | 1.3095 | 0 | 1.7225e-16 | 1.3095 |  | Keep |  | Yes | COMP |  |  |  |  | 2019-10-15 | 2020-03-14 | 2020-03-14 | 2020-04-14 |  | Yes | Shovel Ready |  | 5435558.5 |  |  | 6187462 | 751903.5 |  |  | 5043980.6 | [5 empty] | 20 | [9 empty] | Orinda | Contra Costa | 0 | 0 | E.5014544.04 |  |  |  | 2020 | Q1 | 2019-09-04 | 2020-01-25 | 2020-03-20 |  | Y | MORAGA 1102CB | 1024
35103767 |  | 2020 |  | BUCOCAMPT 5428 PRINCETON WY PARADISE |  |  | CLSD |  | 0 | 251 | 251 | 0.047538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 251 | 0.047538 | 0 | 0 | 0 | 0 | 0.047538 | 0 | 0.16288 | 0 | 0.16288 | 0 | -0.11534 | 0.16288 |  |  |  |  | N/A | [5 empty] | 2019-08-13 | 2019-08-13 | 2019-08-10 | [7 empty] | 46473.7 |  |  |  | 86462.2 | [15 empty] | Paradise | Butte | 39.7457 | -121.644 |  |  |  |  | 2019 | [5 empty] | Y
35105132 |  | 2020 |  | BUCOCAMPT 3681 DION ROAD OROVILLE |  |  | FICL |  | 0 | 450 | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-07-31 | [55 empty] | 450 | 0.085227 | 0 | 0 | 0 | 0 | 0.085227 | 0 | 0.19602 | 0 | 0.19602 | 0 | -0.1108 | 0.19602 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | 2019-09-12 | 2019-09-12 | [27 empty] | Oroville | Butte | 39.7218 | -121.5237 |  |  |  |  | 2019
35106022 |  | 2020 |  | BUCOCAMPT 5548 KEMLYN LN PARADISE |  |  | FICL |  | 0 | 493 | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0.093371 | 0 | 0.060606 | 0 | 0.060606 | 0 | 0.032765 | 0.060606 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-20 | 2019-09-18 | [27 empty] | Paradise | Butte | 39.7484 | -121.625 |  |  |  |  | 2019 | [5 empty] | Y
35106025 |  | 2020 |  | BUCOCAMP 5389 NEWLAND ROAD PARADISE |  |  | CLSD |  | 0 | 734 | 734 | 0.13902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 734 | 0.13902 | 0 | 0 | 0 | 0 | 0.13902 | 0 | 0.13902 | 0 | 0.13902 | 0 | 0 | 0.13902 |  |  |  |  | N/A | [5 empty] | 2019-06-28 | 2019-06-28 | 2019-07-20 | [27 empty] | Paradise | Butte | 39.7485 | -121.5952 |  |  |  |  | 2019
35106027 |  | 2020 |  | BUCOCAMPT 6709 CHAPMAN LN PARADISE |  |  | CLSD |  | 0 | 325 | 325 | 0.061553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 325 | 0.061553 | 0 | 0 | 0 | 0 | 0.061553 | 0 | 0.061553 | 0 | 0.061553 | 0 | 0 | 0.061553 |  |  |  |  | N/A | [7 empty] | 2019-07-05 | [27 empty] | Paradise | Butte | 39.787 | -121.5726 |  |  |  |  | 2019
35106042 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  |  | FICL | 9801 | 0 | 9606 | 9606 | 1.8193 | 5727 | 1.0847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 |  |  | 2019-08-27 | 2019-09-07 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019)7/3 - 7/31: On track for 8/28/2: EEI submitted for 1st ADE Review - ADE TBD8/13: Request for [REDACTED] to assign ADE8/20: 1st ADE correction rtn to contractor8/22: EEI submitted for 2nd rvw [PRELIM DWG ready]8/22: ADE PPROVED - IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/1/19. Caltrans Permit | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 3879 | 0.73466 | 5727 | 1.0847 | 0 | 0 | 1.8193 | 0 | 1.8193 | 0 | 1.8193 | 0 | 0 | 1.8193 |  | Keep | 2019-12-19 | Yes | N/A | 2019-11-14 | 2020-05-14 17:00 | Yes | 2020-05-14 08:00 | 2019-10-07 | 2019-11-14 | 2020-05-14 | 2020-06-08 |  | Yes | Shovel Ready |  | 4332872.1 |  |  | 4524488 | 191615.9 |  |  | 4040877.6 |  |  | -27.67 |  |  | 50 | [9 empty] | Shingletown | Shasta | 40.4951 | -121.8557 | E.5014759.02 |  |  | 2020-071 | 2020 | Q1 | 2019-08-27 | 2019-11-14 | 2020-01-31 |  | Y | VOLTA 11021502 | 293
35106265 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  |  | FICL | 10118 | 0 | 9489 | 9489 | 1.7972 | 9033 | 1.7108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-12 |  |  | 2019-08-27 | 2019-09-14 | 2019-08-27 |  |  | Yes | 2019-10-17 | (Moved into 2019)7/3 - 7/31: On track for 8/98/7: EEI submitted for 1st ADE Review - ADE TBD8/13: Request for [REDACTED] to assign ADE8/20: 1st ADE correction rtn to contractor8/22: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]8/22: ADE Approved - IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | PERTC Requested 10/8/19CIF submitted 8/22/19. Caltrans Annual | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 456 | 0.086364 | 9033 | 1.7108 | 0 | 0 | 1.7972 | 0 | 1.7972 | 0 | 1.7972 | 0 | 0 | 1.7972 |  | Keep | 2020-03-12 | Yes | N/A | 2019-10-05 08:00 | 2020-02-17 | Yes | 2020-02-17 | 2019-10-22 | 2019-11-25 | 2020-02-17 | 2020-06-08 |  | Yes | Shovel Ready |  | 3742002.6 |  |  | 4257794 | 515791.4 |  |  | 3548848.9 | [5 empty] | 51 | [9 empty] | Shingletown | Shasta | 40.493 | -121.8591 | E.5014759.02 |  |  | 2020-072 | 2020 | Q1 | 2019-08-27 | 2019-11-25 | 2020-02-17 |  | Y | VOLTA 11021502 | 293
35106277 |  | 2020 |  | BUCOCAMP 1895 MARYWOOD DR PARADISE |  |  | FICL |  | 0 | 291 | 291 | 0.055114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 291 | 0.055114 | 0 | 0 | 0 | 0 | 0.055114 | 0 | 0.055114 | 0 | 0.055114 | 0 | 0 | 0.055114 |  |  |  |  | N/A | [5 empty] | 2019-09-17 | 2019-09-17 | 2019-09-17 | [29 empty] | 39.74 | -121.5727 |  |  |  |  | 2019
35106331 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  |  | DOCC | 12968 | 0 | 12307 | 12307 | 2.3309 | 12307 | 2.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-03-04 |  |  | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-10-18 | (Moved into 2019) 7/3 - 8/14: On track for 8/16 8/19: EEI submitted for 1st ADE rvw 8/19: 1st ADE corrections rtn to contractor 8/21: EEI submitted for 2nd ADE rvw [PRELIM DWG ready] 8/22: 2nd ADE review complete - routing for approval 8/28: reported to be IN PEND --> [RCC Issue] 9/27 EOD push |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | PERTC Requested 10/8/19 CIF submitted 8/23/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 12307 | 2.3309 | 0 | 0 | 2.3309 | 0 | 2.3309 | 0.15909 | 2.49 | 0 | 0 | 2.3309 |  | Keep | 2020-03-04 | Yes | N/A | 2019-11-22 | 2020-05-28 08:00 | Yes | 2020-05-28 | 2019-10-22 | 2020-02-10 | 2020-05-28 | 2020-05-28 |  | Yes | Shovel Ready |  | 4901211.5 |  |  | 6122412 | 1221200.5 | 246100.3 |  | 4653604.3 | 1506.9 | 4655111.2 |  |  |  | 65 | [9 empty] | Shingletown | Shasta | 40.4974 | -121.8473 | E.5014759.02 |  |  | 2020-073 | 2020 | Q1 | 2019-08-27 | 2020-01-31 | 2020-03-08 |  | Y | VOLTA 11021502 | 293
35107688 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  |  | FICL | 8915 | 0 | 8626 | 8626 | 1.6337 | 8626 | 1.6337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 |  |  | 2019-11-04 | 2019-11-04 | 2019-11-04 |  |  | Yes | 2019-11-04 | (Moved into 2019)7/3 - 7/10: On track for 8/97/10 - 7/16: fielding issue with locked gate and dogs. Received new customer contact7/24 - 7/31: Access issues 8/07: Access issues continue - ALL date push 1 wk for resolution activity8/14 - 8/21: Still in progress of resolving Access issue, w/ PGE support8/21: Will submit for review in 2 parts (part 1 ready/ part 2 3 Locs - Access issues) - EEI to forward Part2 information for PGE support8/22: EEI PT1 submitted for 1st ADE rvw - pending PT2: Access issues x3 LOC (16 17 18) -working with Electric Outreach and it sounds like the contact information we have on record is incorrect (Dogs & Locked Gates)9/04: On Track for 9/30 - fielding to be concluded tomorrow.9/09: EEI PT2 submitted for 1st ADE rvw9/11 - 9/18: ADE to be assigned (push)9/25: Owner ADE coming online - ADE to be assigned this week - Holding target dates - UPDATE: ADE assigned to [REDACTED] 9/2510/02: In Review - 1st ADE target set to 2wk from assignment10/03: ADE 1st rvw corrections rtn to contractor - requesting HFTD peak wind load case. The estimator is saying they were directed to use [REDACTED] load case. (V8 vs V9)10/08: EEI did start and complete this estimate back in July and August, PGE just now getting around to checking the job. Move forward with the estimate as designed unless directed from standards or construction that to update the estimate ( [REDACTED] ); [REDACTED] concurred, in progress ok to finish V8.10/09: 1st rvw target moved to 10/11 - [REDACTED] to confirm 1st review with ADE Ver810/14: ADE returned 1st rvw corrections to contractor - revise and resub10/16: PGE - Areas needing helicopter - inquires in about using composite poles, answers expected by EOW for contractor10/16 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 8/21/19. Caltrans Permit | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 8626 | 1.6337 | 0 | 0 | 1.6337 | 0 | 1.6337 | 0 | 1.6337 | 0 | 0 | 1.6337 |  | Keep | 2019-12-19 | Yes | N/A | 2020-01-07 | 2020-04-10 08:00 | Yes | 2020-04-10 08:00 | 2019-11-07 | 2020-02-17 | 2020-04-10 | 2020-04-10 |  | Yes | Shovel Ready |  | 3932634.5 |  |  | 4120715 | 188080.5 |  |  | 3620857.3 | [5 empty] | 45 | [9 empty] | Shingletown | Shasta | 40.4948 | -121.873 | E.5014759.01 |  |  | 2020-070 | 2020 | Q1 | 2019-11-04 | 2020-02-17 | 2020-03-12 |  | Y | VOLTA 11021502 | 293
35107689 |  | 2020 | 220 Mile Plan | OCGC CWSP - PINE GROVE 1102 - LR1222 - |  |  | DCNL | 10853 | 0 | 11057.2 | 11057.2 | 2.0942 | 11057.2 | 2.0942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-04-30 |  |  | 2019-11-30 | 2019-11-18 | 2019-11-30 |  |  | Yes | 2020-01-29 | 12/25: SAP Export - PEND11/14: ADE APPROVED FOR routing11/13: EN submitted for 2nd ADe rvw11/05: Team assigned to corrections - Volta 2.4 prioritized; Push to EOW [11/08]10/29: Target to submit by Friday10/22 <-- 10/15: Push - EN requesting clarity on differing approach information from PGE (ADE/Planner - CMCS..Construction Notes...); and remaining correction information from ADE10/10: 1st ADE corrections rtn to contractor10/09: ADE assigned ( [REDACTED] )10-08 <-- 9/24: ADE to be assigned9/18: EN submitted for 1st ADE rvw9-17 <-- 9/10: Working with ADE to ensure quality is what ADE is looking for (Elevation Standards), Push to Monday 9/16; 9/189/03: On Track for 9/108/13 Fielding planned for EOM (Aug) |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-04-30 | 2020-04-30 |  |  |  |  | Full |  |  | Full |  |  | PERTC released - Caltrans due on 4/20 - Dist. 10 - ERTC to be issued before this date. Received Caltrans permit and are releasing an ERTC for a GC yard as well. | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 11057.2 | 2.0942 | 0 | 0 | 2.0942 | 0 | 2.0942 | 0 | 2.0942 | 0 | 0 | 2.0942 |  | Keep |  | Yes | COMP |  |  |  |  | 2020-01-30 | 2020-03-31 | 2020-05-12 | 2020-05-11 |  | Yes | Shovel Ready |  | 4631785.2 |  |  | 5851741 | 1219955.8 |  |  | 3462511.9 | [5 empty] | 55 | [9 empty] | Pioneer | Amador | 38.436 | -120.5561 | E.5014745.01 |  |  | 2020-023 | 2020 | Q1 | 2019-11-18 | 2020-02-07 | 2020-04-30 |  | Y | PINE GROVE 11021222 | 20
35109540 |  | 2020 | 220 Mile Plan | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  |  | DOCC | 7717 | 0 | 7065 | 7065 | 1.3381 | 7065 | 1.3381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-09 |  |  | 2019-10-09 | 2019-10-09 | 2019-10-09 |  |  | Yes | 2019-10-30 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/7 : On track8/14: Finishing internal rvw - 8/168/21: Finalizing Internal QUES rvw - 8/238/21: QUES submitted for 1st ADE rvw8/22: ADE assigned - [REDACTED] 23: 1st ADE corrections rtn to contractor9/03: ADE returned (Final) review for corrections9/04: Target submittal 9/5 --> [RCC Issue]9/11: Working through final request (ADE needs pictures), looking at options avoid refielding in order to submit this week. If field activity is avoidable - target EOW submittal.9/18: QUES submitted for 2nd ADE rvw9/20: Rvw rtn to Contractor; QUES submitted for 3rd ADE rvw9/24: Rvw completed by ADE; Ready for routing9/25: Target for routing - EOW 9/2710/02: pending routing10/09: Status? Complete by 10/08? - Casey approved on 10/04 - SAP glitch-tag submitted to correct status |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19. Expedite if OH | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7065 | 1.3381 | 0 | 0 | 1.3381 | 0 | 1.3381 | 0 | 1.3381 | 0 | 0 | 1.3381 |  | Keep | 2019-10-03 | Yes | N/A | 2019-10-16 | 2020-02-18 | Yes | 2020-02-18 | 2019-12-07 |  |  | 2020-02-18 |  | Yes | Shovel Ready |  | 3189967 | 2053626.5 | 75000 | 4228889 | 1038922 |  | 64.37% | 1978626.5 |  |  | -186.606 | 1534769.6985 |  | 39 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.02 |  |  |  | 2020 | Q1 | 2019-10-09 | 2020-01-02 | 2020-02-20 |  | Y | EL DORADO PH 210119752 | 13
35109541 |  |  |  | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  |  | ESTS | 14086 | 1279 | 12807 | 14086 | 2.6678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6678 | 14086 | 2.6678 | SI | 08W | SH | 2022-02-24 17:00 |  |  | 2021-02-28 | 2020-10-31 | 2021-02-28 | 2019-10-18 | 2019-10-18 |  |  | 11/04: Submitted to [REDACTED] escalating for approval on approach proposal; also going to have an easement [PUSH 4-6 months]10/28: [REDACTED] looking at OH proposal; with UG for crossings after walk10/21: Meeting Monday with county in person for job walk10/14 - 10/07: Pending PG&E and county survey09/02: EOD Impact - Push to DEC; will firm up impacts/work with County8/26: Contract signed with 3rd party surveyor; County found discrepancies with property lines, halted 5 projects08/26 - 08/12: ADE in rvw; EST - the JO asking for Transmission Survey to move forward with adding in the ROW’s for the undergrounding on this Brunswick job. As the road runs in and out of the properties for the 2 miles, there are many ROW’s and will take quite awhile08/05: EOD push out 1 month08/05 - 07/22: AT RISK - Equipment placement issues; County pushback on loc; more soil & retaining walls07/22 - 07/15: Waiting on Surveys/Land - Being resurveyed; PGE survey missing some info., need more specific information; Contracts needing to be developed/issued for 3rd party surveying. Anticipate 1 month push.07/08 - 05/13: EOD set to AUG; no change - Waiting for Survey; needs 3rd party engineering (EOD Sept)05/06: Per EST - (potential 2-3 month push anticipated); Land, County, Job Walk, etc....05/01: Waiting on results from [REDACTED] , survey04/29: EST to confirm submittal timeframe04/15: Transmission survey dependancy - feedback needed to assess EOD risk. Work involved a little more extensive04/08: Waiting on survey (around 4/10); Change order and field needs expected.04/01: Applying changes;03/18: Rcving Maps - Going to Google earth/overlays - Meeting; more update coming next week02/20 - 02/19: EST - Check in on base maps; [REDACTED] - just finished going through it, Coordination with EST to take a look and talk if you have any questions.01/29: Confirm Target date EOD...01/23: Per [REDACTED] |  |  |  | 2021 - Q1- M2 [R2021_80] | Iss_R1.3 - EST Implementing Corrections | No | Wood | 74 | 0 | [15 empty] | Full |  |  | ? OH to UG for permitting  CIF submitted 8/26/19. Still needs complete land review -CIF submitted 8/26/19. EDNF OH to UG |  |  |  | Yes |  |  | CIF submitted 8/26/19 |  | 2020-06-20 | Y | 2020-05-21 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6678 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-24 17:00 |  | INPR | 2022-07-01 08:00 | 2022-11-11 17:00 |  | 2023-01-12 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  | 900000 | 538746.2 |  | 900000 | 0 | 215028.1 | 59.86% | 536337.2 | 148634.7 | 684971.9 |  | 201943.7694 |  | 71 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 0 | 0 | E.5015417.03 | ML |  | 2021-080 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-10-31 |  | Y | EL DORADO PH 210119752 | 13 |  |  |  | 2021-03-01 12:35
35109542 |  |  |  | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  |  | FICL | 9724 | 0 | 9673 | 9673 | 1.832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 |  |  | 2019-08-23 | 2019-09-27 | 2019-08-23 |  |  | Yes | 2019-08-23 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/7 : On track8/8: QUES Submitted for 1st ADE rvw - ADE Carlos8/20: Corrections rtn to contractor[PRELIM DWG ready]8/23: Approved - PEND (per [REDACTED] |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19 - Expedite if OH | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y | [11 empty] | 9673 | 1.832 | 0 | 0 | 0 | 0 | 1.832 | 0 | 1.832 | 0 | 1.832 | 0 | 0 | 1.832 |  |  | 2019-11-20 |  | N/A | 2019-09-16 | 2019-11-09 | Yes | 2019-11-09 | 2019-09-16 |  |  | 2020-01-30 |  |  |  |  | 2785685.9 |  |  | 3529311 | 743625.1 | 694021.8 |  | 1944988 | 146676.1 | 2091664.1 | -200.608 |  |  | 49 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.04 | MX |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13
35109543 |  |  |  | CWSP-EL DORADO 2101-19752- PHASE 1.5 |  |  | DOCC | 9909 | 0 | 8922 | 8922 | 1.6898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 |  |  | 2019-09-12 | 2019-09-27 | 2019-09-12 |  |  | Yes | 2019-09-12 | 7/3: QUES to review to provide review on 1st ADE Submital7/16: Request submitted for Job Walk w/ Construction; AB Loop terrain concerns (inclines and hvy vegetation)7/19: QUES Waiting for Construction to confirm a date ( [REDACTED] )7/31: Completed walk - Engineer submitting change - Dates to be reviewed upon receipt8/7 - 8/14 On Track for 8/168/15: QUES submitted for 1st ADE rvw - ADE TBD8/21: ADE [REDACTED] assigned8/22: ADE target for 1st Rvw Completion 8/26 latest8/23 ADE Review STARTED8/25: 1st ADE corrections returned to contractor9/04: QUES submitted for 2nd ADE rvw, [PRELIM DWG ready]; QUES to confirm copy sent to PM - RCC Issue9/11: RCC issue reported as resolved - [REDACTED] approved - need to finalize processing |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 7/30/19 - Expedite if OH | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y | [11 empty] | 8922 | 1.6898 | 0 | 0 | 0 | 0 | 1.6898 | 0 | 1.6898 | 0 | 1.6898 | 0 | 0 | 1.6898 |  |  | 2019-11-20 |  | N/A | 2019-10-03 | 2020-03-06 | Yes | 2020-03-06 | 2019-09-28 |  |  | 2019-12-07 |  |  |  |  | 3151028.8 |  |  | 3608462 | 457433.2 | 518683.7 |  | 2621459.5 | 10885.6 | 2632345.1 | -196.902 |  |  | 50 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015417.05 | MX |  |  | 2019 | Q4 |  |  |  |  | Y | EL DORADO PH 210119752 | 13 |  |  |  | 2021-03-01 13:06
35109545 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  |  | DOCC | 12893 | 0 | 12821 | 12821 | 2.4282 | 12821 | 2.4282 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1006e-15 |  |  | SI | 08W | SH | 2019-12-19 17:00 |  |  | 2019-11-08 |  | 2019-11-08 |  |  | Yes | 2019-11-13 | 11/12: APPROVED - PEND11/08: In Routing - Kicked back for corrections11/06: On Track for EOW10/31: CAL reviewed and relinked - ready for rvw10/30: Re-review QC check; cursory rvw surfaced errors - ADE on vacation10/23: Routed - awaiting approval10/18: ADE 2nd corrections rtn to contractor10/16: Check in with ADE - Starting Tomorrow; completing another project10/10: CAL Submitted for 2nd ADE Rvw [PRELIM DWG ready]10/09: On Track for 10/10: 2nd submittal10/03: ADE 1st corrections returned to contractor10/02 <-- 9/04: in Review; ADE Workload Impact - 10/02 Shaylin to follow up on status with ADE--> [RCC Issue]8/21: ADE Rvw still in progress - target 8/23 correction rtn to contractor8/2: CAL submitted for 1st ADE review - [REDACTED] 7/31 <-- 7/3: On track for 8/5; 1st submittal |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/5/19. Expedite if OH | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 12821 | 2.4282 | 0 | 0 | 2.4282 | -3.1006e-15 | 2.4282 | 0 | 2.4282 | 0 | 3.1006e-15 | 2.4282 |  | Keep | 2019-12-19 17:00 | Yes | N/A | 2019-12-02 08:00 | 2020-04-17 | Yes | 2020-04-17 | 2019-12-04 |  |  | 2020-04-17 |  | Yes | Shovel Ready |  | 4499650.7 | 3861591.2 | 75000 | 4499650 | -0.7 |  | 85.81% | 3786591.2 |  |  | 0 | 1590297.2885 |  | 65 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.02 |  |  |  | 2020 | Q1 | 2019-11-08 | 2019-12-02 | 2020-04-03 |  | Y | EL DORADO ph 210119752 | 13
35109546 |  |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  |  | ADER | 14639 | 1664 | 12975 | 14639 | 2.7725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7725 | 14639 | 2.7725 | SI | 08W | SH | 2022-03-24 17:00 |  |  | 2020-12-31 | 2020-10-31 | 2020-12-31 | 2020-06-02 | 2020-06-02 | Yes |  | [Composite to Wood - Sept List]11/10 - 10/21: ADE working other priority; vacation reminder Nov 9-1610/14: ADE In rvw; priority based10/09: CAL submitted for 3rd ADE rvw10/07: Submittal by 10/909/23: EST target sub (10/02)09/16: EST Conversion Complete08/12: EST in progress08/06: ADE rtn 2nd corrections to CO - OVERHEAD only/ UG pending; EST still getting info / changes to be applied08/05 - 07/15: EST - working with County on more specifics of rejection; working on details with LIDAR to be applied; County request(s) will require another contractor to be brought on (Piggy back with QUES - 30-60 day. Geo Tech dependancies (avg 60-90 day impact); EOD ??07/08: ADE rvw (push); ADE working with EST; El Dorado rejected some design (Lack of detail).07/01 - 06/03: ADE soft target (6/8); (6/19); (6/26)06/02: ADE/ EST - 2nd review, this will really be the first time haven't had the chance to go through the entire estimate - don’t see the CMCS drawing PDF’s in the link . The construction drawings are still missing some vital information. Please upload those as well and let me know when they are ready for me.06/02: CAL submitted for 2nd ADE rvw - [PRELIM DWG ready]; PMgr - would like to provide the preliminary plans to El Dorado County for there cursory review prior to moving this subject project to PEND; Please provide when comfortable with ‘underground’ scope review.05/27 - 05/20: EST on track; Had to apply a couple changes.05/13: EST target sub (5/28)05/12: ADE/EST coordinated on corrections; ADE advised EST to make all the changes, activate DS73 and route to [REDACTED] for his approval. Once you have received that, please upload the approved [REDACTED] to SAP. Remember to note in SAP as well05/06 - 04/29: |  |  |  | 2020 - Q4- M12 [R2021_82] | R3.2 - ADE Review in Progress | No | Wood | 94 | 10 | [15 empty] | Full |  |  | CIF Submitted 9/18/19. OH to UG for permitting only |  |  |  | Yes |  |  | Permit request sent 9/18/19 |  | 2020-05-27 | Y | 2020-05-04 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7725 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-24 17:00 |  | INPR | 2022-06-22 08:00 | 2022-11-02 17:00 |  | 2023-01-03 17:00 | [8 empty] | 900000 | 576073.2 |  | 900000 | 0 |  | 64% | 572172.8 |  |  |  | 207778.2974 |  | 74 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 0 | 0 | E.5015416.03 | TL |  | 2021-082 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-10-26 |  | Y | EL DORADO PH 210119752 | 13
35109547 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  |  | DOCC | 8196 | 0 | 8058 | 8058 | 1.5261 | 8058 | 1.5261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-17 |  |  | 2019-10-16 |  | 2019-10-16 |  |  | Yes | 2020-01-08 | 10//16 IN PEND10/14: ADE approved- Routed by CO10/14: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]10/09: ADE 1st corrections rtn to contractor10/08: ADE assigned ( [REDACTED] ) - 1st Rvw Set at 2 wks9/04 - 10/02: in Review; ADE Workload impact - 10/02 (push 2 wks)--> [RCC Issue]8/21: 1st Submittal in - (Potential AUG Priority GAP FILL)ADE assigned ( [REDACTED] )8/11: CAL submitted for 1st ADE rvw7/3 - 8/7: On track for 8/12 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/9/19 | Full |  |  | Yes | 2020-12-31 |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 8058 | 1.5261 | 0 | 0 | 1.5261 | 0 | 1.5261 | 0 | 1.5261 | 0 | 0 | 1.5261 |  | Keep | 2019-10-17 | Yes | N/A | 2020-01-06 | 2020-03-13 | Yes | 2020-03-13 17:00 | 2020-01-21 | 2020-01-06 | 2020-03-11 | 2020-03-13 |  | Yes | Shovel Ready |  | 3530636.4 | 3127144.1 | 75000 | 3530637 | 0.6 |  | 88.57% | 3085127.1 |  |  |  | 2049059.4252 |  | 41 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.04 |  |  |  | 2020 | Q1 | 2019-10-16 | 2020-01-02 | 2020-03-10 |  | Y | EL DORADO ph 210119752 | 13
35109548 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  |  | DOCC | 16324 | 0 | 15058 | 15058 | 2.8519 | 15058 | 2.8519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-02-19 17:00 |  |  | 2020-01-15 |  | 2020-01-15 | 2019-11-04 | 2019-11-04 | Yes | 2020-01-25 | 04/22: Reaffirmed - pole/change post est. per field request; direct/forward to [REDACTED] (Internal) Team03/11: Est time & rcpt of wood pole places availability at about same time as composite - EST on hold for a final decision; Forward information to J [REDACTED] or review and assess for internal assignment.03/04: EST rcv'd req to move to wood poles; per Construction - breaking ground - EST to review and advise on submittal date.*****12/31: Estimator change - to be stamped and uploaded upon OCalc completion12/30: Approval Rejected - for final corrections12/18: push 2wk: 133 PLCs - request for restamp - target EOW to complete/submit12/13: ADE rtn 3rd corrections to contractor - Doc Electronically signed.12/11: EOD Push - ADE notified 3rd rvw started 12/09 - Working in tandum with EST - target Friday 12/06: CAL submitted for 3rd ADE rvw12/04 - 11/27: On Track for 12/0611/20: Held - Composite pole impact; changes needed11/12: Push 1wk - ADE corrections returned to contractor (3rd rvw anticipated - qty of errors) |  |  |  | 2020 - Q1- M3 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ? Partial Release received. Only 1 pole not released. Easement acquired. 1 pole on USFS | Full |  |  | Yes | 2020-12-31 |  | Permit Request sent 8/16/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 15058 | 2.8519 | 0 | 0 | 2.8519 | 0 | 2.8519 | 0 | 2.8519 | 0 | 0 | 2.8519 |  | Keep | 2020-02-19 17:00 | Yes | N/A | 2020-01-27 | 2020-05-22 | Yes | 2020-05-22 | 2020-01-30 | 2020-01-27 | 2020-05-22 | 2020-05-22 |  | Yes | Shovel Ready |  | 5480368 | 5489335.1 | 450000 | 7082947 | 1602579 |  | 100.2% | 5382470.1 |  |  |  | 1924803.3821 |  | 82 |  | ADE Bandwidth | [7 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015416.05 |  |  |  | 2020 | Q1 | 2020-01-06 | 2020-01-02 | 2020-04-01 |  | Y | EL DORADO ph 210119752 | 13 |  |  |  | 2021-02-25 14:45
35109549 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  |  | DOCC | 6898 | 0 | 7062 | 7062 | 1.3375 | 3446 | 0.65265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 |  |  | 2019-09-18 | 2019-09-18 | 2019-09-18 |  |  | Yes | 2019-09-30 | 7/9: on track 7/197/16: on track 7/197/19: BCF submitted for 1st ADE Rvw7/26: ADE returned corrections to Vendor8/2: 2nd ADE review for this project was not required. Comments from the 1st ADE review have been addressed and the project has been routed for approval [Prelim DWG ready]8/27: [REDACTED] - ready for approval8/28: Concurrance req surfaced correction needs - [REDACTED] to submit for corrective action with Contractor8/30: Approvals for 35109549 have been successfully routed through EES8/27: ADER - Kicked back for corrections8/30: BCF Submitted for 3rd ADE Rvw--> [RCC Issue] 9/27 EOD push9/10: RCC Issues corrected9/16: Applying corections, Applied LATs & LONGs9/17: Ocalc change/Stamp - then ready to route9/18: In PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Partial Release. Veg scope provided 8/29/19. The poles are NOT on USFS. Since we are close to the USFS boundary, some tree removal or tree trimming may affect USFS lands, we need to notify FS for veg work that is happening adjacent to poles 22-25. | Full |  |  | Yes | 2020-12-31 |  | Permit request sent 7/24/19 |  | 1980-01-01 | Y | [11 empty] | 3616 | 0.68485 | 3446 | 0.65265 | 0 | 0 | 1.3375 | 0 | 1.3375 | 0 | 1.3375 | 0 | -1.7225e-16 | 1.3375 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-04 | 2020-04-17 | Yes | 2020-04-17 17:00 | 2019-09-30 | 2019-10-05 | 2020-04-17 | 2020-04-17 |  | Yes | Shovel Ready |  | 3123544.1 | 2813130 | 75000 | 3123544 | -0.1 | 459711.4 | 90.06% | 2635581 | 28251.7 | 2663832.7 | 0 | 2103274.7664 |  | 35 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.02 |  |  |  | 2020 | Q1 | 2019-09-18 | 2020-01-02 | 2020-03-20 |  | Y | EL DORADO ph 210119752 | 13
35109550 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 |  |  | DOCC | 9612 | 0 | 10111 | 10111 | 1.915 | 1537 | 0.2911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 |  |  | 2019-09-18 |  | 2019-09-18 |  |  | Yes | 2019-09-19 | 7/9 - 7/22: on track 7/267/26: BCF submitted for 1st ADE Rvw7/30: ADE [REDACTED] assigned8/6: ADE corrections returned to Contractor8/9: BCF submitted for 2nd ADE Rvw - corrections applied [Prelim DWG ready]8/9: Corrections addressed - routed for approval8/15: Routed for Approval ( [REDACTED] ) 8/29: Stamp/OCALCs uploaded to SAP9/03: Corrections (3rd round), sent to BCF - target completion 9/03 for correction submittal--> [RCC ISSUE] 9/27 EOD push9/10: BCF submitted for 3rd Rvw - RCC Issue corrected9/16: BCF - reported 'ready to route' - resolving validation error9/17: Error cleared - Adding LATs & LONGs; RCC issue to be corrected by 9/189/18: Moved into PEND/UNSC |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/1/19. Expedite if OH | Full |  |  | Yes | 2019-12-31 |  | Permit Request sent 8/1/19 |  | 1980-01-01 | Y | [11 empty] | 8574 | 1.6239 | 1537 | 0.2911 | 0 | 0 | 1.915 | 0 | 1.915 | 0 | 1.915 | 0 | 0 | 1.915 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-04 | 2020-01-31 | Yes | 2020-01-31 | 2019-10-03 | 2020-01-31 | 2020-01-31 | 2020-01-31 |  | Yes | Shovel Ready |  | 3044148 | 2923313.2 | 75000 | 3044150 | 2 | 91713.4 | 96.03% | 2848313.2 | 104121.4 | 2952434.6 | 0 | 1526564.5036 |  | 49 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.03 |  |  |  | 2020 | Q1 | 2019-09-18 | 2020-01-02 | 2020-01-31 |  | Y | EL DORADO ph 210119752 | 13
35109551 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 |  |  | DOCC | 7659 | 0 | 7579 | 7579 | 1.4354 | 1810 | 0.3428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-12 |  |  | 2019-09-12 | 2019-09-12 | 2019-09-12 |  |  | Yes | 2019-10-07 | 8/01: BCF submitted for 1st ADE Rvw8/2: ADE [REDACTED] cy assigned8/12: 1st ADE corrections rtn to contractor8/21: Target 1st correction submittal 8/228/22:BCF submitted for 2nd ADE Rvw - ISSUE - Issue of EES joint utility credits, [REDACTED] to support in resolution [Prelim DWG ready]8/29: issue in EES with the approvals screen being blank. I have submitted a ticket to estimating support 8/29: 2nd ADE Corrections rtn to contractor8/30: ADER - Kick Back for corrections9/03: Corrections targeted for completion and submittal 9/039/10: BCF Submitted for 3rd ADE rvw - RCC Issue corrected |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Partial ERTC Received. Poles on USFS Loc 15, 16, 40 | Full |  |  | Yes | 2020-12-31 |  | Permit Request sent 8/1/19 |  | 1980-01-01 | Y | [11 empty] | 5769 | 1.0926 | 1810 | 0.3428 | 0 | 0 | 1.4354 | 0 | 1.4354 | 0 | 1.4354 | 0 | -1.7225e-16 | 1.4354 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-10-08 | 2019-10-02 | 2020-04-17 | 2020-04-17 |  | Yes | Shovel Ready |  | 3172297.8 | 2761392 | 75000 | 3172299 | 1.2 | 341819.6 | 87.04% | 2686392 | 144086.2 | 2830478.2 |  | 1923756.4006 |  | 39 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.04 |  |  |  | 2020 | Q1 | 2019-09-12 | 2020-01-02 | 2020-03-20 |  | Y | EL DORADO ph 210119752 | 13
35109552 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  |  | DOCC | 11277 | 0 | 11175 | 11175 | 2.1165 | 1491 | 0.28239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-30 |  |  | 2019-08-29 | 2019-09-25 | 2019-08-29 |  |  | Yes | 2019-09-25 | 8/21: ADE 1st corrections rtn to contractor (minor corrections) 8/27: BCF target submittal 8/30 - will check to verify for earlier submittal (8/29) 8/27: BCF submitted corrections for 2nd ADE rvw [PRELIM DWG ready] 8/27: APPROVED by ADE - BCF routing through EDRS --> [RCC Issue] 9/27 EOD push 9/10: RCC Issue corrrected - Routed for Approval 9/17: On target - routing |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/8/19. Expedite if OH | Full |  |  | Yes | 2020-12-31 |  | Permit Request sent 8/8/19 |  | 1980-01-01 | Y | [11 empty] | 9684 | 1.8341 | 1491 | 0.28239 | 0 | 0 | 2.1165 | 0 | 2.1165 | 0 | 2.1165 | 0 | 3.4451e-16 | 2.1165 |  | Keep | 2019-09-30 | Yes | N/A | 2019-10-07 | 2020-02-11 | Yes | 2020-02-11 | 2019-09-28 | 2020-02-07 | 2020-02-07 | 2020-02-11 |  | Yes | Shovel Ready |  | 5804262.1 | 4622930.4 | 175000 | 5804263 | 0.9 | 1209507.2 | 79.64% | 4548604.4 | 46150.5 | 4594754.9 | -298.999 | 2184257.0481 |  | 57 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.05 |  |  |  | 2020 | Q1 | 2019-08-29 | 2020-01-02 | 2020-02-07 |  | Y | EL DORADO ph 210119752 | 13
35109553 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 |  |  | DOCC | 14414 | 0 | 14080 | 14080 | 2.6667 | 6611 | 1.2521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-20 |  |  | 2019-09-26 | 2019-09-26 | 2019-09-26 |  |  | Yes | 2020-03-23 | 7/9 - 8/13: on track 8/198/20: BCF submitted for 1st ADE rvw - ADE TBD8/22: ADE Assigned - [REDACTED] 9/03: Still in ADE Review--> [RCC Issue]9/10 RCC Issue corrected - Still in review9/13: 1st ADE corrections rtn to contractor9/16: BCF Applying corrections9/17: Corrections on target9/19: BCR submitted for 2nd ADE rvw9/23: 2nd Rvw corrections Rtn to Contractor (Some OCalcs incorrect)9/23: BCR submitted for 3rd ADE rvw |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 8/20/19 | Full |  |  | Yes | 2021-04-29 |  | Permit Request sent 8/20/19 |  | 1980-01-01 | Y | [11 empty] | 7469 | 1.4146 | 6611 | 1.2521 | 0 | 0 | 2.6667 | 0 | 2.6667 | 0 | 2.6667 | 0 | 0 | 2.6667 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-21 | 2020-01-29 | Yes | 2020-01-29 | 2020-03-23 |  |  | 2020-01-29 |  | Yes | Shovel Ready |  | 4009924.5 | 3905827.7 | 75000 | 4009924 | -0.5 | 68154.9 | 97.4% | 3830827.7 | 110941.9 | 3941769.6 | 0 | 1464685.3875 |  | 73 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015415.06 |  |  |  | 2020 | Q1 | 2019-09-26 | 2020-01-02 | 2020-01-29 |  | Y | EL DORADO ph 210119752 | 13
35109554 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  |  | DOCC | 7044 | 0 | 6641 | 6641 | 1.2578 | 6641 | 1.2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-05 |  |  | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2019-09-04 | 2019-09-04 | Yes | 2020-01-17 | 03/26 pole needed to be moved about 10' out of the gully it's currently in 01/15: Routed - reviewed; request for final corrections01/14: QUES submitted for ADE final check01/13: QUES submitted for 5th ADE rvw - ADE rtn 5ht corrections; fix loc and route01/03: ADE rtn 4th corrections to contractor - large amount of corrections12/20: QUES submitted for 4th ADE rvw (2) - applied v8 adjustments12/18: On Track for submittal12/11: EOD push to apply ADE design change request12/10: ADE review on hold for EST to correct pole classes (-008 Fire Rebuild Design Guidance)12/09 QUES submitted for 4th ADE rvw11/27: Applying additional corrections from last review 11/20: Design change impact extended rvw process11/14: ADE rtn 3rd corrections to contractor11/13: Check target with ADE - Target by EOW11/06: Redesign/ADE - Resourcing Push for rvw timing.11/05: Submitted for 3rd ADE rvw10/29: In stamping: Target by EOW10/23: Resolution being finalized - Submittal target 10/2510/17: Est - No option to select PLDBID, believe this must be because job was set up in EES prior to the update on EES which brought in the Estimate Structure Builder. - Estimator seeking assistance for a fix.10/17: Per ADE - this job was not approved before the deadline of the implementation of the new PLDBID requirements in EES, this information is required to be inputted before it can be approved by ADE's 10/16: Redoing OCALCS, ADE requested change/information - Wens 23rd target for submittal10/09: Can EOD be held for final processing? (4day push otherwise)10/08: Working Tie-ins with 35057018 - 2nd corrections rtn to contractor9/24 - 10/02: In Review; 10/02 [REDACTED] reached out for status update (waiting on joint pole)9/16: ADE was pulled for previously scheduled work, returned to review.9/11: In Review--> [RCC Issue]9/04: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]8/27: ADE assigned8/23: QUES submitted for 1st ADE rvw8/21: CAD completed - submittal by 8/23 - Assign ADE [REDACTED] when rcv'd8/16: Submitting Friday - stuck in CAD 8/167/24 - 8/07: On Track7/3 |  |  |  | Completed | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/23/19. Expedite if OH | Full |  |  | Yes | 2020-12-31 |  | [REDACTED] to review on 8/20. Permit request sent 8/23/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 6641 | 1.2578 | 0 | 0 | 1.2578 | 0 | 1.2578 | 0 | 1.2578 | 0 | 0 | 1.2578 |  | Keep | 2020-05-05 | Yes | COMP | 2020-02-13 | 2020-04-03 | Yes | 2020-04-03 | 2020-02-04 |  |  | 2020-04-03 |  | Yes | Shovel Ready |  | 2276638 | 2132272.5 | 75000 | 2287663 | 11025 |  | 93.65% | 2058021.5 |  |  |  | 1695286.6737 |  | 36 |  | Veg Started | [7 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.02 |  |  |  | 2020 | Q1 | 2020-01-17 | 2020-02-13 | 2020-03-31 |  | Y | EL DORADO ph 210119752 | 13
35109555 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  |  | DOCC | 11846 | 0 | 11678 | 11678 | 2.2117 | 7702 | 1.4587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-08 |  |  | 2019-11-08 | 2019-11-08 | 2019-11-08 |  |  | Yes | 2019-12-20 | 11/06: ADE unable to 'concur' - working with EES team to resolve issue - Brian K working Rvw and directed on work around to clear EES errors. 11/01: QUES submitted for EES approval - corrections in process 10/29: Reassigned Estimator: corrections and routing targeted for EOW 10/25 ADE rtn 2nd correction to contractor - correct for routing 10/22: ADE rtn from vaca - targeting rvw 10/23 10/16: Check in with ADE - push 5day 10/08: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready] 10/02: 2nd submittal target - 10/11; volume of changes - Wood conversion, internal changes 9/25: Target for submittal 9/27 - QUES to advise of change 9/18: Email to leave as Version 8 / not worry about composite poles: Est. to be converted back to wood. 9/11:on target 9/09: 1st review returned to contractor --> [RCC Issue] 9/04: in Review 8/21: ADE assigned 8/13: QUES submitted for 1st ADE rvw 8/07: On Track for 8/9 7/31: AutoCAD issues resolved, anticipated to submit by end of week. 7/24: AutoCAD issues; Risk of push 7/16: May push 1wk for Internal Review 7/3: QUES to review to provide review on 1st ADE Submital |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/5/19. Expedite if OH | Full |  |  | Yes | 2020-12-31 |  | Permit request sent 8/5/49 |  | 1980-01-01 | Y | [11 empty] | 3976 | 0.75303 | 7702 | 1.4587 | 0 | 0 | 2.2117 | 0 | 2.2117 | 0 | 2.2117 | 0 | 0 | 2.2117 |  | Keep | 2019-11-08 | Yes | N/A | 2019-12-09 | 2020-02-21 | Yes | 2020-02-21 | 2019-12-19 |  |  | 2020-02-21 |  | Yes | Shovel Ready |  | 4471950.5 | 3706462.1 | 75000 | 4477708 | 5757.5 | 646923.5 | 82.88% | 3634489.1 | 190537.9 | 3825027 | -390.892 | 1675810.9169 |  | 60 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.03 |  |  |  | 2020 | Q1 | 2019-11-08 | 2020-01-02 | 2020-02-21 |  | Y | EL DORADO ph 210119752 | 13
35109556 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 |  |  | DOCC | 2783 | 0 | 1618 | 1618 | 0.30644 | 1618 | 0.30644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-10-16 |  |  | 2019-08-26 | 2019-09-05 | 2019-08-26 |  |  | Yes | 2019-08-26 | 7/3 - 7/16: QUES to review to provide review on 1st ADE Submital7/24 - 7/31: On Track for 7/318/6: QUES submitted for 1st ADE Review - ADE TBD; Holding EOD8/1: ADE Assigned - [REDACTED] 15: 1st ADE corrections rtn to contractor8/21: 2nd submittal scheduled for 8/21 (today)[PRELIM DWG ready]8/26: Approved - PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Partial ERTC Received. Poles loc 20-26 | Full |  |  | Yes | 2020-12-31 |  | Permit Request sent 8/1/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 1618 | 0.30644 | 0 | 0 | 0.30644 | 0 | 0.30644 | 0 | 0.30644 | 0 | 0 | 0.30644 |  | Keep | 2019-10-16 | Yes | N/A | 2019-10-21 | 2020-03-06 | Yes | 2020-03-06 | 2019-10-15 | 2019-10-21 | 2020-03-06 | 2020-03-06 |  | Yes | Shovel Ready |  | 1116465.6 | 973206.2 | 75000 | 1197284 | 80818.4 | 131331.8 | 87.16% | 898206.2 | 86927.6 | 985133.8 | -47.181 | 3175852.1236 |  | 14 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015414.04 |  |  |  | 2020 | Q1 | 2019-08-26 | 2020-01-02 | 2020-03-13 |  | Y | EL DORADO ph 210119752 | 13
35109737 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.2 |  |  | FICL | 11274 | 0 | 11610 | 11610 | 2.1989 | 9642 | 1.8261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-11-23 |  |  | 2019-11-08 | 2019-11-08 | 2019-11-08 |  |  | Yes | 2019-11-08 | 11/05: ADE workload- in progress11/01: EN submitted for 3rd ADE rvw10/29: ADE requesting full OCALC report - Report is a consolidation of information, vs individual breakout for specific items. - Req support/feedback from OCALC grp.10/23: ADE rtn 3rd corrections to contractor10/22: ADE returned - requested to progress10/16: ADE to finalize processing10/10: Routed per EN - [REDACTED] on vacation this week (push)10/01 - 10/08: Minor corrections - EN Target for routing by 10/04 - How to Proceed? - ADE requested elevations late in processing (new standards implementation).9/25: ADE 2nd Rvw corrections rtn to Contractor9/10: EN Submitted for 2nd Review - [PRELIM DWG ready]9/10: Corrections complete - System planner on vaca (pending review)--> [RCC Issue]9/03: On Target for mid to EOW correction submittal8/27: Finializing correction - on track8/21: 1st ADE rvw sent to contractor8/20: 1st ADE review scheduled for completed and send to CO8/06: ADE que'd for review, in review process of another 08W - Target date requested - [REDACTED] 7/22: EN Submitted for 1st ADE Review7/16 <-- 7/9: on track for 7/18 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/8/19. | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 1968 | 0.37273 | 9642 | 1.8261 | 0 | 0 | 2.1989 | 0 | 2.1989 | 0 | 2.1989 | 0 | 0 | 2.1989 |  | Keep | 2019-11-23 | Yes | N/A | 2019-11-15 | 2020-03-16 08:00 | Yes | 2020-03-16 08:00 | 2019-11-08 | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | Yes | Shovel Ready |  | 5216877.5 |  |  | 5442195 | 225317.5 |  |  | 4572913.9 | [5 empty] | 57 | [9 empty] | Shingletown | Shasta | 40.5069 | -121.8223 | E.5015533.02 |  |  |  | 2020 | Q1 | 2019-11-08 |  | 2020-02-09 |  | Y | VOLTA 110253130 | 107
35109738 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.3 |  |  | FICL | 9616 | 0 | 10959 | 10959 | 2.0756 | 10959 | 2.0756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-19 |  |  | 2019-10-02 | 2019-10-03 | 2019-10-02 |  |  | Yes | 2019-10-02 | 7/9 - 8/13: on track for 8/288/20: BCF anticipates 8/22 for 1st ADE submittal8/27: Submitting today8/28: EEI Submitted for 1st ADE rvw9/03: On Target (potentially mid to EOW correction submittal)--> [RCC Issue]9/10: Pending ADE Assignment and review9/17: ADE assigned - [REDACTED] - EOD pushed/ADE resource availability9/17: ADE 1st Rvw corrections rtn to ContractorSecond Rvw - .... [PRELIM DWG ready]10/1: Will route when system planner routes for EDRS. Target 10/1-2 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/28/19. Caltrans Permit. ERTC pushed due to land - 10/1 poles located in wetland may cause a delay if it cannot be redesigned. | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 10959 | 2.0756 | 0 | 0 | 2.0756 | 0 | 2.0756 | 0 | 2.0756 | 0 | 0 | 2.0756 |  | Keep | 2019-12-19 | Yes | N/A | 2020-01-06 | 2020-05-28 08:00 | Yes | 2020-05-28 | 2019-11-06 | 2020-02-19 | 2020-05-28 | 2020-06-17 |  | Yes | Shovel Ready |  | 4484183.1 |  |  | 4773512 | 289328.9 |  |  | 4189309.9 |  |  | 0 |  |  | 49 | [9 empty] | Shingletown | Shasta | 40.499 | -121.8389 | E.5015533.03 |  |  |  | 2020 | Q1 | 2019-10-02 | 2020-02-20 | 2020-03-31 |  | Y | VOLTA 110253130 | 107
35109739 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.4 |  |  | DOCC | 12487 | 0 | 12344 | 12344 | 2.3379 | 5807 | 1.0998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 |  |  | 2019-09-20 | 2019-09-20 | 2019-09-20 |  |  | Yes | 2019-09-20 | 7/9: submitted for 1st review 7/22: Pending ADE corrections, Target 7/26 7/30: Corrections Pending 7/31: 1st ADE Review Completed, corrections in progress 8/1: EN req the Job Story/scope of work including units of conductor to install to submit the CIF for this project 8/07: Response received and corrections being applied - EN followed up w/ 2nd submitted - PRELIM DWG (Done) 8/15: ADE submitted for corrections - Vendor submittal 2nd ADE review scheduled for 8/23 8/27: Per EN - Submitting corrections 8/30 EN submitted for 3rd ADE review 9/01: Resent 9/03: CO corrections target submittal by EOW (3rd) --> [RCC Issue] 9/27 EOD push 9/9: EN routed for approval 9/10: EN/ADE workthough Q&A 9/17: Need update on ADE targets and EOD |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/7/19. | Full |  |  | Yes |  |  | Permit request sent 8/6/19 |  | 1980-01-01 | Y | [11 empty] | 6537 | 1.2381 | 5807 | 1.0998 | 0 | 0 | 2.3379 | 0 | 2.3379 | 0 | 2.3379 | 0 | 0 | 2.3379 |  | Keep | 2020-01-11 | Yes | N/A | 2019-10-19 | 2020-01-23 | Yes | 2020-01-23 | 2019-09-20 | 2020-01-31 | 2020-01-31 | 2020-01-23 |  | Yes | Shovel Ready |  | 5522835.9 |  |  | 5748253 | 225417.1 |  |  | 5295743.9 | [5 empty] | 63 | [9 empty] | Shingletown | Shasta | 40.5126 | -121.822 | E.5015533.04 |  |  |  | 2020 | Q1 | 2019-09-20 |  | 2020-02-02 |  | Y | VOLTA 110253130 | 107
35109753 |  |  |  | STS-COND_IDLE_REMV - R/O 32660 SECORT AL |  |  | CLSD |  | 0 | 73 | 73 | 0.013826 | 73 | 0.013826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 73 | 0.013826 | 0 | 0 | 0.013826 | 0 | 0.013826 | 0 | 0.013826 | 0 | 0 | 0.013826 |  | Keep |  |  | N/A | [7 empty] | 2020-01-24 | [29 empty] | 39.2047 | -120.841
35109755 |  |  |  | STS-COND_IDLE_REMV - 5280 FARVIEW CT W/T |  |  | DOCC |  | 0 | 45 | 45 | 0.0085227 | 45 | 0.0085227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 0 | 0 | 45 | 0.0085227 | 0 | 0 | 0.0085227 | 0 | 0.0085227 | 0 | 0.0085227 | 0 | 0 | 0.0085227 |  | Keep |  |  | N/A | [37 empty] | 39.7398 | -121.6338
35109764 |  |  |  | STS-COND_IDLE_REMV - YELLOW WOOD RD ON K |  |  | CLSD |  | 0 | 40 | 40 | 0.0075758 | 40 | 0.0075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 0 | 0 | 40 | 0.0075758 | 0 | 0 | 0.0075758 | 0 | 0.0075758 | 0 | 0.0075758 | 0 | 0 | 0.0075758 |  | Keep |  |  | N/A | [7 empty] | 2020-01-26 | [27 empty] | Feather Falls | Butte | 39.769 | -121.5015
35110440 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.5 |  |  | FICL | 14440 | 0 | 13964 | 13964 | 2.6447 | 13964 | 2.6447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-05 |  |  | 2019-09-13 | 2019-09-25 | 2019-09-13 |  |  | Yes | 2019-09-13 | 7/9 - 8/06: on track for 8/208/20: Submitting Tomorrow8/21: EN submitted for 1st ADE rvw9/03: On Target for mid to EOW correction submittal--> [RCC Issue]9/10: In Review9/11: ADE assigned to [REDACTED] - 1st ADE Corrections sent to [REDACTED] - In Review |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19. | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 13964 | 2.6447 | 0 | 0 | 2.6447 | 0 | 2.6447 | 0 | 2.6447 | 0 | 0 | 2.6447 |  | Keep | 2020-01-05 | Yes | N/A | 2020-02-01 | 2020-05-08 | Yes | 2020-05-08 08:00 | 2019-10-10 | 2020-03-13 | 2020-05-08 | 2020-05-08 |  | Yes | Shovel Ready |  | 5259268 |  |  | 5859212 | 599944 |  |  | 4003656.4 | [5 empty] | 73 | [9 empty] | Shingletown | Shasta | 40.522 | -121.8311 | E.5015533.05 |  |  |  | 2020 | Q1 | 2019-09-13 | 2020-02-20 | 2020-03-31 |  | Y | VOLTA 110253130 | 107
35110441 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH2.6 |  |  | MAPP | 11600 | 0 | 11791 | 11791 | 2.2331 | 11791 | 2.2331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-20 |  |  | 2019-10-03 | 2019-10-03 | 2019-10-03 |  |  | Yes | 2019-10-03 | 7/9 - 8/06: on track for 8/9 8/09: EEI Submitted for 1st ADE Rvw 8/20: ADE verified as assigned 8/23: 1st ADE corrections rtn to contractor 8/30: Estimator in field for week; review in progress 9/03: CO corrections target submittal by EOW --> [RCC Issue] 9/10: Corrections complete - System planner on vaca (pending review) 9/11: EEI submitted for 2nd Rvw - adding some corrections 9/12: EEI submitted for 2nd Rvw - final 9/14: 2nd ADE corrections rtn to contractor (completed the second review for this job. Please make minor corrections, upload job to SAP and route for approval. Also, please verify that the issues regarding 119-125 ) 9/17: EN route for approval target 9/17 (today) 9/17: EN submitted for 3rd ADE rvw 10/1: EN Routing for approval |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/9/19. | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 11791 | 2.2331 | 0 | 0 | 2.2331 | 0 | 2.2331 | 0 | 2.2331 | 0 | -3.4451e-16 | 2.2331 |  | Keep | 2019-12-20 | Yes | COMP | 2020-02-01 | 2020-05-04 | Yes | 2020-05-04 | 2019-10-25 | 2020-02-17 | 2020-05-04 | 2020-05-04 |  | Yes | Shovel Ready |  | 4221227 |  |  | 4651895 | 430668 |  |  | 3294883.6 |  |  | 0 |  |  | 58 | [9 empty] | Shingletown | Shasta | 40.5274 | -121.8352 | E.5015533.06 |  |  |  | 2020 | Q1 | 2019-10-03 | 2020-02-17 | 2020-03-31 |  | Y | VOLTA 110253130 | 107
35110442 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.2 |  |  | FICL | 7345 | 0 | 7155 | 7155 | 1.3551 | 162 | 0.030682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-11-20 |  |  | 2019-08-19 | 2019-09-12 | 2019-08-19 |  |  | Yes | 2019-10-02 | (Moved into 2019)7/3 - 7/31: On track for 8/27/31: EEI submitted for 1st ADE Review[PRELIM DWG ready]8/19: In PEND - settlement errors and mapping errors as all other 08W jobs. AP10 will not clear etc.. [REDACTED] is aware.9/11: Pushing EOD to clear issue--> [RCC Issue] 9/27 EOD push |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 8/19/19 | Full |  |  | Yes |  |  | Permit requested 8/19/19 |  | 1980-01-01 | Y | [11 empty] | 6993 | 1.3244 | 162 | 0.030682 | 0 | 0 | 1.3551 | 0 | 1.3551 | 0 | 1.3551 | 0 | 1.7225e-16 | 1.3551 |  | Keep | 2019-11-20 | Yes | N/A | 2019-12-02 | 2019-12-26 | Yes | 2019-12-26 | 2019-10-14 | 2019-11-02 | 2019-12-14 | 2020-05-28 |  | Yes | Shovel Ready |  | 4645014.2 |  |  | 4820085 | 175070.8 |  |  | 4396860.5 | [5 empty] | 37 | [9 empty] | Shingletown | Shasta | 40.5122 | -121.8041 | E.5015704.02 |  |  |  | 2020 | Q1 | 2019-08-19 | 2020-01-02 | 2020-01-16 |  | Y | VOLTA 11021648 | 283
35110443 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.3 |  |  | FICL | 6545 | 0 | 6630 | 6630 | 1.2557 | 845 | 0.16004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-12-23 |  |  | 2019-09-12 | 2019-09-10 | 2019-09-12 |  |  | Yes | 2019-09-10 | (Moved into 2019) 7/3 - 7/31: On track for 8/2 8/2: EEI submitted for 1st ADE Review [PRELIM DWG ready] 8/19: IN PEND - Volta PH 3.3 approved and into PEND. Same Settlement errors as the others and did not clear AP10 9/11: Pushing dates to clear issue |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 5785 | 1.0956 | 845 | 0.16004 | 0 | 0 | 1.2557 | 0 | 1.2557 | 0 | 1.2557 | 0 | 0 | 1.2557 |  | Keep | 2019-12-23 | Yes | N/A | 2019-12-03 | 2020-01-30 | Yes | 2020-01-30 | 2019-10-01 | 2019-12-04 | 2020-02-01 | 2020-06-08 |  | Yes | Shovel Ready |  | 4028438.4 |  |  | 4241038 | 212599.6 |  |  | 3712360.4 | [5 empty] | 33 | [9 empty] | Shingletown | Shasta | 40.5043 | -121.814 | E.5015704.03 |  |  |  | 2020 | Q1 | 2019-09-12 |  | 2020-02-16 |  | Y | VOLTA 11021648 | 283
35110444 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH3.4 |  |  | FICL | 8204 | 0 | 7783 | 7783 | 1.4741 | 3634 | 0.68826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 |  |  | 2019-09-12 | 2019-09-14 | 2019-09-12 |  |  | Yes | 2019-09-12 | (Moved into 2019)7/3 - 7/31: On track for 8/97/31: EEI submitted for 1st ADE Review8/2: ADE [REDACTED] assigned8/7: ADE ( [REDACTED] ) corrections returned to Contractor; EEI to review timeline to complete corrections8/21: 2nd submittal scheduled for this week, 8/23 latest8/21: EEI submitted OCALC ADE Rvw - 8/22: ADE in approval; once ConDWG & CMCS corrected - ok to concur this job. 9/04 - 9/11: Good to go - RCC issue [PRELIM DWG ready] |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 7/11/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 4149 | 0.7858 | 3634 | 0.68826 | 0 | 0 | 1.4741 | 0 | 1.4741 | 0 | 1.4741 | 0 | 0 | 1.4741 |  | Keep | 2020-01-11 | Yes | N/A | 2019-10-05 | 2020-02-06 17:00 | Yes | 2020-02-06 08:00 | 2019-09-13 | 2019-10-05 | 2020-02-06 | 2020-02-06 |  | Yes | Shovel Ready |  | 4369138.9 |  |  | 4551984 | 182845.1 | 720899.5 |  | 3593144 | 55095.4 | 3648239.4 |  |  |  | 42 | [9 empty] | Shingletown | Shasta | 40.5086 | -121.8083 | E.5015704.04 |  |  |  | 2020 | Q1 | 2019-09-12 |  | 2020-02-24 |  | Y | VOLTA 11021648 | 283
35110445 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.2 |  |  | DOCC | 10160 | 0 | 8668 | 8668 | 1.6417 | 1008 | 0.19091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2019-11-20 |  |  | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019)7/3 - 7/31: On track for 8/168/6: EEI submitted for 1st ADE review - ADE [REDACTED] /20: 1st ADE corrections rtn to contractor8/27: In PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/13/19 | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 7660 | 1.4508 | 1008 | 0.19091 | 0 | 0 | 1.6417 | 0 | 1.6417 | 0 | 1.6417 | 0 | 0 | 1.6417 |  | Keep | 2019-11-20 | Yes | N/A | 2019-10-16 08:00 | 2019-12-26 | Yes | 2019-12-26 | 2019-09-09 | 2019-10-16 | 2019-11-22 |  |  | Yes | Shovel Ready |  | 5440289.1 |  |  | 5440290 | 0.9 | 793010.4 |  | 4612481.1 | 34797.6 | 4647278.7 | -38.488 |  |  | 51 | [9 empty] | Shingletown | Shasta | 40.5264 | -121.747 | E.5015428.02 |  |  | 2020-182 | 2020 | Q1 | 2019-08-27 | 2020-01-02 | 2020-01-18 |  | Y | VOLTA 11029742 | 229
35110446 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.3 |  |  | FICL | 11030 | 0 | 11401 | 11401 | 2.1593 | 11401 | 2.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 |  |  | 2019-08-27 | 2019-09-21 | 2019-08-27 |  |  | Yes | 2019-08-27 | (Moved into 2019) 7/3 - 8/06: On track for 8/16 8/16: EEI submitted for 1st ADE rvw 8/20: 1st Corrections rtn to contractor 8/27: In PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/21/19 | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 11401 | 2.1593 | 0 | 0 | 2.1593 | 0 | 2.1593 | 0 | 2.1593 | 0 | 0 | 2.1593 |  | Keep | 2020-01-11 | Yes | N/A | 2020-01-13 08:00 | 2020-02-18 | Yes | 2020-02-18 17:00 | 2019-10-08 | 2020-01-13 | 2020-02-18 | 2020-07-01 |  | Yes | Shovel Ready |  | 4812157 |  |  | 4988877 | 176720 |  |  | 4263899.6 |  |  | -9.524 |  |  | 56 | [9 empty] | Shingletown | Shasta | 40.5305 | -121.7454 | E.5015428.03 |  |  | 2020-183 | 2020 | Q1 | 2019-08-27 | 2020-01-13 | 2020-02-16 |  | Y | VOLTA 11029742 | 229
35110447 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.4 |  |  | FICL | 6000 | 0 | 6198 | 6198 | 1.1739 | 6198 | 1.1739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-01-11 |  |  | 2019-09-18 | 2019-09-21 | 2019-09-18 |  |  | Yes | 2019-10-30 | (Moved into 2019)7/3 - 8/06: On track for 8/168/07: EEI Submitted for 1st ADE review - Request for [REDACTED] to assign ADE8/20: ADE reassigned to [REDACTED] /25: 1st ADE corrections rtn to contractor8/26 EEI Submitted for 2nd ADE rvw8/28: 2nd ADE corrections rtn to contractor - Waiting on PM stamp to route for approval--> [RCC Issue] 9/27 EOD push9/4 - 9/11: EEI cleared - ok to route - PRELIM DWG (Done)9/18 - RCC issue corrected |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 9/5/19 | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 6198 | 1.1739 | 0 | 0 | 1.1739 | 0 | 1.1739 | 0 | 1.1739 | 0 | 0 | 1.1739 |  | Keep | 2020-01-11 | Yes | N/A | 2020-01-27 | 2020-04-10 17:00 | Yes | 2020-04-10 08:00 | 2019-10-31 | 2020-01-27 | 2020-04-07 | 2020-07-01 |  | Yes | Shovel Ready |  | 4129565.6 |  |  | 4129566 | 0.4 |  |  | 4013101.3 | [5 empty] | 40 | [9 empty] | Shingletown | Shasta | 40.5334 | -121.7392 | E.5015428.04 |  |  | 2020-184 | 2020 | Q1 | 2019-09-18 | 2020-01-27 | 2020-02-21 |  | Y | VOLTA 11029742 | 229
35110448 |  | 2020 | 220 Mile Plan | CWSP-VOLTA 1102-LR 1648-PH4.5 |  |  | MAPP | 10000 | 0 | 10503 | 10503 | 1.9892 | 10503 | 1.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10301 | 1.9509 | NV | 08W | SH | 2020-03-13 08:00 |  |  | 2019-09-16 | 2019-09-23 | 2019-09-16 |  |  | Yes | 2020-09-21 | (Moved into 2019)7/3 - 8/06: On track for 8/168/08 -8/14: EEI Submitted for 1st ADE review - Request for [REDACTED] to assign ADEADE assigned8/23: EEI submitted for 1st ADE rvw (1-4 of 4)8/23: 1st corrections rtn to contractor - email 1-4 of 28/28: EEI submitted for 2nd ADE rvw (1-2 of 2)8/29: 2nd Rvw return to contractor - close enough now that when you make the corrections, please P.E. stamp the OCalc's, attach to SAP, and EDRS9/04: Routing Issues (EES?) - EEI has reached out to EES team for resolution support - PRELIM DWG (Done)--> [RCC Issue] 9/27 EOD push9/11: 3rd review return to contractor - very minor corrections. Once corrected, please go ahead and start the approval process through EES. |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 9/5/19 | Full |  |  | Yes |  |  | Shasta County Annual |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 10503 | 1.9892 | 0 | 0 | 1.9892 | 0 | 1.9892 | 0 | 1.9892 | 0 | 0 | 1.9892 |  | Keep | 2020-03-13 08:00 | Yes | N/A | 2020-02-03 08:00 | 2020-05-28 | Yes | 2020-05-28 | 2020-09-21 | 2020-04-06 | 2020-05-28 | 2020-05-28 |  | Yes | Shovel Ready |  | 5551376.3 |  |  | 6475096 | 923719.7 |  |  | 4619555.6 | [5 empty] | 85 | [9 empty] | Shingletown | Shasta | 40.5326 | -121.7349 | E.5015428.05 |  |  | 2020-185 | 2020 | Q1 | 2019-09-16 | 2020-02-14 | 2020-03-28 |  | Y | VOLTA 11029742 | 229
35110712 |  | 2020 |  | BUCOCAMPT 6359 OAK WAY PARADISE |  |  | CLSD |  | 0 | 2404 | 2404 | 0.4553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-07-31 | [55 empty] | 2404 | 0.4553 | 0 | 0 | 0 | 0 | 0.4553 | 0 | 0.12841 | 0 | 0.12841 | 0 | 0.32689 | 0.12841 |  |  |  |  | N/A | [5 empty] | 2019-09-07 | 2019-09-07 | 2019-09-07 | [7 empty] | 56862.45 |  |  |  | 134084.2 | [15 empty] | Paradise | Butte | 39.7776 | -121.6031 |  |  |  |  | 2019 | [5 empty] | Y
35110725 |  | 2020 |  | BUCOCAMPT 11521 AUREOLE WAY OROVILLE* |  |  | FICL |  | 0 | 281 | 281 | 0.05322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 281 | 0.05322 | 0 | 0 | 0 | 0 | 0.05322 | 0 | 0.26117 | 0 | 0.26117 | 0 | -0.20795 | 0.26117 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-18 | [27 empty] | Oroville | Butte | 39.7256 | -121.5108 |  |  |  |  | 2019
35110795 |  | 2020 |  | BUCOCAMPT 5150 CIRCLE LN PARADISE*ILB |  |  | CLSD |  | 0 | 936 | 936 | 0.17727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 936 | 0.17727 | 0 | 0 | 0 | 0 | 0.17727 | 0 | 0.16742 | 0 | 0.16742 | 0 | 0.0098485 | 0.16742 |  |  |  |  | N/A | [5 empty] | 2019-09-30 | 2019-10-04 | 2019-09-30 | [27 empty] | Paradise | Butte | 39.7378 | 121.5959 |  |  |  |  | 2019
35110799 |  | 2020 |  | BUCOCAMPT 1643 ALEXIS LN PARADISE |  |  | CLSD |  | 0 | 222 | 222 | 0.042045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-07-31 | [55 empty] | 222 | 0.042045 | 0 | 0 | 0 | 0 | 0.042045 | 0 | 0.0094697 | 0 | 0.0094697 | 0 | 0.032576 | 0.0094697 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-16 | [29 empty] | 39.757 | -121.582 |  |  |  |  | 2019
35110843 |  | 2020 |  | BUCOCAMPT 1068 MAPLE PARK DR PARADISE |  |  | CLSD |  | 0 | 377 | 377 | 0.071402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 377 | 0.071402 | 0 | 0 | 0 | 0 | 0.071402 | 0 | 0.21534 | 0 | 0.21534 | 0 | -0.14394 | 0.21534 |  |  |  |  | N/A | [5 empty] | 2019-08-06 | 2019-08-09 | 2019-08-10 | [29 empty] | 39.7609 | -121.6094 |  |  |  |  | 2019
35110849 |  | 2020 |  | BUCOCAMPT 5200 HEATHROW RD PARADISE |  |  | CLSD |  | 0 | 341 | 341 | 0.064583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 341 | 0.064583 | 0 | 0 | 0 | 0 | 0.064583 | 0 | 0.048485 | 0 | 0.048485 | 0 | 0.016098 | 0.048485 |  |  |  |  | N/A | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-08-31 | [7 empty] | 30515.83 |  |  |  | 69887.5 | [15 empty] | Paradise | Butte | 39.7377 | -121.5972 |  |  |  |  | 2019 | [5 empty] | Y
35110916 |  | 2020 |  | BUCOCAMPT 12994 MOHAWK WAY OROVILLE |  |  | DOCC |  | 0 | 503 | 503 | 0.095265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-07-31 | [55 empty] | 503 | 0.095265 | 0 | 0 | 0 | 0 | 0.095265 | 0 | 0.10076 | 0 | 0.10076 | 0 | -0.0054924 | 0.10076 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-07 | [29 empty] | 39.7735 | -121.4995 |  |  |  |  | 2019 | [5 empty] | Y
35110919 |  | 2020 |  | BUCOCAMPT 1290 LUCKY LADY LN PARADISE |  |  | CLSD |  | 0 | 480 | 480 | 0.090909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-07-31 | [55 empty] | 480 | 0.090909 | 0 | 0 | 0 | 0 | 0.090909 | 0 | 0.054924 | 0 | 0.054924 | 0 | 0.035985 | 0.054924 |  |  |  |  | N/A | [5 empty] | 2019-09-09 | 2019-09-09 | 2019-09-12 | [29 empty] | 39.7749 | -121.5995 |  |  |  |  | 2019
35111037 |  |  |  | +STS-COND_IDLE_REMV - 14655 HWY 41 1/P/N |  |  | FICL |  | 0 | 162 | 162 | 0.030682 | 162 | 0.030682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF | [60 empty] | 0 | 0 | 162 | 0.030682 | 0 | 0 | 0.030682 | 0 | 0.030682 | 0 | 0.030682 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-01-15 | [29 empty] | 35.461 | -120.7383
35111038 |  |  |  | +STS-COND_IDLE_REMV-11010 FUENTEDS R |  |  | CLSD |  | 0 | 4875 | 4875 | 0.9233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF | [60 empty] | 4875 | 0.9233 | 0 | 0 | 0 | 0 | 0.9233 | 0 | 0.9233 | 0 | 0.9233 | 0 | 0 | 0.9233 |  |  |  |  | N/A | [7 empty] | 2020-01-06 | [29 empty] | 35.4927 | -120.7772
35111096 |  | 2020 |  | BUCOCAMPT 1398 FOREST SERVICE RD PARADIS |  |  | CLSD |  | 0 | 136 | 136 | 0.025758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 136 | 0.025758 | 0 | 0 | 0 | 0 | 0.025758 | 0 | 0.18182 | 0 | 0.18182 | 0 | -0.15606 | 0.18182 |  |  |  |  | N/A | [5 empty] | 2019-09-17 | 2019-09-17 | 2019-08-27 | [29 empty] | 39.7849 | -121.5916 |  |  |  |  | 2019
35111500 |  |  |  | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD |  |  | CLSD | 3700 | 0 | 1850 | 1850 | 0.35038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-07-03 |  |  | 2019-07-03 |  | 2019-07-03 |  |  | Yes | 2019-09-05 | [22 empty] | Full |  |  | Full |  |  | 8/27/19 - Veg Scope submitted 8/29/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 1850 | 0.35038 | 0 | 0 | 0 | 0 | 0.35038 | 0 | 0.35038 | 0 | 0.35038 | 0 | 0 | 0.35038 |  |  |  |  | N/A |  |  |  |  | 2019-10-03 |  |  | 2019-12-16 |  |  |  |  | 425000 |  |  | 425000 | 0 |  |  | 418578.6 | [15 empty] | Lakeport | Lake | 0 | 0 | 35111500 |  |  |  | 2019 | Q1 |  |  |  |  | Y | UPPER LAKE 11016663 | 871
35112076 |  | 2020 | 220 Mile Plan | OCGC FULTON 1107-OH TO UG MARK W SPG |  |  | MAPP | 7980 | 3657 | 7969 | 11626 | 2.2019 | 10736 | 2.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4451e-16 |  |  | SO | 08W | SH | 2019-09-30 |  |  | 2019-09-30 |  | 2019-09-30 |  |  | Yes | 2019-11-19 | [5 empty] | 100 | Yes | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted Week of 8/12. Veg Scope Needed. CDFW requirements | Full |  |  | Yes |  |  | 10/1/2019 - working on permit revisions |  | 1980-01-01 | Y | [11 empty] | 890 | 0.16856 | 10736 | 2.0333 | 0 | 0 | 2.2019 | 3.4451e-16 | 2.2019 | 0 | 2.2019 | 0 | -3.4451e-16 | 2.2019 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-12-12 | 2020-03-10 | 2020-03-10 | 2020-04-06 |  | Yes | Shovel Ready | [14 empty] | 46 |  | Underground | [7 empty] | Santa Rosa | Sonoma | 0 | 0 | E.5024097.01 |  |  |  | 2020 | Q1 | 2019-09-27 | 2019-11-24 | 2020-03-23 |  |  | FULTON 1107214 | 178
35112425 |  | 2020 |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  |  | DOCC | 6744 | 0 | 6871 | 6871 | 1.3013 | 6871 | 1.3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-10 |  |  | 2019-10-23 | 2019-10-23 | 2019-10-23 |  |  | Yes | 2019-10-23 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/17: EEI submitted for 1st ADE rvw 9/04: ADE TBD --> [RCC Issue] 9/11 - 9/18: In Review; Change Order being submitted for 'composite change' *Job updated to composit poles 9/13: 1st ADE rvw rtn to contractor 9/23: EEI Submitted for 2nd ADE rvw 10/02: In Review 10/03 ADE 2nd rvw corrections rtn to contractor; submit for approval via EES, verify the appropriate tasks and dependencies are activated in the job 10/09: Routed on 10/08 - PGE to close for EOD target 10/11: ADE requested corrections to comments - EEI completed 10/15: Additional corrections provided to EEI in final review - updated dwg uploaded. 10/23: IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Submitted to forest service week of 12/10 | Full |  |  | Yes |  |  | No permit needed |  | 1980-01-01 | Y |  |  |  | Complete | [7 empty] | 0 | 0 | 6871 | 1.3013 | 0 | 0 | 1.3013 | 0 | 1.3013 | 0 | 1.3013 | 0 | 0 | 1.3013 |  | Keep | 2020-03-10 | Yes | N/A | 2020-05-04 | 2020-07-13 | Yes | 2020-07-21 17:00 | 2020-01-03 | 2020-05-04 | 2020-07-08 | 2020-07-21 |  | Yes | Shovel Ready |  | 2963552.3 | 2248913.2 | 44526.9 | 5238478 | 2274925.7 | 731857.5 | 75.88% | 2193938.2 | 37756.6 | 2231694.8 |  | 1728170.8188 |  | 34 | [9 empty] | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.02 |  |  |  | 2020 | Q2 | 2019-10-23 | 2020-03-16 | 2020-06-20 |  | Y | EL DORADO PH 2101CB | 76
35112426 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 |  |  | PREC | 9368 | 0 | 9077 | 9077 | 1.7191 | 39 | 0.0073864 | 0 | 0 | 0 | 0 | 0 | 0 | -2.1639e-15 |  |  | SI | 08W | SH | 2019-09-09 |  |  | 2019-09-09 | 2019-09-21 | 2019-09-09 |  |  | Yes | 2019-09-09 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: In Review 9/11: IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | PERTC Out in October, Partial Release. Forest service review in process starting 11/27 | Full |  |  | Yes |  |  | Drawings submitted 9/11/19 |  | 1980-01-01 | Y | [11 empty] | 9038 | 1.7117 | 39 | 0.0073864 | 0 | 0 | 1.7191 | -2.1639e-15 | 1.7191 | 0 | 1.7191 | 0 | 2.067e-15 | 1.7191 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-11-07 |  |  | 2019-12-21 |  | Yes | Shovel Ready |  |  |  | -259218 | [10 empty] | 47 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.03 |  |  |  | 2020 | Q1 | 2019-09-09 | 2020-01-02 | 2020-01-17 |  | Y | EL DORADO PH 2101CB | 76
35112427 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 |  |  | CLSD | 5221 | 0 | 5069 | 5069 | 0.96004 | 4692 | 0.88864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-13 |  |  | 2019-11-13 | 2019-11-13 | 2019-11-13 |  |  | Yes | 2019-11-13 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal8/13: EEI submitted for 1st ADE rvw8/28: ADE Assigned [REDACTED] /04: In Review9/04: ADE returned review - need more information - Contractor working with ADE on new information standards being requested. (Method to support req under review -OCALC cannot support request). Request will impact multiple projects.--> [RCC Issue]9/18: Completing corrections - target date for submittal to be submitted by EEI9/25: Corrections complete and submitted -Confirm statusx/xx: [REDACTED] requested class update to all poles/ all passing10/01: EEI Submitted for 2nd ADE Review 10/09: Review in process - [REDACTED] to advise on status for completion date (SAP shows construction DEC 2020)10/16: Rvw target EOW - per [REDACTED] /17: ADE rtn 2nd corrections to contractor10/29 <-- 10/23: EEI - submitting change order; poles converting to composite for inaccessibility purposes. EEI to update on new submittal target.10/31: EEI Submitted for 3rd rvw11/05: ADE rtn 3rd corrections to contractor - correct and route for approval11/07: Flagged Pole change out11/13: On Track for 11/15 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERCT Call Complete | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 377 | 0.071402 | 4692 | 0.88864 | 0 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0.96004 | 0 | 0 | 0.96004 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-11-25 |  |  | 2020-02-12 |  | Yes | Shovel Ready |  | 2336753.8 |  | -231631 | 3306693 | 969939.2 |  |  | 1848367.1 | [5 empty] | 27 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.04 |  |  |  | 2020 | Q1 | 2019-11-13 | 2019-12-18 | 2020-01-31 |  | Y | EL DORADO PH 2101CB | 76
35112428 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 |  |  | CLSD | 8571 | 0 | 8571 | 8571 | 1.6233 | 8571 | 1.6233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-12-03 |  |  | 2019-09-28 | 2019-09-28 | 2019-09-28 |  |  | Yes | 2020-01-06 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal 8/16: EEI submitted for 1st ADE rvw 9/04: ADE TBD 9/06: ADE review returned to contractor --> [RCC Issue] 9/11: In Review 9/17: ADE approved, Ocalcs being stamped - scheduled to route by EOW 9/25: Check on rerouting for approval - RCC issues resolved |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call Complete | Full |  |  | Yes |  |  | Drawings submitted 10/1/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 8571 | 1.6233 | 0 | 0 | 1.6233 | 0 | 1.6233 | 0 | 1.6233 | 0 | 0 | 1.6233 |  | Keep | 2019-12-03 | Yes | N/A | 2019-12-18 | 2020-02-27 | Yes | 2020-02-27 | 2020-01-13 | 2020-01-27 | 2020-02-24 | 2020-02-27 |  | Yes | Shovel Ready |  |  |  | -340669 | [10 empty] | 43 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.05 |  |  |  | 2020 | Q1 | 2019-09-28 | 2020-01-06 | 2020-02-13 |  | Y | EL DORADO PH 2101CB | 76
35112429 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  |  | MAPP | 7534 | 0 | 7341 | 7341 | 1.3903 | 7341 | 1.3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-26 |  |  | 2019-10-15 | 2019-10-15 | 2019-10-15 |  |  | Yes | 2020-01-07 | (Moved into 2019) 7/10 - 8/14: on with 8/16 submittal8/19: EEI submitted for 1st ADE rvw9/04: ADE TBD--> [RCC Issue]9/10: ADE assigned to [REDACTED] /11: ADE review returned to contractor9/18: Target correction submittal by EOW9/18: EEI submitted for 2nd ADE rvw - Corrections RTN to contractor10/01: ADE approved final rvw - ready to route10/09: EEI completing stamps - will route - should complete by EOW or early next week |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submtted 9/5/19. | Full |  |  | Yes | 2021-03-01 |  | Drawings submitted 9/5/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7341 | 1.3903 | 0 | 0 | 1.3903 | 0 | 1.3903 | 0 | 1.3903 | 0 | 0 | 1.3903 |  | Keep | 2019-11-26 | Yes | COMP | 2020-03-09 | 2020-07-07 | Yes | 2020-07-18 | 2019-12-26 | 2020-03-09 | 2020-07-10 | 2020-07-18 |  | Yes | Shovel Ready |  | 3891537.9 | 2336552.4 | 75000 | 5585619 | 1694081.1 | 1706577.2 | 60.04% | 2192851.4 | -7890.7 | 2184960.7 |  | 1680560.7781 |  | 38 | [6 empty] | No SCADA |  |  | Pollock Pines | El Dorado | 38.7883 | -120.6157 | E.5015420.06 |  |  |  | 2020 | Q2 | 2019-10-15 | 2020-03-16 | 2020-06-20 |  | Y | EL DORADO PH 2101CB | 76 |  |  |  | 2021-03-01 20:33
35112431 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  |  | CLSD | 8057 | 0 | 8117 | 8117 | 1.5373 | 8118 | 1.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 |  |  | 2020-07-24 | 2020-07-31 | 2020-07-24 |  |  | Yes | 2020-07-27 | 7/3: QUES to review to provide review on 1st ADE Submital 7/16 - 9/11: On track for 9/30; Note: EOD Nov --> [RCC Issue] 9/17: Hold at 9/30 - Potential 1 week push - Training/New Hire ramp up impact - tbd 9/25: Move to 10/8 - Composite Pole conversions 10/02: On track for 10/08; RISK of delay - Resource impact (down to 1 PE for stamping) 10/09: QUES submitted for 1st ADE Rvw 10/16: ADE to be assigned 10/21: ADE assigned (Walter) - Push 2wk - ADE 1st rvw duration 10/29: ADE rtn 1st corrections to contractor 10/30: Power outage impacts - EEI to follow up with status UD/confirm target date(s); Stamped OCALC for loc92 uploaded 11/06: QUES - still working through power issues; Est finalizing 11/13: QUES submitted for 2nd ADE rvw 11/16: ADE return 2nd corrections to contractor 11/25: QUES submitted for 3rd ADE rvw1 11/27: ADE rtn 3rd corrections to contractor 11/27:QUES submitted fro 4th ADE rvw 12/02: ADE apprv'd 12/04: Concur rtn - Correction (Txt size & DWG length not match OCalc and Fld Note) 12/11: Push to meet EOW completion |  |  |  | Completed | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes | 2021-03-01 |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. |  | 2020-08-14 | Y | 2020-06-16 |  |  | 90% complete as of 7/28 | [7 empty] | 0 | 0 | 8117 | 1.5373 | 0 | 0 | 1.5373 | 0 | 1.5373 | 0 | 1.5373 | 0 | 0 | 1.5373 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-03-03 | 2020-06-05 | 2020-10-01 | 2020-10-02 |  | Yes | Shovel Ready |  |  |  | 75000 | [10 empty] | 41 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.02 |  |  |  | 2020 | Q3 | 2019-12-12 | 2020-04-21 | 2020-05-27 |  | Y | EL DORADO PH 210219562 | 52
35112432 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  |  | DOCC | 12968 | 0 | 13228 | 13228 | 2.5053 | 13228 | 2.5053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-21 |  |  | 2020-07-21 | 2020-07-31 | 2020-07-21 | 2019-10-15 | 2019-10-15 | Yes | 2020-07-21 | 07/29: 1] JP lead with AT&T, has a call setup tomorrow to discuss; 2] project has been revised and now need a 95' class H3 pole. Can you check on availability 07/22: PEND: Last communication was Vendor/ [REDACTED] look into AT&T solution --> Joint Pole is going to vette issue with AT&T07/15: On Track07/14: EST routed for approval07/10: Issue flagged [redesign] - an AT&T line that will be too close in proximity to our 21kv line as it crosses a canyon once the new conductor is installed; calc'd location 87 for 55' pole due to construction determining clearance to phone was inadequate. need a 55'-H3 and a 20M anchor instead of a 45' pole and 15M anchor07/08 - 07/01: redesign - EOD (7/24) Original redesign changes applied and completed; |  |  |  | 2020- M7 [RRD-2020_Redesign] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes | 2021-03-01 |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. |  | 2020-06-26 | Y | 2020-04-19 |  |  | Started | [7 empty] | 0 | 0 | 13228 | 2.5053 | 0 | 0 | 2.5053 | 0 | 2.5053 | 0 | 2.5053 | 0 | 0 | 2.5053 |  | Keep | 2020-03-26 | Yes | N/A | 2020-05-08 08:00 | 2020-11-18 | Yes | 2020-11-18 | 2020-09-11 | 2020-05-08 | 2020-11-20 | 2020-11-18 |  | Yes | Shovel Ready |  | 3480529.7 | 3273097.6 | 75000 | 5345911 | 1865381.3 |  | 94.04% | 3199121.6 |  |  |  | 1306467.7448 |  | 65 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.03 |  |  |  | 2020 | Q2 | 2019-11-13 | 2020-04-27 | 2020-07-02 |  | Y | EL DORADO PH 210219562 | 52
35112433 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 |  |  | MAPP | 10344 | 0 | 10543 | 10543 | 1.9968 | 10543 | 1.9968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-26 |  |  | 2019-10-11 | 2019-10-11 | 2019-10-11 |  |  | Yes | 2019-10-11 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift9/04: QUES submitted for 1st ADE rvw--> [RCC Issue]9/11 - 9/25: ADE to be assigned9/26: ADE assigned to [REDACTED] /30: ADE 1st corrections rtn to contractor10/09: On tailend of revisions - stamping |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes |  |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 10543 | 1.9968 | 0 | 0 | 1.9968 | 0 | 1.9968 | 0 | 1.9968 | 0 | 0 | 1.9968 |  | Keep | 2020-03-26 | Yes | N/A | 2020-03-27 | 2020-05-01 | Yes | 2020-05-01 | 2019-12-10 | 2020-05-06 | 2020-05-06 | 2020-06-11 |  | Yes | Shovel Ready |  | 2867736.1 | 2775684.5 | 75000 | 4151673 | 1283936.9 |  | 96.79% | 2700837.5 |  |  |  | 1390080.0683 |  | 52 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.04 |  |  |  | 2020 | Q1 | 2019-10-11 | 2020-04-27 | 2020-06-09 |  | Y | EL DORADO PH 210219562 | 52
35112434 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  |  | DOCC | 7971 | 0 | 7924 | 7924 | 1.5008 | 7924 | 1.5008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 |  |  | 2020-07-24 | 2020-07-31 | 2020-07-24 | 2020-01-14 | 2020-01-14 | Yes | 2020-07-28 | 07/31: PMgr noted Redesign completed; moved back to CONS07/29 - 07/22: Pending response from [REDACTED] ; anticipate rtn feedback by EOW; EOD set 8/707/16: errors in design efforts for theses re-design tasks. Errors primarily effect phases 1.4 and 1.5 (see [REDACTED] email)07/15: QUES provided DWG/COST PDF07/15: Version 2 created; User Status change (EES - [REDACTED] ); [REDACTED] to follow up with reasons for Status changes.07/13: Changes Completed; uploaded to SAP; sent over to [REDACTED] - 07/08: On Track07/01: Internal Ocalc'd poles not in EES; EST unable to put into EES - seeking direction on how to apply - Construction redline? apprx 42 Poles/15 need material - EOD soft target (7/24)6/22 - ??: [Redesign] Wood Pole Conversion*****04/10: INTO PEND04/03: ADE rtn minor corrections - EST to apply and route04/02: QUES submitted for 4th ADE rvw |  |  |  | 2020- M8 [RRD-2020_Redesign] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 12/18/19 | Full |  |  | Yes | 2021-03-01 |  | Drawings submitted 12/18/19 |  | 2020-08-19 | Y | 2020-06-25 | [10 empty] | 0 | 0 | 7924 | 1.5008 | 0 | 0 | 1.5008 | 0 | 1.5008 | 0 | 1.5008 | 0 | 0 | 1.5008 |  | Keep | 2020-05-20 | Yes | N/A | 2020-07-27 08:00 | 2020-10-02 | Yes | 2020-10-02 | 2020-07-21 | 2020-07-27 | 2020-10-02 | 2020-10-02 |  | Yes | Shovel Ready |  | 2743160 | 2303881 | 75000 | 3756886 | 1013726 |  | 83.98% | 2240787 |  |  |  | 1535145.3407 |  | 40 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.05 |  |  |  | 2020 | Q3 | 2020-03-31 | 2020-05-11 | 2020-08-06 |  | Y | EL DORADO PH 210219562 | 52
35112435 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  |  | CLSD | 7185 | 0 | 7006 | 7006 | 1.3269 | 7006 | 1.3269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-24 |  |  | 2020-07-24 | 2020-08-31 | 2020-07-24 | 2019-10-16 | 2019-10-16 | Yes | 2020-07-24 | 07/06: ADER pre-Final corrections communicated - QUES applied corrections07/02: QUES submitted for ADE review07/01: redesign - EST applied redesign - EST routed - EOD (7/17)Redesign******7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift--> [RCC Issue]9/11: 1st Submittal push to 9/20 - 9/18: Push to 9/30 - Training/New Hire ramp up 9/25: On track for 9/30 1st submittal10/02: QUES submitted for 1st ADE rvw - ADE assigned ( [REDACTED] )10/03: ADE return 1st corrections to contractor10/09: Resource availability - in stamping - push to mid following week10/14: QUES submitted for 2nd ADE rvw [PRELIM DWG ready]10/14: ADE approved10/15: Routed |  |  |  | Redesign | EDRS - Pending EDRS approval | No | Obsolete (CONS+) | 0 | 0 |  |  | yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes |  |  | 2-12-2020. 2019 annual previously uploaded. Task should be reset until 2020 permit obtained. |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7006 | 1.3269 | 0 | 0 | 1.3269 | 0 | 1.3269 | 0 | 1.3269 | 0 | 0 | 1.1178 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-12-10 | 2020-04-20 | 2020-09-04 | 2020-09-04 |  | Yes | Shovel Ready |  |  |  | 75000 | [10 empty] | 36 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.06 |  |  |  | 2020 | Q1 | 2019-10-16 | 2020-04-27 | 2020-05-31 |  | Y | EL DORADO PH 210219562 | 52
35112436 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 |  |  | MAPP | 9210 | 0 | 9529 | 9529 | 1.8047 | 9529 | 1.8047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-10 |  |  | 2019-09-28 | 2019-10-06 | 2019-09-28 |  |  | Yes | 2019-09-28 | 7/3: QUES to review to provide review on 1st ADE Submital 7/16 - 8/21: On track for 8/31 9/04: QUES submitted for 1st ADE rvw --> [RCC Issue] 9/11 -9/18: ADE to be assigned 9/23: Corrections rtn to contractor |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 9529 | 1.8047 | 0 | 0 | 1.8047 | 0 | 1.8047 | 0 | 1.8047 | 0 | 0 | 1.8047 |  | Keep | 2020-03-10 | Yes | N/A | 2020-03-09 | 2020-05-08 | Yes | 2020-05-08 | 2019-11-26 |  |  | 2020-05-15 |  | Yes | Shovel Ready |  | 2767806.4 | 2702405 | 75000 | 3899347 | 1131540.6 |  | 97.63% | 2627405 |  |  |  | 1497397.2505 |  | 47 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.07 |  |  |  | 2020 | Q1 | 2019-09-28 | 2020-04-27 | 2020-06-07 |  | Y | EL DORADO PH 210219562 | 52
35112437 |  | 2020 | 220 Mile Plan | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  |  | CLSD | 14893 | 0 | 14550 | 14550 | 2.7557 | 14550 | 2.7557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-04-19 |  |  | 2019-10-24 | 2019-10-24 | 2019-10-24 |  |  | Yes | 2019-10-24 | 7/3: QUES to review to provide review on 1st ADE Submital7/16 - 8/21: On track for 8/319/04: Push to 9/9 - Reprioritized to resolve corrections, resource shift--> [RCC Issue]9/11: QUES Partial 1st submittal for ADE Rvw - Target for OCALC stamped and submit for 9/11 (for full review) - Large Project, 179 Loc.9/15: QUES 1st submittal for ADE Rvw final9/18: ADE assigned - [REDACTED] /25: ADE targeting rvw completion by EOW9/30: ADE 1st rvw corrections rtn to contractor10/02: 2nd submittal at RISK of delay due to 1 PE to stamp10/07 |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/7/2020 | Full |  |  | Yes |  |  |  |  | 2020-06-30 | Y | 2020-04-19 |  |  | Started | [7 empty] | 0 | 0 | 14550 | 2.7557 | 0 | 0 | 2.7557 | 0 | 2.6938 | 0 | 2.6938 | 0 | 0.061932 | 2.6655 | .06 needs to be removed from total. Secoundary span. | Keep |  | Yes | N/A |  |  |  |  | 2019-12-10 |  |  | 2020-08-26 |  | Yes | Shovel Ready |  |  |  | 75000 | [10 empty] | 75 | [9 empty] | Pollock Pines | El Dorado | 0 | 0 | E.5015687.08 |  |  |  | 2020 | Q2 | 2019-10-24 | 2020-04-27 | 2020-07-08 |  | Y | EL DORADO PH 210219562 | 52
35112504 |  | 2020 |  | BUCOCAMPT 12700 CENTERVILLE RD CHICO |  |  | CLSD |  | 0 | 528 | 528 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 528 | 0.1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0.068561 | 0 | 0.068561 | 0 | 0.031439 | 0.068561 |  |  |  |  | N/A | [5 empty] | 2019-08-05 | 2019-08-05 | 2019-08-05 | [7 empty] | 24692.78 |  |  |  | 90735.2 | [15 empty] | Chico | Butte | 39.7631 | -121.6756 |  |  |  |  | 2019 | [5 empty] | Y
35112698 |  | 2020 |  | BUCOCAMPT 5036 EDGEWOOD LN PARADISE |  |  | CLSD |  | 0 | 1164 | 1164 | 0.22045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1164 | 0.22045 | 0 | 0 | 0 | 0 | 0.22045 | 0 | 0.2642 | 0 | 0.2642 | 0 | -0.04375 | 0.2642 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-16 | 2019-09-17 | [7 empty] | 65672.54 |  |  |  | 159464.6 | [17 empty] | 39.7312 | -121.5844 |  |  |  |  | 2019 | [5 empty] | Y
35112699 |  | 2020 |  | BUCOCAMPT 5210 PARKWAY DR PARADISE |  |  | FICL |  | 0 | 299 | 299 | 0.056629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 299 | 0.056629 | 0 | 0 | 0 | 0 | 0.056629 | 0 | 0.062121 | 0 | 0.062121 | 0 | -0.0054924 | 0.062121 |  |  |  |  | N/A | [5 empty] | 2019-08-20 | 2019-08-20 | 2019-08-20 | [29 empty] | 39.7376 | -121.5945 |  |  |  |  | 2019 | [5 empty] | Y
35112770 |  | 2020 |  | BUCOCAMPT 456 GREEN OAKS DR PARADISE |  |  | DOCC |  | 0 | 369 | 369 | 0.069886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 369 | 0.069886 | 0 | 0 | 0 | 0 | 0.069886 | 0 | 0.076326 | 0 | 0.076326 | 0 | -0.0064394 | 0.076326 |  |  |  |  | N/A | [5 empty] | 2019-07-27 | 2019-07-27 | 2019-07-27 | [29 empty] | 39.7424 | -121.634 |  |  |  |  | 2019
35112822 |  | 2020 |  | BUCOCAMPT 13949 ANDOVER DR MAGALIA*ILB |  |  | FICL |  | 0 | 1264 | 1264 | 0.23939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1264 | 0.23939 | 0 | 0 | 0 | 0 | 0.23939 | 0 | 0.11023 | 0 | 0.11023 | 0 | 0.12917 | 0.11023 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-03 | [29 empty] | 39.8172 | -121.5971 |  |  |  |  | 2019 | [5 empty] | Y
35112837 |  | 2020 |  | BUCOCAMP 6037 SHADOW MTN LN PARADIS |  |  | CLSD |  | 0 | 410 | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 410 | 0.077652 | 0 | 0 | 0 | 0 | 0.077652 | 0 | 0.049432 | 0 | 0.049432 | 0 | 0.02822 | 0.049432 |  |  |  |  | N/A | [5 empty] | 2019-09-23 | 2019-09-27 | 2019-09-25 | [29 empty] | 39.764 | -121.6391 |  |  |  |  | 2019
35112838 |  | 2020 |  | BUCOCAMPT 1409 JESSIE LN PARADISE*ILB |  |  | CLSD |  | 0 | 167 | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0.031629 | 0 | 0.029735 | 0 | 0.029735 | 0 | 0.0018939 | 0.029735 |  |  |  |  | N/A | [5 empty] | 2019-11-06 | 2019-11-06 | 2019-11-05 | [7 empty] | 28953.3 |  |  |  | 69952.6 | [15 empty] | Paradise | Butte | 39.7516 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y
35112972 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  |  | ESTS | 6650 | 0 | 6650 | 6650 | 1.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 6113 | 1.1578 | ST | 08W | SH | 2023-12-25 |  |  | 2020-12-31 | 2021-02-28 | 2020-12-31 | 2020-10-02 | 2020-10-02 |  |  | 11/04: EST sub (11/9) 10/28: Pending job walk to proceed. 10/14 - 10/07: Submittal by 10/9; 10/16; 10/26 10/03: ADE rtn 2nd corrections to CO 10/02: EEI submitted for 2nd corrections 09/30: EST target sub (10/9) 09/26: ADE rtn 1st corrections to CO 09/23: ADE assigned; ADE in rvw; priority based 09/22: EEI submitted for 1st ADE rvw 09/02: EST push; sub date (9/14) 08/26 - 08/19: EST target sub (9/7); priorities 08/12 - 08/05: EST Target sub (8/21) 07/29 - 07/22: EST torget sub (8/14); Higher Priority Work 07/15: EST target sub (7/31) 07/08: EST target (7/24); internal review laptop issues ?? 07/01 - 06/24: EST target (7/17); On Track 06/17: EST target (6/26) 06/10: EST target (6/12); finalizing internal rvw - priority based 06/03: Push 1wk - EST internal rvw (6/5) - finalizing corrections (EEI internal rvw) 05/27: Push 1wk - EST internal rvw (6/1) 05/25: Push 1wk - EST internal rvw 05/13 - 03/25: On Track 02/27: Flagged COMPOSITE to WOOD [2] 02/26: On Track 02/19: Est priority alignment shift 02/12: Finializing EST internal rvw - EOW/Early next01/22: Push 2/7; Fielding - JO meeting access issues 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/3/20 11/27: EEI advise +3wk Push (will send details) 11/27 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/12 |  |  |  | 2020 - Q4- M12 [R2022(+)_319] | R2.3 - EST Implementing Corrections |  | Wood | 45 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2595 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-11 17:00 |  | INPR | 2022-03-16 08:00 | 2022-05-11 17:00 |  | 2022-06-10 17:00 | [5 empty] | Yes |  |  | 300000 | 1857879.2 |  | 1 | -299999 |  | 619.3% | 30544.5 |  |  |  | 1475128.1468 |  | 34 | [7 empty] | Remove |  | Pioneer | Amador | 38.4868 | -120.5231 | E.5014727.02 |  |  |  | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | WEST POINT 110113444 | 63
35112973 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  |  | PEND | 4248 | 0 | 4248 | 4248 | 0.80455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80455 |  |  | ST | 08W | SH | 2022-01-19 17:00 |  |  | 2020-09-15 | 2021-02-28 | 2020-09-15 | 2020-08-31 | 2020-08-31 |  | 2020-12-04 | 09/15: APPROVED - INTO PEND 09/14: EEI submitted Final Updates 09/11: Final corrections communicated to ADE/CO 09/02: ADE soft target (9/8); Priority based 08/31: EEI submitted for 2nd ADE rvw 08/26: EST target to route (9/3) - TBD 08/24: ADE rtn 1st corrections to CO; apply and route for approval 08/19 - 08/12: ADE in rvw; priority based 08/10: ADE assigned (Joe DB) 08/05 - 04/08: ADE to be assigned 03/31: EEI submitted for 1st ADE rvw 03/25: QC Adjusted 1st sub; 02/27: Flagged COMPOSITE to WOOD [2] - pulled back 02/21 EEI submitted for 1st ADE rvw 02/19: On Track 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/3/20 11/27: EEI advise +3wk Push (will send details) 11/27 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/12 |  |  |  | 2020 - Q3- M9 [R2022(+)_32] | COMPLETED |  | Wood | 33 | 0 |  |  | Yes |  |  |  | 2020-11-02 | 2020-11-02 |  |  |  |  | Full | 2020-11-02 | 2020-11-02 | Full |  |  | No enviro constraints identified | Full | [5 empty] | [REDACTED] waiting on plans for 35112972 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.80455 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-19 17:00 |  | INPR | 2022-02-25 08:00 | 2022-04-15 17:00 |  | 2022-05-17 17:00 | 2020-12-02 |  |  |  |  | Yes |  |  | 345000 | 1554504.1 |  | 434937.21 | 89937.21 |  | 450.6% | 92852.8 |  |  |  | 1932151.9887 |  | 22 | [7 empty] | Remove |  | Pioneer | Amador | 38.4868 | -120.5231 | E.5014727.03 | TL |  |  | 2021 |  | 2021-02-28 | 2021-05-14 |  |  | Y | WEST POINT 110113444 | 63
35112974 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  |  | ADER | 9021 | 0 | 9021 | 9021 | 1.7085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7085 |  |  | ST | 08W |  | 2022-01-04 17:00 |  |  | 2021-01-31 | 2021-02-28 | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | [Composite to Wood - Sept List]11/04 - 09/02: ADE in rvw; Priority based8/27: Conversion to wood complete08/27: EEI submiitted for 1st ADE rvw [3] - renumbered08/26: EST target sub (9/11)08/22: ADE [rejected] 1st corrections to CO; EST to renumber locations08/20: ADE assigned ( [REDACTED] )08/19- 06/24: ADE to be assigned06/22: EEI resubmitted for 1st ADE rvw [2] - QA06/17 - 03/25 - 02/11: ADE to be assigned02/05: EEI submitted for 1st ADE rvw12/04: 1st ADE push to 1/3/2011/27: EEI advise +3wk Push (will send details)11/27 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2021 - Q1- M1 [R2022(+)_321] | R1.2 - ADE Review in Progress |  | Wood | 64 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7085 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-04 17:00 |  | INPR | 2022-03-09 08:00 | 2022-04-26 17:00 |  | 2022-05-26 17:00 | [8 empty] | 330000 | 1710954.1 |  | 1 | -329999 |  | 518.5% | 29319.3 |  |  |  | 1001423.0848 |  | 46 | [7 empty] | Remove |  | Pioneer | Amador | 38.4868 | -120.5231 | E.5014727.04 |  |  |  | 999 |  | 2021-02-28 | 2021-05-14 |  |  | Y | WEST POINT 110113444 | 63
35112975 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  |  | ADER | 7634 | 0 | 7634 | 7634 | 1.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4458 |  |  | ST | 08W |  | 2022-01-06 17:00 |  |  | 2020-11-30 | 2021-02-28 | 2020-11-30 | 2020-11-06 | 2020-11-06 |  |  | 11/10: ADE in rvw11/06: EEI submitted corrections for 2nd ADE rvw11/04: EST target sub (11/09)10/21: EST sub (TBD) ; Computer crashed; Loaner does not have all the software.10/14 - 10/7: Submittal by 10/1610/2: ADE rtn 1st corrections to CO09/30 - 09/02: ADE in rvw; Priority based08/21: ADE assigned ( [REDACTED] )08/19 - 06/24 - 04/22: ADE to be assigned04/20: EEI submitted for 1st ADE rvw04/15 - 03/25: On Track02/27: Flagged COMPOSITE to WOOD [2]02/26: On Track02/19: Est priority alignment shift02/12: On Track; In Est Rvw01/08: EST push 1st sub target12/04: 1st ADE push to 1/3/2011/27: EEI advise +3wk Push (will send details)11/27 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q4- M11 [R2022(+)_322] | R2.2 - ADE Review in Progress |  | Wood | 59 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4458 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-06 17:00 |  | INPR | 2022-03-11 08:00 | 2022-05-16 17:00 |  | 2022-06-15 17:00 | [8 empty] | 330000 | 1634928.9 |  | 1 | -329999 |  | 495.4% | 20136.7 |  |  |  | 1130786.5591 |  | 39 | [7 empty] | Remove |  | Pioneer | Amador | 38.491 | -120.5266 | E.5014727.05 |  |  |  | 999 |  | 2021-02-28 | 2021-05-14 |  |  | Y | WEST POINT 110113444 | 63
35112976 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  |  | ESTS | 9652 | 0 | 9652 | 9652 | 1.828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.828 |  |  | ST | 08W |  | 2022-01-05 17:00 |  |  | 2021-01-31 | 2021-02-28 | 2021-01-31 | 2020-10-15 | 2020-10-15 |  |  | [Composite to Wood - Sept List]11/04 - 10/28 ADE in rvw; priority based10/15: EEI submitted for 2nd ADE rvw10/14: EST target sub (10/20)10/05 ADE rtn 1st corrections to CO09/30: ADE in rvw; priority based09/29: EEI submitted for 1st ADE rvw [3] - renumbered09/14: [Return] ADE rtn to vendor09/14: ADE assigned ( [REDACTED] ); ADE notified need to start numbering at loc 1.09/02: ADE to be assigned; New pole counts ??08/31 Conversion submitted08/26 - 07/01: ADE to be assigned06/26: EEI resubmitted for 1st ADE rvw [2] - QA06/24 - 01/15: ADE to be assigned01/09: EEI submitted for 1st ADE rvw01/08: EST push 1st sub target12/04: |  |  |  | 2021 - Q1- M1 [R2022(+)_323] | R2.2 - ADE Review in Progress |  | Wood | 50 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.828 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-05 17:00 |  | INPR | 2022-03-10 08:00 | 2022-04-28 17:00 |  | 2022-05-30 17:00 | [8 empty] | 300000 | 1798827.6 |  | 1 | -299999 |  | 599.6% | 13976.6 |  |  |  | 984025.0443 |  | 49 | [7 empty] | Remove |  | Pioneer | Amador | 38.5018 | -120.52 | E.5014727.06 |  |  |  | 999 |  | 2021-02-28 | 2021-05-14 |  |  | Y | WEST POINT 110113444 | 63
35112977 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  |  | PEND | 6072 | 0 | 6072 | 6072 | 1.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 5802 | 1.0989 | ST | 08W |  | 2022-01-17 17:00 |  |  | 2021-01-31 | 2021-02-28 | 2021-01-31 | 2020-10-21 | 2020-10-21 |  | 2020-10-29 | 10/28: EST target route (10/30); CAL routed for approval; ADE rtn 3rd rvw, apply corrections & submit for approval.10/25: ADE rtn 2nd rvw to CO; apply corrections and route for approval10/21: EEI submitted corrections for 2nd ADE rvw10/14 - 10/07: Submittal by 10/1910/05: 1st ADE Review Sent Back[Composite to Wood - Sept List]09/30 - 09/23: ADE in rvw; priority based09/17: ADE assigned ( [REDACTED] )09/02: ADE to be assigned; New pole counts ??8/31 Conversion submitted08/31: EEI submitted for 1st ADE rvw [2] - Converted to wood08/26 - 06/24: ADE to be assigned06/22: EEI resubmitted for 1st ADE rvw [2] - QA06/17 |  |  |  | 2021 - Q1- M1 [R2022(+)_324] | EDRS - Pending EDRS approval |  | Wood | 30 | 0 | [18 empty] | [REDACTED] to submit CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-17 17:00 |  | INPR | 2022-02-23 08:00 | 2022-04-19 17:00 |  | 2022-05-19 17:00 | [8 empty] | 345000 | 1390240 |  | 592701.09 | 247701.09 |  | 403% | 15606.5 |  |  |  | 1208904.3478 |  | 31 | [7 empty] | Remove |  | Pioneer | Amador | 38.5032 | -120.5141 | E.5014727.07 |  |  |  | 999 |  | 2021-02-28 | 2021-05-14 |  |  | Y | WEST POINT 110113444 | 63
35112978 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  |  | PEND | 8477 | 0 | 8477 | 8477 | 1.6055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6055 |  |  | ST | 08W | SH | 2021-11-26 17:00 |  |  | 2020-07-24 | 2020-10-31 | 2020-07-24 | 2020-06-29 | 2020-06-29 | Yes | 2020-10-08 | 7/24: APPROVED - INTO PEND07/24: ADE - Approved for routing07/15: ADE in rvw07/13: QUES submitted for 3rd ADE rvw07/08: EST target sub (7/10) TBD07/07: ADE rtn 2nd corrections to CO07/01: ADE in rvw - Priority based06/29: QUES submitted for 2nd ADE rvw06/24: EST On Track06/17: EST target sub (6/26) 06/09: ADE rtn 1st corrections to CO06/03 - 05/27: ADE rvw - priority based05/19: ADE Assigned ( [REDACTED] )05/06 - 11/20: ADE to be assigned [Q3.9]01/22: QUES submitted for 1st ADE rvw01/15: In stamping with PE9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q4- M10 [R2022(+)_313] | COMPLETED |  | Comp | 6 | 36 |  |  | Yes |  |  |  | 2020-10-10 | 2020-10-10 |  |  |  |  | Full | 2020-10-08 | 2020-10-08 | Full |  |  | Veg ERTC no longer needed. ERTC on track. | Full |  | 2020-09-09 | Yes | 2021-09-09 |  | Submitted to Amador Co on 9/8/20 |  |  |  |  | 2020-10-21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6055 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-11-26 17:00 |  | INPR | 2022-01-03 08:00 | 2022-02-21 17:00 |  | 2022-03-23 17:00 | 2020-10-08 | [7 empty] | 369510 | 1944941.6 |  | 1609077.23 | 1239567.23 |  | 526.3% | 75951 |  |  |  | 1211429.9455 |  | 43 | [7 empty] | Remove |  | Kit Carson | Amador | 38.4979 | -120.5621 | E.5014726.02 | ML |  |  | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | WEST POINT 110113444 | 63
35112979 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  |  | PEND | 5331 | 0 | 5331 | 5331 | 1.0097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0097 |  |  | ST | 08W | SH | 2021-10-06 17:00 |  |  | 2020-08-31 | 2020-10-31 | 2020-08-31 | 2020-06-15 | 2020-06-15 | Yes | 2020-09-17 | 08/19: Pending final rvw & approval08/17: QUES routed for approval; ADE notified not holding for walkdown08/12: Hold up to EOW ??08/05 - 07/22: RISK - Sub target 7/29; pending GC; Only hold for GC if EOD is NOT impacted.07/22 - 07/08: EST target sub (7/21) GC rvw - may take 3wk based on avg turnaround07/06: ADE approved for routing; Waiting for GC review from PMgr.07/02: QUES submitted for 4th ADE rvw07/02: ADE rtn 3rd corrections to CO07/01: On Track; QUES submitted for 3rd ADE rvw06/24: EST target sub (7/6) - Est out for 1wk06/22: ADE rtn 2nd corrections to CO06/17: EST correction near completion - clarified some Q&A with ADE; pending ADE response - Lower Priority06/15: QUES submitted for 2nd ADE rvw - [PRELIM DWG - ready]06/10: EST - Refielding needed; pics uploaded - Targets sub (06/12)06/03: EST target sub (6/5)05/27: ADE rtn 1st corrections to CO05/19: ADE Assigned ( [REDACTED] )05/06 - 1/29: ADE to be assigned [Q3.9]11/15: QUES submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/12 |  |  |  | 2020 - Q3- M8 [R2022(+)_314] | EDRS - Pending EDRS approval |  | Comp | 12 | 27 |  |  | Yes |  |  |  | 2020-10-15 | 2020-10-15 |  |  |  |  | Full | 2020-09-08 | 2020-09-08 | Full |  |  | Job was released in Feb 2020. Please send revised drawings if available. | Full |  | 2020-09-16 | Yes | 2021-09-09 |  | Submitted to Amador Co on 9/8/20 |  |  |  |  | 2020-09-16 |  | On hold pending work plan change - 78% complete as of 11/10/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0097 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-10-06 17:00 |  | INPR | 2022-01-06 08:00 | 2022-02-28 17:00 |  | 2022-03-30 17:00 | 2020-09-16 | [7 empty] | 369510 | 1408760.2 |  | 634232.73 | 264722.73 |  | 381.2% | 104790.6 |  |  |  | 1395283.0343 |  | 27 | [7 empty] | Remove |  | Kit Carson | Amador | 38.501 | -120.5478 | E.5014726.03 | TL |  |  | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | WEST POINT 110113444 | 63
35113072 |  | 2020 |  | BUCOCAMPT 485 LEISURE LANE PARADISE |  |  | DOCC |  | 0 | 366 | 366 | 0.069318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 366 | 0.069318 | 0 | 0 | 0 | 0 | 0.069318 | 0 | 0.093371 | 0 | 0.093371 | 0 | -0.024053 | 0.093371 |  |  |  |  | N/A | [5 empty] | 2019-08-12 | 2019-08-16 | 2019-08-17 | [29 empty] | 39.7366 | -121.6324 |  |  |  |  | 2019
35113075 |  | 2020 |  | BUCOCAMPT 5577 NEWLAND RD PARADISE |  |  | DOCC |  | 0 | 392 | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0.074242 | 0 | 0.20739 | 0 | 0.20739 | 0 | -0.13314 | 0.20739 |  |  |  |  | N/A | [5 empty] | 2019-09-23 | 2019-09-27 | 2019-09-27 | [29 empty] | 39.7523 | -121.6009 |  |  |  |  | 2019 | [5 empty] | Y
35113100 |  |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  |  | PEND | 10233 | 0 | 10233 | 10233 | 1.9381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9381 |  |  | ST | 08W | SH | 2021-11-25 17:00 |  |  | 2020-10-30 | 2020-10-31 | 2020-10-30 | 2020-07-22 | 2020-07-22 |  | 2020-10-12 | 09/30: EST awaiting [REDACTED] (Planning Engineer) and [REDACTED] (ADE) approval.09/23 - 09/17: Planner adjustment; sub target (9/24); progressing, minor ADE/Planner rvw to be completed.08/03: APPROVED - INTO PEND07/29: ADE approved for routing07/22: QUES submitted for 2nd ADE rvw; No walkdown per PMgr07/22: PUSH - Sub target 8/7; pending GC - EST sent followup07/15 - 07/01: GC rvw - may take 3wk based on avg turnaround06/29: EST requesting clarification from ADE on preferred method - double arm as designed or another framing. Est in progress.06/24: EST target sub (7/10) - RISK; Est reassignment and rvw of corrections.06/23: ADE rtn 1st corrections to CO06/17: ADE in rvw - priority based06/09: ADE Assigned (Jon P)06/03 - 05/27: ADE to be assigned05/26: QUES submitted for 1st ADE rvw [QC]05/20 - 12/18: ADE to be assigned [Q3.9]12/17: QUES submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - RD- M9 [R2022(+)_315] | Iss_RD0.0_Rdsn - Estimating Redesign |  | Comp | 13 | 48 |  |  | Yes |  |  |  | 2020-10-08 | 2020-10-08 |  |  |  |  | Full | 2020-10-08 | 2020-10-08 | Full |  |  | Veg ERTC no longer needed. ERTC on track. | Full |  |  | Yes | [7 empty] | 2020-10-21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9381 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-11-25 17:00 |  | INPR | 2022-01-03 08:00 | 2022-02-23 17:00 |  | 2022-03-25 17:00 | 2020-10-12 | [7 empty] | 369510 | 2370500.2 |  | 2254170.42 | 1884660.42 |  | 641.5% | 120896 |  |  |  | 1223125.2864 |  | 52 | [7 empty] | Remove |  | Kit Carson | Amador | 38.5004 | -120.5358 | E.5014726.04 | ML |  |  | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | WEST POINT 110113444 | 63
35113101 |  | 2020 | 220 Mile Plan | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  |  | DOCC | 11056 | 0 | 10830 | 10830 | 2.0511 | 10830 | 2.0511 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10788 | 2.0432 | ST | 08W | SH | 2020-07-27 |  |  | 2020-03-30 | 2020-03-26 | 2020-03-30 | 2020-03-16 | 2020-03-16 | Yes | 2020-12-08 | 03/30: INTO PEND 03/25: EST firm up sub date?? 03/23: ADE rtn 2nd corrections to CO 03/16: QUES submitted for 2nd ADE rvw 03/04: QUES provided 2nd sub to PMgr; Est - Waiting on Tree Trimming information (dependency) - will submit upon rcpt. 02/26: EST confirm 2nd sub date (3/4) 02/22: ADE rtn 1st corrections to CO 02/06: ADE assigned (Carlos); EST - link updated 12/06: QUES submitted for 1st ADE rvw 9/19: EEI stop; QUES assigned 11/20 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q4- M10 [R316] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-07-27 | Yes |  |  | Revising TCP will submit by 6/26 |  | 2020-07-31 | Y | 2020-06-29 | [10 empty] | 0 | 0 | 10830 | 2.0511 | 0 | 0 | 2.0511 | 0 | 2.0496 | 0 | 2.1045 | 0.054924 | 0.0015152 | 2.0496 |  | Keep |  | Yes | COMP |  |  |  |  | 2020-07-27 | 2020-08-24 | 2020-10-03 | 2020-10-03 | 2020-07-17 | yes | Shovel Ready |  | 3128068.2 | 1249271.1 |  | 2715235.15 | -412833.05 | 1823783.5 | 39.93% | 1189271.1 | 115013.6 | 1304284.7 |  | 609062.9186 |  | 58 | [9 empty] | Volcano | Amador | 0 | 0 | E.5014726.05 |  |  |  | 2020 | Q4 | 2020-10-31 | 2020-11-30 |  |  | Y | WEST POINT 110113444 | 63
35113102 |  | 2020 | 220 Mile Plan | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  |  | DOCC | 11533 | 0 | 11757 | 11757 | 2.2267 | 11757 | 2.2267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-17 |  |  | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-02-25 | 2020-02-25 | Yes | 2020-03-20 | 03/20: INTO PEND3/20: EST - Per new requirement, need a note added to CMCS Purpose of work with the Planned units footage; target correction (3/20)03/18: ADE approved for routing - final corrections rtn to CO03/16: ADE rejected (adding the GC review costs to the estimate )03/10: EST request rejection of routing - adding the GC review costs to the estimate 03/04: PUsh to 3/13 (1wk) Waiting on planning approval attachment and planner to complete DS73. Estimator has reached out again to planner this morning. (Who is Planner??)02/26: QUES routed 2/25 in EES, awaiting approval02/19: EST to confirm target date??02/13: ADE rtn 1st corrections to CO02/05: ADE assigned ( [REDACTED] )12/03: QUES submitted for 1st ADE rvw9/19: EEI stop; QUES assigned11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q1- M3 [R317] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | App submitted |  | 2020-07-10 | Y | 2020-06-29 | [10 empty] | 0 | 0 | 11757 | 2.2267 | 0 | 0 | 2.2267 | 0 | 2.2267 | 0 | 2.2267 | 0 | 0 | 2.2267 |  | Keep | 2020-05-19 | Yes | COMP | 2020-08-24 | 2020-09-10 | Yes | 2020-10-03 | 2020-07-02 | 2020-08-24 | 2020-10-03 | 2020-10-03 |  | Yes | Shovel Ready |  | 3198327 |  |  | 4620298 | 1421971 | 1884431.3 |  | 1129835.7 | 184060 | 1313895.7 |  |  |  | 58 | [9 empty] | Volcano | Amador | 0 | 0 | E.5014726.06 |  |  |  | 2020 | Q2 | 2020-03-31 | 2020-05-01 | 2020-06-23 |  | Y | WEST POINT 110113444 | 63 |  |  |  | 2021-03-10 16:27
35113103 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 |  |  | CLSD | 1152 | 0 | 1152 | 1152 | 0.21818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2019-07-26 |  |  | 2019-07-26 |  | 2019-07-26 |  |  | Yes | 2019-07-26 | [5 empty] | 100 | [16 empty] | Full |  |  | Full |  |  | CIF Submitted as of 8/20 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 1152 | 0.21818 | 0 | 0 | 0 | 0 | 0.21818 | 0 | 0.21818 | 0 | 0.21818 | 0 | 0 | 0.21818 |  |  |  |  | N/A |  |  |  |  | 2019-09-16 |  |  | 2019-11-15 |  |  |  |  | 363787 |  |  | 390567 | 26780 |  |  | 319671.6 | [5 empty] | 7 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014319.03 |  |  | 2020-077 | 2019 | Q4 |  |  |  |  | Y | LOS GATOS 1106LB44 | 841
35113104 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 |  |  | CLSD |  | 0 | 1324.3 | 1324.3 | 0.25081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | [9 empty] | 2019-08-19 | [38 empty] | y | [11 empty] | 1324.3 | 0.25081 | 0 | 0 | 0 | 0 | 0.25081 | 0 | 0.25081 | 0 | 0.25081 | 0 | 0 | 0.25081 |  |  |  |  | N/A |  |  |  |  | 2019-09-23 |  |  | 2019-12-19 |  |  |  |  | 417147 |  |  | 517390 | 100243 |  |  | 414586.4 | [15 empty] | Los Gatos | Santa Clara | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113105 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  |  | FICL | 3582 | 0 | 3782 | 3782 | 0.71629 | 3782 | 0.71629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2019-09-12 |  |  | 2019-09-12 |  | 2019-09-12 |  |  | Yes | 2019-11-18 | [5 empty] | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 9/23/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 3782 | 0.71629 | 0 | 0 | 0.71629 | 0 | 0.71629 | 0 | 0.71629 | 0 | 0 | 0.71629 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-12-06 | 2020-02-05 | 2020-04-17 | 2020-11-15 |  | Yes | Shovel Ready |  | 1403671 |  |  | 1425671 | 22000 | 132.3 |  | 1399231.2 | 4307.5 | 1403538.7 |  |  |  | 21 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014319.04 |  |  | 2020-078 | 2020 | Q1 | 2019-09-12 | 2020-02-02 | 2020-03-23 |  | Y | LOS GATOS 1106LB44 | 841
35113106 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  |  | UNSE | 4588 | 0 | 4588 | 4588 | 0.86894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86894 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.86894 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 100000 | 309543.3 |  | 1 | -99999 |  | 309.5% | 5607.8 |  |  |  | 356231.1735 |  | 30 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014534.02 | MX |  | 2021-144 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113107 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  |  | ESTS | 2875 | 0 | 2875 | 2875 | 0.54451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54451 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54451 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 100000 | 309828.5 |  | 1 | -99999 |  | 309.8% | 5898.5 |  |  |  | 569006.7757 |  | 18 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014534.03 | TL |  | 2021-145 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113108 |  | 2021 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Scoped | CONS | 3807 | 0 | 3807 | 3807 | 0.72102 | 0 | 0 | 3807 | 0.72102 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-07-29 |  | Y | 2019-11-22 |  | 2019-11-22 |  |  | Yes | 2020-03-10 | With ADE for review. |  |  |  |  | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 12/11, Caltrans due on 3/1, PERTC on 1/31 | Full |  |  | Yes |  |  | Santa Clara County submitted on 12/30/19 |  | 2020-10-31 | Y | 2020-05-01 |  |  | On hold for August fires | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72102 | 0 | 0 | 0.72102 | 0.72102 | 0 | 0 |  | Keep | 2020-04-30 | Yes | N/A | 2020-08-03 | 2021-03-31 17:00 |  | 2021-06-30 17:00 | 2020-03-10 | 2021-01-05 07:00 | 2021-04-15 16:00 |  | 2020-07-29 | yes |  |  | 1579821 | 1479898.7 | 183849 | 2054719 | 474898 | 382722 | 93.67% | 1094799.5 | 102299.5 | 1197099 |  | 2052499.379 |  | 19 |  | Potential work on 2/1 - Planned to complete between 1/19 and 1st week of Feb | [7 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014534.04 | TL |  | 2020-081 | 2020 | Q3 | 2019-12-06 | 2020-04-01 | 2020-05-09 |  | Y | LOS GATOS 1106LB44 | 841 |  |  |  | 2021-03-03 11:16
35113109 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 |  |  | CLSD |  | 0 | 681 | 681 | 0.12898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | [9 empty] | 2019-11-07 | [38 empty] | Y | [11 empty] | 681 | 0.12898 | 0 | 0 | 0 | 0 | 0.12898 | 0 | 0.12898 | 0 | 0.12898 | 0 | 0 | 0.12898 |  |  |  |  | N/A |  |  |  |  | 2019-11-07 |  |  | 2019-12-18 |  |  |  |  | 300000 |  |  | 300000 | 0 |  |  | 294673.1 | [15 empty] | Los Gatos | Santa Clara | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113110 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  |  | UNSE | 4000 | 0 | 7920 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 10000 |  |  | 10000 | 0 |  |  | 5252.3 | [5 empty] | 16 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014535.03 | ML |  | 2021-141 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113111 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  |  | UNSE | 5600 | 0 | 4065.6 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 10000 |  |  | 10000 | 0 |  |  | 4960.6 | [5 empty] | 17 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014535.04 | ML |  | 2021-142 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35113520 |  | 2020 |  | BUCOCAMPT 1395 SALISBURY LN PARADISE |  |  | FICL |  | 0 | 337 | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 337 | 0.063826 | 0 | 0 | 0 | 0 | 0.063826 | 0 | 0.099432 | 0 | 0.099432 | 0 | -0.035606 | 0.099432 |  |  |  |  | N/A | [5 empty] | 2019-10-21 | 2019-10-25 | 2019-10-18 | [29 empty] | 39.7814 | -121.5947 |  |  |  |  | 2019 | [5 empty] | Y
35113521 |  | 2020 |  | BUCOCAMPT 1651 LIGHTLY LN PARADISE*ILB |  |  | CLSD |  | 0 | 1130 | 1130 | 0.21402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1130 | 0.21402 | 0 | 0 | 0 | 0 | 0.21402 | 0 | 0.087689 | 0 | 0.087689 | 0 | 0.12633 | 0.087689 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-02 | [29 empty] | 39.7582 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y
35113522 |  | 2020 |  | BUCOCAMPT 13832 TULSA CT MAGALIA |  |  | CLSD |  | 0 | 784 | 784 | 0.14848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 784 | 0.14848 | 0 | 0 | 0 | 0 | 0.14848 | 0 | 0.13258 | 0 | 0.13258 | 0 | 0.015909 | 0.13258 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-02 | [7 empty] | 42560.78 |  |  |  | 72364.6 | [17 empty] | 39.8121 | -121.5961 |  |  |  |  | 2019 | [5 empty] | Y
35113524 |  | 2020 |  | BUCOCAMPT 1308 DEODARA WAY PARADISE* |  |  | DOCC |  | 0 | 185 | 185 | 0.035038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 185 | 0.035038 | 0 | 0 | 0 | 0 | 0.035038 | 0 | 0.12917 | 0 | 0.12917 | 0 | -0.094129 | 0.12917 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-19 | [29 empty] | 39.7578 | -121.5984 |  |  |  |  | 2019 | [5 empty] | Y
35113526 |  | 2020 |  | BUCOCAMPT 5601 CAMPUS DR PARADISE |  |  | CLSD |  | 0 | 387 | 387 | 0.073295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 387 | 0.073295 | 0 | 0 | 0 | 0 | 0.073295 | 0 | 0.10152 | 0 | 0.10152 | 0 | -0.02822 | 0.10152 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-16 | 2019-09-14 | [7 empty] | 55724.41 |  |  |  | 61877.2 | [17 empty] | 39.7522 | -121.62 |  |  |  |  | 2019 | [5 empty] | Y
35113528 |  | 2020 |  | BUCOCAMPT 1056 FAIRVIEW DR PARADISE |  |  | CLSD |  | 0 | 200 | 200 | 0.037879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 200 | 0.037879 | 0 | 0 | 0 | 0 | 0.037879 | 0 | 0.18561 | 0 | 0.18561 | 0 | -0.14773 | 0.18561 |  |  |  |  | N/A | [5 empty] | 2019-09-19 | 2019-09-19 | 2019-09-19 | [27 empty] | Paradise | Butte | 39.7635 | -121.6125 |  |  |  |  | 2019
35113871 |  |  |  | SILVERADO 2104 RECONDUCTOR - PHASE 2 |  |  | CLSD | 8976 | 650 | 0 | 650 | 0.12311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-08 |  |  | 2019-02-26 |  | 2019-02-26 |  |  | Yes | 2019-08-27 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Undergrounding redesign in process. Once completed will provide to ENV team / Need laydown | Full |  |  | Yes |  |  | Approved through May 2020 |  | 1980-01-01 | Y | [11 empty] | 650 | 0.12311 | 0 | 0 | 0 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0.12311 | 0 | 0 | 0.12311 |  |  | 2019-08-08 |  | N/A | 2019-10-01 | 2019-12-14 | Yes | 2019-12-14 | 2019-08-30 |  |  | 2019-12-13 | [17 empty] | 35 | [9 empty] | Angwin | Napa | 0 | 0 | E.5014537.02 |  |  |  | 2019 | Q1 | [5 empty] | SILVERADO 2104563322 | 295
35113925 |  | 2020 |  | BUCOCAMPT 6466 LONE CEDAR LN PARADISE |  |  | FICL |  | 0 | 167 | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 167 | 0.031629 | 0 | 0 | 0 | 0 | 0.031629 | 0 | 0.21591 | 0 | 0.21591 | 0 | -0.18428 | 0.21591 |  |  |  |  | N/A | [5 empty] | 2019-08-23 | 2019-08-26 | 2019-09-21 | [29 empty] | 39.7813 | -121.5982 |  |  |  |  | 2019 | [5 empty] | Y
35113950 |  |  |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  |  | UNSC | 19602 | 0 | 18848 | 18848 | 3.5697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5697 |  |  | CC | 08W | SH | 2020-08-28 |  |  | 2020-08-01 | 2020-08-31 | 2020-08-01 | 2019-12-11 | 2019-12-11 | Yes | 2020-12-11 | [2020 Const. Sched]08/01: APPROVED - INTO PEND07/31: Final corrections communicated to ADE/EST07/29: Est target sub( 7/30)07/26: ADE - sent back to the estimator for what should be the final review. I'll keep working with the estimator to get this one to approvals this week07/22: EEI submitted for 5th ADE rvw07/16: ADE rtn 4th corrections to CO07/15: ADE in rvw - target rtn to CO today07/14: ADE need field notes for a couple locations; EST uploaded07/13: EEI submitted for 4th ADE rvw07/10: EST advised, resubmit before end of next week07/09: Request to send Preliminaries to PMgr [REDACTED] ent 7/1007/08: Target sub (7/13); Ocalc07/01: EST target sub (7/10); issues with Caltrans still need to be worked out - redoing OCalcs per ADE06/25: ADE ( [REDACTED] ) provided additional corrections to CO; instructed for all DWGs change ADE to [REDACTED] incorporate GC walkdonw changes, apply and send for final rvw06/24: EST push target |  |  |  | 2020 - Q3- M7 [R2020_75] | COMPLETED |  | Wood | 145 | 2 |  | 2020-08-07 | Yes |  |  |  | 2020-08-04 | 2020-08-04 |  |  |  |  | Partial | 2020-08-04 | 2020-08-04 | Partial |  |  | ** Caltrans DSDD - Pilot Project - District 5 permit issues. Change to 5/30/2020 - enviro on track, though delayed due to estimating out date | Partial |  |  | Yes |  |  | [REDACTED] sending prelim week of 1/6 |  |  |  |  | 2020-08-15 |  | Restricted area. ERTC Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5697 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  | Yes | COMP |  |  |  |  | 2020-12-11 |  |  |  | 2020-08-28 | Yes |  |  | 5124123.3 | 1763903.3 |  | 7087268 | 1963144.7 | 4630467.1 | 34.42% | 131334.4 | 362321.8 | 493656.2 |  | 494132.5034 |  | 140 |  | Risk-Caltrans permit (esitmating by July 24 | [7 empty] | Boulder Creek | Santa Cruz | 37.1332 | -122.1258 | E.5014542.02 | MX |  | 2020-075 | 2020 | Q3 | 2020-02-29 | 2020-07-12 | 2020-08-10 |  | Y | BIG BASIN 110110296 | 354 |  |  |  | 2021-03-11 12:03
35113951 |  |  |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  |  | UNSC | 13637 | 0 | 12799 | 12799 | 2.4241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4241 |  |  | CC | 08W | SH | 2020-08-25 |  |  | 2020-08-17 | 2020-08-31 | 2020-08-17 | 2019-10-09 | 2019-10-09 | Yes | 2020-09-02 | [2020 Const. Sched]08/17: EST routed; Design change request - add 4more spans (7 locs), EST seeking approval; advised to stay with original - APPROVED INTO PEND08/16: ADE provided final corrections to CO; apply and route08/13: ADE rtn 3rd corrections to CO08/12: ADE target sub (8/12)08/05: ADE target sub (8/5-6)07/28: ADE working Rvw; Targeting approval EOW07/22: ADE in rvw07/17: EST submitted for 3rd ADE rvw07/15: On Track07/08 - 07/01: EST applying OCalc changes06/24 - 06/17: ADE target (06/26); per (6/10) comments06/10: EOD Pushed - ADE progress - anticipated 1-2 week push; update via standards version; this is an old job and when we started work on it, HFTD was not in OCalc - EST instructed to continue designing to old standard; Per the direction from J [REDACTED] the poles designed under the old standard must still pass in the current HFTD Load Case06/03: ADE Rvw soft target (6/19); EOD at risk, firm up dates.05/28: EEI resubmitted docs to new ADE for rvw05/27 |  |  |  | 2020 - Q3- M7 [R2020_76] | COMPLETED |  | Wood | 112 | 5 |  | 2020-08-25 | Yes |  |  |  | 2020-07-30 | 2020-07-30 |  |  |  |  | Partial | 2020-07-30 | 2020-07-30 | Partial |  |  | ** Caltrans DSDD - Pilot Project - permit is pushing this to 6/30/20 | Partial |  |  | Yes |  |  | Need start date for Santa Cruz county to issue permit |  |  |  |  | 2020-08-15 |  | Restricted area. ERTC Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4241 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  | Yes | COMP |  |  |  |  | 2020-09-02 |  |  |  | 2020-07-27 | Yes |  |  | 4988613.7 | 1381545.6 |  | 6920313 | 1931699.3 | 4496491.8 | 27.69% | 129800.1 | 362321.8 | 492121.9 |  | 569932.0859 |  | 82 |  | Risk-Caltrans permit (esitmating by July 24 | [5 empty] | Remove |  | Boulder Creek | Santa Cruz | 0 | 0 | E.5014542.03 | MX |  | 2020-076 | 2020 | Q3 | 2020-02-29 | 2020-07-12 | 2020-08-10 |  | Y | BIG BASIN 110110296 | 354
35113959 |  |  |  | STS-OFAC_IDLE_REMV-1229 APPLEMONT RANCH |  |  | DOCC |  | 0 | 462 | 462 | 0.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0766e-17 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 462 | 0.0875 | 0 | 0 | 0.0875 | 1.0766e-17 | 0.0875 | 0 | 0.0875 | 0 | -1.0766e-17 | 0.0875 |  |  |  |  | N/A | [35 empty] | Pollock Pines | El Dorado | 38.7697 | -120.6004
35113993 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  |  | ESTS | 11177.9 | 0 | 11177.9 | 11177.9 | 2.117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.117 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-01-31 | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | 11/04 - 10/07: No updates, can't field due to access issues. EEI in contact with Veg Mgmnt 10/01: Proj Mgr - coordinating w/ stakeholders and Vendor to progress efforts for access to conduct the estimate 09/30 - 08/12: EST scheduled to recheck field conditions for approach to complete estimate 08/05 - 03/26: Unable to field - project manager contacting maintenance to see how they access poles 02/27: Flagged COMPOSITE to WOOD [2] 02/18: Unable to Field (Cliff side/Access Road washed out - helicopter sets per ADE); EST waiting on JO response - To review and firm up 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/20/20 11/27: EEI advise +3wk Push (will send details) 11/20 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/12 |  |  |  | 2021 - Q1- M1 [R2022(+)_169] | Iss_R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Need to clear veg for estimating - Will involve BLM | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.117 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-04 17:00 |  | INPR | 2022-06-09 08:00 | 2022-08-19 17:00 |  | 2022-09-20 17:00 | [5 empty] | Yes |  |  | 250000 | 3498286.4 |  | 1 | -249999 |  | 1399% | 17402.5 |  |  |  | 1652452.8035 |  | 56 | [7 empty] | Remove |  | Pioneer | Amador | 0 | 0 | E.5014728.02 | ML |  | 2020-169 | 2021 |  | 2020-12-31 | 2021-06-29 |  |  | Y | WEST POINT 110112256 | 96
35113994 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  |  | ADER | 7001 | 0 | 7001 | 7001 | 1.3259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3259 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2021-01-31 | 2020-11-30 | 2020-10-26 | 2020-10-26 |  |  | 11/10 - 10/28: ADE in rvw10/26: EEI submitted for 2nd ADE rvw10/21 - 10/14: EST Target sub 10/16; 10/2610/19: Job walk scheduled; concluded for 2 PMs10/07: EST Target sub 10/1209/30 - 08/19: EST target sub (9/4); (9/18); (9/25); (10/12)- EOD @ RISK08/12: EST sub target TBD08/11: ADE rtn 1st corrections to CO08/05: ADE in rvw; priority based07/27: Confirmed Composite to Wood- Question arose; does this mean 100% wood or can Composite be used to address special circumstances. Composite can be utilized for special situations or Wood type unavailablilities.07/22: ADE Assigned ( [REDACTED] )07/15: - 07/01: ADE to be assigned06/16: EEI submitted for 1st ADE rvw06/10 - 05/27: Push 1wk - EST finalizing internal rvw-lower priority (5/29); (6/8); (6/12)05/20: Push 1wk - EST internal rvw (5/22)05/13: On Track05/06 - 04/29: EST sub change (5/15) - priority work04/15 - 04/01: On Track03/25: EST firmed up 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/19: Est priority alignment shift12/04: 1st ADE push to 1/20/2011/27: EEI advise +3wk Push (will send details)11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q4- M11 [R2022(+)_170] | R2.2 - ADE Review in Progress |  | Wood | 47 | 8 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3259 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-02-18 08:00 | 2022-04-18 17:00 |  | 2022-05-18 17:00 | [8 empty] | 250000 | 2636047.2 |  | 1 | -249999 |  | 1054% | 34684.2 |  |  |  | 1988048.7382 |  | 36 | [7 empty] | Remove |  | Pioneer | Amador | 0 | 0 | E.5014728.03 | ML |  | 2020-170 | 2021 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35113995 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  |  | PEND | 7448.1 | 0 | 7448.1 | 7448.1 | 1.4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4106 | 6115 | 1.1581 | ST | 08W | SH | 2023-12-25 |  |  | 2020-10-28 | 2021-01-31 | 2020-10-28 | 2020-08-17 | 2020-08-17 |  | 2020-10-28 | 10/28: APPROVED - INTO PEND10/27: ADE Final rvw communicated to CO; EST applied corrections - rerouted10/21: EST walk completed; being applied and stamped10/14 - 10/8: Job walk will be on 10/1510/7: Routed to ADE in August/Constructibility walk09/30: EST target sub (11/1)09/23: EOD PUSH; Still pending wallkdown; ADE is ready to finalize for routing/approval09/16 - 09/09: JO/EST - Setting up schedule time for job walk09/02 - 08/27: Request with JO to confirm walkdown; Updated dwg provided; awaiting JO final rvw of updated DWG and feedback08/26: Status?? Holding for walkdown?08/19: ADE holding for walkdown; Items resolved; EEI updated and routed for approval08/18: ADE rtn 2nd corrections to CO; minor - apply and route for approval; EST routed for approval; PM seeking EST attend walkdown. Hold for walkdown??08/17: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]08/12 - 08/05: EST target sub (8/14)08/01: ADE rtn 1st corrections to CO07/23: ADE assigned ( [REDACTED] )07/22- 05/13: ADE to be assigned05/06 |  |  |  | 2020 - Q4- M10 [R2022(+)_171] | COMPLETED |  | Wood | 33 | 0 |  |  | Yes | [10 empty] | 2023-12-25 | 2023-12-25 |  |  |  | FERC locations identified | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4106 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-07 17:00 |  | INPR | 2022-03-23 08:00 | 2022-05-19 17:00 |  | 2022-06-20 17:00 | [5 empty] | Yes |  |  | 250000 | 2547698 |  | 838375.56 | 588375.56 |  | 1019% | 42735.2 |  |  |  | 1806077.4479 |  | 38 | [7 empty] | Remove |  | Pioneer | Amador | 0 | 0 | E.5014728.04 | TL |  | 2020-171 | 2021 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35113996 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  |  | PEND | 6270 | 0 | 6270 | 6270 | 1.1875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1875 | 6536 | 1.2379 | ST | 08W |  | 2021-12-21 17:00 |  |  | 2020-09-18 | 2021-01-31 | 2020-09-18 | 2020-09-08 | 2020-09-08 |  | 2020-09-18 | 09/18: APPROVED - INTO PEND09/17: EEI submitted/routed corrections for approval; ADE approved 09/16: EST target sub (9/18)09/13: ADE rtn 2nd corrections to CO09/08: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]09/02: ADE rtn 1st corrections to CO09/02 - 08/19: ADE in rvw; priority based08/12: ADE assigned ( [REDACTED] )08/10: EEI submitted for 1st ADE rvw08/05: On Track07/29: Est target sub (8/7) - Internal rvw07/22: On Track07/15: EST target sub (7/31)07/08 - 07/01: On Track06/24: EST target sub (7/24)06/17: On Track06/10 - 06/03: Push 1mth (6/22); refielding a few locations and pushed out due to other priorities05/27 - 04/01: On Track03/25: EST firmed up 1st sub (5/29)02/27: Flagged COMPOSITE to WOOD [2]02/19 |  |  |  | 2020 - Q3- M9 [R2022(+)_172] | COMPLETED |  | Wood | 31 | 0 | [18 empty] | [REDACTED] to submit CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1875 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2021-12-21 17:00 |  | INPR | 2022-02-18 08:00 | 2022-04-07 17:00 |  | 2022-05-09 17:00 | [8 empty] | 250000 | 1717138 |  | 841954.09 | 591954.09 |  | 686.9% | 95755.9 |  |  |  | 1446010.9474 |  | 32 | [7 empty] | Remove |  | Pioneer | Amador | 0 | 0 | E.5014728.05 |  |  | 2020-172 | 999 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35113997 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  |  | PEND | 6460 | 0 | 6460 | 6460 | 1.2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2235 |  |  | ST | 08W |  | 2021-12-20 17:00 |  |  | 2020-09-16 | 2021-01-31 | 2020-09-16 | 2020-09-14 | 2020-09-14 |  | 2020-09-15 | 09/16: APPROVED INTO PEND 09/02: EST target sub (9/16) 09/01: ADE rtn 1st corrections to CO 08/26 - 08/19: ADE in rvw; priority based 08/13: ADE assigned (Joe) 08/12 - 06/03: ADE to be assigned 05/28: EEI submitted for 1st ADE rvw 05/27 - 05/20: Applying changes based on ADE/OE discussions 05/13: EST sub change - priority work (5/18) 04/29 - 04/01: On Track 03/25: EST firmed up 1st sub 05/20: Push 2wk - EST workload 02/27: Flagged COMPOSITE to WOOD [2] 02/19: Est priority alignment shift 01/08: EST push 1st sub target 12/04: 1st ADE push to 1/20/20 11/27: EEI advise +3wk Push (will send details) 11/20 <-- 9/11: On Track 09/04: On Track for 1st Submittal 12/12 |  |  |  | 2020 - Q3- M9 [R2022(+)_173] | COMPLETED |  | Wood | 46 | 0 | [18 empty] | [REDACTED] to submit CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2235 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2021-12-20 17:00 |  | INPR | 2022-03-31 08:00 | 2022-05-25 17:00 |  | 2022-06-24 17:00 | [8 empty] | 250000 | 1555162.1 |  | 771395.95 | 521395.95 |  | 622.1% | 74130.8 |  |  |  | 1271092.2427 |  | 33 | [7 empty] | Remove |  | Kit Carson | Amador | 38.4618 | -120.5194 | E.5014728.06 |  |  | 2020-173 | 999 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35113998 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  |  | PEND | 5906.8 | 120 | 5787 | 5907 | 1.1187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1187 |  |  | ST | 08W |  | 2021-12-03 17:00 |  |  | 2020-09-29 | 2021-01-31 | 2020-09-29 | 2020-09-29 | 2020-09-29 |  | 2020-09-29 | 09/29: Final rvw communicated for corrections; applied; APPROVED - INTO PEND09/27: ADE rtn 1st corrections to CO; apply and route for approval (minimal)09/23 - 09/02: ADE in rvw; Priority based08/26 - 08/19: ADE assigned ( [REDACTED] )08/12 - 06/24: ADE to be assigned06/16: EEI submitted for 1st ADE rvw06/10 - 04/01: On Track03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]02/19: Est priority alignment shift01/08: EST push 1st sub target12/04: 1st ADE push to 1/20/2011/27: EEI advise +3wk Push (will send details)11/20 <-- 9/11: On Track09/04: On Track for 1st Submittal 12/30 |  |  |  | 2020 - Q3- M9 [R2022(+)_174] | COMPLETED |  | Wood | 41 | 5 | [18 empty] | [REDACTED] to submit CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1187 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2021-12-03 17:00 |  | INPR | 2022-02-16 08:00 | 2022-04-08 17:00 |  | 2022-05-10 17:00 | [8 empty] | 250000 | 1652866.3 |  | 1129039.96 | 879039.96 |  | 661.1% | 124247 |  |  |  | 1477422.3911 |  | 30 | [7 empty] | Remove |  | Kit Carson | Amador | 38.4628 | -120.5299 | E.5014728.07 |  |  | 2020-174 | 999 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35113999 |  |  |  | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  |  | ESTS | 8939.9 | 0 | 8940 | 8940 | 1.6932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6932 |  |  | ST | 08W |  | 2022-01-04 17:00 |  |  | 2020-12-31 | 2021-01-31 | 2020-12-31 | 2020-12-01 | 2020-12-01 |  |  | 11/04: ADE in rvw11/02: ADE assigned ( [REDACTED] )11/02: EEI submitted for 1st ADE rvw10/28 - 10/7: Submittal by 10/16; 10/3009/30 - 09/23: EST push (10/2); (10/16); Priorities09/02 - 08/26: EST target sub (9/18)08/19: EST target sub (9/4); priorities08/12 - 08/05: EST push sub (8/21);07/29: On Track07/22 - 04/29: EST sub change- priority work (5/15); (5/29);(6/12); (06/26); (7/2); (7/10); (7/17); (07/24); (8/07) |  |  |  | 2020 - Q4- M12 [R2022(+)_175] | R1.2 - ADE Review in Progress |  | Wood | 64 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6932 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-04 17:00 |  | INPR | 2022-03-09 08:00 | 2022-05-05 17:00 |  | 2022-06-06 17:00 | [8 empty] | 250000 | 1778926.6 |  | 1 | -249999 |  | 711.6% | 24673.3 |  |  |  | 1050641.2134 |  | 45 | [7 empty] | Remove |  | Kit Carson | Amador | 38.4614 | -120.529 | E.5014728.08 |  |  | 2020-175 | 999 |  | 2021-01-31 | 2021-07-30 |  |  | Y | WEST POINT 110112256 | 96
35114040 |  | 2022 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Scoped | CONS | 7188 | 477 | 7362 | 7839 | 1.4847 | 0 | 0 | 0 | 0 | 7839 | 1.4847 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-20 |  | Y | 2020-07-20 | 2020-04-24 | 2020-07-20 | 2020-03-12 | 2020-03-12 | Yes | 2020-07-16 | 07/14: EOD (8/14); Apply JO feedback, send for CALTRANS rvw; process for approval.07/09: submitted the Cal Trans poles that were in the CRZ zone; Plan and Profile project will be getting submitted for the 4 UG portions for the Cal Trans permit end of next week04/26: Redesign Caltrans CRZ. Needing to relocate poles.- Chg Order submitted**********04/24: APPROVED - INTO PEND04/23: Final approval corrections rtn to CO4/21: EST sub date (4/24) - target tomorrow04/19: ADE rtn 4th corrections to CO04/14: ADE status??04/09: EN submitted for 4th ADE rvw04/07: EST to firm up sub date (4/10)04/03: ADE rtn 3rd corrections to CO03/31: Target 4/1; PE Stamping; EN submitted for 3rd ADE rvw03/24: EST firm up sub (3/23)??03/20: ADE rtn 2nd corrections to CO03/17: ADE status/target (3/17)??03/12: EN submitted for 2nd ADE rvw03/10: Push to 03/20 - Addressing some construction concerns; equipment concerns3/05: EST/ADE working through markups3/03: EST Confirm ON TRACK2/25: EST confirm date (03/06)2/19: ADE Rtn 1st corrections to CO01/28 - 01/21: ADE Status??01/14: ADE Status (~2wk)??01/08: ADE priorities/holidays12/24: ADE assigned ( [REDACTED] )01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment11/19 |  |  |  | Redesign | RD0.0_Rdsn - Estimating Redesign |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-05-01 | 2020-05-01 | Complete |  |  |  | Partial | 2020-05-01 | 2020-05-01 | Partial |  |  | ** Caltrans DSDD - Pilot Project - district 10 permit expected 8/19/2020 - PERTC | Partial |  |  | Yes |  |  | Permit Not Required |  | 2020-07-27 | Y | 2020-06-24 |  |  | 95% complete as of 7/21/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4847 | 0 | 0 | 1.4017 | 1.4017 | 0 | 0 |  | Keep | 2020-07-06 | Yes | COMP | 2020-07-29 | 2021-07-16 17:00 |  | 2021-08-17 17:00 | 2020-07-17 | 2021-06-01 07:00 | 2021-06-30 17:00 |  | 2020-07-16 | yes | Shovel Ready |  | 3107232.1 | 2827711 | 1676839.1 | 4232824 | 1125591.9 | 1875440.6 | 91% | 1188637.5 | 43154 | 1231791.5 |  | 1904619.7321 |  | 48 | [9 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.02 |  |  | 2020-024 | 2020 | Q3 | 2020-04-30 | 2020-08-15 | 2020-09-29 |  | Y | PINE GROVE 11021222 | 2271 |  | PRE
35114041 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  |  | CONS | 7134 | 0 | 6879 | 6879 | 1.3028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3028 |  |  | ST | 08W | SH | 2020-08-07 |  |  | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-01-23 | 2020-01-23 | Yes | 2020-06-17 | [2020 Const. Sched]06/17: ADE approved for routing; routed; APPROVED - INTO PEND06/16: EST submitted for 3rd ADE# rvw06/16: EST restamping/reviewed; with P.E. currently.06/12: ADE rtn 3rd rvw to CO; ADE request corrections complete by next week, to route and approve by end of week.06/09: ADE soft target (6/12)06/03: EST submitted for 3rd ADE rvw06/02: EST target set (06/05)05/27: ADE rtn 2nd corrections to CO05/26: EOD push05/19: In review05/07: ADE to start rvw (5/11); Target rtn (5/22)04/28 - 04/14: EOD shift to MAY; Progress; ADE status; Target date (??)03/03: ADE - 3 Priority Q1 prior to this one.01/23: EN submitted 2nd ADE rvw - [Prelim DWG ready]01/15: ADE rtn 1st corrections to CO01/14: ADE Status (~2wk)??12/31: ADE Assigned ( [REDACTED] )12/03: ADE 1st submittal holding for resource availability & assignment11/19 |  |  |  | 2020 - Q2- M4 [R25] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-04-30 | Yes | 2021-04-30 |  | Received 5/14/20, Requested 2/13/20 |  | 2020-08-25 | Y | 2020-07-27 | 2020-07-09 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3028 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-16 | Yes | COMP | 2022-03-07 08:00 | 2022-05-03 17:00 |  | 2022-06-14 17:00 | 2020-07-07 |  |  |  | 2020-08-07 | Yes | Shovel Ready |  | 1891544 | 1419140.7 |  | 2760383 | 868839 |  | 75.02% | 396867 |  |  |  | 1089266.3027 |  | 54 |  |  | Complete | [6 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.03 |  |  |  | 2020 | Q3 | 2020-04-30 | 2020-10-27 | 2020-12-16 |  | Y | PINE GROVE 11021222 | 20
35114042 |  | 2020 | 220 Mile Plan | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  |  | DOCC | 7522 | 0 | 7123 | 7123 | 1.3491 | 7126 | 1.3496 | 0 | 0 | 0 | 0 | 0 | 0 | -0.00056818 |  |  | ST | 08W | SH | 2020-06-13 |  |  | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-03-06 | 2020-03-06 | Yes | 2020-04-08 | 04/08: IN TO PEND04/07:Final approv corrections sent to CO; 03/31: Routing for approval03/25: EN submitted correction; ADE advised correct03/24: EN submitted for 5ht ADE rvw - ADE rtn 5th correction; Loc-86, OCalc was change to Grade "C" construction? It should be Grade "B" construction.03/24: ADE rtn 4th corrections to CO - Please save all OCalc and it will autosave in SAP as a zip OCalc file for ADE to compare.03/23: EN submitted for 4th ADE rvw03/19: ADE rtn 3rd corrections to CO03/18: EN submitted for 3rd ADE rvw03/17: EST on track03/10: EST set sub date 3/18 - Estimator working 3 Pine Grove03/07: ADE rtn 2nd corrections to CO03/04: EN submitted for 2nd ADE rvw03/24: EST to firm up sub ??03/03: EST Confirm ON TRACK02/25: Redlines done - completing fld walk with for any final changes02/18: EST confirm target date02/15: ADE rtn 1st corrections to CO02/10: ADE assigned ( [REDACTED] )01/28: Push Prelim date due to new Priority Alignments01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment11/19 <-- 10/01: ADE to be assigned - waiting on 2020 priority list; [11/19] 2nd push 1 10/23: EN submitted for 1st ADE rvw10/22 <-- 9/03: On Track - Targeting earlier submittal8/13 Fielding planned for EOM (Aug) |  |  |  | 2020 - Q2- M6 [R26] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-06-12 | 2020-06-12 |  |  |  |  | Full | 2020-06-12 | 2020-06-12 | Full |  |  | ERTC issued 4/13/20- no Caltrans permit required (due 6/12/2020) | Full |  | 2020-06-13 | Yes | 2021-11-30 |  | 5/18/20 Permit not required, Requested 3/5/20 |  | 2020-06-26 | Y | 2020-06-03 | 2020-05-15 |  | preinspection 100% complete 6/17 | [7 empty] | 0 | 0 | 7126 | 1.3496 | 0 | 0 | 1.3496 | -0.00056818 | 1.172 | 0 | 1.3803 | 0.20833 | 0.17765 | 1.172 | Loc 10 - 12 installed AWAC in place of primary | Keep | 2020-05-19 | Yes | COMP | 2020-06-18 | 2020-08-25 17:00 | Yes | 2020-08-25 17:00 | 2020-05-18 | 2020-06-18 | 2020-08-26 | 2020-08-25 | 2020-06-12 | Yes | Shovel Ready |  | 2039341.3 |  |  | 2867650 | 828308.7 | 692797.1 |  | 1318471.6 | 28072.6 | 1346544.2 |  |  |  | 53 |  |  | Complete | [6 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.04 |  |  |  | 2020 | Q3 | 2020-06-30 | 2020-12-27 |  |  | Y | PINE GROVE 11021222 | 20
35114043 |  | 2020 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  |  | DOCC | 5763 | 0 | 5542 | 5542 | 1.0496 | 5542 | 1.0496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-06-15 |  |  | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-01-23 | 2020-01-23 | Yes | 2020-04-24 | 04/24: APPROVED - INTO PEND 04/17: EST routed - (To be confirmed) 04/16: ADE rtn 5th corrections to CO 04/14: EN submitted for 5th ADE rvw - target approval EOW 04/07: EST to firm up sub date (04/03) - 4/10 03/31: ADE rtn 4th corrections to CO - We do not have a 5' rule for uplift strain 03/26: EN submitted for 4 ADE rvw 03/24 - 03/17: Est - Site walk scheduled (next week); rvw if sched is to be cancel - if cancelled; ready to submit. PM request walk. 03/10: EST confirmed sub (3/13) 03/05: ADE rnt 4th corrections to CO 03/03: ADE target EOW; 3rd rvw 02/26: EN submitted for 3rd ADE rvw 02/18: In stamping (target MID/EOW) 02/15: EST/ADE post Field Meet - corrections/change coordination (loc 47-80 span ommission?/ DWG updates) 02/11: EST/ADE coordinating on corrections - Target sub 3 EOW 02/07: ADE to rtn 2nd correction to CO 02/03: ADE rtn from Vaca 1/24: Per ADE OCalcs need to be stamped 1/23: EN submitted for 2nd ADE rvw 1/21: EST/ADE coordinating correction; resolving conflicting information - Target EOW 01/14: EST Clarified some ADE correction requests 01/07: ADE rtn 1st corrections to contractor 12/03: ADE 1st rvw holding for resource availability & assignment 11/19: ADE to be assigned - 1mth push to align 11/06: EN Submitted for 1st ADE rvw 11/05: Internal QC - Tomorrow submittal 10/29 <-- 9/03: On Track 8/13 Fielding planned for EOM (Aug) |  |  |  | 2020 - Q2- M5 [R27] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-05-15 | Yes | 2020-12-31 |  | Submitted |  | 2020-07-10 | Y | 2020-06-15 | 2020-06-03 | [9 empty] | 0 | 0 | 5542 | 1.0496 | 0 | 0 | 1.0496 | 0 | 1.0496 | 0 | 1.1271 | 0.077462 | 0 | 1.0496 |  | Keep | 2020-06-09 17:00 | Yes | N/A | 2020-06-17 08:00 | 2020-08-14 | Yes | 2020-08-14 17:00 | 2020-05-13 | 2020-06-17 | 2020-08-14 | 2020-08-14 |  | Yes | Shovel Ready |  | 1947510.4 |  |  | 2617141 | 669630.6 | 1046982.1 |  | 848440.3 | 52088 | 900528.3 |  |  |  | 39 | [9 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.05 |  |  |  | 2020 | Q3 | 2020-05-31 | 2020-09-01 | 2020-09-30 |  | Y | PINE GROVE 11021222 | 20
35114044 |  | 2021 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Scoped | MAPP | 6449 | 0 | 6126 | 6126 | 1.1602 | 0 | 0 | 6126 | 1.1602 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-27 |  | Y | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-03-06 | 2020-03-06 | Yes | 2020-06-08 | 04/15: EN uploaded newest CMCS - OCALC loc24 need to be saved to SAP; ok to route - routed by EST - INTO PEND04/14: EN submitted for 8th ADE rvw - Newest version CMCS needs upload to SAP04/14: PMgr - hold on routing to add GC cost/constructibility rvw (to send in today)04/13: EN submitted for 7th rvw; ADE request save all OCalc into SAP.04/11: ADE rtn 6th corrections to CO04/10: EN submitted for 6th ADE rvw04/09: ADE rtn 5th corrections to CO04/08: EN submitted for 5th ADE rvw; w/GC corrections04/07 - 03/31: Holding for GC, Sched 4/2 -ON TRACK03/23: EN submitted for 4th ADE rvw; ADE rvw - corrections good, pending GC walkdown impacts to route03/20: ADE rtn 3rd corrections to CO03/17: EST on trackADE to confirm target??03/18: EN submitted for 3rd ADE rvw03/10: EST confirm sub (3/20)3/09: ADE rnt 4th corrections to CO03/06: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]03/03: EST - Confirm 2nd sub date (03/13)02/24: ADE rtn 1st corrections to CO02/18: ADE Assigned ( [REDACTED] )01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment |  |  |  | 2020 - Q2- M6 [R28] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-06-01 | 2020-06-01 | Full |  |  | ** Caltrans DSDD - Pilot Project - Caltrans allowing PG&E to move forward under the Annual. | Full |  | 2020-05-01 | Yes |  |  | Submitted |  | 2020-09-25 | Y | 2020-07-20 | 2020-07-30 |  | 77% complete as of 9/22/20 | [5 empty] | 6126 | 1.1602 | 0 | 0 | 0 | 0 | 5808 | 1.1 | 1.1 | 0.060227 | 1.0966 | 0 | 1.0966 | 0 | 0.0034091 | 0.081061 |  | Keep | 2020-07-16 17:00 | Yes | COMP | 2020-08-12 08:00 | 2020-08-26 17:00 | Yes | 2021-02-25 17:00 | 2020-06-08 | 2021-02-23 07:00 | 2021-02-24 16:00 | 2021-02-25 | 2020-07-27 | Yes |  |  | 2235936.7 |  | 20105.2 | 3012702 | 776765.3 | 1090815 |  | 1096827.7 | 48294 | 1145121.7 |  |  |  | 53 | [9 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.06 | TL |  |  | 2020 | Q3 | 2020-06-30 | 2020-10-01 | 2020-11-02 |  | Y | PINE GROVE 11021222 | 20 |  |  |  | 2021-03-01 20:30
35114045 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  |  | UNSC | 7259 | 0 | 7602 | 7602 | 1.4398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4398 |  |  | ST | 08W | SH | 2020-08-20 |  |  | 2020-06-18 | 2020-09-30 | 2020-06-18 | 2020-04-14 | 2020-04-14 | Yes | 2020-09-10 | 06/18: APPROVED - INTO PEND06/17: ADE approved for routing; routed06/16: EST submitted for 5th ADE rvw06/16: EST target sub (6/19)06/11: ADE rtn 4th corrections to CO; On this 08W job Loc 1, Planning changed the switching configuration Loc 133 on 3511680106/10: EN submitted for 4th ADE rvw06/09: EST waiting for response to ticket; 'webviewer'; [REDACTED] looking to elevate for response.06/01: ADE request holding off on submittal, until issues fixed - until the pole is accessible from webviewer, push (6/05)05/26: EST target sub (5/29)05/20: ADE rtn 3rd corrections to CO05/19 - 05/12: ADE working priority PMs; Push 2week05/08: EN submitted for 3rd ADE rvw05/05: 2.1 Mainline impact - waiting for construction final corrections sub EOW (5/08)04/28: On Track04/22: EST sub target firm up (5/1)04/21: ADE rtn 2nd corrections to CO04/17 EN submitted for 2nd ADE rvw04/14: EST status TBD04/07: Status UD - sub (4/08)03/31: GC walkdown 4/2; holding to implement corrections03/24:Site walk Schedule (3/25) - Submit after update03/17: EST on track03/10: EST to confirm sub date (3/19)03/09: ADE rtn 1st corrections to CO03/03 - 02/25: ADE to firm up Rvw date (03/09)??02/18 ADE assigned ( [REDACTED] )12/03: ADE 1st submittal holding for resource availability & assignment11/22: EN submitted for 1st ADE Rvw11/19: Server issues (past 4 days) - Target EOW; Push PRELIM/EOD anticipating ADE resource impact11/12 <-- 9/03: On Track8/13 Fielding planned for EOM (Aug) |  |  |  | 2020 - Q2- M6 [R29] | COMPLETED |  | Comp | 32 | 43 |  |  | Yes |  |  |  | 2020-07-16 | 2020-07-16 |  |  |  |  | Full | 2020-07-20 | 2020-07-20 | Full |  |  | Received final design on 7/13/20 | Full |  | 2020-06-23 | Yes | 2020-12-31 |  |  |  | 2020-10-03 | Y | 2020-08-20 | 2020-08-03 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4398 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-17 17:00 | Yes | COMP | 2022-02-24 08:00 | 2022-05-12 17:00 |  | 2022-06-13 17:00 | 2020-09-11 |  |  |  |  | No |  |  |  | 2230790.3 |  | 2273638.04 |  |  |  | 386031.2 |  |  |  | 1549404.4704 |  | 37 |  |  | Complete |  |  |  |  | Remove |  | Kit Carson | Amador | 0 | 0 | E.5014745.07 | TL |  | 2021-095 | 2021 | 2020 Reserve | 2020-06-30 | 2020-10-01 | 2020-11-04 |  | Y | PINE GROVE 11021222 | 20
35114046 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  |  | PEND | 6113 | 235 | 6519 | 6754 | 1.2792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2792 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-10-31 | 2020-11-30 | 2020-04-07 | 2020-04-07 | Yes | 2020-11-17 | [Composite to Wood - Sept List]11/10: EST routed; going through final rvw/approval11/07: ADE rtn 4th ADE rvw; last partial; apply; req DS73; ready for approval 11/03: EST target sub (11/6)10/27: EST target sub (10/29)10/26: ADE rtn rvw for 4th corrections to CO; minor; partial10/20: ADE in rvw; priority based10/16: EN submitted tor 5th ADE rvw10/13: EST sub target (10/16)09/26: ADE rtn 4th Corrections to CO; Conversion Rvw; partial09/21: Conversion Complete; submitted09/15: Conversion Target 9/1809/08 - 09/01: EST target sub TBD; Conversion08/25: EST target sub (9/2);applying changes08/18: EST target sub (8/28); EST received information needed; JO says still needs to go through land due to UG change (end portion).08/11: EST target sub (TBD); Meeting scheduled today w/ JO,Vendor & ADEs08/04: EST - spoke with the job owner and he confirmed the vendor would be receiving his review any day now {AUG EOD}07/31: Pending other vendor rvw07/21: Joint proj w/ another vendor; waiting on other vendor review complete to proceed.07/14 - 07/14: On Track07/09: EN submitted Change Order - Moving various poles due to permitting.07/07 - 06/09: EST/JO - req 2 additional poles - land forecasting 6-8 weeks for approval (no easements available)06/02: Est On Track - JO to meet with land for final approval07/09: EN submitted for 5th ADE rvw05/26: Push 1wk (6/12); UG dwgs taking additional time.05/19: Transmission just responded - OH not viable; Need to be UG - need to coordinate w/ 2 additional parties to modify design.05/12: Push (per 5/7 comments); EST target sub (5/22); Emailed JO with 2 approaches, awaiting feedback05/07: changes in Ocalc and EES from 9’ to 8’; per construction not to use 9'; due date of tomorrow will not be possible because I need to get them re-stamped.05/05: Construction walk 5/6; EOW (05/08)04/29: ADE rtn 4th corrections to CO04/28: EN submitted for 4th ADE rvw04/21: ADE rtn 3rd corrections to CO04/15: EN submitted for 3rd ADE rvw04/14: Est target wub 4/1504/08: ADE rtn 2nd corrections to CO04/07: EN submitted for 2nd ADE rvw [2]04/06: ADE Rejected - stamped O Calc is not signed or dated; EST making adjustment for pole availabilities04/03: EN submitted for 2nd ADE rvw03/24: EST 2nd sub target (3/31) - GC Walk needed (3/26)03/17: ADE rtn 1st corrections to CO02/25: ADE 1st rvw Date (03/xx) - Lower in priority; will advise closer to date01/14: ADE Status (~2wk)??12/25: ADE assigned ( [REDACTED] )01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment |  |  |  | 2020 - Q4- M11 [R2021_96] | EDRS - Pending EDRS approval |  | Wood | 36 | 0 |  |  | Yes | [10 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Updated drawings received 9/25/20. Easements are required under new design. Have moved ERTC date from 11/6/20 to 5/6/2021 as placeholder. Enviro reviews complete. | [6 empty] | Plans being modified, wait to submit permit |  |  |  |  | 2020-10-21 |  | On hold pending work plan change - 88% complete as of 11/10/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2792 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-10-25 17:00 |  | INPR | 2022-03-10 08:00 | 2022-04-29 17:00 |  | 2022-05-31 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  | 625000 | 1914297.5 |  | 1161832.82 | 536832.82 | 175708.9 | 306.3% | 184147.2 | 265143.9 | 449291.1 |  | 1496519.2182 |  | 31 |  |  | Complete |  |  |  |  | Remove |  | Pioneer | Amador | 38.436 | -120.5562 | E.5014742.02 | ML |  | 2021-096 | 2021 | 2020 Reserve | 2020-06-30 | 2020-09-28 | 2020-11-05 |  | Y | PINE GROVE 11021222 | 20
35114048 |  | 2021 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Scoped | CONS | 7382 | 0 | 7344 | 7344 | 1.3909 | 0 | 0 | 7344 | 1.3909 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-21 |  | Y | 2020-06-01 | 2020-06-30 | 2020-06-01 | 2020-03-20 | 2020-03-20 | Yes | 2020-06-25 | 06/01: EN submitted final corrections; APPROVED - INTO PEND 5/30: Final corrections rtn to CO; 05/26: EST target sub (5/29) 05/25: ADE rtn 4th corrections to CO; apply corrections and route 05/19: ADE soft target (5/22) 05/15: EN submitted for 4th ADE rvw 05/11: EST target sub (5/15) 05/05: ADE rtn 3rd corrections to CO 04/28: ADE rvw status; target date (??) 04/27: EN submitted for 3rd ADE rvw 04/21: EST firm up sub date (4/24) 04/19: ADE srtn 2nd corrections to CO 04/14: Job walk concluded; ADE starting 2nd rvw 04/07: Status?? 03/31: GC Site walk schedule 4/7 03/24: ADE confirm sub (3/25) ?? - Thursday Site Walk 03/20: EN submitted for 2nd ADE rvw 03/17 - 03/10: EST confirmed sub date (3/17) - Site walk on 3/26; 03/07: ADE rtn 1st corrections to CO 03/03 - 02/25: ADE 1st rvw Date (03/12)?? 02/21: ADE assigned (Nathan) 12/03: ADE 1st submittal holding for resource availability & assignment 11/22: EN submitted for 1st ADE Rvw 11/19: Server issues (past 4 days) - Target EOW 11/12 Push 1mnth [12/13]- ADE to be assigned - waiting on 2020 priority list/Resourcing 11/05<-- 9/03: On Track |  |  |  | 2020 - Q2- M6 [R32] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-05-07 | 2020-05-07 | Full |  |  |  | Full |  | 2020-06-12 | Yes | 2021-05-19 |  | Submitted 5/12 |  | 2020-10-03 | Y | 2020-07-21 | 2020-07-09 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3909 | 0 | 0 | 0.94792 | 0.94792 | 0 | 0 |  | Keep | 2020-07-16 | Yes | COMP | 2020-08-14 08:00 | 2021-04-15 17:00 |  | 2021-05-27 17:00 | 2020-06-25 | 2021-03-09 07:00 | 2021-03-19 16:00 |  | 2020-07-21 | Yes |  |  | 3133899.4 | 1379278.3 | 1810131 | 4178929 | 1045029.6 | 1867374.9 | 44.01% | 1115036.5 | 151488 | 1266524.5 |  | 991637.9935 |  | 55 |  |  | Complete | [6 empty] | Pioneer | Amador | 38.436 | -120.5562 | E.5014742.03 |  |  |  | 2020 | Q3 | 2020-06-30 | 2020-09-28 | 2020-11-17 |  | Y | PINE GROVE 11021222 | 2271 |  | PRE |  | 2021-03-11 14:33
35114049 |  | 2021 | 220 Mile Plan | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Scoped | CONS | 9098 | 0 | 8392 | 8392 | 1.5894 | 3749 | 0.71004 | 4385 | 0.83049 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-07-06 |  | Y | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-16 | 2020-04-16 | Yes | 2020-04-24 | 04/24: APPROVED - INTO PEND04/21: EST firm up sub date (4/24)04/18: ADE rtn 2nd Correctionst to CO04/16: EN submitted for 04/14: Construction complete last Fri; EST to incorporate changes and sub (4/17)04/07: Push to 4/14; in anticipation of applying adjustments from Site walk03/31: GC Sitewalk cancelled - weather; resched 4/7; target sub 4/1003/24 - 03/17: Site walk on 3/2603/10: Est sub On Track03/03: EST - Confirm 2nd sub date (03/20)02/26: ADE rtn 1st corrections to CO02/24: ADE assigned ( [REDACTED] )t rvw holding for resource availability & assignment11/27: EN submitted for 1st ADE rvw11/19 <-- 9/03: Submittal On Track; Push PRELIM/EOD anticipating ADE resource impact |  |  |  | 2020 - Q2- M6 [R33] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-24 | 2020-04-24 | Full |  |  |  | Full |  | 2020-06-15 | Yes | 2021-05-19 |  | Received TCP 5/7 & Submitted, Requested 4/17/20 |  | 2020-07-21 | Y | 2020-06-30 | 2020-06-18 | [9 empty] | 0 | 0 | 4007 | 0.7589 | 4013 | 0.76004 | 1.5189 | 0.070455 | 0.70663 | 0.047727 | 1.5191 | 0.76477 | 0.81231 | 0.70663 |  | Keep | 2020-06-09 17:00 | Yes | COMP | 2020-07-21 | 2020-08-18 17:00 | Yes | 2021-04-29 17:00 | 2020-06-08 | 2021-03-23 07:00 | 2021-03-30 16:00 |  | 2020-07-06 | Yes | Shovel Ready |  | 3322837.3 |  | 1168197.9 | 2193681.27 | -1129156.03 | 2154100.5 |  | 1049014.8 | 119722 | 1168736.8 |  |  |  | 51 |  |  | Complete | [6 empty] | Pioneer | Amador | 38.436 | -120.5562 | E.5014742.04 |  |  |  | 2020 | Q3 | 2020-06-30 | 2020-09-28 | 2020-11-22 |  | Y | PINE GROVE 11021222 | 20 |  |  |  | 2021-03-01 17:15
35114050 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  |  | UNSC | 7377.2 | 0 | 7377.2 | 7377.2 | 1.3972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 |  |  | ST | 08W | SH | 2020-08-27 |  |  | 2020-06-15 | 2020-09-30 | 2020-06-15 | 2020-03-06 | 2020-03-06 | Yes | 2020-06-15 | 06/15: APPROVED - INTO PEND06/14: Final ADE corrections sent to CO06/11: ADE rtn 5th corrections to CO - apply and route06/10: EN submitted for 5th ADE rvw06/09: ADE rtn 4th corrections to CO; ok to route after corrections; EST target EOW06/02: ADE in rvw (6/05)5/28: EN submitted for 4th ADE rvw05/26: EST to coordinated with ADE on complications5/19: EST target sub (5/26)05/18: ADE rtn 3rd corrections to CO05/12 - 04/28: ADE rvw status; target date (??)04/24: EN submitted for 3rd ADE rvw04/21: EST Status - Target 5/2204/14 - 04/07: On Track03/31: GC sitewalk sched TBD - update pending03/24 - 03/17: EST - Sub Target?? Approval in system (double checking disconnect/ Task complete?)03/12: ADE rtn 2nd corrections to CO - This project 35114050 was never approved by planning03/09 - 03/06: EN submitted for 2nd ADE rvw03/03 - 02/25: EST to confirm 2nd sub (3/06)02/21: This project 35114050 was never approved by planning.Please get it approved by planning and upload that EDRS document to SAP when approved.02/21: ADE rtn 1st corrections to CO02/12: ADE priority shift for higher priority work - started again on 2/10; rvwing higher priority corrections.01/28: ADE on Vacation - Push Prelim01/14: ADE Status (~2wk)??12/31: ADE return submittal - Ocalc forms do not have PE stamps on them.12/31: ADE assigned ( [REDACTED] )01/07 <-- 12/17: ADE 1st rvw holding for resource availability & assignment12/13: EN submitted for 1st ADE Rvw12/11 <-- 9/03: Submittal On Track |  |  |  | 2020 - Q2- M6 [R34] | COMPLETED |  | Comp | 14 | 36 |  |  | Yes |  |  |  | 2020-07-16 | 2020-07-16 |  |  |  |  | Full | 2020-07-16 | 2020-07-16 | Full |  |  | CIF Submitted | Full |  | 2020-07-03 | Yes |  |  | Check sent to county on 6/22 - When check received permit will be released |  | 2020-10-31 | Y | 2020-08-27 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3972 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-27 | Yes | COMP | 2022-01-03 08:00 | 2022-02-24 17:00 |  | 2022-03-28 17:00 | 2020-07-17 |  |  |  | 2020-08-13 | Yes |  |  | 2981677.6 | 2414974.6 |  | 4089518 | 1107840.4 |  | 80.99% | 285027.8 |  |  | -47.532 | 1728442.4833 |  | 42 |  |  | Complete |  |  |  |  | Remove |  | Pioneer | Amador | 38.436 | -120.5562 | E.5014742.05 | TL |  | 2021-099 | 2021 | 2020 Reserve | 2020-06-30 | 2020-09-13 | 2020-11-02 |  | Y | PINE GROVE 11021222 | 20
35114051 |  | 2021 |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  |  | CONS | 7628 | 0 | 7628 | 7628 | 1.4447 | 0 | 0 | 7628 | 1.4447 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2020-08-26 | 2019-08-22 | Y | 2020-05-14 | 2020-09-30 | 2020-05-14 | 2020-03-13 | 2020-03-13 | Yes | 2020-05-19 | 05/19: APPROVED - INTO PEND05/14: Final approval corrections rtn to CO - EST submitted final corrections to ADE05/12: EST re-routing 5/1205/09: ADE final corrections rtn to CO05/08: EST routed05/07: EN submitted for th ADE rvw - ADE approved for routing05/06: ADE rtn 4th corrections to CO05/04: EN submitted for ADE rvw - GC corrections applied04/28: Physical walkdown yesterday; GC will submit updates Friday; EST to apply changes04/23: EOD Shift - Progress Risk04/21: Ready for routing - Deciding if virtual walkdown to be conducted to incorporate GC redlindes03/25: EN submitted for 4th ADE rvw03/24: EST to firm up GC sched impact - will firm up once sitewalk scheduled03/xx: ADE rtn corrections - ready for routing; GC site walk schedule??03/24: ADE rtn 3rd corrections to CO - Corrections are OK, pending changes identify by GC during walkdown.Please save all OCalc and it will autosave in SAP as a zip OCalc file. Let me know when done, so I can compare the zip OCalc in SAP to the stamp OCalc file.03/23 EN submitted for 3rd ADE rvw03/18: ADE rtn 2nd corrections to CO03/13: EN submitted for 2nd ADE rvw03/10: EST Status - ON TRACK03/03: EST - Confirm 2nd sub date (03/13)03/02: ADE rtn 1st corrections to CO02/24: ADE Assigned ( [REDACTED] )01/07 <-- 12/17: ADE 1st rvw holding for resource availability & assignment12/10: EN submitted for 1st ADE Rvw12/03 <-- 9/03: Submittal On Track |  |  |  | 2020 - Q2- M6 [R35] | COMPLETED |  | Comp | 10 | 43 |  |  | Yes |  |  |  | 2020-05-12 | 2020-05-12 | N/A |  |  |  | Full | 2020-05-12 | 2020-05-12 | Full |  |  | Caltrans Permit received | Full |  |  | Yes |  |  | Set to TCP on 5/21 - |  | 2020-10-10 | Y | 2020-08-26 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4447 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-27 17:00 | Yes | COMP | 2020-10-02 | 2021-07-23 17:00 |  | 2021-08-24 17:00 | 2020-07-28 | 2020-10-02 07:00 | 2021-03-31 16:00 |  | 2020-08-17 | Yes |  |  | 3949677.8 | 3177218.3 |  | 5342998 | 1393320.2 | 3318337.5 | 80.44% | 628601 | 2739.3 | 631340.3 |  | 2199228.1888 |  | 53 |  |  | Complete | [6 empty] | Pioneer | Amador | 38.4485 | -120.5393 | E.5014742.06 | TL | OH | 2021-100 | 2021 | 2020 Reserve | 2020-06-30 | 2020-09-13 | 2020-11-03 |  | Y | PINE GROVE 11021222 | 2271 |  | PRE |  | 2021-03-11 16:05
35114052 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  |  | UNSC | 4399 | 0 | 4291 | 4291 | 0.81269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81269 |  |  | ST | 08W | SH | 2020-08-31 17:00 |  |  | 2020-06-12 | 2020-09-30 | 2020-06-12 | 2020-04-03 | 2020-04-03 | Yes | 2020-09-04 | 06/14: APPROVED - INTO PEND06/11: ADE request 3 missing OCalcs; EST uploaded; ADE req correction to 2 locs; Planner to DS37 and reroute06/10: Routed06/09: System 'validation error'; EST following up on response.06/02: EST routed5/30: ADE rtn corrections to CO - reroute when complete05/26: EST target sub (5/27)05/19: Est to confirm rcpt; apply correction and route - ADE FW req email.04/29: ADE rtn final corrections; minor, route for approval - EST to confirm04/22: EN submitted for 3rd ADE rvw04/21: EST Status - Target 5/2204/14: EST confirm 3rd sub (4/17)04/09: ADE rtn 2nd corrections to CO04/07: ADE to firm up rvw date (4/08)??04/03: EN Submitted for 2nd ADE rvw03/31 - 03/24: EST firmed up sub (4/3); On Track03/23: ADE rtn 1st corrections to CO03/17: ADE to advise on date closer to target03/09: EN submitted for 1st ADE rvw [2]03/03: EST/ADE - Working with ADE; Seeking Addresses (or Meter No.) w/ Fld notes; Target resubmittal - 02/25: ADE Rejected 1st sub - DO fld notes are incomplete02/25: ADE assigned ( [REDACTED] )01/07: ADE 1st rvw holding for resource availability & assignment12/20: EN submitted for 1st ADE Rvw12/17: Submitting by EOW; submittal should have been 12/3112/03 <-- 9/03: Submittal On Track |  |  |  | 2020 - Q2- M6 [R36] | COMPLETED |  | Comp | 10 | 23 |  |  | Yes |  |  |  | 2020-05-12 | 2020-05-12 |  |  |  |  | Full | 2020-05-12 | 2020-05-12 | Full |  |  |  | Full |  | 2020-08-07 | Yes |  |  | Set to TCP on 5/12/20 - Road closures will need county board approval |  | 2020-09-25 | Y | 2020-08-20 | 2020-08-05 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.81269 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-31 17:00 | Yes | COMP | 2022-02-24 08:00 | 2022-04-15 17:00 |  | 2022-06-16 17:00 | 2020-09-04 |  |  |  |  | No |  |  | 625000 | 1264623.4 |  | 1801039.27 | 1176039.27 |  | 202.3% | 129329.2 |  |  |  | 1556096.8427 |  | 22 |  |  | Complete |  |  |  |  | Remove |  | Pioneer | Amador | 38.4525 | -120.5253 | E.5014742.07 | TL |  | 2021-101 | 2021 | 2020 Reserve | 2020-06-30 | 2020-08-29 | 2020-09-24 |  | Y | PINE GROVE 11021222 | 20
35114053 |  |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  |  | ADER | 8212 | 0 | 8212 | 8212 | 1.5553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5553 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2020-10-31 | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | [Composite to Wood - Sept List]11/10 - 11/03: ADE currently working on this rvw10/27 - 10/13: ADE status requested10/06: ADE Follow-up, need corrections to make the composite to wood conversion09/28: ADE in rvw; Status??09/22: Conversion holding for 1st ADE rvw; Target EOW09/15 - 04/21: ADE actively rvw now - priority based; EST target sub TBD; Conversion04/14 - 04/07: ADE to firm up rvw date (4/20)??03/30: ADE assigned ( [REDACTED] )01/07: ADE 1st rvw holding for resource availability & assignment12/20: EN submitted for 1st ADE Rvw12/17: Submitting by EOW; submittal should have been 12/3112/03 <-- 9/03: Submittal On Track |  |  |  | 2021 - Q1- M1 [R2021_102] | R1.2 - ADE Review in Progress |  | Comp | 0 | 43 | [13 empty] | 2023-12-25 | 2023-12-25 | [8 empty] | 2020-12-31 |  |  |  | 2021-03-15 |  | 2021-02-01 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5553 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-25 17:00 |  | INPR | 2022-07-11 08:00 | 2022-09-20 17:00 |  | 2022-10-20 17:00 | [9 empty] | 1713201.5 |  | 1 |  |  |  | 54019.1 |  |  |  | 1101522.64 |  | 42 |  |  | Complete |  |  |  |  | Remove |  | Pioneer | Amador | 38.4552 | -120.5246 | E.5014742.08 | TL |  | 2021-102 | 2021 | 2020 Reserve | 2020-07-31 | 2020-08-29 | 2020-10-05 |  | Y | PINE GROVE 11021222 | 20
35114100 |  | 2021 | 220 Mile Plan | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Scoped | CONS | 4925 | 0 | 5487 | 5487 | 1.0392 | 0 | 0 | 5487 | 1.0392 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-07-06 |  | Y | 2020-05-18 | 2020-05-18 | 2020-05-18 | 2019-10-28 | 2019-10-28 | Yes | 2020-06-25 | 05/18: APPROVED - INTO PEND05/14:Redesigned and corrected the planning order, now it routed for approval05/13: Push approval to end of May.5/12: think we have a game plan and hope to have this issue resolved by the end of the week or early next week. A new update will either be Wednesday or Saturday, once the update has taken place, [REDACTED] will be able to work the three step process. Since the 35171354 job is still in PEND status, he will be able to move this job back to estimating. He will convert it to the annual 08W planning order with the $14K charge. EES settlements will be updated.04/29 - 04/22: Link provided for assistance04/21: EES is giving me error while routing - clearing issue in process04/14: PM req to be notified on long lead item(s) readiness to order; flagged items for attention during rvw (Good as-is per ADE)04/13: ADE rtn 5th corrections to CO; final/minor |  |  |  | 2020 - Q1- M2 [R300] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-05-22 | 2020-05-22 | Full |  |  | 5/22/2020 new ERTC date (just received from estimating) | Full |  |  | Yes |  |  | Need start date for Santa Cruz county to issue permit |  | 2021-01-31 | Y | 2020-06-08 |  |  | waiting on line clearance to complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0392 | 0 | 0 | 0.95076 | 0.95076 | 0 | 0 |  | Keep | 2020-05-28 | Yes | COMP | 2020-07-27 | 2021-06-17 17:00 |  | 2021-11-17 17:00 | 2020-07-08 | 2021-04-05 07:00 | 2021-04-19 16:00 |  | 2020-07-06 | Yes | Shovel Ready |  | 1944396.9 | 428725.6 | 298329.3 | 2501285 | 556888.1 | 1464459.2 | 22.04% | 426335.9 | 53601.8 | 479937.7 |  | 412551.6982 |  | 28 |  | Potential work on 2/1 - Planned to complete between 1/19 and 1st week of Feb | [7 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.02 |  |  |  | 2020 | Q3 | 2020-02-29 | 2020-05-01 | 2020-06-04 |  | Y | CAMP EVERS 21065020 | 2464 |  | PRE
35114101 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  |  | FICL | 6671 | 0 | 6873 | 6873 | 1.3017 | 6873 | 1.3017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-05-15 |  |  | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2019-11-15 | 2019-11-15 | Yes | 2020-04-28 | 04/28: APPROVED - INTO PEND 04/24: ADE rtn corrections to CO - minor; Final corrections approved - ready for routing. 04/22: CAL submitted for 6th ADE rvw 04/18: ADE rtn corrections to CO 04/10: CAL submittted for 5th ADE rvw - redesigns 03/31: EST - will require the re-design of 18 pole units + 1 additional recloser pole (location TBD by Planner) so 18 pole units @ $470.81/unit + 1 new pole 03/18: ADE status update?? 03/13: CAL submitted for 4th ADE rvw - possible redesign coming. 03/11: Submitting by end of day today 03/03: ADE sent in prelim corrections (last week); to receive updates today; target early next week. 02/19: Push; ADE Status?? 02/12: CAL submitted for 3rd ADE rvw; ADE confirmed 1/23: ADE rtn 2nd corrections to CO 01/15: Per JP - EST corrections ready by Friday (1/17) (moved to Lead position, slowed est., implemented request from JO) 12/04 - 11/27: ADE Status? 11/14: CAL submitted for 2nd ADE rvw 11/13: EST - firmed up 2nd submittal date 11/05: Est recv'ng requests for wood to composite (proj initiated prior to 9/5 issuing of standard) - holding for response 10/26: ADE return 1st corrections to contractor 10/23 <-- 10/16: Check in with ADE (target dates for staggering submittal) 10/02 - 9/25: In review 8/12: CAL submitted for 1st ADE rvw 8/07: Late week changes required rework (Framing issues); pushed submittals 4 days out 7/31 <- 7/10: 8/5 1st ADE submittal (v9) |  |  |  | 2020 - Q1- M2 [R301] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-05-08 | 2020-05-08 | Full |  |  | PERTC received - Full expected in June | Full |  |  | Yes |  |  | Need start date for Santa Cruz county to issue permit |  | 2020-07-14 | Y | 2020-05-15 |  |  | Additional trimming required | [7 empty] | 0 | 0 | 6873 | 1.3017 | 0 | 0 | 1.3017 | 0 | 1.3017 | 0 | 1.3017 | 0 | 0 | 1.3017 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-05-07 | 2020-05-12 | 2020-08-07 | 2020-08-04 |  | Yes | Shovel Ready |  | 2217035.6 |  | 50472.6 | 2641148 | 424112.4 | 889680.6 |  | 1277807.4 | 49547.6 | 1327355 |  |  |  | 40 | [9 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.03 |  |  |  | 2020 | Q2 | 2020-02-29 | 2020-05-01 | 2020-06-04 |  | Y | CAMP EVERS 21065020 | 46
35114102 |  | 2021 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Scoped | CONS | 4333 | 0 | 3909 | 3909 | 0.74034 | 845 | 0.16004 | 3064 | 0.5803 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-05-19 |  | Y | 2020-04-27 | 2020-04-27 | 2020-04-27 | 2019-11-06 | 2019-11-06 | Yes | 2020-04-27 | 04/27: INTO PEND 04/22: EST Routing tomorrow 04/21: ADE rtn 4th corrections to CO; final/minor - approved for routing once complete 04/15: CAL submitted for 4th ADE rvw - Anticipating more changes 04/08: Submitting Change Order (Planning Change); 4/17 sub dependant on CO approval; 04/01: EST firm up sub date (4/2)?? 03/28: ADE rtn 3rd corrections to CO 03/18: ADE status update?? 03/03: CAL submitted for 3rd ADE rvw - ADE to rvw after PH2.2 02/26: EST target sub for 2/28 02/20: ADE rtn 2nd corrections to CO 02/12: ADE - incorporating all the standard changes and feedback from the stakeholder call. It is smaller and should go faster. 1/29: Priority Shift advisement... 1/15: Enviromental issues, Push approx 3 wk; information update expected next week 12/04 - 11/27: ADE Status? 11/13: Push 3 day - ADE review in progress - seeking clarification from EST (OCALC - adding endrise variables) 11/06: CAL submitted for 2nd ADE rvw 11/05: Est recv'ng requests for wood to composite (proj initiated prior to 9/5 issuing of standard) 10/29: ADE return 1st corrections to contractor 10/23 <-- 10/16: Check in with ADE (target dates for staggering submittal) 10/02 <- 9/04: In Review 9/03: CAL submitted for 1st ADE rvw 8/21: Push 8/30 - 2.1 Review comment impacts - held to apply to this section 8/14 <- 7/10: 8/26 1st ADE submittal (v9) |  |  |  | 2020 - Q1- M2 [R302] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Updated drawing on 3/10 - [REDACTED] is reviewing | Full |  |  | Yes |  |  | Need start date for Santa Cruz county to issue permit |  | 2020-07-24 | Y | 2020-05-13 |  |  | 99% complete, 1 location refusal (access concerns) | [7 empty] | 0 | 0 | 845 | 0.16004 | 0 | 0 | 0.16004 | 0.5803 | 0.1589 | 0 | 0.78542 | 0.62652 | 0.0011364 | 0.1589 |  | Keep | 2020-05-19 | Yes | N/A | 2020-08-04 | 2021-06-25 16:00 |  | 2021-11-17 17:00 | 2020-05-01 | 2021-03-30 07:00 | 2021-04-23 16:00 |  |  | Yes | Shovel Ready |  | 1453492.4 | 620532.2 | 428517.6 | 1763594 | 310101.6 | 688371.8 | 42.69% | 615729.9 | 149390.7 | 765120.6 |  | 838170.8918 |  | 21 |  | Potential work on 2/1 - Planned to complete between 1/19 and 1st week of Feb | [7 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.04 |  |  |  | 2020 | Q3 | 2020-02-29 | 2020-05-14 | 2020-06-17 |  | Y | CAMP EVERS 21065020 | 46
35114103 |  | 2021 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Scoped | CONS | 6635 | 0 | 6635 | 6635 | 1.2566 | 0 | 0 | 6635 | 1.2566 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-07-29 |  | Y | 2020-07-03 | 2020-07-31 | 2020-07-03 |  |  | Yes | 2020-07-16 | 04/20: Heard back from [REDACTED] she said she is willing to walk the property and meet w/ team. Says afternoons work best for her, any time from 2:30pm on.04/15: EST status/target date (??) - refield/Customer dependency (access), reestimate based on request redesign.04/08: Redesign - the estimator who fielded this project meet with our land department and identify and stake the pole placements for this revised "back tie". 03/31: EST - will require the re-design of 12 pole units + an additional 12 new pole (Four 3-Pole designs) and additional Fielding so 12 pole units 12/06: IN PEND12/04: CAL submitted for 4th ADE rvw12/02: ADE rtn 3rd corrections to contractor11/27: CAL submitted for 3rd ADE rvw11/25: ADE rtn corrections to contractor11/20: Push 1wk: ADE Bandwith11/14: CAL submitted for 2nd ADE rvw11/13: EST - 2nd sub target date 11/15 (wood/composite change)11/05: Est recv'ng requests for wood to composite (proj initiated prior to 9/5 issuing of standard) - holding for response10/30: ADE return corrections to contractor10/23 <-- 10/16: Push - Finalizing Priority PMS - 1/3 of the way throughCheck in with ADE for target date10/09 |  |  |  | Priority Q3 | Iss_R0.0 - Estimating | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-06-15 | 2020-06-15 |  |  |  |  | Full | 2020-06-01 | 2020-06-01 | Full |  |  | [REDACTED] - 5/13 no longer need an easement. Property owners refused. PERTC released on 1/27/20 - Easement required - expected 7/7/20. Land to prepare docs by 2/7. PERTC due on 1/27 | Full |  |  | Yes |  |  | County reviewing Needs exact date for approval. |  | 2020-11-30 | Y | 2020-07-29 |  |  | On Hold for fire. didn't start as planned, needed to work 4102 additional work | [7 empty] | 0 | 0 | 0 | 0 | 2337 | 0.44261 | 0.44261 | 0.81402 | 0.44261 | 0 | 1.3197 | 0.87708 | 0 | 0 |  | Keep | 2020-07-16 | Yes | COMP | 2020-08-03 | 2021-07-02 17:00 |  | 2021-11-26 17:00 | 2020-07-22 | 2021-03-02 07:00 | 2021-03-26 16:00 |  |  | Yes |  |  | 1943663.4 | 729219.4 | 506601.3 | 2335115 | 391451.6 | 1053181.9 | 37.51% | 719841 | 170640.5 | 890481.5 |  | 580298.1812 |  | 41 |  | Potential work on 2/1 - Planned to complete between 1/19 and 1st week of Feb | [7 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.05 |  |  |  | 2020 | Q3 | 2019-12-13 | 2020-04-15 | 2020-05-19 |  | Y | CAMP EVERS 21065020 | 46 |  |  |  | 2021-03-11 11:25
35114104 |  | 2020 | 220 Mile Plan | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  |  | MAPP | 7619 | 0 | 7775 | 7775 | 1.4725 | 7775 | 1.4725 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00053788 |  |  | CC | 08W | SH | 2020-06-01 |  |  | 2019-11-30 | 2019-11-04 | 2019-11-30 |  |  | Yes | 2019-11-04 | IN PEND10/25: CAL routed10/24: Approved for routing10/23: CAL submitted for 4th ADE rvw10/22: ADE rtn 1st corrections to Contractor10/18: CAL submitted for 3rd ADE rvw10/16: Cal On Track for 3rd corrections10/14: ADE rtn 2nd rvw corrections to contractor10/14: CAL provided docs for 2nd rvw to ADE10/08: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]10/02: ADE requesting adjustment to be applied throughout Est, conflicts with previous ADE requests.10/9/30: ADE 1st correction rtn to contractor - correction for only 1 poleADE reassigned9/27: ADE assigned ( [REDACTED] )9/25 <- 9/04: ADE to be assigned8/29: CAL submitted for 1st ADE rvw8/21: Push 8/30 - 2.1 Review comment impacts - held to apply to this section8/14 <- 7/10: 8/26 1st ADE submittal(v9) |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | [REDACTED] to submit CIF | Full |  |  | Yes |  |  | Everyting submitted waiting on agency |  | 2021-01-15 | Y | 2020-06-01 |  |  | waiting on line clearance to complete | [7 empty] | 0 | 0 | 7772.16 | 1.472 | 0 | 0 | 1.472 | 0.00053788 | 1.4725 | 0 | 1.4725 | 0 | -0.00053788 | 1.4725 |  | Keep | 2020-02-25 | Yes | N/A | 2020-02-14 08:00 | 2020-06-11 | Yes | 2020-06-11 | 2020-02-06 | 2021-01-11 | 2021-01-11 | 2021-02-18 |  | Yes | Shovel Ready |  | 2938512 |  | 143225.4 | 3424639 | 486127 | 851702.6 |  | 2002650.9 | 84158.5 | 2086809.4 |  |  |  | 60 | [9 empty] | Scotts Valley | Santa Cruz | 0 | 0 | E.5015489.06 |  |  |  | 2020 | Q1 | 2019-11-04 | 2020-02-15 | 2020-03-22 |  | Y | CAMP EVERS 21065020 | 46 |  |  |  | 2021-03-11 09:02
35114140 |  |  |  | STS-POLE_IDLE_REMV - #1E 15986 HWY 26GLE |  |  | FICL |  | 0 | 124 | 124 | 0.023485 | 124 | 0.023485 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6914e-18 |  |  | ST | 2AF | IF |  |  |  |  | 2020-04-09 | [55 empty] | 0 | 0 | 124 | 0.023485 | 0 | 0 | 0.023485 | 2.6914e-18 | 0.023485 | 0 | 0.023485 | 0 | -2.6914e-18 | 0.023485 |  | Keep |  |  | N/A | [7 empty] | 2020-08-07 | [29 empty] | 38.3504 | -120.5825
35114431 |  | 2020 | 220 Mile Plan | CWSP - MORAGA 1101 - LR108540 - PH5 |  |  | FICL | 7673 | 166 | 7421 | 7587 | 1.4369 | 7587 | 1.4369 | 0 | 0 | 0 | 0 | 0 | 0 | -1.8948e-15 |  |  | DI | 08W | SH | 2019-12-06 |  |  | 2019-12-06 |  | 2019-12-06 |  |  | Yes | 2019-12-17 | [12 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Waiting on land - estimating redesigning around land issue - EOD 12/5 | Full |  |  | Yes |  |  | PM submitted request on 9/5. Need Cons dates to submit road closure request |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 7587 | 1.4369 | 0 | 0 | 1.4369 | -1.8948e-15 | 1.4369 | 0 | 1.4369 | 0 | 1.8948e-15 | 1.4369 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-01-02 | 2020-03-27 | 2020-03-27 | 2020-03-23 |  | Yes | Shovel Ready |  | 4623344.8 |  |  | 5279014 | 655669.2 |  |  | 4396853.7 |  |  | -206.182 |  |  | 66 | [9 empty] | Concord | Contra Costa | 0 | 0 | E.5014544.05 |  |  |  | 2020 | Q1 | 2019-12-06 | 2020-01-02 | 2020-03-31 |  | Y | MORAGA 1101108540 | 319
35114629 |  | 2020 |  | BUCOCAMPT 6114 N LIBBY RD PARADISE |  |  | CLSD |  | 0 | 511 | 511 | 0.09678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 511 | 0.09678 | 0 | 0 | 0 | 0 | 0.09678 | 0 | 0.10758 | 0 | 0.10758 | 0 | -0.010795 | 0.10758 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | 2019-09-12 | 2019-09-11 | [7 empty] | 27198.46 |  |  |  | 36019.8 | [17 empty] | 39.7675 | -121.5938 |  | MX |  |  | 2019 | [5 empty] | Y
35115046 |  |  |  | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  |  | UNSC | 12936 | 0 | 12936 | 12936 | 2.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 13219 | 2.5036 | YO | 08W | SH | 2021-12-22 17:00 |  |  | 2020-08-13 | 2020-12-31 | 2020-08-13 | 2020-07-22 | 2020-07-22 | Yes | 2020-08-13 | 08/13: APPROVED INTO PEND08/11: ADE request final corrections to CO; apply and route08/05: Checking in with ADE07/22: EEI Routed for approval07/15: EST target sub (7/28)07/14: ADE rtn 1st corrections to CO07/08 - 07/01: ADE in rvw- priority based06/30: ADE assigned ( [REDACTED] )06/24- 04/15: ADE to be assigned04/13: EEI submitted for 1st ADE rvw04/08: EST 1st sub (4/13)03/25: EST firmed up 1st sub03/03: EST to assess impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/24: EEI submitted for ADE rvw02/19: EEI to advise of any changes02/05: x2 56A that are priority; Job walk - need additional field notes01/29: EEI to follow up with target - EST working alternate project01/08: Push - EST prioritizing corrections on previous 08w work12/18 |  |  |  | 2020 - Q4- M10 [R2021_2] | COMPLETED |  | Wood | 110 | 11 |  | 2020-09-18 | Yes |  |  |  | 2020-09-08 | 2020-09-08 |  |  |  |  | Full | 2020-09-29 | 2020-09-29 | Full |  |  |  | Full |  |  | Yes | 2021-10-07 |  |  |  | 2020-12-07 |  | 2020-11-16 | 2020-10-28 |  | Job walk scheduled for 10/13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.45 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | COMP | 2022-04-08 08:00 | 2022-07-21 17:00 |  | 2022-08-22 17:00 | 2020-10-08 | [7 empty] | 250000 | 5079015.3 |  | 250000 | 0 |  | 2032% | 206488.4 |  |  |  | 2073067.4694 |  | 65 |  |  | Complete |  |  |  |  | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014723.02 | MX |  | 2021-002 | 2021 |  | 2020-12-31 | 2021-04-15 |  |  | Y | MIWUK 170110600 | 1
35115047 |  |  |  | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  |  | PEND | 11880 | 0 | 11880 | 11880 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 |  |  | YO | 08W | SH | 2021-12-22 17:00 |  |  | 2020-08-05 | 2020-12-31 | 2020-08-05 | 2020-07-22 | 2020-07-22 | yes | 2020-10-09 | 08/05: APPROVED - INTO PEND08/04: Final corrections to ADE/CO; EEI corrections applied.07/28: EST routed07/24: ADE rtn 3rd corrections to CO07/23: ADE rtn 2nd corrections to CO; EEI submitted for 3rd ADE rvw07/22: ADE in rvw- priority based07/20: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]07/15: EST target sub (7/24)07/08: ADE rtn 1st corrections to CO07/01: ADE assigned ( [REDACTED] )06/26: EEI resubmitted for 1st ADE rvw [2] - QA06/24 - 01/08: ADE to be assigned12/27: EEI submitted for 1st ADE Rvw12/18: ADE resourcing push; Push 1st sub EST Priority shifts12/04 <-- 11/13: On Track 12/1311/06: Push - PSPS/Fielding Impacts10/29 <-- 10/16: On Track 1st ADE Sub 11/2810/09: Push - 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/22 |  |  |  | 2020 - Q3- M9 [R2021_3] | COMPLETED |  | Comp/Wood | 67 | 42 |  | 2020-09-15 | Yes |  |  |  | 2020-02-11 | 2020-02-11 |  |  |  |  | Full | 2020-02-27 | 2020-02-27 | Full |  |  | 2/27/2020 - No poles in USFS but close. No veg points on USFS as of 2/24/20 check-in | Full |  |  | Yes | 2021-10-07 |  |  |  | 2020-12-28 |  | 2020-12-07 | 2020-11-27 |  | Job walk scheduled for 10/13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-03-03 08:00 | 2022-05-27 17:00 |  | 2022-06-28 17:00 | 2020-10-08 | [7 empty] | 250000 | 3720768.3 |  | 250000 | 0 |  | 1488% | 183961 |  |  |  | 1653674.8 |  | 60 |  | Received prelim drawing on 1/2. | Complete |  |  |  |  | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014723.03 | TL |  | 2021-003 | 2021 |  | 2020-12-31 | 2021-01-30 |  |  | Y | MIWUK 170110600 | 1
35115048 |  |  |  | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  |  | ADER | 11352 | 0 | 11352 | 11352 | 2.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 |  |  | YO | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2021-01-31 | 2020-11-30 | 2020-10-27 | 2020-10-27 | Yes |  | 11/06: EEI submitted corrections for 4th ADE rvwc11/04: ADE rtn 3rd rvw to CO11/03: EEI submitted 2nd corrections for ADE rvw10/29: ADE rtn 2nd review to CO10/28 - 10/14: EST target sub (10/28); EEI submitted 1st corrections for ADE rvw10/10: ADE rtn 1st corrections to CO10/01: EST submitted for 1st rvw, Assigned to [REDACTED] 9/30 - 09/23: EST push (9/30); Priorities09/16: EST push sub (9/25);09/02 - 08/26 - 08/19: EST target sub (9/11); priorities08/12 - 08/05: EST target sub (8/31): priorities07/29 - 07/22: On Track07/15 - 07/01: EST target sub (7/31); Priority Work (Big Basin)06/24: EST target sub (7/2)06/17 - 06/10: On Track10/14: EST target sub (10/23)06/03: Push 2wk; ~100 locations - working on other priority jobs05/27 - 05/20: On Track05/13: EST sub change - priority work (6/12)04/29 - 04/01: On Track03/25: EST firmed up 1st sub (5/8)03/18- 03/03: EST to assess impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/26: Push - EST - Awaiting scope updates from planner02/19: Est priority alignment shift; Push 3/06 ; Refielding some locations (Clearance poles), higher volume of locations than anticipated02/12 |  |  |  | 2020 - Q4- M11 [R2021_4] | R4.2 - ADE Review in Progress |  | Wood | 117 | 2 |  | 2021-01-15 | [11 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF submitted 11/16 | [6 empty] | DWG provided to PC on 11/16 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-17 17:00 |  | INPR | 2022-04-07 08:00 | 2022-07-01 17:00 |  | 2022-08-02 17:00 | [8 empty] | 250000 | 3069392.3 |  | 250000 | 0 |  | 1228% | 36747.7 |  |  |  | 1427624.3256 |  | 57 |  |  | Complete |  |  |  |  | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014723.04 | MX |  | 2021-004 | 2021 |  | 2020-12-31 | 2021-04-15 |  |  | Y | MIWUK 170110600 | 1
35115049 |  |  |  | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  |  | ESTS | 11880 | 0 | 11880 | 11880 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 |  |  | YO | 08W | SH | 2023-12-25 |  |  | 2020-11-15 | 2021-01-31 | 2020-11-15 | 2020-08-05 | 2020-08-05 | Yes | 2020-09-24 | 11/04: On Track - pending response on constructibility changes and feedback (Inspector)10/27: Target RD EOD 11/1510/26: EST - working with ADE on approaches to apply changes10/26: PMGR provided construction rvw; As noted by construction management on the attached email, please revise 10/23: EEI submitted for 1st RD ADE rvw [2]; applied adjustments; ADE approved10/22: EEI submitted for 1st RD ADE rvw10/22: ADE - Version 2 has been created in EES. Update Loc-101, 105, 108, 111, & 121; EST - looked into the requested locations and responded with findings10/19: [REDESIGN] ADE - Here is a new project for 35115049 MIWUK 1701 LR10600 PH 1-5; KMZ is ready for SME review. No Agency lands or Waters/Wetlands. ECL is green; ERTC is due 11/16, so if you can have your reviews completed by 11/9 or 11/10, that would be very helpful ======09/24: APPROVED - INTO PEND09/23: Request with Planner for DS73 to be completed to route; ADE rtn 6th corrections to CO09/22: EEI submitted for 6th ADE rvw; Still no word from planner to complete DS7309/19 [REDACTED] |  |  |  | 2020 - RD- M11 [R2021_5] | RD1.3_Rdsn - EST Implementing Redesign Corrections |  | Wood | 104 | 0 |  | 2020-09-30 | Yes |  |  |  | 2020-11-16 | 2020-11-16 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | No enviro constraints identified. Potential land constraints on private property. |  |  | 2020-11-13 |  |  |  | [REDACTED] to submit to county on 10/13/20 |  | 2020-12-20 |  | 2020-12-02 | 2020-11-27 |  | Job walk scheduled for 10/14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-12 08:00 |  | INPR | 2022-02-11 08:00 | 2022-05-09 17:00 |  | 2022-06-08 17:00 | [5 empty] | Yes |  |  | 250000 | 4060326 |  | 250000 | 0 |  | 1624% | 225215.2 |  |  |  | 1804589.3333 |  | 60 |  |  | Complete |  |  |  |  | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014723.05 | MX |  | 2021-005 | 2021 |  | 2020-12-31 | 2021-04-15 |  |  | Y | MIWUK 170110600 | 1
35115050 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Scoped | CONS | 7882 | 0 | 8512 | 8512 | 1.6121 | 0 | 0 | 8512 | 1.6121 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-24 |  | Y | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2019-11-13 | 2019-11-13 | Yes | 2020-02-13 | 02/13: APPROVED - IN PEND02/12: Final corrections requested for APPROVAL - wrong doc upload, generating errors02/06: ADE/EST coordiated to conclude corrections02/05: ADE rtn 5th corrections to CO; EEI submitted for 6th ADE rvw1/30: EEI submitted for 5th ADE rvw; 1/31 EST/ADE coordition on uploads01/29: EST target??1/28: ADE rtn 4th corrections to CO01/23: ADE/EST coordination of corrections; EEI submitted for 4th ADE rvw, OCalcs stamped - except 205,230,263 due for restamp to comply with land's req.01/22: On track per email01/17: ADE request correction ETA; EST target 1/24 Friday01/15: EST target for 4th sub?? EOD at risk? Est priority - working alternate 08W01/08: ADE rtn 3rd corrections to CO12/20: EEI submitted for 3rd ADE rvw12/18: EST Priority shifts12/03 ADE rtn 2nd corrections to contractor11/27 <-- 11/20: Push to 12/06 2nd rvw: ADE bandwith11/14: EEI submitted for 2nd ADE rvw11/06: ADE rtn 1st corrections to contractor10/30: ADE Assigned ( [REDACTED] )10/29 <-- 10/16: ADE to be assigned (waiting for 2020 priority list)10/07: EEI submitted for 1st ADE rvw10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) |  |  |  | 2020 - Q1- M2 [R6] | COMPLETED | Yes | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-05-23 | 2020-05-23 |  |  |  |  | Full | 2020-05-23 | 2020-05-23 | Full |  |  | Caltrans permit - Dist. 10 - Caltrans due 5/22 | Full |  |  | Yes |  |  | T-Line issue |  | 2020-08-14 | Y | 2020-07-23 |  |  | 60% complete as of 8/11 | [7 empty] | 0 | 0 | 0 | 0 | 1600 | 0.30303 | 0.30303 | 1.3091 | 0.27538 | 0 | 1.6241 | 1.3487 | 0.027652 | 0 |  | Keep | 2020-06-30 | Yes | COMP | 2020-08-10 | 2021-04-19 08:00 |  | 2021-04-30 17:00 | 2020-05-15 | 2020-08-10 07:00 | 2021-04-09 16:00 |  | 2020-07-24 | Yes | Shovel Ready |  | 2809593 | 921011 | 744758.2 | 4091239 | 1281646 | 1356797.3 | 32.78% | 918407.8 | 534387.9 | 1452795.7 |  | 571303.8158 |  | 40 | [9 empty] | Twain Harte | Tuolumne | 38.0571 | -120.2065 | E.5014771.02 |  |  | 2020-006 | 2020 | Q3 | 2020-02-29 | 2020-06-12 | 2020-08-04 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35115051 |  |  |  | CWSP - MIWUK 1701_OCB - PH 1.3 |  |  | CONS | 5350 | 0 | 5484 | 5484 | 1.0386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0386 | 5484 | 1.0386 | YO | 08W | SH | 2020-08-05 |  |  | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-01-30 | 2020-01-30 | Yes | 2020-05-08 | 03/03: Concur needed; route for approvals, per [REDACTED] APPROVED - INTO PEND02/26: EEI submitted final corrections; routed for approval02/25: ADE - Returning EES estimate for final changes.02/24: EST - EES has been routed02/19: ADE rtn 3rd corrections to CO; EST to apply and route for approval.02/13: EEI submitted for 3rd ADE rvw02/12: EST target 3rd sub 2/1402/04: ADE rtn 2nd corrections to CO01/30: EEI submitted for 2nd ADE rvw01/29: ADE request refield/notes on some locations01/22: Pending OCALC completion - submit EOW01/08: Est target? Est working 2nd Miwuk job w/ approx 200 locs.12/19: ADE rtn 1st corrections to contractor12/18 <-- 11/06: ADE status?10/30: ADE assigned ( [REDACTED] )10/29 <-- 10/16: ADE to be assigned (waiting for 2020 priority list)10/10: Submitted for 1st ADE rvw10/02: EEI 1st submittal target update to 10/079/04 |  |  |  | 2020 - Q1- M2 [R7] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-02-26 | 2020-02-26 |  |  |  |  | Full | 2020-03-20 | 2020-03-20 | Full |  |  |  | Full |  |  | Yes | 2021-03-27 |  |  |  | 2020-09-25 | Y | 2020-08-05 | 2020-08-05 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0386 | 0 | 0 | 2.1413 | 2.1413 | 0 | 0 |  | Remove | 2020-07-06 | Yes | COMP | 2022-01-05 08:00 | 2022-03-01 17:00 |  | 2022-03-31 17:00 | 2020-05-08 |  |  |  |  | Yes | Shovel Ready |  | 1798332.5 | 1113028.4 |  | 2865068 | 1066735.5 |  | 61.89% | 88023.1 |  |  |  | 1071624.7177 |  | 27 | [9 empty] | Twain Harte | Tuolumne | 38.0571 | -120.2065 | E.5014771.03 | TL |  | 2020-007 | 2020 | Q3 | 2020-02-29 | 2020-06-13 | 2020-07-28 |  | Y | MIWUK 1701CB | 2
35115052 |  |  |  | CWSP - MIWUK 1701_OCB - PH 1.4 |  |  | CONS | 8140 | 0 | 8551 | 8551 | 1.6195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6195 |  |  | YO | 08W | SH | 2020-08-31 |  |  | 2020-07-24 | 2020-05-08 | 2020-07-24 | 2020-02-25 | 2020-02-25 | Yes | 2020-07-23 | 07/22: PEND - Manually updated; not complete - SAP issue still open07/15: EOD (7/24); RISK - Needing to update planned units in SAP - EES ticket submitted05/08: APPROVED - INTO PENDRedesign05/05: EEI re routed for approval04/30: Final approval corrections rtn to CO04/29: ADE status (focusing on completion)04/16: EEI submitted for ADE rvw04/14: EEI submitted for ADE rvw - ADE rtn 6th corrections to CO; when the changes are made and upload the Estimate and all required documents in Sap. I will review the estimate and concur if everything is correct.04/08: ADE rtn 5th corrections to CO04/07: EEI submitted for 4th ADE rvw04/02: ADE rtn 4th corrections to CO03/31: EEI submitted for 4th ADE rvw03/26: ADE rtn 3rd corrections to CO03/23: EEI submitted for 3rd rvw03/18: EST confirmed sub date03/17: ADE rtn 2nd corrections to CO03/13: ADE rcv'd revised stamped OCalcs (in rvw)03/11: Differing status - need to align information??02/25: EEI submitted for 2nd ADE rvw02/12: EST confirmed target date 2/2402/10: ADE rtn 1st corrections to CO02/05: ADE status?? Prelim coming due01/15: ADE prioritizing 1st Qtr job (35072360), not started, records show this is a 2nd Qtr priority.01/04: ADE reassigned [REDACTED] 2/30: ADE Rejected 1st sub - Rtn for Stamping requirements12/27: ADE assigned ( [REDACTED] )12/18: ADE resourcing push12/06: EEI Submitted for 1st ADE rvw11/27: Push to 12/06; firm up Composite impact & Est in review11/20: Composite Pole change impact - push to next wk (9pols/ 11hrs)11/06: Push - PSPS/Fielding & additional pole locations10/29 <-- 10/16: On track 1st sub for 11/610/09: Push - 2wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: Ont Track09/04: On Track for 1st Submittal 10/23 |  |  |  | none- M7 [RRD_Redesign] | Iss_RD0.0_Rdsn - Estimating Redesign |  | Comp | 20 | 50 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2021-01-09 |  | No construction drawings as of yet? |  | 2020-11-20 |  | 2020-08-17 |  |  | 98% complete as of 12/1 - 1 crane tree remains. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6195 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-27 17:00 | Yes | COMP | 2022-01-06 08:00 | 2022-03-09 17:00 |  | 2022-04-08 17:00 | 2020-07-28 |  |  |  | 2020-08-31 | Yes |  |  | 2926489.8 | 1780267.3 |  | 4217803 | 1291313.2 | 2503413.3 | 60.83% | 388669.1 | 34407.4 | 423076.5 |  | 1099264.5707 |  | 41 | [13 empty] | E.5014771.04 | TL |  | 2020-008 | 2020 | Q3 | 2020-03-31 | 2020-04-30 | 2020-06-22 |  | Y | MIWUK 1701CB | 2
35115053 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Scoped | CONS | 9571 | 0 | 9571 | 9571 | 1.8127 | 0 | 0 | 9571 | 1.8127 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-28 |  | Y | 2020-04-08 | 2020-04-06 | 2020-04-08 | 2020-01-17 | 2020-01-17 | Yes | 2020-06-29 | 04/08: Redwork completed - APPROVED; INTO PEND04/01: EEI sub for 6th ADE rvw03/31: ADE rtn 5th corrections to CO03/30: EEI submitted for 5th ADE rvw03/27: ADE rtn 4th corrections to CO03/19,20: EEI submitted for 4th ADE rvw (changes applied); pending change order approval. ADE advise, should be done by EOM, dependent on change order.03/18: Job to go back to Contractor; adding 2 poles, will be 10 pole calculation impact and forms. FE identified an opportunity to reduce veg work on this job by $100k with by slightly re-routing the distribution line.03/04: EST advised - added/revised the materials in EES for the locations added/revised the materials in EES for the locations; changes should be handled as a redline corrections internally by PG&E since this job has technically already been approved ??02/26: Removed from PEND for revision request by PM and Fld Engr - extra materials could be added, due to them having to redesign and re-route a portion of the proposed tapline due to vegetation cost concerns in the field01/30: INTO PEND01/23: EEI submitted for 3rd ADE rvw01/22: ADE rtn 2nd corrections to CO01/14: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]01/08: Est Target?12/27: ADE rtn 1st corrections to contractor12/18 <-- 12/11: Push ADE bandwith/priorities11/27 <-- 11/20: In review11/18: ADE Assigned ( [REDACTED] )11/04: EEI submitted for 1st ADE rvw10/29 <-- 10/16: On track 1st sub for 11/610/09: Push - 2wk; Impacted by numerous scope updates to previously approved key10/02 <-- 9/11: Ont Track09/04 |  |  |  | 2020 - Q1- M2 [R9] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | 3/20/2020 - May move out 2 days as USFS comment period closes on 3/19/20_PARTIAL ERTC issued 2/28/20; Submitted to USFS on 3/6/20 | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-07-22 | Y | 2020-06-08 |  |  | 100% PI/back tie isu | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8127 | 0 | 0 | 1.7366 | 1.7366 | 0 | 0 |  | Keep | 2020-05-19 17:00 | Yes | COMP | 2020-08-11 08:00 | 2021-06-17 17:00 |  | 2021-07-19 17:00 | 2020-07-07 | 2021-04-19 07:00 | 2021-05-28 16:00 |  | 2020-07-28 | Yes | Shovel Ready |  | 1670415.5 | 895273.3 | 204609 | 2296559 | 626143.5 | 744378.6 | 53.59% | 657348.7 | 268688.2 | 926036.9 |  | 493892.2813 |  | 48 | [13 empty] | E.5014771.05 |  |  | 2020-009 | 2020 | Q3 | 2020-02-29 | 2020-04-20 | 2020-06-16 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35115054 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 - OCB - PH 2.2 |  | Scoped | CONS | 7255 | 0 | 7523 | 7523 | 1.4248 | 0 | 0 | 7523 | 1.4248 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-31 |  | Y | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-01-06 | 2020-01-06 | Yes | 2020-02-18 | 02/18: PEND 02/05: ADE approved for routing 02/05: EEI submitted for 4th ADE rvw 01/29: ADE rtn 3rd corrections to CO 01/28: 3rd rvw target EOW (1/31) 01/16: EEI submitted for 3rd ADE rvw 01/13: ADE rtn 2nd corrections to contractor 01/08: ADE target 1/13? 01/06: EEI uploaded Wetstamp Calcs 01/01: ADE request wet stamps 12/31: EEI submitted for 2nd ADE rvw - [PRELIM DWGS ready] 12/18: EST 2nd Push Fielding priorities 12/04 <-- 11/27: Issue with pole loc, requires field visit (Customer/Service pole placement); working on resolution 11/20 <-- 11/13: On Track 2nd submittal 11/11: ADE returned corrections to contractor 10/29 <-- 10/09: ADE to be assigned (waiting for 2020 priority list) 10/01: EEI submitted for 1st ADE rvw 9/04: EEI to supply new target dates (push) |  |  |  | 2020 - Q1- M2 [R121] | COMPLETED |  | Wood | 63 | 0 |  |  | Yes | [9 empty] | Full | 2020-05-02 | 2020-05-02 | Full |  |  | Caltrans permit expected 3/27 - Dist. 10 - 3/27/2020 CHANGE TO 5/2/2020 due to Caltrans rejection of permit (update as of 2/24/2020) | Full |  |  | Yes |  |  | [REDACTED] sending prelim on 12/10/19 |  | 2020-07-24 | Y | 2020-07-03 |  |  | 95% Complete as of 7/14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4248 | 0 | 0 | 1.4612 | 1.4612 | 0 | 0 |  | Keep | 2020-07-01 | Yes | COMP | 2020-08-24 | 2021-04-16 17:00 |  | 2021-04-30 17:00 | 2020-04-06 | 2020-08-24 07:00 | 2021-05-21 16:00 |  | 2020-06-08 | Yes | Shovel Ready |  | 2482661 | 1512020.6 | 747161.7 | 3789178 | 1306517 | 748133.6 | 60.9% | 1300595.9 | 433931.5 | 1734527.4 |  | 1061208.1308 |  | 37 | [9 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5015427.02 |  |  | 2020-121 | 2020 | Q3 | 2020-02-29 | 2020-07-16 | 2020-09-04 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35115055 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 - OCB - PH 2.3 |  | Scoped | CONS | 11088 | 0 | 11269 | 11269 | 2.1343 | 0 | 0 | 11269 | 2.1343 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-01 |  | Y | 2020-04-20 | 2020-04-21 | 2020-04-20 | 2020-04-02 | 2020-04-02 | Yes | 2020-04-21 | 04/20: Routed; complete final corrections for approval; EST applied correcitons; 04/15: EST target 5/17; INTO PEND 04/14: ADE rtn 4th corrections to CO 4/14: EEI submitted for 4th ADE rvw - routed 04/10: ADE rtn 3rd corrections to CO 04/09: EEI submitted for 3rd ADE rvw 04/08: EST - working through 107 locations; require more time than anticipated 04/07: ADE rtn 2nd corrections to CO 04/02: EEI submitted for 2nd Rvw 03/25: On Track 03/16: ADE rtn 1st Corrections to CO 03/11: ADE Status/Target?? 03/03: ADE reassiged (Walter); per request 02/26 - 02/19: ADE check in on status?? 01/28: ADE assigned (MIke T) 01/15 <-- 01/08: ADE to be assigned 12/19: EEI submitted for 1st ADE rvw 12/18: ADE resourcing push; EST Awaiting Ocalc stamping 11/27 <-- 11/13: On Track 12/13 11/06: Push - PSPS/Fielding Impact 10/29 <-- 10/16: On track 1st sub for 11/28 10/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs. 10/02 <-- 9/11: On Track 09/04: On Track for 1st Submittal 11/22 |  |  |  | 2020 - Q1- M3 [R122] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-01-21 | 2020-01-21 |  |  |  |  | Full | 2020-02-04 | 2020-02-04 | Full |  |  |  | Full |  |  | Yes | 2021-03-04 |  |  |  | 2020-07-20 | Y | 2020-07-01 | 2020-07-01 |  | 80% complete as of 7/14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1343 | 0 | 0 | 2.3053 | 2.3053 | 0 | 0 |  | Keep | 2020-06-09 | Yes | COMP | 2020-12-31 08:00 | 2021-04-26 17:00 |  | 2021-06-07 17:00 | 2020-05-15 | 2021-01-07 07:00 | 2021-04-15 16:00 |  | 2020-07-01 | Yes | Shovel Ready |  | 2901359.9 | 1068225.7 | 655429.1 | 3784068 | 882708.1 | 1713310.4 | 36.81% | 1059782.4 | 128267.1 | 1188049.5 |  | 500508.6251 |  | 56 | [9 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5015427.03 | MX |  | 2020-122 | 2020 | Q3 | 2020-03-31 | 2020-07-14 | 2020-09-13 |  | Y | MIWUK 1701CB | 2353 |  | PRE
35115056 |  |  |  | CWSP - MIWUK 1701 - OCB - PH 2.4 |  |  | CONS | 8445 | 0 | 9236 | 9236 | 1.7492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7492 |  |  | YO | 08W | SH | 2020-08-10 |  |  | 2020-07-15 | 2020-07-31 | 2020-07-15 | 2020-02-28 | 2020-02-28 | Yes | 2020-07-07 | 03/31: INTO PEND 03/27: ADE rtn 3rd corrections to CO - EEI submitted for 4th Rvw - ADE request minor correction, begin routing. 03/25: EEI submitted for 3rd ADE rvw 03/21: ADE rtn 2nd corrections to CO 03/18- 003/01: ADE On Track?? 02/28: EEI submitted for 2nd ADE rvw 02/17: ADE rtn 1st corrections to CO 01/29: ADE Progress; Reprioritized in alignment to Q1, ADE needs to align workload... 01/08: ADE work mulitple PMs; target correction rtn to CO Wens next week if possible; another higher priority PM may return in the interum <-- 12/18: ADE status, due next week? 12/03: ADE assigned (Nathan) 11/06: EEI submitted for 1st ADE rvw 10/29 <-- 10/16: On track 1st sub for 11/06 10/09: Push 1wk; Impacted by numerous scope updates to previously approved key 10/02 <-- 9/11: Ont Track 09/04: On Track for 1st Submittal 10/23 |  |  |  | 2020 - Q1- M3 [R123] | COMPLETED |  | Wood | 83 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Estimating being revised - moved to 2/4/20 due to riparian area concerns | Full |  |  | Yes |  |  |  |  | 2020-12-01 |  | 2020-08-10 |  |  | 98% Complete as of 12/1/20 - line covers waiting on [REDACTED] to return | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7492 | 0 | 0 | 1.8169 | 1.8169 | 0 | 0 |  | Remove | 2020-07-06 | Yes | COMP | 2022-02-09 08:00 | 2022-04-22 17:00 |  | 2022-06-07 17:00 | 2020-07-13 |  |  |  |  | Yes |  |  | 3269480.5 | 2227203.2 |  | 4578906 | 1309425.5 |  | 68.12% | 509096.1 |  |  |  | 1273238.7285 |  | 43 | [13 empty] | E.5015427.04 |  |  | 2020-123 | 2020 | Q3 | 2020-03-31 | 2020-05-30 | 2020-07-22 |  | Y | MIWUK 1701CB | 2
35115057 |  |  |  | CWSP - MIWUK 1701 - OCB - PH2.5 |  |  | UNSC | 10875 | 0 | 13653 | 13653 | 2.5858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5858 |  |  | YO | 08W | SH | 2021-01-08 |  |  | 2020-07-26 | 2020-10-31 | 2020-07-26 | 2020-07-14 | 2020-07-14 | Yes | 2020-07-24 | 07/24: APPROVED - INTO PEND 07/21: EEI routed for approval 07/16: ADE rtn 2nd corrections to CO; apply and route 07/15: ADE in rvw - working now. 07/14: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready] 07/09: ADE rtn 1st corrections to CO 07/08 - 07/01: ADE status; checking in with ADE 06/24 - 06/03: ADE in rvw (bundle req) - ADE target EOW 05/29: ADE assigned (Chris) 5/28: EEI submitted for 1st ADE rvw 05/27: EST push 1wk (5/29) - Ready to submit - getting OCalcs signed and stamped 05/20 - 05/13: On Track (5/22) 05/06: EST Redoing parts of the construction dwg 04/29: EST to prioritize and pull in if possible - On a CWSP call about a handful of projects to pull up in the plan. 99% of the work in is PEND and the only impact is the substitution effort. want to be able to bundle with other Miwuk circuits for cost saving in the Bid process 04/28: EST push 1st sub 06/08 04/22 - 04/15: Restart - Under further rvw (1st sub 5/1) 04/08: Est sub date; DWG needs to be redone - EST to firm up 1st sub date 04/01: Laptop issues - reviewing to see how much work needs to be redone 03/25: Waiting on Laptop 03/18- 02/19: Est priority alignment shift; EST Computer unavailable - EST to firm up date to maintain EOD 02/12 - 01/29: Computer Issue - working on file recovery (2wk per TSC) 1/22: Push 1wk, Equipment issues (on loaner computer) 01/15: EST on track?? 01/08: EST push 1st submittal - 03/35: Waiting on Laptop 12/18: ADE resourcing push; EST Priority shifts/laptop issues 11/27 <-- 11/13: On Track 12/13 11/06: Push - PSPS/Fielding Impact 10/29 <-- 10/16: On track 1st sub for 11/28 10/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs. 10/02 <-- 9/11: On Track 09/04: On Track for 1st Submittal 11/22 |  |  |  | 2020 - Q3- M7 [R2022(+)_124] | COMPLETED |  | Comp | 14 | 64 |  |  | Yes |  |  |  | 2020-10-12 | 2020-10-12 |  |  |  |  | Full | 2021-01-08 | 2021-01-08 | Partial |  |  | PERTC excluding USFS was issued 9/28/20. USFS review to be delayed due to Forest Service Closures. Moving ERTC date out 1 month as placeholder. Forest Svs locations; veg scope received week of 9/28. | Partial |  | 2020-09-10 | Yes | 2021-08-24 |  | No construction drawings as of yet? |  | 2020-11-03 | Y | 2020-10-13 | 2020-10-02 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5858 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-22 17:00 | Yes | INPR | 2022-01-18 08:00 | 2022-03-31 17:00 |  | 2022-05-10 17:00 | 2020-09-28 |  |  |  |  | No |  |  | 3295054 | 2933209.6 |  | 4165227 | 870173 |  | 89.01% | 210832.4 |  |  |  | 1134354.8442 |  | 55 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5015427.05 | ML |  | 2020-124 | 2021 | Reserve | 2020-04-30 | 2020-08-13 | 2020-10-12 |  | Y | MIWUK 1701CB | 2
35115147 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 |  |  | FICL | 8690 | 0 | 6478 | 6478 | 1.2269 | 6478 | 1.2269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 |  |  | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-01-17 | 2020-01-17 | Yes | 2020-02-25 | 02/25: IN PEND 02/24: Final corrections requested for approval - PIKE completed and routed 02/18: ADE Status?? 1/28: EST target?? 01/24: ADE rtn 2nd corrections to CO 11/17: PIKE submitted for 2nd rvw - [PRELIM DWG ready] 01/14: Additional fielding completed 1/13; QTY correction and some backtrack adjustments required. 01/06: ADE rtn 1st corrections to contractor 12/31: Large amount of corrections - ADE still in progress 12/17: ADE On track 12/10: ADE working Backlog PMs - reprioritized to 08W 11/26: ADE vacation/Holiday - Push 10/19: Check with ADE on target 10/22: Push 1month (Nov) - ADE Resourcing 10/15: ADE to be assigned - waiting for 2020 priority list 10/08 ADE to be assigned 10/02: PIKE submitted for 1st ADE rvw 10/01: Implementing further adjustments - submitting 10/01 9/17 - 9/24: On Track 9/10: Swap 1st submittal with 3.3 8/27 - 9/03: On track (may swap with another) 8/20: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities 8/13: PIKE communicated potential pressures on 1st ADE submittal target, due to computer limitations and technical issues (Highlights: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis 7/23 - 8/6: On Track for 9/6 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] |  |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 1/7/2020 | Full |  |  | Yes |  |  | Permit not required per SAP No permits needed. |  | 2020-05-29 | Y | 2020-05-01 |  |  | Started 5/1/20 | [7 empty] | 0 | 0 | 6478 | 1.2269 | 0 | 0 | 1.2269 | 0 | 1.2269 | 0 | 1.2269 | 0 | 0 | 1.2269 |  | Keep | 2020-02-17 | Yes | N/A | 2020-05-05 | 2020-08-13 | Yes | 2020-08-13 | 2020-02-26 | 2020-06-30 | 2020-07-22 | 2020-08-13 |  | Yes | Shovel Ready |  | 3614964.3 | 1369454.2 | -233251 | 5398830 | 1783865.7 |  | 37.88% | 1602705.2 |  |  |  | 1116196.0753 |  | 44 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.02 |  |  | 2020-138 | 2020 | Q2 | 2020-03-31 | 2020-08-01 | 2020-09-07 |  | Y | BRUNSWICK 110350070 | 7
35115148 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  |  | FICL | 12685 | 0 | 10627 | 10627 | 2.0127 | 10627 | 2.0127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-05-01 |  |  | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-03-31 | 2020-03-31 | Yes | 2020-04-24 | 04/24: APPROVED - INTO PEND 04/23: EST submitted corrections 04/22: ADE approval req minor correction 04/21: EST routing for approval 4/16: ADE rtn corrections; ready for concur 04/14: Applying corrections (target today- 4/17 latest) 04/13: ADE rtn 3rd corrections to CO 04/07: EST sub date (4/10) 04/01: ADE rtn 2nd corrections to CO 03/31: PIKE submitted for 2nd ADE rvw; PRj Mgr request completion; GC planning to start construction on this phase 5/18/2020 03/24: EST status - in PE stamping 03/17: EST on track 03/11: EST seeking clarification on comments; used FRD Guide TD9001B-008 REV1 (earlier project) 03/10: ADE rtn 1st corrections to CO 03/03 - 02/25: ADE Status/Target date?? <requested> Pushed 01/27: PIKE reSubmitted for 1st ADE rvw; Tie-ins resolved and stamping completed 01/14: No Tie Required, PE Stamping - With Est to adjust and submit; 2nd sub set for 1/24 11/19: Push 1 month - ADE Resourcing 11/05: Tie-in "out of scope" 2ph/3ph?? 10/22: PUSH 1 month - ADE Resourcing 10/15: ADE to be assigned - holding for 2020 priority list 9/24 - 10/08: ADE to be assigned 9/20: PIKE Submitted for 1st ADE rvw 9/17: On track 9/10: Swap 1st submittal with 3.2 8/27 - 9/03: On track 8/13: PIKE communicated potential pressures on 1st ADE submittal target, due to computer limitations and technical issues (Highlights: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis 7/23 - 8/6: On Track for 9/13 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] |  |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 11/27/19 | Full |  |  | Yes | 2020-12-31 |  | Project is complete, waiting for GC to submit As-buillts |  | 2020-07-10 | y | 2020-05-01 |  |  | 14 Units remaining - Started | [7 empty] | 0 | 0 | 10627 | 2.0127 | 0 | 0 | 2.0127 | 0 | 2.0127 | 0 | 2.1231 | 0.11042 | 0 | 2.0127 |  | Keep | 2020-04-13 | Yes | N/A | 2020-06-02 | 2020-07-23 | Yes | 2020-11-20 | 2020-05-15 | 2020-11-30 | 2020-11-30 | 2020-11-20 |  | Yes | Shovel Ready |  | 3793181.4 | 3045752.6 | -387334 | 5062019 | 1268837.6 |  | 80.29% | 3433086.6 |  |  |  | 1513275.0285 |  | 64 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.03 |  |  | 2020-138 | 2020 | Q3 | 2020-03-31 | 2020-06-01 | 2020-07-08 |  | Y | BRUNSWICK 110350070 | 7
35115149 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 |  |  | CLSD | 9091 | 0 | 6692 | 6692 | 1.2674 | 6692 | 1.2674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-30 |  |  | 2019-11-30 | 2019-11-25 | 2019-11-30 |  |  | Yes | 2019-11-27 | 02/04: Engineer communicated no change to design. Reduction in design.01/28: Back to Est/Needing additional EST - Scope changes reroute driven by Customer, move to end of property vs. through. (New PM)01/06: Land feedback - existing line through property - Owner requesting line move to edge of property.11/25: SAP Export - UNSC11/19: Rcv'd clarification - Stay with original; EST Bandwith - working [REDACTED] prioritize (EOW)11/12: Pending ADE clarification - tie in; inconsistent with scope: [REDACTED] assisting on followup for clarification on how to proceed - contacted [REDACTED] Last week 11/05: Working through implementation/scheduling10/29: At Risk for push - Last minute reroute - PIKE/ [REDACTED] to take offline to discusss implementing reroute and schedule impacts10/22: On Track (10/31)10/15: A] Minor corrections (original scope) on track B] CMCS feedback (new information/scope change): Tie-in needing to be 3-wire.10/11: 1st ADE corrections rtn to contractor10/09: |  |  |  | Unassigned | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Easements are no longer needed, project was re-designed to avoid new easements, 2 easements needed. Docs sent to acquisition on 1/13. - Looking at redesign to avoid an easement | Full |  |  | Yes |  |  | Drawings submitted 1/7/2020 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 6692 | 1.2674 | 0 | 0 | 1.2674 | 0 | 1.2674 | 0 | 1.2674 | 0 | 0 | 1.2674 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-02-28 | 2020-04-02 | 2020-05-29 | 2020-06-08 |  | Yes | Shovel Ready |  | 3334606.4 |  | -213318 | 5030060 | 1695453.6 |  |  | 2837051.6 | [5 empty] | 46 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.04 |  |  | 2020-138 | 2020 | Q2 | 2019-11-27 | 2020-08-08 | 2020-09-14 |  | Y | BRUNSWICK 110350070 | 7
35115150 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  |  | FICL | 6046 | 0 | 6241 | 6241 | 1.182 | 6241 | 1.182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-06-26 |  |  | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-02-01 | 2020-02-01 | Yes | 2020-06-01 | 06/01: APPROVED - INTO PEND05/29: Est Routed in EES05/26: Completing stamping; Target (5/29)05/19: On Track05/05: Completing Construction adjust to alternate PM; Target sub to (5/20); apply corrections and stampgin04/28: EST sub target (5/08)04/27: ADE rtn 2nd corrections to CO04/15: ADE reassigned ( [REDACTED] )04/14: [REDACTED] ; back on PSPS; Review for reassignment (rvw may need to be restarted)03/31: [REDACTED] (out sick); following up with status update03/24: PSPS wrapping up - [REDACTED] to rtn to 08W03/17 - 02/25: push[2] ADE Status/Target date?? ( [REDACTED] on PSPS)03/09: EST - has been updated to reflect the design changes and additions asked for by [REDACTED] (added locations)02/11: ADE Status??02/01: PIKE submitted for 2nd ADE rvw - [Prelim DWG ready]01/28: On Track01/08: ADE rtn 1st Corrections to contractor12/06: ADE assigned ( [REDACTED] )11/19 & 10/22: PUSH 1 month (NOV, DEC) - ADE Resourcing10/15: ADE to be assigned - holding for 2020 priority list10/11: PIKE submitted for 1st ADE rvw9/03 - 10/08: On Track8/20 - 8/27: 1st Submittal push 2wks - Priorities/Equip-Resource Availabilities7/23 - 8/6: On Track for 9/277/19: Vendor Provided 1st ADE Sub dates7/16: |  |  |  | 2020 - Q1- M3 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes |  |  | Drawing submitted 1/7/2020 |  | 2020-07-13 | y | 2020-06-08 |  |  | 13 Units remaining - Starting 6/24/20 | [7 empty] | 0 | 0 | 6241 | 1.182 | 0 | 0 | 1.182 | 0 | 1.182 | 0 | 1.2155 | 0.033523 | 1.7225e-16 | 1.182 |  | Keep | 2020-06-26 | Yes | N/A | 2020-06-29 | 2020-08-25 | Yes | 2020-08-25 | 2020-06-10 | 2020-07-06 | 2020-08-25 | 2020-08-25 |  | Yes | Shovel Ready |  | 3214155.4 | 850334.7 | -266072 | 4212019 | 997863.6 |  | 26.45% | 1116406.7 |  |  |  | 719398.6887 |  | 31 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.05 |  |  | 2020-138 | 2020 | Q3 | 2020-03-31 | 2020-06-01 | 2020-07-08 |  | Y | BRUNSWICK 110350070 | 7
35115151 |  | 2021 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Scoped | CONS | 10010 | 0 | 10010 | 10010 | 1.8958 | 0 | 0 | 10010 | 1.8958 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-20 |  | Y | 2020-05-29 | 2020-05-31 | 2020-05-29 | 2020-04-24 | 2020-04-24 | Yes | 2020-07-25 | 05/29: APPROVED - INTO PEND05/27: BCF submited for 5th ADE rvw; approved for rerouting; BCF routed05/23: ADE rtn the corrections to CO; apply and routed05/22: BCF submitted for 4th ADE rvw05/18: ADE rtn 3rd corrections to CO05/08: BCF submitted for 3rd ADE rvw05/05: EST target sub (05/08) - will advise of change05/01: ADE rtn 2nd Corrections to CO04/24: BCF submitted for 2nd ADE rvw04/21: On Track04/14: EST to firm sub date (4/24); EST/ADE working on directions for various items4/11: ADE rtn 1st [2] corrections to CO04/07- 03/17 ADE Status?? (Due) (auto push 4/3, push 4/10)03/04: BCF submitted for 1st ADE rvw [2] - ADE proceeding03/03: EST implementing Export program for formatting; Sub this week02/26 - 02/20: ADE Rejected 2/21; EST coordination of labeling/upload photos - ADE requires more than one photo for some of the poles where there are anchors, services and or TX02/10: ADE assigned (Nathan) - ADE to start review this week01/31: BCF submitted for 1st ADE rvw01/07: On Track12/17: Anticipate Weather impacts. -Visited sight, Fielding scheduled to start in following weeks12/10: Prioritize for Q3 Const.12/02: Veg scheduled to be completed 2nd wk Dec11/12 <-- 10/17: Push 2mnth - J [REDACTED] s. He's going to review the locations mid November and provide a timeframe to complete the veg work10/15: Status quo10/08: Veg management issues (no line of site/access issues)- need line cleared for Estimating to proceed - Est team to initiate communication with Veg Mgmnt; (initial 4wk push) to address/coordinate resolution 10/01 |  |  |  | 2020 - Q2- M4 [R137] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-23 | 2020-04-23 | Full |  |  | CIF Submitted 3/9/2020 | Full |  |  | Yes | 2020-12-20 |  |  |  | 2020-07-31 | Y | 2020-06-29 |  |  | Starting early July | [7 empty] | 0 | 0 | 0 | 0 | 4066 | 0.77008 | 0.77008 | 1.1258 | 0.76951 | 0 | 1.8788 | 1.1093 | 0.00056818 | 0 |  | Keep | 2020-07-18 | Yes | COMP | 2020-08-17 | 2021-04-12 17:00 |  | 2021-07-05 17:00 | 2020-07-27 | 2021-01-05 06:00 | 2021-03-19 16:00 |  | 2020-07-20 | Yes | Shovel Ready |  | 4025666.4 | 3456051.7 | 2520547.9 | 5273989 | 1248322.6 | 2422677.5 | 85.85% | 1408323.8 | 194665.1 | 1602988.9 |  | 1822972.3253 |  | 51 |  | Will be underway | [7 empty] | Nevada City | Nevada | 0 | 0 | E.5015568.02 |  |  | 2020-137 | 2020 | Q3 | 2020-04-30 | 2020-07-14 | 2020-08-25 |  | Y | BRUNSWICK 110350070 | 2144 |  | PRE |  | 2021-03-01 17:19
35115152 |  | 2021 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  |  | CONS | 8460 | 0 | 8460 | 8460 | 1.6023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6023 | 8271 | 1.5665 | SI | 08W | SH | 2020-09-15 |  |  | 2020-08-25 | 2020-08-31 | 2020-08-25 | 2020-05-29 | 2020-05-29 | Yes | 2020-08-26 | [2020 Const. Sched]08/25: APPROVED - INTO PEND08/20: EST - JO needs to complete DS73 in SAP; emailed request08/18: EST target sub (8/19); ADE/EST working through corrections; JO will need to complete their part to finalize.08/17: BCF submitted for ADE rvw; ADE rtn corrections to CO.08/14: ADE rtn 1st conversion corrections to CO08/12: BCF submitted conversion for ADE rvw08/11 - 08/05: EST target (8/11-12)08/04 - 07/02: Change Order approved [Convert to Wood]06/30 - 06/26: EST target sub (7/10); Design change - requires fielding and application of changes.06/24: PG&E Leadership has agreed to have the request added to our 08W job - three spans are tree wire; ensure the solid blade is replaced with the switch proposed by Emilio06/23: Status - Waiting on Planner for approvals (trgt - 6/26)06/19: ADE rtn 5th corrections to CO - BCF submitted for 6th ADE rvw; ADE - SAP should state "In Process". The planning review task is not completed. EST - deactivated the DS42 Task - reactivated it and placed in process.06/18: BCF submitted for 5th ADE rvw06/17: ADE rtn 4th corrections to CO06/16: BCF submittef for 4th ADE rvw06/16: Est Target sub (6/16)06/13: ADE rtn 3rd corrections to CO06/12: BCF submitted for 3rd ADE rvw06/09: EOD pushed - EST target sub (06/19)06/05: ADE rtn 2nd corrections to CO06/02: ADE soft target (6/05) 05/29: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready]05/26: On Track05/19 - 05/05: Pending clarifications from PGE on standards04/28: Clarifying pole height and framing informations; EST/ADE coordinating; To be reviewed on PGE side.04/14 - 04/07: EST On Track (5/1); EST/ADE working through; corrections and requirements03/30: ADE rtn corrections to CO03/24 - 03/17 ADE Status?? (Due)03/04: BCF submitted for 1st ADE rvw [3]03/03: EST implementing Export program for formatting; Sub this week02/24: ADE 2nd rejection - All information for fld notes guidline not provided & DO-Fld note incomplete02/21: BCF submitted for 1st ADE rvw [2]02/18: EST working on export means to put into requested format; review final w/ [REDACTED] (target this week)02/11: EST to review and firm up target. PGE offline rvw of ADE request and format implementation.02/10: EST - delinked all the erroneous zip files and will reupload to SAP. If the error persists, I will look further into 02/10 |  |  |  | 2020 - Q3- M8 [R2020_137] | COMPLETED | No | Wood | 48 | 0 |  | 2020-08-26 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-04-23 | 2020-04-23 | Full |  |  | Land waiting on finalized drawings. | Full |  |  | Yes | 2020-12-20 |  |  |  | 2020-09-04 | Y | 2020-08-10 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6023 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2020-09-14 | Yes | COMP | 2021-05-10 08:00 | 2021-07-02 17:00 |  | 2021-09-24 17:00 | 2020-08-26 | 2021-05-03 07:00 | 2021-05-03 16:00 |  | 2020-08-31 | Yes | Shovel Ready |  | 2679486.3 |  | 2229051.5 | 3591121 | 911634.7 | 2220694.1 |  | 456410.5 | 2381.7 | 458792.2 |  |  |  | 43 | [7 empty] | Remove |  | Nevada City | Nevada | 0 | 0 | E.5015568.03 |  |  | 2020-137 | 2020 | Q3 | 2020-04-30 | 2020-07-14 | 2020-08-25 |  | Y | BRUNSWICK 110350070 | 2144 |  | PRE |  | 2021-03-08 13:42
35115153 |  | 2021 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Scoped | CONS | 10315 | 0 | 9476 | 9476 | 1.7947 | 0 | 0 | 9476 | 1.7947 | 0 | 0 | 0 | 0 | 0 | 9476 | 1.7947 | SI | 08W | SH | 2020-08-05 |  | Y | 2020-07-02 | 2020-07-31 | 2020-07-02 | 2020-05-01 | 2020-05-01 | Yes | 2020-07-27 | [2020 Const. Sched]07/02: APPROVED - INTO PEND06/30: EST Routed - Ready for ADER approval; DS73 need to be completed to approve.06/29: ADE rtn Pre-final corrections to CO; Form 2 changes - ok to route06/26: BCF submitted for 5th ADE rvw06/23: ADE rtn 4th corrections to COxxxx - 06/16: ADE soft target (6/17) - ADE anticipated Approval by EOM; RISK - based on EST turnaround, may push into 1st wk Jul06/12: BCF submitted for 4th ADE rvw06/09: EST target sub (06/12)06/08: ADE rtn 3rd corrections to CO06/02: ADE rvw push 1wk (6/5) - confirmed05/26: EOD pushed; ADE rvw status (5/27)05/22: BCF submitted for 3rd ADE rvw05/19: EST target sub (5/22)05/14: ADE rtn 2nd Corrections to CO05/05: ADE soft target (5/08)05/01: BCF submitted for 2nd ADE review05/01: ADE reassigned (Ed)04/28 - 04/07: EST to firm up Sub date (5/1)04/02: ADE rtn 1st corrections to CO03/31: Per ADE sub 4/203/24 - 03/17 ADE Status?? (Due)03/04: BCF submitted for 1st ADE rvw [2]03/03: EST implementing Export program for formatting; Sub this week02/25: ADE Rejected 1st submittal - DO fld notes not filled out, will require more pics of site (referal to 08W guidelines)02/21: ADE assigned ( [REDACTED] )2/14: BCF submitted for 1st ADE rvw 02/11 - 01/07: On Track12/17: Anticipate Weather impacts. -Visited sight, Fielding scheduled to start in following weeks12/10: Prioritize for Q3 Const.12/02 |  |  |  | 2020 - Q2- M4 [R137] | COMPLETED | No | Comp | 6 | 54 |  | 2020-07-22 | Yes | [9 empty] | Full | 2020-04-23 | 2020-04-23 | Full |  |  | CIF Submitted 3/9/2020 | Full |  |  | Yes | 2020-12-20 |  |  |  | 2020-08-14 | Y | 2020-07-13 |  |  | Starting 7/1/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7947 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-07-30 | Yes | COMP | 2021-03-16 08:00 | 2021-05-20 08:00 |  | 2021-08-11 17:00 | 2020-07-28 | 2021-03-23 07:00 | 2021-05-07 16:00 |  | 2020-08-05 | Yes | Shovel Ready |  | 3206350.7 | 3497219 | 3080584.2 | 4734585 | 1528234.3 | 2350272.3 | 109.1% | 683040 | 173038.4 | 856078.4 |  | 1948640.3883 |  | 52 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015568.04 |  |  | 2020-137 | 2020 | Q3 | 2020-04-30 | 2020-08-26 | 2020-10-07 |  | Y | BRUNSWICK 110350070 | 7 |  |  |  | 2021-02-25 13:06
35115154 |  | 2021 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Scoped | CONS | 8692 | 0 | 8692 | 8692 | 1.6462 | 0 | 0 | 8692 | 1.6462 | 0 | 0 | 0 | 0 | 0 | 8692 | 1.6462 | SI | 08W | SH | 2020-07-30 |  | Y | 2020-07-03 | 2020-07-31 | 2020-07-03 | 2020-05-08 | 2020-05-08 | Yes | 2020-08-13 | [2020 Const. Sched]07/03: APPROVED - INTO PEND06/30: EST Routed - Ready for ADER approval06/29: ADE working final rvw with EST; EST submitted - error when routing through EES. Task Code DS 20 current status is not INPR. 06/26: BCF submitted for 4th ADE rvw06/25: ADE rtn 3rd corrections to CO06/23: ADE soft target (6/25) - ADE anticipated Approval by EOM; RISK - based on EST turnaround, may push into 1st wk Jul6/22: BCF submitted for 3rd ADE rvw06/17: ADE rtn 2nd corrections to CO06/12: ADE Status ??06/09 - 06/03: ADE rvw target (6/5);(6/12)05/27 - 05/19: ADE - in review05/15: ADE request images for Form 2's; EST provided/uploaded05/12: ADE soft target (5/13)05/08: BCF submitted for 2nd ADE (PRELIM DWG ready)05/05: On Track04/28 - 04/07: EST to firm up Sub date (5/8)04/06: ADE rtn 1st corrections to CO03/31: Per ADE sub 4/703/24 - 03/17 ADE Status?? (Due)03/10: ADE Bandwith RISK - to review reassignment needs to meet EOD03/04: BCF submitted for 1st ADE rvw [2]03/03: EST implementing Export program for formatting; Sub this week03/03: ADE rejected 1st sub - Returning estimate due to DO field notes not filled out, and will require more pictures of sites and poles03/03: ADE assigned (Carlos) [T-45]02/21: BCF submitted for 1st ADE rvw02/18 - 01/07: On Track12/17: Anticipate Weather impacts. -Visited sight, Fielding scheduled to start in following weeks12/10: Prioritize for Q3 Const.12/02: Veg scheduled to be completed 2nd wk Dec11/12 <-- 10/17: Push 2mnth - [REDACTED] He's going to review the locations mid November and provide a timeframe to complete the veg work10/15: Status quo10/08: Veg management issues - need line cleared for Estimating to proceed - Est team to initiate communication with Veg Mgmnt; (initial 4wk push) to address/coordinate resolution 10/01 <-- 9/03: No Change at this time - Based on fielding hardships, reviewing for reprioritization8/21: Condition summary provided by BCF - RISK identified potential need to push & shift another project forward7/30 |  |  |  | 2020 - Q2- M4 [R137] | COMPLETED | No | Wood | 54 | 46 |  | 2020-07-28 | Yes | [9 empty] | Full | 2020-04-23 | 2020-04-23 | Full |  |  | CIF Submitted 3/9/2020 | Full |  |  | Yes |  |  | No permit needed |  | 2020-10-15 | Y | 2020-07-22 |  |  | 95% complete as of 9/8/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6462 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-07-30 | Yes | COMP | 2021-03-05 08:00 | 2021-05-17 08:00 |  | 2021-08-06 17:00 | 2020-08-13 | 2021-03-17 07:00 | 2021-04-17 16:00 |  | 2020-07-22 | Yes |  |  | 2796372.2 | 3434538.4 | 2584854.1 | 3872109 | 1075736.8 | 1575629.6 | 122.8% | 1135504.4 | 85238.2 | 1220742.6 |  | 2086327.9742 |  | 44 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015568.05 |  |  |  | 2020 | Q3 | 2020-04-30 | 2020-08-26 | 2020-10-07 |  | Y | BRUNSWICK 110350070 | 7 |  |  |  | 2021-02-25 13:07
35115155 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  |  | DOCC | 10024 | 0 | 9416 | 9416 | 1.7833 | 9416 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-02-17 |  |  | 2019-11-30 | 2019-11-14 | 2019-11-30 |  |  | Yes | 2019-11-14 | 11/12: Waiting for JO Cost ( [REDACTED] )11/01: Status? Target for EOD last week10/29: Routing by Friday - All OCALCs to be sealed10/25: PIKE submitted for 3rd ADE Rvw - ADE APPROVED10/25: ADE returned 2nd corrections to contractor10/22: PIKE to check on submittal status10/15 <-- 10/10: ADE returned 2nd corrections to contractor; PIKE target early next week for next rvw10/09: PIKE submitted for 2nd ADE Rvw - [PRELIM DWG ready]10/01: Job Rejected - corrections to be made per prior ADE feedback9/19: ADE returned corretions to contractor9/18: ADE assigned ( [REDACTED] ) - Resolved access to documents and updates9/10 - |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes | 2020-04-01 |  | Remaining work is located on private property and doesn't require county/city permit |  | 0 | Y | [11 empty] | 0 | 0 | 9416 | 1.7833 | 0 | 0 | 1.7833 | 0 | 1.7833 | 0 | 1.7833 | 0 | 0 | 1.7833 |  | Keep | 2020-02-17 | Yes | N/A | 2020-01-13 | 2020-02-06 | Yes | 2021-02-25 17:00 | 2019-12-26 | 2020-02-14 | 2020-08-01 | 2021-02-25 |  | Yes | Shovel Ready |  | 3856802.4 | 2842232.5 | -291559.8 | 5231108 | 1374305.6 | 665459 | 73.69% | 3154820.5 | 36522.9 | 3191343.4 |  | 1593775.2336 |  | 51 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.02 |  |  | 2020-136 | 2020 | Q1 | 2019-11-14 | 2020-01-15 | 2020-03-30 |  | Y | BRUNSWICK 110350070 | 7 |  |  |  | 2021-03-01 20:33
35115156 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  |  | DOCC | 11386 | 0 | 10035 | 10035 | 1.9006 | 10035 | 1.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-03-24 |  |  | 2020-01-15 | 2020-06-09 | 2020-01-15 | 2019-11-20 | 2019-11-20 | Yes | 2020-06-09 | 01/14: Finalizing Approval (APPR) 01/07: ADE Status?? 12/30: PIKE submitted for 4th ADE rvw (rerouted for EES) 12/19: ADE submitted further corrections to contractor (OCALCs) 12/17: Planning Eng and ADE disconnect - tie in not being implemented. EST Routed Yesterday. EOD at Risk 12/5: ADE submitted further corrections to contractor (tie in changes/design change) 11/21: Routed per EST 11/19: EST finalizing corrects - ADE directed to route upon completion 11/15: ADE rtn corrections to contractor 11/12: Recv'd Land feedback, pending ADE rvw/input 11/05: New Target? easments for back ties needed from land dept 10/30: Per ADE - 1] JO handles permitting; 2] need to verify with land dept easements for back tie, before we can finalize estimate. Contact Project Manager 10/28: Correction Ready pending ADE response - Est. checking with ADE on who handles permitting (Job Owner) 10/22: Est. tied up on another project for submittal 10/15 <-- 10/08: 2nd rvw submittal - target mid next week (10/18) 10/03: ADE returned 1st corrections to contractor 9/12: ADE assigned (Carlos) 8/27: PIKE submitted for 1st ADE Rvw 8/20: Push 1 wk 8/13: PIKE communicated potential push of 1st ADE submittal into early following week. due to computer technical impacts: (IE: Token malfunctions; SAP Access issues) - working through isssues with TSC on case by case basis - may push submittal into early following week. 7/23 - 8/6: On Track for 8/16 7/19: Vendor Provided 1st ADE Sub dates 7/16: Vendor Request for 1st ADE Submittal 7/15: Sub Order issued [Version 8] |  |  |  | 2020 - Q1 | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 10035 | 1.9006 | 0 | 0 | 1.9006 | 0 | 1.9006 | 0 | 1.9006 | 0 | 0 | 1.9006 |  | Keep | 2020-03-24 | Yes | N/A | 2020-04-01 | 2020-06-03 | Yes | 2020-07-03 | 2020-06-11 | 2020-08-25 | 2020-08-25 | 2020-07-03 |  | Yes | Shovel Ready |  | 4488676.2 | 3029846.7 | -174482 | 1357699.57 | -3130976.63 |  | 67.49% | 3204328.7 |  |  |  | 1594179.4296 |  | 57 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.02 |  |  | 2020-136 | 2020 | Q1 | 2020-01-15 | 2020-05-01 | 2020-06-12 |  | Y | BRUNSWICK 110350070 | 7
35115157 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 |  |  | FICL | 15728 | 0 | 9456 | 9456 | 1.7909 | 9456 | 1.7909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-01-15 |  |  | 2019-11-30 | 2019-11-14 | 2019-11-30 |  |  | Yes | 2019-11-14 | 01/06: CNCS conflicts - had to amend and was resubmitted11/12: Waiting for JO Cost ( [REDACTED] 11/05: Status? Routed?10/29: CMCS approval provided 10/19; Sealing OCALCs - Routing Targeted 10/3010/21: |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes | 2020-05-30 |  | Project complete |  | 1980-01-01 | Y |  |  |  | Started | [7 empty] | 0 | 0 | 9456 | 1.7909 | 0 | 0 | 1.7909 | 0 | 1.7909 | 0 | 1.7909 | 0 | 0 | 1.7909 |  | Keep | 2020-01-15 | Yes | N/A | 2020-02-18 08:00 | 2020-06-03 | Yes | 2020-09-30 | 2020-01-06 | 2020-11-30 | 2020-11-30 | 2020-09-30 |  | Yes | Shovel Ready |  | 4249051.4 | 3499680.9 | -314994 | 1580553.38 | -2668498.02 |  | 82.36% | 3814674.9 |  |  |  | 1954136.5431 |  | 79 | [6 empty] | No SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.04 |  |  | 2020-136 | 2020 | Q1 | 2019-11-14 | 2020-02-17 | 2020-04-15 |  | Y | BRUNSWICK 110350070 | 7
35115158 |  | 2020 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 |  |  | CLSD | 13177 | 0 | 11332 | 11332 | 2.1462 | 11332 | 2.1462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-11-30 |  |  | 2019-11-30 | 2020-05-22 | 2019-11-30 |  |  | Yes | 2020-05-22 | 03/03: EST target EOD today for feedback03/02: 1.5 is already in PEND and EES is locked so I would suggest an update to the CMCS/Construction Drawings eliminating the recloser and updating O'calc for the impacted pole03/02: The updated are being finalized and will be completed by EOD for 1.5 tomorrow. The G&W Viper recloser has been moved to PH 1.1. The changes for 1.5 will be download into SAP after updating O'calc, Map, CMCS with removing the recloser information from all files/saving/ combining and uploading. 11/12: Waiting for JO Cost [REDACTED] 1/05: Status? Routed?10/29: FInal uploads; Sealing OCALCs; to be routed by 11/0110/21: ADE approved for routing10/21: PIKE submitted for 3rd ADE rvw10/21: ADE 2nd corrections rtn to contractor10/21: PIKE submitted for 2nd ADE rvw10/15: PIKE to provide communication to [REDACTED] regarding changes - PGE followup on clarity of how CMCS's are to be conducted.10/08 |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | ERTC Call 1/10/2020 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y |  |  |  | Started | [7 empty] | 0 | 0 | 11332 | 2.1462 | 0 | 0 | 2.1462 | 0 | 2.1462 | 0 | 2.1462 | 0 | -3.4451e-16 | 2.1462 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-03-03 | 2020-03-16 | 2020-06-17 | 2020-07-16 |  | Yes | Shovel Ready |  | 4433946.3 |  | -233648 | 1623614.28 | -2810332.02 |  |  | 3386933 | [5 empty] | 66 | [6 empty] | SCADA |  |  | Nevada City | Nevada | 0 | 0 | E.5015569.05 |  |  | 2020-136 | 2020 | Q1 | 2019-11-14 | 2020-04-01 | 2020-05-29 |  | Y | BRUNSWICK 110350070 | 7
35115404 |  |  |  | STS-COND_IDLE_REMV-5745 GOLD ST |  |  | CLSD |  | 0 | 121 | 121 | 0.022917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0028409 |  |  | SI | 2AF | IF |  |  |  |  | 2019-07-23 | [55 empty] | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0.020076 | 0.0028409 | 0.022917 | 0 | 0.022917 | 0 | -0.0028409 | 0.022917 |  |  |  |  | N/A | [7 empty] | 2020-01-23 | [29 empty] | 39.0237 | -120.8195
35115847 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  |  | ESTS | 9566 | 0 | 9566 | 9566 | 1.8117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8117 | 9916 | 1.878 | ST | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2020-10-31 | 2021-01-31 | 2020-10-21 | 2020-10-21 |  |  | [Composite to Wood - Sept List]11/04: EST target sub (11/13)11/02: EST requesting a change order (APPROVED); Construct-ability Walkdown including prep., travel, note and drawing mark-ups. Scope changes based on Construct-ability Walkdown 67 locations will require drawing changes; 45 requiring O'Calc changes 10/28: EST sub (11/03)10/27: ADE rtn 2nd review to CO10/21: CAL submitted for 2nd ADE rvw10/14: EST target (10/16) waiting on fielding for a few locs to complete corrections10/07 - 09/30: EST target sub (10/16) ??09/24: ADE rtn 1st corrections to CO09/23: ADE in rvw; Priority based09/16: ADE assigned ( [REDACTED] )09/15: CAL submitted for 1st ADE rvw [2]; Conversion Complete09/09: Conversion Target (9/11)09/02: Conversion 1st sub TBD08/26 - 10/16: ADE to be assigned11/20 ADE assignment 1mnth push10/16: CAL submitted for 1st ADE rvw10/16 <--9/25: Target 1st Submittal 11/01 ON TRACK8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2021 - Q1- M1 [R2021_41] | R2.3 - EST Implementing Corrections |  | Wood | 88 | 3 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-04-01 |  | 2021-02-15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8117 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-11 17:00 |  | INPR | 2022-06-28 08:00 | 2022-09-07 17:00 |  | 2022-10-07 17:00 | [9 empty] | 2913142.8 |  | 1 |  |  |  | 101923.1 |  |  |  | 1607923.2682 |  | 48 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.02 - JM | ML |  | 2021-041 | 2021 | 2020 Reserve | 2020-06-30 | 2020-09-13 | 2020-10-24 |  | Y | SALT SPRINGS 21023142 | 8
35115848 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  |  | UNSC | 8697 | 0 | 8697 | 8697 | 1.6472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6472 |  |  | ST | 08W | SH | 2020-10-26 |  |  | 2020-07-08 | 2020-09-30 | 2020-07-08 | 2020-04-22 | 2020-04-22 | Yes | 2020-11-03 | 07/08: APPROVED - INTO PEND07/07: EST routed07/01: EST target sub (07/03)06/23: CAL submitted for 6th ADE rvw; ADE approved for routing06/18: ADE rtn 5th corrections to CO06/17: EST provided updated docs to ADE, due to accessibility issue06/17: ADE Status - EOD Risk06/03: ADE soft target (6/8)06/02: CAL submitted for 5th corrections to ADE06/01: ADE rtn 4th corrections to CO - 3rd corrections incomplete [rejected]06/01: CAL submitted for 4th ADE rvw05/27: EST target sub (6/1)05/23: ADE rtn 3rd corrections to CO05/20: CAL submitted for 3rd ADE rvw05/13: EST target sub (5/19)05/13: ADE rtn 2nd corrections to CO05/13: CAL submitted for 2nd ADE rvw [2] - applied walkdown adjustments04/22: ADE reassigned ( [REDACTED] )04/22: CAL submitted for 2nd ADE rvw [2] - QC04/22: EST On Track04/08: QC Rereview/Resubmit; EST date (4/22)03/31: CAL submitted for 2nd ADE rvw02/10: ADE assigned ( [REDACTED] )12/04 <-- 10/16: ADE to be assigned (waiting on 2020 priority list); 11/20 ADE assignment 1mnth push10/16: CAL sumbitted for 1st ADE rvw10/16 <--9/25: Target 1st Submittal 11/01 ON TRACK8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q2- M6 [R141] | COMPLETED |  | Comp | 29 | 44 |  | 2020-07-17 | Yes |  |  |  | 2020-06-12 | 2020-06-12 |  |  |  |  | Full | 2020-07-17 | 2020-07-17 | Full |  |  | CIF submitted | Full |  | 2020-10-26 | Yes | 2021-09-23 |  | Precon complete |  | 2020-11-14 |  | 2020-09-25 | 2020-09-01 |  | 93% complete as of 11/10/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6472 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-31 17:00 | Yes | INPR | 2022-05-04 08:00 | 2022-07-22 17:00 |  | 2022-09-22 17:00 | 2021-02-27 |  |  |  |  | No |  |  |  | 1517209.2 |  | 1308258.35 |  |  |  | 294023 | 1175651 | 1469674 |  | 921106.6547 |  | 44 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.03 - JM | TL |  | 2021-042 | 2021 | 2020 Reserve | 2020-06-30 | 2020-09-13 | 2020-10-21 |  | Y | SALT SPRINGS 21023142 | 8
35115849 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  |  | PEND | 8204 | 0 | 9186 | 9186 | 1.7398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7398 |  |  | ST | 08W | SH | 2021-01-03 |  |  | 2020-03-24 | 2020-04-24 | 2020-03-24 | 2020-03-04 | 2020-03-04 | Yes | 2020-09-02 | 04/22: Found out of PEND - In ESTS; changes appear to be request by Land03/24: INTO PEND03/23: EST Locations updated/Reviewed for concurrance03/13: pending approval03/11: OK'd to route, EST to route by 3/1303/04: CAL submitted for 2nd rvw02/26: On Track02/19: EST reassigned; ADE sent redline corrections to new EST 02/17: ADE rtn 1st corrections to CO02/10: ADE assigned ( [REDACTED] )12/04 <-- 10/16: ADE to be assigned (waiting on 2020 priority list); 11/20 ADE assignment 1mnth push10/10: CAL submitted for 1st ADE rvw10/09 <--9/25: Target 1st Submittal 11/01 ON TRACK8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q2- M6 [R142] | COMPLETED |  | Comp | 28 | 43 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2021-01-03 |  |  |  | [REDACTED] to schedule precon in 2021 |  | 2020-10-03 | Y | 2020-07-22 | 2020-08-25 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7398 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-16 17:00 | Yes | COMP | 2022-01-17 08:00 | 2022-03-22 17:00 |  | 2022-04-21 17:00 | 2020-07-16 |  |  |  | 2020-09-08 | Yes |  |  | 2922407.2 | 1585624.6 |  | 3838828 | 916420.8 |  | 54.25% | 805243.2 |  |  |  | 911397.5493 |  | 42 | [9 empty] | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.04 - JM |  |  |  | 2020 | Q3 | 2020-06-30 | 2020-10-15 | 2020-11-21 |  | Y | SALT SPRINGS 21023142 | 8
35115850 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  |  | UNSC | 6787 | 0 | 6787 | 6787 | 1.2854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2854 | 6856 | 1.2985 | ST | 08W | SH | 2021-12-07 17:00 |  |  | 2020-08-24 | 2020-10-31 | 2020-08-24 | 2020-03-31 | 2020-03-31 | Yes | 2020-09-08 | 08/24: APPROVE - INTO PEND08/14: Final rvw correction communicated08/12: EST routing today {AUG EOD}08/11: ADE approved for routing08/09: CAL submitted for 4th ADE rvw08/06: ADE rtn 3rd corrections to ADE08/05: ADE advised - starting rvw07/29 - 05/13: ADE rvw - priority based; 7/29 (7/31);6/24 ADE was out for 1wk05/06: CAL submitted for 3rd ADE rvw04/29: EST soft target (5/5) - EST to verify04/22: ADE rtn corrections 2nd corrections to CO04/01: ADE target set at 4/1703/31: CAL submitted for 2nd ADE rvw - ADE plans to start next week03/25: EST firm up sub date (3/28)??03/18: ADE rtn 1st corrections to CO02/12: ADE assigned ( [REDACTED] )12/04 <-- 10/16: ADE to be assigned (waiting on 2020 priority list); 11/20 ADE assignment 1mnth push10/15: CAL submitted for 1st ADE rvw10/09 <-- 9/25: Target 1st Submittal 11/15 ON TRACK9/04: Fielding experiencing additional complications, 1st submittal push8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q3- M8 [R2021_44] | COMPLETED |  | Comp/Wood | 30 | 33 |  |  | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-04 | 2020-09-04 | Full |  |  | Received final drawings week of 8/24 | Full |  | 2020-10-26 | Yes | 2021-09-23 |  | Precon complete |  | 2020-11-17 | Y | 2020-10-23 | 2020-10-01 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2854 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-07 17:00 | Yes | COMP | 2022-04-20 08:00 | 2022-06-30 17:00 |  | 2022-08-31 17:00 | 2020-10-29 | [8 empty] | 2002062.4 |  | 1424587.78 |  |  |  | 203622.9 |  |  |  | 1557520.1815 |  | 34 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.05 - JM | TL |  | 2021-044 | 2021 | 2020 Reserve | 2020-06-30 | 2020-10-15 | 2020-11-17 |  | Y | SALT SPRINGS 21023142 | 8
35115851 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  |  | PEND | 6354 | 0 | 6354 | 6354 | 1.2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2034 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-11-29 | 2020-10-31 | 2020-11-29 | 2020-10-07 | 2020-10-07 |  | 2020-11-16 | [Composite to Wood - Sept List]11/11: CAL submitted for RD ADE rvw;Walkdown changes applied11/05: approved subject job needs to go back to ESTS after receiving construction feedback. [REDACTED] has asked me to create a new version in EES but only option I see is the redesign option11/04: EST rvw sub (11/13); EOD End Nov (11/29)11/02: EST Change Order (APPROVED); Construct-ability Walkdown including prep., travel, note and drawing mark-ups. Scope changes based on Construct-ability Walkdown 35 locations will require drawing changes; 23 requiring O'Calc changes======10/12: APPROVED - INTO PEND10/09: CAL submitted for 3rd ADE rvw; ADE rtn 3rd corrections to CO - route for approval10/08: ADE rtn 2nd corretions to CO10/07: CAL submitted for 2nd ADE rvw09/30: EST target sub (10/16) ??09/24: ADE rtn 1st corrections to CO09/23: ADE in rvw; Priority based09/21: ADE assigned ( [REDACTED] )09/16: CAL submitted for 1st ADE rvw; Conversions09/11: EST Conversion Complete09/09: Conversion Target (9/11)09/02: Conversion 1st sub TBD08/26- 12/12: ADE to be assigned12/04 <-- 11/01: CAL submitted for 1st ADE rvw; 11/20 ADE assignment 1mnth push10/23 |  |  |  | 2020 - RD- M11 [R2021_45] | Iss_RD1.2_Rdsn - ADE Redesign Rvw in Progress |  | Wood | 60 | 0 |  | 2020-10-17 | Yes |  |  |  | 2020-12-04 | 2020-12-04 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF submitted 10/20; No enviro constraints identified. Still in ESTS status. Land Task will be completed upon reaching PEND status |  |  | 2020-12-15 |  |  |  | Requested check on 10/26/20 - Submitted permit on 10/26/20 |  | 2021-04-01 |  | 2021-02-15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2034 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-04 17:00 |  | INPR | 2022-05-24 08:00 | 2022-08-03 17:00 |  | 2022-09-02 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  |  | 2591950.9 |  | 1197165.97 |  |  |  | 102245.1 |  |  |  | 2153840.2191 |  | 32 |  | Not started | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.06- JM | TL |  | 2021-045 | 2021 | 2020 Reserve | 2020-06-30 | 2020-10-15 | 2020-11-16 |  | Y | SALT SPRINGS 21023142 | 8
35115852 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  |  | UNSC | 8454 | 0 | 8454 | 8454 | 1.6011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6011 |  |  | ST | 08W | SH | 2020-10-26 |  |  | 2020-05-28 | 2020-09-30 | 2020-05-28 | 2020-04-10 | 2020-04-10 | Yes | 2020-10-19 | 05/28: APPROVED - INTO PEND05/27: EST Target route (5/27 - 29)05/25: ADE rtn 4th corrections to CO - apply and route05/20: ADE rvw - priority based; soft target (5/25) ??05/18: CAL submitted for 4th ADE rvw05/13: EST target sub (5/18)05/07: ADE advised: job ready for final routing. Asked EST to return corrections by 5-15-20. Job has gone thru the constructability reviews.05/03: ADE rtn 3rd corrections to CO04/30: CAL submitted for 3rd ADE rvw04/29: sub 4/30 - internal review04/22: EST On Track (??)04/14: ADE rtn 2nd corrections to CO04/10: CAL submitted for 2nd ADE rvw04/08: EST sub (4/14)04/01: Push to 4/17 - pending OCALC resolution04/01 - 03/04: Pending Change Order approval; Change OCALC or not02/26: EST confirmed sub date 3/602/24: ADE rtn 1st corrections to CO02/18: ADE assigned ( [REDACTED] )12/04 <-- 11/04: CAL submitted for 1st ADE rvw; 11/20 ADE assignment 1mnth push10/23<-- 9/25: Target 1st Submittal 11/15 ON TRACK9/04: Fielding experiencing additional complications, 1st submittal push8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q2- M6 [R145] | COMPLETED |  | Comp | 23 | 43 |  | 2020-08-21 | Yes |  |  |  | 2020-06-01 | 2020-06-01 |  |  |  |  | Full | 2020-06-01 | 2020-06-01 | Full |  |  |  | Full |  | 2020-10-26 | Yes | 2021-10-13 |  | Precon complete |  | 2020-10-16 | Y | 2020-08-13 | 2020-08-20 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6011 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-22 17:00 | Yes | COMP | 2022-05-03 08:00 | 2022-07-13 17:00 |  | 2022-10-13 17:00 | 2021-02-18 |  |  |  |  | No |  |  |  | 2222791.2 |  | 2621905.68 |  |  |  | 175087.8 |  |  |  | 1388258.5209 |  | 43 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015236.07 - JM | ML |  | 2021-046 | 2021 | 2020 Reserve | 2020-06-30 | 2020-10-15 | 2020-11-22 |  | Y | SALT SPRINGS 21023142 | 8
35115853 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  |  | UNSC | 8473 | 0 | 8473 | 8473 | 1.6047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6047 |  |  | ST | 08W | SH | 2020-11-20 |  |  | 2020-11-20 | 2020-07-31 | 2020-11-20 | 2020-04-17 | 2020-04-17 | Yes | 2020-11-13 | [2020 Const. Sched]11/10: EOD tentatively Push (11/20); ADE/EST to firm up date11/04 CAL submitted for ADE RD rvw11/04 - 10/27: Target RD EOD 11/04; wrapping up, working with JP clerk10/12: According to [REDACTED] , both locations 80 & 83 need to be installed within the street limits ( [REDACTED] is 60’ wide). 09/18: [REDESIGN] customer was complaining about clearing for the line conductors. [REDACTED] has suggested that we relocate Location 80 to the south of Location 73 which would put the pole line tangent at the S/W corner of Natchez Drive and Shoshine Drive.08/25: EST - completed the updating the ocalcs & construction drawing, uploaded everything to SAP, and updated the longtext to reflect the changes=====08/04: Redesign APPROVED - INTO PEND07/29: 7/23 Routed07/22: ADE in rvw07/21: CAL submitted redesign for ADE rvw07/02: Change order to be submitted [Convert to Wood]******07/01: EST routed today (7/01) - |  |  |  | 2020 - RD- M11 [R2020_147] | RD1.2_Rdsn - ADE Redesign Rvw in Progress |  | Wood | 81 | 2 |  | 2020-07-30 | Yes |  |  |  | 2020-08-14 | 2020-08-14 |  |  |  |  | Full | 2020-07-13 | 2020-07-13 | Full |  |  | CIF submitted; have completed preliminary reviews, just need final drawings to complete tasks (7/6/2020) | Full |  | 2020-10-20 | Yes | 2021-10-13 |  | Precon to be scheduled |  | 2020-10-03 | Y | 2020-08-03 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6047 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-30 17:00 | Yes | COMP | 2022-02-02 08:00 | 2022-04-14 17:00 |  | 2022-05-05 17:00 | 2020-11-16 |  |  |  | 2020-08-15 | Yes |  |  | 3459187.5 | 2207882.8 |  | 1924559.32 | -1534628.18 |  | 63.82% | 302237.5 |  |  | -388.013 | 1375855.2088 |  | 43 | [7 empty] | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.02 - JM | ML |  | 2020-147 | 2020 | Q3 | 2020-06-30 | 2020-07-30 | 2020-09-06 |  | Y | SALT SPRINGS 21023142 | 8
35115854 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  |  | CONS | 5916 | 0 | 5916 | 5916 | 1.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1205 | 5762 | 1.0913 | ST | 08W | SH | 2020-10-13 |  |  | 2020-05-15 | 2020-09-30 | 2020-05-15 | 2020-05-05 | 2020-05-05 | Yes | 2020-07-21 | 05/15: APPROVED - INTO PEND 05/14: Routed for approval - Final corrections provided 05/13: ADE rvw set (5/22) 05/12: CAL submitted for 3rd ADE rvw 05/07: ADE rtn 2nd corrections to CO 05/05: CAL submitted for 2nd ADE rvw 04/29 - 04/22: EST on Track 04/15: Push (4/30) - (1.3,.5,.6,.7) Redoing poles into prefered list poles. 04/08: EST firm sub date (4/13); Possible Change Order for PM (composite poles, not of perferred list) 04/03: ADE rtn 1st corrections to CO 03/20: ADE assigned (Joe D.B.) 12/04 <-- 9/25: ADE to be assigned; 10/30 Push 1mth ADE/EOD dates; resourcing; 11/20 ADE assignment 1mnth push 9/18: CAL submitted for 1st ADE rvw 8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q3- M7 [R148] | COMPLETED |  | Comp | 26 | 28 |  | 2020-07-17 | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-10-13 | Yes | 2021-10-13 |  | Precon to be scheduled |  | 2020-10-24 | Y | 2020-08-31 | 2020-08-20 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1205 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-31 08:00 | Yes | COMP | 2022-06-14 08:00 | 2022-08-24 17:00 |  | 2022-09-23 17:00 | 2020-09-04 |  |  |  | 2020-10-10 | Yes |  |  |  | 1164690.5 |  | 868859.26 |  |  |  | 153460.3 | 807420 | 960880.3 |  | 1039480.3651 |  | 30 |  |  | Complete | [6 empty] | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.03 - JM | TL |  | 2021-037 | 2021 | 2020 Reserve | 2020-07-31 | 2020-08-30 | 2020-09-29 |  | Y | SALT SPRINGS 21023142 | 8
35115855 |  | 2020 | 220 Mile Plan | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Scoped | DOCC | 7043 | 0 | 5727 | 5727 | 1.0847 | 5727 | 1.0847 | 0 | 0 | 0 | 0 | 0 | 0 | -0.035417 |  |  | ST | 08W | SH | 2020-06-01 |  | Y | 2020-01-15 | 2020-01-15 | 2020-01-15 | 2019-11-24 | 2019-11-24 | Yes | 2020-03-06 | 01/15: IN PEND01/13 <-- 01/10: EST/ADE coordinating on corrections01/09: ADE rtn 4th corrections to contractor01/09: ADE back from vaca/sick01/08: CAL submitted for 4th ADE rvw01/08: ADE under new Subvisor - not que'd - check EES; May need to EES support/listed in grey in EES - Est cancelled routing to apply addition correction reqs from ADE - REROUTED12/18: CAL - routed today12/13: ADE rtn 3rd corrections to contractor12/11: Routed, waiting for approval - in rvw w/ADE11/29: CAL submitted for 3rd ADE rvw11/26: ADE rtn 2nd corrections to contractor11/18: CAL submitted for 2nd ADE rvw11/14: ADE rtn 1st corrections to contractor11/13 <-- 11/06: ADE finalizing other rvw; returning to complete - ADE Bandwith10/23: Push to finalize rvw - 10/22: Reuploaded to SAP10/16: Check in with ADE10/09 <-- 10/08: ADE recv'd all information - in review10/05: ADE missing field notes in SAPADE assigned to [REDACTED] 9/30: CAL submitted for 1st ADE rvw9/25: Target 1st submittal pulled into 9/278/21: 5 Fielders assigned and started, Estimators started |  |  |  | P 2021R-49 Q4 | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted on 12/5 | Full |  |  | Yes |  |  | Submitted on 12/23 |  | 2020-07-10 | Y | 2020-06-01 |  |  | Starting 5/18/20 | [7 empty] | 0 | 0 | 5914 | 1.1201 | 0 | 0 | 1.1201 | -0.035417 | 1.0847 | 0 | 1.308 | 0.2233 | 0.035417 | 1.0847 |  | Keep | 2020-05-19 17:00 | Yes | N/A | 2020-07-27 08:00 | 2020-10-26 17:00 | Yes | 2021-04-26 17:00 | 2020-04-13 | 2020-07-27 | 2020-09-26 | 2020-10-01 |  | Yes | Shovel Ready |  | 1974014.7 |  | -231006.4 | 2958923 | 984908.3 | 393743.7 |  | 1580271 | 0 | 1580271 | -256.636 |  |  | 72 |  | Started - In progress - Crews pulled for fire. | [7 empty] | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.04 - JM |  |  | 2020-149 | 2020 | Q3 | 2020-01-15 | 2020-06-15 | 2020-07-19 |  | Y | SALT SPRINGS 21023142 | 8 |  |  |  | 2021-03-11 09:04
35115856 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  |  | UNSC | 10943 | 0 | 10943 | 10943 | 2.0725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0725 | 10616 | 2.0106 | ST | 08W | SH | 2020-11-06 |  |  | 2020-07-07 | 2020-09-30 | 2020-07-07 | 2020-06-19 | 2020-06-19 | Yes | 2020-12-29 | 07/07: APPROVED - INTO PEND07/02: Final corrections communicated to ADE07/01: EST target sub (07/01)06/29: CAL submitted for 3rd ADE rvw; ADE rtn 3rd corrections to CO - apply and route06/24: EST target sub (6/26)06/22: ADE rtn 2nd correction to CO - apply and route06/19: CAL submitted for 2nd ADE rvw - {PRELIM DWG ready]06/17 - 06/10: EST target (6/17); Hold cleared; resolving overlap and finalizing06/03: EST - overlap issue; on hold; to be reviewed for sched impact.05/27:Push ??; Fielding and changes requiring more time05/20: Additional flding required; Target sub (5/25)05/13: EST target sub (5/15)05/07: ADE rtn 1st corrections to CO04/28: ADE assigned ( [REDACTED] )04/19: CAL submitted for 1st ADE rvw04/08: QC Rereview/Resubmit; Applied Composite/Wood changes; sub date 4/1712/04 <-- 9/25: Target 1st submittal 11/01 ON TRACK; 10/30 Push 1mth ADE/EOD dates; resourcing; 11/20 ADE assignment 1mnth push9/04: Fielding experiencing additional complications, 1st submittal push8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q3- M8 [R150] | COMPLETED |  | Comp | 48 | 52 |  | 2020-07-22 | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-10-26 | Yes | 2021-09-23 |  | Precon complete |  | 2020-11-21 |  | 2020-10-06 | 2020-09-01 |  | On hold pending work plan change - 81% complete as of 12/1/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0725 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-29 17:00 | Yes | COMP | 2022-04-26 08:00 | 2022-07-06 17:00 |  | 2022-10-06 17:00 | 2021-02-04 |  |  |  | 2020-11-06 | Yes |  |  |  | 2076131.3 |  | 2167732.82 |  |  |  | 318812.6 |  |  |  | 1001733.8266 |  | 55 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.05 - JM | TL |  | 2021-038 | 2021 | 2020 Reserve | 2020-08-31 | 2020-09-30 | 2020-11-14 |  | Y | SALT SPRINGS 21023142 | 8
35115857 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  |  | PEND | 6445 | 0 | 6445 | 6445 | 1.2206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2206 | 6445 | 1.2206 | ST | 08W | SH | 2022-02-18 17:00 |  |  | 2020-09-30 | 2020-08-31 | 2020-09-30 | 2020-06-12 | 2020-06-12 | Yes | 2020-07-15 | 06/24: ADE soft target (7/2) - priority based06/19: CAL submitted for 2nd ADE rvw06/18: ADE rtn 2nd corrections to CO; PRE-Final corrections rtn to CO06/17: ADE rvw - priority based06/12: CAL submitted for 2nd ADE rvw - [PRELIM DWG ready]06/10: EST target sub (6/15)06/04: ADE rtn 1st corrections to CO06/03: EST working pole conflicts05/26: ADE - Conflict pole list distributed; Fwd'd to key persons via Brian.05/21: ADE flagged pole conflicts; putting together a spread sheet on the Locations that are in conflict with the 08W "35115857" job and the 95A "31497467" Job; need WIP Cloud.05/20 - 05/13: ADE in rvw - priority based05/07: ADE assigned ( [REDACTED] )05/06: CAL submitted for 1st ADE rvw [2] Wood Conversion04/29: Push (5/08)04/08: QC Rereview/Resubmit; Applied Composite/Wood changes; sub date 4/1712/04 <-- 10/16: ADE to be assigned (waiting on 2020 priority list); 10/30 Push 1mth ADE/EOD dates; resourcing; 11/20 ADE assignment 1mnth push10/09: CAL submitted for 1st ADE rvw9/25: Target 1st submittal 11/01 ON TRACK9/04 |  |  |  | 2020 - Q3- M8 [R151] | R3.2 - ADE Review in Progress |  | Comp/Wood | 36 | 31 |  |  | Yes |  |  |  | 2020-07-07 | 2020-07-07 |  |  |  |  | Full | 2020-08-18 | 2020-08-18 | Full |  |  | CIF submitted with Final Drawings | Full |  | 2020-11-15 |  |  |  | Requested check on 10/17 |  | 2020-12-21 |  | 2020-11-16 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2206 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-18 17:00 |  | INPR | 2022-04-26 08:00 | 2022-07-06 17:00 |  | 2022-08-05 17:00 | [9 empty] | 2658581.5 |  | 1602218.96 |  |  |  | 62439.7 |  |  |  | 2178015.5656 |  | 33 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.06 - JM | TL |  | 2021-039 | 2021 |  | 2020-08-31 | 2021-09-25 |  |  | Y | SALT SPRINGS 21023142 | 8
35115858 |  |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  |  | UNSC | 6507 | 0 | 6883 | 6883 | 1.3036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3036 | 6883 | 1.3036 | ST | 08W | SH | 2020-11-06 |  |  | 2020-07-03 | 2020-09-30 | 2020-07-03 | 2020-06-15 | 2020-06-15 | Yes | 2020-11-04 | 07/03: CAL submitted final corrections and rerouted07/02: ADER Pre-Final corrections communicted to ADE; Pre-Final corrections provided to CO07/01: EST target sub (07/01) - routing06/29: CAL submitted for 4th ADE rvw; ADE rtn 4th corrections to CO - apply and route6/25: ADE rtn 3rd corrections to CO06/24: CAL submitted for 3rd ADE rvw06/17: EST sub (6/24)06/16 ADE rtn 2nd corrections to CO06/15 CAL submitted for 2nd ADE rvw - [PRELIM DWG ready]06/10: On Track; hold cleared06/03 - 05/27: ADE est hold; overlap issue on another PM needing to be resolved, then corrections will continue05/20: EST target sub (5/29)05/17: ADE rtn 1st correctionst to CO05/13: ADE assigned ( [REDACTED] ) - ADE advised, will review this week05/06 - 04/29: ADE to be assigned04/27: CAL submitted for 1st ADE rvw04/08: QC Rereview/Resubmit; Applied Composite/Wood changes; sub date 4/1712/04 <-- 11/02: CAL submitted for 1st ADE rvw10/30 <-- 9/25: Target 1st submittal 11/01 ON TRACK; 10/30 Push 1mth ADE/EOD dates; resourcing9/04: Fielding experiencing additional complications, 1st submittal push8/21: 5 Fielders assigned and started, Estimators started |  |  |  | 2020 - Q3- M8 [R152] | COMPLETED |  | Comp | 12 | 27 |  | 2020-07-21 | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-10-13 | Yes | 2021-09-23 |  | Precon complete |  | 2020-11-28 |  | 2020-10-06 | 2020-09-02 |  | On hold pending work plan change - 85% complete as of 11/10/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3036 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-14 17:00 | Yes | COMP | 2022-05-03 08:00 | 2022-05-31 08:00 |  | 2022-07-29 17:00 | 2021-01-19 |  |  |  | 2020-11-06 | Yes |  |  |  | 1166929.5 |  | 1190982.71 |  |  |  | 202324.4 |  |  |  | 895160.215 |  | 33 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 38.3019 | -120.277 | E.5015235.07 - JM | TL |  | 2021-040 | 2021 | 2020 Reserve | 2020-08-31 | 2020-09-30 | 2020-11-01 |  | Y | SALT SPRINGS 21023142 | 8
35116383 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Scoped | CONS | 7319 | 0 | 7319 | 7319 | 1.3862 | 0 | 0 | 7319 | 1.3862 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-10-15 |  | Y | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-10-01 | 2019-10-01 | Yes | 2019-10-16 | IN PEND10/11: ADE approved for routing10/10: EEI submitted for 2nd ADE rvw [PRELIM DWG ready]10/10: ADE rtn 1st corrections to contractor10/10: ADE assigned ( [REDACTED] )10/07: EEI submitted for 1st ADE Rvw10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-10-15 | 2020-10-15 |  |  |  |  | Full | 2019-12-16 | 2019-12-16 | Full |  |  | PERTC received - Caltrans expected on 3/27 - Dist. 10 | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-07-10 | Y | 2020-06-23 | 2020-06-23 |  | [REDACTED] update/PI 100% - Waiting on BC |  | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3862 | 0 | 0 | 1.3919 | 1.3919 | 0 | 0 |  | Keep | 2020-06-30 | Yes | COMP | 2021-03-08 08:00 | 2021-05-12 17:00 |  | 2021-06-30 17:00 | 2020-03-18 | 2021-03-15 07:00 | 2021-04-09 16:00 |  | 2020-07-08 | Yes | Shovel Ready |  | 2547021 | 1431046 | 722523.9 | 3758449 | 1211428 | 969655.3 | 56.18% | 1084512.1 | 492853.6 | 1577365.7 |  | 1032370.9359 |  | 59 | [9 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5014733.02 - JM | MX |  | 2020-017 | 2020 | Q3 | 2019-10-16 | 2020-04-26 | 2020-06-15 |  | Y | MIWUK 17018060 | 2267 |  | PRE |  | 2021-03-03 12:30
35116384 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Scoped | CONS | 9715 | 0 | 9700 | 9700 | 1.8371 | 0 | 0 | 9700 | 1.8371 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-09-10 |  | Y | 2020-05-08 | 2020-05-31 | 2020-05-08 | 2020-04-24 | 2020-04-24 | Yes | 2020-07-23 | 05/08: APPROVED - INTO PEND05/07: ADE rtn for final corrections to CO - EEI applied final corrections for approval05/05: EEI submitted for 4th ADE rvw05/01: ADE rtn 2nd corrections to CO04/29: ADE target sub (??) - 04/24: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]04/22 - 04/15: EST Status (??) - EEI to follow up with update; applying corrections04/08: EEI target date (4/13)04/02: ADE rtn 1st corrections to CO04/01: per ADE rvw should be done by 4/203/25 - 3/11: ADE status (DUE) ??03/09: EEI submitted for 1st ADE Rvw [2]03/04: EST working on 35116385 - will move to next02/26 - 02/19: Resub target 02/21; EST/ADE coordination; completing some refielding; Push to 2/28 to complete02/12: EST to follow up with return date01/18: ADE Rejected 1st submittal - excessive error, unable to proceed01/15: ADE assigned ( [REDACTED] )01/07: EEI submitted for 1st ADE rvw12/18: ADE resourcing push; Push 1st Sub EST Initial issues with EES11/20: Push to 12/6: EES issues - duplicating and deleting information - EEI to advise on submittal impact; Composite Pole change impact11/06: Push - PSPS impact10/29 <-- 10/16: On track 1st sub for 11/610/09: Push - 2wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 10/23 |  |  |  | 2020 - Q2- M4 [R18] | COMPLETED |  | Comp | 23 | 56 |  |  | Yes |  |  |  | 2020-07-21 | 2020-07-21 |  |  |  |  | Full | 2020-07-21 | 2020-07-21 | Full |  |  | 7/21/2020 - Easement no longer required as of 7/13/20- Enviro reviews to be done by 7/21 | Full |  | 2020-06-26 | Yes | 2021-06-22 |  | No construction drawings as of yet? |  | 2021-03-02 | Y | 2020-09-10 | 2020-08-04 |  | 95% complete as of 12/1/20 - 1 crane tree remains |  | Contract | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8371 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-07-27 17:00 | Yes | COMP | 2021-03-29 08:00 | 2021-05-19 17:00 |  | 2021-05-20 08:00 | 2020-07-28 |  |  |  | 2020-07-23 | Yes |  |  | 3239379.6 | 1058624.7 | 1875779.4 | 4624169 | 1384789.4 | 2231032 | 32.67% | 127817.1 | 880530.5 | 1008347.6 |  | 576241.0738 |  | 49 | [9 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5014733.03 - JM | TL |  | 2020-018 | 2020 | Q3 | 2020-04-30 | 2020-08-13 | 2020-10-09 |  | Y | MIWUK 17018060 | 2267 |  | PRE |  | 2021-03-09 08:32
35116385 |  |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  |  | PEND | 8005 | 0 | 8005 | 8005 | 1.5161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5161 |  |  | YO | 08W | SH | 2022-03-08 17:00 |  |  | 2020-05-27 | 2021-09-30 | 2020-05-27 | 2020-01-13 | 2020-01-13 | Yes | 2020-05-27 | 05/27: ADE rtn 5th corrections to CO; approved for routing; EEI routed; Final rvw rtn to CO; EEI submitted for final rvw; APPROVED - INTO PEND05/20: ADE soft target (5/23) - per ADE Target next week for approval (based on EST sched) - EOD timeframe at risk 05/18: EEI submitted for 5ht ADE rvw05/13: EST target sub (5/18)05/12: ADE rtn 4th corrections to CO04/29: ADE status update (focusing on completion)04/15 - 04/08: Working higher priority PM; ADE target rvw completion next week Monday, will work with EST. to route by EOW next week04/02: EEI submitted for 4th ADE rvw - ADE scheduled to start rvw next week03/31: Push (4/2); Issue with EES - was locked on ADE - now waiting on some OCalc stamps03/25: EST firmed up sub date03/23: ADE rtn 3rd corrections to CO03/11: ADE - Started 3rd review this Monday, target COB next Monday03/05 EEI submitted for 3rd ADE rvw (ADE to start Mon)03/04: EST/ADE coordination - Estimator working on 35116385 - will finish soon after02/26: On Track02/19: EST 3rd sub target 2/28; EST workload balance02/18: ADE rtn 2nd corrections to CO01/13: EEI submitted for 2nd ADE rvw - [Prelim DWG ready]01/08: EST - corrections in progress/ Est bandwith; finished EST on alternate 08W12/18: Push 2nd Sub; Est Priority shifts12/11 <-- 11/27: Push 1wk - added rvw time Composite/workload11/20: Push Composite change impact11/13: EEI to advise on status and 2nd submittal date11/03: ADE returned corrections to contractor10/30: ADE started rvw10/29 <-- 10/23: with ADE for rvw10/16: ADE assigned ( [REDACTED] )10/15: EEI submited for 1st ADE review10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) |  |  |  | 2020 - Q1- M3 [R19] | COMPLETED |  | Comp | 10 | 44 |  |  | Yes |  |  |  | 2021-06-30 | 2021-06-30 | [5 empty] | 2020-10-30 | 2020-10-30 | Partial |  |  | ** Caltrans DSDD - Pilot Project - District 10 delay push to 7/7/20. 6/4/2020 - waiting on caltrans, have received USFS approval. Released a PERTC for veg to start work. | Partial |  |  | Yes | 2021-01-09 |  |  |  | 2021-07-16 |  | 2021-07-05 | 2020-08-19 |  | Walkdown 8/5. MH to request PERTC due to CT permit | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5161 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-08 17:00 |  | INPR | 2022-07-04 08:00 | 2022-09-14 17:00 |  | 2022-09-21 17:00 | [5 empty] | No |  |  | 2814642 | 1608475.6 |  | 3489624 | 674982 |  | 57.14% | 78311.9 |  |  |  | 1060930.8142 |  | 41 |  | Composite pole issue | [5 empty] | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014733.04 - JM | TL |  | 2020-019 | 2022 | Q3 | 2020-03-31 | 2020-07-14 | 2020-09-04 |  | Y | MIWUK 17018060 | 12
35116388 |  |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  |  | PEND | 11220 | 0 | 13109 | 13109 | 2.4828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4828 |  |  | YO | 08W | SH | 2020-11-09 |  |  | 2020-11-09 | 2020-05-31 | 2020-11-09 | 2020-04-10 | 2020-04-10 | Yes | 2020-11-10 | 11/04: On Track10/27: Status (ESTS) - EOD 11/09; Redesign - Back tie/UG (ties in with -6598)=====05/06: APPROVED - IN PEND05/06: EST submitted final corrections - going through final approval05/01: ADE approved for routing - EST routed - Final approval corrections rtn to CO04/30: EEI submitted for 4th ADE rvw04/29: ADE rtn 3rd corrections to CO04/28: EEI submitted for 3rd ADE rvw; ADE will push to make final approval EOW04/23: ADE rtn 2nd corrections to CO04/15: ADE to firm up sub04/10: EEI submitted for 2nd ADE rvw04/08: On Track04/01: EST working higher priority job ( [REDACTED] ); extended sub date (4/20)03/30: ADE rtn 1st corrections to CO03/25: ADE going through JP Intent |  |  |  | 2020 - RD- M11 [R2020_20] | RD1.3_Rdsn - EST Implementing Redesign Corrections |  | Comp | 55 | 68 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-11-02 |  | 2020-08-10 |  |  | 90% Complete as of 10/6/20. - Waiting on redesign for backtie | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4828 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-28 08:00 | Yes | COMP | 2022-01-04 08:00 | 2022-03-09 17:00 |  | 2022-03-23 17:00 | 2020-08-26 |  |  |  | 2020-08-06 | Yes |  |  | 4435361.8 | 2645960.1 |  | 1767022.83 | -2668338.97 |  | 59.65% | 448195.6 |  |  |  | 1065731.1258 |  | 57 | [7 empty] | Remove | [5 empty] | E.5014733.05 - JM | TL |  | 2020-020 | 2020 | Q3 | 2020-03-31 | 2020-05-30 | 2020-07-30 |  | Y | MIWUK 17018060 | 12
35116389 |  |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  |  | ESTS | 9970 | 0 | 9970 | 9970 | 1.8883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8883 | 9970 | 1.8883 | YO | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-10-31 | 2020-11-30 | 2020-07-14 | 2020-07-14 | Yes |  | [Composite to Wood - Sept List]11/04 - 10/7: Submittal by 10/9; 10/30 - redesign OH tie to UG tie w/ 35116388 EOD PUSH; 11/0909/30: EST sub (10/09); Construction rvw request more changes09/23: EST push sub target (10/2); Jobwalk and apply changes09/09: Conversion sub (9/16)09/02: EST converting to wood; Conversion sub (09/08)08/26: EST sub date (8/28)08/21: ADE request review and explain the justification, for large number of services being replaced.08/20: ADE rtn 3rd corrections to CO08/19 - 08/12: ADE in rvw; priority based08/10: EEI submitted for 3rd ADErvw08/05: EST target sub (8/17)07/29: EST target sub (8/3)07/22: ADE rtn 2nd corrections to CO07/15: ADE advised, will complete asap07/14: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]07/08: EST push (7/10)07/01: EST push (7/3); Priority work06/24 - 06/10: On Track; (6/29)06/03: EST push (6/26)05/27: EST push (6/19)05/20: EST target sub (6/12)05/14: ADE rtn 2nd corrections to CO05/13: ADE rvw - Push - priority based05/06 - 04/22: ADE soft target 5/0804/17: ADE assigned ( [REDACTED] )04/16: EEI submitted for 1st ADE rvw04/15: Finishing OCalck stamping04/08 - 02/26: On Track02/19: Est priority alignment shift02/12 |  |  |  | 2020 - Q4- M11 [R2021_78] | R3.3 - EST Implementing Corrections |  | Wood | 42 | 72 | [13 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Caltrans encroachment permit needed for Location 3. Partial ERTC requested. Received veg scope needed for land reviews and cultural constraints. Enviro reviews in progress. | [6 empty] | No construction drawings as of yet? | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8883 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-05 17:00 |  | INPR | 2022-06-22 08:00 | 2022-08-19 17:00 |  | 2022-09-20 17:00 | [8 empty] | 500000 | 1772450.4 |  | 500000 | 0 |  | 354.5% | 83600.1 |  |  |  | 938669.8207 |  | 50 |  |  | Complete |  |  |  |  | Remove |  | Twain Harte | Tuolumne | 0 | 0 | E.5014733.06 - JM | TL |  | 2021-078 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-13 | 2020-11-10 |  | Y | MIWUK 17018060 | 12
35116390 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  |  | DOCC | 5100 | 0 | 4771 | 4771 | 0.9036 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-09-01 |  |  | 2020-01-15 | 2020-01-10 | 2020-01-15 | 2019-12-23 | 2019-12-23 | Yes | 2020-01-10 | 01/08: Routed today12/30: add all updated docs & stamping, ADE approved for routing12/23: EEI submitted for 2nd rvw - [PRELIM DWG ready]12/18: Est set target 2nd sub 12/2012/13: ADE rtn 1st corrections to contractor12/11 - 11/27: ADE priority/workload11/20: Composite Pole change (2 pols/ 1hr)11/19: ADE assigned ( [REDACTED] )11/18: EEI submitted for 1st ADE rvw11/06: Waiting to field - Veg clearing and PSPS impact10/29: PSPS impact to fielding10/23: In accessible locations - working through fielding on 2 locations - Push 1wk10/16: On track 1st sub for 10/14 (EOW)10/09: Push - 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02: EEI 1st submittal target update to 10/079/04: EEI to supply new target dates (push) |  |  |  | Priority Q2 | COMPLETED | No | Wood | 29 | 2 |  |  | Yes |  |  |  | 2020-04-09 | 2020-04-09 |  |  |  |  | Full | 2020-09-01 | 2020-09-01 | Full |  |  | Full ERTC issued 9/1 ** Caltrans Dist. 10 delay to 9/11/20. | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-09-04 | Y | 2020-08-11 | 2020-08-11 |  | Veg complete, Pending post inspect. | [7 empty] | 0 | 0 | 4771 | 0.9036 | 0 | 0 | 0.9036 | 0 | 0.9036 | 0 | 0.95606 | 0.052462 | 0 | 0.9036 |  | Keep | 2020-07-09 | Yes | COMP | 2020-10-05 08:00 | 2020-10-12 17:00 | Yes | 2020-10-12 17:00 | 2020-07-31 | 2020-09-30 | 2020-11-16 | 2021-01-29 | 2020-08-03 | Yes | Shovel Ready |  | 1195542 |  | 41387.5 | 1195542 | 0 |  |  | 719080 | [5 empty] | 26 |  | ADE Bandwidth | [7 empty] | Twain Harte | Tuolumne | 0 | 0 | E.5014733.07 - JM | TL |  | 2020-022 | 2020 | Q3 | 2020-01-10 | 2020-04-24 | 2020-06-07 |  | Y | MIWUK 17018060 | 12
35116391 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Scoped | DOCC | 10840 | 0 | 10932 | 10932 | 2.0705 | 7308 | 1.3841 | 3624 | 0.68636 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-04-07 |  | Y | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2019-12-27 | 2019-12-27 | Yes | 2020-02-25 | 02/25: IN PEND 02/19: QUES submitted for 4th ADE rvw 02/18: ADE rtn 3rd corrections to CO 02/11: QUES submitted for 3rd ADE rvw 02/05: Push - EST PSPS support 01/28: EST/ADE coordinating on some corrections 01/27: ADE rtn corrections to CO 01/08: ADE Status? 12/28: QUES submitted for 2nd ADE rvw 12/18 <-- 12/11 Push - Computer Crash/1 week down time - Workload Balance/Priorities 12/04: On Track 2nd sub 11/29: ADE rtn 1st corrections to contractor 11/27 <-- 11/20: ADE status check? On Track? 11/13 ADE assigned (Brad) 11/08: QUES submitted for 1st ADE rvw 11/06: Target EOD (11/06) - completing stamping; applying final fixes (Transmission Lines - elevation/ avoiding UG) 10/30: In Stamping - Target EOW 10/23: Push 1 wk- Needs to go through JP 10/16: Push- Resource availability (Stamping 1 PE) 10/02: Push to next Friday - Est on conversion updates for priority projects 9/25: On Track 1st ADE submittal 9/30 Potential Pole Composite Standard Impact - Can remain wood; Some already converted - confirming with ADE whether to convert back or remain as is |  |  |  | 2020 - Q1- M2 [R45] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-07 | 2020-04-07 | Full |  |  | Revised ERTC date is 4/7/2020 - Submitted to USFS on 3/23/20 | Full |  |  | Yes |  |  | [REDACTED] sent plans to [REDACTED] on 1/9 |  | 2020-04-21 | Y | [11 empty] | 0 | 0 | 7308 | 1.3841 | 3432 | 0.65 | 2.0341 | 0.036364 | 2.0348 | 0 | 2.0902 | 0.055303 | -0.00075758 | 1.3841 |  | Keep | 2020-03-31 | Yes | N/A | 2020-06-22 | 2021-02-04 | Yes | 2021-01-15 | 2020-04-24 | 2021-01-11 | 2021-01-15 | 2021-02-04 |  | Yes | Shovel Ready |  | 7840406.2 | 1812739.9 | 378038 | 3920203 | -3920203.2 | 5949510.8 | 23.12% | 1810394.6 | 80500.8 | 1890895.4 |  | 875527.5038 |  | 62 | [9 empty] | Twain Harte | Tuolumne | 38.0494 | -120.261 | E.5014773.02 - JM |  |  | 2020-045 | 2020 | Q2 | 2020-02-29 | 2020-03-30 | 2020-05-13 |  | Y | MIWUK 1702CB | 2369 |  | PRE
35116393 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.3 |  |  | CLSD | 13485 | 0 | 13572 | 13572 | 2.5705 | 13572 | 2.5705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2019-10-31 |  |  | 2019-10-31 | 2019-11-21 | 2019-10-31 |  |  | Yes | 2019-11-21 | 01/09: QUES submitted Temp pole information01/03: PM back into redesign - minimize number of shutdowns to customers. New temp pole add and a back-tie.11/15: ADE in approval of redesign11/14: Land redesign; waiting for stamping10/07: IN PEND10/03: QUES submitted for 2nd ADE rvw - APPROVED for routing by ADE10/02: ADE 1st rvw corrections rtn to contractor9/30 ADE assigned ( [REDACTED] )9/27: QUES submitted for 1st ADE rvw9/25: On Track 1st ADE submittal 9/30Potential Pole Composite Standard Impact - Can remain wood; Some already converted - confirming with ADE whether to convert back or remain as is |  |  |  | Priority B | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | [REDACTED] to follow up with [REDACTED] |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 13572 | 2.5705 | 0 | 0 | 2.5705 | 0 | 2.5705 | 0 | 2.5705 | 0 | 0 | 2.5705 |  | Keep |  | Yes | N/A |  |  |  |  | 2019-12-10 | 2020-03-03 | 2020-03-13 | 2020-03-20 |  | Yes | Shovel Ready |  | 4302368 |  |  | 4302367 | -1 |  |  | 4301719 | [5 empty] | 94 |  | Veg Started | [7 empty] | Twain Harte | Tuolumne | 38.0498 | -120.2241 | E.5014773.03 - JM |  |  | 2020-046 | 2020 | Q1 | 2019-10-04 | 2020-01-25 | 2020-03-25 |  | Y | MIWUK 1702CB | 25
35116394 |  | 2020 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.4 |  |  | CLSD | 8790 | 0 | 8858 | 8858 | 1.6777 | 8858 | 1.6777 | 0 | 0 | 0 | 0 | 0 | 0 | -4.8231e-15 |  |  | YO | 08W | SH | 2020-02-19 |  |  | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2019-11-26 | 2019-11-26 | Yes | 2020-02-19 | 02/19: IN PEND02/19: Per [REDACTED] - to be notified of final resolution confirmation, expecting shortly - ready to approve02/05: QUES submitted for 4th ADE for review (new design)1/23: P [REDACTED] (EES TEAM) needs to hold until [REDACTED] gives us the all clear the 252 Planning Orders RCC 15932 being changed to the correct RCC's.1/22: Land approved new design |  |  |  | 2020 - Q2- M4 [R47] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 9/29 | Full |  |  | Yes |  |  | Submitted on 12/26 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 8858 | 1.6777 | 0 | 0 | 1.6777 | -4.8231e-15 | 1.6777 | 0 | 1.6777 | 0 | 4.8231e-15 | 1.6777 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-02-28 | 2020-04-02 | 2020-05-01 | 2020-06-23 |  | Yes | Shovel Ready |  | 1990074.8 |  |  | 2102204 | 112129.2 |  |  | 1826412.3 | [5 empty] | 44 |  | Veg Started | [7 empty] | Twain Harte | Tuolumne | 38.0531 | -120.237 | E.5014773.04 - JM |  |  | 2020-047 | 2020 | Q2 | 2020-04-30 | 2020-04-30 | 2020-06-07 |  | Y | MIWUK 1702CB | 25
35116395 |  | 2021 | 220 Mile Plan | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Scoped | CONS | 7500 | 0 | 9032 | 9032 | 1.7106 | 0 | 0 | 9032 | 1.7106 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-22 |  | Y | 2020-05-22 | 2020-05-31 | 2020-05-22 | 2020-01-24 | 2020-01-24 | Yes | 2020-07-08 | 05/22: APPROVED - INTO PEND05/21: ADE approved for routing05/20: ADE in rvw05/19: QUES submitted for 7th ADE rvw05/14: QUES submitted for 6th ADE rvw; ADE rtn 6th corrections to CO05/13: EST target sub (05/14)05/08: ADE rtn 5th corrections to CO05/06: QUES submitted for 5th ADE rvw05/06: ADE response provided; On track04/29: Ties into mainline with another job - need clarification from ADEs to proceed - differing design requests. Push (5/8)04/23: EOD shift May - progress04/22: EST sub target (4/24)04/21: ADE rtn 4th corrections to CO04/16: QUES submitted for 4th ADE rvw04/15: EST On Track04/08: EST ready - waiting on response from Transmission; need to assess content to firm up sub date.04/01: In for JP revisions to date; Target sub (4/03)03/25: EST firm up sub (3/25)??03/20: ADE rtn 3rd corrections to CO03/05: QUES submmited for 3rd ADE rvw03/04: EST working through stamp corrections - Push to 3/602/26: EST - On Track02/19: EST waiting on OE for Planner driven change/request information02/12: EST Target date 2/21; Stamping (delay/aty bklg)02/03: ADE rtn 2nd corrections to CO01/24: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]01/22: Finalizing Stamping; Estimator change (LOA)01/08: Push Pole 07D/ clarifying how to move forward with work (Job Owner) otherwise waiting on stamps. (Stamping working through backlog and renewing old stamps[700] (4.5wks wrk)- 3rd PE in training))12/18: EST in progress12/05: ADE rtn 1st corrections to contractor12/02: ADE assigned ( [REDACTED] ) - 1st rvw set (2wk) 12/2011/27: 1st rvw push 1mth11/20: ADE to be assigned11/13: QUES submitted for 1st ADE Rvw11/12: Design collaboration with ADE/EST ([***] constructability 35052820)11/06: Target EOW (11/08) - completing Stamping and final fixes10/30: In Stamping - Target EOW10/23: Push 1 wk - Started internal Rvw 10/2310/16 |  |  |  | 2020 - Q2- M4 [R48] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-10 | 2020-04-10 | Full |  |  |  | Full |  |  | Yes |  |  | RP56 cleared 3/31 |  | 2021-03-10 |  | 2020-07-22 |  |  | 98% complete as of 12/1/20. Need line cover. GC has no resources to support | [7 empty] | 0 | 0 | 0 | 0 | 2677 | 0.50701 | 0.50701 | 1.2036 | 0.50701 | 0 | 1.7068 | 1.1998 | 0 | 0 |  | Keep | 2020-07-16 | Yes | COMP | 2021-01-11 08:00 | 2021-03-30 17:00 |  | 2021-03-31 08:00 | 2020-07-08 | 2021-02-16 07:00 | 2021-04-30 16:00 |  |  | Yes |  |  | 2479934.2 | 979612 | 134201.4 | 3714853 | 1234918.8 | 1552964 | 39.5% | 833414.2 | 93556 | 926970.2 |  | 572669.5483 |  | 64 | [9 empty] | Twain Harte | Tuolumne | 38.0596 | -120.2138 | E.5014773.05 - JM |  |  | 2020-048 | 2020 | Q3 | 2020-04-30 | 2020-07-14 | 2020-08-18 |  | Y | MIWUK 1702CB | 2369 |  | PRE |  | 2021-03-10 21:39
35116396 |  |  |  | CWSP-MIWUK 1702-LR8090-PH 1.2 |  |  | CONS | 9510 | 0 | 11216 | 11216 | 2.1242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1242 |  |  | YO | 08W | SH | 2020-12-14 |  |  | 2020-05-30 | 2020-09-30 | 2020-05-30 | 2020-05-05 | 2020-05-05 | Yes | 2020-07-15 | 05/30: APPROVED - INTO PEND05/29: Final review corrections to CO05/28: ADE rtn 3rd corrections to CO - minor corrections and route05/27: ADE in rvw05/26: EEI submitted for 3rd ADe rvw5/20: EST target sub (6/5)05/14: ADE rtn 2nd corrections to CO05/13: ADE rvw - Push - priority based05/06: ADE soft target (05/11)05/05: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]04/29: On Track04/22 - 04/15: Restart - Under further rvw (1st sub 5/29)04/08: Est sub date; DWG needs to be redone - EST to firm up 1st sub date03/25- 01/29: Computer Issue - working to recover files (2wk per TSC)01/08: Est Target 1/13; Push to 1/31 - Driver?01/06: ADE rtn 1st corrections to contractor12/18: ADE status - due next week?12/05: ADE assigned ( [REDACTED] )11/27: ADE to be assigned11/25: EEI submitted for 1st ADE rvw11/13: On Track11/06: Push - PSPS impact10/29 <-- 10/16: On Track 1st sub 11/0610/09:Target dates shifted (resources finishing El Dorado & Volta) 2 wk10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 10/01 |  |  |  | 2020 - Q2- M5 [R177] | COMPLETED |  | Wood | 96 | 18 |  |  | Yes |  |  |  | 2020-07-02 | 2020-07-02 |  |  |  |  | Full | 2020-07-06 | 2020-07-06 | Full |  |  | CIF Submitted | Full |  | 2020-06-19 | Yes |  |  |  |  | 2020-12-11 |  | 2020-11-12 | 2020-09-04 |  | 50% complete as of 12/1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1242 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-14 17:00 | Yes | COMP | 2022-03-22 08:00 | 2022-09-22 17:00 |  | 2022-09-22 17:00 | 2020-09-17 |  |  |  | 2020-12-14 | No |  |  | 4331424.5 | 3600079.6 |  | 6123271 | 1791846.5 |  | 83.11% | 569801.7 |  |  |  | 1694759.2981 |  | 48 | [9 empty] | Twain Harte | Tuolumne | 38.0408 | -120.2291 | E.5014722.02 - JM | ML |  | 2020-177 | 2021 | Reserve | 2020-05-31 | 2020-08-29 | 2020-10-09 |  | Y | MIWUK 17028090 | 102
35116397 |  |  |  | CWSP-MIWUK 1702-LR8090-PH 1.3 |  |  | PEND | 10855 | 0 | 10614 | 10614 | 2.0102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0102 |  |  | YO | 08W | SH | 2020-12-14 |  |  | 2020-06-15 | 2020-09-30 | 2020-06-15 | 2020-05-05 | 2020-05-05 | Yes | 2020-08-14 | 06/15: APPROVED - INTO PEND06/08: Pre - Final corrections - quick rvw provided to ADE06/04: Planner needs to complete task DS7306/03: EST applied corrections and routed06/03: ADE rtn 4th corrections to CO - correct and submit06/02: EEI submitted for 4th ADE rvw05/26: ADE rtn 3rd correctionst to CO05/26: ADE advised EST - will need feedback from Transmission before job can be finished.05/20: EEI submitted for 3rd ADE rvw05/13: EST target sub (5/18)05/12: ADE rtn 2nd corrections to CO05/06: ADE soft target (05/11)05/05: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]04/29: On Track04/22: Push (05/01); priority PMs being worked.04/15: EST target 4/2404/14: ADE rtn 1st corrections to CO06/03: ADE soft target (6/8)03/26: ADE assigned ( [REDACTED] )03/25 - 01/08: ADE to be assigned01/03: EEI submitted12/18: ADE resourcing push; EST Internal review11/27 <-- 11/13: On Track 12/1311/06: Push - PSPS impact10/29 <-- 10/16: On Track 1st sub 11/2810/09 |  |  |  | 2020 - Q3- M7 [R160] | COMPLETED |  | Comp | 15 | 51 |  |  | Yes |  |  |  | 2020-07-30 | 2020-07-30 |  |  |  |  | Full | 2020-08-06 | 2020-08-06 | Full |  |  | CIF Submitted 6/22 | Full |  | 2020-07-31 | Yes |  |  | [REDACTED] to send plans on 6/23 |  | 2020-12-04 |  | 2020-10-13 | 2020-10-02 |  | 94% complete as of 12/1/20 - Line covers needed | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0102 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-21 | Yes | INPR | 2022-03-08 08:00 | 2022-05-31 17:00 |  | 2022-06-01 17:00 | 2020-08-13 |  |  |  | 2020-12-14 | No |  |  | 3639681.8 | 2524641.9 |  | 5174348 | 1534666.2 |  | 69.36% | 64831.8 |  |  |  | 1255898.7405 |  | 55 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0386 | -120.2471 | E.5014722.03 - JM | MX |  | 2020-160 | 2021 | Reserve | 2020-07-31 | 2020-10-29 | 2020-12-12 |  | Y | MIWUK 17028090 | 102
35116398 |  |  |  | CWSP-MIWUK 1702-LR8090-PH 1.4 |  |  | ESTS | 9730 | 0 | 9730 | 9730 | 1.8428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8428 |  |  | YO | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-10-31 | 2020-11-30 | 2020-06-02 | 2020-06-02 | Yes |  | [Composite to Wood - Sept List]11/04 - 10/7: ADE follow-up, issue with the proposed back-tie09/30: ADE in rvw; priority based09/29: EEI submitted for 4th ADE rvw09/23: EST push sub target (9/30)09/22: ADE rtn comments to CO09/21: EEI submitted for 3rd ADE rvw [2]; Conversions09/17: Conversion Complete09/02: EST converting to wood; Conversion sub (9/11)08/26: EST sub date (8/28)08/21: ADE rtn 3rd corrections to CO08/19: ADE in rvw; priority based - status ?? [AUG EOD]08/14: EEI submitted for 3rd ADE rvw08/12 - 08/05: EST push (08/10), (8/14);High QTY locs; working higher priority07/29: On Track07/22: EST target sub (7/31); High QYT locs -Higher priority work07/15: EST Target sub (7/24)07/08 - 07/01: On Track06/24: EST target sub (7/17)06/17: On Track06/10: EST target sub (6/23); lower priority06/09: ADE rtn 2nd corrections to CO06/03: ADE soft Target (6/8)06/02: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]05/27: ETS push 1.5 wk (6/1) - 173 locations - additional questions sent to ADE05/20 - 05/06: EST target sub (05/20) 2 dau push- getting OCalcs stamped05/04: ADE rtn 1st corrections to CO04/29 - 04/01: ADE processing rvw03/30: ADE assigned ( [REDACTED] )03/25 - 01/15: ADE to be assigned01/10 |  |  |  | 2020 - Q4- M11 [R2022(+)_178] | R4.3 - EST Implementing Corrections |  | Wood | 165 | 9 |  | 2021-01-15 | [11 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF submitted 10/21 | [6 empty] | DWG provided to PC on 10/26. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8428 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-02-21 17:00 |  | INPR | 2023-03-30 08:00 | 2023-06-15 17:00 |  | 2023-07-13 17:00 | [8 empty] | 83333 | 4348502.6 |  | 83333 | 0 |  | 5218% | 47043 |  |  |  | 2359721.8631 |  | 49 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0411 | -120.2349 | E.5014722.04 - JM | MX |  | 2020-178 | 2021 | Reserve | 2020-07-31 | 2020-10-29 | 2020-12-09 |  | Y | MIWUK 17028090 | 102
35116399 |  |  |  | CWSP-MIWUK 1702-LR8090-PH 1.5 |  |  | UNSC | 9185 | 0 | 9687 | 9687 | 1.8347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8347 |  |  | YO | 08W | SH | 2022-02-23 17:00 |  |  | 2020-08-21 | 2020-10-31 | 2020-08-21 | 2020-04-28 | 2020-04-28 | Yes | 2020-08-21 | 08/21: ADE - final correction provided; APPROVED - INTO PEND08/19: ADE concur returned - Planning Eng to complete DS7308/18: EEI routed08/17: ADE rtn 6th corrections to CO; EEI submitted for 7th ADE rvw; ADE approved for routing - apply minor corrections08/12: EST (8/21) - Waiting for SCADA; EEI submitted for 6th ADE rvw - SCADA completed08/01: ADE rtn 5th corrections; do not rtn w/o SCADA07/31: EST submitted for 5th ADE rvw07/29: ADE rtn 4th corrections to CO07/28: EEI submitted for 4th ADE rvw07/22: On Track07/15: EST soft target (7/31)07/09: ADE rtn 3rd corrections to CO07/08: ADE in rvw07/07: EEI submitted for 3rd ADE rvw07/01: EST target sub (7/3); per PMgr, will submite w/ place holder amounts and update later06/24: On Track06/17- 05/20: Push sub (5/18),(6/1), (6/8); Awaiting responses from project manager and TLine05/06: EST target sub (05/08)05/01: ADE rtn 2nd corrections to CO04/29: ADE soft target 5/304/28: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]04/22: Sub push (4/27) - Corrections required more time to complete04/15 - 04/08: EEI confirm sub date (4/21)04/07: ADE rtn 1st correctins to CO03/30: ADE assigned ( [REDACTED] )03/25 - 01/15: ADE to be assigned01/10: EEI submitted for 1st ADE rvw01/08: EST On Track12/18: ADE resourcing push; EST More locations than originally expected11/27: Push 2wk to 12/06: Holiday impact/ Larger Scope - 11/20 <-- 11/13: On Track 11/2211/06: Push - PSPS/ Fielding & additional poles impact10/29 <-- 10/16: On Track 1st sub 11/0610/09:Target dates shifted (resources finishing El Dorado & Volta) 2wk10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 10/01 |  |  |  | 2020 - Q3- M8 [R2022(+)_179] | COMPLETED |  | Comp | 36 | 58 |  |  | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-07 | 2020-09-07 | Full |  |  | Received final drawings | Full |  | 2020-09-30 | Yes |  |  |  |  | 2020-11-19 | Y | 2020-11-03 | 2020-10-19 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8347 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-23 17:00 |  | INPR | 2022-06-10 08:00 | 2022-09-14 17:00 |  | 2022-10-26 17:00 | 2020-09-01 | [7 empty] | 300000 | 4547347 |  | 300000 | 0 |  | 1516% | 206092.6 |  |  |  | 2478578.7303 |  | 46 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0262 | -120.2523 | E.5014722.05 - JM | MX |  | 2020-179 | 2021 | Reserve | 2020-07-31 | 2020-10-29 | 2020-12-08 |  | Y | MIWUK 17028090 | 102
35116440 |  |  |  | CWSP-MIWUK 1702-LR8090-PH 1.6 |  |  | ESTS | 9980 | 0 | 9980 | 9980 | 1.8902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8902 |  |  | YO | 08W | SH | 2023-02-02 17:00 |  |  | 2020-11-30 | 2020-10-31 | 2020-11-30 | 2020-10-13 | 2020-10-13 | Yes |  | 11/05: ADE rtn 2nd rvw to CO11/04: Per [REDACTED] - target sub 11/511/04 - 10/19: ADE advised corrections surfacing in review likely to put EOD at RISK and other commitments, upcoming vacation - target sub (10/24)10/13 EEI submitted for 2nd ADE rvw10/14 - 10/7: Submittal by 10/12, 10/14 waiting on Project Manager for costs09/30 - 08/26: EST target sub (9/4); (09/08); (09/11); (9/25); (10/5)08/19: EST target sub (8/28); ADE req more pics08/12 - 08/05: On Track; Photos and meter info missing07/29 - 07/15: Est Target sub (7/20); (7/27); (8/10)07/08: On Track07/01: Est target sub (7/10); Priority Work06/24: EST target sub (7/6); Big Basin focus06/17: Est target 08/12: EST target sub (8/21); ADE requesting additional pics6/22; Higher priority work required06/10: On Track06/03: EST push 1wk (6/15)05/27: On Track05/20: EST target sub (6/5) - Priority PMs ahead of this one05/14: ADE rtn 1st corrections to CO08/05: On Track05/13 - 04/15: ADE Status - review started (??)03/25 - 03/11: Holding 1st rvw soft target - ADE priorities suggest min 3-4 wks (Apr-03;10) before this project based on workload rvw. Update at a later date.01/08: ADE Bandwith - priority work on El Dorado12/18: Confirmed uploaded12/12: ADE check in on wet stamp status - Est to upload by EOD12/10: ADE reassigned ( [REDACTED] ) - review to proceed when wet stamped12/05: ADE assigned ( [REDACTED] )11/27: Push ; ADE Resourcing11/26: EEI submitted for 1st ADE Rvw11/20 <-- 11/13: On Track 11/2211/06: Push PSPS impact10/29 <-- 10/16: On Track 1st sub 11/0610/09:Target dates shifted (resources finishing El Dorado & Volta) 2wk10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 10/01 |  |  |  | 2020 - Q4- M11 [R2022(+)_180] | R2.2 - ADE Review in Progress |  | Wood | 62 | 0 |  | 2021-01-15 | [16 empty] | ** Caltrans DSDD_ CIF submitted 10/21. Redesign: DSDD at Location 68 - [REDACTED] | [6 empty] | DWG provided to PC on 10/26. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8902 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-02-02 17:00 |  | INPR | 2023-05-16 08:00 | 2023-07-24 17:00 |  | 2023-08-23 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  | 275000 | 3643512.1 |  | 275000 | 0 |  | 1325% | 74400.2 |  |  |  | 1927629.6481 |  | 50 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0246 | -120.2446 | E.5014722.06 - JM | ML |  | 2020-180 | 2021 | Reserve | 2020-05-31 | 2020-08-29 | 2020-10-10 |  | Y | MIWUK 17028090 | 102
35116441 |  |  |  | CWSP-MIWUK 1702-LR 38218-PH1.2 |  |  | ESTS | 12015 | 0 | 12015 | 12015 | 2.2756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2756 |  |  | YO | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2020-10-31 | 2021-02-28 | 2020-04-24 | 2020-04-24 | Yes |  | [Composite to Wood - Sept List]11/04 - 10/14: Easement: drawn up w/ upper mngmnt for rvw [Pushing to Jan/Feb]10/07: Waiting on easement, possible Nov or Dec timeframe09/23: Conversion 1st sub (TBD): Waiting on Land Response (Land 2-3 month +1wk to apply)09/16 - 09/02: Conversion 1st sub (9/30)09/01: Conversion to start mid next week; completing Miwuk corrections (higher priority); Also, securing easements (30-60 day)08/26 - 08/05: EST target sub (10/30); EST design change (Customer) - Tree in path not to be removed; modifying easement; pole shifting 10'07/29: On Track08/12 - 07/22: EST target sub (8/7); waiting on land rvw for route change07/17: Estimator change07/15: RISK - EST to check on recent updates and scheduling07/08: Est target sub (7/10); Job Walk changes - Pole move, Customer driven (Tree in path); UG impact - refielding needed, may have easement impacts; Estimator reassignment07/01: ADE rtn 3rd corrections to CO06/29: ADE targeting EOW (7/3)06/24: ADE soft target (7/2) JUL EOD - priority based; RISK - Est goes on leave Aug. ADE confirmed Jun EOD unlikely (201 locations under rvw)06/18: QUES submitted for 3rd ADE rvw06/17: EST On Track06/10: EST Target date (6/19) - Refields needed; ADE asked to replace secondaries that weren't originally fielded.06/03: Pre Construction walk completed; EST sent questions to OE - based on response, may require additional fielding.05/20: (Estimator reassignment); EST halfway through corrections/ADE Q&A; stamping to follow - QTY of corrections/worked some alternate priority needs; Target sub (5/29)05/13: EST target sub (5/22); working refields extending duration05/12: Ade rtn 2nd corrections to CO05/06: ADE in rvw04/23: QUES submitted for 2nd ADE rvw04/22: Need update on 2nd PM for split04/15: Wire conversion; finishing rvw/stamping04/08: High volume of Tree Attachments + Poles; seeking to split PM to second PM; Concerns with FAA system processing issues03/25: EST push sub date from (3/29); Scope change confusion/ revision and stamping, sub date (4/10)03/19: ADE rtn 1st corrections to CO - spot checked OCalc for this job from location 44-189; Frame 4KV neutral; apply what commented on so far, resubmit.03/16: ADE assigned ( [REDACTED] )03/04: NEED ADE Assignment 03-02 to meet EOD (45d)01/17: QUES submitted for 1st ADE rvw01/15: Est finishing up changes and internal rvw12/18: Additional fielding surface more tree services - finishing design12/11: Fielding surfacing additional service poles, push 1wk to apply design adjustments12/04 - 11/20: Check on status of new PM; 12/04 - Resent request11/13: Proposed change communicated via email - pending review/issuance ( [REDACTED] Pole quantities exceed FAA - need split11/06 |  |  |  | 2021 - Q1- M2 [R2022(+)_52] | Iss_R3.3 - EST Implementing Corrections |  | Comp | 41 | 62 |  | 2021-01-15 | [11 empty] | 2023-12-25 | 2023-12-25 |  |  |  | [REDACTED] to submit CIF | [6 empty] | Submitted dwg on 7/2 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2756 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-24 17:00 |  | INPR | 2022-01-18 08:00 | 2022-03-18 08:00 |  | 2022-07-21 17:00 | [8 empty] | 250000 | 6331116.9 |  | 250000 | 0 |  | 2532% | 50606.3 |  |  |  | 2782213.6689 |  | 61 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0486 | -120.2438 | E.5014776.02 - JM | MX |  | 2020-052 | 2021 | Reserve | 2020-04-30 | 2020-07-14 | 2020-08-31 |  | Y | MIWUK 170238218 | 32
35116442 |  | 2021 | 220 Mile Plan | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Scoped | DOCC | 11065 | 0 | 11065 | 11065 | 2.0956 | 9451 | 1.79 | 1614 | 0.30568 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-13 |  | Y | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-01-17 | 2020-01-17 | Yes | 2020-04-01 | 02/27: INTO PEND02/06: Handling change like PSPS - Per ADE; One final thing - Can you edit the Job Story on the estimate to include "Replace Oil Filled Recloser 94249 with new G&W Viper Recloser".Then please route for approvals02/26-02/25: Approval delayed - Converting an MSO to a G&W Viper (2wks to complete site survey...)02/19: FInalizing minor corrections for final approval (target this week)02/14: QUES submitted for 5th ADE rvw02/13: ADE rtn 4th corrections to CO02/11: QUES submitted for 4th ADE rvw02/05: ADE rtn 3rd corrections to CO; close to ready for approval01/31: QUES submitted for 3rd ADE rvw01/29: Waiting on ADE response; if poles not replaced RISK 3kw push01/28 <-- 1/23: EST/ADE coordinating on corrections01/22: ADE rtn 2nd corrections to CO01/09: ADE shed to start rvw in next couple days01/09: QUES submitted for 2nd ADE rvw01/08: EES issue - unable to calc totals; ticket submitted12/18 <-- 12/11 : 12/04: ADE rtn 1st corrections to contractor11/27 <-- 11/20: Check with ADE; Status check with ADE.11/07: ADE assigned ( [REDACTED] )10/30: QUES submitted for 1st ADE rvw10/30 |  |  |  | 2020 - Q1- M2 [R53] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-02-12 | 2020-02-12 |  |  |  |  | Full | 2020-02-12 | 2020-02-12 | Full |  |  | CIF Submitted on 1/22 | Full |  |  | Yes | 2021-03-27 |  |  |  | 2020-07-29 | Y | 2020-07-13 | 2020-07-13 | [7 empty] | 9451 | 1.79 | 0 | 0 | 9451 | 1.79 | 2640 | 0.5 | 2.29 | -0.19432 | 2.2936 | 0 | 2.3491 | 0.055492 | -0.0035985 | 1.7888 |  | Keep | 2020-06-05 | Yes | COMP | 2020-07-15 | 2020-12-15 17:00 | Yes | 2021-01-18 | 2020-06-24 | 2020-11-30 | 2021-01-16 | 2021-02-04 |  | Yes | Shovel Ready |  | 2994830.4 | 2023627 | 203909.1 | 3849738 | 854907.6 | 986874.9 | 67.57% | 1922700.5 | 85255 | 2007955.5 |  | 965634.9354 |  | 56 | [9 empty] | Twain Harte | Tuolumne | 38.0486 | -120.2438 | E.5014776.03 - JM | MX |  | 2020-053 | 2020 | Q3 | 2020-02-29 | 2020-05-13 | 2020-07-13 |  | Y | MIWUK 170238218 | 2678 |  | PRE
35116443 |  |  |  | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  |  | CONS | 9935 | 0 | 10249 | 10249 | 1.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9411 |  |  | YO | 08W | SH | 2020-08-03 |  |  | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-03-31 | 2020-03-31 | Yes | 2020-07-20 | 04/16: INTO PEND04/15: QUES submitted for 3rd ADE Rvw- waiting on costs; EST routed for approval - Final corrections rtn to CO04/14: EST requesting follow up on GC costs; design about ready to submit (date TBD)4/08: EST firm up sub date (4/10) - dependant on GC costs04/05: Prelim provided to [REDACTED] to review final costs (part of corrections req)04/02: ADE rtn 2nd corrections to CO03/31: QUES submitted for 2nd ADE rvw03/25 - 03/11: Push OCALC Versions - Partial resolution - [REDACTED] to get further clarity and work w/ EST upload calc change issue w/ [REDACTED] 3/04: Push (2wk)03/04 |  |  |  | 2020 - Q1- M3 [R54] | COMPLETED |  | Comp | 7 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-09-23 | Y | 2020-08-03 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9411 | 0 | 0 | 1.9134 | 1.9134 | 0 | 0 |  | Remove | 2020-07-20 17:00 | Yes | COMP | 2020-09-01 08:00 | 2022-04-07 08:00 |  | 2022-05-06 17:00 | 2020-08-10 |  |  |  | 2020-07-30 | Yes | Shovel Ready |  | 3345785.2 | 1003489.3 |  | 4826121 | 1480335.8 | 2420796.8 | 29.99% | 799988.4 | 125000 | 924988.4 |  | 516969.8023 |  | 50 |  | Received prelim drawing on 12/30. Request confirmation on GPS for 18 locations. | [7 empty] | Twain Harte | Tuolumne | 38.0486 | -120.2438 | E.5014776.04 - JM | TL |  | 2020-054 | 2020 | Q3 | 2020-03-31 | 2020-05-01 | 2020-06-28 |  | Y | MIWUK 170238218 | 32
35116444 |  | 2021 | 220 Mile Plan | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Scoped | CONS | 9600 | 0 | 11100 | 11100 | 2.1023 | 0 | 0 | 11100 | 2.1023 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-28 |  | Y | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-02-25 | 2020-02-25 | Yes | 2020-06-26 | 04/07: INTO PEND04/05: ADE provided final approval corrections04/02: Uploads needed03/27: QUES submitted for 4th ADE rvw03/26: New Target Date?? Working through changes/approach03/24: ADE complete 3rd corrections 03/20: Push, EST -Trying to reach [REDACTED] d in regards to project to address any GC items. EST computer died.03/12: Routed - [REDACTED] completed today 03/09: ADE rtn 2nd corretions to CO03/04: ADE advise 2nd rvw target early next week (ADE/EST coordination of corrections)02/25: QUES submitted for 2nd ADE rvw02/19 - 01/29: EST status-submittal target; In que for resolution; [2/19] Sending for followup; EST Emailed request for resolution01/21: EST Ready to submit - waiting for EES to finish saving (running in background for weeks); Ticket submitted 01/15: Finishing Stamping01/08: EST - Completing stamping (Stamping working through backlog and renewing old stamps[700] (4.5wks wrk)- 3rd PE in training))12-18 |  |  |  | 2020 - Q1- M2 [R55] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Veg scope requested | Full |  |  | Yes | 2021-01-09 |  |  |  | 2020-06-19 | Y | 2020-05-20 |  |  | PI 100%/TT 40% | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1023 | 0 | 0 | 2.065 | 2.065 | 0 | 0 |  | Keep | 2020-05-05 17:00 | Yes | COMP | 2020-08-04 08:00 | 2021-05-26 08:00 |  | 2021-06-24 17:00 | 2020-06-26 | 2021-04-19 07:00 | 2021-05-28 16:00 |  | 2020-07-28 | Yes | Shovel Ready |  | 2648177.2 | 1209870.8 | 603963.1 | 3531134 | 882956.8 | 1698653.7 | 45.68% | 801667.5 | 147856 | 949523.5 |  | 575506.1103 |  | 48 | [9 empty] | Twain Harte | Tuolumne | 38.0486 | -120.2438 | E.5014776.05 - JM | TL |  | 2020-055 | 2020 | Q3 | 2020-02-29 | 2020-03-15 | 2020-06-10 |  | Y | MIWUK 170238218 | 2678 |  | PRE
35116511 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 2.2 |  |  | UNSC | 6934 | 0 | 6348 | 6348 | 1.2023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2023 |  |  | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-08-04 | 2020-07-31 | 2020-08-04 | 2020-06-19 | 2020-06-19 | Yes | 2020-08-04 | 08/04: APPROVED - INTO PEND08/04: PIKE submitted for 4th ADE rvw; applied adjustment to corrections per ADE (only items); ADE approved for routing08/03: ADE rtn 3rd corrections to CO07/31: PIke submitted for 3rd ADE rvw07/27: On Track07/21 - 07/14: EST target sub (7/29)07/13: ADE rtn 2nd corrections to CO07/07 - 6/23: ADE in rvw - complete another PM06/19: PIKE submitted for 2nd ADE rvw06/16: EST target sub (6/19); Estimator out-of-office, hand off06/09: On Track06/04: EST target sub (6/11); EST rcv'd walkdown information; seeking ADE input and applying changes06/02: EST updating Form 2; Target sub (6/5)05/26: EST target sub (5/29); Estimator change; information hand-off, completing est.05/19 : On Track05/05: EST target sub (05/22)05/01: ADE rtn 1st corrections to CO04/28 - 04/07: ADE status; corrections update (4/24) (??)03/31: ADE to start early next week03/17: ADE assigned ( [REDACTED] ); ADE rvw target (4/6)??12/13: PIKnE submitted for 1st ADE rvw12:10 Flagged for submittal 12/11 - status?12/04: O-Calc update was pushed on Wednesday - generating pole failures. Due to update, some poles required upgrades (O-Calc, DWGs, EES and JPA)11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact)11/12 <-- 10/22: On Track (12/01)10/15 |  |  |  | 2020 - Q3- M8 [R2021_30] | COMPLETED |  | Comp | 0 | 40 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-08-24 | 2020-08-24 | Full |  |  | CIF Submitted 6/17/20 | Full |  | 2020-11-10 | Yes | 2021-11-04 |  | Approved Permit email received 11/5, PreCon held 11/4, Ready for Precon as of 10/27 |  | 2021-01-09 |  | 2020-12-01 | 2020-10-21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2023 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-04-12 08:00 | 2022-06-22 17:00 |  | 2022-08-23 17:00 | 2020-11-09 | [7 empty] | 125000 | 1646084.1 |  | 1026224.53 | 901224.53 |  | 1317% | 88302.7 |  |  |  | 1369143.6749 |  | 63 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015394.02 - JM | TL | OH | 2021-030 | 2021 |  | 2020-07-31 | 2020-11-13 |  |  | Y | STANISLAUS 17021888 | 4
35116512 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 2.3 |  |  | PEND | 9387 | 2381 | 6855 | 9236 | 1.7492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7492 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-07-23 | 2020-06-30 | 2020-07-23 | 2020-06-17 | 2020-06-17 | Yes | 2020-07-23 | 07/23: APPROVED - INTO PEND07/21: EST routed 7/2007/14: EST finalizing cost items; target EOW routing07/07: ADE rtn 3rd corrections to CO - approved for routing; EST appling remaining corrections.07/02: PIKE submitted for 3rd ADE rvw07/01: EST target sub (7/10) - TBD06/30: ADE rtn 2nd corrections to CO06/23: ADE target sub (??)06/17: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready]06/16: On Track06/09: Target sub (6/19);UG to OH; approach finalized; implementing changes.06/02: In progress05/26 - 05/19: Push 3 wk, coordinate/apply; rvwing route with PM/landowner-cust... scheduling meeting for fielding.05/12: Finalizing job walk changes; push to mid week - potential for reroute request. UG to OH possibility.05/05: EST target sub (05/15); Pending no major changes04/28: Push - Job walk occurring today (4/28); EST to apply corrections04/21: On Track04/14: EST firm up sub date (5/1)04/08: ADE rtn 1st corrections to CO04/07: Working priority PMs - push03/31; per ADE done by this weekend3/25: ADE 1st rvw target (4/10)3/16 ADE assigned ( [REDACTED] )12/16: PIKE submitted for 1st ADE rvw11/19 |  |  |  | 2020 - Q3- M8 [R2021_31] | COMPLETED |  | Comp | 7 | 41 |  | 2020-09-21 | Yes |  |  |  | 2020-11-25 | 2020-11-25 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Updated drawings received 6/25/2020; easement is required due 11/25/20. Environmental reviews completed. PERTC is not needed. Small redesign needed to work around easement as of 10/27/20. 11/3/20 2 of 4 easements received. |  |  | 2020-11-10 |  | 2021-11-04 |  | Approved Permit email received 11/5, Ready for Precon as of 10/27 |  | 2021-03-06 |  | 2021-02-01 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7492 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-07-06 08:00 | 2022-09-22 17:00 |  | 2022-11-23 17:00 | [8 empty] | 125000 | 3035333.8 |  | 1578304.87 | 1453304.87 |  | 2428% | 104654.7 |  |  |  | 1735227.6379 |  | 50 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015394.03 - JM | TL | MX | 2021-031 | 2021 |  | 2020-07-31 | 2021-02-26 |  |  | Y | STANISLAUS 17021888 | 4
35116513 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 2.4 |  |  | PEND | 11249 | 0 | 11249 | 11249 | 2.1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1305 | 8690 | 1.6458 | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-10-01 | 2020-08-31 | 2020-10-01 | 2020-07-31 | 2020-07-31 | yes | 2020-10-01 | [Composite to Wood - Sept List]10/01: APPROVED - INTO PEND09/29: Pike submitted for 4th ADE rvw09/21: ADE advised, corrections in progress, started 9/2409/17: ADE rtn 3rd corrections to CO; minor changes and route for approval09/15: ADE in rvw; Priority based09/09: PIKE submitted for 3rd ADE rvw; Conversion Complete09/08: Conversion sub 9/1109/01: OCT EOD; target sub TBD - Conversion Comp to Wood08/25: ADE target sub (8/28) 08/19: PIKE submitted for 3rd ADE rvw08/18:ADE rtn 2nd corrections to CO08/11 - 08/04: ADE in rvw; priority based (8/7); (8/14)07/31: PIKE submitted 2nd ADE rvw - [PRELIM DWG ready]07/27: On Track07/21 - 07/15: EST/ADE coordinating on corrections07/14: EST target sub (7/31)07/13: ADE rtn 1st corrections to CO07/07 - 06/23: Construction questioning 3PH length - Scope change - Change Order(?); change would be an extensive LOE; Looping [REDACTED] in, to review drivers 06/23 - 06/02: ADE Rvw - priority based05/26: PIKE provided Stamped Ocalc for 1st rvw05/19: ADE Rvw - priority based04/28 - 04/08: ADE to firm up date (4/20) (??)04/01: ADE assigned (Ed)12/10: PIKE submitted for 1st ADE rvw12:10 Flagged for submittal 12/9 - status?12/04: O-Calc update was pushed on Wednesday - generating pole failures. Due to update, some poles required upgrades (O-Calc, DWGs, EES and JPA)11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact)11/12 <--10/29: Completing Fielding - PSPS Impacts10/22: Swap 1st Submittal with 2.3 (12/01)10/15: PIKE pulled in ADE 1st Submittal Target (2wk) 9/24 |  |  |  | 2020 - Q4- M10 [R2021_32] | COMPLETED |  | Wood | 57 | 0 |  |  | Yes |  |  |  | 2020-10-15 | 2020-10-15 |  |  |  |  | Full | 2020-10-15 | 2020-10-15 | Full |  |  | CIF Submitted 7/11/20; Prelim reviews completed as of 8/27. Final Drawings received 10/2 | Full |  | 2020-12-01 |  |  |  | Submitted permit request 10/7/2020 - TCP requested 10/16 |  | 2021-03-13 |  | 2021-02-08 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1305 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-08-10 08:00 | 2022-10-20 17:00 |  | 2022-12-21 17:00 | [5 empty] | Yes |  |  | 125000 | 2893282.3 |  | 908863.93 | 783863.93 |  | 2315% | 89292.4 |  |  |  | 1358034.5403 |  | 60 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015394.04 - JM | TL | OH | 2021-032 | 2021 |  | 2020-08-31 | 2020-12-14 |  |  | Y | STANISLAUS 17021888 | 4
35116514 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 2.5 |  |  | PEND | 10882 | 0 | 10852 | 10852 | 2.0553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0553 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-09-22 | 2020-08-31 | 2020-09-22 | 2020-07-24 | 2020-07-24 | yes | 2020-09-22 | [Composite to Wood - Sept List]09/22: APPROVED - INTO PEND09/21: PIKE submitted to 5th ADE rvw09/15: ADE rtn 4th corrections to CO; ready for final upon applying corrections09/09: PIKE Conversion Complete; Documents submitted09/08: Conversion sub 9/1109/01: OCT EOD; target sub TBD - Conversion Comp to Wood08/25: ADE target sub (8/27)08/19: PIKE submitted for 4th ADE rvw08/17: ADE rtn 3rd corrections to CO08/11: ADE in rvw - Priority Based (8/7); (8/14)08/04: PIKE submitted for 3rd ADE rvw07/28: ADE rtn corrections to CO07/24: PIKE submitted to 2nd ADE rvw; [REDACTED] (EST) will be taking over estimating07/21: EST sub (7/22); JPA dependency07/14: On Track; IT ticket resolved late last week07/07: IT ticket submitted (WIP timing out/OCALC issues)- Low Risk for shift06/30: EST Target sub (7/17) |  |  |  | 2020 - Q3- M9 [R2021_33] | COMPLETED |  | Wood | 44 | 19 |  | 2020-09-23 | Yes |  |  |  | 2020-12-31 | 2020-12-31 |  |  |  |  | Full | 2023-12-25 | 2023-12-25 |  |  |  | CIF Submitted 6/22/20; received final drawings week of 9/20/20. Have received veg scope and locations are on USFS. |  |  | 2020-12-15 |  |  |  | Submitted on 10/19 |  | 2021-03-20 |  | 2021-02-22 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0553 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-08-05 08:00 | 2022-10-24 17:00 |  | 2022-12-23 17:00 | [8 empty] | 125000 | 2917903.5 |  | 964490.61 | 839490.61 |  | 2334% | 107022.2 |  |  |  | 1419695.0313 |  | 65 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015394.05 - JM | TL | OH | 2021-033 | 2021 |  | 2020-08-31 | 2020-12-14 |  |  | Y | STANISLAUS 17021888 | 4
35116515 |  | 2021 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 |  |  | UNSC | 8765 | 0 | 9222 | 9222 | 1.7466 | 0 | 0 | 9222 | 1.7466 | 0 | 0 | 0 | 0 | 0 | 9222 | 1.7466 | ST | 08W | SH | 2020-11-30 |  |  | 2020-05-29 | 2020-09-30 | 2020-05-29 | 2020-04-28 | 2020-04-28 | Yes | 2020-05-29 | 05/29: Final review correctionst rtn to CO; EEI routed for approval; APPROVED - INTO PEND05/28: PIKE submitted for 3rd ADE rvw (EES delays); ADE approved for routing5/26: EST Status; finalizing stamping; sub end of day05/19: On Track; low risk - land rights asking to go back on anchors (rework potential)05/12: EST target sub (5/22)05/02: ADE rtn 2nd corrections to CO04/28: PIKE submitted for 2nd ADE rvw; applied job walk items04/21: On Track04/14: Jobwalk complted, feedback changes, require approval - significant amounts of tree clearing being needed is the main reason for the poles being omitted. ADE agreed with changes - provided recommendations on approach/cost awareness -pole height increase. EST to apply changes.04/07: Est move sub to (4/24): Review/Stamping03/24 - 03/10: EST to firm up 2nd sub date (03/16) - EST to follow up; Estimator out and PM walk through to be scheduled (1-2wk).03/05: Prj Mgr request to pull in03/03: ADE rtn 1st corrections to CO02/28: ADE assigned ( [REDACTED] )12/09: ADE rvw push - 3wk - ADE resourcing11/27: PIKE submitted for 1st ADE rvw11/26: On Track11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact)11/12: 1wk Push - ADE availability eased up target, OT reduction and finalization11/05 <-- 10/29: Requiring refielding for issues coming from design.10/22: On Track (11/15)10/15: Est Started, Early stages of CMCS10/01 Started Fielding Phase 1 - apprx 100% in |  |  |  | 2020 - Q3- M7 [R126] | COMPLETED |  | Comp | 17 | 47 |  | 2020-07-20 | Yes |  |  |  | 2020-06-08 | 2020-06-08 |  |  |  |  | Full | 2020-06-08 | 2020-06-08 | Full |  |  | CIF Submitted 4/23/20 | Full |  | 2020-11-30 |  |  |  | Pre-Con meeting to be scheduled when GC returns 9/17/20. Preliminary only, Requested 5/4/20 - Submitted to TCP on 5/4/20 - [REDACTED] to follow up |  | 2020-10-16 | Y | 2020-08-17 | 2020-07-30 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7466 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-07-27 17:00 | Yes | COMP | 2021-05-04 08:00 | 2021-07-05 17:00 |  | 2021-09-09 17:00 | 2020-07-20 | 2021-06-08 07:00 | 2021-09-30 16:00 |  | 2020-10-10 | Yes |  |  | 3203034.7 | 2141709.1 | 2685572 | 4438411 | 1235376.3 |  | 66.86% | 206945.9 |  |  | -312.98 | 1226222.5166 |  | 64 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.02 - JM | TL | OH | 2021-025 | 2021 | 2020 Reserve | 2020-07-31 | 2020-10-14 | 2020-12-07 |  | Y | STANISLAUS 17021888 | 2386 |  | PRE |  | 2021-03-08 13:57
35116516 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 |  |  | PEND | 4528 | 0 | 4825 | 4825 | 0.91383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91383 |  |  | ST | 08W | SH | 2020-11-30 |  |  | 2020-06-09 | 2020-09-30 | 2020-06-09 | 2020-04-30 | 2020-04-30 | Yes | 2020-07-15 | 06/09: APPROVED - INTO PEND06/04: EST applied corrections - rerouting06/03: Final corrections sent to CO06/01: EST routed for approval05/30: ADE approved for routing05/26: PIKE provided est. and sketch per request, seeking final labor and cost check before routing05/26: Est to finalize information for ADE to approve routing05/20: Pending information from Selina05/19: EST Hrs/cost emailed; do not have vegetation, eta 5/29, will apply JE and add est to business case if PM in PEND by then. --> project is under review with land and environmental right now. Our ERTC date is 6/25/2020 - High level GIS provided.05/19: Verify if rvw rtn to CO ...set 3rd sub date; job walk 1.4 - impacted 1.305/15: ADE - Final reviewed job, still waiting on costs from PM. Also please see note below from estimator. Reviewed all Ocalcs, but still GO 9504/30: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready]04/28: EST finalizing last minute; details/corrections; submit end of day04/21: On Track04/14: Construction walk (3/31); Applying changes (push 1-2 days); internal processing04/07: Est set sub date (4/17)03/31: EST to firm up sub date??03/26: ADE rtn 1st corrections to CO03/17 - 03/10: ADE Set/firm up 1st rvw date (3/23)??03/05: Prj Mgr request to pull in03/03: ADE Assigned ( [REDACTED] )12/09: ADE rvw push - 3wk - ADE resourcing12/09: PIKE submitted for 1st ADE rvw12/03 On Track 11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact)11/12: 1wk Push - ADE availability eased up target, OT reduction and finalization11/05 <-- 10/22: On Track (11/15)10/15: Est Started, Early stages of CMCS10/01 Started Fielding Phase 1 - apprx 100% in |  |  |  | 2020 - Q3- M7 [R127] | COMPLETED |  | Comp | 11 | 25 |  |  | Yes | [9 empty] | Full | 2020-06-17 | 2020-06-17 | Full |  |  | CIF Submitted 5/8/20, released 6/16/20 | Full |  | 2020-11-30 |  |  |  | Pre-Con meeting to be scheduled when GC returns 9/17/20. |  | 2020-11-14 |  | 2020-09-26 | 2020-07-30 |  | 90% complete as of 12/9/20 - Need a clearance, will wait for construction to start. 1 crane tree | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91383 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-06 17:00 | Yes | INPR | 2022-02-22 08:00 | 2022-04-18 17:00 |  | 2022-08-12 17:00 | 2020-07-14 |  |  |  | 2020-10-10 | Yes |  |  | 2239023.3 | 1535681.7 |  | 1532501.31 | -706521.99 |  | 68.58% | 159492.8 |  |  |  | 1680497.28 |  | 37 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.03 - JM | ML | OH | 2021-024 | 2021 | 2020 Reserve | 2020-07-31 | 2020-10-14 | 2020-11-25 |  | Y | STANISLAUS 17021888 | 4
35116517 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.5 |  |  | UNSC | 10921 | 0 | 12677 | 12677 | 2.4009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 |  |  | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-08-24 | 2020-08-31 | 2020-08-24 | 2020-08-04 | 2020-08-04 | Yes | 2021-03-10 | 08/24: APPROVED - INTO PEND08/20: Final corrections provided for approval; corrections under way08/18: EST target to route 8/1908/17: ADE rtn 3rd corrections to CO; apply and route08/13: PIKE submitted tor 3rd ADE rvw08/11: ADE rtn 2nd corrections to CO08/04: EST target sub (Today); OCALC/EES system issue; PIKE submitted for 2nd ADE rvw07/27: On Track - in que for stamping07/21 - 07/14: EST target sub (7/31)07/10: ADE rtn 1st corrections to CO07/07: ADE in rvw - priority based06/25: PIKE submitted for 1st ADE rvw [2]06/22: EST submitted06/16 - 06/10: EST - Target Sub (6/24); Applying walkdown changes06/09: On Track (6/9)06/08: PMgr communicated to ADE; EST looped in, make sure the walkdown changes have been incorporated - constructability walkdown conducted In December of 2019; A few poles had to be moved, etc. This was not completed still on this 4/20/2020 construction drawing. EST Target sub (6/9)06/02: Submittal confirmed?? No email record or updates in SAP notes ??05/26: With ADE - EST replotted and submitted; ADE to conclude rvw05/19: EST applied corrections and submitted; Estimator change05/05: EST to submit (5/7)05/01: ADE rtn 1st corrections to CO - [rejected] looks like the new primary lines are drawn in the secondary position. This is confusing and needs to be corrected before I can start my review04/29: PIKE submitted for 1st ADE rvw04/28 - 04/21: On Track4/14: EST prioritized on Brunswick 3.3; Push 1.5 wk04/06: PIKE pulled back for QC review04/01: ADE assigned ( [REDACTED] )03/17: ADE -check with [REDACTED] in skip12/05 PIKE submitted for 1st ADE rvw12/04: O-Calc update was pushed on Wednesday - generating pole failures. Due to update, some poles required upgrades (O-Calc, DWGs, EES and JPA)11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact)11/12: 1wk Push - ADE availability eased up target, OT reduction and finalization11/05<-- 10/22: On Track (11/15)10/15: Fielding Resumed (PSPS impact) - holding dates at this time10/01 Started Fielding Phase 1 - apprx 20% in |  |  |  | 2020 - Q3- M8 [R2021_27] | COMPLETED |  | Comp | 50 | 66 |  | 2020-09-18 | Yes |  |  |  | 2020-08-24 | 2020-08-24 |  |  |  |  | Full | 2020-09-21 | 2020-09-21 | Full |  |  | Waiting on final drawings. Prelim enviro reviews complete. | Full |  | 2020-11-10 |  | 2021-11-04 |  | Approved Permit email received 11/5, PreCon held 11/4, Ready for Precon as of 10/27 |  | 2020-12-05 |  | 2020-12-01 | 2020-10-21 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4009 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-04-14 08:00 | 2022-07-01 17:00 |  | 2022-10-21 17:00 | 2021-03-09 | [7 empty] | 250000 | 3117252.3 |  | 2688006.56 | 2438006.56 |  | 1247% | 117096.8 |  |  |  | 1298342.8369 |  | 116 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.05 - JM | MX | OH | 2021-027 | 2021 |  | 2020-08-31 | 2020-11-14 |  |  | Y | STANISLAUS 17021888 | 4
35116518 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.6 |  |  | PEND | 10922 | 0 | 10922 | 10922 | 2.0686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0686 |  |  | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-10-31 | 2020-08-31 | 2020-10-31 | 2020-08-26 | 2020-08-26 | Yes | 2021-01-21 | [Composite to Wood - Sept List][OCT EOD at RISK]10/27: PIKE submitted corrections for 5th ADE rvw - routing for approval10/27: ADE rtn 3rd rvw to CO; minor10/26: PIKE submitted 3rd corrections for ADE rvw10/20: On Track10/13: EST target sub (10/20); ADE corrections applied - applying Job walk corrections10/09: ADE rtn 2nd corrections to CO10/06 -10/03: ADE advised rvw target 10/1209/28: ADE in rvw; priority based09/23: ADE reassigned ( [REDACTED] )09/22: ADE in rvw; Priority09/15: PIKE submitted for 2nd ADE rvw [2]; Conversions Complete 09/15 - 09/08: Conversion sub 9/18; Estimator reassigned; RISK - ADE going on LOA Sept 25th (tentative - Transition to [REDACTED] )09/01: OCT EOD; target sub TBD - Conversion 64 Comp to Wood (9/18)??08/26: PIKE submitted for 2nd ADE rvw08/25: On Track08/18 - 08/11: EST Target sub (8/21)08/05: ADE rtn 1st corrections to CO; Apply initial ADE corrections 08/04 - 06/23: ADE in rvw - priority based; ADE advised should be rtn to CO soon.06/10: ADE reassigned ( [REDACTED] )06/09 - 05/19: ADE rvw - priority based04/28 - 04/08: ADE to firm up date (??) - lower priority04/06: Rvw in Prog |  |  |  | 2020 - Q4- M10 [R2021_28] | EDRS - EST Routing for approval |  | Wood | 81 | 12 |  | 2020-11-06 | Yes |  |  |  | 2020-11-15 | 2020-11-15 |  |  |  |  | Full | 2020-11-30 | 2020-11-30 | Full |  |  | CIF Submitted 7/11/20; Prelim reviews completed. Received final drawings on 11/4/20 and received list of changes on 11/12 | Full | [7 empty] | 2021-03-13 |  | 2021-02-15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0686 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-06-22 08:00 | 2022-09-01 17:00 |  | 2022-11-02 17:00 | 2021-01-20 | [7 empty] | 250000 | 2776532 |  | 1631980.57 | 1381980.57 |  | 1111% | 120031.8 |  |  |  | 1342253.1551 |  | 92 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.06 - JM | TL | OH | 2021-028 | 2021 |  | 2020-08-31 | 2020-11-14 |  |  | Y | STANISLAUS 17021888 | 4
35116519 |  |  |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 |  |  | PEND | 9579 | 0 | 9268 | 9268 | 1.7553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7553 |  |  | ST | 08W | SH | 2022-02-25 17:00 |  |  | 2020-08-27 | 2020-10-31 | 2020-08-27 | 2020-06-05 | 2020-06-05 | Yes | 2020-12-30 | {AUG EOD} 08/27: APPROVED - INTO PEND 08/26: Final corrections communicated 08/25: PIKE submitted for 5th ADE rvw 08/18: EST sub target (08/21) 08/13: ADE rtn 4th corrections to CO 08/04: ADE in rvw; target 8/10 08/03: PIKE submitted for 4th ADE rvw 07/27: On Track - in que for stamping 07/21: Est target sub (7/31); Estimator being assigned 07/15: ADE rtn 3rd corrections to CO 07/09: Estimator change 07/07: ADE in rvw - priority based 07/02: PIKE submitted for 3rd ADE rvw 06/30: On Track 06/23: EST target sub (7/02); Fixing a worse case load review 06/21: ADE rtn 2nd corrections to CO 06/16 - 06/09: ADE review - priority based 06/05: PIKE submitted for 2nd ADE rvw 06/02: Estimator priority work - Brunswick and other items popped up. Target (6/5) or sooner 05/26: On Track 05/19: Estimator prioritized on Brunswick changes; will be working through stamping ; sub (5/29) 05/12: Finalizing job walk changes; push to mid week 05/05: PH 1.1, 1.3, 1.4 impacted by Job Walk - Construction changes impact design scope (change orders anticipated) 04/28: Push - Job walk occurring today (4/28); EST to apply corrections 04/21 - 04/14: EST firm up sub date(5/1); On Track; 04/13: ADE rtn 1st corrections to CO 03/17: ADE target date?? 03/12: ADE assigned (Linda) 12/09: ADE rvw push - 3wk - ADE resourcing 11/28: PIKE submitted for 1st ADE rvw 11/26: On Track 11/19: Push; Pole Availability - Composite switch (AVG 50%+ Impact) 11/12: 1wk Push - ADE availability eased up target, OT reduction and finalization 11/05 <-- 10/22: On Track (11/15) 10/15: Fielding Resumed (PSPS impact) - holding dates at this time 10/1 Started Fielding Phase 1 - apprx 50% in |  |  |  | 2020 - Q3- M8 [R2021_26] | COMPLETED |  | Comp | 23 | 54 |  | 2020-09-21 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-15 | 2020-09-15 | Full |  |  | CIF Submitted 5/6/20; preliminary enviro reviews completed and waiting for final estimation to release | Full |  | 2020-11-30 |  |  |  | County Pre-Veg meeting scheduled on 10/14. Submitted revised drawings to Calaveras Co on 9/28/20 |  | 2020-12-19 |  | 2020-11-17 | 2020-09-17 |  | Pre Veg meeting with county 10/14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7553 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-25 17:00 |  | INPR | 2022-03-22 08:00 | 2022-05-13 17:00 |  | 2022-09-28 17:00 | 2020-10-29 | [7 empty] | 250000 | 2231559.9 |  | 2253896.9 | 2003896.9 |  | 892.6% | 83922.2 |  |  |  | 1271324.587 |  | 78 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5015701.04 - JM | TL | OH | 2021-026 | 2021 | 2020 Reserve | 2020-07-31 | 2020-10-14 | 2020-12-10 |  | Y | STANISLAUS 17021888 | 4
35116800 |  | 2021 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Scoped | DOCC | 6695 | 0 | 7225 | 7225 | 1.3684 | 3907 | 0.73996 | 3318 | 0.62841 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-08-03 |  | Y | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-13 | 2020-01-13 | Yes | 2020-08-28 | 07/15: EEI routed07/14: EEI submited redesign for ADE rvw; ADE ready for approval07/06: Redesign - 5 new poles on this job to follow PGE existing easement03/12: APPROVED - INTO PEND03/10: In final review (03/10 target)03/09: Routed for approval03/03: ADE rtn 4th corrections to CO - EST complete corrections and route02/26: EEI submitted for 4th ADE rvw02/17: ADE rtn 3rd correction to CO02/10: EEI submitted for 3rd Rvw01/29: Need ADE contact to coordinate corrections (Q&A)01/23: ADE rtn Corrections to CO01/15: EST on track?? EOD at risk??01/14: ADE rtn 2nd corrections to contractor01/13: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]12/30: ADE rtn 1st corrections to Contractor12/18: ADE resourcing push12/16: Est uploaded updated Ocalcs12/13: ADE advised EST on outcome of Stamp meeting and reqs - Ocalcs will need updating12/05: ADE request another project; new OE - need documents uploaded; EST advised on loc of docs12/04: ADE assigned ( [REDACTED] )11/27: ADE to be assigned11/20: Composite Pole impact (32 pols/ 24 hrs)11/13: ADE to be assigned11/05: EEI submitted for 1st ADE rvw10/29 <-- 10/16: On track 1st sub for 11/0610/09: Push 2wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 |  |  |  | Redesign | EDRS - Pending EDRS approval |  | Comp | 10 | 42 |  |  | Yes |  |  |  | 2020-07-17 | 2020-07-17 |  |  |  |  | Full | 2020-04-14 | 2020-04-14 | Full |  |  | Land issue @ LOC 54. Trying to resolve by 7/31. | Full |  |  | Yes |  |  | RP56 cleared 3/31 |  | 2020-09-18 | Y | 2020-08-03 |  |  | 9/2: Per [REDACTED] , one location left...to be complete by 9/15. | [7 empty] | 0 | 0 | 3907 | 0.73996 | 1426 | 0.27008 | 1.01 | 0.35833 | 1.0032 | 0 | 1.3864 | 0.38314 | 0.0068182 | 0.7358 |  | Keep | 2020-03-31 17:00 | Yes | COMP | 2020-08-10 | 2021-01-08 | Yes | 2021-02-04 | 2020-07-28 | 2021-01-07 | 2021-01-07 | 2021-02-04 | 2020-07-20 | Yes |  |  | 2704456.9 | 1564375.4 | 397410 | 2704457 | 0.1 | 1082917.6 | 57.84% | 1390654.6 | 230884.7 | 1621539.3 |  | 1143239.0466 |  | 50 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.02 - JM |  |  | 2020-039 | 2020 | Q3 | 2020-03-31 | 2020-05-14 | 2020-06-16 |  | Y | MIWUK 17026018 | 2411 |  | PRE
35116801 |  | 2021 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Scoped | CONS | 7835 | 580 | 6197 | 6777 | 1.2835 | 1954 | 0.37008 | 4823 | 0.91345 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-07-20 |  | Y | 2020-04-15 | 2020-04-15 | 2020-04-15 | 2020-02-25 | 2020-02-25 | Yes | 2020-05-28 | 04/15: EST routed for approval; APPROVED - INTO PEND04/13: ADE rtn 4th corrections to CO - EST to cancel conflicting 07D PMS (x4)04/08: ADE status (4/8)??04/03: EEI sub for 4th ADE rvw04/01: Est to firm up sub date (4/3)??03/31: ADE rtn 3rd corrections to CO03/24: EEI submitted for 3rd ADE rvw03/18: Est confirmed sub (3/20) - 3/24 clearing up some conflicting information to apply corrections.03/17: ADE rtn 2nd corrections to CO03/11 - 03/03: Push ADE target 3/13; task with getting correct process in place for standards, Rule 20A picking back up - working with Estimators who took over work.02/25: ADE confirmed working 2nd rvw02/25: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]02/19 <-- 01/22: EST to follow up - JO constructability rvw, confirm scope change or not (location shift between PMs); Computer issues - working to recover files (2wk per TSC)01/08: On Track12/18: EST Priority shifts; Ocalc end/rise drop need to be updated on each location12/06: ADE rtn corrections to contractor (EST access issues - req resubmit)11/27 <-- 11/20: ADE priorities may impact; Push 2wk (3-4 projs being balanced)11/13: Check w ADE - On track?11/06: Check in with ADE10/29: With ADE for rvw10/22: ADE assigned ( [REDACTED] ) - Push 2wk for 1st rvw duration10/16: ADE to be assigned (waiting for 2020 priority list)10/14: EEI submitted for 1st ADE rvw10/09: On Track for 10/1410/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 |  |  |  | 2020 - Q2- M4 [R40] | COMPLETED |  | Comp/Wood | 40 | 48 |  |  | Yes | [5 empty] | Complete |  |  |  | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 2020-07-27 | Y | 2020-07-20 | [10 empty] | 0 | 0 | 1954 | 0.37008 | 0 | 0 | 0.37008 | 0.91345 | 0.3661 | 0 | 1.2919 | 0.92576 | 0.0039773 | 0.3661 |  | Keep | 2020-07-06 | Yes | COMP | 2020-08-10 | 2021-04-20 17:00 |  | 2021-06-01 17:00 | 2020-07-22 | 2020-08-25 07:00 | 2021-04-30 16:00 |  | 2020-07-13 | Yes | Contract |  | 2333945.2 | 1618071.7 | 441774.7 | 3408934 | 1074988.8 | 551476.3 | 69.32% | 1400755.2 | 381713.7 | 1782468.9 |  | 1260649.0447 |  | 41 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.03 - JM |  |  | 2020-040 | 2020 | Q3 | 2020-04-30 | 2020-04-30 | 2020-06-05 |  | Y | MIWUK 17026018 | 23
35116802 |  | 2020 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  |  | DOCC | 10855 | 0 | 12725 | 12725 | 2.41 | 12725 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-05-01 |  |  | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-12 | 2020-02-12 | Yes | 2020-05-01 | 02/19: ADE concurring job - issues clearing the FAA screen - sent a Ticket for assistance02/13: ADE rtn 2nd corrections to CO; minor items02/12: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]02/10: ADE rtn 1st corrections to CO01/27: ADE assigned ( [REDACTED] )01/15 <-- 01/08: ADE to be assigned1/03: EEI submitted for 1st ADE rvw12/18: EST Priority shifts11/20: Push to 12/23 |  |  |  | 2020 - Q2- M5 [R41] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full | 2020-04-09 | 2020-04-09 | Full |  |  |  | Full |  |  | Yes |  |  | RP56 cleared 3/31 |  | 2020-06-19 | Y | 2020-05-01 |  |  | Veg confirmed TT 100% complete (6/29) | [7 empty] | 0 | 0 | 12725 | 2.41 | 0 | 0 | 2.41 | 0 | 2.2167 | 0 | 2.2237 | 0.0070076 | 0.19337 | 2.2167 |  | Keep | 2020-04-15 | Yes | NOTN | 2020-06-16 | 2020-09-17 | Yes | 2020-09-17 | 2020-06-08 | 2020-06-15 | 2020-08-20 |  |  | Yes | Shovel Ready |  | 5118557.8 |  | 53034.5 | 2559279 | -2559278.8 |  |  | 2456250.9 | [5 empty] | 86 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.04 - JM |  |  | 2020-041 | 2020 | Q2 | 2020-05-31 | 2020-08-14 | 2020-09-27 |  | Y | MIWUK 17026018 | 23
35116803 |  |  |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  |  | PEND | 10795 | 0 | 12083 | 12083 | 2.2884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2884 |  |  | YO | 08W | SH | 2022-01-24 08:00 |  |  | 2020-08-24 | 2020-10-31 | 2020-08-24 | 2020-08-14 | 2020-08-14 | yes | 2020-10-26 | 08/24: APPROVED - INTO PEND08/21: ADE - Final corrections provided; EEI applied and routed08/19: EST applying final corrections08/17: ADE rtn addition corrections to CO - apply and route08/14: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]08/12: EST target sub (8/14); Waiting for JO costs08/05 - 07/29: On Track07/22 - 07/15: EST target sub (7/31); (8/07) - priorities07/08: On Track07/01: Est target sub (7/17); Priority Work06/24: Est target sub (7/2); Big Basin focus06/17: On Track06/10: Push - Target sub (6/22); for priority work06/03 - 05/13: On Track05/06 - 04/29: EST push for priority work 1wk04/22: Push (05/15); priority PMs being worked.04/15 - 03/25: On Track03/02: ADE rtn 1st corrections to CO02/26: ADE firm up target date (03/17)02/25: ADE assigned ( [REDACTED] )02/13: EEI submitted for 1st ADE rvw02/12: EST on Track02/05 <-- 01/29: Internal review; push EOW or Mid next week01/22: EST in internal review01/08: On Track12/18: EST Priority shifts11/27 <-- 11/13: On Track 12/1311/06: |  |  |  | 2020 - Q3- M8 [R2022(+)_42] | COMPLETED |  | Comp | 2 | 82 |  | 2020-09-22 | Yes |  |  |  | 2020-08-25 | 2020-08-25 |  |  |  |  | Full | 2020-09-21 | 2020-09-21 | Full |  |  | CIF received | Full |  | 2020-11-15 | Yes |  |  | Submitted app in August - 10/13 - [REDACTED] to follow up with county | [6 empty] | [REDACTED] to send drawings to [REDACTED] | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2884 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-24 08:00 |  | INPR | 2022-03-07 08:00 | 2022-06-14 17:00 |  | 2022-07-26 17:00 | 2020-10-23 | [7 empty] | 200000 | 3039613.8 |  | 200000 | 0 |  | 1520% | 167824.6 |  |  |  | 1328243.0575 |  | 54 | [7 empty] | Remove |  | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.05 - JM | ML |  | 2020-042 | 2021 | Reserve | 2020-06-30 | 2020-08-14 | 2020-09-27 |  | Y | MIWUK 17026018 | 23
35116804 |  | 2020 | 220 Mile Plan | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  |  | DOCC | 5340 | 0 | 5368 | 5368 | 1.0167 | 5368 | 1.0167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2020-05-01 |  |  | 2020-04-23 | 2020-04-23 | 2020-04-23 | 2020-01-02 | 2020-01-02 | Yes | 2020-04-23 | 04/23: APPROVED - INTO PEND04/22: Final approval corrections rtn to CO04/21: Routed with associated changes04/20: ADE/EST coordinated on resolution04/17: Routing issues04/15: ADE to advise should be done - EST should be routing04/08: On Track ***no records of activities 2.3 to3.3; Dates applied per EEI update list04/01: ADE rtn 2nd corrections to CO03/25: ADE Status??02/19: Need EST status02/19: ADE update - need to send full pkg (2nd sub); waiting on the planner to review (previous planner has retired and the new one said he will be reviewing all the Miwuk phases )02/07: EEI submitted for 3rd ADE rvw - Incomplete/Partial02/05: Received feed back, EST applying corrections01/29: EST/ADE/JO - coordinating corrections; EEI to firm up submittal target01/22: EST/ADE coordination on corrections01/14: ADE rtn 2nd corrections to CO (pt2) - coordination with EST01/08: Est Target 1/1701/06: ADE rtn 2nd corrections to contractor - attached a document that's attached to sap, it's from planning. only reviewed what I've attached so far, I wanted to get this info to you quickly in case you hadn't heard from the planner.1/03: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]12/16: ADE rtn 1st corrections to contractor12/11: Pushed 2 wk; ADE status?11/21: ADE assigned ( [REDACTED] )11/20 <-- 11/06: ADE to be assigned11/01: EEI submitted for 1st ADE rvw10/29 <-- 10/16: On track 1st sub for 10/1810/09: Push 1wk; Impacted by numerous scope updates to previously approved key unit jobs.10/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 |  |  |  | 2020 - Q1- M3 [R43] | COMPLETED |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 2020-05-26 | Y | 2020-05-01 |  |  | 100% complete | [7 empty] | 0 | 0 | 5368 | 1.0167 | 0 | 0 | 1.0167 | 0 | 1.0167 | 0 | 1.0167 | 0 | 0 | 1.0167 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-05-28 | 2020-06-23 | 2020-08-26 | 2020-08-22 |  | Yes | Shovel Ready |  | 3736373.6 |  |  | 1868187 | -1868186.6 |  |  | 2922109.5 | [5 empty] | 39 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.06 - JM |  |  | 2020-043 | 2020 | Q3 | 2020-03-31 | 2020-03-30 | 2020-04-28 |  | Y | MIWUK 17026018 | 23
35116861 |  | 2020 |  | BUCOCAMPT 546 HILLCREST DR PARADISE*ILB |  |  | DOCC |  | 0 | 1089 | 1089 | 0.20625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1089 | 0.20625 | 0 | 0 | 0 | 0 | 0.20625 | 0 | 0.050189 | 0 | 0.050189 | 0 | 0.15606 | 0.050189 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-14 | [29 empty] | 39.7469 | -121.629 |  |  |  |  | 2019
35116863 |  | 2020 |  | BUCOCAMPT 5721 BONNIE LN PARADISE*ILB |  |  | FICL |  | 0 | 540 | 540 | 0.10227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 540 | 0.10227 | 0 | 0 | 0 | 0 | 0.10227 | 0 | 0.10227 | 0 | 0.10227 | 0 | 0 | 0.10227 |  |  |  |  | N/A | [5 empty] | 2019-11-12 | 2019-11-15 | 2019-11-16 | [29 empty] | 39.7558 | -121.5948 |  |  |  |  | 2019 | [5 empty] | Y
35116866 |  | 2020 |  | BUCOCAMPT 5594 SIERRA PARK DR PARADISE |  |  | FICL |  | 0 | 265 | 265 | 0.050189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 265 | 0.050189 | 0 | 0 | 0 | 0 | 0.050189 | 0 | 0.20625 | 0 | 0.20625 | 0 | -0.15606 | 0.20625 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-18 | [29 empty] | 39.7484 | -121.6256 |  |  |  |  | 2019
35116921 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  |  | PEND | 8460 | 0 | 8059 | 8059 | 1.5263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5263 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2020-08-27 | 2020-08-31 | 2020-08-27 | 2020-05-15 | 2020-05-15 | Yes | 2020-08-27 | 08/27: Final corrections communicated; APPROVED INTO PEND08/25: ADE rtn 5th corrections to CO; BCF submitted for 6th ADE rvw; approved for routing.08/25 - 08/18: ADE in rvw; Priority Based08/14: BCF submitted for 5th ADE rvw08/11 - 08/04: On track07/29: EST target sub (8/14); Estimator out 1 wk07/22: ADE rtn 4th corrections to CO07/21 - 07/07: ADE target sub (7/24); priority based07/02: BCF submitted for 4th ADE rvw06/30: On Track06/23: EST target sub (7/2)06/17: ADE rtn 3rd corrections to CO06/16: ADE Rvw; Aug Priority (07/17); [? 5 HP PMs]06/09 - 06/02: ADE soft target (6/08);(6/12)05/28:BCF submitted for 3rd ADE rvw05/26: EST Target sub (5/29)05/18: ADE - not seen this type of location system used, the locations jump all over the place; ADE does not mind calling for a class 1 poles but the crew foreman is probably going to call and ask if a lesser class pole will work. 05/15: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready]05/05 - 04/07: EST to firm up Sub date(5/15)03/26: ADE rtn 1st corrections to CO - Low level rvw, took as far as he could.03/23: ADE assigned ( [REDACTED] ) - firm up rvw date (4/11)??03/17<-- 10/29: ADE to be assigned10/22: PUSH 1month - ADE resourcing10/18: BCF submitted for 1st ADE rvw10/15 <-- 10/01 |  |  |  | 2020 - Q3- M8 [R2021_85] | COMPLETED |  | Comp | 9 | 46 |  | 2020-09-15 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2023-12-25 | 2023-12-25 |  |  |  | Meeting with Forest Svs on Nov 16 to address concerns with vegetation removals. State Parks package submitted and following up with archaeological concerns. |  |  | 2020-12-01 |  |  |  | Submitted on 10/15/20 - Check sent on 10/16 |  | 2021-03-13 |  | 2021-02-08 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5263 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-07-08 08:00 | 2022-09-19 17:00 |  | 2022-11-18 17:00 | [8 empty] | 250000 | 2177031.5 |  | 1152639.46 | 902639.46 |  | 870.8% | 108228.4 |  |  |  | 1426321.6677 |  | 53 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.02 | TL | OH | 2021-085 | 2021 |  | 2020-07-31 | 2021-08-25 |  |  | Y | STANISLAUS 17021804 | 19
35116922 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  |  | PEND | 6221 | 0 | 6121 | 6121 | 1.1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1593 |  |  | ST | 08W | SH | 2022-02-08 17:00 |  |  | 2020-06-18 | 2020-08-31 | 2020-06-18 | 2020-06-05 | 2020-06-05 | Yes | 2020-11-10 | 06/18: APPROVED - INTO PEND06/18: Final corrections rtn to CO; EST applied final corrections; routed06/17: EST submitted for final review; routed for approval06/16: ADE rtn 2nd corrections to CO; minor - apply and route06/16: ADE Rvw; Aug Priority (07/10); [? 3 HP PMs]06/09: ADE soft target (6/12)06/05: BCF submitted for 2nd ADE rvw06/02: On Track05/26: Push 1wk (6/05); changes applying from job walk05/19 - 05/15: EST target sub (5/29); Estimator prioriy Job Walks05/12: EST target sub (5/22)5/11: ADE rtn 1st corrections to CO05/05: ADE rvw - priority based04/21: Per ADE - Target rtn to CO next week04/14 - 04/14: ADE working priority PMs review status??03/26: ADE request CO to upload all docs to SAP03/24: ADE to firm up sub date (4/12)??03/24: ADE assigned [REDACTED] ()03/17 <-- 10/29: ADE to be assigned - ADE Resourcing10/25: BCF submitted for 1st ADE rvw10/22 <-- 10/01: On Target9/24: Targets dependent on 1.1 - pole increase impact - push 2 weeks |  |  |  | 2020 - Q3- M7 [R155] | COMPLETED |  | Comp/Wood | 22 | 32 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted on 5/23/20 | Full |  | 2020-11-10 |  | 2021-11-04 |  | Approved Permit email received 11/5, PreCon held 11/4, Ready for Precon as of 10/27 |  | 2021-01-09 |  | 2020-11-20 | 2020-10-14 |  | On hold for county preveg meeting | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1593 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-08 17:00 |  | INPR | 2022-04-08 08:00 | 2022-05-30 17:00 |  | 2022-09-28 17:00 | 2020-11-09 | [7 empty] | 125000 | 1572656.3 |  | 966585.11 | 841585.11 |  | 1258% | 70295.7 |  |  |  | 1356579.8504 |  | 54 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.03 | TL | OH | 2021-086 | 2021 |  | 2020-07-31 | 2021-08-25 |  |  | Y | STANISLAUS 17024905 | 82
35116923 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  |  | ADER | 6326 | 0 | 6326 | 6326 | 1.1981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1981 |  |  | ST | 08W | SH | 2022-03-18 17:00 |  |  | 2020-12-31 | 2020-10-31 | 2020-12-31 | 2020-08-13 | 2020-08-13 | Yes |  | [Composite to Wood - Sept List]11/10 - 10/23: ADE in rvw; Priority Based10/07: BCF submitted for 2nd ADE rvw [2] - Conversions complete10/06: EST Submittal by 10/809/28 - 09/08: Conversion 1st sub (10/09)09/01: EST target sub 11/30 (TBD); conversion,, will need to pull in (11/02)?08/25 - 08/18: ADE in rvw; Priority Based08/13: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready]08/11 - 08/04: On Track07/27: EST target sub (8/21); RISK - level of corrections request; renumbering07/23: ADE rtn 1st corrections to CO07/21 - 06/30: ADE rvw - priority based06/19: BCF submitted for 1st ADE rvw [2]06/16 - 06/04: EST - Target (6/19); conducted a walk down of this job on April 23rd with the Project Manager and Construction Supervisor to discuss any design changes required. We made necessary changes and are currently renumbering all the field notes, Ocalcs and drawing locations 06/02 - 05/26: EST sub (6/12); renumbering05/19 - 05/05: EST to complete missing information - priority based04/28 - 04/14: EST/ADE coordinating efforts04/01: ADE rejected 1st submittal; sending this project back as there is a lot of information missing03/26: ADE assigned ( [REDACTED] )03/24<-- 11/05: Push 2wk - ADE Resourcing11/01: BCF submitted for 1st ADE rvw10/29 <-- 10/22 <-- 10/01: On Target9/24: Targets dependent on 1.1 - pole increase impact - push 2 weeks |  |  |  | 2020 - Q4- M12 [R2021_87] | R2.2 - ADE Review in Progress |  | Wood | 65 | 2 | [15 empty] | Full |  |  | 11/6/19 CIF Submitted |  |  | 2020-11-13 |  |  |  | Waiting on Approved Permit - Pre Veg/Cons meeting held 10/5/2020. |  | 2020-11-28 |  | 2020-10-26 | 2020-10-14 |  | 54% complete as of 12/9 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1981 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-18 17:00 |  | INPR | 2022-04-19 08:00 | 2022-06-29 17:00 |  | 2022-08-30 17:00 | [8 empty] | 125000 | 2006777.7 |  | 1 | -124999 |  | 1605% | 59001.3 |  |  |  | 1674958.3079 |  | 69 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.04 | TL | OH | 2021-087 | 2021 | 2020 Reserve | 2020-07-31 | 2020-08-30 | 2020-10-16 |  | Y | STANISLAUS 17024905 | 82
35116924 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  |  | PEND | 9910 | 0 | 9910 | 9910 | 1.8769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8769 |  |  | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-11-30 | 2020-09-30 | 2020-11-30 | 2020-07-10 | 2020-07-10 | Yes | 2020-12-08 | [Composite to Wood - Sept List]11/10: ADE in rvw11/05: BCF submitted corrections for 3rd ADE rvw11/03 - 10/27: Est target sub (11/06)10/22: ADE rtn 2nd rvw to CO10/13: ADE in rvw; target (10/23)10/08: BCF submitted for 2nd ADE rvw [2] - Conversions10/6: Submittal by 10/809/28: Conversion 1st sub (10/09)09/15 - 09/08: Conversion 1st sub (10/02)09/01: EST target sub 10/30 (TBD); conversion, will need to pull in (10/16) ?08/25 - 08/04: EST target sub (8/27); Walkdown - EST apply results; will submit to ADE to continue rvw08/01: ADE rtn 2nd corrections to CO; will rvw after walkdown revisions are made.07/21 - 07/14: ADE rvw - priority based07/11: Job walk being scheduled07/10: BCF submitted for 2nd ADE rvw07/07: On Track06/30: EST target sub (7/10)06/23: ADE return 1st corrections to CO; req to contact PM to inquire if a constructability rvw will be require and any requirements on estimate.- 05/26: EST provided updated notes - with ADE05/19 - 05/05: EST to complete missing information - priority based04/28 - 04/14: EST/ADE coordinating efforts04/13: ADE Rejected 1st submittal; Field notes not complete -There is no OU info… service size, lengths, down guy sizes, no existing anchor info lead lengths.So far none of the ocalc calculations have that info04/06: ADE assigned ( [REDACTED] )03/24 <-- 11/19: ADE to be assigned - ADE Resourcing11/13: BCF Submitted for 1st ADE rvw11/12 <-- 10/01: On Target9/24: Targets dependent on 1.1 - pole increase impact - push 2 weeks |  |  |  | 2020 - Q4- M11 [R2021_88] | R3.2 - ADE Review in Progress |  | Wood | 101 | 0 | [15 empty] | Full |  |  | Estimating revising to avoid easement | [8 empty] | 2021-03-27 |  | 2021-02-15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8769 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-04-07 08:00 | 2022-06-17 17:00 |  | 2022-08-18 17:00 | [5 empty] | Yes |  |  | 250000 | 2735365.7 |  | 1835218.36 | 1585218.36 |  | 1094% | 93827.9 |  |  |  | 1457389.596 |  | 107 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.05 | TL | OH | 2021-088 | 2021 | 2020 Reserve | 2020-08-31 | 2020-09-30 | 2020-11-27 |  | Y | STANISLAUS 17021804 | 19
35116925 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  |  | ADER | 8968 | 0 | 8968 | 8968 | 1.6985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6985 |  |  | ST | 08W | SH | 2022-03-18 17:00 |  |  | 2021-01-31 | 2020-10-31 | 2021-01-31 | 2020-11-03 | 2020-11-03 | Yes |  | [Composite to Wood - Sept List]11/10: EST resub target (11/20); also including constructibility walkdown feedback11/03: ADE [Rejected]; only 5 locs checked. too many missed redlines and errors especially in EES11/02: BCF submitted 2nd corrections for ADE rvw - Converted10/27 - 10/20: EST sub (10/30); Finishing higher priority work; Walkdown needed per PMgr10/06 - 09/08: Conversion 1st sub (10/23)09/08: EST target sub 12/20(TBD); conversion, will need to pull in (12/4)09/02: ADE rtn 1st corrections to CO; EST to complete corrections and conversion09/01: EST 1st sub 12/20(TBD)08/25 - 06/30: ADE in rvw - priority based06/26: BCF submitted for 1st ADE rvw [2] - renumbered06/23 - 06/04: EST Target sub (6/26) - Renumbering; 06/12 - ADE advised BCF - getting ready to begin review again, looking for uploads - EST - to submit next week.06/02 - 05/05: ADE rvw - rejected - priority based04/28 - 04/14: ADE in review; status/date ??04/07: ADE assigned ( [REDACTED] )03/24 <--12/04: ADE to be assigned - ADE Resourcing11/22: BCF Submitted for 1st ADE rvw11/19 <-- 10/01: On Target9/24: Targets dependent on 1.1 - pole increase impact - push 2 weeks |  |  |  | 2021 - Q1- M1 [R2021_89] | R2.3 - EST Implementing Corrections |  | Wood | 53 | 51 | [15 empty] | Full |  |  | CIF Submitted on 1/15/20 | [8 empty] | 2021-04-01 |  | 2021-02-15 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6985 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-18 17:00 |  | INPR | 2022-04-19 08:00 | 2022-07-18 17:00 |  | 2022-09-16 17:00 | [8 empty] | 125000 | 2297341.9 |  | 1 | -124999 |  | 1838% | 70947.3 |  |  |  | 1352583.099 |  | 104 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.06 | MX | OH | 2021-089 | 2021 | 2020 Reserve | 2020-08-31 | 2020-09-30 | 2020-11-24 |  | Y | STANISLAUS 17021804 | 19
35116926 |  |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  |  | PEND | 7880 | 0 | 7711 | 7711 | 1.4604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4604 | 7718 | 1.4617 | ST | 08W | SH | 2022-03-15 17:00 |  |  | 2020-07-16 | 2020-09-30 | 2020-07-16 | 2020-06-05 | 2020-06-05 | Yes | 2020-11-10 | 07/16: APPROVED - INTO PEND07/15: ADE rtn 4th corrections to CO; BCF submitted for 5th ADE rvw; ADE approved for routing.07/14: BCF submitted for 4th ADE rvw07/07: ADE target sub (7/17)07/04: ADE rtn 3rd corrections to CO07/02: BCF submitted for 3rd ADE rvw07/01: ADE clarified instruction change to 18ELF; relocate C/O L5035. Keep Loc-745. So you don't have to fuse the tap at Loc-73006/30: On Track06/23: EST target sub (7/2)06/17: ADE rtn 2nd corrections to CO06/16: ADE Rvw; Sep Priority (07/17); [? 5 HP PMs]06/09: ADE soft target (TBD)06/05: BCF submitted for 2nd ADE rvw06/02: On Track05/26: EST Target Sub (6/5)05/19 - 05/05: Pending clarifications from PGE on standards04/28 - 04/21: EST 2nd sub Target (5/1) - set (5/08)04/17: ADE rtn 2nd corrections to CO04/14: ADE in review; status/date (EOW)04/08: BCF submitted for 1st ADE rvw [2]04/07: ADE rejected 1st submittal; the field note guideline are not followed and DO-Field Note not use. Cannot review this job with the filed notes provided.04/07: ADE assigned ( [REDACTED] )03/24 <--12/04: ADE to be assigned - ADE Resourcing11/22: BCF Submitted for 1st ADE rvw11/19 <-- 11/12: At Risk for slip 1st Submittal - due to PSPS event10/22 <-- 10/01: On Target9/24: Targets dependent on 1.1 - pole increase impact - push 2 weeks |  |  |  | 2020 - Q3- M8 [R158] | COMPLETED |  | Comp/Wood | 28 | 44 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted on 5/23/20 | Full |  | 2020-11-10 |  | 2021-11-04 |  | Approved Permit email received 11/5, PreCon held 11/4, Ready for Precon as of 10/27 |  | 2021-01-09 |  | 2020-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4604 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-15 17:00 |  | INPR | 2022-04-11 08:00 | 2022-06-21 17:00 |  | 2022-08-22 17:00 | 2020-11-09 | [7 empty] | 125000 | 2160080.3 |  | 1575778.82 | 1450778.82 |  | 1728% | 72981.4 |  |  |  | 1479084.9415 |  | 68 |  |  | Complete |  |  |  |  | Remove |  | Arnold | Calaveras | 0 | 0 | E.5014540.07 | TL | OH | 2021-090 | 2021 |  | 2020-08-31 | 2020-11-14 |  |  | Y | STANISLAUS 17021804 | 19
35117007 |  |  |  | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  |  | ESTS | 8402 | 0 | 8402 | 8402 | 1.5913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5913 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-12-31 | 2021-09-30 | 2020-12-31 | 2020-12-17 | 2020-12-17 |  |  | [EOD JAN @ Risk] 11/04 - 10/07: Submittal by 10/16; 10/30, 11/12 IT to provide how to proceed with the fiber that might go UG. 09/30 - 09/23: EST push sub target (10/2) 09/02: EST target (9/11); Composite to Wood shift 08/26 - 08/12: EST target sub (9/4) 07/22- 03/25: EST sub new dates TBD 02/27: Flagged COMPOSITE to WOOD [2] 01/08: Est 1st sub taret changes TBD Anticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M12 [R2021_120] | R0.0 - Estimating |  | Wood | 27 | 16 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5913 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-29 17:00 |  | INPR | 2022-09-13 08:00 | 2023-01-02 17:00 |  | 2023-02-01 17:00 | [8 empty] | 305556 |  |  | 305556 | 0 |  |  | 15519.7 | [8 empty] | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.01 |  |  | 2021-120 | 2022 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35117031 |  | 2020 |  | BUCOCAMPT 1710 RYAN RD PARADISE* |  |  | FICL |  | 0 | 568 | 568 | 0.10758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 568 | 0.10758 | 0 | 0 | 0 | 0 | 0.10758 | 0 | 0.09678 | 0 | 0.09678 | 0 | 0.010795 | 0.09678 |  |  |  |  | N/A | [5 empty] | 2019-10-21 | 2019-10-25 | 2019-10-21 | [29 empty] | 39.7632 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y
35117121 |  | 2020 |  | BUCOCAMPT 5765 DEANNA WAY PARADISE |  |  | FICL |  | 0 | 1140 | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1140 | 0.21591 | 0 | 0 | 0 | 0 | 0.21591 | 0 | 0.031629 | 0 | 0.031629 | 0 | 0.18428 | 0.031629 |  |  |  |  | N/A | [5 empty] | 2019-09-10 | 2019-09-10 | 2019-09-13 | [29 empty] | 39.7558 | -121.592 |  |  |  |  | 2019 | [5 empty] | Y
35117126 |  | 2020 |  | BUCOCAMPT 7070 PENTZ RD PARADISE |  |  | DOCC |  | 0 | 980 | 980 | 0.18561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 980 | 0.18561 | 0 | 0 | 0 | 0 | 0.18561 | 0 | 0.037879 | 0 | 0.037879 | 0 | 0.14773 | 0.037879 |  |  |  |  | N/A | [5 empty] | 2019-09-16 | 2019-09-17 | 2019-09-16 | [29 empty] | 39.7914 | -121.5797 |  |  |  |  | 2019
35117128 |  | 2020 |  | BUCOCAMPT 627 SCOTT DR PARADISE* |  |  | CLSD |  | 0 | 536 | 536 | 0.10152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 536 | 0.10152 | 0 | 0 | 0 | 0 | 0.10152 | 0 | 0.073295 | 0 | 0.073295 | 0 | 0.02822 | 0.073295 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-16 | [7 empty] | 29613.91 |  |  |  | 47816.7 | [17 empty] | 39.7481 | -121.6266 |  |  |  |  | 2019 | [5 empty] | Y
35117130 |  | 2020 |  | BUCOCAMPT 1659 NELSON LN PARADISE*ILB |  |  | FICL |  | 0 | 682 | 682 | 0.12917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 682 | 0.12917 | 0 | 0 | 0 | 0 | 0.12917 | 0 | 0.035038 | 0 | 0.035038 | 0 | 0.094129 | 0.035038 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-11-03 | [29 empty] | 39.7638 | -121.582 |  |  |  |  | 2019 | [5 empty] | Y
35117218 |  | 2020 |  | BUCOCAMPT 840 CENTRAL PARK DR PRDSE*ILB |  |  | CLSD |  | 0 | 700 | 700 | 0.13258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 700 | 0.13258 | 0 | 0 | 0 | 0 | 0.13258 | 0 | 0.14848 | 0 | 0.14848 | 0 | -0.015909 | 0.14848 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-03 | [7 empty] | 55272.31 |  |  |  | 100141 | [17 empty] | 39.7659 | -121.6094 |  |  |  |  | 2019 | [5 empty] | Y
35117219 |  | 2020 |  | BUCOCAMPT 4239 SCHWYHART LN OROVILLE |  |  | DOCC |  | 0 | 463 | 463 | 0.087689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 463 | 0.087689 | 0 | 0 | 0 | 0 | 0.087689 | 0 | 0.21402 | 0 | 0.21402 | 0 | -0.12633 | 0.21402 |  |  |  |  | N/A | [5 empty] | 2019-11-18 | 2019-11-22 | 2019-11-19 | [29 empty] | 39.7908 | -121.4981 |  |  |  |  | 2019 | [5 empty] | Y
35117381 |  | 2020 |  | BUCOCAMPT 2459 HONEY RUN RD CHICO |  |  | CLSD |  | 0 | 525 | 525 | 0.099432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 525 | 0.099432 | 0 | 0 | 0 | 0 | 0.099432 | 0 | 0.063826 | 0 | 0.063826 | 0 | 0.035606 | 0.063826 |  |  |  |  | N/A | [5 empty] | 2019-09-26 | 2019-09-26 | 2019-09-26 | [29 empty] | 39.7422 | -121.6763 |  |  |  |  | 2019
35117406 |  | 2020 |  | BUCOCAMPT 5050 EDEN RD PARADISE |  |  | FICL |  | 0 | 1095 | 1095 | 0.20739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1095 | 0.20739 | 0 | 0 | 0 | 0 | 0.20739 | 0 | 0.074242 | 0 | 0.074242 | 0 | 0.13314 | 0.074242 |  |  |  |  | N/A | [5 empty] | 2019-09-12 | 2019-09-12 | 2019-09-14 | [29 empty] | 39.7331 | -121.6265 |  |  |  |  | 2019
35117411 |  | 2020 |  | BUCOCAMPT 1524 FOREST CIR PARADISE* |  |  | CLSD |  | 0 | 493 | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 493 | 0.093371 | 0 | 0 | 0 | 0 | 0.093371 | 0 | 0.069318 | 0 | 0.069318 | 0 | 0.024053 | 0.069318 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-15 | [7 empty] | 41580.26 |  |  |  | 64791.5 | [17 empty] | 39.7741 | -121.5871 |  |  |  |  | 2019 | [5 empty] | Y
35117443 |  | 2021 | 220 Mile Plan | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Scoped | CONS | 11144 | 0 | 11395 | 11395 | 2.1581 | 0 | 0 | 11395 | 2.1581 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-07-07 |  | Y | 2020-06-03 | 2020-06-23 | 2020-06-03 | 2020-04-13 | 2020-04-13 | Yes | 2021-01-06 | 06/03: APPROVED - IN PEND06/02: Target approval Today (6/2)05/28: routed for approval05/27: ADE rtn 4th corrections to CO05/26: PIKE submitted for 4th ADE rvw05/26: EST update target sub (5/26); target approval EOW05/20: ADE rtn 3rd corrections to CO; Ready to route05/19: ADE soft target (5/21)05/14: PIKE submitted for 3rd ADE rvw05/12: EST finalized stamping, completing NB work; To be submitted today 5/1205/05: EST target sub (5/8)04/28: ADE rtn 2nd corrections to CO04/14: ADE to firm up date (??)04/13: PIKE submitted for 2nd ADE rvw04/07: EST prioritized 1.1; In stamping - target 4/1003/31: EST; PE stamping; tied to finalization of 1.1; ADE finishing higher priority job, will work this one next once recv and complete with other03/24: EST Status on track03/17 - 03/10: Tied to 1.1; working [REDACTED] comments; priority push03/03: EST on 1.1; pushed, Prioritized Bruswick 1.1 changes02/18: EST firm up target date2/14: ADE rtn 1st corrections to CO---12/30 |  |  |  | 2020 - Q2- M4 [R138] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF Submitted 11/25/19 | Full |  |  | Yes | 2020-12-31 |  |  |  | 2020-07-24 | Y | 2020-06-01 |  |  | 157 Units remaining - Started | [7 empty] | 0 | 0 | 0 | 0 | 3432 | 0.65 | 0.65 | 1.5081 | 0.62917 | 0 | 2.1347 | 1.5055 | 0.020833 | 0 |  | Keep | 2020-07-07 | Yes | COMP | 2020-07-28 | 2020-12-03 | Yes | 2021-07-07 17:00 | 2020-12-09 | 2021-01-05 06:00 | 2021-03-12 16:00 |  | 2020-06-23 | Yes | Shovel Ready |  | 4475707 | 2204805.3 | 2450191 | 5778810 | 1303103 | 2011490.8 | 49.26% | 2103914.3 | 360301.9 | 2464216.2 | 0 | 1021621.0605 |  | 56 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015567.06 |  |  | 2020-138 | 2020 | Q3 | 2020-04-30 | 2020-08-01 | 2020-09-07 |  | Y | BRUNSWICK 110350070 | 2144 |  | PRE |  | 2021-03-08 16:55
35117444 |  | 2020 | 220 Mile Plan | CWSP - VOLTA 1102 LR 1648 PH 2.1 |  |  | FICL | 12151 | 0 | 12656 | 12656 | 2.397 | 12656 | 2.397 | 0 | 0 | 0 | 0 | 0 | 0 | -3.1006e-15 |  |  | NV | 08W | SH | 2020-03-26 |  |  | 2019-08-30 | 2019-09-05 | 2019-08-30 |  |  | Yes | 2019-08-30 | 7/9: on track for 7/317/24: PM change from 700-Series [74022391] to 300-Series [35117444]; EES not functioning with 700-Series7/30: On track to submit for 7/318/1: EN submitted for 1st ADE review; ADE TBD8/13 - Request for [REDACTED] to assign ADE8/20: Accessibility issues to documents, resolved - initiating review - EOD pushed 1wk8/21: 1st ADE corrections rtn to contractor8/27: EN routing for approval - today?[PRELIM DWG ready]IN PEND |  |  |  | Completed | COMPLETED | No |  | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/6/19. Caltrans Annual | Full |  |  | Yes |  |  | Permit request sent 8/5/19 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 12656 | 2.397 | 0 | 0 | 2.397 | -3.1006e-15 | 2.397 | 0 | 2.397 | 0 | 3.1006e-15 | 2.397 |  | Keep | 2020-03-26 | Yes | N/A | 2019-12-05 | 2020-04-29 | Yes | 2020-04-29 | 2019-09-28 | 2020-04-29 | 2020-04-29 | 2020-06-11 |  | Yes | Shovel Ready |  | 4798184.2 |  |  | 6272666 | 1474481.8 | 368437.3 |  | 4377928 | 51818.9 | 4429746.9 |  |  |  | 61 |  | 35117444 - new order, old was 74022391 6/27 Long to provide update on 6/28 | [7 empty] | Shingletown | Shasta | 40.5069 | -121.8183 | E.5015533.01 |  |  |  | 2020 | Q1 | 2019-08-30 | 2020-02-17 | 2020-03-23 |  | Y | VOLTA 110253130 | 107
35117550 |  |  |  | STS-OFAC_IDLE_REMV-21495 DRY CREEK RD*KS |  |  | FICL |  | 0 | 793 | 793 | 0.15019 | 793 | 0.15019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2020-03-05 | [55 empty] | 0 | 0 | 793 | 0.15019 | 0 | 0 | 0.15019 | 0 | 0.15019 | 0 | 0.15019 | 0 | 0 | 0.15019 |  |  |  |  | N/A | [7 empty] | 2020-04-03 | [29 empty] | 38.7445 | -122.6397
35118170 |  | 2020 |  | BUCOCAMPT 5732 PACHECO LN PARADISE* |  |  | FICL |  | 0 | 157 | 157 | 0.029735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 157 | 0.029735 | 0 | 0 | 0 | 0 | 0.029735 | 0 | 0.031629 | 0 | 0.031629 | 0 | -0.0018939 | 0.031629 |  |  |  |  | N/A | [5 empty] | 2019-10-21 | 2019-10-25 | 2019-10-21 | [29 empty] | 39.7559 | -121.5981 |  |  |  |  | 2019 | [5 empty] | Y
35118171 |  | 2020 |  | BUCOCAMPT 528 BARBARA WAY PARADISE* |  |  | DOCC |  | 0 | 261 | 261 | 0.049432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 261 | 0.049432 | 0 | 0 | 0 | 0 | 0.049432 | 0 | 0.077652 | 0 | 0.077652 | 0 | -0.02822 | 0.077652 |  |  |  |  | N/A | [5 empty] | 2020-01-13 | 2020-01-17 | 2020-01-24 | [29 empty] | 39.7555 | -121.6298 |  |  |  |  | 2019 | [5 empty] | Y
35118663 |  | 2021 |  | BR-01-01-W (E) HEAVENS GATE PARB |  |  | CONS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | BUCOCAMP |  |  |  |  | 2020-09-30 |  |  |  |  | 2020-09-02 | [28 empty] | ERTC issued in 2019 by a different team. ERTC should be invalid and a new intake is required | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | COMP | 2020-04-23 08:00 | 2020-12-08 08:00 | Yes | 2020-10-19 17:00 | 2020-09-18 | [7 empty] | 915291 | 853574.6 | 41246.6 | 1772954.66 | 857663.66 | 66450.4 | 93.25% | 846417.6 | 2423 | 848840.6 | [13 empty] | Paradise | Butte | 39.7794 | -121.6222 | [10 empty] | Y
35119401 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  |  | FICL | 5642 | 0 | 5683 | 5683 | 1.0763 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | 2020-04-06 |  |  | 2019-12-31 | 2019-12-04 | 2019-12-31 |  |  | Yes | 2020-02-19 | 03/31: will require the re-design of 4 pole units 12/04: INTO PEND12/04: Routed pending final approval11/27: ADE advised Ready to route for approval11/25: Final Corrections communicated to ADE11/22: ADE advised ready for approval11/20: Composite Pole change impact - dates to be adjusted11/13: ADE returned 2nd corrections to contractor; 3rd submittal target 11/1411/06: ADE out sick10/30: Check in with ADE10/23: Push - ADE rvw10/16: ADE will work back in with other Camp Evers - priorities were on 2019 reviews10/09 <- 9/04: In Review; CAL to send submittal communication email to [REDACTED] for followup - [REDACTED] requested status update w/ ADE8/27: CAL submitted for 2nd ADE rvw [PRELIM DWG ready]8/21: 2nd ADE corrections submittal targeted for 8/268/14: |  |  |  | Normal | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | May need 1601 permit or redesign - 2/28/2020 - requesting that a pole be relocated to avoid permitting (or date is at risk) | Full |  |  | Yes |  |  | Submitted on 12/13 |  | 2020-11-30 | Y | [11 empty] | 0 | 0 | 5683 | 1.0763 | 0 | 0 | 1.0763 | 0 | 1.0763 | 0 | 1.0763 | 0 | 0 | 1.0763 |  | Keep | 2020-04-06 | Yes | N/A | 2020-03-12 | 2020-05-07 | Yes | 2020-05-07 | 2020-02-20 | 2020-03-10 | 2020-05-11 | 2020-06-15 |  | Yes | Shovel Ready |  | 2134802 |  | 58664.8 | 2570791 | 435989 | 465895.9 |  | 1619172.5 | 49733.6 | 1668906.1 |  |  |  | 41 | [9 empty] | Scotts Valley | Santa Cruz | 37.1013 | -121.979 | E.5015489.01 |  |  |  | 2020 | Q1 | 2019-12-04 | 2020-04-01 | 2020-05-05 |  | Y | CAMP EVERS 21065020 | 46
35119487 |  | 2020 |  | BUCOCAMPT 6486 SHAW CIRCLE MAGALIA* |  |  | CLSD |  | 0 | 582 | 582 | 0.11023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 582 | 0.11023 | 0 | 0 | 0 | 0 | 0.11023 | 0 | 0.23939 | 0 | 0.23939 | 0 | -0.12917 | 0.23939 |  |  |  |  | N/A | [5 empty] | 2019-10-21 | 2019-10-25 | 2019-10-22 | [7 empty] | 58102.96 |  |  |  | 162102 | [17 empty] | 39.8116 | -121.5972 |  |  |  |  | 2019 | [5 empty] | Y
35119600 |  |  |  | STS-OFAC_IDLE_REMV- 1NE/O 24099 DERSCH |  |  | DOCC |  | 0 | 2107 | 2107 | 0.39905 | 0 | 0 | 2107 | 0.39905 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2019-11-14 | [55 empty] | 0 | 0 | 0 | 0 | 2107 | 0.39905 | 0.39905 | 0 | 0.39905 | 0 | 0.39905 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-03-11 | [29 empty] | 40.4714 | -122.1602
35119726 |  | 2020 |  | BUCOCAMPT 1692 YOUNG AVE PARADISE*ILB |  |  | DOCC |  | 0 | 403 | 403 | 0.076326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 403 | 0.076326 | 0 | 0 | 0 | 0 | 0.076326 | 0 | 0.069886 | 0 | 0.069886 | 0 | 0.0064394 | 0.069886 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-10-23 | [29 empty] | 39.7667 | -121.5819 |  |  |  |  | 2019 | [5 empty] | Y
35119965 |  | 2021 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Scoped | PEND | 4325 | 0 | 4483 | 4483 | 0.84905 | 0 | 0 | 4483 | 0.84905 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-06-01 |  | Y | 2019-12-16 |  | 2019-12-16 |  |  | Yes | 2021-02-26 | Routed 12/11/2019 Waiting on [REDACTED] |  |  |  |  | 100 | [6 empty] | Yes |  |  |  | 2020-05-15 | 2020-05-15 |  |  |  |  | Partial | 2020-05-15 | 2020-05-15 | Partial |  |  | ** Caltrans DSDD - Pilot Project - district 5 permit rejected, due date for updated application is 4/12/2020 - PERTC Issued | Partial |  |  | Yes |  |  | [REDACTED] to submit week of 1/6 |  | 2020-06-29 | Y | 2020-06-01 |  |  | Partially Released (non Caltrans ROW) complete outside of Caltrans ROW | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84905 | 0 | 0 | 0.84905 | 0.84905 | 0 | 0 |  | Keep | 2020-04-23 | Yes | N/A | 2020-07-13 | 2021-10-29 17:00 |  | 2021-10-29 17:00 | 2020-05-18 | 2021-06-07 07:00 | 2021-07-15 16:00 |  |  | Yes | Shovel Ready |  | 1435425 | 1273724.9 | 406653.3 | 1924210 | 488785 | 436696.9 | 88.73% | 786477 | 212251.1 | 998728.1 |  | 1500171.1961 |  | 22 |  | Nothing happinging waiting on DSDD | [7 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014534.05 |  |  | 2020-082 | 2020 | Q3 | 2019-12-06 | 2020-05-01 | 2020-05-28 |  | Y | LOS GATOS 1106LB44 | 1864 |  | PRE
35119966 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F |  |  | FICL | 4325 | 0 | 4325 | 4325 | 0.81913 | 4325 | 0.81913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-03-03 17:00 |  |  | 2019-11-22 |  | 2019-11-22 |  |  | Yes | 2019-11-22 | [5 empty] | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | ** Caltrans DSDD - Pilot Project CIF Submitted on 12/3 | Full |  |  | Yes |  |  | N/A |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 4325 | 0.81913 | 0 | 0 | 0.81913 | 0 | 0.81913 | 0 | 0.81913 | 0 | 0 | 0.81913 |  | Keep | 2020-03-03 17:00 | Yes | N/A | 2020-02-14 | 2020-03-10 | Yes | 2020-03-10 | 2020-01-21 | 2020-02-14 | 2020-03-07 | 2020-03-10 |  | Yes | Shovel Ready |  | 1136000 |  |  | 1552000 | 416000 | 284217.1 |  | 811677.3 | 40105.6 | 851782.9 |  |  |  | 18 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5014534.06 |  |  | 2020-083 | 2020 | Q1 | 2019-12-06 | 2020-02-14 | 2020-02-28 |  | Y | LOS GATOS 1106LB44 | 841
35119967 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  |  | UNSE | 4800 | 0 | 4593.6 | 4593.6 | 0.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 10000 |  |  | 10000 | 0 |  |  | 4842.2 | [5 empty] | 18 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014535.05 | TL |  | 2021-137 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35119968 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  |  | UNSE | 2400 | 0 | 2164.8 | 2164.8 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41 |  |  | DA | 08W | SH | 2023-12-25 | [9 empty] | Need GC Review | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 10000 |  |  | 10000 | 0 |  |  | 5680 | [5 empty] | 9 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 0 | 0 | E.5014535.06 | TL |  | 2021-138 | 2022 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35119969 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  |  | MAPP | 6777 | 0 | 6777 | 6777 | 1.2835 | 6777 | 1.2835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-05-01 |  |  | 2019-12-02 |  | 2019-12-02 |  |  | Yes | 2019-12-02 | [5 empty] | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | caltrans due on 1/30/20 | Full |  |  | Yes |  |  | TCP Received - Santa Clara County submitted 12/3 |  | 2020-07-31 | Y | 2020-05-01 |  |  | Additonal work identified by construction | [7 empty] | 0 | 0 | 6777 | 1.2835 | 0 | 0 | 1.2835 | 0 | 1.2835 | 0 | 1.2835 | 0 | 0 | 1.2835 |  | Keep | 2020-03-23 | Yes | N/A | 2020-04-04 | 2020-08-14 | Yes | 2020-08-14 | 2020-01-22 | 2020-11-20 | 2020-11-20 | 2020-11-18 |  | yes | Shovel Ready |  | 2027153 |  | 2392.4 | 2027153 | 0 | 343541 |  | 1662550.7 | 21061.3 | 1683612 |  |  |  | 28 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5015493.02 |  |  | 2020-197 | 2020 | Q2 | 2019-11-27 | 2020-03-01 | 2020-03-21 |  | Y | LOS GATOS 1106LB44 | 841
35119970 |  | 2020 | 220 Mile Plan | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  |  | FICL | 3090 | 0 | 3090 | 3090 | 0.58523 | 3090 | 0.58523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DA | 08W | SH | 2020-03-27 |  |  | 2019-12-03 |  | 2019-12-03 |  |  | Yes | 2019-12-03 | [5 empty] | 100 | [6 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Submitted to county on 12/16 + 60-90 days |  | 2020-06-30 | Y | [11 empty] | 0 | 0 | 3090 | 0.58523 | 0 | 0 | 0.58523 | 0 | 0.58523 | 0 | 0.58523 | 0 | 0 | 0.58523 |  | Keep | 2020-03-27 | Yes | N/A | 2020-02-22 | 2020-08-09 | Yes | 2020-08-09 | 2020-01-20 | 2020-11-20 | 2020-11-20 | 2020-11-19 |  | yes | Shovel Ready |  | 1829999.7 |  |  | 1850000 | 20000.3 |  |  | 1820978.1 | [5 empty] | 19 | [9 empty] | Los Gatos | Santa Clara | 0 | 0 | E.5015493.03 |  |  | 2020-198 | 2020 | Q1 | 2019-11-22 | 2020-06-01 | 2020-06-24 |  | Y | LOS GATOS 1106LB44 | 841
35119972 |  |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  |  | UNSE | 10400 | 8554 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 |  |  | SJ | 08W | SH | 2023-12-25 | [9 empty] | waiting for Field Scoping checklist | [5 empty] | No | [16 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6201 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 100000 |  |  | 500000 | 400000 |  |  | 77962.1 | [5 empty] | 66 |  |  | Complete | Completed by [REDACTED] early 2019 |  |  |  | Remove |  | Los Gatos | Santa Clara | 37.2056 | -122.0478 | E.5015493.01 | ML |  | 2021-143 | 2021 | [5 empty] | Y | LOS GATOS 1106LB44 | 841
35120063 |  | 2020 |  | BUCOCAMPT 1600 CARSON LN PARADISE* |  |  | FICL |  | 0 | 328 | 328 | 0.062121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 328 | 0.062121 | 0 | 0 | 0 | 0 | 0.062121 | 0 | 0.056629 | 0 | 0.056629 | 0 | 0.0054924 | 0.056629 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-18 | [29 empty] | 39.7748 | -121.5866 |  |  |  |  | 2019 | [5 empty] | Y
35120069 |  | 2020 |  | BUCOCAMPT 4569 RIM VIEW DR CHICO* |  |  | CLSD |  | 0 | 1395 | 1395 | 0.2642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1395 | 0.2642 | 0 | 0 | 0 | 0 | 0.2642 | 0 | 0.22045 | 0 | 0.22045 | 0 | 0.04375 | 0.22045 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-01 | [7 empty] | 59948.38 |  |  |  | 204754.7 | [17 empty] | 39.7539 | -121.6833 |  |  |  |  | 2019 | [5 empty] | Y
35120368 |  | 2020 |  | BUCOCAMPT 5021 RUSSEL DR PARADISE* |  |  | CLSD |  | 0 | 362 | 362 | 0.068561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 362 | 0.068561 | 0 | 0 | 0 | 0 | 0.068561 | 0 | 0.1 | 0 | 0.1 | 0 | -0.031439 | 0.1 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-10-14 | [7 empty] | 45363.2 |  |  |  | 158137.3 | [17 empty] | 39.7446 | -121.6528 |  |  |  |  | 2019 | [5 empty] | Y
35120507 |  | 2020 |  | BUCOCAMPT 766 WILLOW ST PARADISE* |  |  | FICL |  | 0 | 960 | 960 | 0.18182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 960 | 0.18182 | 0 | 0 | 0 | 0 | 0.18182 | 0 | 0.025758 | 0 | 0.025758 | 0 | 0.15606 | 0.025758 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-17 | [29 empty] | 39.7574 | -121.6229 |  |  |  |  | 2019 | [5 empty] | Y
35120508 |  | 2020 |  | BUCOCAMPT 14786 COUTOLENC RD MAGALIA* |  |  | CLSD |  | 0 | 290 | 290 | 0.054924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 290 | 0.054924 | 0 | 0 | 0 | 0 | 0.054924 | 0 | 0.090909 | 0 | 0.090909 | 0 | -0.035985 | 0.090909 |  |  |  |  | N/A | [5 empty] | 2019-10-14 | 2019-10-18 | 2019-10-17 | [7 empty] | 49991.48 |  |  |  | 91385.8 | [17 empty] | 39.843 | -121.5704 |  |  |  |  | 2019 | [5 empty] | Y
35120949 |  | 2021 |  | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  |  | DOCC |  | 10150 | 0 | 10150 | 1.9223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-05-11 |  |  |  | 2020-09-30 |  |  |  |  | 2020-11-20 | [12 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | [5 empty] | Y | [11 empty] | 10150 | 1.9223 | 0 | 0 | 0 | 0 | 1.9223 | 0 | 1.9223 | 0 | 1.9223 | 0 | 0 | 1.9223 |  |  | 2020-05-11 | Yes | COMP | 2019-10-14 | 2020-06-26 08:00 | Yes | 2020-06-26 | 2020-11-20 | 2020-04-20 | 2020-06-19 |  |  | yes | Shovel Ready |  | 13429644.2 |  |  | 14251728 | 822083.8 |  |  | 12233229.1 |  |  | -1431.862 | [5 empty] | Complete | [6 empty] | Paradise | Butte | 0 | 0 |  |  |  |  | 2019 | [5 empty] | Y | PARADISE 11032488 | 1123 |  |  |  | 2021-03-04 11:53
35121259 |  | 2020 |  | BUCOCAMPT 6419 DORA LEE LN PARADISE* |  |  | CLSD |  | 0 | 532 | 532 | 0.10076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 532 | 0.10076 | 0 | 0 | 0 | 0 | 0.10076 | 0 | 0.095265 | 0 | 0.095265 | 0 | 0.0054924 | 0.095265 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-11-07 | [7 empty] | 33327.31 |  |  |  | 80542.2 | [17 empty] | 39.7776 | -121.5937 |  |  |  |  | 2019 | [5 empty] | Y
35121380 |  | 2020 |  | BUCOCAMPT 1412 ANDREA LN PARADISE* |  |  | CLSD |  | 0 | 256 | 256 | 0.048485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 256 | 0.048485 | 0 | 0 | 0 | 0 | 0.048485 | 0 | 0.064583 | 0 | 0.064583 | 0 | -0.016098 | 0.064583 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-02 | [7 empty] | 24425.56 |  |  |  | 108589 | [17 empty] | 39.7813 | -121.594 |  |  |  |  | 2019 | [5 empty] | Y
35122641 |  | 2020 | (blank) | BUCOCAMP - CENTERVILLE CNYN TIE LINE RMV |  |  | UNSC |  | 0 | 21995.1 | 21995.1 | 4.1657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 21995.1 | 4.1657 | 0 | 0 | 0 | 0 | 4.1657 | 0 | 4.1657 | 0 | 4.1657 | 0 | -6.8901e-16 | 4.1657 |  |  |  |  | N/A | [35 empty] | Magalia | Butte | 39.7982 | -121.604 |  |  |  |  | 2019
35123182 |  | 2020 |  | BUCOCAMPT 1608 HEMLOCK LN PARADISE* |  |  | FICL |  | 0 | 1137 | 1137 | 0.21534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-09-26 | [55 empty] | 1137 | 0.21534 | 0 | 0 | 0 | 0 | 0.21534 | 0 | 0.071402 | 0 | 0.071402 | 0 | 0.14394 | 0.071402 |  |  |  |  | N/A | [5 empty] | 2019-10-21 | 2019-10-25 | 2019-10-22 | [29 empty] | 39.7531 | -121.5844 |  |  |  |  | 2019 | [5 empty] | Y
35123195 |  | 2020 |  | BUCOCAMPT 686 MARVIN DR PARADISE* |  |  | DOCC |  | 0 | 50 | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-09-13 | [55 empty] | 50 | 0.0094697 | 0 | 0 | 0 | 0 | 0.0094697 | 0 | 0.042045 | 0 | 0.042045 | 0 | -0.032576 | 0.042045 |  |  |  |  | N/A | [5 empty] | 2019-11-12 | 2019-11-15 | 2019-11-16 | [29 empty] | 39.7465 | -121.6266 |  |  |  |  | 2019 | [5 empty] | Y
35123202 |  | 2020 |  | BUCOCAMPT HOG RANCH RD OROVILLE*ILB |  |  | FICL |  | 0 | 884 | 884 | 0.16742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-07 | [55 empty] | 884 | 0.16742 | 0 | 0 | 0 | 0 | 0.16742 | 0 | 0.17727 | 0 | 0.17727 | 0 | -0.0098485 | 0.17727 |  |  |  |  | N/A | [5 empty] | 2019-11-12 | 2019-11-15 | 2019-11-13 | [29 empty] | 39.7872 | -121.5308 |  |  |  |  | 2019 | [5 empty] | Y
35123825 |  | 2020 |  | BUCOCAMPT 1486 MAGADON RD PARADISE* |  |  | FICL |  | 0 | 1379 | 1379 | 0.26117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1379 | 0.26117 | 0 | 0 | 0 | 0 | 0.26117 | 0 | 0.05322 | 0 | 0.05322 | 0 | 0.20795 | 0.05322 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-10-26 | [29 empty] | 39.7418 | -121.5892 |  |  |  |  | 2019 | [5 empty] | Y
35126057 |  | 2020 |  | BUCOCAMPT 643 CIRCLEWOOD DR PARADISE |  |  | FICL |  | 0 | 678 | 678 | 0.12841 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 678 | 0.12841 | 0 | 0 | 0 | 0 | 0.12841 | 0 | 0.4553 | 0 | 0.4553 | 0 | -0.32689 | 0.4553 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-03 | [29 empty] | 39.7444 | -121.6316 |  |  |  |  | 2019 | [5 empty] | Y
35126138 |  | 2020 |  | BUCOCAMPT 1420 PINE CRK WY PARADISE*ILB |  |  | CLSD |  | 0 | 320 | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0.060606 | 0 | 0.093371 | 0 | 0.093371 | 0 | -0.032765 | 0.093371 |  |  |  |  | N/A | [5 empty] | 2019-11-18 | 2019-11-22 | 2019-11-19 | [7 empty] | 23000.82 |  |  |  | 91370.4 | [17 empty] | 39.766 | -121.5936 |  |  |  |  | 2019 | [5 empty] | Y
35126139 |  | 2020 |  | BUCOCAMPT 6562 MILTON DR MAGALIA |  |  | FICL |  | 0 | 1035 | 1035 | 0.19602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1035 | 0.19602 | 0 | 0 | 0 | 0 | 0.19602 | 0 | 0.085227 | 0 | 0.085227 | 0 | 0.1108 | 0.085227 |  |  |  |  | N/A | [5 empty] | 2019-11-18 | 2019-11-22 | 2019-11-18 | [29 empty] | 39.8098 | -121.5925 |  |  |  |  | 2019 | [5 empty] | Y
35126588 |  | 2020 |  | BUCOCAMPT 1652 KINGS ROW PARADISE*ILB |  |  | CLSD |  | 0 | 860 | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-09-30 | [55 empty] | 860 | 0.16288 | 0 | 0 | 0 | 0 | 0.16288 | 0 | 0.047538 | 0 | 0.047538 | 0 | 0.11534 | 0.047538 |  |  |  |  | N/A | [5 empty] | 2019-10-28 | 2019-11-01 | 2019-11-01 | [7 empty] | 49529.11 |  |  |  | 95387.5 | [17 empty] | 39.7727 | -121.5798 |  |  |  |  | 2019 | [5 empty] | Y
35126592 |  | 2020 |  | BUCOCAMPT 6381 CALVIN DR MAGALIA*ILB |  |  | FICL |  | 0 | 229 | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-07 | [55 empty] | 229 | 0.043371 | 0 | 0 | 0 | 0 | 0.043371 | 0 | 0.16155 | 0 | 0.16155 | 0 | -0.11818 | 0.16155 |  |  |  |  | N/A | [5 empty] | 2019-11-12 | 2019-11-15 | 2019-11-16 | [29 empty] | 39.8078 | -121.5998 |  |  |  |  | 2019 | [5 empty] | Y
35126607 |  | 2020 |  | BUCOCAMPT 6904 DEAN PL PARADISE*ILB |  |  | CLSD |  | 0 | 887 | 887 | 0.16799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-09-30 | [55 empty] | 887 | 0.16799 | 0 | 0 | 0 | 0 | 0.16799 | 0 | 0.096591 | 0 | 0.096591 | 0 | 0.071402 | 0.096591 |  |  |  |  | N/A | [5 empty] | 2019-12-02 | 2019-12-06 | 2019-12-05 | [7 empty] | 28871.21 |  |  |  | 67730.1 | [17 empty] | 39.7869 | -121.5704 |  |  |  |  | 2019 | [5 empty] | Y
35126879 |  | 2020 |  | BUCOCAMPT 5771 BONNIE LN PARADISE*ILB |  |  | CLSD |  | 0 | 292 | 292 | 0.055303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-09-30 | [55 empty] | 292 | 0.055303 | 0 | 0 | 0 | 0 | 0.055303 | 0 | 0.07197 | 0 | 0.07197 | 0 | -0.016667 | 0.07197 |  |  |  |  | N/A | [5 empty] | 2019-11-12 | 2019-11-15 | 2019-11-16 | [7 empty] | 27001.43 |  |  |  | 59790.8 | [17 empty] | 39.7558 | -121.5948 |  |  |  |  | 2019 | [5 empty] | Y
35126986 |  | 2020 |  | BUCOCAMPT 6050 MAXWOOD DR PARADISE*ILB |  |  | CLSD |  | 0 | 1121 | 1121 | 0.21231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP | [60 empty] | 1121 | 0.21231 | 0 | 0 | 0 | 0 | 0.21231 | 0 | 0.018182 | 0 | 0.018182 | 0 | 0.19413 | 0.018182 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-11-11 | [7 empty] | 36203.27 |  |  |  | 79051.8 | [17 empty] | 39.7665 | -121.585 |  |  |  |  | 2019 | [5 empty] | Y
35127511 |  | 2020 |  | BUCOCAMPT 5548 NEWLAND RD PARADISE* |  |  | DOCC |  | 0 | 226 | 226 | 0.042803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-11 | [55 empty] | 226 | 0.042803 | 0 | 0 | 0 | 0 | 0.042803 | 0 | 0.36534 | 0 | 0.36534 | 0 | -0.32254 | 0.36534 |  |  |  |  | N/A | [5 empty] | 2019-12-09 | 2019-12-13 | 2019-12-21 | [29 empty] | 39.7493 | -121.6009 |  |  |  |  | 2019 | [5 empty] | Y
35129304 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  |  | ADER | 9428 | 46 | 9382 | 9428 | 1.7856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7856 | 9428 | 1.7856 | NV | 08W | SH | 2022-04-18 17:00 |  |  | 2020-12-31 | 2021-09-30 | 2020-12-31 | 2020-09-11 | 2020-09-11 |  |  | [Composite to Wood - Sept List] 11/10 - 09/23: ADE in rvw; Priority based 09/16: ADE in rvw; priority based 09/11: CAL submitted for 2nd ADE rvw; Conversion Complete 09/09: Conversion On Track 09/02: ADE rtn 1st corrections to CO; EST converting. 09/02: Conversion 1st sub (9/11) soft target 08/26 - 7/15: ADE in rvw - priority based 07/08: ADE Assigned (John J.) 07/01 - 01/22: ADE to be assigned 01/16: CAL submitted for 1st ADE rvw 12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q4- M12 [R2021_115] | R2.2 - ADE Review in Progress |  | Wood | 47 | 0 | [6 empty] | 2021-01-15 | 2021-01-15 | [5 empty] | 2021-01-15 | 2021-01-15 |  |  |  | ** Caltrans DSDD - Waiting for CT Permit. Due 5/30. Can issue PERTC approx 2-4 weeks after EOD - Waiting on Final Drawings for DSDD (still waiting as of 10/12/20). | [8 empty] | 2020-11-06 |  | 2020-10-23 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7856 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-18 17:00 |  | INPR | 2022-07-13 08:00 | 2022-09-28 17:00 |  | 2022-10-28 17:00 |  |  |  |  | 2020-12-25 |  |  |  | 100000 | 105074.4 |  | 100000 | 0 |  | 105.1% | 103435.6 |  |  |  | 58845.2304 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014721.02 |  |  | 2021-115 | 2022 | 2020 Reserve | 2020-08-31 | 2020-11-14 | 2020-12-24 |  | Y | ORO FINO 11022560 | 61
35129305 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  |  | UNSC | 4373 | 0 | 4373 | 4373 | 0.82822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82822 | 2947 | 0.55814 | NV | 08W | SH | 2020-11-23 |  |  | 2020-07-01 | 2020-09-30 | 2020-07-01 | 2020-06-05 | 2020-06-05 |  | 2020-08-07 | 07/01: APPROVED - INTO PEND06/29: routed - ADE unable to concur - correct items06/25: CAL submitted for 4th ADE rvw; ADE rtn 4th corrections to CO - apply and submit for approval06/24: EST target sub (6/26)06/18: ADE rtn 3rd corrections to CO06/17: CAL submitted for 3rd ADE rvw06/10: EST target sub (6/15)06/08: ADE rtn 2nd corrections to CO06/04: CAL submitted for 2nd ADE rvw - [PRELIM DWG - ready]06/03: EST target sub (6/5) - Estimator workload/priorities05/27: On track05/20: EST target sub (5/29)05/14: ADE rtn 1st corrections to CO04/28: ADE assigned ( [REDACTED] )04/20: CAL submitted for 1st ADE rvw [2] QC04/15: QC Rereview/Resubmit01/15: CAL submitted for 1st ADE rvw12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q3- M8 [R56] | COMPLETED |  | Comp | 6 | 17 |  | 2020-07-17 | Yes |  |  |  | 2020-07-03 | 2020-07-03 |  |  |  |  | Full | 2020-07-03 | 2020-07-03 | Full |  |  | CIF Submitted 3/2/2020 - ERTC issued 7/3/2020 | Full |  | 2020-07-14 | Yes |  |  |  |  | 2020-10-05 | Y | 2020-08-26 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82822 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-06 | Yes | NOTN | 2022-04-25 08:00 | 2022-05-06 17:00 |  | 2022-06-07 17:00 | 2020-08-12 |  |  |  | 2020-11-23 | Yes |  |  | 1199614.7 |  |  | 1594611 | 394996.3 | 1103151.1 |  | 184523.9 | -88060.3 | 96463.6 | [6 empty] | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014721.03 | TL |  | 2021-116 | 2021 | 2020 Reserve | 2020-08-31 | 2020-11-14 | 2020-12-10 |  | Y | ORO FINO 11022560 | 61
35129306 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  |  | PEND | 7772 | 0 | 7772 | 7772 | 1.472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.472 | 7124 | 1.3492 | NV | 08W | SH | 2022-04-01 17:00 |  |  | 2020-09-04 | 2020-10-31 | 2020-09-04 | 2020-07-31 | 2020-07-31 |  | 2020-10-28 | 09/04: APPROVED - INTO PEND 09/01: CAL submitted for rvw/approval 08/28: ADE - final corrections communited to CO; apply and route for approval 08/26: To be approved 08/19: Target to apply/route (tbd) 08/16: ADE rtn 2nd corrections to CO; minor finishing tasks; route upon completion 08/12: ADE Suprv out on vace 08/05: pending approval 07/31: CAL routed for approval 07/29: Routing by 7/31 07/22: ADE rtn 1st corrections to CO; apply corrections and route 07/15 - 7/15: ADE in rvw - priority based 07/08: ADE assigned (Carlos) 07/01 - 01/22: ADE to be assigned 01/16: CAL submitted for 1st ADE rvw 12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q3- M9 [R2021_117] | COMPLETED |  | Comp | 10 | 33 |  | 2020-09-21 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-15 | 2020-09-15 | Full |  |  | CIF Submitted 3/31/2020, Can issue ERTC approx 2 weeks after EOD (expected EOD 12/30/2020) | Full |  | 2020-11-20 | [5 empty] | 2020-11-24 |  | 2020-11-09 | 2020-10-26 |  | On hold pending work plan change - 5% complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.472 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-01 17:00 |  | INPR | 2022-08-16 08:00 | 2022-12-30 17:00 |  | 2023-01-27 17:00 | 2020-10-27 | [7 empty] | 300000 | 41030.4 |  | 300000 | 0 |  | 13.67% | 40948.5 |  |  |  | 27874.4869 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014721.04 | TL |  | 2021-117 | 2021 | 2020 Reserve | 2020-08-31 | 2020-11-14 | 2020-12-20 |  | Y | ORO FINO 11022560 | 61
35129307 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  |  | UNSC | 9325 | 0 | 9325 | 9325 | 1.7661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7661 |  |  | NV | 08W | SH | 2020-11-23 |  |  | 2020-07-13 | 2020-09-30 | 2020-07-13 | 2020-06-12 | 2020-06-12 | Yes | 2020-08-12 | 07/13: Approved for rerouting; APPROVED - INTO PEND07/10: CAL submitted updated docs to SAP07/08: ADE request - Please submit the latest version of ALL PE stamped Ocalc files07/07 ADE - was finally able to download the Est and Condwg files from SAP. Please make the attached changes so I can approve the job - EST applied changes, will be routing shortly; ADE final correction provided to CO; 07/01: CAL routed (6/30)06/27: ADE rtn 2nd corrections to CO - minor - apply and route06/24: ADE rvw - priority based06/11: CAL submitted for 2nd ADE rvw - [PRELIM DWG ready]06/10-06/03: EST target sub (6/08); (6/11)05/27: ADE rtn 1st corrections to CO05/07: ADE assigned ( [REDACTED] )04/29: CAL submitted for 1st ADE rvw [2] QC04/15: QC Rereview/Resubmit01/23: CAL submitted for 1st ADE rvw12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q3- M8 [R56] | COMPLETED |  | Comp | 6 | 36 |  |  | Yes |  |  |  | 2020-08-13 | 2020-08-13 |  |  |  |  | Full | 2020-08-11 | 2020-08-11 | Full |  |  | PM requesting 8/6 ERTC date. Veg start is 8/17/20 | Full |  |  | Yes |  |  |  |  | 2020-11-06 | Y | 2020-08-19 | 2020-08-13 |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7661 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-06 | Yes | COMP | 2022-03-25 08:00 | 2022-03-30 17:00 |  | 2022-04-29 17:00 | 2020-08-18 |  |  |  | 2020-11-23 | Yes |  |  | 2548318.6 | 330858.6 |  | 3319922 | 771603.4 | 2121738.4 | 12.98% | 330342.7 | 96237.5 | 426580.2 |  | 187338.7033 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014721.05 | TL |  | 2021-118 | 2021 | 2020 Reserve | 2020-08-31 | 2020-11-14 | 2020-12-24 |  | Y | ORO FINO 11022560 | 61
35129308 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  |  | ESTS | 8778 | 0 | 8778 | 8778 | 1.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6625 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-12-31 | 2020-11-30 | 2020-08-20 | 2020-08-20 |  |  | [Composite to Wood - Sept List]11/10 - 10/28: ADE in rvw; priority based10/23: CAL submitted 3rd corrections for ADE rvw10/21 - 10/14: Est target (10/21)10/12: ADE rtn 2nd corrections to CO10/07 - 09/16: ADE in rvw; priority based09/11: CAL submitted for 2nd ADE rvw [2]; Conversion Complete09/09: Conversion On Track09/02: Conversion 1st sub (9/11) soft target08/26 - 07/29: ADE in rvw - priority based08/20: CAL submitted for 2nd ADE rvw08/19: On Track08/12: EST sub date (8/20)08/11: ADE rtn 1st corrections to CO08/05 - 7/15: ADE in rvw - priority based07/08: ADE assigned ( [REDACTED] )07/01 - 04/29: ADE to be assigned04/22: CAL submitted for 1st ADE rvw [2] QC04/15: QC Rereview/Resubmit01/30: CAL submitted for 1st Rvw12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q4- M11 [R2022(+)_57] | R3.2 - ADE Review in Progress |  | Wood | 47 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-06-14 |  | 2021-05-24 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6625 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-01 17:00 |  | INPR | 2022-07-22 08:00 | 2022-09-21 17:00 |  | 2022-11-22 17:00 | [5 empty] | Yes |  |  | 100000 |  |  | 100000 | 0 |  |  | 54596.2 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014720.02 | TL |  | 2020-057 | 2021 |  | 2020-12-31 | 2021-03-16 |  |  | Y | ORO FINO 11022560 | 61
35129309 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  |  | PEND | 8902 | 0 | 8902 | 8902 | 1.686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.686 |  |  | NV | 08W | SH | 2022-03-24 17:00 |  |  | 2020-08-03 | 2020-12-31 | 2020-08-03 | 2020-07-19 | 2020-07-19 |  | 2020-12-29 | 07/30: APPROVED - INTO PEND07/27: ADE rtn 3rd corrections to CO; apply and route (to Jack Dufrane); EST routed07/26: CAL submitted for 3rd ADE rvw07/22: EST target sub (7/27)07/20: ADE rtn 2nd corrections to CO07/19: CAL submitted for 2nd ADE rvw - [PRELIM DWG ready]07/15: EST target sub (7/17)07/11: ADE rtn 1st corrections to CO07/09: ADE assigned ( [REDACTED] )07/08 - 04/22: ADE to be assigned04/15: QC Rereview/Resubmit03/24: CAL submitted for 1st ADE rvw [2] QC03/18: Push - Mar 23rd - Laptop issue; Has been reassigned 02/27: Flagged COMPOSITE to WOOD [2]02/26: PM pulled into Composite to Wood Change over; EST to advise on Sub date02/21: CAL submitted for 1st ADE rvw02/19: On Track12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q4- M11 [R2022(+)_57] | COMPLETED |  | Wood | 56 | 0 |  | 2020-09-12 | Yes |  |  |  | 2020-09-03 | 2020-09-03 |  |  |  |  | Full | 2020-09-03 | 2020-09-03 | Full |  |  |  | Full |  | 2020-11-20 | Yes |  |  |  |  | 2021-01-18 |  | 2021-01-04 |  |  | 0% - PI complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.686 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-24 17:00 |  | INPR | 2022-07-04 08:00 | 2022-09-09 17:00 |  | 2022-10-11 17:00 | 2020-10-27 |  |  |  |  | Yes |  |  | 100000 | 37742.9 |  | 100000 | 0 |  | 37.74% | 37638.9 |  |  |  | 22386.2629 | [9 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014720.03 | TL |  | 2020-057 | 2021 |  | 2020-12-31 | 2021-03-16 |  |  | Y | ORO FINO 11022560 | 61
35129310 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  |  | PEND | 10718 | 0 | 10110 | 10110 | 1.9148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9148 | 10110 | 1.9148 | NV | 08W | SH | 2022-04-21 17:00 |  |  | 2020-08-24 | 2020-12-31 | 2020-08-24 | 2020-07-31 | 2020-07-31 |  | 2020-11-03 | 08/24: APPROVED - INTO PEND08/19: Status??08/10: EST routed08/05: ADE rtn 2nd corrections to CO - Apply and route07/31: CAL submitted for 2nd ADE rvw 07/29: On Track07/22: EST target sub (7/31)07/20: ADE rtn 1st corrections to CO07/08: ADE assigned ( [REDACTED] DB)07/01 - 04/29: ADE to be assigned04/24: CAL submitted for 1st ADE rvw [2] QC04/15: QC Rereview/Resubmit03/13: CAL submitted for 1st ADE rvw02/27: Flagged COMPOSITE to WOOD [2]02/26: PM pulled into Composite to Wood Change over; EST to advise on Sub date02/19: |  |  |  | 2020 - Q3- M8 [R2022(+)_57] | COMPLETED |  | Wood | 66 | 4 |  | 2020-09-30 | Yes |  |  |  | 2020-10-09 | 2020-10-09 |  |  |  |  | Full | 2020-10-16 | 2020-10-16 | Full |  |  | CIF received | Full |  | 2020-11-20 | [5 empty] | 2020-12-09 |  | 2020-11-24 | 2020-10-26 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9148 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-21 17:00 |  | INPR | 2022-07-18 08:00 | 2022-12-09 17:00 |  | 2023-01-06 17:00 | 2020-10-26 | [7 empty] | 100000 | 44495.7 |  | 100000 | 0 |  | 44.49% | 44362.7 |  |  |  | 23238.1104 | [9 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014720.04 | TL |  | 2020-057 | 2021 |  | 2020-12-31 | 2021-03-16 |  |  | Y | ORO FINO 11022560 | 61
35129311 |  |  |  | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  |  | PEND | 10500 | 0 | 10500 | 10500 | 1.9886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9886 | 13202 | 2.5004 | NV | 08W | SH | 2022-04-28 17:00 |  |  | 2020-08-25 | 2020-12-31 | 2020-08-25 | 2020-08-04 | 2020-08-04 |  | 2020-11-02 | 08/26: Final rvw provided for approval - minor change; APPROVED INTO PEND 08/19 - 08/12: Approval status ?? 08/04: Routed for approval 07/29: EST target sub (8/14) 07/28: ADE rtn 1st corrections to CO 07/22 - 04/08: ADE to be assigned 04/01: CAL submitted for 1st ADE rvw 03/18: Push - Mar 27; Laptop Issue 02/27: Flagged COMPOSITE to WOOD [2] 02/26: PM pulled into Composite to Wood Change over; EST to advise on Sub date 02/19: On Track 1/22: Push - Pulled EST resources for PSPS 12/04: Need assistance with Elec Planner (On Vacation); Weather Impacts (RISK - Rain & Snow) |  |  |  | 2020 - Q3- M8 [R2022(+)_57] | COMPLETED |  | Wood | 94 | 2 |  | 2020-09-23 | Yes |  |  |  | 2020-08-31 | 2020-08-31 |  |  |  |  | Full | 2020-09-29 | 2020-09-29 | Full |  |  | CIF received | Full |  | 2020-11-20 | [5 empty] | 2020-12-22 |  | 2020-12-10 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9886 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-28 17:00 |  | INPR | 2022-06-17 08:00 | 2022-09-23 17:00 |  | 2022-10-25 17:00 | 2020-10-26 | [7 empty] | 100000 | 49253 |  | 1977294.19 | 1877294.19 |  | 49.25% | 49093.2 |  |  |  | 24767.2229 | [9 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014720.05 | TL |  | 2020-057 | 2021 |  | 2020-12-31 | 2021-03-16 |  |  | Y | ORO FINO 11022560 | 61
35129370 |  | 2020 |  | BUCOCAMPT 5784 HOMESTEAD PL PARADISE*ILB |  |  | FICL |  | 0 | 687 | 687 | 0.13011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-11 | [55 empty] | 687 | 0.13011 | 0 | 0 | 0 | 0 | 0.13011 | 0 | 0.041288 | 0 | 0.041288 | 0 | 0.088826 | 0.041288 |  |  |  |  | N/A | [5 empty] | 2019-11-04 | 2019-11-08 | 2019-11-09 | [29 empty] | 39.756 | -121.5804 |  |  |  |  | 2019 | [5 empty] | Y
35129434 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  |  | PEND | 10670 | 0 | 10670 | 10670 | 2.0208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0208 | 10059 | 1.9051 | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2020-10-23 | 2020-10-23 |  | 2020-11-09 | 11/03: Status ?? 10/23: PIKE applied corrections; routed for approval 10/20: ADE rtn 1st rvw to CO; apply corrections and route for approval 10/13 - 10/6: ADE follow-up 09/23: ADE target set (9/26) 09/21 - 07/27: ADE in rvw - priority based 07/21: ADE Assigned (Chris) 07/17: PIKE submitted for 1st ADE rvw 07/14: EST target sub (7/17) 07/07: Risk - Mon sub; stamping/office closure 06/30: EST Target sub (7/8); implementing corrections and holiday 06/23 - 06/16: EST target date (7/02); Estimator hand off 06/09: EST target sub (6/19); Stamping volume 06/02: EST stamping rvw and late changes - Target sub (6/12) 05/26: ON Track 05/12: EST set 1st sub date 05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June. 04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week 03/17 - 03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06]) 02/27: Flagged COMPOSITE to WOOD [2] 02/25: Move from 3/06 to 3/20: Brunswick prioritization 02/11 -On Track |  |  |  | 2020 - Q4- M11 [R2021_104] | EDRS - Pending EDRS approval |  | Wood | 61 | 21 |  |  | Yes | [10 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-03-24 |  | 2021-03-03 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0208 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-19 17:00 |  | INPR | 2022-09-02 08:00 | 2022-11-24 17:00 |  | 2023-01-25 17:00 | [8 empty] | 250000 | 221421.3 |  | 1281508.77 | 1031508.77 |  | 88.56% | 220515.1 |  |  |  | 109569.3031 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014719.02 | MX |  | 2021-104 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129435 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  |  | PEND | 10796 | 0 | 10796 | 10796 | 2.0447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0447 | 10727 | 2.0316 | NV | 08W | SH | 2022-04-07 17:00 |  |  | 2020-10-08 | 2020-11-30 | 2020-10-08 | 2020-08-31 | 2020-08-31 |  | 2020-12-02 | 10/08: APPROVED - INTO PEND10/6: Routed to ADE for Approval09/29: PIKE submitted for 3rd ADE rvw09/21: EST target sub (9/23) - RISK EOD PUSH09/18: ADE rtn 2nd correction to CO09/15 - 09/08: ADE status; Target 9/16 (or EOW)09/01: ADE in rvw - priority based 08/31: PIKE submitted for 2nd ADE rvw08/25: On Track08/18: EST target sub (8/28)08/14: ADE rtn 1st corrections to CO08/11: ADE status ??08/04 - 07/07: ADE in rvw - priority based; ADE advised on track for (8/11)06/17: ADE assigned ( [REDACTED] )06/15: PIKE submitted for 1st ADE rvw06/09: EST target sub (6/12); Stamping volume, halfway through06/02: On Track05/12: EST set 1st sub date05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June.04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week03/17: Applied new Est 1st sub03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06])02/27: Flagged COMPOSITE to WOOD [2]02/11 -On Track |  |  |  | 2020 - Q4- M10 [R2021_105] | COMPLETED |  | Wood | 44 | 23 |  |  | Yes |  |  |  | 2020-11-30 | 2020-11-30 |  |  |  |  | Full | 2020-11-30 | 2020-11-30 | Full |  |  | CIF submitted 10/15. No enviro constraints identified. | Full |  | 2020-11-20 | [5 empty] | 2021-04-12 |  | 2021-03-24 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0447 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-07 17:00 |  | INPR | 2022-07-11 08:00 | 2022-09-22 17:00 |  | 2022-10-24 17:00 | 2020-11-30 | [7 empty] | 250000 | 156946.6 |  | 1701197.29 | 1451197.29 |  | 62.77% | 156675.2 |  |  |  | 76757.8777 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014719.03 | MX |  | 2021-105 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129436 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  |  | PEND | 10179 | 0 | 10179 | 10179 | 1.9278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9278 |  |  | NV | 08W | SH | 2022-04-21 17:00 |  |  | 2020-09-04 | 2020-12-31 | 2020-09-04 | 2020-07-17 | 2020-07-17 |  | 2020-09-04 | 09/04: ADE ready for approval - APPROVED - INTO PEND 09/03: PIKE submitted for 4th ADE rvw 09/01: EST target sub (9/8) 08/31: ADE rtn 3rd corrections to CO 08/25: ADE in rvw; priority based 08/21: PIKE submitted for 3rd ADE rvw 08/18: Complex locations; identified discrepency - conducting another field check. 08/11 EST target sub (8/21) 08/07: ADE rtn 2nd corrections to CO 08/04: ADE in rvw - priority based 07/17: PIKE submitted for 2nd ADE rvw 07/14: On Track 07/07: EST target sub (7/17); clarified application of corrections; restamping 06/30: Target Sub (7/2); ADE/EST working through corrections and high level comments 06/23: EST target sub (??) - TBD 06/22: ADE rtn 1st corrections to CO 06/04: ADE assigned (Terry) 06/02: ADE to be assigned 06/01: PIKE submitted for 1st ADE rvw 05/12: EST set 1st sub date 05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June. 04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week 03/17: Applied new Est 1st sub 03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06]) 02/27: Flagged COMPOSITE to WOOD [2] 02/18 - 02/11 -On Track 12/03: Flding started - Access issue & Sched RISK (Rain/Snow) |  |  |  | 2020 - Q3- M9 [R2021_106] | COMPLETED |  | Wood | 40 | 6 |  | 2020-09-16 | Yes |  |  |  | 2020-10-31 | 2020-10-31 |  |  |  |  | Full | 2020-10-27 | 2020-10-27 | Full |  |  | Minimal constraints - should not impact ERTC date unless poles are designed in waterways… | Full |  | 2020-11-20 | [5 empty] | 2021-04-12 |  | 2021-03-24 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9278 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-21 17:00 |  | INPR | 2022-07-04 08:00 | 2022-09-21 17:00 |  | 2022-10-21 17:00 | [8 empty] | 250000 | 129731.8 |  | 250000 | 0 |  | 51.89% | 129623.8 |  |  |  | 67293.8308 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014719.04 | MX |  | 2021-106 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129437 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  |  | PEND | 10708 | 0 | 10708 | 10708 | 2.028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.028 | 11288 | 2.1379 | NV | 08W | SH | 2022-03-24 17:00 |  |  | 2020-08-11 | 2020-12-31 | 2020-08-11 | 2020-08-07 | 2020-08-07 |  | 2020-10-06 | 08/11: ADE in rvw - EST routed (8/11) - APPROVED INTO PEND 08/07: PIKE submitted for 2nd ADE rvw 08/04 - 07/27: EST working on coordinating with ADE to rvw some correction details; ADE on vaca 07/21: EST target sub (7/31) 07/17: ADE rtn 1st corrections to CO 07/14 - 07/07: ADE in rvw - priority based 06/25: ADE assigned (Joe DB) 06/23: EST target (06/23) - 10 poles left for stamping; OCALC issues 06/16 - 05/19: On Track; PIKE submitted for 1st ADE rvw 05/12: EST set 1st sub date 05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June. 04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week 03/17: Applied new Est 1st sub 03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06]) 02/27: Flagged COMPOSITE to WOOD [2] 02/18 - 02/11 -On Track 12/03: Flding started - Sched RISK (Rain/Snow) |  |  |  | 2020 - Q3- M9 [R2021_107] | COMPLETED |  | Wood | 41 | 14 |  | 2020-09-30 | Yes |  |  |  | 2020-10-02 | 2020-10-02 |  |  |  |  | Full | 2020-10-02 | 2020-10-02 | Full |  |  | CIF Submitted on 8/18/20 | Full |  | 2020-11-20 | [5 empty] | 2021-05-03 |  | 2021-04-12 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.028 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-24 17:00 |  | INPR | 2022-07-04 08:00 | 2022-09-13 17:00 |  | 2022-10-13 17:00 | 2020-10-06 | [7 empty] | 250000 | 118305 |  | 250000 | 0 |  | 47.32% | 118177.5 |  |  |  | 58334.9272 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014719.05 | MX |  | 2021-107 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129438 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  |  | PEND | 9150 | 0 | 9150 | 9150 | 1.733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.733 | 8582 | 1.6254 | NV | 08W | SH | 2022-04-07 17:00 |  |  | 2020-10-10 | 2020-12-31 | 2020-10-10 | 2020-08-21 | 2020-08-21 |  | 2020-10-10 | 10/10: APPROVED - INTO PEND 10/01: PIKE submitted for 3rd ADE rvw 09/29: EST target sub (10/6) ?? - EOD PUSH 09/25: ADE rtn 2nd corrections to CO 09/23: ADE confirmed target sub (9/24) 09/21 - 9/15: ADE in rvw; Sep EOD - EOD PUSH 09/09: EST applied furher corrections to rvw; rdy for 2nd rww 09/08: ADE status ?? 09/01 - 08/25: ADE in rvw; priority based 08/21: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready] 08/18: Est Target Sub (8/26) 08/14: EST/ADE colaborating on corrections 08/11: ADE rtn 1st corrections to CO 08/11 - 08/04: ADE in rvw; priority based 07/21: ADE assigned (ED) 07/20 - 07/14: Target Sub (7/24); Estimator working priority work 07/07 - 06/30: EST target sub (7/15); Stamping 06/23: On Target - RISK; may roll into next week 06/09 - 05/19: On Track 05/12: EST set 1st sub date 05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June. 04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week 03/17: Applied new Est 1st sub 03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06]) 02/27: Flagged COMPOSITE to WOOD [2] 02/11 -On Track |  |  |  | 2020 - Q4- M10 [R2021_109] | COMPLETED |  | Wood | 71 | 37 |  | 2020-10-14 | Yes |  |  |  | 2020-12-03 | 2020-12-03 | [5 empty] | 2021-02-03 | 2021-02-03 |  |  |  | ** Caltrans DSDD. Environmental reviews are complete. |  |  | 2020-11-20 | [5 empty] | 2021-05-03 |  | 2021-04-12 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.733 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-07 17:00 |  | INPR | 2022-07-18 08:00 | 2022-10-10 17:00 |  | 2022-11-09 17:00 | [8 empty] | 250000 | 185662.9 |  | 1182381.93 | 932381.93 |  | 74.26% | 185487.3 |  |  |  | 107136.6243 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014718.02 | MX |  | 2021-109 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129439 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  |  | PEND | 9792 | 0 | 9792 | 9792 | 1.8545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8545 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-09-11 | 2020-12-31 | 2020-09-11 | 2020-09-04 | 2020-09-04 |  | 2020-09-11 | 09/11: APPROVED - INTO PEND09/08: EST target sub (9/11)09/06: ADE rtn 2nd corrections to CO09/04: PIKE submitted for 2nd ADE rvw - [PRELIM DWG ready]09/01 - 08/12: EST targets sub (9/4)08/11: ADE rtn 1st corrections to CO08/04: ADE in rvw; priority based07/21: ADE sssigned ( [REDACTED] )07/17: PIKE submitted for 1st ADE rvw07/14: EST target sub (7/17);Finalizing stamping07/07: EST target sub (7/10); higher priority work06/30: EST target sub (7/6); finalizing stamping/holiday06/23: On Track - Starting Stamping06/09 - 05/19: On Track05/12: |  |  |  | 2020 - Q3- M9 [R2021_110] | COMPLETED |  | Wood | 81 | 1 |  | 2020-09-22 | Yes |  |  |  | 2021-01-15 | 2021-01-15 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | ** (1 Pole) Caltrans DSDD may be required. Environmental reviews in progress pending clarification on pole redesign. (Enviro reports complete based on original design). |  |  | 2020-11-20 | [5 empty] | 2021-05-03 |  | 2021-04-12 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8545 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-24 17:00 |  | INPR | 2022-07-04 08:00 | 2022-09-15 17:00 |  | 2022-10-17 17:00 | [8 empty] | 250000 | 147245.7 |  | 250000 | 0 |  | 58.89% | 147183.5 |  |  |  | 79397.1912 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014718.03 | MX |  | 2021-110 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129600 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  |  | PEND | 6062 | 0 | 6062 | 6062 | 1.1481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1481 | 5799 | 1.0983 | NV | 08W | SH | 2022-03-24 17:00 |  |  | 2020-08-14 | 2020-12-31 | 2020-08-14 | 2020-07-06 | 2020-07-06 |  | 2020-10-27 | 08/14: Ready for approval - need to up RTS - APPROVED INTO PEND08/05: PIKE submitted for 3rd ADE rvw; EST routed08/04: ADE rtn 2nd corrections to CO07/27 - 07/07: ADE in rvw - priority based; *7/21: EST inquiring about status. ADE to provide 2nd rvw (7/21)07/06: PIKE submitted for 2nd ADE rvw06/25: ADE rtn 1st corrections to CO06/09: ADE assigned ( [REDACTED] )06/05: PIKE submitted for 1st ADE rvw05/12: EST set 1st sub date05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June.04/28 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week03/17: Applied new Est 1st sub03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06])02/27: Flagged COMPOSITE to WOOD [2]02/18 - 02/11 -On Track |  |  |  | 2020 - Q3- M9 [R2021_111] | COMPLETED |  | Wood | 55 | 2 |  | 2020-09-16 | Yes |  |  |  | 2020-10-02 | 2020-10-02 |  |  |  |  | Full | 2020-10-02 | 2020-10-02 | Full |  |  | CIF Submitted on 8/18/20 | Full |  | 2020-11-20 | [5 empty] | 2021-05-24 |  | 2021-05-03 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1481 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-24 17:00 |  | INPR | 2022-07-04 08:00 | 2022-08-22 17:00 |  | 2022-09-21 17:00 | 2020-10-26 | [7 empty] | 250000 | 119441.9 |  | 250000 | 0 |  | 47.77% | 119260.5 |  |  |  | 104033.8555 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014718.04 | MX |  | 2021-111 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129601 |  |  |  | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  |  | PEND | 7408 | 0 | 7408 | 7408 | 1.403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.403 | 7829 | 1.4828 | NV | 08W | SH | 2020-11-20 |  |  | 2020-07-07 | 2020-12-31 | 2020-07-07 | 2020-07-02 | 2020-07-02 | Yes | 2020-11-02 | 07/07: Approved for routing - APPROVED - INTO PEND 07/02: PIKE submitted for 2nd ADE rvw 06/29: ADE rtn 1st corrections to CO; pg 6 of 6; 1st rvw complete 06/25: EST submitted corrections for sht 1-2 of 6 06/27 - 06/23: ADE rtn 1st corrections to CO (pgs of 6); 1-2; 3; 4; 5 06/17: ADE assigned to (Scott) 06/16: PIKE submitted for 1st ADE rvw 06/09: EST finishing up; Stampin Volume - minor slip anticipated 05/12: EST set 1st sub date 05/05: Oro Fino 1st sub targets; 2 per week starting EOM May - complete EOM June. 04/28 - 04/21 - 04/14: Addressing higher priority projects feedback; stamping prioritizations - 1st sub target adjustments TBD next week 03/17: Applied new Est 1st sub 03/03: EST to finalize schedule impact and set 1st sub dates (target EOW [03/06]) 02/27: Flagged COMPOSITE to WOOD [2] 02/25: Move from 3/06 to 3/27: Brunswick prioritization 02/11 -On Track 12/03: Flding started - Sched RISK (Rain/Snow) |  |  |  | 2020 - Q4- M11 [R50] | COMPLETED |  | Wood | 44 | 13 |  | 2020-08-07 | Yes | [9 empty] | Full | 2020-08-12 | 2020-08-12 | Full |  |  | CIF Submitted 6/29 | Full |  | 2020-11-20 | [5 empty] | 2020-11-25 |  | 2020-11-05 | 2020-10-26 |  | On hold pending work plan change - 5% complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.403 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-22 | Yes | INPR | 2022-07-04 08:00 | 2022-09-02 17:00 |  | 2022-10-04 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 2503748.3 | 183208.4 |  | 3374618 | 870869.7 |  | 7.31% | 183037.5 |  |  |  | 130580.5011 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014718.05 | TL |  | 2021-112 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 110276008 | 27
35129602 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.2 |  |  | PEND | 5722 | 0 | 5722 | 5722 | 1.0837 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0837 | 6446 | 1.2208 | NV | 08W | SH | 2020-11-09 |  |  | 2020-07-06 | 2020-09-30 | 2020-07-06 | 2020-04-24 | 2020-04-24 | Yes | 2020-09-29 | 07/06: APROVED - INTO PEND07/01: Final corrections communicated to ADE/EST06/30: DS73 & IN03 task not complete; ADE rtn additional corrections; applying final corrections;Rerouting 7/1;06/26: ADE rtn 6th corrections; Upload all Doc.'s- Zip OCalc need to match with the stamp OCalc. Follow up with the Dist. Eng. on approving the CMCS & attach the EDRS approval to SAP06/25: EN submitted for 6th ADE rvw06/23: EST target sub (6/24)06/19: ADE rtn 5th corrections to CO06/09: ADE rvw - Priority based06/02: ADE soft target (6/05)06/01: EN submitted for 5th ADE rvw05/26: ADE rtn 4th corrections to CO05/19: EST submitted for 4th ADE rvw05/19: EST status - should be in, will double check.05/12: EST - with PE for internal rvw/stamping; Target 5/1305/05: EST target sub (5/11)05/04: ADE rtn 3rd corrections to CO05/01: EN submitted for 3rd ADE rvw04/28: ADE rtn 2nd corrections to CO; EST target sub (05/04)04/24: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]04/21: EST status - Target Today 4/2104/14: Firm up sub date (4/20)04/10: ADE rtn 1st corrections to CO04/07: ADE Assigned ( [REDACTED] )01/20: EN submitted for 1st ADE rvw01/17: Push 3 Days - Scope Change, Need to underground a single crossing. 01/07: On Track12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R10] | COMPLETED |  | Wood | 43 | 0 |  | 2020-08-06 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-15 | 2020-09-15 | Full |  |  | Finalized drawings provided | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2020-11-23 |  | 2020-11-09 | 2020-10-07 |  | On hold pending work plan change | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0837 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-10-29 | Yes | INPR | 2022-08-10 08:00 | 2022-09-13 17:00 |  | 2022-12-06 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 4600257 | 2140360.2 |  | 4600257 | 0 |  | 46.52% | 23966.5 |  |  |  | 1975026.539 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.02 | MX | MX | 2021-007 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129603 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.3 |  |  | PEND | 6970 | 0 | 6970 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 |  |  | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-05-06 | 2020-09-30 | 2020-05-06 | 2020-04-17 | 2020-04-17 | Yes | 2020-09-29 | 05/06: APPROVED - INTO PEND 05/06: ADE rtn corrections for final approval to CO - EN applied corrections - routed 05/05: Routed for approval 04/28: EST - JO meeting today; decision on construction walk 04/20: ADE rtn corrections to CO - Ready for routing; under review for Construction walk (to be scheduled) to pick up redlines prior to routing. 04/17: EN submitted for 2nd ADE rvw - [PRELIM DWG ready] 04/14: Firm up sub date (4/21) 04/11: ADE rtn 1st corrections to CO 04/08: ADE assigned (Maria) 02/07: EN submitted for 1st ADE rvw 02/04: On Track 1st sub 01/14 <-- 12/10: In Progress/No Changes to date 12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R10] | COMPLETED |  | Comp | 16 | 45 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-02-02 |  | 2021-01-19 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-10 08:00 | 2022-09-08 08:00 |  | 2022-11-30 17:00 | 2020-09-28 |  |  |  |  | No |  |  | 250000 | 2464090.2 |  | 250000 | 0 |  | 985.6% | 33588.9 |  |  |  | 1866627.8703 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.03 | TL | MX | 2021-008 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129604 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.4 |  |  | PEND | 7682 | 0 | 7682 | 7682 | 1.4549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4549 | 6845 | 1.2964 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-08-06 | 2020-09-30 | 2020-08-06 | 2020-05-04 | 2020-05-04 | Yes | 2020-09-28 | 08/06: APPROVED - INTO PEND08/05: EN submitted for 3rd ADE rvw08/04: ADE rtn corrections Corrections to CO [2]08/03: Approved for routing; routed07/27: EST sub target (7/31); Issue/fixed; stamping backlog07/21: EST sub target (7/24)07/15: ADE rtn 2nd corrections to CO07/07 - 05/05: ADE rvw - priority based05/04: EN submitted for 2nd ADE rvw04/28: EST sub target (05/04)04/23: ADE rtn 1st corrections to CO04/21: ADE in review04/20: EST finalized upload04/16: EST uploaded DO-Fieldnotes; Incompleted per ADE04/15: ADE rejected 1st submittal - DO field notes template not filled out, need information so I can continue review04/14: ADE assigned ( [REDACTED] )04/07 - 02/04: ADE to be assigned01/31: EN submitted for 1st ADE rvw01/28: On Track01/14 <-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M8 [R2021_9] | COMPLETED |  | Comp | 0 | 47 |  | 2020-09-16 | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-08-31 | 2020-08-31 | Full |  |  | CIF Submitted; Slight delay in ERTC due to tribal consultation | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-01-18 |  | 2021-01-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4549 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-10 08:00 | 2022-09-22 17:00 |  | 2022-12-15 17:00 | 2020-09-28 | [7 empty] | 250000 | 2365220.3 |  | 250000 | 0 |  | 946.1% | 24206.2 |  |  |  | 1625665.6058 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.04 | MX | MX | 2021-009 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129605 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.5 |  |  | PEND | 8342 | 0 | 8342 | 8342 | 1.5799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5799 | 7525 | 1.4252 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-08-06 | 2020-09-30 | 2020-08-06 | 2020-05-08 | 2020-05-08 | Yes | 2020-09-29 | 08/06: APPROVED - INTO PEND08/04: ADE in rvw; Target sub (8/10);{AUG EOD}08/03: EN submitted for 3rd ADE rvw07/27: EST sub target (7/31); Issue/fixed; stamping backlog07/21: EST sub target (7/24)07/15: ADE rtn 2nd corrections to CO07/08 - 05/12: ADE rvw - priority based05/08: EN submitted for 2nd ADE rvw05/05: EST target sub (05/08)04/28: ADE rtn 1st corrections to CO04/21: EST Status - sub date - EST to check on information correction; EST updated fieldnotes and uploaded to SAP (resubmitted)04/15: ADE Rejected 1st submittal - DO field notes template not filled out, need information so I can continue review.Also OU conductor sizes and service spans not included in field notes 04/15: ADE assigned ( [REDACTED] )04/8 - 02/18: ADE to be assigned02/14: EN submitted for 1st ADE rvw02/11 - 02/04: On Track 1st sub01/14 <-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M8 [R2021_11] | COMPLETED |  | Comp | 0 | 46 |  | 2020-09-28 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-09-04 | 2020-09-04 | Full |  |  | Finalized drawings provided | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-03-03 |  | 2021-02-17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5799 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-19 08:00 | 2022-10-04 17:00 |  | 2022-10-05 08:00 | 2020-09-28 | [7 empty] | 250000 | 2610377.3 |  | 250000 | 0 |  | 1044% | 23343.2 |  |  |  | 1652216.7519 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.05 | TL | OH | 2021-011 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129606 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.6 |  |  | PEND | 5223 | 0 | 5223 | 5223 | 0.9892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9892 |  |  | NV | 08W | SH | 2022-08-11 17:00 |  |  | 2020-07-24 | 2020-09-30 | 2020-07-24 | 2020-06-10 | 2020-06-10 | Yes | 2020-11-02 | ADE rvw - priority based06/10: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]06/09: EST On Track06/02: EST target sub (6/15)05/28: ADE rtn 1st corrections to CO05/19 - 05/05: ADE rvw - priority based04/28 - 04/21: with ADE04/15: ADE assigned ( [REDACTED] )04/07- 01/16: ADE to be assigned01/09: EN submitted for 1st ADE rvw01/07: On Track12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R10] | R2.2 - ADE Review in Progress |  | Comp | 11 | 31 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-04 | 2020-09-04 | Full |  |  |  | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-01-04 |  | 2020-12-11 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9892 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-11 17:00 |  | INPR | 2022-08-24 08:00 | 2022-10-04 17:00 |  | 2022-12-27 17:00 | 2020-09-28 | [7 empty] | 250000 | 1796235.9 |  | 250000 | 0 |  | 718.5% | 28266.7 |  |  |  | 1815838.7042 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.06 | MX | OH | 2021-010 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129607 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 1.7 |  |  | PEND | 7972 | 0 | 7972 | 7972 | 1.5098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5098 |  |  | NV | 08W | SH | 2021-12-02 08:00 |  |  | 2020-08-14 | 2020-10-31 | 2020-08-14 | 2020-05-01 | 2020-05-01 | Yes | 2020-10-14 | 08/14: ADE approved for routing -APPROVED INTO PEND08/11: ADE ( [REDACTED] ) working with pole support team to resolve issue {AUG EOD}08/04 - 07/27: EST - waiting on pole loading for corrections (SAP poles don't match design/ estimator cannot delete, |  |  |  | 2020 - Q3- M8 [R2021_12] | COMPLETED |  | Wood | 54 | 0 |  | 2020-09-15 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-08-20 | 2020-08-20 | Full |  |  | Released 8/20 | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-04-23 |  | 2021-04-02 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5098 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-02 08:00 |  | INPR | 2022-05-31 08:00 | 2022-07-07 17:00 |  | 2022-09-29 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 250000 | 2934684.9 |  | 250000 | 0 |  | 1174% | 23706.2 |  |  |  | 1943694.9664 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014748.07 | TL | OH | 2021-012 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129608 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 2.2 |  |  | PEND | 7812 | 0 | 7762 | 7762 | 1.4701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4701 |  |  | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-09-28 | 2020-10-31 | 2020-09-28 | 2020-08-21 | 2020-08-21 |  | 2020-12-03 | 09/28: Approved for routing; Updated/routed; APPROVED - INTO PEND09/25: EN submitted for 4th ADE rvw09/22: EST target sub (9/24); PLC audit tool driving the changes.09/15: Upload completed Saturday; ADE rtn 3rd corrections to CO09/12: EN submitted for 3rd ADE rvw; SAP upload error09/08: On Track09/01: EST target sub (09/11)08/25: ADE rtn 2nd corrections CO08/21: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]08/18 - 08/04: On Track07/27: Change order in today; EST Sub Date (8/21)07/21: EST target sub (TBD); Redline - ADE requesting new Standards. EST to submit Change Order and Sched Impact. Will firm up sub date07/16: ADE rtn 1st corrections to CO07/13: ADE assigned ( [REDACTED] )07/07 - 03/24: ADE to be assigned03/20: EN submitted for 1st ADE rvw03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/04<-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R2021_14] | COMPLETED |  | Wood | 53 | 16 |  | 2020-10-05 | Yes |  |  |  | 2020-11-12 | 2020-11-12 |  |  |  |  | Full | 2020-11-12 | 2020-11-12 | Full |  |  | CIF submitted 9/28/20. No enviro constraints identified. | Full |  | 2020-10-26 | Yes | 2021-12-31 |  |  |  | 2021-05-13 |  | 2021-04-23 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4701 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-09 08:00 | 2022-08-19 17:00 |  | 2022-11-11 17:00 | 2020-11-10 | [7 empty] | 333333 | 2742731.3 |  | 333333 | 0 |  | 822.8% | 37350.5 |  |  |  | 1865707.4548 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.02 | ML | OH | 2021-014 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129609 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 2.3 |  |  | PEND | 5626 | 0 | 5626 | 5626 | 1.0655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0655 |  |  | NV | 08W | SH | 2020-10-28 |  |  | 2020-06-03 | 2020-10-31 | 2020-06-03 | 2020-05-27 | 2020-05-27 | Yes | 2020-09-29 | 06/05: APPROVED - INTO PEND06/03: Final corrections rtn to CO06/02: EST target sub (6/5) - to be routed05/29: ADE rtn 2nd corrections to CO - ready to be routed05/27: EN submitted for 2nd ADE rvw05/26: EST status 5/27 (Holiday)05/19: EST target sub (5/25)05/19: ADE rtn 1st corrections to CO04/29: ADE assigned ( [REDACTED] DB)04/28 - 04/07: ADE to be assigned04/04: EN submitted for 1st ADE rvw03/24 - 03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/04<-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R11] | COMPLETED |  | Wood | 44 | 19 |  | 2020-08-10 | Yes |  |  |  | 2020-08-03 | 2020-08-03 |  |  |  |  | Full | 2020-08-03 | 2020-08-03 | Full |  |  | CIF Submitted | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2020-12-04 |  | 2020-10-28 | 2020-10-07 |  | 92% complete as of 12/1 - will complete on 12/4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0655 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-10-09 | Yes | INPR | 2022-08-16 08:00 | 2022-09-16 17:00 |  | 2022-12-09 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 333333 | 1686214.2 |  | 333333 | 0 |  | 505.9% | 85060.8 |  |  |  | 1582511.727 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.03 | MX | OH | 2021-015 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129610 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 2.4 |  |  | PEND | 8284 | 0 | 8284 | 8284 | 1.5689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5689 | 8176 | 1.5485 | NV | 08W | SH | 2022-08-01 17:00 |  |  | 2020-10-28 | 2020-10-31 | 2020-10-28 | 2020-06-29 | 2020-06-29 | Yes | 2020-10-28 | 10/28: APPROVED - INTO PEND10/27: ADE ready (10/26); DS 73 done; EST communicating with ADE to finalize10/23: ADE anticipates minimal corrections; EST begin upload,Planner needs to complete DS73; will be ready for rvw10/22: EN submitted corrections for 4th ADE rvw10/20: EST target sub (10/22)10/15: ADE rtn 3rd corrections to CO10/14: ADE target subm 10/14-1510/6: ADE Follow-up, EN submitted for 3rd ADE rvw on 9/2909/29: Routed last night; however EES issues - submitting ticket09/21 - 09/22: EST target sub (9/25) - EOD PUSH (1st wk OCT, 10/2)09/20: ADE rtn 2nd correction to CO09/15 - 09/08: ADE status; working now - target EOW (9/18) 09/01 - 06/30: ADE rvw - priority based06/29: EN submitted for 2nd ADE rvw06/26: Scope Change - Chg Ordr submitted06/23: EST target sub (06/29)06/15: ADE rtn 1st rvw corrections to CO06/09 - 04/28: ADE rvw - priority based04/20: ADE assigned ( [REDACTED] )04/14 - 3/17: ADE to be assigned03/13: EN submitted for 1st ADE rvw03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/04<-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q4- M10 [R2021_16] | COMPLETED |  | Wood | 59 | 2 |  | 2020-11-06 | Yes |  |  |  | 2020-11-16 | 2020-11-16 |  |  |  |  | Full | 2020-11-25 | 2020-11-25 | Full |  |  | Prelim reviews are complete. Received final drawings 11/4/20 but need list of changes made. | Full | [7 empty] | 2021-05-13 |  | 2021-06-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5689 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-01 17:00 |  | INPR | 2022-08-16 08:00 | 2022-09-29 17:00 |  | 2022-12-22 17:00 | [8 empty] | 333333 | 2816756.3 |  | 333333 | 0 |  | 845% | 46864.4 |  |  |  | 1795325.1164 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.04 | MX | OH | 2021-016 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129611 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 2.5 |  |  | PEND | 6878 | 0 | 6878 | 6878 | 1.3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3027 |  |  | NV | 08W | SH | 2022-08-11 17:00 |  |  | 2020-08-10 | 2020-10-31 | 2020-08-10 | 2020-05-19 | 2020-05-19 | Yes | 2020-10-13 | 08/10: APPROVED - INTO PEND08/05: EST ready for routing; trouble uploadding08/04: ADE rtn 5th corrections to CO; EST coordinating with ADE; EST routing07/29: EN submitted for 5th ADE rvw07/27: EST sub target (7/31); stamping backlog07/21: EST target sub (7/24); ready to be submitted07/15: ADE rtn 4th corrections to CO07/08: EN submitted for 4th ADE rvw07/01: ADE rtn 3rd corrections to CO06/30: ADE rvw - priority based06/26: Scope Change - Chg Ordr submitted06/25: EN submitted for 3rd ADE rvw6/23 - 06/16: EST target sub (06/19); (6/26, Some design changes needed06/14: ADE rtn 2nd corrections to CO06/09 - 05/26: ADE rvw - priority based05/19: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]05/12: EST Target 2 sub (5/15)04/28: ADE rtn 1st corrections to CO04/20: ADE assigned ( [REDACTED] )04/14 - 04/04: ADE to be assigned03/31: EN submitted for 1st ADE rvw03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/04<-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M8 [R2021_17] | COMPLETED |  | Wood | 45 | 5 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-15 | 2020-09-15 | Full |  |  | Finalized drawings provided | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2020-12-11 |  | 2020-11-23 | 2020-10-07 |  | [REDACTED] to schedule ERTC Call | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3027 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-11 17:00 |  | INPR | 2022-08-24 08:00 | 2022-10-05 17:00 |  | 2022-12-28 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 333333 | 2318032.6 |  | 333333 | 0 |  | 695.4% | 36175.9 |  |  |  | 1779472.5397 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.05 | TL | OH | 2021-017 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129612 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 2.6 |  |  | PEND | 5997 | 0 | 5997 | 5997 | 1.1358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1358 |  |  | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-07-17 | 2020-10-31 | 2020-07-17 | 2020-06-01 | 2020-06-01 | Yes | 2020-09-29 | 07/17: APPROVED - INTO PEND07/14: EN target sub (7/17)07/13: EN submitted for 5th ADE corrections; ADE rtn 5th corrections to CO07/10: ADE rtn 4th corrections to CO07/09: EN submitted for 4th ADE rvw07/06: ADE rtn 3rd corrections to CO07/01: EN submitted for 3rd ADE rvw06/30: On Track06/23: EST target sub (6/30)06/22: ADE rtn 2nd corrections to CO06/09: ADE rvw - priority based06/02: ADE soft target (6/8) - priority lower06/01: EN submitted for 2nd ADE rvw - [PRELIM DWG ready]05/26: EST target sub (6/1)05/20: ADE rtn 1st corrections to CO05/19: ADE rvw - priority based05/12: ADE assigned ( [REDACTED] )04/28: ADE to be assigned04/07: EN submitted for 1st ADE rvw07/01: EN submitted for 3rd ADE rvw03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/04<-- 12/10: In Progress/No Changes to date12/03: Flding to Start next week (Mon 9th) - Sched RISK (rain/snow impacts anticipated) |  |  |  | 2020 - Q3- M9 [R11] | COMPLETED |  | Wood | 74 | 0 |  | 2020-08-11 | Yes |  |  |  | 2020-08-03 | 2020-08-03 |  |  |  |  | Full | 2020-08-03 | 2020-08-03 | Full |  |  |  | Full |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2020-12-19 |  | 2020-11-24 | 2020-10-07 |  | [REDACTED] to schedule ERTC Call | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1358 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-27 17:00 |  | 2022-12-20 17:00 | 2020-09-28 |  |  |  |  | Yes |  |  | 333333 | 1866858.5 |  | 333333 | 0 |  | 560.1% | 35376.6 |  |  |  | 1643657.3087 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014747.06 | TL | OH | 2021-018 | 2021 |  | 2020-09-30 | 2020-12-14 |  |  | Y | ORO FINO 1101CB | 3
35129613 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 3.2 |  |  | PEND | 7303 | 0 | 7303 | 7303 | 1.3831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3831 |  |  | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-09-17 | 2020-10-31 | 2020-09-17 | 2020-09-05 | 2020-09-05 |  | 2020-10-26 | 09/17: APPROVED - INTO PEND09/16: ADE Target sub (9/21)09/16: BCF submitted for 3rd ADE rvw09/15: EST target sub (9/17)09/10: ADE rtn 2nd corrections to CO09/08: ADE in rvw; priority based09/05: BCF submitted for 2nd ADE rvw09/01 - 08/25: Est target sub (9/4)08/18- 08/04: EST target sub (08/28)08/03: ADE rtn 1st corrections to CO07/21 - 07/14: ADE in rvw - priority based07/10: BCF submitted for 1st ADE rvw [2] - resub/numbering07/07 - 06/30: EST target resub (7/10)06/23 - 06/12: ADE request some fixes before Rvw can begin; primarily renumbering [rejected]06/09 - 05/26: ADE rvw - priority based05/21 - ADE assigned ( [REDACTED] )5/14 - 04/04: ADE to be assigned03/27: BCF submitted for 1st ADE rvw03/24 - 03/10: EST No impact/ On Track; Low Risk w/ Transition to Offsite work method ??03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/11 - 02/04: No changes at this time; Low RISK for adjustments01/07: BCF to profide 1st sub FC update - Brunswick move up in priority12/17: BCF finalizing new 1st submittal dates.12/10: Reprioritizing to Brunswick12/06: BCF 1st ADE Submittal target set 1/3011-26 <-- 11/19: In Rvw for WST 1st submittal target date; Soft target - Jan Submittal |  |  |  | 2020 - Q3- M9 [R2021_20] | COMPLETED |  | Wood | 47 | 5 |  |  | Yes |  |  |  | 2020-11-02 | 2020-11-02 |  |  |  |  | Full | 2020-11-02 | 2020-11-02 | Full |  |  | No enviro constraints identified | Full |  | 2020-11-20 | [5 empty] | 2021-02-16 |  | 2021-02-02 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3831 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-28 17:00 |  | 2022-12-21 17:00 | 2020-10-26 | [7 empty] | 125000 | 2131663.7 |  | 250000 | 125000 |  | 1705% | 41091.3 |  |  |  | 1541172.7148 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014746.02 | MX | MX | 2021-020 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 1101CB | 3
35129614 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 3.3 |  |  | PEND | 8896 | 0 | 8896 | 8896 | 1.6848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6848 | 9276 | 1.7568 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-09-03 | 2020-10-31 | 2020-09-03 | 2020-07-24 | 2020-07-24 |  | 2020-10-27 | 09/03: APPROVED - INTO PEND09/01 - 08/25: ADE in rvw; priority based08/21: BCF submitted for 3rd ADE rvw08/18 - 08/04: EST target sub (08/21)08/03: ADE rtn 2nd corrections to CO07/24: BCF submitted for 2nd ADE rvw07/21: REVISION - Impact (7/24)07/16: Change Order - request to remove AWAC secondary07/14 - 06/30: EST target sub (07/17)06/24: ADE rtn 1st correctionst to CO06/23 - 05/26: ADE rvw - priority based05/26: ADE assigned ( [REDACTED] DB)05/19 - 04/04: ADE to be assigned03/24 - 03/10: EST No impact/ On Track ??04/03: BCF submitted for 1st ADR rvw03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/11 - 02/04: No changes at this time; Low RISK for adjustments01/07: BCF to profide 1st sub FC update - Brunswick move up in priority12/17: BCF finalizing new 1st submittal dates.12/10: Reprioritizing to Brunswick12/06: BCF 1st ADE Submittal target set 2/1111-26 <-- 11/19: In Rvw for WST 1st submittal target date; Soft target - Jan Submittal |  |  |  | 2020 - Q3- M9 [R2021_21] | COMPLETED |  | Wood | 75 | 4 |  | 2020-09-16 | Yes |  |  |  | 2020-10-31 | 2020-10-31 |  |  |  |  | Full | 2020-10-26 | 2020-10-26 | Full |  |  | No constraints identified | Full |  | 2020-10-26 | Yes |  |  |  |  | 2021-03-17 |  | 2021-03-03 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6848 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-29 17:00 |  | 2022-12-22 17:00 | 2020-10-27 | [7 empty] | 250000 | 3277096.9 |  | 250000 | 0 |  | 1311% | 44709.9 |  |  |  | 1945039.527 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014746.03 | MX | OH | 2021-021 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 1101CB | 3
35129615 |  |  |  | CWSP - ORO FINO 1101 - OCB PH 3.4 |  |  | PEND | 10990 | 0 | 10990 | 10990 | 2.0814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0814 | 10907 | 2.0657 | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-02 | 2020-10-31 | 2020-11-02 | 2020-10-09 | 2020-10-09 |  | 2020-11-02 | 11/02: APPROVED - INTO PEND10/29: BFC submitted final corrections - routed for approval10/28: ADE approved for routing; in final rvw - 30+ items surfaced. EOD @ RISK10/27: BCF submitted corrections for 4th ADE rvw10/22: ADE rtn 3rd rvw to CO10/21: EST submitted corrections for 3rd ADE rvw10/20: EST sub (10/20) - today10/14: EST target sub (10/18)10/13: ADE rtn 2nd corrections to CO10/09: BCF submitted for 2nd ADE rvw10/06: EST Submittal by 10/9.10/02: ADE rtn 1st corrections to CO; PMGR request to move up in schedule (OCT EOD); EST confirmed Target sub (10/09)- minor corrections.09/28: ADE RD in rvw09/23: BCF submitted for 1st ADE rvw [2]; Redesign changes09/21: EST sub (9/23); Concentrated on completing another priority job09/15 - 09/01: EST sub (9/18); Adjust for Comp/Wood Priority shift08/18 - 08/11: EST - in conversion; Target sub (9/11)07/14 - 07/02: [Revision] design revisions for 87 poles in order to eliminate AWAC secondary and provide poles / transformers to serve customers as necessary06/30: EST will be resubmitting - Design Change; Secondary Removal of Existing AWAC, submitting Chng Ordr - Refielding required for changes - New sub date TBD 06/23 - 05/26: ADE rvw - priority based; ADE sub EOW target; Thursday 6/25 to discuss the best possible path forward in designing the 4th segment of Oro Fino. 05/29: ADE assigned ( [REDACTED] )05/26 - 04/21: ADE to be assigned04/17: BCF submitted for 1st ADE rvw04/14 - 04/04: On Track03/24 - 03/10: EST No impact/ On Track ??03/03: EST to review impact and sched 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/11 - 02/04: No changes at this time; Low RISK for adjustments01/07 |  |  |  | 2020 - Q4- M11 [R2021_22] | COMPLETED |  | Wood | 121 | 0 |  | 2020-11-06 | Yes |  |  |  | 2020-12-18 | 2020-12-18 |  |  |  |  | Full | 2023-12-25 | 2023-12-25 |  |  |  | Design changes requested on 10/7. Waiting on revisions. No environmental constraints identified. | [8 empty] | 2021-06-04 |  | 2021-05-13 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0814 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-01 17:00 |  | INPR | 2022-08-16 08:00 | 2022-10-03 17:00 |  | 2022-12-26 17:00 | [5 empty] | Yes |  |  | 250000 | 4051228.2 |  | 125000 | -125000 |  | 1620% | 89672.2 |  |  |  | 1946358.9532 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014746.04 | TL | MX | 2021-022 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 1101CB | 3
35129616 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  |  | PEND | 8577 | 0 | 8577 | 8577 | 1.6244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6244 |  |  | NV | 08W | SH | 2021-12-22 17:00 |  |  | 2020-08-13 | 2021-09-30 | 2020-08-13 | 2020-08-05 | 2020-08-05 |  | 2020-10-28 | 08/13: APPROVED INTO PEND08/12: QUES routed; Final rvw corrections communicated to ADE; ADE to apply and route.08/10: QUES upload corrections to SAP08/09: ADE rtn 2nd corrections to CO; upload final correction to SAP08/05 QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]xx/xx - 07/29: On Track07/22: EST target sub (8/7)07/20: ADE rtn 1st corrections to CO07/15 - 07/08: ADE in rvw - priority based06/24: ADE in rvw - soft target (7/10)06/19: ADE assigned ( [REDACTED] )06/17 - 05/06: ADE to be assigned04/14: QUES submitted for 1st ADE rvw04/08 - 04/01: EST On Track (4/10)3/23 - 03/11: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/26: On Track; Low risk of push (stamping/Brunswick priority)02/12: (Tree Attachment Impact) Adding additional clearance and secondary poles01/08: No Change12/30: communication - MSO switch to SCADAMATE switch.12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M12 [R2022(+)_13] | COMPLETED |  | Wood | 49 | 6 |  |  | Yes |  |  |  | 2020-08-20 | 2020-08-20 |  |  |  |  | Full | 2020-09-24 | 2020-09-24 | Full |  |  |  | Full |  | 2020-11-20 | [5 empty] | 2021-08-27 |  | 2021-08-06 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6244 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-01-27 08:00 | 2022-05-18 17:00 |  | 2022-07-19 17:00 | 2020-10-27 | [7 empty] | 262500 | 2627069 |  | 262500 | 0 |  | 1001% | 45062.3 |  |  |  | 1617223.3088 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.02 | MX | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129617 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  |  | PEND | 10289 | 0 | 10289 | 10289 | 1.9487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9487 | 10060 | 1.9053 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-09-03 | 2021-09-30 | 2020-09-03 | 2020-08-25 | 2020-08-25 |  | 2020-10-28 | 09/03: APPROVED - INTO PEND09/02: ADE working final rvws08/25: QUES routed for approval08/19: EST - Waiting on Land; Getting GC cost08/13: ADE rtn 1st corrections to CO08/12 - 07/22: ADE in rvw - priority based07/16: ADE assigned ( [REDACTED] DB)07/15 - 05/06: ADE to be assigned03/24: QUES submitted for 1st ADE rvw03/11: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/26: On Track; Low risk of push (stamping/Brunswick priority)02/12: (Tree Attachment Impact) Adding additional clearance and secondary poles12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q3- M9 [R2022(+)_13] | COMPLETED |  | Wood | 98 | 11 |  | 2020-09-18 | Yes |  |  |  | 2020-09-08 | 2020-09-08 |  |  |  |  | Full | 2020-09-09 | 2020-09-09 | Full |  |  | CIF submitted | Full |  | 2020-11-20 | [5 empty] | 2021-08-27 |  | 2021-08-06 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9487 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-11 08:00 | 2022-09-13 17:00 |  | 2022-11-14 17:00 | 2020-10-27 | [7 empty] | 262500 | 3816770.3 |  | 262500 | 0 |  | 1454% | 110179.1 |  |  |  | 1958649.7409 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.03 | TL | MX | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129618 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  |  | PEND | 10520 | 0 | 10520 | 10520 | 1.9924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9924 |  |  | NV | 08W | SH | 2021-12-15 17:00 |  |  | 2020-10-20 | 2021-09-30 | 2020-10-20 | 2020-09-06 | 2020-09-06 |  | 2020-11-14 | 10/20: In final rvw; APPROVED - INTO PEND 10/19: Ready for approval 10/15: ADE rtn 3rd corrections to CO - apply and route 10/14: ADE target (10/16); ADE shifting to PM, in effort to meet target date 10/08: QUES submitted for 3rd ADE rvw 10/7: Submittal by 10/9 09/30 - 09/23: Conversion 1st sub (10/09): EST bandwith (08W, 08J, Training new hire) 09/17: ADE rtn 2nd corrections to CO; Estimator to rtn to office on Monday; Fielding new 08W work 09/16: ADE status - Target sub (9/17); will require corrections 09/08: QUES (routed) - submitted for 2nd ADE rvw 09/02 - 08/05: EST target sub (9/11); w/ redesign 07/28: ADE rtn 1st corrections to CO; EST to redesign to new standards 07/22 - 06/24: ADE in rvw - priority based 06/17: ADE assigned (Donald) - Pole Type check/discussion 07/01 - 05/06: ADE to be assigned 03/31: QUES submitted for 1st ADE rvw 03/25: EST on Track (3/25)?? 03/23: Assigned new 1st sub 03/11: Assigned new 1st sub (4/3) 02/27: Flagged COMPOSITE to WOOD [2] 02/12: Estimating on Track - RISK Stamping push; Change Order - Phase change 12/18: EST spread 1st submittal dates 12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/Resistence Scoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M10 [R2022(+)_13] | COMPLETED |  | Wood | 78 | 0 | [12 empty] | Full | 2020-11-13 | 2020-11-13 | Full |  |  | No enviro constraints identified. | Full | [7 empty] | 2021-07-16 |  | 2021-06-25 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9924 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-15 17:00 |  | INPR | 2022-01-20 08:00 | 2022-04-14 17:00 |  | 2022-05-16 17:00 | 2020-11-13 |  |  |  |  | Yes |  |  | 262500 | 3880904.6 |  | 262500 | 0 |  | 1478% | 94454.3 |  |  |  | 1947830.4456 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.04 | MX | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129619 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  |  | PEND | 8750 | 0 | 8750 | 8750 | 1.6572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6572 |  |  | NV | 08W | SH | 2021-12-22 17:00 |  |  | 2020-09-11 | 2021-09-30 | 2020-09-11 | 2020-08-14 | 2020-08-14 |  | 2020-10-27 | 09/11: APPROVED - INTO PEND09/02: ADE in rvw; priority based08/31: QUES submitted for 3rd ADE rvw08/26 - 08/19: EST target sub (8/31); Change order submitted and approved - applying new standards (recalc loc/redesign and remap)08/17: ADE rtn 2nd corrections to CO08/14: EST/ADE working through some details for corrections; QUES sumitted for 2nd ADE rvw - [PRELIM DWG ready]08/13: ADE rtn 1st corrections to CO08/12- 07/29: ADE in rvw; priority based07/22: EST submitted for 1st ADE rvw [2]; redesign request completed07/08 - 06/24: Change Orders in progress - pull arial cable or leave in.Schedule Impact - EST TBD resubmittal target date; waiting on approval of redesign06/22: EST - proposed design, 3 items flagged for ADE input to proceed with design changes.06/19: ADE rtn to CO: Design Change required - no longer installing aerial cable. Install transformers instead. Only use AC for a midspan service unless it can go on a span guy.06/19: ADE assigned [REDACTED] 06/17 - 05/06: ADE to be assigned04/10: QUES submitted for 1st ADE rvw04/08: On Track - in stamping03/23: Assigned new 1st sub03/11: Assigned new 1st sub (4/6)02/27: Flagged COMPOSITE to WOOD [2]02/26: In stamping (2 day push)02/19 - 02/12: Push: Priority Alignment - In Stamping01/22: Stamping dependency and backlog12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q3- M9 [R2022(+)_13] | COMPLETED |  | Wood | 60 | 0 |  | 2020-09-23 | Yes |  |  |  | 2020-11-01 | 2020-11-01 |  |  |  |  | Full | 2020-10-13 | 2020-10-13 | Full |  |  | Final drawings submitted 9/15/20. No constraints identified. | Full |  | 2020-10-26 | Yes | 2021-12-31 |  |  |  | 2021-09-16 |  | 2021-08-27 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6572 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-01-27 08:00 | 2022-05-18 17:00 |  | 2022-07-19 17:00 | 2020-10-26 |  |  |  |  | Yes |  |  | 262500 | 3247820.6 |  | 262500 | 0 |  | 1237% | 82896.1 |  |  |  | 1959827.7449 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.05 | MX | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129622 |  |  |  | STS-COND_IDLE_REMV - A/F 1EO 3600 BLACKT |  |  | FICL |  | 0 | 320 | 320 | 0.060606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.0066288 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 355 | 0.067235 | 0 | 0 | 0.067235 | -0.0066288 | 0.067235 | 0 | 0.067235 | 0 | 0 | 0.067235 |  |  |  |  | N/A | [7 empty] | 2020-06-17 | [29 empty] | 38.7128 | -120.7982
35129640 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  |  | PEND | 8536 | 0 | 8536 | 8536 | 1.6167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6167 |  |  | NV | 08W | SH | 2021-12-15 17:00 |  |  | 2020-06-25 | 2021-09-30 | 2020-06-25 | 2020-06-18 | 2020-06-18 |  | 2020-11-16 | 06/19: ADE approved for routing 06/18: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready] 06/17: EST target sub (6/26) 06/12: ADE rtn 1st corrections to CO 06/11: ADE assigned (Maria) 06/10 - 05/06: ADE to be assigned 03/21: QUES submitted for 1st ADE rvw (2) 03/11: Assigned new 1st sub (3/20) 02/27: Flagged COMPOSITE to WOOD [2] - pulled back 02/21: QUES submitted for 1st ADE Rvw 02/19: On Track 02/12: Push: Priority Alignment - In Stamping 02/05: Push to EOW - stamping 1/22: ??Scope change - Poles removed from PM?? 12/18: EST spread 1st submittal dates 12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/Resistence Scoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M10 [R13] | EDRS - ADE Approved for Routing |  | Wood | 51 | 1 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  | 2020-11-20 | [5 empty] | 2021-09-16 |  | 2021-08-27 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6167 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-15 17:00 |  | INPR | 2022-01-20 08:00 | 2022-05-11 17:00 |  | 2022-06-10 17:00 | 2020-11-16 | [7 empty] | 262500 | 3093975.6 |  | 262500 | 0 |  | 1179% | 15383.3 |  |  |  | 1913799.3402 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.06 | MX | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129641 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  |  | PEND | 7019 | 0 | 7019 | 7019 | 1.3294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3294 | 7379 | 1.3975 | NV | 08W | SH | 2021-12-22 17:00 |  |  | 2020-07-28 | 2021-09-30 | 2020-07-28 | 2020-07-09 | 2020-07-09 |  | 2020-09-08 | 07/28: Final corrections communicated; QUES submitted for final rvw. APPROVED - INTO PEND07/21: QUES routed for approval; ADE on vacation 07/14: ADE rtn corrections to CO07/14: QUES submitted for 3rd ADE rvw; ADE advised estimator, ask [REDACTED] for project management hours.07/09: QUES submitted for 2nd ADE rvw; ADE rtn 2nd Corrections to CO07/08 - 07/01: EST On Track06/24: EST target sub (7/17); Est out of office06/24: ADE rtn 1st corrections to CO06/17 - 06/10: ADE rvw - priority based05/27: ADE assigned ( [REDACTED] )05/20 - 05/06: ADE to be assigned01/27: QUES submitted for 1st ADE rvw01/22: Scope change - added locations; Eng shift locs onto PM; In stamping12/18: EST spread 1st submittal dates; went into review toda12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q3- M7 [R2022(+)_13] | COMPLETED |  | Comp | 18 | 40 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-08-31 | 2020-08-31 | Full |  |  |  | Full |  | 2020-11-20 | [5 empty] | 2021-10-06 |  | 2021-09-16 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3294 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-02-10 08:00 | 2022-05-30 17:00 |  | 2022-06-29 17:00 | [8 empty] | 262500 | 2569898.7 |  | 262500 | 0 |  | 979% | 41912.8 |  |  |  | 1933190.6448 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.07 | TL | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129642 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  |  | PEND | 6255 | 0 | 6255 | 6255 | 1.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1847 |  |  | NV | 08W | SH | 2021-12-22 17:00 |  |  | 2020-10-31 | 2021-09-30 | 2020-10-31 | 2020-07-28 | 2020-07-28 |  | 2020-10-30 | 10/28: Planner responded with changes; apply for DS73 completion; EST applied; working with planner to finalize. DS73 Complete10/28 - 10/21: Routed for approval; not sent to planner DS7310/21: EST Status; finising up stamping; route (10/23)10/14: EST target sub (10/16)10/08: ADE rtn 2nd corrections to CO10/7: ADE Follow-up09/30 - 09/23 - 7/29: ADE in rvw; priority based [2nd in line]07/28: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]07/22: EST stamping - ON TRACK07/15: Waiting on response from EEI - tie into alternate project(s)07/08 - 07/01: EST target date (7/24); EST working through Q&A with ADE to continue implementing corrections06/30: ADE rtn 1st corrections to CO06/24 - 06/17: ADE rvw - priority based06/15: ADE Assigned ( [REDACTED] )06/10 - 05/27: ADE to be assigned03/23: QUES submitted for 1st ADE rvw (2)03/23: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2] - pulled back02/21: QUES submitted for 1st ADE Rvw02/19: OCalc issue - Ticket submitted; Low RISK; Still On Track02/12: Push: Priority Alignment - In Stamping02/05: EST sent for stamping today (backlog); Push 2wk01/22: Scope change - Added locations; Eng shift locs onto PM12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M10 [R2022(+)_13] | EDRS - Pending EDRS approval |  | Wood | 42 | 3 | [6 empty] | 2020-11-27 | 2020-11-27 |  |  |  |  | Full | 2020-12-01 | 2020-12-01 | Full |  |  | Compared final drawings to existing Land Review and there are no Land issues with the added interset pole at location 57 | Full | [7 empty] | 2021-10-28 |  | 2021-10-06 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1847 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-12-22 17:00 |  | INPR | 2022-02-10 08:00 | 2022-05-30 17:00 |  | 2022-06-29 17:00 | [8 empty] | 262500 | 2304574.4 |  | 262500 | 0 |  | 877.9% | 52429.7 |  |  |  | 1945348.1746 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014760.08 | TL | OH | 2020-013 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129643 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  |  | PEND | 10869 | 0 | 10869 | 10869 | 2.0585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0585 | 11072 | 2.097 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-09-29 | 2020-11-30 | 2020-09-29 | 2020-07-30 | 2020-07-30 |  | 2020-09-23 | 09/23: QUES submitted for 1st ADE rvw; RD, replaced the Cooper Regulator kit with the [REDACTED] in EES; ADE approved.09/22: Redesign - very limited of Cooper Regulators (M262957) units due to very long lead time. Therefore, we are trying to switch full bank installations *****09/15: APPROVED - INTO PEND09/02: EST target sub (9/04) ??; Planning Eng need to complete DS7308/29: ADE rtn 5th corrections to CO; DS73 to be completed08/27: QUES submitted for 5th ADE rvw08/26: ADE rtn 4th corrections to CO08/20: QUES uploaded missing docs08/19: ADE in rvw; priority based08/17: QUES submitted for 4th ADE rvw08/13: ADE rtn 3rd corrections to CO08/12: ADE in rvw; priority based08/10: QUES submitted for 3rd ADE rvw08/05: EST target sub (8/18)08/04: ADE rtn 2nd corrections to CO07/30: QUES submitted for 2nd ADE rvw07/29: EST Sub (8/4); Finalizing Stamping revisions07/22: On Track07/15: EST target sub (7/28)07/02: ADE rtn 1st corrections to CO06/25: ADE assigned ( [REDACTED] )06/24 - 05/27: ADE to be assigned05/14: QUES submitted for 1st ADE rvw05/13: On Track04/29: Internal rvw conducted; big combination of OH/UG04/15: On Track04/08: Moved to 5/1 - still early in process/design03/23: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2]01/29: Fielded, Sched to start.01/08: UG - JO working on whether to proceed with UG (hold on est Progress) Push 1 Month (firm up date next week)12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q3- M9 [R2022(+)_14] | EDRS - EST Routing for approval |  | Wood | 19 | 0 |  | 2020-09-16 | Yes |  |  |  | 2020-10-14 | 2020-10-14 |  |  |  |  | Full | 2020-10-14 | 2020-10-14 | Full |  |  | No constraints identified | Full |  | 2020-11-20 | [5 empty] | 2021-06-04 |  | 2021-05-13 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0585 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-19 17:00 |  | 2022-12-12 17:00 | [5 empty] | Yes |  |  | 271429 | 4825574.8 |  | 271429 | 0 |  | 1778% | 67183.4 |  |  |  | 2344193.1129 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014755.02 | TL | OH | 2020-014 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35129644 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  |  | PEND | 5214 | 0 | 5214 | 5214 | 0.9875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9875 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-07-31 | 2020-11-30 | 2020-07-31 | 2020-07-03 | 2020-07-03 |  | 2020-12-29 | 07/31: APPROVED - INTO PEND07/30: ADE approved for routing07/29: ADE in rvw - priority based07/16: QUES submitted 3rd correcitons for ADE rvw07/15: EST target sub (7/24)07/15: TSC Ticket submitted to modify one of the planned units07/14: ADE rtn 2nd corrections to CO07/08: ADE in rvw - priority based07/03: Ques submitted for 2nd ADE rvw - [PRELIM DWG ready]07/01 EST target sub (7/17) TBD06/29: ADE rtn 1st corrections to CO06/24: ADE in rvw - priority based06/22: ADE assigned ( [REDACTED] ); EST request rvw hold - PGE sent back for redesign w/ wood poles vs. composite, ADE found - PM ok to proceed, alternate PM w/ conversion request.06/17 - 04/08: ADE to be assigned04/07: QUES submitted for 1st ADE rvw04/01: EST waiting on stamping 5 more locations, then ready to submit03/23: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2] - pulled back01/27: QUES submitted for 1st ADE rvw12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M11 [R2022(+)_14] | COMPLETED |  | Wood | 16 | 0 |  |  | Yes |  |  |  | 2020-08-21 | 2020-08-21 |  |  |  |  | Full | 2023-12-25 | 2023-12-25 |  |  |  | Finalized Drawings provided. Locations on USFS. Veg scope received to support USFS submittal week of 9/28. Plumas USFS submittal is Class 2c requiring 15 days to review. Have moved out date by several days to accommodate Thanksgiving holiday. |  |  | 2020-09-28 | Yes | 2021-12-31 |  |  |  | 2021-04-23 |  | 2021-04-02 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9875 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 | Yes | INPR | 2022-08-16 08:00 | 2022-09-26 17:00 |  | 2022-12-19 17:00 | 2020-12-14 |  |  |  |  | Yes |  |  | 271429 | 1571304.5 |  | 271429 | 0 |  | 578.9% | 56014.5 |  |  |  | 1591194.4304 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014755.03 | TL | OH | 2020-014 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35129645 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  |  | PEND | 6367 | 0 | 6367 | 6367 | 1.2059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2059 | 5416 | 1.0258 | NV | 08W | SH | 2023-12-25 |  |  | 2020-08-06 | 2020-11-30 | 2020-08-06 | 2020-07-13 | 2020-07-13 |  | 2020-08-06 | 08/06: APPROVED - INTO PEND08/05: Completing final rvw & corrections08/04: QUES routed07/29: RISK - still awaiting GC rvw07/22: PUSH - Sub target (8/7); pending GC07/15: EST target sub (7/24); corrections applied waiting on GC rvw and costs07/13: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready]; ADE rtn 2nd corrections to CO07/08 - 07/01: EST target date (7/10); instructed to proceed w/o const. rvw06/30: ADE rtn 1st corrections to CO06/24: ADE in rvw - priority based06/22: ADE assigned ( [REDACTED] )06/17 - 02/12: ADE to be assigned02/07: QUES Submitted for 1st ADE rvw02/04: Sent for stamping12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M11 [R2022(+)_14] | COMPLETED |  | Comp | 1 | 18 |  |  | Yes |  |  |  | 2020-10-10 | 2020-10-10 |  |  |  |  | Full | 2023-12-25 | 2023-12-25 |  |  |  | Portion of project on Plumas National Forest property. Need Veg Scope (9/28, still needed as of 10/5, 10/12, 10/20, 10/26, 11/2, 11/9, 11/16, and 11/30). ERTC date is now at risk. Can issue a PERTC for non USFS locations if needed and requested. |  |  | 2020-10-26 | Yes |  |  |  |  | 2021-06-25 |  | 2021-06-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2059 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-27 17:00 |  | 2022-12-20 17:00 | [8 empty] | 271429 | 1973021.4 |  | 271429 | 0 |  | 726.9% | 34416.7 |  |  |  | 1636179.204 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014755.04 | TL | OH | 2020-014 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35129646 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  |  | CONS | 6644 | 0 | 6644 | 6644 | 1.2583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2583 | 5560 | 1.053 | NV | 08W | SH | 2022-07-29 08:00 |  |  | 2020-07-14 | 2020-11-30 | 2020-07-14 | 2020-04-14 | 2020-04-14 |  | 2020-07-14 | 07/14: APPROVED - INTO PEND07/14: QUES applied final corrections; routed for approval07/13: ADE provide final corrections to CO07/08 - 07/01 EST target sub (7/08)06/29: ADE rtn 1st corrections to CO06/24: ADE assigned ( [REDACTED] )06/17 - 04/08: ADE to be assigned04/01: QUES submitted for 1st ADE rvw03/23: Assigned new 1st sub02/27: Flagged COMPOSITE to WOOD [2] - Pulled back02/18: Submitted for 1st ADE rvw02/12: ON Track1/22: Internal rvw; Push Stamping dependacy12/18: EST spread 1st submittal dates12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/ResistenceScoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M11 [R14] | COMPLETED |  | Wood | 43 | 0 |  |  | Yes |  |  |  | 2020-08-18 | 2020-08-18 |  |  |  |  | Full | 2020-09-18 | 2020-09-18 | Full |  |  | Waiting on parks notifications | Full |  | 2020-10-26 | Yes |  |  |  |  | 2021-06-25 |  | 2021-06-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2583 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-07-29 08:00 |  | INPR | 2022-08-16 08:00 | 2022-09-27 17:00 |  | 2022-12-20 17:00 | 2020-10-27 |  |  |  |  | Yes |  |  | 271429 | 2038372.6 |  | 271429 | 0 |  | 751% | 41663 |  |  |  | 1619898.755 |  |  |  |  | Complete | [6 empty] | Magalia | Butte | 0 | 0 | E.5014755.05 | TL | OH | 2020-014 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35129647 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  |  | ESTS | 6429 | 0 | 6429 | 6429 | 1.2176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2176 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2020-08-28 | 2020-08-28 |  |  | 11/10 - 10/28: EST sub (11/06); stamp by Friday; waiting for intrusives 10/21: EST Status; Change order submitted 10/19 - approved; applying changes (JP, Stamps & internal rvw); target sub (10/28) 10/14 EST target sub (10/19) 10/12: ADE rtn 2nd corrections to CO; evacuations & higher priority work impacts 10/7: ADE Follow-up 09/02: ADE in rvw; starting 2nd rvw this week 08/28: QUES submitted for 2nd ADE rvw 08/26: EST target sub (9/4) 08/19 - 08/12: EST target sub (8/28): going through EST final rvw 08/05: EST target sub (??) - TBD; ADE requesting interset poles for span 07/29: EST target sub (7/14) 07/23: ADE rtn 1st corrections to CO 07/22 - 07/01: ADE in rvw - priority based 06/26: ADE assigned (ED) 06/24 - 05/06: ADE to be assigned 04/30: QUES submitted for 1st ADE rvw 04/29: EST in rvw; stamping; Push (5/1) 04/22: On Track 04/15: Higher priority projects going through stamping; will finish stamping 04/08: Finalizing stamping; On Track 04/01: EST On Track 03/23: Assigned new 1st sub 02/27: Flagged COMPOSITE to WOOD [2] 02/12: Est out - Progress hardship to shift Estimator assignment. 02/05: Waiting for joint pole and stamping 12/18: EST spread 1st submittal dates 12/11 - 11/27: Fielding RISK: Snow (1ft deep) & Customer Access/Resistence Scoping Not complete/Incomplete maps - Need Checklist review |  |  |  | 2020 - Q4- M11 [R2022(+)_14] | R2.3 - EST Implementing Corrections |  | Wood | 18 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-06-25 |  | 2021-06-04 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2176 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-08-23 17:00 |  | INPR | 2022-10-11 08:00 | 2022-11-22 17:00 |  | 2023-02-14 17:00 | [5 empty] | Yes |  |  | 271429 | 2387072.1 |  | 271429 | 0 |  | 879.4% | 10856.7 |  |  |  | 1960451.1881 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014755.06 | TL | OH | 2020-014 | 2021 |  | 2020-11-30 | 2021-02-13 |  |  | Y | ORO FINO 11012022 | 10
35129648 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  |  | ESTS | 6113 | 0 | 6113 | 6113 | 1.1578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1578 | 6141 | 1.1631 | NV | 08W | SH | 2023-12-25 |  |  | 2020-12-31 | 2021-09-30 | 2020-12-31 | 2020-10-09 | 2020-10-09 |  |  | 11/04: ADE in rvw; priority based11/03: EEI submitted corrections for 3rd ADE rvw10/28: EST sub (TBD)10/24: ADE rtn 2nd rvw to CO10/21 - 10/14: ADE in rvw10/09: EEI submitted for for 2nd ADE rvw- PRELIM DWG ready10/7: Submittal by 10/909/30 - 09/23: EST target sub (9/25); (10/9)09/12: ADE rtn 1st corrections to CO; Apply corrections and removed composite poles09/03: ADE assigned ( [REDACTED] )09/02: ADE to be assigned08/31: EEI submitted for 1st ADE rvw08/26 - 08/19: EST target sub (9/4); priorities08/12:: EST target sub (8/28)08/07 - 07/29: On Track07/22: EST target sub (8/21) - priorities07/15: On Track07/08: EST target sub (7/31); working priority projects07/01: On Track06/24: EST target sub (7/17)06/17: On Track06/10 - 05/20: Push 2wk (5/29);(6/5);(6/26) - working priority projects05/13 - 05/06: On Track04/29 EST firmed up sub (5/15)04/22 - 04/01: On Track03/25: EST firmed up 1st sub02/27: Flagged COMPOSITE to WOOD [2]02/26: EST push 1st sub02/18: EEI to review schedule01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M12 [R2021_51] | R3.2 - ADE Review in Progress |  | Wood | 29 | 15 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-07-16 |  | 2021-06-25 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1578 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-13 17:00 |  | INPR | 2022-03-21 08:00 | 2022-07-06 17:00 |  | 2022-08-05 17:00 | [8 empty] | 250000 | 2233286.1 |  | 250000 | 0 |  | 893.3% | 17407.2 |  |  |  | 1928962.9655 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5015030.02 | ML | MX | 2021-051 | 2021 |  | 2020-10-31 | 2021-01-14 |  |  | Y | ORO FINO 11012022 | 10
35129649 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  |  | ADER | 8596 | 0 | 8596 | 8596 | 1.628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.628 |  |  | NV | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2021-01-31 | 2020-11-30 | 2020-10-12 | 2020-10-12 |  |  | 11/09: EEI submitted corrections for 3rd ADE rvw[NOV EOD @ Risk]11/04: EEI target sub (11/23); EST bandwith/vacation10/23: EST sub (TBD)10/22: ADE rtn 2nd rvw for corrections to CO10/21: ADE targeting tomorrow, Monday at the latest.10/14: ADE in rvw10/12: EEI submitted for 2nd ADE rvw - PRELIM DWG ready10/7: Submittal by 10/1209/30 - 09/23: EST target sub (10/2)09/16: EST target sub (9/23)09/09: ADE rtn 1st corrections to CO09/02 - 08/12: ADE in rvw; priority based08/06: EST uploaded docs08/05: ADE in rvw - priority based; EST renumbering completed; pending stamping07/28: ADE request Renumbering needed (start loc 1)/ EST working renumbering07/28: ADE Assigned ( [REDACTED] )07/22 - 06/17: ADE to be assigned06/16: EEI submitted for 1st ADE rvw06/10- 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M11 [R2021_121] | R3.2 - ADE Review in Progress |  | Wood | 53 | 4 | [13 empty] | 2023-12-25 | 2023-12-25 | [12 empty] | 2021-05-24 |  | 2021-05-03 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.628 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-05 17:00 |  | INPR | 2022-08-01 08:00 | 2022-10-28 17:00 |  | 2022-11-29 17:00 | [8 empty] | 55556 | 16376.6 |  | 55556 | 0 |  | 29.47% | 16307.3 |  |  |  | 10059.1494 |  |  |  |  | Complete |  |  |  |  | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.02 | ML |  | 2021-121 | 2021 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129650 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  |  | PEND | 7291 | 0 | 7291 | 7291 | 1.3809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3809 |  |  | NV | 08W |  | 2022-01-07 17:00 |  |  | 2020-10-01 | 2021-01-31 | 2020-10-01 | 2020-09-24 | 2020-09-24 |  | 2020-09-30 | 09/29: Routed; ADE concurred09/25: ADE rtn 2nd corrections; minor - apply & route09/24: EEI submitted for 2nd ADE rvw - PRELIM DWG ready09/23: EST target sub (9/25)09/11: ADE rtn for 1st corrections to CO09/08: ADE assigned ( [REDACTED] )09/02 - 08/19: EST target sub (9/4) 08/12:: EST target sub (8/28)08/05 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M10 [R2022(+)_181] | COMPLETED | 0 | Wood | 52 | 0 | [6 empty] | 2020-11-17 | 2020-11-17 |  |  |  |  | Full | 2020-11-17 | 2020-11-17 | Full |  |  | Locations on FERC identified in high level review. May push out ERTC date. | Full | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3809 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-01-07 17:00 |  | INPR | 2022-07-25 08:00 | 2022-11-14 17:00 |  | 2022-12-12 17:00 | [8 empty] | 305556 |  |  | 305556 | 0 |  |  | 99023.8 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.03 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129652 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  |  | PEND | 5493 | 0 | 5493 | 5493 | 1.0403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0403 |  |  | NV | 08W | SH | 2022-04-14 17:00 |  |  | 2020-10-05 | 2021-01-31 | 2020-10-05 | 2020-09-25 | 2020-09-25 |  | 2020-11-24 | 10/05: APPROVED - INTO PEND10/2: 2nd ADE Review Sent Back09/30: ADE in rvw; 09/25: EEI submitted for 2nd ADE rvw09/23 ADE rtn 1st corrections to CO09/16- 08/12: ADE in rvw; priority based08/03: ADE assigned ( [REDACTED] )07/29 - 06/24: ADE to be assigned06/22: EEI submitted for 1st ADE rvw06/17 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M10 [R2022(+)_181] | COMPLETED |  | Wood | 42 | 0 |  | 2020-10-07 | Yes |  |  |  | 2020-11-23 | 2020-11-23 |  |  |  |  | Full | 2020-11-23 | 2020-11-23 | Full |  |  | No enviro constraints identified | Full |  | 2020-11-20 | [5 empty] | 2021-07-05 |  | 2021-06-14 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0403 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-14 17:00 |  | INPR | 2022-10-21 08:00 | 2022-12-30 17:00 |  | 2023-01-31 17:00 | 2020-11-23 |  |  |  |  | Yes |  |  | 305556 | 85043.7 |  | 305556 | 0 |  | 27.83% | 84873.1 |  |  |  | 81745.9924 | [9 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.04 | TL |  | 2020-181 | 2021 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129653 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  |  | PEND | 6678 | 0 | 6678 | 6678 | 1.2648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2648 |  |  | NV | 08W |  | 2022-03-31 17:00 |  |  | 2020-11-04 | 2021-01-31 | 2020-11-04 | 2020-10-22 | 2020-10-22 |  | 2020-11-04 | 11/04: EST to routed - APPROVED INTO PEND11/02: EEI submitted corrections for 3rd ADE rvw; ADE rtn 3rd rvw to CO - approved for routing10/28: 10/26: ADE rtn 2nd rvw to CO10/22: EST submitted corrections for 2nd ADE rvw10/21 - 10/14: EST target sub 10/2610/12: ADE rtn 1st corrections to CO10/7: ADE follow-up09/30: ADE in rvw09/14: ADE assigned ( [REDACTED] )09/11: EEI submitted for 1st ADE rvw08/26: EST target sub (9/4); priorities08/19: On Track08/12: EST target sub (8/28)08/05 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M11 [R2022(+)_181] | COMPLETED |  | Wood | 58 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2648 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-03-31 17:00 |  | INPR | 2022-09-16 08:00 | 2023-01-03 17:00 |  | 2023-01-31 17:00 | [8 empty] | 55556 |  |  | 1351444.1 | 1295888.1 |  |  | 4460.4 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.05 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129654 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  |  | PEND | 10499 | 0 | 10499 | 10499 | 1.9884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9884 |  |  | NV | 08W |  | 2023-12-25 |  |  | 2020-10-21 | 2021-02-28 | 2020-10-21 | 2020-10-16 | 2020-10-16 |  | 2020-10-21 | 10/21: APPROVED - INTO PEND10/19: ADE rtn corrections to CO; EST applied corrections10/18: EST routed10/16: Submitted for 2nd ADE rvw10/14: EST target sub (10/23)10/09 ADE rtn 2st corrections to CO10/7: ADE follow-up09/30 - 09/23: ADE in rvw; Priority based09/08: ADE assigned ( [REDACTED] DB)09/02: ADE to be assigned08/31: EEI submitted for 1st ADE rvw08/26: EST target sub (8/31); priorities08/19: EST target sub (8/28)08/12:: EST target sub (8/21)08/05 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M10 [R2022(+)_181] | COMPLETED |  | Wood | 71 | 1 | [6 empty] | 2020-12-14 | 2020-12-14 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Some locations on FERC to be evaluated by enviro team. | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9884 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-02-10 17:00 |  | INPR | 2022-07-29 08:00 | 2022-11-18 17:00 |  | 2022-12-16 17:00 | [8 empty] | 305556 |  |  | 305556 | 0 |  |  | 128056 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.06 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129655 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  |  | PEND | 9273 | 0 | 9273 | 9273 | 1.7563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7563 |  |  | NV | 08W |  | 2022-03-24 17:00 |  |  | 2020-10-23 | 2021-02-28 | 2020-10-23 | 2020-09-25 | 2020-09-25 |  | 2020-10-23 | 10/23: Final rvw provided to CO; EEI applied corrections/routed; APPROVED - INTO PEND10/22: ADE rtn 4th rvw to CO; ready for approval; EEI routed10/21: EEI submitted corrections for 4th ADE rvw10/20: ADE rtn 3rd corrections to CO10/14: ADE in rvw; priority based10/06: EEI submitted for 3rd ADE rvw10/02: ADE rtn 2nd corrections09/30: ADE in rvw09/25: EEI submitted for 2nd ADE rvw09/23: EST target sub (9/28)08/27: ADE rtn 1st corrections to CO08/26 - 08/19: ADE assigned ( [REDACTED] )08/05: EEI submitted for 1st ADE rvw07/29 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M10 [R2022(+)_181] | COMPLETED |  | Wood | 26 | 17 | [6 empty] | 2020-12-14 | 2020-12-14 |  |  |  |  | Full | 2020-12-15 | 2020-12-15 | Full |  |  | Some locations on FERC and aquatic constraints to be evaluated by enviro team. | Full | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7563 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-03-24 17:00 |  | INPR | 2022-09-09 08:00 | 2022-12-29 17:00 |  | 2023-01-26 17:00 | [8 empty] | 55556 |  |  | 999695.19 | 944139.19 |  |  | 20200.5 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.07 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129656 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  |  | ADER | 8397 | 0 | 8397 | 8397 | 1.5903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5903 |  |  | NV | 08W |  | 2022-03-18 17:00 |  |  | 2020-12-31 | 2021-02-28 | 2020-12-31 | 2020-12-01 | 2020-12-01 |  |  | 11/04: ADE in rvw: Priority based10/29: ADE assigned ( [REDACTED] )10/28: EEI submitted for 1st ADE rvw10/28- 10/7: Submittal by 10/12; 10/16; 10/26; 10/2809/23 - 08/19: On Track08/12: EST target sub (9/30)08/05 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M12 [R2022(+)_181] | R1.2 - ADE Review in Progress |  | Wood | 55 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5903 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-03-18 17:00 |  | INPR | 2022-09-02 08:00 | 2022-12-22 17:00 |  | 2023-01-19 17:00 | [8 empty] | 55556 | 8763.2 |  | 55556 | 0 |  | 15.77% | 8732.7 |  |  |  | 5510.2651 | [9 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.08 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129657 |  |  |  | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  |  | ESTS | 7516 | 0 | 7516 | 7516 | 1.4235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4235 |  |  | NV | 08W |  | 2022-03-18 17:00 |  |  | 2020-12-31 | 2021-02-28 | 2020-12-31 | 2020-12-01 | 2020-12-01 |  |  | 10/28: ADE rtn 2nd rvw to CO10/21 - 10/7: ADE in rvw; priority based09/16: ADE assigned ( [REDACTED] )09/10: EEI submitted for 1st ADE rvw09/08: EST target sub (9/10)09/02 - 08/19: Est target sub (9/4); refielding a couple locs.08/12:: EST target sub (8/21)07/29 - 03/25: EST sub new dates TBD02/27: Flagged COMPOSITE to WOOD [2]01/08: Est 1st sub taret changes TBDAnticipate Snow Impact to initiate |  |  |  | 2020 - Q4- M12 [R2022(+)_181] | R1.3 - EST Implementing Corrections |  | Wood | 37 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4235 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-03-18 17:00 |  | INPR | 2022-09-02 08:00 | 2022-12-21 17:00 |  | 2023-01-18 17:00 | [8 empty] | 55556 |  |  | 55556 | 0 |  |  | 9621.7 | [13 empty] | Remove |  | Magalia | Butte | 0 | 0 | E.5014724.09 |  |  | 2020-181 | 999 |  | 2021-01-31 | 2021-04-16 |  |  | Y | ORO FINO 11022090 | 72
35129767 |  |  |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  |  | ESTS | 13700 | 12455 | 1245 | 13700 | 2.5947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5947 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2020-10-31 | 2021-01-31 | 2020-12-31 | 2020-12-31 |  |  | 11/04 - 10/07: Pending PG&E survey, no right away; land targeting completion EOM (OCT); awaiting survey09/02 - 08/12: Email notes: JO asking for Transmission Survey to move forward with adding in the ROW’s for the undergrounding.Complex situation, the road runs in and out of the properties for the 2 miles so there’s many ROW’s and will take quite awhile.08/12- 06/24: Waiting on maps; Survey - need right aways? - Yes per El Dorado; RISK - push multiple months; high qty right aways 06/17 - 06/03: In Progress05/27 - 05/20: Approx 1mnth for base map + Est processing time; field dependencies still needing to be completed05/13: To be fielded with customer tomorrow (5/14)04/29: Prelim field walk conducted - feedback provided to PMgr - some complicated design/field conditions anticipated/identified04/15 - 04/01: Waiting on Transmission survey team response03/18: Accomodating design change: Working in UG at later date03/04 - 02/12: EST waiting on 'El Dorado' Base map to set schedule; Rcpt of base map may take 1-3 months, +30 estimate to submit; (firm up submittal date)01/29: Priority Adjustment...01/22: Mid Feb; UG scope should be defined and EST will be able to set schedule.01/08: QUES to ROM 1st Sub; For target of CONS-Strt May 1, 1st ADE sub needs to be 2/15 [T-45 Cons Dep + T-28 Prelim Milestone Rvw]12/18: Waiting on UG design rvw [REDACTED] assisting)12/11 <--12/04: QUES to sched 1st ADE to set EOD -Reviewing progress for assignment11/26: Associate Retired - Transitioning action items to alternate; will generate PMs11/20: Check on status of new PMs11/13: Pushed 2 wks - Proposed segmenting maps provided via Estimating - Pending issuance of new PMS ( [REDACTED] )10/23: Push for suborder generation and planning - Dates to be realigned upon completion10/21: 74022380 - New PM 35129767 created - [REDACTED] to assist with suborder approval9/25 - 10/16: Project generating errors - in progress to be resolved and completed.9/11: Email has been recirculated for resolution response (PGE Internal)8/16: Communication request (PGE internal) for map segmentation8/14: Check progress/Status on breakout8/1 - 8/7: Resurfaced request via email group for breakout and conversion to 300-series PM#7/31: Converted to UG - request to be broke into 4 seperate jobs7/24: In estimating; '700' Series - Confirm Version 8 or 9; Version 9 at Nov EOD7/3 - 7/16: recieived change order and approved. Waiting for sub orders6/21: QUES sent proposal to split jobs into 4 suborders5/22: waiting for change order5/8: waiting for updated pricing4/10: Updated Scope for QUES to review4/8: Working Job Packages |  |  |  | 2021 - Q1- M1 [R2022(+)_308] | Iss_R0.0 - Estimating | No | Nul (Low QTY) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5947 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-09 17:00 |  | INPR | 2022-04-26 08:00 | 2022-09-06 17:00 |  | 2022-11-07 17:00 |  |  |  |  | 2020-12-25 | Yes |  |  | 500000 | 150490.9 |  | 500000 | 0 |  | 30.09% | 146472 |  |  |  | 57999.4126 |  | 69 | [7 empty] | Remove |  | Nevada City | Nevada | 39.275 | -121.0207 | E.5015531.02 | ML |  | 2020-058 | 2021 | Reserve | 2020-04-30 | 2020-09-09 | 2020-10-31 |  | Y | BRUNSWICK 11032200 | 117
35130803 |  |  |  | STS-POLE_IDLE_REMV-BEHIND EEL R. SAWMILL |  |  | FICL |  | 0 | 1968 | 1968 | 0.37273 | 1968 | 0.37273 | 0 | 0 | 0 | 0 | 0 | 0 | -0.027273 |  |  | HB | 2AF | IF | [60 empty] | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0.4 | -0.027273 | 0.39905 | 0 | 0.39905 | 0 | 0.00094697 | 0.39905 |  |  |  |  | N/A | [7 empty] | 2020-06-08 | [29 empty] | 40.3993 | -123.9384
35131034 |  | 2020 |  | BUCOCAMPT 2903 NEAL RD PARADISE |  |  | CLSD |  | 0 | 402 | 402 | 0.076136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-21 | [55 empty] | 402 | 0.076136 | 0 | 0 | 0 | 0 | 0.076136 | 0 | 0.048106 | 0 | 0.048106 | 0 | 0.02803 | 0.048106 |  |  |  |  | N/A | [5 empty] | 2019-11-18 | 2019-11-22 | 2019-11-20 | [7 empty] | 31237.77 |  |  |  | 61004.7 | [17 empty] | 39.7161 | -121.6613 |  |  |  |  | 2019 | [5 empty] | Y
35131804 |  | 2020 |  | BUCOCAMPT 13869 TULSA CT MAGALIA*ILB |  |  | FICL |  | 0 | 392 | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95F | BUCOCAMP |  |  |  |  | 2019-10-26 | [55 empty] | 392 | 0.074242 | 0 | 0 | 0 | 0 | 0.074242 | 0 | 0.1053 | 0 | 0.1053 | 0 | -0.031061 | 0.1053 |  |  |  |  | N/A | [5 empty] | 2019-11-18 | 2019-11-22 | 2020-01-18 | [29 empty] | 39.811 | -121.5942 |  |  |  |  | 2019 | [5 empty] | Y
35135297 |  |  |  | STS-REM IDLE 12KV-110 PARKHILL,S.MARGAR |  |  | CLSD |  | 0 | 522 | 522 | 0.098864 | 0 | 0 | 522 | 0.098864 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 522 | 0.098864 | 0.098864 | 0 | 0.098864 | 0 | 0.098864 | 0 | 0 | 0 |  | Keep |  |  | N/A | [7 empty] | 2019-07-11 | [29 empty] | 35.3707 | -120.4072
35135864 |  | 2020 | 220 Mile Plan | CWSP - GRAYS FLAT 401 FUSE 3079 ZONE |  |  | CONS |  | 0 | 9316 | 9316 | 1.7644 | 9316 | 1.7644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2020-06-05 |  |  | 2020-02-10 |  | 2020-02-10 |  |  |  | 2020-02-10 | [12 empty] | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | Expires 10/1 |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 9316 | 1.7644 | 0 | 0 | 1.7644 | 0 | 1.7492 | 0 | 1.7492 | 0 | 0.015152 | 1.7492 |  | Keep | 2020-06-05 | Yes | COMP | 2020-05-26 | 2020-08-05 | Yes | 2020-08-05 | 2020-05-20 |  |  |  |  | Yes | Shovel Ready |  | 347534 |  |  | 347534 | 0 |  |  | 125230.2 | [15 empty] | Twain | Plumas | 40.018 | -121.0405 | 35135864 |  |  |  | 2020 | Q3 | 0 |  | 0 |  | Y | GRAYS FLAT 0401CB | 1833
35137590 |  | 2021 |  | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Scoped | ESTS | 2824 | 0 | 2824 | 2824 | 0.53485 | 0 | 0 | 2824 | 0.53485 | 0 | 0 | 0 | 0 | 1.5152e-10 |  |  | HB | 08W | SH | 2021-04-15 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | 2021-04-15 | [20 empty] | 2021-04-05 | 2021-03-31 | N/A |  |  |  |  | 2021-04-05 | 2021-03-31 |  |  |  | CIF submitted week of 2/15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53485 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-29 17:00 |  | N/A | 2021-11-08 08:00 | 2022-01-18 17:00 |  | 2022-03-21 17:00 |  | 2021-12-31 07:00 | 2021-12-31 16:00 | [5 empty] | 80000 | 50802.7 | 20786.9 | 80000 | 0 |  | 63.5% | 36449.7 |  |  |  | 94985.2181 |  |  |  |  | Complete | Prioritized | [5 empty] | Middletown | Lake | 38.7927 | -122.6592 | 35137590 |  |  | 2021-056 | 2021 |  |  |  | 2020-09-01 |  | Y | MIDDLETOWN 1101CB | 86 |  | ECOP |  | 2021-03-11 14:14
35137593 |  | 2021 |  | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Scoped | ESTS | 7273 | 0 | 7273 | 7273 | 1.3775 | 0 | 0 | 7273 | 1.3775 | 0 | 0 | 0 | 0 | -2.1212e-10 |  |  | HB | 08W | SH | 2021-04-27 17:00 | 2021-03-08 | Y | 2021-04-15 | 2021-04-15 | 2021-04-15 | [20 empty] | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 |  |  |  |  | CIF Submitted | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3775 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-04-27 17:00 |  | N/A | 2021-10-14 08:00 | 2022-01-18 17:00 |  | 2022-03-21 17:00 | [8 empty] | 80000 | 56474.5 | 20786.9 | 80000 | 0 |  | 70.59% | 42121.5 |  |  |  | 40998.9495 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137593 |  |  | 2021-054 | 2021 |  |  |  | 2020-09-01 |  | Y | MIDDLETOWN 11014646 | 328 |  | ECOP |  | 2021-03-11 14:14
35137596 |  | 2021 |  | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Scoped | ESTS | 5131 | 0 | 5131 | 5131 | 0.97178 | 0 | 0 | 5131 | 0.97178 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-23 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | 2021-04-15 | [20 empty] | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 |  |  |  |  | CIF Submitted | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-30 17:00 |  | N/A | 2021-10-26 08:00 | 2022-01-18 17:00 |  | 2022-03-21 17:00 |  | 2021-12-31 07:00 | 2021-12-31 16:00 | [5 empty] | 80000 | 37548.6 | 20786.9 | 80000 | 0 |  | 46.93% | 23195.6 |  |  |  | 38638.9803 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137596 |  |  | 2021-055 | 2021 |  |  |  | 2020-09-01 |  | Y | MIDDLETOWN 11014646 | 328 |  | ECOP |  | 2021-03-11 14:14
35137599 |  |  |  | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  |  | UNSE | 6828 | 0 | 6828 | 6828 | 1.2932 | 0 | 0 | 6828 | 1.2932 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2023-12-25 | 2021-03-31 | N |  | 2021-01-31 | [28 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2932 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-07-09 17:00 |  | N/A | 2021-08-03 08:00 | 2021-12-14 17:00 |  | 2022-02-14 17:00 | [8 empty] | 80000 | 21318.2 |  | 80000 | 0 |  | 26.64% | 6965.2 |  |  |  | 16485.0756 |  |  |  |  | Complete | Prioritized |  |  |  | Remove |  | Kelseyville | Lake | 38.8266 | -122.7269 | 35137599 |  |  | 2021-053 | 2021 |  |  |  | 2020-09-01 |  | Y | MIDDLETOWN 1101614 | 152 |  |  |  | 2021-03-11 10:42
35137767 |  |  |  | REMV IDLE 2 LOCS 1E/O 6S/O R/O 12109 |  |  | FICL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2020-01-29 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-08-31 | [29 empty] | 40.6374 | -122.2152 | [16 empty] | 2021-03-10 13:19
35142826 |  | 2021 | 2020 Rsrv | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Scoped | CONS | 8283 | 0 | 8412 | 8412 | 1.5932 | 0 | 0 | 8412 | 1.5932 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2020-09-02 |  | Y | 2020-06-15 | 2020-09-30 | 2020-06-15 | 2020-06-02 | 2020-06-02 | Yes | 2020-06-15 | 06/15: DS73 complete; APPROVED - INTO PEND06/14: [REDACTED] request DS73 to be completed for approval w/ [REDACTED] /10: Status - EST routed06/03: ADE rtn 2nd corrections to CO - apply and route06/02: QUES submitted for 2nd ADE rvw05/27: On Track05/20: Est target sub (5/29)05/14: ADE rtn 1st corrections to CO04/29: ADE assigned ( [REDACTED] )04/22 - 04/15: ADE to be assigned [Q2.5]04/08:QUES submitted for 1st ADE rvw04/01: EST sub Status - Waiting stamping; 03/18: In stamping03/11: Refielding03/25: EST Status - On Track??01/29: Priority Adjustment..01/24: 1st sub target (~50 poles)01/22: Fielding starting - EST to set target dates (approx 6 wks out for 1st sub)01/08: QUES to ROM 1st Sub12/18<--12/04: QUES to sched 1st ADE to set EOD -Reviewing progress for assignment12/03: PMs Issued - 1st ADE submitted to be scheduled |  |  |  | 2020 - Q2- M5 [R309] | COMPLETED |  | Comp | 9 | 42 |  | 2020-07-17 | Yes |  |  |  | 2020-05-22 | 2020-05-22 |  |  |  |  | Full | 2020-05-22 | 2020-05-22 | Full |  |  | CIF Submitted 4/7/2020 | Full |  |  | Yes |  |  | No permit needed |  | 2020-10-31 | Y | 2020-09-02 |  |  | 95% complete. Refusal Cust will not allow access | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5932 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-08-06 | Yes | COMP | 2021-02-01 08:00 | 2021-03-25 17:00 |  | 2021-06-17 17:00 | 2020-07-17 | 2021-02-01 07:00 | 2021-04-01 16:00 |  | 2020-08-21 | Yes |  |  | 2751921 | 3599488.7 | 2721318.8 | 3876275 | 1124354 | 1301354.8 | 130.8% | 1302171.7 | 148394.5 | 1450566.2 |  | 2259308.1712 |  | 42 | [9 empty] | Nevada City | Nevada | 39.2906 | -120.9978 | E.5015531.03 | TL |  |  | 2021 | Reserve | 2020-05-31 | 2020-10-07 | 2020-11-13 |  | Y | BRUNSWICK 11032200 | 117
35142827 |  |  |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  |  | PEND | 5022 | 0 | 4793 | 4793 | 0.90777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90777 |  |  | SI | 08W | SH | 2020-10-02 |  |  | 2020-08-21 | 2020-10-31 | 2020-08-21 | 2020-07-27 | 2020-07-27 | Yes | 2020-09-14 | 08/xx: APPROVED - INTO PEND08/19: QUES routed08/16: ADE rtn 2nd corrections to CO08/12 - 07/29: ADE in rvw - priority based [Completing Big Basin/delayed]07/27: QUES submitted for 2nd ADE rvw07/22: EST target sub (8/07)07/17: ADE rtn 1st corrections to CO07/15: ADE in rvw07/08 - 06/17: ADE On Track; (7/9 or early next week)06/10 - 05/27: ADE in rvw04/29: ADE assigned [REDACTED] )04/22 - 04/01: ADE to be assigned [Q2.5]03/25 - 3/10: Prj MGR - potential scope changes; projects will tie-in; Phase 1 (the UG portion) will most likely not be built until next year - estimators and make sure we've established a riser location, 3/10: QUES submitted for 1st ADE rvw03/04 - 02/26: EST On Track - In internal rvw/stamping01/29: Priority Adjustment..01/24: 1st sub target (~30 poles)01/22: Fielding starting - EST to set target dates (approx 6 wks out for 1st sub)01/08: QUES to ROM 1st Sub12/18<--12/04: QUES to sched 1st ADE to set EOD -Reviewing progress for assignment12/03: PMs Issued - 1st ADE submitted to be scheduled |  |  |  | 2020 - Q3- M8 [R2022(+)_310] | COMPLETED |  | Comp | 1 | 25 |  | 2020-08-25 | Yes |  |  |  | 2020-10-02 | 2020-10-02 |  |  |  |  | Full | 2020-06-01 | 2020-06-01 | Full |  |  | PERTC Released - Waiting on 1 easement location 1 | Full |  |  | Yes |  |  | No permit needed |  | 2020-11-06 | Y | 2020-09-02 |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.90777 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-09-29 | Yes | COMP | 2021-12-06 08:00 | 2022-04-18 17:00 |  | 2022-06-17 17:00 | 2020-09-14 |  |  |  |  | No |  |  | 1802500.3 |  |  | 2485715 | 683214.7 |  |  | 440416.3 | [5 empty] | 26 | [7 empty] | Remove |  | Nevada City | Nevada | 39.2876 | -121.0018 | E.5015531.04 | TL |  |  | 2021 | Reserve | 2020-05-31 | 2020-10-07 | 2020-11-04 |  | Y | BRUNSWICK 11032200 | 117
35142828 |  |  |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  |  | CONS | 2600 | 0 | 2600 | 2600 | 0.49242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49242 |  |  | SI | 08W | SH | 2020-10-22 |  |  | 2020-07-22 | 2020-07-31 | 2020-07-22 | 2020-05-22 | 2020-05-22 | Yes | 2020-07-28 | 07/24: APPROVED - INTO PEND 07/22: QUES routed 07/01: ADE approved for routing. EST routed; ADER rtn final corrections t to CO xx/xx: QUES submitted for 3rd ADE rvw 06/24: Status estimator needs Land and Environmental cost from the Project Manager. The Project Manager will be returning to work on 6/17/20; PM provided information to Est. 06/17: EST corrections applied; JO information requested & required to submit; JO out of office until (6/17). 06/11: ADE rtn 2nd corrections to CO - correct (2 items), ready for approval 06/10: ADE target shift (6/15) 05/27: ADE soft target (6/5) 05/22: QUES submitted for 2nd ADE rvw - [PRELIM DWG ready] 05/20: Est target sub (5/22) 05/07: ADE rtn 1st corrections to CO 04/30: ADE assigned (Steve) 4/29 - 04/08: ADE to be assigned [Q2.5] 04/06: QUES submitted for 1st ADE rvw 04/01: EST sub Status (3/20) - EOW, appling internal rvw changes 01/01 - 03/25: EST status?? 03/18: EST on track 03/11 - 03/04: Push; Refielding; PM requested 'scope' change 01/24: Priority Adjustment.. 01/25: 1st sub target (~24 poles) 01/22: Fielding starting - EST to set target dates (approx 6 wks out for 1st sub) 01/08: QUES to ROM 1st Sub 12/18<--12/04: QUES to sched 1st ADE to set EOD -Reviewing progress for assignment 12/03: PMs Issued - 1st ADE submitted to be scheduled |  |  |  | 2020 - Q3- M7 [R2022(+)_311] | COMPLETED |  | Comp | 4 | 19 |  | 2020-07-27 | Yes |  |  |  | 2020-05-22 | 2020-05-22 |  |  |  |  | Full | 2020-05-22 | 2020-05-22 | Full |  |  | CIF Submitted 4/7/2020 | Full |  |  | Yes |  |  | No permit needed |  | 2020-11-13 |  | 2020-10-22 | 2020-08-19 |  | 99% complete - 2 refusal locations remain as of 12/1/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49242 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2020-08-06 17:00 | Yes | COMP | 2021-12-06 08:00 | 2021-12-29 17:00 |  | 2022-01-24 17:00 | 2020-08-22 |  |  |  | 2020-08-10 | Yes |  |  | 1107016 | 399180.2 |  | 1844178 | 737162 | 741608.9 | 36.05% | 330917.6 | 34489.5 | 365407.1 |  | 810642.8677 |  | 13 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015531.05 | TL |  |  | 2021 | Reserve | 2020-05-31 | 2020-10-07 | 2020-10-28 |  | Y | BRUNSWICK 11032200 | 117
35144940 |  |  |  | *CANC* PSPS - HICKS 2101 - CB |  |  | CLSD | 7145.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | [5 empty] | 2020-10-31 | [5 empty] | Cancelled | [13 empty] | PSPS - Cancled | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-09-03 |  |  |  |  | 500000 |  |  | 500000 | 0 | [11 empty] | Complete | Install 2 PSPS devices only | [5 empty] | San Jose | Santa Clara | 37.232 | -121.8718 | E.5025645.01 |  |  |  | 1980 | Q3 |  |  | 2020-09-01 |  | Y | HICKS 2101XR250 | 621
35144941 |  |  |  | PSPS - PAUL SWEET 2105 - CB PH 1 |  |  | PEND | 18251 | 3859 | 9792 | 13651 | 2.5854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5854 | 13820 | 2.6174 | CC | 08W | SH | 2023-12-25 |  |  | 2020-11-15 | 2021-12-05 | 2020-11-15 |  |  |  | 2020-12-15 | Scoped | [6 empty] | wood | [6 empty] | PSPS |  | 2020-11-19 | 2020-11-19 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF Submitted 10/4/20. Per field visit week of 10/4, likely to be a Caltrans permit and other redesigns. Requesting input from PM on starting based on current preliminary drawings or if our team may hold off until revisions are made. | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5854 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-05 17:00 |  | INPR | 2022-07-11 08:00 | 2023-01-02 17:00 |  | 2023-01-30 17:00 | [8 empty] | 500000 | 6118838.8 |  | 500000 | 0 |  | 1224% | 225872.4 |  |  |  | 2366674.1531 |  | 1 |  |  | Complete | Easement required from City of Santa Cruz. Looping in GovRel and Acquisition Agent |  |  |  | Remove |  | Santa Cruz | Santa Cruz | 36.9924 | -121.9827 | E.5025646.01 | ML |  | 2021-129 | 2021 |  |  |  | 2020-09-01 |  | Y | PAUL SWEET 2105CB | 2633 |  | PSPS
35144942 |  |  |  | *CANC* PSPS - PAUL SWEET 2105 - CB |  |  | CLSD | 3960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | [5 empty] | 2020-10-31 | [5 empty] | Cancelled | [13 empty] | PSPS - Cancled | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-09-03 |  |  |  |  | 500000 |  |  | 500000 | 0 |  |  | 0 | [8 empty] | Complete | Scope to be updated to be switching and PSPS devices | [5 empty] | Santa Cruz | Santa Cruz | 36.9924 | -121.9827 | E.5025647.01 |  |  |  | 1980 | Q3 |  |  | 2020-09-01 |  | Y | PAUL SWEET 210212850 | 2907
35144943 |  |  |  | PSPS - ROB ROY 2105 - CB |  |  | PEND | 2851.2 | 3326 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 689 | 0.13049 | CC | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-11-30 | 2020-11-30 |  |  |  | 2020-11-16 | Scoped | [6 empty] | wood |  |  |  |  | Yes |  | PSPS |  | 2020-12-03 | 2020-12-03 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Potential Coastal Commission Permit - Veg scope needed to determine if permit is triggered. (still waiting for veg scope as of 11/9/20 and 11/30/20) | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-10-06 17:00 |  | INPR | 2022-10-20 08:00 | 2022-11-21 17:00 |  | 2023-01-20 17:00 | [8 empty] | 500000 | 1744148.2 |  | 500000 | 0 |  | 348.8% | 108113.5 |  |  |  | 2768822.1575 |  | 2 |  |  | Complete | Eliminate scope. Work may trigger Coast Devel Permit (CDP) |  |  |  | Remove |  | Aptos | Santa Cruz | 36.9786 | -121.8666 | E.5025648.01 | ML |  | 2021-134 | 2021 |  |  |  | 2020-09-01 |  | Y | ROB ROY 2105CB | 2781 |  | PSPS
35144944 |  |  |  | PSPS - SNEATH LANE 1107 - LR 48338 |  |  | PEND | 739.2 | 1348 | 0 | 1348 | 0.2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2553 |  |  | PN | 08W | SH | 2022-04-14 17:00 |  |  | 2020-04-30 | 2020-10-31 | 2020-04-30 |  |  | Yes | 2020-05-29 | [5 empty] | COMPLETED | No | No | 3 | 0 |  |  | Yes |  | PSPS |  | 2021-01-15 | 2021-01-15 | [5 empty] | 2021-04-15 | 2021-04-15 |  |  |  | ** Caltrans DSDD - Pilot Project permit submitted. Enviro reviews completed. |  |  |  | Yes |  |  | Cal Trans permit only , rest of project on private property |  | 2021-03-24 |  | 2021-03-18 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2553 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-14 17:00 |  | INPR | 2022-06-01 08:00 | 2022-07-08 17:00 |  | 2022-08-05 17:00 | [5 empty] | Yes |  |  | 500000 | 1502688.3 |  | 500000 | 0 |  | 300.5% | 122631.5 |  |  |  | 5885900.7596 |  | 3 |  |  | Complete | UG 0.14 miles, install PMI9, 5 PSPS devices |  |  |  | Remove |  | South San Francisco | San Mateo | 37.6433 | -122.4679 | 35144944 | ML |  | 2021-135 | 2021 |  |  |  | 2020-09-01 |  | Y | SNEATH LANE 1107CB | 2336 |  | PSPS
35144989 |  |  |  | STS-POLE_IDLE_REMV - 10590 DESCHUTES RD |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2020-12-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.5167 | -122.2386
35145001 |  |  |  | PSPS - CLAYTON 2215 - CB |  |  | PEND | 21042 | 9720 | 375 | 10095 | 1.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9119 | 9720 | 1.8409 | DI | 08W | SH | 2023-12-25 |  |  | 2020-11-30 | 2020-11-30 | 2020-11-30 |  |  | Yes | 2020-10-16 | [7 empty] | No |  |  |  | 2020-10-21 | Yes |  | PSPS |  | 2021-01-20 | 2021-01-20 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | CIF submitted 7/7/20 - Needs easement; Potential for wetland constraints in some underground locations to be discussed with project manager in site walks. Need veg scope information for bio reports; to follow up in January; Revised final drawings sent | [6 empty] | JQ to initiate tasks in SAP - Submitted to City of Clayton on 7/28/20 - [REDACTED] to send final drawings to JQ | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9119 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-06-17 17:00 |  | INPR |  | 2023-02-07 17:00 |  | 2023-03-07 17:00 | [8 empty] | 500000 | 8124300.5 |  | 500000 | 0 |  | 1625% | 193470.2 |  |  |  | 4249262.6686 |  | 9 |  |  | Complete | UG 1.5 miles, OH 0.07 miles, 8 PSPS |  |  |  | Remove |  | Concord | Contra Costa | 0 | 0 | E.5025639.01 | ML | UG | 2021-127 | 2021 |  |  |  | 2020-09-01 |  | Y | CLAYTON 2215CB | 1739 |  | PSPS
35145002 |  |  |  | PSPS - IGNACIO 1101 - CB |  |  | PEND | 3590.4 | 6847 | 0 | 6847 | 1.2968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2968 |  |  | NB | 08W | SH | 2021-03-18 17:00 |  |  | 2020-10-31 | 2020-10-31 | 2020-10-31 | 2020-07-15 | 2020-07-15 |  | 2020-11-02 | [11 empty] | 2020-11-05 | Yes |  | PSPS |  | 2020-11-20 | 2020-11-20 |  |  |  |  | Full | 2020-11-20 | 2020-11-20 | Full |  |  | Preliminary reviews are complete. | Full | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2968 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2021-03-18 17:00 |  | INPR |  | 2021-10-15 17:00 |  | 2021-12-16 17:00 | [8 empty] | 500000 | 126659.6 |  | 500000 | 0 |  | 25.33% | 121570.7 |  |  |  | 97672.3657 |  |  |  |  | Complete | Base map provided. In estimating |  |  |  | Remove |  | Novato | Marin | 0 | 0 | E.5025640.01 | ML |  | 2021-133 | 2021 |  |  |  | 2020-09-01 |  | Y | IGNACIO 1101CB | 2448 |  | PSPS
35145003 |  |  |  | PSPS CWSP - MORAGA 1103 - CB |  |  | UNSC | 1161.6 | 1268 | 420 | 1688 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 1688 | 0.3197 | DI | 08W | SH | 2022-04-07 17:00 |  |  | 2020-05-10 | 2020-10-31 | 2020-05-10 |  |  | Yes | 2020-06-03 | [5 empty] | COMPLETED | No | YES | 10 | 4 |  |  | Yes |  | PSPS |  | 2020-07-15 | 2020-07-15 |  |  |  |  | Full | 2020-07-17 | 2020-07-17 | Full |  |  | CIF Submitted 6/1/20 | Full | [5 empty] | Submitted to [REDACTED] on 10/14/20 |  | 2020-12-21 |  | 2020-11-30 |  |  | Need to meet with GC to determine scope at creek crossing | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-07 17:00 |  | COMP | 2022-05-13 08:00 | 2022-07-22 17:00 |  | 2022-08-19 17:00 | 2020-12-10 | [7 empty] | 500000 | 1168967 |  | 942892 | 442892 |  | 233.8% | 99057.3 |  |  |  | 3656484.455 |  | 5 |  |  | Complete | UG 0.22 miles, PM 3WSW, 4 PSPS devices |  |  |  | Remove |  | Orinda | Contra Costa | 0 | 0 | E.5025641.01 | ML |  | 2021-131 | 2021 |  |  |  | 2020-09-01 |  | Y | MORAGA 1103CB | 2631 |  | PSPS
35145004 |  |  |  | PSPS CWSP - ROSSMOOR 1106 - CB |  |  | PEND | 4171.2 | 3073 | 1965 | 5038 | 0.95417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95417 | 1965 | 0.37216 | DI | 08W | SH | 2023-12-25 |  |  | 2020-06-30 | 2020-10-31 | 2020-06-30 |  |  | Yes | 2020-07-13 | [5 empty] | COMPLETED | No | YES | 21 | 1 |  |  | Yes |  | PSPS |  | 2020-11-20 | 2020-11-20 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | Easement being obtained under [REDACTED] 1109/PM# 74008802; Enviro reviews have been completed |  |  |  | Yes |  |  |  |  | 2020-12-31 |  | 2020-12-09 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95417 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-12 17:00 |  | INPR | 2022-06-24 08:00 | 2022-09-16 17:00 |  | 2022-10-14 17:00 | [8 empty] | 500000 | 2527588.6 |  | 500000 | 0 |  | 505.5% | 98527.5 |  |  |  | 2649001.1528 |  | 2 |  |  | Complete | UG 0.4 miles, OH 0.25 miles 13 PSPS devices |  |  |  | Remove |  | Lafayette | Contra Costa | 37.8624 | -122.0862 | E.5025642.01 | ML |  | 2021-128 | 2021 |  |  |  | 2020-09-01 |  | Y | ROSSMOOR 1106CB | 3259 |  | PSPS
35145005 |  |  |  | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  |  | DOCC | 2481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | [5 empty] | 2020-10-31 | [19 empty] | PSPS - Cancled | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [29 empty] | Base map provided. Need onsite meeting to finalize scope | [5 empty] | Novato | Marin | 0 | 0 | E.5025643.01 |  |  |  | 1980 |  |  |  | 2020-09-01 |  |  | STAFFORD 1101CB | 2382
35145006 |  |  |  | PSPS - STAFFORD 1101 LR 1298 |  |  | PEND | 1425.6 | 1426 | 0 | 1426 | 0.27008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27008 |  |  | NB | 08W | SH | 2023-12-25 |  |  | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-08-14 | 2020-08-14 |  | 2020-12-14 | [14 empty] | PSPS |  | 2020-11-19 | 2020-11-19 | [5 empty] | 2023-12-25 | 2023-12-25 |  |  |  | No enviro constraints identified. New ERTC date based on final design due date of 11/27 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27008 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-01-19 17:00 |  | INPR | 2022-05-19 08:00 | 2022-07-13 17:00 |  | 2022-07-13 17:00 | [8 empty] | 500000 | 1119194.6 |  | 500000 | 0 |  | 223.8% | 132483.8 |  |  |  | 4144002.446 |  |  |  |  | Complete | Base map provided. Need onsite meeting to finalize scope |  |  |  | Remove |  | Novato | Marin | 0 | 0 | E.5025644.01 | ML |  | 2021-132 | 2021 |  |  |  | 2020-09-01 |  | Y | STAFFORD 11011298 | 3483 |  | PSPS
35145458 |  |  |  | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF |  |  |  |  | 2021-02-28 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 37.758 | -120.0408
35145522 |  |  |  | PSPS - CLARKSVILLE 2104 - CB UG |  |  | PEND | 20830 | 20830 | 0 | 20830 | 3.9451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9451 |  |  | SI | 08W | SH | 2022-03-17 17:00 |  |  | 2020-06-15 | 2020-10-31 | 2020-06-15 | 2020-06-08 | 2020-06-08 | Yes | 2020-12-21 | [11 empty] | 2020-08-08 | Yes |  | PSPS |  | 2020-11-15 | 2020-11-15 |  |  |  |  | Full | 2020-08-17 | 2020-08-17 | Full |  |  | Redesign underway to avoid easement - Estimating delayed by fire rebuild | Full |  | 2020-11-30 |  |  |  | Revised drawings submitted on 10/21/20 |  |  | Y |  |  |  | Drawings Provided 5/26/2020 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9451 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-17 17:00 |  | INPR | 2022-04-11 08:00 | 2022-10-04 17:00 |  | 2022-12-05 17:00 | 2020-12-17 | [7 empty] | 500000 | 157814.8 |  | 500000 | 0 | 333739.2 | 31.56% | 156360.8 | 9900 | 166260.8 |  | 40002.9834 |  |  |  |  | Complete | need to verify ex. spare conduits to travel under Caltrans ROW. Most likely need 3rd party engineer for bridge hangers. |  |  |  | Remove |  | El Dorado Hills | El Dorado | 0 | 0 | E.5025635.01 | ML | UG | 2021-125 | 2021 |  |  |  | 2020-09-01 |  | Y | CLARKSVILLE 2104CB | 134 |  | PSPS
35145523 |  |  |  | *CANC* PSPS - FULTON 1102 HARDENING |  |  | CLSD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | [5 empty] | 2020-10-31 | [19 empty] | PSPS - Cancled | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-09-03 | [21 empty] | Most likely to be canceleled once PSS final approval or revised Fire threat district | [5 empty] | Santa Rosa | Sonoma | 38.5187 | -122.7576 | E.5025636.01 |  |  |  | 1980 |  |  |  | 2020-09-01 |  |  | FULTON 1102CB | 2036
35145524 |  | 2021 |  | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Scoped | UNSC | 3800 | 3800 | 0 | 3800 | 0.7197 | 0 | 0 | 3800 | 0.7197 | 0 | 0 | 0 | 0 | 0 | 9175 | 1.7377 | SO | 08W | SH | 2021-03-08 17:00 |  | Y | 2020-11-03 | 2020-12-10 | 2020-11-03 | 2020-08-14 | 2020-08-14 |  | 2021-02-19 | [7 empty] | wood |  |  |  | 2020-11-06 | Yes |  | PSPS |  | 2020-11-19 | 2020-11-19 | Complete |  |  |  | Full | 2020-11-19 | 2020-11-19 | Full |  |  | No enviro constraints identified | Full |  | 2021-03-02 |  | 2022-12-31 |  |  |  | 2021-03-03 | Y | 2021-02-22 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7197 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-08 17:00 |  | COMP | 2021-03-29 08:00 | 2021-07-29 17:00 |  | 2021-09-29 17:00 | 2021-03-06 | 2021-04-26 13:04 | 2021-06-04 12:37 | [5 empty] | 500000 | 3186384.5 | 19836.3 | 8431936 | 7931936 | 322206.6 | 637.3% | 177792.1 | 1.3 | 177793.4 |  | 4427397.4105 |  |  |  |  | Complete | waiting for basemaps | [5 empty] | Santa Rosa | Sonoma | 0 | 0 | E.5025637.01 |  |  | 2021-126 | 2021 |  |  |  | 2020-09-01 |  | Y | RINCON 1103CB | 1755 |  | PSPS |  | 2021-03-09 08:34
35145525 |  | 2021 |  | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Scoped | UNSC | 9398.4 | 7819 | 1056 | 8875 | 1.6809 | 0 | 0 | 8875 | 1.6809 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-03-02 |  | Y | 2020-10-31 | 2020-10-31 | 2020-10-31 | 2020-07-03 | 2020-07-03 |  | 2021-02-23 | [7 empty] | wood |  |  |  | 2020-10-28 | Yes |  | PSPS |  | 2020-11-19 | 2020-11-19 | Complete |  |  |  | Full | 2020-11-19 | 2020-11-19 | Full |  |  | No enviro constraints identified | Full |  | 2021-03-02 | [5 empty] | 2021-03-03 | Y | 2021-02-22 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6809 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-02 |  | COMP | 2021-04-12 08:00 | 2021-07-29 17:00 |  | 2021-09-29 17:00 | 2021-03-03 | 2021-03-29 06:18 | 2021-05-28 06:33 | [5 empty] | 5901787.4 | 3044391.5 | 18928.2 | 7914493 | 2012705.6 |  | 51.58% | 162711.4 |  |  |  | 1811198.5487 |  |  |  |  | Complete | waiting for basemaps | [5 empty] | Santa Rosa | Sonoma | 0 | 0 | E.5025638.01 |  |  | 2021-130 | 2021 |  |  |  | 2020-09-01 |  | Y | RINCON 1104CB | 3302 |  | PSPS |  | 2021-03-09 08:34
35145540 |  | 2021 |  | PSPS - FROGTOWN 1702 - CB |  | Scoped | PEND | 5780 | 2846 | 3872 | 6718 | 1.2723 | 0 | 0 | 6718 | 1.2723 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | SH | 2021-05-27 17:00 |  | Y | 2020-08-19 | 2020-10-31 | 2020-08-19 | 2020-05-22 | 2020-05-22 | Yes | 2020-09-02 | [7 empty] | wood |  |  |  | 2020-09-21 | Yes |  | PSPS |  | 2021-04-10 | 2021-04-10 | Complete | 2021-03-15 |  |  |  | 2021-04-10 | 2021-04-10 |  |  |  | ** Caltrans DSDD - Finalized drawings provided 8/20/2020, Easement fully executed. Need Caltrans Permit. Enviro reviews are complete. |  |  | 2020-10-13 | Yes | 2021-10-13 |  | App submitted on 10/1/20 - [REDACTED] checking with City of Angels Camp. |  | 2021-02-12 | Y | 2020-12-01 | 2020-11-30 |  | Finalized drawings provided 8/20/2020. Requeste Arborist quote. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2723 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-27 17:00 |  | INPR | 2021-06-15 08:00 | 2021-10-12 17:00 |  | 2021-12-13 17:00 | [8 empty] | 500000 | 4354752.4 | 4139274.6 | 500000 | 0 | 228306.4 | 871% | 237918.6 | 33775 | 271693.6 |  | 3422609.8053 |  |  |  |  | Complete | waiting for basemaps. Need 3rd party engineer to design bridge hangers within Caltrans ROW | [5 empty] | Angels Camp | Calaveras | 38.0453 | -120.5253 | E.5025634.01 | ML | MX | 2021-136 | 2021 |  |  |  | 2020-09-01 |  | Y | FROGTOWN 1702CB | 1316 |  | PSPS
35146106 |  | 2021 | Voltage Complaint | RECONDUCTOR - USASA - PHASE II - SM1104 |  | Scoped | CONS |  | 0 | 19299 | 19299 | 3.6551 | 0 | 0 | 19299 | 3.6551 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 06H | Other | 2020-10-12 |  |  |  | 2020-08-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6551 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2020-10-12 |  | N/A | 2021-03-03 | 2021-05-28 17:00 |  | 2021-05-28 17:00 |  | 2021-03-09 07:00 | 2021-05-31 16:00 | [5 empty] | 3853278 | 3158379.6 | 3600000 | 5080736 | 1227458 | 3252823.6 | 81.96% | 562453.4 | 38001 | 600454.4 |  | 864098.8801 | [11 empty] | Paso Robles | San Luis Obispo | 0 | 0 | [10 empty] | Y | [5 empty] | 2021-03-04 14:15
35146183 |  |  |  | STS-OFAC_IDLE_REMV - R/O 3200 AUBURN FOL |  |  | UNSC |  | 0 | 300 | 300 | 0.056818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -0.007197 |  |  | SI | 2AF | IF | [60 empty] | 0 | 0 | 338 | 0.064015 | 0 | 0 | 0.064015 | -0.007197 | 0.064015 | 0 | 0.064015 | 0 | 0 | 0.064015 |  |  |  |  | N/A | [7 empty] | 2019-10-04 | [29 empty] | 38.8342 | -121.1217
35147045 |  |  |  | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC |  |  | CLSD | 2562 | 2100 | 0 | 2100 | 0.39773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39773 |  |  | MI | 08W | [5 empty] | 2020-10-31 | [5 empty] | Cancelled | [13 empty] | PSPS - Cancled | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39773 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-10-03 |  |  |  |  | 500000 |  |  | 500000 | 0 | [8 empty] | 1 |  |  | Pending | Add scope. | [5 empty] | Castro Valley | Alameda | 37.6962 | -122.05 | 35147045 |  |  |  | 1980 | Q3 |  |  | 2020-09-01 |  | Y | CASTRO VALLEY 1108MR341 | 2486
35149197 |  |  |  | STS-POLE_IDLE_REMV-HWY 169 MP 29.32 |  |  | FICL |  | 0 | 339 | 339 | 0.064205 | 339 | 0.064205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2020-04-10 | [55 empty] | 0 | 0 | 339 | 0.064205 | 0 | 0 | 0.064205 | 0 | 0.037879 | 0 | 0.037879 | 0 | 0.026326 | 0.037879 |  |  |  |  | N/A | [7 empty] | 2020-07-01 | [29 empty] | 41.1309 | -123.4587
35150545 |  |  |  | STS-COND_IDLE_REMV- |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 2AF | IF |  |  |  |  | 2020-12-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 38.8882 | -122.5929
35155226 |  |  |  | STS-OFAC_IDLE_REMV - #1 E/O 152 LA HONDA |  |  | PEND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 2AA | IF |  |  |  |  | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 37.3547 | -122.2661
35155680 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  |  | UNSE | 6990 | 0 | 6990 | 6990 | 1.3239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3239 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3239 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Grass Valley | Nevada | 39.2055 | -121.0214 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155681 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  |  | UNSE | 1335 | 0 | 1335 | 1335 | 0.25284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25284 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25284 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155682 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  |  | UNSE | 1930 | 0 | 1930 | 1930 | 0.36553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36553 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36553 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155683 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  |  | UNSE | 6550 | 0 | 6550 | 6550 | 1.2405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2405 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2405 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155684 |  |  |  | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  |  | UNSE | 3288 | 0 | 3288 | 3288 | 0.62273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62273 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62273 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155685 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  |  | UNSE | 3780 | 0 | 3780 | 3780 | 0.71591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71591 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71591 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155686 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  |  | UNSE | 3240 | 0 | 3240 | 3240 | 0.61364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61364 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61364 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155687 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  |  | UNSE | 8886 | 0 | 8886 | 8886 | 1.683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.683 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.683 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155688 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  |  | UNSE | 2961 | 0 | 2961 | 2961 | 0.5608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5608 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5608 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155689 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  |  | UNSE | 4900 | 0 | 4900 | 4900 | 0.92803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92803 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92803 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155690 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  |  | UNSE | 5082 | 0 | 5082 | 5082 | 0.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9625 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9625 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155691 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  |  | UNSE | 3010 | 0 | 3010 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155692 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  |  | UNSE | 5268 | 0 | 5268 | 5268 | 0.99773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99773 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99773 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155693 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  |  | UNSE | 6100 | 0 | 6100 | 6100 | 1.1553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155694 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  |  | UNSE | 5900 | 0 | 5900 | 5900 | 1.1174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1174 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1174 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155695 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  |  | UNSE | 5465 | 0 | 5465 | 5465 | 1.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.035 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.035 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155696 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  |  | UNSE | 2440 | 0 | 2440 | 2440 | 0.46212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46212 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46212 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155697 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  |  | UNSE | 2080 | 0 | 2080 | 2080 | 0.39394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39394 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39394 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155698 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  |  | UNSE | 6332 | 0 | 6332 | 6332 | 1.1992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1992 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1992 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155699 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  |  | UNSE | 2415 | 0 | 2415 | 2415 | 0.45739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45739 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45739 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155740 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 |  |  | UNSE | 3636 | 0 | 3636 | 3636 | 0.68864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68864 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68864 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155741 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  |  | UNSE | 890 | 0 | 890 | 890 | 0.16856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16856 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16856 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155742 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  |  | UNSE | 6100 | 0 | 6100 | 6100 | 1.1553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1553 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155743 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 |  |  | UNSE | 3692 | 0 | 3692 | 3692 | 0.69924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69924 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69924 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155744 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 |  |  | UNSE | 2671 | 0 | 2671 | 2671 | 0.50587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50587 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50587 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155746 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  |  | UNSE | 5910 | 0 | 5910 | 5910 | 1.1193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1193 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1193 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155747 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 |  |  | UNSE | 4025 | 0 | 4025 | 4025 | 0.76231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76231 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76231 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155748 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 |  |  | UNSE | 2740 | 0 | 2740 | 2740 | 0.51894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51894 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51894 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155749 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 |  |  | UNSE | 2662 | 0 | 2662 | 2662 | 0.50417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50417 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.50417 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155750 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  |  | UNSE | 8872 | 0 | 8872 | 8872 | 1.6803 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6803 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6803 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155751 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  |  | UNSE | 2627 | 0 | 2627 | 2627 | 0.49754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49754 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49754 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155752 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  |  | UNSE | 2727 | 0 | 2727 | 2727 | 0.51648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51648 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51648 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155753 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  |  | UNSE | 5611 | 0 | 5611 | 5611 | 1.0627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0627 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0627 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155754 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  |  | UNSE | 6626 | 0 | 6626 | 6626 | 1.2549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2549 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2549 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155755 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  |  | UNSE | 1431 | 0 | 1431 | 1431 | 0.27102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27102 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27102 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155756 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  |  | UNSE | 9214 | 0 | 9214 | 9214 | 1.7451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7451 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7451 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155757 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 |  |  | UNSE | 2913 | 0 | 2913 | 2913 | 0.5517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5517 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5517 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155758 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  |  | UNSE | 3510 | 0 | 3510 | 3510 | 0.66477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66477 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66477 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155759 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 |  |  | UNSE | 3500 | 0 | 3500 | 3500 | 0.66288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66288 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66288 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155840 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 |  |  | UNSE | 2596 | 0 | 2596 | 2596 | 0.49167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49167 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.49167 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155841 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  |  | UNSE | 4491 | 0 | 4491 | 4491 | 0.85057 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85057 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85057 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35155842 |  |  |  | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  |  | UNSE | 808 | 0 | 808 | 808 | 0.15303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15303 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15303 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Nevada City | Nevada | 0 | 0 |  |  |  |  | 999 | [6 empty] | BRUNSWICK 11052140 | 22
35157258 |  |  |  | STS-COND_IDLE_REMV - 2712-2734 E WESTFAL |  |  | FICL |  | 0 | 100 | 100 | 0.018939 | 100 | 0.018939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 100 | 0.018939 | 0 | 0 | 0.018939 | 0 | 0 | 0 | 0.018939 | 0.018939 | 0.018939 | 0 |  | Keep |  |  | N/A | [7 empty] | 2020-08-26 | [29 empty] | 37.4804 | -119.7748
35157845 |  | 2021 | 220 Mile Plan | SILVERADO 2105 WIRE DOWN - PH 3 |  |  | CONS | 6164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W |  | 2020-07-06 |  |  | 2019-07-23 |  | 2019-07-23 |  |  | Yes | 2020-06-30 | [5 empty] | 100 | No | [5 empty] | Yes |  |  |  | 2020-04-30 | 2020-04-30 |  |  |  |  | Full | 2020-04-30 | 2020-04-30 | Full |  |  | UG land rights needed. Home owner started review of proposal 8/23. Redesign due around 2/14/20Update 3/9/20-still pending the project redesign info. With the final segment of the project under new order number, we'll need to complete this task and create new project to track this follow up. -Received drawings 3/23; ERTC to be issued before 4/30 | Full |  |  | Yes | 2021-09-18 |  |  |  | 2020-05-04 | Y | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2676 | 1.2676 | 0 | 0 |  |  |  | Yes | COMP |  |  |  |  | 2020-07-01 |  |  |  | 2020-07-06 | Yes | Shovel Ready |  | 1404334.4 |  |  | 1800635 | 396300.6 |  |  | 432195.3 | [5 empty] | 18 |  | 100% complete | [7 empty] | Saint Helena | Napa | 38.5244 | -122.5511 | E.5014317.04 |  |  |  | 2020 | Q3 | 2019-07-23 | 2020-04-06 | 2020-05-07 |  | Y | SILVERADO 2105658898 | 1361 |  | WDDB
35158717 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  |  | ADER | 7740 | 0 | 7561 | 7561 | 1.432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.432 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 11/01: ADE assigned (Brad) 10/30: CAL submitted for 1st ADE rvw 10/28: PMgr Request for 'Desired EOD' - 01/07 (Jan); 1st sub dependency 11/08 (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M1 [R2021_152] | R1.2 - ADE Review in Progress |  | Wood | 36 | 5 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.432 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 250000 | 2823203.5 |  | 250000 | 0 |  | 1129% | 95524.1 |  |  |  | 1971500.3941 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL |  | 2021-152 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160091 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  |  | ADER | 3447 | 106 | 3432 | 3538 | 0.67008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67008 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/29: ADE assigned (Michael) 10/28: CAL submitted for 1st ADE rvw 10/28: PMgr Request for 'Desired EOD' - 10/26 (OCT; 1st sub dependency expired (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_153] | R1.2 - ADE Review in Progress |  | Wood | 4 | 1 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67008 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 250000 | 1388547.9 |  | 250000 | 0 |  | 555.4% | 90260.7 |  |  |  | 2072225.2436 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-153 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160093 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  |  | ESTS | 6360 | 0 | 6494 | 6494 | 1.2299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2299 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 11/04: EST sub (11/6); CNCS still pending 10/28: PMgr Request for 'Desired EOD' - 12/24 (Dec); 1st sub dependency expired (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M1 [R2021_154] | R0.0 - Estimating |  | Wood | 25 | 13 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2299 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 250000 | 2091297.2 |  | 250000 | 0 |  | 836.5% | 45016.8 |  |  |  | 1700346.3529 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-154 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160094 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  |  | ESTS | 6145 | 0 | 6312 | 6312 | 1.1955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1955 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 11/04: ADE assigned (Ed) 11/03: CAL submitted for 1st ADE rvw 10/28: PMgr Request for 'Desired EOD' - 02/05 (Feb); 1st sub dependency 12/07 (T-60); TBD ?? 09/30 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_155] | R1.2 - ADE Review in Progress |  | Wood | 28 | 4 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1955 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 250000 | 2331386.7 |  | 250000 | 0 |  | 932.5% | 44835.1 |  |  |  | 1950209.4068 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-155 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160095 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  |  | ESTS | 9380 | 2376 | 7022 | 9398 | 1.7799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: PMgr Request for 'Desired EOD' - 12/02 (Dec); 1st sub dependency expired (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_156] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [9 empty] | Yes |  |  | 250000 | 3567459.2 |  | 250000 | 0 |  | 1427% | 63495 |  |  |  | 2004275.8647 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-156 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160096 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  |  | ESTS | 5330 | 4646 | 686 | 5332 | 1.0098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M1 [R2021_157] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0098 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [9 empty] | Yes |  |  | 250000 | 1989298.4 |  | 250000 | 0 |  | 795.7% | 71164.4 |  |  |  | 1969897.8905 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX |  | 2021-157 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160097 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  |  | ADER | 10570 | 5910 | 5015 | 10925 | 2.0691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0691 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 11/02: ADE assigned ( [REDACTED] )11/02: CAL submitted for 1st ADE rvw10/28: PMgr Request for 'Desired EOD' - 10/27 (OCT); 1st sub dependency expired (T-60); NO ??10/21 - 09/16: On Track08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_158] | R1.2 - ADE Review in Progress |  | Wood | 51 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0691 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [9 empty] | Yes |  |  | 250000 | 3846140.7 |  | 250000 | 0 |  | 1538% | 59541.3 |  |  |  | 1858821.3177 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL |  | 2021-158 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160098 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  |  | ESTS | 4895 | 0 | 5500 | 5500 | 1.0417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0417 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 11/04: EST target sub (11/13) 10/28: PMgr Request for 'Desired EOD' - 12/27 (Dec); 1st sub dependency expired (T-60); NO ?? 10/21 - 09/16: On Track 08/26: Meeting scheduled w JO 8/31; 30% fielded - post meeting will conduct further fldng 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_159] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0417 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [9 empty] | Yes |  |  | 250000 | 1837614 |  | 250000 | 0 |  | 735% | 59017.3 |  |  |  | 1764109.44 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL |  | 2021-159 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160341 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  |  | ESTS | 8165 | 1750 | 6415 | 8165 | 1.5464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5464 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: Survey in - started 10/14: Survey anticipated to be received Fri (10/16) 09/16: EST approved for conducting surveying (6wk turn-around) 08/26: SCOPE CHANGE - UG removal and OH added 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_161] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5464 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-03-13 17:00 |  | N/A | 2023-04-05 08:00 | 2023-08-16 17:00 |  | 2023-10-17 17:00 | [5 empty] | Yes |  |  | 71428 | 4392.4 |  | 71428 | 0 |  | 6.14% | 4246.4 |  |  |  | 2840.4007 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | ML | MX | 2021-161 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160342 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  |  | ESTS | 7840 | 5400 | 2440 | 7840 | 1.4848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4848 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: Survey in - started 10/14: Survey anticipated to be received Fri (10/16) 09/16: EST approved for conducting surveying (6wk turn-around) 08/26: SCOPE CHANGE - UG removal and OH added 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_162] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4848 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-03-13 17:00 |  | N/A | 2023-04-05 08:00 | 2023-08-16 17:00 |  | 2023-10-17 17:00 | [5 empty] | Yes |  |  | 71428 | 6013.5 |  | 71428 | 0 |  | 8.41% | 5856.1 |  |  |  | 4049.9082 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | MX | MX | 2021-162 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160343 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  |  | ESTS | 13875 | 0 | 13875 | 13875 | 2.6278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6278 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_163] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6278 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-14 17:00 |  | N/A | 2022-03-22 08:00 | 2022-08-02 17:00 |  | 2022-10-03 17:00 | [5 empty] | Yes |  |  | 71428 | 940.8 |  | 71428 | 0 |  | 1.31% | 924.9 |  |  |  | 358.0125 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL | OH | 2021-163 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160344 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  |  | ESTS | 14192 | 0 | 14192 | 14192 | 2.6879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6879 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_164] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6879 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-03-06 17:00 |  | N/A | 2023-03-14 08:00 | 2023-07-25 17:00 |  | 2023-09-25 17:00 | [5 empty] | Yes |  |  | 71428 | 1662.5 |  | 71428 | 0 |  | 2.32% | 1638.2 |  |  |  | 618.5175 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL | OH | 2021-164 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160345 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  |  | ESTS | 17520 | 0 | 17520 | 17520 | 3.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3182 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_165] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3182 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2023-03-06 17:00 |  | N/A | 2023-03-14 08:00 | 2023-07-25 17:00 |  | 2023-09-25 17:00 | [5 empty] | Yes |  |  | 71428 | 3599.3 |  | 71428 | 0 |  | 5.03% | 3515.6 |  |  |  | 1084.7205 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL | OH | 2021-165 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35160346 |  |  |  | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  |  | ESTS | 2960 | 2960 | 0 | 2960 | 0.56061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56061 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: Survey in - started 10/14: Survey anticipated to be received Fri (10/16) 09/16: EST approved for conducting surveying (6wk turn-around) 08/26: SCOPE CHANGE - UG removal and OH added 08/12: Review design approach - multiple OH/UG switch ups; High qty of private property - EST reviewing with PMgr 08/10: Issued to Vendor - EST to finalize a 1st submittal date |  |  |  | 2021 - Q1- M2 [R2021_166] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.56061 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-03-03 17:00 |  | N/A | 2022-03-11 08:00 | 2022-07-22 17:00 |  | 2022-09-22 17:00 | [5 empty] | Yes |  |  | 71428 | 22137.3 |  | 71428 | 0 |  | 30.99% | 22117.6 |  |  |  | 39488.1568 |  |  |  |  | Complete |  |  |  |  | Remove |  | Nevada City | Nevada | 0 | 0 |  | TL | MX | 2021-166 | 2021 | [5 empty] | Y | BRUNSWICK 11052210 | 21
35162302 |  |  |  | STS-COND_IDLE_REMV - 2SW/O 10640 OAK RUN |  |  | PEND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2020-08-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.5988 | -122.1675
35167136 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 |  |  | ESTS |  | 0 | 5000 | 5000 | 0.94697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 10/28: EST to review if 02/07 Desired EOD can be met - 1st sub target 12/1 (No)08/10: Issued to Vendor |  |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.94697 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-04-25 17:00 |  | N/A | 2022-05-25 08:00 | 2022-10-05 17:00 |  | 2022-12-06 17:00 | [5 empty] | Yes |  |  | 166667 |  |  | 166667 | 0 |  |  | 214.6 | [8 empty] | Complete |  |  |  |  | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461 |  | MX |  | 2021-149 | 2021 | [5 empty] | Y
35167138 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  |  | ESTS |  | 0 | 10745 | 10745 | 2.035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.035 |  |  | SI | 08W | SH | 2023-12-25 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [13 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.035 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-23 17:00 |  | N/A | 2022-06-22 08:00 | 2022-11-02 17:00 |  | 2023-01-03 17:00 | [5 empty] | Yes |  |  | 166667 | 980.2 |  | 166667 | 0 |  | 0.58% | 963.7 |  |  |  | 481.6618 |  |  |  |  | Complete |  |  |  |  | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461 |  | TL |  | 2021-150 | 2021 | [5 empty] | Y
35168820 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-02-28 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35168821 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-02-28 |  |  | 2021-02-28 | 2021-03-31 | 2021-02-28 | 2021-01-24 | 2021-01-24 |  |  | 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M2 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35168822 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-01-31 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M1 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35168823 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W |  | 2021-01-31 |  |  | 2021-01-31 | 2021-03-31 | 2021-01-31 | 2020-12-27 | 2020-12-27 |  |  | 08/10: Issued to Vendor |  |  |  | 2021 - Q1- M1 [R2021_148] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35170202 |  |  |  | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W |  | 2022-04-08 17:00 |  |  | 2021-01-31 |  | 2021-01-31 | 2021-01-01 | 2021-01-01 |  |  | 11/04 - 10/28: EOD Push (Jan); Easement being drawn up; Land avg 2-3 months to process 10/21 - 10/21: Survey complete; easement being drawn up. Will start design upon completion. 10/14: Fires cleared; survey map sent in; clearing up some Q&A - may need refielding, survey identified a more optimal location. 10/07: Fielding held up due to fires 09/02: On Track 08/26: Push Est sub Sept to Nov; With Land to write up easement (potential to take 90days) 08/19: On track - meeting 08/12: Meeting next Wens (1hr) and Del Oro Water 08/05: Meeting sched next coming week(s) with PID to iron out details 08/05: USER STATUS - UNSE ?? 07/29 - 07/08: EST sub (9/18); Round 2 PID 07/01 - 06/24: EST On Track 06/17: 1st sub set (7/24); PID 06/10 - 05/13: Still waiting on response; push 1st sub 05/06 - 04/15: On Track; PID - EST waiting on version to use; will submit once advised. 04/08: 1st sub date; in review on 'how' to design/execute 04/03: requested to avoid delaying of PM#35094515 (Oro Fino 1101 – LR2022 PH1.1) due to dependencies for circuit reroute inside Paradise Irrigation district |  |  |  | 2021 - Q1- M1 [R2022(+)_14] | R0.0 - Estimating |  | Wood (QTY TBD) | 0 | 0 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  | 2022-04-08 17:00 |  | INPR | 2022-07-04 08:00 | 2023-01-09 17:00 |  | 2023-02-06 17:00 | [8 empty] | 271429 | 83066.8 |  | 271429 | 0 |  | 30.6% | 12557.1 | [8 empty] | Complete | [6 empty] | Magalia | Butte | 0 | 0 |  | ML | OH | [7 empty] | Y
35171354 |  | 2020 | 220 Mile Plan | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  |  | CLSD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | SH | [9 empty] | 2020-05-14 | [50 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  | Yes | N/A |  |  |  |  | 2020-06-11 | 2020-04-29 | 2020-04-29 | 2020-04-29 |  |  | Shovel Ready |  |  |  |  | 37409.67 |  |  |  | 39600.7 | [15 empty] | Scotts Valley | Santa Cruz | 37.1013 | -121.979 | [10 empty] | Y
35173253 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 100000 |  |  | 100000 | 0 |  |  | 509.4 | [15 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y
35173255 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 100000 |  |  | 100000 | 0 |  |  | 1534.6 | [15 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y
35173320 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 100000 |  |  | 100000 | 0 |  |  | 509.4 | [15 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y
35173321 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [12 empty] | 100000 |  |  | 100000 | 0 |  |  | 509.4 | [15 empty] | El Dorado Hills | El Dorado | 0 | 0 |  |  |  |  | 999 | [5 empty] | Y
35173754 |  |  |  | ECOP-BRUNSWICK 1106-H08-LR51486 |  |  | UNSE |  | 0 | 33264 | 33264 | 6.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.3 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [12 empty] | 884000 | 12099820.8 |  | 884000 | 0 |  | 1369% | 24766.8 |  |  |  | 1920606.4762 |  |  |  |  | Meeting Required |  |  |  |  | Remove |  | Grass Valley | Nevada | 39.1678 | -120.966 |  | MX |  | 2021-066 | 2021 | [5 empty] | Y | BRUNSWICK 110651486 | 35
35173755 |  |  |  | ECOP-WEST POINT 1101-H02-LR36674 |  |  | ESTS |  | 0 | 12038.4 | 12038.4 | 2.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.28 |  |  | ST | 08W | SH | 2023-12-25 |  |  | 2021-01-15 | 2021-01-15 | 2021-01-15 |  |  |  |  | waiting for Field Scoping checklist | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.28 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [28 empty] | Complete | Scoping Meeting on 7/16/20 |  |  |  | Remove |  | Pioneer | Amador | 38.507 | -120.4931 |  |  |  | 2021-069 | 2021 | [6 empty] | WEST POINT 110136674 | 38
35173756 |  |  |  | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  |  | UNSE |  | 0 | 47520 | 47520 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-16 17:00 |  | N/A | 2022-06-08 08:00 | 2022-10-19 17:00 |  | 2022-12-20 17:00 | [8 empty] | 950000 | 8390 |  | 950000 | 0 |  | 0.88% | 8385.4 |  |  |  | 932.2222 |  |  |  |  | Meeting Required |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.761 | -120.5582 |  | MX |  | 2021-059 | 2021 | [5 empty] | Y
35173959 |  |  |  | CWSP-MIWUK 1702-LR 38218-PH 1.6 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W |  | 2020-12-31 |  |  | 2020-12-31 |  | 2020-12-31 | 2020-10-28 | 2020-10-28 |  |  | 11/04: ADE in rvw; priority based; target mid wk (11/11) 10/28: QUES submitted corrections for 2nd ADE rvw 10/21; Working with Planner for solution to ADE question 10/14 - 10/07: Submittal by 10/23 09/25: ADE rtn 1st corrections to CO 09/15: QUES submitted for 1st ADE rvw; ADE assigned (Donald) 09/02: EST sub (9/11); Transformer items require refield 09/01 - 08/26: EST target sub (9/8); finish stampting 08/19: On Track 08/12: EST target sub (8/31); going into EST internal rvw 08/05: EST to follow up, rvw if 1.2 change impacts this pc 08/05 - 07/08: Dependant on 1.2; Estimator going on leave to be reassigned 07/01 - 06/17: EST 1st sub set (07/31) 06/10- 05/13: EST working 1.2 priority; EST push 1st sub (6/05) 05/06: EST reviewing scope of activities - Sub to be firmed up. 04/29: EST reassignment - new EST coming up to speed, review current state and action items; 1 Sub TBD; ADE pre-assigned (Donald) to align with 35116441 reviews 4/23: PM created for segment coming from PM 35116441; EST working on resource assignment and fielding; 1st sub date TBD |  |  |  | 2020 - Q4- M12 [R2022(+)_] | R2.2 - ADE Review in Progress |  | Wood | 50 | 9 | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Twain Harte | Tuolumne | 38.0486 | -120.2438
35174085 |  | 2020 |  | PSPS - FIA320 - LR @ 101269978 |  |  | UNSC |  | 0 | 528 | 528 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 |  |  | ST | 08W | SH | [9 empty] | 2020-05-11 | [50 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  |  |  | 2020-08-04 | 2021-04-01 07:00 | 2021-04-06 16:00 | [28 empty] | Angels Camp | Calaveras | 38.0878 | -120.5693 | [16 empty] | 2021-03-11 08:46
35174174 |  |  |  | ECOP-STANISLAUS 1702-H03-LR1850 |  |  | UNSE |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 |  |  | ST | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove | [8 empty] | 2021-071 | 2021 | [6 empty] | ECOP - STANISLAUS 1702 - H03 - LR1850 | 66
35174308 |  |  |  | STS-OFAC_IDLE_REMV - 2S/O 1E/O C/O 6699 |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.5867 | -121.935
35174465 |  |  |  | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  |  | UNSE |  | 0 | 47520 | 47520 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-16 17:00 |  | N/A | 2022-06-08 08:00 | 2022-10-19 17:00 |  | 2022-12-20 17:00 | [8 empty] | 950000 |  |  | 950000 | 0 |  |  | 19639 | [8 empty] | Meeting Required |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.761 | -120.5582 |  | MX |  | 2021-057 | 2021 | [5 empty] | Y | EL DORADO PH 21016852 | 18
35174466 |  |  |  | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  |  | UNSE |  | 0 | 38808 | 38808 | 7.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.35 |  |  | SI | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.35 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-05-10 17:00 |  | N/A | 2022-06-02 08:00 | 2022-10-13 17:00 |  | 2022-12-14 17:00 | [8 empty] | 950000 | 12443.4 |  | 950000 | 0 |  | 1.3% | 12429.8 |  |  |  | 1692.9796 |  |  |  |  | Meeting Required |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.761 | -120.5582 |  | MX |  | 2021-060 | 2021 | [5 empty] | Y
35174467 |  |  |  | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  |  | ESTS |  | 0 | 31680 | 31680 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  |  | ST | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Arnold | Calaveras | 38.2392 | -120.3364 |  |  |  | 2021-067 | 2021 | [6 empty] | STANISLAUS 170237276 | 37
35174468 |  |  |  | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  |  | ESTS |  | 0 | 30202 | 30202 | 5.7201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7201 |  |  | ST | 08W | SH | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7201 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Arnold | Calaveras | 38.2392 | -120.3364 |  |  |  | 2021-068 | 2021 | [6 empty] | STANISLAUS 170237276 | 37
35174469 |  |  |  | ECOP-PINE GROVE 1102-H01-LR45292 |  |  | ESTS |  | 0 | 57446.4 | 57446.4 | 10.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.88 |  |  | ST | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.88 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Pioneer | Amador | 38.4537 | -120.5301 |  |  |  | 2021-034 | 2021 | [6 empty] | PINE GROVE 110245292 | 5
35174470 |  |  |  | ECOP-MOLINO 1102-H01-LR318 |  |  | UNSE |  | 0 | 13728 | 13728 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 |  |  | SO | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Occidental | Sonoma | 38.3996 | -122.9586 |  |  |  | 2021-070 | 2021 | [6 empty] | MOLINO 1102318 | 39
35174471 |  |  |  | ECOP-MONTE RIO 1113-H07-LR180 |  |  | UNSE |  | 0 | 5280 | 5280 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | SO | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove | [8 empty] | 2021-073 | 2021
35174472 |  |  |  | ECOP-CALISTOGA 1101-H02-LR43924 |  |  | UNSE |  | 0 | 9979.2 | 9979.2 | 1.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.89 |  |  | NB | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.89 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5719 | -122.5924 |  |  |  | 2021-062 | 2021 | [6 empty] | CALISTOGA 110143924 | 34
35174473 |  |  |  | ECOP-CALISTOGA 1101-H03-LR43924 |  |  | UNSE |  | 0 | 9610 | 9610 | 1.8201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 |  |  | NB | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8201 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5814 | -122.5963 |  |  |  | 2021-064 | 2021 | [6 empty] | CALISTOGA 110143924 | 34
35174474 |  |  |  | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  |  | UNSE |  | 0 | 23232 | 23232 | 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 |  |  | NB | 08W | SH | 2023-12-25 | [9 empty] | Waiting for scoping session | [22 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5803 | -122.598 |  |  |  | 2021-058 | 2021 | [6 empty] | CALISTOGA 1101736 | 24
35174475 |  |  |  | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  |  | UNSE |  | 0 | 15628.8 | 15628.8 | 2.96 | 0 | 0 | 0 | 0 | 15628.8 | 2.96 | 0 | 0 | 0 |  |  | NB | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.96 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5476 | -122.5796
35174476 |  |  |  | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  |  | UNSE |  | 0 | 46358.4 | 46358.4 | 8.78 | 0 | 0 | 0 | 0 | 46358.4 | 8.78 | 0 | 0 | 0 |  |  | SO | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.78 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5596 | -122.6262
35174477 |  |  |  | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  |  | UNSE |  | 0 | 50318.4 | 50318.4 | 9.53 | 0 | 0 | 0 | 0 | 50318.4 | 9.53 | 0 | 0 | 0 |  |  | NB | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.53 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5803 | -122.598
35174478 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Scoped | UNSE |  | 5491.2 | 0 | 5491.2 | 1.04 | 0 | 0 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 1667.1 | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-061 | 2021 | [5 empty] | Y | MIDDLETOWN 1101548 | 474 | 35174478 | ECOP |  | 2021-03-11 13:58
35174479 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Scoped | UNSE |  | 0 | 3761 | 3761 | 0.71231 | 0 | 0 | 0 | 0 | 3761 | 0.71231 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71231 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 67857 |  |  |  | 14039 | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-063 | 2021 | [5 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 13:59
35174501 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Scoped | UNSE |  | 21597 | 0 | 21597 | 4.0903 | 0 | 0 | 0 | 0 | 21597 | 4.0903 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0903 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 22431.3 | [15 empty] | Middletown | Lake | 38.3526 | -122.5226 |  |  |  | 2021-065 | 2021 | [5 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-11 13:59
35174993 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35175843 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175844 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175845 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175846 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175847 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175848 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175849 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175850 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175852 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175853 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | In Scoping | UNSE |  | 0 | 5280 | 5280 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Georgetown | El Dorado | 0 | 0 | [12 empty] | 2131 |  | REMG
35175854 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175855 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175856 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175857 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175858 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35175859 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35176209 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35176210 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 38.9354 | -120.7461
35176211 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0
35176497 |  |  |  | ECOP-STANISLAUS 1702-H03-LR1850 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Arnold | Calaveras | 38.2656 | -120.3398
35176549 |  |  |  | ECOP-MONTE RIO 1113-H07-LR180 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Guerneville | Sonoma | 38.4999 | -123.022
35177107 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16
35177108 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16
35177109 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16
35177110 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16
35177111 |  |  |  | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Georgetown | El Dorado | 0 | 0 | [11 empty] | PLACERVILLE 21061104 | 16
35181199 |  |  |  | ECOP-WEST POINT 1101-H03-TS L373 |  |  | ESTS |  | 0 | 13306 | 13306 | 2.5201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5201 |  |  | ST | 08W | SH | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [33 empty] | Remove |  | Pioneer | Amador | 38.4887 | -120.5375 |  |  |  | 2021-072 | 2021 | [6 empty] | WEST POINT 1101L373 | 69
35185022 |  | 2021 |  | INSTALL 3RD PHASE ON ALLEGHANY 1101 |  |  | UNSC |  | 0 | 800 | 800 | 0.15152 | 0 | 0 | 800 | 0.15152 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 06I |  | 2021-02-25 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15152 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-02-25 17:00 |  | N/A | 2021-03-19 08:00 | 2021-04-30 17:00 |  | 2021-04-30 17:00 |  | 2021-03-23 07:00 | 2021-04-09 16:00 | [5 empty] | 95000 | 360963.9 | 504125.7 | 335994.97 | 240994.97 | -113679.1 | 380% | 98177.1 | 110502 | 208679.1 |  | 2382361.74 | [11 empty] | Nevada City | Nevada | 39.3635 | -120.7913 | [10 empty] | Y
35191130 |  |  |  | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  |  | UNSE |  | 0 | 42768 | 42768 | 8.1 | 0 | 0 | 0 | 0 | 42768 | 8.1 | 0 | 0 | 0 |  |  | NB | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Calistoga | Napa | 38.5844 | -122.661
35191318 |  | 2021 |  | ECOP - SILVERADO 2102 - H02-LR58626 |  | Scoped | ESTS |  | 0 | 11721.6 | 11721.6 | 2.22 | 0 | 0 | 11722 | 2.2201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-03-31 |  | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.22 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 682400 | 45162.4 |  | 682400 | 0 |  | 6.61% | 31090.3 |  |  |  | 20343.4234 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5095 | -122.386 | [10 empty] | Y |  | 663 |  | ECOP |  | 2021-03-11 10:27
35191319 |  | 2021 |  | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Scoped | UNSE |  | 6177.6 | 0 | 6177.6 | 1.17 | 0 | 0 | 0 | 0 | 6178 | 1.1701 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 | 2022-01-25 17:00 |  | 2022-03-28 17:00 | [8 empty] | 312500 |  |  | 312500 | 0 |  |  | 17119.1 | [15 empty] | Nicasio | Marin | 38.046 | -122.646 | [10 empty] | Y |  | 215 | 35191319 | ECOP |  | 2021-03-11 10:43
35191383 |  | 2021 |  | ECOP - SILVERADO 2102 - H01-LR58626 |  | Scoped | ESTS |  | 0 | 7075.2 | 7075.2 | 1.34 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH | 2021-03-31 |  | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 614000 | 34923.2 |  | 614000 | 0 |  | 5.68% | 30366.8 |  |  |  | 26062.0896 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5057 | -122.401 | [10 empty] | Y |  | 663 |  | ECOP |  | 2021-03-11 10:27
35191937 |  | 2021 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Scoped | UNSE |  | 0 | 7718 | 7718 | 1.4617 | 0 | 0 | 0 | 0 | 7718 | 1.4617 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4617 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 237833 |  |  | 237833 | 0 |  |  | 14530 | [15 empty] | Napa | Napa | 38.4108 | -122.4506 | [10 empty] | Y |  | 951 | 35191937 | ECOP |  | 2021-03-11 14:15
35192043 |  |  |  | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | ST | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [33 empty] | Remove |  | Volcano | Amador | 38.4744 | -120.6272
35192053 |  | 2021 |  | STRM-OAKHURST 1103-LR 5120 PH1 |  | Scoped | CONS |  | 0 | 10401.6 | 10401.6 | 1.97 | 0 | 0 | 10401.6 | 1.97 | 0 | 0 | 0 | 0 | 0 | 11569 | 2.1911 | YO | 08W | SH - Wind | 2021-03-19 17:00 |  | Y | [6 empty] | 2021-01-25 | [16 empty] | 2021-02-17 | 2021-02-17 | [5 empty] | 2021-03-01 | 2021-03-01 | Full |  |  | Partial release waiting for VM data |  |  |  | Yes |  |  |  |  | 2021-03-15 |  | 2021-02-08 | [10 empty] | 0 | 0 | 0 | 0 | 8237 | 1.56 | 1.56 | 0.40996 | 1.3843 | 0 | 2.2551 | 0.87083 | 0.17576 | 0 |  | Keep | 2021-03-19 17:00 |  | N/A | 2021-02-08 08:00 | 2021-03-22 17:00 |  | 2021-05-21 17:00 | 2021-02-01 | 2021-02-16 07:00 | 2021-04-30 16:00 | [6 empty] | 1608269.6 | 2843023 | 1877409.58 |  |  |  | 1256551.3 | 761327.5 | 2017878.8 |  | 816380.5076 | [11 empty] | Fish Camp | Mariposa | 37.481 | -119.6374 | [10 empty] | Y |  | 1975 |  | STRM |  | 2021-03-09 08:34
35192280 |  | 2021 |  | ECOP - CLAYTON 2212 - H01-LR2951 |  | Scoped | UNSE |  | 7075.2 | 0 | 7075.2 | 1.34 | 0 | 0 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 3.7879e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [25 empty] | In Progress | 2021-04-11 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-12-31 07:00 | 2021-12-31 16:00 | [5 empty] | 550000 | 91561.9 |  | 550000 | 0 |  | 16.64% | 38305 |  |  |  | 68329.7761 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8682 | -121.8573 | [10 empty] | Y |  | 377 | 35192280 | ECOP |  | 2021-03-11 12:49
35192281 |  | 2021 |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Scoped | UNSE |  | 0 | 1426 | 1426 | 0.27008 | 0 | 0 | 1426 | 0.27008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-07-09 07:00 | 2021-07-09 16:00 | [8 empty] | 950000 |  |  |  | 18727.9 | [15 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-11 10:41
35192282 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Scoped | UNSE |  | 10771 | 0 | 10771 | 2.04 | 0 | 0 | 0 | 0 | 10771 | 2.04 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-07-09 07:00 | 2021-07-09 16:00 | [8 empty] | 950000 |  |  |  | 16998.2 | [15 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | Y |  | 468 | 35192282 | ECOP |  | 2021-03-11 10:43
35192284 |  | 2021 |  | ECOP - SILVERADO 2104 - H05-LR726 |  | Scoped | UNSE |  | 10929.6 | 0 | 10929.6 | 2.07 | 0 | 0 | 10930 | 2.0701 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH |  |  | N | [25 empty] | In Progress | 2021-03-29 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.07 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 190000 | 155254 |  | 190000 | 0 |  | 81.71% | 17181.9 |  |  |  | 75001.9324 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6154 | -122.4315 | [10 empty] | Y |  | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35192290 |  | 2021 |  | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Scoped | ADER |  | 0 | 26400 | 26400 | 5 | 0 | 0 | 26400 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-07-01 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-12 | 2021-03-12 | 2021-03-04 |  |  |  | [OH]03/11: EOD needed to push; PM projects 2-3 wks03/10: ADE in rvw03/04: CAL submitted for 1st ADE rvw; ADE assigned ( [REDACTED] .)03/03: EST submitting today2/24: On Track; 75% EST complete; 109 locs. Target submittal early next week. |  |  |  | 30d - Mar Fasttrack | R1.2 - ADE Review in Progress | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | INPR | 2021-07-26 08:00 | 2021-11-01 17:00 |  | 2021-12-31 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 950000 | 6927773.6 |  | 1 | -949999 |  | 729.2% | 11762.6 |  |  |  | 1385554.72 | [11 empty] | Placerville | El Dorado | 38.739 | -120.9057 |  | MX | OH | [7 empty] | Y |  | 811 |  | ECOP |  | 2021-03-11 16:21
35192291 |  | 2021 |  | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Scoped | UNSE |  | 2534.4 | 0 | 2534.4 | 0.48 | 0 | 0 | 0 | 0 | 2534 | 0.47992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-11-10 17:00 | 2021-04-09 | N | 2021-04-30 |  | 2021-04-30 | [22 empty] | In Progress | 2021-04-19 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-10 17:00 |  | INPR | 2022-02-04 08:00 | 2022-05-06 17:00 |  | 2022-07-07 17:00 | [8 empty] | 500000 | 1628399 |  | 1 | -499999 |  | 325.7% | 13222.4 |  |  |  | 3392497.9167 | [11 empty] | Placerville | El Dorado | 38.7215 | -120.8714 |  | MX | MX | [7 empty] | Y |  | 811 | 35192291 | ECOP |  | 2021-03-11 15:56
35192292 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Scoped | UNSE |  | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-11-16 17:00 | 2021-02-11 | Y | [25 empty] | In Progress | 2021-03-19 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-16 17:00 |  | INPR | 2022-01-19 08:00 | 2022-04-06 08:00 |  | 2022-05-19 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 250000 |  |  | 950000 | 700000 |  |  | 24408.8 | [9 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.5527 | -122.7132 |  | ML | UG | [7 empty] | Y |  | 637 | 35192292 | ECOP |  | 2021-03-05 14:52
35193416 |  |  |  | EP 9265 ALHAMBRA AVE MORADA |  |  | ESTS |  | 0 | 53289.8 | 53289.8 | 10.0928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0928 |  |  | ST | 10K | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0928 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 38.0368 | -121.2422 | [16 empty] | 2021-03-01 20:31
35193574 |  | 2020 | T2/T3 A Tag | SR-CC-SANTA CRUZ-08-16-20 CZU AUG FIRE |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2021-04-05 09:07 | 2021-04-05 15:11 | [30 empty] | 36.9747 | -122.0309
35193585 |  |  |  | SR-CC-MONTEREY-08-16-20 RIVER/CARMEL/DOL |  |  | ESTS |  | 0 | 15417.6 | 15417.6 | 2.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.92 |  |  | CC | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.92 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 36.5626 | -121.5619
35193614 |  |  |  | NO-SA-SOLANO-8/18/20-LNU COMPLEX FIRE OH |  |  | POST |  | 0 | 41923.2 | 41923.2 | 7.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.94 |  |  | SA | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.94 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2021-02-26 | [29 empty] | 0 | 0
35193618 |  | 2020 | T2/T3 A Tag | NR-SO-SONOMA 8/17/20-LNU COMPLEX FIRES |  |  | ESTS |  | 0 | 87648 | 87648 | 16.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6 |  |  | SO | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.6 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [5 empty] | 2021-02-22 07:00 | 2021-02-23 15:00 | [30 empty] | 0 | 0
35194291 |  |  |  | SO-SJ-SANTA CLARA - 08/18/20 - SCU LIGHT |  |  | PEND |  | 0 | 46040.8 | 46040.8 | 8.7198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7198 |  |  | SJ | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.7198 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 0 | 0
35198909 |  |  |  | CV-YO-MADERA CNTY- 9-6-20 CREEK FIRE EVE |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [35 empty] | Oakhurst | Madera | 0 | 0
35199234 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- NORTH COMPLEX FIRE |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.6422 | -121.4233 | [16 empty] | 2021-03-10 13:19
35199565 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H |  | Scoped | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.5439 | -121.4323 | [12 empty] | 1288 |  | FRRB
35199649 |  |  |  | CV-YO-MADERA - 9/10/20 CREEK FIRE SYS H |  |  | POST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2020-09-18 | [29 empty] | 37.1025 | -119.7907
35199922 |  |  |  | CV-FR - CREEK 9/13/20 - CREEK FIRE SYS H |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 37.0441 | -119.3666
35200051 |  | 2020 | T1 A Tag | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H |  | Scoped | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95B | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 39.5752 | -121.3055 | [12 empty] | 1288 |  | FRRB
35201797 |  |  |  | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS/ |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF |  |  |  |  | 2021-04-30 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Groveland | Tuolumne | 37.7534 | -120.05
35204191 |  | 2020 | T2/T3 A Tag | NO-NV- SHASTA 9/27/20 ZOGG FIRE SYS HRDN |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 0 | 0
35204225 |  | 2020 | T2/T3 A Tag | NR-SO-SONOMA- 9/28/20- GLASS FIRE SYS H |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 0 | 0
35204446 |  |  |  | NR-NB-NAPA- 9/27/20- GLASS FIRE SYS HARD |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 95A | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 0 | 0
35204801 |  |  |  | STS-TRAN_IDLE_REMV-4 SPANS W/O 15625 BOW |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-04-30 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Cottonwood | Shasta | 40.3129 | -122.458
35204808 |  |  |  | DR-POLE_IDLE_REMV-BEHIND 10979 SPARROW |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-04-30 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.6076 | -122.2417
35204814 |  |  |  | DR-COND_IDLE_REMV-14820 FERN RD |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.6613 | -121.9488
35204816 |  |  |  | FT-COND_IDLE_REMV-28490 OAK RUN RD TO F |  |  | UNSC |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-04-30 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.7029 | -122.0395
35204821 |  |  |  | STS-POLE_IDLE_REMV-5138 POPLAR AVE |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.4352 | -122.3978
35204834 |  |  |  | STS-COND_IDLE_REMV-INDIAN AVENUE |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.837 | -121.9168
35204835 |  |  |  | STS-COND_IDLE_REMV-INDIAN AVENUE |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.8363 | -121.9171
35206134 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W |  | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [35 empty] | Scotts Valley | Santa Cruz | 37.083 | -122.0061
35206135 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W |  | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [35 empty] | Scotts Valley | Santa Cruz | 37.0846 | -122.0061
35206136 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W |  | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [35 empty] | Scotts Valley | Santa Cruz | 37.0779 | -122.0106
35206138 |  |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W |  | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [35 empty] | Scotts Valley | Santa Cruz | 37.0651 | -122.0174
35207923 |  |  |  | STS-POLE_IDLE_REMV - 1OW/O 5S/O 29901 HW |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.8048 | -121.9299
35207924 |  |  |  | STS-TRAN_IDLE_REMV - 9W/O 5S/O 29901 HWY |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.8049 | -121.9301
35208005 |  |  |  | STS-OFAC_IDLE_REMV-17262 DONN LN.2PN PVT |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.79 | -121.9593
35208054 |  |  |  | STS-COND_IDLE_REMV-BAYNE RD |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 2AF | IF |  |  |  |  | 2021-02-28 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 0 | 0
35211254 |  |  |  | STS-OFAC_IDLE_REMV-11226 DESCHUTES ROAD |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-07-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.6177 | -122.2349
35211698 |  |  |  | STS-COND_IDLE_REMV-CO POLE #85883 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF |  |  |  |  | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.4475 | -122.3152
35212401 |  |  |  | FRRB - MONTICELLO 1101 CB |  |  | UNSE |  | 0 | 369.6 | 369.6 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 369.6 | 0.07 | 0 | 0 | 0.07 | 0 | 0 | 0 |  | 0 | 0.07 | 0 |  |  |  |  | N/A | [35 empty] | Napa | Napa | 38.3013 | -122.2942
35212402 |  |  |  | FRRB - MONTICELLO 1101 LR 666 |  |  | UNSE |  | 0 | 20644.8 | 20644.8 | 3.91 | 20644.8 | 3.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 20644.8 | 3.91 | 0 | 0 | 3.91 | 0 | 0 | 0 |  | 0 | 3.91 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.5092 | -122.2126 | [12 empty] | 815 |  | FRRB
35212403 |  |  |  | FRRB - MONTICELLO 1101 LR 654 |  |  | UNSE |  | 0 | 24288 | 24288 | 4.6 | 24288 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 24288 | 4.6 | 0 | 0 | 4.6 | 0 | 0 | 0 |  | 0 | 4.6 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.511 | -122.2133 | [12 empty] | 1227 |  | FRRB
35212404 |  |  |  | FRRB - MONTICELLO 1101 LR 630 |  |  | UNSE |  | 0 | 33369.6 | 33369.6 | 6.32 | 33369.6 | 6.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 33369.6 | 6.32 | 0 | 0 | 6.32 | 0 | 0 | 0 |  | 0 | 6.32 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.573 | -122.244 | [12 empty] | 732 |  | FRRB
35212405 |  |  |  | FRRB - MONTICELLO 1101 LR 93384 |  |  | UNSE |  | 0 | 69062.4 | 69062.4 | 13.08 | 69062.4 | 13.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 69062.4 | 13.08 | 0 | 0 | 13.08 | 0 | 0 | 0 |  | 0 | 13.08 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.4787 | -122.1871 | [12 empty] | 914 |  | FRRB
35212406 |  |  |  | FRRB - MONTICELLO 1101 LR 37384 |  |  | UNSE |  | 0 | 8184 | 8184 | 1.55 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 8184 | 1.55 | 0 | 0 | 1.55 | 0 | 0 | 0 |  | 0 | 1.55 | 0 |  | Keep |  |  | N/A | [35 empty] | Napa | Napa | 38.4456 | -122.1961 | [12 empty] | 557 |  | FRRB
35212407 |  |  |  | FRRB - SILVERADO 2102 LR 636 |  |  | UNSE |  | 0 | 3537.6 | 3537.6 | 0.67 | 3537.6 | 0.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 3537.6 | 0.67 | 0 | 0 | 0.67 | 0 | 0 | 0 |  | 0 | 0.67 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5088 | -122.4473 | [12 empty] | 1550 |  | FRRB
35212408 |  |  |  | FRRB - SILVERADO 2102 LR 34959 |  |  | UNSE |  | 0 | 9873.6 | 9873.6 | 1.87 | 9873.6 | 1.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 9873.6 | 1.87 | 0 | 0 | 1.87 | 0 | 0 | 0 |  | 0 | 1.87 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5068 | -122.374 | [12 empty] | 579 |  | FRRB
35212409 |  |  |  | FRRB - SILVERADO 2104 LR 645 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5379 | -122.4706 | [12 empty] | 2117 |  | FRRB
35212410 |  |  |  | FRRB - SILVERADO 2104 LR 708 |  |  | UNSE |  | 0 | 3907.2 | 3907.2 | 0.74 | 3907.2 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 3907.2 | 0.74 | 0 | 0 | 0.74 | 0 | 0 | 0 |  | 0 | 0.74 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5146 | -122.4742 | [12 empty] | 1648 |  | FRRB
35212411 |  |  |  | FRRB - SILVERADO 2104 LR 722 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Deer Park | Napa | 38.545 | -122.4756 | [12 empty] | 690 |  | FRRB
35212412 |  |  |  | FRRB - SILVERADO 2104 LR 37632 |  |  | UNSE |  | 0 | 26136 | 26136 | 4.95 | 26136 | 4.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 26136 | 4.95 | 0 | 0 | 4.95 | 0 | 0 | 0 |  | 0 | 4.95 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5348 | -122.4754 | [12 empty] | 1235 |  | FRRB
35212413 |  |  |  | FRRB - SILVERADO 2105 LR 658898 |  |  | UNSE |  | 0 | 10697.28 | 10697.28 | 2.026 | 10697.28 | 2.026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 10697.28 | 2.026 | 0 | 0 | 2.026 | 0 | 0 | 0 |  | 0 | 2.026 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5072 | -122.4909 | [12 empty] | 1361 |  | FRRB
35212414 |  |  |  | FRRB - SILVERADO 2105 LR 131568 |  |  | UNSE |  | 0 | 2513.28 | 2513.28 | 0.476 | 2513.28 | 0.476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 2513.28 | 0.476 | 0 | 0 | 0.476 | 0 | 0 | 0 |  | 0 | 0.476 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5377 | -122.4954 | [12 empty] | 1947 |  | FRRB
35212415 |  |  |  | FRRB - SILVERADO 2105 LR 167360 |  |  | UNSE |  | 0 | 12672 | 12672 | 2.4 | 12672 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 12672 | 2.4 | 0 | 0 | 2.4 | 0 | 0 | 0 |  | 0 | 2.4 | 0 |  | Keep |  |  | N/A | [35 empty] | Saint Helena | Napa | 38.5018 | -122.4771 | [12 empty] | 2174 |  | FRRB
35212416 |  |  |  | FRRB - CALISTOGA 1102 LR 634 |  |  | UNSE |  | 0 | 7920 | 7920 | 1.5 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 7920 | 1.5 | 0 | 0 | 1.5 | 0 | 0 | 0 |  | 0 | 1.5 | 0 |  | Keep |  |  | N/A | [35 empty] | Calistoga | Napa | 38.5859 | -122.5714 | [12 empty] | 1477 |  | FRRB
35212417 |  |  |  | FRRB - CALISTOGA 1102 LR 769230 |  |  | UNSE |  | 0 | 20856 | 20856 | 3.95 | 20856 | 3.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | FRRB | [60 empty] | 0 | 0 | 20856 | 3.95 | 0 | 0 | 3.95 | 0 | 0 | 0 |  | 0 | 3.95 | 0 |  | Keep |  |  | N/A | [35 empty] | Calistoga | Napa | 38.5678 | -122.5383 | [12 empty] | 1624 |  | FRRB
35212418 |  |  |  | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  |  | UNSE |  | 0 | 72336 | 72336 | 13.7 | 72336 | 13.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 72336 | 13.7 | 0 | 0 | 13.7 | 0 | 0 | 0 |  | 0 | 13.7 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4371 | -122.7159 | [12 empty] | 945 |  | FRRB
35212419 |  |  |  | FRRB - DUNBAR 1101 - LR 416 |  |  | UNSE |  | 0 | 12355.2 | 12355.2 | 2.34 | 12355.2 | 2.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 12355.2 | 2.34 | 0 | 0 | 2.34 | 0 | 0 | 0 |  | 0 | 2.34 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4361 | -122.5779 | [12 empty] | 1684 |  | FRRB
35212460 |  |  |  | FRRB - RINCON 1101 LR 14605 |  |  | UNSE |  | 0 | 69854.4 | 69854.4 | 13.23 | 69854.4 | 13.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 69854.4 | 13.23 | 0 | 0 | 13.23 | 0 | 0 | 0 |  | 0 | 13.23 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4588 | -122.6335 | [12 empty] | 0 |  | FRRB
35212461 |  |  |  | FRRB - RINCON 1101 LR 663641 |  |  | UNSE |  | 0 | 3115.2 | 3115.2 | 0.59 | 3115.2 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 3115.2 | 0.59 | 0 | 0 | 0.59 | 0 | 0 | 0 |  | 0 | 0.59 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4497 | -122.6145 | [12 empty] | 2309 |  | FRRB
35212462 |  |  |  | FRRB - RINCON 1103 LR 198 |  |  | UNSE |  | 0 | 13728 | 13728 | 2.6 | 13728 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 13728 | 2.6 | 0 | 0 | 2.6 | 0 | 0 | 0 |  | 0 | 2.6 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4982 | -122.653 | [12 empty] | 1618 |  | FRRB
35212463 |  |  |  | FRRB - RINCON 1103 LR 474 |  |  | UNSE |  | 0 | 87595.2 | 87595.2 | 16.59 | 87595.2 | 16.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 87595.2 | 16.59 | 0 | 0 | 16.59 | 0 | 0 | 0 |  | 0 | 16.59 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.5056 | -122.6457 | [12 empty] | 1342 |  | FRRB
35212464 |  |  |  | FRRB - CALISTOGA 1101 LR 886282 |  |  | UNSE |  | 0 | 5016 | 5016 | 0.95 | 5016 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 5016 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 |  | 0 | 0.95 | 0 |  | Keep |  |  | N/A | [35 empty] | Calistoga | Napa | 38.5602 | -122.6286 | [12 empty] | 0 |  | FRRB
35212465 |  |  |  | FRRB - VACAVILLE 1108 LR 38316 |  |  | UNSE |  | 0 | 33475.2 | 33475.2 | 6.34 | 33475.2 | 6.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SA | 08W | FRRB | [60 empty] | 0 | 0 | 33475.2 | 6.34 | 0 | 0 | 6.34 | 0 | 0 | 0 |  | 0 | 6.34 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3512 | -121.9078 | [12 empty] | 122 |  | FRRB
35212466 |  |  |  | FRRB - VACAVILLE 1108 LR 8762 |  |  | UNSE |  | 0 | 47203.2 | 47203.2 | 8.94 | 47203.2 | 8.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SA | 08W | FRRB | [60 empty] | 0 | 0 | 47203.2 | 8.94 | 0 | 0 | 8.94 | 0 | 0 | 0 |  | 0 | 8.94 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3618 | -122.0227 | [12 empty] | 64 |  | FRRB
35212467 |  |  |  | FRRB - LAURELES 1111 LR 2020 |  |  | UNSE |  | 0 | 6441.6 | 6441.6 | 1.22 | 6441.6 | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 6441.6 | 1.22 | 0 | 0 | 1.22 | 0 | 0 | 0 |  | 0 | 1.22 | 0 |  | Keep |  |  | N/A | [35 empty] | Salinas | Monterey | 36.6689 | -121.6559 | [12 empty] | 2187 |  | FRRB
35212468 |  |  |  | FRRB - POINT MORETTI 1101 LR36516 |  |  | UNSE |  | 0 | 5016 | 5016 | 0.95 | 5016 | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 5016 | 0.95 | 0 | 0 | 0.95 | 0 | 0 | 0 |  | 0 | 0.95 | 0 |  | Keep |  |  | N/A | [35 empty] | Boulder Creek | Santa Cruz | 37.0787 | -122.1336 | [12 empty] | 2542 |  | FRRB
35212469 |  |  |  | FRRB - POINT MORETTI 1101 LR12122 |  |  | UNSE |  | 0 | 24393.6 | 24393.6 | 4.62 | 24393.6 | 4.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 24393.6 | 4.62 | 0 | 0 | 4.62 | 0 | 0 | 0 |  | 0 | 4.62 | 0 |  | Keep |  |  | N/A | [35 empty] | Davenport | Santa Cruz | 37.0666 | -122.2288 | [12 empty] | 2199 |  | FRRB
35212470 |  |  |  | FRRB - POINT MORETTI 1101 LR83716 |  |  | UNSE |  | 0 | 4065.6 | 4065.6 | 0.77 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 4065.6 | 0.77 | 0 | 0 | 0.77 | 0 | 0 | 0 |  | 0 | 0.77 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Cruz | Santa Cruz | 37.0865 | -122.2603 | [12 empty] | 2210 |  | FRRB
35212471 |  |  |  | FRRB - POINT MORETTI 1101 LR5076 |  |  | UNSE |  | 0 | 8976 | 8976 | 1.7 | 8976 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 8976 | 1.7 | 0 | 0 | 1.7 | 0 | 0 | 0 |  | 0 | 1.7 | 0 |  | Keep |  |  | N/A | [35 empty] | Davenport | Santa Cruz | 37.0316 | -122.1893 | [12 empty] | 1393 |  | FRRB
35212472 |  |  |  | FRRB - BIG BASIN 1102 LR5066 |  |  | UNSE |  | 0 | 13411.2 | 13411.2 | 2.54 | 13411.2 | 2.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 13411.2 | 2.54 | 0 | 0 | 2.54 | 0 | 0 | 0 |  | 0 | 2.54 | 0 |  | Keep |  |  | N/A | [35 empty] | Boulder Creek | Santa Cruz | 37.1706 | -122.1655 | [12 empty] | 2359 |  | FRRB
35212473 |  |  |  | FRRB - BIG BASIN 1102 LR10254 |  |  | UNSE |  | 0 | 11668.8 | 11668.8 | 2.21 | 11668.8 | 2.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 11668.8 | 2.21 | 0 | 0 | 2.21 | 0 | 0 | 0 |  | 0 | 2.21 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Cruz | Santa Cruz | 37.1392 | -122.1787 | [12 empty] | 1421 |  | FRRB
35212474 |  |  |  | FRRB - BIG BASIN 1102 LR12758 |  |  | UNSE |  | 0 | 2745.6 | 2745.6 | 0.52 | 2745.6 | 0.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 2745.6 | 0.52 | 0 | 0 | 0.52 | 0 | 0 | 0 |  | 0 | 0.52 | 0 |  | Keep |  |  | N/A | [35 empty] | Boulder Creek | Santa Cruz | 37.1486 | -122.1745 | [12 empty] | 2358 |  | FRRB
35212475 |  |  |  | FRRB - BIG BASIN 1101 CB |  |  | UNSE |  | 0 | 16315.2 | 16315.2 | 3.09 | 16315.2 | 3.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 16315.2 | 3.09 | 0 | 0 | 3.09 | 0 | 0 | 0 |  | 0 | 3.09 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Cruz | Santa Cruz | 36.9557 | -122.0275 | [12 empty] | 2398 |  | FRRB
35212476 |  |  |  | FRRB - BIG BASIN 1101 LR5000 |  |  | UNSE |  | 0 | 7233.6 | 7233.6 | 1.37 | 7233.6 | 1.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 7233.6 | 1.37 | 0 | 0 | 1.37 | 0 | 0 | 0 |  | 0 | 1.37 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Cruz | Santa Cruz | 37.1026 | -122.1416 | [12 empty] | 2579 |  | FRRB
35212477 |  |  |  | FRRB - BIG BASIN 1101 LR10720 |  |  | UNSE |  | 0 | 3115.2 | 3115.2 | 0.59 | 3115.2 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | CC | 08W | FRRB | [60 empty] | 0 | 0 | 3115.2 | 0.59 | 0 | 0 | 0.59 | 0 | 0 | 0 |  | 0 | 0.59 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Cruz | Santa Cruz | 37.1085 | -122.1441 | [12 empty] | 2435 |  | FRRB
35212478 |  |  |  | FRRB - SWIFT 2110 XR332 |  |  | UNSE |  | 0 | 44616 | 44616 | 8.45 | 44616 | 8.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SJ | 08W | FRRB | [60 empty] | 0 | 0 | 44616 | 8.45 | 0 | 0 | 8.45 | 0 | 0 | 0 |  | 0 | 8.45 | 0 |  | Keep |  |  | N/A | [35 empty] | Milpitas | Santa Clara | 37.3494 | -121.6124 | [12 empty] | 1769 |  | FRRB
35212479 |  |  |  | FRRB - BIG BEND 1102 CB |  |  | UNSE |  | 0 | 21331.2 | 21331.2 | 4.04 | 21331.2 | 4.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 21331.2 | 4.04 | 0 | 0 | 4.04 | 0 | 0 | 0 |  | 0 | 4.04 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.4996 | -121.548 | [12 empty] | 865 |  | FRRB
35212480 |  |  |  | FRRB - BIG BEND 1102 LR1972 |  |  | UNSE |  | 0 | 21436.8 | 21436.8 | 4.06 | 21436.8 | 4.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 21436.8 | 4.06 | 0 | 0 | 4.06 | 0 | 0 | 0 |  | 0 | 4.06 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.6444 | -121.4314 | [12 empty] | 1288 |  | FRRB
35212481 |  |  |  | FRRB - WYANDOTTE 1103 LR1508 |  |  | UNSE |  | 0 | 52377.6 | 52377.6 | 9.92 | 52377.6 | 9.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 52377.6 | 9.92 | 0 | 0 | 9.92 | 0 | 0 | 0 |  | 0 | 9.92 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.5047 | -121.4524 | [12 empty] | 1176 |  | FRRB
35212483 |  |  |  | FRRB - WYANDOTTE 1103 LR1974 |  |  | UNSE |  | 0 | 42081.6 | 42081.6 | 7.97 | 42081.6 | 7.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 42081.6 | 7.97 | 0 | 0 | 7.97 | 0 | 0 | 0 |  | 0 | 7.97 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.6394 | -121.4295 | [12 empty] | 1849 |  | FRRB
35212486 |  |  |  | FRRB - KANAKA 1101 CB |  |  | UNSE |  | 0 | 16262.4 | 16262.4 | 3.08 | 16262.4 | 3.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 16262.4 | 3.08 | 0 | 0 | 3.08 | 0 | 0 | 0 |  | 0 | 3.08 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.4996 | -121.548 | [12 empty] | 1480 |  | FRRB
35212487 |  |  |  | FRRB - KANAKA 1101 LR1034 |  |  | UNSE |  | 0 | 14150.4 | 14150.4 | 2.68 | 14150.4 | 2.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 14150.4 | 2.68 | 0 | 0 | 2.68 | 0 | 0 | 0 |  | 0 | 2.68 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.5765 | -121.3019 | [12 empty] | 1566 |  | FRRB
35212488 |  |  |  | FRRB - KANAKA 1101 LR1406 |  |  | UNSE |  | 0 | 47044.8 | 47044.8 | 8.91 | 47044.8 | 8.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 47044.8 | 8.91 | 0 | 0 | 8.91 | 0 | 0 | 0 |  | 0 | 8.91 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.5732 | -121.3176 | [12 empty] | 1728 |  | FRRB
35212489 |  |  |  | FRRB - GIRVAN 1101 LR1330 |  |  | UNSE |  | 0 | 16104 | 16104 | 3.05 | 16104 | 3.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 16104 | 3.05 | 0 | 0 | 3.05 | 0 | 0 | 0 |  | 0 | 3.05 | 0 |  | Keep |  |  | N/A | [35 empty] | Shasta | Shasta | 40.5176 | -122.5059 | [12 empty] | 624 |  | FRRB
35212490 |  |  |  | FRRB - GIRVAN 1101 LR323094 |  |  | UNSE |  | 0 | 28934.4 | 28934.4 | 5.48 | 28934.4 | 5.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 28934.4 | 5.48 | 0 | 0 | 5.48 | 0 | 0 | 0 |  | 0 | 5.48 | 0 |  | Keep |  |  | N/A | [35 empty] | Igo | Shasta | 40.4984 | -122.5727 | [12 empty] | 117 |  | FRRB
35212491 |  |  |  | FRRB - SAN JOAQUIN #3 1103 LR5100 |  |  | UNSE |  | 0 | 5068.8 | 5068.8 | 0.96 | 5068.8 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | FRRB | [60 empty] | 0 | 0 | 5068.8 | 0.96 | 0 | 0 | 0.96 | 0 | 0 | 0 |  | 0 | 0.96 | 0 |  | Keep |  |  | N/A | [37 empty] | 36.9718 | -120.0906 | [12 empty] | 829 |  | FRRB
35212492 |  |  |  | FRRB - AUBERRY 1101 R2845 |  |  | UNSE |  | 0 | 10084.8 | 10084.8 | 1.91 | 10084.8 | 1.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | FRRB | [60 empty] | 0 | 0 | 10084.8 | 1.91 | 0 | 0 | 1.91 | 0 | 0 | 0 |  | 0 | 1.91 | 0 |  | Keep |  |  | N/A | [35 empty] | Auberry | Fresno | 37.1197 | -119.4397 | [12 empty] | 1209 |  | FRRB
35212493 |  |  |  | FRRB - AUBERRY 1101 R324 |  |  | UNSE |  | 0 | 34003.2 | 34003.2 | 6.44 | 34003.2 | 6.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | FRRB | [60 empty] | 0 | 0 | 34003.2 | 6.44 | 0 | 0 | 6.44 | 0 | 0 | 0 |  | 0 | 6.44 | 0 |  | Keep |  |  | N/A | [35 empty] | Auberry | Fresno | 37.0556 | -119.3703 | [12 empty] | 2209 |  | FRRB
35212494 |  |  |  | FRRB - AUBERRY 1101 LR37536 |  |  | UNSE |  | 0 | 13833.6 | 13833.6 | 2.62 | 13833.6 | 2.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | FRRB | [60 empty] | 0 | 0 | 13833.6 | 2.62 | 0 | 0 | 2.62 | 0 | 0 | 0 |  | 0 | 2.62 | 0 |  | Keep |  |  | N/A | [35 empty] | Auberry | Fresno | 37.059 | -119.3881 | [12 empty] | 934 |  | FRRB
35212495 |  |  |  | FRRB - AUBERRY 1101 LR233716 |  |  | UNSE |  | 0 | 45672 | 45672 | 8.65 | 45672 | 8.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | FR | 08W | FRRB | [60 empty] | 0 | 0 | 45672 | 8.65 | 0 | 0 | 8.65 | 0 | 0 | 0 |  | 0 | 8.65 | 0 |  | Keep |  |  | N/A | [35 empty] | Auberry | Fresno | 37.062 | -119.36 | [12 empty] | 0 |  | FRRB
35212496 |  |  |  | FRRB - HB TRINITY COUNTY |  |  | UNSE |  | 0 | 11932.8 | 11932.8 | 2.26 | 11932.8 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | FRRB | [60 empty] | 0 | 0 | 11932.8 | 2.26 | 0 | 0 | 2.26 | 0 | 0 | 0 |  | 0 | 2.26 | 0 |  | Keep |  |  | N/A | [35 empty] | Zenia | Trinity | 0 | 0 | [12 empty] | 1385 |  | FRRB
35217267 |  | 2021 |  | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Scoped | ESTS |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-14 17:00 | 2021-02-18 | Y | 2021-03-31 | 2021-03-31 | 2021-03-12 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-14 17:00 |  | N/A | 2021-06-28 08:00 | 2021-08-30 17:00 |  | 2021-10-11 17:00 | [11 empty] | 1 |  |  |  | 57916.6 | [9 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.4871 | -119.9619 | [10 empty] | Y |  | 10 |  | CWSP |  | 2021-03-11 10:16
35217268 |  | 2021 |  | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 453 | 0.085795 | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; OH] 03/03 - 2/24: [EOD PUSH] Current scope has some overlap with another PM35212441 - scope needs some rework (maybe more UG); Scope includes work along Highway, will require land basemaps (May 7) |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-05-07 |  |  |  | 2021-04-22 |  |  |  |  | Received CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 150000 | 145304.2 | 380000 | 150000 | 0 |  | 96.86% | 13681.2 |  |  |  | 726521 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | Y |  | 11 | 35217268 | CWSP |  | 2021-03-03 12:30
35217269 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Scoped | UNSE |  | 0 | 2270 | 2270 | 0.42992 | 0 | 0 | 0 | 0 | 2270 | 0.42992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-07-09 07:00 | 2021-07-09 16:00 | [8 empty] | 1 |  |  |  | 13593.4 | [15 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-11 10:39
35217270 |  | 2021 |  | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Scoped | ESTS |  | 0 | 2904 | 2904 | 0.55 | 0 | 0 | 0 | 0 | 2904 | 0.55 | 0 | 0 | 0 | 2516 | 0.47652 | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [6 empty] | [Basemap; OH]03/02: Still pending Pre-design mtg; waiting for [REDACTED] 2/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from [REDACTED] Fielding of this project was completed on 2/23/2021. Design started on 2/24/2021. Some poles are in Caltrans ROW, so a base map will be needed for the DSDD program.2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  |  | 30d - Mar Fasttrack | Iss_ON HOLD - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 316666 | 31399.3 |  | 316666 | 0 |  | 9.91% | 17084.5 |  |  |  | 57089.6364 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.9301 | -122.7429 | [10 empty] | Y |  | 9 | 35217270 | CWSP |  | 2021-03-11 10:40
35217271 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Scoped | UNSE |  | 8131 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-07-09 07:00 | 2021-07-09 16:00 | [8 empty] | 1 |  |  |  | 32873.6 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-11 10:40
35217272 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Scoped | UNSE |  | 1584 | 0 | 1584 | 0.3 | 0 | 0 | 0 | 0 | 1584 | 0.3 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  |  | 30d - Apr Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 150000 |  |  | 150000 | 0 |  |  | 19711.7 | [15 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35217273 |  | 2021 |  | SH - UPPER LAKE 1101 CB |  | Scoped | UNSE |  | 0 | 5702.4 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 5702.4 | 1.08 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-10-14 17:00 |  | N | [25 empty] | In Progress | 2021-03-15 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-14 17:00 |  | N/A | 2021-11-15 08:00 | 2022-01-31 17:00 |  | 2022-04-01 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 500000 | 30132.8 |  | 500000 | 0 |  | 6.02% | 14971 |  |  |  | 27900.7407 | [5 empty] | Prioritized | [5 empty] | Upper Lake | Lake | 39.353 | -122.7722 | [10 empty] | Y |  | 6 |  | CWSP |  | 2021-03-11 16:51
35217274 |  | 2021 |  | FRRB - PN DIVISION SAN MATEO COUNTY |  | Scoped | UNSE |  | 11774 | 0 | 11774 | 2.2299 | 0 | 0 | 11774.4 | 2.23 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | PN | 08W | FRRB | 2022-10-12 17:00 | [27 empty] | In Progress | 2021-05-15 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-10-12 17:00 |  | N/A | 2022-11-04 08:00 | 2023-03-17 17:00 |  | 2023-05-18 17:00 | [8 empty] | 500000 | 4609757.5 | 7805000 | 500000 | 0 | 414840.6 | 922% | 18477.4 | 66682 | 85159.4 |  | 2067226.0574 | [5 empty] | Prioritized | [5 empty] | Pescadero | San Mateo | 37.2551 | -122.3815 | [10 empty] | Y |  | 2055 |  | FRRB |  | 2021-03-11 16:52
35217275 |  | 2021 |  | FRRB - PN DIVISION SANTA CRUZ COUNTY |  | Scoped | UNSE |  | 15312 | 0 | 15312 | 2.9 | 0 | 0 | 15312 | 2.9 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | FRRB | 2022-10-12 17:00 | [27 empty] | In Progress | 2021-05-15 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-10-12 17:00 |  | N/A | 2022-11-04 08:00 | 2023-03-17 17:00 |  | 2023-05-18 17:00 | [8 empty] | 500000 | 4619212.8 | 10150000 | 500000 | 0 | 409609.9 | 923.8% | 19090.1 | 71300 | 90390.1 |  | 1592832 | [5 empty] | Prioritized | [5 empty] | Pescadero | San Mateo | 37.2551 | -122.3815 | [10 empty] | Y |  | 2055 |  | FRRB |  | 2021-03-11 16:52
35217667 |  |  |  | STS-POLE_IDLE_REMV - 1S/O 10W/O 30520 MO |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 40.5881 | -121.9244
35219092 |  |  |  | CWSP - POSO MOUNTAIN 2104CB |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Bakersfield | Kern | 35.5492 | -118.9618 | [12 empty] | 15 |  | CWSP
35219093 |  | 2021 |  | CWSP - TIDEWATER 210614072 PH 1.1 |  | Scoped | ESTS |  | 6019 | 0 | 6019 | 1.14 | 0 | 0 | 0 | 0 | 6019 | 1.14 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 350000 |  |  | 350000 | 0 |  |  | 7903.7 | [15 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | Y |  | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35219096 |  | 2021 |  | CWSP - KIRKER 2104442850 PH 1.1 |  | Scoped | UNSE |  | 8817.6 | 0 | 8817.6 | 1.67 | 0 | 0 | 0 | 0 | 8818 | 1.6701 | 0 | 0 | -7.5758e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 500000 | 7818.8 |  | 500000 | 0 |  | 1.56% | 7554.7 |  |  |  | 4681.9162 | [11 empty] | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | Y |  | 21 | 35219096 | CWSP |  | 2021-03-11 12:49
35219097 |  | 2021 |  | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Scoped | ESTS |  | 0 | 12473 | 12473 | 2.3623 | 0 | 0 | 12473 | 2.3623 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-02 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3623 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-02 17:00 |  | INPR | 2021-07-13 08:00 | 2021-11-23 17:00 |  | 2022-01-24 17:00 | [8 empty] | 275000 | 2096158.8 |  | 1 | -274999 |  | 762.2% | 35850.8 |  |  |  | 887334.1188 | [11 empty] | Coarsegold | Madera | 37.2276 | -119.6896 |  | ML | OH | [7 empty] | Y |  | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35219098 |  | 2021 |  | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Scoped | UNSE |  | 0 | 3774 | 3774 | 0.71477 | 0 | 0 | 3774 | 0.71477 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 | 2021-02-18 | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  |  |  | [OH]03/09 - 03/02: EST target sub 3/11; T-Line Pole impact RISK (3 poles); EST will reachout to Trasmission upon submittal.02/23: [EOD PUSH] No Cal/No base map required – Customer Conflict, anticipating Legal resistance from customer. Fielding complete, ADE assigned ( [REDACTED] , EST sub date TBD, 35219119 incorrect (shows as completed subdivision)02/18: Attached circulated for a kmz denoting environmental constraints associated with this project (or both projects now that UG and OH have been split into two order numbers); 02/16: PMgr [REDACTED] 02/17: SCOPE SESSION mtg held, [REDACTED] to see if sub-order [35219119] for UG was with CO or Internal?; |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71477 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 475000 |  |  | 475000 | 0 |  |  | 14572.2 | [9 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | Y |  | 23 | 35219098 | CWSP |  | 2021-03-11 16:54
35219099 |  |  |  | CWSP - HIGHLANDS 1102628 |  | In Scoping | UNSE |  | 0 | 11208 | 11208 | 2.1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1227 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1227 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP |  | 2021-03-11 16:54
35219260 |  | 2021 |  | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-03-31 |  | Y | 2021-03-31 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/10: EST target sub (3/19) 03/03: Fielding completion this week; EST target sub (3/19) |  |  |  | 30d - Apr Fasttrack | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [7 empty] | 1520000 | 300000 |  |  |  | 11707.5 | [15 empty] | Feather Falls | Butte | 39.4631 | -121.5149 | [10 empty] | Y |  | 29 | 35219260 | CWSP |  | 2021-03-08 14:18
35219264 |  |  |  | CWSP - POSO MOUNTAIN 2103CB |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Bakersfield | Kern | 35.559 | -118.9571 | [12 empty] | 30 |  | CWSP
35219265 |  |  |  | CWSP - CRESTA 1101546650 |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.8308 | -121.4091 | [12 empty] | 33 |  | CWSP
35219266 |  | 2021 |  | CWSP - MARIPOSA 2102CB PH 1 |  | Scoped | ESTS |  | 0 | 13713 | 13713 | 2.5972 | 0 | 0 | 13713 | 2.5972 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-17 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | 2021-03-31 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5972 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-17 17:00 |  | N/A | 2021-06-09 08:00 | 2021-10-20 17:00 |  | 2021-12-01 17:00 | [11 empty] | 1 |  |  |  | 87962.4 | [15 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | Y |  | 35 | 35219266 | CWSP |  | 2021-03-11 10:28
35219267 |  |  |  | CWSP - MARIPOSA 2102440236 PH1 |  | In Scoping | UNSE |  | 0 | 22545.6 | 22545.6 | 4.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.27 |  |  | YO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.27 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Mariposa | Mariposa | 37.4858 | -119.9694 | [12 empty] | 50 |  | CWSP
35219268 |  | 2021 |  | CWSP - MARIPOSA 210197142 PH 1 |  | Scoped | ESTS |  | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [20 empty] | 2021-04-19 |  | In Progress | 2021-03-12 |  |  |  | 2021-04-19 |  |  |  |  | Received CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  |  | 2021-08-31 08:00 | 2021-11-23 17:00 |  | 2022-01-04 17:00 | [11 empty] | 1 |  |  |  | 110957.8 | [9 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | Y |  | 36 | 35219268 | CWSP |  | 2021-03-11 10:06
35219269 |  |  |  | CWSP - VACA DIXON 110540092 |  | In Scoping | UNSE |  | 0 | 122337.6 | 122337.6 | 23.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.17 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.17 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.4159 | -121.9706 | [12 empty] | 37 |  | CWSP
35219272 |  | 2021 |  | CWSP - MIDDLETOWN 1101481876 |  | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4857.6 | 0.92 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 |  | Y | 2021-04-30 | 2021-04-16 | 2021-04-16 |  |  |  |  | [OH]03/09: Contradicting AA's; EST reached out to PMgr03/02: EST approved to start per [REDACTED] ; Still pending scoping meeting02/23: [RISK EOD PUSH] EST request mtg - Waiting for scoping meeting 02/16: PMgr transferred to [REDACTED] |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 950000 |  |  | 950000 | 0 |  |  | 8727.4 | [9 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7628 | -122.6133 | [10 empty] | Y |  | 38 |  | CWSP |  | 2021-03-11 10:45
35219273 |  | 2021 |  | CWSP - VOLTA 110149742 |  | Scoped | ADER |  | 0 | 15470 | 15470 | 2.9299 | 0 | 0 | 15470 | 2.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-07-01 17:00 |  | Y | 2021-03-31 | 2021-03-12 | 2021-03-12 |  |  |  |  | [OH]03/10: ADE in rvw03/03: CAL submitted for 1st ADE rvw; ADE assigned ( [REDACTED] DB)03/03: EST sub today; Distribution portion; Trans Portion - 90%, 8-9 Pole adjustments, 2 pole cannot make clearance req; Likely a couple Trans-pole replacement required. Sched impact TBD; Dist est. moving forward.2/24: On Track; 75% EST complete; 94 locs. Distribution portion complete. CAL doing T-pole loading calc scope as well.2/18: [EOD PUSH] Trans-Est down personnel 5 Sr Estimators 7 2 ADEs retiring over next 3-mnths. Resources exhausted/ no capacity to take on work. T-line south group as a possible option?2/17: EST advised 2-Thirds Transmission, will need a plan to drive Transmission response to meet schedule.2/16: Pre engineering fld mtg held – PMgr seeking new EOD |  |  |  | 30d - Mar Fasttrack | Iss_R1.2 - ADE Review in Progress | Yes | [11 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | N/A | 2021-07-26 08:00 | 2021-12-06 17:00 |  | 2022-02-04 17:00 | [11 empty] | 1 |  |  |  | 9173.4 | [9 empty] | Prioritized | [5 empty] | Manton | Tehama | 40.4305 | -121.8716 | [10 empty] | Y |  | 39 |  | CWSP |  | 2021-03-11 10:17
35219275 |  | 2021 |  | CWSP - PUTAH CREEK 110246012 |  | Scoped | PEND |  | 0 | 2746 | 2746 | 0.52008 | 0 | 0 | 2746 | 0.52008 | 0 | 0 | 0 | 0 | 0 |  |  | SA | 08W | SH | 2021-06-25 17:00 |  | Y | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-05 | [16 empty] | 2021-04-26 | [6 empty] | 2021-04-26 |  |  |  |  | waiting for a CIF / full intake. Scoped this project on 1/6/2021 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-25 17:00 |  | N/A | 2021-07-20 08:00 | 2021-09-14 17:00 |  | 2021-10-14 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [6 empty] | 1238653.3 | 950000 | 656614.03 |  |  |  | 6783.4 |  |  |  | 2381678.5958 | [5 empty] | Prioritized | [5 empty] | Winters | Yolo | 38.4831 | -122.0253 | [10 empty] | Y |  | 41 |  | CWSP |  | 2021-03-10 09:42
35219276 |  |  |  | CWSP - VACAVILLE 11046542 |  | In Scoping | UNSE |  | 11404.8 | 0 | 11404.8 | 2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.16 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.16 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35219276 | CWSP
35219280 |  | 2021 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Scoped | UNSE |  | 0 | 8870 | 8870 | 1.6799 | 0 | 0 | 8870 | 1.6799 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  |  |  | [OH]03/10 - 2/24: [EOD PUSH] Awaiting Scope Clarification (preferred scope in SAP has OH & UG) – [REDACTED] to assist in separating PMs |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 475000 |  |  | 475000 | 0 |  |  | 4625.3 | [9 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | Y |  | 43 | 35219280 | CWSP |  | 2021-03-11 10:42
35219281 |  | 2021 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Scoped | UNSE |  | 13200 | 0 | 13200 | 2.5 | 0 | 0 | 0 | 0 | 13200 | 2.5 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 316666 |  |  | 316666 | 0 |  |  | 12840 | [15 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | Y |  | 45 | 35219281 | CWSP |  | 2021-03-11 10:09
35219282 |  |  |  | CWSP - NORTH DUBLIN 2101 CB |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | MI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Dublin | Alameda | 37.7426 | -121.8595 | [12 empty] | 47 |  | CWSP |  | 2021-03-09 12:12
35219283 |  |  |  | CWSP - NORTH DUBLIN 2101 CB |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | MI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Livermore | Alameda | 37.7436 | -121.8575 | [12 empty] | 47 |  | CWSP |  | 2021-03-09 12:11
35219286 |  |  |  | CWSP - DESCHUTES 11049718 PH1.1 |  | Scoped | UNSE |  | 0 | 18241 | 18241 | 3.4547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35219286 | CWSP |  | 2021-03-09 17:18
35219287 |  |  |  | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | In Scoping | UNSE |  | 0 | 50011 | 50011 | 9.4718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.4718 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.4718 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6299 | -122.2445 | [12 empty] | 49 |  | CWSP |  | 2021-03-01 13:32
35219289 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1 |  | In Scoping | UNSE |  | 32472 | 40075.2 | 72547.2 | 13.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.74 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35219291 |  | 2022 |  | CWSP - VACA DIXON 1101126774 |  | Scoped | ESTS |  | 0 | 2112 | 2112 | 0.4 | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | SA | 08W | SH | 2021-05-14 17:00 |  | Y | 2021-03-15 | 2021-03-15 | 2021-03-15 |  |  |  | 2021-03-10 | [18 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-14 17:00 |  | N/A | 2021-06-08 08:00 | 2021-07-01 08:00 |  | 2021-08-31 17:00 | 2021-03-10 | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 950000 | 924513.9 | 1265910 | 165125.99 | -784874.01 |  | 97.31% | 13495.4 |  |  |  | 2311284.75 | [5 empty] | Prioritized | [5 empty] | Vacaville | Solano | 38.3973 | -121.9855 | [10 empty] | Y |  | 20 |  | CWSP |  | 2021-03-11 10:21
35219542 |  |  |  | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | In Scoping | UNSE |  | 739.2 | 0 | 739.2 | 0.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Placerville | El Dorado | 38.7307 | -120.7828 | [12 empty] | 2123 |  | PSPS
35219543 |  |  |  | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | In Scoping | UNSE |  | 1267.2 | 0 | 1267.2 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Placerville | El Dorado | 38.7293 | -120.7998 | [12 empty] | 2123 |  | PSPS
35219587 |  |  |  | CWSP - MARIPOSA 2102440236 PH2 |  | In Scoping | UNSE |  | 0 | 11378.4 | 11378.4 | 2.155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.155 |  |  | YO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.155 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Mariposa | Mariposa | 37.4867 | -119.9603 | [12 empty] | 50 |  | CWSP
35219588 |  |  |  | CWSP - MARIPOSA 2102440236 PH3 |  | In Scoping | UNSE |  | 0 | 11378.4 | 11378.4 | 2.155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.155 |  |  | YO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.155 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Mariposa | Mariposa | 37.4632 | -119.9479 | [12 empty] | 50 |  | CWSP
35219589 |  | 2021 |  | CWSP - WILDWOOD 11011454 |  | Scoped | UNSE |  | 0 | 13622.4 | 13622.4 | 2.58 | 0 | 0 | 0 | 0 | 13622 | 2.5799 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 1 |  |  |  | 10781.6 | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | Y |  | 52 |  | CWSP |  | 2021-03-11 09:28
35219590 |  |  |  | CWSP - VACA DIXON 1105965390 |  | In Scoping | UNSE |  | 0 | 3273.6 | 3273.6 | 0.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.4341 | -121.9915 | [12 empty] | 53 |  | CWSP
35219591 |  |  |  | CWSP - OLETA 1101754718 |  | In Scoping | UNSE |  | 0 | 15206.4 | 15206.4 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 |  |  | ST | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Plymouth | Amador | 38.4692 | -120.8536 | [12 empty] | 54 |  | CWSP
35220895 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Scoped | UNSE |  | 10190 | 1162 | 11352 | 2.15 | 0 | 0 | 1162 | 0.22008 | 10190 | 1.9299 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 13905.1 | [15 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | Y |  | 14 | 35220895 | CWSP |  | 2021-03-11 10:42
35220896 |  |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Scoped | UNSE |  | 1478 | 0 | 1478 | 0.27992 | 0 | 0 | 0 | 0 | 1478 | 0.27992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 | [11 empty] | 1 |  |  |  | 7393.4 | [15 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | Y |  | 14 | 35220896 | CWSP |  | 2021-03-05 11:42
35220936 |  |  |  | FRRB - BUTANO STATE PARK - PN SM |  | Pre-Scope | UNSE |  | 0 | 5016 | 5016 | 0.95 | 0 | 0 | 5016 | 0.95 | 0 | 0 | 0 | 0 | 0 |  |  | PN | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Pescadero | San Mateo | 0 | 0 | [12 empty] | 2186 |  | FRRB
35221704 |  |  |  | STS-POLE_IDLE_REMV - NW C/O BUCKMEADOWS/ |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 2AF | IF | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [37 empty] | 37.7519 | -120.0451
35222045 |  |  |  | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Scoped | UNSE |  | 0 | 4699 | 4699 | 0.88996 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 | [11 empty] | 1 |  |  |  | 6486.3 | [15 empty] | Pope Valley | Napa | 38.7569 | -122.607 | [10 empty] | Y |  | 14 | 35222045 | CWSP |  | 2021-03-05 11:43
35222234 |  |  |  | OAKHURST 1101 - #581 MIAMI MOUNTAIN |  | In Scoping | UNSE |  | 0 | 7920 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 |  |  | YO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oakhurst | Madera | 0 | 0 | [12 empty] | 421 |  | REMG
35222235 |  |  |  | DUNLAP 1102 - #631 UC BERKELEY WHITAKER |  | In Scoping | UNSE |  | 0 | 13728 | 13728 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 13728 | 2.6 | FR | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Kings Canyon National Pk | Tulare | 36.6537 | -118.986 | [12 empty] | 2738 |  | REMG
35222236 |  |  |  | MARIPOSA 2101 - #531 SLAUGHTER HOUSE |  | In Scoping | UNSE |  | 0 | 5227.2 | 5227.2 | 0.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99 |  |  | YO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Mariposa | Mariposa | 37.5115 | -119.9535 | [12 empty] | 428 |  | REMG
35223024 |  | 2021 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 |  | Scoped | UNSE |  | 11827.2 | 0 | 11827.2 | 2.24 | 0 | 0 | 11827 | 2.24 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH |  |  | N | [25 empty] | In Progress | 2021-03-29 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 190000 |  |  | 190000 | 0 | [12 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | Y |  | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35223026 |  | 2021 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 |  | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [25 empty] | In Progress | 2021-03-29 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 190000 |  |  | 190000 | 0 | [12 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | Y |  | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35223027 |  | 2021 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Scoped | ESTS |  | 0 | 10190 | 10190 | 1.9299 | 0 | 0 | 10190 | 1.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-04-30 |  | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 190000 | 34848.7 |  | 190000 | 0 |  | 18.34% | 20776.6 |  |  |  | 18057.03 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | Y |  | 279 | 35192284 | ECOP |  | 2021-03-11 14:16
35223028 |  | 2021 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Scoped | ESTS |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-04-30 | 2021-03-04 | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 190000 |  |  |  | 1124.5 | [9 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | Y |  | 279 | 35192284 | ECOP |  | 2021-03-11 14:16
35223030 |  | 2021 |  | PSPS - BANGOR 1101 CB - MICROGRID |  | Scoped | UNSE |  | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 950000 |  |  | 950000 | 0 |  |  | 12925.5 | [15 empty] | Bangor | Butte | 39.3878 | -121.4038 | [10 empty] | Y |  | 355 |  | PSPS |  | 2021-03-11 09:29
35223032 |  |  |  | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | In Scoping | UNSE |  | 2323.2 | 0 | 2323.2 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Cool | El Dorado | 38.8858 | -121.0157 | [12 empty] | 68 |  | PSPS
35223036 |  | 2021 |  | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Scoped | UNSE |  | 264 | 0 | 264 | 0.05 | 0 | 0 | 0 | 0 | 264 | 0.05 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 500000 |  |  | 500000 | 0 |  |  | 4892.9 | [15 empty] | Grass Valley | Nevada | 39.2376 | -121.0592 | [10 empty] | Y |  | 2134 |  | PSPS |  | 2021-03-11 09:59
35223037 |  | 2021 |  | PSPS - OAKHURST 1101 - OAKHURST |  | Scoped | ESTS |  | 105.6 | 0 | 105.6 | 0.02 | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [9 empty] | Estimator sent this in the wrong way. LPA to reach out | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | INPR | [5 empty] | 2021-07-27 07:00 | 2021-07-30 16:00 | [5 empty] | 500000 | 280281.3 |  | 1 | -499999 |  | 56.05% | 6372.1 |  |  |  | 14014065 | [11 empty] | Oakhurst | Madera | 37.3227 | -119.6344 |  | ML | UG | [7 empty] | Y |  | 847 |  | PSPS |  | 2021-03-11 15:59
35223038 |  |  |  | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | In Scoping | ESTS |  | 2428.8 | 0 | 2428.8 | 0.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 |  |  | ST | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Sutter Creek | Amador | 38.3949 | -120.804 | [12 empty] | 999 | 35223038 | PSPS |  | 2021-03-01 13:14
35223039 |  | 2021 |  | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Scoped | UNSE |  | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 4066 | 0.77008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] Need Basemap |  |  |  | 30d - Apr Fasttrack [2] | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 950000 |  |  | 950000 | 0 |  |  | 10414.2 | [15 empty] | Oroville | Butte | 39.4738 | -121.5307 | [10 empty] | Y |  | 218 |  | PSPS |  | 2021-03-11 10:10
35223060 |  |  |  | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | In Scoping | UNSE |  | 9187.2 | 0 | 9187.2 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Downieville | Sierra | 39.5618 | -120.8274 | [12 empty] | 2010 | 35223060 | PSPS |  | 2021-03-01 13:19
35223061 |  |  |  | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | In Scoping | CNCL |  | 4752 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 |  |  | NB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Calistoga | Napa | 38.5768 | -122.5531 | [12 empty] | 1477 |  | PSPS
35223062 |  |  |  | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | In Scoping | UNSE |  | 950.4 | 0 | 950.4 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 |  |  | NB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Calistoga | Napa | 38.5766 | -122.5839 | [12 empty] | 3098 |  | PSPS
35223063 |  |  |  | PSPS - DUNBAR 1101 - OAKMONT |  | In Scoping | UNSE |  | 798 | 0 | 798 | 0.15114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 |  |  | SO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15114 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4438 | -122.602 | [12 empty] | 2048 | 35223063 | PSPS
35223343 |  | 2021 |  | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Scoped | ESTS |  | 0 | 4329.6 | 4329.6 | 0.82 | 0 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0 | -0.03 |  |  | NV | 08W | FRRB | 2021-05-20 17:00 | [32 empty] | 2021-04-19 |  |  |  |  | Received CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-20 17:00 |  | N/A | 2021-06-18 08:00 | 2022-01-12 17:00 |  | 2022-02-10 17:00 | [8 empty] | 950000 | 3482376.4 | 3490209.3 | 950000 | 0 |  | 366.6% | 52945.8 |  |  |  | 4246800.4878 | [11 empty] | Berry Creek | Butte | 39.6444 | -121.4314 | [10 empty] | Y |  | 1288 |  | FRRB |  | 2021-03-09 11:37
35223344 |  | 2021 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Scoped | ESTS |  | 9065 | 0 | 9065 | 1.7169 | 0 | 0 | 9065 | 1.7169 | 0 | 0 | 0 | 0 | 0 | 9763 | 1.8491 | NV | 08W | FRRB | 2021-02-18 | [8 empty] | 2021-01-27 | [23 empty] | 2021-02-18 | 2021-02-18 | Full |  |  | North Complex Fire - Previously released. If the scope changes and new ERTC required | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7169 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-02-12 08:00 |  | COMP | 2021-02-12 08:00 | 2021-05-12 17:00 |  | 2021-07-08 17:00 | 2021-01-27 | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 7089815 | 4418106.7 | 6324922 | 10286697 | 3196882 | 2136601.8 | 62.31% | 1359558.2 | 3593655 | 4953213.2 |  | 2573370.4772 | [11 empty] | Berry Creek | Butte | 39.6394 | -121.4295 | [10 empty] | Y |  | 1849 |  | FRRB |  | 2021-03-09 11:37
35223345 |  | 2021 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Scoped | UNSC |  | 14353 | 0 | 14353 | 2.7184 | 0 | 0 | 14353 | 2.7184 | 0 | 0 | 0 | 0 | 0 | 19806 | 3.7511 | NV | 08W | FRRB | 2021-02-26 | [8 empty] | 2021-02-17 | [25 empty] | Full |  |  | North Complex Fire - Previously released. If the scope changes and new ERTC required | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7184 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-02-26 |  | COMP | 2021-02-16 | 2021-06-23 17:00 |  | 2021-08-02 17:00 | 2021-02-17 | 2021-04-13 07:00 | 2021-05-30 16:00 | [5 empty] | 7778685 | 8120169.3 | 9514299.24 | 10700839 | 2922154 | 5527338.7 | 104.4% | 1095443.2 | 1155903.1 | 2251346.3 |  | 2987145.1198 | [11 empty] | Berry Creek | Butte | 39.6348 | -121.3915 | [10 empty] | Y |  | 1299 |  | FRRB |  | 2021-03-09 11:37
35223615 |  | 2021 |  | ECOP - LAS GALLINAS A 1105 PH 2 |  | Scoped | UNSE |  | 8606.4 | 0 | 8606.4 | 1.63 | 0 | 0 | 0 | 0 | 8606 | 1.6299 | 0 | 0 | 7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.63 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 | 2022-01-25 17:00 |  | 2022-03-28 17:00 | [8 empty] | 312500 | 1320.1 |  | 312500 | 0 |  | 0.42% | 1002.4 |  |  |  | 809.8773 | [11 empty] | San Rafael | Marin | 38.0443 | -122.6155 | [10 empty] | Y |  | 215 | 35191319 | ECOP |  | 2021-03-05 11:43
35224320 |  |  |  | TULUCAY 1101 RECOND WITH TREE WIRE |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2023-12-25 | [32 empty] | 2023-12-25 | 2023-12-25 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Remove |  |  | N/A | [35 empty] | Napa | Napa | 38.2231 | -122.256 | [12 empty] | 338 |  | WDDB
35224321 |  | 2021 |  | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Scoped | UNSE |  | 0 | 12302.4 | 12302.4 | 2.33 | 0 | 0 | 0 | 0 | 12302 | 2.3299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 1 |  |  |  | 4835.3 | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | Y |  | 52 | 35224321 | CWSP |  | 2021-03-11 09:28
35224377 |  |  |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | In Scoping | UNSE |  | 1108.8 | 0 | 1108.8 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Placerville | El Dorado | 0 | 0 | [12 empty] | 1363 | 35224377 | PSPS |  | 2021-03-01 13:23
35224378 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2 |  | In Scoping | UNSE |  | 19008 | 0 | 19008 | 3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35224712 |  | 2021 |  | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Scoped | UNSE |  | 9134.4 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 0 | 9134 | 1.7299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] 03/10- 02/24: [EOD PUSH] UG – pending basemaps (May 7) |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-05-07 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.73 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 400000 | 390621.4 | 400000 | 400000 | 0 |  | 97.65% | 3330.4 |  |  |  | 225792.7168 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | Y |  | 11 | 35217268 | CWSP |  | 2021-03-03 09:26
35224713 |  | 2021 |  | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Scoped | UNSE |  | 9662.4 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 0 | 9662 | 1.8299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] 03/10 - 02/24: [EOD PUSH] UG – pending basemaps (May 7) 02/21: EST started |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-05-07 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 400000 | 389909.1 | 400000 | 400000 | 0 |  | 97.47% | 2094.1 |  |  |  | 213065.082 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | Y |  | 11 | 35217268 | CWSP |  | 2021-03-03 09:26
35225286 |  |  |  | STS-ANCH_SOIL_REPL - 1106 W. CHURCH ST. |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AA | [5 empty] | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 34.9514 | -120.4527
35225287 |  |  |  | STS-ANCH_SOIL_REPL - A/F 227 GRANT STREE |  |  | ADER |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AA | [5 empty] | 2021-05-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 34.9727 | -120.4334
35225288 |  |  |  | STS-ANCH_SOIL_REPL - S/O 401 DEJOY SANTA |  |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AA | [5 empty] | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 34.957 | -120.4533
35225289 |  |  |  | STS-ANCH_SOIL_REPL - 417 N. RAILROAD SAN |  |  | ESTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | LP | 2AA | [5 empty] | 2021-03-31 | [55 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 34.9575 | -120.4451
35225589 |  | 2021 |  | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Scoped | UNSE |  | 0 | 4699.2 | 4699.2 | 0.89 | 0 | 0 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [6 empty] | [Basemap; OH]03/02: Still pending Pre-design mtg; waiting for PMgr [REDACTED] ; Awaiting Transmission - Engr assigned, approx 2wk turnaround.02/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from [REDACTED] . Fielding of this project was completed on 03/02: 2/23/2021. Design started on 2/24/2021. One Pole is in the Caltrans ROW, so a base map will be needed for the DSDD program.2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  |  | 30d - Mar Fasttrack | Iss_ON HOLD - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 316666 | 14484.8 |  | 316666 | 0 |  | 4.57% | 412.7 |  |  |  | 16275.0562 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | Y |  | 9 | 35217270 | CWSP |  | 2021-03-05 11:44
35225591 |  | 2021 |  | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-03-31 | 2021-03-31 | 2021-03-12 |  |  |  |  | [OH]03/02: EST to submit (3/05); Still pending Pre-design mtg; waiting for PMgr [REDACTED] 02/24: Authorization to begin project without the pre-design fieldwalk was received on 2/18/2021 from [REDACTED] . Fielding of this project was completed on 2/23/2021. Design started on 2/24/2021. With caltransworking on Hwy 29 and a PGE relocation project already complete, verification needed for caltrans ROW.2/23: Status - Unable to get everybody coordinated for walkdown – EST Fielding for design02/16: EST fielding - General statement, Finding Transmission Poles in scope/design. Communicate to Trans Team; also check Highway Crossover/Caltran impacts, will require basemap/permitting. EST to note in SAP longtext |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | Yes | [11 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 316666 | 14378.3 |  | 316666 | 0 |  | 4.54% | 306.2 |  |  |  | 17972.875 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | Y |  | 9 | 35217270 | CWSP |  | 2021-03-11 10:44
35225593 |  | 2021 |  | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Scoped | ADER |  | 0 | 5544 | 5544 | 1.05 | 0 | 0 | 5544 | 1.05 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 400000 | 37960.5 |  | 400000 | 0 |  | 9.49% | 28610.4 |  |  |  | 36152.8571 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8879 | -121.8676 | [10 empty] | Y |  | 377 | 35192280 | ECOP |  | 2021-03-11 12:49
35225594 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Scoped | UNSE |  | 2481.6 | 0 | 2481.6 | 0.47 | 0 | 0 | 0 | 0 | 2482 | 0.47008 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-11-02 17:00 | 2021-02-11 | Y | [25 empty] | In Progress | 2021-03-19 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-02 17:00 |  | INPR | 2022-01-05 08:00 | 2022-03-23 08:00 |  | 2022-05-05 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 250000 |  |  | 1 | -249999 |  |  | 2313.2 | [9 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | ML | UG | [7 empty] | Y |  | 637 | 35192292 | ECOP |  | 2021-03-05 14:52
35225595 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Scoped | UNSE |  | 0 | 5860 | 5860 | 1.1098 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-08-20 17:00 | 2021-02-11 | Y | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | INPR | 2021-09-14 08:00 | 2021-10-29 08:00 |  | 2021-11-29 17:00 |  | 2021-07-16 07:00 | 2021-07-16 16:00 | [5 empty] | 150000 |  |  | 1 | -149999 |  |  | 1732.2 | [9 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | Y |  | 637 | 35192292 | ECOP |  | 2021-03-11 14:35
35225597 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Scoped | ESTS |  | 0 | 3907.2 | 3907.2 | 0.74 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SO | 08W | SH | 2021-07-28 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-28 17:00 |  | INPR | 2021-08-20 08:00 | 2021-10-06 08:00 |  | 2021-11-04 17:00 |  | 2021-07-16 07:00 | 2021-07-16 16:00 | [5 empty] | 150000 |  |  | 1 | -149999 |  |  | 3410.9 | [9 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | Y |  | 637 | 35192292 | ECOP |  | 2021-03-11 14:34
35225598 |  | 2021 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4858 | 0.92008 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-08-06 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | INPR | 2021-08-31 08:00 | 2021-10-15 08:00 |  | 2021-11-15 17:00 |  | 2021-07-16 07:00 | 2021-07-16 16:00 | [5 empty] | 150000 |  |  | 1 | -149999 |  |  | 2647.4 | [9 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | Y |  | 637 | 35192292 | ECOP |  | 2021-03-11 14:34
35225821 |  | 2021 |  | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Scoped | ESTS |  | 5016 | 0 | 5016 | 0.95 | 0 | 0 | 5016 | 0.95 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-05-20 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-20 17:00 |  | N/A | 2021-06-18 08:00 | 2022-01-04 17:00 |  | 2022-02-02 17:00 | [8 empty] | 950000 | 3482088.5 | 3490167.5 | 950000 | 0 |  | 366.5% | 49122.3 |  |  |  | 3665356.3158 | [11 empty] | Berry Creek | Butte | 39.6444 | -121.4314 | [10 empty] | Y |  | 1288 |  | FRRB |  | 2021-03-09 11:37
35225822 |  | 2021 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Scoped | CONS |  | 5647 | 0 | 5647 | 1.0695 | 0 | 0 | 5647 | 1.0695 | 0 | 0 | 0 | 0 | 0 | 4798 | 0.90871 | NV | 08W | FRRB | 2021-03-12 17:00 | [8 empty] | 2021-02-19 | [25 empty] | Full |  |  | North Complex Fire - Previously released. If the scope changes and new ERTC required | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0695 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-12 17:00 |  | COMP | 2021-03-01 | 2021-06-21 17:00 |  | 2021-07-26 17:00 | 2021-02-26 | 2021-03-01 21:24 | 2021-05-07 22:01 | [5 empty] | 950000 | 1284379 | 3743276.52 | 3125130.88 | 2175130.88 | 286170 | 135.2% | 224251.2 | 439578.8 | 663830 |  | 1200906.8744 | [11 empty] | Berry Creek | Butte | 39.6394 | -121.4295 | [10 empty] | Y |  | 1849 |  | FRRB |  | 2021-03-09 11:37
35225823 |  | 2021 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Scoped | CONS |  | 7340 | 0 | 7340 | 1.3902 | 0 | 0 | 7340 | 1.3902 | 0 | 0 | 0 | 0 | 0 | 8431 | 1.5968 | NV | 08W | FRRB | 2021-03-19 17:00 | [8 empty] | 2021-02-02 | [23 empty] | 2021-02-18 | 2021-02-18 | Full |  |  | North Complex Fire - Previously released. If the scope changes and new ERTC required | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3902 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-19 17:00 |  | COMP | 2021-04-07 08:00 | 2021-08-13 17:00 |  | 2021-10-01 17:00 | 2021-02-02 | 2021-03-15 22:56 | 2021-05-14 18:33 | [5 empty] | 950000 | 4767311.6 | 4865530.3 | 950000 | 0 | 349884.9 | 501.8% | 111310.8 | 488804.3 | 600115.1 |  | 3429346.764 | [11 empty] | Berry Creek | Butte | 39.6348 | -121.3915 | [10 empty] | Y |  | 1299 |  | FRRB |  | 2021-03-09 11:37
35225824 |  | 2021 |  | FRRB - WYANDOTTE 1103 - HWY 162 |  | Scoped | UNSC |  | 12150 | 0 | 12150 | 2.3011 | 0 | 0 | 12150 | 2.3011 | 0 | 0 | 0 | 0 | 0 | 15567 | 2.9483 | NV | 08W | FRRB | 2021-03-12 17:00 | [8 empty] | 2021-02-03 | [23 empty] | 2021-02-16 | 2021-02-16 | Full |  |  | Caltrans Permit Required. North Complex Fire - Previously released. If the scope changes and new ERTC required (35200051 is old PM) | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3011 | 0 | 0 |  | 0 | 0 | 0 |  | keep | 2021-03-12 17:00 |  | N/A | 2021-04-09 08:00 | 2021-08-12 17:00 |  | 2021-09-30 17:00 | 2021-02-05 | 2021-04-26 07:00 | 2021-04-26 16:00 | [5 empty] | 950000 | 6916614.9 | 8053977.27 | 950000 | 0 |  | 728.1% | 569892.3 |  |  |  | 3005738.8207 | [11 empty] | Oroville | Butte | 39.5047 | -121.4524 | [10 empty] | Y |  | 1176 |  | FRRB |  | 2021-03-09 11:36
35225825 |  |  |  | CWSP - DESCHUTES 11049718 PH2 |  | Scoped | UNSE |  | 0 | 8217 | 8217 | 1.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35225826 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.1 |  | In Scoping | UNSE |  | 533 | 50237 | 50770 | 9.6155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6155 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6155 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP |  | 2021-03-01 13:30
35225827 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.1 |  | In Scoping | UNSE |  | 0 | 34636.8 | 34636.8 | 6.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.56 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.56 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35225828 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4 |  | In Scoping | UNSE |  | 575 | 42608 | 43183 | 8.1786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1786 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.1786 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP |  | 2021-03-01 13:31
35225829 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5 |  | In Scoping | UNSE |  | 0 | 58713.6 | 58713.6 | 11.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.12 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.12 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP |  | 2021-03-01 13:33
35226240 |  | 2021 |  | CWSP - MARIPOSA 210197142 PH 3 |  | Scoped | PEND |  | 0 | 7814.4 | 7814.4 | 1.48 | 0 | 0 | 7814 | 1.4799 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | YO | 08W | SH | 2021-05-17 |  | Y | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-03 | [16 empty] | 2021-04-19 | [6 empty] | 2021-04-19 |  |  |  |  | CIF Submitted | [8 empty] | 2021-05-31 |  | 2021-05-17 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.48 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-14 17:00 |  | INPR | 2021-06-08 08:00 | 2021-08-31 17:00 |  | 2021-09-28 17:00 | 2021-02-27 | [10 empty] | 655862.69 |  |  |  | 54864.6 | [9 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | Y |  | 36 | 35219268 | CWSP |  | 2021-03-09 10:08
35226241 |  | 2021 |  | CWSP - MARIPOSA 210197142 PH 2 |  | Scoped | ESTS |  | 0 | 7920 | 7920 | 1.5 | 0 | 0 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [20 empty] | 2021-04-20 |  | In Progress | 2021-03-12 |  |  |  | 2021-04-20 |  |  |  |  | Received CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | N/A | 2021-08-31 08:00 | 2021-11-23 17:00 |  | 2021-12-22 17:00 | [11 empty] | 1 |  |  |  | 46124.8 | [9 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | Y |  | 36 | 35219268 | CWSP |  | 2021-03-11 10:06
35226621 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Scoped | UNSE |  | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192282 | ECOP |  | 2021-03-11 10:40
35226622 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Scoped | UNSE |  | 0 | 4013 | 4013 | 0.76004 | 0 | 0 | 4013 | 0.76004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226623 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Scoped | UNSE |  | 0 | 6072 | 6072 | 1.15 | 0 | 0 | 6072 | 1.15 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226624 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Scoped | UNSE |  | 0 | 7709 | 7709 | 1.46 | 0 | 0 | 7709 | 1.46 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 | 2021-03-31 | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.46 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-12-31 07:00 | 2021-12-31 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226625 |  |  |  | FRRB - ELK CREEK 1101 LR 2106 |  | Pre-Scope | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Elk Creek | Glenn | 39.6064 | -122.5416 | [12 empty] | 340 |  | FRRB
35226626 |  |  |  | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Pre-Scope | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Healdsburg | Sonoma | 38.5919 | -122.9622 | [12 empty] | 945 |  | FRRB
35226627 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Scoped | UNSE |  | 0 | 1531.2 | 1531.2 | 0.29 | 0 | 0 | 1531 | 0.28996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded; 30day + 1wk Pre |  |  |  | 30d - Apr Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 150000 |  | 551000 | 150000 | 0 |  |  | 88.8 | [15 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226628 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Scoped | UNSE |  | 4329.6 | 0 | 4329.6 | 0.82 | 0 | 0 | 0 | 0 | 4330 | 0.82008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  |  | 30d - Apr Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 150000 |  |  | 150000 | 0 |  |  | 359 | [15 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35226629 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Scoped | UNSE |  | 23760 | 0 | 23760 | 4.5 | 0 | 0 | 0 | 0 | 23760 | 4.5 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] 03/01 Work awarded - UG, need basemaps (May 14) |  |  |  | 30d - Apr Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 200000 |  |  | 200000 | 0 |  |  | 359 | [15 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35226630 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Scoped | UNSE |  | 0 | 7603.2 | 7603.2 | 1.44 | 0 | 0 | 7608 | 1.4409 | 0 | 0 | 0 | 0 | -0.00090909 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded |  |  |  | 30d - Apr Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 150000 |  | 2736000 | 150000 | 0 | [18 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226631 |  | 2021 |  | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Scoped | UNSE |  | 0 | 8131.2 | 8131.2 | 1.54 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/09: Pre-design sched Mon 3/15; Potential weather impacts. PMgr - requesting ADE assignment 03/01 Work awarded |  |  |  | 30d - Apr Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 150000 |  | 2926000 | 150000 | 0 |  |  | 533.5 | [15 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | Y |  | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226632 |  | 2021 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Scoped | UNSE |  | 792 | 0 | 792 | 0.15 | 0 | 0 | 0 | 0 | 792 | 0.15 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  |  |  | [OH]03/10 - 2/24: [EOD PUSH] Awaiting Scope Clarification (preferred scope in SAP has OH & UG) – [REDACTED] to assist in separating PMs |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-14 07:00 | 2021-06-14 16:00 | [5 empty] | 475000 |  |  | 475000 | 0 |  |  | 1145.8 | [9 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | Y |  | 43 | 35219280 | CWSP |  | 2021-03-10 16:57
35226659 |  |  |  | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.2 |  | In Scoping | UNSE |  | 4382.4 | 5544 | 9926.4 | 1.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.88 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.88 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Nevada City | Nevada | 39.3422 | -121.0615 | [12 empty] | 606 | 35054184 | PRE
35226700 |  | 2021 |  | CWSP - WYANDOTTE 110932586 PH 1.2 |  | Scoped | UNSE |  | 3010 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] Require easment rites 02/24: Not issued to Vendor;[EOD PUSH] UG – pending basemaps (TBD/mid-May bm) |  |  |  | 30d - TBD Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 650000 |  |  | 650000 | 0 | [32 empty] | Y |  | 29 | 35219260 | CWSP |  | 2021-03-04 09:59
35226720 |  |  |  | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.3 |  | In Scoping | UNSE |  | 0 | 2745.6 | 2745.6 | 0.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Nevada City | Nevada | 39.3422 | -121.0615 | [12 empty] | 606 | 35054184 | PRE
35226723 |  |  |  | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.4 |  | In Scoping | UNSE |  | 4065.6 | 1425.6 | 5491.2 | 1.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Nevada City | Nevada | 39.3422 | -121.0615 | [12 empty] | 606 | 35054184 | PRE
35226798 |  | 2021 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Scoped | UNSE |  | 0 | 8395.2 | 8395.2 | 1.59 | 0 | 0 | 0 | 0 | 8395 | 1.59 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Platina | Shasta | 40.3595 | -122.8928 | [12 empty] | 52 | 35224321 | CWSP |  | 2021-03-11 09:30
35226799 |  | 2021 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | Scoped | UNSE |  | 1003.2 | 0 | 1003.2 | 0.19 | 0 | 0 | 0 | 0 | 1003 | 0.18996 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [6 empty] | [Basemap; UG] Need Base Map |  |  |  | 30d - Apr Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Platina | Shasta | 40.3595 | -122.8928 | [12 empty] | 52 | 35224321 | CWSP |  | 2021-03-11 09:30
35226819 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Scoped | UNSE |  | 0 | 10507 | 10507 | 1.99 | 0 | 0 | 0 | 0 | 10507 | 1.99 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:46
35226845 |  | 2021 |  | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Scoped | ESTS |  | 0 | 13833.6 | 13833.6 | 2.62 | 0 | 0 | 13834 | 2.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2021-06-30 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | 2021-04-30 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-30 17:00 |  | INPR | 2021-07-23 08:00 | 2021-10-29 17:00 |  | 2021-12-30 17:00 |  | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 450000 | 2311825 |  | 1 | -449999 |  | 513.7% | 10541.4 |  |  |  | 882375.9542 | [11 empty] | Placerville | El Dorado | 38.7201 | -120.861 |  | TL | OH | [7 empty] | Y |  | 811 | 35192291 | ECOP |  | 2021-03-11 15:59
35226846 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Scoped | ESTS |  | 0 | 9153 | 9153 | 1.7335 | 0 | 0 | 9153 | 1.7335 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-30 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | 2021-04-20 |  |  |  |  | [OH] 03/10: Job walk reschd (3/12); weather 03/03 - 02/24: Ph1.2 Scope changed issued 2/24; added protection; Wen 3/9 Walk |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7335 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 3054367.7 | 3089168.45 | 70000 | 0 |  | 4363% | 2030.9 |  |  |  | 1761942.6916 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-11 10:07
35226847 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Scoped | ESTS |  | 0 | 10475 | 10475 | 1.9839 | 0 | 0 | 10475 | 1.9839 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-30 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | 2021-04-20 |  |  |  |  | [OH] 03/10: Job walk reschd (3/12); weather 03/03 - 02/24: All prelim maps; done; sub 2/25-26; need to upload to EES; Wen 3/9 Walk |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9839 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 3777833 | 3812484.87 | 70000 | 0 |  | 5397% | 1853.1 |  |  |  | 1904244.2234 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-11 10:07
35226848 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Scoped | ESTS |  | 0 | 15153 | 15153 | 2.8699 | 0 | 0 | 15153 | 2.8699 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-11 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-26 | 2021-03-26 |  |  |  |  | [OH] 03/10: Jobwalk tentative 3/18 03/03- 02/24: (3mile) Targeting prelims ready 2/25-26; Job Walk sched (TBD) |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8699 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-11 17:00 |  | INPR | 2021-08-03 08:00 | 2021-12-07 17:00 |  | 2022-01-24 17:00 |  | 2021-05-21 07:00 | 2021-05-21 16:00 | [8 empty] | 1 |  |  |  | 480.3 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-11 10:21
35226849 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Scoped | UNSE |  | 9398 | 0 | 9398 | 1.7799 | 0 | 0 | 0 | 0 | 9398 | 1.7799 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-08-27 17:00 | 2021-02-22 | Y | 2021-05-31 | [6 empty] | [Basemap; UG] 02/24:[EOD PUSH] UG – pending basemaps (4/12 bm); OH piece separated |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-04-12 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-27 17:00 |  | INPR | 2021-10-19 08:00 | 2022-02-08 08:00 |  | 2022-04-08 17:00 |  | 2021-05-21 07:00 | 2021-05-21 16:00 | [8 empty] | 1 |  |  |  | 2225 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-05 14:57
35226850 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Scoped | ESTS |  | 0 | 9187 | 9187 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-02 | 2021-04-09 |  |  |  |  | [OH] 03/10: EST target sub (3/12); applying JW adjustments 03/03 - 02/24: Prelim maps ready by 2/26; Walk next Thurs 3/4 |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | 2021-08-24 08:00 |  | 2021-10-22 17:00 |  | 2021-05-21 07:00 | 2021-05-21 16:00 | [8 empty] | 1 |  |  |  | 3141.1 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-11 14:33
35226851 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Scoped | ESTS |  | 0 | 11563 | 11563 | 2.19 | 0 | 0 | 11563 | 2.19 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-12 | 2021-03-12 |  |  |  |  | [OH] 03/10: Job walk (03/11) 03/03: Job walk (TBD) 02/24: Prelim maps ready by 2/26 |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-25 08:00 | 2021-09-24 08:00 |  | 2021-11-24 17:00 |  | 2021-05-21 07:00 | 2021-05-21 16:00 | [8 empty] | 1 |  |  |  | 1992.9 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-11 10:20
35226852 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Scoped | ESTS |  | 0 | 13164 | 13164 | 2.4932 | 0 | 0 | 13164 | 2.4932 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-16 | 2021-03-01 | Y | 2021-04-16 | 2021-04-30 | 2021-04-16 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 7914215.7 | 7975840.77 | 70000 | 0 |  | 11306% | 9764.1 |  |  |  | 3174343.5807 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 159 | 35062376 | PRE |  | 2021-03-11 10:07
35226853 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Scoped | ESTS |  | 0 | 14807 | 14807 | 2.8044 | 0 | 0 | 14807 | 2.8044 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-30 | 2021-03-01 | Y | 2021-04-30 | 2021-04-30 | 2021-04-16 | [22 empty] | N/A | 2021-04-19 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8044 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 5739276.8 | 5802223.75 | 70000 | 0 |  | 8199% | 14838.4 |  |  |  | 2046557.8108 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226854 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Scoped | ESTS |  | 0 | 5438.4 | 5438.4 | 1.03 | 0 | 0 | 5438 | 1.0299 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-04-16 | 2021-03-01 | Y | 2021-04-16 | 2021-04-30 | 2021-04-16 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.03 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 2069574.7 | 2086816.03 | 70000 | 0 |  | 2957% | 29922.4 |  |  |  | 2009295.8252 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226856 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Scoped | ESTS |  | 0 | 10262 | 10262 | 1.9436 | 0 | 0 | 10262 | 1.9436 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-16 | 2021-03-01 | Y | 2021-04-16 | 2021-04-30 | 2021-04-16 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-05-21 07:00 | 2021-05-21 16:00 | [5 empty] | 70000 | 8797079.2 | 8862572.16 | 70000 | 0 |  | 12567% | 4474.2 |  |  |  | 4526269.5553 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226857 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Scoped | UNSE |  | 4488 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0 | 4488 | 0.85 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 1191.2 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174478 | ECOP |  | 2021-03-11 13:59
35226858 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Scoped | UNSE |  | 0 | 2006.4 | 2006.4 | 0.38 | 0 | 0 | 0 | 0 | 2006 | 0.37992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 492.3 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226859 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Scoped | UNSE |  | 0 | 4646.4 | 4646.4 | 0.88 | 0 | 0 | 0 | 0 | 4646 | 0.87992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 557.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226861 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Scoped | UNSE |  | 0 | 3484.8 | 3484.8 | 0.66 | 0 | 0 | 0 | 0 | 3485 | 0.66004 | 0 | 0 | -3.7879e-05 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 566.7 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226862 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Scoped | UNSE |  | 0 | 3062.4 | 3062.4 | 0.58 | 0 | 0 | 0 | 0 | 3062 | 0.57992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 155000 |  |  | 155000 | 0 |  |  | 454.3 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226863 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Scoped | UNSE |  | 0 | 2786 | 2786 | 0.52765 | 0 | 0 | 0 | 0 | 2786 | 0.52765 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52765 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 67857 |  |  |  | 110.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226864 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Scoped | UNSE |  | 0 | 1724 | 1724 | 0.32652 | 0 | 0 | 0 | 0 | 1724 | 0.32652 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 67857 |  |  |  | 110.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226865 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Scoped | UNSE |  | 0 | 1243 | 1243 | 0.23542 | 0 | 0 | 0 | 0 | 1243 | 0.23542 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23542 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | 67857 |  |  |  | 110.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226866 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Scoped | UNSE |  | 0 | 2736 | 2736 | 0.51818 | 0 | 0 | 0 | 0 | 2736 | 0.51818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 14:17
35226870 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Scoped | UNSE |  | 0 | 2215 | 2215 | 0.41951 | 0 | 0 | 0 | 0 | 2215 | 0.41951 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41951 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-11 14:17
35226871 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Scoped | UNSE |  | 6124 | 420 | 6544 | 1.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [Hybrid] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [12 empty] | 474 | 35174479 | ECOP |  | 2021-03-01 13:46
35226872 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Scoped | UNSE |  | 2552 | 1168 | 3720 | 0.70455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [Hybrid] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [12 empty] | 474 | 35174479 | ECOP |  | 2021-03-01 13:46
35226873 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Scoped | UNSE |  | 5488 | 0 | 5488 | 1.0394 | 0 | 0 | 0 | 0 | 5488 | 1.0394 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35226878 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Scoped | UNSE |  | 3109 | 0 | 3109 | 0.58883 | 0 | 0 | 0 | 0 | 3109 | 0.58883 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35226900 |  | 2021 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 |  | Scoped | UNSE |  | 0 | 3643.2 | 3643.2 | 0.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69 |  |  | NV | 08W | SH - Remote Grid | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Platina | Shasta | 40.3595 | -122.8928 | [12 empty] | 52 | 35224321 | CWSP |  | 2021-03-04 14:32
35227001 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Scoped | UNSE |  | 3809 | 0 | 3809 | 0.7214 | 0 | 0 | 0 | 0 | 3809 | 0.7214 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7214 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227002 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Scoped | UNSE |  | 2286 | 0 | 2286 | 0.43295 | 0 | 0 | 0 | 0 | 2286 | 0.43295 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43295 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227003 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Scoped | UNSE |  | 3067 | 0 | 3067 | 0.58087 | 0 | 0 | 0 | 0 | 3067 | 0.58087 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58087 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227004 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Scoped | UNSE |  | 1839 | 0 | 1839 | 0.3483 | 0 | 0 | 0 | 0 | 1839 | 0.3483 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3483 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174479 | ECOP |  | 2021-03-09 14:28
35227007 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Scoped | UNSE |  | 15183 | 0 | 15183 | 2.8756 | 0 | 0 | 0 | 0 | 15183 | 2.8756 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 117750 |  |  | 118750 | 1000 |  |  | 347.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-02-26 12:06
35227010 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Scoped | UNSE |  | 0 | 834 | 834 | 0.15795 | 0 | 0 | 0 | 0 | 834 | 0.15795 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15795 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 584.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-02-26 13:16
35227013 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 |  | Scoped | UNSE |  | 0 | 168 | 168 | 0.031818 | 0 | 0 | 0 | 0 | 168 | 0.031818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 | [18 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-02-26 13:17
35227015 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Scoped | UNSE |  | 0 | 5106 | 5106 | 0.96705 | 0 | 0 | 0 | 0 | 5106 | 0.96705 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96705 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 110.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-02-26 12:06
35227018 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Scoped | UNSE |  | 0 | 6312 | 6312 | 1.1955 | 0 | 0 | 0 | 0 | 6312 | 1.1955 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1955 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 703.4 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-11 14:00
35227021 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Scoped | UNSE |  | 0 | 1144 | 1144 | 0.21667 | 0 | 0 | 0 | 0 | 1144 | 0.21667 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21667 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 703.4 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-02-26 13:18
35227025 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Scoped | UNSE |  | 2900 | 0 | 2900 | 0.54924 | 0 | 0 | 0 | 0 | 2900 | 0.54924 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [6 empty] | [Basemap; UG] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  |  | 118750 | 0 |  |  | 347.9 | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-04 09:07
35227027 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | [6 empty] | [OH] |  |  |  | 30d - Apr Fasttrack [2] | R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-05 11:46
35227028 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Scoped | UNSE |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Cal-trans-Basemap |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-05 11:46
35227029 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Scoped | UNSE |  | 0 | 5491 | 5491 | 1.04 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Basemap; OH] Need Base Map |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [44 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227030 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Scoped | UNSE |  | 7287 | 1796 | 9083 | 1.7203 | 0 | 0 | 1796 | 0.34015 | 7287 | 1.3801 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Hybrid] Need Base Map |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7203 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227031 |  | 2021 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Scoped | UNSE |  | 8184 | 2534 | 10718 | 2.0299 | 0 | 0 | 2534 | 0.47992 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [6 empty] | [Hybrid] Need Base Map |  |  |  | 30d - TBD Fasttrack [2] | Iss_R0.0 - Estimating | [12 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | Y |  | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227032 |  | 2021 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Scoped | UNSE |  | 0 | 4600 | 4600 | 0.87121 | 0 | 0 | 0 | 0 | 4600 | 0.87121 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87121 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 237833 |  |  | 237833 | 0 |  |  | 454.3 | [15 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | Y |  | 951 | 35191937 | ECOP |  | 2021-03-11 14:18
35227033 |  | 2021 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Scoped | UNSE |  | 0 | 6936 | 6936 | 1.3136 | 0 | 0 | 0 | 0 | 6936 | 1.3136 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3136 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 237833 |  |  | 237833 | 0 |  |  | 110.9 | [15 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | Y |  | 951 | 35191937 | ECOP |  | 2021-02-26 12:07
35227096 |  | 2021 |  | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Scoped | CONS |  | 0 | 5596.8 | 5596.8 | 1.06 | 0 | 0 | 5596.8 | 1.06 | 0 | 0 | 0 | 0 | 0 | 5598 | 1.0602 | YO | 08W | SH - Wind | 2021-03-22 17:00 |  | Y | [6 empty] | 2021-01-23 | [16 empty] | 2021-02-17 | 2021-02-17 | [5 empty] | 2021-02-17 | 2021-02-17 | Partial |  |  | Pending veg scope | Partial |  |  | Yes |  |  |  |  | 2021-03-15 |  | 2021-02-22 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.06 | 0 | 0 | 1.0598 | 1.0598 | 0 | 0 |  | Keep | 2021-03-22 17:00 |  | N/A | 2021-02-02 08:00 | 2021-02-16 17:00 | Yes | 2021-06-10 17:00 | 2021-01-23 | 2021-02-16 07:00 | 2021-04-30 16:00 | [7 empty] | 2183706 | 326951.18 |  |  |  | 255746.9 | 941909.8 | 1197656.7 | [13 empty] | Fish Camp | Mariposa | 37.4809 | -119.6371 | [10 empty] | Y |  | 1975 |  | STRM |  | 2021-03-09 08:37
35227160 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Scoped | UNSE |  | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:48
35227161 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Scoped | UNSE |  | 0 | 3907 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:48
35227162 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Scoped | UNSE |  | 1690 | 0 | 1690 | 0.32008 | 0 | 0 | 0 | 0 | 1690 | 0.32008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227163 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Scoped | UNSE |  | 0 | 2429 | 2429 | 0.46004 | 0 | 0 | 0 | 0 | 2429 | 0.46004 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227164 |  | 2021 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Scoped | UNSE |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | Y |  | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227165 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Scoped | UNSE |  | 5333 | 0 | 5333 | 1.01 | 0 | 0 | 0 | 0 | 5333 | 1.01 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 352.9 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227167 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 288.2 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227168 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Scoped | UNSE |  | 8290 | 0 | 8290 | 1.5701 | 0 | 0 | 0 | 0 | 8290 | 1.5701 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 288.2 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227201 |  | 2021 |  | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Scoped | CONS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 0 | 4355 | 0.82481 | YO | 08W | SH - Wind | 2021-03-22 17:00 |  | Y | [6 empty] | 2021-01-24 | [16 empty] | 2021-02-17 | 2021-02-17 | [5 empty] | 2021-02-17 | 2021-02-17 | Partial |  |  | Pending veg scope | Partial |  |  | Yes |  |  |  |  | 2021-03-15 |  | 2021-02-22 | [10 empty] | 0 | 0 | 0 | 0 | 4889 | 0.92595 | 0.92595 | -0.12595 | 0.92595 | 0 | 0.94943 | 0.023485 | 0 | 0 |  | Keep | 2021-03-22 17:00 |  | N/A | 2021-02-22 08:00 | 2021-03-30 17:00 |  | 2021-05-31 17:00 | 2021-02-01 | 2021-02-09 06:03 | 2021-04-02 17:26 | [8 empty] | 512371.91 |  |  |  | 265293 | 761327.5 | 1026620.5 | [13 empty] | Fish Camp | Mariposa | 37.4809 | -119.6371 | [10 empty] | Y |  | 1975 |  | STRM |  | 2021-03-11 11:21
35227204 |  |  |  | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.5 |  | In Scoping | UNSE |  | 0 | 6864 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Nevada City | Nevada | 39.3422 | -121.0615 | [12 empty] | 606 | 35054184 | PRE
35227260 |  | 2021 |  | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Scoped | ESTS |  | 0 | 12443 | 12443 | 2.3566 | 0 | 0 | 12443 | 2.3566 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-16 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | 2021-04-16 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3566 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-16 17:00 |  | INPR | 2021-07-13 08:00 | 2021-11-23 17:00 |  | 2022-01-24 17:00 | [8 empty] | 275000 | 2050512.1 |  | 1 | -274999 |  | 745.6% | 915.2 |  |  |  | 870103.9852 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | Y |  | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35227261 |  | 2021 |  | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Scoped | ESTS |  | 0 | 11421 | 11421 | 2.1631 | 0 | 0 | 11421 | 2.1631 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-18 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | 2021-04-16 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1631 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-18 17:00 |  | INPR | 2021-07-13 08:00 | 2021-11-23 17:00 |  | 2022-01-24 17:00 | [8 empty] | 250000 | 2052176.4 |  | 1 | -249999 |  | 820.9% | 14672.7 |  |  |  | 948734.0331 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | Y |  | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35227262 |  | 2021 |  | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Scoped | ESTS |  | 0 | 6152 | 6152 | 1.1652 | 0 | 0 | 6152 | 1.1652 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-07-02 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-02 17:00 |  | INPR | 2021-07-27 08:00 | 2021-12-07 17:00 |  | 2022-02-07 17:00 | [8 empty] | 150000 | 1883041.6 |  | 1 | -149999 |  | 1255% | 15646.1 |  |  |  | 1616134.5332 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | Y |  | 22 | 35219097 | CWSP |  | 2021-03-11 16:00
35227263 |  | 2021 |  | CWSP - MARIPOSA 2102CB PH 2 |  | Scoped | ESTS |  | 0 | 1315.42 | 1315.42 | 0.24913 | 0 | 0 | 1315 | 0.24905 | 0 | 0 | 0 | 0 | 7.9545e-05 |  |  | YO | 08W | SH | 2021-05-25 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | 2021-03-31 | [22 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24913 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-25 17:00 |  | N/A | 2021-06-22 08:00 | 2021-10-19 17:00 |  | 2021-11-18 17:00 | [11 empty] | 1 |  |  |  | 35936.1 | [15 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | Y |  | 35 | 35219266 | CWSP |  | 2021-03-11 10:08
35227651 |  |  |  | CWSP - VACAVILLE 11046542 PH 1.2 |  | In Scoping | UNSE |  | 0 | 12196.8 | 12196.8 | 2.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.31 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35219276 | CWSP
35227652 |  |  |  | CWSP - VACAVILLE 11046542 PH 1.3 |  | In Scoping | UNSE |  | 2164.8 | 0 | 2164.8 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35219276 | CWSP
35227653 |  |  |  | CWSP - VACAVILLE 11046542 PH 1.4 |  | In Scoping | UNSE |  | 0 | 10560 | 10560 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35219276 | CWSP
35227654 |  |  |  | CWSP - VACAVILLE 11046542 PH 1.5 |  | In Scoping | UNSE |  | 0 | 3801.6 | 3801.6 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35219276 | CWSP
35227655 |  | 2021 |  | CWSP - KIRKER 2104442850 PH 1.2 |  | Scoped | UNSE |  | 0 | 19905.6 | 19905.6 | 3.77 | 0 | 0 | 0 | 0 | 19906 | 3.7701 | 0 | 0 | -7.5758e-05 |  |  | DI | 08W | SH - Remote Grid |  |  | Y | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.77 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 450000 |  |  | 450000 | 0 |  |  | 265.3 | [15 empty] | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | Y |  | 21 | 35219096 | CWSP |  | 2021-03-11 11:20
35227656 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2.3 |  | In Scoping | UNSE |  | 0 | 3960 | 3960 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35227657 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2.4 |  | In Scoping | UNSE |  | 5280 | 0 | 5280 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35227658 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2.5 |  | In Scoping | UNSE |  | 211.2 | 0 | 211.2 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35227659 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2.6 |  | In Scoping | UNSE |  | 1267.2 | 0 | 1267.2 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35227860 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:50
35227861 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Scoped | UNSE |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227862 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Scoped | UNSE |  | 0 | 5755 | 5755 | 1.09 | 0 | 0 | 5755 | 1.09 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227863 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227864 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Scoped | UNSE |  | 3274 | 0 | 3274 | 0.62008 | 0 | 0 | 0 | 0 | 3274 | 0.62008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 64.8 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227866 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Scoped | UNSE |  | 0 | 2746 | 2746 | 0.52008 | 0 | 0 | 2746 | 0.52008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227867 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Scoped | UNSE |  | 0 | 5174 | 5174 | 0.97992 | 0 | 0 | 5174 | 0.97992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 103.7 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:52
35227868 |  | 2021 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Scoped | UNSE |  | 0 | 2112 | 2112 | 0.4 | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 64.8 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35217271 | CWSP |  | 2021-03-05 11:52
35227870 |  |  |  | CWSP - VACAVILLE 11046542 - PH 2.2 |  | In Scoping | UNSE |  | 0 | 7128 | 7128 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.35 |  |  | SA | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.35 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Vacaville | Solano | 38.3423 | -122.0077 | [12 empty] | 42 | 35224378 | CWSP
35228186 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Scoped | UNSE |  | 7867 | 0 | 7867 | 1.49 | 0 | 0 | 0 | 0 | 7867 | 1.49 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 64.8 | [15 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220895 | CWSP |  | 2021-03-05 11:52
35228187 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Scoped | UNSE |  | 0 | 3326 | 3326 | 0.62992 | 0 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220895 | CWSP |  | 2021-03-05 11:52
35228188 |  | 2021 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Scoped | UNSE |  | 0 | 19694.4 | 19694.4 | 3.73 | 0 | 0 | 19694 | 3.7299 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH - Remote Grid | 2021-06-14 17:00 |  | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.73 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | 2021-11-17 17:00 |  | 2022-01-18 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 | [19 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | Y |  | 14 | 35220895 | CWSP |  | 2021-03-11 10:42
35228449 |  | 2021 |  | RIO DELL STORM REBUILD |  | Scoped | CONS |  | 0 | 15048 | 15048 | 2.85 | 0 | 0 | 15048 | 2.85 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH - Wind | 2021-03-01 |  | Y | [6 empty] | 2021-02-10 | [16 empty] | 2021-02-17 | 2021-02-17 | [5 empty] | 2021-02-17 | 2021-02-17 | Full |  |  | Revised Veg scope. New project number will be created for veg scope. |  |  |  | Yes |  |  |  |  | 2021-03-07 | Y | 2021-02-12 | [10 empty] | 0 | 0 | 0 | 0 | 14816 | 2.8061 | 2.8061 | 0.043939 | 2.8061 | 0 | 2.8061 | 0 | 0 | 0 |  | Keep | 2021-03-01 |  | N/A | 2021-02-08 | 2021-04-06 17:00 |  | 2021-06-07 17:00 | 2021-02-19 | [7 empty] | 6518166 | 2526192.6 |  | 6518166 | 0 | 4602010.6 | 38.75% | 1584540.3 | 331615.1 | 1916155.4 |  | 886383.3684 | [5 empty] | Prioritized | [5 empty] | Myers Flat | Humboldt | 40.3679 | -124.0594 | [10 empty] | Y |  | 585 |  | STRM |  | 2021-03-11 16:01
35228774 |  |  |  | PSPS - DUNBAR 1101 - OAKMONT PH 2 |  | In Scoping | UNSE |  | 5143 | 0 | 5143 | 0.97405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97405 |  |  | SO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97405 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4438 | -122.602 | [12 empty] | 2048 | 35223063 | PSPS
35228775 |  |  |  | PSPS - DUNBAR 1101 - OAKMONT PH 3 |  | In Scoping | UNSE |  | 4679 | 0 | 4679 | 0.88617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88617 |  |  | SO | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88617 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Santa Rosa | Sonoma | 38.4438 | -122.602 | [12 empty] | 2048 | 35223063 | PSPS
35229043 |  |  |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 |  | In Scoping | UNSE |  | 2183 | 0 | 2183 | 0.41345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41345 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41345 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Feather Falls | Butte | 39.5752 | -121.3053 | [10 empty] | Y |  | 1849 |  | FRRB |  | 2021-03-09 11:36
35229051 |  |  |  | CORNING 1102 - REMOTE GRID #299 & # 300 |  | In Scoping | UNSE |  | 0 | 16051 | 16051 | 3.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Flournoy | Tehama | 0 | 0 | [12 empty] | 413 |  | REMG |  | 2021-03-09 12:17
35229119 |  | 2021 |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Scoped | UNSE |  | 3221 | 0 | 3221 | 0.61004 | 0 | 0 | 3221 | 0.61004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 | 2021-02-18 | Y | 2021-04-30 | [6 empty] | [Basemap; UG] 03/09 - 03/02: EOD date on hold for basemap receipt 02/24: [EOD PUSH] UG – pending basemaps (Mar 12) |  |  |  | 30d - Mar Fasttrack | Iss_R0.0 - Estimating | [12 empty] | In Progress | 2021-03-12 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-06-30 07:00 | 2021-06-30 16:00 | [5 empty] | 475000 |  |  | 475000 | 0 |  |  | 2465.3 | [9 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | Y |  | 23 | 35219098 | CWSP |  | 2021-03-11 11:36
35231543 |  | 2021 |  | CWSP - TIDEWATER 210614072 PH 1.2 |  | Scoped | ESTS |  | 6864 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 6864 | 1.3 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [25 empty] | In Progress | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 350000 |  |  | 350000 | 0 |  |  | 1311.1 | [15 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | Y |  | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35231544 |  | 2021 |  | CWSP - TIDEWATER 210614072 PH 1.3 |  | Scoped | ESTS |  | 0 | 6336 | 6336 | 1.2 | 0 | 0 | 6336 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 181000 |  |  | 181000 | 0 |  |  | 644.9 | [15 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | Y |  | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35231607 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Scoped | ESTS |  | 0 | 8691 | 8691 | 1.646 | 0 | 0 | 8691 | 1.646 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-04-30 | 2021-02-18 | Y | 2021-04-30 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/10 - 03/03: Job Walk 03/16; waiting on walk to submit; Enviromental rvwing water way easements (due back 3/12) 02/24:Prelim maps ready by 2/26 |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.646 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 70000 | 2836423.6 | 2867422.68 | 70000 | 0 |  | 4052% | 2070.9 |  |  |  | 1723198.321 | [8 empty] | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-11 10:06
35231608 |  | 2021 |  | CNCL-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Scoped | UNSE |  | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0 | 0 | 0 | 1742 | 0.32992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [6 empty] | [OH] 03/11: Repurposed order number for Phase 1.6, added scope, remove 856’ of hardening in Phase 1.2. 02/24: Being cancelled ao 02/24; was not commity approved scope |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | In Progress | 2021-04-12 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [8 empty] | 1 |  |  |  | 1265.8 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-04 09:43
35231609 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Scoped | ESTS |  | 0 | 7023 | 7023 | 1.3301 | 0 | 0 | 7023 | 1.3301 | 0 | 0 | 0 | 0 | 0 | 8783 | 1.6634 | SI | 08W | SH | 2021-03-31 | 2021-02-18 | Y | 2021-03-31 | 2021-04-02 | 2021-04-02 |  |  |  |  | [OH] 03/10 - 03/03: Job Walk 3/16 02/24: Prelim maps ready by 2/26 |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [12 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3301 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [5 empty] | 2021-07-09 07:00 | 2021-07-09 16:00 | [5 empty] | 70000 | 2615040.7 | 2649841.53 | 70000 | 0 |  | 3736% | 2743.7 |  |  |  | 1966028.0359 |  |  |  | Site survey requested 3/9/2021 |  |  |  |  | SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062374 | PRE |  | 2021-03-11 10:02
35231620 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.2 |  | In Scoping | UNSE |  | 13740 | 0 | 13740 | 2.6023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6023 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6023 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231621 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.3 |  | In Scoping | UNSE |  | 13276 | 0 | 13276 | 2.5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5144 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5144 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231622 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.4 |  | In Scoping | UNSE |  | 24550 | 0 | 24550 | 4.6496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6496 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.6496 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231623 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.5 |  | In Scoping | UNSE |  | 0 | 7120 | 7120 | 1.3485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3485 |  |  | HB | 08W | SH - Remote Grid | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3485 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP |  | 2021-03-04 14:34
35231624 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.6 |  | In Scoping | UNSE |  | 0 | 6228 | 6228 | 1.1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1795 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1795 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231625 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.7 |  | In Scoping | UNSE |  | 0 | 4152 | 4152 | 0.78636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78636 |  |  | HB | 08W | SH - Remote Grid | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78636 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP |  | 2021-03-04 14:34
35231626 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.8 |  | In Scoping | UNSE |  | 0 | 4124 | 4124 | 0.78106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78106 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78106 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231627 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.9 |  | In Scoping | UNSE |  | 0 | 1862 | 1862 | 0.35265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35265 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35265 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231628 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.10 |  | In Scoping | UNSE |  | 0 | 1078 | 1078 | 0.20417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20417 |  |  | HB | 08W | SH - Remote Grid | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20417 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP |  | 2021-03-04 14:34
35231629 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.11 |  | In Scoping | UNSE |  | 0 | 6382 | 6382 | 1.2087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2087 |  |  | HB | 08W | SH - Remote Grid | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2087 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP |  | 2021-03-04 14:34
35231630 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.12 |  | In Scoping | UNSE |  | 0 | 1574 | 1574 | 0.29811 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29811 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29811 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35231631 |  |  |  | CWSP - HIGHLANDS 1102628 PH 1.13 |  | In Scoping | UNSE |  | 0 | 2000 | 2000 | 0.37879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 |  |  | HB | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.37879 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Clearlake | Lake | 38.9822 | -122.6031 | [12 empty] | 27 | 35219099 | CWSP
35232280 |  | 2021 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Scoped | ESTS |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 | 3235 | 0.61269 | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-02 | 2021-04-09 |  |  |  |  | [OH] 03/10: EST target sub (3/12); applying JW adjustments and ADE rvw revisions 03/03 - 02/24: [EOD PUSH] Walk next Thurs 3/4 |  |  |  | 30d - Mar Fasttrack | R0.0 - Estimating | [10 empty] | 2021-04-13 | 2021-04-13 | N/A |  |  |  |  | 2021-04-13 | 2021-04-13 |  |  |  | received CIF | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | 2021-07-27 08:00 |  | 2021-09-24 17:00 |  | 2021-06-30 07:00 | 2021-06-30 16:00 | [8 empty] | 1 |  |  |  | 3197.7 | [15 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | Y |  | 227 | 35062375 | PRE |  | 2021-03-11 14:33
35232298 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Scoped | UNSE |  | 1276 | 0 | 1276 | 0.24167 | 0 | 0 | 1276 | 0.24167 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24167 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500468.3 | 845833.33 | 67857 | 0 |  | 737.5% | 4216.3 |  |  |  | 2070903.3103 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:01
35232442 |  |  |  | CWSP - DESCHUTES 11049718 PH 2.2 |  | Scoped | UNSE |  | 0 | 16251 | 16251 | 3.0778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:23
35232443 |  |  |  | CWSP - DESCHUTES 11049718 PH 2.3 |  | Scoped | UNSE |  | 0 | 5468 | 5468 | 1.0356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35232444 |  |  |  | CWSP - DESCHUTES 11049718 PH 2.4 |  | Scoped | UNSE |  | 0 | 18648 | 18648 | 3.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:23
35232445 |  |  |  | CWSP - DESCHUTES 11049718 PH 2.5 |  | Scoped | UNSE |  | 0 | 13748 | 13748 | 2.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35232650 |  | 2021 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 |  | Scoped | UNSE |  | 9028 | 0 | 9028 | 1.7098 | 0 | 0 | 0 | 0 | 9028 | 1.7098 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [25 empty] | In Progress | 2021-04-15 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 316667 |  |  | 316667 | 0 | [18 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | Y |  | 45 | 35219281 | CWSP |  | 2021-03-11 10:30
35232651 |  | 2021 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 |  | Scoped | UNSE |  | 0 | 9187.2 | 9187.2 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [25 empty] | N/A | [31 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 316667 |  |  | 316667 | 0 | [18 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | Y |  | 45 | 35219281 | CWSP |  | 2021-03-11 10:01
35232718 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | In Scoping | UNSE |  | 6336 | 0 | 6336 | 1.2 | 0 | 0 | 6336 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 118750 |  | 4200000 | 118750 | 0 |  |  | 3484.6 | [15 empty] | Berry Creek | Butte | 39.6343 | -121.4112 | [10 empty] | Y |  | 1849 |  | FRRB |  | 2021-03-09 17:01
35232960 |  |  |  | CWSP - DESCHUTES 11049718 PH1.2 |  | Scoped | UNSE |  | 0 | 16057 | 16057 | 3.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [12 empty] | 48 | 35219286 | CWSP |  | 2021-03-09 17:18
35233038 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Scoped | UNSE |  | 1227 | 0 | 1227 | 0.23239 | 0 | 0 | 1227 | 0.23239 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23239 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500185.3 | 813352.27 | 67857 | 0 |  | 737.1% | 185.3 |  |  |  | 2152386.621 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:01
35233039 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Scoped | UNSE |  | 1936 | 0 | 1936 | 0.36667 | 0 | 0 | 1936 | 0.36667 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36667 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 1283333.33 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 1363839.5455 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:01
35233166 |  |  |  | FRRB - BIG BEND 11021972 - B4 |  | Scoped | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.6444 | -121.4314 | [12 empty] | 1288 |  | FRRB |  | 2021-03-01 13:36
35233300 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Scoped | UNSE |  | 1711 | 0 | 1711 | 0.32405 | 0 | 0 | 1711 | 0.32405 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32405 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 1134185.61 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 1543187.2355 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:01
35233301 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Scoped | UNSE |  | 1920 | 0 | 1920 | 0.36364 | 0 | 0 | 1920 | 0.36364 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36364 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 1272727.27 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 1375204.875 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:02
35233302 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 |  | Scoped | UNSE |  | 651 | 0 | 651 | 0.1233 | 0 | 0 | 651 | 0.1233 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1233 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 |  | 500000 | 67857 | 0 | [18 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:02
35233303 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Scoped | UNSE |  | 461 | 0 | 461 | 0.087311 | 0 | 0 | 461 | 0.087311 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.087311 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 500000 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 5727534.4035 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-11 12:38
35233304 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 |  | Scoped | UNSE |  | 1606 | 0 | 1606 | 0.30417 | 0 | 0 | 1606 | 0.30417 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.30417 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 |  | 1064583.33 | 67857 | 0 | [18 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:02
35233305 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Scoped | UNSE |  | 1529 | 0 | 1529 | 0.28958 | 0 | 0 | 1529 | 0.28958 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28958 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 1013541.67 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 1726875.9712 | [11 empty] | Berry Creek | Butte | 39.6425 | -121.4237 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:02
35233306 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Scoped | UNSE |  | 1376 | 0 | 1376 | 0.26061 | 0 | 0 | 1376 | 0.26061 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26061 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 500000 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 1918890.5233 | [11 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-11 12:38
35233307 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Scoped | UNSE |  | 3153 | 0 | 3153 | 0.59716 | 0 | 0 | 3153 | 0.59716 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.59716 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 | 500074.5 | 2090056.82 | 67857 | 0 |  | 737% | 74.5 |  |  |  | 837422.569 | [11 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233308 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Scoped | UNSE |  | 4896 | 0 | 4896 | 0.92727 | 0 | 0 | 4896 | 0.92727 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92727 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 |  | 1761818.18 | 67857 | 0 | [18 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-11 12:38
35233309 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 |  | Scoped | UNSE |  | 1935 | 0 | 1935 | 0.36648 | 0 | 0 | 1935 | 0.36648 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36648 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67857 |  | 1282670.45 | 67857 | 0 | [18 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233310 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Scoped | UNSE |  | 766 | 0 | 766 | 0.14508 | 0 | 0 | 766 | 0.14508 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14508 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 67859 |  | 500000 | 67859 | 0 | [18 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233311 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Scoped | UNSE |  | 6600 | 0 | 6600 | 1.25 | 0 | 0 | 6600 | 1.25 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 118750 |  | 4375000 | 118750 | 0 | [18 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233312 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Scoped | UNSE |  | 5808 | 0 | 5808 | 1.1 | 0 | 0 | 5808 | 1.1 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 118750 |  | 3850000 | 118750 | 0 | [18 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233314 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Scoped | UNSE |  | 8448 | 0 | 8448 | 1.6 | 0 | 0 | 8448 | 1.6 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 118750 |  | 5600000 | 118750 | 0 |  |  | 110.9 | [15 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233315 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Scoped | UNSE |  | 5068 | 0 | 5068 | 0.95985 | 0 | 0 | 5068 | 0.95985 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | 2021-06-10 17:00 | [59 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95985 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-10 17:00 |  | N/A | 2021-07-12 08:00 | 2021-10-11 15:00 |  | 2021-11-10 15:00 | [8 empty] | 118750 |  | 3360000 | 118750 | 0 |  |  | 110.9 | [15 empty] | Berry Creek | Butte | 0 | 0 | [10 empty] | Y |  | 1849 | 35232298 | FRRB |  | 2021-03-09 17:03
35233947 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233948 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP |  | 2021-03-01 13:27
35233949 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233950 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233951 |  |  |  | CWSP - OREGON TRAIL 110335002 PH1.6 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233952 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233953 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233954 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233955 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233956 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233957 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233958 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233959 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.6 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35233995 |  |  |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 |  | In Scoping | UNSE |  | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Placerville | El Dorado | 0 | 0 | [12 empty] | 1363 | 35224377 | PSPS |  | 2021-03-01 13:23
35233996 |  |  |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 |  | In Scoping | UNSE |  | 3748.8 | 0 | 3748.8 | 0.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Placerville | El Dorado | 0 | 0 | [12 empty] | 1363 | 35224377 | PSPS |  | 2021-03-01 13:23
35234284 |  |  |  | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 |  | In Scoping | UNSE |  | 2376 | 0 | 2376 | 0.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 |  |  | ST | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Sutter Creek | Amador | 38.3949 | -120.804 | [12 empty] | 999 | 35223038 | PSPS |  | 2021-03-01 13:14
35234380 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234381 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.7 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234382 |  |  |  | CWSP - OREGON TRAIL 110335002 PH2.8 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234383 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.6 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234384 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.7 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234385 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.8 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234386 |  |  |  | CWSP - OREGON TRAIL 110335002 PH3.9 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234387 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234388 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234389 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234390 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234391 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.6 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234392 |  |  |  | CWSP - OREGON TRAIL 110335002 PH4.7 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234393 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234394 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234395 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234396 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234397 |  |  |  | CWSP - OREGON TRAIL 110335002 PH5.6 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234398 |  |  |  | CWSP - OREGON TRAIL 110335002 PHASE 6.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234399 |  |  |  | CWSP - OREGON TRAIL 110335002 PHASE 6.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234400 |  |  |  | CWSP - OREGON TRAIL 110335002 PHASE 6.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234401 |  |  |  | CWSP - OREGON TRAIL 110335002 PHASE 6.5 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Redding | Shasta | 40.6242 | -122.3039 | [12 empty] | 49 |  | CWSP
35234526 |  |  |  | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 |  | In Scoping | UNSE |  | 0 | 2112 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 |  |  | ST | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Sutter Creek | Amador | 38.3949 | -120.804 | [12 empty] | 999 | 35223038 | PSPS |  | 2021-03-01 13:14
35234527 |  |  |  | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.2 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Downieville | Sierra | 39.5618 | -120.8274 | [12 empty] | 2010 | 35223060 | PSPS |  | 2021-03-01 13:19
35234528 |  |  |  | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.3 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Downieville | Sierra | 39.5618 | -120.8274 | [12 empty] | 2010 | 35223060 | PSPS
35234529 |  |  |  | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.4 |  | In Scoping | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Downieville | Sierra | 39.5618 | -120.8274 | [12 empty] | 2010 | 35223060 | PSPS
35234756 |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | Scoped | UNSE |  | 14689 | 0 | 14689 | 2.782 | 0 | 0 | 0 | 0 | 14689 | 2.782 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-11 14:00
35234758 |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | Scoped | UNSE |  | 3073 | 0 | 3073 | 0.58201 | 0 | 0 | 0 | 0 | 3073 | 0.58201 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-05 11:41
35234862 |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | Scoped | UNSE |  | 422 | 0 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 422 | 0.079924 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-05 11:42
35234865 |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | Scoped | UNSE |  | 3419 | 0 | 3419 | 0.64754 | 0 | 0 | 0 | 0 | 3419 | 0.64754 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [57 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64754 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | Y |  | 474 | 35174501 | ECOP |  | 2021-03-05 11:42
35235139 |  |  |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | In Scoping | UNSE |  | 0 | 604 | 604 | 0.11439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11439 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.11439 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.6645 | -121.4316 | [16 empty] | 2021-03-09 12:13
35235669 |  |  |  | FRRB - WYANDOTTE 1103 - W4 PH4 |  |  | UNSE |  | 0 | 2730 | 2730 | 0.51705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51705 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.646 | -121.4244
35235670 |  |  |  | FRRB - WYANDOTTE 1103 - W5 PH5 |  |  | UNSE |  | 0 | 3555 | 3555 | 0.6733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6733 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6733 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.646 | -121.4244
35235671 |  |  |  | FRRB - WYANDOTTE 1103 - W6 PH6 |  |  | UNSE |  | 0 | 4445 | 4445 | 0.84186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84186 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.84186 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.646 | -121.4244
35235672 |  |  |  | FRRB - WYANDOTTE 1103 - W7 PH7 |  |  | UNSE |  | 0 | 2353 | 2353 | 0.44564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44564 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.44564 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.5852 | -121.4309
35235673 |  |  |  | FRRB - WYANDOTTE 1103 - W8 PH8 |  |  | UNSE |  | 0 | 1445 | 1445 | 0.27367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27367 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27367 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.5852 | -121.4309
35235674 |  |  |  | FRRB - BIG BEND 1102 - B1 PH1 |  |  | UNSE |  | 0 | 1246 | 1246 | 0.23598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23598 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23598 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235675 |  |  |  | FRRB - BIG BEND 1102 - B2 PH2 |  |  | UNSE |  | 0 | 988 | 988 | 0.18712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18712 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18712 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235676 |  |  |  | FRRB - BIG BEND 1102 - B3 PH3 |  |  | UNSE |  | 0 | 3089 | 3089 | 0.58504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58504 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58504 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235677 |  |  |  | FRRB - BIG BEND 1102 - B4 PH4 |  |  | UNSE |  | 0 | 101 | 101 | 0.019129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019129 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.019129 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235678 |  |  |  | FRRB - BIG BEND 1102 - B5 PH5 |  |  | UNSE |  | 0 | 18651 | 18651 | 3.5324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5324 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5324 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235679 |  |  |  | FRRB - BIG BEND 1102 - B6 PH6 |  |  | UNSE |  | 0 | 3557 | 3557 | 0.67367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67367 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.67367 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Berry Creek | Butte | 39.655 | -121.459
35235700 |  |  |  | FRRB - KANAKA 1101 - K1 PH1 |  |  | UNSE |  | 0 | 2317 | 2317 | 0.43883 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43883 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43883 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.5757 | -121.3049
35235701 |  |  |  | FRRB - KANAKA 1101 - K2 PH2 |  |  | UNSE |  | 0 | 1137 | 1137 | 0.21534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21534 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21534 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.5762 | -121.3051
35235702 |  |  |  | FRRB - KANAKA 1101 - K3 PH3 |  |  | UNSE |  | 0 | 3537 | 3537 | 0.66989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66989 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66989 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.5762 | -121.3051
35235703 |  |  |  | FRRB - KANAKA 1101 - K4 PH4 |  |  | UNSE |  | 0 | 123 | 123 | 0.023295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023295 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023295 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.5762 | -121.3051
35235704 |  |  |  | FRRB - KANAKA 1101 - K5 PH5 |  |  | UNSE |  | 0 | 1893 | 1893 | 0.35852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35852 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.35852 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [35 empty] | Oroville | Butte | 39.5762 | -121.3051
35235705 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Scoped | UNSE |  | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  | 4620000 | 118750 | 0 | [18 empty] | Berry Creek | Butte | 39.646 | -121.4244 | [10 empty] | Y | [5 empty] | 2021-03-11 12:38
35235706 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Scoped | UNSE |  | 6125 | 0 | 6125 | 1.16 | 0 | 0 | 6125 | 1.16 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.16 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  | 4060000 | 118750 | 0 | [18 empty] | Berry Creek | Butte | 39.646 | -121.4244 | [10 empty] | Y | [5 empty] | 2021-03-11 12:38
35235707 |  | 2021 |  | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Scoped | UNSE |  | 5016 | 0 | 5016 | 0.95 | 0 | 0 | 5016 | 0.95 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | FRRB | [60 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [12 empty] | 118750 |  | 3325000 | 118750 | 0 | [18 empty] | Berry Creek | Butte | 39.646 | -121.4244 | [10 empty] | Y | [5 empty] | 2021-03-11 12:39
44119915 |  |  |  | STS-OFAC_IDLE_DEEN - 41569 LILLEY MT DR |  |  | CLSD |  | 0 | 400 | 400 | 0.075758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 |  |  | YO | KAA | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.075758 | 0 | 0 | 0.075758 | 0.075758 | 0 | 0 |  |  |  |  | N/A | [37 empty] | 37.1935 | -119.7917
74008802 |  | 2021 |  | INST ROSSMOOR 1109 FDR_MORAGA BK5 EMERG |  |  | CONS | 12142 | 1395 | 11144 | 12539 | 2.3748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3748 |  |  | DI | 06A |  | 2020-07-08 |  |  | 2019-12-23 |  | 2019-12-23 |  |  | Yes | [7 empty] | No | [25 empty] | Yes |  |  |  |  | 2020-09-15 |  | 2020-07-08 |  |  | 99% complete as of 8/25/20 - Waiting on condemnation for weedeating. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3748 | 0 | 0 | 1.1604 | 1.1604 | 0 | 0 |  |  | 2020-06-03 17:00 |  | N/A | 2020-07-07 08:00 | 2021-06-24 17:00 |  | 2021-07-22 17:00 |  | 2020-10-01 07:00 | 2021-07-07 16:00 | [5 empty] | 11000000 | 8756989.8 | 5000000 | 13185339 | 2185339 | 2125811.4 | 79.6% | 6167085.2 | 2707103.4 | 8874188.6 |  | 3687447.6548 |  |  |  | 1395' of New 1109 circuit being undergrounded in tier 2 5692' of new 1109 OH Hardened circuit being installed from location 53 - 92 5452' of existing 1108 OH being hardened in place in tier 2 from location 53 - 92 Total hardened footage = 12539 | [7 empty] | Lafayette | Contra Costa | 37.9561 | -122.0286 | T.0000291.02 |  |  |  | 2021 | Q3 |  | 2020-07-01 | 0 |  | Y
74021903 |  |  |  | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  |  | DOCC | 27264 | 0 | 25191 | 25191 | 4.771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-06-12 |  |  | 2019-06-12 |  | 2019-06-12 |  |  | Yes | 2019-06-18 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | covers both jobs |  | 1980-01-01 | Y | [11 empty] | 25191 | 4.771 | 0 | 0 | 0 | 0 | 4.771 | 0 | 4.771 | 0 | 4.771 | 0 | 6.8901e-16 | 4.771 |  |  | 2019-02-08 |  | N/A | 2019-05-06 | 2019-07-19 | Yes | 2019-07-19 17:00 | 2019-07-27 |  |  | 2019-07-19 |  |  |  |  | 12463097 |  |  | 12463097 | 0 |  |  | 12434525.6 | [5 empty] | 180 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015036.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | BRUNSWICK 11051030 | 351
74021960 |  |  |  | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  |  | DOCC | 31000 | 0 | 31023 | 31023 | 5.8756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-02-08 |  |  | 2019-01-01 | 2020-10-31 | 2019-01-01 |  |  | Yes | 2019-06-24 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | [REDACTED] completing BLM request - Expected to be clear by 4/8/19 | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 31023 | 5.8756 | 0 | 0 | 0 | 0 | 5.8756 | 0 | 5.8756 | 0 | 5.8756 | 0 | 6.8901e-16 | 5.8756 |  |  | 2019-02-08 |  | N/A | 2019-01-25 | 2019-06-21 17:00 | Yes | 2019-06-21 | 2019-07-27 |  |  | 2019-08-02 |  |  |  |  | 15621955 |  |  | 15621955 | 0 | 127015.4 |  | 15475726.8 | 19212.8 | 15494939.6 |  |  |  | 220 | [9 empty] | Nevada City | Nevada | 0 | 0 | E.5015470.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | BRUNSWICK 110532536 | 9
74021961 |  |  |  | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  |  | DOCC | 35410 | 0 | 25170 | 25170 | 4.767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2019-02-08 |  |  | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-08-09 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  | Land issues - [REDACTED] to handle | Full |  |  | Yes |  |  | Received and under review 7/23 |  | 1980-01-01 | Y | [11 empty] | 25170 | 4.767 | 0 | 0 | 0 | 0 | 4.767 | 0 | 4.767 | 0 | 8.0506 | 3.2835 | -6.8901e-16 | 4.767 |  |  | 2019-02-08 |  | NOTN | 2019-04-11 | 2019-10-07 | Yes | 2019-10-07 | 2019-07-31 | [7 empty] | 6996439 | 20423652.2 |  | 6996439 | 0 | -14150734.5 | 291.9% | 20414448.4 | 732725.1 | 21147173.5 |  | 4284341.8203 |  | 390 | [9 empty] | Forestville | Sonoma | 38.5056 | -122.9307 | E.5014743.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | MONTE RIO 1113652 | 115
74021963 |  | 2020 | 220 Mile Plan | CWSP - OAKLAND K 1102 OCB ZONE |  |  | MAPP | 14784 | 0 | 14577.5 | 14577.5 | 2.7609 | 1508 | 0.28561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | EB | 08W | SH | 2019-05-20 |  |  | 2019-05-20 |  | 2019-05-20 |  |  | Yes | 2019-05-20 | [5 empty] | COMPLETED | No | No |  |  |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | Waiting on access routes for EB Park, Looking into partial release. | Full |  |  | Yes |  |  | [REDACTED] to check if permits need to be renewed past 10/16 |  | 1980-01-01 | Y | [11 empty] | 13069.5 | 2.4753 | 1508 | 0.28561 | 0 | 0 | 2.7609 | 0 | 2.7609 | 0 | 2.7609 | 0 | 0 | 2.7609 |  | Keep | 2019-04-22 | Yes | N/A | 2019-08-26 08:00 | 2020-06-02 | Yes | 2020-06-02 | 2019-07-01 | 2020-05-20 | 2020-05-28 | 2020-06-02 |  | Yes | Shovel Ready |  | 8217834 |  |  | 8217834 | 0 | 151958.7 |  | 8058031.6 | 7843.7 | 8065875.3 |  |  |  | 86 | [9 empty] | Oakland | Alameda | 37.8027 | -122.272 | E.5014543.01 |  |  |  | 2020 | Q1 | 2019-05-20 | 2020-01-02 | 2020-06-05 |  | Y | OAKLAND K 1102CB | 265 |  |  |  | 2021-03-01 20:34
74022040 |  |  |  | 2019 CALISTOGA 1101 HIGH SPLICE COUNT |  |  | FICL | 5438.4 | 0 | 6652.8 | 6652.8 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-03-01 |  |  | 2019-03-01 |  | 2019-03-01 |  |  | Yes | 2019-03-30 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  | expires 12/4/19 |  | 1980-01-01 | Y | [11 empty] | 6652.8 | 1.26 | 0 | 0 | 0 | 0 | 1.26 | 0 | 1.26 | 0 | 1.26 | 0 | 0 | 1.26 |  |  |  |  | N/A |  |  |  |  | 2019-03-29 |  |  | 2019-03-29 | [17 empty] | 45 | [9 empty] | Calistoga | Napa | 38.5985 | -122.6193 | E.5013428.01 |  |  |  | 2019 | Q2 | [5 empty] | CALISTOGA 1101734 | 882 |  |  |  | 2021-03-01 20:31
74022382 |  |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 |  |  | CLSD | 12627 | 0 | 12389 | 12389 | 2.3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2019-09-12 |  |  | 2019-09-12 |  | 2019-09-12 |  |  | Yes | 2019-09-12 | Section 11st ADE Submittal - sched for 7/30/197/3 - 7/24: on track 7/307/31: Friday Submittal8/5: QUES submitted for 1st ADE Review8/6 [REDACTED] assigned & Estimate uploaded to SAP8/20: Go ahead for EDRS - [PRELIM DWG ready]9/04 - 9/11: Approved - RCC Issues |  |  |  | Completed | COMPLETED | No |  | 0 | 0 | [12 empty] | Full |  |  | Full |  |  | CIF submitted 8/7/19. KMZ received. Currently reviewing | Full |  |  | Yes |  |  | Private - no permit needed |  | 1980-01-01 | Y | [11 empty] | 12389 | 2.3464 | 0 | 0 | 0 | 0 | 2.3464 | 0 | 2.3464 | 0 | 2.3464 | 0 | -3.4451e-16 | 2.3464 |  |  |  |  | N/A |  |  |  |  | 2019-10-08 |  |  | 2019-12-20 | [17 empty] | 59 | [9 empty] | North San Juan | Nevada | 0 | 0 | E.5015491.01 |  |  |  | 2019 | Q4 |  |  |  |  | Y | COLUMBIA HILL 11012212 | 198
74022383 |  |  |  | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  |  | UNSE | 59136 | 0 | 59136 | 59136 | 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 |  |  | SI | 08W | [17 empty] | No | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.2 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | INPR | [25 empty] | 203 | [7 empty] | Remove |  | Pollock Pines | El Dorado | 0 | 0 | E.5015490.01 |  |  |  | 999 | [6 empty] | EL DORADO PH 210126000 | 67
74022384 |  | 2021 | 220 Mile Plan | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Scoped | CONS | 29328 | 0 | 29328 | 29328 | 5.5545 | 5069 | 0.96004 | 24259 | 4.5945 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2020-12-20 |  | Y | 2019-06-06 |  | 2019-06-06 |  |  | Yes | 2019-06-06 | [6 empty] | No | [5 empty] | Yes |  |  |  | 2020-05-08 | 2020-05-08 |  |  |  |  | Full | 2020-05-08 | 2020-05-08 | Full |  |  | PERTC for veg only. Veg starting in March. 6/30/2020- Veg work is scheduled to start 3/3 though constraints with spotted owls in some limited locations; overall 1600 permit submittal is pending completion of the veg work. ERTC for System Hardening also pending new design for pole location previously sited in jurisdictional area. 6/30/2020 - Need to remove a pole from construction drawing to avoid permitting. Have already received questions from CDFW regarding lack of permits on vegetation scope. | Full |  |  | Yes |  |  | Received and under review 7/23 |  |  | Y | 2020-04-15 |  |  | 90% complete - need to coordinate remaining work with fire rebuild. | [5 empty] | 6696 | 1.2682 | 0 | 0 | 5069 | 0.96004 | 10666 | 2.0201 | 2.9801 | 2.5744 | 2.9843 | 0 | 5.311 | 2.3267 | -0.0041667 | 1.007 |  | Keep | 2020-12-20 | Yes | COMP | 2020-06-08 | 2020-11-18 | Yes | 2021-05-28 17:00 | 2020-05-11 | 2021-03-10 07:00 | 2021-03-10 16:00 |  |  | Yes |  |  | 9219723 | 8344925.6 | 2395900 | 9998553 | 778830 | 54642.2 | 90.51% | 7832768.6 | 1332312.2 | 9165080.8 |  | 1502359.7643 |  | 330 |  | 2/1 - RDO / 2/2 - Prep for wire pull / 2/3 - Wire pull | [7 empty] | Geyserville | Sonoma | 38.5914 | -122.92 | E.5015487.01 |  |  | 2020-069 | 2020 | Q3 | 2019-06-06 | 2020-08-01 | 2020-11-06 |  | Y | FITCH MOUNTAIN 111324918 | 481 |  | PRE |  | 2021-03-08 17:24
74022385 |  |  |  | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  |  | APPR | 12773 | 11422 | 1351 | 12773 | 2.4191 | 0 | 0 | 0 | 0 | 12773 | 2.4191 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-02-02 17:00 |  |  | 2021-01-01 | 2020-10-31 | 2021-01-01 | 2020-12-15 | 2020-12-15 | Yes | 2020-02-25 | Caltrans issue requiring PM involvment to set meeting up to determine exact requirments. |  |  |  |  | 100 | No | [5 empty] | Yes |  |  |  | 2020-12-15 | 2020-12-15 | [5 empty] | 2020-12-15 | 2020-12-15 |  |  |  | ** Caltrans DSDD - Pilot Project - and tribal outreach needed. As of 3/31/20 - still waiting for response from Caltrans (have been following up on environmental side) DSDD still needed? Per [REDACTED] , CT Permit at Sac HQ - [REDACTED] |  |  |  | Yes | 2020-12-31 |  | Annual | [6 empty] | Held up on Caltrans Issue | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4191 | 0 | 0 |  | 0 | 0 | 0 |  | Remove | 2022-02-02 17:00 |  | INPR | 2022-05-31 08:00 | 2022-08-09 08:00 |  | 2022-09-07 17:00 | [5 empty] | No |  |  | 45454 |  |  | 3523187 | 3477733 |  |  | 917437.9 | [5 empty] | 64 |  | CalTrans required completed & ADE approved. There is an issue with FFE that will not let me push the estimate to SAP. A work order ticket has been submitted & we are waiting for follow up. There will be some CalTrans comments that will most likely create additional work, but there is not an anticipated date of when the comments will be back to us. | [7 empty] | Kelseyville | Lake | 38.9024 | -122.7519 | E.5015029.01 |  |  |  | 2022 | Q3 | 2020-01-31 | 2020-06-01 | 2020-08-28 |  | Y | KONOCTI 1102532 | 153
74022387 |  |  |  | CWSP-MIDDLETOWN 1101-TS 1079 |  |  | CLSD | 20445 | 0 | 20962 | 20962 | 3.9701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2019-01-01 |  |  | 2019-01-01 |  | 2019-01-01 |  |  | Yes | 2019-04-05 | [6 empty] | No | [15 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes |  |  |  |  | 1980-01-01 | Y | [11 empty] | 20962 | 3.9701 | 0 | 0 | 0 | 0 | 3.9701 | 0 | 3.9701 | 0 | 3.9701 | 0 | 0 | 3.9701 |  |  |  |  | N/A |  |  |  |  | 2019-04-08 |  |  | 2019-04-30 |  |  |  |  | 5829000 |  |  | 5829000 | 0 |  |  | 5591711.7 | [5 empty] | 135 | [9 empty] | Middletown | Lake | 38.9024 | -122.7519 | E.5014744.01 |  |  |  | 2019 | Q2 |  |  |  |  | Y | MIDDLETOWN 11011079 | 127
74022388 |  | 2020 | 220 Mile Plan | OCGC CWSP: X-1104 OH RECOND SKYLINE |  |  | DOCC | 3677 | 4475 | 0 | 4475 | 0.84754 | 4475 | 0.84754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | EB | 08W | SH | 2019-12-16 |  |  | 2019-10-08 |  | 2019-10-08 |  |  | Yes | 2019-10-08 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/21 | Full |  |  | Yes |  |  | Submitted request on 8/20. No response from [REDACTED] |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 4475 | 0.84754 | 0 | 0 | 0.84754 | 0 | 0.72159 | 0 | 0.72159 | 0 | 0.12595 | 0.72159 |  | Keep | 2019-12-16 | Yes | N/A | 2020-02-14 | 2020-12-01 | Yes | 2020-12-01 | 2020-01-09 | 2020-11-04 | 2020-11-04 | 2020-11-05 |  | Yes | Shovel Ready |  | 5318809.2 |  |  | 5476214 | 157404.8 |  |  | 4474559.3 | [5 empty] | 23 |  | MSO Hold | [7 empty] | Oakland | Alameda | 37.8317 | -122.1857 | E.5014312.01 |  | UG |  | 2020 | Q1 | 2019-09-27 | 2020-04-01 | 2020-09-30 |  | Y | OAKLAND X 1104CR022 | 435
74022389 |  |  |  | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 |  |  | CLSD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | [61 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [7 empty] | 2021-01-07 |  |  |  |  | 500000 |  |  | 500000 | 0 |  |  | 0.1 | [13 empty] | Remove |  | Paradise | Butte | 39.761 | -121.6181 | [10 empty] | Y | PARADISE 11062234 | 28
74022390 |  | 2020 | 220 Mile Plan | CWSP - SILVERADO 2104- LR722-PH 1A |  |  | MAPP | 4150 | 0 | 5108 | 5108 | 0.96742 | 5108 | 0.96742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-22 |  |  | 2019-08-08 |  | 2019-08-08 |  |  | Yes | 2020-01-13 | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Drawing received 7/29/19 Spotted Owl LOP | Full |  |  | Yes | 2020-12-31 |  | Verbal Approval on 8/26, should issue by end of week |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 5108 | 0.96742 | 0 | 0 | 0.96742 | 0 | 0.96742 | 0 | 0.96742 | 0 | 0 | 0.96742 |  | Keep | 2019-08-22 | Yes | N/A | 2019-12-02 | 2020-05-21 | Yes | 2020-05-21 | 2019-09-19 | 2019-12-02 | 2020-04-02 | 2020-05-19 |  | Yes | Shovel Ready |  | 2849999.6 |  |  | 2850000 | 0.4 | 151008.4 |  | 2691262.8 | 7728.4 | 2698991.2 |  |  |  | 21 | [9 empty] | Saint Helena | Napa | 38.4989 | -122.4616 | E.5014772.01 |  |  |  | 2020 | Q1 | 2019-08-09 | 2020-01-02 | 2020-01-30 |  | Y | SILVERADO 2104722 | 160
74024171 |  |  |  | CALISTOGA 1101 HIGH SPLICE COUNT |  |  | DOCC | 14098 | 0 | 13780 | 13780 | 2.6098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2019-08-12 |  |  | 2019-06-10 |  | 2019-06-10 |  |  | Yes | 2019-08-17 | [5 empty] | 100 | No | [15 empty] | Full |  |  | Full |  |  | Caltrans permit, possible partial release. TCP needed for land release - Partial Released 8/16/19 | Full |  |  | Yes |  |  | Received all remaining permits on 1/3/2019. Uploaded to SAP Docs |  | 1980-01-01 | Y | [11 empty] | 13780 | 2.6098 | 0 | 0 | 0 | 0 | 2.6098 | 0 | 2.6098 | 0 | 2.6098 | 0 | 0 | 2.6098 |  |  | 2019-08-12 |  | N/A | 2019-09-03 | 2020-05-13 | Yes | 2020-05-13 | 2019-08-23 |  |  | 2020-05-13 | [7 empty] | 1714904 |  |  |  | 3307150.8 | [5 empty] | 72 | [9 empty] | Calistoga | Napa | 38.5767 | -122.6204 | E.5019956.01 |  |  |  | 2019 | Q3 |  |  |  |  | Y | CALISTOGA 1101736 | 24 |  |  |  | 2021-03-01 20:31
74028021 |  | 2020 | 220 Mile Plan | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  |  | CONS |  | 0 | 9716 | 9716 | 1.8402 | 9716 | 1.8402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2020-03-13 |  |  | 2020-01-30 |  | 2020-01-30 | 2020-03-05 | 2020-03-05 | Yes | 2020-04-29 | 01/15: Added to CO Est tracking; Dates unconfirmed; set 1st submittal T+30 from [REDACTED] notification he would prioritize.1/8 Email driven completion request - priority; [REDACTED] to prioritize |  |  |  | 2020 - Q1- M2 [R0] | COMPLETED | No | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2020-03-13 | 2020-03-13 |  |  |  |  | Partial | 2020-03-13 | 2020-03-13 | Partial |  |  |  | Partial |  |  | Yes |  |  | Will need to review. |  | 1980-01-01 | Y | [11 empty] | 0 | 0 | 9716 | 1.8402 | 0 | 0 | 1.8402 | 0 | 1.8402 | 0 | 1.8402 | 0 | 0 | 1.8402 |  | Keep | 2020-02-17 | Yes | N/A | 2020-05-05 | 2020-09-16 | Yes | 2021-04-22 17:00 | 2020-05-06 | 2020-04-30 | 2020-07-31 |  |  | Yes | Shovel Ready |  | 4356060 | 4508525.7 | 173177.8 | 4467090 | 111030 | -1203344.9 | 103.5% | 4437013.5 | 1122391.4 | 5559404.9 |  | 2450083.9539 | [11 empty] | Forestville | Sonoma | 38.5056 | -122.9307 | E.5014743.02 |  |  |  | 2020 | Q2 | 2020-01-30 | 2020-03-15 | 2020-04-28 |  | Y | MONTE RIO 1113652 | 115
99999998 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [65 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | N/A | [43 empty] | 2019
99999999 | [8 empty] | 0 | 270 | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [65 empty] | 270 | 0.051136 | 0 | 0 | 0 | 0 | 0.051136 | 0 | 0 | 0 |  | 0 | 0.051136 | 0 |  | 2019 Idle Facilities true up |  |  | N/A | [43 empty] | 2019
Note on J1: Redacted says: This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on K1: Redacted says: This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.

## conductor_pz_summary_hftd_23_re
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | device_operating_number | hftd_23_primary_length_under_1km | primary_length_m | primary_length_m_hftd_23 | Miles | pixel_count | mean_ignition_probability | ignition_rank | mean_mavf_core | mavf_consequence_rank | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | kpmg_Consolidated Risk Score | KPMG_rank
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | CUS391 | TRUE | 36.3577 | 36.3577 | 0.022596 | 1 | 0.00039685 | 69 | 7972.4858 | 5 | 3.1639 | 3.1639 | 1 |  | 3570
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 276-G | TRUE | 23.7478 | 23.7478 | 0.014759 | 1 | 0.00025382 | 208 | 7401.5283 | 7 | 1.8786 | 1.8786 | 2 | 0.16 | 1261
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 90130 | TRUE | 151.1499 | 151.1499 | 0.09394 | 1 | 0.00016255 | 619 | 10411.5469 | 1 | 1.6924 | 1.6924 | 3 | 2.44 | 603
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 688294 | TRUE | 24.3604 | 24.3604 | 0.01514 | 1 | 0.0001714 | 553 | 8415.9766 | 3 | 1.4425 | 1.4425 | 4 |  | 3420
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | CB | TRUE | 289.8399 | 85.2366 | 0.052975 | 4 | 0.00035401 | 88 | 3206.0204 | 240 | 1.3006 | 5.2026 | 5 | 0.29 | 1032
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | CB | FALSE | 1791.2622 | 1791.2622 | 1.1133 | 3 | 0.0002511 | 214 | 4819.6954 | 90 | 1.2559 | 3.7676 | 6 | 0.09 | 1534
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 1586 | FALSE | 11983.5348 | 11983.5348 | 7.4478 | 39 | 0.00044628 | 48 | 3225.6011 | 233 | 1.2524 | 48.8434 | 7 | 0.24 | 1102
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 302610 | FALSE | 9188.9357 | 7571.5921 | 4.7058 | 53 | 0.00021011 | 357 | 4327.9371 | 121 | 0.91632 | 48.565 | 8 |  | 3061
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 965078 | FALSE | 11264.1399 | 10089.0761 | 6.2704 | 59 | 0.00026416 | 185 | 3338.3605 | 220 | 0.87629 | 51.7008 | 9 |  | 2774
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 241564 | FALSE | 1774.1526 | 1146.9072 | 0.71281 | 14 | 0.0001265 | 1073 | 6191.5313 | 26 | 0.77248 | 10.8148 | 10 |  | 2961
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | CB | FALSE | 7724.4676 | 7724.4676 | 4.8008 | 13 | 0.00026518 | 181 | 3512.0536 | 200 | 0.73491 | 9.5539 | 11 | 0.13 | 1365
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 378446 | TRUE | 173.2196 | 157.9488 | 0.098166 | 3 | 0.00015629 | 683 | 4122.2296 | 142 | 0.73151 | 2.1945 | 12 |  | 3619
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | CB | TRUE | 1420.4117 | 752.0336 | 0.46739 | 12 | 0.00032056 | 109 | 1676.5244 | 530 | 0.72481 | 8.6977 | 13 | 0.71 | 802
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 830 | FALSE | 62803.2175 | 44622.1036 | 27.7328 | 212 | 0.00015679 | 675 | 4619.5228 | 102 | 0.71618 | 151.8291 | 14 | 0.14 | 1322
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | CB | FALSE | 12231.0905 | 8613.688 | 5.3534 | 38 | 0.00011189 | 1370 | 5318.8037 | 51 | 0.70423 | 26.7607 | 15 | 0.04 | 2163
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 4440 | TRUE | 376.2849 | 376.2849 | 0.23386 | 4 | 0.00015164 | 724 | 3234.1311 | 230 | 0.68656 | 2.7463 | 16 | 1.05 | 722
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | CB | TRUE | 135.534 | 135.534 | 0.084235 | 1 | 9.9283e-05 | 1662 | 6756.3685 | 11 | 0.67079 | 0.67079 | 17 | 2.37 | 609
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 14072 | FALSE | 6206.8729 | 5897.3117 | 3.6652 | 30 | 0.0001306 | 999 | 5236.689 | 59 | 0.65331 | 19.5994 | 18 | 0.05 | 2003
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 980662 | TRUE | 366.2635 | 366.2635 | 0.22763 | 3 | 0.00014325 | 821 | 4824.4797 | 89 | 0.64187 | 1.9256 | 19 |  | 3599
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 126774 | FALSE | 1267.3386 | 1267.3386 | 0.78766 | 11 | 9.3598e-05 | 1808 | 6310.2508 | 24 | 0.62029 | 6.8232 | 20 |  | 3568
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 442850 | FALSE | 9258.545 | 9258.545 | 5.7542 | 30 | 9.1768e-05 | 1852 | 6349.6612 | 21 | 0.61454 | 18.4361 | 21 | 0.08 | 1644
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | CB | FALSE | 3906.143 | 3906.143 | 2.4277 | 27 | 0.00013159 | 989 | 4767.3932 | 95 | 0.59573 | 16.0848 | 22 | 2.54 | 600
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 118494 | FALSE | 1737.509 | 1714.9565 | 1.0659 | 12 | 0.00012542 | 1091 | 4982.7835 | 79 | 0.58092 | 6.971 | 23 |  | 3276
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 784704 | TRUE | 43.8835 | 43.8835 | 0.027274 | 1 | 0.00019096 | 437 | 2953.5029 | 279 | 0.564 | 0.564 | 24 | 1.81 | 641
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 113684 | TRUE | 748.9574 | 590.6521 | 0.36709 | 4 | 9.2988e-05 | 1823 | 6848.1417 | 10 | 0.55276 | 2.211 | 25 |  | 3509
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 250154 | TRUE | 458.5489 | 458.5489 | 0.28499 | 4 | 0.00011419 | 1315 | 5210.7292 | 61 | 0.55243 | 2.2097 | 26 |  | 3150
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 628 | FALSE | 22883.905 | 22883.905 | 14.2224 | 51 | 0.00010064 | 1633 | 5903.6105 | 33 | 0.5487 | 27.9838 | 27 | 5.08 | 496
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 3202 | TRUE | 630.3021 | 630.3021 | 0.39174 | 9 | 8.3995e-05 | 2093 | 6312.7784 | 23 | 0.53731 | 4.8358 | 28 | 9.63 | 406
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 32586 | FALSE | 2375.6773 | 2158.8587 | 1.3417 | 15 | 0.00014236 | 834 | 3072.9006 | 260 | 0.52987 | 7.9481 | 29 | 1.13 | 712
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | CB | FALSE | 3746.9222 | 3746.9222 | 2.3287 | 10 | 5.421e-05 | 2939 | 9615.8541 | 2 | 0.51619 | 5.1619 | 30 | 0.05 | 1951
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 200-G | TRUE | 13.7161 | 13.7161 | 0.0085246 | 1 | 0.00015982 | 645 | 3189.8253 | 242 | 0.50979 | 0.50979 | 31 | 18.16 | 324
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 394G | TRUE | 18.1683 | 18.1683 | 0.011292 | 1 | 0.00015982 | 646 | 3189.8253 | 243 | 0.50979 | 0.50979 | 32 | 18.15 | 325
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 546650 | FALSE | 1443.177 | 1443.177 | 0.89694 | 6 | 0.00052979 | 27 | 978.3256 | 845 | 0.50291 | 3.0174 | 33 |  | 2920
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 47214 | TRUE | 43.972 | 43.972 | 0.027329 | 1 | 5.8357e-05 | 2823 | 8298.4728 | 4 | 0.48427 | 0.48427 | 34 | 2.46 | 602
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | CB | FALSE | 8571.1084 | 8453.5074 | 5.2539 | 31 | 0.00011156 | 1382 | 3466.6155 | 205 | 0.47165 | 14.6212 | 35 | 0.06 | 1807
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 97142 | FALSE | 7406.0615 | 7406.0615 | 4.6029 | 40 | 0.00010428 | 1545 | 5130.9585 | 66 | 0.47122 | 18.8487 | 36 | 0.05 | 1966
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 40092 | FALSE | 68288.9427 | 37272.9556 | 23.1653 | 464 | 0.00010079 | 1627 | 4668.9585 | 100 | 0.46772 | 217.022 | 37 | 5.23 | 493
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 481876 | FALSE | 2559.0375 | 1373.1162 | 0.8534 | 14 | 8.3175e-05 | 2127 | 5568.7809 | 46 | 0.46769 | 6.5476 | 38 |  | 2766
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 49742 | FALSE | 5593.8568 | 5593.8568 | 3.4766 | 28 | 5.8016e-05 | 2835 | 7932.3948 | 6 | 0.46433 | 13.0013 | 39 | 0.05 | 1993
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 48180 | TRUE | 21.1502 | 21.1502 | 0.013145 | 2 | 8.1559e-05 | 2167 | 5130.0926 | 67 | 0.46103 | 0.92206 | 40 | 0.05 | 1938
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 46012 | FALSE | 4834.6736 | 1025.1447 | 0.63713 | 38 | 9.4944e-05 | 1768 | 4755.8708 | 96 | 0.45557 | 17.3115 | 41 |  | 3124
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 6542 | FALSE | 23588.1989 | 23588.1989 | 14.6602 | 140 | 0.00010109 | 1623 | 4849.1896 | 86 | 0.44642 | 62.4985 | 42 | 0.1 | 1469
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 64118 | FALSE | 15416.9418 | 2646.9433 | 1.6451 | 101 | 0.00019755 | 406 | 2096.5335 | 427 | 0.44262 | 44.7046 | 43 | 0.02 | 2515
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | CB | TRUE | 20.574 | 20.574 | 0.012787 | 1 | 0.00031529 | 111 | 1402.4592 | 637 | 0.44218 | 0.44218 | 44 | 0.04 | 2165
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 6953 | FALSE | 9187.973 | 9187.973 | 5.7104 | 58 | 0.00011159 | 1378 | 4228.1533 | 135 | 0.4353 | 25.2473 | 45 | 4.2 | 525
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 96324 | TRUE | 775.7684 | 775.7684 | 0.48214 | 6 | 0.00013262 | 970 | 3560.1407 | 193 | 0.4317 | 2.5902 | 46 | 0.03 | 2285
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | CB | FALSE | 2942.9352 | 2836.5864 | 1.7629 | 23 | 0.00018049 | 510 | 2272.276 | 388 | 0.42859 | 9.8576 | 47 | 0.07 | 1708
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 9718 | FALSE | 56853.1165 | 29935.2858 | 18.6049 | 357 | 8.8629e-05 | 1967 | 4802.059 | 94 | 0.42526 | 151.8163 | 48 | 0.07 | 1758
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 35002 | FALSE | 91942.988 | 91942.988 | 57.1429 | 641 | 0.00011631 | 1264 | 3934.2214 | 153 | 0.42185 | 270.4028 | 49 | 0.4 | 943
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 440236 | FALSE | 6874.8043 | 6874.8043 | 4.2727 | 38 | 0.00016814 | 575 | 3899.3651 | 157 | 0.4205 | 15.979 | 50 |  | 3110
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 881362 | TRUE | 1747.5089 | 480.0321 | 0.29834 | 10 | 0.00010401 | 1552 | 3804.2183 | 168 | 0.41959 | 4.1959 | 51 |  | 3475
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 1454 | FALSE | 12602.1173 | 12602.1173 | 7.8323 | 31 | 9.3126e-05 | 1817 | 5114.2446 | 68 | 0.41883 | 12.9837 | 52 | 0.03 | 2353
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 965390 | FALSE | 2587.1085 | 1209.1092 | 0.75147 | 21 | 9.949e-05 | 1657 | 4819.484 | 91 | 0.41415 | 8.6971 | 53 |  | 3088
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 754718 | FALSE | 4640.5633 | 4640.5633 | 2.8841 | 29 | 0.00013445 | 936 | 2737.1841 | 306 | 0.40712 | 11.8066 | 54 |  | 3456
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | CB | TRUE | 1122.2361 | 221.6704 | 0.13777 | 9 | 0.00036283 | 82 | 802.2368 | 941 | 0.40561 | 3.6505 | 55 | 0.11 | 1412
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | CB | FALSE | 11032.7196 | 11032.7196 | 6.8569 | 54 | 0.00014918 | 748 | 2134.6994 | 416 | 0.40353 | 21.7909 | 56 | 0.11 | 1422
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | CB | FALSE | 4029.4321 | 4029.4321 | 2.5043 | 34 | 0.00017446 | 532 | 2332.9065 | 378 | 0.39837 | 13.5444 | 57 | 0.04 | 2081
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 698 | FALSE | 16605.929 | 11071.0466 | 6.8807 | 97 | 9.4179e-05 | 1790 | 4392.8078 | 115 | 0.39723 | 38.5312 | 58 | 0.06 | 1832
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 979830 | TRUE | 696.7531 | 680.7511 | 0.42309 | 7 | 7.12e-05 | 2441 | 5107.124 | 69 | 0.3972 | 2.7804 | 59 |  | 3328
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 95878 | FALSE | 30094.5573 | 9856.7705 | 6.126 | 191 | 0.00017374 | 535 | 2217.9989 | 398 | 0.3965 | 75.7306 | 60 | 0.02 | 2524
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 5310 | FALSE | 45195.5088 | 45195.5088 | 28.0892 | 299 | 6.7329e-05 | 2551 | 6694.8526 | 15 | 0.39401 | 117.8076 | 61 | 19.51 | 312
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 361952 | FALSE | 2196.587 | 2196.587 | 1.3652 | 9 | 0.00011545 | 1290 | 3151.4111 | 248 | 0.39288 | 3.536 | 62 | 1.9 | 631
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | CB | FALSE | 29229.2172 | 29229.2172 | 18.1661 | 204 | 8.2084e-05 | 2150 | 5306.8686 | 52 | 0.39206 | 79.9801 | 63 | 0.11 | 1431
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 8762 | FALSE | 26274.6884 | 22259.6162 | 13.8344 | 147 | 7.8661e-05 | 2244 | 4502.8739 | 108 | 0.39138 | 57.5327 | 64 | 0.12 | 1395
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 1634 | FALSE | 29441.3626 | 29110.7694 | 18.0925 | 192 | 8.4909e-05 | 2064 | 4929.5026 | 80 | 0.39094 | 75.0607 | 65 | 0.18 | 1222
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 10335 | FALSE | 9369.0411 | 9369.0411 | 5.8229 | 69 | 9.5888e-05 | 1732 | 4247.144 | 133 | 0.39082 | 26.9663 | 66 | 1.53 | 668
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 865502 | TRUE | 4467.1172 | 644.9532 | 0.40084 | 27 | 0.00011299 | 1344 | 3613.4467 | 189 | 0.38957 | 10.5185 | 67 |  | 3119
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | CB | FALSE | 40215.5467 | 40215.5467 | 24.9941 | 262 | 0.00012902 | 1029 | 2606.3425 | 328 | 0.38665 | 101.3032 | 68 | 9.11 | 412
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | N54 | FALSE | 34748.7236 | 32201.1783 | 20.0132 | 221 | 9.3045e-05 | 1819 | 4184.3432 | 138 | 0.38568 | 85.2354 | 69 | 3.07 | 564
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 37222 | FALSE | 40893.1758 | 40893.1758 | 25.4153 | 152 | 0.00011309 | 1341 | 3498.721 | 202 | 0.3839 | 58.3523 | 70 | 0.05 | 2044
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 1532 | FALSE | 7926.8978 | 6133.1893 | 3.8118 | 27 | 6.5114e-05 | 2606 | 6536.3281 | 17 | 0.38077 | 10.2807 | 71 | 0.01 | 2591
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 75802 | TRUE | 680.0226 | 576.1553 | 0.35808 | 6 | 0.0002061 | 377 | 1316.5155 | 676 | 0.37901 | 2.2741 | 72 | 3.09 | 563
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 2408 | FALSE | 22439.0865 | 18541.2413 | 11.5235 | 76 | 0.00027566 | 167 | 1710.6647 | 521 | 0.37815 | 28.7393 | 73 | 0.15 | 1306
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 623120 | FALSE | 12233.579 | 10535.1094 | 6.5476 | 67 | 0.00013171 | 986 | 3211.1058 | 239 | 0.3774 | 25.2855 | 74 |  | 2966
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 1904 | FALSE | 64429.3728 | 51242.8521 | 31.8476 | 332 | 0.00018482 | 475 | 1914.8501 | 471 | 0.37685 | 125.1141 | 75 | 0.11 | 1439
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | CB | FALSE | 14817.1823 | 14817.1823 | 9.2089 | 80 | 0.00011233 | 1359 | 3549.008 | 194 | 0.37545 | 30.036 | 76 | 0.07 | 1694
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 984788 | TRUE | 5.0644 | 5.0644 | 0.0031475 | 1 | 7.6238e-05 | 2303 | 4898.9282 | 84 | 0.37348 | 0.37348 | 77 |  | 3623
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 570682 | FALSE | 3264.3372 | 3264.3372 | 2.0288 | 26 | 9.6836e-05 | 1718 | 4471.4183 | 111 | 0.37306 | 9.6995 | 78 | 5.65 | 481
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 11101 | FALSE | 5931.2678 | 5931.2678 | 3.6863 | 37 | 6.6475e-05 | 2575 | 6042.3197 | 28 | 0.36793 | 13.6135 | 79 | 5.36 | 488
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 9473 | FALSE | 4735.3386 | 3890.479 | 2.4179 | 27 | 9.0946e-05 | 1883 | 3855.297 | 162 | 0.36547 | 9.8678 | 80 | 1.5 | 669
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 445650 | FALSE | 1066.4109 | 1066.4109 | 0.66278 | 5 | 6.0341e-05 | 2764 | 6011.651 | 29 | 0.36477 | 1.8239 | 81 |  | 3333
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 414 | FALSE | 18899.455 | 9544.4247 | 5.9319 | 114 | 0.00014586 | 791 | 3081.157 | 259 | 0.36434 | 41.5353 | 82 | 1.22 | 699
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 884904 | FALSE | 18739.6016 | 18723.6816 | 11.6368 | 77 | 0.0001019 | 1605 | 3934.604 | 152 | 0.36326 | 27.9711 | 83 |  | 2842
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 592742 | TRUE | 684.4552 | 546.7453 | 0.3398 | 5 | 6.9919e-05 | 2474 | 5228.5371 | 60 | 0.36227 | 1.8113 | 84 |  | 3618
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 1568 | FALSE | 37176.4968 | 37176.4968 | 23.1053 | 136 | 9.0935e-05 | 1885 | 3456.9848 | 206 | 0.36191 | 49.2203 | 85 | 0.1 | 1479
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | CB | FALSE | 22365.4615 | 7612.1604 | 4.731 | 146 | 0.00014565 | 795 | 2568.6158 | 335 | 0.36174 | 52.8144 | 86 | 14.97 | 351
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | N02 | TRUE | 70.934 | 70.934 | 0.044086 | 1 | 0.00025248 | 210 | 1429.5746 | 625 | 0.36094 | 0.36094 | 87 | 2.56 | 597
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 5020 | FALSE | 26887.6514 | 26064.8634 | 16.1994 | 159 | 8.5726e-05 | 2036 | 4882.5801 | 85 | 0.36009 | 57.2543 | 88 | 0.1 | 1468
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 3105 | FALSE | 9965.2703 | 9659.0441 | 6.0031 | 65 | 6.4265e-05 | 2635 | 5852.1243 | 38 | 0.35978 | 23.3856 | 89 | 2.42 | 605
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 389190 | FALSE | 4452.7835 | 3542.8058 | 2.2019 | 18 | 0.00010318 | 1566 | 3658.7668 | 184 | 0.35946 | 6.4703 | 90 |  | 3524
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 799940 | TRUE | 1340.3375 | 954.7701 | 0.59339 | 9 | 9.2053e-05 | 1842 | 3744.3748 | 176 | 0.35844 | 3.2259 | 91 |  | 3537
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 67858 | FALSE | 18377.3415 | 18377.3415 | 11.4216 | 107 | 6.8002e-05 | 2535 | 5416.4769 | 50 | 0.35702 | 38.201 | 92 | 2.79 | 581
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 945670 | TRUE | 403.0974 | 334.4297 | 0.20785 | 3 | 6.3935e-05 | 2648 | 5860.0064 | 36 | 0.35536 | 1.0661 | 93 |  | 3578
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | Y54 | FALSE | 55238.5351 | 54847.9366 | 34.0882 | 296 | 8.0013e-05 | 2204 | 4332.6246 | 120 | 0.35181 | 104.1359 | 94 | 0.39 | 950
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | CB | TRUE | 169.7516 | 136.2242 | 0.084664 | 2 | 0.00017127 | 555 | 1962.7321 | 461 | 0.35138 | 0.70277 | 95 | 2.89 | 573
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 867486 | FALSE | 5219.4397 | 3405.4305 | 2.1165 | 20 | 7.3948e-05 | 2361 | 3380.0089 | 213 | 0.35061 | 7.0121 | 96 |  | 3172
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 400 | FALSE | 5057.3021 | 5057.3021 | 3.1431 | 8 | 9.5474e-05 | 1743 | 3849.0683 | 163 | 0.34896 | 2.7917 | 97 | 0.31 | 1006
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | CB | FALSE | 27398.7529 | 27398.7529 | 17.0284 | 154 | 6.9314e-05 | 2496 | 5271.5559 | 56 | 0.348 | 53.5915 | 98 | 0.07 | 1725
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 49024 | FALSE | 26972.4504 | 26707.9675 | 16.5991 | 209 | 8.4768e-05 | 2071 | 4699.5815 | 98 | 0.34786 | 72.7038 | 99 | 9.03 | 415
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 1370 | FALSE | 35764.2 | 21861.3958 | 13.5869 | 272 | 0.00010359 | 1559 | 3756.8301 | 175 | 0.34561 | 94.0068 | 100 | 0.05 | 1954
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 35974 | TRUE | 1338.7863 | 398.8739 | 0.2479 | 11 | 7.6845e-05 | 2289 | 4333.8495 | 119 | 0.34404 | 3.7844 | 101 | 0.03 | 2393
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 874798 | TRUE | 662.24 | 662.24 | 0.41158 | 3 | 6.6045e-05 | 2587 | 6079.8606 | 27 | 0.33623 | 1.0087 | 102 |  | 3523
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 964 | FALSE | 8651.6925 | 4999.6692 | 3.1073 | 41 | 0.00013223 | 977 | 2706.926 | 309 | 0.33456 | 13.717 | 103 | 0.45 | 917
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5703 | FALSE | 12751.5705 | 8525.0586 | 5.2984 | 96 | 0.00012007 | 1186 | 2775.9092 | 303 | 0.33328 | 31.9947 | 104 | 0.07 | 1684
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 1632 | FALSE | 13751.6318 | 13751.6318 | 8.5467 | 19 | 8.8891e-05 | 1954 | 4338.5101 | 118 | 0.33244 | 6.3164 | 105 | 0.05 | 1948
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | CB | FALSE | 6348.7863 | 4804 | 2.9857 | 44 | 0.00014557 | 797 | 1870.2515 | 482 | 0.32751 | 14.4105 | 106 | 0.03 | 2238
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 895760 | FALSE | 19502.5171 | 14756.3663 | 9.1711 | 96 | 9.5565e-05 | 1740 | 3633.0115 | 188 | 0.32643 | 31.3373 | 107 |  | 3035
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | Y04 | FALSE | 35997.3396 | 25194.6309 | 15.6586 | 238 | 6.6358e-05 | 2580 | 5141.1422 | 64 | 0.32463 | 77.261 | 108 | 2.84 | 576
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | CB | TRUE | 1275.2265 | 525.8096 | 0.32679 | 9 | 0.00013923 | 884 | 1814.5621 | 503 | 0.32442 | 2.9197 | 109 | 0.04 | 2217
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 768 | FALSE | 31882.0115 | 27234.0747 | 16.9261 | 115 | 9.5052e-05 | 1764 | 3417.6208 | 210 | 0.32431 | 37.2953 | 110 | 0.05 | 2000
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 478952 | FALSE | 5727.3171 | 1143.6662 | 0.71079 | 39 | 0.00011288 | 1347 | 2674.3103 | 318 | 0.32368 | 12.6234 | 111 |  | 3082
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 1202 | FALSE | 12713.8882 | 12713.8882 | 7.9017 | 41 | 0.00015857 | 657 | 2432.9018 | 355 | 0.32328 | 13.2544 | 112 | 2.4 | 607
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 1566 | FALSE | 24740.5736 | 19451.0946 | 12.0889 | 94 | 8.022e-05 | 2199 | 4262.1109 | 129 | 0.3225 | 30.3149 | 113 | 0.05 | 2042
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 426745 | TRUE | 328.8561 | 328.8561 | 0.20439 | 3 | 0.00020048 | 394 | 1570.5843 | 571 | 0.32224 | 0.96673 | 114 |  | 3365
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 153260 | TRUE | 424.4592 | 424.4592 | 0.2638 | 2 | 9.6022e-05 | 1729 | 3917.3903 | 154 | 0.32186 | 0.64373 | 115 |  | 3584
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 9726 | FALSE | 27359.7494 | 25257.4681 | 15.6976 | 197 | 8.9511e-05 | 1931 | 4058.7556 | 145 | 0.32131 | 63.2977 | 116 | 3.58 | 541
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 323094 | FALSE | 58176.4815 | 58176.4815 | 36.1569 | 208 | 0.00010508 | 1524 | 3224.7709 | 234 | 0.32037 | 66.6373 | 117 | 0.08 | 1636
4869 | BELL 11082202 | 152701108 | BELL 1108 | 2202 | FALSE | 53635.0932 | 52339.4363 | 32.5292 | 363 | 0.0001269 | 1065 | 2599.5441 | 330 | 0.32016 | 116.2183 | 118 | 0.16 | 1264
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 296804 | FALSE | 5287.5044 | 5287.5044 | 3.2862 | 12 | 0.00014395 | 815 | 2252.1128 | 392 | 0.31954 | 3.8345 | 119 |  | 3361
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | CB | FALSE | 1481.3738 | 1293.943 | 0.80419 | 9 | 0.00018563 | 469 | 1193.2799 | 733 | 0.31824 | 2.8642 | 120 | 0.39 | 953
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | A20 | FALSE | 12666.4228 | 11999.0835 | 7.4575 | 92 | 8.3458e-05 | 2117 | 4208.4041 | 137 | 0.3179 | 29.2466 | 121 | 0.09 | 1561
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 38316 | FALSE | 36512.8123 | 25616.7426 | 15.9209 | 232 | 7.2587e-05 | 2403 | 4684.5531 | 99 | 0.31672 | 73.4796 | 122 | 3 | 569
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 544790 | FALSE | 27462.4335 | 26342.4042 | 16.3719 | 185 | 8.3921e-05 | 2097 | 3941.9662 | 151 | 0.31273 | 57.8548 | 123 |  | 2696
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 5525 | FALSE | 21152.7165 | 21152.7165 | 13.1465 | 175 | 5.9719e-05 | 2783 | 5306.8404 | 53 | 0.31171 | 54.5497 | 124 | 0.17 | 1227
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 878 | FALSE | 9206.6572 | 5430.6654 | 3.3752 | 49 | 0.00017681 | 519 | 2682.7456 | 315 | 0.31109 | 15.2435 | 125 | 0.63 | 834
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | CB | FALSE | 36834.5436 | 36834.5436 | 22.8928 | 193 | 0.00011343 | 1334 | 2972.4937 | 272 | 0.31093 | 60.0095 | 126 | 10.25 | 399
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 828 | FALSE | 17153.3338 | 13828.9706 | 8.5948 | 112 | 8.3934e-05 | 2094 | 3831.1552 | 164 | 0.31086 | 34.8164 | 127 | 5.94 | 476
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | R308 | FALSE | 6217.3701 | 6217.3701 | 3.8641 | 22 | 6.1262e-05 | 2743 | 4314.2777 | 123 | 0.30901 | 6.7983 | 128 | 0.04 | 2136
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | CB | FALSE | 2646.4634 | 2646.4634 | 1.6448 | 13 | 0.00028983 | 139 | 1109.8091 | 772 | 0.30873 | 4.0135 | 129 | 5.34 | 489
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 976428 | FALSE | 16955.2499 | 14081.5812 | 8.7518 | 82 | 0.00013702 | 908 | 2148.1965 | 412 | 0.30752 | 25.2165 | 130 |  | 3305
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 96792 | FALSE | 8212.3137 | 6394.0351 | 3.9739 | 30 | 7.1793e-05 | 2425 | 5020.5256 | 72 | 0.30689 | 9.2067 | 131 |  | 3057
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 6210 | FALSE | 17177.2503 | 17177.2503 | 10.6757 | 49 | 4.8609e-05 | 3072 | 5877.8631 | 34 | 0.30465 | 14.9278 | 132 | 0.06 | 1874
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | A12 | FALSE | 64854.5144 | 64854.5144 | 40.3073 | 180 | 9.1245e-05 | 1867 | 3289.4433 | 226 | 0.30414 | 54.7453 | 133 | 0.11 | 1446
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | CB | FALSE | 16489.2317 | 14163.76 | 8.8028 | 107 | 0.00015725 | 671 | 2292.759 | 385 | 0.30391 | 32.5187 | 134 | 6.82 | 459
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | CB | FALSE | 24190.4571 | 22339.3117 | 13.884 | 147 | 0.00012222 | 1145 | 2373.5412 | 366 | 0.30349 | 44.6134 | 135 | 0.16 | 1273
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | CB | FALSE | 16978.5039 | 16978.5039 | 10.5522 | 33 | 8.5557e-05 | 2039 | 4275.4303 | 128 | 0.30244 | 9.9805 | 136 | 0.03 | 2265
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | CB | TRUE | 12832.3568 | 56.5182 | 0.035126 | 105 | 9.1038e-05 | 1880 | 3530.2398 | 198 | 0.30185 | 31.6947 | 137 | 0.03 | 2249
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | N50 | FALSE | 3586.1974 | 3586.1974 | 2.2288 | 24 | 0.00020174 | 390 | 1403.0605 | 636 | 0.30039 | 7.2094 | 138 | 6.6 | 465
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 354890 | FALSE | 19596.9379 | 15016.4864 | 9.3328 | 131 | 0.00011262 | 1350 | 1727.5671 | 518 | 0.29712 | 38.9233 | 139 |  | 2675
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 1382 | FALSE | 8797.2782 | 8797.2782 | 5.4675 | 67 | 0.00010202 | 1603 | 2904.98 | 289 | 0.29503 | 19.7671 | 140 | 0.07 | 1732
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | CB | FALSE | 55860.8325 | 55860.8325 | 34.7177 | 368 | 5.1188e-05 | 3010 | 6445.9013 | 19 | 0.29173 | 107.3565 | 141 | 0.21 | 1150
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | CB | FALSE | 44193.7001 | 42311.3503 | 26.2967 | 280 | 7.4699e-05 | 2339 | 3983.5914 | 150 | 0.29054 | 81.3506 | 142 | 18.05 | 326
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 1600 | FALSE | 17254.9785 | 7231.4682 | 4.4944 | 106 | 9.3311e-05 | 1813 | 3227.6771 | 231 | 0.2889 | 30.6232 | 143 | 0.04 | 2087
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 10030 | FALSE | 59186.5885 | 54599.1868 | 33.9336 | 227 | 5.1982e-05 | 2993 | 5711.1735 | 43 | 0.28655 | 65.0478 | 144 | 0.04 | 2223
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 669720 | FALSE | 7831.1318 | 3612.2461 | 2.245 | 22 | 8.813e-05 | 1979 | 4178.9611 | 140 | 0.28655 | 6.3042 | 145 |  | 3370
3809 | WISE 11022230 | 152271102 | WISE 1102 | 2230 | FALSE | 40267.1112 | 38210.8819 | 23.7482 | 278 | 9.8822e-05 | 1674 | 3101.6196 | 254 | 0.28438 | 79.0585 | 146 | 8.79 | 420
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 327814 | FALSE | 23697.2526 | 18621.0587 | 11.5731 | 119 | 5.813e-05 | 2832 | 5439.3493 | 48 | 0.28428 | 33.8288 | 147 |  | 2778
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 280170 | FALSE | 24945.6136 | 20943.3132 | 13.0164 | 102 | 0.00011005 | 1411 | 2725.4901 | 307 | 0.28426 | 28.9943 | 148 |  | 2855
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 2949 | TRUE | 766.5719 | 766.5719 | 0.47643 | 6 | 4.9947e-05 | 3039 | 6323.2739 | 22 | 0.28416 | 1.7049 | 149 | 2.67 | 590
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | CB | FALSE | 17940.9873 | 8017.5323 | 4.9829 | 118 | 0.00011905 | 1205 | 2481.2226 | 344 | 0.28403 | 33.5157 | 150 | 0.04 | 2142
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 5300 | FALSE | 89782.9365 | 89782.9365 | 55.8005 | 507 | 6.1292e-05 | 2742 | 5197.3797 | 62 | 0.28372 | 143.8456 | 151 | 0.2 | 1159
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 750 | FALSE | 14900.5272 | 7342.9025 | 4.5636 | 93 | 0.00015288 | 720 | 2183.6202 | 404 | 0.28318 | 26.3354 | 152 | 3.16 | 559
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | Y66 | FALSE | 29410.1773 | 27268.3855 | 16.9474 | 138 | 5.9163e-05 | 2801 | 4926.5491 | 81 | 0.28279 | 39.0253 | 153 | 8.36 | 431
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 10320 | FALSE | 18962.0898 | 18962.0898 | 11.785 | 133 | 7.3548e-05 | 2380 | 3652.1529 | 186 | 0.28179 | 37.4782 | 154 | 0.06 | 1810
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 58990 | TRUE | 971.5045 | 427.9744 | 0.26599 | 6 | 0.00011359 | 1330 | 3017.9754 | 266 | 0.28025 | 1.6815 | 155 |  | 3495
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 277014 | FALSE | 26491.1541 | 8850.8283 | 5.5008 | 149 | 7.4914e-05 | 2333 | 3435.5989 | 208 | 0.28002 | 41.7232 | 156 |  | 2840
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 53118 | FALSE | 15490.2629 | 15490.2629 | 9.6273 | 47 | 5.9428e-05 | 2792 | 5134.3568 | 65 | 0.27952 | 13.1375 | 157 | 0.08 | 1618
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 654021 | TRUE | 1396.0557 | 329.1954 | 0.2046 | 12 | 6.2033e-05 | 2719 | 5297.9521 | 54 | 0.27878 | 3.3454 | 158 |  | 3351
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 35598 | FALSE | 17452.8092 | 17452.8092 | 10.847 | 122 | 0.00012105 | 1163 | 2054.3578 | 443 | 0.27855 | 33.9836 | 159 | 2.42 | 604
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 1574 | FALSE | 30217.612 | 27209.5234 | 16.9108 | 221 | 9.7752e-05 | 1698 | 3321.0394 | 222 | 0.27852 | 61.5533 | 160 | 0.1 | 1499
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 4626 | FALSE | 50138.0738 | 43527.4256 | 27.0525 | 238 | 9.7355e-05 | 1704 | 2906.275 | 288 | 0.27841 | 66.2609 | 161 | 0.08 | 1626
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 873457 | FALSE | 3228.1461 | 2440.6531 | 1.5169 | 18 | 6.4601e-05 | 2620 | 3816.6955 | 166 | 0.27723 | 4.9901 | 162 |  | 3525
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | R2578 | FALSE | 74560.0099 | 74560.0099 | 46.3393 | 506 | 5.751e-05 | 2848 | 5003.4373 | 77 | 0.27714 | 140.2335 | 163 | 0.12 | 1377
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | CB | FALSE | 61825.449 | 61825.449 | 38.4248 | 420 | 0.00010575 | 1502 | 2969.029 | 273 | 0.27679 | 116.2539 | 164 | 0.1 | 1498
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 9570 | FALSE | 12951.7997 | 12951.7997 | 8.0496 | 59 | 6.9285e-05 | 2498 | 4812.6159 | 92 | 0.27669 | 16.3249 | 165 | 0.03 | 2273
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | CB | FALSE | 22596.9807 | 22596.9807 | 14.0441 | 79 | 8.9146e-05 | 1941 | 3040.7048 | 264 | 0.2766 | 21.851 | 166 | 0.05 | 2045
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | CB | TRUE | 286.9891 | 286.9891 | 0.17836 | 2 | 0.00034143 | 96 | 952.1877 | 859 | 0.27613 | 0.55227 | 167 |  | 3629
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 64664 | FALSE | 46084.8025 | 44670.3665 | 27.7628 | 263 | 0.00011497 | 1301 | 2595.543 | 331 | 0.27567 | 72.501 | 168 | 7.76 | 441
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 1350 | FALSE | 34999.9271 | 34999.9271 | 21.7526 | 212 | 0.00015371 | 714 | 2128.0484 | 418 | 0.27537 | 58.3793 | 169 | 0.14 | 1328
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | MR765 | FALSE | 3411.7079 | 3330.9197 | 2.0702 | 15 | 0.00016258 | 618 | 1924.3853 | 466 | 0.2736 | 4.104 | 170 |  | 3219
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 8352 | FALSE | 19103.6731 | 10298.4219 | 6.4005 | 133 | 7.7051e-05 | 2286 | 3533.4319 | 197 | 0.27308 | 36.3202 | 171 | 0.04 | 2110
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 716 | FALSE | 27459.7262 | 24685.2253 | 15.342 | 109 | 0.00010173 | 1611 | 2445.3377 | 351 | 0.27295 | 29.7514 | 172 | 0.09 | 1540
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 2198 | FALSE | 33673.9837 | 32552.0609 | 20.2312 | 248 | 0.00015745 | 669 | 1901.3176 | 477 | 0.27291 | 67.6807 | 173 | 5.01 | 498
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 400470 | TRUE | 475.2183 | 334.0108 | 0.20759 | 3 | 0.0001432 | 822 | 1757.1387 | 513 | 0.27287 | 0.81862 | 174 |  | 3474
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | R309 | FALSE | 13825.8859 | 13825.8859 | 8.5928 | 92 | 4.4689e-05 | 3170 | 5876.5086 | 35 | 0.27286 | 25.1032 | 175 | 0.07 | 1734
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 998 | FALSE | 27408.0031 | 23900.855 | 14.8545 | 205 | 0.00011619 | 1266 | 2601.6522 | 329 | 0.27124 | 55.6044 | 176 | 9.39 | 410
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | MR572 | FALSE | 19863.5833 | 13342.8208 | 8.2926 | 80 | 8.353e-05 | 2113 | 3855.5003 | 161 | 0.27121 | 21.6967 | 177 | 0.06 | 1900
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 6552 | FALSE | 20088.9562 | 20088.9562 | 12.4854 | 139 | 0.00023194 | 279 | 1458.479 | 613 | 0.2712 | 37.6964 | 178 | 0.07 | 1674
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 80670 | FALSE | 26435.3887 | 23201.6685 | 14.4199 | 158 | 9.3264e-05 | 1814 | 3120.2999 | 252 | 0.27059 | 42.753 | 179 | 0.07 | 1687
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 118944 | FALSE | 8499.846 | 3772.9974 | 2.3449 | 41 | 7.2601e-05 | 2402 | 3739.9482 | 177 | 0.27039 | 11.0862 | 180 |  | 3148
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 482 | FALSE | 41604.9679 | 39433.4736 | 24.5081 | 188 | 8.3389e-05 | 2120 | 3402.5308 | 212 | 0.26975 | 50.7128 | 181 | 0.11 | 1426
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | CB | FALSE | 37179.8547 | 36440.0989 | 22.6477 | 254 | 0.00012368 | 1127 | 2336.1435 | 377 | 0.26784 | 68.0313 | 182 | 0.11 | 1411
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 636114 | FALSE | 32974.1643 | 32974.1643 | 20.4936 | 153 | 5.0431e-05 | 3029 | 5596.4616 | 45 | 0.26702 | 40.8546 | 183 |  | 3171
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 564710 | TRUE | 541.7371 | 273.7323 | 0.17013 | 7 | 4.7515e-05 | 3102 | 4812.031 | 93 | 0.26624 | 1.8637 | 184 |  | 3533
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 275986 | TRUE | 934.5883 | 934.5883 | 0.58085 | 5 | 8.2974e-05 | 2131 | 2938.8625 | 283 | 0.26526 | 1.3263 | 185 |  | 3473
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 50072 | FALSE | 68212.3656 | 68212.3656 | 42.3943 | 424 | 8.3823e-05 | 2099 | 2904.6654 | 290 | 0.26524 | 112.4633 | 186 | 0.17 | 1228
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 10070 | FALSE | 42054.457 | 42054.457 | 26.137 | 249 | 5.9269e-05 | 2796 | 3802.6518 | 169 | 0.2644 | 65.835 | 187 | 0.16 | 1265
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 10880 | FALSE | 64212.5757 | 63861.6467 | 39.6903 | 362 | 5.4719e-05 | 2925 | 5019.3026 | 74 | 0.2637 | 95.458 | 188 | 0.25 | 1077
1822 | BELL 110750172 | 152701107 | BELL 1107 | 50172 | FALSE | 30233.9103 | 28142.3136 | 17.4906 | 210 | 8.9513e-05 | 1930 | 3226.5987 | 232 | 0.2635 | 55.3341 | 189 | 3.07 | 565
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 13652 | FALSE | 6914.8485 | 6914.8485 | 4.2976 | 58 | 0.00011431 | 1311 | 2370.7576 | 367 | 0.26339 | 15.2768 | 190 | 4.89 | 502
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 399855 | FALSE | 4438.9669 | 4409.9199 | 2.7408 | 19 | 0.00012846 | 1040 | 1799.172 | 506 | 0.26331 | 5.0028 | 191 |  | 2826
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 4710 | FALSE | 2414.0517 | 2414.0517 | 1.5003 | 18 | 7.3983e-05 | 2359 | 3402.6996 | 211 | 0.26308 | 4.7355 | 192 | 0.06 | 1858
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 1808 | FALSE | 25003.3757 | 25003.3757 | 15.5397 | 171 | 0.00012923 | 1021 | 2096.2914 | 428 | 0.26282 | 44.9426 | 193 | 0.09 | 1564
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 1380 | FALSE | 37070.8959 | 28672.6173 | 17.8201 | 204 | 0.00010398 | 1553 | 2782.7866 | 301 | 0.26207 | 53.462 | 194 | 0.07 | 1696
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 45190 | FALSE | 60483.5997 | 60483.5997 | 37.5908 | 416 | 4.4054e-05 | 3190 | 5858.6509 | 37 | 0.26095 | 108.5552 | 195 | 0.15 | 1301
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | B504R | FALSE | 18129.2647 | 14074.6887 | 8.7475 | 97 | 9.8714e-05 | 1676 | 3474.2779 | 204 | 0.26071 | 25.289 | 196 | 0.1 | 1494
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 18292 | TRUE | 8145.543 | 73.0344 | 0.045391 | 73 | 0.00010766 | 1460 | 2089.0547 | 431 | 0.26015 | 18.9907 | 197 | 4.97 | 499
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | CB | FALSE | 15377.0316 | 15053.0301 | 9.3555 | 98 | 0.00013609 | 918 | 2689.4423 | 314 | 0.25991 | 25.4708 | 198 | 1.45 | 674
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 10990 | FALSE | 64432.5092 | 64432.5092 | 40.0451 | 390 | 6.2843e-05 | 2688 | 4452.3041 | 112 | 0.25971 | 101.2865 | 199 | 0.23 | 1118
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 85162 | FALSE | 9267.4821 | 9267.4821 | 5.7598 | 28 | 4.8495e-05 | 3077 | 5246.1165 | 57 | 0.2589 | 7.2492 | 200 | 0.09 | 1512
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36652 | FALSE | 58152.9177 | 58152.9177 | 36.1423 | 357 | 6.9107e-05 | 2503 | 3912.9423 | 155 | 0.25884 | 92.4048 | 201 | 2.74 | 586
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 660 | FALSE | 15616.9486 | 9914.559 | 6.1619 | 91 | 0.00011219 | 1361 | 2640.3198 | 322 | 0.25883 | 23.5531 | 202 | 0.02 | 2506
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 696 | FALSE | 15381.4122 | 10464.5667 | 6.5038 | 87 | 0.00011584 | 1275 | 2155.4593 | 411 | 0.25793 | 22.4395 | 203 | 0.04 | 2141
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | CB | FALSE | 109280.4349 | 109280.4349 | 67.9182 | 589 | 7.6086e-05 | 2305 | 3828.8466 | 165 | 0.25597 | 150.7655 | 204 | 0.64 | 828
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 534 | FALSE | 33775.8497 | 30432.3399 | 18.9138 | 142 | 8.2307e-05 | 2145 | 3212.6445 | 237 | 0.25577 | 36.3189 | 205 | 0.12 | 1397
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 93504 | FALSE | 4036.8011 | 3461.2366 | 2.1512 | 15 | 6.0933e-05 | 2750 | 4082.5968 | 144 | 0.25426 | 3.8139 | 206 | 0.06 | 1896
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 873304 | FALSE | 1312.9508 | 1312.9508 | 0.816 | 5 | 6.945e-05 | 2489 | 4833.6394 | 88 | 0.25419 | 1.2709 | 207 |  | 3605
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 59714 | FALSE | 7503.916 | 7503.916 | 4.6637 | 34 | 9.4275e-05 | 1786 | 2408.1592 | 360 | 0.25391 | 8.6328 | 208 | 0.04 | 2176
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 990354 | TRUE | 170.3854 | 170.3854 | 0.1059 | 2 | 0.00030725 | 122 | 583.9962 | 1119 | 0.25341 | 0.50682 | 209 | 0.02 | 2532
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 526 | FALSE | 17461.3012 | 16256.6321 | 10.1036 | 100 | 0.00011252 | 1356 | 2700.181 | 312 | 0.25318 | 25.318 | 210 | 0.07 | 1679
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 558 | FALSE | 15006.3638 | 4818.3603 | 2.9946 | 72 | 0.00022789 | 291 | 857.3477 | 909 | 0.25266 | 18.1915 | 211 | 0.01 | 2601
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 568 | FALSE | 14789.9903 | 12940.6184 | 8.0426 | 118 | 0.00012911 | 1024 | 2034.9748 | 449 | 0.25222 | 29.7625 | 212 | 0.1 | 1493
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | R902 | FALSE | 24261.144 | 24261.144 | 15.0784 | 156 | 6.3332e-05 | 2666 | 4129.7341 | 141 | 0.25137 | 39.2136 | 213 | 0.07 | 1688
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | MR169 | FALSE | 15006.414 | 4976.4795 | 3.0929 | 96 | 9.4566e-05 | 1776 | 2310.912 | 383 | 0.25044 | 24.0426 | 214 | 0.02 | 2435
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 99904 | FALSE | 8949.4853 | 8949.4853 | 5.5621 | 54 | 0.00018177 | 500 | 1184.3918 | 739 | 0.25006 | 13.5032 | 215 | 39.72 | 187
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 37504 | FALSE | 5704.6998 | 1890.9339 | 1.1752 | 41 | 0.00013442 | 938 | 1727.1376 | 519 | 0.24974 | 10.2392 | 216 | 0.02 | 2505
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | CB | FALSE | 6924.1001 | 6924.1001 | 4.3034 | 22 | 5.902e-05 | 2806 | 4006.0392 | 149 | 0.24862 | 5.4697 | 217 | 0.07 | 1691
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 702710 | FALSE | 7335.7671 | 4286.5556 | 2.6641 | 49 | 0.00021702 | 330 | 1323.547 | 672 | 0.24845 | 12.174 | 218 |  | 3072
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 66146 | TRUE | 252.3083 | 252.3083 | 0.15681 | 4 | 0.00010984 | 1414 | 2698.6732 | 313 | 0.24793 | 0.99171 | 219 | 0.12 | 1382
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 346006 | FALSE | 3918.3073 | 3650.4625 | 2.2688 | 5 | 7.7555e-05 | 2277 | 3061.2643 | 262 | 0.24765 | 1.2382 | 220 |  | 3479
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 90036 | FALSE | 23187.5221 | 21561.1762 | 13.4004 | 87 | 7.3822e-05 | 2364 | 4520.2585 | 105 | 0.24724 | 21.5103 | 221 | 0.1 | 1505
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 5732 | FALSE | 5445.3198 | 5445.3198 | 3.3843 | 37 | 5.3285e-05 | 2956 | 4484.9828 | 109 | 0.24719 | 9.1461 | 222 | 0.14 | 1324
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 37282 | FALSE | 96262.8931 | 86430.7687 | 53.7171 | 498 | 6.5439e-05 | 2602 | 4244.8756 | 134 | 0.24522 | 122.1205 | 223 | 0.36 | 969
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 63334 | FALSE | 27819.9713 | 27819.9713 | 17.2902 | 154 | 5.0298e-05 | 3032 | 5273.9392 | 55 | 0.24446 | 37.6467 | 224 | 10.23 | 400
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 31502 | FALSE | 19104.3686 | 19104.3686 | 11.8734 | 102 | 0.00014287 | 828 | 1982.4694 | 459 | 0.24429 | 24.9173 | 225 | 0.08 | 1616
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 35874 | TRUE | 329.4831 | 329.4831 | 0.20478 | 4 | 0.0002322 | 276 | 974.717 | 846 | 0.24298 | 0.97191 | 226 | 0.03 | 2258
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 9372 | FALSE | 28750.7098 | 28750.7098 | 17.8687 | 190 | 0.00012144 | 1159 | 1860.3939 | 487 | 0.24281 | 46.1342 | 227 | 6.15 | 472
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 756 | TRUE | 948.4078 | 948.4078 | 0.58944 | 7 | 0.00037409 | 76 | 1141.7089 | 757 | 0.24238 | 1.6966 | 228 | 0.02 | 2431
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | N60 | FALSE | 14171.0101 | 13316.658 | 8.2764 | 66 | 6.3749e-05 | 2655 | 3875.817 | 160 | 0.24236 | 15.9958 | 229 | 0.04 | 2143
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 685276 | FALSE | 34821.9656 | 10432.3869 | 6.4838 | 216 | 7.8086e-05 | 2256 | 3212.4401 | 238 | 0.24208 | 52.2897 | 230 |  | 2761
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 416226 | TRUE | 397.9238 | 186.6616 | 0.11601 | 5 | 8.4899e-05 | 2065 | 2680.4211 | 316 | 0.24182 | 1.2091 | 231 |  | 3167
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 17011 | FALSE | 3005.3172 | 3005.3172 | 1.8678 | 22 | 9.7443e-05 | 1702 | 2978.7374 | 270 | 0.24153 | 5.3136 | 232 | 0.07 | 1747
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | Y02 | FALSE | 21138.3499 | 16812.4916 | 10.449 | 158 | 6.2768e-05 | 2691 | 3729.2174 | 180 | 0.24142 | 38.1442 | 233 | 0.07 | 1717
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 186326 | FALSE | 20743.7329 | 19088.8539 | 11.8638 | 123 | 0.00011431 | 1312 | 2157.6907 | 410 | 0.24114 | 29.6596 | 234 |  | 3066
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | CB | FALSE | 13066.3244 | 13066.3244 | 8.1208 | 67 | 0.00015785 | 665 | 1253.7272 | 700 | 0.24096 | 16.1444 | 235 | 0.13 | 1360
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 117644 | FALSE | 3757.3782 | 1080.3525 | 0.67144 | 12 | 9.3021e-05 | 1820 | 2949.3645 | 280 | 0.23987 | 2.8784 | 236 |  | 3416
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 617260 | FALSE | 4545.7003 | 1876.8402 | 1.1665 | 15 | 9.4125e-05 | 1791 | 3143.4533 | 249 | 0.2396 | 3.5941 | 237 |  | 3506
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 63389 | TRUE | 391.5938 | 0 | 0 | 2 | 0.00010287 | 1573 | 1639.5129 | 547 | 0.23935 | 0.47871 | 238 |  | 3610
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 904 | FALSE | 5777.0339 | 5445.6493 | 3.3845 | 30 | 9.2995e-05 | 1822 | 2564.652 | 336 | 0.23862 | 7.1587 | 239 | 1.48 | 670
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 19522 | FALSE | 16493.1882 | 15565.1755 | 9.6738 | 113 | 8.878e-05 | 1959 | 3187.9029 | 244 | 0.23827 | 26.9251 | 240 | 34.17 | 216
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | MR387 | FALSE | 8072.5307 | 8065.9096 | 5.013 | 24 | 6.2945e-05 | 2681 | 3500.2914 | 201 | 0.23776 | 5.7062 | 241 | 0.06 | 1882
109 | WISE 11022054 | 152271102 | WISE 1102 | 2054 | FALSE | 20940.0353 | 20940.0353 | 13.0143 | 147 | 0.00010429 | 1544 | 2815.7078 | 298 | 0.23735 | 34.8898 | 242 | 3.46 | 547
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 318686 | FALSE | 4853.6414 | 2345.6024 | 1.4578 | 7 | 6.5096e-05 | 2607 | 3652.241 | 185 | 0.23683 | 1.6578 | 243 |  | 3349
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 1314 | FALSE | 23311.1376 | 9677.7607 | 6.0148 | 161 | 8.2165e-05 | 2148 | 3017.906 | 267 | 0.23664 | 38.0983 | 244 | 1.18 | 703
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | R353 | FALSE | 22190.5443 | 22190.5443 | 13.7915 | 53 | 3.7075e-05 | 3313 | 6512.8186 | 18 | 0.23576 | 12.4952 | 245 | 0.07 | 1773
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 12608 | FALSE | 27131.1027 | 27131.1027 | 16.8621 | 187 | 6.2935e-05 | 2683 | 3772.462 | 174 | 0.23545 | 44.029 | 246 | 11.8 | 381
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 707358 | FALSE | 37001.2559 | 30537.9753 | 18.9795 | 219 | 4.1347e-05 | 3238 | 5721.8442 | 41 | 0.23489 | 51.4409 | 247 |  | 2974
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 92888 | TRUE | 765.3621 | 400.6025 | 0.24898 | 4 | 0.00010691 | 1480 | 2347.6932 | 375 | 0.23471 | 0.93885 | 248 | 0.01 | 2581
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 8482 | FALSE | 23390.9929 | 23390.9929 | 14.5376 | 117 | 0.00010252 | 1587 | 2287.3259 | 386 | 0.23437 | 27.4214 | 249 | 0.05 | 2057
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 725408 | FALSE | 2105.6406 | 1530.1897 | 0.95102 | 9 | 9.3021e-05 | 1821 | 2838.0743 | 294 | 0.23427 | 2.1085 | 250 |  | 3511
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | R56 | FALSE | 19965.7505 | 18526.1855 | 11.5141 | 117 | 9.8997e-05 | 1669 | 2922.3966 | 284 | 0.2342 | 27.401 | 251 | 1.75 | 644
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 1892 | FALSE | 5154.3447 | 5154.3447 | 3.2034 | 12 | 0.00011418 | 1317 | 1393.5299 | 640 | 0.23339 | 2.8006 | 252 | 0.06 | 1887
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 37334 | FALSE | 15392.9848 | 15392.9848 | 9.5668 | 70 | 5.2877e-05 | 2973 | 4838.4242 | 87 | 0.23311 | 16.3175 | 253 | 0.07 | 1730
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 3988 | FALSE | 29512.4633 | 27217.7374 | 16.9159 | 68 | 4.0141e-05 | 3264 | 5944.554 | 32 | 0.23303 | 15.8463 | 254 | 0.1 | 1471
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | CB | FALSE | 23543.7827 | 17030.244 | 10.5844 | 164 | 0.00014109 | 852 | 1638.3807 | 548 | 0.23182 | 38.0188 | 255 | 0.08 | 1577
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | M84 | FALSE | 39352.9214 | 37718.995 | 23.4425 | 145 | 7.1467e-05 | 2434 | 3431.3832 | 209 | 0.23169 | 33.5958 | 256 | 0.05 | 2018
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | N58 | FALSE | 11929.7838 | 7319.6094 | 4.5492 | 91 | 8.9683e-05 | 1923 | 2958.7213 | 277 | 0.23099 | 21.0205 | 257 | 1.43 | 676
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5597 | FALSE | 8229.9238 | 8229.9238 | 5.1149 | 22 | 5.7292e-05 | 2855 | 4008.4187 | 148 | 0.23009 | 5.062 | 258 | 0.06 | 1847
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 412 | FALSE | 27547.3528 | 16599.9817 | 10.317 | 152 | 9.7196e-05 | 1709 | 2705.0187 | 311 | 0.23008 | 34.9724 | 259 | 0.04 | 2122
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 2731 | FALSE | 2630.6286 | 2630.6286 | 1.6349 | 13 | 8.1626e-05 | 2166 | 3132.5166 | 251 | 0.2296 | 2.9847 | 260 | 0.25 | 1088
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | CB | FALSE | 9780.4489 | 2376.9126 | 1.4773 | 72 | 0.00018501 | 472 | 1136.289 | 760 | 0.22956 | 16.5281 | 261 | 0.02 | 2474
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 226050 | FALSE | 24153.2004 | 7845.4549 | 4.876 | 160 | 0.00012494 | 1099 | 1958.1377 | 463 | 0.22913 | 36.6601 | 262 |  | 2875
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 10400 | FALSE | 72169.1615 | 68567.3531 | 42.6149 | 539 | 6.3171e-05 | 2673 | 4382.9111 | 117 | 0.22826 | 123.0305 | 263 | 0.67 | 815
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 50078 | FALSE | 77925.0015 | 77925.0015 | 48.4307 | 427 | 6.6516e-05 | 2573 | 3492.1838 | 203 | 0.22791 | 97.3194 | 264 | 0.18 | 1215
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 37472 | FALSE | 23988.0552 | 14935.9015 | 9.2827 | 157 | 0.00012968 | 1013 | 1878.4311 | 481 | 0.22739 | 35.7007 | 265 | 0.05 | 2001
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 10820 | FALSE | 46507.9226 | 46392.4448 | 28.8331 | 327 | 6.2605e-05 | 2698 | 4312.1018 | 124 | 0.2269 | 74.1966 | 266 | 0.19 | 1188
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 96554 | FALSE | 23931.0858 | 12987.3897 | 8.0717 | 172 | 7.0376e-05 | 2458 | 3307.1204 | 223 | 0.22645 | 38.9486 | 267 | 1.68 | 653
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | CB | FALSE | 2444.9029 | 1435.1005 | 0.89192 | 20 | 0.0002022 | 389 | 1029.6753 | 809 | 0.22632 | 4.5263 | 268 | 0.01 | 2599
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | Y50 | FALSE | 20651.346 | 17101.0403 | 10.6284 | 147 | 6.643e-05 | 2578 | 3157.5997 | 246 | 0.22624 | 33.2573 | 269 | 4.23 | 523
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 1230 | FALSE | 31242.042 | 27069.5791 | 16.8239 | 136 | 8.4359e-05 | 2080 | 2820.2882 | 297 | 0.22608 | 30.7471 | 270 | 0.08 | 1627
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 9026 | FALSE | 39327.0742 | 20154.6992 | 12.5262 | 282 | 7.3532e-05 | 2382 | 3010.4191 | 268 | 0.22599 | 63.7295 | 271 | 0.04 | 2131
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 672 | FALSE | 35787.4101 | 35088.8854 | 21.8079 | 140 | 0.00010502 | 1528 | 2485.285 | 343 | 0.22571 | 31.5995 | 272 | 0.66 | 819
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 1630 | FALSE | 22751.2492 | 4020.9242 | 2.499 | 152 | 5.7083e-05 | 2858 | 3897.064 | 159 | 0.22562 | 34.2944 | 273 | 0.02 | 2518
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | R2839 | FALSE | 20608.9537 | 20608.9537 | 12.8085 | 121 | 6.3713e-05 | 2657 | 3802.0162 | 170 | 0.22501 | 27.2266 | 274 | 0.07 | 1746
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 2582 | FALSE | 33578.71 | 32011.0943 | 19.895 | 186 | 8.3332e-05 | 2124 | 2966.3342 | 275 | 0.22449 | 41.7559 | 275 | 0.31 | 999
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 1622 | FALSE | 54701.9644 | 54701.9644 | 33.9975 | 126 | 4.7554e-05 | 3098 | 5068.1116 | 70 | 0.22413 | 28.2406 | 276 | 0.15 | 1289
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | R2579 | FALSE | 56162.7607 | 56162.7607 | 34.9054 | 286 | 4.3679e-05 | 3195 | 4995.9654 | 78 | 0.22394 | 64.0469 | 277 | 0.05 | 1982
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | R1013 | FALSE | 20054.4308 | 20054.4308 | 12.4639 | 132 | 5.2064e-05 | 2991 | 4310.3961 | 125 | 0.22385 | 29.5483 | 278 | 0.08 | 1599
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 726 | FALSE | 56301.3396 | 48875.2274 | 30.3762 | 263 | 0.00010365 | 1558 | 2367.3738 | 368 | 0.22347 | 58.7725 | 279 | 5.19 | 495
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | CB | FALSE | 11342.4728 | 11342.4728 | 7.0494 | 33 | 9.1397e-05 | 1864 | 1823.5922 | 499 | 0.22294 | 7.3571 | 280 | 1.24 | 696
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 1664 | FALSE | 47581.2918 | 47581.2918 | 29.572 | 244 | 0.00016153 | 624 | 1257.5627 | 697 | 0.22209 | 54.1896 | 281 | 0.09 | 1544
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | Y72 | FALSE | 10347.4182 | 10265.6354 | 6.3801 | 36 | 7.4862e-05 | 2335 | 2941.2416 | 282 | 0.2213 | 7.967 | 282 | 0.05 | 1994
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 508502 | FALSE | 25902.2253 | 18917.893 | 11.7575 | 115 | 8.1215e-05 | 2178 | 2793.3826 | 300 | 0.22043 | 25.3491 | 283 |  | 2971
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | CB | FALSE | 26399.8993 | 26026.0287 | 16.1753 | 152 | 0.00012844 | 1042 | 2226.2508 | 395 | 0.21931 | 33.3354 | 284 | 0.08 | 1659
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 9504 | FALSE | 23288.5561 | 23283.8699 | 14.471 | 97 | 5.1866e-05 | 2997 | 4524.1542 | 104 | 0.21922 | 21.2645 | 285 | 0.67 | 812
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | CB | FALSE | 13738.3645 | 13738.3645 | 8.5384 | 32 | 4.0322e-05 | 3260 | 5713.5203 | 42 | 0.21869 | 6.998 | 286 | 0.06 | 1881
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | CB | FALSE | 25047.8448 | 25047.8448 | 15.5673 | 65 | 0.00013384 | 945 | 2147.2351 | 413 | 0.21823 | 14.185 | 287 | 0.06 | 1867
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 36622 | FALSE | 15095.8174 | 8277.82 | 5.1447 | 42 | 0.00010696 | 1475 | 1906.2139 | 474 | 0.21771 | 9.1438 | 288 | 0.01 | 2620
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 13018 | FALSE | 2657.2717 | 1090.3862 | 0.67768 | 20 | 0.00024176 | 241 | 916.9696 | 877 | 0.21662 | 4.3325 | 289 | 0.04 | 2205
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | CB | FALSE | 4716.8976 | 4354.341 | 2.7062 | 38 | 0.00020157 | 391 | 1548.9969 | 580 | 0.21644 | 8.2246 | 290 | 0.07 | 1689
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | N52 | FALSE | 10571.3698 | 10571.3698 | 6.5701 | 32 | 0.00016961 | 565 | 1370.1644 | 652 | 0.21643 | 6.9258 | 291 | 0.06 | 1851
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 1536 | FALSE | 29066.1076 | 28603.8149 | 17.7774 | 79 | 4.6575e-05 | 3124 | 4923.7257 | 83 | 0.21608 | 17.0703 | 292 | 0.07 | 1705
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 665952 | TRUE | 1521.662 | 243.3824 | 0.15126 | 13 | 7.1774e-05 | 2427 | 3135.666 | 250 | 0.21591 | 2.8069 | 293 |  | 3252
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 47786 | FALSE | 2915.7036 | 2915.7036 | 1.8121 | 13 | 8.7369e-05 | 2003 | 2875.37 | 291 | 0.21513 | 2.7967 | 294 | 0.01 | 2571
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 736078 | TRUE | 432.8669 | 373.6781 | 0.23224 | 3 | 6.8384e-05 | 2526 | 3199.3848 | 241 | 0.2146 | 0.64381 | 295 |  | 3522
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 306972 | TRUE | 120.3234 | 83.4407 | 0.051859 | 2 | 0.00015818 | 661 | 1356.3524 | 660 | 0.21455 | 0.4291 | 296 |  | 3576
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | CB | FALSE | 4947.493 | 4947.493 | 3.0749 | 21 | 0.00013269 | 965 | 2090.7818 | 430 | 0.21399 | 4.4937 | 297 | 0.32 | 995
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 11210 | FALSE | 27492.7886 | 27492.7886 | 17.0869 | 139 | 4.899e-05 | 3064 | 4555.1801 | 103 | 0.21387 | 29.7273 | 298 | 0.02 | 2413
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 385838 | FALSE | 2645.3497 | 2006.1588 | 1.2468 | 11 | 9.3256e-05 | 1815 | 1869.8054 | 483 | 0.21349 | 2.3484 | 299 |  | 3295
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 2944 | FALSE | 24391.9365 | 24262.4198 | 15.0792 | 148 | 5.6051e-05 | 2885 | 4103.8075 | 143 | 0.21331 | 31.5694 | 300 | 0.08 | 1576
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 1582 | FALSE | 24298.6245 | 10265.1395 | 6.3798 | 173 | 8.393e-05 | 2096 | 2774.3491 | 305 | 0.21327 | 36.8955 | 301 | 0.05 | 1927
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 7360 | FALSE | 14342.2552 | 14342.2552 | 8.9138 | 83 | 5.7731e-05 | 2844 | 3097.6367 | 256 | 0.21272 | 17.6557 | 302 | 0 | 2643
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 472084 | FALSE | 11718.4795 | 7454.711 | 4.6331 | 66 | 0.00014287 | 829 | 1759.7585 | 512 | 0.21229 | 14.0108 | 303 | 0.03 | 2360
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 11290 | FALSE | 12662.0411 | 12662.0411 | 7.8695 | 75 | 8.7993e-05 | 1982 | 2545.3939 | 339 | 0.21224 | 15.9178 | 304 | 0.1 | 1455
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | CB | TRUE | 168.4127 | 168.4127 | 0.10467 | 1 | 9.0971e-05 | 1882 | 2332.6265 | 379 | 0.2122 | 0.2122 | 305 | 0.27 | 1058
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 37466 | FALSE | 50978.0825 | 50460.2287 | 31.3612 | 345 | 3.2323e-05 | 3395 | 6743.7065 | 13 | 0.21127 | 72.8874 | 306 | 0.08 | 1598
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | CB | FALSE | 22068.3915 | 11401.8921 | 7.0863 | 148 | 5.6901e-05 | 2864 | 2830.5359 | 295 | 0.21085 | 31.2055 | 307 | 1.66 | 655
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 77098 | FALSE | 20978.2648 | 19250.5668 | 11.9643 | 112 | 5.0472e-05 | 3025 | 4289.2504 | 127 | 0.21042 | 23.5673 | 308 | 2.69 | 589
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 806 | FALSE | 55052.2104 | 33831.6044 | 21.0265 | 229 | 9.1806e-05 | 1850 | 2097.6482 | 426 | 0.21008 | 48.1076 | 309 | 0.15 | 1276
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 21210 | FALSE | 26056.9931 | 20686.2377 | 12.8566 | 111 | 5.4908e-05 | 2916 | 4309.2408 | 126 | 0.20896 | 23.1943 | 310 | 0.06 | 1808
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 79932 | FALSE | 52854.9374 | 35504.8505 | 22.0664 | 345 | 8.0348e-05 | 2196 | 2706.2696 | 310 | 0.20828 | 71.8562 | 311 | 0.1 | 1497
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 454 | FALSE | 8909.2195 | 8909.2195 | 5.5371 | 54 | 6.6514e-05 | 2574 | 3069.2553 | 261 | 0.20738 | 11.1984 | 312 | 0.38 | 962
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 90180 | FALSE | 7976.0066 | 7976.0066 | 4.9571 | 49 | 5.4502e-05 | 2932 | 3678.4222 | 183 | 0.20688 | 10.1373 | 313 | 0.02 | 2514
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 644756 | FALSE | 31848.1753 | 27875.8932 | 17.325 | 163 | 0.00011577 | 1279 | 1915.4825 | 470 | 0.20636 | 33.6372 | 314 |  | 3049
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 2002 | FALSE | 48391.7593 | 35045.7729 | 21.7811 | 109 | 5.5059e-05 | 2908 | 4261.2835 | 130 | 0.20473 | 22.3155 | 315 | 0.05 | 1965
1537 | BELL 11072400 | 152701107 | BELL 1107 | 2400 | FALSE | 44680.5549 | 41414.8349 | 25.7395 | 320 | 0.00010832 | 1445 | 2117.8289 | 423 | 0.20423 | 65.3543 | 316 | 10.83 | 393
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 296 | FALSE | 23764.0701 | 23764.0701 | 14.7695 | 123 | 8.734e-05 | 2004 | 2337.6554 | 376 | 0.20401 | 25.0928 | 317 | 6.9 | 457
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | CB | FALSE | 39932.7775 | 21735.4144 | 13.5086 | 273 | 0.00010469 | 1537 | 2355.7077 | 371 | 0.20316 | 55.4629 | 318 | 0.09 | 1519
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 936897 | TRUE | 1562.7499 | 665.5519 | 0.41364 | 12 | 0.00014733 | 769 | 1798.1732 | 507 | 0.20267 | 2.432 | 319 |  | 3507
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 34338 | FALSE | 16775.5793 | 15726.6133 | 9.7742 | 66 | 6.79e-05 | 2539 | 3085.8385 | 258 | 0.2022 | 13.3455 | 320 | 0.08 | 1669
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | R2850 | FALSE | 42428.4265 | 42428.4265 | 26.3694 | 222 | 3.6057e-05 | 3337 | 5548.3018 | 47 | 0.20166 | 44.7693 | 321 | 0.17 | 1244
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | CB | FALSE | 32934.7957 | 25410.3119 | 15.7926 | 114 | 0.00011157 | 1381 | 1859.3886 | 488 | 0.20132 | 22.9503 | 322 | 0.04 | 2202
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | CB | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00012264 | 1138 | 1641.5431 | 545 | 0.20132 | 0.20132 | 323 | 0.02 | 2423
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | MR176 | FALSE | 68684.3236 | 62474.1803 | 38.828 | 256 | 5.5783e-05 | 2894 | 3634.7993 | 187 | 0.20121 | 51.5086 | 324 | 0.19 | 1184
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 514987 | FALSE | 21614.682 | 13379.7927 | 8.3156 | 63 | 4.6195e-05 | 3132 | 4320.4063 | 122 | 0.20048 | 12.6303 | 325 |  | 3128
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 11158 | FALSE | 47609.4929 | 20499.8935 | 12.7408 | 229 | 9.6418e-05 | 1721 | 2379.6196 | 364 | 0.20008 | 45.8175 | 326 | 0.06 | 1777
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | R314 | FALSE | 71701.2396 | 68245.5324 | 42.4149 | 390 | 3.2526e-05 | 3393 | 6228.9607 | 25 | 0.20004 | 78.017 | 327 | 0.11 | 1437
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 4646 | FALSE | 29868.2951 | 29868.2951 | 18.5633 | 165 | 0.00010487 | 1531 | 2139.2524 | 415 | 0.19983 | 32.9712 | 328 | 36.87 | 205
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4200 | FALSE | 7940.3444 | 6495.7462 | 4.0371 | 37 | 0.00011057 | 1400 | 2908.2309 | 287 | 0.19927 | 7.3729 | 329 | 0.05 | 1995
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 49122 | FALSE | 6376.3554 | 6376.3554 | 3.9629 | 40 | 4.9196e-05 | 3060 | 3584.6164 | 191 | 0.19907 | 7.9627 | 330 | 1.33 | 682
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 96844 | FALSE | 9556.2941 | 9556.2941 | 5.9393 | 63 | 0.00023552 | 260 | 862.5947 | 906 | 0.19881 | 12.5249 | 331 | 46.48 | 142
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 85766 | FALSE | 29746.7523 | 29746.7523 | 18.4877 | 166 | 0.00013073 | 996 | 2062.5576 | 442 | 0.19865 | 32.9759 | 332 | 0.1 | 1495
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 391250 | FALSE | 1481.3226 | 1481.3226 | 0.92065 | 3 | 0.00010172 | 1612 | 1985.1612 | 457 | 0.19841 | 0.59524 | 333 |  | 3356
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | CB | FALSE | 42270.0145 | 42270.0145 | 26.271 | 131 | 0.00014762 | 766 | 1407.8483 | 633 | 0.19817 | 25.9607 | 334 | 0.25 | 1086
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 1276 | FALSE | 20806.9121 | 20806.9121 | 12.9316 | 116 | 9.8156e-05 | 1687 | 2220.124 | 397 | 0.19794 | 22.9608 | 335 | 0.05 | 1931
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 796386 | FALSE | 64232.6683 | 57391.9753 | 35.6693 | 159 | 5.7453e-05 | 2849 | 3563.2207 | 192 | 0.19792 | 31.4686 | 336 |  | 2815
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | CB | FALSE | 20983.2028 | 20983.2028 | 13.0411 | 77 | 2.8008e-05 | 3460 | 6753.7935 | 12 | 0.19768 | 15.2216 | 337 | 0.07 | 1765
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 628 | FALSE | 14091.1105 | 6713.6414 | 4.1726 | 98 | 0.00010294 | 1570 | 2036.6122 | 448 | 0.19686 | 19.2923 | 338 | 0.05 | 2063
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 90550 | FALSE | 12911.2772 | 12911.2772 | 8.0244 | 47 | 5.1033e-05 | 3014 | 3547.8361 | 195 | 0.19624 | 9.2235 | 339 | 0.02 | 2486
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 2106 | FALSE | 21303.4581 | 21303.4581 | 13.2402 | 67 | 3.7752e-05 | 3302 | 5722.5441 | 40 | 0.1961 | 13.1388 | 340 | 0.03 | 2286
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 7040 | FALSE | 39870.081 | 39870.081 | 24.7794 | 230 | 4.8475e-05 | 3079 | 4388.1035 | 116 | 0.19605 | 45.0921 | 341 | 0.07 | 1719
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 500 | FALSE | 47144.6891 | 34375.7452 | 21.3647 | 214 | 0.00018229 | 495 | 1298.6787 | 684 | 0.19576 | 41.8921 | 342 | 2.86 | 574
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 19910 | FALSE | 33304.7006 | 33304.7006 | 20.699 | 226 | 0.00010076 | 1629 | 2072.4287 | 435 | 0.19568 | 44.2238 | 343 | 0.32 | 994
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 555644 | TRUE | 5004.528 | 268.6791 | 0.16699 | 19 | 0.00011733 | 1240 | 1847.862 | 491 | 0.19539 | 3.7125 | 344 |  | 3453
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 708166 | FALSE | 33499.3555 | 18511.1854 | 11.5048 | 162 | 7.986e-05 | 2209 | 2528.2807 | 340 | 0.19539 | 31.6535 | 345 | 9.62 | 407
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 3419 | FALSE | 12848.2917 | 12848.2917 | 7.9853 | 38 | 9.3996e-05 | 1794 | 2318.7771 | 381 | 0.19531 | 7.4218 | 346 | 0.08 | 1610
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 41396 | FALSE | 11819.9639 | 10868.1559 | 6.7546 | 75 | 0.00014922 | 747 | 1168.3526 | 746 | 0.19503 | 14.6272 | 347 | 0.08 | 1642
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | CB | FALSE | 34280.1417 | 27168.7986 | 16.8855 | 236 | 7.8906e-05 | 2237 | 2954.5395 | 278 | 0.19501 | 46.0213 | 348 | 0.13 | 1353
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 584840 | FALSE | 72531.1064 | 72531.1064 | 45.0784 | 449 | 3.4014e-05 | 3370 | 5963.8827 | 31 | 0.19446 | 87.311 | 349 | 0.16 | 1267
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 41356 | FALSE | 52238.1569 | 52238.1569 | 32.4662 | 318 | 8.9642e-05 | 1926 | 2383.6073 | 362 | 0.19445 | 61.8351 | 350 | 1.05 | 720
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 1532 | FALSE | 68074.9976 | 62691.3369 | 38.9629 | 465 | 0.00014754 | 767 | 1398.4344 | 638 | 0.19412 | 90.2637 | 351 | 0.07 | 1756
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 1208 | FALSE | 61463.0017 | 53098.4432 | 33.0009 | 334 | 7.3226e-05 | 2389 | 2975.7795 | 271 | 0.19404 | 64.811 | 352 | 0.06 | 1784
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | CB | FALSE | 12293.5283 | 12293.5283 | 7.6405 | 36 | 4.9465e-05 | 3052 | 3520.3689 | 199 | 0.19398 | 6.9834 | 353 | 0.13 | 1346
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 613086 | FALSE | 14704.7375 | 8243.1424 | 5.1231 | 63 | 2.9814e-05 | 3430 | 6359.1487 | 20 | 0.19391 | 12.2166 | 354 |  | 2913
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | CB | FALSE | 34332.3301 | 30178.5623 | 18.7561 | 171 | 0.00012918 | 1023 | 1585.4725 | 565 | 0.19378 | 33.1366 | 355 | 0.08 | 1606
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 745850 | TRUE | 1558.6923 | 771.4701 | 0.47947 | 7 | 5.3176e-05 | 2960 | 3897.9708 | 158 | 0.19369 | 1.3558 | 356 |  | 3539
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 793776 | FALSE | 1956.9595 | 1956.9595 | 1.2163 | 6 | 0.00010286 | 1574 | 1821.9134 | 500 | 0.19328 | 1.1597 | 357 |  | 3579
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 604 | FALSE | 42817.3578 | 42516.8793 | 26.4244 | 240 | 0.00012061 | 1176 | 1665.6014 | 537 | 0.19315 | 46.357 | 358 | 8.39 | 428
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 532 | FALSE | 7102.1777 | 7099.179 | 4.4122 | 34 | 0.00016574 | 585 | 1247.6791 | 702 | 0.19264 | 6.5497 | 359 | 0.65 | 824
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 2032 | FALSE | 15248.6713 | 14097.676 | 8.7618 | 52 | 6.4621e-05 | 2618 | 3297.3647 | 225 | 0.19237 | 10.0031 | 360 | 0.06 | 1841
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 13044 | FALSE | 9652.7072 | 7674.8454 | 4.7699 | 51 | 0.00014015 | 867 | 1674.4804 | 533 | 0.19229 | 9.8065 | 361 | 0.05 | 1986
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 7140 | FALSE | 42300.5526 | 42300.5526 | 26.29 | 296 | 2.8237e-05 | 3453 | 6738.8921 | 14 | 0.19202 | 56.8394 | 362 | 3.46 | 546
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 82350 | FALSE | 33588.8136 | 31579.2765 | 19.6266 | 230 | 8.9019e-05 | 1948 | 2107.591 | 425 | 0.19196 | 44.1515 | 363 | 0.3 | 1019
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 7220 | FALSE | 39952.2483 | 39952.2483 | 24.8305 | 188 | 4.2565e-05 | 3217 | 4516.9217 | 107 | 0.19171 | 36.0414 | 364 | 0.06 | 1901
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | CB | TRUE | 25.9334 | 25.9334 | 0.016118 | 1 | 0.00013855 | 888 | 1382.2827 | 648 | 0.19152 | 0.19152 | 365 | 0.05 | 1929
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 645910 | TRUE | 3990.9244 | 774.6277 | 0.48143 | 14 | 0.00012447 | 1110 | 1323.2798 | 673 | 0.19134 | 2.6788 | 366 |  | 3245
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 98478 | FALSE | 9678.6987 | 9678.6987 | 6.0154 | 34 | 6.1513e-05 | 2732 | 3101.9251 | 253 | 0.19124 | 6.5022 | 367 | 0.06 | 1824
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 5607 | FALSE | 10708.8001 | 7265.9446 | 4.5158 | 71 | 6.7647e-05 | 2544 | 3213.7492 | 235 | 0.19115 | 13.5714 | 368 | 0.05 | 2002
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 524 | TRUE | 4106.6103 | 399.4552 | 0.24826 | 31 | 8.7723e-05 | 1992 | 2173.4374 | 408 | 0.19015 | 5.8946 | 369 | 0.71 | 803
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 697216 | FALSE | 21374.2842 | 21374.2842 | 13.2842 | 145 | 8.8971e-05 | 1951 | 1998.7247 | 456 | 0.18992 | 27.5378 | 370 | 1.72 | 648
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | CB | FALSE | 32077.0701 | 28146.4256 | 17.4931 | 170 | 9.0631e-05 | 1893 | 2204.8048 | 402 | 0.18973 | 32.2538 | 371 | 5.76 | 479
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 6512 | FALSE | 1047.7996 | 1047.7996 | 0.65121 | 5 | 6.0555e-05 | 2761 | 1094.509 | 777 | 0.18909 | 0.94545 | 372 | 0.08 | 1593
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 805882 | TRUE | 497.9369 | 477.3024 | 0.29665 | 6 | 0.00016012 | 642 | 1125.8811 | 766 | 0.18904 | 1.1343 | 373 |  | 3553
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 1228 | FALSE | 69440.241 | 17449.9174 | 10.8452 | 368 | 0.00011636 | 1263 | 1613.8231 | 557 | 0.18877 | 69.4681 | 374 | 0.04 | 2078
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 1580 | FALSE | 80785.153 | 76365.8976 | 47.4617 | 383 | 0.00012062 | 1174 | 1821.2183 | 501 | 0.18779 | 71.9249 | 375 | 0.11 | 1451
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 31500 | FALSE | 18887.7142 | 7501.4293 | 4.6622 | 111 | 5.0427e-05 | 3030 | 3238.0724 | 229 | 0.18759 | 20.823 | 376 | 0.02 | 2550
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 96224 | FALSE | 31213.3049 | 31213.3049 | 19.3992 | 174 | 6.6243e-05 | 2582 | 2944.2439 | 281 | 0.18755 | 32.6329 | 377 | 0.79 | 777
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | CB | FALSE | 47599.3495 | 47599.3495 | 29.5832 | 121 | 0.00014957 | 743 | 1075.8896 | 783 | 0.1873 | 22.6633 | 378 | 0.07 | 1739
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 37288 | FALSE | 137232.3506 | 137232.3506 | 85.2905 | 678 | 4.4383e-05 | 3179 | 4408.5685 | 114 | 0.18718 | 126.9051 | 379 | 0.6 | 850
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 885215 | FALSE | 3239.6899 | 3225.5678 | 2.0047 | 23 | 4.5966e-05 | 3138 | 3739.8152 | 178 | 0.18705 | 4.3021 | 380 |  | 3435
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 128 | FALSE | 60127.5406 | 56205.3694 | 34.9319 | 269 | 9.706e-05 | 1712 | 2077.9375 | 434 | 0.18687 | 50.2671 | 381 | 0.3 | 1014
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 69722 | FALSE | 10673.4289 | 10673.4289 | 6.6336 | 68 | 0.00014836 | 760 | 1483.0501 | 601 | 0.18675 | 12.6993 | 382 | 0.34 | 983
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 85132 | FALSE | 50093.0189 | 50093.0189 | 31.133 | 217 | 4.257e-05 | 3216 | 4662.7247 | 101 | 0.18633 | 40.4342 | 383 | 0.13 | 1354
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 48952 | FALSE | 17050.5619 | 17050.5619 | 10.597 | 123 | 0.00010175 | 1609 | 2266.9677 | 389 | 0.18561 | 22.8305 | 384 | 0.07 | 1722
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 212772 | FALSE | 1753.1585 | 1609.198 | 1.0001 | 11 | 0.00010227 | 1596 | 1767.7041 | 510 | 0.18554 | 2.041 | 385 |  | 3087
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 79788 | FALSE | 67378.0299 | 63661.5746 | 39.5659 | 157 | 0.00011886 | 1209 | 1546.745 | 582 | 0.18551 | 29.1256 | 386 | 0.12 | 1399
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 13052 | FALSE | 31493.7185 | 31480.1828 | 19.5651 | 213 | 9.5258e-05 | 1758 | 2083.3172 | 433 | 0.18514 | 39.4358 | 387 | 0.12 | 1398
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 795010 | FALSE | 6022.8068 | 5964.9276 | 3.7072 | 12 | 3.8042e-05 | 3300 | 5006.5635 | 76 | 0.18505 | 2.2206 | 388 |  | 3401
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 1550 | FALSE | 35703.4386 | 31009.474 | 19.2725 | 237 | 9.1451e-05 | 1860 | 2378.2716 | 365 | 0.18396 | 43.5983 | 389 | 0.06 | 1796
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 1556 | FALSE | 64601.0138 | 61930.0824 | 38.4898 | 411 | 5.2815e-05 | 2977 | 3779.2145 | 173 | 0.18357 | 75.4478 | 390 | 0.18 | 1205
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 365572 | TRUE | 696.8465 | 611.8589 | 0.38027 | 2 | 9.4733e-05 | 1772 | 2195.1828 | 403 | 0.18299 | 0.36597 | 391 |  | 3633
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | CB | FALSE | 24813.8274 | 24813.8274 | 15.4219 | 127 | 0.00010514 | 1517 | 1354.0744 | 662 | 0.18254 | 23.1832 | 392 | 0.07 | 1749
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 466348 | FALSE | 48812.3964 | 26039.2723 | 16.1835 | 294 | 9.3721e-05 | 1802 | 2063.8243 | 440 | 0.18223 | 53.5743 | 393 |  | 2838
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 35470 | FALSE | 40109.7772 | 33111.1919 | 20.5787 | 174 | 7.9998e-05 | 2205 | 2635.2321 | 323 | 0.18214 | 31.6926 | 394 | 1.26 | 692
2265 | BELL 1108CB | 152701108 | BELL 1108 | CB | TRUE | 9628.7582 | 0 | 0 | 83 | 0.00016581 | 584 | 955.774 | 856 | 0.18213 | 15.1167 | 395 | 0.04 | 2098
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 37476 | FALSE | 14076.4929 | 4231.6102 | 2.63 | 82 | 0.0001427 | 830 | 1332.1225 | 666 | 0.18107 | 14.8479 | 396 | 0.03 | 2366
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 12612 | FALSE | 32502.2662 | 31091.451 | 19.3235 | 195 | 7.8143e-05 | 2254 | 2667.8797 | 319 | 0.18095 | 35.2855 | 397 | 3.37 | 549
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 1510 | TRUE | 5333.1807 | 613.4018 | 0.38123 | 35 | 9.6024e-05 | 1728 | 1460.1171 | 611 | 0.18088 | 6.3309 | 398 | 0.5 | 894
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 641367 | FALSE | 63879.2901 | 63879.2901 | 39.7012 | 278 | 6.9782e-05 | 2482 | 2628.7284 | 324 | 0.18079 | 50.2607 | 399 |  | 3081
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | Y504R | FALSE | 18910.1435 | 18838.2347 | 11.708 | 112 | 7.2579e-05 | 2404 | 2414.4364 | 358 | 0.18021 | 20.1836 | 400 | 0.36 | 972
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 7060 | FALSE | 28760.1957 | 28760.1957 | 17.8746 | 162 | 4.1619e-05 | 3231 | 4251.992 | 132 | 0.18019 | 29.1914 | 401 | 0.05 | 2062
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 48268 | FALSE | 8165.6241 | 8152.5339 | 5.0668 | 30 | 2.8075e-05 | 3458 | 6541.9938 | 16 | 0.17977 | 5.3932 | 402 | 0.03 | 2409
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2757 | FALSE | 4222.897 | 4222.897 | 2.6245 | 16 | 7.3477e-05 | 2384 | 2563.9177 | 338 | 0.1791 | 2.8656 | 403 | 0.07 | 1748
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | R1817 | FALSE | 31029.2187 | 31029.2187 | 19.2848 | 145 | 3.1982e-05 | 3401 | 5976.6981 | 30 | 0.17888 | 25.9373 | 404 | 0.08 | 1648
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 7070 | FALSE | 28250.671 | 28250.671 | 17.5579 | 103 | 3.6129e-05 | 3333 | 5058.188 | 71 | 0.17873 | 18.4097 | 405 | 0.06 | 1902
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 890 | FALSE | 39539.8399 | 39211.6931 | 24.3702 | 203 | 0.00013749 | 903 | 1564.6167 | 573 | 0.17857 | 36.2505 | 406 | 0.6 | 852
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | CB | FALSE | 15262.2312 | 6326.3363 | 3.9318 | 97 | 0.0001432 | 823 | 1232.8613 | 712 | 0.1779 | 17.2565 | 407 | 0.04 | 2123
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 90730 | FALSE | 13402.9331 | 13402.9331 | 8.33 | 77 | 0.00022241 | 309 | 801.5027 | 942 | 0.17712 | 13.6383 | 408 | 0.07 | 1738
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | CB | FALSE | 1862.134 | 1862.134 | 1.1573 | 2 | 2.6503e-05 | 3479 | 5012.0663 | 75 | 0.17665 | 0.3533 | 409 | 0.11 | 1430
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | CB | FALSE | 3124.8792 | 3111.1631 | 1.9336 | 12 | 0.00016891 | 568 | 1033.5651 | 803 | 0.17607 | 2.1128 | 410 | 0.03 | 2391
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 89934 | FALSE | 8917.9013 | 8917.9013 | 5.5425 | 56 | 0.00022642 | 301 | 791.9341 | 950 | 0.17581 | 9.8455 | 411 | 0.04 | 2125
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 594 | FALSE | 23079.0447 | 23079.0447 | 14.3437 | 155 | 0.00011929 | 1200 | 1640.4713 | 546 | 0.17563 | 27.2219 | 412 | 0.16 | 1253
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 53184 | FALSE | 51204.6527 | 51204.6527 | 31.8239 | 123 | 4.4635e-05 | 3174 | 4517.1008 | 106 | 0.17544 | 21.5791 | 413 | 0.06 | 1844
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 208 | FALSE | 20077.9466 | 20077.9466 | 12.4785 | 95 | 9.3548e-05 | 1810 | 1783.8562 | 508 | 0.1754 | 16.663 | 414 | 11.75 | 382
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 2026 | FALSE | 10220.4249 | 10220.4249 | 6.352 | 26 | 0.00034659 | 95 | 363.8152 | 1347 | 0.17512 | 4.5532 | 415 | 0.84 | 768
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | CB | FALSE | 17435.9444 | 12032.4791 | 7.4782 | 60 | 6.3071e-05 | 2678 | 1838.5396 | 494 | 0.17499 | 10.4995 | 416 | 0.03 | 2401
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 3700 | FALSE | 29156.0449 | 29156.0449 | 18.1206 | 116 | 0.00013347 | 952 | 1560.5823 | 576 | 0.17472 | 20.2673 | 417 | 0.06 | 1905
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 710384 | FALSE | 15468.9282 | 8584.2298 | 5.3351 | 84 | 5.8195e-05 | 2830 | 3710.5415 | 182 | 0.17469 | 14.6739 | 418 |  | 2697
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 913400 | TRUE | 1667.834 | 172.3529 | 0.10712 | 14 | 0.00011832 | 1223 | 1563.2661 | 575 | 0.17457 | 2.444 | 419 |  | 3465
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 1690 | FALSE | 26217.8201 | 17377.7027 | 10.8003 | 77 | 0.0001954 | 415 | 901.067 | 883 | 0.17449 | 13.4358 | 420 | 7.44 | 444
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 10090 | FALSE | 70938.5406 | 70938.5406 | 44.0886 | 435 | 5.7014e-05 | 2861 | 3810.3636 | 167 | 0.17437 | 75.8506 | 421 | 0.3 | 1021
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | CB | FALSE | 4580.4088 | 3639.3631 | 2.2619 | 17 | 0.00012727 | 1059 | 1563.9973 | 574 | 0.1743 | 2.9631 | 422 |  | 3230
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 323962 | FALSE | 46007.9913 | 33116.5425 | 20.5821 | 282 | 7.3879e-05 | 2363 | 2674.5475 | 317 | 0.17389 | 49.0357 | 423 | 22.52 | 293
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 51476 | FALSE | 10437.2128 | 7926.327 | 4.9262 | 74 | 9.4268e-05 | 1787 | 2122.2216 | 419 | 0.1736 | 12.8462 | 424 | 14.32 | 355
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | N64 | FALSE | 20207.5385 | 17721.3198 | 11.0139 | 101 | 0.00011489 | 1302 | 1611.5581 | 558 | 0.17314 | 17.4874 | 425 | 0.05 | 2025
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 1217 | FALSE | 27736.9205 | 22843.3853 | 14.1973 | 116 | 5.896e-05 | 2808 | 3212.896 | 236 | 0.17295 | 20.0623 | 426 | 2.25 | 617
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 673618 | TRUE | 533.16 | 171.3788 | 0.10651 | 4 | 5.0101e-05 | 3035 | 3451.8103 | 207 | 0.17294 | 0.69175 | 427 |  | 3547
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 35244 | FALSE | 28098.7686 | 28098.7686 | 17.4635 | 146 | 7.6076e-05 | 2306 | 1918.8043 | 468 | 0.17286 | 25.237 | 428 | 0.1 | 1464
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 1960 | FALSE | 39696.7204 | 39696.7204 | 24.6717 | 223 | 4.465e-05 | 3171 | 4411.9471 | 113 | 0.17242 | 38.4488 | 429 | 0.42 | 933
7293 | WISE 11022234 | 152271102 | WISE 1102 | 2234 | FALSE | 24349.9914 | 24349.9914 | 15.1336 | 179 | 8.3357e-05 | 2123 | 2208.9033 | 401 | 0.17198 | 30.784 | 430 | 1.04 | 723
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 421412 | FALSE | 5653.9032 | 1616.3093 | 1.0045 | 38 | 0.00012063 | 1173 | 1137.8972 | 758 | 0.17127 | 6.5083 | 431 |  | 3003
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 9722 | FALSE | 7647.7388 | 5139.2872 | 3.1941 | 55 | 9.2715e-05 | 1828 | 2011.1796 | 454 | 0.17084 | 9.3959 | 432 | 2.06 | 625
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 10570 | FALSE | 15440.8056 | 15440.8056 | 9.5965 | 92 | 5.2246e-05 | 2985 | 3374.5233 | 214 | 0.17053 | 15.6885 | 433 | 0.28 | 1043
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | N42 | FALSE | 9607.0794 | 5997.3144 | 3.7274 | 30 | 9.7321e-05 | 1705 | 2091.1209 | 429 | 0.17017 | 5.105 | 434 | 0 | 2631
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 221165 | FALSE | 7814.4254 | 7056.9288 | 4.3859 | 39 | 7.1264e-05 | 2439 | 2286.9555 | 387 | 0.17016 | 6.6364 | 435 |  | 2797
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 13372 | FALSE | 6191.0561 | 6152.1597 | 3.8236 | 5 | 3.5403e-05 | 3342 | 4181.8896 | 139 | 0.17014 | 0.85069 | 436 | 1.32 | 686
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 9072 | FALSE | 46343.9208 | 46343.9208 | 28.8029 | 279 | 4.9258e-05 | 3057 | 3602.3143 | 190 | 0.1698 | 47.3736 | 437 | 4.2 | 524
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 334476 | TRUE | 102.0354 | 89.9428 | 0.0559 | 2 | 3.6826e-05 | 3318 | 3174.6241 | 245 | 0.16961 | 0.33922 | 438 |  | 3587
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 658 | FALSE | 21722.426 | 4561.1197 | 2.8348 | 136 | 9.6216e-05 | 1727 | 1846.2822 | 492 | 0.16943 | 23.042 | 439 | 0.53 | 882
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 520 | FALSE | 75123.246 | 75123.246 | 46.6894 | 437 | 8.2363e-05 | 2144 | 2644.041 | 320 | 0.16915 | 73.9165 | 440 | 35.85 | 210
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | CB | FALSE | 33441.4577 | 25226.3338 | 15.6783 | 190 | 6.5983e-05 | 2589 | 2246.0111 | 394 | 0.16908 | 32.1248 | 441 | 5.92 | 477
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | X10 | FALSE | 70912.2192 | 34475.596 | 21.4267 | 156 | 7.3071e-05 | 2393 | 2615.2408 | 327 | 0.16893 | 26.3532 | 442 | 0 | 2634
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 51794 | FALSE | 6308.4167 | 6303.8446 | 3.9179 | 32 | 0.00021523 | 339 | 651.61 | 1061 | 0.16883 | 5.4026 | 443 | 0.05 | 1924
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | XR564 | FALSE | 11653.8006 | 9126.8572 | 5.6724 | 81 | 0.0001173 | 1241 | 1539.4612 | 583 | 0.16792 | 13.6018 | 444 | 0.06 | 1891
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 6090 | TRUE | 1284.821 | 879.5421 | 0.54664 | 10 | 0.00015776 | 667 | 641.9698 | 1070 | 0.16726 | 1.6726 | 445 | 0.04 | 2133
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 82846 | FALSE | 8140.1207 | 7626.8316 | 4.7401 | 61 | 4.657e-05 | 3125 | 3781.4967 | 171 | 0.16626 | 10.1421 | 446 | 0.09 | 1543
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 2228 | FALSE | 34201.7241 | 33727.1471 | 20.9616 | 199 | 0.0001094 | 1423 | 1826.2902 | 498 | 0.16595 | 33.0243 | 447 | 0.19 | 1187
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 117616 | TRUE | 584.7856 | 298.3487 | 0.18542 | 5 | 0.00010782 | 1453 | 3364.4337 | 215 | 0.16564 | 0.82819 | 448 |  | 3494
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 772792 | FALSE | 4440.4408 | 3782.0495 | 2.3506 | 19 | 0.00011586 | 1274 | 1705.2974 | 522 | 0.16509 | 3.1366 | 449 |  | 3485
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 439572 | FALSE | 2069.8545 | 1977.3978 | 1.229 | 18 | 0.00012277 | 1136 | 1750.9686 | 514 | 0.16479 | 2.9663 | 450 |  | 3004
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | TS1115 | FALSE | 28340.5083 | 28340.5083 | 17.6137 | 147 | 6.6142e-05 | 2584 | 2220.2472 | 396 | 0.16462 | 24.1996 | 451 | 0.06 | 1872
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 514412 | FALSE | 1675.5188 | 1659.5168 | 1.0314 | 5 | 8.0594e-05 | 2190 | 2318.4458 | 382 | 0.16405 | 0.82024 | 452 |  | 3090
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 226562 | FALSE | 1660.7794 | 1371.9928 | 0.8527 | 7 | 8.6131e-05 | 2031 | 1632.6529 | 550 | 0.16403 | 1.1482 | 453 |  | 3116
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 98896 | FALSE | 8090.5275 | 8090.5275 | 5.0283 | 25 | 7.975e-05 | 2213 | 2478.9758 | 348 | 0.16402 | 4.1004 | 454 | 0.04 | 2181
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | CB | FALSE | 19101.7778 | 10648.1095 | 6.6178 | 143 | 0.00016037 | 641 | 1368.6904 | 653 | 0.16378 | 23.42 | 455 | 0.24 | 1101
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 48480 | FALSE | 16927.9852 | 16927.9852 | 10.5208 | 125 | 0.00013445 | 937 | 1828.9756 | 497 | 0.16355 | 20.4433 | 456 | 0.7 | 806
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 915324 | FALSE | 5487.5306 | 3584.8296 | 2.228 | 27 | 4.7601e-05 | 3097 | 3729.4821 | 179 | 0.16319 | 4.406 | 457 |  | 3321
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 530 | FALSE | 17644.1656 | 17644.1656 | 10.9659 | 23 | 0.00014892 | 752 | 1687.6433 | 526 | 0.16273 | 3.7427 | 458 | 0.71 | 801
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 561208 | FALSE | 4547.6852 | 1347.5454 | 0.8375 | 15 | 0.0001103 | 1407 | 1867.3968 | 484 | 0.1626 | 2.439 | 459 |  | 3487
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 94006 | FALSE | 24566.5609 | 22341.6897 | 13.8855 | 112 | 0.00010255 | 1585 | 1667.7925 | 536 | 0.1626 | 18.2107 | 460 | 0.05 | 1968
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | CB | FALSE | 19725.7628 | 17048.207 | 10.5955 | 144 | 0.00010337 | 1563 | 1745.3469 | 516 | 0.16238 | 23.3827 | 461 | 0.11 | 1421
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | CB | TRUE | 3.6129 | 3.6129 | 0.0022454 | 1 | 3.2861e-05 | 3387 | 4925.3659 | 82 | 0.16185 | 0.16185 | 462 |  | 3620
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 34069 | FALSE | 25331.8473 | 25331.8473 | 15.7438 | 156 | 6.2676e-05 | 2694 | 2622.4246 | 326 | 0.16138 | 25.1758 | 463 | 0.09 | 1525
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 98680 | TRUE | 46.5973 | 46.5973 | 0.02896 | 1 | 7.2821e-05 | 2397 | 2215.7621 | 399 | 0.16135 | 0.16135 | 464 |  | 3628
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 1752 | FALSE | 16018.6134 | 13551.3973 | 8.4222 | 96 | 9.1598e-05 | 1854 | 2012.9288 | 453 | 0.16096 | 15.4521 | 465 | 0.04 | 2161
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 37498 | FALSE | 26197.7415 | 26197.7415 | 16.282 | 129 | 0.00018072 | 507 | 890.6369 | 887 | 0.16073 | 20.7336 | 466 | 0.07 | 1723
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 7203 | FALSE | 30305.2229 | 29904.6733 | 18.5859 | 197 | 9.5139e-05 | 1761 | 1859.3118 | 489 | 0.16043 | 31.6051 | 467 | 0.19 | 1194
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 48212 | FALSE | 17385.8137 | 17215.2669 | 10.6994 | 110 | 0.00014482 | 804 | 1204.0224 | 729 | 0.1603 | 17.6327 | 468 | 18.57 | 319
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 605393 | FALSE | 40299.6716 | 33375.8865 | 20.7432 | 119 | 6.0131e-05 | 2768 | 2777.2648 | 302 | 0.15998 | 19.0373 | 469 |  | 2710
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 1610 | FALSE | 61821.9357 | 61821.9357 | 38.4226 | 295 | 4.3413e-05 | 3203 | 3907.4677 | 156 | 0.15996 | 47.1875 | 470 | 0.13 | 1340
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 428314 | FALSE | 29650.5939 | 23673.0872 | 14.7129 | 73 | 6.2949e-05 | 2680 | 2640.9062 | 321 | 0.15993 | 11.675 | 471 |  | 2732
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 592404 | FALSE | 2658.3381 | 2642.3361 | 1.6422 | 20 | 0.00017009 | 563 | 1297.0483 | 685 | 0.15963 | 3.1926 | 472 |  | 3024
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 38438 | FALSE | 27128.309 | 27128.309 | 16.8604 | 181 | 9.156e-05 | 1855 | 1679.673 | 529 | 0.15947 | 28.8637 | 473 | 0.08 | 1665
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 548 | FALSE | 45554.629 | 44099.7789 | 27.4082 | 298 | 0.00022053 | 318 | 593.8352 | 1108 | 0.15935 | 47.4878 | 474 | 94.8 | 26
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 8721 | FALSE | 4901.8588 | 4400.8399 | 2.7351 | 29 | 5.0888e-05 | 3017 | 2918.1731 | 285 | 0.1593 | 4.6198 | 475 | 0.04 | 2186
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 51238 | FALSE | 63137.7388 | 63137.7388 | 39.2404 | 335 | 5.1642e-05 | 3004 | 2984.3431 | 269 | 0.15926 | 53.3509 | 476 | 2.31 | 614
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 84088 | FALSE | 28026.8017 | 25963.7603 | 16.1366 | 127 | 0.00012489 | 1101 | 1457.8018 | 614 | 0.15858 | 20.1391 | 477 |  | 2748
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 428534 | FALSE | 8740.0932 | 7301.7326 | 4.5381 | 18 | 6.0557e-05 | 2760 | 3052.7595 | 263 | 0.15819 | 2.8474 | 478 |  | 2880
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 964556 | FALSE | 8160.0956 | 8116.5647 | 5.0445 | 31 | 0.00010503 | 1527 | 1599.6673 | 562 | 0.15803 | 4.8988 | 479 |  | 3279
7447 | BELL 1109CB | 152701109 | BELL 1109 | CB | TRUE | 5601.5402 | 484.8416 | 0.30133 | 53 | 0.00031144 | 116 | 533.425 | 1167 | 0.15794 | 8.3708 | 480 | 0.06 | 1805
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 24918 | FALSE | 8843.8557 | 8843.8557 | 5.4965 | 49 | 0.00017491 | 529 | 1042.2333 | 799 | 0.1575 | 7.7177 | 481 | 40.7 | 183
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 705777 | FALSE | 9890.0744 | 9890.0744 | 6.1467 | 46 | 0.00010551 | 1505 | 1615.1994 | 555 | 0.15746 | 7.2434 | 482 |  | 3062
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 542 | FALSE | 54014.7834 | 53958.2006 | 33.5352 | 311 | 0.00010864 | 1433 | 1525.8914 | 585 | 0.15746 | 48.9707 | 483 | 0.08 | 1662
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | CB | FALSE | 10535.3716 | 10535.3716 | 6.5478 | 40 | 5.8247e-05 | 2827 | 2851.4073 | 292 | 0.15705 | 6.2822 | 484 | 0.03 | 2244
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 383183 | FALSE | 23681.1054 | 23566.6207 | 14.6467 | 53 | 0.0001153 | 1293 | 1780.7074 | 509 | 0.15687 | 8.3141 | 485 |  | 3164
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 152632 | FALSE | 3427.183 | 3099.3949 | 1.9263 | 13 | 5.6437e-05 | 2875 | 2775.5237 | 304 | 0.15681 | 2.0385 | 486 |  | 3200
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 1456 | FALSE | 6155.4627 | 6155.4627 | 3.8256 | 46 | 0.00024152 | 242 | 701.6004 | 1021 | 0.15596 | 7.1739 | 487 | 25.79 | 270
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 5104 | FALSE | 2898.3737 | 2898.3737 | 1.8014 | 11 | 0.00010952 | 1422 | 1407.1508 | 634 | 0.15579 | 1.7137 | 488 | 0.08 | 1654
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 79306 | FALSE | 13157.0108 | 6087.9659 | 3.7837 | 73 | 0.00011173 | 1374 | 1345.2863 | 664 | 0.15551 | 11.352 | 489 | 5.6 | 482
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | R372 | FALSE | 6703.9319 | 6703.9319 | 4.1665 | 14 | 2.9441e-05 | 3432 | 4227.7566 | 136 | 0.15539 | 2.1754 | 490 | 0 | 2626
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 869946 | FALSE | 47850.9 | 47850.9 | 29.7395 | 197 | 2.1689e-05 | 3527 | 7360.2383 | 8 | 0.15534 | 30.6024 | 491 | 4.76 | 507
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 946229 | TRUE | 3345.1938 | 352.3912 | 0.21901 | 27 | 9.1153e-05 | 1875 | 1903.3963 | 476 | 0.15489 | 4.1819 | 492 |  | 3308
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | CB | TRUE | 33.3215 | 28.7495 | 0.017868 | 2 | 0.00010268 | 1578 | 1672.4211 | 534 | 0.15464 | 0.30929 | 493 |  | 3632
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 19502 | FALSE | 92686.5675 | 72356.9682 | 44.9701 | 672 | 0.00010455 | 1541 | 1716.1429 | 520 | 0.15447 | 103.8019 | 494 | 25.98 | 269
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | CB | FALSE | 15673.7726 | 8550.61 | 5.3142 | 114 | 0.00011244 | 1357 | 1000.9631 | 834 | 0.15412 | 17.5695 | 495 | 0.03 | 2253
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 408 | FALSE | 61335.3992 | 60046.2209 | 37.319 | 280 | 0.00011339 | 1336 | 1624.3846 | 553 | 0.15401 | 43.1236 | 496 | 0.16 | 1258
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 7420 | FALSE | 37320.8645 | 37320.8645 | 23.1951 | 263 | 2.746e-05 | 3465 | 5752.6874 | 39 | 0.15397 | 40.4954 | 497 | 0.11 | 1450
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 88998 | FALSE | 22218.0314 | 12794.9324 | 7.9521 | 116 | 8.749e-05 | 2000 | 1675.3538 | 531 | 0.15352 | 17.8079 | 498 | 12.75 | 368
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 942170 | FALSE | 14564.2628 | 5038.647 | 3.1315 | 99 | 8.0364e-05 | 2195 | 1848.528 | 490 | 0.15348 | 15.1945 | 499 |  | 2892
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | CB | FALSE | 19525.0238 | 11777.3852 | 7.3197 | 154 | 0.00010262 | 1582 | 1549.2867 | 579 | 0.15336 | 23.6178 | 500 | 0.1 | 1453
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | Y52 | FALSE | 33466.442 | 31529.2091 | 19.5955 | 141 | 6.2219e-05 | 2713 | 2469.9036 | 349 | 0.15332 | 21.6184 | 501 | 0.22 | 1124
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | CB | FALSE | 40316.4241 | 40301.3395 | 25.0474 | 275 | 0.00012985 | 1011 | 1360.5287 | 658 | 0.15318 | 42.1242 | 502 | 0.14 | 1317
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 9480 | FALSE | 19971.3977 | 19971.3977 | 12.4123 | 80 | 7.4134e-05 | 2352 | 2457.1272 | 350 | 0.15314 | 12.251 | 503 | 0.05 | 1946
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 1573 | FALSE | 29066.997 | 29066.997 | 18.0653 | 156 | 6.9197e-05 | 2500 | 1984.6936 | 458 | 0.15282 | 23.8402 | 504 | 0.09 | 1514
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 2220 | FALSE | 45533.9477 | 44226.4373 | 27.4869 | 266 | 0.00015667 | 676 | 1115.795 | 768 | 0.15235 | 40.5244 | 505 | 0.28 | 1037
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 287172 | FALSE | 42975.8424 | 32888.5181 | 20.4403 | 258 | 0.00014341 | 820 | 1064.6586 | 789 | 0.15216 | 39.2578 | 506 | 0.11 | 1432
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 2012 | FALSE | 16177.0749 | 14813.8509 | 9.2069 | 64 | 7.8985e-05 | 2236 | 2049.1767 | 445 | 0.15189 | 9.7211 | 507 | 0.03 | 2261
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | N48 | FALSE | 76703.6711 | 76703.6711 | 47.6716 | 292 | 5.999e-05 | 2778 | 2624.8703 | 325 | 0.15188 | 44.3489 | 508 | 0.11 | 1419
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 301886 | FALSE | 12466.9499 | 4239.6365 | 2.635 | 90 | 8.8332e-05 | 1976 | 1844.2972 | 493 | 0.15165 | 13.6484 | 509 |  | 3073
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | N04 | TRUE | 859.5841 | 859.5841 | 0.53424 | 4 | 0.00013464 | 932 | 1420.9296 | 631 | 0.1516 | 0.60641 | 510 | 10.35 | 398
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 701650 | FALSE | 1191.0562 | 1191.0562 | 0.74025 | 12 | 0.00018462 | 478 | 500.0347 | 1199 | 0.15159 | 1.8191 | 511 |  | 3496
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 1280 | FALSE | 37796.6985 | 12933.8174 | 8.0384 | 238 | 0.00011562 | 1283 | 1326.8732 | 670 | 0.1512 | 35.9845 | 512 | 0.03 | 2282
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 14026 | FALSE | 16308.5206 | 16308.5206 | 10.1358 | 101 | 6.4324e-05 | 2633 | 2347.8148 | 374 | 0.15084 | 15.2344 | 513 | 3.03 | 567
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 42344 | FALSE | 17541.9825 | 15185.6709 | 9.438 | 123 | 6.005e-05 | 2772 | 2518.1117 | 341 | 0.15077 | 18.5441 | 514 | 5.29 | 491
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 748272 | FALSE | 6311.5498 | 1206.1255 | 0.74961 | 26 | 6.9164e-05 | 2501 | 2825.842 | 296 | 0.15028 | 3.9074 | 515 |  | 3317
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 618 | FALSE | 17470.7407 | 13890.2601 | 8.6329 | 119 | 8.8705e-05 | 1961 | 1646.4565 | 544 | 0.15 | 17.8498 | 516 | 3.18 | 555
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | Y26 | FALSE | 25494.2608 | 24411.1885 | 15.1717 | 133 | 6.226e-05 | 2711 | 2408.6488 | 359 | 0.14946 | 19.8785 | 517 | 0.08 | 1586
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 37374 | FALSE | 3616.7474 | 3616.7474 | 2.2478 | 9 | 0.00024971 | 217 | 652.1813 | 1060 | 0.14938 | 1.3444 | 518 | 10.97 | 392
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 4522 | FALSE | 19482.3353 | 14178.9489 | 8.8123 | 128 | 0.00013265 | 968 | 1211.0142 | 727 | 0.14919 | 19.0963 | 519 | 1.62 | 661
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 51792 | FALSE | 15055.1772 | 15055.1772 | 9.3569 | 99 | 0.00012104 | 1164 | 1431.6373 | 622 | 0.14914 | 14.7646 | 520 | 0.08 | 1632
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | Y48 | FALSE | 19054.6896 | 7064.3192 | 4.3905 | 157 | 6.9914e-05 | 2475 | 2423.7326 | 357 | 0.14907 | 23.4041 | 521 | 0.03 | 2278
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 1604 | FALSE | 29168.7634 | 6733.9297 | 4.1852 | 166 | 0.00022087 | 316 | 698.8592 | 1023 | 0.14905 | 24.7419 | 522 | 0.05 | 1969
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 537148 | TRUE | 2468.9992 | 923.0762 | 0.5737 | 14 | 8.9697e-05 | 1921 | 711.3098 | 1014 | 0.14902 | 2.0863 | 523 |  | 3541
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 2180 | FALSE | 71112.0664 | 71112.0664 | 44.1964 | 444 | 8.9044e-05 | 1947 | 1832.2635 | 495 | 0.1487 | 66.0238 | 524 | 0.31 | 1000
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 2181 | FALSE | 38165.6009 | 27116.6383 | 16.8531 | 120 | 3.7006e-05 | 3315 | 4260.274 | 131 | 0.14869 | 17.8426 | 525 | 0.05 | 2017
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 2044 | FALSE | 20271.6961 | 13688.923 | 8.5077 | 67 | 0.00011519 | 1295 | 1533.5317 | 584 | 0.14865 | 9.9595 | 526 | 0.03 | 2330
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 87352 | FALSE | 42830.7404 | 42830.7404 | 26.6195 | 215 | 7.6529e-05 | 2294 | 2120.5795 | 420 | 0.14862 | 31.9523 | 527 | 0.03 | 2333
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 307494 | FALSE | 54418.6325 | 49958.7477 | 31.0496 | 279 | 7.0522e-05 | 2454 | 2167.8038 | 409 | 0.14841 | 41.4062 | 528 | 3.66 | 537
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 64044 | FALSE | 11992.1979 | 9649.0485 | 5.9969 | 46 | 6.4018e-05 | 2645 | 2318.9503 | 380 | 0.14834 | 6.8236 | 529 | 0.92 | 747
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 12249 | FALSE | 3869.5175 | 3869.5175 | 2.4049 | 25 | 0.0001396 | 877 | 1383.6803 | 645 | 0.14826 | 3.7065 | 530 | 0.06 | 1811
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 11206 | FALSE | 28786.4552 | 28782.1678 | 17.8882 | 146 | 5.7399e-05 | 2853 | 3353.7714 | 217 | 0.14787 | 21.5893 | 531 | 7.09 | 451
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 80454 | FALSE | 51836.245 | 51220.5161 | 31.8338 | 254 | 8.7906e-05 | 1985 | 1652.3048 | 542 | 0.14786 | 37.5574 | 532 | 0.09 | 1550
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 196 | FALSE | 11699.1957 | 9030.0657 | 5.6122 | 36 | 5.8544e-05 | 2820 | 2429.7049 | 356 | 0.14755 | 5.3118 | 533 | 1.88 | 635
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 66006 | FALSE | 14550.7056 | 14550.7056 | 9.0433 | 98 | 0.00016119 | 629 | 1078.2399 | 782 | 0.14747 | 14.4519 | 534 | 51.49 | 116
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | CB | FALSE | 14152.8775 | 11300.0596 | 7.023 | 87 | 0.00030831 | 120 | 452.1633 | 1245 | 0.14742 | 12.8257 | 535 | 0.09 | 1511
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 1026 | FALSE | 44906.7347 | 36171.5421 | 22.4808 | 273 | 7.2065e-05 | 2414 | 2265.0826 | 390 | 0.14732 | 40.2177 | 536 | 0.08 | 1587
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 10110 | FALSE | 79840.1784 | 79840.1784 | 49.621 | 518 | 7.1892e-05 | 2423 | 1946.3474 | 464 | 0.1471 | 76.1986 | 537 | 0.85 | 766
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 1636 | FALSE | 29887.6303 | 29071.18 | 18.0679 | 200 | 0.00012911 | 1025 | 1282.4693 | 688 | 0.14693 | 29.387 | 538 | 0.42 | 935
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | N40 | FALSE | 4749.4542 | 4628.046 | 2.8763 | 23 | 7.224e-05 | 2412 | 1911.8815 | 472 | 0.14681 | 3.3766 | 539 | 0.92 | 746
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 1348 | FALSE | 51267.8367 | 46964.6472 | 29.1887 | 357 | 6.4485e-05 | 2628 | 2847.109 | 293 | 0.14666 | 52.3583 | 540 | 0.1 | 1507
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 5490 | FALSE | 40241.3391 | 40241.3391 | 25.0102 | 276 | 5.4815e-05 | 2921 | 3287.8025 | 227 | 0.14657 | 40.4521 | 541 | 31.17 | 233
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 239062 | FALSE | 22613.4239 | 19618.6008 | 12.193 | 113 | 7.6414e-05 | 2296 | 2401.1977 | 361 | 0.14634 | 16.5367 | 542 |  | 3021
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 68436 | FALSE | 14664.9715 | 14664.9715 | 9.1143 | 45 | 0.00011581 | 1278 | 1690.836 | 525 | 0.14627 | 6.582 | 543 | 3.52 | 544
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 2010 | FALSE | 10727.9171 | 10727.9171 | 6.6674 | 39 | 0.00053737 | 26 | 277.3564 | 1477 | 0.14585 | 5.6882 | 544 | 0.08 | 1579
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 19762 | FALSE | 8713.8007 | 7078.7756 | 4.3995 | 72 | 0.00017135 | 554 | 1134.0874 | 762 | 0.14549 | 10.4755 | 545 | 0.25 | 1082
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 2008 | FALSE | 29196.2282 | 9225.9589 | 5.734 | 154 | 5.6038e-05 | 2886 | 2966.3445 | 274 | 0.14517 | 22.3567 | 546 | 2.46 | 601
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | N44 | FALSE | 29207.7388 | 29207.7388 | 18.1527 | 109 | 8.2092e-05 | 2149 | 1862.5151 | 486 | 0.14496 | 15.8008 | 547 | 0.19 | 1171
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 1102 | FALSE | 69889.6015 | 69889.6015 | 43.4367 | 431 | 0.00010803 | 1451 | 1375.9559 | 650 | 0.14479 | 62.4048 | 548 | 0.21 | 1154
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 64090 | FALSE | 21993.72 | 21993.72 | 13.6692 | 170 | 4.4336e-05 | 3181 | 3248.9701 | 228 | 0.1444 | 24.5486 | 549 | 4.94 | 501
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 1268 | FALSE | 17550.3384 | 17538.5447 | 10.9003 | 106 | 8.5846e-05 | 2035 | 1744.856 | 517 | 0.14435 | 15.3013 | 550 | 0.13 | 1351
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 9590 | FALSE | 58387.0707 | 58387.0707 | 36.2878 | 387 | 6.1765e-05 | 2727 | 2433.9636 | 353 | 0.144 | 55.7277 | 551 | 0.28 | 1045
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | A60 | FALSE | 14423.3233 | 11709.0954 | 7.2773 | 88 | 8.0147e-05 | 2202 | 2043.3402 | 447 | 0.14391 | 12.6644 | 552 | 1.69 | 651
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 429006 | FALSE | 3229.4467 | 3213.4446 | 1.9972 | 23 | 0.00015434 | 701 | 805.9602 | 934 | 0.1436 | 3.3029 | 553 | 0.04 | 2192
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 1578 | FALSE | 56424.6884 | 48498.4276 | 30.142 | 269 | 5.3137e-05 | 2963 | 2721.7009 | 308 | 0.14355 | 38.6147 | 554 | 0.07 | 1761
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | CB | FALSE | 20557.4413 | 20557.4413 | 12.7765 | 85 | 0.0001276 | 1055 | 1467.6776 | 609 | 0.14347 | 12.1951 | 555 | 0.15 | 1305
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 1448 | FALSE | 49484.9793 | 49484.9793 | 30.7551 | 232 | 9.5357e-05 | 1749 | 1437.1719 | 620 | 0.14347 | 33.2848 | 556 | 0.06 | 1912
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 37384 | FALSE | 15082.1187 | 15082.1187 | 9.3736 | 71 | 6.7163e-05 | 2554 | 2257.655 | 391 | 0.14324 | 10.17 | 557 | 0.13 | 1350
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 3990 | FALSE | 8945.4958 | 6963.5326 | 4.3279 | 25 | 3.4486e-05 | 3361 | 3780.3852 | 172 | 0.14297 | 3.5744 | 558 | 0.05 | 1957
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 636 | FALSE | 15178.9816 | 15178.9816 | 9.4338 | 108 | 0.00010078 | 1628 | 1486.0094 | 600 | 0.14279 | 15.4213 | 559 | 5.46 | 486
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 65764 | FALSE | 16669.4005 | 16669.4005 | 10.3601 | 34 | 4.7811e-05 | 3096 | 3350.0688 | 218 | 0.1423 | 4.8382 | 560 | 0.03 | 2268
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 189488 | FALSE | 1343.2605 | 1327.2585 | 0.8249 | 8 | 2.6518e-05 | 3478 | 5673.1262 | 44 | 0.14211 | 1.1369 | 561 |  | 3556
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | Y12 | FALSE | 49636.2362 | 42701.7878 | 26.5393 | 274 | 4.9026e-05 | 3063 | 2917.17 | 286 | 0.14205 | 38.9225 | 562 | 31.53 | 230
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 451856 | TRUE | 105.147 | 105.147 | 0.065349 | 2 | 5.0483e-05 | 3022 | 2807.0375 | 299 | 0.14172 | 0.28345 | 563 |  | 3442
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 6392 | FALSE | 8838.9848 | 8838.9848 | 5.4935 | 37 | 7.9657e-05 | 2215 | 1801.3357 | 505 | 0.14162 | 5.2399 | 564 | 16.9 | 336
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 242919 | FALSE | 2111.493 | 2111.493 | 1.3123 | 15 | 0.00019735 | 407 | 815.191 | 928 | 0.14151 | 2.1226 | 565 |  | 2911
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | CB | FALSE | 14807.5224 | 14807.5224 | 9.2029 | 54 | 0.00019854 | 400 | 804.6312 | 935 | 0.14139 | 7.6353 | 566 | 0.07 | 1742
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | M54 | FALSE | 48740.6445 | 31884.2274 | 19.8162 | 166 | 5.3034e-05 | 2966 | 2348.1035 | 373 | 0.14114 | 23.4289 | 567 | 0.02 | 2478
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 2070 | FALSE | 46879.1188 | 28951.6433 | 17.9936 | 303 | 7.9201e-05 | 2227 | 1863.8372 | 485 | 0.14111 | 42.7554 | 568 | 2.76 | 584
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | CB | FALSE | 1579.2012 | 1277.3495 | 0.79388 | 11 | 0.0001171 | 1244 | 1362.5146 | 655 | 0.14108 | 1.5519 | 569 | 0.61 | 848
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 746082 | FALSE | 1306.1318 | 1306.1318 | 0.81177 | 6 | 0.00011547 | 1287 | 1442.5612 | 617 | 0.14016 | 0.84097 | 570 | 0.11 | 1442
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 4650 | FALSE | 9890.161 | 6190.488 | 3.8474 | 80 | 0.0001146 | 1305 | 915.7398 | 878 | 0.14007 | 11.2058 | 571 | 0.03 | 2344
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 1616 | FALSE | 79228.8196 | 75536.2374 | 46.9461 | 454 | 5.1839e-05 | 2998 | 2965.2949 | 276 | 0.13915 | 63.1735 | 572 | 3.66 | 538
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 4456 | FALSE | 37862.2156 | 37862.2156 | 23.5315 | 102 | 2.7821e-05 | 3462 | 5239.6007 | 58 | 0.13881 | 14.1582 | 573 | 0.11 | 1440
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 2502 | FALSE | 28650.0789 | 28650.0789 | 17.8061 | 80 | 0.00011917 | 1201 | 1243.1177 | 705 | 0.13859 | 11.0874 | 574 | 0.04 | 2183
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 4160 | FALSE | 36723.9834 | 36723.9834 | 22.8241 | 192 | 7.1016e-05 | 2443 | 2062.9169 | 441 | 0.13839 | 26.57 | 575 | 0.07 | 1759
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 152874 | TRUE | 1306.3422 | 982.3028 | 0.61051 | 10 | 6.4919e-05 | 2611 | 2044.3409 | 446 | 0.13803 | 1.3803 | 576 |  | 3483
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 186060 | FALSE | 24068.765 | 17542.5963 | 10.9028 | 161 | 0.00011716 | 1242 | 1235.1524 | 709 | 0.13732 | 22.1085 | 577 |  | 2791
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 2679 | FALSE | 11435.2637 | 11435.2637 | 7.1071 | 70 | 6.4611e-05 | 2619 | 2176.5839 | 406 | 0.13732 | 9.6123 | 578 | 23.85 | 281
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 34959 | FALSE | 42625.8356 | 41473.2756 | 25.7758 | 205 | 7.1759e-05 | 2428 | 1907.4668 | 473 | 0.13657 | 27.9958 | 579 | 0.46 | 910
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 1516 | FALSE | 41402.7558 | 40856.6045 | 25.3925 | 123 | 9.2444e-05 | 1832 | 1638.3577 | 549 | 0.13616 | 16.7471 | 580 | 0.06 | 1821
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 11300 | FALSE | 5912.6947 | 5912.6947 | 3.6748 | 41 | 0.00013924 | 881 | 1480.6406 | 604 | 0.1361 | 5.5803 | 581 | 0.19 | 1177
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 51582 | FALSE | 15330.2671 | 15330.2671 | 9.5278 | 105 | 0.00014185 | 842 | 981.2465 | 843 | 0.13574 | 14.2523 | 582 | 0.04 | 2150
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 732836 | FALSE | 24952.5776 | 18788.6293 | 11.6772 | 154 | 4.1312e-05 | 3239 | 3303.5879 | 224 | 0.1353 | 20.8364 | 583 |  | 2673
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 720 | FALSE | 13087.7745 | 10923.6575 | 6.7891 | 70 | 6.3429e-05 | 2663 | 2299.4316 | 384 | 0.1353 | 9.4707 | 584 | 2.79 | 580
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 4230 | FALSE | 36923.3874 | 36847.6248 | 22.9009 | 59 | 0.00036561 | 80 | 373.6796 | 1331 | 0.13512 | 7.9721 | 585 | 0.02 | 2536
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 13352 | FALSE | 58907.8743 | 55896.819 | 34.7401 | 409 | 0.00012489 | 1100 | 1100.974 | 774 | 0.13486 | 55.1568 | 586 | 30.41 | 238
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 594143 | TRUE | 6633.044 | 814.5641 | 0.50625 | 60 | 9.5762e-05 | 1734 | 729.5737 | 990 | 0.13461 | 8.0769 | 587 |  | 3123
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 406 | FALSE | 53036.2911 | 19984.6537 | 12.4205 | 312 | 8.8388e-05 | 1975 | 1508.2873 | 594 | 0.1343 | 41.9011 | 588 | 0.13 | 1362
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 7849F | FALSE | 13949.6344 | 13949.6344 | 8.6698 | 61 | 3.1633e-05 | 3406 | 5019.3612 | 73 | 0.13395 | 8.1711 | 589 | 0.04 | 2222
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 348657 | FALSE | 3761.8937 | 3253.8359 | 2.0223 | 29 | 8.3622e-05 | 2107 | 2006.4651 | 455 | 0.13388 | 3.8825 | 590 |  | 3007
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 870548 | FALSE | 8185.9487 | 8185.9487 | 5.0876 | 56 | 0.00010519 | 1515 | 1377.0688 | 649 | 0.13326 | 7.4625 | 591 |  | 3309
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 76020 | FALSE | 23407.8426 | 15031.7581 | 9.3423 | 137 | 5.4998e-05 | 2910 | 2512.6527 | 342 | 0.13318 | 18.2456 | 592 | 0.45 | 918
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 1306 | FALSE | 19638.9419 | 15260.277 | 9.4843 | 117 | 9.0495e-05 | 1898 | 1507.2616 | 595 | 0.13303 | 15.5648 | 593 | 0.07 | 1743
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 2540 | FALSE | 28748.5934 | 26122.3431 | 16.2351 | 135 | 0.00054969 | 24 | 203.3955 | 1636 | 0.13296 | 17.9496 | 594 | 0.02 | 2424
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | CB | TRUE | 1312.9371 | 596.6183 | 0.3708 | 11 | 0.00014984 | 739 | 1023.6412 | 812 | 0.13274 | 1.4601 | 595 | 0.08 | 1591
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 10416 | FALSE | 1110.1976 | 1110.1976 | 0.68999 | 7 | 0.00010788 | 1452 | 1426.8175 | 628 | 0.1325 | 0.92748 | 596 | 0.02 | 2491
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 770 | FALSE | 24751.8286 | 13838.1959 | 8.6005 | 110 | 0.00012303 | 1134 | 1361.4118 | 656 | 0.13217 | 14.5382 | 597 | 0.02 | 2513
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 384582 | FALSE | 7304.3535 | 7304.3535 | 4.5397 | 8 | 5.1941e-05 | 2994 | 4044.7807 | 147 | 0.13184 | 1.0547 | 598 |  | 3417
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 96390 | FALSE | 16282.4885 | 13753.525 | 8.5479 | 124 | 0.00016254 | 620 | 924.5376 | 871 | 0.13125 | 16.2749 | 599 | 0.12 | 1378
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | CB | FALSE | 16260.0032 | 8994.5064 | 5.5901 | 86 | 9.3599e-05 | 1807 | 1513.1588 | 589 | 0.1308 | 11.2491 | 600 | 0.04 | 2129
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | CB | FALSE | 14117.7933 | 14117.7933 | 8.7743 | 70 | 8.3932e-05 | 2095 | 1625.1549 | 551 | 0.13063 | 9.1442 | 601 | 0.03 | 2355
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 9753 | FALSE | 3306.1166 | 3306.1166 | 2.0548 | 23 | 6.1494e-05 | 2733 | 2174.098 | 407 | 0.13059 | 3.0036 | 602 | 0.08 | 1584
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 627416 | TRUE | 5034.3822 | 971.5124 | 0.6038 | 14 | 9.4498e-05 | 1779 | 1192.7699 | 735 | 0.13024 | 1.8234 | 603 |  | 3590
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 13474 | FALSE | 11606.5963 | 4726.1259 | 2.9373 | 99 | 9.8916e-05 | 1672 | 1472.7962 | 605 | 0.13001 | 12.8713 | 604 | 1.54 | 666
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 309438 | FALSE | 13011.7309 | 5938.6322 | 3.6909 | 93 | 0.00010698 | 1474 | 1153.73 | 754 | 0.12966 | 12.0584 | 605 |  | 3000
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 2212 | FALSE | 14695.9754 | 14695.9754 | 9.1336 | 76 | 0.00022108 | 315 | 358.4844 | 1358 | 0.12922 | 9.8207 | 606 | 41.81 | 174
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 1304 | FALSE | 30935.6957 | 30935.6957 | 19.2267 | 175 | 7.3325e-05 | 2386 | 1973.0848 | 460 | 0.12902 | 22.578 | 607 | 0.29 | 1031
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 886522 | FALSE | 30828.6552 | 10908.527 | 6.7797 | 154 | 6.1458e-05 | 2736 | 2215.6632 | 400 | 0.12899 | 19.8644 | 608 |  | 2965
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 1520 | FALSE | 31725.4009 | 6700.2969 | 4.1643 | 230 | 0.00011878 | 1212 | 1243.3344 | 704 | 0.1287 | 29.6011 | 609 | 0.04 | 2162
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 5391 | FALSE | 1530.1829 | 1530.1829 | 0.95101 | 7 | 4.9284e-05 | 3055 | 2595.0683 | 333 | 0.12868 | 0.90075 | 610 | 2.85 | 575
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 19042 | FALSE | 13701.0778 | 10069.7209 | 6.2584 | 89 | 0.00010259 | 1584 | 1548.81 | 581 | 0.12861 | 11.4466 | 611 | 0.17 | 1229
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 356 | FALSE | 24352.0152 | 17245.1485 | 10.7179 | 136 | 0.00012922 | 1022 | 991.1123 | 839 | 0.12847 | 17.4723 | 612 | 8.54 | 423
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 7446 | FALSE | 69991.8942 | 69991.8942 | 43.5002 | 427 | 0.00013367 | 949 | 983.1088 | 842 | 0.12828 | 54.7764 | 613 | 0.18 | 1220
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 35588 | FALSE | 4954.8551 | 4954.8551 | 3.0795 | 18 | 9.2798e-05 | 1827 | 1278.0574 | 690 | 0.12786 | 2.3016 | 614 | 0.6 | 851
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 59763 | FALSE | 4532.1933 | 4532.1933 | 2.8168 | 30 | 5.4981e-05 | 2912 | 2480.207 | 346 | 0.12716 | 3.8149 | 615 | 2.26 | 616
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 1702 | FALSE | 29294.348 | 26958.2044 | 16.7546 | 177 | 4.2191e-05 | 3220 | 3360.288 | 216 | 0.12716 | 22.5069 | 616 | 0.14 | 1332
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 188268 | FALSE | 8709.5262 | 6867.4982 | 4.2682 | 66 | 0.00013545 | 924 | 756.6199 | 968 | 0.1264 | 8.3425 | 617 |  | 2932
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 7823F | FALSE | 7527.4054 | 7527.4054 | 4.6783 | 49 | 2.6117e-05 | 3486 | 5142.2922 | 63 | 0.12636 | 6.1917 | 618 | 0.06 | 1848
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 877670 | FALSE | 10595.2996 | 10595.2996 | 6.585 | 28 | 7.9345e-05 | 2225 | 1606.4027 | 561 | 0.12626 | 3.5352 | 619 | 0.06 | 1803
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | W80 | FALSE | 30507.2399 | 30491.2345 | 18.9504 | 129 | 0.00012461 | 1105 | 990.5879 | 840 | 0.12598 | 16.2519 | 620 | 0.26 | 1062
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 350030 | FALSE | 14009.015 | 9325.238 | 5.7957 | 107 | 0.00012847 | 1039 | 957.5657 | 855 | 0.12598 | 13.4795 | 621 |  | 3314
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 288980 | TRUE | 1137.5268 | 532.3299 | 0.33085 | 6 | 5.3751e-05 | 2947 | 2359.4228 | 370 | 0.12531 | 0.75188 | 622 |  | 3583
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 955138 | FALSE | 4475.7732 | 4227.5124 | 2.6274 | 16 | 6.7551e-05 | 2548 | 1883.3994 | 478 | 0.12515 | 2.0024 | 623 |  | 3270
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 1330 | FALSE | 50161.9849 | 49990.913 | 31.0696 | 264 | 0.00011447 | 1308 | 1373.7242 | 651 | 0.12503 | 33.0087 | 624 | 0.19 | 1173
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 5152 | FALSE | 2685.0442 | 2685.0442 | 1.6688 | 17 | 0.00018787 | 456 | 675.7903 | 1038 | 0.1239 | 2.1064 | 625 | 12.52 | 374
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 1282 | FALSE | 26604.6713 | 22934.9277 | 14.2542 | 164 | 7.8872e-05 | 2239 | 1748.6654 | 515 | 0.12376 | 20.2971 | 626 | 4.57 | 514
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | CB | FALSE | 14342.9846 | 2348.085 | 1.4593 | 124 | 5.5469e-05 | 2900 | 1580.4692 | 569 | 0.12375 | 15.3456 | 627 | 0.03 | 2351
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 1644 | FALSE | 36747.479 | 36747.479 | 22.8387 | 244 | 0.00010131 | 1620 | 1382.8849 | 646 | 0.12375 | 30.1941 | 628 | 0.08 | 1604
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 78448 | FALSE | 47671.1997 | 31387.7639 | 19.5076 | 188 | 3.1679e-05 | 3405 | 4051.9056 | 146 | 0.12365 | 23.2453 | 629 | 0.05 | 2059
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 1770 | FALSE | 13849.8333 | 13849.8333 | 8.6077 | 66 | 0.00044353 | 51 | 343.9532 | 1380 | 0.12342 | 8.1457 | 630 | 0.02 | 2504
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | Y06 | FALSE | 63281.543 | 48855.5405 | 30.3639 | 304 | 5.4903e-05 | 2917 | 2033.2985 | 450 | 0.12317 | 37.4433 | 631 | 0.14 | 1333
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 10587 | FALSE | 35336.5514 | 35336.5514 | 21.9618 | 212 | 8.4096e-05 | 2092 | 1469.4238 | 607 | 0.12297 | 26.0703 | 632 | 0.13 | 1334
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 156 | FALSE | 18958.8699 | 9919.8336 | 6.1652 | 110 | 0.00012453 | 1107 | 875.9596 | 896 | 0.12268 | 13.4944 | 633 | 0.21 | 1144
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 69866 | FALSE | 10571.2356 | 10571.2356 | 6.5701 | 46 | 0.00023172 | 281 | 514.4343 | 1188 | 0.12256 | 5.6379 | 634 | 3.53 | 543
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 705100 | FALSE | 13322.8036 | 11885.1942 | 7.3867 | 78 | 0.00013638 | 915 | 900.0548 | 884 | 0.12223 | 9.5341 | 635 |  | 3106
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 7110 | FALSE | 29983.2616 | 29983.2616 | 18.6347 | 132 | 4.0372e-05 | 3258 | 3332.8764 | 221 | 0.12197 | 16.0996 | 636 | 0.03 | 2230
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 604 | FALSE | 28058.6741 | 28058.6741 | 17.4386 | 169 | 0.00010038 | 1638 | 1390.9913 | 641 | 0.12169 | 20.5661 | 637 | 38.24 | 196
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 781445 | TRUE | 577.8877 | 405.5365 | 0.25204 | 6 | 0.00010546 | 1508 | 1075.6001 | 784 | 0.12145 | 0.72871 | 638 |  | 3291
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 153199 | FALSE | 8788.2197 | 4750.5459 | 2.9525 | 53 | 4.9986e-05 | 3037 | 2588.0496 | 334 | 0.1214 | 6.4339 | 639 |  | 3364
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 572 | FALSE | 34429.3225 | 34429.3225 | 21.398 | 155 | 0.00020812 | 372 | 588.4642 | 1115 | 0.12097 | 18.7503 | 640 | 5.06 | 497
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | A16 | FALSE | 32308.0619 | 31835.9088 | 19.7861 | 122 | 9.9134e-05 | 1665 | 1262.4628 | 693 | 0.12088 | 14.7476 | 641 | 0.07 | 1702
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 2455 | FALSE | 10165.5764 | 10165.5764 | 6.3179 | 84 | 3.5175e-05 | 3348 | 3535.7199 | 196 | 0.12034 | 10.1082 | 642 | 0.08 | 1657
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 3008 | FALSE | 24475.225 | 13636.9493 | 8.4754 | 55 | 6.8766e-05 | 2515 | 2119.5029 | 421 | 0.1202 | 6.6112 | 643 | 0.01 | 2614
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | CB | FALSE | 66423.2503 | 66423.2503 | 41.2823 | 448 | 0.00014731 | 770 | 1022.0989 | 813 | 0.12006 | 53.7868 | 644 | 29.66 | 239
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 1504 | FALSE | 23629.2409 | 17735.4007 | 11.0226 | 186 | 0.00021184 | 352 | 618.3499 | 1084 | 0.12006 | 22.3307 | 645 | 0.12 | 1402
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | CB | FALSE | 1831.3319 | 1593.4993 | 0.99037 | 15 | 0.00021275 | 345 | 713.5234 | 1009 | 0.11989 | 1.7983 | 646 | 0.07 | 1726
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 855412 | FALSE | 50683.3516 | 45702.3865 | 28.4042 | 108 | 6.4443e-05 | 2629 | 1812.7947 | 504 | 0.11956 | 12.9123 | 647 | 0.05 | 2051
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 3152 | FALSE | 27364.6036 | 26923.3255 | 16.733 | 134 | 8.4438e-05 | 2079 | 1552.0849 | 578 | 0.11956 | 16.0208 | 648 | 0.08 | 1624
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 7722 | FALSE | 100229.7186 | 96782.5255 | 60.1507 | 572 | 0.00010462 | 1540 | 1087.3028 | 779 | 0.11928 | 68.2291 | 649 | 0.25 | 1084
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 1264 | FALSE | 56286.9636 | 56286.9636 | 34.9826 | 307 | 0.00011647 | 1260 | 1094.5256 | 776 | 0.11917 | 36.585 | 650 | 0.39 | 957
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | CB | FALSE | 45692.926 | 45174.6839 | 28.0762 | 315 | 0.00014305 | 825 | 1166.4722 | 747 | 0.11916 | 37.536 | 651 | 0.25 | 1090
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 822606 | FALSE | 29230.0954 | 21701.9466 | 13.4878 | 144 | 3.2057e-05 | 3400 | 3717.2296 | 181 | 0.11894 | 17.1275 | 652 |  | 2678
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | MR186 | TRUE | 4135.7533 | 818.8837 | 0.50894 | 27 | 8.9465e-05 | 1933 | 1490.2334 | 599 | 0.11874 | 3.2061 | 653 | 0.02 | 2461
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 8372 | FALSE | 101264.4904 | 94481.7777 | 58.7208 | 629 | 0.00011802 | 1229 | 985.1922 | 841 | 0.11858 | 74.5861 | 654 | 0.21 | 1139
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 9400 | FALSE | 101537.78 | 101537.78 | 63.1061 | 667 | 6.6859e-05 | 2561 | 1882.7942 | 479 | 0.11849 | 79.0304 | 655 | 1.17 | 705
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | N62 | FALSE | 8948.1922 | 8948.1922 | 5.5613 | 39 | 7.0521e-05 | 2455 | 1674.5706 | 532 | 0.11842 | 4.6183 | 656 | 0.13 | 1344
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | CB | FALSE | 30610.8387 | 30610.8387 | 19.0248 | 245 | 0.00018342 | 484 | 745.8005 | 978 | 0.11812 | 28.9401 | 657 | 0.61 | 844
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | CB | FALSE | 39248.3153 | 36287.6403 | 22.5529 | 243 | 0.00015786 | 664 | 1177.1526 | 742 | 0.11807 | 28.6917 | 658 | 0.1 | 1491
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 528460 | FALSE | 6121.8319 | 3043.5918 | 1.8916 | 12 | 3.9909e-05 | 3271 | 3097.7847 | 255 | 0.11792 | 1.415 | 659 |  | 3454
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 6110 | FALSE | 47929.948 | 17714.3763 | 11.0096 | 179 | 4.1885e-05 | 3228 | 2595.4532 | 332 | 0.11737 | 21.0097 | 660 | 0.03 | 2313
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 50140 | FALSE | 10038.7802 | 6357.3386 | 3.9511 | 82 | 0.0001527 | 722 | 724.1364 | 995 | 0.11734 | 9.6215 | 661 | 0.07 | 1721
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 777686 | FALSE | 3079.762 | 2707.2733 | 1.6826 | 17 | 6.1974e-05 | 2721 | 2050.5492 | 444 | 0.11731 | 1.9944 | 662 |  | 3452
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 58626 | FALSE | 24491.7338 | 24491.7338 | 15.2217 | 125 | 9.1234e-05 | 1869 | 1427.3169 | 627 | 0.117 | 14.6249 | 663 | 33.89 | 218
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 157026 | FALSE | 5200.077 | 5200.077 | 3.2319 | 44 | 6.6096e-05 | 2586 | 1923.6933 | 467 | 0.11682 | 5.1403 | 664 | 0.05 | 1989
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 11232 | FALSE | 27747.6591 | 20505.608 | 12.7443 | 222 | 7.7668e-05 | 2269 | 1686.0292 | 527 | 0.11656 | 25.8772 | 665 | 3.3 | 550
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 2102 | FALSE | 62912.0633 | 60307.8799 | 37.4816 | 417 | 0.00013035 | 1002 | 1146.8943 | 755 | 0.11621 | 48.4576 | 666 | 0.75 | 787
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | CB | FALSE | 12241.4218 | 6260.0525 | 3.8906 | 90 | 0.00013491 | 927 | 773.6055 | 956 | 0.11609 | 10.4477 | 667 | 0.03 | 2310
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 484 | FALSE | 78528.1935 | 53688.8082 | 33.3678 | 379 | 0.00011833 | 1222 | 896.8187 | 885 | 0.11607 | 43.9888 | 668 | 0.17 | 1225
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | CB | FALSE | 18716.511 | 18050.1072 | 11.2182 | 124 | 0.00013241 | 974 | 792.6979 | 948 | 0.11592 | 14.3743 | 669 | 0.08 | 1643
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 119949 | FALSE | 3756.7927 | 2221.8702 | 1.3809 | 25 | 7.5613e-05 | 2320 | 1497.9784 | 598 | 0.11529 | 2.8822 | 670 |  | 3429
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | CB | FALSE | 21668.4067 | 9680.057 | 6.0162 | 110 | 0.00011397 | 1323 | 734.8074 | 989 | 0.11521 | 12.6729 | 671 | 0.03 | 2334
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 745811 | TRUE | 780.426 | 641.2916 | 0.39857 | 8 | 7.9022e-05 | 2235 | 1106.1185 | 773 | 0.11506 | 0.92047 | 672 |  | 3113
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 91900 | FALSE | 22248.6035 | 14519.294 | 9.0238 | 91 | 0.00012885 | 1031 | 1012.5441 | 824 | 0.11491 | 10.4566 | 673 | 1.72 | 650
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 97354 | FALSE | 16339.8299 | 14168.242 | 8.8056 | 59 | 2.3546e-05 | 3509 | 5418.3509 | 49 | 0.11488 | 6.7778 | 674 | 0.06 | 1885
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 19642 | FALSE | 2579.2739 | 1246.4399 | 0.77467 | 17 | 0.00024874 | 219 | 453.1258 | 1242 | 0.11477 | 1.9511 | 675 | 0.96 | 739
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 9470 | FALSE | 36749.5976 | 36749.5976 | 22.84 | 277 | 8.8658e-05 | 1964 | 1395.4992 | 639 | 0.11474 | 31.7833 | 676 | 0.01 | 2586
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 943820 | FALSE | 3953.9711 | 3039.5845 | 1.8891 | 13 | 9.0029e-05 | 1913 | 1434.295 | 621 | 0.11464 | 1.4903 | 677 |  | 3527
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 1594 | FALSE | 39042.2093 | 39042.2093 | 24.2649 | 160 | 0.00012552 | 1089 | 1126.4421 | 765 | 0.11449 | 18.3178 | 678 | 0.12 | 1390
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 10240 | FALSE | 34689.059 | 34689.059 | 21.5594 | 189 | 7.4292e-05 | 2350 | 1439.7612 | 619 | 0.11431 | 21.6045 | 679 | 0.31 | 1009
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 674 | FALSE | 32462.2926 | 27296.9382 | 16.9652 | 122 | 0.00011908 | 1203 | 1499.689 | 597 | 0.11401 | 13.9092 | 680 | 0.15 | 1285
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 61892 | FALSE | 48456.6488 | 48456.6488 | 30.116 | 318 | 8.0969e-05 | 2183 | 1584.3018 | 567 | 0.11372 | 36.1635 | 681 | 38.89 | 193
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 55206 | TRUE | 3467.0084 | 0 | 0 | 28 | 0.00010976 | 1415 | 967.1576 | 851 | 0.11351 | 3.1783 | 682 | 0.04 | 2213
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 734 | FALSE | 26724.941 | 22050.8989 | 13.7047 | 162 | 0.00015037 | 732 | 885.8837 | 889 | 0.11348 | 18.3842 | 683 | 1.06 | 719
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | CB | FALSE | 19422.567 | 19422.567 | 12.0712 | 106 | 0.00011506 | 1297 | 1154.679 | 753 | 0.11341 | 12.0218 | 684 | 5.58 | 484
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 45262 | FALSE | 46333.9347 | 46333.9347 | 28.7967 | 221 | 0.00010272 | 1577 | 1038.3077 | 800 | 0.11334 | 25.0485 | 685 | 0.06 | 1915
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 1344 | FALSE | 20065.0071 | 16285.3354 | 10.1214 | 152 | 6.9299e-05 | 2497 | 2362.2491 | 369 | 0.11327 | 17.2178 | 686 | 4.34 | 522
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 699062 | FALSE | 3006.4235 | 1359.6473 | 0.84503 | 20 | 8.6499e-05 | 2024 | 1257.9802 | 696 | 0.11322 | 2.2645 | 687 |  | 3300
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 12392 | FALSE | 23572.5391 | 23572.5391 | 14.6504 | 178 | 0.00010936 | 1424 | 1246.8521 | 703 | 0.11309 | 20.1293 | 688 | 55.71 | 101
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 421358 | FALSE | 23870.6711 | 23870.6711 | 14.8357 | 169 | 0.00012254 | 1140 | 802.5537 | 940 | 0.11286 | 19.0733 | 689 |  | 2784
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 722 | FALSE | 12705.3582 | 12705.3582 | 7.8964 | 99 | 0.00026082 | 194 | 569.6012 | 1130 | 0.11274 | 11.1613 | 690 | 46.62 | 140
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 3751 | FALSE | 16451.1737 | 15802.8651 | 9.8215 | 65 | 4.4896e-05 | 3163 | 3153.8117 | 247 | 0.11269 | 7.325 | 691 | 0.03 | 2272
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | CB | FALSE | 14665.1565 | 5449.7896 | 3.3871 | 81 | 0.00012146 | 1157 | 1050.3758 | 796 | 0.11258 | 9.1187 | 692 | 0.04 | 2099
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 51756 | FALSE | 56082.3102 | 17440.8058 | 10.8395 | 264 | 8.4998e-05 | 2060 | 1131.9939 | 763 | 0.11252 | 29.7041 | 693 | 1.15 | 707
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 501106 | FALSE | 16962.6839 | 16083.896 | 9.9962 | 86 | 2.2874e-05 | 3513 | 4753.376 | 97 | 0.11248 | 9.6734 | 694 |  | 2889
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 19772 | FALSE | 29712.1582 | 28840.3765 | 17.9244 | 185 | 0.00010637 | 1489 | 1084.3194 | 780 | 0.11233 | 20.7806 | 695 | 41.36 | 177
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 593454 | FALSE | 65282.8123 | 51502.8241 | 32.0092 | 324 | 8.6965e-05 | 2012 | 1565.5344 | 572 | 0.11221 | 36.3549 | 696 |  | 2656
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 1530 | FALSE | 28483.8521 | 18168.0106 | 11.2915 | 167 | 5.6107e-05 | 2884 | 2176.9842 | 405 | 0.11218 | 18.7349 | 697 | 0.01 | 2573
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 81296 | FALSE | 24680.7336 | 17571.0511 | 10.9205 | 124 | 0.00010636 | 1490 | 869.9858 | 899 | 0.11218 | 13.9107 | 698 | 0.05 | 2005
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 77546 | FALSE | 69346.9327 | 69346.9327 | 43.0994 | 403 | 9.5092e-05 | 1762 | 1309.4241 | 678 | 0.11214 | 45.1922 | 699 | 0.19 | 1189
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 752630 | FALSE | 30558.9663 | 30558.9663 | 18.9925 | 154 | 6.484e-05 | 2614 | 1699.6449 | 523 | 0.11205 | 17.2553 | 700 |  | 2886
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 213984 | FALSE | 11162.845 | 11162.845 | 6.9378 | 47 | 9.4494e-05 | 1780 | 1225.6338 | 715 | 0.11198 | 5.263 | 701 |  | 2957
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 38748 | FALSE | 24704.6186 | 24704.6186 | 15.354 | 178 | 7.1784e-05 | 2426 | 1618.5371 | 554 | 0.11192 | 19.9215 | 702 | 0.01 | 2604
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 99720 | FALSE | 19787.8115 | 14780.8133 | 9.1863 | 134 | 8.8188e-05 | 1977 | 1157.381 | 751 | 0.11177 | 14.9768 | 703 | 7.05 | 453
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | CB | FALSE | 17394.4702 | 14019.0952 | 8.7129 | 134 | 0.00023184 | 280 | 615.3789 | 1088 | 0.11172 | 14.9707 | 704 | 0.06 | 1909
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 75370 | FALSE | 23702.8229 | 17823.7139 | 11.0775 | 133 | 0.0001129 | 1346 | 1122.5953 | 767 | 0.11161 | 14.8441 | 705 | 0.05 | 2009
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 37586 | FALSE | 22457.0278 | 22457.0278 | 13.9571 | 72 | 0.00013607 | 919 | 959.2045 | 854 | 0.11137 | 8.0187 | 706 | 0.07 | 1736
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 7831 | FALSE | 14300.9674 | 14300.9674 | 8.8881 | 86 | 5.8164e-05 | 2831 | 1904.4724 | 475 | 0.1113 | 9.5719 | 707 | 0.1 | 1473
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 317796 | FALSE | 11760.0744 | 8148.5566 | 5.0644 | 65 | 7.0178e-05 | 2466 | 1382.5193 | 647 | 0.11087 | 7.2063 | 708 |  | 3222
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 585 | FALSE | 22730.6203 | 22730.6203 | 14.1272 | 95 | 6.2212e-05 | 2714 | 1313.2645 | 677 | 0.11082 | 10.5283 | 709 | 0.1 | 1490
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 690954 | FALSE | 6889.4894 | 6410.0397 | 3.9839 | 12 | 1.5494e-05 | 3583 | 7160.5307 | 9 | 0.11057 | 1.3268 | 710 |  | 3318
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | CB | FALSE | 53866.9528 | 51789.1777 | 32.1872 | 417 | 0.00011056 | 1401 | 1269.855 | 691 | 0.11044 | 46.0525 | 711 | 0.78 | 780
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | CB | TRUE | 7260.7146 | 263.08 | 0.16351 | 61 | 0.00011907 | 1204 | 713.2367 | 1010 | 0.1104 | 6.7341 | 712 | 0.02 | 2463
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 839302 | FALSE | 1806.4039 | 1806.4039 | 1.1227 | 8 | 4.4881e-05 | 3164 | 2564.3756 | 337 | 0.11001 | 0.88007 | 713 |  | 3595
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 1204 | FALSE | 47393.9854 | 41374.6655 | 25.7145 | 233 | 8.8982e-05 | 1950 | 1305.1155 | 679 | 0.10989 | 25.6033 | 714 | 0.09 | 1553
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 2790 | FALSE | 17696.042 | 16028.2028 | 9.9616 | 115 | 0.00014264 | 831 | 967.5085 | 850 | 0.10954 | 12.5971 | 715 | 0.18 | 1201
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 68190 | FALSE | 40559.778 | 38588.9503 | 23.9832 | 238 | 3.6266e-05 | 3328 | 3033.8848 | 265 | 0.10937 | 26.0311 | 716 | 0.06 | 1813
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 664732 | FALSE | 1437.8147 | 1437.8147 | 0.89361 | 6 | 9.0941e-05 | 1884 | 1650.3416 | 543 | 0.10842 | 0.65051 | 717 | 1.72 | 649
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 600 | FALSE | 39281.1533 | 30870.3 | 19.186 | 164 | 0.00011588 | 1272 | 1083.2564 | 781 | 0.10818 | 17.7408 | 718 | 0.15 | 1297
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | CB | FALSE | 7158.565 | 3619.1597 | 2.2493 | 59 | 0.00018211 | 497 | 299.7205 | 1447 | 0.10789 | 6.3658 | 719 | 0.1 | 1483
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 229588 | FALSE | 21565.3961 | 15531.0208 | 9.6526 | 149 | 8.8674e-05 | 1963 | 1224.4513 | 716 | 0.10786 | 16.0708 | 720 |  | 3033
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 1623 | FALSE | 24554.2111 | 24554.2111 | 15.2605 | 152 | 7.6286e-05 | 2301 | 1590.8242 | 564 | 0.1076 | 16.3546 | 721 | 0.2 | 1165
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 551904 | TRUE | 35.7178 | 35.7178 | 0.022199 | 1 | 0.00014066 | 859 | 763.0871 | 960 | 0.10733 | 0.10733 | 722 | 0.87 | 755
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 937710 | FALSE | 2292.7758 | 1372.1379 | 0.85279 | 8 | 9.5377e-05 | 1748 | 1144.507 | 756 | 0.10733 | 0.85862 | 723 |  | 3387
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 9472 | FALSE | 11800.3384 | 4934.5741 | 3.0669 | 90 | 8.6625e-05 | 2018 | 1503.1801 | 596 | 0.10731 | 9.6577 | 724 | 0.04 | 2109
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 51740 | FALSE | 34181.0044 | 25031.397 | 15.5571 | 129 | 6.4996e-05 | 2610 | 1615.1565 | 556 | 0.107 | 13.8028 | 725 | 0.06 | 1828
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 36666 | FALSE | 29026.438 | 27295.7526 | 16.9644 | 207 | 7.008e-05 | 2471 | 1591.1088 | 563 | 0.10683 | 22.1131 | 726 | 0.11 | 1436
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 1704 | FALSE | 4825.0456 | 4825.0456 | 2.9988 | 9 | 0.00018499 | 473 | 1060.4778 | 792 | 0.1065 | 0.95854 | 727 | 1.47 | 671
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 75382 | FALSE | 37601.9152 | 37336.0999 | 23.2045 | 198 | 0.00010957 | 1420 | 1232.3374 | 713 | 0.10636 | 21.0588 | 728 | 11.14 | 387
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 220154 | TRUE | 4466.0624 | 427.7941 | 0.26588 | 30 | 0.00014785 | 765 | 533.1924 | 1168 | 0.10579 | 3.1738 | 729 |  | 3155
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | CB | FALSE | 58448.7227 | 58073.6402 | 36.093 | 382 | 0.00010807 | 1450 | 1111.2712 | 769 | 0.10567 | 40.3677 | 730 | 0.26 | 1065
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 4410 | FALSE | 36702.381 | 36702.381 | 22.8107 | 232 | 6.2011e-05 | 2720 | 1654.2525 | 541 | 0.10548 | 24.471 | 731 | 0.16 | 1272
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 630 | FALSE | 31341.2103 | 30113.0466 | 18.7154 | 93 | 5.6908e-05 | 2863 | 1625.0866 | 552 | 0.10515 | 9.7794 | 732 | 0.15 | 1293
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 966 | FALSE | 3670.4356 | 1555.849 | 0.96697 | 34 | 0.00012939 | 1020 | 514.9608 | 1186 | 0.10505 | 3.5716 | 733 | 0.33 | 984
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 43008 | FALSE | 20752.8612 | 20697.7732 | 12.8637 | 145 | 0.00024315 | 238 | 866.3217 | 903 | 0.10501 | 15.2269 | 734 |  | 3002
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | XR070 | FALSE | 13972.8614 | 10519.5514 | 6.5379 | 90 | 8.0053e-05 | 2203 | 1459.1172 | 612 | 0.10473 | 9.4261 | 735 | 0.15 | 1280
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 2112 | FALSE | 31201.9016 | 31201.9016 | 19.3921 | 222 | 0.00012958 | 1016 | 755.541 | 969 | 0.1046 | 23.2211 | 736 | 9 | 416
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 2216 | FALSE | 93046.0132 | 91192.0768 | 56.6762 | 663 | 0.00017534 | 526 | 744.5838 | 980 | 0.10438 | 69.2068 | 737 | 0.89 | 752
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | CB | TRUE | 64.9169 | 64.9169 | 0.040346 | 2 | 8.2597e-05 | 2140 | 1260.6413 | 694 | 0.10413 | 0.20825 | 738 | 0.04 | 2172
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 65516 | FALSE | 18264.4613 | 12394.5836 | 7.7033 | 137 | 9.0277e-05 | 1904 | 1198.218 | 730 | 0.104 | 14.2484 | 739 | 1.33 | 685
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 65908 | FALSE | 26966.3027 | 22380.0869 | 13.9093 | 205 | 0.00010013 | 1641 | 1026.2121 | 810 | 0.10393 | 21.3052 | 740 | 0.11 | 1441
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 12606 | FALSE | 36144.366 | 36144.366 | 22.4639 | 216 | 6.3081e-05 | 2677 | 1680.4042 | 528 | 0.10392 | 22.4476 | 741 | 3.18 | 556
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 1652 | FALSE | 39344.5137 | 33895.2642 | 21.066 | 170 | 8.6737e-05 | 2017 | 1367.2683 | 654 | 0.10352 | 17.5982 | 742 | 0.06 | 1779
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 19572 | TRUE | 4463.6596 | 595.3794 | 0.37003 | 12 | 8.8886e-05 | 1956 | 995.992 | 836 | 0.10348 | 1.2418 | 743 | 0.4 | 947
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 13442 | FALSE | 49960.437 | 40749.3903 | 25.3259 | 272 | 6.9011e-05 | 2508 | 1672.073 | 535 | 0.10338 | 28.1191 | 744 | 0.16 | 1269
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 284874 | FALSE | 7928.0423 | 3450.771 | 2.1447 | 56 | 0.00016281 | 613 | 825.2112 | 923 | 0.10322 | 5.7804 | 745 |  | 2708
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 9792 | FALSE | 44037.0343 | 1255.3676 | 0.78022 | 329 | 0.00010469 | 1536 | 1266.1791 | 692 | 0.10322 | 33.9591 | 746 | 1.85 | 639
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 62157 | TRUE | 72.1015 | 72.1015 | 0.044811 | 3 | 0.00013141 | 991 | 794.5095 | 944 | 0.10257 | 0.30771 | 747 | 0.04 | 2185
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 91464 | FALSE | 11314.1038 | 11314.1038 | 7.0318 | 81 | 0.00016471 | 590 | 737.1972 | 986 | 0.10229 | 8.2855 | 748 | 0.15 | 1286
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 2212 | FALSE | 54144.6309 | 25107.5196 | 15.6044 | 136 | 5.0479e-05 | 3023 | 1941.9065 | 465 | 0.10222 | 13.9025 | 749 | 0.05 | 2020
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 36536 | FALSE | 31849.3061 | 27701.0415 | 17.2163 | 206 | 9.0039e-05 | 1912 | 1240.3355 | 706 | 0.10219 | 21.0515 | 750 | 6.79 | 460
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 2584 | FALSE | 15108.9141 | 14615.3184 | 9.0835 | 83 | 7.5728e-05 | 2313 | 1697.4775 | 524 | 0.1019 | 8.4581 | 751 | 0.06 | 1883
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 90356 | FALSE | 27619.1431 | 7749.0513 | 4.8161 | 148 | 4.5741e-05 | 3146 | 2250.7696 | 393 | 0.10189 | 15.079 | 752 | 0.02 | 2540
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 345230 | FALSE | 4014.2831 | 1908.1944 | 1.186 | 22 | 0.00013065 | 997 | 832.9519 | 920 | 0.10181 | 2.2398 | 753 |  | 3505
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 4646 | TRUE | 480.2865 | 242.399 | 0.15065 | 8 | 0.00023752 | 255 | 1510.1147 | 591 | 0.10163 | 0.81301 | 754 | 0.12 | 1368
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | CB | TRUE | 993.1092 | 957.3027 | 0.59497 | 10 | 0.00022667 | 299 | 666.0518 | 1045 | 0.10116 | 1.0116 | 755 | 1.11 | 714
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 56048 | FALSE | 8009.5026 | 8009.5026 | 4.9779 | 27 | 0.00051047 | 29 | 201.585 | 1638 | 0.10102 | 2.7275 | 756 | 0.04 | 2118
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 4360 | FALSE | 14899.0043 | 12170.4858 | 7.564 | 76 | 4.8295e-05 | 3087 | 2072.1488 | 436 | 0.10101 | 7.6765 | 757 | 0.1 | 1496
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 1202 | FALSE | 73649.8789 | 73649.8789 | 45.7737 | 459 | 9.3805e-05 | 1798 | 1469.356 | 608 | 0.10087 | 46.3007 | 758 | 0.24 | 1107
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 38864 | FALSE | 12167.5887 | 2907.107 | 1.8068 | 94 | 9.1373e-05 | 1865 | 1176.5294 | 743 | 0.10076 | 9.4715 | 759 | 0.03 | 2406
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 204 | FALSE | 31553.8482 | 31553.8482 | 19.6108 | 107 | 0.00017266 | 545 | 673.9659 | 1039 | 0.10067 | 10.7713 | 760 | 11.03 | 390
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 10019 | FALSE | 3187.4941 | 3187.4941 | 1.981 | 11 | 5.9517e-05 | 2788 | 1607.8644 | 559 | 0.10052 | 1.1057 | 761 | 0.01 | 2577
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 42348 | FALSE | 5997.998 | 2160.8096 | 1.343 | 53 | 6.8961e-05 | 2511 | 1015.3292 | 819 | 0.10037 | 5.3194 | 762 | 0.49 | 895
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 934355 | TRUE | 1942.6666 | 915.6706 | 0.56909 | 12 | 8.3455e-05 | 2118 | 1431.4244 | 623 | 0.10029 | 1.2035 | 763 |  | 3546
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 48484 | FALSE | 67054.8672 | 67054.8672 | 41.6749 | 450 | 0.00013313 | 956 | 878.6779 | 893 | 0.09998 | 44.991 | 764 | 0.43 | 927
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 7559 | FALSE | 7193.5229 | 7193.5229 | 4.4708 | 52 | 6.8486e-05 | 2522 | 1663.4994 | 538 | 0.099807 | 5.1899 | 765 | 0.1 | 1474
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 718 | FALSE | 47250.4225 | 43463.4041 | 27.0127 | 247 | 6.3139e-05 | 2675 | 1440.3304 | 618 | 0.099744 | 24.6369 | 766 | 0.18 | 1211
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 63500 | TRUE | 5562.1132 | 327.1501 | 0.20333 | 46 | 0.00011792 | 1230 | 448.3626 | 1251 | 0.099652 | 4.584 | 767 | 1.81 | 642
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 1608 | FALSE | 53827.5719 | 53827.5719 | 33.4541 | 252 | 0.00019009 | 441 | 523.0258 | 1180 | 0.099644 | 25.1102 | 768 | 0.06 | 1838
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 248490 | FALSE | 43282.2287 | 17726.6224 | 11.0172 | 228 | 9.8358e-05 | 1682 | 1137.7994 | 759 | 0.099611 | 22.7114 | 769 |  | 2654
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 443164 | FALSE | 15151.4475 | 4499.5872 | 2.7965 | 111 | 0.00012907 | 1027 | 720.9883 | 997 | 0.099321 | 11.0246 | 770 |  | 2651
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 92622 | FALSE | 50349.3756 | 50311.0535 | 31.2685 | 257 | 0.00011545 | 1291 | 1017.6191 | 817 | 0.098498 | 25.314 | 771 | 0.07 | 1774
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 154362 | FALSE | 11970.1824 | 3480.2712 | 2.163 | 90 | 0.00011044 | 1403 | 797.5542 | 943 | 0.098415 | 8.8574 | 772 |  | 2686
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | CB | FALSE | 3412.1639 | 2836.6716 | 1.763 | 16 | 0.00010435 | 1543 | 961.0572 | 853 | 0.098349 | 1.5736 | 773 | 0.87 | 758
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 93870 | FALSE | 54990.4582 | 29826.9597 | 18.5376 | 342 | 6.6942e-05 | 2559 | 1508.5624 | 593 | 0.098287 | 33.6143 | 774 | 0.09 | 1545
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | CB | TRUE | 859.9008 | 859.9008 | 0.53443 | 5 | 0.00010841 | 1440 | 866.0652 | 904 | 0.098274 | 0.49137 | 775 | 0.05 | 1958
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | A10 | FALSE | 49945.6996 | 49945.6996 | 31.0415 | 264 | 7.3622e-05 | 2377 | 1325.7939 | 671 | 0.098002 | 25.8725 | 776 | 7.4 | 446
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 2706 | FALSE | 23999.9081 | 9304.8867 | 5.783 | 190 | 0.0001407 | 858 | 837.755 | 918 | 0.09785 | 18.5915 | 777 | 0.94 | 743
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 934 | FALSE | 49660.3767 | 49660.3767 | 30.8641 | 279 | 9.3799e-05 | 1799 | 1233.6573 | 711 | 0.097599 | 27.2301 | 778 | 35.78 | 211
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 13498 | FALSE | 1603.6406 | 1585.9579 | 0.98568 | 13 | 0.00013812 | 892 | 567.2293 | 1131 | 0.097071 | 1.2619 | 779 | 0.06 | 1831
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 90090 | FALSE | 48332.111 | 48332.111 | 30.0386 | 168 | 9.2359e-05 | 1833 | 1129.7718 | 764 | 0.09692 | 16.2826 | 780 | 0.05 | 2011
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 83158 | FALSE | 31398.3782 | 28429.994 | 17.6694 | 132 | 6.3068e-05 | 2679 | 1552.5213 | 577 | 0.09689 | 12.7894 | 781 | 0.06 | 1781
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 2500 | FALSE | 48136.3959 | 48136.3959 | 29.917 | 143 | 8.5236e-05 | 2049 | 1216.4356 | 720 | 0.096773 | 13.8385 | 782 | 0.21 | 1155
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 603392 | FALSE | 5227.4341 | 4685.9835 | 2.9124 | 17 | 5.2363e-05 | 2983 | 1917.7994 | 469 | 0.096621 | 1.6426 | 783 |  | 3382
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13312 | FALSE | 28501.0245 | 21155.7388 | 13.1484 | 190 | 0.00021994 | 321 | 408.8559 | 1287 | 0.096554 | 18.3453 | 784 | 0.12 | 1376
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 1958 | FALSE | 54465.3426 | 54465.3426 | 33.8504 | 353 | 0.00011848 | 1218 | 944.1299 | 865 | 0.096142 | 33.9382 | 785 | 0.29 | 1022
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | CB | FALSE | 20899.9329 | 19267.3702 | 11.9747 | 95 | 0.00020717 | 375 | 574.8898 | 1127 | 0.095782 | 9.0993 | 786 | 5.57 | 485
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 35466 | FALSE | 11836.6618 | 11836.6618 | 7.3565 | 82 | 0.00016771 | 578 | 531.3358 | 1171 | 0.095562 | 7.8361 | 787 | 0.06 | 1799
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 9811 | FALSE | 14351.9184 | 5776.4657 | 3.5901 | 92 | 8.2868e-05 | 2133 | 845.358 | 914 | 0.095333 | 8.7707 | 788 | 0.03 | 2316
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | CB | TRUE | 7060.6838 | 875.6492 | 0.54422 | 45 | 5.6384e-05 | 2879 | 1585.2096 | 566 | 0.095165 | 4.2824 | 789 | 0.89 | 750
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | CB | TRUE | 3890.2841 | 517.8814 | 0.32187 | 37 | 0.00015375 | 712 | 238.7834 | 1569 | 0.095153 | 3.5207 | 790 | 0.1 | 1501
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | CB | FALSE | 9278.0237 | 5281.0095 | 3.2822 | 53 | 6.9821e-05 | 2480 | 949.0975 | 862 | 0.095135 | 5.0422 | 791 | 0.02 | 2553
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 632 | FALSE | 29843.7661 | 29492.7895 | 18.3299 | 193 | 0.00011902 | 1207 | 950.7759 | 861 | 0.094959 | 18.327 | 792 | 90.53 | 32
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 1064 | FALSE | 31650.7422 | 31650.7422 | 19.6711 | 179 | 9.295e-05 | 1824 | 1110.3932 | 771 | 0.094905 | 16.9879 | 793 | 64.19 | 79
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 6008 | FALSE | 37504.3181 | 37504.3181 | 23.3091 | 236 | 8.3382e-05 | 2122 | 1032.7499 | 806 | 0.094797 | 22.3721 | 794 | 0.31 | 1010
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | CB | FALSE | 8828.3789 | 2269.8172 | 1.4107 | 51 | 8.6513e-05 | 2023 | 1197.2249 | 732 | 0.094773 | 4.8334 | 795 | 0.08 | 1602
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10100 | FALSE | 18902.6869 | 16723.3035 | 10.3936 | 142 | 0.0001056 | 1504 | 1406.8011 | 635 | 0.094733 | 13.4521 | 796 | 0.13 | 1337
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | XR524 | FALSE | 17990.142 | 17523.6666 | 10.891 | 59 | 7.365e-05 | 2373 | 1425.9142 | 629 | 0.09443 | 5.5714 | 797 | 0.13 | 1349
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | CB | FALSE | 14024.7064 | 1067.201 | 0.66327 | 93 | 0.00014666 | 778 | 560.4187 | 1134 | 0.094346 | 8.7742 | 798 | 0.02 | 2531
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 854149 | FALSE | 1703.8848 | 1563.4443 | 0.97169 | 12 | 3.9219e-05 | 3281 | 2116.0059 | 424 | 0.094333 | 1.132 | 799 |  | 3095
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | CB | FALSE | 14181.9325 | 13470.2412 | 8.3718 | 64 | 8.6926e-05 | 2014 | 1158.1157 | 750 | 0.094159 | 6.0262 | 800 | 0.04 | 2092
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 373667 | FALSE | 6861.5817 | 5269.4021 | 3.275 | 45 | 0.00010834 | 1444 | 757.3214 | 967 | 0.09414 | 4.2363 | 801 |  | 2927
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 396 | FALSE | 25908.1895 | 25908.1895 | 16.102 | 182 | 0.00013862 | 887 | 571.5533 | 1129 | 0.093951 | 17.099 | 802 | 46.49 | 141
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | MR182 | FALSE | 11548.6884 | 10768.7759 | 6.6928 | 56 | 6.1377e-05 | 2738 | 1819.6137 | 502 | 0.093921 | 5.2596 | 803 | 0.09 | 1515
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 4786 | FALSE | 28973.985 | 28973.985 | 18.0074 | 173 | 9.6661e-05 | 1720 | 894.0898 | 886 | 0.09378 | 16.224 | 804 | 0.23 | 1115
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 77578 | FALSE | 51848.8987 | 34427.9014 | 21.3971 | 389 | 0.00014958 | 742 | 862.3434 | 907 | 0.09328 | 36.2858 | 805 | 0.14 | 1325
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 4744 | FALSE | 32972.1771 | 27938.0536 | 17.3636 | 161 | 0.00026417 | 184 | 386.3695 | 1311 | 0.093231 | 15.0101 | 806 | 0.03 | 2396
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 2704 | FALSE | 9132.5937 | 2300.3426 | 1.4297 | 76 | 0.00016088 | 633 | 611.8282 | 1093 | 0.093023 | 7.0698 | 807 | 0.54 | 874
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 826 | FALSE | 12455.7726 | 12455.7726 | 7.7413 | 89 | 0.00010691 | 1478 | 923.3771 | 872 | 0.092902 | 8.2683 | 808 | 15.71 | 347
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 233646 | FALSE | 18091.6284 | 15102.5612 | 9.3863 | 127 | 8.2168e-05 | 2147 | 1174.21 | 744 | 0.092653 | 11.7669 | 809 |  | 2976
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 75884 | FALSE | 18035.3275 | 17165.4943 | 10.6684 | 94 | 0.00017444 | 533 | 718.5697 | 1003 | 0.09258 | 8.7025 | 810 | 3.43 | 548
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 1402 | FALSE | 71104.0432 | 71104.0432 | 44.1915 | 541 | 9.1419e-05 | 1862 | 1211.8423 | 726 | 0.092281 | 49.924 | 811 | 35.4 | 214
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | CB | FALSE | 9345.3494 | 2462.2686 | 1.5303 | 66 | 0.00012054 | 1177 | 1190.2745 | 738 | 0.092174 | 6.0835 | 812 | 0.04 | 2090
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 660 | FALSE | 31347.0514 | 16353.7146 | 10.1639 | 233 | 0.00011883 | 1211 | 1011.3875 | 826 | 0.092166 | 21.4747 | 813 | 0.63 | 835
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 46960 | FALSE | 3112.6164 | 1465.0556 | 0.91054 | 14 | 5.4278e-05 | 2938 | 2071.3937 | 437 | 0.092145 | 1.29 | 814 | 0.02 | 2539
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 666 | FALSE | 21923.7063 | 19462.335 | 12.0959 | 90 | 5.9029e-05 | 2805 | 1514.7635 | 588 | 0.092048 | 8.2843 | 815 | 0.87 | 754
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 55612 | FALSE | 35781.5314 | 35781.5314 | 22.2384 | 93 | 0.00015401 | 707 | 611.9681 | 1092 | 0.090894 | 8.4532 | 816 | 0.12 | 1370
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 409622 | FALSE | 20757.639 | 20534.7896 | 12.7625 | 156 | 0.00034981 | 90 | 622.0881 | 1080 | 0.090831 | 14.1696 | 817 |  | 2825
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 13424 | FALSE | 5801.6622 | 2404.2277 | 1.4942 | 43 | 0.00013059 | 1000 | 649.8195 | 1066 | 0.090714 | 3.9007 | 818 | 0.03 | 2394
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 384360 | FALSE | 10034.7798 | 7892.4211 | 4.9052 | 70 | 9.2299e-05 | 1835 | 1163.0519 | 748 | 0.090426 | 6.3298 | 819 |  | 2667
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 1598 | FALSE | 53928.0023 | 53928.0023 | 33.5165 | 251 | 9.7528e-05 | 1700 | 806.3409 | 933 | 0.09042 | 22.6955 | 820 | 22.35 | 294
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 86816 | FALSE | 7103.5026 | 7103.5026 | 4.4149 | 51 | 0.00023289 | 272 | 393.4562 | 1304 | 0.090319 | 4.6062 | 821 | 6.82 | 458
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | M18 | FALSE | 28757.9291 | 24562.1098 | 15.2655 | 81 | 5.4886e-05 | 2918 | 1831.3141 | 496 | 0.090027 | 7.2922 | 822 | 0.57 | 861
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 948 | FALSE | 12598.6878 | 10159.6075 | 6.3142 | 73 | 6.6707e-05 | 2564 | 1385.8323 | 644 | 0.089784 | 6.5542 | 823 | 0.06 | 1788
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 212096 | FALSE | 6500.9175 | 4124.0159 | 2.5631 | 42 | 6.3229e-05 | 2670 | 1654.3016 | 540 | 0.089733 | 3.7688 | 824 |  | 3265
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 297862 | TRUE | 519.2262 | 503.2242 | 0.31276 | 4 | 7.9187e-05 | 2228 | 3345.084 | 219 | 0.089567 | 0.35827 | 825 |  | 3575
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 858898 | FALSE | 31911.4059 | 31551.7735 | 19.6096 | 152 | 4.9929e-05 | 3040 | 1510.095 | 592 | 0.089508 | 13.6052 | 826 |  | 3043
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 373772 | TRUE | 28.6691 | 28.6691 | 0.017818 | 2 | 0.00012505 | 1097 | 655.2599 | 1058 | 0.089417 | 0.17883 | 827 | 1.87 | 637
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 570 | FALSE | 34272.8021 | 28557.0384 | 17.7483 | 199 | 0.00010582 | 1500 | 921.351 | 874 | 0.089292 | 17.7691 | 828 | 0.22 | 1129
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 5100 | FALSE | 34326.3844 | 34326.3844 | 21.334 | 204 | 8.9144e-05 | 1942 | 1331.1763 | 667 | 0.089218 | 18.2004 | 829 | 0.33 | 989
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 88962 | FALSE | 6442.5415 | 3996.9259 | 2.4841 | 45 | 4.8649e-05 | 3070 | 1156.9132 | 752 | 0.089174 | 4.0128 | 830 | 0.04 | 2070
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 56026 | FALSE | 24339.1905 | 24339.1905 | 15.1269 | 158 | 0.00012905 | 1028 | 717.5714 | 1005 | 0.089061 | 14.0716 | 831 | 0.07 | 1750
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 528 | FALSE | 19817.3234 | 6048.4547 | 3.7591 | 110 | 0.00013971 | 873 | 614.5051 | 1089 | 0.08906 | 9.7966 | 832 | 0.03 | 2395
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 736 | FALSE | 55772.0682 | 55772.0682 | 34.6626 | 350 | 0.00013305 | 957 | 690.2141 | 1030 | 0.088841 | 31.0945 | 833 | 98.57 | 21
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | CB | FALSE | 21689.1163 | 18499.2196 | 11.4973 | 14 | 0.00021618 | 336 | 754.1992 | 970 | 0.088539 | 1.2395 | 834 | 0.04 | 2124
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 10580 | FALSE | 18949.2019 | 12416.9837 | 7.7172 | 129 | 0.00010187 | 1606 | 1422.4147 | 630 | 0.088489 | 11.415 | 835 | 0.05 | 1984
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 47872 | FALSE | 6709.5897 | 6709.5897 | 4.17 | 52 | 0.00017338 | 538 | 451.2799 | 1248 | 0.088422 | 4.5979 | 836 | 1.21 | 701
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | A14 | FALSE | 40416.4237 | 40416.4237 | 25.119 | 152 | 7.4204e-05 | 2351 | 1301.8625 | 681 | 0.088418 | 13.4395 | 837 | 0.07 | 1686
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 75252 | FALSE | 98047.1456 | 93174.0996 | 57.9081 | 401 | 7.7651e-05 | 2271 | 1110.9654 | 770 | 0.088153 | 35.3494 | 838 | 0.18 | 1204
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 1700 | FALSE | 35014.8434 | 34930.2373 | 21.7093 | 255 | 0.00014818 | 762 | 706.0979 | 1016 | 0.087918 | 22.4191 | 839 | 0.15 | 1281
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 339792 | FALSE | 5788.3897 | 4221.2236 | 2.6235 | 43 | 0.00011358 | 1331 | 632.6218 | 1077 | 0.087729 | 3.7723 | 840 |  | 3181
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 984552 | FALSE | 9221.3481 | 7304.6852 | 4.5399 | 53 | 7.8725e-05 | 2243 | 1388.9327 | 642 | 0.087511 | 4.6381 | 841 |  | 3254
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 80726 | FALSE | 29692.476 | 12661.4918 | 7.8692 | 217 | 0.00011841 | 1219 | 698.1741 | 1024 | 0.087369 | 18.9591 | 842 | 0.05 | 2014
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 348318 | TRUE | 597.0392 | 597.0392 | 0.37106 | 6 | 4.521e-05 | 3156 | 2033.0031 | 451 | 0.087346 | 0.52408 | 843 |  | 2972
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 76694 | FALSE | 7317.351 | 7317.351 | 4.5478 | 37 | 7.2614e-05 | 2401 | 1607.6376 | 560 | 0.087295 | 3.2299 | 844 | 0.06 | 1907
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 9190 | FALSE | 14438.9195 | 14438.9195 | 8.9738 | 104 | 0.00015927 | 649 | 560.2186 | 1135 | 0.087115 | 9.06 | 845 | 0.12 | 1405
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 75970 | FALSE | 11378.8384 | 11378.8384 | 7.072 | 33 | 0.0002301 | 284 | 549.4916 | 1145 | 0.08694 | 2.869 | 846 | 0.07 | 1700
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | CB | FALSE | 4772.9739 | 3724.6766 | 2.3149 | 47 | 0.00012677 | 1067 | 1037.4258 | 802 | 0.086583 | 4.0694 | 847 | 3.02 | 568
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 1590 | FALSE | 10388.8945 | 10388.8945 | 6.4567 | 63 | 0.00013775 | 898 | 828.3749 | 922 | 0.086534 | 5.4516 | 848 | 0.58 | 859
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | CB | FALSE | 45670.4217 | 45670.4217 | 28.3844 | 294 | 9.5334e-05 | 1751 | 1012.9872 | 821 | 0.086354 | 25.3881 | 849 | 0.47 | 909
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 7380 | FALSE | 45386.7416 | 20845.5533 | 12.9556 | 240 | 4.451e-05 | 3175 | 2480.8683 | 345 | 0.086218 | 20.6923 | 850 | 0.07 | 1707
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 48950 | FALSE | 20081.7793 | 20081.7793 | 12.4809 | 145 | 0.00013937 | 880 | 612.4235 | 1091 | 0.085979 | 12.467 | 851 | 0.08 | 1608
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 161818 | TRUE | 7658.7384 | 212.3638 | 0.13198 | 59 | 5.7073e-05 | 2859 | 1511.2201 | 590 | 0.08588 | 5.0669 | 852 | 0.02 | 2419
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 320270 | FALSE | 27707.7793 | 13648.6049 | 8.4827 | 137 | 5.4419e-05 | 2934 | 1519.0093 | 586 | 0.08574 | 11.7464 | 853 | 0.03 | 2384
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | XR176 | FALSE | 44222.2898 | 36252.5852 | 22.5311 | 309 | 8.4526e-05 | 2077 | 1005.2282 | 831 | 0.085689 | 26.478 | 854 | 0.3 | 1018
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | CB | FALSE | 10972.0561 | 9142.0744 | 5.6818 | 69 | 0.00014429 | 809 | 861.7339 | 908 | 0.08567 | 5.9113 | 855 | 0.08 | 1609
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 167726 | FALSE | 6114.3744 | 6114.3744 | 3.8001 | 50 | 7.7871e-05 | 2262 | 1006.5075 | 830 | 0.08544 | 4.272 | 856 |  | 2859
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 9765 | TRUE | 1507.3257 | 425.4979 | 0.26445 | 16 | 4.0376e-05 | 3257 | 1304.4493 | 680 | 0.085394 | 1.3663 | 857 | 1.11 | 715
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 87304 | FALSE | 23764.1584 | 4634.8119 | 2.8806 | 100 | 0.00010497 | 1530 | 1066.2761 | 788 | 0.085339 | 8.5339 | 858 | 0.01 | 2567
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | CB | FALSE | 79932.4071 | 51306.3985 | 31.8871 | 469 | 0.00011158 | 1379 | 802.5661 | 939 | 0.085283 | 39.9976 | 859 | 0.15 | 1300
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 537096 | TRUE | 844.1463 | 775.9765 | 0.48227 | 6 | 0.00013769 | 900 | 635.9861 | 1072 | 0.085228 | 0.51137 | 860 |  | 3492
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | CB | FALSE | 3161.2302 | 1492.4904 | 0.92759 | 19 | 0.00014572 | 793 | 421.9203 | 1271 | 0.085217 | 1.6191 | 861 | 0.04 | 2178
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 2004 | FALSE | 86935.2431 | 40225.06 | 25 | 174 | 5.0473e-05 | 3024 | 1960.2216 | 462 | 0.085175 | 14.8204 | 862 | 0.02 | 2549
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | V10 | FALSE | 7811.0705 | 3504.8307 | 2.1783 | 54 | 0.00010776 | 1457 | 473.6801 | 1219 | 0.085103 | 4.5956 | 863 |  | 2796
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | R82 | FALSE | 111857.9563 | 61789.4025 | 38.4024 | 563 | 6.819e-05 | 2530 | 1317.1207 | 675 | 0.084913 | 47.806 | 864 | 0.03 | 2235
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | CB | FALSE | 27411.8293 | 27411.8293 | 17.0366 | 139 | 0.00012425 | 1113 | 619.8955 | 1081 | 0.084888 | 11.7994 | 865 | 0.48 | 900
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | L3141 | FALSE | 22528.5486 | 22255.8256 | 13.8321 | 97 | 7.5574e-05 | 2322 | 1221.0879 | 717 | 0.084539 | 8.2002 | 866 | 0.09 | 1535
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | CB | FALSE | 35287.6178 | 28413.1031 | 17.6589 | 111 | 0.00022836 | 290 | 382.0524 | 1317 | 0.084457 | 9.3748 | 867 | 0.06 | 1910
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 104 | FALSE | 34991.65 | 34991.65 | 21.7475 | 235 | 0.00014639 | 782 | 473.3298 | 1220 | 0.084332 | 19.818 | 868 | 67.59 | 72
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 2748 | FALSE | 31538.4076 | 20831.4864 | 12.9469 | 245 | 0.00018393 | 480 | 692.2861 | 1029 | 0.084145 | 20.6156 | 869 | 0.1 | 1477
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 739448 | FALSE | 3763.2993 | 2860.1443 | 1.7776 | 12 | 4.5704e-05 | 3149 | 1064.5547 | 790 | 0.084104 | 1.0093 | 870 |  | 3393
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 51658 | FALSE | 14039.3789 | 13140.1209 | 8.1666 | 108 | 0.00011684 | 1253 | 818.1348 | 925 | 0.084002 | 9.0722 | 871 | 1.43 | 677
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 98568 | TRUE | 2444.4926 | 168.1421 | 0.1045 | 7 | 7.0182e-05 | 2465 | 834.7615 | 919 | 0.083995 | 0.58797 | 872 |  | 3457
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 637242 | FALSE | 35417.2163 | 27085.716 | 16.8339 | 193 | 7.1873e-05 | 2424 | 1184.0184 | 740 | 0.083893 | 16.1913 | 873 |  | 2879
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 507389 | TRUE | 305.6652 | 212.3341 | 0.13197 | 4 | 8.9376e-05 | 1934 | 719.0918 | 1002 | 0.083842 | 0.33537 | 874 |  | 3399
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 2228 | FALSE | 16654.619 | 5410.2105 | 3.3625 | 80 | 5.6416e-05 | 2878 | 1582.2639 | 568 | 0.082955 | 6.6364 | 875 | 0.03 | 2232
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 91948 | FALSE | 11942.5868 | 11942.5868 | 7.4224 | 69 | 0.00010599 | 1494 | 1019.808 | 815 | 0.082927 | 5.7219 | 876 | 0.99 | 733
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | XR366 | FALSE | 17766.1133 | 13567.8022 | 8.4324 | 129 | 7.1306e-05 | 2437 | 1012.8648 | 822 | 0.082848 | 10.6874 | 877 | 0.21 | 1134
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 685160 | TRUE | 2780.4715 | 943.7591 | 0.58655 | 17 | 5.0437e-05 | 3028 | 1467.3789 | 610 | 0.082766 | 1.407 | 878 |  | 3392
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 4994 | FALSE | 6920.6464 | 2185.8295 | 1.3585 | 45 | 0.00012652 | 1071 | 520.9041 | 1182 | 0.082765 | 3.7244 | 879 | 0.64 | 830
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 737236 | FALSE | 14223.4405 | 14101.6239 | 8.7642 | 88 | 0.00012645 | 1074 | 720.3446 | 999 | 0.082425 | 7.2534 | 880 |  | 2868
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 79140 | FALSE | 19909.2046 | 15742.3512 | 9.7839 | 154 | 9.382e-05 | 1797 | 973.1017 | 848 | 0.082367 | 12.6845 | 881 | 7.99 | 438
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 454432 | FALSE | 23226.2401 | 23226.2401 | 14.4352 | 112 | 5.5708e-05 | 2898 | 1234.8209 | 710 | 0.08233 | 9.221 | 882 |  | 2714
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 51790 | FALSE | 13931.0144 | 12725.5168 | 7.909 | 106 | 0.00015838 | 659 | 660.4485 | 1052 | 0.082229 | 8.7163 | 883 | 0.33 | 990
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 144510 | FALSE | 8266.8346 | 5010.1846 | 3.1138 | 41 | 8.3654e-05 | 2104 | 950.8265 | 860 | 0.08218 | 3.3694 | 884 |  | 2896
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 5202 | FALSE | 27474.7329 | 26267.8985 | 16.3256 | 162 | 8.8527e-05 | 1973 | 910.6874 | 881 | 0.082155 | 13.3091 | 885 | 0.12 | 1403
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 11236 | FALSE | 31777.9091 | 31777.9091 | 19.7501 | 143 | 0.00011636 | 1262 | 616.8333 | 1086 | 0.081838 | 11.7029 | 886 | 0.05 | 2012
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 3485 | FALSE | 2803.9876 | 2803.9876 | 1.7427 | 23 | 0.00011552 | 1286 | 723.112 | 996 | 0.081749 | 1.8802 | 887 |  | 2910
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 632 | FALSE | 23697.8024 | 23697.8024 | 14.7283 | 81 | 6.7966e-05 | 2537 | 1288.5976 | 686 | 0.081559 | 6.6063 | 888 | 0.05 | 2027
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4609 | FALSE | 7321.9227 | 7321.9227 | 4.5506 | 41 | 3.728e-05 | 3310 | 2145.8949 | 414 | 0.081381 | 3.3366 | 889 | 0.06 | 1911
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7004 | FALSE | 31981.9475 | 12745.3246 | 7.9213 | 128 | 5.8428e-05 | 2822 | 1357.6846 | 659 | 0.081062 | 10.3759 | 890 | 0.03 | 2338
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | XR398 | FALSE | 63835.5147 | 60665.5292 | 37.7039 | 341 | 8.3663e-05 | 2103 | 945.2451 | 864 | 0.080766 | 27.5412 | 891 | 0.67 | 814
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 1821 | FALSE | 6061.921 | 5767.6056 | 3.5846 | 33 | 6.9086e-05 | 2504 | 1429.8724 | 624 | 0.080483 | 2.6559 | 892 | 0.08 | 1594
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 95756 | FALSE | 29109.9093 | 11950.3804 | 7.4272 | 200 | 7.0248e-05 | 2461 | 1033.0935 | 805 | 0.080379 | 16.0759 | 893 | 0.03 | 2343
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | M82 | FALSE | 23986.1463 | 17447.2632 | 10.8435 | 149 | 4.471e-05 | 3168 | 1573.1869 | 570 | 0.080327 | 11.9687 | 894 | 0.04 | 2147
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 2056 | FALSE | 10443.0868 | 8069.9513 | 5.0155 | 70 | 0.00011546 | 1289 | 677.9317 | 1037 | 0.080308 | 5.6215 | 895 | 3.29 | 551
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 808 | FALSE | 8110.4608 | 4081.7731 | 2.5368 | 39 | 8.0754e-05 | 2186 | 1061.2531 | 791 | 0.0803 | 3.1317 | 896 | 0.09 | 1528
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 3290 | FALSE | 21820.8937 | 21820.8937 | 13.5618 | 135 | 0.00032761 | 105 | 278.5419 | 1474 | 0.080281 | 10.8379 | 897 | 0.08 | 1641
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 372132 | TRUE | 2259.794 | 673.2222 | 0.41841 | 13 | 0.00010261 | 1583 | 1099.8675 | 775 | 0.08025 | 1.0433 | 898 |  | 3103
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 807988 | FALSE | 6722.2779 | 6706.2477 | 4.168 | 15 | 0.00010987 | 1413 | 855.2361 | 912 | 0.080023 | 1.2003 | 899 |  | 3415
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 643162 | FALSE | 9798.1377 | 5532.3244 | 3.4384 | 41 | 6.7079e-05 | 2555 | 1192.2958 | 736 | 0.079941 | 3.2776 | 900 |  | 3054
10896 | CMC 1102CB | 183111102 | CMC 1102 | CB | TRUE | 581.8342 | 581.8342 | 0.36161 | 5 | 0.00015983 | 644 | 548.9355 | 1146 | 0.079905 | 0.39953 | 901 | 0.03 | 2328
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 4300 | FALSE | 43675.508 | 43384.1036 | 26.9634 | 268 | 0.00011959 | 1194 | 736.9291 | 987 | 0.079811 | 21.3893 | 902 | 28.67 | 249
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 1703 | FALSE | 3959.9015 | 1455.5285 | 0.90462 | 7 | 2.6035e-05 | 3487 | 3088.567 | 257 | 0.079525 | 0.55668 | 903 | 0.01 | 2618
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 935216 | FALSE | 33848.7529 | 33848.7529 | 21.0371 | 204 | 0.00011214 | 1365 | 509.4897 | 1191 | 0.079474 | 16.2127 | 904 |  | 3025
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 1510 | FALSE | 41028.1557 | 41028.1557 | 25.4992 | 243 | 8.893e-05 | 1952 | 939.2458 | 866 | 0.079411 | 19.297 | 905 | 0.18 | 1216
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 19632 | FALSE | 14659.9971 | 8997.9268 | 5.5922 | 110 | 0.00013387 | 944 | 1009.1241 | 828 | 0.07935 | 8.7285 | 906 | 23.44 | 286
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | A08 | FALSE | 39406.6597 | 16842.5186 | 10.4677 | 257 | 7.6018e-05 | 2308 | 953.5418 | 857 | 0.079335 | 20.3891 | 907 | 0.05 | 2006
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | CB | FALSE | 35256.7174 | 21554.4713 | 13.3962 | 149 | 5.7418e-05 | 2852 | 1255.3202 | 698 | 0.079316 | 11.8181 | 908 | 3.17 | 557
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | CB | FALSE | 5135.5453 | 5135.5453 | 3.1918 | 17 | 0.00032833 | 104 | 166.3867 | 1733 | 0.079299 | 1.3481 | 909 | 0.73 | 794
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | Q12 | FALSE | 25798.2458 | 18203.0478 | 11.3133 | 142 | 5.3235e-05 | 2958 | 1483.0103 | 602 | 0.079257 | 11.2544 | 910 | 0.12 | 1401
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 188426 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00011833 | 1221 | 665.6862 | 1046 | 0.078773 | 0.078773 | 911 |  | 3613
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 4281 | FALSE | 21439.832 | 21439.832 | 13.3249 | 138 | 8.4234e-05 | 2085 | 980.9559 | 844 | 0.078646 | 10.8532 | 912 | 0.09 | 1527
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 7863 | FALSE | 6797.0988 | 6797.0988 | 4.2244 | 42 | 6.1162e-05 | 2744 | 1254.5183 | 699 | 0.078616 | 3.3019 | 913 | 0.06 | 1859
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 93384 | FALSE | 27406.0322 | 25967.2197 | 16.1387 | 101 | 6.3629e-05 | 2660 | 1407.9794 | 632 | 0.078583 | 7.9369 | 914 | 0.06 | 1857
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 1314 | FALSE | 1489.219 | 1489.219 | 0.92556 | 13 | 0.00014408 | 813 | 554.638 | 1141 | 0.078235 | 1.0171 | 915 | 7.88 | 439
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 2248 | FALSE | 14727.9744 | 14727.9744 | 9.1535 | 28 | 6.5811e-05 | 2594 | 1037.9427 | 801 | 0.077859 | 2.18 | 916 | 0.05 | 1922
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | Q10 | FALSE | 38031.0006 | 38031.0006 | 23.6364 | 289 | 6.4596e-05 | 2621 | 1216.6013 | 719 | 0.077836 | 22.4946 | 917 | 7.07 | 452
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | CB | FALSE | 18838.7982 | 5515.7018 | 3.428 | 135 | 0.00010957 | 1419 | 752.8216 | 973 | 0.077778 | 10.5 | 918 | 0.02 | 2544
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | XR268 | FALSE | 12802.5937 | 12802.5937 | 7.9569 | 61 | 0.00011557 | 1284 | 557.5427 | 1138 | 0.077596 | 4.7333 | 919 | 0.46 | 913
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 1312 | FALSE | 15822.8795 | 15822.8795 | 9.834 | 120 | 0.00013526 | 925 | 772.6153 | 957 | 0.077577 | 9.3092 | 920 | 0.15 | 1291
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | V38 | FALSE | 27926.3564 | 19405.5321 | 12.0606 | 212 | 7.3599e-05 | 2379 | 651.082 | 1062 | 0.077544 | 16.4392 | 921 | 0.17 | 1245
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 307342 | TRUE | 573.1034 | 354.0238 | 0.22003 | 6 | 0.00013565 | 923 | 341.2059 | 1386 | 0.077416 | 0.46449 | 922 |  | 3441
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 24550 | FALSE | 34688.2788 | 17797.4846 | 11.0612 | 203 | 9.3917e-05 | 1795 | 616.7423 | 1087 | 0.077338 | 15.6996 | 923 | 0.07 | 1711
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 514 | FALSE | 8494.876 | 5391.2208 | 3.3507 | 71 | 0.00014873 | 755 | 482.2809 | 1214 | 0.077302 | 5.4884 | 924 | 0.09 | 1537
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 49746 | TRUE | 601.9007 | 601.9007 | 0.37408 | 3 | 0.00034014 | 97 | 221.8686 | 1601 | 0.077172 | 0.23152 | 925 | 0.04 | 2076
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 630 | FALSE | 6902.8394 | 2654.0652 | 1.6495 | 55 | 7.7866e-05 | 2263 | 873.6447 | 897 | 0.077168 | 4.2442 | 926 | 0.03 | 2363
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 201311 | FALSE | 17668.9636 | 12645.7551 | 7.8594 | 108 | 6.4312e-05 | 2634 | 1215.4291 | 722 | 0.077053 | 8.3218 | 927 |  | 3015
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 35706 | FALSE | 16269.027 | 16269.027 | 10.1113 | 97 | 0.00041981 | 62 | 185.2954 | 1670 | 0.076898 | 7.4591 | 928 | 4.82 | 505
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 2410 | FALSE | 12099.1952 | 5248.3008 | 3.2618 | 96 | 0.00011208 | 1366 | 705.3971 | 1019 | 0.076748 | 7.3678 | 929 | 0.05 | 1959
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 87402 | FALSE | 18273.7697 | 18273.7697 | 11.3572 | 42 | 9.1928e-05 | 1846 | 973.3911 | 847 | 0.07664 | 3.2189 | 930 | 1.23 | 698
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 3760 | FALSE | 10446.6343 | 10415.8967 | 6.4735 | 6 | 4.6244e-05 | 3131 | 4483.9501 | 110 | 0.076506 | 0.45904 | 931 | 0.03 | 2370
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | CB | FALSE | 5307.8327 | 5307.8327 | 3.2988 | 25 | 0.0001265 | 1072 | 430.0286 | 1260 | 0.076253 | 1.9063 | 932 | 12.67 | 370
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 4614 | FALSE | 20206.8972 | 20206.8972 | 12.5587 | 95 | 0.00011071 | 1396 | 701.2564 | 1022 | 0.075773 | 7.1985 | 933 |  | 3306
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 37536 | FALSE | 8687.6907 | 8687.6907 | 5.3994 | 60 | 4.0037e-05 | 3267 | 1761.4133 | 511 | 0.075515 | 4.5309 | 934 | 0.07 | 1729
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 1437 | FALSE | 7854.9148 | 4577.3445 | 2.8448 | 39 | 5.9276e-05 | 2795 | 1361.2842 | 657 | 0.075332 | 2.9379 | 935 | 0.03 | 2404
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 583202 | FALSE | 15783.8472 | 7874.8461 | 4.8942 | 106 | 0.00010066 | 1631 | 594.6514 | 1106 | 0.075101 | 7.9607 | 936 | 0.05 | 2004
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 538 | FALSE | 10176.8073 | 10176.8073 | 6.3249 | 48 | 6.409e-05 | 2642 | 1480.7363 | 603 | 0.074937 | 3.597 | 937 | 2.14 | 620
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 854266 | TRUE | 966.2653 | 321.4105 | 0.19976 | 6 | 9.5722e-05 | 1736 | 1072.2651 | 785 | 0.074827 | 0.44896 | 938 |  | 3418
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7099 | FALSE | 12439.4387 | 12439.4387 | 7.7312 | 83 | 0.00011588 | 1273 | 664.3931 | 1047 | 0.074794 | 6.2079 | 939 | 0.28 | 1036
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 274 | FALSE | 29743.739 | 10398.2127 | 6.4625 | 173 | 0.00011599 | 1270 | 494.2707 | 1207 | 0.074787 | 12.9382 | 940 | 1.24 | 695
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 1606 | TRUE | 42761.0948 | 254.3531 | 0.15808 | 280 | 7.0898e-05 | 2446 | 1248.3017 | 701 | 0.074511 | 20.863 | 941 | 0.02 | 2551
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | CB | FALSE | 3483.5782 | 3483.5782 | 2.1651 | 16 | 0.00013085 | 995 | 558.6934 | 1136 | 0.074456 | 1.1913 | 942 | 21.08 | 302
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | CB | FALSE | 21509.9694 | 15956.2359 | 9.9169 | 121 | 5.192e-05 | 2995 | 1288.0652 | 687 | 0.074106 | 8.9669 | 943 | 0.03 | 2320
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 999 | FALSE | 3715.0604 | 3715.0604 | 2.3089 | 22 | 0.00010639 | 1488 | 1017.494 | 818 | 0.074075 | 1.6297 | 944 | 0.09 | 1529
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 6751 | FALSE | 36483.9202 | 36483.9202 | 22.6749 | 139 | 0.00018185 | 499 | 410.6545 | 1284 | 0.073927 | 10.2759 | 945 | 39.14 | 190
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | CB | FALSE | 15601.4012 | 15601.4012 | 9.6963 | 97 | 0.00011323 | 1340 | 789.9349 | 952 | 0.073848 | 7.1632 | 946 | 0.18 | 1203
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 134232 | FALSE | 11553.3534 | 2618.9112 | 1.6277 | 89 | 0.0001535 | 717 | 426.3987 | 1264 | 0.0737 | 6.5593 | 947 |  | 3092
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | CB | TRUE | 2722.4304 | 952.8122 | 0.59218 | 22 | 0.00019758 | 405 | 236.9089 | 1576 | 0.073682 | 1.621 | 948 | 0.13 | 1352
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | Y24 | FALSE | 31605.3339 | 30845.6135 | 19.1707 | 91 | 6.8807e-05 | 2514 | 1387.2959 | 643 | 0.073569 | 6.6947 | 949 | 0.26 | 1061
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | CB | TRUE | 6455.7985 | 567.3027 | 0.35258 | 55 | 0.00018028 | 511 | 272.2112 | 1489 | 0.073561 | 4.0458 | 950 | 0.64 | 831
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 792 | FALSE | 33585.8452 | 31119.1615 | 19.3407 | 180 | 9.905e-05 | 1667 | 711.86 | 1012 | 0.073389 | 13.2101 | 951 | 87.74 | 36
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | V40 | FALSE | 37151.701 | 23652.2282 | 14.7 | 194 | 7.9558e-05 | 2220 | 1050.089 | 797 | 0.073389 | 14.2374 | 952 | 0.06 | 1795
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 47488 | FALSE | 33425.2179 | 30588.7641 | 19.011 | 207 | 0.00011402 | 1320 | 706.1851 | 1015 | 0.07338 | 15.1897 | 953 | 0.19 | 1176
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | Y44 | FALSE | 18687.8674 | 16745.9311 | 10.4077 | 45 | 6.0111e-05 | 2770 | 1213.3424 | 724 | 0.073295 | 3.2983 | 954 | 0.1 | 1484
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | A70 | FALSE | 107377.7331 | 39764.0285 | 24.7135 | 659 | 6.9565e-05 | 2486 | 1197.409 | 731 | 0.073157 | 48.2106 | 955 | 3.57 | 542
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | R322 | FALSE | 12336.4699 | 12336.4699 | 7.6672 | 44 | 3.5123e-05 | 3349 | 2118.7775 | 422 | 0.073065 | 3.2149 | 956 | 0.06 | 1886
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 9460 | FALSE | 18052.5322 | 17926.192 | 11.1412 | 91 | 8.3561e-05 | 2112 | 856.971 | 910 | 0.073014 | 6.6443 | 957 | 0.01 | 2611
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 84944 | FALSE | 93674.3078 | 93674.3078 | 58.219 | 439 | 7.7782e-05 | 2268 | 921.9165 | 873 | 0.072725 | 31.9262 | 958 |  | 2719
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 810594 | TRUE | 1080.6364 | 899.4073 | 0.55899 | 6 | 0.0001145 | 1307 | 459.6008 | 1235 | 0.072684 | 0.4361 | 959 |  | 3228
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | CB | FALSE | 25933.7558 | 8735.2446 | 5.429 | 200 | 0.00014636 | 784 | 521.6714 | 1181 | 0.072647 | 14.5295 | 960 | 0.55 | 869
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 980192 | FALSE | 6178.6453 | 6178.6453 | 3.8401 | 19 | 3.4326e-05 | 3362 | 2382.3266 | 363 | 0.072592 | 1.3793 | 961 |  | 3513
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | CB | TRUE | 4213.006 | 696.6837 | 0.43299 | 36 | 6.8096e-05 | 2534 | 412.1878 | 1283 | 0.07222 | 2.5999 | 962 | 0.06 | 1816
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | CB | FALSE | 29664.4521 | 21174.1488 | 13.1598 | 91 | 0.00013717 | 905 | 720.7685 | 998 | 0.072102 | 6.5613 | 963 | 0.02 | 2565
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 4086 | FALSE | 18494.2051 | 18494.2051 | 11.4942 | 66 | 0.00012787 | 1052 | 634.8288 | 1073 | 0.072098 | 4.7585 | 964 | 0.12 | 1393
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 132 | FALSE | 40702.0776 | 40702.0776 | 25.2965 | 184 | 7.3728e-05 | 2369 | 1030.4196 | 808 | 0.071994 | 13.2468 | 965 | 4.02 | 529
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 1596 | FALSE | 35104.5465 | 35104.5465 | 21.8176 | 132 | 6.0424e-05 | 2763 | 1180.3203 | 741 | 0.071922 | 9.4937 | 966 | 0.01 | 2583
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 13490 | FALSE | 8773.504 | 6875.4256 | 4.2731 | 49 | 0.00015838 | 660 | 538.4381 | 1161 | 0.071878 | 3.522 | 967 | 0.05 | 1975
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 49144 | FALSE | 34128.6869 | 29574.1503 | 18.3805 | 169 | 0.00016343 | 606 | 803.7485 | 937 | 0.071512 | 12.0855 | 968 | 0.08 | 1646
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | CB | TRUE | 26588.5909 | 184.0196 | 0.11437 | 188 | 9.7905e-05 | 1694 | 539.3221 | 1159 | 0.0715 | 13.442 | 969 | 0.02 | 2564
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 7134 | FALSE | 37777.9012 | 32518.1243 | 20.2101 | 172 | 9.5256e-05 | 1759 | 696.6949 | 1025 | 0.071297 | 12.2631 | 970 | 0.09 | 1546
4319 | MESA 11016111 | 182821101 | MESA 1101 | 6111 | FALSE | 41513.5486 | 39023.9015 | 24.2535 | 202 | 4.9757e-05 | 3042 | 1337.456 | 665 | 0.071153 | 14.3729 | 971 | 9.09 | 413
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 740076 | TRUE | 14283.4902 | 632.3767 | 0.39302 | 106 | 0.00010531 | 1512 | 793.8066 | 947 | 0.071071 | 7.5335 | 972 |  | 2963
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 799924 | TRUE | 621.6151 | 621.6151 | 0.38634 | 4 | 0.00011059 | 1397 | 1327.4203 | 669 | 0.070818 | 0.28327 | 973 |  | 3334
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 724884 | FALSE | 22726.0215 | 22589.092 | 14.0392 | 167 | 0.00017254 | 546 | 443.793 | 1254 | 0.070791 | 11.822 | 974 |  | 2712
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 469810 | FALSE | 9545.8932 | 3464.1714 | 2.153 | 14 | 8.3298e-05 | 2125 | 778.0104 | 955 | 0.070672 | 0.98941 | 975 |  | 3354
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 980944 | FALSE | 26900.3072 | 16783.2453 | 10.4309 | 198 | 0.00019807 | 404 | 366.1605 | 1345 | 0.070566 | 13.9721 | 976 |  | 2798
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 76068 | FALSE | 31093.7701 | 27642.9269 | 17.1802 | 232 | 7.7128e-05 | 2284 | 1055.6938 | 794 | 0.070348 | 16.3207 | 977 | 6.25 | 470
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | CB | TRUE | 4411.9174 | 914.1112 | 0.56812 | 33 | 8.0383e-05 | 2194 | 401.4638 | 1294 | 0.070136 | 2.3145 | 978 |  | 3048
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 306476 | FALSE | 16292.4669 | 3106.377 | 1.9306 | 49 | 0.00010648 | 1486 | 598.7531 | 1101 | 0.069853 | 3.4228 | 979 |  | 3316
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 65454 | FALSE | 3114.2101 | 2176.3172 | 1.3526 | 23 | 6.0844e-05 | 2754 | 1192.0123 | 737 | 0.069594 | 1.6007 | 980 | 2.09 | 622
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 1500 | FALSE | 41880.4686 | 41880.4686 | 26.0289 | 261 | 0.00012847 | 1038 | 750.2992 | 975 | 0.069495 | 18.1383 | 981 | 0.21 | 1153
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 8920 | TRUE | 158.1242 | 158.1242 | 0.098275 | 2 | 0.00017718 | 518 | 499.4912 | 1200 | 0.069477 | 0.13895 | 982 | 0.19 | 1196
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 10000 | FALSE | 53656.1229 | 47097.1904 | 29.2711 | 230 | 6.3422e-05 | 2664 | 1330.8242 | 668 | 0.069198 | 15.9156 | 983 | 0.02 | 2464
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | V36 | FALSE | 21377.0625 | 18028.895 | 11.205 | 150 | 6.1929e-05 | 2723 | 1033.145 | 804 | 0.069118 | 10.3677 | 984 | 6.65 | 464
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 77086 | FALSE | 6051.2822 | 4371.5846 | 2.717 | 47 | 0.00020917 | 363 | 405.3593 | 1291 | 0.068998 | 3.2429 | 985 |  | 3331
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 85152 | FALSE | 37332.1384 | 37332.1384 | 23.2021 | 279 | 4.413e-05 | 3188 | 1657.8134 | 539 | 0.068983 | 19.2463 | 986 | 8.2 | 433
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 544 | TRUE | 16214.8056 | 786.2676 | 0.48867 | 98 | 8.9779e-05 | 1918 | 761.7873 | 963 | 0.068781 | 6.7406 | 987 |  | 2803
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 97188 | FALSE | 10919.7899 | 10919.7899 | 6.7867 | 71 | 0.00011852 | 1217 | 794.0069 | 946 | 0.068613 | 4.8715 | 988 | 0.06 | 1870
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | R2838 | FALSE | 32896.73 | 32896.73 | 20.4455 | 210 | 3.7309e-05 | 3308 | 2069.6718 | 438 | 0.068544 | 14.3942 | 989 | 0.21 | 1136
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | CB | TRUE | 46.711 | 46.711 | 0.029031 | 1 | 0.00015165 | 723 | 451.5011 | 1247 | 0.068469 | 0.068469 | 990 | 4.71 | 509
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 835115 | FALSE | 29192.1081 | 29192.1081 | 18.143 | 191 | 7.8182e-05 | 2253 | 868.4883 | 902 | 0.068398 | 13.0639 | 991 |  | 2775
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | Y70 | FALSE | 13947.1347 | 10839.1211 | 6.7366 | 61 | 5.1111e-05 | 3011 | 1300.1446 | 683 | 0.068291 | 4.1658 | 992 | 0.02 | 2489
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 295566 | TRUE | 3409.6411 | 751.534 | 0.46708 | 18 | 5.22e-05 | 2987 | 1215.0443 | 723 | 0.068263 | 1.2287 | 993 |  | 2864
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 1804 | FALSE | 69024.1301 | 69024.1301 | 42.8988 | 394 | 0.00011734 | 1239 | 495.1119 | 1205 | 0.068197 | 26.8697 | 994 | 0.15 | 1295
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 2260 | FALSE | 36303.3353 | 25414.2279 | 15.795 | 185 | 7.1484e-05 | 2433 | 1004.259 | 833 | 0.067786 | 12.5404 | 995 | 0.08 | 1667
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 583708 | FALSE | 1263.0794 | 1011.3641 | 0.62857 | 11 | 9.3798e-05 | 1800 | 952.2243 | 858 | 0.067762 | 0.74538 | 996 |  | 3189
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | CB | FALSE | 2698.3212 | 1098.894 | 0.68297 | 23 | 9.8521e-05 | 1678 | 430.579 | 1258 | 0.067722 | 1.5576 | 997 | 0.47 | 908
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | Y46 | FALSE | 76660.9296 | 50653.8838 | 31.4816 | 277 | 4.2068e-05 | 3223 | 1429.3656 | 626 | 0.067522 | 18.7037 | 998 | 0.13 | 1364
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | CB | FALSE | 21488.1146 | 9459.2642 | 5.879 | 171 | 0.00014623 | 785 | 382.8028 | 1314 | 0.067405 | 11.5263 | 999 | 0.05 | 1971
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 456397 | FALSE | 2239.0721 | 2239.0721 | 1.3916 | 19 | 9.783e-05 | 1696 | 785.4652 | 954 | 0.067328 | 1.2792 | 1000 |  | 3391
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | CB | FALSE | 3697.5337 | 3697.5337 | 2.298 | 32 | 0.00012582 | 1082 | 762.0604 | 962 | 0.067293 | 2.1534 | 1001 | 0.05 | 1960
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 146070 | FALSE | 22680.3921 | 20479.5896 | 12.7281 | 167 | 6.6917e-05 | 2560 | 1071.9697 | 786 | 0.067012 | 11.191 | 1002 |  | 2871
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 64908 | FALSE | 10254.7707 | 6238.0239 | 3.877 | 84 | 0.00035803 | 84 | 246.1325 | 1550 | 0.066995 | 5.6276 | 1003 | 0.84 | 767
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 53732 | FALSE | 12542.8 | 12542.8 | 7.7954 | 77 | 9.701e-05 | 1714 | 766.0355 | 959 | 0.066862 | 5.1484 | 1004 | 17.55 | 332
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 43924 | FALSE | 15096.7446 | 12523.7999 | 7.7836 | 107 | 0.00015399 | 708 | 446.2971 | 1252 | 0.066852 | 7.1532 | 1005 | 91.99 | 30
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | P02 | TRUE | 11656.6661 | 515.0322 | 0.32009 | 93 | 5.0919e-05 | 3016 | 803.9256 | 936 | 0.06682 | 6.2143 | 1006 | 0.32 | 993
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 172096 | TRUE | 1240.5827 | 425.5098 | 0.26446 | 12 | 0.00013435 | 939 | 425.6324 | 1267 | 0.06657 | 0.79884 | 1007 |  | 3077
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | CB | FALSE | 20191.5411 | 12387.7147 | 7.699 | 131 | 0.00018717 | 460 | 356.2256 | 1362 | 0.06648 | 8.7089 | 1008 | 0.06 | 1904
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 39256 | FALSE | 42581.0612 | 42581.0612 | 26.4643 | 287 | 0.00012638 | 1077 | 694.1209 | 1026 | 0.066296 | 19.0271 | 1009 | 0.26 | 1068
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 49484 | FALSE | 4257.4421 | 4257.4421 | 2.646 | 27 | 0.000124 | 1121 | 880.5018 | 890 | 0.06627 | 1.7893 | 1010 | 0.02 | 2543
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 2664 | FALSE | 17552.7674 | 12910.8902 | 8.0242 | 132 | 0.00019724 | 409 | 283.8161 | 1468 | 0.066185 | 8.7364 | 1011 | 7.85 | 440
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 98998 | TRUE | 20001.4994 | 118.1019 | 0.073401 | 136 | 8.5457e-05 | 2044 | 370.2201 | 1337 | 0.066014 | 8.9779 | 1012 | 0.02 | 2466
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | A18 | FALSE | 29115.6622 | 14189.3642 | 8.8187 | 188 | 6.7022e-05 | 2556 | 932.8875 | 868 | 0.065994 | 12.4068 | 1013 | 1.58 | 663
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 141073 | FALSE | 3422.9373 | 1996.4523 | 1.2408 | 27 | 0.00018845 | 450 | 208.8541 | 1621 | 0.065722 | 1.7745 | 1014 |  | 3174
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 9220 | FALSE | 18356.5403 | 17704.0281 | 11.0031 | 123 | 0.00012861 | 1036 | 658.7055 | 1055 | 0.065661 | 8.0763 | 1015 | 0.19 | 1191
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 1342 | FALSE | 62297.5033 | 33351.1972 | 20.7279 | 440 | 0.00011151 | 1385 | 593.3765 | 1111 | 0.065366 | 28.7609 | 1016 | 1.74 | 645
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | W531R | FALSE | 17380.2917 | 10443.673 | 6.4908 | 100 | 6.9698e-05 | 2483 | 735.723 | 988 | 0.065356 | 6.5356 | 1017 | 0.07 | 1731
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 13322 | FALSE | 66617.6825 | 66617.6825 | 41.4032 | 490 | 6.243e-05 | 2708 | 1047.9717 | 798 | 0.065331 | 32.0124 | 1018 | 0.31 | 1005
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 21160 | FALSE | 38269.4773 | 38269.4773 | 23.7846 | 194 | 4.477e-05 | 3167 | 1259.0438 | 695 | 0.065187 | 12.6462 | 1019 | 0.07 | 1757
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 126697 | FALSE | 1766.1223 | 1641.863 | 1.0204 | 10 | 6.1082e-05 | 2745 | 1011.3761 | 827 | 0.065062 | 0.65062 | 1020 |  | 3433
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | CB | FALSE | 2729.0129 | 2729.0129 | 1.6961 | 12 | 0.00018833 | 451 | 298.7993 | 1449 | 0.06474 | 0.77689 | 1021 | 0.03 | 2234
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 124 | FALSE | 29762.4384 | 29762.4384 | 18.4975 | 99 | 0.00011564 | 1282 | 546.7406 | 1151 | 0.064597 | 6.3951 | 1022 | 4.64 | 511
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | Q08 | FALSE | 19981.628 | 19981.628 | 12.4187 | 148 | 5.6432e-05 | 2876 | 1236.4827 | 708 | 0.064559 | 9.5547 | 1023 | 4.37 | 521
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 542920 | FALSE | 2484.216 | 2034.8319 | 1.2647 | 10 | 2.943e-05 | 3433 | 2350.3357 | 372 | 0.064427 | 0.64427 | 1024 |  | 3478
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | R12 | FALSE | 64632.5351 | 52796.2686 | 32.8131 | 278 | 5.1483e-05 | 3005 | 1212.0624 | 725 | 0.064341 | 17.8868 | 1025 | 0.1 | 1470
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 1993 | FALSE | 4771.9686 | 4470.3512 | 2.7783 | 39 | 6.0989e-05 | 2747 | 818.0593 | 926 | 0.064212 | 2.5043 | 1026 | 3.17 | 558
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 66730 | FALSE | 1703.3079 | 1703.3079 | 1.0586 | 6 | 0.00011857 | 1215 | 919.8595 | 875 | 0.064035 | 0.38421 | 1027 | 0.49 | 897
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 87432 | FALSE | 21925.1583 | 15708.5355 | 9.7629 | 81 | 7.1409e-05 | 2436 | 994.1805 | 837 | 0.063901 | 5.176 | 1028 | 0.09 | 1521
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 1325 | FALSE | 13829.5499 | 13829.5499 | 8.5951 | 80 | 0.00012793 | 1047 | 449.2232 | 1249 | 0.063613 | 5.0891 | 1029 | 12.01 | 378
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 1216 | FALSE | 30877.2329 | 21628.5531 | 13.4422 | 182 | 0.00012873 | 1035 | 525.6183 | 1178 | 0.063522 | 11.561 | 1030 | 0.07 | 1733
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 18935 | FALSE | 10773.8274 | 10773.8274 | 6.696 | 76 | 0.00011327 | 1337 | 910.0927 | 882 | 0.063224 | 4.805 | 1031 | 8.29 | 432
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | N30 | FALSE | 32768.3238 | 32768.3238 | 20.3656 | 120 | 6.3151e-05 | 2674 | 927.1943 | 870 | 0.063152 | 7.5782 | 1032 | 0.09 | 1530
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 2070 | FALSE | 15059.4591 | 14786.6222 | 9.1899 | 72 | 0.00014395 | 814 | 498.0458 | 1203 | 0.063106 | 4.5436 | 1033 | 0.07 | 1760
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 116402 | FALSE | 11255.0357 | 3810.8828 | 2.3685 | 64 | 5.7437e-05 | 2850 | 1320.2856 | 674 | 0.062979 | 4.0307 | 1034 |  | 2740
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 186912 | FALSE | 97116.525 | 94273.5723 | 58.5914 | 606 | 9.5424e-05 | 1747 | 711.7437 | 1013 | 0.06292 | 38.1293 | 1035 | 0.18 | 1223
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 4170 | FALSE | 15319.6405 | 15319.6405 | 9.5212 | 45 | 4.2938e-05 | 3210 | 1356.0496 | 661 | 0.062779 | 2.8251 | 1036 | 0.03 | 2358
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 8189 | FALSE | 1685.4401 | 1685.4401 | 1.0475 | 11 | 0.00035454 | 86 | 166.396 | 1732 | 0.062553 | 0.68809 | 1037 | 0.02 | 2537
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | CB | FALSE | 27174.1674 | 1828.844 | 1.1366 | 175 | 0.0001054 | 1510 | 467.1503 | 1226 | 0.062374 | 10.9155 | 1038 | 0.02 | 2425
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 203380 | TRUE | 3178.2991 | 809.5956 | 0.50317 | 26 | 0.00010239 | 1592 | 687.7534 | 1032 | 0.062335 | 1.6207 | 1039 |  | 3423
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 12342 | TRUE | 1750.136 | 352.0949 | 0.21883 | 16 | 0.00013409 | 942 | 663.7688 | 1049 | 0.062293 | 0.99668 | 1040 | 0.32 | 996
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 13478 | FALSE | 24836.1056 | 19846.6513 | 12.3348 | 169 | 0.0001203 | 1180 | 594.448 | 1107 | 0.062159 | 10.5049 | 1041 | 0.09 | 1570
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 2094 | FALSE | 27452.3558 | 25248.6295 | 15.6921 | 139 | 0.00021404 | 343 | 379.7853 | 1321 | 0.062103 | 8.6323 | 1042 | 3.85 | 533
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 2028 | FALSE | 17437.7183 | 17437.7183 | 10.8376 | 86 | 0.00015423 | 702 | 243.285 | 1559 | 0.062015 | 5.3333 | 1043 | 0.41 | 939
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 12282 | FALSE | 58482.1143 | 58482.1143 | 36.3469 | 261 | 0.00011986 | 1190 | 718.4403 | 1004 | 0.061928 | 16.1631 | 1044 | 0.18 | 1206
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 2537 | FALSE | 8030.1143 | 8030.1143 | 4.9907 | 37 | 9.2031e-05 | 1844 | 618.6971 | 1083 | 0.061762 | 2.2852 | 1045 | 0.2 | 1156
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | A46 | TRUE | 13904.7944 | 633.1098 | 0.39348 | 94 | 8.1941e-05 | 2157 | 550.2411 | 1144 | 0.06175 | 5.8045 | 1046 | 0.02 | 2447
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 51738 | TRUE | 1844.3225 | 26.6806 | 0.016582 | 19 | 0.00013923 | 882 | 441.8941 | 1255 | 0.061564 | 1.1697 | 1047 | 17.24 | 335
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | V78 | FALSE | 47471.3302 | 47471.3302 | 29.5036 | 164 | 6.8753e-05 | 2516 | 918.2768 | 876 | 0.061453 | 10.0783 | 1048 | 0.19 | 1179
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | TRUE | 63.3636 | 63.3636 | 0.039381 | 1 | 0.00010321 | 1565 | 595.1616 | 1105 | 0.061428 | 0.061428 | 1049 | 8.51 | 425
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 127563 | FALSE | 11105.9314 | 11105.9314 | 6.9024 | 63 | 7.2173e-05 | 2413 | 803.5682 | 938 | 0.061336 | 3.8642 | 1050 | 23.56 | 283
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 351038 | FALSE | 22506.9662 | 2661.6552 | 1.6542 | 130 | 7.0209e-05 | 2462 | 1068.3127 | 787 | 0.061316 | 7.971 | 1051 |  | 3029
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 1496 | FALSE | 26084.969 | 23526.9728 | 14.6221 | 201 | 7.6403e-05 | 2297 | 864.7228 | 905 | 0.06121 | 12.3032 | 1052 | 0.06 | 1790
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | CB | TRUE | 56.7484 | 56.7484 | 0.035269 | 1 | 0.0001609 | 632 | 380.3958 | 1320 | 0.061207 | 0.061207 | 1053 |  | 3497
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 2408 | FALSE | 18614.5661 | 18614.5661 | 11.569 | 124 | 0.000106 | 1493 | 623.6203 | 1079 | 0.060864 | 7.5471 | 1054 | 0.34 | 981
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | CB | FALSE | 4357.8457 | 4357.8457 | 2.7084 | 3 | 0.00010885 | 1430 | 808.7175 | 931 | 0.060819 | 0.18246 | 1055 | 0.02 | 2472
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | CB | TRUE | 11952.1608 | 777.7423 | 0.48337 | 85 | 0.00011707 | 1245 | 452.6669 | 1244 | 0.060715 | 5.1608 | 1056 | 0.06 | 1775
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 452 | FALSE | 31530.7427 | 8129.076 | 5.0523 | 207 | 0.00010226 | 1598 | 743.369 | 981 | 0.060708 | 12.5666 | 1057 | 0.67 | 816
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 670 | TRUE | 4937.5444 | 587.1475 | 0.36491 | 43 | 0.00012733 | 1058 | 393.8186 | 1302 | 0.06056 | 2.6041 | 1058 | 0.03 | 2292
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | CB | FALSE | 13703.2012 | 13703.2012 | 8.5166 | 51 | 0.00018978 | 443 | 315.2875 | 1424 | 0.060495 | 3.0852 | 1059 | 2.08 | 624
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 2013 | TRUE | 7412.4545 | 238.9679 | 0.14852 | 51 | 5.2169e-05 | 2988 | 888.4761 | 888 | 0.06048 | 3.0845 | 1060 | 0.44 | 923
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | L5407 | FALSE | 29410.8857 | 29410.8857 | 18.279 | 153 | 4.5895e-05 | 3142 | 1349.9596 | 663 | 0.060463 | 9.2508 | 1061 | 0.09 | 1522
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 56972 | FALSE | 13791.0471 | 13791.0471 | 8.5712 | 57 | 0.00011753 | 1234 | 612.4545 | 1090 | 0.060186 | 3.4306 | 1062 | 0.04 | 2114
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | CB | FALSE | 3229.2079 | 2904.3184 | 1.805 | 19 | 0.00016629 | 580 | 366.1668 | 1344 | 0.05984 | 1.137 | 1063 | 0.04 | 2199
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 708161 | FALSE | 1824.6356 | 1615.0007 | 1.0037 | 12 | 0.00012306 | 1133 | 461.5277 | 1234 | 0.059606 | 0.71527 | 1064 |  | 3411
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6064 | FALSE | 13322.7276 | 10776.9352 | 6.6979 | 66 | 0.00027944 | 157 | 244.0042 | 1557 | 0.059515 | 3.928 | 1065 | 1.74 | 646
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 36680 | FALSE | 32219.8242 | 15055.3944 | 9.357 | 265 | 8.2363e-05 | 2143 | 715.9031 | 1008 | 0.059472 | 15.7601 | 1066 | 2.94 | 572
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 844168 | FALSE | 18710.7045 | 7309.0201 | 4.5426 | 100 | 5.7956e-05 | 2836 | 877.0353 | 894 | 0.059437 | 5.9437 | 1067 |  | 3097
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 2110 | FALSE | 32283.1191 | 31798.2221 | 19.7627 | 224 | 0.00013772 | 899 | 464.9832 | 1230 | 0.059423 | 13.3106 | 1068 | 0.21 | 1147
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 696 | FALSE | 11659.1184 | 6037.9333 | 3.7526 | 79 | 7.4535e-05 | 2343 | 617.4166 | 1085 | 0.059025 | 4.663 | 1069 | 0.32 | 991
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 1540 | TRUE | 20738.5879 | 256.3874 | 0.15935 | 157 | 0.00010932 | 1426 | 527.982 | 1175 | 0.058865 | 9.2418 | 1070 | 0.04 | 2210
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 2708 | FALSE | 17128.5396 | 15094.9992 | 9.3816 | 124 | 0.00011703 | 1249 | 634.212 | 1074 | 0.058775 | 7.2881 | 1071 | 0.09 | 1533
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 460414 | FALSE | 10774.9077 | 8655.1604 | 5.3792 | 38 | 8.546e-05 | 2043 | 785.6181 | 953 | 0.058719 | 2.2313 | 1072 |  | 2688
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 48750 | FALSE | 28839.2375 | 28839.2375 | 17.9237 | 165 | 9.931e-05 | 1660 | 705.0697 | 1020 | 0.058621 | 9.6724 | 1073 | 19.06 | 315
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 82622 | FALSE | 41703.3816 | 41703.3816 | 25.9188 | 254 | 8.8106e-05 | 1980 | 753.4327 | 972 | 0.058508 | 14.8609 | 1074 | 0.2 | 1166
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | CB | FALSE | 38608.5003 | 37939.8486 | 23.5798 | 181 | 6.1591e-05 | 2729 | 1004.6328 | 832 | 0.058399 | 10.5701 | 1075 | 0.03 | 2280
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 512912 | FALSE | 3140.8885 | 1435.1217 | 0.89193 | 23 | 6.2939e-05 | 2682 | 742.0792 | 982 | 0.058383 | 1.3428 | 1076 |  | 2970
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | CB | FALSE | 63324.3345 | 63324.3345 | 39.3563 | 375 | 0.00014192 | 841 | 477.8627 | 1217 | 0.058367 | 21.8875 | 1077 | 0.76 | 785
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 2562 | FALSE | 55111.7044 | 31122.7322 | 19.3429 | 222 | 5.835e-05 | 2824 | 1193.0263 | 734 | 0.057915 | 12.8572 | 1078 | 0.05 | 1950
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 338 | FALSE | 23338.4107 | 12496.8829 | 7.7669 | 176 | 0.00010195 | 1604 | 593.3845 | 1110 | 0.05791 | 10.1921 | 1079 | 7.05 | 454
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 4523 | FALSE | 4420.7892 | 1471.0588 | 0.91427 | 28 | 9.5345e-05 | 1750 | 593.4447 | 1109 | 0.057806 | 1.6186 | 1080 |  | 3449
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 289947 | TRUE | 3212.1673 | 447.6357 | 0.27821 | 21 | 8.5184e-05 | 2054 | 855.7073 | 911 | 0.057658 | 1.2108 | 1081 |  | 3472
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1087 | FALSE | 3157.1282 | 3157.1282 | 1.9622 | 22 | 0.00010484 | 1532 | 532.5062 | 1170 | 0.05764 | 1.2681 | 1082 | 7.64 | 443
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 816852 | FALSE | 70141.7466 | 20545.6876 | 12.7692 | 423 | 4.2631e-05 | 3214 | 1516.9463 | 587 | 0.057549 | 24.3431 | 1083 |  | 2655
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | CB | FALSE | 20142.5456 | 20085.8093 | 12.4834 | 141 | 0.00015851 | 658 | 382.2019 | 1316 | 0.057543 | 8.1136 | 1084 | 0.64 | 827
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 7070 | FALSE | 26486.1632 | 10307.0829 | 6.4059 | 132 | 5.0065e-05 | 3036 | 1217.7073 | 718 | 0.057494 | 7.5892 | 1085 | 0.03 | 2323
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 1654 | FALSE | 28221.2564 | 28221.2564 | 17.5396 | 168 | 8.908e-05 | 1943 | 662.2613 | 1051 | 0.057486 | 9.6576 | 1086 | 0.1 | 1492
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 3745 | FALSE | 7247.2343 | 7247.2343 | 4.5042 | 52 | 0.00018327 | 486 | 535.7815 | 1164 | 0.057415 | 2.9856 | 1087 | 1.01 | 730
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | CB | FALSE | 50985.8349 | 50985.8349 | 31.6879 | 293 | 8.4764e-05 | 2072 | 750.5824 | 974 | 0.05741 | 16.8213 | 1088 | 0.1 | 1456
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 751990 | FALSE | 39452.6049 | 39436.6029 | 24.51 | 243 | 0.00013521 | 926 | 355.8632 | 1363 | 0.057382 | 13.9439 | 1089 |  | 2702
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 51584 | FALSE | 35041.5534 | 35041.5534 | 21.7785 | 224 | 7.7619e-05 | 2272 | 869.1368 | 901 | 0.057318 | 12.8393 | 1090 | 0.08 | 1655
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1404 | FALSE | 5740.3584 | 2402.8891 | 1.4934 | 47 | 0.0001882 | 452 | 397.9556 | 1298 | 0.057199 | 2.6884 | 1091 | 0.03 | 2347
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | CB | FALSE | 15329.2524 | 14012.7161 | 8.709 | 102 | 8.2611e-05 | 2139 | 748.7975 | 976 | 0.057183 | 5.8326 | 1092 | 18.75 | 318
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 89150 | FALSE | 15332.2939 | 15332.2939 | 9.5291 | 88 | 0.00012195 | 1149 | 582.7266 | 1121 | 0.057148 | 5.029 | 1093 | 0.48 | 905
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | CB | FALSE | 2345.4974 | 1187.935 | 0.73831 | 21 | 7.6681e-05 | 2290 | 471.5803 | 1223 | 0.057097 | 1.199 | 1094 | 0.67 | 818
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 4756 | FALSE | 18962.2338 | 15139.4165 | 9.4092 | 95 | 0.000145 | 802 | 459.0245 | 1236 | 0.057032 | 5.4181 | 1095 | 0.05 | 1943
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 2124 | FALSE | 5026.2322 | 5026.2322 | 3.1238 | 6 | 0.00058653 | 20 | 170.3508 | 1714 | 0.057006 | 0.34203 | 1096 | 1.87 | 636
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | CB | FALSE | 1058.7166 | 1058.7166 | 0.658 | 7 | 0.00022337 | 306 | 221.0499 | 1604 | 0.057005 | 0.39904 | 1097 | 0.06 | 1873
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 901690 | FALSE | 63574.4496 | 60028.2631 | 37.3078 | 306 | 5.6692e-05 | 2868 | 1011.6278 | 825 | 0.056927 | 17.4196 | 1098 | 0.62 | 841
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | CB | FALSE | 36057.8693 | 23579.7024 | 14.6549 | 190 | 0.00011058 | 1399 | 511.8263 | 1189 | 0.056867 | 10.8047 | 1099 | 0.02 | 2512
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 853720 | FALSE | 50276.8108 | 50276.8108 | 31.2472 | 140 | 6.2471e-05 | 2705 | 1012.617 | 823 | 0.056625 | 7.9275 | 1100 |  | 2684
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 37368 | FALSE | 9786.5772 | 9786.5772 | 6.0824 | 48 | 7.032e-05 | 2459 | 880.1307 | 892 | 0.056596 | 2.7166 | 1101 | 0.06 | 1898
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | CB | FALSE | 4540.438 | 4454.6417 | 2.7686 | 35 | 0.00019479 | 417 | 248.765 | 1543 | 0.056508 | 1.9778 | 1102 | 0.3 | 1017
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 37410 | FALSE | 8875.6069 | 8413.1179 | 5.2288 | 42 | 0.00021128 | 354 | 348.1422 | 1375 | 0.056472 | 2.3718 | 1103 | 0.04 | 2173
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | CB | FALSE | 15108.5071 | 11908.479 | 7.4012 | 76 | 7.9073e-05 | 2231 | 565.89 | 1132 | 0.056447 | 4.29 | 1104 | 0.45 | 919
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | CB | FALSE | 24719.9919 | 16900.9683 | 10.504 | 116 | 0.0002473 | 224 | 245.6875 | 1552 | 0.056321 | 6.5332 | 1105 | 3.13 | 561
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 775992 | FALSE | 5059.1291 | 3381.5311 | 2.1016 | 34 | 0.00012419 | 1115 | 374.1489 | 1330 | 0.056251 | 1.9125 | 1106 |  | 2954
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 461703 | FALSE | 1414.65 | 1414.65 | 0.87921 | 8 | 7.7835e-05 | 2265 | 327.199 | 1402 | 0.05614 | 0.44912 | 1107 |  | 3274
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 51800 | FALSE | 15718.5986 | 14796.5287 | 9.1961 | 128 | 0.00016264 | 616 | 342.7814 | 1383 | 0.05603 | 7.1719 | 1108 | 3.81 | 534
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | M80 | FALSE | 93735.5013 | 93735.5013 | 58.257 | 397 | 4.5707e-05 | 3147 | 1161.6823 | 749 | 0.055911 | 22.1966 | 1109 | 0.42 | 930
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 1991 | FALSE | 11465.3295 | 11465.3295 | 7.1257 | 51 | 0.00016331 | 608 | 395.6046 | 1299 | 0.055786 | 2.8451 | 1110 | 56.35 | 99
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 6697 | FALSE | 6657.3541 | 6657.3541 | 4.1376 | 46 | 0.00010476 | 1534 | 551.7785 | 1143 | 0.055767 | 2.5653 | 1111 | 0.1 | 1462
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 11270 | FALSE | 20312.1456 | 20312.1456 | 12.6241 | 123 | 0.00012756 | 1056 | 499.3074 | 1201 | 0.055685 | 6.8493 | 1112 | 0.11 | 1443
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 5040 | FALSE | 6507.5662 | 6507.5662 | 4.0445 | 46 | 0.0002406 | 244 | 218.6982 | 1609 | 0.055628 | 2.5589 | 1113 | 20.75 | 304
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 171410 | FALSE | 7035.3214 | 2217.9639 | 1.3785 | 40 | 0.00011961 | 1192 | 536.0514 | 1163 | 0.055603 | 2.2241 | 1114 |  | 3405
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 450 | FALSE | 30451.6805 | 9311.1997 | 5.7869 | 208 | 0.00012825 | 1043 | 484.352 | 1210 | 0.055438 | 11.531 | 1115 | 0.04 | 2211
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | CB | FALSE | 14529.9116 | 11213.2305 | 6.9691 | 99 | 0.00015794 | 663 | 471.1517 | 1224 | 0.05535 | 5.4797 | 1116 | 0.06 | 1842
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 35492 | FALSE | 34847.1678 | 16074.976 | 9.9907 | 219 | 9.7259e-05 | 1708 | 426.1888 | 1265 | 0.055239 | 12.0973 | 1117 | 0.03 | 2257
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 829470 | FALSE | 16595.0205 | 16595.0205 | 10.3139 | 93 | 0.00011788 | 1231 | 515.0682 | 1185 | 0.055226 | 5.136 | 1118 |  | 3047
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8110 | FALSE | 13110.3306 | 13110.3306 | 8.1481 | 99 | 0.0001169 | 1252 | 657.3966 | 1057 | 0.055185 | 5.4634 | 1119 | 0.15 | 1283
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 859443 | TRUE | 777.6394 | 475.2837 | 0.29539 | 5 | 4.9574e-05 | 3047 | 1445.6352 | 616 | 0.055167 | 0.27584 | 1120 |  | 3268
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | CB | FALSE | 9029.352 | 9029.352 | 5.6118 | 38 | 3.4574e-05 | 3359 | 1447.0842 | 615 | 0.055113 | 2.0943 | 1121 | 0 | 2649
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 85002 | FALSE | 57093.5104 | 57093.5104 | 35.4838 | 394 | 7.6265e-05 | 2302 | 729.1639 | 992 | 0.055026 | 21.6802 | 1122 | 0.87 | 759
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 13412 | FALSE | 62439.7255 | 62439.7255 | 38.8065 | 333 | 0.00011911 | 1202 | 811.1905 | 930 | 0.055018 | 18.321 | 1123 | 0.87 | 756
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 61736 | FALSE | 26875.6469 | 19558.6498 | 12.1558 | 129 | 6.0018e-05 | 2773 | 726.4231 | 994 | 0.054986 | 7.0932 | 1124 | 0.05 | 1936
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 1576 | FALSE | 12974.577 | 12974.577 | 8.0638 | 51 | 7.9987e-05 | 2206 | 832.2405 | 921 | 0.054922 | 2.801 | 1125 | 0.07 | 1744
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 352 | FALSE | 19238.6019 | 9086.2434 | 5.6471 | 123 | 0.00014867 | 757 | 547.944 | 1149 | 0.054876 | 6.7498 | 1126 | 0.04 | 2196
6906 | IONE 1101CB | 163881101 | IONE 1101 | CB | FALSE | 22613.9915 | 2970.8687 | 1.8464 | 85 | 0.00012529 | 1093 | 646.6464 | 1068 | 0.054859 | 4.663 | 1127 | 0.02 | 2492
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 6807 | FALSE | 7894.5527 | 7894.5527 | 4.9065 | 49 | 0.00014837 | 759 | 586.6523 | 1116 | 0.054517 | 2.6713 | 1128 | 0.08 | 1650
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 75140 | FALSE | 32224.0105 | 13968.9875 | 8.6818 | 238 | 4.9487e-05 | 3050 | 824.0667 | 924 | 0.054483 | 12.967 | 1129 | 0.07 | 1713
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 831781 | FALSE | 2564.8738 | 1186.1396 | 0.73719 | 19 | 7.3782e-05 | 2367 | 806.9369 | 932 | 0.054336 | 1.0324 | 1130 |  | 3304
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 9722 | FALSE | 62437.5165 | 62437.5165 | 38.8052 | 359 | 0.00010174 | 1610 | 529.226 | 1174 | 0.054308 | 19.4965 | 1131 | 0.52 | 890
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | XR152 | FALSE | 20635.5048 | 14045.9028 | 8.7296 | 156 | 8.0844e-05 | 2185 | 646.2065 | 1069 | 0.054285 | 8.4685 | 1132 | 0.08 | 1583
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | CB | TRUE | 830.42 | 224.6189 | 0.1396 | 9 | 0.00020912 | 364 | 241.4035 | 1563 | 0.054215 | 0.48794 | 1133 | 0.02 | 2507
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 135854 | FALSE | 4250.0634 | 2325.1244 | 1.4451 | 34 | 6.0566e-05 | 2759 | 1134.6908 | 761 | 0.053974 | 1.8351 | 1134 |  | 3213
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 1588 | FALSE | 13991.4401 | 13991.4401 | 8.6957 | 33 | 0.00018106 | 503 | 584.74 | 1118 | 0.053968 | 1.7809 | 1135 | 0.19 | 1195
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 2642 | FALSE | 7497.8568 | 7497.8568 | 4.6599 | 27 | 9.0401e-05 | 1902 | 716.2407 | 1006 | 0.053841 | 1.4537 | 1136 | 0.03 | 2270
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 2014 | FALSE | 35984.1335 | 35984.1335 | 22.3643 | 181 | 0.00010418 | 1548 | 602.3767 | 1097 | 0.053762 | 9.731 | 1137 | 0.2 | 1157
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 63464 | FALSE | 21920.8692 | 21920.8692 | 13.6239 | 70 | 0.00012137 | 1160 | 659.6276 | 1053 | 0.05356 | 3.7492 | 1138 | 0.13 | 1359
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 47966 | FALSE | 27271.3222 | 27271.3222 | 16.9492 | 167 | 0.00020988 | 360 | 215.8045 | 1610 | 0.053445 | 8.9254 | 1139 | 0.13 | 1355
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1564 | FALSE | 17092.5832 | 1891.6003 | 1.1756 | 133 | 7.329e-05 | 2387 | 869.3002 | 900 | 0.053412 | 7.1038 | 1140 | 0.62 | 839
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 814616 | TRUE | 3902.6921 | 157.4015 | 0.097826 | 28 | 8.7257e-05 | 2006 | 602.3323 | 1098 | 0.053409 | 1.4955 | 1141 |  | 2683
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 694042 | TRUE | 972.0471 | 972.0471 | 0.60413 | 8 | 0.00011883 | 1210 | 338.8363 | 1389 | 0.053395 | 0.42716 | 1142 |  | 3427
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 7742 | FALSE | 73623.591 | 73535.6671 | 45.7027 | 475 | 9.9171e-05 | 1663 | 595.5649 | 1104 | 0.053392 | 25.3612 | 1143 | 1.43 | 675
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | CB | FALSE | 22863.3142 | 22355.1304 | 13.8938 | 170 | 0.0001075 | 1464 | 527.7867 | 1176 | 0.053282 | 9.058 | 1144 | 0.12 | 1366
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 8974 | FALSE | 21278.6691 | 21278.6691 | 13.2248 | 149 | 0.00020534 | 378 | 324.7416 | 1406 | 0.05299 | 7.8956 | 1145 | 76.03 | 55
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 322 | FALSE | 23201.9813 | 22860.7646 | 14.2081 | 167 | 0.00013802 | 893 | 458.1425 | 1238 | 0.052976 | 8.847 | 1146 | 35.69 | 212
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | M88 | FALSE | 24723.9577 | 4969.351 | 3.0885 | 85 | 4.85e-05 | 3076 | 599.8118 | 1100 | 0.052933 | 4.4993 | 1147 | 0.01 | 2589
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 8884 | FALSE | 12033.5669 | 12033.5669 | 7.4789 | 74 | 0.00017464 | 530 | 305.5705 | 1438 | 0.052785 | 3.9061 | 1148 | 48.31 | 129
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 2500 | FALSE | 25777.1884 | 25777.1884 | 16.0206 | 106 | 0.00032433 | 107 | 205.0308 | 1627 | 0.052654 | 5.5813 | 1149 | 11.96 | 380
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 4500 | FALSE | 132540.1743 | 38902.9544 | 24.1783 | 516 | 4.6379e-05 | 3128 | 1229.9776 | 714 | 0.052537 | 27.1089 | 1150 | 0.03 | 2255
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 1302 | FALSE | 23388.5169 | 22389.9711 | 13.9155 | 113 | 5.0169e-05 | 3034 | 1215.8532 | 721 | 0.052453 | 5.9272 | 1151 | 0.06 | 1889
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | CB | FALSE | 6175.4075 | 6175.4075 | 3.838 | 9 | 9.2622e-05 | 1830 | 515.1474 | 1184 | 0.052345 | 0.4711 | 1152 | 0.01 | 2588
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 244246 | FALSE | 1936.2709 | 1936.2709 | 1.2034 | 11 | 0.00016313 | 610 | 330.8536 | 1396 | 0.052269 | 0.57496 | 1153 |  | 3548
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 51484 | FALSE | 26385.5393 | 24741.7275 | 15.3771 | 195 | 0.0001406 | 862 | 372.49 | 1333 | 0.052211 | 10.1812 | 1154 | 0.17 | 1239
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 975698 | FALSE | 7671.0517 | 1441.7984 | 0.89608 | 44 | 4.3563e-05 | 3200 | 962.1828 | 852 | 0.052194 | 2.2966 | 1155 |  | 3170
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 612 | FALSE | 6362.7002 | 6362.7002 | 3.9544 | 25 | 8.4863e-05 | 2067 | 719.6048 | 1000 | 0.05213 | 1.3033 | 1156 | 0.42 | 931
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 776244 | TRUE | 783.9385 | 274.5802 | 0.17065 | 5 | 5.5048e-05 | 2909 | 540.4117 | 1158 | 0.052117 | 0.26059 | 1157 |  | 3366
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 4947 | FALSE | 16652.8009 | 16652.8009 | 10.3498 | 56 | 0.00016312 | 611 | 298.2938 | 1450 | 0.052018 | 2.913 | 1158 | 9.04 | 414
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 7108 | FALSE | 20715.9427 | 15478.9307 | 9.6202 | 99 | 5.144e-05 | 3007 | 993.4887 | 838 | 0.05186 | 5.1341 | 1159 | 0.06 | 1876
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 72036 | FALSE | 21135.8241 | 20864.4611 | 12.9673 | 105 | 8.1485e-05 | 2168 | 844.1543 | 916 | 0.051819 | 5.441 | 1160 | 14.82 | 354
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 37506 | FALSE | 18602.139 | 18602.139 | 11.5613 | 77 | 0.00015655 | 678 | 345.7654 | 1377 | 0.051705 | 3.9812 | 1161 | 4.56 | 516
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | CB | FALSE | 10891.762 | 10891.762 | 6.7693 | 40 | 7.3648e-05 | 2374 | 760.2437 | 965 | 0.051564 | 2.0626 | 1162 | 0.19 | 1197
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | CB | FALSE | 4864.6418 | 2361.7078 | 1.4678 | 33 | 0.00010062 | 1634 | 651.0467 | 1063 | 0.051416 | 1.6967 | 1163 | 0.02 | 2516
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 960 | FALSE | 8826.9021 | 6237.2835 | 3.8765 | 33 | 0.00010013 | 1642 | 470.8479 | 1225 | 0.051413 | 1.6966 | 1164 | 0.04 | 2083
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 90970 | FALSE | 6924.4221 | 2317.6472 | 1.4404 | 45 | 0.00014799 | 763 | 359.43 | 1356 | 0.051234 | 2.3055 | 1165 | 0.91 | 749
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | CB | FALSE | 20034.2871 | 12973.5363 | 8.0631 | 159 | 0.00012464 | 1103 | 555.1824 | 1140 | 0.051116 | 8.1275 | 1166 | 0.08 | 1582
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 569005 | FALSE | 3858.1769 | 1152.5978 | 0.71634 | 38 | 7.7445e-05 | 2278 | 606.2479 | 1095 | 0.051027 | 1.939 | 1167 |  | 3255
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | CB | FALSE | 10545.3693 | 10545.3693 | 6.554 | 31 | 0.00031506 | 112 | 137.2983 | 1822 | 0.050873 | 1.5771 | 1168 | 0.17 | 1226
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 737698 | TRUE | 340.8251 | 324.8619 | 0.2019 | 3 | 4.5459e-05 | 3153 | 1051.0501 | 795 | 0.050749 | 0.15225 | 1169 |  | 3626
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 50548 | TRUE | 7824.3085 | 154.2272 | 0.095853 | 58 | 0.00014087 | 856 | 418.2026 | 1274 | 0.050695 | 2.9403 | 1170 | 1.85 | 638
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 684566 | FALSE | 4872.6951 | 4856.693 | 3.0185 | 4 | 3.3492e-05 | 3376 | 2480.1079 | 347 | 0.050626 | 0.20251 | 1171 |  | 3437
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 2424 | FALSE | 30415.1718 | 30186.9031 | 18.7613 | 141 | 6.6531e-05 | 2572 | 747.4809 | 977 | 0.050559 | 7.1288 | 1172 | 0.17 | 1231
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 286542 | FALSE | 9381.8687 | 3501.8559 | 2.1764 | 25 | 2.3634e-05 | 3508 | 2087.6942 | 432 | 0.050527 | 1.2632 | 1173 |  | 3581
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 148 | FALSE | 24974.2018 | 24850.3478 | 15.4446 | 107 | 5.3405e-05 | 2952 | 932.2932 | 869 | 0.050374 | 5.39 | 1174 | 0.13 | 1343
2728 | MESA 1103M72 | 182821103 | MESA 1103 | M72 | FALSE | 24045.3968 | 13551.8371 | 8.4225 | 180 | 5.9996e-05 | 2776 | 772.2065 | 958 | 0.050224 | 9.0403 | 1175 | 0.09 | 1574
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 1508 | FALSE | 43792.5733 | 43792.5733 | 27.2173 | 249 | 0.00022481 | 303 | 269.7872 | 1498 | 0.050062 | 12.4656 | 1176 | 0.5 | 893
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 664 | FALSE | 17972.9054 | 15503.1919 | 9.6353 | 140 | 0.00013278 | 964 | 291.1861 | 1461 | 0.050043 | 7.006 | 1177 | 0.12 | 1389
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 32120 | FALSE | 65924.4872 | 65394.3269 | 40.6428 | 485 | 0.00015495 | 695 | 454.7289 | 1240 | 0.049959 | 24.23 | 1178 | 0.23 | 1120
1827 | BELL 11082226 | 152701108 | BELL 1108 | 2226 | FALSE | 41003.1194 | 38762.6482 | 24.0911 | 329 | 0.00015086 | 729 | 321.4507 | 1412 | 0.049738 | 16.3638 | 1179 | 0.14 | 1330
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 83288 | FALSE | 27936.7507 | 27936.7507 | 17.3628 | 140 | 0.00010219 | 1600 | 523.0336 | 1179 | 0.049736 | 6.9631 | 1180 | 56.24 | 100
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 1490 | FALSE | 24262.143 | 16986.9503 | 10.5575 | 122 | 4.6732e-05 | 3120 | 1014.4444 | 820 | 0.0497 | 6.0634 | 1181 | 0.01 | 2607
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | XR258 | FALSE | 42613.4021 | 35307.703 | 21.9439 | 117 | 7.1286e-05 | 2438 | 813.0901 | 929 | 0.049692 | 5.814 | 1182 | 0.07 | 1728
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 552 | FALSE | 24092.9744 | 15233.6156 | 9.4678 | 172 | 0.00013239 | 975 | 420.6103 | 1272 | 0.049565 | 8.5251 | 1183 | 2.64 | 591
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 654924 | FALSE | 8067.2123 | 4423.0701 | 2.749 | 61 | 8.0217e-05 | 2200 | 663.8303 | 1048 | 0.049343 | 3.0099 | 1184 |  | 2692
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | M52 | FALSE | 56469.342 | 54530.2399 | 33.8908 | 131 | 6.7691e-05 | 2540 | 719.2711 | 1001 | 0.04915 | 6.4386 | 1185 | 0.09 | 1551
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 55798 | FALSE | 37886.6196 | 37886.6196 | 23.5467 | 246 | 0.00011154 | 1383 | 632.8382 | 1075 | 0.049086 | 12.0752 | 1186 | 6.76 | 461
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 2243 | FALSE | 3051.2175 | 3051.2175 | 1.8963 | 16 | 0.00019188 | 434 | 257.113 | 1528 | 0.049051 | 0.78482 | 1187 | 4.86 | 503
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 1070 | FALSE | 13188.3135 | 12735.6646 | 7.9153 | 100 | 8.36e-05 | 2108 | 545.0696 | 1153 | 0.048737 | 4.8737 | 1188 | 0.08 | 1639
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 36902 | FALSE | 23754.9885 | 19990.5557 | 12.4242 | 147 | 6.372e-05 | 2656 | 753.8177 | 971 | 0.048735 | 7.1641 | 1189 | 0.05 | 2037
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | MR276 | FALSE | 6265.9535 | 6199.9698 | 3.8533 | 42 | 0.00011011 | 1409 | 507.3387 | 1193 | 0.048684 | 2.0447 | 1190 | 0.45 | 920
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 51676 | FALSE | 18975.7232 | 12910.4516 | 8.0239 | 145 | 0.00015332 | 718 | 372.9974 | 1332 | 0.048603 | 7.0475 | 1191 | 1.53 | 667
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 894956 | FALSE | 2635.3424 | 1243.2231 | 0.77267 | 16 | 4.142e-05 | 3237 | 1280.1289 | 689 | 0.048471 | 0.77554 | 1192 |  | 3371
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 567884 | FALSE | 4535.2993 | 4025.5628 | 2.5019 | 27 | 5.6021e-05 | 2887 | 815.5904 | 927 | 0.048164 | 1.3004 | 1193 |  | 2926
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 1602 | FALSE | 36538.7848 | 29307.7542 | 18.2149 | 109 | 0.00014214 | 837 | 344.2493 | 1379 | 0.048111 | 5.244 | 1194 | 0.07 | 1681
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 292 | FALSE | 31568.6739 | 25055.0465 | 15.5718 | 165 | 0.00011528 | 1294 | 534.9666 | 1165 | 0.048057 | 7.9294 | 1195 | 0.1 | 1486
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 1760 | FALSE | 20336.5883 | 15610.272 | 9.7018 | 73 | 0.00026452 | 183 | 220.0765 | 1605 | 0.048043 | 3.5072 | 1196 | 0 | 2647
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 4160 | FALSE | 34990.3559 | 34990.3559 | 21.7466 | 194 | 0.00015367 | 716 | 332.5299 | 1395 | 0.047994 | 9.3109 | 1197 | 0.11 | 1435
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | CB | FALSE | 26803.1335 | 19300.4618 | 11.9953 | 191 | 0.00043617 | 57 | 153.1917 | 1768 | 0.047992 | 9.1665 | 1198 | 0.08 | 1590
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 1216 | FALSE | 8821.9491 | 8821.9491 | 5.4829 | 32 | 4.4432e-05 | 3178 | 673.2647 | 1041 | 0.04796 | 1.5347 | 1199 | 0.02 | 2470
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | V76 | FALSE | 30510.6388 | 30510.6388 | 18.9625 | 59 | 6.8997e-05 | 2510 | 662.2635 | 1050 | 0.047925 | 2.8276 | 1200 | 0.05 | 2034
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 65606 | FALSE | 20505.679 | 20505.679 | 12.7444 | 145 | 0.00013634 | 916 | 329.1085 | 1398 | 0.047918 | 6.9481 | 1201 | 65.5 | 77
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 753254 | TRUE | 576.081 | 561.1486 | 0.34876 | 2 | 0.0001316 | 988 | 1237.8633 | 707 | 0.047657 | 0.095314 | 1202 |  | 3631
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 59596 | FALSE | 58128.5973 | 33598.813 | 20.8818 | 294 | 6.8689e-05 | 2517 | 659.4011 | 1054 | 0.047553 | 13.9806 | 1203 | 0.08 | 1603
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 991285 | TRUE | 2786.1304 | 525.9001 | 0.32685 | 24 | 8.6607e-05 | 2019 | 543.9338 | 1154 | 0.047469 | 1.1393 | 1204 |  | 2968
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 2402 | FALSE | 6035.4639 | 2411.6802 | 1.4989 | 18 | 6.5093e-05 | 2608 | 759.0384 | 966 | 0.047353 | 0.85235 | 1205 | 0.04 | 2096
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 4788 | FALSE | 111874.9537 | 111874.9537 | 69.5307 | 673 | 7.0255e-05 | 2460 | 791.3267 | 951 | 0.047319 | 31.8454 | 1206 | 1.08 | 718
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 19772 | FALSE | 6198.5938 | 6198.5938 | 3.8525 | 41 | 7.7179e-05 | 2283 | 525.9561 | 1177 | 0.047283 | 1.9386 | 1207 | 48.67 | 125
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 178 | FALSE | 21896.763 | 19626.441 | 12.1979 | 182 | 0.0001498 | 741 | 376.3772 | 1328 | 0.047227 | 8.5954 | 1208 | 24.56 | 276
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | R2845 | FALSE | 28680.0593 | 28680.0593 | 17.8248 | 172 | 4.0941e-05 | 3246 | 1025.9007 | 811 | 0.047182 | 8.1154 | 1209 | 0.19 | 1180
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 68362 | FALSE | 11797.2095 | 8312.3827 | 5.1662 | 96 | 0.00012657 | 1070 | 343.9077 | 1382 | 0.047076 | 4.5193 | 1210 |  | 2751
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 785888 | FALSE | 11268.8078 | 7730.7085 | 4.8047 | 49 | 7.806e-05 | 2258 | 321.3673 | 1413 | 0.047021 | 2.304 | 1211 |  | 2753
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 92474 | FALSE | 25104.6477 | 24305.4181 | 15.1059 | 173 | 0.00013452 | 934 | 428.2739 | 1261 | 0.046937 | 8.12 | 1212 | 0.26 | 1060
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | MR339 | FALSE | 11213.6735 | 1921.2331 | 1.1941 | 73 | 5.8956e-05 | 2809 | 692.7863 | 1028 | 0.046887 | 3.4227 | 1213 | 1 | 731
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 88630 | FALSE | 1252.5971 | 1252.5971 | 0.77849 | 6 | 6.5372e-05 | 2605 | 876.4135 | 895 | 0.046842 | 0.28105 | 1214 | 0.03 | 2399
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | XR178 | FALSE | 20866.1928 | 9493.9491 | 5.9005 | 138 | 8.7818e-05 | 1989 | 483.5128 | 1211 | 0.04683 | 6.4625 | 1215 | 0.94 | 744
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 39190 | FALSE | 2877.2566 | 2877.2566 | 1.7882 | 17 | 6.3388e-05 | 2665 | 760.9398 | 964 | 0.046743 | 0.79463 | 1216 | 0 | 2644
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 180193 | FALSE | 3981.725 | 3477.0858 | 2.161 | 23 | 0.00010067 | 1630 | 430.5545 | 1259 | 0.046684 | 1.0737 | 1217 |  | 3467
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 467470 | FALSE | 4805.9002 | 2987.9 | 1.857 | 40 | 0.00023296 | 271 | 103.254 | 1936 | 0.046424 | 1.857 | 1218 |  | 2799
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | XR064 | FALSE | 6026.8923 | 1175.6095 | 0.73065 | 35 | 8.4777e-05 | 2070 | 462.9277 | 1232 | 0.046387 | 1.6236 | 1219 |  | 3069
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 37388 | FALSE | 20103.5682 | 13050.4067 | 8.1109 | 56 | 2.1126e-05 | 3533 | 2437.488 | 352 | 0.046193 | 2.5868 | 1220 | 0 | 2639
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 817491 | FALSE | 3153.3616 | 2279.4584 | 1.4167 | 24 | 0.00010509 | 1523 | 532.8427 | 1169 | 0.046183 | 1.1084 | 1221 |  | 3191
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | XR082 | FALSE | 32889.5484 | 31674.5025 | 19.6858 | 186 | 6.2383e-05 | 2710 | 716.1395 | 1007 | 0.046133 | 8.5807 | 1222 | 0.21 | 1151
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 767280 | TRUE | 1164.558 | 816.4039 | 0.5074 | 11 | 4.3875e-05 | 3191 | 579.646 | 1124 | 0.046117 | 0.50728 | 1223 |  | 3440
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 678 | FALSE | 57111.2211 | 56857.8795 | 35.3374 | 325 | 0.00011031 | 1406 | 496.7562 | 1204 | 0.046077 | 14.9751 | 1224 | 2.05 | 626
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 38998 | TRUE | 9317.0359 | 189.4976 | 0.11777 | 61 | 3.5e-05 | 3353 | 912.9133 | 879 | 0.046064 | 2.8099 | 1225 | 0.01 | 2570
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 600112 | FALSE | 2016.2056 | 1283.9759 | 0.798 | 18 | 0.00016569 | 586 | 185.2798 | 1671 | 0.045774 | 0.82393 | 1226 |  | 3379
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 654 | FALSE | 14047.9314 | 13220.1574 | 8.2164 | 71 | 8.6928e-05 | 2013 | 576.6406 | 1126 | 0.045547 | 3.2338 | 1227 | 0.06 | 1895
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | XR254 | FALSE | 40510.5344 | 40510.5344 | 25.1775 | 134 | 6.9418e-05 | 2490 | 745.0432 | 979 | 0.045544 | 6.1028 | 1228 | 0.31 | 1003
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 658 | FALSE | 17510.52 | 17510.52 | 10.8829 | 107 | 0.00014355 | 818 | 343.9435 | 1381 | 0.045341 | 4.8515 | 1229 | 50.23 | 119
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 7124 | FALSE | 51663.5431 | 17797.9944 | 11.0615 | 286 | 6.2921e-05 | 2684 | 727.3308 | 993 | 0.045279 | 12.9498 | 1230 | 0.05 | 2026
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 3606 | FALSE | 26641.1753 | 17219.5096 | 10.702 | 129 | 8.6419e-05 | 2025 | 738.4699 | 985 | 0.045178 | 5.828 | 1231 | 0.09 | 1541
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 37550 | TRUE | 5259.0816 | 590.535 | 0.36702 | 33 | 6.5837e-05 | 2592 | 741.2586 | 983 | 0.045042 | 1.4864 | 1232 | 1.25 | 693
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 367100 | TRUE | 1041.0726 | 900.8036 | 0.55985 | 6 | 8.144e-05 | 2169 | 654.3693 | 1059 | 0.04493 | 0.26958 | 1233 |  | 3526
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 9330 | FALSE | 66516.2766 | 66516.2766 | 41.3401 | 345 | 4.8089e-05 | 3091 | 936.7226 | 867 | 0.044648 | 15.4037 | 1234 | 0.27 | 1056
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 37632 | FALSE | 42770.2942 | 42770.2942 | 26.5819 | 304 | 0.0001591 | 651 | 314.3513 | 1426 | 0.044601 | 13.5588 | 1235 | 2.55 | 599
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 912460 | TRUE | 716.9415 | 226.2188 | 0.1406 | 6 | 0.0002094 | 362 | 319.3069 | 1418 | 0.044495 | 0.26697 | 1236 |  | 3384
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 37054 | FALSE | 14849.4038 | 14394.233 | 8.9461 | 76 | 0.00045585 | 46 | 99.7602 | 1954 | 0.044439 | 3.3774 | 1237 | 0.04 | 2218
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 92012 | FALSE | 29794.6367 | 29794.6367 | 18.5175 | 219 | 0.00021006 | 358 | 266.7744 | 1505 | 0.044304 | 9.7026 | 1238 | 27.19 | 260
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 351084 | FALSE | 14339.9461 | 3813.7275 | 2.3702 | 91 | 6.4148e-05 | 2639 | 844.8485 | 915 | 0.044255 | 4.0272 | 1239 |  | 2770
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | CB | FALSE | 44653.7534 | 44000.0643 | 27.3462 | 341 | 0.00012378 | 1124 | 546.8562 | 1150 | 0.044085 | 15.0331 | 1240 | 0.94 | 742
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 1544 | FALSE | 44972.2866 | 27291.0085 | 16.9615 | 135 | 2.4864e-05 | 3497 | 2130.6474 | 417 | 0.044056 | 5.9476 | 1241 | 0 | 2640
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 7100 | FALSE | 29355.7923 | 3757.8694 | 2.3355 | 130 | 3.9155e-05 | 3282 | 1207.5405 | 728 | 0.04396 | 5.7148 | 1242 | 0.01 | 2576
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 2302 | FALSE | 2152.9343 | 2152.9343 | 1.3381 | 19 | 6.3222e-05 | 2671 | 648.1357 | 1067 | 0.043905 | 0.8342 | 1243 | 0.01 | 2616
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 1378 | FALSE | 3084.1467 | 1447.5189 | 0.89964 | 25 | 0.00011131 | 1388 | 372.4728 | 1334 | 0.043839 | 1.096 | 1244 | 0.02 | 2452
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 39524 | FALSE | 24862.4083 | 8232.0089 | 5.1162 | 138 | 0.00038497 | 72 | 130.5694 | 1844 | 0.04372 | 6.0334 | 1245 | 0.03 | 2332
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 180398 | FALSE | 8946.0191 | 8946.0191 | 5.56 | 48 | 0.0002082 | 371 | 244.7887 | 1555 | 0.04366 | 2.0957 | 1246 | 24.5 | 278
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 47860 | TRUE | 6236.9476 | 466.0192 | 0.28963 | 54 | 7.3661e-05 | 2372 | 319.7615 | 1416 | 0.043573 | 2.353 | 1247 | 0.02 | 2411
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 982992 | FALSE | 14390.2086 | 14390.2086 | 8.9436 | 52 | 4.6115e-05 | 3136 | 911.2189 | 880 | 0.043526 | 2.2633 | 1248 |  | 3292
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 691436 | FALSE | 3576.8147 | 1680.7069 | 1.0446 | 28 | 0.00012089 | 1165 | 323.1464 | 1409 | 0.043449 | 1.2166 | 1249 |  | 3034
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 112804 | FALSE | 30691.3669 | 16512.5111 | 10.2626 | 67 | 9.7484e-05 | 1701 | 651.0362 | 1064 | 0.043443 | 2.9107 | 1250 |  | 3111
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 1466 | FALSE | 33154.3349 | 33039.7041 | 20.5343 | 211 | 0.0001572 | 672 | 705.5165 | 1017 | 0.043245 | 9.1248 | 1251 | 0.07 | 1677
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 4814 | FALSE | 44262.9015 | 43433.15 | 26.9939 | 117 | 0.00018022 | 512 | 271.8858 | 1490 | 0.043216 | 5.0562 | 1252 | 0.83 | 769
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 7902 | FALSE | 26218.9532 | 18823.9554 | 11.6992 | 143 | 0.00018704 | 461 | 146.5682 | 1787 | 0.043162 | 6.1722 | 1253 | 0.06 | 1892
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 78268 | FALSE | 15647.3206 | 15647.3206 | 9.7249 | 114 | 0.00016165 | 623 | 303.7186 | 1445 | 0.043133 | 4.9171 | 1254 | 73.54 | 60
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1212 | FALSE | 3797.0171 | 2977.1941 | 1.8503 | 25 | 0.00010853 | 1436 | 197.8244 | 1646 | 0.043056 | 1.0764 | 1255 | 28.71 | 247
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | CB | FALSE | 32987.4913 | 18947.9362 | 11.7762 | 226 | 0.00012255 | 1139 | 327.7945 | 1401 | 0.043018 | 9.722 | 1256 | 0.04 | 2117
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 98036 | FALSE | 14803.9566 | 14803.9566 | 9.2007 | 64 | 0.00012504 | 1098 | 294.291 | 1456 | 0.042868 | 2.7435 | 1257 | 0.04 | 2216
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 4630 | FALSE | 5558.0773 | 1729.1767 | 1.0747 | 42 | 7.7824e-05 | 2266 | 548.6975 | 1148 | 0.042814 | 1.7982 | 1258 | 0.05 | 2061
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 166282 | FALSE | 38601.364 | 38601.364 | 23.9909 | 256 | 0.00012662 | 1069 | 425.8459 | 1266 | 0.042498 | 10.8796 | 1259 |  | 2757
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 1028 | FALSE | 28404.1063 | 28404.1063 | 17.6533 | 208 | 0.00012459 | 1106 | 555.8921 | 1139 | 0.042483 | 8.8364 | 1260 | 8.08 | 437
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 370932 | TRUE | 2172.9579 | 619.9296 | 0.38529 | 6 | 3.0451e-05 | 3423 | 729.2934 | 991 | 0.042464 | 0.25478 | 1261 |  | 2828
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | CB | FALSE | 5303.193 | 2471.5392 | 1.5361 | 31 | 0.0001612 | 628 | 200.4454 | 1640 | 0.042406 | 1.3146 | 1262 | 0.01 | 2593
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 3113 | FALSE | 1919.7007 | 1919.7007 | 1.1931 | 9 | 5.1754e-05 | 2999 | 970.9306 | 849 | 0.042389 | 0.3815 | 1263 | 12.05 | 376
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 968 | FALSE | 44551.6644 | 42969.09 | 26.7055 | 283 | 0.00010481 | 1533 | 381.6576 | 1318 | 0.042383 | 11.9944 | 1264 | 33.68 | 221
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 31322 | FALSE | 46269.6305 | 9420.014 | 5.8546 | 310 | 0.00011583 | 1276 | 412.2583 | 1282 | 0.04237 | 13.1348 | 1265 | 0.05 | 1992
332 | MESA 1101CB | 182821101 | MESA 1101 | CB | FALSE | 40952.4168 | 22299.6831 | 13.8593 | 230 | 5.1221e-05 | 3009 | 603.2532 | 1096 | 0.042367 | 9.7444 | 1266 | 0.03 | 2242
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 1682 | TRUE | 14763.8266 | 326.6132 | 0.20299 | 112 | 0.00012357 | 1130 | 359.4666 | 1355 | 0.042324 | 4.7402 | 1267 | 0.48 | 906
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 12842 | FALSE | 27066.2595 | 25454.1408 | 15.8199 | 209 | 0.00018752 | 457 | 122.8933 | 1862 | 0.042311 | 8.8429 | 1268 | 24.93 | 275
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | MR299 | FALSE | 7955.2462 | 7955.2462 | 4.9442 | 58 | 9.0049e-05 | 1910 | 452.8222 | 1243 | 0.042276 | 2.452 | 1269 | 0.4 | 946
5875 | MESA 11016113 | 182821101 | MESA 1101 | 6113 | FALSE | 15649.5972 | 2800.3205 | 1.7404 | 100 | 5.0937e-05 | 3015 | 1017.9876 | 816 | 0.042268 | 4.2268 | 1270 | 0.86 | 762
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 6080 | FALSE | 55307.7629 | 55307.7629 | 34.374 | 322 | 0.00011497 | 1300 | 414.8336 | 1277 | 0.042249 | 13.6042 | 1271 | 0.17 | 1242
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 7124 | FALSE | 1081.3743 | 1081.3743 | 0.67208 | 5 | 0.0002308 | 283 | 190.3883 | 1663 | 0.042229 | 0.21114 | 1272 | 0.05 | 1941
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 641042 | FALSE | 10558.7861 | 2300.7684 | 1.4299 | 22 | 2.7605e-05 | 3464 | 1880.7413 | 480 | 0.042194 | 0.92827 | 1273 |  | 3414
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 37132 | FALSE | 9343.2123 | 9343.2123 | 5.8068 | 50 | 0.00010209 | 1601 | 598.7122 | 1102 | 0.042173 | 2.1086 | 1274 |  | 3104
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 204480 | TRUE | 3182.9165 | 807.68 | 0.50198 | 28 | 0.00015459 | 699 | 296.133 | 1455 | 0.04209 | 1.1785 | 1275 |  | 3169
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 80620 | FALSE | 8949.87 | 1997.9252 | 1.2417 | 51 | 7.4695e-05 | 2340 | 506.899 | 1194 | 0.04205 | 2.1446 | 1276 | 0.61 | 849
796 | MESA 1101M86 | 182821101 | MESA 1101 | M86 | FALSE | 33517.8054 | 20500.8716 | 12.7414 | 217 | 4.9333e-05 | 3053 | 762.6869 | 961 | 0.041844 | 9.0801 | 1277 | 0.04 | 2086
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | Y10 | FALSE | 24460.4132 | 7788.8369 | 4.8408 | 122 | 3.6552e-05 | 3322 | 632.6734 | 1076 | 0.041779 | 5.0971 | 1278 | 0.05 | 1949
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 4566 | FALSE | 28160.2778 | 20128.0864 | 12.5097 | 180 | 0.00011406 | 1319 | 393.9766 | 1301 | 0.041761 | 7.5169 | 1279 | 0.11 | 1420
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 1834 | FALSE | 38353.1383 | 37922.7084 | 23.5691 | 217 | 8.1071e-05 | 2182 | 531.0758 | 1172 | 0.041581 | 9.0231 | 1280 | 0.17 | 1247
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 502 | FALSE | 65884.6113 | 60591.0346 | 37.6576 | 331 | 9.3364e-05 | 1812 | 435.9933 | 1257 | 0.041554 | 13.7543 | 1281 | 0.21 | 1137
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 282 | FALSE | 8222.1189 | 4475.09 | 2.7813 | 62 | 8.3509e-05 | 2115 | 543.5705 | 1155 | 0.041526 | 2.5746 | 1282 | 2.35 | 612
3229 | WISE 1102CB | 152271102 | WISE 1102 | CB | FALSE | 23260.435 | 22633.2401 | 14.0667 | 177 | 0.00014209 | 838 | 392.5466 | 1305 | 0.041442 | 7.3353 | 1283 | 0.11 | 1427
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 13512 | FALSE | 49131.7705 | 45791.8869 | 28.4598 | 345 | 0.00019634 | 412 | 199.5912 | 1642 | 0.041392 | 14.2801 | 1284 | 59.2 | 89
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 2586 | FALSE | 17615.5168 | 10070.6101 | 6.2589 | 91 | 4.8503e-05 | 3075 | 1089.5717 | 778 | 0.041237 | 3.7526 | 1285 | 0.09 | 1567
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 556430 | FALSE | 26122.847 | 7792.8441 | 4.8433 | 122 | 1.6369e-05 | 3574 | 2433.0686 | 354 | 0.041063 | 5.0096 | 1286 |  | 3028
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2236 | FALSE | 4120.4561 | 4120.4561 | 2.5609 | 11 | 0.00027956 | 156 | 116.7508 | 1889 | 0.040994 | 0.45093 | 1287 | 0.26 | 1069
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 1972 | FALSE | 34265.9827 | 34265.9827 | 21.2964 | 177 | 0.00011711 | 1243 | 377.3246 | 1326 | 0.040961 | 7.25 | 1288 | 73.04 | 64
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 99214 | FALSE | 3296.9506 | 2953.539 | 1.8356 | 21 | 0.00014798 | 764 | 541.677 | 1157 | 0.040838 | 0.85759 | 1289 | 0.04 | 2193
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | Y36 | FALSE | 73124.8896 | 60717.9561 | 37.7365 | 283 | 4.3104e-05 | 3207 | 946.8115 | 863 | 0.0408 | 11.5464 | 1290 | 0.14 | 1321
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 166 | FALSE | 15936.7517 | 9969.1209 | 6.1958 | 110 | 0.00012238 | 1141 | 339.9187 | 1388 | 0.040759 | 4.4835 | 1291 | 0.03 | 2283
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 2100 | FALSE | 62879.0761 | 62879.0761 | 39.0796 | 403 | 0.00011682 | 1254 | 355.7448 | 1364 | 0.040696 | 16.4004 | 1292 | 0.14 | 1318
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 402 | FALSE | 37926.2925 | 37584.6138 | 23.359 | 151 | 0.0001662 | 581 | 293.7692 | 1458 | 0.040695 | 6.145 | 1293 | 0.07 | 1764
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 440856 | FALSE | 56881.4108 | 56011.6123 | 34.8114 | 349 | 6.3248e-05 | 2669 | 673.5389 | 1040 | 0.040647 | 14.1857 | 1294 |  | 3143
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 6054 | FALSE | 11579.672 | 11579.672 | 7.1968 | 58 | 0.00029784 | 132 | 184.0031 | 1677 | 0.040642 | 2.3572 | 1295 | 0.09 | 1573
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 1204 | FALSE | 18353.2445 | 15255.8356 | 9.4816 | 124 | 0.00012564 | 1084 | 378.7617 | 1322 | 0.040535 | 5.0263 | 1296 | 0.06 | 1888
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 214 | FALSE | 18868.3768 | 18868.3768 | 11.7268 | 142 | 0.0001516 | 725 | 205.0666 | 1626 | 0.040503 | 5.7514 | 1297 | 44.57 | 157
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 76030 | FALSE | 10072.8355 | 8222.4339 | 5.1103 | 55 | 9.557e-05 | 1739 | 498.7327 | 1202 | 0.040366 | 2.2201 | 1298 | 0.02 | 2538
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 1976 | FALSE | 38264.4277 | 38264.4277 | 23.7815 | 217 | 7.4462e-05 | 2346 | 572.7278 | 1128 | 0.040282 | 8.7412 | 1299 | 81.96 | 47
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | CB | FALSE | 29408.7196 | 16846.5197 | 10.4702 | 203 | 0.00013798 | 894 | 318.5868 | 1420 | 0.040232 | 8.1671 | 1300 | 0.05 | 1952
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 2106 | FALSE | 44861.5543 | 44861.5543 | 27.8816 | 264 | 0.00012115 | 1162 | 368.597 | 1341 | 0.040196 | 10.6117 | 1301 | 51.56 | 115
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 176050 | FALSE | 33994.9384 | 33994.9384 | 21.128 | 168 | 3.5007e-05 | 3352 | 1021.4734 | 814 | 0.040157 | 6.7464 | 1302 |  | 2863
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 2053 | FALSE | 9238.0472 | 9238.0472 | 5.7415 | 74 | 7.8295e-05 | 2252 | 578.9534 | 1125 | 0.040131 | 2.9697 | 1303 | 18.91 | 317
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | CB | FALSE | 14777.824 | 9580.003 | 5.954 | 90 | 0.00019434 | 422 | 250.1874 | 1539 | 0.040116 | 3.6104 | 1304 | 6.07 | 474
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 168892 | TRUE | 1078.2209 | 264.3207 | 0.16428 | 8 | 7.0494e-05 | 2456 | 277.1976 | 1478 | 0.040099 | 0.32079 | 1305 |  | 3240
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 81390 | FALSE | 29957.8137 | 29957.8137 | 18.6189 | 208 | 0.00014065 | 861 | 348.4797 | 1374 | 0.039915 | 8.3022 | 1306 | 0.15 | 1288
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 504 | FALSE | 36253.1832 | 36253.1832 | 22.5315 | 205 | 0.00010544 | 1509 | 471.8115 | 1221 | 0.039748 | 8.1484 | 1307 | 47.4 | 133
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | CB | FALSE | 15315.8587 | 15315.8587 | 9.5189 | 44 | 0.00010811 | 1449 | 444.7581 | 1253 | 0.03956 | 1.7406 | 1308 | 15.25 | 349
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | MR748 | FALSE | 10026.1125 | 10026.1125 | 6.2313 | 86 | 9.5898e-05 | 1731 | 353.7631 | 1368 | 0.039516 | 3.3984 | 1309 |  | 2749
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 989608 | FALSE | 3673.9458 | 1209.612 | 0.75178 | 6 | 0.00015502 | 693 | 503.7259 | 1195 | 0.039513 | 0.23708 | 1310 |  | 2877
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | V56 | FALSE | 15985.6627 | 15022.8264 | 9.3367 | 115 | 6.4252e-05 | 2636 | 557.9025 | 1137 | 0.039442 | 4.5359 | 1311 | 0.1 | 1460
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 891 | FALSE | 5070.4899 | 5070.4899 | 3.1513 | 41 | 0.00012462 | 1104 | 268.5604 | 1501 | 0.03939 | 1.615 | 1312 | 2.7 | 588
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 116 | FALSE | 17433.6477 | 16625.8808 | 10.3331 | 112 | 0.00017861 | 515 | 262.5016 | 1515 | 0.039363 | 4.4087 | 1313 | 33.71 | 220
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 539938 | FALSE | 4460.237 | 4460.237 | 2.7721 | 26 | 0.00021663 | 334 | 141.7664 | 1805 | 0.039354 | 1.0232 | 1314 |  | 2851
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 37486 | FALSE | 12199.5088 | 11162.2658 | 6.9374 | 85 | 0.00018807 | 454 | 224.247 | 1597 | 0.039237 | 3.3351 | 1315 | 0 | 2623
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | CB | FALSE | 6932.7551 | 2351.3614 | 1.4614 | 47 | 0.00016197 | 622 | 176.7445 | 1692 | 0.039234 | 1.844 | 1316 | 0.02 | 2556
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | V02 | FALSE | 29266.1566 | 29266.1566 | 18.189 | 202 | 6.7472e-05 | 2550 | 602.2374 | 1099 | 0.039184 | 7.9151 | 1317 | 0.29 | 1026
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 1656 | FALSE | 51859.3271 | 51859.3271 | 32.2308 | 208 | 0.00010206 | 1602 | 466.1612 | 1228 | 0.039176 | 8.1485 | 1318 | 0.07 | 1727
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 1302 | FALSE | 55353.0299 | 32333.7369 | 20.0955 | 317 | 6.346e-05 | 2662 | 792.5298 | 949 | 0.039053 | 12.3798 | 1319 | 0.08 | 1620
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | CB | FALSE | 30614.8922 | 9216.7854 | 5.7283 | 243 | 0.00023355 | 268 | 176.6871 | 1693 | 0.03873 | 9.4114 | 1320 | 0.04 | 2075
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 158138 | TRUE | 1490.1049 | 829.4376 | 0.5155 | 10 | 2.484e-05 | 3499 | 1008.6051 | 829 | 0.038704 | 0.38704 | 1321 |  | 3560
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | CB | FALSE | 12760.2493 | 12447.7538 | 7.7363 | 22 | 0.00012371 | 1125 | 391.2799 | 1306 | 0.038702 | 0.85144 | 1322 | 6.72 | 462
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 1260 | FALSE | 4901.8674 | 4807.0969 | 2.9876 | 36 | 0.00023996 | 246 | 168.4314 | 1724 | 0.038665 | 1.3919 | 1323 |  | 2682
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 580658 | FALSE | 16767.5085 | 15111.3604 | 9.3918 | 107 | 6.1348e-05 | 2739 | 693.004 | 1027 | 0.038518 | 4.1214 | 1324 |  | 2759
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 91960 | FALSE | 11326.1042 | 10487.6883 | 6.5181 | 90 | 7.983e-05 | 2210 | 850.9359 | 913 | 0.038488 | 3.4639 | 1325 | 0.06 | 1880
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 2506 | FALSE | 20286.2385 | 20286.2385 | 12.608 | 89 | 0.00011138 | 1386 | 409.6677 | 1285 | 0.038425 | 3.4198 | 1326 | 0.12 | 1404
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 220 | FALSE | 15438.0154 | 15438.0154 | 9.5948 | 105 | 0.00011441 | 1309 | 311.3432 | 1429 | 0.038284 | 4.0198 | 1327 | 9.46 | 408
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | R90 | FALSE | 56951.1784 | 48580.6781 | 30.1931 | 259 | 6.3209e-05 | 2672 | 705.4586 | 1018 | 0.038279 | 9.9144 | 1328 | 0.16 | 1275
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | Q06 | FALSE | 20064.3385 | 20064.3385 | 12.4701 | 154 | 5.9491e-05 | 2790 | 680.2301 | 1036 | 0.038111 | 5.8691 | 1329 | 0.24 | 1099
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 68192 | FALSE | 10168.9958 | 4402.6894 | 2.7363 | 72 | 0.00012081 | 1168 | 238.5636 | 1570 | 0.037972 | 2.734 | 1330 | 0.05 | 1932
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 334 | FALSE | 14855.8514 | 9584.4637 | 5.9568 | 84 | 0.00013014 | 1009 | 232.8142 | 1581 | 0.037896 | 3.1833 | 1331 | 0.12 | 1407
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 37454 | FALSE | 19681.6074 | 10482.9729 | 6.5152 | 114 | 0.00010014 | 1640 | 404.6575 | 1292 | 0.037721 | 4.3002 | 1332 | 0.03 | 2377
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | V62 | FALSE | 11154.8311 | 11108.5021 | 6.904 | 50 | 5.5981e-05 | 2890 | 671.7711 | 1042 | 0.037409 | 1.8704 | 1333 | 0.29 | 1023
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 78372 | FALSE | 27765.2096 | 26751.8084 | 16.6264 | 198 | 9.64e-05 | 1722 | 422.9319 | 1270 | 0.037304 | 7.3862 | 1334 | 0.18 | 1212
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | D514R | FALSE | 7698.3807 | 5032.0091 | 3.1274 | 73 | 0.00011281 | 1348 | 304.6429 | 1441 | 0.037278 | 2.7213 | 1335 | 0.15 | 1282
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | XR526 | FALSE | 8725.9018 | 3365.6589 | 2.0918 | 64 | 8.9522e-05 | 1929 | 366.774 | 1343 | 0.037122 | 2.3758 | 1336 | 0.07 | 1699
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | Y42 | FALSE | 26985.4956 | 5628.4599 | 3.4981 | 127 | 5.2153e-05 | 2990 | 480.936 | 1215 | 0.037118 | 4.714 | 1337 | 0.03 | 2346
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 168616 | FALSE | 13634.7639 | 5078.9905 | 3.1566 | 102 | 0.00012703 | 1064 | 319.4815 | 1417 | 0.03705 | 3.7791 | 1338 |  | 3144
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 104102 | FALSE | 5954.6843 | 5329.5584 | 3.3123 | 32 | 7.2705e-05 | 2398 | 458.1953 | 1237 | 0.03704 | 1.1853 | 1339 |  | 2769
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | N46 | FALSE | 9360.6261 | 9360.6261 | 5.8177 | 29 | 8.7946e-05 | 1983 | 551.9562 | 1142 | 0.036988 | 1.0726 | 1340 | 4.74 | 508
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 2426 | FALSE | 27934.4989 | 13782.7728 | 8.566 | 226 | 0.00017076 | 559 | 240.3744 | 1566 | 0.036874 | 8.3335 | 1341 | 0.09 | 1513
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 474 | FALSE | 29501.1448 | 29501.1448 | 18.3351 | 174 | 9.7853e-05 | 1695 | 328.9251 | 1399 | 0.036813 | 6.4055 | 1342 | 75.79 | 56
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 2230 | FALSE | 17863.1589 | 10972.6709 | 6.8196 | 112 | 5.685e-05 | 2866 | 738.5033 | 984 | 0.036587 | 4.0978 | 1343 | 1.14 | 710
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 8902 | FALSE | 29281.8886 | 22787.1296 | 14.1623 | 145 | 9.4843e-05 | 1771 | 290.9381 | 1462 | 0.036496 | 5.2919 | 1344 | 0.33 | 986
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 1606 | FALSE | 8892.9459 | 8892.9459 | 5.527 | 40 | 0.00014678 | 776 | 232.8508 | 1580 | 0.036482 | 1.4593 | 1345 | 0.01 | 2612
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 1238 | FALSE | 11344.0767 | 5824.674 | 3.6201 | 81 | 0.00010773 | 1458 | 597.355 | 1103 | 0.036431 | 2.9509 | 1346 | 1.29 | 689
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | CB | FALSE | 18045.0473 | 16189.7881 | 10.062 | 76 | 0.00014573 | 792 | 355.2175 | 1365 | 0.036334 | 2.7614 | 1347 | 0.04 | 2159
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 76498 | FALSE | 23942.9529 | 23942.9529 | 14.8806 | 119 | 0.00014996 | 736 | 219.4832 | 1606 | 0.036331 | 4.3234 | 1348 | 0.07 | 1718
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 870396 | FALSE | 4752.0973 | 1326.4884 | 0.82442 | 40 | 7.7997e-05 | 2259 | 529.8735 | 1173 | 0.036327 | 1.4531 | 1349 |  | 3499
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 89606 | FALSE | 19260.5468 | 18716.1946 | 11.6322 | 100 | 0.00018082 | 506 | 280.3009 | 1471 | 0.036226 | 3.6226 | 1350 | 2.6 | 595
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | CB | FALSE | 36887.0265 | 35506.5152 | 22.0674 | 293 | 0.00013284 | 960 | 388.0347 | 1309 | 0.036175 | 10.5993 | 1351 | 0.18 | 1199
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 194 | FALSE | 13676.557 | 10907.7439 | 6.7792 | 62 | 5.7737e-05 | 2843 | 536.066 | 1162 | 0.03614 | 2.2407 | 1352 | 0.13 | 1363
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | XR186 | FALSE | 25721.3505 | 4651.2538 | 2.8908 | 191 | 7.0623e-05 | 2453 | 451.6726 | 1246 | 0.036035 | 6.8827 | 1353 | 0.23 | 1109
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 2392 | FALSE | 14284.081 | 9811.7074 | 6.098 | 111 | 0.0001898 | 442 | 159.9243 | 1747 | 0.036 | 3.996 | 1354 |  | 2700
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | R94 | FALSE | 33827.9009 | 22380.6586 | 13.9097 | 179 | 5.5341e-05 | 2903 | 687.195 | 1033 | 0.035946 | 6.4343 | 1355 | 0.08 | 1614
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 4701 | FALSE | 14095.9599 | 3388.7478 | 2.1061 | 65 | 6.2737e-05 | 2693 | 533.9217 | 1166 | 0.035932 | 2.3356 | 1356 | 0.03 | 2301
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 1346 | FALSE | 49591.6622 | 49591.6622 | 30.8214 | 410 | 0.00012199 | 1148 | 241.2851 | 1564 | 0.035841 | 14.6948 | 1357 | 0.17 | 1232
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | R58 | TRUE | 19359.8745 | 870.4973 | 0.54102 | 130 | 8.6053e-05 | 2033 | 466.191 | 1227 | 0.035811 | 4.6554 | 1358 | 0.03 | 2357
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 7062 | FALSE | 19664.1429 | 19664.1429 | 12.2213 | 53 | 5.2216e-05 | 2986 | 685.2904 | 1034 | 0.035805 | 1.8977 | 1359 | 0.1 | 1452
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 17430 | FALSE | 2364.8217 | 2364.8217 | 1.4697 | 15 | 0.00011951 | 1195 | 247.4437 | 1547 | 0.035767 | 0.5365 | 1360 | 32.76 | 224
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 658898 | FALSE | 27632.4579 | 27632.4579 | 17.1737 | 151 | 0.00015549 | 689 | 248.309 | 1546 | 0.035763 | 5.4002 | 1361 | 57.88 | 94
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 1358 | FALSE | 15167.5785 | 13566.1241 | 8.4314 | 51 | 5.9055e-05 | 2804 | 689.2289 | 1031 | 0.035574 | 1.8143 | 1362 | 0.06 | 1890
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 7522 | FALSE | 108391.3301 | 108391.3301 | 67.3656 | 745 | 0.00012077 | 1170 | 356.6073 | 1360 | 0.035529 | 26.4689 | 1363 | 0.39 | 959
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 97300 | FALSE | 5161.3802 | 5161.3802 | 3.2078 | 32 | 0.00052613 | 28 | 106.2466 | 1924 | 0.035439 | 1.1341 | 1364 | 0 | 2624
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | MR284 | FALSE | 24162.974 | 23633.8875 | 14.6886 | 134 | 7.4599e-05 | 2342 | 581.0664 | 1123 | 0.035373 | 4.7399 | 1365 | 0.73 | 795
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 70288 | FALSE | 18879.7984 | 18879.7984 | 11.7339 | 94 | 0.00019388 | 426 | 228.6007 | 1590 | 0.035369 | 3.3247 | 1366 | 36.18 | 207
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | CB | FALSE | 9981.732 | 6230.9216 | 3.8725 | 51 | 2.7369e-05 | 3466 | 650.8554 | 1065 | 0.03535 | 1.8029 | 1367 |  | 2870
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 666 | FALSE | 3872.5577 | 3872.5577 | 2.4068 | 12 | 9.2943e-05 | 1825 | 378.2419 | 1323 | 0.035311 | 0.42373 | 1368 | 4.95 | 500
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 548420 | FALSE | 8380.7958 | 8369.7684 | 5.2018 | 54 | 8.6035e-05 | 2034 | 589.6218 | 1114 | 0.035261 | 1.9041 | 1369 |  | 3251
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 55398 | FALSE | 18355.8501 | 5879.4418 | 3.6541 | 82 | 9.9295e-05 | 1661 | 371.6607 | 1336 | 0.035221 | 2.8881 | 1370 | 0.05 | 2019
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 48000 | FALSE | 21345.6496 | 15284.0145 | 9.4991 | 115 | 8.6887e-05 | 2015 | 388.2741 | 1308 | 0.035167 | 4.0442 | 1371 | 0.07 | 1767
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | CB | TRUE | 1663.8056 | 978.5043 | 0.60814 | 7 | 0.00029336 | 136 | 117.5975 | 1884 | 0.035133 | 0.24593 | 1372 | 0.22 | 1130
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 41650 | FALSE | 26091.6846 | 1862.3816 | 1.1575 | 152 | 9.0143e-05 | 1906 | 368.6652 | 1340 | 0.035126 | 5.3392 | 1373 | 1.15 | 706
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 2052 | FALSE | 7781.6967 | 7781.6967 | 4.8364 | 53 | 0.00010975 | 1416 | 342.2139 | 1385 | 0.034981 | 1.854 | 1374 | 16.17 | 340
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 510 | FALSE | 13083.2788 | 6767.6989 | 4.2062 | 101 | 7.5461e-05 | 2323 | 619.5024 | 1082 | 0.03495 | 3.5299 | 1375 | 0.06 | 1875
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 8972 | FALSE | 10000.1577 | 10000.1577 | 6.2151 | 60 | 0.00015146 | 726 | 262.3952 | 1516 | 0.034933 | 2.096 | 1376 | 24.19 | 280
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 8842 | TRUE | 4786.8365 | 241.1115 | 0.14985 | 42 | 6.9889e-05 | 2476 | 340.0317 | 1387 | 0.03478 | 1.4608 | 1377 | 1.42 | 678
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 48894 | FALSE | 16156.7591 | 14293.1803 | 8.8833 | 119 | 0.00018242 | 493 | 147.0551 | 1786 | 0.034658 | 4.1244 | 1378 | 4.42 | 518
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 2058 | FALSE | 34315.2065 | 34315.2065 | 21.327 | 256 | 0.00016588 | 583 | 212.3054 | 1613 | 0.034582 | 8.853 | 1379 | 0.1 | 1472
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 523764 | TRUE | 581.2133 | 177.5745 | 0.11036 | 5 | 5.3526e-05 | 2949 | 454.5614 | 1241 | 0.034478 | 0.17239 | 1380 |  | 3531
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | MR196 | FALSE | 21187.4678 | 6333.1478 | 3.9361 | 96 | 5.2612e-05 | 2979 | 626.9753 | 1078 | 0.034417 | 3.304 | 1381 | 0.62 | 842
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 93062 | FALSE | 13326.2559 | 13326.2559 | 8.2823 | 84 | 5.3764e-05 | 2946 | 519.6534 | 1183 | 0.034301 | 2.8813 | 1382 | 47.16 | 137
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 650772 | FALSE | 4368.3364 | 1261.3702 | 0.78395 | 10 | 8.4256e-05 | 2083 | 361.8664 | 1350 | 0.03426 | 0.3426 | 1383 |  | 3534
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | CB | FALSE | 36721.9242 | 31128.549 | 19.3465 | 268 | 0.00025192 | 213 | 162.0895 | 1742 | 0.034245 | 9.1777 | 1384 | 0.18 | 1200
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | CB | FALSE | 3490.2509 | 3490.2509 | 2.1692 | 23 | 0.00020947 | 361 | 222.197 | 1600 | 0.034029 | 0.78267 | 1385 | 9.67 | 405
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 94468 | FALSE | 2757.0604 | 2757.0604 | 1.7135 | 21 | 6.6616e-05 | 2567 | 514.9233 | 1187 | 0.033993 | 0.71385 | 1386 |  | 3480
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 1552 | FALSE | 42573.1939 | 23841.5992 | 14.8177 | 221 | 3.5304e-05 | 3346 | 839.4452 | 917 | 0.033912 | 7.4946 | 1387 | 0.02 | 2427
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | CB | TRUE | 10585.951 | 124.2488 | 0.077221 | 65 | 0.00011177 | 1373 | 315.2576 | 1425 | 0.033863 | 2.2011 | 1388 | 0.02 | 2451
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 477952 | TRUE | 2593.1423 | 282.8465 | 0.17579 | 14 | 3.3616e-05 | 3374 | 2064.1113 | 439 | 0.033843 | 0.47381 | 1389 |  | 3390
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 9752 | FALSE | 6185.1828 | 6137.4536 | 3.8145 | 41 | 8.5187e-05 | 2053 | 359.3768 | 1357 | 0.033837 | 1.3873 | 1390 | 0.08 | 1592
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6014 | FALSE | 11167.2532 | 11167.2532 | 6.9405 | 73 | 0.00012645 | 1075 | 322.1745 | 1410 | 0.033829 | 2.4695 | 1391 | 0.11 | 1416
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 1451 | FALSE | 14799.0551 | 9963.2757 | 6.1922 | 61 | 7.7841e-05 | 2264 | 590.7109 | 1112 | 0.03381 | 2.0624 | 1392 | 0.07 | 1693
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 5076 | FALSE | 14477.3637 | 12059.1468 | 7.4948 | 67 | 0.00010771 | 1459 | 265.797 | 1508 | 0.033758 | 2.2618 | 1393 | 0.04 | 2127
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 102734 | TRUE | 954.1374 | 954.1374 | 0.593 | 7 | 8.9773e-05 | 1919 | 197.0875 | 1650 | 0.033754 | 0.23628 | 1394 |  | 3280
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 11790 | TRUE | 22.8988 | 22.8988 | 0.014232 | 1 | 0.00070892 | 7 | 47.5828 | 2227 | 0.033732 | 0.033732 | 1395 | 0.2 | 1164
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 342498 | TRUE | 1151.7336 | 49.0072 | 0.030458 | 9 | 7.9908e-05 | 2207 | 500.2762 | 1198 | 0.033722 | 0.3035 | 1396 |  | 3521
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 495270 | TRUE | 13307.7021 | 863.3194 | 0.53656 | 50 | 9.0841e-05 | 1888 | 589.9667 | 1113 | 0.033688 | 1.6844 | 1397 |  | 2953
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 600 | FALSE | 11716.5391 | 5966.5276 | 3.7082 | 107 | 8.5491e-05 | 2040 | 380.66 | 1319 | 0.033514 | 3.586 | 1398 | 2.36 | 611
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 2414 | FALSE | 23793.415 | 23793.415 | 14.7877 | 168 | 0.00014567 | 794 | 312.3629 | 1427 | 0.033489 | 5.6261 | 1399 | 0.1 | 1503
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 1730 | FALSE | 13645.4759 | 13645.4759 | 8.4807 | 73 | 0.00014065 | 860 | 278.461 | 1475 | 0.033438 | 2.441 | 1400 | 45.96 | 146
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1334 | FALSE | 25612.9912 | 2886.1165 | 1.7937 | 155 | 6.0867e-05 | 2753 | 682.7098 | 1035 | 0.033359 | 5.1706 | 1401 | 1.21 | 700
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | H82 | FALSE | 58651.4755 | 52489.3402 | 32.6223 | 262 | 9.3414e-05 | 1811 | 388.9088 | 1307 | 0.033242 | 8.7095 | 1402 | 0.77 | 782
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 9012 | FALSE | 25166.2142 | 25166.2142 | 15.6409 | 176 | 0.00013267 | 966 | 372.3651 | 1335 | 0.033219 | 5.8466 | 1403 | 0.42 | 934
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 807000 | FALSE | 1709.8584 | 1354.2941 | 0.8417 | 7 | 3.235e-05 | 3394 | 880.4035 | 891 | 0.033203 | 0.23242 | 1404 |  | 3594
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 14028 | FALSE | 12751.8037 | 6133.5417 | 3.812 | 103 | 0.00010822 | 1447 | 214.1406 | 1611 | 0.033074 | 3.4066 | 1405 | 0.04 | 2224
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 1044 | FALSE | 9889.843 | 9889.843 | 6.1466 | 17 | 0.00010748 | 1465 | 324.5037 | 1407 | 0.033036 | 0.56161 | 1406 | 18.93 | 316
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1040 | FALSE | 9753.1063 | 1682.9824 | 1.046 | 62 | 0.00011564 | 1281 | 448.3969 | 1250 | 0.032999 | 2.0459 | 1407 | 0.73 | 796
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 2310 | FALSE | 4180.455 | 1304.6994 | 0.81088 | 34 | 0.00013671 | 911 | 509.3332 | 1192 | 0.032911 | 1.119 | 1408 | 0.05 | 1962
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | CB | FALSE | 30214.013 | 30214.013 | 18.7781 | 154 | 0.00013214 | 980 | 326.6135 | 1403 | 0.03289 | 5.065 | 1409 | 0.04 | 2085
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 12832 | FALSE | 24421.2649 | 23234.3604 | 14.4402 | 166 | 0.00017093 | 557 | 211.8635 | 1615 | 0.032787 | 5.4427 | 1410 | 28.99 | 245
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 599142 | TRUE | 3668.6338 | 573.3105 | 0.35631 | 19 | 2.2881e-05 | 3512 | 2022.5531 | 452 | 0.03274 | 0.62205 | 1411 |  | 3488
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 1812 | FALSE | 30912.6745 | 30912.6745 | 19.2124 | 234 | 0.0001396 | 878 | 157.2117 | 1758 | 0.032657 | 7.6418 | 1412 | 0.91 | 748
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 113634 | FALSE | 13932.988 | 2941.0752 | 1.8279 | 76 | 7.4759e-05 | 2338 | 364.1214 | 1346 | 0.032654 | 2.4817 | 1413 |  | 3229
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | CB | FALSE | 4270.3268 | 4270.3268 | 2.654 | 7 | 0.000239 | 249 | 194.5881 | 1655 | 0.032515 | 0.22761 | 1414 | 0.03 | 2354
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 2224 | FALSE | 16910.6519 | 16910.6519 | 10.51 | 123 | 0.00022231 | 310 | 204.3067 | 1631 | 0.032512 | 3.999 | 1415 | 31.55 | 229
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 37462 | FALSE | 7845.6326 | 3795.803 | 2.3591 | 63 | 0.00014083 | 857 | 230.0252 | 1586 | 0.032457 | 2.0448 | 1416 | 0.04 | 2166
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 894006 | TRUE | 1042.8451 | 627.9545 | 0.39028 | 8 | 7.1494e-05 | 2432 | 670.4008 | 1043 | 0.03239 | 0.25912 | 1417 |  | 3282
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | V14 | FALSE | 13117.1277 | 13103.4117 | 8.1438 | 69 | 5.3161e-05 | 2961 | 462.6018 | 1233 | 0.03238 | 2.2342 | 1418 | 0.07 | 1714
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 8412 | FALSE | 31508.6751 | 31508.6751 | 19.5828 | 201 | 0.00012406 | 1118 | 308.2082 | 1435 | 0.032352 | 6.5027 | 1419 | 0.24 | 1093
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 7002 | FALSE | 29669.7133 | 13447.6997 | 8.3578 | 117 | 6.5838e-05 | 2591 | 548.8506 | 1147 | 0.032323 | 3.7818 | 1420 | 0.03 | 2407
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 10254 | FALSE | 3449.8351 | 3449.8351 | 2.1441 | 11 | 0.00025218 | 212 | 138.3979 | 1814 | 0.03232 | 0.35552 | 1421 | 0.29 | 1030
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | CB | FALSE | 6578.3972 | 6578.3972 | 4.0885 | 51 | 0.00035059 | 89 | 89.0767 | 2007 | 0.032289 | 1.6467 | 1422 | 4 | 530
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 907698 | FALSE | 3034.3117 | 2466.4182 | 1.5329 | 14 | 0.00012445 | 1111 | 261.4537 | 1520 | 0.03225 | 0.4515 | 1423 |  | 3140
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 2500 | FALSE | 11167.0911 | 10490.7768 | 6.5201 | 74 | 0.00015128 | 727 | 218.7989 | 1608 | 0.032243 | 2.3859 | 1424 | 57.37 | 96
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 1020 | FALSE | 46299.321 | 46299.321 | 28.7752 | 311 | 9.6344e-05 | 1725 | 368.887 | 1339 | 0.032187 | 10.0103 | 1425 | 69 | 71
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 2006 | FALSE | 14941.7424 | 13398.0902 | 8.327 | 75 | 0.00034661 | 94 | 97.9891 | 1968 | 0.03216 | 2.412 | 1426 | 0.09 | 1508
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 760730 | TRUE | 4317.2275 | 964.21 | 0.59926 | 17 | 7.566e-05 | 2318 | 407.7093 | 1289 | 0.032096 | 0.54562 | 1427 |  | 3530
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 5462 | FALSE | 37447.0905 | 37447.0905 | 23.2735 | 248 | 0.00016384 | 602 | 227.1186 | 1593 | 0.032082 | 7.9564 | 1428 | 37.76 | 199
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 63170 | FALSE | 21717.2784 | 20031.3406 | 12.4496 | 86 | 0.00032558 | 106 | 126.7281 | 1853 | 0.031951 | 2.7478 | 1429 | 0.11 | 1410
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6917 | FALSE | 11229.1017 | 11229.1017 | 6.9789 | 58 | 0.00011705 | 1246 | 334.9674 | 1393 | 0.031941 | 1.8526 | 1430 | 28.69 | 248
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 887932 | FALSE | 7830.582 | 2732.0868 | 1.698 | 34 | 3.8049e-05 | 3299 | 1172.2774 | 745 | 0.031896 | 1.0845 | 1431 |  | 2945
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 619542 | FALSE | 2424.259 | 2408.2569 | 1.4967 | 21 | 0.00013244 | 972 | 252.7945 | 1536 | 0.031874 | 0.66935 | 1432 |  | 3241
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 1130 | FALSE | 32234.9294 | 32234.9294 | 20.0341 | 231 | 8.1217e-05 | 2177 | 401.3828 | 1295 | 0.031834 | 7.3538 | 1433 | 0.19 | 1198
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 37238 | FALSE | 18384.2813 | 18384.2813 | 11.4259 | 79 | 9.076e-05 | 1890 | 274.1817 | 1485 | 0.031693 | 2.5038 | 1434 | 39.57 | 188
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 10610 | FALSE | 2196.7777 | 2196.7777 | 1.3653 | 22 | 7.4106e-05 | 2354 | 439.5957 | 1256 | 0.031595 | 0.6951 | 1435 | 0.3 | 1012
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 85870 | FALSE | 27055.9571 | 18409.1169 | 11.4413 | 109 | 5.897e-05 | 2807 | 581.2408 | 1122 | 0.031502 | 3.4337 | 1436 | 0.05 | 1923
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 478 | FALSE | 32233.0286 | 13396.6859 | 8.3261 | 213 | 9.7957e-05 | 1693 | 387.6512 | 1310 | 0.031296 | 6.6661 | 1437 | 6.33 | 468
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | CB | TRUE | 9680.979 | 75.4379 | 0.046885 | 69 | 8.4474e-05 | 2078 | 195.8633 | 1653 | 0.031266 | 2.1574 | 1438 | 3.69 | 536
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 463260 | TRUE | 886.169 | 873.7132 | 0.54302 | 6 | 9.5911e-05 | 1730 | 333.1332 | 1394 | 0.031168 | 0.18701 | 1439 |  | 3601
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | CB | FALSE | 17669.2412 | 14555.9213 | 9.0466 | 119 | 0.00013143 | 990 | 316.505 | 1422 | 0.031137 | 3.7053 | 1440 | 0.06 | 1894
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 2556 | FALSE | 10719.4797 | 10719.4797 | 6.6622 | 41 | 0.00022017 | 320 | 170.5273 | 1713 | 0.031032 | 1.2723 | 1441 | 40.37 | 184
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | CB | FALSE | 7207.9497 | 1811.9234 | 1.1261 | 57 | 3.6174e-05 | 3330 | 275.7036 | 1484 | 0.03103 | 1.7687 | 1442 | 0.02 | 2494
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | M98 | FALSE | 15843.0204 | 12614.6664 | 7.8401 | 56 | 2.6579e-05 | 3477 | 870.0926 | 898 | 0.030988 | 1.7353 | 1443 | 0.06 | 1829
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 9265 | FALSE | 8915.672 | 8915.672 | 5.5411 | 45 | 9.8e-05 | 1691 | 342.4629 | 1384 | 0.03098 | 1.3941 | 1444 | 0.08 | 1605
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 524356 | FALSE | 4107.6805 | 2088.1166 | 1.2978 | 29 | 0.00010421 | 1547 | 511.0846 | 1190 | 0.030872 | 0.89528 | 1445 |  | 2991
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 806 | FALSE | 18143.3915 | 18143.3915 | 11.2762 | 65 | 0.00012168 | 1154 | 338.7274 | 1390 | 0.030867 | 2.0063 | 1446 | 48.53 | 127
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 1750 | FALSE | 13589.0424 | 13584.4704 | 8.4428 | 62 | 0.00032404 | 108 | 98.8868 | 1959 | 0.030822 | 1.911 | 1447 | 0.13 | 1338
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 5380 | FALSE | 22971.0374 | 22971.0374 | 14.2766 | 143 | 7.8304e-05 | 2250 | 414.5903 | 1278 | 0.030806 | 4.4053 | 1448 | 0.46 | 911
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 578 | FALSE | 29556.6676 | 27517.4977 | 17.1022 | 170 | 8.7604e-05 | 1997 | 393.466 | 1303 | 0.030756 | 5.2285 | 1449 | 37.08 | 203
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 806 | FALSE | 4898.4533 | 4898.4533 | 3.0444 | 17 | 0.00027974 | 154 | 135.7877 | 1828 | 0.030667 | 0.52134 | 1450 | 0.55 | 868
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 657038 | FALSE | 16275.5331 | 4182.6167 | 2.5995 | 72 | 4.9064e-05 | 3062 | 415.5682 | 1276 | 0.030657 | 2.2073 | 1451 |  | 3078
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 467046 | FALSE | 34550.7467 | 24654.328 | 15.3228 | 266 | 0.00018345 | 482 | 166.8005 | 1729 | 0.030581 | 8.1346 | 1452 |  | 2816
4703 | WISE 1101CB | 152271101 | WISE 1101 | CB | FALSE | 14435.5526 | 7662.7202 | 4.7624 | 112 | 0.00015887 | 652 | 243.3221 | 1558 | 0.030561 | 3.4229 | 1453 | 0.05 | 2032
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 3127 | FALSE | 15418.4131 | 15054.5807 | 9.3565 | 78 | 0.00010691 | 1479 | 266.083 | 1507 | 0.030422 | 2.3729 | 1454 | 0.62 | 840
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 1646 | FALSE | 38843.3191 | 38535.0265 | 23.9497 | 215 | 6.2043e-05 | 2718 | 560.4541 | 1133 | 0.030417 | 6.5396 | 1455 | 13.62 | 364
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | CB | TRUE | 200.8618 | 200.8618 | 0.12484 | 2 | 9.0416e-05 | 1899 | 309.1042 | 1433 | 0.030413 | 0.060827 | 1456 | 0.72 | 797
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 11212 | FALSE | 35943.9954 | 35943.9954 | 22.3393 | 155 | 8.85e-05 | 1974 | 349.3135 | 1372 | 0.030264 | 4.691 | 1457 | 0.06 | 1822
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | A02 | FALSE | 41006.5742 | 41006.5742 | 25.4858 | 253 | 5.864e-05 | 2818 | 542.8818 | 1156 | 0.030233 | 7.649 | 1458 | 2.41 | 606
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 60090 | FALSE | 10545.4488 | 10545.4488 | 6.554 | 62 | 0.00016362 | 604 | 206.0102 | 1623 | 0.030171 | 1.8706 | 1459 | 0.06 | 1906
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 713592 | FALSE | 16948.2792 | 16715.2405 | 10.3886 | 152 | 6.2494e-05 | 2704 | 490.9201 | 1208 | 0.030005 | 4.5608 | 1460 |  | 2997
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | CB | FALSE | 9227.3447 | 4545.9264 | 2.8253 | 60 | 7.4812e-05 | 2336 | 409.6387 | 1286 | 0.029932 | 1.7959 | 1461 | 5.21 | 494
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 19552 | FALSE | 34339.9089 | 34339.9089 | 21.3424 | 238 | 0.0001768 | 520 | 361.0634 | 1351 | 0.029928 | 7.123 | 1462 | 0.45 | 915
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 534019 | FALSE | 1193.5001 | 1147.9573 | 0.71346 | 5 | 0.0001111 | 1391 | 269.5494 | 1499 | 0.029893 | 0.14947 | 1463 |  | 3519
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 3174 | FALSE | 35498.7494 | 29750.1978 | 18.4899 | 162 | 0.00035838 | 83 | 115.2454 | 1894 | 0.029875 | 4.8397 | 1464 | 0.13 | 1336
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 8040 | FALSE | 41434.2849 | 11785.9847 | 7.325 | 145 | 5.9131e-05 | 2803 | 495.056 | 1206 | 0.02987 | 4.3312 | 1465 | 0.01 | 2600
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 8971 | FALSE | 12716.2407 | 12716.2407 | 7.9032 | 72 | 0.00010597 | 1496 | 268.1837 | 1504 | 0.029749 | 2.1419 | 1466 |  | 3293
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 936674 | FALSE | 6354.8382 | 1063.5848 | 0.66102 | 56 | 8.2565e-05 | 2141 | 408.407 | 1288 | 0.029729 | 1.6648 | 1467 |  | 2866
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 41392 | FALSE | 23588.435 | 7062.7077 | 4.3895 | 171 | 0.00011368 | 1327 | 289.7407 | 1465 | 0.029696 | 5.078 | 1468 | 3.21 | 554
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 3783 | TRUE | 16200.7401 | 142.5109 | 0.088571 | 96 | 9.2314e-05 | 1834 | 351.5102 | 1370 | 0.029685 | 2.8498 | 1469 |  | 3259
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 46860 | FALSE | 5362.8484 | 1149.598 | 0.71448 | 15 | 0.0001367 | 912 | 145.8531 | 1790 | 0.029648 | 0.44471 | 1470 | 0.03 | 2247
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 6064 | FALSE | 31643.7207 | 30550.9366 | 18.9875 | 199 | 7.5696e-05 | 2315 | 471.6661 | 1222 | 0.029564 | 5.8832 | 1471 | 0.2 | 1167
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | Y18 | FALSE | 12113.6185 | 7856.8971 | 4.8831 | 60 | 4.1779e-05 | 3229 | 658.0763 | 1056 | 0.029555 | 1.7733 | 1472 | 0.08 | 1647
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 13450 | FALSE | 7994.7686 | 1509.284 | 0.93803 | 42 | 7.6415e-05 | 2295 | 360.8067 | 1352 | 0.029532 | 1.2403 | 1473 |  | 2741
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 2936 | FALSE | 53378.6829 | 53378.6829 | 33.1751 | 249 | 0.00014373 | 817 | 191.382 | 1659 | 0.029513 | 7.3486 | 1474 | 0.15 | 1299
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 688780 | TRUE | 2079.7156 | 922.8958 | 0.57358 | 14 | 0.00019275 | 430 | 228.6665 | 1589 | 0.029456 | 0.41239 | 1475 |  | 2839
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 1510 | FALSE | 21171.8285 | 21171.8285 | 13.1584 | 107 | 0.00046286 | 44 | 80.26 | 2047 | 0.029417 | 3.1476 | 1476 | 0.13 | 1358
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 634 | FALSE | 27022.9414 | 18046.5459 | 11.216 | 178 | 0.00012722 | 1060 | 223.109 | 1599 | 0.029373 | 5.2284 | 1477 | 0.7 | 808
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 522 | FALSE | 17218.2435 | 12875.7792 | 8.0023 | 109 | 8.4103e-05 | 2091 | 350.0759 | 1371 | 0.029361 | 3.2003 | 1478 | 0.06 | 1861
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 75686 | FALSE | 8282.1233 | 7450.4021 | 4.6305 | 31 | 0.00011699 | 1250 | 264.1333 | 1511 | 0.029281 | 0.90772 | 1479 | 0.04 | 2067
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | CB | FALSE | 7605.9803 | 7605.9803 | 4.7271 | 37 | 0.00011114 | 1390 | 255.7947 | 1533 | 0.029281 | 1.0834 | 1480 | 0.23 | 1113
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | CB | FALSE | 9497.7631 | 9497.7631 | 5.9029 | 69 | 0.00021208 | 351 | 141.7322 | 1806 | 0.029248 | 2.0181 | 1481 | 0.04 | 2126
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 91810 | FALSE | 47379.4324 | 47379.4324 | 29.4465 | 296 | 0.00010548 | 1507 | 312.0704 | 1428 | 0.029203 | 8.6442 | 1482 | 44.17 | 160
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 331444 | FALSE | 7051.4008 | 3579.9474 | 2.225 | 44 | 0.00010727 | 1466 | 260.3745 | 1523 | 0.029048 | 1.2781 | 1483 |  | 3273
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | CB | FALSE | 31622.6384 | 31622.6384 | 19.6536 | 162 | 0.00011093 | 1392 | 299.4116 | 1448 | 0.029034 | 4.7034 | 1484 | 78.02 | 52
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 899734 | FALSE | 5471.5337 | 5471.5337 | 3.4006 | 36 | 0.00048435 | 35 | 103.6873 | 1931 | 0.028754 | 1.0351 | 1485 |  | 3329
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | CB | FALSE | 10872.4032 | 5779.9667 | 3.5923 | 75 | 4.9567e-05 | 3048 | 502.0965 | 1196 | 0.028742 | 2.1556 | 1486 | 0.7 | 805
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 684564 | TRUE | 4176.2924 | 443.3906 | 0.27557 | 28 | 6.665e-05 | 2566 | 311.0083 | 1430 | 0.02858 | 0.80024 | 1487 |  | 3243
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 978364 | FALSE | 4026.4295 | 1557.6573 | 0.96809 | 36 | 4.8923e-05 | 3067 | 319.1206 | 1419 | 0.028543 | 1.0276 | 1488 |  | 2850
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | CB | FALSE | 41366.5121 | 1446.4903 | 0.899 | 288 | 7.2635e-05 | 2400 | 424.917 | 1268 | 0.028499 | 8.2077 | 1489 | 0.17 | 1224
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 3702 | FALSE | 7962.9538 | 7864.1375 | 4.8876 | 35 | 5.5767e-05 | 2896 | 546.4749 | 1152 | 0.028477 | 0.99668 | 1490 | 0.03 | 2383
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | R86 | FALSE | 23197.4547 | 17574.2947 | 10.9225 | 160 | 5.7553e-05 | 2847 | 490.6496 | 1209 | 0.028407 | 4.5451 | 1491 | 0.08 | 1637
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 711900 | FALSE | 20250.2667 | 14456.1594 | 8.9846 | 116 | 7.6946e-05 | 2288 | 301.111 | 1446 | 0.028347 | 3.2883 | 1492 | 0.24 | 1097
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 289662 | TRUE | 1302.884 | 533.3553 | 0.33148 | 11 | 2.7822e-05 | 3461 | 483.4846 | 1212 | 0.028227 | 0.31049 | 1493 |  | 3149
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 648 | FALSE | 26216.5179 | 6117.4965 | 3.802 | 187 | 9.6901e-05 | 1716 | 305.0125 | 1439 | 0.028161 | 5.2662 | 1494 | 2.81 | 578
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 1618 | FALSE | 9746.1598 | 9746.1598 | 6.0573 | 15 | 0.00010839 | 1441 | 237.7895 | 1574 | 0.028087 | 0.42131 | 1495 | 0 | 2632
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | CB | TRUE | 1951.9603 | 159.1645 | 0.098921 | 22 | 5.9141e-05 | 2802 | 153.2438 | 1767 | 0.028017 | 0.61638 | 1496 | 0.28 | 1038
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 6014 | FALSE | 8043.0218 | 8043.0218 | 4.9988 | 50 | 0.000124 | 1120 | 242.0554 | 1562 | 0.027926 | 1.3963 | 1497 | 0.1 | 1478
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | MR298 | FALSE | 8473.8006 | 8244.1822 | 5.1238 | 39 | 7.0694e-05 | 2452 | 586.0273 | 1117 | 0.027925 | 1.0891 | 1498 | 0.26 | 1070
739 | COTATI 1105CB | 42271105 | COTATI 1105 | CB | FALSE | 4309.0759 | 4309.0759 | 2.6781 | 35 | 0.00011326 | 1338 | 266.28 | 1506 | 0.027854 | 0.97488 | 1499 | 11.62 | 384
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | Y22 | FALSE | 40867.3286 | 16721.66 | 10.3926 | 178 | 4.3833e-05 | 3193 | 413.6922 | 1281 | 0.027743 | 4.9383 | 1500 | 0.04 | 2132
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 76842 | FALSE | 9156.7064 | 9156.7064 | 5.6909 | 33 | 0.00012448 | 1109 | 276.9184 | 1479 | 0.027724 | 0.91488 | 1501 | 0.08 | 1635
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | A66 | FALSE | 54313.8381 | 54313.8381 | 33.7563 | 429 | 6.1474e-05 | 2734 | 473.9679 | 1218 | 0.027639 | 11.8573 | 1502 | 0.27 | 1052
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | CB | TRUE | 10934.0811 | 0 | 0 | 68 | 0.00011128 | 1389 | 204.9489 | 1629 | 0.027594 | 1.8764 | 1503 | 0.03 | 2305
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | V82 | FALSE | 22558.9801 | 14130.1147 | 8.7819 | 174 | 7.4918e-05 | 2332 | 326.0495 | 1404 | 0.027572 | 4.7975 | 1504 | 0.06 | 1792
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 7502 | FALSE | 36933.3454 | 36933.3454 | 22.9542 | 267 | 0.00011381 | 1324 | 264.2675 | 1509 | 0.027532 | 7.351 | 1505 | 38.11 | 197
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | V12 | FALSE | 33868.1694 | 33868.1694 | 21.0492 | 127 | 8.411e-05 | 2090 | 399.923 | 1297 | 0.027414 | 3.4815 | 1506 | 0.24 | 1100
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 10986 | FALSE | 31785.0255 | 14988.5933 | 9.3155 | 180 | 9.4351e-05 | 1785 | 282.1821 | 1470 | 0.027411 | 4.9339 | 1507 | 0.19 | 1190
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 682 | FALSE | 23844.5349 | 23844.5349 | 14.8195 | 97 | 0.00016349 | 605 | 167.4124 | 1727 | 0.027282 | 2.6464 | 1508 | 2.58 | 596
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 3010 | FALSE | 50085.8598 | 50061.44 | 31.1134 | 229 | 6.2602e-05 | 2699 | 457.2691 | 1239 | 0.027281 | 6.2474 | 1509 | 0.11 | 1434
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 556 | TRUE | 12171.5187 | 285.9131 | 0.1777 | 90 | 6.0969e-05 | 2748 | 422.9587 | 1269 | 0.027227 | 2.4505 | 1510 | 1.68 | 652
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 6074 | FALSE | 5923.6574 | 5923.6574 | 3.6816 | 34 | 0.00013034 | 1003 | 156.7867 | 1759 | 0.027132 | 0.92248 | 1511 | 1.63 | 660
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 818874 | FALSE | 10865.8424 | 9148.5425 | 5.6859 | 42 | 8.8075e-05 | 1981 | 323.2606 | 1408 | 0.02708 | 1.1374 | 1512 |  | 3177
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 869408 | TRUE | 710.7103 | 710.7103 | 0.44171 | 6 | 0.00016423 | 597 | 150.5967 | 1775 | 0.027041 | 0.16225 | 1513 |  | 2977
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 7006 | TRUE | 11204.5058 | 0 | 0 | 42 | 6.1931e-05 | 2722 | 240.1753 | 1567 | 0.027015 | 1.1346 | 1514 | 0 | 2622
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 889948 | TRUE | 2120.3673 | 706.8877 | 0.43933 | 8 | 7.9649e-05 | 2217 | 479.8183 | 1216 | 0.026886 | 0.21509 | 1515 |  | 3380
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | N34 | FALSE | 22008.9702 | 6041.6356 | 3.7549 | 62 | 9.4539e-05 | 1778 | 242.6816 | 1560 | 0.02675 | 1.6585 | 1516 | 0 | 2638
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 120 | FALSE | 10326.1868 | 10326.1868 | 6.4178 | 67 | 0.00021509 | 341 | 93.788 | 1989 | 0.026687 | 1.788 | 1517 | 79.25 | 50
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | CB | FALSE | 11922.4207 | 11922.4207 | 7.4098 | 78 | 6.4644e-05 | 2617 | 270.2338 | 1497 | 0.026652 | 2.0789 | 1518 | 0.11 | 1413
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 82542 | FALSE | 24330.9579 | 19513.0606 | 12.1274 | 150 | 0.00024689 | 227 | 125.8806 | 1856 | 0.026646 | 3.9969 | 1519 | 0.25 | 1073
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 904574 | FALSE | 2518.7659 | 2518.7659 | 1.5654 | 25 | 0.0002218 | 312 | 119.8467 | 1870 | 0.026628 | 0.6657 | 1520 |  | 3362
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | CB | FALSE | 10055.4219 | 1899.3733 | 1.1805 | 75 | 5.022e-05 | 3033 | 198.6367 | 1643 | 0.026552 | 1.9914 | 1521 | 0.04 | 2084
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 5973 | TRUE | 3972.7876 | 138.2354 | 0.085914 | 35 | 0.00011259 | 1351 | 248.9959 | 1541 | 0.026544 | 0.92904 | 1522 |  | 2881
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 773926 | TRUE | 3395.2146 | 706.7417 | 0.43924 | 25 | 7.9069e-05 | 2232 | 668.6259 | 1044 | 0.026524 | 0.66311 | 1523 |  | 3448
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | CB | TRUE | 8832.9668 | 0 | 0 | 64 | 0.00011152 | 1384 | 254.8686 | 1534 | 0.026458 | 1.6933 | 1524 |  | 3122
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | CB | TRUE | 8317.4057 | 587.3881 | 0.36506 | 40 | 7.0186e-05 | 2464 | 270.6989 | 1494 | 0.026426 | 1.057 | 1525 | 2.37 | 608
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | CB | FALSE | 23251.1044 | 23251.1044 | 14.4507 | 153 | 0.00019229 | 432 | 98.7244 | 1962 | 0.026396 | 4.0386 | 1526 | 44.02 | 163
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 3446 | TRUE | 13148.5405 | 475.0126 | 0.29522 | 87 | 0.00014693 | 773 | 117.907 | 1882 | 0.026372 | 2.2944 | 1527 | 0.23 | 1108
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 37326 | FALSE | 8213.253 | 8213.253 | 5.1046 | 31 | 5.9994e-05 | 2777 | 369.1163 | 1338 | 0.026358 | 0.8171 | 1528 | 0.04 | 2195
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 48632 | FALSE | 4391.6286 | 4391.6286 | 2.7294 | 38 | 0.00010681 | 1483 | 115.1661 | 1895 | 0.026323 | 1.0003 | 1529 | 0.07 | 1766
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 36676 | FALSE | 27305.8877 | 27305.8877 | 16.9707 | 173 | 8.1258e-05 | 2175 | 346.1968 | 1376 | 0.026145 | 4.5232 | 1530 | 34.1 | 217
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 1902 | FALSE | 7840.3138 | 7840.3138 | 4.8728 | 44 | 0.00013679 | 909 | 253.4699 | 1535 | 0.026064 | 1.1468 | 1531 | 31.9 | 227
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 1100 | FALSE | 10937.7288 | 5979.935 | 3.7166 | 68 | 8.9766e-05 | 1920 | 293.7962 | 1457 | 0.026059 | 1.772 | 1532 | 0.03 | 2389
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 676060 | TRUE | 1407.162 | 722.7771 | 0.44921 | 9 | 0.00025905 | 197 | 109.1 | 1913 | 0.026046 | 0.23441 | 1533 |  | 3446
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 11188 | FALSE | 48202.5217 | 48202.5217 | 29.9581 | 294 | 0.00012846 | 1041 | 211.2891 | 1617 | 0.02599 | 7.641 | 1534 | 0.06 | 1852
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 47006 | FALSE | 7194.664 | 7194.664 | 4.4715 | 51 | 0.00041526 | 65 | 106.8362 | 1923 | 0.025936 | 1.3227 | 1535 | 0.13 | 1347
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | CB | FALSE | 10088.6649 | 2844.8661 | 1.7681 | 76 | 0.00011862 | 1213 | 152.4537 | 1770 | 0.025924 | 1.9702 | 1536 | 0.01 | 2606
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 2034 | FALSE | 17672.0047 | 17659.7087 | 10.9756 | 99 | 0.00023619 | 258 | 172.9141 | 1707 | 0.025842 | 2.5583 | 1537 | 0.4 | 942
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 346 | FALSE | 40386.1099 | 22629.4944 | 14.0643 | 309 | 0.00013985 | 869 | 232.58 | 1582 | 0.025706 | 7.9433 | 1538 | 0.07 | 1770
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 2839 | FALSE | 2358.3859 | 2358.3859 | 1.4657 | 20 | 0.00011836 | 1220 | 279.5294 | 1473 | 0.02569 | 0.5138 | 1539 | 0.07 | 1683
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | CB | FALSE | 7803.1232 | 3646.1026 | 2.2661 | 50 | 6.1558e-05 | 2731 | 249.9677 | 1540 | 0.025673 | 1.2836 | 1540 | 0.06 | 1893
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 430286 | FALSE | 8696.3655 | 5942.5051 | 3.6933 | 13 | 7.0159e-05 | 2468 | 482.818 | 1213 | 0.025652 | 0.33348 | 1541 |  | 3410
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 502672 | FALSE | 30486.256 | 2285.3291 | 1.4203 | 127 | 5.9745e-05 | 2781 | 641.4967 | 1071 | 0.025636 | 3.2558 | 1542 | 0.03 | 2388
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 11054 | FALSE | 41601.4757 | 39167.0021 | 24.3425 | 272 | 0.00015629 | 682 | 157.984 | 1754 | 0.025605 | 6.9646 | 1543 | 1.82 | 640
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | XR188 | TRUE | 5000.7034 | 608.151 | 0.37797 | 43 | 0.00010266 | 1579 | 145.3531 | 1791 | 0.025596 | 1.1006 | 1544 | 0.05 | 1999
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 616 | FALSE | 49320.745 | 4247.523 | 2.6399 | 198 | 8.18e-05 | 2160 | 268.44 | 1503 | 0.025585 | 5.0659 | 1545 | 0.02 | 2449
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 781566 | FALSE | 1246.3402 | 1113.5139 | 0.69205 | 11 | 0.00014318 | 824 | 155.6264 | 1762 | 0.025518 | 0.28069 | 1546 |  | 3459
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 9560 | FALSE | 35435.963 | 35435.963 | 22.0236 | 226 | 5.282e-05 | 2976 | 582.977 | 1120 | 0.025353 | 5.7297 | 1547 | 0.31 | 1001
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 7104 | FALSE | 19430.6652 | 19430.6652 | 12.0762 | 148 | 0.0001151 | 1296 | 163.538 | 1738 | 0.025302 | 3.7447 | 1548 | 13.46 | 365
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 9002 | FALSE | 9863.4451 | 1568.4919 | 0.97482 | 74 | 0.0001072 | 1468 | 178.96 | 1685 | 0.025292 | 1.8716 | 1549 | 0.04 | 2144
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 636 | FALSE | 10208.6635 | 8793.2474 | 5.465 | 81 | 0.00012369 | 1126 | 135.9278 | 1827 | 0.025287 | 2.0483 | 1550 | 0.41 | 940
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 37484 | FALSE | 15938.0756 | 12688.6958 | 7.8861 | 74 | 0.0001949 | 416 | 197.6391 | 1647 | 0.025267 | 1.8698 | 1551 | 3.58 | 540
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 844294 | FALSE | 9847.8884 | 3879.784 | 2.4113 | 55 | 0.0001067 | 1485 | 276.8057 | 1480 | 0.025242 | 1.3883 | 1552 |  | 2882
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 37522 | TRUE | 4999.5672 | 833.6297 | 0.5181 | 43 | 3.7339e-05 | 3307 | 997.9464 | 835 | 0.025221 | 1.0845 | 1553 | 0.42 | 937
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 922 | FALSE | 12634.8407 | 12589.4258 | 7.8244 | 84 | 5.9231e-05 | 2798 | 352.2884 | 1369 | 0.025187 | 2.1157 | 1554 | 0.06 | 1854
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | V46 | FALSE | 33477.4498 | 32077.3964 | 19.9362 | 206 | 6.5385e-05 | 2604 | 359.6086 | 1354 | 0.025184 | 5.1879 | 1555 | 0.58 | 860
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | CB | FALSE | 10840.0956 | 10840.0956 | 6.7372 | 79 | 5.5221e-05 | 2906 | 463.403 | 1231 | 0.025156 | 1.9873 | 1556 | 0 | 2629
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 608 | FALSE | 28658.1175 | 28658.1175 | 17.8111 | 74 | 9.5295e-05 | 1755 | 248.4816 | 1545 | 0.025135 | 1.86 | 1557 | 0.18 | 1210
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 93234 | FALSE | 18471.7273 | 18471.7273 | 11.4803 | 96 | 0.0002481 | 222 | 135.7036 | 1830 | 0.025062 | 2.4059 | 1558 | 7.72 | 442
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | CB | TRUE | 6358.3504 | 326.8592 | 0.20314 | 48 | 0.00010128 | 1621 | 121.8474 | 1865 | 0.025061 | 1.2029 | 1559 | 0.07 | 1754
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 9732 | FALSE | 33758.8908 | 33758.8908 | 20.9813 | 267 | 0.00010167 | 1613 | 282.8705 | 1469 | 0.025046 | 6.6872 | 1560 | 4.84 | 504
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 524 | FALSE | 20718.9245 | 9871.5042 | 6.1352 | 162 | 9.4892e-05 | 1769 | 289.834 | 1464 | 0.02502 | 4.0533 | 1561 | 3.23 | 553
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 63868 | FALSE | 25546.2406 | 25546.2406 | 15.8771 | 171 | 8.8626e-05 | 1968 | 190.8082 | 1660 | 0.024964 | 4.2689 | 1562 | 0.04 | 2158
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 578852 | FALSE | 38890.7673 | 33210.6867 | 20.6406 | 173 | 9.1712e-05 | 1853 | 190.7466 | 1661 | 0.024946 | 4.3156 | 1563 | 0 | 2630
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 5134 | FALSE | 4886.1695 | 1018.6198 | 0.63308 | 23 | 6.0194e-05 | 2767 | 173.1479 | 1703 | 0.024922 | 0.57321 | 1564 | 0.02 | 2554
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 384530 | FALSE | 6144.6716 | 6144.6716 | 3.8189 | 12 | 0.00011661 | 1259 | 223.8048 | 1598 | 0.024779 | 0.29735 | 1565 |  | 3460
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 1034 | FALSE | 17942.0463 | 17942.0463 | 11.1511 | 80 | 8.3104e-05 | 2129 | 308.8782 | 1434 | 0.024689 | 1.9751 | 1566 | 37.44 | 201
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 1806 | FALSE | 6482.8365 | 6482.8365 | 4.0291 | 17 | 0.00015564 | 687 | 310.6981 | 1431 | 0.024567 | 0.41764 | 1567 | 0.08 | 1588
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 7040 | FALSE | 36891.8795 | 33515.8907 | 20.8303 | 119 | 0.00010008 | 1645 | 276.795 | 1481 | 0.02433 | 2.8953 | 1568 | 0.03 | 2398
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 8050 | FALSE | 19488.3045 | 19488.3045 | 12.1121 | 137 | 6.4562e-05 | 2624 | 296.266 | 1454 | 0.024311 | 3.3307 | 1569 | 82.85 | 41
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 397902 | TRUE | 2608.3236 | 717.5326 | 0.44595 | 9 | 1.8967e-05 | 3553 | 1301.6353 | 682 | 0.024302 | 0.21872 | 1570 |  | 3589
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 61816 | FALSE | 37826.9874 | 37826.9874 | 23.5096 | 228 | 9.0781e-05 | 1889 | 261.0762 | 1521 | 0.0243 | 5.5405 | 1571 | 0.1 | 1458
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | CB | FALSE | 26239.5079 | 25449.7716 | 15.8171 | 183 | 5.9389e-05 | 2793 | 407.261 | 1290 | 0.024236 | 4.4352 | 1572 | 0.24 | 1103
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 472660 | FALSE | 2333.6937 | 2333.6937 | 1.4504 | 18 | 0.00011189 | 1371 | 307.8995 | 1436 | 0.024226 | 0.43606 | 1573 |  | 3221
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | CB | TRUE | 2139.8633 | 621.7387 | 0.38641 | 28 | 0.00025903 | 198 | 63.383 | 2133 | 0.024194 | 0.67743 | 1574 | 1.36 | 681
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 321000 | FALSE | 4053.5113 | 2330.3266 | 1.4483 | 13 | 3.5425e-05 | 3341 | 465.5516 | 1229 | 0.024187 | 0.31443 | 1575 |  | 3503
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 734248 | TRUE | 774.6582 | 774.6582 | 0.48145 | 9 | 9.7301e-05 | 1706 | 238.3995 | 1571 | 0.024166 | 0.2175 | 1576 |  | 2824
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 42650 | FALSE | 4322.5083 | 1459.6214 | 0.90716 | 37 | 0.00018107 | 502 | 100.7676 | 1951 | 0.024082 | 0.89104 | 1577 | 0.04 | 2229
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 90548 | FALSE | 28870.4925 | 28870.4925 | 17.9431 | 168 | 0.00013973 | 872 | 196.9334 | 1651 | 0.024003 | 4.0325 | 1578 | 0.67 | 811
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 224708 | FALSE | 1049.1603 | 1033.1582 | 0.64211 | 9 | 0.00015636 | 681 | 235.0194 | 1578 | 0.02399 | 0.21591 | 1579 |  | 3374
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 35424 | FALSE | 22308.0719 | 22308.0719 | 13.8646 | 147 | 0.00020736 | 374 | 171.1392 | 1711 | 0.023757 | 3.4923 | 1580 | 74.11 | 58
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 51696 | FALSE | 32551.2584 | 28077.2635 | 17.4501 | 238 | 0.00017871 | 514 | 165.4297 | 1734 | 0.023753 | 5.6532 | 1581 | 0.86 | 763
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 738866 | FALSE | 4335.7412 | 3280.2516 | 2.0387 | 28 | 6.3795e-05 | 2653 | 268.4844 | 1502 | 0.023732 | 0.66451 | 1582 | 0.1 | 1506
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 940112 | TRUE | 489.7385 | 455.0253 | 0.2828 | 2 | 5.8767e-05 | 2813 | 268.9489 | 1500 | 0.023701 | 0.047401 | 1583 |  | 3616
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 438074 | TRUE | 2039.2275 | 516.2478 | 0.32085 | 6 | 3.2276e-05 | 3397 | 1470.0727 | 606 | 0.023646 | 0.14187 | 1584 |  | 3592
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 350 | FALSE | 31334.246 | 8365.2365 | 5.199 | 194 | 8.9262e-05 | 1940 | 270.3135 | 1496 | 0.023632 | 4.5846 | 1585 | 0.09 | 1536
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | CB | FALSE | 15763.1114 | 12699.351 | 7.8927 | 97 | 5.9509e-05 | 2789 | 274.1428 | 1486 | 0.023627 | 2.2918 | 1586 | 0.1 | 1488
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | L3361 | FALSE | 3015.6838 | 3015.6838 | 1.8743 | 21 | 6.3649e-05 | 2658 | 377.9344 | 1325 | 0.023616 | 0.49595 | 1587 | 0.09 | 1563
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 122 | FALSE | 11125.688 | 2112.7276 | 1.3131 | 54 | 6.2796e-05 | 2689 | 203.6365 | 1635 | 0.023602 | 1.2745 | 1588 | 0.03 | 2263
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 95294 | FALSE | 43494.7194 | 43494.7194 | 27.0321 | 186 | 0.00012237 | 1142 | 194.7256 | 1654 | 0.023449 | 4.3615 | 1589 | 0.05 | 2049
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 764 | FALSE | 23643.468 | 23643.468 | 14.6945 | 146 | 0.00012366 | 1128 | 171.5032 | 1710 | 0.023389 | 3.4148 | 1590 | 57.88 | 95
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 516510 | FALSE | 13673.0725 | 6073.3479 | 3.7746 | 73 | 9.3061e-05 | 1818 | 270.871 | 1493 | 0.02337 | 1.706 | 1591 |  | 3347
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 3172 | FALSE | 60635.9905 | 60635.9905 | 37.6855 | 448 | 0.00020312 | 385 | 59.0594 | 2161 | 0.023346 | 10.4588 | 1592 | 67.49 | 73
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 154256 | TRUE | 446.5228 | 430.6088 | 0.26763 | 2 | 0.00011705 | 1248 | 293.424 | 1459 | 0.023318 | 0.046636 | 1593 |  | 3510
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 307998 | TRUE | 911.4775 | 895.4026 | 0.5565 | 6 | 0.00010251 | 1588 | 237.8428 | 1573 | 0.023314 | 0.13989 | 1594 |  | 3235
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 170 | FALSE | 33470.2158 | 28905.2433 | 17.9647 | 223 | 9.0997e-05 | 1881 | 278.3702 | 1476 | 0.023285 | 5.1925 | 1595 | 10.49 | 396
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 347280 | FALSE | 20187.7037 | 12761.9341 | 7.9316 | 99 | 7.6036e-05 | 2307 | 290.5041 | 1463 | 0.023256 | 2.3024 | 1596 |  | 3109
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8302 | FALSE | 13154.2224 | 13154.2224 | 8.1754 | 83 | 9.5232e-05 | 1760 | 244.7794 | 1556 | 0.023206 | 1.9261 | 1597 | 0.09 | 1552
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 3090 | FALSE | 17393.6531 | 17393.6531 | 10.8102 | 58 | 0.00018901 | 447 | 142.6437 | 1798 | 0.023177 | 1.3443 | 1598 | 0.06 | 1843
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 2040 | FALSE | 14724.8662 | 14724.8662 | 9.1516 | 21 | 0.00015655 | 679 | 141.5532 | 1807 | 0.023168 | 0.48652 | 1599 | 17.99 | 328
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | XR548 | FALSE | 14288.8839 | 2708.1629 | 1.6831 | 95 | 8.7871e-05 | 1987 | 271.2652 | 1492 | 0.023159 | 2.2001 | 1600 | 0.04 | 2088
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 10870 | FALSE | 4188.8092 | 3071.5505 | 1.909 | 28 | 0.00010127 | 1622 | 246.1327 | 1549 | 0.023077 | 0.64616 | 1601 | 0.04 | 2108
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 3168 | FALSE | 48228.3961 | 48228.3961 | 29.9741 | 285 | 0.00015583 | 684 | 176.2133 | 1695 | 0.023045 | 6.5678 | 1602 | 0.24 | 1095
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 531594 | FALSE | 4284.5499 | 3998.7287 | 2.4852 | 25 | 5.9727e-05 | 2782 | 338.5434 | 1391 | 0.022917 | 0.57293 | 1603 |  | 3558
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 8140 | FALSE | 42456.9039 | 42456.9039 | 26.3871 | 260 | 8.2014e-05 | 2153 | 273.2886 | 1487 | 0.022915 | 5.958 | 1604 | 41.27 | 178
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | A22 | TRUE | 21048.1737 | 0 | 0 | 167 | 6.0117e-05 | 2769 | 362.8063 | 1349 | 0.022889 | 3.8224 | 1605 | 0.03 | 2288
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 557000 | TRUE | 398.6933 | 335.0317 | 0.20822 | 3 | 0.00012959 | 1015 | 348.9375 | 1373 | 0.022855 | 0.068564 | 1606 |  | 3596
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 2006 | FALSE | 27571.1883 | 27571.1883 | 17.1356 | 151 | 6.0918e-05 | 2751 | 384.5024 | 1313 | 0.022834 | 3.4479 | 1607 | 0.22 | 1125
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 641808 | FALSE | 41435.7029 | 41435.7029 | 25.7525 | 234 | 0.00014735 | 768 | 181.2789 | 1681 | 0.022822 | 5.3404 | 1608 | 0.36 | 973
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 7142 | FALSE | 24816.4121 | 6275.5413 | 3.9003 | 100 | 7.7237e-05 | 2282 | 356.2375 | 1361 | 0.022773 | 2.2773 | 1609 | 0.03 | 2276
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 58448 | FALSE | 7774.1256 | 7141.1012 | 4.4382 | 22 | 8.8643e-05 | 1966 | 261.6309 | 1519 | 0.022766 | 0.50086 | 1610 |  | 3368
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 630456 | FALSE | 8616.6169 | 8616.6169 | 5.3553 | 37 | 0.00023208 | 277 | 84.9164 | 2030 | 0.022761 | 0.84216 | 1611 |  | 2888
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 84278 | FALSE | 2506.1692 | 2490.1671 | 1.5476 | 18 | 7.3083e-05 | 2392 | 245.6104 | 1553 | 0.022717 | 0.4089 | 1612 | 2.62 | 594
5345 | ELK 11011300 | 42981101 | ELK 1101 | 1300 | FALSE | 15995.4516 | 5711.2619 | 3.5496 | 64 | 8.5201e-05 | 2052 | 259.4524 | 1525 | 0.02261 | 1.447 | 1613 | 0.01 | 2613
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 9712 | FALSE | 29909.7326 | 29909.7326 | 18.589 | 214 | 0.00017251 | 547 | 156.1721 | 1761 | 0.022607 | 4.838 | 1614 | 0.65 | 825
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 1902 | FALSE | 11685.375 | 10562.7391 | 6.5648 | 43 | 0.00014928 | 746 | 134.194 | 1834 | 0.022585 | 0.97115 | 1615 | 0.08 | 1666
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 895310 | TRUE | 4366.1321 | 592.9592 | 0.36853 | 31 | 6.4236e-05 | 2637 | 241.124 | 1565 | 0.022565 | 0.69951 | 1616 |  | 3336
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | MR178 | FALSE | 21546.6859 | 2579.6297 | 1.6033 | 117 | 6.7557e-05 | 2547 | 427.86 | 1263 | 0.022562 | 2.6398 | 1617 |  | 2847
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 198 | FALSE | 10335.8179 | 10335.8179 | 6.4238 | 62 | 0.0001183 | 1224 | 193.0004 | 1658 | 0.02256 | 1.3987 | 1618 | 41.1 | 181
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 251688 | FALSE | 12475.4445 | 11233.7101 | 6.9818 | 68 | 7.4101e-05 | 2355 | 394.4035 | 1300 | 0.022486 | 1.5291 | 1619 |  | 3207
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 858200 | FALSE | 9571.0308 | 9200.2096 | 5.718 | 31 | 6.601e-05 | 2588 | 330.1244 | 1397 | 0.022446 | 0.69582 | 1620 |  | 3395
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 59128 | FALSE | 11301.2737 | 1201.9482 | 0.74702 | 65 | 0.00010017 | 1639 | 414.1368 | 1279 | 0.022397 | 1.4558 | 1621 |  | 2980
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 85112 | FALSE | 10932.2503 | 10932.2503 | 6.7944 | 54 | 7.2027e-05 | 2417 | 306.4662 | 1437 | 0.022386 | 1.2088 | 1622 | 0.07 | 1740
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 518 | FALSE | 36303.8238 | 4840.0159 | 3.0081 | 165 | 0.0001564 | 680 | 133.4232 | 1837 | 0.02237 | 3.6911 | 1623 | 0.31 | 1002
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 769230 | FALSE | 27505.7293 | 17732.852 | 11.021 | 160 | 0.00011179 | 1372 | 159.0323 | 1749 | 0.022338 | 3.574 | 1624 | 0.28 | 1034
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 37350 | FALSE | 39069.9006 | 39069.9006 | 24.2821 | 255 | 7.6956e-05 | 2287 | 360.2031 | 1353 | 0.02227 | 5.6788 | 1625 | 13.94 | 359
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 648698 | FALSE | 30462.3699 | 17135.0454 | 10.6495 | 173 | 2.2209e-05 | 3516 | 1031.0161 | 807 | 0.022255 | 3.85 | 1626 |  | 2707
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | CB | FALSE | 12882.1278 | 12682.5013 | 7.8822 | 86 | 0.00028932 | 141 | 75.4177 | 2064 | 0.022172 | 1.9068 | 1627 | 0.07 | 1701
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 1514 | FALSE | 23767.6372 | 23767.6372 | 14.7717 | 123 | 0.0005607 | 23 | 46.0416 | 2239 | 0.022168 | 2.7266 | 1628 | 0.07 | 1675
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 512313 | TRUE | 1333.0799 | 785.9125 | 0.48845 | 10 | 3.7023e-05 | 3314 | 418.9141 | 1273 | 0.022063 | 0.22063 | 1629 |  | 3136
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 895784 | FALSE | 16727.2163 | 12538.91 | 7.793 | 110 | 8.3743e-05 | 2101 | 275.8868 | 1483 | 0.022046 | 2.4251 | 1630 |  | 3006
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 75204 | FALSE | 29879.1855 | 1376.4738 | 0.85548 | 130 | 8.0747e-05 | 2187 | 212.0292 | 1614 | 0.021935 | 2.8515 | 1631 | 0.01 | 2584
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 848530 | TRUE | 2567.2359 | 715.3706 | 0.44461 | 17 | 9.0059e-05 | 1909 | 263.7059 | 1513 | 0.021849 | 0.37143 | 1632 |  | 3381
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 34416 | FALSE | 16821.5127 | 16821.5127 | 10.4546 | 113 | 8.8542e-05 | 1971 | 264.2059 | 1510 | 0.021823 | 2.466 | 1633 | 42.3 | 170
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | CB | FALSE | 28620.471 | 28620.471 | 17.7877 | 195 | 0.00020845 | 368 | 153.8768 | 1765 | 0.02173 | 4.2374 | 1634 | 37.1 | 202
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 144140 | TRUE | 2469.4129 | 417.0111 | 0.25917 | 20 | 0.00015373 | 713 | 178.8701 | 1686 | 0.021719 | 0.43439 | 1635 |  | 3076
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 311906 | FALSE | 1528.1122 | 1112.4459 | 0.69139 | 12 | 0.00010712 | 1471 | 200.1105 | 1641 | 0.021675 | 0.2601 | 1636 |  | 3445
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 8652 | FALSE | 21158.9046 | 21158.9046 | 13.1503 | 114 | 0.0003142 | 113 | 77.6007 | 2059 | 0.021633 | 2.4661 | 1637 | 8.55 | 422
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 2416 | FALSE | 50020.1074 | 46563.0328 | 28.9391 | 360 | 0.00016423 | 598 | 156.2016 | 1760 | 0.021547 | 7.7569 | 1638 | 0.56 | 863
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 630 | FALSE | 21891.4244 | 20012.2615 | 12.4377 | 154 | 9.5266e-05 | 1756 | 292.7922 | 1460 | 0.021529 | 3.3154 | 1639 | 0.13 | 1357
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 771258 | TRUE | 308.3578 | 308.3578 | 0.19165 | 4 | 6.8099e-05 | 2532 | 427.9894 | 1262 | 0.021484 | 0.085935 | 1640 |  | 3432
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 3902 | FALSE | 8223.6344 | 8223.6344 | 5.111 | 9 | 0.00018188 | 498 | 110.945 | 1907 | 0.021389 | 0.1925 | 1641 | 0.02 | 2480
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | CB | FALSE | 22023.4026 | 21461.232 | 13.3382 | 163 | 0.00013265 | 967 | 170.2363 | 1715 | 0.021383 | 3.4854 | 1642 | 0.14 | 1316
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 609690 | FALSE | 12043.451 | 7774.3071 | 4.8318 | 72 | 7.5587e-05 | 2321 | 321.8791 | 1411 | 0.021383 | 1.5396 | 1643 |  | 2744
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 6502 | FALSE | 6145.0425 | 1500.682 | 0.93268 | 52 | 0.00017025 | 561 | 88.4192 | 2012 | 0.021251 | 1.1051 | 1644 | 1.73 | 647
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 59046 | FALSE | 6015.5462 | 5641.1576 | 3.506 | 15 | 0.00010509 | 1522 | 101.9046 | 1945 | 0.021246 | 0.31869 | 1645 | 0.25 | 1078
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 9712 | FALSE | 39765.9579 | 39765.9579 | 24.7147 | 226 | 0.00014908 | 750 | 116.696 | 1890 | 0.021241 | 4.8004 | 1646 | 0.54 | 877
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 2072 | TRUE | 27455.5664 | 501.4668 | 0.31166 | 193 | 9.3699e-05 | 1804 | 181.6575 | 1679 | 0.021197 | 4.091 | 1647 | 0.03 | 2308
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 708 | FALSE | 7904.2269 | 6040.8568 | 3.7544 | 61 | 0.00013285 | 959 | 152.2948 | 1771 | 0.02118 | 1.292 | 1648 | 0.54 | 876
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 1010 | FALSE | 71394.2707 | 71394.2707 | 44.3718 | 479 | 0.00011001 | 1412 | 172.5805 | 1708 | 0.021168 | 10.1396 | 1649 | 129.45 | 6
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 5460 | FALSE | 18980.3372 | 18980.3372 | 11.7964 | 91 | 0.000114 | 1322 | 193.3663 | 1657 | 0.021116 | 1.9215 | 1650 | 41.43 | 176
9400 | BELL 110880680 | 152701108 | BELL 1108 | 80680 | FALSE | 2866.5185 | 1030.5857 | 0.64051 | 24 | 0.00023396 | 265 | 175.0191 | 1697 | 0.021095 | 0.50627 | 1651 | 0.04 | 2179
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 80930 | FALSE | 29528.4888 | 29528.4888 | 18.3521 | 180 | 6.8218e-05 | 2529 | 304.5139 | 1442 | 0.021019 | 3.7835 | 1652 | 0.22 | 1126
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | CB | TRUE | 11751.5136 | 394.0047 | 0.24488 | 100 | 0.00016594 | 582 | 73.1844 | 2079 | 0.021017 | 2.1017 | 1653 | 0.02 | 2416
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 902 | FALSE | 19453.8935 | 19453.8935 | 12.0907 | 83 | 9.1473e-05 | 1858 | 227.244 | 1592 | 0.020905 | 1.7351 | 1654 | 0.72 | 798
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 783467 | FALSE | 16521.4957 | 16448.6096 | 10.2229 | 61 | 8.018e-05 | 2201 | 245.1782 | 1554 | 0.020785 | 1.2679 | 1655 |  | 3145
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 1180 | FALSE | 20847.2086 | 20847.2086 | 12.9566 | 141 | 0.00012525 | 1094 | 118.9045 | 1874 | 0.020771 | 2.9287 | 1656 | 0.11 | 1417
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 814656 | TRUE | 28.1252 | 28.1252 | 0.01748 | 1 | 0.00086571 | 4 | 23.8451 | 2401 | 0.020643 | 0.020643 | 1657 |  | 3634
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | CB | FALSE | 3707.9332 | 3707.9332 | 2.3045 | 31 | 9.4015e-05 | 1792 | 320.4886 | 1415 | 0.020623 | 0.63931 | 1658 | 0.11 | 1444
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 812366 | FALSE | 4450.8969 | 4421.1038 | 2.7477 | 28 | 8.5129e-05 | 2055 | 149.7437 | 1778 | 0.020596 | 0.57668 | 1659 |  | 2843
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 694641 | FALSE | 6527.852 | 6527.852 | 4.0571 | 49 | 7.3209e-05 | 2390 | 257.8416 | 1526 | 0.020553 | 1.0071 | 1660 |  | 3355
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 7144 | FALSE | 7491.0055 | 7491.0055 | 4.6557 | 52 | 8.7335e-05 | 2005 | 376.542 | 1327 | 0.020479 | 1.0649 | 1661 | 0.36 | 967
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 752596 | TRUE | 1041.1396 | 395.1334 | 0.24558 | 6 | 0.00010963 | 1418 | 256.5638 | 1530 | 0.020465 | 0.12279 | 1662 |  | 3606
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 851 | FALSE | 2029.0984 | 2029.0984 | 1.2611 | 14 | 0.00014146 | 845 | 190.4229 | 1662 | 0.020416 | 0.28582 | 1663 | 44.15 | 161
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 4790 | FALSE | 52731.0383 | 52731.0383 | 32.7726 | 305 | 0.00011374 | 1325 | 232.2083 | 1584 | 0.020377 | 6.2151 | 1664 | 47.18 | 136
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 60080 | FALSE | 16285.3103 | 15418.9407 | 9.5829 | 64 | 0.00014044 | 864 | 185.0893 | 1672 | 0.020345 | 1.3021 | 1665 | 0.24 | 1091
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 11132 | FALSE | 69633.6958 | 69633.6958 | 43.2776 | 420 | 0.00012774 | 1054 | 197.2748 | 1649 | 0.020262 | 8.5102 | 1666 | 0.54 | 875
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 65932 | FALSE | 7276.7194 | 7276.7194 | 4.5225 | 48 | 0.00012509 | 1096 | 211.5152 | 1616 | 0.020219 | 0.97052 | 1667 | 64.62 | 78
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 83098 | FALSE | 12739.0077 | 12739.0077 | 7.9173 | 104 | 7.5775e-05 | 2312 | 344.4746 | 1378 | 0.020137 | 2.0942 | 1668 | 45.66 | 147
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 318 | FALSE | 31114.0365 | 31114.0365 | 19.3375 | 228 | 0.00011669 | 1256 | 178.6742 | 1688 | 0.020097 | 4.5821 | 1669 | 88.23 | 35
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 7068 | FALSE | 6155.1451 | 6139.1207 | 3.8155 | 12 | 7.071e-05 | 2451 | 336.2364 | 1392 | 0.019995 | 0.23993 | 1670 | 0.05 | 1997
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | CB | FALSE | 10025.1577 | 6936.1203 | 4.3108 | 73 | 0.00013127 | 993 | 100.6191 | 1952 | 0.019906 | 1.4531 | 1671 | 0.05 | 1978
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | V60 | FALSE | 25811.5583 | 25811.5583 | 16.042 | 142 | 6.4335e-05 | 2632 | 354.0238 | 1367 | 0.0199 | 2.8258 | 1672 | 0.51 | 892
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 368158 | FALSE | 14121.5307 | 4484.8758 | 2.7874 | 105 | 0.0001001 | 1644 | 219.1144 | 1607 | 0.019862 | 2.0855 | 1673 |  | 2756
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 1376 | FALSE | 14477.8455 | 14477.8455 | 8.998 | 70 | 0.00013205 | 982 | 179.7284 | 1683 | 0.019836 | 1.3885 | 1674 | 0.02 | 2535
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 714 | FALSE | 17594.5823 | 5568.6627 | 3.4609 | 121 | 0.0001288 | 1033 | 138.0832 | 1817 | 0.019829 | 2.3993 | 1675 | 0.08 | 1672
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 75340 | FALSE | 7696.0179 | 7696.0179 | 4.7831 | 62 | 0.00022111 | 314 | 112.7853 | 1902 | 0.01968 | 1.2202 | 1676 | 43.45 | 168
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 4817 | FALSE | 5079.2964 | 5079.2964 | 3.1568 | 42 | 0.00011215 | 1364 | 172.256 | 1709 | 0.019666 | 0.82599 | 1677 | 8.13 | 436
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 951424 | FALSE | 5857.3043 | 1124.2371 | 0.69872 | 49 | 6.6606e-05 | 2568 | 260.8969 | 1522 | 0.019501 | 0.95554 | 1678 |  | 3026
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 3304 | FALSE | 27901.6416 | 27901.6416 | 17.341 | 88 | 0.00030684 | 123 | 72.4308 | 2081 | 0.019486 | 1.7148 | 1679 | 0.14 | 1315
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 10342 | FALSE | 2930.8819 | 2930.8819 | 1.8216 | 23 | 0.00012225 | 1143 | 225.3144 | 1595 | 0.019463 | 0.44766 | 1680 | 0.23 | 1111
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 38436 | FALSE | 7699.8876 | 7253.5318 | 4.5081 | 62 | 0.00011304 | 1342 | 129.1673 | 1847 | 0.019424 | 1.2043 | 1681 | 0.17 | 1243
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 540991 | FALSE | 2594.6741 | 2544.5262 | 1.5814 | 16 | 6.9859e-05 | 2477 | 260.165 | 1524 | 0.019417 | 0.31068 | 1682 |  | 3290
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 1504 | FALSE | 19432.0475 | 17454.8051 | 10.8482 | 64 | 0.00027686 | 165 | 148.5088 | 1782 | 0.019342 | 1.2379 | 1683 | 0.01 | 2608
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 416 | FALSE | 5187.8358 | 4249.986 | 2.6414 | 28 | 0.00012384 | 1122 | 177.6431 | 1689 | 0.019316 | 0.54085 | 1684 | 0.35 | 975
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 1546 | FALSE | 37312.9087 | 22193.9329 | 13.7936 | 102 | 2.0489e-05 | 3539 | 794.3875 | 945 | 0.019258 | 1.9643 | 1685 | 0.02 | 2496
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 6018 | FALSE | 30239.5339 | 25219.5525 | 15.6741 | 160 | 8.5245e-05 | 2048 | 248.6459 | 1544 | 0.019223 | 3.0757 | 1686 | 0.05 | 1942
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 807953 | TRUE | 1013.1517 | 745.8215 | 0.46353 | 11 | 0.00012129 | 1161 | 149.9335 | 1777 | 0.019176 | 0.21093 | 1687 |  | 2915
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 223792 | FALSE | 1426.5673 | 1262.347 | 0.78455 | 10 | 7.6537e-05 | 2293 | 237.9603 | 1572 | 0.019106 | 0.19106 | 1688 |  | 2832
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | CB | FALSE | 14256.0927 | 10229.3323 | 6.3576 | 98 | 0.00010673 | 1484 | 150.89 | 1774 | 0.019021 | 1.864 | 1689 | 0.06 | 1871
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 7702 | TRUE | 30606.5708 | 0 | 0 | 168 | 8.5206e-05 | 2051 | 328.4397 | 1400 | 0.018893 | 3.174 | 1690 | 0.04 | 2103
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 70960 | FALSE | 18837.8278 | 9297.8122 | 5.7786 | 103 | 0.00023998 | 245 | 91.5029 | 1995 | 0.018609 | 1.9167 | 1691 | 0 | 2636
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 2987 | FALSE | 3171.9583 | 3171.9583 | 1.9714 | 18 | 0.0002636 | 186 | 74.107 | 2072 | 0.018603 | 0.33485 | 1692 | 15.92 | 343
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | CB | FALSE | 24644.898 | 24644.898 | 15.3169 | 123 | 0.00014722 | 772 | 162.3912 | 1740 | 0.0185 | 2.2755 | 1693 | 73.53 | 61
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 928 | FALSE | 24779.274 | 22468.3871 | 13.9642 | 125 | 9.505e-05 | 1765 | 208.5932 | 1622 | 0.018489 | 2.3111 | 1694 | 0.05 | 2054
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | CB | FALSE | 6642.1904 | 4240.0548 | 2.6352 | 54 | 0.00012016 | 1183 | 144.2308 | 1793 | 0.018327 | 0.98966 | 1695 | 0.11 | 1449
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 1305 | FALSE | 18201.3708 | 18201.3708 | 11.3122 | 105 | 0.00010838 | 1442 | 197.4917 | 1648 | 0.01831 | 1.9226 | 1696 | 0.76 | 784
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 575872 | FALSE | 2328.1768 | 1906.857 | 1.1851 | 12 | 0.00010594 | 1497 | 157.6636 | 1757 | 0.018279 | 0.21935 | 1697 |  | 3165
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | H80 | FALSE | 31889.194 | 31889.194 | 19.8193 | 164 | 9.888e-05 | 1673 | 213.2657 | 1612 | 0.018248 | 2.9927 | 1698 |  | 2739
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 9432 | FALSE | 32768.2312 | 28100.4349 | 17.4645 | 251 | 0.0001473 | 771 | 86.1349 | 2022 | 0.018233 | 4.5765 | 1699 | 0.25 | 1080
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | CB | FALSE | 28981.2992 | 28981.2992 | 18.012 | 104 | 0.00012953 | 1019 | 141.7915 | 1804 | 0.018204 | 1.8932 | 1700 | 44.04 | 162
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 79086 | FALSE | 11075.7434 | 10954.594 | 6.8083 | 82 | 0.00011015 | 1408 | 169.8424 | 1717 | 0.018179 | 1.4907 | 1701 | 0.08 | 1638
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 32556 | TRUE | 2113.2756 | 188.0999 | 0.1169 | 19 | 0.00017313 | 540 | 58.9098 | 2162 | 0.018147 | 0.34478 | 1702 | 0.05 | 2039
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 2094 | FALSE | 5517.0419 | 5517.0419 | 3.4289 | 11 | 0.00021985 | 323 | 101.8231 | 1947 | 0.018088 | 0.19897 | 1703 | 0.01 | 2580
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | CB | FALSE | 19055.2866 | 19055.2866 | 11.8429 | 80 | 8.794e-05 | 1984 | 356.7774 | 1359 | 0.018079 | 1.4463 | 1704 | 0.23 | 1117
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 482838 | FALSE | 17714.345 | 14284.261 | 8.8777 | 52 | 6.1569e-05 | 2730 | 318.0089 | 1421 | 0.018057 | 0.93898 | 1705 |  | 3180
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 2422 | FALSE | 13951.5772 | 13951.5772 | 8.671 | 81 | 0.00012199 | 1147 | 229.8045 | 1587 | 0.018043 | 1.4615 | 1706 | 0.07 | 1676
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 437194 | FALSE | 1741.9129 | 1702.9792 | 1.0584 | 17 | 9.4479e-05 | 1781 | 148.2733 | 1783 | 0.018026 | 0.30645 | 1707 |  | 3303
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 86876 | FALSE | 13761.5335 | 3945.9351 | 2.4524 | 110 | 6.2134e-05 | 2715 | 110.516 | 1909 | 0.018007 | 1.9808 | 1708 | 0.03 | 2303
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 711966 | FALSE | 19227.2924 | 6326.045 | 3.9317 | 122 | 9.0078e-05 | 1907 | 205.4077 | 1625 | 0.017908 | 2.1848 | 1709 |  | 2982
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 1720 | FALSE | 9489.0848 | 9489.0848 | 5.8975 | 34 | 6.9471e-05 | 2488 | 304.935 | 1440 | 0.017864 | 0.60738 | 1710 | 23.51 | 285
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 2766 | FALSE | 5300.562 | 5300.562 | 3.2943 | 31 | 0.00018321 | 487 | 59.8653 | 2154 | 0.017834 | 0.55287 | 1711 | 29.29 | 242
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 261774 | FALSE | 21761.0718 | 21761.0718 | 13.5246 | 142 | 9.9916e-05 | 1650 | 183.8239 | 1678 | 0.01783 | 2.5319 | 1712 |  | 2952
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | CB | FALSE | 17908.5118 | 3627.2584 | 2.2544 | 118 | 9.0618e-05 | 1894 | 263.1957 | 1514 | 0.017802 | 2.1007 | 1713 | 0.7 | 809
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 432 | FALSE | 12624.3351 | 12624.3351 | 7.8461 | 72 | 0.00017278 | 544 | 132.4511 | 1841 | 0.017729 | 1.2765 | 1714 | 0.96 | 740
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 850102 | TRUE | 3948.9067 | 287.4404 | 0.17865 | 23 | 4.4232e-05 | 3186 | 279.8882 | 1472 | 0.01772 | 0.40756 | 1715 |  | 2955
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 90320 | FALSE | 44849.664 | 44849.664 | 27.8742 | 282 | 7.4079e-05 | 2356 | 382.5749 | 1315 | 0.017701 | 4.9917 | 1716 | 0.1 | 1463
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 2232 | FALSE | 32508.1294 | 25513.6468 | 15.8568 | 128 | 4.4844e-05 | 3165 | 539.0362 | 1160 | 0.017667 | 2.2614 | 1717 | 4.69 | 510
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 750804 | TRUE | 449.416 | 390.0676 | 0.24243 | 5 | 0.00016489 | 588 | 71.3665 | 2087 | 0.017655 | 0.088275 | 1718 |  | 3500
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 1589 | FALSE | 6873.0951 | 6873.0951 | 4.2717 | 52 | 8.5041e-05 | 2058 | 184.9596 | 1673 | 0.01765 | 0.91781 | 1719 | 0.08 | 1649
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 36816 | FALSE | 8023.9266 | 8023.9266 | 4.9869 | 60 | 0.00012475 | 1102 | 139.9542 | 1810 | 0.017625 | 1.0575 | 1720 | 0.09 | 1516
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | CB | FALSE | 11789.4236 | 11789.4236 | 7.3272 | 71 | 0.00029554 | 134 | 73.697 | 2075 | 0.017606 | 1.25 | 1721 | 13.84 | 360
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 1378 | FALSE | 40111.5829 | 39490.7149 | 24.5436 | 201 | 0.00013379 | 948 | 148.5755 | 1780 | 0.017574 | 3.5323 | 1722 | 0.05 | 2031
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 117328 | FALSE | 23158.4732 | 9894.6539 | 6.1496 | 44 | 4.0861e-05 | 3248 | 400.677 | 1296 | 0.017549 | 0.77216 | 1723 |  | 3271
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 1954 | FALSE | 17187.784 | 4223.5591 | 2.625 | 132 | 0.00016112 | 630 | 102.5688 | 1939 | 0.017468 | 2.3057 | 1724 | 0.07 | 1692
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 6060 | FALSE | 6540.8971 | 6540.8971 | 4.0652 | 50 | 0.00014094 | 855 | 178.7675 | 1687 | 0.01746 | 0.873 | 1725 | 0.1 | 1461
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 5042 | FALSE | 11222.6237 | 9737.3633 | 6.0518 | 90 | 0.0001242 | 1114 | 141.9193 | 1803 | 0.01743 | 1.5687 | 1726 | 6.17 | 471
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 739858 | FALSE | 8002.9028 | 7850.7225 | 4.8793 | 46 | 0.00010369 | 1557 | 204.17 | 1632 | 0.017426 | 0.80161 | 1727 |  | 3225
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 1406 | FALSE | 43882.3619 | 43882.3619 | 27.2731 | 204 | 9.5492e-05 | 1742 | 157.7153 | 1755 | 0.017352 | 3.5397 | 1728 | 0.18 | 1217
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 477914 | TRUE | 388.2883 | 307.8291 | 0.19132 | 3 | 0.00012285 | 1135 | 285.164 | 1467 | 0.017329 | 0.051987 | 1729 |  | 3582
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 796050 | TRUE | 5067.2794 | 383.7484 | 0.2385 | 45 | 4.1549e-05 | 3233 | 109.4022 | 1911 | 0.017291 | 0.7781 | 1730 |  | 2738
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 1721 | FALSE | 10927.2973 | 10927.2973 | 6.7914 | 52 | 0.0001634 | 607 | 107.9769 | 1918 | 0.01726 | 0.89751 | 1731 | 0.12 | 1367
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 298 | FALSE | 20337.8041 | 20253.8323 | 12.5878 | 123 | 0.00016852 | 572 | 115.628 | 1892 | 0.017238 | 2.1202 | 1732 | 85.76 | 39
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 92870 | TRUE | 25931.8169 | 185.9475 | 0.11557 | 187 | 6.3919e-05 | 2649 | 163.1162 | 1739 | 0.017207 | 3.2176 | 1733 | 2.3 | 615
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 597518 | TRUE | 2581.15 | 65.1647 | 0.0405 | 30 | 4.6337e-05 | 3129 | 233.218 | 1579 | 0.017175 | 0.51524 | 1734 | 0.07 | 1768
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 3312 | FALSE | 14682.6253 | 12944.3529 | 8.045 | 82 | 3.1897e-05 | 3403 | 501.3484 | 1197 | 0.017169 | 1.4079 | 1735 | 0.05 | 1934
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 1488 | FALSE | 53867.328 | 3970.6557 | 2.4678 | 217 | 3.7897e-05 | 3301 | 226.8447 | 1594 | 0.01714 | 3.7195 | 1736 | 0.01 | 2597
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | CB | FALSE | 6895.2449 | 6754.5413 | 4.198 | 47 | 0.00021084 | 355 | 102.4575 | 1940 | 0.017137 | 0.80543 | 1737 | 0.07 | 1698
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 60114 | FALSE | 39130.9882 | 39130.9882 | 24.3201 | 220 | 0.00014614 | 787 | 173.2936 | 1702 | 0.016971 | 3.7337 | 1738 | 112.13 | 13
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 184604 | FALSE | 16467.2376 | 3361.2922 | 2.0891 | 106 | 3.7123e-05 | 3311 | 169.9457 | 1716 | 0.016935 | 1.7951 | 1739 |  | 2831
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | CB | FALSE | 3204.0009 | 1997.9569 | 1.2417 | 29 | 5.2977e-05 | 2969 | 262.0724 | 1517 | 0.016895 | 0.48997 | 1740 | 0.03 | 2250
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 3121 | FALSE | 4501.3904 | 4501.3904 | 2.7976 | 36 | 0.0001378 | 897 | 129.4168 | 1846 | 0.016885 | 0.60788 | 1741 | 54.14 | 108
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 8860 | FALSE | 6108.7785 | 3211.911 | 1.9962 | 34 | 0.0001502 | 733 | 173.1129 | 1705 | 0.016867 | 0.57347 | 1742 | 0.03 | 2306
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 1464 | FALSE | 1371.4854 | 1371.4854 | 0.85238 | 10 | 0.00011205 | 1368 | 126.5814 | 1854 | 0.01686 | 0.1686 | 1743 | 0.09 | 1538
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | CB | FALSE | 6022.6718 | 6022.6718 | 3.7431 | 20 | 0.00011138 | 1387 | 174.7898 | 1698 | 0.016801 | 0.33603 | 1744 | 22.21 | 295
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | N32 | FALSE | 47644.4105 | 47470.9597 | 29.5034 | 251 | 5.7034e-05 | 2860 | 298.1993 | 1451 | 0.016765 | 4.208 | 1745 | 0.14 | 1326
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 19582 | FALSE | 11698.5344 | 11698.5344 | 7.2707 | 80 | 0.0001731 | 541 | 110.8991 | 1908 | 0.016762 | 1.341 | 1746 | 0.2 | 1168
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 2166 | FALSE | 6559.0006 | 6559.0006 | 4.0764 | 41 | 0.00012787 | 1051 | 196.1831 | 1652 | 0.016743 | 0.68648 | 1747 | 0.04 | 2069
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | CB | FALSE | 17261.1138 | 17261.1138 | 10.7279 | 77 | 6.6357e-05 | 2581 | 354.4682 | 1366 | 0.016728 | 1.2881 | 1748 | 0.09 | 1562
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 95324 | FALSE | 10430.483 | 10430.483 | 6.4826 | 40 | 0.00024711 | 226 | 97.4816 | 1970 | 0.016671 | 0.66685 | 1749 | 0.05 | 1990
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 323694 | FALSE | 10298.1869 | 10298.1869 | 6.4004 | 17 | 0.00023892 | 250 | 89.5148 | 2002 | 0.016661 | 0.28324 | 1750 |  | 3406
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 438596 | FALSE | 17736.2716 | 17736.2716 | 11.0232 | 69 | 0.00028911 | 142 | 66.1845 | 2114 | 0.016624 | 1.1471 | 1751 |  | 3135
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2002 | FALSE | 4546.6103 | 4546.6103 | 2.8257 | 27 | 9.936e-05 | 1659 | 177.0336 | 1690 | 0.01654 | 0.44657 | 1752 | 0.03 | 2271
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 804 | FALSE | 35223.4878 | 35223.4878 | 21.8915 | 163 | 9.1106e-05 | 1878 | 209.4933 | 1620 | 0.016525 | 2.6936 | 1753 | 22.85 | 291
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 13496 | FALSE | 8111.7845 | 3211.8845 | 1.9962 | 58 | 8.2907e-05 | 2132 | 168.1169 | 1725 | 0.016506 | 0.95734 | 1754 | 0.04 | 2107
249 | RINCON 1103CB | 43321103 | RINCON 1103 | CB | FALSE | 6066.7415 | 3931.2505 | 2.4433 | 41 | 0.00016438 | 593 | 84.7695 | 2033 | 0.016461 | 0.67489 | 1755 | 3.87 | 532
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 439030 | FALSE | 31570.1115 | 31570.1115 | 19.621 | 200 | 4.6813e-05 | 3117 | 247.3908 | 1548 | 0.016434 | 3.2868 | 1756 | 0.34 | 978
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2012 | FALSE | 48303.6952 | 3708.2991 | 2.3047 | 73 | 4.249e-05 | 3218 | 610.7432 | 1094 | 0.016401 | 1.1972 | 1757 | 0.01 | 2617
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | FALSE | 6465.1165 | 6465.1165 | 4.0181 | 13 | 0.00010277 | 1576 | 122.9227 | 1861 | 0.01639 | 0.21307 | 1758 | 8.51 | 424
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 430 | FALSE | 11355.5979 | 11355.5979 | 7.0575 | 92 | 0.00013784 | 896 | 143.4477 | 1796 | 0.016311 | 1.5006 | 1759 | 1.14 | 709
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 1067 | FALSE | 1306.3843 | 1306.3843 | 0.81192 | 11 | 0.00037762 | 75 | 25.9963 | 2377 | 0.016 | 0.176 | 1760 | 0.39 | 956
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | CB | FALSE | 17781.8863 | 17449.8742 | 10.8452 | 133 | 0.00028585 | 146 | 98.8838 | 1960 | 0.015996 | 2.1275 | 1761 | 0.03 | 2400
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13430 | FALSE | 21106.6036 | 21106.6036 | 13.1178 | 129 | 3.9032e-05 | 3286 | 375.4366 | 1329 | 0.015945 | 2.057 | 1762 | 23.77 | 282
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 772781 | FALSE | 2316.7745 | 2316.7745 | 1.4399 | 12 | 0.00017201 | 551 | 85.3434 | 2027 | 0.015766 | 0.1892 | 1763 |  | 3286
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 3166 | FALSE | 19778.1528 | 19778.1528 | 12.2922 | 147 | 0.00014138 | 848 | 96.7473 | 1974 | 0.015763 | 2.3172 | 1764 | 0.13 | 1348
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | CB | FALSE | 7713.2869 | 7713.2869 | 4.7938 | 20 | 0.0002169 | 332 | 123.6935 | 1859 | 0.015736 | 0.31472 | 1765 | 0.28 | 1044
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 86696 | FALSE | 15512.3886 | 15512.3886 | 9.641 | 86 | 0.00022753 | 293 | 118.1033 | 1879 | 0.015606 | 1.3421 | 1766 | 11.17 | 386
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 416 | FALSE | 26082.6279 | 26031.4486 | 16.1787 | 79 | 0.00016777 | 576 | 81.2878 | 2042 | 0.015542 | 1.2278 | 1767 | 0.36 | 968
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 3170 | FALSE | 64049.8846 | 64049.8846 | 39.8073 | 445 | 0.00014644 | 781 | 151.3568 | 1773 | 0.015534 | 6.9125 | 1768 | 0.47 | 907
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | XR332 | FALSE | 29699.1922 | 29699.1922 | 18.4582 | 83 | 7.378e-05 | 2368 | 296.6239 | 1452 | 0.015532 | 1.2892 | 1769 | 0.12 | 1374
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 8170 | FALSE | 12697.6373 | 12388.5528 | 7.6995 | 109 | 0.00012036 | 1178 | 138.0395 | 1818 | 0.015509 | 1.6904 | 1770 | 0.24 | 1094
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | CB | FALSE | 11971.7401 | 11971.7401 | 7.4405 | 18 | 8.5097e-05 | 2056 | 173.0854 | 1706 | 0.015422 | 0.27759 | 1771 | 0.15 | 1279
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 338520 | FALSE | 12890.8329 | 12653.3631 | 7.8641 | 87 | 0.00011206 | 1367 | 151.4662 | 1772 | 0.015412 | 1.3409 | 1772 |  | 2737
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 1584 | FALSE | 20998.6153 | 20998.6153 | 13.0507 | 136 | 0.00015385 | 710 | 117.4189 | 1885 | 0.015387 | 2.0926 | 1773 | 0.14 | 1331
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 152 | FALSE | 16493.2298 | 2668.6977 | 1.6586 | 125 | 0.0001196 | 1193 | 103.0488 | 1937 | 0.015258 | 1.9072 | 1774 | 2.09 | 621
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 13494 | FALSE | 12093.2449 | 4454.735 | 2.7686 | 93 | 8.9665e-05 | 1924 | 170.6202 | 1712 | 0.015212 | 1.4148 | 1775 | 2.55 | 598
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 383748 | TRUE | 582.318 | 582.318 | 0.36191 | 4 | 0.00011476 | 1303 | 237.7564 | 1575 | 0.015207 | 0.060827 | 1776 |  | 3542
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 6084 | FALSE | 24635.3535 | 24635.3535 | 15.311 | 120 | 0.00027675 | 166 | 46.9926 | 2233 | 0.015158 | 1.8189 | 1777 | 0.26 | 1064
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 462 | FALSE | 6310.2369 | 4550.7014 | 2.8283 | 40 | 9.8301e-05 | 1683 | 125.2992 | 1858 | 0.015132 | 0.6053 | 1778 | 0.04 | 2104
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 7048 | FALSE | 47036.8755 | 18663.2877 | 11.5993 | 173 | 4.4641e-05 | 3172 | 271.6147 | 1491 | 0.015069 | 2.607 | 1779 | 0.05 | 2050
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | CB | FALSE | 19625.3536 | 4723.1827 | 2.9355 | 52 | 0.00018739 | 458 | 86.4729 | 2019 | 0.015061 | 0.78316 | 1780 | 0 | 2627
10131 | CMC 1101CB | 183111101 | CMC 1101 | CB | FALSE | 3286.0633 | 3286.0633 | 2.0423 | 16 | 7.411e-05 | 2353 | 272.3255 | 1488 | 0.014989 | 0.23983 | 1781 | 0.06 | 1879
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 1462 | FALSE | 16147.0874 | 16116.0676 | 10.0162 | 51 | 0.00019151 | 435 | 137.3214 | 1821 | 0.01495 | 0.76245 | 1782 | 0.07 | 1710
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 58498 | FALSE | 3648.0777 | 1920.6561 | 1.1937 | 34 | 0.00025665 | 200 | 43.134 | 2259 | 0.01494 | 0.50797 | 1783 | 0.03 | 2375
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 65866 | FALSE | 13028.5461 | 5501.1432 | 3.419 | 65 | 4.6622e-05 | 3122 | 158.5163 | 1752 | 0.014918 | 0.9697 | 1784 | 0.04 | 2201
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 549904 | TRUE | 8119.1519 | 250.4434 | 0.15565 | 54 | 6.4657e-05 | 2616 | 224.282 | 1596 | 0.014902 | 0.80473 | 1785 | 1.15 | 708
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 909424 | TRUE | 642.3156 | 642.3156 | 0.3992 | 8 | 0.00010292 | 1571 | 136.9205 | 1825 | 0.014888 | 0.1191 | 1786 |  | 3602
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 749231 | FALSE | 18200.1936 | 8940.1081 | 5.5563 | 141 | 6.0256e-05 | 2765 | 210.5727 | 1619 | 0.014847 | 2.0934 | 1787 |  | 3055
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 51486 | FALSE | 91205.7549 | 91205.7549 | 56.6847 | 656 | 0.00011965 | 1191 | 123.462 | 1860 | 0.014797 | 9.7068 | 1788 | 90.93 | 31
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 65574 | TRUE | 2814.0897 | 939.5268 | 0.58392 | 23 | 0.00030901 | 119 | 33.131 | 2321 | 0.014793 | 0.34024 | 1789 | 0.01 | 2582
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 37344 | TRUE | 14261.5059 | 181.3406 | 0.1127 | 75 | 2.2098e-05 | 3519 | 310.2738 | 1432 | 0.014768 | 1.1076 | 1790 | 0.01 | 2575
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 1612 | FALSE | 14766.2971 | 14766.2971 | 9.1773 | 86 | 0.00012715 | 1062 | 147.1224 | 1785 | 0.014748 | 1.2683 | 1791 | 0.03 | 2352
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 665674 | TRUE | 2469.7606 | 698.7983 | 0.43431 | 20 | 0.00016815 | 574 | 82.7929 | 2037 | 0.014722 | 0.29443 | 1792 |  | 2823
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 70952 | FALSE | 2749.7949 | 2724.6488 | 1.6934 | 29 | 3.988e-05 | 3272 | 320.7855 | 1414 | 0.014692 | 0.42606 | 1793 | 0.06 | 1812
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 47964 | FALSE | 12397.0354 | 10475.6408 | 6.5107 | 68 | 0.00011035 | 1405 | 129.5748 | 1845 | 0.014662 | 0.99704 | 1794 | 0.39 | 958
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 98224 | FALSE | 3847.8762 | 3847.8762 | 2.3915 | 23 | 7.8885e-05 | 2238 | 166.5531 | 1730 | 0.014654 | 0.33704 | 1795 |  | 3151
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 61602 | FALSE | 17974.447 | 15796.3436 | 9.8175 | 137 | 0.00027732 | 164 | 142.021 | 1802 | 0.014648 | 2.0068 | 1796 | 0.06 | 1802
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 2905 | FALSE | 15594.3492 | 15594.3492 | 9.692 | 83 | 0.00011324 | 1339 | 142.3421 | 1801 | 0.014648 | 1.2158 | 1797 | 0.04 | 2182
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 1006 | FALSE | 32324.6992 | 17529.4826 | 10.8946 | 266 | 0.00017105 | 556 | 184.0652 | 1676 | 0.014639 | 3.8939 | 1798 | 0.05 | 1920
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 4045 | TRUE | 3179.9108 | 576.108 | 0.35805 | 18 | 0.00013215 | 979 | 114.5305 | 1897 | 0.014618 | 0.26312 | 1799 | 0.03 | 2324
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 861266 | FALSE | 3852.0148 | 2503.894 | 1.5562 | 31 | 0.00018468 | 477 | 101.2826 | 1949 | 0.014616 | 0.45311 | 1800 |  | 3353
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 2084 | FALSE | 29723.3403 | 29723.3403 | 18.4732 | 219 | 0.00012877 | 1034 | 131.3983 | 1843 | 0.014579 | 3.1928 | 1801 | 0.11 | 1414
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 4904 | FALSE | 29337.0631 | 29337.0631 | 18.2331 | 121 | 0.00023865 | 252 | 61.1434 | 2146 | 0.014552 | 1.7608 | 1802 | 0.44 | 925
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 714370 | FALSE | 4274.3031 | 3423.0115 | 2.1274 | 28 | 8.0252e-05 | 2198 | 368.3867 | 1342 | 0.014533 | 0.40694 | 1803 |  | 3083
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | XR010 | FALSE | 22011.3924 | 4483.0278 | 2.7862 | 160 | 7.8729e-05 | 2242 | 168.0653 | 1726 | 0.014407 | 2.3052 | 1804 | 0.05 | 1996
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 823854 | FALSE | 6899.0553 | 3307.4207 | 2.0556 | 33 | 3.9519e-05 | 3276 | 363.6041 | 1348 | 0.01437 | 0.47422 | 1805 |  | 2786
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 88772 | FALSE | 69339.2928 | 39135.7756 | 24.323 | 474 | 6.1067e-05 | 2746 | 187.0188 | 1668 | 0.014358 | 6.8057 | 1806 | 0.2 | 1160
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 8852 | FALSE | 7650.5094 | 7473.9899 | 4.6451 | 46 | 0.00028421 | 148 | 54.47 | 2184 | 0.014354 | 0.66027 | 1807 | 0.05 | 1930
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 1386 | FALSE | 11052.9537 | 11052.9537 | 6.8695 | 47 | 6.3474e-05 | 2661 | 296.3406 | 1453 | 0.014294 | 0.67181 | 1808 | 0.01 | 2619
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 10170 | FALSE | 26253.3221 | 26253.3221 | 16.3165 | 149 | 4.8216e-05 | 3089 | 256.1773 | 1532 | 0.014293 | 2.1297 | 1809 | 83.16 | 40
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 5661 | FALSE | 8173.4897 | 4658.2663 | 2.8951 | 66 | 8.6364e-05 | 2026 | 169.0465 | 1721 | 0.014289 | 0.94309 | 1810 | 1.66 | 657
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 903030 | FALSE | 2341.4408 | 2341.4408 | 1.4552 | 17 | 0.00011468 | 1304 | 137.2956 | 1823 | 0.014278 | 0.24273 | 1811 |  | 2699
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 2718 | TRUE | 11657.4654 | 495.6422 | 0.30804 | 114 | 0.00022728 | 295 | 102.6178 | 1938 | 0.014276 | 1.6275 | 1812 | 0.04 | 2074
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | V18 | FALSE | 6444.7052 | 4344.0922 | 2.6999 | 41 | 3.6107e-05 | 3335 | 204.0579 | 1633 | 0.014215 | 0.5828 | 1813 | 0.08 | 1634
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 7038 | FALSE | 35749.3707 | 29491.4615 | 18.3291 | 186 | 5.6518e-05 | 2873 | 250.588 | 1538 | 0.014161 | 2.6339 | 1814 | 0.12 | 1392
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 77204 | FALSE | 11918.386 | 11918.386 | 7.4073 | 68 | 0.00011817 | 1226 | 128.4194 | 1848 | 0.014094 | 0.95841 | 1815 |  | 2893
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | CB | FALSE | 7292.0294 | 7292.0294 | 4.532 | 7 | 0.00010421 | 1546 | 1059.6264 | 793 | 0.01407 | 0.098493 | 1816 | 0.03 | 2309
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | CB | FALSE | 7034.6563 | 7034.6563 | 4.3721 | 40 | 0.00012824 | 1044 | 93.9669 | 1986 | 0.014057 | 0.5623 | 1817 | 38.69 | 195
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 60094 | FALSE | 15867.8413 | 15867.8413 | 9.8619 | 95 | 0.00016875 | 569 | 93.9049 | 1987 | 0.014041 | 1.3339 | 1818 | 55.68 | 102
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 67898 | FALSE | 9738.6344 | 6917.4777 | 4.2992 | 70 | 0.00010226 | 1597 | 138.197 | 1816 | 0.014037 | 0.98259 | 1819 | 0.06 | 1819
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 613456 | FALSE | 38029.4611 | 21637.0644 | 13.4475 | 145 | 5.8725e-05 | 2815 | 256.2574 | 1531 | 0.014028 | 2.0341 | 1820 |  | 3187
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 5012 | FALSE | 17904.0624 | 17904.0624 | 11.1274 | 131 | 0.00021567 | 337 | 62.8252 | 2137 | 0.014012 | 1.8356 | 1821 | 0.09 | 1569
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 11244 | FALSE | 34513.2878 | 33294.1457 | 20.6924 | 202 | 0.00014416 | 812 | 70.2755 | 2093 | 0.01399 | 2.826 | 1822 | 0.12 | 1385
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 528 | FALSE | 6520.0631 | 5521.142 | 3.4314 | 50 | 8.1342e-05 | 2172 | 173.339 | 1701 | 0.013987 | 0.69934 | 1823 | 0.08 | 1607
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 337126 | FALSE | 3227.6651 | 1128.521 | 0.70138 | 28 | 3.3027e-05 | 3386 | 257.5116 | 1527 | 0.013964 | 0.39101 | 1824 |  | 3051
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 280 | FALSE | 10907.0769 | 1106.406 | 0.68764 | 52 | 6.7218e-05 | 2553 | 180.7486 | 1682 | 0.013918 | 0.72376 | 1825 | 0.72 | 800
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 302 | FALSE | 16561.5527 | 14104.3324 | 8.7659 | 123 | 0.00011341 | 1335 | 134.8667 | 1832 | 0.013839 | 1.7022 | 1826 | 14.9 | 352
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 534 | FALSE | 27841.2407 | 25519.0889 | 15.8602 | 162 | 9.6936e-05 | 1715 | 161.0686 | 1743 | 0.01369 | 2.2178 | 1827 | 36.61 | 206
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 1320 | FALSE | 32275.3239 | 31878.2376 | 19.8125 | 179 | 0.00033316 | 101 | 41.1443 | 2271 | 0.013687 | 2.4499 | 1828 | 0.21 | 1149
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | CB | FALSE | 34051.8134 | 34051.8134 | 21.1633 | 240 | 0.00019472 | 419 | 88.9032 | 2008 | 0.01359 | 3.2616 | 1829 | 21.63 | 299
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 135762 | FALSE | 4515.3768 | 1189.5286 | 0.7393 | 28 | 9.6391e-05 | 1723 | 173.1219 | 1704 | 0.013539 | 0.3791 | 1830 |  | 3246
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 1322 | FALSE | 30035.9017 | 25851.0688 | 16.0665 | 81 | 4.4702e-05 | 3169 | 378.0361 | 1324 | 0.01351 | 1.0943 | 1831 | 0.03 | 2289
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | CB | FALSE | 5107.0559 | 3866.6599 | 2.4031 | 37 | 0.00013283 | 961 | 86.715 | 2017 | 0.013499 | 0.49946 | 1832 | 0.57 | 862
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 861496 | FALSE | 7188.816 | 7188.816 | 4.4679 | 51 | 8.7717e-05 | 1993 | 163.8005 | 1737 | 0.013491 | 0.68805 | 1833 |  | 3201
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 510 | FALSE | 11861.6385 | 11861.6385 | 7.3721 | 77 | 0.00017549 | 525 | 112.7525 | 1903 | 0.013466 | 1.0369 | 1834 | 48.83 | 124
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 920 | FALSE | 42024.2659 | 28596.0082 | 17.7725 | 258 | 8.9648e-05 | 1925 | 168.9827 | 1722 | 0.013411 | 3.4601 | 1835 | 0.09 | 1572
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 4624 | TRUE | 6101.7647 | 50.6724 | 0.031493 | 42 | 0.00012548 | 1090 | 117.1975 | 1886 | 0.013292 | 0.55825 | 1836 | 0.02 | 2483
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 516 | FALSE | 17602.5759 | 17602.5759 | 10.9401 | 135 | 0.00019441 | 420 | 70.1443 | 2094 | 0.013281 | 1.7929 | 1837 | 1.39 | 679
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 942143 | FALSE | 13604.5625 | 8138.4591 | 5.0581 | 74 | 0.00011237 | 1358 | 105.0805 | 1928 | 0.013216 | 0.97798 | 1838 |  | 3068
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 83354 | FALSE | 8260.8147 | 8260.8147 | 5.1341 | 36 | 5.4313e-05 | 2936 | 210.679 | 1618 | 0.013182 | 0.47457 | 1839 | 0.05 | 1967
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 38868 | FALSE | 6917.0797 | 3119.1276 | 1.9386 | 61 | 0.00010371 | 1555 | 103.4846 | 1934 | 0.01315 | 0.80215 | 1840 | 0.02 | 2534
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | CB | TRUE | 26.5151 | 26.5151 | 0.016479 | 1 | 7.8863e-05 | 2240 | 166.4117 | 1731 | 0.013124 | 0.013124 | 1841 | 0.04 | 2184
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | CB | FALSE | 10780.8577 | 1904.2009 | 1.1835 | 85 | 9.0041e-05 | 1911 | 158.1087 | 1753 | 0.013117 | 1.115 | 1842 | 0.05 | 2028
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | CB | FALSE | 2138.4101 | 1870.8826 | 1.1628 | 21 | 0.00038645 | 70 | 21.5686 | 2432 | 0.013096 | 0.27501 | 1843 | 20.42 | 305
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 296492 | FALSE | 3708.9492 | 1270.5979 | 0.78968 | 29 | 7.4532e-05 | 2344 | 198.5181 | 1644 | 0.013092 | 0.37968 | 1844 |  | 3311
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 858388 | FALSE | 13234.6519 | 7717.2675 | 4.7963 | 72 | 2.6749e-05 | 3476 | 315.5206 | 1423 | 0.013047 | 0.93942 | 1845 |  | 2860
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 3383 | FALSE | 3031.9376 | 2267.9133 | 1.4095 | 24 | 0.00010952 | 1421 | 99.0724 | 1957 | 0.012944 | 0.31066 | 1846 | 0.05 | 2040
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 97982 | FALSE | 15545.7354 | 15545.7354 | 9.6617 | 104 | 8.3073e-05 | 2130 | 187.9326 | 1666 | 0.012892 | 1.3407 | 1847 | 33.04 | 223
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 371694 | TRUE | 6199.8125 | 365.7311 | 0.2273 | 40 | 6.8585e-05 | 2519 | 205.0285 | 1628 | 0.012819 | 0.51277 | 1848 |  | 3089
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 1974 | FALSE | 36068.6353 | 36068.6353 | 22.4168 | 259 | 8.2005e-05 | 2154 | 157.702 | 1756 | 0.012814 | 3.3188 | 1849 | 125.77 | 11
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 3052 | FALSE | 25170.0534 | 20257.093 | 12.5899 | 163 | 9.5443e-05 | 1745 | 138.2678 | 1815 | 0.012795 | 2.0855 | 1850 | 0.66 | 820
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | LB48 | FALSE | 23668.374 | 23668.374 | 14.71 | 142 | 0.0001412 | 849 | 89.798 | 2000 | 0.012757 | 1.8115 | 1851 | 0.79 | 776
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | MR190 | FALSE | 18265.303 | 1336.9264 | 0.83091 | 130 | 5.632e-05 | 2880 | 303.8443 | 1444 | 0.012744 | 1.6567 | 1852 | 0.03 | 2386
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | CB | FALSE | 17493.6949 | 8660.4867 | 5.3825 | 20 | 9.4687e-05 | 1773 | 120.7431 | 1868 | 0.012742 | 0.25483 | 1853 |  | 3269
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 10140 | FALSE | 26724.0842 | 26724.0842 | 16.6091 | 188 | 8.934e-05 | 1937 | 119.5136 | 1871 | 0.012696 | 2.3869 | 1854 | 1.03 | 724
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 10040 | FALSE | 28379.0201 | 28379.0201 | 17.6377 | 213 | 7.3465e-05 | 2385 | 189.319 | 1665 | 0.01266 | 2.6967 | 1855 | 0.64 | 829
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 640 | FALSE | 5054.3067 | 1636.7685 | 1.0173 | 43 | 9.1535e-05 | 1857 | 103.5522 | 1933 | 0.012658 | 0.54429 | 1856 | 0.06 | 1786
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 5739 | FALSE | 10731.8696 | 10731.8696 | 6.6699 | 74 | 0.00014982 | 740 | 107.9805 | 1917 | 0.012582 | 0.93104 | 1857 | 0.05 | 2052
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | A06 | TRUE | 3295.4951 | 441.6127 | 0.27446 | 27 | 6.1339e-05 | 2740 | 154.3644 | 1764 | 0.012566 | 0.33927 | 1858 | 23.54 | 284
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 40666 | TRUE | 2641.929 | 575.1734 | 0.35747 | 18 | 0.00018607 | 467 | 44.5439 | 2250 | 0.012564 | 0.22615 | 1859 | 0.03 | 2374
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 113082 | FALSE | 11746.8209 | 9857.3648 | 6.1264 | 75 | 8.9487e-05 | 1932 | 142.6253 | 1799 | 0.012535 | 0.94012 | 1860 |  | 3001
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 2096 | FALSE | 22772.919 | 22772.919 | 14.1535 | 129 | 9.8802e-05 | 1675 | 133.1159 | 1838 | 0.012531 | 1.6166 | 1861 | 53.86 | 110
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 663244 | TRUE | 704.8457 | 464.3934 | 0.28862 | 6 | 6.412e-05 | 2640 | 270.589 | 1495 | 0.012526 | 0.075153 | 1862 |  | 3250
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 37202 | FALSE | 46485.9706 | 40065.4375 | 24.9008 | 190 | 0.00062222 | 16 | 17.2008 | 2500 | 0.012512 | 2.3773 | 1863 | 0.05 | 1933
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | LB44 | FALSE | 31139.8726 | 31139.8726 | 19.3536 | 213 | 0.00014639 | 783 | 100.8516 | 1950 | 0.012499 | 2.6623 | 1864 | 1.29 | 690
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 1802 | FALSE | 35771.0229 | 35771.0229 | 22.2318 | 259 | 0.00015681 | 674 | 79.811 | 2049 | 0.012496 | 3.2365 | 1865 | 95.5 | 25
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 465074 | FALSE | 7662.1855 | 7662.1855 | 4.7621 | 57 | 0.00013238 | 976 | 95.1304 | 1981 | 0.012495 | 0.7122 | 1866 |  | 2986
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 200856 | FALSE | 4144.4334 | 4144.4334 | 2.5758 | 31 | 0.00022223 | 311 | 73.6449 | 2076 | 0.012452 | 0.38602 | 1867 |  | 3102
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 7632 | FALSE | 13210.2353 | 3566.1023 | 2.2163 | 35 | 2.897e-05 | 3441 | 263.7953 | 1512 | 0.012428 | 0.43499 | 1868 | 0.01 | 2590
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 526864 | FALSE | 5659.7355 | 5008.6837 | 3.1129 | 18 | 5.2603e-05 | 2980 | 261.8161 | 1518 | 0.012408 | 0.22335 | 1869 |  | 2901
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 649874 | TRUE | 608.4651 | 608.4651 | 0.37816 | 5 | 0.00011808 | 1227 | 142.79 | 1797 | 0.012324 | 0.061618 | 1870 |  | 3543
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 5078 | FALSE | 23873.1972 | 23873.1972 | 14.8373 | 154 | 0.00030756 | 121 | 41.9114 | 2267 | 0.012313 | 1.8962 | 1871 | 17.59 | 330
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | CB | FALSE | 37542.2534 | 4224.1485 | 2.6253 | 255 | 0.00013212 | 981 | 102.3882 | 1942 | 0.012302 | 3.1369 | 1872 | 0.03 | 2408
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 3094 | FALSE | 14546.7613 | 6578.8406 | 4.0888 | 63 | 6.4104e-05 | 2641 | 239.8109 | 1568 | 0.012298 | 0.77477 | 1873 | 0.06 | 1850
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | CB | FALSE | 26652.3351 | 26652.3351 | 16.5645 | 128 | 0.00011861 | 1214 | 102.4016 | 1941 | 0.012215 | 1.5636 | 1874 | 82.53 | 43
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 976553 | FALSE | 3112.5676 | 1744.6035 | 1.0843 | 20 | 6.6999e-05 | 2557 | 174.5173 | 1699 | 0.012197 | 0.24394 | 1875 |  | 3407
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | CB | FALSE | 14175.8367 | 14066.7084 | 8.7425 | 88 | 0.00026507 | 182 | 43.8173 | 2253 | 0.012162 | 1.0703 | 1876 | 27.97 | 254
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 317782 | TRUE | 6689.8142 | 874.1929 | 0.54331 | 53 | 0.00012534 | 1092 | 127.094 | 1852 | 0.012141 | 0.64349 | 1877 |  | 2852
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6014 | FALSE | 19985.2036 | 9962.9663 | 6.192 | 106 | 7.6568e-05 | 2291 | 149.4232 | 1779 | 0.012138 | 1.2867 | 1878 | 0.02 | 2473
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 676164 | TRUE | 4417.8948 | 487.5008 | 0.30298 | 26 | 4.5549e-05 | 3152 | 245.9244 | 1551 | 0.012062 | 0.3136 | 1879 |  | 3115
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | CB | FALSE | 10098.7974 | 10098.7974 | 6.2764 | 73 | 0.000256 | 203 | 35.5525 | 2306 | 0.01204 | 0.87889 | 1880 | 11.22 | 385
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 411508 | TRUE | 731.3696 | 726.7977 | 0.45171 | 6 | 0.00014592 | 790 | 114.8976 | 1896 | 0.012026 | 0.072157 | 1881 |  | 3464
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 466 | TRUE | 2421.8686 | 622.9644 | 0.38717 | 21 | 0.00011297 | 1345 | 121.2049 | 1867 | 0.01202 | 0.25243 | 1882 |  | 2947
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 329930 | FALSE | 19740.5748 | 10526.1812 | 6.5421 | 137 | 0.00012563 | 1085 | 89.3966 | 2004 | 0.012012 | 1.6456 | 1883 | 0.03 | 2300
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 539450 | FALSE | 3896.0108 | 2403.5482 | 1.4938 | 28 | 9.1165e-05 | 1874 | 148.5497 | 1781 | 0.011978 | 0.33537 | 1884 |  | 2917
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 2768 | FALSE | 13051.8561 | 12269.0577 | 7.6253 | 88 | 0.00012814 | 1045 | 88.7266 | 2009 | 0.011963 | 1.0528 | 1885 | 7.41 | 445
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 587857 | TRUE | 3120.9828 | 171.8621 | 0.10681 | 28 | 8.567e-05 | 2038 | 73.8505 | 2073 | 0.011944 | 0.33442 | 1886 |  | 3211
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 11800 | FALSE | 15325.4468 | 15325.4468 | 9.5248 | 116 | 9.1188e-05 | 1873 | 242.093 | 1561 | 0.011866 | 1.3764 | 1887 | 49.43 | 123
2749 | ELK 1101900 | 42981101 | ELK 1101 | 900 | FALSE | 34419.9463 | 14125.5477 | 8.7791 | 185 | 5.5462e-05 | 2901 | 228.3452 | 1591 | 0.011859 | 2.1939 | 1888 | 0.01 | 2598
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 2646 | FALSE | 28413.9838 | 28413.9838 | 17.6594 | 149 | 0.00010253 | 1586 | 176.2359 | 1694 | 0.01184 | 1.7642 | 1889 |  | 2720
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 386844 | TRUE | 2561.2262 | 615.6019 | 0.3826 | 19 | 4.5617e-05 | 3150 | 232.4795 | 1583 | 0.01183 | 0.22478 | 1890 |  | 3226
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | XR264 | TRUE | 33068.0694 | 0 | 0 | 258 | 7.958e-05 | 2219 | 168.5722 | 1723 | 0.011726 | 3.0254 | 1891 | 0.77 | 783
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 968652 | FALSE | 3017.7923 | 1606.1834 | 0.99825 | 25 | 0.00010466 | 1539 | 114.1474 | 1898 | 0.011684 | 0.2921 | 1892 |  | 2946
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 63598 | FALSE | 3076.8023 | 3076.8023 | 1.9122 | 24 | 0.0001935 | 427 | 74.3537 | 2071 | 0.011681 | 0.28035 | 1893 | 50.16 | 120
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 870444 | FALSE | 4770.1261 | 4746.504 | 2.95 | 35 | 0.00012787 | 1050 | 122.3071 | 1864 | 0.011666 | 0.40831 | 1894 |  | 3038
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 716 | FALSE | 14319.9438 | 14319.9438 | 8.8999 | 109 | 0.00010523 | 1513 | 113.9799 | 1900 | 0.01165 | 1.2698 | 1895 | 14.14 | 357
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 350336 | FALSE | 2699.1632 | 1936.9418 | 1.2038 | 13 | 7.7558e-05 | 2276 | 139.0255 | 1813 | 0.011629 | 0.15117 | 1896 |  | 3323
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 809986 | FALSE | 3460.671 | 1661.0044 | 1.0323 | 18 | 4.7551e-05 | 3100 | 119.23 | 1872 | 0.011626 | 0.20927 | 1897 |  | 3484
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 98374 | FALSE | 6103.4021 | 1330.8093 | 0.8271 | 46 | 0.00011986 | 1189 | 56.1694 | 2175 | 0.011616 | 0.53436 | 1898 | 0.02 | 2442
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 91424 | TRUE | 14089.3649 | 303.1658 | 0.18842 | 95 | 6.4005e-05 | 2646 | 160.2049 | 1745 | 0.01155 | 1.0973 | 1899 | 0.02 | 2546
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 262 | FALSE | 9547.2777 | 2067.1657 | 1.2848 | 61 | 0.00010047 | 1637 | 112.2285 | 1905 | 0.011548 | 0.70445 | 1900 | 0.05 | 1983
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 247660 | FALSE | 5200.0544 | 3858.4886 | 2.3981 | 35 | 8.3565e-05 | 2111 | 144.077 | 1794 | 0.011541 | 0.40392 | 1901 |  | 2689
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 2210 | FALSE | 36938.5346 | 36938.5346 | 22.9574 | 280 | 9.2627e-05 | 1829 | 84.7902 | 2032 | 0.01151 | 3.2229 | 1902 | 105.34 | 19
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 5480 | FALSE | 27352.0687 | 27352.0687 | 16.9994 | 180 | 7.0805e-05 | 2447 | 169.2363 | 1720 | 0.011505 | 2.0709 | 1903 | 0.6 | 854
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 1360 | FALSE | 36445.2787 | 36106.6297 | 22.4404 | 92 | 4.8938e-05 | 3066 | 304.0594 | 1443 | 0.011504 | 1.0584 | 1904 | 0.01 | 2568
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | XR044 | TRUE | 3013.9349 | 677.8018 | 0.42126 | 18 | 0.00010855 | 1434 | 79.5829 | 2050 | 0.011436 | 0.20585 | 1905 | 0.02 | 2555
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 1419 | FALSE | 24160.9517 | 24160.9517 | 15.0161 | 130 | 6.2459e-05 | 2706 | 145.1035 | 1792 | 0.011428 | 1.4856 | 1906 | 0.17 | 1249
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 324510 | FALSE | 20073.6016 | 20073.6016 | 12.4758 | 154 | 6.2523e-05 | 2702 | 194.5257 | 1656 | 0.011404 | 1.7562 | 1907 | 0.14 | 1320
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 10050 | FALSE | 11290.6239 | 11290.6239 | 7.0172 | 81 | 9.8289e-05 | 1684 | 101.871 | 1946 | 0.01137 | 0.92095 | 1908 | 0.52 | 888
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 93116 | FALSE | 68103.7314 | 68103.7314 | 42.3267 | 453 | 9.1189e-05 | 1872 | 118.4962 | 1875 | 0.011348 | 5.1406 | 1909 | 26.17 | 268
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | CB | FALSE | 27455.7877 | 6641.9361 | 4.128 | 121 | 2.9423e-05 | 3434 | 158.5842 | 1751 | 0.011318 | 1.3695 | 1910 | 0.05 | 2010
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 51788 | FALSE | 20901.6945 | 8188.5748 | 5.0892 | 153 | 0.00012561 | 1087 | 89.1639 | 2005 | 0.011264 | 1.7234 | 1911 | 0.7 | 807
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 9032 | FALSE | 37853.3581 | 36827.5633 | 22.8885 | 175 | 3.6108e-05 | 3334 | 413.8546 | 1280 | 0.011207 | 1.9611 | 1912 | 0.02 | 2552
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 4622 | FALSE | 21650.6648 | 21650.6648 | 13.456 | 109 | 0.00028635 | 145 | 73.5891 | 2077 | 0.011136 | 1.2138 | 1913 | 0.1 | 1454
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | MR243 | FALSE | 8929.805 | 8929.805 | 5.5499 | 72 | 8.9046e-05 | 1946 | 128.0484 | 1849 | 0.011084 | 0.79807 | 1914 |  | 2988
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 429574 | FALSE | 15346.7415 | 8004.0474 | 4.9745 | 114 | 0.00019074 | 439 | 99.3413 | 1955 | 0.011083 | 1.2634 | 1915 |  | 2857
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | CB | FALSE | 13124.836 | 11515.5312 | 7.1569 | 82 | 7.3716e-05 | 2370 | 185.6036 | 1669 | 0.011075 | 0.90815 | 1916 | 0.07 | 1709
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 8896 | FALSE | 2488.0112 | 1537.9857 | 0.95586 | 14 | 0.00022997 | 285 | 52.1302 | 2200 | 0.011065 | 0.15491 | 1917 | 2.98 | 570
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 42896 | FALSE | 8829.785 | 3686.5968 | 2.2912 | 71 | 0.00019577 | 414 | 80.3834 | 2046 | 0.011029 | 0.78303 | 1918 | 0.04 | 2101
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 304826 | FALSE | 14243.5781 | 8398.3076 | 5.2196 | 61 | 1.8551e-05 | 3558 | 384.6024 | 1312 | 0.010995 | 0.6707 | 1919 |  | 2949
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | CB | FALSE | 17461.9206 | 17461.9206 | 10.8527 | 136 | 0.00014936 | 745 | 159.9625 | 1746 | 0.010952 | 1.4895 | 1920 | 17.74 | 329
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 2560 | FALSE | 26913.6157 | 26913.6157 | 16.7269 | 179 | 8.9581e-05 | 1928 | 135.7772 | 1829 | 0.010913 | 1.9534 | 1921 | 75.77 | 57
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 613562 | FALSE | 9602.6341 | 5945.3079 | 3.695 | 29 | 4.482e-05 | 3166 | 198.1499 | 1645 | 0.010904 | 0.31622 | 1922 |  | 3204
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 189602 | FALSE | 1011.2208 | 1011.2208 | 0.62848 | 9 | 0.00010514 | 1518 | 134.7619 | 1833 | 0.010902 | 0.098117 | 1923 |  | 3183
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 33542 | FALSE | 4316.4835 | 4316.4835 | 2.6827 | 39 | 0.00031343 | 114 | 29.934 | 2346 | 0.010901 | 0.42515 | 1924 | 20.17 | 307
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 37848 | FALSE | 9580.5994 | 9580.5994 | 5.9544 | 60 | 7.1725e-05 | 2430 | 176.9482 | 1691 | 0.010901 | 0.65406 | 1925 | 39.39 | 189
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3891 | FALSE | 5583.0951 | 5583.0951 | 3.4699 | 23 | 0.0002266 | 300 | 68.3151 | 2101 | 0.010887 | 0.2504 | 1926 | 21.8 | 297
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 341542 | FALSE | 10584.332 | 9768.7602 | 6.0713 | 47 | 8.7167e-05 | 2009 | 161.0484 | 1744 | 0.010885 | 0.5116 | 1927 |  | 3412
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 7514 | FALSE | 16121.906 | 14595.7178 | 9.0713 | 118 | 0.00025507 | 206 | 51.2832 | 2206 | 0.010882 | 1.2841 | 1928 | 4.42 | 519
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 999 | FALSE | 1412.3755 | 1412.3755 | 0.8778 | 7 | 0.00015392 | 709 | 122.3126 | 1863 | 0.010787 | 0.075506 | 1929 | 28.44 | 250
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 492068 | FALSE | 13334.8935 | 11954.6281 | 7.4298 | 75 | 6.9325e-05 | 2495 | 169.7517 | 1718 | 0.010772 | 0.80789 | 1930 |  | 2812
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 84572 | TRUE | 3629.8323 | 844.7995 | 0.52505 | 27 | 6.1461e-05 | 2735 | 146.1205 | 1788 | 0.010769 | 0.29075 | 1931 | 0.05 | 2022
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 893 | TRUE | 16957.7992 | 312.2303 | 0.19405 | 91 | 8.78e-05 | 1990 | 114.1416 | 1899 | 0.010724 | 0.9759 | 1932 | 0.02 | 2482
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 1650 | FALSE | 34931.9743 | 34931.9743 | 21.7104 | 154 | 4.7419e-05 | 3105 | 252.2302 | 1537 | 0.010701 | 1.6479 | 1933 | 0.12 | 1379
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 97086 | FALSE | 41345.0987 | 41345.0987 | 25.6961 | 301 | 7.7565e-05 | 2275 | 132.4839 | 1840 | 0.010689 | 3.2174 | 1934 | 48.08 | 132
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 591122 | TRUE | 748.6821 | 748.6821 | 0.46531 | 7 | 0.00022033 | 319 | 51.0001 | 2207 | 0.010649 | 0.074542 | 1935 |  | 3085
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 91216 | FALSE | 65291.6361 | 65291.6361 | 40.579 | 380 | 8.9695e-05 | 1922 | 143.7419 | 1795 | 0.010587 | 4.0231 | 1936 | 0.25 | 1085
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 246 | FALSE | 21497.7557 | 21497.7557 | 13.3609 | 148 | 0.00011216 | 1363 | 98.1055 | 1967 | 0.010561 | 1.563 | 1937 | 6.5 | 466
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 3088 | FALSE | 24808.0862 | 24808.0862 | 15.4183 | 175 | 7.2041e-05 | 2415 | 135.1128 | 1831 | 0.010503 | 1.8381 | 1938 | 0.12 | 1369
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | CB | FALSE | 37414.4172 | 25753.259 | 16.0058 | 153 | 5.557e-05 | 2899 | 155.1527 | 1763 | 0.010468 | 1.6015 | 1939 | 0.06 | 1833
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 97816 | FALSE | 8457.2763 | 8457.2763 | 5.2562 | 50 | 4.697e-05 | 3114 | 169.4239 | 1719 | 0.010402 | 0.52009 | 1940 | 0.19 | 1193
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 47968 | FALSE | 65100.4862 | 65100.4862 | 40.4602 | 306 | 5.7195e-05 | 2856 | 229.0575 | 1588 | 0.010385 | 3.1777 | 1941 | 0.12 | 1380
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 60024 | FALSE | 6398.0407 | 6398.0407 | 3.9764 | 27 | 8.433e-05 | 2081 | 118.0471 | 1880 | 0.010381 | 0.28029 | 1942 | 22.82 | 292
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 94936 | FALSE | 14750.2856 | 14750.2856 | 9.1674 | 82 | 0.00010473 | 1535 | 117.7375 | 1883 | 0.010365 | 0.84992 | 1943 | 0.07 | 1716
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 808 | FALSE | 9941.3745 | 9941.3745 | 6.1786 | 23 | 8.8814e-05 | 1958 | 107.5525 | 1920 | 0.010361 | 0.23829 | 1944 | 0.23 | 1116
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 706399 | TRUE | 1848.7276 | 537.9717 | 0.33435 | 16 | 4.8672e-05 | 3069 | 204.8708 | 1630 | 0.010338 | 0.1654 | 1945 |  | 3173
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 19752 | FALSE | 58764.7318 | 58764.7318 | 36.5225 | 436 | 0.00017226 | 548 | 104.6256 | 1929 | 0.0103 | 4.4909 | 1946 | 119.92 | 12
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 131568 | FALSE | 7881.7386 | 6658.8017 | 4.1385 | 57 | 0.00013576 | 921 | 77.208 | 2060 | 0.010281 | 0.58604 | 1947 |  | 2951
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 38632 | FALSE | 7538.4158 | 7535.3678 | 4.6833 | 58 | 0.00018341 | 485 | 125.725 | 1857 | 0.010245 | 0.59423 | 1948 | 0.22 | 1128
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 337220 | FALSE | 8725.086 | 7959.8917 | 4.9471 | 28 | 0.00012555 | 1088 | 76.0082 | 2062 | 0.010237 | 0.28665 | 1949 |  | 3451
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | CB | FALSE | 37377.2089 | 37377.2089 | 23.2301 | 171 | 0.00013678 | 910 | 60.8273 | 2149 | 0.010207 | 1.7454 | 1950 | 66.07 | 74
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 70198 | FALSE | 5102.4847 | 3628.2739 | 2.255 | 36 | 9.8288e-05 | 1685 | 164.1355 | 1736 | 0.010197 | 0.36709 | 1951 | 0.07 | 1763
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 400 | FALSE | 1650.11 | 1410.4889 | 0.87662 | 14 | 7.9738e-05 | 2214 | 97.4469 | 1971 | 0.010195 | 0.14273 | 1952 | 0.05 | 2066
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 37426 | FALSE | 8142.4343 | 1270.4089 | 0.78956 | 65 | 4.6458e-05 | 3126 | 164.8689 | 1735 | 0.010169 | 0.66101 | 1953 | 0.25 | 1079
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 4004 | FALSE | 32627.9425 | 14083.7966 | 8.7531 | 180 | 5.3736e-05 | 2948 | 159.4123 | 1748 | 0.010124 | 1.8224 | 1954 | 0.05 | 1947
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 1280 | FALSE | 13974.6466 | 13812.836 | 8.5847 | 111 | 0.00015949 | 648 | 83.4065 | 2034 | 0.010109 | 1.1221 | 1955 | 0.14 | 1310
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | L3355 | FALSE | 3618.1853 | 3618.1853 | 2.2487 | 27 | 8.1776e-05 | 2161 | 67.8566 | 2102 | 0.010104 | 0.2728 | 1956 | 44.71 | 155
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 95016 | FALSE | 7771.8455 | 1223.0109 | 0.76011 | 69 | 5.7126e-05 | 2857 | 109.0983 | 1914 | 0.010066 | 0.69458 | 1957 | 0.02 | 2499
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 2474 | FALSE | 13467.3498 | 13410.8685 | 8.3349 | 83 | 3.6201e-05 | 3329 | 276.607 | 1482 | 0.010035 | 0.83287 | 1958 | 10.79 | 394
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 414 | FALSE | 35132.3675 | 2113.8048 | 1.3137 | 260 | 5.6e-05 | 2889 | 105.7924 | 1925 | 0.009991 | 2.5977 | 1959 | 1.9 | 632
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | CB | FALSE | 4118.8768 | 4062.5857 | 2.5249 | 34 | 0.00043164 | 58 | 21.0417 | 2435 | 0.0099584 | 0.33859 | 1960 | 0.39 | 952
10564 | WISE 110163199 | 152271101 | WISE 1101 | 63199 | TRUE | 1501.4082 | 989.41 | 0.61492 | 8 | 0.00018345 | 483 | 115.9454 | 1891 | 0.0099235 | 0.079388 | 1961 | 0.04 | 2215
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | XR292 | FALSE | 19536.8147 | 17975.9221 | 11.1721 | 130 | 6.4726e-05 | 2615 | 181.5173 | 1680 | 0.0098996 | 1.287 | 1962 | 0.15 | 1292
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | CB | FALSE | 13834.375 | 12733.914 | 7.9142 | 113 | 0.00013093 | 994 | 85.2135 | 2029 | 0.0098816 | 1.1166 | 1963 | 0.08 | 1671
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | W26 | FALSE | 4390.419 | 4390.419 | 2.7287 | 18 | 6.7545e-05 | 2549 | 162.1198 | 1741 | 0.0098794 | 0.17783 | 1964 | 0.05 | 1956
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 1131 | FALSE | 4424.1224 | 4424.1224 | 2.7496 | 33 | 8.1427e-05 | 2171 | 131.8339 | 1842 | 0.0098607 | 0.3254 | 1965 | 3.76 | 535
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 568 | FALSE | 20285.8832 | 20285.8832 | 12.6078 | 129 | 0.00011941 | 1198 | 98.3927 | 1966 | 0.0098399 | 1.2694 | 1966 | 40.01 | 186
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 4008 | FALSE | 56919.5652 | 56919.5652 | 35.3757 | 138 | 4.9605e-05 | 3045 | 221.1468 | 1603 | 0.0097859 | 1.3505 | 1967 | 0.04 | 2151
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 5002 | FALSE | 22234.4783 | 21939.7249 | 13.6356 | 161 | 0.00029646 | 133 | 37.2556 | 2295 | 0.0097721 | 1.5733 | 1968 | 18.45 | 322
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 52456 | FALSE | 16414.576 | 16414.576 | 10.2017 | 96 | 0.00013704 | 907 | 96.4288 | 1977 | 0.0097493 | 0.93593 | 1969 | 0.06 | 1899
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 965598 | FALSE | 25622.1563 | 14815.8266 | 9.2081 | 139 | 4.3766e-05 | 3194 | 205.6396 | 1624 | 0.0097442 | 1.3544 | 1970 |  | 2894
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 203504 | TRUE | 514.0425 | 226.4943 | 0.14077 | 4 | 0.00021969 | 325 | 71.3633 | 2088 | 0.0097327 | 0.038931 | 1971 |  | 3389
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 742 | FALSE | 2084.4879 | 2084.4879 | 1.2955 | 21 | 0.00010714 | 1469 | 98.5688 | 1964 | 0.009698 | 0.20366 | 1972 | 0.02 | 2502
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 2208 | FALSE | 20533.4109 | 18971.647 | 11.791 | 159 | 0.0001453 | 800 | 55.2252 | 2180 | 0.0096885 | 1.5405 | 1973 | 0.15 | 1278
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 13532 | FALSE | 8576.7798 | 8576.7798 | 5.3305 | 46 | 9.988e-05 | 1652 | 99.3016 | 1956 | 0.0096754 | 0.44507 | 1974 | 0 | 2625
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 5120 | FALSE | 9912.3897 | 9912.3897 | 6.1606 | 19 | 7.7594e-05 | 2273 | 140.142 | 1809 | 0.0096488 | 0.18333 | 1975 | 15.79 | 345
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 539980 | TRUE | 697.2903 | 474.6546 | 0.295 | 4 | 0.0001397 | 874 | 59.5974 | 2157 | 0.0096291 | 0.038517 | 1976 |  | 2837
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 617828 | FALSE | 4970.4215 | 2303.2847 | 1.4315 | 28 | 9.4549e-05 | 1777 | 105.7723 | 1926 | 0.0096279 | 0.26958 | 1977 |  | 2776
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 380686 | FALSE | 4931.6119 | 3014.5331 | 1.8735 | 34 | 0.00017304 | 543 | 55.7388 | 2176 | 0.0095954 | 0.32624 | 1978 |  | 2938
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 1243 | FALSE | 8319.7013 | 8319.7013 | 5.1707 | 50 | 9.2023e-05 | 1845 | 108.0493 | 1916 | 0.0095359 | 0.47679 | 1979 |  | 2768
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 467560 | FALSE | 3279.179 | 3279.179 | 2.038 | 27 | 0.00027911 | 159 | 44.0774 | 2252 | 0.009532 | 0.25736 | 1980 |  | 2891
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 728460 | FALSE | 2312.7118 | 1173.0161 | 0.72903 | 17 | 9.9769e-05 | 1653 | 103.6058 | 1932 | 0.0095302 | 0.16201 | 1981 |  | 3014
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 19622 | FALSE | 18790.8494 | 9040.145 | 5.6185 | 165 | 0.00016432 | 596 | 119.9283 | 1869 | 0.0095283 | 1.5722 | 1982 | 0.05 | 1921
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 1250 | FALSE | 5741.9405 | 5741.9405 | 3.5686 | 26 | 0.00015475 | 698 | 75.9474 | 2063 | 0.0094996 | 0.24699 | 1983 | 71.72 | 66
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 5024 | TRUE | 526.6111 | 526.6111 | 0.32729 | 4 | 0.00017161 | 552 | 35.72 | 2305 | 0.0094858 | 0.037943 | 1984 | 11.71 | 383
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | CB | TRUE | 14676.6694 | 318.0802 | 0.19769 | 91 | 4.4438e-05 | 3177 | 137.3401 | 1820 | 0.0094639 | 0.86121 | 1985 |  | 2802
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 220608 | FALSE | 3563.3452 | 1678.7883 | 1.0434 | 10 | 2.1846e-05 | 3522 | 416.4617 | 1275 | 0.009449 | 0.09449 | 1986 |  | 2941
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 50010 | FALSE | 15036.1048 | 9841.1126 | 6.1163 | 117 | 0.00024302 | 239 | 56.6031 | 2173 | 0.0094406 | 1.1046 | 1987 | 18.42 | 323
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 34008 | FALSE | 36886.2403 | 36886.2403 | 22.9249 | 259 | 0.00010265 | 1580 | 90.3162 | 1998 | 0.0094239 | 2.4408 | 1988 | 82.16 | 46
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 3030 | FALSE | 41820.8596 | 16131.8418 | 10.026 | 186 | 2.9058e-05 | 3440 | 203.8088 | 1634 | 0.0094083 | 1.7499 | 1989 | 0.06 | 1801
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 58095 | TRUE | 251.9158 | 251.9158 | 0.15657 | 2 | 0.00013161 | 987 | 71.4359 | 2085 | 0.0094017 | 0.018803 | 1990 | 1.66 | 656
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 2600 | FALSE | 32204.7216 | 32204.7216 | 20.0154 | 114 | 9.7968e-05 | 1692 | 92.2082 | 1992 | 0.0093006 | 1.0603 | 1991 | 6.68 | 463
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 642 | FALSE | 14995.9698 | 14995.9698 | 9.3201 | 127 | 0.00012083 | 1167 | 94.1376 | 1984 | 0.0092364 | 1.173 | 1992 | 16.12 | 341
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 474 | FALSE | 14496.4925 | 14496.4925 | 9.0096 | 77 | 9.2233e-05 | 1837 | 111.515 | 1906 | 0.0092125 | 0.70936 | 1993 | 0.09 | 1510
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 695270 | FALSE | 1764.2137 | 1116.1992 | 0.69372 | 12 | 6.659e-05 | 2569 | 184.7862 | 1675 | 0.009199 | 0.11039 | 1994 |  | 3425
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | MR525 | TRUE | 98.2491 | 17.8831 | 0.011114 | 2 | 6.2244e-05 | 2712 | 142.6154 | 1800 | 0.0091967 | 0.018393 | 1995 |  | 3348
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1324 | FALSE | 38651.4549 | 1638.5898 | 1.0184 | 169 | 2.205e-05 | 3520 | 325.2371 | 1405 | 0.0091756 | 1.5507 | 1996 | 0.02 | 2488
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 610800 | FALSE | 4080.4254 | 3862.9953 | 2.4009 | 33 | 8.5461e-05 | 2042 | 102.3732 | 1943 | 0.0091096 | 0.30062 | 1997 |  | 3147
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 910230 | FALSE | 3166.5297 | 1560.5069 | 0.96986 | 27 | 0.00023935 | 248 | 37.0091 | 2298 | 0.0090947 | 0.24556 | 1998 |  | 3058
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 532 | FALSE | 15658.0016 | 15658.0016 | 9.7315 | 124 | 0.00024726 | 225 | 48.9408 | 2215 | 0.0090595 | 1.1234 | 1999 | 47.27 | 135
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 542272 | FALSE | 12585.3616 | 12585.3616 | 7.8219 | 80 | 0.00018486 | 474 | 31.5637 | 2334 | 0.0090446 | 0.72357 | 2000 |  | 2940
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 253331 | TRUE | 639.8394 | 107.6584 | 0.06691 | 5 | 0.0001555 | 688 | 63.3453 | 2134 | 0.0090171 | 0.045085 | 2001 |  | 3284
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 6577 | FALSE | 5581.4139 | 5581.4139 | 3.4689 | 33 | 0.00018059 | 509 | 33.2037 | 2318 | 0.0089943 | 0.29681 | 2002 |  | 3482
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 90242 | FALSE | 7016.5204 | 6652.6427 | 4.1346 | 51 | 0.00013965 | 876 | 54.8847 | 2183 | 0.0089934 | 0.45866 | 2003 | 0.05 | 1980
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 802 | FALSE | 20585.105 | 13782.7792 | 8.5661 | 162 | 0.00013761 | 901 | 59.5964 | 2158 | 0.0089568 | 1.451 | 2004 | 0.09 | 1542
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 481660 | FALSE | 1777.5904 | 1750.3957 | 1.0879 | 21 | 0.00013748 | 904 | 66.8278 | 2109 | 0.0089565 | 0.18809 | 2005 |  | 3360
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 625902 | FALSE | 9066.5477 | 4214.4266 | 2.6193 | 26 | 5.2521e-05 | 2981 | 97.9588 | 1969 | 0.0089147 | 0.23178 | 2006 |  | 2735
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 4002 | FALSE | 30655.7932 | 29553.7891 | 18.3678 | 140 | 4.2612e-05 | 3215 | 236.2342 | 1577 | 0.0088999 | 1.246 | 2007 | 0.18 | 1202
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | A88 | FALSE | 4298.2003 | 1506.8203 | 0.93649 | 41 | 7.0724e-05 | 2450 | 118.2966 | 1877 | 0.008869 | 0.36363 | 2008 | 0.51 | 891
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 1602 | FALSE | 26067.9128 | 26067.9128 | 16.2013 | 121 | 7.2028e-05 | 2416 | 103.4039 | 1935 | 0.0088619 | 1.0723 | 2009 | 0.28 | 1033
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | VR816 | FALSE | 6675.8935 | 6675.8935 | 4.1491 | 49 | 0.00021002 | 359 | 34.0265 | 2312 | 0.0088541 | 0.43385 | 2010 | 78.58 | 51
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 35576 | FALSE | 12676.983 | 12676.983 | 7.8788 | 77 | 9.958e-05 | 1656 | 90.2081 | 1999 | 0.0088445 | 0.68102 | 2011 | 51.58 | 114
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 357407 | TRUE | 396.3684 | 382.6506 | 0.23782 | 5 | 5.6115e-05 | 2883 | 139.4252 | 1811 | 0.0088377 | 0.044188 | 2012 |  | 3206
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 75274 | TRUE | 5361.6389 | 623.7122 | 0.38764 | 43 | 7.4779e-05 | 2337 | 100.4794 | 1953 | 0.0088331 | 0.37982 | 2013 | 2.09 | 623
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 64758 | FALSE | 16840.1197 | 16840.1197 | 10.4662 | 97 | 0.00025463 | 207 | 41.2688 | 2270 | 0.0087918 | 0.8528 | 2014 | 58.76 | 91
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 534548 | TRUE | 825.2513 | 643.683 | 0.40005 | 7 | 8.8763e-05 | 1960 | 139.419 | 1812 | 0.008746 | 0.061222 | 2015 |  | 3194
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 504 | FALSE | 10763.1252 | 10763.1252 | 6.6893 | 53 | 0.00011675 | 1255 | 93.9031 | 1988 | 0.0087025 | 0.46123 | 2016 | 0.26 | 1063
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 530 | TRUE | 7365.5043 | 114.9911 | 0.071467 | 55 | 7.7592e-05 | 2274 | 96.695 | 1976 | 0.0087005 | 0.47853 | 2017 | 0.03 | 2248
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 37520 | FALSE | 3437.9631 | 3437.9631 | 2.1367 | 20 | 0.0002436 | 236 | 45.2659 | 2244 | 0.0086846 | 0.17369 | 2018 | 30.52 | 237
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 180 | FALSE | 3158.1165 | 3158.1165 | 1.9628 | 28 | 0.00023287 | 273 | 37.4189 | 2293 | 0.0086779 | 0.24298 | 2019 | 48.66 | 126
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 1302 | FALSE | 28390.9957 | 12188.0095 | 7.5749 | 189 | 9.155e-05 | 1856 | 135.9642 | 1826 | 0.0086777 | 1.6401 | 2020 | 0.07 | 1751
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 1303 | FALSE | 25207.4138 | 25207.4138 | 15.6665 | 146 | 8.2868e-05 | 2134 | 109.1634 | 1912 | 0.0086648 | 1.2651 | 2021 | 55.45 | 103
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 2232 | FALSE | 16843.7265 | 16843.7265 | 10.4684 | 88 | 0.00014558 | 796 | 81.1031 | 2043 | 0.0086414 | 0.76044 | 2022 | 16.24 | 339
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 725939 | TRUE | 1338.4571 | 150.5355 | 0.093558 | 14 | 0.0001664 | 579 | 36.2434 | 2303 | 0.0086108 | 0.12055 | 2023 |  | 3249
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 6601 | FALSE | 3063.6094 | 3063.6094 | 1.904 | 19 | 0.00011592 | 1271 | 66.3782 | 2113 | 0.0085862 | 0.16314 | 2024 |  | 3470
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 348368 | FALSE | 14957.0247 | 4473.6471 | 2.7804 | 107 | 6.0549e-05 | 2762 | 137.0477 | 1824 | 0.0085797 | 0.91803 | 2025 |  | 2865
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 4859 | FALSE | 3008.5895 | 3008.5895 | 1.8699 | 22 | 0.00015733 | 670 | 65.9715 | 2116 | 0.0085572 | 0.18826 | 2026 | 30.63 | 236
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | CB | FALSE | 7381.7293 | 5917.6189 | 3.6778 | 32 | 7.2016e-05 | 2418 | 150.0597 | 1776 | 0.0085315 | 0.27301 | 2027 | 0.06 | 1914
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 6852 | FALSE | 40624.2727 | 40624.2727 | 25.2481 | 309 | 0.00015417 | 703 | 140.8238 | 1808 | 0.0085289 | 2.6354 | 2028 | 106.87 | 16
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | CB | FALSE | 5578.7405 | 1480.1268 | 0.9199 | 28 | 6.1871e-05 | 2724 | 91.0203 | 1996 | 0.0085282 | 0.23879 | 2029 | 0.25 | 1074
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 4923 | FALSE | 4611.3164 | 4611.3164 | 2.866 | 12 | 0.00010517 | 1516 | 65.4057 | 2122 | 0.008518 | 0.10222 | 2030 | 0.06 | 1877
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 63502 | FALSE | 16836.9835 | 16836.9835 | 10.4643 | 107 | 0.00012514 | 1095 | 60.239 | 2153 | 0.0084952 | 0.90898 | 2031 | 0.16 | 1256
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 2068 | FALSE | 17517.3264 | 17517.3264 | 10.8871 | 90 | 0.00011364 | 1328 | 80.7377 | 2044 | 0.0084897 | 0.76407 | 2032 | 0.32 | 992
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | CB | FALSE | 24321.9127 | 2030.3761 | 1.2619 | 199 | 0.00016447 | 591 | 61.5586 | 2143 | 0.0084763 | 1.6868 | 2033 | 0.03 | 2311
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 8233 | FALSE | 7978.7453 | 7978.7453 | 4.9588 | 51 | 7.9873e-05 | 2208 | 109.5763 | 1910 | 0.008467 | 0.43182 | 2034 | 41.72 | 175
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | CB | FALSE | 27644.3487 | 27644.3487 | 17.1811 | 231 | 0.00016053 | 637 | 70.3363 | 2092 | 0.0084422 | 1.9501 | 2035 | 0.21 | 1148
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | CB | FALSE | 15842.0085 | 9046.8091 | 5.6226 | 127 | 0.0002078 | 373 | 65.6703 | 2119 | 0.008393 | 1.0659 | 2036 | 0.19 | 1172
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 19612 | FALSE | 14689.1647 | 14689.1647 | 9.1294 | 102 | 0.00021799 | 328 | 33.636 | 2313 | 0.0083743 | 0.85418 | 2037 | 36 | 208
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1500 | FALSE | 2059.653 | 1869.3575 | 1.1618 | 8 | 8.3383e-05 | 2121 | 83.3451 | 2035 | 0.0083473 | 0.066779 | 2038 | 0.06 | 1818
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 11010 | FALSE | 3501.2634 | 3501.2634 | 2.176 | 26 | 0.00023343 | 269 | 31.1531 | 2340 | 0.0083235 | 0.21641 | 2039 | 12.24 | 375
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 237522 | FALSE | 26805.1596 | 1485.982 | 0.92354 | 39 | 3.422e-05 | 3366 | 404.1911 | 1293 | 0.0082937 | 0.32346 | 2040 |  | 3130
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | MR334 | FALSE | 9742.4846 | 9116.5949 | 5.666 | 80 | 8.203e-05 | 2151 | 200.4591 | 1639 | 0.0082358 | 0.65886 | 2041 |  | 2808
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | CB | FALSE | 28877.5917 | 25353.1416 | 15.7571 | 216 | 0.00013825 | 891 | 45.587 | 2242 | 0.008163 | 1.7632 | 2042 | 0.16 | 1262
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 152774 | FALSE | 12406.0754 | 10319.2603 | 6.4135 | 84 | 6.212e-05 | 2716 | 152.7782 | 1769 | 0.0081314 | 0.68304 | 2043 |  | 2709
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 920793 | FALSE | 12855.6086 | 10473.7039 | 6.5094 | 51 | 8.6884e-05 | 2016 | 85.5215 | 2025 | 0.008033 | 0.40968 | 2044 |  | 2833
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 1820 | FALSE | 9227.6622 | 9227.6622 | 5.735 | 51 | 7.9052e-05 | 2234 | 127.8002 | 1850 | 0.0080276 | 0.40941 | 2045 | 46.68 | 139
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 238990 | TRUE | 9730.7173 | 65.0773 | 0.040446 | 84 | 0.00017934 | 513 | 66.7295 | 2111 | 0.0080184 | 0.67354 | 2046 |  | 2918
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 6663 | FALSE | 3787.49 | 3787.49 | 2.3539 | 17 | 7.5146e-05 | 2328 | 97.3101 | 1972 | 0.0079953 | 0.13592 | 2047 | 1.13 | 713
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | CB | FALSE | 23959.1283 | 5020.5865 | 3.1203 | 191 | 0.00012086 | 1166 | 54.2982 | 2185 | 0.007993 | 1.5267 | 2048 | 0.11 | 1429
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | CB | FALSE | 63333.9358 | 37375.4287 | 23.229 | 440 | 0.00026939 | 173 | 30.0518 | 2342 | 0.0079104 | 3.4806 | 2049 | 0.19 | 1174
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 11062 | FALSE | 21428.2343 | 21428.2343 | 13.3177 | 88 | 0.00013572 | 922 | 71.1136 | 2090 | 0.007899 | 0.69511 | 2050 | 0.25 | 1075
7844 | ELK 11011260 | 42981101 | ELK 1101 | 1260 | FALSE | 25231.41 | 25226.838 | 15.6786 | 120 | 9.4953e-05 | 1767 | 70.6215 | 2091 | 0.0078966 | 0.94759 | 2051 | 0.04 | 2197
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 39104 | FALSE | 49366.035 | 49366.035 | 30.6812 | 346 | 0.00016953 | 566 | 33.5173 | 2314 | 0.007888 | 2.7292 | 2052 | 0.26 | 1066
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | CB | FALSE | 14345.0573 | 13611.4014 | 8.4595 | 92 | 0.00011705 | 1247 | 67.2853 | 2106 | 0.0078811 | 0.72506 | 2053 | 0.43 | 926
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 92172 | TRUE | 5246.1471 | 190.7947 | 0.11858 | 45 | 0.00012597 | 1079 | 55.6458 | 2177 | 0.0078638 | 0.35387 | 2054 | 0.61 | 846
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 69412 | FALSE | 34124.5253 | 25048.7626 | 15.5679 | 150 | 9.9166e-05 | 1664 | 96.7198 | 1975 | 0.0078448 | 1.1767 | 2055 | 0.06 | 1862
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | CB | FALSE | 12364.4219 | 3069.8489 | 1.9079 | 111 | 3.2822e-05 | 3389 | 173.8407 | 1700 | 0.0077955 | 0.8653 | 2056 | 0.03 | 2405
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 1296 | FALSE | 8913.723 | 5630.7668 | 3.4995 | 37 | 6.5385e-05 | 2603 | 134.0606 | 1835 | 0.007772 | 0.28757 | 2057 | 0.02 | 2458
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | CB | FALSE | 14659.7522 | 14659.7522 | 9.1111 | 110 | 0.00023141 | 282 | 46.7348 | 2235 | 0.0077431 | 0.85174 | 2058 | 50.51 | 118
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 1340 | FALSE | 28996.5273 | 28996.5273 | 18.0215 | 144 | 3.4761e-05 | 3354 | 286.6355 | 1466 | 0.0077101 | 1.1103 | 2059 | 0.06 | 1820
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 614 | FALSE | 2222.7419 | 2222.7419 | 1.3814 | 18 | 0.00013751 | 902 | 52.9107 | 2196 | 0.0076984 | 0.13857 | 2060 | 47.35 | 134
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 320 | FALSE | 4467.496 | 4467.496 | 2.7766 | 29 | 0.00021698 | 331 | 31.2121 | 2339 | 0.0076924 | 0.22308 | 2061 | 49.68 | 122
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 36514 | FALSE | 11050.0531 | 11050.0531 | 6.8677 | 64 | 0.00015664 | 677 | 62.082 | 2141 | 0.0076624 | 0.4904 | 2062 | 0.67 | 813
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 5156 | FALSE | 16018.9017 | 7784.4976 | 4.8381 | 114 | 9.9942e-05 | 1647 | 85.2613 | 2028 | 0.0076261 | 0.86938 | 2063 | 0.53 | 881
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 1308 | FALSE | 51491.5441 | 51491.5441 | 32.0022 | 245 | 8.9849e-05 | 1917 | 98.5183 | 1965 | 0.0076242 | 1.8679 | 2064 | 0.09 | 1559
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 1036 | TRUE | 989.4598 | 989.4598 | 0.61495 | 4 | 6.243e-05 | 2709 | 118.9656 | 1873 | 0.0076073 | 0.030429 | 2065 | 0.09 | 1531
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | V06 | FALSE | 10508.9376 | 3602.7995 | 2.2392 | 66 | 4.6125e-05 | 3135 | 94.4714 | 1983 | 0.007606 | 0.50199 | 2066 | 0.87 | 757
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 5722 | FALSE | 3182.5999 | 3182.5999 | 1.978 | 23 | 7.5358e-05 | 2325 | 108.5957 | 1915 | 0.0076053 | 0.17492 | 2067 | 0.29 | 1024
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | CB | FALSE | 10759.8557 | 10367.8883 | 6.4437 | 54 | 7.9345e-05 | 2224 | 98.8454 | 1961 | 0.0075954 | 0.41015 | 2068 | 0.46 | 912
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 343 | FALSE | 7140.9406 | 7140.9406 | 4.4381 | 39 | 0.0001241 | 1116 | 75.0943 | 2067 | 0.0075606 | 0.29486 | 2069 | 38.93 | 192
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 96986 | FALSE | 9497.5055 | 9497.5055 | 5.9027 | 63 | 0.00018221 | 496 | 38.932 | 2285 | 0.0075562 | 0.47604 | 2070 | 0.41 | 938
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | CB | FALSE | 14786.8555 | 5089.2485 | 3.163 | 92 | 0.00018939 | 445 | 47.0523 | 2232 | 0.0075338 | 0.69311 | 2071 | 0.06 | 1839
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 695411 | FALSE | 13352.973 | 13352.973 | 8.2989 | 99 | 0.00013199 | 984 | 79.3253 | 2051 | 0.0075292 | 0.74539 | 2072 |  | 3065
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 216324 | FALSE | 4626.1816 | 3681.9233 | 2.2883 | 23 | 0.00013316 | 955 | 50.0452 | 2210 | 0.0075204 | 0.17297 | 2073 |  | 3409
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | CB | TRUE | 5946.2245 | 0 | 0 | 51 | 0.00020302 | 386 | 24.2582 | 2398 | 0.0074949 | 0.38224 | 2074 | 0.05 | 1988
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 36764 | FALSE | 7038.6749 | 5034.5882 | 3.129 | 46 | 4.659e-05 | 3123 | 107.3772 | 1922 | 0.0074941 | 0.34473 | 2075 | 0 | 2633
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 758024 | FALSE | 10378.3257 | 7589.8929 | 4.7171 | 72 | 9.0405e-05 | 1901 | 69.6669 | 2097 | 0.007484 | 0.53884 | 2076 |  | 2992
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 930190 | FALSE | 30053.7833 | 27579.5424 | 17.1408 | 207 | 0.00014885 | 753 | 53.3783 | 2192 | 0.0074761 | 1.5476 | 2077 |  | 2690
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 10940 | FALSE | 17097.711 | 13824.9592 | 8.5923 | 138 | 0.0001288 | 1032 | 78.9158 | 2055 | 0.0073788 | 1.0183 | 2078 | 0.13 | 1356
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | CB | TRUE | 31613.0704 | 164.6636 | 0.10234 | 261 | 5.2389e-05 | 2982 | 125.9834 | 1855 | 0.0073172 | 1.9098 | 2079 |  | 2718
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 4036 | FALSE | 40366.1816 | 16000.3845 | 9.9443 | 57 | 4.3272e-05 | 3204 | 184.9055 | 1674 | 0.0073003 | 0.41612 | 2080 | 0.02 | 2455
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 380922 | FALSE | 4341.3947 | 1588.6005 | 0.98732 | 30 | 5.3037e-05 | 2965 | 107.6713 | 1919 | 0.0072901 | 0.2187 | 2081 |  | 3357
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 76850 | FALSE | 5941.1146 | 3458.1261 | 2.1492 | 51 | 0.00012907 | 1026 | 65.4632 | 2120 | 0.0072691 | 0.37072 | 2082 | 0.04 | 2220
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 4018 | FALSE | 85010.3668 | 71470.9964 | 44.4195 | 280 | 6.7671e-05 | 2541 | 115.5373 | 1893 | 0.0072679 | 2.035 | 2083 | 0.08 | 1661
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 346 | FALSE | 16160.3417 | 16160.3417 | 10.0437 | 101 | 0.00015809 | 662 | 67.6609 | 2104 | 0.0072159 | 0.72881 | 2084 | 0.97 | 737
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 258878 | FALSE | 7396.9293 | 5357.1763 | 3.3295 | 26 | 3.9953e-05 | 3270 | 107.5084 | 1921 | 0.0072141 | 0.18757 | 2085 |  | 3114
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 137662 | FALSE | 13866.4902 | 13813.2405 | 8.585 | 104 | 0.00014441 | 806 | 94.0043 | 1985 | 0.0071841 | 0.74714 | 2086 | 0.76 | 786
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | CB | FALSE | 54723.5805 | 54723.5805 | 34.0109 | 337 | 0.00011257 | 1353 | 93.6722 | 1990 | 0.0071702 | 2.4164 | 2087 | 71.14 | 67
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 953474 | FALSE | 17115.5789 | 17115.5789 | 10.6374 | 133 | 0.000245 | 233 | 47.063 | 2231 | 0.0071239 | 0.94748 | 2088 |  | 2666
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 722270 | TRUE | 712.8056 | 283.5574 | 0.17623 | 5 | 3.323e-05 | 3380 | 133.0363 | 1839 | 0.0070957 | 0.035479 | 2089 |  | 3434
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 140 | FALSE | 13525.925 | 13525.925 | 8.4064 | 96 | 0.0002562 | 201 | 19.1476 | 2459 | 0.0070376 | 0.67561 | 2090 | 16.37 | 338
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 4914 | FALSE | 22650.1521 | 17097.4476 | 10.6261 | 138 | 0.00016776 | 577 | 39.2521 | 2282 | 0.0070374 | 0.97117 | 2091 | 0.08 | 1621
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 10330 | FALSE | 15550.3229 | 15550.3229 | 9.6646 | 90 | 7.2321e-05 | 2408 | 118.1064 | 1878 | 0.0069896 | 0.62906 | 2092 | 0.31 | 1008
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 9702 | FALSE | 14797.576 | 1035.9167 | 0.64383 | 91 | 3.6155e-05 | 3331 | 189.6534 | 1664 | 0.006985 | 0.63564 | 2093 | 0.01 | 2605
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 3050 | FALSE | 4223.7094 | 4223.7094 | 2.6251 | 18 | 0.00010688 | 1481 | 71.3502 | 2089 | 0.0069828 | 0.12569 | 2094 | 11.06 | 389
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 581588 | TRUE | 1519.7137 | 313.0143 | 0.19454 | 14 | 0.00011751 | 1235 | 44.2079 | 2251 | 0.0069585 | 0.097419 | 2095 |  | 3376
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 2140 | FALSE | 55629.2693 | 55629.2693 | 34.5738 | 373 | 7.6296e-05 | 2300 | 87.1186 | 2015 | 0.0069513 | 2.5928 | 2096 | 99.53 | 20
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 331806 | TRUE | 1086.2067 | 799.0558 | 0.49662 | 5 | 0.00010249 | 1590 | 66.6724 | 2112 | 0.0069274 | 0.034637 | 2097 |  | 3162
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 6175 | FALSE | 4418.4642 | 4418.4642 | 2.7461 | 30 | 7.0467e-05 | 2457 | 113.3507 | 1901 | 0.0069045 | 0.20713 | 2098 | 0.08 | 1596
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 803 | FALSE | 15630.8479 | 15630.8479 | 9.7146 | 93 | 8.737e-05 | 2002 | 89.4789 | 2003 | 0.0068944 | 0.64118 | 2099 | 0.14 | 1319
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 228 | FALSE | 15665.2534 | 3403.012 | 2.115 | 123 | 0.00014113 | 851 | 47.1197 | 2230 | 0.0068367 | 0.84091 | 2100 | 1.03 | 725
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 603250 | TRUE | 2274.9057 | 927.3694 | 0.57636 | 21 | 0.00016094 | 631 | 57.7467 | 2167 | 0.0068337 | 0.14351 | 2101 |  | 3184
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 618 | TRUE | 16180.0386 | 742.2572 | 0.46132 | 118 | 9.7103e-05 | 1711 | 69.2887 | 2098 | 0.0068234 | 0.80516 | 2102 | 17.57 | 331
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 8601 | TRUE | 961.631 | 961.631 | 0.59766 | 9 | 0.00015446 | 700 | 60.8174 | 2150 | 0.0067792 | 0.061013 | 2103 | 35.86 | 209
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 7240 | FALSE | 41066.7491 | 1553.9231 | 0.96577 | 234 | 4.3626e-05 | 3198 | 175.637 | 1696 | 0.0067642 | 1.5828 | 2104 | 0.02 | 2533
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 138 | TRUE | 26504.92 | 104.0479 | 0.064666 | 197 | 6.5875e-05 | 2590 | 63.508 | 2131 | 0.0067556 | 1.3309 | 2105 | 0.62 | 838
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 59770 | FALSE | 11687.7507 | 7749.7634 | 4.8165 | 97 | 8.5709e-05 | 2037 | 89.7185 | 2001 | 0.0067467 | 0.65443 | 2106 | 0.09 | 1532
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 566352 | TRUE | 1524.3755 | 680.7554 | 0.42309 | 9 | 3.3385e-05 | 3378 | 153.3762 | 1766 | 0.0067421 | 0.060679 | 2107 |  | 3079
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 990464 | FALSE | 8550.7923 | 3365.9887 | 2.092 | 53 | 2.9572e-05 | 3431 | 166.8203 | 1728 | 0.0067321 | 0.3568 | 2108 |  | 3234
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 37034 | FALSE | 7287.0481 | 7287.0481 | 4.5289 | 16 | 0.00011223 | 1360 | 44.6194 | 2249 | 0.006701 | 0.10722 | 2109 | 0.31 | 1007
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 50550 | TRUE | 16250.0266 | 0 | 0 | 127 | 0.00012612 | 1078 | 64.7345 | 2124 | 0.0066813 | 0.84852 | 2110 | 0.74 | 790
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 39458 | FALSE | 8594.1592 | 1902.6531 | 1.1825 | 72 | 7.6303e-05 | 2298 | 85.8335 | 2024 | 0.0066627 | 0.47971 | 2111 | 0.27 | 1048
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 8512 | FALSE | 39804.5313 | 39804.5313 | 24.7387 | 228 | 0.00015985 | 643 | 38.9598 | 2284 | 0.0066372 | 1.5133 | 2112 | 8.94 | 418
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 904 | FALSE | 11554.8525 | 2469.2456 | 1.5346 | 78 | 4.3101e-05 | 3208 | 64.1478 | 2127 | 0.0066274 | 0.51694 | 2113 | 0.04 | 2146
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 89714 | TRUE | 11363.665 | 178.2278 | 0.11077 | 71 | 8.7635e-05 | 1996 | 68.3169 | 2100 | 0.0066271 | 0.47052 | 2114 | 0.02 | 2528
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 344 | FALSE | 9676.0469 | 2427.2453 | 1.5085 | 77 | 0.00010403 | 1551 | 64.3203 | 2126 | 0.0066172 | 0.50953 | 2115 | 1.32 | 687
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 11092 | FALSE | 36100.2834 | 36100.2834 | 22.4365 | 239 | 0.00011036 | 1404 | 74.4691 | 2070 | 0.0066099 | 1.5798 | 2116 | 0.14 | 1314
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 645 | FALSE | 1626.8938 | 1626.8938 | 1.0111 | 13 | 9.1232e-05 | 1870 | 67.7241 | 2103 | 0.0065604 | 0.085285 | 2117 | 60.62 | 88
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 474708 | TRUE | 1392.1284 | 422.046 | 0.2623 | 13 | 0.00016436 | 594 | 18.3674 | 2470 | 0.0065356 | 0.084962 | 2118 |  | 3063
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | A64 | FALSE | 18905.9424 | 3242.5015 | 2.0152 | 150 | 7.5966e-05 | 2309 | 88.4837 | 2011 | 0.0065293 | 0.9794 | 2119 | 0.02 | 2493
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 861610 | FALSE | 11222.3603 | 1689.7743 | 1.0502 | 99 | 0.00027833 | 162 | 23.4916 | 2410 | 0.0065286 | 0.64633 | 2120 |  | 2695
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 86326 | FALSE | 1145.996 | 1133.0955 | 0.70422 | 5 | 8.4164e-05 | 2088 | 38.1596 | 2289 | 0.0065228 | 0.032614 | 2121 |  | 3481
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 404 | FALSE | 7372.5748 | 3785.8959 | 2.3529 | 63 | 6.9011e-05 | 2509 | 86.9459 | 2016 | 0.0065164 | 0.41053 | 2122 | 0.24 | 1106
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | CB | FALSE | 15016.5066 | 13697.3672 | 8.513 | 117 | 0.00025615 | 202 | 34.5981 | 2310 | 0.0065148 | 0.76223 | 2123 | 0.09 | 1568
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 77384 | FALSE | 7595.6346 | 7595.6346 | 4.7207 | 61 | 0.00017011 | 562 | 62.7847 | 2138 | 0.0065145 | 0.39738 | 2124 | 0.65 | 823
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 1504 | FALSE | 13347.4853 | 13347.4853 | 8.2955 | 95 | 5.8288e-05 | 2825 | 84.8611 | 2031 | 0.0065125 | 0.61869 | 2125 | 45.39 | 148
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 920400 | FALSE | 7975.407 | 7538.764 | 4.6854 | 66 | 0.00044142 | 53 | 18.0732 | 2478 | 0.0064968 | 0.42879 | 2126 |  | 2964
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | MR297 | FALSE | 9710.6915 | 9531.5764 | 5.9239 | 66 | 6.9143e-05 | 2502 | 221.7666 | 1602 | 0.0064881 | 0.42822 | 2127 | 0.06 | 1849
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 354 | FALSE | 12035.3765 | 1010.2026 | 0.62784 | 79 | 9.3149e-05 | 1816 | 134.0043 | 1836 | 0.0064828 | 0.51214 | 2128 |  | 2822
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 560 | FALSE | 9061.7878 | 8145.5491 | 5.0625 | 31 | 9.9934e-05 | 1648 | 60.8351 | 2148 | 0.0064599 | 0.20026 | 2129 | 0.02 | 2420
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 36880 | FALSE | 13851.9467 | 9899.4771 | 6.1526 | 92 | 8.6095e-05 | 2032 | 179.7214 | 1684 | 0.0064477 | 0.59319 | 2130 | 0.08 | 1578
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 1104 | FALSE | 79643.684 | 79643.684 | 49.4989 | 462 | 0.00011856 | 1216 | 56.9205 | 2171 | 0.0064469 | 2.9785 | 2131 | 111.82 | 14
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 10315 | FALSE | 8831.8074 | 8831.8074 | 5.489 | 53 | 0.00010699 | 1472 | 59.7801 | 2155 | 0.006431 | 0.34084 | 2132 |  | 3064
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 982462 | FALSE | 2320.5593 | 2320.5593 | 1.4422 | 18 | 9.629e-05 | 1726 | 75.3379 | 2065 | 0.006427 | 0.11569 | 2133 |  | 3100
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | CB | TRUE | 2754.8033 | 5.4992 | 0.0034177 | 26 | 0.00020884 | 366 | 19.5341 | 2454 | 0.0064174 | 0.16685 | 2134 | 0.01 | 2596
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 19712 | FALSE | 20850.3369 | 20776.2868 | 12.9125 | 151 | 0.000145 | 801 | 90.5715 | 1997 | 0.0064118 | 0.96818 | 2135 | 0.12 | 1371
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 13438 | FALSE | 26618.9181 | 26618.9181 | 16.5438 | 172 | 0.00010264 | 1581 | 69.7074 | 2096 | 0.0063999 | 1.1008 | 2136 | 82.17 | 45
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 49756 | FALSE | 9480.1738 | 1727.7805 | 1.0738 | 40 | 7.5687e-05 | 2316 | 118.0346 | 1881 | 0.0063622 | 0.25449 | 2137 | 0.01 | 2594
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | CB | FALSE | 4085.1757 | 4085.1757 | 2.539 | 27 | 6.8809e-05 | 2513 | 75.2459 | 2066 | 0.0062536 | 0.16885 | 2138 | 0.07 | 1752
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 36870 | TRUE | 3829.3681 | 541.2922 | 0.33642 | 29 | 0.00011992 | 1188 | 41.8373 | 2269 | 0.0062483 | 0.1812 | 2139 | 0.04 | 2157
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 3113 | FALSE | 16133.333 | 16133.333 | 10.0269 | 68 | 8.3643e-05 | 2106 | 76.2422 | 2061 | 0.0062347 | 0.42396 | 2140 | 0.05 | 1961
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 2214 | FALSE | 29878.7054 | 24265.0129 | 15.0808 | 233 | 0.00042568 | 61 | 48.0844 | 2221 | 0.0062243 | 1.4503 | 2141 | 51.75 | 113
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 79826 | FALSE | 16584.8842 | 16584.8842 | 10.3076 | 95 | 0.00015691 | 673 | 91.848 | 1994 | 0.0062159 | 0.59051 | 2142 | 0.15 | 1290
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 98174 | FALSE | 19681.5881 | 19681.5881 | 12.2322 | 66 | 7.9168e-05 | 2229 | 58.0357 | 2166 | 0.0062048 | 0.40952 | 2143 | 22.16 | 296
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 50070 | FALSE | 28555.3412 | 28555.3412 | 17.7473 | 201 | 0.00011083 | 1394 | 43.6964 | 2255 | 0.0062036 | 1.2469 | 2144 | 128.64 | 7
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 413816 | FALSE | 17928.3843 | 17928.3843 | 11.1426 | 104 | 0.00011948 | 1197 | 65.9071 | 2117 | 0.0061927 | 0.64404 | 2145 | 0.87 | 760
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 483444 | FALSE | 8714.6826 | 3311.0968 | 2.0579 | 67 | 5.4635e-05 | 2929 | 67.496 | 2105 | 0.0061552 | 0.4124 | 2146 |  | 2731
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 8582 | FALSE | 19173.6398 | 15254.7771 | 9.4809 | 163 | 0.00018689 | 463 | 41.133 | 2272 | 0.0061345 | 0.99993 | 2147 | 0.05 | 1953
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | LA60 | FALSE | 13957.1729 | 13957.1729 | 8.6744 | 61 | 0.00010054 | 1636 | 81.9054 | 2041 | 0.0061263 | 0.3737 | 2148 | 41.93 | 173
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 1502 | FALSE | 11680.2523 | 11680.2523 | 7.2593 | 80 | 8.0915e-05 | 2184 | 65.4099 | 2121 | 0.0061144 | 0.48915 | 2149 | 27.78 | 255
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | CB | FALSE | 8114.1348 | 6042.2888 | 3.7553 | 50 | 0.00011189 | 1369 | 66.0103 | 2115 | 0.0060781 | 0.30391 | 2150 | 0.06 | 1817
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 653758 | TRUE | 582.3673 | 582.3673 | 0.36194 | 5 | 5.5782e-05 | 2895 | 104.6024 | 1930 | 0.0060671 | 0.030336 | 2151 |  | 3538
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 38698 | FALSE | 25178.9612 | 25178.9612 | 15.6488 | 103 | 9.2036e-05 | 1843 | 61.204 | 2145 | 0.0060349 | 0.62159 | 2152 | 4.1 | 526
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 9112 | FALSE | 8500.5119 | 1386.5143 | 0.86172 | 68 | 4.4335e-05 | 3182 | 101.7861 | 1948 | 0.0060009 | 0.40806 | 2153 | 0.04 | 2214
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 821698 | FALSE | 1364.9269 | 1364.9269 | 0.84831 | 9 | 5.5293e-05 | 2904 | 187.6587 | 1667 | 0.0060008 | 0.054007 | 2154 |  | 3345
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 409621 | TRUE | 945.4612 | 219.1314 | 0.13619 | 4 | 8.5029e-05 | 2059 | 85.5196 | 2026 | 0.0059943 | 0.023977 | 2155 |  | 3567
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 12518 | FALSE | 25177.1399 | 25177.1399 | 15.6477 | 145 | 0.00025023 | 216 | 28.5941 | 2352 | 0.0059295 | 0.85978 | 2156 | 0.8 | 774
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 2104 | FALSE | 15810.2753 | 15810.2753 | 9.8261 | 123 | 0.00020356 | 384 | 19.3883 | 2456 | 0.0059169 | 0.72777 | 2157 | 38.88 | 194
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 5470 | FALSE | 14989.8273 | 14989.8273 | 9.3162 | 104 | 0.00010143 | 1618 | 96.9488 | 1973 | 0.0059093 | 0.61457 | 2158 | 14.88 | 353
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 94892 | TRUE | 15531.7609 | 345.9853 | 0.21503 | 66 | 3.5047e-05 | 3351 | 201.9181 | 1637 | 0.0059064 | 0.38983 | 2159 |  | 2790
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 94770 | FALSE | 6459.1608 | 3806.5671 | 2.3658 | 55 | 0.00027047 | 172 | 16.4987 | 2510 | 0.0059058 | 0.32482 | 2160 | 0.27 | 1050
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 328 | FALSE | 22172.9748 | 2414.9476 | 1.5009 | 173 | 9.4997e-05 | 1766 | 59.7612 | 2156 | 0.0058817 | 1.0175 | 2161 | 1 | 732
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 47952 | FALSE | 16717.6297 | 16717.6297 | 10.3901 | 88 | 0.00011754 | 1233 | 58.6557 | 2163 | 0.0058506 | 0.51485 | 2162 | 0.09 | 1517
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 825 | TRUE | 3371.6214 | 749.4567 | 0.46579 | 26 | 6.9953e-05 | 2473 | 79.9838 | 2048 | 0.0058122 | 0.15112 | 2163 |  | 2782
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 3026 | FALSE | 36330.5251 | 35201.2582 | 21.8777 | 238 | 5.5886e-05 | 2892 | 99.002 | 1958 | 0.0057671 | 1.3726 | 2164 | 2.36 | 610
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | XR494 | TRUE | 11814.5496 | 737.5052 | 0.45836 | 98 | 5.6428e-05 | 2877 | 82.0467 | 2040 | 0.0057504 | 0.56354 | 2165 | 0.04 | 2167
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 77670 | FALSE | 10996.9079 | 10874.5833 | 6.7586 | 98 | 0.00011661 | 1258 | 47.4912 | 2228 | 0.0057454 | 0.56305 | 2166 | 19.77 | 309
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 10294 | FALSE | 13501.9938 | 13501.9938 | 8.3915 | 95 | 0.00023536 | 261 | 22.5874 | 2416 | 0.0057046 | 0.54194 | 2167 | 48.18 | 131
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 480 | FALSE | 25809.6606 | 2502.4894 | 1.5553 | 161 | 6.7656e-05 | 2543 | 89.1189 | 2006 | 0.0057021 | 0.91803 | 2168 | 0.01 | 2595
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 8912 | FALSE | 6310.9141 | 6268.7877 | 3.8961 | 52 | 0.000205 | 381 | 25.8096 | 2383 | 0.0056974 | 0.29627 | 2169 | 26.71 | 266
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 482 | TRUE | 6000.1069 | 595.0555 | 0.36983 | 38 | 6e-05 | 2775 | 118.3715 | 1876 | 0.0056711 | 0.2155 | 2170 | 0.74 | 789
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 12992 | FALSE | 22915.4569 | 22915.4569 | 14.242 | 160 | 0.00020519 | 379 | 28.593 | 2353 | 0.0056575 | 0.90521 | 2171 | 1.14 | 711
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | CB | FALSE | 1694.4122 | 1694.4122 | 1.0531 | 22 | 5.8522e-05 | 2821 | 53.0175 | 2195 | 0.0056462 | 0.12422 | 2172 | 0.02 | 2450
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 47198 | FALSE | 9365.2067 | 4939.462 | 3.0699 | 70 | 0.00010692 | 1477 | 39.3397 | 2280 | 0.0056207 | 0.39345 | 2173 | 0.04 | 2116
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 167360 | FALSE | 15830.4656 | 15413.5909 | 9.5796 | 70 | 0.0001177 | 1232 | 51.7218 | 2203 | 0.0056116 | 0.39281 | 2174 |  | 3176
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 8000 | FALSE | 23055.4602 | 23055.4602 | 14.3291 | 174 | 0.00011159 | 1377 | 95.7818 | 1979 | 0.0056032 | 0.97497 | 2175 | 0.55 | 871
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | CB | TRUE | 4645.037 | 606.8044 | 0.37713 | 37 | 4.6425e-05 | 3127 | 105.6404 | 1927 | 0.0055946 | 0.207 | 2176 | 0.05 | 1970
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2028 | FALSE | 3747.9741 | 3373.7724 | 2.0968 | 38 | 7.449e-05 | 2345 | 86.2641 | 2021 | 0.0055851 | 0.21223 | 2177 | 0.08 | 1658
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | A50 | FALSE | 33669.9383 | 31118.7087 | 19.3404 | 269 | 5.5958e-05 | 2891 | 116.8319 | 1888 | 0.0055802 | 1.5011 | 2178 | 0.22 | 1131
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 1294 | FALSE | 32661.4744 | 31953.6798 | 19.8593 | 234 | 6.861e-05 | 2518 | 79.062 | 2054 | 0.0055387 | 1.2961 | 2179 | 0.53 | 883
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | P150 | FALSE | 3652.8381 | 3652.8381 | 2.2703 | 18 | 9.5063e-05 | 1763 | 45.0393 | 2245 | 0.0055206 | 0.09937 | 2180 | 0.03 | 2243
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 1660 | FALSE | 7855.6793 | 7855.6793 | 4.8823 | 43 | 0.00014039 | 865 | 43.7408 | 2254 | 0.0055185 | 0.23729 | 2181 | 0.02 | 2545
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | CB | FALSE | 7739.8411 | 2580.5041 | 1.6038 | 68 | 0.00014616 | 786 | 21.7605 | 2428 | 0.0054995 | 0.37397 | 2182 | 0.06 | 1798
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 610148 | FALSE | 19896.3037 | 3154.5584 | 1.9606 | 58 | 4.5598e-05 | 3151 | 102.3263 | 1944 | 0.0054812 | 0.31791 | 2183 |  | 3231
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 94178 | FALSE | 6646.4632 | 3457.4484 | 2.1488 | 57 | 7.3272e-05 | 2388 | 42.0306 | 2265 | 0.0054615 | 0.3113 | 2184 | 0.03 | 2290
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | CB | FALSE | 9963.4073 | 9963.4073 | 6.1923 | 59 | 0.00022265 | 308 | 33.5088 | 2315 | 0.0054141 | 0.31943 | 2185 | 0.49 | 898
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6012 | FALSE | 15479.7977 | 10729.2764 | 6.6683 | 79 | 9.0533e-05 | 1896 | 70.018 | 2095 | 0.0054078 | 0.42722 | 2186 | 0.08 | 1585
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 2020 | FALSE | 55275.2572 | 55275.2572 | 34.3538 | 281 | 9.1434e-05 | 1861 | 43.1327 | 2260 | 0.005376 | 1.5107 | 2187 | 0.23 | 1114
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | V50 | FALSE | 16840.5394 | 11517.5193 | 7.1582 | 107 | 4.7059e-05 | 3112 | 96.3505 | 1978 | 0.005367 | 0.57427 | 2188 | 0.11 | 1428
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 404 | FALSE | 19975.081 | 19975.081 | 12.4146 | 152 | 0.00018515 | 471 | 26.3611 | 2372 | 0.0053668 | 0.81576 | 2189 | 92.58 | 29
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 57926 | TRUE | 18926.9724 | 200.7916 | 0.12479 | 97 | 5.4965e-05 | 2914 | 62.5543 | 2139 | 0.0053561 | 0.51954 | 2190 |  | 2900
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 5188 | FALSE | 3280.6197 | 3280.6197 | 2.0389 | 19 | 0.00034885 | 92 | 16.3316 | 2511 | 0.0053482 | 0.10162 | 2191 | 7.26 | 449
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 652 | FALSE | 2607.8717 | 2607.8717 | 1.6208 | 25 | 0.00027854 | 161 | 20.0324 | 2448 | 0.0053427 | 0.13357 | 2192 | 55.16 | 104
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 260 | FALSE | 9537.0372 | 4317.1662 | 2.6831 | 68 | 6.2862e-05 | 2687 | 71.585 | 2084 | 0.0053405 | 0.36316 | 2193 | 0.78 | 778
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 574315 | FALSE | 12024.0849 | 11904.9852 | 7.399 | 78 | 0.00010886 | 1429 | 65.6711 | 2118 | 0.005318 | 0.4148 | 2194 |  | 2800
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 76952 | FALSE | 18206.8026 | 3648.4496 | 2.2675 | 161 | 0.00026698 | 179 | 39.5343 | 2276 | 0.0052383 | 0.84337 | 2195 | 0.06 | 1785
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 501771 | FALSE | 7891.6601 | 7891.6601 | 4.9047 | 54 | 4.0591e-05 | 3256 | 137.8049 | 1819 | 0.0052248 | 0.28214 | 2196 |  | 3217
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 440 | FALSE | 17666.8696 | 13392.7701 | 8.3237 | 107 | 5.2851e-05 | 2975 | 95.646 | 1980 | 0.0051543 | 0.5515 | 2197 | 0.05 | 1917
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 75612 | TRUE | 15618.6787 | 0 | 0 | 114 | 6.2516e-05 | 2703 | 68.7688 | 2099 | 0.0051135 | 0.58294 | 2198 |  | 2747
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 12122 | FALSE | 12740.7086 | 10570.3766 | 6.5695 | 63 | 0.00010779 | 1455 | 51.4668 | 2205 | 0.0051004 | 0.32133 | 2199 | 0.03 | 2382
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 940 | FALSE | 5636.9672 | 1911.101 | 1.1878 | 46 | 0.00018608 | 466 | 23.9825 | 2400 | 0.005067 | 0.23308 | 2200 | 7.35 | 447
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 32726 | FALSE | 19770.2597 | 19581.5665 | 12.17 | 146 | 0.00014193 | 840 | 48.5752 | 2218 | 0.00506 | 0.73876 | 2201 | 0.1 | 1475
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 2452 | TRUE | 11049.8485 | 228.5177 | 0.14202 | 87 | 5.4568e-05 | 2931 | 79.1562 | 2053 | 0.0050248 | 0.43716 | 2202 | 13.72 | 363
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | XR578 | TRUE | 1108.6732 | 261.0602 | 0.16225 | 12 | 5.1652e-05 | 3003 | 53.5212 | 2190 | 0.0050174 | 0.060209 | 2203 | 0.02 | 2414
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 528344 | FALSE | 43372.0838 | 43372.0838 | 26.9559 | 171 | 9.687e-05 | 1717 | 60.4469 | 2152 | 0.0049999 | 0.85498 | 2204 |  | 2950
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 148504 | TRUE | 3218.0268 | 275.7602 | 0.17139 | 14 | 6.4053e-05 | 2643 | 71.3988 | 2086 | 0.0049963 | 0.069948 | 2205 |  | 3134
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 2293 | FALSE | 2820.5709 | 2820.5709 | 1.753 | 21 | 6.9405e-05 | 2492 | 78.9038 | 2056 | 0.0049653 | 0.10427 | 2206 | 0.04 | 2140
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | CB | FALSE | 2574.4725 | 2574.4725 | 1.6 | 18 | 0.00018307 | 488 | 33.0833 | 2322 | 0.0049349 | 0.088829 | 2207 | 0.05 | 1919
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 11533 | FALSE | 4249.6596 | 4249.6596 | 2.6412 | 28 | 9.1401e-05 | 1863 | 58.6478 | 2164 | 0.0048855 | 0.13679 | 2208 | 29.27 | 243
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | R324 | FALSE | 17238.3934 | 17238.3934 | 10.7137 | 119 | 3.9517e-05 | 3277 | 112.2851 | 1904 | 0.0048731 | 0.5799 | 2209 | 35.54 | 213
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 83716 | FALSE | 4275.4859 | 4027.3677 | 2.503 | 22 | 0.00011418 | 1318 | 54.1847 | 2187 | 0.0048588 | 0.10689 | 2210 | 0.02 | 2436
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 878870 | FALSE | 4057.446 | 4057.446 | 2.5217 | 29 | 0.00048816 | 33 | 4.9842 | 2754 | 0.0048412 | 0.1404 | 2211 |  | 2967
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 1184 | FALSE | 18935.6341 | 18820.6068 | 11.6971 | 136 | 0.00016372 | 603 | 34.7864 | 2309 | 0.0048403 | 0.65828 | 2212 | 54.38 | 107
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 2130 | FALSE | 23180.7639 | 23180.7639 | 14.4069 | 163 | 5.7718e-05 | 2845 | 88.5821 | 2010 | 0.0048209 | 0.78581 | 2213 | 63.53 | 81
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | MR273 | FALSE | 1164.6083 | 1164.6083 | 0.72381 | 13 | 7.8527e-05 | 2248 | 62.481 | 2140 | 0.0047919 | 0.062294 | 2214 |  | 3564
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 44119 | TRUE | 4510.2451 | 512.7214 | 0.31866 | 35 | 5.2979e-05 | 2968 | 87.4332 | 2013 | 0.0047623 | 0.16668 | 2215 | 0.04 | 2190
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1082 | FALSE | 4959.0869 | 2511.2326 | 1.5607 | 36 | 3.822e-05 | 3296 | 64.7708 | 2123 | 0.0047619 | 0.17143 | 2216 | 1.65 | 659
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 8130 | FALSE | 15961.1359 | 15961.1359 | 9.9199 | 123 | 8.1184e-05 | 2179 | 72.5007 | 2080 | 0.0047602 | 0.5855 | 2217 | 65.59 | 76
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | CB | TRUE | 5810.1426 | 159.6823 | 0.099243 | 47 | 0.00010848 | 1437 | 74.8868 | 2068 | 0.0047601 | 0.22372 | 2218 | 0.03 | 2307
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 127462 | TRUE | 205.3095 | 189.2737 | 0.11763 | 2 | 0.00015962 | 647 | 47.5976 | 2225 | 0.0047158 | 0.0094316 | 2219 |  | 3622
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 829530 | FALSE | 4171.4477 | 2687.7051 | 1.6704 | 32 | 7.4329e-05 | 2348 | 92.7573 | 1991 | 0.0047024 | 0.15048 | 2220 |  | 3320
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 673480 | FALSE | 20487.8392 | 20487.8392 | 12.7333 | 88 | 0.00010713 | 1470 | 66.7652 | 2110 | 0.0046984 | 0.41346 | 2221 |  | 2733
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | CB | FALSE | 6307.2067 | 6307.2067 | 3.92 | 54 | 0.00038312 | 73 | 17.6674 | 2486 | 0.0046671 | 0.25202 | 2222 | 0.09 | 1518
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 432 | FALSE | 79373.0607 | 79373.0607 | 49.3307 | 320 | 6.1723e-05 | 2728 | 74.7952 | 2069 | 0.0046501 | 1.488 | 2223 | 0.19 | 1170
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | CB | FALSE | 1162.2395 | 1162.2395 | 0.72234 | 10 | 0.00013488 | 929 | 47.6107 | 2224 | 0.0046279 | 0.046279 | 2224 | 0.01 | 2572
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 38514 | FALSE | 17257.2473 | 17257.2473 | 10.7254 | 102 | 0.00021556 | 338 | 24.5363 | 2394 | 0.0046099 | 0.47021 | 2225 | 0.75 | 788
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 1922 | FALSE | 7694.4261 | 7391.7604 | 4.594 | 70 | 0.00019092 | 438 | 30.2755 | 2341 | 0.004588 | 0.32116 | 2226 | 17.29 | 334
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 60118 | FALSE | 44902.9478 | 44902.9478 | 27.9074 | 323 | 0.00017204 | 550 | 26.0465 | 2376 | 0.0045775 | 1.4785 | 2227 | 45.32 | 149
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | MR172 | TRUE | 1779.1253 | 856.8002 | 0.5325 | 26 | 6.2738e-05 | 2692 | 64.6297 | 2125 | 0.0045679 | 0.11876 | 2228 | 27.77 | 256
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 681991 | FALSE | 6056.3505 | 2212.0344 | 1.3748 | 50 | 6.8561e-05 | 2521 | 61.126 | 2147 | 0.0045171 | 0.22586 | 2229 |  | 2909
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 1232 | FALSE | 3935.7724 | 3637.3088 | 2.2606 | 22 | 9.124e-05 | 1868 | 55.6272 | 2178 | 0.0045024 | 0.099054 | 2230 | 3.14 | 560
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 1212 | TRUE | 6586.9975 | 0 | 0 | 62 | 4.464e-05 | 3173 | 87.4084 | 2014 | 0.0044984 | 0.2789 | 2231 | 0.42 | 928
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | CB | TRUE | 35309.4801 | 290.0531 | 0.18027 | 155 | 3.607e-05 | 3336 | 256.8183 | 1529 | 0.0044835 | 0.69495 | 2232 |  | 3056
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 317156 | FALSE | 18303.2443 | 3816.311 | 2.3719 | 67 | 5.1745e-05 | 3000 | 86.4803 | 2018 | 0.0044039 | 0.29506 | 2233 |  | 3166
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 1535 | FALSE | 4933.5895 | 4933.5895 | 3.0662 | 30 | 6.0964e-05 | 2749 | 63.4215 | 2132 | 0.0043786 | 0.13136 | 2234 | 52.41 | 112
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | CB | TRUE | 3629.5545 | 353.0082 | 0.2194 | 38 | 5.0792e-05 | 3020 | 63.168 | 2135 | 0.0043636 | 0.16582 | 2235 | 0.22 | 1127
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 432198 FM | TRUE | 3829.098 | 907.0096 | 0.56371 | 31 | 7.0176e-05 | 2467 | 53.7914 | 2188 | 0.004363 | 0.13525 | 2236 |  | 3344
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 5384 | FALSE | 28128.0957 | 25050.2712 | 15.5688 | 202 | 0.0002103 | 356 | 21.9397 | 2426 | 0.0043604 | 0.88081 | 2237 | 0.18 | 1214
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 332 | FALSE | 9174.8238 | 9174.8238 | 5.7022 | 67 | 0.00022781 | 292 | 15.3212 | 2526 | 0.0043573 | 0.29194 | 2238 | 30.76 | 235
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 1989 | FALSE | 1195.1936 | 1195.1936 | 0.74282 | 9 | 0.00014388 | 816 | 55.5275 | 2179 | 0.0043487 | 0.039138 | 2239 | 44.54 | 158
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 10723 | TRUE | 6.3415 | 6.3415 | 0.0039412 | 1 | 9.0549e-05 | 1895 | 47.5921 | 2226 | 0.0043094 | 0.0043094 | 2240 | 48.3 | 130
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 309298 | FALSE | 3091.9426 | 1768.6422 | 1.0992 | 23 | 9.5445e-05 | 1744 | 39.3183 | 2281 | 0.0043094 | 0.099116 | 2241 |  | 3197
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 23444 | FALSE | 23380.6907 | 23380.6907 | 14.5312 | 135 | 0.00010219 | 1599 | 47.2338 | 2229 | 0.0042666 | 0.57599 | 2242 | 0.12 | 1396
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 60124 | FALSE | 36140.2282 | 36140.2282 | 22.4613 | 267 | 0.00016531 | 587 | 37.1047 | 2296 | 0.0042657 | 1.1389 | 2243 | 77.48 | 53
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 392 | TRUE | 10922.1116 | 404.9115 | 0.25165 | 68 | 9.4205e-05 | 1789 | 58.5408 | 2165 | 0.0042431 | 0.28853 | 2244 | 0.28 | 1035
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | N532R | FALSE | 7429.2796 | 5942.762 | 3.6935 | 65 | 9.0315e-05 | 1903 | 44.8885 | 2247 | 0.004228 | 0.27482 | 2245 | 0.09 | 1560
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 2253 | FALSE | 2335.3363 | 2335.3363 | 1.4514 | 12 | 0.00020821 | 370 | 19.8765 | 2451 | 0.0041981 | 0.050377 | 2246 | 0.17 | 1238
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 1341 | FALSE | 15927.2159 | 15927.2159 | 9.8988 | 87 | 5.9226e-05 | 2799 | 79.2605 | 2052 | 0.0041901 | 0.36454 | 2247 | 0.52 | 886
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 53120 | TRUE | 12732.032 | 173.1766 | 0.10763 | 92 | 2.9816e-05 | 3429 | 159.0093 | 1750 | 0.004183 | 0.38483 | 2248 |  | 2793
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | CB | TRUE | 3345.6946 | 710.3038 | 0.44146 | 26 | 0.00011363 | 1329 | 21.0918 | 2434 | 0.0041416 | 0.10768 | 2249 | 0.02 | 2541
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | CB | FALSE | 11999.4505 | 11999.4505 | 7.4577 | 74 | 0.00013448 | 935 | 29.3004 | 2350 | 0.0041406 | 0.3064 | 2250 | 69.29 | 70
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 1214 | FALSE | 7293.1721 | 5549.8668 | 3.4493 | 45 | 4.7944e-05 | 3095 | 64.0131 | 2129 | 0.004132 | 0.18594 | 2251 | 0.05 | 2016
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 26000 | FALSE | 55311.5705 | 55311.5705 | 34.3764 | 339 | 0.00010511 | 1521 | 49.7196 | 2212 | 0.0041222 | 1.3974 | 2252 | 73.15 | 63
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 9110 | FALSE | 15217.7544 | 1491.4373 | 0.92693 | 138 | 0.00014546 | 798 | 26.6167 | 2370 | 0.0040502 | 0.55893 | 2253 | 0.04 | 2097
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 94368 | TRUE | 768.9303 | 596.3821 | 0.37065 | 9 | 0.00048312 | 36 | 49.2875 | 2214 | 0.0040353 | 0.036317 | 2254 | 0.02 | 2527
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 22774 | FALSE | 5970.2453 | 1624.1247 | 1.0094 | 27 | 3.9002e-05 | 3287 | 127.212 | 1851 | 0.0040151 | 0.10841 | 2255 | 0.01 | 2610
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 12124 | FALSE | 7217.2962 | 7217.2962 | 4.4856 | 59 | 0.000304 | 126 | 21.0181 | 2436 | 0.0040119 | 0.2367 | 2256 | 0.28 | 1041
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | CB | FALSE | 5575.8129 | 2217.6155 | 1.3783 | 61 | 0.0006536 | 11 | 4.7351 | 2763 | 0.0039747 | 0.24245 | 2257 | 15.11 | 350
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 2740 | FALSE | 30939.0056 | 30939.0056 | 19.2287 | 235 | 0.00018236 | 494 | 38.193 | 2288 | 0.003969 | 0.93271 | 2258 | 0.14 | 1313
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 173014 | FALSE | 5456.0353 | 5290.5313 | 3.2881 | 43 | 0.00018414 | 479 | 19.9675 | 2449 | 0.0039357 | 0.16924 | 2259 |  | 2680
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | L373 | FALSE | 11899.5211 | 11899.5211 | 7.3956 | 93 | 5.9702e-05 | 2784 | 62.944 | 2136 | 0.0039044 | 0.36311 | 2260 | 72.86 | 65
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 1048 | FALSE | 8484.8832 | 8484.8832 | 5.2734 | 72 | 0.00016147 | 626 | 26.1474 | 2375 | 0.0039018 | 0.28093 | 2261 | 0.13 | 1345
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 22136 | FALSE | 8542.0356 | 2842.9957 | 1.7669 | 59 | 4.541e-05 | 3155 | 51.6014 | 2204 | 0.0038829 | 0.22909 | 2262 | 0.01 | 2587
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 552724 | FALSE | 23613.9534 | 2363.8176 | 1.4691 | 77 | 7.2387e-05 | 2405 | 63.51 | 2130 | 0.0038689 | 0.29791 | 2263 |  | 3158
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 106534 | FALSE | 4199.7803 | 1949.2483 | 1.2115 | 38 | 0.00024793 | 223 | 15.6992 | 2522 | 0.0038425 | 0.14601 | 2264 |  | 3012
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 18396 | TRUE | 1851.7327 | 293.2889 | 0.18228 | 16 | 3.5702e-05 | 3339 | 53.4957 | 2191 | 0.0038298 | 0.061277 | 2265 | 4.8 | 506
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 9092 | TRUE | 15725.9351 | 255.1238 | 0.15856 | 113 | 0.0001025 | 1589 | 29.6083 | 2349 | 0.0038237 | 0.43208 | 2266 | 1.99 | 627
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 953336 | FALSE | 19079.6136 | 19079.6136 | 11.8581 | 132 | 9.944e-05 | 1658 | 31.4057 | 2336 | 0.0038168 | 0.50381 | 2267 |  | 2724
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 60120 | FALSE | 6993.663 | 6993.663 | 4.3466 | 42 | 0.0001694 | 567 | 23.8386 | 2403 | 0.0038109 | 0.16006 | 2268 | 27.45 | 257
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 4016 | FALSE | 20664.9565 | 3776.8409 | 2.3473 | 59 | 4.6142e-05 | 3134 | 98.5723 | 1963 | 0.0038045 | 0.22447 | 2269 | 0.01 | 2621
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 50486 | FALSE | 18786.575 | 18786.575 | 11.6759 | 163 | 0.00010932 | 1425 | 43.079 | 2261 | 0.0037623 | 0.61325 | 2270 | 86.95 | 38
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 1222 | FALSE | 27771.0153 | 27771.0153 | 17.2598 | 218 | 0.0001881 | 453 | 22.6532 | 2414 | 0.0037571 | 0.81905 | 2271 | 105.89 | 18
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 53477 | FALSE | 3295.7871 | 3295.7871 | 2.0483 | 21 | 0.00016065 | 635 | 22.7228 | 2413 | 0.0037529 | 0.078812 | 2272 | 34.99 | 215
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | CB | FALSE | 5699.8132 | 4772.4685 | 2.9661 | 49 | 0.00014009 | 868 | 39.048 | 2283 | 0.0037209 | 0.18233 | 2273 | 0.11 | 1423
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 98606 | TRUE | 13179.7667 | 138.4782 | 0.086065 | 88 | 8.8531e-05 | 1972 | 91.908 | 1993 | 0.0037138 | 0.32681 | 2274 |  | 2931
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 13597 | TRUE | 751.816 | 751.816 | 0.46726 | 6 | 0.00014116 | 850 | 23.8355 | 2404 | 0.0037122 | 0.022273 | 2275 | 8.42 | 427
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | P304 | FALSE | 9851.3779 | 8440.4652 | 5.2458 | 47 | 9.3563e-05 | 1809 | 31.6902 | 2333 | 0.0037077 | 0.17426 | 2276 | 0.09 | 1556
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 9042 | FALSE | 5080.7921 | 5080.7921 | 3.1577 | 31 | 4.1887e-05 | 3227 | 82.8476 | 2036 | 0.0036996 | 0.11469 | 2277 | 0.11 | 1447
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 52910 | FALSE | 5038.2048 | 3510.8305 | 2.182 | 41 | 5.3924e-05 | 2944 | 73.7782 | 2074 | 0.0036877 | 0.1512 | 2278 | 0.81 | 773
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | L3733 | FALSE | 2820.1267 | 2820.1267 | 1.7527 | 22 | 6.6103e-05 | 2585 | 57.3124 | 2169 | 0.0036798 | 0.080956 | 2279 | 42.03 | 171
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9742 | FALSE | 14685.6636 | 14685.6636 | 9.1272 | 120 | 4.1561e-05 | 3232 | 86.0041 | 2023 | 0.0036718 | 0.44061 | 2280 | 37.7 | 200
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 1268 | FALSE | 7937.7862 | 7937.7862 | 4.9334 | 46 | 4.2343e-05 | 3219 | 82.2871 | 2039 | 0.0036642 | 0.16855 | 2281 | 0.09 | 1520
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 270 | FALSE | 12312.4188 | 3397.4138 | 2.1115 | 101 | 2.7315e-05 | 3467 | 46.9819 | 2234 | 0.0036568 | 0.36934 | 2282 | 0.04 | 2120
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 383092 | TRUE | 613.1926 | 613.1926 | 0.3811 | 5 | 0.00016062 | 636 | 14.3241 | 2544 | 0.0036345 | 0.018173 | 2283 | 0.2 | 1163
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 413916 | FALSE | 6367.8068 | 2275.8898 | 1.4145 | 24 | 2.8421e-05 | 3448 | 60.5803 | 2151 | 0.0036248 | 0.086994 | 2284 |  | 3529
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 338878 | FALSE | 7522.3054 | 3300.0012 | 2.051 | 23 | 6.6373e-05 | 2579 | 72.1128 | 2083 | 0.0036203 | 0.083266 | 2285 |  | 3067
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 524 | FALSE | 10078.6837 | 10078.6837 | 6.2639 | 76 | 0.00026116 | 193 | 18.5187 | 2467 | 0.0036171 | 0.2749 | 2286 | 109.05 | 15
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | CB | FALSE | 19272.7585 | 4335.2228 | 2.6944 | 149 | 0.00011557 | 1285 | 29.7426 | 2348 | 0.0036086 | 0.53768 | 2287 | 1.01 | 729
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 1290 | FALSE | 20913.8819 | 6586.7468 | 4.0937 | 126 | 8.6173e-05 | 2030 | 27.953 | 2362 | 0.0035797 | 0.45104 | 2288 | 0.02 | 2529
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | CB | FALSE | 35929.6836 | 35929.6836 | 22.3304 | 271 | 0.00017817 | 517 | 43.307 | 2257 | 0.0035789 | 0.96987 | 2289 | 173.81 | 3
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 461338 | FALSE | 2872.7742 | 2872.7742 | 1.7854 | 24 | 9.4013e-05 | 1793 | 40.8144 | 2273 | 0.0035591 | 0.085418 | 2290 |  | 2814
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | CB | FALSE | 3780.8041 | 1415.7705 | 0.87991 | 32 | 0.00022566 | 302 | 20.6051 | 2441 | 0.0035509 | 0.11363 | 2291 | 2.79 | 582
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 949522 | TRUE | 726.8328 | 708.2171 | 0.44016 | 2 | 0.00014682 | 775 | 72.2883 | 2082 | 0.0035464 | 0.0070929 | 2292 |  | 3609
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 13444 | FALSE | 27386.8447 | 27386.8447 | 17.021 | 221 | 7.9645e-05 | 2218 | 41.9022 | 2268 | 0.0035258 | 0.77919 | 2293 | 73.64 | 59
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | XR162 | TRUE | 14645.8548 | 989.1765 | 0.61478 | 122 | 5.6508e-05 | 2874 | 50.8473 | 2208 | 0.0035232 | 0.42983 | 2294 | 0.05 | 1985
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 246084 | TRUE | 830.435 | 385.2443 | 0.23943 | 7 | 7.141e-05 | 2435 | 49.9181 | 2211 | 0.0035033 | 0.024523 | 2295 |  | 3377
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10728 | FALSE | 16852.1183 | 16852.1183 | 10.4737 | 134 | 0.00034915 | 91 | 6.6304 | 2693 | 0.0034865 | 0.46719 | 2296 | 1.09 | 717
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 63124 | FALSE | 9481.8427 | 9481.8427 | 5.893 | 65 | 0.00021667 | 333 | 31.8764 | 2329 | 0.0034764 | 0.22596 | 2297 | 31.64 | 228
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | CB | FALSE | 2376.1029 | 2376.1029 | 1.4768 | 18 | 0.00021932 | 326 | 147.9963 | 1784 | 0.0034725 | 0.062504 | 2298 | 0.24 | 1098
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 1374 | FALSE | 13460.5941 | 12470.1527 | 7.7503 | 117 | 0.0001756 | 523 | 21.2592 | 2433 | 0.0034694 | 0.40592 | 2299 | 0.12 | 1408
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 203126 | TRUE | 10848.7001 | 107.4611 | 0.066788 | 58 | 6.8097e-05 | 2533 | 54.2531 | 2186 | 0.0034419 | 0.19963 | 2300 |  | 3261
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 37300 | FALSE | 11208.5924 | 11208.5924 | 6.9662 | 41 | 9.1788e-05 | 1851 | 39.4946 | 2278 | 0.0034152 | 0.14002 | 2301 | 37.82 | 198
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 54932 | FALSE | 7042.6654 | 7042.6654 | 4.377 | 46 | 5.4607e-05 | 2930 | 80.6481 | 2045 | 0.0034144 | 0.15706 | 2302 | 25.23 | 272
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 741980 | FALSE | 15211.0337 | 9241.1429 | 5.7434 | 81 | 0.00018104 | 504 | 20.6165 | 2440 | 0.0034064 | 0.27592 | 2303 |  | 2729
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 464 | FALSE | 13038.4156 | 3443.5911 | 2.1402 | 103 | 8.8656e-05 | 1965 | 37.0346 | 2297 | 0.0034005 | 0.35026 | 2304 | 0.04 | 2168
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 31304 | FALSE | 34880.3162 | 34880.3162 | 21.6783 | 119 | 0.00010968 | 1417 | 25.8228 | 2381 | 0.0033857 | 0.40289 | 2305 | 0.23 | 1121
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 792628 | TRUE | 1482.8091 | 365.6177 | 0.22723 | 13 | 7.1975e-05 | 2420 | 145.9054 | 1789 | 0.0033779 | 0.043913 | 2306 |  | 3408
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | P146 | FALSE | 5911.5651 | 5843.5425 | 3.6318 | 36 | 0.00010288 | 1572 | 24.7391 | 2392 | 0.0033674 | 0.12123 | 2307 | 0.05 | 1925
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 304 | TRUE | 74.6067 | 74.6067 | 0.046368 | 2 | 0.00013842 | 890 | 24.2406 | 2399 | 0.0033555 | 0.006711 | 2308 | 0.18 | 1213
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 663641 | FALSE | 1909.334 | 1173.5613 | 0.72937 | 13 | 0.00014217 | 836 | 35.4244 | 2307 | 0.0033545 | 0.043609 | 2309 |  | 3093
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 9230 | FALSE | 5065.9524 | 4064.6381 | 2.5262 | 41 | 0.00012174 | 1152 | 32.1288 | 2327 | 0.0033425 | 0.13704 | 2310 | 0.04 | 2191
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 336664 | FALSE | 2515.571 | 1158.7417 | 0.72016 | 16 | 6.759e-05 | 2546 | 46.5783 | 2238 | 0.0033324 | 0.053319 | 2311 |  | 3098
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 477890 | FALSE | 4846.0499 | 1726.9794 | 1.0733 | 35 | 9.2097e-05 | 1839 | 48.2183 | 2219 | 0.0033264 | 0.11642 | 2312 |  | 2995
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 4222 | FALSE | 26146.3036 | 4245.3884 | 2.6385 | 87 | 3.1604e-05 | 3407 | 230.387 | 1585 | 0.0033258 | 0.28934 | 2313 | 0.02 | 2510
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 53130 | FALSE | 22213.2961 | 22213.2961 | 13.8057 | 168 | 4.8271e-05 | 3088 | 94.8297 | 1982 | 0.0033207 | 0.55788 | 2314 | 57.28 | 97
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 806392 | FALSE | 8744.0051 | 5446.9277 | 3.3853 | 79 | 6.382e-05 | 2652 | 38.9119 | 2286 | 0.0033155 | 0.26192 | 2315 |  | 2691
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 476 | FALSE | 24463.8896 | 4825.127 | 2.9988 | 97 | 4.5962e-05 | 3139 | 73.5453 | 2078 | 0.0032902 | 0.31915 | 2316 | 0.02 | 2460
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 258688 | FALSE | 5700.7117 | 1727.2951 | 1.0735 | 17 | 1.3021e-05 | 3601 | 51.8497 | 2202 | 0.0032882 | 0.0559 | 2317 |  | 3463
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 183860 | FALSE | 12288.1398 | 7942.1796 | 4.9361 | 92 | 0.00018091 | 505 | 20.123 | 2446 | 0.0032843 | 0.30215 | 2318 |  | 2779
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 52088 | FALSE | 3986.2342 | 3986.2342 | 2.4775 | 28 | 0.00019225 | 433 | 17.8963 | 2482 | 0.0032783 | 0.091793 | 2319 | 0.06 | 1856
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 1482 | FALSE | 19365.2645 | 19365.2645 | 12.0356 | 43 | 0.0001494 | 744 | 53.6934 | 2189 | 0.0032735 | 0.14076 | 2320 | 0.01 | 2603
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 97574 | FALSE | 8779.1351 | 5743.5714 | 3.5697 | 60 | 8.4627e-05 | 2073 | 42.7148 | 2264 | 0.0032547 | 0.19528 | 2321 |  | 3327
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | X06 | TRUE | 20798.4951 | 651.9578 | 0.40519 | 40 | 5.1105e-05 | 3012 | 121.2254 | 1866 | 0.0032533 | 0.13013 | 2322 | 0.03 | 2295
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 5178 | FALSE | 11550.9267 | 11550.9267 | 7.1789 | 84 | 0.0001826 | 491 | 17.8913 | 2483 | 0.0032408 | 0.27223 | 2323 | 0.58 | 856
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 2762 | FALSE | 17774.3074 | 15060.1277 | 9.3599 | 138 | 9.1063e-05 | 1879 | 28.3252 | 2356 | 0.0032245 | 0.44498 | 2324 | 0.08 | 1622
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 9032 | FALSE | 7741.5059 | 3452.7748 | 2.1459 | 72 | 0.00021411 | 342 | 20.493 | 2443 | 0.0032245 | 0.23216 | 2325 | 0.08 | 1581
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | CB | FALSE | 46476.8109 | 7426.5465 | 4.6156 | 214 | 5.8116e-05 | 2833 | 45.5892 | 2241 | 0.003207 | 0.6863 | 2326 | 0.02 | 2421
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 733408 | FALSE | 5546.1563 | 5546.1563 | 3.447 | 45 | 0.00017527 | 527 | 18.0229 | 2479 | 0.0032065 | 0.14429 | 2327 |  | 2660
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 786782 | FALSE | 5173.0207 | 3549.2326 | 2.2059 | 46 | 0.00014664 | 779 | 8.3437 | 2661 | 0.0032053 | 0.14745 | 2328 |  | 2734
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 1658 | FALSE | 7306.3402 | 7306.3402 | 4.5409 | 25 | 0.0001398 | 870 | 46.6629 | 2236 | 0.0031839 | 0.079597 | 2329 | 0.02 | 2471
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 7080 | FALSE | 17026.2434 | 17026.2434 | 10.5819 | 67 | 5.6266e-05 | 2881 | 33.4031 | 2317 | 0.0031698 | 0.21238 | 2330 | 0 | 2646
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 716954 | FALSE | 18261.1322 | 11115.6995 | 6.9085 | 97 | 0.00020479 | 383 | 15.7424 | 2521 | 0.0031691 | 0.30741 | 2331 |  | 3112
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 44150 | FALSE | 5746.8082 | 5746.8082 | 3.5717 | 13 | 9.8025e-05 | 1689 | 54.8965 | 2182 | 0.0031685 | 0.04119 | 2332 | 0 | 2641
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 3583 | FALSE | 4565.0094 | 4565.0094 | 2.8372 | 38 | 0.00013592 | 920 | 25.7125 | 2385 | 0.0031615 | 0.12014 | 2333 | 0.78 | 781
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | CB | FALSE | 6922.9717 | 6922.9717 | 4.3027 | 57 | 0.00036472 | 81 | 15.0767 | 2531 | 0.0031502 | 0.17956 | 2334 | 10.19 | 401
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 37210 | FALSE | 9746.716 | 9746.716 | 6.0576 | 65 | 0.00021978 | 324 | 16.5241 | 2509 | 0.0031442 | 0.20437 | 2335 | 0.45 | 916
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | CB | FALSE | 6249.0561 | 1615.0564 | 1.0038 | 45 | 3.6368e-05 | 3327 | 61.4823 | 2144 | 0.003121 | 0.14045 | 2336 | 0.03 | 2317
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 1258 | TRUE | 7855.298 | 501.9247 | 0.31195 | 65 | 3.9619e-05 | 3275 | 27.811 | 2365 | 0.0031184 | 0.2027 | 2337 |  | 2726
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | CB | FALSE | 15128.6127 | 8212.888 | 5.1043 | 106 | 2.9958e-05 | 3427 | 117.1254 | 1887 | 0.0031059 | 0.32923 | 2338 | 0.03 | 2246
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | CB | TRUE | 460.8364 | 460.8364 | 0.28641 | 6 | 0.00063458 | 14 | 4.0266 | 2776 | 0.0031037 | 0.018622 | 2339 | 7.35 | 448
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 457900 | FALSE | 26252.3118 | 19380.7293 | 12.0452 | 208 | 0.00047135 | 40 | 18.1285 | 2474 | 0.0030985 | 0.64448 | 2340 |  | 2650
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 1306 | TRUE | 6582.7615 | 393.5916 | 0.24462 | 55 | 0.00018261 | 490 | 20.3553 | 2444 | 0.0030939 | 0.17016 | 2341 | 9.44 | 409
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 2476 | FALSE | 14000.8931 | 13050.7122 | 8.1111 | 75 | 7.3608e-05 | 2378 | 31.4311 | 2335 | 0.0030704 | 0.23028 | 2342 | 0.03 | 2379
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | CB | FALSE | 11764.5735 | 5407.5285 | 3.3608 | 91 | 5.0448e-05 | 3027 | 32.7091 | 2324 | 0.0030523 | 0.27776 | 2343 | 0.09 | 1557
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 555034 | FALSE | 4077.2208 | 2404.9179 | 1.4947 | 8 | 0.00031076 | 117 | 13.913 | 2553 | 0.0030461 | 0.024368 | 2344 |  | 3508
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 8952 | FALSE | 10739.4056 | 10739.4056 | 6.6746 | 82 | 0.0001072 | 1467 | 39.4973 | 2277 | 0.0030386 | 0.24916 | 2345 | 9.23 | 411
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 10424 | FALSE | 11629.4934 | 9151.9906 | 5.688 | 87 | 0.00013475 | 931 | 22.367 | 2420 | 0.0030267 | 0.26332 | 2346 | 0.25 | 1072
2267 | ELK 11011298 | 42981101 | ELK 1101 | 1298 | FALSE | 25951.4505 | 19969.5788 | 12.4112 | 119 | 7.3623e-05 | 2376 | 48.6421 | 2217 | 0.0030233 | 0.35978 | 2347 | 0.03 | 2376
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 9210 | FALSE | 36192.6146 | 36192.6146 | 22.4939 | 124 | 4.5003e-05 | 3160 | 67.0376 | 2108 | 0.0030209 | 0.37459 | 2348 | 0.31 | 1004
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | L1697 | FALSE | 9283.5435 | 9283.5435 | 5.7698 | 70 | 8.7849e-05 | 1988 | 45.9015 | 2240 | 0.0030208 | 0.21145 | 2349 | 2.74 | 585
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 51744 | FALSE | 2867.8226 | 2099.9047 | 1.3051 | 25 | 0.00013923 | 883 | 25.8185 | 2382 | 0.0030149 | 0.075372 | 2350 | 0.2 | 1162
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 616 | TRUE | 12968.0682 | 798.8754 | 0.4965 | 103 | 0.00011091 | 1393 | 20.2831 | 2445 | 0.0030112 | 0.31016 | 2351 | 0.3 | 1020
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | LB50 | FALSE | 18304.0568 | 18130.2581 | 11.268 | 65 | 0.00012813 | 1046 | 26.2606 | 2373 | 0.0029902 | 0.19436 | 2352 | 0.21 | 1142
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | CB | FALSE | 26145.2982 | 26145.2982 | 16.2494 | 187 | 8.1435e-05 | 2170 | 64.1413 | 2128 | 0.0029901 | 0.55914 | 2353 | 197.3 | 2
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 167792 | FALSE | 7540.5809 | 7540.5809 | 4.6865 | 48 | 0.00016417 | 599 | 22.3539 | 2421 | 0.0029842 | 0.14324 | 2354 | 27.41 | 258
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 34426 | FALSE | 11062.821 | 7591.2944 | 4.718 | 81 | 0.0001041 | 1549 | 18.642 | 2465 | 0.0029697 | 0.24054 | 2355 | 0.2 | 1161
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | LA64 | FALSE | 20425.5788 | 20425.5788 | 12.6946 | 152 | 0.00024137 | 243 | 12.4217 | 2580 | 0.0029684 | 0.4512 | 2356 | 0.94 | 741
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 8091 | FALSE | 9678.478 | 9678.478 | 6.0152 | 69 | 0.00018296 | 489 | 17.2834 | 2497 | 0.0029648 | 0.20457 | 2357 | 0.38 | 961
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 12758 | FALSE | 9624.9945 | 9624.9945 | 5.982 | 70 | 0.00033735 | 98 | 10.9337 | 2611 | 0.002947 | 0.20629 | 2358 | 6.96 | 456
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 5066 | FALSE | 22120.764 | 22120.764 | 13.7481 | 121 | 0.00018064 | 508 | 16.1765 | 2514 | 0.0029066 | 0.35169 | 2359 | 0.48 | 902
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 602 | FALSE | 38446.6728 | 26032.3379 | 16.1792 | 115 | 5.7752e-05 | 2842 | 48.2008 | 2220 | 0.0028981 | 0.33328 | 2360 | 0.08 | 1633
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 1384 | FALSE | 14709.9253 | 14709.9253 | 9.1423 | 106 | 0.00030207 | 128 | 17.1106 | 2502 | 0.0028857 | 0.30589 | 2361 | 0.08 | 1664
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 10714 | FALSE | 31415.1888 | 22795.5157 | 14.1675 | 212 | 8.9964e-05 | 1915 | 34.8828 | 2308 | 0.002884 | 0.61141 | 2362 | 0.2 | 1158
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | CB | FALSE | 17856.3948 | 7352.5883 | 4.5697 | 146 | 2.5847e-05 | 3489 | 57.0849 | 2170 | 0.0028615 | 0.41777 | 2363 | 0.1 | 1489
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 147198 | FALSE | 3096.6231 | 2173.9439 | 1.3511 | 24 | 0.00013298 | 958 | 27.8556 | 2363 | 0.0028527 | 0.068464 | 2364 |  | 3161
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 5206 | FALSE | 11520.3774 | 11520.3774 | 7.16 | 78 | 0.00028525 | 147 | 13.4764 | 2563 | 0.0028387 | 0.22141 | 2365 | 16.08 | 342
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 202 | FALSE | 8481.1425 | 8481.1425 | 5.2711 | 55 | 0.00023689 | 257 | 9.574 | 2632 | 0.0028293 | 0.15561 | 2366 | 77.47 | 54
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 2624 | FALSE | 30794.7642 | 29790.8638 | 18.5151 | 148 | 5.858e-05 | 2819 | 45.0109 | 2246 | 0.0028273 | 0.41844 | 2367 | 0.19 | 1182
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 10590 | FALSE | 26358.3376 | 26358.3376 | 16.3818 | 199 | 7.2916e-05 | 2395 | 56.6573 | 2172 | 0.0028226 | 0.56169 | 2368 | 0.28 | 1046
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | CB | FALSE | 14569.4696 | 14569.4696 | 9.055 | 110 | 0.00015914 | 650 | 17.5722 | 2489 | 0.0028161 | 0.30977 | 2369 | 97.72 | 22
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | LC14 | FALSE | 17935.8798 | 15879.1839 | 9.869 | 137 | 0.0001215 | 1156 | 25.9229 | 2378 | 0.0028157 | 0.38575 | 2370 | 0.15 | 1303
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 2046 | FALSE | 14788.0543 | 14724.19 | 9.1511 | 57 | 2.9135e-05 | 3438 | 49.5192 | 2213 | 0.0028141 | 0.1604 | 2371 | 3.25 | 552
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 84480 | FALSE | 7615.7819 | 7615.7819 | 4.7332 | 50 | 0.00012015 | 1184 | 18.1285 | 2473 | 0.0028064 | 0.14032 | 2372 | 43.55 | 166
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | V58 | FALSE | 3619.1201 | 1838.4445 | 1.1426 | 25 | 3.6836e-05 | 3317 | 42.8997 | 2262 | 0.0027879 | 0.069698 | 2373 | 0.25 | 1081
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 2436 | FALSE | 8535.8961 | 8535.8961 | 5.3051 | 19 | 3.5783e-05 | 3338 | 86.4703 | 2020 | 0.0027598 | 0.052436 | 2374 | 0.06 | 1878
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 69550 | FALSE | 28222.9499 | 28222.9499 | 17.5407 | 188 | 0.00019115 | 436 | 15.1137 | 2529 | 0.0027545 | 0.51784 | 2375 | 0.88 | 753
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 294 | TRUE | 13929.6308 | 0 | 0 | 66 | 3.7559e-05 | 3303 | 12.2945 | 2582 | 0.002743 | 0.18104 | 2376 | 1.46 | 672
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 7273 | FALSE | 10648.4179 | 10648.4179 | 6.618 | 38 | 0.00010776 | 1456 | 24.4514 | 2395 | 0.0027408 | 0.10415 | 2377 |  | 3023
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 2637 | FALSE | 6500.6025 | 6500.6025 | 4.0402 | 28 | 7.3634e-05 | 2375 | 33.1621 | 2319 | 0.0027385 | 0.076678 | 2378 | 0.06 | 1783
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 10912 | FALSE | 7824.9032 | 7824.9032 | 4.8632 | 54 | 0.00030255 | 127 | 14.5938 | 2539 | 0.0027343 | 0.14765 | 2379 | 17.3 | 333
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | CB | TRUE | 830.5012 | 830.5012 | 0.51616 | 7 | 2.8327e-05 | 3450 | 82.5251 | 2038 | 0.0027213 | 0.019049 | 2380 | 0 | 2645
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 12824 | FALSE | 19725.4463 | 1410.0846 | 0.87637 | 97 | 5.8888e-05 | 2811 | 61.7022 | 2142 | 0.0027199 | 0.26383 | 2381 | 0.19 | 1178
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 4048 | FALSE | 45554.4794 | 29209.8997 | 18.1541 | 157 | 5.5174e-05 | 2907 | 56.2888 | 2174 | 0.0027194 | 0.42694 | 2382 | 0.07 | 1678
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 2206 | FALSE | 27876.5924 | 6659.3031 | 4.1388 | 227 | 0.00050121 | 31 | 12.7346 | 2573 | 0.0027 | 0.61291 | 2383 |  | 2664
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 91926 | FALSE | 17004.3113 | 10358.7223 | 6.438 | 48 | 0.00024845 | 221 | 9.7992 | 2628 | 0.0026935 | 0.12929 | 2384 | 0.04 | 2095
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 3010 | TRUE | 14671.2868 | 569.5009 | 0.35395 | 106 | 8.4289e-05 | 2082 | 23.6594 | 2409 | 0.0026922 | 0.28537 | 2385 | 0.03 | 2262
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 1888 | FALSE | 30440.0056 | 30440.0056 | 18.9186 | 231 | 9.5589e-05 | 1738 | 52.6578 | 2198 | 0.0026855 | 0.62036 | 2386 | 136.25 | 4
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10298 | FALSE | 21540.3253 | 17635.9746 | 10.9608 | 138 | 0.00011425 | 1313 | 23.0219 | 2412 | 0.0026825 | 0.37018 | 2387 | 0.67 | 817
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 10214 | FALSE | 22409.5851 | 22409.5851 | 13.9276 | 149 | 0.00015 | 735 | 18.095 | 2476 | 0.0026769 | 0.39885 | 2388 | 59.12 | 90
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 36674 | FALSE | 15144.1466 | 15144.1466 | 9.4121 | 125 | 0.00010056 | 1635 | 28.0218 | 2361 | 0.0026639 | 0.33299 | 2389 | 88.72 | 34
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 29362 | FALSE | 18377.6602 | 12371.5145 | 7.6889 | 74 | 0.00019406 | 424 | 17.4096 | 2493 | 0.0026559 | 0.19654 | 2390 | 0.15 | 1302
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 37286 | FALSE | 5924.4605 | 4150.8287 | 2.5798 | 25 | 7.3809e-05 | 2365 | 26.9712 | 2368 | 0.0026543 | 0.066357 | 2391 | 0.03 | 2256
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 10207 | FALSE | 5731.5328 | 5731.5328 | 3.5622 | 38 | 5.2727e-05 | 2978 | 53.21 | 2193 | 0.0026426 | 0.10042 | 2392 | 4.55 | 517
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 437582 | FALSE | 3785.2974 | 1172.6243 | 0.72879 | 31 | 9.3714e-05 | 1803 | 36.8732 | 2299 | 0.0026389 | 0.081807 | 2393 |  | 2902
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | MR337 | FALSE | 30458.1324 | 14629.5479 | 9.0923 | 193 | 2.0736e-05 | 3536 | 31.7021 | 2331 | 0.0026206 | 0.50578 | 2394 |  | 2704
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 95690 | FALSE | 6226.9882 | 6226.9882 | 3.8701 | 58 | 0.00043813 | 55 | 3.7552 | 2782 | 0.0026164 | 0.15175 | 2395 | 0.66 | 821
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 450582 | FALSE | 6805.9936 | 4807.846 | 2.9881 | 50 | 8.4551e-05 | 2074 | 22.3998 | 2418 | 0.0026097 | 0.13049 | 2396 | 0.06 | 1776
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | CB | FALSE | 8801.7452 | 2701.0978 | 1.6787 | 82 | 0.00031315 | 115 | 15.1124 | 2530 | 0.0026094 | 0.21397 | 2397 | 0.1 | 1502
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | CB | FALSE | 7486.7827 | 7486.7827 | 4.6531 | 45 | 0.00027461 | 168 | 11.6886 | 2594 | 0.0025849 | 0.11632 | 2398 | 26.9 | 264
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | CB | FALSE | 8911.8997 | 7279.8498 | 4.5245 | 36 | 3.3044e-05 | 3385 | 43.2592 | 2258 | 0.0025799 | 0.092875 | 2399 | 0.04 | 2119
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | CB | TRUE | 2118.6497 | 279.4297 | 0.17367 | 22 | 6.8306e-05 | 2527 | 21.6949 | 2429 | 0.0025794 | 0.056746 | 2400 | 0.44 | 921
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 173934 | FALSE | 17611.7153 | 17611.7153 | 10.9458 | 125 | 0.00011937 | 1199 | 28.2053 | 2358 | 0.0025705 | 0.32131 | 2401 |  | 2727
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | V66 | FALSE | 26099.4541 | 5840.07 | 3.6296 | 151 | 5.4939e-05 | 2915 | 48.8236 | 2216 | 0.0025703 | 0.38811 | 2402 | 0.03 | 2264
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | CB | TRUE | 9964.9315 | 415.9182 | 0.25849 | 45 | 5.4044e-05 | 2942 | 29.9475 | 2345 | 0.0025606 | 0.11523 | 2403 | 0.02 | 2456
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 2784 | FALSE | 24673.5503 | 23592.2379 | 14.6627 | 202 | 0.0002125 | 349 | 16.1455 | 2515 | 0.0025529 | 0.51568 | 2404 | 21.1 | 301
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 247511 | FALSE | 3219.7109 | 1938.4111 | 1.2047 | 26 | 5.8722e-05 | 2816 | 39.41 | 2279 | 0.0025357 | 0.065929 | 2405 |  | 2844
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | XR374 | TRUE | 4853.8508 | 763.9032 | 0.47477 | 29 | 5.5868e-05 | 2893 | 52.1032 | 2201 | 0.002531 | 0.073398 | 2406 | 0.04 | 2155
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 1520 | FALSE | 14435.9237 | 14435.9237 | 8.972 | 69 | 0.0002442 | 234 | 18.3262 | 2471 | 0.002519 | 0.17381 | 2407 | 0.04 | 2139
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 424048 | FALSE | 1501.8611 | 1068.5882 | 0.66413 | 12 | 6.0749e-05 | 2756 | 33.0472 | 2323 | 0.002517 | 0.030204 | 2408 |  | 3298
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | CB | FALSE | 10068.8846 | 2571.5148 | 1.5982 | 80 | 4.1301e-05 | 3240 | 78.3943 | 2057 | 0.0025158 | 0.20127 | 2409 | 0.42 | 929
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 477 | FALSE | 2946.6356 | 2946.6356 | 1.8313 | 25 | 0.00015508 | 692 | 16.2294 | 2513 | 0.002515 | 0.062875 | 2410 | 3.59 | 539
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 823548 | FALSE | 31748.5399 | 31748.5399 | 19.7318 | 231 | 6.0776e-05 | 2755 | 41.9518 | 2266 | 0.0025098 | 0.57976 | 2411 |  | 2944
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 19742 | FALSE | 12071.9353 | 10549.7356 | 6.5567 | 92 | 0.00023207 | 278 | 8.0743 | 2669 | 0.0025093 | 0.23086 | 2412 | 0.09 | 1571
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 646 | FALSE | 19795.1478 | 13544.3225 | 8.4179 | 154 | 0.00011949 | 1196 | 18.0896 | 2477 | 0.0025033 | 0.3855 | 2413 | 28.71 | 246
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 160 | FALSE | 10761.0163 | 4469.2889 | 2.7777 | 77 | 9.2493e-05 | 1831 | 17.9801 | 2481 | 0.0024952 | 0.19213 | 2414 | 0.04 | 2105
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | XR028 | FALSE | 16732.9664 | 1226.5796 | 0.76232 | 134 | 6.205e-05 | 2717 | 31.865 | 2330 | 0.0024946 | 0.33428 | 2415 | 0.03 | 2231
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | CB | FALSE | 27553.0792 | 12591.5795 | 7.8257 | 180 | 4.197e-05 | 3225 | 36.6519 | 2300 | 0.0024688 | 0.44438 | 2416 | 0.03 | 2341
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 45268 | FALSE | 12405.1563 | 4400.5557 | 2.735 | 112 | 8.3437e-05 | 2119 | 27.4918 | 2366 | 0.0024458 | 0.27393 | 2417 | 0.06 | 1780
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 914376 | TRUE | 11215.1853 | 862.0577 | 0.53577 | 93 | 8.1801e-05 | 2159 | 28.2406 | 2357 | 0.0024267 | 0.22569 | 2418 | 0.04 | 2227
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 478699 | FALSE | 1763.8687 | 1328.3865 | 0.8256 | 14 | 8.2786e-05 | 2136 | 37.3598 | 2294 | 0.0024262 | 0.033967 | 2419 |  | 3466
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 2022 | FALSE | 25888.9554 | 25888.9554 | 16.0901 | 207 | 0.0001628 | 614 | 14.0752 | 2547 | 0.0024209 | 0.50113 | 2420 | 126.01 | 10
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 772210 | FALSE | 5622.5297 | 1329.7793 | 0.82646 | 32 | 0.0003009 | 129 | 8.4673 | 2658 | 0.0023979 | 0.076733 | 2421 |  | 2876
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | CB | FALSE | 14897.5939 | 14897.5939 | 9.2589 | 116 | 0.00026838 | 176 | 10.7214 | 2615 | 0.0023893 | 0.27716 | 2422 | 0.08 | 1670
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | CB | FALSE | 7077.2532 | 2179.3543 | 1.3545 | 22 | 7.8614e-05 | 2246 | 23.8165 | 2407 | 0.0023847 | 0.052462 | 2423 | 0.16 | 1259
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 415382 | TRUE | 1920.3588 | 97.0433 | 0.060313 | 8 | 1.7728e-05 | 3562 | 59.385 | 2159 | 0.0023723 | 0.018978 | 2424 |  | 3205
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 76088 | FALSE | 17715.9929 | 17715.9929 | 11.0106 | 124 | 8.4526e-05 | 2076 | 27.0945 | 2367 | 0.0023715 | 0.29407 | 2425 | 0.08 | 1589
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 36888 | TRUE | 977.9121 | 977.9121 | 0.60778 | 7 | 0.00011804 | 1228 | 17.0465 | 2504 | 0.0023702 | 0.016592 | 2426 | 28.15 | 253
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 647842 | TRUE | 1016.9284 | 187.7325 | 0.11668 | 6 | 4.4258e-05 | 3184 | 47.9751 | 2222 | 0.0023697 | 0.014218 | 2427 |  | 2958
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 3970 | FALSE | 11750.7224 | 11750.7224 | 7.3031 | 87 | 0.00015476 | 697 | 11.2679 | 2601 | 0.0023638 | 0.20565 | 2428 | 0.85 | 765
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 1236 | FALSE | 6557.8129 | 5809.1133 | 3.6104 | 34 | 0.00011532 | 1292 | 31.2219 | 2338 | 0.0023633 | 0.080354 | 2429 | 0.06 | 1825
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 23190 | FALSE | 5918.813 | 5918.813 | 3.6786 | 45 | 0.00031007 | 118 | 11.1572 | 2604 | 0.0023536 | 0.10591 | 2430 | 0.09 | 1566
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 10270 | FALSE | 6119.8962 | 6119.8962 | 3.8035 | 39 | 3.2245e-05 | 3398 | 67.2012 | 2107 | 0.002349 | 0.091612 | 2431 | 0.07 | 1697
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 4421 | TRUE | 585.3593 | 585.3593 | 0.3638 | 5 | 8.4837e-05 | 2068 | 28.5837 | 2354 | 0.0023217 | 0.011609 | 2432 | 18.46 | 321
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | V74 | FALSE | 8209.0598 | 6901.1378 | 4.2891 | 61 | 4.7405e-05 | 3107 | 40.6895 | 2274 | 0.0023119 | 0.14103 | 2433 | 0.09 | 1509
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | CB | FALSE | 7725.5743 | 3167.0883 | 1.9684 | 66 | 5.6002e-05 | 2888 | 47.8787 | 2223 | 0.0022934 | 0.15136 | 2434 | 0.04 | 2137
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 10720 | FALSE | 7578.3102 | 7578.3102 | 4.71 | 44 | 0.00059263 | 19 | 5.4692 | 2730 | 0.002283 | 0.10045 | 2435 | 61.7 | 86
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | V88 | FALSE | 5002.7309 | 1732.6065 | 1.0768 | 48 | 3.4227e-05 | 3365 | 36.539 | 2301 | 0.002278 | 0.10934 | 2436 | 0.6 | 853
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 32180 | FALSE | 4085.725 | 3970.2131 | 2.4675 | 36 | 0.0001328 | 963 | 9.9964 | 2624 | 0.0022763 | 0.081948 | 2437 | 0.25 | 1076
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 8403 | FALSE | 7867.7292 | 7867.7292 | 4.8898 | 42 | 0.00015778 | 666 | 14.7825 | 2533 | 0.0022738 | 0.095499 | 2438 | 0.41 | 941
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 1415 | FALSE | 1913.2696 | 1280.0188 | 0.79554 | 14 | 0.00015384 | 711 | 13.6482 | 2558 | 0.0022706 | 0.031789 | 2439 | 2.72 | 587
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 2090 | FALSE | 23726.1931 | 23726.1931 | 14.7459 | 183 | 0.00011006 | 1410 | 20.7182 | 2438 | 0.0022675 | 0.41496 | 2440 | 71.03 | 68
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | CB | TRUE | 19915.785 | 875.3178 | 0.54401 | 166 | 8.6265e-05 | 2028 | 19.7079 | 2452 | 0.0022645 | 0.37591 | 2441 | 3.46 | 545
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 12840 | FALSE | 6323.0478 | 6323.0478 | 3.9298 | 50 | 0.00014417 | 811 | 15.7468 | 2520 | 0.002258 | 0.1129 | 2442 | 0.4 | 948
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 49394 | FALSE | 14105.1915 | 1836.8422 | 1.1416 | 111 | 2.0592e-05 | 3538 | 59.3555 | 2160 | 0.0022509 | 0.24985 | 2443 | 0.03 | 2277
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2760 | FALSE | 4358.9956 | 4358.9956 | 2.7091 | 28 | 8.7661e-05 | 1995 | 28.0773 | 2360 | 0.0022393 | 0.062701 | 2444 | 0.65 | 826
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 2327 | FALSE | 2038.9698 | 1914.889 | 1.1901 | 20 | 0.00013326 | 953 | 15.5189 | 2523 | 0.0022381 | 0.044762 | 2445 | 0.08 | 1640
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 445166 | FALSE | 15269.7955 | 12164.2635 | 7.5601 | 71 | 5.9661e-05 | 2785 | 28.1893 | 2359 | 0.0022354 | 0.15871 | 2446 | 0.06 | 1845
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 45292 | FALSE | 17350.6047 | 17350.6047 | 10.7835 | 132 | 8.1993e-05 | 2156 | 36.0802 | 2304 | 0.002235 | 0.29501 | 2447 | 129.86 | 5
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | CB | FALSE | 2942.811 | 2690.5619 | 1.6722 | 19 | 0.00013353 | 951 | 20.0821 | 2447 | 0.0022279 | 0.042331 | 2448 | 0.05 | 2033
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 438 | FALSE | 9219.1151 | 8226.4088 | 5.1127 | 48 | 7.125e-05 | 2440 | 29.805 | 2347 | 0.0022241 | 0.10675 | 2449 | 0.05 | 2035
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 738 | FALSE | 12990.1187 | 4208.5049 | 2.6156 | 106 | 7.6101e-05 | 2304 | 26.5188 | 2371 | 0.0022159 | 0.23488 | 2450 | 0.03 | 2251
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | CB | FALSE | 3376.1921 | 3376.1921 | 2.0983 | 27 | 0.00018738 | 459 | 22.0757 | 2425 | 0.0021922 | 0.059189 | 2451 | 44.75 | 154
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 78672 | FALSE | 14393.4787 | 6078.7898 | 3.778 | 123 | 7.9821e-05 | 2211 | 9.5346 | 2635 | 0.0021883 | 0.26916 | 2452 | 0.15 | 1304
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 678 | FALSE | 3004.004 | 3004.004 | 1.867 | 17 | 0.00013325 | 954 | 26.6461 | 2369 | 0.002188 | 0.037196 | 2453 | 48.48 | 128
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 86658 | FALSE | 1081.812 | 1029.0279 | 0.63954 | 7 | 0.00024387 | 235 | 13.6494 | 2557 | 0.0021861 | 0.015303 | 2454 | 0.02 | 2563
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 1021 | FALSE | 6702.9103 | 6702.9103 | 4.1659 | 56 | 6.9851e-05 | 2478 | 34.4442 | 2311 | 0.0021716 | 0.12161 | 2455 | 8.36 | 430
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 10296 | FALSE | 23203.5804 | 23203.5804 | 14.4211 | 181 | 0.00028227 | 151 | 8.472 | 2657 | 0.0021702 | 0.3928 | 2456 | 20.94 | 303
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 987714 | FALSE | 1590.9598 | 1218.9668 | 0.75759 | 6 | 0.00013453 | 933 | 18.5736 | 2466 | 0.0021699 | 0.01302 | 2457 |  | 3580
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 2514 | FALSE | 31420.4965 | 17648.4979 | 10.9686 | 212 | 0.00019439 | 421 | 17.5789 | 2488 | 0.0021687 | 0.45975 | 2458 | 0.04 | 2164
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 508410 | FALSE | 8406.5825 | 7530.8771 | 4.6805 | 73 | 0.0002728 | 169 | 8.8564 | 2647 | 0.002162 | 0.15783 | 2459 |  | 2754
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 5074 | FALSE | 4940.828 | 2196.7079 | 1.3653 | 34 | 7.8643e-05 | 2245 | 54.9615 | 2181 | 0.0021548 | 0.073264 | 2460 | 0.03 | 2294
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 344250 | FALSE | 1668.1837 | 1299.2708 | 0.8075 | 10 | 4.8899e-05 | 3068 | 38.0392 | 2290 | 0.0021484 | 0.021484 | 2461 | 0.03 | 2252
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 355914 | FALSE | 14935.3832 | 13002.7807 | 8.0813 | 104 | 0.0002048 | 382 | 13.3148 | 2566 | 0.0021471 | 0.2233 | 2462 |  | 2817
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | W20 | FALSE | 6313.3606 | 3551.7376 | 2.2074 | 48 | 4.0736e-05 | 3252 | 28.7718 | 2351 | 0.0021357 | 0.10251 | 2463 | 0.02 | 2548
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 5020 | FALSE | 24253.1314 | 24253.1314 | 15.0734 | 185 | 0.00021261 | 348 | 14.5867 | 2540 | 0.0021265 | 0.3934 | 2464 | 82.74 | 42
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 857148 | FALSE | 3180.8041 | 1503.7135 | 0.93456 | 31 | 4.5954e-05 | 3140 | 22.3402 | 2422 | 0.0021126 | 0.065491 | 2465 |  | 3247
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 554 | TRUE | 17322.4157 | 0 | 0 | 130 | 6.9536e-05 | 2487 | 22.3741 | 2419 | 0.0021107 | 0.2744 | 2466 | 0.33 | 985
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 39216 | FALSE | 5158.2623 | 2624.8047 | 1.6313 | 41 | 0.00049128 | 32 | 7.6005 | 2675 | 0.0021 | 0.086098 | 2467 | 0.31 | 998
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 4706 | FALSE | 18429.634 | 18429.634 | 11.4541 | 138 | 8.047e-05 | 2193 | 25.0428 | 2390 | 0.0020959 | 0.28923 | 2468 | 94.56 | 27
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 6645 | FALSE | 6787.3604 | 6787.3604 | 4.2184 | 52 | 9.5316e-05 | 1753 | 25.6675 | 2386 | 0.0020868 | 0.10851 | 2469 | 54.01 | 109
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | MR332 | TRUE | 4548.7457 | 520.6629 | 0.32359 | 31 | 7.6303e-05 | 2299 | 24.407 | 2396 | 0.0020705 | 0.064186 | 2470 | 0.38 | 963
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 868170 | FALSE | 15451.7071 | 14595.2194 | 9.071 | 59 | 3.81e-05 | 3298 | 52.9097 | 2197 | 0.0020479 | 0.12083 | 2471 |  | 2853
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 3144 | FALSE | 8269.2517 | 7828.9119 | 4.8657 | 58 | 0.00015369 | 715 | 19.1385 | 2460 | 0.0020462 | 0.11868 | 2472 | 0.09 | 1549
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 839669 | TRUE | 1273.7836 | 989.219 | 0.6148 | 12 | 0.00010611 | 1492 | 23.2008 | 2411 | 0.0020383 | 0.02446 | 2473 |  | 3373
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 5096 | FALSE | 32680.7032 | 32680.7032 | 20.3112 | 232 | 0.00019642 | 411 | 13.592 | 2561 | 0.0020379 | 0.4728 | 2474 | 12.58 | 372
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | CB | FALSE | 3445.1403 | 3361.7302 | 2.0893 | 23 | 0.00019412 | 423 | 17.2869 | 2496 | 0.0020369 | 0.046849 | 2475 | 0.54 | 878
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | CB | FALSE | 3448.2579 | 2568.9228 | 1.5966 | 22 | 5.2908e-05 | 2970 | 18.4256 | 2469 | 0.0020177 | 0.044389 | 2476 | 0.05 | 1991
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | CB | FALSE | 7286.2366 | 7286.2366 | 4.5284 | 49 | 0.00021269 | 347 | 6.3725 | 2702 | 0.0020136 | 0.098667 | 2477 | 46.29 | 143
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2500 | FALSE | 3521.417 | 3521.417 | 2.1886 | 26 | 4.8353e-05 | 3083 | 44.8707 | 2248 | 0.0019811 | 0.05151 | 2478 | 0.16 | 1255
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 169700 | FALSE | 13421.5222 | 13421.5222 | 8.3415 | 63 | 7.4011e-05 | 2357 | 25.346 | 2387 | 0.001973 | 0.1243 | 2479 |  | 2693
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | CB | FALSE | 14982.4076 | 8539.83 | 5.3075 | 130 | 9.0885e-05 | 1886 | 25.7754 | 2384 | 0.0019722 | 0.25639 | 2480 | 0.62 | 843
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 134 | FALSE | 13416.4816 | 13272.5409 | 8.2489 | 99 | 9.5754e-05 | 1735 | 24.5453 | 2393 | 0.0019671 | 0.19475 | 2481 | 0.04 | 2145
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 995672 | FALSE | 9263.8953 | 5928.6387 | 3.6847 | 79 | 0.00018258 | 492 | 13.4013 | 2564 | 0.0019604 | 0.15487 | 2482 | 0.08 | 1645
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 99096 | FALSE | 15944.165 | 15895.8244 | 9.8793 | 56 | 9.384e-05 | 1796 | 20.9972 | 2437 | 0.0019603 | 0.10978 | 2483 | 0.05 | 2008
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 121988 | FALSE | 11219.1712 | 11219.1712 | 6.9728 | 92 | 0.00027094 | 171 | 5.2336 | 2742 | 0.0019488 | 0.17929 | 2484 |  | 2725
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 10960 | FALSE | 45089.9597 | 30132.5387 | 18.7275 | 320 | 9.2109e-05 | 1838 | 18.2529 | 2472 | 0.0019454 | 0.62252 | 2485 | 0.12 | 1381
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 453266 | TRUE | 510.1509 | 510.1509 | 0.31706 | 5 | 4.863e-05 | 3071 | 42.8367 | 2263 | 0.0019312 | 0.0096562 | 2486 |  | 3444
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | CB | FALSE | 12268.6539 | 7279.3949 | 4.5242 | 93 | 7.194e-05 | 2421 | 13.0319 | 2569 | 0.0019107 | 0.17769 | 2487 | 1.2 | 702
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 93418 | FALSE | 4145.9232 | 4145.9232 | 2.5767 | 23 | 6.4515e-05 | 2627 | 45.5233 | 2243 | 0.0019038 | 0.043787 | 2488 | 0.16 | 1254
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 697500 | FALSE | 10836.6474 | 10836.6474 | 6.735 | 74 | 0.00017368 | 536 | 8.0975 | 2667 | 0.0019029 | 0.14082 | 2489 |  | 3178
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 835658 | TRUE | 1187.2489 | 50.0391 | 0.0311 | 11 | 7.6553e-05 | 2292 | 17.3633 | 2494 | 0.0018987 | 0.020885 | 2490 |  | 3337
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 1158 | FALSE | 8353.2531 | 3588.3989 | 2.2302 | 65 | 5.6863e-05 | 2865 | 5.9152 | 2715 | 0.0018981 | 0.12337 | 2491 | 0.17 | 1241
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 576 | FALSE | 13079.4255 | 1582.5592 | 0.98357 | 116 | 0.00012308 | 1132 | 17.5488 | 2490 | 0.0018636 | 0.21618 | 2492 | 0.15 | 1287
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 7008 | FALSE | 29112.5788 | 8088.7008 | 5.0272 | 122 | 2.175e-05 | 3523 | 36.2639 | 2302 | 0.0018473 | 0.22537 | 2493 | 0.03 | 2381
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 648928 | FALSE | 7727.8743 | 6359.2353 | 3.9523 | 44 | 6.1331e-05 | 2741 | 57.7042 | 2168 | 0.0018437 | 0.081123 | 2494 | 0.04 | 2170
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 535998 | FALSE | 7941.4498 | 7140.4635 | 4.4378 | 43 | 0.00012357 | 1129 | 19.4088 | 2455 | 0.0018414 | 0.079178 | 2495 |  | 3367
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 12947 | FALSE | 5709.2465 | 5709.2465 | 3.5483 | 49 | 0.00010562 | 1503 | 18.015 | 2480 | 0.0018388 | 0.0901 | 2496 | 10.69 | 395
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 57840 | FALSE | 4238.9331 | 4238.9331 | 2.6345 | 29 | 0.00029837 | 131 | 7.443 | 2678 | 0.0018331 | 0.053161 | 2497 | 0.36 | 971
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | CB | TRUE | 28346.0077 | 787.8623 | 0.48966 | 259 | 8.1627e-05 | 2165 | 14.0393 | 2549 | 0.0018283 | 0.47354 | 2498 | 0.05 | 1935
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 954 | FALSE | 13095.0592 | 12372.699 | 7.6897 | 78 | 9.4465e-05 | 1782 | 22.5908 | 2415 | 0.0018244 | 0.1423 | 2499 | 0.05 | 1972
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 1704 | FALSE | 21239.3917 | 21231.8185 | 13.1957 | 160 | 0.00012962 | 1014 | 19.3786 | 2457 | 0.001823 | 0.29168 | 2500 | 0.18 | 1207
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 9031 | FALSE | 1741.4201 | 1741.4201 | 1.0823 | 17 | 0.00019853 | 401 | 5.6599 | 2722 | 0.0018195 | 0.030932 | 2501 | 26.99 | 262
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | CB | FALSE | 25157.6923 | 15741.0344 | 9.7831 | 214 | 7.9295e-05 | 2226 | 25.8956 | 2379 | 0.0018118 | 0.38772 | 2502 | 0.19 | 1192
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | V28 | FALSE | 14462.1376 | 1958.2873 | 1.2171 | 99 | 2.0931e-05 | 3535 | 31.9058 | 2328 | 0.0018053 | 0.17873 | 2503 | 0.03 | 2284
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 6421 | FALSE | 2777.3682 | 2777.3682 | 1.7261 | 20 | 5.7665e-05 | 2846 | 26.2004 | 2374 | 0.0018044 | 0.036089 | 2504 | 0.14 | 1307
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 12760 | FALSE | 42462.3954 | 42462.3954 | 26.3906 | 299 | 0.00019594 | 413 | 10.5604 | 2618 | 0.0017903 | 0.53531 | 2505 | 1.92 | 630
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | CB | FALSE | 3500.023 | 3442.3441 | 2.1394 | 26 | 0.00012024 | 1181 | 17.4311 | 2492 | 0.0017811 | 0.04631 | 2506 | 0.23 | 1119
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | BL 1101 | FALSE | 13568.3761 | 13568.3761 | 8.4328 | 101 | 0.00030613 | 124 | 6.186 | 2709 | 0.0017681 | 0.17858 | 2507 | 25.42 | 271
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 10190 | FALSE | 13591.0884 | 13591.0884 | 8.4469 | 61 | 6.3642e-05 | 2659 | 28.5039 | 2355 | 0.0017583 | 0.10725 | 2508 | 52.84 | 111
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 272636 | TRUE | 431.3681 | 431.3681 | 0.2681 | 5 | 2.8514e-05 | 3445 | 33.4034 | 2316 | 0.0017542 | 0.0087708 | 2509 |  | 3545
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 510055 | TRUE | 1976.5067 | 817.6203 | 0.50815 | 11 | 5.9313e-05 | 2794 | 33.1507 | 2320 | 0.0017489 | 0.019238 | 2510 |  | 3426
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 307832 | FALSE | 22986.441 | 2614.1136 | 1.6247 | 133 | 5.4142e-05 | 2940 | 52.2996 | 2199 | 0.0017438 | 0.23192 | 2511 |  | 2750
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 19542 | FALSE | 15319.5774 | 15319.5774 | 9.5212 | 111 | 0.00024603 | 231 | 13.9871 | 2550 | 0.0017374 | 0.19285 | 2512 | 87.42 | 37
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 2100 | FALSE | 6391.6672 | 6391.6672 | 3.9724 | 47 | 0.00013966 | 875 | 17.2588 | 2498 | 0.0017366 | 0.081621 | 2513 | 19.6 | 310
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 8299 | FALSE | 1934.2169 | 1934.2169 | 1.2021 | 13 | 0.0001379 | 895 | 14.6935 | 2537 | 0.0017192 | 0.02235 | 2514 | 62.52 | 83
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 108540 | FALSE | 7751.409 | 7751.409 | 4.8175 | 44 | 0.00010534 | 1511 | 10.8681 | 2613 | 0.001717 | 0.075547 | 2515 | 25 | 274
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8120 | FALSE | 14371.6326 | 14371.6326 | 8.932 | 108 | 0.00014141 | 847 | 24.2646 | 2397 | 0.0017068 | 0.18434 | 2516 | 0.12 | 1384
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | E510R | TRUE | 9824.475 | 807.8365 | 0.50207 | 84 | 6.4371e-05 | 2631 | 25.303 | 2388 | 0.0017029 | 0.14305 | 2517 | 0.06 | 1864
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 2902 | FALSE | 11242.8228 | 11242.8228 | 6.9875 | 8 | 0.00012146 | 1158 | 50.5933 | 2209 | 0.0016954 | 0.013563 | 2518 | 0.04 | 2100
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 863822 | TRUE | 1030.95 | 168.7519 | 0.10488 | 8 | 3.6716e-05 | 3321 | 27.8163 | 2364 | 0.0016933 | 0.013546 | 2519 |  | 2906
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 396264 | FALSE | 10259.9636 | 7704.2 | 4.7882 | 95 | 0.00010348 | 1560 | 21.8184 | 2427 | 0.0016927 | 0.16081 | 2520 |  | 2903
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 2200 | FALSE | 8965.9106 | 8965.9106 | 5.5723 | 64 | 0.00010183 | 1607 | 17.8909 | 2484 | 0.0016888 | 0.10808 | 2521 | 54.83 | 105
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 2406 | TRUE | 6309.8622 | 123.5636 | 0.076795 | 50 | 0.0001488 | 754 | 13.0398 | 2568 | 0.0016854 | 0.084272 | 2522 | 0.98 | 736
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 7611 | FALSE | 7068.0362 | 7068.0362 | 4.3928 | 42 | 8.7447e-05 | 2001 | 37.9943 | 2291 | 0.0016834 | 0.070701 | 2523 | 0.49 | 896
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 33050 | FALSE | 6143.4432 | 1793.1664 | 1.1145 | 56 | 0.000194 | 425 | 9.4021 | 2637 | 0.0016799 | 0.094072 | 2524 | 2.96 | 571
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 39424 | FALSE | 3992.9225 | 1481.6598 | 0.92086 | 36 | 9.8e-05 | 1690 | 17.4915 | 2491 | 0.0016754 | 0.060313 | 2525 |  | 3138
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 5082 | FALSE | 33362.418 | 32012.7007 | 19.896 | 215 | 0.00012065 | 1172 | 16.3155 | 2512 | 0.0016672 | 0.35844 | 2526 | 2.33 | 613
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 2768 | FALSE | 12969.9695 | 10109.7249 | 6.2832 | 92 | 7.5187e-05 | 2326 | 22.2701 | 2424 | 0.0016647 | 0.15315 | 2527 | 0.05 | 2021
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 85234 | FALSE | 12730.8347 | 12730.8347 | 7.9123 | 92 | 7.7367e-05 | 2279 | 30.0376 | 2343 | 0.0016524 | 0.15202 | 2528 | 0.02 | 2526
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 230272 | FALSE | 1833.3676 | 1377.39 | 0.85605 | 18 | 5.0412e-05 | 3031 | 15.9138 | 2516 | 0.0016485 | 0.029673 | 2529 |  | 2836
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 557468 | FALSE | 3768.3144 | 1423.6732 | 0.88482 | 28 | 0.0001751 | 528 | 10.813 | 2614 | 0.0016475 | 0.046129 | 2530 |  | 3042
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 1300 | FALSE | 9816.2612 | 5145.088 | 3.1977 | 84 | 0.00010467 | 1538 | 15.4386 | 2525 | 0.0016445 | 0.13814 | 2531 | 0.08 | 1580
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | CB | FALSE | 1947.472 | 1251.1033 | 0.77757 | 19 | 5.3489e-05 | 2951 | 32.6064 | 2325 | 0.0016436 | 0.031229 | 2532 | 0.03 | 2359
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 218894 | TRUE | 1856.9722 | 540.1994 | 0.33574 | 14 | 6.9371e-05 | 2494 | 15.8967 | 2518 | 0.00163 | 0.022819 | 2533 |  | 2758
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 13481 | TRUE | 1739.6965 | 0 | 0 | 14 | 0.0001142 | 1314 | 13.6321 | 2559 | 0.0016289 | 0.022805 | 2534 | 0.03 | 2380
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | D4982 | FALSE | 4312.861 | 4312.861 | 2.6805 | 21 | 3.0625e-05 | 3421 | 38.5371 | 2287 | 0.0016248 | 0.034121 | 2535 | 33.37 | 222
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 2038 | FALSE | 21510.9233 | 21510.9233 | 13.3691 | 155 | 0.00018694 | 462 | 18.4659 | 2468 | 0.0016155 | 0.2504 | 2536 | 0.06 | 1908
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 2268 | FALSE | 35117.3516 | 35117.3516 | 21.8256 | 217 | 8.4177e-05 | 2087 | 23.7294 | 2408 | 0.0016039 | 0.34805 | 2537 | 69.93 | 69
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 52664 | TRUE | 5174.4008 | 284.4033 | 0.17676 | 44 | 5.8197e-05 | 2829 | 25.8938 | 2380 | 0.0016028 | 0.070524 | 2538 |  | 2705
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10726 | FALSE | 16936.721 | 16936.721 | 10.5262 | 124 | 0.00026294 | 188 | 7.1636 | 2683 | 0.0016007 | 0.19849 | 2539 | 15.77 | 346
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 1331 | FALSE | 7064.7733 | 7064.7733 | 4.3908 | 63 | 0.00010598 | 1495 | 12.1416 | 2583 | 0.0015977 | 0.10065 | 2540 | 46.2 | 144
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | P166 | FALSE | 7343.1285 | 7068.5222 | 4.3931 | 27 | 0.00014292 | 827 | 10.6287 | 2617 | 0.0015975 | 0.043133 | 2541 | 0.97 | 738
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 36516 | FALSE | 6699.7019 | 6699.7019 | 4.1639 | 53 | 0.00037131 | 77 | 6.3459 | 2704 | 0.0015908 | 0.08431 | 2542 | 29.13 | 244
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 5304 | FALSE | 8039.9737 | 5763.285 | 3.5819 | 60 | 9.186e-05 | 1848 | 18.674 | 2464 | 0.0015784 | 0.094707 | 2543 | 0.05 | 1963
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 685852 | TRUE | 222.9305 | 104.9331 | 0.065216 | 3 | 0.00011257 | 1352 | 15.9116 | 2517 | 0.0015648 | 0.0046945 | 2544 |  | 3611
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | CB | TRUE | 16165.5618 | 153.7468 | 0.095554 | 111 | 7.0207e-05 | 2463 | 11.081 | 2607 | 0.0015644 | 0.17365 | 2545 | 0.1 | 1466
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 60050 | FALSE | 13116.246 | 13116.246 | 8.1518 | 98 | 0.00010761 | 1461 | 16.5517 | 2508 | 0.0015546 | 0.15235 | 2546 | 0.1 | 1480
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 391312 | TRUE | 1866.0468 | 229.6394 | 0.14272 | 13 | 5.8919e-05 | 2810 | 14.6684 | 2538 | 0.0015528 | 0.020186 | 2547 |  | 3544
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 322 | FALSE | 11857.5634 | 11550.5948 | 7.1787 | 88 | 0.0001706 | 560 | 11.411 | 2599 | 0.0015474 | 0.13618 | 2548 | 1.05 | 721
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 950688 | FALSE | 5883.5054 | 5883.5054 | 3.6566 | 50 | 0.00010781 | 1454 | 17.1924 | 2501 | 0.0015407 | 0.077034 | 2549 |  | 2854
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 9240 | FALSE | 17656.496 | 17656.496 | 10.9736 | 151 | 8.9367e-05 | 1936 | 23.8246 | 2406 | 0.0015394 | 0.23246 | 2550 | 0.09 | 1524
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 80982 | TRUE | 836.5231 | 836.5231 | 0.5199 | 8 | 7.4451e-05 | 2347 | 11.9509 | 2588 | 0.0015382 | 0.012305 | 2551 | 41.95 | 172
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 5144 | FALSE | 6368.9288 | 6368.9288 | 3.9583 | 36 | 0.00020138 | 392 | 8.6508 | 2650 | 0.0015295 | 0.055061 | 2552 | 32.7 | 225
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 3019 | TRUE | 1511.5981 | 426.9368 | 0.26534 | 11 | 7.3049e-05 | 2394 | 21.6652 | 2431 | 0.0015165 | 0.016682 | 2553 |  | 2928
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 173590 | FALSE | 6901.197 | 6901.197 | 4.2891 | 46 | 9.087e-05 | 1887 | 19.2098 | 2458 | 0.0015131 | 0.069603 | 2554 |  | 2921
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | CB | FALSE | 4176.9151 | 1037.2766 | 0.64467 | 36 | 0.00021226 | 350 | 8.6501 | 2651 | 0.0015072 | 0.054259 | 2555 | 0.03 | 2345
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 234 | FALSE | 10290.6171 | 5584.5077 | 3.4708 | 81 | 0.0001531 | 719 | 12.3014 | 2581 | 0.0015051 | 0.12191 | 2556 | 0.04 | 2094
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | CB | FALSE | 7703.9355 | 4253.8822 | 2.6438 | 61 | 0.00011905 | 1206 | 11.75 | 2592 | 0.0014997 | 0.091479 | 2557 | 1.94 | 628
1710 | ELK 110191336 | 42981101 | ELK 1101 | 91336 | FALSE | 13315.5222 | 12740.7114 | 7.9184 | 78 | 8.2847e-05 | 2135 | 14.0784 | 2546 | 0.0014969 | 0.11676 | 2558 | 0.04 | 2153
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 969182 | FALSE | 8578.2654 | 8578.2654 | 5.3314 | 64 | 0.00023272 | 274 | 7.8723 | 2672 | 0.0014937 | 0.095599 | 2559 |  | 2685
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 950 | FALSE | 11853.1557 | 9978.6098 | 6.2017 | 85 | 0.00011166 | 1376 | 9.5946 | 2629 | 0.0014937 | 0.12697 | 2560 | 0.09 | 1575
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | CB | FALSE | 17569.8608 | 1899.4744 | 1.1805 | 140 | 3.3628e-05 | 3373 | 17.212 | 2499 | 0.0014894 | 0.20851 | 2561 | 0.55 | 873
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 304 | TRUE | 3131.1603 | 221.043 | 0.13738 | 27 | 7.2267e-05 | 2410 | 12.9614 | 2570 | 0.0014798 | 0.039953 | 2562 | 0.03 | 2304
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 4796 | FALSE | 11571.4706 | 11571.4706 | 7.1917 | 114 | 8.3272e-05 | 2126 | 15.4981 | 2524 | 0.0014707 | 0.16766 | 2563 | 50.63 | 117
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 3002 | FALSE | 13206.8342 | 11656.2739 | 7.2444 | 76 | 8.5336e-05 | 2046 | 10.9995 | 2610 | 0.001464 | 0.11126 | 2564 | 0.15 | 1296
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 201156 | FALSE | 2780.2158 | 2335.0863 | 1.4513 | 26 | 0.000132 | 983 | 11.0364 | 2609 | 0.0014632 | 0.038044 | 2565 |  | 2996
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 315500 | FALSE | 5515.195 | 1783.0288 | 1.1082 | 22 | 2.1144e-05 | 3532 | 19.9522 | 2450 | 0.0014578 | 0.032073 | 2566 |  | 3335
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 39156 | FALSE | 7678.6279 | 5580.9258 | 3.4686 | 62 | 0.00036657 | 79 | 5.0499 | 2749 | 0.0014467 | 0.089693 | 2567 | 0.4 | 949
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 533648 | FALSE | 10867.8258 | 10867.8258 | 6.7544 | 93 | 0.00016205 | 621 | 8.4995 | 2655 | 0.0014323 | 0.13321 | 2568 | 0.11 | 1415
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 668674 | FALSE | 15298.6549 | 15298.6549 | 9.5082 | 112 | 0.00024869 | 220 | 8.5559 | 2654 | 0.0014289 | 0.16003 | 2569 |  | 2801
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 12590 | FALSE | 8818.0631 | 8233.9726 | 5.1174 | 69 | 0.00032896 | 102 | 7.9903 | 2671 | 0.0014267 | 0.09844 | 2570 | 0.34 | 980
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 45261 | TRUE | 20192.7526 | 164.9958 | 0.10255 | 10 | 7.3888e-05 | 2362 | 8.6022 | 2652 | 0.001423 | 0.01423 | 2571 |  | 3326
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1313 | FALSE | 1996.4298 | 1996.4298 | 1.2408 | 19 | 0.00014421 | 810 | 12.5764 | 2576 | 0.0014057 | 0.026709 | 2572 | 44.58 | 156
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 75972 | FALSE | 7223.394 | 5386.1403 | 3.3475 | 61 | 6.5028e-05 | 2609 | 22.3 | 2423 | 0.0013938 | 0.085021 | 2573 | 0.52 | 885
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 8982 | FALSE | 7434.3823 | 7434.3823 | 4.6205 | 50 | 0.00014907 | 751 | 11.9525 | 2587 | 0.0013928 | 0.06964 | 2574 | 0.08 | 1625
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 39154 | FALSE | 1419.8889 | 1419.8889 | 0.88247 | 11 | 0.00019824 | 403 | 21.6746 | 2430 | 0.0013923 | 0.015315 | 2575 | 62.39 | 84
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | CB | FALSE | 6227.6638 | 6227.6638 | 3.8705 | 47 | 0.00010177 | 1608 | 5.1216 | 2747 | 0.0013913 | 0.065391 | 2576 | 0.03 | 2337
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1765 | FALSE | 2336.7952 | 2336.7952 | 1.4523 | 20 | 0.00017078 | 558 | 6.0123 | 2713 | 0.0013887 | 0.027774 | 2577 | 15.71 | 348
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 36596 | FALSE | 20043.7619 | 6572.3951 | 4.0848 | 145 | 1.719e-05 | 3570 | 17.052 | 2503 | 0.0013847 | 0.20079 | 2578 | 0.03 | 2397
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 5000 | FALSE | 3149.0186 | 3149.0186 | 1.9571 | 23 | 0.00041733 | 64 | 2.1336 | 2834 | 0.0013814 | 0.031772 | 2579 | 24.55 | 277
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | CB | TRUE | 244.7023 | 7.571 | 0.0047054 | 6 | 8.8688e-05 | 1962 | 31.698 | 2332 | 0.001321 | 0.0079259 | 2580 |  | 3593
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 1316 | FALSE | 22645.6685 | 22101.0688 | 13.7359 | 166 | 7.7968e-05 | 2260 | 13.3542 | 2565 | 0.0013124 | 0.21786 | 2581 | 0.12 | 1400
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 35562 | FALSE | 22914.0776 | 22914.0776 | 14.2412 | 147 | 0.00010505 | 1525 | 11.7038 | 2593 | 0.0013006 | 0.19119 | 2582 | 0.16 | 1270
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 1318 | FALSE | 16637.0018 | 13693.4076 | 8.5105 | 113 | 0.00013033 | 1004 | 8.2659 | 2664 | 0.0012974 | 0.14661 | 2583 | 9.77 | 404
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | L491 | FALSE | 3564.5514 | 3564.5514 | 2.2154 | 31 | 0.00010065 | 1632 | 5.4343 | 2732 | 0.0012903 | 0.039999 | 2584 | 33.77 | 219
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | XR244 | TRUE | 22757.8317 | 0 | 0 | 157 | 6.3757e-05 | 2654 | 15.2591 | 2527 | 0.0012825 | 0.20135 | 2585 | 0.59 | 855
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | CB | TRUE | 3592.4976 | 971.3906 | 0.60372 | 31 | 0.0002505 | 215 | 3.3852 | 2798 | 0.0012726 | 0.039451 | 2586 | 0.05 | 1979
842 | ELK 11011272 | 42981101 | ELK 1101 | 1272 | FALSE | 36077.8728 | 35548.517 | 22.0935 | 236 | 0.00010152 | 1616 | 17.6496 | 2487 | 0.0012681 | 0.29926 | 2587 | 0.25 | 1089
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | CB | FALSE | 9891.2145 | 4885.2685 | 3.0362 | 66 | 2.8183e-05 | 3454 | 23.8416 | 2402 | 0.0012656 | 0.083532 | 2588 | 0.03 | 2371
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 12256 | FALSE | 10425.1159 | 10425.1159 | 6.4793 | 86 | 9.8504e-05 | 1679 | 19.6956 | 2453 | 0.0012622 | 0.10855 | 2589 | 60.88 | 87
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | W34 | FALSE | 15456.5208 | 12223.0154 | 7.5967 | 112 | 3.8291e-05 | 3294 | 31.2471 | 2337 | 0.0012584 | 0.14094 | 2590 |  | 2657
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 903238 | FALSE | 9893.8007 | 6450.8713 | 4.0092 | 30 | 4.7333e-05 | 3108 | 30.0306 | 2344 | 0.001258 | 0.037741 | 2591 |  | 3186
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 448 | FALSE | 14554.2556 | 3932.5973 | 2.4441 | 116 | 9.7296e-05 | 1707 | 15.8508 | 2519 | 0.001256 | 0.1457 | 2592 |  | 2652
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 81514 | FALSE | 7697.8392 | 4781.286 | 2.9716 | 65 | 8.7032e-05 | 2011 | 13.7396 | 2556 | 0.0012525 | 0.08141 | 2593 | 0.04 | 2121
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 2204 | FALSE | 11625.6324 | 11625.6324 | 7.2254 | 84 | 9.4601e-05 | 1775 | 11.1006 | 2606 | 0.0012429 | 0.1044 | 2594 | 40.14 | 185
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 11046 | FALSE | 25866.5621 | 25866.5621 | 16.0762 | 194 | 0.00016384 | 601 | 6.3121 | 2705 | 0.0012326 | 0.23912 | 2595 | 1.33 | 683
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 8522 | FALSE | 15153.8377 | 3071.2008 | 1.9088 | 123 | 0.0001684 | 573 | 8.4903 | 2656 | 0.0012059 | 0.14833 | 2596 | 0.11 | 1425
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 959032 | FALSE | 1582.9544 | 1283.5288 | 0.79772 | 11 | 0.00012885 | 1030 | 15.1847 | 2528 | 0.0012034 | 0.013238 | 2597 |  | 3517
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 872066 | TRUE | 1285.5374 | 856.8881 | 0.53256 | 13 | 8.9931e-05 | 1916 | 14.7027 | 2535 | 0.0011906 | 0.015478 | 2598 |  | 3074
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 2764 | FALSE | 9871.3778 | 9871.3778 | 6.1351 | 68 | 0.0002671 | 178 | 5.6584 | 2724 | 0.0011906 | 0.080958 | 2599 | 0.05 | 2046
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1943 | FALSE | 1959.963 | 1959.963 | 1.2181 | 17 | 0.00014604 | 788 | 5.6591 | 2723 | 0.0011872 | 0.020183 | 2600 |  | 3220
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 641544 | FALSE | 7956.2573 | 7956.2573 | 4.9448 | 58 | 0.00010868 | 1431 | 9.0793 | 2642 | 0.0011816 | 0.068531 | 2601 |  | 2763
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 64565 | FALSE | 1284.2848 | 1284.2848 | 0.79819 | 13 | 0.00016067 | 634 | 14.7117 | 2534 | 0.001175 | 0.015275 | 2602 | 0.3 | 1013
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | CB | TRUE | 26742.8753 | 940.9991 | 0.58483 | 226 | 4.1039e-05 | 3242 | 20.6872 | 2439 | 0.0011724 | 0.26497 | 2603 |  | 2752
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 9500 | FALSE | 10910.9002 | 9168.0738 | 5.698 | 71 | 6.6682e-05 | 2565 | 18.8342 | 2462 | 0.0011663 | 0.082807 | 2604 | 1.62 | 662
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 836528 | FALSE | 4695.3621 | 4679.584 | 2.9084 | 39 | 3.0209e-05 | 3424 | 39.6633 | 2275 | 0.0011552 | 0.045051 | 2605 |  | 2820
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | CB | FALSE | 25409.8546 | 24616.6476 | 15.2993 | 192 | 0.00012212 | 1146 | 9.4762 | 2636 | 0.0011504 | 0.22088 | 2606 | 0.14 | 1327
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | CB | TRUE | 3504.1175 | 755.1177 | 0.46931 | 25 | 5.9264e-05 | 2797 | 9.8829 | 2625 | 0.001149 | 0.028724 | 2607 |  | 2717
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 704542 | TRUE | 487.4963 | 345.9417 | 0.215 | 3 | 0.00010371 | 1556 | 10.6423 | 2616 | 0.0011475 | 0.0034424 | 2608 |  | 3612
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 624200 | FALSE | 3744.0071 | 2491.858 | 1.5487 | 6 | 9.1262e-06 | 3614 | 78.1632 | 2058 | 0.0011432 | 0.0068593 | 2609 |  | 3383
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | L5381 | FALSE | 1955.4877 | 1955.4877 | 1.2153 | 15 | 8.6227e-05 | 2029 | 11.1601 | 2603 | 0.0011429 | 0.017144 | 2610 | 63.74 | 80
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 218424 | TRUE | 877.6167 | 866.5125 | 0.53854 | 4 | 6.9394e-05 | 2493 | 17.8902 | 2485 | 0.0011372 | 0.0045488 | 2611 |  | 3498
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 55402 | FALSE | 14989.6887 | 3994.4825 | 2.4826 | 104 | 6.4572e-05 | 2623 | 16.7266 | 2505 | 0.0011234 | 0.11683 | 2612 | 0.02 | 2517
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 503000 | FALSE | 7554.2208 | 7373.131 | 4.5824 | 54 | 0.00017004 | 564 | 3.5877 | 2787 | 0.0011185 | 0.060401 | 2613 |  | 2789
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 240 | FALSE | 4953.3762 | 4953.3762 | 3.0785 | 42 | 0.00020071 | 393 | 8.5626 | 2653 | 0.0011134 | 0.046762 | 2614 | 27.15 | 261
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 10930 | FALSE | 18316.5864 | 1585.2477 | 0.98524 | 149 | 9.2072e-05 | 1841 | 11.2167 | 2602 | 0.0011126 | 0.16578 | 2615 | 0.03 | 2315
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 1139 | FALSE | 3291.1128 | 3291.1128 | 2.0454 | 25 | 0.00021661 | 335 | 5.771 | 2718 | 0.0011071 | 0.027677 | 2616 | 19.12 | 313
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 1480 | FALSE | 3913.3341 | 3463.9371 | 2.1529 | 20 | 6.904e-05 | 2506 | 14.3241 | 2543 | 0.0011038 | 0.022077 | 2617 | 0.02 | 2410
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 75622 | FALSE | 9209.8908 | 1956.9061 | 1.2162 | 78 | 8.9335e-05 | 1938 | 14.1186 | 2545 | 0.0010989 | 0.085711 | 2618 | 1.24 | 694
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | CB | FALSE | 17419.9506 | 9244.2642 | 5.7453 | 121 | 8.2774e-05 | 2137 | 22.4988 | 2417 | 0.001078 | 0.13044 | 2619 | 36.92 | 204
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 97924 | FALSE | 8287.4089 | 8287.4089 | 5.1507 | 49 | 8.4247e-05 | 2084 | 16.5614 | 2507 | 0.0010653 | 0.052198 | 2620 | 28.19 | 252
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 842642 | FALSE | 9353.842 | 9353.842 | 5.8135 | 80 | 0.00015044 | 731 | 10.167 | 2622 | 0.0010503 | 0.084021 | 2621 | 0.11 | 1445
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | CB | FALSE | 8798.7393 | 5676.9517 | 3.5282 | 72 | 0.00028651 | 144 | 7.3277 | 2682 | 0.0010502 | 0.075616 | 2622 | 5.26 | 492
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | S1547 | FALSE | 4459.8848 | 4459.8848 | 2.7718 | 39 | 5.3114e-05 | 2964 | 14.6954 | 2536 | 0.0010487 | 0.040901 | 2623 | 82.41 | 44
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 1277 | TRUE | 3471.3767 | 0 | 0 | 30 | 4.0209e-05 | 3263 | 12.7259 | 2574 | 0.001018 | 0.030539 | 2624 | 0.04 | 2212
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 7290 | FALSE | 1075.4071 | 1075.4071 | 0.66837 | 8 | 2.8269e-05 | 3452 | 23.8308 | 2405 | 0.0010126 | 0.0081011 | 2625 | 0 | 2635
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 644462 | TRUE | 2486.8085 | 567.6161 | 0.35278 | 24 | 0.00010098 | 1625 | 12.9287 | 2571 | 0.0010124 | 0.024298 | 2626 |  | 3468
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | LC12 | FALSE | 12044.6481 | 12044.6481 | 7.4858 | 86 | 0.00017659 | 521 | 13.8877 | 2554 | 0.0010097 | 0.086838 | 2627 | 0.56 | 865
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 498932 | FALSE | 6861.4641 | 6024.2456 | 3.7441 | 57 | 0.00014672 | 777 | 8.6826 | 2649 | 0.0010076 | 0.057431 | 2628 | 0.09 | 1548
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 5731 | FALSE | 5029.6194 | 5029.6194 | 3.1259 | 41 | 0.00015547 | 690 | 3.5444 | 2790 | 0.0010067 | 0.041274 | 2629 | 0.05 | 1973
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | CB | FALSE | 28734.8817 | 28123.7558 | 17.479 | 148 | 7.11e-05 | 2442 | 13.9274 | 2552 | 0.0010065 | 0.14896 | 2630 | 0.36 | 966
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | CB | FALSE | 10346.1129 | 2141.3708 | 1.3309 | 82 | 8.1676e-05 | 2163 | 6.4364 | 2698 | 0.0010058 | 0.082476 | 2631 | 0.06 | 1846
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 87222 | FALSE | 8479.914 | 8240.0573 | 5.1212 | 57 | 0.00010497 | 1529 | 10.4869 | 2620 | 0.0010031 | 0.057176 | 2632 | 0.1 | 1504
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | CB | FALSE | 14092.576 | 11980.8022 | 7.4461 | 86 | 0.00012586 | 1080 | 5.5912 | 2727 | 0.0010024 | 0.086208 | 2633 | 0.22 | 1132
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 509068 | FALSE | 2868.1374 | 1655.4712 | 1.0289 | 22 | 0.00010648 | 1487 | 17.3491 | 2495 | 0.0010019 | 0.022042 | 2634 |  | 3297
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 975388 | TRUE | 2101.0589 | 775.2264 | 0.48181 | 18 | 4.0105e-05 | 3265 | 13.2566 | 2567 | 0.0010016 | 0.018029 | 2635 |  | 3242
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 5394 | FALSE | 24529.1372 | 23340.3938 | 14.5061 | 180 | 0.00013063 | 998 | 7.7218 | 2674 | 0.00099214 | 0.17859 | 2636 | 43.45 | 169
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 887180 | FALSE | 8692.4371 | 8589.4892 | 5.3384 | 61 | 5.5738e-05 | 2897 | 12.9178 | 2572 | 0.00098628 | 0.060163 | 2637 | 0.07 | 1715
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 4698 | FALSE | 12883.0062 | 12883.0062 | 8.0068 | 101 | 0.00018389 | 481 | 12.0639 | 2584 | 0.00097756 | 0.098734 | 2638 | 0.05 | 1998
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | L7283 | FALSE | 1053.4945 | 1053.4945 | 0.65475 | 12 | 7.514e-05 | 2329 | 13.9335 | 2551 | 0.00097446 | 0.011693 | 2639 | 29.37 | 241
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 51732 | FALSE | 12971.5884 | 1093.5921 | 0.67967 | 110 | 0.00019845 | 402 | 3.0886 | 2809 | 0.00097323 | 0.10706 | 2640 | 0.02 | 2495
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 96738 | FALSE | 10792.8538 | 10792.8538 | 6.7078 | 84 | 0.00020283 | 387 | 5.4435 | 2731 | 0.00097276 | 0.081712 | 2641 | 21.67 | 298
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 692576 | FALSE | 5517.9962 | 3874.9491 | 2.4083 | 51 | 0.0001303 | 1007 | 7.0569 | 2686 | 0.0009691 | 0.049424 | 2642 |  | 2983
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 8848 | FALSE | 16215.0785 | 6200.2521 | 3.8535 | 117 | 6.6972e-05 | 2558 | 11.0461 | 2608 | 0.00096385 | 0.11277 | 2643 | 0.22 | 1123
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 50396 | FALSE | 21037.3757 | 20827.3892 | 12.9443 | 162 | 8.5221e-05 | 2050 | 11.5065 | 2597 | 0.00096084 | 0.15566 | 2644 | 20.38 | 306
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 114 | TRUE | 4957.8887 | 17.4908 | 0.010871 | 40 | 8.3173e-05 | 2128 | 9.1847 | 2640 | 0.00096055 | 0.038422 | 2645 | 8.42 | 426
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 60116 | FALSE | 19634.1928 | 19634.1928 | 12.2027 | 151 | 0.00020011 | 397 | 4.9468 | 2757 | 0.00095505 | 0.14421 | 2646 | 0.89 | 751
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1703 | FALSE | 2213.9946 | 2213.9946 | 1.376 | 16 | 0.00013016 | 1008 | 6.0137 | 2712 | 0.00095446 | 0.015271 | 2647 | 43.57 | 165
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | CB | FALSE | 21117.9549 | 15035.2163 | 9.3444 | 130 | 6.8162e-05 | 2531 | 7.7386 | 2673 | 0.00094726 | 0.12314 | 2648 | 0.52 | 887
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 217974 | FALSE | 6862.6922 | 6593.0651 | 4.0976 | 44 | 0.00013259 | 971 | 7.0882 | 2685 | 0.00093976 | 0.04135 | 2649 |  | 2978
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | A32 | FALSE | 9519.6113 | 2633.3805 | 1.6367 | 76 | 6.2625e-05 | 2697 | 14.4505 | 2541 | 0.00093807 | 0.071294 | 2650 | 0.03 | 2314
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 1850 | FALSE | 21661.1812 | 21661.1812 | 13.4625 | 182 | 0.00013942 | 879 | 5.1605 | 2745 | 0.00093342 | 0.16988 | 2651 | 73.2 | 62
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4218 | FALSE | 7931.9123 | 7690.241 | 4.7795 | 27 | 0.00022706 | 297 | 5.3463 | 2735 | 0.00093079 | 0.025131 | 2652 | 0.09 | 1526
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 76752 | FALSE | 4380.3192 | 4380.3192 | 2.7224 | 36 | 0.00025263 | 209 | 5.3491 | 2733 | 0.00091318 | 0.032874 | 2653 | 0.44 | 924
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 1030 | FALSE | 25567.0003 | 25567.0003 | 15.89 | 217 | 0.00014916 | 749 | 5.1044 | 2748 | 0.00090994 | 0.19746 | 2654 | 21.6 | 300
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1808 | FALSE | 2949.8139 | 2949.8139 | 1.8333 | 27 | 9.0273e-05 | 1905 | 7.9905 | 2670 | 0.00090929 | 0.024551 | 2655 | 46.07 | 145
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 36720 | FALSE | 12840.8619 | 9577.7665 | 5.9526 | 87 | 5.288e-05 | 2972 | 18.0958 | 2475 | 0.00089535 | 0.077895 | 2656 | 0.12 | 1394
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | MR366 | TRUE | 15876.8969 | 0 | 0 | 134 | 1.4916e-05 | 3586 | 46.6158 | 2237 | 0.00088159 | 0.11813 | 2657 |  | 2698
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | CB | FALSE | 23033.3792 | 23033.3792 | 14.3153 | 170 | 0.00010514 | 1519 | 8.871 | 2646 | 0.0008744 | 0.14865 | 2658 | 0.65 | 822
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 3142 | FALSE | 28901.7283 | 28901.7283 | 17.9625 | 256 | 8.7499e-05 | 1999 | 11.3039 | 2600 | 0.00086175 | 0.22061 | 2659 | 128.2 | 8
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | CB | FALSE | 12456.8292 | 3768.052 | 2.3419 | 111 | 9.7026e-05 | 1713 | 9.3336 | 2638 | 0.00085884 | 0.095332 | 2660 | 0.34 | 979
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | L3151 | FALSE | 1595.4085 | 1595.4085 | 0.99155 | 13 | 0.0001267 | 1068 | 7.3809 | 2679 | 0.00085242 | 0.011082 | 2661 | 25 | 273
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 12838 | FALSE | 3807.4911 | 3807.4911 | 2.3664 | 32 | 0.00058408 | 21 | 1.5522 | 2860 | 0.00085046 | 0.027215 | 2662 | 8.72 | 421
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 403102 | TRUE | 2765.6183 | 788.5735 | 0.4901 | 18 | 0.00014171 | 843 | 5.3389 | 2736 | 0.00084561 | 0.015221 | 2663 |  | 3267
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 2010 | FALSE | 6409.6213 | 6409.6213 | 3.9836 | 43 | 8.8563e-05 | 1970 | 8.3553 | 2660 | 0.00084365 | 0.036277 | 2664 | 0.11 | 1409
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 4446 | TRUE | 17302.7635 | 0 | 0 | 124 | 4.9277e-05 | 3056 | 12.6776 | 2575 | 0.00084052 | 0.10422 | 2665 | 0.04 | 2135
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 669542 | FALSE | 5668.7589 | 5668.7589 | 3.5232 | 49 | 0.00018473 | 476 | 4.4449 | 2769 | 0.0008334 | 0.040836 | 2666 |  | 2960
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 90120 | FALSE | 8309.1292 | 5041.5999 | 3.1334 | 64 | 0.00010439 | 1542 | 5.6342 | 2725 | 0.00082387 | 0.052727 | 2667 | 0.04 | 2200
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 7948F | FALSE | 13813.6905 | 1712.0139 | 1.064 | 74 | 2.7103e-05 | 3472 | 53.0836 | 2194 | 0.00082174 | 0.060809 | 2668 | 0.02 | 2432
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | CB | FALSE | 19644.2096 | 2188.9817 | 1.3605 | 180 | 4.3869e-05 | 3192 | 3.8934 | 2779 | 0.0008192 | 0.14746 | 2669 | 0.05 | 1928
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 6028 | FALSE | 13370.3026 | 13370.3026 | 8.3097 | 115 | 0.00011502 | 1298 | 6.888 | 2688 | 0.0008147 | 0.09369 | 2670 | 56.37 | 98
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 432 | FALSE | 18069.9686 | 1802.3639 | 1.1202 | 130 | 5.4493e-05 | 2933 | 13.5928 | 2560 | 0.00080536 | 0.1047 | 2671 | 0.03 | 2402
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 10720 | FALSE | 7675.033 | 7675.033 | 4.7701 | 25 | 2.2157e-05 | 3517 | 32.3965 | 2326 | 0.00079114 | 0.019779 | 2672 | 23.43 | 287
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | CB | FALSE | 3388.6184 | 3388.6184 | 2.106 | 21 | 6.388e-05 | 2651 | 12.5128 | 2578 | 0.00079069 | 0.016605 | 2673 | 0.04 | 2209
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 76468 | FALSE | 4744.0085 | 1281.0776 | 0.79619 | 35 | 9.8202e-05 | 1686 | 6.3972 | 2700 | 0.00078905 | 0.027617 | 2674 | 0.03 | 2373
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | CB | FALSE | 4816.3453 | 4816.3453 | 2.9934 | 40 | 0.00013401 | 943 | 11.9588 | 2585 | 0.0007688 | 0.030752 | 2675 | 31.2 | 232
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | CB | FALSE | 11748.8949 | 6728.9489 | 4.1821 | 92 | 9.2886e-05 | 1826 | 6.3592 | 2703 | 0.00076238 | 0.070139 | 2676 | 0.16 | 1251
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | CB | FALSE | 19605.5563 | 19605.5563 | 12.1849 | 151 | 0.00013907 | 885 | 11.5584 | 2596 | 0.00075189 | 0.11354 | 2677 | 0.07 | 1772
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 38218 | FALSE | 17605.0564 | 17605.0564 | 10.9416 | 132 | 9.9008e-05 | 1668 | 8.1704 | 2665 | 0.00074696 | 0.098599 | 2678 | 94.05 | 28
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 5090 | FALSE | 34218.6566 | 34218.6566 | 21.267 | 245 | 0.00010692 | 1476 | 6.8561 | 2689 | 0.00074249 | 0.18191 | 2679 | 1.26 | 691
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 824 | TRUE | 12575.4803 | 137.5107 | 0.085463 | 103 | 0.00010133 | 1619 | 3.4457 | 2797 | 0.00072721 | 0.074902 | 2680 |  | 2674
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 9280 | FALSE | 10262.6071 | 10262.6071 | 6.3783 | 80 | 8.3881e-05 | 2098 | 8.09 | 2668 | 0.00072124 | 0.057699 | 2681 | 2.82 | 577
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 11056 | FALSE | 6785.5939 | 6717.0632 | 4.1747 | 48 | 0.00016442 | 592 | 4.026 | 2778 | 0.00071991 | 0.034556 | 2682 | 0.3 | 1011
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 530 | TRUE | 43254.3781 | 117.5277 | 0.073044 | 255 | 0.00014869 | 756 | 5.1756 | 2744 | 0.00070447 | 0.17964 | 2683 | 0.02 | 2508
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 1818 | FALSE | 5027.483 | 4942.4923 | 3.0718 | 26 | 4.1e-05 | 3243 | 14.3865 | 2542 | 0.00069935 | 0.018183 | 2684 | 0.72 | 799
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 2796 | FALSE | 31981.5846 | 31981.5846 | 19.8767 | 253 | 0.00012583 | 1081 | 6.8299 | 2691 | 0.00069507 | 0.17585 | 2685 | 44.5 | 159
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 10442 | FALSE | 16579.0287 | 9105.2092 | 5.6589 | 133 | 0.00016483 | 589 | 3.6401 | 2786 | 0.00069444 | 0.092361 | 2686 | 0.29 | 1027
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | CB | FALSE | 5806.4035 | 3043.2971 | 1.8914 | 48 | 0.00014993 | 737 | 3.6937 | 2784 | 0.00069407 | 0.033315 | 2687 | 0.04 | 2177
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 237791 | FALSE | 3420.2949 | 2280.4467 | 1.4173 | 23 | 0.0001987 | 399 | 3.165 | 2804 | 0.00069283 | 0.015935 | 2688 |  | 3489
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 285704 | FALSE | 1923.7717 | 1685.8276 | 1.0477 | 17 | 0.00023236 | 275 | 9.8522 | 2626 | 0.00068515 | 0.011648 | 2689 |  | 3385
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 10600 | FALSE | 21367.0688 | 21367.0688 | 13.2797 | 161 | 7.3663e-05 | 2371 | 8.335 | 2662 | 0.000683 | 0.10996 | 2690 | 276.94 | 1
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 428102 | FALSE | 20879.8446 | 19729.9421 | 12.2622 | 158 | 0.00012781 | 1053 | 4.9782 | 2755 | 0.00068264 | 0.10786 | 2691 | 0.55 | 866
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 480430 | FALSE | 8153.37 | 1450.1348 | 0.90126 | 39 | 5.7435e-05 | 2851 | 18.7653 | 2463 | 0.00068138 | 0.026574 | 2692 |  | 3372
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 662 | FALSE | 13657.9642 | 10019.7655 | 6.2273 | 104 | 6.0639e-05 | 2758 | 8.9744 | 2644 | 0.00067921 | 0.070638 | 2693 | 0.07 | 1724
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 54728 | FALSE | 7898.4984 | 1667.872 | 1.0366 | 37 | 3.3775e-05 | 3371 | 43.321 | 2256 | 0.00066262 | 0.024517 | 2694 | 0.79 | 775
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 7347 | FALSE | 1315.3758 | 1315.3758 | 0.81751 | 10 | 0.00013644 | 913 | 4.8202 | 2760 | 0.00065864 | 0.0065864 | 2695 | 43.48 | 167
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 13026 | FALSE | 12912.9615 | 12912.9615 | 8.0255 | 70 | 4.9241e-05 | 3058 | 11.6076 | 2595 | 0.00065269 | 0.045688 | 2696 | 8.38 | 429
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 320094 | TRUE | 1539.8883 | 440.0576 | 0.2735 | 11 | 3.4565e-05 | 3360 | 25.2958 | 2389 | 0.00064788 | 0.0071266 | 2697 |  | 2907
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 15401 | FALSE | 1388.1732 | 1388.1732 | 0.86276 | 11 | 0.00019479 | 418 | 6.5489 | 2694 | 0.00064146 | 0.0070561 | 2698 | 41.15 | 179
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 256 | FALSE | 2415.6319 | 2415.6319 | 1.5013 | 17 | 0.00023971 | 247 | 1.4646 | 2867 | 0.00063627 | 0.010817 | 2699 | 24.25 | 279
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 758594 | FALSE | 3264.6914 | 1943.4938 | 1.2079 | 21 | 0.00012955 | 1018 | 6.1576 | 2711 | 0.00062774 | 0.013182 | 2700 |  | 3075
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 1779 | TRUE | 677.0293 | 540.9099 | 0.33618 | 5 | 6.6577e-05 | 2570 | 9.5735 | 2633 | 0.00062625 | 0.0031313 | 2701 |  | 3516
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | A30 | TRUE | 2568.419 | 401.1046 | 0.24929 | 25 | 5.8029e-05 | 2834 | 6.399 | 2699 | 0.00062089 | 0.015522 | 2702 | 0.02 | 2500
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 3100 | FALSE | 23694.1727 | 19636.3272 | 12.2041 | 198 | 6.4544e-05 | 2625 | 14.9697 | 2532 | 0.00061511 | 0.12179 | 2703 | 0.06 | 1863
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 90334 | FALSE | 5394.0455 | 5394.0455 | 3.3524 | 44 | 3.2303e-05 | 3396 | 20.5875 | 2442 | 0.00061497 | 0.027059 | 2704 | 11.09 | 388
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 2194 | FALSE | 4329.2096 | 2142.6429 | 1.3317 | 36 | 0.00018519 | 470 | 3.3664 | 2801 | 0.00060703 | 0.021853 | 2705 | 1.88 | 634
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | XR602 | TRUE | 1368.2778 | 391.3667 | 0.24324 | 13 | 8.4195e-05 | 2086 | 9.8269 | 2627 | 0.00060529 | 0.0078688 | 2706 | 0.03 | 2240
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | CB | FALSE | 7588.8389 | 3330.3293 | 2.0698 | 47 | 0.0003055 | 125 | 1.7499 | 2851 | 0.00059825 | 0.028118 | 2707 | 0.99 | 735
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 50142 | FALSE | 6580.4447 | 3596.2025 | 2.2351 | 55 | 0.00011566 | 1280 | 5.2494 | 2740 | 0.00059558 | 0.032757 | 2708 | 2.21 | 618
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | CB | TRUE | 8192.7885 | 792.3448 | 0.49245 | 70 | 0.00016303 | 612 | 5.4892 | 2729 | 0.00059471 | 0.04163 | 2709 | 0.06 | 1815
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 12041 | FALSE | 10143.7851 | 10143.7851 | 6.3044 | 65 | 0.00013198 | 985 | 5.1866 | 2743 | 0.00059297 | 0.038543 | 2710 | 30.78 | 234
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | C558R | FALSE | 23093.6755 | 1942.5032 | 1.2073 | 180 | 4.7416e-05 | 3106 | 10.0864 | 2623 | 0.00059158 | 0.10648 | 2711 | 12.02 | 377
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 1804 | FALSE | 13482.9013 | 13482.9013 | 8.3797 | 118 | 0.00010094 | 1626 | 6.3117 | 2706 | 0.00058985 | 0.069602 | 2712 | 106.77 | 17
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 635040 | TRUE | 340.9559 | 324.181 | 0.20148 | 2 | 9.5316e-05 | 1752 | 11.9488 | 2590 | 0.0005888 | 0.0011776 | 2713 |  | 3585
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 776806 | TRUE | 1634.4876 | 412.4097 | 0.25631 | 15 | 4.0998e-05 | 3244 | 13.7861 | 2555 | 0.00058477 | 0.0087716 | 2714 |  | 3094
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 3611 | FALSE | 2597.3823 | 2597.3823 | 1.6143 | 23 | 5.2349e-05 | 2984 | 11.435 | 2598 | 0.00057745 | 0.013281 | 2715 | 32.3 | 226
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | XR250 | TRUE | 9406.4624 | 0 | 0 | 80 | 6.5499e-05 | 2601 | 5.0345 | 2750 | 0.00057262 | 0.04581 | 2716 | 4.1 | 527
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | CB | TRUE | 1304.8232 | 357.3361 | 0.22209 | 16 | 7.3542e-05 | 2381 | 5.012 | 2752 | 0.00057058 | 0.0091293 | 2717 |  | 3215
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | CB | TRUE | 5451.3154 | 266.9695 | 0.16592 | 50 | 3.1382e-05 | 3410 | 8.3028 | 2663 | 0.0005603 | 0.028015 | 2718 | 0.02 | 2459
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 53038 | FALSE | 10729.3555 | 10729.3555 | 6.6683 | 62 | 6.9809e-05 | 2481 | 8.8864 | 2645 | 0.00055181 | 0.034212 | 2719 | 0.63 | 833
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 978 | FALSE | 47571.501 | 22458.2021 | 13.9579 | 130 | 3.6377e-05 | 3326 | 24.8644 | 2391 | 0.00055148 | 0.071692 | 2720 | 0.07 | 1680
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 908 | FALSE | 3616.7994 | 1126.3756 | 0.70005 | 42 | 6.1442e-05 | 2737 | 3.4612 | 2796 | 0.00055062 | 0.023126 | 2721 |  | 3005
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 719490 | FALSE | 4856.6254 | 4856.6254 | 3.0184 | 44 | 6.7665e-05 | 2542 | 6.5472 | 2695 | 0.00054847 | 0.024132 | 2722 |  | 2777
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | CB | FALSE | 5887.1186 | 3755.8808 | 2.3343 | 56 | 5.471e-05 | 2926 | 5.5819 | 2728 | 0.00054657 | 0.030608 | 2723 | 0.07 | 1682
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 418480 | FALSE | 1216.9885 | 1216.9885 | 0.75636 | 13 | 0.00010549 | 1506 | 5.5937 | 2726 | 0.0005464 | 0.0071032 | 2724 |  | 3256
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 8894 | FALSE | 18146.6988 | 18102.2842 | 11.2506 | 110 | 0.00011302 | 1343 | 4.8209 | 2759 | 0.00053494 | 0.058844 | 2725 | 5.41 | 487
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2564 | FALSE | 3603.0114 | 3598.4394 | 2.2364 | 21 | 3.9721e-05 | 3274 | 12.5176 | 2577 | 0.00053291 | 0.011191 | 2726 | 0.1 | 1482
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | CB | TRUE | 9060.4473 | 490.8425 | 0.30506 | 88 | 4.3627e-05 | 3197 | 6.3791 | 2701 | 0.00052634 | 0.046318 | 2727 |  | 2703
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 1276 | FALSE | 6144.8964 | 6012.4282 | 3.7367 | 56 | 0.00018947 | 444 | 3.4619 | 2795 | 0.00052522 | 0.029412 | 2728 | 0.53 | 884
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 47143 | FALSE | 7882.6346 | 7882.6346 | 4.8991 | 67 | 0.00016052 | 638 | 2.9032 | 2815 | 0.00052216 | 0.034985 | 2729 | 0.63 | 837
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 562376 | FALSE | 12962.1789 | 12746.1039 | 7.9218 | 82 | 6.0914e-05 | 2752 | 14.0412 | 2548 | 0.00052151 | 0.042763 | 2730 |  | 2872
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 154 | TRUE | 15159.6857 | 20.5741 | 0.012787 | 108 | 0.00013977 | 871 | 1.0919 | 2887 | 0.00051973 | 0.056131 | 2731 | 0.03 | 2260
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | CB | FALSE | 8918.2943 | 8918.2943 | 5.5428 | 46 | 0.00023568 | 259 | 2.1334 | 2835 | 0.00051722 | 0.023792 | 2732 | 44.97 | 153
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 10718 | FALSE | 13624.5702 | 13624.5702 | 8.4677 | 98 | 0.00029137 | 138 | 2.007 | 2842 | 0.0005122 | 0.050195 | 2733 | 0.58 | 858
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 32536 | FALSE | 17537.3204 | 17537.3204 | 10.8995 | 144 | 0.00010307 | 1568 | 6.8331 | 2690 | 0.00050182 | 0.072262 | 2734 | 126.24 | 9
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 12946 | FALSE | 5267.6978 | 3912.0696 | 2.4314 | 41 | 7.1582e-05 | 2431 | 5.8607 | 2717 | 0.00050028 | 0.020511 | 2735 | 0.3 | 1016
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 716 | TRUE | 14760.549 | 161.153 | 0.10016 | 124 | 5.8731e-05 | 2814 | 7.5935 | 2676 | 0.00049954 | 0.061943 | 2736 | 0.53 | 880
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | S2247 | FALSE | 2394.0014 | 2394.0014 | 1.4879 | 21 | 7.5118e-05 | 2331 | 9.1225 | 2641 | 0.00049228 | 0.010338 | 2737 | 96.94 | 23
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 778286 | FALSE | 4188.0047 | 4188.0047 | 2.6029 | 5 | 3.6444e-05 | 3323 | 19.0779 | 2461 | 0.0004909 | 0.0024545 | 2738 | 0 | 2637
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 457174 | TRUE | 1940.6507 | 925.5451 | 0.57523 | 14 | 0.00011583 | 1277 | 1.7636 | 2850 | 0.00048348 | 0.0067687 | 2739 |  | 3313
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 825520 | FALSE | 2407.6531 | 1896.9242 | 1.1789 | 21 | 4.6815e-05 | 3116 | 8.3859 | 2659 | 0.00047064 | 0.0098834 | 2740 |  | 3202
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1264 | FALSE | 5420.1776 | 3078.9362 | 1.9136 | 50 | 5.6664e-05 | 2869 | 10.5255 | 2619 | 0.00046357 | 0.023178 | 2741 | 0.61 | 847
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 45984 | FALSE | 7772.9197 | 7772.9197 | 4.8309 | 68 | 5.7852e-05 | 2840 | 4.9585 | 2756 | 0.00046238 | 0.031442 | 2742 | 0.06 | 1809
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 90374 | FALSE | 7135.3675 | 6578.4615 | 4.0885 | 48 | 9.4382e-05 | 1784 | 3.531 | 2791 | 0.0004592 | 0.022042 | 2743 | 0.06 | 1794
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | CB | TRUE | 22820.5615 | 0 | 0 | 197 | 8.4141e-05 | 2089 | 3.1167 | 2806 | 0.00045724 | 0.090077 | 2744 | 43.8 | 164
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 9270 | FALSE | 9370.6933 | 9370.6933 | 5.8239 | 68 | 0.00011547 | 1288 | 6.0072 | 2714 | 0.00045602 | 0.03101 | 2745 | 40.93 | 182
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | XR234 | TRUE | 1908.9722 | 4.1246 | 0.0025635 | 26 | 4.1932e-05 | 3226 | 7.3799 | 2680 | 0.00045563 | 0.011846 | 2746 | 0.03 | 2236
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 1238 | FALSE | 5923.8162 | 5923.8162 | 3.6817 | 30 | 0.00026272 | 189 | 9.5821 | 2630 | 0.0004533 | 0.013599 | 2747 | 62.35 | 85
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 81146 | FALSE | 9033.4152 | 1226.8593 | 0.7625 | 79 | 7.3782e-05 | 2366 | 10.282 | 2621 | 0.00045161 | 0.035677 | 2748 | 0.03 | 2350
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 22412 | FALSE | 24417.5389 | 3680.7169 | 2.2876 | 130 | 3.6957e-05 | 3316 | 12.5116 | 2579 | 0.0004496 | 0.058447 | 2749 |  | 2781
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5302 | FALSE | 9546.4932 | 9546.4932 | 5.9332 | 57 | 0.00026232 | 191 | 2.1517 | 2833 | 0.00044854 | 0.025567 | 2750 | 1.02 | 727
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | CB | TRUE | 4340.9857 | 216.2085 | 0.13437 | 38 | 4.6882e-05 | 3115 | 6.7721 | 2692 | 0.00044808 | 0.017027 | 2751 | 8.14 | 434
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | CB | FALSE | 9677.833 | 9246.0032 | 5.7464 | 73 | 0.00012957 | 1017 | 4.2973 | 2773 | 0.00044728 | 0.032652 | 2752 | 0.53 | 879
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 440 | FALSE | 19525.153 | 3309.7658 | 2.057 | 158 | 8.4963e-05 | 2062 | 3.5276 | 2792 | 0.00044177 | 0.0698 | 2753 | 0.17 | 1237
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 12596 | FALSE | 17025.8657 | 12925.0786 | 8.033 | 140 | 8.8891e-05 | 1955 | 5.6622 | 2721 | 0.00043371 | 0.060719 | 2754 | 0.06 | 1804
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 9759 | FALSE | 4110.5786 | 4110.5786 | 2.5547 | 32 | 0.00015886 | 653 | 4.5245 | 2765 | 0.00043106 | 0.013794 | 2755 |  | 2867
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | CB | FALSE | 6570.8 | 6570.8 | 4.0838 | 11 | 6.9646e-05 | 2484 | 248.9538 | 1542 | 0.00042329 | 0.0046561 | 2756 | 0.02 | 2523
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | L2219 | FALSE | 5447.1163 | 5447.1163 | 3.3854 | 41 | 7.2244e-05 | 2411 | 7.0237 | 2687 | 0.00042266 | 0.017329 | 2757 | 49.71 | 121
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 12705 | TRUE | 9361.8686 | 0 | 0 | 74 | 2.2116e-05 | 3518 | 9.0486 | 2643 | 0.00042265 | 0.031276 | 2758 |  | 2827
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 69032 | FALSE | 13655.5842 | 13655.5842 | 8.487 | 101 | 8.8998e-05 | 1949 | 4.7713 | 2762 | 0.00041877 | 0.042296 | 2759 | 0.08 | 1653
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 520832 | FALSE | 12960.7664 | 9719.2853 | 6.0406 | 90 | 0.00014149 | 844 | 3.7624 | 2781 | 0.00040636 | 0.036573 | 2760 |  | 2787
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 903182 | FALSE | 1770.3755 | 1052.7078 | 0.65426 | 15 | 5.4676e-05 | 2927 | 4.2832 | 2774 | 0.00040533 | 0.0060799 | 2761 |  | 3258
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 1286 | FALSE | 12241.8563 | 7682.9666 | 4.775 | 92 | 6.6713e-05 | 2563 | 5.3157 | 2739 | 0.00040112 | 0.036903 | 2762 | 0.07 | 1737
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 76008 | FALSE | 25670.8015 | 25670.8015 | 15.9545 | 170 | 9.3618e-05 | 1806 | 4.261 | 2775 | 0.000401 | 0.068169 | 2763 | 96.79 | 24
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 228906 | TRUE | 2215.3527 | 988.5949 | 0.61442 | 21 | 3.9761e-05 | 3273 | 5.3472 | 2734 | 0.00039716 | 0.0083403 | 2764 |  | 3330
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 99432 | FALSE | 13966.781 | 2359.0159 | 1.4661 | 115 | 2.7226e-05 | 3470 | 10.878 | 2612 | 0.00039549 | 0.045481 | 2765 | 0.07 | 1745
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 4905 | FALSE | 3704.1382 | 3704.1382 | 2.3021 | 35 | 8.1261e-05 | 2174 | 6.1793 | 2710 | 0.00038885 | 0.01361 | 2766 | 65.75 | 75
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 60092 | FALSE | 15629.1336 | 15629.1336 | 9.7136 | 108 | 0.00019731 | 408 | 2.9279 | 2813 | 0.00038814 | 0.041919 | 2767 | 0.39 | 951
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 8442 | FALSE | 19428.9727 | 19428.9727 | 12.0752 | 50 | 6.3912e-05 | 2650 | 8.1497 | 2666 | 0.00038233 | 0.019117 | 2768 | 0.11 | 1438
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 1210 | FALSE | 8832.2253 | 5252.6146 | 3.2645 | 73 | 0.00023323 | 270 | 1.6941 | 2853 | 0.00038163 | 0.027859 | 2769 | 0.29 | 1025
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 419634 | TRUE | 1981.0133 | 165.107 | 0.10261 | 14 | 7.8094e-05 | 2255 | 6.2924 | 2707 | 0.00037832 | 0.0052965 | 2770 |  | 3436
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | CB | TRUE | 14648.5405 | 486.1753 | 0.30216 | 107 | 1.7992e-05 | 3560 | 4.7299 | 2764 | 0.00037788 | 0.040433 | 2771 | 0.25 | 1087
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 418 | FALSE | 19645.0637 | 8262.136 | 5.135 | 130 | 5.7927e-05 | 2837 | 5.0022 | 2753 | 0.00037742 | 0.049065 | 2772 | 0.06 | 1897
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 337544 | TRUE | 1419.0103 | 579.0642 | 0.35989 | 13 | 0.00011348 | 1333 | 3.7153 | 2783 | 0.00037689 | 0.0048996 | 2773 |  | 3561
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 7050 | FALSE | 15143.783 | 15143.783 | 9.4119 | 67 | 3.0197e-05 | 3425 | 13.5475 | 2562 | 0.0003702 | 0.024804 | 2774 | 0 | 2642
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 8089 | FALSE | 4528.4761 | 4528.4761 | 2.8145 | 29 | 0.00010867 | 1432 | 3.3453 | 2802 | 0.00036614 | 0.010618 | 2775 | 4.59 | 513
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 84166 | FALSE | 13898.1694 | 13231.1785 | 8.2232 | 97 | 0.0002829 | 150 | 1.5368 | 2863 | 0.00036427 | 0.035334 | 2776 |  | 3013
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 1252 | FALSE | 6608.6355 | 6608.6355 | 4.1073 | 50 | 0.00013383 | 946 | 3.8677 | 2780 | 0.00036141 | 0.018071 | 2777 | 11.02 | 391
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | M501R | FALSE | 7503.1067 | 4016.4433 | 2.4962 | 60 | 4.6793e-05 | 3118 | 3.6463 | 2785 | 0.00035751 | 0.021451 | 2778 | 0.03 | 2319
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | CB | TRUE | 2357.516 | 24.568 | 0.015269 | 24 | 1.8797e-05 | 3556 | 2.0509 | 2838 | 0.00035038 | 0.0084091 | 2779 |  | 3009
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 1052 | FALSE | 6204.8696 | 5356.147 | 3.3289 | 49 | 5.6569e-05 | 2870 | 5.2348 | 2741 | 0.00034866 | 0.017084 | 2780 | 0.08 | 1629
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | CB | FALSE | 2115.1186 | 1181.1241 | 0.73407 | 17 | 7.5667e-05 | 2317 | 2.8608 | 2817 | 0.00034683 | 0.0058961 | 2781 | 0.04 | 2077
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | CR020 | FALSE | 3932.8974 | 3932.8974 | 2.4443 | 15 | 9.3739e-05 | 1801 | 4.8237 | 2758 | 0.00034485 | 0.0051727 | 2782 | 41.15 | 180
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 857972 | FALSE | 2082.0425 | 1672.4824 | 1.0395 | 18 | 4.6793e-05 | 3119 | 6.2207 | 2708 | 0.00034064 | 0.0061316 | 2783 |  | 3208
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 143744 | FALSE | 1706.1115 | 1706.1115 | 1.0604 | 13 | 0.00045932 | 45 | 1.8946 | 2847 | 0.00033981 | 0.0044176 | 2784 |  | 3153
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 84318 | FALSE | 16486.0902 | 16486.0902 | 10.2462 | 142 | 8.547e-05 | 2041 | 8.7666 | 2648 | 0.00033804 | 0.048002 | 2785 | 0.05 | 2065
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | L1969 | FALSE | 1768.6139 | 1768.6139 | 1.0992 | 16 | 7.7816e-05 | 2267 | 7.4947 | 2677 | 0.00032448 | 0.0051917 | 2786 | 58.12 | 93
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | LB40 | FALSE | 14924.9201 | 13714.1212 | 8.5234 | 131 | 7.571e-05 | 2314 | 4.7844 | 2761 | 0.00032354 | 0.042384 | 2787 | 0.15 | 1298
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 9690 | FALSE | 27916.5832 | 27916.5832 | 17.3503 | 185 | 4.7987e-05 | 3093 | 9.3188 | 2639 | 0.00031402 | 0.058094 | 2788 | 45.06 | 151
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 402866 | FALSE | 2560.4032 | 2560.4032 | 1.5913 | 20 | 8.0485e-05 | 2192 | 2.4422 | 2826 | 0.0003137 | 0.0062739 | 2789 | 0.02 | 2566
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | CB | TRUE | 2195.0052 | 304.3324 | 0.18914 | 18 | 7.9462e-05 | 2222 | 3.5853 | 2789 | 0.00031227 | 0.0056208 | 2790 | 1.29 | 688
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | CB | TRUE | 7402.9758 | 10.2676 | 0.0063814 | 69 | 2.9198e-05 | 3436 | 37.685 | 2292 | 0.00031202 | 0.02153 | 2791 | 1.11 | 716
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | BR160 | FALSE | 18386.4832 | 13394.711 | 8.3249 | 132 | 6.9198e-05 | 2499 | 3.3682 | 2800 | 0.00031068 | 0.04101 | 2792 | 0.24 | 1104
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 720639 | FALSE | 5844.6694 | 2660.7876 | 1.6537 | 25 | 0.00018595 | 468 | 1.9664 | 2846 | 0.0003062 | 0.0076549 | 2793 |  | 3105
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | W10 | FALSE | 3001.7775 | 2354.9644 | 1.4636 | 29 | 3.4275e-05 | 3364 | 7.1616 | 2684 | 0.00030601 | 0.0088744 | 2794 | 0.04 | 2112
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 9096 | FALSE | 10649.9386 | 5304.2381 | 3.2966 | 78 | 3.3536e-05 | 3375 | 6.4596 | 2697 | 0.00030601 | 0.023869 | 2795 | 0.04 | 2102
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | CB | FALSE | 11982.8259 | 11982.8259 | 7.4474 | 97 | 5.9625e-05 | 2786 | 4.4752 | 2768 | 0.00030421 | 0.029509 | 2796 | 0.19 | 1186
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 420146 | FALSE | 5058.5239 | 4389.3602 | 2.728 | 43 | 0.00013429 | 940 | 3.382 | 2799 | 0.00030412 | 0.013077 | 2797 |  | 3266
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | MR650 | FALSE | 4320.1366 | 2086.6412 | 1.2969 | 30 | 3.1219e-05 | 3411 | 6.4702 | 2696 | 0.00029523 | 0.0088568 | 2798 | 0.07 | 1706
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 472 | FALSE | 7739.1551 | 4930.8208 | 3.0645 | 71 | 9.5789e-05 | 1733 | 2.7474 | 2818 | 0.00029462 | 0.020918 | 2799 | 0.08 | 1630
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 4690 | FALSE | 23028.3671 | 18710.8643 | 11.6289 | 161 | 8.9068e-05 | 1944 | 4.3458 | 2772 | 0.00029439 | 0.047396 | 2800 | 0.16 | 1260
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5166 | FALSE | 8840.5786 | 8840.5786 | 5.4945 | 81 | 9.5629e-05 | 1737 | 3.5862 | 2788 | 0.00028991 | 0.023482 | 2801 | 31.21 | 231
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 48868 | TRUE | 3010.868 | 0 | 0 | 21 | 2.3959e-05 | 3505 | 3.0775 | 2810 | 0.00028316 | 0.0059463 | 2802 | 0.31 | 997
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 1640 | FALSE | 16804.166 | 16804.166 | 10.4439 | 59 | 7.8829e-05 | 2241 | 5.7047 | 2720 | 0.00028287 | 0.016689 | 2803 | 0.01 | 2569
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3032 | FALSE | 15762.9704 | 5799.169 | 3.6042 | 84 | 2.4376e-05 | 3503 | 5.9133 | 2716 | 0.00028141 | 0.023638 | 2804 | 0.03 | 2349
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 693441 | FALSE | 6859.835 | 6859.835 | 4.2634 | 59 | 4.9575e-05 | 3046 | 4.4985 | 2767 | 0.00027928 | 0.016478 | 2805 | 0.29 | 1029
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2183 | FALSE | 4246.8638 | 4246.8638 | 2.6394 | 33 | 9.4677e-05 | 1774 | 4.3864 | 2771 | 0.00027436 | 0.009054 | 2806 | 0.05 | 2047
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 952 | FALSE | 16341.5936 | 16341.5936 | 10.1564 | 130 | 0.00010228 | 1595 | 2.9907 | 2812 | 0.00027431 | 0.03566 | 2807 | 0.36 | 970
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | CB | FALSE | 11616.1021 | 9822.6918 | 6.1048 | 86 | 0.0005458 | 25 | 1.1717 | 2883 | 0.00026897 | 0.023131 | 2808 | 19.78 | 308
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 446423 | FALSE | 2345.7749 | 1135.402 | 0.70566 | 23 | 0.00012326 | 1131 | 2.131 | 2836 | 0.00026534 | 0.0061027 | 2809 |  | 2912
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 37278 | FALSE | 10929.4406 | 10929.4406 | 6.7927 | 99 | 0.00011401 | 1321 | 2.7082 | 2820 | 0.00026318 | 0.026055 | 2810 | 62.81 | 82
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | CB | FALSE | 18604.4746 | 8502.7441 | 5.2845 | 115 | 8.1074e-05 | 2181 | 1.4421 | 2868 | 0.00025895 | 0.029779 | 2811 | 0.23 | 1110
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 68920 | FALSE | 11754.4382 | 10341.5361 | 6.4273 | 91 | 9.0413e-05 | 1900 | 5.0244 | 2751 | 0.0002577 | 0.02345 | 2812 | 0.16 | 1274
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | CB | FALSE | 7764.6762 | 7472.667 | 4.6443 | 53 | 0.0005799 | 22 | 0.9633 | 2896 | 0.0002457 | 0.013022 | 2813 | 38.98 | 191
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 410 | FALSE | 3634.5971 | 2502.9293 | 1.5556 | 28 | 2.4862e-05 | 3498 | 2.3255 | 2830 | 0.00024476 | 0.0068532 | 2814 | 0.06 | 1826
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | CB | TRUE | 13992.2701 | 885.5612 | 0.55038 | 109 | 0.00021179 | 353 | 2.0247 | 2841 | 0.00024231 | 0.026412 | 2815 | 0.21 | 1152
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | CB | FALSE | 19709.1046 | 14267.6715 | 8.8674 | 60 | 0.0002127 | 346 | 1.2563 | 2877 | 0.00023784 | 0.01427 | 2816 | 0.11 | 1433
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 63100 | FALSE | 6591.8886 | 6591.8886 | 4.0969 | 55 | 0.00023384 | 266 | 1.3628 | 2873 | 0.00023675 | 0.013021 | 2817 | 5.34 | 490
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1701 | FALSE | 2248.9876 | 2248.9876 | 1.3978 | 18 | 9.908e-05 | 1666 | 2.7097 | 2819 | 0.00023556 | 0.0042401 | 2818 | 29.59 | 240
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 5001 | TRUE | 2742.1134 | 0 | 0 | 25 | 3.0913e-05 | 3419 | 4.514 | 2766 | 0.00023403 | 0.0058507 | 2819 | 6.31 | 469
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | CB | TRUE | 5657.7233 | 67.4906 | 0.041946 | 43 | 3.1411e-05 | 3409 | 11.8961 | 2591 | 0.000232 | 0.0099759 | 2820 | 0.04 | 2072
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | CB | FALSE | 13792.1671 | 9469.8097 | 5.8855 | 102 | 0.00017335 | 539 | 0.99807 | 2891 | 0.00023023 | 0.023483 | 2821 | 0.21 | 1141
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 857172 | TRUE | 1843.2099 | 152.0386 | 0.094493 | 15 | 8.7874e-05 | 1986 | 3.2284 | 2803 | 0.00022992 | 0.0034488 | 2822 |  | 3212
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 5060 | TRUE | 1113.3002 | 291.5638 | 0.18121 | 12 | 7.5643e-05 | 2319 | 1.3951 | 2871 | 0.00022663 | 0.0027196 | 2823 |  | 3502
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 114284 | TRUE | 893.7863 | 451.7326 | 0.28075 | 11 | 8.3715e-05 | 2102 | 4.3909 | 2770 | 0.00022547 | 0.0024802 | 2824 |  | 3236
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 37276 | FALSE | 18746.4684 | 18746.4684 | 11.651 | 168 | 0.00010311 | 1567 | 2.0474 | 2839 | 0.00022047 | 0.037039 | 2825 | 88.82 | 33
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 2026 | FALSE | 16422.8166 | 8438.7955 | 5.2447 | 126 | 4.8317e-05 | 3086 | 5.725 | 2719 | 0.00021753 | 0.027409 | 2826 | 0.07 | 1690
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 688590 | FALSE | 3500.4301 | 1691.536 | 1.0513 | 32 | 4.9847e-05 | 3041 | 3.0358 | 2811 | 0.00021706 | 0.0069459 | 2827 |  | 2671
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 705 | TRUE | 2028.0775 | 622.3172 | 0.38677 | 20 | 0.00010699 | 1473 | 4.0264 | 2777 | 0.00021298 | 0.0042596 | 2828 |  | 2895
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 8090 | FALSE | 6501.5338 | 6501.5338 | 4.0407 | 53 | 0.00010162 | 1614 | 1.8606 | 2848 | 0.00021162 | 0.011216 | 2829 | 58.21 | 92
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | W50 | TRUE | 5818.6322 | 997.9458 | 0.62023 | 40 | 1.4796e-05 | 3587 | 16.6866 | 2506 | 0.00021093 | 0.0084371 | 2830 | 0.03 | 2302
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 79628 | FALSE | 23813.9358 | 23813.9358 | 14.8005 | 156 | 7.9122e-05 | 2230 | 2.6556 | 2822 | 0.00021051 | 0.032839 | 2831 | 0.17 | 1233
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 1226 | FALSE | 12605.0062 | 12282.9745 | 7.6339 | 96 | 0.00012073 | 1171 | 0.80895 | 2902 | 0.00020916 | 0.02008 | 2832 | 1.01 | 728
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | CR192 | FALSE | 6810.4625 | 3963.0316 | 2.463 | 54 | 8.0733e-05 | 2188 | 1.3873 | 2872 | 0.00020828 | 0.011247 | 2833 | 0.21 | 1135
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | V22 | TRUE | 810.5999 | 50.4916 | 0.031381 | 14 | 2.0015e-05 | 3542 | 3.4621 | 2794 | 0.00020377 | 0.0028528 | 2834 |  | 2885
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 3066 | TRUE | 26.0345 | 26.0345 | 0.016181 | 2 | 5.3309e-05 | 2953 | 11.9582 | 2586 | 0.00020359 | 0.00040718 | 2835 | 0.44 | 922
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 8132 | FALSE | 5814.9582 | 4248.014 | 2.6402 | 47 | 9.8938e-05 | 1671 | 2.0883 | 2837 | 0.00020337 | 0.0095582 | 2836 | 0.04 | 2079
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 1166 | FALSE | 24234.157 | 20163.1012 | 12.5314 | 213 | 0.00022306 | 307 | 0.8473 | 2900 | 0.00020294 | 0.043227 | 2837 | 1.46 | 673
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | CB | FALSE | 5679.6302 | 5679.6302 | 3.5299 | 43 | 0.00015288 | 721 | 0.6192 | 2911 | 0.00020121 | 0.0086519 | 2838 | 23.03 | 289
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 964592 | TRUE | 1787.6075 | 941.9387 | 0.58542 | 15 | 2.9092e-05 | 3439 | 9.5689 | 2634 | 0.00019824 | 0.0029736 | 2839 |  | 3528
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 1200 | FALSE | 4658.8808 | 4658.8808 | 2.8955 | 34 | 8.1804e-05 | 2158 | 2.8623 | 2816 | 0.00019566 | 0.0066525 | 2840 | 4.42 | 520
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 53192 | TRUE | 3316.9892 | 889.758 | 0.55299 | 30 | 5.4105e-05 | 2941 | 5.3377 | 2737 | 0.0001937 | 0.0058109 | 2841 |  | 3032
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 660408 | TRUE | 3217.4282 | 570.687 | 0.35468 | 26 | 3.0978e-05 | 3417 | 7.378 | 2681 | 0.00019086 | 0.0049624 | 2842 |  | 3121
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | CB | FALSE | 3053.2387 | 1333.5262 | 0.82879 | 33 | 7.2893e-05 | 2396 | 1.9862 | 2843 | 0.00018865 | 0.0062254 | 2843 | 0.02 | 2444
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 750618 | FALSE | 1583.7149 | 1538.3917 | 0.95612 | 13 | 5.3287e-05 | 2955 | 3.1105 | 2807 | 0.0001837 | 0.002388 | 2844 |  | 2755
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | CB | FALSE | 6937.627 | 6745.77 | 4.1925 | 55 | 9.8691e-05 | 1677 | 3.0905 | 2808 | 0.00018024 | 0.0099135 | 2845 | 0.1 | 1500
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 402/2 LR | FALSE | 10638.2509 | 10545.4353 | 6.554 | 91 | 0.00012174 | 1151 | 1.633 | 2857 | 0.00017917 | 0.016305 | 2846 |  | 2922
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | S2123 | FALSE | 2988.9855 | 2988.9855 | 1.8577 | 25 | 0.00012986 | 1010 | 1.9671 | 2845 | 0.00017177 | 0.0042941 | 2847 |  | 3018
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 290705 | FALSE | 5314.0636 | 5193.0778 | 3.2275 | 38 | 0.0001966 | 410 | 2.568 | 2823 | 0.00016712 | 0.0063506 | 2848 |  | 2706
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 829194 | FALSE | 18124.3826 | 18124.3826 | 11.2644 | 142 | 0.00022979 | 286 | 0.40121 | 2916 | 0.00016422 | 0.023319 | 2849 |  | 2858
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 12990 | FALSE | 21277.9249 | 21277.9249 | 13.2243 | 161 | 0.00018796 | 455 | 1.0994 | 2886 | 0.00016127 | 0.025964 | 2850 | 0.86 | 764
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 32747 | FALSE | 2820.8108 | 1047.4929 | 0.65102 | 26 | 0.00014649 | 780 | 1.2825 | 2876 | 0.00016086 | 0.0041824 | 2851 | 1.65 | 658
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 76178 | FALSE | 32532.3048 | 32532.3048 | 20.219 | 248 | 0.00012177 | 1150 | 3.133 | 2805 | 0.00015934 | 0.039517 | 2852 | 0.13 | 1361
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 3716 | TRUE | 21171.7372 | 690.7324 | 0.42929 | 157 | 6.4877e-05 | 2613 | 1.6769 | 2855 | 0.00015488 | 0.024316 | 2853 | 0.03 | 2321
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 57886 | FALSE | 8466.0843 | 6549.4745 | 4.0705 | 81 | 8.2619e-05 | 2138 | 0.94597 | 2899 | 0.00015101 | 0.012232 | 2854 | 0.08 | 1619
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | A40 | FALSE | 20639.8903 | 6084.3101 | 3.7814 | 174 | 4.3444e-05 | 3202 | 1.431 | 2870 | 0.00015079 | 0.026237 | 2855 | 0.03 | 2254
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 8918 | FALSE | 3457.885 | 2431.0442 | 1.5109 | 30 | 0.00022692 | 298 | 2.4426 | 2824 | 0.0001494 | 0.0044819 | 2856 | 2.79 | 579
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 56468 | FALSE | 9625.3334 | 8910.5893 | 5.538 | 85 | 0.00022965 | 287 | 1.0912 | 2888 | 0.0001483 | 0.012606 | 2857 | 12.55 | 373
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 419718 | FALSE | 3649.8042 | 3649.8042 | 2.2684 | 25 | 0.00013422 | 941 | 1.0173 | 2890 | 0.0001469 | 0.0036725 | 2858 |  | 3248
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 1278 | FALSE | 12855.1379 | 9099.8598 | 5.6556 | 96 | 9.744e-05 | 1703 | 1.5519 | 2861 | 0.00014529 | 0.013948 | 2859 | 0.05 | 1918
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 1220 | TRUE | 7829.4679 | 0 | 0 | 57 | 2.5969e-05 | 3488 | 1.1753 | 2882 | 0.00013353 | 0.0076113 | 2860 | 0.03 | 2239
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | CB | FALSE | 24857.1517 | 22896.4557 | 14.2302 | 209 | 9.1121e-05 | 1876 | 1.2034 | 2878 | 0.00012965 | 0.027098 | 2861 | 0.08 | 1613
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 68380 | FALSE | 10711.9675 | 10711.9675 | 6.6575 | 88 | 0.00012793 | 1048 | 2.2263 | 2832 | 0.00012865 | 0.011322 | 2862 | 0.74 | 791
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | MR544 | TRUE | 7120.8066 | 27.9821 | 0.017391 | 62 | 9.0189e-06 | 3615 | 1.9811 | 2844 | 0.00012274 | 0.0076101 | 2863 | 0.04 | 2154
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 10954 | FALSE | 11428.7483 | 11428.7483 | 7.103 | 90 | 9.1892e-05 | 1847 | 2.4422 | 2825 | 0.00012262 | 0.011036 | 2864 | 0.16 | 1268
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 1282 | TRUE | 5984.1771 | 0 | 0 | 56 | 9.973e-05 | 1654 | 1.1951 | 2881 | 0.00012029 | 0.0067363 | 2865 | 0.03 | 2326
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 15341 | TRUE | 2075.9695 | 391.2765 | 0.24318 | 18 | 3.4322e-05 | 3363 | 5.3372 | 2738 | 0.00011859 | 0.0021346 | 2866 | 0.74 | 792
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 303870 | FALSE | 1292.4248 | 1028.4638 | 0.63919 | 7 | 5.3155e-05 | 2962 | 2.3249 | 2831 | 0.0001185 | 0.00082948 | 2867 |  | 3080
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 426 | FALSE | 6243.6329 | 3219.5011 | 2.0009 | 52 | 5.7367e-05 | 2854 | 1.7424 | 2852 | 0.00011662 | 0.0060642 | 2868 | 0.04 | 2194
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 774760 | FALSE | 5348.863 | 5348.863 | 3.3243 | 37 | 0.00022083 | 317 | 0.70854 | 2908 | 0.00011197 | 0.0041429 | 2869 |  | 3263
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 74648 | TRUE | 7581.2034 | 262.1986 | 0.16296 | 63 | 8.4795e-05 | 2069 | 1.0707 | 2889 | 0.00011106 | 0.0069966 | 2870 | 0.42 | 932
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 69124 | FALSE | 4347.2792 | 4347.2792 | 2.7019 | 33 | 8.5315e-05 | 2047 | 1.5063 | 2864 | 0.00010917 | 0.0036026 | 2871 | 0.05 | 2055
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 116815 | FALSE | 4074.4873 | 2540.2857 | 1.5788 | 33 | 0.00019069 | 440 | 1.5062 | 2865 | 0.00010723 | 0.0035385 | 2872 |  | 3182
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 93038 | FALSE | 4552.6155 | 2107.4343 | 1.3098 | 39 | 0.00019968 | 398 | 1.284 | 2875 | 0.00010645 | 0.0041517 | 2873 | 0.03 | 2241
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 2032 | TRUE | 14427.8487 | 905.5345 | 0.56279 | 103 | 2.5379e-05 | 3492 | 0.98818 | 2894 | 0.0001063 | 0.010949 | 2874 | 0.14 | 1323
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3442 | FALSE | 8430.8944 | 5599.863 | 3.4803 | 68 | 0.00011662 | 1257 | 0.7637 | 2904 | 0.00010618 | 0.0072205 | 2875 | 0.07 | 1685
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 33060 | TRUE | 7941.0149 | 856.2789 | 0.53218 | 64 | 0.00022712 | 296 | 0.31239 | 2924 | 9.9531e-05 | 0.00637 | 2876 | 0.02 | 2560
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | P148 | FALSE | 7362.5215 | 1361.9079 | 0.84643 | 54 | 4.5868e-05 | 3143 | 1.5547 | 2859 | 9.8792e-05 | 0.0053348 | 2877 |  | 2783
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 75348 | FALSE | 8532.4043 | 8532.4043 | 5.3029 | 77 | 8.3581e-05 | 2110 | 1.3013 | 2874 | 9.5481e-05 | 0.0073521 | 2878 | 79.37 | 49
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 1232 | FALSE | 14610.263 | 12420.8061 | 7.7196 | 64 | 4.2772e-05 | 3212 | 1.5493 | 2862 | 9.0864e-05 | 0.0058153 | 2879 | 0.05 | 2007
4735 | ELK 11018779 | 42981101 | ELK 1101 | 8779 | FALSE | 6865.4129 | 6865.4129 | 4.2669 | 41 | 0.00012002 | 1187 | 1.8049 | 2849 | 8.9792e-05 | 0.0036815 | 2880 | 0.05 | 2060
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 3034 | TRUE | 31905.8871 | 80.3377 | 0.04993 | 193 | 4.5789e-05 | 3145 | 2.3733 | 2828 | 8.716e-05 | 0.016822 | 2881 | 0.02 | 2481
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 86032 | FALSE | 4656.0497 | 1615.684 | 1.0042 | 23 | 2.8164e-05 | 3455 | 3.5085 | 2793 | 8.538e-05 | 0.0019637 | 2882 | 0.82 | 770
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 922138 | FALSE | 3566.848 | 2524.6386 | 1.5691 | 24 | 4.9756e-05 | 3043 | 2.046 | 2840 | 8.4169e-05 | 0.00202 | 2883 |  | 3016
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 12106 | TRUE | 19539.3367 | 556.8348 | 0.34608 | 139 | 8.3645e-05 | 2105 | 0.75016 | 2905 | 8.0919e-05 | 0.011248 | 2884 | 0.06 | 1840
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 56774 | TRUE | 4425.2807 | 385.0871 | 0.23933 | 39 | 1.6584e-05 | 3572 | 2.9096 | 2814 | 7.8722e-05 | 0.0030702 | 2885 |  | 2668
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | CB | FALSE | 16799.2868 | 16799.2868 | 10.4408 | 132 | 9.6671e-05 | 1719 | 1.6868 | 2854 | 7.4597e-05 | 0.0098468 | 2886 | 0.13 | 1339
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 37088 | FALSE | 18269.9988 | 11434.4875 | 7.1066 | 135 | 4.8424e-05 | 3080 | 2.354 | 2829 | 7.338e-05 | 0.0099063 | 2887 | 0.04 | 2198
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1226 | FALSE | 12686.9371 | 2717.7424 | 1.6891 | 102 | 7.3175e-05 | 2391 | 0.9972 | 2892 | 7.0366e-05 | 0.0071773 | 2888 | 0.01 | 2602
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 279670 | FALSE | 7840.1687 | 6244.093 | 3.8807 | 54 | 9.3625e-05 | 1805 | 0.35903 | 2923 | 7.0093e-05 | 0.003785 | 2889 |  | 3141
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 103126 | TRUE | 487.0335 | 487.0335 | 0.30269 | 5 | 0.0010399 | 1 | 0.066432 | 2993 | 6.9083e-05 | 0.00034541 | 2890 |  | 3462
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 4639 | FALSE | 5228.1955 | 5228.1955 | 3.2493 | 44 | 0.00013355 | 950 | 1.1467 | 2885 | 6.7888e-05 | 0.0029871 | 2891 | 1.36 | 680
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 10141 | FALSE | 4694.7775 | 4694.7775 | 2.9178 | 21 | 5.6214e-05 | 2882 | 1.1979 | 2879 | 6.784e-05 | 0.0014246 | 2892 | 4.61 | 512
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 910 | FALSE | 11465.6942 | 2722.6312 | 1.6921 | 89 | 0.00012024 | 1182 | 0.77728 | 2903 | 6.6955e-05 | 0.005959 | 2893 | 0.04 | 2206
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 690098 | FALSE | 12079.1397 | 11883.9636 | 7.3859 | 108 | 8.8852e-05 | 1957 | 0.94645 | 2898 | 6.6684e-05 | 0.0072019 | 2894 |  | 2672
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 36656 | TRUE | 1041.7398 | 220.7989 | 0.13723 | 14 | 0.00098372 | 2 | 0.065517 | 3361 | 6.4706e-05 | 0.00090588 | 2895 |  | 3040
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | MR210 | FALSE | 12199.0798 | 1314.2646 | 0.81682 | 103 | 2.3777e-05 | 3506 | 0.99149 | 2893 | 6.2939e-05 | 0.0064828 | 2896 | 1.94 | 629
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | CR014 | FALSE | 16905.8619 | 16905.8619 | 10.5071 | 137 | 0.00013845 | 889 | 0.41497 | 2915 | 6.2366e-05 | 0.0085442 | 2897 | 0.99 | 734
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 65444 | TRUE | 757.2593 | 757.2593 | 0.47064 | 9 | 0.00091179 | 3 | 0.066431 | 3074 | 6.0572e-05 | 0.00054514 | 2898 | 12.01 | 379
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 528 | FALSE | 4980.15 | 2865.7848 | 1.7811 | 46 | 4.0677e-05 | 3254 | 1.441 | 2869 | 5.4065e-05 | 0.002487 | 2899 | 0.21 | 1140
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 189010 | TRUE | 84.167 | 59.0426 | 0.036695 | 4 | 0.000791 | 5 | 0.065792 | 3268 | 5.2348e-05 | 0.00020939 | 2900 |  | 3386
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 507513 | FALSE | 8339.9553 | 4803.4 | 2.9853 | 65 | 0.00010329 | 1564 | 1.1629 | 2884 | 4.9269e-05 | 0.0032025 | 2901 |  | 2887
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | L503R | FALSE | 6910.8038 | 6910.8038 | 4.2951 | 62 | 0.00010589 | 1498 | 0.83292 | 2901 | 4.8731e-05 | 0.0030213 | 2902 | 0.09 | 1547
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 590402 | FALSE | 9614.0154 | 3916.034 | 2.4338 | 78 | 5.9195e-05 | 2800 | 0.67392 | 2910 | 4.8446e-05 | 0.0037788 | 2903 |  | 3086
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 468200 | TRUE | 531.6801 | 531.6801 | 0.33044 | 4 | 0.00072422 | 6 | 0.066431 | 3033 | 4.8111e-05 | 0.00019244 | 2904 |  | 3132
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 5039 | TRUE | 4245.0462 | 0 | 0 | 28 | 7.2354e-05 | 2407 | 1.1951 | 2880 | 4.5334e-05 | 0.0012694 | 2905 |  | 3275
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 2486 | TRUE | 189.7916 | 146.4228 | 0.091002 | 2 | 0.00067148 | 8 | 0.065791 | 3270 | 4.4268e-05 | 8.8537e-05 | 2906 |  | 3565
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 828400 | TRUE | 50.1094 | 50.1094 | 0.031143 | 2 | 0.00066466 | 9 | 0.066431 | 3040 | 4.4154e-05 | 8.8308e-05 | 2907 |  | 3627
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 1362 | TRUE | 24.9514 | 24.9514 | 0.015507 | 1 | 0.00065973 | 10 | 0.066431 | 3035 | 4.3827e-05 | 4.3827e-05 | 2908 | 0.04 | 2068
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | BR194 | FALSE | 8491.9295 | 6148.6965 | 3.8214 | 74 | 6.6442e-05 | 2577 | 0.38709 | 2919 | 4.3185e-05 | 0.0031957 | 2909 | 0.12 | 1386
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 1212 | FALSE | 3248.6095 | 3232.6075 | 2.0091 | 33 | 0.00064007 | 12 | 0.066393 | 3123 | 4.2503e-05 | 0.0014026 | 2910 |  | 3117
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 10996 | FALSE | 1226.2093 | 1226.2093 | 0.76209 | 8 | 0.00063772 | 13 | 0.066431 | 3070 | 4.2365e-05 | 0.00033892 | 2911 | 3.1 | 562
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 99226 | FALSE | 5537.6206 | 1841.8715 | 1.1447 | 42 | 0.00062786 | 15 | 0.065639 | 3326 | 4.1187e-05 | 0.0017299 | 2912 |  | 3154
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 956 | FALSE | 19682.0883 | 18278.7267 | 11.3603 | 145 | 8.7665e-05 | 1994 | 0.39404 | 2918 | 4.0908e-05 | 0.0059316 | 2913 | 0.15 | 1277
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 5300 | FALSE | 15760.3239 | 15760.3239 | 9.7951 | 115 | 0.00020513 | 380 | 0.27315 | 2925 | 3.9714e-05 | 0.0045672 | 2914 |  | 2767
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 95050 | TRUE | 223.2117 | 223.2117 | 0.13873 | 5 | 0.00059508 | 17 | 0.066431 | 3081 | 3.9532e-05 | 0.00019766 | 2915 | 0.24 | 1092
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 7170 | FALSE | 8726.7127 | 8726.7127 | 5.4237 | 54 | 2.872e-05 | 3442 | 2.7066 | 2821 | 3.9493e-05 | 0.0021326 | 2916 | 0 | 2648
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 5400 | TRUE | 731.4241 | 731.4241 | 0.45458 | 4 | 0.00059378 | 18 | 0.066431 | 3083 | 3.9445e-05 | 0.00015778 | 2917 | 0.27 | 1057
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 38430 | FALSE | 10237.4777 | 6060.3575 | 3.7665 | 90 | 5.3215e-05 | 2959 | 0.59378 | 2912 | 3.7768e-05 | 0.0033991 | 2918 | 0.19 | 1175
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | CB | FALSE | 6247.2514 | 1003.198 | 0.62349 | 47 | 4.8424e-05 | 3081 | 0.73812 | 2907 | 3.5184e-05 | 0.0016536 | 2919 |  | 2772
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 449638 | TRUE | 41.9833 | 41.9833 | 0.026093 | 1 | 0.00016049 | 640 | 0.21903 | 2930 | 3.5151e-05 | 3.5151e-05 | 2920 |  | 2904
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 777484 | FALSE | 5712.0142 | 1455.0408 | 0.90431 | 50 | 1.3219e-05 | 3597 | 5.1374 | 2746 | 3.5066e-05 | 0.0017533 | 2921 |  | 2773
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 2534 | FALSE | 5245.4729 | 5105.9059 | 3.1733 | 49 | 0.00050354 | 30 | 0.066327 | 3143 | 3.3375e-05 | 0.0016354 | 2922 | 0.49 | 899
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | CB | TRUE | 6265.5755 | 560.1275 | 0.34812 | 51 | 1.5294e-05 | 3585 | 1.6186 | 2858 | 3.2507e-05 | 0.0016578 | 2923 | 0.17 | 1234
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 2488 | FALSE | 5690.0714 | 5690.0714 | 3.5364 | 47 | 0.0004856 | 34 | 0.066431 | 3043 | 3.2259e-05 | 0.0015162 | 2924 |  | 2916
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 181562 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00048291 | 37 | 0.066432 | 2996 | 3.208e-05 | 3.208e-05 | 2925 |  | 3615
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 283794 | FALSE | 4034.8507 | 3810.7404 | 2.3684 | 37 | 0.00048267 | 38 | 0.066328 | 3142 | 3.2004e-05 | 0.0011841 | 2926 |  | 2942
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 35592 | FALSE | 21129.6388 | 21129.6388 | 13.1322 | 149 | 0.00014429 | 808 | 0.38535 | 2920 | 3.1961e-05 | 0.0047622 | 2927 | 0.14 | 1329
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 3907 | FALSE | 1437.9091 | 1437.9091 | 0.89367 | 16 | 0.00047789 | 39 | 0.066432 | 3009 | 3.1747e-05 | 0.00050795 | 2928 | 0.56 | 864
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 3186 | FALSE | 15806.1877 | 15806.1877 | 9.8236 | 143 | 7.9358e-05 | 2223 | 0.39871 | 2917 | 3.1551e-05 | 0.0045118 | 2929 | 0.04 | 2226
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 435168 | FALSE | 2902.2955 | 2068.4077 | 1.2855 | 26 | 4.9503e-05 | 3049 | 0.97971 | 2895 | 3.1131e-05 | 0.00080941 | 2930 |  | 3011
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 244027 | TRUE | 620.9738 | 492.7502 | 0.30625 | 6 | 0.00047101 | 41 | 0.065791 | 3272 | 3.093e-05 | 0.00018558 | 2931 |  | 3214
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 95394 | TRUE | 790.3942 | 790.3942 | 0.49123 | 8 | 0.00046445 | 43 | 0.066431 | 3075 | 3.0854e-05 | 0.00024683 | 2932 | 8.99 | 417
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 36042 | FALSE | 14063.6211 | 13184.5103 | 8.1942 | 119 | 0.00046491 | 42 | 0.066335 | 3138 | 3.0817e-05 | 0.0036673 | 2933 |  | 2883
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 561686 | TRUE | 147.2029 | 147.2029 | 0.091487 | 1 | 0.00044669 | 47 | 0.066431 | 3105 | 2.9674e-05 | 2.9674e-05 | 2934 |  | 3430
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 16010 | FALSE | 2728.9115 | 2728.9115 | 1.696 | 25 | 0.00044502 | 49 | 0.066431 | 3054 | 2.9564e-05 | 0.00073909 | 2935 | 0.3 | 1015
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 38404 | FALSE | 9333.1056 | 5730.6143 | 3.5616 | 47 | 0.00010907 | 1427 | 0.73881 | 2906 | 2.9507e-05 | 0.0013868 | 2936 | 0.08 | 1611
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 395180 | FALSE | 2394.7505 | 2263.8752 | 1.407 | 20 | 1.6162e-05 | 3578 | 2.4421 | 2827 | 2.9412e-05 | 0.00058824 | 2937 |  | 3059
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 214052 | TRUE | 1011.6764 | 941.1587 | 0.58493 | 7 | 0.00044429 | 50 | 0.066065 | 3204 | 2.933e-05 | 0.00020531 | 2938 |  | 3447
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 176130 | TRUE | 32.0737 | 32.0737 | 0.019934 | 1 | 0.00044128 | 54 | 0.066432 | 3008 | 2.9315e-05 | 2.9315e-05 | 2939 |  | 3388
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | CB | TRUE | 225.7012 | 190.3788 | 0.11832 | 6 | 0.00043795 | 56 | 0.066004 | 3225 | 2.9049e-05 | 0.00017429 | 2940 | 0.17 | 1240
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | CB | FALSE | 5993.6916 | 2211.8341 | 1.3747 | 46 | 0.0004418 | 52 | 0.065541 | 3355 | 2.9018e-05 | 0.0013348 | 2941 | 4.56 | 515
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 969778 | FALSE | 1070.9786 | 1070.9786 | 0.66562 | 9 | 0.00042983 | 59 | 0.066432 | 3004 | 2.8554e-05 | 0.00025699 | 2942 |  | 3193
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 954322 | FALSE | 6923.0973 | 6923.0973 | 4.3027 | 63 | 0.0004268 | 60 | 0.066431 | 3044 | 2.8353e-05 | 0.0017862 | 2943 |  | 2742
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 5479 | TRUE | 289.2777 | 289.2777 | 0.17979 | 3 | 0.00041807 | 63 | 0.066431 | 3086 | 2.7773e-05 | 8.3319e-05 | 2944 | 2.14 | 619
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | BL 2101 | TRUE | 5.191 | 5.191 | 0.0032262 | 1 | 0.00041248 | 66 | 0.066431 | 3087 | 2.7401e-05 | 2.7401e-05 | 2945 | 6.05 | 475
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | CB | FALSE | 2742.3098 | 2742.3098 | 1.7044 | 19 | 0.00040765 | 67 | 0.066431 | 3078 | 2.7081e-05 | 0.00051453 | 2946 | 26.67 | 267
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 10722 | TRUE | 937.9448 | 937.9448 | 0.58294 | 9 | 0.00040174 | 68 | 0.066431 | 3060 | 2.6688e-05 | 0.00024019 | 2947 | 14.01 | 358
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | L510R | FALSE | 15698.8958 | 15538.9501 | 9.6575 | 136 | 8.2413e-05 | 2142 | 0.24129 | 2927 | 2.6158e-05 | 0.0035575 | 2948 | 0.21 | 1146
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 781318 | TRUE | 172.1377 | 172.1377 | 0.10698 | 3 | 0.00038201 | 74 | 0.066431 | 3034 | 2.5377e-05 | 7.6132e-05 | 2949 |  | 3210
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 53544 | FALSE | 1728.2043 | 1035.1182 | 0.64333 | 19 | 0.00038613 | 71 | 0.06569 | 3314 | 2.5314e-05 | 0.00048097 | 2950 |  | 2807
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | CB | TRUE | 10480.8911 | 272.5459 | 0.16939 | 83 | 4.1439e-05 | 3235 | 0.25769 | 2926 | 2.5206e-05 | 0.0020921 | 2951 | 5.67 | 480
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5146 | FALSE | 9534.7408 | 9534.7408 | 5.9259 | 63 | 0.00036971 | 78 | 0.066431 | 3063 | 2.4561e-05 | 0.0015473 | 2952 | 0.55 | 870
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 837904 | FALSE | 3252.9939 | 1669.2171 | 1.0374 | 25 | 3.8294e-05 | 3293 | 0.69841 | 2909 | 2.4435e-05 | 0.00061089 | 2953 |  | 2930
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 961990 | FALSE | 10972.2602 | 10972.2602 | 6.8193 | 91 | 0.00035642 | 85 | 0.066431 | 3018 | 2.3677e-05 | 0.0021547 | 2954 |  | 2984
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 772517 | FALSE | 2777.244 | 2777.244 | 1.7261 | 24 | 0.00035423 | 87 | 0.066378 | 3129 | 2.3519e-05 | 0.00056446 | 2955 |  | 3281
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | CB | FALSE | 12509.5528 | 12509.5528 | 7.7747 | 106 | 0.00034662 | 93 | 0.066431 | 3076 | 2.3026e-05 | 0.0024408 | 2956 | 1.58 | 665
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 528232 | TRUE | 149.6502 | 149.6502 | 0.093008 | 2 | 0.00033485 | 99 | 0.066432 | 3013 | 2.2245e-05 | 4.449e-05 | 2957 |  | 3604
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | CB | TRUE | 149.4178 | 149.4178 | 0.092864 | 2 | 0.00033388 | 100 | 0.066432 | 3002 | 2.218e-05 | 4.436e-05 | 2958 | 0.05 | 1937
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | V84 | TRUE | 15879.9521 | 369.7837 | 0.22982 | 126 | 7.2115e-06 | 3627 | 0.37923 | 2921 | 2.1832e-05 | 0.0027508 | 2959 |  | 2861
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | CB | FALSE | 2249.8408 | 2245.2688 | 1.3954 | 16 | 0.00032886 | 103 | 0.066351 | 3136 | 2.1827e-05 | 0.00034924 | 2960 | 0.1 | 1487
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 39126 | FALSE | 3634.7812 | 3634.7812 | 2.259 | 31 | 0.00031627 | 110 | 0.066431 | 3079 | 2.101e-05 | 0.00065131 | 2961 | 15.84 | 344
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 834583 | TRUE | 981.0329 | 981.0329 | 0.60972 | 7 | 0.00030071 | 130 | 0.066431 | 3073 | 1.9977e-05 | 0.00013984 | 2962 | 4.09 | 528
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 737512 | FALSE | 11180.7593 | 10917.3933 | 6.7852 | 89 | 0.0002931 | 137 | 0.066402 | 3118 | 1.9465e-05 | 0.0017324 | 2963 |  | 3008
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 11384 | FALSE | 8402.4777 | 8402.4777 | 5.2222 | 59 | 0.00028937 | 140 | 0.066431 | 3069 | 1.9223e-05 | 0.0011342 | 2964 | 13.77 | 362
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 762780 | TRUE | 1282.4551 | 400.767 | 0.24908 | 11 | 0.0002944 | 135 | 0.065383 | 3424 | 1.9222e-05 | 0.00021145 | 2965 |  | 3209
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 262343 | FALSE | 1232.8709 | 1232.8709 | 0.76623 | 11 | 0.00028891 | 143 | 0.066432 | 3003 | 1.9193e-05 | 0.00021112 | 2966 |  | 3404
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 9741 | FALSE | 1036.4661 | 1036.4661 | 0.64417 | 10 | 0.00028291 | 149 | 0.066431 | 3057 | 1.8794e-05 | 0.00018794 | 2967 | 14.27 | 356
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5028 | FALSE | 8087.7219 | 8087.7219 | 5.0266 | 59 | 0.00027873 | 160 | 0.066431 | 3056 | 1.8516e-05 | 0.0010925 | 2968 | 0.63 | 832
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 851116 | TRUE | 405.8442 | 316.0008 | 0.1964 | 4 | 0.00027959 | 155 | 0.066111 | 3190 | 1.8459e-05 | 7.3835e-05 | 2969 |  | 2981
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 926235 | TRUE | 416.1419 | 305.3669 | 0.18979 | 4 | 0.00027977 | 153 | 0.065791 | 3274 | 1.8372e-05 | 7.3487e-05 | 2970 |  | 3532
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 981056 | TRUE | 227.7546 | 132.017 | 0.082049 | 2 | 0.00027805 | 163 | 0.065789 | 3285 | 1.8259e-05 | 3.6518e-05 | 2971 |  | 3476
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 99658 | TRUE | 4406.3905 | 0 | 0 | 39 | 0.00027979 | 152 | 0.06515 | 3578 | 1.8228e-05 | 0.0007109 | 2972 | 0.05 | 2030
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 78862 | TRUE | 1804.4635 | 123.6088 | 0.076823 | 17 | 0.00027939 | 158 | 0.065225 | 3497 | 1.8213e-05 | 0.00030962 | 2973 | 5.76 | 478
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 12584 | FALSE | 41638.8897 | 5651.1648 | 3.5122 | 297 | 5.9861e-05 | 2779 | 0.22529 | 2929 | 1.8188e-05 | 0.0054019 | 2974 | 0.03 | 2245
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | V72 | FALSE | 14155.2453 | 9610.0836 | 5.9727 | 101 | 2.6938e-05 | 3473 | 1.494 | 2866 | 1.8115e-05 | 0.0018297 | 2975 | 0.05 | 1974
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 11006 | FALSE | 3281.0215 | 3281.0215 | 2.0392 | 24 | 0.00027097 | 170 | 0.066431 | 3059 | 1.8001e-05 | 0.00043202 | 2976 | 0.37 | 965
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 32.8824 | 32.8824 | 0.020437 | 1 | 0.00026849 | 175 | 0.066431 | 3046 | 1.7836e-05 | 1.7836e-05 | 2977 |  | 3493
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | CB | TRUE | 221.0797 | 221.0797 | 0.1374 | 2 | 0.0002671 | 177 | 0.066431 | 3047 | 1.7744e-05 | 3.5488e-05 | 2978 | 0.03 | 2339
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 710556 | TRUE | 81.8649 | 65.863 | 0.040934 | 2 | 0.00026928 | 174 | 0.065792 | 3269 | 1.7662e-05 | 3.5324e-05 | 2979 |  | 3566
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 958726 | FALSE | 1647.4395 | 1605.4653 | 0.9978 | 13 | 0.00026566 | 180 | 0.066333 | 3140 | 1.7619e-05 | 0.00022904 | 2980 |  | 2975
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 5401 | FALSE | 4047.5171 | 4047.5171 | 2.5155 | 34 | 0.0002635 | 187 | 0.066431 | 3064 | 1.7505e-05 | 0.00059516 | 2981 | 18.02 | 327
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | CB | TRUE | 158.4451 | 158.4451 | 0.098474 | 2 | 0.00026209 | 192 | 0.066431 | 3100 | 1.7411e-05 | 3.4822e-05 | 2982 | 0.02 | 2438
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 1064 | FALSE | 7144.3316 | 1005.39 | 0.62485 | 51 | 5.2154e-05 | 2989 | 0.37559 | 2922 | 1.7391e-05 | 0.00088693 | 2983 | 0.02 | 2426
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 761310 | TRUE | 43.1053 | 43.1053 | 0.02679 | 1 | 0.00026016 | 195 | 0.066432 | 3006 | 1.7283e-05 | 1.7283e-05 | 2984 | 9.94 | 403
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 5232 | FALSE | 7264.9547 | 7264.9547 | 4.5152 | 50 | 0.00025977 | 196 | 0.066431 | 3065 | 1.7257e-05 | 0.00086284 | 2985 | 0.52 | 889
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 956424 | FALSE | 2618.2583 | 1661.8272 | 1.0328 | 21 | 0.00026235 | 190 | 0.065882 | 3247 | 1.7224e-05 | 0.00036171 | 2986 |  | 3301
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 10786 | FALSE | 7392.1952 | 7392.1952 | 4.5943 | 58 | 0.00025715 | 199 | 0.066431 | 3068 | 1.7083e-05 | 0.0009908 | 2987 | 23.31 | 288
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 11048 | FALSE | 2138.5875 | 1473.7073 | 0.91592 | 19 | 0.00025575 | 204 | 0.065825 | 3261 | 1.6894e-05 | 0.00032099 | 2988 | 0.22 | 1122
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 100040 | FALSE | 1340.2293 | 1324.2274 | 0.82301 | 7 | 0.00025542 | 205 | 0.065698 | 3313 | 1.6779e-05 | 0.00011745 | 2989 |  | 3490
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 74170 | FALSE | 5752.9394 | 5752.9394 | 3.5755 | 43 | 0.00025227 | 211 | 0.066431 | 3071 | 1.6759e-05 | 0.00072063 | 2990 | 54.65 | 106
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | CB | TRUE | 89.3518 | 89.3518 | 0.055533 | 2 | 0.0002491 | 218 | 0.066431 | 3102 | 1.6548e-05 | 3.3096e-05 | 2991 | 0.02 | 2430
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 19732 | FALSE | 14898.6258 | 14898.6258 | 9.2596 | 125 | 0.00024625 | 229 | 0.066432 | 3015 | 1.6359e-05 | 0.0020448 | 2992 | 0.39 | 954
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 11044 | FALSE | 19649.9105 | 12291.7272 | 7.6394 | 144 | 0.00024668 | 228 | 0.06589 | 3246 | 1.6316e-05 | 0.0023496 | 2993 | 0.26 | 1067
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 357568 | FALSE | 3842.9954 | 1927.7671 | 1.1981 | 35 | 0.00024621 | 230 | 0.065663 | 3320 | 1.6214e-05 | 0.0005675 | 2994 |  | 2905
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 2651 | FALSE | 1316.7963 | 1238.5246 | 0.76975 | 10 | 0.00024324 | 237 | 0.066303 | 3149 | 1.6143e-05 | 0.00016143 | 2995 | 0.05 | 1964
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 837 | FALSE | 2514.1986 | 1083.651 | 0.67349 | 22 | 0.00024512 | 232 | 0.065733 | 3299 | 1.6143e-05 | 0.00035514 | 2996 | 0.03 | 2298
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 7401 | FALSE | 1710.0336 | 1710.0336 | 1.0628 | 12 | 0.00023873 | 251 | 0.066431 | 3026 | 1.5859e-05 | 0.00019031 | 2997 | 5.59 | 483
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 9773 | TRUE | 724.8545 | 724.8545 | 0.4505 | 6 | 0.00023796 | 254 | 0.066431 | 3077 | 1.5808e-05 | 9.4849e-05 | 2998 | 6.09 | 473
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 95576 | TRUE | 3539.5092 | 0 | 0 | 30 | 0.00024199 | 240 | 0.06515 | 3580 | 1.5765e-05 | 0.00047296 | 2999 | 0.02 | 2521
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 234378 | FALSE | 1230.3375 | 1030.7217 | 0.6406 | 13 | 0.00023818 | 253 | 0.065939 | 3237 | 1.5727e-05 | 0.00020445 | 3000 |  | 2969
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 11004 | FALSE | 6981.3249 | 6981.3249 | 4.3389 | 60 | 0.000234 | 264 | 0.066431 | 3053 | 1.5545e-05 | 0.00093268 | 3001 | 0.81 | 772
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 296428 | FALSE | 5326.8427 | 2768.6124 | 1.7207 | 14 | 0.00023533 | 262 | 0.065703 | 3308 | 1.5492e-05 | 0.00021689 | 3002 |  | 3554
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | CB | TRUE | 6762.3674 | 0 | 0 | 59 | 0.00023708 | 256 | 0.065169 | 3547 | 1.545e-05 | 0.00091153 | 3003 |  | 3195
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 50008 | FALSE | 7897.7178 | 1828.8508 | 1.1366 | 64 | 0.00023509 | 263 | 0.06535 | 3436 | 1.5377e-05 | 0.0009841 | 3004 | 0.7 | 810
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 910235 | TRUE | 1774.1223 | 851.0444 | 0.52893 | 16 | 0.00023372 | 267 | 0.065631 | 3328 | 1.5283e-05 | 0.00024453 | 3005 |  | 2923
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | LC26 | FALSE | 9057.4757 | 9057.4757 | 5.6293 | 74 | 0.00022734 | 294 | 0.066432 | 2991 | 1.5103e-05 | 0.0011176 | 3006 | 0.12 | 1372
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | CB | FALSE | 2889.8933 | 1390.1141 | 0.86396 | 28 | 0.0002292 | 288 | 0.065745 | 3295 | 1.5035e-05 | 0.00042097 | 3007 | 0.09 | 1554
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | CB | TRUE | 9322.594 | 131.7629 | 0.081891 | 81 | 0.00022849 | 289 | 0.065197 | 3511 | 1.4894e-05 | 0.0012064 | 3008 |  | 2874
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 64682 | FALSE | 2835.1135 | 2835.1135 | 1.762 | 22 | 0.00022403 | 304 | 0.066431 | 3092 | 1.4883e-05 | 0.00032742 | 3009 | 46.82 | 138
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 841 | FALSE | 1307.0396 | 1307.0396 | 0.81233 | 12 | 0.00022352 | 305 | 0.066431 | 3027 | 1.4849e-05 | 0.00017819 | 3010 | 0.34 | 982
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 546438 | FALSE | 1552.7497 | 1541.3848 | 0.95798 | 14 | 0.00022139 | 313 | 0.066248 | 3162 | 1.4698e-05 | 0.00020577 | 3011 |  | 3363
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 4913 | FALSE | 6065.3094 | 6065.3094 | 3.7696 | 54 | 1.9829e-05 | 3546 | 0.94688 | 2897 | 1.4645e-05 | 0.00079082 | 3012 | 0.02 | 2519
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | CR346 | TRUE | 330.9469 | 330.9469 | 0.20568 | 3 | 0.00021988 | 322 | 0.066432 | 2961 | 1.4607e-05 | 4.3821e-05 | 3013 | 0.27 | 1053
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 19562 | FALSE | 11663.8964 | 11663.8964 | 7.2492 | 98 | 0.00021832 | 327 | 0.066431 | 3051 | 1.4503e-05 | 0.0014213 | 3014 | 80.06 | 48
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | LA42 | FALSE | 4459.4554 | 4459.4554 | 2.7716 | 35 | 0.00021752 | 329 | 0.066431 | 3062 | 1.445e-05 | 0.00050575 | 3015 | 0.48 | 904
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 975350 | TRUE | 405.3394 | 73.1065 | 0.045436 | 3 | 0.00015577 | 686 | 0.090462 | 2933 | 1.4284e-05 | 4.2852e-05 | 3016 |  | 3591
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | CB | FALSE | 2054.39 | 1346.787 | 0.83703 | 15 | 0.00021376 | 344 | 0.065919 | 3239 | 1.4099e-05 | 0.00021149 | 3017 | 0.16 | 1250
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 920850 | TRUE | 514.6425 | 322.1994 | 0.20025 | 3 | 0.00021514 | 340 | 0.065576 | 3348 | 1.406e-05 | 4.2181e-05 | 3018 |  | 3600
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 8611 | FALSE | 2893.9317 | 2893.9317 | 1.7986 | 22 | 0.00020875 | 367 | 0.066432 | 3005 | 1.3867e-05 | 0.00030508 | 3019 | 0.05 | 1987
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 2043 | TRUE | 902.2238 | 902.2238 | 0.56074 | 8 | 0.00020837 | 369 | 0.066431 | 3028 | 1.3842e-05 | 0.00011074 | 3020 | 28.28 | 251
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 1247 | TRUE | 443.4693 | 443.4693 | 0.27562 | 3 | 0.00020644 | 376 | 0.066431 | 3039 | 1.3714e-05 | 4.1142e-05 | 3021 | 45.01 | 152
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 661309 | TRUE | 2205.0428 | 453.7966 | 0.28204 | 16 | 0.00020886 | 365 | 0.065469 | 3383 | 1.3667e-05 | 0.00021867 | 3022 |  | 3369
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 600529 | TRUE | 435.4123 | 422.8048 | 0.26277 | 4 | 0.00020229 | 388 | 0.066112 | 3188 | 1.3356e-05 | 5.3422e-05 | 3023 |  | 3471
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 968601 | TRUE | 12.2398 | 12.2398 | 0.0076071 | 1 | 0.00020045 | 395 | 0.066431 | 3041 | 1.3316e-05 | 1.3316e-05 | 3024 |  | 3573
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5696 | FALSE | 9835.0739 | 8152.2263 | 5.0666 | 90 | 0.00020042 | 396 | 0.066175 | 3179 | 1.3265e-05 | 0.0011939 | 3025 | 0.11 | 1418
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 216442 | TRUE | 327.4361 | 327.4361 | 0.2035 | 4 | 0.00012382 | 1123 | 0.10422 | 2932 | 1.2906e-05 | 5.1625e-05 | 3026 |  | 3403
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 7181 | FALSE | 1244.1443 | 1244.1443 | 0.77324 | 11 | 0.00019333 | 428 | 0.066432 | 3010 | 1.2843e-05 | 0.00014128 | 3027 | 7.1 | 450
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 7603 | FALSE | 1527.2306 | 1527.2306 | 0.94918 | 11 | 0.00019238 | 431 | 0.066431 | 3055 | 1.278e-05 | 0.00014058 | 3028 | 0.27 | 1054
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | LC24 | FALSE | 18535.4178 | 13258.5886 | 8.2403 | 154 | 0.00019316 | 429 | 0.066006 | 3215 | 1.2747e-05 | 0.001963 | 3029 | 0.08 | 1601
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 83424 | FALSE | 2603.9122 | 2600.4486 | 1.6162 | 7 | 0.00018902 | 446 | 0.066249 | 3161 | 1.2546e-05 | 8.7822e-05 | 3030 | 8.82 | 419
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 16000 | FALSE | 6212.4721 | 3353.5945 | 2.0843 | 51 | 0.000189 | 448 | 0.065804 | 3266 | 1.2496e-05 | 0.0006373 | 3031 | 13.79 | 361
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | CB | TRUE | 26.6683 | 26.6683 | 0.016574 | 1 | 0.00018686 | 464 | 0.066431 | 3104 | 1.2413e-05 | 1.2413e-05 | 3032 | 0.2 | 1169
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 344092 | TRUE | 131.1041 | 115.3192 | 0.071671 | 2 | 0.00018617 | 465 | 0.066431 | 3037 | 1.2368e-05 | 2.4736e-05 | 3033 |  | 3598
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 208930 | TRUE | 1425.5587 | 187.1265 | 0.1163 | 10 | 0.00018882 | 449 | 11.1381 | 2605 | 1.2302e-05 | 0.00012302 | 3034 |  | 2804
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 11172 | FALSE | 3921.2737 | 3218.2333 | 2.0001 | 38 | 0.00018146 | 501 | 0.066162 | 3181 | 1.2003e-05 | 0.00045612 | 3035 | 0.11 | 1424
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | CB | TRUE | 408.9065 | 408.9065 | 0.25414 | 4 | 0.0001783 | 516 | 0.066431 | 3029 | 1.1845e-05 | 4.7378e-05 | 3036 | 13.33 | 366
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | LA46 | FALSE | 2411.7925 | 2411.7925 | 1.4989 | 20 | 0.00017602 | 522 | 0.066431 | 3058 | 1.1694e-05 | 0.00023387 | 3037 | 19.55 | 311
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 463510 | FALSE | 4881.4666 | 4697.8741 | 2.9197 | 41 | 0.0001755 | 524 | 0.066369 | 3132 | 1.1648e-05 | 0.00047756 | 3038 |  | 3239
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 8898 | FALSE | 1034.8013 | 1034.8013 | 0.64313 | 9 | 0.00017399 | 534 | 0.066431 | 3061 | 1.1558e-05 | 0.00010403 | 3039 | 0.71 | 804
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | MR359 | TRUE | 10891.9524 | 0 | 0 | 90 | 2.5295e-05 | 3493 | 0.41659 | 2914 | 1.1476e-05 | 0.0010328 | 3040 |  | 2849
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 92868 | TRUE | 1050.3516 | 203.5363 | 0.1265 | 14 | 0.00017449 | 531 | 0.065522 | 3360 | 1.1443e-05 | 0.0001602 | 3041 | 0.39 | 955
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 391688 | FALSE | 2071.721 | 2071.721 | 1.2876 | 16 | 0.00017212 | 549 | 0.066431 | 3109 | 1.1434e-05 | 0.00018295 | 3042 |  | 2694
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 55638 | FALSE | 5639.9215 | 2949.5648 | 1.8332 | 42 | 0.00017356 | 537 | 0.065698 | 3312 | 1.1416e-05 | 0.00047946 | 3043 | 0.27 | 1049
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | W503R | TRUE | 12304.5424 | 121.8736 | 0.075745 | 89 | 1.999e-05 | 3544 | 0.42059 | 2913 | 1.1363e-05 | 0.0010113 | 3044 |  | 2765
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 409224 | TRUE | 353.3451 | 138.7205 | 0.086215 | 4 | 0.0001558 | 685 | 0.071835 | 2942 | 1.131e-05 | 4.524e-05 | 3045 |  | 3518
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 38684 | TRUE | 100.1157 | 38.3974 | 0.023864 | 1 | 0.00017305 | 542 | 0.065149 | 3581 | 1.1274e-05 | 1.1274e-05 | 3046 | 0.02 | 2437
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 506 | FALSE | 2021.7882 | 2021.7882 | 1.2565 | 18 | 0.00016864 | 571 | 0.066431 | 3019 | 1.1203e-05 | 0.00020165 | 3047 | 19.11 | 314
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 2299 | FALSE | 2927.8179 | 2927.8179 | 1.8197 | 25 | 0.00016866 | 570 | 0.06638 | 3127 | 1.1198e-05 | 0.00027996 | 3048 | 3.04 | 566
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 8752 | FALSE | 2987.795 | 2987.795 | 1.8569 | 32 | 0.00016401 | 600 | 0.066391 | 3124 | 1.0889e-05 | 0.00034845 | 3049 | 0.14 | 1308
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 10946 | FALSE | 13600.904 | 9098.3132 | 5.6546 | 112 | 0.00016435 | 595 | 0.06595 | 3235 | 1.0851e-05 | 0.0012153 | 3050 | 0.4 | 945
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | CR214 | FALSE | 4637.1496 | 4637.1496 | 2.882 | 35 | 0.00016318 | 609 | 0.066431 | 3098 | 1.0841e-05 | 0.00037942 | 3051 | 26.71 | 265
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | CR288 | FALSE | 4382.4988 | 4382.4988 | 2.7237 | 46 | 0.00016278 | 615 | 0.066431 | 3090 | 1.0814e-05 | 0.00049744 | 3052 | 0.78 | 779
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | CR022 | FALSE | 6467.1642 | 6467.1642 | 4.0194 | 48 | 0.00016152 | 625 | 0.066431 | 3103 | 1.073e-05 | 0.00051505 | 3053 | 12.67 | 369
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 1101/2 | TRUE | 31.1897 | 31.1897 | 0.019385 | 1 | 0.00016141 | 627 | 0.066431 | 3050 | 1.0723e-05 | 1.0723e-05 | 3054 |  | 3431
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 496570 | TRUE | 701.3537 | 389.3118 | 0.24196 | 8 | 0.00016262 | 617 | 0.065632 | 3327 | 1.0717e-05 | 8.5734e-05 | 3055 |  | 3421
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 250 | FALSE | 1985.3414 | 1985.3414 | 1.2339 | 14 | 0.0001605 | 639 | 0.066431 | 3020 | 1.0662e-05 | 0.00014927 | 3056 | 12.63 | 371
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 390720 | TRUE | 218.4469 | 202.4448 | 0.12582 | 2 | 0.00015881 | 655 | 0.066432 | 2955 | 1.055e-05 | 2.11e-05 | 3057 |  | 3617
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 1262 | FALSE | 7115.8815 | 6311.248 | 3.9225 | 57 | 0.00015861 | 656 | 0.066252 | 3160 | 1.0529e-05 | 0.00060016 | 3058 | 0.45 | 914
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 250129 | TRUE | 467.9989 | 401.6728 | 0.24964 | 5 | 0.00015745 | 668 | 0.066432 | 2964 | 1.046e-05 | 5.23e-05 | 3059 |  | 3307
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | CB | FALSE | 3786.5637 | 1101.4532 | 0.68456 | 37 | 0.00015882 | 654 | 0.065393 | 3421 | 1.0397e-05 | 0.00038468 | 3060 | 0.08 | 1623
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 451760 | TRUE | 98.2563 | 98.2563 | 0.061067 | 2 | 0.000155 | 694 | 0.066432 | 2956 | 1.0297e-05 | 2.0594e-05 | 3061 |  | 3571
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 210 | FALSE | 12611.9142 | 10477.8716 | 6.512 | 107 | 0.00015483 | 696 | 0.066181 | 3174 | 1.0255e-05 | 0.0010973 | 3062 | 0.61 | 845
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 79118 | TRUE | 31.1564 | 31.1564 | 0.019364 | 2 | 0.00015411 | 704 | 0.066431 | 3084 | 1.0238e-05 | 2.0475e-05 | 3063 | 13.07 | 367
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 212 | FALSE | 3618.1725 | 3618.1725 | 2.2487 | 27 | 0.00015405 | 705 | 0.066431 | 3024 | 1.0234e-05 | 0.00027631 | 3064 | 26.95 | 263
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 1625 | FALSE | 1400.9701 | 1400.9701 | 0.87071 | 10 | 0.00015401 | 706 | 0.066431 | 3067 | 1.0231e-05 | 0.00010231 | 3065 | 45.14 | 150
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 104220 | FALSE | 5237.7249 | 1476.8749 | 0.91788 | 45 | 0.00015541 | 691 | 0.065461 | 3392 | 1.0177e-05 | 0.00045796 | 3066 |  | 3107
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | CB | FALSE | 12682.0012 | 7810.3005 | 4.8541 | 107 | 0.00015094 | 728 | 0.065845 | 3256 | 9.9897e-06 | 0.0010689 | 3067 | 0.33 | 987
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | CR204 | FALSE | 6639.5298 | 6639.5298 | 4.1265 | 49 | 0.00015005 | 734 | 0.066431 | 3107 | 9.9677e-06 | 0.00048842 | 3068 | 0.48 | 901
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | CB | TRUE | 191.1806 | 191.1806 | 0.11882 | 2 | 0.00014987 | 738 | 0.066432 | 3011 | 9.9558e-06 | 1.9912e-05 | 3069 | 0.03 | 2348
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | CR178 | TRUE | 529.8862 | 529.8862 | 0.32933 | 7 | 0.00014846 | 758 | 0.066432 | 2953 | 9.8623e-06 | 6.9036e-05 | 3070 | 0.29 | 1028
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | CB | TRUE | 14599.8126 | 271.1511 | 0.16852 | 108 | 0.00013381 | 947 | 0.073352 | 2938 | 9.8448e-06 | 0.0010632 | 3071 | 0.04 | 2189
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 51474 | TRUE | 7519.049 | 594.1189 | 0.36925 | 68 | 0.00015085 | 730 | 0.065188 | 3526 | 9.839e-06 | 0.00066905 | 3072 | 0.02 | 2433
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 932140 | TRUE | 1542.2382 | 861.7057 | 0.53555 | 15 | 0.00014685 | 774 | 0.065836 | 3258 | 9.669e-06 | 0.00014503 | 3073 |  | 2908
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | CB | TRUE | 11988.7275 | 167.7195 | 0.10424 | 114 | 0.00014824 | 761 | 0.06517 | 3545 | 9.6632e-06 | 0.0011016 | 3074 | 0.07 | 1673
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 532 | TRUE | 844.3261 | 844.3261 | 0.52475 | 8 | 0.00014487 | 803 | 0.066431 | 3021 | 9.6241e-06 | 7.6993e-05 | 3075 | 27.34 | 259
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | CB | FALSE | 3812.8299 | 1129.2677 | 0.70184 | 32 | 0.00014601 | 789 | 0.06551 | 3366 | 9.5675e-06 | 0.00030616 | 3076 | 0.04 | 2130
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 6129 | FALSE | 5155.4944 | 5155.4944 | 3.2042 | 39 | 0.0001435 | 819 | 0.066432 | 3007 | 9.5328e-06 | 0.00037178 | 3077 | 0.06 | 1793
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | CB | TRUE | 35.3815 | 35.3815 | 0.02199 | 1 | 0.00014293 | 826 | 0.066432 | 2990 | 9.4951e-06 | 9.4951e-06 | 3078 | 0.05 | 1945
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | CB | FALSE | 22008.731 | 1759.2867 | 1.0934 | 102 | 0.00014538 | 799 | 0.065157 | 3559 | 9.4726e-06 | 0.0009662 | 3079 | 0.03 | 2325
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 5026 | FALSE | 2967.0616 | 2967.0616 | 1.844 | 23 | 0.00014253 | 832 | 0.066431 | 3023 | 9.4686e-06 | 0.00021778 | 3080 | 0.35 | 976
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 379946 | FALSE | 2891.0032 | 1211.8313 | 0.75316 | 15 | 0.00014448 | 805 | 0.06515 | 3577 | 9.4131e-06 | 0.0001412 | 3081 |  | 3120
8927 | ELK 1101CB | 42981101 | ELK 1101 | CB | TRUE | 39.9198 | 39.9198 | 0.02481 | 1 | 0.0001444 | 807 | 0.065148 | 3597 | 9.4072e-06 | 9.4072e-06 | 3082 | 0.01 | 2574
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 296476 | FALSE | 1196.6443 | 1061.0328 | 0.65944 | 11 | 0.00014203 | 839 | 0.065849 | 3254 | 9.3993e-06 | 0.00010339 | 3083 |  | 3030
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 297538 | FALSE | 1703.5587 | 1703.5587 | 1.0588 | 15 | 0.000141 | 854 | 0.066432 | 3014 | 9.367e-06 | 0.0001405 | 3084 |  | 3160
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 337226 | TRUE | 1293.8077 | 458.4827 | 0.28495 | 13 | 0.00014222 | 835 | 0.065742 | 3297 | 9.3615e-06 | 0.0001217 | 3085 |  | 2998
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | CB | TRUE | 10759.641 | 358.8557 | 0.22303 | 85 | 0.00014251 | 833 | 0.065166 | 3549 | 9.286e-06 | 0.00078931 | 3086 | 0.26 | 1071
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 51478 | TRUE | 90.198 | 81.0541 | 0.050375 | 3 | 0.00014054 | 863 | 0.065577 | 3343 | 9.2483e-06 | 2.7745e-05 | 3087 | 1.23 | 697
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | CB | FALSE | 11489.4556 | 2237.7238 | 1.3908 | 99 | 0.00014106 | 853 | 0.065344 | 3440 | 9.2292e-06 | 0.00091369 | 3088 | 0.02 | 2562
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | BR166 | TRUE | 61.4345 | 61.4345 | 0.038182 | 2 | 0.00013883 | 886 | 0.066432 | 2952 | 9.2229e-06 | 1.8446e-05 | 3089 | 0.05 | 1939
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | CB | TRUE | 10445.4547 | 0 | 0 | 86 | 0.00014143 | 846 | 0.065148 | 3602 | 9.2139e-06 | 0.0007924 | 3090 | 0.28 | 1040
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 241646 | TRUE | 2237.0921 | 583.4204 | 0.3626 | 13 | 0.00014029 | 866 | 0.065148 | 3600 | 9.1396e-06 | 0.00011881 | 3091 |  | 3536
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 91742 | FALSE | 7594.7858 | 3844.7445 | 2.3895 | 67 | 0.00013708 | 906 | 0.065724 | 3302 | 9.0186e-06 | 0.00060425 | 3092 | 0.12 | 1387
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 3820 | TRUE | 23262.4232 | 0 | 0 | 115 | 0.0001364 | 914 | 0.065808 | 3265 | 8.9864e-06 | 0.0010334 | 3093 | 0.02 | 2422
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 209146 | FALSE | 9672.039 | 4936.2554 | 3.0679 | 85 | 0.00013627 | 917 | 0.065797 | 3267 | 8.9692e-06 | 0.00076238 | 3094 |  | 2810
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 1780 | TRUE | 115.3297 | 115.3297 | 0.071678 | 1 | 0.00013489 | 928 | 0.06643 | 3113 | 8.9608e-06 | 8.9608e-06 | 3095 | 0.87 | 761
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 328808 | TRUE | 186.4686 | 186.4686 | 0.11589 | 1 | 0.00013477 | 930 | 0.066432 | 2960 | 8.9528e-06 | 8.9528e-06 | 3096 |  | 3574
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 6219 | FALSE | 1488.6262 | 1488.6262 | 0.92519 | 11 | 0.00013222 | 978 | 0.066431 | 3066 | 8.7836e-06 | 9.662e-05 | 3097 | 7 | 455
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 184814 | TRUE | 2352.3551 | 682.245 | 0.42402 | 20 | 0.00013241 | 973 | 0.065475 | 3379 | 8.707e-06 | 0.00017414 | 3098 |  | 2762
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 832694 | TRUE | 477.5655 | 461.5634 | 0.28686 | 5 | 0.0001169 | 1251 | 0.073805 | 2937 | 8.7057e-06 | 4.3529e-05 | 3099 |  | 3535
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 35934 | TRUE | 5459.9113 | 78.4109 | 0.048733 | 46 | 0.00013282 | 962 | 0.065203 | 3509 | 8.6658e-06 | 0.00039863 | 3100 |  | 2806
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 490728 | FALSE | 1414.5018 | 1044.2482 | 0.649 | 11 | 0.00013128 | 992 | 0.065966 | 3228 | 8.6628e-06 | 9.5291e-05 | 3101 |  | 2925
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 798018 | FALSE | 1485.4108 | 1448.3137 | 0.90013 | 13 | 0.0001303 | 1006 | 0.066234 | 3166 | 8.6422e-06 | 0.00011235 | 3102 |  | 3340
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | CB | TRUE | 1752.4587 | 342.98 | 0.21316 | 11 | 0.00013264 | 969 | 0.065147 | 3621 | 8.6414e-06 | 9.5055e-05 | 3103 |  | 3350
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 894156 | TRUE | 625.3701 | 625.3701 | 0.38867 | 4 | 0.0001303 | 1005 | 0.066111 | 3196 | 8.6111e-06 | 3.4445e-05 | 3104 |  | 3450
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 718674 | FALSE | 1848.6771 | 1301.8094 | 0.80908 | 16 | 0.0001305 | 1001 | 0.065951 | 3233 | 8.6092e-06 | 0.00013775 | 3105 |  | 3168
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 610322 | TRUE | 220.6867 | 220.6867 | 0.13716 | 3 | 0.00012983 | 1012 | 0.066004 | 3217 | 8.5935e-06 | 2.578e-05 | 3106 |  | 3607
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 9658 | TRUE | 156.0125 | 156.0125 | 0.096962 | 3 | 0.00012787 | 1049 | 0.066432 | 2984 | 8.4949e-06 | 2.5485e-05 | 3107 | 0.04 | 2071
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | CR206 | FALSE | 2877.1568 | 2877.1568 | 1.7882 | 22 | 0.00012717 | 1061 | 0.066431 | 3108 | 8.4479e-06 | 0.00018585 | 3108 | 0.28 | 1042
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 5291 | TRUE | 1596.261 | 50.439 | 0.031348 | 14 | 0.00012858 | 1037 | 0.065239 | 3485 | 8.4226e-06 | 0.00011792 | 3109 |  | 3053
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 5404 | FALSE | 7456.6431 | 4377.7978 | 2.7208 | 63 | 0.00012738 | 1057 | 0.065779 | 3291 | 8.4149e-06 | 0.00053014 | 3110 | 0.15 | 1284
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 205854 | TRUE | 505.1079 | 505.1079 | 0.31393 | 5 | 0.00012714 | 1063 | 0.065923 | 3238 | 8.3652e-06 | 4.1826e-05 | 3111 |  | 3625
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 5402 | FALSE | 10826.3428 | 4595.9767 | 2.8564 | 87 | 0.0001269 | 1066 | 0.065546 | 3353 | 8.3234e-06 | 0.00072413 | 3112 | 0.19 | 1181
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 431214 | TRUE | 794.6731 | 500.3272 | 0.31096 | 9 | 0.00012639 | 1076 | 0.065861 | 3253 | 8.308e-06 | 7.4772e-05 | 3113 |  | 3396
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 158468 | FALSE | 1388.9106 | 1120.0792 | 0.69613 | 11 | 0.00012572 | 1083 | 0.066083 | 3201 | 8.3063e-06 | 9.1369e-05 | 3114 |  | 3084
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 816 | FALSE | 4123.7572 | 3941.7419 | 2.4498 | 29 | 0.00012427 | 1112 | 0.066299 | 3150 | 8.2407e-06 | 0.00023898 | 3115 | 0.05 | 2024
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | N510R | TRUE | 1403.237 | 401.7471 | 0.24969 | 15 | 0.00012562 | 1086 | 0.065412 | 3409 | 8.2224e-06 | 0.00012334 | 3116 | 0.19 | 1183
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 798032 | TRUE | 259.8305 | 244.5065 | 0.15196 | 2 | 0.00012449 | 1108 | 0.065789 | 3287 | 8.1969e-06 | 1.6394e-05 | 3117 |  | 3569
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 2062 | FALSE | 8420.6852 | 2556.2544 | 1.5887 | 83 | 0.00012402 | 1119 | 0.065581 | 3338 | 8.1613e-06 | 0.00067739 | 3118 | 0.04 | 2221
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 1457 | FALSE | 1229.3805 | 1229.3805 | 0.76406 | 9 | 0.00012274 | 1137 | 0.066431 | 3025 | 8.1539e-06 | 7.3385e-05 | 3119 | 0.27 | 1047
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 967039 | TRUE | 469.6042 | 292.9124 | 0.18205 | 3 | 0.00012406 | 1117 | 0.065578 | 3342 | 8.139e-06 | 2.4417e-05 | 3120 |  | 3394
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | CR102 | TRUE | 316.3322 | 316.3322 | 0.1966 | 6 | 0.00012168 | 1153 | 0.066431 | 3101 | 8.0835e-06 | 4.8501e-05 | 3121 | 0.08 | 1651
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 960240 | TRUE | 816.2732 | 816.2732 | 0.50732 | 5 | 0.00012223 | 1144 | 0.066176 | 3175 | 8.0789e-06 | 4.0394e-05 | 3122 |  | 3597
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 531976 | FALSE | 2102.4835 | 2102.4835 | 1.3067 | 17 | 0.00012078 | 1169 | 0.066431 | 3080 | 8.0236e-06 | 0.0001364 | 3123 |  | 3322
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 36.9839 | 36.9839 | 0.022986 | 1 | 0.00012061 | 1175 | 0.066431 | 3045 | 8.0126e-06 | 8.0126e-06 | 3124 |  | 3540
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 284356 | TRUE | 325.8775 | 218.127 | 0.13557 | 4 | 0.00012158 | 1155 | 0.066111 | 3192 | 7.9902e-06 | 3.1961e-05 | 3125 |  | 3341
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | CR101 | TRUE | 28.3921 | 28.3921 | 0.017646 | 1 | 0.00011894 | 1208 | 0.066432 | 2948 | 7.9011e-06 | 7.9011e-06 | 3126 | 0.27 | 1055
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | CR224 | TRUE | 1656.0037 | 656.3547 | 0.40793 | 17 | 0.00012031 | 1179 | 0.065676 | 3317 | 7.8938e-06 | 0.0001342 | 3127 | 0.04 | 2180
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 441010 | TRUE | 1310.5118 | 592.4873 | 0.36823 | 4 | 6.8458e-05 | 2523 | 0.11315 | 2931 | 7.8772e-06 | 3.1509e-05 | 3128 |  | 3562
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 535284 | TRUE | 913.1511 | 10.8615 | 0.0067505 | 9 | 0.00012012 | 1185 | 0.065436 | 3401 | 7.8608e-06 | 7.0747e-05 | 3129 |  | 2746
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 8746 | TRUE | 832.2162 | 645.6965 | 0.4013 | 8 | 0.00011829 | 1225 | 0.06579 | 3278 | 7.8216e-06 | 6.2573e-05 | 3130 | 0.55 | 867
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 60052 | FALSE | 3169.0097 | 3169.0097 | 1.9696 | 28 | 0.00011748 | 1236 | 0.066432 | 3001 | 7.8045e-06 | 0.00021853 | 3131 | 0.05 | 1976
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 75210 | TRUE | 618.926 | 618.926 | 0.38467 | 6 | 0.00011638 | 1261 | 0.066432 | 2967 | 7.7312e-06 | 4.6387e-05 | 3132 | 0.05 | 2048
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | CR008 | FALSE | 7178.6151 | 7178.6151 | 4.4615 | 65 | 0.00011602 | 1269 | 0.066431 | 3099 | 7.7074e-06 | 0.00050098 | 3133 | 0.17 | 1230
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 2213 | TRUE | 689.8513 | 689.8513 | 0.42875 | 6 | 0.00011622 | 1265 | 0.066218 | 3167 | 7.6893e-06 | 4.6136e-05 | 3134 | 0.02 | 2454
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 553571 | TRUE | 319.9061 | 174.9029 | 0.1087 | 4 | 0.00011616 | 1267 | 0.065791 | 3271 | 7.6617e-06 | 3.0647e-05 | 3135 |  | 3296
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | CB | TRUE | 64360.3141 | 0 | 0 | 374 | 0.00011744 | 1237 | 0.065148 | 3603 | 7.6507e-06 | 0.0028614 | 3136 |  | 2721
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 60082 | TRUE | 6614.3058 | 0 | 0 | 57 | 0.00011735 | 1238 | 0.06517 | 3546 | 7.6477e-06 | 0.00043592 | 3137 |  | 2780
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 327226 | TRUE | 144.3861 | 79.5833 | 0.049461 | 2 | 0.0001161 | 1268 | 0.065791 | 3273 | 7.6459e-06 | 1.5292e-05 | 3138 |  | 3458
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 90846 | TRUE | 149.205 | 149.205 | 0.092731 | 2 | 0.00011453 | 1306 | 0.066431 | 3082 | 7.6083e-06 | 1.5217e-05 | 3139 | 0.01 | 2578
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 787007 | TRUE | 354.8281 | 307.1886 | 0.19092 | 5 | 0.00010238 | 1593 | 0.070735 | 2943 | 7.5915e-06 | 3.7958e-05 | 3140 |  | 3398
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | CB | FALSE | 2354.3543 | 1281.2412 | 0.7963 | 18 | 0.00011498 | 1299 | 0.065789 | 3286 | 7.5882e-06 | 0.00013659 | 3141 | 0.02 | 2484
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | CB | FALSE | 5901.3044 | 5623.7964 | 3.4952 | 45 | 0.00011418 | 1316 | 0.066318 | 3144 | 7.5759e-06 | 0.00034092 | 3142 | 0.06 | 1823
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 645092 | FALSE | 2229.6022 | 2229.6022 | 1.3857 | 16 | 0.0001137 | 1326 | 0.066352 | 3135 | 7.5529e-06 | 0.00012085 | 3143 |  | 3010
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 84640 | TRUE | 1219.4213 | 660.5476 | 0.41053 | 14 | 0.00011439 | 1310 | 0.06579 | 3276 | 7.5307e-06 | 0.00010543 | 3144 | 0.06 | 1834
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | CB | TRUE | 80.9954 | 80.9954 | 0.050339 | 3 | 0.00011256 | 1354 | 0.066431 | 3089 | 7.4775e-06 | 2.2433e-05 | 3145 | 0.03 | 2362
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 658899 | TRUE | 987.2682 | 941.3759 | 0.58507 | 8 | 0.00011266 | 1349 | 0.066271 | 3156 | 7.4661e-06 | 5.9729e-05 | 3146 |  | 2819
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 814784 | TRUE | 296.0572 | 280.0552 | 0.17406 | 3 | 0.00011354 | 1332 | 0.066004 | 3223 | 7.4475e-06 | 2.2342e-05 | 3147 |  | 3559
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | CR266 | FALSE | 1901.6084 | 1901.6084 | 1.1819 | 8 | 0.00011171 | 1375 | 0.066431 | 3110 | 7.421e-06 | 5.9368e-05 | 3148 | 23 | 290
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 6867 | TRUE | 1328.3948 | 985.9493 | 0.61277 | 11 | 0.00011216 | 1362 | 0.066081 | 3202 | 7.4136e-06 | 8.155e-05 | 3149 | 0.06 | 1791
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 9052 | FALSE | 8315.3581 | 7722.3255 | 4.7995 | 65 | 0.00011158 | 1380 | 0.066333 | 3139 | 7.4082e-06 | 0.00048153 | 3150 | 0.1 | 1459
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 296894 | TRUE | 465.5322 | 278.1636 | 0.17288 | 6 | 0.00011252 | 1355 | 0.065577 | 3344 | 7.398e-06 | 4.4388e-05 | 3151 |  | 3312
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 407286 | TRUE | 98.0196 | 98.0196 | 0.06092 | 1 | 0.00011059 | 1398 | 0.066431 | 3111 | 7.3466e-06 | 7.3466e-06 | 3152 |  | 3557
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 705523 | TRUE | 1068.2355 | 321.9298 | 0.20008 | 11 | 0.00011081 | 1395 | 0.065615 | 3332 | 7.293e-06 | 8.0224e-05 | 3153 |  | 3044
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 183888 | FALSE | 4871.8577 | 1898.9745 | 1.1802 | 43 | 0.00011047 | 1402 | 0.065447 | 3396 | 7.2344e-06 | 0.00031108 | 3154 |  | 2846
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 892332 | TRUE | 410.223 | 410.223 | 0.25496 | 4 | 0.00010843 | 1438 | 0.066432 | 2994 | 7.2035e-06 | 2.8814e-05 | 3155 |  | 3332
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | CR312 | FALSE | 5934.1286 | 5934.1286 | 3.6881 | 42 | 0.00010828 | 1446 | 0.066401 | 3119 | 7.189e-06 | 0.00030194 | 3156 | 0.12 | 1375
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 191725 | TRUE | 766.9235 | 558.1402 | 0.34689 | 8 | 0.00010854 | 1435 | 0.066111 | 3189 | 7.1671e-06 | 5.7337e-05 | 3157 |  | 2999
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 394169 | TRUE | 962.9958 | 642.0804 | 0.39906 | 7 | 0.00010894 | 1428 | 0.065699 | 3310 | 7.1481e-06 | 5.0037e-05 | 3158 |  | 3287
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 380760 | FALSE | 1136.5362 | 1053.0262 | 0.65446 | 12 | 0.00010812 | 1448 | 0.066113 | 3186 | 7.1451e-06 | 8.5741e-05 | 3159 |  | 3461
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | CR188 | FALSE | 5760.2047 | 5760.2047 | 3.58 | 47 | 0.00010753 | 1463 | 0.066431 | 3016 | 7.1432e-06 | 0.00033573 | 3160 | 0.38 | 960
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 983580 | FALSE | 4036.4763 | 3958.5011 | 2.4602 | 33 | 0.00010756 | 1462 | 0.066393 | 3122 | 7.1402e-06 | 0.00023563 | 3161 |  | 3159
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | CR326 | FALSE | 2098.9601 | 2098.9601 | 1.3045 | 17 | 0.00010686 | 1482 | 0.066431 | 3106 | 7.0989e-06 | 0.00012068 | 3162 | 16.75 | 337
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 618957 | TRUE | 394.8447 | 301.119 | 0.18715 | 4 | 0.00010843 | 1439 | 0.065151 | 3574 | 7.0643e-06 | 2.8257e-05 | 3163 |  | 3555
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 302192 | TRUE | 22573.2133 | 0 | 0 | 79 | 0.00010836 | 1443 | 0.065152 | 3561 | 7.0599e-06 | 0.00055773 | 3164 | 0.74 | 793
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 432850 | FALSE | 1988.3274 | 1988.3274 | 1.2358 | 26 | 0.0001052 | 1514 | 0.066431 | 3017 | 6.9884e-06 | 0.0001817 | 3165 |  | 2834
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 2204 | TRUE | 592.6413 | 592.6413 | 0.36833 | 8 | 0.00010504 | 1526 | 0.066432 | 2980 | 6.9782e-06 | 5.5825e-05 | 3166 | 0.04 | 2073
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 813976 | TRUE | 328.1808 | 312.2978 | 0.19409 | 4 | 0.00010513 | 1520 | 0.066111 | 3194 | 6.9422e-06 | 2.7769e-05 | 3167 |  | 3515
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | CB | TRUE | 17820.8713 | 0 | 0 | 150 | 0.00010626 | 1491 | 0.065148 | 3591 | 6.9228e-06 | 0.0010384 | 3168 |  | 2669
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 111666 | TRUE | 1605.5548 | 182.6023 | 0.11349 | 13 | 0.00010584 | 1499 | 0.06525 | 3479 | 6.9214e-06 | 8.9978e-05 | 3169 |  | 2676
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 6627 | TRUE | 910.3808 | 910.3808 | 0.56581 | 8 | 0.00010404 | 1550 | 0.066431 | 3048 | 6.9114e-06 | 5.5291e-05 | 3170 | 0.03 | 2267
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 68970 | TRUE | 5207.2001 | 75.6257 | 0.047002 | 44 | 0.00010579 | 1501 | 0.065151 | 3565 | 6.892e-06 | 0.00030325 | 3171 | 0.08 | 1617
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 489276 | TRUE | 1058.1278 | 723.7002 | 0.44978 | 9 | 0.00010344 | 1561 | 0.066147 | 3182 | 6.8546e-06 | 6.1691e-05 | 3172 |  | 3253
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 71630 | FALSE | 3041.9597 | 2182.1843 | 1.3562 | 26 | 0.00010295 | 1569 | 0.066037 | 3211 | 6.8241e-06 | 0.00017743 | 3173 | 0.21 | 1143
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | LC22 | FALSE | 13269.3389 | 12038.7869 | 7.4822 | 114 | 0.0001028 | 1575 | 0.066274 | 3155 | 6.8223e-06 | 0.00077774 | 3174 | 0.08 | 1600
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 68694 | TRUE | 3377.3751 | 0 | 0 | 32 | 0.00010397 | 1554 | 0.065151 | 3573 | 6.7736e-06 | 0.00021675 | 3175 |  | 2914
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 168368 | TRUE | 1090.7031 | 590.4471 | 0.36697 | 8 | 0.00010339 | 1562 | 0.065308 | 3460 | 6.7491e-06 | 5.3993e-05 | 3176 |  | 3294
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 782389 | TRUE | 861.6016 | 585.9597 | 0.36418 | 8 | 0.00010151 | 1617 | 0.065955 | 3232 | 6.7151e-06 | 5.3721e-05 | 3177 |  | 3216
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 72990 | FALSE | 5262.4562 | 1175.6663 | 0.73068 | 38 | 0.00010233 | 1594 | 0.065487 | 3374 | 6.7147e-06 | 0.00025516 | 3178 | 0.03 | 2293
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | LC16 | FALSE | 8170.2082 | 6889.2884 | 4.2817 | 72 | 0.00010102 | 1624 | 0.066218 | 3168 | 6.7061e-06 | 0.00048284 | 3179 | 0.17 | 1248
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 954811 | TRUE | 903.9347 | 282.8935 | 0.17582 | 9 | 0.00010244 | 1591 | 0.065576 | 3345 | 6.7055e-06 | 6.0349e-05 | 3180 |  | 2805
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 818262 | TRUE | 1433.202 | 292.9133 | 0.18205 | 11 | 0.00010153 | 1615 | 0.0655 | 3368 | 6.6573e-06 | 7.3231e-05 | 3181 |  | 2994
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1614 | FALSE | 3000.4112 | 3000.4112 | 1.8648 | 5 | 0.00010012 | 1643 | 9.5753 | 2631 | 6.6513e-06 | 3.3257e-05 | 3182 | 0.01 | 2585
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | CB | FALSE | 4270.3121 | 4270.3121 | 2.654 | 36 | 0.00010003 | 1646 | 0.066396 | 3120 | 6.6432e-06 | 0.00023916 | 3183 | 0.08 | 1628
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 418 | FALSE | 22746.3302 | 22539.2945 | 14.0083 | 178 | 9.9716e-05 | 1655 | 0.066381 | 3126 | 6.6205e-06 | 0.0011785 | 3184 | 0.17 | 1236
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | P138 | FALSE | 2470.0232 | 2259.003 | 1.404 | 15 | 9.8986e-05 | 1670 | 0.066089 | 3200 | 6.5684e-06 | 9.8527e-05 | 3185 | 0.04 | 2093
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | CB | TRUE | 42.5019 | 42.5019 | 0.026415 | 1 | 9.8387e-05 | 1681 | 0.066432 | 2999 | 6.536e-06 | 6.536e-06 | 3186 | 0.03 | 2336
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | CB | TRUE | 5967.294 | 629.206 | 0.39105 | 71 | 9.9922e-05 | 1649 | 0.065224 | 3498 | 6.5265e-06 | 0.00046338 | 3187 | 0.18 | 1209
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 11555 | FALSE | 1379.9837 | 1379.9837 | 0.85767 | 11 | 9.8049e-05 | 1688 | 0.066432 | 2976 | 6.5136e-06 | 7.165e-05 | 3188 | 0.16 | 1271
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 8888 | TRUE | 2206.3607 | 0 | 0 | 25 | 9.99e-05 | 1651 | 0.065147 | 3614 | 6.5082e-06 | 0.0001627 | 3189 |  | 3244
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 801904 | TRUE | 22.3881 | 22.3881 | 0.013914 | 1 | 8.2208e-05 | 2146 | 0.079148 | 2934 | 6.5066e-06 | 6.5066e-06 | 3190 | 0.06 | 1865
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | MR341 | TRUE | 1045.185 | 417.225 | 0.25931 | 11 | 9.8401e-05 | 1680 | 0.065731 | 3300 | 6.5027e-06 | 7.1529e-05 | 3191 |  | 3142
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 9973 | TRUE | 921.5182 | 921.5182 | 0.57273 | 7 | 9.7761e-05 | 1697 | 0.066431 | 3072 | 6.4944e-06 | 4.5461e-05 | 3192 |  | 3027
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 55787 | TRUE | 58.9251 | 58.9251 | 0.036622 | 1 | 9.7709e-05 | 1699 | 0.066432 | 2989 | 6.491e-06 | 6.491e-06 | 3193 | 0.05 | 2023
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 3342 | FALSE | 3691.7497 | 3691.7497 | 2.2944 | 30 | 9.6371e-05 | 1724 | 0.066431 | 3097 | 6.402e-06 | 0.00019206 | 3194 | 0.04 | 2113
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | CB | FALSE | 16824.5332 | 5560.2483 | 3.4557 | 140 | 9.7183e-05 | 1710 | 0.065554 | 3352 | 6.3852e-06 | 0.00089393 | 3195 | 0.06 | 1789
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 583284 | TRUE | 404.4133 | 236.5766 | 0.14703 | 4 | 9.5521e-05 | 1741 | 0.066111 | 3197 | 6.3368e-06 | 2.5347e-05 | 3196 |  | 3325
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 678650 | FALSE | 2024.9152 | 1808.9819 | 1.1243 | 14 | 9.5259e-05 | 1757 | 0.066065 | 3203 | 6.2788e-06 | 8.7903e-05 | 3197 |  | 3091
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | CR422 | FALSE | 3299.6109 | 3238.2816 | 2.0126 | 24 | 9.4398e-05 | 1783 | 0.066378 | 3128 | 6.2703e-06 | 0.00015049 | 3198 | 0.06 | 1855
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 2028 | FALSE | 14061.7847 | 14048.0686 | 8.7309 | 107 | 9.4213e-05 | 1788 | 0.06642 | 3114 | 6.2585e-06 | 0.00066966 | 3199 | 0.05 | 2036
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 4041 | FALSE | 7568.2918 | 2174.4689 | 1.3514 | 54 | 9.5438e-05 | 1746 | 0.065458 | 3394 | 6.2484e-06 | 0.00033741 | 3200 | 0.04 | 2187
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | CB | FALSE | 7432.6484 | 1011.6246 | 0.62873 | 66 | 9.5309e-05 | 1754 | 0.065326 | 3450 | 6.2313e-06 | 0.00041127 | 3201 | 0.17 | 1235
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1230 | FALSE | 7038.4432 | 1747.5573 | 1.0861 | 57 | 9.4865e-05 | 1770 | 0.065398 | 3418 | 6.2233e-06 | 0.00035473 | 3202 | 0.02 | 2465
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 184035 | TRUE | 995.7775 | 905.936 | 0.56304 | 9 | 9.1457e-05 | 1859 | 0.066289 | 3152 | 6.0721e-06 | 5.4649e-05 | 3203 |  | 3118
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 9048 | TRUE | 24.5909 | 24.5909 | 0.015283 | 1 | 9.1221e-05 | 1871 | 0.066432 | 2958 | 6.06e-06 | 6.06e-06 | 3204 | 0.06 | 1869
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1663 | FALSE | 1947.6462 | 1947.6462 | 1.2105 | 17 | 9.1109e-05 | 1877 | 0.066432 | 3000 | 6.0525e-06 | 0.00010289 | 3205 | 0.08 | 1656
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | MR279 | TRUE | 323.7748 | 4.572 | 0.0028415 | 5 | 9.2277e-05 | 1836 | 0.065405 | 3413 | 6.0521e-06 | 3.0261e-05 | 3206 |  | 3402
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 534 | FALSE | 2541.7011 | 1569.6662 | 0.97555 | 22 | 9.1303e-05 | 1866 | 0.065908 | 3243 | 6.0384e-06 | 0.00013284 | 3207 | 0.08 | 1668
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | CB | FALSE | 2551.5911 | 2551.5911 | 1.5858 | 22 | 9.066e-05 | 1892 | 0.066432 | 2986 | 6.0227e-06 | 0.0001325 | 3208 | 0.07 | 1703
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 526955 | TRUE | 753.5469 | 713.9611 | 0.44373 | 6 | 9.0519e-05 | 1897 | 0.066431 | 3022 | 6.0133e-06 | 3.608e-05 | 3209 |  | 3070
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 92582 | TRUE | 4514.9648 | 245.7655 | 0.15274 | 41 | 9.2095e-05 | 1840 | 0.065147 | 3619 | 5.9997e-06 | 0.00024599 | 3210 | 0.07 | 1704
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 588020 | TRUE | 2885.7528 | 385.2385 | 0.23943 | 19 | 9.1832e-05 | 1849 | 0.065219 | 3500 | 5.9904e-06 | 0.00011382 | 3211 |  | 3050
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | LB86 | FALSE | 8620.4875 | 7270.7679 | 4.5188 | 69 | 8.9584e-05 | 1927 | 0.066208 | 3169 | 5.9458e-06 | 0.00041026 | 3212 | 0.13 | 1335
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | BR164 | TRUE | 91.5845 | 91.5845 | 0.05692 | 2 | 8.9373e-05 | 1935 | 0.066432 | 2968 | 5.9372e-06 | 1.1874e-05 | 3213 | 0.05 | 1944
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 291744 | TRUE | 231.1314 | 195.7909 | 0.12168 | 3 | 9.0072e-05 | 1908 | 0.066004 | 3218 | 5.9276e-06 | 1.7783e-05 | 3214 |  | 3455
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 156268 | TRUE | 3622.1133 | 52.7453 | 0.032781 | 31 | 9.074e-05 | 1891 | 0.065189 | 3522 | 5.914e-06 | 0.00018333 | 3215 |  | 3199
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | CB | FALSE | 3450.2108 | 3450.2108 | 2.1443 | 23 | 8.8928e-05 | 1953 | 0.066432 | 2985 | 5.9077e-06 | 0.00013588 | 3216 | 1.33 | 684
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | LA401R | FALSE | 6369.4185 | 4956.3951 | 3.0804 | 55 | 8.9288e-05 | 1939 | 0.066129 | 3184 | 5.9068e-06 | 0.00032487 | 3217 | 0.06 | 1827
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 63274 | TRUE | 13077.1161 | 74.3652 | 0.046218 | 119 | 8.9998e-05 | 1914 | 0.06516 | 3555 | 5.8646e-06 | 0.00069789 | 3218 | 1.68 | 654
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 964292 | TRUE | 128.1599 | 128.1599 | 0.079652 | 2 | 8.8164e-05 | 1978 | 0.066432 | 2995 | 5.8569e-06 | 1.1714e-05 | 3219 |  | 3491
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 81770 | TRUE | 2254.8682 | 110.4225 | 0.068628 | 21 | 8.9058e-05 | 1945 | 0.065148 | 3588 | 5.8019e-06 | 0.00012184 | 3220 |  | 3289
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | P136 | FALSE | 9489.9011 | 7931.4997 | 4.9295 | 43 | 8.0523e-05 | 2191 | 0.07255 | 2940 | 5.7997e-06 | 0.00024939 | 3221 | 0.03 | 2269
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | CB | FALSE | 1079.0936 | 1079.0936 | 0.67066 | 8 | 8.7249e-05 | 2007 | 0.066432 | 3012 | 5.7961e-06 | 4.6369e-05 | 3222 | 0.06 | 1836
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 1308 | TRUE | 7407.352 | 244.9631 | 0.15225 | 60 | 8.8597e-05 | 1969 | 0.065216 | 3502 | 5.7874e-06 | 0.00034724 | 3223 | 8.14 | 435
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 401/2 LR | TRUE | 235.881 | 158.249 | 0.098352 | 4 | 8.7563e-05 | 1998 | 0.066112 | 3187 | 5.7731e-06 | 2.3093e-05 | 3224 |  | 2987
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 4039 | FALSE | 3724.1919 | 3048.4169 | 1.8946 | 32 | 8.7081e-05 | 2010 | 0.066191 | 3171 | 5.7609e-06 | 0.00018435 | 3225 | 0.06 | 1903
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 4037 | FALSE | 2780.393 | 1840.2464 | 1.1437 | 22 | 8.7734e-05 | 1991 | 0.065616 | 3331 | 5.7543e-06 | 0.0001266 | 3226 | 0.04 | 2149
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 10850 | TRUE | 3044.0072 | 994.8842 | 0.61832 | 28 | 8.6545e-05 | 2022 | 0.065652 | 3324 | 5.704e-06 | 0.00015971 | 3227 | 0.04 | 2091
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 48636 | TRUE | 4495.7291 | 86.4222 | 0.053712 | 38 | 8.7238e-05 | 2008 | 0.065185 | 3527 | 5.6861e-06 | 0.00021607 | 3228 | 0.01 | 2615
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 944560 | TRUE | 944.5774 | 282.6401 | 0.17566 | 9 | 8.6599e-05 | 2020 | 0.065433 | 3404 | 5.6635e-06 | 5.0971e-05 | 3229 |  | 3260
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 162952 | FALSE | 3475.2506 | 2846.7585 | 1.7693 | 25 | 8.5367e-05 | 2045 | 0.066175 | 3178 | 5.6583e-06 | 0.00014146 | 3230 |  | 2962
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 725292 | TRUE | 1519.9145 | 339.5862 | 0.21105 | 13 | 8.6305e-05 | 2027 | 0.065451 | 3395 | 5.658e-06 | 7.3554e-05 | 3231 |  | 2665
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 42914 | TRUE | 6917.2252 | 665.6425 | 0.4137 | 51 | 8.6589e-05 | 2021 | 0.065332 | 3443 | 5.6577e-06 | 0.00028854 | 3232 | 0.03 | 2387
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | CR208 | FALSE | 3895.4111 | 3895.4111 | 2.421 | 29 | 8.498e-05 | 2061 | 0.066431 | 3052 | 5.6453e-06 | 0.00016371 | 3233 | 0.19 | 1185
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 189400 | FALSE | 5552.3042 | 4446.7436 | 2.7637 | 45 | 8.4949e-05 | 2063 | 0.066033 | 3212 | 5.6305e-06 | 0.00025337 | 3234 |  | 2728
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 987158 | TRUE | 443.4139 | 397.6831 | 0.24716 | 2 | 8.4891e-05 | 2066 | 0.06579 | 3277 | 5.6215e-06 | 1.1243e-05 | 3235 |  | 3339
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | CB | FALSE | 7634.7258 | 7634.7258 | 4.745 | 55 | 8.4537e-05 | 2075 | 0.066409 | 3116 | 5.6154e-06 | 0.00030885 | 3236 | 0.16 | 1263
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | CR170 | FALSE | 2012.9175 | 2012.9175 | 1.251 | 17 | 8.3822e-05 | 2100 | 0.066432 | 2973 | 5.5684e-06 | 9.4663e-05 | 3237 | 0.21 | 1138
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 189700 | TRUE | 2164.8558 | 306.7254 | 0.19063 | 22 | 8.5054e-05 | 2057 | 0.065265 | 3473 | 5.5512e-06 | 0.00012213 | 3238 |  | 3343
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 79146 | TRUE | 3115.0804 | 85.6157 | 0.05321 | 28 | 8.3512e-05 | 2114 | 0.065194 | 3514 | 5.451e-06 | 0.00015263 | 3239 | 0.02 | 2490
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 634576 | FALSE | 3306.7049 | 2935.0444 | 1.8241 | 29 | 8.2017e-05 | 2152 | 0.066255 | 3159 | 5.4462e-06 | 0.00015794 | 3240 |  | 2939
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | D520R | TRUE | 5652.8623 | 0 | 0 | 50 | 8.3586e-05 | 2109 | 0.065148 | 3583 | 5.4455e-06 | 0.00027228 | 3241 |  | 2659
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 69586 | TRUE | 9651.4745 | 688.9218 | 0.42817 | 80 | 8.3471e-05 | 2116 | 0.065228 | 3492 | 5.4423e-06 | 0.00043538 | 3242 | 0.02 | 2429
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | CB | FALSE | 13332.3504 | 7661.9306 | 4.7619 | 102 | 7.7932e-05 | 2261 | 0.072303 | 2941 | 5.4342e-06 | 0.00055429 | 3243 | 0.07 | 1735
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 174072 | TRUE | 172.7033 | 172.7033 | 0.10734 | 3 | 8.1758e-05 | 2162 | 0.066004 | 3219 | 5.3939e-06 | 1.6182e-05 | 3244 |  | 3129
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 834094 | TRUE | 201.2345 | 155.4829 | 0.096633 | 3 | 8.2e-05 | 2155 | 0.065582 | 3337 | 5.3913e-06 | 1.6174e-05 | 3245 |  | 3572
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 9024 | FALSE | 6139.1912 | 5646.8015 | 3.5095 | 62 | 8.1167e-05 | 2180 | 0.066328 | 3141 | 5.3873e-06 | 0.00033401 | 3246 | 0.12 | 1406
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 2235 | TRUE | 1389.3312 | 296.6637 | 0.18438 | 10 | 8.163e-05 | 2164 | 0.065407 | 3411 | 5.3477e-06 | 5.3477e-05 | 3247 | 0.03 | 2392
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 264914 | FALSE | 1490.2678 | 1396.6171 | 0.868 | 14 | 8.0285e-05 | 2197 | 0.066248 | 3164 | 5.3219e-06 | 7.4507e-05 | 3248 |  | 2934
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 310 | TRUE | 5801.4081 | 319.7974 | 0.19876 | 48 | 8.1312e-05 | 2173 | 0.065285 | 3466 | 5.3143e-06 | 0.00025509 | 3249 | 0.63 | 836
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 6617 | FALSE | 2923.677 | 2923.677 | 1.8171 | 13 | 7.8082e-05 | 2257 | 0.068388 | 2946 | 5.304e-06 | 6.8952e-05 | 3250 | 1.03 | 726
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 590690 | TRUE | 383.2694 | 102.0304 | 0.063412 | 4 | 8.1235e-05 | 2176 | 0.065148 | 3587 | 5.2923e-06 | 2.1169e-05 | 3251 |  | 2919
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 12712 | FALSE | 5357.9341 | 1227.8521 | 0.76312 | 46 | 8.0658e-05 | 2189 | 0.065483 | 3376 | 5.2813e-06 | 0.00024294 | 3252 | 10.37 | 397
4164 | ELK 11014628 | 42981101 | ELK 1101 | 4628 | FALSE | 6688.9793 | 3975.7324 | 2.4709 | 54 | 7.9821e-05 | 2212 | 0.065813 | 3262 | 5.2551e-06 | 0.00028378 | 3253 | 0.03 | 2361
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | L522R | FALSE | 6797.2077 | 3031.8636 | 1.8843 | 56 | 7.9525e-05 | 2221 | 0.065744 | 3296 | 5.255e-06 | 0.00029428 | 3254 | 1.17 | 704
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 803535 | TRUE | 262.4984 | 262.4984 | 0.16314 | 3 | 7.8567e-05 | 2247 | 0.066431 | 3038 | 5.2193e-06 | 1.5658e-05 | 3255 |  | 3608
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 2000 | FALSE | 14495.3301 | 14495.3301 | 9.0089 | 101 | 7.8422e-05 | 2249 | 0.066432 | 2979 | 5.2097e-06 | 0.00052618 | 3256 | 0.12 | 1391
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 434 | TRUE | 1839.9407 | 49.2215 | 0.030591 | 16 | 7.9657e-05 | 2216 | 0.065231 | 3489 | 5.2024e-06 | 8.3238e-05 | 3257 |  | 2993
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 784032 | TRUE | 974.4826 | 863.751 | 0.53682 | 11 | 7.8303e-05 | 2251 | 0.066199 | 3170 | 5.1906e-06 | 5.7096e-05 | 3258 |  | 3137
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | CB | FALSE | 7735.7733 | 2937.1415 | 1.8254 | 60 | 7.5124e-05 | 2330 | 1.6497 | 2856 | 5.1594e-06 | 0.00030957 | 3259 | 0.22 | 1133
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | CR210 | FALSE | 4546.547 | 4546.547 | 2.8257 | 35 | 7.7661e-05 | 2270 | 0.066431 | 3091 | 5.1591e-06 | 0.00018057 | 3260 | 0.14 | 1309
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 471 | TRUE | 2001.813 | 0 | 0 | 16 | 7.9063e-05 | 2233 | 0.06523 | 3491 | 5.1543e-06 | 8.2468e-05 | 3261 | 0.33 | 988
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 494 | FALSE | 14793.4066 | 9034.9185 | 5.6152 | 114 | 7.7057e-05 | 2285 | 0.06596 | 3230 | 5.1065e-06 | 0.00058215 | 3262 | 0.23 | 1112
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 9116 | FALSE | 6878.1556 | 1335.9769 | 0.83032 | 53 | 7.7353e-05 | 2280 | 0.065341 | 3442 | 5.0499e-06 | 0.00026765 | 3263 | 0.08 | 1597
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 527766 | TRUE | 66.9649 | 66.9649 | 0.041619 | 1 | 7.5879e-05 | 2310 | 0.066432 | 2954 | 5.0408e-06 | 5.0408e-06 | 3264 |  | 3285
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 648439 | TRUE | 225.8757 | 10.9115 | 0.0067816 | 3 | 7.7251e-05 | 2281 | 0.065151 | 3571 | 5.033e-06 | 1.5099e-05 | 3265 |  | 3196
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 8858 | FALSE | 3073.6226 | 3073.6226 | 1.9103 | 27 | 7.5167e-05 | 2327 | 0.066432 | 2966 | 4.9935e-06 | 0.00013482 | 3266 | 0.08 | 1631
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 5065 | FALSE | 3543.5774 | 3543.5774 | 2.2023 | 27 | 7.4898e-05 | 2334 | 0.066432 | 2987 | 4.9756e-06 | 0.00013434 | 3267 | 0.1 | 1465
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 2553 | FALSE | 3992.3117 | 1548.3173 | 0.96229 | 32 | 7.5372e-05 | 2324 | 0.065669 | 3318 | 4.9535e-06 | 0.00015851 | 3268 | 0.05 | 2058
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 305072 | FALSE | 6216.8943 | 5044.0425 | 3.1349 | 45 | 7.4673e-05 | 2341 | 0.066118 | 3185 | 4.9532e-06 | 0.0002229 | 3269 |  | 2933
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 227862 | TRUE | 2810.7104 | 319.3369 | 0.19847 | 26 | 7.5864e-05 | 2311 | 0.065246 | 3481 | 4.952e-06 | 0.00012875 | 3270 |  | 2736
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 885952 | TRUE | 299.4502 | 283.4481 | 0.17616 | 4 | 7.3952e-05 | 2360 | 0.066111 | 3195 | 4.9074e-06 | 1.963e-05 | 3271 |  | 3397
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 779030 | TRUE | 1061.942 | 827.4759 | 0.51428 | 11 | 7.3516e-05 | 2383 | 0.066315 | 3145 | 4.881e-06 | 5.3691e-05 | 3272 |  | 3224
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | CB | TRUE | 5313.0282 | 378.608 | 0.23531 | 52 | 7.4297e-05 | 2349 | 0.065199 | 3510 | 4.847e-06 | 0.00025204 | 3273 |  | 2771
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | CB | TRUE | 10978.5428 | 257.3233 | 0.15993 | 91 | 7.4003e-05 | 2358 | 0.2391 | 2928 | 4.8414e-06 | 0.00044057 | 3274 | 0.04 | 2111
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | CB | FALSE | 3052.0291 | 3052.0291 | 1.8968 | 23 | 7.2318e-05 | 2409 | 0.066432 | 2962 | 4.8042e-06 | 0.0001105 | 3275 | 0.1 | 1457
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 586832 | FALSE | 6692.9945 | 6145.6408 | 3.8195 | 53 | 7.2377e-05 | 2406 | 0.066311 | 3146 | 4.7995e-06 | 0.00025437 | 3276 |  | 2711
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 3323 | TRUE | 214.7286 | 214.7286 | 0.13345 | 2 | 7.1735e-05 | 2429 | 0.066431 | 3042 | 4.7655e-06 | 9.5309e-06 | 3277 | 0.27 | 1051
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 10290 | TRUE | 9277.251 | 4.572 | 0.0028415 | 75 | 7.2679e-05 | 2399 | 0.065164 | 3550 | 4.7388e-06 | 0.00035541 | 3278 |  | 2841
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 687295 | FALSE | 1495.545 | 1495.545 | 0.92949 | 14 | 7.0919e-05 | 2445 | 0.066432 | 2963 | 4.7113e-06 | 6.5958e-05 | 3279 |  | 2878
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | CB | TRUE | 6661.6605 | 0 | 0 | 61 | 7.201e-05 | 2419 | 0.065151 | 3564 | 4.6915e-06 | 0.00028618 | 3280 | 0.11 | 1448
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | CB | TRUE | 1531.5459 | 0 | 0 | 17 | 7.1938e-05 | 2422 | 0.065151 | 3566 | 4.6868e-06 | 7.9676e-05 | 3281 | 0.25 | 1083
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 395936 | TRUE | 1081.2511 | 685.7662 | 0.42621 | 6 | 7.0765e-05 | 2449 | 0.066004 | 3222 | 4.6656e-06 | 2.7994e-05 | 3282 |  | 3422
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 12474 | FALSE | 13789.0355 | 5487.3001 | 3.4104 | 105 | 7.0779e-05 | 2448 | 0.065612 | 3333 | 4.6505e-06 | 0.00048831 | 3283 | 0.04 | 2152
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 307651 | TRUE | 416.3767 | 169.0436 | 0.10506 | 4 | 7.1015e-05 | 2444 | 0.065151 | 3569 | 4.6267e-06 | 1.8507e-05 | 3284 |  | 3486
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 262924 | FALSE | 3139.8868 | 3032.2865 | 1.8846 | 30 | 6.9614e-05 | 2485 | 0.066389 | 3125 | 4.6224e-06 | 0.00013867 | 3285 |  | 3238
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 439 | FALSE | 1501.1745 | 1069.2533 | 0.66455 | 12 | 7.0104e-05 | 2470 | 0.066111 | 3191 | 4.6178e-06 | 5.5413e-05 | 3286 | 1.58 | 664
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 319320 | TRUE | 221.6252 | 210.6172 | 0.1309 | 3 | 7.001e-05 | 2472 | 0.065578 | 3340 | 4.6148e-06 | 1.3844e-05 | 3287 |  | 3552
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 620294 | TRUE | 312.2722 | 249.6637 | 0.15517 | 4 | 7.0122e-05 | 2469 | 0.065468 | 3388 | 4.6109e-06 | 1.8443e-05 | 3288 |  | 3315
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 3116 | TRUE | 87.1475 | 87.1475 | 0.054163 | 2 | 6.9021e-05 | 2507 | 0.066431 | 3085 | 4.5851e-06 | 9.1703e-06 | 3289 |  | 3514
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 782320 | TRUE | 606.8883 | 340.3108 | 0.2115 | 5 | 6.9413e-05 | 2491 | 0.065662 | 3321 | 4.5524e-06 | 2.2762e-05 | 3290 |  | 3175
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | CB | TRUE | 14121.4272 | 0 | 0 | 124 | 6.9844e-05 | 2479 | 0.065151 | 3576 | 4.5504e-06 | 0.00056425 | 3291 | 0.02 | 2434
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 4431 | FALSE | 2379.8246 | 2267.622 | 1.4093 | 16 | 6.857e-05 | 2520 | 0.066271 | 3158 | 4.548e-06 | 7.2768e-05 | 3292 | 2.63 | 593
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 186938 | FALSE | 4893.222 | 2672.105 | 1.6607 | 41 | 6.8848e-05 | 2512 | 0.0659 | 3245 | 4.5458e-06 | 0.00018638 | 3293 |  | 2792
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 602871 | FALSE | 1324.4478 | 1324.4478 | 0.82315 | 14 | 6.84e-05 | 2525 | 0.06634 | 3137 | 4.5365e-06 | 6.3511e-05 | 3294 |  | 3232
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 48262 | FALSE | 9974.998 | 9974.998 | 6.1995 | 74 | 6.8225e-05 | 2528 | 0.066414 | 3115 | 4.5315e-06 | 0.00033533 | 3295 | 0.16 | 1266
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | CR220 | TRUE | 2216.0779 | 325.3992 | 0.20224 | 19 | 6.9057e-05 | 2505 | 0.065417 | 3408 | 4.51e-06 | 8.5689e-05 | 3296 | 0.06 | 1884
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 8942 | FALSE | 4451.7025 | 3407.8974 | 2.118 | 35 | 6.7999e-05 | 2536 | 0.066102 | 3198 | 4.5084e-06 | 0.00015779 | 3297 | 0.07 | 1712
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 404226 | FALSE | 1578.9748 | 1403.5728 | 0.87233 | 15 | 6.7624e-05 | 2545 | 0.066004 | 3221 | 4.4777e-06 | 6.7165e-05 | 3298 |  | 2985
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 4674 | TRUE | 11266.4783 | 72.8 | 0.045245 | 85 | 6.8436e-05 | 2524 | 0.065148 | 3604 | 4.4584e-06 | 0.00037897 | 3299 | 0.02 | 2468
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | CB | FALSE | 9310.1865 | 3594.4279 | 2.234 | 73 | 6.7929e-05 | 2538 | 0.065429 | 3407 | 4.4533e-06 | 0.00032509 | 3300 | 0.03 | 2291
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 617344 | FALSE | 3993.4046 | 2952.1893 | 1.8348 | 34 | 6.6754e-05 | 2562 | 0.065865 | 3252 | 4.4076e-06 | 0.00014986 | 3301 |  | 3099
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | CB | TRUE | 3983.613 | 901.4332 | 0.56024 | 34 | 5.1406e-05 | 3008 | 0.069389 | 2944 | 4.3928e-06 | 0.00014935 | 3302 | 0.16 | 1257
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | CB | FALSE | 5468.4733 | 4727.7308 | 2.9383 | 42 | 6.6223e-05 | 2583 | 0.066187 | 3172 | 4.392e-06 | 0.00018447 | 3303 | 0.12 | 1373
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 68454 | FALSE | 17728.9798 | 13589.2158 | 8.4458 | 142 | 6.656e-05 | 2571 | 0.066016 | 3214 | 4.3912e-06 | 0.00062355 | 3304 | 0.14 | 1311
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 22158 | TRUE | 14506.5343 | 184.8198 | 0.11487 | 119 | 6.7278e-05 | 2552 | 0.065158 | 3557 | 4.3836e-06 | 0.00052165 | 3305 | 0.04 | 2174
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 12850 | FALSE | 6644.9449 | 1063.4476 | 0.66094 | 52 | 6.6462e-05 | 2576 | 0.065295 | 3464 | 4.3733e-06 | 0.00022741 | 3306 | 0.02 | 2487
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 498 | FALSE | 4821.7264 | 4596.7491 | 2.8569 | 18 | 6.582e-05 | 2593 | 0.066146 | 3183 | 4.3648e-06 | 7.8567e-05 | 3307 | 0.05 | 1926
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 5357 | FALSE | 5401.7845 | 5401.7845 | 3.3572 | 37 | 6.5663e-05 | 2599 | 0.066432 | 2965 | 4.3621e-06 | 0.0001614 | 3308 | 10.09 | 402
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 9490 | FALSE | 2186.2244 | 2004.014 | 1.2455 | 21 | 6.5775e-05 | 2597 | 0.066187 | 3173 | 4.3539e-06 | 9.1432e-05 | 3309 | 0.07 | 1753
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 480328 | TRUE | 859.3222 | 472.375 | 0.29358 | 7 | 6.5647e-05 | 2600 | 0.065698 | 3311 | 4.3254e-06 | 3.0278e-05 | 3310 |  | 2811
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 2654 | FALSE | 2963.5999 | 2963.5999 | 1.8419 | 23 | 6.4898e-05 | 2612 | 0.066432 | 2988 | 4.3113e-06 | 9.916e-05 | 3311 | 0.09 | 1555
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | CB | TRUE | 1021.9623 | 373.7851 | 0.23231 | 8 | 6.5789e-05 | 2595 | 0.065148 | 3585 | 4.2861e-06 | 3.4288e-05 | 3312 |  | 3278
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 253312 | TRUE | 698.8026 | 682.8006 | 0.42436 | 2 | 6.5784e-05 | 2596 | 713.1431 | 1011 | 4.2859e-06 | 8.5718e-06 | 3313 |  | 3438
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 173702 | TRUE | 213.4901 | 86.6803 | 0.053872 | 3 | 6.5664e-05 | 2598 | 0.065148 | 3599 | 4.2778e-06 | 1.2834e-05 | 3314 |  | 3550
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 65474 | FALSE | 5862.6816 | 3837.7425 | 2.3852 | 47 | 6.4376e-05 | 2630 | 0.065968 | 3227 | 4.2638e-06 | 0.0002004 | 3315 | 0.05 | 2056
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 218962 | TRUE | 167.2894 | 86.3363 | 0.053658 | 2 | 5.4301e-05 | 2937 | 0.078474 | 2935 | 4.2591e-06 | 8.5182e-06 | 3316 |  | 3037
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 772224 | TRUE | 126.2491 | 91.9583 | 0.057152 | 2 | 6.4042e-05 | 2644 | 0.06579 | 3275 | 4.2158e-06 | 8.4316e-06 | 3317 |  | 3588
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 84797 | TRUE | 2211.5607 | 66.6995 | 0.041454 | 21 | 6.4533e-05 | 2626 | 0.065331 | 3445 | 4.2155e-06 | 8.8525e-05 | 3318 | 0.02 | 2441
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | CB | TRUE | 3818.0634 | 493.1815 | 0.30651 | 38 | 6.4589e-05 | 2622 | 0.065215 | 3503 | 4.2137e-06 | 0.00016012 | 3319 | 0.01 | 2579
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | CB | TRUE | 8168.5567 | 0 | 0 | 67 | 6.4156e-05 | 2638 | 0.065525 | 3359 | 4.207e-06 | 0.00028187 | 3320 |  | 2730
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 1254 | FALSE | 15241.9933 | 9639.5738 | 5.991 | 130 | 6.3299e-05 | 2668 | 0.06587 | 3250 | 4.1869e-06 | 0.0005443 | 3321 | 0.81 | 771
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 36864 | TRUE | 910.3949 | 889.7222 | 0.55297 | 10 | 6.2904e-05 | 2685 | 0.066303 | 3147 | 4.1763e-06 | 4.1763e-05 | 3322 | 0.03 | 2369
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 9642 | FALSE | 1925.8934 | 1925.8934 | 1.197 | 18 | 6.2785e-05 | 2690 | 0.066432 | 2983 | 4.1709e-06 | 7.5077e-05 | 3323 | 0.04 | 2171
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | CB | TRUE | 15331.9124 | 23.5925 | 0.014663 | 121 | 6.3977e-05 | 2647 | 0.065159 | 3556 | 4.1691e-06 | 0.00050446 | 3324 | 0.02 | 2479
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | CB | TRUE | 49.1761 | 49.1761 | 0.030563 | 1 | 6.2654e-05 | 2695 | 0.066431 | 3094 | 4.1622e-06 | 4.1622e-06 | 3325 | 0 | 2628
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 267868 | FALSE | 1937.2772 | 1363.5441 | 0.84745 | 13 | 6.31e-05 | 2676 | 0.065839 | 3257 | 4.157e-06 | 5.4041e-05 | 3326 |  | 3346
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 9154 | FALSE | 10556.7719 | 6776.6762 | 4.2117 | 95 | 6.2892e-05 | 2686 | 0.065945 | 3236 | 4.1518e-06 | 0.00039442 | 3327 | 0.03 | 2237
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 2510 | FALSE | 14243.477 | 12778.5068 | 7.9419 | 22 | 6.2454e-05 | 2707 | 0.066023 | 3213 | 4.1333e-06 | 9.0933e-05 | 3328 | 0.02 | 2457
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 554 | TRUE | 4453.2978 | 52.9857 | 0.032931 | 35 | 6.333e-05 | 2667 | 0.065188 | 3524 | 4.1303e-06 | 0.00014456 | 3329 |  | 2848
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 265211 | TRUE | 282.195 | 238.1693 | 0.14802 | 4 | 6.2639e-05 | 2696 | 0.065789 | 3282 | 4.1276e-06 | 1.651e-05 | 3330 |  | 3146
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | CB | FALSE | 8287.061 | 8183.2875 | 5.0859 | 67 | 6.1848e-05 | 2725 | 0.066374 | 3130 | 4.1068e-06 | 0.00027516 | 3331 | 0.08 | 1652
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 3012 | TRUE | 22106.1049 | 301.9386 | 0.18766 | 160 | 6.253e-05 | 2701 | 0.065164 | 3551 | 4.0749e-06 | 0.00065198 | 3332 | 0.04 | 2138
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | XR248 | TRUE | 2436.8191 | 0 | 0 | 22 | 6.254e-05 | 2700 | 0.065147 | 3632 | 4.0743e-06 | 8.9634e-05 | 3333 |  | 3052
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 709451 | TRUE | 302.4738 | 302.4738 | 0.18799 | 5 | 6.0665e-05 | 2757 | 0.066432 | 2951 | 4.0301e-06 | 2.0151e-05 | 3334 |  | 3439
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | CB | TRUE | 15770.5803 | 273.8424 | 0.17019 | 135 | 6.178e-05 | 2726 | 0.065185 | 3529 | 4.0299e-06 | 0.00054404 | 3335 | 0.02 | 2453
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | CB | FALSE | 9896.0278 | 4879.3813 | 3.0326 | 92 | 6.0199e-05 | 2766 | 0.065711 | 3305 | 3.9708e-06 | 0.00036531 | 3336 | 0.35 | 974
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 189500 | FALSE | 1726.2402 | 1225.686 | 0.76177 | 17 | 6.0082e-05 | 2771 | 0.065903 | 3244 | 3.9708e-06 | 6.7503e-05 | 3337 |  | 3131
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | CB | FALSE | 2366.505 | 2366.505 | 1.4708 | 17 | 5.9542e-05 | 2787 | 0.066432 | 2992 | 3.9555e-06 | 6.7244e-05 | 3338 | 0.14 | 1312
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 2606 | FALSE | 4663.4326 | 1279.376 | 0.79514 | 52 | 5.9834e-05 | 2780 | 0.065394 | 3420 | 3.9158e-06 | 0.00020362 | 3339 | 0.06 | 1806
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 1970 | TRUE | 6915.717 | 0 | 0 | 60 | 6.0013e-05 | 2774 | 0.065151 | 3563 | 3.9099e-06 | 0.00023459 | 3340 | 0.06 | 1913
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 145998 | FALSE | 4112.6069 | 4027.966 | 2.5034 | 28 | 5.8787e-05 | 2812 | 0.066294 | 3151 | 3.8997e-06 | 0.00010919 | 3341 |  | 2898
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 9114 | FALSE | 11036.3123 | 10977.6209 | 6.8226 | 92 | 5.8649e-05 | 2817 | 0.066404 | 3117 | 3.8947e-06 | 0.00035832 | 3342 | 0.17 | 1246
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 9026 | FALSE | 8105.233 | 1184.1509 | 0.73595 | 71 | 5.949e-05 | 2791 | 0.065382 | 3425 | 3.8932e-06 | 0.00027642 | 3343 | 0.03 | 2274
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 9656 | TRUE | 188.9883 | 188.9883 | 0.11746 | 2 | 5.8277e-05 | 2826 | 0.066432 | 2981 | 3.8714e-06 | 7.7429e-06 | 3344 |  | 3621
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | CR184 | FALSE | 5568.9906 | 5568.9906 | 3.4612 | 43 | 5.7871e-05 | 2839 | 0.066432 | 2949 | 3.8445e-06 | 0.00016531 | 3345 | 0.05 | 2043
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | P142 | FALSE | 5002.4344 | 1963.5704 | 1.2204 | 41 | 5.8204e-05 | 2828 | 0.065555 | 3351 | 3.8432e-06 | 0.00015757 | 3346 | 0.02 | 2469
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 643778 | TRUE | 406.3148 | 270.3051 | 0.168 | 4 | 5.7794e-05 | 2841 | 0.06547 | 3381 | 3.7919e-06 | 1.5168e-05 | 3347 |  | 3549
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 882610 | TRUE | 653.6335 | 228.3158 | 0.1419 | 8 | 5.7922e-05 | 2838 | 0.065308 | 3458 | 3.7868e-06 | 3.0295e-05 | 3348 |  | 3400
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 526868 | FALSE | 2061.1443 | 1780.5165 | 1.1066 | 20 | 5.6772e-05 | 2867 | 0.066239 | 3165 | 3.7614e-06 | 7.5227e-05 | 3349 |  | 2663
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 58642 | FALSE | 2892.0319 | 2892.0319 | 1.7974 | 13 | 5.6521e-05 | 2871 | 0.066431 | 3049 | 3.7548e-06 | 4.8812e-05 | 3350 | 0.02 | 2501
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 2379 | FALSE | 1171.3689 | 1171.3689 | 0.72801 | 11 | 5.6518e-05 | 2872 | 0.066432 | 2969 | 3.7546e-06 | 4.1301e-05 | 3351 | 0.09 | 1523
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 468158 | TRUE | 1565.7596 | 826.6133 | 0.51374 | 12 | 5.6983e-05 | 2862 | 0.065469 | 3384 | 3.7407e-06 | 4.4889e-05 | 3352 |  | 2897
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 650808 | TRUE | 998.3572 | 843.3592 | 0.52415 | 8 | 5.3264e-05 | 2957 | 0.068808 | 2945 | 3.6894e-06 | 2.9515e-05 | 3353 |  | 3257
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 555372 | FALSE | 6684.5288 | 6684.5288 | 4.1545 | 54 | 5.5277e-05 | 2905 | 0.066432 | 2978 | 3.6721e-06 | 0.0001983 | 3354 | 0.13 | 1342
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 55262 | TRUE | 266.534 | 266.534 | 0.16565 | 4 | 5.499e-05 | 2911 | 0.066431 | 3095 | 3.653e-06 | 1.4612e-05 | 3355 | 0.06 | 1866
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 96874 | FALSE | 1722.0177 | 1345.5157 | 0.83624 | 16 | 5.4971e-05 | 2913 | 0.06595 | 3234 | 3.6408e-06 | 5.8253e-05 | 3356 |  | 3127
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | CB | FALSE | 4041.5057 | 3727.5543 | 2.3167 | 24 | 5.482e-05 | 2920 | 0.066271 | 3157 | 3.64e-06 | 8.736e-05 | 3357 | 0.04 | 2207
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | CR282 | FALSE | 6573.0208 | 6573.0208 | 4.0852 | 45 | 5.4739e-05 | 2924 | 0.066432 | 2977 | 3.6364e-06 | 0.00016364 | 3358 | 0.06 | 1916
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | CB | TRUE | 1686.9104 | 61.191 | 0.03803 | 24 | 5.5357e-05 | 2902 | 0.065254 | 3478 | 3.6135e-06 | 8.6724e-05 | 3359 | 0.03 | 2342
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 9488 | FALSE | 2122.5518 | 1460.401 | 0.90765 | 18 | 5.4746e-05 | 2923 | 0.06579 | 3279 | 3.6034e-06 | 6.486e-05 | 3360 | 0.02 | 2561
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 558727 | TRUE | 2270.5335 | 217.1494 | 0.13496 | 22 | 5.4871e-05 | 2919 | 0.065381 | 3426 | 3.5926e-06 | 7.9037e-05 | 3361 |  | 2835
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 42226 | TRUE | 4032.3201 | 940.1806 | 0.58433 | 32 | 5.4774e-05 | 2922 | 0.065308 | 3457 | 3.588e-06 | 0.00011482 | 3362 |  | 3126
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 309087 | TRUE | 645.6047 | 302.4969 | 0.188 | 6 | 5.4354e-05 | 2935 | 0.065578 | 3341 | 3.575e-06 | 2.145e-05 | 3363 |  | 3096
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 238418 | TRUE | 1291.252 | 331.2384 | 0.20587 | 6 | 5.4643e-05 | 2928 | 0.065361 | 3433 | 3.5615e-06 | 2.1369e-05 | 3364 |  | 2935
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 428 | TRUE | 2739.6912 | 0 | 0 | 21 | 5.3944e-05 | 2943 | 0.065212 | 3505 | 3.5167e-06 | 7.3852e-05 | 3365 | 0.37 | 964
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | XR326 | TRUE | 21948.0156 | 0 | 0 | 163 | 5.3862e-05 | 2945 | 0.065147 | 3608 | 3.509e-06 | 0.00057196 | 3366 | 0.04 | 2188
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 39786 | TRUE | 5442.5467 | 454.7368 | 0.28262 | 44 | 5.3497e-05 | 2950 | 0.065245 | 3482 | 3.496e-06 | 0.00015383 | 3367 | 0.21 | 1145
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 9118 | FALSE | 4822.7839 | 1265.7827 | 0.78669 | 41 | 5.3297e-05 | 2954 | 0.065429 | 3406 | 3.4915e-06 | 0.00014315 | 3368 | 0.42 | 936
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 991788 | FALSE | 5495.9742 | 1222.0634 | 0.75952 | 43 | 5.288e-05 | 2971 | 0.065395 | 3419 | 3.4631e-06 | 0.00014892 | 3369 |  | 2890
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | XR246 | TRUE | 6374.5348 | 71.5932 | 0.044495 | 61 | 5.3027e-05 | 2967 | 0.06519 | 3521 | 3.4559e-06 | 0.00021081 | 3370 |  | 3218
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 76678 | TRUE | 597.8557 | 88.7522 | 0.05516 | 8 | 5.2866e-05 | 2974 | 0.065468 | 3386 | 3.4511e-06 | 2.7609e-05 | 3371 | 0.02 | 2467
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 741586 | FALSE | 1137.7952 | 1137.7952 | 0.70714 | 9 | 5.1683e-05 | 3002 | 0.066431 | 3093 | 3.4334e-06 | 3.09e-05 | 3372 |  | 3342
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 8958 | FALSE | 9585.6333 | 5438.9297 | 3.3803 | 73 | 5.1694e-05 | 3001 | 0.065833 | 3259 | 3.4119e-06 | 0.00024907 | 3373 | 0.04 | 2204
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 502026 | TRUE | 1729.6385 | 180.5393 | 0.11221 | 17 | 5.2048e-05 | 2992 | 0.065374 | 3427 | 3.4024e-06 | 5.784e-05 | 3374 |  | 3302
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | LB16 | FALSE | 13211.9515 | 4399.0652 | 2.734 | 97 | 5.1468e-05 | 3006 | 0.065597 | 3335 | 3.3964e-06 | 0.00032945 | 3375 | 0.03 | 2296
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 951816 | TRUE | 539.1734 | 539.1734 | 0.3351 | 6 | 5.1065e-05 | 3013 | 0.066431 | 3112 | 3.3923e-06 | 2.0354e-05 | 3376 |  | 3551
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | LC40 | TRUE | 2260.1219 | 26.7728 | 0.016639 | 28 | 5.1876e-05 | 2996 | 0.065193 | 3517 | 3.3827e-06 | 9.4717e-05 | 3377 | 0.02 | 2440
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | CR182 | FALSE | 7768.8154 | 7768.8154 | 4.8284 | 56 | 5.0879e-05 | 3018 | 0.066432 | 2959 | 3.38e-06 | 0.00018928 | 3378 | 0.15 | 1294
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 903036 | TRUE | 576.6112 | 306.6437 | 0.19058 | 5 | 5.0816e-05 | 3019 | 0.065404 | 3415 | 3.3474e-06 | 1.6737e-05 | 3379 |  | 3419
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | CB | FALSE | 5576.1236 | 3611.6831 | 2.2447 | 46 | 5.0453e-05 | 3026 | 0.065847 | 3255 | 3.3325e-06 | 0.0001533 | 3380 | 0.18 | 1221
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 66732 | TRUE | 3298.663 | 334.9483 | 0.20817 | 23 | 5.0745e-05 | 3021 | 0.065259 | 3476 | 3.3135e-06 | 7.6211e-05 | 3381 | 0.04 | 2115
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 2355 | TRUE | 1676.4836 | 644.3598 | 0.40047 | 13 | 4.9957e-05 | 3038 | 0.065643 | 3325 | 3.2963e-06 | 4.2852e-05 | 3382 | 0.06 | 1797
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 119798 | TRUE | 129.7041 | 129.7041 | 0.080612 | 2 | 4.9475e-05 | 3051 | 0.066432 | 2975 | 3.2867e-06 | 6.5735e-06 | 3383 |  | 3428
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 81716 | TRUE | 406.7505 | 406.7505 | 0.2528 | 5 | 4.9207e-05 | 3059 | 0.066432 | 2971 | 3.2689e-06 | 1.6345e-05 | 3384 |  | 3512
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 950286 | FALSE | 1710.7995 | 1710.7995 | 1.0633 | 17 | 4.911e-05 | 3061 | 0.066432 | 2974 | 3.2625e-06 | 5.5462e-05 | 3385 |  | 3046
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | CB | FALSE | 6891.3641 | 1520.1281 | 0.94477 | 66 | 4.9607e-05 | 3044 | 0.065478 | 3378 | 3.2502e-06 | 0.00021451 | 3386 | 0.05 | 2029
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 107508 | TRUE | 282.9574 | 0 | 0 | 2 | 4.9331e-05 | 3054 | 0.065151 | 3568 | 3.214e-06 | 6.4279e-06 | 3387 |  | 3203
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | CR172 | TRUE | 3350.0951 | 904.9661 | 0.56244 | 30 | 4.8943e-05 | 3065 | 0.065361 | 3434 | 3.209e-06 | 9.6271e-05 | 3388 | 0.05 | 2015
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 11074 | FALSE | 4972.7567 | 4718.31 | 2.9324 | 41 | 4.8374e-05 | 3082 | 0.066275 | 3154 | 3.1905e-06 | 0.00013081 | 3389 | 0.48 | 903
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | MR441 | TRUE | 350.4949 | 40.2016 | 0.024985 | 8 | 4.8606e-05 | 3074 | 0.065309 | 3456 | 3.1892e-06 | 2.5513e-05 | 3390 |  | 3190
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 764698 | TRUE | 357.0375 | 133.4071 | 0.082913 | 5 | 4.8608e-05 | 3073 | 0.065407 | 3412 | 3.1867e-06 | 1.5933e-05 | 3391 |  | 3156
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | P126 | FALSE | 3297.3508 | 1680.8363 | 1.0446 | 25 | 4.8344e-05 | 3085 | 0.065713 | 3304 | 3.1848e-06 | 7.9621e-05 | 3392 | 0.03 | 2259
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 7315 | TRUE | 3607.614 | 0 | 0 | 32 | 4.8486e-05 | 3078 | 0.065151 | 3567 | 3.1589e-06 | 0.00010108 | 3393 |  | 2795
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 33064 | TRUE | 5902.0297 | 0 | 0 | 49 | 4.8351e-05 | 3084 | 0.065148 | 3593 | 3.15e-06 | 0.00015435 | 3394 |  | 3017
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | CR100 | FALSE | 5399.0675 | 5399.0675 | 3.3555 | 40 | 4.7216e-05 | 3109 | 0.066432 | 2972 | 3.1366e-06 | 0.00012546 | 3395 | 0.04 | 2134
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | CB | TRUE | 3679.779 | 47.6524 | 0.029616 | 34 | 4.8123e-05 | 3090 | 0.065185 | 3530 | 3.1364e-06 | 0.00010664 | 3396 | 0.03 | 2233
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | BR178 | TRUE | 10667.1601 | 48.2003 | 0.029957 | 93 | 4.805e-05 | 3092 | 0.065161 | 3553 | 3.1309e-06 | 0.00029117 | 3397 | 0.24 | 1105
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | L534R | FALSE | 3066.0904 | 1291.9266 | 0.80294 | 34 | 4.7553e-05 | 3099 | 0.065526 | 3358 | 3.1282e-06 | 0.00010636 | 3398 | 0.06 | 1853
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | P176 | TRUE | 5384.4602 | 354.4687 | 0.2203 | 44 | 4.7444e-05 | 3104 | 0.066098 | 3199 | 3.1268e-06 | 0.00013758 | 3399 | 0.06 | 1778
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 92792 | TRUE | 2338.4551 | 0 | 0 | 21 | 4.7946e-05 | 3094 | 0.065148 | 3598 | 3.1236e-06 | 6.5595e-05 | 3400 | 0.04 | 2169
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 504524 | TRUE | 2446.524 | 610.0991 | 0.37918 | 15 | 4.7542e-05 | 3101 | 0.065322 | 3452 | 3.1216e-06 | 4.6823e-05 | 3401 |  | 3262
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 747522 | TRUE | 1686.5664 | 412.9409 | 0.25664 | 16 | 4.7461e-05 | 3103 | 0.065468 | 3390 | 3.1133e-06 | 4.9813e-05 | 3402 |  | 3378
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 121588 | FALSE | 3050.4627 | 1356.1967 | 0.84288 | 27 | 4.7074e-05 | 3111 | 0.065623 | 3330 | 3.0983e-06 | 8.3654e-05 | 3403 |  | 2743
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 1256 | FALSE | 12257.9124 | 12003.1718 | 7.46 | 88 | 4.6726e-05 | 3121 | 0.066359 | 3134 | 3.098e-06 | 0.00027263 | 3404 | 0.07 | 1720
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 595689 | TRUE | 356.3825 | 44.7654 | 0.027822 | 4 | 4.6978e-05 | 3113 | 0.065468 | 3387 | 3.0826e-06 | 1.233e-05 | 3405 |  | 3152
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 640 | TRUE | 6850.9553 | 0 | 0 | 56 | 4.7109e-05 | 3110 | 0.065185 | 3528 | 3.0722e-06 | 0.00017204 | 3406 | 0.02 | 2509
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 9089 | FALSE | 2700.0603 | 2319.95 | 1.4419 | 20 | 4.6292e-05 | 3130 | 0.066175 | 3177 | 3.0684e-06 | 6.1368e-05 | 3407 | 0.03 | 2365
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 968736 | FALSE | 1533.9821 | 1132.2658 | 0.70371 | 9 | 4.6179e-05 | 3133 | 0.065575 | 3349 | 3.0372e-06 | 2.7334e-05 | 3408 |  | 2899
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 37284 | TRUE | 823.8475 | 303.068 | 0.18836 | 15 | 4.5944e-05 | 3141 | 0.065918 | 3241 | 3.0199e-06 | 4.5299e-05 | 3409 |  | 2937
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 48752 | TRUE | 3375.7798 | 23.2085 | 0.014424 | 28 | 4.6007e-05 | 3137 | 0.065151 | 3572 | 2.9974e-06 | 8.3928e-05 | 3410 | 0.02 | 2446
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | CB | FALSE | 3860.7171 | 2930.2271 | 1.8211 | 31 | 4.5082e-05 | 3157 | 0.066059 | 3208 | 2.9927e-06 | 9.2772e-05 | 3411 | 0.06 | 1837
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 1218 | TRUE | 3546.1366 | 106.7452 | 0.066343 | 28 | 4.5839e-05 | 3144 | 0.065197 | 3512 | 2.9904e-06 | 8.3731e-05 | 3412 | 0.03 | 2368
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 84764 | TRUE | 4092.9318 | 339.9136 | 0.21126 | 33 | 4.5707e-05 | 3148 | 0.065268 | 3472 | 2.9818e-06 | 9.8398e-05 | 3413 |  | 2990
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 12828 | FALSE | 7906.6719 | 1834.1595 | 1.1399 | 66 | 4.4984e-05 | 3161 | 0.065458 | 3393 | 2.9651e-06 | 0.0001957 | 3414 |  | 2662
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | CB | TRUE | 2059.8957 | 523.3275 | 0.32525 | 23 | 4.4906e-05 | 3162 | 0.065538 | 3356 | 2.9632e-06 | 6.8153e-05 | 3415 |  | 2989
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 395498 | TRUE | 792.3855 | 171.0291 | 0.1063 | 8 | 4.5439e-05 | 3154 | 0.065308 | 3459 | 2.9622e-06 | 2.3698e-05 | 3416 |  | 3227
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 683542 | TRUE | 222.9115 | 222.9115 | 0.13854 | 2 | 4.4358e-05 | 3180 | 0.066431 | 3030 | 2.9468e-06 | 5.8935e-06 | 3417 |  | 3237
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 405812 | TRUE | 695.3753 | 295.2493 | 0.1835 | 7 | 4.5015e-05 | 3158 | 0.065517 | 3362 | 2.9445e-06 | 2.0611e-05 | 3418 |  | 3019
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | L541R | TRUE | 978.5878 | 0 | 0 | 11 | 4.5011e-05 | 3159 | 0.065148 | 3586 | 2.9324e-06 | 3.2256e-05 | 3419 |  | 3233
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | CB | TRUE | 3805.7329 | 538.4598 | 0.33465 | 40 | 4.4235e-05 | 3185 | 0.065436 | 3400 | 2.9186e-06 | 0.00011674 | 3420 | 0.04 | 2228
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | CR256 | FALSE | 2967.1612 | 1965.4224 | 1.2215 | 27 | 4.4194e-05 | 3187 | 0.065813 | 3263 | 2.9181e-06 | 7.879e-05 | 3421 | 0.05 | 2053
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 144690 | TRUE | 900.0003 | 418.942 | 0.26037 | 10 | 3.5334e-05 | 3344 | 0.075693 | 2936 | 2.905e-06 | 2.905e-05 | 3422 |  | 3264
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | MR233 | TRUE | 1023.3374 | 370.9448 | 0.23054 | 7 | 4.4443e-05 | 3176 | 0.065331 | 3447 | 2.9035e-06 | 2.0325e-05 | 3423 |  | 3504
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 318 | FALSE | 18622.6335 | 2887.2825 | 1.7945 | 150 | 4.4269e-05 | 3183 | 0.065347 | 3439 | 2.9031e-06 | 0.00043547 | 3424 |  | 2830
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 87784 | FALSE | 2328.7215 | 2328.7215 | 1.4473 | 23 | 4.3587e-05 | 3199 | 0.066432 | 2997 | 2.8956e-06 | 6.6598e-05 | 3425 | 0.12 | 1383
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | CB | TRUE | 22.2055 | 22.2055 | 0.013801 | 1 | 4.352e-05 | 3201 | 0.066431 | 3088 | 2.8911e-06 | 2.8911e-06 | 3426 | 1.9 | 633
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 4456 | TRUE | 8052.7827 | 0 | 0 | 62 | 4.4073e-05 | 3189 | 0.065151 | 3562 | 2.8714e-06 | 0.00017803 | 3427 | 0.03 | 2297
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 785521 | TRUE | 292.996 | 109.0213 | 0.067757 | 3 | 4.3673e-05 | 3196 | 0.065575 | 3350 | 2.8654e-06 | 8.5962e-06 | 3428 |  | 3223
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 2246 | FALSE | 2937.4924 | 2937.4924 | 1.8257 | 23 | 4.2984e-05 | 3209 | 0.066432 | 2998 | 2.8555e-06 | 6.5676e-05 | 3429 | 0.1 | 1481
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 8922 | FALSE | 1940.3902 | 1940.3902 | 1.206 | 11 | 4.2932e-05 | 3211 | 0.066431 | 3096 | 2.852e-06 | 3.1372e-05 | 3430 | 0.18 | 1208
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | CB | FALSE | 4044.2651 | 2195.0074 | 1.3642 | 37 | 4.3121e-05 | 3206 | 0.065703 | 3309 | 2.8459e-06 | 0.0001053 | 3431 | 0.02 | 2448
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 35388 | TRUE | 727.2974 | 517.0139 | 0.32133 | 8 | 4.2702e-05 | 3213 | 0.066111 | 3193 | 2.8344e-06 | 2.2676e-05 | 3432 | 0.94 | 745
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | CB | TRUE | 3068.5523 | 350.3296 | 0.21773 | 34 | 4.3221e-05 | 3205 | 0.065226 | 3495 | 2.8181e-06 | 9.5817e-05 | 3433 |  | 2943
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 733078 | TRUE | 567.873 | 551.871 | 0.34299 | 7 | 4.2163e-05 | 3221 | 0.066065 | 3206 | 2.777e-06 | 1.9439e-05 | 3434 |  | 3310
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | CB | TRUE | 7954.9462 | 769.1621 | 0.47804 | 66 | 4.1996e-05 | 3224 | 0.065264 | 3474 | 2.758e-06 | 0.00018203 | 3435 | 0.02 | 2428
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 420730 | FALSE | 2651.706 | 1292.6324 | 0.80338 | 21 | 4.1694e-05 | 3230 | 0.065759 | 3293 | 2.7513e-06 | 5.7777e-05 | 3436 |  | 2760
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 880795 | TRUE | 506.0077 | 163.9752 | 0.10191 | 6 | 4.2077e-05 | 3222 | 0.065147 | 3611 | 2.7412e-06 | 1.6447e-05 | 3437 |  | 3277
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 947314 | TRUE | 2331.8511 | 461.4011 | 0.28676 | 22 | 4.1433e-05 | 3236 | 0.065323 | 3451 | 2.7164e-06 | 5.9761e-05 | 3438 |  | 3163
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 37074 | TRUE | 506.0081 | 21.9456 | 0.013639 | 6 | 4.1439e-05 | 3234 | 0.065361 | 3435 | 2.7134e-06 | 1.628e-05 | 3439 | 0.03 | 2372
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 79774 | FALSE | 2604.0952 | 1435.8821 | 0.89241 | 24 | 4.0919e-05 | 3247 | 0.065682 | 3315 | 2.698e-06 | 6.4753e-05 | 3440 | 0.05 | 2041
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 12586 | FALSE | 10478.2506 | 3041.3304 | 1.8902 | 85 | 4.1068e-05 | 3241 | 0.065464 | 3391 | 2.697e-06 | 0.00022925 | 3441 | 0.05 | 2013
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | CR254 | FALSE | 2477.3187 | 1687.0283 | 1.0485 | 20 | 4.0719e-05 | 3253 | 0.065918 | 3242 | 2.6941e-06 | 5.3882e-05 | 3442 | 0.03 | 2367
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 36922 | TRUE | 8825.2123 | 0 | 0 | 37 | 4.0991e-05 | 3245 | 0.065148 | 3595 | 2.6705e-06 | 9.8808e-05 | 3443 |  | 2948
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 798137 | TRUE | 581.8228 | 68.0149 | 0.042272 | 5 | 4.0802e-05 | 3250 | 0.065404 | 3417 | 2.6637e-06 | 1.3319e-05 | 3444 |  | 3045
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 2016 | TRUE | 6829.6992 | 150.9724 | 0.09383 | 65 | 4.0813e-05 | 3249 | 0.065188 | 3525 | 2.6614e-06 | 0.00017299 | 3445 | 0.04 | 2208
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 317890 | TRUE | 125.8315 | 125.8315 | 0.078205 | 2 | 3.9991e-05 | 3269 | 0.066431 | 3031 | 2.6567e-06 | 5.3133e-06 | 3446 |  | 3501
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | CB | TRUE | 3469.4672 | 0 | 0 | 28 | 4.0756e-05 | 3251 | 0.065151 | 3570 | 2.6553e-06 | 7.4348e-05 | 3447 | 0.09 | 1558
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | CB | TRUE | 1170.6003 | 164.2523 | 0.10208 | 11 | 4.0346e-05 | 3259 | 0.065497 | 3371 | 2.651e-06 | 2.9161e-05 | 3448 | 0.27 | 1059
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 65894 | TRUE | 1441.6391 | 0 | 0 | 12 | 4.0627e-05 | 3255 | 0.065148 | 3601 | 2.6468e-06 | 3.1761e-05 | 3449 |  | 3031
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 931192 | FALSE | 11415.5971 | 3615.6701 | 2.2472 | 87 | 4.0212e-05 | 3262 | 0.065487 | 3375 | 2.6467e-06 | 0.00023026 | 3450 |  | 3020
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 2142 | TRUE | 2588.0177 | 151.8851 | 0.094397 | 26 | 4.0293e-05 | 3261 | 0.065246 | 3480 | 2.6301e-06 | 6.8383e-05 | 3451 | 0.08 | 1615
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | CB | FALSE | 4654.0755 | 1041.2537 | 0.64714 | 39 | 4.0081e-05 | 3266 | 0.065411 | 3410 | 2.6231e-06 | 0.0001023 | 3452 | 0.04 | 2160
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | CB | TRUE | 9581.6812 | 369.0017 | 0.22934 | 76 | 4.0032e-05 | 3268 | 0.065241 | 3484 | 2.617e-06 | 0.00019889 | 3453 | 0.16 | 1252
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 680537 | TRUE | 1060.8184 | 362.7293 | 0.22544 | 9 | 3.9362e-05 | 3278 | 0.065433 | 3403 | 2.5979e-06 | 2.3381e-05 | 3454 |  | 3424
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 512070 | TRUE | 481.613 | 279.6247 | 0.17379 | 5 | 3.9072e-05 | 3285 | 0.065661 | 3322 | 2.586e-06 | 1.293e-05 | 3455 |  | 3413
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | CB | FALSE | 9084.5965 | 2733.348 | 1.6988 | 81 | 3.9255e-05 | 3280 | 0.065515 | 3364 | 2.5838e-06 | 0.00020929 | 3456 | 0.24 | 1096
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | MR204 | TRUE | 4739.0907 | 326.5252 | 0.20294 | 46 | 3.9361e-05 | 3279 | 0.065259 | 3475 | 2.5759e-06 | 0.00011849 | 3457 |  | 2785
885 | EDES 1112CR308 | 13681112 | EDES 1112 | CR308 | FALSE | 5698.3231 | 5168.8003 | 3.2124 | 53 | 3.8446e-05 | 3292 | 0.066287 | 3153 | 2.5524e-06 | 0.00013527 | 3458 | 0.07 | 1769
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 12494 | TRUE | 4190.5486 | 220.1167 | 0.1368 | 35 | 3.9122e-05 | 3283 | 0.065184 | 3532 | 2.5505e-06 | 8.9268e-05 | 3459 |  | 3101
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | CB | TRUE | 8504.0553 | 0 | 0 | 41 | 3.9093e-05 | 3284 | 0.065147 | 3625 | 2.5468e-06 | 0.00010442 | 3460 | 0.18 | 1219
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 206248 | TRUE | 893.3087 | 83.0039 | 0.051587 | 10 | 3.895e-05 | 3288 | 0.065404 | 3414 | 2.5435e-06 | 2.5435e-05 | 3461 |  | 3179
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 37436 | FALSE | 3311.0305 | 1208.0743 | 0.75082 | 33 | 3.8691e-05 | 3289 | 0.065576 | 3347 | 2.5374e-06 | 8.3735e-05 | 3462 | 0.1 | 1485
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 9120 | FALSE | 11903.5244 | 2858.0041 | 1.7763 | 112 | 3.8665e-05 | 3290 | 0.065446 | 3397 | 2.5361e-06 | 0.00028404 | 3463 | 0.07 | 1741
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 398620 | TRUE | 770.3641 | 758.0837 | 0.47115 | 7 | 3.8215e-05 | 3297 | 0.066248 | 3163 | 2.531e-06 | 1.7717e-05 | 3464 |  | 3477
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 184672 | FALSE | 5259.1473 | 2666.0437 | 1.657 | 46 | 3.8231e-05 | 3295 | 0.065706 | 3307 | 2.5255e-06 | 0.00011617 | 3465 |  | 2869
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | CB | TRUE | 8128.5867 | 387.1496 | 0.24062 | 57 | 3.8448e-05 | 3291 | 0.065193 | 3515 | 2.5112e-06 | 0.00014314 | 3466 | 0.03 | 2279
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 2064 | FALSE | 1409.3976 | 1409.3976 | 0.87595 | 15 | 3.7422e-05 | 3305 | 0.066432 | 2982 | 2.486e-06 | 3.729e-05 | 3467 | 0.08 | 1660
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 42542 | TRUE | 5717.1489 | 862.3483 | 0.53595 | 52 | 3.7508e-05 | 3304 | 0.065348 | 3438 | 2.465e-06 | 0.00012818 | 3468 | 0.03 | 2335
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 34438 | FALSE | 8258.6725 | 3709.6211 | 2.3055 | 67 | 3.7308e-05 | 3309 | 0.065492 | 3373 | 2.4545e-06 | 0.00016445 | 3469 | 0.06 | 1800
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 97318 | TRUE | 1594.8254 | 294.9732 | 0.18333 | 18 | 3.7395e-05 | 3306 | 0.065576 | 3346 | 2.4455e-06 | 4.4019e-05 | 3470 | 0.03 | 2327
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 3049 | FALSE | 2682.1998 | 1650.9947 | 1.0261 | 23 | 3.708e-05 | 3312 | 0.065874 | 3249 | 2.4445e-06 | 5.6224e-05 | 3471 | 2.64 | 592
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 965060 | TRUE | 112.5171 | 99.6543 | 0.061936 | 1 | 3.6723e-05 | 3320 | 0.066431 | 3036 | 2.4396e-06 | 2.4396e-06 | 3472 |  | 3624
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 758798 | TRUE | 68.038 | 53.2652 | 0.033105 | 2 | 3.6428e-05 | 3325 | 0.065789 | 3289 | 2.4159e-06 | 4.8318e-06 | 3473 |  | 3603
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | CB | TRUE | 18410.6369 | 20.7388 | 0.012889 | 171 | 3.6749e-05 | 3319 | 0.065155 | 3560 | 2.3948e-06 | 0.00040951 | 3474 | 0.28 | 1039
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | P160 | TRUE | 10321.2013 | 0 | 0 | 96 | 3.6431e-05 | 3324 | 0.065148 | 3582 | 2.3734e-06 | 0.00022785 | 3475 | 2.76 | 583
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 116034 | TRUE | 4982.0059 | 539.5091 | 0.33531 | 41 | 3.6154e-05 | 3332 | 0.065278 | 3469 | 2.3641e-06 | 9.6928e-05 | 3476 |  | 2713
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 75844 | TRUE | 864.7167 | 272.6844 | 0.16947 | 10 | 3.5678e-05 | 3340 | 0.065275 | 3470 | 2.3271e-06 | 2.3271e-05 | 3477 | 0.02 | 2485
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 8846 | FALSE | 7060.9911 | 3588.6165 | 2.2303 | 61 | 3.5185e-05 | 3347 | 0.065737 | 3298 | 2.3218e-06 | 0.00014163 | 3478 | 0.04 | 2219
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | CB | TRUE | 1584.8668 | 745.3166 | 0.46322 | 19 | 3.5327e-05 | 3345 | 0.06535 | 3437 | 2.3127e-06 | 4.3942e-05 | 3479 | 0.02 | 2415
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 936988 | FALSE | 10891.0554 | 10891.0554 | 6.7688 | 86 | 3.4698e-05 | 3356 | 0.066432 | 2957 | 2.3051e-06 | 0.00019824 | 3480 |  | 2818
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 1270 | TRUE | 2454.7077 | 0 | 0 | 21 | 3.5345e-05 | 3343 | 0.06515 | 3579 | 2.3027e-06 | 4.8357e-05 | 3481 |  | 3133
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 258792 | FALSE | 4808.6867 | 4793.9751 | 2.9795 | 36 | 3.4657e-05 | 3358 | 0.066396 | 3121 | 2.3019e-06 | 8.287e-05 | 3482 |  | 2788
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 902998 | FALSE | 9746.2747 | 1732.2882 | 1.0766 | 81 | 3.5078e-05 | 3350 | 0.065372 | 3428 | 2.2981e-06 | 0.00018615 | 3483 |  | 2809
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 48936 | FALSE | 9703.0008 | 7437.214 | 4.6223 | 86 | 3.4701e-05 | 3355 | 0.066043 | 3210 | 2.2943e-06 | 0.00019731 | 3484 | 0.08 | 1663
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | P128 | TRUE | 4067.7934 | 190.9091 | 0.11865 | 31 | 3.4672e-05 | 3357 | 0.065272 | 3471 | 2.2678e-06 | 7.0301e-05 | 3485 | 0.03 | 2403
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 206332 | TRUE | 973.8303 | 488.8653 | 0.30383 | 7 | 3.1898e-05 | 3402 | 0.072747 | 2939 | 2.2569e-06 | 1.5798e-05 | 3486 |  | 3039
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | BR304 | FALSE | 5760.7882 | 2392.7287 | 1.4871 | 53 | 3.4151e-05 | 3368 | 0.06568 | 3316 | 2.2492e-06 | 0.00011921 | 3487 | 0.08 | 1595
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 685656 | FALSE | 5880.2294 | 1923.4165 | 1.1954 | 43 | 3.4111e-05 | 3369 | 0.06533 | 3449 | 2.2325e-06 | 9.5996e-05 | 3488 |  | 2845
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 60136 | TRUE | 6522.6172 | 0 | 0 | 57 | 3.4156e-05 | 3367 | 0.065147 | 3622 | 2.2252e-06 | 0.00012684 | 3489 |  | 2829
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 8872 | FALSE | 9042.2667 | 7244.0552 | 4.5022 | 77 | 3.3183e-05 | 3382 | 0.066165 | 3180 | 2.2015e-06 | 0.00016952 | 3490 | 0.09 | 1565
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 68070 | TRUE | 3445.6939 | 373.7094 | 0.23226 | 30 | 3.3642e-05 | 3372 | 0.065233 | 3488 | 2.1953e-06 | 6.5858e-05 | 3491 | 0.02 | 2503
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 504941 | TRUE | 1025.616 | 663.24 | 0.41221 | 6 | 3.3217e-05 | 3381 | 0.065578 | 3339 | 2.194e-06 | 1.3164e-05 | 3492 |  | 3375
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 9704 | TRUE | 4114.9938 | 786.5986 | 0.48887 | 29 | 3.3423e-05 | 3377 | 0.065369 | 3429 | 2.1872e-06 | 6.3429e-05 | 3493 | 0.4 | 944
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 9030 | FALSE | 4149.4333 | 3272.4558 | 2.0338 | 37 | 3.3072e-05 | 3384 | 0.06605 | 3209 | 2.1865e-06 | 8.0902e-05 | 3494 | 0.1 | 1476
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 2070 | TRUE | 3077.1707 | 843.4628 | 0.52422 | 26 | 3.3159e-05 | 3383 | 0.065444 | 3398 | 2.1767e-06 | 5.6595e-05 | 3495 | 0.04 | 2156
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 972264 | TRUE | 337.1983 | 0 | 0 | 4 | 3.3356e-05 | 3379 | 0.065151 | 3575 | 2.1732e-06 | 8.6927e-06 | 3496 |  | 3520
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 2082 | FALSE | 4925.5933 | 2445.1965 | 1.5197 | 46 | 3.2758e-05 | 3390 | 0.065762 | 3292 | 2.1552e-06 | 9.9139e-05 | 3497 | 0.08 | 1612
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 203897 | TRUE | 1017.3713 | 367.9073 | 0.22866 | 9 | 3.2839e-05 | 3388 | 0.065433 | 3405 | 2.1509e-06 | 1.9358e-05 | 3498 |  | 3108
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 656108 | TRUE | 1195.0984 | 838.7097 | 0.52126 | 10 | 3.2603e-05 | 3392 | 0.065918 | 3240 | 2.1478e-06 | 2.1478e-05 | 3499 |  | 2956
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | BR196 | TRUE | 5817.7228 | 0 | 0 | 51 | 3.2633e-05 | 3391 | 0.065172 | 3540 | 2.127e-06 | 0.00010848 | 3500 | 0.05 | 1940
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | CB | FALSE | 15907.2746 | 5284.9861 | 3.2846 | 136 | 3.2105e-05 | 3399 | 0.065515 | 3363 | 2.1195e-06 | 0.00028825 | 3501 | 0.06 | 1835
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 9104 | FALSE | 9586.0766 | 9148.567 | 5.6859 | 79 | 3.1817e-05 | 3404 | 0.066367 | 3133 | 2.113e-06 | 0.00016692 | 3502 | 0.18 | 1218
617 | OAK 0401CB | 12600401 | OAK 0401 | CB | FALSE | 8716.4726 | 5585.5806 | 3.4715 | 68 | 3.153e-05 | 3408 | 0.06596 | 3231 | 2.0871e-06 | 0.00014192 | 3503 | 0.09 | 1539
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 9698 | TRUE | 1062.5186 | 929.6624 | 0.57779 | 10 | 3.1068e-05 | 3415 | 0.066303 | 3148 | 2.0607e-06 | 2.0607e-05 | 3504 | 0.07 | 1771
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | BR316 | FALSE | 6608.6922 | 6608.6922 | 4.1073 | 56 | 3.0991e-05 | 3416 | 0.066432 | 2970 | 2.0588e-06 | 0.00011529 | 3505 | 0.12 | 1388
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 57953 | TRUE | 1217.1907 | 353.2769 | 0.21956 | 11 | 3.1168e-05 | 3413 | 0.065497 | 3370 | 2.0515e-06 | 2.2566e-05 | 3506 | 0.34 | 977
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | CB | TRUE | 8361.6686 | 466.2641 | 0.28979 | 63 | 3.1091e-05 | 3414 | 0.065209 | 3507 | 2.0367e-06 | 0.00012831 | 3507 | 0.03 | 2390
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | CB | TRUE | 1166.6657 | 0 | 0 | 15 | 3.1212e-05 | 3412 | 0.065147 | 3617 | 2.0334e-06 | 3.0501e-05 | 3508 |  | 3022
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | CB | TRUE | 7506.165 | 0 | 0 | 70 | 3.0936e-05 | 3418 | 0.065147 | 3616 | 2.0154e-06 | 0.00014108 | 3509 | 0.05 | 2064
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | CB | TRUE | 7799.5565 | 109.5296 | 0.068073 | 62 | 3.075e-05 | 3420 | 0.065188 | 3523 | 2.0046e-06 | 0.00012428 | 3510 | 0.02 | 2475
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 781759 | TRUE | 264.5561 | 210.4887 | 0.13082 | 4 | 3.0572e-05 | 3422 | 0.065789 | 3288 | 2.0026e-06 | 8.0105e-06 | 3511 |  | 3469
254 | HICKS 1116CB | 83431116 | HICKS 1116 | CB | TRUE | 22837.5991 | 336.1648 | 0.20893 | 165 | 2.9963e-05 | 3426 | 0.065178 | 3539 | 1.9553e-06 | 0.00032262 | 3512 | 0.04 | 2128
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 1019 | TRUE | 1173.8689 | 432.0709 | 0.26853 | 10 | 2.9828e-05 | 3428 | 0.065279 | 3468 | 1.946e-06 | 1.946e-05 | 3513 | 0.07 | 1695
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 546744 | TRUE | 633.1716 | 428.8696 | 0.26654 | 7 | 2.921e-05 | 3435 | 0.065882 | 3248 | 1.934e-06 | 1.3538e-05 | 3514 |  | 3577
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 994213 | TRUE | 860.1534 | 198.7798 | 0.12354 | 8 | 2.9167e-05 | 3437 | 0.065311 | 3455 | 1.9051e-06 | 1.5241e-05 | 3515 |  | 3071
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 849701 | TRUE | 220.6039 | 213.7724 | 0.13286 | 2 | 2.8441e-05 | 3447 | 0.065789 | 3283 | 1.8894e-06 | 3.7788e-06 | 3516 |  | 3358
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 9540 | FALSE | 3592.089 | 2319.7097 | 1.4417 | 32 | 2.8532e-05 | 3444 | 0.06587 | 3251 | 1.8885e-06 | 6.0431e-05 | 3517 | 0.02 | 2557
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 884949 | TRUE | 693.01 | 312.7335 | 0.19437 | 5 | 2.8569e-05 | 3443 | 0.065663 | 3319 | 1.8768e-06 | 9.3841e-06 | 3518 |  | 3352
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 965216 | FALSE | 2651.8859 | 2642.7419 | 1.6425 | 21 | 2.8136e-05 | 3457 | 0.066371 | 3131 | 1.868e-06 | 3.9227e-05 | 3519 |  | 3185
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 104588 | TRUE | 1238.8359 | 581.4114 | 0.36135 | 11 | 2.8291e-05 | 3451 | 0.065731 | 3301 | 1.8653e-06 | 2.0518e-05 | 3520 |  | 2924
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 31512 | TRUE | 3255.9931 | 0 | 0 | 29 | 2.8486e-05 | 3446 | 0.065148 | 3589 | 1.8558e-06 | 5.3819e-05 | 3521 | 6.49 | 467
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 344 | FALSE | 12052.7047 | 1314.7551 | 0.81713 | 97 | 2.8339e-05 | 3449 | 0.065283 | 3467 | 1.8552e-06 | 0.00017996 | 3522 | 0.06 | 1814
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | W52 | FALSE | 6677.88 | 5033.3373 | 3.1282 | 51 | 2.807e-05 | 3459 | 0.066004 | 3224 | 1.8539e-06 | 9.4548e-05 | 3523 | 0.05 | 1977
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | BR180 | TRUE | 3108.6276 | 675.0712 | 0.41956 | 25 | 2.814e-05 | 3456 | 0.065507 | 3367 | 1.8513e-06 | 4.6282e-05 | 3524 | 3.92 | 531
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | CR306 | FALSE | 1619.5833 | 1619.5833 | 1.0066 | 16 | 2.7663e-05 | 3463 | 0.066432 | 2950 | 1.8377e-06 | 2.9404e-05 | 3525 | 0.04 | 2175
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | CB | TRUE | 9244.1392 | 431.1151 | 0.26794 | 75 | 2.7307e-05 | 3468 | 0.065217 | 3501 | 1.7835e-06 | 0.00013376 | 3526 | 0.02 | 2558
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | CB | TRUE | 4463.0648 | 40.2966 | 0.025045 | 38 | 2.7246e-05 | 3469 | 0.065182 | 3535 | 1.7766e-06 | 6.751e-05 | 3527 | 0.04 | 2082
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 8862 | TRUE | 4562.4649 | 0 | 0 | 38 | 2.7115e-05 | 3471 | 0.065147 | 3615 | 1.7665e-06 | 6.7125e-05 | 3528 | 0.02 | 2559
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 57046 | TRUE | 1135.0639 | 48.9091 | 0.030397 | 12 | 2.6931e-05 | 3474 | 0.065362 | 3431 | 1.7587e-06 | 2.1104e-05 | 3529 |  | 2873
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | MR205 | TRUE | 8740.8692 | 0 | 0 | 73 | 2.6763e-05 | 3475 | 0.065182 | 3534 | 1.7478e-06 | 0.00012759 | 3530 |  | 2764
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 9112 | FALSE | 5302.286 | 1359.4094 | 0.84488 | 43 | 2.6492e-05 | 3480 | 0.065387 | 3422 | 1.7421e-06 | 7.4909e-05 | 3531 | 0.55 | 872
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | BR236 | TRUE | 850.4173 | 819.8964 | 0.50957 | 7 | 2.6231e-05 | 3484 | 0.066065 | 3207 | 1.7373e-06 | 1.2161e-05 | 3532 | 0.06 | 1860
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 820379 | TRUE | 298.2228 | 245.2911 | 0.15245 | 2 | 2.6136e-05 | 3485 | 0.066431 | 3032 | 1.7362e-06 | 3.4724e-06 | 3533 |  | 3139
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 573610 | TRUE | 5029.4735 | 0 | 0 | 41 | 2.6462e-05 | 3481 | 0.065179 | 3538 | 1.7259e-06 | 7.0764e-05 | 3534 |  | 2722
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 9148 | TRUE | 6634.7635 | 0 | 0 | 51 | 2.6423e-05 | 3482 | 0.065147 | 3618 | 1.7214e-06 | 8.7791e-05 | 3535 | 0.07 | 1762
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 9094 | TRUE | 4020.7215 | 160.2742 | 0.099611 | 32 | 2.6274e-05 | 3483 | 0.065228 | 3493 | 1.7132e-06 | 5.4823e-05 | 3536 | 0.02 | 2542
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 2634 | TRUE | 2692.6366 | 0 | 0 | 23 | 2.5666e-05 | 3490 | 0.065148 | 3596 | 1.6721e-06 | 3.8458e-05 | 3537 | 0.02 | 2497
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | CR150 | TRUE | 755.1885 | 348.5421 | 0.21662 | 6 | 2.5203e-05 | 3494 | 0.065789 | 3290 | 1.667e-06 | 1.0002e-05 | 3538 | 0.05 | 1981
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | CB | TRUE | 3993.2278 | 151.4693 | 0.094139 | 40 | 2.5491e-05 | 3491 | 0.06518 | 3537 | 1.6633e-06 | 6.6534e-05 | 3539 |  | 3157
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 375239 | TRUE | 343.55 | 145.1624 | 0.090219 | 4 | 2.5051e-05 | 3495 | 0.065468 | 3385 | 1.6455e-06 | 6.5821e-06 | 3540 |  | 3299
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 345099 | TRUE | 497.3995 | 293.3262 | 0.1823 | 5 | 2.4872e-05 | 3496 | 0.065404 | 3416 | 1.6312e-06 | 8.156e-06 | 3541 |  | 3324
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 3116 | FALSE | 1685.1043 | 1250.9687 | 0.77748 | 10 | 2.4549e-05 | 3500 | 0.066175 | 3176 | 1.6267e-06 | 1.6267e-05 | 3542 | 0.01 | 2592
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 502466 | TRUE | 854.2839 | 226.0238 | 0.14047 | 10 | 2.4427e-05 | 3501 | 0.065532 | 3357 | 1.6151e-06 | 1.6151e-05 | 3543 |  | 2745
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | CB | FALSE | 12969.6445 | 1669.1452 | 1.0374 | 103 | 2.4362e-05 | 3504 | 0.065322 | 3453 | 1.6033e-06 | 0.00016514 | 3544 | 0.03 | 2287
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | BR346 | TRUE | 11386.6089 | 0 | 0 | 102 | 2.4397e-05 | 3502 | 0.065147 | 3620 | 1.5894e-06 | 0.00016212 | 3545 | 0.02 | 2439
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | CB | FALSE | 8520.938 | 4604.9325 | 2.862 | 70 | 2.3671e-05 | 3507 | 0.065808 | 3264 | 1.5619e-06 | 0.00010933 | 3546 | 0.05 | 2038
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 850884 | FALSE | 2534.335 | 1368.1711 | 0.85032 | 19 | 2.3486e-05 | 3510 | 0.065756 | 3294 | 1.5552e-06 | 2.9549e-05 | 3547 |  | 3036
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 915474 | TRUE | 13475.5148 | 697.4237 | 0.43345 | 98 | 2.3059e-05 | 3511 | 0.065213 | 3504 | 1.5073e-06 | 0.00014771 | 3548 |  | 2723
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 83200 | TRUE | 4654.5591 | 0 | 0 | 48 | 2.2575e-05 | 3514 | 0.065158 | 3558 | 1.471e-06 | 7.0606e-05 | 3549 |  | 2716
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 48338 | TRUE | 1760.6636 | 181.1517 | 0.11259 | 17 | 2.2364e-05 | 3515 | 0.065147 | 3613 | 1.4569e-06 | 2.4768e-05 | 3550 | 0.03 | 2329
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 9126 | FALSE | 3038.2902 | 1621.4045 | 1.0077 | 25 | 2.1702e-05 | 3526 | 0.065969 | 3226 | 1.4329e-06 | 3.5823e-05 | 3551 | 0.04 | 2080
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 2614 | FALSE | 3446.6772 | 1037.2147 | 0.64463 | 28 | 2.1909e-05 | 3521 | 0.065331 | 3444 | 1.4317e-06 | 4.0087e-05 | 3552 | 0.03 | 2331
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 86496 | FALSE | 10364.0845 | 1600.54 | 0.99474 | 94 | 2.1714e-05 | 3525 | 0.065366 | 3430 | 1.4269e-06 | 0.00013413 | 3553 | 0.02 | 2498
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 888954 | TRUE | 504.7129 | 0 | 0 | 6 | 2.1724e-05 | 3524 | 0.065147 | 3623 | 1.4152e-06 | 8.4914e-06 | 3554 |  | 3272
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | CR164 | FALSE | 10563.0436 | 2405.3877 | 1.495 | 85 | 2.1366e-05 | 3530 | 0.065434 | 3402 | 1.4079e-06 | 0.00011967 | 3555 | 0.03 | 2312
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 209865 | TRUE | 1489.582 | 423.0102 | 0.2629 | 11 | 2.1415e-05 | 3529 | 0.065497 | 3369 | 1.4074e-06 | 1.5482e-05 | 3556 |  | 3125
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 153228 | TRUE | 6680.4391 | 463.496 | 0.28806 | 54 | 2.1538e-05 | 3528 | 0.065195 | 3513 | 1.4041e-06 | 7.5821e-05 | 3557 | 0.02 | 2445
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | XR300 | TRUE | 1391.3933 | 526.7556 | 0.32738 | 14 | 2.1221e-05 | 3531 | 0.065331 | 3446 | 1.3951e-06 | 1.9531e-05 | 3558 | 0.04 | 2106
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 173396 | TRUE | 265.7346 | 265.7346 | 0.16516 | 3 | 2.0973e-05 | 3534 | 0.066004 | 3220 | 1.3889e-06 | 4.1666e-06 | 3559 |  | 3563
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 313472 | TRUE | 1178.1951 | 43.1608 | 0.026825 | 9 | 2.0676e-05 | 3537 | 0.06529 | 3465 | 1.3509e-06 | 1.2158e-05 | 3560 |  | 3319
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 151462 | TRUE | 247.7748 | 247.7748 | 0.15399 | 3 | 2.0466e-05 | 3540 | 0.066005 | 3216 | 1.3417e-06 | 4.025e-06 | 3561 |  | 3443
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 472928 | TRUE | 1622.1027 | 124.8253 | 0.077579 | 14 | 2.0412e-05 | 3541 | 0.065331 | 3448 | 1.3331e-06 | 1.8663e-05 | 3562 |  | 3192
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | CR252 | FALSE | 9962.669 | 1765.2604 | 1.0971 | 92 | 2.0001e-05 | 3543 | 0.065384 | 3423 | 1.3184e-06 | 0.0001213 | 3563 | 0.03 | 2364
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | MR379 | FALSE | 2535.6763 | 1749.5827 | 1.0874 | 22 | 1.987e-05 | 3545 | 0.065965 | 3229 | 1.3088e-06 | 2.8794e-05 | 3564 |  | 2658
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 3487 | TRUE | 2909.578 | 0 | 0 | 20 | 1.9374e-05 | 3547 | 0.065147 | 3626 | 1.2622e-06 | 2.5244e-05 | 3565 |  | 3359
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | CB | TRUE | 4613.0306 | 118.7443 | 0.0738 | 41 | 1.9334e-05 | 3548 | 0.065148 | 3592 | 1.2596e-06 | 5.1642e-05 | 3566 | 0.02 | 2443
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 246034 | TRUE | 413.5355 | 202.2758 | 0.12572 | 4 | 1.9193e-05 | 3549 | 0.065471 | 3380 | 1.2578e-06 | 5.0314e-06 | 3567 |  | 3188
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | V44 | FALSE | 1767.9988 | 1259.7645 | 0.78295 | 17 | 1.8999e-05 | 3551 | 0.065827 | 3260 | 1.2575e-06 | 2.1378e-05 | 3568 | 0.03 | 2281
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | CR330 | FALSE | 3874.576 | 1155.5838 | 0.7182 | 31 | 1.8986e-05 | 3552 | 0.065438 | 3399 | 1.2463e-06 | 3.8635e-05 | 3569 | 0.03 | 2322
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | CR328 | TRUE | 7907.5061 | 956.1241 | 0.59424 | 68 | 1.9049e-05 | 3550 | 0.065298 | 3462 | 1.2458e-06 | 8.4712e-05 | 3570 |  | 2687
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 85904 | FALSE | 3179.0036 | 1684.9898 | 1.0472 | 24 | 1.8827e-05 | 3555 | 0.065629 | 3329 | 1.2443e-06 | 2.9864e-05 | 3571 | 0.03 | 2340
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 13333 | TRUE | 480.3389 | 70.7861 | 0.043994 | 4 | 1.8911e-05 | 3554 | 0.065469 | 3382 | 1.2398e-06 | 4.9594e-06 | 3572 | 0.02 | 2476
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | V80 | TRUE | 3197.8948 | 222.7519 | 0.13844 | 28 | 1.8567e-05 | 3557 | 0.065193 | 3516 | 1.2121e-06 | 3.3939e-05 | 3573 |  | 2973
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 9090 | TRUE | 4202.8057 | 0 | 0 | 38 | 1.848e-05 | 3559 | 0.065147 | 3627 | 1.2039e-06 | 4.5748e-05 | 3574 |  | 2679
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | CB | TRUE | 9405.5468 | 893.6462 | 0.5554 | 84 | 1.7813e-05 | 3561 | 0.065258 | 3477 | 1.1648e-06 | 9.7839e-05 | 3575 | 0.03 | 2356
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 8956 | TRUE | 2231.1917 | 474.6132 | 0.29497 | 18 | 1.7617e-05 | 3564 | 0.065361 | 3432 | 1.1529e-06 | 2.0752e-05 | 3576 |  | 2884
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 751 | TRUE | 4384.8994 | 264.612 | 0.16446 | 31 | 1.7653e-05 | 3563 | 0.065234 | 3487 | 1.1521e-06 | 3.5714e-05 | 3577 | 0.02 | 2530
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | CB | TRUE | 8238.1953 | 128.9588 | 0.080148 | 69 | 1.7565e-05 | 3565 | 0.065167 | 3548 | 1.1453e-06 | 7.9023e-05 | 3578 | 0.04 | 2203
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | BR110 | TRUE | 5064.9775 | 0 | 0 | 45 | 1.7521e-05 | 3566 | 0.065147 | 3628 | 1.1415e-06 | 5.1365e-05 | 3579 | 18.55 | 320
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 2644 | FALSE | 2922.7748 | 1828.1218 | 1.1362 | 23 | 1.7252e-05 | 3567 | 0.065706 | 3306 | 1.1355e-06 | 2.6115e-05 | 3580 | 0.03 | 2385
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | CB | TRUE | 16910.3925 | 74.5132 | 0.04631 | 140 | 1.6863e-05 | 3571 | 0.065612 | 3334 | 1.1257e-06 | 0.0001576 | 3581 |  | 2813
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 38582 | TRUE | 8624.1276 | 853.8778 | 0.53069 | 53 | 1.7201e-05 | 3569 | 0.065245 | 3483 | 1.1245e-06 | 5.9598e-05 | 3582 |  | 2701
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 6783 | TRUE | 6579.5365 | 0 | 0 | 50 | 1.7237e-05 | 3568 | 0.065147 | 3629 | 1.1229e-06 | 5.6147e-05 | 3583 | 1.8 | 643
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | W12 | FALSE | 10251.7677 | 6046.1264 | 3.7577 | 70 | 1.562e-05 | 3581 | 0.06699 | 2947 | 1.0833e-06 | 7.5829e-05 | 3584 | 0.07 | 1755
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 500 | TRUE | 5066.4275 | 426.2211 | 0.2649 | 39 | 1.6529e-05 | 3573 | 0.065312 | 3454 | 1.0777e-06 | 4.203e-05 | 3585 |  | 2856
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | MR218 | FALSE | 18150.1664 | 10386.8132 | 6.4554 | 134 | 1.6173e-05 | 3577 | 0.065722 | 3303 | 1.0693e-06 | 0.00014329 | 3586 | 0.06 | 1868
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | CB | FALSE | 18622.3449 | 1675.1277 | 1.0411 | 153 | 1.6122e-05 | 3579 | 0.065231 | 3490 | 1.0578e-06 | 0.00016184 | 3587 | 0.03 | 2299
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | CB | TRUE | 2575.0657 | 47.0231 | 0.029225 | 21 | 1.6197e-05 | 3575 | 0.065147 | 3630 | 1.0552e-06 | 2.2159e-05 | 3588 | 0.03 | 2266
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | P190 | TRUE | 3318.5959 | 0 | 0 | 28 | 1.6177e-05 | 3576 | 0.065148 | 3590 | 1.0539e-06 | 2.951e-05 | 3589 | 0.06 | 1830
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | CB | TRUE | 11158.113 | 159.3502 | 0.099037 | 95 | 1.5874e-05 | 3580 | 0.065161 | 3554 | 1.0373e-06 | 9.8546e-05 | 3590 |  | 2653
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | CB | TRUE | 7478.2552 | 0 | 0 | 59 | 1.558e-05 | 3582 | 0.06517 | 3542 | 1.0169e-06 | 5.9995e-05 | 3591 | 0.04 | 2225
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | CR198 | TRUE | 8475.9687 | 515.4771 | 0.32037 | 70 | 1.5357e-05 | 3584 | 0.065239 | 3486 | 1.006e-06 | 7.0418e-05 | 3592 | 0.02 | 2547
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 760530 | TRUE | 2038.4891 | 342.5788 | 0.21291 | 13 | 1.4653e-05 | 3588 | 0.065542 | 3354 | 9.624e-07 | 1.2511e-05 | 3593 |  | 3041
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | W22 | FALSE | 10106.4598 | 4174.2289 | 2.5943 | 85 | 1.451e-05 | 3590 | 0.065661 | 3323 | 9.5877e-07 | 8.1495e-05 | 3594 | 0.1 | 1467
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | MR201 | FALSE | 13962.3911 | 2014.3888 | 1.252 | 112 | 1.4628e-05 | 3589 | 0.065296 | 3463 | 9.5698e-07 | 0.00010718 | 3595 |  | 2794
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 1224 | TRUE | 3249.7676 | 17.2769 | 0.010738 | 29 | 1.4357e-05 | 3591 | 0.065191 | 3519 | 9.3531e-07 | 2.7124e-05 | 3596 | 0.02 | 2522
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | CB | TRUE | 6943.4772 | 158.1749 | 0.098306 | 63 | 1.4057e-05 | 3592 | 0.065208 | 3508 | 9.1814e-07 | 5.7843e-05 | 3597 | 0.06 | 1787
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | CB | TRUE | 11783.4703 | 4.3429 | 0.0026991 | 99 | 1.3941e-05 | 3593 | 0.065147 | 3631 | 9.0819e-07 | 8.9911e-05 | 3598 | 0.02 | 2417
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | P124 | TRUE | 5089.5347 | 0 | 0 | 43 | 1.3878e-05 | 3594 | 0.065148 | 3584 | 9.0411e-07 | 3.8877e-05 | 3599 | 0.02 | 2525
3672 | EDES 1112CB | 13681112 | EDES 1112 | CB | TRUE | 911.838 | 70.4619 | 0.043792 | 16 | 1.3748e-05 | 3595 | 0.065227 | 3494 | 8.9903e-07 | 1.4384e-05 | 3600 | 0.03 | 2275
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 9110 | TRUE | 6943.3735 | 472.9116 | 0.29392 | 58 | 1.3463e-05 | 3596 | 0.06517 | 3544 | 8.7872e-07 | 5.0966e-05 | 3601 | 0.03 | 2318
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 88190 | TRUE | 4658.7637 | 163.0348 | 0.10133 | 34 | 1.3144e-05 | 3598 | 0.065223 | 3499 | 8.5763e-07 | 2.9159e-05 | 3602 | 0.01 | 2609
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 9440 | TRUE | 5507.5 | 123.7395 | 0.076905 | 55 | 1.3106e-05 | 3599 | 0.065171 | 3541 | 8.5438e-07 | 4.6991e-05 | 3603 |  | 2959
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 125484 | FALSE | 2451.828 | 1202.5462 | 0.74739 | 4 | 1.3036e-05 | 3600 | 11.9509 | 2589 | 8.4928e-07 | 3.3971e-06 | 3604 |  | 3614
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 793774 | TRUE | 378.8633 | 111.8888 | 0.069539 | 3 | 1.2894e-05 | 3602 | 0.065147 | 3633 | 8.3998e-07 | 2.52e-06 | 3605 |  | 3586
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | CB | TRUE | 4157.1829 | 423.1153 | 0.26297 | 35 | 1.2627e-05 | 3603 | 0.065184 | 3531 | 8.2339e-07 | 2.8819e-05 | 3606 | 0.04 | 2089
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 714759 | TRUE | 1469.7626 | 361.9191 | 0.22493 | 11 | 1.2348e-05 | 3605 | 0.065497 | 3372 | 8.1071e-07 | 8.9178e-06 | 3607 |  | 2936
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | CR242 | TRUE | 7351.3672 | 499.489 | 0.31043 | 59 | 1.2355e-05 | 3604 | 0.065191 | 3520 | 8.0537e-07 | 4.7517e-05 | 3608 | 0.02 | 2462
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | MR236 | FALSE | 13624.1451 | 2212.8784 | 1.3753 | 112 | 1.2234e-05 | 3607 | 0.065342 | 3441 | 8.0193e-07 | 8.9816e-05 | 3609 |  | 2670
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | CB | TRUE | 3472.0335 | 0 | 0 | 28 | 1.2296e-05 | 3606 | 0.065147 | 3624 | 8.0102e-07 | 2.2429e-05 | 3610 | 0.02 | 2412
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | CB | TRUE | 30164.8941 | 0 | 0 | 253 | 1.2121e-05 | 3608 | 0.065147 | 3612 | 7.8965e-07 | 0.00019978 | 3611 |  | 2681
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 2642 | TRUE | 3637.2616 | 0 | 0 | 28 | 1.2095e-05 | 3609 | 0.065148 | 3594 | 7.8793e-07 | 2.2062e-05 | 3612 | 0.02 | 2511
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | MR545 | FALSE | 7246.1985 | 3496.0754 | 2.1728 | 66 | 1.1654e-05 | 3610 | 0.065789 | 3280 | 7.6919e-07 | 5.0766e-05 | 3613 | 0.06 | 1782
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 191498 | TRUE | 267.6915 | 189.8568 | 0.118 | 2 | 1.1046e-05 | 3611 | 0.065789 | 3281 | 7.2794e-07 | 1.4559e-06 | 3614 |  | 3198
749 | WALDO 0401CB | 13350401 | WALDO 0401 | CB | TRUE | 6516.7767 | 0 | 0 | 56 | 1.0513e-05 | 3612 | 0.06517 | 3543 | 6.8547e-07 | 3.8386e-05 | 3615 | 0.03 | 2378
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 337754 | TRUE | 259.7315 | 97.7177 | 0.060732 | 3 | 9.3717e-06 | 3613 | 0.065147 | 3606 | 6.1054e-07 | 1.8316e-06 | 3616 |  | 3283
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 404754 | FALSE | 1404.0353 | 1388.0334 | 0.86267 | 2 | 8.7569e-06 | 3616 | 0.065789 | 3284 | 5.7048e-07 | 1.141e-06 | 3617 |  | 3630
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 9060 | FALSE | 14415.2582 | 1524.9134 | 0.94774 | 98 | 8.4533e-06 | 3617 | 0.065226 | 3496 | 5.5361e-07 | 5.4254e-05 | 3618 | 0.58 | 857
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 501762 | TRUE | 2438.6275 | 775.0508 | 0.4817 | 23 | 8.4178e-06 | 3618 | 0.065482 | 3377 | 5.5098e-07 | 1.2672e-05 | 3619 |  | 2821
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 934870 | TRUE | 804.8523 | 147.5524 | 0.091704 | 7 | 8.4048e-06 | 3619 | 0.065514 | 3365 | 5.496e-07 | 3.8472e-06 | 3620 |  | 3338
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | CR284 | FALSE | 1550.6574 | 1235.8311 | 0.76807 | 14 | 7.7666e-06 | 3623 | 0.066065 | 3205 | 5.1364e-07 | 7.191e-06 | 3621 | 0.04 | 2148
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | CR002 | TRUE | 1715.8521 | 269.8408 | 0.16771 | 16 | 7.83e-06 | 3620 | 0.065308 | 3461 | 5.1358e-07 | 8.2173e-06 | 3622 | 0.13 | 1341
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 330790 | TRUE | 714.0791 | 199.5624 | 0.12403 | 8 | 7.7899e-06 | 3621 | 0.065468 | 3389 | 5.0999e-07 | 4.0799e-06 | 3623 |  | 2979
915 | WALDO 0402CB | 13350402 | WALDO 0402 | CB | TRUE | 3475.548 | 0 | 0 | 27 | 7.7732e-06 | 3622 | 0.065147 | 3610 | 5.064e-07 | 1.3673e-05 | 3624 | 0.05 | 1955
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | CB | TRUE | 13277.3465 | 69.3073 | 0.043075 | 103 | 7.67e-06 | 3624 | 0.065147 | 3609 | 4.9968e-07 | 5.1467e-05 | 3625 |  | 2677
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | CB | TRUE | 1942.0349 | 0 | 0 | 20 | 7.5209e-06 | 3625 | 0.065211 | 3506 | 4.9106e-07 | 9.8213e-06 | 3626 |  | 2929
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 52715 | TRUE | 6122.4469 | 0 | 0 | 60 | 7.374e-06 | 3626 | 0.065147 | 3605 | 4.8039e-07 | 2.8824e-05 | 3627 |  | 2661
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | V48 | TRUE | 4125.7287 | 198.7298 | 0.12351 | 39 | 7.0816e-06 | 3628 | 0.06518 | 3536 | 4.6154e-07 | 1.8e-05 | 3628 | 0.02 | 2477
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 458451 | FALSE | 3952.1728 | 1967.4653 | 1.2228 | 29 | 6.9026e-06 | 3629 | 0.06559 | 3336 | 4.5289e-07 | 1.3134e-05 | 3629 |  | 2862
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | CB | TRUE | 7369.6347 | 597.2084 | 0.37117 | 58 | 6.6635e-06 | 3630 | 0.065191 | 3518 | 4.3467e-07 | 2.5211e-05 | 3630 | 0.02 | 2520
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 36948 | TRUE | 13534.0061 | 809.6273 | 0.50319 | 109 | 6.1078e-06 | 3631 | 0.065183 | 3533 | 3.9816e-07 | 4.34e-05 | 3631 |  | 2715
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 132304 | TRUE | 1491.8996 | 118.6631 | 0.07375 | 13 | 5.8099e-06 | 3632 | 0.065147 | 3607 | 3.785e-07 | 4.9205e-06 | 3632 |  | 3288
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 36526 | TRUE | 10589.2357 | 72.2645 | 0.044913 | 84 | 5.5602e-06 | 3633 | 0.065163 | 3552 | 3.6398e-07 | 3.0574e-05 | 3633 | 0.02 | 2418
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | W04 | TRUE | 3941.4804 | 437.2441 | 0.27175 | 26 | 3.5981e-06 | 3634 | 0.065147 | 3634 | 2.344e-07 | 6.0945e-06 | 3634 |  | 3060
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | CB | TRUE | 0 | 0 | 0 |  |  | 3635 |  | 3635 |  | 0 | 3635 |  | 3635

## Cancelled Projects
Order | KEEP | Exec. Status | LTIP Condition 1 | LTIP Condition 2 | Priority | Original OH Miles | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | 2018 KPMG CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notif. | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | EASOP Risk Reduced | EASOP NPV ($000) | EASOP RSE | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost
35219265 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3843.5 | UNSE | 102251101 | CRESTA 1101 | CRESTA 1101546650 | 6 | 0.89694 | 33 | 3.0174 | 0.50291 | 845 | 0 |  | Tier 2 & 3 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543353 | E.5034700.01.01 | 120141941 | 35219265 | CWSP - CRESTA 1101546650 | 4752 | 0 | 0 | 0 |  | 2021-00911 | 2323.2 | 0.44 | 500000 |  |  |  |  | 0 | 0 |  |  |  | 0
35224320 | RE-ASSIGN |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 42301101 | TULUCAY 1101 | TULUCAY 1101628 | 98 | 4.1726 | 338 | 19.2923 | 0.19686 | 448 | 0 | 2350 | Tier 2 | WDDB | NAPA | Napa | North Bay | Bay Area | 5530168 |  | 113676059 | 31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 10050 | 0 | 0 | 0 |  | 2020-88272 | 7392 | 1.4 | 2360320 |  |  |  |  | 0 | 0 |  |  |  | 0
35219092 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3311.75 | UNSE | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 2104CB | 38 | 5.3534 | 15 | 26.7607 | 0.70423 | 51 | 0 |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794539 | E.5034691.01.01 | 120141620 | 35219092 | CWSP - POSO MOUNTAIN 2104CB | 28248 | 0 | 0 | 0 | [9 empty] | 0 | 0 |  |  |  | 0
35219264 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 2965.22 | UNSE | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 2103CB | 10 | 2.3287 | 30 | 5.1619 | 0.51619 | 2 | 0 |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794550 | E.5034699.01.01 | 120141886 | 35219264 | CWSP - POSO MOUNTAIN 2103CB | 12302.4 | 0 | 0 | 0 | [9 empty] | 0 | 0 |  |  |  | 0
35219282 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 1866.02 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | 0 |  | Tier 2 | CWSP | DUBLIN | Alameda | Mission | Central Coast | 5543349 | E.5034711.01.01 | 120142312 | 35219282 | CWSP - NORTH DUBLIN 2101 CB | 5280 | 0 | 0 | 0 |  | 2020-88260 | 5280 | 1 | 1699520 | 2021-04299 |  |  |  | 0 | 0 |  |  |  | 0
35219283 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3025.68 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | 0 |  | Tier 2 | CWSP | PLEASANTON | Contra Costa | Mission | Central Coast | 5543351 | E.5034712.01.01 | 120142316 | 35219283 | CWSP - NORTH DUBLIN 2101 CB | 4329.6 | 0 | 0 | 0 |  | 2020-88250 | 4329.6 | 0.82 | 1370560 | 2021-04306 |  |  |  | 0 | 0 |  |  |  | 0
35223061 | CANCEL |  | MEET | MEET |  |  |  | 0 | 2021 |  |  | 0 | 840.53 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | 0 |  |  | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.02 | 120242677 | 35223061 | PSPS - Calistoga 1102634 | 0 | 4752 | 0 | 0 |  | 2021-01583 | 4752 | 0.9 | 711300 | 2021-07704 |  |  |  | 0 |  |  |  |  | 0
35098621 | Completed |  | COMP |  |  |  | 1.07 | 0 | 2020 | 1.07 |  | 1.07 | 1372204.3 | DOCC | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.0162 | 198 | Tier 3 | PRE | NORTH SAN JUAN | Nevada | Sierra | Northern | 5785303 | E.5015491.04 | 117177530 | 35098621 | CWSP-COLUMBIA HILL 1101-LR2212-PH4 | 1881 | 3761 | 0 | 0 |  | 2018-57269 | 9820.8 | 1.86 | 1975040 | 2019-28761 | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 |  |  |  | 2019-39374 | 2020-25928 | 0 | 3761 | 1881 | 5642 | 1.0686 | 2185500 | 2927538 | 387.3626
|  |  | CNCL |  |  |  | 0.04 | 0.04 | 2021 |  |  |  | 0 | CNCL | 48011144 | CALPINE 1144 | CALPINE 1144304 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  | CWSP |  |  |  |  | 5543354 | E.5034701.01.01 |  | CNCL | CWSP - CALPINE 1144304 | [13 empty] | 0 | 0
35145522 | PSPS - HOLD |  | HOLD |  |  |  | 3.95 | 3.95 | 2021 |  |  |  | 142609.46 | PEND | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | 107 | 8.8028 | 134 | 32.5187 | 0.30391 | 385 | 14.4458 | 541 | Tier 3 | PSPS | El Dorado Hills | El Dorado | Sierra | Northern | 5788783 | E.5025635.01 | 118265394 | 35145522 | PSPS - Clarksville 2104 - CB | 0 | 13464 | 0 | 0 |  | 2019-80671 | 13464 | 2.55 | 23720000 | N/A | 0 | 13464 | 0 | 13464 | 2.55 | 10710000 |  |  |  | 2020-38602
35145001 | PSPS - HOLD |  | HOLD |  |  |  | 1.6 | 1.6 | 2021 |  |  |  | 146558.55 | PEND | 12022215 | CLAYTON 2215 | CLAYTON 2215184604 | 106 | 2.0891 | 1739 | 1.7951 | 0.016935 | 1716 | 1.3512 | 1165 | Tier 3 | PSPS | CONCORD | CONTRA COSTA | Diablo | Bay Area | 5788778 | E.5025639 | 118259181 | 35145001 | PSPS - Clayton 2215 – CB | 475.2 | 20592 | 0 | 0 |  | 2019-79149 | 11616 | 2.2 | 19530000 | N/A | 0 | 20592 | 475.2 | 21067.2 | 3.99 | 16758000
35145002 | PSPS - HOLD |  | HOLD |  |  |  | 0.68 | 0.68 | 2021 |  |  |  | 115275.8 | APPR | 42481101 | IGNACIO 1101 | IGNACIO 1101CB | 19 | 1.6722 | 2448 | 0.042331 | 0.0022279 | 2447 | 0.017042 | 2421 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788780 | E.5025640 | 118262844 | 35145002 | PSPS - Ignacio 1101 - CB | 0 | 3590.4 | 0 | 0 |  | 2019-78952 | 3585.12 | 0.679 | 2194800 | N/A | 0 | 3590.4 | 0 | 3590.4 | 0.68 | 2856000
35145003 | PSPS - HOLD |  | HOLD |  |  |  | 0.28 | 0.28 | 2021 |  |  |  | 92273.67 | PEND | 13801103 | MORAGA 1103 | MORAGA 1103CB | 82 | 1.3309 | 2631 | 0.082476 | 0.0010058 | 2698 | 0.017178 | 2231 | Tier 3 | PSPS | ORINDA | CONTRA COSTA | Diablo | Bay Area | 5788781 | E.5025641 | 118263229 | 35145003 | PSPS - Moraga 1103 - CB | 0 | 1161.6 | 0 | 0 |  | 2019-78960 | 1161.6 | 0.22 | 2050000 | N/A | 0 | 1161.6 | 0 | 1161.6 | 0.22 | 924000 |  |  |  | 2020-33628
35144941 | PSPS - HOLD |  | HOLD |  |  |  | 2.59 | 2.59 | 2021 |  |  |  | 180088.06 | ADER | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105CB | 86 | 7.4461 | 2633 | 0.086208 | 0.0010024 | 2727 | 0.020645 | 1376 | Tier 3 | PSPS | SANTA CRUZ | SANTA CRUZ | Central Coast | Central Coast | 5788792 | E.5025646 | 118261469 | 35144941 | PSPS - Paul Sweet 2105 - CB PH 1 | 17212.8 | 1056 | 0 | 0 |  | 2020-07355 | 16737.6 | 3.17 | 4786588 | N/A | 0 | 1056 | 17212.8 | 18268.8 | 3.46 | 14532000 |  |  |  | 2020-45854
35144943 | PSPS - HOLD |  | HOLD |  |  |  | 0.63 | 0.63 | 2021 |  |  |  | 95498.4 | ESTS | 83692105 | ROB ROY 2105 | ROB ROY 2105CB | 17 | 0.73407 | 2781 | 0.0058961 | 0.00034683 | 2817 | 0.0050096 | 2564 | Tier 3 | PSPS | APTOS | SANTA CRUZ | Central Coast | Central Coast | 5788791 | E.5025648 | 118261587 | 35144943 | PSPS - Rob Roy 2105 - CB | 0 | 2851.2 | 0 | 0 |  | 2020-03578 | 3326.4 | 0.63 | 1574100 | N/A | 0 | 2851.2 | 0 | 2851.2 | 0.54 | 2268000
35145004 | PSPS - HOLD |  | HOLD |  |  |  | 0.62 | 0.62 | 2021 |  |  |  | 86709.38 | PEND | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | 60 | 1.8254 | 3259 | 0.00030957 | 5.1594e-06 | 2856 | 0.00010409 | 1372 | Tier 3 | PSPS | LAFAYETTE | CONTRA COSTA | Diablo | Bay Area | 5788782 | E.5025642 | 118263746 | 35145004 | PSPS - Rossmoor 1106 – CB | 0 | 4171.2 | 0 | 0 |  | 2019-79022 | 2112 | 0.4 | 3720000 | N/A | 0 | 4171.2 | 0 | 4171.2 | 0.79 | 3318000 |  |  |  | 2020-31291
35072360 | In-Construction - HOLD |  | HOLD |  |  |  | 1.05 | 1.05 | 2021 |  |  |  | 718998.64 | CONS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.0086401 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5783906 | E.5015236.01 | 114754229 | 35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 5541 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 5305 | 5305 | 1.0047 | 1929090.9091 |  |  | 0 | 2019-64378 | 2020-45688 | 0 | 0 | 5541 | 5541 | 1.0494 | 1932059 | 2583069 | 348.6842
35144944 | PSPS - HOLD |  | HOLD |  |  |  | 0.26 | 0.26 | 2021 |  |  |  | 118187.81 | PEND | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 | 2144 | 0.036015 | 2845 | Tier 3 | PSPS | SOUTH SAN FRANCISO | SAN MATEO | Peninsula | Central Coast | 5530170 |  | 118261958 | 35144944 | PSPS – Sneath Lane 1107 – CB | 0 | 739.2 | 0 | 0 |  | 2019-78877 | 739.2 | 0.14 | 738936 | N/A | 0 | 739.2 | 0 | 739.2 | 0.14 | 588000 |  |  |  | 2020-18832
35145006 | PSPS - HOLD |  | HOLD |  |  |  | 0.27 | 0.27 | 2021 |  |  |  | 126808.89 | ESTS | 43201101 | STAFFORD 1101 | STAFFORD 1101902998 | 81 | 1.0766 | 3483 | 0.00018615 | 2.2981e-06 | 3428 | 4.6216e-05 | 2388 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788788 | E.5025644 | 118263874 | 35145006 | PSPS - Stafford 1101 - LR 1298 | 0 | 1425.6 | 0 | 0 |  | 2019-79042 | 1425.6 | 0.27 | 2500000 | N/A | 0 | 1425.6 | 0 | 1425.6 | 0.27 | 1134000 |  |  |  | 2020-51115
Note on B8: Redacted says: says this job is no longer required. Please cancel.

## MPP Workplan SH Cut
Order | Job Owner | Job Owner Name | Order Desc | Primary Status | Order User Status | Program | Category | Sub-Category | MAT | Project Reporting Year | Order In DOT
35219589 |  |  | CWSP - WILDWOOD 11011454 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35224321 |  |  | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226798 |  |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226799 |  |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226900 |  |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217272 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226627 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226628 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226629 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226630 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226631 |  |  | CWSP - KESWICK 1101 LR 1586 PH 1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35107688 |  |  | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35106042 |  |  | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35106265 |  |  | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109737 |  |  | CWSP-VOLTA 1102-LR 1648-PH2.2 | FICL | FICL SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109738 |  |  | CWSP-VOLTA 1102-LR 1648-PH2.3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110440 |  |  | CWSP-VOLTA 1102-LR 1648-PH2.5 | FICL | FICL srdy crdy redl | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110441 |  |  | CWSP-VOLTA 1102-LR 1648-PH2.6 | MAPP | MAPP SRDY CRDY REDL IDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110442 |  |  | CWSP-VOLTA 1102-LR 1648-PH3.2 | FICL | FICL SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110443 |  |  | CWSP-VOLTA 1102-LR 1648-PH3.3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110444 |  |  | CWSP-VOLTA 1102-LR 1648-PH3.4 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110446 |  |  | CWSP-VOLTA 1102-LR 1648-PH4.3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110447 |  |  | CWSP-VOLTA 1102-LR 1648-PH4.4 | FICL | FICL ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110448 |  |  | CWSP-VOLTA 1102-LR 1648-PH4.5 | MAPP | MAPP SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35117444 |  |  | CWSP - VOLTA 1102 LR 1648 PH 2.1 | FICL | FICL SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35058905 |  |  | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35106331 |  |  | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109739 |  |  | CWSP-VOLTA 1102-LR 1648-PH2.4 | DOCC | DOCC CONT SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35110445 |  |  | CWSP-VOLTA 1102-LR 1648-PH4.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35135864 |  |  | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35219291 |  |  | CWSP - VACA DIXON 1101126774 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2022 | TRUE
35219275 |  |  | CWSP - PUTAH CREEK 110246012 | PEND | PEND | System Hardening | MPP |  | 08W | 2021 | TRUE
35219281 |  |  | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35232650 |  |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35232651 |  |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35026643 |  |  | DIAMOND SPRINGS 1105 - LR 2102 | DCNL | DCNL ERDY HOLD | System Hardening | MPP |  | 08W | 2021 | TRUE
31098626 |  |  | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | FICL | FICL SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35223036 |  |  | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35115152 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | CONS | CONS | System Hardening | MPP |  | 08W | 2021 | TRUE
35115157 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115148 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | FICL | FICL SRDY CRDY REDL CDOC CDPR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115149 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | CLSD | CLSD SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35061206 |  |  | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35061212 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35061213 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115155 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115156 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | DOCC | DOCC ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115158 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | CLSD | CLSD SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115151 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35115153 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35115154 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35115147 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | FICL | FICL ERDY SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115150 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35117443 |  |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | CONS | CONS ERDY SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35142826 |  |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | CONS | CONS SRDY | System Hardening | MPP | 2020 Rsrv | 08W | 2021 | TRUE
35098621 |  |  | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35192290 |  |  | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | ADER | ADER | System Hardening | MPP |  | 08W | 2021 | TRUE
35192291 |  |  | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226845 |  |  | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35112425 |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP |  | 08W | 2020 | TRUE
35112426 |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 | PREC | PREC SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112427 |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | CLSD | CLSD SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112428 |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | CLSD | CLSD SRDY CRDY IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112429 |  |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | MAPP | MAPP SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109540 |  |  | CWSP-EL DORADO 2101-19752- PHASE 1.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35095166 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | CLSD | CLSD ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112433 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | MAPP | MAPP SRDY CRDY IDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112435 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | CLSD | CLSD SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112436 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | MAPP | MAPP SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112437 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | CLSD | CLSD SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109554 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109555 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | DOCC | DOCC CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109556 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109549 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109550 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109551 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109552 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109553 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | DOCC | DOCC CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109545 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | DOCC | DOCC CONT SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109547 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35109548 |  |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112431 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | CLSD | CLSD SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112432 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35112434 |  |  | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35062374 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35062375 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35062376 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226846 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35226847 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35226848 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35226849 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226850 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226851 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226852 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226853 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226854 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226856 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35231607 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35231608 |  |  | CNCL-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35231609 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35232280 |  |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
74028021 |  |  | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
74022384 |  |  | CWSP - FITCH MOUNTAIN 1113 LR 24918 | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35112076 |  |  | OCGC FULTON 1107-OH TO UG MARK W SPG | MAPP | MAPP SRDY REDL IDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35192292 |  |  | ECOP - FULTON 1107 - H02-LR604 PH1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35225594 |  |  | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35225595 |  |  | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35225597 |  |  | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35225598 |  |  | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35145524 |  |  | PSPS - RINCON 1101 1103 SYSTEM HARDENING | UNSC | UNSC ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35145525 |  |  | PSPS - RINCON 1102 1104 SYSTEM HARDENING | UNSC | UNSC SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35015704 |  |  | OH RECONDUCTR ROB ROY 2105 -S026CC117 | PEND | PEND | System Hardening | MPP |  | 08W | 2022 | TRUE
35085847 |  |  | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | PEND | PEND | System Hardening | MPP |  | 08W | 2022 | TRUE
35081748 |  |  | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | CLSD | CLSD REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35052731 |  |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | PEND | PEND CONT SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114100 |  |  | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114101 |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | FICL | FICL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35114102 |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114103 |  |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | CONS | CONS ERDY SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114104 |  |  | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | MAPP | MAPP SRDY CRDY REDL CDOC CDPR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35119401 |  |  | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | FICL | FICL ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35171354 |  |  | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | CLSD | CLSD ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35031662 |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | FICL | FICL SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35113105 |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | FICL | FICL SRDY CRDY IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35113108 |  |  | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35119969 |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | MAPP | MAPP SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35119970 |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | FICL | FICL SRDY CRDY IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35119965 |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | PEND | PEND | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35119966 |  |  | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | FICL | FICL ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35192280 |  |  | ECOP - CLAYTON 2212 - H01-LR2951 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35225593 |  |  | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | ADER | ADER ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35219093 |  |  | CWSP - TIDEWATER 210614072 PH 1.1 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35231543 |  |  | CWSP - TIDEWATER 210614072 PH 1.2 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35231544 |  |  | CWSP - TIDEWATER 210614072 PH 1.3 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35114431 |  |  | CWSP - MORAGA 1101 - LR108540 - PH5 | FICL | FICL ERDY CRDY IDOC IDCR MTRL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35053033 |  |  | CWSP - TASSAJARA 2112 - FUSE 18053 | MAPP | MAPP SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35103324 |  |  | CWSP - ROSSMOOR 1102 - OCB | CLSD | CLSD SRDY CRDY REDL MTRL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
31343500 |  |  | CWSP ORINDA 401 HIGH SPLICE COUNT | FICL | FICL SRDY CRDY REDL MTRL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35103065 |  |  | CWSP - MORAGA 1101 - LR 108540 PH 1 | FICL | FICL SRDY CRDY REDL IDOC IDCR MTRL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35103323 |  |  | CWSP - MORAGA 1101 - LR 108540 - PH 2 | DOCC | DOCC REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35103325 |  |  | CWSP - MORAGA 1102 & 1104 - OCB | CLSD | CLSD SRDY CRDY IDOC IDCR MTRL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35219096 |  |  | CWSP - KIRKER 2104442850 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227655 |  |  | CWSP - KIRKER 2104442850 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
74021963 |  |  | CWSP - OAKLAND K 1102 OCB ZONE | MAPP | MAPP SRDY CRDY IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
74022388 |  |  | OCGC CWSP: X-1104 OH RECOND SKYLINE | DOCC | DOCC SRDY REDL IDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
31248532 |  |  | CWSP HALF MOON BAY 1101 LS CO4063 | CLSD | CLSD SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35217274 |  |  | FRRB - PN DIVISION SAN MATEO COUNTY | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217275 |  |  | FRRB - PN DIVISION SANTA CRUZ COUNTY | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35145540 |  |  | PSPS - FROGTOWN 1702 - CB | PEND | PEND | System Hardening | MPP |  | 08W | 2021 | TRUE
35174085 |  |  | PSPS - FIA320 - LR @ 101269978 | UNSC | UNSC SRDY | System Hardening | MPP |  | 08W | 2020 | TRUE
35094513 |  |  | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | PEND | PEND | System Hardening | MPP |  | 08W | 2021 | TRUE
35115855 |  |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | DOCC | DOCC SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116515 |  |  | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | UNSC | UNSC SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35075103 |  |  | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 | DCNL | DCNL | System Hardening | MPP |  | 08W | 2021 | TRUE
35043291 |  |  | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 | CLSD | CLSD SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35114051 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | CONS | CONS SRDY CRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35114043 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | DOCC | DOCC SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35107689 |  |  | OCGC CWSP - PINE GROVE 1102 - LR1222 - | DCNL | DCNL SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35114048 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114049 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35114040 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | CONS | CONS SRDY HOLD | System Hardening | MPP | 220 Mile Plan | 08W | 2022 | TRUE
35114042 |  |  | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | DOCC | DOCC SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35114044 |  |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | MAPP | MAPP ERDY SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35113102 |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | DOCC | DOCC ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35113101 |  |  | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | DOCC | DOCC SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115053 |  |  | CWSP - MIWUK 1701_OCB - PH 1.5 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35219097 |  |  | CWSP - COARSEGOLD 2104CB PH 1.1 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35227260 |  |  | CWSP - COARSEGOLD 2104CB PH 1.2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35227261 |  |  | CWSP - COARSEGOLD 2104CB PH 1.3 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35227262 |  |  | CWSP - COARSEGOLD 2104CB PH 1.4 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35192053 |  |  | STRM-OAKHURST 1103-LR 5120 PH1 | CONS | CONS SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35227096 |  |  | STRM - OAKHURST 1103 - LR 5120 PH 2 | CONS | CONS SRDY CRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35227201 |  |  | STRM - OAKHURST 1103 - LR 5120 PH 3 | CONS | CONS SRDY CRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35052737 |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | PEND | PEND ERDY | System Hardening | MPP | 2021 Rsrv | 08W | 2022 | TRUE
35219266 |  |  | CWSP - MARIPOSA 2102CB PH 1 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35227263 |  |  | CWSP - MARIPOSA 2102CB PH 2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35217267 |  |  | TITLE: SH - MARIPOSA 2102 LR 241564 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35219268 |  |  | CWSP - MARIPOSA 210197142 PH 1 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226241 |  |  | CWSP - MARIPOSA 210197142 PH 2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226240 |  |  | CWSP - MARIPOSA 210197142 PH 3 | PEND | PEND | System Hardening | MPP |  | 08W | 2021 | TRUE
35056746 |  |  | CWSP - MIWUK 1701 OCB PHASE 2.1 | CONS | CONS ERDY SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35223037 |  |  | PSPS - OAKHURST 1101 - OAKHURST | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35116442 |  |  | CWSP-MIWUK 1702-LR 38218-PH 1.3 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116800 |  |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | DOCC | DOCC | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116391 |  |  | CWSP - MIWUK 1702 - OCB - PH 1.2 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35052821 |  |  | CWSP - MIWUK 1701 – OCB - PH 1.1 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35052825 |  |  | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35115054 |  |  | CWSP - MIWUK 1701 – OCB - PH 2.2 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35115050 |  |  | CWSP - MIWUK 1701_OCB - PH 1.2 | CONS | CONS ERDY SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116383 |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116384 |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116390 |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | DOCC | DOCC ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116801 |  |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | CONS | CONS SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35052820 |  |  | CWSP - MIWUK 1702 - OCB - PH 1.1 | FICL | FICL SRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35115055 |  |  | CWSP - MIWUK 1701 – OCB - PH 2.3 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116444 |  |  | CWSP-MIWUK 1702-LR 38218-PH 1.5 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35116802 |  |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | DOCC | DOCC SRDY CDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116804 |  |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | DOCC | DOCC SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116393 |  |  | CWSP - MIWUK 1702 - OCB - PH 1.3 | CLSD | CLSD SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116394 |  |  | CWSP - MIWUK 1702 - OCB - PH 1.4 | CLSD | CLSD SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35116395 |  |  | CWSP - MIWUK 1702 - OCB - PH 1.5 | CONS | CONS SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35137593 |  |  | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35137596 |  |  | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35094394 |  |  | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | MAPP | MAPP SRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35094397 |  |  | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | MAPP | MAPP SRDY CRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35094393 |  |  | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | FICL | FICL SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35217270 |  |  | CWSP - KONOCTI 1102 LR 965078 PH1 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35225589 |  |  | CWSP - KONOCTI 1102 LR 965078 PH2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35225591 |  |  | CWSP - KONOCTI 1102 LR 965078 PH3 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35174478 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35174479 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35174501 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35137590 |  |  | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35226857 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226858 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226859 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226861 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226862 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226863 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226864 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226865 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226866 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226870 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226871 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226872 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226873 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226878 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227001 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227002 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227003 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227004 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227007 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227010 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227013 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227015 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227018 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227021 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227025 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35192281 |  |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35192282 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217269 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217271 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35219098 |  |  | CWSP - MIDDLETOWN 1101118494 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35219272 |  |  | CWSP - MIDDLETOWN 1101481876 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35220895 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226621 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226622 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226623 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226624 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227027 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227028 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227029 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227030 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227031 |  |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226819 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227160 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227161 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227162 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227163 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227164 |  |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227165 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227167 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227168 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227860 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227861 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227862 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227863 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227864 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227866 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227867 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227868 |  |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35228186 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35228187 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35228188 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35229119 |  |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35228449 |  |  | RIO DELL STORM REBUILD | CONS | CONS | System Hardening | MPP |  | 08W | 2021 | TRUE
35219280 |  |  | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35226632 |  |  | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217273 |  |  | SH - UPPER LAKE 1101 CB | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35085534 |  |  | CWSP - SILVERADO 2104 - LR722 PH 1E | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35085535 |  |  | CWSP - SILVERADO 2104 - LR722 PH 1F | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
74022390 |  |  | CWSP - SILVERADO 2104- LR722-PH 1A | MAPP | MAPP SRDY REDL | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35085537 |  |  | CWSP - SILVERADO 2104 - LR722 PH 1H | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
31207090 |  |  | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | DOCC | DOCC SRDY CRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35191937 |  |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227032 |  |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35227033 |  |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35191319 |  |  | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35192284 |  |  | ECOP - SILVERADO 2104 - H05-LR726 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223024 |  |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223026 |  |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223027 |  |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35223028 |  |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35085538 |  |  | SILVERADO 2105 WIRE DOWN - PH 1 | FICL | FICL SRDY CRDY REDL IDOC IDCR | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35085539 |  |  | SILVERADO 2105 WIRE DOWN - PH 2 | DOCC | DOCC SRDY CRDY IDOC | System Hardening | MPP | 220 Mile Plan | 08W | 2020 | TRUE
35191318 |  |  | ECOP - SILVERADO 2102 - H02-LR58626 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35191383 |  |  | ECOP - SILVERADO 2102 - H01-LR58626 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35157845 |  |  | SILVERADO 2105 WIRE DOWN - PH 3 | CONS | CONS ERDY SRDY | System Hardening | MPP | 220 Mile Plan | 08W | 2021 | TRUE
35223615 |  |  | ECOP - LAS GALLINAS A 1105 PH 2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35103942 |  |  | *CANC* BR-09-03-W (E) CONNIE CIR PA*CANC | CLSD | CLSD CANC | System Hardening | MPP |  | 08W | 2021 | FALSE
35226700 |  |  | CWSP - WYANDOTTE 110932586 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223030 |  |  | PSPS - BANGOR 1101 CB - MICROGRID | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35217268 |  |  | CWSP - BUCKS CREEK 1101 CB PH 1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35224712 |  |  | CWSP - BUCKS CREEK 1101 CB PH 2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35224713 |  |  | CWSP - BUCKS CREEK 1101 CB PH 3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223343 |  |  | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35225821 |  |  | FRRB - BIG BEND - LAKE MADRONE ZONE 2 | ESTS | ESTS | System Hardening | MPP |  | 08W | 2021 | TRUE
35232298 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35232718 |  |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233306 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233307 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233308 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233309 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233310 |  |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233311 |  |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233312 |  |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233314 |  |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233315 |  |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233038 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233039 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233300 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233301 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233302 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233303 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233304 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35233305 |  |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35235705 |  |  | FRRB - WYANDOTTE 1103 - W2 PH2.6 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35235706 |  |  | FRRB - WYANDOTTE 1103 - W2 PH2.7 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35235707 |  |  | FRRB - WYANDOTTE 1103 - W2 PH2.8 | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35223344 |  |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | ESTS | ESTS SRDY CRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35223345 |  |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | UNSC | UNSC SRDY CRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35225822 |  |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | CONS | CONS SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35225823 |  |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | CONS | CONS SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35121739 |  |  | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 | CLSD | CLSD ERDY | System Hardening | MPP |  | 08W | 2020 | FALSE
35219273 |  |  | CWSP - VOLTA 110149742 | ADER | ADER ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35223039 |  |  | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | UNSE | UNSE | System Hardening | MPP |  | 08W | 2021 | TRUE
35219260 |  |  | CWSP - WYANDOTTE 110932586 PH 1.1 | ESTS | ESTS ERDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35225824 |  |  | FRRB - WYANDOTTE 1103 - HWY 162 | UNSC | UNSC SRDY | System Hardening | MPP |  | 08W | 2021 | TRUE
35105656 |  |  | *CANC*BR-04-02-W (E) CASTLE DR PARB | CLSD | CLSD CANC | System Hardening | MPP |  | 08W | 2021 | FALSE
35110374 |  |  | *CANC*BR-03-06-W (E) LUNAR LN PARB | CLSD | CLSD CANC | System Hardening | MPP | 2020 | 08W | 2021 | FALSE
35118701 |  |  | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA | CLSD | CLSD CANC | System Hardening | MPP | 2020 | 08W | 2020 | FALSE
35120949 |  |  | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | DOCC | DOCC | System Hardening | MPP |  | 08W | 2021 | TRUE

## De-energized Idle Lines
DEEN Idle Lines
Disposition Category | Item # | Item # (Cat 2) | Location (Webviewer GUID) | # of Idle Segments | Division | HFTD | Circuit ID | Circuit Name | Device | Length (GIS) | De-energization Completed (Y/N) | Within 600 ft of Transmission Line | T-Line within 600 ft | Addtl Information | DEEN Comments | DEEN Category | Idle Removal (I/R) | EC_PM Information
3 | Item 1 | IF Item 1 | {576003C3-CCA3-4D96-83BD-8B8CD5DD2EFF} {190CE1B4-F03D-46D6-BFE3-8D492AFED845} {3A1E720B-8AE3-4178-8FC3-EBE9E00136F8} | 3 | Sierra | Tier 2 | 153082106 | PLACERVILLE 2106 |  | 0.14205 | Y | N |  | De-energize idle line downstream of SAP Pole id 101387670. Idle line SAP Pole ids 103960502, 103960503, 103960504 | Flying bells installed. | Dispatch |  | EC 118283959 PM 35208054 UNSE Status as of 10/22/20, Priority E
3 | Item 2 | IF Item 10 | {3A2880C2-A76D-4DB0-B949-A8302A9311AC} | 1 | North Valley | Tier 3 | 102911103 | WYANDOTTE 1103 |  | 0.29042 | Y | N |  | De-energize idle line downstream of SAP Pole id 100376078. Idle line SAP Pole ids 100426294, 100376077, 100376076, 100426293, 100376075, 100425663. IF 106898732 / RW 110829043 11/3/15 notes to I/R equipment. | This line has burnt down. Jatko Rd Berry Creek - EC tags created - line to be removed. Tag 119782047 - SAP id 100376077 Tag 119782055 - SAP id 100426294 Tag 119782056 - SAP id 100426293 Tag 119782059 - SAP id 100425663 Tag 119782060 - SAP id 100376076 Tag 119846639 - SAP id 100376075 | Dispatch |  | EC 119782047 - SAP id 100376077 EC 119782055 - SAP id 100426294 EC 119782056 - SAP id 100426293 EC 119782059 - SAP id 100425663 EC 119782060 - SAP id 100376076 EC 119846639 - SAP id 100376075 PM 35199234 - 95A Cap Major Event ERDY Status 10/16/20; Priority A
3 | Item 3 | IF Item 11 | {61988FFE-CF66-4A62-A8D0-BC4A5821A7A8} | 1 | North Valley | Tier 2 | 102931101 | COTTONWOOD 1101 |  | 0.26683 | Y | N |  | De-energize idle line downstream of SAP Pole id 101511512. Idle line SAP Pole ids: 101511505, 101511507, 101511508, 101511509, 101511510, 101511511, 101511506 Idle Transformer CGC# - 118726035719 | AFW - De-energized on 11/12/20. | Dispatch |  | EC 110840126 PM 35204801 UNSE Status as of 10/2/20, Priority F
3 | Item 4 | IF Item 12 | {8E6E622B-0FEB-4E5D-A4E1-744345242A8B} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.13743 | Y | N |  | De-energize idle line downstream of SAP Pole id 101519958 . Idle line SAP Pole ids 101519961, 101519960, 101519959 Idle Transformer CGC# - 120233054783 Montgomery Creek Indian Reservation | AFW Cancelled as line was found de-energized on 11/9/20. | Dispatch |  | EC 110880096 PM 35204835 UNSE Status as of 10/2/20, Priority F
3 | Item 5 | IF Item 13 | {A26BABB5-9636-4D02-B7BB-459B3B7D79FC} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.10502 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480189. Idle line SAP Pole ids 101480187, 101480185 | Installed bells per job order.08/06/2019 07:48:04 PST [REDACTED] . IF investigation complete - Sent letter to customer. Letter was signed for, but received no response within the allotted time. Please I/R: 15 KVA tx (CGC 120116553055) and pole (101480187). | Dispatch |  | EC 117716950 PM35208005 UNSE Status as of 10/22/20, Priority F
4 | Item 6 | IF Item 14 | {3266FF9E-D915-4FF8-84E5-A0EA3A6BCF6E} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.096355 | Y | N |  | De-energize idle line downstream of SAP Pole id 103982823. Idle line SAP Pole ids 101459101, 101459102, 101459103 Idle Transformer CGC# - 119884349548 | This tap line is open at take off pole 1 Pole SE of sap id 101459101 600 ft s/o Swede Creek Rd 7 400 ft w/o Oak Run Rd. ; GC foreman completed PM 35090253 on 7/2020 to replace pole said he left the tap line open and de-energized. | Dispatch |  | Old EC 102544673 was cancelled 2015 IF tag flagged segment as TOS-F No new EC tag found
3 | Item 7 | IF Item 15 | {9A18086E-7D6A-4294-B058-42FE0460712D} | 1 | North Valley | Tier 3 | 103351101 | DESCHUTES 1101 |  | 0.045927 | Y | N |  | De-energize idle line downstream of SAP Pole id 101456353. Idle line SAP Pole ids 101456355, 101456354 Idle Transformer CGC# - 120019549840 | 5/28/20 Safety assessment by [REDACTED] , already de-energized. | Dispatch |  | EC 110850632 PM 35204816 UNSE Status as of 10/2/20, Priority F
2 | Item 8 | IF Item 16 | {74E868F9-4884-4A4E-9569-2763757B9DB3} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.18721 | Y | N |  | 6/09/20 Safety assessment - inspection performed by [REDACTED] - no idle facilities found at this location - work already completed. Original I/R for Pole ids 101483592, 101483616, 103313660, 101483618 | 6/09/20 Safety assessment - inspection performed by [REDACTED] - no idle facilities found at this location - work already completed. | Compliance | Removal appears to be completed | Removal appears to be completed
3 | Item 9 | IF Item 17 | {6543650F-F099-40A4-AD93-C7C045536CBB} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.12204 | Y | N |  | De-energize idle line downstream of SAP Pole id 103992280. Idle line SAP Pole Ids 101470353, 101470354, 101470356 Downstream from Active Transformer CGC# - 119542546073 | AFW - De-energized on 11/12/20; installed flying bells. 8/11/20 I/R Poles part of PM 35162302 in PEND status, Priority E - Schd Compl Yr 0. | Dispatch |  | PM 35162302 PEND status, Priority E
2 | Item 10 | IF Item 18 | {51437E84-9721-4711-90A5-07E7D44061E6} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.041878 | Y | N |  | 9/03/2020 13:54:37 PST [REDACTED] and crew completed 8/31/2020. Removed pole # 120565385. Final confirmed construction operation. Construction pkg uploaded into SAP.Orig job for Pole SAP id 101459572Idle Transformer CGC# - 119405347516 | Removal appears to be completed. | Completed per SAP Construction Notes | Removal appears to be completed | Removal appears to be completed
3 | Item 11 | IF Item 19 | {85938312-5226-433D-9824-63E05E8CD1CF} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.045971 | Y | N |  | De-energize idle line downstream of SAP Pole id 101470261. Idle line SAP Pole Id 101470262 Downstream from Active Transformer CGC# - 119341645963 | AFW - De-energized on 11/12/20. PM 35144989 (12/20/19) in ESTS status - Priority F - Schd Compl Yr 1+. | Dispatch |  | PM 35144989 ESTS status, Priority F
4 | Item 12 | IF Item 2 | {73D39B71-D07F-49C9-82CA-CA9AF54FAFA2} {191A669B-561D-431B-B682-B3AEA0508675} {E15C83DD-6D9E-499F-8D02-4838C43A2F2F} | 3 | Central Coast | Tier 2 | 182981102 | JOLON 1102 | Fuse 9189 | 0.086583 | Y | N |  | Idle line SAP Pole ids 103905961, 103905960, 103905959 SAP id associated with Fuse - 101727361 Idle Transformers CGC# - 413728523719, 413727423693 | Fuses are out. 8/23/18 Customer rep called and asked that idle facilities be kept as property is being sold. 6/16/20 Realquest search shows property still belongs to original owner and has not sold. | Dispatch |  | IF Notif 114779549 TOS-AG No recent EC tag found
3 | Item 13 | IF Item 20 | {BDE7B1C1-59B6-42C5-BF78-685CF4B8AB44} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.030087 | Y | N |  | 8/28/18 as part of discovery on another job. Conductor between 25' pole and 45' pole removed. Idle tap line runs to Open Point - Flying Bells installed - mostly likely de-energized unless there are jumpers. See Completed Const Pkg map in SAP: SAP Pole ids 101459086, 101459092 | TX already removed from 45' pole (101459086) on PM 31404117 in 2018 as part of discovery on another job. Conductor between 25' pole and 45' pole removed. Idle tap line runs to Open Point - Flying Bells installed. | Completed per SAP Construction Notes |  | EC 114961329 PM 35211254 UNSE Status as of 11/3/20, Priority F
4 | Item 14 | IF Item 21 | {3DBE3C44-FA24-4FD5-832D-79EDB56CE462} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.18779 | Y | N |  | De-energize idle line downstream of SAP Pole id 101468999. Idle line SAP Pole ids 101469008, 101469010, 101469011, 101469013 | This one is de-energized at the takeoff pole with flying bells cut open. | Dispatch |  | EC 110850642
3 | Item 15 | IF Item 22 | {D23C066B-D42F-47FA-8A00-07210FA157F7} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.015091 | Y | N |  | De-energize idle line downstream of SAP Pole id 101469872. Idle line SAP Pole id 101469874 | De-energized as jumpers are open at DE pole. | Dispatch |  | EC 110848230 PM 35204808 UNSE Status as of 10/2/20, Priority F
4 | Item 16 | IF Item 23 | {05403C66-A759-4E07-9234-FBAFBCDA9720} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.055565 | Y | N |  | De-energize idle line downstream of SAP Pole id 101490145. Idle line SAP Pole ids 101490155, 101490146 | The line is de-energized. The primary jumpers are open at the pole SAP 101490145 de-energized to EOL. | Dispatch |  | EC 116685701
3 | Item 17 | IF Item 24 | {27882F52-129D-4AC3-B879-9963436910AE} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.10463 | Y | N |  | De-energize idle line downstream of SAP Pole id 101490996. Idle line SAP Pole Ids 101490997, 101490998, 101490999 Idle Transformer CGC# - 118891040185 | AFW - De-energized on 11/12/20. SAP Note: 1/5/08 Idle 3 Pole Tap - Customer no longer wants. 11/13/15 IF investigation completed - no response from customer. | Dispatch |  | EC 110852551 PM 35204821 UNSE Status as of 10/2/20, Priority F
3 | Item 18 | IF Item 25 | {365E373B-0227-4801-8061-596AB4B9C91D} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 | Fuse 85883 | 0.071985 | Y | N |  | Idle line SAP Pole ids 101497622, 101497623 SAP id associated with Fuse 101497618 Idle Transformer CGC# - 119122240616 | Open jumpers; no fuses at this location. | Dispatch |  | EC 115104605 PM 35211698 UNSE Status as of 11/4/20, Priority F
4 | Item 19 | IF Item 26 | {0B461792-6532-4DDA-97BA-5C1D2D76D5FB} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.091225 | Y | N |  | De-energize idle line downstream of SAP Pole id 101481900. Idle line SAP Pole Ids 101481899, 101481898, 101481897 Idle Transformer CGC# - 118883039870 | The line is de-energized. The primary jumpers are open at SAP 101481900 de-energized to EOL. | Dispatch |  | EC 103690736
4 | Item 20 | IF Item 27 | {0F071E73-9573-4E7E-B2F1-99A97D9A1D9B} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.060437 | Y | N |  | Idle line SAP Pole Ids 101476890, 101476892 Idle Transformer CGC# - 120333247918 | The jumpers are open at pole SAP 101476889. 11/25/15 IF investigation - mapped as TOS-F - TX CGC# 120333247918; SAP Pole Ids 101476890 & 101476892. | Dispatch |  | EC 102537346
4 | Item 21 | IF Item 28 | {BFF6E942-70A4-428C-AE23-923E91045611} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.040196 | Y | N |  | De-energize idle line downstream of SAP Pole id 101456829. Idle line SAP Pole id 101456831 | Jumpers are opened at pole sap 101456829 and the line is de-energized. | Dispatch |  | EC 117686717
4 | Item 22 | IF Item 29 | {B24FCC37-3A01-4A67-826C-629F863DA5CF} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.041775 | Y | N |  | De-energize idle line downstream of SAP Pole id 101477601. Idle line SAP Pole id 101477605 | The line de-energized. There are flying bells cut in the line on the south side of pole SAP 101477601 and the jumpers are open de-energized to EOL. | Dispatch |  | No recent EC tag found
4 | Item 23a | IF Item 3 | {AB25D357-6F3A-4E2E-9BB9-D746B4D88732} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.091756 | Y | N |  | Idle line SAP Pole ids 102264187, 102264188 | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117229008 for Idle Pole decay
4 | Item 23b | IF Item 4 | {C7886B68-B543-4539-B820-65ADAC983066} {5D1840F7-F006-4876-A874-5B1A47F72DFC} {916A8C59-6A21-4B56-AC46-8058ED1E9464} {CD616D50-AE5C-4891-86C2-7ACC23C3A412} {DF2C9EAE-26F0-4C85-B937-505E4C9F7E11} {E8E5EFF6-D150-41D8-9E24-567B7B5F159C} {F49D2031-F91D-41D9-BF8B-125E76A1D0FA} {33AFA394-E183-4DEA-AB24-0DE592C87158} {F559D60B-172B-4518-A0D6-E78C6A3C2938} {98CE8E62-F3DC-490D-9CF6-4FE7423DAD37} {CC2FC4FA-6670-4D00-8D9F-F1D237632C07} | 11 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.77059 | Y | N |  | Idle line SAP Pole ids 102264184, 102264185, 102264186, 102264187, 102264188 102264198, 102264243, 102264189, 102264190, 102264192, 102264199, 102264200, 102264201, 102264202, 102264191, 102264193, 102264194, 102264195 102264204, 102264205, 102264208, 102264196, 102264197, 102264235, 102264240, 102264241, 102264244, 102264245, 102264246, 102264246 Idle Transformers: Transformer CGC# - 219262833684 Transformer CGC# - 219259833715 Transformer CGC# - 219248033734 Transformer CGC# - 219252533703 Transformer CGC# - 219251133757 Transformer CGC# - 219256033755 Transformer CGC# - 219246933781 Transformer CGC# - 219248533796 Transformer CGC# - 219252233738 Transformer CGC# - 219247133806 Transformer CGC# - 219241633879 May be associated with Berryessa Marina Resort Fire | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117229314 for one of the idle poles
4 | Item 23c | IF Item ID 18 | {AD4C8A53-0A10-4852-8820-04D602A82D61} {4771FF04-7FDA-43F4-99B1-B935934192D2} | 2 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.16418 | Y | N |  | Idle line SAP ids 102264235, 102264240 | Line was found already de-energized 11/5/20. | Dispatch |  | No recent EC tag found
4 | Item 24 | IF Item 30 | {1D3B2B78-5B6A-4888-ACD3-E557CC2C88D9} {44A1B8D9-AA8B-4F05-9A68-217A62A434C8} | 2 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 | Fuse 7647 | 0.3018 | Y | Y | Round Mtn-Table Mtn #2 (500kV) | Idle line SAP Pole ids 101475546, 101475551, 101475560, 101475548, 103368433, 101475555, 101475556, 101475558, 101475561 Idle Transformer CGC# - 120173449402 SAP id associated with Fuse 101475546 SAP Pole id 101475548 associated with TX on next pole beyond Fuse | The line is de-energized. Cutouts 7647 are open and the line is de-energized to the EOL. Last contact with customer in 2016 when she requested to keep line and would be submitting application. No activity since. | Dispatch |  | EC 110850619 PM 31225848 was cancelled
3 | Item 25 | IF Item 31 | {B6B7C1C7-E771-4378-B886-41EFA1B2C45B} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.21042 | Y | N |  | Per Safety Assessment on 5/18/20 conductor has been removed. | Per Safety Assessment on 5/18/20 conductor has been removed. | Compliance |  | EC 110850621 PM 35204814 UNSE Status, Priority F
3 | Item 26 | IF Item 32 | {60B4A640-4AC1-4CAB-BAF1-1B0DEA0C8422} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.145 | Y | N |  | De-energize idle line downstream of SAP Pole id 103322317. Idle line SAP Pole ids 101480717, 101480718 Idle Transformer CGC# - 120184745650 | The line is de-energized from open jumpers at pole SAP 103322317. PM 35174308 in ESTS status, Priority E (Schd Compl Yr 0) as of 7/15/20. | Dispatch |  | EC 118946100 PM 35174308 ESTS Status, Priority E
4 | Item 27 | IF Item 33 | {326EA39F-C7EB-43EE-B28F-CE3162FE7DFF} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.068764 | Y | N |  | De-energize idle line downstream of SAP Pole id 101475484. Idle line SAP Pole Ids 101475485, 101475486, 101475487 | The line is de-energized. The primary jumpers are opened at SAP 101475484 and the primary wire is removed/de-energized. | Dispatch |  | EC 119038871
4 | Item 28 | IF Item 34 | {3C6734CA-F14D-45C3-98BE-B40DF241CCD5} {150808D2-E042-4316-A50B-00BD5BA0B46F} | 2 | Los Padres | Tier 2 | 182611103 | PASO ROBLES 1103 |  | 0.75402 | Y | N |  | Heritage Ranch (Nacimiento Lake Dr - Parkway Circle) - CPS9 site visited 8/27/20 and verified. | Fuses Open - Cut and Clear. Field verified by [REDACTED] on 8/27/20. | SNBR Field Visit |  | EC 117193084 for De-energization
3 | Item 29 | IF Item 35 | {0F97BC63-445F-4B1D-A15B-DBD0C5DB1286} {1A828214-D994-4DAC-B956-6EB58A86576B} {02552A21-398F-4F72-A924-A9CCDD09B21A} {70BF414A-A697-49AA-A93C-5605A08B1E6C} {5D36EC8D-3E05-4275-AE0E-20A535DECFEA} | 5 | Yosemite | Tier 2 | 252192105 | BEAR VALLEY 2105 | Switch 4628 | 1.3627 | Y | N |  | Open SW 4628 to de-energize idle facilities. Buck Meadows (Bear Valley) | 4628 Is de-energized from Flying Bells located at Sap Id 103089929. OH Idle Facility Removal, Priority F, ESTS status, PM 35145458. | Email Dispatch |  | PM 35145458 ESTS Status, Priority F
4 | Item 30 | IF Item 5 | {E0D40BBB-77DC-4A82-ADE6-C4FF67FF00C4} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.61669 | Y | N |  | De-energize idle line downstream of SAP Pole id 102290530. Idle line SAP Pole ids 102290529, 102290528, 102290527 Idle Transformer CGC# - 219436824952 | Line was found already de-energized 11/5/20 by NB crew. | Dispatch |  | EC 107535759 PM 31137450 but cancelled in 2018
1 | Item 31 | IF Item 6 | {3866CF69-A5DE-4217-9413-AC604070AF44} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.14237 | Y | N |  | IF line burnt down - LNU Fire - IF has been removed. | Update 8/25/20: 18:06:39 Pst [REDACTED] Cancelled due to emergency A Tag created during LNU Fire Major Event. Changed A Tag from pole replacement to pole removal per guidance from [REDACTED] . Addtl Notification 119668805 / PM 31511571. [REDACTED] no longer in webviewer (IF removed) - LNU Fire area. | Already removed from GIS | Line burnt | EC 119668805
4 | Item 32 | IF Item 7 | {026CAA13-AB1D-42BE-B935-A3C206B0B2FC} | 1 | Humboldt | Tier 2 | 043141103 | MIDDLETOWN 1103 |  | 0.43374 | Y | N |  | De-energize idle line downstream of SAP Pole id 102204918. Idle line SAP Pole ids 102204927, 102204926, 102204925, 102204924, 102204923, 102204922, 102204921, 102204920, 102204919 Idle Transformer CGC# - 218513540110 | Flying Bells Installed. SAP notes updated 5/27/20 - Per IF desk, same owner who agreed to removal in 2015. IF 119041548 to I/R idle tap line. | Dispatch |  | EC 110554917; Per 5/27/20 SAP notes same owner who agreed to removal in 2015 still agrees with removal.
3 | Item 33 | IF Item 8 | {33514C1A-31A9-4D98-9615-A85688A35159} | 1 | Humboldt | Tier 2 | 043361103 | HIGHLANDS 1103 |  | 0.083584 | Y | N |  | De-energize idle line downstream of SAP Pole id 103605301. Idle tap line ends near TX Padmount T0755; used to supply temp power to UG; Idle line SAP Pole ids 103830981, 103830982 | Jumpers cut and clear. EC 112885271 - OH Idle Facility Removal, Priority F, ESTS status, PM 35150545 (2/27/20); Remove Idle tap line and poles supplied temp power to underground. | Dispatch |  | PM 35150545 ESTS status, Priority F
4 | Item 34 | IF Item 9 | {7424AE9E-B065-4FFC-846C-44CDCD8E9176} {88CDE43A-6151-446E-84F2-2FAD7377612B} {377053A1-0CEC-49D1-A2C4-BA2DE4732A46} | 3 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 |  | 3.5012 | Y | N |  | Big Meadows - Confirmation from [REDACTED] that line has de-energized. Provided circuit map. The 3-2 C 21kV circuit (idle) runs in parallel to 3-2AR 21kV circuit. | Per [REDACTED] in Compliance map was sent to us that shows this has been de-energized for over 10 years - provided circuit map. The 3-2 C 21kV circuit (idle) runs in parallel to 3-2AR 21kV circuit. | SNBR/Compliance |  | No recent EC tag found
4 | Item 35 | IF Item ID 1 | {9DAE7BF2-7E01-49F9-99A6-BC6DED2282B3} | 1 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 |  | 0.048292 | Y | N |  | Idle line SAP Pole Id 101074029 Idle Transformer CGC# - 321595938343 | Per [REDACTED] (Compliance) 10/6/20 - Jumpers cut in the clear at sap ID 101074038, which de-energizes tx on sap id 101074029. | Compliance |  | S9 119515842
3 | Item 36 | IF Item ID 10 | {3C541C61-0F12-41AE-9DA1-5F0111126A6C} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.16172 | Y | Y | Round Mtn-Table Mtn #2 (500kV) | De-energize idle line downstream of SAP Pole id 101479924. Idle line SAP Pole ids 101480009, 101480008, 103169204, 101479927 Idle Transformer CGC# - 120197653617 SAP Pole id 101480008 with TX at EOL. | The line is de-energized from jumpers open at flying bells at sap pole 101479924. | Dispatch |  | EC 117218967 PM 35207924, UNSE Status, Priority F EC 117218934 PM 35207923, UNSE Status, Priority E
4 | Item 37 | IF Item ID 11 | {22E39901-42E5-4DD4-84BC-31F5336FA4E4} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.063231 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480247. Idle line SAP Pole ids 101480263, 101480248 Idle Transformer CGC# - 120216453547 | The primary jumpers are open at Pole SAP 101480247 to EOL de-energized. | Dispatch |  | EC 117166992
1 | Item 38 | IF Item ID 12 | {80FE9D6A-3816-450D-A642-A4D00E895C35} | 1 | North Valley | Tier 3 | 102911105 | BIG BEND 1102 |  | 0.20374 | Y | N |  | De-energize idle line downstream of SAP Pole id 100412447. Idle line SAP Pole ids 100416739, 100412449, 100370365, 100412448, 100370364, 100370362 Idle Transformer CGC# - 221902774153 | Per M&C Supervisor this line has burnt down - email from [REDACTED] (NV). | Dispatch | Line burnt | Line burnt
1 | Item 39 | IF Item ID 13 | {935F9C88-99E9-43DF-B4D9-4113BFA72D88} | 1 | North Valley | Tier 3 | 102911103 | WYANDOTTE 1103 |  | 0.18668 | Y | N |  | De-energize idle line downstream of SAP Pole id 100376122. Idle line SAP Pole ids 100427950, 100376124, 100376123, 100427949 Idle Transformer CGC# - 221620370823 | Per M&C Supervisor this line has burnt down - email from [REDACTED] (NV). | Dispatch | Line burnt | Line burnt
4 | Item 40 | IF Item ID 14 | {9177CDDD-AF4F-4743-80DE-3BC72A213013} | 1 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 | Switch 69395 | 0.0054208 | Y | N |  | Open Switch 69395 to de-energize idle line. Idle line SAP Pole ids 103121316, 103121317 Idle Transformer CGC# - 122349932061 SAP id associated with Switch 69395 42645419 | Switch open and de-energized. | Dispatch |  | No recent EC tag found
4 | Item 41 | IF Item ID 15 | {5122961F-9649-43B0-A627-398DFBD83A84} | 1 | North Valley | Tier 2 | 102541101 | VOLTA 1101 |  | 0.26396 | Y | N |  | De-energize idle line downstream of SAP Pole id 101553210. Idle line SAP Pole ids 101553217, 101553216, 101553215, 101553214, 101553213, 101553212 | This tap line has open jumpers de-energized from the take off pole. | Dispatch |  | No recent EC tag found
3 | Item 42 | IF Item ID 16 | {D1F8EB39-F2AC-40AF-A5A3-B94EB780FD89} {5190FE93-D41F-46C9-86DF-94E2F3CCF972} | 2 | Humboldt | Tier 2 | 043361103 | HIGHLANDS 1103 | Fuse 5991 | 0.49348 | Y | Y | Lower Lake Homes Take (115kV) | Idle line SAP Pole ids 103928800, 102304945, 103928898, 103793587, 102304948, 102304949, 103928895, 102304951, 103793588, 102304953, 102304954, and 102304955 Idle Transformers CGC# - 218671044202, 218676044369 SAP Pole id 102304948 with TX middle of idle line | Line has been de-energized and grounded 10/14/2020. | Dispatch |  | EC 117748668, 117748783, 117748780, 117748785, 117748669, 117748784, 117748666 PM 35037391
4 | Item 43 | IF Item ID 17 | {98752110-4824-4447-8148-00F4014209BB} | 1 | Humboldt | Tier 3 | 043191101 | REDBUD 1101 |  | 0.04269 | Y | N |  | De-energize idle line downstream of SAP Pole id 102308426. Idle line SAP Pole id 103922760 Open point with subtype of flying bell on idle segment Downstream from Active Transformer CGC# - 218270551810 | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117255005
4 | Item 44 | IF Item ID 2 | {8D30ACCF-AD51-41A0-A5E3-13CD5F656295} {AB10C1D8-FD1E-498F-AE6C-82A79966AEBE} {42AC2F68-7A1A-43FA-B599-C086D910E907} | 3 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 | Fuse 14542 | 0.1874 | Y | N |  | Idle line SAP Pole Ids 103344115, 103344113, 101072782, 103344112, 103344114 Idle Transformer CGC# - 321679837422 | Per [REDACTED] (Compliance) 10/6/20 - TX and service pole idle, cut outs open. Fuse is open so de-energized. | Compliance |  | No recent EC tag found RW109910970 from 2015
4 | Item 45 | IF Item ID 20 | {3EC927F9-E22E-49D1-888E-E98A921987C9} | 1 | Los Padres | Tier 2 | 182721104 | SANTA YNEZ 1104 |  | 0.11163 | Y | N |  | Per [REDACTED] (Compliance Inspector) - jumper wires were removed - de-energized. Happy Canyon Road.Idle SAP Pole id 103760228Idle Transformer CGC# - 514094242144 | Per [REDACTED] (Compliance Inspector) - jumper wires were removed - de-energized. | SNBR/Compliance |  | No recent EC tag found RW 110885647 from 2015
4 | Item 46 | IF Item ID 21 | {E0CF85A3-864E-408F-9816-07BB365004DA} | 1 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 | Switch 82839 | 0.0084041 | Y | Y | Caribou-Westwood (60kV) | Idle line SAP Pole ids 103771036, 103771037 Idle Transformer CGC# - 122555930668 SAP id associated with Switch 44161565 SAP Pole id 103771037 with TX near Switch | Switch open on arrival. | Dispatch |  | No recent EC tag found
4 | Item 47 | IF Item ID 3 | {CE8FBF0F-74A2-43C9-9C88-8B882C35186F} {68F4C1EE-AC66-4C6B-8B76-99E6A7280CD3} | 2 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 | Fuse 2222 | 0.078543 | Y | N |  | Idle line SAP Pole Ids 101086508, 101086507 Idle Transformers CGC# - 321511036205, 321509036197 | Per [REDACTED] (Compliance) 10/6/20 - Fuse 2222 Open, line is idle. | Compliance |  | No recent EC tag found
4 | Item 48 | IF Item ID 4 | {CDCC7E6E-9631-44BD-815A-0B52E1A38964} | 1 | Yosemite | Tier 2 | 252192105 |  |  | 0.41252 | Y | N |  | Idle line SAP Pole Ids 101073810, 101073809, 101073808, 101073807, 101073806, 101073804, 101073803 Open point on idle line | Per [REDACTED] in Compliance, line confirmed de-energized on 11/4/2020. | SNBR/Compliance |  | No recent EC tag not found
3 | Item 49 | IF Item ID 6 | {12227378-9860-4FBF-9AC1-C57B6B5F5C2E} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.093922 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480797. Idle line SAP Pole ids 101480809, 101480798 | The line is de-energized from open jumpers at pole SAP 101480797. | Dispatch |  | EC 117102934 PM 35217667, UNSE Status, Priority F
4 | Item 50 | IF Item ID 7 | {5E8A014C-2508-4ED6-AB12-D2D5877FD6FD} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 | Fuse 11655 | 0.259 | Y | Y | Volta-Deschutes (60kV) | Idle line SAP Pole ids 103141283, 103141284, 103141285, 103141286, 103141287, 103141288 SAP id associated with Fuse 101483642 No TX on idle line | Cutouts 11655 found open upon arrival. Line is de-energized. | Dispatch |  | No recent EC tag found
4 | Item 51 | IF Item ID 8 | {56D5FC07-2D29-4BAE-AD9F-816045A7CE24} | 1 | North Valley | Tier 3 | 103351101 | DESCHUTES 1101 |  | 0.19099 | Y | N |  | De-energize idle line downstream of SAP Pole id 101479479. Idle line SAP Pole ids 101479480, 101479487, 101479482, 101479483, 101479486, 101479484, 101479485 | The primary jumpers are open at SAP 101479479 to EOL de-energized. Customer contact in 2016 suggested customer might have future use but no activity since. | Dispatch |  | EC 117311260
4 | Item 52 | IF Item ID 9 | {907B565F-2E2C-47F3-8BC4-8A9776D431A0} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.14634 | Y | N |  | De-energize idle line downstream of SAP Pole id 101519745. Idle line SAP Pole ids 101519746, 101519785, 101519784 Idle Transformer CGC# - 120261155249 | The primary jumpers are open at pole SAP 101519745 to EOL de-energized. Customer contact in 2015 suggested customer might have future use but no activity since. | Dispatch |  | EC 117214527
4 | Item 53 | Ph 3 QR Add 1 | {A16A506F-D4B6-4829-B0DE-6948576564DB} | 1 | North Bay | Tier 3 | 043292102 | PUEBLO 2102 |  | 0.045894 | Y | N |  | Idle line SAP Pole ids 103917226, 102269282 Near Transformer CGC# - 218817526480 | Line was found already de-energized 11/5/20 by NB dispatch. | Dispatch |  | EC 116873740
3 | Item 54 | Ph 3 QR Add 3 | {EE04AEAE-B8E5-4F1E-9ABA-71E9D60EB159} | 1 | Peninsula | Tier 2 | 024131102 | MENLO 1102 |  | 0.07226 | Y | N |  | Idle line SAP Pole ids 100271867, 100271868PM 35155226 for I/R in ESTS status as of 3/2/20; in ADE review 4/27/20; Job Owner [REDACTED] | Per SAP 6/13/19 notes from WSIP Inspection, already de-energized and flagged as idle in GIS. Set for removal - PM 35155226, ESTS status. | SNBR/Compliance |  | PM 35155226 PEND status, Priority E
|  |  | Total Idle Segments | 83 |  |  |  |  | Total Miles | 13.9894
2020-12-11
Disposition Category |  |  | De-energization Project Breakout: | # of Segments | Miles (Length)
1 |  |  | Line Burnt (Fire area) | 3 | 0.53279
2 |  |  | Appears removal have been completed | 2 | 0.22909
3 |  |  | PMs created pre-2021 | 9 | 1.6865
4 |  |  | Idle Removal for Planning | 69 | 11.541
|  |  | Total | 83 | 13.9894
Updated 12/14/2020
Disposition Category |  |  | De-energization Project Breakout: | # of Segments | Miles (Length)
1 |  |  | Line Burnt (Fire area) | 3 | 0.53279
2 |  |  | Appears removal have been completed | 2 | 0.22909
3 |  |  | PMs created pre-2021 | 27 | 4.0005
4 |  |  | Idle Removal for Planning | 51 | 9.227
|  |  | Total | 83 | 13.9894
Note on B2: Redacted says: Item # (New) for
Note on C2: Redacted says: Item # per Source extract tab
Note on M8: Redacted says: At the closest point from idle segment to Round Mtn-Cottonwood #2 is ~ 900 ft.
Note on M39: Redacted says: ~900 ft from Briceburg Jct-Marioposa Tap (70kV)
Note on M55: Redacted says: ~1300 ft from Round Mtn-Cottonwood #2 (230kV)

## Weekly Summary
Status Summary as of 12/21/20 |  |  |  | Process Summary
Order Status | # of jobs | Miles | Notes | Document | # of jobs | % of jobs | Miles | Notes |  | Responsible Group/Party | Total Expected Days | Total Actual Days | Date Start | Date End
UNSE | 64 | 363.28 |  | AA routed & appr | 62 | 62.63% | 178.86 |  | Planning Order Request Date | Grid Design | 5 business days
ESTS/ADER/APPR | 4 | 4.38 |  | Field Scoping | 24 | 24.24% | 36.19 |  | PM Number Requested Date | Grid Design | 1 business day
PEND | 4 | 6.38 |  | CMCS | 31 | 31.31% | 50.96 |  | Create Job Package | Planning DE | # of days/mile
UNSC | 1 | 1.47 |  | Business Case | 27 | 27.27% | 43.71 |  | AA Routed | Planning DE | Date job packaged created
[9 empty] | AA Approved | Various | 1 week
CONS | 26 | 40.66 | [6 empty] | Field Scoping (scheduling) | Various | 2 weeks
TOTAL | 99 | 416.17 | [6 empty] | Adjustments to Scope/back to planning | Planning DE/Estimating | 1-2 weeks
[9 empty] | ESTS will submit CMCS to planning for approval | Estimating | # of days/mile
[9 empty] | Scheduling | Project Manager | ?????
[9 empty] | Construction (25%, 50%, 75%) | Construction Team | # of weeks/mile