## Sheet1
Order | Job Owner Name | Project Reporting Year | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles
35116385 |  |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Scoped | PEND | 8005 | 0 | 8005 | 8005 | 1.5161 | 0 | 0 | 0 | 0 | 80005 | 15.1525
35062375 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Scoped | UNSE |  | 5860 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 5860 | 1.1098
35226849 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Scoped | UNSE |  | 9398 | 0 | 9398 | 1.7799 | 0 | 0 | 0 | 0 | 9398 | 1.7799
35225594 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Scoped | UNSE |  | 2481.6 | 0 | 2481.6 | 0.47 | 0 | 0 | 0 | 0 | 2482 | 0.47008
35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Scoped | UNSE |  | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8
35217270 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Scoped | ESTS |  | 0 | 2904 | 2904 | 0.55 | 0 | 0 | 0 | 0 | 2904 | 0.55
35225589 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Scoped | ESTS |  | 0 | 4699.2 | 4699.2 | 0.89 | 0 | 0 | 0 | 0 | 4699 | 0.88996
35225591 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Scoped | UNSE |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8
35217269 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Scoped | UNSE |  | 0 | 2270 | 2270 | 0.42992 | 0 | 0 | 0 | 0 | 2270 | 0.42992
35226819 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Scoped | UNSE |  | 0 | 10507 | 10507 | 1.99 | 0 | 0 | 0 | 0 | 10507 | 1.99
35227160 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Scoped | UNSE |  | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 6970 | 1.3201
35227161 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Scoped | UNSE |  | 0 | 3907 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3907 | 0.73996
35227162 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Scoped | UNSE |  | 1690 | 0 | 1690 | 0.32008 | 0 | 0 | 0 | 0 | 1690 | 0.32008
35227163 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Scoped | UNSE |  | 0 | 2429 | 2429 | 0.46004 | 0 | 0 | 0 | 0 | 2429 | 0.46004
35227164 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Scoped | UNSE |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 4752 | 0.9
35220895 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Scoped | UNSE |  | 10190 | 0 | 10190 | 1.9299 | 0 | 0 | 0 | 0 | 10190 | 1.9299
35228186 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Scoped | UNSE |  | 7867 | 0 | 7867 | 1.49 | 0 | 0 | 0 | 0 | 7867 | 1.49
35220896 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Scoped | UNSE |  | 1478 | 0 | 1478 | 0.27992 | 0 | 0 | 0 | 0 | 1478 | 0.27992
35227165 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Scoped | UNSE |  | 5333 | 0 | 5333 | 1.01 | 0 | 0 | 0 | 0 | 5333 | 1.01
35227167 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 9504 | 1.8
35227168 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Scoped | UNSE |  | 8290 | 0 | 8290 | 1.5701 | 0 | 0 | 0 | 0 | 8290 | 1.5701
35217271 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Scoped | UNSE |  | 8131 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 8131 | 1.54
35227864 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Scoped | UNSE |  | 3274 | 0 | 3274 | 0.62008 | 0 | 0 | 0 | 0 | 3274 | 0.62008
35226632 |  | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Scoped | UNSE |  | 792 | 0 | 792 | 0.15 | 0 | 0 | 0 | 0 | 792 | 0.15
35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Scoped | UNSE |  | 6177.6 | 0 | 6177.6 | 1.17 | 0 | 0 | 0 | 0 | 6178 | 1.1701
35223615 |  | 2021 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Scoped | UNSE |  | 8606.4 | 0 | 8606.4 | 1.63 | 0 | 0 | 0 | 0 | 8606 | 1.6299
35227030 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Scoped | UNSE |  | 7287 | 0 | 7287 | 1.3801 | 0 | 0 | 0 | 0 | 7287 | 1.3801
35227031 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Scoped | UNSE |  | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 8184 | 1.55
35192282 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Scoped | UNSE |  | 10771 | 0 | 10771 | 2.04 | 0 | 0 | 0 | 0 | 10771 | 2.04
35226621 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Scoped | UNSE |  | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 8184 | 1.55
35217273 |  | 2021 | SH - UPPER LAKE 1101 CB |  | Scoped | UNSE |  | 0 | 5702.4 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 5702.4 | 1.08
35174478 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Scoped | UNSE |  | 5491.2 | 0 | 5491.2 | 1.04 | 0 | 0 | 0 | 0 | 5491 | 1.04
35226857 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Scoped | UNSE |  | 4488 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0 | 4488 | 0.85
35226858 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Scoped | ESTS |  | 0 | 2006.4 | 2006.4 | 0.38 | 0 | 0 | 0 | 0 | 2006 | 0.37992
35226859 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Scoped | ESTS |  | 0 | 4646.4 | 4646.4 | 0.88 | 0 | 0 | 0 | 0 | 4646 | 0.87992
35226861 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Scoped | ESTS |  | 0 | 3484.8 | 3484.8 | 0.66 | 0 | 0 | 0 | 0 | 3485 | 0.66004
35226862 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Scoped | ESTS |  | 0 | 3062.4 | 3062.4 | 0.58 | 0 | 0 | 0 | 0 | 3062 | 0.57992
35174479 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Scoped | ESTS |  | 0 | 3761 | 3761 | 0.71231 | 0 | 0 | 0 | 0 | 3761 | 0.71231
35226878 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Scoped | UNSE |  | 3109 | 0 | 3109 | 0.58883 | 0 | 0 | 0 | 0 | 3109 | 0.58883
35227001 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Scoped | UNSE |  | 3809 | 0 | 3809 | 0.7214 | 0 | 0 | 0 | 0 | 3809 | 0.7214
35227002 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Scoped | UNSE |  | 2286 | 0 | 2286 | 0.43295 | 0 | 0 | 0 | 0 | 2286 | 0.43295
35227003 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Scoped | UNSE |  | 3067 | 0 | 3067 | 0.58087 | 0 | 0 | 0 | 0 | 3067 | 0.58087
35227004 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Scoped | UNSE |  | 1839 | 0 | 1839 | 0.3483 | 0 | 0 | 0 | 0 | 1839 | 0.3483
35236439 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | In Scoping | UNSE |  | 5914 | 0 | 5914 | 1.1201 | 0 | 0 | 0 | 0 | 5914 | 1.1201
35236660 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | In Scoping | UNSE |  | 2534 | 0 | 2534 | 0.47992 | 0 | 0 | 0 | 0 | 2534 | 0.47992
35226863 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Scoped | ESTS |  | 0 | 2786 | 2786 | 0.52765 | 0 | 0 | 0 | 0 | 2786 | 0.52765
35226864 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Scoped | ESTS |  | 0 | 1724 | 1724 | 0.32652 | 0 | 0 | 0 | 0 | 1724 | 0.32652
35226865 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Scoped | ESTS |  | 0 | 1243 | 1243 | 0.23542 | 0 | 0 | 0 | 0 | 1243 | 0.23542
35226866 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Scoped | ESTS |  | 0 | 2736 | 2736 | 0.51818 | 0 | 0 | 0 | 0 | 2736 | 0.51818
35226870 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Scoped | ESTS |  | 0 | 2215 | 2215 | 0.41951 | 0 | 0 | 0 | 0 | 2215 | 0.41951
35226871 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Scoped | UNSE |  | 6124 | 420 | 6544 | 1.2394 | 0 | 0 | 0 | 0 | 420 | 0.079545
35226872 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Scoped | UNSE |  | 2552 | 1168 | 3720 | 0.70455 | 0 | 0 | 0 | 0 | 1168 | 0.22121
35226873 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Scoped | UNSE |  | 5488 | 0 | 5488 | 1.0394 | 0 | 0 | 0 | 0 | 5488 | 1.0394
35174501 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Scoped | UNSE |  | 21597 | 0 | 21597 | 4.0903 | 0 | 0 | 0 | 0 | 21597 | 4.0903
35234758 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | Scoped | UNSE |  | 3073 | 0 | 3073 | 0.58201 | 0 | 0 | 0 | 0 | 3073 | 0.58201
35234862 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | Scoped | UNSE |  | 422 | 0 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 422 | 0.079924
35234865 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | Scoped | UNSE |  | 3419 | 0 | 3419 | 0.64754 | 0 | 0 | 0 | 0 | 3419 | 0.64754
35227007 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Scoped | UNSE |  | 15183 | 0 | 15183 | 2.8756 | 0 | 0 | 0 | 0 | 15183 | 2.8756
35227010 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Scoped | UNSE |  | 0 | 834 | 834 | 0.15795 | 0 | 0 | 0 | 0 | 834 | 0.15795
35227013 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 |  | Scoped | UNSE |  | 0 | 168 | 168 | 0.031818 | 0 | 0 | 0 | 0 | 168 | 0.031818
35227015 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Scoped | UNSE |  | 0 | 5106 | 5106 | 0.96705 | 0 | 0 | 0 | 0 | 5106 | 0.96705
35227018 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Scoped | UNSE |  | 0 | 6312 | 6312 | 1.1955 | 0 | 0 | 0 | 0 | 6312 | 1.1955
35227021 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Scoped | UNSE |  | 0 | 1144 | 1144 | 0.21667 | 0 | 0 | 0 | 0 | 1144 | 0.21667
35227025 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Scoped | UNSE |  | 2900 | 0 | 2900 | 0.54924 | 0 | 0 | 0 | 0 | 2900 | 0.54924
35234756 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | Scoped | UNSE |  | 14689 | 0 | 14689 | 2.782 | 0 | 0 | 0 | 0 | 14689 | 2.782
35224321 |  | 2021 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Scoped | ESTS |  | 0 | 12302.4 | 12302.4 | 2.33 | 0 | 0 | 0 | 0 | 12302 | 2.3299
35219589 |  | 2021 | CWSP - WILDWOOD 11011454 |  | Scoped | UNSE |  | 0 | 13622.4 | 13622.4 | 2.58 | 0 | 0 | 0 | 0 | 13622 | 2.5799
35226798 |  | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Scoped | UNSE |  | 0 | 8395.2 | 8395.2 | 1.59 | 0 | 0 | 0 | 0 | 8395 | 1.59
35226799 |  | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | Scoped | UNSE |  | 1003.2 | 0 | 1003.2 | 0.19 | 0 | 0 | 0 | 0 | 1003 | 0.18996
35113950 |  |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Scoped | PEND | 19602 | 0 | 18848 | 18848 | 3.5697 | 0 | 0 | 0 | 0 | 0 | 0
35113951 |  |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Scoped | UNSC | 13637 | 0 | 12799 | 12799 | 2.4241 | 0 | 0 | 0 | 0 | 0 | 0
35232650 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 |  | Scoped | UNSE |  | 9028 | 0 | 9028 | 1.7098 | 0 | 0 | 0 | 0 | 9028 | 1.7098
35219281 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Scoped | UNSE |  | 13200 | 0 | 13200 | 2.5 | 0 | 0 | 0 | 0 | 13200 | 2.5
35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Scoped | UNSE |  | 8106 | 0 | 8106 | 1.5352 | 0 | 0 | 0 | 0 | 8106 | 1.5352
35231608 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Scoped | ESTS |  | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0 | 0 | 0 | 1742 | 0.32992
35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Scoped | UNSE |  | 22892 | 0 | 22892 | 4.3356 | 0 | 0 | 0 | 0 | 22892 | 4.3356
35223036 |  | 2021 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Scoped | UNSE |  | 264 | 0 | 264 | 0.05 | 0 | 0 | 0 | 0 | 264 | 0.05
35219096 |  | 2021 | CWSP - KIRKER 2104442850 PH 1.1 |  | Scoped | UNSE |  | 8817.6 | 0 | 8817.6 | 1.67 | 0 | 0 | 0 | 0 | 8818 | 1.6701
35227655 |  | 2021 | CWSP - KIRKER 2104442850 PH 1.2 |  | Scoped | UNSE |  | 0 | 19905.6 | 19905.6 | 3.77 | 0 | 0 | 0 | 0 | 19906 | 3.7701
35219093 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Scoped | ESTS |  | 6019 | 0 | 6019 | 1.14 | 0 | 0 | 0 | 0 | 6019 | 1.14
35231543 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Scoped | UNSE |  | 6864 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 6864 | 1.3
35144944 |  |  | PSPS - SNEATH LANE 1107 - LR 48338 |  | Scoped | PEND | 739.2 | 1348 | 0 | 1348 | 0.2553 | 0 | 0 | 0 | 0 | 0 | 0
35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Scoped | UNSE |  | 2534.4 | 0 | 2534.4 | 0.48 | 0 | 0 | 0 | 0 | 2534 | 0.47992
35217268 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 1056 | 0.2
35224712 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Scoped | UNSE |  | 9134.4 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 0 | 9134 | 1.7299
35224713 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Scoped | UNSE |  | 9662.4 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 0 | 9662 | 1.8299
35056733 |  |  | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  |  | PEND | 11252.4 | 1930 | 9322 | 11252 | 2.1311 | 0 | 0 | 0 | 0 | 0 | 0
35109541 |  |  | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  |  | ESTS | 14086 | 1279 | 12807 | 14086 | 2.6678 | 0 | 0 | 0 | 0 | 0 | 0
35057010 |  |  | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  |  | APPR | 6914 | 3135 | 3779 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 0 | 0
35057018 |  |  | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  |  | PEND | 10624 | 10624 | 0 | 10624 | 2.0121 | 0 | 0 | 0 | 0 | 0 | 0
35217272 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Scoped | UNSE |  | 1584 | 0 | 1584 | 0.3 | 0 | 0 | 0 | 0 | 1584 | 0.3
35226628 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Scoped | UNSE |  | 4329.6 | 0 | 4329.6 | 0.82 | 0 | 0 | 0 | 0 | 4330 | 0.82008
35226629 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Scoped | UNSE |  | 23760 | 0 | 23760 | 4.5 | 0 | 0 | 0 | 0 | 23760 | 4.5
35226700 |  | 2021 | CWSP - WYANDOTTE 110932586 PH 1.2 |  | Scoped | UNSE |  | 3010 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 3010 | 0.57008
35223030 |  | 2021 | PSPS - BANGOR 1101 CB - MICROGRID |  | Scoped | UNSE |  | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0 | 0 | 0 | 3010 | 0.57008
35223039 |  | 2021 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Scoped | UNSE |  | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 4066 | 0.77008
Note on I1: [REDACTED]:This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on J1: [REDACTED]:This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.

## Sheet2
Row Labels | Sum of 2022 Forecast Feet | Sum of 2022 Forecast Miles
| 80005 | 15.1525
35116385
CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 80005 | 15.1525
| 21964 | 4.1598
35062375
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 5860 | 1.1098
35192292
ECOP - FULTON 1107 - H02-LR604 PH1.1 | 4224 | 0.8
35225594
ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 2482 | 0.47008
35226849
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 9398 | 1.7799
| 154123.4 | 29.19
35191319
ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 6178 | 1.1701
35192282
ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 10771 | 2.04
35217269
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 2270 | 0.42992
35217270
CWSP - KONOCTI 1102 LR 965078 PH1 | 2904 | 0.55
35217271
CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 8131 | 1.54
35217273
SH - UPPER LAKE 1101 CB | 5702.4 | 1.08
35220895
CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 10190 | 1.9299
35220896
CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 1478 | 0.27992
35223615
ECOP - LAS GALLINAS A 1105 PH 2 | 8606 | 1.6299
35225589
CWSP - KONOCTI 1102 LR 965078 PH2 | 4699 | 0.88996
35225591
CWSP - KONOCTI 1102 LR 965078 PH3 | 4224 | 0.8
35226621
ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 8184 | 1.55
35226632
CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 792 | 0.15
35226819
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | 10507 | 1.99
35227030
ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 7287 | 1.3801
35227031
ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 8184 | 1.55
35227160
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 6970 | 1.3201
35227161
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | 3907 | 0.73996
35227162
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 1690 | 0.32008
35227163
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | 2429 | 0.46004
35227164
CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | 4752 | 0.9
35227165
CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 5333 | 1.01
35227167
CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 9504 | 1.8
35227168
CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 8290 | 1.5701
35227864
CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 3274 | 0.62008
35228186
CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 7867 | 1.49
| 142124 | 26.9174
35174478
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 5491 | 1.04
35174479
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | 3761 | 0.71231
35174501
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 21597 | 4.0903
35226857
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 4488 | 0.85
35226858
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | 2006 | 0.37992
35226859
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | 4646 | 0.87992
35226861
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 3485 | 0.66004
35226862
ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 3062 | 0.57992
35226863
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 2786 | 0.52765
35226864
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 1724 | 0.32652
35226865
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 1243 | 0.23542
35226866
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 2736 | 0.51818
35226870
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 2215 | 0.41951
35226871
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | 420 | 0.079545
35226872
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 1168 | 0.22121
35226873
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 5488 | 1.0394
35226878
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 3109 | 0.58883
35227001
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 3809 | 0.7214
35227002
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 2286 | 0.43295
35227003
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 3067 | 0.58087
35227004
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 1839 | 0.3483
35227007
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 15183 | 2.8756
35227010
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | 834 | 0.15795
35227013
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | 168 | 0.031818
35227015
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | 5106 | 0.96705
35227018
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | 6312 | 1.1955
35227021
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 1144 | 0.21667
35227025
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 2900 | 0.54924
35234756
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | 14689 | 2.782
35234758
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | 3073 | 0.58201
35234862
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | 422 | 0.079924
35234865
ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | 3419 | 0.64754
35236439
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | 5914 | 1.1201
35236660
ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | 2534 | 0.47992
| 35322 | 6.6898
35219589
CWSP - WILDWOOD 11011454 | 13622 | 2.5799
35224321
CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | 12302 | 2.3299
35226798
CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 8395 | 1.59
35226799
CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 1003 | 0.18996
| 0 | 0
35113950
CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | 0 | 0
35113951
CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | 0 | 0
| 55232 | 10.4606
35062374
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 8106 | 1.5352
35062376
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 22892 | 4.3356
35219281
CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 13200 | 2.5
35223036
PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 264 | 0.05
35231608
CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 1742 | 0.32992
35232650
CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 9028 | 1.7098
| 41607 | 7.8801
35144944
PSPS - SNEATH LANE 1107 - LR 48338 | 0 | 0
35219093
CWSP - TIDEWATER 210614072 PH 1.1 | 6019 | 1.14
35219096
CWSP - KIRKER 2104442850 PH 1.1 | 8818 | 1.6701
35227655
CWSP - KIRKER 2104442850 PH 1.2 | 19906 | 3.7701
35231543
CWSP - TIDEWATER 210614072 PH 1.2 | 6864 | 1.3
| 2534 | 0.47992
35192291
ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 2534 | 0.47992
| 59612 | 11.2902
35056733
CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 0 | 0
35057010
CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 0 | 0
35057018
CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 0 | 0
35109541
CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 0 | 0
35217268
CWSP - BUCKS CREEK 1101 CB PH 1 | 1056 | 0.2
35217272
CWSP - KESWICK 1101 LR 1586 PH 1.1 | 1584 | 0.3
35223030
PSPS - BANGOR 1101 CB - MICROGRID | 3010 | 0.57008
35223039
PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 4066 | 0.77008
35224712
CWSP - BUCKS CREEK 1101 CB PH 2 | 9134 | 1.7299
35224713
CWSP - BUCKS CREEK 1101 CB PH 3 | 9662 | 1.8299
35226628
CWSP - KESWICK 1101 LR 1586 PH 1.3 | 4330 | 0.82008
35226629
CWSP - KESWICK 1101 LR 1586 PH 1.4 | 23760 | 4.5
35226700
CWSP - WYANDOTTE 110932586 PH 1.2 | 3010 | 0.57008
(blank)
(blank)
(blank)
Grand Total | 592523.4 | 112.2203