## 2021 Exec Status
| 2021 | [5 empty] | Circuit Name | Division | Miles
Status | Mileage | Projects |  |  |  |  | ALLEGHANY 1101 | Sierra | 1.74
0. PG&E Responsibility to Design | 31.8 | 1 |  |  |  |  | BANGOR 1101 | Sierra | 0.85
1. PM Not Created | 0 | 0 |  |  |  |  | BIG BASIN 1101 | Central Coast | 7.6233
2. PM Created (UNSE) | 85.134 | 39 |  |  |  |  | BIG BEND 1102 | North Valley | 33.8894
3. Design in Progress | 0 | 0 |  |  |  |  | BRUNSWICK 1103 | Sierra | 5.7485
4. Preliminary Scope Review | 0 | 0 |  |  |  |  | BRUNSWICK 1110 | Sierra | 0.055871
5. Return to Engineer | 0.95 | 1 |  |  |  |  | BUCKS CREEK 1101 | North Valley | 5.4104
6. AA Submitted/Field Desktop Meeting Scheduled | 0.41098 | 1 | Scoped Miles |  |  |  | CALISTOGA 1102 | North Bay | 0.18
7. AA Approved/Field Desktop Meeting Scheduled | 26.7936 | 20 | Overhead | Underground | Removal | Remote Grid | CAMP EVERS 2106 | Central Coast | 1.0392
8. Estimating Field Verification | 5.42 | 2 | 0 | 5.42 | 0 | 0 | CLAYTON 2212 | Diablo | 2.8186
9. Return to Planning | 57.46 | 31 | 48.49 | 6.37 | 0 | 2.6 | COARSEGOLD 2104 | Yosemite | 8.2815
10. Field Review Incorporated | 8.8013 | 7 | 0 | 2.1514 | 0 | 6.65 | COLUMBIA HILL 1101 | Sierra | 0
11. Grid Design completed review | 63.7907 | 41 | 34.2155 | 25.5771 | 0.44811 | 3.55 | CORNING 1102 | North Valley | 3.04
12. Scheduled for Approval meeting | 0 | 0 | 0 | 0 | 0 | 0 | CRESTA 1101 | North Valley | 0
13. Project Scope Approved | 168.7748 | 137 | 78.645 | 80.0653 | 6.7951 | 3.0494 | DESCHUTES 1104 | North Valley | 18.3011
14. In Estimating (ESTS) | 100.987 | 68 | 85.9565 | 23.6025 | 0.99792 | 0 | DIAMOND SPRINGS 1105 | Sierra | 1.6339
15. ADE Review (ADER) | 12.6946 | 5 | 12.6945 | 0 | 0 | 0 | DIAMOND SPRINGS 1107 | Sierra | 8.465
16. CMCS Approved (DS73) | 0 | 0 | 0 | 0 | 0 | 0 | DUNBAR 1101 | Sonoma | 2.4614
17. Estimate Approval (APPR) | 0 | 0 | 0 | 0 | 0 | 0 | DUNLAP 1102 | Fresno | 2.6
18. Pending Dependencies (PEND) | 20.6935 | 19 | 14.1833 | 5.9175 | 0.84356 | 0 | ELK CREEK 1101 | North Valley | 7.9
19. Construction Ready (UNSC) | 19.2591 | 7 | 10.517 | 11.5521 | 0 | 0 | FITCH MOUNTAIN 1113 | Sonoma | 6.0758
20. In-Construction (CONS) | 34.7642 | 31 | 49.9793 | 4.0335 | 0 | 0 | FROGTOWN 1701 | Stockton | 0.59
| 637.7339 | 410 | 334.6812 | 164.6893 | 9.0847 | 15.8494 | FROGTOWN 1702 | Stockton | 1.2739
[7 empty] | FULTON 1107 | Sonoma | 4.015
[7 empty] | HALF MOON BAY 1103 | Peninsula | 6.37
[7 empty] | HIGHLANDS 1102 | Humboldt | 18.42
[7 empty] | KESWICK 1101 | North Valley | 9.1078
[7 empty] | KIRKER 2104 | Diablo | 5.44
[7 empty] | KONOCTI 1102 | Humboldt | 3.1514
[7 empty] | LAS GALLINAS A 1105 | North Bay | 2.7962
[7 empty] | LOS GATOS 1106 | De Anza | 0.84905
[7 empty] | MARIPOSA 2101 | Yosemite | 5.5536
[7 empty] | MARIPOSA 2102 | Yosemite | 12.15
[7 empty] | MARTELL 1101 |  | 1.31
[7 empty] | MIDDLETOWN 1101 | Humboldt | 48.7783
[7 empty] | MIDDLETOWN 1102 | Humboldt | 6.8034
[7 empty] | MIDDLETOWN 1103 | Humboldt | 23.9445
[7 empty] | MIWUK 1701 | Yosemite | 16.4706
[7 empty] | MIWUK 1702 | Yosemite | 4.4664
[7 empty] | MOUNTAIN QUARRIES 2101 | Sierra | 6.3809
[7 empty] | NORTH DUBLIN 2101 | Mission | 0
[7 empty] | OAKHURST 1101 | Yosemite | 2.6721
[7 empty] | OAKHURST 1103 | Yosemite | -0.37496
[7 empty] | OLETA 1101 | Stockton | 2.92
[7 empty] | OREGON TRAIL 1103 | North Valley | 62.0978
[7 empty] | PINE GROVE 1102 | Stockton | 4.3156
[7 empty] | PLACERVILLE 1112 | Sierra | 0.38015
[7 empty] | PLACERVILLE 2106 | Sierra | 2.19
[7 empty] | POSO MOUNTAIN 2103 | Kern | 0
[7 empty] | POSO MOUNTAIN 2104 | Kern | 0
[7 empty] | POTTER VALLEY P H 1105 | Humboldt | 1.8343
[7 empty] | PUEBLO 2102 | North Bay | 3.3379
[7 empty] | PUTAH CREEK 1102 | Sacramento | 0.52
[7 empty] | RINCON 1103 | Sonoma | 1.5
[7 empty] | RINCON 1104 | Sonoma | 1.78
[7 empty] | RIO DELL 1102 | Humboldt | 0.08375
[7 empty] | ROB ROY 2105 | Central Coast | 1.86
[7 empty] | SHINGLE SPRINGS 2109 | Sierra | 30.1644
[7 empty] | SILVERADO 2102 | North Bay | 3.5445
[7 empty] | SILVERADO 2104 | North Bay | 6.1621
[7 empty] | SILVERADO 2105 | North Bay | 0
[7 empty] | STANISLAUS 1702 | Stockton | 1.9112
[7 empty] | TIDEWATER 2106 | Diablo | 3.64
[7 empty] | TULUCAY 1101 | North Bay | 0
[7 empty] | UPPER LAKE 1101 | North Coast | 1.1055
[7 empty] | VACA DIXON 1101 | Sacramento | 0.39811
[7 empty] | VACA DIXON 1105 | Sacramento | 31.33
[7 empty] | VACAVILLE 1104 | Sacramento | 14.58
[7 empty] | VARIOUS | Various | 31.8
[7 empty] | VOLTA 1101 | North Valley | 3.461
[7 empty] | WILDWOOD 1101 | North Valley | 8.09
[7 empty] | WYANDOTTE 1103 | North Valley | 73.4703
[7 empty] | WYANDOTTE 1109 | North Valley | 1.9093

## Project List
Order | KEEP | Exec. Status | LTIP Condition 1 | LTIP Condition 2 | Priority | Original OH Miles | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | 2018 KPMG CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notif. | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | EASOP Risk Reduced | EASOP NPV ($000) | EASOP RSE | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost
35212495 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.65 | 0 | 2020 |  |  | 7.65 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101233716 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.04 | 119985141 | 35212495 | FRRB - AUBERRY 1101 LR233716 | - | - | - | - | [9 empty] | 0 | 0
35212464 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.48 | 0 | 2020 |  |  | 0.48 | 0 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101886282 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793893 | E.5034566.01.07 | 119983588 | 35212464 | FRRB - CALISTOGA 1101 LR 886282 | - | - | - | - | [9 empty] | 0 | 0
35212487 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.82 | 0 | 2020 |  |  | 1.82 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011034 | 80 | 11.1511 | 1566 | 1.9751 | 0.024689 | 1434 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.06 | 119983959 | 35212487 | FRRB - KANAKA 1101 LR1034 | - | - | - | - | [9 empty] | 0 | 0
35212460 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 17.43 | 3 | 2020 |  |  | 14.43 | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 110114605 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.03 | 119983565 | 35212460 | FRRB - RINCON 1101 LR 14605 | - | - | - | - | [9 empty] | 0 | 0
35212466 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.94 | 0.68 | 2020 |  |  | 8.26 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 11088762 | 147 | 13.8344 | 64 | 57.5327 | 0.39138 | 108 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.02 | 119984990 | 35212466 | FRRB - VACAVILLE 1108 LR 8762 | - | - | - | - | [9 empty] | 0 | 0
35212490 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.44 | 0.72 | 2020 |  |  | 4.72 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 1101323094 | 208 | 36.1569 | 117 | 66.6373 | 0.32037 | 234 | #VALUE! |  |  | FRRB | IGO | Shasta | North Valley | Northern | 5793919 | E.5034573.01.02 | 119984003 | 35212490 | FRRB - GIRVAN 1101 LR323094 | - | - | - | - | [9 empty] | 0 | 0
35212465 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.34 | 0 | 2020 |  |  | 6.34 | 0 | UNSE | 63601108 | VACAVILLE 1108 | VACAVILLE 110838316 | 232 | 15.9209 | 122 | 73.4796 | 0.31672 | 99 | #VALUE! |  |  | FRRB | VACAVILLE | Solano | Sacramento | Northern | 5793894 | E.5034567.01.01 | 119933526 | 35212465 | FRRB - VACAVILLE 1108 LR 38316 | - | - | - | - | [9 empty] | 0 | 0
35212406 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110137384 | 71 | 9.3736 | 557 | 10.17 | 0.14324 | 391 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.06 | 119983061 | 35212406 | FRRB - MONTICELLO 1101 LR 37384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212408 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.58 | 0 | 2020 |  |  | 1.58 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 210234959 | 205 | 25.7758 | 579 | 27.9958 | 0.13657 | 473 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.08 | 119983069 | 35212408 | FRRB - SILVERADO 2102 LR 34959 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212489 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.16 | -2.24 | 2020 |  |  | 6.4 | 0 | UNSE | 103401101 | GIRVAN 1101 | GIRVAN 11011330 | 264 | 31.0696 | 624 | 33.0087 | 0.12503 | 651 | #VALUE! |  |  | FRRB | REDDING | Shasta | North Valley | Northern | 5793919 | E.5034573.01.01 | 119933733 | 35212489 | FRRB - GIRVAN 1101 LR1330 | - | - | - | - | [9 empty] | 0 | 0
35212411 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.17 | 0 | 2020 |  |  | 0.17 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104722 | 99 | 7.8964 | 690 | 11.1613 | 0.11274 | 1130 | #VALUE! |  |  | FRRB | DEER PARK | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.11 | 119983147 | 35212411 | FRRB - SILVERADO 2104 LR 722 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212404 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5 | 0 | 2020 |  |  | 5 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101630 | 93 | 18.7154 | 732 | 9.7794 | 0.10515 | 552 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.04 | 119982981 | 35212404 | FRRB - MONTICELLO 1101 LR 630 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35122401 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.31 | 0 | 2020 |  |  | 7.31 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101CB | 5 | 0.53443 | 775 | 0.49137 | 0.098274 | 904 | #VALUE! |  |  | FRRB | STRAWBERRY VALLEY | Yuba | North Valley | Northern | 5793892 | E.5034565.01.01 | 119933522 | 35122401 | FRRB - MONTICELLO 1101 CB | - | - | - | - |  |  |  | 0 |  | 2019-39360 |  |  |  | 0 | 0
35212402 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.42 | 0 | 2020 |  |  | 2.42 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101666 | 90 | 12.0959 | 815 | 8.2843 | 0.092048 | 588 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.02 | 119982885 | 35212402 | FRRB - MONTICELLO 1101 LR 666 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212491 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | 0 | 2020 |  |  | 0.96 | 0 | UNSE | 252531103 | SAN JOAQUIN #3 | SAN JOAQUIN #3 11035100 | 204 | 21.334 | 829 | 18.2004 | 0.089218 | 667 | #VALUE! |  |  | FRRB | NORTH FORK | Madera | Yosemite | Central Valley | 5793920 | E.5034574.01.01 | 119933734 | 35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 | - | - | - | - | [9 empty] | 0 | 0
35212479 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7 | 3.84 | 2020 |  |  | 3.16 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.01 | 119933732 | 35212479 | FRRB - BIG BEND 1102 CB | - | - | - | - | [9 empty] | 0 | 0
35212405 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.9 | 0 | 2020 |  |  | 11.9 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 110193384 | 101 | 16.1387 | 914 | 7.9369 | 0.078583 | 632 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.05 | 119982987 | 35212405 | FRRB - MONTICELLO 1101 LR 93384 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212494 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | 0 | 2020 |  |  | 1.38 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 110137536 | 60 | 5.3994 | 934 | 4.5309 | 0.075515 | 511 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.03 | 119984007 | 35212494 | FRRB - AUBERRY 1101 LR37536 | - | - | - | - | [9 empty] | 0 | 0
35212418 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 13.7 | 0 | 2020 |  |  | 13.7 | 0 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | #VALUE! |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.01 | 119933523 | 35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | - | - | - | - | [9 empty] | 0 | 0
35212481 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 11.52 | 0.87 | 2020 |  |  | 10.65 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.03 | 119983951 | 35212481 | FRRB - WYANDOTTE 1103 LR1508 | - | - | - | - | [9 empty] | 0 | 0
35212492 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.05 | 0 | 2020 |  |  | 3.05 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R2845 | 172 | 17.8248 | 1209 | 8.1154 | 0.047182 | 811 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.01 | 119933735 | 35212492 | FRRB - AUBERRY 1101 R2845 | - | - | - | - | [9 empty] | 0 | 0
35212403 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.58 | 0 | 2020 |  |  | 3.58 | 0 | UNSE | 43051101 | MONTICELLO 1101 | MONTICELLO 1101654 | 71 | 8.2164 | 1227 | 3.2338 | 0.045547 | 1126 | #VALUE! |  |  | FRRB | NAPA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.03 | 119982889 | 35212403 | FRRB - MONTICELLO 1101 LR 654 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212412 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.13 | -0.58 | 2020 |  |  | 4.71 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 210437632 | 304 | 26.5819 | 1235 | 13.5588 | 0.044601 | 1426 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.12 | 119983231 | 35212412 | FRRB - SILVERADO 2104 LR 37632 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212480 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 6.12 | 3.74 | 2020 |  |  | 2.38 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.02 | 119983950 | 35212480 | FRRB - BIG BEND 1102 LR1972 | - | - | - | - | [9 empty] | 0 | 0
35212463 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.5 | 0 | 2020 |  |  | 7.5 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103474 | 174 | 18.3351 | 1342 | 6.4055 | 0.036813 | 1399 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.06 | 119983582 | 35212463 | FRRB - RINCON 1103 LR 474 | - | - | - | - | [9 empty] | 0 | 0
35212413 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.38 | -2.25 | 2020 |  |  | 3.63 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.13 | 119983363 | 35212413 | FRRB - SILVERADO 2105 LR 658898 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212496 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.26 | -0.37 | 2020 |  |  | 2.63 | 0 | UNSE | 192411101 | LOW GAP 1101 | LOW GAP 1101CB | 23 | 2.1692 | 1385 | 0.78267 | 0.034029 | 1600 | #VALUE! |  |  | FRRB | ZENIA | Trinity | Humboldt | Northern | 5793922 | E.5034576.01.01 | 119933736 | 35212496 | FRRB - LOW GAP 1101 | - | - | - | - | [9 empty] | 0 | 0
35212471 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.83 | 0 | 2020 |  |  | 1.83 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 | 1508 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.04 | 119983629 | 35212471 | FRRB - POINT MORETTI 1101 LR5076 | - | - | - | - | [9 empty] | 0 | 0
35212473 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.21 | 0 | 2020 |  |  | 2.21 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110210254 | 11 | 2.1441 | 1421 | 0.35552 | 0.03232 | 1814 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.06 | 119983704 | 35212473 | FRRB - BIG BASIN 1102 LR10254 | - | - | - | - | [9 empty] | 0 | 0
35212416 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.252 | 0 | 2020 |  |  | 1.252 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.16 | 119983454 | 35212416 | FRRB - CALISTOGA 1102 LR 634 | - | - | - | - | [9 empty] | 0 | 0
35212486 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 9.46 | 5.02 | 2020 |  |  | 4.44 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.05 | 119983955 | 35212486 | FRRB - KANAKA 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212407 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.96 | -0.19 | 2020 |  |  | 1.15 | 0 | UNSE | 43432102 | SILVERADO 2102 | SILVERADO 2102636 | 81 | 5.465 | 1550 | 2.0483 | 0.025287 | 1827 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.07 | 119983066 | 35212407 | FRRB - SILVERADO 2102 LR 636 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212462 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.16 | -0.35 | 2020 |  |  | 12.51 | 0 | UNSE | 43321103 | RINCON 1103 | RINCON 1103198 | 62 | 6.4238 | 1618 | 1.3987 | 0.02256 | 1658 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.05 | 119983580 | 35212462 | FRRB - RINCON 1103 LR 198 | - | - | - | - | [9 empty] | 0 | 0
35212417 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.2 | 0.18 | 2020 |  |  | 4.02 | 0 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102769230 | 160 | 11.021 | 1624 | 3.574 | 0.022338 | 1749 | #VALUE! |  |  | FRRB | CALISTOGA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.17 | 119983463 | 35212417 | FRRB - CALISTOGA 1102 LR 769230 | - | - | - | - | [9 empty] | 0 | 0
35212410 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.41 | 0 | 2020 |  |  | 0.41 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104708 | 61 | 3.7544 | 1648 | 1.292 | 0.02118 | 1771 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.10 | 119983145 | 35212410 | FRRB - SILVERADO 2104 LR 708 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212419 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101416 | 28 | 2.6414 | 1684 | 0.54085 | 0.019316 | 1689 | #VALUE! |  |  | FRRB | KENWOOD | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.02 | 119983560 | 35212419 | FRRB - DUNBAR 1101 - LR 416 | - | - | - | - | [9 empty] | 0 | 0
35212488 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 4.74 | 0.34 | 2020 |  |  | 4.4 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 11011406 | 204 | 27.2731 | 1728 | 3.5397 | 0.017352 | 1755 | #VALUE! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5793918 | E.5034572.01.07 | 119984001 | 35212488 | FRRB - KANAKA 1101 LR1406 | - | - | - | - | [9 empty] | 0 | 0
35212478 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 7.99 | 0 | 2020 |  |  | 7.99 | 0 | UNSE | 83392110 | SWIFT 2110 | SWIFT 2110XR332 | 83 | 18.4582 | 1769 | 1.2892 | 0.015532 | 1452 | #VALUE! |  |  | FRRB | LIVERMORE | Santa Clara | San Jose | Central Coast | 5793897 | E.5034571.01.01 | 119933730 | 35212478 | FRRB - SWIFT 2110 XR332 | - | - | - | - | [9 empty] | 0 | 0
35212483 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 12.53 | 11 | 2020 |  |  | 1.53 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | #VALUE! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.04 | 119983953 | 35212483 | FRRB - WYANDOTTE 1103 LR1974 | - | - | - | - | [9 empty] | 0 | 0
35212414 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0.24 | 2020 |  |  | 0.98 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105131568 | 57 | 4.1385 | 1947 | 0.58604 | 0.010281 | 2060 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.14 | 119983432 | 35212414 | FRRB - SILVERADO 2105 LR 131568 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212409 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.97 | 0 | 2020 |  |  | 0.97 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104645 | 13 | 1.0111 | 2117 | 0.085285 | 0.0065604 | 2103 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.09 | 119983129 | 35212409 | FRRB - SILVERADO 2104 LR 645 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212415 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.31 | 0 | 2020 |  |  | 2.31 | 0 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | 70 | 9.5796 | 2174 | 0.39281 | 0.0056116 | 2203 | #VALUE! |  |  | FRRB | SAINT HELENA | Napa | North Bay | Bay Area | 5793892 | E.5034565.01.15 | 119983433 | 35212415 | FRRB - SILVERADO 2105 LR 167360 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35212467 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 1.22 | 0 | 2020 |  |  | 1.22 | 0 | UNSE | 182371111 | LAURELES 1111 | LAURELES 11112020 | 281 | 34.3538 | 2187 | 1.5107 | 0.005376 | 2260 | #VALUE! |  |  | FRRB | CARMEL VALLEY | Monterey | Central Coast | Central Coast | 5793895 | E.5034568.01.01 | 119933604 | 35212467 | FRRB - LAURELES 1111 LR 2020 | - | - | - | - | [9 empty] | 0 | 0
35212469 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 5.23 | 2.95 | 2020 |  |  | 2.28 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 63 | 6.5695 | 2199 | 0.32133 | 0.0051004 | 2205 | #VALUE! |  |  | FRRB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.02 | 119983626 | 35212469 | FRRB - POINT MORETTI 1101 LR12122 | - | - | - | - | [9 empty] | 0 | 0
35212493 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 8.92 | 3.6 | 2020 |  |  | 5.32 | 0 | UNSE | 254151101 | AUBERRY 1101 | AUBERRY 1101R324 | 119 | 10.7137 | 2209 | 0.5799 | 0.0048731 | 1904 | #VALUE! |  |  | FRRB | AUBERRY | Fresno | Fresno | Central Valley | 5793921 | E.5034575.01.02 | 119984006 | 35212493 | FRRB - AUBERRY 1101 R324 | - | - | - | - | [9 empty] | 0 | 0
35212470 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.77 | 0 | 2020 |  |  | 0.77 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110183716 | 22 | 2.503 | 2210 | 0.10689 | 0.0048588 | 2187 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.03 | 119983627 | 35212470 | FRRB - POINT MORETTI 1101 LR83716 | - | - | - | - | [9 empty] | 0 | 0
35212461 | FRRB - 2020 |  | PLAN |  | 2020999 |  |  | 0 | 2020 |  |  |  | 0 | UNSE | 43321101 | RINCON 1101 | RINCON 1101663641 | 13 | 0.72937 | 2309 | 0.043609 | 0.0033545 | 2307 | #VALUE! |  |  | FRRB | SANTA ROSA | Sonoma | Sonoma | Northern | 5793893 | E.5034566.01.04 | 119983567 | 35212461 | FRRB - RINCON 1101 LR 663641 | - | - | - | - | [9 empty] | 0 | 0
35212474 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.52 | 0 | 2020 |  |  | 0.52 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 70 | 5.982 | 2358 | 0.20629 | 0.002947 | 2611 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.07 | 119983709 | 35212474 | FRRB - BIG BASIN 1102 LR12758 | - | - | - | - | [9 empty] | 0 | 0
35212472 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.51 | 1.37 | 2020 |  |  | 1.14 | 0 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 11025066 | 121 | 13.7481 | 2359 | 0.35169 | 0.0029066 | 2514 | #VALUE! |  |  | FRRB | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.05 | 119983702 | 35212472 | FRRB - BIG BASIN 1102 LR5066 | - | - | - | - | [9 empty] | 0 | 0
35212475 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 3.09 | 0 | 2020 |  |  | 3.09 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 1101CB | 45 | 4.6531 | 2398 | 0.11632 | 0.0025849 | 2594 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.08 | 119983868 | 35212475 | FRRB - BIG BASIN 1101 CB | - | - | - | - | [9 empty] | 0 | 0
35212477 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.59 | 0 | 2020 |  |  | 0.59 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 110110720 | 44 | 4.71 | 2435 | 0.10045 | 0.002283 | 2730 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.10 | 119983869 | 35212477 | FRRB - BIG BASIN 1101 LR10720 | - | - | - | - | [9 empty] | 0 | 0
35212468 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 0.89 | 0 | 2020 |  |  | 0.89 | 0 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136516 | 53 | 4.1639 | 2542 | 0.08431 | 0.0015908 | 2704 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.01 | 119933606 | 35212468 | FRRB - POINT MORETTI 1101 LR36516 | - | - | - | - | [9 empty] | 0 | 0
35212476 | FRRB - 2020 |  | PLAN |  | 2020999 |  | 2.58 | 0 | 2020 |  |  | 2.58 | 0 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 11015000 | 23 | 1.9571 | 2579 | 0.031772 | 0.0013814 | 2834 | #VALUE! |  |  | FRRB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5793896 | E.5034569.01.09 | 119985051 | 35212476 | FRRB - BIG BASIN 1101 LR5000 | - | - | - | - | [9 empty] | 0 | 0
74022384 | In-Construction | 20 | MEET | No | 2021001 | 5.6 | 5.4458 | 2.0458 | 2020 | 0.96 | 2.44 | 3.4 | 7730061.7 | CONS | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 111324918 | 49 | 5.4965 | 481 | 7.7177 | 0.1575 | 799 | 4.7409 | 209 | Tier 3 | PRE | GEYSERVILLE | Sonoma | Sonoma | Northern | 5782860 | E.5015487.01 | 114753320 | 74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | 28754 | 0 | 0 | 0 |  | 2018-55406 | 29568 | 5.6 | 5959500 | N/A | 0 | 0 | 29040 | 29040 | 5.5 | 10560000 |  |  | 0 | 2019-34744 | 2019-02348 | 0 | 0 | 28754 | 28754 | 5.4458
35119965 | In-Construction | 18 | No | No | 2021002 | 0.87 | 0.84905 | 0.84905 | 2020 | 0 |  | 0 | 753735.73 | PEND | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.072413 | 841 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786602 | E.5014534.05 | 117721840 | 35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | 4483 | 0 | 0 | 0 |  | 2018-31656 | 8077 | 1.5297 | 903333 | 2018-53540 | 0 | 0 | 1584 | 1584 | 0.3 | 576000 |  |  | 0 | 2019-78779 | 2020-24016 | 4483 | 0 | 4483 | 4483 | 0.84905 | 1435425 | 1924210 | 320.193
35094397 | In-Construction | 20 | No | No | 2021003 | 0.87 | 1.0646 | 0.0045833 | 2020 | 0 |  | 1.06 | 1293821.27 | FICL | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.076193 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785167 | E.5015029.11 | 117131100 | 35094397 | CWSP-KONOCTI 1102-LR 532-PH10 | 5621 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 |  |  | 0 | 2019-62948 | 2020-36368 | 0 | 0 | 5621 | 5621 | 1.0646 | 1438986 | 1733017 | 256.0018
35061206 | In-Construction | 20 | No | No | 2021004 | 1.966 | 1.7652 | 0.93515 | 2020 | 0 |  | 0.83 | 2116692.05 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.076892 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783070 | E.5015569.01 | 115106231 | 35061206 | CWSP-BRUNSWICK 1103-LR50070-PH 1.1 | 9320 | 0 | 0 | 0 |  | 2018-85016 | 10380.48 | 1.966 | 2108720 | 2019-76345 | 0 | 0 | 9320 | 9320 | 1.7652 | 3389090.9091 |  |  | 0 | 2020-03978 | 2020-30766 | 0 | 0 | 9320 | 9320 | 1.7652 | 3459498 | 4711641 | 371.1908
35061212 | In-Construction | 20 | No | No | 2021005 | 9 | 1.7888 | 1.7888 | 2020 | 0 |  | 0 | 1563667.61 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.077924 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783071 | E.5015568.01 | 115106486 | 35061212 | CWSP-BRUNSWICK 1103-LR50070-PH 2.1 | 9445 | 0 | 0 | 0 |  | 2018-85027 | 47520 | 9 | 9533800 | 2019-76348 | 0 | 0 | 9445 | 9445 | 1.7888 | 3434545.4545 |  |  | 0 | 2020-06702 | 2020-46891 | 0 | 0 | 9445 | 9445 | 1.7888 | 3890031 | 4913095 | 411.8614 |  | 2020-04589
35115151 | In-Construction | 20 | No | No | 2021006 | 2.25 | 1.8964 | 0.5664 | 2020 | 0 |  | 1.33 | 1413101.03 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.08261 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785721 | E.5015568.02 | 117493857 | 35115151 | CWSP-BRUNSWICK 1103-LR50070-PH 2.2 | 10013 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 | 0 | 0 | 10013 | 10013 | 1.8964 | 3641090.9091 |  |  | 0 | 2020-23454 | 2020-46448 | 0 | 0 | 10013 | 10013 | 1.8964 | 4025667 | 5273989 | 402.044 |  | 2020-38642
35115152 | In-Construction - 2 | 20 | No | No | 2021007 |  | 1.57 | 1.57 | 2021 |  |  | 0 | 444607.71 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.068391 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785722 | E.5015568.03 | 117495855 | 35115152 | CWSP-BRUNSWICK 1103-LR50070-PH 2.3 | 8271 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 |  |  |  | 0 | 0 | 0 |  |  |  | 2020-55781 | 2020-58697 | 0 | 0 | 8271 | 8271 | 1.5665 | 2679486 | 3591121 | 323.9616
35117443 | In-Construction | 20 | No | No | 2021008 | 1.543 | 2.1581 | 0.88814 | 2021 | 1.27 |  | 1.27 | 2059072.23 | CONS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.094012 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5786518 | E.5015567.06 | 117634567 | 35117443 | CWSP-BRUNSWICK 1103-LR50070-PH 3.6 | 11395 | 0 | 0 | 0 |  | 2018-85051 | 8147.04 | 1.543 | 1630650 | 2019-76353 | 0 | 0 | 11395 | 11395 | 2.1581 | 4143636.3636 |  |  | 0 | 2020-32576 | 2020-42958 | 0 | 0 | 11395 | 11395 | 2.1581 | 4475708 | 5778810 | 392.7782
35116383 | In-Construction | 20 | No | No | 2021009 | 1.97 | 1.3862 | 1.3862 | 2020 | 0 |  | 0 | 1001640.21 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.036514 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785966 | E.5014733.02 | 117604600 | 35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | 7319 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 7080 | 7080 | 1.3409 | 2574545.4545 |  |  | 0 | 2019-60218 | 2020-25651 | 0 | 0 | 7319 | 7319 | 1.3862 | 2547023 | 3758449 | 348.0015
35116384 | In-Construction | 20 | No | No | 2021010 | 1.97 | 1.8371 | 1.6671 | 2020 | 0.17 |  | 0.17 | 136058.76 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.048393 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785967 | E.5014733.03 | 117604604 | 35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | 9700 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 9715 | 9715 | 1.84 | 3532727.2727 |  |  | 0 | 2020-00930 | 2020-48509 | 0 | 0 | 9700 | 9700 | 1.8371 | 3239382 | 4624169 | 333.9569
35116385 | In-Construction - 2 | 18 | No | No | 2021011 |  | 1.4 | 1.4 |  |  |  | 0 | 76246.05 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.036879 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785968 | E.5014733.04 | 117604609 | 35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 7392 | 0 | 0 | 0 |  | 2018-59382 |  |  |  | 2019-35887
35114048 | In-Construction | 20 | No | No | 2021012 | 15.9024 | 1.3909 | 1.3909 | 2020 | 0 |  | 0 | 989501.44 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.040923 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785997 | E.5014742.03 | 117499466 | 35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 | 7344 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7382 | 7382 | 1.3981 | 2684363.6364 |  |  | 0 | 2019-73207 | 2020-43723 | 0 | 0 | 7344 | 7344 | 1.3909 | 3133899 | 4178929 | 426.7292
35114051 | In-Construction - 2 | 20 | No | No | 2021013 |  | 1.44 | 1.44 | 2021 |  |  | 0 | 572688.79 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.042367 | 2 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786000 | E.5014742.06 | 117502234 | 35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 | 7698 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7628 | 7628 | 1.4447 | 2773818.1818 |  |  |  | 2019-72313 | 2020-47316 | 0 | 0 | 7698 | 7698 | 1.458 | 3949678 | 5342998 | 513.0785
35052821 | In-Construction | 20 | No | No | 2021014 | 2.304 | 2.0744 | 1.8344 | 2020 | 0 |  | 0.24 | 624839.65 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.044256 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5784646 | E.5014771.01 | 114593976 | 35052821 | CWSP-MIWUK 1701–OCB-PH 1.1 | 10953 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9750 | 9750 | 1.8466 | 3545454.5455 |  |  | 0 | 2019-52652 | 2020-46847 | 0 | 0 | 10953 | 10953 | 2.0744 | 3322975 | 4765282 | 303.3849
35115050 | In-Construction | 20 | No | No | 2021015 | 2.304 | 1.6121 | 1.3121 | 2020 | 0 |  | 0.3 | 938688.07 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.034393 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785972 | E.5014771.02 | 117495948 | 35115050 | CWSP-MIWUK 1701–OCB-PH 1.2 | 8512 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 8270 | 8270 | 1.5663 | 3007272.7273 |  |  | 0 | 2019-79491 | 2020-40482 | 0 | 0 | 8512 | 8512 | 1.6121 | 2809593 | 4091239 | 330.0744
35115053 | In-Construction | 20 | No | No | 2021016 | 2.304 | 1.7203 | 1.7203 | 2020 | 0 |  | 0 | 639830.82 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.036701 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785975 | E.5014771.05 | 117496041 | 35115053 | CWSP-MIWUK 1701–OCB-PH 1.5 | 9083 | 0 | 0 | 0 |  | 2018-75405 | 12165.12 | 2.304 | 2436520 | 2019-35897 | 0 | 0 | 9571 | 9571 | 1.8127 | 3480363.6364 |  |  | 0 | 2020-56266 | 2020-27365 | 0 | 0 | 9083 | 9083 | 1.7203 | 1670418 | 2296559 | 183.906
35056746 | In-Construction | 20 | No | No | 2021017 | 1.96 | 2.0335 | 2.0335 | 2020 | 0 |  | 0 | 379211.58 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.043384 | 2 | Tier 3 | PRE | MI WUK VLG | Tuolumne | Yosemite | Central Valley | 5782537 | E.5015427.01 | 114996821 | 35056746 | CWSP-MIWUK 1701-OCB-PH 2.1 | 10737 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 10615 | 10615 | 2.0104 | 3860000 |  |  | 0 | 2019-65579 | 2020-47773 | 0 | 0 | 10737 | 10737 | 2.0335 | 2950902 | 3642331 | 274.8349
35115054 | In-Construction | 20 | No | No | 2021018 | 1.96 | 1.4259 | 1.3959 | 2020 | 0.03 |  | 0.03 | 1030177.37 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.030421 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785986 | E.5015427.02 | 117490035 | 35115054 | CWSP-MIWUK 1701-OCB-PH 2.2 | 7529 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 7255 | 7255 | 1.3741 | 2638181.8182 |  |  | 0 | 2019-53298 | 2020-44293 | 0 | 0 | 7529 | 7529 | 1.4259 | 2482662 | 3789178 | 329.7466
35115055 | In-Construction | 20 | No | No | 2021019 | 1.96 | 2.1343 | 2.1343 | 2020 | 0 |  | 0 | 1056972.26 | CONS | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.045533 | 2 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785987 | E.5015427.03 | 117490481 | 35115055 | CWSP-MIWUK 1701-OCB-PH 2.3 | 11269 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 11088 | 11088 | 2.1 | 4032000 |  |  | 0 | 2019-68750 | 2020-34644 | 0 | 0 | 11269 | 11269 | 2.1343 | 2901359 | 3784068 | 257.4638
35116391 | In-Construction | 20 | No | No | 2021020 | 2.04 | 2.0902 | 0.060152 | 2020 | 1.38 | 0.65 | 2.03 | 1738295.65 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.044332 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785976 | E.5014773.02 | 117605551 | 35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | 11036 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 10840 | 10840 | 2.053 | 3941818.1818 |  |  | 0 | 2019-64313 | 2020-18345 | 0 | 0 | 11036 | 11036 | 2.0902 | 3920204 | 5835429 | 355.2196
35116395 | In-Construction | 20 | No | No | 2021021 | 2.04 | 1.7106 | 1.0206 | 2021 | 0.69 |  | 0.69 | 871873.06 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702CB | 110 | 9.055 | 2369 | 0.30977 | 0.0028161 | 2489 | 0.036282 | 25 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785979 | E.5014773.05 | 117605558 | 35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | 9032 | 0 | 0 | 0 |  | 2018-71642 | 10771.2 | 2.04 | 2205280 | 2019-35893 | 0 | 0 | 7500 | 7500 | 1.4205 | 2727272.7273 |  |  | 0 | 2019-57777 | 2020-44284 | 0 | 0 | 9032 | 9032 | 1.7106 | 2479935 | 3714853 | 274.5721
35116800 | In-Construction | 20 | No | No | 2021022 | 1.78 | 1.4252 | 0.41519 | 2020 | 0.74 | 0.27 | 1.01 | 1345941.39 | DOCC | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.025962 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785961 | E.5014730.02 | 117605265 | 35116800 | CWSP-MIWUK 1702-LR 6018-PH1.2 | 7525 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 6695 | 6695 | 1.268 | 2434545.4545 |  |  | 0 | 2020-45856 | 2020-18449 | 0 | 0 | 7525 | 7525 | 1.4252 | 2704457 | 4030625 | 359.3963
35114100 | In-Construction | 20 | No | No | 2021023 | 1.61 | 1.0392 | 1.0392 | 2020 | 0 |  | 0 | 414882.69 | CONS | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.016816 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5786131 | E.5015489.02 | 117545617 | 35114100 | CWSP-CAMP EVERS 2106-LR5020-PH2.2 | 5487 | 0 | 0 | 0 |  | 2018-64516 | 8500.8 | 1.61 | 1747200 | N/A | 0 | 0 | 5491.2 | 5491.2 | 1.04 | 1996800 |  |  | 0 | 2019-82353 | 2020-34359 | 0 | 0 | 5487 | 5487 | 1.0392 | 2119397 | 2502285 | 386.2579
35052825 | In-Construction | 20 | No | No | 2021024 | 1.95 | 1.1682 | 0.86818 | 2020 | 0 |  | 0.3 | 526634.81 | CONS | 163661702 | MIWUK 1702 | MIWUK 1702S2247 | 21 | 1.4879 | 2737 | 0.010338 | 0.00049228 | 2641 | 0.0050323 | 26 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785221 | E.5014722.01 | 114701195 | 35052825 | CWSP-MIWUK 1702-LR 8090-PH 1.1 | 6168 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 5785 | 5785 | 1.0956 | 2103636.3636 |  |  | 0 | 2019-54146 | 2020-43899 | 0 | 0 | 6168 | 6168 | 1.1682 | 2342292 | 3544410 | 379.749
35116442 | In-Construction | 20 | No | No | 2021025 | 1.85 | 2.29 | 0 | 2020 | 1.79 | 0.5 | 2.29 | 1885616.25 | DOCC | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.012794 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785982 | E.5014776.03 | 117605169 | 35116442 | CWSP-MIWUK 1702-LR38218-PH1.3 | 12386 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 11065 | 11065 | 2.0956 | 4023636.3636 |  |  | 0 | 2020-11921 | 2020-34785 | 0 | 0 | 12386 | 12386 | 2.3458 | 2994831 | 3849738 | 241.7916
35116444 | In-Construction | 20 | No | No | 2021026 | 1.85 | 2.1023 | 2.1023 | 2020 | 0 |  | 0 | 783780.73 | CONS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.011746 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785984 | E.5014776.05 | 117605182 | 35116444 | CWSP-MIWUK 1702-LR38218-PH1.5 | 11100 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 9600 | 9600 | 1.8182 | 3490909.0909 |  |  | 0 | 2019-57736 | 2020-27703 | 0 | 0 | 11100 | 11100 | 2.1023 | 2648178 | 3531134 | 238.5746
31361965 | In-Construction - 2 | 20 | No | MEET | 2021027 |  | 0.45 | 0.45 | 2021 |  |  | 0 | 299497.23 | CONS | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | 1845 | 0.068224 | 1151 | Tier 3 | WDDB | KENWOOD | Sonoma | Sonoma | Northern | 5530175 |  | 113751296 | 31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 | 0 | 2367 | 0 | 0 |  | 2018-69430 | 2300 | 0.43561 | 345000 | N/A |  |  |  | 0 | 0 | 0 |  |  | 0 | 2019-35371 | 2019-34365 | 0 | 0 | 2367 | 2367 | 0.4483 | 797947 | 1245293 | 337.1132
31334291 | In-Construction - 2 | 18 | No | No | 2021028 |  | 0.51 | 0.51 | 2021 |  |  | 0 | 359205.19 | PEND | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | 2061 | 0.01337 | 2292 | Tier 3 | WDDB | FORT BRAGG | Mendocino | Humboldt | Northern | 5530164 |  | 112994395 | 31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 2710 | 0 | 0 | 0 |  | 2018-10393 | 1920 | 0.36364 | 212000 | N/A | 0 | 0 | 2692.8 | 2692.8 | 0.51 | 979200 |  |  |  |  | 2019-31651 | 0 | 0 | 2710 | 2710 | 0.51326 | 688000 | 1115000 | 253.8745 |  | 2019-19275
35085847 | In-Construction - 2 | 18 | No | No | 2021029 |  | 0.86 | 0.86 | 2021 |  |  | 0 | 78220.3 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 7.6345e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5530169 | P.12006 | 113255606 | 35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 4555 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 | [5 empty] | 2020-66516 | 0 | 0 | 4555 | 4555 | 0.86269 | 2900525 | 5126422 | 636.7783
35015704 | In-Construction - 2 | 18 | No | No | 2021030 |  | 1 | 1 | 2021 |  |  | 0 | 59185.27 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 8.8773e-05 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5533644 |  | 113255603 | 35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 5300 | 0 | 0 | 0 |  | 2017-105215 | 5300 | 1.0038 | 502000 |  |  |  |  | 0 | 0
35052731 | DSDD | 19 | No | No | 2021031 | 2.43 | 1.4733 | 1.4733 | 2020 | 0 |  | 0 | 156546.34 | PEND | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.02488 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5782530 | E.5014542.01 | 114607365 | 35052731 | CWSP - BIG BASIN 1101 - LR10296 PH 1.1 | 7779 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 2020-46872 | 2020-54946 | 0 | 0 | 7779 | 7779 | 1.4733 | 3391041 | 4994628 | 435.9225
35113950 | DSDD | 19 | No | No | 2021032 |  | 3.57 | 3.57 |  |  |  | 0 | 128116.76 | PEND | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.060289 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5786124 | E.5014542.02 | 117560045 | 35113950 | CWSP - BIG BASIN 1101 - LR10296 PH 1.2 | 18849.6 | 0 | 0 | 0 |  | 2018-42216 |  |  |  | N/A
35113951 | DSDD | 19 | No | No | 2021033 |  | 2.58 | 2.58 |  |  |  | 0 | 126690.53 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.04357 | 354 | Tier 3 | CWSP | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5786125 | E.5014542.03 | 117560047 | 35113951 | CWSP - BIG BASIN 1101 - LR10296 PH 1.3 | 13622.4 | 0 | 0 | 0 |  | 2018-42216 |  |  |  | N/A
35145540 | PSPS - Scoped | 18 | MEET | MEET | 2021034 | 0.5 | 1.2739 | 1.2739 | 2020 | 0 |  | 0 | 232831.42 | PEND | 163451702 | FROGTOWN 1702 | FROGTOWN 1702CB | 47 | 1.4614 | 1316 | 1.844 | 0.039234 | 1692 | 1.602 | 3052 | Tier 3 | PSPS | Angels | Calaveras | Stockton | Central Valley | 5788779 | E.5025634 | 118259180 | 35145540 | PSPS – Frogtown 1702 – CB | 0 | 2272 | 4454 | 0 |  | 2019-80603 | 2640 | 0.5 | 3900000 | N/A | 4454 | 2272 | 0 | 6726 | 1.2739 | 2100000 |  |  | 0 | 2020-42690
35094513 | DSDD | 18 | No | No | 2021035 | 1.54 | 1.9112 | 1.9112 | 2020 | 0 |  | 0 | 196248.63 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.0098421 | 19 | Tier 3 | CWSP | ARNOLD | Calaveras | Stockton | Central Valley | 5785245 | E.5014540.01 | 114567769 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10091 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 10091 | 10091 | 1.9112 | 3669454.5455 |  |  | 0 | 2020-43006 | 2021-08435
35145525 | PSPS - Scoped | 18 | MEET | MEET | 2021036 | 1.78 | 1.78 | 1.78 | 2020 | 0 |  | 0 | 159118.2 | PEND | 43321104 | RINCON 1104 | RINCON 1104CB | 34 | 0.56024 | 3302 | 0.00014935 | 4.3928e-06 | 2944 | 0.00046978 | 1522 | Tier 2 | PSPS | Santa Rosa | Sonoma | Sonoma | Northern | 5788787 | E.5025638.01 | 118266592 | 35145525 | PSPS - Rincon 1102 and 1104 - CB | 0 | 9398.4 | 0 | 0 |  | 2019-82382 | 9398.4 | 1.78 | 17891818 | N/A | 0 | 9398.4 | 0 | 9398.4 | 1.78 | 7476000 |  |  | 0 | 2020-50683 | [10 empty] | 2020-28718
35145524 | PSPS - Scoped | 18 | MEET | MEET | 2021037 | 1.5 | 1.5 | 1.5 | 2020 | 0 |  | 0 | 187474.57 | PEND | 43321103 | RINCON 1103 | RINCON 1103CB | 41 | 2.4433 | 1755 | 0.67489 | 0.016461 | 2033 | 0.41019 | 628 | Tier 3 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5788786 | E.5025637 | 118266591 | 35145524 | PSPS - Rincon 1101 and 1103- CB | 0 | 7920 | 0 | 0 |  | 2019-82381 | 7920 | 1.5 | 14953636 | N/A | 0 | 7920 | 0 | 7920 | 1.5 | 6300000 |  |  | 0 | 2020-48279
35137590 | ECOP - Top 20% | 14 | MEET | No | 2021038 | 0.52992 | 0.53485 | 0.53485 | 2021 |  |  | 0 | 38375.53 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101CB | 146 | 4.731 | 86 | 52.8144 | 0.36174 | 335 | 3.7019 | 413 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5530164 |  | 118093216 | 35137590 | ECOP-MIDDLETOWN 1101-H02-CB | 2824 | 0 | 0 | 0 |  | 2019-73180 | 2798 | 0.52992 | 564800 | 2020-03-04 | 0 | 0 | 2824 | 2824 | 0.53485 | 1026909.0909 |  |  | 0
35137593 | ECOP - Top 20% | 14 | MEET | No | 2021039 | 1.3799 | 1.3775 | 1.3775 | 2021 |  |  | 0 | 45256.98 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.5169 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118125945 | 35137593 | ECOP-MIDDLETOWN 1101-H07-LR4646 | 7273 | 0 | 0 | 0 |  | 2019-73200 | 7286 | 1.3799 | 1454600 | 2020-03-04 | 0 | 0 | 7273 | 7273 | 1.3775 | 2644727.2727 |  |  | 0
35137596 | ECOP - Top 20% | 14 | MEET | No | 2021040 | 0.96989 | 0.97178 | 0.97178 | 2021 |  |  | 0 | 30594.16 | PEND | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 11014646 | 165 | 18.5633 | 328 | 32.9712 | 0.19983 | 415 | 1.0701 | 235 | Tier 3 | ECOP | COBB | Lake | Humboldt | Northern | 5530164 |  | 118127757 | 35137596 | ECOP-MIDDLETOWN 1101-H08-LR4646 | 5131 | 0 | 0 | 0 |  | 2019-73285 | 5121 | 0.96989 | 1026000 | 2020-03-04 | 0 | 0 | 5131 | 5131 | 0.97178 | 1865818.1818 |  |  | 0
35192284 | ECOP - Top 20% | 13 | MEET | MEET | 2021041 |  | 1.086 | 1.086 | 2021 |  |  | 0 | 17722.51 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.0802 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5792107 | E.5034416.01 | 119556691 | 35192284 | ECOP - SILVERADO 2104 - H05-LR726 PH 1 | 0 | 5734 | 0 | 0 |  | 2020-77337 | 5734 | 1.09 | 6664630 | 2021-00327 | 0 | 5734 | 0 | 5734 | 1.086 | 4505396 |  |  | 0
35223024 | ECOP - Top 20% | 13 | MEET | MEET | 2021042 |  | 1.2659 | 1.2659 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 2.4248 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.01 | 120245076 | 35223024 | ECOP - SILVERADO 2104 - H05-LR726 PH 2 | 0 | 6684 | 0 | 0 |  | 2020-77337 | 6684 | 1.27 | 0 | 2021-00327 | 0 | 6684 | 0 | 6684 | 1.2659 | 4738320 |  |  | 0
35223026 | ECOP - Top 20% | 13 | MEET | No | 2021043 |  | 1.0348 | 1.0348 | 2021 |  |  | 0 | 0 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.2414 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.02 | 120245190 | 35223026 | ECOP - SILVERADO 2104 - H05-LR726 PH 3 | 5464 | 0 | 0 | 0 |  | 2020-77337 | 5464 | 1.03 | 0 | 2021-00327 | 0 | 0 | 5464 | 5464 | 1.0348 | 3702224 |  |  | 0
35223027 | ECOP - Top 20% | 14 | MEET | No | 2021044 |  | 1.5674 | 1.5674 | 2021 |  |  | 0 | 30298.91 | ESTS | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.8803 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.03 | 120245192 | 35223027 | ECOP - SILVERADO 2104 - H05-LR726 PH 4 | 8276 | 0 | 0 | 0 |  | 2020-77337 | 8276 | 1.57 | 0 | 2021-00327 | 0 | 0 | 8276 | 8276 | 1.5674 | 1898194 |  |  | 0
35223028 | ECOP - Top 20% | 14 | MEET | No | 2021045 |  | 1.208 | 1.208 | 2021 |  |  | 0 | 3215.73 | ESTS | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | 1.4491 | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.04 | 120245193 | 35223028 | ECOP - SILVERADO 2104 - H05-LR726 PH 5 | 6378 | 0 | 0 | 0 |  | 2020-77337 | 6378 | 1.21 | 0 | 2021-00327 | 0 | 0 | 6378 | 6378 | 1.208 | 1330059 |  |  | 0
35238098 | ECOP - Top 20% | 14 | MEET | No | 2021046 |  | 0 | 0 |  |  |  | 0 | 0 | ESTS | 43432104 | SILVERADO 2104 | SILVERADO 2104726 | 263 | 30.3762 | 279 | 58.7725 | 0.22347 | 368 | #DIV/0! | 582 | Tier 3 | ECOP | POPE VALLEY | Napa | North Bay | Bay Area | 5794998 | E.5034767.01.05 | 120658775 | 35238098 | ECOP - SILVERADO 2104 - H05-LR726 PH 6 | 0 | 0 | 0 | 0 |  | 2020-77337 |  |  |  | 2021-00327
35225593 | ECOP - Top 20% | 14 | MEET | No | 2021047 |  | 1.1756 | 1.1756 | 2021 |  |  | 0 | 37298.34 | ESTS | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 1.2261 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5544143 | E.5034791.01 | 120424181 | 35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH 2 | 6207 | 0 | 0 | 0 | 2020-77593 | 2020-77594 | 0 | 0 | 0 | 2021-02769 | 0 | 0 | 6207 | 6207 | 1.1756 | 1283732 |  |  | 0
35192281 | ECOP - Top 20% | 13 | MEET | No | 2021048 |  | 0.30663 | 0.30663 | 2021 |  |  | 0 | 19200.33 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.3133 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792097 | E.5034406.01 | 119556250 | 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.1 | 1619 | 0 | 0 | 0 | 2020-78060 | 2020-78081 | 31363.2 | 5.94 | 8593932 | 2021-04756 | 0 | 0 | 1619 | 1619 | 0.30663 | 344842 | 14.37 | 51800 | 3604.7321
35227027 | ECOP - Top 20% | 13 | MEET | No | 2021049 |  | 0.97576 | 0.97576 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.997 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.26 | 120449717 | 35227027 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.2 | 5152 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5152 | 5152 | 0.97576 | 1065537 | 0 | 0 | 0
35227028 | ECOP - Top 20% | 13 | MEET | No | 2021050 |  | 0.61723 | 0.61723 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.63067 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.27 | 120449719 | 35227028 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.3 | 3259 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 3259 | 3259 | 0.61723 | 684026 | 0 | 0 | 0
35227029 | ECOP - Top 20% | 13 | MEET | No | 2021051 |  | 1.0886 | 1.0886 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.1123 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.28 | 120449800 | 35227029 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.4 | 5748 | 0 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 0 | 5748 | 5748 | 1.0886 | 1198801 | 0 | 0 | 0
35236437 | ECOP - Top 20% | 13 | MEET | MEET | 2021052 |  | 0.34 | 0.34 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.55472 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.35 | 120617837 | 35236437 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.7 | 0 | 1795.2 | 0 | 0 |  | 2020-78081 |  |  |  | 2021-04756
35236438 | ECOP - Top 20% | 13 | MEET | MEET | 2021053 |  | 0.48 | 0.48 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.78314 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.36 | 120617839 | 35236438 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.8 | 0 | 2534.4 | 0 | 0 |  | 2020-78081 |  |  |  | 2021-04756
35226622 | ECOP - Top 20% | 13 | MEET | No | 2021054 |  | 0.87841 | 0.87841 | 2021 |  |  | 0 | 148.9 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.89753 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.02 | 120445225 | 35226622 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.3 | 4638 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 4638 | 4638 | 0.87841 | 1129975 | 0 | 0 | 0
35226623 | ECOP - Top 20% | 13 | MEET | No | 2021055 |  | 1.2953 | 1.2953 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 1.3235 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.03 | 120445227 | 35226623 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.4 | 6839 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 6839 | 6839 | 1.2953 | 1454442 | 0 | 0 | 0
35226624 | ECOP - Top 20% | 13 | MEET | No | 2021056 |  | 0.70795 | 0.70795 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 0.72337 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.04 | 120445228 | 35226624 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.5 | 3738 | 0 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 0 | 3738 | 3738 | 0.70795 | 783093 | 0 | 0 | 0
35225595 | ECOP - Top 20% | 13 | MEET | No | 2021057 |  | 0.87803 | 0.87803 | 2021 |  |  | 0 | 1924.13 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.64201 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.02 | 120424186 | 35225595 | ECOP - FULTON 1107 - H02-LR604 Ph 1.3 | 4636 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4636 | 4636 | 0.87803 | 2648900 |  |  | 0
35225597 | ECOP - Top 20% | 14 | MEET | No | 2021058 |  | 0.77576 | 0.77576 | 2021 |  |  | 0 | 5731.66 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.56723 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.03 | 124024187 | 35225597 | ECOP - FULTON 1107 - H02-LR604 Ph 1.4 | 4096 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4096 | 4096 | 0.77576 | 1917600 |  |  | 0
35225598 | ECOP - Top 20% | 14 | MEET | No | 2021059 |  | 0.88144 | 0.88144 | 2021 |  |  | 0 | 2853.7 | ESTS | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.6445 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.04 | 120424188 | 35225598 | ECOP - FULTON 1107 - H02-LR604 Ph 1.5 | 4654 | 0 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 0 | 4654 | 4654 | 0.88144 | 1766100 |  |  | 0
35174479 | ECOP - Top 20% | 14 | MEET | No | 2021060 |  | 0.72159 | 0.72159 | 2021 |  |  | 0 | 13984.08 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.77515 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790119 | E.5033918.01 | 118913025 | 35174479 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.1 | 3810 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 48840 | 9.25 | 13481516 | 2021-04464 | 0 | 0 | 3810 | 3810 | 0.72159 | 20851272.7273 | 14.32 | 47200 | 3296.0894
35226863 | ECOP - Top 20% | 14 | MEET | No | 2021061 |  | 0.52765 | 0.52765 | 2021 |  |  | 0 | 445.09 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.56681 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.06 | 120449205 | 35226863 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.2 | 2786 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2786 | 2786 | 0.52765 | 0 |  |  | 0
35226864 | ECOP - Top 20% | 14 | MEET | No | 2021062 |  | 0.32652 | 0.32652 | 2021 |  |  | 0 | 445.09 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.35075 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.07 | 120449207 | 35226864 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.3 | 1724 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1724 | 1724 | 0.32652 | 0 |  |  | 0
35226865 | ECOP - Top 20% | 14 | MEET | No | 2021063 |  | 0.23542 | 0.23542 | 2021 |  |  | 0 | 445.09 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.25289 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.08 | 120449208 | 35226865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.4 | 1243 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 |  | 0 | 1243 | 1243 | 0.23542 | 0 |  |  | 0
35226866 | ECOP - Top 20% | 14 | MEET | No | 2021064 |  | 0.51818 | 0.51818 | 2021 |  |  | 0 | 334.22 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.55664 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.09 | 120449230 | 35226866 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.5 | 2736 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2736 | 2736 | 0.51818 | 0 |  |  | 0
35226870 | ECOP - Top 20% | 14 | MEET | No | 2021065 |  | 0.41951 | 0.41951 | 2021 |  |  | 0 | 223.35 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.45064 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.10 | 120449231 | 35226870 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.6 | 2215 | 0 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2215 | 2215 | 0.41951 | 0 |  |  | 0
35226871 | ECOP - Top 20% | 13 | MEET | MEET | 2021066 |  | 1.9117 | 1.9117 | 2021 |  |  | 0 | 454.17 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.2398 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.11 | 120449235 | 35226871 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.7 | 420 | 6124 | 3550 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 3205 | 6124 | 420 | 9749 | 1.8464 | 0 |  |  | 0
35226872 | ECOP - Top 20% | 13 | MEET | MEET | 2021067 |  | 1.4881 | 1.4881 | 2021 |  |  | 0 | 583.77 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.4242 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.12 | 120449236 | 35226872 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.8 | 1168 | 2552 | 4137 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 2328 | 2552 | 1168 | 6048 | 1.1455 | 0 |  |  | 0
35226873 | ECOP - Top 20% | 13 | MEET | No | 2021068 |  | 1.0394 | 1.0394 | 2021 |  |  | 0 | 360.99 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.7829 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.13 | 120449450 | 35226873 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.9 | 0 | 0 | 0 | 5488 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 4734 | 0 | 0 | 4734 | 0.89659 | 0 |  |  | 0
35226878 | ECOP - Top 20% | 13 | MEET | MEET | 2021069 |  | 0.58883 | 0.58883 | 2021 |  |  | 0 | 458.19 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.01 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.14 | 120449453 | 35226878 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.10 | 0 | 3109 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3034 | 3034 | 0.57462 | 0 |  |  | 0
35227001 | ECOP - Top 20% | 13 | MEET | MEET | 2021070 |  | 0.7214 | 0.7214 | 2021 |  |  | 0 | 347.32 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2374 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.15 | 120449454 | 35227001 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.11 | 0 | 3809 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3591 | 3591 | 0.68011 | 0 |  |  | 0
35227002 | ECOP - Top 20% | 13 | MEET | MEET | 2021071 |  | 0.43295 | 0.43295 | 2021 |  |  | 0 | 217.72 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.74264 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.16 | 120449455 | 35227002 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.12 | 0 | 2286 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 2286 | 2286 | 0.43295 | 0 |  |  | 0
35227003 | ECOP - Top 20% | 13 | MEET | MEET | 2021072 |  | 0.58087 | 0.58087 | 2021 |  |  | 0 | 358.93 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99636 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.17 | 120449456 | 35227003 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.13 | 0 | 3067 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 3067 | 3067 | 0.58087 | 0 |  |  | 0
35227004 | ECOP - Top 20% | 13 | MEET | MEET | 2021073 |  | 0.3483 | 0.3483 | 2021 |  |  | 0 | 229.33 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.59743 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.18 | 120449457 | 35227004 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.14 | 0 | 1839 | 0 | 0 | 2020-53217 | 2020-53670 | 0 | 0 | 0 | 2021-04464 | 0 | 0 | 1763 | 1763 | 0.3339 | 0 |  |  | 0
35236439 | ECOP - Top 20% | 13 | MEET | MEET | 2021074 |  | 1.12 | 1.12 |  |  |  | 0 | 74.45 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9211 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.37 | 120617881 | 35236439 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.15 | 0 | 5913.6 | 0 | 0 | 2020-53217 | 2020-53670 |  |  |  | 2021-04464
35236660 | ECOP - Top 20% | 13 | MEET | MEET | 2021075 |  | 0.48 | 0.48 |  |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.82334 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.38 | 120617882 | 35236660 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 2.16 | 0 | 2534.4 | 0 | 0 | 2020-53217 | 2020-53670 |  |  |  | 2021-04464
35191383 | ECOP - Top 20% | 14 | MEET | No | 2021076 |  | 1.3286 | 1.3286 | 2021 |  |  | 0 | 33562.65 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 0.79143 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541309 | E.5034359.01 | 119518528 | 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 7015 | 0 | 0 | 0 |  | 2020-78168 | 7022.4 | 1.33 | 1143750 | 2021-00326 | 0 | 0 | 7015 | 7015 | 1.3286 | 1175890 |  |  | 0
35191318 | ECOP - Top 20% | 14 | MEET | No | 2021077 |  | 2.2159 | 2.2159 | 2021 |  |  | 0 | 37707.22 | ESTS | 43432102 | SILVERADO 2102 | SILVERADO 210258626 | 125 | 15.2217 | 663 | 14.6249 | 0.117 | 627 | 1.32 | 250 | Tier 3 | ECOP | SAINT HELENA | Napa | North Bay | Bay Area | 5541303 | E.5034352.01 | 119518390 | 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 11700 | 0 | 0 | 0 | 2020-76797 | 2020-76801 | 11721.6 | 2.22 | 1685400 | 2021-00256 | 0 | 0 | 11700 | 11700 | 2.2159 | 2027400 |  |  | 0
35192290 | ECOP | 15 | No | No | 2021078 |  | 5.0004 | 5.0004 | 2021 |  |  | 0 | 177990.16 | ADER | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 3.5024 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792092 | E.5034401.01 | 119556075 | 35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 26402 | 0 | 0 | 0 |  | 2020-66261 | 26400 | 5 | 5575214 | 2021-04162 | 0 | 0 | 26402 | 26402 | 5.0004 | 5633062 | 3.49 | 12500 | 3581.6619
35226845 | ECOP | 14 | No | No | 2021079 |  | 2.3674 | 2.3674 | 2021 |  |  | 0 | 13840.38 | ESTS | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.6582 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5795298 | E.5034803.01.01 | 120448987 | 35226845 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 2 | 12500 | 0 | 0 | 0 |  | 2020-69602 |  |  |  | 2021-04462 | 0 | 0 | 12500 | 12500 | 2.3674 | 2880250 |  |  | 0
35231544 | Top 50 Miles | 14 | MEET | No | 2021080 | 1.2 | 1.2 | 1.2 | 2021 |  |  | 0 | 866.92 | ESTS | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 3.9785 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.03 | 120504131 | 35231544 | CWSP - TIDEWATER 210614072 PH 3 | 6336 | 0 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 0 | 6336 | 6336 | 1.2 |  |  |  | 0
35226627 | Top 50 Miles | 13 | MEET | No | 2021081 | 0.29 | 0.31231 | 0.31231 | 2021 |  |  | 0 | 217.67 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 1.2699 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.02 | 120445375 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 2 | 1649 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0
35226630 | Top 50 Miles | 13 | MEET | No | 2021082 | 1.44 | 1.4061 | 1.4061 | 2021 |  |  | 0 | 34.82 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.7171 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.05 | 120445421 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 5 | 7424 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0
35226631 | Top 50 Miles | 13 | MEET | No | 2021083 | 1.54 | 1.5326 | 1.5326 | 2021 |  |  | 0 | 597.58 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 6.2315 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.06 | 120445423 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 6 | 8092 | 0 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0
35217267 | Top 50 Miles | 14 | MEET | No | 2021084 | 0.71281 | 0.71 | 0.71 | 2021 |  |  | 0 | 62536.9 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102241564 | 14 | 0.71281 | 10 | 10.8148 | 0.77248 | 26 | 6.6788 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794209 | E.5034606.01.01 | 120047657 | 35217267 | CWSP - MARIPOSA 2102 LR 241564 | 3748.8 | 0 | 0 | 0 |  | 2020-83810 | 3748.8 | 0.71 | 804541 | 2021-02743 |  |  | 3748.8 | 3748.8 | 0.71 |  |  |  | 0
35227860 | Top 50 Miles | 13 | MEET | No | 2021085 |  | 0.19583 | 0.19583 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.66472 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.07 | 120462186 | 35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 1034 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 1034 | 1034 | 0.19583 | 223852 | 0 | 0 | 0
35227861 | Top 50 Miles | 13 | MEET | No | 2021086 |  | 1.5339 | 1.5339 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.2066 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.08 | 120462188 | 35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 8099 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 8099 | 8099 | 1.5339 | 1685035 | 0 | 0 | 0
35227862 | Top 50 Miles | 13 | MEET | No | 2021087 |  | 0.93466 | 0.93466 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.1725 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.09 | 120462232 | 35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 4935 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4935 | 4935 | 0.93466 | 1020657 | 0 | 0 | 0
35227863 | Top 50 Miles | 13 | MEET | No | 2021088 |  | 0.79129 | 0.79129 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.6859 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.10 | 120462233 | 35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 4178 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 4178 | 4178 | 0.79129 | 874094 | 0 | 0 | 0
35227866 | Top 50 Miles | 13 | MEET | No | 2021089 |  | 0.52386 | 0.52386 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.12 | 120462238 | 35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 2766 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2766 | 2766 | 0.52386 | 592064 | 0 | 0 | 0
35227867 | Top 50 Miles | 13 | MEET | No | 2021090 |  | 0.99527 | 0.99527 | 2021 |  |  | 0 | 302.05 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.3782 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.13 | 120462241 | 35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 5255 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 5255 | 5255 | 0.99527 | 1116839 | 0 | 0 | 0
35227868 | Top 50 Miles | 13 | MEET | No | 2021091 |  | 0.51686 | 0.51686 | 2021 |  |  | 0 | 288.15 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.7544 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.14 | 120462242 | 35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 2729 | 0 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 0 | 2729 | 2729 | 0.51686 | 584412 | 0 | 0 | 0
35228187 | Top 50 Miles | 13 | MEET | No | 2021092 |  | 0.62879 | 0.62879 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 2.1343 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.16 | 120475324 | 35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH 2.3 | 3320 | 0 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 0 | 3320 | 3320 | 0.62879 | 733000 | 0 | 0 | 0
35228188 | Top 50 Miles | 13 | MEET | MEET | 2021093 |  | 3.73 | 3.73 | 2021 |  |  | 0 | 223.35 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 20.4207 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.17 | 120475326 | 35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH 2.4 | 0 | 0 | 19694.4 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 19694 | 0 | 0 | 19694 | 3.7299 | 667600 | 0 | 0 | 0
35236661 | Top 50 Miles | 13 | MEET | No | 2021094 |  | 0.22 | 0.22 |  |  |  | 0 | 0 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 0.74675 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.18 | 120617883 | 35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH 2.5 | 1161.6 | 0 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 0 | 1162 | 1162 | 0.22008
35222045 | Top 50 Miles | 13 | MEET | No | 2021095 |  | 0.88864 | 0.88864 | 2021 |  |  | 0 | 6674.95 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 3.0163 |  |  | CWSP | MIDDLETOWN | Napa | Humboldt | Northern | 5794898 | E.5034741.01.01 | 120233319 | 35222045 | CWSP - MIDDLETOWN 1103 LR 830 PH4 | 4692 | 0 | 0 | 0 | N/A | 2020-87784 | 3907.2 | 0.74 | 808000 | 2021-03692 | 0 | 0 | 4692 | 4692 | 0.88864 | 970399 | 3.02 | 2500 | 827.8146
35226846 | Top 20% MAVF CPZ | 14 | MEET | No | 2021096 | 1.54 | 1.5714 | 1.5714 | 2021 |  |  | 0 | 2570.18 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.5154 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.01 | 120448989 | 35226846 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.2 | 8297 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 8131 | 8131 | 1.54 | 2395810.5729 |  |  | 0
35226847 | Top 20% MAVF CPZ | 14 | MEET | No | 2021097 | 1.9299 | 1.9839 | 1.9839 | 2021 |  |  | 0 | 2358.16 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.1757 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.02 | 120449140 | 35226847 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.3 | 10475 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 0 | 10190 | 10190 | 1.9299 | 3002497.8155 |  |  | 0
35231607 | Top 20% MAVF CPZ | 14 | MEET | No | 2021098 | 1.4799 | 1.646 | 1.646 | 2021 |  |  | 0 | 2555.9 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.6349 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.11 | 120504093 | 35231607 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.4 | 8691 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7814 | 7814 | 1.4799 | 2302406.0776 |  |  | 0
35231609 | Top 20% MAVF CPZ | 14 | MEET | No | 2021099 | 1.3299 | 1.3301 | 1.3301 | 2021 |  |  | 0 | 3304.03 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.1292 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.13 | 120504096 | 35231609 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.5 | 7023 | 0 | 0 | 0 | [5 empty] | 2021-04171 | 0 | 0 | 7022 | 7022 | 1.3299 | 2069042.1649 |  |  | 0
35226848 | Top 20% MAVF CPZ | 14 | MEET | No | 2021100 | 2.8701 | 2.4445 | 2.4445 | 2021 |  |  | 0 | 1635.56 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.913 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.03 | 120449141 | 35226848 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.2 | 12907 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 15154 | 15154 | 2.8701 | 4392047.6357 |  |  | 0
35226850 | Top 20% MAVF CPZ | 14 | MEET | No | 2021101 | 2.29 | 1.5451 | 1.5451 | 2021 |  |  | 0 | 3417.01 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.4733 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.05 | 120449143 | 35226850 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.4 | 8158 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 9187 | 9187 | 1.74 | 2662646.2735 |  |  | 0
35226851 | Top 20% MAVF CPZ | 14 | MEET | No | 2021102 | 2.19 | 1.8784 | 1.8784 | 2021 |  |  | 0 | 2130.25 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.0069 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.06 | 120449144 | 35226851 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.5 | 9918 | 0 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 0 | 11563 | 11563 | 2.19 | 3351276.6802 |  |  | 0
35232280 | Top 20% MAVF CPZ | 18 | MEET | No | 2021103 | 0.6 | 0.6 | 0.6 | 2021 |  |  | 0 | 4787.38 | PEND | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.96045 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.14 | 120527401 | 35232280 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.6 | 3168 | 0 | 0 | 0 | [5 empty] | 2021-04169 | 3168 | 0 | 0 | 3168 | 0.6 | 918173.8755 |  |  | 0
35226852 | Top 20% MAVF CPZ | 14 | MEET | No | 2021104 | 2.93 | 2.4932 | 2.4932 | 2021 |  |  | 0 | 18981.53 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 4.8429 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.07 | 120449145 | 35226852 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 3.2 | 13164 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 15470.4 | 15470.4 | 2.93 | 5502901.5208 |  |  | 0
35226853 | Top 20% MAVF CPZ | 14 | MEET | No | 2021105 | 2.92 | 2.8044 | 2.8044 | 2021 |  |  | 0 | 22484.33 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 5.4473 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.08 | 120449146 | 35226853 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 3.3 | 14807 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 264 | 15153.6 | 15417.6 | 2.92 | 5484120.2869 |  |  | 0
35226854 | Top 20% MAVF CPZ | 14 | MEET | No | 2021106 | 1.03 | 1.0299 | 1.0299 | 2021 |  |  | 0 | 40169.15 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 2.0006 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.09 | 120449147 | 35226854 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 3.4 | 5438 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 5438.4 | 0 | 0 | 5438.4 | 1.03 | 1934467.0875 |  |  | 0
35226856 | Top 20% MAVF CPZ | 14 | MEET | No | 2021107 | 4.53 | 1.9436 | 1.9436 | 2021 |  |  | 0 | 6970.47 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 3.7753 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.10 | 120449149 | 35226856 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 3.5 | 10262 | 0 | 0 | 0 |  | 2018-89227 |  |  |  | 2021-05102 | 0 | 0 | 23918.4 | 23918.4 | 4.53 | 8507898.9383 |  |  | 0
35026643 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2021108 | 1.63 | 1.6339 | 1.6339 | 2021 |  |  | 0 | 58947.75 | UNSE | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 11052102 | 417 | 37.4816 | 666 | 48.4576 | 0.11621 | 755 | 1.5795 | 957 | Tier 2 | WDDB | DIAMOND SPRINGS | El Dorado | Sierra | Northern | 5530173 |  | 114258488 | 35026643 | RECONDUCTOR DIAMOND SPRINGS 1105 | 5727 | 0 | 2900 | 0 | n/a | 2018-38234 | 7400 | 1.4015 | 2100000 | 2021-03592 |  |  |  | 0 | 0 |  | 1.58 | 2900 | 1835.443
35075103 | Top 20% MAVF CPZ | 18 | MEET | No | 2021109 |  | 0.59 | 0.59 | 2021 |  |  | 0 | 102763.37 | PEND | 163451701 | FROGTOWN 1701 | FROGTOWN 17011623 | 152 | 15.2605 | 721 | 16.3546 | 0.1076 | 564 | 0.39202 | 1409 | Tier 3 | WDDB | MURPHYS | Calaveras | Stockton | Central Valley | 5530176 |  | 116475141 | 35075103 | FROGTOWN 1701 - 3115FT RECOND HFTD TIER2 | 3115.2 | 0 | 0 | 0 |  | 2019-20625 2021-08733 | 3115 | 0.58996 | 623000 | 2021-04261 |  |  |  | 0 | 0 |  |  |  | 0
77799999 | Line Removal | 0 | MEET | MEET | 2021110 |  | 31.8 | 31.8 | 2021 |  |  | 0 | 0 | UNSE | Various | VARIOUS | VARIOUS | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  |  | Various | Various | Various | Various |  |  |  |  | VARIOUS | 0 | 0 | 167904 | 0 | [9 empty] | 0 |  |  |  |  | 0
35226625 | FRRB - REMG - 2021 | 2 | MEET | No | 2021111 |  | 7.9 | 7.9 | 2021 |  |  | 0 | 1756.67 | UNSE | 102781101 | ELK CREEK 1101 | ELK CREEK 11012106 | 67 | 13.2402 | 340 | 13.1388 | 0.1961 | 40 | 7.7611 |  |  | FRRB | ELK CREEK | Glenn | North Valley | Northern | 5795150 | E.5034795.01.01 | 120445306 | 35226625 | FRRB - ELK CREEK 1101 LR 2106 | 0 | 0 | 0 | 41712 | [9 empty] | 0 | 0 |  |  |  | 0
35217274 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021112 |  | 2.52 | 2.52 | 2021 |  |  | 0 | 19664.6 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.18857 |  |  | FRRB | PESCADERO | San Mateo | Peninsula | Central Coast | 5794202 | E.5034613.01.01 | 120048101 | 35217274 | FRRB - PN DIVISION SAN MATEO COUNTY | 0 | 13305.6 | 0 | 0 |  | 2020-84558 | 13305.6 | 2.52 | 4621000 |  |  | 13305.6 | 0 | 13305.6 | 2.52 |  |  |  | 0
35217275 | FRRB - UG - 2021 | 8 | MEET | MEET | 2021113 |  | 2.9 | 2.9 | 2021 |  |  | 0 | 20329.7 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 110369412 | 150 | 15.5679 | 2055 | 1.1767 | 0.0078448 | 1975 | 0.21701 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794201 | E.5034614.01.01 | 120048103 | 35217275 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 0 | 15312 | 0 | 0 |  | 2020-87935 | 15312 | 2.9 | 5352500 |  |  |  |  | 0 | 0 |  |  |  | 0
35226626 | FRRB - REMG - 2021 | 2 | MEET | No | 2021114 |  | 4.03 | 4.03 | 2021 |  |  | 0 | 9817.75 | UNSE | 42751113 | FITCH MOUNTAIN 1113 | FITCH MOUNTAIN 11136751 | 139 | 22.6749 | 945 | 10.2759 | 0.073927 | 1284 | 1.8081 |  |  | FRRB | HEALDSBURG | Sonoma | Sonoma | Northern | 5795151 | E.5034796.01.01 | 120445370 | 35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | 0 | 0 | 0 | 21278.4 | [9 empty] | 0 |  |  |  |  | 0
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021115 |  | 2.56 | 2.56 | 2021 |  |  | 0 | -679894.08 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.54034 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 13516.8 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021116 |  | 4.8 | 4.8 | 2021 |  |  | 0 | -179287.42 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.6177 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 25344 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0
35199565 | FRRB - OH - 2021 | 14 | MEET | No | 2021117 |  | 6.72 | 6.72 | 2021 |  |  | 0 | -679894.08 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.9082 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119750044 | 35199565 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 35481.6 | 0 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0
35200051 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021118 |  | 7.25 | 7.25 | 2021 |  |  | 0 | -179287.42 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 3.2873 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5541890 |  | 119765913 | 35200051 | NO-NV-BUTTE 9/8/20- N. CMPLX FIRE SYS H | 0 | 38280 | 0 | 0 | [9 empty] | 0 |  |  |  |  | 0
35220936 | FRRB - UG - 2021 | 5 | MEET | MEET | 2021119 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 7688.08 | UNSE | 24101103 | HALF MOON BAY 1103 | HALF MOON BAY 11036012 | 79 | 6.6683 | 2186 | 0.42722 | 0.0054078 | 2095 | 0.060255 |  |  | FRRB | PESCADERO | Santa Cruz | Peninsula | Central Coast | 5794202 | E.5034613.01.02 | 120224375 | 35220936 | FRRB - BUTANO STATE PARK - PN SM | 0 | 5016 | 0 | 0 | [14 empty] | 0
35223343 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021120 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 58667.59 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.28647 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.08 | 120255838 | 35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 1 | 0 | 4488 | 0 | 0 |  | 2021-02744 | 4488 | 0.85 | 1338480 | [9 empty] | 0
35225821 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021121 |  | 0.95 | 0.95 | 2021 |  |  | 0 | 49185.41 | ESTS | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.32018 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.11 | 120424578 | 35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE ZONE 2 | 0 | 5016 | 0 | 0 |  | 2021-02748 | 5016 | 0.95 | 1638720 | [9 empty] | 0
35235139 | FRRB - UG - 2021 | 2 | MEET | No | 2021122 |  | 0 | [5 empty] | 222.76 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5794519 | E.5034825.01.22 | 120582960 | 35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH 3 | 0 | 0 | 0 | 0 |  |  |  |  | 11624000
35229043 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021123 |  | 0.41345 | 0.41345 | 2021 | 0.41 |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.060599 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.01 | 120493696 | 35229043 | FRRB – WYANDOTTE 1103 - BALD ROCK ZONE 1 | 0 | 2183 | 0 | 0 | [14 empty] | 0
35223344 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021124 |  | 4.1617 | 4.1617 | 2021 |  |  | 0 | 513596.61 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.60999 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.09 | 120255980 | 35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | 0 | 21974 | 0 | 0 |  | 2021-02746 | 9081.6 | 1.72 | 3007400 | [9 empty] | 0 |  | 2021-07956
35223345 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021125 |  | 4.454 | 4.454 | 2021 |  |  | 0 | 1587400.03 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 1.6208 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.10 | 120255982 | 35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | 0 | 23517 | 0 | 0 |  | 2021-02747 | 13147.2 | 2.49 | 4312040 | [9 empty] | 0 | 2021-09321 | 2021-11881
35225822 | FRRB - UG - 2021 | 20 | MEET | MEET | 2021126 |  | 1.8693 | 1.8693 | 2021 |  |  | 0 | 407737.08 | CONS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.27399 |  | Tier 3 | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.12 | 120424579 | 35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | 0 | 9870 | 0 | 0 |  | 2021-02749 | 5755.2 | 1.09 | 1954920 | [9 empty] | 0 |  | 2021-14698
35225823 | FRRB - UG - 2021 | 20 | MEET | MEET | 2021127 |  | 1.7159 | 1.7159 | 2021 |  |  | 0 | 120220.71 | CONS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.6244 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.13 | 120424672 | 35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | 0 | 9060 | 0 | 0 |  | 2021-02750 | 9081.6 | 1.72 | 3005800 | [9 empty] | 0 |  | 2021-17135
35225824 | FRRB - UG - 2021 | 19 | MEET | MEET | 2021128 |  | 2.9364 | 2.9364 | 2021 |  |  | 0 | 569229.37 | UNSC | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 1.3314 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5793918 | E.5034572.01.14 | 120424703 | 35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | 0 | 15504 | 0 | 0 |  | 2021-02751 | 13464 | 2.55 | 4213480 | [9 empty] | 0 |  | 2021-09839
35222234 | Remote Grid Pilot | 10 | MEET | No | 2021129 |  | 2.62 | 2.62 | 2021 |  |  | 0 | 0 | UNSE | 254421101 | OAKHURST 1101 | OAKHURST 110110090 | 435 | 44.0886 | 421 | 75.8506 | 0.17437 | 167 | 4.4624 |  |  | REMG | OAKHURST | Mariposa | Yosemite | Central Valley | 5543982 | E.5034752.01.01 | 120237130 | 35222234 | REMG - OAKHURST 110110090 | 0 | 0 | 0 | 13833.6 |  | 2021-00557 | 13833.6 | 2.62 | 4816500 | 2021-17162 |  |  |  | 0 |  |  |  |  | 0
35232298 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021130 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 5706.09 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.035177 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.02 | 120532441 | 35232298 | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | 0 | 1267.2 | 0 | 0 |  | 2021-09904
35233038 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021131 |  | 0.23 | 0.23 | 2021 |  |  | 0 | 185.32 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.033711 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.05 | 120542278 | 35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | 0 | 1214.4 | 0 | 0 |  | 2021-09904
35233039 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021132 |  | 0.37 | 0.37 | 2021 |  |  | 0 | 74.46 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.06 | 120542500 | 35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | 0 | 1953.6 | 0 | 0 |  | 2021-09904
35233300 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021133 |  | 0.32 | 0.32 | 2021 |  |  | 0 | 74.45 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.046902 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.07 | 120542502 | 35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | 0 | 1689.6 | 0 | 0 |  | 2021-09904
35233301 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021134 |  | 0.36 | 0.36 | 2021 |  |  | 0 | 74.45 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.052765 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.08 | 120542503 | 35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | 0 | 1900.8 | 0 | 0 |  | 2021-09904
35233302 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021135 |  | 0.12 | 0.12 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.017588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.09 | 120542504 | 35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | 0 | 633.6 | 0 | 0 |  | 2021-09904
35233303 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021136 |  | 0.09 | 0.09 | 2021 |  |  | 0 | 74.45 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.013191 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.10 | 120542505 | 35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | 0 | 475.2 | 0 | 0 |  | 2021-09904
35233304 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021137 |  | 0.3 | 0.3 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.043971 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.11 | 120542506 | 35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | 0 | 1584 | 0 | 0 |  | 2021-09904
35233305 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021138 |  | 0.29 | 0.29 | 2021 |  |  | 0 | 185.32 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.042505 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.12 | 120542507 | 35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | 0 | 1531.2 | 0 | 0 |  | 2021-09904
35233306 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021139 |  | 0.26 | 0.26 | 2021 |  |  | 0 | 74.45 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.038108 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.13 | 120541535 | 35233306 | FRRB - WYANDOTTE 1103 - W1 PH 1.10 | 0 | 1372.8 | 0 | 0 |  | 2021-09904
35233307 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021140 |  | 0.6 | 0.6 | 2021 |  |  | 0 | 74.45 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.087942 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.14 | 120541538 | 35233307 | FRRB - WYANDOTTE 1103 - W1 PH 1.11 | 0 | 3168 | 0 | 0 |  | 2021-09904
35233308 | FRRB - UG - 2021 | 14 | MEET | MEET | 2021141 |  | 0.93 | 0.93 | 2021 |  |  | 0 | 74.45 | ESTS | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.13631 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.15 | 120541539 | 35233308 | FRRB - WYANDOTTE 1103 - W1 PH 1.12 | 0 | 4910.4 | 0 | 0 |  | 2021-09904
35233309 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021142 |  | 0.37 | 0.37 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.054231 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.16 | 120541630 | 35233309 | FRRB - WYANDOTTE 1103 - W1 PH 1.13 | 0 | 1953.6 | 0 | 0 |  | 2021-09904
35233310 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021143 |  | 0.15 | 0.15 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.021985 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.17 | 120541632 | 35233310 | FRRB - WYANDOTTE 1103 - W1 PH 1.14 | 0 | 792 | 0 | 0 |  | 2021-09904
35232718 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021144 |  | 1.2 | 1.2 | 2021 |  |  | 0 | 4844.94 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17588 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.03 | 120538803 | 35232718 | FRRB - WYANDOTTE 1103 - W2 PH 2.1 | 0 | 6336 | 0 | 0 |  | 2021-12804 | 68851.2 | 13.04 | 22032320
35233311 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021145 |  | 1.25 | 1.25 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.18321 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.18 | 120541633 | 35233311 | FRRB - WYANDOTTE 1103 - W2 PH 2.2 | 0 | 6600 | 0 | 0 |  | 2021-12804
35233312 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021146 |  | 1.1 | 1.1 | 2021 |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.16123 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.19 | 120541634 | 35233312 | FRRB - WYANDOTTE 1103 - W2 PH 2.3 | 0 | 5808 | 0 | 0 |  | 2021-12804
35233314 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021147 |  | 1.6 | 1.6 | 2021 |  |  | 0 | 110.87 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.23451 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.20 | 120541635 | 35233314 | FRRB - WYANDOTTE 1103 - W2 PH 2.4 | 0 | 8448 | 0 | 0 |  | 2021-12804
35233315 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021148 |  | 0.96004 | 0.96004 | 2021 |  |  | 0 | 110.87 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.14071 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.21 | 120541636 | 35233315 | FRRB - WYANDOTTE 1103 - W2 PH 2.5 | 0 | 5069 | 0 | 0 |  | 2021-12804
35235705 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021149 |  | 1.3201 | 1.3201 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.19348 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.40 | 120594567 | 35235705 | FRRB - WYANDOTTE 1103 - W2 PH 2.6 | 0 | 6970 | 0 | 0 |  | 2021-12804
35235706 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021150 |  | 1.16 | 1.16 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.17003 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.41 | 120594568 | 35235706 | FRRB - WYANDOTTE 1103 - W2 PH 2.7 | 0 | 6125 | 0 | 0 |  | 2021-12804
35235707 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021151 |  | 0.95 | 0.95 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 0.14065 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.42 | 120594569 | 35235707 | FRRB - WYANDOTTE 1103 - W2 PH 2.8 | 0 | 0 | 5016 | 0 |  | 2021-12804
35235320 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021152 |  | 10 | 10 |  |  |  | 0 | 1044.43 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 3.6389 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.23 | 120582839 | 35235320 | FRRB - WYANDOTTE 1103 - W3 PH 3 | 0 | 52800 | 0 | 0 |  | 2021-18851 | 36326.4 | 6.88 | 11624000
35235669 | FRRB - UG - 2021 | 6 | MEET | MEET | 2021153 |  | 0.41098 | 0.41098 |  |  |  | 0 | 731 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.14955 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.24 | 120594870 | 35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | 0 | 2170 | 0 | 0
35235671 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021154 |  | 0.49242 | 0.49242 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.17919 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.26 | 120594872 | 35235671 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | 0 | 2600 | 0 | 0
35239095 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021155 |  | 1.1326 | 1.1326 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.41213 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.66 | 120685501 | 35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 |  | 5980
35239096 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021156 |  | 0.88125 | 0.88125 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.32068 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.67 | 120685505 | 35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 |  | 4653
35239097 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021157 |  | 1.0127 | 1.0127 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.36851 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.68 | 120685508 | 35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 |  | 5347
35239098 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021158 |  | 1.3792 | 1.3792 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.50186 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.69 | 120685590 | 35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 |  | 7282
35239099 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021159 |  | 0.65758 | 0.65758 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.23928 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.70 | 120685592 | 35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 |  | 3472
35236991 | FRRB - REMG - 2021 | 2 | MEET | MEET | 2021160 |  | 1.5188 | 1.5188 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.55266 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.52 | 120627593 | 35236991 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | 0 | 8019 | 0 | 0
35236993 | FRRB - REMG - 2021 | 2 | MEET | No | 2021161 |  | 0.39773 | 0.39773 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.14473 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.54 | 120627595 | 35236993 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | 0 | 0 | 0 | 2100
35236995 | FRRB - REMG - 2021 | 2 | MEET | No | 2021162 |  | 1.972 | 1.972 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.71758 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.55 | 120627597 | 35236995 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | 0 | 0 | 0 | 10412
35235670 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021163 |  | 3.91 | 3.91 |  |  |  | 0 | 76.56 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 1.4228 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.25 | 120594871 | 35235670 | FRRB - WYANDOTTE 1103 - W5 PH 5 | 0 | 20645 | 0 | 0
35235672 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021164 |  | 1.64 | 1.64 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.59676 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.27 | 120594873 | 35235672 | FRRB - WYANDOTTE 1103 - W7 PH 7 | 0 | 8659 | 0 | 0
35235673 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021165 |  | 2.14 | 2.14 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.77871 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.28 | 120594874 | 35235673 | FRRB - WYANDOTTE 1103 - W8 PH 8 | 0 | 11299 | 0 | 0
35235674 | FRRB - UG - 2021 | 7 | MEET | MEET | 2021166 |  | 4.3 | 4.3 |  |  |  | 0 | 76.56 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 2.9484 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.29 | 120596259 | 35235674 | FRRB - BIG BEND 1102 - B1 PH 1 | 0 | 22704 | 0 | 0 |  | 2021-18846 | 2798.4 | 0.53 | 1060160
35235675 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021167 |  | 1 | 1 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 1102CB | 139 | 17.0366 | 865 | 11.7994 | 0.084888 | 1081 | 0.68567 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.30 | 120596615 | 35235675 | FRRB - BIG BEND 1102 - B2 PH 2 | 0 | 5280 | 0 | 0
35235676 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021168 |  | 2.3701 | 2.3701 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.79878 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.31 | 120598345 | 35235676 | FRRB - BIG BEND 1102 - B3 PH 3 | 0 | 12514 | 0 | 0
35235677 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021169 |  | 4.2 | 4.2 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4155 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.32 | 120598407 | 35235677 | FRRB - BIG BEND 1102 - B4 PH 4 | 0 | 22176 | 0 | 0
35235678 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021170 |  | 4.4 | 4.4 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 1.4829 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.33 | 120598535 | 35235678 | FRRB - BIG BEND 1102 - B5 PH 5 | 0 | 23232 | 0 | 0
35235679 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021171 |  | 6.5 | 6.5 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 2.1907 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.34 | 120598623 | 35235679 | FRRB - BIG BEND 1102 - B6 PH 6 | 0 | 34320 | 0 | 0
35235700 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021172 |  | 5.44 | 5.44 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.2343 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.35 | 120598982 | 35235700 | FRRB - KANAKA 1101 - K1 PH 1 | 0 | 28723 | 0 | 0
35235701 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021173 |  | 3.49 | 3.49 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.79185 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.36 | 120599070 | 35235701 | FRRB - KANAKA 1101 - K2 PH 2 | 0 | 18427 | 0 | 0
35235702 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021174 |  | 2.14 | 2.14 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.48554 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.37 | 120599072 | 35235702 | FRRB - KANAKA 1101 - K3 PH3 | 0 | 11299 | 0 | 0
35235703 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021175 |  | 8.44 | 8.44 |  |  |  | 0 | 76.56 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.915 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.38 | 120599073 | 35235703 | FRRB - KANAKA 1101 - K4 PH 4 | 0 | 44563 | 0 | 0
35235704 | FRRB - UG - 2021 | 2 | MEET | MEET | 2021176 |  | 6.1 | 6.1 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 1.384 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.39 | 120599076 | 35235704 | FRRB - KANAKA 1101 - K5 PH 5 | 0 | 32208 | 0 | 0
35237021 | FRRB - UG - 2021 | 2 | MEET | No | 2021178 |  | 0 | 0 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | #DIV/0! |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.43 | 120627369 | 35237021 | FRRB - KANAKA 1101 - K6 PH 6 | 0 | 0 | 0 | 0
35236983 | FRRB - REMG - 2021 | 2 | MEET | No | 2021179 |  | 0.30303 | 0.30303 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.10213 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.45 | 120627452 | 35236983 | NCF - RG - BB1102 - FH-73T (PARTIAL) | 0 | 0 | 0 | 1600
35236997 | FRRB - REMG - 2021 | 2 | MEET | No | 2021180 |  | 1.6562 | 1.6562 |  |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | 0.5582 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.56 | 120627598 | 35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 | 0 | 0 | 0 | 8745
35236982 | FRRB - REMG - 2021 | 2 | MEET | No | 2021181 |  | 1.9248 | 1.9248 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.43672 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.44 | 120627450 | 35236982 | NCF - RG - K1101 - REMOVAL 33 | 0 | 0 | 0 | 10163
35236985 | FRRB - REMG - 2021 | 2 | MEET | No | 2021182 |  | 1.5911 | 1.5911 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.36101 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.47 | 120627455 | 35236985 | NCF - RG - K1101 - REMOVAL 28, 105, 150 | 0 | 0 | 0 | 8401
35236986 | FRRB - REMG - 2021 | 2 | MEET | No | 2021183 |  | 1.5748 | 1.5748 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.35731 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.48 | 120627456 | 35236986 | NCF - RG - K1101 - REMOVAL 5 | 0 | 0 | 0 | 8315
35236988 | FRRB - REMG - 2021 | 2 | MEET | No | 2021184 |  | 0.24489 | 0.24489 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.055563 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.49 | 120627500 | 35236988 | NCF - RG - K1101 - REMOVAL 4 | 0 | 0 | 0 | 1293
35236989 | FRRB - REMG - 2021 | 2 | MEET | No | 2021185 |  | 0.47216 | 0.47216 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.10713 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.50 | 120627501 | 35236989 | NCF - RG - K1101 - REMOVAL 1 | 0 | 0 | 0 | 2493
35236992 | FRRB - REMG - 2021 | 2 | MEET | No | 2021186 |  | 0.58712 | 0.58712 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.13321 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.53 | 120627594 | 35236992 | NCF - RG - K1101 - REMOVAL 24 | 0 | 0 | 0 | 3100
35236999 | FRRB - REMG - 2021 | 2 | MEET | No | 2021187 |  | 1.0038 | 1.0038 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.22775 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.57 | 120627599 | 35236999 | NCF - RG - K1101 - REMOVAL 3 | 0 | 0 | 0 | 5300
35237020 | FRRB - REMG - 2021 | 2 | MEET | No | 2021188 |  | 0.39773 | 0.39773 |  |  |  | 0 | 0 | UNSE | 103221101 | KANAKA 1101 | KANAKA 1101CB | 37 | 4.7271 | 1480 | 1.0834 | 0.029281 | 1533 | 0.090241 |  |  | FRRB | OROVILLE | Butte | North Valley | Northern | 5795419 | E.5034825.01.58 | 120627702 | 35237020 | NCF - RG - K1101 - REMOVAL 50 | 0 | 0 | 0 | 2100
35236984 | FRRB - REMG - 2021 | 2 | MEET | No | 2021189 |  | 1.8559 | 1.8559 |  |  |  | 0 | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | 0.84149 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.46 | 120627454 | 35236984 | NCF - RG - W1103 - REMOVAL 95, 96 | 0 | 0 | 0 | 9799
35236990 | FRRB - REMG - 2021 | 2 | MEET | No | 2021190 |  | 0.37841 | 0.37841 |  |  |  | 0 | 161.39 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031976 | 217 | 23.7815 | 1299 | 8.7412 | 0.040282 | 1128 | 0.1377 |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.51 | 120627591 | 35236990 | NCF - RG - W1103 - REMOVAL 72 | 0 | 0 | 0 | 1998
35222236 | Remote Grid Pilot | 10 | MEET | No | 2021191 |  | 0.99 | 0.99 | 2021 |  |  | 0 | 0 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210135244 | 146 | 17.4635 | 428 | 25.237 | 0.17286 | 468 | 1.4164 |  |  | REMG | MARIPOSA | Mariposa | Yosemite | Central Valley | 5543983 | E.5034753.01.01 | 120237131 | 35222236 | REMG - MARIPOSA 210135244 | 0 | 0 | 0 | 5227.2 |  | 2020-88214 | 5227.2 | 0.99 | 780759 | 2021-17152 |  |  |  | 0 |  |  |  |  | 0
35175853 | Remote Grid Pilot | 13 | No | No | 2021192 |  | 0.7 | 0.7 | 2021 |  |  | 0 | 7692.52 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.0417 |  |  | REMG | GEORGETOWN | El Dorado | Sierra | Northern | 5790554 | E.5015422.03 | 118981960 | 35175853 | REMG - PLACERVILLE 21061104 | 0 | 0 | 0 | 3696 |  | 2018-84079 | 45936 | 8.7 | 9322600 |  |  |  |  | 0 |  |  |  |  | 0
35222235 | Remote Grid Pilot | 9 | No | No | 2021193 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 15606.92 | UNSE | 254061102 | DUNLAP 1102 | DUNLAP 1102778286 | 5 | 2.6029 | 2738 | 0.0024545 | 0.0004909 | 2461 | 0.0024273 |  |  | REMG | BADGER | Tulare | Fresno | Central Valley | 5794900 | E.5034754.01.01 | 120236988 | 35222235 | REMG - DUNLAP 1102778286 | 0 | 0 | 0 | 13728 |  | 2020-88308 | 13728 | 2.6 | 613214 |  |  |  |  | 0 |  |  |  |  | 0
35229051 | Remote Grid Pilot | 10 | MEET | No | 2021194 |  | 3.04 | 3.04 | 2021 |  |  | 0 | 8907.39 | UNSE | 103331102 | CORNING 1102 | CORNING 110253184 | 123 | 31.8239 | 413 | 21.5791 | 0.17544 | 106 | 2.0407 |  |  | REMG | FLOURNEY | Tehama | North Valley | Northern | 5795612 | E.5034827.01.01 | 120494134 | 35229051 | CORNING 1102 - REMOTE GRID #299 & # 300 | 0 | 0 | 0 | 16051 |  | 2021-09834 | [12 empty] | 0
35219543 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021195 |  | 0.24015 | 0.24015 | 2021 |  |  | 0 | 4441.95 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.021288 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.02 | 120135657 | 35219543 | PSPS - West Main St / Reservoir St - PLA PH 1.1 | 0 | 1268 | 0 | 0 |  | 2021-01722 | 1267.2 | 0.24 | 850440 | 2021-12131 |  |  |  | 0 |  |  |  |  | 0
35223036 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021196 |  | 0.055871 | 0.055871 | 2021 |  |  | 0 | 4966.04 | UNSE | 152481110 | BRUNSWICK 1110 | BRUNSWICK 1110CB | 26 | 0.0034177 | 2134 | 0.16685 | 0.0064174 | 2454 | 2.7003 |  |  | PSPS | GRASS VALLEY | Nevada | Sierra | Northern | 5794983 | E.5034759.01.01 | 120242599 | 35223036 | PSPS - Brunswick 1110CB | 0 | 295 | 0 | 0 |  | 2021-01470 | 264 | 0.05 | 88320 | 2021-08160 |  |  |  | 0 |  |  | 0.04 | 300 | 7500
35223030 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021197 |  | 0.85 | 0.85 | 2021 |  |  | 0 | 14951.84 | UNSE | 103191101 | BANGOR 1101 | BANGOR 1101CB | 171 | 18.7561 | 355 | 33.1366 | 0.19378 | 565 | 1.4867 |  |  | PSPS | BANGOR | Butte | Sierra | Northern | 5794981 | E.5034757.01.01 | 120242544 | 35223030 | PSPS - Bangor 1101CB | 0 | 4488 | 0 | 0 |  | 2021-01574 | 3009.6 | 0.57 | 1556240 | 2021-08449 |  |  |  | 0 |  |  | 1 | 3700 | 3700
35223062 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021198 |  | 0.18 | 0.18 | 2021 |  |  | 0 | 7106.36 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102184814 | 20 | 0.42402 | 3098 | 0.00017414 | 8.707e-06 | 3379 | 7.3185e-05 |  | Tier 2 | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.01 | 120242676 | 35223062 | PSPS - Calistoga 1102184814 | 0 | 950.4 | 0 | 0 |  | 2021-01578 | 950.4 | 0.18 | 579050 | 2021-07698 |  |  |  | 0 |  |  |  |  | 0
35223038 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021199 |  | 0.46 | 0.46 | 2021 |  |  | 0 | 8921.72 | UNSE | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | 0.89286 |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.01 | 120242693 | 35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH 1.1 | 0 | 2428.8 | 0 | 0 |  | 2021-01713 | 4593.6 | 0.87 | 911350 | 2021-12822 |  |  |  | 0 |  |  |  |  | 0
35234284 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021200 |  | 0.45 | 0.45 | 2021 |  |  | 0 | 0 | UNSE | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | 0.87345 |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.02 | 120539923 | 35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH 1.2 | 0 | 2376 | 0 | 0 | [5 empty] | 2021-12822
35234526 | PSPS - Community Resiliency | 9 | MEET | No | 2021201 |  | 0.4 | 0.4 | 2021 |  |  | 0 | 0 | UNSE | 163541101 | MARTELL 1101 | MARTELL 1101CB | 171 | 5.879 | 999 | 11.5263 | 0.067405 | 1314 | 0.48623 |  | Tier 2 | PSPS | SUTTER CREEK | Amador | Stockton | Central Valley | 5794988 | E.5034764.01.03 | 120574717 | 35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH 1.3 | 2112 | 0 | 0 | 0 | [5 empty] | 2021-12822
35223060 | PSPS - Community Resiliency | 9 | MEET | MEET | 2021202 |  | 1.74 | 1.74 | 2021 |  |  | 0 | 5062.09 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | 0.18012 |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.01 | 120242671 | 35223060 | PSPS-ALLEGHANY 1101-Downieville PH 1.1 | 0 | 9187.2 | 0 | 0 |  | 2021-01568 | 9187.2 | 1.74 | 4040000 |  |  |  |  | 0 |  |  |  |  | 0
35234527 | PSPS - Community Resiliency | 9 | MEET | No | 2021203 |  | 0 | 0 | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.02 | 120574718 | 35234527 | PSPS-ALLEGHANY 1101-Downieville PH 1.2 | 0 | 0 | 0 | 0
35234528 | PSPS - Community Resiliency | 9 | MEET | No | 2021204 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.03 | 120574870 | 35234528 | PSPS-ALLEGHANY 1101-Downieville PH 1.3 | 0 | 0 | 0 | 0
35234529 | PSPS - Community Resiliency | 9 | MEET | No | 2021205 |  |  |  | 2021 |  |  | 0 | 0 | UNSE | 152101101 | ALLEGHANY 1101 | ALLEGHANY 1101VR816 | 49 | 4.1491 | 2010 | 0.43385 | 0.0088541 | 2312 | #DIV/0! |  |  | PSPS | DOWNIEVILLE | Sierra | Sierra | Northern | 5794984 | E.5034760.01.04 | 120574871 | 35234529 | PSPS-ALLEGHANY 1101-Downieville PH 1.4 | 0 | 0 | 0 | 0
35223063 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021206 |  | 0.15114 | 0.15114 | 2021 |  |  | 0 | 4536.46 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.073206 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.01 | 120242673 | 35223063 | PSPS - DUNBAR 1101 - OAKMONT PH 1 | 0 | 798 | 0 | 0 |  | 2021-01566 | 10190.4 | 1.93 | 4690000 | 2021-14008 |  |  |  | 0 |  |  |  |  | 0
35228774 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021207 |  | 0.97405 | 0.97405 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.47181 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.02 | 120487476 | 35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | 0 | 5143 | 0 | 0 |  | 2021-01566 |  |  |  | 2021-14008 | [8 empty] | 0
35228775 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021208 |  | 0.88617 | 0.88617 | 2021 |  |  | 0 | 0 | UNSE | 43071101 | DUNBAR 1101 | DUNBAR 1101CB | 191 | 3.1203 | 2048 | 1.5267 | 0.007993 | 2185 | 0.42924 |  | Tier 2 | PSPS | SANTA ROSA | Sonoma | Sonoma | Northern | 5794985 | E.5034761.01.03 | 120487477 | 35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | 0 | 4679 | 0 | 0 |  | 2021-01566 |  |  |  | 2021-14008 | [8 empty] | 0
35223032 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021209 |  | 0.43087 | 0.43087 | 2021 |  |  | 0 | 9433.34 | UNSE | 152282102 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 2101CB | 262 | 24.9941 | 68 | 101.3032 | 0.38665 | 328 | 1.7289 |  | Tier 2 | PSPS | COOL | El Dorado | Sierra | Northern | 5794982 | E.5034758.01.01 | 120242546 | 35223032 | PSPS - Mounatin Quarries 2101CB | 0 | 2275 | 0 | 0 |  | 2021-01503 | 2323.2 | 0.44 | 745920 | 2021-10707 |  |  |  | 0 |  |  |  |  | 0
35223037 | PSPS - Community Resiliency | 18 | MEET | MEET | 2021210 |  | 0.052083 | 0.052083 | 2021 |  |  | 0 | 15952.32 | PEND | 254421101 | OAKHURST 1101 | OAKHURST 1101CB | 47 | 2.3149 | 847 | 4.0694 | 0.086583 | 802 | 0.090642 |  | Tier 3 | PSPS | OAKHURST | Madera | Yosemite | Central Valley | 5794989 | E.5034765.01.01 | 120242694 | 35223037 | PSPS - Oakhurst 1101CB | 0 | 275 | 0 | 0 |  | 2021-01716 | 580.8 | 0.11 | 181120 | 2021-06095 |  |  |  | 0 |  |  | 0.0891 | 200 | 2244.6689
35224377 | PSPS - Community Resiliency | 11 | MEET | MEET | 2021211 |  | 0.21 | 0.21 | 2021 |  |  | 0 | 4776.92 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.081687 |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.01 | 120360607 | 35224377 | PSPS - PLACERVILLE 21067522 PH 1.1 | 0 | 1108.8 | 0 | 0 |  | 2021-01725 | 5966.4 | 1.13 | 2731920 | 2021-13409 |  |  |  | 0 |  |  |  |  | 0
35233995 | PSPS - Community Resiliency | 11 | MEET | MEET | 2021212 |  | 0.57 | 0.57 | 2021 |  |  | 0 | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.22172 |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.02 | 120563909 | 35233995 | PSPS - PLACERVILLE 21067522 PH 1.2 | 0 | 3009.6 | 0 | 0 |  | 2021-01725 |  |  |  | 2021-13409
35233996 | PSPS - Community Resiliency | 11 | MEET | MEET | 2021213 |  | 0.71 | 0.71 | 2021 |  |  | 0 | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21067522 | 745 | 67.3656 | 1363 | 26.4689 | 0.035529 | 1360 | 0.27618 |  | Tier 3 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5795018 | E.5034778.01.03 | 120563933 | 35233996 | PSPS - PLACERVILLE 21067522 PH 1.3 | 0 | 3748.8 | 0 | 0 |  | 2021-01725 |  |  |  | 2021-13409
35223039 | PSPS - Community Resiliency | 13 | MEET | MEET | 2021214 | 0.63 | 0.60739 | 0.60739 | 2021 |  |  | 0 | 12807.39 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 1109702710 | 49 | 2.6641 | 218 | 12.174 | 0.24845 | 672 | 2.522 |  | Tier 2 | PSPS | OROVILLE | Butte | North Valley | Northern | 5794987 | E.5034763.01.01 | 120242691 | 35223039 | PSPS - Wyandotte 1109702710 | 705 | 2502 | 0 | 0 |  | 2021-01576 | 4065.6 | 0.77 | 1517740 | 2021-08443 |  |  |  | 0 |  |  | 1.51 | 2600 | 1721.8543
35219542 | PSPS - Community Resiliency | 10 | MEET | MEET | 2021215 |  | 0.14 | 0.14 | 2021 |  |  | 0 | 7543.77 | UNSE | 153081112 | PLACERVILLE 1112 | PLACERVILLE 1112CB | 117 | 8.513 | 2123 | 0.76223 | 0.0065148 | 2310 | 0.01241 |  | Tier 2 | PSPS | PLACERVILLE | El Dorado | Sierra | Northern | 5543321 | E.5034715.01.01 | 120135655 | 35219542 | PSPS - Eskaton Village | 0 | 739.2 | 0 | 0 |  | 2021-01718 | 739.2 | 0.14 | 544560 | 2021-11652 |  |  |  | 0 |  |  |  |  | 0
35144944 | PSPS - Community Resiliency | 18 | MEET | No | 2021216 |  | 0.26 | 0.26 |  |  |  | 0 | 122738.87 | PEND | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 | 2144 | 0.022555 |  |  | PSPS | SOUTH SAN FRANCISCO | San Mateo | Peninsula | Central Coast | 5530170 |  | 118261958 | 35144944 | PSPS - Sneath Lane 1107CB | 1372.8 | 0 | 0 | 0
35219291 | Top 250 Miles | 18 | MEET | No | 2021400 |  | 0.39811 | 0.39811 | 2021 |  |  | 0 | 13994.6 | PEND | 63591101 | VACA DIXON 1101 | VACA DIXON 1101126774 | 11 | 0.78766 | 20 | 6.8232 | 0.62029 | 24 | 2.1382 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5543350 | E.5034693.01.01 | 120141627 | 35219291 | CWSP - VACA DIXON 1101126774 | 2102 | 0 | 0 | 0 |  | 2021-01500 | 2112 | 0.4 | 1561600 | 2021-04312 |  |  |  | 0 | 0 |  |  |  | 0
35219097 | Top 250 Miles | 14 | MEET | No | 2021401 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 42851.58 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.01 | 120141762 | 35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 | 45302.4 | 8.58 | 7867593 | 2021-04771 |  |  |  | 0 | 0 |  | 26.69 | 19300 | 723.1173
35227260 | Top 250 Miles | 14 | MEET | No | 2021402 |  | 2.36 | 2.36 | 2021 |  |  | 0 | 5138.83 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 9.6946 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.02 | 120457078 | 35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | 12460.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0
35227261 | Top 250 Miles | 14 | MEET | No | 2021403 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 26240.86 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 8.873 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.03 | 120457111 | 35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0
35227262 | Top 250 Miles | 14 | MEET | No | 2021404 |  | 1.4015 | 1.4015 | 2021 |  |  | 0 | 28369.21 | ESTS | 254432104 | COARSEGOLD 2104 | COARSEGOLD 2104CB | 27 | 2.4277 | 22 | 16.0848 | 0.59573 | 95 | 5.7572 |  | Tier 2 | CWSP | COARSEGOLD | Madera | Yosemite | Central Valley | 5794546 | E.5034695.01.04 | 120457115 | 35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | 7400 | 0 | 0 | 0 |  | 2021-01581 |  |  |  | 2021-04771 | [6 empty] | 0 | 0 | 0
35219098 | Top 250 Miles | 14 | MEET | No | 2021405 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 15520.22 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 2.9196 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120141805 | 35219098 | CWSP - MIDDLETOWN 1101118494 PH 1 | 3801.6 | 0 | 0 | 0 |  | 2020-88310 | 7022.4 | 1.33 | 1830000 | 2021-04412 |  |  |  | 0 | 0 |  | 5.54 | 5600 | 1010.8303
35229119 | Top 250 Miles | 13 | MEET | MEET | 2021406 |  | 0.61 | 0.61 | 2021 |  |  | 0 | 2458.16 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101118494 | 12 | 1.0659 | 23 | 6.971 | 0.58092 | 79 | 3.9497 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.01 | 120496477 | 35229119 | CWSP - MIDDLETOWN 1101118494 PH 2 | 0 | 3220.8 | 0 | 0 |  | 2020-88310 |  |  |  | 2021-04412 | [8 empty] | 0
35219099 | Top 250 Miles | 11 | MEET | No | 2021407 |  | 2.12 | 2.12 | 2021 |  |  | 0 | 25781.91 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 2.5862 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.01 | 120141849 | 35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | 11193.6 | 0 | 0 | 0 |  | 2021-00785 | 91344 | 17.3 | 25150000 | 2021-08349 |  |  |  | 0 | 0 |  |  |  | 0
35231620 | Top 250 Miles | 11 | MEET | MEET | 2021408 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 5.0645 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.02 | 120504137 | 35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | 0 | 13728 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231621 | Top 250 Miles | 11 | MEET | MEET | 2021409 |  | 2.51 | 2.51 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 4.8892 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.03 | 120504138 | 35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | 0 | 13252.8 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231622 | Top 250 Miles | 11 | MEET | MEET | 2021410 |  | 4.65 | 4.65 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 9.0577 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.04 | 120504139 | 35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | 0 | 24552 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231623 | Top 250 Miles | 11 | MEET | No | 2021411 |  | 1.35 | 1.35 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 2.6297 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.05 | 120504160 | 35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | 0 | 0 | 0 | 7128 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231624 | Top 250 Miles | 11 | MEET | No | 2021412 |  | 1.18 | 1.18 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 1.4395 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.06 | 120504163 | 35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | 6230.4 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231625 | Top 250 Miles | 11 | MEET | No | 2021413 |  | 0.79 | 0.79 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 1.5388 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.07 | 120504164 | 35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | 0 | 0 | 0 | 4171.2 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231626 | Top 250 Miles | 11 | MEET | No | 2021414 |  | 0.78 | 0.78 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 0.95152 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.08 | 120504165 | 35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | 4118.4 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231627 | Top 250 Miles | 11 | MEET | No | 2021415 |  | 0.35 | 0.35 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 0.42696 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.09 | 120504167 | 35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | 1848 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231628 | Top 250 Miles | 11 | MEET | No | 2021416 |  | 0.2 | 0.2 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 0.38958 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.10 | 120504170 | 35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | 0 | 0 | 0 | 1056 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231629 | Top 250 Miles | 11 | MEET | No | 2021417 |  | 1.21 | 1.21 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 2.357 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.11 | 120504175 | 35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | 0 | 0 | 0 | 6388.8 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231630 | Top 250 Miles | 11 | MEET | No | 2021418 |  | 0.3 | 0.3 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 0.36597 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.12 | 120504176 | 35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | 1584 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35231631 | Top 250 Miles | 11 | MEET | No | 2021419 |  | 0.38 | 0.38 | 2021 |  |  | 0 | 0 | UNSE | 43361102 | HIGHLANDS 1102 | HIGHLANDS 1102628 | 51 | 14.2224 | 27 | 27.9838 | 0.5487 | 33 | 0.46356 |  | Tier 2 & 3 | CWSP | CLEARLAKE | Lake | Humboldt | Northern | 5794549 | E.5034697.01.13 | 120504177 | 35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | 2006.4 | 0 | 0 | 0 |  | 2021-00785 |  |  |  | 2021-08349 | [8 empty] | 0
35219260 | Top 250 Miles | 15 | MEET | No | 2021420 | 0.84 | 0.84432 | 0.84432 | 2021 |  |  | 0 | 12108.03 | ADER | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 3.1009 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034698.01.01 | 120141880 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1 | 4458 | 0 | 0 | 0 |  | 2021-01235 | 6916.8 | 1.31 | 2194368 | 2021-04349 |  |  |  | 0 | 0 |  | 6.25 | 4000 | 640
35219266 | Top 250 Miles | 15 | MEET | No | 2021421 |  | 2.6 | 2.6 | 2021 |  |  | 0 | 92968.93 | ADER | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 4.4861 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.01 | 120141949 | 35219266 | CWSP - MARIPOSA 2102CB PH 1 | 13728 | 0 | 0 | 0 |  | 2021-01236 | 27720 | 5.25 | 8003586 | 2021-04769 |  |  |  | 0 | 0 |  |  |  | 0
35227263 | Top 250 Miles | 14 | MEET | No | 2021422 |  | 0.25 | 0.25 | 2021 |  |  | 0 | 41747.52 | ESTS | 254452102 | MARIPOSA 2102 | MARIPOSA 2102CB | 31 | 5.2539 | 35 | 14.6212 | 0.47165 | 205 | 0.43135 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.05 | 120457435 | 35227263 | CWSP - MARIPOSA 2102CB PH 2 | 1320 | 0 | 0 | 0 |  | 2021-01236 |  |  |  | 2021-04769 | [8 empty] | 0
35219268 | Top 250 Miles | 14 | MEET | No | 2021423 |  | 1.6212 | 1.6212 | 2021 |  |  | 0 | 118399.66 | ESTS | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 4.1161 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.01 | 120142035 | 35219268 | CWSP - MARIPOSA 210197142 PH 1.1 | 8560 | 0 | 0 | 0 |  | 2021-01027 | 24288 | 4.6 | 7389000 |  |  |  |  | 0 | 0 |  |  |  | 0
35226241 | Top 250 Miles | 15 | MEET | No | 2021424 |  | 1.4799 | 1.4799 | 2021 |  |  | 0 | 49204.13 | ADER | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7573 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.02 | 120431331 | 35226241 | CWSP - MARIPOSA 210197142 PH 1.2 | 7814 | 0 | 0 | 0 | [14 empty] | 0
35226240 | Top 250 Miles | 18 | MEET | No | 2021425 |  | 1.4625 | 1.4625 | 2021 |  |  | 0 | 57526.76 | PEND | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | 3.7131 |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.03 | 120431332 | 35226240 | CWSP - MARIPOSA 210197142 PH 1.3 | 7722 | 0 | 0 | 0 | [14 empty] | 0
35219269 | Top 250 Miles | 9 | MEET | No | 2021426 |  | 2.14 | 2.14 | 2021 |  |  | 0 | 15048.47 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 12.43 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.01 | 120142106 | 35219269 | CWSP - VACA DIXON 110540092 PH 1.1 | 11299.2 | 0 | 0 | 0 |  | 2021-08140 | 130574.4 | 24.73 | 28158240 | 2021-18870 |  |  |  | 0 | 0 |  |  |  | 0
35237258 | Top 250 Miles | 9 | MEET | No | 2021427 |  | 2.15 | 2.15 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 12.4881 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.03 | 120638208 | 35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | 11352 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237259 | Top 250 Miles | 9 | MEET | No | 2021428 |  | 3.2 | 3.2 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 18.5869 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.04 | 120638232 | 35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | 16896 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237360 | Top 250 Miles | 9 | MEET | No | 2021429 |  | 3.01 | 3.01 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 17.4833 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.05 | 120638237 | 35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | 15892.8 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237361 | Top 250 Miles | 9 | MEET | No | 2021430 |  | 2.87 | 2.87 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 16.6701 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.06 | 120638239 | 35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | 15153.6 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237364 | Top 250 Miles | 9 | MEET | No | 2021431 |  | 3.03 | 3.03 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 17.5995 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.07 | 120638279 | 35237364 | CWSP - VACA DIXON 110540092 PH 1.6 | 15998.4 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237365 | Top 250 Miles | 9 | MEET | No | 2021432 |  | 2.81 | 2.81 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 16.3216 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.08 | 120638322 | 35237365 | CWSP - VACA DIXON 110540092 PH 1.7 | 14836.8 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237366 | Top 250 Miles | 9 | MEET | No | 2021433 |  | 2.19 | 2.19 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 12.7204 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.09 | 120638324 | 35237366 | CWSP - VACA DIXON 110540092 PH 1.8 | 11563.2 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237368 | Top 250 Miles | 9 | MEET | No | 2021434 |  | 2.93 | 2.93 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 17.0187 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.10 | 120638327 | 35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | 15470.4 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237369 | Top 250 Miles | 9 | MEET | No | 2021435 |  | 2.38 | 2.38 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 13.824 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.11 | 120638383 | 35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | 12566.4 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237370 | Top 250 Miles | 9 | MEET | No | 2021436 |  | 3.53 | 3.53 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 20.5037 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.12 | 120638388 | 35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | 18638.4 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35237371 | Top 250 Miles | 9 | MEET | No | 2021437 |  | 0.34 | 0.34 |  |  |  | 0 | 0 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 110540092 | 464 | 23.1653 | 37 | 217.022 | 0.46772 | 100 | 1.9749 |  |  | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.13 | 120638441 | 35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | 1795.2 | 0 | 0 | 0 |  | 2021-08140 |  |  |  | 2021-18870
35219272 | Top 250 Miles | 14 | MEET | No | 2021438 |  | 0.85436 | 0.85436 | 2021 |  |  | 0 | 8703.42 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101481876 | 14 | 0.8534 | 38 | 6.5476 | 0.46769 | 46 | 4.0641 |  | Tier 2 & 3 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794547 | E.5034696.01.02 | 120142171 | 35219272 | CWSP - MIDDLETOWN 1101481876 | 4511 | 0 | 0 | 0 |  | 2020-88311 | 4857.6 | 0.92 | 1280000 | 2021-04297 |  |  |  | 0 | 0 |  |  |  | 0
35219273 | Top 250 Miles | 14 | MEET | No | 2021439 | 3.46 | 3.461 | 3.461 | 2021 |  |  | 0 | 127893.84 | ESTS | 102541101 | VOLTA 1101 | VOLTA 110149742 | 28 | 3.4766 | 39 | 13.0013 | 0.46433 | 6 | 8.0246 |  | Tier 2 | CWSP | MANTON | Tehama | North Valley | Northern | 5794543 | E.5034705.01.01 | 120142173 | 35219273 | CWSP - VOLTA 110149742 | 18274 | 0 | 0 | 0 |  | 2021-00903 | 18374.4 | 3.48 | 8182317 | 2021-03779 | 0 | 0 | 18744 | 18744 | 3.55 | 6700000 |  |  | 0
35219275 | Top 250 Miles | 18 | MEET | No | 2021440 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 8749.24 | PEND | 63681102 | PUTAH CREEK 1102 | PUTAH CREEK 110246012 | 38 | 0.63713 | 41 | 17.3115 | 0.45557 | 96 | 8.7599 |  | Tier 2 | CWSP | WINTERS | Solano | Sacramento | Northern | 5543347 | E.5034706.01.01 | 120142210 | 35219275 | CWSP - PUTAH CREEK 110246012 | 2745.6 | 0 | 0 | 0 |  | 2020-88233 | 2745.6 | 0.52 | 566066 | 2021-02904 |  |  |  | 0 | 0 |  |  |  | 0
35219276 | Top 250 Miles | 13 | MEET | MEET | 2021441 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 30939.22 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.1163 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.01 | 120142212 | 35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | 0 | 11404.8 | 0 | 0 |  | 2021-01037 | 40444.8 | 7.66 | 11826060 | 2021-05667 |  |  |  | 0 | 0 |  |  |  | 0
35227651 | Top 250 Miles | 13 | MEET | No | 2021442 |  | 2.31 | 2.31 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 6.1057 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.03 | 120462109 | 35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | 12196.8 | 0 | 0 | 0 |  | 2021-01037 |  |  |  | 2021-05667 | [8 empty] | 0
35227652 | Top 250 Miles | 13 | MEET | MEET | 2021443 |  | 0.41 | 0.41 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.7304 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.04 | 120462111 | 35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | 0 | 2164.8 | 0 | 0 |  | 2021-01037 |  |  |  | 2021-05667 | [8 empty] | 0
35227653 | Top 250 Miles | 13 | MEET | No | 2021444 |  | 2 | 2 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.2863 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.05 | 120462112 | 35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | 10560 | 0 | 0 | 0 |  | 2021-01037 |  |  |  | 2021-05667 | [8 empty] | 0
35227654 | Top 250 Miles | 13 | MEET | No | 2021445 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 1.9031 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.06 | 120462113 | 35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | 3801.6 | 0 | 0 | 0 |  | 2021-01037 |  |  |  | 2021-05667 | [8 empty] | 0
35224378 | Top 250 Miles | 11 | MEET | No | 2021446 |  | 3.6 | 3.6 | 2021 |  |  | 0 | 14495.02 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 9.5154 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.02 | 120406213 | 35224378 | CWSP - VACAVILLE 11046542 PH 2.1 | 19008 | 0 | 0 | 0 |  | 2021-01589 | 36854.4 | 6.98 | 8840920 | 2021-06068 | [8 empty] | 0
35227870 | Top 250 Miles | 11 | MEET | MEET | 2021447 |  | 1.35 | 1.35 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 5.6977 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.07 | 120462116 | 35227870 | CWSP - VACAVILLE 11046542 PH 2.2 | 0 | 7128 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0
35227656 | Top 250 Miles | 11 | MEET | MEET | 2021448 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 3.1654 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.08 | 120462117 | 35227656 | CWSP - VACAVILLE 11046542 PH 2.3 | 0 | 3960 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0
35227657 | Top 250 Miles | 11 | MEET | No | 2021449 |  | 1 | 1 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 2.6432 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.09 | 120462180 | 35227657 | CWSP - VACAVILLE 11046542 PH 2.4 | 5280 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0
35227658 | Top 250 Miles | 11 | MEET | No | 2021450 |  | 0.04 | 0.04 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.10573 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.10 | 120462182 | 35227658 | CWSP - VACAVILLE 11046542 PH 2.5 | 211.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0
35227659 | Top 250 Miles | 11 | MEET | No | 2021451 |  | 0.24 | 0.24 | 2021 |  |  | 0 | 0 | UNSE | 63601104 | VACAVILLE 1104 | VACAVILLE 11046542 | 140 | 14.6602 | 42 | 62.4985 | 0.44642 | 86 | 0.63436 |  | Tier 3 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794545 | E.5034707.01.11 | 120462184 | 35227659 | CWSP - VACAVILLE 11046542 PH 2.6 | 1267.2 | 0 | 0 | 0 |  | 2021-01589 |  |  |  | 2021-06068 | [8 empty] | 0
35219280 | Top 250 Miles | 13 | MEET | MEET | 2021452 |  | 0.15152 | 0.15152 | 2021 |  |  | 0 | 4599.62 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 4.0762 |  | Tier 2 | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.01 | 120142216 | 35219280 | CWSP - POTTER VALLEY P H 110564118 PH 1 | 0 | 800 | 0 | 0 |  | 2020-88312 | 9820.8 | 1.86 | 2340000 | 2021-03822 |  |  |  | 0 | 0 |  |  |  | 0
35226632 | Top 250 Miles | 13 | MEET | No | 2021453 |  | 1.6828 | 1.6828 | 2021 |  |  | 0 | 1143.1 | UNSE | 42281105 | POTTER VALLEY P H 1105 | POTTER VALLEY P H 110564118 | 101 | 1.6451 | 43 | 44.7046 | 0.44262 | 427 | 28.3517 |  |  | CWSP | POTTER VALLEY | Mendoino | Humboldt | Northern | 5794548 | E.5034709.01.02 | 120445424 | 35226632 | CWSP - POTTER VALLEY P H 110564118 PH 2 | 8885 | 0 | 0 | 0 |  | 2020-88312 | - | - | - | 2021-03822 | [8 empty] | 0
35232651 | Top 250 Miles | 13 | MEET | No | 2021454 |  | 1.74 | 1.74 | 2021 |  |  | 0 | 0 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 4.7696 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.03 | 120529255 | 35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 9187 | 0 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0
35219286 | Top 250 Miles | 13 | MEET | No | 2021455 | 2.91 | 3.4547 | 3.4547 | 2021 |  |  | 0 | 13486.26 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.4782 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.01 | 120142352 | 35219286 | CWSP - DESCHUTES 11049718 PH1.1 | 18241 | 0 | 0 | 0 |  | 2021-03394 | 31574.4 | 5.98 | 6757905 | 2021-12071 |  |  | 15365 | 15365 | 2.91 |  |  |  | 0
35232960 | Top 250 Miles | 13 | MEET | No | 2021456 | 2.9299 | 3.0411 | 3.0411 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.3856 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.07 | 120537723 | 35232960 | CWSP - DESCHUTES 11049718 PH1.2 | 16057 | 0 | 0 | 0 |  | 2021-03394 |  |  |  | 2021-12071 |  |  | 15470 | 15470 | 2.9299
35225825 | Top 250 Miles | 13 | MEET | No | 2021457 | 1.5299 | 1.5562 | 1.5562 | 2021 |  |  | 0 | 14213.74 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 7.8734 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.02 | 120426401 | 35225825 | CWSP - DESCHUTES 11049718 PH2.1 | 8217 | 0 | 0 | 0 |  | 2021-03395 | 56126.4 | 10.63 | 9724400 | 2021-12064 | [8 empty] | 0
35232442 | Top 250 Miles | 13 | MEET | No | 2021458 | 3.1299 | 3.0778 | 3.0778 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 15.5714 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.03 | 120528704 | 35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | 16251 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0
35232443 | Top 250 Miles | 13 | MEET | No | 2021459 | 1 | 1.0356 | 1.0356 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 5.2393 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.04 | 120528712 | 35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | 5468 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0
35232444 | Top 250 Miles | 13 | MEET | No | 2021460 | 3.4701 | 3.5318 | 3.5318 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 17.8682 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.05 | 120528751 | 35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | 18648 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0
35232445 | Top 250 Miles | 13 | MEET | No | 2021461 | 2.6 | 2.6038 | 2.6038 | 2021 |  |  | 0 | 0 | UNSE | 103351104 | DESCHUTES 1104 | DESCHUTES 11049718 | 357 | 18.6049 | 48 | 151.8163 | 0.42526 | 94 | 13.1731 |  | Tier 2 | CWSP | PALO CEDRO | Shasta | North Valley | Northern | 5794554 | E.5034713.01.06 | 120528752 | 35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | 13748 | 0 | 0 | 0 |  | 2021-03395 |  |  |  | 2021-12064 | [8 empty] | 0
35219289 | Top 250 Miles | 11 | MEET | MEET | 2021462 | 57.14 | 4.3544 | 4.3544 | 2021 |  |  | 0 | 9671.99 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 20.3989 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.02 | 120142359 | 35219289 | CWSP - OREGON TRAIL 110335002 PH 1.1 | 0 | 22991 | 0 | 0 |  | 2021-05564 | 58396.8 | 11.06 | 20682782 | 2021-17990 |  |  |  | 0 | 0 |  |  |  | 0
35233947 | Top 250 Miles | 11 | MEET | No | 2021463 |  | 1.8436 | 1.8436 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 5.4088 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.38 | 120564156 | 35233947 | CWSP - OREGON TRAIL 110335002 PH 1.2 | 9734 | 0 | 0 | 0 |  | 2021-05564 |  |  |  | 2021-17990
35233948 | Top 250 Miles | 11 | MEET | MEET | 2021464 |  | 2.5871 | 2.5871 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 12.1199 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.39 | 120564181 | 35233948 | CWSP - OREGON TRAIL 110335002 PH 1.3 | 0 | 13660 | 0 | 0 |  | 2021-05564 |  |  |  | 2021-17990
35233949 | Top 250 Miles | 11 | MEET | No | 2021465 |  | 1.9769 | 1.9769 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 5.7999 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.40 | 120564182 | 35233949 | CWSP - OREGON TRAIL 110335002 PH 1.4 | 10438 | 0 | 0 | 0 |  | 2021-05564 |  |  |  | 2021-17990
35233950 | Top 250 Miles | 11 | MEET | MEET | 2021466 |  | 2.7542 | 2.7542 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 12.9025 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.41 | 120564183 | 35233950 | CWSP - OREGON TRAIL 110335002 PH 1.5 | 0 | 14542 | 0 | 0 |  | 2021-05564 |  |  |  | 2021-17990
35233951 | Top 250 Miles | 11 | MEET | No | 2021467 |  | 1.5648 | 1.5648 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 4.5908 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.42 | 120564184 | 35233951 | CWSP - OREGON TRAIL 110335002 PH 1.6 | 8262 | 0 | 0 | 0 |  | 2021-05564 |  |  |  | 2021-17990
35225826 | Top 250 Miles | 13 | MEET | No | 2021468 |  | 2.5424 | 2.5424 | 2021 |  |  | 0 | 5299.82 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 7.4591 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.03 | 120426402 | 35225826 | CWSP - OREGON TRAIL 110335002 PH 2.1 | 13424 | 0 | 0 | 0 |  | 2021-05558 | 51268.8 | 9.71 |  | 2021-13405 | [8 empty] | 0
35233952 | Top 250 Miles | 13 | MEET | No | 2021469 |  | 2.1616 | 2.1616 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 6.3417 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.08 | 120563958 | 35233952 | CWSP - OREGON TRAIL 110335002 PH 2.2 | 11413 | 0 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35233953 | Top 250 Miles | 13 | MEET | MEET | 2021470 |  | 0.84034 | 0.84034 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 3.9368 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.09 | 120563959 | 35233953 | CWSP - OREGON TRAIL 110335002 PH 2.3 | 0 | 4437 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35233955 | Top 250 Miles | 13 | MEET | MEET | 2021471 |  | 0.54924 | 0.54924 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.573 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.10 | 120564050 | 35233955 | CWSP - OREGON TRAIL 110335002 PH 2.4 | 0 | 2900 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35233957 | Top 250 Miles | 13 | MEET | MEET | 2021472 |  | 0.10208 | 0.10208 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 0.47823 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.11 | 120564051 | 35233957 | CWSP - OREGON TRAIL 110335002 PH 2.5 | 0 | 539 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35233959 | Top 250 Miles | 13 | MEET | No | 2021473 |  | 0.34602 | 0.34602 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 1.0152 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.12 | 120564052 | 35233959 | CWSP - OREGON TRAIL 110335002 PH 2.6 | 1827 | 0 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35234381 | Top 250 Miles | 13 | MEET | No | 2021474 |  | 1.5468 | 1.5468 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 4.538 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.13 | 120564055 | 35234381 | CWSP - OREGON TRAIL 110335002 PH 2.7 | 8167 | 0 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35234382 | Top 250 Miles | 13 | MEET | No | 2021475 |  | 1.5875 | 1.5875 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 4.6575 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.14 | 120564057 | 35234382 | CWSP - OREGON TRAIL 110335002 PH 2.8 | 8382 | 0 | 0 | 0 |  | 2021-05558 |  |  |  | 2021-13405
35225827 | Top 250 Miles | 13 | MEET | MEET | 2021476 |  | 0.84564 | 0.84564 | 2021 |  |  | 0 | 1258.83 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 3.9616 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.04 | 120426404 | 35225827 | CWSP - OREGON TRAIL 110335002 PH 3.1 | 0 | 4465 | 0 | 0 |  | 2021-05859 | 34636.8 | 6.56 | 8895474 | 2021-14573 | [8 empty] | 0
35233954 | Top 250 Miles | 13 | MEET | No | 2021477 |  | 0.21212 | 0.21212 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 0.62234 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.15 | 120564059 | 35233954 | CWSP - OREGON TRAIL 110335002 PH 3.2 | 1120 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35233956 | Top 250 Miles | 13 | MEET | No | 2021488 |  | 0.25455 | 0.25455 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 0.7468 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.16 | 120564070 | 35233956 | CWSP - OREGON TRAIL 110335002 PH 3.3 | 1344 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35233958 | Top 250 Miles | 13 | MEET | No | 2021489 |  | 0.20814 | 0.20814 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 0.61067 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.17 | 120564071 | 35233958 | CWSP - OREGON TRAIL 110335002 PH 3.4 | 1099 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35234380 | Top 250 Miles | 13 | MEET | No | 2021490 |  | 2.2419 | 2.2419 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 6.5773 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.18 | 120564073 | 35234380 | CWSP - OREGON TRAIL 110335002 PH 3.5 | 11837 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35234383 | Top 250 Miles | 13 | MEET | MEET | 2021491 |  | 1.1985 | 1.1985 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 5.6146 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.19 | 120564074 | 35234383 | CWSP - OREGON TRAIL 110335002 PH 3.6 | 0 | 6328 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35234384 | Top 250 Miles | 13 | MEET | No | 2021492 |  | 0.058144 | 0.058144 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 0.17059 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.20 | 120564075 | 35234384 | CWSP - OREGON TRAIL 110335002 PH 3.7 | 307 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35234385 | Top 250 Miles | 13 | MEET | No | 2021493 |  | 0.67443 | 0.67443 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 1.9787 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.21 | 120564076 | 35234385 | CWSP - OREGON TRAIL 110335002 PH 3.8 | 3561 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35234386 | Top 250 Miles | 13 | MEET | No | 2021494 |  | 0.85777 | 0.85777 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.5166 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.22 | 120564078 | 35234386 | CWSP - OREGON TRAIL 110335002 PH 3.9 | 4529 | 0 | 0 | 0 |  | 2021-05859 |  |  |  | 2021-14573
35225828 | Top 250 Miles | 11 | MEET | MEET | 2021495 |  | 2.5314 | 2.5314 | 2021 |  |  | 0 | 1212.98 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 11.8591 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.05 | 120426405 | 35225828 | CWSP - OREGON TRAIL 110335002 PH 4.1 | 0 | 13366 | 0 | 0 |  | 2021-05891 | 48470.4 | 9.18 | 11128700 | 2021-18326 | [8 empty] | 0
35234387 | Top 250 Miles | 11 | MEET | No | 2021496 |  | 0.93996 | 0.93996 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.7577 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.23 | 120564102 | 35234387 | CWSP - OREGON TRAIL 110335002 PH 4.2 | 4963 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35234388 | Top 250 Miles | 11 | MEET | No | 2021497 |  | 2.0402 | 2.0402 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 5.9855 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.24 | 120564104 | 35234388 | CWSP - OREGON TRAIL 110335002 PH 4.3 | 10772 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35234389 | Top 250 Miles | 11 | MEET | No | 2021498 |  | 0.9 | 0.9 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.6405 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.25 | 120564107 | 35234389 | CWSP - OREGON TRAIL 110335002 PH 4.4 | 4752 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35234390 | Top 250 Miles | 11 | MEET | No | 2021499 |  | 0.52008 | 0.52008 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 1.5258 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.26 | 120564108 | 35234390 | CWSP - OREGON TRAIL 110335002 PH 4.5 | 2746 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35234391 | Top 250 Miles | 11 | MEET | No | 2021500 |  | 1.26 | 1.26 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 3.6968 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.27 | 120564120 | 35234391 | CWSP - OREGON TRAIL 110335002 PH 4.6 | 6653 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35234392 | Top 250 Miles | 11 | MEET | No | 2021501 |  | 1.66 | 1.66 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 4.8703 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.28 | 120564121 | 35234392 | CWSP - OREGON TRAIL 110335002 PH 4.7 | 8765 | 0 | 0 | 0 |  | 2021-05891 |  |  |  | 2021-18326
35225829 | Top 250 Miles | 11 | MEET | No | 2021502 |  | 2.19 | 2.19 | 2021 |  |  | 0 | 785.9 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 6.4252 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.06 | 120426406 | 35225829 | CWSP - OREGON TRAIL 110335002 PH 5.1 | 11563.2 | 0 | 0 | 0 |  | 2021-05936 | 58713.6 | 11.12 |  | 2021-19142 | [8 empty] | 0
35234393 | Top 250 Miles | 11 | MEET | No | 2021503 |  | 2.42 | 2.42 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 7.1 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.29 | 120564122 | 35234393 | CWSP - OREGON TRAIL 110335002 PH 5.2 | 12777.6 | 0 | 0 | 0 |  | 2021-05936 |  |  |  | 2021-19142
35234394 | Top 250 Miles | 11 | MEET | MEET | 2021504 |  | 2.2381 | 2.2381 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 7.3721 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.30 | 120564123 | 35234394 | CWSP - OREGON TRAIL 110335002 PH 5.3 | 9451.2 | 0 | 2366 | 0 |  | 2021-05936 |  |  |  | 2021-19142
35234395 | Top 250 Miles | 11 | MEET | No | 2021505 |  | 2.71 | 2.71 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 7.9508 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.31 | 120564126 | 35234395 | CWSP - OREGON TRAIL 110335002 PH 5.4 | 14308.8 | 0 | 0 | 0 |  | 2021-05936 |  |  |  | 2021-19142
35234396 | Top 250 Miles | 11 | MEET | No | 2021506 |  | 1.69 | 1.69 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 4.9582 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.32 | 120564127 | 35234396 | CWSP - OREGON TRAIL 110335002 PH 5.5 | 8923.2 | 0 | 0 | 0 |  | 2021-05936 |  |  |  | 2021-19142
35234397 | Top 250 Miles | 11 | MEET | No | 2021507 |  | 0.72 | 0.72 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.1124 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.33 | 120564129 | 35234397 | CWSP - OREGON TRAIL 110335002 PH 5.6 | 3801.6 | 0 | 0 | 0 |  | 2021-05936 |  |  |  | 2021-19142
35219287 | Top 250 Miles | 9 | MEET | No | 2021508 |  | 2.4 | 2.4 | 2021 |  |  | 0 | 9816.7 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 7.0413 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.01 | 120142356 | 35219287 | CWSP - OREGON TRAIL 110335002 PH 6.1 | 12672 | 0 | 0 | 0 |  | 2021-06038 | 46992 | 8.9 |  | 2021-19261 |  |  |  | 0 | 0 |  |  |  | 0
35234398 | Top 250 Miles | 9 | MEET | No | 2021509 |  | 2.85 | 2.85 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 8.3615 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.34 | 120564152 | 35234398 | CWSP - OREGON TRAIL 110335002 PH 6.2 | 15048 | 0 | 0 | 0 |  | 2021-06038 |  |  |  | 2021-19261
35234399 | Top 250 Miles | 9 | MEET | MEET | 2021510 |  | 0.48 | 0.48 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 2.2487 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.35 | 120564153 | 35234399 | CWSP - OREGON TRAIL 110335002 PH 6.3 | 0 | 2534.4 | 0 | 0 |  | 2021-06038 |  |  |  | 2021-19261
35234400 | Top 250 Miles | 9 | MEET | MEET | 2021511 |  | 1.39 | 1.39 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 6.5118 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.36 | 120564154 | 35234400 | CWSP - OREGON TRAIL 110335002 PH 6.4 | 0 | 7339.2 | 0 | 0 |  | 2021-06038 |  |  |  | 2021-19261
35234401 | Top 250 Miles | 9 | MEET | MEET | 2021512 |  | 1.85 | 1.85 | 2021 |  |  | 0 | 0 | UNSE | 103521103 | OREGON TRAIL 1103 | OREGON TRAIL 110335002 | 641 | 57.1429 | 49 | 270.4028 | 0.42185 | 153 | 8.6667 |  |  | CWSP | REDDING | Shasta | North Valley | Northern | 5794555 | E.5034714.01.37 | 120564155 | 35234401 | CWSP - OREGON TRAIL 110335002 PH 6.5 | 0 | 9768 | 0 | 0 |  | 2021-06038 |  |  |  | 2021-19261
35219267 | Top 250 Miles | 9 | MEET | No | 2021513 |  | 4.27 | 4.27 | 2021 |  |  | 0 | 16443.5 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 9.9007 |  | Tier 2 & 3 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.02 | 120142033 | 35219267 | CWSP - MARIPOSA 2102440236 PH 1.1 | 22545.6 | 0 | 0 | 0 |  | 2021-01697 | 45302.4 | 8.58 | 950000 | 2021-14891 |  |  |  | 0 | 0 |  |  |  | 0
35219587 | Top 250 Miles | 9 | MEET | No | 2021514 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 6643.14 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.03 | 120165147 | 35219587 | CWSP - MARIPOSA 2102440236 PH 1.2 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 |  |  |  | 2021-14891 | [8 empty] | 0
35219588 | Top 250 Miles | 9 | MEET | No | 2021515 |  | 2.16 | 2.16 | 2021 |  |  | 0 | 5967.22 | UNSE | 254452102 | MARIPOSA 2102 | MARIPOSA 2102440236 | 38 | 4.2727 | 50 | 15.979 | 0.4205 | 157 | 5.0083 |  |  | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794552 | E.5034702.01.04 | 120165148 | 35219588 | CWSP - MARIPOSA 2102440236 PH 1.3 | 11404.8 | 0 | 0 | 0 |  | 2021-01697 |  |  |  | 2021-14891 | [8 empty] | 0
35219589 | Top 250 Miles | 13 | MEET | No | 2021516 |  | 3.03 | 3.03 | 2021 |  |  | 0 | 11088.98 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 3.1142 |  | Tier 2 | CWSP | PLATINA | Shasta | North Valley | Northern | 5794561 | E.5034719.01.01 | 120165231 | 35219589 | CWSP - WILDWOOD 11011454 | 14836.8 | 0 | 0 | 0 |  | 2021-01188 | 15048 | 2.85 | 2940110 | 2021-04308 |  |  | 14837 | 14837 | 2.81 |  |  |  | 0
35224321 | Top 250 Miles | 14 | MEET | No | 2021517 |  | 2.46 | 2.46 | 2021 |  |  | 0 | 5273.72 | ESTS | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 2.5283 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.01 | 120401277 | 35224321 | CWSP - WILDWOOD 11011454 TEHAMA CO PH 1.1 | 12988.8 | 0 | 0 | 0 |  | 2021-01193 | 26664 | 5.05 | 7710294 | 2021-04257 |  |  | 12989 | 12989 | 2.46 |  |  |  | 0
35226798 | Top 250 Miles | 13 | MEET | No | 2021518 |  | 1.72 | 1.72 | 2021 |  |  | 0 | 217.2 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 1.7678 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.02 | 120450942 | 35226798 | CWSP - WILDWOOD 11011454 TEHAMA CO PH 1.2 | 9081.6 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 9082 | 9082 | 1.7201 |  |  |  | 0
35226799 | Top 250 Miles | 13 | MEET | No | 2021519 |  | 0.19 | 0.19 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.19528 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.03 | 120450944 | 35226799 | CWSP - WILDWOOD 11011454 TEHAMA CO PH 1.3 | 1003.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 1003 | 1003 | 0.18996 |  |  |  | 0
35226900 | Top 250 Miles | 13 | MEET | No | 2021520 |  | 0.69 | 0.69 | 2021 |  |  | 0 | 0 | UNSE | 103611101 | WILDWOOD 1101 | WILDWOOD 11011454 | 31 | 7.8323 | 52 | 12.9837 | 0.41883 | 68 | 0.70917 |  | Tier 2 | CWSP | PLATINA | Tehama | North Valley | Northern | 5795128 | E.5034784.01.04 | 120450946 | 35226900 | CWSP - WILDWOOD 11011454 TEHAMA CO PH 1.4 | 3643.2 | 0 | 0 | 0 |  | 2021-01193 |  |  |  | 2021-04257 |  |  | 3643 | 3643 | 0.68996 |  |  |  | 0
35219590 | Top 250 Miles | 9 | MEET | No | 2021521 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 7182.24 | UNSE | 63591105 | VACA DIXON 1105 | VACA DIXON 1105965390 | 21 | 0.75147 | 53 | 8.6971 | 0.41415 | 91 | 5.3817 |  | Tier 2 | CWSP | VACAVILLE | Solano | Sacramento | Northern | 5794542 | E.5034704.01.02 | 120165232 | 35219590 | CWSP - VACA DIXON 1105965390 | 3960 | 0 | 0 | 0 |  | 2021-01565 | 3168 | 0.6 | 1047680 | 2021-15750 | [8 empty] | 0
35219591 | Top 250 Miles | 9 | MEET | No | 2021522 |  | 1.25 | 1.25 | 2021 |  |  | 0 | 9553.27 | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | 3.1726 |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.01 | 120173637 | 35219591 | CWSP - OLETA 1101754718 PH 1.1 | 6600 | 0 | 0 | 0 |  | 2021-08929 |  |  |  | 2021-17654 | [8 empty] | 0
35236662 | Top 250 Miles | 9 | MEET | No | 2021523 |  | 1.67 | 1.67 |  |  |  | 0 | 0 | UNSE | 163541101 | OLETA 1101 | OLETA 1101754718 | 29 | 2.8841 | 54 | 11.8066 | 0.40712 | 306 | 4.2386 |  |  | CWSP | PLYMOUTH | Amador | Stockton | Central Valley | 5794611 | E.5034721.01.02 | 120618060 | 35236662 | CWSP - OLETA 1101754718 PH 1.2 | 8817.6 | 0 | 0 | 0 |  | 2021-08929 |  |  |  | 2021-17654
35192053 | Storm Rebuild | 20 | No | No | 2021524 |  | 1.97 | -0.22 | 2021 | 2.19 |  | 2.19 | 1426116.07 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.036346 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034391.01 | 119554059 | 35192053 | STRM - OAKHURST 1103 - LR 5120 PH 1 | 10401.6 | 0 | 0 | 0 | N/A | 2021-04765 | 21965 | 4.16 | 7671845 | [9 empty] | 0 | 2021-04813 | 2021-14000 | 0 | 0 | 10401.6 | 10401.6 | 1.97 | 3249223 | 4270370 | 312.3772
35227096 | Storm Rebuild | 20 | No | No | 2021525 |  | 1.0602 | -0.029773 | 2021 | 1.09 |  | 1.09 | 502741.26 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.019561 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.01 | 120457011 | 35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 | 5598 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04843 | 2021-16689 | 0 | 0 | 5598 | 5598 | 1.0602 | 2556406 | 3296441 | 456.6642
35227201 | Storm Rebuild | 20 | No | No | 2021526 |  | 0.82481 | -0.12519 | 2021 | 0.95 |  | 0.95 | 499104.57 | CONS | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.015218 | 404 | Tier 3 | STRM | FISH CAMP | MARIPOSA | YOSEMITE | CENTRAL VALLEY | 5792082 | E.5034813.01.02 | 120457012 | 35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 | 4355 | 0 | 0 | 0 | [14 empty] | 0 | 2021-04837 |  | 0 | 0 | 4355 | 4355 | 0.82481
35228449 | Storm Rebuild | 19 | MEET | No | 2021527 | 2.89 | 2.8937 | 0.08375 | 2021 | 2.81 |  | 2.81 | 2080183.31 | DOCC | 192251102 | RIO DELL 1102 | Rio Dell 11024230 | 59 | 22.9009 | 585 | 7.9721 | 0.13512 | 1331 | 0.62455 | 3088 | Tier 2 | STRM | MYERS FLAT | HUMBOLDT | HUMBOLDT | NORTHERN | 5795392 |  | 120481753 | 35228449 | Rio Dell Storm Rebuild | 15279 | 0 | 0 | 0 | N/A | N/A | 15279 | 2.8937 | 5469187.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0 | 2021-06858 | 2021-11321 | 0 | 0 | 15279 | 15279 | 2.8937 | 9426416 | 12825799 | 616.9524
35233166 | FRRB - UG - 2021 | 14 | MEET | No | 2021528 |  | 0 |  | 2021 |  |  | 0 | 0 | UNSE | 103751102 | BIG BEND 1102 | BIG BEND 11021972 | 177 | 21.2964 | 1288 | 7.25 | 0.040961 | 1326 | #DIV/0! |  |  | FRRB | BERRY CREEK | Butte | North Valley | Northern | 5795419 | E.5034825.01.04 | 120541098 | 35233166 | FRRB - Big Bend 11021972 - B4 | 0 | 0 | 0 | 0
35114040 | In-Construction | 20 | No | No | 2022001 | 5.2 | 1.4847 | 1.4847 | 2020 | 0 |  | 0 | 1172669.53 | CONS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.043681 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785991 | E.5014745.02 | 117500499 | 35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | 7839 | 0 | 0 | 0 |  | 2018-49722 | 27456 | 5.2 | 5674800 | 2019-35977 | 0 | 0 | 7188 | 7188 | 1.3614 | 2613818.1818 |  |  | 0 | 2020-20653 | 2020-39428 | 0 | 0 | 7839 | 7839 | 1.4847 | 3107232 | 4232854 | 396.3812
35052737 | DSDD | 18 | No | No | 2022002 | 1.97 | 1.5867 | 1.5867 | 2020 | 0 |  | 0 | 105057.37 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.041798 | 12 | Tier 3 | CWSP | LONG BARN | Tuolumne | Yosemite | Central Valley | 5785238 | E.5014733.01 | 114675474 | 35052737 | CWSP-MIWUK 1701-LR8060-PH 1.1 | 8378 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8605 | 8605 | 1.6297 | 3129090.9091 |  |  | 0 | 2019-63683 | 2020-27366 | 0 | 0 | 8378 | 8378 | 1.5867 | 2060222 | 2768676 | 245.9086
35192280 | ECOP - Top 20% | 14 | MEET | MEET | 2022003 |  | 1.643 | 1.643 | 2021 |  |  | 0 | 38985.67 | UNSE | 12022212 | CLAYTON 2212 | CLAYTON 221296224 | 174 | 19.3992 | 377 | 32.6329 | 0.18755 | 281 | 2.7362 | 267 | Tier 3 | ECOP | CONCORD | Contra Costa | Diablo | Bay Area | 5792091 | E.5034400.01 | 119556070 | 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 PH1 | 0 | 8675 | 0 | 0 | 2020-77593 | 2020-77594 | 14414.4 | 2.73 | 4538638 | 2021-02769 | 0 | 8675 | 0 | 8675 | 1.643 | 3687300 |  |  | 0
35225589 | Top 50 Miles | 14 | MEET | No | 2022004 | 1.056 | 1.0983 | 1.0983 | 2021 |  |  | 0 | 644.49 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 5.6145 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.02 | 120423768 | 35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 5799 | 0 | 0 | 0 |  | 2020-81645 |  |  |  | 2021-01900 | [8 empty] | 0
35225591 | Top 50 Miles | 14 | MEET | MEET | 2022005 | 1.4156 | 1.4723 | 1.4723 | 2021 |  |  | 0 | 274.58 | UNSE | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 9.4535 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.03 | 120423769 | 35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 4527 | 0 | 3247 | 0 |  | 2020-81645 |  |  |  | 2021-01900 | [8 empty] | 0
35217268 | Top 50 Miles | 14 | MEET | MEET | 2022006 |  | 0.25795 | 0.25795 | 2021 |  |  | 0 | 13912.8 | UNSE | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 0.34672 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.01 | 120047659 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 1158 | 204 | 0 | 0 | 2020-81775 | 2020-81782 | 21436.8 | 4.06 | 6144137 | 2021-03744 |  | 9662.4 | 11774.4 | 21436.8 | 4.06 |  |  |  | 0
35224712 | Top 50 Miles | 14 | MEET | MEET | 2022007 |  | 3.2869 | 3.2869 | 2021 |  |  | 0 | 3387.63 | UNSE | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 6.3054 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.02 | 120427328 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 1222 | 16133 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0
35224713 | Top 50 Miles | 14 | MEET | MEET | 2022008 |  | 1.8655 | 1.8655 | 2021 |  |  | 0 | 2193.1 | UNSE | 102211101 | BUCKS CREEK 1101 | BUCKS CREEK 1101CB | 13 | 4.8008 | 11 | 9.5539 | 0.73491 | 200 | 3.6531 |  | Tier 2 & 3 | CWSP | BELDEN | Plumas | North Valley | Northern | 5794208 | E.5034607.01.03 | 120427329 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 160 | 9690 | 0 | 0 |  | 2020-81782 |  |  |  | 2021-03744 | [8 empty] | 0
35062375 | Top 20% MAVF CPZ | 14 | MEET | MEET | 2022009 | 1.11 | 1.0902 | 1.0902 | 2021 |  |  | 0 | 152349.65 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 2.7865 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783068 | E.5015571.01 | 115323921 | 35062375 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.1 | 0 | 5756 | 0 | 0 |  | 2018-89225 | 63518.4 | 12.03 | 13033162 | 2021-04169 | 0 | 5861 | 0 | 5861 | 1.11 | 1698679.6353 |  |  | 0
35191319 | ECOP - Top 20% | 13 | MEET | MEET | 2022010 | 1.04 | 1.1705 | 1.1705 | 2021 |  |  | 0 | 17378.26 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 2.8131 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5541305 | E.5034355.01 | 119518398 | 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH 1 | 0 | 6180 | 0 | 0 |  | 2020-76901 | 5491.2 | 1.04 | 1673104 | 2021-02773 | 0 | 5985 | 0 | 5985 | 1.1335 | 2201900 |  |  | 0
35223615 | ECOP - Top 20% | 13 | MEET | MEET | 2022011 |  | 1.6258 | 1.6258 | 2021 |  |  | 0 | 1259.57 | UNSE | 42991105 | LAS GALLINAS A 1105 | LAS GALLINAS A 110599904 | 54 | 5.5621 | 215 | 13.5032 | 0.25006 | 739 | 3.9074 | 213 | Tier 3 | ECOP | NICASIO | Marin | North Bay | Northern | 5795129 | E.5034355.02 | 120401360 | 35223615 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 PH 2 | 0 | 8584 | 0 | 0 |  | 2020-76901 | 0 | 0 | 0 | 2021-02773 | 0 | 8465 | 0 | 8465 | 1.6032 | 3288180 |  |  | 0
35227030 | ECOP - Top 20% | 13 | MEET | MEET | 2022012 |  | 1.7072 | 1.7072 | 2021 |  |  | 0 | 614.57 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 2.5275 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.29 | 120449801 | 35227030 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.5 | 2233 | 6781 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 6781 | 2233 | 9014 | 1.7072 | 2820684 | 0 | 0 | 0
35227031 | ECOP - Top 20% | 13 | MEET | MEET | 2022013 |  | 2.03 | 2.03 | 2021 |  |  | 0 | 711.77 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.0193 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.30 | 120449802 | 35227031 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 1.6 | 2534.4 | 8184 | 0 | 0 |  | 2020-78081 | 0 | 0 | 0 | 2021-04756 | 0 | 7672 | 2834 | 10506 | 1.9898 | 3192728 | 0 | 0 | 0
35192282 | ECOP - Top 20% | 13 | MEET | MEET | 2022014 |  | 2.2621 | 2.2621 | 2021 |  |  | 0 | 16995.29 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.6907 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5792098 | E.5034407.01 | 119556300 | 35192282 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.1 | 0 | 11944 | 0 | 0 | 2020-78129 | 2020-78306 | 40920 | 7.75 | 11896580 | 2021-03830 | 0 | 11944 |  | 11944 | 2.2621 | 4133200 | 0 | 0 | 0
35226621 | ECOP - Top 20% | 13 | MEET | MEET | 2022015 |  | 2.6562 | 2.6562 | 2021 |  |  | 0 | 223.35 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 110148212 | 110 | 10.6994 | 468 | 17.6327 | 0.1603 | 729 | 3.9941 | 375 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795152 | E.5034794.01.01 | 120445224 | 35226621 | ECOP - MIDDLETOWN 1101 - H16-LR48212 - PH 2.2 | 2941 | 11084 | 0 | 0 | 2020-78129 | 2020-78306 | 0 | 0 | 0 | 2021-03830 | 0 | 11084 | 2941 | 14025 | 2.6562 | 4029758 | 0 | 0 | 0
35192292 | ECOP - Top 20% | 13 | MEET | MEET | 2022016 |  | 0.95114 | 0.95114 | 2021 |  |  | 0 | 40677.1 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 1.0419 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5792094 | E.5034403.01 | 119556108 | 35192292 | ECOP - FULTON 1107 - H02-LR604 Ph 1.1 | 830 | 4192 | 0 | 0 | 2020-78732 | 2020-78779 | 19800 | 3.75 | 4686150 | 2021-02767 | 0 | 4192 | 830 | 5022 | 0.95114 | 1887200 |  |  | 0
35225594 | ECOP - Top 20% | 13 | MEET | MEET | 2022017 |  | 0.5286 | 0.5286 | 2021 |  |  | 0 | 2502.1 | UNSE | 42561107 | FULTON 1107 | FULTON 1107604 | 169 | 17.4386 | 637 | 20.5661 | 0.12169 | 641 | 0.5956 | 225 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5795144 | E.5034792.01.01 | 120424183 | 35225594 | ECOP - FULTON 1107 - H02-LR604 Ph 1.2 | 261 | 2530 | 0 | 0 |  | 2020-78779 | 0 | 0 | 0 | 2021-02767 | 0 | 2530 | 389 | 2919 | 0.55284 | 864959 |  |  | 0
35174478 | ECOP - Top 20% | 13 | MEET | MEET | 2022018 |  | 1.79 | 1.79 | 2021 |  |  | 0 | 2423.68 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.0704 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790111 | E.5033917.01 | 118913024 | 35174478 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.1 | 0 | 9451.2 | 0 | 0 | 2020-51635 | 2020-51816 | 21489.6 | 4.07 | 6162189 | 2021-04465 | 0 | 9463 | 518 | 9981 | 1.8903 | 3159460 |  |  | 0
35226857 | ECOP - Top 20% | 13 | MEET | MEET | 2022019 |  | 1.94 | 1.94 | 2021 |  |  | 0 | 1337.1 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 3.3277 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.01 | 120449200 | 35226857 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.2 | 0 | 10243.2 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 10242 | 0 | 10242 | 1.9398 | 3613740 |  |  | 0
35226858 | ECOP - Top 20% | 14 | MEET | MEET | 2022020 |  | 0.74295 | 0.74295 | 2021 |  |  | 0 | 640.2 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0502 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.02 | 120449201 | 35226858 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.3 | 1900.8 | 0 | 2022 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 2022 | 0 | 1889 | 3911 | 0.74072 | 510683 |  |  | 0
35226859 | ECOP - Top 20% | 14 | MEET | No | 2022021 |  | 0.88 | 0.88 | 2021 |  |  | 0 | 1040.86 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.94531 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.03 | 120449202 | 35226859 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.4 | 4646.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 | 0 | 0 | 4659 | 4659 | 0.88239 | 1123574 |  |  | 0
35226861 | ECOP - Top 20% | 14 | MEET | No | 2022022 |  | 0.75 | 0.75 | 2021 |  |  | 0 | 1049.68 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.80566 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.04 | 120449203 | 35226861 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.5 | 3960 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3986 | 3986 | 0.75492 | 824385 |  |  | 0
35226862 | ECOP - Top 20% | 14 | MEET | No | 2022023 |  | 0.58 | 0.58 | 2021 |  |  | 0 | 937.2 | ESTS | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.62305 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.05 | 120449204 | 35226862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 1.6 | 3062.4 | 0 | 0 | 0 |  | 2020-51816 | 0 | 0 | 0 | 2021-04465 |  | 0 | 3073 | 3073 | 0.58201 | 635558 |  |  | 0
35174501 | ECOP - Top 20% | 13 | MEET | MEET | 2022024 |  | 1.683 | 1.683 | 2021 |  |  | 0 | 22527.53 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 2.8867 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5790112 | E.5033919.01 | 118913026 | 35174501 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.1 | 0 | 8886 | 0 | 0 | 2020-53723 | 2020-53724 | 50952 | 9.65 | 16768361 | 2021-04463 | 0 | 8886 | 0 | 8886 | 1.683 | 18931272.7273 |  |  | 0
35227007 | ECOP - Top 20% | 13 | MEET | MEET | 2022025 |  | 1.1288 | 1.1288 | 2021 |  |  | 0 | 726.91 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.9362 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.19 | 120449533 | 35227007 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.2 | 0 | 5960 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 5960 | 0 | 5960 | 1.1288 | 0 |  |  | 0
35227010 | ECOP - Top 20% | 13 | MEET | No | 2022026 |  | 0.15985 | 0.15985 | 2021 |  |  | 0 | 1244.61 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.17171 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.20 | 120449536 | 35227010 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.3 | 844 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 844 | 844 | 0.15985 | 0 |  |  | 0
35227013 | ECOP - Top 20% | 13 | MEET | No | 2022027 |  | 0.026894 | 0.026894 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.02889 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.21 | 120449539 | 35227013 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.4 | 142 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 142 | 142 | 0.026894 | 0 |  |  | 0
35227015 | ECOP - Top 20% | 13 | MEET | No | 2022028 |  | 0.95758 | 0.95758 | 2021 |  |  | 0 | 296.19 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0286 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.22 | 120449710 | 35227015 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.5 | 5056 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 5056 | 5056 | 0.95758 | 0 |  |  | 0
35227018 | ECOP - Top 20% | 13 | MEET | No | 2022029 |  | 1.2 | 1.2 | 2021 |  |  | 0 | 1008.42 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.2891 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.23 | 120449711 | 35227018 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.6 | 6336 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 6336 | 6336 | 1.2 | 0 |  |  | 0
35227021 | ECOP - Top 20% | 13 | MEET | No | 2022030 |  | 0.21989 | 0.21989 | 2021 |  |  | 0 | 776.16 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.23621 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.24 | 120449712 | 35227021 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.7 | 1161 | 0 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 0 | 1161 | 1161 | 0.21989 | 0 |  |  | 0
35227025 | ECOP - Top 20% | 13 | MEET | MEET | 2022031 |  | 0.7536 | 0.7536 | 2021 |  |  | 0 | 421.64 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.0184 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.25 | 120449714 | 35227025 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.8 | 2259 | 1720 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 1720 | 2259 | 3979 | 0.7536 | 0 |  |  | 0
35234756 | ECOP - Top 20% | 13 | MEET | MEET | 2022032 |  | 2.782 | 2.782 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 4.7719 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.31 | 120580906 | 35234756 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.9 | 0 | 14689 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 14689 | 0 | 14689 | 2.782 | 0 |  |  | 0
35234758 | ECOP - Top 20% | 13 | MEET | MEET | 2022033 |  | 0.58201 | 0.58201 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.99831 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.32 | 120580957 | 35234758 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.10 | 0 | 3073 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3073 | 0 | 3073 | 0.58201 | 0 |  |  | 0
35234862 | ECOP - Top 20% | 13 | MEET | MEET | 2022034 |  | 0.079924 | 0.079924 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 0.13709 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.33 | 120580959 | 35234862 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.11 | 0 | 422 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 422 | 0 | 422 | 0.079924 | 0 |  |  | 0
35234865 | ECOP - Top 20% | 13 | MEET | MEET | 2022035 |  | 0.64754 | 0.64754 | 2021 |  |  | 0 | 0 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101548 | 298 | 27.4082 | 474 | 47.4878 | 0.15935 | 1108 | 1.1107 | 30 | Tier 3 | ECOP | MIDDLETOWN | Lake | Humboldt | Northern | 5795300 | E.5034805.01.34 | 120581001 | 35234865 | ECOP - MIDDLETOWN 1101 - H12 - LR548-PH 3.12 | 0 | 3419 | 0 | 0 | 2020-53723 | 2020-53724 | 0 | 0 | 0 | 2021-04463 | 0 | 3419 | 0 | 3419 | 0.64754 | 0 |  |  | 0
35192291 | ECOP | 13 | No | MEET | 2022036 |  | 1.0972 | 1.0972 | 2021 |  |  | 0 | 35094.18 | UNSE | 152261107 | DIAMOND SPRINGS 1107 | DIAMOND SPRINGS 11071402 | 541 | 44.1915 | 811 | 49.924 | 0.092281 | 726 | 1.1858 | 244 | Tier 3 | ECOP | PLACERVILLE | El Dorado | Sierra | Northern | 5792093 | E.5034402.01 | 119556091 | 35192291 | ECOP - DIAMOND SPRINGS 1101 - H02-LR1402 PH 1 | 521 | 5272 | 0 | 0 |  | 2020-69602 | 15100.8 | 2.86 | 3208863 | 2021-04462 | 0 | 5272 | 521 | 5793 | 1.0972 | 2442393 |  |  | 0
35191937 | ECOP | 13 | No | No | 2022037 |  | 1.4528 | 1.4528 | 2021 |  |  | 0 | 14460.77 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.61524 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5792064 | E.5034372.01 | 119553837 | 35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1 | 7671 | 0 | 0 | 0 | 2020-61147 | 2020-61154 | 17635.2 | 3.34 | 3777700 | 2021-04460 |  | 4540.8 | 13094.4 | 17635.2 | 3.34 |  |  |  | 0
35227032 | ECOP | 13 | No | No | 2022038 |  | 0.575 | 0.575 | 2021 |  |  | 0 | 557.73 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.2435 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.01 | 120449806 | 35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 2 | 3036 | 0 | 0 | 0 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0
35227033 | ECOP | 13 | No | No | 2022039 |  | 1.31 | 1.31 | 2021 |  |  | 0 | 215.33 | UNSE | 43292102 | PUEBLO 2102 | PUEBLO 2102792 | 180 | 19.3407 | 951 | 13.2101 | 0.073389 | 1012 | 0.88583 | 40 | Tier 3 | ECOP | NAPA | Napa | North Bay | Bay Area | 5795301 | E.5034806.01.02 | 120449807 | 35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 3 | 0 | 0 | 0 | 6917 | 2020-61147 | 2020-61154 |  |  |  | 2021-04460 | [8 empty] | 0
35219093 | Top 50 Miles | 13 | MEET | MEET | 2022040 | 1.14 | 1.14 | 1.14 | 2021 |  |  | 0 | 8259.44 | ESTS | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.0351 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.01 | 120141622 | 35219093 | CWSP - TIDEWATER 210614072 PH 1 | 0 | 6019.2 | 0 | 0 |  | 2020-87771 | 25396.8 | 4.81 | 8092656 | 2021-08732 | 0 | 6019.2 | 0 | 6019.2 | 1.14 |  |  |  | 0
35231543 | Top 50 Miles | 13 | MEET | MEET | 2022041 | 1.3 | 1.3 | 1.3 | 2021 |  |  | 0 | 1620.67 | UNSE | 14652106 | TIDEWATER 2106 | TIDEWATER 210614072 | 30 | 3.6652 | 18 | 19.5994 | 0.65331 | 59 | 6.8821 |  | Tier 2 | CWSP | CONCORD | Contra Costa | Diablo | Bay Area | 5794540 | E.5034692.01.02 | 120504099 | 35231543 | CWSP - TIDEWATER 210614072 PH 2 | 0 | 6864 | 0 | 0 |  | 2020-87771 |  |  |  | 2021-08732 | 0 | 6864 | 0 | 6864 | 1.3 |  |  |  | 0
35217273 | Top 50 Miles | 13 | MEET | MEET | 2022042 | 1.1133 | 1.1055 | 1.1055 | 2021 |  |  | 0 | 14860.19 | UNSE | 42871101 | UPPER LAKE 1101 | UPPER LAKE 1101CB | 3 | 1.1133 | 6 | 3.7676 | 1.2559 | 90 | 3.6826 |  | Tier 2 | CWSP | UPPER LAKE | Lake | North Coast | Northern | 5794203 | E.5034612.01.01 | 120048019 | 35217273 | CWSP - UPPER LAKE 1101 CB | 240 | 0 | 5596.8 | 0 | 2020-81991 | 2020-82007 | 211.2 | 0.04 | 970000 | 2021-03151 | 5596.8 |  | 211.2 | 5808 | 1.1 |  |  |  | 0
35217272 | Top 50 Miles | 13 | MEET | MEET | 2022043 | 0.3 | 0.34053 | 0.34053 | 2021 |  |  | 0 | 19621.5 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 2.1677 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.01 | 120048018 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1 | 94 | 1704 | 0 | 0 | 2020-81561 | 2020-82753 | 42926.4 | 8.13 | 22711843 | 2021-03825 |  | 34161.6 | 8764.8 | 42926.4 | 8.13 |  | 41.75 | 31200 | 747.3054
35226628 | Top 50 Miles | 13 | MEET | MEET | 2022044 | 0.82 | 0.81913 | 0.81913 | 2021 |  |  | 0 | 423.02 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 5.3182 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.03 | 120445377 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 3 | 0 | 4325 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0
35226629 | Top 50 Miles | 13 | MEET | MEET | 2022045 | 4.5 | 4.6972 | 4.6972 | 2021 |  |  | 0 | 423.02 | UNSE | 103451101 | KESWICK 1101 | KESWICK 11011586 | 39 | 7.4478 | 7 | 48.8434 | 1.2524 | 233 | 30.4963 |  | Tier 3 | CWSP | REDDING | Shasta | North Valley | Northern | 5794204 | E.5034611.01.04 | 120445378 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 4 | 0 | 24801 | 0 | 0 | 2020-81561 | 2020-82753 | - | - | 0 | 2021-03825 | [6 empty] | 0 | 0 | 0
35217269 | Top 50 Miles | 13 | MEET | MEET | 2022046 | 0.1288 | 0.52083 | 0.52083 | 2021 |  |  | 0 | 13455.36 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.8658 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.01 | 120048011 | 35217269 | SH - MIDDLETOWN 1102 LR 302610 PH 1 | 630 | 2120 | 0 | 0 | 2020-81207 | 2020-81139 | 26294.4 | 4.98 | 6542572 | 2021-04671 |  | 9240 | 17054.4 | 26294.4 | 4.98 |  | 39.7 | 22200 | 559.194
35226819 | Top 50 Miles | 13 | MEET | No | 2022047 | 0.32668 | 1.321 | 1.321 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 8.4527 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.02 | 120456652 | 35226819 | SH - MIDDLETOWN 1102 LR 302610 PH 2 | 6975 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35227160 | Top 50 Miles | 13 | MEET | MEET | 2022048 | 0.70305 | 2.843 | 2.843 | 2021 |  |  | 0 | 30.35 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 28.9198 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.03 | 120456653 | 35227160 | SH - MIDDLETOWN 1102 LR 302610 PH 3 | 176 | 14835 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35227161 | Top 50 Miles | 13 | MEET | No | 2022049 | 0.18069 | 0.73068 | 0.73068 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.6753 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.04 | 120456654 | 35227161 | SH - MIDDLETOWN 1102 LR 302610 PH 4 | 3858 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35227162 | Top 50 Miles | 13 | MEET | MEET | 2022050 | 0.10332 | 0.4178 | 0.4178 | 2021 |  |  | 0 | 30.35 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 4.2687 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.05 | 120456655 | 35227162 | SH - MIDDLETOWN 1102 LR 302610 PH 5 | 0 | 2206 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35227163 | Top 50 Miles | 13 | MEET | No | 2022051 | 0.10168 | 0.41117 | 0.41117 | 2021 |  |  | 0 | 0 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 2.6309 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.06 | 120456657 | 35227163 | SH - MIDDLETOWN 1102 LR 302610 PH 6 | 2171 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35227164 | Top 50 Miles | 13 | MEET | No | 2022052 | 0.13821 | 0.5589 | 0.5589 | 2021 |  |  | 0 | 223.35 | UNSE | 43141102 | MIDDLETOWN 1102 | MIDDLETOWN 1102302610 | 53 | 4.7058 | 8 | 48.565 | 0.91632 | 121 | 3.5762 |  | Tier 2 | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794207 | E.5034608.01.07 | 120456658 | 35227164 | SH - MIDDLETOWN 1102 LR 302610 PH 7 | 2951 | 0 | 0 | 0 |  | 2020-81139 |  |  |  | 2021-04671 | [6 empty] | 0 | 0 | 0
35217270 | Top 50 Miles | 14 | MEET | No | 2022053 | 0.55395 | 0.57614 | 0.57614 | 2021 |  |  | 0 | 17137.88 | ESTS | 43311101 | KONOCTI 1102 | KONOCTI 1102965078 | 59 | 6.2704 | 9 | 51.7008 | 0.87629 | 220 | 2.9452 |  | Tier 3 | CWSP | KELSEYVILLE | Lake | Humboldt | Northern | 5794206 | E.5034609.01.01 | 120048013 | 35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 3042 | 0 | 0 | 0 | 2020-81626 | 2020-81645 | 11035.2 | 2.09 | 2458800 | 2021-01900 |  |  | 11035.2 | 11035.2 | 2.09 |  |  |  | 0
35217271 | Top 50 Miles | 13 | MEET | MEET | 2022054 |  | 2.8496 | 2.8496 | 2021 |  |  | 0 | 32521.76 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 15.4448 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.01 | 120048017 | 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 0 | 15046 | 0 | 0 |  | 2020-87776 | 38016 | 7.2 | 11000000 | 2021-05676 | 0 | 15046 | 0 | 15046 | 2.8496 | 5487320 | 34.46 | 31600 | 917.0052
35227864 | Top 50 Miles | 13 | MEET | MEET | 2022055 |  | 1.8392 | 1.8392 | 2021 |  |  | 0 | 288.15 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.9684 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.11 | 120462234 | 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 0 | 9711 | 0 | 0 |  | 2020-87776 |  |  |  | 2021-05676 | 0 | 9711 | 0 | 9711 | 1.8392 | 3498820 | 0 | 0 | 0
35220895 | Top 50 Miles | 13 | MEET | MEET | 2022056 |  | 2.1489 | 2.1489 | 2021 |  |  | 0 | 14298.74 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 11.2106 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.02 | 120221891 | 35220895 | CWSP - MIDDLETOWN 1103 LR 830 PH 2.1 | 1137 | 10209 | 0 | 0 |  | 2020-87780 | 48681.6 | 9.22 | 7050000 | 2021-06302 | 0 | 10209 | 1137 | 11346 | 2.1489 | 3553334 | 19.39 | 18300 | 943.7855
35228186 | Top 50 Miles | 13 | MEET | MEET | 2022057 |  | 1.4847 | 1.4847 | 2021 |  |  | 0 | 288.15 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.0468 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.15 | 120475322 | 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH 2.2 | 0 | 7839 | 0 | 0 |  | 2020-87780 |  |  |  | 2021-06302 | 0 | 7839 | 0 | 7839 | 1.4847 | 2916780 | 0 | 0 | 0
35220896 | Top 50 Miles | 13 | MEET | MEET | 2022058 |  | 0.2803 | 0.2803 | 2021 |  |  | 0 | 7574.12 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 1.5192 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.03 | 120222356 | 35220896 | CWSP - MIDDLETOWN 1103 LR 830 PH 3.1 | 0 | 1480 | 0 | 0 |  | 2020-87782 | 19219.2 | 3.64 | 3976000 | 2021-04672 | 0 | 1480 | 0 | 1480 | 0.2803 | 653600 | 21.1 | 23300 | 1104.2654
35227165 | Top 50 Miles | 13 | MEET | MEET | 2022059 |  | 1.0112 | 1.0112 | 2021 |  |  | 0 | 482.55 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 5.4805 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.04 | 120456740 | 35227165 | CWSP - MIDDLETOWN 1103 LR 830 PH 3.2 | 0 | 5339 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 5339 | 0 | 5339 | 1.0112 | 1743480 | 0 | 0 | 0
35227167 | Top 50 Miles | 13 | MEET | MEET | 2022060 |  | 1.7975 | 1.7975 | 2021 |  |  | 0 | 288.15 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 9.7426 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.05 | 120456741 | 35227167 | CWSP - MIDDLETOWN 1103 LR 830 PH 3.3 | 0 | 9491 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 9491 | 0 | 9491 | 1.7975 | 3107120 | 0 | 0 | 0
35227168 | Top 50 Miles | 13 | MEET | MEET | 2022061 |  | 1.5741 | 1.5741 | 2021 |  |  | 0 | 288.15 | UNSE | 43141103 | MIDDLETOWN 1103 | MIDDLETOWN 1103830 | 212 | 27.7328 | 14 | 151.8291 | 0.71618 | 102 | 8.5313 |  |  | CWSP | MIDDLETOWN | Lake | Humboldt | Northern | 5794205 | E.5034610.01.06 | 120456742 | 35227168 | CWSP - MIDDLETOWN 1103 LR 830 PH 3.4 | 0 | 8311 | 0 | 0 |  | 2020-87782 |  |  |  | 2021-04672 | 0 | 8311 | 0 | 8311 | 1.5741 | 2764520 | 0 | 0 | 0
35062374 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022062 | 1.56 | 1.5352 | 1.5352 | 2021 |  |  | 0 | 105658.14 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 3.9241 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783067 | E.5015572.01 | 115323920 | 35062374 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.1 | 0 | 8106 | 0 | 0 |  | 2018-89221 | 45038.4 | 8.53 | 9171850 | 2021-04171 | 0 | 8237 | 0 | 8237 | 1.56 | 2427043.6218 |  |  | 0
35231608 | Top 20% MAVF CPZ | 14 | MEET | No | 2022063 | 0.32992 | 0.16212 | 0.16212 | 2021 |  |  | 0 | 1260.4 | ESTS | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 0.25951 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.12 | 120504095 | 35231608 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 1.6 | 856 | 0 | 0 | 0 |  | 2018-89221 |  |  |  | 2021-04171 | 0 | 1742 | 0 | 1742 | 0.32992 | 513282.7473 |  |  | 0
35226849 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022064 | 1.7799 | 1.7833 | 1.7833 | 2021 |  |  | 0 | 2420.8 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 21099372 | 190 | 17.8687 | 227 | 46.1342 | 0.24281 | 487 | 4.5583 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5795299 | E.5034804.01.04 | 120449142 | 35226849 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 2.3 | 0 | 9416 | 0 | 0 |  | 2018-89225 |  |  |  | 2021-04169 | 0 | 9398 | 0 | 9398 | 1.7799 | 2723799.8997 |  |  | 0
35062376 | Top 20% MAVF CPZ | 13 | MEET | MEET | 2022065 | 2.53 | 4.3231 | 4.3231 | 2021 |  |  | 0 | 23924.79 | UNSE | 153652109 | SHINGLE SPRINGS 2109 | SHINGLE SPRINGS 210935598 | 122 | 10.847 | 159 | 33.9836 | 0.27855 | 443 | 13.4088 | 554 | Tier 3 | PRE | SHINGLE SPRINGS | El Dorado | Sierra | Northern | 5783069 | E.5015570.01 | 115323922 | 35062376 | CWSP - SHINGLE SPRINGS 2109-LR 9372-PH 3.1 | 0 | 22826 | 0 | 0 |  | 2018-89227 | 58080 | 11 | 11965840 | 2021-05102 | 0 | 13358.4 | 0 | 13358.4 | 2.53 | 4751652.1664 |  |  | 0
35219096 | Top 250 Miles | 13 | MEET | MEET | 2022066 |  | 1.67 | 1.67 | 2021 |  |  | 0 | 7802.49 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 5.297 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.01 | 120141671 | 35219096 | CWSP - KIRKER 2104442850 PH 1 | 0 | 8817.6 | 0 | 0 |  | 2021-01226 | 9240 | 1.75 | 4945020 | 2021-06017 |  |  |  | 0 | 0 |  |  |  | 0
35227655 | Top 250 Miles | 13 | MEET | No | 2022067 |  | 3.77 | 3.77 | 2021 |  |  | 0 | 339.39 | UNSE | 14452104 | KIRKER 2104 | KIRKER 2104442850 | 30 | 5.7542 | 21 | 18.4361 | 0.61454 | 21 | 7.4888 |  | Tier 2 | CWSP | PITTSBURG | Contra Costa | Diablo | Bay Area | 5794544 | E.5034694.01.02 | 120462115 | 35227655 | CWSP - KIRKER 2104442850 PH 2 | 19905.6 | 0 | 0 | 0 |  | 2021-01226 |  |  |  | 2021-06017 | [8 empty] | 0
35226700 | Top 250 Miles | 13 | MEET | MEET | 2022068 | 0.46 | 0.45758 | 0.45758 | 2021 |  |  | 0 | 0 | UNSE | 102911109 | WYANDOTTE 1109 | WYANDOTTE 110932586 | 15 | 1.3417 | 29 | 7.9481 | 0.52987 | 260 | 2.6834 |  | Tier 2 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543352 | E.5034802.01.02 | 120447112 | 35226700 | CWSP - WYANDOTTE 110932586 PH 2 | 0 | 2416 | 0 | 0 |  | 2021-01235 |  |  |  | 2021-04349 | [6 empty] | 0 | 0 | 0
35219281 | Top 250 Miles | 13 | MEET | MEET | 2022069 |  | 2.5 | 2.5 | 2021 |  |  | 0 | 13199.62 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 10.9428 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.01 | 120142240 | 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.1 | 0 | 13200 | 0 | 0 |  | 2021-00875 | 30940.8 | 5.86 | 8236794 | 2021-10593 |  |  |  | 0 | 0 |  |  |  | 0
35232650 | Top 250 Miles | 13 | MEET | MEET | 2022070 |  | 1.71 | 1.71 | 2021 |  |  | 0 | 0 | UNSE | 152282101 | MOUNTAIN QUARRIES 2101 | MOUNTAIN QUARRIES 21016953 | 58 | 5.7104 | 45 | 25.2473 | 0.4353 | 135 | 7.485 |  |  | CWSP | COOL | El Dorado | Sierra | Northern | 5794551 | E.5034710.01.02 | 120529254 | 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 0 | 9029 | 0 | 0 |  | 2021-00875 |  |  |  | 2021-10593 | [8 empty] | 0
35238567 | Top 250 Miles | 2 | MEET | No |  |  | 0 | [6 empty] | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210197142 | 40 | 4.6029 | 36 | 18.8487 | 0.47122 | 66 | #DIV/0! |  | Tier 2 | CWSP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5794541 | E.5034703.01.04 | 120659911 | 35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | 0 | 0 | 0 | 0
35056733 | PSS Approved | 18 | No | No |  |  | 2.13 | 2.13 |  |  |  | 0 | 563675.92 | PEND | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.17548 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782532 | E.5015417.01 | 114987201 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 11246.4 | 0 | 0 | 0 |  | 2018-78760 | 27482.4 | 5.205 | 5577870 | 2019-32231 | 0 | 0 | 11246.4 | 11246.4 | 2.13 | 4089600 |  |  |  | 2020-50008 | 2019-55678 | [6 empty] | 2020-33819
35109541 | PSS Approved | 14 | No | No |  |  | 2.67 | 2.67 |  |  |  | 0 | 518321.93 | ESTS | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.21997 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5785513 | E.5015417.03 | 117348508 | 35109541 | CWSP - EL DORADO 2101 - LR19752 - PH 1.3 | 14097.6 | 0 | 0 | 0 |  | 2018-78760 | 27482.4 | 5.205 | 5577870 | 2019-32231 | 0 | 0 | 14097.6 | 14097.6 | 2.67 | 5126400 |  |  |  | 2019-67211
35057010 | PSS Approved | 14 | No | No |  |  | 1.31 | 1.31 |  |  |  | 0 | 306863.36 | ESTS | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.10793 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782533 | E.5015416.01 | 114987251 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 57446 | 0 | 0 | 0 |  | 2018-78870 | 9556.8 | 1.81 | 1856290 | 2019-52013 | 0 | 0 | 57446 | 57446 | 10.8799 | 20889454.5455 |  |  |  | 2020-60830 | [7 empty] | 2020-35209
35109546 | PSS Approved | 15 | No | No |  |  | 2.77 | 2.77 |  |  |  | 0 | 522531 | ADER | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.22821 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5785517 | E.5015416.03 | 117349071 | 35109546 | CWSP - EL DORADO 2101 - 19752 - PH 2.3 | 14625 | 0 | 0 | 0 |  | 2018-78870 | 9556.8 | 1.81 | 1856290 | 2019-52013 | 0 | 0 | 14625.6 | 14625.6 | 2.77 | 5318400 |  |  |  | 2020-61719
35057018 | PSS Approved | 18 | No | MEET |  |  | 2.01 | 2.01 |  |  |  | 0 | 235256.92 | PEND | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.24131 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782535 | E.5015414.01 | 114987363 | 35057018 | CWSP - EL DORADO 2101 - LR19752 - PH4.1 | 507 | 11379 | 0 | 0 |  | 2018-78881 | 37118.4 | 7.03 | 7593680 | 2019-32237 | 0 | 11379 | 507 | 11886 | 2.2511 | 9246720 |  |  |  | 2019-54822 | [7 empty] | 2020-35302
Note on AL255: [REDACTED]: Suborder table states this also includes .4 miles of bare wire. Should total be .8 miles?

## conductor_pz_summary_hftd_23_re
PZ_idx | circuit_protection_zone_id | feeder_id | feeder_name | device_operating_number | hftd_23_primary_length_under_1km | primary_length_m | primary_length_m_hftd_23 | Miles | pixel_count | mean_ignition_probability | ignition_rank | mean_mavf_core | mavf_consequence_rank | mean_mavf_core_risk | Total Risk Value | mean_mavf_core_risk_rank | kpmg_Consolidated Risk Score | KPMG_rank
10544 | OREGON TRAIL 1103CUS391 | 103521103 | OREGON TRAIL 1103 | CUS391 | TRUE | 36.3577 | 36.3577 | 0.022596 | 1 | 0.00039685 | 69 | 7972.4858 | 5 | 3.1639 | 3.1639 | 1 |  | 3570
11024 | CALPINE 1144276-G | 48011144 | CALPINE 1144 | 276-G | TRUE | 23.7478 | 23.7478 | 0.014759 | 1 | 0.00025382 | 208 | 7401.5283 | 7 | 1.8786 | 1.8786 | 2 | 0.16 | 1261
9665 | MARIPOSA 210190130 | 254452101 | MARIPOSA 2101 | 90130 | TRUE | 151.1499 | 151.1499 | 0.09394 | 1 | 0.00016255 | 619 | 10411.5469 | 1 | 1.6924 | 1.6924 | 3 | 2.44 | 603
9783 | SHEPHERD 2111688294 | 252062111 | SHEPHERD 2111 | 688294 | TRUE | 24.3604 | 24.3604 | 0.01514 | 1 | 0.0001714 | 553 | 8415.9766 | 3 | 1.4425 | 1.4425 | 4 |  | 3420
10354 | MIDDLETOWN 1103CB | 43141103 | MIDDLETOWN 1103 | CB | TRUE | 289.8399 | 85.2366 | 0.052975 | 4 | 0.00035401 | 88 | 3206.0204 | 240 | 1.3006 | 5.2026 | 5 | 0.29 | 1032
10600 | UPPER LAKE 1101CB | 42871101 | UPPER LAKE 1101 | CB | FALSE | 1791.2622 | 1791.2622 | 1.1133 | 3 | 0.0002511 | 214 | 4819.6954 | 90 | 1.2559 | 3.7676 | 6 | 0.09 | 1534
8894 | KESWICK 11011586 | 103451101 | KESWICK 1101 | 1586 | FALSE | 11983.5348 | 11983.5348 | 7.4478 | 39 | 0.00044628 | 48 | 3225.6011 | 233 | 1.2524 | 48.8434 | 7 | 0.24 | 1102
6776 | MIDDLETOWN 1102302610 | 43141102 | MIDDLETOWN 1102 | 302610 | FALSE | 9188.9357 | 7571.5921 | 4.7058 | 53 | 0.00021011 | 357 | 4327.9371 | 121 | 0.91632 | 48.565 | 8 |  | 3061
2373 | KONOCTI 1102965078 | 43311102 | KONOCTI 1102 | 965078 | FALSE | 11264.1399 | 10089.0761 | 6.2704 | 59 | 0.00026416 | 185 | 3338.3605 | 220 | 0.87629 | 51.7008 | 9 |  | 2774
5527 | MARIPOSA 2102241564 | 254452102 | MARIPOSA 2102 | 241564 | FALSE | 1774.1526 | 1146.9072 | 0.71281 | 14 | 0.0001265 | 1073 | 6191.5313 | 26 | 0.77248 | 10.8148 | 10 |  | 2961
7968 | BUCKS CREEK 1101CB | 102211101 | BUCKS CREEK 1101 | CB | FALSE | 7724.4676 | 7724.4676 | 4.8008 | 13 | 0.00026518 | 181 | 3512.0536 | 200 | 0.73491 | 9.5539 | 11 | 0.13 | 1365
10918 | DEL MAR 2109378446 | 152582109 | DEL MAR 2109 | 378446 | TRUE | 173.2196 | 157.9488 | 0.098166 | 3 | 0.00015629 | 683 | 4122.2296 | 142 | 0.73151 | 2.1945 | 12 |  | 3619
6966 | MIDDLETOWN 1102CB | 43141102 | MIDDLETOWN 1102 | CB | TRUE | 1420.4117 | 752.0336 | 0.46739 | 12 | 0.00032056 | 109 | 1676.5244 | 530 | 0.72481 | 8.6977 | 13 | 0.71 | 802
3511 | MIDDLETOWN 1103830 | 43141103 | MIDDLETOWN 1103 | 830 | FALSE | 62803.2175 | 44622.1036 | 27.7328 | 212 | 0.00015679 | 675 | 4619.5228 | 102 | 0.71618 | 151.8291 | 14 | 0.14 | 1322
9537 | POSO MOUNTAIN 2104CB | 253642104 | POSO MOUNTAIN 2104 | CB | FALSE | 12231.0905 | 8613.688 | 5.3534 | 38 | 0.00011189 | 1370 | 5318.8037 | 51 | 0.70423 | 26.7607 | 15 | 0.04 | 2163
10827 | INDIAN FLAT 11044440 | 252691104 | INDIAN FLAT 1104 | 4440 | TRUE | 376.2849 | 376.2849 | 0.23386 | 4 | 0.00015164 | 724 | 3234.1311 | 230 | 0.68656 | 2.7463 | 16 | 1.05 | 722
10242 | ELK CREEK 1101CB | 102781101 | ELK CREEK 1101 | CB | TRUE | 135.534 | 135.534 | 0.084235 | 1 | 9.9283e-05 | 1662 | 6756.3685 | 11 | 0.67079 | 0.67079 | 17 | 2.37 | 609
5791 | TIDEWATER 210614072 | 14652106 | TIDEWATER 2106 | 14072 | FALSE | 6206.8729 | 5897.3117 | 3.6652 | 30 | 0.0001306 | 999 | 5236.689 | 59 | 0.65331 | 19.5994 | 18 | 0.05 | 2003
10735 | HARTLEY 1101980662 | 43211101 | HARTLEY 1101 | 980662 | TRUE | 366.2635 | 366.2635 | 0.22763 | 3 | 0.00014325 | 821 | 4824.4797 | 89 | 0.64187 | 1.9256 | 19 |  | 3599
10532 | VACA DIXON 1101126774 | 63591101 | VACA DIXON 1101 | 126774 | FALSE | 1267.3386 | 1267.3386 | 0.78766 | 11 | 9.3598e-05 | 1808 | 6310.2508 | 24 | 0.62029 | 6.8232 | 20 |  | 3568
10277 | KIRKER 2104442850 | 14452104 | KIRKER 2104 | 442850 | FALSE | 9258.545 | 9258.545 | 5.7542 | 30 | 9.1768e-05 | 1852 | 6349.6612 | 21 | 0.61454 | 18.4361 | 21 | 0.08 | 1644
8742 | COARSEGOLD 2104CB | 254432104 | COARSEGOLD 2104 | CB | FALSE | 3906.143 | 3906.143 | 2.4277 | 27 | 0.00013159 | 989 | 4767.3932 | 95 | 0.59573 | 16.0848 | 22 | 2.54 | 600
8905 | MIDDLETOWN 1101118494 | 43141101 | MIDDLETOWN 1101 | 118494 | FALSE | 1737.509 | 1714.9565 | 1.0659 | 12 | 0.00012542 | 1091 | 4982.7835 | 79 | 0.58092 | 6.971 | 23 |  | 3276
10515 | STAFFORD 1102784704 | 43201102 | STAFFORD 1102 | 784704 | TRUE | 43.8835 | 43.8835 | 0.027274 | 1 | 0.00019096 | 437 | 2953.5029 | 279 | 0.564 | 0.564 | 24 | 1.81 | 641
10181 | PEABODY 2108113684 | 63642108 | PEABODY 2108 | 113684 | TRUE | 748.9574 | 590.6521 | 0.36709 | 4 | 9.2988e-05 | 1823 | 6848.1417 | 10 | 0.55276 | 2.211 | 25 |  | 3509
7688 | PEABODY 2106250154 | 63642106 | PEABODY 2106 | 250154 | TRUE | 458.5489 | 458.5489 | 0.28499 | 4 | 0.00011419 | 1315 | 5210.7292 | 61 | 0.55243 | 2.2097 | 26 |  | 3150
7743 | HIGHLANDS 1102628 | 43361102 | HIGHLANDS 1102 | 628 | FALSE | 22883.905 | 22883.905 | 14.2224 | 51 | 0.00010064 | 1633 | 5903.6105 | 33 | 0.5487 | 27.9838 | 27 | 5.08 | 496
6480 | TASSAJARA 21123202 | 14662112 | TASSAJARA 2112 | 3202 | TRUE | 630.3021 | 630.3021 | 0.39174 | 9 | 8.3995e-05 | 2093 | 6312.7784 | 23 | 0.53731 | 4.8358 | 28 | 9.63 | 406
10043 | WYANDOTTE 110932586 | 102911109 | WYANDOTTE 1109 | 32586 | FALSE | 2375.6773 | 2158.8587 | 1.3417 | 15 | 0.00014236 | 834 | 3072.9006 | 260 | 0.52987 | 7.9481 | 29 | 1.13 | 712
10052 | POSO MOUNTAIN 2103CB | 253642103 | POSO MOUNTAIN 2103 | CB | FALSE | 3746.9222 | 3746.9222 | 2.3287 | 10 | 5.421e-05 | 2939 | 9615.8541 | 2 | 0.51619 | 5.1619 | 30 | 0.05 | 1951
10924 | CALPINE 1146200-G | 48011146 | CALPINE 1146 | 200-G | TRUE | 13.7161 | 13.7161 | 0.0085246 | 1 | 0.00015982 | 645 | 3189.8253 | 242 | 0.50979 | 0.50979 | 31 | 18.16 | 324
11090 | CALPINE 1146394G | 48011146 | CALPINE 1146 | 394G | TRUE | 18.1683 | 18.1683 | 0.011292 | 1 | 0.00015982 | 646 | 3189.8253 | 243 | 0.50979 | 0.50979 | 32 | 18.15 | 325
4828 | CRESTA 1101546650 | 102251101 | CRESTA 1101 | 546650 | FALSE | 1443.177 | 1443.177 | 0.89694 | 6 | 0.00052979 | 27 | 978.3256 | 845 | 0.50291 | 3.0174 | 33 |  | 2920
9923 | CLOVERDALE 110247214 | 42821102 | CLOVERDALE 1102 | 47214 | TRUE | 43.972 | 43.972 | 0.027329 | 1 | 5.8357e-05 | 2823 | 8298.4728 | 4 | 0.48427 | 0.48427 | 34 | 2.46 | 602
8034 | MARIPOSA 2102CB | 254452102 | MARIPOSA 2102 | CB | FALSE | 8571.1084 | 8453.5074 | 5.2539 | 31 | 0.00011156 | 1382 | 3466.6155 | 205 | 0.47165 | 14.6212 | 35 | 0.06 | 1807
7873 | MARIPOSA 210197142 | 254452101 | MARIPOSA 2101 | 97142 | FALSE | 7406.0615 | 7406.0615 | 4.6029 | 40 | 0.00010428 | 1545 | 5130.9585 | 66 | 0.47122 | 18.8487 | 36 | 0.05 | 1966
4526 | VACA DIXON 110540092 | 63591105 | VACA DIXON 1105 | 40092 | FALSE | 68288.9427 | 37272.9556 | 23.1653 | 464 | 0.00010079 | 1627 | 4668.9585 | 100 | 0.46772 | 217.022 | 37 | 5.23 | 493
2215 | MIDDLETOWN 1101481876 | 43141101 | MIDDLETOWN 1101 | 481876 | FALSE | 2559.0375 | 1373.1162 | 0.8534 | 14 | 8.3175e-05 | 2127 | 5568.7809 | 46 | 0.46769 | 6.5476 | 38 |  | 2766
9655 | VOLTA 110149742 | 102541101 | VOLTA 1101 | 49742 | FALSE | 5593.8568 | 5593.8568 | 3.4766 | 28 | 5.8016e-05 | 2835 | 7932.3948 | 6 | 0.46433 | 13.0013 | 39 | 0.05 | 1993
10699 | SUNOL 110148180 | 14241101 | SUNOL 1101 | 48180 | TRUE | 21.1502 | 21.1502 | 0.013145 | 2 | 8.1559e-05 | 2167 | 5130.0926 | 67 | 0.46103 | 0.92206 | 40 | 0.05 | 1938
7414 | PUTAH CREEK 110246012 | 63681102 | PUTAH CREEK 1102 | 46012 | FALSE | 4834.6736 | 1025.1447 | 0.63713 | 38 | 9.4944e-05 | 1768 | 4755.8708 | 96 | 0.45557 | 17.3115 | 41 |  | 3124
4076 | VACAVILLE 11046542 | 63601104 | VACAVILLE 1104 | 6542 | FALSE | 23588.1989 | 23588.1989 | 14.6602 | 140 | 0.00010109 | 1623 | 4849.1896 | 86 | 0.44642 | 62.4985 | 42 | 0.1 | 1469
7056 | POTTER VALLEY P H 110564118 | 42281105 | POTTER VALLEY P H 1105 | 64118 | FALSE | 15416.9418 | 2646.9433 | 1.6451 | 101 | 0.00019755 | 406 | 2096.5335 | 427 | 0.44262 | 44.7046 | 43 | 0.02 | 2515
10934 | POINT MORETTI 1101CB | 82931101 | POINT MORETTI 1101 | CB | TRUE | 20.574 | 20.574 | 0.012787 | 1 | 0.00031529 | 111 | 1402.4592 | 637 | 0.44218 | 0.44218 | 44 | 0.04 | 2165
5032 | MOUNTAIN QUARRIES 21016953 | 152282101 | MOUNTAIN QUARRIES 2101 | 6953 | FALSE | 9187.973 | 9187.973 | 5.7104 | 58 | 0.00011159 | 1378 | 4228.1533 | 135 | 0.4353 | 25.2473 | 45 | 4.2 | 525
9729 | BRENTWOOD 210596324 | 14592105 | BRENTWOOD 2105 | 96324 | TRUE | 775.7684 | 775.7684 | 0.48214 | 6 | 0.00013262 | 970 | 3560.1407 | 193 | 0.4317 | 2.5902 | 46 | 0.03 | 2285
6662 | NORTH DUBLIN 2101CB | 14052101 | NORTH DUBLIN 2101 | CB | FALSE | 2942.9352 | 2836.5864 | 1.7629 | 23 | 0.00018049 | 510 | 2272.276 | 388 | 0.42859 | 9.8576 | 47 | 0.07 | 1708
1690 | DESCHUTES 11049718 | 103351104 | DESCHUTES 1104 | 9718 | FALSE | 56853.1165 | 29935.2858 | 18.6049 | 357 | 8.8629e-05 | 1967 | 4802.059 | 94 | 0.42526 | 151.8163 | 48 | 0.07 | 1758
193 | OREGON TRAIL 110335002 | 103521103 | OREGON TRAIL 1103 | 35002 | FALSE | 91942.988 | 91942.988 | 57.1429 | 641 | 0.00011631 | 1264 | 3934.2214 | 153 | 0.42185 | 270.4028 | 49 | 0.4 | 943
7274 | MARIPOSA 2102440236 | 254452102 | MARIPOSA 2102 | 440236 | FALSE | 6874.8043 | 6874.8043 | 4.2727 | 38 | 0.00016814 | 575 | 3899.3651 | 157 | 0.4205 | 15.979 | 50 |  | 3110
10024 | CLEAR LAKE 1101881362 | 42141101 | CLEAR LAKE 1101 | 881362 | TRUE | 1747.5089 | 480.0321 | 0.29834 | 10 | 0.00010401 | 1552 | 3804.2183 | 168 | 0.41959 | 4.1959 | 51 |  | 3475
7141 | WILDWOOD 11011454 | 103611101 | WILDWOOD 1101 | 1454 | FALSE | 12602.1173 | 12602.1173 | 7.8323 | 31 | 9.3126e-05 | 1817 | 5114.2446 | 68 | 0.41883 | 12.9837 | 52 | 0.03 | 2353
7033 | VACA DIXON 1105965390 | 63591105 | VACA DIXON 1105 | 965390 | FALSE | 2587.1085 | 1209.1092 | 0.75147 | 21 | 9.949e-05 | 1657 | 4819.484 | 91 | 0.41415 | 8.6971 | 53 |  | 3088
9936 | OLETA 1101754718 | 163541101 | OLETA 1101 | 754718 | FALSE | 4640.5633 | 4640.5633 | 2.8841 | 29 | 0.00013445 | 936 | 2737.1841 | 306 | 0.40712 | 11.8066 | 54 |  | 3456
10113 | CALISTOGA 1101CB | 42711101 | CALISTOGA 1101 | CB | TRUE | 1122.2361 | 221.6704 | 0.13777 | 9 | 0.00036283 | 82 | 802.2368 | 941 | 0.40561 | 3.6505 | 55 | 0.11 | 1412
9252 | STANISLAUS 1701CB | 162821701 | STANISLAUS 1701 | CB | FALSE | 11032.7196 | 11032.7196 | 6.8569 | 54 | 0.00014918 | 748 | 2134.6994 | 416 | 0.40353 | 21.7909 | 56 | 0.11 | 1422
9014 | MARIPOSA 2101CB | 254452101 | MARIPOSA 2101 | CB | FALSE | 4029.4321 | 4029.4321 | 2.5043 | 34 | 0.00017446 | 532 | 2332.9065 | 378 | 0.39837 | 13.5444 | 57 | 0.04 | 2081
4909 | HARTLEY 1101698 | 43211101 | HARTLEY 1101 | 698 | FALSE | 16605.929 | 11071.0466 | 6.8807 | 97 | 9.4179e-05 | 1790 | 4392.8078 | 115 | 0.39723 | 38.5312 | 58 | 0.06 | 1832
9239 | BANGOR 1101979830 | 103191101 | BANGOR 1101 | 979830 | TRUE | 696.7531 | 680.7511 | 0.42309 | 7 | 7.12e-05 | 2441 | 5107.124 | 69 | 0.3972 | 2.7804 | 59 |  | 3328
4242 | POTTER VALLEY P H 110495878 | 42281104 | POTTER VALLEY P H 1104 | 95878 | FALSE | 30094.5573 | 9856.7705 | 6.126 | 191 | 0.00017374 | 535 | 2217.9989 | 398 | 0.3965 | 75.7306 | 60 | 0.02 | 2524
2058 | COARSEGOLD 21045310 | 254432104 | COARSEGOLD 2104 | 5310 | FALSE | 45195.5088 | 45195.5088 | 28.0892 | 299 | 6.7329e-05 | 2551 | 6694.8526 | 15 | 0.39401 | 117.8076 | 61 | 19.51 | 312
8298 | STAFFORD 1102361952 | 43201102 | STAFFORD 1102 | 361952 | FALSE | 2196.587 | 2196.587 | 1.3652 | 9 | 0.00011545 | 1290 | 3151.4111 | 248 | 0.39288 | 3.536 | 62 | 1.9 | 631
1488 | AUBERRY 1101CB | 254151101 | AUBERRY 1101 | CB | FALSE | 29229.2172 | 29229.2172 | 18.1661 | 204 | 8.2084e-05 | 2150 | 5306.8686 | 52 | 0.39206 | 79.9801 | 63 | 0.11 | 1431
3596 | VACAVILLE 11088762 | 63601108 | VACAVILLE 1108 | 8762 | FALSE | 26274.6884 | 22259.6162 | 13.8344 | 147 | 7.8661e-05 | 2244 | 4502.8739 | 108 | 0.39138 | 57.5327 | 64 | 0.12 | 1395
6014 | OREGON TRAIL 11041634 | 103521104 | OREGON TRAIL 1104 | 1634 | FALSE | 29441.3626 | 29110.7694 | 18.0925 | 192 | 8.4909e-05 | 2064 | 4929.5026 | 80 | 0.39094 | 75.0607 | 65 | 0.18 | 1222
6392 | COARSEGOLD 210410335 | 254432104 | COARSEGOLD 2104 | 10335 | FALSE | 9369.0411 | 9369.0411 | 5.8229 | 69 | 9.5888e-05 | 1732 | 4247.144 | 133 | 0.39082 | 26.9663 | 66 | 1.53 | 668
7352 | JAMESON 1102865502 | 63801102 | JAMESON 1102 | 865502 | TRUE | 4467.1172 | 644.9532 | 0.40084 | 27 | 0.00011299 | 1344 | 3613.4467 | 189 | 0.38957 | 10.5185 | 67 |  | 3119
3943 | MOUNTAIN QUARRIES 2101CB | 152282101 | MOUNTAIN QUARRIES 2101 | CB | FALSE | 40215.5467 | 40215.5467 | 24.9941 | 262 | 0.00012902 | 1029 | 2606.3425 | 328 | 0.38665 | 101.3032 | 68 | 9.11 | 412
2633 | PASO ROBLES 1103N54 | 182611103 | PASO ROBLES 1103 | N54 | FALSE | 34748.7236 | 32201.1783 | 20.0132 | 221 | 9.3045e-05 | 1819 | 4184.3432 | 138 | 0.38568 | 85.2354 | 69 | 3.07 | 564
6808 | PHILO 110137222 | 42601101 | PHILO 1101 | 37222 | FALSE | 40893.1758 | 40893.1758 | 25.4153 | 152 | 0.00011309 | 1341 | 3498.721 | 202 | 0.3839 | 58.3523 | 70 | 0.05 | 2044
8006 | RISING RIVER 11011532 | 103551101 | RISING RIVER 1101 | 1532 | FALSE | 7926.8978 | 6133.1893 | 3.8118 | 27 | 6.5114e-05 | 2606 | 6536.3281 | 17 | 0.38077 | 10.2807 | 71 | 0.01 | 2591
10120 | DEL MAR 210975802 | 152582109 | DEL MAR 2109 | 75802 | TRUE | 680.0226 | 576.1553 | 0.35808 | 6 | 0.0002061 | 377 | 1316.5155 | 676 | 0.37901 | 2.2741 | 72 | 3.09 | 563
8754 | NOTRE DAME 11042408 | 102041104 | NOTRE DAME 1104 | 2408 | FALSE | 22439.0865 | 18541.2413 | 11.5235 | 76 | 0.00027566 | 167 | 1710.6647 | 521 | 0.37815 | 28.7393 | 73 | 0.15 | 1306
5603 | HIGHLANDS 1102623120 | 43361102 | HIGHLANDS 1102 | 623120 | FALSE | 12233.579 | 10535.1094 | 6.5476 | 67 | 0.00013171 | 986 | 3211.1058 | 239 | 0.3774 | 25.2855 | 74 |  | 2966
2079 | POTTER VALLEY P H 11051904 | 42281105 | POTTER VALLEY P H 1105 | 1904 | FALSE | 64429.3728 | 51242.8521 | 31.8476 | 332 | 0.00018482 | 475 | 1914.8501 | 471 | 0.37685 | 125.1141 | 75 | 0.11 | 1439
8836 | VOLTA 1101CB | 102541101 | VOLTA 1101 | CB | FALSE | 14817.1823 | 14817.1823 | 9.2089 | 80 | 0.00011233 | 1359 | 3549.008 | 194 | 0.37545 | 30.036 | 76 | 0.07 | 1694
10966 | HICKS 2101984788 | 83432101 | HICKS 2101 | 984788 | TRUE | 5.0644 | 5.0644 | 0.0031475 | 1 | 7.6238e-05 | 2303 | 4898.9282 | 84 | 0.37348 | 0.37348 | 77 |  | 3623
6191 | COARSEGOLD 2104570682 | 254432104 | COARSEGOLD 2104 | 570682 | FALSE | 3264.3372 | 3264.3372 | 2.0288 | 26 | 9.6836e-05 | 1718 | 4471.4183 | 111 | 0.37306 | 9.6995 | 78 | 5.65 | 481
8841 | NORTH DUBLIN 210311101 | 14052103 | NORTH DUBLIN 2103 | 11101 | FALSE | 5931.2678 | 5931.2678 | 3.6863 | 37 | 6.6475e-05 | 2575 | 6042.3197 | 28 | 0.36793 | 13.6135 | 79 | 5.36 | 488
7776 | NORTH DUBLIN 21039473 | 14052103 | NORTH DUBLIN 2103 | 9473 | FALSE | 4735.3386 | 3890.479 | 2.4179 | 27 | 9.0946e-05 | 1883 | 3855.297 | 162 | 0.36547 | 9.8678 | 80 | 1.5 | 669
9266 | WILLOW PASS 2107445650 | 13912107 | WILLOW PASS 2107 | 445650 | FALSE | 1066.4109 | 1066.4109 | 0.66278 | 5 | 6.0341e-05 | 2764 | 6011.651 | 29 | 0.36477 | 1.8239 | 81 |  | 3333
2272 | MIDDLETOWN 1102414 | 43141102 | MIDDLETOWN 1102 | 414 | FALSE | 18899.455 | 9544.4247 | 5.9319 | 114 | 0.00014586 | 791 | 3081.157 | 259 | 0.36434 | 41.5353 | 82 | 1.22 | 699
3625 | CAYETANO 2109884904 | 14422109 | CAYETANO 2109 | 884904 | FALSE | 18739.6016 | 18723.6816 | 11.6368 | 77 | 0.0001019 | 1605 | 3934.604 | 152 | 0.36326 | 27.9711 | 83 |  | 2842
10903 | PEABODY 2106592742 | 63642106 | PEABODY 2106 | 592742 | TRUE | 684.4552 | 546.7453 | 0.3398 | 5 | 6.9919e-05 | 2474 | 5228.5371 | 60 | 0.36227 | 1.8113 | 84 |  | 3618
5260 | VOLTA 11011568 | 102541101 | VOLTA 1101 | 1568 | FALSE | 37176.4968 | 37176.4968 | 23.1053 | 136 | 9.0935e-05 | 1885 | 3456.9848 | 206 | 0.36191 | 49.2203 | 85 | 0.1 | 1479
4693 | MIDDLETOWN 1101CB | 43141101 | MIDDLETOWN 1101 | CB | FALSE | 22365.4615 | 7612.1604 | 4.731 | 146 | 0.00014565 | 795 | 2568.6158 | 335 | 0.36174 | 52.8144 | 86 | 14.97 | 351
10547 | PASO ROBLES 1103N02 | 182611103 | PASO ROBLES 1103 | N02 | TRUE | 70.934 | 70.934 | 0.044086 | 1 | 0.00025248 | 210 | 1429.5746 | 625 | 0.36094 | 0.36094 | 87 | 2.56 | 597
2088 | COARSEGOLD 21035020 | 254432103 | COARSEGOLD 2103 | 5020 | FALSE | 26887.6514 | 26064.8634 | 16.1994 | 159 | 8.5726e-05 | 2036 | 4882.5801 | 85 | 0.36009 | 57.2543 | 88 | 0.1 | 1468
7913 | JESSUP 11023105 | 103441102 | JESSUP 1102 | 3105 | FALSE | 9965.2703 | 9659.0441 | 6.0031 | 65 | 6.4265e-05 | 2635 | 5852.1243 | 38 | 0.35978 | 23.3856 | 89 | 2.42 | 605
10257 | CAYETANO 2111389190 | 14422111 | CAYETANO 2111 | 389190 | FALSE | 4452.7835 | 3542.8058 | 2.2019 | 18 | 0.00010318 | 1566 | 3658.7668 | 184 | 0.35946 | 6.4703 | 90 |  | 3524
10351 | VACAVILLE 1109799940 | 63601109 | VACAVILLE 1109 | 799940 | TRUE | 1340.3375 | 954.7701 | 0.59339 | 9 | 9.2053e-05 | 1842 | 3744.3748 | 176 | 0.35844 | 3.2259 | 91 |  | 3537
745 | PUTAH CREEK 110267858 | 63681102 | PUTAH CREEK 1102 | 67858 | FALSE | 18377.3415 | 18377.3415 | 11.4216 | 107 | 6.8002e-05 | 2535 | 5416.4769 | 50 | 0.35702 | 38.201 | 92 | 2.79 | 581
10611 | PEABODY 2113945670 | 63642113 | PEABODY 2113 | 945670 | TRUE | 403.0974 | 334.4297 | 0.20785 | 3 | 6.3935e-05 | 2648 | 5860.0064 | 36 | 0.35536 | 1.0661 | 93 |  | 3578
835 | ZACA 1102Y54 | 182681102 | ZACA 1102 | Y54 | FALSE | 55238.5351 | 54847.9366 | 34.0882 | 296 | 8.0013e-05 | 2204 | 4332.6246 | 120 | 0.35181 | 104.1359 | 94 | 0.39 | 950
9806 | OLETA 1101CB | 163541101 | OLETA 1101 | CB | TRUE | 169.7516 | 136.2242 | 0.084664 | 2 | 0.00017127 | 555 | 1962.7321 | 461 | 0.35138 | 0.70277 | 95 | 2.89 | 573
7864 | SISQUOC 1103867486 | 182811103 | SISQUOC 1103 | 867486 | FALSE | 5219.4397 | 3405.4305 | 2.1165 | 20 | 7.3948e-05 | 2361 | 3380.0089 | 213 | 0.35061 | 7.0121 | 96 |  | 3172
10173 | CALPINE 1146400 | 48011146 | CALPINE 1146 | 400 | FALSE | 5057.3021 | 5057.3021 | 3.1431 | 8 | 9.5474e-05 | 1743 | 3849.0683 | 163 | 0.34896 | 2.7917 | 97 | 0.31 | 1006
615 | KERCKHOFF 1101CB | 252561101 | KERCKHOFF 1101 | CB | FALSE | 27398.7529 | 27398.7529 | 17.0284 | 154 | 6.9314e-05 | 2496 | 5271.5559 | 56 | 0.348 | 53.5915 | 98 | 0.07 | 1725
1695 | DESCHUTES 110449024 | 103351104 | DESCHUTES 1104 | 49024 | FALSE | 26972.4504 | 26707.9675 | 16.5991 | 209 | 8.4768e-05 | 2071 | 4699.5815 | 98 | 0.34786 | 72.7038 | 99 | 9.03 | 415
3728 | DESCHUTES 11041370 | 103351104 | DESCHUTES 1104 | 1370 | FALSE | 35764.2 | 21861.3958 | 13.5869 | 272 | 0.00010359 | 1559 | 3756.8301 | 175 | 0.34561 | 94.0068 | 100 | 0.05 | 1954
10316 | CORNING 110135974 | 103331101 | CORNING 1101 | 35974 | TRUE | 1338.7863 | 398.8739 | 0.2479 | 11 | 7.6845e-05 | 2289 | 4333.8495 | 119 | 0.34404 | 3.7844 | 101 | 0.03 | 2393
10256 | VACAVILLE 1104874798 | 63601104 | VACAVILLE 1104 | 874798 | TRUE | 662.24 | 662.24 | 0.41158 | 3 | 6.6045e-05 | 2587 | 6079.8606 | 27 | 0.33623 | 1.0087 | 102 |  | 3523
6277 | WILLITS 1103964 | 42661103 | WILLITS 1103 | 964 | FALSE | 8651.6925 | 4999.6692 | 3.1073 | 41 | 0.00013223 | 977 | 2706.926 | 309 | 0.33456 | 13.717 | 103 | 0.45 | 917
6777 | BELL 11085703 | 152701108 | BELL 1108 | 5703 | FALSE | 12751.5705 | 8525.0586 | 5.2984 | 96 | 0.00012007 | 1186 | 2775.9092 | 303 | 0.33328 | 31.9947 | 104 | 0.07 | 1684
10040 | PANORAMA 11021632 | 103461102 | PANORAMA 1102 | 1632 | FALSE | 13751.6318 | 13751.6318 | 8.5467 | 19 | 8.8891e-05 | 1954 | 4338.5101 | 118 | 0.33244 | 6.3164 | 105 | 0.05 | 1948
9960 | WILLITS 1103CB | 42661103 | WILLITS 1103 | CB | FALSE | 6348.7863 | 4804 | 2.9857 | 44 | 0.00014557 | 797 | 1870.2515 | 482 | 0.32751 | 14.4105 | 106 | 0.03 | 2238
6501 | SAN MIGUEL 1104895760 | 182661104 | SAN MIGUEL 1104 | 895760 | FALSE | 19502.5171 | 14756.3663 | 9.1711 | 96 | 9.5565e-05 | 1740 | 3633.0115 | 188 | 0.32643 | 31.3373 | 107 |  | 3035
4461 | SANTA YNEZ 1104Y04 | 182721104 | SANTA YNEZ 1104 | Y04 | FALSE | 35997.3396 | 25194.6309 | 15.6586 | 238 | 6.6358e-05 | 2580 | 5141.1422 | 64 | 0.32463 | 77.261 | 108 | 2.84 | 576
10609 | PEABODY 2106CB | 63642106 | PEABODY 2106 | CB | TRUE | 1275.2265 | 525.8096 | 0.32679 | 9 | 0.00013923 | 884 | 1814.5621 | 503 | 0.32442 | 2.9197 | 109 | 0.04 | 2217
3147 | HOPLAND 1101768 | 42251101 | HOPLAND 1101 | 768 | FALSE | 31882.0115 | 27234.0747 | 16.9261 | 115 | 9.5052e-05 | 1764 | 3417.6208 | 210 | 0.32431 | 37.2953 | 110 | 0.05 | 2000
6991 | COVELO 1101478952 | 43061101 | COVELO 1101 | 478952 | FALSE | 5727.3171 | 1143.6662 | 0.71079 | 39 | 0.00011288 | 1347 | 2674.3103 | 318 | 0.32368 | 12.6234 | 111 |  | 3082
9010 | STAFFORD 11021202 | 43201102 | STAFFORD 1102 | 1202 | FALSE | 12713.8882 | 12713.8882 | 7.9017 | 41 | 0.00015857 | 657 | 2432.9018 | 355 | 0.32328 | 13.2544 | 112 | 2.4 | 607
5081 | RED BLUFF 11041566 | 103541104 | RED BLUFF 1104 | 1566 | FALSE | 24740.5736 | 19451.0946 | 12.0889 | 94 | 8.022e-05 | 2199 | 4262.1109 | 129 | 0.3225 | 30.3149 | 113 | 0.05 | 2042
9508 | ANDERSON 1101426745 | 103261101 | ANDERSON 1101 | 426745 | TRUE | 328.8561 | 328.8561 | 0.20439 | 3 | 0.00020048 | 394 | 1570.5843 | 571 | 0.32224 | 0.96673 | 114 |  | 3365
10637 | SYCAMORE CREEK 1111153260 | 102971111 | SYCAMORE CREEK 1111 | 153260 | TRUE | 424.4592 | 424.4592 | 0.2638 | 2 | 9.6022e-05 | 1729 | 3917.3903 | 154 | 0.32186 | 0.64373 | 115 |  | 3584
3800 | DESCHUTES 11049726 | 103351104 | DESCHUTES 1104 | 9726 | FALSE | 27359.7494 | 25257.4681 | 15.6976 | 197 | 8.9511e-05 | 1931 | 4058.7556 | 145 | 0.32131 | 63.2977 | 116 | 3.58 | 541
4142 | GIRVAN 1101323094 | 103401101 | GIRVAN 1101 | 323094 | FALSE | 58176.4815 | 58176.4815 | 36.1569 | 208 | 0.00010508 | 1524 | 3224.7709 | 234 | 0.32037 | 66.6373 | 117 | 0.08 | 1636
4869 | BELL 11082202 | 152701108 | BELL 1108 | 2202 | FALSE | 53635.0932 | 52339.4363 | 32.5292 | 363 | 0.0001269 | 1065 | 2599.5441 | 330 | 0.32016 | 116.2183 | 118 | 0.16 | 1264
9492 | OLETA 1101296804 | 163541101 | OLETA 1101 | 296804 | FALSE | 5287.5044 | 5287.5044 | 3.2862 | 12 | 0.00014395 | 815 | 2252.1128 | 392 | 0.31954 | 3.8345 | 119 |  | 3361
10541 | CLARKSVILLE 2105CB | 153612105 | CLARKSVILLE 2105 | CB | FALSE | 1481.3738 | 1293.943 | 0.80419 | 9 | 0.00018563 | 469 | 1193.2799 | 733 | 0.31824 | 2.8642 | 120 | 0.39 | 953
5372 | TEMPLETON 2113A20 | 183052113 | TEMPLETON 2113 | A20 | FALSE | 12666.4228 | 11999.0835 | 7.4575 | 92 | 8.3458e-05 | 2117 | 4208.4041 | 137 | 0.3179 | 29.2466 | 121 | 0.09 | 1561
8293 | VACAVILLE 110838316 | 63601108 | VACAVILLE 1108 | 38316 | FALSE | 36512.8123 | 25616.7426 | 15.9209 | 232 | 7.2587e-05 | 2403 | 4684.5531 | 99 | 0.31672 | 73.4796 | 122 | 3 | 569
907 | COTTONWOOD 1102544790 | 102931102 | COTTONWOOD 1102 | 544790 | FALSE | 27462.4335 | 26342.4042 | 16.3719 | 185 | 8.3921e-05 | 2097 | 3941.9662 | 151 | 0.31273 | 57.8548 | 123 |  | 2696
6176 | COARSEGOLD 21045525 | 254432104 | COARSEGOLD 2104 | 5525 | FALSE | 21152.7165 | 21152.7165 | 13.1465 | 175 | 5.9719e-05 | 2783 | 5306.8404 | 53 | 0.31171 | 54.5497 | 124 | 0.17 | 1227
3989 | MIDDLETOWN 1102878 | 43141102 | MIDDLETOWN 1102 | 878 | FALSE | 9206.6572 | 5430.6654 | 3.3752 | 49 | 0.00017681 | 519 | 2682.7456 | 315 | 0.31109 | 15.2435 | 125 | 0.63 | 834
2201 | RACETRACK 1704CB | 163761704 | RACETRACK 1704 | CB | FALSE | 36834.5436 | 36834.5436 | 22.8928 | 193 | 0.00011343 | 1334 | 2972.4937 | 272 | 0.31093 | 60.0095 | 126 | 10.25 | 399
4707 | HIGHLANDS 1103828 | 43361103 | HIGHLANDS 1103 | 828 | FALSE | 17153.3338 | 13828.9706 | 8.5948 | 112 | 8.3934e-05 | 2094 | 3831.1552 | 164 | 0.31086 | 34.8164 | 127 | 5.94 | 476
8759 | KERCKHOFF 1101R308 | 252561101 | KERCKHOFF 1101 | R308 | FALSE | 6217.3701 | 6217.3701 | 3.8641 | 22 | 6.1262e-05 | 2743 | 4314.2777 | 123 | 0.30901 | 6.7983 | 128 | 0.04 | 2136
7918 | FORESTHILL 1102CB | 152181102 | FORESTHILL 1102 | CB | FALSE | 2646.4634 | 2646.4634 | 1.6448 | 13 | 0.00028983 | 139 | 1109.8091 | 772 | 0.30873 | 4.0135 | 129 | 5.34 | 489
9076 | SYCAMORE CREEK 1111976428 | 102971111 | SYCAMORE CREEK 1111 | 976428 | FALSE | 16955.2499 | 14081.5812 | 8.7518 | 82 | 0.00013702 | 908 | 2148.1965 | 412 | 0.30752 | 25.2165 | 130 |  | 3305
6711 | PUTAH CREEK 110396792 | 63681103 | PUTAH CREEK 1103 | 96792 | FALSE | 8212.3137 | 6394.0351 | 3.9739 | 30 | 7.1793e-05 | 2425 | 5020.5256 | 72 | 0.30689 | 9.2067 | 131 |  | 3057
9779 | COARSEGOLD 21046210 | 254432104 | COARSEGOLD 2104 | 6210 | FALSE | 17177.2503 | 17177.2503 | 10.6757 | 49 | 4.8609e-05 | 3072 | 5877.8631 | 34 | 0.30465 | 14.9278 | 132 | 0.06 | 1874
7407 | TEMPLETON 2113A12 | 183052113 | TEMPLETON 2113 | A12 | FALSE | 64854.5144 | 64854.5144 | 40.3073 | 180 | 9.1245e-05 | 1867 | 3289.4433 | 226 | 0.30414 | 54.7453 | 133 | 0.11 | 1446
6929 | CLARKSVILLE 2104CB | 153612104 | CLARKSVILLE 2104 | CB | FALSE | 16489.2317 | 14163.76 | 8.8028 | 107 | 0.00015725 | 671 | 2292.759 | 385 | 0.30391 | 32.5187 | 134 | 6.82 | 459
8076 | NORTH DUBLIN 2103CB | 14052103 | NORTH DUBLIN 2103 | CB | FALSE | 24190.4571 | 22339.3117 | 13.884 | 147 | 0.00012222 | 1145 | 2373.5412 | 366 | 0.30349 | 44.6134 | 135 | 0.16 | 1273
9798 | BALCH NO 1 1101CB | 252501101 | BALCH NO 1 1101 | CB | FALSE | 16978.5039 | 16978.5039 | 10.5522 | 33 | 8.5557e-05 | 2039 | 4275.4303 | 128 | 0.30244 | 9.9805 | 136 | 0.03 | 2265
8821 | SANTA YNEZ 1104CB | 182721104 | SANTA YNEZ 1104 | CB | TRUE | 12832.3568 | 56.5182 | 0.035126 | 105 | 9.1038e-05 | 1880 | 3530.2398 | 198 | 0.30185 | 31.6947 | 137 | 0.03 | 2249
12 | PASO ROBLES 1103N50 | 182611103 | PASO ROBLES 1103 | N50 | FALSE | 3586.1974 | 3586.1974 | 2.2288 | 24 | 0.00020174 | 390 | 1403.0605 | 636 | 0.30039 | 7.2094 | 138 | 6.6 | 465
461 | KONOCTI 1102354890 | 43311102 | KONOCTI 1102 | 354890 | FALSE | 19596.9379 | 15016.4864 | 9.3328 | 131 | 0.00011262 | 1350 | 1727.5671 | 518 | 0.29712 | 38.9233 | 139 |  | 2675
4081 | OREGON TRAIL 11021382 | 103521102 | OREGON TRAIL 1102 | 1382 | FALSE | 8797.2782 | 8797.2782 | 5.4675 | 67 | 0.00010202 | 1603 | 2904.98 | 289 | 0.29503 | 19.7671 | 140 | 0.07 | 1732
207 | AUBERRY 1102CB | 254151102 | AUBERRY 1102 | CB | FALSE | 55860.8325 | 55860.8325 | 34.7177 | 368 | 5.1188e-05 | 3010 | 6445.9013 | 19 | 0.29173 | 107.3565 | 141 | 0.21 | 1150
929 | CORRAL 1101CB | 162991101 | CORRAL 1101 | CB | FALSE | 44193.7001 | 42311.3503 | 26.2967 | 280 | 7.4699e-05 | 2339 | 3983.5914 | 150 | 0.29054 | 81.3506 | 142 | 18.05 | 326
3287 | ANDERSON 11031600 | 103261103 | ANDERSON 1103 | 1600 | FALSE | 17254.9785 | 7231.4682 | 4.4944 | 106 | 9.3311e-05 | 1813 | 3227.6771 | 231 | 0.2889 | 30.6232 | 143 | 0.04 | 2087
1107 | COARSEGOLD 210410030 | 254432104 | COARSEGOLD 2104 | 10030 | FALSE | 59186.5885 | 54599.1868 | 33.9336 | 227 | 5.1982e-05 | 2993 | 5711.1735 | 43 | 0.28655 | 65.0478 | 144 | 0.04 | 2223
9519 | ARBUCKLE 1104669720 | 62081104 | ARBUCKLE 1104 | 669720 | FALSE | 7831.1318 | 3612.2461 | 2.245 | 22 | 8.813e-05 | 1979 | 4178.9611 | 140 | 0.28655 | 6.3042 | 145 |  | 3370
3809 | WISE 11022230 | 152271102 | WISE 1102 | 2230 | FALSE | 40267.1112 | 38210.8819 | 23.7482 | 278 | 9.8822e-05 | 1674 | 3101.6196 | 254 | 0.28438 | 79.0585 | 146 | 8.79 | 420
2464 | SHEPHERD 2111327814 | 252062111 | SHEPHERD 2111 | 327814 | FALSE | 23697.2526 | 18621.0587 | 11.5731 | 119 | 5.813e-05 | 2832 | 5439.3493 | 48 | 0.28428 | 33.8288 | 147 |  | 2778
3815 | PANORAMA 1102280170 | 103461102 | PANORAMA 1102 | 280170 | FALSE | 24945.6136 | 20943.3132 | 13.0164 | 102 | 0.00011005 | 1411 | 2725.4901 | 307 | 0.28426 | 28.9943 | 148 |  | 2855
10166 | TEMPLETON 21132949 | 183052113 | TEMPLETON 2113 | 2949 | TRUE | 766.5719 | 766.5719 | 0.47643 | 6 | 4.9947e-05 | 3039 | 6323.2739 | 22 | 0.28416 | 1.7049 | 149 | 2.67 | 590
6611 | DESCHUTES 1101CB | 103351101 | DESCHUTES 1101 | CB | FALSE | 17940.9873 | 8017.5323 | 4.9829 | 118 | 0.00011905 | 1205 | 2481.2226 | 344 | 0.28403 | 33.5157 | 150 | 0.04 | 2142
195 | COARSEGOLD 21045300 | 254432104 | COARSEGOLD 2104 | 5300 | FALSE | 89782.9365 | 89782.9365 | 55.8005 | 507 | 6.1292e-05 | 2742 | 5197.3797 | 62 | 0.28372 | 143.8456 | 151 | 0.2 | 1159
5871 | FLINT 1101750 | 152531101 | FLINT 1101 | 750 | FALSE | 14900.5272 | 7342.9025 | 4.5636 | 93 | 0.00015288 | 720 | 2183.6202 | 404 | 0.28318 | 26.3354 | 152 | 3.16 | 559
952 | SANTA YNEZ 1104Y66 | 182721104 | SANTA YNEZ 1104 | Y66 | FALSE | 29410.1773 | 27268.3855 | 16.9474 | 138 | 5.9163e-05 | 2801 | 4926.5491 | 81 | 0.28279 | 39.0253 | 153 | 8.36 | 431
1401 | SAN JOAQUIN #2 110310320 | 252521103 | SAN JOAQUIN #2 1103 | 10320 | FALSE | 18962.0898 | 18962.0898 | 11.785 | 133 | 7.3548e-05 | 2380 | 3652.1529 | 186 | 0.28179 | 37.4782 | 154 | 0.06 | 1810
10123 | FULTON 110258990 | 42561102 | FULTON 1102 | 58990 | TRUE | 971.5045 | 427.9744 | 0.26599 | 6 | 0.00011359 | 1330 | 3017.9754 | 266 | 0.28025 | 1.6815 | 155 |  | 3495
3591 | SANTA YNEZ 1101277014 | 182721101 | SANTA YNEZ 1101 | 277014 | FALSE | 26491.1541 | 8850.8283 | 5.5008 | 149 | 7.4914e-05 | 2333 | 3435.5989 | 208 | 0.28002 | 41.7232 | 156 |  | 2840
2737 | VOLTA 110153118 | 102541101 | VOLTA 1101 | 53118 | FALSE | 15490.2629 | 15490.2629 | 9.6273 | 47 | 5.9428e-05 | 2792 | 5134.3568 | 65 | 0.27952 | 13.1375 | 157 | 0.08 | 1618
9393 | PUTAH CREEK 1103654021 | 63681103 | PUTAH CREEK 1103 | 654021 | TRUE | 1396.0557 | 329.1954 | 0.2046 | 12 | 6.2033e-05 | 2719 | 5297.9521 | 54 | 0.27878 | 3.3454 | 158 |  | 3351
5717 | SHINGLE SPRINGS 210935598 | 153652109 | SHINGLE SPRINGS 2109 | 35598 | FALSE | 17452.8092 | 17452.8092 | 10.847 | 122 | 0.00012105 | 1163 | 2054.3578 | 443 | 0.27855 | 33.9836 | 159 | 2.42 | 604
1630 | OREGON TRAIL 11041574 | 103521104 | OREGON TRAIL 1104 | 1574 | FALSE | 30217.612 | 27209.5234 | 16.9108 | 221 | 9.7752e-05 | 1698 | 3321.0394 | 222 | 0.27852 | 61.5533 | 160 | 0.1 | 1499
2168 | HOPLAND 11014626 | 42251101 | HOPLAND 1101 | 4626 | FALSE | 50138.0738 | 43527.4256 | 27.0525 | 238 | 9.7355e-05 | 1704 | 2906.275 | 288 | 0.27841 | 66.2609 | 161 | 0.08 | 1626
10275 | SAN MIGUEL 1105873457 | 182661105 | SAN MIGUEL 1105 | 873457 | FALSE | 3228.1461 | 2440.6531 | 1.5169 | 18 | 6.4601e-05 | 2620 | 3816.6955 | 166 | 0.27723 | 4.9901 | 162 |  | 3525
5141 | AUBERRY 1101R2578 | 254151101 | AUBERRY 1101 | R2578 | FALSE | 74560.0099 | 74560.0099 | 46.3393 | 506 | 5.751e-05 | 2848 | 5003.4373 | 77 | 0.27714 | 140.2335 | 163 | 0.12 | 1377
710 | COARSEGOLD 2103CB | 254432103 | COARSEGOLD 2103 | CB | FALSE | 61825.449 | 61825.449 | 38.4248 | 420 | 0.00010575 | 1502 | 2969.029 | 273 | 0.27679 | 116.2539 | 164 | 0.1 | 1498
9397 | BEAR VALLEY 21059570 | 252192105 | BEAR VALLEY 2105 | 9570 | FALSE | 12951.7997 | 12951.7997 | 8.0496 | 59 | 6.9285e-05 | 2498 | 4812.6159 | 92 | 0.27669 | 16.3249 | 165 | 0.03 | 2273
4772 | COARSEGOLD 2102CB | 254432102 | COARSEGOLD 2102 | CB | FALSE | 22596.9807 | 22596.9807 | 14.0441 | 79 | 8.9146e-05 | 1941 | 3040.7048 | 264 | 0.2766 | 21.851 | 166 | 0.05 | 2045
11028 | NARROWS PH 1151CB | 153131151 | NARROWS PH 1151 | CB | TRUE | 286.9891 | 286.9891 | 0.17836 | 2 | 0.00034143 | 96 | 952.1877 | 859 | 0.27613 | 0.55227 | 167 |  | 3629
5439 | KONOCTI 110264664 | 43311102 | KONOCTI 1102 | 64664 | FALSE | 46084.8025 | 44670.3665 | 27.7628 | 263 | 0.00011497 | 1301 | 2595.543 | 331 | 0.27567 | 72.501 | 168 | 7.76 | 441
307 | MOUNTAIN QUARRIES 21011350 | 152282101 | MOUNTAIN QUARRIES 2101 | 1350 | FALSE | 34999.9271 | 34999.9271 | 21.7526 | 212 | 0.00015371 | 714 | 2128.0484 | 418 | 0.27537 | 58.3793 | 169 | 0.14 | 1328
8396 | NORTH DUBLIN 2101MR765 | 14052101 | NORTH DUBLIN 2101 | MR765 | FALSE | 3411.7079 | 3330.9197 | 2.0702 | 15 | 0.00016258 | 618 | 1924.3853 | 466 | 0.2736 | 4.104 | 170 |  | 3219
6379 | PUTAH CREEK 11028352 | 63681102 | PUTAH CREEK 1102 | 8352 | FALSE | 19103.6731 | 10298.4219 | 6.4005 | 133 | 7.7051e-05 | 2286 | 3533.4319 | 197 | 0.27308 | 36.3202 | 171 | 0.04 | 2110
7979 | KONOCTI 1102716 | 43311102 | KONOCTI 1102 | 716 | FALSE | 27459.7262 | 24685.2253 | 15.342 | 109 | 0.00010173 | 1611 | 2445.3377 | 351 | 0.27295 | 29.7514 | 172 | 0.09 | 1540
1249 | PENRYN 11032198 | 152561103 | PENRYN 1103 | 2198 | FALSE | 33673.9837 | 32552.0609 | 20.2312 | 248 | 0.00015745 | 669 | 1901.3176 | 477 | 0.27291 | 67.6807 | 173 | 5.01 | 498
10021 | OLETA 1101400470 | 163541101 | OLETA 1101 | 400470 | TRUE | 475.2183 | 334.0108 | 0.20759 | 3 | 0.0001432 | 822 | 1757.1387 | 513 | 0.27287 | 0.81862 | 174 |  | 3474
3674 | AUBERRY 1102R309 | 254151102 | AUBERRY 1102 | R309 | FALSE | 13825.8859 | 13825.8859 | 8.5928 | 92 | 4.4689e-05 | 3170 | 5876.5086 | 35 | 0.27286 | 25.1032 | 175 | 0.07 | 1734
1420 | MIDDLETOWN 1102998 | 43141102 | MIDDLETOWN 1102 | 998 | FALSE | 27408.0031 | 23900.855 | 14.8545 | 205 | 0.00011619 | 1266 | 2601.6522 | 329 | 0.27124 | 55.6044 | 176 | 9.39 | 410
6398 | CAYETANO 2109MR572 | 14422109 | CAYETANO 2109 | MR572 | FALSE | 19863.5833 | 13342.8208 | 8.2926 | 80 | 8.353e-05 | 2113 | 3855.5003 | 161 | 0.27121 | 21.6967 | 177 | 0.06 | 1900
6361 | APPLE HILL 21026552 | 153662102 | APPLE HILL 2102 | 6552 | FALSE | 20088.9562 | 20088.9562 | 12.4854 | 139 | 0.00023194 | 279 | 1458.479 | 613 | 0.2712 | 37.6964 | 178 | 0.07 | 1674
5677 | BANGOR 110180670 | 103191101 | BANGOR 1101 | 80670 | FALSE | 26435.3887 | 23201.6685 | 14.4199 | 158 | 9.3264e-05 | 1814 | 3120.2999 | 252 | 0.27059 | 42.753 | 179 | 0.07 | 1687
7666 | JAMESON 1103118944 | 63801103 | JAMESON 1103 | 118944 | FALSE | 8499.846 | 3772.9974 | 2.3449 | 41 | 7.2601e-05 | 2402 | 3739.9482 | 177 | 0.27039 | 11.0862 | 180 |  | 3148
5313 | HIGHLANDS 1103482 | 43361103 | HIGHLANDS 1103 | 482 | FALSE | 41604.9679 | 39433.4736 | 24.5081 | 188 | 8.3389e-05 | 2120 | 3402.5308 | 212 | 0.26975 | 50.7128 | 181 | 0.11 | 1426
5299 | HIGGINS 1109CB | 152691109 | HIGGINS 1109 | CB | FALSE | 37179.8547 | 36440.0989 | 22.6477 | 254 | 0.00012368 | 1127 | 2336.1435 | 377 | 0.26784 | 68.0313 | 182 | 0.11 | 1411
7848 | OAKHURST 1101636114 | 254421101 | OAKHURST 1101 | 636114 | FALSE | 32974.1643 | 32974.1643 | 20.4936 | 153 | 5.0431e-05 | 3029 | 5596.4616 | 45 | 0.26702 | 40.8546 | 183 |  | 3171
10324 | SANTA YNEZ 1104564710 | 182721104 | SANTA YNEZ 1104 | 564710 | TRUE | 541.7371 | 273.7323 | 0.17013 | 7 | 4.7515e-05 | 3102 | 4812.031 | 93 | 0.26624 | 1.8637 | 184 |  | 3533
10018 | LINCOLN 1104275986 | 153701104 | LINCOLN 1104 | 275986 | TRUE | 934.5883 | 934.5883 | 0.58085 | 5 | 8.2974e-05 | 2131 | 2938.8625 | 283 | 0.26526 | 1.3263 | 185 |  | 3473
5709 | HIGGINS 110950072 | 152691109 | HIGGINS 1109 | 50072 | FALSE | 68212.3656 | 68212.3656 | 42.3943 | 424 | 8.3823e-05 | 2099 | 2904.6654 | 290 | 0.26524 | 112.4633 | 186 | 0.17 | 1228
3710 | MARIPOSA 210110070 | 254452101 | MARIPOSA 2101 | 10070 | FALSE | 42054.457 | 42054.457 | 26.137 | 249 | 5.9269e-05 | 2796 | 3802.6518 | 169 | 0.2644 | 65.835 | 187 | 0.16 | 1265
3891 | MARIPOSA 210210880 | 254452102 | MARIPOSA 2102 | 10880 | FALSE | 64212.5757 | 63861.6467 | 39.6903 | 362 | 5.4719e-05 | 2925 | 5019.3026 | 74 | 0.2637 | 95.458 | 188 | 0.25 | 1077
1822 | BELL 110750172 | 152701107 | BELL 1107 | 50172 | FALSE | 30233.9103 | 28142.3136 | 17.4906 | 210 | 8.9513e-05 | 1930 | 3226.5987 | 232 | 0.2635 | 55.3341 | 189 | 3.07 | 565
7084 | VACAVILLE 111113652 | 63601111 | VACAVILLE 1111 | 13652 | FALSE | 6914.8485 | 6914.8485 | 4.2976 | 58 | 0.00011431 | 1311 | 2370.7576 | 367 | 0.26339 | 15.2768 | 190 | 4.89 | 502
3429 | CLOVERDALE 1101399855 | 42821101 | CLOVERDALE 1101 | 399855 | FALSE | 4438.9669 | 4409.9199 | 2.7408 | 19 | 0.00012846 | 1040 | 1799.172 | 506 | 0.26331 | 5.0028 | 191 |  | 2826
9762 | HARTLEY 11014710 | 43211101 | HARTLEY 1101 | 4710 | FALSE | 2414.0517 | 2414.0517 | 1.5003 | 18 | 7.3983e-05 | 2359 | 3402.6996 | 211 | 0.26308 | 4.7355 | 192 | 0.06 | 1858
2103 | DOBBINS 11011808 | 153741101 | DOBBINS 1101 | 1808 | FALSE | 25003.3757 | 25003.3757 | 15.5397 | 171 | 0.00012923 | 1021 | 2096.2914 | 428 | 0.26282 | 44.9426 | 193 | 0.09 | 1564
3817 | DESCHUTES 11011380 | 103351101 | DESCHUTES 1101 | 1380 | FALSE | 37070.8959 | 28672.6173 | 17.8201 | 204 | 0.00010398 | 1553 | 2782.7866 | 301 | 0.26207 | 53.462 | 194 | 0.07 | 1696
1392 | SAND CREEK 110345190 | 254601103 | SAND CREEK 1103 | 45190 | FALSE | 60483.5997 | 60483.5997 | 37.5908 | 416 | 4.4054e-05 | 3190 | 5858.6509 | 37 | 0.26095 | 108.5552 | 195 | 0.15 | 1301
4741 | BRENTWOOD 2105B504R | 14592105 | BRENTWOOD 2105 | B504R | FALSE | 18129.2647 | 14074.6887 | 8.7475 | 97 | 9.8714e-05 | 1676 | 3474.2779 | 204 | 0.26071 | 25.289 | 196 | 0.1 | 1494
7636 | VACA DIXON 110118292 | 63591101 | VACA DIXON 1101 | 18292 | TRUE | 8145.543 | 73.0344 | 0.045391 | 73 | 0.00010766 | 1460 | 2089.0547 | 431 | 0.26015 | 18.9907 | 197 | 4.97 | 499
4859 | OREGON TRAIL 1102CB | 103521102 | OREGON TRAIL 1102 | CB | FALSE | 15377.0316 | 15053.0301 | 9.3555 | 98 | 0.00013609 | 918 | 2689.4423 | 314 | 0.25991 | 25.4708 | 198 | 1.45 | 674
1063 | MARIPOSA 210110990 | 254452101 | MARIPOSA 2101 | 10990 | FALSE | 64432.5092 | 64432.5092 | 40.0451 | 390 | 6.2843e-05 | 2688 | 4452.3041 | 112 | 0.25971 | 101.2865 | 199 | 0.23 | 1118
9382 | CORNING 110185162 | 103331101 | CORNING 1101 | 85162 | FALSE | 9267.4821 | 9267.4821 | 5.7598 | 28 | 4.8495e-05 | 3077 | 5246.1165 | 57 | 0.2589 | 7.2492 | 200 | 0.09 | 1512
1035 | CORRAL 110136652 | 162991101 | CORRAL 1101 | 36652 | FALSE | 58152.9177 | 58152.9177 | 36.1423 | 357 | 6.9107e-05 | 2503 | 3912.9423 | 155 | 0.25884 | 92.4048 | 201 | 2.74 | 586
4603 | UPPER LAKE 1101660 | 42871101 | UPPER LAKE 1101 | 660 | FALSE | 15616.9486 | 9914.559 | 6.1619 | 91 | 0.00011219 | 1361 | 2640.3198 | 322 | 0.25883 | 23.5531 | 202 | 0.02 | 2506
521 | WILLITS 1103696 | 42661103 | WILLITS 1103 | 696 | FALSE | 15381.4122 | 10464.5667 | 6.5038 | 87 | 0.00011584 | 1275 | 2155.4593 | 411 | 0.25793 | 22.4395 | 203 | 0.04 | 2141
134 | SAN JOAQUIN #2 1103CB | 252521103 | SAN JOAQUIN #2 1103 | CB | FALSE | 109280.4349 | 109280.4349 | 67.9182 | 589 | 7.6086e-05 | 2305 | 3828.8466 | 165 | 0.25597 | 150.7655 | 204 | 0.64 | 828
3686 | UKIAH 1111534 | 42771111 | UKIAH 1111 | 534 | FALSE | 33775.8497 | 30432.3399 | 18.9138 | 142 | 8.2307e-05 | 2145 | 3212.6445 | 237 | 0.25577 | 36.3189 | 205 | 0.12 | 1397
8712 | ELK CREEK 110193504 | 102781101 | ELK CREEK 1101 | 93504 | FALSE | 4036.8011 | 3461.2366 | 2.1512 | 15 | 6.0933e-05 | 2750 | 4082.5968 | 144 | 0.25426 | 3.8139 | 206 | 0.06 | 1896
10786 | PEABODY 2113873304 | 63642113 | PEABODY 2113 | 873304 | FALSE | 1312.9508 | 1312.9508 | 0.816 | 5 | 6.945e-05 | 2489 | 4833.6394 | 88 | 0.25419 | 1.2709 | 207 |  | 3605
9423 | CLAY 110359714 | 163341103 | CLAY 1103 | 59714 | FALSE | 7503.916 | 7503.916 | 4.6637 | 34 | 9.4275e-05 | 1786 | 2408.1592 | 360 | 0.25391 | 8.6328 | 208 | 0.04 | 2176
9267 | POTTER VALLEY P H 1105990354 | 42281105 | POTTER VALLEY P H 1105 | 990354 | TRUE | 170.3854 | 170.3854 | 0.1059 | 2 | 0.00030725 | 122 | 583.9962 | 1119 | 0.25341 | 0.50682 | 209 | 0.02 | 2532
4480 | LUCERNE 1106526 | 43351106 | LUCERNE 1106 | 526 | FALSE | 17461.3012 | 16256.6321 | 10.1036 | 100 | 0.00011252 | 1356 | 2700.181 | 312 | 0.25318 | 25.318 | 210 | 0.07 | 1679
3034 | HOPLAND 1101558 | 42251101 | HOPLAND 1101 | 558 | FALSE | 15006.3638 | 4818.3603 | 2.9946 | 72 | 0.00022789 | 291 | 857.3477 | 909 | 0.25266 | 18.1915 | 211 | 0.01 | 2601
4451 | HIGHLANDS 1103568 | 43361103 | HIGHLANDS 1103 | 568 | FALSE | 14789.9903 | 12940.6184 | 8.0426 | 118 | 0.00012911 | 1024 | 2034.9748 | 449 | 0.25222 | 29.7625 | 212 | 0.1 | 1493
5062 | AUBERRY 1102R902 | 254151102 | AUBERRY 1102 | R902 | FALSE | 24261.144 | 24261.144 | 15.0784 | 156 | 6.3332e-05 | 2666 | 4129.7341 | 141 | 0.25137 | 39.2136 | 213 | 0.07 | 1688
5371 | SUNOL 1101MR169 | 14241101 | SUNOL 1101 | MR169 | FALSE | 15006.414 | 4976.4795 | 3.0929 | 96 | 9.4566e-05 | 1776 | 2310.912 | 383 | 0.25044 | 24.0426 | 214 | 0.02 | 2435
8139 | LAS GALLINAS A 110599904 | 42991105 | LAS GALLINAS A 1105 | 99904 | FALSE | 8949.4853 | 8949.4853 | 5.5621 | 54 | 0.00018177 | 500 | 1184.3918 | 739 | 0.25006 | 13.5032 | 215 | 39.72 | 187
4462 | WILLITS 110337504 | 42661103 | WILLITS 1103 | 37504 | FALSE | 5704.6998 | 1890.9339 | 1.1752 | 41 | 0.00013442 | 938 | 1727.1376 | 519 | 0.24974 | 10.2392 | 216 | 0.02 | 2505
4593 | POSO MOUNTAIN 2101CB | 253642101 | POSO MOUNTAIN 2101 | CB | FALSE | 6924.1001 | 6924.1001 | 4.3034 | 22 | 5.902e-05 | 2806 | 4006.0392 | 149 | 0.24862 | 5.4697 | 217 | 0.07 | 1691
6909 | WYANDOTTE 1109702710 | 102911109 | WYANDOTTE 1109 | 702710 | FALSE | 7335.7671 | 4286.5556 | 2.6641 | 49 | 0.00021702 | 330 | 1323.547 | 672 | 0.24845 | 12.174 | 218 |  | 3072
9944 | WYANDOTTE 110366146 | 102911103 | WYANDOTTE 1103 | 66146 | TRUE | 252.3083 | 252.3083 | 0.15681 | 4 | 0.00010984 | 1414 | 2698.6732 | 313 | 0.24793 | 0.99171 | 219 | 0.12 | 1382
10031 | SOLEDAD 2102346006 | 182052102 | SOLEDAD 2102 | 346006 | FALSE | 3918.3073 | 3650.4625 | 2.2688 | 5 | 7.7555e-05 | 2277 | 3061.2643 | 262 | 0.24765 | 1.2382 | 220 |  | 3479
905 | CORNING 110290036 | 103331102 | CORNING 1102 | 90036 | FALSE | 23187.5221 | 21561.1762 | 13.4004 | 87 | 7.3822e-05 | 2364 | 4520.2585 | 105 | 0.24724 | 21.5103 | 221 | 0.1 | 1505
5847 | OAKHURST 11035732 | 254421103 | OAKHURST 1103 | 5732 | FALSE | 5445.3198 | 5445.3198 | 3.3843 | 37 | 5.3285e-05 | 2956 | 4484.9828 | 109 | 0.24719 | 9.1461 | 222 | 0.14 | 1324
5505 | MARIPOSA 210237282 | 254452102 | MARIPOSA 2102 | 37282 | FALSE | 96262.8931 | 86430.7687 | 53.7171 | 498 | 6.5439e-05 | 2602 | 4244.8756 | 134 | 0.24522 | 122.1205 | 223 | 0.36 | 969
4841 | OAKHURST 110363334 | 254421103 | OAKHURST 1103 | 63334 | FALSE | 27819.9713 | 27819.9713 | 17.2902 | 154 | 5.0298e-05 | 3032 | 5273.9392 | 55 | 0.24446 | 37.6467 | 224 | 10.23 | 400
8342 | BANGOR 110131502 | 103191101 | BANGOR 1101 | 31502 | FALSE | 19104.3686 | 19104.3686 | 11.8734 | 102 | 0.00014287 | 828 | 1982.4694 | 459 | 0.24429 | 24.9173 | 225 | 0.08 | 1616
9205 | POINT MORETTI 110135874 | 82931101 | POINT MORETTI 1101 | 35874 | TRUE | 329.4831 | 329.4831 | 0.20478 | 4 | 0.0002322 | 276 | 974.717 | 846 | 0.24298 | 0.97191 | 226 | 0.03 | 2258
2854 | SHINGLE SPRINGS 21099372 | 153652109 | SHINGLE SPRINGS 2109 | 9372 | FALSE | 28750.7098 | 28750.7098 | 17.8687 | 190 | 0.00012144 | 1159 | 1860.3939 | 487 | 0.24281 | 46.1342 | 227 | 6.15 | 472
10573 | GEYSERVILLE 1102756 | 42891102 | GEYSERVILLE 1102 | 756 | TRUE | 948.4078 | 948.4078 | 0.58944 | 7 | 0.00037409 | 76 | 1141.7089 | 757 | 0.24238 | 1.6966 | 228 | 0.02 | 2431
6313 | SAN MIGUEL 1104N60 | 182661104 | SAN MIGUEL 1104 | N60 | FALSE | 14171.0101 | 13316.658 | 8.2764 | 66 | 6.3749e-05 | 2655 | 3875.817 | 160 | 0.24236 | 15.9958 | 229 | 0.04 | 2143
2085 | LINCOLN 1104685276 | 153701104 | LINCOLN 1104 | 685276 | FALSE | 34821.9656 | 10432.3869 | 6.4838 | 216 | 7.8086e-05 | 2256 | 3212.4401 | 238 | 0.24208 | 52.2897 | 230 |  | 2761
7825 | HORSESHOE 1101416226 | 152571101 | HORSESHOE 1101 | 416226 | TRUE | 397.9238 | 186.6616 | 0.11601 | 5 | 8.4899e-05 | 2065 | 2680.4211 | 316 | 0.24182 | 1.2091 | 231 |  | 3167
9295 | BROWNS VALLEY 110117011 | 152921101 | BROWNS VALLEY 1101 | 17011 | FALSE | 3005.3172 | 3005.3172 | 1.8678 | 22 | 9.7443e-05 | 1702 | 2978.7374 | 270 | 0.24153 | 5.3136 | 232 | 0.07 | 1747
1428 | ZACA 1102Y02 | 182681102 | ZACA 1102 | Y02 | FALSE | 21138.3499 | 16812.4916 | 10.449 | 158 | 6.2768e-05 | 2691 | 3729.2174 | 180 | 0.24142 | 38.1442 | 233 | 0.07 | 1717
6825 | OLETA 1102186326 | 163541102 | OLETA 1102 | 186326 | FALSE | 20743.7329 | 19088.8539 | 11.8638 | 123 | 0.00011431 | 1312 | 2157.6907 | 410 | 0.24114 | 29.6596 | 234 |  | 3066
7670 | STANISLAUS 1702CB | 162821702 | STANISLAUS 1702 | CB | FALSE | 13066.3244 | 13066.3244 | 8.1208 | 67 | 0.00015785 | 665 | 1253.7272 | 700 | 0.24096 | 16.1444 | 235 | 0.13 | 1360
9773 | MADISON 2101117644 | 63172101 | MADISON 2101 | 117644 | FALSE | 3757.3782 | 1080.3525 | 0.67144 | 12 | 9.3021e-05 | 1820 | 2949.3645 | 280 | 0.23987 | 2.8784 | 236 |  | 3416
10170 | PUTAH CREEK 1105617260 | 63681105 | PUTAH CREEK 1105 | 617260 | FALSE | 4545.7003 | 1876.8402 | 1.1665 | 15 | 9.4125e-05 | 1791 | 3143.4533 | 249 | 0.2396 | 3.5941 | 237 |  | 3506
10828 | BUELLTON 110163389 | 183041101 | BUELLTON 1101 | 63389 | TRUE | 391.5938 | 0 | 0 | 2 | 0.00010287 | 1573 | 1639.5129 | 547 | 0.23935 | 0.47871 | 238 |  | 3610
8291 | CLEAR LAKE 1102904 | 42141102 | CLEAR LAKE 1102 | 904 | FALSE | 5777.0339 | 5445.6493 | 3.3845 | 30 | 9.2995e-05 | 1822 | 2564.652 | 336 | 0.23862 | 7.1587 | 239 | 1.48 | 670
6235 | SHINGLE SPRINGS 210519522 | 153652105 | SHINGLE SPRINGS 2105 | 19522 | FALSE | 16493.1882 | 15565.1755 | 9.6738 | 113 | 8.878e-05 | 1959 | 3187.9029 | 244 | 0.23827 | 26.9251 | 240 | 34.17 | 216
9843 | SUNOL 1101MR387 | 14241101 | SUNOL 1101 | MR387 | FALSE | 8072.5307 | 8065.9096 | 5.013 | 24 | 6.2945e-05 | 2681 | 3500.2914 | 201 | 0.23776 | 5.7062 | 241 | 0.06 | 1882
109 | WISE 11022054 | 152271102 | WISE 1102 | 2054 | FALSE | 20940.0353 | 20940.0353 | 13.0143 | 147 | 0.00010429 | 1544 | 2815.7078 | 298 | 0.23735 | 34.8898 | 242 | 3.46 | 547
9387 | ANTELOPE 1101318686 | 252021101 | ANTELOPE 1101 | 318686 | FALSE | 4853.6414 | 2345.6024 | 1.4578 | 7 | 6.5096e-05 | 2607 | 3652.241 | 185 | 0.23683 | 1.6578 | 243 |  | 3349
2465 | JESSUP 11021314 | 103441102 | JESSUP 1102 | 1314 | FALSE | 23311.1376 | 9677.7607 | 6.0148 | 161 | 8.2165e-05 | 2148 | 3017.906 | 267 | 0.23664 | 38.0983 | 244 | 1.18 | 703
4610 | KERCKHOFF 1101R353 | 252561101 | KERCKHOFF 1101 | R353 | FALSE | 22190.5443 | 22190.5443 | 13.7915 | 53 | 3.7075e-05 | 3313 | 6512.8186 | 18 | 0.23576 | 12.4952 | 245 | 0.07 | 1773
7566 | CORRAL 110112608 | 162991101 | CORRAL 1101 | 12608 | FALSE | 27131.1027 | 27131.1027 | 16.8621 | 187 | 6.2935e-05 | 2683 | 3772.462 | 174 | 0.23545 | 44.029 | 246 | 11.8 | 381
5704 | SHEPHERD 2111707358 | 252062111 | SHEPHERD 2111 | 707358 | FALSE | 37001.2559 | 30537.9753 | 18.9795 | 219 | 4.1347e-05 | 3238 | 5721.8442 | 41 | 0.23489 | 51.4409 | 247 |  | 2974
10861 | PEORIA 170492888 | 163781704 | PEORIA 1704 | 92888 | TRUE | 765.3621 | 400.6025 | 0.24898 | 4 | 0.00010691 | 1480 | 2347.6932 | 375 | 0.23471 | 0.93885 | 248 | 0.01 | 2581
5055 | FROGTOWN 17028482 | 163451702 | FROGTOWN 1702 | 8482 | FALSE | 23390.9929 | 23390.9929 | 14.5376 | 117 | 0.00010252 | 1587 | 2287.3259 | 386 | 0.23437 | 27.4214 | 249 | 0.05 | 2057
10192 | MADISON 2101725408 | 63172101 | MADISON 2101 | 725408 | FALSE | 2105.6406 | 1530.1897 | 0.95102 | 9 | 9.3021e-05 | 1821 | 2838.0743 | 294 | 0.23427 | 2.1085 | 250 |  | 3511
852 | PASO ROBLES 1104R56 | 182611104 | PASO ROBLES 1104 | R56 | FALSE | 19965.7505 | 18526.1855 | 11.5141 | 117 | 9.8997e-05 | 1669 | 2922.3966 | 284 | 0.2342 | 27.401 | 251 | 1.75 | 644
9420 | FRENCH GULCH 11011892 | 103381101 | FRENCH GULCH 1101 | 1892 | FALSE | 5154.3447 | 5154.3447 | 3.2034 | 12 | 0.00011418 | 1317 | 1393.5299 | 640 | 0.23339 | 2.8006 | 252 | 0.06 | 1887
2713 | ELK CREEK 110137334 | 102781101 | ELK CREEK 1101 | 37334 | FALSE | 15392.9848 | 15392.9848 | 9.5668 | 70 | 5.2877e-05 | 2973 | 4838.4242 | 87 | 0.23311 | 16.3175 | 253 | 0.07 | 1730
8722 | POSO MOUNTAIN 21033988 | 253642103 | POSO MOUNTAIN 2103 | 3988 | FALSE | 29512.4633 | 27217.7374 | 16.9159 | 68 | 4.0141e-05 | 3264 | 5944.554 | 32 | 0.23303 | 15.8463 | 254 | 0.1 | 1471
6130 | OREGON TRAIL 1104CB | 103521104 | OREGON TRAIL 1104 | CB | FALSE | 23543.7827 | 17030.244 | 10.5844 | 164 | 0.00014109 | 852 | 1638.3807 | 548 | 0.23182 | 38.0188 | 255 | 0.08 | 1577
6781 | PALMER 1101M84 | 183031101 | PALMER 1101 | M84 | FALSE | 39352.9214 | 37718.995 | 23.4425 | 145 | 7.1467e-05 | 2434 | 3431.3832 | 209 | 0.23169 | 33.5958 | 256 | 0.05 | 2018
7251 | PASO ROBLES 1103N58 | 182611103 | PASO ROBLES 1103 | N58 | FALSE | 11929.7838 | 7319.6094 | 4.5492 | 91 | 8.9683e-05 | 1923 | 2958.7213 | 277 | 0.23099 | 21.0205 | 257 | 1.43 | 676
9345 | CHOLAME 21025597 | 182562102 | CHOLAME 2102 | 5597 | FALSE | 8229.9238 | 8229.9238 | 5.1149 | 22 | 5.7292e-05 | 2855 | 4008.4187 | 148 | 0.23009 | 5.062 | 258 | 0.06 | 1847
6582 | UPPER LAKE 1101412 | 42871101 | UPPER LAKE 1101 | 412 | FALSE | 27547.3528 | 16599.9817 | 10.317 | 152 | 9.7196e-05 | 1709 | 2705.0187 | 311 | 0.23008 | 34.9724 | 259 | 0.04 | 2122
7180 | PASO ROBLES 11032731 | 182611103 | PASO ROBLES 1103 | 2731 | FALSE | 2630.6286 | 2630.6286 | 1.6349 | 13 | 8.1626e-05 | 2166 | 3132.5166 | 251 | 0.2296 | 2.9847 | 260 | 0.25 | 1088
6731 | DEL MAR 2109CB | 152582109 | DEL MAR 2109 | CB | FALSE | 9780.4489 | 2376.9126 | 1.4773 | 72 | 0.00018501 | 472 | 1136.289 | 760 | 0.22956 | 16.5281 | 261 | 0.02 | 2474
4193 | ANDERSON 1103226050 | 103261103 | ANDERSON 1103 | 226050 | FALSE | 24153.2004 | 7845.4549 | 4.876 | 160 | 0.00012494 | 1099 | 1958.1377 | 463 | 0.22913 | 36.6601 | 262 |  | 2875
2449 | COARSEGOLD 210410400 | 254432104 | COARSEGOLD 2104 | 10400 | FALSE | 72169.1615 | 68567.3531 | 42.6149 | 539 | 6.3171e-05 | 2673 | 4382.9111 | 117 | 0.22826 | 123.0305 | 263 | 0.67 | 815
6456 | HIGGINS 110950078 | 152691109 | HIGGINS 1109 | 50078 | FALSE | 77925.0015 | 77925.0015 | 48.4307 | 427 | 6.6516e-05 | 2573 | 3492.1838 | 203 | 0.22791 | 97.3194 | 264 | 0.18 | 1215
6171 | WYANDOTTE 110737472 | 102911107 | WYANDOTTE 1107 | 37472 | FALSE | 23988.0552 | 14935.9015 | 9.2827 | 157 | 0.00012968 | 1013 | 1878.4311 | 481 | 0.22739 | 35.7007 | 265 | 0.05 | 2001
1604 | COARSEGOLD 210310820 | 254432103 | COARSEGOLD 2103 | 10820 | FALSE | 46507.9226 | 46392.4448 | 28.8331 | 327 | 6.2605e-05 | 2698 | 4312.1018 | 124 | 0.2269 | 74.1966 | 266 | 0.19 | 1188
3581 | JESSUP 110296554 | 103441102 | JESSUP 1102 | 96554 | FALSE | 23931.0858 | 12987.3897 | 8.0717 | 172 | 7.0376e-05 | 2458 | 3307.1204 | 223 | 0.22645 | 38.9486 | 267 | 1.68 | 653
10176 | CLARK ROAD 1102CB | 103091102 | CLARK ROAD 1102 | CB | FALSE | 2444.9029 | 1435.1005 | 0.89192 | 20 | 0.0002022 | 389 | 1029.6753 | 809 | 0.22632 | 4.5263 | 268 | 0.01 | 2599
1714 | BUELLTON 1102Y50 | 183041102 | BUELLTON 1102 | Y50 | FALSE | 20651.346 | 17101.0403 | 10.6284 | 147 | 6.643e-05 | 2578 | 3157.5997 | 246 | 0.22624 | 33.2573 | 269 | 4.23 | 523
2661 | CLAY 11031230 | 163341103 | CLAY 1103 | 1230 | FALSE | 31242.042 | 27069.5791 | 16.8239 | 136 | 8.4359e-05 | 2080 | 2820.2882 | 297 | 0.22608 | 30.7471 | 270 | 0.08 | 1627
511 | COTTONWOOD 11029026 | 102931102 | COTTONWOOD 1102 | 9026 | FALSE | 39327.0742 | 20154.6992 | 12.5262 | 282 | 7.3532e-05 | 2382 | 3010.4191 | 268 | 0.22599 | 63.7295 | 271 | 0.04 | 2131
5682 | CLOVERDALE 1102672 | 42821102 | CLOVERDALE 1102 | 672 | FALSE | 35787.4101 | 35088.8854 | 21.8079 | 140 | 0.00010502 | 1528 | 2485.285 | 343 | 0.22571 | 31.5995 | 272 | 0.66 | 819
920 | RED BLUFF 11041630 | 103541104 | RED BLUFF 1104 | 1630 | FALSE | 22751.2492 | 4020.9242 | 2.499 | 152 | 5.7083e-05 | 2858 | 3897.064 | 159 | 0.22562 | 34.2944 | 273 | 0.02 | 2518
6155 | AUBERRY 1101R2839 | 254151101 | AUBERRY 1101 | R2839 | FALSE | 20608.9537 | 20608.9537 | 12.8085 | 121 | 6.3713e-05 | 2657 | 3802.0162 | 170 | 0.22501 | 27.2266 | 274 | 0.07 | 1746
252 | CLARK ROAD 11022582 | 103091102 | CLARK ROAD 1102 | 2582 | FALSE | 33578.71 | 32011.0943 | 19.895 | 186 | 8.3332e-05 | 2124 | 2966.3342 | 275 | 0.22449 | 41.7559 | 275 | 0.31 | 999
5168 | CORNING 11021622 | 103331102 | CORNING 1102 | 1622 | FALSE | 54701.9644 | 54701.9644 | 33.9975 | 126 | 4.7554e-05 | 3098 | 5068.1116 | 70 | 0.22413 | 28.2406 | 276 | 0.15 | 1289
2620 | AUBERRY 1101R2579 | 254151101 | AUBERRY 1101 | R2579 | FALSE | 56162.7607 | 56162.7607 | 34.9054 | 286 | 4.3679e-05 | 3195 | 4995.9654 | 78 | 0.22394 | 64.0469 | 277 | 0.05 | 1982
7109 | AUBERRY 1102R1013 | 254151102 | AUBERRY 1102 | R1013 | FALSE | 20054.4308 | 20054.4308 | 12.4639 | 132 | 5.2064e-05 | 2991 | 4310.3961 | 125 | 0.22385 | 29.5483 | 278 | 0.08 | 1599
1039 | SILVERADO 2104726 | 43432104 | SILVERADO 2104 | 726 | FALSE | 56301.3396 | 48875.2274 | 30.3762 | 263 | 0.00010365 | 1558 | 2367.3738 | 368 | 0.22347 | 58.7725 | 279 | 5.19 | 495
8364 | PEORIA 1705CB | 163781705 | PEORIA 1705 | CB | FALSE | 11342.4728 | 11342.4728 | 7.0494 | 33 | 9.1397e-05 | 1864 | 1823.5922 | 499 | 0.22294 | 7.3571 | 280 | 1.24 | 696
42 | CEDAR CREEK 11011664 | 103321101 | CEDAR CREEK 1101 | 1664 | FALSE | 47581.2918 | 47581.2918 | 29.572 | 244 | 0.00016153 | 624 | 1257.5627 | 697 | 0.22209 | 54.1896 | 281 | 0.09 | 1544
8613 | ZACA 1101Y72 | 182681101 | ZACA 1101 | Y72 | FALSE | 10347.4182 | 10265.6354 | 6.3801 | 36 | 7.4862e-05 | 2335 | 2941.2416 | 282 | 0.2213 | 7.967 | 282 | 0.05 | 1994
5656 | PANORAMA 1102508502 | 103461102 | PANORAMA 1102 | 508502 | FALSE | 25902.2253 | 18917.893 | 11.7575 | 115 | 8.1215e-05 | 2178 | 2793.3826 | 300 | 0.22043 | 25.3491 | 283 |  | 2971
2018 | SMARTVILLE 1101CB | 153791101 | SMARTVILLE 1101 | CB | FALSE | 26399.8993 | 26026.0287 | 16.1753 | 152 | 0.00012844 | 1042 | 2226.2508 | 395 | 0.21931 | 33.3354 | 284 | 0.08 | 1659
8459 | CAYETANO 21099504 | 14422109 | CAYETANO 2109 | 9504 | FALSE | 23288.5561 | 23283.8699 | 14.471 | 97 | 5.1866e-05 | 2997 | 4524.1542 | 104 | 0.21922 | 21.2645 | 285 | 0.67 | 812
3475 | SO. CAL. EDISON #3 1101CB | 258861101 | SO. CAL. EDISON #3 1101 | CB | FALSE | 13738.3645 | 13738.3645 | 8.5384 | 32 | 4.0322e-05 | 3260 | 5713.5203 | 42 | 0.21869 | 6.998 | 286 | 0.06 | 1881
5637 | NARROWS 2101CB | 153132101 | NARROWS 2101 | CB | FALSE | 25047.8448 | 25047.8448 | 15.5673 | 65 | 0.00013384 | 945 | 2147.2351 | 413 | 0.21823 | 14.185 | 287 | 0.06 | 1867
8049 | BROWNS VALLEY 110136622 | 152921101 | BROWNS VALLEY 1101 | 36622 | FALSE | 15095.8174 | 8277.82 | 5.1447 | 42 | 0.00010696 | 1475 | 1906.2139 | 474 | 0.21771 | 9.1438 | 288 | 0.01 | 2620
5251 | WYANDOTTE 110313018 | 102911103 | WYANDOTTE 1103 | 13018 | FALSE | 2657.2717 | 1090.3862 | 0.67768 | 20 | 0.00024176 | 241 | 916.9696 | 877 | 0.21662 | 4.3325 | 289 | 0.04 | 2205
7438 | OREGON TRAIL 1103CB | 103521103 | OREGON TRAIL 1103 | CB | FALSE | 4716.8976 | 4354.341 | 2.7062 | 38 | 0.00020157 | 391 | 1548.9969 | 580 | 0.21644 | 8.2246 | 290 | 0.07 | 1689
9233 | PASO ROBLES 1103N52 | 182611103 | PASO ROBLES 1103 | N52 | FALSE | 10571.3698 | 10571.3698 | 6.5701 | 32 | 0.00016961 | 565 | 1370.1644 | 652 | 0.21643 | 6.9258 | 291 | 0.06 | 1851
5544 | TYLER 11051536 | 103571105 | TYLER 1105 | 1536 | FALSE | 29066.1076 | 28603.8149 | 17.7774 | 79 | 4.6575e-05 | 3124 | 4923.7257 | 83 | 0.21608 | 17.0703 | 292 | 0.07 | 1705
8708 | PUTAH CREEK 1105665952 | 63681105 | PUTAH CREEK 1105 | 665952 | TRUE | 1521.662 | 243.3824 | 0.15126 | 13 | 7.1774e-05 | 2427 | 3135.666 | 250 | 0.21591 | 2.8069 | 293 |  | 3252
9580 | SUMMIT 110147786 | 152591101 | SUMMIT 1101 | 47786 | FALSE | 2915.7036 | 2915.7036 | 1.8121 | 13 | 8.7369e-05 | 2003 | 2875.37 | 291 | 0.21513 | 2.7967 | 294 | 0.01 | 2571
10253 | CLOVERDALE 1102736078 | 42821102 | CLOVERDALE 1102 | 736078 | TRUE | 432.8669 | 373.6781 | 0.23224 | 3 | 6.8384e-05 | 2526 | 3199.3848 | 241 | 0.2146 | 0.64381 | 295 |  | 3522
10589 | DEL MAR 2109306972 | 152582109 | DEL MAR 2109 | 306972 | TRUE | 120.3234 | 83.4407 | 0.051859 | 2 | 0.00015818 | 661 | 1356.3524 | 660 | 0.21455 | 0.4291 | 296 |  | 3576
9314 | CALPINE 1146CB | 48011146 | CALPINE 1146 | CB | FALSE | 4947.493 | 4947.493 | 3.0749 | 21 | 0.00013269 | 965 | 2090.7818 | 430 | 0.21399 | 4.4937 | 297 | 0.32 | 995
5389 | BEAR VALLEY 210511210 | 252192105 | BEAR VALLEY 2105 | 11210 | FALSE | 27492.7886 | 27492.7886 | 17.0869 | 139 | 4.899e-05 | 3064 | 4555.1801 | 103 | 0.21387 | 29.7273 | 298 | 0.02 | 2413
9003 | HARTLEY 1102385838 | 43211102 | HARTLEY 1102 | 385838 | FALSE | 2645.3497 | 2006.1588 | 1.2468 | 11 | 9.3256e-05 | 1815 | 1869.8054 | 483 | 0.21349 | 2.3484 | 299 |  | 3295
4243 | CLAYTON 22122944 | 12022212 | CLAYTON 2212 | 2944 | FALSE | 24391.9365 | 24262.4198 | 15.0792 | 148 | 5.6051e-05 | 2885 | 4103.8075 | 143 | 0.21331 | 31.5694 | 300 | 0.08 | 1576
3022 | DESCHUTES 11041582 | 103351104 | DESCHUTES 1104 | 1582 | FALSE | 24298.6245 | 10265.1395 | 6.3798 | 173 | 8.393e-05 | 2096 | 2774.3491 | 305 | 0.21327 | 36.8955 | 301 | 0.05 | 1927
5186 | DUNLAP 11027360 | 254061102 | DUNLAP 1102 | 7360 | FALSE | 14342.2552 | 14342.2552 | 8.9138 | 83 | 5.7731e-05 | 2844 | 3097.6367 | 256 | 0.21272 | 17.6557 | 302 | 0 | 2643
7188 | UPPER LAKE 1101472084 | 42871101 | UPPER LAKE 1101 | 472084 | FALSE | 11718.4795 | 7454.711 | 4.6331 | 66 | 0.00014287 | 829 | 1759.7585 | 512 | 0.21229 | 14.0108 | 303 | 0.03 | 2360
1958 | CURTIS 170411290 | 163351704 | CURTIS 1704 | 11290 | FALSE | 12662.0411 | 12662.0411 | 7.8695 | 75 | 8.7993e-05 | 1982 | 2545.3939 | 339 | 0.21224 | 15.9178 | 304 | 0.1 | 1455
10301 | SCE VEGAS 1701CB | 188881701 | SCE VEGAS 1701 | CB | TRUE | 168.4127 | 168.4127 | 0.10467 | 1 | 9.0971e-05 | 1882 | 2332.6265 | 379 | 0.2122 | 0.2122 | 305 | 0.27 | 1058
4384 | AUBERRY 110237466 | 254151102 | AUBERRY 1102 | 37466 | FALSE | 50978.0825 | 50460.2287 | 31.3612 | 345 | 3.2323e-05 | 3395 | 6743.7065 | 13 | 0.21127 | 72.8874 | 306 | 0.08 | 1598
2676 | BUELLTON 1102CB | 183041102 | BUELLTON 1102 | CB | FALSE | 22068.3915 | 11401.8921 | 7.0863 | 148 | 5.6901e-05 | 2864 | 2830.5359 | 295 | 0.21085 | 31.2055 | 307 | 1.66 | 655
5276 | SANTA YNEZ 110477098 | 182721104 | SANTA YNEZ 1104 | 77098 | FALSE | 20978.2648 | 19250.5668 | 11.9643 | 112 | 5.0472e-05 | 3025 | 4289.2504 | 127 | 0.21042 | 23.5673 | 308 | 2.69 | 589
7565 | SILVERADO 2104806 | 43432104 | SILVERADO 2104 | 806 | FALSE | 55052.2104 | 33831.6044 | 21.0265 | 229 | 9.1806e-05 | 1850 | 2097.6482 | 426 | 0.21008 | 48.1076 | 309 | 0.15 | 1276
1159 | LONE TREE 210521210 | 13232105 | LONE TREE 2105 | 21210 | FALSE | 26056.9931 | 20686.2377 | 12.8566 | 111 | 5.4908e-05 | 2916 | 4309.2408 | 126 | 0.20896 | 23.1943 | 310 | 0.06 | 1808
1515 | WYANDOTTE 110979932 | 102911109 | WYANDOTTE 1109 | 79932 | FALSE | 52854.9374 | 35504.8505 | 22.0664 | 345 | 8.0348e-05 | 2196 | 2706.2696 | 310 | 0.20828 | 71.8562 | 311 | 0.1 | 1497
4727 | REDBUD 1101454 | 43191101 | REDBUD 1101 | 454 | FALSE | 8909.2195 | 8909.2195 | 5.5371 | 54 | 6.6514e-05 | 2574 | 3069.2553 | 261 | 0.20738 | 11.1984 | 312 | 0.38 | 962
2411 | MARIPOSA 210190180 | 254452101 | MARIPOSA 2101 | 90180 | FALSE | 7976.0066 | 7976.0066 | 4.9571 | 49 | 5.4502e-05 | 2932 | 3678.4222 | 183 | 0.20688 | 10.1373 | 313 | 0.02 | 2514
6630 | MIDDLETOWN 1101644756 | 43141101 | MIDDLETOWN 1101 | 644756 | FALSE | 31848.1753 | 27875.8932 | 17.325 | 163 | 0.00011577 | 1279 | 1915.4825 | 470 | 0.20636 | 33.6372 | 314 |  | 3049
8301 | ELK CREEK 11012002 | 102781101 | ELK CREEK 1101 | 2002 | FALSE | 48391.7593 | 35045.7729 | 21.7811 | 109 | 5.5059e-05 | 2908 | 4261.2835 | 130 | 0.20473 | 22.3155 | 315 | 0.05 | 1965
1537 | BELL 11072400 | 152701107 | BELL 1107 | 2400 | FALSE | 44680.5549 | 41414.8349 | 25.7395 | 320 | 0.00010832 | 1445 | 2117.8289 | 423 | 0.20423 | 65.3543 | 316 | 10.83 | 393
2016 | PETALUMA C 1108296 | 42631108 | PETALUMA C 1108 | 296 | FALSE | 23764.0701 | 23764.0701 | 14.7695 | 123 | 8.734e-05 | 2004 | 2337.6554 | 376 | 0.20401 | 25.0928 | 317 | 6.9 | 457
1327 | DESCHUTES 1104CB | 103351104 | DESCHUTES 1104 | CB | FALSE | 39932.7775 | 21735.4144 | 13.5086 | 273 | 0.00010469 | 1537 | 2355.7077 | 371 | 0.20316 | 55.4629 | 318 | 0.09 | 1519
10175 | JESSUP 1102936897 | 103441102 | JESSUP 1102 | 936897 | TRUE | 1562.7499 | 665.5519 | 0.41364 | 12 | 0.00014733 | 769 | 1798.1732 | 507 | 0.20267 | 2.432 | 319 |  | 3507
2512 | CLAY 110334338 | 163341103 | CLAY 1103 | 34338 | FALSE | 16775.5793 | 15726.6133 | 9.7742 | 66 | 6.79e-05 | 2539 | 3085.8385 | 258 | 0.2022 | 13.3455 | 320 | 0.08 | 1669
3530 | AUBERRY 1102R2850 | 254151102 | AUBERRY 1102 | R2850 | FALSE | 42428.4265 | 42428.4265 | 26.3694 | 222 | 3.6057e-05 | 3337 | 5548.3018 | 47 | 0.20166 | 44.7693 | 321 | 0.17 | 1244
4238 | NORTH BRANCH 1101CB | 163231101 | NORTH BRANCH 1101 | CB | FALSE | 32934.7957 | 25410.3119 | 15.7926 | 114 | 0.00011157 | 1381 | 1859.3886 | 488 | 0.20132 | 22.9503 | 322 | 0.04 | 2202
11083 | NARROWS 2104CB | 153132104 | NARROWS 2104 | CB | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00012264 | 1138 | 1641.5431 | 545 | 0.20132 | 0.20132 | 323 | 0.02 | 2423
389 | VASCO 1102MR176 | 13751102 | VASCO 1102 | MR176 | FALSE | 68684.3236 | 62474.1803 | 38.828 | 256 | 5.5783e-05 | 2894 | 3634.7993 | 187 | 0.20121 | 51.5086 | 324 | 0.19 | 1184
7455 | SAN MIGUEL 1104514987 | 182661104 | SAN MIGUEL 1104 | 514987 | FALSE | 21614.682 | 13379.7927 | 8.3156 | 63 | 4.6195e-05 | 3132 | 4320.4063 | 122 | 0.20048 | 12.6303 | 325 |  | 3128
7507 | NORTH BRANCH 110111158 | 163231101 | NORTH BRANCH 1101 | 11158 | FALSE | 47609.4929 | 20499.8935 | 12.7408 | 229 | 9.6418e-05 | 1721 | 2379.6196 | 364 | 0.20008 | 45.8175 | 326 | 0.06 | 1777
3193 | AUBERRY 1101R314 | 254151101 | AUBERRY 1101 | R314 | FALSE | 71701.2396 | 68245.5324 | 42.4149 | 390 | 3.2526e-05 | 3393 | 6228.9607 | 25 | 0.20004 | 78.017 | 327 | 0.11 | 1437
1293 | MIDDLETOWN 11014646 | 43141101 | MIDDLETOWN 1101 | 4646 | FALSE | 29868.2951 | 29868.2951 | 18.5633 | 165 | 0.00010487 | 1531 | 2139.2524 | 415 | 0.19983 | 32.9712 | 328 | 36.87 | 205
9642 | LUCERNE 11034200 | 43351103 | LUCERNE 1103 | 4200 | FALSE | 7940.3444 | 6495.7462 | 4.0371 | 37 | 0.00011057 | 1400 | 2908.2309 | 287 | 0.19927 | 7.3729 | 329 | 0.05 | 1995
7729 | AUBERRY 110149122 | 254151101 | AUBERRY 1101 | 49122 | FALSE | 6376.3554 | 6376.3554 | 3.9629 | 40 | 4.9196e-05 | 3060 | 3584.6164 | 191 | 0.19907 | 7.9627 | 330 | 1.33 | 682
464 | WOODACRE 110196844 | 43021101 | WOODACRE 1101 | 96844 | FALSE | 9556.2941 | 9556.2941 | 5.9393 | 63 | 0.00023552 | 260 | 862.5947 | 906 | 0.19881 | 12.5249 | 331 | 46.48 | 142
4726 | SHINGLE SPRINGS 210985766 | 153652109 | SHINGLE SPRINGS 2109 | 85766 | FALSE | 29746.7523 | 29746.7523 | 18.4877 | 166 | 0.00013073 | 996 | 2062.5576 | 442 | 0.19865 | 32.9759 | 332 | 0.1 | 1495
9424 | VINEYARD 2110391250 | 14502110 | VINEYARD 2110 | 391250 | FALSE | 1481.3226 | 1481.3226 | 0.92065 | 3 | 0.00010172 | 1612 | 1985.1612 | 457 | 0.19841 | 0.59524 | 333 |  | 3356
308 | CALPINE 1144CB | 48011144 | CALPINE 1144 | CB | FALSE | 42270.0145 | 42270.0145 | 26.271 | 131 | 0.00014762 | 766 | 1407.8483 | 633 | 0.19817 | 25.9607 | 334 | 0.25 | 1086
7335 | UPPER LAKE 11011276 | 42871101 | UPPER LAKE 1101 | 1276 | FALSE | 20806.9121 | 20806.9121 | 12.9316 | 116 | 9.8156e-05 | 1687 | 2220.124 | 397 | 0.19794 | 22.9608 | 335 | 0.05 | 1931
3179 | CHOLAME 2102796386 | 182562102 | CHOLAME 2102 | 796386 | FALSE | 64232.6683 | 57391.9753 | 35.6693 | 159 | 5.7453e-05 | 2849 | 3563.2207 | 192 | 0.19792 | 31.4686 | 336 |  | 2815
9031 | SAND CREEK 1103CB | 254601103 | SAND CREEK 1103 | CB | FALSE | 20983.2028 | 20983.2028 | 13.0411 | 77 | 2.8008e-05 | 3460 | 6753.7935 | 12 | 0.19768 | 15.2216 | 337 | 0.07 | 1765
6545 | TULUCAY 1101628 | 42301101 | TULUCAY 1101 | 628 | FALSE | 14091.1105 | 6713.6414 | 4.1726 | 98 | 0.00010294 | 1570 | 2036.6122 | 448 | 0.19686 | 19.2923 | 338 | 0.05 | 2063
4963 | BEAR VALLEY 210190550 | 252192101 | BEAR VALLEY 2101 | 90550 | FALSE | 12911.2772 | 12911.2772 | 8.0244 | 47 | 5.1033e-05 | 3014 | 3547.8361 | 195 | 0.19624 | 9.2235 | 339 | 0.02 | 2486
8575 | ELK CREEK 11012106 | 102781101 | ELK CREEK 1101 | 2106 | FALSE | 21303.4581 | 21303.4581 | 13.2402 | 67 | 3.7752e-05 | 3302 | 5722.5441 | 40 | 0.1961 | 13.1388 | 340 | 0.03 | 2286
3500 | DUNLAP 11037040 | 254061103 | DUNLAP 1103 | 7040 | FALSE | 39870.081 | 39870.081 | 24.7794 | 230 | 4.8475e-05 | 3079 | 4388.1035 | 116 | 0.19605 | 45.0921 | 341 | 0.07 | 1719
2568 | LAYTONVILLE 1102500 | 42681102 | LAYTONVILLE 1102 | 500 | FALSE | 47144.6891 | 34375.7452 | 21.3647 | 214 | 0.00018229 | 495 | 1298.6787 | 684 | 0.19576 | 41.8921 | 342 | 2.86 | 574
2190 | DIAMOND SPRINGS 110519910 | 152261105 | DIAMOND SPRINGS 1105 | 19910 | FALSE | 33304.7006 | 33304.7006 | 20.699 | 226 | 0.00010076 | 1629 | 2072.4287 | 435 | 0.19568 | 44.2238 | 343 | 0.32 | 994
9927 | FITCH MOUNTAIN 1111555644 | 42751111 | FITCH MOUNTAIN 1111 | 555644 | TRUE | 5004.528 | 268.6791 | 0.16699 | 19 | 0.00011733 | 1240 | 1847.862 | 491 | 0.19539 | 3.7125 | 344 |  | 3453
41 | REDBUD 1101708166 | 43191101 | REDBUD 1101 | 708166 | FALSE | 33499.3555 | 18511.1854 | 11.5048 | 162 | 7.986e-05 | 2209 | 2528.2807 | 340 | 0.19539 | 31.6535 | 345 | 9.62 | 407
8428 | CALPELLA 11013419 | 43411101 | CALPELLA 1101 | 3419 | FALSE | 12848.2917 | 12848.2917 | 7.9853 | 38 | 9.3996e-05 | 1794 | 2318.7771 | 381 | 0.19531 | 7.4218 | 346 | 0.08 | 1610
4645 | OLETA 110241396 | 163541102 | OLETA 1102 | 41396 | FALSE | 11819.9639 | 10868.1559 | 6.7546 | 75 | 0.00014922 | 747 | 1168.3526 | 746 | 0.19503 | 14.6272 | 347 | 0.08 | 1642
1354 | CORRAL 1102CB | 162991102 | CORRAL 1102 | CB | FALSE | 34280.1417 | 27168.7986 | 16.8855 | 236 | 7.8906e-05 | 2237 | 2954.5395 | 278 | 0.19501 | 46.0213 | 348 | 0.13 | 1353
6647 | TIVY VALLEY 1107584840 | 252941107 | TIVY VALLEY 1107 | 584840 | FALSE | 72531.1064 | 72531.1064 | 45.0784 | 449 | 3.4014e-05 | 3370 | 5963.8827 | 31 | 0.19446 | 87.311 | 349 | 0.16 | 1267
4112 | JESSUP 110141356 | 103441101 | JESSUP 1101 | 41356 | FALSE | 52238.1569 | 52238.1569 | 32.4662 | 318 | 8.9642e-05 | 1926 | 2383.6073 | 362 | 0.19445 | 61.8351 | 350 | 1.05 | 720
1219 | APPLE HILL 21021532 | 153662102 | APPLE HILL 2102 | 1532 | FALSE | 68074.9976 | 62691.3369 | 38.9629 | 465 | 0.00014754 | 767 | 1398.4344 | 638 | 0.19412 | 90.2637 | 351 | 0.07 | 1756
4008 | OLETA 11011208 | 163541101 | OLETA 1101 | 1208 | FALSE | 61463.0017 | 53098.4432 | 33.0009 | 334 | 7.3226e-05 | 2389 | 2975.7795 | 271 | 0.19404 | 64.811 | 352 | 0.06 | 1784
9763 | WISHON 1101CB | 251511101 | WISHON 1101 | CB | FALSE | 12293.5283 | 12293.5283 | 7.6405 | 36 | 4.9465e-05 | 3052 | 3520.3689 | 199 | 0.19398 | 6.9834 | 353 | 0.13 | 1346
4721 | COPPERMINE 1104613086 | 252411104 | COPPERMINE 1104 | 613086 | FALSE | 14704.7375 | 8243.1424 | 5.1231 | 63 | 2.9814e-05 | 3430 | 6359.1487 | 20 | 0.19391 | 12.2166 | 354 |  | 2913
8166 | BANGOR 1101CB | 103191101 | BANGOR 1101 | CB | FALSE | 34332.3301 | 30178.5623 | 18.7561 | 171 | 0.00012918 | 1023 | 1585.4725 | 565 | 0.19378 | 33.1366 | 355 | 0.08 | 1606
10364 | MADISON 2101745850 | 63172101 | MADISON 2101 | 745850 | TRUE | 1558.6923 | 771.4701 | 0.47947 | 7 | 5.3176e-05 | 2960 | 3897.9708 | 158 | 0.19369 | 1.3558 | 356 |  | 3539
10620 | OLETA 1102793776 | 163541102 | OLETA 1102 | 793776 | FALSE | 1956.9595 | 1956.9595 | 1.2163 | 6 | 0.00010286 | 1574 | 1821.9134 | 500 | 0.19328 | 1.1597 | 357 |  | 3579
1881 | PENRYN 1103604 | 152561103 | PENRYN 1103 | 604 | FALSE | 42817.3578 | 42516.8793 | 26.4244 | 240 | 0.00012061 | 1176 | 1665.6014 | 537 | 0.19315 | 46.357 | 358 | 8.39 | 428
10174 | LAS GALLINAS A 1105532 | 42991105 | LAS GALLINAS A 1105 | 532 | FALSE | 7102.1777 | 7099.179 | 4.4122 | 34 | 0.00016574 | 585 | 1247.6791 | 702 | 0.19264 | 6.5497 | 359 | 0.65 | 824
9563 | ELK CREEK 11012032 | 102781101 | ELK CREEK 1101 | 2032 | FALSE | 15248.6713 | 14097.676 | 8.7618 | 52 | 6.4621e-05 | 2618 | 3297.3647 | 225 | 0.19237 | 10.0031 | 360 | 0.06 | 1841
7617 | WYANDOTTE 110213044 | 102911102 | WYANDOTTE 1102 | 13044 | FALSE | 9652.7072 | 7674.8454 | 4.7699 | 51 | 0.00014015 | 867 | 1674.4804 | 533 | 0.19229 | 9.8065 | 361 | 0.05 | 1986
3855 | SAND CREEK 11037140 | 254601103 | SAND CREEK 1103 | 7140 | FALSE | 42300.5526 | 42300.5526 | 26.29 | 296 | 2.8237e-05 | 3453 | 6738.8921 | 14 | 0.19202 | 56.8394 | 362 | 3.46 | 546
5056 | BANGOR 110182350 | 103191101 | BANGOR 1101 | 82350 | FALSE | 33588.8136 | 31579.2765 | 19.6266 | 230 | 8.9019e-05 | 1948 | 2107.591 | 425 | 0.19196 | 44.1515 | 363 | 0.3 | 1019
523 | DUNLAP 11037220 | 254061103 | DUNLAP 1103 | 7220 | FALSE | 39952.2483 | 39952.2483 | 24.8305 | 188 | 4.2565e-05 | 3217 | 4516.9217 | 107 | 0.19171 | 36.0414 | 364 | 0.06 | 1901
8426 | FORT ROSS 1121CB | 42851121 | FORT ROSS 1121 | CB | TRUE | 25.9334 | 25.9334 | 0.016118 | 1 | 0.00013855 | 888 | 1382.2827 | 648 | 0.19152 | 0.19152 | 365 | 0.05 | 1929
8629 | FOOTHILL 1101645910 | 182951101 | FOOTHILL 1101 | 645910 | TRUE | 3990.9244 | 774.6277 | 0.48143 | 14 | 0.00012447 | 1110 | 1323.2798 | 673 | 0.19134 | 2.6788 | 366 |  | 3245
7469 | PALMER 110198478 | 183031101 | PALMER 1101 | 98478 | FALSE | 9678.6987 | 9678.6987 | 6.0154 | 34 | 6.1513e-05 | 2732 | 3101.9251 | 253 | 0.19124 | 6.5022 | 367 | 0.06 | 1824
5366 | WYANDOTTE 11095607 | 102911109 | WYANDOTTE 1109 | 5607 | FALSE | 10708.8001 | 7265.9446 | 4.5158 | 71 | 6.7647e-05 | 2544 | 3213.7492 | 235 | 0.19115 | 13.5714 | 368 | 0.05 | 2002
9473 | HARTLEY 1102524 | 43211102 | HARTLEY 1102 | 524 | TRUE | 4106.6103 | 399.4552 | 0.24826 | 31 | 8.7723e-05 | 1992 | 2173.4374 | 408 | 0.19015 | 5.8946 | 369 | 0.71 | 803
6494 | WISE 1102697216 | 152271102 | WISE 1102 | 697216 | FALSE | 21374.2842 | 21374.2842 | 13.2842 | 145 | 8.8971e-05 | 1951 | 1998.7247 | 456 | 0.18992 | 27.5378 | 370 | 1.72 | 648
4257 | REDBUD 1102CB | 43191102 | REDBUD 1102 | CB | FALSE | 32077.0701 | 28146.4256 | 17.4931 | 170 | 9.0631e-05 | 1893 | 2204.8048 | 402 | 0.18973 | 32.2538 | 371 | 5.76 | 479
9558 | BRENTWOOD 21056512 | 14592105 | BRENTWOOD 2105 | 6512 | FALSE | 1047.7996 | 1047.7996 | 0.65121 | 5 | 6.0555e-05 | 2761 | 1094.509 | 777 | 0.18909 | 0.94545 | 372 | 0.08 | 1593
10458 | DEL MAR 2109805882 | 152582109 | DEL MAR 2109 | 805882 | TRUE | 497.9369 | 477.3024 | 0.29665 | 6 | 0.00016012 | 642 | 1125.8811 | 766 | 0.18904 | 1.1343 | 373 |  | 3553
2068 | OLETA 11021228 | 163541102 | OLETA 1102 | 1228 | FALSE | 69440.241 | 17449.9174 | 10.8452 | 368 | 0.00011636 | 1263 | 1613.8231 | 557 | 0.18877 | 69.4681 | 374 | 0.04 | 2078
2280 | DESCHUTES 11011580 | 103351101 | DESCHUTES 1101 | 1580 | FALSE | 80785.153 | 76365.8976 | 47.4617 | 383 | 0.00012062 | 1174 | 1821.2183 | 501 | 0.18779 | 71.9249 | 375 | 0.11 | 1451
6271 | COTTONWOOD 110131500 | 102931101 | COTTONWOOD 1101 | 31500 | FALSE | 18887.7142 | 7501.4293 | 4.6622 | 111 | 5.0427e-05 | 3030 | 3238.0724 | 229 | 0.18759 | 20.823 | 376 | 0.02 | 2550
449 | CLAYTON 221296224 | 12022212 | CLAYTON 2212 | 96224 | FALSE | 31213.3049 | 31213.3049 | 19.3992 | 174 | 6.6243e-05 | 2582 | 2944.2439 | 281 | 0.18755 | 32.6329 | 377 | 0.79 | 777
9225 | BUCKS CREEK 1102CB | 102211102 | BUCKS CREEK 1102 | CB | FALSE | 47599.3495 | 47599.3495 | 29.5832 | 121 | 0.00014957 | 743 | 1075.8896 | 783 | 0.1873 | 22.6633 | 378 | 0.07 | 1739
4556 | MARIPOSA 210237288 | 254452102 | MARIPOSA 2102 | 37288 | FALSE | 137232.3506 | 137232.3506 | 85.2905 | 678 | 4.4383e-05 | 3179 | 4408.5685 | 114 | 0.18718 | 126.9051 | 379 | 0.6 | 850
9851 | PANORAMA 1101885215 | 103461101 | PANORAMA 1101 | 885215 | FALSE | 3239.6899 | 3225.5678 | 2.0047 | 23 | 4.5966e-05 | 3138 | 3739.8152 | 178 | 0.18705 | 4.3021 | 380 |  | 3435
1129 | PETALUMA C 1109128 | 42631109 | PETALUMA C 1109 | 128 | FALSE | 60127.5406 | 56205.3694 | 34.9319 | 269 | 9.706e-05 | 1712 | 2077.9375 | 434 | 0.18687 | 50.2671 | 381 | 0.3 | 1014
5974 | DOBBINS 110169722 | 153741101 | DOBBINS 1101 | 69722 | FALSE | 10673.4289 | 10673.4289 | 6.6336 | 68 | 0.00014836 | 760 | 1483.0501 | 601 | 0.18675 | 12.6993 | 382 | 0.34 | 983
6088 | TYLER 110585132 | 103571105 | TYLER 1105 | 85132 | FALSE | 50093.0189 | 50093.0189 | 31.133 | 217 | 4.257e-05 | 3216 | 4662.7247 | 101 | 0.18633 | 40.4342 | 383 | 0.13 | 1354
6487 | STILLWATER 110248952 | 103561102 | STILLWATER 1102 | 48952 | FALSE | 17050.5619 | 17050.5619 | 10.597 | 123 | 0.00010175 | 1609 | 2266.9677 | 389 | 0.18561 | 22.8305 | 384 | 0.07 | 1722
7029 | PENRYN 1106212772 | 152561106 | PENRYN 1106 | 212772 | FALSE | 1753.1585 | 1609.198 | 1.0001 | 11 | 0.00010227 | 1596 | 1767.7041 | 510 | 0.18554 | 2.041 | 385 |  | 3087
7958 | GEYSERVILLE 110179788 | 42891101 | GEYSERVILLE 1101 | 79788 | FALSE | 67378.0299 | 63661.5746 | 39.5659 | 157 | 0.00011886 | 1209 | 1546.745 | 582 | 0.18551 | 29.1256 | 386 | 0.12 | 1399
2772 | WYANDOTTE 110913052 | 102911109 | WYANDOTTE 1109 | 13052 | FALSE | 31493.7185 | 31480.1828 | 19.5651 | 213 | 9.5258e-05 | 1758 | 2083.3172 | 433 | 0.18514 | 39.4358 | 387 | 0.12 | 1398
9699 | LOGAN CREEK 2102795010 | 103142102 | LOGAN CREEK 2102 | 795010 | FALSE | 6022.8068 | 5964.9276 | 3.7072 | 12 | 3.8042e-05 | 3300 | 5006.5635 | 76 | 0.18505 | 2.2206 | 388 |  | 3401
2290 | JESSUP 11021550 | 103441102 | JESSUP 1102 | 1550 | FALSE | 35703.4386 | 31009.474 | 19.2725 | 237 | 9.1451e-05 | 1860 | 2378.2716 | 365 | 0.18396 | 43.5983 | 389 | 0.06 | 1796
881 | RED BLUFF 11011556 | 103541101 | RED BLUFF 1101 | 1556 | FALSE | 64601.0138 | 61930.0824 | 38.4898 | 411 | 5.2815e-05 | 2977 | 3779.2145 | 173 | 0.18357 | 75.4478 | 390 | 0.18 | 1205
11061 | SAN LUIS OBISPO 1103365572 | 182631103 | SAN LUIS OBISPO 1103 | 365572 | TRUE | 696.8465 | 611.8589 | 0.38027 | 2 | 9.4733e-05 | 1772 | 2195.1828 | 403 | 0.18299 | 0.36597 | 391 |  | 3633
6935 | CEDAR CREEK 1101CB | 103321101 | CEDAR CREEK 1101 | CB | FALSE | 24813.8274 | 24813.8274 | 15.4219 | 127 | 0.00010514 | 1517 | 1354.0744 | 662 | 0.18254 | 23.1832 | 392 | 0.07 | 1749
3564 | JAMESON 1105466348 | 63801105 | JAMESON 1105 | 466348 | FALSE | 48812.3964 | 26039.2723 | 16.1835 | 294 | 9.3721e-05 | 1802 | 2063.8243 | 440 | 0.18223 | 53.5743 | 393 |  | 2838
2550 | COTTONWOOD 110335470 | 102931103 | COTTONWOOD 1103 | 35470 | FALSE | 40109.7772 | 33111.1919 | 20.5787 | 174 | 7.9998e-05 | 2205 | 2635.2321 | 323 | 0.18214 | 31.6926 | 394 | 1.26 | 692
2265 | BELL 1108CB | 152701108 | BELL 1108 | CB | TRUE | 9628.7582 | 0 | 0 | 83 | 0.00016581 | 584 | 955.774 | 856 | 0.18213 | 15.1167 | 395 | 0.04 | 2098
6694 | POTTER VALLEY P H 110537476 | 42281105 | POTTER VALLEY P H 1105 | 37476 | FALSE | 14076.4929 | 4231.6102 | 2.63 | 82 | 0.0001427 | 830 | 1332.1225 | 666 | 0.18107 | 14.8479 | 396 | 0.03 | 2366
2442 | CORRAL 110112612 | 162991101 | CORRAL 1101 | 12612 | FALSE | 32502.2662 | 31091.451 | 19.3235 | 195 | 7.8143e-05 | 2254 | 2667.8797 | 319 | 0.18095 | 35.2855 | 397 | 3.37 | 549
2325 | COTTONWOOD 11011510 | 102931101 | COTTONWOOD 1101 | 1510 | TRUE | 5333.1807 | 613.4018 | 0.38123 | 35 | 9.6024e-05 | 1728 | 1460.1171 | 611 | 0.18088 | 6.3309 | 398 | 0.5 | 894
6987 | TEMPLETON 2113641367 | 183052113 | TEMPLETON 2113 | 641367 | FALSE | 63879.2901 | 63879.2901 | 39.7012 | 278 | 6.9782e-05 | 2482 | 2628.7284 | 324 | 0.18079 | 50.2607 | 399 |  | 3081
1077 | CLAYTON 2212Y504R | 12022212 | CLAYTON 2212 | Y504R | FALSE | 18910.1435 | 18838.2347 | 11.708 | 112 | 7.2579e-05 | 2404 | 2414.4364 | 358 | 0.18021 | 20.1836 | 400 | 0.36 | 972
6538 | DUNLAP 11027060 | 254061102 | DUNLAP 1102 | 7060 | FALSE | 28760.1957 | 28760.1957 | 17.8746 | 162 | 4.1619e-05 | 3231 | 4251.992 | 132 | 0.18019 | 29.1914 | 401 | 0.05 | 2062
8223 | POSO MOUNTAIN 210448268 | 253642104 | POSO MOUNTAIN 2104 | 48268 | FALSE | 8165.6241 | 8152.5339 | 5.0668 | 30 | 2.8075e-05 | 3458 | 6541.9938 | 16 | 0.17977 | 5.3932 | 402 | 0.03 | 2409
7847 | OILFIELDS 11032757 | 182391103 | OILFIELDS 1103 | 2757 | FALSE | 4222.897 | 4222.897 | 2.6245 | 16 | 7.3477e-05 | 2384 | 2563.9177 | 338 | 0.1791 | 2.8656 | 403 | 0.07 | 1748
1905 | TIVY VALLEY 1107R1817 | 252941107 | TIVY VALLEY 1107 | R1817 | FALSE | 31029.2187 | 31029.2187 | 19.2848 | 145 | 3.1982e-05 | 3401 | 5976.6981 | 30 | 0.17888 | 25.9373 | 404 | 0.08 | 1648
3840 | SAND CREEK 11037070 | 254601103 | SAND CREEK 1103 | 7070 | FALSE | 28250.671 | 28250.671 | 17.5579 | 103 | 3.6129e-05 | 3333 | 5058.188 | 71 | 0.17873 | 18.4097 | 405 | 0.06 | 1902
1011 | CALISTOGA 1101890 | 42711101 | CALISTOGA 1101 | 890 | FALSE | 39539.8399 | 39211.6931 | 24.3702 | 203 | 0.00013749 | 903 | 1564.6167 | 573 | 0.17857 | 36.2505 | 406 | 0.6 | 852
1851 | KONOCTI 1102CB | 43311102 | KONOCTI 1102 | CB | FALSE | 15262.2312 | 6326.3363 | 3.9318 | 97 | 0.0001432 | 823 | 1232.8613 | 712 | 0.1779 | 17.2565 | 407 | 0.04 | 2123
7708 | COLUMBIA HILL 110190730 | 152471101 | COLUMBIA HILL 1101 | 90730 | FALSE | 13402.9331 | 13402.9331 | 8.33 | 77 | 0.00022241 | 309 | 801.5027 | 942 | 0.17712 | 13.6383 | 408 | 0.07 | 1738
10514 | SCE TEHACHAPI 1101CB | 258131101 | SCE TEHACHAPI 1101 | CB | FALSE | 1862.134 | 1862.134 | 1.1573 | 2 | 2.6503e-05 | 3479 | 5012.0663 | 75 | 0.17665 | 0.3533 | 409 | 0.11 | 1430
5375 | TASSAJARA 2109CB | 14662109 | TASSAJARA 2109 | CB | FALSE | 3124.8792 | 3111.1631 | 1.9336 | 12 | 0.00016891 | 568 | 1033.5651 | 803 | 0.17607 | 2.1128 | 410 | 0.03 | 2391
8181 | APPLE HILL 210289934 | 153662102 | APPLE HILL 2102 | 89934 | FALSE | 8917.9013 | 8917.9013 | 5.5425 | 56 | 0.00022642 | 301 | 791.9341 | 950 | 0.17581 | 9.8455 | 411 | 0.04 | 2125
3827 | HIGGINS 1109594 | 152691109 | HIGGINS 1109 | 594 | FALSE | 23079.0447 | 23079.0447 | 14.3437 | 155 | 0.00011929 | 1200 | 1640.4713 | 546 | 0.17563 | 27.2219 | 412 | 0.16 | 1253
329 | CORNING 110253184 | 103331102 | CORNING 1102 | 53184 | FALSE | 51204.6527 | 51204.6527 | 31.8239 | 123 | 4.4635e-05 | 3174 | 4517.1008 | 106 | 0.17544 | 21.5791 | 413 | 0.06 | 1844
6969 | PETALUMA C 1108208 | 42631108 | PETALUMA C 1108 | 208 | FALSE | 20077.9466 | 20077.9466 | 12.4785 | 95 | 9.3548e-05 | 1810 | 1783.8562 | 508 | 0.1754 | 16.663 | 414 | 11.75 | 382
8229 | GARBERVILLE 11012026 | 192221101 | GARBERVILLE 1101 | 2026 | FALSE | 10220.4249 | 10220.4249 | 6.352 | 26 | 0.00034659 | 95 | 363.8152 | 1347 | 0.17512 | 4.5532 | 415 | 0.84 | 768
8173 | ZACA 1101CB | 182681101 | ZACA 1101 | CB | FALSE | 17435.9444 | 12032.4791 | 7.4782 | 60 | 6.3071e-05 | 2678 | 1838.5396 | 494 | 0.17499 | 10.4995 | 416 | 0.03 | 2401
5131 | PHILO 11013700 | 42601101 | PHILO 1101 | 3700 | FALSE | 29156.0449 | 29156.0449 | 18.1206 | 116 | 0.00013347 | 952 | 1560.5823 | 576 | 0.17472 | 20.2673 | 417 | 0.06 | 1905
908 | PUTAH CREEK 1102710384 | 63681102 | PUTAH CREEK 1102 | 710384 | FALSE | 15468.9282 | 8584.2298 | 5.3351 | 84 | 5.8195e-05 | 2830 | 3710.5415 | 182 | 0.17469 | 14.6739 | 418 |  | 2697
9983 | JAMESON 1105913400 | 63801105 | JAMESON 1105 | 913400 | TRUE | 1667.834 | 172.3529 | 0.10712 | 14 | 0.00011832 | 1223 | 1563.2661 | 575 | 0.17457 | 2.444 | 419 |  | 3465
6899 | FORT SEWARD 11211690 | 192321121 | FORT SEWARD 1121 | 1690 | FALSE | 26217.8201 | 17377.7027 | 10.8003 | 77 | 0.0001954 | 415 | 901.067 | 883 | 0.17449 | 13.4358 | 420 | 7.44 | 444
2810 | OAKHURST 110110090 | 254421101 | OAKHURST 1101 | 10090 | FALSE | 70938.5406 | 70938.5406 | 44.0886 | 435 | 5.7014e-05 | 2861 | 3810.3636 | 167 | 0.17437 | 75.8506 | 421 | 0.3 | 1021
8488 | BROWNS VALLEY 1101CB | 152921101 | BROWNS VALLEY 1101 | CB | FALSE | 4580.4088 | 3639.3631 | 2.2619 | 17 | 0.00012727 | 1059 | 1563.9973 | 574 | 0.1743 | 2.9631 | 422 |  | 3230
1886 | REDBUD 1101323962 | 43191101 | REDBUD 1101 | 323962 | FALSE | 46007.9913 | 33116.5425 | 20.5821 | 282 | 7.3879e-05 | 2363 | 2674.5475 | 317 | 0.17389 | 49.0357 | 423 | 22.52 | 293
7655 | SHINGLE SPRINGS 210851476 | 153652108 | SHINGLE SPRINGS 2108 | 51476 | FALSE | 10437.2128 | 7926.327 | 4.9262 | 74 | 9.4268e-05 | 1787 | 2122.2216 | 419 | 0.1736 | 12.8462 | 424 | 14.32 | 355
6143 | OILFIELDS 1103N64 | 182391103 | OILFIELDS 1103 | N64 | FALSE | 20207.5385 | 17721.3198 | 11.0139 | 101 | 0.00011489 | 1302 | 1611.5581 | 558 | 0.17314 | 17.4874 | 425 | 0.05 | 2025
3312 | OLETA 11011217 | 163541101 | OLETA 1101 | 1217 | FALSE | 27736.9205 | 22843.3853 | 14.1973 | 116 | 5.896e-05 | 2808 | 3212.896 | 236 | 0.17295 | 20.0623 | 426 | 2.25 | 617
10420 | SANTA YNEZ 1101673618 | 182721101 | SANTA YNEZ 1101 | 673618 | TRUE | 533.16 | 171.3788 | 0.10651 | 4 | 5.0101e-05 | 3035 | 3451.8103 | 207 | 0.17294 | 0.69175 | 427 |  | 3547
50 | MARIPOSA 210135244 | 254452101 | MARIPOSA 2101 | 35244 | FALSE | 28098.7686 | 28098.7686 | 17.4635 | 146 | 7.6076e-05 | 2306 | 1918.8043 | 468 | 0.17286 | 25.237 | 428 | 0.1 | 1464
6824 | MARIPOSA 21021960 | 254452102 | MARIPOSA 2102 | 1960 | FALSE | 39696.7204 | 39696.7204 | 24.6717 | 223 | 4.465e-05 | 3171 | 4411.9471 | 113 | 0.17242 | 38.4488 | 429 | 0.42 | 933
7293 | WISE 11022234 | 152271102 | WISE 1102 | 2234 | FALSE | 24349.9914 | 24349.9914 | 15.1336 | 179 | 8.3357e-05 | 2123 | 2208.9033 | 401 | 0.17198 | 30.784 | 430 | 1.04 | 723
6103 | CALPELLA 1102421412 | 43411102 | CALPELLA 1102 | 421412 | FALSE | 5653.9032 | 1616.3093 | 1.0045 | 38 | 0.00012063 | 1173 | 1137.8972 | 758 | 0.17127 | 6.5083 | 431 |  | 3003
8262 | DESCHUTES 11019722 | 103351101 | DESCHUTES 1101 | 9722 | FALSE | 7647.7388 | 5139.2872 | 3.1941 | 55 | 9.2715e-05 | 1828 | 2011.1796 | 454 | 0.17084 | 9.3959 | 432 | 2.06 | 625
3350 | OAKHURST 110310570 | 254421103 | OAKHURST 1103 | 10570 | FALSE | 15440.8056 | 15440.8056 | 9.5965 | 92 | 5.2246e-05 | 2985 | 3374.5233 | 214 | 0.17053 | 15.6885 | 433 | 0.28 | 1043
7252 | OILFIELDS 1103N42 | 182391103 | OILFIELDS 1103 | N42 | FALSE | 9607.0794 | 5997.3144 | 3.7274 | 30 | 9.7321e-05 | 1705 | 2091.1209 | 429 | 0.17017 | 5.105 | 434 | 0 | 2631
2738 | SAN BENITO 2101221165 | 182742101 | SAN BENITO 2101 | 221165 | FALSE | 7814.4254 | 7056.9288 | 4.3859 | 39 | 7.1264e-05 | 2439 | 2286.9555 | 387 | 0.17016 | 6.6364 | 435 |  | 2797
10162 | MADISON 210113372 | 63172101 | MADISON 2101 | 13372 | FALSE | 6191.0561 | 6152.1597 | 3.8236 | 5 | 3.5403e-05 | 3342 | 4181.8896 | 139 | 0.17014 | 0.85069 | 436 | 1.32 | 686
4788 | COTTONWOOD 11039072 | 102931103 | COTTONWOOD 1103 | 9072 | FALSE | 46343.9208 | 46343.9208 | 28.8029 | 279 | 4.9258e-05 | 3057 | 3602.3143 | 190 | 0.1698 | 47.3736 | 437 | 4.2 | 524
10660 | CLAYTON 2212334476 | 12022212 | CLAYTON 2212 | 334476 | TRUE | 102.0354 | 89.9428 | 0.0559 | 2 | 3.6826e-05 | 3318 | 3174.6241 | 245 | 0.16961 | 0.33922 | 438 |  | 3587
5708 | HARTLEY 1101658 | 43211101 | HARTLEY 1101 | 658 | FALSE | 21722.426 | 4561.1197 | 2.8348 | 136 | 9.6216e-05 | 1727 | 1846.2822 | 492 | 0.16943 | 23.042 | 439 | 0.53 | 882
52 | HIGHLANDS 1103520 | 43361103 | HIGHLANDS 1103 | 520 | FALSE | 75123.246 | 75123.246 | 46.6894 | 437 | 8.2363e-05 | 2144 | 2644.041 | 320 | 0.16915 | 73.9165 | 440 | 35.85 | 210
5485 | ZACA 1102CB | 182681102 | ZACA 1102 | CB | FALSE | 33441.4577 | 25226.3338 | 15.6783 | 190 | 6.5983e-05 | 2589 | 2246.0111 | 394 | 0.16908 | 32.1248 | 441 | 5.92 | 477
2709 | CHOLAME 2102X10 | 182562102 | CHOLAME 2102 | X10 | FALSE | 70912.2192 | 34475.596 | 21.4267 | 156 | 7.3071e-05 | 2393 | 2615.2408 | 327 | 0.16893 | 26.3532 | 442 | 0 | 2634
2509 | HIGGINS 111051794 | 152691110 | HIGGINS 1110 | 51794 | FALSE | 6308.4167 | 6303.8446 | 3.9179 | 32 | 0.00021523 | 339 | 651.61 | 1061 | 0.16883 | 5.4026 | 443 | 0.05 | 1924
3144 | MORGAN HILL 2105XR564 | 83242105 | MORGAN HILL 2105 | XR564 | FALSE | 11653.8006 | 9126.8572 | 5.6724 | 81 | 0.0001173 | 1241 | 1539.4612 | 583 | 0.16792 | 13.6018 | 444 | 0.06 | 1891
8832 | PEORIA 17046090 | 163781704 | PEORIA 1704 | 6090 | TRUE | 1284.821 | 879.5421 | 0.54664 | 10 | 0.00015776 | 667 | 641.9698 | 1070 | 0.16726 | 1.6726 | 445 | 0.04 | 2133
6712 | CORNING 110182846 | 103331101 | CORNING 1101 | 82846 | FALSE | 8140.1207 | 7626.8316 | 4.7401 | 61 | 4.657e-05 | 3125 | 3781.4967 | 171 | 0.16626 | 10.1421 | 446 | 0.09 | 1543
3069 | NARROWS 21052228 | 153132105 | NARROWS 2105 | 2228 | FALSE | 34201.7241 | 33727.1471 | 20.9616 | 199 | 0.0001094 | 1423 | 1826.2902 | 498 | 0.16595 | 33.0243 | 447 | 0.19 | 1187
10116 | SANTA YNEZ 1104117616 | 182721104 | SANTA YNEZ 1104 | 117616 | TRUE | 584.7856 | 298.3487 | 0.18542 | 5 | 0.00010782 | 1453 | 3364.4337 | 215 | 0.16564 | 0.82819 | 448 |  | 3494
10070 | SILVERADO 2102772792 | 43432102 | SILVERADO 2102 | 772792 | FALSE | 4440.4408 | 3782.0495 | 2.3506 | 19 | 0.00011586 | 1274 | 1705.2974 | 522 | 0.16509 | 3.1366 | 449 |  | 3485
6113 | MIDDLETOWN 1101439572 | 43141101 | MIDDLETOWN 1101 | 439572 | FALSE | 2069.8545 | 1977.3978 | 1.229 | 18 | 0.00012277 | 1136 | 1750.9686 | 514 | 0.16479 | 2.9663 | 450 |  | 3004
1940 | NORTH BRANCH 1101TS1115 | 163231101 | NORTH BRANCH 1101 | TS1115 | FALSE | 28340.5083 | 28340.5083 | 17.6137 | 147 | 6.6142e-05 | 2584 | 2220.2472 | 396 | 0.16462 | 24.1996 | 451 | 0.06 | 1872
7043 | ANDERSON 1101514412 | 103261101 | ANDERSON 1101 | 514412 | FALSE | 1675.5188 | 1659.5168 | 1.0314 | 5 | 8.0594e-05 | 2190 | 2318.4458 | 382 | 0.16405 | 0.82024 | 452 |  | 3090
7318 | PUEBLO 2102226562 | 43292102 | PUEBLO 2102 | 226562 | FALSE | 1660.7794 | 1371.9928 | 0.8527 | 7 | 8.6131e-05 | 2031 | 1632.6529 | 550 | 0.16403 | 1.1482 | 453 |  | 3116
9693 | WILDWOOD 110198896 | 103611101 | WILDWOOD 1101 | 98896 | FALSE | 8090.5275 | 8090.5275 | 5.0283 | 25 | 7.975e-05 | 2213 | 2478.9758 | 348 | 0.16402 | 4.1004 | 454 | 0.04 | 2181
8907 | SHINGLE SPRINGS 1103CB | 153651103 | SHINGLE SPRINGS 1103 | CB | FALSE | 19101.7778 | 10648.1095 | 6.6178 | 143 | 0.00016037 | 641 | 1368.6904 | 653 | 0.16378 | 23.42 | 455 | 0.24 | 1101
3737 | KESWICK 110148480 | 103451101 | KESWICK 1101 | 48480 | FALSE | 16927.9852 | 16927.9852 | 10.5208 | 125 | 0.00013445 | 937 | 1828.9756 | 497 | 0.16355 | 20.4433 | 456 | 0.7 | 806
9178 | CORNING 1102915324 | 103331102 | CORNING 1102 | 915324 | FALSE | 5487.5306 | 3584.8296 | 2.228 | 27 | 4.7601e-05 | 3097 | 3729.4821 | 179 | 0.16319 | 4.406 | 457 |  | 3321
9985 | BOLINAS 1101530 | 42261101 | BOLINAS 1101 | 530 | FALSE | 17644.1656 | 17644.1656 | 10.9659 | 23 | 0.00014892 | 752 | 1687.6433 | 526 | 0.16273 | 3.7427 | 458 | 0.71 | 801
10086 | NAPA 1102561208 | 42021102 | NAPA 1102 | 561208 | FALSE | 4547.6852 | 1347.5454 | 0.8375 | 15 | 0.0001103 | 1407 | 1867.3968 | 484 | 0.1626 | 2.439 | 459 |  | 3487
7995 | HOPLAND 110194006 | 42251101 | HOPLAND 1101 | 94006 | FALSE | 24566.5609 | 22341.6897 | 13.8855 | 112 | 0.00010255 | 1585 | 1667.7925 | 536 | 0.1626 | 18.2107 | 460 | 0.05 | 1968
5192 | HIGHLANDS 1103CB | 43361103 | HIGHLANDS 1103 | CB | FALSE | 19725.7628 | 17048.207 | 10.5955 | 144 | 0.00010337 | 1563 | 1745.3469 | 516 | 0.16238 | 23.3827 | 461 | 0.11 | 1421
10927 | SCE REFUGIO 1701CB | 188071701 | SCE REFUGIO 1701 | CB | TRUE | 3.6129 | 3.6129 | 0.0022454 | 1 | 3.2861e-05 | 3387 | 4925.3659 | 82 | 0.16185 | 0.16185 | 462 |  | 3620
1961 | NARROWS 210534069 | 153132105 | NARROWS 2105 | 34069 | FALSE | 25331.8473 | 25331.8473 | 15.7438 | 156 | 6.2676e-05 | 2694 | 2622.4246 | 326 | 0.16138 | 25.1758 | 463 | 0.09 | 1525
11018 | CLAY 110398680 | 163341103 | CLAY 1103 | 98680 | TRUE | 46.5973 | 46.5973 | 0.02896 | 1 | 7.2821e-05 | 2397 | 2215.7621 | 399 | 0.16135 | 0.16135 | 464 |  | 3628
5283 | ANDERSON 11011752 | 103261101 | ANDERSON 1101 | 1752 | FALSE | 16018.6134 | 13551.3973 | 8.4222 | 96 | 9.1598e-05 | 1854 | 2012.9288 | 453 | 0.16096 | 15.4521 | 465 | 0.04 | 2161
4672 | LOW GAP 110137498 | 192411101 | LOW GAP 1101 | 37498 | FALSE | 26197.7415 | 26197.7415 | 16.282 | 129 | 0.00018072 | 507 | 890.6369 | 887 | 0.16073 | 20.7336 | 466 | 0.07 | 1723
1841 | NARROWS 21057203 | 153132105 | NARROWS 2105 | 7203 | FALSE | 30305.2229 | 29904.6733 | 18.5859 | 197 | 9.5139e-05 | 1761 | 1859.3118 | 489 | 0.16043 | 31.6051 | 467 | 0.19 | 1194
652 | MIDDLETOWN 110148212 | 43141101 | MIDDLETOWN 1101 | 48212 | FALSE | 17385.8137 | 17215.2669 | 10.6994 | 110 | 0.00014482 | 804 | 1204.0224 | 729 | 0.1603 | 17.6327 | 468 | 18.57 | 319
1128 | SAN MIGUEL 1106605393 | 182661106 | SAN MIGUEL 1106 | 605393 | FALSE | 40299.6716 | 33375.8865 | 20.7432 | 119 | 6.0131e-05 | 2768 | 2777.2648 | 302 | 0.15998 | 19.0373 | 469 |  | 2710
3473 | COTTONWOOD 11011610 | 102931101 | COTTONWOOD 1101 | 1610 | FALSE | 61821.9357 | 61821.9357 | 38.4226 | 295 | 4.3413e-05 | 3203 | 3907.4677 | 156 | 0.15996 | 47.1875 | 470 | 0.13 | 1340
1571 | SAN MIGUEL 1106428314 | 182661106 | SAN MIGUEL 1106 | 428314 | FALSE | 29650.5939 | 23673.0872 | 14.7129 | 73 | 6.2949e-05 | 2680 | 2640.9062 | 321 | 0.15993 | 11.675 | 471 |  | 2732
6359 | FROGTOWN 1702592404 | 163451702 | FROGTOWN 1702 | 592404 | FALSE | 2658.3381 | 2642.3361 | 1.6422 | 20 | 0.00017009 | 563 | 1297.0483 | 685 | 0.15963 | 3.1926 | 472 |  | 3024
7337 | WYANDOTTE 110738438 | 102911107 | WYANDOTTE 1107 | 38438 | FALSE | 27128.309 | 27128.309 | 16.8604 | 181 | 9.156e-05 | 1855 | 1679.673 | 529 | 0.15947 | 28.8637 | 473 | 0.08 | 1665
932 | MIDDLETOWN 1101548 | 43141101 | MIDDLETOWN 1101 | 548 | FALSE | 45554.629 | 44099.7789 | 27.4082 | 298 | 0.00022053 | 318 | 593.8352 | 1108 | 0.15935 | 47.4878 | 474 | 94.8 | 26
9379 | SUNOL 11018721 | 14241101 | SUNOL 1101 | 8721 | FALSE | 4901.8588 | 4400.8399 | 2.7351 | 29 | 5.0888e-05 | 3017 | 2918.1731 | 285 | 0.1593 | 4.6198 | 475 | 0.04 | 2186
1763 | RED BLUFF 110451238 | 103541104 | RED BLUFF 1104 | 51238 | FALSE | 63137.7388 | 63137.7388 | 39.2404 | 335 | 5.1642e-05 | 3004 | 2984.3431 | 269 | 0.15926 | 53.3509 | 476 | 2.31 | 614
1814 | CLOVERDALE 110184088 | 42821101 | CLOVERDALE 1101 | 84088 | FALSE | 28026.8017 | 25963.7603 | 16.1366 | 127 | 0.00012489 | 1101 | 1457.8018 | 614 | 0.15858 | 20.1391 | 477 |  | 2748
4306 | RAWSON 1103428534 | 103531103 | RAWSON 1103 | 428534 | FALSE | 8740.0932 | 7301.7326 | 4.5381 | 18 | 6.0557e-05 | 2760 | 3052.7595 | 263 | 0.15819 | 2.8474 | 478 |  | 2880
8922 | CLOVERDALE 1101964556 | 42821101 | CLOVERDALE 1101 | 964556 | FALSE | 8160.0956 | 8116.5647 | 5.0445 | 31 | 0.00010503 | 1527 | 1599.6673 | 562 | 0.15803 | 4.8988 | 479 |  | 3279
7447 | BELL 1109CB | 152701109 | BELL 1109 | CB | TRUE | 5601.5402 | 484.8416 | 0.30133 | 53 | 0.00031144 | 116 | 533.425 | 1167 | 0.15794 | 8.3708 | 480 | 0.06 | 1805
5391 | FITCH MOUNTAIN 111324918 | 42751113 | FITCH MOUNTAIN 1113 | 24918 | FALSE | 8843.8557 | 8843.8557 | 5.4965 | 49 | 0.00017491 | 529 | 1042.2333 | 799 | 0.1575 | 7.7177 | 481 | 40.7 | 183
6800 | GEYSERVILLE 1101705777 | 42891101 | GEYSERVILLE 1101 | 705777 | FALSE | 9890.0744 | 9890.0744 | 6.1467 | 46 | 0.00010551 | 1505 | 1615.1994 | 555 | 0.15746 | 7.2434 | 482 |  | 3062
29 | CALPELLA 1101542 | 43411101 | CALPELLA 1101 | 542 | FALSE | 54014.7834 | 53958.2006 | 33.5352 | 311 | 0.00010864 | 1433 | 1525.8914 | 585 | 0.15746 | 48.9707 | 483 | 0.08 | 1662
9538 | PIT NO 1 1101CB | 103721101 | PIT NO 1 1101 | CB | FALSE | 10535.3716 | 10535.3716 | 6.5478 | 40 | 5.8247e-05 | 2827 | 2851.4073 | 292 | 0.15705 | 6.2822 | 484 | 0.03 | 2244
7813 | CLOVERDALE 1102383183 | 42821102 | CLOVERDALE 1102 | 383183 | FALSE | 23681.1054 | 23566.6207 | 14.6467 | 53 | 0.0001153 | 1293 | 1780.7074 | 509 | 0.15687 | 8.3141 | 485 |  | 3164
8188 | LAKEVILLE 1102152632 | 43371102 | LAKEVILLE 1102 | 152632 | FALSE | 3427.183 | 3099.3949 | 1.9263 | 13 | 5.6437e-05 | 2875 | 2775.5237 | 304 | 0.15681 | 2.0385 | 486 |  | 3200
5065 | WOODACRE 11011456 | 43021101 | WOODACRE 1101 | 1456 | FALSE | 6155.4627 | 6155.4627 | 3.8256 | 46 | 0.00024152 | 242 | 701.6004 | 1021 | 0.15596 | 7.1739 | 487 | 25.79 | 270
5726 | POINT MORETTI 11015104 | 82931101 | POINT MORETTI 1101 | 5104 | FALSE | 2898.3737 | 2898.3737 | 1.8014 | 11 | 0.00010952 | 1422 | 1407.1508 | 634 | 0.15579 | 1.7137 | 488 | 0.08 | 1654
3142 | MOLINO 110279306 | 42571102 | MOLINO 1102 | 79306 | FALSE | 13157.0108 | 6087.9659 | 3.7837 | 73 | 0.00011173 | 1374 | 1345.2863 | 664 | 0.15551 | 11.352 | 489 | 5.6 | 482
10072 | BALCH NO 1 1101R372 | 252501101 | BALCH NO 1 1101 | R372 | FALSE | 6703.9319 | 6703.9319 | 4.1665 | 14 | 2.9441e-05 | 3432 | 4227.7566 | 136 | 0.15539 | 2.1754 | 490 | 0 | 2626
1776 | TIVY VALLEY 1107869946 | 252941107 | TIVY VALLEY 1107 | 869946 | FALSE | 47850.9 | 47850.9 | 29.7395 | 197 | 2.1689e-05 | 3527 | 7360.2383 | 8 | 0.15534 | 30.6024 | 491 | 4.76 | 507
9099 | BELL 1110946229 | 152701110 | BELL 1110 | 946229 | TRUE | 3345.1938 | 352.3912 | 0.21901 | 27 | 9.1153e-05 | 1875 | 1903.3963 | 476 | 0.15489 | 4.1819 | 492 |  | 3308
11045 | CLARK ROAD 1101CB | 103091101 | CLARK ROAD 1101 | CB | TRUE | 33.3215 | 28.7495 | 0.017868 | 2 | 0.00010268 | 1578 | 1672.4211 | 534 | 0.15464 | 0.30929 | 493 |  | 3632
1243 | SHINGLE SPRINGS 110419502 | 153651104 | SHINGLE SPRINGS 1104 | 19502 | FALSE | 92686.5675 | 72356.9682 | 44.9701 | 672 | 0.00010455 | 1541 | 1716.1429 | 520 | 0.15447 | 103.8019 | 494 | 25.98 | 269
3579 | WILLITS 1102CB | 42661102 | WILLITS 1102 | CB | FALSE | 15673.7726 | 8550.61 | 5.3142 | 114 | 0.00011244 | 1357 | 1000.9631 | 834 | 0.15412 | 17.5695 | 495 | 0.03 | 2253
6413 | UKIAH 1114408 | 42771114 | UKIAH 1114 | 408 | FALSE | 61335.3992 | 60046.2209 | 37.319 | 280 | 0.00011339 | 1336 | 1624.3846 | 553 | 0.15401 | 43.1236 | 496 | 0.16 | 1258
4125 | SAND CREEK 11037420 | 254601103 | SAND CREEK 1103 | 7420 | FALSE | 37320.8645 | 37320.8645 | 23.1951 | 263 | 2.746e-05 | 3465 | 5752.6874 | 39 | 0.15397 | 40.4954 | 497 | 0.11 | 1450
6897 | SALMON CREEK 110188998 | 43161101 | SALMON CREEK 1101 | 88998 | FALSE | 22218.0314 | 12794.9324 | 7.9521 | 116 | 8.749e-05 | 2000 | 1675.3538 | 531 | 0.15352 | 17.8079 | 498 | 12.75 | 368
4452 | SILVERADO 2102942170 | 43432102 | SILVERADO 2102 | 942170 | FALSE | 14564.2628 | 5038.647 | 3.1315 | 99 | 8.0364e-05 | 2195 | 1848.528 | 490 | 0.15348 | 15.1945 | 499 |  | 2892
59 | VACAVILLE 1111CB | 63601111 | VACAVILLE 1111 | CB | FALSE | 19525.0238 | 11777.3852 | 7.3197 | 154 | 0.00010262 | 1582 | 1549.2867 | 579 | 0.15336 | 23.6178 | 500 | 0.1 | 1453
5605 | SANTA YNEZ 1101Y52 | 182721101 | SANTA YNEZ 1101 | Y52 | FALSE | 33466.442 | 31529.2091 | 19.5955 | 141 | 6.2219e-05 | 2713 | 2469.9036 | 349 | 0.15332 | 21.6184 | 501 | 0.22 | 1124
4437 | STILLWATER 1102CB | 103561102 | STILLWATER 1102 | CB | FALSE | 40316.4241 | 40301.3395 | 25.0474 | 275 | 0.00012985 | 1011 | 1360.5287 | 658 | 0.15318 | 42.1242 | 502 | 0.14 | 1317
3264 | BEAR VALLEY 21059480 | 252192105 | BEAR VALLEY 2105 | 9480 | FALSE | 19971.3977 | 19971.3977 | 12.4123 | 80 | 7.4134e-05 | 2352 | 2457.1272 | 350 | 0.15314 | 12.251 | 503 | 0.05 | 1946
1519 | FROGTOWN 17021573 | 163451702 | FROGTOWN 1702 | 1573 | FALSE | 29066.997 | 29066.997 | 18.0653 | 156 | 6.9197e-05 | 2500 | 1984.6936 | 458 | 0.15282 | 23.8402 | 504 | 0.09 | 1514
1732 | NARROWS 21022220 | 153132102 | NARROWS 2102 | 2220 | FALSE | 45533.9477 | 44226.4373 | 27.4869 | 266 | 0.00015667 | 676 | 1115.795 | 768 | 0.15235 | 40.5244 | 505 | 0.28 | 1037
2529 | FULTON 1102287172 | 42561102 | FULTON 1102 | 287172 | FALSE | 42975.8424 | 32888.5181 | 20.4403 | 258 | 0.00014341 | 820 | 1064.6586 | 789 | 0.15216 | 39.2578 | 506 | 0.11 | 1432
9038 | OTTER 11022012 | 182941102 | OTTER 1102 | 2012 | FALSE | 16177.0749 | 14813.8509 | 9.2069 | 64 | 7.8985e-05 | 2236 | 2049.1767 | 445 | 0.15189 | 9.7211 | 507 | 0.03 | 2261
6205 | OILFIELDS 1103N48 | 182391103 | OILFIELDS 1103 | N48 | FALSE | 76703.6711 | 76703.6711 | 47.6716 | 292 | 5.999e-05 | 2778 | 2624.8703 | 325 | 0.15188 | 44.3489 | 508 | 0.11 | 1419
6912 | BANGOR 1101301886 | 103191101 | BANGOR 1101 | 301886 | FALSE | 12466.9499 | 4239.6365 | 2.635 | 90 | 8.8332e-05 | 1976 | 1844.2972 | 493 | 0.15165 | 13.6484 | 509 |  | 3073
10865 | PASO ROBLES 1103N04 | 182611103 | PASO ROBLES 1103 | N04 | TRUE | 859.5841 | 859.5841 | 0.53424 | 4 | 0.00013464 | 932 | 1420.9296 | 631 | 0.1516 | 0.60641 | 510 | 10.35 | 398
10126 | WINDSOR 1103701650 | 43501103 | WINDSOR 1103 | 701650 | FALSE | 1191.0562 | 1191.0562 | 0.74025 | 12 | 0.00018462 | 478 | 500.0347 | 1199 | 0.15159 | 1.8191 | 511 |  | 3496
2118 | LUCERNE 11031280 | 43351103 | LUCERNE 1103 | 1280 | FALSE | 37796.6985 | 12933.8174 | 8.0384 | 238 | 0.00011562 | 1283 | 1326.8732 | 670 | 0.1512 | 35.9845 | 512 | 0.03 | 2282
7467 | CORRAL 110214026 | 162991102 | CORRAL 1102 | 14026 | FALSE | 16308.5206 | 16308.5206 | 10.1358 | 101 | 6.4324e-05 | 2633 | 2347.8148 | 374 | 0.15084 | 15.2344 | 513 | 3.03 | 567
2447 | SAN LUIS OBISPO 110342344 | 182631103 | SAN LUIS OBISPO 1103 | 42344 | FALSE | 17541.9825 | 15185.6709 | 9.438 | 123 | 6.005e-05 | 2772 | 2518.1117 | 341 | 0.15077 | 18.5441 | 514 | 5.29 | 491
9162 | PUTAH CREEK 1105748272 | 63681105 | PUTAH CREEK 1105 | 748272 | FALSE | 6311.5498 | 1206.1255 | 0.74961 | 26 | 6.9164e-05 | 2501 | 2825.842 | 296 | 0.15028 | 3.9074 | 515 |  | 3317
6146 | PETALUMA C 1108618 | 42631108 | PETALUMA C 1108 | 618 | FALSE | 17470.7407 | 13890.2601 | 8.6329 | 119 | 8.8705e-05 | 1961 | 1646.4565 | 544 | 0.15 | 17.8498 | 516 | 3.18 | 555
7759 | BUELLTON 1101Y26 | 183041101 | BUELLTON 1101 | Y26 | FALSE | 25494.2608 | 24411.1885 | 15.1717 | 133 | 6.226e-05 | 2711 | 2408.6488 | 359 | 0.14946 | 19.8785 | 517 | 0.08 | 1586
8614 | WILLOW CREEK 110237374 | 192171102 | WILLOW CREEK 1102 | 37374 | FALSE | 3616.7474 | 3616.7474 | 2.2478 | 9 | 0.00024971 | 217 | 652.1813 | 1060 | 0.14938 | 1.3444 | 518 | 10.97 | 392
1351 | FULTON 11024522 | 42561102 | FULTON 1102 | 4522 | FALSE | 19482.3353 | 14178.9489 | 8.8123 | 128 | 0.00013265 | 968 | 1211.0142 | 727 | 0.14919 | 19.0963 | 519 | 1.62 | 661
5116 | APPLE HILL 210251792 | 153662102 | APPLE HILL 2102 | 51792 | FALSE | 15055.1772 | 15055.1772 | 9.3569 | 99 | 0.00012104 | 1164 | 1431.6373 | 622 | 0.14914 | 14.7646 | 520 | 0.08 | 1632
2803 | ZACA 1102Y48 | 182681102 | ZACA 1102 | Y48 | FALSE | 19054.6896 | 7064.3192 | 4.3905 | 157 | 6.9914e-05 | 2475 | 2423.7326 | 357 | 0.14907 | 23.4041 | 521 | 0.03 | 2278
453 | GARBERVILLE 11011604 | 192221101 | GARBERVILLE 1101 | 1604 | FALSE | 29168.7634 | 6733.9297 | 4.1852 | 166 | 0.00022087 | 316 | 698.8592 | 1023 | 0.14905 | 24.7419 | 522 | 0.05 | 1969
10386 | CALISTOGA 1101537148 | 42711101 | CALISTOGA 1101 | 537148 | TRUE | 2468.9992 | 923.0762 | 0.5737 | 14 | 8.9697e-05 | 1921 | 711.3098 | 1014 | 0.14902 | 2.0863 | 523 |  | 3541
1087 | GRASS VALLEY 11032180 | 152031103 | GRASS VALLEY 1103 | 2180 | FALSE | 71112.0664 | 71112.0664 | 44.1964 | 444 | 8.9044e-05 | 1947 | 1832.2635 | 495 | 0.1487 | 66.0238 | 524 | 0.31 | 1000
6232 | POSO MOUNTAIN 21012181 | 253642101 | POSO MOUNTAIN 2101 | 2181 | FALSE | 38165.6009 | 27116.6383 | 16.8531 | 120 | 3.7006e-05 | 3315 | 4260.274 | 131 | 0.14869 | 17.8426 | 525 | 0.05 | 2017
1083 | CLARK ROAD 11022044 | 103091102 | CLARK ROAD 1102 | 2044 | FALSE | 20271.6961 | 13688.923 | 8.5077 | 67 | 0.00011519 | 1295 | 1533.5317 | 584 | 0.14865 | 9.9595 | 526 | 0.03 | 2330
1119 | MERCED FALLS 110287352 | 252811102 | MERCED FALLS 1102 | 87352 | FALSE | 42830.7404 | 42830.7404 | 26.6195 | 215 | 7.6529e-05 | 2294 | 2120.5795 | 420 | 0.14862 | 31.9523 | 527 | 0.03 | 2333
3359 | WISE 1102307494 | 152271102 | WISE 1102 | 307494 | FALSE | 54418.6325 | 49958.7477 | 31.0496 | 279 | 7.0522e-05 | 2454 | 2167.8038 | 409 | 0.14841 | 41.4062 | 528 | 3.66 | 537
8461 | PUTAH CREEK 110264044 | 63681102 | PUTAH CREEK 1102 | 64044 | FALSE | 11992.1979 | 9649.0485 | 5.9969 | 46 | 6.4018e-05 | 2645 | 2318.9503 | 380 | 0.14834 | 6.8236 | 529 | 0.92 | 747
7436 | MENLO 110212249 | 24131102 | MENLO 1102 | 12249 | FALSE | 3869.5175 | 3869.5175 | 2.4049 | 25 | 0.0001396 | 877 | 1383.6803 | 645 | 0.14826 | 3.7065 | 530 | 0.06 | 1811
170 | NORTH BRANCH 110111206 | 163231101 | NORTH BRANCH 1101 | 11206 | FALSE | 28786.4552 | 28782.1678 | 17.8882 | 146 | 5.7399e-05 | 2853 | 3353.7714 | 217 | 0.14787 | 21.5893 | 531 | 7.09 | 451
2440 | VOLTA 110180454 | 102541101 | VOLTA 1101 | 80454 | FALSE | 51836.245 | 51220.5161 | 31.8338 | 254 | 8.7906e-05 | 1985 | 1652.3048 | 542 | 0.14786 | 37.5574 | 532 | 0.09 | 1550
6322 | SALMON CREEK 1101196 | 43161101 | SALMON CREEK 1101 | 196 | FALSE | 11699.1957 | 9030.0657 | 5.6122 | 36 | 5.8544e-05 | 2820 | 2429.7049 | 356 | 0.14755 | 5.3118 | 533 | 1.88 | 635
6558 | MOLINO 110266006 | 42571102 | MOLINO 1102 | 66006 | FALSE | 14550.7056 | 14550.7056 | 9.0433 | 98 | 0.00016119 | 629 | 1078.2399 | 782 | 0.14747 | 14.4519 | 534 | 51.49 | 116
6860 | GARBERVILLE 1101CB | 192221101 | GARBERVILLE 1101 | CB | FALSE | 14152.8775 | 11300.0596 | 7.023 | 87 | 0.00030831 | 120 | 452.1633 | 1245 | 0.14742 | 12.8257 | 535 | 0.09 | 1511
2892 | WYANDOTTE 11071026 | 102911107 | WYANDOTTE 1107 | 1026 | FALSE | 44906.7347 | 36171.5421 | 22.4808 | 273 | 7.2065e-05 | 2414 | 2265.0826 | 390 | 0.14732 | 40.2177 | 536 | 0.08 | 1587
1817 | COARSEGOLD 210410110 | 254432104 | COARSEGOLD 2104 | 10110 | FALSE | 79840.1784 | 79840.1784 | 49.621 | 518 | 7.1892e-05 | 2423 | 1946.3474 | 464 | 0.1471 | 76.1986 | 537 | 0.85 | 766
5315 | GIRVAN 11011636 | 103401101 | GIRVAN 1101 | 1636 | FALSE | 29887.6303 | 29071.18 | 18.0679 | 200 | 0.00012911 | 1025 | 1282.4693 | 688 | 0.14693 | 29.387 | 538 | 0.42 | 935
7739 | OILFIELDS 1103N40 | 182391103 | OILFIELDS 1103 | N40 | FALSE | 4749.4542 | 4628.046 | 2.8763 | 23 | 7.224e-05 | 2412 | 1911.8815 | 472 | 0.14681 | 3.3766 | 539 | 0.92 | 746
1598 | COTTONWOOD 11031348 | 102931103 | COTTONWOOD 1103 | 1348 | FALSE | 51267.8367 | 46964.6472 | 29.1887 | 357 | 6.4485e-05 | 2628 | 2847.109 | 293 | 0.14666 | 52.3583 | 540 | 0.1 | 1507
2008 | OAKHURST 11015490 | 254421101 | OAKHURST 1101 | 5490 | FALSE | 40241.3391 | 40241.3391 | 25.0102 | 276 | 5.4815e-05 | 2921 | 3287.8025 | 227 | 0.14657 | 40.4521 | 541 | 31.17 | 233
6294 | OLETA 1101239062 | 163541101 | OLETA 1101 | 239062 | FALSE | 22613.4239 | 19618.6008 | 12.193 | 113 | 7.6414e-05 | 2296 | 2401.1977 | 361 | 0.14634 | 16.5367 | 542 |  | 3021
6920 | LAYTONVILLE 110268436 | 42681102 | LAYTONVILLE 1102 | 68436 | FALSE | 14664.9715 | 14664.9715 | 9.1143 | 45 | 0.00011581 | 1278 | 1690.836 | 525 | 0.14627 | 6.582 | 543 | 3.52 | 544
1698 | GARBERVILLE 11022010 | 192221102 | GARBERVILLE 1102 | 2010 | FALSE | 10727.9171 | 10727.9171 | 6.6674 | 39 | 0.00053737 | 26 | 277.3564 | 1477 | 0.14585 | 5.6882 | 544 | 0.08 | 1579
2911 | SHINGLE SPRINGS 210819762 | 153652108 | SHINGLE SPRINGS 2108 | 19762 | FALSE | 8713.8007 | 7078.7756 | 4.3995 | 72 | 0.00017135 | 554 | 1134.0874 | 762 | 0.14549 | 10.4755 | 545 | 0.25 | 1082
2598 | ELK CREEK 11012008 | 102781101 | ELK CREEK 1101 | 2008 | FALSE | 29196.2282 | 9225.9589 | 5.734 | 154 | 5.6038e-05 | 2886 | 2966.3445 | 274 | 0.14517 | 22.3567 | 546 | 2.46 | 601
2127 | OILFIELDS 1103N44 | 182391103 | OILFIELDS 1103 | N44 | FALSE | 29207.7388 | 29207.7388 | 18.1527 | 109 | 8.2092e-05 | 2149 | 1862.5151 | 486 | 0.14496 | 15.8008 | 547 | 0.19 | 1171
381 | MOUNTAIN QUARRIES 21011102 | 152282101 | MOUNTAIN QUARRIES 2101 | 1102 | FALSE | 69889.6015 | 69889.6015 | 43.4367 | 431 | 0.00010803 | 1451 | 1375.9559 | 650 | 0.14479 | 62.4048 | 548 | 0.21 | 1154
3913 | CORNING 110164090 | 103331101 | CORNING 1101 | 64090 | FALSE | 21993.72 | 21993.72 | 13.6692 | 170 | 4.4336e-05 | 3181 | 3248.9701 | 228 | 0.1444 | 24.5486 | 549 | 4.94 | 501
2481 | BROWNS VALLEY 11011268 | 152921101 | BROWNS VALLEY 1101 | 1268 | FALSE | 17550.3384 | 17538.5447 | 10.9003 | 106 | 8.5846e-05 | 2035 | 1744.856 | 517 | 0.14435 | 15.3013 | 550 | 0.13 | 1351
948 | MARIPOSA 21029590 | 254452102 | MARIPOSA 2102 | 9590 | FALSE | 58387.0707 | 58387.0707 | 36.2878 | 387 | 6.1765e-05 | 2727 | 2433.9636 | 353 | 0.144 | 55.7277 | 551 | 0.28 | 1045
4109 | TEMPLETON 2113A60 | 183052113 | TEMPLETON 2113 | A60 | FALSE | 14423.3233 | 11709.0954 | 7.2773 | 88 | 8.0147e-05 | 2202 | 2043.3402 | 447 | 0.14391 | 12.6644 | 552 | 1.69 | 651
9361 | CLOVERDALE 1102429006 | 42821102 | CLOVERDALE 1102 | 429006 | FALSE | 3229.4467 | 3213.4446 | 1.9972 | 23 | 0.00015434 | 701 | 805.9602 | 934 | 0.1436 | 3.3029 | 553 | 0.04 | 2192
429 | COTTONWOOD 11021578 | 102931102 | COTTONWOOD 1102 | 1578 | FALSE | 56424.6884 | 48498.4276 | 30.142 | 269 | 5.3137e-05 | 2963 | 2721.7009 | 308 | 0.14355 | 38.6147 | 554 | 0.07 | 1761
3755 | INDIAN FLAT 1104CB | 252691104 | INDIAN FLAT 1104 | CB | FALSE | 20557.4413 | 20557.4413 | 12.7765 | 85 | 0.0001276 | 1055 | 1467.6776 | 609 | 0.14347 | 12.1951 | 555 | 0.15 | 1305
5039 | OREGON TRAIL 11031448 | 103521103 | OREGON TRAIL 1103 | 1448 | FALSE | 49484.9793 | 49484.9793 | 30.7551 | 232 | 9.5357e-05 | 1749 | 1437.1719 | 620 | 0.14347 | 33.2848 | 556 | 0.06 | 1912
5385 | MONTICELLO 110137384 | 43051101 | MONTICELLO 1101 | 37384 | FALSE | 15082.1187 | 15082.1187 | 9.3736 | 71 | 6.7163e-05 | 2554 | 2257.655 | 391 | 0.14324 | 10.17 | 557 | 0.13 | 1350
9323 | POSO MOUNTAIN 21013990 | 253642101 | POSO MOUNTAIN 2101 | 3990 | FALSE | 8945.4958 | 6963.5326 | 4.3279 | 25 | 3.4486e-05 | 3361 | 3780.3852 | 172 | 0.14297 | 3.5744 | 558 | 0.05 | 1957
8609 | PETALUMA C 1108636 | 42631108 | PETALUMA C 1108 | 636 | FALSE | 15178.9816 | 15178.9816 | 9.4338 | 108 | 0.00010078 | 1628 | 1486.0094 | 600 | 0.14279 | 15.4213 | 559 | 5.46 | 486
9301 | VOLTA 110165764 | 102541101 | VOLTA 1101 | 65764 | FALSE | 16669.4005 | 16669.4005 | 10.3601 | 34 | 4.7811e-05 | 3096 | 3350.0688 | 218 | 0.1423 | 4.8382 | 560 | 0.03 | 2268
10478 | STONE CORRAL 1110189488 | 252921110 | STONE CORRAL 1110 | 189488 | FALSE | 1343.2605 | 1327.2585 | 0.8249 | 8 | 2.6518e-05 | 3478 | 5673.1262 | 44 | 0.14211 | 1.1369 | 561 |  | 3556
1096 | CABRILLO 1103Y12 | 183101103 | CABRILLO 1103 | Y12 | FALSE | 49636.2362 | 42701.7878 | 26.5393 | 274 | 4.9026e-05 | 3063 | 2917.17 | 286 | 0.14205 | 38.9225 | 562 | 31.53 | 230
9878 | CEDAR CREEK 1101451856 | 103321101 | CEDAR CREEK 1101 | 451856 | TRUE | 105.147 | 105.147 | 0.065349 | 2 | 5.0483e-05 | 3022 | 2807.0375 | 299 | 0.14172 | 0.28345 | 563 |  | 3442
9745 | TASSAJARA 21126392 | 14662112 | TASSAJARA 2112 | 6392 | FALSE | 8838.9848 | 8838.9848 | 5.4935 | 37 | 7.9657e-05 | 2215 | 1801.3357 | 505 | 0.14162 | 5.2399 | 564 | 16.9 | 336
4697 | CALISTOGA 1101242919 | 42711101 | CALISTOGA 1101 | 242919 | FALSE | 2111.493 | 2111.493 | 1.3123 | 15 | 0.00019735 | 407 | 815.191 | 928 | 0.14151 | 2.1226 | 565 |  | 2911
5376 | FORT SEWARD 1121CB | 192321121 | FORT SEWARD 1121 | CB | FALSE | 14807.5224 | 14807.5224 | 9.2029 | 54 | 0.00019854 | 400 | 804.6312 | 935 | 0.14139 | 7.6353 | 566 | 0.07 | 1742
4876 | SISQUOC 1102M54 | 182811102 | SISQUOC 1102 | M54 | FALSE | 48740.6445 | 31884.2274 | 19.8162 | 166 | 5.3034e-05 | 2966 | 2348.1035 | 373 | 0.14114 | 23.4289 | 567 | 0.02 | 2478
4881 | LINCOLN 11042070 | 153701104 | LINCOLN 1104 | 2070 | FALSE | 46879.1188 | 28951.6433 | 17.9936 | 303 | 7.9201e-05 | 2227 | 1863.8372 | 485 | 0.14111 | 42.7554 | 568 | 2.76 | 584
8866 | SAN RAMON 2101CB | 14232101 | SAN RAMON 2101 | CB | FALSE | 1579.2012 | 1277.3495 | 0.79388 | 11 | 0.0001171 | 1244 | 1362.5146 | 655 | 0.14108 | 1.5519 | 569 | 0.61 | 848
10487 | HIGGINS 1107746082 | 152691107 | HIGGINS 1107 | 746082 | FALSE | 1306.1318 | 1306.1318 | 0.81177 | 6 | 0.00011547 | 1287 | 1442.5612 | 617 | 0.14016 | 0.84097 | 570 | 0.11 | 1442
3139 | WILLITS 11044650 | 42661104 | WILLITS 1104 | 4650 | FALSE | 9890.161 | 6190.488 | 3.8474 | 80 | 0.0001146 | 1305 | 915.7398 | 878 | 0.14007 | 11.2058 | 571 | 0.03 | 2344
474 | COTTONWOOD 11031616 | 102931103 | COTTONWOOD 1103 | 1616 | FALSE | 79228.8196 | 75536.2374 | 46.9461 | 454 | 5.1839e-05 | 2998 | 2965.2949 | 276 | 0.13915 | 63.1735 | 572 | 3.66 | 538
4424 | POSO MOUNTAIN 21014456 | 253642101 | POSO MOUNTAIN 2101 | 4456 | FALSE | 37862.2156 | 37862.2156 | 23.5315 | 102 | 2.7821e-05 | 3462 | 5239.6007 | 58 | 0.13881 | 14.1582 | 573 | 0.11 | 1440
7546 | LAYTONVILLE 11022502 | 42681102 | LAYTONVILLE 1102 | 2502 | FALSE | 28650.0789 | 28650.0789 | 17.8061 | 80 | 0.00011917 | 1201 | 1243.1177 | 705 | 0.13859 | 11.0874 | 574 | 0.04 | 2183
7849 | BEAR VALLEY 21014160 | 252192101 | BEAR VALLEY 2101 | 4160 | FALSE | 36723.9834 | 36723.9834 | 22.8241 | 192 | 7.1016e-05 | 2443 | 2062.9169 | 441 | 0.13839 | 26.57 | 575 | 0.07 | 1759
10064 | WILLOW PASS 1101152874 | 13911101 | WILLOW PASS 1101 | 152874 | TRUE | 1306.3422 | 982.3028 | 0.61051 | 10 | 6.4919e-05 | 2611 | 2044.3409 | 446 | 0.13803 | 1.3803 | 576 |  | 3483
2621 | LINCOLN 1101186060 | 153701101 | LINCOLN 1101 | 186060 | FALSE | 24068.765 | 17542.5963 | 10.9028 | 161 | 0.00011716 | 1242 | 1235.1524 | 709 | 0.13732 | 22.1085 | 577 |  | 2791
5254 | SHINGLE SPRINGS 21092679 | 153652109 | SHINGLE SPRINGS 2109 | 2679 | FALSE | 11435.2637 | 11435.2637 | 7.1071 | 70 | 6.4611e-05 | 2619 | 2176.5839 | 406 | 0.13732 | 9.6123 | 578 | 23.85 | 281
3959 | SILVERADO 210234959 | 43432102 | SILVERADO 2102 | 34959 | FALSE | 42625.8356 | 41473.2756 | 25.7758 | 205 | 7.1759e-05 | 2428 | 1907.4668 | 473 | 0.13657 | 27.9958 | 579 | 0.46 | 910
4389 | VOLTA 11011516 | 102541101 | VOLTA 1101 | 1516 | FALSE | 41402.7558 | 40856.6045 | 25.3925 | 123 | 9.2444e-05 | 1832 | 1638.3577 | 549 | 0.13616 | 16.7471 | 580 | 0.06 | 1821
9812 | CURTIS 170411300 | 163351704 | CURTIS 1704 | 11300 | FALSE | 5912.6947 | 5912.6947 | 3.6748 | 41 | 0.00013924 | 881 | 1480.6406 | 604 | 0.1361 | 5.5803 | 581 | 0.19 | 1177
4676 | NARROWS 210551582 | 153132105 | NARROWS 2105 | 51582 | FALSE | 15330.2671 | 15330.2671 | 9.5278 | 105 | 0.00014185 | 842 | 981.2465 | 843 | 0.13574 | 14.2523 | 582 | 0.04 | 2150
430 | TEJON 1102732836 | 252931102 | TEJON 1102 | 732836 | FALSE | 24952.5776 | 18788.6293 | 11.6772 | 154 | 4.1312e-05 | 3239 | 3303.5879 | 224 | 0.1353 | 20.8364 | 583 |  | 2673
4932 | MONTICELLO 1101720 | 43051101 | MONTICELLO 1101 | 720 | FALSE | 13087.7745 | 10923.6575 | 6.7891 | 70 | 6.3429e-05 | 2663 | 2299.4316 | 384 | 0.1353 | 9.4707 | 584 | 2.79 | 580
6310 | RIO DELL 11024230 | 192251102 | RIO DELL 1102 | 4230 | FALSE | 36923.3874 | 36847.6248 | 22.9009 | 59 | 0.00036561 | 80 | 373.6796 | 1331 | 0.13512 | 7.9721 | 585 | 0.02 | 2536
517 | CLARKSVILLE 210413352 | 153612104 | CLARKSVILLE 2104 | 13352 | FALSE | 58907.8743 | 55896.819 | 34.7401 | 409 | 0.00012489 | 1100 | 1100.974 | 774 | 0.13486 | 55.1568 | 586 | 30.41 | 238
7402 | MARIPOSA 2102594143 | 254452102 | MARIPOSA 2102 | 594143 | TRUE | 6633.044 | 814.5641 | 0.50625 | 60 | 9.5762e-05 | 1734 | 729.5737 | 990 | 0.13461 | 8.0769 | 587 |  | 3123
19 | CLEAR LAKE 1101406 | 42141101 | CLEAR LAKE 1101 | 406 | FALSE | 53036.2911 | 19984.6537 | 12.4205 | 312 | 8.8388e-05 | 1975 | 1508.2873 | 594 | 0.1343 | 41.9011 | 588 | 0.13 | 1362
4720 | DUNLAP 11027849F | 254061102 | DUNLAP 1102 | 7849F | FALSE | 13949.6344 | 13949.6344 | 8.6698 | 61 | 3.1633e-05 | 3406 | 5019.3612 | 73 | 0.13395 | 8.1711 | 589 | 0.04 | 2222
6125 | JESSUP 1103348657 | 103441103 | JESSUP 1103 | 348657 | FALSE | 3761.8937 | 3253.8359 | 2.0223 | 29 | 8.3622e-05 | 2107 | 2006.4651 | 455 | 0.13388 | 3.8825 | 590 |  | 3007
9100 | BANGOR 1101870548 | 103191101 | BANGOR 1101 | 870548 | FALSE | 8185.9487 | 8185.9487 | 5.0876 | 56 | 0.00010519 | 1515 | 1377.0688 | 649 | 0.13326 | 7.4625 | 591 |  | 3309
7774 | RED BLUFF 110176020 | 103541101 | RED BLUFF 1101 | 76020 | FALSE | 23407.8426 | 15031.7581 | 9.3423 | 137 | 5.4998e-05 | 2910 | 2512.6527 | 342 | 0.13318 | 18.2456 | 592 | 0.45 | 918
5975 | HARTLEY 11011306 | 43211101 | HARTLEY 1101 | 1306 | FALSE | 19638.9419 | 15260.277 | 9.4843 | 117 | 9.0495e-05 | 1898 | 1507.2616 | 595 | 0.13303 | 15.5648 | 593 | 0.07 | 1743
3100 | GARBERVILLE 11022540 | 192221102 | GARBERVILLE 1102 | 2540 | FALSE | 28748.5934 | 26122.3431 | 16.2351 | 135 | 0.00054969 | 24 | 203.3955 | 1636 | 0.13296 | 17.9496 | 594 | 0.02 | 2424
9542 | OLETA 1102CB | 163541102 | OLETA 1102 | CB | TRUE | 1312.9371 | 596.6183 | 0.3708 | 11 | 0.00014984 | 739 | 1023.6412 | 812 | 0.13274 | 1.4601 | 595 | 0.08 | 1591
6900 | SALT SPRINGS 210110416 | 163692101 | SALT SPRINGS 2101 | 10416 | FALSE | 1110.1976 | 1110.1976 | 0.68999 | 7 | 0.00010788 | 1452 | 1426.8175 | 628 | 0.1325 | 0.92748 | 596 | 0.02 | 2491
1019 | HOPLAND 1101770 | 42251101 | HOPLAND 1101 | 770 | FALSE | 24751.8286 | 13838.1959 | 8.6005 | 110 | 0.00012303 | 1134 | 1361.4118 | 656 | 0.13217 | 14.5382 | 597 | 0.02 | 2513
9774 | WILDWOOD 1101384582 | 103611101 | WILDWOOD 1101 | 384582 | FALSE | 7304.3535 | 7304.3535 | 4.5397 | 8 | 5.1941e-05 | 2994 | 4044.7807 | 147 | 0.13184 | 1.0547 | 598 |  | 3417
6290 | WYANDOTTE 110796390 | 102911107 | WYANDOTTE 1107 | 96390 | FALSE | 16282.4885 | 13753.525 | 8.5479 | 124 | 0.00016254 | 620 | 924.5376 | 871 | 0.13125 | 16.2749 | 599 | 0.12 | 1378
8217 | VINEYARD 2110CB | 14502110 | VINEYARD 2110 | CB | FALSE | 16260.0032 | 8994.5064 | 5.5901 | 86 | 9.3599e-05 | 1807 | 1513.1588 | 589 | 0.1308 | 11.2491 | 600 | 0.04 | 2129
7155 | PEORIA 1701CB | 163781701 | PEORIA 1701 | CB | FALSE | 14117.7933 | 14117.7933 | 8.7743 | 70 | 8.3932e-05 | 2095 | 1625.1549 | 551 | 0.13063 | 9.1442 | 601 | 0.03 | 2355
1707 | HIGGINS 11039753 | 152691103 | HIGGINS 1103 | 9753 | FALSE | 3306.1166 | 3306.1166 | 2.0548 | 23 | 6.1494e-05 | 2733 | 2174.098 | 407 | 0.13059 | 3.0036 | 602 | 0.08 | 1584
10679 | COVELO 1101627416 | 43061101 | COVELO 1101 | 627416 | TRUE | 5034.3822 | 971.5124 | 0.6038 | 14 | 9.4498e-05 | 1779 | 1192.7699 | 735 | 0.13024 | 1.8234 | 603 |  | 3590
2248 | CORRAL 110313474 | 162991103 | CORRAL 1103 | 13474 | FALSE | 11606.5963 | 4726.1259 | 2.9373 | 99 | 9.8916e-05 | 1672 | 1472.7962 | 605 | 0.13001 | 12.8713 | 604 | 1.54 | 666
6056 | MARIPOSA 2101309438 | 254452101 | MARIPOSA 2101 | 309438 | FALSE | 13011.7309 | 5938.6322 | 3.6909 | 93 | 0.00010698 | 1474 | 1153.73 | 754 | 0.12966 | 12.0584 | 605 |  | 3000
5806 | COLUMBIA HILL 11012212 | 152471101 | COLUMBIA HILL 1101 | 2212 | FALSE | 14695.9754 | 14695.9754 | 9.1336 | 76 | 0.00022108 | 315 | 358.4844 | 1358 | 0.12922 | 9.8207 | 606 | 41.81 | 174
5628 | PUEBLO 11041304 | 43291104 | PUEBLO 1104 | 1304 | FALSE | 30935.6957 | 30935.6957 | 19.2267 | 175 | 7.3325e-05 | 2386 | 1973.0848 | 460 | 0.12902 | 22.578 | 607 | 0.29 | 1031
5578 | VASCO 1102886522 | 13751102 | VASCO 1102 | 886522 | FALSE | 30828.6552 | 10908.527 | 6.7797 | 154 | 6.1458e-05 | 2736 | 2215.6632 | 400 | 0.12899 | 19.8644 | 608 |  | 2965
2390 | WYANDOTTE 11091520 | 102911109 | WYANDOTTE 1109 | 1520 | FALSE | 31725.4009 | 6700.2969 | 4.1643 | 230 | 0.00011878 | 1212 | 1243.3344 | 704 | 0.1287 | 29.6011 | 609 | 0.04 | 2162
2104 | LINCOLN 11045391 | 153701104 | LINCOLN 1104 | 5391 | FALSE | 1530.1829 | 1530.1829 | 0.95101 | 7 | 4.9284e-05 | 3055 | 2595.0683 | 333 | 0.12868 | 0.90075 | 610 | 2.85 | 575
826 | TASSAJARA 210419042 | 14662104 | TASSAJARA 2104 | 19042 | FALSE | 13701.0778 | 10069.7209 | 6.2584 | 89 | 0.00010259 | 1584 | 1548.81 | 581 | 0.12861 | 11.4466 | 611 | 0.17 | 1229
7172 | FITCH MOUNTAIN 1113356 | 42751113 | FITCH MOUNTAIN 1113 | 356 | FALSE | 24352.0152 | 17245.1485 | 10.7179 | 136 | 0.00012922 | 1022 | 991.1123 | 839 | 0.12847 | 17.4723 | 612 | 8.54 | 423
761 | BANGOR 11017446 | 103191101 | BANGOR 1101 | 7446 | FALSE | 69991.8942 | 69991.8942 | 43.5002 | 427 | 0.00013367 | 949 | 983.1088 | 842 | 0.12828 | 54.7764 | 613 | 0.18 | 1220
9800 | CALISTOGA 110135588 | 42711101 | CALISTOGA 1101 | 35588 | FALSE | 4954.8551 | 4954.8551 | 3.0795 | 18 | 9.2798e-05 | 1827 | 1278.0574 | 690 | 0.12786 | 2.3016 | 614 | 0.6 | 851
9664 | PASO ROBLES 110359763 | 182611103 | PASO ROBLES 1103 | 59763 | FALSE | 4532.1933 | 4532.1933 | 2.8168 | 30 | 5.4981e-05 | 2912 | 2480.207 | 346 | 0.12716 | 3.8149 | 615 | 2.26 | 616
5583 | RED BLUFF 11031702 | 103541103 | RED BLUFF 1103 | 1702 | FALSE | 29294.348 | 26958.2044 | 16.7546 | 177 | 4.2191e-05 | 3220 | 3360.288 | 216 | 0.12716 | 22.5069 | 616 | 0.14 | 1332
4955 | WILLITS 1104188268 | 42661104 | WILLITS 1104 | 188268 | FALSE | 8709.5262 | 6867.4982 | 4.2682 | 66 | 0.00013545 | 924 | 756.6199 | 968 | 0.1264 | 8.3425 | 617 |  | 2932
9342 | SAND CREEK 11037823F | 254601103 | SAND CREEK 1103 | 7823F | FALSE | 7527.4054 | 7527.4054 | 4.6783 | 49 | 2.6117e-05 | 3486 | 5142.2922 | 63 | 0.12636 | 6.1917 | 618 | 0.06 | 1848
7895 | PEORIA 1704877670 | 163781704 | PEORIA 1704 | 877670 | FALSE | 10595.2996 | 10595.2996 | 6.585 | 28 | 7.9345e-05 | 2225 | 1606.4027 | 561 | 0.12626 | 3.5352 | 619 | 0.06 | 1803
1593 | MENLO 1102W80 | 24131102 | MENLO 1102 | W80 | FALSE | 30507.2399 | 30491.2345 | 18.9504 | 129 | 0.00012461 | 1105 | 990.5879 | 840 | 0.12598 | 16.2519 | 620 | 0.26 | 1062
9134 | SAN LUIS OBISPO 1104350030 | 182631104 | SAN LUIS OBISPO 1104 | 350030 | FALSE | 14009.015 | 9325.238 | 5.7957 | 107 | 0.00012847 | 1039 | 957.5657 | 855 | 0.12598 | 13.4795 | 621 |  | 3314
10634 | EDENVALE 2107288980 | 82952107 | EDENVALE 2107 | 288980 | TRUE | 1137.5268 | 532.3299 | 0.33085 | 6 | 5.3751e-05 | 2947 | 2359.4228 | 370 | 0.12531 | 0.75188 | 622 |  | 3583
8835 | SOLEDAD 2102955138 | 182052102 | SOLEDAD 2102 | 955138 | FALSE | 4475.7732 | 4227.5124 | 2.6274 | 16 | 6.7551e-05 | 2548 | 1883.3994 | 478 | 0.12515 | 2.0024 | 623 |  | 3270
6170 | GIRVAN 11011330 | 103401101 | GIRVAN 1101 | 1330 | FALSE | 50161.9849 | 49990.913 | 31.0696 | 264 | 0.00011447 | 1308 | 1373.7242 | 651 | 0.12503 | 33.0087 | 624 | 0.19 | 1173
9760 | RINCON 11035152 | 43321103 | RINCON 1103 | 5152 | FALSE | 2685.0442 | 2685.0442 | 1.6688 | 17 | 0.00018787 | 456 | 675.7903 | 1038 | 0.1239 | 2.1064 | 625 | 12.52 | 374
6631 | HIGHLANDS 11031282 | 43361103 | HIGHLANDS 1103 | 1282 | FALSE | 26604.6713 | 22934.9277 | 14.2542 | 164 | 7.8872e-05 | 2239 | 1748.6654 | 515 | 0.12376 | 20.2971 | 626 | 4.57 | 514
7124 | SANTA YNEZ 1102CB | 182721102 | SANTA YNEZ 1102 | CB | FALSE | 14342.9846 | 2348.085 | 1.4593 | 124 | 5.5469e-05 | 2900 | 1580.4692 | 569 | 0.12375 | 15.3456 | 627 | 0.03 | 2351
547 | STILLWATER 11021644 | 103561102 | STILLWATER 1102 | 1644 | FALSE | 36747.479 | 36747.479 | 22.8387 | 244 | 0.00010131 | 1620 | 1382.8849 | 646 | 0.12375 | 30.1941 | 628 | 0.08 | 1604
6046 | WOODWARD 210878448 | 255292108 | WOODWARD 2108 | 78448 | FALSE | 47671.1997 | 31387.7639 | 19.5076 | 188 | 3.1679e-05 | 3405 | 4051.9056 | 146 | 0.12365 | 23.2453 | 629 | 0.05 | 2059
7443 | GARBERVILLE 11011770 | 192221101 | GARBERVILLE 1101 | 1770 | FALSE | 13849.8333 | 13849.8333 | 8.6077 | 66 | 0.00044353 | 51 | 343.9532 | 1380 | 0.12342 | 8.1457 | 630 | 0.02 | 2504
2056 | BUELLTON 1101Y06 | 183041101 | BUELLTON 1101 | Y06 | FALSE | 63281.543 | 48855.5405 | 30.3639 | 304 | 5.4903e-05 | 2917 | 2033.2985 | 450 | 0.12317 | 37.4433 | 631 | 0.14 | 1333
1863 | DIAMOND SPRINGS 110610587 | 152261106 | DIAMOND SPRINGS 1106 | 10587 | FALSE | 35336.5514 | 35336.5514 | 21.9618 | 212 | 8.4096e-05 | 2092 | 1469.4238 | 607 | 0.12297 | 26.0703 | 632 | 0.13 | 1334
5060 | CLOVERDALE 1102156 | 42821102 | CLOVERDALE 1102 | 156 | FALSE | 18958.8699 | 9919.8336 | 6.1652 | 110 | 0.00012453 | 1107 | 875.9596 | 896 | 0.12268 | 13.4944 | 633 | 0.21 | 1144
8874 | BRIDGEVILLE 110169866 | 192461101 | BRIDGEVILLE 1101 | 69866 | FALSE | 10571.2356 | 10571.2356 | 6.5701 | 46 | 0.00023172 | 281 | 514.4343 | 1188 | 0.12256 | 5.6379 | 634 | 3.53 | 543
7200 | DIAMOND SPRINGS 1104705100 | 152261104 | DIAMOND SPRINGS 1104 | 705100 | FALSE | 13322.8036 | 11885.1942 | 7.3867 | 78 | 0.00013638 | 915 | 900.0548 | 884 | 0.12223 | 9.5341 | 635 |  | 3106
5273 | SAND CREEK 11037110 | 254601103 | SAND CREEK 1103 | 7110 | FALSE | 29983.2616 | 29983.2616 | 18.6347 | 132 | 4.0372e-05 | 3258 | 3332.8764 | 221 | 0.12197 | 16.0996 | 636 | 0.03 | 2230
3234 | FULTON 1107604 | 42561107 | FULTON 1107 | 604 | FALSE | 28058.6741 | 28058.6741 | 17.4386 | 169 | 0.00010038 | 1638 | 1390.9913 | 641 | 0.12169 | 20.5661 | 637 | 38.24 | 196
8992 | TIDEWATER 2106781445 | 14652106 | TIDEWATER 2106 | 781445 | TRUE | 577.8877 | 405.5365 | 0.25204 | 6 | 0.00010546 | 1508 | 1075.6001 | 784 | 0.12145 | 0.72871 | 638 |  | 3291
9503 | SAN LUIS OBISPO 1103153199 | 182631103 | SAN LUIS OBISPO 1103 | 153199 | FALSE | 8788.2197 | 4750.5459 | 2.9525 | 53 | 4.9986e-05 | 3037 | 2588.0496 | 334 | 0.1214 | 6.4339 | 639 |  | 3364
8489 | LAYTONVILLE 1102572 | 42681102 | LAYTONVILLE 1102 | 572 | FALSE | 34429.3225 | 34429.3225 | 21.398 | 155 | 0.00020812 | 372 | 588.4642 | 1115 | 0.12097 | 18.7503 | 640 | 5.06 | 497
1408 | ATASCADERO 1103A16 | 182541103 | ATASCADERO 1103 | A16 | FALSE | 32308.0619 | 31835.9088 | 19.7861 | 122 | 9.9134e-05 | 1665 | 1262.4628 | 693 | 0.12088 | 14.7476 | 641 | 0.07 | 1702
68 | TEJON 11022455 | 252931102 | TEJON 1102 | 2455 | FALSE | 10165.5764 | 10165.5764 | 6.3179 | 84 | 3.5175e-05 | 3348 | 3535.7199 | 196 | 0.12034 | 10.1082 | 642 | 0.08 | 1657
6764 | MAXWELL 11053008 | 62881105 | MAXWELL 1105 | 3008 | FALSE | 24475.225 | 13636.9493 | 8.4754 | 55 | 6.8766e-05 | 2515 | 2119.5029 | 421 | 0.1202 | 6.6112 | 643 | 0.01 | 2614
3997 | APPLE HILL 2102CB | 153662102 | APPLE HILL 2102 | CB | FALSE | 66423.2503 | 66423.2503 | 41.2823 | 448 | 0.00014731 | 770 | 1022.0989 | 813 | 0.12006 | 53.7868 | 644 | 29.66 | 239
4706 | WYANDOTTE 11031504 | 102911103 | WYANDOTTE 1103 | 1504 | FALSE | 23629.2409 | 17735.4007 | 11.0226 | 186 | 0.00021184 | 352 | 618.3499 | 1084 | 0.12006 | 22.3307 | 645 | 0.12 | 1402
8185 | CLARKSVILLE 2109CB | 153612109 | CLARKSVILLE 2109 | CB | FALSE | 1831.3319 | 1593.4993 | 0.99037 | 15 | 0.00021275 | 345 | 713.5234 | 1009 | 0.11989 | 1.7983 | 646 | 0.07 | 1726
5862 | HOLLISTER 2102855412 | 182492102 | HOLLISTER 2102 | 855412 | FALSE | 50683.3516 | 45702.3865 | 28.4042 | 108 | 6.4443e-05 | 2629 | 1812.7947 | 504 | 0.11956 | 12.9123 | 647 | 0.05 | 2051
2833 | MARTELL 11033152 | 163011103 | MARTELL 1103 | 3152 | FALSE | 27364.6036 | 26923.3255 | 16.733 | 134 | 8.4438e-05 | 2079 | 1552.0849 | 578 | 0.11956 | 16.0208 | 648 | 0.08 | 1624
3141 | DIAMOND SPRINGS 11057722 | 152261105 | DIAMOND SPRINGS 1105 | 7722 | FALSE | 100229.7186 | 96782.5255 | 60.1507 | 572 | 0.00010462 | 1540 | 1087.3028 | 779 | 0.11928 | 68.2291 | 649 | 0.25 | 1084
501 | DOBBINS 11011264 | 153741101 | DOBBINS 1101 | 1264 | FALSE | 56286.9636 | 56286.9636 | 34.9826 | 307 | 0.00011647 | 1260 | 1094.5256 | 776 | 0.11917 | 36.585 | 650 | 0.39 | 957
855 | HIGGINS 1103CB | 152691103 | HIGGINS 1103 | CB | FALSE | 45692.926 | 45174.6839 | 28.0762 | 315 | 0.00014305 | 825 | 1166.4722 | 747 | 0.11916 | 37.536 | 651 | 0.25 | 1090
491 | TIVY VALLEY 1107822606 | 252941107 | TIVY VALLEY 1107 | 822606 | FALSE | 29230.0954 | 21701.9466 | 13.4878 | 144 | 3.2057e-05 | 3400 | 3717.2296 | 181 | 0.11894 | 17.1275 | 652 |  | 2678
8121 | CAYETANO 2109MR186 | 14422109 | CAYETANO 2109 | MR186 | TRUE | 4135.7533 | 818.8837 | 0.50894 | 27 | 8.9465e-05 | 1933 | 1490.2334 | 599 | 0.11874 | 3.2061 | 653 | 0.02 | 2461
2634 | APPLE HILL 21028372 | 153662102 | APPLE HILL 2102 | 8372 | FALSE | 101264.4904 | 94481.7777 | 58.7208 | 629 | 0.00011802 | 1229 | 985.1922 | 841 | 0.11858 | 74.5861 | 654 | 0.21 | 1139
1440 | MARIPOSA 21019400 | 254452101 | MARIPOSA 2101 | 9400 | FALSE | 101537.78 | 101537.78 | 63.1061 | 667 | 6.6859e-05 | 2561 | 1882.7942 | 479 | 0.11849 | 79.0304 | 655 | 1.17 | 705
8059 | OILFIELDS 1103N62 | 182391103 | OILFIELDS 1103 | N62 | FALSE | 8948.1922 | 8948.1922 | 5.5613 | 39 | 7.0521e-05 | 2455 | 1674.5706 | 532 | 0.11842 | 4.6183 | 656 | 0.13 | 1344
1860 | SHINGLE SPRINGS 2105CB | 153652105 | SHINGLE SPRINGS 2105 | CB | FALSE | 30610.8387 | 30610.8387 | 19.0248 | 245 | 0.00018342 | 484 | 745.8005 | 978 | 0.11812 | 28.9401 | 657 | 0.61 | 844
1237 | NARROWS 2102CB | 153132102 | NARROWS 2102 | CB | FALSE | 39248.3153 | 36287.6403 | 22.5529 | 243 | 0.00015786 | 664 | 1177.1526 | 742 | 0.11807 | 28.6917 | 658 | 0.1 | 1491
9931 | CORTINA 1101528460 | 63121101 | CORTINA 1101 | 528460 | FALSE | 6121.8319 | 3043.5918 | 1.8916 | 12 | 3.9909e-05 | 3271 | 3097.7847 | 255 | 0.11792 | 1.415 | 659 |  | 3454
6877 | COARSEGOLD 21036110 | 254432103 | COARSEGOLD 2103 | 6110 | FALSE | 47929.948 | 17714.3763 | 11.0096 | 179 | 4.1885e-05 | 3228 | 2595.4532 | 332 | 0.11737 | 21.0097 | 660 | 0.03 | 2313
3126 | HORSESHOE 110150140 | 152571101 | HORSESHOE 1101 | 50140 | FALSE | 10038.7802 | 6357.3386 | 3.9511 | 82 | 0.0001527 | 722 | 724.1364 | 995 | 0.11734 | 9.6215 | 661 | 0.07 | 1721
9916 | SAN LUIS OBISPO 1104777686 | 182631104 | SAN LUIS OBISPO 1104 | 777686 | FALSE | 3079.762 | 2707.2733 | 1.6826 | 17 | 6.1974e-05 | 2721 | 2050.5492 | 444 | 0.11731 | 1.9944 | 662 |  | 3452
8080 | SILVERADO 210258626 | 43432102 | SILVERADO 2102 | 58626 | FALSE | 24491.7338 | 24491.7338 | 15.2217 | 125 | 9.1234e-05 | 1869 | 1427.3169 | 627 | 0.117 | 14.6249 | 663 | 33.89 | 218
4277 | SAN JOAQUIN #2 1103157026 | 252521103 | SAN JOAQUIN #2 1103 | 157026 | FALSE | 5200.077 | 5200.077 | 3.2319 | 44 | 6.6096e-05 | 2586 | 1923.6933 | 467 | 0.11682 | 5.1403 | 664 | 0.05 | 1989
6827 | PEORIA 170411232 | 163781704 | PEORIA 1704 | 11232 | FALSE | 27747.6591 | 20505.608 | 12.7443 | 222 | 7.7668e-05 | 2269 | 1686.0292 | 527 | 0.11656 | 25.8772 | 665 | 3.3 | 550
772 | DIAMOND SPRINGS 11052102 | 152261105 | DIAMOND SPRINGS 1105 | 2102 | FALSE | 62912.0633 | 60307.8799 | 37.4816 | 417 | 0.00013035 | 1002 | 1146.8943 | 755 | 0.11621 | 48.4576 | 666 | 0.75 | 787
1946 | WILLITS 1104CB | 42661104 | WILLITS 1104 | CB | FALSE | 12241.4218 | 6260.0525 | 3.8906 | 90 | 0.00013491 | 927 | 773.6055 | 956 | 0.11609 | 10.4477 | 667 | 0.03 | 2310
2370 | GEYSERVILLE 1102484 | 42891102 | GEYSERVILLE 1102 | 484 | FALSE | 78528.1935 | 53688.8082 | 33.3678 | 379 | 0.00011833 | 1222 | 896.8187 | 885 | 0.11607 | 43.9888 | 668 | 0.17 | 1225
7186 | HIGGINS 1104CB | 152691104 | HIGGINS 1104 | CB | FALSE | 18716.511 | 18050.1072 | 11.2182 | 124 | 0.00013241 | 974 | 792.6979 | 948 | 0.11592 | 14.3743 | 669 | 0.08 | 1643
9814 | PENRYN 1105119949 | 152561105 | PENRYN 1105 | 119949 | FALSE | 3756.7927 | 2221.8702 | 1.3809 | 25 | 7.5613e-05 | 2320 | 1497.9784 | 598 | 0.11529 | 2.8822 | 670 |  | 3429
7423 | CLAY 1103CB | 163341103 | CLAY 1103 | CB | FALSE | 21668.4067 | 9680.057 | 6.0162 | 110 | 0.00011397 | 1323 | 734.8074 | 989 | 0.11521 | 12.6729 | 671 | 0.03 | 2334
7292 | TIDEWATER 2106745811 | 14652106 | TIDEWATER 2106 | 745811 | TRUE | 780.426 | 641.2916 | 0.39857 | 8 | 7.9022e-05 | 2235 | 1106.1185 | 773 | 0.11506 | 0.92047 | 672 |  | 3113
8864 | WOODACRE 110191900 | 43021101 | WOODACRE 1101 | 91900 | FALSE | 22248.6035 | 14519.294 | 9.0238 | 91 | 0.00012885 | 1031 | 1012.5441 | 824 | 0.11491 | 10.4566 | 673 | 1.72 | 650
9782 | SAND CREEK 110397354 | 254601103 | SAND CREEK 1103 | 97354 | FALSE | 16339.8299 | 14168.242 | 8.8056 | 59 | 2.3546e-05 | 3509 | 5418.3509 | 49 | 0.11488 | 6.7778 | 674 | 0.06 | 1885
7321 | CLARKSVILLE 210619642 | 153612106 | CLARKSVILLE 2106 | 19642 | FALSE | 2579.2739 | 1246.4399 | 0.77467 | 17 | 0.00024874 | 219 | 453.1258 | 1242 | 0.11477 | 1.9511 | 675 | 0.96 | 739
1291 | MERCED FALLS 11029470 | 252811102 | MERCED FALLS 1102 | 9470 | FALSE | 36749.5976 | 36749.5976 | 22.84 | 277 | 8.8658e-05 | 1964 | 1395.4992 | 639 | 0.11474 | 31.7833 | 676 | 0.01 | 2586
10278 | PUEBLO 2102943820 | 43292102 | PUEBLO 2102 | 943820 | FALSE | 3953.9711 | 3039.5845 | 1.8891 | 13 | 9.0029e-05 | 1913 | 1434.295 | 621 | 0.11464 | 1.4903 | 677 |  | 3527
2358 | WHITMORE 11011594 | 103601101 | WHITMORE 1101 | 1594 | FALSE | 39042.2093 | 39042.2093 | 24.2649 | 160 | 0.00012552 | 1089 | 1126.4421 | 765 | 0.11449 | 18.3178 | 678 | 0.12 | 1390
892 | MARIPOSA 210110240 | 254452101 | MARIPOSA 2101 | 10240 | FALSE | 34689.059 | 34689.059 | 21.5594 | 189 | 7.4292e-05 | 2350 | 1439.7612 | 619 | 0.11431 | 21.6045 | 679 | 0.31 | 1009
4813 | CLOVERDALE 1102674 | 42821102 | CLOVERDALE 1102 | 674 | FALSE | 32462.2926 | 27296.9382 | 16.9652 | 122 | 0.00011908 | 1203 | 1499.689 | 597 | 0.11401 | 13.9092 | 680 | 0.15 | 1285
4778 | SHINGLE SPRINGS 210961892 | 153652109 | SHINGLE SPRINGS 2109 | 61892 | FALSE | 48456.6488 | 48456.6488 | 30.116 | 318 | 8.0969e-05 | 2183 | 1584.3018 | 567 | 0.11372 | 36.1635 | 681 | 38.89 | 193
9093 | BANGOR 110155206 | 103191101 | BANGOR 1101 | 55206 | TRUE | 3467.0084 | 0 | 0 | 28 | 0.00010976 | 1415 | 967.1576 | 851 | 0.11351 | 3.1783 | 682 | 0.04 | 2213
395 | CALISTOGA 1101734 | 42711101 | CALISTOGA 1101 | 734 | FALSE | 26724.941 | 22050.8989 | 13.7047 | 162 | 0.00015037 | 732 | 885.8837 | 889 | 0.11348 | 18.3842 | 683 | 1.06 | 719
7143 | COTATI 1103CB | 42271103 | COTATI 1103 | CB | FALSE | 19422.567 | 19422.567 | 12.0712 | 106 | 0.00011506 | 1297 | 1154.679 | 753 | 0.11341 | 12.0218 | 684 | 5.58 | 484
2744 | WHITMORE 110145262 | 103601101 | WHITMORE 1101 | 45262 | FALSE | 46333.9347 | 46333.9347 | 28.7967 | 221 | 0.00010272 | 1577 | 1038.3077 | 800 | 0.11334 | 25.0485 | 685 | 0.06 | 1915
4167 | COTTONWOOD 11031344 | 102931103 | COTTONWOOD 1103 | 1344 | FALSE | 20065.0071 | 16285.3354 | 10.1214 | 152 | 6.9299e-05 | 2497 | 2362.2491 | 369 | 0.11327 | 17.2178 | 686 | 4.34 | 522
9035 | CLEAR LAKE 1101699062 | 42141101 | CLEAR LAKE 1101 | 699062 | FALSE | 3006.4235 | 1359.6473 | 0.84503 | 20 | 8.6499e-05 | 2024 | 1257.9802 | 696 | 0.11322 | 2.2645 | 687 |  | 3300
2015 | SHINGLE SPRINGS 210912392 | 153652109 | SHINGLE SPRINGS 2109 | 12392 | FALSE | 23572.5391 | 23572.5391 | 14.6504 | 178 | 0.00010936 | 1424 | 1246.8521 | 703 | 0.11309 | 20.1293 | 688 | 55.71 | 101
2546 | PLACERVILLE 1110421358 | 153081110 | PLACERVILLE 1110 | 421358 | FALSE | 23870.6711 | 23870.6711 | 14.8357 | 169 | 0.00012254 | 1140 | 802.5537 | 940 | 0.11286 | 19.0733 | 689 |  | 2784
6240 | SILVERADO 2104722 | 43432104 | SILVERADO 2104 | 722 | FALSE | 12705.3582 | 12705.3582 | 7.8964 | 99 | 0.00026082 | 194 | 569.6012 | 1130 | 0.11274 | 11.1613 | 690 | 46.62 | 140
6314 | TEJON 11023751 | 252931102 | TEJON 1102 | 3751 | FALSE | 16451.1737 | 15802.8651 | 9.8215 | 65 | 4.4896e-05 | 3163 | 3153.8117 | 247 | 0.11269 | 7.325 | 691 | 0.03 | 2272
8377 | CAYETANO 2111CB | 14422111 | CAYETANO 2111 | CB | FALSE | 14665.1565 | 5449.7896 | 3.3871 | 81 | 0.00012146 | 1157 | 1050.3758 | 796 | 0.11258 | 9.1187 | 692 | 0.04 | 2099
84 | LINCOLN 110451756 | 153701104 | LINCOLN 1104 | 51756 | FALSE | 56082.3102 | 17440.8058 | 10.8395 | 264 | 8.4998e-05 | 2060 | 1131.9939 | 763 | 0.11252 | 29.7041 | 693 | 1.15 | 707
4410 | MC ARTHUR 1101501106 | 103491101 | MC ARTHUR 1101 | 501106 | FALSE | 16962.6839 | 16083.896 | 9.9962 | 86 | 2.2874e-05 | 3513 | 4753.376 | 97 | 0.11248 | 9.6734 | 694 |  | 2889
1376 | CLARKSVILLE 210419772 | 153612104 | CLARKSVILLE 2104 | 19772 | FALSE | 29712.1582 | 28840.3765 | 17.9244 | 185 | 0.00010637 | 1489 | 1084.3194 | 780 | 0.11233 | 20.7806 | 695 | 41.36 | 177
138 | CLARKSVILLE 2103593454 | 153612103 | CLARKSVILLE 2103 | 593454 | FALSE | 65282.8123 | 51502.8241 | 32.0092 | 324 | 8.6965e-05 | 2012 | 1565.5344 | 572 | 0.11221 | 36.3549 | 696 |  | 2656
6028 | RISING RIVER 11011530 | 103551101 | RISING RIVER 1101 | 1530 | FALSE | 28483.8521 | 18168.0106 | 11.2915 | 167 | 5.6107e-05 | 2884 | 2176.9842 | 405 | 0.11218 | 18.7349 | 697 | 0.01 | 2573
6687 | CLARK ROAD 110281296 | 103091102 | CLARK ROAD 1102 | 81296 | FALSE | 24680.7336 | 17571.0511 | 10.9205 | 124 | 0.00010636 | 1490 | 869.9858 | 899 | 0.11218 | 13.9107 | 698 | 0.05 | 2005
2672 | APPLE HILL 210277546 | 153662102 | APPLE HILL 2102 | 77546 | FALSE | 69346.9327 | 69346.9327 | 43.0994 | 403 | 9.5092e-05 | 1762 | 1309.4241 | 678 | 0.11214 | 45.1922 | 699 | 0.19 | 1189
4377 | MARIPOSA 2101752630 | 254452101 | MARIPOSA 2101 | 752630 | FALSE | 30558.9663 | 30558.9663 | 18.9925 | 154 | 6.484e-05 | 2614 | 1699.6449 | 523 | 0.11205 | 17.2553 | 700 |  | 2886
5474 | COTATI 1105213984 | 42271105 | COTATI 1105 | 213984 | FALSE | 11162.845 | 11162.845 | 6.9378 | 47 | 9.4494e-05 | 1780 | 1225.6338 | 715 | 0.11198 | 5.263 | 701 |  | 2957
6448 | MERCED FALLS 110238748 | 252811102 | MERCED FALLS 1102 | 38748 | FALSE | 24704.6186 | 24704.6186 | 15.354 | 178 | 7.1784e-05 | 2426 | 1618.5371 | 554 | 0.11192 | 19.9215 | 702 | 0.01 | 2604
1645 | COTATI 110599720 | 42271105 | COTATI 1105 | 99720 | FALSE | 19787.8115 | 14780.8133 | 9.1863 | 134 | 8.8188e-05 | 1977 | 1157.381 | 751 | 0.11177 | 14.9768 | 703 | 7.05 | 453
439 | HIGGINS 1110CB | 152691110 | HIGGINS 1110 | CB | FALSE | 17394.4702 | 14019.0952 | 8.7129 | 134 | 0.00023184 | 280 | 615.3789 | 1088 | 0.11172 | 14.9707 | 704 | 0.06 | 1909
6646 | UPPER LAKE 110175370 | 42871101 | UPPER LAKE 1101 | 75370 | FALSE | 23702.8229 | 17823.7139 | 11.0775 | 133 | 0.0001129 | 1346 | 1122.5953 | 767 | 0.11161 | 14.8441 | 705 | 0.05 | 2009
3320 | LAYTONVILLE 110237586 | 42681102 | LAYTONVILLE 1102 | 37586 | FALSE | 22457.0278 | 22457.0278 | 13.9571 | 72 | 0.00013607 | 919 | 959.2045 | 854 | 0.11137 | 8.0187 | 706 | 0.07 | 1736
8527 | HIGGINS 11097831 | 152691109 | HIGGINS 1109 | 7831 | FALSE | 14300.9674 | 14300.9674 | 8.8881 | 86 | 5.8164e-05 | 2831 | 1904.4724 | 475 | 0.1113 | 9.5719 | 707 | 0.1 | 1473
8404 | TEMPLETON 2110317796 | 183052110 | TEMPLETON 2110 | 317796 | FALSE | 11760.0744 | 8148.5566 | 5.0644 | 65 | 7.0178e-05 | 2466 | 1382.5193 | 647 | 0.11087 | 7.2063 | 708 |  | 3222
9399 | CALAVERAS CEMENT 1101585 | 162211101 | CALAVERAS CEMENT 1101 | 585 | FALSE | 22730.6203 | 22730.6203 | 14.1272 | 95 | 6.2212e-05 | 2714 | 1313.2645 | 677 | 0.11082 | 10.5283 | 709 | 0.1 | 1490
9168 | CAL WATER 1102690954 | 255451102 | CAL WATER 1102 | 690954 | FALSE | 6889.4894 | 6410.0397 | 3.9839 | 12 | 1.5494e-05 | 3583 | 7160.5307 | 9 | 0.11057 | 1.3268 | 710 |  | 3318
1850 | OAKHURST 1103CB | 254421103 | OAKHURST 1103 | CB | FALSE | 53866.9528 | 51789.1777 | 32.1872 | 417 | 0.00011056 | 1401 | 1269.855 | 691 | 0.11044 | 46.0525 | 711 | 0.78 | 780
4124 | CALPELLA 1102CB | 43411102 | CALPELLA 1102 | CB | TRUE | 7260.7146 | 263.08 | 0.16351 | 61 | 0.00011907 | 1204 | 713.2367 | 1010 | 0.1104 | 6.7341 | 712 | 0.02 | 2463
10720 | OCEANO 1103839302 | 182601103 | OCEANO 1103 | 839302 | FALSE | 1806.4039 | 1806.4039 | 1.1227 | 8 | 4.4881e-05 | 3164 | 2564.3756 | 337 | 0.11001 | 0.88007 | 713 |  | 3595
2355 | OLETA 11021204 | 163541102 | OLETA 1102 | 1204 | FALSE | 47393.9854 | 41374.6655 | 25.7145 | 233 | 8.8982e-05 | 1950 | 1305.1155 | 679 | 0.10989 | 25.6033 | 714 | 0.09 | 1553
635 | BRUNSWICK 11062790 | 152481106 | BRUNSWICK 1106 | 2790 | FALSE | 17696.042 | 16028.2028 | 9.9616 | 115 | 0.00014264 | 831 | 967.5085 | 850 | 0.10954 | 12.5971 | 715 | 0.18 | 1201
6919 | COTTONWOOD 110168190 | 102931101 | COTTONWOOD 1101 | 68190 | FALSE | 40559.778 | 38588.9503 | 23.9832 | 238 | 3.6266e-05 | 3328 | 3033.8848 | 265 | 0.10937 | 26.0311 | 716 | 0.06 | 1813
10335 | PETALUMA C 1109664732 | 42631109 | PETALUMA C 1109 | 664732 | FALSE | 1437.8147 | 1437.8147 | 0.89361 | 6 | 9.0941e-05 | 1884 | 1650.3416 | 543 | 0.10842 | 0.65051 | 717 | 1.72 | 649
4157 | CALPELLA 1101600 | 43411101 | CALPELLA 1101 | 600 | FALSE | 39281.1533 | 30870.3 | 19.186 | 164 | 0.00011588 | 1272 | 1083.2564 | 781 | 0.10818 | 17.7408 | 718 | 0.15 | 1297
3546 | LUCERNE 1103CB | 43351103 | LUCERNE 1103 | CB | FALSE | 7158.565 | 3619.1597 | 2.2493 | 59 | 0.00018211 | 497 | 299.7205 | 1447 | 0.10789 | 6.3658 | 719 | 0.1 | 1483
6463 | SONOMA 1105229588 | 42721105 | SONOMA 1105 | 229588 | FALSE | 21565.3961 | 15531.0208 | 9.6526 | 149 | 8.8674e-05 | 1963 | 1224.4513 | 716 | 0.10786 | 16.0708 | 720 |  | 3033
2133 | FROGTOWN 17011623 | 163451701 | FROGTOWN 1701 | 1623 | FALSE | 24554.2111 | 24554.2111 | 15.2605 | 152 | 7.6286e-05 | 2301 | 1590.8242 | 564 | 0.1076 | 16.3546 | 721 | 0.2 | 1165
10925 | GOLDTREE 1105551904 | 182581105 | GOLDTREE 1105 | 551904 | TRUE | 35.7178 | 35.7178 | 0.022199 | 1 | 0.00014066 | 859 | 763.0871 | 960 | 0.10733 | 0.10733 | 722 | 0.87 | 755
9605 | NOTRE DAME 1104937710 | 102041104 | NOTRE DAME 1104 | 937710 | FALSE | 2292.7758 | 1372.1379 | 0.85279 | 8 | 9.5377e-05 | 1748 | 1144.507 | 756 | 0.10733 | 0.85862 | 723 |  | 3387
3953 | JAMESON 11059472 | 63801105 | JAMESON 1105 | 9472 | FALSE | 11800.3384 | 4934.5741 | 3.0669 | 90 | 8.6625e-05 | 2018 | 1503.1801 | 596 | 0.10731 | 9.6577 | 724 | 0.04 | 2109
6952 | OLETA 110151740 | 163541101 | OLETA 1101 | 51740 | FALSE | 34181.0044 | 25031.397 | 15.5571 | 129 | 6.4996e-05 | 2610 | 1615.1565 | 556 | 0.107 | 13.8028 | 725 | 0.06 | 1828
4360 | CORRAL 110236666 | 162991102 | CORRAL 1102 | 36666 | FALSE | 29026.438 | 27295.7526 | 16.9644 | 207 | 7.008e-05 | 2471 | 1591.1088 | 563 | 0.10683 | 22.1131 | 726 | 0.11 | 1436
10467 | BIG BEND 11011704 | 103751101 | BIG BEND 1101 | 1704 | FALSE | 4825.0456 | 4825.0456 | 2.9988 | 9 | 0.00018499 | 473 | 1060.4778 | 792 | 0.1065 | 0.95854 | 727 | 1.47 | 671
2963 | KONOCTI 110275382 | 43311102 | KONOCTI 1102 | 75382 | FALSE | 37601.9152 | 37336.0999 | 23.2045 | 198 | 0.00010957 | 1420 | 1232.3374 | 713 | 0.10636 | 21.0588 | 728 | 11.14 | 387
7719 | GEYSERVILLE 1102220154 | 42891102 | GEYSERVILLE 1102 | 220154 | TRUE | 4466.0624 | 427.7941 | 0.26588 | 30 | 0.00014785 | 765 | 533.1924 | 1168 | 0.10579 | 3.1738 | 729 |  | 3155
4276 | NARROWS 2105CB | 153132105 | NARROWS 2105 | CB | FALSE | 58448.7227 | 58073.6402 | 36.093 | 382 | 0.00010807 | 1450 | 1111.2712 | 769 | 0.10567 | 40.3677 | 730 | 0.26 | 1065
4123 | MARIPOSA 21014410 | 254452101 | MARIPOSA 2101 | 4410 | FALSE | 36702.381 | 36702.381 | 22.8107 | 232 | 6.2011e-05 | 2720 | 1654.2525 | 541 | 0.10548 | 24.471 | 731 | 0.16 | 1272
5996 | MONTICELLO 1101630 | 43051101 | MONTICELLO 1101 | 630 | FALSE | 31341.2103 | 30113.0466 | 18.7154 | 93 | 5.6908e-05 | 2863 | 1625.0866 | 552 | 0.10515 | 9.7794 | 732 | 0.15 | 1293
7010 | WILLITS 1103966 | 42661103 | WILLITS 1103 | 966 | FALSE | 3670.4356 | 1555.849 | 0.96697 | 34 | 0.00012939 | 1020 | 514.9608 | 1186 | 0.10505 | 3.5716 | 733 | 0.33 | 984
6094 | PARADISE 110443008 | 102831104 | PARADISE 1104 | 43008 | FALSE | 20752.8612 | 20697.7732 | 12.8637 | 145 | 0.00024315 | 238 | 866.3217 | 903 | 0.10501 | 15.2269 | 734 |  | 3002
6540 | MORGAN HILL 2105XR070 | 83242105 | MORGAN HILL 2105 | XR070 | FALSE | 13972.8614 | 10519.5514 | 6.5379 | 90 | 8.0053e-05 | 2203 | 1459.1172 | 612 | 0.10473 | 9.4261 | 735 | 0.15 | 1280
1104 | BRUNSWICK 11042112 | 152481104 | BRUNSWICK 1104 | 2112 | FALSE | 31201.9016 | 31201.9016 | 19.3921 | 222 | 0.00012958 | 1016 | 755.541 | 969 | 0.1046 | 23.2211 | 736 | 9 | 416
3331 | NARROWS 21052216 | 153132105 | NARROWS 2105 | 2216 | FALSE | 93046.0132 | 91192.0768 | 56.6762 | 663 | 0.00017534 | 526 | 744.5838 | 980 | 0.10438 | 69.2068 | 737 | 0.89 | 752
10962 | POINT ARENA 1101CB | 43381101 | POINT ARENA 1101 | CB | TRUE | 64.9169 | 64.9169 | 0.040346 | 2 | 8.2597e-05 | 2140 | 1260.6413 | 694 | 0.10413 | 0.20825 | 738 | 0.04 | 2172
7695 | JAMESON 110265516 | 63801102 | JAMESON 1102 | 65516 | FALSE | 18264.4613 | 12394.5836 | 7.7033 | 137 | 9.0277e-05 | 1904 | 1198.218 | 730 | 0.104 | 14.2484 | 739 | 1.33 | 685
4131 | CURTIS 170565908 | 163351705 | CURTIS 1705 | 65908 | FALSE | 26966.3027 | 22380.0869 | 13.9093 | 205 | 0.00010013 | 1641 | 1026.2121 | 810 | 0.10393 | 21.3052 | 740 | 0.11 | 1441
386 | CORRAL 110112606 | 162991101 | CORRAL 1101 | 12606 | FALSE | 36144.366 | 36144.366 | 22.4639 | 216 | 6.3081e-05 | 2677 | 1680.4042 | 528 | 0.10392 | 22.4476 | 741 | 3.18 | 556
1298 | DESCHUTES 11011652 | 103351101 | DESCHUTES 1101 | 1652 | FALSE | 39344.5137 | 33895.2642 | 21.066 | 170 | 8.6737e-05 | 2017 | 1367.2683 | 654 | 0.10352 | 17.5982 | 742 | 0.06 | 1779
10344 | CLARKSVILLE 210319572 | 153612103 | CLARKSVILLE 2103 | 19572 | TRUE | 4463.6596 | 595.3794 | 0.37003 | 12 | 8.8886e-05 | 1956 | 995.992 | 836 | 0.10348 | 1.2418 | 743 | 0.4 | 947
2338 | CLAY 110113442 | 163341101 | CLAY 1101 | 13442 | FALSE | 49960.437 | 40749.3903 | 25.3259 | 272 | 6.9011e-05 | 2508 | 1672.073 | 535 | 0.10338 | 28.1191 | 744 | 0.16 | 1269
1080 | PLACER 1103284874 | 152461103 | PLACER 1103 | 284874 | FALSE | 7928.0423 | 3450.771 | 2.1447 | 56 | 0.00016281 | 613 | 825.2112 | 923 | 0.10322 | 5.7804 | 745 |  | 2708
2572 | VACA DIXON 11059792 | 63591105 | VACA DIXON 1105 | 9792 | FALSE | 44037.0343 | 1255.3676 | 0.78022 | 329 | 0.00010469 | 1536 | 1266.1791 | 692 | 0.10322 | 33.9591 | 746 | 1.85 | 639
10829 | MILPITAS 110962157 | 82831109 | MILPITAS 1109 | 62157 | TRUE | 72.1015 | 72.1015 | 0.044811 | 3 | 0.00013141 | 991 | 794.5095 | 944 | 0.10257 | 0.30771 | 747 | 0.04 | 2185
9526 | DOBBINS 110191464 | 153741101 | DOBBINS 1101 | 91464 | FALSE | 11314.1038 | 11314.1038 | 7.0318 | 81 | 0.00016471 | 590 | 737.1972 | 986 | 0.10229 | 8.2855 | 748 | 0.15 | 1286
4686 | ELK CREEK 11012212 | 102781101 | ELK CREEK 1101 | 2212 | FALSE | 54144.6309 | 25107.5196 | 15.6044 | 136 | 5.0479e-05 | 3023 | 1941.9065 | 465 | 0.10222 | 13.9025 | 749 | 0.05 | 2020
2703 | COTATI 110536536 | 42271105 | COTATI 1105 | 36536 | FALSE | 31849.3061 | 27701.0415 | 17.2163 | 206 | 9.0039e-05 | 1912 | 1240.3355 | 706 | 0.10219 | 21.0515 | 750 | 6.79 | 460
261 | CLARK ROAD 11022584 | 103091102 | CLARK ROAD 1102 | 2584 | FALSE | 15108.9141 | 14615.3184 | 9.0835 | 83 | 7.5728e-05 | 2313 | 1697.4775 | 524 | 0.1019 | 8.4581 | 751 | 0.06 | 1883
6202 | COARSEGOLD 210490356 | 254432104 | COARSEGOLD 2104 | 90356 | FALSE | 27619.1431 | 7749.0513 | 4.8161 | 148 | 4.5741e-05 | 3146 | 2250.7696 | 393 | 0.10189 | 15.079 | 752 | 0.02 | 2540
10164 | CALPELLA 1101345230 | 43411101 | CALPELLA 1101 | 345230 | FALSE | 4014.2831 | 1908.1944 | 1.186 | 22 | 0.00013065 | 997 | 832.9519 | 920 | 0.10181 | 2.2398 | 753 |  | 3505
10372 | CLOVERDALE 11024646 | 42821102 | CLOVERDALE 1102 | 4646 | TRUE | 480.2865 | 242.399 | 0.15065 | 8 | 0.00023752 | 255 | 1510.1147 | 591 | 0.10163 | 0.81301 | 754 | 0.12 | 1368
10615 | STAFFORD 1102CB | 43201102 | STAFFORD 1102 | CB | TRUE | 993.1092 | 957.3027 | 0.59497 | 10 | 0.00022667 | 299 | 666.0518 | 1045 | 0.10116 | 1.0116 | 755 | 1.11 | 714
10097 | GARBERVILLE 110256048 | 192221102 | GARBERVILLE 1102 | 56048 | FALSE | 8009.5026 | 8009.5026 | 4.9779 | 27 | 0.00051047 | 29 | 201.585 | 1638 | 0.10102 | 2.7275 | 756 | 0.04 | 2118
2214 | MONTICELLO 11014360 | 43051101 | MONTICELLO 1101 | 4360 | FALSE | 14899.0043 | 12170.4858 | 7.564 | 76 | 4.8295e-05 | 3087 | 2072.1488 | 436 | 0.10101 | 7.6765 | 757 | 0.1 | 1496
2869 | NARROWS 21011202 | 153132101 | NARROWS 2101 | 1202 | FALSE | 73649.8789 | 73649.8789 | 45.7737 | 459 | 9.3805e-05 | 1798 | 1469.356 | 608 | 0.10087 | 46.3007 | 758 | 0.24 | 1107
2918 | JESSUP 110338864 | 103441103 | JESSUP 1103 | 38864 | FALSE | 12167.5887 | 2907.107 | 1.8068 | 94 | 9.1373e-05 | 1865 | 1176.5294 | 743 | 0.10076 | 9.4715 | 759 | 0.03 | 2406
8434 | FORT ROSS 1121204 | 42851121 | FORT ROSS 1121 | 204 | FALSE | 31553.8482 | 31553.8482 | 19.6108 | 107 | 0.00017266 | 545 | 673.9659 | 1039 | 0.10067 | 10.7713 | 760 | 11.03 | 390
9462 | BEAR VALLEY 210110019 | 252192101 | BEAR VALLEY 2101 | 10019 | FALSE | 3187.4941 | 3187.4941 | 1.981 | 11 | 5.9517e-05 | 2788 | 1607.8644 | 559 | 0.10052 | 1.1057 | 761 | 0.01 | 2577
3132 | MORGAN HILL 210542348 | 83242105 | MORGAN HILL 2105 | 42348 | FALSE | 5997.998 | 2160.8096 | 1.343 | 53 | 6.8961e-05 | 2511 | 1015.3292 | 819 | 0.10037 | 5.3194 | 762 | 0.49 | 895
10415 | SAN LUIS OBISPO 1103934355 | 182631103 | SAN LUIS OBISPO 1103 | 934355 | TRUE | 1942.6666 | 915.6706 | 0.56909 | 12 | 8.3455e-05 | 2118 | 1431.4244 | 623 | 0.10029 | 1.2035 | 763 |  | 3546
800 | NARROWS 210248484 | 153132102 | NARROWS 2102 | 48484 | FALSE | 67054.8672 | 67054.8672 | 41.6749 | 450 | 0.00013313 | 956 | 878.6779 | 893 | 0.09998 | 44.991 | 764 | 0.43 | 927
3794 | HIGGINS 11077559 | 152691107 | HIGGINS 1107 | 7559 | FALSE | 7193.5229 | 7193.5229 | 4.4708 | 52 | 6.8486e-05 | 2522 | 1663.4994 | 538 | 0.099807 | 5.1899 | 765 | 0.1 | 1474
4136 | MONTICELLO 1101718 | 43051101 | MONTICELLO 1101 | 718 | FALSE | 47250.4225 | 43463.4041 | 27.0127 | 247 | 6.3139e-05 | 2675 | 1440.3304 | 618 | 0.099744 | 24.6369 | 766 | 0.18 | 1211
2696 | OLETA 110163500 | 163541101 | OLETA 1101 | 63500 | TRUE | 5562.1132 | 327.1501 | 0.20333 | 46 | 0.00011792 | 1230 | 448.3626 | 1251 | 0.099652 | 4.584 | 767 | 1.81 | 642
3595 | CEDAR CREEK 11011608 | 103321101 | CEDAR CREEK 1101 | 1608 | FALSE | 53827.5719 | 53827.5719 | 33.4541 | 252 | 0.00019009 | 441 | 523.0258 | 1180 | 0.099644 | 25.1102 | 768 | 0.06 | 1838
80 | WHEATLAND 1105248490 | 152811105 | WHEATLAND 1105 | 248490 | FALSE | 43282.2287 | 17726.6224 | 11.0172 | 228 | 9.8358e-05 | 1682 | 1137.7994 | 759 | 0.099611 | 22.7114 | 769 |  | 2654
24 | FITCH MOUNTAIN 1113443164 | 42751113 | FITCH MOUNTAIN 1113 | 443164 | FALSE | 15151.4475 | 4499.5872 | 2.7965 | 111 | 0.00012907 | 1027 | 720.9883 | 997 | 0.099321 | 11.0246 | 770 |  | 2651
6194 | CLARK ROAD 110292622 | 103091102 | CLARK ROAD 1102 | 92622 | FALSE | 50349.3756 | 50311.0535 | 31.2685 | 257 | 0.00011545 | 1291 | 1017.6191 | 817 | 0.098498 | 25.314 | 771 | 0.07 | 1774
643 | PENRYN 1105154362 | 152561105 | PENRYN 1105 | 154362 | FALSE | 11970.1824 | 3480.2712 | 2.163 | 90 | 0.00011044 | 1403 | 797.5542 | 943 | 0.098415 | 8.8574 | 772 |  | 2686
10663 | SAN RAMON 2102CB | 14232102 | SAN RAMON 2102 | CB | FALSE | 3412.1639 | 2836.6716 | 1.763 | 16 | 0.00010435 | 1543 | 961.0572 | 853 | 0.098349 | 1.5736 | 773 | 0.87 | 758
7571 | BROWNS VALLEY 110193870 | 152921101 | BROWNS VALLEY 1101 | 93870 | FALSE | 54990.4582 | 29826.9597 | 18.5376 | 342 | 6.6942e-05 | 2559 | 1508.5624 | 593 | 0.098287 | 33.6143 | 774 | 0.09 | 1545
9322 | MONTICELLO 1101CB | 43051101 | MONTICELLO 1101 | CB | TRUE | 859.9008 | 859.9008 | 0.53443 | 5 | 0.00010841 | 1440 | 866.0652 | 904 | 0.098274 | 0.49137 | 775 | 0.05 | 1958
5943 | TEMPLETON 2113A10 | 183052113 | TEMPLETON 2113 | A10 | FALSE | 49945.6996 | 49945.6996 | 31.0415 | 264 | 7.3622e-05 | 2377 | 1325.7939 | 671 | 0.098002 | 25.8725 | 776 | 7.4 | 446
5478 | PENRYN 11072706 | 152561107 | PENRYN 1107 | 2706 | FALSE | 23999.9081 | 9304.8867 | 5.783 | 190 | 0.0001407 | 858 | 837.755 | 918 | 0.09785 | 18.5915 | 777 | 0.94 | 743
3757 | WILLITS 1104934 | 42661104 | WILLITS 1104 | 934 | FALSE | 49660.3767 | 49660.3767 | 30.8641 | 279 | 9.3799e-05 | 1799 | 1233.6573 | 711 | 0.097599 | 27.2301 | 778 | 35.78 | 211
7329 | CORRAL 110213498 | 162991102 | CORRAL 1102 | 13498 | FALSE | 1603.6406 | 1585.9579 | 0.98568 | 13 | 0.00013812 | 892 | 567.2293 | 1131 | 0.097071 | 1.2619 | 779 | 0.06 | 1831
6184 | PEORIA 170190090 | 163781701 | PEORIA 1701 | 90090 | FALSE | 48332.111 | 48332.111 | 30.0386 | 168 | 9.2359e-05 | 1833 | 1129.7718 | 764 | 0.09692 | 16.2826 | 780 | 0.05 | 2011
1027 | OILFIELDS 110383158 | 182391103 | OILFIELDS 1103 | 83158 | FALSE | 31398.3782 | 28429.994 | 17.6694 | 132 | 6.3068e-05 | 2679 | 1552.5213 | 577 | 0.09689 | 12.7894 | 781 | 0.06 | 1781
3208 | WILLITS 11032500 | 42661103 | WILLITS 1103 | 2500 | FALSE | 48136.3959 | 48136.3959 | 29.917 | 143 | 8.5236e-05 | 2049 | 1216.4356 | 720 | 0.096773 | 13.8385 | 782 | 0.21 | 1155
9576 | LLAGAS 2104603392 | 83182104 | LLAGAS 2104 | 603392 | FALSE | 5227.4341 | 4685.9835 | 2.9124 | 17 | 5.2363e-05 | 2983 | 1917.7994 | 469 | 0.096621 | 1.6426 | 783 |  | 3382
211 | APPLE HILL 110313312 | 153661103 | APPLE HILL 1103 | 13312 | FALSE | 28501.0245 | 21155.7388 | 13.1484 | 190 | 0.00021994 | 321 | 408.8559 | 1287 | 0.096554 | 18.3453 | 784 | 0.12 | 1376
1106 | BANGOR 11011958 | 103191101 | BANGOR 1101 | 1958 | FALSE | 54465.3426 | 54465.3426 | 33.8504 | 353 | 0.00011848 | 1218 | 944.1299 | 865 | 0.096142 | 33.9382 | 785 | 0.29 | 1022
5073 | LAYTONVILLE 1102CB | 42681102 | LAYTONVILLE 1102 | CB | FALSE | 20899.9329 | 19267.3702 | 11.9747 | 95 | 0.00020717 | 375 | 574.8898 | 1127 | 0.095782 | 9.0993 | 786 | 5.57 | 485
7859 | MOUNTAIN QUARRIES 210135466 | 152282101 | MOUNTAIN QUARRIES 2101 | 35466 | FALSE | 11836.6618 | 11836.6618 | 7.3565 | 82 | 0.00016771 | 578 | 531.3358 | 1171 | 0.095562 | 7.8361 | 787 | 0.06 | 1799
871 | PEORIA 17019811 | 163781701 | PEORIA 1701 | 9811 | FALSE | 14351.9184 | 5776.4657 | 3.5901 | 92 | 8.2868e-05 | 2133 | 845.358 | 914 | 0.095333 | 8.7707 | 788 | 0.03 | 2316
669 | CABRILLO 1103CB | 183101103 | CABRILLO 1103 | CB | TRUE | 7060.6838 | 875.6492 | 0.54422 | 45 | 5.6384e-05 | 2879 | 1585.2096 | 566 | 0.095165 | 4.2824 | 789 | 0.89 | 750
3438 | CALISTOGA 1102CB | 42711102 | CALISTOGA 1102 | CB | TRUE | 3890.2841 | 517.8814 | 0.32187 | 37 | 0.00015375 | 712 | 238.7834 | 1569 | 0.095153 | 3.5207 | 790 | 0.1 | 1501
8923 | SUNOL 1101CB | 14241101 | SUNOL 1101 | CB | FALSE | 9278.0237 | 5281.0095 | 3.2822 | 53 | 6.9821e-05 | 2480 | 949.0975 | 862 | 0.095135 | 5.0422 | 791 | 0.02 | 2553
5883 | SILVERADO 2104632 | 43432104 | SILVERADO 2104 | 632 | FALSE | 29843.7661 | 29492.7895 | 18.3299 | 193 | 0.00011902 | 1207 | 950.7759 | 861 | 0.094959 | 18.327 | 792 | 90.53 | 32
5762 | CHALLENGE 11021064 | 103201102 | CHALLENGE 1102 | 1064 | FALSE | 31650.7422 | 31650.7422 | 19.6711 | 179 | 9.295e-05 | 1824 | 1110.3932 | 771 | 0.094905 | 16.9879 | 793 | 64.19 | 79
847 | CURTIS 17026008 | 163351702 | CURTIS 1702 | 6008 | FALSE | 37504.3181 | 37504.3181 | 23.3091 | 236 | 8.3382e-05 | 2122 | 1032.7499 | 806 | 0.094797 | 22.3721 | 794 | 0.31 | 1010
7905 | CAYETANO 2109CB | 14422109 | CAYETANO 2109 | CB | FALSE | 8828.3789 | 2269.8172 | 1.4107 | 51 | 8.6513e-05 | 2023 | 1197.2249 | 732 | 0.094773 | 4.8334 | 795 | 0.08 | 1602
6145 | OAKHURST 110210100 | 254421102 | OAKHURST 1102 | 10100 | FALSE | 18902.6869 | 16723.3035 | 10.3936 | 142 | 0.0001056 | 1504 | 1406.8011 | 635 | 0.094733 | 13.4521 | 796 | 0.13 | 1337
6083 | MILPITAS 1109XR524 | 82831109 | MILPITAS 1109 | XR524 | FALSE | 17990.142 | 17523.6666 | 10.891 | 59 | 7.365e-05 | 2373 | 1425.9142 | 629 | 0.09443 | 5.5714 | 797 | 0.13 | 1349
370 | UKIAH 1114CB | 42771114 | UKIAH 1114 | CB | FALSE | 14024.7064 | 1067.201 | 0.66327 | 93 | 0.00014666 | 778 | 560.4187 | 1134 | 0.094346 | 8.7742 | 798 | 0.02 | 2531
7085 | MESA 1103854149 | 182821103 | MESA 1103 | 854149 | FALSE | 1703.8848 | 1563.4443 | 0.97169 | 12 | 3.9219e-05 | 3281 | 2116.0059 | 424 | 0.094333 | 1.132 | 799 |  | 3095
8026 | PEORIA 1704CB | 163781704 | PEORIA 1704 | CB | FALSE | 14181.9325 | 13470.2412 | 8.3718 | 64 | 8.6926e-05 | 2014 | 1158.1157 | 750 | 0.094159 | 6.0262 | 800 | 0.04 | 2092
4910 | PUEBLO 2103373667 | 43292103 | PUEBLO 2103 | 373667 | FALSE | 6861.5817 | 5269.4021 | 3.275 | 45 | 0.00010834 | 1444 | 757.3214 | 967 | 0.09414 | 4.2363 | 801 |  | 2927
3504 | MOLINO 1102396 | 42571102 | MOLINO 1102 | 396 | FALSE | 25908.1895 | 25908.1895 | 16.102 | 182 | 0.00013862 | 887 | 571.5533 | 1129 | 0.093951 | 17.099 | 802 | 46.49 | 141
8266 | LAS POSITAS 2108MR182 | 14402108 | LAS POSITAS 2108 | MR182 | FALSE | 11548.6884 | 10768.7759 | 6.6928 | 56 | 6.1377e-05 | 2738 | 1819.6137 | 502 | 0.093921 | 5.2596 | 803 | 0.09 | 1515
6506 | CALAVERAS CEMENT 11014786 | 162211101 | CALAVERAS CEMENT 1101 | 4786 | FALSE | 28973.985 | 28973.985 | 18.0074 | 173 | 9.6661e-05 | 1720 | 894.0898 | 886 | 0.09378 | 16.224 | 804 | 0.23 | 1115
1161 | WYANDOTTE 110777578 | 102911107 | WYANDOTTE 1107 | 77578 | FALSE | 51848.8987 | 34427.9014 | 21.3971 | 389 | 0.00014958 | 742 | 862.3434 | 907 | 0.09328 | 36.2858 | 805 | 0.14 | 1325
5393 | GARBERVILLE 11024744 | 192221102 | GARBERVILLE 1102 | 4744 | FALSE | 32972.1771 | 27938.0536 | 17.3636 | 161 | 0.00026417 | 184 | 386.3695 | 1311 | 0.093231 | 15.0101 | 806 | 0.03 | 2396
5755 | PENRYN 11072704 | 152561107 | PENRYN 1107 | 2704 | FALSE | 9132.5937 | 2300.3426 | 1.4297 | 76 | 0.00016088 | 633 | 611.8282 | 1093 | 0.093023 | 7.0698 | 807 | 0.54 | 874
8038 | WILLITS 1103826 | 42661103 | WILLITS 1103 | 826 | FALSE | 12455.7726 | 12455.7726 | 7.7413 | 89 | 0.00010691 | 1478 | 923.3771 | 872 | 0.092902 | 8.2683 | 808 | 15.71 | 347
5718 | PETALUMA C 1108233646 | 42631108 | PETALUMA C 1108 | 233646 | FALSE | 18091.6284 | 15102.5612 | 9.3863 | 127 | 8.2168e-05 | 2147 | 1174.21 | 744 | 0.092653 | 11.7669 | 809 |  | 2976
7314 | CLARKSVILLE 210575884 | 153612105 | CLARKSVILLE 2105 | 75884 | FALSE | 18035.3275 | 17165.4943 | 10.6684 | 94 | 0.00017444 | 533 | 718.5697 | 1003 | 0.09258 | 8.7025 | 810 | 3.43 | 548
837 | DIAMOND SPRINGS 11071402 | 152261107 | DIAMOND SPRINGS 1107 | 1402 | FALSE | 71104.0432 | 71104.0432 | 44.1915 | 541 | 9.1419e-05 | 1862 | 1211.8423 | 726 | 0.092281 | 49.924 | 811 | 35.4 | 214
1640 | JESSUP 1101CB | 103441101 | JESSUP 1101 | CB | FALSE | 9345.3494 | 2462.2686 | 1.5303 | 66 | 0.00012054 | 1177 | 1190.2745 | 738 | 0.092174 | 6.0835 | 812 | 0.04 | 2090
2558 | PENRYN 1103660 | 152561103 | PENRYN 1103 | 660 | FALSE | 31347.0514 | 16353.7146 | 10.1639 | 233 | 0.00011883 | 1211 | 1011.3875 | 826 | 0.092166 | 21.4747 | 813 | 0.63 | 835
9244 | KERN OIL 110646960 | 252721106 | KERN OIL 1106 | 46960 | FALSE | 3112.6164 | 1465.0556 | 0.91054 | 14 | 5.4278e-05 | 2938 | 2071.3937 | 437 | 0.092145 | 1.29 | 814 | 0.02 | 2539
4181 | MONTICELLO 1101666 | 43051101 | MONTICELLO 1101 | 666 | FALSE | 21923.7063 | 19462.335 | 12.0959 | 90 | 5.9029e-05 | 2805 | 1514.7635 | 588 | 0.092048 | 8.2843 | 815 | 0.87 | 754
8910 | BRIDGEVILLE 110255612 | 192461102 | BRIDGEVILLE 1102 | 55612 | FALSE | 35781.5314 | 35781.5314 | 22.2384 | 93 | 0.00015401 | 707 | 611.9681 | 1092 | 0.090894 | 8.4532 | 816 | 0.12 | 1370
3415 | PARADISE 1104409622 | 102831104 | PARADISE 1104 | 409622 | FALSE | 20757.639 | 20534.7896 | 12.7625 | 156 | 0.00034981 | 90 | 622.0881 | 1080 | 0.090831 | 14.1696 | 817 |  | 2825
4056 | CALAVERAS CEMENT 110113424 | 162211101 | CALAVERAS CEMENT 1101 | 13424 | FALSE | 5801.6622 | 2404.2277 | 1.4942 | 43 | 0.00013059 | 1000 | 649.8195 | 1066 | 0.090714 | 3.9007 | 818 | 0.03 | 2394
345 | COTTONWOOD 1101384360 | 102931101 | COTTONWOOD 1101 | 384360 | FALSE | 10034.7798 | 7892.4211 | 4.9052 | 70 | 9.2299e-05 | 1835 | 1163.0519 | 748 | 0.090426 | 6.3298 | 819 |  | 2667
287 | WHITMORE 11011598 | 103601101 | WHITMORE 1101 | 1598 | FALSE | 53928.0023 | 53928.0023 | 33.5165 | 251 | 9.7528e-05 | 1700 | 806.3409 | 933 | 0.09042 | 22.6955 | 820 | 22.35 | 294
8279 | LOW GAP 110186816 | 192411101 | LOW GAP 1101 | 86816 | FALSE | 7103.5026 | 7103.5026 | 4.4149 | 51 | 0.00023289 | 272 | 393.4562 | 1304 | 0.090319 | 4.6062 | 821 | 6.82 | 458
7426 | SANTA MARIA 1108M18 | 182671108 | SANTA MARIA 1108 | M18 | FALSE | 28757.9291 | 24562.1098 | 15.2655 | 81 | 5.4886e-05 | 2918 | 1831.3141 | 496 | 0.090027 | 7.2922 | 822 | 0.57 | 861
7586 | KONOCTI 1102948 | 43311102 | KONOCTI 1102 | 948 | FALSE | 12598.6878 | 10159.6075 | 6.3142 | 73 | 6.6707e-05 | 2564 | 1385.8323 | 644 | 0.089784 | 6.5542 | 823 | 0.06 | 1788
8787 | GIRVAN 1102212096 | 103401102 | GIRVAN 1102 | 212096 | FALSE | 6500.9175 | 4124.0159 | 2.5631 | 42 | 6.3229e-05 | 2670 | 1654.3016 | 540 | 0.089733 | 3.7688 | 824 |  | 3265
10586 | LOS MOLINOS 1101297862 | 103481101 | LOS MOLINOS 1101 | 297862 | TRUE | 519.2262 | 503.2242 | 0.31276 | 4 | 7.9187e-05 | 2228 | 3345.084 | 219 | 0.089567 | 0.35827 | 825 |  | 3575
6573 | SISQUOC 1103858898 | 182811103 | SISQUOC 1103 | 858898 | FALSE | 31911.4059 | 31551.7735 | 19.6096 | 152 | 4.9929e-05 | 3040 | 1510.095 | 592 | 0.089508 | 13.6052 | 826 |  | 3043
10830 | PETALUMA C 1109373772 | 42631109 | PETALUMA C 1109 | 373772 | TRUE | 28.6691 | 28.6691 | 0.017818 | 2 | 0.00012505 | 1097 | 655.2599 | 1058 | 0.089417 | 0.17883 | 827 | 1.87 | 637
817 | CLOVERDALE 1102570 | 42821102 | CLOVERDALE 1102 | 570 | FALSE | 34272.8021 | 28557.0384 | 17.7483 | 199 | 0.00010582 | 1500 | 921.351 | 874 | 0.089292 | 17.7691 | 828 | 0.22 | 1129
5781 | SAN JOAQUIN #3 11035100 | 252531103 | SAN JOAQUIN #3 1103 | 5100 | FALSE | 34326.3844 | 34326.3844 | 21.334 | 204 | 8.9144e-05 | 1942 | 1331.1763 | 667 | 0.089218 | 18.2004 | 829 | 0.33 | 989
6729 | SAN LUIS OBISPO 110788962 | 182631107 | SAN LUIS OBISPO 1107 | 88962 | FALSE | 6442.5415 | 3996.9259 | 2.4841 | 45 | 4.8649e-05 | 3070 | 1156.9132 | 752 | 0.089174 | 4.0128 | 830 | 0.04 | 2070
5238 | DIAMOND SPRINGS 110656026 | 152261106 | DIAMOND SPRINGS 1106 | 56026 | FALSE | 24339.1905 | 24339.1905 | 15.1269 | 158 | 0.00012905 | 1028 | 717.5714 | 1005 | 0.089061 | 14.0716 | 831 | 0.07 | 1750
4137 | UKIAH 1114528 | 42771114 | UKIAH 1114 | 528 | FALSE | 19817.3234 | 6048.4547 | 3.7591 | 110 | 0.00013971 | 873 | 614.5051 | 1089 | 0.08906 | 9.7966 | 832 | 0.03 | 2395
2145 | CALISTOGA 1101736 | 42711101 | CALISTOGA 1101 | 736 | FALSE | 55772.0682 | 55772.0682 | 34.6626 | 350 | 0.00013305 | 957 | 690.2141 | 1030 | 0.088841 | 31.0945 | 833 | 98.57 | 21
8817 | WYANDOTTE 1105CB | 102911105 | WYANDOTTE 1105 | CB | FALSE | 21689.1163 | 18499.2196 | 11.4973 | 14 | 0.00021618 | 336 | 754.1992 | 970 | 0.088539 | 1.2395 | 834 | 0.04 | 2124
3899 | PEORIA 170510580 | 163781705 | PEORIA 1705 | 10580 | FALSE | 18949.2019 | 12416.9837 | 7.7172 | 129 | 0.00010187 | 1606 | 1422.4147 | 630 | 0.088489 | 11.415 | 835 | 0.05 | 1984
5666 | WOODSIDE 110147872 | 24251101 | WOODSIDE 1101 | 47872 | FALSE | 6709.5897 | 6709.5897 | 4.17 | 52 | 0.00017338 | 538 | 451.2799 | 1248 | 0.088422 | 4.5979 | 836 | 1.21 | 701
7241 | ATASCADERO 1103A14 | 182541103 | ATASCADERO 1103 | A14 | FALSE | 40416.4237 | 40416.4237 | 25.119 | 152 | 7.4204e-05 | 2351 | 1301.8625 | 681 | 0.088418 | 13.4395 | 837 | 0.07 | 1686
878 | FROGTOWN 170275252 | 163451702 | FROGTOWN 1702 | 75252 | FALSE | 98047.1456 | 93174.0996 | 57.9081 | 401 | 7.7651e-05 | 2271 | 1110.9654 | 770 | 0.088153 | 35.3494 | 838 | 0.18 | 1204
4836 | GRASS VALLEY 11031700 | 152031103 | GRASS VALLEY 1103 | 1700 | FALSE | 35014.8434 | 34930.2373 | 21.7093 | 255 | 0.00014818 | 762 | 706.0979 | 1016 | 0.087918 | 22.4191 | 839 | 0.15 | 1281
7987 | BELL 1108339792 | 152701108 | BELL 1108 | 339792 | FALSE | 5788.3897 | 4221.2236 | 2.6235 | 43 | 0.00011358 | 1331 | 632.6218 | 1077 | 0.087729 | 3.7723 | 840 |  | 3181
8725 | LLAGAS 2101984552 | 83182101 | LLAGAS 2101 | 984552 | FALSE | 9221.3481 | 7304.6852 | 4.5399 | 53 | 7.8725e-05 | 2243 | 1388.9327 | 642 | 0.087511 | 4.6381 | 841 |  | 3254
4715 | GIRVAN 110280726 | 103401102 | GIRVAN 1102 | 80726 | FALSE | 29692.476 | 12661.4918 | 7.8692 | 217 | 0.00011841 | 1219 | 698.1741 | 1024 | 0.087369 | 18.9591 | 842 | 0.05 | 2014
5678 | SAN LUIS OBISPO 1102348318 | 182631102 | SAN LUIS OBISPO 1102 | 348318 | TRUE | 597.0392 | 597.0392 | 0.37106 | 6 | 4.521e-05 | 3156 | 2033.0031 | 451 | 0.087346 | 0.52408 | 843 |  | 2972
8497 | BEAR VALLEY 210576694 | 252192105 | BEAR VALLEY 2105 | 76694 | FALSE | 7317.351 | 7317.351 | 4.5478 | 37 | 7.2614e-05 | 2401 | 1607.6376 | 560 | 0.087295 | 3.2299 | 844 | 0.06 | 1907
4933 | RACETRACK 17039190 | 163761703 | RACETRACK 1703 | 9190 | FALSE | 14438.9195 | 14438.9195 | 8.9738 | 104 | 0.00015927 | 649 | 560.2186 | 1135 | 0.087115 | 9.06 | 845 | 0.12 | 1405
10437 | RIO DELL 110275970 | 192251102 | RIO DELL 1102 | 75970 | FALSE | 11378.8384 | 11378.8384 | 7.072 | 33 | 0.0002301 | 284 | 549.4916 | 1145 | 0.08694 | 2.869 | 846 | 0.07 | 1700
3279 | OAKHURST 1101CB | 254421101 | OAKHURST 1101 | CB | FALSE | 4772.9739 | 3724.6766 | 2.3149 | 47 | 0.00012677 | 1067 | 1037.4258 | 802 | 0.086583 | 4.0694 | 847 | 3.02 | 568
6810 | KESWICK 11011590 | 103451101 | KESWICK 1101 | 1590 | FALSE | 10388.8945 | 10388.8945 | 6.4567 | 63 | 0.00013775 | 898 | 828.3749 | 922 | 0.086534 | 5.4516 | 848 | 0.58 | 859
2304 | SAN JOAQUIN #3 1103CB | 252531103 | SAN JOAQUIN #3 1103 | CB | FALSE | 45670.4217 | 45670.4217 | 28.3844 | 294 | 9.5334e-05 | 1751 | 1012.9872 | 821 | 0.086354 | 25.3881 | 849 | 0.47 | 909
7373 | TIVY VALLEY 11077380 | 252941107 | TIVY VALLEY 1107 | 7380 | FALSE | 45386.7416 | 20845.5533 | 12.9556 | 240 | 4.451e-05 | 3175 | 2480.8683 | 345 | 0.086218 | 20.6923 | 850 | 0.07 | 1707
1492 | STILLWATER 110148950 | 103561101 | STILLWATER 1101 | 48950 | FALSE | 20081.7793 | 20081.7793 | 12.4809 | 145 | 0.00013937 | 880 | 612.4235 | 1091 | 0.085979 | 12.467 | 851 | 0.08 | 1608
3172 | RED BLUFF 1105161818 | 103541105 | RED BLUFF 1105 | 161818 | TRUE | 7658.7384 | 212.3638 | 0.13198 | 59 | 5.7073e-05 | 2859 | 1511.2201 | 590 | 0.08588 | 5.0669 | 852 | 0.02 | 2419
5834 | SANTA YNEZ 1102320270 | 182721102 | SANTA YNEZ 1102 | 320270 | FALSE | 27707.7793 | 13648.6049 | 8.4827 | 137 | 5.4419e-05 | 2934 | 1519.0093 | 586 | 0.08574 | 11.7464 | 853 | 0.03 | 2384
742 | MORGAN HILL 2105XR176 | 83242105 | MORGAN HILL 2105 | XR176 | FALSE | 44222.2898 | 36252.5852 | 22.5311 | 309 | 8.4526e-05 | 2077 | 1005.2282 | 831 | 0.085689 | 26.478 | 854 | 0.3 | 1018
8450 | MARTELL 1102CB | 163011102 | MARTELL 1102 | CB | FALSE | 10972.0561 | 9142.0744 | 5.6818 | 69 | 0.00014429 | 809 | 861.7339 | 908 | 0.08567 | 5.9113 | 855 | 0.08 | 1609
3883 | COTATI 1102167726 | 42271102 | COTATI 1102 | 167726 | FALSE | 6114.3744 | 6114.3744 | 3.8001 | 50 | 7.7871e-05 | 2262 | 1006.5075 | 830 | 0.08544 | 4.272 | 856 |  | 2859
10186 | CLAYTON 22159765 | 12022215 | CLAYTON 2215 | 9765 | TRUE | 1507.3257 | 425.4979 | 0.26445 | 16 | 4.0376e-05 | 3257 | 1304.4493 | 680 | 0.085394 | 1.3663 | 857 | 1.11 | 715
5425 | CORNING 110187304 | 103331101 | CORNING 1101 | 87304 | FALSE | 23764.1584 | 4634.8119 | 2.8806 | 100 | 0.00010497 | 1530 | 1066.2761 | 788 | 0.085339 | 8.5339 | 858 | 0.01 | 2567
4113 | PHILO 1101CB | 42601101 | PHILO 1101 | CB | FALSE | 79932.4071 | 51306.3985 | 31.8871 | 469 | 0.00011158 | 1379 | 802.5661 | 939 | 0.085283 | 39.9976 | 859 | 0.15 | 1300
10106 | GEYSERVILLE 1102537096 | 42891102 | GEYSERVILLE 1102 | 537096 | TRUE | 844.1463 | 775.9765 | 0.48227 | 6 | 0.00013769 | 900 | 635.9861 | 1072 | 0.085228 | 0.51137 | 860 |  | 3492
9409 | CLAY 1102CB | 163341102 | CLAY 1102 | CB | FALSE | 3161.2302 | 1492.4904 | 0.92759 | 19 | 0.00014572 | 793 | 421.9203 | 1271 | 0.085217 | 1.6191 | 861 | 0.04 | 2178
6247 | ELK CREEK 11012004 | 102781101 | ELK CREEK 1101 | 2004 | FALSE | 86935.2431 | 40225.06 | 25 | 174 | 5.0473e-05 | 3024 | 1960.2216 | 462 | 0.085175 | 14.8204 | 862 | 0.02 | 2549
2719 | SAN LUIS OBISPO 1104V10 | 182631104 | SAN LUIS OBISPO 1104 | V10 | FALSE | 7811.0705 | 3504.8307 | 2.1783 | 54 | 0.00010776 | 1457 | 473.6801 | 1219 | 0.085103 | 4.5956 | 863 |  | 2796
541 | TEMPLETON 2113R82 | 183052113 | TEMPLETON 2113 | R82 | FALSE | 111857.9563 | 61789.4025 | 38.4024 | 563 | 6.819e-05 | 2530 | 1317.1207 | 675 | 0.084913 | 47.806 | 864 | 0.03 | 2235
7060 | BIG BEND 1102CB | 103751102 | BIG BEND 1102 | CB | FALSE | 27411.8293 | 27411.8293 | 17.0366 | 139 | 0.00012425 | 1113 | 619.8955 | 1081 | 0.084888 | 11.7994 | 865 | 0.48 | 900
7634 | IONE 1101L3141 | 163881101 | IONE 1101 | L3141 | FALSE | 22528.5486 | 22255.8256 | 13.8321 | 97 | 7.5574e-05 | 2322 | 1221.0879 | 717 | 0.084539 | 8.2002 | 866 | 0.09 | 1535
1449 | FORT SEWARD 1122CB | 192321122 | FORT SEWARD 1122 | CB | FALSE | 35287.6178 | 28413.1031 | 17.6589 | 111 | 0.00022836 | 290 | 382.0524 | 1317 | 0.084457 | 9.3748 | 867 | 0.06 | 1910
3137 | MOLINO 1102104 | 42571102 | MOLINO 1102 | 104 | FALSE | 34991.65 | 34991.65 | 21.7475 | 235 | 0.00014639 | 782 | 473.3298 | 1220 | 0.084332 | 19.818 | 868 | 67.59 | 72
4967 | NARROWS 21052748 | 153132105 | NARROWS 2105 | 2748 | FALSE | 31538.4076 | 20831.4864 | 12.9469 | 245 | 0.00018393 | 480 | 692.2861 | 1029 | 0.084145 | 20.6156 | 869 | 0.1 | 1477
9631 | EDENVALE 2107739448 | 82952107 | EDENVALE 2107 | 739448 | FALSE | 3763.2993 | 2860.1443 | 1.7776 | 12 | 4.5704e-05 | 3149 | 1064.5547 | 790 | 0.084104 | 1.0093 | 870 |  | 3393
5449 | PENRYN 110351658 | 152561103 | PENRYN 1103 | 51658 | FALSE | 14039.3789 | 13140.1209 | 8.1666 | 108 | 0.00011684 | 1253 | 818.1348 | 925 | 0.084002 | 9.0722 | 871 | 1.43 | 677
9940 | MILPITAS 110598568 | 82831105 | MILPITAS 1105 | 98568 | TRUE | 2444.4926 | 168.1421 | 0.1045 | 7 | 7.0182e-05 | 2465 | 834.7615 | 919 | 0.083995 | 0.58797 | 872 |  | 3457
4281 | PUEBLO 1105637242 | 43291105 | PUEBLO 1105 | 637242 | FALSE | 35417.2163 | 27085.716 | 16.8339 | 193 | 7.1873e-05 | 2424 | 1184.0184 | 740 | 0.083893 | 16.1913 | 873 |  | 2879
9696 | LAS GALLINAS A 1104507389 | 42991104 | LAS GALLINAS A 1104 | 507389 | TRUE | 305.6652 | 212.3341 | 0.13197 | 4 | 8.9376e-05 | 1934 | 719.0918 | 1002 | 0.083842 | 0.33537 | 874 |  | 3399
3446 | ELK CREEK 11012228 | 102781101 | ELK CREEK 1101 | 2228 | FALSE | 16654.619 | 5410.2105 | 3.3625 | 80 | 5.6416e-05 | 2878 | 1582.2639 | 568 | 0.082955 | 6.6364 | 875 | 0.03 | 2232
2644 | WILLITS 110391948 | 42661103 | WILLITS 1103 | 91948 | FALSE | 11942.5868 | 11942.5868 | 7.4224 | 69 | 0.00010599 | 1494 | 1019.808 | 815 | 0.082927 | 5.7219 | 876 | 0.99 | 733
2263 | SWIFT 2110XR366 | 83392110 | SWIFT 2110 | XR366 | FALSE | 17766.1133 | 13567.8022 | 8.4324 | 129 | 7.1306e-05 | 2437 | 1012.8648 | 822 | 0.082848 | 10.6874 | 877 | 0.21 | 1134
9623 | SANTA YNEZ 1104685160 | 182721104 | SANTA YNEZ 1104 | 685160 | TRUE | 2780.4715 | 943.7591 | 0.58655 | 17 | 5.0437e-05 | 3028 | 1467.3789 | 610 | 0.082766 | 1.407 | 878 |  | 3392
7942 | FULTON 11024994 | 42561102 | FULTON 1102 | 4994 | FALSE | 6920.6464 | 2185.8295 | 1.3585 | 45 | 0.00012652 | 1071 | 520.9041 | 1182 | 0.082765 | 3.7244 | 879 | 0.64 | 830
4041 | FROGTOWN 1702737236 | 163451702 | FROGTOWN 1702 | 737236 | FALSE | 14223.4405 | 14101.6239 | 8.7642 | 88 | 0.00012645 | 1074 | 720.3446 | 999 | 0.082425 | 7.2534 | 880 |  | 2868
4759 | COTATI 110379140 | 42271103 | COTATI 1103 | 79140 | FALSE | 19909.2046 | 15742.3512 | 9.7839 | 154 | 9.382e-05 | 1797 | 973.1017 | 848 | 0.082367 | 12.6845 | 881 | 7.99 | 438
1164 | BEAR VALLEY 2105454432 | 252192105 | BEAR VALLEY 2105 | 454432 | FALSE | 23226.2401 | 23226.2401 | 14.4352 | 112 | 5.5708e-05 | 2898 | 1234.8209 | 710 | 0.08233 | 9.221 | 882 |  | 2714
4634 | SHINGLE SPRINGS 211051790 | 153652110 | SHINGLE SPRINGS 2110 | 51790 | FALSE | 13931.0144 | 12725.5168 | 7.909 | 106 | 0.00015838 | 659 | 660.4485 | 1052 | 0.082229 | 8.7163 | 883 | 0.33 | 990
4491 | CALPELLA 1102144510 | 43411102 | CALPELLA 1102 | 144510 | FALSE | 8266.8346 | 5010.1846 | 3.1138 | 41 | 8.3654e-05 | 2104 | 950.8265 | 860 | 0.08218 | 3.3694 | 884 |  | 2896
3945 | DOBBINS 11015202 | 153741101 | DOBBINS 1101 | 5202 | FALSE | 27474.7329 | 26267.8985 | 16.3256 | 162 | 8.8527e-05 | 1973 | 910.6874 | 881 | 0.082155 | 13.3091 | 885 | 0.12 | 1403
5174 | CALAVERAS CEMENT 110111236 | 162211101 | CALAVERAS CEMENT 1101 | 11236 | FALSE | 31777.9091 | 31777.9091 | 19.7501 | 143 | 0.00011636 | 1262 | 616.8333 | 1086 | 0.081838 | 11.7029 | 886 | 0.05 | 2012
4695 | SILVERADO 21043485 | 43432104 | SILVERADO 2104 | 3485 | FALSE | 2803.9876 | 2803.9876 | 1.7427 | 23 | 0.00011552 | 1286 | 723.112 | 996 | 0.081749 | 1.8802 | 887 |  | 2910
5312 | PETALUMA C 1108632 | 42631108 | PETALUMA C 1108 | 632 | FALSE | 23697.8024 | 23697.8024 | 14.7283 | 81 | 6.7966e-05 | 2537 | 1288.5976 | 686 | 0.081559 | 6.6063 | 888 | 0.05 | 2027
8333 | BEAR VALLEY 21054609 | 252192105 | BEAR VALLEY 2105 | 4609 | FALSE | 7321.9227 | 7321.9227 | 4.5506 | 41 | 3.728e-05 | 3310 | 2145.8949 | 414 | 0.081381 | 3.3366 | 889 | 0.06 | 1911
7354 | JOLON 11027004 | 182981102 | JOLON 1102 | 7004 | FALSE | 31981.9475 | 12745.3246 | 7.9213 | 128 | 5.8428e-05 | 2822 | 1357.6846 | 659 | 0.081062 | 10.3759 | 890 | 0.03 | 2338
4785 | MORGAN HILL 2111XR398 | 83242111 | MORGAN HILL 2111 | XR398 | FALSE | 63835.5147 | 60665.5292 | 37.7039 | 341 | 8.3663e-05 | 2103 | 945.2451 | 864 | 0.080766 | 27.5412 | 891 | 0.67 | 814
9589 | CLAY 11031821 | 163341103 | CLAY 1103 | 1821 | FALSE | 6061.921 | 5767.6056 | 3.5846 | 33 | 6.9086e-05 | 2504 | 1429.8724 | 624 | 0.080483 | 2.6559 | 892 | 0.08 | 1594
1075 | LINCOLN 110195756 | 153701101 | LINCOLN 1101 | 95756 | FALSE | 29109.9093 | 11950.3804 | 7.4272 | 200 | 7.0248e-05 | 2461 | 1033.0935 | 805 | 0.080379 | 16.0759 | 893 | 0.03 | 2343
3754 | PALMER 1101M82 | 183031101 | PALMER 1101 | M82 | FALSE | 23986.1463 | 17447.2632 | 10.8435 | 149 | 4.471e-05 | 3168 | 1573.1869 | 570 | 0.080327 | 11.9687 | 894 | 0.04 | 2147
5126 | CRESCENT MILLS 21012056 | 103132101 | CRESCENT MILLS 2101 | 2056 | FALSE | 10443.0868 | 8069.9513 | 5.0155 | 70 | 0.00011546 | 1289 | 677.9317 | 1037 | 0.080308 | 5.6215 | 895 | 3.29 | 551
7701 | SILVERADO 2102808 | 43432102 | SILVERADO 2102 | 808 | FALSE | 8110.4608 | 4081.7731 | 2.5368 | 39 | 8.0754e-05 | 2186 | 1061.2531 | 791 | 0.0803 | 3.1317 | 896 | 0.09 | 1528
1034 | HOOPA 11013290 | 192401101 | HOOPA 1101 | 3290 | FALSE | 21820.8937 | 21820.8937 | 13.5618 | 135 | 0.00032761 | 105 | 278.5419 | 1474 | 0.080281 | 10.8379 | 897 | 0.08 | 1641
7166 | GANSNER 1101372132 | 103021101 | GANSNER 1101 | 372132 | TRUE | 2259.794 | 673.2222 | 0.41841 | 13 | 0.00010261 | 1583 | 1099.8675 | 775 | 0.08025 | 1.0433 | 898 |  | 3103
9769 | UKIAH 1111807988 | 42771111 | UKIAH 1111 | 807988 | FALSE | 6722.2779 | 6706.2477 | 4.168 | 15 | 0.00010987 | 1413 | 855.2361 | 912 | 0.080023 | 1.2003 | 899 |  | 3415
6682 | OILFIELDS 1103643162 | 182391103 | OILFIELDS 1103 | 643162 | FALSE | 9798.1377 | 5532.3244 | 3.4384 | 41 | 6.7079e-05 | 2555 | 1192.2958 | 736 | 0.079941 | 3.2776 | 900 |  | 3054
10896 | CMC 1102CB | 183111102 | CMC 1102 | CB | TRUE | 581.8342 | 581.8342 | 0.36161 | 5 | 0.00015983 | 644 | 548.9355 | 1146 | 0.079905 | 0.39953 | 901 | 0.03 | 2328
2989 | KONOCTI 11024300 | 43311102 | KONOCTI 1102 | 4300 | FALSE | 43675.508 | 43384.1036 | 26.9634 | 268 | 0.00011959 | 1194 | 736.9291 | 987 | 0.079811 | 21.3893 | 902 | 28.67 | 249
10408 | POSO MOUNTAIN 21011703 | 253642101 | POSO MOUNTAIN 2101 | 1703 | FALSE | 3959.9015 | 1455.5285 | 0.90462 | 7 | 2.6035e-05 | 3487 | 3088.567 | 257 | 0.079525 | 0.55668 | 903 | 0.01 | 2618
6364 | PLACERVILLE 2106935216 | 153082106 | PLACERVILLE 2106 | 935216 | FALSE | 33848.7529 | 33848.7529 | 21.0371 | 204 | 0.00011214 | 1365 | 509.4897 | 1191 | 0.079474 | 16.2127 | 904 |  | 3025
4098 | WYANDOTTE 11071510 | 102911107 | WYANDOTTE 1107 | 1510 | FALSE | 41028.1557 | 41028.1557 | 25.4992 | 243 | 8.893e-05 | 1952 | 939.2458 | 866 | 0.079411 | 19.297 | 905 | 0.18 | 1216
7076 | CLARKSVILLE 210419632 | 153612104 | CLARKSVILLE 2104 | 19632 | FALSE | 14659.9971 | 8997.9268 | 5.5922 | 110 | 0.00013387 | 944 | 1009.1241 | 828 | 0.07935 | 8.7285 | 906 | 23.44 | 286
1230 | TEMPLETON 2113A08 | 183052113 | TEMPLETON 2113 | A08 | FALSE | 39406.6597 | 16842.5186 | 10.4677 | 257 | 7.6018e-05 | 2308 | 953.5418 | 857 | 0.079335 | 20.3891 | 907 | 0.05 | 2006
5155 | FOOTHILL 1101CB | 182951101 | FOOTHILL 1101 | CB | FALSE | 35256.7174 | 21554.4713 | 13.3962 | 149 | 5.7418e-05 | 2852 | 1255.3202 | 698 | 0.079316 | 11.8181 | 908 | 3.17 | 557
2049 | FRUITLAND 1141CB | 192311141 | FRUITLAND 1141 | CB | FALSE | 5135.5453 | 5135.5453 | 3.1918 | 17 | 0.00032833 | 104 | 166.3867 | 1733 | 0.079299 | 1.3481 | 909 | 0.73 | 794
4771 | OCEANO 1104Q12 | 182601104 | OCEANO 1104 | Q12 | FALSE | 25798.2458 | 18203.0478 | 11.3133 | 142 | 5.3235e-05 | 2958 | 1483.0103 | 602 | 0.079257 | 11.2544 | 910 | 0.12 | 1401
10844 | SPRING GAP 1702188426 | 162831702 | SPRING GAP 1702 | 188426 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00011833 | 1221 | 665.6862 | 1046 | 0.078773 | 0.078773 | 911 |  | 3613
1175 | HIGGINS 11044281 | 152691104 | HIGGINS 1104 | 4281 | FALSE | 21439.832 | 21439.832 | 13.3249 | 138 | 8.4234e-05 | 2085 | 980.9559 | 844 | 0.078646 | 10.8532 | 912 | 0.09 | 1527
9778 | HIGGINS 11097863 | 152691109 | HIGGINS 1109 | 7863 | FALSE | 6797.0988 | 6797.0988 | 4.2244 | 42 | 6.1162e-05 | 2744 | 1254.5183 | 699 | 0.078616 | 3.3019 | 913 | 0.06 | 1859
6230 | MONTICELLO 110193384 | 43051101 | MONTICELLO 1101 | 93384 | FALSE | 27406.0322 | 25967.2197 | 16.1387 | 101 | 6.3629e-05 | 2660 | 1407.9794 | 632 | 0.078583 | 7.9369 | 914 | 0.06 | 1857
9152 | MIDDLETOWN 11011314 | 43141101 | MIDDLETOWN 1101 | 1314 | FALSE | 1489.219 | 1489.219 | 0.92556 | 13 | 0.00014408 | 813 | 554.638 | 1141 | 0.078235 | 1.0171 | 915 | 7.88 | 439
10292 | BIG MEADOWS 21012248 | 102812101 | BIG MEADOWS 2101 | 2248 | FALSE | 14727.9744 | 14727.9744 | 9.1535 | 28 | 6.5811e-05 | 2594 | 1037.9427 | 801 | 0.077859 | 2.18 | 916 | 0.05 | 1922
3275 | OCEANO 1104Q10 | 182601104 | OCEANO 1104 | Q10 | FALSE | 38031.0006 | 38031.0006 | 23.6364 | 289 | 6.4596e-05 | 2621 | 1216.6013 | 719 | 0.077836 | 22.4946 | 917 | 7.07 | 452
5179 | HARTLEY 1102CB | 43211102 | HARTLEY 1102 | CB | FALSE | 18838.7982 | 5515.7018 | 3.428 | 135 | 0.00010957 | 1419 | 752.8216 | 973 | 0.077778 | 10.5 | 918 | 0.02 | 2544
8256 | MORGAN HILL 2105XR268 | 83242105 | MORGAN HILL 2105 | XR268 | FALSE | 12802.5937 | 12802.5937 | 7.9569 | 61 | 0.00011557 | 1284 | 557.5427 | 1138 | 0.077596 | 4.7333 | 919 | 0.46 | 913
1037 | MIDDLETOWN 11021312 | 43141102 | MIDDLETOWN 1102 | 1312 | FALSE | 15822.8795 | 15822.8795 | 9.834 | 120 | 0.00013526 | 925 | 772.6153 | 957 | 0.077577 | 9.3092 | 920 | 0.15 | 1291
3607 | OCEANO 1104V38 | 182601104 | OCEANO 1104 | V38 | FALSE | 27926.3564 | 19405.5321 | 12.0606 | 212 | 7.3599e-05 | 2379 | 651.082 | 1062 | 0.077544 | 16.4392 | 921 | 0.17 | 1245
9877 | CLOVERDALE 1102307342 | 42821102 | CLOVERDALE 1102 | 307342 | TRUE | 573.1034 | 354.0238 | 0.22003 | 6 | 0.00013565 | 923 | 341.2059 | 1386 | 0.077416 | 0.46449 | 922 |  | 3441
3974 | FITCH MOUNTAIN 111324550 | 42751113 | FITCH MOUNTAIN 1113 | 24550 | FALSE | 34688.2788 | 17797.4846 | 11.0612 | 203 | 9.3917e-05 | 1795 | 616.7423 | 1087 | 0.077338 | 15.6996 | 923 | 0.07 | 1711
962 | MIDDLETOWN 1102514 | 43141102 | MIDDLETOWN 1102 | 514 | FALSE | 8494.876 | 5391.2208 | 3.3507 | 71 | 0.00014873 | 755 | 482.2809 | 1214 | 0.077302 | 5.4884 | 924 | 0.09 | 1537
10365 | CURTIS 170349746 | 163351703 | CURTIS 1703 | 49746 | TRUE | 601.9007 | 601.9007 | 0.37408 | 3 | 0.00034014 | 97 | 221.8686 | 1601 | 0.077172 | 0.23152 | 925 | 0.04 | 2076
3098 | PETALUMA C 1108630 | 42631108 | PETALUMA C 1108 | 630 | FALSE | 6902.8394 | 2654.0652 | 1.6495 | 55 | 7.7866e-05 | 2263 | 873.6447 | 897 | 0.077168 | 4.2442 | 926 | 0.03 | 2363
6234 | SAN JUSTO 1101201311 | 183181101 | SAN JUSTO 1101 | 201311 | FALSE | 17668.9636 | 12645.7551 | 7.8594 | 108 | 6.4312e-05 | 2634 | 1215.4291 | 722 | 0.077053 | 8.3218 | 927 |  | 3015
6221 | GARBERVILLE 110135706 | 192221101 | GARBERVILLE 1101 | 35706 | FALSE | 16269.027 | 16269.027 | 10.1113 | 97 | 0.00041981 | 62 | 185.2954 | 1670 | 0.076898 | 7.4591 | 928 | 4.82 | 505
2802 | PENRYN 11072410 | 152561107 | PENRYN 1107 | 2410 | FALSE | 12099.1952 | 5248.3008 | 3.2618 | 96 | 0.00011208 | 1366 | 705.3971 | 1019 | 0.076748 | 7.3678 | 929 | 0.05 | 1959
8295 | COTATI 110387402 | 42271103 | COTATI 1103 | 87402 | FALSE | 18273.7697 | 18273.7697 | 11.3572 | 42 | 9.1928e-05 | 1846 | 973.3911 | 847 | 0.07664 | 3.2189 | 930 | 1.23 | 698
10268 | TEJON 11023760 | 252931102 | TEJON 1102 | 3760 | FALSE | 10446.6343 | 10415.8967 | 6.4735 | 6 | 4.6244e-05 | 3131 | 4483.9501 | 110 | 0.076506 | 0.45904 | 931 | 0.03 | 2370
10279 | VOLTA 1102CB | 102541102 | VOLTA 1102 | CB | FALSE | 5307.8327 | 5307.8327 | 3.2988 | 25 | 0.0001265 | 1072 | 430.0286 | 1260 | 0.076253 | 1.9063 | 932 | 12.67 | 370
9092 | FORT ROSS 11214614 | 42851121 | FORT ROSS 1121 | 4614 | FALSE | 20206.8972 | 20206.8972 | 12.5587 | 95 | 0.00011071 | 1396 | 701.2564 | 1022 | 0.075773 | 7.1985 | 933 |  | 3306
3923 | AUBERRY 110137536 | 254151101 | AUBERRY 1101 | 37536 | FALSE | 8687.6907 | 8687.6907 | 5.3994 | 60 | 4.0037e-05 | 3267 | 1761.4133 | 511 | 0.075515 | 4.5309 | 934 | 0.07 | 1729
5756 | CABRILLO 11031437 | 183101103 | CABRILLO 1103 | 1437 | FALSE | 7854.9148 | 4577.3445 | 2.8448 | 39 | 5.9276e-05 | 2795 | 1361.2842 | 657 | 0.075332 | 2.9379 | 935 | 0.03 | 2404
6109 | FITCH MOUNTAIN 1113583202 | 42751113 | FITCH MOUNTAIN 1113 | 583202 | FALSE | 15783.8472 | 7874.8461 | 4.8942 | 106 | 0.00010066 | 1631 | 594.6514 | 1106 | 0.075101 | 7.9607 | 936 | 0.05 | 2004
4163 | WILLITS 1103538 | 42661103 | WILLITS 1103 | 538 | FALSE | 10176.8073 | 10176.8073 | 6.3249 | 48 | 6.409e-05 | 2642 | 1480.7363 | 603 | 0.074937 | 3.597 | 937 | 2.14 | 620
9780 | SONOMA 1107854266 | 42721107 | SONOMA 1107 | 854266 | TRUE | 966.2653 | 321.4105 | 0.19976 | 6 | 9.5722e-05 | 1736 | 1072.2651 | 785 | 0.074827 | 0.44896 | 938 |  | 3418
260 | BRUNSWICK 11067099 | 152481106 | BRUNSWICK 1106 | 7099 | FALSE | 12439.4387 | 12439.4387 | 7.7312 | 83 | 0.00011588 | 1273 | 664.3931 | 1047 | 0.074794 | 6.2079 | 939 | 0.28 | 1036
3084 | GEYSERVILLE 1102274 | 42891102 | GEYSERVILLE 1102 | 274 | FALSE | 29743.739 | 10398.2127 | 6.4625 | 173 | 0.00011599 | 1270 | 494.2707 | 1207 | 0.074787 | 12.9382 | 940 | 1.24 | 695
6342 | MADISON 21011606 | 63172101 | MADISON 2101 | 1606 | TRUE | 42761.0948 | 254.3531 | 0.15808 | 280 | 7.0898e-05 | 2446 | 1248.3017 | 701 | 0.074511 | 20.863 | 941 | 0.02 | 2551
10492 | DRUM 1101CB | 152321101 | DRUM 1101 | CB | FALSE | 3483.5782 | 3483.5782 | 2.1651 | 16 | 0.00013085 | 995 | 558.6934 | 1136 | 0.074456 | 1.1913 | 942 | 21.08 | 302
874 | RISING RIVER 1101CB | 103551101 | RISING RIVER 1101 | CB | FALSE | 21509.9694 | 15956.2359 | 9.9169 | 121 | 5.192e-05 | 2995 | 1288.0652 | 687 | 0.074106 | 8.9669 | 943 | 0.03 | 2320
8386 | PEORIA 1705999 | 163781705 | PEORIA 1705 | 999 | FALSE | 3715.0604 | 3715.0604 | 2.3089 | 22 | 0.00010639 | 1488 | 1017.494 | 818 | 0.074075 | 1.6297 | 944 | 0.09 | 1529
7502 | FITCH MOUNTAIN 11136751 | 42751113 | FITCH MOUNTAIN 1113 | 6751 | FALSE | 36483.9202 | 36483.9202 | 22.6749 | 139 | 0.00018185 | 499 | 410.6545 | 1284 | 0.073927 | 10.2759 | 945 | 39.14 | 190
5338 | SAN JOAQUIN #3 1102CB | 252531102 | SAN JOAQUIN #3 1102 | CB | FALSE | 15601.4012 | 15601.4012 | 9.6963 | 97 | 0.00011323 | 1340 | 789.9349 | 952 | 0.073848 | 7.1632 | 946 | 0.18 | 1203
7052 | CALISTOGA 1101134232 | 42711101 | CALISTOGA 1101 | 134232 | FALSE | 11553.3534 | 2618.9112 | 1.6277 | 89 | 0.0001535 | 717 | 426.3987 | 1264 | 0.0737 | 6.5593 | 947 |  | 3092
10249 | SILVERADO 2102CB | 43432102 | SILVERADO 2102 | CB | TRUE | 2722.4304 | 952.8122 | 0.59218 | 22 | 0.00019758 | 405 | 236.9089 | 1576 | 0.073682 | 1.621 | 948 | 0.13 | 1352
6791 | CABRILLO 1104Y24 | 183101104 | CABRILLO 1104 | Y24 | FALSE | 31605.3339 | 30845.6135 | 19.1707 | 91 | 6.8807e-05 | 2514 | 1387.2959 | 643 | 0.073569 | 6.6947 | 949 | 0.26 | 1061
3606 | HORSESHOE 1101CB | 152571101 | HORSESHOE 1101 | CB | TRUE | 6455.7985 | 567.3027 | 0.35258 | 55 | 0.00018028 | 511 | 272.2112 | 1489 | 0.073561 | 4.0458 | 950 | 0.64 | 831
2673 | PUEBLO 2102792 | 43292102 | PUEBLO 2102 | 792 | FALSE | 33585.8452 | 31119.1615 | 19.3407 | 180 | 9.905e-05 | 1667 | 711.86 | 1012 | 0.073389 | 13.2101 | 951 | 87.74 | 36
4637 | SAN LUIS OBISPO 1104V40 | 182631104 | SAN LUIS OBISPO 1104 | V40 | FALSE | 37151.701 | 23652.2282 | 14.7 | 194 | 7.9558e-05 | 2220 | 1050.089 | 797 | 0.073389 | 14.2374 | 952 | 0.06 | 1795
2241 | CURTIS 170247488 | 163351702 | CURTIS 1702 | 47488 | FALSE | 33425.2179 | 30588.7641 | 19.011 | 207 | 0.00011402 | 1320 | 706.1851 | 1015 | 0.07338 | 15.1897 | 953 | 0.19 | 1176
9651 | PURISIMA 1101Y44 | 182971101 | PURISIMA 1101 | Y44 | FALSE | 18687.8674 | 16745.9311 | 10.4077 | 45 | 6.0111e-05 | 2770 | 1213.3424 | 724 | 0.073295 | 3.2983 | 954 | 0.1 | 1484
1008 | TEMPLETON 2113A70 | 183052113 | TEMPLETON 2113 | A70 | FALSE | 107377.7331 | 39764.0285 | 24.7135 | 659 | 6.9565e-05 | 2486 | 1197.409 | 731 | 0.073157 | 48.2106 | 955 | 3.57 | 542
3782 | AUBERRY 1101R322 | 254151101 | AUBERRY 1101 | R322 | FALSE | 12336.4699 | 12336.4699 | 7.6672 | 44 | 3.5123e-05 | 3349 | 2118.7775 | 422 | 0.073065 | 3.2149 | 956 | 0.06 | 1886
700 | MERCED FALLS 11029460 | 252811102 | MERCED FALLS 1102 | 9460 | FALSE | 18052.5322 | 17926.192 | 11.1412 | 91 | 8.3561e-05 | 2112 | 856.971 | 910 | 0.073014 | 6.6443 | 957 | 0.01 | 2611
1286 | CURTIS 170384944 | 163351703 | CURTIS 1703 | 84944 | FALSE | 93674.3078 | 93674.3078 | 58.219 | 439 | 7.7782e-05 | 2268 | 921.9165 | 873 | 0.072725 | 31.9262 | 958 |  | 2719
8476 | ALTO 1124810594 | 42031124 | ALTO 1124 | 810594 | TRUE | 1080.6364 | 899.4073 | 0.55899 | 6 | 0.0001145 | 1307 | 459.6008 | 1235 | 0.072684 | 0.4361 | 959 |  | 3228
1350 | PENRYN 1107CB | 152561107 | PENRYN 1107 | CB | FALSE | 25933.7558 | 8735.2446 | 5.429 | 200 | 0.00014636 | 784 | 521.6714 | 1181 | 0.072647 | 14.5295 | 960 | 0.55 | 869
10196 | SANTA YNEZ 1101980192 | 182721101 | SANTA YNEZ 1101 | 980192 | FALSE | 6178.6453 | 6178.6453 | 3.8401 | 19 | 3.4326e-05 | 3362 | 2382.3266 | 363 | 0.072592 | 1.3793 | 961 |  | 3513
4126 | VACAVILLE 1104CB | 63601104 | VACAVILLE 1104 | CB | TRUE | 4213.006 | 696.6837 | 0.43299 | 36 | 6.8096e-05 | 2534 | 412.1878 | 1283 | 0.07222 | 2.5999 | 962 | 0.06 | 1816
6142 | JOLON 1103CB | 182981103 | JOLON 1103 | CB | FALSE | 29664.4521 | 21174.1488 | 13.1598 | 91 | 0.00013717 | 905 | 720.7685 | 998 | 0.072102 | 6.5613 | 963 | 0.02 | 2565
4505 | LOW GAP 11014086 | 192411101 | LOW GAP 1101 | 4086 | FALSE | 18494.2051 | 18494.2051 | 11.4942 | 66 | 0.00012787 | 1052 | 634.8288 | 1073 | 0.072098 | 4.7585 | 964 | 0.12 | 1393
5220 | COTATI 1103132 | 42271103 | COTATI 1103 | 132 | FALSE | 40702.0776 | 40702.0776 | 25.2965 | 184 | 7.3728e-05 | 2369 | 1030.4196 | 808 | 0.071994 | 13.2468 | 965 | 4.02 | 529
2886 | VOLTA 11011596 | 102541101 | VOLTA 1101 | 1596 | FALSE | 35104.5465 | 35104.5465 | 21.8176 | 132 | 6.0424e-05 | 2763 | 1180.3203 | 741 | 0.071922 | 9.4937 | 966 | 0.01 | 2583
7748 | PEORIA 170413490 | 163781704 | PEORIA 1704 | 13490 | FALSE | 8773.504 | 6875.4256 | 4.2731 | 49 | 0.00015838 | 660 | 538.4381 | 1161 | 0.071878 | 3.522 | 967 | 0.05 | 1975
1885 | OREGON TRAIL 110249144 | 103521102 | OREGON TRAIL 1102 | 49144 | FALSE | 34128.6869 | 29574.1503 | 18.3805 | 169 | 0.00016343 | 606 | 803.7485 | 937 | 0.071512 | 12.0855 | 968 | 0.08 | 1646
3676 | COTTONWOOD 1101CB | 102931101 | COTTONWOOD 1101 | CB | TRUE | 26588.5909 | 184.0196 | 0.11437 | 188 | 9.7905e-05 | 1694 | 539.3221 | 1159 | 0.0715 | 13.442 | 969 | 0.02 | 2564
7714 | FROGTOWN 17027134 | 163451702 | FROGTOWN 1702 | 7134 | FALSE | 37777.9012 | 32518.1243 | 20.2101 | 172 | 9.5256e-05 | 1759 | 696.6949 | 1025 | 0.071297 | 12.2631 | 970 | 0.09 | 1546
4319 | MESA 11016111 | 182821101 | MESA 1101 | 6111 | FALSE | 41513.5486 | 39023.9015 | 24.2535 | 202 | 4.9757e-05 | 3042 | 1337.456 | 665 | 0.071153 | 14.3729 | 971 | 9.09 | 413
5571 | CLEAR LAKE 1101740076 | 42141101 | CLEAR LAKE 1101 | 740076 | TRUE | 14283.4902 | 632.3767 | 0.39302 | 106 | 0.00010531 | 1512 | 793.8066 | 947 | 0.071071 | 7.5335 | 972 |  | 2963
9268 | OLETA 1102799924 | 163541102 | OLETA 1102 | 799924 | TRUE | 621.6151 | 621.6151 | 0.38634 | 4 | 0.00011059 | 1397 | 1327.4203 | 669 | 0.070818 | 0.28327 | 973 |  | 3334
1141 | BELL 1109724884 | 152701109 | BELL 1109 | 724884 | FALSE | 22726.0215 | 22589.092 | 14.0392 | 167 | 0.00017254 | 546 | 443.793 | 1254 | 0.070791 | 11.822 | 974 |  | 2712
9406 | EDENVALE 2107469810 | 82952107 | EDENVALE 2107 | 469810 | FALSE | 9545.8932 | 3464.1714 | 2.153 | 14 | 8.3298e-05 | 2125 | 778.0104 | 955 | 0.070672 | 0.98941 | 975 |  | 3354
2788 | WYANDOTTE 1110980944 | 102911110 | WYANDOTTE 1110 | 980944 | FALSE | 26900.3072 | 16783.2453 | 10.4309 | 198 | 0.00019807 | 404 | 366.1605 | 1345 | 0.070566 | 13.9721 | 976 |  | 2798
3339 | JESSUP 110276068 | 103441102 | JESSUP 1102 | 76068 | FALSE | 31093.7701 | 27642.9269 | 17.1802 | 232 | 7.7128e-05 | 2284 | 1055.6938 | 794 | 0.070348 | 16.3207 | 977 | 6.25 | 470
6626 | CLAY 1101CB | 163341101 | CLAY 1101 | CB | TRUE | 4411.9174 | 914.1112 | 0.56812 | 33 | 8.0383e-05 | 2194 | 401.4638 | 1294 | 0.070136 | 2.3145 | 978 |  | 3048
9158 | COVELO 1101306476 | 43061101 | COVELO 1101 | 306476 | FALSE | 16292.4669 | 3106.377 | 1.9306 | 49 | 0.00010648 | 1486 | 598.7531 | 1101 | 0.069853 | 3.4228 | 979 |  | 3316
5752 | MONTICELLO 110165454 | 43051101 | MONTICELLO 1101 | 65454 | FALSE | 3114.2101 | 2176.3172 | 1.3526 | 23 | 6.0844e-05 | 2754 | 1192.0123 | 737 | 0.069594 | 1.6007 | 980 | 2.09 | 622
2727 | OREGON TRAIL 11031500 | 103521103 | OREGON TRAIL 1103 | 1500 | FALSE | 41880.4686 | 41880.4686 | 26.0289 | 261 | 0.00012847 | 1038 | 750.2992 | 975 | 0.069495 | 18.1383 | 981 | 0.21 | 1153
10741 | HALF MOON BAY 11038920 | 24101103 | HALF MOON BAY 1103 | 8920 | TRUE | 158.1242 | 158.1242 | 0.098275 | 2 | 0.00017718 | 518 | 499.4912 | 1200 | 0.069477 | 0.13895 | 982 | 0.19 | 1196
2684 | BEAR VALLEY 210110000 | 252192101 | BEAR VALLEY 2101 | 10000 | FALSE | 53656.1229 | 47097.1904 | 29.2711 | 230 | 6.3422e-05 | 2664 | 1330.8242 | 668 | 0.069198 | 15.9156 | 983 | 0.02 | 2464
1190 | OCEANO 1104V36 | 182601104 | OCEANO 1104 | V36 | FALSE | 21377.0625 | 18028.895 | 11.205 | 150 | 6.1929e-05 | 2723 | 1033.145 | 804 | 0.069118 | 10.3677 | 984 | 6.65 | 464
9260 | DIAMOND SPRINGS 110777086 | 152261107 | DIAMOND SPRINGS 1107 | 77086 | FALSE | 6051.2822 | 4371.5846 | 2.717 | 47 | 0.00020917 | 363 | 405.3593 | 1291 | 0.068998 | 3.2429 | 985 |  | 3331
87 | CORNING 110185152 | 103331101 | CORNING 1101 | 85152 | FALSE | 37332.1384 | 37332.1384 | 23.2021 | 279 | 4.413e-05 | 3188 | 1657.8134 | 539 | 0.068983 | 19.2463 | 986 | 8.2 | 433
2893 | UKIAH 1114544 | 42771114 | UKIAH 1114 | 544 | TRUE | 16214.8056 | 786.2676 | 0.48867 | 98 | 8.9779e-05 | 1918 | 761.7873 | 963 | 0.068781 | 6.7406 | 987 |  | 2803
69 | BROWNS VALLEY 110197188 | 152921101 | BROWNS VALLEY 1101 | 97188 | FALSE | 10919.7899 | 10919.7899 | 6.7867 | 71 | 0.00011852 | 1217 | 794.0069 | 946 | 0.068613 | 4.8715 | 988 | 0.06 | 1870
1342 | AUBERRY 1101R2838 | 254151101 | AUBERRY 1101 | R2838 | FALSE | 32896.73 | 32896.73 | 20.4455 | 210 | 3.7309e-05 | 3308 | 2069.6718 | 438 | 0.068544 | 14.3942 | 989 | 0.21 | 1136
9647 | GARCIA 0401CB | 43040401 | GARCIA 0401 | CB | TRUE | 46.711 | 46.711 | 0.029031 | 1 | 0.00015165 | 723 | 451.5011 | 1247 | 0.068469 | 0.068469 | 990 | 4.71 | 509
2407 | FROGTOWN 1702835115 | 163451702 | FROGTOWN 1702 | 835115 | FALSE | 29192.1081 | 29192.1081 | 18.143 | 191 | 7.8182e-05 | 2253 | 868.4883 | 902 | 0.068398 | 13.0639 | 991 |  | 2775
3939 | ZACA 1101Y70 | 182681101 | ZACA 1101 | Y70 | FALSE | 13947.1347 | 10839.1211 | 6.7366 | 61 | 5.1111e-05 | 3011 | 1300.1446 | 683 | 0.068291 | 4.1658 | 992 | 0.02 | 2489
3966 | SAN BENITO 2101295566 | 182742101 | SAN BENITO 2101 | 295566 | TRUE | 3409.6411 | 751.534 | 0.46708 | 18 | 5.22e-05 | 2987 | 1215.0443 | 723 | 0.068263 | 1.2287 | 993 |  | 2864
1800 | BANGOR 11011804 | 103191101 | BANGOR 1101 | 1804 | FALSE | 69024.1301 | 69024.1301 | 42.8988 | 394 | 0.00011734 | 1239 | 495.1119 | 1205 | 0.068197 | 26.8697 | 994 | 0.15 | 1295
1078 | BIG MEADOWS 21012260 | 102812101 | BIG MEADOWS 2101 | 2260 | FALSE | 36303.3353 | 25414.2279 | 15.795 | 185 | 7.1484e-05 | 2433 | 1004.259 | 833 | 0.067786 | 12.5404 | 995 | 0.08 | 1667
8083 | ANDERSON 1101583708 | 103261101 | ANDERSON 1101 | 583708 | FALSE | 1263.0794 | 1011.3641 | 0.62857 | 11 | 9.3798e-05 | 1800 | 952.2243 | 858 | 0.067762 | 0.74538 | 996 |  | 3189
6638 | SAN RAMON 2117CB | 14232117 | SAN RAMON 2117 | CB | FALSE | 2698.3212 | 1098.894 | 0.68297 | 23 | 9.8521e-05 | 1678 | 430.579 | 1258 | 0.067722 | 1.5576 | 997 | 0.47 | 908
7538 | CABRILLO 1103Y46 | 183101103 | CABRILLO 1103 | Y46 | FALSE | 76660.9296 | 50653.8838 | 31.4816 | 277 | 4.2068e-05 | 3223 | 1429.3656 | 626 | 0.067522 | 18.7037 | 998 | 0.13 | 1364
4175 | MARTELL 1101CB | 163011101 | MARTELL 1101 | CB | FALSE | 21488.1146 | 9459.2642 | 5.879 | 171 | 0.00014623 | 785 | 382.8028 | 1314 | 0.067405 | 11.5263 | 999 | 0.05 | 1971
9619 | PETALUMA C 1108456397 | 42631108 | PETALUMA C 1108 | 456397 | FALSE | 2239.0721 | 2239.0721 | 1.3916 | 19 | 9.783e-05 | 1696 | 785.4652 | 954 | 0.067328 | 1.2792 | 1000 |  | 3391
3701 | FRENCH GULCH 1101CB | 103381101 | FRENCH GULCH 1101 | CB | FALSE | 3697.5337 | 3697.5337 | 2.298 | 32 | 0.00012582 | 1082 | 762.0604 | 962 | 0.067293 | 2.1534 | 1001 | 0.05 | 1960
4093 | RED BLUFF 1105146070 | 103541105 | RED BLUFF 1105 | 146070 | FALSE | 22680.3921 | 20479.5896 | 12.7281 | 167 | 6.6917e-05 | 2560 | 1071.9697 | 786 | 0.067012 | 11.191 | 1002 |  | 2871
1562 | LAYTONVILLE 110264908 | 42681102 | LAYTONVILLE 1102 | 64908 | FALSE | 10254.7707 | 6238.0239 | 3.877 | 84 | 0.00035803 | 84 | 246.1325 | 1550 | 0.066995 | 5.6276 | 1003 | 0.84 | 767
7452 | SAN RAMON 210853732 | 14232108 | SAN RAMON 2108 | 53732 | FALSE | 12542.8 | 12542.8 | 7.7954 | 77 | 9.701e-05 | 1714 | 766.0355 | 959 | 0.066862 | 5.1484 | 1004 | 17.55 | 332
509 | CALISTOGA 110143924 | 42711101 | CALISTOGA 1101 | 43924 | FALSE | 15096.7446 | 12523.7999 | 7.7836 | 107 | 0.00015399 | 708 | 446.2971 | 1252 | 0.066852 | 7.1532 | 1005 | 91.99 | 30
2808 | PASO ROBLES 1104P02 | 182611104 | PASO ROBLES 1104 | P02 | TRUE | 11656.6661 | 515.0322 | 0.32009 | 93 | 5.0919e-05 | 3016 | 803.9256 | 936 | 0.06682 | 6.2143 | 1006 | 0.32 | 993
6977 | CLOVERDALE 1102172096 | 42821102 | CLOVERDALE 1102 | 172096 | TRUE | 1240.5827 | 425.5098 | 0.26446 | 12 | 0.00013435 | 939 | 425.6324 | 1267 | 0.06657 | 0.79884 | 1007 |  | 3077
6400 | PHILO 1102CB | 42601102 | PHILO 1102 | CB | FALSE | 20191.5411 | 12387.7147 | 7.699 | 131 | 0.00018717 | 460 | 356.2256 | 1362 | 0.06648 | 8.7089 | 1008 | 0.06 | 1904
1390 | CURTIS 170539256 | 163351705 | CURTIS 1705 | 39256 | FALSE | 42581.0612 | 42581.0612 | 26.4643 | 287 | 0.00012638 | 1077 | 694.1209 | 1026 | 0.066296 | 19.0271 | 1009 | 0.26 | 1068
9080 | SUMMIT 110249484 | 152591102 | SUMMIT 1102 | 49484 | FALSE | 4257.4421 | 4257.4421 | 2.646 | 27 | 0.000124 | 1121 | 880.5018 | 890 | 0.06627 | 1.7893 | 1010 | 0.02 | 2543
493 | BRUNSWICK 11102664 | 152481110 | BRUNSWICK 1110 | 2664 | FALSE | 17552.7674 | 12910.8902 | 8.0242 | 132 | 0.00019724 | 409 | 283.8161 | 1468 | 0.066185 | 8.7364 | 1011 | 7.85 | 440
6828 | SILVERADO 210298998 | 43432102 | SILVERADO 2102 | 98998 | TRUE | 20001.4994 | 118.1019 | 0.073401 | 136 | 8.5457e-05 | 2044 | 370.2201 | 1337 | 0.066014 | 8.9779 | 1012 | 0.02 | 2466
828 | ATASCADERO 1103A18 | 182541103 | ATASCADERO 1103 | A18 | FALSE | 29115.6622 | 14189.3642 | 8.8187 | 188 | 6.7022e-05 | 2556 | 932.8875 | 868 | 0.065994 | 12.4068 | 1013 | 1.58 | 663
7881 | CALISTOGA 1102141073 | 42711102 | CALISTOGA 1102 | 141073 | FALSE | 3422.9373 | 1996.4523 | 1.2408 | 27 | 0.00018845 | 450 | 208.8541 | 1621 | 0.065722 | 1.7745 | 1014 |  | 3174
5591 | CURTIS 17029220 | 163351702 | CURTIS 1702 | 9220 | FALSE | 18356.5403 | 17704.0281 | 11.0031 | 123 | 0.00012861 | 1036 | 658.7055 | 1055 | 0.065661 | 8.0763 | 1015 | 0.19 | 1191
1187 | PENRYN 11051342 | 152561105 | PENRYN 1105 | 1342 | FALSE | 62297.5033 | 33351.1972 | 20.7279 | 440 | 0.00011151 | 1385 | 593.3765 | 1111 | 0.065366 | 28.7609 | 1016 | 1.74 | 645
8143 | CLAYTON 2215W531R | 12022215 | CLAYTON 2215 | W531R | FALSE | 17380.2917 | 10443.673 | 6.4908 | 100 | 6.9698e-05 | 2483 | 735.723 | 988 | 0.065356 | 6.5356 | 1017 | 0.07 | 1731
2291 | SHINGLE SPRINGS 210913322 | 153652109 | SHINGLE SPRINGS 2109 | 13322 | FALSE | 66617.6825 | 66617.6825 | 41.4032 | 490 | 6.243e-05 | 2708 | 1047.9717 | 798 | 0.065331 | 32.0124 | 1018 | 0.31 | 1005
2286 | BEAR VALLEY 210521160 | 252192105 | BEAR VALLEY 2105 | 21160 | FALSE | 38269.4773 | 38269.4773 | 23.7846 | 194 | 4.477e-05 | 3167 | 1259.0438 | 695 | 0.065187 | 12.6462 | 1019 | 0.07 | 1757
9841 | MESA 1103126697 | 182821103 | MESA 1103 | 126697 | FALSE | 1766.1223 | 1641.863 | 1.0204 | 10 | 6.1082e-05 | 2745 | 1011.3761 | 827 | 0.065062 | 0.65062 | 1020 |  | 3433
9670 | FRENCH GULCH 1102CB | 103381102 | FRENCH GULCH 1102 | CB | FALSE | 2729.0129 | 2729.0129 | 1.6961 | 12 | 0.00018833 | 451 | 298.7993 | 1449 | 0.06474 | 0.77689 | 1021 | 0.03 | 2234
2589 | FORT ROSS 1121124 | 42851121 | FORT ROSS 1121 | 124 | FALSE | 29762.4384 | 29762.4384 | 18.4975 | 99 | 0.00011564 | 1282 | 546.7406 | 1151 | 0.064597 | 6.3951 | 1022 | 4.64 | 511
2518 | OCEANO 1104Q08 | 182601104 | OCEANO 1104 | Q08 | FALSE | 19981.628 | 19981.628 | 12.4187 | 148 | 5.6432e-05 | 2876 | 1236.4827 | 708 | 0.064559 | 9.5547 | 1023 | 4.37 | 521
10030 | MC ARTHUR 1102542920 | 103491102 | MC ARTHUR 1102 | 542920 | FALSE | 2484.216 | 2034.8319 | 1.2647 | 10 | 2.943e-05 | 3433 | 2350.3357 | 372 | 0.064427 | 0.64427 | 1024 |  | 3478
4185 | PASO ROBLES 1104R12 | 182611104 | PASO ROBLES 1104 | R12 | FALSE | 64632.5351 | 52796.2686 | 32.8131 | 278 | 5.1483e-05 | 3005 | 1212.0624 | 725 | 0.064341 | 17.8868 | 1025 | 0.1 | 1470
7956 | JESSUP 11011993 | 103441101 | JESSUP 1101 | 1993 | FALSE | 4771.9686 | 4470.3512 | 2.7783 | 39 | 6.0989e-05 | 2747 | 818.0593 | 926 | 0.064212 | 2.5043 | 1026 | 3.17 | 558
10640 | CALISTOGA 110266730 | 42711102 | CALISTOGA 1102 | 66730 | FALSE | 1703.3079 | 1703.3079 | 1.0586 | 6 | 0.00011857 | 1215 | 919.8595 | 875 | 0.064035 | 0.38421 | 1027 | 0.49 | 897
9262 | LAKEVILLE 110287432 | 43371102 | LAKEVILLE 1102 | 87432 | FALSE | 21925.1583 | 15708.5355 | 9.7629 | 81 | 7.1409e-05 | 2436 | 994.1805 | 837 | 0.063901 | 5.176 | 1028 | 0.09 | 1521
6678 | MIDDLETOWN 11011325 | 43141101 | MIDDLETOWN 1101 | 1325 | FALSE | 13829.5499 | 13829.5499 | 8.5951 | 80 | 0.00012793 | 1047 | 449.2232 | 1249 | 0.063613 | 5.0891 | 1029 | 12.01 | 378
5737 | UKIAH 11151216 | 42771115 | UKIAH 1115 | 1216 | FALSE | 30877.2329 | 21628.5531 | 13.4422 | 182 | 0.00012873 | 1035 | 525.6183 | 1178 | 0.063522 | 11.561 | 1030 | 0.07 | 1733
1518 | DIAMOND SPRINGS 110518935 | 152261105 | DIAMOND SPRINGS 1105 | 18935 | FALSE | 10773.8274 | 10773.8274 | 6.696 | 76 | 0.00011327 | 1337 | 910.0927 | 882 | 0.063224 | 4.805 | 1031 | 8.29 | 432
8962 | TEMPLETON 2110N30 | 183052110 | TEMPLETON 2110 | N30 | FALSE | 32768.3238 | 32768.3238 | 20.3656 | 120 | 6.3151e-05 | 2674 | 927.1943 | 870 | 0.063152 | 7.5782 | 1032 | 0.09 | 1530
5800 | CLARK ROAD 11022070 | 103091102 | CLARK ROAD 1102 | 2070 | FALSE | 15059.4591 | 14786.6222 | 9.1899 | 72 | 0.00014395 | 814 | 498.0458 | 1203 | 0.063106 | 4.5436 | 1033 | 0.07 | 1760
1728 | TEMPLETON 2112116402 | 183052112 | TEMPLETON 2112 | 116402 | FALSE | 11255.0357 | 3810.8828 | 2.3685 | 64 | 5.7437e-05 | 2850 | 1320.2856 | 674 | 0.062979 | 4.0307 | 1034 |  | 2740
727 | APPLE HILL 2102186912 | 153662102 | APPLE HILL 2102 | 186912 | FALSE | 97116.525 | 94273.5723 | 58.5914 | 606 | 9.5424e-05 | 1747 | 711.7437 | 1013 | 0.06292 | 38.1293 | 1035 | 0.18 | 1223
7181 | BEAR VALLEY 21054170 | 252192105 | BEAR VALLEY 2105 | 4170 | FALSE | 15319.6405 | 15319.6405 | 9.5212 | 45 | 4.2938e-05 | 3210 | 1356.0496 | 661 | 0.062779 | 2.8251 | 1036 | 0.03 | 2358
8856 | GARBERVILLE 11028189 | 192221102 | GARBERVILLE 1102 | 8189 | FALSE | 1685.4401 | 1685.4401 | 1.0475 | 11 | 0.00035454 | 86 | 166.396 | 1732 | 0.062553 | 0.68809 | 1037 | 0.02 | 2537
1917 | PANORAMA 1101CB | 103461101 | PANORAMA 1101 | CB | FALSE | 27174.1674 | 1828.844 | 1.1366 | 175 | 0.0001054 | 1510 | 467.1503 | 1226 | 0.062374 | 10.9155 | 1038 | 0.02 | 2425
9789 | TASSAJARA 2106203380 | 14662106 | TASSAJARA 2106 | 203380 | TRUE | 3178.2991 | 809.5956 | 0.50317 | 26 | 0.00010239 | 1592 | 687.7534 | 1032 | 0.062335 | 1.6207 | 1039 |  | 3423
8449 | VACAVILLE 111112342 | 63601111 | VACAVILLE 1111 | 12342 | TRUE | 1750.136 | 352.0949 | 0.21883 | 16 | 0.00013409 | 942 | 663.7688 | 1049 | 0.062293 | 0.99668 | 1040 | 0.32 | 996
3572 | OLETA 110113478 | 163541101 | OLETA 1101 | 13478 | FALSE | 24836.1056 | 19846.6513 | 12.3348 | 169 | 0.0001203 | 1180 | 594.448 | 1107 | 0.062159 | 10.5049 | 1041 | 0.09 | 1570
1028 | LOW GAP 11012094 | 192411101 | LOW GAP 1101 | 2094 | FALSE | 27452.3558 | 25248.6295 | 15.6921 | 139 | 0.00021404 | 343 | 379.7853 | 1321 | 0.062103 | 8.6323 | 1042 | 3.85 | 533
3105 | NOTRE DAME 11042028 | 102041104 | NOTRE DAME 1104 | 2028 | FALSE | 17437.7183 | 17437.7183 | 10.8376 | 86 | 0.00015423 | 702 | 243.285 | 1559 | 0.062015 | 5.3333 | 1043 | 0.41 | 939
2667 | FROGTOWN 170212282 | 163451702 | FROGTOWN 1702 | 12282 | FALSE | 58482.1143 | 58482.1143 | 36.3469 | 261 | 0.00011986 | 1190 | 718.4403 | 1004 | 0.061928 | 16.1631 | 1044 | 0.18 | 1206
7606 | NOTRE DAME 11042537 | 102041104 | NOTRE DAME 1104 | 2537 | FALSE | 8030.1143 | 8030.1143 | 4.9907 | 37 | 9.2031e-05 | 1844 | 618.6971 | 1083 | 0.061762 | 2.2852 | 1045 | 0.2 | 1156
2093 | ATASCADERO 1103A46 | 182541103 | ATASCADERO 1103 | A46 | TRUE | 13904.7944 | 633.1098 | 0.39348 | 94 | 8.1941e-05 | 2157 | 550.2411 | 1144 | 0.06175 | 5.8045 | 1046 | 0.02 | 2447
7485 | SHINGLE SPRINGS 210551738 | 153652105 | SHINGLE SPRINGS 2105 | 51738 | TRUE | 1844.3225 | 26.6806 | 0.016582 | 19 | 0.00013923 | 882 | 441.8941 | 1255 | 0.061564 | 1.1697 | 1047 | 17.24 | 335
284 | PERRY 1101V78 | 183071101 | PERRY 1101 | V78 | FALSE | 47471.3302 | 47471.3302 | 29.5036 | 164 | 6.8753e-05 | 2516 | 918.2768 | 876 | 0.061453 | 10.0783 | 1048 | 0.19 | 1179
10468 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | TRUE | 63.3636 | 63.3636 | 0.039381 | 1 | 0.00010321 | 1565 | 595.1616 | 1105 | 0.061428 | 0.061428 | 1049 | 8.51 | 425
8597 | ORO FINO 1102127563 | 103031102 | ORO FINO 1102 | 127563 | FALSE | 11105.9314 | 11105.9314 | 6.9024 | 63 | 7.2173e-05 | 2413 | 803.5682 | 938 | 0.061336 | 3.8642 | 1050 | 23.56 | 283
6425 | MADISON 2101351038 | 63172101 | MADISON 2101 | 351038 | FALSE | 22506.9662 | 2661.6552 | 1.6542 | 130 | 7.0209e-05 | 2462 | 1068.3127 | 787 | 0.061316 | 7.971 | 1051 |  | 3029
5524 | JESSUP 11011496 | 103441101 | JESSUP 1101 | 1496 | FALSE | 26084.969 | 23526.9728 | 14.6221 | 201 | 7.6403e-05 | 2297 | 864.7228 | 905 | 0.06121 | 12.3032 | 1052 | 0.06 | 1790
10127 | SPAULDING 1101CB | 152251101 | SPAULDING 1101 | CB | TRUE | 56.7484 | 56.7484 | 0.035269 | 1 | 0.0001609 | 632 | 380.3958 | 1320 | 0.061207 | 0.061207 | 1053 |  | 3497
4318 | HIGGINS 11102408 | 152691110 | HIGGINS 1110 | 2408 | FALSE | 18614.5661 | 18614.5661 | 11.569 | 124 | 0.000106 | 1493 | 623.6203 | 1079 | 0.060864 | 7.5471 | 1054 | 0.34 | 981
7906 | PIT NO 7 1101CB | 103501101 | PIT NO 7 1101 | CB | FALSE | 4357.8457 | 4357.8457 | 2.7084 | 3 | 0.00010885 | 1430 | 808.7175 | 931 | 0.060819 | 0.18246 | 1055 | 0.02 | 2472
7035 | SYCAMORE CREEK 1111CB | 102971111 | SYCAMORE CREEK 1111 | CB | TRUE | 11952.1608 | 777.7423 | 0.48337 | 85 | 0.00011707 | 1245 | 452.6669 | 1244 | 0.060715 | 5.1608 | 1056 | 0.06 | 1775
4688 | UPPER LAKE 1101452 | 42871101 | UPPER LAKE 1101 | 452 | FALSE | 31530.7427 | 8129.076 | 5.0523 | 207 | 0.00010226 | 1598 | 743.369 | 981 | 0.060708 | 12.5666 | 1057 | 0.67 | 816
7853 | CLOVERDALE 1102670 | 42821102 | CLOVERDALE 1102 | 670 | TRUE | 4937.5444 | 587.1475 | 0.36491 | 43 | 0.00012733 | 1058 | 393.8186 | 1302 | 0.06056 | 2.6041 | 1058 | 0.03 | 2292
9980 | BRIDGEVILLE 1101CB | 192461101 | BRIDGEVILLE 1101 | CB | FALSE | 13703.2012 | 13703.2012 | 8.5166 | 51 | 0.00018978 | 443 | 315.2875 | 1424 | 0.060495 | 3.0852 | 1059 | 2.08 | 624
3075 | REDBUD 11022013 | 43191102 | REDBUD 1102 | 2013 | TRUE | 7412.4545 | 238.9679 | 0.14852 | 51 | 5.2169e-05 | 2988 | 888.4761 | 888 | 0.06048 | 3.0845 | 1060 | 0.44 | 923
377 | FROGTOWN 1702L5407 | 163451702 | FROGTOWN 1702 | L5407 | FALSE | 29410.8857 | 29410.8857 | 18.279 | 153 | 4.5895e-05 | 3142 | 1349.9596 | 663 | 0.060463 | 9.2508 | 1061 | 0.09 | 1522
599 | CURTIS 170356972 | 163351703 | CURTIS 1703 | 56972 | FALSE | 13791.0471 | 13791.0471 | 8.5712 | 57 | 0.00011753 | 1234 | 612.4545 | 1090 | 0.060186 | 3.4306 | 1062 | 0.04 | 2114
9546 | COTATI 1102CB | 42271102 | COTATI 1102 | CB | FALSE | 3229.2079 | 2904.3184 | 1.805 | 19 | 0.00016629 | 580 | 366.1668 | 1344 | 0.05984 | 1.137 | 1063 | 0.04 | 2199
9754 | CALPELLA 1102708161 | 43411102 | CALPELLA 1102 | 708161 | FALSE | 1824.6356 | 1615.0007 | 1.0037 | 12 | 0.00012306 | 1133 | 461.5277 | 1234 | 0.059606 | 0.71527 | 1064 |  | 3411
7941 | FRUITLAND 11426064 | 192311142 | FRUITLAND 1142 | 6064 | FALSE | 13322.7276 | 10776.9352 | 6.6979 | 66 | 0.00027944 | 157 | 244.0042 | 1557 | 0.059515 | 3.928 | 1065 | 1.74 | 646
1172 | CORRAL 110336680 | 162991103 | CORRAL 1103 | 36680 | FALSE | 32219.8242 | 15055.3944 | 9.357 | 265 | 8.2363e-05 | 2143 | 715.9031 | 1008 | 0.059472 | 15.7601 | 1066 | 2.94 | 572
7127 | SONOMA 1107844168 | 42721107 | SONOMA 1107 | 844168 | FALSE | 18710.7045 | 7309.0201 | 4.5426 | 100 | 5.7956e-05 | 2836 | 877.0353 | 894 | 0.059437 | 5.9437 | 1067 |  | 3097
2372 | GRASS VALLEY 11032110 | 152031103 | GRASS VALLEY 1103 | 2110 | FALSE | 32283.1191 | 31798.2221 | 19.7627 | 224 | 0.00013772 | 899 | 464.9832 | 1230 | 0.059423 | 13.3106 | 1068 | 0.21 | 1147
2173 | PUEBLO 1105696 | 43291105 | PUEBLO 1105 | 696 | FALSE | 11659.1184 | 6037.9333 | 3.7526 | 79 | 7.4535e-05 | 2343 | 617.4166 | 1085 | 0.059025 | 4.663 | 1069 | 0.32 | 991
2604 | JESSUP 11031540 | 103441103 | JESSUP 1103 | 1540 | TRUE | 20738.5879 | 256.3874 | 0.15935 | 157 | 0.00010932 | 1426 | 527.982 | 1175 | 0.058865 | 9.2418 | 1070 | 0.04 | 2210
8024 | PENRYN 11072708 | 152561107 | PENRYN 1107 | 2708 | FALSE | 17128.5396 | 15094.9992 | 9.3816 | 124 | 0.00011703 | 1249 | 634.212 | 1074 | 0.058775 | 7.2881 | 1071 | 0.09 | 1533
660 | GABILAN 1101460414 | 182331101 | GABILAN 1101 | 460414 | FALSE | 10774.9077 | 8655.1604 | 5.3792 | 38 | 8.546e-05 | 2043 | 785.6181 | 953 | 0.058719 | 2.2313 | 1072 |  | 2688
2838 | MENDOCINO 110148750 | 42951101 | MENDOCINO 1101 | 48750 | FALSE | 28839.2375 | 28839.2375 | 17.9237 | 165 | 9.931e-05 | 1660 | 705.0697 | 1020 | 0.058621 | 9.6724 | 1073 | 19.06 | 315
5642 | ALHAMBRA 110582622 | 14101105 | ALHAMBRA 1105 | 82622 | FALSE | 41703.3816 | 41703.3816 | 25.9188 | 254 | 8.8106e-05 | 1980 | 753.4327 | 972 | 0.058508 | 14.8609 | 1074 | 0.2 | 1166
5965 | JOLON 1102CB | 182981102 | JOLON 1102 | CB | FALSE | 38608.5003 | 37939.8486 | 23.5798 | 181 | 6.1591e-05 | 2729 | 1004.6328 | 832 | 0.058399 | 10.5701 | 1075 | 0.03 | 2280
5646 | SANTA YNEZ 1104512912 | 182721104 | SANTA YNEZ 1104 | 512912 | FALSE | 3140.8885 | 1435.1217 | 0.89193 | 23 | 6.2939e-05 | 2682 | 742.0792 | 982 | 0.058383 | 1.3428 | 1076 |  | 2970
1584 | COLUMBIA HILL 1101CB | 152471101 | COLUMBIA HILL 1101 | CB | FALSE | 63324.3345 | 63324.3345 | 39.3563 | 375 | 0.00014192 | 841 | 477.8627 | 1217 | 0.058367 | 21.8875 | 1077 | 0.76 | 785
8255 | CRESCENT MILLS 21012562 | 103132101 | CRESCENT MILLS 2101 | 2562 | FALSE | 55111.7044 | 31122.7322 | 19.3429 | 222 | 5.835e-05 | 2824 | 1193.0263 | 734 | 0.057915 | 12.8572 | 1078 | 0.05 | 1950
2533 | MOLINO 1101338 | 42571101 | MOLINO 1101 | 338 | FALSE | 23338.4107 | 12496.8829 | 7.7669 | 176 | 0.00010195 | 1604 | 593.3845 | 1110 | 0.05791 | 10.1921 | 1079 | 7.05 | 454
9899 | LLAGAS 21014523 | 83182101 | LLAGAS 2101 | 4523 | FALSE | 4420.7892 | 1471.0588 | 0.91427 | 28 | 9.5345e-05 | 1750 | 593.4447 | 1109 | 0.057806 | 1.6186 | 1080 |  | 3449
10017 | PASO ROBLES 1107289947 | 182611107 | PASO ROBLES 1107 | 289947 | TRUE | 3212.1673 | 447.6357 | 0.27821 | 21 | 8.5184e-05 | 2054 | 855.7073 | 911 | 0.057658 | 1.2108 | 1081 |  | 3472
451 | CALISTOGA 11011087 | 42711101 | CALISTOGA 1101 | 1087 | FALSE | 3157.1282 | 3157.1282 | 1.9622 | 22 | 0.00010484 | 1532 | 532.5062 | 1170 | 0.05764 | 1.2681 | 1082 | 7.64 | 443
90 | TYLER 1105816852 | 103571105 | TYLER 1105 | 816852 | FALSE | 70141.7466 | 20545.6876 | 12.7692 | 423 | 4.2631e-05 | 3214 | 1516.9463 | 587 | 0.057549 | 24.3431 | 1083 |  | 2655
67 | WOODACRE 1102CB | 43021102 | WOODACRE 1102 | CB | FALSE | 20142.5456 | 20085.8093 | 12.4834 | 141 | 0.00015851 | 658 | 382.2019 | 1316 | 0.057543 | 8.1136 | 1084 | 0.64 | 827
3103 | JOLON 11027070 | 182981102 | JOLON 1102 | 7070 | FALSE | 26486.1632 | 10307.0829 | 6.4059 | 132 | 5.0065e-05 | 3036 | 1217.7073 | 718 | 0.057494 | 7.5892 | 1085 | 0.03 | 2323
6894 | DESCHUTES 11011654 | 103351101 | DESCHUTES 1101 | 1654 | FALSE | 28221.2564 | 28221.2564 | 17.5396 | 168 | 8.908e-05 | 1943 | 662.2613 | 1051 | 0.057486 | 9.6576 | 1086 | 0.1 | 1492
1819 | ALTO 11243745 | 42031124 | ALTO 1124 | 3745 | FALSE | 7247.2343 | 7247.2343 | 4.5042 | 52 | 0.00018327 | 486 | 535.7815 | 1164 | 0.057415 | 2.9856 | 1087 | 1.01 | 730
1989 | ELECTRA 1101CB | 162161101 | ELECTRA 1101 | CB | FALSE | 50985.8349 | 50985.8349 | 31.6879 | 293 | 8.4764e-05 | 2072 | 750.5824 | 974 | 0.05741 | 16.8213 | 1088 | 0.1 | 1456
994 | BUTTE 1105751990 | 103081105 | BUTTE 1105 | 751990 | FALSE | 39452.6049 | 39436.6029 | 24.51 | 243 | 0.00013521 | 926 | 355.8632 | 1363 | 0.057382 | 13.9439 | 1089 |  | 2702
7429 | MOUNTAIN QUARRIES 210151584 | 152282101 | MOUNTAIN QUARRIES 2101 | 51584 | FALSE | 35041.5534 | 35041.5534 | 21.7785 | 224 | 7.7619e-05 | 2272 | 869.1368 | 901 | 0.057318 | 12.8393 | 1090 | 0.08 | 1655
7628 | WISE 11011404 | 152271101 | WISE 1101 | 1404 | FALSE | 5740.3584 | 2402.8891 | 1.4934 | 47 | 0.0001882 | 452 | 397.9556 | 1298 | 0.057199 | 2.6884 | 1091 | 0.03 | 2347
7386 | SAN RAMON 2108CB | 14232108 | SAN RAMON 2108 | CB | FALSE | 15329.2524 | 14012.7161 | 8.709 | 102 | 8.2611e-05 | 2139 | 748.7975 | 976 | 0.057183 | 5.8326 | 1092 | 18.75 | 318
9327 | CALISTOGA 110189150 | 42711101 | CALISTOGA 1101 | 89150 | FALSE | 15332.2939 | 15332.2939 | 9.5291 | 88 | 0.00012195 | 1149 | 582.7266 | 1121 | 0.057148 | 5.029 | 1093 | 0.48 | 905
4436 | SAN RAMON 2119CB | 14232119 | SAN RAMON 2119 | CB | FALSE | 2345.4974 | 1187.935 | 0.73831 | 21 | 7.6681e-05 | 2290 | 471.5803 | 1223 | 0.057097 | 1.199 | 1094 | 0.67 | 818
4471 | ELECTRA 11024756 | 162161102 | ELECTRA 1102 | 4756 | FALSE | 18962.2338 | 15139.4165 | 9.4092 | 95 | 0.000145 | 802 | 459.0245 | 1236 | 0.057032 | 5.4181 | 1095 | 0.05 | 1943
10516 | GARBERVILLE 11022124 | 192221102 | GARBERVILLE 1102 | 2124 | FALSE | 5026.2322 | 5026.2322 | 3.1238 | 6 | 0.00058653 | 20 | 170.3508 | 1714 | 0.057006 | 0.34203 | 1096 | 1.87 | 636
10428 | ANNAPOLIS 1101CB | 42861101 | ANNAPOLIS 1101 | CB | FALSE | 1058.7166 | 1058.7166 | 0.658 | 7 | 0.00022337 | 306 | 221.0499 | 1604 | 0.057005 | 0.39904 | 1097 | 0.06 | 1873
5436 | TEMPLETON 2110901690 | 183052110 | TEMPLETON 2110 | 901690 | FALSE | 63574.4496 | 60028.2631 | 37.3078 | 306 | 5.6692e-05 | 2868 | 1011.6278 | 825 | 0.056927 | 17.4196 | 1098 | 0.62 | 841
1208 | HOPLAND 1101CB | 42251101 | HOPLAND 1101 | CB | FALSE | 36057.8693 | 23579.7024 | 14.6549 | 190 | 0.00011058 | 1399 | 511.8263 | 1189 | 0.056867 | 10.8047 | 1099 | 0.02 | 2512
582 | SWIFT 2110853720 | 83392110 | SWIFT 2110 | 853720 | FALSE | 50276.8108 | 50276.8108 | 31.2472 | 140 | 6.2471e-05 | 2705 | 1012.617 | 823 | 0.056625 | 7.9275 | 1100 |  | 2684
6471 | SALMON CREEK 110137368 | 43161101 | SALMON CREEK 1101 | 37368 | FALSE | 9786.5772 | 9786.5772 | 6.0824 | 48 | 7.032e-05 | 2459 | 880.1307 | 892 | 0.056596 | 2.7166 | 1101 | 0.06 | 1898
7036 | WOODACRE 1101CB | 43021101 | WOODACRE 1101 | CB | FALSE | 4540.438 | 4454.6417 | 2.7686 | 35 | 0.00019479 | 417 | 248.765 | 1543 | 0.056508 | 1.9778 | 1102 | 0.3 | 1017
9354 | FRUITLAND 114137410 | 192311141 | FRUITLAND 1141 | 37410 | FALSE | 8875.6069 | 8413.1179 | 5.2288 | 42 | 0.00021128 | 354 | 348.1422 | 1375 | 0.056472 | 2.3718 | 1103 | 0.04 | 2173
8408 | GOLDTREE 1105CB | 182581105 | GOLDTREE 1105 | CB | FALSE | 15108.5071 | 11908.479 | 7.4012 | 76 | 7.9073e-05 | 2231 | 565.89 | 1132 | 0.056447 | 4.29 | 1104 | 0.45 | 919
1036 | FRUITLAND 1142CB | 192311142 | FRUITLAND 1142 | CB | FALSE | 24719.9919 | 16900.9683 | 10.504 | 116 | 0.0002473 | 224 | 245.6875 | 1552 | 0.056321 | 6.5332 | 1105 | 3.13 | 561
5437 | FITCH MOUNTAIN 1113775992 | 42751113 | FITCH MOUNTAIN 1113 | 775992 | FALSE | 5059.1291 | 3381.5311 | 2.1016 | 34 | 0.00012419 | 1115 | 374.1489 | 1330 | 0.056251 | 1.9125 | 1106 |  | 2954
8868 | SALMON CREEK 1101461703 | 43161101 | SALMON CREEK 1101 | 461703 | FALSE | 1414.65 | 1414.65 | 0.87921 | 8 | 7.7835e-05 | 2265 | 327.199 | 1402 | 0.05614 | 0.44912 | 1107 |  | 3274
1882 | SHINGLE SPRINGS 211051800 | 153652110 | SHINGLE SPRINGS 2110 | 51800 | FALSE | 15718.5986 | 14796.5287 | 9.1961 | 128 | 0.00016264 | 616 | 342.7814 | 1383 | 0.05603 | 7.1719 | 1108 | 3.81 | 534
3611 | SANTA MARIA 1108M80 | 182671108 | SANTA MARIA 1108 | M80 | FALSE | 93735.5013 | 93735.5013 | 58.257 | 397 | 4.5707e-05 | 3147 | 1161.6823 | 749 | 0.055911 | 22.1966 | 1109 | 0.42 | 930
6376 | MONTE RIO 11131991 | 42811113 | MONTE RIO 1113 | 1991 | FALSE | 11465.3295 | 11465.3295 | 7.1257 | 51 | 0.00016331 | 608 | 395.6046 | 1299 | 0.055786 | 2.8451 | 1110 | 56.35 | 99
1111 | PEORIA 17056697 | 163781705 | PEORIA 1705 | 6697 | FALSE | 6657.3541 | 6657.3541 | 4.1376 | 46 | 0.00010476 | 1534 | 551.7785 | 1143 | 0.055767 | 2.5653 | 1111 | 0.1 | 1462
3012 | RACETRACK 170311270 | 163761703 | RACETRACK 1703 | 11270 | FALSE | 20312.1456 | 20312.1456 | 12.6241 | 123 | 0.00012756 | 1056 | 499.3074 | 1201 | 0.055685 | 6.8493 | 1112 | 0.11 | 1443
722 | MONTE RIO 11125040 | 42811112 | MONTE RIO 1112 | 5040 | FALSE | 6507.5662 | 6507.5662 | 4.0445 | 46 | 0.0002406 | 244 | 218.6982 | 1609 | 0.055628 | 2.5589 | 1113 | 20.75 | 304
9716 | WINDSOR 1103171410 | 43501103 | WINDSOR 1103 | 171410 | FALSE | 7035.3214 | 2217.9639 | 1.3785 | 40 | 0.00011961 | 1192 | 536.0514 | 1163 | 0.055603 | 2.2241 | 1114 |  | 3405
15 | MENDOCINO 1101450 | 42951101 | MENDOCINO 1101 | 450 | FALSE | 30451.6805 | 9311.1997 | 5.7869 | 208 | 0.00012825 | 1043 | 484.352 | 1210 | 0.055438 | 11.531 | 1115 | 0.04 | 2211
6036 | PLACER 1103CB | 152461103 | PLACER 1103 | CB | FALSE | 14529.9116 | 11213.2305 | 6.9691 | 99 | 0.00015794 | 663 | 471.1517 | 1224 | 0.05535 | 5.4797 | 1116 | 0.06 | 1842
6178 | GEYSERVILLE 110135492 | 42891101 | GEYSERVILLE 1101 | 35492 | FALSE | 34847.1678 | 16074.976 | 9.9907 | 219 | 9.7259e-05 | 1708 | 426.1888 | 1265 | 0.055239 | 12.0973 | 1117 | 0.03 | 2257
6625 | WYANDOTTE 1107829470 | 102911107 | WYANDOTTE 1107 | 829470 | FALSE | 16595.0205 | 16595.0205 | 10.3139 | 93 | 0.00011788 | 1231 | 515.0682 | 1185 | 0.055226 | 5.136 | 1118 |  | 3047
7721 | CURTIS 17058110 | 163351705 | CURTIS 1705 | 8110 | FALSE | 13110.3306 | 13110.3306 | 8.1481 | 99 | 0.0001169 | 1252 | 657.3966 | 1057 | 0.055185 | 5.4634 | 1119 | 0.15 | 1283
8806 | CLAYTON 2212859443 | 12022212 | CLAYTON 2212 | 859443 | TRUE | 777.6394 | 475.2837 | 0.29539 | 5 | 4.9574e-05 | 3047 | 1445.6352 | 616 | 0.055167 | 0.27584 | 1120 |  | 3268
8792 | DUNLAP 1103CB | 254061103 | DUNLAP 1103 | CB | FALSE | 9029.352 | 9029.352 | 5.6118 | 38 | 3.4574e-05 | 3359 | 1447.0842 | 615 | 0.055113 | 2.0943 | 1121 | 0 | 2649
4534 | MERCED FALLS 110285002 | 252811102 | MERCED FALLS 1102 | 85002 | FALSE | 57093.5104 | 57093.5104 | 35.4838 | 394 | 7.6265e-05 | 2302 | 729.1639 | 992 | 0.055026 | 21.6802 | 1122 | 0.87 | 759
2247 | FROGTOWN 170113412 | 163451701 | FROGTOWN 1701 | 13412 | FALSE | 62439.7255 | 62439.7255 | 38.8065 | 333 | 0.00011911 | 1202 | 811.1905 | 930 | 0.055018 | 18.321 | 1123 | 0.87 | 756
3205 | COTATI 110361736 | 42271103 | COTATI 1103 | 61736 | FALSE | 26875.6469 | 19558.6498 | 12.1558 | 129 | 6.0018e-05 | 2773 | 726.4231 | 994 | 0.054986 | 7.0932 | 1124 | 0.05 | 1936
9516 | WILDWOOD 11011576 | 103611101 | WILDWOOD 1101 | 1576 | FALSE | 12974.577 | 12974.577 | 8.0638 | 51 | 7.9987e-05 | 2206 | 832.2405 | 921 | 0.054922 | 2.801 | 1125 | 0.07 | 1744
4729 | FITCH MOUNTAIN 1113352 | 42751113 | FITCH MOUNTAIN 1113 | 352 | FALSE | 19238.6019 | 9086.2434 | 5.6471 | 123 | 0.00014867 | 757 | 547.944 | 1149 | 0.054876 | 6.7498 | 1126 | 0.04 | 2196
6906 | IONE 1101CB | 163881101 | IONE 1101 | CB | FALSE | 22613.9915 | 2970.8687 | 1.8464 | 85 | 0.00012529 | 1093 | 646.6464 | 1068 | 0.054859 | 4.663 | 1127 | 0.02 | 2492
1910 | FROGTOWN 17016807 | 163451701 | FROGTOWN 1701 | 6807 | FALSE | 7894.5527 | 7894.5527 | 4.9065 | 49 | 0.00014837 | 759 | 586.6523 | 1116 | 0.054517 | 2.6713 | 1128 | 0.08 | 1650
1099 | HIGHLANDS 110275140 | 43361102 | HIGHLANDS 1102 | 75140 | FALSE | 32224.0105 | 13968.9875 | 8.6818 | 238 | 4.9487e-05 | 3050 | 824.0667 | 924 | 0.054483 | 12.967 | 1129 | 0.07 | 1713
9073 | CORRAL 1103831781 | 162991103 | CORRAL 1103 | 831781 | FALSE | 2564.8738 | 1186.1396 | 0.73719 | 19 | 7.3782e-05 | 2367 | 806.9369 | 932 | 0.054336 | 1.0324 | 1130 |  | 3304
1018 | APPLE HILL 21029722 | 153662102 | APPLE HILL 2102 | 9722 | FALSE | 62437.5165 | 62437.5165 | 38.8052 | 359 | 0.00010174 | 1610 | 529.226 | 1174 | 0.054308 | 19.4965 | 1131 | 0.52 | 890
882 | MORGAN HILL 2105XR152 | 83242105 | MORGAN HILL 2105 | XR152 | FALSE | 20635.5048 | 14045.9028 | 8.7296 | 156 | 8.0844e-05 | 2185 | 646.2065 | 1069 | 0.054285 | 8.4685 | 1132 | 0.08 | 1583
7464 | CLARKSVILLE 2106CB | 153612106 | CLARKSVILLE 2106 | CB | TRUE | 830.42 | 224.6189 | 0.1396 | 9 | 0.00020912 | 364 | 241.4035 | 1563 | 0.054215 | 0.48794 | 1133 | 0.02 | 2507
8313 | RED BLUFF 1104135854 | 103541104 | RED BLUFF 1104 | 135854 | FALSE | 4250.0634 | 2325.1244 | 1.4451 | 34 | 6.0566e-05 | 2759 | 1134.6908 | 761 | 0.053974 | 1.8351 | 1134 |  | 3213
8191 | KESWICK 11011588 | 103451101 | KESWICK 1101 | 1588 | FALSE | 13991.4401 | 13991.4401 | 8.6957 | 33 | 0.00018106 | 503 | 584.74 | 1118 | 0.053968 | 1.7809 | 1135 | 0.19 | 1195
5209 | OLETA 11022642 | 163541102 | OLETA 1102 | 2642 | FALSE | 7497.8568 | 7497.8568 | 4.6599 | 27 | 9.0401e-05 | 1902 | 716.2407 | 1006 | 0.053841 | 1.4537 | 1136 | 0.03 | 2270
2961 | SYCAMORE CREEK 11112014 | 102971111 | SYCAMORE CREEK 1111 | 2014 | FALSE | 35984.1335 | 35984.1335 | 22.3643 | 181 | 0.00010418 | 1548 | 602.3767 | 1097 | 0.053762 | 9.731 | 1137 | 0.2 | 1157
5221 | EL DORADO PH 210163464 | 152762101 | EL DORADO PH 2101 | 63464 | FALSE | 21920.8692 | 21920.8692 | 13.6239 | 70 | 0.00012137 | 1160 | 659.6276 | 1053 | 0.05356 | 3.7492 | 1138 | 0.13 | 1359
1685 | WILLOW CREEK 110347966 | 192171103 | WILLOW CREEK 1103 | 47966 | FALSE | 27271.3222 | 27271.3222 | 16.9492 | 167 | 0.00020988 | 360 | 215.8045 | 1610 | 0.053445 | 8.9254 | 1139 | 0.13 | 1355
1361 | RED BLUFF 11051564 | 103541105 | RED BLUFF 1105 | 1564 | FALSE | 17092.5832 | 1891.6003 | 1.1756 | 133 | 7.329e-05 | 2387 | 869.3002 | 900 | 0.053412 | 7.1038 | 1140 | 0.62 | 839
566 | MORGAN HILL 2110814616 | 83242110 | MORGAN HILL 2110 | 814616 | TRUE | 3902.6921 | 157.4015 | 0.097826 | 28 | 8.7257e-05 | 2006 | 602.3323 | 1098 | 0.053409 | 1.4955 | 1141 |  | 2683
9804 | FROGTOWN 1702694042 | 163451702 | FROGTOWN 1702 | 694042 | TRUE | 972.0471 | 972.0471 | 0.60413 | 8 | 0.00011883 | 1210 | 338.8363 | 1389 | 0.053395 | 0.42716 | 1142 |  | 3427
548 | SHINGLE SPRINGS 21107742 | 153652110 | SHINGLE SPRINGS 2110 | 7742 | FALSE | 73623.591 | 73535.6671 | 45.7027 | 475 | 9.9171e-05 | 1663 | 595.5649 | 1104 | 0.053392 | 25.3612 | 1143 | 1.43 | 675
4014 | CURTIS 1704CB | 163351704 | CURTIS 1704 | CB | FALSE | 22863.3142 | 22355.1304 | 13.8938 | 170 | 0.0001075 | 1464 | 527.7867 | 1176 | 0.053282 | 9.058 | 1144 | 0.12 | 1366
5744 | WOODSIDE 11018974 | 24251101 | WOODSIDE 1101 | 8974 | FALSE | 21278.6691 | 21278.6691 | 13.2248 | 149 | 0.00020534 | 378 | 324.7416 | 1406 | 0.05299 | 7.8956 | 1145 | 76.03 | 55
4200 | MOLINO 1101322 | 42571101 | MOLINO 1101 | 322 | FALSE | 23201.9813 | 22860.7646 | 14.2081 | 167 | 0.00013802 | 893 | 458.1425 | 1238 | 0.052976 | 8.847 | 1146 | 35.69 | 212
7680 | PALMER 1101M88 | 183031101 | PALMER 1101 | M88 | FALSE | 24723.9577 | 4969.351 | 3.0885 | 85 | 4.85e-05 | 3076 | 599.8118 | 1100 | 0.052933 | 4.4993 | 1147 | 0.01 | 2589
2401 | WOODSIDE 11018884 | 24251101 | WOODSIDE 1101 | 8884 | FALSE | 12033.5669 | 12033.5669 | 7.4789 | 74 | 0.00017464 | 530 | 305.5705 | 1438 | 0.052785 | 3.9061 | 1148 | 48.31 | 129
5333 | GARBERVILLE 11022500 | 192221102 | GARBERVILLE 1102 | 2500 | FALSE | 25777.1884 | 25777.1884 | 16.0206 | 106 | 0.00032433 | 107 | 205.0308 | 1627 | 0.052654 | 5.5813 | 1149 | 11.96 | 380
3787 | BEAR VALLEY 21014500 | 252192101 | BEAR VALLEY 2101 | 4500 | FALSE | 132540.1743 | 38902.9544 | 24.1783 | 516 | 4.6379e-05 | 3128 | 1229.9776 | 714 | 0.052537 | 27.1089 | 1150 | 0.03 | 2255
8553 | RED BLUFF 11041302 | 103541104 | RED BLUFF 1104 | 1302 | FALSE | 23388.5169 | 22389.9711 | 13.9155 | 113 | 5.0169e-05 | 3034 | 1215.8532 | 721 | 0.052453 | 5.9272 | 1151 | 0.06 | 1889
10783 | BEAR VALLEY 2105CB | 252192105 | BEAR VALLEY 2105 | CB | FALSE | 6175.4075 | 6175.4075 | 3.838 | 9 | 9.2622e-05 | 1830 | 515.1474 | 1184 | 0.052345 | 0.4711 | 1152 | 0.01 | 2588
10429 | BUTTE 1105244246 | 103081105 | BUTTE 1105 | 244246 | FALSE | 1936.2709 | 1936.2709 | 1.2034 | 11 | 0.00016313 | 610 | 330.8536 | 1396 | 0.052269 | 0.57496 | 1153 |  | 3548
1753 | BRUNSWICK 110651484 | 152481106 | BRUNSWICK 1106 | 51484 | FALSE | 26385.5393 | 24741.7275 | 15.3771 | 195 | 0.0001406 | 862 | 372.49 | 1333 | 0.052211 | 10.1812 | 1154 | 0.17 | 1239
7841 | STONE CORRAL 1110975698 | 252921110 | STONE CORRAL 1110 | 975698 | FALSE | 7671.0517 | 1441.7984 | 0.89608 | 44 | 4.3563e-05 | 3200 | 962.1828 | 852 | 0.052194 | 2.2966 | 1155 |  | 3170
10305 | MIDDLETOWN 1101612 | 43141101 | MIDDLETOWN 1101 | 612 | FALSE | 6362.7002 | 6362.7002 | 3.9544 | 25 | 8.4863e-05 | 2067 | 719.6048 | 1000 | 0.05213 | 1.3033 | 1156 | 0.42 | 931
9510 | PUEBLO 2103776244 | 43292103 | PUEBLO 2103 | 776244 | TRUE | 783.9385 | 274.5802 | 0.17065 | 5 | 5.5048e-05 | 2909 | 540.4117 | 1158 | 0.052117 | 0.26059 | 1157 |  | 3366
2874 | FORT ROSS 11214947 | 42851121 | FORT ROSS 1121 | 4947 | FALSE | 16652.8009 | 16652.8009 | 10.3498 | 56 | 0.00016312 | 611 | 298.2938 | 1450 | 0.052018 | 2.913 | 1158 | 9.04 | 414
5370 | FROGTOWN 17027108 | 163451702 | FROGTOWN 1702 | 7108 | FALSE | 20715.9427 | 15478.9307 | 9.6202 | 99 | 5.144e-05 | 3007 | 993.4887 | 838 | 0.05186 | 5.1341 | 1159 | 0.06 | 1876
7742 | WEST POINT 110272036 | 163201102 | WEST POINT 1102 | 72036 | FALSE | 21135.8241 | 20864.4611 | 12.9673 | 105 | 8.1485e-05 | 2168 | 844.1543 | 916 | 0.051819 | 5.441 | 1160 | 14.82 | 354
8013 | WILLITS 110337506 | 42661103 | WILLITS 1103 | 37506 | FALSE | 18602.139 | 18602.139 | 11.5613 | 77 | 0.00015655 | 678 | 345.7654 | 1377 | 0.051705 | 3.9812 | 1161 | 4.56 | 516
8123 | OTTER 1102CB | 182941102 | OTTER 1102 | CB | FALSE | 10891.762 | 10891.762 | 6.7693 | 40 | 7.3648e-05 | 2374 | 760.2437 | 965 | 0.051564 | 2.0626 | 1162 | 0.19 | 1197
7649 | HARTLEY 1101CB | 43211101 | HARTLEY 1101 | CB | FALSE | 4864.6418 | 2361.7078 | 1.4678 | 33 | 0.00010062 | 1634 | 651.0467 | 1063 | 0.051416 | 1.6967 | 1163 | 0.02 | 2516
4094 | HOPLAND 1101960 | 42251101 | HOPLAND 1101 | 960 | FALSE | 8826.9021 | 6237.2835 | 3.8765 | 33 | 0.00010013 | 1642 | 470.8479 | 1225 | 0.051413 | 1.6966 | 1164 | 0.04 | 2083
7517 | PENRYN 110790970 | 152561107 | PENRYN 1107 | 90970 | FALSE | 6924.4221 | 2317.6472 | 1.4404 | 45 | 0.00014799 | 763 | 359.43 | 1356 | 0.051234 | 2.3055 | 1165 | 0.91 | 749
371 | CURTIS 1701CB | 163351701 | CURTIS 1701 | CB | FALSE | 20034.2871 | 12973.5363 | 8.0631 | 159 | 0.00012464 | 1103 | 555.1824 | 1140 | 0.051116 | 8.1275 | 1166 | 0.08 | 1582
8728 | CORRAL 1103569005 | 162991103 | CORRAL 1103 | 569005 | FALSE | 3858.1769 | 1152.5978 | 0.71634 | 38 | 7.7445e-05 | 2278 | 606.2479 | 1095 | 0.051027 | 1.939 | 1167 |  | 3255
3664 | PLACERVILLE 2106CB | 153082106 | PLACERVILLE 2106 | CB | FALSE | 10545.3693 | 10545.3693 | 6.554 | 31 | 0.00031506 | 112 | 137.2983 | 1822 | 0.050873 | 1.5771 | 1168 | 0.17 | 1226
10993 | MESA 1103737698 | 182821103 | MESA 1103 | 737698 | TRUE | 340.8251 | 324.8619 | 0.2019 | 3 | 4.5459e-05 | 3153 | 1051.0501 | 795 | 0.050749 | 0.15225 | 1169 |  | 3626
7973 | PENRYN 110550548 | 152561105 | PENRYN 1105 | 50548 | TRUE | 7824.3085 | 154.2272 | 0.095853 | 58 | 0.00014087 | 856 | 418.2026 | 1274 | 0.050695 | 2.9403 | 1170 | 1.85 | 638
9859 | CUYAMA 1103684566 | 253141103 | CUYAMA 1103 | 684566 | FALSE | 4872.6951 | 4856.693 | 3.0185 | 4 | 3.3492e-05 | 3376 | 2480.1079 | 347 | 0.050626 | 0.20251 | 1171 |  | 3437
7777 | GANSNER 11012424 | 103021101 | GANSNER 1101 | 2424 | FALSE | 30415.1718 | 30186.9031 | 18.7613 | 141 | 6.6531e-05 | 2572 | 747.4809 | 977 | 0.050559 | 7.1288 | 1172 | 0.17 | 1231
10622 | TEJON 1103286542 | 252931103 | TEJON 1103 | 286542 | FALSE | 9381.8687 | 3501.8559 | 2.1764 | 25 | 2.3634e-05 | 3508 | 2087.6942 | 432 | 0.050527 | 1.2632 | 1173 |  | 3581
2224 | COTATI 1103148 | 42271103 | COTATI 1103 | 148 | FALSE | 24974.2018 | 24850.3478 | 15.4446 | 107 | 5.3405e-05 | 2952 | 932.2932 | 869 | 0.050374 | 5.39 | 1174 | 0.13 | 1343
2728 | MESA 1103M72 | 182821103 | MESA 1103 | M72 | FALSE | 24045.3968 | 13551.8371 | 8.4225 | 180 | 5.9996e-05 | 2776 | 772.2065 | 958 | 0.050224 | 9.0403 | 1175 | 0.09 | 1574
4743 | WYANDOTTE 11031508 | 102911103 | WYANDOTTE 1103 | 1508 | FALSE | 43792.5733 | 43792.5733 | 27.2173 | 249 | 0.00022481 | 303 | 269.7872 | 1498 | 0.050062 | 12.4656 | 1176 | 0.5 | 893
1729 | LUCERNE 1106664 | 43351106 | LUCERNE 1106 | 664 | FALSE | 17972.9054 | 15503.1919 | 9.6353 | 140 | 0.00013278 | 964 | 291.1861 | 1461 | 0.050043 | 7.006 | 1177 | 0.12 | 1389
1094 | HIGGINS 110332120 | 152691103 | HIGGINS 1103 | 32120 | FALSE | 65924.4872 | 65394.3269 | 40.6428 | 485 | 0.00015495 | 695 | 454.7289 | 1240 | 0.049959 | 24.23 | 1178 | 0.23 | 1120
1827 | BELL 11082226 | 152701108 | BELL 1108 | 2226 | FALSE | 41003.1194 | 38762.6482 | 24.0911 | 329 | 0.00015086 | 729 | 321.4507 | 1412 | 0.049738 | 16.3638 | 1179 | 0.14 | 1330
971 | KANAKA 110183288 | 103221101 | KANAKA 1101 | 83288 | FALSE | 27936.7507 | 27936.7507 | 17.3628 | 140 | 0.00010219 | 1600 | 523.0336 | 1179 | 0.049736 | 6.9631 | 1180 | 56.24 | 100
6396 | MC ARTHUR 11011490 | 103491101 | MC ARTHUR 1101 | 1490 | FALSE | 24262.143 | 16986.9503 | 10.5575 | 122 | 4.6732e-05 | 3120 | 1014.4444 | 820 | 0.0497 | 6.0634 | 1181 | 0.01 | 2607
1501 | PIERCY 2110XR258 | 83912110 | PIERCY 2110 | XR258 | FALSE | 42613.4021 | 35307.703 | 21.9439 | 117 | 7.1286e-05 | 2438 | 813.0901 | 929 | 0.049692 | 5.814 | 1182 | 0.07 | 1728
4371 | BELLEVUE 2103552 | 43182103 | BELLEVUE 2103 | 552 | FALSE | 24092.9744 | 15233.6156 | 9.4678 | 172 | 0.00013239 | 975 | 420.6103 | 1272 | 0.049565 | 8.5251 | 1183 | 2.64 | 591
774 | MORGAN HILL 2110654924 | 83242110 | MORGAN HILL 2110 | 654924 | FALSE | 8067.2123 | 4423.0701 | 2.749 | 61 | 8.0217e-05 | 2200 | 663.8303 | 1048 | 0.049343 | 3.0099 | 1184 |  | 2692
4796 | SISQUOC 1102M52 | 182811102 | SISQUOC 1102 | M52 | FALSE | 56469.342 | 54530.2399 | 33.8908 | 131 | 6.7691e-05 | 2540 | 719.2711 | 1001 | 0.04915 | 6.4386 | 1185 | 0.09 | 1551
899 | RACETRACK 170455798 | 163761704 | RACETRACK 1704 | 55798 | FALSE | 37886.6196 | 37886.6196 | 23.5467 | 246 | 0.00011154 | 1383 | 632.8382 | 1075 | 0.049086 | 12.0752 | 1186 | 6.76 | 461
8632 | STELLING 11102243 | 83481110 | STELLING 1110 | 2243 | FALSE | 3051.2175 | 3051.2175 | 1.8963 | 16 | 0.00019188 | 434 | 257.113 | 1528 | 0.049051 | 0.78482 | 1187 | 4.86 | 503
4409 | HIGGINS 11071070 | 152691107 | HIGGINS 1107 | 1070 | FALSE | 13188.3135 | 12735.6646 | 7.9153 | 100 | 8.36e-05 | 2108 | 545.0696 | 1153 | 0.048737 | 4.8737 | 1188 | 0.08 | 1639
2076 | SAN JUSTO 110136902 | 183181101 | SAN JUSTO 1101 | 36902 | FALSE | 23754.9885 | 19990.5557 | 12.4242 | 147 | 6.372e-05 | 2656 | 753.8177 | 971 | 0.048735 | 7.1641 | 1189 | 0.05 | 2037
6423 | TASSAJARA 2113MR276 | 14662113 | TASSAJARA 2113 | MR276 | FALSE | 6265.9535 | 6199.9698 | 3.8533 | 42 | 0.00011011 | 1409 | 507.3387 | 1193 | 0.048684 | 2.0447 | 1190 | 0.45 | 920
7009 | PENRYN 110551676 | 152561105 | PENRYN 1105 | 51676 | FALSE | 18975.7232 | 12910.4516 | 8.0239 | 145 | 0.00015332 | 718 | 372.9974 | 1332 | 0.048603 | 7.0475 | 1191 | 1.53 | 667
9522 | STONE CORRAL 1110894956 | 252921110 | STONE CORRAL 1110 | 894956 | FALSE | 2635.3424 | 1243.2231 | 0.77267 | 16 | 4.142e-05 | 3237 | 1280.1289 | 689 | 0.048471 | 0.77554 | 1192 |  | 3371
4908 | DIVIDE 1103567884 | 182571103 | DIVIDE 1103 | 567884 | FALSE | 4535.2993 | 4025.5628 | 2.5019 | 27 | 5.6021e-05 | 2887 | 815.5904 | 927 | 0.048164 | 1.3004 | 1193 |  | 2926
537 | FORT SEWARD 11211602 | 192321121 | FORT SEWARD 1121 | 1602 | FALSE | 36538.7848 | 29307.7542 | 18.2149 | 109 | 0.00014214 | 837 | 344.2493 | 1379 | 0.048111 | 5.244 | 1194 | 0.07 | 1681
522 | MONTE RIO 1111292 | 42811111 | MONTE RIO 1111 | 292 | FALSE | 31568.6739 | 25055.0465 | 15.5718 | 165 | 0.00011528 | 1294 | 534.9666 | 1165 | 0.048057 | 7.9294 | 1195 | 0.1 | 1486
6679 | LAYTONVILLE 11011760 | 42681101 | LAYTONVILLE 1101 | 1760 | FALSE | 20336.5883 | 15610.272 | 9.7018 | 73 | 0.00026452 | 183 | 220.0765 | 1605 | 0.048043 | 3.5072 | 1196 | 0 | 2647
7262 | LOW GAP 11014160 | 192411101 | LOW GAP 1101 | 4160 | FALSE | 34990.3559 | 34990.3559 | 21.7466 | 194 | 0.00015367 | 716 | 332.5299 | 1395 | 0.047994 | 9.3109 | 1197 | 0.11 | 1435
2115 | GARBERVILLE 1102CB | 192221102 | GARBERVILLE 1102 | CB | FALSE | 26803.1335 | 19300.4618 | 11.9953 | 191 | 0.00043617 | 57 | 153.1917 | 1768 | 0.047992 | 9.1665 | 1198 | 0.08 | 1590
859 | SALT SPRINGS 21011216 | 163692101 | SALT SPRINGS 2101 | 1216 | FALSE | 8821.9491 | 8821.9491 | 5.4829 | 32 | 4.4432e-05 | 3178 | 673.2647 | 1041 | 0.04796 | 1.5347 | 1199 | 0.02 | 2470
4717 | CAMBRIA 1101V76 | 182771101 | CAMBRIA 1101 | V76 | FALSE | 30510.6388 | 30510.6388 | 18.9625 | 59 | 6.8997e-05 | 2510 | 662.2635 | 1050 | 0.047925 | 2.8276 | 1200 | 0.05 | 2034
3890 | KANAKA 110165606 | 103221101 | KANAKA 1101 | 65606 | FALSE | 20505.679 | 20505.679 | 12.7444 | 145 | 0.00013634 | 916 | 329.1085 | 1398 | 0.047918 | 6.9481 | 1201 | 65.5 | 77
11044 | SAN LUIS OBISPO 1104753254 | 182631104 | SAN LUIS OBISPO 1104 | 753254 | TRUE | 576.081 | 561.1486 | 0.34876 | 2 | 0.0001316 | 988 | 1237.8633 | 707 | 0.047657 | 0.095314 | 1202 |  | 3631
868 | PEORIA 170459596 | 163781704 | PEORIA 1704 | 59596 | FALSE | 58128.5973 | 33598.813 | 20.8818 | 294 | 6.8689e-05 | 2517 | 659.4011 | 1054 | 0.047553 | 13.9806 | 1203 | 0.08 | 1603
5643 | CLEAR LAKE 1102991285 | 42141102 | CLEAR LAKE 1102 | 991285 | TRUE | 2786.1304 | 525.9001 | 0.32685 | 24 | 8.6607e-05 | 2019 | 543.9338 | 1154 | 0.047469 | 1.1393 | 1204 |  | 2968
2996 | BURNEY 11012402 | 103311101 | BURNEY 1101 | 2402 | FALSE | 6035.4639 | 2411.6802 | 1.4989 | 18 | 6.5093e-05 | 2608 | 759.0384 | 966 | 0.047353 | 0.85235 | 1205 | 0.04 | 2096
982 | WEST POINT 11024788 | 163201102 | WEST POINT 1102 | 4788 | FALSE | 111874.9537 | 111874.9537 | 69.5307 | 673 | 7.0255e-05 | 2460 | 791.3267 | 951 | 0.047319 | 31.8454 | 1206 | 1.08 | 718
6337 | MIWUK 170219772 | 163661702 | MIWUK 1702 | 19772 | FALSE | 6198.5938 | 6198.5938 | 3.8525 | 41 | 7.7179e-05 | 2283 | 525.9561 | 1177 | 0.047283 | 1.9386 | 1207 | 48.67 | 125
1317 | MOLINO 1102178 | 42571102 | MOLINO 1102 | 178 | FALSE | 21896.763 | 19626.441 | 12.1979 | 182 | 0.0001498 | 741 | 376.3772 | 1328 | 0.047227 | 8.5954 | 1208 | 24.56 | 276
2756 | AUBERRY 1101R2845 | 254151101 | AUBERRY 1101 | R2845 | FALSE | 28680.0593 | 28680.0593 | 17.8248 | 172 | 4.0941e-05 | 3246 | 1025.9007 | 811 | 0.047182 | 8.1154 | 1209 | 0.19 | 1180
1878 | JESSUP 110168362 | 103441101 | JESSUP 1101 | 68362 | FALSE | 11797.2095 | 8312.3827 | 5.1662 | 96 | 0.00012657 | 1070 | 343.9077 | 1382 | 0.047076 | 4.5193 | 1210 |  | 2751
1899 | SAN BENITO 2104785888 | 182742104 | SAN BENITO 2104 | 785888 | FALSE | 11268.8078 | 7730.7085 | 4.8047 | 49 | 7.806e-05 | 2258 | 321.3673 | 1413 | 0.047021 | 2.304 | 1211 |  | 2753
1312 | MOUNTAIN QUARRIES 210192474 | 152282101 | MOUNTAIN QUARRIES 2101 | 92474 | FALSE | 25104.6477 | 24305.4181 | 15.1059 | 173 | 0.00013452 | 934 | 428.2739 | 1261 | 0.046937 | 8.12 | 1212 | 0.26 | 1060
9280 | FREMONT 1104MR339 | 14351104 | FREMONT 1104 | MR339 | FALSE | 11213.6735 | 1921.2331 | 1.1941 | 73 | 5.8956e-05 | 2809 | 692.7863 | 1028 | 0.046887 | 3.4227 | 1213 | 1 | 731
10367 | PEORIA 170488630 | 163781704 | PEORIA 1704 | 88630 | FALSE | 1252.5971 | 1252.5971 | 0.77849 | 6 | 6.5372e-05 | 2605 | 876.4135 | 895 | 0.046842 | 0.28105 | 1214 | 0.03 | 2399
3920 | LLAGAS 2107XR178 | 83182107 | LLAGAS 2107 | XR178 | FALSE | 20866.1928 | 9493.9491 | 5.9005 | 138 | 8.7818e-05 | 1989 | 483.5128 | 1211 | 0.04683 | 6.4625 | 1215 | 0.94 | 744
9293 | DUNLAP 110239190 | 254061102 | DUNLAP 1102 | 39190 | FALSE | 2877.2566 | 2877.2566 | 1.7882 | 17 | 6.3388e-05 | 2665 | 760.9398 | 964 | 0.046743 | 0.79463 | 1216 | 0 | 2644
9995 | GEYSERVILLE 1102180193 | 42891102 | GEYSERVILLE 1102 | 180193 | FALSE | 3981.725 | 3477.0858 | 2.161 | 23 | 0.00010067 | 1630 | 430.5545 | 1259 | 0.046684 | 1.0737 | 1217 |  | 3467
2795 | BELL 1108467470 | 152701108 | BELL 1108 | 467470 | FALSE | 4805.9002 | 2987.9 | 1.857 | 40 | 0.00023296 | 271 | 103.254 | 1936 | 0.046424 | 1.857 | 1218 |  | 2799
6866 | EDENVALE 1102XR064 | 82951102 | EDENVALE 1102 | XR064 | FALSE | 6026.8923 | 1175.6095 | 0.73065 | 35 | 8.4777e-05 | 2070 | 462.9277 | 1232 | 0.046387 | 1.6236 | 1219 |  | 3069
2884 | MC ARTHUR 110137388 | 103491101 | MC ARTHUR 1101 | 37388 | FALSE | 20103.5682 | 13050.4067 | 8.1109 | 56 | 2.1126e-05 | 3533 | 2437.488 | 352 | 0.046193 | 2.5868 | 1220 | 0 | 2639
8090 | PENRYN 1105817491 | 152561105 | PENRYN 1105 | 817491 | FALSE | 3153.3616 | 2279.4584 | 1.4167 | 24 | 0.00010509 | 1523 | 532.8427 | 1169 | 0.046183 | 1.1084 | 1221 |  | 3191
196 | MILPITAS 1109XR082 | 82831109 | MILPITAS 1109 | XR082 | FALSE | 32889.5484 | 31674.5025 | 19.6858 | 186 | 6.2383e-05 | 2710 | 716.1395 | 1007 | 0.046133 | 8.5807 | 1222 | 0.21 | 1151
9874 | JARVIS 1108767280 | 13501108 | JARVIS 1108 | 767280 | TRUE | 1164.558 | 816.4039 | 0.5074 | 11 | 4.3875e-05 | 3191 | 579.646 | 1124 | 0.046117 | 0.50728 | 1223 |  | 3440
3653 | PUEBLO 2103678 | 43292103 | PUEBLO 2103 | 678 | FALSE | 57111.2211 | 56857.8795 | 35.3374 | 325 | 0.00011031 | 1406 | 496.7562 | 1204 | 0.046077 | 14.9751 | 1224 | 2.05 | 626
4529 | MC ARTHUR 110138998 | 103491101 | MC ARTHUR 1101 | 38998 | TRUE | 9317.0359 | 189.4976 | 0.11777 | 61 | 3.5e-05 | 3353 | 912.9133 | 879 | 0.046064 | 2.8099 | 1225 | 0.01 | 2570
9562 | MOLINO 1101600112 | 42571101 | MOLINO 1101 | 600112 | FALSE | 2016.2056 | 1283.9759 | 0.798 | 18 | 0.00016569 | 586 | 185.2798 | 1671 | 0.045774 | 0.82393 | 1226 |  | 3379
8471 | MONTICELLO 1101654 | 43051101 | MONTICELLO 1101 | 654 | FALSE | 14047.9314 | 13220.1574 | 8.2164 | 71 | 8.6928e-05 | 2013 | 576.6406 | 1126 | 0.045547 | 3.2338 | 1227 | 0.06 | 1895
9084 | SWIFT 2110XR254 | 83392110 | SWIFT 2110 | XR254 | FALSE | 40510.5344 | 40510.5344 | 25.1775 | 134 | 6.9418e-05 | 2490 | 745.0432 | 979 | 0.045544 | 6.1028 | 1228 | 0.31 | 1003
5247 | MOLINO 1102658 | 42571102 | MOLINO 1102 | 658 | FALSE | 17510.52 | 17510.52 | 10.8829 | 107 | 0.00014355 | 818 | 343.9435 | 1381 | 0.045341 | 4.8515 | 1229 | 50.23 | 119
1624 | CLAY 11037124 | 163341103 | CLAY 1103 | 7124 | FALSE | 51663.5431 | 17797.9944 | 11.0615 | 286 | 6.2921e-05 | 2684 | 727.3308 | 993 | 0.045279 | 12.9498 | 1230 | 0.05 | 2026
6683 | UKIAH 11143606 | 42771114 | UKIAH 1114 | 3606 | FALSE | 26641.1753 | 17219.5096 | 10.702 | 129 | 8.6419e-05 | 2025 | 738.4699 | 985 | 0.045178 | 5.828 | 1231 | 0.09 | 1541
6114 | GANSNER 110137550 | 103021101 | GANSNER 1101 | 37550 | TRUE | 5259.0816 | 590.535 | 0.36702 | 33 | 6.5837e-05 | 2592 | 741.2586 | 983 | 0.045042 | 1.4864 | 1232 | 1.25 | 693
10276 | LAKEVILLE 1102367100 | 43371102 | LAKEVILLE 1102 | 367100 | TRUE | 1041.0726 | 900.8036 | 0.55985 | 6 | 8.144e-05 | 2169 | 654.3693 | 1059 | 0.04493 | 0.26958 | 1233 |  | 3526
3592 | CURTIS 17039330 | 163351703 | CURTIS 1703 | 9330 | FALSE | 66516.2766 | 66516.2766 | 41.3401 | 345 | 4.8089e-05 | 3091 | 936.7226 | 867 | 0.044648 | 15.4037 | 1234 | 0.27 | 1056
1338 | SILVERADO 210437632 | 43432104 | SILVERADO 2104 | 37632 | FALSE | 42770.2942 | 42770.2942 | 26.5819 | 304 | 0.0001591 | 651 | 314.3513 | 1426 | 0.044601 | 13.5588 | 1235 | 2.55 | 599
9592 | BELL 1107912460 | 152701107 | BELL 1107 | 912460 | TRUE | 716.9415 | 226.2188 | 0.1406 | 6 | 0.0002094 | 362 | 319.3069 | 1418 | 0.044495 | 0.26697 | 1236 |  | 3384
9543 | GARBERVILLE 110237054 | 192221102 | GARBERVILLE 1102 | 37054 | FALSE | 14849.4038 | 14394.233 | 8.9461 | 76 | 0.00045585 | 46 | 99.7602 | 1954 | 0.044439 | 3.3774 | 1237 | 0.04 | 2218
528 | PLACERVILLE 210692012 | 153082106 | PLACERVILLE 2106 | 92012 | FALSE | 29794.6367 | 29794.6367 | 18.5175 | 219 | 0.00021006 | 358 | 266.7744 | 1505 | 0.044304 | 9.7026 | 1238 | 27.19 | 260
2289 | PASO ROBLES 1103351084 | 182611103 | PASO ROBLES 1103 | 351084 | FALSE | 14339.9461 | 3813.7275 | 2.3702 | 91 | 6.4148e-05 | 2639 | 844.8485 | 915 | 0.044255 | 4.0272 | 1239 |  | 2770
4151 | SHINGLE SPRINGS 2109CB | 153652109 | SHINGLE SPRINGS 2109 | CB | FALSE | 44653.7534 | 44000.0643 | 27.3462 | 341 | 0.00012378 | 1124 | 546.8562 | 1150 | 0.044085 | 15.0331 | 1240 | 0.94 | 742
8694 | MC ARTHUR 11011544 | 103491101 | MC ARTHUR 1101 | 1544 | FALSE | 44972.2866 | 27291.0085 | 16.9615 | 135 | 2.4864e-05 | 3497 | 2130.6474 | 417 | 0.044056 | 5.9476 | 1241 | 0 | 2640
5303 | STONE CORRAL 11087100 | 252921108 | STONE CORRAL 1108 | 7100 | FALSE | 29355.7923 | 3757.8694 | 2.3355 | 130 | 3.9155e-05 | 3282 | 1207.5405 | 728 | 0.04396 | 5.7148 | 1242 | 0.01 | 2576
5138 | SUMMIT 11022302 | 152591102 | SUMMIT 1102 | 2302 | FALSE | 2152.9343 | 2152.9343 | 1.3381 | 19 | 6.3222e-05 | 2671 | 648.1357 | 1067 | 0.043905 | 0.8342 | 1243 | 0.01 | 2616
3403 | PENRYN 11051378 | 152561105 | PENRYN 1105 | 1378 | FALSE | 3084.1467 | 1447.5189 | 0.89964 | 25 | 0.00011131 | 1388 | 372.4728 | 1334 | 0.043839 | 1.096 | 1244 | 0.02 | 2452
5562 | GARBERVILLE 110139524 | 192221101 | GARBERVILLE 1101 | 39524 | FALSE | 24862.4083 | 8232.0089 | 5.1162 | 138 | 0.00038497 | 72 | 130.5694 | 1844 | 0.04372 | 6.0334 | 1245 | 0.03 | 2332
3303 | BIG BEND 1101180398 | 103751101 | BIG BEND 1101 | 180398 | FALSE | 8946.0191 | 8946.0191 | 5.56 | 48 | 0.0002082 | 371 | 244.7887 | 1555 | 0.04366 | 2.0957 | 1246 | 24.5 | 278
5481 | VACAVILLE 110847860 | 63601108 | VACAVILLE 1108 | 47860 | TRUE | 6236.9476 | 466.0192 | 0.28963 | 54 | 7.3661e-05 | 2372 | 319.7615 | 1416 | 0.043573 | 2.353 | 1247 | 0.02 | 2411
8994 | SAN LUIS OBISPO 1104982992 | 182631104 | SAN LUIS OBISPO 1104 | 982992 | FALSE | 14390.2086 | 14390.2086 | 8.9436 | 52 | 4.6115e-05 | 3136 | 911.2189 | 880 | 0.043526 | 2.2633 | 1248 |  | 3292
6482 | UKIAH 1113691436 | 42771113 | UKIAH 1113 | 691436 | FALSE | 3576.8147 | 1680.7069 | 1.0446 | 28 | 0.00012089 | 1165 | 323.1464 | 1409 | 0.043449 | 1.2166 | 1249 |  | 3034
7283 | COVELO 1101112804 | 43061101 | COVELO 1101 | 112804 | FALSE | 30691.3669 | 16512.5111 | 10.2626 | 67 | 9.7484e-05 | 1701 | 651.0362 | 1064 | 0.043443 | 2.9107 | 1250 |  | 3111
2688 | STILLWATER 11021466 | 103561102 | STILLWATER 1102 | 1466 | FALSE | 33154.3349 | 33039.7041 | 20.5343 | 211 | 0.0001572 | 672 | 705.5165 | 1017 | 0.043245 | 9.1248 | 1251 | 0.07 | 1677
6122 | EEL RIVER 11024814 | 192381102 | EEL RIVER 1102 | 4814 | FALSE | 44262.9015 | 43433.15 | 26.9939 | 117 | 0.00018022 | 512 | 271.8858 | 1490 | 0.043216 | 5.0562 | 1252 | 0.83 | 769
8658 | MENLO 11037902 | 24131103 | MENLO 1103 | 7902 | FALSE | 26218.9532 | 18823.9554 | 11.6992 | 143 | 0.00018704 | 461 | 146.5682 | 1787 | 0.043162 | 6.1722 | 1253 | 0.06 | 1892
5986 | SILVERADO 210478268 | 43432104 | SILVERADO 2104 | 78268 | FALSE | 15647.3206 | 15647.3206 | 9.7249 | 114 | 0.00016165 | 623 | 303.7186 | 1445 | 0.043133 | 4.9171 | 1254 | 73.54 | 60
3705 | ALTO 11221212 | 42031122 | ALTO 1122 | 1212 | FALSE | 3797.0171 | 2977.1941 | 1.8503 | 25 | 0.00010853 | 1436 | 197.8244 | 1646 | 0.043056 | 1.0764 | 1255 | 28.71 | 247
565 | CALPELLA 1101CB | 43411101 | CALPELLA 1101 | CB | FALSE | 32987.4913 | 18947.9362 | 11.7762 | 226 | 0.00012255 | 1139 | 327.7945 | 1401 | 0.043018 | 9.722 | 1256 | 0.04 | 2117
1815 | OTTER 110298036 | 182941102 | OTTER 1102 | 98036 | FALSE | 14803.9566 | 14803.9566 | 9.2007 | 64 | 0.00012504 | 1098 | 294.291 | 1456 | 0.042868 | 2.7435 | 1257 | 0.04 | 2216
5821 | HIGHLANDS 11034630 | 43361103 | HIGHLANDS 1103 | 4630 | FALSE | 5558.0773 | 1729.1767 | 1.0747 | 42 | 7.7824e-05 | 2266 | 548.6975 | 1148 | 0.042814 | 1.7982 | 1258 | 0.05 | 2061
1927 | HIGGINS 1110166282 | 152691110 | HIGGINS 1110 | 166282 | FALSE | 38601.364 | 38601.364 | 23.9909 | 256 | 0.00012662 | 1069 | 425.8459 | 1266 | 0.042498 | 10.8796 | 1259 |  | 2757
6705 | GIRVAN 11021028 | 103401102 | GIRVAN 1102 | 1028 | FALSE | 28404.1063 | 28404.1063 | 17.6533 | 208 | 0.00012459 | 1106 | 555.8921 | 1139 | 0.042483 | 8.8364 | 1260 | 8.08 | 437
3470 | OILFIELDS 1103370932 | 182391103 | OILFIELDS 1103 | 370932 | TRUE | 2172.9579 | 619.9296 | 0.38529 | 6 | 3.0451e-05 | 3423 | 729.2934 | 991 | 0.042464 | 0.25478 | 1261 |  | 2828
9825 | GIRVAN 1101CB | 103401101 | GIRVAN 1101 | CB | FALSE | 5303.193 | 2471.5392 | 1.5361 | 31 | 0.0001612 | 628 | 200.4454 | 1640 | 0.042406 | 1.3146 | 1262 | 0.01 | 2593
4531 | CRESCENT MILLS 21013113 | 103132101 | CRESCENT MILLS 2101 | 3113 | FALSE | 1919.7007 | 1919.7007 | 1.1931 | 9 | 5.1754e-05 | 2999 | 970.9306 | 849 | 0.042389 | 0.3815 | 1263 | 12.05 | 376
4502 | WILLITS 1103968 | 42661103 | WILLITS 1103 | 968 | FALSE | 44551.6644 | 42969.09 | 26.7055 | 283 | 0.00010481 | 1533 | 381.6576 | 1318 | 0.042383 | 11.9944 | 1264 | 33.68 | 221
293 | MENDOCINO 110131322 | 42951101 | MENDOCINO 1101 | 31322 | FALSE | 46269.6305 | 9420.014 | 5.8546 | 310 | 0.00011583 | 1276 | 412.2583 | 1282 | 0.04237 | 13.1348 | 1265 | 0.05 | 1992
332 | MESA 1101CB | 182821101 | MESA 1101 | CB | FALSE | 40952.4168 | 22299.6831 | 13.8593 | 230 | 5.1221e-05 | 3009 | 603.2532 | 1096 | 0.042367 | 9.7444 | 1266 | 0.03 | 2242
6761 | HORSESHOE 11011682 | 152571101 | HORSESHOE 1101 | 1682 | TRUE | 14763.8266 | 326.6132 | 0.20299 | 112 | 0.00012357 | 1130 | 359.4666 | 1355 | 0.042324 | 4.7402 | 1267 | 0.48 | 906
4789 | APPLE HILL 110412842 | 153661104 | APPLE HILL 1104 | 12842 | FALSE | 27066.2595 | 25454.1408 | 15.8199 | 209 | 0.00018752 | 457 | 122.8933 | 1862 | 0.042311 | 8.8429 | 1268 | 24.93 | 275
5435 | SUNOL 1101MR299 | 14241101 | SUNOL 1101 | MR299 | FALSE | 7955.2462 | 7955.2462 | 4.9442 | 58 | 9.0049e-05 | 1910 | 452.8222 | 1243 | 0.042276 | 2.452 | 1269 | 0.4 | 946
5875 | MESA 11016113 | 182821101 | MESA 1101 | 6113 | FALSE | 15649.5972 | 2800.3205 | 1.7404 | 100 | 5.0937e-05 | 3015 | 1017.9876 | 816 | 0.042268 | 4.2268 | 1270 | 0.86 | 762
6536 | PINE GROVE 11026080 | 163751102 | PINE GROVE 1102 | 6080 | FALSE | 55307.7629 | 55307.7629 | 34.374 | 322 | 0.00011497 | 1300 | 414.8336 | 1277 | 0.042249 | 13.6042 | 1271 | 0.17 | 1242
10453 | RIO DELL 11027124 | 192251102 | RIO DELL 1102 | 7124 | FALSE | 1081.3743 | 1081.3743 | 0.67208 | 5 | 0.0002308 | 283 | 190.3883 | 1663 | 0.042229 | 0.21114 | 1272 | 0.05 | 1941
9767 | SAN BERNARD 1101641042 | 253191101 | SAN BERNARD 1101 | 641042 | FALSE | 10558.7861 | 2300.7684 | 1.4299 | 22 | 2.7605e-05 | 3464 | 1880.7413 | 480 | 0.042194 | 0.92827 | 1273 |  | 3414
7173 | OTTER 110237132 | 182941102 | OTTER 1102 | 37132 | FALSE | 9343.2123 | 9343.2123 | 5.8068 | 50 | 0.00010209 | 1601 | 598.7122 | 1102 | 0.042173 | 2.1086 | 1274 |  | 3104
7839 | FROGTOWN 1702204480 | 163451702 | FROGTOWN 1702 | 204480 | TRUE | 3182.9165 | 807.68 | 0.50198 | 28 | 0.00015459 | 699 | 296.133 | 1455 | 0.04209 | 1.1785 | 1275 |  | 3169
1556 | HOPLAND 110180620 | 42251101 | HOPLAND 1101 | 80620 | FALSE | 8949.87 | 1997.9252 | 1.2417 | 51 | 7.4695e-05 | 2340 | 506.899 | 1194 | 0.04205 | 2.1446 | 1276 | 0.61 | 849
796 | MESA 1101M86 | 182821101 | MESA 1101 | M86 | FALSE | 33517.8054 | 20500.8716 | 12.7414 | 217 | 4.9333e-05 | 3053 | 762.6869 | 961 | 0.041844 | 9.0801 | 1277 | 0.04 | 2086
4020 | CABRILLO 1103Y10 | 183101103 | CABRILLO 1103 | Y10 | FALSE | 24460.4132 | 7788.8369 | 4.8408 | 122 | 3.6552e-05 | 3322 | 632.6734 | 1076 | 0.041779 | 5.0971 | 1278 | 0.05 | 1949
4294 | FITCH MOUNTAIN 11134566 | 42751113 | FITCH MOUNTAIN 1113 | 4566 | FALSE | 28160.2778 | 20128.0864 | 12.5097 | 180 | 0.00011406 | 1319 | 393.9766 | 1301 | 0.041761 | 7.5169 | 1279 | 0.11 | 1420
3368 | PEORIA 17051834 | 163781705 | PEORIA 1705 | 1834 | FALSE | 38353.1383 | 37922.7084 | 23.5691 | 217 | 8.1071e-05 | 2182 | 531.0758 | 1172 | 0.041581 | 9.0231 | 1280 | 0.17 | 1247
4811 | CALAVERAS CEMENT 1101502 | 162211101 | CALAVERAS CEMENT 1101 | 502 | FALSE | 65884.6113 | 60591.0346 | 37.6576 | 331 | 9.3364e-05 | 1812 | 435.9933 | 1257 | 0.041554 | 13.7543 | 1281 | 0.21 | 1137
8493 | COTATI 1102282 | 42271102 | COTATI 1102 | 282 | FALSE | 8222.1189 | 4475.09 | 2.7813 | 62 | 8.3509e-05 | 2115 | 543.5705 | 1155 | 0.041526 | 2.5746 | 1282 | 2.35 | 612
3229 | WISE 1102CB | 152271102 | WISE 1102 | CB | FALSE | 23260.435 | 22633.2401 | 14.0667 | 177 | 0.00014209 | 838 | 392.5466 | 1305 | 0.041442 | 7.3353 | 1283 | 0.11 | 1427
2423 | APPLE HILL 110413512 | 153661104 | APPLE HILL 1104 | 13512 | FALSE | 49131.7705 | 45791.8869 | 28.4598 | 345 | 0.00019634 | 412 | 199.5912 | 1642 | 0.041392 | 14.2801 | 1284 | 59.2 | 89
3013 | BIG MEADOWS 21012586 | 102812101 | BIG MEADOWS 2101 | 2586 | FALSE | 17615.5168 | 10070.6101 | 6.2589 | 91 | 4.8503e-05 | 3075 | 1089.5717 | 778 | 0.041237 | 3.7526 | 1285 | 0.09 | 1567
6401 | COPPERMINE 1104556430 | 252411104 | COPPERMINE 1104 | 556430 | FALSE | 26122.847 | 7792.8441 | 4.8433 | 122 | 1.6369e-05 | 3574 | 2433.0686 | 354 | 0.041063 | 5.0096 | 1286 |  | 3028
9989 | ORO FINO 11022236 | 103031102 | ORO FINO 1102 | 2236 | FALSE | 4120.4561 | 4120.4561 | 2.5609 | 11 | 0.00027956 | 156 | 116.7508 | 1889 | 0.040994 | 0.45093 | 1287 | 0.26 | 1069
3633 | BIG BEND 11021972 | 103751102 | BIG BEND 1102 | 1972 | FALSE | 34265.9827 | 34265.9827 | 21.2964 | 177 | 0.00011711 | 1243 | 377.3246 | 1326 | 0.040961 | 7.25 | 1288 | 73.04 | 64
7419 | MARTELL 110299214 | 163011102 | MARTELL 1102 | 99214 | FALSE | 3296.9506 | 2953.539 | 1.8356 | 21 | 0.00014798 | 764 | 541.677 | 1157 | 0.040838 | 0.85759 | 1289 | 0.04 | 2193
5589 | BUELLTON 1101Y36 | 183041101 | BUELLTON 1101 | Y36 | FALSE | 73124.8896 | 60717.9561 | 37.7365 | 283 | 4.3104e-05 | 3207 | 946.8115 | 863 | 0.0408 | 11.5464 | 1290 | 0.14 | 1321
2824 | GEYSERVILLE 1101166 | 42891101 | GEYSERVILLE 1101 | 166 | FALSE | 15936.7517 | 9969.1209 | 6.1958 | 110 | 0.00012238 | 1141 | 339.9187 | 1388 | 0.040759 | 4.4835 | 1291 | 0.03 | 2283
612 | DIAMOND SPRINGS 11062100 | 152261106 | DIAMOND SPRINGS 1106 | 2100 | FALSE | 62879.0761 | 62879.0761 | 39.0796 | 403 | 0.00011682 | 1254 | 355.7448 | 1364 | 0.040696 | 16.4004 | 1292 | 0.14 | 1318
4758 | LAYTONVILLE 1101402 | 42681101 | LAYTONVILLE 1101 | 402 | FALSE | 37926.2925 | 37584.6138 | 23.359 | 151 | 0.0001662 | 581 | 293.7692 | 1458 | 0.040695 | 6.145 | 1293 | 0.07 | 1764
7625 | ATASCADERO 1103440856 | 182541103 | ATASCADERO 1103 | 440856 | FALSE | 56881.4108 | 56011.6123 | 34.8114 | 349 | 6.3248e-05 | 2669 | 673.5389 | 1040 | 0.040647 | 14.1857 | 1294 |  | 3143
3291 | FRUITLAND 11426054 | 192311142 | FRUITLAND 1142 | 6054 | FALSE | 11579.672 | 11579.672 | 7.1968 | 58 | 0.00029784 | 132 | 184.0031 | 1677 | 0.040642 | 2.3572 | 1295 | 0.09 | 1573
2753 | CALPELLA 11011204 | 43411101 | CALPELLA 1101 | 1204 | FALSE | 18353.2445 | 15255.8356 | 9.4816 | 124 | 0.00012564 | 1084 | 378.7617 | 1322 | 0.040535 | 5.0263 | 1296 | 0.06 | 1888
6226 | FULTON 1107214 | 42561107 | FULTON 1107 | 214 | FALSE | 18868.3768 | 18868.3768 | 11.7268 | 142 | 0.0001516 | 725 | 205.0666 | 1626 | 0.040503 | 5.7514 | 1297 | 44.57 | 157
6297 | PEORIA 170176030 | 163781701 | PEORIA 1701 | 76030 | FALSE | 10072.8355 | 8222.4339 | 5.1103 | 55 | 9.557e-05 | 1739 | 498.7327 | 1202 | 0.040366 | 2.2201 | 1298 | 0.02 | 2538
4946 | WYANDOTTE 11031976 | 102911103 | WYANDOTTE 1103 | 1976 | FALSE | 38264.4277 | 38264.4277 | 23.7815 | 217 | 7.4462e-05 | 2346 | 572.7278 | 1128 | 0.040282 | 8.7412 | 1299 | 81.96 | 47
3803 | CALAVERAS CEMENT 1101CB | 162211101 | CALAVERAS CEMENT 1101 | CB | FALSE | 29408.7196 | 16846.5197 | 10.4702 | 203 | 0.00013798 | 894 | 318.5868 | 1420 | 0.040232 | 8.1671 | 1300 | 0.05 | 1952
601 | FORESTHILL 11022106 | 152181102 | FORESTHILL 1102 | 2106 | FALSE | 44861.5543 | 44861.5543 | 27.8816 | 264 | 0.00012115 | 1162 | 368.597 | 1341 | 0.040196 | 10.6117 | 1301 | 51.56 | 115
3937 | AUBERRY 1101176050 | 254151101 | AUBERRY 1101 | 176050 | FALSE | 33994.9384 | 33994.9384 | 21.128 | 168 | 3.5007e-05 | 3352 | 1021.4734 | 814 | 0.040157 | 6.7464 | 1302 |  | 2863
3563 | SHINGLE SPRINGS 21092053 | 153652109 | SHINGLE SPRINGS 2109 | 2053 | FALSE | 9238.0472 | 9238.0472 | 5.7415 | 74 | 7.8295e-05 | 2252 | 578.9534 | 1125 | 0.040131 | 2.9697 | 1303 | 18.91 | 317
639 | LAYTONVILLE 1101CB | 42681101 | LAYTONVILLE 1101 | CB | FALSE | 14777.824 | 9580.003 | 5.954 | 90 | 0.00019434 | 422 | 250.1874 | 1539 | 0.040116 | 3.6104 | 1304 | 6.07 | 474
8583 | UKIAH 1111168892 | 42771111 | UKIAH 1111 | 168892 | TRUE | 1078.2209 | 264.3207 | 0.16428 | 8 | 7.0494e-05 | 2456 | 277.1976 | 1478 | 0.040099 | 0.32079 | 1305 |  | 3240
6071 | SHINGLE SPRINGS 210981390 | 153652109 | SHINGLE SPRINGS 2109 | 81390 | FALSE | 29957.8137 | 29957.8137 | 18.6189 | 208 | 0.00014065 | 861 | 348.4797 | 1374 | 0.039915 | 8.3022 | 1306 | 0.15 | 1288
5271 | WILLITS 1104504 | 42661104 | WILLITS 1104 | 504 | FALSE | 36253.1832 | 36253.1832 | 22.5315 | 205 | 0.00010544 | 1509 | 471.8115 | 1221 | 0.039748 | 8.1484 | 1307 | 47.4 | 133
8156 | PIKE CITY 1102CB | 152201102 | PIKE CITY 1102 | CB | FALSE | 15315.8587 | 15315.8587 | 9.5189 | 44 | 0.00010811 | 1449 | 444.7581 | 1253 | 0.03956 | 1.7406 | 1308 | 15.25 | 349
1834 | CASTRO VALLEY 1110MR748 | 14091110 | CASTRO VALLEY 1110 | MR748 | FALSE | 10026.1125 | 10026.1125 | 6.2313 | 86 | 9.5898e-05 | 1731 | 353.7631 | 1368 | 0.039516 | 3.3984 | 1309 |  | 2749
4232 | GABILAN 1101989608 | 182331101 | GABILAN 1101 | 989608 | FALSE | 3673.9458 | 1209.612 | 0.75178 | 6 | 0.00015502 | 693 | 503.7259 | 1195 | 0.039513 | 0.23708 | 1310 |  | 2877
2029 | OCEANO 1102V56 | 182601102 | OCEANO 1102 | V56 | FALSE | 15985.6627 | 15022.8264 | 9.3367 | 115 | 6.4252e-05 | 2636 | 557.9025 | 1137 | 0.039442 | 4.5359 | 1311 | 0.1 | 1460
6282 | MOLINO 1101891 | 42571101 | MOLINO 1101 | 891 | FALSE | 5070.4899 | 5070.4899 | 3.1513 | 41 | 0.00012462 | 1104 | 268.5604 | 1501 | 0.03939 | 1.615 | 1312 | 2.7 | 588
7224 | MIRABEL 1101116 | 42091101 | MIRABEL 1101 | 116 | FALSE | 17433.6477 | 16625.8808 | 10.3331 | 112 | 0.00017861 | 515 | 262.5016 | 1515 | 0.039363 | 4.4087 | 1313 | 33.71 | 220
3752 | MONTE RIO 1113539938 | 42811113 | MONTE RIO 1113 | 539938 | FALSE | 4460.237 | 4460.237 | 2.7721 | 26 | 0.00021663 | 334 | 141.7664 | 1805 | 0.039354 | 1.0232 | 1314 |  | 2851
8901 | BRIDGEVILLE 110237486 | 192461102 | BRIDGEVILLE 1102 | 37486 | FALSE | 12199.5088 | 11162.2658 | 6.9374 | 85 | 0.00018807 | 454 | 224.247 | 1597 | 0.039237 | 3.3351 | 1315 | 0 | 2623
3640 | FROGTOWN 1702CB | 163451702 | FROGTOWN 1702 | CB | FALSE | 6932.7551 | 2351.3614 | 1.4614 | 47 | 0.00016197 | 622 | 176.7445 | 1692 | 0.039234 | 1.844 | 1316 | 0.02 | 2556
4627 | SAN LUIS OBISPO 1107V02 | 182631107 | SAN LUIS OBISPO 1107 | V02 | FALSE | 29266.1566 | 29266.1566 | 18.189 | 202 | 6.7472e-05 | 2550 | 602.2374 | 1099 | 0.039184 | 7.9151 | 1317 | 0.29 | 1026
2477 | CEDAR CREEK 11011656 | 103321101 | CEDAR CREEK 1101 | 1656 | FALSE | 51859.3271 | 51859.3271 | 32.2308 | 208 | 0.00010206 | 1602 | 466.1612 | 1228 | 0.039176 | 8.1485 | 1318 | 0.07 | 1727
6350 | NAPA 11121302 | 42021112 | NAPA 1112 | 1302 | FALSE | 55353.0299 | 32333.7369 | 20.0955 | 317 | 6.346e-05 | 2662 | 792.5298 | 949 | 0.039053 | 12.3798 | 1319 | 0.08 | 1620
798 | HIGGINS 1107CB | 152691107 | HIGGINS 1107 | CB | FALSE | 30614.8922 | 9216.7854 | 5.7283 | 243 | 0.00023355 | 268 | 176.6871 | 1693 | 0.03873 | 9.4114 | 1320 | 0.04 | 2075
10498 | CLAYTON 2212158138 | 12022212 | CLAYTON 2212 | 158138 | TRUE | 1490.1049 | 829.4376 | 0.5155 | 10 | 2.484e-05 | 3499 | 1008.6051 | 829 | 0.038704 | 0.38704 | 1321 |  | 3560
9150 | SPANISH CREEK 4401CB | 103104401 | SPANISH CREEK 4401 | CB | FALSE | 12760.2493 | 12447.7538 | 7.7363 | 22 | 0.00012371 | 1125 | 391.2799 | 1306 | 0.038702 | 0.85144 | 1322 | 6.72 | 462
561 | ALTO 11221260 | 42031122 | ALTO 1122 | 1260 | FALSE | 4901.8674 | 4807.0969 | 2.9876 | 36 | 0.00023996 | 246 | 168.4314 | 1724 | 0.038665 | 1.3919 | 1323 |  | 2682
2054 | PUEBLO 1104580658 | 43291104 | PUEBLO 1104 | 580658 | FALSE | 16767.5085 | 15111.3604 | 9.3918 | 107 | 6.1348e-05 | 2739 | 693.004 | 1027 | 0.038518 | 4.1214 | 1324 |  | 2759
3362 | REDBUD 110191960 | 43191101 | REDBUD 1101 | 91960 | FALSE | 11326.1042 | 10487.6883 | 6.5181 | 90 | 7.983e-05 | 2210 | 850.9359 | 913 | 0.038488 | 3.4639 | 1325 | 0.06 | 1880
3879 | WILLITS 11032506 | 42661103 | WILLITS 1103 | 2506 | FALSE | 20286.2385 | 20286.2385 | 12.608 | 89 | 0.00011138 | 1386 | 409.6677 | 1285 | 0.038425 | 3.4198 | 1326 | 0.12 | 1404
2472 | SANTA ROSA A 1104220 | 42151104 | SANTA ROSA A 1104 | 220 | FALSE | 15438.0154 | 15438.0154 | 9.5948 | 105 | 0.00011441 | 1309 | 311.3432 | 1429 | 0.038284 | 4.0198 | 1327 | 9.46 | 408
2655 | TEMPLETON 2110R90 | 183052110 | TEMPLETON 2110 | R90 | FALSE | 56951.1784 | 48580.6781 | 30.1931 | 259 | 6.3209e-05 | 2672 | 705.4586 | 1018 | 0.038279 | 9.9144 | 1328 | 0.16 | 1275
4442 | OCEANO 1104Q06 | 182601104 | OCEANO 1104 | Q06 | FALSE | 20064.3385 | 20064.3385 | 12.4701 | 154 | 5.9491e-05 | 2790 | 680.2301 | 1036 | 0.038111 | 5.8691 | 1329 | 0.24 | 1099
3161 | MARTELL 110368192 | 163011103 | MARTELL 1103 | 68192 | FALSE | 10168.9958 | 4402.6894 | 2.7363 | 72 | 0.00012081 | 1168 | 238.5636 | 1570 | 0.037972 | 2.734 | 1330 | 0.05 | 1932
7038 | MIRABEL 1102334 | 42091102 | MIRABEL 1102 | 334 | FALSE | 14855.8514 | 9584.4637 | 5.9568 | 84 | 0.00013014 | 1009 | 232.8142 | 1581 | 0.037896 | 3.1833 | 1331 | 0.12 | 1407
6568 | GEYSERVILLE 110137454 | 42891101 | GEYSERVILLE 1101 | 37454 | FALSE | 19681.6074 | 10482.9729 | 6.5152 | 114 | 0.00010014 | 1640 | 404.6575 | 1292 | 0.037721 | 4.3002 | 1332 | 0.03 | 2377
9085 | SAN LUIS OBISPO 1107V62 | 182631107 | SAN LUIS OBISPO 1107 | V62 | FALSE | 11154.8311 | 11108.5021 | 6.904 | 50 | 5.5981e-05 | 2890 | 671.7711 | 1042 | 0.037409 | 1.8704 | 1333 | 0.29 | 1023
3181 | SONOMA 110478372 | 42721104 | SONOMA 1104 | 78372 | FALSE | 27765.2096 | 26751.8084 | 16.6264 | 198 | 9.64e-05 | 1722 | 422.9319 | 1270 | 0.037304 | 7.3862 | 1334 | 0.18 | 1212
296 | TASSAJARA 2112D514R | 14662112 | TASSAJARA 2112 | D514R | FALSE | 7698.3807 | 5032.0091 | 3.1274 | 73 | 0.00011281 | 1348 | 304.6429 | 1441 | 0.037278 | 2.7213 | 1335 | 0.15 | 1282
5732 | SWIFT 2107XR526 | 83392107 | SWIFT 2107 | XR526 | FALSE | 8725.9018 | 3365.6589 | 2.0918 | 64 | 8.9522e-05 | 1929 | 366.774 | 1343 | 0.037122 | 2.3758 | 1336 | 0.07 | 1699
4671 | PURISIMA 1101Y42 | 182971101 | PURISIMA 1101 | Y42 | FALSE | 26985.4956 | 5628.4599 | 3.4981 | 127 | 5.2153e-05 | 2990 | 480.936 | 1215 | 0.037118 | 4.714 | 1337 | 0.03 | 2346
7642 | PENRYN 1105168616 | 152561105 | PENRYN 1105 | 168616 | FALSE | 13634.7639 | 5078.9905 | 3.1566 | 102 | 0.00012703 | 1064 | 319.4815 | 1417 | 0.03705 | 3.7791 | 1338 |  | 3144
2287 | OCEANO 1104104102 | 182601104 | OCEANO 1104 | 104102 | FALSE | 5954.6843 | 5329.5584 | 3.3123 | 32 | 7.2705e-05 | 2398 | 458.1953 | 1237 | 0.03704 | 1.1853 | 1339 |  | 2769
9499 | OILFIELDS 1103N46 | 182391103 | OILFIELDS 1103 | N46 | FALSE | 9360.6261 | 9360.6261 | 5.8177 | 29 | 8.7946e-05 | 1983 | 551.9562 | 1142 | 0.036988 | 1.0726 | 1340 | 4.74 | 508
5619 | NARROWS 21052426 | 153132105 | NARROWS 2105 | 2426 | FALSE | 27934.4989 | 13782.7728 | 8.566 | 226 | 0.00017076 | 559 | 240.3744 | 1566 | 0.036874 | 8.3335 | 1341 | 0.09 | 1513
3889 | RINCON 1103474 | 43321103 | RINCON 1103 | 474 | FALSE | 29501.1448 | 29501.1448 | 18.3351 | 174 | 9.7853e-05 | 1695 | 328.9251 | 1399 | 0.036813 | 6.4055 | 1342 | 75.79 | 56
6070 | CRESCENT MILLS 21012230 | 103132101 | CRESCENT MILLS 2101 | 2230 | FALSE | 17863.1589 | 10972.6709 | 6.8196 | 112 | 5.685e-05 | 2866 | 738.5033 | 984 | 0.036587 | 4.0978 | 1343 | 1.14 | 710
7395 | HALF MOON BAY 11018902 | 24101101 | HALF MOON BAY 1101 | 8902 | FALSE | 29281.8886 | 22787.1296 | 14.1623 | 145 | 9.4843e-05 | 1771 | 290.9381 | 1462 | 0.036496 | 5.2919 | 1344 | 0.33 | 986
8155 | PIT NO 5 11011606 | 101321101 | PIT NO 5 1101 | 1606 | FALSE | 8892.9459 | 8892.9459 | 5.527 | 40 | 0.00014678 | 776 | 232.8508 | 1580 | 0.036482 | 1.4593 | 1345 | 0.01 | 2612
6340 | ELECTRA 11011238 | 162161101 | ELECTRA 1101 | 1238 | FALSE | 11344.0767 | 5824.674 | 3.6201 | 81 | 0.00010773 | 1458 | 597.355 | 1103 | 0.036431 | 2.9509 | 1346 | 1.29 | 689
988 | FROGTOWN 1701CB | 163451701 | FROGTOWN 1701 | CB | FALSE | 18045.0473 | 16189.7881 | 10.062 | 76 | 0.00014573 | 792 | 355.2175 | 1365 | 0.036334 | 2.7614 | 1347 | 0.04 | 2159
6703 | POTTER VALLEY P H 110576498 | 42281105 | POTTER VALLEY P H 1105 | 76498 | FALSE | 23942.9529 | 23942.9529 | 14.8806 | 119 | 0.00014996 | 736 | 219.4832 | 1606 | 0.036331 | 4.3234 | 1348 | 0.07 | 1718
10138 | LLAGAS 2107870396 | 83182107 | LLAGAS 2107 | 870396 | FALSE | 4752.0973 | 1326.4884 | 0.82442 | 40 | 7.7997e-05 | 2259 | 529.8735 | 1173 | 0.036327 | 1.4531 | 1349 |  | 3499
7528 | LAYTONVILLE 110189606 | 42681101 | LAYTONVILLE 1101 | 89606 | FALSE | 19260.5468 | 18716.1946 | 11.6322 | 100 | 0.00018082 | 506 | 280.3009 | 1471 | 0.036226 | 3.6226 | 1350 | 2.6 | 595
1489 | CURTIS 1702CB | 163351702 | CURTIS 1702 | CB | FALSE | 36887.0265 | 35506.5152 | 22.0674 | 293 | 0.00013284 | 960 | 388.0347 | 1309 | 0.036175 | 10.5993 | 1351 | 0.18 | 1199
3159 | SALMON CREEK 1101194 | 43161101 | SALMON CREEK 1101 | 194 | FALSE | 13676.557 | 10907.7439 | 6.7792 | 62 | 5.7737e-05 | 2843 | 536.066 | 1162 | 0.03614 | 2.2407 | 1352 | 0.13 | 1363
5649 | MORGAN HILL 2111XR186 | 83242111 | MORGAN HILL 2111 | XR186 | FALSE | 25721.3505 | 4651.2538 | 2.8908 | 191 | 7.0623e-05 | 2453 | 451.6726 | 1246 | 0.036035 | 6.8827 | 1353 | 0.23 | 1109
972 | BRUNSWICK 11062392 | 152481106 | BRUNSWICK 1106 | 2392 | FALSE | 14284.081 | 9811.7074 | 6.098 | 111 | 0.0001898 | 442 | 159.9243 | 1747 | 0.036 | 3.996 | 1354 |  | 2700
4961 | TEMPLETON 2110R94 | 183052110 | TEMPLETON 2110 | R94 | FALSE | 33827.9009 | 22380.6586 | 13.9097 | 179 | 5.5341e-05 | 2903 | 687.195 | 1033 | 0.035946 | 6.4343 | 1355 | 0.08 | 1614
2592 | CAYUCOS 11014701 | 182551101 | CAYUCOS 1101 | 4701 | FALSE | 14095.9599 | 3388.7478 | 2.1061 | 65 | 6.2737e-05 | 2693 | 533.9217 | 1166 | 0.035932 | 2.3356 | 1356 | 0.03 | 2301
160 | MOUNTAIN QUARRIES 21011346 | 152282101 | MOUNTAIN QUARRIES 2101 | 1346 | FALSE | 49591.6622 | 49591.6622 | 30.8214 | 410 | 0.00012199 | 1148 | 241.2851 | 1564 | 0.035841 | 14.6948 | 1357 | 0.17 | 1232
3187 | SAN MIGUEL 1104R58 | 182661104 | SAN MIGUEL 1104 | R58 | TRUE | 19359.8745 | 870.4973 | 0.54102 | 130 | 8.6053e-05 | 2033 | 466.191 | 1227 | 0.035811 | 4.6554 | 1358 | 0.03 | 2357
8179 | LOS OSITOS 21037062 | 182082103 | LOS OSITOS 2103 | 7062 | FALSE | 19664.1429 | 19664.1429 | 12.2213 | 53 | 5.2216e-05 | 2986 | 685.2904 | 1034 | 0.035805 | 1.8977 | 1359 | 0.1 | 1452
7911 | OAKLAND K 110217430 | 12101102 | OAKLAND K 1102 | 17430 | FALSE | 2364.8217 | 2364.8217 | 1.4697 | 15 | 0.00011951 | 1195 | 247.4437 | 1547 | 0.035767 | 0.5365 | 1360 | 32.76 | 224
88 | SILVERADO 2105658898 | 43432105 | SILVERADO 2105 | 658898 | FALSE | 27632.4579 | 27632.4579 | 17.1737 | 151 | 0.00015549 | 689 | 248.309 | 1546 | 0.035763 | 5.4002 | 1361 | 57.88 | 94
2757 | BURNEY 11011358 | 103311101 | BURNEY 1101 | 1358 | FALSE | 15167.5785 | 13566.1241 | 8.4314 | 51 | 5.9055e-05 | 2804 | 689.2289 | 1031 | 0.035574 | 1.8143 | 1362 | 0.06 | 1890
2335 | PLACERVILLE 21067522 | 153082106 | PLACERVILLE 2106 | 7522 | FALSE | 108391.3301 | 108391.3301 | 67.3656 | 745 | 0.00012077 | 1170 | 356.6073 | 1360 | 0.035529 | 26.4689 | 1363 | 0.39 | 959
10054 | GARBERVILLE 110197300 | 192221101 | GARBERVILLE 1101 | 97300 | FALSE | 5161.3802 | 5161.3802 | 3.2078 | 32 | 0.00052613 | 28 | 106.2466 | 1924 | 0.035439 | 1.1341 | 1364 | 0 | 2624
2680 | SAN RAMON 2107MR284 | 14232107 | SAN RAMON 2107 | MR284 | FALSE | 24162.974 | 23633.8875 | 14.6886 | 134 | 7.4599e-05 | 2342 | 581.0664 | 1123 | 0.035373 | 4.7399 | 1365 | 0.73 | 795
6323 | FORT ROSS 112170288 | 42851121 | FORT ROSS 1121 | 70288 | FALSE | 18879.7984 | 18879.7984 | 11.7339 | 94 | 0.00019388 | 426 | 228.6007 | 1590 | 0.035369 | 3.3247 | 1366 | 36.18 | 207
4070 | CLAYTON 2213CB | 12022213 | CLAYTON 2213 | CB | FALSE | 9981.732 | 6230.9216 | 3.8725 | 51 | 2.7369e-05 | 3466 | 650.8554 | 1065 | 0.03535 | 1.8029 | 1367 |  | 2870
5947 | GARCIA 0401666 | 43040401 | GARCIA 0401 | 666 | FALSE | 3872.5577 | 3872.5577 | 2.4068 | 12 | 9.2943e-05 | 1825 | 378.2419 | 1323 | 0.035311 | 0.42373 | 1368 | 4.95 | 500
8699 | UKIAH 1113548420 | 42771113 | UKIAH 1113 | 548420 | FALSE | 8380.7958 | 8369.7684 | 5.2018 | 54 | 8.6035e-05 | 2034 | 589.6218 | 1114 | 0.035261 | 1.9041 | 1369 |  | 3251
7081 | NOVATO 110455398 | 42211104 | NOVATO 1104 | 55398 | FALSE | 18355.8501 | 5879.4418 | 3.6541 | 82 | 9.9295e-05 | 1661 | 371.6607 | 1336 | 0.035221 | 2.8881 | 1370 | 0.05 | 2019
2938 | PETALUMA C 110948000 | 42631109 | PETALUMA C 1109 | 48000 | FALSE | 21345.6496 | 15284.0145 | 9.4991 | 115 | 8.6887e-05 | 2015 | 388.2741 | 1308 | 0.035167 | 4.0442 | 1371 | 0.07 | 1767
9847 | PENRYN 1105CB | 152561105 | PENRYN 1105 | CB | TRUE | 1663.8056 | 978.5043 | 0.60814 | 7 | 0.00029336 | 136 | 117.5975 | 1884 | 0.035133 | 0.24593 | 1372 | 0.22 | 1130
1921 | WYANDOTTE 110641650 | 102911106 | WYANDOTTE 1106 | 41650 | FALSE | 26091.6846 | 1862.3816 | 1.1575 | 152 | 9.0143e-05 | 1906 | 368.6652 | 1340 | 0.035126 | 5.3392 | 1373 | 1.15 | 706
7481 | OTTER 11012052 | 182941101 | OTTER 1101 | 2052 | FALSE | 7781.6967 | 7781.6967 | 4.8364 | 53 | 0.00010975 | 1416 | 342.2139 | 1385 | 0.034981 | 1.854 | 1374 | 16.17 | 340
3295 | REDBUD 1102510 | 43191102 | REDBUD 1102 | 510 | FALSE | 13083.2788 | 6767.6989 | 4.2062 | 101 | 7.5461e-05 | 2323 | 619.5024 | 1082 | 0.03495 | 3.5299 | 1375 | 0.06 | 1875
4887 | WOODSIDE 11018972 | 24251101 | WOODSIDE 1101 | 8972 | FALSE | 10000.1577 | 10000.1577 | 6.2151 | 60 | 0.00015146 | 726 | 262.3952 | 1516 | 0.034933 | 2.096 | 1376 | 24.19 | 280
9433 | JAMESON 11028842 | 63801102 | JAMESON 1102 | 8842 | TRUE | 4786.8365 | 241.1115 | 0.14985 | 42 | 6.9889e-05 | 2476 | 340.0317 | 1387 | 0.03478 | 1.4608 | 1377 | 1.42 | 678
5225 | SHADY GLEN 110248894 | 152431102 | SHADY GLEN 1102 | 48894 | FALSE | 16156.7591 | 14293.1803 | 8.8833 | 119 | 0.00018242 | 493 | 147.0551 | 1786 | 0.034658 | 4.1244 | 1378 | 4.42 | 518
4594 | WEIMAR 11012058 | 152491101 | WEIMAR 1101 | 2058 | FALSE | 34315.2065 | 34315.2065 | 21.327 | 256 | 0.00016588 | 583 | 212.3054 | 1613 | 0.034582 | 8.853 | 1379 | 0.1 | 1472
10315 | CLAYTON 2212523764 | 12022212 | CLAYTON 2212 | 523764 | TRUE | 581.2133 | 177.5745 | 0.11036 | 5 | 5.3526e-05 | 2949 | 454.5614 | 1241 | 0.034478 | 0.17239 | 1380 |  | 3531
4872 | SUNOL 1101MR196 | 14241101 | SUNOL 1101 | MR196 | FALSE | 21187.4678 | 6333.1478 | 3.9361 | 96 | 5.2612e-05 | 2979 | 626.9753 | 1078 | 0.034417 | 3.304 | 1381 | 0.62 | 842
1388 | MIWUK 170193062 | 163661701 | MIWUK 1701 | 93062 | FALSE | 13326.2559 | 13326.2559 | 8.2823 | 84 | 5.3764e-05 | 2946 | 519.6534 | 1183 | 0.034301 | 2.8813 | 1382 | 47.16 | 137
10333 | SAN ARDO 1101650772 | 182191101 | SAN ARDO 1101 | 650772 | FALSE | 4368.3364 | 1261.3702 | 0.78395 | 10 | 8.4256e-05 | 2083 | 361.8664 | 1350 | 0.03426 | 0.3426 | 1383 |  | 3534
132 | APPLE HILL 1103CB | 153661103 | APPLE HILL 1103 | CB | FALSE | 36721.9242 | 31128.549 | 19.3465 | 268 | 0.00025192 | 213 | 162.0895 | 1742 | 0.034245 | 9.1777 | 1384 | 0.18 | 1200
7451 | LOW GAP 1101CB | 192411101 | LOW GAP 1101 | CB | FALSE | 3490.2509 | 3490.2509 | 2.1692 | 23 | 0.00020947 | 361 | 222.197 | 1600 | 0.034029 | 0.78267 | 1385 | 9.67 | 405
10038 | JESSUP 110194468 | 103441101 | JESSUP 1101 | 94468 | FALSE | 2757.0604 | 2757.0604 | 1.7135 | 21 | 6.6616e-05 | 2567 | 514.9233 | 1187 | 0.033993 | 0.71385 | 1386 |  | 3480
3608 | PIT NO 1 11011552 | 103721101 | PIT NO 1 1101 | 1552 | FALSE | 42573.1939 | 23841.5992 | 14.8177 | 221 | 3.5304e-05 | 3346 | 839.4452 | 917 | 0.033912 | 7.4946 | 1387 | 0.02 | 2427
5359 | SAN LUIS OBISPO 1104CB | 182631104 | SAN LUIS OBISPO 1104 | CB | TRUE | 10585.951 | 124.2488 | 0.077221 | 65 | 0.00011177 | 1373 | 315.2576 | 1425 | 0.033863 | 2.2011 | 1388 | 0.02 | 2451
9613 | REEDLEY 1112477952 | 252341112 | REEDLEY 1112 | 477952 | TRUE | 2593.1423 | 282.8465 | 0.17579 | 14 | 3.3616e-05 | 3374 | 2064.1113 | 439 | 0.033843 | 0.47381 | 1389 |  | 3390
6901 | JESSUP 11019752 | 103441101 | JESSUP 1101 | 9752 | FALSE | 6185.1828 | 6137.4536 | 3.8145 | 41 | 8.5187e-05 | 2053 | 359.3768 | 1357 | 0.033837 | 1.3873 | 1390 | 0.08 | 1592
8898 | RACETRACK 17036014 | 163761703 | RACETRACK 1703 | 6014 | FALSE | 11167.2532 | 11167.2532 | 6.9405 | 73 | 0.00012645 | 1075 | 322.1745 | 1410 | 0.033829 | 2.4695 | 1391 | 0.11 | 1416
7674 | LLAGAS 21011451 | 83182101 | LLAGAS 2101 | 1451 | FALSE | 14799.0551 | 9963.2757 | 6.1922 | 61 | 7.7841e-05 | 2264 | 590.7109 | 1112 | 0.03381 | 2.0624 | 1392 | 0.07 | 1693
5880 | POINT MORETTI 11015076 | 82931101 | POINT MORETTI 1101 | 5076 | FALSE | 14477.3637 | 12059.1468 | 7.4948 | 67 | 0.00010771 | 1459 | 265.797 | 1508 | 0.033758 | 2.2618 | 1393 | 0.04 | 2127
8948 | CLARKSVILLE 2109102734 | 153612109 | CLARKSVILLE 2109 | 102734 | TRUE | 954.1374 | 954.1374 | 0.593 | 7 | 8.9773e-05 | 1919 | 197.0875 | 1650 | 0.033754 | 0.23628 | 1394 |  | 3280
10958 | CURTIS 170511790 | 163351705 | CURTIS 1705 | 11790 | TRUE | 22.8988 | 22.8988 | 0.014232 | 1 | 0.00070892 | 7 | 47.5828 | 2227 | 0.033732 | 0.033732 | 1395 | 0.2 | 1164
10247 | MILPITAS 1108342498 | 82831108 | MILPITAS 1108 | 342498 | TRUE | 1151.7336 | 49.0072 | 0.030458 | 9 | 7.9908e-05 | 2207 | 500.2762 | 1198 | 0.033722 | 0.3035 | 1396 |  | 3521
5434 | MADISON 1105495270 | 63171105 | MADISON 1105 | 495270 | TRUE | 13307.7021 | 863.3194 | 0.53656 | 50 | 9.0841e-05 | 1888 | 589.9667 | 1113 | 0.033688 | 1.6844 | 1397 |  | 2953
5420 | PETALUMA C 1108600 | 42631108 | PETALUMA C 1108 | 600 | FALSE | 11716.5391 | 5966.5276 | 3.7082 | 107 | 8.5491e-05 | 2040 | 380.66 | 1319 | 0.033514 | 3.586 | 1398 | 2.36 | 611
5203 | HALSEY 11012414 | 152241101 | HALSEY 1101 | 2414 | FALSE | 23793.415 | 23793.415 | 14.7877 | 168 | 0.00014567 | 794 | 312.3629 | 1427 | 0.033489 | 5.6261 | 1399 | 0.1 | 1503
322 | PIKE CITY 11011730 | 152201101 | PIKE CITY 1101 | 1730 | FALSE | 13645.4759 | 13645.4759 | 8.4807 | 73 | 0.00014065 | 860 | 278.461 | 1475 | 0.033438 | 2.441 | 1400 | 45.96 | 146
5994 | RED BLUFF 11011334 | 103541101 | RED BLUFF 1101 | 1334 | FALSE | 25612.9912 | 2886.1165 | 1.7937 | 155 | 6.0867e-05 | 2753 | 682.7098 | 1035 | 0.033359 | 5.1706 | 1401 | 1.21 | 700
3212 | HALF MOON BAY 1103H82 | 24101103 | HALF MOON BAY 1103 | H82 | FALSE | 58651.4755 | 52489.3402 | 32.6223 | 262 | 9.3414e-05 | 1811 | 388.9088 | 1307 | 0.033242 | 8.7095 | 1402 | 0.77 | 782
1462 | GIRVAN 11029012 | 103401102 | GIRVAN 1102 | 9012 | FALSE | 25166.2142 | 25166.2142 | 15.6409 | 176 | 0.00013267 | 966 | 372.3651 | 1335 | 0.033219 | 5.8466 | 1403 | 0.42 | 934
10706 | GONZALES 1104807000 | 182131104 | GONZALES 1104 | 807000 | FALSE | 1709.8584 | 1354.2941 | 0.8417 | 7 | 3.235e-05 | 3394 | 880.4035 | 891 | 0.033203 | 0.23242 | 1404 |  | 3594
5652 | CORRAL 110214028 | 162991102 | CORRAL 1102 | 14028 | FALSE | 12751.8037 | 6133.5417 | 3.812 | 103 | 0.00010822 | 1447 | 214.1406 | 1611 | 0.033074 | 3.4066 | 1405 | 0.04 | 2224
7408 | KANAKA 11011044 | 103221101 | KANAKA 1101 | 1044 | FALSE | 9889.843 | 9889.843 | 6.1466 | 17 | 0.00010748 | 1465 | 324.5037 | 1407 | 0.033036 | 0.56161 | 1406 | 18.93 | 316
2114 | WYANDOTTE 11091040 | 102911109 | WYANDOTTE 1109 | 1040 | FALSE | 9753.1063 | 1682.9824 | 1.046 | 62 | 0.00011564 | 1281 | 448.3969 | 1250 | 0.032999 | 2.0459 | 1407 | 0.73 | 796
9307 | LINCOLN 11012310 | 153701101 | LINCOLN 1101 | 2310 | FALSE | 4180.455 | 1304.6994 | 0.81088 | 34 | 0.00013671 | 911 | 509.3332 | 1192 | 0.032911 | 1.119 | 1408 | 0.05 | 1962
4870 | BEAR VALLEY 2101CB | 252192101 | BEAR VALLEY 2101 | CB | FALSE | 30214.013 | 30214.013 | 18.7781 | 154 | 0.00013214 | 980 | 326.6135 | 1403 | 0.03289 | 5.065 | 1409 | 0.04 | 2085
3833 | APPLE HILL 110412832 | 153661104 | APPLE HILL 1104 | 12832 | FALSE | 24421.2649 | 23234.3604 | 14.4402 | 166 | 0.00017093 | 557 | 211.8635 | 1615 | 0.032787 | 5.4427 | 1410 | 28.99 | 245
10090 | TIVY VALLEY 1107599142 | 252941107 | TIVY VALLEY 1107 | 599142 | TRUE | 3668.6338 | 573.3105 | 0.35631 | 19 | 2.2881e-05 | 3512 | 2022.5531 | 452 | 0.03274 | 0.62205 | 1411 |  | 3488
2297 | STANISLAUS 17011812 | 162821701 | STANISLAUS 1701 | 1812 | FALSE | 30912.6745 | 30912.6745 | 19.2124 | 234 | 0.0001396 | 878 | 157.2117 | 1758 | 0.032657 | 7.6418 | 1412 | 0.91 | 748
8485 | HOLLISTER 2102113634 | 182492102 | HOLLISTER 2102 | 113634 | FALSE | 13932.988 | 2941.0752 | 1.8279 | 76 | 7.4759e-05 | 2338 | 364.1214 | 1346 | 0.032654 | 2.4817 | 1413 |  | 3229
7193 | ELECTRA 1102CB | 162161102 | ELECTRA 1102 | CB | FALSE | 4270.3268 | 4270.3268 | 2.654 | 7 | 0.000239 | 249 | 194.5881 | 1655 | 0.032515 | 0.22761 | 1414 | 0.03 | 2354
5731 | PLACERVILLE 21062224 | 153082106 | PLACERVILLE 2106 | 2224 | FALSE | 16910.6519 | 16910.6519 | 10.51 | 123 | 0.00022231 | 310 | 204.3067 | 1631 | 0.032512 | 3.999 | 1415 | 31.55 | 229
4312 | MENDOCINO 110137462 | 42951101 | MENDOCINO 1101 | 37462 | FALSE | 7845.6326 | 3795.803 | 2.3591 | 63 | 0.00014083 | 857 | 230.0252 | 1586 | 0.032457 | 2.0448 | 1416 | 0.04 | 2166
8959 | OLETA 1101894006 | 163541101 | OLETA 1101 | 894006 | TRUE | 1042.8451 | 627.9545 | 0.39028 | 8 | 7.1494e-05 | 2432 | 670.4008 | 1043 | 0.03239 | 0.25912 | 1417 |  | 3282
4513 | SAN LUIS OBISPO 1104V14 | 182631104 | SAN LUIS OBISPO 1104 | V14 | FALSE | 13117.1277 | 13103.4117 | 8.1438 | 69 | 5.3161e-05 | 2961 | 462.6018 | 1233 | 0.03238 | 2.2342 | 1418 | 0.07 | 1714
4357 | APPLE HILL 11038412 | 153661103 | APPLE HILL 1103 | 8412 | FALSE | 31508.6751 | 31508.6751 | 19.5828 | 201 | 0.00012406 | 1118 | 308.2082 | 1435 | 0.032352 | 6.5027 | 1419 | 0.24 | 1093
2717 | JOLON 11027002 | 182981102 | JOLON 1102 | 7002 | FALSE | 29669.7133 | 13447.6997 | 8.3578 | 117 | 6.5838e-05 | 2591 | 548.8506 | 1147 | 0.032323 | 3.7818 | 1420 | 0.03 | 2407
5768 | BIG BASIN 110210254 | 82841102 | BIG BASIN 1102 | 10254 | FALSE | 3449.8351 | 3449.8351 | 2.1441 | 11 | 0.00025218 | 212 | 138.3979 | 1814 | 0.03232 | 0.35552 | 1421 | 0.29 | 1030
5734 | APPLE HILL 1104CB | 153661104 | APPLE HILL 1104 | CB | FALSE | 6578.3972 | 6578.3972 | 4.0885 | 51 | 0.00035059 | 89 | 89.0767 | 2007 | 0.032289 | 1.6467 | 1422 | 4 | 530
7601 | JARVIS 1111907698 | 13501111 | JARVIS 1111 | 907698 | FALSE | 3034.3117 | 2466.4182 | 1.5329 | 14 | 0.00012445 | 1111 | 261.4537 | 1520 | 0.03225 | 0.4515 | 1423 |  | 3140
7801 | HALF MOON BAY 11012500 | 24101101 | HALF MOON BAY 1101 | 2500 | FALSE | 11167.0911 | 10490.7768 | 6.5201 | 74 | 0.00015128 | 727 | 218.7989 | 1608 | 0.032243 | 2.3859 | 1424 | 57.37 | 96
4135 | BRUNSWICK 11041020 | 152481104 | BRUNSWICK 1104 | 1020 | FALSE | 46299.321 | 46299.321 | 28.7752 | 311 | 9.6344e-05 | 1725 | 368.887 | 1339 | 0.032187 | 10.0103 | 1425 | 69 | 71
7772 | FRUITLAND 11422006 | 192311142 | FRUITLAND 1142 | 2006 | FALSE | 14941.7424 | 13398.0902 | 8.327 | 75 | 0.00034661 | 94 | 97.9891 | 1968 | 0.03216 | 2.412 | 1426 | 0.09 | 1508
10311 | MADISON 2101760730 | 63172101 | MADISON 2101 | 760730 | TRUE | 4317.2275 | 964.21 | 0.59926 | 17 | 7.566e-05 | 2318 | 407.7093 | 1289 | 0.032096 | 0.54562 | 1427 |  | 3530
1525 | CHALLENGE 11025462 | 103201102 | CHALLENGE 1102 | 5462 | FALSE | 37447.0905 | 37447.0905 | 23.2735 | 248 | 0.00016384 | 602 | 227.1186 | 1593 | 0.032082 | 7.9564 | 1428 | 37.76 | 199
7510 | FRUITLAND 114263170 | 192311142 | FRUITLAND 1142 | 63170 | FALSE | 21717.2784 | 20031.3406 | 12.4496 | 86 | 0.00032558 | 106 | 126.7281 | 1853 | 0.031951 | 2.7478 | 1429 | 0.11 | 1410
8635 | MOLINO 11026917 | 42571102 | MOLINO 1102 | 6917 | FALSE | 11229.1017 | 11229.1017 | 6.9789 | 58 | 0.00011705 | 1246 | 334.9674 | 1393 | 0.031941 | 1.8526 | 1430 | 28.69 | 248
5301 | REEDLEY 1104887932 | 252341104 | REEDLEY 1104 | 887932 | FALSE | 7830.582 | 2732.0868 | 1.698 | 34 | 3.8049e-05 | 3299 | 1172.2774 | 745 | 0.031896 | 1.0845 | 1431 |  | 2945
8600 | CALPELLA 1101619542 | 43411101 | CALPELLA 1101 | 619542 | FALSE | 2424.259 | 2408.2569 | 1.4967 | 21 | 0.00013244 | 972 | 252.7945 | 1536 | 0.031874 | 0.66935 | 1432 |  | 3241
145 | MOUNTAIN QUARRIES 21011130 | 152282101 | MOUNTAIN QUARRIES 2101 | 1130 | FALSE | 32234.9294 | 32234.9294 | 20.0341 | 231 | 8.1217e-05 | 2177 | 401.3828 | 1295 | 0.031834 | 7.3538 | 1433 | 0.19 | 1198
8867 | FORESTHILL 110137238 | 152181101 | FORESTHILL 1101 | 37238 | FALSE | 18384.2813 | 18384.2813 | 11.4259 | 79 | 9.076e-05 | 1890 | 274.1817 | 1485 | 0.031693 | 2.5038 | 1434 | 39.57 | 188
10121 | COARSEGOLD 210210610 | 254432102 | COARSEGOLD 2102 | 10610 | FALSE | 2196.7777 | 2196.7777 | 1.3653 | 22 | 7.4106e-05 | 2354 | 439.5957 | 1256 | 0.031595 | 0.6951 | 1435 | 0.3 | 1012
8481 | PERRY 110185870 | 183071101 | PERRY 1101 | 85870 | FALSE | 27055.9571 | 18409.1169 | 11.4413 | 109 | 5.897e-05 | 2807 | 581.2408 | 1122 | 0.031502 | 3.4337 | 1436 | 0.05 | 1923
3885 | BELLEVUE 2103478 | 43182103 | BELLEVUE 2103 | 478 | FALSE | 32233.0286 | 13396.6859 | 8.3261 | 213 | 9.7957e-05 | 1693 | 387.6512 | 1310 | 0.031296 | 6.6661 | 1437 | 6.33 | 468
1942 | UKIAH 1113CB | 42771113 | UKIAH 1113 | CB | TRUE | 9680.979 | 75.4379 | 0.046885 | 69 | 8.4474e-05 | 2078 | 195.8633 | 1653 | 0.031266 | 2.1574 | 1438 | 3.69 | 536
10742 | GEYSERVILLE 1101463260 | 42891101 | GEYSERVILLE 1101 | 463260 | TRUE | 886.169 | 873.7132 | 0.54302 | 6 | 9.5911e-05 | 1730 | 333.1332 | 1394 | 0.031168 | 0.18701 | 1439 |  | 3601
8417 | CURTIS 1703CB | 163351703 | CURTIS 1703 | CB | FALSE | 17669.2412 | 14555.9213 | 9.0466 | 119 | 0.00013143 | 990 | 316.505 | 1422 | 0.031137 | 3.7053 | 1440 | 0.06 | 1894
1279 | ORO FINO 11022556 | 103031102 | ORO FINO 1102 | 2556 | FALSE | 10719.4797 | 10719.4797 | 6.6622 | 41 | 0.00022017 | 320 | 170.5273 | 1713 | 0.031032 | 1.2723 | 1441 | 40.37 | 184
1200 | OCEANO 1106CB | 182601106 | OCEANO 1106 | CB | FALSE | 7207.9497 | 1811.9234 | 1.1261 | 57 | 3.6174e-05 | 3330 | 275.7036 | 1484 | 0.03103 | 1.7687 | 1442 | 0.02 | 2494
766 | SISQUOC 1103M98 | 182811103 | SISQUOC 1103 | M98 | FALSE | 15843.0204 | 12614.6664 | 7.8401 | 56 | 2.6579e-05 | 3477 | 870.0926 | 898 | 0.030988 | 1.7353 | 1443 | 0.06 | 1829
8592 | STELLING 11109265 | 83481110 | STELLING 1110 | 9265 | FALSE | 8915.672 | 8915.672 | 5.5411 | 45 | 9.8e-05 | 1691 | 342.4629 | 1384 | 0.03098 | 1.3941 | 1444 | 0.08 | 1605
5933 | MIRABEL 1102524356 | 42091102 | MIRABEL 1102 | 524356 | FALSE | 4107.6805 | 2088.1166 | 1.2978 | 29 | 0.00010421 | 1547 | 511.0846 | 1190 | 0.030872 | 0.89528 | 1445 |  | 2991
802 | ALLEGHANY 1101806 | 152101101 | ALLEGHANY 1101 | 806 | FALSE | 18143.3915 | 18143.3915 | 11.2762 | 65 | 0.00012168 | 1154 | 338.7274 | 1390 | 0.030867 | 2.0063 | 1446 | 48.53 | 127
1506 | GARBERVILLE 11011750 | 192221101 | GARBERVILLE 1101 | 1750 | FALSE | 13589.0424 | 13584.4704 | 8.4428 | 62 | 0.00032404 | 108 | 98.8868 | 1959 | 0.030822 | 1.911 | 1447 | 0.13 | 1338
4004 | COARSEGOLD 21025380 | 254432102 | COARSEGOLD 2102 | 5380 | FALSE | 22971.0374 | 22971.0374 | 14.2766 | 143 | 7.8304e-05 | 2250 | 414.5903 | 1278 | 0.030806 | 4.4053 | 1448 | 0.46 | 911
1308 | RINCON 1101578 | 43321101 | RINCON 1101 | 578 | FALSE | 29556.6676 | 27517.4977 | 17.1022 | 170 | 8.7604e-05 | 1997 | 393.466 | 1303 | 0.030756 | 5.2285 | 1449 | 37.08 | 203
10309 | BOLINAS 1101806 | 42261101 | BOLINAS 1101 | 806 | FALSE | 4898.4533 | 4898.4533 | 3.0444 | 17 | 0.00027974 | 154 | 135.7877 | 1828 | 0.030667 | 0.52134 | 1450 | 0.55 | 868
6983 | BASALT 1106657038 | 42461106 | BASALT 1106 | 657038 | FALSE | 16275.5331 | 4182.6167 | 2.5995 | 72 | 4.9064e-05 | 3062 | 415.5682 | 1276 | 0.030657 | 2.2073 | 1451 |  | 3078
3194 | DIAMOND SPRINGS 1103467046 | 152261103 | DIAMOND SPRINGS 1103 | 467046 | FALSE | 34550.7467 | 24654.328 | 15.3228 | 266 | 0.00018345 | 482 | 166.8005 | 1729 | 0.030581 | 8.1346 | 1452 |  | 2816
4703 | WISE 1101CB | 152271101 | WISE 1101 | CB | FALSE | 14435.5526 | 7662.7202 | 4.7624 | 112 | 0.00015887 | 652 | 243.3221 | 1558 | 0.030561 | 3.4229 | 1453 | 0.05 | 2032
6843 | DUNBAR 11033127 | 43071103 | DUNBAR 1103 | 3127 | FALSE | 15418.4131 | 15054.5807 | 9.3565 | 78 | 0.00010691 | 1479 | 266.083 | 1507 | 0.030422 | 2.3729 | 1454 | 0.62 | 840
3373 | VOLTA 11021646 | 102541102 | VOLTA 1102 | 1646 | FALSE | 38843.3191 | 38535.0265 | 23.9497 | 215 | 6.2043e-05 | 2718 | 560.4541 | 1133 | 0.030417 | 6.5396 | 1455 | 13.62 | 364
9167 | WILDWOOD 1101CB | 103611101 | WILDWOOD 1101 | CB | TRUE | 200.8618 | 200.8618 | 0.12484 | 2 | 9.0416e-05 | 1899 | 309.1042 | 1433 | 0.030413 | 0.060827 | 1456 | 0.72 | 797
1377 | FROGTOWN 170211212 | 163451702 | FROGTOWN 1702 | 11212 | FALSE | 35943.9954 | 35943.9954 | 22.3393 | 155 | 8.85e-05 | 1974 | 349.3135 | 1372 | 0.030264 | 4.691 | 1457 | 0.06 | 1822
2196 | ATASCADERO 1101A02 | 182541101 | ATASCADERO 1101 | A02 | FALSE | 41006.5742 | 41006.5742 | 25.4858 | 253 | 5.864e-05 | 2818 | 542.8818 | 1156 | 0.030233 | 7.649 | 1458 | 2.41 | 606
6596 | STELLING 111060090 | 83481110 | STELLING 1110 | 60090 | FALSE | 10545.4488 | 10545.4488 | 6.554 | 62 | 0.00016362 | 604 | 206.0102 | 1623 | 0.030171 | 1.8706 | 1459 | 0.06 | 1906
6029 | PANORAMA 1101713592 | 103461101 | PANORAMA 1101 | 713592 | FALSE | 16948.2792 | 16715.2405 | 10.3886 | 152 | 6.2494e-05 | 2704 | 490.9201 | 1208 | 0.030005 | 4.5608 | 1460 |  | 2997
3261 | CRESCENT MILLS 2101CB | 103132101 | CRESCENT MILLS 2101 | CB | FALSE | 9227.3447 | 4545.9264 | 2.8253 | 60 | 7.4812e-05 | 2336 | 409.6387 | 1286 | 0.029932 | 1.7959 | 1461 | 5.21 | 494
4399 | PLACERVILLE 210619552 | 153082106 | PLACERVILLE 2106 | 19552 | FALSE | 34339.9089 | 34339.9089 | 21.3424 | 238 | 0.0001768 | 520 | 361.0634 | 1351 | 0.029928 | 7.123 | 1462 | 0.45 | 915
10240 | LLAGAS 2105534019 | 83182105 | LLAGAS 2105 | 534019 | FALSE | 1193.5001 | 1147.9573 | 0.71346 | 5 | 0.0001111 | 1391 | 269.5494 | 1499 | 0.029893 | 0.14947 | 1463 |  | 3519
5361 | HOOPA 11013174 | 192401101 | HOOPA 1101 | 3174 | FALSE | 35498.7494 | 29750.1978 | 18.4899 | 162 | 0.00035838 | 83 | 115.2454 | 1894 | 0.029875 | 4.8397 | 1464 | 0.13 | 1336
5027 | PEORIA 17048040 | 163781704 | PEORIA 1704 | 8040 | FALSE | 41434.2849 | 11785.9847 | 7.325 | 145 | 5.9131e-05 | 2803 | 495.056 | 1206 | 0.02987 | 4.3312 | 1465 | 0.01 | 2600
9000 | CASTRO VALLEY 11088971 | 14091108 | CASTRO VALLEY 1108 | 8971 | FALSE | 12716.2407 | 12716.2407 | 7.9032 | 72 | 0.00010597 | 1496 | 268.1837 | 1504 | 0.029749 | 2.1419 | 1466 |  | 3293
3972 | CORRAL 1103936674 | 162991103 | CORRAL 1103 | 936674 | FALSE | 6354.8382 | 1063.5848 | 0.66102 | 56 | 8.2565e-05 | 2141 | 408.407 | 1288 | 0.029729 | 1.6648 | 1467 |  | 2866
5038 | MOLINO 110241392 | 42571102 | MOLINO 1102 | 41392 | FALSE | 23588.435 | 7062.7077 | 4.3895 | 171 | 0.00011368 | 1327 | 289.7407 | 1465 | 0.029696 | 5.078 | 1468 | 3.21 | 554
8758 | PUTAH CREEK 11033783 | 63681103 | PUTAH CREEK 1103 | 3783 | TRUE | 16200.7401 | 142.5109 | 0.088571 | 96 | 9.2314e-05 | 1834 | 351.5102 | 1370 | 0.029685 | 2.8498 | 1469 |  | 3259
10009 | OREGON TRAIL 110346860 | 103521103 | OREGON TRAIL 1103 | 46860 | FALSE | 5362.8484 | 1149.598 | 0.71448 | 15 | 0.0001367 | 912 | 145.8531 | 1790 | 0.029648 | 0.44471 | 1470 | 0.03 | 2247
944 | CURTIS 17036064 | 163351703 | CURTIS 1703 | 6064 | FALSE | 31643.7207 | 30550.9366 | 18.9875 | 199 | 7.5696e-05 | 2315 | 471.6661 | 1222 | 0.029564 | 5.8832 | 1471 | 0.2 | 1167
5754 | SANTA YNEZ 1102Y18 | 182721102 | SANTA YNEZ 1102 | Y18 | FALSE | 12113.6185 | 7856.8971 | 4.8831 | 60 | 4.1779e-05 | 3229 | 658.0763 | 1056 | 0.029555 | 1.7733 | 1472 | 0.08 | 1647
1748 | CLAY 110113450 | 163341101 | CLAY 1101 | 13450 | FALSE | 7994.7686 | 1509.284 | 0.93803 | 42 | 7.6415e-05 | 2295 | 360.8067 | 1352 | 0.029532 | 1.2403 | 1473 |  | 2741
2073 | WILLOW CREEK 11032936 | 192171103 | WILLOW CREEK 1103 | 2936 | FALSE | 53378.6829 | 53378.6829 | 33.1751 | 249 | 0.00014373 | 817 | 191.382 | 1659 | 0.029513 | 7.3486 | 1474 | 0.15 | 1299
3589 | MIRABEL 1101688780 | 42091101 | MIRABEL 1101 | 688780 | TRUE | 2079.7156 | 922.8958 | 0.57358 | 14 | 0.00019275 | 430 | 228.6665 | 1589 | 0.029456 | 0.41239 | 1475 |  | 2839
4182 | GARBERVILLE 11021510 | 192221102 | GARBERVILLE 1102 | 1510 | FALSE | 21171.8285 | 21171.8285 | 13.1584 | 107 | 0.00046286 | 44 | 80.26 | 2047 | 0.029417 | 3.1476 | 1476 | 0.13 | 1358
3154 | CALISTOGA 1102634 | 42711102 | CALISTOGA 1102 | 634 | FALSE | 27022.9414 | 18046.5459 | 11.216 | 178 | 0.00012722 | 1060 | 223.109 | 1599 | 0.029373 | 5.2284 | 1477 | 0.7 | 808
133 | GEYSERVILLE 1102522 | 42891102 | GEYSERVILLE 1102 | 522 | FALSE | 17218.2435 | 12875.7792 | 8.0023 | 109 | 8.4103e-05 | 2091 | 350.0759 | 1371 | 0.029361 | 3.2003 | 1478 | 0.06 | 1861
10360 | OLEMA 110175686 | 42291101 | OLEMA 1101 | 75686 | FALSE | 8282.1233 | 7450.4021 | 4.6305 | 31 | 0.00011699 | 1250 | 264.1333 | 1511 | 0.029281 | 0.90772 | 1479 | 0.04 | 2067
9801 | KANAKA 1101CB | 103221101 | KANAKA 1101 | CB | FALSE | 7605.9803 | 7605.9803 | 4.7271 | 37 | 0.00011114 | 1390 | 255.7947 | 1533 | 0.029281 | 1.0834 | 1480 | 0.23 | 1113
4062 | WHITMORE 1101CB | 103601101 | WHITMORE 1101 | CB | FALSE | 9497.7631 | 9497.7631 | 5.9029 | 69 | 0.00021208 | 351 | 141.7322 | 1806 | 0.029248 | 2.0181 | 1481 | 0.04 | 2126
1547 | WILLITS 110391810 | 42661103 | WILLITS 1103 | 91810 | FALSE | 47379.4324 | 47379.4324 | 29.4465 | 296 | 0.00010548 | 1507 | 312.0704 | 1428 | 0.029203 | 8.6442 | 1482 | 44.17 | 160
8861 | GEYSERVILLE 1102331444 | 42891102 | GEYSERVILLE 1102 | 331444 | FALSE | 7051.4008 | 3579.9474 | 2.225 | 44 | 0.00010727 | 1466 | 260.3745 | 1523 | 0.029048 | 1.2781 | 1483 |  | 3273
3080 | PIKE CITY 1101CB | 152201101 | PIKE CITY 1101 | CB | FALSE | 31622.6384 | 31622.6384 | 19.6536 | 162 | 0.00011093 | 1392 | 299.4116 | 1448 | 0.029034 | 4.7034 | 1484 | 78.02 | 52
9245 | FRUITLAND 1142899734 | 192311142 | FRUITLAND 1142 | 899734 | FALSE | 5471.5337 | 5471.5337 | 3.4006 | 36 | 0.00048435 | 35 | 103.6873 | 1931 | 0.028754 | 1.0351 | 1485 |  | 3329
2842 | SAN LUIS OBISPO 1101CB | 182631101 | SAN LUIS OBISPO 1101 | CB | FALSE | 10872.4032 | 5779.9667 | 3.5923 | 75 | 4.9567e-05 | 3048 | 502.0965 | 1196 | 0.028742 | 2.1556 | 1486 | 0.7 | 805
8606 | PUEBLO 1105684564 | 43291105 | PUEBLO 1105 | 684564 | TRUE | 4176.2924 | 443.3906 | 0.27557 | 28 | 6.665e-05 | 2566 | 311.0083 | 1430 | 0.02858 | 0.80024 | 1487 |  | 3243
3749 | VINEYARD 2107978364 | 14502107 | VINEYARD 2107 | 978364 | FALSE | 4026.4295 | 1557.6573 | 0.96809 | 36 | 4.8923e-05 | 3067 | 319.1206 | 1419 | 0.028543 | 1.0276 | 1488 |  | 2850
1264 | TEMPLETON 2113CB | 183052113 | TEMPLETON 2113 | CB | FALSE | 41366.5121 | 1446.4903 | 0.899 | 288 | 7.2635e-05 | 2400 | 424.917 | 1268 | 0.028499 | 8.2077 | 1489 | 0.17 | 1224
6493 | POINT ARENA 11013702 | 43381101 | POINT ARENA 1101 | 3702 | FALSE | 7962.9538 | 7864.1375 | 4.8876 | 35 | 5.5767e-05 | 2896 | 546.4749 | 1152 | 0.028477 | 0.99668 | 1490 | 0.03 | 2383
2973 | TEMPLETON 2111R86 | 183052111 | TEMPLETON 2111 | R86 | FALSE | 23197.4547 | 17574.2947 | 10.9225 | 160 | 5.7553e-05 | 2847 | 490.6496 | 1209 | 0.028407 | 4.5451 | 1491 | 0.08 | 1637
2170 | MC KEE 1111711900 | 83531111 | MC KEE 1111 | 711900 | FALSE | 20250.2667 | 14456.1594 | 8.9846 | 116 | 7.6946e-05 | 2288 | 301.111 | 1446 | 0.028347 | 3.2883 | 1492 | 0.24 | 1097
7676 | JARVIS 1108289662 | 13501108 | JARVIS 1108 | 289662 | TRUE | 1302.884 | 533.3553 | 0.33148 | 11 | 2.7822e-05 | 3461 | 483.4846 | 1212 | 0.028227 | 0.31049 | 1493 |  | 3149
5235 | BELLEVUE 2103648 | 43182103 | BELLEVUE 2103 | 648 | FALSE | 26216.5179 | 6117.4965 | 3.802 | 187 | 9.6901e-05 | 1716 | 305.0125 | 1439 | 0.028161 | 5.2662 | 1494 | 2.81 | 578
10298 | PIT NO 5 11011618 | 101321101 | PIT NO 5 1101 | 1618 | FALSE | 9746.1598 | 9746.1598 | 6.0573 | 15 | 0.00010839 | 1441 | 237.7895 | 1574 | 0.028087 | 0.42131 | 1495 | 0 | 2632
5972 | TASSAJARA 2104CB | 14662104 | TASSAJARA 2104 | CB | TRUE | 1951.9603 | 159.1645 | 0.098921 | 22 | 5.9141e-05 | 2802 | 153.2438 | 1767 | 0.028017 | 0.61638 | 1496 | 0.28 | 1038
2469 | ELECTRA 11026014 | 162161102 | ELECTRA 1102 | 6014 | FALSE | 8043.0218 | 8043.0218 | 4.9988 | 50 | 0.000124 | 1120 | 242.0554 | 1562 | 0.027926 | 1.3963 | 1497 | 0.1 | 1478
1225 | SUNOL 1101MR298 | 14241101 | SUNOL 1101 | MR298 | FALSE | 8473.8006 | 8244.1822 | 5.1238 | 39 | 7.0694e-05 | 2452 | 586.0273 | 1117 | 0.027925 | 1.0891 | 1498 | 0.26 | 1070
739 | COTATI 1105CB | 42271105 | COTATI 1105 | CB | FALSE | 4309.0759 | 4309.0759 | 2.6781 | 35 | 0.00011326 | 1338 | 266.28 | 1506 | 0.027854 | 0.97488 | 1499 | 11.62 | 384
1612 | CABRILLO 1104Y22 | 183101104 | CABRILLO 1104 | Y22 | FALSE | 40867.3286 | 16721.66 | 10.3926 | 178 | 4.3833e-05 | 3193 | 413.6922 | 1281 | 0.027743 | 4.9383 | 1500 | 0.04 | 2132
2769 | ANNAPOLIS 110176842 | 42861101 | ANNAPOLIS 1101 | 76842 | FALSE | 9156.7064 | 9156.7064 | 5.6909 | 33 | 0.00012448 | 1109 | 276.9184 | 1479 | 0.027724 | 0.91488 | 1501 | 0.08 | 1635
2631 | TEMPLETON 2111A66 | 183052111 | TEMPLETON 2111 | A66 | FALSE | 54313.8381 | 54313.8381 | 33.7563 | 429 | 6.1474e-05 | 2734 | 473.9679 | 1218 | 0.027639 | 11.8573 | 1502 | 0.27 | 1052
2379 | SAN LUIS OBISPO 1103CB | 182631103 | SAN LUIS OBISPO 1103 | CB | TRUE | 10934.0811 | 0 | 0 | 68 | 0.00011128 | 1389 | 204.9489 | 1629 | 0.027594 | 1.8764 | 1503 | 0.03 | 2305
4288 | SAN LUIS OBISPO 1103V82 | 182631103 | SAN LUIS OBISPO 1103 | V82 | FALSE | 22558.9801 | 14130.1147 | 8.7819 | 174 | 7.4918e-05 | 2332 | 326.0495 | 1404 | 0.027572 | 4.7975 | 1504 | 0.06 | 1792
3496 | APPLE HILL 21027502 | 153662102 | APPLE HILL 2102 | 7502 | FALSE | 36933.3454 | 36933.3454 | 22.9542 | 267 | 0.00011381 | 1324 | 264.2675 | 1509 | 0.027532 | 7.351 | 1505 | 38.11 | 197
3795 | SAN LUIS OBISPO 1101V12 | 182631101 | SAN LUIS OBISPO 1101 | V12 | FALSE | 33868.1694 | 33868.1694 | 21.0492 | 127 | 8.411e-05 | 2090 | 399.923 | 1297 | 0.027414 | 3.4815 | 1506 | 0.24 | 1100
5816 | PAUL SWEET 210710986 | 83252107 | PAUL SWEET 2107 | 10986 | FALSE | 31785.0255 | 14988.5933 | 9.3155 | 180 | 9.4351e-05 | 1785 | 282.1821 | 1470 | 0.027411 | 4.9339 | 1507 | 0.19 | 1190
9709 | LAYTONVILLE 1102682 | 42681102 | LAYTONVILLE 1102 | 682 | FALSE | 23844.5349 | 23844.5349 | 14.8195 | 97 | 0.00016349 | 605 | 167.4124 | 1727 | 0.027282 | 2.6464 | 1508 | 2.58 | 596
1461 | LOS OSITOS 21033010 | 182082103 | LOS OSITOS 2103 | 3010 | FALSE | 50085.8598 | 50061.44 | 31.1134 | 229 | 6.2602e-05 | 2699 | 457.2691 | 1239 | 0.027281 | 6.2474 | 1509 | 0.11 | 1434
6161 | HIGHLANDS 1102556 | 43361102 | HIGHLANDS 1102 | 556 | TRUE | 12171.5187 | 285.9131 | 0.1777 | 90 | 6.0969e-05 | 2748 | 422.9587 | 1269 | 0.027227 | 2.4505 | 1510 | 1.68 | 652
8442 | MARTELL 11016074 | 163011101 | MARTELL 1101 | 6074 | FALSE | 5923.6574 | 5923.6574 | 3.6816 | 34 | 0.00013034 | 1003 | 156.7867 | 1759 | 0.027132 | 0.92248 | 1511 | 1.63 | 660
7912 | HALF MOON BAY 1101818874 | 24101101 | HALF MOON BAY 1101 | 818874 | FALSE | 10865.8424 | 9148.5425 | 5.6859 | 42 | 8.8075e-05 | 1981 | 323.2606 | 1408 | 0.02708 | 1.1374 | 1512 |  | 3177
5790 | HIGGINS 1110869408 | 152691110 | HIGGINS 1110 | 869408 | TRUE | 710.7103 | 710.7103 | 0.44171 | 6 | 0.00016423 | 597 | 150.5967 | 1775 | 0.027041 | 0.16225 | 1513 |  | 2977
9590 | OILFIELDS 11037006 | 182391103 | OILFIELDS 1103 | 7006 | TRUE | 11204.5058 | 0 | 0 | 42 | 6.1931e-05 | 2722 | 240.1753 | 1567 | 0.027015 | 1.1346 | 1514 | 0 | 2622
9570 | SWIFT 2102889948 | 83392102 | SWIFT 2102 | 889948 | TRUE | 2120.3673 | 706.8877 | 0.43933 | 8 | 7.9649e-05 | 2217 | 479.8183 | 1216 | 0.026886 | 0.21509 | 1515 |  | 3380
9335 | SAN MIGUEL 1106N34 | 182661106 | SAN MIGUEL 1106 | N34 | FALSE | 22008.9702 | 6041.6356 | 3.7549 | 62 | 9.4539e-05 | 1778 | 242.6816 | 1560 | 0.02675 | 1.6585 | 1516 | 0 | 2638
8060 | MONTE RIO 1112120 | 42811112 | MONTE RIO 1112 | 120 | FALSE | 10326.1868 | 10326.1868 | 6.4178 | 67 | 0.00021509 | 341 | 93.788 | 1989 | 0.026687 | 1.788 | 1517 | 79.25 | 50
2780 | HIGHLANDS 1102CB | 43361102 | HIGHLANDS 1102 | CB | FALSE | 11922.4207 | 11922.4207 | 7.4098 | 78 | 6.4644e-05 | 2617 | 270.2338 | 1497 | 0.026652 | 2.0789 | 1518 | 0.11 | 1413
5253 | HOOPA 110182542 | 192401101 | HOOPA 1101 | 82542 | FALSE | 24330.9579 | 19513.0606 | 12.1274 | 150 | 0.00024689 | 227 | 125.8806 | 1856 | 0.026646 | 3.9969 | 1519 | 0.25 | 1073
9493 | BRUNSWICK 1103904574 | 152481103 | BRUNSWICK 1103 | 904574 | FALSE | 2518.7659 | 2518.7659 | 1.5654 | 25 | 0.0002218 | 312 | 119.8467 | 1870 | 0.026628 | 0.6657 | 1520 |  | 3362
2834 | WILLOW PASS 1101CB | 13911101 | WILLOW PASS 1101 | CB | FALSE | 10055.4219 | 1899.3733 | 1.1805 | 75 | 5.022e-05 | 3033 | 198.6367 | 1643 | 0.026552 | 1.9914 | 1521 | 0.04 | 2084
4322 | WYANDOTTE 11095973 | 102911109 | WYANDOTTE 1109 | 5973 | TRUE | 3972.7876 | 138.2354 | 0.085914 | 35 | 0.00011259 | 1351 | 248.9959 | 1541 | 0.026544 | 0.92904 | 1522 |  | 2881
9896 | PUEBLO 2102773926 | 43292102 | PUEBLO 2102 | 773926 | TRUE | 3395.2146 | 706.7417 | 0.43924 | 25 | 7.9069e-05 | 2232 | 668.6259 | 1044 | 0.026524 | 0.66311 | 1523 |  | 3448
7392 | WINDSOR 1103CB | 43501103 | WINDSOR 1103 | CB | TRUE | 8832.9668 | 0 | 0 | 64 | 0.00011152 | 1384 | 254.8686 | 1534 | 0.026458 | 1.6933 | 1524 |  | 3122
7312 | PEABODY 2113CB | 63642113 | PEABODY 2113 | CB | TRUE | 8317.4057 | 587.3881 | 0.36506 | 40 | 7.0186e-05 | 2464 | 270.6989 | 1494 | 0.026426 | 1.057 | 1525 | 2.37 | 608
5020 | BONNIE NOOK 1101CB | 152301101 | BONNIE NOOK 1101 | CB | FALSE | 23251.1044 | 23251.1044 | 14.4507 | 153 | 0.00019229 | 432 | 98.7244 | 1962 | 0.026396 | 4.0386 | 1526 | 44.02 | 163
2080 | NEWBURG 11313446 | 192151131 | NEWBURG 1131 | 3446 | TRUE | 13148.5405 | 475.0126 | 0.29522 | 87 | 0.00014693 | 773 | 117.907 | 1882 | 0.026372 | 2.2944 | 1527 | 0.23 | 1108
5621 | FORT ROSS 112137326 | 42851121 | FORT ROSS 1121 | 37326 | FALSE | 8213.253 | 8213.253 | 5.1046 | 31 | 5.9994e-05 | 2777 | 369.1163 | 1338 | 0.026358 | 0.8171 | 1528 | 0.04 | 2195
7707 | SUMMIT 110148632 | 152591101 | SUMMIT 1101 | 48632 | FALSE | 4391.6286 | 4391.6286 | 2.7294 | 38 | 0.00010681 | 1483 | 115.1661 | 1895 | 0.026323 | 1.0003 | 1529 | 0.07 | 1766
4086 | WEST POINT 110236676 | 163201102 | WEST POINT 1102 | 36676 | FALSE | 27305.8877 | 27305.8877 | 16.9707 | 173 | 8.1258e-05 | 2175 | 346.1968 | 1376 | 0.026145 | 4.5232 | 1530 | 34.1 | 217
3634 | CHALLENGE 11021902 | 103201102 | CHALLENGE 1102 | 1902 | FALSE | 7840.3138 | 7840.3138 | 4.8728 | 44 | 0.00013679 | 909 | 253.4699 | 1535 | 0.026064 | 1.1468 | 1531 | 31.9 | 227
5849 | HOPLAND 11011100 | 42251101 | HOPLAND 1101 | 1100 | FALSE | 10937.7288 | 5979.935 | 3.7166 | 68 | 8.9766e-05 | 1920 | 293.7962 | 1457 | 0.026059 | 1.772 | 1532 | 0.03 | 2389
9887 | NOVATO 1104676060 | 42211104 | NOVATO 1104 | 676060 | TRUE | 1407.162 | 722.7771 | 0.44921 | 9 | 0.00025905 | 197 | 109.1 | 1913 | 0.026046 | 0.23441 | 1533 |  | 3446
6186 | CALAVERAS CEMENT 110111188 | 162211101 | CALAVERAS CEMENT 1101 | 11188 | FALSE | 48202.5217 | 48202.5217 | 29.9581 | 294 | 0.00012846 | 1041 | 211.2891 | 1617 | 0.02599 | 7.641 | 1534 | 0.06 | 1852
6575 | CLARK ROAD 110247006 | 103091102 | CLARK ROAD 1102 | 47006 | FALSE | 7194.664 | 7194.664 | 4.4715 | 51 | 0.00041526 | 65 | 106.8362 | 1923 | 0.025936 | 1.3227 | 1535 | 0.13 | 1347
5041 | MARTELL 1103CB | 163011103 | MARTELL 1103 | CB | FALSE | 10088.6649 | 2844.8661 | 1.7681 | 76 | 0.00011862 | 1213 | 152.4537 | 1770 | 0.025924 | 1.9702 | 1536 | 0.01 | 2606
7535 | PARADISE 11042034 | 102831104 | PARADISE 1104 | 2034 | FALSE | 17672.0047 | 17659.7087 | 10.9756 | 99 | 0.00023619 | 258 | 172.9141 | 1707 | 0.025842 | 2.5583 | 1537 | 0.4 | 942
3586 | PENRYN 1107346 | 152561107 | PENRYN 1107 | 346 | FALSE | 40386.1099 | 22629.4944 | 14.0643 | 309 | 0.00013985 | 869 | 232.58 | 1582 | 0.025706 | 7.9433 | 1538 | 0.07 | 1770
8624 | JESSUP 11012839 | 103441101 | JESSUP 1101 | 2839 | FALSE | 2358.3859 | 2358.3859 | 1.4657 | 20 | 0.00011836 | 1220 | 279.5294 | 1473 | 0.02569 | 0.5138 | 1539 | 0.07 | 1683
2763 | GOLDTREE 1108CB | 182581108 | GOLDTREE 1108 | CB | FALSE | 7803.1232 | 3646.1026 | 2.2661 | 50 | 6.1558e-05 | 2731 | 249.9677 | 1540 | 0.025673 | 1.2836 | 1540 | 0.06 | 1893
9750 | COVELO 1101430286 | 43061101 | COVELO 1101 | 430286 | FALSE | 8696.3655 | 5942.5051 | 3.6933 | 13 | 7.0159e-05 | 2468 | 482.818 | 1213 | 0.025652 | 0.33348 | 1541 |  | 3410
8494 | BRENTWOOD 2105502672 | 14592105 | BRENTWOOD 2105 | 502672 | FALSE | 30486.256 | 2285.3291 | 1.4203 | 127 | 5.9745e-05 | 2781 | 641.4967 | 1071 | 0.025636 | 3.2558 | 1542 | 0.03 | 2388
5780 | GREEN VALLEY 210111054 | 83192101 | GREEN VALLEY 2101 | 11054 | FALSE | 41601.4757 | 39167.0021 | 24.3425 | 272 | 0.00015629 | 682 | 157.984 | 1754 | 0.025605 | 6.9646 | 1543 | 1.82 | 640
5526 | LLAGAS 2107XR188 | 83182107 | LLAGAS 2107 | XR188 | TRUE | 5000.7034 | 608.151 | 0.37797 | 43 | 0.00010266 | 1579 | 145.3531 | 1791 | 0.025596 | 1.1006 | 1544 | 0.05 | 1999
3427 | COTATI 1105616 | 42271105 | COTATI 1105 | 616 | FALSE | 49320.745 | 4247.523 | 2.6399 | 198 | 8.18e-05 | 2160 | 268.44 | 1503 | 0.025585 | 5.0659 | 1545 | 0.02 | 2449
9956 | CLARKSVILLE 2109781566 | 153612109 | CLARKSVILLE 2109 | 781566 | FALSE | 1246.3402 | 1113.5139 | 0.69205 | 11 | 0.00014318 | 824 | 155.6264 | 1762 | 0.025518 | 0.28069 | 1546 |  | 3459
1199 | BEAR VALLEY 21059560 | 252192105 | BEAR VALLEY 2105 | 9560 | FALSE | 35435.963 | 35435.963 | 22.0236 | 226 | 5.282e-05 | 2976 | 582.977 | 1120 | 0.025353 | 5.7297 | 1547 | 0.31 | 1001
4849 | ELECTRA 11017104 | 162161101 | ELECTRA 1101 | 7104 | FALSE | 19430.6652 | 19430.6652 | 12.0762 | 148 | 0.0001151 | 1296 | 163.538 | 1738 | 0.025302 | 3.7447 | 1548 | 13.46 | 365
4914 | JESSUP 11019002 | 103441101 | JESSUP 1101 | 9002 | FALSE | 9863.4451 | 1568.4919 | 0.97482 | 74 | 0.0001072 | 1468 | 178.96 | 1685 | 0.025292 | 1.8716 | 1549 | 0.04 | 2144
6329 | SILVERADO 2102636 | 43432102 | SILVERADO 2102 | 636 | FALSE | 10208.6635 | 8793.2474 | 5.465 | 81 | 0.00012369 | 1126 | 135.9278 | 1827 | 0.025287 | 2.0483 | 1550 | 0.41 | 940
7235 | BRIDGEVILLE 110137484 | 192461101 | BRIDGEVILLE 1101 | 37484 | FALSE | 15938.0756 | 12688.6958 | 7.8861 | 74 | 0.0001949 | 416 | 197.6391 | 1647 | 0.025267 | 1.8698 | 1551 | 3.58 | 540
4335 | UKIAH 1114844294 | 42771114 | UKIAH 1114 | 844294 | FALSE | 9847.8884 | 3879.784 | 2.4113 | 55 | 0.0001067 | 1485 | 276.8057 | 1480 | 0.025242 | 1.3883 | 1552 |  | 2882
5817 | TIVY VALLEY 110737522 | 252941107 | TIVY VALLEY 1107 | 37522 | TRUE | 4999.5672 | 833.6297 | 0.5181 | 43 | 3.7339e-05 | 3307 | 997.9464 | 835 | 0.025221 | 1.0845 | 1553 | 0.42 | 937
402 | REDBUD 1102922 | 43191102 | REDBUD 1102 | 922 | FALSE | 12634.8407 | 12589.4258 | 7.8244 | 84 | 5.9231e-05 | 2798 | 352.2884 | 1369 | 0.025187 | 2.1157 | 1554 | 0.06 | 1854
4837 | SAN LUIS OBISPO 1104V46 | 182631104 | SAN LUIS OBISPO 1104 | V46 | FALSE | 33477.4498 | 32077.3964 | 19.9362 | 206 | 6.5385e-05 | 2604 | 359.6086 | 1354 | 0.025184 | 5.1879 | 1555 | 0.58 | 860
6418 | DUNLAP 1102CB | 254061102 | DUNLAP 1102 | CB | FALSE | 10840.0956 | 10840.0956 | 6.7372 | 79 | 5.5221e-05 | 2906 | 463.403 | 1231 | 0.025156 | 1.9873 | 1556 | 0 | 2629
8607 | ANNAPOLIS 1101608 | 42861101 | ANNAPOLIS 1101 | 608 | FALSE | 28658.1175 | 28658.1175 | 17.8111 | 74 | 9.5295e-05 | 1755 | 248.4816 | 1545 | 0.025135 | 1.86 | 1557 | 0.18 | 1210
8805 | FRUITLAND 114293234 | 192311142 | FRUITLAND 1142 | 93234 | FALSE | 18471.7273 | 18471.7273 | 11.4803 | 96 | 0.0002481 | 222 | 135.7036 | 1830 | 0.025062 | 2.4059 | 1558 | 7.72 | 442
3300 | FULTON 1102CB | 42561102 | FULTON 1102 | CB | TRUE | 6358.3504 | 326.8592 | 0.20314 | 48 | 0.00010128 | 1621 | 121.8474 | 1865 | 0.025061 | 1.2029 | 1559 | 0.07 | 1754
4515 | GIRVAN 11019732 | 103401101 | GIRVAN 1101 | 9732 | FALSE | 33758.8908 | 33758.8908 | 20.9813 | 267 | 0.00010167 | 1613 | 282.8705 | 1469 | 0.025046 | 6.6872 | 1560 | 4.84 | 504
602 | STAFFORD 1102524 | 43201102 | STAFFORD 1102 | 524 | FALSE | 20718.9245 | 9871.5042 | 6.1352 | 162 | 9.4892e-05 | 1769 | 289.834 | 1464 | 0.02502 | 4.0533 | 1561 | 3.23 | 553
6121 | OTTER 110263868 | 182941102 | OTTER 1102 | 63868 | FALSE | 25546.2406 | 25546.2406 | 15.8771 | 171 | 8.8626e-05 | 1968 | 190.8082 | 1660 | 0.024964 | 4.2689 | 1562 | 0.04 | 2158
4102 | SPAULDING 1101578852 | 152251101 | SPAULDING 1101 | 578852 | FALSE | 38890.7673 | 33210.6867 | 20.6406 | 173 | 9.1712e-05 | 1853 | 190.7466 | 1661 | 0.024946 | 4.3156 | 1563 | 0 | 2630
9390 | COAST RD 04015134 | 88820401 | COAST RD 0401 | 5134 | FALSE | 4886.1695 | 1018.6198 | 0.63308 | 23 | 6.0194e-05 | 2767 | 173.1479 | 1703 | 0.024922 | 0.57321 | 1564 | 0.02 | 2554
9959 | BRIDGEVILLE 1102384530 | 192461102 | BRIDGEVILLE 1102 | 384530 | FALSE | 6144.6716 | 6144.6716 | 3.8189 | 12 | 0.00011661 | 1259 | 223.8048 | 1598 | 0.024779 | 0.29735 | 1565 |  | 3460
2322 | KANAKA 11011034 | 103221101 | KANAKA 1101 | 1034 | FALSE | 17942.0463 | 17942.0463 | 11.1511 | 80 | 8.3104e-05 | 2129 | 308.8782 | 1434 | 0.024689 | 1.9751 | 1566 | 37.44 | 201
5230 | BANGOR 11011806 | 103191101 | BANGOR 1101 | 1806 | FALSE | 6482.8365 | 6482.8365 | 4.0291 | 17 | 0.00015564 | 687 | 310.6981 | 1431 | 0.024567 | 0.41764 | 1567 | 0.08 | 1588
4084 | JOLON 11027040 | 182981102 | JOLON 1102 | 7040 | FALSE | 36891.8795 | 33515.8907 | 20.8303 | 119 | 0.00010008 | 1645 | 276.795 | 1481 | 0.02433 | 2.8953 | 1568 | 0.03 | 2398
7751 | MIWUK 17018050 | 163661701 | MIWUK 1701 | 8050 | FALSE | 19488.3045 | 19488.3045 | 12.1121 | 137 | 6.4562e-05 | 2624 | 296.266 | 1454 | 0.024311 | 3.3307 | 1569 | 82.85 | 41
10676 | KERN OIL 1106397902 | 252721106 | KERN OIL 1106 | 397902 | TRUE | 2608.3236 | 717.5326 | 0.44595 | 9 | 1.8967e-05 | 3553 | 1301.6353 | 682 | 0.024302 | 0.21872 | 1570 |  | 3589
5615 | ELECTRA 110161816 | 162161101 | ELECTRA 1101 | 61816 | FALSE | 37826.9874 | 37826.9874 | 23.5096 | 228 | 9.0781e-05 | 1889 | 261.0762 | 1521 | 0.0243 | 5.5405 | 1571 | 0.1 | 1458
801 | OCEANO 1102CB | 182601102 | OCEANO 1102 | CB | FALSE | 26239.5079 | 25449.7716 | 15.8171 | 183 | 5.9389e-05 | 2793 | 407.261 | 1290 | 0.024236 | 4.4352 | 1572 | 0.24 | 1103
8403 | MOLINO 1101472660 | 42571101 | MOLINO 1101 | 472660 | FALSE | 2333.6937 | 2333.6937 | 1.4504 | 18 | 0.00011189 | 1371 | 307.8995 | 1436 | 0.024226 | 0.43606 | 1573 |  | 3221
4244 | BRUNSWICK 1104CB | 152481104 | BRUNSWICK 1104 | CB | TRUE | 2139.8633 | 621.7387 | 0.38641 | 28 | 0.00025903 | 198 | 63.383 | 2133 | 0.024194 | 0.67743 | 1574 | 1.36 | 681
10152 | SPENCE 1102321000 | 182201102 | SPENCE 1102 | 321000 | FALSE | 4053.5113 | 2330.3266 | 1.4483 | 13 | 3.5425e-05 | 3341 | 465.5516 | 1229 | 0.024187 | 0.31443 | 1575 |  | 3503
3391 | COTATI 1105734248 | 42271105 | COTATI 1105 | 734248 | TRUE | 774.6582 | 774.6582 | 0.48145 | 9 | 9.7301e-05 | 1706 | 238.3995 | 1571 | 0.024166 | 0.2175 | 1576 |  | 2824
9545 | WYANDOTTE 110942650 | 102911109 | WYANDOTTE 1109 | 42650 | FALSE | 4322.5083 | 1459.6214 | 0.90716 | 37 | 0.00018107 | 502 | 100.7676 | 1951 | 0.024082 | 0.89104 | 1577 | 0.04 | 2229
4392 | CLARK ROAD 110290548 | 103091102 | CLARK ROAD 1102 | 90548 | FALSE | 28870.4925 | 28870.4925 | 17.9431 | 168 | 0.00013973 | 872 | 196.9334 | 1651 | 0.024003 | 4.0325 | 1578 | 0.67 | 811
9548 | FROGTOWN 1702224708 | 163451702 | FROGTOWN 1702 | 224708 | FALSE | 1049.1603 | 1033.1582 | 0.64211 | 9 | 0.00015636 | 681 | 235.0194 | 1578 | 0.02399 | 0.21591 | 1579 |  | 3374
2473 | COLUMBIA HILL 110135424 | 152471101 | COLUMBIA HILL 1101 | 35424 | FALSE | 22308.0719 | 22308.0719 | 13.8646 | 147 | 0.00020736 | 374 | 171.1392 | 1711 | 0.023757 | 3.4923 | 1580 | 74.11 | 58
3207 | SHADY GLEN 110151696 | 152431101 | SHADY GLEN 1101 | 51696 | FALSE | 32551.2584 | 28077.2635 | 17.4501 | 238 | 0.00017871 | 514 | 165.4297 | 1734 | 0.023753 | 5.6532 | 1581 | 0.86 | 763
7684 | PETALUMA C 1109738866 | 42631109 | PETALUMA C 1109 | 738866 | FALSE | 4335.7412 | 3280.2516 | 2.0387 | 28 | 6.3795e-05 | 2653 | 268.4844 | 1502 | 0.023732 | 0.66451 | 1582 | 0.1 | 1506
10885 | MORGAN HILL 2111940112 | 83242111 | MORGAN HILL 2111 | 940112 | TRUE | 489.7385 | 455.0253 | 0.2828 | 2 | 5.8767e-05 | 2813 | 268.9489 | 1500 | 0.023701 | 0.047401 | 1583 |  | 3616
10683 | SAN BERNARD 1101438074 | 253191101 | SAN BERNARD 1101 | 438074 | TRUE | 2039.2275 | 516.2478 | 0.32085 | 6 | 3.2276e-05 | 3397 | 1470.0727 | 606 | 0.023646 | 0.14187 | 1584 |  | 3592
274 | GEYSERVILLE 1102350 | 42891102 | GEYSERVILLE 1102 | 350 | FALSE | 31334.246 | 8365.2365 | 5.199 | 194 | 8.9262e-05 | 1940 | 270.3135 | 1496 | 0.023632 | 4.5846 | 1585 | 0.09 | 1536
6780 | FOOTHILL 1102CB | 182951102 | FOOTHILL 1102 | CB | FALSE | 15763.1114 | 12699.351 | 7.8927 | 97 | 5.9509e-05 | 2789 | 274.1428 | 1486 | 0.023627 | 2.2918 | 1586 | 0.1 | 1488
5469 | FROGTOWN 1701L3361 | 163451701 | FROGTOWN 1701 | L3361 | FALSE | 3015.6838 | 3015.6838 | 1.8743 | 21 | 6.3649e-05 | 2658 | 377.9344 | 1325 | 0.023616 | 0.49595 | 1587 | 0.09 | 1563
279 | GEYSERVILLE 1101122 | 42891101 | GEYSERVILLE 1101 | 122 | FALSE | 11125.688 | 2112.7276 | 1.3131 | 54 | 6.2796e-05 | 2689 | 203.6365 | 1635 | 0.023602 | 1.2745 | 1588 | 0.03 | 2263
1737 | FORT BRAGG A 110195294 | 42761101 | FORT BRAGG A 1101 | 95294 | FALSE | 43494.7194 | 43494.7194 | 27.0321 | 186 | 0.00012237 | 1142 | 194.7256 | 1654 | 0.023449 | 4.3615 | 1589 | 0.05 | 2049
1091 | COLUMBIA HILL 1101764 | 152471101 | COLUMBIA HILL 1101 | 764 | FALSE | 23643.468 | 23643.468 | 14.6945 | 146 | 0.00012366 | 1128 | 171.5032 | 1710 | 0.023389 | 3.4148 | 1590 | 57.88 | 95
9377 | COVELO 1101516510 | 43061101 | COVELO 1101 | 516510 | FALSE | 13673.0725 | 6073.3479 | 3.7746 | 73 | 9.3061e-05 | 1818 | 270.871 | 1493 | 0.02337 | 1.706 | 1591 |  | 3347
2700 | PINE GROVE 11023172 | 163751102 | PINE GROVE 1102 | 3172 | FALSE | 60635.9905 | 60635.9905 | 37.6855 | 448 | 0.00020312 | 385 | 59.0594 | 2161 | 0.023346 | 10.4588 | 1592 | 67.49 | 73
10187 | LLAGAS 2105154256 | 83182105 | LLAGAS 2105 | 154256 | TRUE | 446.5228 | 430.6088 | 0.26763 | 2 | 0.00011705 | 1248 | 293.424 | 1459 | 0.023318 | 0.046636 | 1593 |  | 3510
8561 | FROGTOWN 1702307998 | 163451702 | FROGTOWN 1702 | 307998 | TRUE | 911.4775 | 895.4026 | 0.5565 | 6 | 0.00010251 | 1588 | 237.8428 | 1573 | 0.023314 | 0.13989 | 1594 |  | 3235
4078 | PENNGROVE 1101170 | 43471101 | PENNGROVE 1101 | 170 | FALSE | 33470.2158 | 28905.2433 | 17.9647 | 223 | 9.0997e-05 | 1881 | 278.3702 | 1476 | 0.023285 | 5.1925 | 1595 | 10.49 | 396
7270 | LAKEVILLE 1102347280 | 43371102 | LAKEVILLE 1102 | 347280 | FALSE | 20187.7037 | 12761.9341 | 7.9316 | 99 | 7.6036e-05 | 2307 | 290.5041 | 1463 | 0.023256 | 2.3024 | 1596 |  | 3109
2895 | ALHAMBRA 11058302 | 14101105 | ALHAMBRA 1105 | 8302 | FALSE | 13154.2224 | 13154.2224 | 8.1754 | 83 | 9.5232e-05 | 1760 | 244.7794 | 1556 | 0.023206 | 1.9261 | 1597 | 0.09 | 1552
9502 | WILLOW CREEK 11033090 | 192171103 | WILLOW CREEK 1103 | 3090 | FALSE | 17393.6531 | 17393.6531 | 10.8102 | 58 | 0.00018901 | 447 | 142.6437 | 1798 | 0.023177 | 1.3443 | 1598 | 0.06 | 1843
6394 | ORO FINO 11022040 | 103031102 | ORO FINO 1102 | 2040 | FALSE | 14724.8662 | 14724.8662 | 9.1516 | 21 | 0.00015655 | 679 | 141.5532 | 1807 | 0.023168 | 0.48652 | 1599 | 17.99 | 328
2990 | HICKS 2101XR548 | 83432101 | HICKS 2101 | XR548 | FALSE | 14288.8839 | 2708.1629 | 1.6831 | 95 | 8.7871e-05 | 1987 | 271.2652 | 1492 | 0.023159 | 2.2001 | 1600 | 0.04 | 2088
633 | RACETRACK 170310870 | 163761703 | RACETRACK 1703 | 10870 | FALSE | 4188.8092 | 3071.5505 | 1.909 | 28 | 0.00010127 | 1622 | 246.1327 | 1549 | 0.023077 | 0.64616 | 1601 | 0.04 | 2108
4692 | PINE GROVE 11023168 | 163751102 | PINE GROVE 1102 | 3168 | FALSE | 48228.3961 | 48228.3961 | 29.9741 | 285 | 0.00015583 | 684 | 176.2133 | 1695 | 0.023045 | 6.5678 | 1602 | 0.24 | 1095
10488 | HALF MOON BAY 1103531594 | 24101103 | HALF MOON BAY 1103 | 531594 | FALSE | 4284.5499 | 3998.7287 | 2.4852 | 25 | 5.9727e-05 | 2782 | 338.5434 | 1391 | 0.022917 | 0.57293 | 1603 |  | 3558
1419 | CURTIS 17048140 | 163351704 | CURTIS 1704 | 8140 | FALSE | 42456.9039 | 42456.9039 | 26.3871 | 260 | 8.2014e-05 | 2153 | 273.2886 | 1487 | 0.022915 | 5.958 | 1604 | 41.27 | 178
5050 | ATASCADERO 1101A22 | 182541101 | ATASCADERO 1101 | A22 | TRUE | 21048.1737 | 0 | 0 | 167 | 6.0117e-05 | 2769 | 362.8063 | 1349 | 0.022889 | 3.8224 | 1605 | 0.03 | 2288
10722 | TASSAJARA 2103557000 | 14662103 | TASSAJARA 2103 | 557000 | TRUE | 398.6933 | 335.0317 | 0.20822 | 3 | 0.00012959 | 1015 | 348.9375 | 1373 | 0.022855 | 0.068564 | 1606 |  | 3596
4033 | GANSNER 11012006 | 103021101 | GANSNER 1101 | 2006 | FALSE | 27571.1883 | 27571.1883 | 17.1356 | 151 | 6.0918e-05 | 2751 | 384.5024 | 1313 | 0.022834 | 3.4479 | 1607 | 0.22 | 1125
5518 | BIG BEND 1101641808 | 103751101 | BIG BEND 1101 | 641808 | FALSE | 41435.7029 | 41435.7029 | 25.7525 | 234 | 0.00014735 | 768 | 181.2789 | 1681 | 0.022822 | 5.3404 | 1608 | 0.36 | 973
8814 | CLAY 11037142 | 163341103 | CLAY 1103 | 7142 | FALSE | 24816.4121 | 6275.5413 | 3.9003 | 100 | 7.7237e-05 | 2282 | 356.2375 | 1361 | 0.022773 | 2.2773 | 1609 | 0.03 | 2276
9514 | HALF MOON BAY 110258448 | 24101102 | HALF MOON BAY 1102 | 58448 | FALSE | 7774.1256 | 7141.1012 | 4.4382 | 22 | 8.8643e-05 | 1966 | 261.6309 | 1519 | 0.022766 | 0.50086 | 1610 |  | 3368
4404 | EEL RIVER 1102630456 | 192381102 | EEL RIVER 1102 | 630456 | FALSE | 8616.6169 | 8616.6169 | 5.3553 | 37 | 0.00023208 | 277 | 84.9164 | 2030 | 0.022761 | 0.84216 | 1611 |  | 2888
9626 | SAUSALITO 110284278 | 42491102 | SAUSALITO 1102 | 84278 | FALSE | 2506.1692 | 2490.1671 | 1.5476 | 18 | 7.3083e-05 | 2392 | 245.6104 | 1553 | 0.022717 | 0.4089 | 1612 | 2.62 | 594
5345 | ELK 11011300 | 42981101 | ELK 1101 | 1300 | FALSE | 15995.4516 | 5711.2619 | 3.5496 | 64 | 8.5201e-05 | 2052 | 259.4524 | 1525 | 0.02261 | 1.447 | 1613 | 0.01 | 2613
3272 | KESWICK 11019712 | 103451101 | KESWICK 1101 | 9712 | FALSE | 29909.7326 | 29909.7326 | 18.589 | 214 | 0.00017251 | 547 | 156.1721 | 1761 | 0.022607 | 4.838 | 1614 | 0.65 | 825
7529 | EEL RIVER 11021902 | 192381102 | EEL RIVER 1102 | 1902 | FALSE | 11685.375 | 10562.7391 | 6.5648 | 43 | 0.00014928 | 746 | 134.194 | 1834 | 0.022585 | 0.97115 | 1615 | 0.08 | 1666
9292 | PUEBLO 2102895310 | 43292102 | PUEBLO 2102 | 895310 | TRUE | 4366.1321 | 592.9592 | 0.36853 | 31 | 6.4236e-05 | 2637 | 241.124 | 1565 | 0.022565 | 0.69951 | 1616 |  | 3336
3684 | VASCO 1102MR178 | 13751102 | VASCO 1102 | MR178 | FALSE | 21546.6859 | 2579.6297 | 1.6033 | 117 | 6.7557e-05 | 2547 | 427.86 | 1263 | 0.022562 | 2.6398 | 1617 |  | 2847
6059 | RINCON 1103198 | 43321103 | RINCON 1103 | 198 | FALSE | 10335.8179 | 10335.8179 | 6.4238 | 62 | 0.0001183 | 1224 | 193.0004 | 1658 | 0.02256 | 1.3987 | 1618 | 41.1 | 181
8232 | FOOTHILL 1101251688 | 182951101 | FOOTHILL 1101 | 251688 | FALSE | 12475.4445 | 11233.7101 | 6.9818 | 68 | 7.4101e-05 | 2355 | 394.4035 | 1300 | 0.022486 | 1.5291 | 1619 |  | 3207
9659 | CAMBRIA 1101858200 | 182771101 | CAMBRIA 1101 | 858200 | FALSE | 9571.0308 | 9200.2096 | 5.718 | 31 | 6.601e-05 | 2588 | 330.1244 | 1397 | 0.022446 | 0.69582 | 1620 |  | 3395
5819 | COTTONWOOD 110359128 | 102931103 | COTTONWOOD 1103 | 59128 | FALSE | 11301.2737 | 1201.9482 | 0.74702 | 65 | 0.00010017 | 1639 | 414.1368 | 1279 | 0.022397 | 1.4558 | 1621 |  | 2980
9234 | WILDWOOD 110185112 | 103611101 | WILDWOOD 1101 | 85112 | FALSE | 10932.2503 | 10932.2503 | 6.7944 | 54 | 7.2027e-05 | 2417 | 306.4662 | 1437 | 0.022386 | 1.2088 | 1622 | 0.07 | 1740
2051 | LAYTONVILLE 1101518 | 42681101 | LAYTONVILLE 1101 | 518 | FALSE | 36303.8238 | 4840.0159 | 3.0081 | 165 | 0.0001564 | 680 | 133.4232 | 1837 | 0.02237 | 3.6911 | 1623 | 0.31 | 1002
4400 | CALISTOGA 1102769230 | 42711102 | CALISTOGA 1102 | 769230 | FALSE | 27505.7293 | 17732.852 | 11.021 | 160 | 0.00011179 | 1372 | 159.0323 | 1749 | 0.022338 | 3.574 | 1624 | 0.28 | 1034
1232 | VOLTA 110237350 | 102541102 | VOLTA 1102 | 37350 | FALSE | 39069.9006 | 39069.9006 | 24.2821 | 255 | 7.6956e-05 | 2287 | 360.2031 | 1353 | 0.02227 | 5.6788 | 1625 | 13.94 | 359
1076 | MC ARTHUR 1101648698 | 103491101 | MC ARTHUR 1101 | 648698 | FALSE | 30462.3699 | 17135.0454 | 10.6495 | 173 | 2.2209e-05 | 3516 | 1031.0161 | 807 | 0.022255 | 3.85 | 1626 |  | 2707
6771 | HALSEY 1102CB | 152241102 | HALSEY 1102 | CB | FALSE | 12882.1278 | 12682.5013 | 7.8822 | 86 | 0.00028932 | 141 | 75.4177 | 2064 | 0.022172 | 1.9068 | 1627 | 0.07 | 1701
1966 | GARBERVILLE 11011514 | 192221101 | GARBERVILLE 1101 | 1514 | FALSE | 23767.6372 | 23767.6372 | 14.7717 | 123 | 0.0005607 | 23 | 46.0416 | 2239 | 0.022168 | 2.7266 | 1628 | 0.07 | 1675
7554 | SAN LUIS OBISPO 1105512313 | 182631105 | SAN LUIS OBISPO 1105 | 512313 | TRUE | 1333.0799 | 785.9125 | 0.48845 | 10 | 3.7023e-05 | 3314 | 418.9141 | 1273 | 0.022063 | 0.22063 | 1629 |  | 3136
6120 | PUEBLO 2103895784 | 43292103 | PUEBLO 2103 | 895784 | FALSE | 16727.2163 | 12538.91 | 7.793 | 110 | 8.3743e-05 | 2101 | 275.8868 | 1483 | 0.022046 | 2.4251 | 1630 |  | 3006
63 | CORRAL 110175204 | 162991101 | CORRAL 1101 | 75204 | FALSE | 29879.1855 | 1376.4738 | 0.85548 | 130 | 8.0747e-05 | 2187 | 212.0292 | 1614 | 0.021935 | 2.8515 | 1631 | 0.01 | 2584
9574 | MONROE 2103848530 | 43302103 | MONROE 2103 | 848530 | TRUE | 2567.2359 | 715.3706 | 0.44461 | 17 | 9.0059e-05 | 1909 | 263.7059 | 1513 | 0.021849 | 0.37143 | 1632 |  | 3381
7210 | WEST POINT 110234416 | 163201102 | WEST POINT 1102 | 34416 | FALSE | 16821.5127 | 16821.5127 | 10.4546 | 113 | 8.8542e-05 | 1971 | 264.2059 | 1510 | 0.021823 | 2.466 | 1633 | 42.3 | 170
2105 | WEST POINT 1102CB | 163201102 | WEST POINT 1102 | CB | FALSE | 28620.471 | 28620.471 | 17.7877 | 195 | 0.00020845 | 368 | 153.8768 | 1765 | 0.02173 | 4.2374 | 1634 | 37.1 | 202
6954 | WYANDOTTE 1110144140 | 102911110 | WYANDOTTE 1110 | 144140 | TRUE | 2469.4129 | 417.0111 | 0.25917 | 20 | 0.00015373 | 713 | 178.8701 | 1686 | 0.021719 | 0.43439 | 1635 |  | 3076
9884 | ELK 1101311906 | 42981101 | ELK 1101 | 311906 | FALSE | 1528.1122 | 1112.4459 | 0.69139 | 12 | 0.00010712 | 1471 | 200.1105 | 1641 | 0.021675 | 0.2601 | 1636 |  | 3445
1046 | GARBERVILLE 11028652 | 192221102 | GARBERVILLE 1102 | 8652 | FALSE | 21158.9046 | 21158.9046 | 13.1503 | 114 | 0.0003142 | 113 | 77.6007 | 2059 | 0.021633 | 2.4661 | 1637 | 8.55 | 422
3164 | BRUNSWICK 11062416 | 152481106 | BRUNSWICK 1106 | 2416 | FALSE | 50020.1074 | 46563.0328 | 28.9391 | 360 | 0.00016423 | 598 | 156.2016 | 1760 | 0.021547 | 7.7569 | 1638 | 0.56 | 863
3168 | LUCERNE 1103630 | 43351103 | LUCERNE 1103 | 630 | FALSE | 21891.4244 | 20012.2615 | 12.4377 | 154 | 9.5266e-05 | 1756 | 292.7922 | 1460 | 0.021529 | 3.3154 | 1639 | 0.13 | 1357
9831 | HALF MOON BAY 1101771258 | 24101101 | HALF MOON BAY 1101 | 771258 | TRUE | 308.3578 | 308.3578 | 0.19165 | 4 | 6.8099e-05 | 2532 | 427.9894 | 1262 | 0.021484 | 0.085935 | 1640 |  | 3432
8239 | FRUITLAND 11413902 | 192311141 | FRUITLAND 1141 | 3902 | FALSE | 8223.6344 | 8223.6344 | 5.111 | 9 | 0.00018188 | 498 | 110.945 | 1907 | 0.021389 | 0.1925 | 1641 | 0.02 | 2480
4880 | CURTIS 1705CB | 163351705 | CURTIS 1705 | CB | FALSE | 22023.4026 | 21461.232 | 13.3382 | 163 | 0.00013265 | 967 | 170.2363 | 1715 | 0.021383 | 3.4854 | 1642 | 0.14 | 1316
1762 | VINEYARD 2108609690 | 14502108 | VINEYARD 2108 | 609690 | FALSE | 12043.451 | 7774.3071 | 4.8318 | 72 | 7.5587e-05 | 2321 | 321.8791 | 1411 | 0.021383 | 1.5396 | 1643 |  | 2744
7400 | CLARKSVILLE 21096502 | 153612109 | CLARKSVILLE 2109 | 6502 | FALSE | 6145.0425 | 1500.682 | 0.93268 | 52 | 0.00017025 | 561 | 88.4192 | 2012 | 0.021251 | 1.1051 | 1644 | 1.73 | 647
10207 | MONTE RIO 111159046 | 42811111 | MONTE RIO 1111 | 59046 | FALSE | 6015.5462 | 5641.1576 | 3.506 | 15 | 0.00010509 | 1522 | 101.9046 | 1945 | 0.021246 | 0.31869 | 1645 | 0.25 | 1078
4878 | PLACERVILLE 21069712 | 153082106 | PLACERVILLE 2106 | 9712 | FALSE | 39765.9579 | 39765.9579 | 24.7147 | 226 | 0.00014908 | 750 | 116.696 | 1890 | 0.021241 | 4.8004 | 1646 | 0.54 | 877
2046 | LINCOLN 11042072 | 153701104 | LINCOLN 1104 | 2072 | TRUE | 27455.5664 | 501.4668 | 0.31166 | 193 | 9.3699e-05 | 1804 | 181.6575 | 1679 | 0.021197 | 4.091 | 1647 | 0.03 | 2308
7243 | SILVERADO 2104708 | 43432104 | SILVERADO 2104 | 708 | FALSE | 7904.2269 | 6040.8568 | 3.7544 | 61 | 0.00013285 | 959 | 152.2948 | 1771 | 0.02118 | 1.292 | 1648 | 0.54 | 876
593 | BRUNSWICK 11021010 | 152481102 | BRUNSWICK 1102 | 1010 | FALSE | 71394.2707 | 71394.2707 | 44.3718 | 479 | 0.00011001 | 1412 | 172.5805 | 1708 | 0.021168 | 10.1396 | 1649 | 129.45 | 6
5896 | CHALLENGE 11015460 | 103201101 | CHALLENGE 1101 | 5460 | FALSE | 18980.3372 | 18980.3372 | 11.7964 | 91 | 0.000114 | 1322 | 193.3663 | 1657 | 0.021116 | 1.9215 | 1650 | 41.43 | 176
9400 | BELL 110880680 | 152701108 | BELL 1108 | 80680 | FALSE | 2866.5185 | 1030.5857 | 0.64051 | 24 | 0.00023396 | 265 | 175.0191 | 1697 | 0.021095 | 0.50627 | 1651 | 0.04 | 2179
6134 | CALAVERAS CEMENT 110180930 | 162211101 | CALAVERAS CEMENT 1101 | 80930 | FALSE | 29528.4888 | 29528.4888 | 18.3521 | 180 | 6.8218e-05 | 2529 | 304.5139 | 1442 | 0.021019 | 3.7835 | 1652 | 0.22 | 1126
5626 | WYANDOTTE 1103CB | 102911103 | WYANDOTTE 1103 | CB | TRUE | 11751.5136 | 394.0047 | 0.24488 | 100 | 0.00016594 | 582 | 73.1844 | 2079 | 0.021017 | 2.1017 | 1653 | 0.02 | 2416
5183 | ALTO 1125902 | 42031125 | ALTO 1125 | 902 | FALSE | 19453.8935 | 19453.8935 | 12.0907 | 83 | 9.1473e-05 | 1858 | 227.244 | 1592 | 0.020905 | 1.7351 | 1654 | 0.72 | 798
7644 | LLAGAS 2101783467 | 83182101 | LLAGAS 2101 | 783467 | FALSE | 16521.4957 | 16448.6096 | 10.2229 | 61 | 8.018e-05 | 2201 | 245.1782 | 1554 | 0.020785 | 1.2679 | 1655 |  | 3145
7011 | MOUNTAIN QUARRIES 21011180 | 152282101 | MOUNTAIN QUARRIES 2101 | 1180 | FALSE | 20847.2086 | 20847.2086 | 12.9566 | 141 | 0.00012525 | 1094 | 118.9045 | 1874 | 0.020771 | 2.9287 | 1656 | 0.11 | 1417
11063 | APPLE HILL 1104814656 | 153661104 | APPLE HILL 1104 | 814656 | TRUE | 28.1252 | 28.1252 | 0.01748 | 1 | 0.00086571 | 4 | 23.8451 | 2401 | 0.020643 | 0.020643 | 1657 |  | 3634
9926 | BUCKS CREEK 1103CB | 102211103 | BUCKS CREEK 1103 | CB | FALSE | 3707.9332 | 3707.9332 | 2.3045 | 31 | 9.4015e-05 | 1792 | 320.4886 | 1415 | 0.020623 | 0.63931 | 1658 | 0.11 | 1444
3649 | FROGTOWN 1702812366 | 163451702 | FROGTOWN 1702 | 812366 | FALSE | 4450.8969 | 4421.1038 | 2.7477 | 28 | 8.5129e-05 | 2055 | 149.7437 | 1778 | 0.020596 | 0.57668 | 1659 |  | 2843
9417 | DUNBAR 1102694641 | 43071102 | DUNBAR 1102 | 694641 | FALSE | 6527.852 | 6527.852 | 4.0571 | 49 | 7.3209e-05 | 2390 | 257.8416 | 1526 | 0.020553 | 1.0071 | 1660 |  | 3355
8194 | STANISLAUS 17017144 | 162821701 | STANISLAUS 1701 | 7144 | FALSE | 7491.0055 | 7491.0055 | 4.6557 | 52 | 8.7335e-05 | 2005 | 376.542 | 1327 | 0.020479 | 1.0649 | 1661 | 0.36 | 967
10788 | FITCH MOUNTAIN 1111752596 | 42751111 | FITCH MOUNTAIN 1111 | 752596 | TRUE | 1041.1396 | 395.1334 | 0.24558 | 6 | 0.00010963 | 1418 | 256.5638 | 1530 | 0.020465 | 0.12279 | 1662 |  | 3606
3463 | WOODACRE 1102851 | 43021102 | WOODACRE 1102 | 851 | FALSE | 2029.0984 | 2029.0984 | 1.2611 | 14 | 0.00014146 | 845 | 190.4229 | 1662 | 0.020416 | 0.28582 | 1663 | 44.15 | 161
331 | WEST POINT 11024790 | 163201102 | WEST POINT 1102 | 4790 | FALSE | 52731.0383 | 52731.0383 | 32.7726 | 305 | 0.00011374 | 1325 | 232.2083 | 1584 | 0.020377 | 6.2151 | 1664 | 47.18 | 136
8939 | STELLING 111060080 | 83481110 | STELLING 1110 | 60080 | FALSE | 16285.3103 | 15418.9407 | 9.5829 | 64 | 0.00014044 | 864 | 185.0893 | 1672 | 0.020345 | 1.3021 | 1665 | 0.24 | 1091
5387 | PLACERVILLE 210611132 | 153082106 | PLACERVILLE 2106 | 11132 | FALSE | 69633.6958 | 69633.6958 | 43.2776 | 420 | 0.00012774 | 1054 | 197.2748 | 1649 | 0.020262 | 8.5102 | 1666 | 0.54 | 875
3326 | ORO FINO 110265932 | 103031102 | ORO FINO 1102 | 65932 | FALSE | 7276.7194 | 7276.7194 | 4.5225 | 48 | 0.00012509 | 1096 | 211.5152 | 1616 | 0.020219 | 0.97052 | 1667 | 64.62 | 78
7230 | PINE GROVE 110283098 | 163751102 | PINE GROVE 1102 | 83098 | FALSE | 12739.0077 | 12739.0077 | 7.9173 | 104 | 7.5775e-05 | 2312 | 344.4746 | 1378 | 0.020137 | 2.0942 | 1668 | 45.66 | 147
2235 | MOLINO 1102318 | 42571102 | MOLINO 1102 | 318 | FALSE | 31114.0365 | 31114.0365 | 19.3375 | 228 | 0.00011669 | 1256 | 178.6742 | 1688 | 0.020097 | 4.5821 | 1669 | 88.23 | 35
9552 | JOLON 11027068 | 182981102 | JOLON 1102 | 7068 | FALSE | 6155.1451 | 6139.1207 | 3.8155 | 12 | 7.071e-05 | 2451 | 336.2364 | 1392 | 0.019995 | 0.23993 | 1670 | 0.05 | 1997
7621 | UKIAH 1115CB | 42771115 | UKIAH 1115 | CB | FALSE | 10025.1577 | 6936.1203 | 4.3108 | 73 | 0.00013127 | 993 | 100.6191 | 1952 | 0.019906 | 1.4531 | 1671 | 0.05 | 1978
5118 | SAN LUIS OBISPO 1107V60 | 182631107 | SAN LUIS OBISPO 1107 | V60 | FALSE | 25811.5583 | 25811.5583 | 16.042 | 142 | 6.4335e-05 | 2632 | 354.0238 | 1367 | 0.0199 | 2.8258 | 1672 | 0.51 | 892
1916 | MOLINO 1104368158 | 42571104 | MOLINO 1104 | 368158 | FALSE | 14121.5307 | 4484.8758 | 2.7874 | 105 | 0.0001001 | 1644 | 219.1144 | 1607 | 0.019862 | 2.0855 | 1673 |  | 2756
8812 | ANTLER 11011376 | 103271101 | ANTLER 1101 | 1376 | FALSE | 14477.8455 | 14477.8455 | 8.998 | 70 | 0.00013205 | 982 | 179.7284 | 1683 | 0.019836 | 1.3885 | 1674 | 0.02 | 2535
3393 | SILVERADO 2102714 | 43432102 | SILVERADO 2102 | 714 | FALSE | 17594.5823 | 5568.6627 | 3.4609 | 121 | 0.0001288 | 1033 | 138.0832 | 1817 | 0.019829 | 2.3993 | 1675 | 0.08 | 1672
8102 | FORESTHILL 110175340 | 152181101 | FORESTHILL 1101 | 75340 | FALSE | 7696.0179 | 7696.0179 | 4.7831 | 62 | 0.00022111 | 314 | 112.7853 | 1902 | 0.01968 | 1.2202 | 1676 | 43.45 | 168
7713 | DUNBAR 11014817 | 43071101 | DUNBAR 1101 | 4817 | FALSE | 5079.2964 | 5079.2964 | 3.1568 | 42 | 0.00011215 | 1364 | 172.256 | 1709 | 0.019666 | 0.82599 | 1677 | 8.13 | 436
6368 | EAST QUINCY 1101951424 | 102551101 | EAST QUINCY 1101 | 951424 | FALSE | 5857.3043 | 1124.2371 | 0.69872 | 49 | 6.6606e-05 | 2568 | 260.8969 | 1522 | 0.019501 | 0.95554 | 1678 |  | 3026
6762 | HOOPA 11013304 | 192401101 | HOOPA 1101 | 3304 | FALSE | 27901.6416 | 27901.6416 | 17.341 | 88 | 0.00030684 | 123 | 72.4308 | 2081 | 0.019486 | 1.7148 | 1679 | 0.14 | 1315
4845 | SAN JOAQUIN #3 110210342 | 252531102 | SAN JOAQUIN #3 1102 | 10342 | FALSE | 2930.8819 | 2930.8819 | 1.8216 | 23 | 0.00012225 | 1143 | 225.3144 | 1595 | 0.019463 | 0.44766 | 1680 | 0.23 | 1111
3381 | LUCERNE 110638436 | 43351106 | LUCERNE 1106 | 38436 | FALSE | 7699.8876 | 7253.5318 | 4.5081 | 62 | 0.00011304 | 1342 | 129.1673 | 1847 | 0.019424 | 1.2043 | 1681 | 0.17 | 1243
8990 | HALF MOON BAY 1103540991 | 24101103 | HALF MOON BAY 1103 | 540991 | FALSE | 2594.6741 | 2544.5262 | 1.5814 | 16 | 6.9859e-05 | 2477 | 260.165 | 1524 | 0.019417 | 0.31068 | 1682 |  | 3290
1522 | RIO DELL 11021504 | 192251102 | RIO DELL 1102 | 1504 | FALSE | 19432.0475 | 17454.8051 | 10.8482 | 64 | 0.00027686 | 165 | 148.5088 | 1782 | 0.019342 | 1.2379 | 1683 | 0.01 | 2608
6286 | DUNBAR 1101416 | 43071101 | DUNBAR 1101 | 416 | FALSE | 5187.8358 | 4249.986 | 2.6414 | 28 | 0.00012384 | 1122 | 177.6431 | 1689 | 0.019316 | 0.54085 | 1684 | 0.35 | 975
2445 | MC ARTHUR 11011546 | 103491101 | MC ARTHUR 1101 | 1546 | FALSE | 37312.9087 | 22193.9329 | 13.7936 | 102 | 2.0489e-05 | 3539 | 794.3875 | 945 | 0.019258 | 1.9643 | 1685 | 0.02 | 2496
2748 | HALF MOON BAY 11036018 | 24101103 | HALF MOON BAY 1103 | 6018 | FALSE | 30239.5339 | 25219.5525 | 15.6741 | 160 | 8.5245e-05 | 2048 | 248.6459 | 1544 | 0.019223 | 3.0757 | 1686 | 0.05 | 1942
4766 | CLOVERDALE 1101807953 | 42821101 | CLOVERDALE 1101 | 807953 | TRUE | 1013.1517 | 745.8215 | 0.46353 | 11 | 0.00012129 | 1161 | 149.9335 | 1777 | 0.019176 | 0.21093 | 1687 |  | 2915
3508 | CLEAR LAKE 1102223792 | 42141102 | CLEAR LAKE 1102 | 223792 | FALSE | 1426.5673 | 1262.347 | 0.78455 | 10 | 7.6537e-05 | 2293 | 237.9603 | 1572 | 0.019106 | 0.19106 | 1688 |  | 2832
3278 | KONOCTI 1108CB | 43311108 | KONOCTI 1108 | CB | FALSE | 14256.0927 | 10229.3323 | 6.3576 | 98 | 0.00010673 | 1484 | 150.89 | 1774 | 0.019021 | 1.864 | 1689 | 0.06 | 1871
218 | MADISON 21017702 | 63172101 | MADISON 2101 | 7702 | TRUE | 30606.5708 | 0 | 0 | 168 | 8.5206e-05 | 2051 | 328.4397 | 1400 | 0.018893 | 3.174 | 1690 | 0.04 | 2103
5100 | RIO DELL 110270960 | 192251102 | RIO DELL 1102 | 70960 | FALSE | 18837.8278 | 9297.8122 | 5.7786 | 103 | 0.00023998 | 245 | 91.5029 | 1995 | 0.018609 | 1.9167 | 1691 | 0 | 2636
1226 | FORT ROSS 11212987 | 42851121 | FORT ROSS 1121 | 2987 | FALSE | 3171.9583 | 3171.9583 | 1.9714 | 18 | 0.0002636 | 186 | 74.107 | 2072 | 0.018603 | 0.33485 | 1692 | 15.92 | 343
4217 | CHALLENGE 1102CB | 103201102 | CHALLENGE 1102 | CB | FALSE | 24644.898 | 24644.898 | 15.3169 | 123 | 0.00014722 | 772 | 162.3912 | 1740 | 0.0185 | 2.2755 | 1693 | 73.53 | 61
4592 | PHILO 1102928 | 42601102 | PHILO 1102 | 928 | FALSE | 24779.274 | 22468.3871 | 13.9642 | 125 | 9.505e-05 | 1765 | 208.5932 | 1622 | 0.018489 | 2.3111 | 1694 | 0.05 | 2054
4143 | MENDOCINO 1101CB | 42951101 | MENDOCINO 1101 | CB | FALSE | 6642.1904 | 4240.0548 | 2.6352 | 54 | 0.00012016 | 1183 | 144.2308 | 1793 | 0.018327 | 0.98966 | 1695 | 0.11 | 1449
5556 | WEST POINT 11021305 | 163201102 | WEST POINT 1102 | 1305 | FALSE | 18201.3708 | 18201.3708 | 11.3122 | 105 | 0.00010838 | 1442 | 197.4917 | 1648 | 0.01831 | 1.9226 | 1696 | 0.76 | 784
7818 | SONOMA 1105575872 | 42721105 | SONOMA 1105 | 575872 | FALSE | 2328.1768 | 1906.857 | 1.1851 | 12 | 0.00010594 | 1497 | 157.6636 | 1757 | 0.018279 | 0.21935 | 1697 |  | 3165
1713 | HALF MOON BAY 1103H80 | 24101103 | HALF MOON BAY 1103 | H80 | FALSE | 31889.194 | 31889.194 | 19.8193 | 164 | 9.888e-05 | 1673 | 213.2657 | 1612 | 0.018248 | 2.9927 | 1698 |  | 2739
3304 | DIAMOND SPRINGS 11039432 | 152261103 | DIAMOND SPRINGS 1103 | 9432 | FALSE | 32768.2312 | 28100.4349 | 17.4645 | 251 | 0.0001473 | 771 | 86.1349 | 2022 | 0.018233 | 4.5765 | 1699 | 0.25 | 1080
1922 | ALLEGHANY 1102CB | 152101102 | ALLEGHANY 1102 | CB | FALSE | 28981.2992 | 28981.2992 | 18.012 | 104 | 0.00012953 | 1019 | 141.7915 | 1804 | 0.018204 | 1.8932 | 1700 | 44.04 | 162
4888 | DUNBAR 110179086 | 43071101 | DUNBAR 1101 | 79086 | FALSE | 11075.7434 | 10954.594 | 6.8083 | 82 | 0.00011015 | 1408 | 169.8424 | 1717 | 0.018179 | 1.4907 | 1701 | 0.08 | 1638
1290 | FROGTOWN 170232556 | 163451702 | FROGTOWN 1702 | 32556 | TRUE | 2113.2756 | 188.0999 | 0.1169 | 19 | 0.00017313 | 540 | 58.9098 | 2162 | 0.018147 | 0.34478 | 1702 | 0.05 | 2039
4459 | CLARK ROAD 11022094 | 103091102 | CLARK ROAD 1102 | 2094 | FALSE | 5517.0419 | 5517.0419 | 3.4289 | 11 | 0.00021985 | 323 | 101.8231 | 1947 | 0.018088 | 0.19897 | 1703 | 0.01 | 2580
8596 | SAN JOAQUIN #3 1101CB | 252531101 | SAN JOAQUIN #3 1101 | CB | FALSE | 19055.2866 | 19055.2866 | 11.8429 | 80 | 8.794e-05 | 1984 | 356.7774 | 1359 | 0.018079 | 1.4463 | 1704 | 0.23 | 1117
7985 | MERCED FALLS 1102482838 | 252811102 | MERCED FALLS 1102 | 482838 | FALSE | 17714.345 | 14284.261 | 8.8777 | 52 | 6.1569e-05 | 2730 | 318.0089 | 1421 | 0.018057 | 0.93898 | 1705 |  | 3180
5651 | MOUNTAIN QUARRIES 21012422 | 152282101 | MOUNTAIN QUARRIES 2101 | 2422 | FALSE | 13951.5772 | 13951.5772 | 8.671 | 81 | 0.00012199 | 1147 | 229.8045 | 1587 | 0.018043 | 1.4615 | 1706 | 0.07 | 1676
9070 | SILVERADO 2102437194 | 43432102 | SILVERADO 2102 | 437194 | FALSE | 1741.9129 | 1702.9792 | 1.0584 | 17 | 9.4479e-05 | 1781 | 148.2733 | 1783 | 0.018026 | 0.30645 | 1707 |  | 3303
2577 | HARTLEY 110186876 | 43211101 | HARTLEY 1101 | 86876 | FALSE | 13761.5335 | 3945.9351 | 2.4524 | 110 | 6.2134e-05 | 2715 | 110.516 | 1909 | 0.018007 | 1.9808 | 1708 | 0.03 | 2303
5850 | GEYSERVILLE 1101711966 | 42891101 | GEYSERVILLE 1101 | 711966 | FALSE | 19227.2924 | 6326.045 | 3.9317 | 122 | 9.0078e-05 | 1907 | 205.4077 | 1625 | 0.017908 | 2.1848 | 1709 |  | 2982
8508 | PIKE CITY 11011720 | 152201101 | PIKE CITY 1101 | 1720 | FALSE | 9489.0848 | 9489.0848 | 5.8975 | 34 | 6.9471e-05 | 2488 | 304.935 | 1440 | 0.017864 | 0.60738 | 1710 | 23.51 | 285
4021 | GRASS VALLEY 11012766 | 152031101 | GRASS VALLEY 1101 | 2766 | FALSE | 5300.562 | 5300.562 | 3.2943 | 31 | 0.00018321 | 487 | 59.8653 | 2154 | 0.017834 | 0.55287 | 1711 | 29.29 | 242
5421 | DUNBAR 1102261774 | 43071102 | DUNBAR 1102 | 261774 | FALSE | 21761.0718 | 21761.0718 | 13.5246 | 142 | 9.9916e-05 | 1650 | 183.8239 | 1678 | 0.01783 | 2.5319 | 1712 |  | 2952
1746 | TEMPLETON 2111CB | 183052111 | TEMPLETON 2111 | CB | FALSE | 17908.5118 | 3627.2584 | 2.2544 | 118 | 9.0618e-05 | 1894 | 263.1957 | 1514 | 0.017802 | 2.1007 | 1713 | 0.7 | 809
2820 | ALTO 1124432 | 42031124 | ALTO 1124 | 432 | FALSE | 12624.3351 | 12624.3351 | 7.8461 | 72 | 0.00017278 | 544 | 132.4511 | 1841 | 0.017729 | 1.2765 | 1714 | 0.96 | 740
5452 | PUEBLO 2102850102 | 43292102 | PUEBLO 2102 | 850102 | TRUE | 3948.9067 | 287.4404 | 0.17865 | 23 | 4.4232e-05 | 3186 | 279.8882 | 1472 | 0.01772 | 0.40756 | 1715 |  | 2955
3283 | CURTIS 170390320 | 163351703 | CURTIS 1703 | 90320 | FALSE | 44849.664 | 44849.664 | 27.8742 | 282 | 7.4079e-05 | 2356 | 382.5749 | 1315 | 0.017701 | 4.9917 | 1716 | 0.1 | 1463
3501 | CRESCENT MILLS 21012232 | 103132101 | CRESCENT MILLS 2101 | 2232 | FALSE | 32508.1294 | 25513.6468 | 15.8568 | 128 | 4.4844e-05 | 3165 | 539.0362 | 1160 | 0.017667 | 2.2614 | 1717 | 4.69 | 510
10143 | GRASS VALLEY 1101750804 | 152031101 | GRASS VALLEY 1101 | 750804 | TRUE | 449.416 | 390.0676 | 0.24243 | 5 | 0.00016489 | 588 | 71.3665 | 2087 | 0.017655 | 0.088275 | 1718 |  | 3500
3289 | MONTICELLO 11011589 | 43051101 | MONTICELLO 1101 | 1589 | FALSE | 6873.0951 | 6873.0951 | 4.2717 | 52 | 8.5041e-05 | 2058 | 184.9596 | 1673 | 0.01765 | 0.91781 | 1719 | 0.08 | 1649
1138 | ELECTRA 110136816 | 162161101 | ELECTRA 1101 | 36816 | FALSE | 8023.9266 | 8023.9266 | 4.9869 | 60 | 0.00012475 | 1102 | 139.9542 | 1810 | 0.017625 | 1.0575 | 1720 | 0.09 | 1516
9331 | WILLOW CREEK 1102CB | 192171102 | WILLOW CREEK 1102 | CB | FALSE | 11789.4236 | 11789.4236 | 7.3272 | 71 | 0.00029554 | 134 | 73.697 | 2075 | 0.017606 | 1.25 | 1721 | 13.84 | 360
6284 | ANTLER 11011378 | 103271101 | ANTLER 1101 | 1378 | FALSE | 40111.5829 | 39490.7149 | 24.5436 | 201 | 0.00013379 | 948 | 148.5755 | 1780 | 0.017574 | 3.5323 | 1722 | 0.05 | 2031
8843 | HOLLISTER 2104117328 | 182492104 | HOLLISTER 2104 | 117328 | FALSE | 23158.4732 | 9894.6539 | 6.1496 | 44 | 4.0861e-05 | 3248 | 400.677 | 1296 | 0.017549 | 0.77216 | 1723 |  | 3271
106 | WYANDOTTE 11101954 | 102911110 | WYANDOTTE 1110 | 1954 | FALSE | 17187.784 | 4223.5591 | 2.625 | 132 | 0.00016112 | 630 | 102.5688 | 1939 | 0.017468 | 2.3057 | 1724 | 0.07 | 1692
7269 | CURTIS 17046060 | 163351704 | CURTIS 1704 | 6060 | FALSE | 6540.8971 | 6540.8971 | 4.0652 | 50 | 0.00014094 | 855 | 178.7675 | 1687 | 0.01746 | 0.873 | 1725 | 0.1 | 1461
4024 | MOLINO 11015042 | 42571101 | MOLINO 1101 | 5042 | FALSE | 11222.6237 | 9737.3633 | 6.0518 | 90 | 0.0001242 | 1114 | 141.9193 | 1803 | 0.01743 | 1.5687 | 1726 | 6.17 | 471
8422 | FROGTOWN 1702739858 | 163451702 | FROGTOWN 1702 | 739858 | FALSE | 8002.9028 | 7850.7225 | 4.8793 | 46 | 0.00010369 | 1557 | 204.17 | 1632 | 0.017426 | 0.80161 | 1727 |  | 3225
3353 | KANAKA 11011406 | 103221101 | KANAKA 1101 | 1406 | FALSE | 43882.3619 | 43882.3619 | 27.2731 | 204 | 9.5492e-05 | 1742 | 157.7153 | 1755 | 0.017352 | 3.5397 | 1728 | 0.18 | 1217
10623 | MORGAN HILL 2111477914 | 83242111 | MORGAN HILL 2111 | 477914 | TRUE | 388.2883 | 307.8291 | 0.19132 | 3 | 0.00012285 | 1135 | 285.164 | 1467 | 0.017329 | 0.051987 | 1729 |  | 3582
1703 | SAN LUIS OBISPO 1105796050 | 182631105 | SAN LUIS OBISPO 1105 | 796050 | TRUE | 5067.2794 | 383.7484 | 0.2385 | 45 | 4.1549e-05 | 3233 | 109.4022 | 1911 | 0.017291 | 0.7781 | 1730 |  | 2738
2587 | MENLO 11031721 | 24131103 | MENLO 1103 | 1721 | FALSE | 10927.2973 | 10927.2973 | 6.7914 | 52 | 0.0001634 | 607 | 107.9769 | 1918 | 0.01726 | 0.89751 | 1731 | 0.12 | 1367
5617 | MIRABEL 1101298 | 42091101 | MIRABEL 1101 | 298 | FALSE | 20337.8041 | 20253.8323 | 12.5878 | 123 | 0.00016852 | 572 | 115.628 | 1892 | 0.017238 | 2.1202 | 1732 | 85.76 | 39
183 | CLEAR LAKE 110192870 | 42141101 | CLEAR LAKE 1101 | 92870 | TRUE | 25931.8169 | 185.9475 | 0.11557 | 187 | 6.3919e-05 | 2649 | 163.1162 | 1739 | 0.017207 | 3.2176 | 1733 | 2.3 | 615
5761 | SAN LUIS OBISPO 1102597518 | 182631102 | SAN LUIS OBISPO 1102 | 597518 | TRUE | 2581.15 | 65.1647 | 0.0405 | 30 | 4.6337e-05 | 3129 | 233.218 | 1579 | 0.017175 | 0.51524 | 1734 | 0.07 | 1768
694 | PIT NO 1 11013312 | 103721101 | PIT NO 1 1101 | 3312 | FALSE | 14682.6253 | 12944.3529 | 8.045 | 82 | 3.1897e-05 | 3403 | 501.3484 | 1197 | 0.017169 | 1.4079 | 1735 | 0.05 | 1934
6571 | MC ARTHUR 11011488 | 103491101 | MC ARTHUR 1101 | 1488 | FALSE | 53867.328 | 3970.6557 | 2.4678 | 217 | 3.7897e-05 | 3301 | 226.8447 | 1594 | 0.01714 | 3.7195 | 1736 | 0.01 | 2597
7993 | STILLWATER 1101CB | 103561101 | STILLWATER 1101 | CB | FALSE | 6895.2449 | 6754.5413 | 4.198 | 47 | 0.00021084 | 355 | 102.4575 | 1940 | 0.017137 | 0.80543 | 1737 | 0.07 | 1698
3453 | LOS GATOS 110760114 | 82021107 | LOS GATOS 1107 | 60114 | FALSE | 39130.9882 | 39130.9882 | 24.3201 | 220 | 0.00014614 | 787 | 173.2936 | 1702 | 0.016971 | 3.7337 | 1738 | 112.13 | 13
3503 | CLAYTON 2215184604 | 12022215 | CLAYTON 2215 | 184604 | FALSE | 16467.2376 | 3361.2922 | 2.0891 | 106 | 3.7123e-05 | 3311 | 169.9457 | 1716 | 0.016935 | 1.7951 | 1739 |  | 2831
5231 | BURNEY 1101CB | 103311101 | BURNEY 1101 | CB | FALSE | 3204.0009 | 1997.9569 | 1.2417 | 29 | 5.2977e-05 | 2969 | 262.0724 | 1517 | 0.016895 | 0.48997 | 1740 | 0.03 | 2250
5033 | ALTO 11243121 | 42031124 | ALTO 1124 | 3121 | FALSE | 4501.3904 | 4501.3904 | 2.7976 | 36 | 0.0001378 | 897 | 129.4168 | 1846 | 0.016885 | 0.60788 | 1741 | 54.14 | 108
4749 | FRUITLAND 11418860 | 192311141 | FRUITLAND 1141 | 8860 | FALSE | 6108.7785 | 3211.911 | 1.9962 | 34 | 0.0001502 | 733 | 173.1129 | 1705 | 0.016867 | 0.57347 | 1742 | 0.03 | 2306
8284 | FRENCH GULCH 11011464 | 103381101 | FRENCH GULCH 1101 | 1464 | FALSE | 1371.4854 | 1371.4854 | 0.85238 | 10 | 0.00011205 | 1368 | 126.5814 | 1854 | 0.01686 | 0.1686 | 1743 | 0.09 | 1538
10232 | TIGER CREEK 0201CB | 161380201 | TIGER CREEK 0201 | CB | FALSE | 6022.6718 | 6022.6718 | 3.7431 | 20 | 0.00011138 | 1387 | 174.7898 | 1698 | 0.016801 | 0.33603 | 1744 | 22.21 | 295
5809 | TEMPLETON 2110N32 | 183052110 | TEMPLETON 2110 | N32 | FALSE | 47644.4105 | 47470.9597 | 29.5034 | 251 | 5.7034e-05 | 2860 | 298.1993 | 1451 | 0.016765 | 4.208 | 1745 | 0.14 | 1326
7289 | PLACERVILLE 111019582 | 153081110 | PLACERVILLE 1110 | 19582 | FALSE | 11698.5344 | 11698.5344 | 7.2707 | 80 | 0.0001731 | 541 | 110.8991 | 1908 | 0.016762 | 1.341 | 1746 | 0.2 | 1168
9046 | OTTER 11022166 | 182941102 | OTTER 1102 | 2166 | FALSE | 6559.0006 | 6559.0006 | 4.0764 | 41 | 0.00012787 | 1051 | 196.1831 | 1652 | 0.016743 | 0.68648 | 1747 | 0.04 | 2069
3955 | GRAYS FLAT 0401CB | 102530401 | GRAYS FLAT 0401 | CB | FALSE | 17261.1138 | 17261.1138 | 10.7279 | 77 | 6.6357e-05 | 2581 | 354.4682 | 1366 | 0.016728 | 1.2881 | 1748 | 0.09 | 1562
4383 | FRUITLAND 114195324 | 192311141 | FRUITLAND 1141 | 95324 | FALSE | 10430.483 | 10430.483 | 6.4826 | 40 | 0.00024711 | 226 | 97.4816 | 1970 | 0.016671 | 0.66685 | 1749 | 0.05 | 1990
9718 | GARBERVILLE 1101323694 | 192221101 | GARBERVILLE 1101 | 323694 | FALSE | 10298.1869 | 10298.1869 | 6.4004 | 17 | 0.00023892 | 250 | 89.5148 | 2002 | 0.016661 | 0.28324 | 1750 |  | 3406
7551 | GARBERVILLE 1101438596 | 192221101 | GARBERVILLE 1101 | 438596 | FALSE | 17736.2716 | 17736.2716 | 11.0232 | 69 | 0.00028911 | 142 | 66.1845 | 2114 | 0.016624 | 1.1471 | 1751 |  | 3135
9937 | OTTER 11022002 | 182941102 | OTTER 1102 | 2002 | FALSE | 4546.6103 | 4546.6103 | 2.8257 | 27 | 9.936e-05 | 1659 | 177.0336 | 1690 | 0.01654 | 0.44657 | 1752 | 0.03 | 2271
5432 | ALLEGHANY 1101804 | 152101101 | ALLEGHANY 1101 | 804 | FALSE | 35223.4878 | 35223.4878 | 21.8915 | 163 | 9.1106e-05 | 1878 | 209.4933 | 1620 | 0.016525 | 2.6936 | 1753 | 22.85 | 291
6356 | NORTH BRANCH 110113496 | 163231101 | NORTH BRANCH 1101 | 13496 | FALSE | 8111.7845 | 3211.8845 | 1.9962 | 58 | 8.2907e-05 | 2132 | 168.1169 | 1725 | 0.016506 | 0.95734 | 1754 | 0.04 | 2107
249 | RINCON 1103CB | 43321103 | RINCON 1103 | CB | FALSE | 6066.7415 | 3931.2505 | 2.4433 | 41 | 0.00016438 | 593 | 84.7695 | 2033 | 0.016461 | 0.67489 | 1755 | 3.87 | 532
1025 | MARIPOSA 2101439030 | 254452101 | MARIPOSA 2101 | 439030 | FALSE | 31570.1115 | 31570.1115 | 19.621 | 200 | 4.6813e-05 | 3117 | 247.3908 | 1548 | 0.016434 | 3.2868 | 1756 | 0.34 | 978
8791 | GLENN 11012012 | 102601101 | GLENN 1101 | 2012 | FALSE | 48303.6952 | 3708.2991 | 2.3047 | 73 | 4.249e-05 | 3218 | 610.7432 | 1094 | 0.016401 | 1.1972 | 1757 | 0.01 | 2617
10780 | CALPINE 1144962 | 48011144 | CALPINE 1144 | 962 | FALSE | 6465.1165 | 6465.1165 | 4.0181 | 13 | 0.00010277 | 1576 | 122.9227 | 1861 | 0.01639 | 0.21307 | 1758 | 8.51 | 424
715 | ALTO 1124430 | 42031124 | ALTO 1124 | 430 | FALSE | 11355.5979 | 11355.5979 | 7.0575 | 92 | 0.00013784 | 896 | 143.4477 | 1796 | 0.016311 | 1.5006 | 1759 | 1.14 | 709
9633 | MONTE RIO 11131067 | 42811113 | MONTE RIO 1113 | 1067 | FALSE | 1306.3843 | 1306.3843 | 0.81192 | 11 | 0.00037762 | 75 | 25.9963 | 2377 | 0.016 | 0.176 | 1760 | 0.39 | 956
1412 | PLACERVILLE 1109CB | 153081109 | PLACERVILLE 1109 | CB | FALSE | 17781.8863 | 17449.8742 | 10.8452 | 133 | 0.00028585 | 146 | 98.8838 | 1960 | 0.015996 | 2.1275 | 1761 | 0.03 | 2400
8245 | BEAR VALLEY 210513430 | 252192105 | BEAR VALLEY 2105 | 13430 | FALSE | 21106.6036 | 21106.6036 | 13.1178 | 129 | 3.9032e-05 | 3286 | 375.4366 | 1329 | 0.015945 | 2.057 | 1762 | 23.77 | 282
8966 | MORAGA 1101772781 | 13801101 | MORAGA 1101 | 772781 | FALSE | 2316.7745 | 2316.7745 | 1.4399 | 12 | 0.00017201 | 551 | 85.3434 | 2027 | 0.015766 | 0.1892 | 1763 |  | 3286
3619 | PINE GROVE 11013166 | 163751101 | PINE GROVE 1101 | 3166 | FALSE | 19778.1528 | 19778.1528 | 12.2922 | 147 | 0.00014138 | 848 | 96.7473 | 1974 | 0.015763 | 2.3172 | 1764 | 0.13 | 1348
4486 | WEST POINT 1101CB | 163201101 | WEST POINT 1101 | CB | FALSE | 7713.2869 | 7713.2869 | 4.7938 | 20 | 0.0002169 | 332 | 123.6935 | 1859 | 0.015736 | 0.31472 | 1765 | 0.28 | 1044
3894 | BONNIE NOOK 110186696 | 152301101 | BONNIE NOOK 1101 | 86696 | FALSE | 15512.3886 | 15512.3886 | 9.641 | 86 | 0.00022753 | 293 | 118.1033 | 1879 | 0.015606 | 1.3421 | 1766 | 11.17 | 386
1913 | OLEMA 1101416 | 42291101 | OLEMA 1101 | 416 | FALSE | 26082.6279 | 26031.4486 | 16.1787 | 79 | 0.00016777 | 576 | 81.2878 | 2042 | 0.015542 | 1.2278 | 1767 | 0.36 | 968
2787 | PINE GROVE 11013170 | 163751101 | PINE GROVE 1101 | 3170 | FALSE | 64049.8846 | 64049.8846 | 39.8073 | 445 | 0.00014644 | 781 | 151.3568 | 1773 | 0.015534 | 6.9125 | 1768 | 0.47 | 907
8370 | SWIFT 2110XR332 | 83392110 | SWIFT 2110 | XR332 | FALSE | 29699.1922 | 29699.1922 | 18.4582 | 83 | 7.378e-05 | 2368 | 296.6239 | 1452 | 0.015532 | 1.2892 | 1769 | 0.12 | 1374
6569 | CURTIS 17058170 | 163351705 | CURTIS 1705 | 8170 | FALSE | 12697.6373 | 12388.5528 | 7.6995 | 109 | 0.00012036 | 1178 | 138.0395 | 1818 | 0.015509 | 1.6904 | 1770 | 0.24 | 1094
9835 | SPRING GAP 1702CB | 162831702 | SPRING GAP 1702 | CB | FALSE | 11971.7401 | 11971.7401 | 7.4405 | 18 | 8.5097e-05 | 2056 | 173.0854 | 1706 | 0.015422 | 0.27759 | 1771 | 0.15 | 1279
1693 | BUCKS CREEK 1103338520 | 102211103 | BUCKS CREEK 1103 | 338520 | FALSE | 12890.8329 | 12653.3631 | 7.8641 | 87 | 0.00011206 | 1367 | 151.4662 | 1772 | 0.015412 | 1.3409 | 1772 |  | 2737
4370 | OREGON TRAIL 11021584 | 103521102 | OREGON TRAIL 1102 | 1584 | FALSE | 20998.6153 | 20998.6153 | 13.0507 | 136 | 0.00015385 | 710 | 117.4189 | 1885 | 0.015387 | 2.0926 | 1773 | 0.14 | 1331
6223 | MOLINO 1101152 | 42571101 | MOLINO 1101 | 152 | FALSE | 16493.2298 | 2668.6977 | 1.6586 | 125 | 0.0001196 | 1193 | 103.0488 | 1937 | 0.015258 | 1.9072 | 1774 | 2.09 | 621
991 | PEORIA 170413494 | 163781704 | PEORIA 1704 | 13494 | FALSE | 12093.2449 | 4454.735 | 2.7686 | 93 | 8.9665e-05 | 1924 | 170.6202 | 1712 | 0.015212 | 1.4148 | 1775 | 2.55 | 598
10392 | VINEYARD 2108383748 | 14502108 | VINEYARD 2108 | 383748 | TRUE | 582.318 | 582.318 | 0.36191 | 4 | 0.00011476 | 1303 | 237.7564 | 1575 | 0.015207 | 0.060827 | 1776 |  | 3542
5782 | GARBERVILLE 11026084 | 192221102 | GARBERVILLE 1102 | 6084 | FALSE | 24635.3535 | 24635.3535 | 15.311 | 120 | 0.00027675 | 166 | 46.9926 | 2233 | 0.015158 | 1.8189 | 1777 | 0.26 | 1064
8670 | COTATI 1102462 | 42271102 | COTATI 1102 | 462 | FALSE | 6310.2369 | 4550.7014 | 2.8283 | 40 | 9.8301e-05 | 1683 | 125.2992 | 1858 | 0.015132 | 0.6053 | 1778 | 0.04 | 2104
5839 | SOLEDAD 21027048 | 182052102 | SOLEDAD 2102 | 7048 | FALSE | 47036.8755 | 18663.2877 | 11.5993 | 173 | 4.4641e-05 | 3172 | 271.6147 | 1491 | 0.015069 | 2.607 | 1779 | 0.05 | 2050
5090 | BRIDGEVILLE 1102CB | 192461102 | BRIDGEVILLE 1102 | CB | FALSE | 19625.3536 | 4723.1827 | 2.9355 | 52 | 0.00018739 | 458 | 86.4729 | 2019 | 0.015061 | 0.78316 | 1780 | 0 | 2627
10131 | CMC 1101CB | 183111101 | CMC 1101 | CB | FALSE | 3286.0633 | 3286.0633 | 2.0423 | 16 | 7.411e-05 | 2353 | 272.3255 | 1488 | 0.014989 | 0.23983 | 1781 | 0.06 | 1879
4953 | FRENCH GULCH 11021462 | 103381102 | FRENCH GULCH 1102 | 1462 | FALSE | 16147.0874 | 16116.0676 | 10.0162 | 51 | 0.00019151 | 435 | 137.3214 | 1821 | 0.01495 | 0.76245 | 1782 | 0.07 | 1710
8365 | GRASS VALLEY 110358498 | 152031103 | GRASS VALLEY 1103 | 58498 | FALSE | 3648.0777 | 1920.6561 | 1.1937 | 34 | 0.00025665 | 200 | 43.134 | 2259 | 0.01494 | 0.50797 | 1783 | 0.03 | 2375
4523 | TIDEWATER 210665866 | 14652106 | TIDEWATER 2106 | 65866 | FALSE | 13028.5461 | 5501.1432 | 3.419 | 65 | 4.6622e-05 | 3122 | 158.5163 | 1752 | 0.014918 | 0.9697 | 1784 | 0.04 | 2201
7430 | FOOTHILL 1101549904 | 182951101 | FOOTHILL 1101 | 549904 | TRUE | 8119.1519 | 250.4434 | 0.15565 | 54 | 6.4657e-05 | 2616 | 224.282 | 1596 | 0.014902 | 0.80473 | 1785 | 1.15 | 708
10743 | ANDERSON 1101909424 | 103261101 | ANDERSON 1101 | 909424 | TRUE | 642.3156 | 642.3156 | 0.3992 | 8 | 0.00010292 | 1571 | 136.9205 | 1825 | 0.014888 | 0.1191 | 1786 |  | 3602
6685 | OCEANO 1102749231 | 182601102 | OCEANO 1102 | 749231 | FALSE | 18200.1936 | 8940.1081 | 5.5563 | 141 | 6.0256e-05 | 2765 | 210.5727 | 1619 | 0.014847 | 2.0934 | 1787 |  | 3055
2541 | BRUNSWICK 110651486 | 152481106 | BRUNSWICK 1106 | 51486 | FALSE | 91205.7549 | 91205.7549 | 56.6847 | 656 | 0.00011965 | 1191 | 123.462 | 1860 | 0.014797 | 9.7068 | 1788 | 90.93 | 31
7750 | BRUNSWICK 110765574 | 152481107 | BRUNSWICK 1107 | 65574 | TRUE | 2814.0897 | 939.5268 | 0.58392 | 23 | 0.00030901 | 119 | 33.131 | 2321 | 0.014793 | 0.34024 | 1789 | 0.01 | 2582
5279 | MC ARTHUR 110137344 | 103491101 | MC ARTHUR 1101 | 37344 | TRUE | 14261.5059 | 181.3406 | 0.1127 | 75 | 2.2098e-05 | 3519 | 310.2738 | 1432 | 0.014768 | 1.1076 | 1790 | 0.01 | 2575
7132 | ANTLER 11011612 | 103271101 | ANTLER 1101 | 1612 | FALSE | 14766.2971 | 14766.2971 | 9.1773 | 86 | 0.00012715 | 1062 | 147.1224 | 1785 | 0.014748 | 1.2683 | 1791 | 0.03 | 2352
3386 | NEWBURG 1132665674 | 192151132 | NEWBURG 1132 | 665674 | TRUE | 2469.7606 | 698.7983 | 0.43431 | 20 | 0.00016815 | 574 | 82.7929 | 2037 | 0.014722 | 0.29443 | 1792 |  | 2823
7872 | PIT NO 1 110170952 | 103721101 | PIT NO 1 1101 | 70952 | FALSE | 2749.7949 | 2724.6488 | 1.6934 | 29 | 3.988e-05 | 3272 | 320.7855 | 1414 | 0.014692 | 0.42606 | 1793 | 0.06 | 1812
5114 | DUNBAR 110147964 | 43071101 | DUNBAR 1101 | 47964 | FALSE | 12397.0354 | 10475.6408 | 6.5107 | 68 | 0.00011035 | 1405 | 129.5748 | 1845 | 0.014662 | 0.99704 | 1794 | 0.39 | 958
7691 | POINT ARENA 110198224 | 43381101 | POINT ARENA 1101 | 98224 | FALSE | 3847.8762 | 3847.8762 | 2.3915 | 23 | 7.8885e-05 | 2238 | 166.5531 | 1730 | 0.014654 | 0.33704 | 1795 |  | 3151
2530 | BRUNSWICK 111061602 | 152481110 | BRUNSWICK 1110 | 61602 | FALSE | 17974.447 | 15796.3436 | 9.8175 | 137 | 0.00027732 | 164 | 142.021 | 1802 | 0.014648 | 2.0068 | 1796 | 0.06 | 1802
7167 | FRENCH GULCH 11012905 | 103381101 | FRENCH GULCH 1101 | 2905 | FALSE | 15594.3492 | 15594.3492 | 9.692 | 83 | 0.00011324 | 1339 | 142.3421 | 1801 | 0.014648 | 1.2158 | 1797 | 0.04 | 2182
4457 | HIGGINS 11041006 | 152691104 | HIGGINS 1104 | 1006 | FALSE | 32324.6992 | 17529.4826 | 10.8946 | 266 | 0.00017105 | 556 | 184.0652 | 1676 | 0.014639 | 3.8939 | 1798 | 0.05 | 1920
7710 | CARLOTTA 11214045 | 192291121 | CARLOTTA 1121 | 4045 | TRUE | 3179.9108 | 576.108 | 0.35805 | 18 | 0.00013215 | 979 | 114.5305 | 1897 | 0.014618 | 0.26312 | 1799 | 0.03 | 2324
9405 | SILVERADO 2105861266 | 43432105 | SILVERADO 2105 | 861266 | FALSE | 3852.0148 | 2503.894 | 1.5562 | 31 | 0.00018468 | 477 | 101.2826 | 1949 | 0.014616 | 0.45311 | 1800 |  | 3353
463 | WEIMAR 11012084 | 152491101 | WEIMAR 1101 | 2084 | FALSE | 29723.3403 | 29723.3403 | 18.4732 | 219 | 0.00012877 | 1034 | 131.3983 | 1843 | 0.014579 | 3.1928 | 1801 | 0.11 | 1414
3551 | WILLOW CREEK 11014904 | 192171101 | WILLOW CREEK 1101 | 4904 | FALSE | 29337.0631 | 29337.0631 | 18.2331 | 121 | 0.00023865 | 252 | 61.1434 | 2146 | 0.014552 | 1.7608 | 1802 | 0.44 | 925
6996 | KONOCTI 1102714370 | 43311102 | KONOCTI 1102 | 714370 | FALSE | 4274.3031 | 3423.0115 | 2.1274 | 28 | 8.0252e-05 | 2198 | 368.3867 | 1342 | 0.014533 | 0.40694 | 1803 |  | 3083
1102 | MC KEE 1107XR010 | 83531107 | MC KEE 1107 | XR010 | FALSE | 22011.3924 | 4483.0278 | 2.7862 | 160 | 7.8729e-05 | 2242 | 168.0653 | 1726 | 0.014407 | 2.3052 | 1804 | 0.05 | 1996
2551 | SOLEDAD 2102823854 | 182052102 | SOLEDAD 2102 | 823854 | FALSE | 6899.0553 | 3307.4207 | 2.0556 | 33 | 3.9519e-05 | 3276 | 363.6041 | 1348 | 0.01437 | 0.47422 | 1805 |  | 2786
2101 | SAN BENITO 210488772 | 182742104 | SAN BENITO 2104 | 88772 | FALSE | 69339.2928 | 39135.7756 | 24.323 | 474 | 6.1067e-05 | 2746 | 187.0188 | 1668 | 0.014358 | 6.8057 | 1806 | 0.2 | 1160
7410 | RIO DELL 11028852 | 192251102 | RIO DELL 1102 | 8852 | FALSE | 7650.5094 | 7473.9899 | 4.6451 | 46 | 0.00028421 | 148 | 54.47 | 2184 | 0.014354 | 0.66027 | 1807 | 0.05 | 1930
5404 | PIT NO 3 21011386 | 103732101 | PIT NO 3 2101 | 1386 | FALSE | 11052.9537 | 11052.9537 | 6.8695 | 47 | 6.3474e-05 | 2661 | 296.3406 | 1453 | 0.014294 | 0.67181 | 1808 | 0.01 | 2619
4186 | MARIPOSA 210110170 | 254452101 | MARIPOSA 2101 | 10170 | FALSE | 26253.3221 | 26253.3221 | 16.3165 | 149 | 4.8216e-05 | 3089 | 256.1773 | 1532 | 0.014293 | 2.1297 | 1809 | 83.16 | 40
7884 | SONOMA 11045661 | 42721104 | SONOMA 1104 | 5661 | FALSE | 8173.4897 | 4658.2663 | 2.8951 | 66 | 8.6364e-05 | 2026 | 169.0465 | 1721 | 0.014289 | 0.94309 | 1810 | 1.66 | 657
967 | DUNBAR 1102903030 | 43071102 | DUNBAR 1102 | 903030 | FALSE | 2341.4408 | 2341.4408 | 1.4552 | 17 | 0.00011468 | 1304 | 137.2956 | 1823 | 0.014278 | 0.24273 | 1811 |  | 2699
3516 | NARROWS 21022718 | 153132102 | NARROWS 2102 | 2718 | TRUE | 11657.4654 | 495.6422 | 0.30804 | 114 | 0.00022728 | 295 | 102.6178 | 1938 | 0.014276 | 1.6275 | 1812 | 0.04 | 2074
5103 | SAN LUIS OBISPO 1107V18 | 182631107 | SAN LUIS OBISPO 1107 | V18 | FALSE | 6444.7052 | 4344.0922 | 2.6999 | 41 | 3.6107e-05 | 3335 | 204.0579 | 1633 | 0.014215 | 0.5828 | 1813 | 0.08 | 1634
177 | KING CITY 11037038 | 182031103 | KING CITY 1103 | 7038 | FALSE | 35749.3707 | 29491.4615 | 18.3291 | 186 | 5.6518e-05 | 2873 | 250.588 | 1538 | 0.014161 | 2.6339 | 1814 | 0.12 | 1392
4472 | WEST POINT 110277204 | 163201102 | WEST POINT 1102 | 77204 | FALSE | 11918.386 | 11918.386 | 7.4073 | 68 | 0.00011817 | 1226 | 128.4194 | 1848 | 0.014094 | 0.95841 | 1815 |  | 2893
8017 | PIT NO 3 2101CB | 103732101 | PIT NO 3 2101 | CB | FALSE | 7292.0294 | 7292.0294 | 4.532 | 7 | 0.00010421 | 1546 | 1059.6264 | 793 | 0.01407 | 0.098493 | 1816 | 0.03 | 2309
4764 | ALLEGHANY 1101CB | 152101101 | ALLEGHANY 1101 | CB | FALSE | 7034.6563 | 7034.6563 | 4.3721 | 40 | 0.00012824 | 1044 | 93.9669 | 1986 | 0.014057 | 0.5623 | 1817 | 38.69 | 195
2091 | STELLING 111060094 | 83481110 | STELLING 1110 | 60094 | FALSE | 15867.8413 | 15867.8413 | 9.8619 | 95 | 0.00016875 | 569 | 93.9049 | 1987 | 0.014041 | 1.3339 | 1818 | 55.68 | 102
2701 | PEORIA 170567898 | 163781705 | PEORIA 1705 | 67898 | FALSE | 9738.6344 | 6917.4777 | 4.2992 | 70 | 0.00010226 | 1597 | 138.197 | 1816 | 0.014037 | 0.98259 | 1819 | 0.06 | 1819
8037 | CAYUCOS 1102613456 | 182551102 | CAYUCOS 1102 | 613456 | FALSE | 38029.4611 | 21637.0644 | 13.4475 | 145 | 5.8725e-05 | 2815 | 256.2574 | 1531 | 0.014028 | 2.0341 | 1820 |  | 3187
4958 | WILLOW CREEK 11035012 | 192171103 | WILLOW CREEK 1103 | 5012 | FALSE | 17904.0624 | 17904.0624 | 11.1274 | 131 | 0.00021567 | 337 | 62.8252 | 2137 | 0.014012 | 1.8356 | 1821 | 0.09 | 1569
1586 | MARTELL 110111244 | 163011101 | MARTELL 1101 | 11244 | FALSE | 34513.2878 | 33294.1457 | 20.6924 | 202 | 0.00014416 | 812 | 70.2755 | 2093 | 0.01399 | 2.826 | 1822 | 0.12 | 1385
8222 | DUNBAR 1102528 | 43071102 | DUNBAR 1102 | 528 | FALSE | 6520.0631 | 5521.142 | 3.4314 | 50 | 8.1342e-05 | 2172 | 173.339 | 1701 | 0.013987 | 0.69934 | 1823 | 0.08 | 1607
6649 | SAN LUIS OBISPO 1108337126 | 182631108 | SAN LUIS OBISPO 1108 | 337126 | FALSE | 3227.6651 | 1128.521 | 0.70138 | 28 | 3.3027e-05 | 3386 | 257.5116 | 1527 | 0.013964 | 0.39101 | 1824 |  | 3051
716 | LAKEVILLE 1102280 | 43371102 | LAKEVILLE 1102 | 280 | FALSE | 10907.0769 | 1106.406 | 0.68764 | 52 | 6.7218e-05 | 2553 | 180.7486 | 1682 | 0.013918 | 0.72376 | 1825 | 0.72 | 800
1162 | DUNBAR 1101302 | 43071101 | DUNBAR 1101 | 302 | FALSE | 16561.5527 | 14104.3324 | 8.7659 | 123 | 0.00011341 | 1335 | 134.8667 | 1832 | 0.013839 | 1.7022 | 1826 | 14.9 | 352
5443 | DUNBAR 1103534 | 43071103 | DUNBAR 1103 | 534 | FALSE | 27841.2407 | 25519.0889 | 15.8602 | 162 | 9.6936e-05 | 1715 | 161.0686 | 1743 | 0.01369 | 2.2178 | 1827 | 36.61 | 206
3834 | STILLWATER 11011320 | 103561101 | STILLWATER 1101 | 1320 | FALSE | 32275.3239 | 31878.2376 | 19.8125 | 179 | 0.00033316 | 101 | 41.1443 | 2271 | 0.013687 | 2.4499 | 1828 | 0.21 | 1149
3066 | SHADY GLEN 1102CB | 152431102 | SHADY GLEN 1102 | CB | FALSE | 34051.8134 | 34051.8134 | 21.1633 | 240 | 0.00019472 | 419 | 88.9032 | 2008 | 0.01359 | 3.2616 | 1829 | 21.63 | 299
8639 | GREEN VALLEY 2101135762 | 83192101 | GREEN VALLEY 2101 | 135762 | FALSE | 4515.3768 | 1189.5286 | 0.7393 | 28 | 9.6391e-05 | 1723 | 173.1219 | 1704 | 0.013539 | 0.3791 | 1830 |  | 3246
1363 | BURNEY 11011322 | 103311101 | BURNEY 1101 | 1322 | FALSE | 30035.9017 | 25851.0688 | 16.0665 | 81 | 4.4702e-05 | 3169 | 378.0361 | 1324 | 0.01351 | 1.0943 | 1831 | 0.03 | 2289
5427 | PENRYN 1103CB | 152561103 | PENRYN 1103 | CB | FALSE | 5107.0559 | 3866.6599 | 2.4031 | 37 | 0.00013283 | 961 | 86.715 | 2017 | 0.013499 | 0.49946 | 1832 | 0.57 | 862
8202 | DUNBAR 1102861496 | 43071102 | DUNBAR 1102 | 861496 | FALSE | 7188.816 | 7188.816 | 4.4679 | 51 | 8.7717e-05 | 1993 | 163.8005 | 1737 | 0.013491 | 0.68805 | 1833 |  | 3201
3776 | ALTO 1125510 | 42031125 | ALTO 1125 | 510 | FALSE | 11861.6385 | 11861.6385 | 7.3721 | 77 | 0.00017549 | 525 | 112.7525 | 1903 | 0.013466 | 1.0369 | 1834 | 48.83 | 124
2524 | PHILO 1102920 | 42601102 | PHILO 1102 | 920 | FALSE | 42024.2659 | 28596.0082 | 17.7725 | 258 | 8.9648e-05 | 1925 | 168.9827 | 1722 | 0.013411 | 3.4601 | 1835 | 0.09 | 1572
8287 | LUCERNE 11034624 | 43351103 | LUCERNE 1103 | 4624 | TRUE | 6101.7647 | 50.6724 | 0.031493 | 42 | 0.00012548 | 1090 | 117.1975 | 1886 | 0.013292 | 0.55825 | 1836 | 0.02 | 2483
3582 | SAN RAFAEL 1108516 | 42011108 | SAN RAFAEL 1108 | 516 | FALSE | 17602.5759 | 17602.5759 | 10.9401 | 135 | 0.00019441 | 420 | 70.1443 | 2094 | 0.013281 | 1.7929 | 1837 | 1.39 | 679
6863 | GREEN VALLEY 2101942143 | 83192101 | GREEN VALLEY 2101 | 942143 | FALSE | 13604.5625 | 8138.4591 | 5.0581 | 74 | 0.00011237 | 1358 | 105.0805 | 1928 | 0.013216 | 0.97798 | 1838 |  | 3068
7880 | POINT ARENA 110183354 | 43381101 | POINT ARENA 1101 | 83354 | FALSE | 8260.8147 | 8260.8147 | 5.1341 | 36 | 5.4313e-05 | 2936 | 210.679 | 1618 | 0.013182 | 0.47457 | 1839 | 0.05 | 1967
2799 | TASSAJARA 211238868 | 14662112 | TASSAJARA 2112 | 38868 | FALSE | 6917.0797 | 3119.1276 | 1.9386 | 61 | 0.00010371 | 1555 | 103.4846 | 1934 | 0.01315 | 0.80215 | 1840 | 0.02 | 2534
10912 | TOCALOMA 0241CB | 43150241 | TOCALOMA 0241 | CB | TRUE | 26.5151 | 26.5151 | 0.016479 | 1 | 7.8863e-05 | 2240 | 166.4117 | 1731 | 0.013124 | 0.013124 | 1841 | 0.04 | 2184
6124 | ANDERSON 1101CB | 103261101 | ANDERSON 1101 | CB | FALSE | 10780.8577 | 1904.2009 | 1.1835 | 85 | 9.0041e-05 | 1911 | 158.1087 | 1753 | 0.013117 | 1.115 | 1842 | 0.05 | 2028
6165 | BRUNSWICK 1105CB | 152481105 | BRUNSWICK 1105 | CB | FALSE | 2138.4101 | 1870.8826 | 1.1628 | 21 | 0.00038645 | 70 | 21.5686 | 2432 | 0.013096 | 0.27501 | 1843 | 20.42 | 305
9119 | SONOMA 1106296492 | 42721106 | SONOMA 1106 | 296492 | FALSE | 3708.9492 | 1270.5979 | 0.78968 | 29 | 7.4532e-05 | 2344 | 198.5181 | 1644 | 0.013092 | 0.37968 | 1844 |  | 3311
3902 | SOLEDAD 2102858388 | 182052102 | SOLEDAD 2102 | 858388 | FALSE | 13234.6519 | 7717.2675 | 4.7963 | 72 | 2.6749e-05 | 3476 | 315.5206 | 1423 | 0.013047 | 0.93942 | 1845 |  | 2860
6187 | JESSUP 11013383 | 103441101 | JESSUP 1101 | 3383 | FALSE | 3031.9376 | 2267.9133 | 1.4095 | 24 | 0.00010952 | 1421 | 99.0724 | 1957 | 0.012944 | 0.31066 | 1846 | 0.05 | 2040
4407 | APPLE HILL 210297982 | 153662102 | APPLE HILL 2102 | 97982 | FALSE | 15545.7354 | 15545.7354 | 9.6617 | 104 | 8.3073e-05 | 2130 | 187.9326 | 1666 | 0.012892 | 1.3407 | 1847 | 33.04 | 223
7041 | JAMESON 1105371694 | 63801105 | JAMESON 1105 | 371694 | TRUE | 6199.8125 | 365.7311 | 0.2273 | 40 | 6.8585e-05 | 2519 | 205.0285 | 1628 | 0.012819 | 0.51277 | 1848 |  | 3089
3447 | WYANDOTTE 11031974 | 102911103 | WYANDOTTE 1103 | 1974 | FALSE | 36068.6353 | 36068.6353 | 22.4168 | 259 | 8.2005e-05 | 2154 | 157.702 | 1756 | 0.012814 | 3.3188 | 1849 | 125.77 | 11
7950 | SONOMA 11033052 | 42721103 | SONOMA 1103 | 3052 | FALSE | 25170.0534 | 20257.093 | 12.5899 | 163 | 9.5443e-05 | 1745 | 138.2678 | 1815 | 0.012795 | 2.0855 | 1850 | 0.66 | 820
5166 | LOS GATOS 1106LB48 | 82021106 | LOS GATOS 1106 | LB48 | FALSE | 23668.374 | 23668.374 | 14.71 | 142 | 0.0001412 | 849 | 89.798 | 2000 | 0.012757 | 1.8115 | 1851 | 0.79 | 776
3055 | LAS POSITAS 2108MR190 | 14402108 | LAS POSITAS 2108 | MR190 | FALSE | 18265.303 | 1336.9264 | 0.83091 | 130 | 5.632e-05 | 2880 | 303.8443 | 1444 | 0.012744 | 1.6567 | 1852 | 0.03 | 2386
8820 | HICKS 2101CB | 83432101 | HICKS 2101 | CB | FALSE | 17493.6949 | 8660.4867 | 5.3825 | 20 | 9.4687e-05 | 1773 | 120.7431 | 1868 | 0.012742 | 0.25483 | 1853 |  | 3269
987 | OAKHURST 110310140 | 254421103 | OAKHURST 1103 | 10140 | FALSE | 26724.0842 | 26724.0842 | 16.6091 | 188 | 8.934e-05 | 1937 | 119.5136 | 1871 | 0.012696 | 2.3869 | 1854 | 1.03 | 724
1124 | COARSEGOLD 210210040 | 254432102 | COARSEGOLD 2102 | 10040 | FALSE | 28379.0201 | 28379.0201 | 17.6377 | 213 | 7.3465e-05 | 2385 | 189.319 | 1665 | 0.01266 | 2.6967 | 1855 | 0.64 | 829
6998 | PUEBLO 1104640 | 43291104 | PUEBLO 1104 | 640 | FALSE | 5054.3067 | 1636.7685 | 1.0173 | 43 | 9.1535e-05 | 1857 | 103.5522 | 1933 | 0.012658 | 0.54429 | 1856 | 0.06 | 1786
2113 | HALSEY 11025739 | 152241102 | HALSEY 1102 | 5739 | FALSE | 10731.8696 | 10731.8696 | 6.6699 | 74 | 0.00014982 | 740 | 107.9805 | 1917 | 0.012582 | 0.93104 | 1857 | 0.05 | 2052
9463 | ATASCADERO 1103A06 | 182541103 | ATASCADERO 1103 | A06 | TRUE | 3295.4951 | 441.6127 | 0.27446 | 27 | 6.1339e-05 | 2740 | 154.3644 | 1764 | 0.012566 | 0.33927 | 1858 | 23.54 | 284
673 | FLINT 110140666 | 152531101 | FLINT 1101 | 40666 | TRUE | 2641.929 | 575.1734 | 0.35747 | 18 | 0.00018607 | 467 | 44.5439 | 2250 | 0.012564 | 0.22615 | 1859 | 0.03 | 2374
6086 | SONOMA 1102113082 | 42721102 | SONOMA 1102 | 113082 | FALSE | 11746.8209 | 9857.3648 | 6.1264 | 75 | 8.9487e-05 | 1932 | 142.6253 | 1799 | 0.012535 | 0.94012 | 1860 |  | 3001
4138 | ORO FINO 11022096 | 103031102 | ORO FINO 1102 | 2096 | FALSE | 22772.919 | 22772.919 | 14.1535 | 129 | 9.8802e-05 | 1675 | 133.1159 | 1838 | 0.012531 | 1.6166 | 1861 | 53.86 | 110
8669 | HORSESHOE 1101663244 | 152571101 | HORSESHOE 1101 | 663244 | TRUE | 704.8457 | 464.3934 | 0.28862 | 6 | 6.412e-05 | 2640 | 270.589 | 1495 | 0.012526 | 0.075153 | 1862 |  | 3250
1101 | HOOPA 110137202 | 192401101 | HOOPA 1101 | 37202 | FALSE | 46485.9706 | 40065.4375 | 24.9008 | 190 | 0.00062222 | 16 | 17.2008 | 2500 | 0.012512 | 2.3773 | 1863 | 0.05 | 1933
1135 | LOS GATOS 1106LB44 | 82021106 | LOS GATOS 1106 | LB44 | FALSE | 31139.8726 | 31139.8726 | 19.3536 | 213 | 0.00014639 | 783 | 100.8516 | 1950 | 0.012499 | 2.6623 | 1864 | 1.29 | 690
5450 | FORESTHILL 11011802 | 152181101 | FORESTHILL 1101 | 1802 | FALSE | 35771.0229 | 35771.0229 | 22.2318 | 259 | 0.00015681 | 674 | 79.811 | 2049 | 0.012496 | 3.2365 | 1865 | 95.5 | 25
5898 | WISE 1102465074 | 152271102 | WISE 1102 | 465074 | FALSE | 7662.1855 | 7662.1855 | 4.7621 | 57 | 0.00013238 | 976 | 95.1304 | 1981 | 0.012495 | 0.7122 | 1866 |  | 2986
7150 | FRUITLAND 1141200856 | 192311141 | FRUITLAND 1141 | 200856 | FALSE | 4144.4334 | 4144.4334 | 2.5758 | 31 | 0.00022223 | 311 | 73.6449 | 2076 | 0.012452 | 0.38602 | 1867 |  | 3102
6814 | SAN ARDO 11017632 | 182191101 | SAN ARDO 1101 | 7632 | FALSE | 13210.2353 | 3566.1023 | 2.2163 | 35 | 2.897e-05 | 3441 | 263.7953 | 1512 | 0.012428 | 0.43499 | 1868 | 0.01 | 2590
4514 | SOLEDAD 2101526864 | 182052101 | SOLEDAD 2101 | 526864 | FALSE | 5659.7355 | 5008.6837 | 3.1129 | 18 | 5.2603e-05 | 2980 | 261.8161 | 1518 | 0.012408 | 0.22335 | 1869 |  | 2901
10395 | CLARKSVILLE 2109649874 | 153612109 | CLARKSVILLE 2109 | 649874 | TRUE | 608.4651 | 608.4651 | 0.37816 | 5 | 0.00011808 | 1227 | 142.79 | 1797 | 0.012324 | 0.061618 | 1870 |  | 3543
368 | POINT MORETTI 11015078 | 82931101 | POINT MORETTI 1101 | 5078 | FALSE | 23873.1972 | 23873.1972 | 14.8373 | 154 | 0.00030756 | 121 | 41.9114 | 2267 | 0.012313 | 1.8962 | 1871 | 17.59 | 330
4025 | CARLOTTA 1121CB | 192291121 | CARLOTTA 1121 | CB | FALSE | 37542.2534 | 4224.1485 | 2.6253 | 255 | 0.00013212 | 981 | 102.3882 | 1942 | 0.012302 | 3.1369 | 1872 | 0.03 | 2408
9319 | GONZALES 11013094 | 182131101 | GONZALES 1101 | 3094 | FALSE | 14546.7613 | 6578.8406 | 4.0888 | 63 | 6.4104e-05 | 2641 | 239.8109 | 1568 | 0.012298 | 0.77477 | 1873 | 0.06 | 1850
5655 | CHALLENGE 1101CB | 103201101 | CHALLENGE 1101 | CB | FALSE | 26652.3351 | 26652.3351 | 16.5645 | 128 | 0.00011861 | 1214 | 102.4016 | 1941 | 0.012215 | 1.5636 | 1874 | 82.53 | 43
9730 | MC KEE 1108976553 | 83531108 | MC KEE 1108 | 976553 | FALSE | 3112.5676 | 1744.6035 | 1.0843 | 20 | 6.6999e-05 | 2557 | 174.5173 | 1699 | 0.012197 | 0.24394 | 1875 |  | 3407
8214 | BRUNSWICK 1106CB | 152481106 | BRUNSWICK 1106 | CB | FALSE | 14175.8367 | 14066.7084 | 8.7425 | 88 | 0.00026507 | 182 | 43.8173 | 2253 | 0.012162 | 1.0703 | 1876 | 27.97 | 254
3779 | NOTRE DAME 1103317782 | 102041103 | NOTRE DAME 1103 | 317782 | TRUE | 6689.8142 | 874.1929 | 0.54331 | 53 | 0.00012534 | 1092 | 127.094 | 1852 | 0.012141 | 0.64349 | 1877 |  | 2852
1366 | HALF MOON BAY 11036014 | 24101103 | HALF MOON BAY 1103 | 6014 | FALSE | 19985.2036 | 9962.9663 | 6.192 | 106 | 7.6568e-05 | 2291 | 149.4232 | 1779 | 0.012138 | 1.2867 | 1878 | 0.02 | 2473
7316 | HOLLISTER 2102676164 | 182492102 | HOLLISTER 2102 | 676164 | TRUE | 4417.8948 | 487.5008 | 0.30298 | 26 | 4.5549e-05 | 3152 | 245.9244 | 1551 | 0.012062 | 0.3136 | 1879 |  | 3115
2140 | BRUNSWICK 1102CB | 152481102 | BRUNSWICK 1102 | CB | FALSE | 10098.7974 | 10098.7974 | 6.2764 | 73 | 0.000256 | 203 | 35.5525 | 2306 | 0.01204 | 0.87889 | 1880 | 11.22 | 385
9978 | FROGTOWN 1702411508 | 163451702 | FROGTOWN 1702 | 411508 | TRUE | 731.3696 | 726.7977 | 0.45171 | 6 | 0.00014592 | 790 | 114.8976 | 1896 | 0.012026 | 0.072157 | 1881 |  | 3464
5364 | FULTON 1104466 | 42561104 | FULTON 1104 | 466 | TRUE | 2421.8686 | 622.9644 | 0.38717 | 21 | 0.00011297 | 1345 | 121.2049 | 1867 | 0.01202 | 0.25243 | 1882 |  | 2947
916 | WYANDOTTE 1105329930 | 102911105 | WYANDOTTE 1105 | 329930 | FALSE | 19740.5748 | 10526.1812 | 6.5421 | 137 | 0.00012563 | 1085 | 89.3966 | 2004 | 0.012012 | 1.6456 | 1883 | 0.03 | 2300
4781 | SONOMA 1105539450 | 42721105 | SONOMA 1105 | 539450 | FALSE | 3896.0108 | 2403.5482 | 1.4938 | 28 | 9.1165e-05 | 1874 | 148.5497 | 1781 | 0.011978 | 0.33537 | 1884 |  | 2917
5493 | SHADY GLEN 11012768 | 152431101 | SHADY GLEN 1101 | 2768 | FALSE | 13051.8561 | 12269.0577 | 7.6253 | 88 | 0.00012814 | 1045 | 88.7266 | 2009 | 0.011963 | 1.0528 | 1885 | 7.41 | 445
8268 | LLAGAS 2101587857 | 83182101 | LLAGAS 2101 | 587857 | TRUE | 3120.9828 | 171.8621 | 0.10681 | 28 | 8.567e-05 | 2038 | 73.8505 | 2073 | 0.011944 | 0.33442 | 1886 |  | 3211
1441 | MIWUK 170111800 | 163661701 | MIWUK 1701 | 11800 | FALSE | 15325.4468 | 15325.4468 | 9.5248 | 116 | 9.1188e-05 | 1873 | 242.093 | 1561 | 0.011866 | 1.3764 | 1887 | 49.43 | 123
2749 | ELK 1101900 | 42981101 | ELK 1101 | 900 | FALSE | 34419.9463 | 14125.5477 | 8.7791 | 185 | 5.5462e-05 | 2901 | 228.3452 | 1591 | 0.011859 | 2.1939 | 1888 | 0.01 | 2598
1288 | CALAVERAS CEMENT 11012646 | 162211101 | CALAVERAS CEMENT 1101 | 2646 | FALSE | 28413.9838 | 28413.9838 | 17.6594 | 149 | 0.00010253 | 1586 | 176.2359 | 1694 | 0.01184 | 1.7642 | 1889 |  | 2720
8429 | FOOTHILL 1101386844 | 182951101 | FOOTHILL 1101 | 386844 | TRUE | 2561.2262 | 615.6019 | 0.3826 | 19 | 4.5617e-05 | 3150 | 232.4795 | 1583 | 0.01183 | 0.22478 | 1890 |  | 3226
6057 | LLAGAS 2101XR264 | 83182101 | LLAGAS 2101 | XR264 | TRUE | 33068.0694 | 0 | 0 | 258 | 7.958e-05 | 2219 | 168.5722 | 1723 | 0.011726 | 3.0254 | 1891 | 0.77 | 783
5358 | UKIAH 1113968652 | 42771113 | UKIAH 1113 | 968652 | FALSE | 3017.7923 | 1606.1834 | 0.99825 | 25 | 0.00010466 | 1539 | 114.1474 | 1898 | 0.011684 | 0.2921 | 1892 |  | 2946
9622 | SAN RAFAEL 110863598 | 42011108 | SAN RAFAEL 1108 | 63598 | FALSE | 3076.8023 | 3076.8023 | 1.9122 | 24 | 0.0001935 | 427 | 74.3537 | 2071 | 0.011681 | 0.28035 | 1893 | 50.16 | 120
6523 | ALTO 1124870444 | 42031124 | ALTO 1124 | 870444 | FALSE | 4770.1261 | 4746.504 | 2.95 | 35 | 0.00012787 | 1050 | 122.3071 | 1864 | 0.011666 | 0.40831 | 1894 |  | 3038
4747 | SANTA ROSA A 1104716 | 42151104 | SANTA ROSA A 1104 | 716 | FALSE | 14319.9438 | 14319.9438 | 8.8999 | 109 | 0.00010523 | 1513 | 113.9799 | 1900 | 0.01165 | 1.2698 | 1895 | 14.14 | 357
9188 | HALF MOON BAY 1102350336 | 24101102 | HALF MOON BAY 1102 | 350336 | FALSE | 2699.1632 | 1936.9418 | 1.2038 | 13 | 7.7558e-05 | 2276 | 139.0255 | 1813 | 0.011629 | 0.15117 | 1896 |  | 3323
10068 | SAN LUIS OBISPO 1108809986 | 182631108 | SAN LUIS OBISPO 1108 | 809986 | FALSE | 3460.671 | 1661.0044 | 1.0323 | 18 | 4.7551e-05 | 3100 | 119.23 | 1872 | 0.011626 | 0.20927 | 1897 |  | 3484
3493 | MARTELL 110198374 | 163011101 | MARTELL 1101 | 98374 | FALSE | 6103.4021 | 1330.8093 | 0.8271 | 46 | 0.00011986 | 1189 | 56.1694 | 2175 | 0.011616 | 0.53436 | 1898 | 0.02 | 2442
3767 | HOLLISTER 210491424 | 182492104 | HOLLISTER 2104 | 91424 | TRUE | 14089.3649 | 303.1658 | 0.18842 | 95 | 6.4005e-05 | 2646 | 160.2049 | 1745 | 0.01155 | 1.0973 | 1899 | 0.02 | 2546
7603 | CLOVERDALE 1102262 | 42821102 | CLOVERDALE 1102 | 262 | FALSE | 9547.2777 | 2067.1657 | 1.2848 | 61 | 0.00010047 | 1637 | 112.2285 | 1905 | 0.011548 | 0.70445 | 1900 | 0.05 | 1983
712 | SILVERADO 2105247660 | 43432105 | SILVERADO 2105 | 247660 | FALSE | 5200.0544 | 3858.4886 | 2.3981 | 35 | 8.3565e-05 | 2111 | 144.077 | 1794 | 0.011541 | 0.40392 | 1901 |  | 2689
4631 | BRUNSWICK 11052210 | 152481105 | BRUNSWICK 1105 | 2210 | FALSE | 36938.5346 | 36938.5346 | 22.9574 | 280 | 9.2627e-05 | 1829 | 84.7902 | 2032 | 0.01151 | 3.2229 | 1902 | 105.34 | 19
1236 | OAKHURST 11035480 | 254421103 | OAKHURST 1103 | 5480 | FALSE | 27352.0687 | 27352.0687 | 16.9994 | 180 | 7.0805e-05 | 2447 | 169.2363 | 1720 | 0.011505 | 2.0709 | 1903 | 0.6 | 854
2425 | PIT NO 3 21011360 | 103732101 | PIT NO 3 2101 | 1360 | FALSE | 36445.2787 | 36106.6297 | 22.4404 | 92 | 4.8938e-05 | 3066 | 304.0594 | 1443 | 0.011504 | 1.0584 | 1904 | 0.01 | 2568
9598 | MILPITAS 1109XR044 | 82831109 | MILPITAS 1109 | XR044 | TRUE | 3013.9349 | 677.8018 | 0.42126 | 18 | 0.00010855 | 1434 | 79.5829 | 2050 | 0.011436 | 0.20585 | 1905 | 0.02 | 2555
3999 | CALAVERAS CEMENT 11011419 | 162211101 | CALAVERAS CEMENT 1101 | 1419 | FALSE | 24160.9517 | 24160.9517 | 15.0161 | 130 | 6.2459e-05 | 2706 | 145.1035 | 1792 | 0.011428 | 1.4856 | 1906 | 0.17 | 1249
3421 | HIGGINS 1104324510 | 152691104 | HIGGINS 1104 | 324510 | FALSE | 20073.6016 | 20073.6016 | 12.4758 | 154 | 6.2523e-05 | 2702 | 194.5257 | 1656 | 0.011404 | 1.7562 | 1907 | 0.14 | 1320
6037 | COARSEGOLD 210210050 | 254432102 | COARSEGOLD 2102 | 10050 | FALSE | 11290.6239 | 11290.6239 | 7.0172 | 81 | 9.8289e-05 | 1684 | 101.871 | 1946 | 0.01137 | 0.92095 | 1908 | 0.52 | 888
942 | WEST POINT 110293116 | 163201102 | WEST POINT 1102 | 93116 | FALSE | 68103.7314 | 68103.7314 | 42.3267 | 453 | 9.1189e-05 | 1872 | 118.4962 | 1875 | 0.011348 | 5.1406 | 1909 | 26.17 | 268
1810 | CABRILLO 1104CB | 183101104 | CABRILLO 1104 | CB | FALSE | 27455.7877 | 6641.9361 | 4.128 | 121 | 2.9423e-05 | 3434 | 158.5842 | 1751 | 0.011318 | 1.3695 | 1910 | 0.05 | 2010
1626 | MOLINO 110251788 | 42571102 | MOLINO 1102 | 51788 | FALSE | 20901.6945 | 8188.5748 | 5.0892 | 153 | 0.00012561 | 1087 | 89.1639 | 2005 | 0.011264 | 1.7234 | 1911 | 0.7 | 807
6259 | RISING RIVER 11019032 | 103551101 | RISING RIVER 1101 | 9032 | FALSE | 37853.3581 | 36827.5633 | 22.8885 | 175 | 3.6108e-05 | 3334 | 413.8546 | 1280 | 0.011207 | 1.9611 | 1912 | 0.02 | 2552
1825 | FORT BRAGG A 11014622 | 42761101 | FORT BRAGG A 1101 | 4622 | FALSE | 21650.6648 | 21650.6648 | 13.456 | 109 | 0.00028635 | 145 | 73.5891 | 2077 | 0.011136 | 1.2138 | 1913 | 0.1 | 1454
5920 | CASTRO VALLEY 1110MR243 | 14091110 | CASTRO VALLEY 1110 | MR243 | FALSE | 8929.805 | 8929.805 | 5.5499 | 72 | 8.9046e-05 | 1946 | 128.0484 | 1849 | 0.011084 | 0.79807 | 1914 |  | 2988
3864 | PLACER 1103429574 | 152461103 | PLACER 1103 | 429574 | FALSE | 15346.7415 | 8004.0474 | 4.9745 | 114 | 0.00019074 | 439 | 99.3413 | 1955 | 0.011083 | 1.2634 | 1915 |  | 2857
4013 | LAURELES 1111CB | 182371111 | LAURELES 1111 | CB | FALSE | 13124.836 | 11515.5312 | 7.1569 | 82 | 7.3716e-05 | 2370 | 185.6036 | 1669 | 0.011075 | 0.90815 | 1916 | 0.07 | 1709
9810 | MENLO 11028896 | 24131102 | MENLO 1102 | 8896 | FALSE | 2488.0112 | 1537.9857 | 0.95586 | 14 | 0.00022997 | 285 | 52.1302 | 2200 | 0.011065 | 0.15491 | 1917 | 2.98 | 570
8395 | CARLOTTA 112142896 | 192291121 | CARLOTTA 1121 | 42896 | FALSE | 8829.785 | 3686.5968 | 2.2912 | 71 | 0.00019577 | 414 | 80.3834 | 2046 | 0.011029 | 0.78303 | 1918 | 0.04 | 2101
5390 | SOLEDAD 2102304826 | 182052102 | SOLEDAD 2102 | 304826 | FALSE | 14243.5781 | 8398.3076 | 5.2196 | 61 | 1.8551e-05 | 3558 | 384.6024 | 1312 | 0.010995 | 0.6707 | 1919 |  | 2949
4943 | PINE GROVE 1102CB | 163751102 | PINE GROVE 1102 | CB | FALSE | 17461.9206 | 17461.9206 | 10.8527 | 136 | 0.00014936 | 745 | 159.9625 | 1746 | 0.010952 | 1.4895 | 1920 | 17.74 | 329
2277 | ORO FINO 11022560 | 103031102 | ORO FINO 1102 | 2560 | FALSE | 26913.6157 | 26913.6157 | 16.7269 | 179 | 8.9581e-05 | 1928 | 135.7772 | 1829 | 0.010913 | 1.9534 | 1921 | 75.77 | 57
8219 | CAMPHORA 1101613562 | 182071101 | CAMPHORA 1101 | 613562 | FALSE | 9602.6341 | 5945.3079 | 3.695 | 29 | 4.482e-05 | 3166 | 198.1499 | 1645 | 0.010904 | 0.31622 | 1922 |  | 3204
8001 | MOLINO 1102189602 | 42571102 | MOLINO 1102 | 189602 | FALSE | 1011.2208 | 1011.2208 | 0.62848 | 9 | 0.00010514 | 1518 | 134.7619 | 1833 | 0.010902 | 0.098117 | 1923 |  | 3183
8797 | CAMP EVERS 210533542 | 83622105 | CAMP EVERS 2105 | 33542 | FALSE | 4316.4835 | 4316.4835 | 2.6827 | 39 | 0.00031343 | 114 | 29.934 | 2346 | 0.010901 | 0.42515 | 1924 | 20.17 | 307
6026 | ROSSMOOR 110837848 | 14161108 | ROSSMOOR 1108 | 37848 | FALSE | 9580.5994 | 9580.5994 | 5.9544 | 60 | 7.1725e-05 | 2430 | 176.9482 | 1691 | 0.010901 | 0.65406 | 1925 | 39.39 | 189
9862 | MONTE RIO 11113891 | 42811111 | MONTE RIO 1111 | 3891 | FALSE | 5583.0951 | 5583.0951 | 3.4699 | 23 | 0.0002266 | 300 | 68.3151 | 2101 | 0.010887 | 0.2504 | 1926 | 21.8 | 297
9761 | HALF MOON BAY 1103341542 | 24101103 | HALF MOON BAY 1103 | 341542 | FALSE | 10584.332 | 9768.7602 | 6.0713 | 47 | 8.7167e-05 | 2009 | 161.0484 | 1744 | 0.010885 | 0.5116 | 1927 |  | 3412
6971 | WILLOW CREEK 11037514 | 192171103 | WILLOW CREEK 1103 | 7514 | FALSE | 16121.906 | 14595.7178 | 9.0713 | 118 | 0.00025507 | 206 | 51.2832 | 2206 | 0.010882 | 1.2841 | 1928 | 4.42 | 519
8324 | MONTE RIO 1112999 | 42811112 | MONTE RIO 1112 | 999 | FALSE | 1412.3755 | 1412.3755 | 0.8778 | 7 | 0.00015392 | 709 | 122.3126 | 1863 | 0.010787 | 0.075506 | 1929 | 28.44 | 250
3097 | ATASCADERO 1103492068 | 182541103 | ATASCADERO 1103 | 492068 | FALSE | 13334.8935 | 11954.6281 | 7.4298 | 75 | 6.9325e-05 | 2495 | 169.7517 | 1718 | 0.010772 | 0.80789 | 1930 |  | 2812
1425 | CLAY 110184572 | 163341101 | CLAY 1101 | 84572 | TRUE | 3629.8323 | 844.7995 | 0.52505 | 27 | 6.1461e-05 | 2735 | 146.1205 | 1788 | 0.010769 | 0.29075 | 1931 | 0.05 | 2022
8269 | COTATI 1105893 | 42271105 | COTATI 1105 | 893 | TRUE | 16957.7992 | 312.2303 | 0.19405 | 91 | 8.78e-05 | 1990 | 114.1416 | 1899 | 0.010724 | 0.9759 | 1932 | 0.02 | 2482
1839 | VOLTA 11021650 | 102541102 | VOLTA 1102 | 1650 | FALSE | 34931.9743 | 34931.9743 | 21.7104 | 154 | 4.7419e-05 | 3105 | 252.2302 | 1537 | 0.010701 | 1.6479 | 1933 | 0.12 | 1379
5835 | APPLE HILL 110497086 | 153661104 | APPLE HILL 1104 | 97086 | FALSE | 41345.0987 | 41345.0987 | 25.6961 | 301 | 7.7565e-05 | 2275 | 132.4839 | 1840 | 0.010689 | 3.2174 | 1934 | 48.08 | 132
7014 | ALTO 1122591122 | 42031122 | ALTO 1122 | 591122 | TRUE | 748.6821 | 748.6821 | 0.46531 | 7 | 0.00022033 | 319 | 51.0001 | 2207 | 0.010649 | 0.074542 | 1935 |  | 3085
1545 | MARTELL 110191216 | 163011101 | MARTELL 1101 | 91216 | FALSE | 65291.6361 | 65291.6361 | 40.579 | 380 | 8.9695e-05 | 1922 | 143.7419 | 1795 | 0.010587 | 4.0231 | 1936 | 0.25 | 1085
812 | DUNBAR 1102246 | 43071102 | DUNBAR 1102 | 246 | FALSE | 21497.7557 | 21497.7557 | 13.3609 | 148 | 0.00011216 | 1363 | 98.1055 | 1967 | 0.010561 | 1.563 | 1937 | 6.5 | 466
6481 | DEL MONTE 21043088 | 182222104 | DEL MONTE 2104 | 3088 | FALSE | 24808.0862 | 24808.0862 | 15.4183 | 175 | 7.2041e-05 | 2415 | 135.1128 | 1831 | 0.010503 | 1.8381 | 1938 | 0.12 | 1369
336 | CAMBRIA 1102CB | 182771102 | CAMBRIA 1102 | CB | FALSE | 37414.4172 | 25753.259 | 16.0058 | 153 | 5.557e-05 | 2899 | 155.1527 | 1763 | 0.010468 | 1.6015 | 1939 | 0.06 | 1833
3334 | VOLTA 110297816 | 102541102 | VOLTA 1102 | 97816 | FALSE | 8457.2763 | 8457.2763 | 5.2562 | 50 | 4.697e-05 | 3114 | 169.4239 | 1719 | 0.010402 | 0.52009 | 1940 | 0.19 | 1193
1241 | CALAVERAS CEMENT 110147968 | 162211101 | CALAVERAS CEMENT 1101 | 47968 | FALSE | 65100.4862 | 65100.4862 | 40.4602 | 306 | 5.7195e-05 | 2856 | 229.0575 | 1588 | 0.010385 | 3.1777 | 1941 | 0.12 | 1380
8572 | LOS GATOS 110760024 | 82021107 | LOS GATOS 1107 | 60024 | FALSE | 6398.0407 | 6398.0407 | 3.9764 | 27 | 8.433e-05 | 2081 | 118.0471 | 1880 | 0.010381 | 0.28029 | 1942 | 22.82 | 292
8425 | PINE GROVE 110194936 | 163751101 | PINE GROVE 1101 | 94936 | FALSE | 14750.2856 | 14750.2856 | 9.1674 | 82 | 0.00010473 | 1535 | 117.7375 | 1883 | 0.010365 | 0.84992 | 1943 | 0.07 | 1716
10220 | ALLEGHANY 1101808 | 152101101 | ALLEGHANY 1101 | 808 | FALSE | 9941.3745 | 9941.3745 | 6.1786 | 23 | 8.8814e-05 | 1958 | 107.5525 | 1920 | 0.010361 | 0.23829 | 1944 | 0.23 | 1116
7876 | PUEBLO 2103706399 | 43292103 | PUEBLO 2103 | 706399 | TRUE | 1848.7276 | 537.9717 | 0.33435 | 16 | 4.8672e-05 | 3069 | 204.8708 | 1630 | 0.010338 | 0.1654 | 1945 |  | 3173
1021 | EL DORADO PH 210119752 | 152762101 | EL DORADO PH 2101 | 19752 | FALSE | 58764.7318 | 58764.7318 | 36.5225 | 436 | 0.00017226 | 548 | 104.6256 | 1929 | 0.0103 | 4.4909 | 1946 | 119.92 | 12
5417 | SILVERADO 2105131568 | 43432105 | SILVERADO 2105 | 131568 | FALSE | 7881.7386 | 6658.8017 | 4.1385 | 57 | 0.00013576 | 921 | 77.208 | 2060 | 0.010281 | 0.58604 | 1947 |  | 2951
3018 | LUCERNE 110638632 | 43351106 | LUCERNE 1106 | 38632 | FALSE | 7538.4158 | 7535.3678 | 4.6833 | 58 | 0.00018341 | 485 | 125.725 | 1857 | 0.010245 | 0.59423 | 1948 | 0.22 | 1128
9909 | OLEMA 1101337220 | 42291101 | OLEMA 1101 | 337220 | FALSE | 8725.086 | 7959.8917 | 4.9471 | 28 | 0.00012555 | 1088 | 76.0082 | 2062 | 0.010237 | 0.28665 | 1949 |  | 3451
7162 | BIG BEND 1101CB | 103751101 | BIG BEND 1101 | CB | FALSE | 37377.2089 | 37377.2089 | 23.2301 | 171 | 0.00013678 | 910 | 60.8273 | 2149 | 0.010207 | 1.7454 | 1950 | 66.07 | 74
9067 | PEORIA 170570198 | 163781705 | PEORIA 1705 | 70198 | FALSE | 5102.4847 | 3628.2739 | 2.255 | 36 | 9.8288e-05 | 1685 | 164.1355 | 1736 | 0.010197 | 0.36709 | 1951 | 0.07 | 1763
6816 | REDBUD 1101400 | 43191101 | REDBUD 1101 | 400 | FALSE | 1650.11 | 1410.4889 | 0.87662 | 14 | 7.9738e-05 | 2214 | 97.4469 | 1971 | 0.010195 | 0.14273 | 1952 | 0.05 | 2066
5252 | POINT ARENA 110137426 | 43381101 | POINT ARENA 1101 | 37426 | FALSE | 8142.4343 | 1270.4089 | 0.78956 | 65 | 4.6458e-05 | 3126 | 164.8689 | 1735 | 0.010169 | 0.66101 | 1953 | 0.25 | 1079
7444 | HOLLISTER 21064004 | 182492106 | HOLLISTER 2106 | 4004 | FALSE | 32627.9425 | 14083.7966 | 8.7531 | 180 | 5.3736e-05 | 2948 | 159.4123 | 1748 | 0.010124 | 1.8224 | 1954 | 0.05 | 1947
2021 | WOODACRE 11021280 | 43021102 | WOODACRE 1102 | 1280 | FALSE | 13974.6466 | 13812.836 | 8.5847 | 111 | 0.00015949 | 648 | 83.4065 | 2034 | 0.010109 | 1.1221 | 1955 | 0.14 | 1310
9350 | WEST POINT 1101L3355 | 163201101 | WEST POINT 1101 | L3355 | FALSE | 3618.1853 | 3618.1853 | 2.2487 | 27 | 8.1776e-05 | 2161 | 67.8566 | 2102 | 0.010104 | 0.2728 | 1956 | 44.71 | 155
4549 | ALHAMBRA 110595016 | 14101105 | ALHAMBRA 1105 | 95016 | FALSE | 7771.8455 | 1223.0109 | 0.76011 | 69 | 5.7126e-05 | 2857 | 109.0983 | 1914 | 0.010066 | 0.69458 | 1957 | 0.02 | 2499
5052 | BIG MEADOWS 21012474 | 102812101 | BIG MEADOWS 2101 | 2474 | FALSE | 13467.3498 | 13410.8685 | 8.3349 | 83 | 3.6201e-05 | 3329 | 276.607 | 1482 | 0.010035 | 0.83287 | 1958 | 10.79 | 394
616 | SONOMA 1104414 | 42721104 | SONOMA 1104 | 414 | FALSE | 35132.3675 | 2113.8048 | 1.3137 | 260 | 5.6e-05 | 2889 | 105.7924 | 1925 | 0.009991 | 2.5977 | 1959 | 1.9 | 632
8621 | FELTON 0401CB | 83140401 | FELTON 0401 | CB | FALSE | 4118.8768 | 4062.5857 | 2.5249 | 34 | 0.00043164 | 58 | 21.0417 | 2435 | 0.0099584 | 0.33859 | 1960 | 0.39 | 952
10564 | WISE 110163199 | 152271101 | WISE 1101 | 63199 | TRUE | 1501.4082 | 989.41 | 0.61492 | 8 | 0.00018345 | 483 | 115.9454 | 1891 | 0.0099235 | 0.079388 | 1961 | 0.04 | 2215
6010 | MORGAN HILL 2111XR292 | 83242111 | MORGAN HILL 2111 | XR292 | FALSE | 19536.8147 | 17975.9221 | 11.1721 | 130 | 6.4726e-05 | 2615 | 181.5173 | 1680 | 0.0098996 | 1.287 | 1962 | 0.15 | 1292
222 | DUNBAR 1102CB | 43071102 | DUNBAR 1102 | CB | FALSE | 13834.375 | 12733.914 | 7.9142 | 113 | 0.00013093 | 994 | 85.2135 | 2029 | 0.0098816 | 1.1166 | 1963 | 0.08 | 1671
8045 | PERRY 1101W26 | 183071101 | PERRY 1101 | W26 | FALSE | 4390.419 | 4390.419 | 2.7287 | 18 | 6.7545e-05 | 2549 | 162.1198 | 1741 | 0.0098794 | 0.17783 | 1964 | 0.05 | 1956
7530 | BUCKS CREEK 11031131 | 102211103 | BUCKS CREEK 1103 | 1131 | FALSE | 4424.1224 | 4424.1224 | 2.7496 | 33 | 8.1427e-05 | 2171 | 131.8339 | 1842 | 0.0098607 | 0.3254 | 1965 | 3.76 | 535
7965 | RINCON 1103568 | 43321103 | RINCON 1103 | 568 | FALSE | 20285.8832 | 20285.8832 | 12.6078 | 129 | 0.00011941 | 1198 | 98.3927 | 1966 | 0.0098399 | 1.2694 | 1966 | 40.01 | 186
7623 | PANOCHE 11034008 | 253671103 | PANOCHE 1103 | 4008 | FALSE | 56919.5652 | 56919.5652 | 35.3757 | 138 | 4.9605e-05 | 3045 | 221.1468 | 1603 | 0.0097859 | 1.3505 | 1967 | 0.04 | 2151
1557 | WILLOW CREEK 11015002 | 192171101 | WILLOW CREEK 1101 | 5002 | FALSE | 22234.4783 | 21939.7249 | 13.6356 | 161 | 0.00029646 | 133 | 37.2556 | 2295 | 0.0097721 | 1.5733 | 1968 | 18.45 | 322
2260 | EL DORADO PH 210152456 | 152762101 | EL DORADO PH 2101 | 52456 | FALSE | 16414.576 | 16414.576 | 10.2017 | 96 | 0.00013704 | 907 | 96.4288 | 1977 | 0.0097493 | 0.93593 | 1969 | 0.06 | 1899
4474 | SPENCE 1104965598 | 182201104 | SPENCE 1104 | 965598 | FALSE | 25622.1563 | 14815.8266 | 9.2081 | 139 | 4.3766e-05 | 3194 | 205.6396 | 1624 | 0.0097442 | 1.3544 | 1970 |  | 2894
9612 | DIAMOND SPRINGS 1107203504 | 152261107 | DIAMOND SPRINGS 1107 | 203504 | TRUE | 514.0425 | 226.4943 | 0.14077 | 4 | 0.00021969 | 325 | 71.3633 | 2088 | 0.0097327 | 0.038931 | 1971 |  | 3389
7259 | SUMMIT 1101742 | 152591101 | SUMMIT 1101 | 742 | FALSE | 2084.4879 | 2084.4879 | 1.2955 | 21 | 0.00010714 | 1469 | 98.5688 | 1964 | 0.009698 | 0.20366 | 1972 | 0.02 | 2502
3486 | GRASS VALLEY 11012208 | 152031101 | GRASS VALLEY 1101 | 2208 | FALSE | 20533.4109 | 18971.647 | 11.791 | 159 | 0.0001453 | 800 | 55.2252 | 2180 | 0.0096885 | 1.5405 | 1973 | 0.15 | 1278
6926 | EL DORADO PH 210113532 | 152762101 | EL DORADO PH 2101 | 13532 | FALSE | 8576.7798 | 8576.7798 | 5.3305 | 46 | 9.988e-05 | 1652 | 99.3016 | 1956 | 0.0096754 | 0.44507 | 1974 | 0 | 2625
4034 | OAKHURST 11035120 | 254421103 | OAKHURST 1103 | 5120 | FALSE | 9912.3897 | 9912.3897 | 6.1606 | 19 | 7.7594e-05 | 2273 | 140.142 | 1809 | 0.0096488 | 0.18333 | 1975 | 15.79 | 345
3547 | RINCON 1101539980 | 43321101 | RINCON 1101 | 539980 | TRUE | 697.2903 | 474.6546 | 0.295 | 4 | 0.0001397 | 874 | 59.5974 | 2157 | 0.0096291 | 0.038517 | 1976 |  | 2837
2441 | SILVERADO 2103617828 | 43432103 | SILVERADO 2103 | 617828 | FALSE | 4970.4215 | 2303.2847 | 1.4315 | 28 | 9.4549e-05 | 1777 | 105.7723 | 1926 | 0.0096279 | 0.26958 | 1977 |  | 2776
5129 | NEWBURG 1131380686 | 192151131 | NEWBURG 1131 | 380686 | FALSE | 4931.6119 | 3014.5331 | 1.8735 | 34 | 0.00017304 | 543 | 55.7388 | 2176 | 0.0095954 | 0.32624 | 1978 |  | 2938
2275 | BUTTE 11051243 | 103081105 | BUTTE 1105 | 1243 | FALSE | 8319.7013 | 8319.7013 | 5.1707 | 50 | 9.2023e-05 | 1845 | 108.0493 | 1916 | 0.0095359 | 0.47679 | 1979 |  | 2768
4445 | PINE GROVE 1102467560 | 163751102 | PINE GROVE 1102 | 467560 | FALSE | 3279.179 | 3279.179 | 2.038 | 27 | 0.00027911 | 159 | 44.0774 | 2252 | 0.009532 | 0.25736 | 1980 |  | 2891
6213 | JESSUP 1103728460 | 103441103 | JESSUP 1103 | 728460 | FALSE | 2312.7118 | 1173.0161 | 0.72903 | 17 | 9.9769e-05 | 1653 | 103.6058 | 1932 | 0.0095302 | 0.16201 | 1981 |  | 3014
3085 | SHINGLE SPRINGS 210819622 | 153652108 | SHINGLE SPRINGS 2108 | 19622 | FALSE | 18790.8494 | 9040.145 | 5.6185 | 165 | 0.00016432 | 596 | 119.9283 | 1869 | 0.0095283 | 1.5722 | 1982 | 0.05 | 1921
9214 | SAN RAFAEL 11081250 | 42011108 | SAN RAFAEL 1108 | 1250 | FALSE | 5741.9405 | 5741.9405 | 3.5686 | 26 | 0.00015475 | 698 | 75.9474 | 2063 | 0.0094996 | 0.24699 | 1983 | 71.72 | 66
10597 | MONTE RIO 11135024 | 42811113 | MONTE RIO 1113 | 5024 | TRUE | 526.6111 | 526.6111 | 0.32729 | 4 | 0.00017161 | 552 | 35.72 | 2305 | 0.0094858 | 0.037943 | 1984 | 11.71 | 383
2882 | WILLOW PASS 2108CB | 13912108 | WILLOW PASS 2108 | CB | TRUE | 14676.6694 | 318.0802 | 0.19769 | 91 | 4.4438e-05 | 3177 | 137.3401 | 1820 | 0.0094639 | 0.86121 | 1985 |  | 2802
5172 | LOS OSITOS 2103220608 | 182082103 | LOS OSITOS 2103 | 220608 | FALSE | 3563.3452 | 1678.7883 | 1.0434 | 10 | 2.1846e-05 | 3522 | 416.4617 | 1275 | 0.009449 | 0.09449 | 1986 |  | 2941
1655 | BRUNSWICK 110750010 | 152481107 | BRUNSWICK 1107 | 50010 | FALSE | 15036.1048 | 9841.1126 | 6.1163 | 117 | 0.00024302 | 239 | 56.6031 | 2173 | 0.0094406 | 1.1046 | 1987 | 18.42 | 323
3494 | WILLITS 110434008 | 42661104 | WILLITS 1104 | 34008 | FALSE | 36886.2403 | 36886.2403 | 22.9249 | 259 | 0.00010265 | 1580 | 90.3162 | 1998 | 0.0094239 | 2.4408 | 1988 | 82.16 | 46
7626 | RESERVATION ROAD 11023030 | 182731102 | RESERVATION ROAD 1102 | 3030 | FALSE | 41820.8596 | 16131.8418 | 10.026 | 186 | 2.9058e-05 | 3440 | 203.8088 | 1634 | 0.0094083 | 1.7499 | 1989 | 0.06 | 1801
10686 | HARTLEY 110158095 | 43211101 | HARTLEY 1101 | 58095 | TRUE | 251.9158 | 251.9158 | 0.15657 | 2 | 0.00013161 | 987 | 71.4359 | 2085 | 0.0094017 | 0.018803 | 1990 | 1.66 | 656
7656 | PHILO 11022600 | 42601102 | PHILO 1102 | 2600 | FALSE | 32204.7216 | 32204.7216 | 20.0154 | 114 | 9.7968e-05 | 1692 | 92.2082 | 1992 | 0.0093006 | 1.0603 | 1991 | 6.68 | 463
7863 | SANTA ROSA A 1104642 | 42151104 | SANTA ROSA A 1104 | 642 | FALSE | 14995.9698 | 14995.9698 | 9.3201 | 127 | 0.00012083 | 1167 | 94.1376 | 1984 | 0.0092364 | 1.173 | 1992 | 16.12 | 341
581 | POINT ARENA 1101474 | 43381101 | POINT ARENA 1101 | 474 | FALSE | 14496.4925 | 14496.4925 | 9.0096 | 77 | 9.2233e-05 | 1837 | 111.515 | 1906 | 0.0092125 | 0.70936 | 1993 | 0.09 | 1510
9791 | LOS OSITOS 2103695270 | 182082103 | LOS OSITOS 2103 | 695270 | FALSE | 1764.2137 | 1116.1992 | 0.69372 | 12 | 6.659e-05 | 2569 | 184.7862 | 1675 | 0.009199 | 0.11039 | 1994 |  | 3425
9383 | CASTRO VALLEY 1110MR525 | 14091110 | CASTRO VALLEY 1110 | MR525 | TRUE | 98.2491 | 17.8831 | 0.011114 | 2 | 6.2244e-05 | 2712 | 142.6154 | 1800 | 0.0091967 | 0.018393 | 1995 |  | 3348
5023 | MC ARTHUR 11021324 | 103491102 | MC ARTHUR 1102 | 1324 | FALSE | 38651.4549 | 1638.5898 | 1.0184 | 169 | 2.205e-05 | 3520 | 325.2371 | 1405 | 0.0091756 | 1.5507 | 1996 | 0.02 | 2488
7662 | CASTRO VALLEY 1110610800 | 14091110 | CASTRO VALLEY 1110 | 610800 | FALSE | 4080.4254 | 3862.9953 | 2.4009 | 33 | 8.5461e-05 | 2042 | 102.3732 | 1943 | 0.0091096 | 0.30062 | 1997 |  | 3147
6717 | NEWBURG 1132910230 | 192151132 | NEWBURG 1132 | 910230 | FALSE | 3166.5297 | 1560.5069 | 0.96986 | 27 | 0.00023935 | 248 | 37.0091 | 2298 | 0.0090947 | 0.24556 | 1998 |  | 3058
10 | KONOCTI 1102532 | 43311102 | KONOCTI 1102 | 532 | FALSE | 15658.0016 | 15658.0016 | 9.7315 | 124 | 0.00024726 | 225 | 48.9408 | 2215 | 0.0090595 | 1.1234 | 1999 | 47.27 | 135
5170 | EL DORADO PH 2102542272 | 152762102 | EL DORADO PH 2102 | 542272 | FALSE | 12585.3616 | 12585.3616 | 7.8219 | 80 | 0.00018486 | 474 | 31.5637 | 2334 | 0.0090446 | 0.72357 | 2000 |  | 2940
8963 | MIRABEL 1101253331 | 42091101 | MIRABEL 1101 | 253331 | TRUE | 639.8394 | 107.6584 | 0.06691 | 5 | 0.0001555 | 688 | 63.3453 | 2134 | 0.0090171 | 0.045085 | 2001 |  | 3284
10053 | ROB ROY 21046577 | 83692104 | ROB ROY 2104 | 6577 | FALSE | 5581.4139 | 5581.4139 | 3.4689 | 33 | 0.00018059 | 509 | 33.2037 | 2318 | 0.0089943 | 0.29681 | 2002 |  | 3482
8505 | NEWBURG 113190242 | 192151131 | NEWBURG 1131 | 90242 | FALSE | 7016.5204 | 6652.6427 | 4.1346 | 51 | 0.00013965 | 876 | 54.8847 | 2183 | 0.0089934 | 0.45866 | 2003 | 0.05 | 1980
283 | SAN RAFAEL 1104802 | 42011104 | SAN RAFAEL 1104 | 802 | FALSE | 20585.105 | 13782.7792 | 8.5661 | 162 | 0.00013761 | 901 | 59.5964 | 2158 | 0.0089568 | 1.451 | 2004 | 0.09 | 1542
9446 | ECHO SUMMIT 1101481660 | 158031101 | ECHO SUMMIT 1101 | 481660 | FALSE | 1777.5904 | 1750.3957 | 1.0879 | 21 | 0.00013748 | 904 | 66.8278 | 2109 | 0.0089565 | 0.18809 | 2005 |  | 3360
1636 | LOS COCHES 1101625902 | 182151101 | LOS COCHES 1101 | 625902 | FALSE | 9066.5477 | 4214.4266 | 2.6193 | 26 | 5.2521e-05 | 2981 | 97.9588 | 1969 | 0.0089147 | 0.23178 | 2006 |  | 2735
8007 | SAN JUSTO 11014002 | 183181101 | SAN JUSTO 1101 | 4002 | FALSE | 30655.7932 | 29553.7891 | 18.3678 | 140 | 4.2612e-05 | 3215 | 236.2342 | 1577 | 0.0088999 | 1.246 | 2007 | 0.18 | 1202
4827 | ATASCADERO 1103A88 | 182541103 | ATASCADERO 1103 | A88 | FALSE | 4298.2003 | 1506.8203 | 0.93649 | 41 | 7.0724e-05 | 2450 | 118.2966 | 1877 | 0.008869 | 0.36363 | 2008 | 0.51 | 891
6300 | DRUM 11011602 | 152321101 | DRUM 1101 | 1602 | FALSE | 26067.9128 | 26067.9128 | 16.2013 | 121 | 7.2028e-05 | 2416 | 103.4039 | 1935 | 0.0088619 | 1.0723 | 2009 | 0.28 | 1033
7254 | ALLEGHANY 1101VR816 | 152101101 | ALLEGHANY 1101 | VR816 | FALSE | 6675.8935 | 6675.8935 | 4.1491 | 49 | 0.00021002 | 359 | 34.0265 | 2312 | 0.0088541 | 0.43385 | 2010 | 78.58 | 51
2986 | PINE GROVE 110235576 | 163751102 | PINE GROVE 1102 | 35576 | FALSE | 12676.983 | 12676.983 | 7.8788 | 77 | 9.958e-05 | 1656 | 90.2081 | 1999 | 0.0088445 | 0.68102 | 2011 | 51.58 | 114
8230 | SAN LUIS OBISPO 1102357407 | 182631102 | SAN LUIS OBISPO 1102 | 357407 | TRUE | 396.3684 | 382.6506 | 0.23782 | 5 | 5.6115e-05 | 2883 | 139.4252 | 1811 | 0.0088377 | 0.044188 | 2012 |  | 3206
1189 | PEORIA 170575274 | 163781705 | PEORIA 1705 | 75274 | TRUE | 5361.6389 | 623.7122 | 0.38764 | 43 | 7.4779e-05 | 2337 | 100.4794 | 1953 | 0.0088331 | 0.37982 | 2013 | 2.09 | 623
299 | MONTE RIO 111164758 | 42811111 | MONTE RIO 1111 | 64758 | FALSE | 16840.1197 | 16840.1197 | 10.4662 | 97 | 0.00025463 | 207 | 41.2688 | 2270 | 0.0087918 | 0.8528 | 2014 | 58.76 | 91
8131 | HARTLEY 1101534548 | 43211101 | HARTLEY 1101 | 534548 | TRUE | 825.2513 | 643.683 | 0.40005 | 7 | 8.8763e-05 | 1960 | 139.419 | 1812 | 0.008746 | 0.061222 | 2015 |  | 3194
3395 | BOLINAS 1101504 | 42261101 | BOLINAS 1101 | 504 | FALSE | 10763.1252 | 10763.1252 | 6.6893 | 53 | 0.00011675 | 1255 | 93.9031 | 1988 | 0.0087025 | 0.46123 | 2016 | 0.26 | 1063
6220 | LAKEVILLE 1102530 | 43371102 | LAKEVILLE 1102 | 530 | TRUE | 7365.5043 | 114.9911 | 0.071467 | 55 | 7.7592e-05 | 2274 | 96.695 | 1976 | 0.0087005 | 0.47853 | 2017 | 0.03 | 2248
8104 | MONTE RIO 111137520 | 42811111 | MONTE RIO 1111 | 37520 | FALSE | 3437.9631 | 3437.9631 | 2.1367 | 20 | 0.0002436 | 236 | 45.2659 | 2244 | 0.0086846 | 0.17369 | 2018 | 30.52 | 237
5024 | MONTE RIO 1113180 | 42811113 | MONTE RIO 1113 | 180 | FALSE | 3158.1165 | 3158.1165 | 1.9628 | 28 | 0.00023287 | 273 | 37.4189 | 2293 | 0.0086779 | 0.24298 | 2019 | 48.66 | 126
2418 | CLEAR LAKE 11011302 | 42141101 | CLEAR LAKE 1101 | 1302 | FALSE | 28390.9957 | 12188.0095 | 7.5749 | 189 | 9.155e-05 | 1856 | 135.9642 | 1826 | 0.0086777 | 1.6401 | 2020 | 0.07 | 1751
6344 | WEST POINT 11021303 | 163201102 | WEST POINT 1102 | 1303 | FALSE | 25207.4138 | 25207.4138 | 15.6665 | 146 | 8.2868e-05 | 2134 | 109.1634 | 1912 | 0.0086648 | 1.2651 | 2021 | 55.45 | 103
147 | SHADY GLEN 11022232 | 152431102 | SHADY GLEN 1102 | 2232 | FALSE | 16843.7265 | 16843.7265 | 10.4684 | 88 | 0.00014558 | 796 | 81.1031 | 2043 | 0.0086414 | 0.76044 | 2022 | 16.24 | 339
8652 | LOYOLA 1102725939 | 82161102 | LOYOLA 1102 | 725939 | TRUE | 1338.4571 | 150.5355 | 0.093558 | 14 | 0.0001664 | 579 | 36.2434 | 2303 | 0.0086108 | 0.12055 | 2023 |  | 3249
10013 | GREEN VALLEY 21016601 | 83192101 | GREEN VALLEY 2101 | 6601 | FALSE | 3063.6094 | 3063.6094 | 1.904 | 19 | 0.00011592 | 1271 | 66.3782 | 2113 | 0.0085862 | 0.16314 | 2024 |  | 3470
3970 | PUEBLO 1105348368 | 43291105 | PUEBLO 1105 | 348368 | FALSE | 14957.0247 | 4473.6471 | 2.7804 | 107 | 6.0549e-05 | 2762 | 137.0477 | 1824 | 0.0085797 | 0.91803 | 2025 |  | 2865
5419 | MIRABEL 11014859 | 42091101 | MIRABEL 1101 | 4859 | FALSE | 3008.5895 | 3008.5895 | 1.8699 | 22 | 0.00015733 | 670 | 65.9715 | 2116 | 0.0085572 | 0.18826 | 2026 | 30.63 | 236
3836 | PURISIMA 1101CB | 182971101 | PURISIMA 1101 | CB | FALSE | 7381.7293 | 5917.6189 | 3.6778 | 32 | 7.2016e-05 | 2418 | 150.0597 | 1776 | 0.0085315 | 0.27301 | 2027 | 0.06 | 1914
589 | EL DORADO PH 21016852 | 152762101 | EL DORADO PH 2101 | 6852 | FALSE | 40624.2727 | 40624.2727 | 25.2481 | 309 | 0.00015417 | 703 | 140.8238 | 1808 | 0.0085289 | 2.6354 | 2028 | 106.87 | 16
7704 | GOLDTREE 1107CB | 182581107 | GOLDTREE 1107 | CB | FALSE | 5578.7405 | 1480.1268 | 0.9199 | 28 | 6.1871e-05 | 2724 | 91.0203 | 1996 | 0.0085282 | 0.23879 | 2029 | 0.25 | 1074
10273 | POINT ARENA 11014923 | 43381101 | POINT ARENA 1101 | 4923 | FALSE | 4611.3164 | 4611.3164 | 2.866 | 12 | 0.00010517 | 1516 | 65.4057 | 2122 | 0.008518 | 0.10222 | 2030 | 0.06 | 1877
327 | CURTIS 170463502 | 163351704 | CURTIS 1704 | 63502 | FALSE | 16836.9835 | 16836.9835 | 10.4643 | 107 | 0.00012514 | 1095 | 60.239 | 2153 | 0.0084952 | 0.90898 | 2031 | 0.16 | 1256
7937 | CLARK ROAD 11022068 | 103091102 | CLARK ROAD 1102 | 2068 | FALSE | 17517.3264 | 17517.3264 | 10.8871 | 90 | 0.00011364 | 1328 | 80.7377 | 2044 | 0.0084897 | 0.76407 | 2032 | 0.32 | 992
4769 | WYANDOTTE 1107CB | 102911107 | WYANDOTTE 1107 | CB | FALSE | 24321.9127 | 2030.3761 | 1.2619 | 199 | 0.00016447 | 591 | 61.5586 | 2143 | 0.0084763 | 1.6868 | 2033 | 0.03 | 2311
7564 | COLUMBIA HILL 11018233 | 152471101 | COLUMBIA HILL 1101 | 8233 | FALSE | 7978.7453 | 7978.7453 | 4.9588 | 51 | 7.9873e-05 | 2208 | 109.5763 | 1910 | 0.008467 | 0.43182 | 2034 | 41.72 | 175
2536 | HALSEY 1101CB | 152241101 | HALSEY 1101 | CB | FALSE | 27644.3487 | 27644.3487 | 17.1811 | 231 | 0.00016053 | 637 | 70.3363 | 2092 | 0.0084422 | 1.9501 | 2035 | 0.21 | 1148
2174 | DIAMOND SPRINGS 1104CB | 152261104 | DIAMOND SPRINGS 1104 | CB | FALSE | 15842.0085 | 9046.8091 | 5.6226 | 127 | 0.0002078 | 373 | 65.6703 | 2119 | 0.008393 | 1.0659 | 2036 | 0.19 | 1172
4975 | EL DORADO PH 210119612 | 152762101 | EL DORADO PH 2101 | 19612 | FALSE | 14689.1647 | 14689.1647 | 9.1294 | 102 | 0.00021799 | 328 | 33.636 | 2313 | 0.0083743 | 0.85418 | 2037 | 36 | 208
7088 | SAUSALITO 11021500 | 42491102 | SAUSALITO 1102 | 1500 | FALSE | 2059.653 | 1869.3575 | 1.1618 | 8 | 8.3383e-05 | 2121 | 83.3451 | 2035 | 0.0083473 | 0.066779 | 2038 | 0.06 | 1818
4510 | CAMP EVERS 210511010 | 83622105 | CAMP EVERS 2105 | 11010 | FALSE | 3501.2634 | 3501.2634 | 2.176 | 26 | 0.00023343 | 269 | 31.1531 | 2340 | 0.0083235 | 0.21641 | 2039 | 12.24 | 375
7509 | WESTLEY 1103237522 | 162671103 | WESTLEY 1103 | 237522 | FALSE | 26805.1596 | 1485.982 | 0.92354 | 39 | 3.422e-05 | 3366 | 404.1911 | 1293 | 0.0082937 | 0.32346 | 2040 |  | 3130
2971 | CASTRO VALLEY 1111MR334 | 14091111 | CASTRO VALLEY 1111 | MR334 | FALSE | 9742.4846 | 9116.5949 | 5.666 | 80 | 8.203e-05 | 2151 | 200.4591 | 1639 | 0.0082358 | 0.65886 | 2041 |  | 2808
143 | RACETRACK 1703CB | 163761703 | RACETRACK 1703 | CB | FALSE | 28877.5917 | 25353.1416 | 15.7571 | 216 | 0.00013825 | 891 | 45.587 | 2242 | 0.008163 | 1.7632 | 2042 | 0.16 | 1262
1117 | MORGAN HILL 2104152774 | 83242104 | MORGAN HILL 2104 | 152774 | FALSE | 12406.0754 | 10319.2603 | 6.4135 | 84 | 6.212e-05 | 2716 | 152.7782 | 1769 | 0.0081314 | 0.68304 | 2043 |  | 2709
3526 | SILVERADO 2103920793 | 43432103 | SILVERADO 2103 | 920793 | FALSE | 12855.6086 | 10473.7039 | 6.5094 | 51 | 8.6884e-05 | 2016 | 85.5215 | 2025 | 0.008033 | 0.40968 | 2044 |  | 2833
7263 | FORESTHILL 11011820 | 152181101 | FORESTHILL 1101 | 1820 | FALSE | 9227.6622 | 9227.6622 | 5.735 | 51 | 7.9052e-05 | 2234 | 127.8002 | 1850 | 0.0080276 | 0.40941 | 2045 | 46.68 | 139
4807 | PLACER 1103238990 | 152461103 | PLACER 1103 | 238990 | TRUE | 9730.7173 | 65.0773 | 0.040446 | 84 | 0.00017934 | 513 | 66.7295 | 2111 | 0.0080184 | 0.67354 | 2046 |  | 2918
7786 | UPPER LAKE 11016663 | 42871101 | UPPER LAKE 1101 | 6663 | FALSE | 3787.49 | 3787.49 | 2.3539 | 17 | 7.5146e-05 | 2328 | 97.3101 | 1972 | 0.0079953 | 0.13592 | 2047 | 1.13 | 713
797 | DUNBAR 1101CB | 43071101 | DUNBAR 1101 | CB | FALSE | 23959.1283 | 5020.5865 | 3.1203 | 191 | 0.00012086 | 1166 | 54.2982 | 2185 | 0.007993 | 1.5267 | 2048 | 0.11 | 1429
1103 | HOOPA 1101CB | 192401101 | HOOPA 1101 | CB | FALSE | 63333.9358 | 37375.4287 | 23.229 | 440 | 0.00026939 | 173 | 30.0518 | 2342 | 0.0079104 | 3.4806 | 2049 | 0.19 | 1174
8668 | BIG BASIN 110211062 | 82841102 | BIG BASIN 1102 | 11062 | FALSE | 21428.2343 | 21428.2343 | 13.3177 | 88 | 0.00013572 | 922 | 71.1136 | 2090 | 0.007899 | 0.69511 | 2050 | 0.25 | 1075
7844 | ELK 11011260 | 42981101 | ELK 1101 | 1260 | FALSE | 25231.41 | 25226.838 | 15.6786 | 120 | 9.4953e-05 | 1767 | 70.6215 | 2091 | 0.0078966 | 0.94759 | 2051 | 0.04 | 2197
2387 | HALSEY 110239104 | 152241102 | HALSEY 1102 | 39104 | FALSE | 49366.035 | 49366.035 | 30.6812 | 346 | 0.00016953 | 566 | 33.5173 | 2314 | 0.007888 | 2.7292 | 2052 | 0.26 | 1066
1085 | MORAGA 1101CB | 13801101 | MORAGA 1101 | CB | FALSE | 14345.0573 | 13611.4014 | 8.4595 | 92 | 0.00011705 | 1247 | 67.2853 | 2106 | 0.0078811 | 0.72506 | 2053 | 0.43 | 926
6726 | MARTELL 110292172 | 163011102 | MARTELL 1102 | 92172 | TRUE | 5246.1471 | 190.7947 | 0.11858 | 45 | 0.00012597 | 1079 | 55.6458 | 2177 | 0.0078638 | 0.35387 | 2054 | 0.61 | 846
1984 | HALF MOON BAY 110369412 | 24101103 | HALF MOON BAY 1103 | 69412 | FALSE | 34124.5253 | 25048.7626 | 15.5679 | 150 | 9.9166e-05 | 1664 | 96.7198 | 1975 | 0.0078448 | 1.1767 | 2055 | 0.06 | 1862
2299 | VINEYARD 2107CB | 14502107 | VINEYARD 2107 | CB | FALSE | 12364.4219 | 3069.8489 | 1.9079 | 111 | 3.2822e-05 | 3389 | 173.8407 | 1700 | 0.0077955 | 0.8653 | 2056 | 0.03 | 2405
9627 | POINT ARENA 11011296 | 43381101 | POINT ARENA 1101 | 1296 | FALSE | 8913.723 | 5630.7668 | 3.4995 | 37 | 6.5385e-05 | 2603 | 134.0606 | 1835 | 0.007772 | 0.28757 | 2057 | 0.02 | 2458
2765 | FORESTHILL 1101CB | 152181101 | FORESTHILL 1101 | CB | FALSE | 14659.7522 | 14659.7522 | 9.1111 | 110 | 0.00023141 | 282 | 46.7348 | 2235 | 0.0077431 | 0.85174 | 2058 | 50.51 | 118
4087 | BURNEY 11011340 | 103311101 | BURNEY 1101 | 1340 | FALSE | 28996.5273 | 28996.5273 | 18.0215 | 144 | 3.4761e-05 | 3354 | 286.6355 | 1466 | 0.0077101 | 1.1103 | 2059 | 0.06 | 1820
8844 | MIDDLETOWN 1101614 | 43141101 | MIDDLETOWN 1101 | 614 | FALSE | 2222.7419 | 2222.7419 | 1.3814 | 18 | 0.00013751 | 902 | 52.9107 | 2196 | 0.0076984 | 0.13857 | 2060 | 47.35 | 134
3083 | MONTE RIO 1113320 | 42811113 | MONTE RIO 1113 | 320 | FALSE | 4467.496 | 4467.496 | 2.7766 | 29 | 0.00021698 | 331 | 31.2121 | 2339 | 0.0076924 | 0.22308 | 2061 | 49.68 | 122
7740 | POINT MORETTI 110136514 | 82931101 | POINT MORETTI 1101 | 36514 | FALSE | 11050.0531 | 11050.0531 | 6.8677 | 64 | 0.00015664 | 677 | 62.082 | 2141 | 0.0076624 | 0.4904 | 2062 | 0.67 | 813
898 | COTATI 11055156 | 42271105 | COTATI 1105 | 5156 | FALSE | 16018.9017 | 7784.4976 | 4.8381 | 114 | 9.9942e-05 | 1647 | 85.2613 | 2028 | 0.0076261 | 0.86938 | 2063 | 0.53 | 881
3027 | PHILO 11021308 | 42601102 | PHILO 1102 | 1308 | FALSE | 51491.5441 | 51491.5441 | 32.0022 | 245 | 8.9849e-05 | 1917 | 98.5183 | 1965 | 0.0076242 | 1.8679 | 2064 | 0.09 | 1559
10504 | KANAKA 11011036 | 103221101 | KANAKA 1101 | 1036 | TRUE | 989.4598 | 989.4598 | 0.61495 | 4 | 6.243e-05 | 2709 | 118.9656 | 1873 | 0.0076073 | 0.030429 | 2065 | 0.09 | 1531
2446 | FOOTHILL 1102V06 | 182951102 | FOOTHILL 1102 | V06 | FALSE | 10508.9376 | 3602.7995 | 2.2392 | 66 | 4.6125e-05 | 3135 | 94.4714 | 1983 | 0.007606 | 0.50199 | 2066 | 0.87 | 757
4588 | COARSEGOLD 21025722 | 254432102 | COARSEGOLD 2102 | 5722 | FALSE | 3182.5999 | 3182.5999 | 1.978 | 23 | 7.5358e-05 | 2325 | 108.5957 | 1915 | 0.0076053 | 0.17492 | 2067 | 0.29 | 1024
8714 | OTTER 1101CB | 182941101 | OTTER 1101 | CB | FALSE | 10759.8557 | 10367.8883 | 6.4437 | 54 | 7.9345e-05 | 2224 | 98.8454 | 1961 | 0.0075954 | 0.41015 | 2068 | 0.46 | 912
9866 | DUNBAR 1101343 | 43071101 | DUNBAR 1101 | 343 | FALSE | 7140.9406 | 7140.9406 | 4.4381 | 39 | 0.0001241 | 1116 | 75.0943 | 2067 | 0.0075606 | 0.29486 | 2069 | 38.93 | 192
723 | BIG BASIN 110296986 | 82841102 | BIG BASIN 1102 | 96986 | FALSE | 9497.5055 | 9497.5055 | 5.9027 | 63 | 0.00018221 | 496 | 38.932 | 2285 | 0.0075562 | 0.47604 | 2070 | 0.41 | 938
5272 | NEWBURG 1133CB | 192151133 | NEWBURG 1133 | CB | FALSE | 14786.8555 | 5089.2485 | 3.163 | 92 | 0.00018939 | 445 | 47.0523 | 2232 | 0.0075338 | 0.69311 | 2071 | 0.06 | 1839
6817 | HALF MOON BAY 1103695411 | 24101103 | HALF MOON BAY 1103 | 695411 | FALSE | 13352.973 | 13352.973 | 8.2989 | 99 | 0.00013199 | 984 | 79.3253 | 2051 | 0.0075292 | 0.74539 | 2072 |  | 3065
9735 | EEL RIVER 1103216324 | 192381103 | EEL RIVER 1103 | 216324 | FALSE | 4626.1816 | 3681.9233 | 2.2883 | 23 | 0.00013316 | 955 | 50.0452 | 2210 | 0.0075204 | 0.17297 | 2073 |  | 3409
803 | DIAMOND SPRINGS 1107CB | 152261107 | DIAMOND SPRINGS 1107 | CB | TRUE | 5946.2245 | 0 | 0 | 51 | 0.00020302 | 386 | 24.2582 | 2398 | 0.0074949 | 0.38224 | 2074 | 0.05 | 1988
2229 | EL DORADO PH 210136764 | 152762101 | EL DORADO PH 2101 | 36764 | FALSE | 7038.6749 | 5034.5882 | 3.129 | 46 | 4.659e-05 | 3123 | 107.3772 | 1922 | 0.0074941 | 0.34473 | 2075 | 0 | 2633
5945 | SANTA ROSA A 1111758024 | 42151111 | SANTA ROSA A 1111 | 758024 | FALSE | 10378.3257 | 7589.8929 | 4.7171 | 72 | 9.0405e-05 | 1901 | 69.6669 | 2097 | 0.007484 | 0.53884 | 2076 |  | 2992
726 | DIAMOND SPRINGS 1106930190 | 152261106 | DIAMOND SPRINGS 1106 | 930190 | FALSE | 30053.7833 | 27579.5424 | 17.1408 | 207 | 0.00014885 | 753 | 53.3783 | 2192 | 0.0074761 | 1.5476 | 2077 |  | 2690
353 | CURTIS 170210940 | 163351702 | CURTIS 1702 | 10940 | FALSE | 17097.711 | 13824.9592 | 8.5923 | 138 | 0.0001288 | 1032 | 78.9158 | 2055 | 0.0073788 | 1.0183 | 2078 | 0.13 | 1356
1231 | RED BLUFF 1103CB | 103541103 | RED BLUFF 1103 | CB | TRUE | 31613.0704 | 164.6636 | 0.10234 | 261 | 5.2389e-05 | 2982 | 125.9834 | 1855 | 0.0073172 | 1.9098 | 2079 |  | 2718
10001 | PANOCHE 11034036 | 253671103 | PANOCHE 1103 | 4036 | FALSE | 40366.1816 | 16000.3845 | 9.9443 | 57 | 4.3272e-05 | 3204 | 184.9055 | 1674 | 0.0073003 | 0.41612 | 2080 | 0.02 | 2455
9426 | GREEN VALLEY 2101380922 | 83192101 | GREEN VALLEY 2101 | 380922 | FALSE | 4341.3947 | 1588.6005 | 0.98732 | 30 | 5.3037e-05 | 2965 | 107.6713 | 1919 | 0.0072901 | 0.2187 | 2081 |  | 3357
1700 | LUCERNE 110676850 | 43351106 | LUCERNE 1106 | 76850 | FALSE | 5941.1146 | 3458.1261 | 2.1492 | 51 | 0.00012907 | 1026 | 65.4632 | 2120 | 0.0072691 | 0.37072 | 2082 | 0.04 | 2220
2002 | HOLLISTER 21054018 | 182492105 | HOLLISTER 2105 | 4018 | FALSE | 85010.3668 | 71470.9964 | 44.4195 | 280 | 6.7671e-05 | 2541 | 115.5373 | 1893 | 0.0072679 | 2.035 | 2083 | 0.08 | 1661
2867 | MONTE RIO 1113346 | 42811113 | MONTE RIO 1113 | 346 | FALSE | 16160.3417 | 16160.3417 | 10.0437 | 101 | 0.00015809 | 662 | 67.6609 | 2104 | 0.0072159 | 0.72881 | 2084 | 0.97 | 737
7311 | LOS OSITOS 2102258878 | 182082102 | LOS OSITOS 2102 | 258878 | FALSE | 7396.9293 | 5357.1763 | 3.3295 | 26 | 3.9953e-05 | 3270 | 107.5084 | 1921 | 0.0072141 | 0.18757 | 2085 |  | 3114
1213 | WOODACRE 1102137662 | 43021102 | WOODACRE 1102 | 137662 | FALSE | 13866.4902 | 13813.2405 | 8.585 | 104 | 0.00014441 | 806 | 94.0043 | 1985 | 0.0071841 | 0.74714 | 2086 | 0.76 | 786
2384 | BONNIE NOOK 1102CB | 152301102 | BONNIE NOOK 1102 | CB | FALSE | 54723.5805 | 54723.5805 | 34.0109 | 337 | 0.00011257 | 1353 | 93.6722 | 1990 | 0.0071702 | 2.4164 | 2087 | 71.14 | 67
324 | PLACERVILLE 1110953474 | 153081110 | PLACERVILLE 1110 | 953474 | FALSE | 17115.5789 | 17115.5789 | 10.6374 | 133 | 0.000245 | 233 | 47.063 | 2231 | 0.0071239 | 0.94748 | 2088 |  | 2666
9849 | FOOTHILL 1101722270 | 182951101 | FOOTHILL 1101 | 722270 | TRUE | 712.8056 | 283.5574 | 0.17623 | 5 | 3.323e-05 | 3380 | 133.0363 | 1839 | 0.0070957 | 0.035479 | 2089 |  | 3434
3510 | MONTE RIO 1111140 | 42811111 | MONTE RIO 1111 | 140 | FALSE | 13525.925 | 13525.925 | 8.4064 | 96 | 0.0002562 | 201 | 19.1476 | 2459 | 0.0070376 | 0.67561 | 2090 | 16.37 | 338
1551 | CARLOTTA 11214914 | 192291121 | CARLOTTA 1121 | 4914 | FALSE | 22650.1521 | 17097.4476 | 10.6261 | 138 | 0.00016776 | 577 | 39.2521 | 2282 | 0.0070374 | 0.97117 | 2091 | 0.08 | 1621
4560 | COARSEGOLD 210210330 | 254432102 | COARSEGOLD 2102 | 10330 | FALSE | 15550.3229 | 15550.3229 | 9.6646 | 90 | 7.2321e-05 | 2408 | 118.1064 | 1878 | 0.0069896 | 0.62906 | 2092 | 0.31 | 1008
6442 | PIT NO 1 11019702 | 103721101 | PIT NO 1 1101 | 9702 | FALSE | 14797.576 | 1035.9167 | 0.64383 | 91 | 3.6155e-05 | 3331 | 189.6534 | 1664 | 0.006985 | 0.63564 | 2093 | 0.01 | 2605
8877 | WILLOW CREEK 11013050 | 192171101 | WILLOW CREEK 1101 | 3050 | FALSE | 4223.7094 | 4223.7094 | 2.6251 | 18 | 0.00010688 | 1481 | 71.3502 | 2089 | 0.0069828 | 0.12569 | 2094 | 11.06 | 389
9559 | SONOMA 1103581588 | 42721103 | SONOMA 1103 | 581588 | TRUE | 1519.7137 | 313.0143 | 0.19454 | 14 | 0.00011751 | 1235 | 44.2079 | 2251 | 0.0069585 | 0.097419 | 2095 |  | 3376
2326 | BRUNSWICK 11052140 | 152481105 | BRUNSWICK 1105 | 2140 | FALSE | 55629.2693 | 55629.2693 | 34.5738 | 373 | 7.6296e-05 | 2300 | 87.1186 | 2015 | 0.0069513 | 2.5928 | 2096 | 99.53 | 20
7797 | SAUSALITO 1101331806 | 42491101 | SAUSALITO 1101 | 331806 | TRUE | 1086.2067 | 799.0558 | 0.49662 | 5 | 0.00010249 | 1590 | 66.6724 | 2112 | 0.0069274 | 0.034637 | 2097 |  | 3162
1778 | WEIMAR 11026175 | 152491102 | WEIMAR 1102 | 6175 | FALSE | 4418.4642 | 4418.4642 | 2.7461 | 30 | 7.0467e-05 | 2457 | 113.3507 | 1901 | 0.0069045 | 0.20713 | 2098 | 0.08 | 1596
2962 | CURTIS 1704803 | 163351704 | CURTIS 1704 | 803 | FALSE | 15630.8479 | 15630.8479 | 9.7146 | 93 | 8.737e-05 | 2002 | 89.4789 | 2003 | 0.0068944 | 0.64118 | 2099 | 0.14 | 1319
5429 | MIRABEL 1101228 | 42091101 | MIRABEL 1101 | 228 | FALSE | 15665.2534 | 3403.012 | 2.115 | 123 | 0.00014113 | 851 | 47.1197 | 2230 | 0.0068367 | 0.84091 | 2100 | 1.03 | 725
8011 | HORSESHOE 1101603250 | 152571101 | HORSESHOE 1101 | 603250 | TRUE | 2274.9057 | 927.3694 | 0.57636 | 21 | 0.00016094 | 631 | 57.7467 | 2167 | 0.0068337 | 0.14351 | 2101 |  | 3184
7095 | PUEBLO 2102618 | 43292102 | PUEBLO 2102 | 618 | TRUE | 16180.0386 | 742.2572 | 0.46132 | 118 | 9.7103e-05 | 1711 | 69.2887 | 2098 | 0.0068234 | 0.80516 | 2102 | 17.57 | 331
8240 | WOODSIDE 11018601 | 24251101 | WOODSIDE 1101 | 8601 | TRUE | 961.631 | 961.631 | 0.59766 | 9 | 0.00015446 | 700 | 60.8174 | 2150 | 0.0067792 | 0.061013 | 2103 | 35.86 | 209
3848 | REEDLEY 11127240 | 252341112 | REEDLEY 1112 | 7240 | FALSE | 41066.7491 | 1553.9231 | 0.96577 | 234 | 4.3626e-05 | 3198 | 175.637 | 1696 | 0.0067642 | 1.5828 | 2104 | 0.02 | 2533
4429 | SONOMA 1105138 | 42721105 | SONOMA 1105 | 138 | TRUE | 26504.92 | 104.0479 | 0.064666 | 197 | 6.5875e-05 | 2590 | 63.508 | 2131 | 0.0067556 | 1.3309 | 2105 | 0.62 | 838
1588 | CORRAL 110359770 | 162991103 | CORRAL 1103 | 59770 | FALSE | 11687.7507 | 7749.7634 | 4.8165 | 97 | 8.5709e-05 | 2037 | 89.7185 | 2001 | 0.0067467 | 0.65443 | 2106 | 0.09 | 1532
6984 | GABILAN 1101566352 | 182331101 | GABILAN 1101 | 566352 | TRUE | 1524.3755 | 680.7554 | 0.42309 | 9 | 3.3385e-05 | 3378 | 153.3762 | 1766 | 0.0067421 | 0.060679 | 2107 |  | 3079
8546 | SPENCE 1102990464 | 182201102 | SPENCE 1102 | 990464 | FALSE | 8550.7923 | 3365.9887 | 2.092 | 53 | 2.9572e-05 | 3431 | 166.8203 | 1728 | 0.0067321 | 0.3568 | 2108 |  | 3234
9813 | BOLINAS 110137034 | 42261101 | BOLINAS 1101 | 37034 | FALSE | 7287.0481 | 7287.0481 | 4.5289 | 16 | 0.00011223 | 1360 | 44.6194 | 2249 | 0.006701 | 0.10722 | 2109 | 0.31 | 1007
8495 | PENRYN 110550550 | 152561105 | PENRYN 1105 | 50550 | TRUE | 16250.0266 | 0 | 0 | 127 | 0.00012612 | 1078 | 64.7345 | 2124 | 0.0066813 | 0.84852 | 2110 | 0.74 | 790
533 | HIGHLANDS 110439458 | 43361104 | HIGHLANDS 1104 | 39458 | FALSE | 8594.1592 | 1902.6531 | 1.1825 | 72 | 7.6303e-05 | 2298 | 85.8335 | 2024 | 0.0066627 | 0.47971 | 2111 | 0.27 | 1048
6908 | MENLO 11038512 | 24131103 | MENLO 1103 | 8512 | FALSE | 39804.5313 | 39804.5313 | 24.7387 | 228 | 0.00015985 | 643 | 38.9598 | 2284 | 0.0066372 | 1.5133 | 2112 | 8.94 | 418
1455 | LAS GALLINAS A 1105904 | 42991105 | LAS GALLINAS A 1105 | 904 | FALSE | 11554.8525 | 2469.2456 | 1.5346 | 78 | 4.3101e-05 | 3208 | 64.1478 | 2127 | 0.0066274 | 0.51694 | 2113 | 0.04 | 2146
2184 | GEYSERVILLE 110289714 | 42891102 | GEYSERVILLE 1102 | 89714 | TRUE | 11363.665 | 178.2278 | 0.11077 | 71 | 8.7635e-05 | 1996 | 68.3169 | 2100 | 0.0066271 | 0.47052 | 2114 | 0.02 | 2528
2865 | MOLINO 1102344 | 42571102 | MOLINO 1102 | 344 | FALSE | 9676.0469 | 2427.2453 | 1.5085 | 77 | 0.00010403 | 1551 | 64.3203 | 2126 | 0.0066172 | 0.50953 | 2115 | 1.32 | 687
2057 | SHINGLE SPRINGS 210911092 | 153652109 | SHINGLE SPRINGS 2109 | 11092 | FALSE | 36100.2834 | 36100.2834 | 22.4365 | 239 | 0.00011036 | 1404 | 74.4691 | 2070 | 0.0066099 | 1.5798 | 2116 | 0.14 | 1314
10095 | SILVERADO 2104645 | 43432104 | SILVERADO 2104 | 645 | FALSE | 1626.8938 | 1626.8938 | 1.0111 | 13 | 9.1232e-05 | 1870 | 67.7241 | 2103 | 0.0065604 | 0.085285 | 2117 | 60.62 | 88
6812 | CLOVERDALE 1101474708 | 42821101 | CLOVERDALE 1101 | 474708 | TRUE | 1392.1284 | 422.046 | 0.2623 | 13 | 0.00016436 | 594 | 18.3674 | 2470 | 0.0065356 | 0.084962 | 2118 |  | 3063
891 | TEMPLETON 2108A64 | 183052108 | TEMPLETON 2108 | A64 | FALSE | 18905.9424 | 3242.5015 | 2.0152 | 150 | 7.5966e-05 | 2309 | 88.4837 | 2011 | 0.0065293 | 0.9794 | 2119 | 0.02 | 2493
851 | HIGGINS 1110861610 | 152691110 | HIGGINS 1110 | 861610 | FALSE | 11222.3603 | 1689.7743 | 1.0502 | 99 | 0.00027833 | 162 | 23.4916 | 2410 | 0.0065286 | 0.64633 | 2120 |  | 2695
10050 | MIRABEL 110286326 | 42091102 | MIRABEL 1102 | 86326 | FALSE | 1145.996 | 1133.0955 | 0.70422 | 5 | 8.4164e-05 | 2088 | 38.1596 | 2289 | 0.0065228 | 0.032614 | 2121 |  | 3481
1904 | SONOMA 1105404 | 42721105 | SONOMA 1105 | 404 | FALSE | 7372.5748 | 3785.8959 | 2.3529 | 63 | 6.9011e-05 | 2509 | 86.9459 | 2016 | 0.0065164 | 0.41053 | 2122 | 0.24 | 1106
4884 | PLACERVILLE 1112CB | 153081112 | PLACERVILLE 1112 | CB | FALSE | 15016.5066 | 13697.3672 | 8.513 | 117 | 0.00025615 | 202 | 34.5981 | 2310 | 0.0065148 | 0.76223 | 2123 | 0.09 | 1568
3571 | OAKHURST 110377384 | 254421103 | OAKHURST 1103 | 77384 | FALSE | 7595.6346 | 7595.6346 | 4.7207 | 61 | 0.00017011 | 562 | 62.7847 | 2138 | 0.0065145 | 0.39738 | 2124 | 0.65 | 823
2586 | VOLTA 11021504 | 102541102 | VOLTA 1102 | 1504 | FALSE | 13347.4853 | 13347.4853 | 8.2955 | 95 | 5.8288e-05 | 2825 | 84.8611 | 2031 | 0.0065125 | 0.61869 | 2125 | 45.39 | 148
5574 | PARADISE 1104920400 | 102831104 | PARADISE 1104 | 920400 | FALSE | 7975.407 | 7538.764 | 4.6854 | 66 | 0.00044142 | 53 | 18.0732 | 2478 | 0.0064968 | 0.42879 | 2126 |  | 2964
3679 | SUNOL 1101MR297 | 14241101 | SUNOL 1101 | MR297 | FALSE | 9710.6915 | 9531.5764 | 5.9239 | 66 | 6.9143e-05 | 2502 | 221.7666 | 1602 | 0.0064881 | 0.42822 | 2127 | 0.06 | 1849
3379 | GEYSERVILLE 1101354 | 42891101 | GEYSERVILLE 1101 | 354 | FALSE | 12035.3765 | 1010.2026 | 0.62784 | 79 | 9.3149e-05 | 1816 | 134.0043 | 1836 | 0.0064828 | 0.51214 | 2128 |  | 2822
5354 | FORT ROSS 1121560 | 42851121 | FORT ROSS 1121 | 560 | FALSE | 9061.7878 | 8145.5491 | 5.0625 | 31 | 9.9934e-05 | 1648 | 60.8351 | 2148 | 0.0064599 | 0.20026 | 2129 | 0.02 | 2420
1701 | CALAVERAS CEMENT 110136880 | 162211101 | CALAVERAS CEMENT 1101 | 36880 | FALSE | 13851.9467 | 9899.4771 | 6.1526 | 92 | 8.6095e-05 | 2032 | 179.7214 | 1684 | 0.0064477 | 0.59319 | 2130 | 0.08 | 1578
3076 | PLACERVILLE 21061104 | 153082106 | PLACERVILLE 2106 | 1104 | FALSE | 79643.684 | 79643.684 | 49.4989 | 462 | 0.00011856 | 1216 | 56.9205 | 2171 | 0.0064469 | 2.9785 | 2131 | 111.82 | 14
6813 | CASTRO VALLEY 111010315 | 14091110 | CASTRO VALLEY 1110 | 10315 | FALSE | 8831.8074 | 8831.8074 | 5.489 | 53 | 0.00010699 | 1472 | 59.7801 | 2155 | 0.006431 | 0.34084 | 2132 |  | 3064
7135 | MOLINO 1102982462 | 42571102 | MOLINO 1102 | 982462 | FALSE | 2320.5593 | 2320.5593 | 1.4422 | 18 | 9.629e-05 | 1726 | 75.3379 | 2065 | 0.006427 | 0.11569 | 2133 |  | 3100
8349 | BRUNSWICK 1110CB | 152481110 | BRUNSWICK 1110 | CB | TRUE | 2754.8033 | 5.4992 | 0.0034177 | 26 | 0.00020884 | 366 | 19.5341 | 2454 | 0.0064174 | 0.16685 | 2134 | 0.01 | 2596
3244 | PLACERVILLE 111219712 | 153081112 | PLACERVILLE 1112 | 19712 | FALSE | 20850.3369 | 20776.2868 | 12.9125 | 151 | 0.000145 | 801 | 90.5715 | 1997 | 0.0064118 | 0.96818 | 2135 | 0.12 | 1371
3409 | PINE GROVE 110213438 | 163751102 | PINE GROVE 1102 | 13438 | FALSE | 26618.9181 | 26618.9181 | 16.5438 | 172 | 0.00010264 | 1581 | 69.7074 | 2096 | 0.0063999 | 1.1008 | 2136 | 82.17 | 45
9640 | OLEMA 110149756 | 42291101 | OLEMA 1101 | 49756 | FALSE | 9480.1738 | 1727.7805 | 1.0738 | 40 | 7.5687e-05 | 2316 | 118.0346 | 1881 | 0.0063622 | 0.25449 | 2137 | 0.01 | 2594
5813 | PERRY 1101CB | 183071101 | PERRY 1101 | CB | FALSE | 4085.1757 | 4085.1757 | 2.539 | 27 | 6.8809e-05 | 2513 | 75.2459 | 2066 | 0.0062536 | 0.16885 | 2138 | 0.07 | 1752
5598 | FROGTOWN 170236870 | 163451702 | FROGTOWN 1702 | 36870 | TRUE | 3829.3681 | 541.2922 | 0.33642 | 29 | 0.00011992 | 1188 | 41.8373 | 2269 | 0.0062483 | 0.1812 | 2139 | 0.04 | 2157
7823 | FORT BRAGG A 11013113 | 42761101 | FORT BRAGG A 1101 | 3113 | FALSE | 16133.333 | 16133.333 | 10.0269 | 68 | 8.3643e-05 | 2106 | 76.2422 | 2061 | 0.0062347 | 0.42396 | 2140 | 0.05 | 1961
3839 | PARADISE 11052214 | 102831105 | PARADISE 1105 | 2214 | FALSE | 29878.7054 | 24265.0129 | 15.0808 | 233 | 0.00042568 | 61 | 48.0844 | 2221 | 0.0062243 | 1.4503 | 2141 | 51.75 | 113
955 | STANISLAUS 170179826 | 162821701 | STANISLAUS 1701 | 79826 | FALSE | 16584.8842 | 16584.8842 | 10.3076 | 95 | 0.00015691 | 673 | 91.848 | 1994 | 0.0062159 | 0.59051 | 2142 | 0.15 | 1290
165 | CHALLENGE 110198174 | 103201101 | CHALLENGE 1101 | 98174 | FALSE | 19681.5881 | 19681.5881 | 12.2322 | 66 | 7.9168e-05 | 2229 | 58.0357 | 2166 | 0.0062048 | 0.40952 | 2143 | 22.16 | 296
2120 | BRUNSWICK 110350070 | 152481103 | BRUNSWICK 1103 | 50070 | FALSE | 28555.3412 | 28555.3412 | 17.7473 | 201 | 0.00011083 | 1394 | 43.6964 | 2255 | 0.0062036 | 1.2469 | 2144 | 128.64 | 7
4607 | SARATOGA 1107413816 | 83371107 | SARATOGA 1107 | 413816 | FALSE | 17928.3843 | 17928.3843 | 11.1426 | 104 | 0.00011948 | 1197 | 65.9071 | 2117 | 0.0061927 | 0.64404 | 2145 | 0.87 | 760
1564 | SAN LUIS OBISPO 1101483444 | 182631101 | SAN LUIS OBISPO 1101 | 483444 | FALSE | 8714.6826 | 3311.0968 | 2.0579 | 67 | 5.4635e-05 | 2929 | 67.496 | 2105 | 0.0061552 | 0.4124 | 2146 |  | 2731
4427 | PLACERVILLE 11118582 | 153081111 | PLACERVILLE 1111 | 8582 | FALSE | 19173.6398 | 15254.7771 | 9.4809 | 163 | 0.00018689 | 463 | 41.133 | 2272 | 0.0061345 | 0.99993 | 2147 | 0.05 | 1953
9649 | LOS GATOS 1107LA60 | 82021107 | LOS GATOS 1107 | LA60 | FALSE | 13957.1729 | 13957.1729 | 8.6744 | 61 | 0.00010054 | 1636 | 81.9054 | 2041 | 0.0061263 | 0.3737 | 2148 | 41.93 | 173
3992 | VOLTA 11021502 | 102541102 | VOLTA 1102 | 1502 | FALSE | 11680.2523 | 11680.2523 | 7.2593 | 80 | 8.0915e-05 | 2184 | 65.4099 | 2121 | 0.0061144 | 0.48915 | 2149 | 27.78 | 255
4576 | VALLEY VIEW 1106CB | 14341106 | VALLEY VIEW 1106 | CB | FALSE | 8114.1348 | 6042.2888 | 3.7553 | 50 | 0.00011189 | 1369 | 66.0103 | 2115 | 0.0060781 | 0.30391 | 2150 | 0.06 | 1817
10363 | SAN LEANDRO U 1114653758 | 13111114 | SAN LEANDRO U 1114 | 653758 | TRUE | 582.3673 | 582.3673 | 0.36194 | 5 | 5.5782e-05 | 2895 | 104.6024 | 1930 | 0.0060671 | 0.030336 | 2151 |  | 3538
7007 | ORO FINO 110238698 | 103031102 | ORO FINO 1102 | 38698 | FALSE | 25178.9612 | 25178.9612 | 15.6488 | 103 | 9.2036e-05 | 1843 | 61.204 | 2145 | 0.0060349 | 0.62159 | 2152 | 4.1 | 526
3531 | HALF MOON BAY 11039112 | 24101103 | HALF MOON BAY 1103 | 9112 | FALSE | 8500.5119 | 1386.5143 | 0.86172 | 68 | 4.4335e-05 | 3182 | 101.7861 | 1948 | 0.0060009 | 0.40806 | 2153 | 0.04 | 2214
9344 | HALF MOON BAY 1101821698 | 24101101 | HALF MOON BAY 1101 | 821698 | FALSE | 1364.9269 | 1364.9269 | 0.84831 | 9 | 5.5293e-05 | 2904 | 187.6587 | 1667 | 0.0060008 | 0.054007 | 2154 |  | 3345
10526 | SANTA ROSA A 1108409621 | 42151108 | SANTA ROSA A 1108 | 409621 | TRUE | 945.4612 | 219.1314 | 0.13619 | 4 | 8.5029e-05 | 2059 | 85.5196 | 2026 | 0.0059943 | 0.023977 | 2155 |  | 3567
3796 | CAMP EVERS 210612518 | 83622106 | CAMP EVERS 2106 | 12518 | FALSE | 25177.1399 | 25177.1399 | 15.6477 | 145 | 0.00025023 | 216 | 28.5941 | 2352 | 0.0059295 | 0.85978 | 2156 | 0.8 | 774
2601 | BRUNSWICK 11062104 | 152481106 | BRUNSWICK 1106 | 2104 | FALSE | 15810.2753 | 15810.2753 | 9.8261 | 123 | 0.00020356 | 384 | 19.3883 | 2456 | 0.0059169 | 0.72777 | 2157 | 38.88 | 194
2204 | OAKHURST 11035470 | 254421103 | OAKHURST 1103 | 5470 | FALSE | 14989.8273 | 14989.8273 | 9.3162 | 104 | 0.00010143 | 1618 | 96.9488 | 1973 | 0.0059093 | 0.61457 | 2158 | 14.88 | 353
2618 | ARVIN 110194892 | 253801101 | ARVIN 1101 | 94892 | TRUE | 15531.7609 | 345.9853 | 0.21503 | 66 | 3.5047e-05 | 3351 | 201.9181 | 1637 | 0.0059064 | 0.38983 | 2159 |  | 2790
6041 | CAMP EVERS 210694770 | 83622106 | CAMP EVERS 2106 | 94770 | FALSE | 6459.1608 | 3806.5671 | 2.3658 | 55 | 0.00027047 | 172 | 16.4987 | 2510 | 0.0059058 | 0.32482 | 2160 | 0.27 | 1050
1981 | COTATI 1105328 | 42271105 | COTATI 1105 | 328 | FALSE | 22172.9748 | 2414.9476 | 1.5009 | 173 | 9.4997e-05 | 1766 | 59.7612 | 2156 | 0.0058817 | 1.0175 | 2161 | 1 | 732
519 | POINT ARENA 110147952 | 43381101 | POINT ARENA 1101 | 47952 | FALSE | 16717.6297 | 16717.6297 | 10.3901 | 88 | 0.00011754 | 1233 | 58.6557 | 2163 | 0.0058506 | 0.51485 | 2162 | 0.09 | 1517
2535 | COTATI 1102825 | 42271102 | COTATI 1102 | 825 | TRUE | 3371.6214 | 749.4567 | 0.46579 | 26 | 6.9953e-05 | 2473 | 79.9838 | 2048 | 0.0058122 | 0.15112 | 2163 |  | 2782
698 | RESERVATION ROAD 11013026 | 182731101 | RESERVATION ROAD 1101 | 3026 | FALSE | 36330.5251 | 35201.2582 | 21.8777 | 238 | 5.5886e-05 | 2892 | 99.002 | 1958 | 0.0057671 | 1.3726 | 2164 | 2.36 | 610
4296 | MORGAN HILL 2105XR494 | 83242105 | MORGAN HILL 2105 | XR494 | TRUE | 11814.5496 | 737.5052 | 0.45836 | 98 | 5.6428e-05 | 2877 | 82.0467 | 2040 | 0.0057504 | 0.56354 | 2165 | 0.04 | 2167
875 | FULTON 110777670 | 42561107 | FULTON 1107 | 77670 | FALSE | 10996.9079 | 10874.5833 | 6.7586 | 98 | 0.00011661 | 1258 | 47.4912 | 2228 | 0.0057454 | 0.56305 | 2166 | 19.77 | 309
2839 | CAMP EVERS 210510294 | 83622105 | CAMP EVERS 2105 | 10294 | FALSE | 13501.9938 | 13501.9938 | 8.3915 | 95 | 0.00023536 | 261 | 22.5874 | 2416 | 0.0057046 | 0.54194 | 2167 | 48.18 | 131
4923 | GEYSERVILLE 1101480 | 42891101 | GEYSERVILLE 1101 | 480 | FALSE | 25809.6606 | 2502.4894 | 1.5553 | 161 | 6.7656e-05 | 2543 | 89.1189 | 2006 | 0.0057021 | 0.91803 | 2168 | 0.01 | 2595
5117 | WOODSIDE 11018912 | 24251101 | WOODSIDE 1101 | 8912 | FALSE | 6310.9141 | 6268.7877 | 3.8961 | 52 | 0.000205 | 381 | 25.8096 | 2383 | 0.0056974 | 0.29627 | 2169 | 26.71 | 266
6008 | GEYSERVILLE 1101482 | 42891101 | GEYSERVILLE 1101 | 482 | TRUE | 6000.1069 | 595.0555 | 0.36983 | 38 | 6e-05 | 2775 | 118.3715 | 1876 | 0.0056711 | 0.2155 | 2170 | 0.74 | 789
3612 | BIG BASIN 110212992 | 82841102 | BIG BASIN 1102 | 12992 | FALSE | 22915.4569 | 22915.4569 | 14.242 | 160 | 0.00020519 | 379 | 28.593 | 2353 | 0.0056575 | 0.90521 | 2171 | 1.14 | 711
151 | SUMMIT 1102CB | 152591102 | SUMMIT 1102 | CB | FALSE | 1694.4122 | 1694.4122 | 1.0531 | 22 | 5.8522e-05 | 2821 | 53.0175 | 2195 | 0.0056462 | 0.12422 | 2172 | 0.02 | 2450
585 | LUCERNE 110647198 | 43351106 | LUCERNE 1106 | 47198 | FALSE | 9365.2067 | 4939.462 | 3.0699 | 70 | 0.00010692 | 1477 | 39.3397 | 2280 | 0.0056207 | 0.39345 | 2173 | 0.04 | 2116
7910 | SILVERADO 2105167360 | 43432105 | SILVERADO 2105 | 167360 | FALSE | 15830.4656 | 15413.5909 | 9.5796 | 70 | 0.0001177 | 1232 | 51.7218 | 2203 | 0.0056116 | 0.39281 | 2174 |  | 3176
1304 | CURTIS 17028000 | 163351702 | CURTIS 1702 | 8000 | FALSE | 23055.4602 | 23055.4602 | 14.3291 | 174 | 0.00011159 | 1377 | 95.7818 | 1979 | 0.0056032 | 0.97497 | 2175 | 0.55 | 871
417 | RALSTON 1101CB | 24141101 | RALSTON 1101 | CB | TRUE | 4645.037 | 606.8044 | 0.37713 | 37 | 4.6425e-05 | 3127 | 105.6404 | 1927 | 0.0055946 | 0.207 | 2176 | 0.05 | 1970
1975 | RALSTON 11022028 | 24141102 | RALSTON 1102 | 2028 | FALSE | 3747.9741 | 3373.7724 | 2.0968 | 38 | 7.449e-05 | 2345 | 86.2641 | 2021 | 0.0055851 | 0.21223 | 2177 | 0.08 | 1658
6769 | ATASCADERO 1101A50 | 182541101 | ATASCADERO 1101 | A50 | FALSE | 33669.9383 | 31118.7087 | 19.3404 | 269 | 5.5958e-05 | 2891 | 116.8319 | 1888 | 0.0055802 | 1.5011 | 2178 | 0.22 | 1131
2377 | GUALALA 11121294 | 42841112 | GUALALA 1112 | 1294 | FALSE | 32661.4744 | 31953.6798 | 19.8593 | 234 | 6.861e-05 | 2518 | 79.062 | 2054 | 0.0055387 | 1.2961 | 2179 | 0.53 | 883
5858 | FAIRVIEW 2207P150 | 13432207 | FAIRVIEW 2207 | P150 | FALSE | 3652.8381 | 3652.8381 | 2.2703 | 18 | 9.5063e-05 | 1763 | 45.0393 | 2245 | 0.0055206 | 0.09937 | 2180 | 0.03 | 2243
2861 | PIT NO 5 11011660 | 101321101 | PIT NO 5 1101 | 1660 | FALSE | 7855.6793 | 7855.6793 | 4.8823 | 43 | 0.00014039 | 865 | 43.7408 | 2254 | 0.0055185 | 0.23729 | 2181 | 0.02 | 2545
4568 | RINCON 1101CB | 43321101 | RINCON 1101 | CB | FALSE | 7739.8411 | 2580.5041 | 1.6038 | 68 | 0.00014616 | 786 | 21.7605 | 2428 | 0.0054995 | 0.37397 | 2182 | 0.06 | 1798
8511 | SAN ARDO 1101610148 | 182191101 | SAN ARDO 1101 | 610148 | FALSE | 19896.3037 | 3154.5584 | 1.9606 | 58 | 4.5598e-05 | 3151 | 102.3263 | 1944 | 0.0054812 | 0.31791 | 2183 |  | 3231
4730 | HARTLEY 110194178 | 43211101 | HARTLEY 1101 | 94178 | FALSE | 6646.4632 | 3457.4484 | 2.1488 | 57 | 7.3272e-05 | 2388 | 42.0306 | 2265 | 0.0054615 | 0.3113 | 2184 | 0.03 | 2290
1445 | BIG BASIN 1102CB | 82841102 | BIG BASIN 1102 | CB | FALSE | 9963.4073 | 9963.4073 | 6.1923 | 59 | 0.00022265 | 308 | 33.5088 | 2315 | 0.0054141 | 0.31943 | 2185 | 0.49 | 898
6388 | HALF MOON BAY 11036012 | 24101103 | HALF MOON BAY 1103 | 6012 | FALSE | 15479.7977 | 10729.2764 | 6.6683 | 79 | 9.0533e-05 | 1896 | 70.018 | 2095 | 0.0054078 | 0.42722 | 2186 | 0.08 | 1585
629 | LAURELES 11112020 | 182371111 | LAURELES 1111 | 2020 | FALSE | 55275.2572 | 55275.2572 | 34.3538 | 281 | 9.1434e-05 | 1861 | 43.1327 | 2260 | 0.005376 | 1.5107 | 2187 | 0.23 | 1114
3079 | OCEANO 1102V50 | 182601102 | OCEANO 1102 | V50 | FALSE | 16840.5394 | 11517.5193 | 7.1582 | 107 | 4.7059e-05 | 3112 | 96.3505 | 1978 | 0.005367 | 0.57427 | 2188 | 0.11 | 1428
342 | WOODACRE 1101404 | 43021101 | WOODACRE 1101 | 404 | FALSE | 19975.081 | 19975.081 | 12.4146 | 152 | 0.00018515 | 471 | 26.3611 | 2372 | 0.0053668 | 0.81576 | 2189 | 92.58 | 29
4506 | TIDEWATER 210657926 | 14652106 | TIDEWATER 2106 | 57926 | TRUE | 18926.9724 | 200.7916 | 0.12479 | 97 | 5.4965e-05 | 2914 | 62.5543 | 2139 | 0.0053561 | 0.51954 | 2190 |  | 2900
6794 | CAMP EVERS 21055188 | 83622105 | CAMP EVERS 2105 | 5188 | FALSE | 3280.6197 | 3280.6197 | 2.0389 | 19 | 0.00034885 | 92 | 16.3316 | 2511 | 0.0053482 | 0.10162 | 2191 | 7.26 | 449
4962 | MONTE RIO 1113652 | 42811113 | MONTE RIO 1113 | 652 | FALSE | 2607.8717 | 2607.8717 | 1.6208 | 25 | 0.00027854 | 161 | 20.0324 | 2448 | 0.0053427 | 0.13357 | 2192 | 55.16 | 104
5950 | COTATI 1102260 | 42271102 | COTATI 1102 | 260 | FALSE | 9537.0372 | 4317.1662 | 2.6831 | 68 | 6.2862e-05 | 2687 | 71.585 | 2084 | 0.0053405 | 0.36316 | 2193 | 0.78 | 778
2816 | HICKS 2101574315 | 83432101 | HICKS 2101 | 574315 | FALSE | 12024.0849 | 11904.9852 | 7.399 | 78 | 0.00010886 | 1429 | 65.6711 | 2118 | 0.005318 | 0.4148 | 2194 |  | 2800
4882 | NARROWS 210276952 | 153132102 | NARROWS 2102 | 76952 | FALSE | 18206.8026 | 3648.4496 | 2.2675 | 161 | 0.00026698 | 179 | 39.5343 | 2276 | 0.0052383 | 0.84337 | 2195 | 0.06 | 1785
8374 | SAN JOAQUIN #3 1103501771 | 252531103 | SAN JOAQUIN #3 1103 | 501771 | FALSE | 7891.6601 | 7891.6601 | 4.9047 | 54 | 4.0591e-05 | 3256 | 137.8049 | 1819 | 0.0052248 | 0.28214 | 2196 |  | 3217
4446 | OTTER 1101440 | 182941101 | OTTER 1101 | 440 | FALSE | 17666.8696 | 13392.7701 | 8.3237 | 107 | 5.2851e-05 | 2975 | 95.646 | 1980 | 0.0051543 | 0.5515 | 2197 | 0.05 | 1917
1813 | PUEBLO 210375612 | 43292103 | PUEBLO 2103 | 75612 | TRUE | 15618.6787 | 0 | 0 | 114 | 6.2516e-05 | 2703 | 68.7688 | 2099 | 0.0051135 | 0.58294 | 2198 |  | 2747
3962 | POINT MORETTI 110112122 | 82931101 | POINT MORETTI 1101 | 12122 | FALSE | 12740.7086 | 10570.3766 | 6.5695 | 63 | 0.00010779 | 1455 | 51.4668 | 2205 | 0.0051004 | 0.32133 | 2199 | 0.03 | 2382
6972 | BRUNSWICK 1102940 | 152481102 | BRUNSWICK 1102 | 940 | FALSE | 5636.9672 | 1911.101 | 1.1878 | 46 | 0.00018608 | 466 | 23.9825 | 2400 | 0.005067 | 0.23308 | 2200 | 7.35 | 447
2994 | SHADY GLEN 110132726 | 152431101 | SHADY GLEN 1101 | 32726 | FALSE | 19770.2597 | 19581.5665 | 12.17 | 146 | 0.00014193 | 840 | 48.5752 | 2218 | 0.00506 | 0.73876 | 2201 | 0.1 | 1475
5931 | EAST QUINCY 11012452 | 102551101 | EAST QUINCY 1101 | 2452 | TRUE | 11049.8485 | 228.5177 | 0.14202 | 87 | 5.4568e-05 | 2931 | 79.1562 | 2053 | 0.0050248 | 0.43716 | 2202 | 13.72 | 363
1799 | MORGAN HILL 2105XR578 | 83242105 | MORGAN HILL 2105 | XR578 | TRUE | 1108.6732 | 261.0602 | 0.16225 | 12 | 5.1652e-05 | 3003 | 53.5212 | 2190 | 0.0050174 | 0.060209 | 2203 | 0.02 | 2414
5416 | ANNAPOLIS 1101528344 | 42861101 | ANNAPOLIS 1101 | 528344 | FALSE | 43372.0838 | 43372.0838 | 26.9559 | 171 | 9.687e-05 | 1717 | 60.4469 | 2152 | 0.0049999 | 0.85498 | 2204 |  | 2950
7537 | LOS OSITOS 2102148504 | 182082102 | LOS OSITOS 2102 | 148504 | TRUE | 3218.0268 | 275.7602 | 0.17139 | 14 | 6.4053e-05 | 2643 | 71.3988 | 2086 | 0.0049963 | 0.069948 | 2205 |  | 3134
235 | KONOCTI 11022293 | 43311102 | KONOCTI 1102 | 2293 | FALSE | 2820.5709 | 2820.5709 | 1.753 | 21 | 6.9405e-05 | 2492 | 78.9038 | 2056 | 0.0049653 | 0.10427 | 2206 | 0.04 | 2140
3072 | ANTLER 1101CB | 103271101 | ANTLER 1101 | CB | FALSE | 2574.4725 | 2574.4725 | 1.6 | 18 | 0.00018307 | 488 | 33.0833 | 2322 | 0.0049349 | 0.088829 | 2207 | 0.05 | 1919
8410 | CAMP EVERS 210611533 | 83622106 | CAMP EVERS 2106 | 11533 | FALSE | 4249.6596 | 4249.6596 | 2.6412 | 28 | 9.1401e-05 | 1863 | 58.6478 | 2164 | 0.0048855 | 0.13679 | 2208 | 29.27 | 243
3050 | AUBERRY 1101R324 | 254151101 | AUBERRY 1101 | R324 | FALSE | 17238.3934 | 17238.3934 | 10.7137 | 119 | 3.9517e-05 | 3277 | 112.2851 | 1904 | 0.0048731 | 0.5799 | 2209 | 35.54 | 213
9906 | POINT MORETTI 110183716 | 82931101 | POINT MORETTI 1101 | 83716 | FALSE | 4275.4859 | 4027.3677 | 2.503 | 22 | 0.00011418 | 1318 | 54.1847 | 2187 | 0.0048588 | 0.10689 | 2210 | 0.02 | 2436
5631 | PARADISE 1105878870 | 102831105 | PARADISE 1105 | 878870 | FALSE | 4057.446 | 4057.446 | 2.5217 | 29 | 0.00048816 | 33 | 4.9842 | 2754 | 0.0048412 | 0.1404 | 2211 |  | 2967
1901 | MOUNTAIN QUARRIES 21011184 | 152282101 | MOUNTAIN QUARRIES 2101 | 1184 | FALSE | 18935.6341 | 18820.6068 | 11.6971 | 136 | 0.00016372 | 603 | 34.7864 | 2309 | 0.0048403 | 0.65828 | 2212 | 54.38 | 107
4871 | BRUNSWICK 11052130 | 152481105 | BRUNSWICK 1105 | 2130 | FALSE | 23180.7639 | 23180.7639 | 14.4069 | 163 | 5.7718e-05 | 2845 | 88.5821 | 2010 | 0.0048209 | 0.78581 | 2213 | 63.53 | 81
10520 | CASTRO VALLEY 1110MR273 | 14091110 | CASTRO VALLEY 1110 | MR273 | FALSE | 1164.6083 | 1164.6083 | 0.72381 | 13 | 7.8527e-05 | 2248 | 62.481 | 2140 | 0.0047919 | 0.062294 | 2214 |  | 3564
9367 | REDBUD 110244119 | 43191102 | REDBUD 1102 | 44119 | TRUE | 4510.2451 | 512.7214 | 0.31866 | 35 | 5.2979e-05 | 2968 | 87.4332 | 2013 | 0.0047623 | 0.16668 | 2215 | 0.04 | 2190
1147 | STAFFORD 11011082 | 43201101 | STAFFORD 1101 | 1082 | FALSE | 4959.0869 | 2511.2326 | 1.5607 | 36 | 3.822e-05 | 3296 | 64.7708 | 2123 | 0.0047619 | 0.17143 | 2216 | 1.65 | 659
2516 | MIWUK 17028130 | 163661702 | MIWUK 1702 | 8130 | FALSE | 15961.1359 | 15961.1359 | 9.9199 | 123 | 8.1184e-05 | 2179 | 72.5007 | 2080 | 0.0047602 | 0.5855 | 2217 | 65.59 | 76
2340 | JESSUP 1102CB | 103441102 | JESSUP 1102 | CB | TRUE | 5810.1426 | 159.6823 | 0.099243 | 47 | 0.00010848 | 1437 | 74.8868 | 2068 | 0.0047601 | 0.22372 | 2218 | 0.03 | 2307
10932 | CALPELLA 1102127462 | 43411102 | CALPELLA 1102 | 127462 | TRUE | 205.3095 | 189.2737 | 0.11763 | 2 | 0.00015962 | 647 | 47.5976 | 2225 | 0.0047158 | 0.0094316 | 2219 |  | 3622
9177 | MORAGA 1105829530 | 13801105 | MORAGA 1105 | 829530 | FALSE | 4171.4477 | 2687.7051 | 1.6704 | 32 | 7.4329e-05 | 2348 | 92.7573 | 1991 | 0.0047024 | 0.15048 | 2220 |  | 3320
1591 | SAN JOAQUIN #3 1101673480 | 252531101 | SAN JOAQUIN #3 1101 | 673480 | FALSE | 20487.8392 | 20487.8392 | 12.7333 | 88 | 0.00010713 | 1470 | 66.7652 | 2110 | 0.0046984 | 0.41346 | 2221 |  | 2733
7450 | WILLOW CREEK 1103CB | 192171103 | WILLOW CREEK 1103 | CB | FALSE | 6307.2067 | 6307.2067 | 3.92 | 54 | 0.00038312 | 73 | 17.6674 | 2486 | 0.0046671 | 0.25202 | 2222 | 0.09 | 1518
3048 | LAURELES 1111432 | 182371111 | LAURELES 1111 | 432 | FALSE | 79373.0607 | 79373.0607 | 49.3307 | 320 | 6.1723e-05 | 2728 | 74.7952 | 2069 | 0.0046501 | 1.488 | 2223 | 0.19 | 1170
9657 | PIT NO 5 1101CB | 101321101 | PIT NO 5 1101 | CB | FALSE | 1162.2395 | 1162.2395 | 0.72234 | 10 | 0.00013488 | 929 | 47.6107 | 2224 | 0.0046279 | 0.046279 | 2224 | 0.01 | 2572
2107 | MIRABEL 110238514 | 42091102 | MIRABEL 1102 | 38514 | FALSE | 17257.2473 | 17257.2473 | 10.7254 | 102 | 0.00021556 | 338 | 24.5363 | 2394 | 0.0046099 | 0.47021 | 2225 | 0.75 | 788
4382 | WOODSIDE 11011922 | 24251101 | WOODSIDE 1101 | 1922 | FALSE | 7694.4261 | 7391.7604 | 4.594 | 70 | 0.00019092 | 438 | 30.2755 | 2341 | 0.004588 | 0.32116 | 2226 | 17.29 | 334
4539 | LOS GATOS 110760118 | 82021107 | LOS GATOS 1107 | 60118 | FALSE | 44902.9478 | 44902.9478 | 27.9074 | 323 | 0.00017204 | 550 | 26.0465 | 2376 | 0.0045775 | 1.4785 | 2227 | 45.32 | 149
8332 | VINEYARD 2108MR172 | 14502108 | VINEYARD 2108 | MR172 | TRUE | 1779.1253 | 856.8002 | 0.5325 | 26 | 6.2738e-05 | 2692 | 64.6297 | 2125 | 0.0045679 | 0.11876 | 2228 | 27.77 | 256
4690 | CORRAL 1103681991 | 162991103 | CORRAL 1103 | 681991 | FALSE | 6056.3505 | 2212.0344 | 1.3748 | 50 | 6.8561e-05 | 2521 | 61.126 | 2147 | 0.0045171 | 0.22586 | 2229 |  | 2909
10188 | BOLINAS 11011232 | 42261101 | BOLINAS 1101 | 1232 | FALSE | 3935.7724 | 3637.3088 | 2.2606 | 22 | 9.124e-05 | 1868 | 55.6272 | 2178 | 0.0045024 | 0.099054 | 2230 | 3.14 | 560
4590 | REDBUD 11021212 | 43191102 | REDBUD 1102 | 1212 | TRUE | 6586.9975 | 0 | 0 | 62 | 4.464e-05 | 3173 | 87.4084 | 2014 | 0.0044984 | 0.2789 | 2231 | 0.42 | 928
6700 | TIVY VALLEY 1107CB | 252941107 | TIVY VALLEY 1107 | CB | TRUE | 35309.4801 | 290.0531 | 0.18027 | 155 | 3.607e-05 | 3336 | 256.8183 | 1529 | 0.0044835 | 0.69495 | 2232 |  | 3056
7824 | CAYUCOS 1102317156 | 182551102 | CAYUCOS 1102 | 317156 | FALSE | 18303.2443 | 3816.311 | 2.3719 | 67 | 5.1745e-05 | 3000 | 86.4803 | 2018 | 0.0044039 | 0.29506 | 2233 |  | 3166
9117 | WEST POINT 11021535 | 163201102 | WEST POINT 1102 | 1535 | FALSE | 4933.5895 | 4933.5895 | 3.0662 | 30 | 6.0964e-05 | 2749 | 63.4215 | 2132 | 0.0043786 | 0.13136 | 2234 | 52.41 | 112
1000 | MORGAN HILL 2111CB | 83242111 | MORGAN HILL 2111 | CB | TRUE | 3629.5545 | 353.0082 | 0.2194 | 38 | 5.0792e-05 | 3020 | 63.168 | 2135 | 0.0043636 | 0.16582 | 2235 | 0.22 | 1127
9339 | LAKEWOOD 2109432198 FM | 13532109 | LAKEWOOD 2109 | 432198 FM | TRUE | 3829.098 | 907.0096 | 0.56371 | 31 | 7.0176e-05 | 2467 | 53.7914 | 2188 | 0.004363 | 0.13525 | 2236 |  | 3344
420 | ARCATA 11225384 | 192021122 | ARCATA 1122 | 5384 | FALSE | 28128.0957 | 25050.2712 | 15.5688 | 202 | 0.0002103 | 356 | 21.9397 | 2426 | 0.0043604 | 0.88081 | 2237 | 0.18 | 1214
268 | MIRABEL 1102332 | 42091102 | MIRABEL 1102 | 332 | FALSE | 9174.8238 | 9174.8238 | 5.7022 | 67 | 0.00022781 | 292 | 15.3212 | 2526 | 0.0043573 | 0.29194 | 2238 | 30.76 | 235
6281 | MONTE RIO 11131989 | 42811113 | MONTE RIO 1113 | 1989 | FALSE | 1195.1936 | 1195.1936 | 0.74282 | 9 | 0.00014388 | 816 | 55.5275 | 2179 | 0.0043487 | 0.039138 | 2239 | 44.54 | 158
11081 | OAKHURST 110310723 | 254421103 | OAKHURST 1103 | 10723 | TRUE | 6.3415 | 6.3415 | 0.0039412 | 1 | 9.0549e-05 | 1895 | 47.5921 | 2226 | 0.0043094 | 0.0043094 | 2240 | 48.3 | 130
8151 | SILVERADO 2105309298 | 43432105 | SILVERADO 2105 | 309298 | FALSE | 3091.9426 | 1768.6422 | 1.0992 | 23 | 9.5445e-05 | 1744 | 39.3183 | 2281 | 0.0043094 | 0.099116 | 2241 |  | 3197
4858 | GUALALA 111223444 | 42841112 | GUALALA 1112 | 23444 | FALSE | 23380.6907 | 23380.6907 | 14.5312 | 135 | 0.00010219 | 1599 | 47.2338 | 2229 | 0.0042666 | 0.57599 | 2242 | 0.12 | 1396
2658 | CAMP EVERS 210660124 | 83622106 | CAMP EVERS 2106 | 60124 | FALSE | 36140.2282 | 36140.2282 | 22.4613 | 267 | 0.00016531 | 587 | 37.1047 | 2296 | 0.0042657 | 1.1389 | 2243 | 77.48 | 53
7144 | BELLEVUE 1102392 | 43181102 | BELLEVUE 1102 | 392 | TRUE | 10922.1116 | 404.9115 | 0.25165 | 68 | 9.4205e-05 | 1789 | 58.5408 | 2165 | 0.0042431 | 0.28853 | 2244 | 0.28 | 1035
5164 | MORAGA 1104N532R | 13801104 | MORAGA 1104 | N532R | FALSE | 7429.2796 | 5942.762 | 3.6935 | 65 | 9.0315e-05 | 1903 | 44.8885 | 2247 | 0.004228 | 0.27482 | 2245 | 0.09 | 1560
9096 | BIG BASIN 11022253 | 82841102 | BIG BASIN 1102 | 2253 | FALSE | 2335.3363 | 2335.3363 | 1.4514 | 12 | 0.00020821 | 370 | 19.8765 | 2451 | 0.0041981 | 0.050377 | 2246 | 0.17 | 1238
4580 | WEST POINT 11021341 | 163201102 | WEST POINT 1102 | 1341 | FALSE | 15927.2159 | 15927.2159 | 9.8988 | 87 | 5.9226e-05 | 2799 | 79.2605 | 2052 | 0.0041901 | 0.36454 | 2247 | 0.52 | 886
2630 | MC ARTHUR 110153120 | 103491101 | MC ARTHUR 1101 | 53120 | TRUE | 12732.032 | 173.1766 | 0.10763 | 92 | 2.9816e-05 | 3429 | 159.0093 | 1750 | 0.004183 | 0.38483 | 2248 |  | 2793
9114 | LAS GALLINAS A 1105CB | 42991105 | LAS GALLINAS A 1105 | CB | TRUE | 3345.6946 | 710.3038 | 0.44146 | 26 | 0.00011363 | 1329 | 21.0918 | 2434 | 0.0041416 | 0.10768 | 2249 | 0.02 | 2541
2500 | EL DORADO PH 2101CB | 152762101 | EL DORADO PH 2101 | CB | FALSE | 11999.4505 | 11999.4505 | 7.4577 | 74 | 0.00013448 | 935 | 29.3004 | 2350 | 0.0041406 | 0.3064 | 2250 | 69.29 | 70
2083 | ALTO 11201214 | 42031120 | ALTO 1120 | 1214 | FALSE | 7293.1721 | 5549.8668 | 3.4493 | 45 | 4.7944e-05 | 3095 | 64.0131 | 2129 | 0.004132 | 0.18594 | 2251 | 0.05 | 2016
1240 | EL DORADO PH 210126000 | 152762101 | EL DORADO PH 2101 | 26000 | FALSE | 55311.5705 | 55311.5705 | 34.3764 | 339 | 0.00010511 | 1521 | 49.7196 | 2212 | 0.0041222 | 1.3974 | 2252 | 73.15 | 63
2830 | MENLO 11029110 | 24131102 | MENLO 1102 | 9110 | FALSE | 15217.7544 | 1491.4373 | 0.92693 | 138 | 0.00014546 | 798 | 26.6167 | 2370 | 0.0040502 | 0.55893 | 2253 | 0.04 | 2097
8665 | BRUNSWICK 111094368 | 152481110 | BRUNSWICK 1110 | 94368 | TRUE | 768.9303 | 596.3821 | 0.37065 | 9 | 0.00048312 | 36 | 49.2875 | 2214 | 0.0040353 | 0.036317 | 2254 | 0.02 | 2527
2181 | MERCED FALLS 110222774 | 252811102 | MERCED FALLS 1102 | 22774 | FALSE | 5970.2453 | 1624.1247 | 1.0094 | 27 | 3.9002e-05 | 3287 | 127.212 | 1851 | 0.0040151 | 0.10841 | 2255 | 0.01 | 2610
2725 | BIG BASIN 110212124 | 82841102 | BIG BASIN 1102 | 12124 | FALSE | 7217.2962 | 7217.2962 | 4.4856 | 59 | 0.000304 | 126 | 21.0181 | 2436 | 0.0040119 | 0.2367 | 2256 | 0.28 | 1041
1448 | PARADISE 1103CB | 102831103 | PARADISE 1103 | CB | FALSE | 5575.8129 | 2217.6155 | 1.3783 | 61 | 0.0006536 | 11 | 4.7351 | 2763 | 0.0039747 | 0.24245 | 2257 | 15.11 | 350
3467 | WEIMAR 11012740 | 152491101 | WEIMAR 1101 | 2740 | FALSE | 30939.0056 | 30939.0056 | 19.2287 | 235 | 0.00018236 | 494 | 38.193 | 2288 | 0.003969 | 0.93271 | 2258 | 0.14 | 1313
497 | AUBURN 1101173014 | 152161101 | AUBURN 1101 | 173014 | FALSE | 5456.0353 | 5290.5313 | 3.2881 | 43 | 0.00018414 | 479 | 19.9675 | 2449 | 0.0039357 | 0.16924 | 2259 |  | 2680
7194 | WEST POINT 1101L373 | 163201101 | WEST POINT 1101 | L373 | FALSE | 11899.5211 | 11899.5211 | 7.3956 | 93 | 5.9702e-05 | 2784 | 62.944 | 2136 | 0.0039044 | 0.36311 | 2260 | 72.86 | 65
6474 | STAFFORD 11021048 | 43201102 | STAFFORD 1102 | 1048 | FALSE | 8484.8832 | 8484.8832 | 5.2734 | 72 | 0.00016147 | 626 | 26.1474 | 2375 | 0.0039018 | 0.28093 | 2261 | 0.13 | 1345
4378 | RESERVATION ROAD 110222136 | 182731102 | RESERVATION ROAD 1102 | 22136 | FALSE | 8542.0356 | 2842.9957 | 1.7669 | 59 | 4.541e-05 | 3155 | 51.6014 | 2204 | 0.0038829 | 0.22909 | 2262 | 0.01 | 2587
7747 | ANITA 1106552724 | 102841106 | ANITA 1106 | 552724 | FALSE | 23613.9534 | 2363.8176 | 1.4691 | 77 | 7.2387e-05 | 2405 | 63.51 | 2130 | 0.0038689 | 0.29791 | 2263 |  | 3158
6189 | PLACER 1101106534 | 152461101 | PLACER 1101 | 106534 | FALSE | 4199.7803 | 1949.2483 | 1.2115 | 38 | 0.00024793 | 223 | 15.6992 | 2522 | 0.0038425 | 0.14601 | 2264 |  | 3012
8134 | MORAGA 110518396 | 13801105 | MORAGA 1105 | 18396 | TRUE | 1851.7327 | 293.2889 | 0.18228 | 16 | 3.5702e-05 | 3339 | 53.4957 | 2191 | 0.0038298 | 0.061277 | 2265 | 4.8 | 506
2828 | PANORAMA 11019092 | 103461101 | PANORAMA 1101 | 9092 | TRUE | 15725.9351 | 255.1238 | 0.15856 | 113 | 0.0001025 | 1589 | 29.6083 | 2349 | 0.0038237 | 0.43208 | 2266 | 1.99 | 627
1451 | MIWUK 1701953336 | 163661701 | MIWUK 1701 | 953336 | FALSE | 19079.6136 | 19079.6136 | 11.8581 | 132 | 9.944e-05 | 1658 | 31.4057 | 2336 | 0.0038168 | 0.50381 | 2267 |  | 2724
8189 | CAMP EVERS 210660120 | 83622106 | CAMP EVERS 2106 | 60120 | FALSE | 6993.663 | 6993.663 | 4.3466 | 42 | 0.0001694 | 567 | 23.8386 | 2403 | 0.0038109 | 0.16006 | 2268 | 27.45 | 257
3086 | PANOCHE 11034016 | 253671103 | PANOCHE 1103 | 4016 | FALSE | 20664.9565 | 3776.8409 | 2.3473 | 59 | 4.6142e-05 | 3134 | 98.5723 | 1963 | 0.0038045 | 0.22447 | 2269 | 0.01 | 2621
3744 | FORESTHILL 110150486 | 152181101 | FORESTHILL 1101 | 50486 | FALSE | 18786.575 | 18786.575 | 11.6759 | 163 | 0.00010932 | 1425 | 43.079 | 2261 | 0.0037623 | 0.61325 | 2270 | 86.95 | 38
1371 | PINE GROVE 11021222 | 163751102 | PINE GROVE 1102 | 1222 | FALSE | 27771.0153 | 27771.0153 | 17.2598 | 218 | 0.0001881 | 453 | 22.6532 | 2414 | 0.0037571 | 0.81905 | 2271 | 105.89 | 18
2904 | MONTE RIO 111153477 | 42811111 | MONTE RIO 1111 | 53477 | FALSE | 3295.7871 | 3295.7871 | 2.0483 | 21 | 0.00016065 | 635 | 22.7228 | 2413 | 0.0037529 | 0.078812 | 2272 | 34.99 | 215
4467 | RINCON 1102CB | 43321102 | RINCON 1102 | CB | FALSE | 5699.8132 | 4772.4685 | 2.9661 | 49 | 0.00014009 | 868 | 39.048 | 2283 | 0.0037209 | 0.18233 | 2273 | 0.11 | 1423
4949 | BRENTWOOD 210598606 | 14592105 | BRENTWOOD 2105 | 98606 | TRUE | 13179.7667 | 138.4782 | 0.086065 | 88 | 8.8531e-05 | 1972 | 91.908 | 1993 | 0.0037138 | 0.32681 | 2274 |  | 2931
8946 | MIRABEL 110213597 | 42091102 | MIRABEL 1102 | 13597 | TRUE | 751.816 | 751.816 | 0.46726 | 6 | 0.00014116 | 850 | 23.8355 | 2404 | 0.0037122 | 0.022273 | 2275 | 8.42 | 427
3893 | FAIRVIEW 2207P304 | 13432207 | FAIRVIEW 2207 | P304 | FALSE | 9851.3779 | 8440.4652 | 5.2458 | 47 | 9.3563e-05 | 1809 | 31.6902 | 2333 | 0.0037077 | 0.17426 | 2276 | 0.09 | 1556
7178 | BURNEY 11019042 | 103311101 | BURNEY 1101 | 9042 | FALSE | 5080.7921 | 5080.7921 | 3.1577 | 31 | 4.1887e-05 | 3227 | 82.8476 | 2036 | 0.0036996 | 0.11469 | 2277 | 0.11 | 1447
8790 | MONTICELLO 110152910 | 43051101 | MONTICELLO 1101 | 52910 | FALSE | 5038.2048 | 3510.8305 | 2.182 | 41 | 5.3924e-05 | 2944 | 73.7782 | 2074 | 0.0036877 | 0.1512 | 2278 | 0.81 | 773
8586 | WEST POINT 1102L3733 | 163201102 | WEST POINT 1102 | L3733 | FALSE | 2820.1267 | 2820.1267 | 1.7527 | 22 | 6.6103e-05 | 2585 | 57.3124 | 2169 | 0.0036798 | 0.080956 | 2279 | 42.03 | 171
2143 | VOLTA 11029742 | 102541102 | VOLTA 1102 | 9742 | FALSE | 14685.6636 | 14685.6636 | 9.1272 | 120 | 4.1561e-05 | 3232 | 86.0041 | 2023 | 0.0036718 | 0.44061 | 2280 | 37.7 | 200
8195 | SAUSALITO 11021268 | 42491102 | SAUSALITO 1102 | 1268 | FALSE | 7937.7862 | 7937.7862 | 4.9334 | 46 | 4.2343e-05 | 3219 | 82.2871 | 2039 | 0.0036642 | 0.16855 | 2281 | 0.09 | 1520
200 | PETALUMA C 1109270 | 42631109 | PETALUMA C 1109 | 270 | FALSE | 12312.4188 | 3397.4138 | 2.1115 | 101 | 2.7315e-05 | 3467 | 46.9819 | 2234 | 0.0036568 | 0.36934 | 2282 | 0.04 | 2120
9326 | COARSEGOLD 2102383092 | 254432102 | COARSEGOLD 2102 | 383092 | TRUE | 613.1926 | 613.1926 | 0.3811 | 5 | 0.00016062 | 636 | 14.3241 | 2544 | 0.0036345 | 0.018173 | 2283 | 0.2 | 1163
10306 | SOLEDAD 1114413916 | 182051114 | SOLEDAD 1114 | 413916 | FALSE | 6367.8068 | 2275.8898 | 1.4145 | 24 | 2.8421e-05 | 3448 | 60.5803 | 2151 | 0.0036248 | 0.086994 | 2284 |  | 3529
6836 | LLAGAS 2106338878 | 83182106 | LLAGAS 2106 | 338878 | FALSE | 7522.3054 | 3300.0012 | 2.051 | 23 | 6.6373e-05 | 2579 | 72.1128 | 2083 | 0.0036203 | 0.083266 | 2285 |  | 3067
685 | MONTE RIO 1113524 | 42811113 | MONTE RIO 1113 | 524 | FALSE | 10078.6837 | 10078.6837 | 6.2639 | 76 | 0.00026116 | 193 | 18.5187 | 2467 | 0.0036171 | 0.2749 | 2286 | 109.05 | 15
3555 | DUNBAR 1103CB | 43071103 | DUNBAR 1103 | CB | FALSE | 19272.7585 | 4335.2228 | 2.6944 | 149 | 0.00011557 | 1285 | 29.7426 | 2348 | 0.0036086 | 0.53768 | 2287 | 1.01 | 729
6157 | IGNACIO 11041290 | 42481104 | IGNACIO 1104 | 1290 | FALSE | 20913.8819 | 6586.7468 | 4.0937 | 126 | 8.6173e-05 | 2030 | 27.953 | 2362 | 0.0035797 | 0.45104 | 2288 | 0.02 | 2529
1177 | ORO FINO 1101CB | 103031101 | ORO FINO 1101 | CB | FALSE | 35929.6836 | 35929.6836 | 22.3304 | 271 | 0.00017817 | 517 | 43.307 | 2257 | 0.0035789 | 0.96987 | 2289 | 173.81 | 3
3178 | PENNGROVE 1101461338 | 43471101 | PENNGROVE 1101 | 461338 | FALSE | 2872.7742 | 2872.7742 | 1.7854 | 24 | 9.4013e-05 | 1793 | 40.8144 | 2273 | 0.0035591 | 0.085418 | 2290 |  | 2814
3360 | GRASS VALLEY 1101CB | 152031101 | GRASS VALLEY 1101 | CB | FALSE | 3780.8041 | 1415.7705 | 0.87991 | 32 | 0.00022566 | 302 | 20.6051 | 2441 | 0.0035509 | 0.11363 | 2291 | 2.79 | 582
10815 | HICKS 2101949522 | 83432101 | HICKS 2101 | 949522 | TRUE | 726.8328 | 708.2171 | 0.44016 | 2 | 0.00014682 | 775 | 72.2883 | 2082 | 0.0035464 | 0.0070929 | 2292 |  | 3609
6548 | WEST POINT 110113444 | 163201101 | WEST POINT 1101 | 13444 | FALSE | 27386.8447 | 27386.8447 | 17.021 | 221 | 7.9645e-05 | 2218 | 41.9022 | 2268 | 0.0035258 | 0.77919 | 2293 | 73.64 | 59
2950 | HICKS 2101XR162 | 83432101 | HICKS 2101 | XR162 | TRUE | 14645.8548 | 989.1765 | 0.61478 | 122 | 5.6508e-05 | 2874 | 50.8473 | 2208 | 0.0035232 | 0.42983 | 2294 | 0.05 | 1985
9560 | VINEYARD 2107246084 | 14502107 | VINEYARD 2107 | 246084 | TRUE | 830.435 | 385.2443 | 0.23943 | 7 | 7.141e-05 | 2435 | 49.9181 | 2211 | 0.0035033 | 0.024523 | 2295 |  | 3377
3073 | CAMP EVERS 210510728 | 83622105 | CAMP EVERS 2105 | 10728 | FALSE | 16852.1183 | 16852.1183 | 10.4737 | 134 | 0.00034915 | 91 | 6.6304 | 2693 | 0.0034865 | 0.46719 | 2296 | 1.09 | 717
7203 | BRUNSWICK 110663124 | 152481106 | BRUNSWICK 1106 | 63124 | FALSE | 9481.8427 | 9481.8427 | 5.893 | 65 | 0.00021667 | 333 | 31.8764 | 2329 | 0.0034764 | 0.22596 | 2297 | 31.64 | 228
7594 | SHINGLE SPRINGS 2108CB | 153652108 | SHINGLE SPRINGS 2108 | CB | FALSE | 2376.1029 | 2376.1029 | 1.4768 | 18 | 0.00021932 | 326 | 147.9963 | 1784 | 0.0034725 | 0.062504 | 2298 | 0.24 | 1098
180 | HIGGINS 11041374 | 152691104 | HIGGINS 1104 | 1374 | FALSE | 13460.5941 | 12470.1527 | 7.7503 | 117 | 0.0001756 | 523 | 21.2592 | 2433 | 0.0034694 | 0.40592 | 2299 | 0.12 | 1408
8764 | TRES PINOS 1111203126 | 183221111 | TRES PINOS 1111 | 203126 | TRUE | 10848.7001 | 107.4611 | 0.066788 | 58 | 6.8097e-05 | 2533 | 54.2531 | 2186 | 0.0034419 | 0.19963 | 2300 |  | 3261
6133 | SALT SPRINGS 210237300 | 163692102 | SALT SPRINGS 2102 | 37300 | FALSE | 11208.5924 | 11208.5924 | 6.9662 | 41 | 9.1788e-05 | 1851 | 39.4946 | 2278 | 0.0034152 | 0.14002 | 2301 | 37.82 | 198
8353 | VOLTA 110254932 | 102541102 | VOLTA 1102 | 54932 | FALSE | 7042.6654 | 7042.6654 | 4.377 | 46 | 5.4607e-05 | 2930 | 80.6481 | 2045 | 0.0034144 | 0.15706 | 2302 | 25.23 | 272
1504 | HUMBOLDT BAY 1102741980 | 192341102 | HUMBOLDT BAY 1102 | 741980 | FALSE | 15211.0337 | 9241.1429 | 5.7434 | 81 | 0.00018104 | 504 | 20.6165 | 2440 | 0.0034064 | 0.27592 | 2303 |  | 2729
341 | COTATI 1102464 | 42271102 | COTATI 1102 | 464 | FALSE | 13038.4156 | 3443.5911 | 2.1402 | 103 | 8.8656e-05 | 1965 | 37.0346 | 2297 | 0.0034005 | 0.35026 | 2304 | 0.04 | 2168
1877 | FORT BRAGG A 110231304 | 42761102 | FORT BRAGG A 1102 | 31304 | FALSE | 34880.3162 | 34880.3162 | 21.6783 | 119 | 0.00010968 | 1417 | 25.8228 | 2381 | 0.0033857 | 0.40289 | 2305 | 0.23 | 1121
9731 | FITCH MOUNTAIN 1111792628 | 42751111 | FITCH MOUNTAIN 1111 | 792628 | TRUE | 1482.8091 | 365.6177 | 0.22723 | 13 | 7.1975e-05 | 2420 | 145.9054 | 1789 | 0.0033779 | 0.043913 | 2306 |  | 3408
10338 | FRANKLIN 1104P146 | 13921104 | FRANKLIN 1104 | P146 | FALSE | 5911.5651 | 5843.5425 | 3.6318 | 36 | 0.00010288 | 1572 | 24.7391 | 2392 | 0.0033674 | 0.12123 | 2307 | 0.05 | 1925
11025 | CALPINE 1144304 | 48011144 | CALPINE 1144 | 304 | TRUE | 74.6067 | 74.6067 | 0.046368 | 2 | 0.00013842 | 890 | 24.2406 | 2399 | 0.0033555 | 0.006711 | 2308 | 0.18 | 1213
7073 | RINCON 1101663641 | 43321101 | RINCON 1101 | 663641 | FALSE | 1909.334 | 1173.5613 | 0.72937 | 13 | 0.00014217 | 836 | 35.4244 | 2307 | 0.0033545 | 0.043609 | 2309 |  | 3093
37 | CURTIS 17019230 | 163351701 | CURTIS 1701 | 9230 | FALSE | 5065.9524 | 4064.6381 | 2.5262 | 41 | 0.00012174 | 1152 | 32.1288 | 2327 | 0.0033425 | 0.13704 | 2310 | 0.04 | 2191
7129 | GANSNER 1101336664 | 103021101 | GANSNER 1101 | 336664 | FALSE | 2515.571 | 1158.7417 | 0.72016 | 16 | 6.759e-05 | 2546 | 46.5783 | 2238 | 0.0033324 | 0.053319 | 2311 |  | 3098
6003 | CALPELLA 1102477890 | 43411102 | CALPELLA 1102 | 477890 | FALSE | 4846.0499 | 1726.9794 | 1.0733 | 35 | 9.2097e-05 | 1839 | 48.2183 | 2219 | 0.0033264 | 0.11642 | 2312 |  | 2995
6936 | LAMONT 11024222 | 253911102 | LAMONT 1102 | 4222 | FALSE | 26146.3036 | 4245.3884 | 2.6385 | 87 | 3.1604e-05 | 3407 | 230.387 | 1585 | 0.0033258 | 0.28934 | 2313 | 0.02 | 2510
1031 | VOLTA 110253130 | 102541102 | VOLTA 1102 | 53130 | FALSE | 22213.2961 | 22213.2961 | 13.8057 | 168 | 4.8271e-05 | 3088 | 94.8297 | 1982 | 0.0033207 | 0.55788 | 2314 | 57.28 | 97
729 | RADUM 1105806392 | 13151105 | RADUM 1105 | 806392 | FALSE | 8744.0051 | 5446.9277 | 3.3853 | 79 | 6.382e-05 | 2652 | 38.9119 | 2286 | 0.0033155 | 0.26192 | 2315 |  | 2691
6737 | POINT ARENA 1101476 | 43381101 | POINT ARENA 1101 | 476 | FALSE | 24463.8896 | 4825.127 | 2.9988 | 97 | 4.5962e-05 | 3139 | 73.5453 | 2078 | 0.0032902 | 0.31915 | 2316 | 0.02 | 2460
9971 | LOS OSITOS 2103258688 | 182082103 | LOS OSITOS 2103 | 258688 | FALSE | 5700.7117 | 1727.2951 | 1.0735 | 17 | 1.3021e-05 | 3601 | 51.8497 | 2202 | 0.0032882 | 0.0559 | 2317 |  | 3463
2467 | HARRIS 1109183860 | 192431109 | HARRIS 1109 | 183860 | FALSE | 12288.1398 | 7942.1796 | 4.9361 | 92 | 0.00018091 | 505 | 20.123 | 2446 | 0.0032843 | 0.30215 | 2318 |  | 2779
3741 | PINE GROVE 110152088 | 163751101 | PINE GROVE 1101 | 52088 | FALSE | 3986.2342 | 3986.2342 | 2.4775 | 28 | 0.00019225 | 433 | 17.8963 | 2482 | 0.0032783 | 0.091793 | 2319 | 0.06 | 1856
8487 | PIT NO 3 21011482 | 103732101 | PIT NO 3 2101 | 1482 | FALSE | 19365.2645 | 19365.2645 | 12.0356 | 43 | 0.0001494 | 744 | 53.6934 | 2189 | 0.0032735 | 0.14076 | 2320 | 0.01 | 2603
9213 | GREEN VALLEY 210197574 | 83192101 | GREEN VALLEY 2101 | 97574 | FALSE | 8779.1351 | 5743.5714 | 3.5697 | 60 | 8.4627e-05 | 2073 | 42.7148 | 2264 | 0.0032547 | 0.19528 | 2321 |  | 3327
6945 | CHOLAME 2102X06 | 182562102 | CHOLAME 2102 | X06 | TRUE | 20798.4951 | 651.9578 | 0.40519 | 40 | 5.1105e-05 | 3012 | 121.2254 | 1866 | 0.0032533 | 0.13013 | 2322 | 0.03 | 2295
1559 | PAUL SWEET 21065178 | 83252106 | PAUL SWEET 2106 | 5178 | FALSE | 11550.9267 | 11550.9267 | 7.1789 | 84 | 0.0001826 | 491 | 17.8913 | 2483 | 0.0032408 | 0.27223 | 2323 | 0.58 | 856
8048 | DEL MONTE 21042762 | 182222104 | DEL MONTE 2104 | 2762 | FALSE | 17774.3074 | 15060.1277 | 9.3599 | 138 | 9.1063e-05 | 1879 | 28.3252 | 2356 | 0.0032245 | 0.44498 | 2324 | 0.08 | 1622
394 | WOODSIDE 11049032 | 24251104 | WOODSIDE 1104 | 9032 | FALSE | 7741.5059 | 3452.7748 | 2.1459 | 72 | 0.00021411 | 342 | 20.493 | 2443 | 0.0032245 | 0.23216 | 2325 | 0.08 | 1581
3140 | BAYWOOD 1101CB | 182801101 | BAYWOOD 1101 | CB | FALSE | 46476.8109 | 7426.5465 | 4.6156 | 214 | 5.8116e-05 | 2833 | 45.5892 | 2241 | 0.003207 | 0.6863 | 2326 | 0.02 | 2421
197 | BRUNSWICK 1105733408 | 152481105 | BRUNSWICK 1105 | 733408 | FALSE | 5546.1563 | 5546.1563 | 3.447 | 45 | 0.00017527 | 527 | 18.0229 | 2479 | 0.0032065 | 0.14429 | 2327 |  | 2660
1600 | RINCON 1104786782 | 43321104 | RINCON 1104 | 786782 | FALSE | 5173.0207 | 3549.2326 | 2.2059 | 46 | 0.00014664 | 779 | 8.3437 | 2661 | 0.0032053 | 0.14745 | 2328 |  | 2734
7931 | PIT NO 5 11011658 | 101321101 | PIT NO 5 1101 | 1658 | FALSE | 7306.3402 | 7306.3402 | 4.5409 | 25 | 0.0001398 | 870 | 46.6629 | 2236 | 0.0031839 | 0.079597 | 2329 | 0.02 | 2471
4023 | DUNLAP 11037080 | 254061103 | DUNLAP 1103 | 7080 | FALSE | 17026.2434 | 17026.2434 | 10.5819 | 67 | 5.6266e-05 | 2881 | 33.4031 | 2317 | 0.0031698 | 0.21238 | 2330 | 0 | 2646
7290 | ARCATA 1121716954 | 192021121 | ARCATA 1121 | 716954 | FALSE | 18261.1322 | 11115.6995 | 6.9085 | 97 | 0.00020479 | 383 | 15.7424 | 2521 | 0.0031691 | 0.30741 | 2331 |  | 3112
8705 | CARLOTTA 112144150 | 192291121 | CARLOTTA 1121 | 44150 | FALSE | 5746.8082 | 5746.8082 | 3.5717 | 13 | 9.8025e-05 | 1689 | 54.8965 | 2182 | 0.0031685 | 0.04119 | 2332 | 0 | 2641
5063 | WOODSIDE 11043583 | 24251104 | WOODSIDE 1104 | 3583 | FALSE | 4565.0094 | 4565.0094 | 2.8372 | 38 | 0.00013592 | 920 | 25.7125 | 2385 | 0.0031615 | 0.12014 | 2333 | 0.78 | 781
8125 | PINE GROVE 1101CB | 163751101 | PINE GROVE 1101 | CB | FALSE | 6922.9717 | 6922.9717 | 4.3027 | 57 | 0.00036472 | 81 | 15.0767 | 2531 | 0.0031502 | 0.17956 | 2334 | 10.19 | 401
6730 | CAMP EVERS 210637210 | 83622106 | CAMP EVERS 2106 | 37210 | FALSE | 9746.716 | 9746.716 | 6.0576 | 65 | 0.00021978 | 324 | 16.5241 | 2509 | 0.0031442 | 0.20437 | 2335 | 0.45 | 916
82 | SNEATH LANE 1107CB | 22721107 | SNEATH LANE 1107 | CB | FALSE | 6249.0561 | 1615.0564 | 1.0038 | 45 | 3.6368e-05 | 3327 | 61.4823 | 2144 | 0.003121 | 0.14045 | 2336 | 0.03 | 2317
1487 | STAFFORD 11021258 | 43201102 | STAFFORD 1102 | 1258 | TRUE | 7855.298 | 501.9247 | 0.31195 | 65 | 3.9619e-05 | 3275 | 27.811 | 2365 | 0.0031184 | 0.2027 | 2337 |  | 2726
201 | RESERVATION ROAD 1101CB | 182731101 | RESERVATION ROAD 1101 | CB | FALSE | 15128.6127 | 8212.888 | 5.1043 | 106 | 2.9958e-05 | 3427 | 117.1254 | 1887 | 0.0031059 | 0.32923 | 2338 | 0.03 | 2246
9832 | WILLOW CREEK 1101CB | 192171101 | WILLOW CREEK 1101 | CB | TRUE | 460.8364 | 460.8364 | 0.28641 | 6 | 0.00063458 | 14 | 4.0266 | 2776 | 0.0031037 | 0.018622 | 2339 | 7.35 | 448
22 | PARADISE 1104457900 | 102831104 | PARADISE 1104 | 457900 | FALSE | 26252.3118 | 19380.7293 | 12.0452 | 208 | 0.00047135 | 40 | 18.1285 | 2474 | 0.0030985 | 0.64448 | 2340 |  | 2650
7703 | SILVERADO 21051306 | 43432105 | SILVERADO 2105 | 1306 | TRUE | 6582.7615 | 393.5916 | 0.24462 | 55 | 0.00018261 | 490 | 20.3553 | 2444 | 0.0030939 | 0.17016 | 2341 | 9.44 | 409
8415 | BIG MEADOWS 21012476 | 102812101 | BIG MEADOWS 2101 | 2476 | FALSE | 14000.8931 | 13050.7122 | 8.1111 | 75 | 7.3608e-05 | 2378 | 31.4311 | 2335 | 0.0030704 | 0.23028 | 2342 | 0.03 | 2379
2480 | REDBUD 1101CB | 43191101 | REDBUD 1101 | CB | FALSE | 11764.5735 | 5407.5285 | 3.3608 | 91 | 5.0448e-05 | 3027 | 32.7091 | 2324 | 0.0030523 | 0.27776 | 2343 | 0.09 | 1557
10178 | MAPLE CREEK 1101555034 | 192101101 | MAPLE CREEK 1101 | 555034 | FALSE | 4077.2208 | 2404.9179 | 1.4947 | 8 | 0.00031076 | 117 | 13.913 | 2553 | 0.0030461 | 0.024368 | 2344 |  | 3508
1443 | MENLO 11028952 | 24131102 | MENLO 1102 | 8952 | FALSE | 10739.4056 | 10739.4056 | 6.6746 | 82 | 0.0001072 | 1467 | 39.4973 | 2277 | 0.0030386 | 0.24916 | 2345 | 9.23 | 411
5316 | PAUL SWEET 210610424 | 83252106 | PAUL SWEET 2106 | 10424 | FALSE | 11629.4934 | 9151.9906 | 5.688 | 87 | 0.00013475 | 931 | 22.367 | 2420 | 0.0030267 | 0.26332 | 2346 | 0.25 | 1072
2267 | ELK 11011298 | 42981101 | ELK 1101 | 1298 | FALSE | 25951.4505 | 19969.5788 | 12.4112 | 119 | 7.3623e-05 | 2376 | 48.6421 | 2217 | 0.0030233 | 0.35978 | 2347 | 0.03 | 2376
6724 | CURTIS 17039210 | 163351703 | CURTIS 1703 | 9210 | FALSE | 36192.6146 | 36192.6146 | 22.4939 | 124 | 4.5003e-05 | 3160 | 67.0376 | 2108 | 0.0030209 | 0.37459 | 2348 | 0.31 | 1004
3063 | ELECTRA 1101L1697 | 162161101 | ELECTRA 1101 | L1697 | FALSE | 9283.5435 | 9283.5435 | 5.7698 | 70 | 8.7849e-05 | 1988 | 45.9015 | 2240 | 0.0030208 | 0.21145 | 2349 | 2.74 | 585
8682 | CLARKSVILLE 210951744 | 153612109 | CLARKSVILLE 2109 | 51744 | FALSE | 2867.8226 | 2099.9047 | 1.3051 | 25 | 0.00013923 | 883 | 25.8185 | 2382 | 0.0030149 | 0.075372 | 2350 | 0.2 | 1162
6410 | SILVERADO 2105616 | 43432105 | SILVERADO 2105 | 616 | TRUE | 12968.0682 | 798.8754 | 0.4965 | 103 | 0.00011091 | 1393 | 20.2831 | 2445 | 0.0030112 | 0.31016 | 2351 | 0.3 | 1020
2231 | HICKS 2103LB50 | 83432103 | HICKS 2103 | LB50 | FALSE | 18304.0568 | 18130.2581 | 11.268 | 65 | 0.00012813 | 1046 | 26.2606 | 2373 | 0.0029902 | 0.19436 | 2352 | 0.21 | 1142
1742 | MIWUK 1701CB | 163661701 | MIWUK 1701 | CB | FALSE | 26145.2982 | 26145.2982 | 16.2494 | 187 | 8.1435e-05 | 2170 | 64.1413 | 2128 | 0.0029901 | 0.55914 | 2353 | 197.3 | 2
4916 | SARATOGA 1107167792 | 83371107 | SARATOGA 1107 | 167792 | FALSE | 7540.5809 | 7540.5809 | 4.6865 | 48 | 0.00016417 | 599 | 22.3539 | 2421 | 0.0029842 | 0.14324 | 2354 | 27.41 | 258
55 | CURTIS 170234426 | 163351702 | CURTIS 1702 | 34426 | FALSE | 11062.821 | 7591.2944 | 4.718 | 81 | 0.0001041 | 1549 | 18.642 | 2465 | 0.0029697 | 0.24054 | 2355 | 0.2 | 1161
4236 | LOS GATOS 1106LA64 | 82021106 | LOS GATOS 1106 | LA64 | FALSE | 20425.5788 | 20425.5788 | 12.6946 | 152 | 0.00024137 | 243 | 12.4217 | 2580 | 0.0029684 | 0.4512 | 2356 | 0.94 | 741
6476 | PAUL SWEET 21068091 | 83252106 | PAUL SWEET 2106 | 8091 | FALSE | 9678.478 | 9678.478 | 6.0152 | 69 | 0.00018296 | 489 | 17.2834 | 2497 | 0.0029648 | 0.20457 | 2357 | 0.38 | 961
7197 | BIG BASIN 110212758 | 82841102 | BIG BASIN 1102 | 12758 | FALSE | 9624.9945 | 9624.9945 | 5.982 | 70 | 0.00033735 | 98 | 10.9337 | 2611 | 0.002947 | 0.20629 | 2358 | 6.96 | 456
2069 | BIG BASIN 11025066 | 82841102 | BIG BASIN 1102 | 5066 | FALSE | 22120.764 | 22120.764 | 13.7481 | 121 | 0.00018064 | 508 | 16.1765 | 2514 | 0.0029066 | 0.35169 | 2359 | 0.48 | 902
8715 | OLEMA 1101602 | 42291101 | OLEMA 1101 | 602 | FALSE | 38446.6728 | 26032.3379 | 16.1792 | 115 | 5.7752e-05 | 2842 | 48.2008 | 2220 | 0.0028981 | 0.33328 | 2360 | 0.08 | 1633
5548 | ANTLER 11011384 | 103271101 | ANTLER 1101 | 1384 | FALSE | 14709.9253 | 14709.9253 | 9.1423 | 106 | 0.00030207 | 128 | 17.1106 | 2502 | 0.0028857 | 0.30589 | 2361 | 0.08 | 1664
2497 | ROB ROY 210410714 | 83692104 | ROB ROY 2104 | 10714 | FALSE | 31415.1888 | 22795.5157 | 14.1675 | 212 | 8.9964e-05 | 1915 | 34.8828 | 2308 | 0.002884 | 0.61141 | 2362 | 0.2 | 1158
2343 | OCEANO 1104CB | 182601104 | OCEANO 1104 | CB | FALSE | 17856.3948 | 7352.5883 | 4.5697 | 146 | 2.5847e-05 | 3489 | 57.0849 | 2170 | 0.0028615 | 0.41777 | 2363 | 0.1 | 1489
7790 | SANTA ROSA A 1111147198 | 42151111 | SANTA ROSA A 1111 | 147198 | FALSE | 3096.6231 | 2173.9439 | 1.3511 | 24 | 0.00013298 | 958 | 27.8556 | 2363 | 0.0028527 | 0.068464 | 2364 |  | 3161
5803 | BEN LOMOND 04015206 | 83040401 | BEN LOMOND 0401 | 5206 | FALSE | 11520.3774 | 11520.3774 | 7.16 | 78 | 0.00028525 | 147 | 13.4764 | 2563 | 0.0028387 | 0.22141 | 2365 | 16.08 | 342
6276 | MONTE RIO 1113202 | 42811113 | MONTE RIO 1113 | 202 | FALSE | 8481.1425 | 8481.1425 | 5.2711 | 55 | 0.00023689 | 257 | 9.574 | 2632 | 0.0028293 | 0.15561 | 2366 | 77.47 | 54
6911 | DEL MONTE 21042624 | 182222104 | DEL MONTE 2104 | 2624 | FALSE | 30794.7642 | 29790.8638 | 18.5151 | 148 | 5.858e-05 | 2819 | 45.0109 | 2246 | 0.0028273 | 0.41844 | 2367 | 0.19 | 1182
3771 | CURTIS 170510590 | 163351705 | CURTIS 1705 | 10590 | FALSE | 26358.3376 | 26358.3376 | 16.3818 | 199 | 7.2916e-05 | 2395 | 56.6573 | 2172 | 0.0028226 | 0.56169 | 2368 | 0.28 | 1046
2714 | MIWUK 1702CB | 163661702 | MIWUK 1702 | CB | FALSE | 14569.4696 | 14569.4696 | 9.055 | 110 | 0.00015914 | 650 | 17.5722 | 2489 | 0.0028161 | 0.30977 | 2369 | 97.72 | 22
3825 | SARATOGA 1105LC14 | 83371105 | SARATOGA 1105 | LC14 | FALSE | 17935.8798 | 15879.1839 | 9.869 | 137 | 0.0001215 | 1156 | 25.9229 | 2378 | 0.0028157 | 0.38575 | 2370 | 0.15 | 1303
5150 | HAMILTON BRANCH 11012046 | 102361101 | HAMILTON BRANCH 1101 | 2046 | FALSE | 14788.0543 | 14724.19 | 9.1511 | 57 | 2.9135e-05 | 3438 | 49.5192 | 2213 | 0.0028141 | 0.1604 | 2371 | 3.25 | 552
6397 | BRUNSWICK 110584480 | 152481105 | BRUNSWICK 1105 | 84480 | FALSE | 7615.7819 | 7615.7819 | 4.7332 | 50 | 0.00012015 | 1184 | 18.1285 | 2473 | 0.0028064 | 0.14032 | 2372 | 43.55 | 166
7609 | SAN LUIS OBISPO 1107V58 | 182631107 | SAN LUIS OBISPO 1107 | V58 | FALSE | 3619.1201 | 1838.4445 | 1.1426 | 25 | 3.6836e-05 | 3317 | 42.8997 | 2262 | 0.0027879 | 0.069698 | 2373 | 0.25 | 1081
10167 | HAMILTON BRANCH 11012436 | 102361101 | HAMILTON BRANCH 1101 | 2436 | FALSE | 8535.8961 | 8535.8961 | 5.3051 | 19 | 3.5783e-05 | 3338 | 86.4703 | 2020 | 0.0027598 | 0.052436 | 2374 | 0.06 | 1878
289 | BIG BASIN 110169550 | 82841101 | BIG BASIN 1101 | 69550 | FALSE | 28222.9499 | 28222.9499 | 17.5407 | 188 | 0.00019115 | 436 | 15.1137 | 2529 | 0.0027545 | 0.51784 | 2375 | 0.88 | 753
3662 | SONOMA 1107294 | 42721107 | SONOMA 1107 | 294 | TRUE | 13929.6308 | 0 | 0 | 66 | 3.7559e-05 | 3303 | 12.2945 | 2582 | 0.002743 | 0.18104 | 2376 | 1.46 | 672
6355 | BIG RIVER 11017273 | 43081101 | BIG RIVER 1101 | 7273 | FALSE | 10648.4179 | 10648.4179 | 6.618 | 38 | 0.00010776 | 1456 | 24.4514 | 2395 | 0.0027408 | 0.10415 | 2377 |  | 3023
7672 | POINT ARENA 11012637 | 43381101 | POINT ARENA 1101 | 2637 | FALSE | 6500.6025 | 6500.6025 | 4.0402 | 28 | 7.3634e-05 | 2375 | 33.1621 | 2319 | 0.0027385 | 0.076678 | 2378 | 0.06 | 1783
1790 | CAMP EVERS 210510912 | 83622105 | CAMP EVERS 2105 | 10912 | FALSE | 7824.9032 | 7824.9032 | 4.8632 | 54 | 0.00030255 | 127 | 14.5938 | 2539 | 0.0027343 | 0.14765 | 2379 | 17.3 | 333
10750 | BOGARD 1101CB | 103301101 | BOGARD 1101 | CB | TRUE | 830.5012 | 830.5012 | 0.51616 | 7 | 2.8327e-05 | 3450 | 82.5251 | 2038 | 0.0027213 | 0.019049 | 2380 | 0 | 2645
6610 | GREEN VALLEY 210112824 | 83192101 | GREEN VALLEY 2101 | 12824 | FALSE | 19725.4463 | 1410.0846 | 0.87637 | 97 | 5.8888e-05 | 2811 | 61.7022 | 2142 | 0.0027199 | 0.26383 | 2381 | 0.19 | 1178
6375 | HOLLISTER 21054048 | 182492105 | HOLLISTER 2105 | 4048 | FALSE | 45554.4794 | 29209.8997 | 18.1541 | 157 | 5.5174e-05 | 2907 | 56.2888 | 2174 | 0.0027194 | 0.42694 | 2382 | 0.07 | 1678
317 | PARADISE 11042206 | 102831104 | PARADISE 1104 | 2206 | FALSE | 27876.5924 | 6659.3031 | 4.1388 | 227 | 0.00050121 | 31 | 12.7346 | 2573 | 0.0027 | 0.61291 | 2383 |  | 2664
6305 | WILLOW CREEK 110191926 | 192171101 | WILLOW CREEK 1101 | 91926 | FALSE | 17004.3113 | 10358.7223 | 6.438 | 48 | 0.00024845 | 221 | 9.7992 | 2628 | 0.0026935 | 0.12929 | 2384 | 0.04 | 2095
5185 | SILVERADO 21023010 | 43432102 | SILVERADO 2102 | 3010 | TRUE | 14671.2868 | 569.5009 | 0.35395 | 106 | 8.4289e-05 | 2082 | 23.6594 | 2409 | 0.0026922 | 0.28537 | 2385 | 0.03 | 2262
122 | STANISLAUS 17021888 | 162821702 | STANISLAUS 1702 | 1888 | FALSE | 30440.0056 | 30440.0056 | 18.9186 | 231 | 9.5589e-05 | 1738 | 52.6578 | 2198 | 0.0026855 | 0.62036 | 2386 | 136.25 | 4
7468 | ROB ROY 210410298 | 83692104 | ROB ROY 2104 | 10298 | FALSE | 21540.3253 | 17635.9746 | 10.9608 | 138 | 0.00011425 | 1313 | 23.0219 | 2412 | 0.0026825 | 0.37018 | 2387 | 0.67 | 817
3981 | CAMP EVERS 210510214 | 83622105 | CAMP EVERS 2105 | 10214 | FALSE | 22409.5851 | 22409.5851 | 13.9276 | 149 | 0.00015 | 735 | 18.095 | 2476 | 0.0026769 | 0.39885 | 2388 | 59.12 | 90
4982 | WEST POINT 110136674 | 163201101 | WEST POINT 1101 | 36674 | FALSE | 15144.1466 | 15144.1466 | 9.4121 | 125 | 0.00010056 | 1635 | 28.0218 | 2361 | 0.0026639 | 0.33299 | 2389 | 88.72 | 34
7345 | WILLOW CREEK 110129362 | 192171101 | WILLOW CREEK 1101 | 29362 | FALSE | 18377.6602 | 12371.5145 | 7.6889 | 74 | 0.00019406 | 424 | 17.4096 | 2493 | 0.0026559 | 0.19654 | 2390 | 0.15 | 1302
8996 | FORT ORD 210637286 | 182402106 | FORT ORD 2106 | 37286 | FALSE | 5924.4605 | 4150.8287 | 2.5798 | 25 | 7.3809e-05 | 2365 | 26.9712 | 2368 | 0.0026543 | 0.066357 | 2391 | 0.03 | 2256
8063 | COARSEGOLD 210210207 | 254432102 | COARSEGOLD 2102 | 10207 | FALSE | 5731.5328 | 5731.5328 | 3.5622 | 38 | 5.2727e-05 | 2978 | 53.21 | 2193 | 0.0026426 | 0.10042 | 2392 | 4.55 | 517
4536 | TASSAJARA 2108437582 | 14662108 | TASSAJARA 2108 | 437582 | FALSE | 3785.2974 | 1172.6243 | 0.72879 | 31 | 9.3714e-05 | 1803 | 36.8732 | 2299 | 0.0026389 | 0.081807 | 2393 |  | 2902
1013 | CASTRO VALLEY 1108MR337 | 14091108 | CASTRO VALLEY 1108 | MR337 | FALSE | 30458.1324 | 14629.5479 | 9.0923 | 193 | 2.0736e-05 | 3536 | 31.7021 | 2331 | 0.0026206 | 0.50578 | 2394 |  | 2704
1167 | BIG BASIN 110195690 | 82841101 | BIG BASIN 1101 | 95690 | FALSE | 6226.9882 | 6226.9882 | 3.8701 | 58 | 0.00043813 | 55 | 3.7552 | 2782 | 0.0026164 | 0.15175 | 2395 | 0.66 | 821
7588 | IGNACIO 1104450582 | 42481104 | IGNACIO 1104 | 450582 | FALSE | 6805.9936 | 4807.846 | 2.9881 | 50 | 8.4551e-05 | 2074 | 22.3998 | 2418 | 0.0026097 | 0.13049 | 2396 | 0.06 | 1776
976 | BRUNSWICK 1103CB | 152481103 | BRUNSWICK 1103 | CB | FALSE | 8801.7452 | 2701.0978 | 1.6787 | 82 | 0.00031315 | 115 | 15.1124 | 2530 | 0.0026094 | 0.21397 | 2397 | 0.1 | 1502
3119 | BIG BASIN 1101CB | 82841101 | BIG BASIN 1101 | CB | FALSE | 7486.7827 | 7486.7827 | 4.6531 | 45 | 0.00027461 | 168 | 11.6886 | 2594 | 0.0025849 | 0.11632 | 2398 | 26.9 | 264
8530 | MORRO BAY 1102CB | 183011102 | MORRO BAY 1102 | CB | FALSE | 8911.8997 | 7279.8498 | 4.5245 | 36 | 3.3044e-05 | 3385 | 43.2592 | 2258 | 0.0025799 | 0.092875 | 2399 | 0.04 | 2119
1372 | TASSAJARA 2112CB | 14662112 | TASSAJARA 2112 | CB | TRUE | 2118.6497 | 279.4297 | 0.17367 | 22 | 6.8306e-05 | 2527 | 21.6949 | 2429 | 0.0025794 | 0.056746 | 2400 | 0.44 | 921
1496 | BRUNSWICK 1103173934 | 152481103 | BRUNSWICK 1103 | 173934 | FALSE | 17611.7153 | 17611.7153 | 10.9458 | 125 | 0.00011937 | 1199 | 28.2053 | 2358 | 0.0025705 | 0.32131 | 2401 |  | 2727
1818 | MORRO BAY 1101V66 | 183011101 | MORRO BAY 1101 | V66 | FALSE | 26099.4541 | 5840.07 | 3.6296 | 151 | 5.4939e-05 | 2915 | 48.8236 | 2216 | 0.0025703 | 0.38811 | 2402 | 0.03 | 2264
3089 | CAMBRIA 1101CB | 182771101 | CAMBRIA 1101 | CB | TRUE | 9964.9315 | 415.9182 | 0.25849 | 45 | 5.4044e-05 | 2942 | 29.9475 | 2345 | 0.0025606 | 0.11523 | 2403 | 0.02 | 2456
3722 | BRUNSWICK 11032784 | 152481103 | BRUNSWICK 1103 | 2784 | FALSE | 24673.5503 | 23592.2379 | 14.6627 | 202 | 0.0002125 | 349 | 16.1455 | 2515 | 0.0025529 | 0.51568 | 2404 | 21.1 | 301
3654 | PENNGROVE 1101247511 | 43471101 | PENNGROVE 1101 | 247511 | FALSE | 3219.7109 | 1938.4111 | 1.2047 | 26 | 5.8722e-05 | 2816 | 39.41 | 2279 | 0.0025357 | 0.065929 | 2405 |  | 2844
2397 | MILPITAS 1109XR374 | 82831109 | MILPITAS 1109 | XR374 | TRUE | 4853.8508 | 763.9032 | 0.47477 | 29 | 5.5868e-05 | 2893 | 52.1032 | 2201 | 0.002531 | 0.073398 | 2406 | 0.04 | 2155
1430 | ANTLER 11011520 | 103271101 | ANTLER 1101 | 1520 | FALSE | 14435.9237 | 14435.9237 | 8.972 | 69 | 0.0002442 | 234 | 18.3262 | 2471 | 0.002519 | 0.17381 | 2407 | 0.04 | 2139
9020 | EAST QUINCY 1101424048 | 102551101 | EAST QUINCY 1101 | 424048 | FALSE | 1501.8611 | 1068.5882 | 0.66413 | 12 | 6.0749e-05 | 2756 | 33.0472 | 2323 | 0.002517 | 0.030204 | 2408 |  | 3298
5728 | HALF MOON BAY 1101CB | 24101101 | HALF MOON BAY 1101 | CB | FALSE | 10068.8846 | 2571.5148 | 1.5982 | 80 | 4.1301e-05 | 3240 | 78.3943 | 2057 | 0.0025158 | 0.20127 | 2409 | 0.42 | 929
2399 | MONTE RIO 1113477 | 42811113 | MONTE RIO 1113 | 477 | FALSE | 2946.6356 | 2946.6356 | 1.8313 | 25 | 0.00015508 | 692 | 16.2294 | 2513 | 0.002515 | 0.062875 | 2410 | 3.59 | 539
5291 | MIWUK 1702823548 | 163661702 | MIWUK 1702 | 823548 | FALSE | 31748.5399 | 31748.5399 | 19.7318 | 231 | 6.0776e-05 | 2755 | 41.9518 | 2266 | 0.0025098 | 0.57976 | 2411 |  | 2944
2843 | PLACERVILLE 111219742 | 153081112 | PLACERVILLE 1112 | 19742 | FALSE | 12071.9353 | 10549.7356 | 6.5567 | 92 | 0.00023207 | 278 | 8.0743 | 2669 | 0.0025093 | 0.23086 | 2412 | 0.09 | 1571
7112 | BELLEVUE 2103646 | 43182103 | BELLEVUE 2103 | 646 | FALSE | 19795.1478 | 13544.3225 | 8.4179 | 154 | 0.00011949 | 1196 | 18.0896 | 2477 | 0.0025033 | 0.3855 | 2413 | 28.71 | 246
637 | DUNBAR 1101160 | 43071101 | DUNBAR 1101 | 160 | FALSE | 10761.0163 | 4469.2889 | 2.7777 | 77 | 9.2493e-05 | 1831 | 17.9801 | 2481 | 0.0024952 | 0.19213 | 2414 | 0.04 | 2105
551 | MC KEE 1103XR028 | 83531103 | MC KEE 1103 | XR028 | FALSE | 16732.9664 | 1226.5796 | 0.76232 | 134 | 6.205e-05 | 2717 | 31.865 | 2330 | 0.0024946 | 0.33428 | 2415 | 0.03 | 2231
4532 | RESERVATION ROAD 1102CB | 182731102 | RESERVATION ROAD 1102 | CB | FALSE | 27553.0792 | 12591.5795 | 7.8257 | 180 | 4.197e-05 | 3225 | 36.6519 | 2300 | 0.0024688 | 0.44438 | 2416 | 0.03 | 2341
2736 | ROSSMOOR 110845268 | 14161108 | ROSSMOOR 1108 | 45268 | FALSE | 12405.1563 | 4400.5557 | 2.735 | 112 | 8.3437e-05 | 2119 | 27.4918 | 2366 | 0.0024458 | 0.27393 | 2417 | 0.06 | 1780
4245 | SONOMA 1104914376 | 42721104 | SONOMA 1104 | 914376 | TRUE | 11215.1853 | 862.0577 | 0.53577 | 93 | 8.1801e-05 | 2159 | 28.2406 | 2357 | 0.0024267 | 0.22569 | 2418 | 0.04 | 2227
9993 | STELLING 1109478699 | 83481109 | STELLING 1109 | 478699 | FALSE | 1763.8687 | 1328.3865 | 0.8256 | 14 | 8.2786e-05 | 2136 | 37.3598 | 2294 | 0.0024262 | 0.033967 | 2419 |  | 3466
1421 | ORO FINO 11012022 | 103031101 | ORO FINO 1101 | 2022 | FALSE | 25888.9554 | 25888.9554 | 16.0901 | 207 | 0.0001628 | 614 | 14.0752 | 2547 | 0.0024209 | 0.50113 | 2420 | 126.01 | 10
4226 | RIO DELL 1102772210 | 192251102 | RIO DELL 1102 | 772210 | FALSE | 5622.5297 | 1329.7793 | 0.82646 | 32 | 0.0003009 | 129 | 8.4673 | 2658 | 0.0023979 | 0.076733 | 2421 |  | 2876
3489 | WEIMAR 1101CB | 152491101 | WEIMAR 1101 | CB | FALSE | 14897.5939 | 14897.5939 | 9.2589 | 116 | 0.00026838 | 176 | 10.7214 | 2615 | 0.0023893 | 0.27716 | 2422 | 0.08 | 1670
9667 | NORTH TOWER 2101CB | 42042101 | NORTH TOWER 2101 | CB | FALSE | 7077.2532 | 2179.3543 | 1.3545 | 22 | 7.8614e-05 | 2246 | 23.8165 | 2407 | 0.0023847 | 0.052462 | 2423 | 0.16 | 1259
8228 | GONZALES 1104415382 | 182131104 | GONZALES 1104 | 415382 | TRUE | 1920.3588 | 97.0433 | 0.060313 | 8 | 1.7728e-05 | 3562 | 59.385 | 2159 | 0.0023723 | 0.018978 | 2424 |  | 3205
4259 | DIAMOND SPRINGS 110676088 | 152261106 | DIAMOND SPRINGS 1106 | 76088 | FALSE | 17715.9929 | 17715.9929 | 11.0106 | 124 | 8.4526e-05 | 2076 | 27.0945 | 2367 | 0.0023715 | 0.29407 | 2425 | 0.08 | 1589
9364 | MIWUK 170236888 | 163661702 | MIWUK 1702 | 36888 | TRUE | 977.9121 | 977.9121 | 0.60778 | 7 | 0.00011804 | 1228 | 17.0465 | 2504 | 0.0023702 | 0.016592 | 2426 | 28.15 | 253
5480 | PUEBLO 2102647842 | 43292102 | PUEBLO 2102 | 647842 | TRUE | 1016.9284 | 187.7325 | 0.11668 | 6 | 4.4258e-05 | 3184 | 47.9751 | 2222 | 0.0023697 | 0.014218 | 2427 |  | 2958
1607 | MONTE RIO 11133970 | 42811113 | MONTE RIO 1113 | 3970 | FALSE | 11750.7224 | 11750.7224 | 7.3031 | 87 | 0.00015476 | 697 | 11.2679 | 2601 | 0.0023638 | 0.20565 | 2428 | 0.85 | 765
4343 | BOLINAS 11011236 | 42261101 | BOLINAS 1101 | 1236 | FALSE | 6557.8129 | 5809.1133 | 3.6104 | 34 | 0.00011532 | 1292 | 31.2219 | 2338 | 0.0023633 | 0.080354 | 2429 | 0.06 | 1825
4341 | PLACERVILLE 210623190 | 153082106 | PLACERVILLE 2106 | 23190 | FALSE | 5918.813 | 5918.813 | 3.6786 | 45 | 0.00031007 | 118 | 11.1572 | 2604 | 0.0023536 | 0.10591 | 2430 | 0.09 | 1566
6831 | INDIAN FLAT 110410270 | 252691104 | INDIAN FLAT 1104 | 10270 | FALSE | 6119.8962 | 6119.8962 | 3.8035 | 39 | 3.2245e-05 | 3398 | 67.2012 | 2107 | 0.002349 | 0.091612 | 2431 | 0.07 | 1697
10358 | KONOCTI 11024421 | 43311102 | KONOCTI 1102 | 4421 | TRUE | 585.3593 | 585.3593 | 0.3638 | 5 | 8.4837e-05 | 2068 | 28.5837 | 2354 | 0.0023217 | 0.011609 | 2432 | 18.46 | 321
822 | PERRY 1101V74 | 183071101 | PERRY 1101 | V74 | FALSE | 8209.0598 | 6901.1378 | 4.2891 | 61 | 4.7405e-05 | 3107 | 40.6895 | 2274 | 0.0023119 | 0.14103 | 2433 | 0.09 | 1509
1876 | HATTON 1102CB | 182291102 | HATTON 1102 | CB | FALSE | 7725.5743 | 3167.0883 | 1.9684 | 66 | 5.6002e-05 | 2888 | 47.8787 | 2223 | 0.0022934 | 0.15136 | 2434 | 0.04 | 2137
5363 | BIG BASIN 110110720 | 82841101 | BIG BASIN 1101 | 10720 | FALSE | 7578.3102 | 7578.3102 | 4.71 | 44 | 0.00059263 | 19 | 5.4692 | 2730 | 0.002283 | 0.10045 | 2435 | 61.7 | 86
3635 | PERRY 1101V88 | 183071101 | PERRY 1101 | V88 | FALSE | 5002.7309 | 1732.6065 | 1.0768 | 48 | 3.4227e-05 | 3365 | 36.539 | 2301 | 0.002278 | 0.10934 | 2436 | 0.6 | 853
4348 | SANTA ROSA A 110432180 | 42151104 | SANTA ROSA A 1104 | 32180 | FALSE | 4085.725 | 3970.2131 | 2.4675 | 36 | 0.0001328 | 963 | 9.9964 | 2624 | 0.0022763 | 0.081948 | 2437 | 0.25 | 1076
9525 | BIG BASIN 11028403 | 82841102 | BIG BASIN 1102 | 8403 | FALSE | 7867.7292 | 7867.7292 | 4.8898 | 42 | 0.00015778 | 666 | 14.7825 | 2533 | 0.0022738 | 0.095499 | 2438 | 0.41 | 941
7227 | SAN RAFAEL 11071415 | 42011107 | SAN RAFAEL 1107 | 1415 | FALSE | 1913.2696 | 1280.0188 | 0.79554 | 14 | 0.00015384 | 711 | 13.6482 | 2558 | 0.0022706 | 0.031789 | 2439 | 2.72 | 587
649 | ORO FINO 11022090 | 103031102 | ORO FINO 1102 | 2090 | FALSE | 23726.1931 | 23726.1931 | 14.7459 | 183 | 0.00011006 | 1410 | 20.7182 | 2438 | 0.0022675 | 0.41496 | 2440 | 71.03 | 68
2752 | FULTON 1107CB | 42561107 | FULTON 1107 | CB | TRUE | 19915.785 | 875.3178 | 0.54401 | 166 | 8.6265e-05 | 2028 | 19.7079 | 2452 | 0.0022645 | 0.37591 | 2441 | 3.46 | 545
8081 | CAMP EVERS 210612840 | 83622106 | CAMP EVERS 2106 | 12840 | FALSE | 6323.0478 | 6323.0478 | 3.9298 | 50 | 0.00014417 | 811 | 15.7468 | 2520 | 0.002258 | 0.1129 | 2442 | 0.4 | 948
365 | PURISIMA 110149394 | 182971101 | PURISIMA 1101 | 49394 | FALSE | 14105.1915 | 1836.8422 | 1.1416 | 111 | 2.0592e-05 | 3538 | 59.3555 | 2160 | 0.0022509 | 0.24985 | 2443 | 0.03 | 2277
707 | DEL MONTE 21042760 | 182222104 | DEL MONTE 2104 | 2760 | FALSE | 4358.9956 | 4358.9956 | 2.7091 | 28 | 8.7661e-05 | 1995 | 28.0773 | 2360 | 0.0022393 | 0.062701 | 2444 | 0.65 | 826
7540 | LUCERNE 11062327 | 43351106 | LUCERNE 1106 | 2327 | FALSE | 2038.9698 | 1914.889 | 1.1901 | 20 | 0.00013326 | 953 | 15.5189 | 2523 | 0.0022381 | 0.044762 | 2445 | 0.08 | 1640
9432 | GUALALA 1111445166 | 42841111 | GUALALA 1111 | 445166 | FALSE | 15269.7955 | 12164.2635 | 7.5601 | 71 | 5.9661e-05 | 2785 | 28.1893 | 2359 | 0.0022354 | 0.15871 | 2446 | 0.06 | 1845
2414 | PINE GROVE 110245292 | 163751102 | PINE GROVE 1102 | 45292 | FALSE | 17350.6047 | 17350.6047 | 10.7835 | 132 | 8.1993e-05 | 2156 | 36.0802 | 2304 | 0.002235 | 0.29501 | 2447 | 129.86 | 5
7039 | IGNACIO 1101CB | 42481101 | IGNACIO 1101 | CB | FALSE | 2942.811 | 2690.5619 | 1.6722 | 19 | 0.00013353 | 951 | 20.0821 | 2447 | 0.0022279 | 0.042331 | 2448 | 0.05 | 2033
6713 | LAURELES 1112438 | 182371112 | LAURELES 1112 | 438 | FALSE | 9219.1151 | 8226.4088 | 5.1127 | 48 | 7.125e-05 | 2440 | 29.805 | 2347 | 0.0022241 | 0.10675 | 2449 | 0.05 | 2035
1808 | HARTLEY 1101738 | 43211101 | HARTLEY 1101 | 738 | FALSE | 12990.1187 | 4208.5049 | 2.6156 | 106 | 7.6101e-05 | 2304 | 26.5188 | 2371 | 0.0022159 | 0.23488 | 2450 | 0.03 | 2251
9055 | ORO FINO 1102CB | 103031102 | ORO FINO 1102 | CB | FALSE | 3376.1921 | 3376.1921 | 2.0983 | 27 | 0.00018738 | 459 | 22.0757 | 2425 | 0.0021922 | 0.059189 | 2451 | 44.75 | 154
500 | ALTO 112278672 | 42031122 | ALTO 1122 | 78672 | FALSE | 14393.4787 | 6078.7898 | 3.778 | 123 | 7.9821e-05 | 2211 | 9.5346 | 2635 | 0.0021883 | 0.26916 | 2452 | 0.15 | 1304
9919 | MONTE RIO 1113678 | 42811113 | MONTE RIO 1113 | 678 | FALSE | 3004.004 | 3004.004 | 1.867 | 17 | 0.00013325 | 954 | 26.6461 | 2369 | 0.002188 | 0.037196 | 2453 | 48.48 | 128
8710 | SUMMIT 110186658 | 152591101 | SUMMIT 1101 | 86658 | FALSE | 1081.812 | 1029.0279 | 0.63954 | 7 | 0.00024387 | 235 | 13.6494 | 2557 | 0.0021861 | 0.015303 | 2454 | 0.02 | 2563
3183 | PINE GROVE 11011021 | 163751101 | PINE GROVE 1101 | 1021 | FALSE | 6702.9103 | 6702.9103 | 4.1659 | 56 | 6.9851e-05 | 2478 | 34.4442 | 2311 | 0.0021716 | 0.12161 | 2455 | 8.36 | 430
3039 | BIG BASIN 110110296 | 82841101 | BIG BASIN 1101 | 10296 | FALSE | 23203.5804 | 23203.5804 | 14.4211 | 181 | 0.00028227 | 151 | 8.472 | 2657 | 0.0021702 | 0.3928 | 2456 | 20.94 | 303
10621 | EEL RIVER 1103987714 | 192381103 | EEL RIVER 1103 | 987714 | FALSE | 1590.9598 | 1218.9668 | 0.75759 | 6 | 0.00013453 | 933 | 18.5736 | 2466 | 0.0021699 | 0.01302 | 2457 |  | 3580
2552 | HALSEY 11022514 | 152241102 | HALSEY 1102 | 2514 | FALSE | 31420.4965 | 17648.4979 | 10.9686 | 212 | 0.00019439 | 421 | 17.5789 | 2488 | 0.0021687 | 0.45975 | 2458 | 0.04 | 2164
1900 | PLACERVILLE 1111508410 | 153081111 | PLACERVILLE 1111 | 508410 | FALSE | 8406.5825 | 7530.8771 | 4.6805 | 73 | 0.0002728 | 169 | 8.8564 | 2647 | 0.002162 | 0.15783 | 2459 |  | 2754
7805 | POINT MORETTI 11015074 | 82931101 | POINT MORETTI 1101 | 5074 | FALSE | 4940.828 | 2196.7079 | 1.3653 | 34 | 7.8643e-05 | 2245 | 54.9615 | 2181 | 0.0021548 | 0.073264 | 2460 | 0.03 | 2294
9738 | ECHO SUMMIT 1101344250 | 158031101 | ECHO SUMMIT 1101 | 344250 | FALSE | 1668.1837 | 1299.2708 | 0.8075 | 10 | 4.8899e-05 | 3068 | 38.0392 | 2290 | 0.0021484 | 0.021484 | 2461 | 0.03 | 2252
3248 | HARRIS 1109355914 | 192431109 | HARRIS 1109 | 355914 | FALSE | 14935.3832 | 13002.7807 | 8.0813 | 104 | 0.0002048 | 382 | 13.3148 | 2566 | 0.0021471 | 0.2233 | 2462 |  | 2817
5158 | MORRO BAY 1101W20 | 183011101 | MORRO BAY 1101 | W20 | FALSE | 6313.3606 | 3551.7376 | 2.2074 | 48 | 4.0736e-05 | 3252 | 28.7718 | 2351 | 0.0021357 | 0.10251 | 2463 | 0.02 | 2548
5206 | CAMP EVERS 21065020 | 83622106 | CAMP EVERS 2106 | 5020 | FALSE | 24253.1314 | 24253.1314 | 15.0734 | 185 | 0.00021261 | 348 | 14.5867 | 2540 | 0.0021265 | 0.3934 | 2464 | 82.74 | 42
8641 | PETALUMA C 1109857148 | 42631109 | PETALUMA C 1109 | 857148 | FALSE | 3180.8041 | 1503.7135 | 0.93456 | 31 | 4.5954e-05 | 3140 | 22.3402 | 2422 | 0.0021126 | 0.065491 | 2465 |  | 3247
4750 | PENNGROVE 1101554 | 43471101 | PENNGROVE 1101 | 554 | TRUE | 17322.4157 | 0 | 0 | 130 | 6.9536e-05 | 2487 | 22.3741 | 2419 | 0.0021107 | 0.2744 | 2466 | 0.33 | 985
5805 | PARADISE 110439216 | 102831104 | PARADISE 1104 | 39216 | FALSE | 5158.2623 | 2624.8047 | 1.6313 | 41 | 0.00049128 | 32 | 7.6005 | 2675 | 0.0021 | 0.086098 | 2467 | 0.31 | 998
3222 | WEST POINT 11014706 | 163201101 | WEST POINT 1101 | 4706 | FALSE | 18429.634 | 18429.634 | 11.4541 | 138 | 8.047e-05 | 2193 | 25.0428 | 2390 | 0.0020959 | 0.28923 | 2468 | 94.56 | 27
2065 | EL DORADO PH 21026645 | 152762102 | EL DORADO PH 2102 | 6645 | FALSE | 6787.3604 | 6787.3604 | 4.2184 | 52 | 9.5316e-05 | 1753 | 25.6675 | 2386 | 0.0020868 | 0.10851 | 2469 | 54.01 | 109
6903 | VINEYARD 2107MR332 | 14502107 | VINEYARD 2107 | MR332 | TRUE | 4548.7457 | 520.6629 | 0.32359 | 31 | 7.6303e-05 | 2299 | 24.407 | 2396 | 0.0020705 | 0.064186 | 2470 | 0.38 | 963
3802 | MORRO BAY 1102868170 | 183011102 | MORRO BAY 1102 | 868170 | FALSE | 15451.7071 | 14595.2194 | 9.071 | 59 | 3.81e-05 | 3298 | 52.9097 | 2197 | 0.0020479 | 0.12083 | 2471 |  | 2853
3290 | TAR FLAT 04023144 | 163240402 | TAR FLAT 0402 | 3144 | FALSE | 8269.2517 | 7828.9119 | 4.8657 | 58 | 0.00015369 | 715 | 19.1385 | 2460 | 0.0020462 | 0.11868 | 2472 | 0.09 | 1549
9541 | RINCON 1101839669 | 43321101 | RINCON 1101 | 839669 | TRUE | 1273.7836 | 989.219 | 0.6148 | 12 | 0.00010611 | 1492 | 23.2008 | 2411 | 0.0020383 | 0.02446 | 2473 |  | 3373
671 | CAMP EVERS 21045096 | 83622104 | CAMP EVERS 2104 | 5096 | FALSE | 32680.7032 | 32680.7032 | 20.3112 | 232 | 0.00019642 | 411 | 13.592 | 2561 | 0.0020379 | 0.4728 | 2474 | 12.58 | 372
6416 | PLACER 1102CB | 152461102 | PLACER 1102 | CB | FALSE | 3445.1403 | 3361.7302 | 2.0893 | 23 | 0.00019412 | 423 | 17.2869 | 2496 | 0.0020369 | 0.046849 | 2475 | 0.54 | 878
9674 | GUALALA 1112CB | 42841112 | GUALALA 1112 | CB | FALSE | 3448.2579 | 2568.9228 | 1.5966 | 22 | 5.2908e-05 | 2970 | 18.4256 | 2469 | 0.0020177 | 0.044389 | 2476 | 0.05 | 1991
1510 | MONTE RIO 1113CB | 42811113 | MONTE RIO 1113 | CB | FALSE | 7286.2366 | 7286.2366 | 4.5284 | 49 | 0.00021269 | 347 | 6.3725 | 2702 | 0.0020136 | 0.098667 | 2477 | 46.29 | 143
1572 | ECHO SUMMIT 11012500 | 158031101 | ECHO SUMMIT 1101 | 2500 | FALSE | 3521.417 | 3521.417 | 2.1886 | 26 | 4.8353e-05 | 3083 | 44.8707 | 2248 | 0.0019811 | 0.05151 | 2478 | 0.16 | 1255
808 | PEORIA 1701169700 | 163781701 | PEORIA 1701 | 169700 | FALSE | 13421.5222 | 13421.5222 | 8.3415 | 63 | 7.4011e-05 | 2357 | 25.346 | 2387 | 0.001973 | 0.1243 | 2479 |  | 2693
1792 | MORAGA 1102CB | 13801102 | MORAGA 1102 | CB | FALSE | 14982.4076 | 8539.83 | 5.3075 | 130 | 9.0885e-05 | 1886 | 25.7754 | 2384 | 0.0019722 | 0.25639 | 2480 | 0.62 | 843
6608 | FORT ROSS 1121134 | 42851121 | FORT ROSS 1121 | 134 | FALSE | 13416.4816 | 13272.5409 | 8.2489 | 99 | 9.5754e-05 | 1735 | 24.5453 | 2393 | 0.0019671 | 0.19475 | 2481 | 0.04 | 2145
5795 | HIGGINS 1103995672 | 152691103 | HIGGINS 1103 | 995672 | FALSE | 9263.8953 | 5928.6387 | 3.6847 | 79 | 0.00018258 | 492 | 13.4013 | 2564 | 0.0019604 | 0.15487 | 2482 | 0.08 | 1645
7320 | FAIRVIEW 220799096 | 13432207 | FAIRVIEW 2207 | 99096 | FALSE | 15944.165 | 15895.8244 | 9.8793 | 56 | 9.384e-05 | 1796 | 20.9972 | 2437 | 0.0019603 | 0.10978 | 2483 | 0.05 | 2008
1460 | PARADISE 1105121988 | 102831105 | PARADISE 1105 | 121988 | FALSE | 11219.1712 | 11219.1712 | 6.9728 | 92 | 0.00027094 | 171 | 5.2336 | 2742 | 0.0019488 | 0.17929 | 2484 |  | 2725
223 | ROB ROY 210410960 | 83692104 | ROB ROY 2104 | 10960 | FALSE | 45089.9597 | 30132.5387 | 18.7275 | 320 | 9.2109e-05 | 1838 | 18.2529 | 2472 | 0.0019454 | 0.62252 | 2485 | 0.12 | 1381
9882 | VOLTA 1102453266 | 102541102 | VOLTA 1102 | 453266 | TRUE | 510.1509 | 510.1509 | 0.31706 | 5 | 4.863e-05 | 3071 | 42.8367 | 2263 | 0.0019312 | 0.0096562 | 2486 |  | 3444
2825 | COTATI 1104CB | 42271104 | COTATI 1104 | CB | FALSE | 12268.6539 | 7279.3949 | 4.5242 | 93 | 7.194e-05 | 2421 | 13.0319 | 2569 | 0.0019107 | 0.17769 | 2487 | 1.2 | 702
9868 | VOLTA 110293418 | 102541102 | VOLTA 1102 | 93418 | FALSE | 4145.9232 | 4145.9232 | 2.5767 | 23 | 6.4515e-05 | 2627 | 45.5233 | 2243 | 0.0019038 | 0.043787 | 2488 | 0.16 | 1254
7915 | LOS GATOS 1106697500 | 82021106 | LOS GATOS 1106 | 697500 | FALSE | 10836.6474 | 10836.6474 | 6.735 | 74 | 0.00017368 | 536 | 8.0975 | 2667 | 0.0019029 | 0.14082 | 2489 |  | 3178
9296 | DUNBAR 1103835658 | 43071103 | DUNBAR 1103 | 835658 | TRUE | 1187.2489 | 50.0391 | 0.0311 | 11 | 7.6553e-05 | 2292 | 17.3633 | 2494 | 0.0018987 | 0.020885 | 2490 |  | 3337
6742 | ALTO 11251158 | 42031125 | ALTO 1125 | 1158 | FALSE | 8353.2531 | 3588.3989 | 2.2302 | 65 | 5.6863e-05 | 2865 | 5.9152 | 2715 | 0.0018981 | 0.12337 | 2491 | 0.17 | 1241
4000 | RINCON 1101576 | 43321101 | RINCON 1101 | 576 | FALSE | 13079.4255 | 1582.5592 | 0.98357 | 116 | 0.00012308 | 1132 | 17.5488 | 2490 | 0.0018636 | 0.21618 | 2492 | 0.15 | 1287
4995 | SOLEDAD 21027008 | 182052102 | SOLEDAD 2102 | 7008 | FALSE | 29112.5788 | 8088.7008 | 5.0272 | 122 | 2.175e-05 | 3523 | 36.2639 | 2302 | 0.0018473 | 0.22537 | 2493 | 0.03 | 2381
6887 | HATTON 1102648928 | 182291102 | HATTON 1102 | 648928 | FALSE | 7727.8743 | 6359.2353 | 3.9523 | 44 | 6.1331e-05 | 2741 | 57.7042 | 2168 | 0.0018437 | 0.081123 | 2494 | 0.04 | 2170
9513 | GREEN VALLEY 2101535998 | 83192101 | GREEN VALLEY 2101 | 535998 | FALSE | 7941.4498 | 7140.4635 | 4.4378 | 43 | 0.00012357 | 1129 | 19.4088 | 2455 | 0.0018414 | 0.079178 | 2495 |  | 3367
2632 | APPLE HILL 110412947 | 153661104 | APPLE HILL 1104 | 12947 | FALSE | 5709.2465 | 5709.2465 | 3.5483 | 49 | 0.00010562 | 1503 | 18.015 | 2480 | 0.0018388 | 0.0901 | 2496 | 10.69 | 395
7783 | MIRABEL 110257840 | 42091102 | MIRABEL 1102 | 57840 | FALSE | 4238.9331 | 4238.9331 | 2.6345 | 29 | 0.00029837 | 131 | 7.443 | 2678 | 0.0018331 | 0.053161 | 2497 | 0.36 | 971
26 | TASSAJARA 2103CB | 14662103 | TASSAJARA 2103 | CB | TRUE | 28346.0077 | 787.8623 | 0.48966 | 259 | 8.1627e-05 | 2165 | 14.0393 | 2549 | 0.0018283 | 0.47354 | 2498 | 0.05 | 1935
8978 | BIG RIVER 1101954 | 43081101 | BIG RIVER 1101 | 954 | FALSE | 13095.0592 | 12372.699 | 7.6897 | 78 | 9.4465e-05 | 1782 | 22.5908 | 2415 | 0.0018244 | 0.1423 | 2499 | 0.05 | 1972
85 | HALSEY 11011704 | 152241101 | HALSEY 1101 | 1704 | FALSE | 21239.3917 | 21231.8185 | 13.1957 | 160 | 0.00012962 | 1014 | 19.3786 | 2457 | 0.001823 | 0.29168 | 2500 | 0.18 | 1207
2388 | CAMP EVERS 21059031 | 83622105 | CAMP EVERS 2105 | 9031 | FALSE | 1741.4201 | 1741.4201 | 1.0823 | 17 | 0.00019853 | 401 | 5.6599 | 2722 | 0.0018195 | 0.030932 | 2501 | 26.99 | 262
2038 | MORAGA 1104CB | 13801104 | MORAGA 1104 | CB | FALSE | 25157.6923 | 15741.0344 | 9.7831 | 214 | 7.9295e-05 | 2226 | 25.8956 | 2379 | 0.0018118 | 0.38772 | 2502 | 0.19 | 1192
6140 | OCEANO 1106V28 | 182601106 | OCEANO 1106 | V28 | FALSE | 14462.1376 | 1958.2873 | 1.2171 | 99 | 2.0931e-05 | 3535 | 31.9058 | 2328 | 0.0018053 | 0.17873 | 2503 | 0.03 | 2284
9346 | LAURELES 11116421 | 182371111 | LAURELES 1111 | 6421 | FALSE | 2777.3682 | 2777.3682 | 1.7261 | 20 | 5.7665e-05 | 2846 | 26.2004 | 2374 | 0.0018044 | 0.036089 | 2504 | 0.14 | 1307
680 | CAMP EVERS 210612760 | 83622106 | CAMP EVERS 2106 | 12760 | FALSE | 42462.3954 | 42462.3954 | 26.3906 | 299 | 0.00019594 | 413 | 10.5604 | 2618 | 0.0017903 | 0.53531 | 2505 | 1.92 | 630
1725 | BOLINAS 1101CB | 42261101 | BOLINAS 1101 | CB | FALSE | 3500.023 | 3442.3441 | 2.1394 | 26 | 0.00012024 | 1181 | 17.4311 | 2492 | 0.0017811 | 0.04631 | 2506 | 0.23 | 1119
1486 | BEN LOMOND 1101BL 1101 | 83041101 | BEN LOMOND 1101 | BL 1101 | FALSE | 13568.3761 | 13568.3761 | 8.4328 | 101 | 0.00030613 | 124 | 6.186 | 2709 | 0.0017681 | 0.17858 | 2507 | 25.42 | 271
8439 | OAKHURST 110310190 | 254421103 | OAKHURST 1103 | 10190 | FALSE | 13591.0884 | 13591.0884 | 8.4469 | 61 | 6.3642e-05 | 2659 | 28.5039 | 2355 | 0.0017583 | 0.10725 | 2508 | 52.84 | 111
10411 | BURNEY 1102272636 | 103311102 | BURNEY 1102 | 272636 | TRUE | 431.3681 | 431.3681 | 0.2681 | 5 | 2.8514e-05 | 3445 | 33.4034 | 2316 | 0.0017542 | 0.0087708 | 2509 |  | 3545
9794 | SONOMA 1106510055 | 42721106 | SONOMA 1106 | 510055 | TRUE | 1976.5067 | 817.6203 | 0.50815 | 11 | 5.9313e-05 | 2794 | 33.1507 | 2320 | 0.0017489 | 0.019238 | 2510 |  | 3426
1870 | TEMPLETON 2110307832 | 183052110 | TEMPLETON 2110 | 307832 | FALSE | 22986.441 | 2614.1136 | 1.6247 | 133 | 5.4142e-05 | 2940 | 52.2996 | 2199 | 0.0017438 | 0.23192 | 2511 |  | 2750
4149 | EL DORADO PH 210219542 | 152762102 | EL DORADO PH 2102 | 19542 | FALSE | 15319.5774 | 15319.5774 | 9.5212 | 111 | 0.00024603 | 231 | 13.9871 | 2550 | 0.0017374 | 0.19285 | 2512 | 87.42 | 37
5394 | BRUNSWICK 11052100 | 152481105 | BRUNSWICK 1105 | 2100 | FALSE | 6391.6672 | 6391.6672 | 3.9724 | 47 | 0.00013966 | 875 | 17.2588 | 2498 | 0.0017366 | 0.081621 | 2513 | 19.6 | 310
7138 | MONTE RIO 11138299 | 42811113 | MONTE RIO 1113 | 8299 | FALSE | 1934.2169 | 1934.2169 | 1.2021 | 13 | 0.0001379 | 895 | 14.6935 | 2537 | 0.0017192 | 0.02235 | 2514 | 62.52 | 83
2315 | MORAGA 1101108540 | 13801101 | MORAGA 1101 | 108540 | FALSE | 7751.409 | 7751.409 | 4.8175 | 44 | 0.00010534 | 1511 | 10.8681 | 2613 | 0.001717 | 0.075547 | 2515 | 25 | 274
110 | RACETRACK 17038120 | 163761703 | RACETRACK 1703 | 8120 | FALSE | 14371.6326 | 14371.6326 | 8.932 | 108 | 0.00014141 | 847 | 24.2646 | 2397 | 0.0017068 | 0.18434 | 2516 | 0.12 | 1384
1996 | MORAGA 1103E510R | 13801103 | MORAGA 1103 | E510R | TRUE | 9824.475 | 807.8365 | 0.50207 | 84 | 6.4371e-05 | 2631 | 25.303 | 2388 | 0.0017029 | 0.14305 | 2517 | 0.06 | 1864
2784 | FRENCH GULCH 11022902 | 103381102 | FRENCH GULCH 1102 | 2902 | FALSE | 11242.8228 | 11242.8228 | 6.9875 | 8 | 0.00012146 | 1158 | 50.5933 | 2209 | 0.0016954 | 0.013563 | 2518 | 0.04 | 2100
4648 | HALF MOON BAY 1102863822 | 24101102 | HALF MOON BAY 1102 | 863822 | TRUE | 1030.95 | 168.7519 | 0.10488 | 8 | 3.6716e-05 | 3321 | 27.8163 | 2364 | 0.0016933 | 0.013546 | 2519 |  | 2906
4537 | LAKEWOOD 2107396264 | 13532107 | LAKEWOOD 2107 | 396264 | FALSE | 10259.9636 | 7704.2 | 4.7882 | 95 | 0.00010348 | 1560 | 21.8184 | 2427 | 0.0016927 | 0.16081 | 2520 |  | 2903
6727 | BRUNSWICK 11032200 | 152481103 | BRUNSWICK 1103 | 2200 | FALSE | 8965.9106 | 8965.9106 | 5.5723 | 64 | 0.00010183 | 1607 | 17.8909 | 2484 | 0.0016888 | 0.10808 | 2521 | 54.83 | 105
5446 | PENRYN 11052406 | 152561105 | PENRYN 1105 | 2406 | TRUE | 6309.8622 | 123.5636 | 0.076795 | 50 | 0.0001488 | 754 | 13.0398 | 2568 | 0.0016854 | 0.084272 | 2522 | 0.98 | 736
9065 | OTTER 11017611 | 182941101 | OTTER 1101 | 7611 | FALSE | 7068.0362 | 7068.0362 | 4.3928 | 42 | 8.7447e-05 | 2001 | 37.9943 | 2291 | 0.0016834 | 0.070701 | 2523 | 0.49 | 896
4321 | BRUNSWICK 110633050 | 152481106 | BRUNSWICK 1106 | 33050 | FALSE | 6143.4432 | 1793.1664 | 1.1145 | 56 | 0.000194 | 425 | 9.4021 | 2637 | 0.0016799 | 0.094072 | 2524 | 2.96 | 571
7573 | ROSSMOOR 110639424 | 14161106 | ROSSMOOR 1106 | 39424 | FALSE | 3992.9225 | 1481.6598 | 0.92086 | 36 | 9.8e-05 | 1690 | 17.4915 | 2491 | 0.0016754 | 0.060313 | 2525 |  | 3138
1005 | ROB ROY 21045082 | 83692104 | ROB ROY 2104 | 5082 | FALSE | 33362.418 | 32012.7007 | 19.896 | 215 | 0.00012065 | 1172 | 16.3155 | 2512 | 0.0016672 | 0.35844 | 2526 | 2.33 | 613
5885 | LAURELES 11122768 | 182371112 | LAURELES 1112 | 2768 | FALSE | 12969.9695 | 10109.7249 | 6.2832 | 92 | 7.5187e-05 | 2326 | 22.2701 | 2424 | 0.0016647 | 0.15315 | 2527 | 0.05 | 2021
2281 | VOLTA 110185234 | 102541101 | VOLTA 1101 | 85234 | FALSE | 12730.8347 | 12730.8347 | 7.9123 | 92 | 7.7367e-05 | 2279 | 30.0376 | 2343 | 0.0016524 | 0.15202 | 2528 | 0.02 | 2526
3545 | PACIFICA 1104230272 | 22811104 | PACIFICA 1104 | 230272 | FALSE | 1833.3676 | 1377.39 | 0.85605 | 18 | 5.0412e-05 | 3031 | 15.9138 | 2516 | 0.0016485 | 0.029673 | 2529 |  | 2836
6564 | NEWBURG 1131557468 | 192151131 | NEWBURG 1131 | 557468 | FALSE | 3768.3144 | 1423.6732 | 0.88482 | 28 | 0.0001751 | 528 | 10.813 | 2614 | 0.0016475 | 0.046129 | 2530 |  | 3042
2123 | IGNACIO 11011300 | 42481101 | IGNACIO 1101 | 1300 | FALSE | 9816.2612 | 5145.088 | 3.1977 | 84 | 0.00010467 | 1538 | 15.4386 | 2525 | 0.0016445 | 0.13814 | 2531 | 0.08 | 1580
7516 | SAN LUIS OBISPO 1107CB | 182631107 | SAN LUIS OBISPO 1107 | CB | FALSE | 1947.472 | 1251.1033 | 0.77757 | 19 | 5.3489e-05 | 2951 | 32.6064 | 2325 | 0.0016436 | 0.031229 | 2532 | 0.03 | 2359
1994 | SILVERADO 2103218894 | 43432103 | SILVERADO 2103 | 218894 | TRUE | 1856.9722 | 540.1994 | 0.33574 | 14 | 6.9371e-05 | 2494 | 15.8967 | 2518 | 0.00163 | 0.022819 | 2533 |  | 2758
10204 | DUNBAR 110113481 | 43071101 | DUNBAR 1101 | 13481 | TRUE | 1739.6965 | 0 | 0 | 14 | 0.0001142 | 1314 | 13.6321 | 2559 | 0.0016289 | 0.022805 | 2534 | 0.03 | 2380
3837 | AUBERRY 1101D4982 | 254151101 | AUBERRY 1101 | D4982 | FALSE | 4312.861 | 4312.861 | 2.6805 | 21 | 3.0625e-05 | 3421 | 38.5371 | 2287 | 0.0016248 | 0.034121 | 2535 | 33.37 | 222
586 | WEIMAR 11022038 | 152491102 | WEIMAR 1102 | 2038 | FALSE | 21510.9233 | 21510.9233 | 13.3691 | 155 | 0.00018694 | 462 | 18.4659 | 2468 | 0.0016155 | 0.2504 | 2536 | 0.06 | 1908
5218 | SYCAMORE CREEK 11112268 | 102971111 | SYCAMORE CREEK 1111 | 2268 | FALSE | 35117.3516 | 35117.3516 | 21.8256 | 217 | 8.4177e-05 | 2087 | 23.7294 | 2408 | 0.0016039 | 0.34805 | 2537 | 69.93 | 69
1040 | GANSNER 110152664 | 103021101 | GANSNER 1101 | 52664 | TRUE | 5174.4008 | 284.4033 | 0.17676 | 44 | 5.8197e-05 | 2829 | 25.8938 | 2380 | 0.0016028 | 0.070524 | 2538 |  | 2705
3804 | POINT MORETTI 110110726 | 82931101 | POINT MORETTI 1101 | 10726 | FALSE | 16936.721 | 16936.721 | 10.5262 | 124 | 0.00026294 | 188 | 7.1636 | 2683 | 0.0016007 | 0.19849 | 2539 | 15.77 | 346
1389 | STANISLAUS 17011331 | 162821701 | STANISLAUS 1701 | 1331 | FALSE | 7064.7733 | 7064.7733 | 4.3908 | 63 | 0.00010598 | 1495 | 12.1416 | 2583 | 0.0015977 | 0.10065 | 2540 | 46.2 | 144
8302 | VALLEY VIEW 1106P166 | 14341106 | VALLEY VIEW 1106 | P166 | FALSE | 7343.1285 | 7068.5222 | 4.3931 | 27 | 0.00014292 | 827 | 10.6287 | 2617 | 0.0015975 | 0.043133 | 2541 | 0.97 | 738
7677 | POINT MORETTI 110136516 | 82931101 | POINT MORETTI 1101 | 36516 | FALSE | 6699.7019 | 6699.7019 | 4.1639 | 53 | 0.00037131 | 77 | 6.3459 | 2704 | 0.0015908 | 0.08431 | 2542 | 29.13 | 244
9231 | ROB ROY 21045304 | 83692104 | ROB ROY 2104 | 5304 | FALSE | 8039.9737 | 5763.285 | 3.5819 | 60 | 9.186e-05 | 1848 | 18.674 | 2464 | 0.0015784 | 0.094707 | 2543 | 0.05 | 1963
10838 | LAS GALLINAS A 1106685852 | 42991106 | LAS GALLINAS A 1106 | 685852 | TRUE | 222.9305 | 104.9331 | 0.065216 | 3 | 0.00011257 | 1352 | 15.9116 | 2517 | 0.0015648 | 0.0046945 | 2544 |  | 3611
1125 | LAS GALLINAS A 1106CB | 42991106 | LAS GALLINAS A 1106 | CB | TRUE | 16165.5618 | 153.7468 | 0.095554 | 111 | 7.0207e-05 | 2463 | 11.081 | 2607 | 0.0015644 | 0.17365 | 2545 | 0.1 | 1466
6613 | HICKS 111660050 | 83431116 | HICKS 1116 | 60050 | FALSE | 13116.246 | 13116.246 | 8.1518 | 98 | 0.00010761 | 1461 | 16.5517 | 2508 | 0.0015546 | 0.15235 | 2546 | 0.1 | 1480
10410 | PUEBLO 2102391312 | 43292102 | PUEBLO 2102 | 391312 | TRUE | 1866.0468 | 229.6394 | 0.14272 | 13 | 5.8919e-05 | 2810 | 14.6684 | 2538 | 0.0015528 | 0.020186 | 2547 |  | 3544
3988 | SAN RAFAEL 1108322 | 42011108 | SAN RAFAEL 1108 | 322 | FALSE | 11857.5634 | 11550.5948 | 7.1787 | 88 | 0.0001706 | 560 | 11.411 | 2599 | 0.0015474 | 0.13618 | 2548 | 1.05 | 721
3811 | OAKLAND X 1106950688 | 12541106 | OAKLAND X 1106 | 950688 | FALSE | 5883.5054 | 5883.5054 | 3.6566 | 50 | 0.00010781 | 1454 | 17.1924 | 2501 | 0.0015407 | 0.077034 | 2549 |  | 2854
1254 | CURTIS 17039240 | 163351703 | CURTIS 1703 | 9240 | FALSE | 17656.496 | 17656.496 | 10.9736 | 151 | 8.9367e-05 | 1936 | 23.8246 | 2406 | 0.0015394 | 0.23246 | 2550 | 0.09 | 1524
9703 | VOLTA 110280982 | 102541102 | VOLTA 1102 | 80982 | TRUE | 836.5231 | 836.5231 | 0.5199 | 8 | 7.4451e-05 | 2347 | 11.9509 | 2588 | 0.0015382 | 0.012305 | 2551 | 41.95 | 172
8204 | BEN LOMOND 04015144 | 83040401 | BEN LOMOND 0401 | 5144 | FALSE | 6368.9288 | 6368.9288 | 3.9583 | 36 | 0.00020138 | 392 | 8.6508 | 2650 | 0.0015295 | 0.055061 | 2552 | 32.7 | 225
4922 | BIG RIVER 11013019 | 43081101 | BIG RIVER 1101 | 3019 | TRUE | 1511.5981 | 426.9368 | 0.26534 | 11 | 7.3049e-05 | 2394 | 21.6652 | 2431 | 0.0015165 | 0.016682 | 2553 |  | 2928
4844 | SANTA ROSA A 1104173590 | 42151104 | SANTA ROSA A 1104 | 173590 | FALSE | 6901.197 | 6901.197 | 4.2891 | 46 | 9.087e-05 | 1887 | 19.2098 | 2458 | 0.0015131 | 0.069603 | 2554 |  | 2921
7483 | FLINT 1101CB | 152531101 | FLINT 1101 | CB | FALSE | 4176.9151 | 1037.2766 | 0.64467 | 36 | 0.00021226 | 350 | 8.6501 | 2651 | 0.0015072 | 0.054259 | 2555 | 0.03 | 2345
6669 | DUNBAR 1101234 | 43071101 | DUNBAR 1101 | 234 | FALSE | 10290.6171 | 5584.5077 | 3.4708 | 81 | 0.0001531 | 719 | 12.3014 | 2581 | 0.0015051 | 0.12191 | 2556 | 0.04 | 2094
7886 | OAKHURST 1102CB | 254421102 | OAKHURST 1102 | CB | FALSE | 7703.9355 | 4253.8822 | 2.6438 | 61 | 0.00011905 | 1206 | 11.75 | 2592 | 0.0014997 | 0.091479 | 2557 | 1.94 | 628
1710 | ELK 110191336 | 42981101 | ELK 1101 | 91336 | FALSE | 13315.5222 | 12740.7114 | 7.9184 | 78 | 8.2847e-05 | 2135 | 14.0784 | 2546 | 0.0014969 | 0.11676 | 2558 | 0.04 | 2153
583 | MONTE RIO 1111969182 | 42811111 | MONTE RIO 1111 | 969182 | FALSE | 8578.2654 | 8578.2654 | 5.3314 | 64 | 0.00023272 | 274 | 7.8723 | 2672 | 0.0014937 | 0.095599 | 2559 |  | 2685
3182 | KONOCTI 1108950 | 43311108 | KONOCTI 1108 | 950 | FALSE | 11853.1557 | 9978.6098 | 6.2017 | 85 | 0.00011166 | 1376 | 9.5946 | 2629 | 0.0014937 | 0.12697 | 2560 | 0.09 | 1575
5332 | CLAYTON 2212CB | 12022212 | CLAYTON 2212 | CB | FALSE | 17569.8608 | 1899.4744 | 1.1805 | 140 | 3.3628e-05 | 3373 | 17.212 | 2499 | 0.0014894 | 0.20851 | 2561 | 0.55 | 873
4270 | LAS GALLINAS A 1104304 | 42991104 | LAS GALLINAS A 1104 | 304 | TRUE | 3131.1603 | 221.043 | 0.13738 | 27 | 7.2267e-05 | 2410 | 12.9614 | 2570 | 0.0014798 | 0.039953 | 2562 | 0.03 | 2304
886 | SALT SPRINGS 21024796 | 163692102 | SALT SPRINGS 2102 | 4796 | FALSE | 11571.4706 | 11571.4706 | 7.1917 | 114 | 8.3272e-05 | 2126 | 15.4981 | 2524 | 0.0014707 | 0.16766 | 2563 | 50.63 | 117
1846 | BIG RIVER 11013002 | 43081101 | BIG RIVER 1101 | 3002 | FALSE | 13206.8342 | 11656.2739 | 7.2444 | 76 | 8.5336e-05 | 2046 | 10.9995 | 2610 | 0.001464 | 0.11126 | 2564 | 0.15 | 1296
6005 | MIRABEL 1101201156 | 42091101 | MIRABEL 1101 | 201156 | FALSE | 2780.2158 | 2335.0863 | 1.4513 | 26 | 0.000132 | 983 | 11.0364 | 2609 | 0.0014632 | 0.038044 | 2565 |  | 2996
9286 | SOLEDAD 2101315500 | 182052101 | SOLEDAD 2101 | 315500 | FALSE | 5515.195 | 1783.0288 | 1.1082 | 22 | 2.1144e-05 | 3532 | 19.9522 | 2450 | 0.0014578 | 0.032073 | 2566 |  | 3335
2001 | SAN RAFAEL 110839156 | 42011108 | SAN RAFAEL 1108 | 39156 | FALSE | 7678.6279 | 5580.9258 | 3.4686 | 62 | 0.00036657 | 79 | 5.0499 | 2749 | 0.0014467 | 0.089693 | 2567 | 0.4 | 949
2593 | HIGGINS 1104533648 | 152691104 | HIGGINS 1104 | 533648 | FALSE | 10867.8258 | 10867.8258 | 6.7544 | 93 | 0.00016205 | 621 | 8.4995 | 2655 | 0.0014323 | 0.13321 | 2568 | 0.11 | 1415
2853 | EL DORADO PH 2101668674 | 152762101 | EL DORADO PH 2101 | 668674 | FALSE | 15298.6549 | 15298.6549 | 9.5082 | 112 | 0.00024869 | 220 | 8.5559 | 2654 | 0.0014289 | 0.16003 | 2569 |  | 2801
701 | CAMP EVERS 210512590 | 83622105 | CAMP EVERS 2105 | 12590 | FALSE | 8818.0631 | 8233.9726 | 5.1174 | 69 | 0.00032896 | 102 | 7.9903 | 2671 | 0.0014267 | 0.09844 | 2570 | 0.34 | 980
9206 | SISQUOC 110245261 | 182811102 | SISQUOC 1102 | 45261 | TRUE | 20192.7526 | 164.9958 | 0.10255 | 10 | 7.3888e-05 | 2362 | 8.6022 | 2652 | 0.001423 | 0.01423 | 2571 |  | 3326
6505 | MONTE RIO 11131313 | 42811113 | MONTE RIO 1113 | 1313 | FALSE | 1996.4298 | 1996.4298 | 1.2408 | 19 | 0.00014421 | 810 | 12.5764 | 2576 | 0.0014057 | 0.026709 | 2572 | 44.58 | 156
4406 | COTATI 110475972 | 42271104 | COTATI 1104 | 75972 | FALSE | 7223.394 | 5386.1403 | 3.3475 | 61 | 6.5028e-05 | 2609 | 22.3 | 2423 | 0.0013938 | 0.085021 | 2573 | 0.52 | 885
7967 | MENLO 11038982 | 24131103 | MENLO 1103 | 8982 | FALSE | 7434.3823 | 7434.3823 | 4.6205 | 50 | 0.00014907 | 751 | 11.9525 | 2587 | 0.0013928 | 0.06964 | 2574 | 0.08 | 1625
9897 | ORO FINO 110239154 | 103031102 | ORO FINO 1102 | 39154 | FALSE | 1419.8889 | 1419.8889 | 0.88247 | 11 | 0.00019824 | 403 | 21.6746 | 2430 | 0.0013923 | 0.015315 | 2575 | 62.39 | 84
5536 | GUALALA 1111CB | 42841111 | GUALALA 1111 | CB | FALSE | 6227.6638 | 6227.6638 | 3.8705 | 47 | 0.00010177 | 1608 | 5.1216 | 2747 | 0.0013913 | 0.065391 | 2576 | 0.03 | 2337
3869 | PINE GROVE 11021765 | 163751102 | PINE GROVE 1102 | 1765 | FALSE | 2336.7952 | 2336.7952 | 1.4523 | 20 | 0.00017078 | 558 | 6.0123 | 2713 | 0.0013887 | 0.027774 | 2577 | 15.71 | 348
2705 | FORT ORD 210736596 | 182402107 | FORT ORD 2107 | 36596 | FALSE | 20043.7619 | 6572.3951 | 4.0848 | 145 | 1.719e-05 | 3570 | 17.052 | 2503 | 0.0013847 | 0.20079 | 2578 | 0.03 | 2397
5302 | BIG BASIN 11015000 | 82841101 | BIG BASIN 1101 | 5000 | FALSE | 3149.0186 | 3149.0186 | 1.9571 | 23 | 0.00041733 | 64 | 2.1336 | 2834 | 0.0013814 | 0.031772 | 2579 | 24.55 | 277
10692 | ROSSMOOR 1109CB | 14161109 | ROSSMOOR 1109 | CB | TRUE | 244.7023 | 7.571 | 0.0047054 | 6 | 8.8688e-05 | 1962 | 31.698 | 2332 | 0.001321 | 0.0079259 | 2580 |  | 3593
5396 | FORT BRAGG A 11041316 | 42761104 | FORT BRAGG A 1104 | 1316 | FALSE | 22645.6685 | 22101.0688 | 13.7359 | 166 | 7.7968e-05 | 2260 | 13.3542 | 2565 | 0.0013124 | 0.21786 | 2581 | 0.12 | 1400
6380 | GUALALA 111135562 | 42841111 | GUALALA 1111 | 35562 | FALSE | 22914.0776 | 22914.0776 | 14.2412 | 147 | 0.00010505 | 1525 | 11.7038 | 2593 | 0.0013006 | 0.19119 | 2582 | 0.16 | 1270
5878 | OLEMA 11011318 | 42291101 | OLEMA 1101 | 1318 | FALSE | 16637.0018 | 13693.4076 | 8.5105 | 113 | 0.00013033 | 1004 | 8.2659 | 2664 | 0.0012974 | 0.14661 | 2583 | 9.77 | 404
7013 | SALT SPRINGS 2102L491 | 163692102 | SALT SPRINGS 2102 | L491 | FALSE | 3564.5514 | 3564.5514 | 2.2154 | 31 | 0.00010065 | 1632 | 5.4343 | 2732 | 0.0012903 | 0.039999 | 2584 | 33.77 | 219
3314 | LLAGAS 2101XR244 | 83182101 | LLAGAS 2101 | XR244 | TRUE | 22757.8317 | 0 | 0 | 157 | 6.3757e-05 | 2654 | 15.2591 | 2527 | 0.0012825 | 0.20135 | 2585 | 0.59 | 855
595 | GARBERVILLE 1103CB | 192221103 | GARBERVILLE 1103 | CB | TRUE | 3592.4976 | 971.3906 | 0.60372 | 31 | 0.0002505 | 215 | 3.3852 | 2798 | 0.0012726 | 0.039451 | 2586 | 0.05 | 1979
842 | ELK 11011272 | 42981101 | ELK 1101 | 1272 | FALSE | 36077.8728 | 35548.517 | 22.0935 | 236 | 0.00010152 | 1616 | 17.6496 | 2487 | 0.0012681 | 0.29926 | 2587 | 0.25 | 1089
3308 | SNEATH LANE 1106CB | 22721106 | SNEATH LANE 1106 | CB | FALSE | 9891.2145 | 4885.2685 | 3.0362 | 66 | 2.8183e-05 | 3454 | 23.8416 | 2402 | 0.0012656 | 0.083532 | 2588 | 0.03 | 2371
4674 | WEST POINT 110112256 | 163201101 | WEST POINT 1101 | 12256 | FALSE | 10425.1159 | 10425.1159 | 6.4793 | 86 | 9.8504e-05 | 1679 | 19.6956 | 2453 | 0.0012622 | 0.10855 | 2589 | 60.88 | 87
141 | MORRO BAY 1102W34 | 183011102 | MORRO BAY 1102 | W34 | FALSE | 15456.5208 | 12223.0154 | 7.5967 | 112 | 3.8291e-05 | 3294 | 31.2471 | 2337 | 0.0012584 | 0.14094 | 2590 |  | 2657
8023 | HOLLISTER 2105903238 | 182492105 | HOLLISTER 2105 | 903238 | FALSE | 9893.8007 | 6450.8713 | 4.0092 | 30 | 4.7333e-05 | 3108 | 30.0306 | 2344 | 0.001258 | 0.037741 | 2591 |  | 3186
53 | DUNBAR 1102448 | 43071102 | DUNBAR 1102 | 448 | FALSE | 14554.2556 | 3932.5973 | 2.4441 | 116 | 9.7296e-05 | 1707 | 15.8508 | 2519 | 0.001256 | 0.1457 | 2592 |  | 2652
5111 | ALHAMBRA 110581514 | 14101105 | ALHAMBRA 1105 | 81514 | FALSE | 7697.8392 | 4781.286 | 2.9716 | 65 | 8.7032e-05 | 2011 | 13.7396 | 2556 | 0.0012525 | 0.08141 | 2593 | 0.04 | 2121
347 | BRUNSWICK 11052204 | 152481105 | BRUNSWICK 1105 | 2204 | FALSE | 11625.6324 | 11625.6324 | 7.2254 | 84 | 9.4601e-05 | 1775 | 11.1006 | 2606 | 0.0012429 | 0.1044 | 2594 | 40.14 | 185
2860 | CAMP EVERS 210311046 | 83622103 | CAMP EVERS 2103 | 11046 | FALSE | 25866.5621 | 25866.5621 | 16.0762 | 194 | 0.00016384 | 601 | 6.3121 | 2705 | 0.0012326 | 0.23912 | 2595 | 1.33 | 683
5152 | WOODSIDE 11018522 | 24251101 | WOODSIDE 1101 | 8522 | FALSE | 15153.8377 | 3071.2008 | 1.9088 | 123 | 0.0001684 | 573 | 8.4903 | 2656 | 0.0012059 | 0.14833 | 2596 | 0.11 | 1425
10217 | PAUL SWEET 2102959032 | 83252102 | PAUL SWEET 2102 | 959032 | FALSE | 1582.9544 | 1283.5288 | 0.79772 | 11 | 0.00012885 | 1030 | 15.1847 | 2528 | 0.0012034 | 0.013238 | 2597 |  | 3517
6918 | DUNBAR 1103872066 | 43071103 | DUNBAR 1103 | 872066 | TRUE | 1285.5374 | 856.8881 | 0.53256 | 13 | 8.9931e-05 | 1916 | 14.7027 | 2535 | 0.0011906 | 0.015478 | 2598 |  | 3074
5057 | WEIMAR 11012764 | 152491101 | WEIMAR 1101 | 2764 | FALSE | 9871.3778 | 9871.3778 | 6.1351 | 68 | 0.0002671 | 178 | 5.6584 | 2724 | 0.0011906 | 0.080958 | 2599 | 0.05 | 2046
8401 | IGNACIO 11051943 | 42481105 | IGNACIO 1105 | 1943 | FALSE | 1959.963 | 1959.963 | 1.2181 | 17 | 0.00014604 | 788 | 5.6591 | 2723 | 0.0011872 | 0.020183 | 2600 |  | 3220
2098 | VOLTA 1102641544 | 102541102 | VOLTA 1102 | 641544 | FALSE | 7956.2573 | 7956.2573 | 4.9448 | 58 | 0.00010868 | 1431 | 9.0793 | 2642 | 0.0011816 | 0.068531 | 2601 |  | 2763
5971 | SANTA ROSA A 110464565 | 42151104 | SANTA ROSA A 1104 | 64565 | FALSE | 1284.2848 | 1284.2848 | 0.79819 | 13 | 0.00016067 | 634 | 14.7117 | 2534 | 0.001175 | 0.015275 | 2602 | 0.3 | 1013
1887 | NAPA 1112CB | 42021112 | NAPA 1112 | CB | TRUE | 26742.8753 | 940.9991 | 0.58483 | 226 | 4.1039e-05 | 3242 | 20.6872 | 2439 | 0.0011724 | 0.26497 | 2603 |  | 2752
5833 | DEL MONTE 21049500 | 182222104 | DEL MONTE 2104 | 9500 | FALSE | 10910.9002 | 9168.0738 | 5.698 | 71 | 6.6682e-05 | 2565 | 18.8342 | 2462 | 0.0011663 | 0.082807 | 2604 | 1.62 | 662
3301 | RALSTON 1101836528 | 24141101 | RALSTON 1101 | 836528 | FALSE | 4695.3621 | 4679.584 | 2.9084 | 39 | 3.0209e-05 | 3424 | 39.6633 | 2275 | 0.0011552 | 0.045051 | 2605 |  | 2820
1278 | LOS GATOS 1107CB | 82021107 | LOS GATOS 1107 | CB | FALSE | 25409.8546 | 24616.6476 | 15.2993 | 192 | 0.00012212 | 1146 | 9.4762 | 2636 | 0.0011504 | 0.22088 | 2606 | 0.14 | 1327
1215 | SAN RAMON 2106CB | 14232106 | SAN RAMON 2106 | CB | TRUE | 3504.1175 | 755.1177 | 0.46931 | 25 | 5.9264e-05 | 2797 | 9.8829 | 2625 | 0.001149 | 0.028724 | 2607 |  | 2717
10840 | CLOVERDALE 1101704542 | 42821101 | CLOVERDALE 1101 | 704542 | TRUE | 487.4963 | 345.9417 | 0.215 | 3 | 0.00010371 | 1556 | 10.6423 | 2616 | 0.0011475 | 0.0034424 | 2608 |  | 3612
9582 | LOS OSITOS 2102624200 | 182082102 | LOS OSITOS 2102 | 624200 | FALSE | 3744.0071 | 2491.858 | 1.5487 | 6 | 9.1262e-06 | 3614 | 78.1632 | 2058 | 0.0011432 | 0.0068593 | 2609 |  | 3383
6642 | STANISLAUS 1702L5381 | 162821702 | STANISLAUS 1702 | L5381 | FALSE | 1955.4877 | 1955.4877 | 1.2153 | 15 | 8.6227e-05 | 2029 | 11.1601 | 2603 | 0.0011429 | 0.017144 | 2610 | 63.74 | 80
10129 | VALLEY VIEW 1103218424 | 14341103 | VALLEY VIEW 1103 | 218424 | TRUE | 877.6167 | 866.5125 | 0.53854 | 4 | 6.9394e-05 | 2493 | 17.8902 | 2485 | 0.0011372 | 0.0045488 | 2611 |  | 3498
2575 | BIG RIVER 110155402 | 43081101 | BIG RIVER 1101 | 55402 | FALSE | 14989.6887 | 3994.4825 | 2.4826 | 104 | 6.4572e-05 | 2623 | 16.7266 | 2505 | 0.0011234 | 0.11683 | 2612 | 0.02 | 2517
2609 | MIRABEL 1102503000 | 42091102 | MIRABEL 1102 | 503000 | FALSE | 7554.2208 | 7373.131 | 4.5824 | 54 | 0.00017004 | 564 | 3.5877 | 2787 | 0.0011185 | 0.060401 | 2613 |  | 2789
8405 | MONTE RIO 1111240 | 42811111 | MONTE RIO 1111 | 240 | FALSE | 4953.3762 | 4953.3762 | 3.0785 | 42 | 0.00020071 | 393 | 8.5626 | 2653 | 0.0011134 | 0.046762 | 2614 | 27.15 | 261
1947 | ROB ROY 210410930 | 83692104 | ROB ROY 2104 | 10930 | FALSE | 18316.5864 | 1585.2477 | 0.98524 | 149 | 9.2072e-05 | 1841 | 11.2167 | 2602 | 0.0011126 | 0.16578 | 2615 | 0.03 | 2315
6789 | MIRABEL 11021139 | 42091102 | MIRABEL 1102 | 1139 | FALSE | 3291.1128 | 3291.1128 | 2.0454 | 25 | 0.00021661 | 335 | 5.771 | 2718 | 0.0011071 | 0.027677 | 2616 | 19.12 | 313
10452 | PIT NO 3 21011480 | 103732101 | PIT NO 3 2101 | 1480 | FALSE | 3913.3341 | 3463.9371 | 2.1529 | 20 | 6.904e-05 | 2506 | 14.3241 | 2543 | 0.0011038 | 0.022077 | 2617 | 0.02 | 2410
3881 | CORRAL 110275622 | 162991102 | CORRAL 1102 | 75622 | FALSE | 9209.8908 | 1956.9061 | 1.2162 | 78 | 8.9335e-05 | 1938 | 14.1186 | 2545 | 0.0010989 | 0.085711 | 2618 | 1.24 | 694
656 | MORAGA 1105CB | 13801105 | MORAGA 1105 | CB | FALSE | 17419.9506 | 9244.2642 | 5.7453 | 121 | 8.2774e-05 | 2137 | 22.4988 | 2417 | 0.001078 | 0.13044 | 2619 | 36.92 | 204
7044 | SALT SPRINGS 210297924 | 163692102 | SALT SPRINGS 2102 | 97924 | FALSE | 8287.4089 | 8287.4089 | 5.1507 | 49 | 8.4247e-05 | 2084 | 16.5614 | 2507 | 0.0010653 | 0.052198 | 2620 | 28.19 | 252
1866 | HIGGINS 1104842642 | 152691104 | HIGGINS 1104 | 842642 | FALSE | 9353.842 | 9353.842 | 5.8135 | 80 | 0.00015044 | 731 | 10.167 | 2622 | 0.0010503 | 0.084021 | 2621 | 0.11 | 1445
1316 | SHADY GLEN 1101CB | 152431101 | SHADY GLEN 1101 | CB | FALSE | 8798.7393 | 5676.9517 | 3.5282 | 72 | 0.00028651 | 144 | 7.3277 | 2682 | 0.0010502 | 0.075616 | 2622 | 5.26 | 492
8148 | MIWUK 1702S1547 | 163661702 | MIWUK 1702 | S1547 | FALSE | 4459.8848 | 4459.8848 | 2.7718 | 39 | 5.3114e-05 | 2964 | 14.6954 | 2536 | 0.0010487 | 0.040901 | 2623 | 82.41 | 44
4763 | SNEATH LANE 11071277 | 22721107 | SNEATH LANE 1107 | 1277 | TRUE | 3471.3767 | 0 | 0 | 30 | 4.0209e-05 | 3263 | 12.7259 | 2574 | 0.001018 | 0.030539 | 2624 | 0.04 | 2212
10287 | DUNLAP 11027290 | 254061102 | DUNLAP 1102 | 7290 | FALSE | 1075.4071 | 1075.4071 | 0.66837 | 8 | 2.8269e-05 | 3452 | 23.8308 | 2405 | 0.0010126 | 0.0081011 | 2625 | 0 | 2635
9998 | RESEARCH 2102644462 | 14692102 | RESEARCH 2102 | 644462 | TRUE | 2486.8085 | 567.6161 | 0.35278 | 24 | 0.00010098 | 1625 | 12.9287 | 2571 | 0.0010124 | 0.024298 | 2626 |  | 3468
1937 | SARATOGA 1107LC12 | 83371107 | SARATOGA 1107 | LC12 | FALSE | 12044.6481 | 12044.6481 | 7.4858 | 86 | 0.00017659 | 521 | 13.8877 | 2554 | 0.0010097 | 0.086838 | 2627 | 0.56 | 865
3 | HIGGINS 1104498932 | 152691104 | HIGGINS 1104 | 498932 | FALSE | 6861.4641 | 6024.2456 | 3.7441 | 57 | 0.00014672 | 777 | 8.6826 | 2649 | 0.0010076 | 0.057431 | 2628 | 0.09 | 1548
7928 | HALSEY 11015731 | 152241101 | HALSEY 1101 | 5731 | FALSE | 5029.6194 | 5029.6194 | 3.1259 | 41 | 0.00015547 | 690 | 3.5444 | 2790 | 0.0010067 | 0.041274 | 2629 | 0.05 | 1973
5582 | TAMARACK 1101CB | 152291101 | TAMARACK 1101 | CB | FALSE | 28734.8817 | 28123.7558 | 17.479 | 148 | 7.11e-05 | 2442 | 13.9274 | 2552 | 0.0010065 | 0.14896 | 2630 | 0.36 | 966
5935 | MORAGA 1103CB | 13801103 | MORAGA 1103 | CB | FALSE | 10346.1129 | 2141.3708 | 1.3309 | 82 | 8.1676e-05 | 2163 | 6.4364 | 2698 | 0.0010058 | 0.082476 | 2631 | 0.06 | 1846
6299 | PEORIA 170587222 | 163781705 | PEORIA 1705 | 87222 | FALSE | 8479.914 | 8240.0573 | 5.1212 | 57 | 0.00010497 | 1529 | 10.4869 | 2620 | 0.0010031 | 0.057176 | 2632 | 0.1 | 1504
2943 | PAUL SWEET 2105CB | 83252105 | PAUL SWEET 2105 | CB | FALSE | 14092.576 | 11980.8022 | 7.4461 | 86 | 0.00012586 | 1080 | 5.5912 | 2727 | 0.0010024 | 0.086208 | 2633 | 0.22 | 1132
9018 | GREEN VALLEY 2101509068 | 83192101 | GREEN VALLEY 2101 | 509068 | FALSE | 2868.1374 | 1655.4712 | 1.0289 | 22 | 0.00010648 | 1487 | 17.3491 | 2495 | 0.0010019 | 0.022042 | 2634 |  | 3297
8604 | MORGAN HILL 2105975388 | 83242105 | MORGAN HILL 2105 | 975388 | TRUE | 2101.0589 | 775.2264 | 0.48181 | 18 | 4.0105e-05 | 3265 | 13.2566 | 2567 | 0.0010016 | 0.018029 | 2635 |  | 3242
5120 | PAUL SWEET 21045394 | 83252104 | PAUL SWEET 2104 | 5394 | FALSE | 24529.1372 | 23340.3938 | 14.5061 | 180 | 0.00013063 | 998 | 7.7218 | 2674 | 0.00099214 | 0.17859 | 2636 | 43.45 | 169
6690 | GUALALA 1111887180 | 42841111 | GUALALA 1111 | 887180 | FALSE | 8692.4371 | 8589.4892 | 5.3384 | 61 | 5.5738e-05 | 2897 | 12.9178 | 2572 | 0.00098628 | 0.060163 | 2637 | 0.07 | 1715
3875 | FORT BRAGG A 11014698 | 42761101 | FORT BRAGG A 1101 | 4698 | FALSE | 12883.0062 | 12883.0062 | 8.0068 | 101 | 0.00018389 | 481 | 12.0639 | 2584 | 0.00097756 | 0.098734 | 2638 | 0.05 | 1998
8479 | SALT SPRINGS 2102L7283 | 163692102 | SALT SPRINGS 2102 | L7283 | FALSE | 1053.4945 | 1053.4945 | 0.65475 | 12 | 7.514e-05 | 2329 | 13.9335 | 2551 | 0.00097446 | 0.011693 | 2639 | 29.37 | 241
1105 | PLACER 110451732 | 152461104 | PLACER 1104 | 51732 | FALSE | 12971.5884 | 1093.5921 | 0.67967 | 110 | 0.00019845 | 402 | 3.0886 | 2809 | 0.00097323 | 0.10706 | 2640 | 0.02 | 2495
6916 | BEN LOMOND 110196738 | 83041101 | BEN LOMOND 1101 | 96738 | FALSE | 10792.8538 | 10792.8538 | 6.7078 | 84 | 0.00020283 | 387 | 5.4435 | 2731 | 0.00097276 | 0.081712 | 2641 | 21.67 | 298
5851 | SAN RAFAEL 1109692576 | 42011109 | SAN RAFAEL 1109 | 692576 | FALSE | 5517.9962 | 3874.9491 | 2.4083 | 51 | 0.0001303 | 1007 | 7.0569 | 2686 | 0.0009691 | 0.049424 | 2642 |  | 2983
1894 | HALF MOON BAY 11028848 | 24101102 | HALF MOON BAY 1102 | 8848 | FALSE | 16215.0785 | 6200.2521 | 3.8535 | 117 | 6.6972e-05 | 2558 | 11.0461 | 2608 | 0.00096385 | 0.11277 | 2643 | 0.22 | 1123
3844 | OLEMA 110150396 | 42291101 | OLEMA 1101 | 50396 | FALSE | 21037.3757 | 20827.3892 | 12.9443 | 162 | 8.5221e-05 | 2050 | 11.5065 | 2597 | 0.00096084 | 0.15566 | 2644 | 20.38 | 306
8685 | SANTA ROSA A 1111114 | 42151111 | SANTA ROSA A 1111 | 114 | TRUE | 4957.8887 | 17.4908 | 0.010871 | 40 | 8.3173e-05 | 2128 | 9.1847 | 2640 | 0.00096055 | 0.038422 | 2645 | 8.42 | 426
3877 | LOS GATOS 110660116 | 82021106 | LOS GATOS 1106 | 60116 | FALSE | 19634.1928 | 19634.1928 | 12.2027 | 151 | 0.00020011 | 397 | 4.9468 | 2757 | 0.00095505 | 0.14421 | 2646 | 0.89 | 751
46 | MONTE RIO 11111703 | 42811111 | MONTE RIO 1111 | 1703 | FALSE | 2213.9946 | 2213.9946 | 1.376 | 16 | 0.00013016 | 1008 | 6.0137 | 2712 | 0.00095446 | 0.015271 | 2647 | 43.57 | 165
2992 | EMERALD LAKE 0401CB | 24080401 | EMERALD LAKE 0401 | CB | FALSE | 21117.9549 | 15035.2163 | 9.3444 | 130 | 6.8162e-05 | 2531 | 7.7386 | 2673 | 0.00094726 | 0.12314 | 2648 | 0.52 | 887
5798 | DIAMOND SPRINGS 1107217974 | 152261107 | DIAMOND SPRINGS 1107 | 217974 | FALSE | 6862.6922 | 6593.0651 | 4.0976 | 44 | 0.00013259 | 971 | 7.0882 | 2685 | 0.00093976 | 0.04135 | 2649 |  | 2978
5351 | TEMPLETON 2113A32 | 183052113 | TEMPLETON 2113 | A32 | FALSE | 9519.6113 | 2633.3805 | 1.6367 | 76 | 6.2625e-05 | 2697 | 14.4505 | 2541 | 0.00093807 | 0.071294 | 2650 | 0.03 | 2314
5142 | STANISLAUS 17021850 | 162821702 | STANISLAUS 1702 | 1850 | FALSE | 21661.1812 | 21661.1812 | 13.4625 | 182 | 0.00013942 | 879 | 5.1605 | 2745 | 0.00093342 | 0.16988 | 2651 | 73.2 | 62
7375 | ARCATA 11224218 | 192021122 | ARCATA 1122 | 4218 | FALSE | 7931.9123 | 7690.241 | 4.7795 | 27 | 0.00022706 | 297 | 5.3463 | 2735 | 0.00093079 | 0.025131 | 2652 | 0.09 | 1526
2956 | BIG BASIN 110276752 | 82841102 | BIG BASIN 1102 | 76752 | FALSE | 4380.3192 | 4380.3192 | 2.7224 | 36 | 0.00025263 | 209 | 5.3491 | 2733 | 0.00091318 | 0.032874 | 2653 | 0.44 | 924
3629 | BRUNSWICK 11051030 | 152481105 | BRUNSWICK 1105 | 1030 | FALSE | 25567.0003 | 25567.0003 | 15.89 | 217 | 0.00014916 | 749 | 5.1044 | 2748 | 0.00090994 | 0.19746 | 2654 | 21.6 | 300
9250 | MIWUK 17021808 | 163661702 | MIWUK 1702 | 1808 | FALSE | 2949.8139 | 2949.8139 | 1.8333 | 27 | 9.0273e-05 | 1905 | 7.9905 | 2670 | 0.00090929 | 0.024551 | 2655 | 46.07 | 145
8540 | DEL MONTE 210436720 | 182222104 | DEL MONTE 2104 | 36720 | FALSE | 12840.8619 | 9577.7665 | 5.9526 | 87 | 5.288e-05 | 2972 | 18.0958 | 2475 | 0.00089535 | 0.077895 | 2656 | 0.12 | 1394
950 | JARVIS 1108MR366 | 13501108 | JARVIS 1108 | MR366 | TRUE | 15876.8969 | 0 | 0 | 134 | 1.4916e-05 | 3586 | 46.6158 | 2237 | 0.00088159 | 0.11813 | 2657 |  | 2698
1888 | ROB ROY 2104CB | 83692104 | ROB ROY 2104 | CB | FALSE | 23033.3792 | 23033.3792 | 14.3153 | 170 | 0.00010514 | 1519 | 8.871 | 2646 | 0.0008744 | 0.14865 | 2658 | 0.65 | 822
311 | SALT SPRINGS 21023142 | 163692102 | SALT SPRINGS 2102 | 3142 | FALSE | 28901.7283 | 28901.7283 | 17.9625 | 256 | 8.7499e-05 | 1999 | 11.3039 | 2600 | 0.00086175 | 0.22061 | 2659 | 128.2 | 8
978 | BRYANT 0402CB | 13090402 | BRYANT 0402 | CB | FALSE | 12456.8292 | 3768.052 | 2.3419 | 111 | 9.7026e-05 | 1713 | 9.3336 | 2638 | 0.00085884 | 0.095332 | 2660 | 0.34 | 979
7054 | STANISLAUS 1702L3151 | 162821702 | STANISLAUS 1702 | L3151 | FALSE | 1595.4085 | 1595.4085 | 0.99155 | 13 | 0.0001267 | 1068 | 7.3809 | 2679 | 0.00085242 | 0.011082 | 2661 | 25 | 273
3980 | BIG BASIN 110112838 | 82841101 | BIG BASIN 1101 | 12838 | FALSE | 3807.4911 | 3807.4911 | 2.3664 | 32 | 0.00058408 | 21 | 1.5522 | 2860 | 0.00085046 | 0.027215 | 2662 | 8.72 | 421
8804 | SILVERADO 2103403102 | 43432103 | SILVERADO 2103 | 403102 | TRUE | 2765.6183 | 788.5735 | 0.4901 | 18 | 0.00014171 | 843 | 5.3389 | 2736 | 0.00084561 | 0.015221 | 2663 |  | 3267
6283 | HATTON 11022010 | 182291102 | HATTON 1102 | 2010 | FALSE | 6409.6213 | 6409.6213 | 3.9836 | 43 | 8.8563e-05 | 1970 | 8.3553 | 2660 | 0.00084365 | 0.036277 | 2664 | 0.11 | 1409
164 | CORONA 11034446 | 43491103 | CORONA 1103 | 4446 | TRUE | 17302.7635 | 0 | 0 | 124 | 4.9277e-05 | 3056 | 12.6776 | 2575 | 0.00084052 | 0.10422 | 2665 | 0.04 | 2135
5512 | MORAGA 1101669542 | 13801101 | MORAGA 1101 | 669542 | FALSE | 5668.7589 | 5668.7589 | 3.5232 | 49 | 0.00018473 | 476 | 4.4449 | 2769 | 0.0008334 | 0.040836 | 2666 |  | 2960
5671 | CURTIS 170190120 | 163351701 | CURTIS 1701 | 90120 | FALSE | 8309.1292 | 5041.5999 | 3.1334 | 64 | 0.00010439 | 1542 | 5.6342 | 2725 | 0.00082387 | 0.052727 | 2667 | 0.04 | 2200
5328 | OROSI 11027948F | 252841102 | OROSI 1102 | 7948F | FALSE | 13813.6905 | 1712.0139 | 1.064 | 74 | 2.7103e-05 | 3472 | 53.0836 | 2194 | 0.00082174 | 0.060809 | 2668 | 0.02 | 2432
3271 | STAFFORD 1101CB | 43201101 | STAFFORD 1101 | CB | FALSE | 19644.2096 | 2188.9817 | 1.3605 | 180 | 4.3869e-05 | 3192 | 3.8934 | 2779 | 0.0008192 | 0.14746 | 2669 | 0.05 | 1928
3349 | STANISLAUS 17026028 | 162821702 | STANISLAUS 1702 | 6028 | FALSE | 13370.3026 | 13370.3026 | 8.3097 | 115 | 0.00011502 | 1298 | 6.888 | 2688 | 0.0008147 | 0.09369 | 2670 | 56.37 | 98
4063 | REDBUD 1102432 | 43191102 | REDBUD 1102 | 432 | FALSE | 18069.9686 | 1802.3639 | 1.1202 | 130 | 5.4493e-05 | 2933 | 13.5928 | 2560 | 0.00080536 | 0.1047 | 2671 | 0.03 | 2402
4207 | SPRING GAP 170210720 | 162831702 | SPRING GAP 1702 | 10720 | FALSE | 7675.033 | 7675.033 | 4.7701 | 25 | 2.2157e-05 | 3517 | 32.3965 | 2326 | 0.00079114 | 0.019779 | 2672 | 23.43 | 287
6208 | BIG MEADOWS 2101CB | 102812101 | BIG MEADOWS 2101 | CB | FALSE | 3388.6184 | 3388.6184 | 2.106 | 21 | 6.388e-05 | 2651 | 12.5128 | 2578 | 0.00079069 | 0.016605 | 2673 | 0.04 | 2209
682 | ROSSMOOR 110676468 | 14161106 | ROSSMOOR 1106 | 76468 | FALSE | 4744.0085 | 1281.0776 | 0.79619 | 35 | 9.8202e-05 | 1686 | 6.3972 | 2700 | 0.00078905 | 0.027617 | 2674 | 0.03 | 2373
5936 | OAKLAND K 1102CB | 12101102 | OAKLAND K 1102 | CB | FALSE | 4816.3453 | 4816.3453 | 2.9934 | 40 | 0.00013401 | 943 | 11.9588 | 2585 | 0.0007688 | 0.030752 | 2675 | 31.2 | 232
5479 | ROSSMOOR 1108CB | 14161108 | ROSSMOOR 1108 | CB | FALSE | 11748.8949 | 6728.9489 | 4.1821 | 92 | 9.2886e-05 | 1826 | 6.3592 | 2703 | 0.00076238 | 0.070139 | 2676 | 0.16 | 1251
3739 | WEIMAR 1102CB | 152491102 | WEIMAR 1102 | CB | FALSE | 19605.5563 | 19605.5563 | 12.1849 | 151 | 0.00013907 | 885 | 11.5584 | 2596 | 0.00075189 | 0.11354 | 2677 | 0.07 | 1772
4477 | MIWUK 170238218 | 163661702 | MIWUK 1702 | 38218 | FALSE | 17605.0564 | 17605.0564 | 10.9416 | 132 | 9.9008e-05 | 1668 | 8.1704 | 2665 | 0.00074696 | 0.098599 | 2678 | 94.05 | 28
262 | ROB ROY 21055090 | 83692105 | ROB ROY 2105 | 5090 | FALSE | 34218.6566 | 34218.6566 | 21.267 | 245 | 0.00010692 | 1476 | 6.8561 | 2689 | 0.00074249 | 0.18191 | 2679 | 1.26 | 691
459 | HARTLEY 1102824 | 43211102 | HARTLEY 1102 | 824 | TRUE | 12575.4803 | 137.5107 | 0.085463 | 103 | 0.00010133 | 1619 | 3.4457 | 2797 | 0.00072721 | 0.074902 | 2680 |  | 2674
3196 | SPRING GAP 17029280 | 162831702 | SPRING GAP 1702 | 9280 | FALSE | 10262.6071 | 10262.6071 | 6.3783 | 80 | 8.3881e-05 | 2098 | 8.09 | 2668 | 0.00072124 | 0.057699 | 2681 | 2.82 | 577
1359 | CAMP EVERS 210311056 | 83622103 | CAMP EVERS 2103 | 11056 | FALSE | 6785.5939 | 6717.0632 | 4.1747 | 48 | 0.00016442 | 592 | 4.026 | 2778 | 0.00071991 | 0.034556 | 2682 | 0.3 | 1011
2485 | EEL RIVER 1102530 | 192381102 | EEL RIVER 1102 | 530 | TRUE | 43254.3781 | 117.5277 | 0.073044 | 255 | 0.00014869 | 756 | 5.1756 | 2744 | 0.00070447 | 0.17964 | 2683 | 0.02 | 2508
6651 | PINECREST 04011818 | 163160401 | PINECREST 0401 | 1818 | FALSE | 5027.483 | 4942.4923 | 3.0718 | 26 | 4.1e-05 | 3243 | 14.3865 | 2542 | 0.00069935 | 0.018183 | 2684 | 0.72 | 799
413 | BRUNSWICK 11062796 | 152481106 | BRUNSWICK 1106 | 2796 | FALSE | 31981.5846 | 31981.5846 | 19.8767 | 253 | 0.00012583 | 1081 | 6.8299 | 2691 | 0.00069507 | 0.17585 | 2685 | 44.5 | 159
4105 | CAMP EVERS 210410442 | 83622104 | CAMP EVERS 2104 | 10442 | FALSE | 16579.0287 | 9105.2092 | 5.6589 | 133 | 0.00016483 | 589 | 3.6401 | 2786 | 0.00069444 | 0.092361 | 2686 | 0.29 | 1027
2116 | LUCERNE 1106CB | 43351106 | LUCERNE 1106 | CB | FALSE | 5806.4035 | 3043.2971 | 1.8914 | 48 | 0.00014993 | 737 | 3.6937 | 2784 | 0.00069407 | 0.033315 | 2687 | 0.04 | 2177
10094 | HARRIS 1109237791 | 192431109 | HARRIS 1109 | 237791 | FALSE | 3420.2949 | 2280.4467 | 1.4173 | 23 | 0.0001987 | 399 | 3.165 | 2804 | 0.00069283 | 0.015935 | 2688 |  | 3489
9596 | BRUNSWICK 1104285704 | 152481104 | BRUNSWICK 1104 | 285704 | FALSE | 1923.7717 | 1685.8276 | 1.0477 | 17 | 0.00023236 | 275 | 9.8522 | 2626 | 0.00068515 | 0.011648 | 2689 |  | 3385
591 | MIWUK 170110600 | 163661701 | MIWUK 1701 | 10600 | FALSE | 21367.0688 | 21367.0688 | 13.2797 | 161 | 7.3663e-05 | 2371 | 8.335 | 2662 | 0.000683 | 0.10996 | 2690 | 276.94 | 1
7040 | PAUL SWEET 2106428102 | 83252106 | PAUL SWEET 2106 | 428102 | FALSE | 20879.8446 | 19729.9421 | 12.2622 | 158 | 0.00012781 | 1053 | 4.9782 | 2755 | 0.00068264 | 0.10786 | 2691 | 0.55 | 866
9535 | HOLLISTER 2105480430 | 182492105 | HOLLISTER 2105 | 480430 | FALSE | 8153.37 | 1450.1348 | 0.90126 | 39 | 5.7435e-05 | 2851 | 18.7653 | 2463 | 0.00068138 | 0.026574 | 2692 |  | 3372
751 | GUALALA 1112662 | 42841112 | GUALALA 1112 | 662 | FALSE | 13657.9642 | 10019.7655 | 6.2273 | 104 | 6.0639e-05 | 2758 | 8.9744 | 2644 | 0.00067921 | 0.070638 | 2693 | 0.07 | 1724
9192 | PURISIMA 110154728 | 182971101 | PURISIMA 1101 | 54728 | FALSE | 7898.4984 | 1667.872 | 1.0366 | 37 | 3.3775e-05 | 3371 | 43.321 | 2256 | 0.00066262 | 0.024517 | 2694 | 0.79 | 775
6603 | MIRABEL 11027347 | 42091102 | MIRABEL 1102 | 7347 | FALSE | 1315.3758 | 1315.3758 | 0.81751 | 10 | 0.00013644 | 913 | 4.8202 | 2760 | 0.00065864 | 0.0065864 | 2695 | 43.48 | 167
6890 | CHALLENGE 110113026 | 103201101 | CHALLENGE 1101 | 13026 | FALSE | 12912.9615 | 12912.9615 | 8.0255 | 70 | 4.9241e-05 | 3058 | 11.6076 | 2595 | 0.00065269 | 0.045688 | 2696 | 8.38 | 429
4651 | PACIFICA 1102320094 | 22811102 | PACIFICA 1102 | 320094 | TRUE | 1539.8883 | 440.0576 | 0.2735 | 11 | 3.4565e-05 | 3360 | 25.2958 | 2389 | 0.00064788 | 0.0071266 | 2697 |  | 2907
7773 | MONTE RIO 111215401 | 42811112 | MONTE RIO 1112 | 15401 | FALSE | 1388.1732 | 1388.1732 | 0.86276 | 11 | 0.00019479 | 418 | 6.5489 | 2694 | 0.00064146 | 0.0070561 | 2698 | 41.15 | 179
8375 | MONTE RIO 1111256 | 42811111 | MONTE RIO 1111 | 256 | FALSE | 2415.6319 | 2415.6319 | 1.5013 | 17 | 0.00023971 | 247 | 1.4646 | 2867 | 0.00063627 | 0.010817 | 2699 | 24.25 | 279
6923 | OLEMA 1101758594 | 42291101 | OLEMA 1101 | 758594 | FALSE | 3264.6914 | 1943.4938 | 1.2079 | 21 | 0.00012955 | 1018 | 6.1576 | 2711 | 0.00062774 | 0.013182 | 2700 |  | 3075
10215 | IGNACIO 11011779 | 42481101 | IGNACIO 1101 | 1779 | TRUE | 677.0293 | 540.9099 | 0.33618 | 5 | 6.6577e-05 | 2570 | 9.5735 | 2633 | 0.00062625 | 0.0031313 | 2701 |  | 3516
4571 | TEMPLETON 2113A30 | 183052113 | TEMPLETON 2113 | A30 | TRUE | 2568.419 | 401.1046 | 0.24929 | 25 | 5.8029e-05 | 2834 | 6.399 | 2699 | 0.00062089 | 0.015522 | 2702 | 0.02 | 2500
5501 | FORT BRAGG A 11013100 | 42761101 | FORT BRAGG A 1101 | 3100 | FALSE | 23694.1727 | 19636.3272 | 12.2041 | 198 | 6.4544e-05 | 2625 | 14.9697 | 2532 | 0.00061511 | 0.12179 | 2703 | 0.06 | 1863
7330 | HAMILTON BRANCH 110190334 | 102361101 | HAMILTON BRANCH 1101 | 90334 | FALSE | 5394.0455 | 5394.0455 | 3.3524 | 44 | 3.2303e-05 | 3396 | 20.5875 | 2442 | 0.00061497 | 0.027059 | 2704 | 11.09 | 388
3053 | HIGGINS 11032194 | 152691103 | HIGGINS 1103 | 2194 | FALSE | 4329.2096 | 2142.6429 | 1.3317 | 36 | 0.00018519 | 470 | 3.3664 | 2801 | 0.00060703 | 0.021853 | 2705 | 1.88 | 634
9597 | MORGAN HILL 2105XR602 | 83242105 | MORGAN HILL 2105 | XR602 | TRUE | 1368.2778 | 391.3667 | 0.24324 | 13 | 8.4195e-05 | 2086 | 9.8269 | 2627 | 0.00060529 | 0.0078688 | 2706 | 0.03 | 2240
5378 | DIAMOND SPRINGS 1105CB | 152261105 | DIAMOND SPRINGS 1105 | CB | FALSE | 7588.8389 | 3330.3293 | 2.0698 | 47 | 0.0003055 | 125 | 1.7499 | 2851 | 0.00059825 | 0.028118 | 2707 | 0.99 | 735
1437 | HORSESHOE 110450142 | 152571104 | HORSESHOE 1104 | 50142 | FALSE | 6580.4447 | 3596.2025 | 2.2351 | 55 | 0.00011566 | 1280 | 5.2494 | 2740 | 0.00059558 | 0.032757 | 2708 | 2.21 | 618
4026 | MIRABEL 1101CB | 42091101 | MIRABEL 1101 | CB | TRUE | 8192.7885 | 792.3448 | 0.49245 | 70 | 0.00016303 | 612 | 5.4892 | 2729 | 0.00059471 | 0.04163 | 2709 | 0.06 | 1815
7798 | LOS GATOS 110712041 | 82021107 | LOS GATOS 1107 | 12041 | FALSE | 10143.7851 | 10143.7851 | 6.3044 | 65 | 0.00013198 | 985 | 5.1866 | 2743 | 0.00059297 | 0.038543 | 2710 | 30.78 | 234
1553 | MEADOW LANE 2106C558R | 14302106 | MEADOW LANE 2106 | C558R | FALSE | 23093.6755 | 1942.5032 | 1.2073 | 180 | 4.7416e-05 | 3106 | 10.0864 | 2623 | 0.00059158 | 0.10648 | 2711 | 12.02 | 377
380 | STANISLAUS 17021804 | 162821702 | STANISLAUS 1702 | 1804 | FALSE | 13482.9013 | 13482.9013 | 8.3797 | 118 | 0.00010094 | 1626 | 6.3117 | 2706 | 0.00058985 | 0.069602 | 2712 | 106.77 | 17
10645 | DIAMOND SPRINGS 1103635040 | 152261103 | DIAMOND SPRINGS 1103 | 635040 | TRUE | 340.9559 | 324.181 | 0.20148 | 2 | 9.5316e-05 | 1752 | 11.9488 | 2590 | 0.0005888 | 0.0011776 | 2713 |  | 3585
7077 | CORONA 1103776806 | 43491103 | CORONA 1103 | 776806 | TRUE | 1634.4876 | 412.4097 | 0.25631 | 15 | 4.0998e-05 | 3244 | 13.7861 | 2555 | 0.00058477 | 0.0087716 | 2714 |  | 3094
4432 | BRUNSWICK 11053611 | 152481105 | BRUNSWICK 1105 | 3611 | FALSE | 2597.3823 | 2597.3823 | 1.6143 | 23 | 5.2349e-05 | 2984 | 11.435 | 2598 | 0.00057745 | 0.013281 | 2715 | 32.3 | 226
5741 | HICKS 2101XR250 | 83432101 | HICKS 2101 | XR250 | TRUE | 9406.4624 | 0 | 0 | 80 | 6.5499e-05 | 2601 | 5.0345 | 2750 | 0.00057262 | 0.04581 | 2716 | 4.1 | 527
8362 | CASTRO VALLEY 1111CB | 14091111 | CASTRO VALLEY 1111 | CB | TRUE | 1304.8232 | 357.3361 | 0.22209 | 16 | 7.3542e-05 | 2381 | 5.012 | 2752 | 0.00057058 | 0.0091293 | 2717 |  | 3215
4792 | HALF MOON BAY 1102CB | 24101102 | HALF MOON BAY 1102 | CB | TRUE | 5451.3154 | 266.9695 | 0.16592 | 50 | 3.1382e-05 | 3410 | 8.3028 | 2663 | 0.0005603 | 0.028015 | 2718 | 0.02 | 2459
2151 | MIWUK 170153038 | 163661701 | MIWUK 1701 | 53038 | FALSE | 10729.3555 | 10729.3555 | 6.6683 | 62 | 6.9809e-05 | 2481 | 8.8864 | 2645 | 0.00055181 | 0.034212 | 2719 | 0.63 | 833
5668 | ALLEGHANY 1101978 | 152101101 | ALLEGHANY 1101 | 978 | FALSE | 47571.501 | 22458.2021 | 13.9579 | 130 | 3.6377e-05 | 3326 | 24.8644 | 2391 | 0.00055148 | 0.071692 | 2720 | 0.07 | 1680
6116 | IGNACIO 1105908 | 42481105 | IGNACIO 1105 | 908 | FALSE | 3616.7994 | 1126.3756 | 0.70005 | 42 | 6.1442e-05 | 2737 | 3.4612 | 2796 | 0.00055062 | 0.023126 | 2721 |  | 3005
2452 | OAKHURST 1103719490 | 254421103 | OAKHURST 1103 | 719490 | FALSE | 4856.6254 | 4856.6254 | 3.0184 | 44 | 6.7665e-05 | 2542 | 6.5472 | 2695 | 0.00054847 | 0.024132 | 2722 |  | 2777
1532 | HAMILTON BRANCH 1101CB | 102361101 | HAMILTON BRANCH 1101 | CB | FALSE | 5887.1186 | 3755.8808 | 2.3343 | 56 | 5.471e-05 | 2926 | 5.5819 | 2728 | 0.00054657 | 0.030608 | 2723 | 0.07 | 1682
8732 | EL CERRITO G 1112418480 | 12501112 | EL CERRITO G 1112 | 418480 | FALSE | 1216.9885 | 1216.9885 | 0.75636 | 13 | 0.00010549 | 1506 | 5.5937 | 2726 | 0.0005464 | 0.0071032 | 2724 |  | 3256
4263 | HALF MOON BAY 11038894 | 24101103 | HALF MOON BAY 1103 | 8894 | FALSE | 18146.6988 | 18102.2842 | 11.2506 | 110 | 0.00011302 | 1343 | 4.8209 | 2759 | 0.00053494 | 0.058844 | 2725 | 5.41 | 487
4900 | CHESTER 11022564 | 103181102 | CHESTER 1102 | 2564 | FALSE | 3603.0114 | 3598.4394 | 2.2364 | 21 | 3.9721e-05 | 3274 | 12.5176 | 2577 | 0.00053291 | 0.011191 | 2726 | 0.1 | 1482
1003 | SANTA ROSA A 1111CB | 42151111 | SANTA ROSA A 1111 | CB | TRUE | 9060.4473 | 490.8425 | 0.30506 | 88 | 4.3627e-05 | 3197 | 6.3791 | 2701 | 0.00052634 | 0.046318 | 2727 |  | 2703
8503 | SAN RAFAEL 11071276 | 42011107 | SAN RAFAEL 1107 | 1276 | FALSE | 6144.8964 | 6012.4282 | 3.7367 | 56 | 0.00018947 | 444 | 3.4619 | 2795 | 0.00052522 | 0.029412 | 2728 | 0.53 | 884
6580 | MIWUK 170247143 | 163661702 | MIWUK 1702 | 47143 | FALSE | 7882.6346 | 7882.6346 | 4.8991 | 67 | 0.00016052 | 638 | 2.9032 | 2815 | 0.00052216 | 0.034985 | 2729 | 0.63 | 837
4101 | LAURELES 1112562376 | 182371112 | LAURELES 1112 | 562376 | FALSE | 12962.1789 | 12746.1039 | 7.9218 | 82 | 6.0914e-05 | 2752 | 14.0412 | 2548 | 0.00052151 | 0.042763 | 2730 |  | 2872
5934 | FITCH MOUNTAIN 1113154 | 42751113 | FITCH MOUNTAIN 1113 | 154 | TRUE | 15159.6857 | 20.5741 | 0.012787 | 108 | 0.00013977 | 871 | 1.0919 | 2887 | 0.00051973 | 0.056131 | 2731 | 0.03 | 2260
5473 | EL DORADO PH 2102CB | 152762102 | EL DORADO PH 2102 | CB | FALSE | 8918.2943 | 8918.2943 | 5.5428 | 46 | 0.00023568 | 259 | 2.1334 | 2835 | 0.00051722 | 0.023792 | 2732 | 44.97 | 153
4174 | CAMP EVERS 210610718 | 83622106 | CAMP EVERS 2106 | 10718 | FALSE | 13624.5702 | 13624.5702 | 8.4677 | 98 | 0.00029137 | 138 | 2.007 | 2842 | 0.0005122 | 0.050195 | 2733 | 0.58 | 858
4155 | BRUNSWICK 110532536 | 152481105 | BRUNSWICK 1105 | 32536 | FALSE | 17537.3204 | 17537.3204 | 10.8995 | 144 | 0.00010307 | 1568 | 6.8331 | 2690 | 0.00050182 | 0.072262 | 2734 | 126.24 | 9
4857 | SEACLIFF 040112946 | 83500401 | SEACLIFF 0401 | 12946 | FALSE | 5267.6978 | 3912.0696 | 2.4314 | 41 | 7.1582e-05 | 2431 | 5.8607 | 2717 | 0.00050028 | 0.020511 | 2735 | 0.3 | 1016
3888 | PUEBLO 1105716 | 43291105 | PUEBLO 1105 | 716 | TRUE | 14760.549 | 161.153 | 0.10016 | 124 | 5.8731e-05 | 2814 | 7.5935 | 2676 | 0.00049954 | 0.061943 | 2736 | 0.53 | 880
6409 | MIWUK 1702S2247 | 163661702 | MIWUK 1702 | S2247 | FALSE | 2394.0014 | 2394.0014 | 1.4879 | 21 | 7.5118e-05 | 2331 | 9.1225 | 2641 | 0.00049228 | 0.010338 | 2737 | 96.94 | 23
9855 | DUNLAP 1102778286 | 254061102 | DUNLAP 1102 | 778286 | FALSE | 4188.0047 | 4188.0047 | 2.6029 | 5 | 3.6444e-05 | 3323 | 19.0779 | 2461 | 0.0004909 | 0.0024545 | 2738 | 0 | 2637
9129 | ROSSMOOR 1102457174 | 14161102 | ROSSMOOR 1102 | 457174 | TRUE | 1940.6507 | 925.5451 | 0.57523 | 14 | 0.00011583 | 1277 | 1.7636 | 2850 | 0.00048348 | 0.0067687 | 2739 |  | 3313
8205 | ATASCADERO 1102825520 | 182541102 | ATASCADERO 1102 | 825520 | FALSE | 2407.6531 | 1896.9242 | 1.1789 | 21 | 4.6815e-05 | 3116 | 8.3859 | 2659 | 0.00047064 | 0.0098834 | 2740 |  | 3202
2233 | IGNACIO 11011264 | 42481101 | IGNACIO 1101 | 1264 | FALSE | 5420.1776 | 3078.9362 | 1.9136 | 50 | 5.6664e-05 | 2869 | 10.5255 | 2619 | 0.00046357 | 0.023178 | 2741 | 0.61 | 847
4702 | BURNEY 110145984 | 103311101 | BURNEY 1101 | 45984 | FALSE | 7772.9197 | 7772.9197 | 4.8309 | 68 | 5.7852e-05 | 2840 | 4.9585 | 2756 | 0.00046238 | 0.031442 | 2742 | 0.06 | 1809
911 | PEORIA 170590374 | 163781705 | PEORIA 1705 | 90374 | FALSE | 7135.3675 | 6578.4615 | 4.0885 | 48 | 9.4382e-05 | 1784 | 3.531 | 2791 | 0.0004592 | 0.022042 | 2743 | 0.06 | 1794
4097 | SILVERADO 2103CB | 43432103 | SILVERADO 2103 | CB | TRUE | 22820.5615 | 0 | 0 | 197 | 8.4141e-05 | 2089 | 3.1167 | 2806 | 0.00045724 | 0.090077 | 2744 | 43.8 | 164
5992 | MIWUK 17029270 | 163661702 | MIWUK 1702 | 9270 | FALSE | 9370.6933 | 9370.6933 | 5.8239 | 68 | 0.00011547 | 1288 | 6.0072 | 2714 | 0.00045602 | 0.03101 | 2745 | 40.93 | 182
9472 | LLAGAS 2105XR234 | 83182105 | LLAGAS 2105 | XR234 | TRUE | 1908.9722 | 4.1246 | 0.0025635 | 26 | 4.1932e-05 | 3226 | 7.3799 | 2680 | 0.00045563 | 0.011846 | 2746 | 0.03 | 2236
6378 | WOODACRE 11011238 | 43021101 | WOODACRE 1101 | 1238 | FALSE | 5923.8162 | 5923.8162 | 3.6817 | 30 | 0.00026272 | 189 | 9.5821 | 2630 | 0.0004533 | 0.013599 | 2747 | 62.35 | 85
1227 | MORAGA 110381146 | 13801103 | MORAGA 1103 | 81146 | FALSE | 9033.4152 | 1226.8593 | 0.7625 | 79 | 7.3782e-05 | 2366 | 10.282 | 2621 | 0.00045161 | 0.035677 | 2748 | 0.03 | 2350
2519 | CAMPHORA 110122412 | 182071101 | CAMPHORA 1101 | 22412 | FALSE | 24417.5389 | 3680.7169 | 2.2876 | 130 | 3.6957e-05 | 3316 | 12.5116 | 2579 | 0.0004496 | 0.058447 | 2749 |  | 2781
2793 | CAMP EVERS 21065302 | 83622106 | CAMP EVERS 2106 | 5302 | FALSE | 9546.4932 | 9546.4932 | 5.9332 | 57 | 0.00026232 | 191 | 2.1517 | 2833 | 0.00044854 | 0.025567 | 2750 | 1.02 | 727
5402 | PACIFICA 1101CB | 22811101 | PACIFICA 1101 | CB | TRUE | 4340.9857 | 216.2085 | 0.13437 | 38 | 4.6882e-05 | 3115 | 6.7721 | 2692 | 0.00044808 | 0.017027 | 2751 | 8.14 | 434
6879 | SEACLIFF 0401CB | 83500401 | SEACLIFF 0401 | CB | FALSE | 9677.833 | 9246.0032 | 5.7464 | 73 | 0.00012957 | 1017 | 4.2973 | 2773 | 0.00044728 | 0.032652 | 2752 | 0.53 | 879
5244 | DUNBAR 1103440 | 43071103 | DUNBAR 1103 | 440 | FALSE | 19525.153 | 3309.7658 | 2.057 | 158 | 8.4963e-05 | 2062 | 3.5276 | 2792 | 0.00044177 | 0.0698 | 2753 | 0.17 | 1237
4679 | ROB ROY 210412596 | 83692104 | ROB ROY 2104 | 12596 | FALSE | 17025.8657 | 12925.0786 | 8.033 | 140 | 8.8891e-05 | 1955 | 5.6622 | 2721 | 0.00043371 | 0.060719 | 2754 | 0.06 | 1804
4037 | EL DORADO PH 21019759 | 152762101 | EL DORADO PH 2101 | 9759 | FALSE | 4110.5786 | 4110.5786 | 2.5547 | 32 | 0.00015886 | 653 | 4.5245 | 2765 | 0.00043106 | 0.013794 | 2755 |  | 2867
909 | TULE POWER HOUSE 1101CB | 258591101 | TULE POWER HOUSE 1101 | CB | FALSE | 6570.8 | 6570.8 | 4.0838 | 11 | 6.9646e-05 | 2484 | 248.9538 | 1542 | 0.00042329 | 0.0046561 | 2756 | 0.02 | 2523
7552 | WEST POINT 1101L2219 | 163201101 | WEST POINT 1101 | L2219 | FALSE | 5447.1163 | 5447.1163 | 3.3854 | 41 | 7.2244e-05 | 2411 | 7.0237 | 2687 | 0.00042266 | 0.017329 | 2757 | 49.71 | 121
3464 | SERRAMONTE 110412705 | 22861104 | SERRAMONTE 1104 | 12705 | TRUE | 9361.8686 | 0 | 0 | 74 | 2.2116e-05 | 3518 | 9.0486 | 2643 | 0.00042265 | 0.031276 | 2758 |  | 2827
7216 | BIG RIVER 110169032 | 43081101 | BIG RIVER 1101 | 69032 | FALSE | 13655.5842 | 13655.5842 | 8.487 | 101 | 8.8998e-05 | 1949 | 4.7713 | 2762 | 0.00041877 | 0.042296 | 2759 | 0.08 | 1653
2590 | WOODSIDE 1104520832 | 24251104 | WOODSIDE 1104 | 520832 | FALSE | 12960.7664 | 9719.2853 | 6.0406 | 90 | 0.00014149 | 844 | 3.7624 | 2781 | 0.00040636 | 0.036573 | 2760 |  | 2787
8755 | HALF MOON BAY 1101903182 | 24101101 | HALF MOON BAY 1101 | 903182 | FALSE | 1770.3755 | 1052.7078 | 0.65426 | 15 | 5.4676e-05 | 2927 | 4.2832 | 2774 | 0.00040533 | 0.0060799 | 2761 |  | 3258
4732 | BIG RIVER 11011286 | 43081101 | BIG RIVER 1101 | 1286 | FALSE | 12241.8563 | 7682.9666 | 4.775 | 92 | 6.6713e-05 | 2563 | 5.3157 | 2739 | 0.00040112 | 0.036903 | 2762 | 0.07 | 1737
3369 | ORO FINO 110276008 | 103031102 | ORO FINO 1102 | 76008 | FALSE | 25670.8015 | 25670.8015 | 15.9545 | 170 | 9.3618e-05 | 1806 | 4.261 | 2775 | 0.000401 | 0.068169 | 2763 | 96.79 | 24
9255 | LAS GALLINAS A 1106228906 | 42991106 | LAS GALLINAS A 1106 | 228906 | TRUE | 2215.3527 | 988.5949 | 0.61442 | 21 | 3.9761e-05 | 3273 | 5.3472 | 2734 | 0.00039716 | 0.0083403 | 2764 |  | 3330
2888 | FOOTHILL 110299432 | 182951102 | FOOTHILL 1102 | 99432 | FALSE | 13966.781 | 2359.0159 | 1.4661 | 115 | 2.7226e-05 | 3470 | 10.878 | 2612 | 0.00039549 | 0.045481 | 2765 | 0.07 | 1745
7168 | STANISLAUS 17024905 | 162821702 | STANISLAUS 1702 | 4905 | FALSE | 3704.1382 | 3704.1382 | 2.3021 | 35 | 8.1261e-05 | 2174 | 6.1793 | 2710 | 0.00038885 | 0.01361 | 2766 | 65.75 | 75
4177 | LOS GATOS 110760092 | 82021107 | LOS GATOS 1107 | 60092 | FALSE | 15629.1336 | 15629.1336 | 9.7136 | 108 | 0.00019731 | 408 | 2.9279 | 2813 | 0.00038814 | 0.041919 | 2767 | 0.39 | 951
9726 | SALT SPRINGS 21028442 | 163692102 | SALT SPRINGS 2102 | 8442 | FALSE | 19428.9727 | 19428.9727 | 12.0752 | 50 | 6.3912e-05 | 2650 | 8.1497 | 2666 | 0.00038233 | 0.019117 | 2768 | 0.11 | 1438
1168 | SAN RAFAEL 11081210 | 42011108 | SAN RAFAEL 1108 | 1210 | FALSE | 8832.2253 | 5252.6146 | 3.2645 | 73 | 0.00023323 | 270 | 1.6941 | 2853 | 0.00038163 | 0.027859 | 2769 | 0.29 | 1025
9856 | PUEBLO 1105419634 | 43291105 | PUEBLO 1105 | 419634 | TRUE | 1981.0133 | 165.107 | 0.10261 | 14 | 7.8094e-05 | 2255 | 6.2924 | 2707 | 0.00037832 | 0.0052965 | 2770 |  | 3436
1493 | SAN RAMON 2107CB | 14232107 | SAN RAMON 2107 | CB | TRUE | 14648.5405 | 486.1753 | 0.30216 | 107 | 1.7992e-05 | 3560 | 4.7299 | 2764 | 0.00037788 | 0.040433 | 2771 | 0.25 | 1087
531 | SAN RAFAEL 1109418 | 42011109 | SAN RAFAEL 1109 | 418 | FALSE | 19645.0637 | 8262.136 | 5.135 | 130 | 5.7927e-05 | 2837 | 5.0022 | 2753 | 0.00037742 | 0.049065 | 2772 | 0.06 | 1897
10509 | PAUL SWEET 2102337544 | 83252102 | PAUL SWEET 2102 | 337544 | TRUE | 1419.0103 | 579.0642 | 0.35989 | 13 | 0.00011348 | 1333 | 3.7153 | 2783 | 0.00037689 | 0.0048996 | 2773 |  | 3561
910 | DUNLAP 11027050 | 254061102 | DUNLAP 1102 | 7050 | FALSE | 15143.783 | 15143.783 | 9.4119 | 67 | 3.0197e-05 | 3425 | 13.5475 | 2562 | 0.0003702 | 0.024804 | 2774 | 0 | 2642
3656 | HALF MOON BAY 11038089 | 24101103 | HALF MOON BAY 1103 | 8089 | FALSE | 4528.4761 | 4528.4761 | 2.8145 | 29 | 0.00010867 | 1432 | 3.3453 | 2802 | 0.00036614 | 0.010618 | 2775 | 4.59 | 513
6207 | CAMP EVERS 210584166 | 83622105 | CAMP EVERS 2105 | 84166 | FALSE | 13898.1694 | 13231.1785 | 8.2232 | 97 | 0.0002829 | 150 | 1.5368 | 2863 | 0.00036427 | 0.035334 | 2776 |  | 3013
6326 | OLEMA 11011252 | 42291101 | OLEMA 1101 | 1252 | FALSE | 6608.6355 | 6608.6355 | 4.1073 | 50 | 0.00013383 | 946 | 3.8677 | 2780 | 0.00036141 | 0.018071 | 2777 | 11.02 | 391
872 | FAIRVIEW 2207M501R | 13432207 | FAIRVIEW 2207 | M501R | FALSE | 7503.1067 | 4016.4433 | 2.4962 | 60 | 4.6793e-05 | 3118 | 3.6463 | 2785 | 0.00035751 | 0.021451 | 2778 | 0.03 | 2319
6151 | EDENVALE 2113CB | 82952113 | EDENVALE 2113 | CB | TRUE | 2357.516 | 24.568 | 0.015269 | 24 | 1.8797e-05 | 3556 | 2.0509 | 2838 | 0.00035038 | 0.0084091 | 2779 |  | 3009
6316 | BIG RIVER 11011052 | 43081101 | BIG RIVER 1101 | 1052 | FALSE | 6204.8696 | 5356.147 | 3.3289 | 49 | 5.6569e-05 | 2870 | 5.2348 | 2741 | 0.00034866 | 0.017084 | 2780 | 0.08 | 1629
4831 | ROB ROY 2105CB | 83692105 | ROB ROY 2105 | CB | FALSE | 2115.1186 | 1181.1241 | 0.73407 | 17 | 7.5667e-05 | 2317 | 2.8608 | 2817 | 0.00034683 | 0.0058961 | 2781 | 0.04 | 2077
5876 | OAKLAND X 1106CR020 | 12541106 | OAKLAND X 1106 | CR020 | FALSE | 3932.8974 | 3932.8974 | 2.4443 | 15 | 9.3739e-05 | 1801 | 4.8237 | 2758 | 0.00034485 | 0.0051727 | 2782 | 41.15 | 180
8254 | DOLAN ROAD 1101857972 | 182381101 | DOLAN ROAD 1101 | 857972 | FALSE | 2082.0425 | 1672.4824 | 1.0395 | 18 | 4.6793e-05 | 3119 | 6.2207 | 2708 | 0.00034064 | 0.0061316 | 2783 |  | 3208
7697 | PARADISE 1103143744 | 102831103 | PARADISE 1103 | 143744 | FALSE | 1706.1115 | 1706.1115 | 1.0604 | 13 | 0.00045932 | 45 | 1.8946 | 2847 | 0.00033981 | 0.0044176 | 2784 |  | 3153
4615 | PEORIA 170184318 | 163781701 | PEORIA 1701 | 84318 | FALSE | 16486.0902 | 16486.0902 | 10.2462 | 142 | 8.547e-05 | 2041 | 8.7666 | 2648 | 0.00033804 | 0.048002 | 2785 | 0.05 | 2065
8175 | WEST POINT 1101L1969 | 163201101 | WEST POINT 1101 | L1969 | FALSE | 1768.6139 | 1768.6139 | 1.0992 | 16 | 7.7816e-05 | 2267 | 7.4947 | 2677 | 0.00032448 | 0.0051917 | 2786 | 58.12 | 93
2671 | LOS GATOS 1101LB40 | 82021101 | LOS GATOS 1101 | LB40 | FALSE | 14924.9201 | 13714.1212 | 8.5234 | 131 | 7.571e-05 | 2314 | 4.7844 | 2761 | 0.00032354 | 0.042384 | 2787 | 0.15 | 1298
1669 | SPRING GAP 17029690 | 162831702 | SPRING GAP 1702 | 9690 | FALSE | 27916.5832 | 27916.5832 | 17.3503 | 185 | 4.7987e-05 | 3093 | 9.3188 | 2639 | 0.00031402 | 0.058094 | 2788 | 45.06 | 151
1740 | GUALALA 1111402866 | 42841111 | GUALALA 1111 | 402866 | FALSE | 2560.4032 | 2560.4032 | 1.5913 | 20 | 8.0485e-05 | 2192 | 2.4422 | 2826 | 0.0003137 | 0.0062739 | 2789 | 0.02 | 2566
6457 | ATASCADERO 1103CB | 182541103 | ATASCADERO 1103 | CB | TRUE | 2195.0052 | 304.3324 | 0.18914 | 18 | 7.9462e-05 | 2222 | 3.5853 | 2789 | 0.00031227 | 0.0056208 | 2790 | 1.29 | 688
4913 | SAN LUIS OBISPO 1108CB | 182631108 | SAN LUIS OBISPO 1108 | CB | TRUE | 7402.9758 | 10.2676 | 0.0063814 | 69 | 2.9198e-05 | 3436 | 37.685 | 2292 | 0.00031202 | 0.02153 | 2791 | 1.11 | 716
3199 | EL CERRITO G 1105BR160 | 12501105 | EL CERRITO G 1105 | BR160 | FALSE | 18386.4832 | 13394.711 | 8.3249 | 132 | 6.9198e-05 | 2499 | 3.3682 | 2800 | 0.00031068 | 0.04101 | 2792 | 0.24 | 1104
7182 | EEL RIVER 1102720639 | 192381102 | EEL RIVER 1102 | 720639 | FALSE | 5844.6694 | 2660.7876 | 1.6537 | 25 | 0.00018595 | 468 | 1.9664 | 2846 | 0.0003062 | 0.0076549 | 2793 |  | 3105
6389 | PERRY 1101W10 | 183071101 | PERRY 1101 | W10 | FALSE | 3001.7775 | 2354.9644 | 1.4636 | 29 | 3.4275e-05 | 3364 | 7.1616 | 2684 | 0.00030601 | 0.0088744 | 2794 | 0.04 | 2112
5102 | DEL MONTE 21049096 | 182222104 | DEL MONTE 2104 | 9096 | FALSE | 10649.9386 | 5304.2381 | 3.2966 | 78 | 3.3536e-05 | 3375 | 6.4596 | 2697 | 0.00030601 | 0.023869 | 2795 | 0.04 | 2102
483 | EL CERRITO G 1105CB | 12501105 | EL CERRITO G 1105 | CB | FALSE | 11982.8259 | 11982.8259 | 7.4474 | 97 | 5.9625e-05 | 2786 | 4.4752 | 2768 | 0.00030421 | 0.029509 | 2796 | 0.19 | 1186
8801 | WOODSIDE 1104420146 | 24251104 | WOODSIDE 1104 | 420146 | FALSE | 5058.5239 | 4389.3602 | 2.728 | 43 | 0.00013429 | 940 | 3.382 | 2799 | 0.00030412 | 0.013077 | 2797 |  | 3266
2740 | SUNOL 1101MR650 | 14241101 | SUNOL 1101 | MR650 | FALSE | 4320.1366 | 2086.6412 | 1.2969 | 30 | 3.1219e-05 | 3411 | 6.4702 | 2696 | 0.00029523 | 0.0088568 | 2798 | 0.07 | 1706
1558 | RINCON 1103472 | 43321103 | RINCON 1103 | 472 | FALSE | 7739.1551 | 4930.8208 | 3.0645 | 71 | 9.5789e-05 | 1733 | 2.7474 | 2818 | 0.00029462 | 0.020918 | 2799 | 0.08 | 1630
1849 | FORT BRAGG A 11044690 | 42761104 | FORT BRAGG A 1104 | 4690 | FALSE | 23028.3671 | 18710.8643 | 11.6289 | 161 | 8.9068e-05 | 1944 | 4.3458 | 2772 | 0.00029439 | 0.047396 | 2800 | 0.16 | 1260
1214 | ROB ROY 21055166 | 83692105 | ROB ROY 2105 | 5166 | FALSE | 8840.5786 | 8840.5786 | 5.4945 | 81 | 9.5629e-05 | 1737 | 3.5862 | 2788 | 0.00028991 | 0.023482 | 2801 | 31.21 | 231
6981 | HALF MOON BAY 110148868 | 24101101 | HALF MOON BAY 1101 | 48868 | TRUE | 3010.868 | 0 | 0 | 21 | 2.3959e-05 | 3505 | 3.0775 | 2810 | 0.00028316 | 0.0059463 | 2802 | 0.31 | 997
5899 | VOLTA 11011640 | 102541101 | VOLTA 1101 | 1640 | FALSE | 16804.166 | 16804.166 | 10.4439 | 59 | 7.8829e-05 | 2241 | 5.7047 | 2720 | 0.00028287 | 0.016689 | 2803 | 0.01 | 2569
7108 | RESERVATION ROAD 11023032 | 182731102 | RESERVATION ROAD 1102 | 3032 | FALSE | 15762.9704 | 5799.169 | 3.6042 | 84 | 2.4376e-05 | 3503 | 5.9133 | 2716 | 0.00028141 | 0.023638 | 2804 | 0.03 | 2349
5988 | SPRING GAP 1702693441 | 162831702 | SPRING GAP 1702 | 693441 | FALSE | 6859.835 | 6859.835 | 4.2634 | 59 | 4.9575e-05 | 3046 | 4.4985 | 2767 | 0.00027928 | 0.016478 | 2805 | 0.29 | 1029
5979 | BIG RIVER 11012183 | 43081101 | BIG RIVER 1101 | 2183 | FALSE | 4246.8638 | 4246.8638 | 2.6394 | 33 | 9.4677e-05 | 1774 | 4.3864 | 2771 | 0.00027436 | 0.009054 | 2806 | 0.05 | 2047
760 | BIG RIVER 1101952 | 43081101 | BIG RIVER 1101 | 952 | FALSE | 16341.5936 | 16341.5936 | 10.1564 | 130 | 0.00010228 | 1595 | 2.9907 | 2812 | 0.00027431 | 0.03566 | 2807 | 0.36 | 970
1378 | PARADISE 1105CB | 102831105 | PARADISE 1105 | CB | FALSE | 11616.1021 | 9822.6918 | 6.1048 | 86 | 0.0005458 | 25 | 1.1717 | 2883 | 0.00026897 | 0.023131 | 2808 | 19.78 | 308
4711 | RESEARCH 2102446423 | 14692102 | RESEARCH 2102 | 446423 | FALSE | 2345.7749 | 1135.402 | 0.70566 | 23 | 0.00012326 | 1131 | 2.131 | 2836 | 0.00026534 | 0.0061027 | 2809 |  | 2912
534 | STANISLAUS 170237278 | 162821702 | STANISLAUS 1702 | 37278 | FALSE | 10929.4406 | 10929.4406 | 6.7927 | 99 | 0.00011401 | 1321 | 2.7082 | 2820 | 0.00026318 | 0.026055 | 2810 | 62.81 | 82
956 | PAUL SWEET 2106CB | 83252106 | PAUL SWEET 2106 | CB | FALSE | 18604.4746 | 8502.7441 | 5.2845 | 115 | 8.1074e-05 | 2181 | 1.4421 | 2868 | 0.00025895 | 0.029779 | 2811 | 0.23 | 1110
832 | ROSSMOOR 110168920 | 14161101 | ROSSMOOR 1101 | 68920 | FALSE | 11754.4382 | 10341.5361 | 6.4273 | 91 | 9.0413e-05 | 1900 | 5.0244 | 2751 | 0.0002577 | 0.02345 | 2812 | 0.16 | 1274
5459 | PARADISE 1106CB | 102831106 | PARADISE 1106 | CB | FALSE | 7764.6762 | 7472.667 | 4.6443 | 53 | 0.0005799 | 22 | 0.9633 | 2896 | 0.0002457 | 0.013022 | 2813 | 38.98 | 191
8168 | SAUSALITO 1102410 | 42491102 | SAUSALITO 1102 | 410 | FALSE | 3634.5971 | 2502.9293 | 1.5556 | 28 | 2.4862e-05 | 3498 | 2.3255 | 2830 | 0.00024476 | 0.0068532 | 2814 | 0.06 | 1826
2941 | DIAMOND SPRINGS 1103CB | 152261103 | DIAMOND SPRINGS 1103 | CB | TRUE | 13992.2701 | 885.5612 | 0.55038 | 109 | 0.00021179 | 353 | 2.0247 | 2841 | 0.00024231 | 0.026412 | 2815 | 0.21 | 1152
5531 | MAPLE CREEK 1101CB | 192101101 | MAPLE CREEK 1101 | CB | FALSE | 19709.1046 | 14267.6715 | 8.8674 | 60 | 0.0002127 | 346 | 1.2563 | 2877 | 0.00023784 | 0.01427 | 2816 | 0.11 | 1433
6907 | BRUNSWICK 111063100 | 152481110 | BRUNSWICK 1110 | 63100 | FALSE | 6591.8886 | 6591.8886 | 4.0969 | 55 | 0.00023384 | 266 | 1.3628 | 2873 | 0.00023675 | 0.013021 | 2817 | 5.34 | 490
2877 | MONTE RIO 11111701 | 42811111 | MONTE RIO 1111 | 1701 | FALSE | 2248.9876 | 2248.9876 | 1.3978 | 18 | 9.908e-05 | 1666 | 2.7097 | 2819 | 0.00023556 | 0.0042401 | 2818 | 29.59 | 240
6347 | PACIFICA 11015001 | 22811101 | PACIFICA 1101 | 5001 | TRUE | 2742.1134 | 0 | 0 | 25 | 3.0913e-05 | 3419 | 4.514 | 2766 | 0.00023403 | 0.0058507 | 2819 | 6.31 | 469
1625 | SAN LUIS OBISPO 1105CB | 182631105 | SAN LUIS OBISPO 1105 | CB | TRUE | 5657.7233 | 67.4906 | 0.041946 | 43 | 3.1411e-05 | 3409 | 11.8961 | 2591 | 0.000232 | 0.0099759 | 2820 | 0.04 | 2072
5409 | SAN RAFAEL 1108CB | 42011108 | SAN RAFAEL 1108 | CB | FALSE | 13792.1671 | 9469.8097 | 5.8855 | 102 | 0.00017335 | 539 | 0.99807 | 2891 | 0.00023023 | 0.023483 | 2821 | 0.21 | 1141
8271 | ROSSMOOR 1107857172 | 14161107 | ROSSMOOR 1107 | 857172 | TRUE | 1843.2099 | 152.0386 | 0.094493 | 15 | 8.7874e-05 | 1986 | 3.2284 | 2803 | 0.00022992 | 0.0034488 | 2822 |  | 3212
10147 | WINDSOR 11035060 | 43501103 | WINDSOR 1103 | 5060 | TRUE | 1113.3002 | 291.5638 | 0.18121 | 12 | 7.5643e-05 | 2319 | 1.3951 | 2871 | 0.00022663 | 0.0027196 | 2823 |  | 3502
8566 | CORONA 1103114284 | 43491103 | CORONA 1103 | 114284 | TRUE | 893.7863 | 451.7326 | 0.28075 | 11 | 8.3715e-05 | 2102 | 4.3909 | 2770 | 0.00022547 | 0.0024802 | 2824 |  | 3236
849 | STANISLAUS 170237276 | 162821702 | STANISLAUS 1702 | 37276 | FALSE | 18746.4684 | 18746.4684 | 11.651 | 168 | 0.00010311 | 1567 | 2.0474 | 2839 | 0.00022047 | 0.037039 | 2825 | 88.82 | 33
3868 | HATTON 11012026 | 182291101 | HATTON 1101 | 2026 | FALSE | 16422.8166 | 8438.7955 | 5.2447 | 126 | 4.8317e-05 | 3086 | 5.725 | 2719 | 0.00021753 | 0.027409 | 2826 | 0.07 | 1690
427 | SAUSALITO 1101688590 | 42491101 | SAUSALITO 1101 | 688590 | FALSE | 3500.4301 | 1691.536 | 1.0513 | 32 | 4.9847e-05 | 3041 | 3.0358 | 2811 | 0.00021706 | 0.0069459 | 2827 |  | 2671
4476 | CALISTOGA 1102705 | 42711102 | CALISTOGA 1102 | 705 | TRUE | 2028.0775 | 622.3172 | 0.38677 | 20 | 0.00010699 | 1473 | 4.0264 | 2777 | 0.00021298 | 0.0042596 | 2828 |  | 2895
1205 | MIWUK 17028090 | 163661702 | MIWUK 1702 | 8090 | FALSE | 6501.5338 | 6501.5338 | 4.0407 | 53 | 0.00010162 | 1614 | 1.8606 | 2848 | 0.00021162 | 0.011216 | 2829 | 58.21 | 92
61 | CAMBRIA 1102W50 | 182771102 | CAMBRIA 1102 | W50 | TRUE | 5818.6322 | 997.9458 | 0.62023 | 40 | 1.4796e-05 | 3587 | 16.6866 | 2506 | 0.00021093 | 0.0084371 | 2830 | 0.03 | 2302
189 | BIG RIVER 110179628 | 43081101 | BIG RIVER 1101 | 79628 | FALSE | 23813.9358 | 23813.9358 | 14.8005 | 156 | 7.9122e-05 | 2230 | 2.6556 | 2822 | 0.00021051 | 0.032839 | 2831 | 0.17 | 1233
3166 | ALTO 11251226 | 42031125 | ALTO 1125 | 1226 | FALSE | 12605.0062 | 12282.9745 | 7.6339 | 96 | 0.00012073 | 1171 | 0.80895 | 2902 | 0.00020916 | 0.02008 | 2832 | 1.01 | 728
6809 | OAKLAND D 1112CR192 | 12041112 | OAKLAND D 1112 | CR192 | FALSE | 6810.4625 | 3963.0316 | 2.463 | 54 | 8.0733e-05 | 2188 | 1.3873 | 2872 | 0.00020828 | 0.011247 | 2833 | 0.21 | 1135
4374 | OCEANO 1103V22 | 182601103 | OCEANO 1103 | V22 | TRUE | 810.5999 | 50.4916 | 0.031381 | 14 | 2.0015e-05 | 3542 | 3.4621 | 2794 | 0.00020377 | 0.0028528 | 2834 |  | 2885
9957 | DEL MONTE 21043066 | 182222104 | DEL MONTE 2104 | 3066 | TRUE | 26.0345 | 26.0345 | 0.016181 | 2 | 5.3309e-05 | 2953 | 11.9582 | 2586 | 0.00020359 | 0.00040718 | 2835 | 0.44 | 922
4818 | ROSSMOOR 11018132 | 14161101 | ROSSMOOR 1101 | 8132 | FALSE | 5814.9582 | 4248.014 | 2.6402 | 47 | 9.8938e-05 | 1671 | 2.0883 | 2837 | 0.00020337 | 0.0095582 | 2836 | 0.04 | 2079
2856 | SAN RAFAEL 11071166 | 42011107 | SAN RAFAEL 1107 | 1166 | FALSE | 24234.157 | 20163.1012 | 12.5314 | 213 | 0.00022306 | 307 | 0.8473 | 2900 | 0.00020294 | 0.043227 | 2837 | 1.46 | 673
445 | MONTE RIO 1112CB | 42811112 | MONTE RIO 1112 | CB | FALSE | 5679.6302 | 5679.6302 | 3.5299 | 43 | 0.00015288 | 721 | 0.6192 | 2911 | 0.00020121 | 0.0086519 | 2838 | 23.03 | 289
10280 | SAUSALITO 1102964592 | 42491102 | SAUSALITO 1102 | 964592 | TRUE | 1787.6075 | 941.9387 | 0.58542 | 15 | 2.9092e-05 | 3439 | 9.5689 | 2634 | 0.00019824 | 0.0029736 | 2839 |  | 3528
1145 | OLEMA 11011200 | 42291101 | OLEMA 1101 | 1200 | FALSE | 4658.8808 | 4658.8808 | 2.8955 | 34 | 8.1804e-05 | 2158 | 2.8623 | 2816 | 0.00019566 | 0.0066525 | 2840 | 4.42 | 520
6437 | HAMILTON BRANCH 110153192 | 102361101 | HAMILTON BRANCH 1101 | 53192 | TRUE | 3316.9892 | 889.758 | 0.55299 | 30 | 5.4105e-05 | 2941 | 5.3377 | 2737 | 0.0001937 | 0.0058109 | 2841 |  | 3032
7381 | PACIFICA 1102660408 | 22811102 | PACIFICA 1102 | 660408 | TRUE | 3217.4282 | 570.687 | 0.35468 | 26 | 3.0978e-05 | 3417 | 7.378 | 2681 | 0.00019086 | 0.0049624 | 2842 |  | 3121
5360 | ALHAMBRA 1105CB | 14101105 | ALHAMBRA 1105 | CB | FALSE | 3053.2387 | 1333.5262 | 0.82879 | 33 | 7.2893e-05 | 2396 | 1.9862 | 2843 | 0.00018865 | 0.0062254 | 2843 | 0.02 | 2444
1909 | MORAGA 1104750618 | 13801104 | MORAGA 1104 | 750618 | FALSE | 1583.7149 | 1538.3917 | 0.95612 | 13 | 5.3287e-05 | 2955 | 3.1105 | 2807 | 0.0001837 | 0.002388 | 2844 |  | 2755
7663 | SOBRANTE 1103CB | 14671103 | SOBRANTE 1103 | CB | FALSE | 6937.627 | 6745.77 | 4.1925 | 55 | 9.8691e-05 | 1677 | 3.0905 | 2808 | 0.00018024 | 0.0099135 | 2845 | 0.1 | 1500
4846 | ORINDA 0402402/2 LR | 12350402 | ORINDA 0402 | 402/2 LR | FALSE | 10638.2509 | 10545.4353 | 6.554 | 91 | 0.00012174 | 1151 | 1.633 | 2857 | 0.00017917 | 0.016305 | 2846 |  | 2922
6268 | CURTIS 1702S2123 | 163351702 | CURTIS 1702 | S2123 | FALSE | 2988.9855 | 2988.9855 | 1.8577 | 25 | 0.00012986 | 1010 | 1.9671 | 2845 | 0.00017177 | 0.0042941 | 2847 |  | 3018
1067 | DIAMOND SPRINGS 1106290705 | 152261106 | DIAMOND SPRINGS 1106 | 290705 | FALSE | 5314.0636 | 5193.0778 | 3.2275 | 38 | 0.0001966 | 410 | 2.568 | 2823 | 0.00016712 | 0.0063506 | 2848 |  | 2706
3874 | PARADISE 1105829194 | 102831105 | PARADISE 1105 | 829194 | FALSE | 18124.3826 | 18124.3826 | 11.2644 | 142 | 0.00022979 | 286 | 0.40121 | 2916 | 0.00016422 | 0.023319 | 2849 |  | 2858
1686 | CAMP EVERS 210312990 | 83622103 | CAMP EVERS 2103 | 12990 | FALSE | 21277.9249 | 21277.9249 | 13.2243 | 161 | 0.00018796 | 455 | 1.0994 | 2886 | 0.00016127 | 0.025964 | 2850 | 0.86 | 764
6595 | HIGGINS 110432747 | 152691104 | HIGGINS 1104 | 32747 | FALSE | 2820.8108 | 1047.4929 | 0.65102 | 26 | 0.00014649 | 780 | 1.2825 | 2876 | 0.00016086 | 0.0041824 | 2851 | 1.65 | 658
2910 | HALSEY 110176178 | 152241101 | HALSEY 1101 | 76178 | FALSE | 32532.3048 | 32532.3048 | 20.219 | 248 | 0.00012177 | 1150 | 3.133 | 2805 | 0.00015934 | 0.039517 | 2852 | 0.13 | 1361
2602 | PRUNEDALE 11103716 | 182961110 | PRUNEDALE 1110 | 3716 | TRUE | 21171.7372 | 690.7324 | 0.42929 | 157 | 6.4877e-05 | 2613 | 1.6769 | 2855 | 0.00015488 | 0.024316 | 2853 | 0.03 | 2321
6371 | BAY MEADOWS 210257886 | 24012102 | BAY MEADOWS 2102 | 57886 | FALSE | 8466.0843 | 6549.4745 | 4.0705 | 81 | 8.2619e-05 | 2138 | 0.94597 | 2899 | 0.00015101 | 0.012232 | 2854 | 0.08 | 1619
3718 | TEMPLETON 2108A40 | 183052108 | TEMPLETON 2108 | A40 | FALSE | 20639.8903 | 6084.3101 | 3.7814 | 174 | 4.3444e-05 | 3202 | 1.431 | 2870 | 0.00015079 | 0.026237 | 2855 | 0.03 | 2254
8208 | BRUNSWICK 11038918 | 152481103 | BRUNSWICK 1103 | 8918 | FALSE | 3457.885 | 2431.0442 | 1.5109 | 30 | 0.00022692 | 298 | 2.4426 | 2824 | 0.0001494 | 0.0044819 | 2856 | 2.79 | 579
833 | BRUNSWICK 110456468 | 152481104 | BRUNSWICK 1104 | 56468 | FALSE | 9625.3334 | 8910.5893 | 5.538 | 85 | 0.00022965 | 287 | 1.0912 | 2888 | 0.0001483 | 0.012606 | 2857 | 12.55 | 373
8651 | MORGAN HILL 2111419718 | 83242111 | MORGAN HILL 2111 | 419718 | FALSE | 3649.8042 | 3649.8042 | 2.2684 | 25 | 0.00013422 | 941 | 1.0173 | 2890 | 0.0001469 | 0.0036725 | 2858 |  | 3248
4060 | KONOCTI 11081278 | 43311108 | KONOCTI 1108 | 1278 | FALSE | 12855.1379 | 9099.8598 | 5.6556 | 96 | 9.744e-05 | 1703 | 1.5519 | 2861 | 0.00014529 | 0.013948 | 2859 | 0.05 | 1918
5993 | LAS GALLINAS A 11041220 | 42991104 | LAS GALLINAS A 1104 | 1220 | TRUE | 7829.4679 | 0 | 0 | 57 | 2.5969e-05 | 3488 | 1.1753 | 2882 | 0.00013353 | 0.0076113 | 2860 | 0.03 | 2239
1481 | SOBRANTE 1101CB | 14671101 | SOBRANTE 1101 | CB | FALSE | 24857.1517 | 22896.4557 | 14.2302 | 209 | 9.1121e-05 | 1876 | 1.2034 | 2878 | 0.00012965 | 0.027098 | 2861 | 0.08 | 1613
6330 | CURTIS 170268380 | 163351702 | CURTIS 1702 | 68380 | FALSE | 10711.9675 | 10711.9675 | 6.6575 | 88 | 0.00012793 | 1048 | 2.2263 | 2832 | 0.00012865 | 0.011322 | 2862 | 0.74 | 791
2410 | SAN LEANDRO U 1114MR544 | 13111114 | SAN LEANDRO U 1114 | MR544 | TRUE | 7120.8066 | 27.9821 | 0.017391 | 62 | 9.0189e-06 | 3615 | 1.9811 | 2844 | 0.00012274 | 0.0076101 | 2863 | 0.04 | 2154
5853 | ROB ROY 210410954 | 83692104 | ROB ROY 2104 | 10954 | FALSE | 11428.7483 | 11428.7483 | 7.103 | 90 | 9.1892e-05 | 1847 | 2.4422 | 2825 | 0.00012262 | 0.011036 | 2864 | 0.16 | 1268
4344 | NOVATO 11041282 | 42211104 | NOVATO 1104 | 1282 | TRUE | 5984.1771 | 0 | 0 | 56 | 9.973e-05 | 1654 | 1.1951 | 2881 | 0.00012029 | 0.0067363 | 2865 | 0.03 | 2326
8432 | SNEATH LANE 110715341 | 22721107 | SNEATH LANE 1107 | 15341 | TRUE | 2075.9695 | 391.2765 | 0.24318 | 18 | 3.4322e-05 | 3363 | 5.3372 | 2738 | 0.00011859 | 0.0021346 | 2866 | 0.74 | 792
6986 | RESERVATION ROAD 1102303870 | 182731102 | RESERVATION ROAD 1102 | 303870 | FALSE | 1292.4248 | 1028.4638 | 0.63919 | 7 | 5.3155e-05 | 2962 | 2.3249 | 2831 | 0.0001185 | 0.00082948 | 2867 |  | 3080
4626 | COTATI 1104426 | 42271104 | COTATI 1104 | 426 | FALSE | 6243.6329 | 3219.5011 | 2.0009 | 52 | 5.7367e-05 | 2854 | 1.7424 | 2852 | 0.00011662 | 0.0060642 | 2868 | 0.04 | 2194
8778 | PAUL SWEET 2107774760 | 83252107 | PAUL SWEET 2107 | 774760 | FALSE | 5348.863 | 5348.863 | 3.3243 | 37 | 0.00022083 | 317 | 0.70854 | 2908 | 0.00011197 | 0.0041429 | 2869 |  | 3263
4484 | FROGTOWN 170274648 | 163451702 | FROGTOWN 1702 | 74648 | TRUE | 7581.2034 | 262.1986 | 0.16296 | 63 | 8.4795e-05 | 2069 | 1.0707 | 2889 | 0.00011106 | 0.0069966 | 2870 | 0.42 | 932
6192 | PEORIA 170169124 | 163781701 | PEORIA 1701 | 69124 | FALSE | 4347.2792 | 4347.2792 | 2.7019 | 33 | 8.5315e-05 | 2047 | 1.5063 | 2864 | 0.00010917 | 0.0036026 | 2871 | 0.05 | 2055
8000 | DIAMOND SPRINGS 1107116815 | 152261107 | DIAMOND SPRINGS 1107 | 116815 | FALSE | 4074.4873 | 2540.2857 | 1.5788 | 33 | 0.00019069 | 440 | 1.5062 | 2865 | 0.00010723 | 0.0035385 | 2872 |  | 3182
8610 | HOOPA 110193038 | 192401101 | HOOPA 1101 | 93038 | FALSE | 4552.6155 | 2107.4343 | 1.3098 | 39 | 0.00019968 | 398 | 1.284 | 2875 | 0.00010645 | 0.0041517 | 2873 | 0.03 | 2241
995 | HALF MOON BAY 11022032 | 24101102 | HALF MOON BAY 1102 | 2032 | TRUE | 14427.8487 | 905.5345 | 0.56279 | 103 | 2.5379e-05 | 3492 | 0.98818 | 2894 | 0.0001063 | 0.010949 | 2874 | 0.14 | 1323
7250 | ORINDA 04013442 | 12350401 | ORINDA 0401 | 3442 | FALSE | 8430.8944 | 5599.863 | 3.4803 | 68 | 0.00011662 | 1257 | 0.7637 | 2904 | 0.00010618 | 0.0072205 | 2875 | 0.07 | 1685
367 | ARCATA 112233060 | 192021122 | ARCATA 1122 | 33060 | TRUE | 7941.0149 | 856.2789 | 0.53218 | 64 | 0.00022712 | 296 | 0.31239 | 2924 | 9.9531e-05 | 0.00637 | 2876 | 0.02 | 2560
2545 | FAIRVIEW 2207P148 | 13432207 | FAIRVIEW 2207 | P148 | FALSE | 7362.5215 | 1361.9079 | 0.84643 | 54 | 4.5868e-05 | 3143 | 1.5547 | 2859 | 9.8792e-05 | 0.0053348 | 2877 |  | 2783
5688 | STANISLAUS 170275348 | 162821702 | STANISLAUS 1702 | 75348 | FALSE | 8532.4043 | 8532.4043 | 5.3029 | 77 | 8.3581e-05 | 2110 | 1.3013 | 2874 | 9.5481e-05 | 0.0073521 | 2878 | 79.37 | 49
5946 | SALT SPRINGS 21011232 | 163692101 | SALT SPRINGS 2101 | 1232 | FALSE | 14610.263 | 12420.8061 | 7.7196 | 64 | 4.2772e-05 | 3212 | 1.5493 | 2862 | 9.0864e-05 | 0.0058153 | 2879 | 0.05 | 2007
4735 | ELK 11018779 | 42981101 | ELK 1101 | 8779 | FALSE | 6865.4129 | 6865.4129 | 4.2669 | 41 | 0.00012002 | 1187 | 1.8049 | 2849 | 8.9792e-05 | 0.0036815 | 2880 | 0.05 | 2060
744 | GABILAN 11013034 | 182331101 | GABILAN 1101 | 3034 | TRUE | 31905.8871 | 80.3377 | 0.04993 | 193 | 4.5789e-05 | 3145 | 2.3733 | 2828 | 8.716e-05 | 0.016822 | 2881 | 0.02 | 2481
8975 | SPRING GAP 170286032 | 162831702 | SPRING GAP 1702 | 86032 | FALSE | 4656.0497 | 1615.684 | 1.0042 | 23 | 2.8164e-05 | 3455 | 3.5085 | 2793 | 8.538e-05 | 0.0019637 | 2882 | 0.82 | 770
6252 | CHESTER 1101922138 | 103181101 | CHESTER 1101 | 922138 | FALSE | 3566.848 | 2524.6386 | 1.5691 | 24 | 4.9756e-05 | 3043 | 2.046 | 2840 | 8.4169e-05 | 0.00202 | 2883 |  | 3016
320 | GREEN VALLEY 210112106 | 83192101 | GREEN VALLEY 2101 | 12106 | TRUE | 19539.3367 | 556.8348 | 0.34608 | 139 | 8.3645e-05 | 2105 | 0.75016 | 2905 | 8.0919e-05 | 0.011248 | 2884 | 0.06 | 1840
390 | PETALUMA C 110856774 | 42631108 | PETALUMA C 1108 | 56774 | TRUE | 4425.2807 | 385.0871 | 0.23933 | 39 | 1.6584e-05 | 3572 | 2.9096 | 2814 | 7.8722e-05 | 0.0030702 | 2885 |  | 2668
3580 | SOBRANTE 1102CB | 14671102 | SOBRANTE 1102 | CB | FALSE | 16799.2868 | 16799.2868 | 10.4408 | 132 | 9.6671e-05 | 1719 | 1.6868 | 2854 | 7.4597e-05 | 0.0098468 | 2886 | 0.13 | 1339
5433 | HATTON 110137088 | 182291101 | HATTON 1101 | 37088 | FALSE | 18269.9988 | 11434.4875 | 7.1066 | 135 | 4.8424e-05 | 3080 | 2.354 | 2829 | 7.338e-05 | 0.0099063 | 2887 | 0.04 | 2198
2226 | FORT BRAGG A 11021226 | 42761102 | FORT BRAGG A 1102 | 1226 | FALSE | 12686.9371 | 2717.7424 | 1.6891 | 102 | 7.3175e-05 | 2391 | 0.9972 | 2892 | 7.0366e-05 | 0.0071773 | 2888 | 0.01 | 2602
7611 | DIAMOND SPRINGS 1106279670 | 152261106 | DIAMOND SPRINGS 1106 | 279670 | FALSE | 7840.1687 | 6244.093 | 3.8807 | 54 | 9.3625e-05 | 1805 | 0.35903 | 2923 | 7.0093e-05 | 0.003785 | 2889 |  | 3141
9967 | CRESTA 1101103126 | 102251101 | CRESTA 1101 | 103126 | TRUE | 487.0335 | 487.0335 | 0.30269 | 5 | 0.0010399 | 1 | 0.066432 | 2993 | 6.9083e-05 | 0.00034541 | 2890 |  | 3462
6701 | BRUNSWICK 11064639 | 152481106 | BRUNSWICK 1106 | 4639 | FALSE | 5228.1955 | 5228.1955 | 3.2493 | 44 | 0.00013355 | 950 | 1.1467 | 2885 | 6.7888e-05 | 0.0029871 | 2891 | 1.36 | 680
8130 | LAURELES 111110141 | 182371111 | LAURELES 1111 | 10141 | FALSE | 4694.7775 | 4694.7775 | 2.9178 | 21 | 5.6214e-05 | 2882 | 1.1979 | 2879 | 6.784e-05 | 0.0014246 | 2892 | 4.61 | 512
17 | SAN RAFAEL 1106910 | 42011106 | SAN RAFAEL 1106 | 910 | FALSE | 11465.6942 | 2722.6312 | 1.6921 | 89 | 0.00012024 | 1182 | 0.77728 | 2903 | 6.6955e-05 | 0.005959 | 2893 | 0.04 | 2206
428 | SOBRANTE 1102690098 | 14671102 | SOBRANTE 1102 | 690098 | FALSE | 12079.1397 | 11883.9636 | 7.3859 | 108 | 8.8852e-05 | 1957 | 0.94645 | 2898 | 6.6684e-05 | 0.0072019 | 2894 |  | 2672
6532 | PARADISE 110536656 | 102831105 | PARADISE 1105 | 36656 | TRUE | 1041.7398 | 220.7989 | 0.13723 | 14 | 0.00098372 | 2 | 0.065517 | 3361 | 6.4706e-05 | 0.00090588 | 2895 |  | 3040
1066 | JARVIS 1101MR210 | 13501101 | JARVIS 1101 | MR210 | FALSE | 12199.0798 | 1314.2646 | 0.81682 | 103 | 2.3777e-05 | 3506 | 0.99149 | 2893 | 6.2939e-05 | 0.0064828 | 2896 | 1.94 | 629
5877 | OAKLAND K 1102CR014 | 12101102 | OAKLAND K 1102 | CR014 | FALSE | 16905.8619 | 16905.8619 | 10.5071 | 137 | 0.00013845 | 889 | 0.41497 | 2915 | 6.2366e-05 | 0.0085442 | 2897 | 0.99 | 734
7339 | BIG BASIN 110165444 | 82841101 | BIG BASIN 1101 | 65444 | TRUE | 757.2593 | 757.2593 | 0.47064 | 9 | 0.00091179 | 3 | 0.066431 | 3074 | 6.0572e-05 | 0.00054514 | 2898 | 12.01 | 379
1476 | BOLINAS 1101528 | 42261101 | BOLINAS 1101 | 528 | FALSE | 4980.15 | 2865.7848 | 1.7811 | 46 | 4.0677e-05 | 3254 | 1.441 | 2869 | 5.4065e-05 | 0.002487 | 2899 | 0.21 | 1140
9601 | CAMP EVERS 2104189010 | 83622104 | CAMP EVERS 2104 | 189010 | TRUE | 84.167 | 59.0426 | 0.036695 | 4 | 0.000791 | 5 | 0.065792 | 3268 | 5.2348e-05 | 0.00020939 | 2900 |  | 3386
4401 | SILVERADO 2103507513 | 43432103 | SILVERADO 2103 | 507513 | FALSE | 8339.9553 | 4803.4 | 2.9853 | 65 | 0.00010329 | 1564 | 1.1629 | 2884 | 4.9269e-05 | 0.0032025 | 2901 |  | 2887
625 | ROSSMOOR 1101L503R | 14161101 | ROSSMOOR 1101 | L503R | FALSE | 6910.8038 | 6910.8038 | 4.2951 | 62 | 0.00010589 | 1498 | 0.83292 | 2901 | 4.8731e-05 | 0.0030213 | 2902 | 0.09 | 1547
7021 | DOLAN ROAD 1101590402 | 182381101 | DOLAN ROAD 1101 | 590402 | FALSE | 9614.0154 | 3916.034 | 2.4338 | 78 | 5.9195e-05 | 2800 | 0.67392 | 2910 | 4.8446e-05 | 0.0037788 | 2903 |  | 3086
7515 | PARADISE 1103468200 | 102831103 | PARADISE 1103 | 468200 | TRUE | 531.6801 | 531.6801 | 0.33044 | 4 | 0.00072422 | 6 | 0.066431 | 3033 | 4.8111e-05 | 0.00019244 | 2904 |  | 3132
8899 | NAPA 11025039 | 42021102 | NAPA 1102 | 5039 | TRUE | 4245.0462 | 0 | 0 | 28 | 7.2354e-05 | 2407 | 1.1951 | 2880 | 4.5334e-05 | 0.0012694 | 2905 |  | 3275
10522 | PARADISE 11042486 | 102831104 | PARADISE 1104 | 2486 | TRUE | 189.7916 | 146.4228 | 0.091002 | 2 | 0.00067148 | 8 | 0.065791 | 3270 | 4.4268e-05 | 8.8537e-05 | 2906 |  | 3565
11006 | PARADISE 1105828400 | 102831105 | PARADISE 1105 | 828400 | TRUE | 50.1094 | 50.1094 | 0.031143 | 2 | 0.00066466 | 9 | 0.066431 | 3040 | 4.4154e-05 | 8.8308e-05 | 2907 |  | 3627
10495 | CEDAR CREEK 11011362 | 103321101 | CEDAR CREEK 1101 | 1362 | TRUE | 24.9514 | 24.9514 | 0.015507 | 1 | 0.00065973 | 10 | 0.066431 | 3035 | 4.3827e-05 | 4.3827e-05 | 2908 | 0.04 | 2068
4622 | EL CERRITO G 1105BR194 | 12501105 | EL CERRITO G 1105 | BR194 | FALSE | 8491.9295 | 6148.6965 | 3.8214 | 74 | 6.6442e-05 | 2577 | 0.38709 | 2919 | 4.3185e-05 | 0.0031957 | 2909 | 0.12 | 1386
7319 | PARADISE 11061212 | 102831106 | PARADISE 1106 | 1212 | FALSE | 3248.6095 | 3232.6075 | 2.0091 | 33 | 0.00064007 | 12 | 0.066393 | 3123 | 4.2503e-05 | 0.0014026 | 2910 |  | 3117
10489 | CAMP EVERS 210510996 | 83622105 | CAMP EVERS 2105 | 10996 | FALSE | 1226.2093 | 1226.2093 | 0.76209 | 8 | 0.00063772 | 13 | 0.066431 | 3070 | 4.2365e-05 | 0.00033892 | 2911 | 3.1 | 562
7716 | PARADISE 110599226 | 102831105 | PARADISE 1105 | 99226 | FALSE | 5537.6206 | 1841.8715 | 1.1447 | 42 | 0.00062786 | 15 | 0.065639 | 3326 | 4.1187e-05 | 0.0017299 | 2912 |  | 3154
6446 | FORT BRAGG A 1102956 | 42761102 | FORT BRAGG A 1102 | 956 | FALSE | 19682.0883 | 18278.7267 | 11.3603 | 145 | 8.7665e-05 | 1994 | 0.39404 | 2918 | 4.0908e-05 | 0.0059316 | 2913 | 0.15 | 1277
2257 | BIG TREES 04025300 | 83050402 | BIG TREES 0402 | 5300 | FALSE | 15760.3239 | 15760.3239 | 9.7951 | 115 | 0.00020513 | 380 | 0.27315 | 2925 | 3.9714e-05 | 0.0045672 | 2914 |  | 2767
9775 | CAMP EVERS 210595050 | 83622105 | CAMP EVERS 2105 | 95050 | TRUE | 223.2117 | 223.2117 | 0.13873 | 5 | 0.00059508 | 17 | 0.066431 | 3081 | 3.9532e-05 | 0.00019766 | 2915 | 0.24 | 1092
2020 | DUNLAP 11037170 | 254061103 | DUNLAP 1103 | 7170 | FALSE | 8726.7127 | 8726.7127 | 5.4237 | 54 | 2.872e-05 | 3442 | 2.7066 | 2821 | 3.9493e-05 | 0.0021326 | 2916 | 0 | 2648
9147 | BEN LOMOND 04015400 | 83040401 | BEN LOMOND 0401 | 5400 | TRUE | 731.4241 | 731.4241 | 0.45458 | 4 | 0.00059378 | 18 | 0.066431 | 3083 | 3.9445e-05 | 0.00015778 | 2917 | 0.27 | 1057
2924 | ROB ROY 210538430 | 83692105 | ROB ROY 2105 | 38430 | FALSE | 10237.4777 | 6060.3575 | 3.7665 | 90 | 5.3215e-05 | 2959 | 0.59378 | 2912 | 3.7768e-05 | 0.0033991 | 2918 | 0.19 | 1175
2345 | MORGAN HILL 2106CB | 83242106 | MORGAN HILL 2106 | CB | FALSE | 6247.2514 | 1003.198 | 0.62349 | 47 | 4.8424e-05 | 3081 | 0.73812 | 2907 | 3.5184e-05 | 0.0016536 | 2919 |  | 2772
4552 | SHINGLE SPRINGS 2108449638 | 153652108 | SHINGLE SPRINGS 2108 | 449638 | TRUE | 41.9833 | 41.9833 | 0.026093 | 1 | 0.00016049 | 640 | 0.21903 | 2930 | 3.5151e-05 | 3.5151e-05 | 2920 |  | 2904
2359 | PACIFICA 1101777484 | 22811101 | PACIFICA 1101 | 777484 | FALSE | 5712.0142 | 1455.0408 | 0.90431 | 50 | 1.3219e-05 | 3597 | 5.1374 | 2746 | 3.5066e-05 | 0.0017533 | 2921 |  | 2773
6715 | PARADISE 11032534 | 102831103 | PARADISE 1103 | 2534 | FALSE | 5245.4729 | 5105.9059 | 3.1733 | 49 | 0.00050354 | 30 | 0.066327 | 3143 | 3.3375e-05 | 0.0016354 | 2922 | 0.49 | 899
416 | PACIFICA 1102CB | 22811102 | PACIFICA 1102 | CB | TRUE | 6265.5755 | 560.1275 | 0.34812 | 51 | 1.5294e-05 | 3585 | 1.6186 | 2858 | 3.2507e-05 | 0.0016578 | 2923 | 0.17 | 1234
4774 | PARADISE 11042488 | 102831104 | PARADISE 1104 | 2488 | FALSE | 5690.0714 | 5690.0714 | 3.5364 | 47 | 0.0004856 | 34 | 0.066431 | 3043 | 3.2259e-05 | 0.0015162 | 2924 |  | 2916
10872 | WILLOW CREEK 1103181562 | 192171103 | WILLOW CREEK 1103 | 181562 | TRUE | 4.572 | 4.572 | 0.0028415 | 1 | 0.00048291 | 37 | 0.066432 | 2996 | 3.208e-05 | 3.208e-05 | 2925 |  | 3615
5198 | PARADISE 1104283794 | 102831104 | PARADISE 1104 | 283794 | FALSE | 4034.8507 | 3810.7404 | 2.3684 | 37 | 0.00048267 | 38 | 0.066328 | 3142 | 3.2004e-05 | 0.0011841 | 2926 |  | 2942
2421 | FORT BRAGG A 110235592 | 42761102 | FORT BRAGG A 1102 | 35592 | FALSE | 21129.6388 | 21129.6388 | 13.1322 | 149 | 0.00014429 | 808 | 0.38535 | 2920 | 3.1961e-05 | 0.0047622 | 2927 | 0.14 | 1329
6748 | BRUNSWICK 11103907 | 152481110 | BRUNSWICK 1110 | 3907 | FALSE | 1437.9091 | 1437.9091 | 0.89367 | 16 | 0.00047789 | 39 | 0.066432 | 3009 | 3.1747e-05 | 0.00050795 | 2928 | 0.56 | 864
1323 | PEORIA 17013186 | 163781701 | PEORIA 1701 | 3186 | FALSE | 15806.1877 | 15806.1877 | 9.8236 | 143 | 7.9358e-05 | 2223 | 0.39871 | 2917 | 3.1551e-05 | 0.0045118 | 2929 | 0.04 | 2226
6182 | BERESFORD 0403435168 | 24040403 | BERESFORD 0403 | 435168 | FALSE | 2902.2955 | 2068.4077 | 1.2855 | 26 | 4.9503e-05 | 3049 | 0.97971 | 2895 | 3.1131e-05 | 0.00080941 | 2930 |  | 3011
8329 | BRUNSWICK 1104244027 | 152481104 | BRUNSWICK 1104 | 244027 | TRUE | 620.9738 | 492.7502 | 0.30625 | 6 | 0.00047101 | 41 | 0.065791 | 3272 | 3.093e-05 | 0.00018558 | 2931 |  | 3214
10464 | CAMP EVERS 210595394 | 83622105 | CAMP EVERS 2105 | 95394 | TRUE | 790.3942 | 790.3942 | 0.49123 | 8 | 0.00046445 | 43 | 0.066431 | 3075 | 3.0854e-05 | 0.00024683 | 2932 | 8.99 | 417
4342 | PARADISE 110636042 | 102831106 | PARADISE 1106 | 36042 | FALSE | 14063.6211 | 13184.5103 | 8.1942 | 119 | 0.00046491 | 42 | 0.066335 | 3138 | 3.0817e-05 | 0.0036673 | 2933 |  | 2883
9818 | ANDERSON 1101561686 | 103261101 | ANDERSON 1101 | 561686 | TRUE | 147.2029 | 147.2029 | 0.091487 | 1 | 0.00044669 | 47 | 0.066431 | 3105 | 2.9674e-05 | 2.9674e-05 | 2934 |  | 3430
2309 | BEN LOMOND 040116010 | 83040401 | BEN LOMOND 0401 | 16010 | FALSE | 2728.9115 | 2728.9115 | 1.696 | 25 | 0.00044502 | 49 | 0.066431 | 3054 | 2.9564e-05 | 0.00073909 | 2935 | 0.3 | 1015
2259 | LAKEWOOD 210738404 | 13532107 | LAKEWOOD 2107 | 38404 | FALSE | 9333.1056 | 5730.6143 | 3.5616 | 47 | 0.00010907 | 1427 | 0.73881 | 2906 | 2.9507e-05 | 0.0013868 | 2936 | 0.08 | 1611
6756 | FAIRMOUNT 0401395180 | 12650401 | FAIRMOUNT 0401 | 395180 | FALSE | 2394.7505 | 2263.8752 | 1.407 | 20 | 1.6162e-05 | 3578 | 2.4421 | 2827 | 2.9412e-05 | 0.00058824 | 2937 |  | 3059
9891 | RIO DELL 1102214052 | 192251102 | RIO DELL 1102 | 214052 | TRUE | 1011.6764 | 941.1587 | 0.58493 | 7 | 0.00044429 | 50 | 0.066065 | 3204 | 2.933e-05 | 0.00020531 | 2938 |  | 3447
9611 | DIAMOND SPRINGS 1106176130 | 152261106 | DIAMOND SPRINGS 1106 | 176130 | TRUE | 32.0737 | 32.0737 | 0.019934 | 1 | 0.00044128 | 54 | 0.066432 | 3008 | 2.9315e-05 | 2.9315e-05 | 2939 |  | 3388
9648 | CAMP EVERS 2103CB | 83622103 | CAMP EVERS 2103 | CB | TRUE | 225.7012 | 190.3788 | 0.11832 | 6 | 0.00043795 | 56 | 0.066004 | 3225 | 2.9049e-05 | 0.00017429 | 2940 | 0.17 | 1240
7669 | PARADISE 1104CB | 102831104 | PARADISE 1104 | CB | FALSE | 5993.6916 | 2211.8341 | 1.3747 | 46 | 0.0004418 | 52 | 0.065541 | 3355 | 2.9018e-05 | 0.0013348 | 2941 | 4.56 | 515
8116 | BRUNSWICK 1107969778 | 152481107 | BRUNSWICK 1107 | 969778 | FALSE | 1070.9786 | 1070.9786 | 0.66562 | 9 | 0.00042983 | 59 | 0.066432 | 3004 | 2.8554e-05 | 0.00025699 | 2942 |  | 3193
1751 | PARADISE 1104954322 | 102831104 | PARADISE 1104 | 954322 | FALSE | 6923.0973 | 6923.0973 | 4.3027 | 63 | 0.0004268 | 60 | 0.066431 | 3044 | 2.8353e-05 | 0.0017862 | 2943 |  | 2742
6559 | BIG BASIN 11015479 | 82841101 | BIG BASIN 1101 | 5479 | TRUE | 289.2777 | 289.2777 | 0.17979 | 3 | 0.00041807 | 63 | 0.066431 | 3086 | 2.7773e-05 | 8.3319e-05 | 2944 | 2.14 | 619
11110 | CAMP EVERS 2105BL 2101 | 83622105 | CAMP EVERS 2105 | BL 2101 | TRUE | 5.191 | 5.191 | 0.0032262 | 1 | 0.00041248 | 66 | 0.066431 | 3087 | 2.7401e-05 | 2.7401e-05 | 2945 | 6.05 | 475
7068 | BURNS 2101CB | 183582101 | BURNS 2101 | CB | FALSE | 2742.3098 | 2742.3098 | 1.7044 | 19 | 0.00040765 | 67 | 0.066431 | 3078 | 2.7081e-05 | 0.00051453 | 2946 | 26.67 | 267
10401 | POINT MORETTI 110110722 | 82931101 | POINT MORETTI 1101 | 10722 | TRUE | 937.9448 | 937.9448 | 0.58294 | 9 | 0.00040174 | 68 | 0.066431 | 3060 | 2.6688e-05 | 0.00024019 | 2947 | 14.01 | 358
2162 | SOBRANTE 1102L510R | 14671102 | SOBRANTE 1102 | L510R | FALSE | 15698.8958 | 15538.9501 | 9.6575 | 136 | 8.2413e-05 | 2142 | 0.24129 | 2927 | 2.6158e-05 | 0.0035575 | 2948 | 0.21 | 1146
8264 | MIRABEL 1101781318 | 42091101 | MIRABEL 1101 | 781318 | TRUE | 172.1377 | 172.1377 | 0.10698 | 3 | 0.00038201 | 74 | 0.066431 | 3034 | 2.5377e-05 | 7.6132e-05 | 2949 |  | 3210
2959 | PARADISE 110453544 | 102831104 | PARADISE 1104 | 53544 | FALSE | 1728.2043 | 1035.1182 | 0.64333 | 19 | 0.00038613 | 71 | 0.06569 | 3314 | 2.5314e-05 | 0.00048097 | 2950 |  | 2807
2047 | VALLEY VIEW 1103CB | 14341103 | VALLEY VIEW 1103 | CB | TRUE | 10480.8911 | 272.5459 | 0.16939 | 83 | 4.1439e-05 | 3235 | 0.25769 | 2926 | 2.5206e-05 | 0.0020921 | 2951 | 5.67 | 480
3341 | CAMP EVERS 21055146 | 83622105 | CAMP EVERS 2105 | 5146 | FALSE | 9534.7408 | 9534.7408 | 5.9259 | 63 | 0.00036971 | 78 | 0.066431 | 3063 | 2.4561e-05 | 0.0015473 | 2952 | 0.55 | 870
4945 | CASTRO VALLEY 1102837904 | 14091102 | CASTRO VALLEY 1102 | 837904 | FALSE | 3252.9939 | 1669.2171 | 1.0374 | 25 | 3.8294e-05 | 3293 | 0.69841 | 2909 | 2.4435e-05 | 0.00061089 | 2953 |  | 2930
5852 | PARADISE 1104961990 | 102831104 | PARADISE 1104 | 961990 | FALSE | 10972.2602 | 10972.2602 | 6.8193 | 91 | 0.00035642 | 85 | 0.066431 | 3018 | 2.3677e-05 | 0.0021547 | 2954 |  | 2984
8958 | PARADISE 1103772517 | 102831103 | PARADISE 1103 | 772517 | FALSE | 2777.244 | 2777.244 | 1.7261 | 24 | 0.00035423 | 87 | 0.066378 | 3129 | 2.3519e-05 | 0.00056446 | 2955 |  | 3281
5973 | BEN LOMOND 0401CB | 83040401 | BEN LOMOND 0401 | CB | FALSE | 12509.5528 | 12509.5528 | 7.7747 | 106 | 0.00034662 | 93 | 0.066431 | 3076 | 2.3026e-05 | 0.0024408 | 2956 | 1.58 | 665
10776 | GRASS VALLEY 1101528232 | 152031101 | GRASS VALLEY 1101 | 528232 | TRUE | 149.6502 | 149.6502 | 0.093008 | 2 | 0.00033485 | 99 | 0.066432 | 3013 | 2.2245e-05 | 4.449e-05 | 2957 |  | 3604
10760 | FLINT 1102CB | 152531102 | FLINT 1102 | CB | TRUE | 149.4178 | 149.4178 | 0.092864 | 2 | 0.00033388 | 100 | 0.066432 | 3002 | 2.218e-05 | 4.436e-05 | 2958 | 0.05 | 1937
3909 | MORRO BAY 1102V84 | 183011102 | MORRO BAY 1102 | V84 | TRUE | 15879.9521 | 369.7837 | 0.22982 | 126 | 7.2115e-06 | 3627 | 0.37923 | 2921 | 2.1832e-05 | 0.0027508 | 2959 |  | 2861
7549 | PLACERVILLE 1111CB | 153081111 | PLACERVILLE 1111 | CB | FALSE | 2249.8408 | 2245.2688 | 1.3954 | 16 | 0.00032886 | 103 | 0.066351 | 3136 | 2.1827e-05 | 0.00034924 | 2960 | 0.1 | 1487
6107 | POINT MORETTI 110139126 | 82931101 | POINT MORETTI 1101 | 39126 | FALSE | 3634.7812 | 3634.7812 | 2.259 | 31 | 0.00031627 | 110 | 0.066431 | 3079 | 2.101e-05 | 0.00065131 | 2961 | 15.84 | 344
9485 | CAMP EVERS 2106834583 | 83622106 | CAMP EVERS 2106 | 834583 | TRUE | 981.0329 | 981.0329 | 0.60972 | 7 | 0.00030071 | 130 | 0.066431 | 3073 | 1.9977e-05 | 0.00013984 | 2962 | 4.09 | 528
6136 | BIG TREES 0402737512 | 83050402 | BIG TREES 0402 | 737512 | FALSE | 11180.7593 | 10917.3933 | 6.7852 | 89 | 0.0002931 | 137 | 0.066402 | 3118 | 1.9465e-05 | 0.0017324 | 2963 |  | 3008
940 | CAMP EVERS 210511384 | 83622105 | CAMP EVERS 2105 | 11384 | FALSE | 8402.4777 | 8402.4777 | 5.2222 | 59 | 0.00028937 | 140 | 0.066431 | 3069 | 1.9223e-05 | 0.0011342 | 2964 | 13.77 | 362
8260 | DIAMOND SPRINGS 1106762780 | 152261106 | DIAMOND SPRINGS 1106 | 762780 | TRUE | 1282.4551 | 400.767 | 0.24908 | 11 | 0.0002944 | 135 | 0.065383 | 3424 | 1.9222e-05 | 0.00021145 | 2965 |  | 3209
9711 | BRUNSWICK 1103262343 | 152481103 | BRUNSWICK 1103 | 262343 | FALSE | 1232.8709 | 1232.8709 | 0.76623 | 11 | 0.00028891 | 143 | 0.066432 | 3003 | 1.9193e-05 | 0.00021112 | 2966 |  | 3404
6422 | BIG BASIN 11029741 | 82841102 | BIG BASIN 1102 | 9741 | FALSE | 1036.4661 | 1036.4661 | 0.64417 | 10 | 0.00028291 | 149 | 0.066431 | 3057 | 1.8794e-05 | 0.00018794 | 2967 | 14.27 | 356
471 | BIG BASIN 11015028 | 82841101 | BIG BASIN 1101 | 5028 | FALSE | 8087.7219 | 8087.7219 | 5.0266 | 59 | 0.00027873 | 160 | 0.066431 | 3056 | 1.8516e-05 | 0.0010925 | 2968 | 0.63 | 832
5836 | BRUNSWICK 1103851116 | 152481103 | BRUNSWICK 1103 | 851116 | TRUE | 405.8442 | 316.0008 | 0.1964 | 4 | 0.00027959 | 155 | 0.066111 | 3190 | 1.8459e-05 | 7.3835e-05 | 2969 |  | 2981
10320 | DIAMOND SPRINGS 1106926235 | 152261106 | DIAMOND SPRINGS 1106 | 926235 | TRUE | 416.1419 | 305.3669 | 0.18979 | 4 | 0.00027977 | 153 | 0.065791 | 3274 | 1.8372e-05 | 7.3487e-05 | 2970 |  | 3532
10026 | SARATOGA 1103981056 | 83371103 | SARATOGA 1103 | 981056 | TRUE | 227.7546 | 132.017 | 0.082049 | 2 | 0.00027805 | 163 | 0.065789 | 3285 | 1.8259e-05 | 3.6518e-05 | 2971 |  | 3476
7034 | DIAMOND SPRINGS 110699658 | 152261106 | DIAMOND SPRINGS 1106 | 99658 | TRUE | 4406.3905 | 0 | 0 | 39 | 0.00027979 | 152 | 0.06515 | 3578 | 1.8228e-05 | 0.0007109 | 2972 | 0.05 | 2030
4269 | BRUNSWICK 110378862 | 152481103 | BRUNSWICK 1103 | 78862 | TRUE | 1804.4635 | 123.6088 | 0.076823 | 17 | 0.00027939 | 158 | 0.065225 | 3497 | 1.8213e-05 | 0.00030962 | 2973 | 5.76 | 478
3650 | ROB ROY 210512584 | 83692105 | ROB ROY 2105 | 12584 | FALSE | 41638.8897 | 5651.1648 | 3.5122 | 297 | 5.9861e-05 | 2779 | 0.22529 | 2929 | 1.8188e-05 | 0.0054019 | 2974 | 0.03 | 2245
2640 | PERRY 1101V72 | 183071101 | PERRY 1101 | V72 | FALSE | 14155.2453 | 9610.0836 | 5.9727 | 101 | 2.6938e-05 | 3473 | 1.494 | 2866 | 1.8115e-05 | 0.0018297 | 2975 | 0.05 | 1974
7574 | CAMP EVERS 210611006 | 83622106 | CAMP EVERS 2106 | 11006 | FALSE | 3281.0215 | 3281.0215 | 2.0392 | 24 | 0.00027097 | 170 | 0.066431 | 3059 | 1.8001e-05 | 0.00043202 | 2976 | 0.37 | 965
10111 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 32.8824 | 32.8824 | 0.020437 | 1 | 0.00026849 | 175 | 0.066431 | 3046 | 1.7836e-05 | 1.7836e-05 | 2977 |  | 3493
7350 | SUMMIT 1101CB | 152591101 | SUMMIT 1101 | CB | TRUE | 221.0797 | 221.0797 | 0.1374 | 2 | 0.0002671 | 177 | 0.066431 | 3047 | 1.7744e-05 | 3.5488e-05 | 2978 | 0.03 | 2339
10523 | CAMP EVERS 2104710556 | 83622104 | CAMP EVERS 2104 | 710556 | TRUE | 81.8649 | 65.863 | 0.040934 | 2 | 0.00026928 | 174 | 0.065792 | 3269 | 1.7662e-05 | 3.5324e-05 | 2979 |  | 3566
5707 | FLINT 1101958726 | 152531101 | FLINT 1101 | 958726 | FALSE | 1647.4395 | 1605.4653 | 0.9978 | 13 | 0.00026566 | 180 | 0.066333 | 3140 | 1.7619e-05 | 0.00022904 | 2980 |  | 2975
8628 | POINT MORETTI 11015401 | 82931101 | POINT MORETTI 1101 | 5401 | FALSE | 4047.5171 | 4047.5171 | 2.5155 | 34 | 0.0002635 | 187 | 0.066431 | 3064 | 1.7505e-05 | 0.00059516 | 2981 | 18.02 | 327
10455 | POTTER VALLEY P H 1104CB | 42281104 | POTTER VALLEY P H 1104 | CB | TRUE | 158.4451 | 158.4451 | 0.098474 | 2 | 0.00026209 | 192 | 0.066431 | 3100 | 1.7411e-05 | 3.4822e-05 | 2982 | 0.02 | 2438
1795 | BOLINAS 11011064 | 42261101 | BOLINAS 1101 | 1064 | FALSE | 7144.3316 | 1005.39 | 0.62485 | 51 | 5.2154e-05 | 2989 | 0.37559 | 2922 | 1.7391e-05 | 0.00088693 | 2983 | 0.02 | 2426
11067 | BRUNSWICK 1104761310 | 152481104 | BRUNSWICK 1104 | 761310 | TRUE | 43.1053 | 43.1053 | 0.02679 | 1 | 0.00026016 | 195 | 0.066432 | 3006 | 1.7283e-05 | 1.7283e-05 | 2984 | 9.94 | 403
130 | CAMP EVERS 21055232 | 83622105 | CAMP EVERS 2105 | 5232 | FALSE | 7264.9547 | 7264.9547 | 4.5152 | 50 | 0.00025977 | 196 | 0.066431 | 3065 | 1.7257e-05 | 0.00086284 | 2985 | 0.52 | 889
9051 | BRUNSWICK 1103956424 | 152481103 | BRUNSWICK 1103 | 956424 | FALSE | 2618.2583 | 1661.8272 | 1.0328 | 21 | 0.00026235 | 190 | 0.065882 | 3247 | 1.7224e-05 | 0.00036171 | 2986 |  | 3301
7122 | CAMP EVERS 210510786 | 83622105 | CAMP EVERS 2105 | 10786 | FALSE | 7392.1952 | 7392.1952 | 4.5943 | 58 | 0.00025715 | 199 | 0.066431 | 3068 | 1.7083e-05 | 0.0009908 | 2987 | 23.31 | 288
7997 | CAMP EVERS 210411048 | 83622104 | CAMP EVERS 2104 | 11048 | FALSE | 2138.5875 | 1473.7073 | 0.91592 | 19 | 0.00025575 | 204 | 0.065825 | 3261 | 1.6894e-05 | 0.00032099 | 2988 | 0.22 | 1122
10098 | RALSTON 1101100040 | 24141101 | RALSTON 1101 | 100040 | FALSE | 1340.2293 | 1324.2274 | 0.82301 | 7 | 0.00025542 | 205 | 0.065698 | 3313 | 1.6779e-05 | 0.00011745 | 2989 |  | 3490
4770 | CAMP EVERS 210574170 | 83622105 | CAMP EVERS 2105 | 74170 | FALSE | 5752.9394 | 5752.9394 | 3.5755 | 43 | 0.00025227 | 211 | 0.066431 | 3071 | 1.6759e-05 | 0.00072063 | 2990 | 54.65 | 106
10059 | POTTER VALLEY P H 1105CB | 42281105 | POTTER VALLEY P H 1105 | CB | TRUE | 89.3518 | 89.3518 | 0.055533 | 2 | 0.0002491 | 218 | 0.066431 | 3102 | 1.6548e-05 | 3.3096e-05 | 2991 | 0.02 | 2430
1470 | PLACERVILLE 210619732 | 153082106 | PLACERVILLE 2106 | 19732 | FALSE | 14898.6258 | 14898.6258 | 9.2596 | 125 | 0.00024625 | 229 | 0.066432 | 3015 | 1.6359e-05 | 0.0020448 | 2992 | 0.39 | 954
5865 | CAMP EVERS 210611044 | 83622106 | CAMP EVERS 2106 | 11044 | FALSE | 19649.9105 | 12291.7272 | 7.6394 | 144 | 0.00024668 | 228 | 0.06589 | 3246 | 1.6316e-05 | 0.0023496 | 2993 | 0.26 | 1067
4584 | BRUNSWICK 1107357568 | 152481107 | BRUNSWICK 1107 | 357568 | FALSE | 3842.9954 | 1927.7671 | 1.1981 | 35 | 0.00024621 | 230 | 0.065663 | 3320 | 1.6214e-05 | 0.0005675 | 2994 |  | 2905
4170 | SAN RAFAEL 11042651 | 42011104 | SAN RAFAEL 1104 | 2651 | FALSE | 1316.7963 | 1238.5246 | 0.76975 | 10 | 0.00024324 | 237 | 0.066303 | 3149 | 1.6143e-05 | 0.00016143 | 2995 | 0.05 | 1964
4250 | SAN RAFAEL 1106837 | 42011106 | SAN RAFAEL 1106 | 837 | FALSE | 2514.1986 | 1083.651 | 0.67349 | 22 | 0.00024512 | 232 | 0.065733 | 3299 | 1.6143e-05 | 0.00035514 | 2996 | 0.03 | 2298
8770 | MIRABEL 11027401 | 42091102 | MIRABEL 1102 | 7401 | FALSE | 1710.0336 | 1710.0336 | 1.0628 | 12 | 0.00023873 | 251 | 0.066431 | 3026 | 1.5859e-05 | 0.00019031 | 2997 | 5.59 | 483
5879 | BIG BASIN 11019773 | 82841101 | BIG BASIN 1101 | 9773 | TRUE | 724.8545 | 724.8545 | 0.4505 | 6 | 0.00023796 | 254 | 0.066431 | 3077 | 1.5808e-05 | 9.4849e-05 | 2998 | 6.09 | 473
4254 | BRUNSWICK 111095576 | 152481110 | BRUNSWICK 1110 | 95576 | TRUE | 3539.5092 | 0 | 0 | 30 | 0.00024199 | 240 | 0.06515 | 3580 | 1.5765e-05 | 0.00047296 | 2999 | 0.02 | 2521
5644 | BRUNSWICK 1103234378 | 152481103 | BRUNSWICK 1103 | 234378 | FALSE | 1230.3375 | 1030.7217 | 0.6406 | 13 | 0.00023818 | 253 | 0.065939 | 3237 | 1.5727e-05 | 0.00020445 | 3000 |  | 2969
644 | CAMP EVERS 210511004 | 83622105 | CAMP EVERS 2105 | 11004 | FALSE | 6981.3249 | 6981.3249 | 4.3389 | 60 | 0.000234 | 264 | 0.066431 | 3053 | 1.5545e-05 | 0.00093268 | 3001 | 0.81 | 772
10461 | GIRVAN 1102296428 | 103401102 | GIRVAN 1102 | 296428 | FALSE | 5326.8427 | 2768.6124 | 1.7207 | 14 | 0.00023533 | 262 | 0.065703 | 3308 | 1.5492e-05 | 0.00021689 | 3002 |  | 3554
8135 | WOODSIDE 1101CB | 24251101 | WOODSIDE 1101 | CB | TRUE | 6762.3674 | 0 | 0 | 59 | 0.00023708 | 256 | 0.065169 | 3547 | 1.545e-05 | 0.00091153 | 3003 |  | 3195
555 | BRUNSWICK 110750008 | 152481107 | BRUNSWICK 1107 | 50008 | FALSE | 7897.7178 | 1828.8508 | 1.1366 | 64 | 0.00023509 | 263 | 0.06535 | 3436 | 1.5377e-05 | 0.0009841 | 3004 | 0.7 | 810
4851 | DIAMOND SPRINGS 1106910235 | 152261106 | DIAMOND SPRINGS 1106 | 910235 | TRUE | 1774.1223 | 851.0444 | 0.52893 | 16 | 0.00023372 | 267 | 0.065631 | 3328 | 1.5283e-05 | 0.00024453 | 3005 |  | 2923
436 | SARATOGA 1107LC26 | 83371107 | SARATOGA 1107 | LC26 | FALSE | 9057.4757 | 9057.4757 | 5.6293 | 74 | 0.00022734 | 294 | 0.066432 | 2991 | 1.5103e-05 | 0.0011176 | 3006 | 0.12 | 1372
3317 | PLACERVILLE 1110CB | 153081110 | PLACERVILLE 1110 | CB | FALSE | 2889.8933 | 1390.1141 | 0.86396 | 28 | 0.0002292 | 288 | 0.065745 | 3295 | 1.5035e-05 | 0.00042097 | 3007 | 0.09 | 1554
4169 | GRASS VALLEY 1102CB | 152031102 | GRASS VALLEY 1102 | CB | TRUE | 9322.594 | 131.7629 | 0.081891 | 81 | 0.00022849 | 289 | 0.065197 | 3511 | 1.4894e-05 | 0.0012064 | 3008 |  | 2874
1767 | MONTE RIO 111264682 | 42811112 | MONTE RIO 1112 | 64682 | FALSE | 2835.1135 | 2835.1135 | 1.762 | 22 | 0.00022403 | 304 | 0.066431 | 3092 | 1.4883e-05 | 0.00032742 | 3009 | 46.82 | 138
7374 | MIRABEL 1102841 | 42091102 | MIRABEL 1102 | 841 | FALSE | 1307.0396 | 1307.0396 | 0.81233 | 12 | 0.00022352 | 305 | 0.066431 | 3027 | 1.4849e-05 | 0.00017819 | 3010 | 0.34 | 982
9494 | SAN RAFAEL 1101546438 | 42011101 | SAN RAFAEL 1101 | 546438 | FALSE | 1552.7497 | 1541.3848 | 0.95798 | 14 | 0.00022139 | 313 | 0.066248 | 3162 | 1.4698e-05 | 0.00020577 | 3011 |  | 3363
7746 | SALT SPRINGS 21014913 | 163692101 | SALT SPRINGS 2101 | 4913 | FALSE | 6065.3094 | 6065.3094 | 3.7696 | 54 | 1.9829e-05 | 3546 | 0.94688 | 2897 | 1.4645e-05 | 0.00079082 | 3012 | 0.02 | 2519
7346 | OAKLAND K 1101CR346 | 12101101 | OAKLAND K 1101 | CR346 | TRUE | 330.9469 | 330.9469 | 0.20568 | 3 | 0.00021988 | 322 | 0.066432 | 2961 | 1.4607e-05 | 4.3821e-05 | 3013 | 0.27 | 1053
112 | EL DORADO PH 210219562 | 152762102 | EL DORADO PH 2102 | 19562 | FALSE | 11663.8964 | 11663.8964 | 7.2492 | 98 | 0.00021832 | 327 | 0.066431 | 3051 | 1.4503e-05 | 0.0014213 | 3014 | 80.06 | 48
3957 | LOS GATOS 1106LA42 | 82021106 | LOS GATOS 1106 | LA42 | FALSE | 4459.4554 | 4459.4554 | 2.7716 | 35 | 0.00021752 | 329 | 0.066431 | 3062 | 1.445e-05 | 0.00050575 | 3015 | 0.48 | 904
10681 | GEYSERVILLE 1101975350 | 42891101 | GEYSERVILLE 1101 | 975350 | TRUE | 405.3394 | 73.1065 | 0.045436 | 3 | 0.00015577 | 686 | 0.090462 | 2933 | 1.4284e-05 | 4.2852e-05 | 3016 |  | 3591
10208 | SHINGLE SPRINGS 2110CB | 153652110 | SHINGLE SPRINGS 2110 | CB | FALSE | 2054.39 | 1346.787 | 0.83703 | 15 | 0.00021376 | 344 | 0.065919 | 3239 | 1.4099e-05 | 0.00021149 | 3017 | 0.16 | 1250
10739 | FORT BRAGG A 1104920850 | 42761104 | FORT BRAGG A 1104 | 920850 | TRUE | 514.6425 | 322.1994 | 0.20025 | 3 | 0.00021514 | 340 | 0.065576 | 3348 | 1.406e-05 | 4.2181e-05 | 3018 |  | 3600
9733 | AUBURN 11028611 | 152161102 | AUBURN 1102 | 8611 | FALSE | 2893.9317 | 2893.9317 | 1.7986 | 22 | 0.00020875 | 367 | 0.066432 | 3005 | 1.3867e-05 | 0.00030508 | 3019 | 0.05 | 1987
6925 | MIRABEL 11022043 | 42091102 | MIRABEL 1102 | 2043 | TRUE | 902.2238 | 902.2238 | 0.56074 | 8 | 0.00020837 | 369 | 0.066431 | 3028 | 1.3842e-05 | 0.00011074 | 3020 | 28.28 | 251
6206 | SAN RAFAEL 11081247 | 42011108 | SAN RAFAEL 1108 | 1247 | TRUE | 443.4693 | 443.4693 | 0.27562 | 3 | 0.00020644 | 376 | 0.066431 | 3039 | 1.3714e-05 | 4.1142e-05 | 3021 | 45.01 | 152
9515 | HARRIS 1109661309 | 192431109 | HARRIS 1109 | 661309 | TRUE | 2205.0428 | 453.7966 | 0.28204 | 16 | 0.00020886 | 365 | 0.065469 | 3383 | 1.3667e-05 | 0.00021867 | 3022 |  | 3369
10016 | CAMP EVERS 2104600529 | 83622104 | CAMP EVERS 2104 | 600529 | TRUE | 435.4123 | 422.8048 | 0.26277 | 4 | 0.00020229 | 388 | 0.066112 | 3188 | 1.3356e-05 | 5.3422e-05 | 3023 |  | 3471
10551 | PUEBLO 1104968601 | 43291104 | PUEBLO 1104 | 968601 | TRUE | 12.2398 | 12.2398 | 0.0076071 | 1 | 0.00020045 | 395 | 0.066431 | 3041 | 1.3316e-05 | 1.3316e-05 | 3024 |  | 3573
8097 | SARATOGA 11075696 | 83371107 | SARATOGA 1107 | 5696 | FALSE | 9835.0739 | 8152.2263 | 5.0666 | 90 | 0.00020042 | 396 | 0.066175 | 3179 | 1.3265e-05 | 0.0011939 | 3025 | 0.11 | 1418
9710 | GEYSERVILLE 1101216442 | 42891101 | GEYSERVILLE 1101 | 216442 | TRUE | 327.4361 | 327.4361 | 0.2035 | 4 | 0.00012382 | 1123 | 0.10422 | 2932 | 1.2906e-05 | 5.1625e-05 | 3026 |  | 3403
8869 | BRUNSWICK 11047181 | 152481104 | BRUNSWICK 1104 | 7181 | FALSE | 1244.1443 | 1244.1443 | 0.77324 | 11 | 0.00019333 | 428 | 0.066432 | 3010 | 1.2843e-05 | 0.00014128 | 3027 | 7.1 | 450
8464 | CAMP EVERS 21067603 | 83622106 | CAMP EVERS 2106 | 7603 | FALSE | 1527.2306 | 1527.2306 | 0.94918 | 11 | 0.00019238 | 431 | 0.066431 | 3055 | 1.278e-05 | 0.00014058 | 3028 | 0.27 | 1054
1616 | SARATOGA 1106LC24 | 83371106 | SARATOGA 1106 | LC24 | FALSE | 18535.4178 | 13258.5886 | 8.2403 | 154 | 0.00019316 | 429 | 0.066006 | 3215 | 1.2747e-05 | 0.001963 | 3029 | 0.08 | 1601
10877 | MORAGA 110183424 | 13801101 | MORAGA 1101 | 83424 | FALSE | 2603.9122 | 2600.4486 | 1.6162 | 7 | 0.00018902 | 446 | 0.066249 | 3161 | 1.2546e-05 | 8.7822e-05 | 3030 | 8.82 | 419
7661 | CAMP EVERS 210616000 | 83622106 | CAMP EVERS 2106 | 16000 | FALSE | 6212.4721 | 3353.5945 | 2.0843 | 51 | 0.000189 | 448 | 0.065804 | 3266 | 1.2496e-05 | 0.0006373 | 3031 | 13.79 | 361
11062 | KESWICK 1101CB | 103451101 | KESWICK 1101 | CB | TRUE | 26.6683 | 26.6683 | 0.016574 | 1 | 0.00018686 | 464 | 0.066431 | 3104 | 1.2413e-05 | 1.2413e-05 | 3032 | 0.2 | 1169
10730 | STAFFORD 1101344092 | 43201101 | STAFFORD 1101 | 344092 | TRUE | 131.1041 | 115.3192 | 0.071671 | 2 | 0.00018617 | 465 | 0.066431 | 3037 | 1.2368e-05 | 2.4736e-05 | 3033 |  | 3598
2899 | PLACER 1101208930 | 152461101 | PLACER 1101 | 208930 | TRUE | 1425.5587 | 187.1265 | 0.1163 | 10 | 0.00018882 | 449 | 11.1381 | 2605 | 1.2302e-05 | 0.00012302 | 3034 |  | 2804
3721 | SHINGLE SPRINGS 210511172 | 153652105 | SHINGLE SPRINGS 2105 | 11172 | FALSE | 3921.2737 | 3218.2333 | 2.0001 | 38 | 0.00018146 | 501 | 0.066162 | 3181 | 1.2003e-05 | 0.00045612 | 3035 | 0.11 | 1424
8829 | MONTE RIO 1111CB | 42811111 | MONTE RIO 1111 | CB | TRUE | 408.9065 | 408.9065 | 0.25414 | 4 | 0.0001783 | 516 | 0.066431 | 3029 | 1.1845e-05 | 4.7378e-05 | 3036 | 13.33 | 366
3789 | LOS GATOS 1106LA46 | 82021106 | LOS GATOS 1106 | LA46 | FALSE | 2411.7925 | 2411.7925 | 1.4989 | 20 | 0.00017602 | 522 | 0.066431 | 3058 | 1.1694e-05 | 0.00023387 | 3037 | 19.55 | 311
8577 | SARATOGA 1115463510 | 83371115 | SARATOGA 1115 | 463510 | FALSE | 4881.4666 | 4697.8741 | 2.9197 | 41 | 0.0001755 | 524 | 0.066369 | 3132 | 1.1648e-05 | 0.00047756 | 3038 |  | 3239
8231 | HALF MOON BAY 11038898 | 24101103 | HALF MOON BAY 1103 | 8898 | FALSE | 1034.8013 | 1034.8013 | 0.64313 | 9 | 0.00017399 | 534 | 0.066431 | 3061 | 1.1558e-05 | 0.00010403 | 3039 | 0.71 | 804
3716 | CASTRO VALLEY 1102MR359 | 14091102 | CASTRO VALLEY 1102 | MR359 | TRUE | 10891.9524 | 0 | 0 | 90 | 2.5295e-05 | 3493 | 0.41659 | 2914 | 1.1476e-05 | 0.0010328 | 3040 |  | 2849
9742 | MONROE 210392868 | 43302103 | MONROE 2103 | 92868 | TRUE | 1050.3516 | 203.5363 | 0.1265 | 14 | 0.00017449 | 531 | 0.065522 | 3360 | 1.1443e-05 | 0.0001602 | 3041 | 0.39 | 955
830 | OAKLAND X 1104391688 | 12541104 | OAKLAND X 1104 | 391688 | FALSE | 2071.721 | 2071.721 | 1.2876 | 16 | 0.00017212 | 549 | 0.066431 | 3109 | 1.1434e-05 | 0.00018295 | 3042 |  | 2694
3807 | CAMP EVERS 210355638 | 83622103 | CAMP EVERS 2103 | 55638 | FALSE | 5639.9215 | 2949.5648 | 1.8332 | 42 | 0.00017356 | 537 | 0.065698 | 3312 | 1.1416e-05 | 0.00047946 | 3043 | 0.27 | 1049
2161 | LAKEWOOD 2227W503R | 13532227 | LAKEWOOD 2227 | W503R | TRUE | 12304.5424 | 121.8736 | 0.075745 | 89 | 1.999e-05 | 3544 | 0.42059 | 2913 | 1.1363e-05 | 0.0010113 | 3044 |  | 2765
10225 | CLOVERDALE 1101409224 | 42821101 | CLOVERDALE 1101 | 409224 | TRUE | 353.3451 | 138.7205 | 0.086215 | 4 | 0.0001558 | 685 | 0.071835 | 2942 | 1.131e-05 | 4.524e-05 | 3045 |  | 3518
9704 | DEL MAR 210938684 | 152582109 | DEL MAR 2109 | 38684 | TRUE | 100.1157 | 38.3974 | 0.023864 | 1 | 0.00017305 | 542 | 0.065149 | 3581 | 1.1274e-05 | 1.1274e-05 | 3046 | 0.02 | 2437
6951 | MONTE RIO 1111506 | 42811111 | MONTE RIO 1111 | 506 | FALSE | 2021.7882 | 2021.7882 | 1.2565 | 18 | 0.00016864 | 571 | 0.066431 | 3019 | 1.1203e-05 | 0.00020165 | 3047 | 19.11 | 314
7579 | WOODSIDE 11012299 | 24251101 | WOODSIDE 1101 | 2299 | FALSE | 2927.8179 | 2927.8179 | 1.8197 | 25 | 0.00016866 | 570 | 0.06638 | 3127 | 1.1198e-05 | 0.00027996 | 3048 | 3.04 | 566
4426 | SHINGLE SPRINGS 11038752 | 153651103 | SHINGLE SPRINGS 1103 | 8752 | FALSE | 2987.795 | 2987.795 | 1.8569 | 32 | 0.00016401 | 600 | 0.066391 | 3124 | 1.0889e-05 | 0.00034845 | 3049 | 0.14 | 1308
3276 | CAMP EVERS 210310946 | 83622103 | CAMP EVERS 2103 | 10946 | FALSE | 13600.904 | 9098.3132 | 5.6546 | 112 | 0.00016435 | 595 | 0.06595 | 3235 | 1.0851e-05 | 0.0012153 | 3050 | 0.4 | 945
4220 | OAKLAND X 1104CR214 | 12541104 | OAKLAND X 1104 | CR214 | FALSE | 4637.1496 | 4637.1496 | 2.882 | 35 | 0.00016318 | 609 | 0.066431 | 3098 | 1.0841e-05 | 0.00037942 | 3051 | 26.71 | 265
3032 | OAKLAND X 1104CR288 | 12541104 | OAKLAND X 1104 | CR288 | FALSE | 4382.4988 | 4382.4988 | 2.7237 | 46 | 0.00016278 | 615 | 0.066431 | 3090 | 1.0814e-05 | 0.00049744 | 3052 | 0.78 | 779
3352 | OAKLAND X 1104CR022 | 12541104 | OAKLAND X 1104 | CR022 | FALSE | 6467.1642 | 6467.1642 | 4.0194 | 48 | 0.00016152 | 625 | 0.066431 | 3103 | 1.073e-05 | 0.00051505 | 3053 | 12.67 | 369
9828 | ALLEGHANY 11021101/2 | 152101102 | ALLEGHANY 1102 | 1101/2 | TRUE | 31.1897 | 31.1897 | 0.019385 | 1 | 0.00016141 | 627 | 0.066431 | 3050 | 1.0723e-05 | 1.0723e-05 | 3054 |  | 3431
9784 | CAMP EVERS 2104496570 | 83622104 | CAMP EVERS 2104 | 496570 | TRUE | 701.3537 | 389.3118 | 0.24196 | 8 | 0.00016262 | 617 | 0.065632 | 3327 | 1.0717e-05 | 8.5734e-05 | 3055 |  | 3421
6309 | MONTE RIO 1113250 | 42811113 | MONTE RIO 1113 | 250 | FALSE | 1985.3414 | 1985.3414 | 1.2339 | 14 | 0.0001605 | 639 | 0.066431 | 3020 | 1.0662e-05 | 0.00014927 | 3056 | 12.63 | 371
10893 | FROGTOWN 1702390720 | 163451702 | FROGTOWN 1702 | 390720 | TRUE | 218.4469 | 202.4448 | 0.12582 | 2 | 0.00015881 | 655 | 0.066432 | 2955 | 1.055e-05 | 2.11e-05 | 3057 |  | 3617
4614 | SAN RAFAEL 11081262 | 42011108 | SAN RAFAEL 1108 | 1262 | FALSE | 7115.8815 | 6311.248 | 3.9225 | 57 | 0.00015861 | 656 | 0.066252 | 3160 | 1.0529e-05 | 0.00060016 | 3058 | 0.45 | 914
9095 | LLAGAS 2107250129 | 83182107 | LLAGAS 2107 | 250129 | TRUE | 467.9989 | 401.6728 | 0.24964 | 5 | 0.00015745 | 668 | 0.066432 | 2964 | 1.046e-05 | 5.23e-05 | 3059 |  | 3307
8911 | CAMP EVERS 2106CB | 83622106 | CAMP EVERS 2106 | CB | FALSE | 3786.5637 | 1101.4532 | 0.68456 | 37 | 0.00015882 | 654 | 0.065393 | 3421 | 1.0397e-05 | 0.00038468 | 3060 | 0.08 | 1623
10545 | PASO ROBLES 1103451760 | 182611103 | PASO ROBLES 1103 | 451760 | TRUE | 98.2563 | 98.2563 | 0.061067 | 2 | 0.000155 | 694 | 0.066432 | 2956 | 1.0297e-05 | 2.0594e-05 | 3061 |  | 3571
1830 | SANTA ROSA A 1104210 | 42151104 | SANTA ROSA A 1104 | 210 | FALSE | 12611.9142 | 10477.8716 | 6.512 | 107 | 0.00015483 | 696 | 0.066181 | 3174 | 1.0255e-05 | 0.0010973 | 3062 | 0.61 | 845
10656 | MIWUK 170179118 | 163661701 | MIWUK 1701 | 79118 | TRUE | 31.1564 | 31.1564 | 0.019364 | 2 | 0.00015411 | 704 | 0.066431 | 3084 | 1.0238e-05 | 2.0475e-05 | 3063 | 13.07 | 367
7888 | MONTE RIO 1112212 | 42811112 | MONTE RIO 1112 | 212 | FALSE | 3618.1725 | 3618.1725 | 2.2487 | 27 | 0.00015405 | 705 | 0.066431 | 3024 | 1.0234e-05 | 0.00027631 | 3064 | 26.95 | 263
5285 | CAMP EVERS 21061625 | 83622106 | CAMP EVERS 2106 | 1625 | FALSE | 1400.9701 | 1400.9701 | 0.87071 | 10 | 0.00015401 | 706 | 0.066431 | 3067 | 1.0231e-05 | 0.00010231 | 3065 | 45.14 | 150
7246 | HUMBOLDT BAY 1102104220 | 192341102 | HUMBOLDT BAY 1102 | 104220 | FALSE | 5237.7249 | 1476.8749 | 0.91788 | 45 | 0.00015541 | 691 | 0.065461 | 3392 | 1.0177e-05 | 0.00045796 | 3066 |  | 3107
3485 | SAN RAFAEL 1107CB | 42011107 | SAN RAFAEL 1107 | CB | FALSE | 12682.0012 | 7810.3005 | 4.8541 | 107 | 0.00015094 | 728 | 0.065845 | 3256 | 9.9897e-06 | 0.0010689 | 3067 | 0.33 | 987
1447 | OAKLAND K 1104CR204 | 12101104 | OAKLAND K 1104 | CR204 | FALSE | 6639.5298 | 6639.5298 | 4.1265 | 49 | 0.00015005 | 734 | 0.066431 | 3107 | 9.9677e-06 | 0.00048842 | 3068 | 0.48 | 901
10822 | GRASS VALLEY 1103CB | 152031103 | GRASS VALLEY 1103 | CB | TRUE | 191.1806 | 191.1806 | 0.11882 | 2 | 0.00014987 | 738 | 0.066432 | 3011 | 9.9558e-06 | 1.9912e-05 | 3069 | 0.03 | 2348
3457 | OAKLAND K 1101CR178 | 12101101 | OAKLAND K 1101 | CR178 | TRUE | 529.8862 | 529.8862 | 0.32933 | 7 | 0.00014846 | 758 | 0.066432 | 2953 | 9.8623e-06 | 6.9036e-05 | 3070 | 0.29 | 1028
3129 | SYCAMORE CREEK 1109CB | 102971109 | SYCAMORE CREEK 1109 | CB | TRUE | 14599.8126 | 271.1511 | 0.16852 | 108 | 0.00013381 | 947 | 0.073352 | 2938 | 9.8448e-06 | 0.0010632 | 3071 | 0.04 | 2189
2013 | SHINGLE SPRINGS 210851474 | 153652108 | SHINGLE SPRINGS 2108 | 51474 | TRUE | 7519.049 | 594.1189 | 0.36925 | 68 | 0.00015085 | 730 | 0.065188 | 3526 | 9.839e-06 | 0.00066905 | 3072 | 0.02 | 2433
4677 | MIDDLETOWN 1101932140 | 43141101 | MIDDLETOWN 1101 | 932140 | TRUE | 1542.2382 | 861.7057 | 0.53555 | 15 | 0.00014685 | 774 | 0.065836 | 3258 | 9.669e-06 | 0.00014503 | 3073 |  | 2908
3638 | WOODSIDE 1104CB | 24251104 | WOODSIDE 1104 | CB | TRUE | 11988.7275 | 167.7195 | 0.10424 | 114 | 0.00014824 | 761 | 0.06517 | 3545 | 9.6632e-06 | 0.0011016 | 3074 | 0.07 | 1673
8277 | MONTE RIO 1113532 | 42811113 | MONTE RIO 1113 | 532 | TRUE | 844.3261 | 844.3261 | 0.52475 | 8 | 0.00014487 | 803 | 0.066431 | 3021 | 9.6241e-06 | 7.6993e-05 | 3075 | 27.34 | 259
854 | SHINGLE SPRINGS 1104CB | 153651104 | SHINGLE SPRINGS 1104 | CB | FALSE | 3812.8299 | 1129.2677 | 0.70184 | 32 | 0.00014601 | 789 | 0.06551 | 3366 | 9.5675e-06 | 0.00030616 | 3076 | 0.04 | 2130
6660 | HALSEY 11026129 | 152241102 | HALSEY 1102 | 6129 | FALSE | 5155.4944 | 5155.4944 | 3.2042 | 39 | 0.0001435 | 819 | 0.066432 | 3007 | 9.5328e-06 | 0.00037178 | 3077 | 0.06 | 1793
10561 | BIG RIVER 1101CB | 43081101 | BIG RIVER 1101 | CB | TRUE | 35.3815 | 35.3815 | 0.02199 | 1 | 0.00014293 | 826 | 0.066432 | 2990 | 9.4951e-06 | 9.4951e-06 | 3078 | 0.05 | 1945
4323 | GIRVAN 1102CB | 103401102 | GIRVAN 1102 | CB | FALSE | 22008.731 | 1759.2867 | 1.0934 | 102 | 0.00014538 | 799 | 0.065157 | 3559 | 9.4726e-06 | 0.0009662 | 3079 | 0.03 | 2325
5228 | MONTE RIO 11135026 | 42811113 | MONTE RIO 1113 | 5026 | FALSE | 2967.0616 | 2967.0616 | 1.844 | 23 | 0.00014253 | 832 | 0.066431 | 3023 | 9.4686e-06 | 0.00021778 | 3080 | 0.35 | 976
7379 | CALPELLA 1102379946 | 43411102 | CALPELLA 1102 | 379946 | FALSE | 2891.0032 | 1211.8313 | 0.75316 | 15 | 0.00014448 | 805 | 0.06515 | 3577 | 9.4131e-06 | 0.0001412 | 3081 |  | 3120
8927 | ELK 1101CB | 42981101 | ELK 1101 | CB | TRUE | 39.9198 | 39.9198 | 0.02481 | 1 | 0.0001444 | 807 | 0.065148 | 3597 | 9.4072e-06 | 9.4072e-06 | 3082 | 0.01 | 2574
6426 | ALTO 1125296476 | 42031125 | ALTO 1125 | 296476 | FALSE | 1196.6443 | 1061.0328 | 0.65944 | 11 | 0.00014203 | 839 | 0.065849 | 3254 | 9.3993e-06 | 0.00010339 | 3083 |  | 3030
7763 | BRUNSWICK 1105297538 | 152481105 | BRUNSWICK 1105 | 297538 | FALSE | 1703.5587 | 1703.5587 | 1.0588 | 15 | 0.000141 | 854 | 0.066432 | 3014 | 9.367e-06 | 0.0001405 | 3084 |  | 3160
6048 | SILVERADO 2105337226 | 43432105 | SILVERADO 2105 | 337226 | TRUE | 1293.8077 | 458.4827 | 0.28495 | 13 | 0.00014222 | 835 | 0.065742 | 3297 | 9.3615e-06 | 0.0001217 | 3085 |  | 2998
785 | MIRABEL 1102CB | 42091102 | MIRABEL 1102 | CB | TRUE | 10759.641 | 358.8557 | 0.22303 | 85 | 0.00014251 | 833 | 0.065166 | 3549 | 9.286e-06 | 0.00078931 | 3086 | 0.26 | 1071
10915 | CLARKSVILLE 210551478 | 153612105 | CLARKSVILLE 2105 | 51478 | TRUE | 90.198 | 81.0541 | 0.050375 | 3 | 0.00014054 | 863 | 0.065577 | 3343 | 9.2483e-06 | 2.7745e-05 | 3087 | 1.23 | 697
3642 | AUBURN 1102CB | 152161102 | AUBURN 1102 | CB | FALSE | 11489.4556 | 2237.7238 | 1.3908 | 99 | 0.00014106 | 853 | 0.065344 | 3440 | 9.2292e-06 | 0.00091369 | 3088 | 0.02 | 2562
10606 | BERKELEY F 1105BR166 | 12061105 | BERKELEY F 1105 | BR166 | TRUE | 61.4345 | 61.4345 | 0.038182 | 2 | 0.00013883 | 886 | 0.066432 | 2952 | 9.2229e-06 | 1.8446e-05 | 3089 | 0.05 | 1939
2771 | RIO DELL 1102CB | 192251102 | RIO DELL 1102 | CB | TRUE | 10445.4547 | 0 | 0 | 86 | 0.00014143 | 846 | 0.065148 | 3602 | 9.2139e-06 | 0.0007924 | 3090 | 0.28 | 1040
10346 | EEL RIVER 1103241646 | 192381103 | EEL RIVER 1103 | 241646 | TRUE | 2237.0921 | 583.4204 | 0.3626 | 13 | 0.00014029 | 866 | 0.065148 | 3600 | 9.1396e-06 | 0.00011881 | 3091 |  | 3536
964 | SAN RAFAEL 110991742 | 42011109 | SAN RAFAEL 1109 | 91742 | FALSE | 7594.7858 | 3844.7445 | 2.3895 | 67 | 0.00013708 | 906 | 0.065724 | 3302 | 9.0186e-06 | 0.00060425 | 3092 | 0.12 | 1387
5348 | EEL RIVER 11033820 | 192381103 | EEL RIVER 1103 | 3820 | TRUE | 23262.4232 | 0 | 0 | 115 | 0.0001364 | 914 | 0.065808 | 3265 | 8.9864e-06 | 0.0010334 | 3093 | 0.02 | 2422
3020 | SARATOGA 1104209146 | 83371104 | SARATOGA 1104 | 209146 | FALSE | 9672.039 | 4936.2554 | 3.0679 | 85 | 0.00013627 | 917 | 0.065797 | 3267 | 8.9692e-06 | 0.00076238 | 3094 |  | 2810
10029 | MONTICELLO 11011780 | 43051101 | MONTICELLO 1101 | 1780 | TRUE | 115.3297 | 115.3297 | 0.071678 | 1 | 0.00013489 | 928 | 0.06643 | 3113 | 8.9608e-06 | 8.9608e-06 | 3095 | 0.87 | 761
10582 | OAKLAND X 1101328808 | 12541101 | OAKLAND X 1101 | 328808 | TRUE | 186.4686 | 186.4686 | 0.11589 | 1 | 0.00013477 | 930 | 0.066432 | 2960 | 8.9528e-06 | 8.9528e-06 | 3096 |  | 3574
8839 | BIG BASIN 11026219 | 82841102 | BIG BASIN 1102 | 6219 | FALSE | 1488.6262 | 1488.6262 | 0.92519 | 11 | 0.00013222 | 978 | 0.066431 | 3066 | 8.7836e-06 | 9.662e-05 | 3097 | 7 | 455
2096 | CALISTOGA 1102184814 | 42711102 | CALISTOGA 1102 | 184814 | TRUE | 2352.3551 | 682.245 | 0.42402 | 20 | 0.00013241 | 973 | 0.065475 | 3379 | 8.707e-06 | 0.00017414 | 3098 |  | 2762
10342 | FROGTOWN 1702832694 | 163451702 | FROGTOWN 1702 | 832694 | TRUE | 477.5655 | 461.5634 | 0.28686 | 5 | 0.0001169 | 1251 | 0.073805 | 2937 | 8.7057e-06 | 4.3529e-05 | 3099 |  | 3535
2914 | EUREKA E 110435934 | 192331104 | EUREKA E 1104 | 35934 | TRUE | 5459.9113 | 78.4109 | 0.048733 | 46 | 0.00013282 | 962 | 0.065203 | 3509 | 8.6658e-06 | 0.00039863 | 3100 |  | 2806
4896 | IGNACIO 1105490728 | 42481105 | IGNACIO 1105 | 490728 | FALSE | 1414.5018 | 1044.2482 | 0.649 | 11 | 0.00013128 | 992 | 0.065966 | 3228 | 8.6628e-06 | 9.5291e-05 | 3101 |  | 2925
9315 | LAKEWOOD 2224798018 | 13532224 | LAKEWOOD 2224 | 798018 | FALSE | 1485.4108 | 1448.3137 | 0.90013 | 13 | 0.0001303 | 1006 | 0.066234 | 3166 | 8.6422e-06 | 0.00011235 | 3102 |  | 3340
9391 | WATERSHED 0402CB | 24240402 | WATERSHED 0402 | CB | TRUE | 1752.4587 | 342.98 | 0.21316 | 11 | 0.00013264 | 969 | 0.065147 | 3621 | 8.6414e-06 | 9.5055e-05 | 3103 |  | 3350
9903 | PACIFICA 1102894156 | 22811102 | PACIFICA 1102 | 894156 | TRUE | 625.3701 | 625.3701 | 0.38867 | 4 | 0.0001303 | 1005 | 0.066111 | 3196 | 8.6111e-06 | 3.4445e-05 | 3104 |  | 3450
7834 | GREENBRAE 1103718674 | 43091103 | GREENBRAE 1103 | 718674 | FALSE | 1848.6771 | 1301.8094 | 0.80908 | 16 | 0.0001305 | 1001 | 0.065951 | 3233 | 8.6092e-06 | 0.00013775 | 3105 |  | 3168
10810 | PLACERVILLE 1111610322 | 153081111 | PLACERVILLE 1111 | 610322 | TRUE | 220.6867 | 220.6867 | 0.13716 | 3 | 0.00012983 | 1012 | 0.066004 | 3217 | 8.5935e-06 | 2.578e-05 | 3106 |  | 3607
10497 | FORT ORD 21069658 | 182402106 | FORT ORD 2106 | 9658 | TRUE | 156.0125 | 156.0125 | 0.096962 | 3 | 0.00012787 | 1049 | 0.066432 | 2984 | 8.4949e-06 | 2.5485e-05 | 3107 | 0.04 | 2071
5369 | OAKLAND K 1104CR206 | 12101104 | OAKLAND K 1104 | CR206 | FALSE | 2877.1568 | 2877.1568 | 1.7882 | 22 | 0.00012717 | 1061 | 0.066431 | 3108 | 8.4479e-06 | 0.00018585 | 3108 | 0.28 | 1042
6668 | PAUL SWEET 21075291 | 83252107 | PAUL SWEET 2107 | 5291 | TRUE | 1596.261 | 50.439 | 0.031348 | 14 | 0.00012858 | 1037 | 0.065239 | 3485 | 8.4226e-06 | 0.00011792 | 3109 |  | 3053
4822 | CAMP EVERS 21035404 | 83622103 | CAMP EVERS 2103 | 5404 | FALSE | 7456.6431 | 4377.7978 | 2.7208 | 63 | 0.00012738 | 1057 | 0.065779 | 3291 | 8.4149e-06 | 0.00053014 | 3110 | 0.15 | 1284
10986 | RINCON 1101205854 | 43321101 | RINCON 1101 | 205854 | TRUE | 505.1079 | 505.1079 | 0.31393 | 5 | 0.00012714 | 1063 | 0.065923 | 3238 | 8.3652e-06 | 4.1826e-05 | 3111 |  | 3625
1364 | CAMP EVERS 21035402 | 83622103 | CAMP EVERS 2103 | 5402 | FALSE | 10826.3428 | 4595.9767 | 2.8564 | 87 | 0.0001269 | 1066 | 0.065546 | 3353 | 8.3234e-06 | 0.00072413 | 3112 | 0.19 | 1181
9661 | SARATOGA 1105431214 | 83371105 | SARATOGA 1105 | 431214 | TRUE | 794.6731 | 500.3272 | 0.31096 | 9 | 0.00012639 | 1076 | 0.065861 | 3253 | 8.308e-06 | 7.4772e-05 | 3113 |  | 3396
6999 | JESSUP 1102158468 | 103441102 | JESSUP 1102 | 158468 | FALSE | 1388.9106 | 1120.0792 | 0.69613 | 11 | 0.00012572 | 1083 | 0.066083 | 3201 | 8.3063e-06 | 9.1369e-05 | 3114 |  | 3084
7019 | FORT BRAGG A 1102816 | 42761102 | FORT BRAGG A 1102 | 816 | FALSE | 4123.7572 | 3941.7419 | 2.4498 | 29 | 0.00012427 | 1112 | 0.066299 | 3150 | 8.2407e-06 | 0.00023898 | 3115 | 0.05 | 2024
9287 | SOBRANTE 1103N510R | 14671103 | SOBRANTE 1103 | N510R | TRUE | 1403.237 | 401.7471 | 0.24969 | 15 | 0.00012562 | 1086 | 0.065412 | 3409 | 8.2224e-06 | 0.00012334 | 3116 | 0.19 | 1183
10537 | FROGTOWN 1702798032 | 163451702 | FROGTOWN 1702 | 798032 | TRUE | 259.8305 | 244.5065 | 0.15196 | 2 | 0.00012449 | 1108 | 0.065789 | 3287 | 8.1969e-06 | 1.6394e-05 | 3117 |  | 3569
7405 | HARRIS 11082062 | 192431108 | HARRIS 1108 | 2062 | FALSE | 8420.6852 | 2556.2544 | 1.5887 | 83 | 0.00012402 | 1119 | 0.065581 | 3338 | 8.1613e-06 | 0.00067739 | 3118 | 0.04 | 2221
3886 | SAN RAFAEL 11081457 | 42011108 | SAN RAFAEL 1108 | 1457 | FALSE | 1229.3805 | 1229.3805 | 0.76406 | 9 | 0.00012274 | 1137 | 0.066431 | 3025 | 8.1539e-06 | 7.3385e-05 | 3119 | 0.27 | 1047
9639 | IGNACIO 1105967039 | 42481105 | IGNACIO 1105 | 967039 | TRUE | 469.6042 | 292.9124 | 0.18205 | 3 | 0.00012406 | 1117 | 0.065578 | 3342 | 8.139e-06 | 2.4417e-05 | 3120 |  | 3394
10422 | OAKLAND J 1102CR102 | 12091102 | OAKLAND J 1102 | CR102 | TRUE | 316.3322 | 316.3322 | 0.1966 | 6 | 0.00012168 | 1153 | 0.066431 | 3101 | 8.0835e-06 | 4.8501e-05 | 3121 | 0.08 | 1651
10726 | CALISTOGA 1102960240 | 42711102 | CALISTOGA 1102 | 960240 | TRUE | 816.2732 | 816.2732 | 0.50732 | 5 | 0.00012223 | 1144 | 0.066176 | 3175 | 8.0789e-06 | 4.0394e-05 | 3122 |  | 3597
9181 | MIWUK 1702531976 | 163661702 | MIWUK 1702 | 531976 | FALSE | 2102.4835 | 2102.4835 | 1.3067 | 17 | 0.00012078 | 1169 | 0.066431 | 3080 | 8.0236e-06 | 0.0001364 | 3123 |  | 3322
10385 | ALLEGHANY 11011101/2 | 152101101 | ALLEGHANY 1101 | 1101/2 | TRUE | 36.9839 | 36.9839 | 0.022986 | 1 | 0.00012061 | 1175 | 0.066431 | 3045 | 8.0126e-06 | 8.0126e-06 | 3124 |  | 3540
9316 | FORT BRAGG A 1103284356 | 42761103 | FORT BRAGG A 1103 | 284356 | TRUE | 325.8775 | 218.127 | 0.13557 | 4 | 0.00012158 | 1155 | 0.066111 | 3192 | 7.9902e-06 | 3.1961e-05 | 3125 |  | 3341
10880 | OAKLAND X 1104CR101 | 12541104 | OAKLAND X 1104 | CR101 | TRUE | 28.3921 | 28.3921 | 0.017646 | 1 | 0.00011894 | 1208 | 0.066432 | 2948 | 7.9011e-06 | 7.9011e-06 | 3126 | 0.27 | 1055
4441 | OAKLAND X 1101CR224 | 12541101 | OAKLAND X 1101 | CR224 | TRUE | 1656.0037 | 656.3547 | 0.40793 | 17 | 0.00012031 | 1179 | 0.065676 | 3317 | 7.8938e-06 | 0.0001342 | 3127 | 0.04 | 2180
10513 | OILFIELDS 1103441010 | 182391103 | OILFIELDS 1103 | 441010 | TRUE | 1310.5118 | 592.4873 | 0.36823 | 4 | 6.8458e-05 | 2523 | 0.11315 | 2931 | 7.8772e-06 | 3.1509e-05 | 3128 |  | 3562
1793 | SAN RAFAEL 1109535284 | 42011109 | SAN RAFAEL 1109 | 535284 | TRUE | 913.1511 | 10.8615 | 0.0067505 | 9 | 0.00012012 | 1185 | 0.065436 | 3401 | 7.8608e-06 | 7.0747e-05 | 3129 |  | 2746
8925 | FRUITLAND 11418746 | 192311141 | FRUITLAND 1141 | 8746 | TRUE | 832.2162 | 645.6965 | 0.4013 | 8 | 0.00011829 | 1225 | 0.06579 | 3278 | 7.8216e-06 | 6.2573e-05 | 3130 | 0.55 | 867
8734 | LOS GATOS 110160052 | 82021101 | LOS GATOS 1101 | 60052 | FALSE | 3169.0097 | 3169.0097 | 1.9696 | 28 | 0.00011748 | 1236 | 0.066432 | 3001 | 7.8045e-06 | 0.00021853 | 3131 | 0.05 | 1976
6798 | SAN CARLOS 110475210 | 24181104 | SAN CARLOS 1104 | 75210 | TRUE | 618.926 | 618.926 | 0.38467 | 6 | 0.00011638 | 1261 | 0.066432 | 2967 | 7.7312e-06 | 4.6387e-05 | 3132 | 0.05 | 2048
6381 | OAKLAND X 1106CR008 | 12541106 | OAKLAND X 1106 | CR008 | FALSE | 7178.6151 | 7178.6151 | 4.4615 | 65 | 0.00011602 | 1269 | 0.066431 | 3099 | 7.7074e-06 | 0.00050098 | 3133 | 0.17 | 1230
10638 | SAN RAFAEL 11092213 | 42011109 | SAN RAFAEL 1109 | 2213 | TRUE | 689.8513 | 689.8513 | 0.42875 | 6 | 0.00011622 | 1265 | 0.066218 | 3167 | 7.6893e-06 | 4.6136e-05 | 3134 | 0.02 | 2454
9009 | ALTO 1124553571 | 42031124 | ALTO 1124 | 553571 | TRUE | 319.9061 | 174.9029 | 0.1087 | 4 | 0.00011616 | 1267 | 0.065791 | 3271 | 7.6617e-06 | 3.0647e-05 | 3135 |  | 3296
1292 | EEL RIVER 1103CB | 192381103 | EEL RIVER 1103 | CB | TRUE | 64360.3141 | 0 | 0 | 374 | 0.00011744 | 1237 | 0.065148 | 3603 | 7.6507e-06 | 0.0028614 | 3136 |  | 2721
2486 | LOYOLA 110260082 | 82161102 | LOYOLA 1102 | 60082 | TRUE | 6614.3058 | 0 | 0 | 57 | 0.00011735 | 1238 | 0.06517 | 3546 | 7.6477e-06 | 0.00043592 | 3137 |  | 2780
9942 | BRUNSWICK 1104327226 | 152481104 | BRUNSWICK 1104 | 327226 | TRUE | 144.3861 | 79.5833 | 0.049461 | 2 | 0.0001161 | 1268 | 0.065791 | 3273 | 7.6459e-06 | 1.5292e-05 | 3138 |  | 3458
10778 | PIT NO 5 110190846 | 101321101 | PIT NO 5 1101 | 90846 | TRUE | 149.205 | 149.205 | 0.092731 | 2 | 0.00011453 | 1306 | 0.066431 | 3082 | 7.6083e-06 | 1.5217e-05 | 3139 | 0.01 | 2578
9691 | STELLING 1109787007 | 83481109 | STELLING 1109 | 787007 | TRUE | 354.8281 | 307.1886 | 0.19092 | 5 | 0.00010238 | 1593 | 0.070735 | 2943 | 7.5915e-06 | 3.7958e-05 | 3140 |  | 3398
1439 | TAR FLAT 0402CB | 163240402 | TAR FLAT 0402 | CB | FALSE | 2354.3543 | 1281.2412 | 0.7963 | 18 | 0.00011498 | 1299 | 0.065789 | 3286 | 7.5882e-06 | 0.00013659 | 3141 | 0.02 | 2484
4239 | TAR FLAT 0401CB | 163240401 | TAR FLAT 0401 | CB | FALSE | 5901.3044 | 5623.7964 | 3.4952 | 45 | 0.00011418 | 1316 | 0.066318 | 3144 | 7.5759e-06 | 0.00034092 | 3142 | 0.06 | 1823
6173 | OAKLAND X 1104645092 | 12541104 | OAKLAND X 1104 | 645092 | FALSE | 2229.6022 | 2229.6022 | 1.3857 | 16 | 0.0001137 | 1326 | 0.066352 | 3135 | 7.5529e-06 | 0.00012085 | 3143 |  | 3010
9734 | HIGHLANDS 110484640 | 43361104 | HIGHLANDS 1104 | 84640 | TRUE | 1219.4213 | 660.5476 | 0.41053 | 14 | 0.00011439 | 1310 | 0.06579 | 3276 | 7.5307e-06 | 0.00010543 | 3144 | 0.06 | 1834
10502 | TRIDAM POWERHOUSE 2101CB | 168152101 | TRIDAM POWERHOUSE 2101 | CB | TRUE | 80.9954 | 80.9954 | 0.050339 | 3 | 0.00011256 | 1354 | 0.066431 | 3089 | 7.4775e-06 | 2.2433e-05 | 3145 | 0.03 | 2362
3266 | UKIAH 1113658899 | 42771113 | UKIAH 1113 | 658899 | TRUE | 987.2682 | 941.3759 | 0.58507 | 8 | 0.00011266 | 1349 | 0.066271 | 3156 | 7.4661e-06 | 5.9729e-05 | 3146 |  | 2819
10496 | FROGTOWN 1702814784 | 163451702 | FROGTOWN 1702 | 814784 | TRUE | 296.0572 | 280.0552 | 0.17406 | 3 | 0.00011354 | 1332 | 0.066004 | 3223 | 7.4475e-06 | 2.2342e-05 | 3147 |  | 3559
9921 | OAKLAND X 1106CR266 | 12541106 | OAKLAND X 1106 | CR266 | FALSE | 1901.6084 | 1901.6084 | 1.1819 | 8 | 0.00011171 | 1375 | 0.066431 | 3110 | 7.421e-06 | 5.9368e-05 | 3148 | 23 | 290
7361 | SARATOGA 11076867 | 83371107 | SARATOGA 1107 | 6867 | TRUE | 1328.3948 | 985.9493 | 0.61277 | 11 | 0.00011216 | 1362 | 0.066081 | 3202 | 7.4136e-06 | 8.155e-05 | 3149 | 0.06 | 1791
7276 | SAN CARLOS 11049052 | 24181104 | SAN CARLOS 1104 | 9052 | FALSE | 8315.3581 | 7722.3255 | 4.7995 | 65 | 0.00011158 | 1380 | 0.066333 | 3139 | 7.4082e-06 | 0.00048153 | 3150 | 0.1 | 1459
9123 | UKIAH 1114296894 | 42771114 | UKIAH 1114 | 296894 | TRUE | 465.5322 | 278.1636 | 0.17288 | 6 | 0.00011252 | 1355 | 0.065577 | 3344 | 7.398e-06 | 4.4388e-05 | 3151 |  | 3312
10484 | SANTA ROSA A 1111407286 | 42151111 | SANTA ROSA A 1111 | 407286 | TRUE | 98.0196 | 98.0196 | 0.06092 | 1 | 0.00011059 | 1398 | 0.066431 | 3111 | 7.3466e-06 | 7.3466e-06 | 3152 |  | 3557
6588 | HARRIS 1108705523 | 192431108 | HARRIS 1108 | 705523 | TRUE | 1068.2355 | 321.9298 | 0.20008 | 11 | 0.00011081 | 1395 | 0.065615 | 3332 | 7.293e-06 | 8.0224e-05 | 3153 |  | 3044
3678 | RESEARCH 2102183888 | 14692102 | RESEARCH 2102 | 183888 | FALSE | 4871.8577 | 1898.9745 | 1.1802 | 43 | 0.00011047 | 1402 | 0.065447 | 3396 | 7.2344e-06 | 0.00031108 | 3154 |  | 2846
9265 | ROSSMOOR 1104892332 | 14161104 | ROSSMOOR 1104 | 892332 | TRUE | 410.223 | 410.223 | 0.25496 | 4 | 0.00010843 | 1438 | 0.066432 | 2994 | 7.2035e-06 | 2.8814e-05 | 3155 |  | 3332
5151 | EDES 1112CR312 | 13681112 | EDES 1112 | CR312 | FALSE | 5934.1286 | 5934.1286 | 3.6881 | 42 | 0.00010828 | 1446 | 0.066401 | 3119 | 7.189e-06 | 0.00030194 | 3156 | 0.12 | 1375
6055 | SILVERADO 2105191725 | 43432105 | SILVERADO 2105 | 191725 | TRUE | 766.9235 | 558.1402 | 0.34689 | 8 | 0.00010854 | 1435 | 0.066111 | 3189 | 7.1671e-06 | 5.7337e-05 | 3157 |  | 2999
8973 | DIAMOND SPRINGS 1103394169 | 152261103 | DIAMOND SPRINGS 1103 | 394169 | TRUE | 962.9958 | 642.0804 | 0.39906 | 7 | 0.00010894 | 1428 | 0.065699 | 3310 | 7.1481e-06 | 5.0037e-05 | 3158 |  | 3287
9966 | MONROE 2107380760 | 43302107 | MONROE 2107 | 380760 | FALSE | 1136.5362 | 1053.0262 | 0.65446 | 12 | 0.00010812 | 1448 | 0.066113 | 3186 | 7.1451e-06 | 8.5741e-05 | 3159 |  | 3461
2463 | OAKLAND K 1103CR188 | 12101103 | OAKLAND K 1103 | CR188 | FALSE | 5760.2047 | 5760.2047 | 3.58 | 47 | 0.00010753 | 1463 | 0.066431 | 3016 | 7.1432e-06 | 0.00033573 | 3160 | 0.38 | 960
7755 | HICKS 1116983580 | 83431116 | HICKS 1116 | 983580 | FALSE | 4036.4763 | 3958.5011 | 2.4602 | 33 | 0.00010756 | 1462 | 0.066393 | 3122 | 7.1402e-06 | 0.00023563 | 3161 |  | 3159
2292 | OAKLAND K 1104CR326 | 12101104 | OAKLAND K 1104 | CR326 | FALSE | 2098.9601 | 2098.9601 | 1.3045 | 17 | 0.00010686 | 1482 | 0.066431 | 3106 | 7.0989e-06 | 0.00012068 | 3162 | 16.75 | 337
10476 | SAN RAFAEL 1106618957 | 42011106 | SAN RAFAEL 1106 | 618957 | TRUE | 394.8447 | 301.119 | 0.18715 | 4 | 0.00010843 | 1439 | 0.065151 | 3574 | 7.0643e-06 | 2.8257e-05 | 3163 |  | 3555
3538 | CORTINA 1101302192 | 63121101 | CORTINA 1101 | 302192 | TRUE | 22573.2133 | 0 | 0 | 79 | 0.00010836 | 1443 | 0.065152 | 3561 | 7.0599e-06 | 0.00055773 | 3164 | 0.74 | 793
3533 | OAKLAND K 1104432850 | 12101104 | OAKLAND K 1104 | 432850 | FALSE | 1988.3274 | 1988.3274 | 1.2358 | 26 | 0.0001052 | 1514 | 0.066431 | 3017 | 6.9884e-06 | 0.0001817 | 3165 |  | 2834
9797 | DEL MONTE 21032204 | 182222103 | DEL MONTE 2103 | 2204 | TRUE | 592.6413 | 592.6413 | 0.36833 | 8 | 0.00010504 | 1526 | 0.066432 | 2980 | 6.9782e-06 | 5.5825e-05 | 3166 | 0.04 | 2073
10205 | BERKELEY F 1103813976 | 12061103 | BERKELEY F 1103 | 813976 | TRUE | 328.1808 | 312.2978 | 0.19409 | 4 | 0.00010513 | 1520 | 0.066111 | 3194 | 6.9422e-06 | 2.7769e-05 | 3167 |  | 3515
398 | ROSSMOOR 1104CB | 14161104 | ROSSMOOR 1104 | CB | TRUE | 17820.8713 | 0 | 0 | 150 | 0.00010626 | 1491 | 0.065148 | 3591 | 6.9228e-06 | 0.0010384 | 3168 |  | 2669
465 | MOLINO 1102111666 | 42571102 | MOLINO 1102 | 111666 | TRUE | 1605.5548 | 182.6023 | 0.11349 | 13 | 0.00010584 | 1499 | 0.06525 | 3479 | 6.9214e-06 | 8.9978e-05 | 3169 |  | 2676
9817 | SUMMIT 11016627 | 152591101 | SUMMIT 1101 | 6627 | TRUE | 910.3808 | 910.3808 | 0.56581 | 8 | 0.00010404 | 1550 | 0.066431 | 3048 | 6.9114e-06 | 5.5291e-05 | 3170 | 0.03 | 2267
6657 | SAN RAFAEL 110168970 | 42011101 | SAN RAFAEL 1101 | 68970 | TRUE | 5207.2001 | 75.6257 | 0.047002 | 44 | 0.00010579 | 1501 | 0.065151 | 3565 | 6.892e-06 | 0.00030325 | 3171 | 0.08 | 1617
8713 | GANSNER 1101489276 | 103021101 | GANSNER 1101 | 489276 | TRUE | 1058.1278 | 723.7002 | 0.44978 | 9 | 0.00010344 | 1561 | 0.066147 | 3182 | 6.8546e-06 | 6.1691e-05 | 3172 |  | 3253
6405 | ROB ROY 210571630 | 83692105 | ROB ROY 2105 | 71630 | FALSE | 3041.9597 | 2182.1843 | 1.3562 | 26 | 0.00010295 | 1569 | 0.066037 | 3211 | 6.8241e-06 | 0.00017743 | 3173 | 0.21 | 1143
1284 | SARATOGA 1106LC22 | 83371106 | SARATOGA 1106 | LC22 | FALSE | 13269.3389 | 12038.7869 | 7.4822 | 114 | 0.0001028 | 1575 | 0.066274 | 3155 | 6.8223e-06 | 0.00077774 | 3174 | 0.08 | 1600
4762 | SAN RAFAEL 110668694 | 42011106 | SAN RAFAEL 1106 | 68694 | TRUE | 3377.3751 | 0 | 0 | 32 | 0.00010397 | 1554 | 0.065151 | 3573 | 6.7736e-06 | 0.00021675 | 3175 |  | 2914
9002 | PAUL SWEET 2102168368 | 83252102 | PAUL SWEET 2102 | 168368 | TRUE | 1090.7031 | 590.4471 | 0.36697 | 8 | 0.00010339 | 1562 | 0.065308 | 3460 | 6.7491e-06 | 5.3993e-05 | 3176 |  | 3294
8371 | RINCON 1102782389 | 43321102 | RINCON 1102 | 782389 | TRUE | 861.6016 | 585.9597 | 0.36418 | 8 | 0.00010151 | 1617 | 0.065955 | 3232 | 6.7151e-06 | 5.3721e-05 | 3177 |  | 3216
7829 | UKIAH 111472990 | 42771114 | UKIAH 1114 | 72990 | FALSE | 5262.4562 | 1175.6663 | 0.73068 | 38 | 0.00010233 | 1594 | 0.065487 | 3374 | 6.7147e-06 | 0.00025516 | 3178 | 0.03 | 2293
4895 | SARATOGA 1103LC16 | 83371103 | SARATOGA 1103 | LC16 | FALSE | 8170.2082 | 6889.2884 | 4.2817 | 72 | 0.00010102 | 1624 | 0.066218 | 3168 | 6.7061e-06 | 0.00048284 | 3179 | 0.17 | 1248
2902 | WAYNE 0401954811 | 13810401 | WAYNE 0401 | 954811 | TRUE | 903.9347 | 282.8935 | 0.17582 | 9 | 0.00010244 | 1591 | 0.065576 | 3345 | 6.7055e-06 | 6.0349e-05 | 3180 |  | 2805
6002 | SAN RAFAEL 1105818262 | 42011105 | SAN RAFAEL 1105 | 818262 | TRUE | 1433.202 | 292.9133 | 0.18205 | 11 | 0.00010153 | 1615 | 0.0655 | 3368 | 6.6573e-06 | 7.3231e-05 | 3181 |  | 2994
9719 | PIT NO 5 11011614 | 101321101 | PIT NO 5 1101 | 1614 | FALSE | 3000.4112 | 3000.4112 | 1.8648 | 5 | 0.00010012 | 1643 | 9.5753 | 2631 | 6.6513e-06 | 3.3257e-05 | 3182 | 0.01 | 2585
5122 | RIDGE 0401CB | 12840401 | RIDGE 0401 | CB | FALSE | 4270.3121 | 4270.3121 | 2.654 | 36 | 0.00010003 | 1646 | 0.066396 | 3120 | 6.6432e-06 | 0.00023916 | 3183 | 0.08 | 1628
1193 | FORT BRAGG A 1102418 | 42761102 | FORT BRAGG A 1102 | 418 | FALSE | 22746.3302 | 22539.2945 | 14.0083 | 178 | 9.9716e-05 | 1655 | 0.066381 | 3126 | 6.6205e-06 | 0.0011785 | 3184 | 0.17 | 1236
8138 | FRANKLIN 1101P138 | 13921101 | FRANKLIN 1101 | P138 | FALSE | 2470.0232 | 2259.003 | 1.404 | 15 | 9.8986e-05 | 1670 | 0.066089 | 3200 | 6.5684e-06 | 9.8527e-05 | 3185 | 0.04 | 2093
11032 | HIGHLANDS 1101CB | 43361101 | HIGHLANDS 1101 | CB | TRUE | 42.5019 | 42.5019 | 0.026415 | 1 | 9.8387e-05 | 1681 | 0.066432 | 2999 | 6.536e-06 | 6.536e-06 | 3186 | 0.03 | 2336
3671 | CAMP EVERS 2104CB | 83622104 | CAMP EVERS 2104 | CB | TRUE | 5967.294 | 629.206 | 0.39105 | 71 | 9.9922e-05 | 1649 | 0.065224 | 3498 | 6.5265e-06 | 0.00046338 | 3187 | 0.18 | 1209
8113 | WOODSIDE 110411555 | 24251104 | WOODSIDE 1104 | 11555 | FALSE | 1379.9837 | 1379.9837 | 0.85767 | 11 | 9.8049e-05 | 1688 | 0.066432 | 2976 | 6.5136e-06 | 7.165e-05 | 3188 | 0.16 | 1271
8611 | CAROLANDS 04018888 | 24060401 | CAROLANDS 0401 | 8888 | TRUE | 2206.3607 | 0 | 0 | 25 | 9.99e-05 | 1651 | 0.065147 | 3614 | 6.5082e-06 | 0.0001627 | 3189 |  | 3244
10705 | CLOVERDALE 1102801904 | 42821102 | CLOVERDALE 1102 | 801904 | TRUE | 22.3881 | 22.3881 | 0.013914 | 1 | 8.2208e-05 | 2146 | 0.079148 | 2934 | 6.5066e-06 | 6.5066e-06 | 3190 | 0.06 | 1865
7620 | CASTRO VALLEY 1110MR341 | 14091110 | CASTRO VALLEY 1110 | MR341 | TRUE | 1045.185 | 417.225 | 0.25931 | 11 | 9.8401e-05 | 1680 | 0.065731 | 3300 | 6.5027e-06 | 7.1529e-05 | 3191 |  | 3142
6399 | ROB ROY 21049973 | 83692104 | ROB ROY 2104 | 9973 | TRUE | 921.5182 | 921.5182 | 0.57273 | 7 | 9.7761e-05 | 1697 | 0.066431 | 3072 | 6.4944e-06 | 4.5461e-05 | 3192 |  | 3027
4710 | VIEJO 220255787 | 182852202 | VIEJO 2202 | 55787 | TRUE | 58.9251 | 58.9251 | 0.036622 | 1 | 9.7709e-05 | 1699 | 0.066432 | 2989 | 6.491e-06 | 6.491e-06 | 3193 | 0.05 | 2023
3931 | LAS AROMAS 04013342 | 13600401 | LAS AROMAS 0401 | 3342 | FALSE | 3691.7497 | 3691.7497 | 2.2944 | 30 | 9.6371e-05 | 1724 | 0.066431 | 3097 | 6.402e-06 | 0.00019206 | 3194 | 0.04 | 2113
738 | SAN RAFAEL 1104CB | 42011104 | SAN RAFAEL 1104 | CB | FALSE | 16824.5332 | 5560.2483 | 3.4557 | 140 | 9.7183e-05 | 1710 | 0.065554 | 3352 | 6.3852e-06 | 0.00089393 | 3195 | 0.06 | 1789
9201 | HICKS 1116583284 | 83431116 | HICKS 1116 | 583284 | TRUE | 404.4133 | 236.5766 | 0.14703 | 4 | 9.5521e-05 | 1741 | 0.066111 | 3197 | 6.3368e-06 | 2.5347e-05 | 3196 |  | 3325
7050 | EAST QUINCY 1101678650 | 102551101 | EAST QUINCY 1101 | 678650 | FALSE | 2024.9152 | 1808.9819 | 1.1243 | 14 | 9.5259e-05 | 1757 | 0.066065 | 3203 | 6.2788e-06 | 8.7903e-05 | 3197 |  | 3091
9107 | OAKLAND K 1103CR422 | 12101103 | OAKLAND K 1103 | CR422 | FALSE | 3299.6109 | 3238.2816 | 2.0126 | 24 | 9.4398e-05 | 1783 | 0.066378 | 3128 | 6.2703e-06 | 0.00015049 | 3198 | 0.06 | 1855
2296 | LAURELES 11112028 | 182371111 | LAURELES 1111 | 2028 | FALSE | 14061.7847 | 14048.0686 | 8.7309 | 107 | 9.4213e-05 | 1788 | 0.06642 | 3114 | 6.2585e-06 | 0.00066966 | 3199 | 0.05 | 2036
4668 | KONOCTI 11084041 | 43311108 | KONOCTI 1108 | 4041 | FALSE | 7568.2918 | 2174.4689 | 1.3514 | 54 | 9.5438e-05 | 1746 | 0.065458 | 3394 | 6.2484e-06 | 0.00033741 | 3200 | 0.04 | 2187
4517 | SILVERADO 2105CB | 43432105 | SILVERADO 2105 | CB | FALSE | 7432.6484 | 1011.6246 | 0.62873 | 66 | 9.5309e-05 | 1754 | 0.065326 | 3450 | 6.2313e-06 | 0.00041127 | 3201 | 0.17 | 1235
1407 | SAN RAFAEL 11061230 | 42011106 | SAN RAFAEL 1106 | 1230 | FALSE | 7038.4432 | 1747.5573 | 1.0861 | 57 | 9.4865e-05 | 1770 | 0.065398 | 3418 | 6.2233e-06 | 0.00035473 | 3202 | 0.02 | 2465
7332 | LOS GATOS 1101184035 | 82021101 | LOS GATOS 1101 | 184035 | TRUE | 995.7775 | 905.936 | 0.56304 | 9 | 9.1457e-05 | 1859 | 0.066289 | 3152 | 6.0721e-06 | 5.4649e-05 | 3203 |  | 3118
10579 | SAN CARLOS 11049048 | 24181104 | SAN CARLOS 1104 | 9048 | TRUE | 24.5909 | 24.5909 | 0.015283 | 1 | 9.1221e-05 | 1871 | 0.066432 | 2958 | 6.06e-06 | 6.06e-06 | 3204 | 0.06 | 1869
2032 | LUCERNE 11031663 | 43351103 | LUCERNE 1103 | 1663 | FALSE | 1947.6462 | 1947.6462 | 1.2105 | 17 | 9.1109e-05 | 1877 | 0.066432 | 3000 | 6.0525e-06 | 0.00010289 | 3205 | 0.08 | 1656
9700 | SAN RAMON 2103MR279 | 14232103 | SAN RAMON 2103 | MR279 | TRUE | 323.7748 | 4.572 | 0.0028415 | 5 | 9.2277e-05 | 1836 | 0.065405 | 3413 | 6.0521e-06 | 3.0261e-05 | 3206 |  | 3402
5325 | SAN RAFAEL 1105534 | 42011105 | SAN RAFAEL 1105 | 534 | FALSE | 2541.7011 | 1569.6662 | 0.97555 | 22 | 9.1303e-05 | 1866 | 0.065908 | 3243 | 6.0384e-06 | 0.00013284 | 3207 | 0.08 | 1668
8122 | HATTON 1101CB | 182291101 | HATTON 1101 | CB | FALSE | 2551.5911 | 2551.5911 | 1.5858 | 22 | 9.066e-05 | 1892 | 0.066432 | 2986 | 6.0227e-06 | 0.0001325 | 3208 | 0.07 | 1703
6886 | ALTO 1124526955 | 42031124 | ALTO 1124 | 526955 | TRUE | 753.5469 | 713.9611 | 0.44373 | 6 | 9.0519e-05 | 1897 | 0.066431 | 3022 | 6.0133e-06 | 3.608e-05 | 3209 |  | 3070
5909 | CAMP EVERS 210392582 | 83622103 | CAMP EVERS 2103 | 92582 | TRUE | 4514.9648 | 245.7655 | 0.15274 | 41 | 9.2095e-05 | 1840 | 0.065147 | 3619 | 5.9997e-06 | 0.00024599 | 3210 | 0.07 | 1704
6632 | SAN RAFAEL 1106588020 | 42011106 | SAN RAFAEL 1106 | 588020 | TRUE | 2885.7528 | 385.2385 | 0.23943 | 19 | 9.1832e-05 | 1849 | 0.065219 | 3500 | 5.9904e-06 | 0.00011382 | 3211 |  | 3050
763 | LOS GATOS 1108LB86 | 82021108 | LOS GATOS 1108 | LB86 | FALSE | 8620.4875 | 7270.7679 | 4.5188 | 69 | 8.9584e-05 | 1927 | 0.066208 | 3169 | 5.9458e-06 | 0.00041026 | 3212 | 0.13 | 1335
10570 | EL CERRITO G 1105BR164 | 12501105 | EL CERRITO G 1105 | BR164 | TRUE | 91.5845 | 91.5845 | 0.05692 | 2 | 8.9373e-05 | 1935 | 0.066432 | 2968 | 5.9372e-06 | 1.1874e-05 | 3213 | 0.05 | 1944
9932 | ALTO 1125291744 | 42031125 | ALTO 1125 | 291744 | TRUE | 231.1314 | 195.7909 | 0.12168 | 3 | 9.0072e-05 | 1908 | 0.066004 | 3218 | 5.9276e-06 | 1.7783e-05 | 3214 |  | 3455
8178 | DOLAN ROAD 1101156268 | 182381101 | DOLAN ROAD 1101 | 156268 | TRUE | 3622.1133 | 52.7453 | 0.032781 | 31 | 9.074e-05 | 1891 | 0.065189 | 3522 | 5.914e-06 | 0.00018333 | 3215 |  | 3199
6600 | VIEJO 2202CB | 182852202 | VIEJO 2202 | CB | FALSE | 3450.2108 | 3450.2108 | 2.1443 | 23 | 8.8928e-05 | 1953 | 0.066432 | 2985 | 5.9077e-06 | 0.00013588 | 3216 | 1.33 | 684
4067 | LAS AROMAS 0401LA401R | 13600401 | LAS AROMAS 0401 | LA401R | FALSE | 6369.4185 | 4956.3951 | 3.0804 | 55 | 8.9288e-05 | 1939 | 0.066129 | 3184 | 5.9068e-06 | 0.00032487 | 3217 | 0.06 | 1827
807 | RESEARCH 210263274 | 14692102 | RESEARCH 2102 | 63274 | TRUE | 13077.1161 | 74.3652 | 0.046218 | 119 | 8.9998e-05 | 1914 | 0.06516 | 3555 | 5.8646e-06 | 0.00069789 | 3218 | 1.68 | 654
10104 | LAKEWOOD 1102964292 | 13531102 | LAKEWOOD 1102 | 964292 | TRUE | 128.1599 | 128.1599 | 0.079652 | 2 | 8.8164e-05 | 1978 | 0.066432 | 2995 | 5.8569e-06 | 1.1714e-05 | 3219 |  | 3491
8987 | ROSSMOOR 110181770 | 14161101 | ROSSMOOR 1101 | 81770 | TRUE | 2254.8682 | 110.4225 | 0.068628 | 21 | 8.9058e-05 | 1945 | 0.065148 | 3588 | 5.8019e-06 | 0.00012184 | 3220 |  | 3289
9943 | FRANKLIN 1104P136 | 13921104 | FRANKLIN 1104 | P136 | FALSE | 9489.9011 | 7931.4997 | 4.9295 | 43 | 8.0523e-05 | 2191 | 0.07255 | 2940 | 5.7997e-06 | 0.00024939 | 3221 | 0.03 | 2269
9679 | DOBBINS 1101CB | 153741101 | DOBBINS 1101 | CB | FALSE | 1079.0936 | 1079.0936 | 0.67066 | 8 | 8.7249e-05 | 2007 | 0.066432 | 3012 | 5.7961e-06 | 4.6369e-05 | 3222 | 0.06 | 1836
734 | SILVERADO 21051308 | 43432105 | SILVERADO 2105 | 1308 | TRUE | 7407.352 | 244.9631 | 0.15225 | 60 | 8.8597e-05 | 1969 | 0.065216 | 3502 | 5.7874e-06 | 0.00034724 | 3223 | 8.14 | 435
5907 | ORINDA 0401401/2 LR | 12350401 | ORINDA 0401 | 401/2 LR | TRUE | 235.881 | 158.249 | 0.098352 | 4 | 8.7563e-05 | 1998 | 0.066112 | 3187 | 5.7731e-06 | 2.3093e-05 | 3224 |  | 2987
648 | KONOCTI 11084039 | 43311108 | KONOCTI 1108 | 4039 | FALSE | 3724.1919 | 3048.4169 | 1.8946 | 32 | 8.7081e-05 | 2010 | 0.066191 | 3171 | 5.7609e-06 | 0.00018435 | 3225 | 0.06 | 1903
5547 | KONOCTI 11084037 | 43311108 | KONOCTI 1108 | 4037 | FALSE | 2780.393 | 1840.2464 | 1.1437 | 22 | 8.7734e-05 | 1991 | 0.065616 | 3331 | 5.7543e-06 | 0.0001266 | 3226 | 0.04 | 2149
3274 | RACETRACK 170310850 | 163761703 | RACETRACK 1703 | 10850 | TRUE | 3044.0072 | 994.8842 | 0.61832 | 28 | 8.6545e-05 | 2022 | 0.065652 | 3324 | 5.704e-06 | 0.00015971 | 3227 | 0.04 | 2091
5740 | SUMMIT 110148636 | 152591101 | SUMMIT 1101 | 48636 | TRUE | 4495.7291 | 86.4222 | 0.053712 | 38 | 8.7238e-05 | 2008 | 0.065185 | 3527 | 5.6861e-06 | 0.00021607 | 3228 | 0.01 | 2615
8762 | VASONA 1102944560 | 83771102 | VASONA 1102 | 944560 | TRUE | 944.5774 | 282.6401 | 0.17566 | 9 | 8.6599e-05 | 2020 | 0.065433 | 3404 | 5.6635e-06 | 5.0971e-05 | 3229 |  | 3260
5538 | BERKELEY F 1103162952 | 12061103 | BERKELEY F 1103 | 162952 | FALSE | 3475.2506 | 2846.7585 | 1.7693 | 25 | 8.5367e-05 | 2045 | 0.066175 | 3178 | 5.6583e-06 | 0.00014146 | 3230 |  | 2962
319 | DUNBAR 1103725292 | 43071103 | DUNBAR 1103 | 725292 | TRUE | 1519.9145 | 339.5862 | 0.21105 | 13 | 8.6305e-05 | 2027 | 0.065451 | 3395 | 5.658e-06 | 7.3554e-05 | 3231 |  | 2665
5356 | SOBRANTE 110142914 | 14671101 | SOBRANTE 1101 | 42914 | TRUE | 6917.2252 | 665.6425 | 0.4137 | 51 | 8.6589e-05 | 2021 | 0.065332 | 3443 | 5.6577e-06 | 0.00028854 | 3232 | 0.03 | 2387
4656 | OAKLAND K 1104CR208 | 12101104 | OAKLAND K 1104 | CR208 | FALSE | 3895.4111 | 3895.4111 | 2.421 | 29 | 8.498e-05 | 2061 | 0.066431 | 3052 | 5.6453e-06 | 0.00016371 | 3233 | 0.19 | 1185
1498 | SAN RAFAEL 1101189400 | 42011101 | SAN RAFAEL 1101 | 189400 | FALSE | 5552.3042 | 4446.7436 | 2.7637 | 45 | 8.4949e-05 | 2063 | 0.066033 | 3212 | 5.6305e-06 | 0.00025337 | 3234 |  | 2728
9302 | NEWBURG 1131987158 | 192151131 | NEWBURG 1131 | 987158 | TRUE | 443.4139 | 397.6831 | 0.24716 | 2 | 8.4891e-05 | 2066 | 0.06579 | 3277 | 5.6215e-06 | 1.1243e-05 | 3235 |  | 3339
1260 | PALO SECO 0401CB | 13180401 | PALO SECO 0401 | CB | FALSE | 7634.7258 | 7634.7258 | 4.745 | 55 | 8.4537e-05 | 2075 | 0.066409 | 3116 | 5.6154e-06 | 0.00030885 | 3236 | 0.16 | 1263
7087 | OAKLAND K 1101CR170 | 12101101 | OAKLAND K 1101 | CR170 | FALSE | 2012.9175 | 2012.9175 | 1.251 | 17 | 8.3822e-05 | 2100 | 0.066432 | 2973 | 5.5684e-06 | 9.4663e-05 | 3237 | 0.21 | 1138
9325 | TASSAJARA 2108189700 | 14662108 | TASSAJARA 2108 | 189700 | TRUE | 2164.8558 | 306.7254 | 0.19063 | 22 | 8.5054e-05 | 2057 | 0.065265 | 3473 | 5.5512e-06 | 0.00012213 | 3238 |  | 3343
8529 | ROSSMOOR 110479146 | 14161104 | ROSSMOOR 1104 | 79146 | TRUE | 3115.0804 | 85.6157 | 0.05321 | 28 | 8.3512e-05 | 2114 | 0.065194 | 3514 | 5.451e-06 | 0.00015263 | 3239 | 0.02 | 2490
5159 | PAUL SWEET 2109634576 | 83252109 | PAUL SWEET 2109 | 634576 | FALSE | 3306.7049 | 2935.0444 | 1.8241 | 29 | 8.2017e-05 | 2152 | 0.066255 | 3159 | 5.4462e-06 | 0.00015794 | 3240 |  | 2939
176 | TASSAJARA 2108D520R | 14662108 | TASSAJARA 2108 | D520R | TRUE | 5652.8623 | 0 | 0 | 50 | 8.3586e-05 | 2109 | 0.065148 | 3583 | 5.4455e-06 | 0.00027228 | 3241 |  | 2659
2934 | LAKEWOOD 210769586 | 13532107 | LAKEWOOD 2107 | 69586 | TRUE | 9651.4745 | 688.9218 | 0.42817 | 80 | 8.3471e-05 | 2116 | 0.065228 | 3492 | 5.4423e-06 | 0.00043538 | 3242 | 0.02 | 2429
2160 | HIGHLANDS 1104CB | 43361104 | HIGHLANDS 1104 | CB | FALSE | 13332.3504 | 7661.9306 | 4.7619 | 102 | 7.7932e-05 | 2261 | 0.072303 | 2941 | 5.4342e-06 | 0.00055429 | 3243 | 0.07 | 1735
7487 | GANSNER 1101174072 | 103021101 | GANSNER 1101 | 174072 | TRUE | 172.7033 | 172.7033 | 0.10734 | 3 | 8.1758e-05 | 2162 | 0.066004 | 3219 | 5.3939e-06 | 1.6182e-05 | 3244 |  | 3129
10550 | SANTA ROSA A 1104834094 | 42151104 | SANTA ROSA A 1104 | 834094 | TRUE | 201.2345 | 155.4829 | 0.096633 | 3 | 8.2e-05 | 2155 | 0.065582 | 3337 | 5.3913e-06 | 1.6174e-05 | 3245 |  | 3572
6137 | CAROLANDS 04049024 | 24060404 | CAROLANDS 0404 | 9024 | FALSE | 6139.1912 | 5646.8015 | 3.5095 | 62 | 8.1167e-05 | 2180 | 0.066328 | 3141 | 5.3873e-06 | 0.00033401 | 3246 | 0.12 | 1406
8307 | SAN RAFAEL 11042235 | 42011104 | SAN RAFAEL 1104 | 2235 | TRUE | 1389.3312 | 296.6637 | 0.18438 | 10 | 8.163e-05 | 2164 | 0.065407 | 3411 | 5.3477e-06 | 5.3477e-05 | 3247 | 0.03 | 2392
4970 | CASTRO VALLEY 1110264914 | 14091110 | CASTRO VALLEY 1110 | 264914 | FALSE | 1490.2678 | 1396.6171 | 0.868 | 14 | 8.0285e-05 | 2197 | 0.066248 | 3164 | 5.3219e-06 | 7.4507e-05 | 3248 |  | 2934
6336 | SAN RAFAEL 1101310 | 42011101 | SAN RAFAEL 1101 | 310 | TRUE | 5801.4081 | 319.7974 | 0.19876 | 48 | 8.1312e-05 | 2173 | 0.065285 | 3466 | 5.3143e-06 | 0.00025509 | 3249 | 0.63 | 836
5625 | LAURELES 11116617 | 182371111 | LAURELES 1111 | 6617 | FALSE | 2923.677 | 2923.677 | 1.8171 | 13 | 7.8082e-05 | 2257 | 0.068388 | 2946 | 5.304e-06 | 6.8952e-05 | 3250 | 1.03 | 726
4819 | GANSNER 1101590690 | 103021101 | GANSNER 1101 | 590690 | TRUE | 383.2694 | 102.0304 | 0.063412 | 4 | 8.1235e-05 | 2176 | 0.065148 | 3587 | 5.2923e-06 | 2.1169e-05 | 3251 |  | 2919
3357 | TASSAJARA 210812712 | 14662108 | TASSAJARA 2108 | 12712 | FALSE | 5357.9341 | 1227.8521 | 0.76312 | 46 | 8.0658e-05 | 2189 | 0.065483 | 3376 | 5.2813e-06 | 0.00024294 | 3252 | 10.37 | 397
4164 | ELK 11014628 | 42981101 | ELK 1101 | 4628 | FALSE | 6688.9793 | 3975.7324 | 2.4709 | 54 | 7.9821e-05 | 2212 | 0.065813 | 3262 | 5.2551e-06 | 0.00028378 | 3253 | 0.03 | 2361
5329 | ROSSMOOR 1106L522R | 14161106 | ROSSMOOR 1106 | L522R | FALSE | 6797.2077 | 3031.8636 | 1.8843 | 56 | 7.9525e-05 | 2221 | 0.065744 | 3296 | 5.255e-06 | 0.00029428 | 3254 | 1.17 | 704
10811 | STAFFORD 1101803535 | 43201101 | STAFFORD 1101 | 803535 | TRUE | 262.4984 | 262.4984 | 0.16314 | 3 | 7.8567e-05 | 2247 | 0.066431 | 3038 | 5.2193e-06 | 1.5658e-05 | 3255 |  | 3608
7133 | DEL MONTE 21032000 | 182222103 | DEL MONTE 2103 | 2000 | FALSE | 14495.3301 | 14495.3301 | 9.0089 | 101 | 7.8422e-05 | 2249 | 0.066432 | 2979 | 5.2097e-06 | 0.00052618 | 3256 | 0.12 | 1391
5982 | SAN RAFAEL 1107434 | 42011107 | SAN RAFAEL 1107 | 434 | TRUE | 1839.9407 | 49.2215 | 0.030591 | 16 | 7.9657e-05 | 2216 | 0.065231 | 3489 | 5.2024e-06 | 8.3238e-05 | 3257 |  | 2993
7562 | IGNACIO 1105784032 | 42481105 | IGNACIO 1105 | 784032 | TRUE | 974.4826 | 863.751 | 0.53682 | 11 | 7.8303e-05 | 2251 | 0.066199 | 3170 | 5.1906e-06 | 5.7096e-05 | 3258 |  | 3137
4422 | ROSSMOOR 1106CB | 14161106 | ROSSMOOR 1106 | CB | FALSE | 7735.7733 | 2937.1415 | 1.8254 | 60 | 7.5124e-05 | 2330 | 1.6497 | 2856 | 5.1594e-06 | 0.00030957 | 3259 | 0.22 | 1133
788 | OAKLAND K 1104CR210 | 12101104 | OAKLAND K 1104 | CR210 | FALSE | 4546.547 | 4546.547 | 2.8257 | 35 | 7.7661e-05 | 2270 | 0.066431 | 3091 | 5.1591e-06 | 0.00018057 | 3260 | 0.14 | 1309
5398 | HARTLEY 1101471 | 43211101 | HARTLEY 1101 | 471 | TRUE | 2001.813 | 0 | 0 | 16 | 7.9063e-05 | 2233 | 0.06523 | 3491 | 5.1543e-06 | 8.2468e-05 | 3261 | 0.33 | 988
3021 | SAN RAFAEL 1101494 | 42011101 | SAN RAFAEL 1101 | 494 | FALSE | 14793.4066 | 9034.9185 | 5.6152 | 114 | 7.7057e-05 | 2285 | 0.06596 | 3230 | 5.1065e-06 | 0.00058215 | 3262 | 0.23 | 1112
2946 | WOODSIDE 11049116 | 24251104 | WOODSIDE 1104 | 9116 | FALSE | 6878.1556 | 1335.9769 | 0.83032 | 53 | 7.7353e-05 | 2280 | 0.065341 | 3442 | 5.0499e-06 | 0.00026765 | 3263 | 0.08 | 1597
8964 | MARIPOSA 2102527766 | 254452102 | MARIPOSA 2102 | 527766 | TRUE | 66.9649 | 66.9649 | 0.041619 | 1 | 7.5879e-05 | 2310 | 0.066432 | 2954 | 5.0408e-06 | 5.0408e-06 | 3264 |  | 3285
8147 | LAS GALLINAS A 1105648439 | 42991105 | LAS GALLINAS A 1105 | 648439 | TRUE | 225.8757 | 10.9115 | 0.0067816 | 3 | 7.7251e-05 | 2281 | 0.065151 | 3571 | 5.033e-06 | 1.5099e-05 | 3265 |  | 3196
6797 | EMERALD LAKE 04028858 | 24080402 | EMERALD LAKE 0402 | 8858 | FALSE | 3073.6226 | 3073.6226 | 1.9103 | 27 | 7.5167e-05 | 2327 | 0.066432 | 2966 | 4.9935e-06 | 0.00013482 | 3266 | 0.08 | 1631
8050 | BIG RIVER 11015065 | 43081101 | BIG RIVER 1101 | 5065 | FALSE | 3543.5774 | 3543.5774 | 2.2023 | 27 | 7.4898e-05 | 2334 | 0.066432 | 2987 | 4.9756e-06 | 0.00013434 | 3267 | 0.1 | 1465
6040 | RACETRACK 17032553 | 163761703 | RACETRACK 1703 | 2553 | FALSE | 3992.3117 | 1548.3173 | 0.96229 | 32 | 7.5372e-05 | 2324 | 0.065669 | 3318 | 4.9535e-06 | 0.00015851 | 3268 | 0.05 | 2058
4959 | VALLEY VIEW 1105305072 | 14341105 | VALLEY VIEW 1105 | 305072 | FALSE | 6216.8943 | 5044.0425 | 3.1349 | 45 | 7.4673e-05 | 2341 | 0.066118 | 3185 | 4.9532e-06 | 0.0002229 | 3269 |  | 2933
1675 | CASTRO VALLEY 1111227862 | 14091111 | CASTRO VALLEY 1111 | 227862 | TRUE | 2810.7104 | 319.3369 | 0.19847 | 26 | 7.5864e-05 | 2311 | 0.065246 | 3481 | 4.952e-06 | 0.00012875 | 3270 |  | 2736
9676 | PACIFICA 1103885952 | 22811103 | PACIFICA 1103 | 885952 | TRUE | 299.4502 | 283.4481 | 0.17616 | 4 | 7.3952e-05 | 2360 | 0.066111 | 3195 | 4.9074e-06 | 1.963e-05 | 3271 |  | 3397
8421 | EL CERRITO G 1112779030 | 12501112 | EL CERRITO G 1112 | 779030 | TRUE | 1061.942 | 827.4759 | 0.51428 | 11 | 7.3516e-05 | 2383 | 0.066315 | 3145 | 4.881e-06 | 5.3691e-05 | 3272 |  | 3224
2317 | VACAVILLE 1112CB | 63601112 | VACAVILLE 1112 | CB | TRUE | 5313.0282 | 378.608 | 0.23531 | 52 | 7.4297e-05 | 2349 | 0.065199 | 3510 | 4.847e-06 | 0.00025204 | 3273 |  | 2771
2187 | NEWBURG 1131CB | 192151131 | NEWBURG 1131 | CB | TRUE | 10978.5428 | 257.3233 | 0.15993 | 91 | 7.4003e-05 | 2358 | 0.2391 | 2928 | 4.8414e-06 | 0.00044057 | 3274 | 0.04 | 2111
8107 | EMERALD LAKE 0402CB | 24080402 | EMERALD LAKE 0402 | CB | FALSE | 3052.0291 | 3052.0291 | 1.8968 | 23 | 7.2318e-05 | 2409 | 0.066432 | 2962 | 4.8042e-06 | 0.0001105 | 3275 | 0.1 | 1457
1133 | SAN CARLOS 1103586832 | 24181103 | SAN CARLOS 1103 | 586832 | FALSE | 6692.9945 | 6145.6408 | 3.8195 | 53 | 7.2377e-05 | 2406 | 0.066311 | 3146 | 4.7995e-06 | 0.00025437 | 3276 |  | 2711
9839 | SAN RAFAEL 11073323 | 42011107 | SAN RAFAEL 1107 | 3323 | TRUE | 214.7286 | 214.7286 | 0.13345 | 2 | 7.1735e-05 | 2429 | 0.066431 | 3042 | 4.7655e-06 | 9.5309e-06 | 3277 | 0.27 | 1051
3598 | PAUL SWEET 210210290 | 83252102 | PAUL SWEET 2102 | 10290 | TRUE | 9277.251 | 4.572 | 0.0028415 | 75 | 7.2679e-05 | 2399 | 0.065164 | 3550 | 4.7388e-06 | 0.00035541 | 3278 |  | 2841
4237 | PAUL SWEET 2109687295 | 83252109 | PAUL SWEET 2109 | 687295 | FALSE | 1495.545 | 1495.545 | 0.92949 | 14 | 7.0919e-05 | 2445 | 0.066432 | 2963 | 4.7113e-06 | 6.5958e-05 | 3279 |  | 2878
4104 | GREENBRAE 1103CB | 43091103 | GREENBRAE 1103 | CB | TRUE | 6661.6605 | 0 | 0 | 61 | 7.201e-05 | 2419 | 0.065151 | 3564 | 4.6915e-06 | 0.00028618 | 3280 | 0.11 | 1448
9040 | SAN RAFAEL 1101CB | 42011101 | SAN RAFAEL 1101 | CB | TRUE | 1531.5459 | 0 | 0 | 17 | 7.1938e-05 | 2422 | 0.065151 | 3566 | 4.6868e-06 | 7.9676e-05 | 3281 | 0.25 | 1083
9787 | ATASCADERO 1103395936 | 182541103 | ATASCADERO 1103 | 395936 | TRUE | 1081.2511 | 685.7662 | 0.42621 | 6 | 7.0765e-05 | 2449 | 0.066004 | 3222 | 4.6656e-06 | 2.7994e-05 | 3282 |  | 3422
3209 | ROB ROY 210512474 | 83692105 | ROB ROY 2105 | 12474 | FALSE | 13789.0355 | 5487.3001 | 3.4104 | 105 | 7.0779e-05 | 2448 | 0.065612 | 3333 | 4.6505e-06 | 0.00048831 | 3283 | 0.04 | 2152
10084 | SAN RAFAEL 1106307651 | 42011106 | SAN RAFAEL 1106 | 307651 | TRUE | 416.3767 | 169.0436 | 0.10506 | 4 | 7.1015e-05 | 2444 | 0.065151 | 3569 | 4.6267e-06 | 1.8507e-05 | 3284 |  | 3486
8574 | BIG RIVER 1101262924 | 43081101 | BIG RIVER 1101 | 262924 | FALSE | 3139.8868 | 3032.2865 | 1.8846 | 30 | 6.9614e-05 | 2485 | 0.066389 | 3125 | 4.6224e-06 | 0.00013867 | 3285 |  | 3238
9375 | BIG MEADOWS 2101439 | 102812101 | BIG MEADOWS 2101 | 439 | FALSE | 1501.1745 | 1069.2533 | 0.66455 | 12 | 7.0104e-05 | 2470 | 0.066111 | 3191 | 4.6178e-06 | 5.5413e-05 | 3286 | 1.58 | 664
10457 | ALTO 1124319320 | 42031124 | ALTO 1124 | 319320 | TRUE | 221.6252 | 210.6172 | 0.1309 | 3 | 7.001e-05 | 2472 | 0.065578 | 3340 | 4.6148e-06 | 1.3844e-05 | 3287 |  | 3552
9137 | BERKELEY F 1103620294 | 12061103 | BERKELEY F 1103 | 620294 | TRUE | 312.2722 | 249.6637 | 0.15517 | 4 | 7.0122e-05 | 2469 | 0.065468 | 3388 | 4.6109e-06 | 1.8443e-05 | 3288 |  | 3315
10199 | SALT SPRINGS 21023116 | 163692102 | SALT SPRINGS 2102 | 3116 | TRUE | 87.1475 | 87.1475 | 0.054163 | 2 | 6.9021e-05 | 2507 | 0.066431 | 3085 | 4.5851e-06 | 9.1703e-06 | 3289 |  | 3514
7887 | EAST QUINCY 1101782320 | 102551101 | EAST QUINCY 1101 | 782320 | TRUE | 606.8883 | 340.3108 | 0.2115 | 5 | 6.9413e-05 | 2491 | 0.065662 | 3321 | 4.5524e-06 | 2.2762e-05 | 3290 |  | 3175
5305 | SAN RAFAEL 1105CB | 42011105 | SAN RAFAEL 1105 | CB | TRUE | 14121.4272 | 0 | 0 | 124 | 6.9844e-05 | 2479 | 0.065151 | 3576 | 4.5504e-06 | 0.00056425 | 3291 | 0.02 | 2434
8451 | GUALALA 11124431 | 42841112 | GUALALA 1112 | 4431 | FALSE | 2379.8246 | 2267.622 | 1.4093 | 16 | 6.857e-05 | 2520 | 0.066271 | 3158 | 4.548e-06 | 7.2768e-05 | 3292 | 2.63 | 593
2628 | EAST QUINCY 1101186938 | 102551101 | EAST QUINCY 1101 | 186938 | FALSE | 4893.222 | 2672.105 | 1.6607 | 41 | 6.8848e-05 | 2512 | 0.0659 | 3245 | 4.5458e-06 | 0.00018638 | 3293 |  | 2792
8531 | VALLEY VIEW 1106602871 | 14341106 | VALLEY VIEW 1106 | 602871 | FALSE | 1324.4478 | 1324.4478 | 0.82315 | 14 | 6.84e-05 | 2525 | 0.06634 | 3137 | 4.5365e-06 | 6.3511e-05 | 3294 |  | 3232
6262 | HIGHLANDS 110448262 | 43361104 | HIGHLANDS 1104 | 48262 | FALSE | 9974.998 | 9974.998 | 6.1995 | 74 | 6.8225e-05 | 2528 | 0.066414 | 3115 | 4.5315e-06 | 0.00033533 | 3295 | 0.16 | 1266
3513 | FLORENCE 0401CR220 | 12690401 | FLORENCE 0401 | CR220 | TRUE | 2216.0779 | 325.3992 | 0.20224 | 19 | 6.9057e-05 | 2505 | 0.065417 | 3408 | 4.51e-06 | 8.5689e-05 | 3296 | 0.06 | 1884
5570 | SAN CARLOS 11048942 | 24181104 | SAN CARLOS 1104 | 8942 | FALSE | 4451.7025 | 3407.8974 | 2.118 | 35 | 6.7999e-05 | 2536 | 0.066102 | 3198 | 4.5084e-06 | 0.00015779 | 3297 | 0.07 | 1712
5867 | ARLINGTON 0401404226 | 13700401 | ARLINGTON 0401 | 404226 | FALSE | 1578.9748 | 1403.5728 | 0.87233 | 15 | 6.7624e-05 | 2545 | 0.066004 | 3221 | 4.4777e-06 | 6.7165e-05 | 3298 |  | 2985
1380 | HARRIS 11084674 | 192431108 | HARRIS 1108 | 4674 | TRUE | 11266.4783 | 72.8 | 0.045245 | 85 | 6.8436e-05 | 2524 | 0.065148 | 3604 | 4.4584e-06 | 0.00037897 | 3299 | 0.02 | 2468
7856 | FORT BRAGG A 1102CB | 42761102 | FORT BRAGG A 1102 | CB | FALSE | 9310.1865 | 3594.4279 | 2.234 | 73 | 6.7929e-05 | 2538 | 0.065429 | 3407 | 4.4533e-06 | 0.00032509 | 3300 | 0.03 | 2291
7134 | DEL MONTE 2103617344 | 182222103 | DEL MONTE 2103 | 617344 | FALSE | 3993.4046 | 2952.1893 | 1.8348 | 34 | 6.6754e-05 | 2562 | 0.065865 | 3252 | 4.4076e-06 | 0.00014986 | 3301 |  | 3099
3773 | RINCON 1104CB | 43321104 | RINCON 1104 | CB | TRUE | 3983.613 | 901.4332 | 0.56024 | 34 | 5.1406e-05 | 3008 | 0.069389 | 2944 | 4.3928e-06 | 0.00014935 | 3302 | 0.16 | 1257
7255 | VIEJO 2203CB | 182852203 | VIEJO 2203 | CB | FALSE | 5468.4733 | 4727.7308 | 2.9383 | 42 | 6.6223e-05 | 2583 | 0.066187 | 3172 | 4.392e-06 | 0.00018447 | 3303 | 0.12 | 1373
1976 | LAURELES 111268454 | 182371112 | LAURELES 1112 | 68454 | FALSE | 17728.9798 | 13589.2158 | 8.4458 | 142 | 6.656e-05 | 2571 | 0.066016 | 3214 | 4.3912e-06 | 0.00062355 | 3304 | 0.14 | 1311
1047 | DOLAN ROAD 110122158 | 182381101 | DOLAN ROAD 1101 | 22158 | TRUE | 14506.5343 | 184.8198 | 0.11487 | 119 | 6.7278e-05 | 2552 | 0.065158 | 3557 | 4.3836e-06 | 0.00052165 | 3305 | 0.04 | 2174
4984 | PAUL SWEET 210212850 | 83252102 | PAUL SWEET 2102 | 12850 | FALSE | 6644.9449 | 1063.4476 | 0.66094 | 52 | 6.6462e-05 | 2576 | 0.065295 | 3464 | 4.3733e-06 | 0.00022741 | 3306 | 0.02 | 2487
10216 | GUALALA 1111498 | 42841111 | GUALALA 1111 | 498 | FALSE | 4821.7264 | 4596.7491 | 2.8569 | 18 | 6.582e-05 | 2593 | 0.066146 | 3183 | 4.3648e-06 | 7.8567e-05 | 3307 | 0.05 | 1926
5466 | WEST POINT 11025357 | 163201102 | WEST POINT 1102 | 5357 | FALSE | 5401.7845 | 5401.7845 | 3.3572 | 37 | 6.5663e-05 | 2599 | 0.066432 | 2965 | 4.3621e-06 | 0.0001614 | 3308 | 10.09 | 402
5373 | VIEJO 22019490 | 182852201 | VIEJO 2201 | 9490 | FALSE | 2186.2244 | 2004.014 | 1.2455 | 21 | 6.5775e-05 | 2597 | 0.066187 | 3173 | 4.3539e-06 | 9.1432e-05 | 3309 | 0.07 | 1753
3074 | GANSNER 1101480328 | 103021101 | GANSNER 1101 | 480328 | TRUE | 859.3222 | 472.375 | 0.29358 | 7 | 6.5647e-05 | 2600 | 0.065698 | 3311 | 4.3254e-06 | 3.0278e-05 | 3310 |  | 2811
2211 | DEL MONTE 21032654 | 182222103 | DEL MONTE 2103 | 2654 | FALSE | 2963.5999 | 2963.5999 | 1.8419 | 23 | 6.4898e-05 | 2612 | 0.066432 | 2988 | 4.3113e-06 | 9.916e-05 | 3311 | 0.09 | 1555
8914 | CLAYTON 2217CB | 12022217 | CLAYTON 2217 | CB | TRUE | 1021.9623 | 373.7851 | 0.23231 | 8 | 6.5789e-05 | 2595 | 0.065148 | 3585 | 4.2861e-06 | 3.4288e-05 | 3312 |  | 3278
9870 | PUEBLO 2103253312 | 43292103 | PUEBLO 2103 | 253312 | TRUE | 698.8026 | 682.8006 | 0.42436 | 2 | 6.5784e-05 | 2596 | 713.1431 | 1011 | 4.2859e-06 | 8.5718e-06 | 3313 |  | 3438
10448 | DOLAN ROAD 1101173702 | 182381101 | DOLAN ROAD 1101 | 173702 | TRUE | 213.4901 | 86.6803 | 0.053872 | 3 | 6.5664e-05 | 2598 | 0.065148 | 3599 | 4.2778e-06 | 1.2834e-05 | 3314 |  | 3550
7265 | ALTO 112265474 | 42031122 | ALTO 1122 | 65474 | FALSE | 5862.6816 | 3837.7425 | 2.3852 | 47 | 6.4376e-05 | 2630 | 0.065968 | 3227 | 4.2638e-06 | 0.0002004 | 3315 | 0.05 | 2056
6511 | PACIFICA 1103218962 | 22811103 | PACIFICA 1103 | 218962 | TRUE | 167.2894 | 86.3363 | 0.053658 | 2 | 5.4301e-05 | 2937 | 0.078474 | 2935 | 4.2591e-06 | 8.5182e-06 | 3316 |  | 3037
10670 | VACAVILLE 1111772224 | 63601111 | VACAVILLE 1111 | 772224 | TRUE | 126.2491 | 91.9583 | 0.057152 | 2 | 6.4042e-05 | 2644 | 0.06579 | 3275 | 4.2158e-06 | 8.4316e-06 | 3317 |  | 3588
5386 | CAROLANDS 040484797 | 24060404 | CAROLANDS 0404 | 84797 | TRUE | 2211.5607 | 66.6995 | 0.041454 | 21 | 6.4533e-05 | 2626 | 0.065331 | 3445 | 4.2155e-06 | 8.8525e-05 | 3318 | 0.02 | 2441
1724 | LAURELES 1112CB | 182371112 | LAURELES 1112 | CB | TRUE | 3818.0634 | 493.1815 | 0.30651 | 38 | 6.4589e-05 | 2622 | 0.065215 | 3503 | 4.2137e-06 | 0.00016012 | 3319 | 0.01 | 2579
1512 | ATASCADERO 1102CB | 182541102 | ATASCADERO 1102 | CB | TRUE | 8168.5567 | 0 | 0 | 67 | 6.4156e-05 | 2638 | 0.065525 | 3359 | 4.207e-06 | 0.00028187 | 3320 |  | 2730
557 | GREENBRAE 11021254 | 43091102 | GREENBRAE 1102 | 1254 | FALSE | 15241.9933 | 9639.5738 | 5.991 | 130 | 6.3299e-05 | 2668 | 0.06587 | 3250 | 4.1869e-06 | 0.0005443 | 3321 | 0.81 | 771
9628 | SAN CARLOS 110436864 | 24181104 | SAN CARLOS 1104 | 36864 | TRUE | 910.3949 | 889.7222 | 0.55297 | 10 | 6.2904e-05 | 2685 | 0.066303 | 3147 | 4.1763e-06 | 4.1763e-05 | 3322 | 0.03 | 2369
7091 | HATTON 11029642 | 182291102 | HATTON 1102 | 9642 | FALSE | 1925.8934 | 1925.8934 | 1.197 | 18 | 6.2785e-05 | 2690 | 0.066432 | 2983 | 4.1709e-06 | 7.5077e-05 | 3323 | 0.04 | 2171
757 | LAKEWOOD 1102CB | 13531102 | LAKEWOOD 1102 | CB | TRUE | 15331.9124 | 23.5925 | 0.014663 | 121 | 6.3977e-05 | 2647 | 0.065159 | 3556 | 4.1691e-06 | 0.00050446 | 3324 | 0.02 | 2479
10987 | ECHO SUMMIT 1101CB | 158031101 | ECHO SUMMIT 1101 | CB | TRUE | 49.1761 | 49.1761 | 0.030563 | 1 | 6.2654e-05 | 2695 | 0.066431 | 3094 | 4.1622e-06 | 4.1622e-06 | 3325 | 0 | 2628
9358 | PACIFICA 1102267868 | 22811102 | PACIFICA 1102 | 267868 | FALSE | 1937.2772 | 1363.5441 | 0.84745 | 13 | 6.31e-05 | 2676 | 0.065839 | 3257 | 4.157e-06 | 5.4041e-05 | 3326 |  | 3346
5985 | BERESFORD 04039154 | 24040403 | BERESFORD 0403 | 9154 | FALSE | 10556.7719 | 6776.6762 | 4.2117 | 95 | 6.2892e-05 | 2686 | 0.065945 | 3236 | 4.1518e-06 | 0.00039442 | 3327 | 0.03 | 2237
7732 | BIG MEADOWS 21012510 | 102812101 | BIG MEADOWS 2101 | 2510 | FALSE | 14243.477 | 12778.5068 | 7.9419 | 22 | 6.2454e-05 | 2707 | 0.066023 | 3213 | 4.1333e-06 | 9.0933e-05 | 3328 | 0.02 | 2457
3692 | LAS GALLINAS A 1107554 | 42991107 | LAS GALLINAS A 1107 | 554 | TRUE | 4453.2978 | 52.9857 | 0.032931 | 35 | 6.333e-05 | 2667 | 0.065188 | 3524 | 4.1303e-06 | 0.00014456 | 3329 |  | 2848
7653 | WOOD 0401265211 | 13380401 | WOOD 0401 | 265211 | TRUE | 282.195 | 238.1693 | 0.14802 | 4 | 6.2639e-05 | 2696 | 0.065789 | 3282 | 4.1276e-06 | 1.651e-05 | 3330 |  | 3146
7212 | VIEJO 2201CB | 182852201 | VIEJO 2201 | CB | FALSE | 8287.061 | 8183.2875 | 5.0859 | 67 | 6.1848e-05 | 2725 | 0.066374 | 3130 | 4.1068e-06 | 0.00027516 | 3331 | 0.08 | 1652
4015 | DOLAN ROAD 11013012 | 182381101 | DOLAN ROAD 1101 | 3012 | TRUE | 22106.1049 | 301.9386 | 0.18766 | 160 | 6.253e-05 | 2701 | 0.065164 | 3551 | 4.0749e-06 | 0.00065198 | 3332 | 0.04 | 2138
6661 | HICKS 2103XR248 | 83432103 | HICKS 2103 | XR248 | TRUE | 2436.8191 | 0 | 0 | 22 | 6.254e-05 | 2700 | 0.065147 | 3632 | 4.0743e-06 | 8.9634e-05 | 3333 |  | 3052
9871 | SARATOGA 1103709451 | 83371103 | SARATOGA 1103 | 709451 | TRUE | 302.4738 | 302.4738 | 0.18799 | 5 | 6.0665e-05 | 2757 | 0.066432 | 2951 | 4.0301e-06 | 2.0151e-05 | 3334 |  | 3439
3396 | SARATOGA 1107CB | 83371107 | SARATOGA 1107 | CB | TRUE | 15770.5803 | 273.8424 | 0.17019 | 135 | 6.178e-05 | 2726 | 0.065185 | 3529 | 4.0299e-06 | 0.00054404 | 3335 | 0.02 | 2453
697 | SANTA ROSA A 1107CB | 42151107 | SANTA ROSA A 1107 | CB | FALSE | 9896.0278 | 4879.3813 | 3.0326 | 92 | 6.0199e-05 | 2766 | 0.065711 | 3305 | 3.9708e-06 | 0.00036531 | 3336 | 0.35 | 974
7511 | BERKELEY F 1105189500 | 12061105 | BERKELEY F 1105 | 189500 | FALSE | 1726.2402 | 1225.686 | 0.76177 | 17 | 6.0082e-05 | 2771 | 0.065903 | 3244 | 3.9708e-06 | 6.7503e-05 | 3337 |  | 3131
5683 | OAKLAND K 1104CB | 12101104 | OAKLAND K 1104 | CB | FALSE | 2366.505 | 2366.505 | 1.4708 | 17 | 5.9542e-05 | 2787 | 0.066432 | 2992 | 3.9555e-06 | 6.7244e-05 | 3338 | 0.14 | 1312
4165 | VIEJO 22022606 | 182852202 | VIEJO 2202 | 2606 | FALSE | 4663.4326 | 1279.376 | 0.79514 | 52 | 5.9834e-05 | 2780 | 0.065394 | 3420 | 3.9158e-06 | 0.00020362 | 3339 | 0.06 | 1806
5028 | PUEBLO 21031970 | 43292103 | PUEBLO 2103 | 1970 | TRUE | 6915.717 | 0 | 0 | 60 | 6.0013e-05 | 2774 | 0.065151 | 3563 | 3.9099e-06 | 0.00023459 | 3340 | 0.06 | 1913
4499 | MORGAN HILL 2109145998 | 83242109 | MORGAN HILL 2109 | 145998 | FALSE | 4112.6069 | 4027.966 | 2.5034 | 28 | 5.8787e-05 | 2812 | 0.066294 | 3151 | 3.8997e-06 | 0.00010919 | 3341 |  | 2898
1014 | VIEJO 22019114 | 182852201 | VIEJO 2201 | 9114 | FALSE | 11036.3123 | 10977.6209 | 6.8226 | 92 | 5.8649e-05 | 2817 | 0.066404 | 3117 | 3.8947e-06 | 0.00035832 | 3342 | 0.17 | 1246
230 | CAROLANDS 04049026 | 24060404 | CAROLANDS 0404 | 9026 | FALSE | 8105.233 | 1184.1509 | 0.73595 | 71 | 5.949e-05 | 2791 | 0.065382 | 3425 | 3.8932e-06 | 0.00027642 | 3343 | 0.03 | 2274
10928 | FORT ORD 21069656 | 182402106 | FORT ORD 2106 | 9656 | TRUE | 188.9883 | 188.9883 | 0.11746 | 2 | 5.8277e-05 | 2826 | 0.066432 | 2981 | 3.8714e-06 | 7.7429e-06 | 3344 |  | 3621
5034 | OAKLAND J 1102CR184 | 12091102 | OAKLAND J 1102 | CR184 | FALSE | 5568.9906 | 5568.9906 | 3.4612 | 43 | 5.7871e-05 | 2839 | 0.066432 | 2949 | 3.8445e-06 | 0.00016531 | 3345 | 0.05 | 2043
4211 | FAIRVIEW 2207P142 | 13432207 | FAIRVIEW 2207 | P142 | FALSE | 5002.4344 | 1963.5704 | 1.2204 | 41 | 5.8204e-05 | 2828 | 0.065555 | 3351 | 3.8432e-06 | 0.00015757 | 3346 | 0.02 | 2469
10430 | BELL 1107643778 | 152701107 | BELL 1107 | 643778 | TRUE | 406.3148 | 270.3051 | 0.168 | 4 | 5.7794e-05 | 2841 | 0.06547 | 3381 | 3.7919e-06 | 1.5168e-05 | 3347 |  | 3549
9697 | DOLAN ROAD 1101882610 | 182381101 | DOLAN ROAD 1101 | 882610 | TRUE | 653.6335 | 228.3158 | 0.1419 | 8 | 5.7922e-05 | 2838 | 0.065308 | 3458 | 3.7868e-06 | 3.0295e-05 | 3348 |  | 3400
238 | LOS GATOS 1102526868 | 82021102 | LOS GATOS 1102 | 526868 | FALSE | 2061.1443 | 1780.5165 | 1.1066 | 20 | 5.6772e-05 | 2867 | 0.066239 | 3165 | 3.7614e-06 | 7.5227e-05 | 3349 |  | 2663
7260 | SUMMIT 110158642 | 152591101 | SUMMIT 1101 | 58642 | FALSE | 2892.0319 | 2892.0319 | 1.7974 | 13 | 5.6521e-05 | 2871 | 0.066431 | 3049 | 3.7548e-06 | 4.8812e-05 | 3350 | 0.02 | 2501
535 | ATASCADERO 11012379 | 182541101 | ATASCADERO 1101 | 2379 | FALSE | 1171.3689 | 1171.3689 | 0.72801 | 11 | 5.6518e-05 | 2872 | 0.066432 | 2969 | 3.7546e-06 | 4.1301e-05 | 3351 | 0.09 | 1523
4492 | DEL MONTE 2103468158 | 182222103 | DEL MONTE 2103 | 468158 | TRUE | 1565.7596 | 826.6133 | 0.51374 | 12 | 5.6983e-05 | 2862 | 0.065469 | 3384 | 3.7407e-06 | 4.4889e-05 | 3352 |  | 2897
8753 | HALF MOON BAY 1102650808 | 24101102 | HALF MOON BAY 1102 | 650808 | TRUE | 998.3572 | 843.3592 | 0.52415 | 8 | 5.3264e-05 | 2957 | 0.068808 | 2945 | 3.6894e-06 | 2.9515e-05 | 3353 |  | 3257
43 | WOODSIDE 1104555372 | 24251104 | WOODSIDE 1104 | 555372 | FALSE | 6684.5288 | 6684.5288 | 4.1545 | 54 | 5.5277e-05 | 2905 | 0.066432 | 2978 | 3.6721e-06 | 0.0001983 | 3354 | 0.13 | 1342
10659 | ECHO SUMMIT 110155262 | 158031101 | ECHO SUMMIT 1101 | 55262 | TRUE | 266.534 | 266.534 | 0.16565 | 4 | 5.499e-05 | 2911 | 0.066431 | 3095 | 3.653e-06 | 1.4612e-05 | 3355 | 0.06 | 1866
7441 | SAN LUIS OBISPO 110596874 | 182631105 | SAN LUIS OBISPO 1105 | 96874 | FALSE | 1722.0177 | 1345.5157 | 0.83624 | 16 | 5.4971e-05 | 2913 | 0.06595 | 3234 | 3.6408e-06 | 5.8253e-05 | 3356 |  | 3127
9136 | VIEJO 2204CB | 182852204 | VIEJO 2204 | CB | FALSE | 4041.5057 | 3727.5543 | 2.3167 | 24 | 5.482e-05 | 2920 | 0.066271 | 3157 | 3.64e-06 | 8.736e-05 | 3357 | 0.04 | 2207
4971 | EDES 1112CR282 | 13681112 | EDES 1112 | CR282 | FALSE | 6573.0208 | 6573.0208 | 4.0852 | 45 | 5.4739e-05 | 2924 | 0.066432 | 2977 | 3.6364e-06 | 0.00016364 | 3358 | 0.06 | 1916
7343 | ATASCADERO 1101CB | 182541101 | ATASCADERO 1101 | CB | TRUE | 1686.9104 | 61.191 | 0.03803 | 24 | 5.5357e-05 | 2902 | 0.065254 | 3478 | 3.6135e-06 | 8.6724e-05 | 3359 | 0.03 | 2342
8700 | VIEJO 22029488 | 182852202 | VIEJO 2202 | 9488 | FALSE | 2122.5518 | 1460.401 | 0.90765 | 18 | 5.4746e-05 | 2923 | 0.06579 | 3279 | 3.6034e-06 | 6.486e-05 | 3360 | 0.02 | 2561
3541 | SEACLIFF 0402558727 | 83500402 | SEACLIFF 0402 | 558727 | TRUE | 2270.5335 | 217.1494 | 0.13496 | 22 | 5.4871e-05 | 2919 | 0.065381 | 3426 | 3.5926e-06 | 7.9037e-05 | 3361 |  | 2835
7420 | DEL MONTE 210342226 | 182222103 | DEL MONTE 2103 | 42226 | TRUE | 4032.3201 | 940.1806 | 0.58433 | 32 | 5.4774e-05 | 2922 | 0.065308 | 3457 | 3.588e-06 | 0.00011482 | 3362 |  | 3126
7115 | LAS GALLINAS A 1104309087 | 42991104 | LAS GALLINAS A 1104 | 309087 | TRUE | 645.6047 | 302.4969 | 0.188 | 6 | 5.4354e-05 | 2935 | 0.065578 | 3341 | 3.575e-06 | 2.145e-05 | 3363 |  | 3096
5040 | TEMPLETON 2112238418 | 183052112 | TEMPLETON 2112 | 238418 | TRUE | 1291.252 | 331.2384 | 0.20587 | 6 | 5.4643e-05 | 2928 | 0.065361 | 3433 | 3.5615e-06 | 2.1369e-05 | 3364 |  | 2935
77 | ALTO 1124428 | 42031124 | ALTO 1124 | 428 | TRUE | 2739.6912 | 0 | 0 | 21 | 5.3944e-05 | 2943 | 0.065212 | 3505 | 3.5167e-06 | 7.3852e-05 | 3365 | 0.37 | 964
288 | MORGAN HILL 2110XR326 | 83242110 | MORGAN HILL 2110 | XR326 | TRUE | 21948.0156 | 0 | 0 | 163 | 5.3862e-05 | 2945 | 0.065147 | 3608 | 3.509e-06 | 0.00057196 | 3366 | 0.04 | 2188
1912 | SANTA ROSA A 110439786 | 42151104 | SANTA ROSA A 1104 | 39786 | TRUE | 5442.5467 | 454.7368 | 0.28262 | 44 | 5.3497e-05 | 2950 | 0.065245 | 3482 | 3.496e-06 | 0.00015383 | 3367 | 0.21 | 1145
6503 | VIEJO 22029118 | 182852202 | VIEJO 2202 | 9118 | FALSE | 4822.7839 | 1265.7827 | 0.78669 | 41 | 5.3297e-05 | 2954 | 0.065429 | 3406 | 3.4915e-06 | 0.00014315 | 3368 | 0.42 | 936
4440 | SANTA ROSA A 1104991788 | 42151104 | SANTA ROSA A 1104 | 991788 | FALSE | 5495.9742 | 1222.0634 | 0.75952 | 43 | 5.288e-05 | 2971 | 0.065395 | 3419 | 3.4631e-06 | 0.00014892 | 3369 |  | 2890
8382 | MORGAN HILL 2109XR246 | 83242109 | MORGAN HILL 2109 | XR246 | TRUE | 6374.5348 | 71.5932 | 0.044495 | 61 | 5.3027e-05 | 2967 | 0.06519 | 3521 | 3.4559e-06 | 0.00021081 | 3370 |  | 3218
8657 | OCEANO 110376678 | 182601103 | OCEANO 1103 | 76678 | TRUE | 597.8557 | 88.7522 | 0.05516 | 8 | 5.2866e-05 | 2974 | 0.065468 | 3386 | 3.4511e-06 | 2.7609e-05 | 3371 | 0.02 | 2467
9324 | ECHO SUMMIT 1101741586 | 158031101 | ECHO SUMMIT 1101 | 741586 | FALSE | 1137.7952 | 1137.7952 | 0.70714 | 9 | 5.1683e-05 | 3002 | 0.066431 | 3093 | 3.4334e-06 | 3.09e-05 | 3372 |  | 3342
392 | BELMONT 11038958 | 24031103 | BELMONT 1103 | 8958 | FALSE | 9585.6333 | 5438.9297 | 3.3803 | 73 | 5.1694e-05 | 3001 | 0.065833 | 3259 | 3.4119e-06 | 0.00024907 | 3373 | 0.04 | 2204
9058 | LOS GATOS 1101502026 | 82021101 | LOS GATOS 1101 | 502026 | TRUE | 1729.6385 | 180.5393 | 0.11221 | 17 | 5.2048e-05 | 2992 | 0.065374 | 3427 | 3.4024e-06 | 5.784e-05 | 3374 |  | 3302
2028 | HICKS 1116LB16 | 83431116 | HICKS 1116 | LB16 | FALSE | 13211.9515 | 4399.0652 | 2.734 | 97 | 5.1468e-05 | 3006 | 0.065597 | 3335 | 3.3964e-06 | 0.00032945 | 3375 | 0.03 | 2296
10450 | OAKLAND J 1102951816 | 12091102 | OAKLAND J 1102 | 951816 | TRUE | 539.1734 | 539.1734 | 0.3351 | 6 | 5.1065e-05 | 3013 | 0.066431 | 3112 | 3.3923e-06 | 2.0354e-05 | 3376 |  | 3551
3081 | SARATOGA 1103LC40 | 83371103 | SARATOGA 1103 | LC40 | TRUE | 2260.1219 | 26.7728 | 0.016639 | 28 | 5.1876e-05 | 2996 | 0.065193 | 3517 | 3.3827e-06 | 9.4717e-05 | 3377 | 0.02 | 2440
5298 | SAN LEANDRO U 1109CR182 | 13111109 | SAN LEANDRO U 1109 | CR182 | FALSE | 7768.8154 | 7768.8154 | 4.8284 | 56 | 5.0879e-05 | 3018 | 0.066432 | 2959 | 3.38e-06 | 0.00018928 | 3378 | 0.15 | 1294
9781 | SAN LUIS OBISPO 1108903036 | 182631108 | SAN LUIS OBISPO 1108 | 903036 | TRUE | 576.6112 | 306.6437 | 0.19058 | 5 | 5.0816e-05 | 3019 | 0.065404 | 3415 | 3.3474e-06 | 1.6737e-05 | 3379 |  | 3419
1847 | ALTO 1122CB | 42031122 | ALTO 1122 | CB | FALSE | 5576.1236 | 3611.6831 | 2.2447 | 46 | 5.0453e-05 | 3026 | 0.065847 | 3255 | 3.3325e-06 | 0.0001533 | 3380 | 0.18 | 1221
559 | PACIFICA 110266732 | 22811102 | PACIFICA 1102 | 66732 | TRUE | 3298.663 | 334.9483 | 0.20817 | 23 | 5.0745e-05 | 3021 | 0.065259 | 3476 | 3.3135e-06 | 7.6211e-05 | 3381 | 0.04 | 2115
7812 | LUCERNE 11062355 | 43351106 | LUCERNE 1106 | 2355 | TRUE | 1676.4836 | 644.3598 | 0.40047 | 13 | 4.9957e-05 | 3038 | 0.065643 | 3325 | 3.2963e-06 | 4.2852e-05 | 3382 | 0.06 | 1797
9811 | PACIFICA 1103119798 | 22811103 | PACIFICA 1103 | 119798 | TRUE | 129.7041 | 129.7041 | 0.080612 | 2 | 4.9475e-05 | 3051 | 0.066432 | 2975 | 3.2867e-06 | 6.5735e-06 | 3383 |  | 3428
10195 | ALTO 112081716 | 42031120 | ALTO 1120 | 81716 | TRUE | 406.7505 | 406.7505 | 0.2528 | 5 | 4.9207e-05 | 3059 | 0.066432 | 2971 | 3.2689e-06 | 1.6345e-05 | 3384 |  | 3512
6620 | LOS GATOS 1101950286 | 82021101 | LOS GATOS 1101 | 950286 | FALSE | 1710.7995 | 1710.7995 | 1.0633 | 17 | 4.911e-05 | 3061 | 0.066432 | 2974 | 3.2625e-06 | 5.5462e-05 | 3385 |  | 3046
5964 | RALSTON 1102CB | 24141102 | RALSTON 1102 | CB | FALSE | 6891.3641 | 1520.1281 | 0.94477 | 66 | 4.9607e-05 | 3044 | 0.065478 | 3378 | 3.2502e-06 | 0.00021451 | 3386 | 0.05 | 2029
8215 | GREENBRAE 1104107508 | 43091104 | GREENBRAE 1104 | 107508 | TRUE | 282.9574 | 0 | 0 | 2 | 4.9331e-05 | 3054 | 0.065151 | 3568 | 3.214e-06 | 6.4279e-06 | 3387 |  | 3203
1635 | OAKLAND K 1101CR172 | 12101101 | OAKLAND K 1101 | CR172 | TRUE | 3350.0951 | 904.9661 | 0.56244 | 30 | 4.8943e-05 | 3065 | 0.065361 | 3434 | 3.209e-06 | 9.6271e-05 | 3388 | 0.05 | 2015
3774 | PAUL SWEET 210411074 | 83252104 | PAUL SWEET 2104 | 11074 | FALSE | 4972.7567 | 4718.31 | 2.9324 | 41 | 4.8374e-05 | 3082 | 0.066275 | 3154 | 3.1905e-06 | 0.00013081 | 3389 | 0.48 | 903
8087 | SAN RAMON 2107MR441 | 14232107 | SAN RAMON 2107 | MR441 | TRUE | 350.4949 | 40.2016 | 0.024985 | 8 | 4.8606e-05 | 3074 | 0.065309 | 3456 | 3.1892e-06 | 2.5513e-05 | 3390 |  | 3190
7720 | SAN RAFAEL 1106764698 | 42011106 | SAN RAFAEL 1106 | 764698 | TRUE | 357.0375 | 133.4071 | 0.082913 | 5 | 4.8608e-05 | 3073 | 0.065407 | 3412 | 3.1867e-06 | 1.5933e-05 | 3391 |  | 3156
3736 | VALLEY VIEW 1105P126 | 14341105 | VALLEY VIEW 1105 | P126 | FALSE | 3297.3508 | 1680.8363 | 1.0446 | 25 | 4.8344e-05 | 3085 | 0.065713 | 3304 | 3.1848e-06 | 7.9621e-05 | 3392 | 0.03 | 2259
2670 | GREENBRAE 11037315 | 43091103 | GREENBRAE 1103 | 7315 | TRUE | 3607.614 | 0 | 0 | 32 | 4.8486e-05 | 3078 | 0.065151 | 3567 | 3.1589e-06 | 0.00010108 | 3393 |  | 2795
6253 | FORT BRAGG A 110233064 | 42761102 | FORT BRAGG A 1102 | 33064 | TRUE | 5902.0297 | 0 | 0 | 49 | 4.8351e-05 | 3084 | 0.065148 | 3593 | 3.15e-06 | 0.00015435 | 3394 |  | 3017
4022 | EDES 1112CR100 | 13681112 | EDES 1112 | CR100 | FALSE | 5399.0675 | 5399.0675 | 3.3555 | 40 | 4.7216e-05 | 3109 | 0.066432 | 2972 | 3.1366e-06 | 0.00012546 | 3395 | 0.04 | 2134
1730 | LOS GATOS 1101CB | 82021101 | LOS GATOS 1101 | CB | TRUE | 3679.779 | 47.6524 | 0.029616 | 34 | 4.8123e-05 | 3090 | 0.065185 | 3530 | 3.1364e-06 | 0.00010664 | 3396 | 0.03 | 2233
5067 | EL CERRITO G 1112BR178 | 12501112 | EL CERRITO G 1112 | BR178 | TRUE | 10667.1601 | 48.2003 | 0.029957 | 93 | 4.805e-05 | 3092 | 0.065161 | 3553 | 3.1309e-06 | 0.00029117 | 3397 | 0.24 | 1105
3732 | SOBRANTE 1101L534R | 14671101 | SOBRANTE 1101 | L534R | FALSE | 3066.0904 | 1291.9266 | 0.80294 | 34 | 4.7553e-05 | 3099 | 0.065526 | 3358 | 3.1282e-06 | 0.00010636 | 3398 | 0.06 | 1853
4550 | VALLEY VIEW 1106P176 | 14341106 | VALLEY VIEW 1106 | P176 | TRUE | 5384.4602 | 354.4687 | 0.2203 | 44 | 4.7444e-05 | 3104 | 0.066098 | 3199 | 3.1268e-06 | 0.00013758 | 3399 | 0.06 | 1778
7024 | VIEJO 220292792 | 182852202 | VIEJO 2202 | 92792 | TRUE | 2338.4551 | 0 | 0 | 21 | 4.7946e-05 | 3094 | 0.065148 | 3598 | 3.1236e-06 | 6.5595e-05 | 3400 | 0.04 | 2169
8774 | TULUCAY 1101504524 | 42301101 | TULUCAY 1101 | 504524 | TRUE | 2446.524 | 610.0991 | 0.37918 | 15 | 4.7542e-05 | 3101 | 0.065322 | 3452 | 3.1216e-06 | 4.6823e-05 | 3401 |  | 3262
9561 | ATASCADERO 1101747522 | 182541101 | ATASCADERO 1101 | 747522 | TRUE | 1686.5664 | 412.9409 | 0.25664 | 16 | 4.7461e-05 | 3103 | 0.065468 | 3390 | 3.1133e-06 | 4.9813e-05 | 3402 |  | 3378
1757 | OAKLAND X 1106121588 | 12541106 | OAKLAND X 1106 | 121588 | FALSE | 3050.4627 | 1356.1967 | 0.84288 | 27 | 4.7074e-05 | 3111 | 0.065623 | 3330 | 3.0983e-06 | 8.3654e-05 | 3403 |  | 2743
641 | ALTO 11251256 | 42031125 | ALTO 1125 | 1256 | FALSE | 12257.9124 | 12003.1718 | 7.46 | 88 | 4.6726e-05 | 3121 | 0.066359 | 3134 | 3.098e-06 | 0.00027263 | 3404 | 0.07 | 1720
7693 | SARATOGA 1103595689 | 83371103 | SARATOGA 1103 | 595689 | TRUE | 356.3825 | 44.7654 | 0.027822 | 4 | 4.6978e-05 | 3113 | 0.065468 | 3387 | 3.0826e-06 | 1.233e-05 | 3405 |  | 3152
1201 | RINCON 1102640 | 43321102 | RINCON 1102 | 640 | TRUE | 6850.9553 | 0 | 0 | 56 | 4.7109e-05 | 3110 | 0.065185 | 3528 | 3.0722e-06 | 0.00017204 | 3406 | 0.02 | 2509
8249 | VIEJO 22029089 | 182852202 | VIEJO 2202 | 9089 | FALSE | 2700.0603 | 2319.95 | 1.4419 | 20 | 4.6292e-05 | 3130 | 0.066175 | 3177 | 3.0684e-06 | 6.1368e-05 | 3407 | 0.03 | 2365
4500 | PACIFICA 1102968736 | 22811102 | PACIFICA 1102 | 968736 | FALSE | 1533.9821 | 1132.2658 | 0.70371 | 9 | 4.6179e-05 | 3133 | 0.065575 | 3349 | 3.0372e-06 | 2.7334e-05 | 3408 |  | 2899
5121 | BURNEY 110237284 | 103311102 | BURNEY 1102 | 37284 | TRUE | 823.8475 | 303.068 | 0.18836 | 15 | 4.5944e-05 | 3141 | 0.065918 | 3241 | 3.0199e-06 | 4.5299e-05 | 3409 |  | 2937
3124 | SAN RAFAEL 110648752 | 42011106 | SAN RAFAEL 1106 | 48752 | TRUE | 3375.7798 | 23.2085 | 0.014424 | 28 | 4.6007e-05 | 3137 | 0.065151 | 3572 | 2.9974e-06 | 8.3928e-05 | 3410 | 0.02 | 2446
292 | RIDGE 0402CB | 12840402 | RIDGE 0402 | CB | FALSE | 3860.7171 | 2930.2271 | 1.8211 | 31 | 4.5082e-05 | 3157 | 0.066059 | 3208 | 2.9927e-06 | 9.2772e-05 | 3411 | 0.06 | 1837
5812 | LAS GALLINAS A 11051218 | 42991105 | LAS GALLINAS A 1105 | 1218 | TRUE | 3546.1366 | 106.7452 | 0.066343 | 28 | 4.5839e-05 | 3144 | 0.065197 | 3512 | 2.9904e-06 | 8.3731e-05 | 3412 | 0.03 | 2368
5928 | IGNACIO 110584764 | 42481105 | IGNACIO 1105 | 84764 | TRUE | 4092.9318 | 339.9136 | 0.21126 | 33 | 4.5707e-05 | 3148 | 0.065268 | 3472 | 2.9818e-06 | 9.8398e-05 | 3413 |  | 2990
231 | PAUL SWEET 210912828 | 83252109 | PAUL SWEET 2109 | 12828 | FALSE | 7906.6719 | 1834.1595 | 1.1399 | 66 | 4.4984e-05 | 3161 | 0.065458 | 3393 | 2.9651e-06 | 0.0001957 | 3414 |  | 2662
5926 | CASTRO VALLEY 1110CB | 14091110 | CASTRO VALLEY 1110 | CB | TRUE | 2059.8957 | 523.3275 | 0.32525 | 23 | 4.4906e-05 | 3162 | 0.065538 | 3356 | 2.9632e-06 | 6.8153e-05 | 3415 |  | 2989
8452 | HARRIS 1108395498 | 192431108 | HARRIS 1108 | 395498 | TRUE | 792.3855 | 171.0291 | 0.1063 | 8 | 4.5439e-05 | 3154 | 0.065308 | 3459 | 2.9622e-06 | 2.3698e-05 | 3416 |  | 3227
8569 | IGNACIO 1105683542 | 42481105 | IGNACIO 1105 | 683542 | TRUE | 222.9115 | 222.9115 | 0.13854 | 2 | 4.4358e-05 | 3180 | 0.066431 | 3030 | 2.9468e-06 | 5.8935e-06 | 3417 |  | 3237
6289 | STAFFORD 1101405812 | 43201101 | STAFFORD 1101 | 405812 | TRUE | 695.3753 | 295.2493 | 0.1835 | 7 | 4.5015e-05 | 3158 | 0.065517 | 3362 | 2.9445e-06 | 2.0611e-05 | 3418 |  | 3019
8541 | ROSSMOOR 1106L541R | 14161106 | ROSSMOOR 1106 | L541R | TRUE | 978.5878 | 0 | 0 | 11 | 4.5011e-05 | 3159 | 0.065148 | 3586 | 2.9324e-06 | 3.2256e-05 | 3419 |  | 3233
3241 | OAKLAND K 1101CB | 12101101 | OAKLAND K 1101 | CB | TRUE | 3805.7329 | 538.4598 | 0.33465 | 40 | 4.4235e-05 | 3185 | 0.065436 | 3400 | 2.9186e-06 | 0.00011674 | 3420 | 0.04 | 2228
6045 | OAKLAND J 1105CR256 | 12091105 | OAKLAND J 1105 | CR256 | FALSE | 2967.1612 | 1965.4224 | 1.2215 | 27 | 4.4194e-05 | 3187 | 0.065813 | 3263 | 2.9181e-06 | 7.879e-05 | 3421 | 0.05 | 2053
8780 | SAN LUIS OBISPO 1108144690 | 182631108 | SAN LUIS OBISPO 1108 | 144690 | TRUE | 900.0003 | 418.942 | 0.26037 | 10 | 3.5334e-05 | 3344 | 0.075693 | 2936 | 2.905e-06 | 2.905e-05 | 3422 |  | 3264
10157 | CASTRO VALLEY 1108MR233 | 14091108 | CASTRO VALLEY 1108 | MR233 | TRUE | 1023.3374 | 370.9448 | 0.23054 | 7 | 4.4443e-05 | 3176 | 0.065331 | 3447 | 2.9035e-06 | 2.0325e-05 | 3423 |  | 3504
3481 | IGNACIO 1105318 | 42481105 | IGNACIO 1105 | 318 | FALSE | 18622.6335 | 2887.2825 | 1.7945 | 150 | 4.4269e-05 | 3183 | 0.065347 | 3439 | 2.9031e-06 | 0.00043547 | 3424 |  | 2830
1523 | HAMILTON BRANCH 110187784 | 102361101 | HAMILTON BRANCH 1101 | 87784 | FALSE | 2328.7215 | 2328.7215 | 1.4473 | 23 | 4.3587e-05 | 3199 | 0.066432 | 2997 | 2.8956e-06 | 6.6598e-05 | 3425 | 0.12 | 1383
10922 | PINECREST 0401CB | 163160401 | PINECREST 0401 | CB | TRUE | 22.2055 | 22.2055 | 0.013801 | 1 | 4.352e-05 | 3201 | 0.066431 | 3088 | 2.8911e-06 | 2.8911e-06 | 3426 | 1.9 | 633
1324 | SONOMA 11054456 | 42721105 | SONOMA 1105 | 4456 | TRUE | 8052.7827 | 0 | 0 | 62 | 4.4073e-05 | 3189 | 0.065151 | 3562 | 2.8714e-06 | 0.00017803 | 3427 | 0.03 | 2297
8419 | SAN CARLOS 1103785521 | 24181103 | SAN CARLOS 1103 | 785521 | TRUE | 292.996 | 109.0213 | 0.067757 | 3 | 4.3673e-05 | 3196 | 0.065575 | 3350 | 2.8654e-06 | 8.5962e-06 | 3428 |  | 3223
6629 | BIG MEADOWS 21012246 | 102812101 | BIG MEADOWS 2101 | 2246 | FALSE | 2937.4924 | 2937.4924 | 1.8257 | 23 | 4.2984e-05 | 3209 | 0.066432 | 2998 | 2.8555e-06 | 6.5676e-05 | 3429 | 0.1 | 1481
692 | ECHO SUMMIT 11018922 | 158031101 | ECHO SUMMIT 1101 | 8922 | FALSE | 1940.3902 | 1940.3902 | 1.206 | 11 | 4.2932e-05 | 3211 | 0.066431 | 3096 | 2.852e-06 | 3.1372e-05 | 3430 | 0.18 | 1208
5593 | SNEATH LANE 1102CB | 22721102 | SNEATH LANE 1102 | CB | FALSE | 4044.2651 | 2195.0074 | 1.3642 | 37 | 4.3121e-05 | 3206 | 0.065703 | 3309 | 2.8459e-06 | 0.0001053 | 3431 | 0.02 | 2448
7382 | VIEJO 220235388 | 182852202 | VIEJO 2202 | 35388 | TRUE | 727.2974 | 517.0139 | 0.32133 | 8 | 4.2702e-05 | 3213 | 0.066111 | 3193 | 2.8344e-06 | 2.2676e-05 | 3432 | 0.94 | 745
5265 | IGNACIO 1103CB | 42481103 | IGNACIO 1103 | CB | TRUE | 3068.5523 | 350.3296 | 0.21773 | 34 | 4.3221e-05 | 3205 | 0.065226 | 3495 | 2.8181e-06 | 9.5817e-05 | 3433 |  | 2943
9102 | HICKS 1116733078 | 83431116 | HICKS 1116 | 733078 | TRUE | 567.873 | 551.871 | 0.34299 | 7 | 4.2163e-05 | 3221 | 0.066065 | 3206 | 2.777e-06 | 1.9439e-05 | 3434 |  | 3310
199 | OAKLAND K 1103CB | 12101103 | OAKLAND K 1103 | CB | TRUE | 7954.9462 | 769.1621 | 0.47804 | 66 | 4.1996e-05 | 3224 | 0.065264 | 3474 | 2.758e-06 | 0.00018203 | 3435 | 0.02 | 2428
2072 | RALSTON 1101420730 | 24141101 | RALSTON 1101 | 420730 | FALSE | 2651.706 | 1292.6324 | 0.80338 | 21 | 4.1694e-05 | 3230 | 0.065759 | 3293 | 2.7513e-06 | 5.7777e-05 | 3436 |  | 2760
8913 | WOOD 0401880795 | 13380401 | WOOD 0401 | 880795 | TRUE | 506.0077 | 163.9752 | 0.10191 | 6 | 4.2077e-05 | 3222 | 0.065147 | 3611 | 2.7412e-06 | 1.6447e-05 | 3437 |  | 3277
7811 | VIEJO 2203947314 | 182852203 | VIEJO 2203 | 947314 | TRUE | 2331.8511 | 461.4011 | 0.28676 | 22 | 4.1433e-05 | 3236 | 0.065323 | 3451 | 2.7164e-06 | 5.9761e-05 | 3438 |  | 3163
8336 | OLEMA 110137074 | 42291101 | OLEMA 1101 | 37074 | TRUE | 506.0081 | 21.9456 | 0.013639 | 6 | 4.1439e-05 | 3234 | 0.065361 | 3435 | 2.7134e-06 | 1.628e-05 | 3439 | 0.03 | 2372
6224 | SAN CARLOS 110479774 | 24181104 | SAN CARLOS 1104 | 79774 | FALSE | 2604.0952 | 1435.8821 | 0.89241 | 24 | 4.0919e-05 | 3247 | 0.065682 | 3315 | 2.698e-06 | 6.4753e-05 | 3440 | 0.05 | 2041
2094 | ROB ROY 210512586 | 83692105 | ROB ROY 2105 | 12586 | FALSE | 10478.2506 | 3041.3304 | 1.8902 | 85 | 4.1068e-05 | 3241 | 0.065464 | 3391 | 2.697e-06 | 0.00022925 | 3441 | 0.05 | 2013
8276 | OAKLAND J 1102CR254 | 12091102 | OAKLAND J 1102 | CR254 | FALSE | 2477.3187 | 1687.0283 | 1.0485 | 20 | 4.0719e-05 | 3253 | 0.065918 | 3242 | 2.6941e-06 | 5.3882e-05 | 3442 | 0.03 | 2367
5380 | CASTROVILLE 210436922 | 182352104 | CASTROVILLE 2104 | 36922 | TRUE | 8825.2123 | 0 | 0 | 37 | 4.0991e-05 | 3245 | 0.065148 | 3595 | 2.6705e-06 | 9.8808e-05 | 3443 |  | 2948
6593 | FOOTHILL 1101798137 | 182951101 | FOOTHILL 1101 | 798137 | TRUE | 581.8228 | 68.0149 | 0.042272 | 5 | 4.0802e-05 | 3250 | 0.065404 | 3417 | 2.6637e-06 | 1.3319e-05 | 3444 |  | 3045
1687 | BIG MEADOWS 21012016 | 102812101 | BIG MEADOWS 2101 | 2016 | TRUE | 6829.6992 | 150.9724 | 0.09383 | 65 | 4.0813e-05 | 3249 | 0.065188 | 3525 | 2.6614e-06 | 0.00017299 | 3445 | 0.04 | 2208
10145 | GREENBRAE 1104317890 | 43091104 | GREENBRAE 1104 | 317890 | TRUE | 125.8315 | 125.8315 | 0.078205 | 2 | 3.9991e-05 | 3269 | 0.066431 | 3031 | 2.6567e-06 | 5.3133e-06 | 3446 |  | 3501
3009 | GREENBRAE 1102CB | 43091102 | GREENBRAE 1102 | CB | TRUE | 3469.4672 | 0 | 0 | 28 | 4.0756e-05 | 3251 | 0.065151 | 3570 | 2.6553e-06 | 7.4348e-05 | 3447 | 0.09 | 1558
9193 | LOS GATOS 1106CB | 82021106 | LOS GATOS 1106 | CB | TRUE | 1170.6003 | 164.2523 | 0.10208 | 11 | 4.0346e-05 | 3259 | 0.065497 | 3371 | 2.651e-06 | 2.9161e-05 | 3448 | 0.27 | 1059
6430 | FORT BRAGG A 110465894 | 42761104 | FORT BRAGG A 1104 | 65894 | TRUE | 1441.6391 | 0 | 0 | 12 | 4.0627e-05 | 3255 | 0.065148 | 3601 | 2.6468e-06 | 3.1761e-05 | 3449 |  | 3031
6292 | RIO DEL MAR 0401931192 | 83260401 | RIO DEL MAR 0401 | 931192 | FALSE | 11415.5971 | 3615.6701 | 2.2472 | 87 | 4.0212e-05 | 3262 | 0.065487 | 3375 | 2.6467e-06 | 0.00023026 | 3450 |  | 3020
8372 | LAURELES 11122142 | 182371112 | LAURELES 1112 | 2142 | TRUE | 2588.0177 | 151.8851 | 0.094397 | 26 | 4.0293e-05 | 3261 | 0.065246 | 3480 | 2.6301e-06 | 6.8383e-05 | 3451 | 0.08 | 1615
4353 | FLORENCE 0401CB | 12690401 | FLORENCE 0401 | CB | FALSE | 4654.0755 | 1041.2537 | 0.64714 | 39 | 4.0081e-05 | 3266 | 0.065411 | 3410 | 2.6231e-06 | 0.0001023 | 3452 | 0.04 | 2160
1560 | SANTA ROSA A 1104CB | 42151104 | SANTA ROSA A 1104 | CB | TRUE | 9581.6812 | 369.0017 | 0.22934 | 76 | 4.0032e-05 | 3268 | 0.065241 | 3484 | 2.617e-06 | 0.00019889 | 3453 | 0.16 | 1252
9790 | PAUL SWEET 2109680537 | 83252109 | PAUL SWEET 2109 | 680537 | TRUE | 1060.8184 | 362.7293 | 0.22544 | 9 | 3.9362e-05 | 3278 | 0.065433 | 3403 | 2.5979e-06 | 2.3381e-05 | 3454 |  | 3424
9764 | PACIFICA 1102512070 | 22811102 | PACIFICA 1102 | 512070 | TRUE | 481.613 | 279.6247 | 0.17379 | 5 | 3.9072e-05 | 3285 | 0.065661 | 3322 | 2.586e-06 | 1.293e-05 | 3455 |  | 3413
2324 | ALTO 1124CB | 42031124 | ALTO 1124 | CB | FALSE | 9084.5965 | 2733.348 | 1.6988 | 81 | 3.9255e-05 | 3280 | 0.065515 | 3364 | 2.5838e-06 | 0.00020929 | 3456 | 0.24 | 1096
2547 | CASTRO VALLEY 1102MR204 | 14091102 | CASTRO VALLEY 1102 | MR204 | TRUE | 4739.0907 | 326.5252 | 0.20294 | 46 | 3.9361e-05 | 3279 | 0.065259 | 3475 | 2.5759e-06 | 0.00011849 | 3457 |  | 2785
885 | EDES 1112CR308 | 13681112 | EDES 1112 | CR308 | FALSE | 5698.3231 | 5168.8003 | 3.2124 | 53 | 3.8446e-05 | 3292 | 0.066287 | 3153 | 2.5524e-06 | 0.00013527 | 3458 | 0.07 | 1769
7145 | HICKS 111512494 | 83431115 | HICKS 1115 | 12494 | TRUE | 4190.5486 | 220.1167 | 0.1368 | 35 | 3.9122e-05 | 3283 | 0.065184 | 3532 | 2.5505e-06 | 8.9268e-05 | 3459 |  | 3101
970 | CAYUCOS 1102CB | 182551102 | CAYUCOS 1102 | CB | TRUE | 8504.0553 | 0 | 0 | 41 | 3.9093e-05 | 3284 | 0.065147 | 3625 | 2.5468e-06 | 0.00010442 | 3460 | 0.18 | 1219
7960 | LOS GATOS 1101206248 | 82021101 | LOS GATOS 1101 | 206248 | TRUE | 893.3087 | 83.0039 | 0.051587 | 10 | 3.895e-05 | 3288 | 0.065404 | 3414 | 2.5435e-06 | 2.5435e-05 | 3461 |  | 3179
2461 | HAMILTON BRANCH 110137436 | 102361101 | HAMILTON BRANCH 1101 | 37436 | FALSE | 3311.0305 | 1208.0743 | 0.75082 | 33 | 3.8691e-05 | 3289 | 0.065576 | 3347 | 2.5374e-06 | 8.3735e-05 | 3462 | 0.1 | 1485
5208 | VIEJO 22029120 | 182852202 | VIEJO 2202 | 9120 | FALSE | 11903.5244 | 2858.0041 | 1.7763 | 112 | 3.8665e-05 | 3290 | 0.065446 | 3397 | 2.5361e-06 | 0.00028404 | 3463 | 0.07 | 1741
10027 | PACIFICA 1103398620 | 22811103 | PACIFICA 1103 | 398620 | TRUE | 770.3641 | 758.0837 | 0.47115 | 7 | 3.8215e-05 | 3297 | 0.066248 | 3163 | 2.531e-06 | 1.7717e-05 | 3464 |  | 3477
4053 | OAKLAND X 1105184672 | 12541105 | OAKLAND X 1105 | 184672 | FALSE | 5259.1473 | 2666.0437 | 1.657 | 46 | 3.8231e-05 | 3295 | 0.065706 | 3307 | 2.5255e-06 | 0.00011617 | 3465 |  | 2869
5327 | FAIRVIEW 2207CB | 13432207 | FAIRVIEW 2207 | CB | TRUE | 8128.5867 | 387.1496 | 0.24062 | 57 | 3.8448e-05 | 3291 | 0.065193 | 3515 | 2.5112e-06 | 0.00014314 | 3466 | 0.03 | 2279
1098 | VIEJO 22012064 | 182852201 | VIEJO 2201 | 2064 | FALSE | 1409.3976 | 1409.3976 | 0.87595 | 15 | 3.7422e-05 | 3305 | 0.066432 | 2982 | 2.486e-06 | 3.729e-05 | 3467 | 0.08 | 1660
3180 | STAFFORD 110242542 | 43201102 | STAFFORD 1102 | 42542 | TRUE | 5717.1489 | 862.3483 | 0.53595 | 52 | 3.7508e-05 | 3304 | 0.065348 | 3438 | 2.465e-06 | 0.00012818 | 3468 | 0.03 | 2335
4684 | SNEATH LANE 110134438 | 22721101 | SNEATH LANE 1101 | 34438 | FALSE | 8258.6725 | 3709.6211 | 2.3055 | 67 | 3.7308e-05 | 3309 | 0.065492 | 3373 | 2.4545e-06 | 0.00016445 | 3469 | 0.06 | 1800
5609 | BURNEY 110297318 | 103311102 | BURNEY 1102 | 97318 | TRUE | 1594.8254 | 294.9732 | 0.18333 | 18 | 3.7395e-05 | 3306 | 0.065576 | 3346 | 2.4455e-06 | 4.4019e-05 | 3470 | 0.03 | 2327
3808 | HAMILTON BRANCH 11013049 | 102361101 | HAMILTON BRANCH 1101 | 3049 | FALSE | 2682.1998 | 1650.9947 | 1.0261 | 23 | 3.708e-05 | 3312 | 0.065874 | 3249 | 2.4445e-06 | 5.6224e-05 | 3471 | 2.64 | 592
10978 | ALTO 1124965060 | 42031124 | ALTO 1124 | 965060 | TRUE | 112.5171 | 99.6543 | 0.061936 | 1 | 3.6723e-05 | 3320 | 0.066431 | 3036 | 2.4396e-06 | 2.4396e-06 | 3472 |  | 3624
10767 | SAUSALITO 1102758798 | 42491102 | SAUSALITO 1102 | 758798 | TRUE | 68.038 | 53.2652 | 0.033105 | 2 | 3.6428e-05 | 3325 | 0.065789 | 3289 | 2.4159e-06 | 4.8318e-06 | 3473 |  | 3603
2223 | PAUL SWEET 2109CB | 83252109 | PAUL SWEET 2109 | CB | TRUE | 18410.6369 | 20.7388 | 0.012889 | 171 | 3.6749e-05 | 3319 | 0.065155 | 3560 | 2.3948e-06 | 0.00040951 | 3474 | 0.28 | 1039
4848 | VALLEY VIEW 1103P160 | 14341103 | VALLEY VIEW 1103 | P160 | TRUE | 10321.2013 | 0 | 0 | 96 | 3.6431e-05 | 3324 | 0.065148 | 3582 | 2.3734e-06 | 0.00022785 | 3475 | 2.76 | 583
1157 | MORAGA 1105116034 | 13801105 | MORAGA 1105 | 116034 | TRUE | 4982.0059 | 539.5091 | 0.33531 | 41 | 3.6154e-05 | 3332 | 0.065278 | 3469 | 2.3641e-06 | 9.6928e-05 | 3476 |  | 2713
6537 | SNEATH LANE 110275844 | 22721102 | SNEATH LANE 1102 | 75844 | TRUE | 864.7167 | 272.6844 | 0.16947 | 10 | 3.5678e-05 | 3340 | 0.065275 | 3470 | 2.3271e-06 | 2.3271e-05 | 3477 | 0.02 | 2485
1692 | SAN CARLOS 11048846 | 24181104 | SAN CARLOS 1104 | 8846 | FALSE | 7060.9911 | 3588.6165 | 2.2303 | 61 | 3.5185e-05 | 3347 | 0.065737 | 3298 | 2.3218e-06 | 0.00014163 | 3478 | 0.04 | 2219
5922 | SNEATH LANE 1101CB | 22721101 | SNEATH LANE 1101 | CB | TRUE | 1584.8668 | 745.3166 | 0.46322 | 19 | 3.5327e-05 | 3345 | 0.06535 | 3437 | 2.3127e-06 | 4.3942e-05 | 3479 | 0.02 | 2415
3263 | SAN LEANDRO U 1109936988 | 13111109 | SAN LEANDRO U 1109 | 936988 | FALSE | 10891.0554 | 10891.0554 | 6.7688 | 86 | 3.4698e-05 | 3356 | 0.066432 | 2957 | 2.3051e-06 | 0.00019824 | 3480 |  | 2818
7536 | WILLITS 11021270 | 42661102 | WILLITS 1102 | 1270 | TRUE | 2454.7077 | 0 | 0 | 21 | 3.5345e-05 | 3343 | 0.06515 | 3579 | 2.3027e-06 | 4.8357e-05 | 3481 |  | 3133
2607 | WALDO 0402258792 | 13350402 | WALDO 0402 | 258792 | FALSE | 4808.6867 | 4793.9751 | 2.9795 | 36 | 3.4657e-05 | 3358 | 0.066396 | 3121 | 2.3019e-06 | 8.287e-05 | 3482 |  | 2788
2976 | STAFFORD 1101902998 | 43201101 | STAFFORD 1101 | 902998 | FALSE | 9746.2747 | 1732.2882 | 1.0766 | 81 | 3.5078e-05 | 3350 | 0.065372 | 3428 | 2.2981e-06 | 0.00018615 | 3483 |  | 2809
28 | RALSTON 110148936 | 24141101 | RALSTON 1101 | 48936 | FALSE | 9703.0008 | 7437.214 | 4.6223 | 86 | 3.4701e-05 | 3355 | 0.066043 | 3210 | 2.2943e-06 | 0.00019731 | 3484 | 0.08 | 1663
6723 | VALLEY VIEW 1106P128 | 14341106 | VALLEY VIEW 1106 | P128 | TRUE | 4067.7934 | 190.9091 | 0.11865 | 31 | 3.4672e-05 | 3357 | 0.065272 | 3471 | 2.2678e-06 | 7.0301e-05 | 3485 | 0.03 | 2403
6528 | LAS GALLINAS A 1106206332 | 42991106 | LAS GALLINAS A 1106 | 206332 | TRUE | 973.8303 | 488.8653 | 0.30383 | 7 | 3.1898e-05 | 3402 | 0.072747 | 2939 | 2.2569e-06 | 1.5798e-05 | 3486 |  | 3039
2106 | SPRUCE 0402BR304 | 13340402 | SPRUCE 0402 | BR304 | FALSE | 5760.7882 | 2392.7287 | 1.4871 | 53 | 3.4151e-05 | 3368 | 0.06568 | 3316 | 2.2492e-06 | 0.00011921 | 3487 | 0.08 | 1595
3661 | LAS GALLINAS A 1106685656 | 42991106 | LAS GALLINAS A 1106 | 685656 | FALSE | 5880.2294 | 1923.4165 | 1.1954 | 43 | 3.4111e-05 | 3369 | 0.06533 | 3449 | 2.2325e-06 | 9.5996e-05 | 3488 |  | 2845
3471 | LOS GATOS 110160136 | 82021101 | LOS GATOS 1101 | 60136 | TRUE | 6522.6172 | 0 | 0 | 57 | 3.4156e-05 | 3367 | 0.065147 | 3622 | 2.2252e-06 | 0.00012684 | 3489 |  | 2829
4292 | EMERALD LAKE 04028872 | 24080402 | EMERALD LAKE 0402 | 8872 | FALSE | 9042.2667 | 7244.0552 | 4.5022 | 77 | 3.3183e-05 | 3382 | 0.066165 | 3180 | 2.2015e-06 | 0.00016952 | 3490 | 0.09 | 1565
1116 | SNEATH LANE 110168070 | 22721101 | SNEATH LANE 1101 | 68070 | TRUE | 3445.6939 | 373.7094 | 0.23226 | 30 | 3.3642e-05 | 3372 | 0.065233 | 3488 | 2.1953e-06 | 6.5858e-05 | 3491 | 0.02 | 2503
9555 | IGNACIO 1103504941 | 42481103 | IGNACIO 1103 | 504941 | TRUE | 1025.616 | 663.24 | 0.41221 | 6 | 3.3217e-05 | 3381 | 0.065578 | 3339 | 2.194e-06 | 1.3164e-05 | 3492 |  | 3375
4494 | VIEJO 22019704 | 182852201 | VIEJO 2201 | 9704 | TRUE | 4114.9938 | 786.5986 | 0.48887 | 29 | 3.3423e-05 | 3377 | 0.065369 | 3429 | 2.1872e-06 | 6.3429e-05 | 3493 | 0.4 | 944
3505 | WOODSIDE 11049030 | 24251104 | WOODSIDE 1104 | 9030 | FALSE | 4149.4333 | 3272.4558 | 2.0338 | 37 | 3.3072e-05 | 3384 | 0.06605 | 3209 | 2.1865e-06 | 8.0902e-05 | 3494 | 0.1 | 1476
4601 | HATTON 11022070 | 182291102 | HATTON 1102 | 2070 | TRUE | 3077.1707 | 843.4628 | 0.52422 | 26 | 3.3159e-05 | 3383 | 0.065444 | 3398 | 2.1767e-06 | 5.6595e-05 | 3495 | 0.04 | 2156
10245 | GREENBRAE 1104972264 | 43091104 | GREENBRAE 1104 | 972264 | TRUE | 337.1983 | 0 | 0 | 4 | 3.3356e-05 | 3379 | 0.065151 | 3575 | 2.1732e-06 | 8.6927e-06 | 3496 |  | 3520
6525 | HAMILTON BRANCH 11012082 | 102361101 | HAMILTON BRANCH 1101 | 2082 | FALSE | 4925.5933 | 2445.1965 | 1.5197 | 46 | 3.2758e-05 | 3390 | 0.065762 | 3292 | 2.1552e-06 | 9.9139e-05 | 3497 | 0.08 | 1612
7268 | HICKS 1116203897 | 83431116 | HICKS 1116 | 203897 | TRUE | 1017.3713 | 367.9073 | 0.22866 | 9 | 3.2839e-05 | 3388 | 0.065433 | 3405 | 2.1509e-06 | 1.9358e-05 | 3498 |  | 3108
5472 | CHESTER 1101656108 | 103181101 | CHESTER 1101 | 656108 | TRUE | 1195.0984 | 838.7097 | 0.52126 | 10 | 3.2603e-05 | 3392 | 0.065918 | 3240 | 2.1478e-06 | 2.1478e-05 | 3499 |  | 2956
659 | EL CERRITO G 1112BR196 | 12501112 | EL CERRITO G 1112 | BR196 | TRUE | 5817.7228 | 0 | 0 | 51 | 3.2633e-05 | 3391 | 0.065172 | 3540 | 2.127e-06 | 0.00010848 | 3500 | 0.05 | 1940
286 | OAKLAND X 1106CB | 12541106 | OAKLAND X 1106 | CB | FALSE | 15907.2746 | 5284.9861 | 3.2846 | 136 | 3.2105e-05 | 3399 | 0.065515 | 3363 | 2.1195e-06 | 0.00028825 | 3501 | 0.06 | 1835
3401 | VIEJO 22029104 | 182852202 | VIEJO 2202 | 9104 | FALSE | 9586.0766 | 9148.567 | 5.6859 | 79 | 3.1817e-05 | 3404 | 0.066367 | 3133 | 2.113e-06 | 0.00016692 | 3502 | 0.18 | 1218
617 | OAK 0401CB | 12600401 | OAK 0401 | CB | FALSE | 8716.4726 | 5585.5806 | 3.4715 | 68 | 3.153e-05 | 3408 | 0.06596 | 3231 | 2.0871e-06 | 0.00014192 | 3503 | 0.09 | 1539
5991 | VIEJO 22019698 | 182852201 | VIEJO 2201 | 9698 | TRUE | 1062.5186 | 929.6624 | 0.57779 | 10 | 3.1068e-05 | 3415 | 0.066303 | 3148 | 2.0607e-06 | 2.0607e-05 | 3504 | 0.07 | 1771
2044 | SPRUCE 0401BR316 | 13340401 | SPRUCE 0401 | BR316 | FALSE | 6608.6922 | 6608.6922 | 4.1073 | 56 | 3.0991e-05 | 3416 | 0.066432 | 2970 | 2.0588e-06 | 0.00011529 | 3505 | 0.12 | 1388
7179 | EL CERRITO G 111257953 | 12501112 | EL CERRITO G 1112 | 57953 | TRUE | 1217.1907 | 353.2769 | 0.21956 | 11 | 3.1168e-05 | 3413 | 0.065497 | 3370 | 2.0515e-06 | 2.2566e-05 | 3506 | 0.34 | 977
5036 | FRANKLIN 1104CB | 13921104 | FRANKLIN 1104 | CB | TRUE | 8361.6686 | 466.2641 | 0.28979 | 63 | 3.1091e-05 | 3414 | 0.065209 | 3507 | 2.0367e-06 | 0.00012831 | 3507 | 0.03 | 2390
6325 | LOS GATOS 1108CB | 82021108 | LOS GATOS 1108 | CB | TRUE | 1166.6657 | 0 | 0 | 15 | 3.1212e-05 | 3412 | 0.065147 | 3617 | 2.0334e-06 | 3.0501e-05 | 3508 |  | 3022
6874 | LOS GATOS 1102CB | 82021102 | LOS GATOS 1102 | CB | TRUE | 7506.165 | 0 | 0 | 70 | 3.0936e-05 | 3418 | 0.065147 | 3616 | 2.0154e-06 | 0.00014108 | 3509 | 0.05 | 2064
1424 | PACIFICA 1103CB | 22811103 | PACIFICA 1103 | CB | TRUE | 7799.5565 | 109.5296 | 0.068073 | 62 | 3.075e-05 | 3420 | 0.065188 | 3523 | 2.0046e-06 | 0.00012428 | 3510 | 0.02 | 2475
10000 | ALTO 1125781759 | 42031125 | ALTO 1125 | 781759 | TRUE | 264.5561 | 210.4887 | 0.13082 | 4 | 3.0572e-05 | 3422 | 0.065789 | 3288 | 2.0026e-06 | 8.0105e-06 | 3511 |  | 3469
254 | HICKS 1116CB | 83431116 | HICKS 1116 | CB | TRUE | 22837.5991 | 336.1648 | 0.20893 | 165 | 2.9963e-05 | 3426 | 0.065178 | 3539 | 1.9553e-06 | 0.00032262 | 3512 | 0.04 | 2128
1238 | STAFFORD 11021019 | 43201102 | STAFFORD 1102 | 1019 | TRUE | 1173.8689 | 432.0709 | 0.26853 | 10 | 2.9828e-05 | 3428 | 0.065279 | 3468 | 1.946e-06 | 1.946e-05 | 3513 | 0.07 | 1695
10590 | CHESTER 1102546744 | 103181102 | CHESTER 1102 | 546744 | TRUE | 633.1716 | 428.8696 | 0.26654 | 7 | 2.921e-05 | 3435 | 0.065882 | 3248 | 1.934e-06 | 1.3538e-05 | 3514 |  | 3577
6891 | ALTO 1124994213 | 42031124 | ALTO 1124 | 994213 | TRUE | 860.1534 | 198.7798 | 0.12354 | 8 | 2.9167e-05 | 3437 | 0.065311 | 3455 | 1.9051e-06 | 1.5241e-05 | 3515 |  | 3071
9434 | BERKELEY F 1105849701 | 12061105 | BERKELEY F 1105 | 849701 | TRUE | 220.6039 | 213.7724 | 0.13286 | 2 | 2.8441e-05 | 3447 | 0.065789 | 3283 | 1.8894e-06 | 3.7788e-06 | 3516 |  | 3358
6092 | VIEJO 22049540 | 182852204 | VIEJO 2204 | 9540 | FALSE | 3592.089 | 2319.7097 | 1.4417 | 32 | 2.8532e-05 | 3444 | 0.06587 | 3251 | 1.8885e-06 | 6.0431e-05 | 3517 | 0.02 | 2557
9394 | ALTO 1124884949 | 42031124 | ALTO 1124 | 884949 | TRUE | 693.01 | 312.7335 | 0.19437 | 5 | 2.8569e-05 | 3443 | 0.065663 | 3319 | 1.8768e-06 | 9.3841e-06 | 3518 |  | 3352
8014 | WALDO 0401965216 | 13350401 | WALDO 0401 | 965216 | FALSE | 2651.8859 | 2642.7419 | 1.6425 | 21 | 2.8136e-05 | 3457 | 0.066371 | 3131 | 1.868e-06 | 3.9227e-05 | 3519 |  | 3185
4883 | LAS PULGAS 0401104588 | 24120401 | LAS PULGAS 0401 | 104588 | TRUE | 1238.8359 | 581.4114 | 0.36135 | 11 | 2.8291e-05 | 3451 | 0.065731 | 3301 | 1.8653e-06 | 2.0518e-05 | 3520 |  | 2924
8033 | MORAGA 110531512 | 13801105 | MORAGA 1105 | 31512 | TRUE | 3255.9931 | 0 | 0 | 29 | 2.8486e-05 | 3446 | 0.065148 | 3589 | 1.8558e-06 | 5.3819e-05 | 3521 | 6.49 | 467
4423 | SAN RAFAEL 1105344 | 42011105 | SAN RAFAEL 1105 | 344 | FALSE | 12052.7047 | 1314.7551 | 0.81713 | 97 | 2.8339e-05 | 3449 | 0.065283 | 3467 | 1.8552e-06 | 0.00017996 | 3522 | 0.06 | 1814
3011 | PERRY 1101W52 | 183071101 | PERRY 1101 | W52 | FALSE | 6677.88 | 5033.3373 | 3.1282 | 51 | 2.807e-05 | 3459 | 0.066004 | 3224 | 1.8539e-06 | 9.4548e-05 | 3523 | 0.05 | 1977
2767 | EL CERRITO G 1112BR180 | 12501112 | EL CERRITO G 1112 | BR180 | TRUE | 3108.6276 | 675.0712 | 0.41956 | 25 | 2.814e-05 | 3456 | 0.065507 | 3367 | 1.8513e-06 | 4.6282e-05 | 3524 | 3.92 | 531
7505 | EDES 1112CR306 | 13681112 | EDES 1112 | CR306 | FALSE | 1619.5833 | 1619.5833 | 1.0066 | 16 | 2.7663e-05 | 3463 | 0.066432 | 2950 | 1.8377e-06 | 2.9404e-05 | 3525 | 0.04 | 2175
349 | ALHAMBRA 1102CB | 14101102 | ALHAMBRA 1102 | CB | TRUE | 9244.1392 | 431.1151 | 0.26794 | 75 | 2.7307e-05 | 3468 | 0.065217 | 3501 | 1.7835e-06 | 0.00013376 | 3526 | 0.02 | 2558
5900 | CHESTER 1102CB | 103181102 | CHESTER 1102 | CB | TRUE | 4463.0648 | 40.2966 | 0.025045 | 38 | 2.7246e-05 | 3469 | 0.065182 | 3535 | 1.7766e-06 | 6.751e-05 | 3527 | 0.04 | 2082
6024 | WOODSIDE 11028862 | 24251102 | WOODSIDE 1102 | 8862 | TRUE | 4562.4649 | 0 | 0 | 38 | 2.7115e-05 | 3471 | 0.065147 | 3615 | 1.7665e-06 | 6.7125e-05 | 3528 | 0.02 | 2559
4122 | BURNEY 110257046 | 103311102 | BURNEY 1102 | 57046 | TRUE | 1135.0639 | 48.9091 | 0.030397 | 12 | 2.6931e-05 | 3474 | 0.065362 | 3431 | 1.7587e-06 | 2.1104e-05 | 3529 |  | 2873
2110 | CASTRO VALLEY 1108MR205 | 14091108 | CASTRO VALLEY 1108 | MR205 | TRUE | 8740.8692 | 0 | 0 | 73 | 2.6763e-05 | 3475 | 0.065182 | 3534 | 1.7478e-06 | 0.00012759 | 3530 |  | 2764
2448 | VIEJO 22029112 | 182852202 | VIEJO 2202 | 9112 | FALSE | 5302.286 | 1359.4094 | 0.84488 | 43 | 2.6492e-05 | 3480 | 0.065387 | 3422 | 1.7421e-06 | 7.4909e-05 | 3531 | 0.55 | 872
8885 | EL CERRITO G 1110BR236 | 12501110 | EL CERRITO G 1110 | BR236 | TRUE | 850.4173 | 819.8964 | 0.50957 | 7 | 2.6231e-05 | 3484 | 0.066065 | 3207 | 1.7373e-06 | 1.2161e-05 | 3532 | 0.06 | 1860
7598 | ALTO 1123820379 | 42031123 | ALTO 1123 | 820379 | TRUE | 298.2228 | 245.2911 | 0.15245 | 2 | 2.6136e-05 | 3485 | 0.066431 | 3032 | 1.7362e-06 | 3.4724e-06 | 3533 |  | 3139
1294 | VIEJO 2203573610 | 182852203 | VIEJO 2203 | 573610 | TRUE | 5029.4735 | 0 | 0 | 41 | 2.6462e-05 | 3481 | 0.065179 | 3538 | 1.7259e-06 | 7.0764e-05 | 3534 |  | 2722
2844 | SAN CARLOS 11039148 | 24181103 | SAN CARLOS 1103 | 9148 | TRUE | 6634.7635 | 0 | 0 | 51 | 2.6423e-05 | 3482 | 0.065147 | 3618 | 1.7214e-06 | 8.7791e-05 | 3535 | 0.07 | 1762
469 | VIEJO 22039094 | 182852203 | VIEJO 2203 | 9094 | TRUE | 4020.7215 | 160.2742 | 0.099611 | 32 | 2.6274e-05 | 3483 | 0.065228 | 3493 | 1.7132e-06 | 5.4823e-05 | 3536 | 0.02 | 2542
7298 | VIEJO 22032634 | 182852203 | VIEJO 2203 | 2634 | TRUE | 2692.6366 | 0 | 0 | 23 | 2.5666e-05 | 3490 | 0.065148 | 3596 | 1.6721e-06 | 3.8458e-05 | 3537 | 0.02 | 2497
8157 | OAKLAND J 1105CR150 | 12091105 | OAKLAND J 1105 | CR150 | TRUE | 755.1885 | 348.5421 | 0.21662 | 6 | 2.5203e-05 | 3494 | 0.065789 | 3290 | 1.667e-06 | 1.0002e-05 | 3538 | 0.05 | 1981
7733 | FORT BRAGG A 1103CB | 42761103 | FORT BRAGG A 1103 | CB | TRUE | 3993.2278 | 151.4693 | 0.094139 | 40 | 2.5491e-05 | 3491 | 0.06518 | 3537 | 1.6633e-06 | 6.6534e-05 | 3539 |  | 3157
9029 | MORGAN HILL 2105375239 | 83242105 | MORGAN HILL 2105 | 375239 | TRUE | 343.55 | 145.1624 | 0.090219 | 4 | 2.5051e-05 | 3495 | 0.065468 | 3385 | 1.6455e-06 | 6.5821e-06 | 3540 |  | 3299
9198 | MORGAN HILL 2105345099 | 83242105 | MORGAN HILL 2105 | 345099 | TRUE | 497.3995 | 293.3262 | 0.1823 | 5 | 2.4872e-05 | 3496 | 0.065404 | 3416 | 1.6312e-06 | 8.156e-06 | 3541 |  | 3324
8274 | SALT SPRINGS 21013116 | 163692101 | SALT SPRINGS 2101 | 3116 | FALSE | 1685.1043 | 1250.9687 | 0.77748 | 10 | 2.4549e-05 | 3500 | 0.066175 | 3176 | 1.6267e-06 | 1.6267e-05 | 3542 | 0.01 | 2592
1788 | BERKELEY F 0402502466 | 12060402 | BERKELEY F 0402 | 502466 | TRUE | 854.2839 | 226.0238 | 0.14047 | 10 | 2.4427e-05 | 3501 | 0.065532 | 3357 | 1.6151e-06 | 1.6151e-05 | 3543 |  | 2745
2459 | BERKELEY F 1105CB | 12061105 | BERKELEY F 1105 | CB | FALSE | 12969.6445 | 1669.1452 | 1.0374 | 103 | 2.4362e-05 | 3504 | 0.065322 | 3453 | 1.6033e-06 | 0.00016514 | 3544 | 0.03 | 2287
179 | EL CERRITO G 1108BR346 | 12501108 | EL CERRITO G 1108 | BR346 | TRUE | 11386.6089 | 0 | 0 | 102 | 2.4397e-05 | 3502 | 0.065147 | 3620 | 1.5894e-06 | 0.00016212 | 3545 | 0.02 | 2439
1332 | HOLLYWOOD 0401CB | 13170401 | HOLLYWOOD 0401 | CB | FALSE | 8520.938 | 4604.9325 | 2.862 | 70 | 2.3671e-05 | 3507 | 0.065808 | 3264 | 1.5619e-06 | 0.00010933 | 3546 | 0.05 | 2038
6502 | ESTUDILLO 0401850884 | 13480401 | ESTUDILLO 0401 | 850884 | FALSE | 2534.335 | 1368.1711 | 0.85032 | 19 | 2.3486e-05 | 3510 | 0.065756 | 3294 | 1.5552e-06 | 2.9549e-05 | 3547 |  | 3036
1386 | PACIFICA 1103915474 | 22811103 | PACIFICA 1103 | 915474 | TRUE | 13475.5148 | 697.4237 | 0.43345 | 98 | 2.3059e-05 | 3511 | 0.065213 | 3504 | 1.5073e-06 | 0.00014771 | 3548 |  | 2723
1210 | COTATI 110283200 | 42271102 | COTATI 1102 | 83200 | TRUE | 4654.5591 | 0 | 0 | 48 | 2.2575e-05 | 3514 | 0.065158 | 3558 | 1.471e-06 | 7.0606e-05 | 3549 |  | 2716
7453 | SNEATH LANE 110748338 | 22721107 | SNEATH LANE 1107 | 48338 | TRUE | 1760.6636 | 181.1517 | 0.11259 | 17 | 2.2364e-05 | 3515 | 0.065147 | 3613 | 1.4569e-06 | 2.4768e-05 | 3550 | 0.03 | 2329
4821 | RALSTON 11029126 | 24141102 | RALSTON 1102 | 9126 | FALSE | 3038.2902 | 1621.4045 | 1.0077 | 25 | 2.1702e-05 | 3526 | 0.065969 | 3226 | 1.4329e-06 | 3.5823e-05 | 3551 | 0.04 | 2080
7237 | PACIFIC GROVE 04222614 | 182440422 | PACIFIC GROVE 0422 | 2614 | FALSE | 3446.6772 | 1037.2147 | 0.64463 | 28 | 2.1909e-05 | 3521 | 0.065331 | 3444 | 1.4317e-06 | 4.0087e-05 | 3552 | 0.03 | 2331
1100 | DEL MONTE 210386496 | 182222103 | DEL MONTE 2103 | 86496 | FALSE | 10364.0845 | 1600.54 | 0.99474 | 94 | 2.1714e-05 | 3525 | 0.065366 | 3430 | 1.4269e-06 | 0.00013413 | 3553 | 0.02 | 2498
8851 | SAN CARLOS 1103888954 | 24181103 | SAN CARLOS 1103 | 888954 | TRUE | 504.7129 | 0 | 0 | 6 | 2.1724e-05 | 3524 | 0.065147 | 3623 | 1.4152e-06 | 8.4914e-06 | 3554 |  | 3272
2645 | OAKLAND J 1106CR164 | 12091106 | OAKLAND J 1106 | CR164 | FALSE | 10563.0436 | 2405.3877 | 1.495 | 85 | 2.1366e-05 | 3530 | 0.065434 | 3402 | 1.4079e-06 | 0.00011967 | 3555 | 0.03 | 2312
7417 | EL CERRITO G 1112209865 | 12501112 | EL CERRITO G 1112 | 209865 | TRUE | 1489.582 | 423.0102 | 0.2629 | 11 | 2.1415e-05 | 3529 | 0.065497 | 3369 | 1.4074e-06 | 1.5482e-05 | 3556 |  | 3125
45 | OAKLAND J 1105153228 | 12091105 | OAKLAND J 1105 | 153228 | TRUE | 6680.4391 | 463.496 | 0.28806 | 54 | 2.1538e-05 | 3528 | 0.065195 | 3513 | 1.4041e-06 | 7.5821e-05 | 3557 | 0.02 | 2445
8437 | SWIFT 2109XR300 | 83392109 | SWIFT 2109 | XR300 | TRUE | 1391.3933 | 526.7556 | 0.32738 | 14 | 2.1221e-05 | 3531 | 0.065331 | 3446 | 1.3951e-06 | 1.9531e-05 | 3558 | 0.04 | 2106
10517 | EL CERRITO G 1110173396 | 12501110 | EL CERRITO G 1110 | 173396 | TRUE | 265.7346 | 265.7346 | 0.16516 | 3 | 2.0973e-05 | 3534 | 0.066004 | 3220 | 1.3889e-06 | 4.1666e-06 | 3559 |  | 3563
9170 | SAN CARLOS 1103313472 | 24181103 | SAN CARLOS 1103 | 313472 | TRUE | 1178.1951 | 43.1608 | 0.026825 | 9 | 2.0676e-05 | 3537 | 0.06529 | 3465 | 1.3509e-06 | 1.2158e-05 | 3560 |  | 3319
9880 | IGNACIO 1103151462 | 42481103 | IGNACIO 1103 | 151462 | TRUE | 247.7748 | 247.7748 | 0.15399 | 3 | 2.0466e-05 | 3540 | 0.066005 | 3216 | 1.3417e-06 | 4.025e-06 | 3561 |  | 3443
8103 | WOODSIDE 1102472928 | 24251102 | WOODSIDE 1102 | 472928 | TRUE | 1622.1027 | 124.8253 | 0.077579 | 14 | 2.0412e-05 | 3541 | 0.065331 | 3448 | 1.3331e-06 | 1.8663e-05 | 3562 |  | 3192
657 | OAKLAND J 1102CR252 | 12091102 | OAKLAND J 1102 | CR252 | FALSE | 9962.669 | 1765.2604 | 1.0971 | 92 | 2.0001e-05 | 3543 | 0.065384 | 3423 | 1.3184e-06 | 0.0001213 | 3563 | 0.03 | 2364
146 | CASTRO VALLEY 1110MR379 | 14091110 | CASTRO VALLEY 1110 | MR379 | FALSE | 2535.6763 | 1749.5827 | 1.0874 | 22 | 1.987e-05 | 3545 | 0.065965 | 3229 | 1.3088e-06 | 2.8794e-05 | 3564 |  | 2658
9441 | MORRO BAY 11013487 | 183011101 | MORRO BAY 1101 | 3487 | TRUE | 2909.578 | 0 | 0 | 20 | 1.9374e-05 | 3547 | 0.065147 | 3626 | 1.2622e-06 | 2.5244e-05 | 3565 |  | 3359
5751 | FORT BRAGG A 1104CB | 42761104 | FORT BRAGG A 1104 | CB | TRUE | 4613.0306 | 118.7443 | 0.0738 | 41 | 1.9334e-05 | 3548 | 0.065148 | 3592 | 1.2596e-06 | 5.1642e-05 | 3566 | 0.02 | 2443
8075 | ALTO 1124246034 | 42031124 | ALTO 1124 | 246034 | TRUE | 413.5355 | 202.2758 | 0.12572 | 4 | 1.9193e-05 | 3549 | 0.065471 | 3380 | 1.2578e-06 | 5.0314e-06 | 3567 |  | 3188
447 | OCEANO 1105V44 | 182601105 | OCEANO 1105 | V44 | FALSE | 1767.9988 | 1259.7645 | 0.78295 | 17 | 1.8999e-05 | 3551 | 0.065827 | 3260 | 1.2575e-06 | 2.1378e-05 | 3568 | 0.03 | 2281
3262 | OAKLAND J 1106CR330 | 12091106 | OAKLAND J 1106 | CR330 | FALSE | 3874.576 | 1155.5838 | 0.7182 | 31 | 1.8986e-05 | 3552 | 0.065438 | 3399 | 1.2463e-06 | 3.8635e-05 | 3569 | 0.03 | 2322
650 | OAKLAND J 1116CR328 | 12091116 | OAKLAND J 1116 | CR328 | TRUE | 7907.5061 | 956.1241 | 0.59424 | 68 | 1.9049e-05 | 3550 | 0.065298 | 3462 | 1.2458e-06 | 8.4712e-05 | 3570 |  | 2687
4530 | VIEJO 220285904 | 182852202 | VIEJO 2202 | 85904 | FALSE | 3179.0036 | 1684.9898 | 1.0472 | 24 | 1.8827e-05 | 3555 | 0.065629 | 3329 | 1.2443e-06 | 2.9864e-05 | 3571 | 0.03 | 2340
4873 | ALHAMBRA 110213333 | 14101102 | ALHAMBRA 1102 | 13333 | TRUE | 480.3389 | 70.7861 | 0.043994 | 4 | 1.8911e-05 | 3554 | 0.065469 | 3382 | 1.2398e-06 | 4.9594e-06 | 3572 | 0.02 | 2476
5686 | MORRO BAY 1102V80 | 183011102 | MORRO BAY 1102 | V80 | TRUE | 3197.8948 | 222.7519 | 0.13844 | 28 | 1.8567e-05 | 3557 | 0.065193 | 3516 | 1.2121e-06 | 3.3939e-05 | 3573 |  | 2973
495 | BELMONT 11109090 | 24031110 | BELMONT 1110 | 9090 | TRUE | 4202.8057 | 0 | 0 | 38 | 1.848e-05 | 3559 | 0.065147 | 3627 | 1.2039e-06 | 4.5748e-05 | 3574 |  | 2679
1032 | ALTO 1123CB | 42031123 | ALTO 1123 | CB | TRUE | 9405.5468 | 893.6462 | 0.5554 | 84 | 1.7813e-05 | 3561 | 0.065258 | 3477 | 1.1648e-06 | 9.7839e-05 | 3575 | 0.03 | 2356
4356 | BELMONT 11038956 | 24031103 | BELMONT 1103 | 8956 | TRUE | 2231.1917 | 474.6132 | 0.29497 | 18 | 1.7617e-05 | 3564 | 0.065361 | 3432 | 1.1529e-06 | 2.0752e-05 | 3576 |  | 2884
3862 | GREENBRAE 1104751 | 43091104 | GREENBRAE 1104 | 751 | TRUE | 4384.8994 | 264.612 | 0.16446 | 31 | 1.7653e-05 | 3563 | 0.065234 | 3487 | 1.1521e-06 | 3.5714e-05 | 3577 | 0.02 | 2530
3522 | CHESTER 1101CB | 103181101 | CHESTER 1101 | CB | TRUE | 8238.1953 | 128.9588 | 0.080148 | 69 | 1.7565e-05 | 3565 | 0.065167 | 3548 | 1.1453e-06 | 7.9023e-05 | 3578 | 0.04 | 2203
1797 | BERKELEY F 1103BR110 | 12061103 | BERKELEY F 1103 | BR110 | TRUE | 5064.9775 | 0 | 0 | 45 | 1.7521e-05 | 3566 | 0.065147 | 3628 | 1.1415e-06 | 5.1365e-05 | 3579 | 18.55 | 320
3950 | MONTEREY 04022644 | 182090402 | MONTEREY 0402 | 2644 | FALSE | 2922.7748 | 1828.1218 | 1.1362 | 23 | 1.7252e-05 | 3567 | 0.065706 | 3306 | 1.1355e-06 | 2.6115e-05 | 3580 | 0.03 | 2385
3110 | KIRKER 2104CB | 14452104 | KIRKER 2104 | CB | TRUE | 16910.3925 | 74.5132 | 0.04631 | 140 | 1.6863e-05 | 3571 | 0.065612 | 3334 | 1.1257e-06 | 0.0001576 | 3581 |  | 2813
973 | DEL MONTE 110138582 | 182221101 | DEL MONTE 1101 | 38582 | TRUE | 8624.1276 | 853.8778 | 0.53069 | 53 | 1.7201e-05 | 3569 | 0.065245 | 3483 | 1.1245e-06 | 5.9598e-05 | 3582 |  | 2701
72 | PACIFICA 11026783 | 22811102 | PACIFICA 1102 | 6783 | TRUE | 6579.5365 | 0 | 0 | 50 | 1.7237e-05 | 3568 | 0.065147 | 3629 | 1.1229e-06 | 5.6147e-05 | 3583 | 1.8 | 643
6129 | PERRY 1101W12 | 183071101 | PERRY 1101 | W12 | FALSE | 10251.7677 | 6046.1264 | 3.7577 | 70 | 1.562e-05 | 3581 | 0.06699 | 2947 | 1.0833e-06 | 7.5829e-05 | 3584 | 0.07 | 1755
3828 | ALTO 1120500 | 42031120 | ALTO 1120 | 500 | TRUE | 5066.4275 | 426.2211 | 0.2649 | 39 | 1.6529e-05 | 3573 | 0.065312 | 3454 | 1.0777e-06 | 4.203e-05 | 3585 |  | 2856
2036 | SAN LEANDRO U 1114MR218 | 13111114 | SAN LEANDRO U 1114 | MR218 | FALSE | 18150.1664 | 10386.8132 | 6.4554 | 134 | 1.6173e-05 | 3577 | 0.065722 | 3303 | 1.0693e-06 | 0.00014329 | 3586 | 0.06 | 1868
66 | OAKLAND X 1105CB | 12541105 | OAKLAND X 1105 | CB | FALSE | 18622.3449 | 1675.1277 | 1.0411 | 153 | 1.6122e-05 | 3579 | 0.065231 | 3490 | 1.0578e-06 | 0.00016184 | 3587 | 0.03 | 2299
3740 | BERKELEY F 0402CB | 12060402 | BERKELEY F 0402 | CB | TRUE | 2575.0657 | 47.0231 | 0.029225 | 21 | 1.6197e-05 | 3575 | 0.065147 | 3630 | 1.0552e-06 | 2.2159e-05 | 3588 | 0.03 | 2266
2665 | VALLEY VIEW 1105P190 | 14341105 | VALLEY VIEW 1105 | P190 | TRUE | 3318.5959 | 0 | 0 | 28 | 1.6177e-05 | 3576 | 0.065148 | 3590 | 1.0539e-06 | 2.951e-05 | 3589 | 0.06 | 1830
62 | BAY MEADOWS 2102CB | 24012102 | BAY MEADOWS 2102 | CB | TRUE | 11158.113 | 159.3502 | 0.099037 | 95 | 1.5874e-05 | 3580 | 0.065161 | 3554 | 1.0373e-06 | 9.8546e-05 | 3590 |  | 2653
3225 | VALLEY VIEW 1105CB | 14341105 | VALLEY VIEW 1105 | CB | TRUE | 7478.2552 | 0 | 0 | 59 | 1.558e-05 | 3582 | 0.06517 | 3542 | 1.0169e-06 | 5.9995e-05 | 3591 | 0.04 | 2225
1682 | OAKLAND J 1118CR198 | 12091118 | OAKLAND J 1118 | CR198 | TRUE | 8475.9687 | 515.4771 | 0.32037 | 70 | 1.5357e-05 | 3584 | 0.065239 | 3486 | 1.006e-06 | 7.0418e-05 | 3592 | 0.02 | 2547
6551 | EL CERRITO G 1111760530 | 12501111 | EL CERRITO G 1111 | 760530 | TRUE | 2038.4891 | 342.5788 | 0.21291 | 13 | 1.4653e-05 | 3588 | 0.065542 | 3354 | 9.624e-07 | 1.2511e-05 | 3593 |  | 3041
838 | MORRO BAY 1102W22 | 183011102 | MORRO BAY 1102 | W22 | FALSE | 10106.4598 | 4174.2289 | 2.5943 | 85 | 1.451e-05 | 3590 | 0.065661 | 3323 | 9.5877e-07 | 8.1495e-05 | 3594 | 0.1 | 1467
2660 | CASTRO VALLEY 1105MR201 | 14091105 | CASTRO VALLEY 1105 | MR201 | FALSE | 13962.3911 | 2014.3888 | 1.252 | 112 | 1.4628e-05 | 3589 | 0.065296 | 3463 | 9.5698e-07 | 0.00010718 | 3595 |  | 2794
6961 | SAUSALITO 11021224 | 42491102 | SAUSALITO 1102 | 1224 | TRUE | 3249.7676 | 17.2769 | 0.010738 | 29 | 1.4357e-05 | 3591 | 0.065191 | 3519 | 9.3531e-07 | 2.7124e-05 | 3596 | 0.02 | 2522
2515 | EL CERRITO G 1113CB | 12501113 | EL CERRITO G 1113 | CB | TRUE | 6943.4772 | 158.1749 | 0.098306 | 63 | 1.4057e-05 | 3592 | 0.065208 | 3508 | 9.1814e-07 | 5.7843e-05 | 3597 | 0.06 | 1787
3037 | EL CERRITO G 1108CB | 12501108 | EL CERRITO G 1108 | CB | TRUE | 11783.4703 | 4.3429 | 0.0026991 | 99 | 1.3941e-05 | 3593 | 0.065147 | 3631 | 9.0819e-07 | 8.9911e-05 | 3598 | 0.02 | 2417
2758 | VALLEY VIEW 1105P124 | 14341105 | VALLEY VIEW 1105 | P124 | TRUE | 5089.5347 | 0 | 0 | 43 | 1.3878e-05 | 3594 | 0.065148 | 3584 | 9.0411e-07 | 3.8877e-05 | 3599 | 0.02 | 2525
3672 | EDES 1112CB | 13681112 | EDES 1112 | CB | TRUE | 911.838 | 70.4619 | 0.043792 | 16 | 1.3748e-05 | 3595 | 0.065227 | 3494 | 8.9903e-07 | 1.4384e-05 | 3600 | 0.03 | 2275
2376 | VIEJO 22049110 | 182852204 | VIEJO 2204 | 9110 | TRUE | 6943.3735 | 472.9116 | 0.29392 | 58 | 1.3463e-05 | 3596 | 0.06517 | 3544 | 8.7872e-07 | 5.0966e-05 | 3601 | 0.03 | 2318
552 | ALTO 112088190 | 42031120 | ALTO 1120 | 88190 | TRUE | 4658.7637 | 163.0348 | 0.10133 | 34 | 1.3144e-05 | 3598 | 0.065223 | 3499 | 8.5763e-07 | 2.9159e-05 | 3602 | 0.01 | 2609
5498 | VIEJO 22049440 | 182852204 | VIEJO 2204 | 9440 | TRUE | 5507.5 | 123.7395 | 0.076905 | 55 | 1.3106e-05 | 3599 | 0.065171 | 3541 | 8.5438e-07 | 4.6991e-05 | 3603 |  | 2959
10858 | SOLEDAD 2101125484 | 182052101 | SOLEDAD 2101 | 125484 | FALSE | 2451.828 | 1202.5462 | 0.74739 | 4 | 1.3036e-05 | 3600 | 11.9509 | 2589 | 8.4928e-07 | 3.3971e-06 | 3604 |  | 3614
10655 | OCEANO 1104793774 | 182601104 | OCEANO 1104 | 793774 | TRUE | 378.8633 | 111.8888 | 0.069539 | 3 | 1.2894e-05 | 3602 | 0.065147 | 3633 | 8.3998e-07 | 2.52e-06 | 3605 |  | 3586
4160 | EL CERRITO G 1110CB | 12501110 | EL CERRITO G 1110 | CB | TRUE | 4157.1829 | 423.1153 | 0.26297 | 35 | 1.2627e-05 | 3603 | 0.065184 | 3531 | 8.2339e-07 | 2.8819e-05 | 3606 | 0.04 | 2089
5087 | EDES 1112714759 | 13681112 | EDES 1112 | 714759 | TRUE | 1469.7626 | 361.9191 | 0.22493 | 11 | 1.2348e-05 | 3605 | 0.065497 | 3372 | 8.1071e-07 | 8.9178e-06 | 3607 |  | 2936
2691 | BOSTON 0401CR242 | 13320401 | BOSTON 0401 | CR242 | TRUE | 7351.3672 | 499.489 | 0.31043 | 59 | 1.2355e-05 | 3604 | 0.065191 | 3520 | 8.0537e-07 | 4.7517e-05 | 3608 | 0.02 | 2462
425 | CASTRO VALLEY 1105MR236 | 14091105 | CASTRO VALLEY 1105 | MR236 | FALSE | 13624.1451 | 2212.8784 | 1.3753 | 112 | 1.2234e-05 | 3607 | 0.065342 | 3441 | 8.0193e-07 | 8.9816e-05 | 3609 |  | 2670
5569 | MORRO BAY 1101CB | 183011101 | MORRO BAY 1101 | CB | TRUE | 3472.0335 | 0 | 0 | 28 | 1.2296e-05 | 3606 | 0.065147 | 3624 | 8.0102e-07 | 2.2429e-05 | 3610 | 0.02 | 2412
513 | OAKLAND J 1116CB | 12091116 | OAKLAND J 1116 | CB | TRUE | 30164.8941 | 0 | 0 | 253 | 1.2121e-05 | 3608 | 0.065147 | 3612 | 7.8965e-07 | 0.00019978 | 3611 |  | 2681
4433 | MONTEREY 04012642 | 182090401 | MONTEREY 0401 | 2642 | TRUE | 3637.2616 | 0 | 0 | 28 | 1.2095e-05 | 3609 | 0.065148 | 3594 | 7.8793e-07 | 2.2062e-05 | 3612 | 0.02 | 2511
1060 | SAN LEANDRO U 1114MR545 | 13111114 | SAN LEANDRO U 1114 | MR545 | FALSE | 7246.1985 | 3496.0754 | 2.1728 | 66 | 1.1654e-05 | 3610 | 0.065789 | 3280 | 7.6919e-07 | 5.0766e-05 | 3613 | 0.06 | 1782
8159 | SAN LUIS OBISPO 1103191498 | 182631103 | SAN LUIS OBISPO 1103 | 191498 | TRUE | 267.6915 | 189.8568 | 0.118 | 2 | 1.1046e-05 | 3611 | 0.065789 | 3281 | 7.2794e-07 | 1.4559e-06 | 3614 |  | 3198
749 | WALDO 0401CB | 13350401 | WALDO 0401 | CB | TRUE | 6516.7767 | 0 | 0 | 56 | 1.0513e-05 | 3612 | 0.06517 | 3543 | 6.8547e-07 | 3.8386e-05 | 3615 | 0.03 | 2378
8960 | OCEANO 1104337754 | 182601104 | OCEANO 1104 | 337754 | TRUE | 259.7315 | 97.7177 | 0.060732 | 3 | 9.3717e-06 | 3613 | 0.065147 | 3606 | 6.1054e-07 | 1.8316e-06 | 3616 |  | 3283
11035 | SOLEDAD 2101404754 | 182052101 | SOLEDAD 2101 | 404754 | FALSE | 1404.0353 | 1388.0334 | 0.86267 | 2 | 8.7569e-06 | 3616 | 0.065789 | 3284 | 5.7048e-07 | 1.141e-06 | 3617 |  | 3630
2616 | DEL MONTE 21029060 | 182222102 | DEL MONTE 2102 | 9060 | FALSE | 14415.2582 | 1524.9134 | 0.94774 | 98 | 8.4533e-06 | 3617 | 0.065226 | 3496 | 5.5361e-07 | 5.4254e-05 | 3618 | 0.58 | 857
3316 | SAN LEANDRO U 1114501762 | 13111114 | SAN LEANDRO U 1114 | 501762 | TRUE | 2438.6275 | 775.0508 | 0.4817 | 23 | 8.4178e-06 | 3618 | 0.065482 | 3377 | 5.5098e-07 | 1.2672e-05 | 3619 |  | 2821
9297 | PACIFICA 1102934870 | 22811102 | PACIFICA 1102 | 934870 | TRUE | 804.8523 | 147.5524 | 0.091704 | 7 | 8.4048e-06 | 3619 | 0.065514 | 3365 | 5.496e-07 | 3.8472e-06 | 3620 |  | 3338
7940 | SAN LEANDRO U 1109CR284 | 13111109 | SAN LEANDRO U 1109 | CR284 | FALSE | 1550.6574 | 1235.8311 | 0.76807 | 14 | 7.7666e-06 | 3623 | 0.066065 | 3205 | 5.1364e-07 | 7.191e-06 | 3621 | 0.04 | 2148
3930 | SAN LEANDRO U 1109CR002 | 13111109 | SAN LEANDRO U 1109 | CR002 | TRUE | 1715.8521 | 269.8408 | 0.16771 | 16 | 7.83e-06 | 3620 | 0.065308 | 3461 | 5.1358e-07 | 8.2173e-06 | 3622 | 0.13 | 1341
5801 | BELMONT 1110330790 | 24031110 | BELMONT 1110 | 330790 | TRUE | 714.0791 | 199.5624 | 0.12403 | 8 | 7.7899e-06 | 3621 | 0.065468 | 3389 | 5.0999e-07 | 4.0799e-06 | 3623 |  | 2979
915 | WALDO 0402CB | 13350402 | WALDO 0402 | CB | TRUE | 3475.548 | 0 | 0 | 27 | 7.7732e-06 | 3622 | 0.065147 | 3610 | 5.064e-07 | 1.3673e-05 | 3624 | 0.05 | 1955
472 | BANCROFT 0401CB | 13030401 | BANCROFT 0401 | CB | TRUE | 13277.3465 | 69.3073 | 0.043075 | 103 | 7.67e-06 | 3624 | 0.065147 | 3609 | 4.9968e-07 | 5.1467e-05 | 3625 |  | 2677
4940 | BERKELEY T 0404CB | 12660404 | BERKELEY T 0404 | CB | TRUE | 1942.0349 | 0 | 0 | 20 | 7.5209e-06 | 3625 | 0.065211 | 3506 | 4.9106e-07 | 9.8213e-06 | 3626 |  | 2929
206 | PACIFICA 110252715 | 22811102 | PACIFICA 1102 | 52715 | TRUE | 6122.4469 | 0 | 0 | 60 | 7.374e-06 | 3626 | 0.065147 | 3605 | 4.8039e-07 | 2.8824e-05 | 3627 |  | 2661
4875 | OCEANO 1105V48 | 182601105 | OCEANO 1105 | V48 | TRUE | 4125.7287 | 198.7298 | 0.12351 | 39 | 7.0816e-06 | 3628 | 0.06518 | 3536 | 4.6154e-07 | 1.8e-05 | 3628 | 0.02 | 2477
3910 | SAN LEANDRO U 1114458451 | 13111114 | SAN LEANDRO U 1114 | 458451 | FALSE | 3952.1728 | 1967.4653 | 1.2228 | 29 | 6.9026e-06 | 3629 | 0.06559 | 3336 | 4.5289e-07 | 1.3134e-05 | 3629 |  | 2862
1300 | BANCROFT 0402CB | 13030402 | BANCROFT 0402 | CB | TRUE | 7369.6347 | 597.2084 | 0.37117 | 58 | 6.6635e-06 | 3630 | 0.065191 | 3518 | 4.3467e-07 | 2.5211e-05 | 3630 | 0.02 | 2520
1186 | VIEJO 220436948 | 182852204 | VIEJO 2204 | 36948 | TRUE | 13534.0061 | 809.6273 | 0.50319 | 109 | 6.1078e-06 | 3631 | 0.065183 | 3533 | 3.9816e-07 | 4.34e-05 | 3631 |  | 2715
8981 | CASTRO VALLEY 1105132304 | 14091105 | CASTRO VALLEY 1105 | 132304 | TRUE | 1491.8996 | 118.6631 | 0.07375 | 13 | 5.8099e-06 | 3632 | 0.065147 | 3607 | 3.785e-07 | 4.9205e-06 | 3632 |  | 3288
3358 | FORT BRAGG A 110436526 | 42761104 | FORT BRAGG A 1104 | 36526 | TRUE | 10589.2357 | 72.2645 | 0.044913 | 84 | 5.5602e-06 | 3633 | 0.065163 | 3552 | 3.6398e-07 | 3.0574e-05 | 3633 | 0.02 | 2418
6760 | MORRO BAY 1101W04 | 183011101 | MORRO BAY 1101 | W04 | TRUE | 3941.4804 | 437.2441 | 0.27175 | 26 | 3.5981e-06 | 3634 | 0.065147 | 3634 | 2.344e-07 | 6.0945e-06 | 3634 |  | 3060
11118 | DIABLO CANYON 1101CB | 189001101 | DIABLO CANYON 1101 | CB | TRUE | 0 | 0 | 0 |  |  | 3635 |  | 3635 |  | 0 | 3635 |  | 3635

## Cancelled Projects
Order | KEEP | Exec. Status | LTIP Condition 1 | LTIP Condition 2 | Priority | Original OH Miles | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | 2018 KPMG CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notif. | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | EASOP Risk Reduced | EASOP NPV ($000) | EASOP RSE | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost
35219265 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3843.5 | UNSE | 102251101 | CRESTA 1101 | CRESTA 1101546650 | 6 | 0.89694 | 33 | 3.0174 | 0.50291 | 845 | 0 |  | Tier 2 & 3 | CWSP | OROVILLE | Butte | North Valley | Northern | 5543353 | E.5034700.01.01 | 120141941 | 35219265 | CWSP - CRESTA 1101546650 | 4752 | 0 | 0 | 0 |  | 2021-00911 | 2323.2 | 0.44 | 500000 |  |  |  |  | 0 | 0 |  |  |  | 0
35224320 | RE-ASSIGN |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 0 | UNSE | 42301101 | TULUCAY 1101 | TULUCAY 1101628 | 98 | 4.1726 | 338 | 19.2923 | 0.19686 | 448 | 0 | 2350 | Tier 2 | WDDB | NAPA | Napa | North Bay | Bay Area | 5530168 |  | 113676059 | 31354988 | TULUCAY 1101 RECOND WITH TREE WIRE | 10050 | 0 | 0 | 0 |  | 2020-88272 | 7392 | 1.4 | 2360320 |  |  |  |  | 0 | 0 |  |  |  | 0
35219092 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3311.75 | UNSE | 253642104 | POSO MOUNTAIN 2104 | POSO MOUNTAIN 2104CB | 38 | 5.3534 | 15 | 26.7607 | 0.70423 | 51 | 0 |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794539 | E.5034691.01.01 | 120141620 | 35219092 | CWSP - POSO MOUNTAIN 2104CB | 28248 | 0 | 0 | 0 | [9 empty] | 0 | 0 |  |  |  | 0
35219264 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 2965.22 | UNSE | 253642103 | POSO MOUNTAIN 2103 | POSO MOUNTAIN 2103CB | 10 | 2.3287 | 30 | 5.1619 | 0.51619 | 2 | 0 |  |  | CWSP | BAKERSFIELD | Kern | Kern | Central Valley | 5794550 | E.5034699.01.01 | 120141886 | 35219264 | CWSP - POSO MOUNTAIN 2103CB | 12302.4 | 0 | 0 | 0 | [9 empty] | 0 | 0 |  |  |  | 0
35219282 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 1866.02 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | 0 |  | Tier 2 | CWSP | DUBLIN | Alameda | Mission | Central Coast | 5543349 | E.5034711.01.01 | 120142312 | 35219282 | CWSP - NORTH DUBLIN 2101 CB | 5280 | 0 | 0 | 0 |  | 2020-88260 | 5280 | 1 | 1699520 | 2021-04299 |  |  |  | 0 | 0 |  |  |  | 0
35219283 | CANCEL |  | MEET | No |  |  |  | 0 | 2021 |  |  | 0 | 3025.68 | UNSE | 14052101 | NORTH DUBLIN 2101 | NORTH DUBLIN 2101CB | 23 | 1.7629 | 47 | 9.8576 | 0.42859 | 388 | 0 |  | Tier 2 | CWSP | PLEASANTON | Contra Costa | Mission | Central Coast | 5543351 | E.5034712.01.01 | 120142316 | 35219283 | CWSP - NORTH DUBLIN 2101 CB | 4329.6 | 0 | 0 | 0 |  | 2020-88250 | 4329.6 | 0.82 | 1370560 | 2021-04306 |  |  |  | 0 | 0 |  |  |  | 0
35223061 | CANCEL |  | MEET | MEET |  |  |  | 0 | 2021 |  |  | 0 | 840.53 | UNSE | 42711102 | CALISTOGA 1102 | CALISTOGA 1102634 | 178 | 11.216 | 1477 | 5.2284 | 0.029373 | 1599 | 0 |  |  | PSPS | CALISTOGA | Napa | North Bay | Bay Area | 5794986 | E.5034762.01.02 | 120242677 | 35223061 | PSPS - Calistoga 1102634 | 0 | 4752 | 0 | 0 |  | 2021-01583 | 4752 | 0.9 | 711300 | 2021-07704 |  |  |  | 0 |  |  |  |  | 0
35098621 | Completed |  | COMP |  |  |  | 1.07 | 0 | 2020 | 1.07 |  | 1.07 | 1372204.3 | DOCC | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.0162 | 198 | Tier 3 | PRE | NORTH SAN JUAN | Nevada | Sierra | Northern | 5785303 | E.5015491.04 | 117177530 | 35098621 | CWSP-COLUMBIA HILL 1101-LR2212-PH4 | 1881 | 3761 | 0 | 0 |  | 2018-57269 | 9820.8 | 1.86 | 1975040 | 2019-28761 | 0 | 0 | 5649.6 | 5649.6 | 1.07 | 2054400 |  |  |  | 2019-39374 | 2020-25928 | 0 | 3761 | 1881 | 5642 | 1.0686 | 2185500 | 2927538 | 387.3626
|  |  | CNCL |  |  |  | 0.04 | 0.04 | 2021 |  |  |  | 0 | CNCL | 48011144 | CALPINE 1144 | CALPINE 1144304 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! |  |  | CWSP |  |  |  |  | 5543354 | E.5034701.01.01 |  | CNCL | CWSP - CALPINE 1144304 | [13 empty] | 0 | 0
35145522 | PSPS - HOLD |  | HOLD |  |  |  | 3.95 | 3.95 | 2021 |  |  |  | 142609.46 | PEND | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | 107 | 8.8028 | 134 | 32.5187 | 0.30391 | 385 | 14.4458 | 541 | Tier 3 | PSPS | El Dorado Hills | El Dorado | Sierra | Northern | 5788783 | E.5025635.01 | 118265394 | 35145522 | PSPS - Clarksville 2104 - CB | 0 | 13464 | 0 | 0 |  | 2019-80671 | 13464 | 2.55 | 23720000 | N/A | 0 | 13464 | 0 | 13464 | 2.55 | 10710000 |  |  |  | 2020-38602
35145001 | PSPS - HOLD |  | HOLD |  |  |  | 1.6 | 1.6 | 2021 |  |  |  | 146558.55 | PEND | 12022215 | CLAYTON 2215 | CLAYTON 2215184604 | 106 | 2.0891 | 1739 | 1.7951 | 0.016935 | 1716 | 1.3512 | 1165 | Tier 3 | PSPS | CONCORD | CONTRA COSTA | Diablo | Bay Area | 5788778 | E.5025639 | 118259181 | 35145001 | PSPS - Clayton 2215 – CB | 475.2 | 20592 | 0 | 0 |  | 2019-79149 | 11616 | 2.2 | 19530000 | N/A | 0 | 20592 | 475.2 | 21067.2 | 3.99 | 16758000
35145002 | PSPS - HOLD |  | HOLD |  |  |  | 0.68 | 0.68 | 2021 |  |  |  | 115275.8 | APPR | 42481101 | IGNACIO 1101 | IGNACIO 1101CB | 19 | 1.6722 | 2448 | 0.042331 | 0.0022279 | 2447 | 0.017042 | 2421 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788780 | E.5025640 | 118262844 | 35145002 | PSPS - Ignacio 1101 - CB | 0 | 3590.4 | 0 | 0 |  | 2019-78952 | 3585.12 | 0.679 | 2194800 | N/A | 0 | 3590.4 | 0 | 3590.4 | 0.68 | 2856000
35145003 | PSPS - HOLD |  | HOLD |  |  |  | 0.28 | 0.28 | 2021 |  |  |  | 92273.67 | PEND | 13801103 | MORAGA 1103 | MORAGA 1103CB | 82 | 1.3309 | 2631 | 0.082476 | 0.0010058 | 2698 | 0.017178 | 2231 | Tier 3 | PSPS | ORINDA | CONTRA COSTA | Diablo | Bay Area | 5788781 | E.5025641 | 118263229 | 35145003 | PSPS - Moraga 1103 - CB | 0 | 1161.6 | 0 | 0 |  | 2019-78960 | 1161.6 | 0.22 | 2050000 | N/A | 0 | 1161.6 | 0 | 1161.6 | 0.22 | 924000 |  |  |  | 2020-33628
35144941 | PSPS - HOLD |  | HOLD |  |  |  | 2.59 | 2.59 | 2021 |  |  |  | 180088.06 | ADER | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105CB | 86 | 7.4461 | 2633 | 0.086208 | 0.0010024 | 2727 | 0.020645 | 1376 | Tier 3 | PSPS | SANTA CRUZ | SANTA CRUZ | Central Coast | Central Coast | 5788792 | E.5025646 | 118261469 | 35144941 | PSPS - Paul Sweet 2105 - CB PH 1 | 17212.8 | 1056 | 0 | 0 |  | 2020-07355 | 16737.6 | 3.17 | 4786588 | N/A | 0 | 1056 | 17212.8 | 18268.8 | 3.46 | 14532000 |  |  |  | 2020-45854
35144943 | PSPS - HOLD |  | HOLD |  |  |  | 0.63 | 0.63 | 2021 |  |  |  | 95498.4 | ESTS | 83692105 | ROB ROY 2105 | ROB ROY 2105CB | 17 | 0.73407 | 2781 | 0.0058961 | 0.00034683 | 2817 | 0.0050096 | 2564 | Tier 3 | PSPS | APTOS | SANTA CRUZ | Central Coast | Central Coast | 5788791 | E.5025648 | 118261587 | 35144943 | PSPS - Rob Roy 2105 - CB | 0 | 2851.2 | 0 | 0 |  | 2020-03578 | 3326.4 | 0.63 | 1574100 | N/A | 0 | 2851.2 | 0 | 2851.2 | 0.54 | 2268000
35145004 | PSPS - HOLD |  | HOLD |  |  |  | 0.62 | 0.62 | 2021 |  |  |  | 86709.38 | PEND | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | 60 | 1.8254 | 3259 | 0.00030957 | 5.1594e-06 | 2856 | 0.00010409 | 1372 | Tier 3 | PSPS | LAFAYETTE | CONTRA COSTA | Diablo | Bay Area | 5788782 | E.5025642 | 118263746 | 35145004 | PSPS - Rossmoor 1106 – CB | 0 | 4171.2 | 0 | 0 |  | 2019-79022 | 2112 | 0.4 | 3720000 | N/A | 0 | 4171.2 | 0 | 4171.2 | 0.79 | 3318000 |  |  |  | 2020-31291
35072360 | In-Construction - HOLD |  | HOLD |  |  |  | 1.05 | 1.05 | 2021 |  |  |  | 718998.64 | CONS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.0086401 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5783906 | E.5015236.01 | 114754229 | 35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 5541 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 5305 | 5305 | 1.0047 | 1929090.9091 |  |  | 0 | 2019-64378 | 2020-45688 | 0 | 0 | 5541 | 5541 | 1.0494 | 1932059 | 2583069 | 348.6842
35144944 | PSPS - HOLD |  | HOLD |  |  |  | 0.26 | 0.26 | 2021 |  |  |  | 118187.81 | PEND | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 | 2144 | 0.036015 | 2845 | Tier 3 | PSPS | SOUTH SAN FRANCISO | SAN MATEO | Peninsula | Central Coast | 5530170 |  | 118261958 | 35144944 | PSPS – Sneath Lane 1107 – CB | 0 | 739.2 | 0 | 0 |  | 2019-78877 | 739.2 | 0.14 | 738936 | N/A | 0 | 739.2 | 0 | 739.2 | 0.14 | 588000 |  |  |  | 2020-18832
35145006 | PSPS - HOLD |  | HOLD |  |  |  | 0.27 | 0.27 | 2021 |  |  |  | 126808.89 | ESTS | 43201101 | STAFFORD 1101 | STAFFORD 1101902998 | 81 | 1.0766 | 3483 | 0.00018615 | 2.2981e-06 | 3428 | 4.6216e-05 | 2388 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788788 | E.5025644 | 118263874 | 35145006 | PSPS - Stafford 1101 - LR 1298 | 0 | 1425.6 | 0 | 0 |  | 2019-79042 | 1425.6 | 0.27 | 2500000 | N/A | 0 | 1425.6 | 0 | 1425.6 | 0.27 | 1134000 |  |  |  | 2020-51115
35116515 | In-Construction - 2 Deferred | 19 | No | No | 2021028 |  | 1.75 | 1.75 | 2021 |  |  | 0 | 152800.55 | UNSC | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.035578 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786036 | E.5015701.02 | 117607998 | 35116515 | CWSP–STANISLAUS 1702-LR1888-PH 1.2 | 9222 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 8765 | 8765 | 1.66 | 3187272.7273 |  |  |  | 2019-69359 | 2020-48497 | 0 | 0 | 9222 | 9222 | 1.7466 | 3203035 | 4438411 | 347.3254
35157845 | In-Construction - Deferred | 20 | No | No | 2021002 | 1.27 | 1.2676 | 1.2676 | 2020 | 0 |  | 0 | 431041.62 | CONS | 43432105 | SILVERADO 2105 | SILVERADO 2105658898 | 151 | 17.1737 | 1361 | 5.4002 | 0.035763 | 1546 | 0.24713 | 104 | Tier 2 | WDDB | SAINT HELENA | Napa | North Bay | Bay Area | 5784869 | E.5014317.04 | 116952175 | 35157845 | SILVERADO 2105 WIRE DOWN - PH 3 | 6693 | 0 | 0 | 0 |  | N/A |  |  |  | N/A | 0 | 0 | 6705.6 | 6705.6 | 1.27 | 2438400 |  |  | 0 | 2020-03939 | 2020-42595 | 0 | 0 | 6693 | 6693 | 1.2676 | 1404334 | 1800634 | 209.8213
35054184 | Top 20% MAVF CPZ | 11 | MEET | No | 2021108 |  | 0.91 | 0.91 | 2021 |  |  | 0 | 21905.73 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.60664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5530173 | E.5019937.01.01 | 114941996 | 35054184 | CWSP-COLUMBIA HILL 1101-TS8233-PH 1 | 4804.8 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 4805 | 0.91004 | 5227500 | 2021-03589 |  |  |  | 0 | 0 |  |  |  | 0
35226659 | Top 20% MAVF CPZ | 11 | MEET | MEET | 2021109 |  | 1.88 | 1.88 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 1.5835 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.02 | 120447026 | 35226659 | CWSP-COLUMBIA HILL 1101-TS8233-PH 2 | 5544 | 4382.4 | 0 | 0 | 2018-69650 | 2018-72909 | 9926 | 1.8799 |  | 2021-03589 | [8 empty] | 0
35226720 | Top 20% MAVF CPZ | 11 | MEET | No | 2021110 |  | 0.52 | 0.52 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.34665 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.03 | 120447027 | 35226720 | CWSP-COLUMBIA HILL 1101-TS8233-PH 3 | 2745.6 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 2746 | 0.52008 |  | 2021-03589 | [8 empty] | 0
35226723 | Top 20% MAVF CPZ | 11 | MEET | MEET | 2021111 |  | 1.04 | 1.04 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.99964 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.04 | 120447110 | 35226723 | CWSP-COLUMBIA HILL 1101-TS8233-PH 4 | 1425.6 | 4065.6 | 0 | 0 | 2018-69650 | 2018-72909 | 5492 | 1.0402 |  | 2021-03589 | [8 empty] | 0
35227204 | Top 20% MAVF CPZ | 11 | MEET | No | 2021112 |  | 1.3 | 1.3 | 2021 |  |  | 0 | 0 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 11012212 | 76 | 9.1336 | 606 | 9.8207 | 0.12922 | 1358 | 0.86664 | 198 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5795126 | E.5019937.01.05 | 120447111 | 35227204 | CWSP-COLUMBIA HILL 1101-TS8233-PH 5 | 6864 | 0 | 0 | 0 | 2018-69650 | 2018-72909 | 6864 | 1.3 |  | 2021-03589 | [8 empty] | 0
Note on B8: [REDACTED] says this job is no longer required. Please cancel.

## De-energized Idle Lines
DEEN Idle Lines
Disposition Category | Item # | Item # (Cat 2) | Location (Webviewer GUID) | # of Idle Segments | Division | HFTD | Circuit ID | Circuit Name | Device | Length (GIS) | De-energization Completed (Y/N) | Within 600 ft of Transmission Line | T-Line within 600 ft | Addtl Information | DEEN Comments | DEEN Category | Idle Removal (I/R) | EC_PM Information
3 | Item 1 | IF Item 1 | {576003C3-CCA3-4D96-83BD-8B8CD5DD2EFF} {190CE1B4-F03D-46D6-BFE3-8D492AFED845} {3A1E720B-8AE3-4178-8FC3-EBE9E00136F8} | 3 | Sierra | Tier 2 | 153082106 | PLACERVILLE 2106 |  | 0.14205 | Y | N |  | De-energize idle line downstream of SAP Pole id 101387670. Idle line SAP Pole ids 103960502, 103960503, 103960504 | Flying bells installed. | Dispatch |  | EC 118283959 PM 35208054 UNSE Status as of 10/22/20, Priority E
3 | Item 2 | IF Item 10 | {3A2880C2-A76D-4DB0-B949-A8302A9311AC} | 1 | North Valley | Tier 3 | 102911103 | WYANDOTTE 1103 |  | 0.29042 | Y | N |  | De-energize idle line downstream of SAP Pole id 100376078. Idle line SAP Pole ids 100426294, 100376077, 100376076, 100426293, 100376075, 100425663. IF 106898732 / RW 110829043 11/3/15 notes to I/R equipment. | This line has burnt down. Jatko Rd Berry Creek - EC tags created - line to be removed. Tag 119782047 - SAP id 100376077 Tag 119782055 - SAP id 100426294 Tag 119782056 - SAP id 100426293 Tag 119782059 - SAP id 100425663 Tag 119782060 - SAP id 100376076 Tag 119846639 - SAP id 100376075 | Dispatch |  | EC 119782047 - SAP id 100376077 EC 119782055 - SAP id 100426294 EC 119782056 - SAP id 100426293 EC 119782059 - SAP id 100425663 EC 119782060 - SAP id 100376076 EC 119846639 - SAP id 100376075 PM 35199234 - 95A Cap Major Event ERDY Status 10/16/20; Priority A
3 | Item 3 | IF Item 11 | {61988FFE-CF66-4A62-A8D0-BC4A5821A7A8} | 1 | North Valley | Tier 2 | 102931101 | COTTONWOOD 1101 |  | 0.26683 | Y | N |  | De-energize idle line downstream of SAP Pole id 101511512. Idle line SAP Pole ids: 101511505, 101511507, 101511508, 101511509, 101511510, 101511511, 101511506 Idle Transformer CGC# - 118726035719 | AFW - De-energized on 11/12/20. | Dispatch |  | EC 110840126 PM 35204801 UNSE Status as of 10/2/20, Priority F
3 | Item 4 | IF Item 12 | {8E6E622B-0FEB-4E5D-A4E1-744345242A8B} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.13743 | Y | N |  | De-energize idle line downstream of SAP Pole id 101519958 . Idle line SAP Pole ids 101519961, 101519960, 101519959 Idle Transformer CGC# - 120233054783 Montgomery Creek Indian Reservation | AFW - Cancelled as line was found de-energized on 11/9/20. | Dispatch |  | EC 110880096 PM 35204835 UNSE Status as of 10/2/20, Priority F
3 | Item 5 | IF Item 13 | {A26BABB5-9636-4D02-B7BB-459B3B7D79FC} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.10502 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480189. Idle line SAP Pole ids 101480187, 101480185 | Installed bells per job order.08/06/2019 07:48:04 PST [REDACTED]. IF investigation complete - Sent letter to customer. Letter was signed for, but received no response within the allotted time. Please I/R: 15 KVA tx (CGC 120116553055) and pole (101480187). | Dispatch |  | EC 117716950 PM35208005 UNSE Status as of 10/22/20, Priority F
4 | Item 6 | IF Item 14 | {3266FF9E-D915-4FF8-84E5-A0EA3A6BCF6E} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.096355 | Y | N |  | De-energize idle line downstream of SAP Pole id 103982823. Idle line SAP Pole ids 101459101, 101459102, 101459103 Idle Transformer CGC# - 119884349548 | This tap line is open at take off pole 1 Pole SE of sap id 101459101 600 ft s/o Swede Creek Rd 7 400 ft w/o Oak Run Rd. ; GC foreman completed PM 35090253 on 7/2020 to replace pole said he left the tap line open and de-energized. | Dispatch |  | Old EC 102544673 was cancelled 2015 IF tag flagged segment as TOS-F No new EC tag found
3 | Item 7 | IF Item 15 | {9A18086E-7D6A-4294-B058-42FE0460712D} | 1 | North Valley | Tier 3 | 103351101 | DESCHUTES 1101 |  | 0.045927 | Y | N |  | De-energize idle line downstream of SAP Pole id 101456353. Idle line SAP Pole ids 101456355, 101456354 Idle Transformer CGC# - 120019549840 | 5/28/20 Safety assessment by [REDACTED] already de-energized. | Dispatch |  | EC 110850632 PM 35204816 UNSE Status as of 10/2/20, Priority F
2 | Item 8 | IF Item 16 | {74E868F9-4884-4A4E-9569-2763757B9DB3} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.18721 | Y | N |  | 6/09/20 Safety assessment - inspection performed by [REDACTED] - no idle facilities found at this location - work already completed. Original I/R for Pole ids 101483592, 101483616, 103313660, 101483618 | 6/09/20 Safety assessment - inspection performed by [REDACTED] - no idle facilities found at this location - work already completed. | Compliance | Removal appears to be completed | Removal appears to be completed
3 | Item 9 | IF Item 17 | {6543650F-F099-40A4-AD93-C7C045536CBB} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 |  | 0.12204 | Y | N |  | De-energize idle line downstream of SAP Pole id 103992280. Idle line SAP Pole Ids 101470353, 101470354, 101470356 Downstream from Active Transformer CGC# - 119542546073 | AFW - De-energized on 11/12/20; installed flying bells.8/11/20 I/R Poles part of PM 35162302 in PEND status, Priority E - Schd Compl Yr 0. | Dispatch |  | PM 35162302 PEND status, Priority E
2 | Item 10 | IF Item 18 | {51437E84-9721-4711-90A5-07E7D44061E6} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.041878 | Y | N |  | 9/03/2020 13:54:37 PST [REDACTED] Phone [REDACTED] and crew completed 8/31/2020. Removed pole # 120565385. Final confirmed construction operation. Construction pkg uploaded into SAP.Orig job for Pole SAP id 101459572Idle Transformer CGC# - 119405347516 | Removal appears to be completed. | Completed per SAP Construction Notes | Removal appears to be completed | Removal appears to be completed
3 | Item 11 | IF Item 19 | {85938312-5226-433D-9824-63E05E8CD1CF} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.045971 | Y | N |  | De-energize idle line downstream of SAP Pole id 101470261. Idle line SAP Pole Id 101470262 Downstream from Active Transformer CGC# - 119341645963 | AFW - De-energized on 11/12/20.PM 35144989 (12/20/19) in ESTS status - Priority F - Schd Compl Yr 1+. | Dispatch |  | PM 35144989 ESTS status, Priority F
4 | Item 12 | IF Item 2 | {73D39B71-D07F-49C9-82CA-CA9AF54FAFA2} {191A669B-561D-431B-B682-B3AEA0508675} {E15C83DD-6D9E-499F-8D02-4838C43A2F2F} | 3 | Central Coast | Tier 2 | 182981102 | JOLON 1102 | Fuse 9189 | 0.086583 | Y | N |  | Idle line SAP Pole ids 103905961, 103905960, 103905959 SAP id associated with Fuse - 101727361 Idle Transformers CGC# - 413728523719, 413727423693 | Fuses are out. 8/23/18 Customer rep called and asked that idle facilities be kept as property is being sold. 6/16/20 Realquest search shows property still belongs to original owner and has not sold. | Dispatch |  | IF Notif 114779549 TOS-AG No recent EC tag found
3 | Item 13 | IF Item 20 | {BDE7B1C1-59B6-42C5-BF78-685CF4B8AB44} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.030087 | Y | N |  | 8/28/18 as part of discovery on another job. Conductor between 25' pole and 45' pole removed. Idle tap line runs to Open Point - Flying Bells installed - mostly likely de-energized unless there are jumpers. See Completed Const Pkg map in SAP: SAP Pole ids 101459086, 101459092 | TX already removed from 45' pole (101459086) on PM 31404117 in 2018 as part of discovery on another job. Conductor between 25' pole and 45' pole removed. Idle tap line runs to Open Point - Flying Bells installed. | Completed per SAP Construction Notes |  | EC 114961329 PM 35211254 UNSE Status as of 11/3/20, Priority F
4 | Item 14 | IF Item 21 | {3DBE3C44-FA24-4FD5-832D-79EDB56CE462} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.18779 | Y | N |  | De-energize idle line downstream of SAP Pole id 101468999. Idle line SAP Pole ids 101469008, 101469010, 101469011, 101469013 | This one is de-energized at the takeoff pole with flying bells cut open. | Dispatch |  | EC 110850642
3 | Item 15 | IF Item 22 | {D23C066B-D42F-47FA-8A00-07210FA157F7} | 1 | North Valley | Tier 2 | 103351104 | DESCHUTES 1104 |  | 0.015091 | Y | N |  | De-energize idle line downstream of SAP Pole id 101469872. Idle line SAP Pole id 101469874 | De-energized as jumpers are open at DE pole. | Dispatch |  | EC 110848230 PM 35204808 UNSE Status as of 10/2/20, Priority F
4 | Item 16 | IF Item 23 | {05403C66-A759-4E07-9234-FBAFBCDA9720} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.055565 | Y | N |  | De-energize idle line downstream of SAP Pole id 101490145. Idle line SAP Pole ids 101490155, 101490146 | The line is de-energized. The primary jumpers are open at the pole SAP 101490145 de-energized to [REDACTED] . | Dispatch |  | EC 116685701
3 | Item 17 | IF Item 24 | {27882F52-129D-4AC3-B879-9963436910AE} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.10463 | Y | N |  | De-energize idle line downstream of SAP Pole id 101490996. Idle line SAP Pole Ids 101490997, 101490998, 101490999 Idle Transformer CGC# - 118891040185 | AFW - De-energized on 11/12/20.SAP Note: 1/5/08 Idle 3 Pole Tap - Customer no longer wants. 11/13/15 IF investigation completed - no response from customer. | Dispatch |  | EC 110852551 PM 35204821 UNSE Status as of 10/2/20, Priority F
3 | Item 18 | IF Item 25 | {365E373B-0227-4801-8061-596AB4B9C91D} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 | Fuse 85883 | 0.071985 | Y | N |  | Idle line SAP Pole ids 101497622, 101497623 SAP id associated with Fuse 101497618 Idle Transformer CGC# - 119122240616 | Open jumpers; no fuses at this location. | Dispatch |  | EC 115104605 PM 35211698 UNSE Status as of 11/4/20, Priority F
4 | Item 19 | IF Item 26 | {0B461792-6532-4DDA-97BA-5C1D2D76D5FB} | 1 | North Valley | Tier 2 | 103441102 | JESSUP 1102 |  | 0.091225 | Y | N |  | De-energize idle line downstream of SAP Pole id 101481900. Idle line SAP Pole Ids 101481899, 101481898, 101481897 Idle Transformer CGC# - 118883039870 | The line is de-energized. The primary jumpers are open at SAP 101481900 de-energized to EOL. | Dispatch |  | EC 103690736
4 | Item 20 | IF Item 27 | {0F071E73-9573-4E7E-B2F1-99A97D9A1D9B} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.060437 | Y | N |  | Idle line SAP Pole Ids 101476890, 101476892 Idle Transformer CGC# - 120333247918 | The jumpers are open at pole SAP 101476889. 11/25/15 IF investigation - mapped as TOS-F - TX CGC# 120333247918; SAP Pole Ids 101476890 & 101476892. | Dispatch |  | EC 102537346
4 | Item 21 | IF Item 28 | {BFF6E942-70A4-428C-AE23-923E91045611} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.040196 | Y | N |  | De-energize idle line downstream of SAP Pole id 101456829. Idle line SAP Pole id 101456831 | Jumpers are opened at pole sap 101456829 and the line is de-energized. | Dispatch |  | EC 117686717
4 | Item 22 | IF Item 29 | {B24FCC37-3A01-4A67-826C-629F863DA5CF} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.041775 | Y | N |  | De-energize idle line downstream of SAP Pole id 101477601. Idle line SAP Pole id 101477605 | The line de-energized. There are flying bells cut in the line on the south side of pole SAP 101477601 and the jumpers are open de-energized to EOL. | Dispatch |  | No recent EC tag found
4 | Item 23a | IF Item 3 | {AB25D357-6F3A-4E2E-9BB9-D746B4D88732} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.091756 | Y | N |  | Idle line SAP Pole ids 102264187, 102264188 | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117229008 for Idle Pole decay
4 | Item 23b | IF Item 4 | {C7886B68-B543-4539-B820-65ADAC983066} {5D1840F7-F006-4876-A874-5B1A47F72DFC} {916A8C59-6A21-4B56-AC46-8058ED1E9464} {CD616D50-AE5C-4891-86C2-7ACC23C3A412} {DF2C9EAE-26F0-4C85-B937-505E4C9F7E11} {E8E5EFF6-D150-41D8-9E24-567B7B5F159C} {F49D2031-F91D-41D9-BF8B-125E76A1D0FA} {33AFA394-E183-4DEA-AB24-0DE592C87158} {F559D60B-172B-4518-A0D6-E78C6A3C2938} {98CE8E62-F3DC-490D-9CF6-4FE7423DAD37} {CC2FC4FA-6670-4D00-8D9F-F1D237632C07} | 11 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.77059 | Y | N |  | Idle line SAP Pole ids 102264184, 102264185, 102264186, 102264187, 102264188 102264198, 102264243, 102264189, 102264190, 102264192, 102264199, 102264200, 102264201, 102264202, 102264191, 102264193, 102264194, 102264195 102264204, 102264205, 102264208, 102264196, 102264197, 102264235, 102264240, 102264241, 102264244, 102264245, 102264246, 102264246 Idle Transformers: Transformer CGC# - 219262833684 Transformer CGC# - 219259833715 Transformer CGC# - 219248033734 Transformer CGC# - 219252533703 Transformer CGC# - 219251133757 Transformer CGC# - 219256033755 Transformer CGC# - 219246933781 Transformer CGC# - 219248533796 Transformer CGC# - 219252233738 Transformer CGC# - 219247133806 Transformer CGC# - 219241633879 May be associated with Berryessa Marina Resort Fire | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117229314 for one of the idle poles
4 | Item 23c | IF Item ID 18 | {AD4C8A53-0A10-4852-8820-04D602A82D61} {4771FF04-7FDA-43F4-99B1-B935934192D2} | 2 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.16418 | Y | N |  | Idle line SAP ids 102264235, 102264240 | Line was found already de-energized 11/5/20. | Dispatch |  | No recent EC tag found
4 | Item 24 | IF Item 30 | {1D3B2B78-5B6A-4888-ACD3-E557CC2C88D9} {44A1B8D9-AA8B-4F05-9A68-217A62A434C8} | 2 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 | Fuse 7647 | 0.3018 | Y | Y | Round Mtn-Table Mtn #2 (500kV) | Idle line SAP Pole ids 101475546, 101475551, 101475560, 101475548, 103368433, 101475555, 101475556, 101475558, 101475561 Idle Transformer CGC# - 120173449402 SAP id associated with Fuse 101475546 SAP Pole id 101475548 associated with TX on next pole beyond Fuse | The line is de-energized. Cutouts 7647 are open and the line is de-energized to the EOL. Last contact with customer in 2016 when she requested to keep line and would be submitting application. No activity since. | Dispatch |  | EC 110850619 PM 31225848 was cancelled
3 | Item 25 | IF Item 31 | {B6B7C1C7-E771-4378-B886-41EFA1B2C45B} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.21042 | Y | N |  | Per Safety Assessment on 5/18/20 conductor has been removed. | Per Safety Assessment on 5/18/20 conductor has been removed. | Compliance |  | EC 110850621 PM 35204814 UNSE Status, Priority F
3 | Item 26 | IF Item 32 | {60B4A640-4AC1-4CAB-BAF1-1B0DEA0C8422} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.145 | Y | N |  | De-energize idle line downstream of SAP Pole id 103322317. Idle line SAP Pole ids 101480717, 101480718 Idle Transformer CGC# - 120184745650 | The line is de-energized from open jumpers at pole SAP 103322317. PM 35174308 in ESTS status, Priority E (Schd Compl Yr 0) as of 7/15/20. | Dispatch |  | EC 118946100 PM 35174308 ESTS Status, Priority E
4 | Item 27 | IF Item 33 | {326EA39F-C7EB-43EE-B28F-CE3162FE7DFF} | 1 | North Valley | Tier 3 | 103601101 | WHITMORE 1101 |  | 0.068764 | Y | N |  | De-energize idle line downstream of SAP Pole id 101475484. Idle line SAP Pole Ids 101475485, 101475486, 101475487 | The line is de-energized. The primary jumpers are opened at SAP 101475484 and the primary wire is removed/de-energized. | Dispatch |  | EC 119038871
4 | Item 28 | IF Item 34 | {3C6734CA-F14D-45C3-98BE-B40DF241CCD5} {150808D2-E042-4316-A50B-00BD5BA0B46F} | 2 | Los Padres | Tier 2 | 182611103 | PASO ROBLES 1103 |  | 0.75402 | Y | N |  | Heritage Ranch (Nacimiento Lake Dr - Parkway Circle) - [REDACTED] site visited 8/27/20 and verified. | Fuses Open - Cut and Clear. Field verified by [REDACTED] on 8/27/20. | SNBR Field Visit |  | EC 117193084 for De-energization
3 | Item 29 | IF Item 35 | {0F97BC63-445F-4B1D-A15B-DBD0C5DB1286} {1A828214-D994-4DAC-B956-6EB58A86576B} {02552A21-398F-4F72-A924-A9CCDD09B21A} {70BF414A-A697-49AA-A93C-5605A08B1E6C} {5D36EC8D-3E05-4275-AE0E-20A535DECFEA} | 5 | Yosemite | Tier 2 | 252192105 | BEAR VALLEY 2105 | Switch 4628 | 1.3627 | Y | N |  | Open SW 4628 to de-energize idle facilities. Buck Meadows (Bear Valley) | 4628 Is de-energized from Flying Bells located at Sap Id 103089929. OH Idle Facility Removal, Priority F, ESTS status, PM 35145458. | Email Dispatch |  | PM 35145458 ESTS Status, Priority F
4 | Item 30 | IF Item 5 | {E0D40BBB-77DC-4A82-ADE6-C4FF67FF00C4} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.61669 | Y | N |  | De-energize idle line downstream of SAP Pole id 102290530. Idle line SAP Pole ids 102290529, 102290528, 102290527 Idle Transformer CGC# - 219436824952 | Line was found already de-energized 11/5/20 by NB crew. | Dispatch |  | EC 107535759 PM 31137450 but cancelled in 2018
1 | Item 31 | IF Item 6 | {3866CF69-A5DE-4217-9413-AC604070AF44} | 1 | North Bay | Tier 2 | 043051101 | MONTICELLO 1101 |  | 0.14237 | Y | N |  | IF line burnt down - LNU Fire - IF has been removed. | Update 8/25/20: 18:06:39 [REDACTED] EC 116954434 Cancelled due to emergency A Tag created during LNU Fire Major Event. Changed A Tag from pole replacement to pole removal per guidance from [REDACTED]. Addtl Notification 119668805 / PM 31511571. GUID no longer in webviewer (IF removed) - LNU Fire area. | Already removed from GIS | Line burnt | EC 119668805
4 | Item 32 | IF Item 7 | {026CAA13-AB1D-42BE-B935-A3C206B0B2FC} | 1 | Humboldt | Tier 2 | 043141103 | MIDDLETOWN 1103 |  | 0.43374 | Y | N |  | De-energize idle line downstream of SAP Pole id 102204918. Idle line SAP Pole ids 102204927, 102204926, 102204925, 102204924, 102204923, 102204922, 102204921, 102204920, 102204919 Idle Transformer CGC# - 218513540110 | Flying Bells Installed. SAP notes updated 5/27/20 - Per IF desk, same owner who agreed to removal in 2015. IF 119041548 to I/R idle tap line. | Dispatch |  | EC 110554917; Per 5/27/20 SAP notes same owner who agreed to removal in 2015 still agrees with removal.
3 | Item 33 | IF Item 8 | {33514C1A-31A9-4D98-9615-A85688A35159} | 1 | Humboldt | Tier 2 | 043361103 | HIGHLANDS 1103 |  | 0.083584 | Y | N |  | De-energize idle line downstream of SAP Pole id 103605301. Idle tap line ends near TX Padmount T0755; used to supply temp power to UG; Idle line SAP Pole ids 103830981, 103830982 | Jumpers cut and clear. EC 112885271 - OH Idle Facility Removal, Priority F, ESTS status, PM 35150545 (2/27/20); Remove Idle tap line and poles supplied temp power to underground. | Dispatch |  | PM 35150545 ESTS status, Priority F
4 | Item 34 | IF Item 9 | {7424AE9E-B065-4FFC-846C-44CDCD8E9176} {88CDE43A-6151-446E-84F2-2FAD7377612B} {377053A1-0CEC-49D1-A2C4-BA2DE4732A46} | 3 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 |  | 3.5012 | Y | N |  | Big Meadows - Confirmation from [REDACTED] that line has de-energized. Provided circuit map. The 3-2 C 21kV circuit (idle) runs in parallel to 3-2AR 21kV circuit. | Per [REDACTED] in Compliance map was sent to us that shows this has been de-energized for over 10 years - provided circuit map. The 3-2 C 21kV circuit (idle) runs in parallel to 3-2AR 21kV circuit. | SNBR/Compliance |  | No recent EC tag found
4 | Item 35 | IF Item ID 1 | {9DAE7BF2-7E01-49F9-99A6-BC6DED2282B3} | 1 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 |  | 0.048292 | Y | N |  | Idle line SAP Pole Id 101074029 Idle Transformer CGC# - 321595938343 | Per [REDACTED] (Compliance) 10/6/20 - Jumpers cut in the clear at sap ID 101074038, which de-energizes tx on sap id 101074029. | Compliance |  | S9 119515842
3 | Item 36 | IF Item ID 10 | {3C541C61-0F12-41AE-9DA1-5F0111126A6C} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.16172 | Y | Y | Round Mtn-Table Mtn #2 (500kV) | De-energize idle line downstream of SAP Pole id 101479924. Idle line SAP Pole ids 101480009, 101480008, 103169204, 101479927 Idle Transformer CGC# - 120197653617 SAP Pole id 101480008 with TX at EOL. | The line is de-energized from jumpers open at flying bells at sap pole 101479924. | Dispatch |  | EC 117218967 PM 35207924, UNSE Status, Priority F EC 117218934 PM 35207923, UNSE Status, Priority E
4 | Item 37 | IF Item ID 11 | {22E39901-42E5-4DD4-84BC-31F5336FA4E4} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.063231 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480247. Idle line SAP Pole ids 101480263, 101480248 Idle Transformer CGC# - 120216453547 | The primary jumpers are open at Pole SAP 101480247 to EOL de-energized. | Dispatch |  | EC 117166992
1 | Item 38 | IF Item ID 12 | {80FE9D6A-3816-450D-A642-A4D00E895C35} | 1 | North Valley | Tier 3 | 102911105 | BIG BEND 1102 |  | 0.20374 | Y | N |  | De-energize idle line downstream of SAP Pole id 100412447. Idle line SAP Pole ids 100416739, 100412449, 100370365, 100412448, 100370364, 100370362 Idle Transformer CGC# - 221902774153 | Per M&C Supervisor this line has burnt down - email from [REDACTED] (NV). | Dispatch | Line burnt | Line burnt
1 | Item 39 | IF Item ID 13 | {935F9C88-99E9-43DF-B4D9-4113BFA72D88} | 1 | North Valley | Tier 3 | 102911103 | WYANDOTTE 1103 |  | 0.18668 | Y | N |  | De-energize idle line downstream of SAP Pole id 100376122. Idle line SAP Pole ids 100427950, 100376124, 100376123, 100427949 Idle Transformer CGC# - 221620370823 | Per M&C Supervisor this line has burnt down - email from [REDACTED] (NV). | Dispatch | Line burnt | Line burnt
4 | Item 40 | IF Item ID 14 | {9177CDDD-AF4F-4743-80DE-3BC72A213013} | 1 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 | Switch 69395 | 0.0054208 | Y | N |  | Open Switch 69395 to de-energize idle line. Idle line SAP Pole ids 103121316, 103121317 Idle Transformer CGC# - 122349932061 SAP id associated with Switch 69395 42645419 | Switch open and de-energized. | Dispatch |  | No recent EC tag found
4 | Item 41 | IF Item ID 15 | {5122961F-9649-43B0-A627-398DFBD83A84} | 1 | North Valley | Tier 2 | 102541101 | VOLTA 1101 |  | 0.26396 | Y | N |  | De-energize idle line downstream of SAP Pole id 101553210. Idle line SAP Pole ids 101553217, 101553216, 101553215, 101553214, 101553213, 101553212 | This tap line has open jumpers de-energized from the take off pole. | Dispatch |  | No recent EC tag found
3 | Item 42 | IF Item ID 16 | {D1F8EB39-F2AC-40AF-A5A3-B94EB780FD89} {5190FE93-D41F-46C9-86DF-94E2F3CCF972} | 2 | Humboldt | Tier 2 | 043361103 | HIGHLANDS 1103 | Fuse 5991 | 0.49348 | Y | Y | Lower Lake Homes Take (115kV) | Idle line SAP Pole ids 103928800, 102304945, 103928898, 103793587, 102304948, 102304949, 103928895, 102304951, 103793588, 102304953, 102304954, and 102304955 Idle Transformers CGC# - 218671044202, 218676044369 SAP Pole id 102304948 with TX middle of idle line | Line has been de-energized and grounded 10/14/2020. | Dispatch |  | EC 117748668, 117748783, 117748780, 117748785, 117748669, 117748784, 117748666 PM 35037391
4 | Item 43 | IF Item ID 17 | {98752110-4824-4447-8148-00F4014209BB} | 1 | Humboldt | Tier 3 | 043191101 | REDBUD 1101 |  | 0.04269 | Y | N |  | De-energize idle line downstream of SAP Pole id 102308426. Idle line SAP Pole id 103922760 Open point with subtype of flying bell on idle segment Downstream from Active Transformer CGC# - 218270551810 | Line was found already de-energized 11/5/20. | Dispatch |  | EC 117255005
4 | Item 44 | IF Item ID 2 | {8D30ACCF-AD51-41A0-A5E3-13CD5F656295} {AB10C1D8-FD1E-498F-AE6C-82A79966AEBE} {42AC2F68-7A1A-43FA-B599-C086D910E907} | 3 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 | Fuse 14542 | 0.1874 | Y | N |  | Idle line SAP Pole Ids 103344115, 103344113, 101072782, 103344112, 103344114 Idle Transformer CGC# - 321679837422 | Per [REDACTED] (Compliance) 10/6/20 - TX and service pole idle, cut outs open. Fuse is open so de-energized. | Compliance |  | No recent EC tag found RW109910970 from 2015
4 | Item 45 | IF Item ID 20 | {3EC927F9-E22E-49D1-888E-E98A921987C9} | 1 | Los Padres | Tier 2 | 182721104 | SANTA YNEZ 1104 |  | 0.11163 | Y | N |  | Per [REDACTED] (Compliance Inspector) - jumper wires were removed - de-energized. Happy Canyon Road.Idle SAP Pole id 103760228Idle Transformer CGC# - 514094242144 | Per [REDACTED] (Compliance Inspector) - jumper wires were removed - de-energized. | SNBR/Compliance |  | No recent EC tag found RW 110885647 from 2015
4 | Item 46 | IF Item ID 21 | {E0CF85A3-864E-408F-9816-07BB365004DA} | 1 | North Valley | Tier 2 | 102812101 | BIG MEADOWS 2101 | Switch 82839 | 0.0084041 | Y | Y | Caribou-Westwood (60kV) | Idle line SAP Pole ids 103771036, 103771037 Idle Transformer CGC# - 122555930668 SAP id associated with Switch 44161565 SAP Pole id 103771037 with TX near Switch | Switch open on arrival. | Dispatch |  | No recent EC tag found
4 | Item 47 | IF Item ID 3 | {CE8FBF0F-74A2-43C9-9C88-8B882C35186F} {68F4C1EE-AC66-4C6B-8B76-99E6A7280CD3} | 2 | Yosemite | Tier 2 | 254452101 | MARIPOSA 2101 | Fuse 2222 | 0.078543 | Y | N |  | Idle line SAP Pole Ids 101086508, 101086507 Idle Transformers CGC# - 321511036205, 321509036197 | Per [REDACTED] (Compliance) 10/6/20 - Fuse 2222 Open, line is idle. | Compliance |  | No recent EC tag found
4 | Item 48 | IF Item ID 4 | {CDCC7E6E-9631-44BD-815A-0B52E1A38964} | 1 | Yosemite | Tier 2 | 252192105 |  |  | 0.41252 | Y | N |  | Idle line SAP Pole Ids 101073810, 101073809, 101073808, 101073807, 101073806, 101073804, 101073803 Open point on idle line | Per [REDACTED] in Compliance, line confirmed de-energized on 11/4/2020. | SNBR/Compliance |  | No recent EC tag not found
3 | Item 49 | IF Item ID 6 | {12227378-9860-4FBF-9AC1-C57B6B5F5C2E} | 1 | North Valley | Tier 2 | 103601101 | WHITMORE 1101 |  | 0.093922 | Y | N |  | De-energize idle line downstream of SAP Pole id 101480797. Idle line SAP Pole ids 101480809, 101480798 | The line is de-energized from open jumpers at pole SAP 101480797. | Dispatch |  | EC 117102934 PM 35217667, UNSE Status, Priority F
4 | Item 50 | IF Item ID 7 | {5E8A014C-2508-4ED6-AB12-D2D5877FD6FD} | 1 | North Valley | Tier 2 | 103351101 | DESCHUTES 1101 | Fuse 11655 | 0.259 | Y | Y | Volta-Deschutes (60kV) | Idle line SAP Pole ids 103141283, 103141284, 103141285, 103141286, 103141287, 103141288 SAP id associated with Fuse 101483642 No TX on idle line | Cutouts 11655 found open upon arrival. Line is de-energized. | Dispatch |  | No recent EC tag found
4 | Item 51 | IF Item ID 8 | {56D5FC07-2D29-4BAE-AD9F-816045A7CE24} | 1 | North Valley | Tier 3 | 103351101 | DESCHUTES 1101 |  | 0.19099 | Y | N |  | De-energize idle line downstream of SAP Pole id 101479479. Idle line SAP Pole ids 101479480, 101479487, 101479482, 101479483, 101479486, 101479484, 101479485 | The primary jumpers are open at SAP 101479479 to EOL de-energized. Customer contact in 2016 suggested customer might have future use but no activity since. | Dispatch |  | EC 117311260
4 | Item 52 | IF Item ID 9 | {907B565F-2E2C-47F3-8BC4-8A9776D431A0} | 1 | North Valley | Tier 2 | 103321101 | CEDAR CREEK 1101 |  | 0.14634 | Y | N |  | De-energize idle line downstream of SAP Pole id 101519745. Idle line SAP Pole ids 101519746, 101519785, 101519784 Idle Transformer CGC# - 120261155249 | The primary jumpers are open at pole SAP 101519745 to EOL de-energized. Customer contact in 2015 suggested customer might have future use but no activity since. | Dispatch |  | EC 117214527
4 | Item 53 | Ph 3 QR Add 1 | {A16A506F-D4B6-4829-B0DE-6948576564DB} | 1 | North Bay | Tier 3 | 043292102 | PUEBLO 2102 |  | 0.045894 | Y | N |  | Idle line SAP Pole ids 103917226, 102269282 Near Transformer CGC# - 218817526480 | Line was found already de-energized 11/5/20 by NB dispatch. | Dispatch |  | EC 116873740
3 | Item 54 | Ph 3 QR Add 3 | {EE04AEAE-B8E5-4F1E-9ABA-71E9D60EB159} | 1 | Peninsula | Tier 2 | 024131102 | MENLO 1102 |  | 0.07226 | Y | N |  | Idle line SAP Pole ids 100271867, 100271868PM 35155226 for I/R in ESTS status as of 3/2/20; in ADE review 4/27/20; Job Owner [REDACTED] | Per SAP 6/13/19 notes from WSIP Inspection, already de-energized and flagged as idle in GIS. Set for removal - PM 35155226, ESTS status. | SNBR/Compliance |  | PM 35155226 PEND status, Priority E
|  |  | Total Idle Segments | 83 |  |  |  |  | Total Miles | 13.9894
2020-12-11
Disposition Category |  |  | De-energization Project Breakout: | # of Segments | Miles (Length)
1 |  |  | Line Burnt (Fire area) | 3 | 0.53279
2 |  |  | Appears removal have been completed | 2 | 0.22909
3 |  |  | PMs created pre-2021 | 9 | 1.6865
4 |  |  | Idle Removal for Planning | 69 | 11.541
|  |  | Total | 83 | 13.9894
Updated 12/14/2020
Disposition Category |  |  | De-energization Project Breakout: | # of Segments | Miles (Length)
1 |  |  | Line Burnt (Fire area) | 3 | 0.53279
2 |  |  | Appears removal have been completed | 2 | 0.22909
3 |  |  | PMs created pre-2021 | 27 | 4.0005
4 |  |  | Idle Removal for Planning | 51 | 9.227
|  |  | Total | 83 | 13.9894
Note on B2: [REDACTED] Item # (New) for [REDACTED]
Note on C2: [REDACTED] Item # per Source extract tab
Note on M8: [REDACTED] At the closest point from idle segment to Round Mtn-Cottonwood #2 is ~ 900 ft.
Note on M39: [REDACTED] ~900 ft from Briceburg Jct-Marioposa Tap (70kV)
Note on M55: [REDACTED] ~1300 ft from Round Mtn-Cottonwood #2 (230kV)

## Weekly Summary
Status Summary as of 12/21/20 |  |  |  | Process Summary
Order Status | # of jobs | Miles | Notes | Document | # of jobs | % of jobs | Miles | Notes |  | Responsible Group/Party | Total Expected Days | Total Actual Days | Date Start | Date End
UNSE | 64 | 363.28 |  | AA routed & appr | 62 | 62.63% | 178.86 |  | Planning Order Request Date | Grid Design | 5 business days
ESTS/ADER/APPR | 4 | 4.38 |  | Field Scoping | 24 | 24.24% | 36.19 |  | PM Number Requested Date | Grid Design | 1 business day
PEND | 4 | 6.38 |  | CMCS | 31 | 31.31% | 50.96 |  | Create Job Package | Planning DE | # of days/mile
UNSC | 1 | 1.47 |  | Business Case | 27 | 27.27% | 43.71 |  | AA Routed | Planning DE | Date job packaged created
[9 empty] | AA Approved | Various | 1 week
CONS | 26 | 40.66 | [6 empty] | Field Scoping (scheduling) | Various | 2 weeks
TOTAL | 99 | 416.17 | [6 empty] | Adjustments to Scope/back to planning | Planning DE/Estimating | 1-2 weeks
[9 empty] | ESTS will submit CMCS to planning for approval | Estimating | # of days/mile
[9 empty] | Scheduling | Project Manager | ?????
[9 empty] | Construction (25%, 50%, 75%) | Construction Team | # of weeks/mile