## Sheet1
Change ID | Change Request Type | Order | Notification | Order Description | Change Request Status | MAT | Sub-Category | Updated Sub-Category | Civil Resource | Electric Resource | New Civil Resource | New Electric Resource | Business Justification | User Status | Job Owner | Job Owner Name | Strike Force Population | Exclusions | Updated Strike Force Population | Updated Exclusions | Past Due Reason | Estimating Review | Estimating Comments | Construction Review | Construction Comments | Program Manager | Program Manager Review | Program Manager Comments | Warning Message | Portfolio Manager Review | Portfolio Manager Comments | Last Changed On | Last Changed Name | Created On | Creator Name
60006 | Add project | 35043296 | 112191208 | WDDB - WILLOW CRK 1103 LR 3090 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSC | [19 empty] | 2021-03-19 13:51
60013 | Add project | 35094396 | 117130859 | CWSP-KONOCTI 1102-LR 532 PH 9 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSC | [19 empty] | 2021-03-19 13:52
53043 | Defer project | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:24 |  | 2021-03-12 11:43
60010 | Add project | 35094389 | 117130852 | CWSP-KONOCTI 1102-LR 532 PH 2 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | ESTS | [19 empty] | 2021-03-19 13:52
52900 | Defer project | 35226700 | 14272795 | CWSP - WYANDOTTE 110932586 PH 1.2 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:24 |  | 2021-03-11 09:15
60009 | Add project | 35050951 | 114848376 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:52
53042 | Defer project | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:24 |  | 2021-03-12 11:46
60014 | Add project | 74022385 | 114691436 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | APPR | [19 empty] | 2021-03-19 13:52
60012 | Add project | 35094395 | 117130858 | CWSP-KONOCTI 1102-LR 532 PH 8 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | ESTS | [19 empty] | 2021-03-19 13:52
59916 | Defer project | 35174478 | 118913024 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:28 |  | 2021-03-18 21:18
59944 | Defer project | 35062375 | 115323921 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Program Manager Review | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 09:46 |  | 2021-03-19 07:54
60011 | Add project | 35094391 | 117130854 | CWSP-KONOCTI 1102-LR 532 PH 4 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSC | [19 empty] | 2021-03-19 13:52
59917 | Defer project | 35174479 | 118913025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:15 |  | 2021-03-18 21:20
53037 | Defer project | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:16 |  | 2021-03-12 12:06
53046 | Defer project | 35219093 | 120141622 | CWSP - TIDEWATER 210614072 PH 1.1 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:14 |  | 2021-03-12 12:01
52431 | Defer project | 35223039 | 120242691 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [5 empty] | Approve so long as all info is provided | 2021-03-25 10:15 |  | 2021-03-09 15:59
59945 | Defer project | 35192292 | 119556108 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Program Manager Review | 08W | [6 empty] | Defer to 2022, 08W ECOP 100% UG project dependencies will not be completed until 2022. | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:16 |  | 2021-03-19 07:54
53040 | Defer project | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-12 11:54
59938 | Defer project | 35226857 | 120449200 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:15 |  | 2021-03-18 21:22
59930 | Defer project | 35227004 | 120449457 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:15 |  | 2021-03-18 21:38
59915 | Defer project | 35174501 | 118913026 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:14 |  | 2021-03-18 21:21
59946 | Defer project | 35226849 | 120449142 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Program Manager Review | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-19 07:54
52591 | Defer project | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-10 14:56
53047 | Defer project | 35219096 | 120141671 | CWSP - KIRKER 2104442850 PH 1.1 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-12 12:02
59576 | Defer project | 35223030 | 120242544 | PSPS - BANGOR 1101 CB - MICROGRID | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per project Manager, This will be a 2022 project due to the underground scope | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-17 10:21
59934 | Defer project | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 09:54 |  | 2021-03-18 21:31
59923 | Defer project | 35227015 | 120449710 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 09:54 |  | 2021-03-18 21:42
59947 | Defer project | 35225594 | 120424183 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | Program Manager Review | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-19 07:54
52586 | Defer project | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-10 14:18
53044 | Defer project | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-12 11:52
53039 | Defer project | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-12 12:09
53038 | Defer project | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-12 12:15
59926 | Defer project | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:30
52584 | Defer project | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-10 14:05
52588 | Defer project | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-10 14:31
52589 | Defer project | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-10 14:31
59922 | Defer project | 35226861 | 120449203 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:26
59942 | Defer project | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:28
59929 | Defer project | 35227001 | 120449454 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:35
59928 | Defer project | 35227003 | 120449456 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:37
53041 | Defer project | 35232650 | 120529254 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:16 |  | 2021-03-12 11:56
59935 | Defer project | 35227021 | 120449712 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:44
59941 | Defer project | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-18 21:29
59924 | Defer project | 35226873 | 120449450 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-18 21:33
59940 | Defer project | 35227018 | 120449711 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:13 |  | 2021-03-18 21:43
59933 | Defer project | 35226858 | 120449201 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:16 |  | 2021-03-18 21:24
59925 | Defer project | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:06 |  | 2021-03-18 21:30
59932 | Defer project | 35227007 | 120449533 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:06 |  | 2021-03-18 21:39
60004 | Add project | 35234862 | 120580959 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:51
52592 | Defer project | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Program Manager Review | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-10 15:03
59918 | Defer project | 35226859 | 120449202 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:25
59927 | Defer project | 35226862 | 120449204 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | ESTS | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:27
59936 | Defer project | 35226878 | 120449453 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:34
59931 | Defer project | 35227002 | 120449455 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:36
59919 | Defer project | 35227010 | 120449536 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:40
59920 | Defer project | 35227013 | 120449539 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:07 |  | 2021-03-18 21:41
60005 | Add project | 35234865 | 120581001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:51
60003 | Add project | 35234758 | 120580957 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:51
53045 | Defer project | 35231543 | 120504099 | CWSP - TIDEWATER 210614072 PH 1.2 | Program Manager Review | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 10:16 |  | 2021-03-12 12:04
59913 | Add project | 35220896 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Program Manager Review | 08W | [6 empty] | New project | UNSE | [19 empty] | 2021-03-18 17:37
60015 | Add project | 35223062 |  | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:46
60016 | Add project | 35223032 |  | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:46
60017 | Add project | 35219276 |  | CWSP - VACAVILLE 11046542 PH 1.1 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:46
60018 | Add project | 35227651 |  | CWSP - VACAVILLE 11046542 PH 1.2 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60019 | Add project | 35227652 |  | CWSP - VACAVILLE 11046542 PH 1.3 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60020 | Add project | 35227653 |  | CWSP - VACAVILLE 11046542 PH 1.4 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60021 | Add project | 35227654 |  | CWSP - VACAVILLE 11046542 PH 1.5 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60022 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60023 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60024 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60025 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60026 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60027 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60028 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60029 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60030 | Add project | 35225827 |  | CWSP - OREGON TRAIL 110335002 PH3.1 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60031 | Add project | 35233954 |  | CWSP - OREGON TRAIL 110335002 PH3.2 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60032 | Add project | 35233956 |  | CWSP - OREGON TRAIL 110335002 PH3.3 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60033 | Add project | 35233958 |  | CWSP - OREGON TRAIL 110335002 PH3.4 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60034 | Add project | 35234380 |  | CWSP - OREGON TRAIL 110335002 PH3.5 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60035 | Add project | 35234383 |  | CWSP - OREGON TRAIL 110335002 PH3.6 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60036 | Add project | 35234384 |  | CWSP - OREGON TRAIL 110335002 PH3.7 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60037 | Add project | 35234385 |  | CWSP - OREGON TRAIL 110335002 PH3.8 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60038 | Add project | 35234386 |  | CWSP - OREGON TRAIL 110335002 PH3.9 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60039 | Add project | 35236437 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60040 | Add project | 35236438 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60041 | Add project | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60042 | Add project | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60043 | Add project | 35236661 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60044 | Add project | 35219543 |  | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Program Manager Review | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | UNSE | [19 empty] | 2021-03-19 14:44
60395 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60396 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60397 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60398 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60399 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60400 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60401 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60402 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Program Manager Review | 08W | [6 empty] | Adding this project as part of SH program | UNSE | [19 empty] | 2021-03-23 10:47
60489 | Add project | 35116385 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Program Manager Review | 08W | [6 empty] | Adding project to 2022 per PM & PM Supervisor | PEND | [19 empty] | 2021-03-24 14:22
60490 | Add project | 35116440 |  | CWSP-MIWUK 1702-LR8090-PH 1.6 | Program Manager Review | 08W | [6 empty] | Adding project to 2022 per PM & PM Supervisor | ESTS | [19 empty] | 2021-03-24 14:26
60778 | Add project | 35235139 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Program Manager Review | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | UNSE | [19 empty] | 2021-03-25 08:47
60779 | Add project | 35235676 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Program Manager Review | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | UNSE | [19 empty] | 2021-03-25 08:47
60007 | Add project | 35046211 | 114730956 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:52
60008 | Add project | 35050942 | 114848297 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:52
59939 | Defer project | 35227025 | 120449714 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Program Manager Review | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | UNSE | [7 empty] | Approved |  | Approved | Defer project approved | [6 empty] | 2021-03-25 09:46 |  | 2021-03-18 21:45
60002 | Add project | 35234756 | 120580906 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Program Manager Review | 08W | [6 empty] | Fire hardening job needs to be added to work plan | UNSE | [19 empty] | 2021-03-19 13:51