## Sheet1
Order | Parent order | Priority | Link to Materials | Project Manager | Project Reporting Year | Project Name | Caltrans Dist. | Caltrans DSDD? | UG Ft. | OH Ft. | Division | ADE or Estimator | Land Surveyor | Survey Vendor | Basmap Status | ETA Prelim. Basemap COMP | Actual Deliv. Prelim. Basemap | Pothole Needed? | ETA Final Basemap COMP | Land Comments
35094513 |  | 1 | missing |  | 2021 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10 | Yes | 428 | 9423 | ST |  |  |  | COMP |  |  |  |  | Completed and part of the DSDD Pilot Program
35219268 |  | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 1 | 10 | TBD | 0 | 8553.6 | YO |  |  |  | COMP | 2021-03-12 | 2021-03-12 |  |  | Basemap delivered to team 3/12/21
35226241 | 35219268 | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 2 | 10 | TBD | 0 | 7920 | YO |  |  |  | COMP | 2021-03-12 | 2021-03-12 |  |  | Basemap delivered to team 3/12/21
35219266 |  | 1 | 35219266 |  | 2021 | CWSP - MARIPOSA 2102CB PH 1 | 10 | TBD | 0 | 13713 | YO |  |  |  | INPR | 2021-04-09 |  |  |  | [Redacted] to send crew for minimum CT requirements
35192292 |  | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 4 | No | 4224 | 0 | SO |  |  |  | COMP | 2021-03-19 | 2021-03-19 |  |  | Basemap delivered to team 3/19/21
35225594 | 35192292 | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 4 | No | 2481.6 | 0 | SO |  |  |  | COMP | 2021-03-19 | 2021-03-19 |  |  | Basemap delivered to team 3/19/21
35223024 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 4 | No | 11827.2 | 0 | NB |  |  |  | INPR | 2021-04-09 |  |  |  | Field crew got very bad poison oak; delayed a week
35192284 |  | 1 | 35192284 |  | 2021 | ECOP - SILVERADO 2104 - H05-LR726 | 4 | No | 10929.6 | 0 | NB |  |  |  | INPR | 2021-04-09 |  |  |  | Field crew got very bad poison oak; delayed a week
35223026 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 4 | No | 9504 | 0 | NB |  |  |  | INPR | 2021-04-09 |  |  |  | Field crew got very bad poison oak; delayed a week
35217273 |  | 1 | 35217273 |  | 2021 | SH - UPPER LAKE 1101 CB | 1 | Yes | 0 | 5702.4 | HB |  |  |  | COMP | 2021-03-15 | 2021-03-16 |  |  | Basemap delivered to team 3/16/21
35217270 |  | 1 | 35217270 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 | 1 | Yes | 0 | 2904 | HB |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35225589 |  | 1 |  |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH2 | 1 | Yes | 0 | 4699 |  |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35225591 |  | 1 |  |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH3 | 1 | Yes | 0 | 4224 |  |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35145540 |  | 1 | missing |  | 2021 | PSPS - FROGTOWN 1702 - CB | 10 | Yes | 2846 | 3872 | ST |  |  |  | COMP | 2021-03-15 | 2021-03-15 |  |  | Corrections from Estimating and BCF needed
35217275 |  | 1 | 35217275 |  | 2021 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 4 | No | 0 | 15312 | PN |  |  |  | INPR | 2021-05-15 |  |  |  | This is a part of Fire Rebuild, not SH
35217274 |  | 1 | 35217274 |  | 2021 | FRRB - PN DIVISION SAN MATEO COUNTY | 4 | No | 0 | 11774.4 | PN |  |  |  | INPR | 2021-05-15 |  |  |  | This is a part of Fire Rebuild, not SH
35223615 | 35191319 | 1 | 35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 PH 2 | 4 | No | 8606.4 | 0 | NB |  |  |  | INPR | 2021-05-07 |  |  |  | Waiting for [Redacted] to approve SOW and cost
35062376 |  | 1 | 35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 3 | No | 13358.4 | 0 | SI |  |  |  | INPR | 2021-04-19
35062374 |  | 1 | 35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 3 | No | 8236.8 | 0 | SI |  |  |  | COMP | 2021-04-05 | 2021-04-06 |  |  | Basemap delivered to team 4/6/21
35231608 |  | 1 |  |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 3 | No | 1742 | 0 |  |  |  |  | NA | NA |  |  |  | No UG; basemap no longer needed
35062375 |  | 1 | 35062375 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 3 | No | 5860 | 0 | SI |  |  |  | INPR | 2021-04-12
35192291 |  | 1 | 35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 3 | No | 2534.4 | 0 | SI |  |  |  | INPR | 2021-04-19 |  |  |  | ETA changed to 4/19 - county permit for lane closure 2-3 weeks out
35217268 |  | 1 |  |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 1 | 2 | Yes | 0 | 1056 |  |  |  |  | NA | NA |  |  |  | No UG; phases 2 & 3 will capture all mapping needs
35224712 |  | 1 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 | 2 | Yes | 9134 | 0 | NV |  |  |  | INPR | 2021-05-07 |  |  |  | Coordinate mobile lidar w Caltrans
35224713 |  | 1 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 | 2 | Yes | 9662.4 | 0 | NV |  |  |  | INPR | 2021-05-07 |  |  |  | Coordinate mobile lidar w Caltrans
35226849 |  | 1 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 3 | No | 9398 | 0 | SI |  |  |  | INPR | 2021-04-12
35226853 |  | 1 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 3 | No | 264 | 15153.6 | SI |  |  |  | NA | NA |  |  |  | No UG; basemap no longer needed
35192280 |  | 1 | 35192280 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 | 4 | No | 7075.2 | 0 | DI |  |  |  | COMP | 2021-04-11 | 2021-04-02 |  |  | Basemap delivered to team 4/2/21
35217272 |  | 1 | 35217272 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 2 | No | 1584 | 0 | NV |  |  |  | INPR | 2021-05-01
35226628 | 35217272 | 1 | 35217272 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 2 | No | 4330 | 0 | NV |  |  |  | INPR | 2021-05-01
35226629 | 35217272 | 1 | 35217272 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 2 | No | 23760 | 0 | NV |  |  |  | INPR | 2021-05-01
35226700 |  | 1 | missing |  | 2021 | CWSP - WYANDOTTE 110932586 PH 1.2 | 3 | No | 3010 | 0 | NV |  |  |  | INPR | 2021-04-16 |  |  |  | Need Land Rights clarification from [Redacted]
35217269 |  | 1 | 35217269 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 1 | Yes | 0 | 2270 | HB |  |  |  | RFP | 2021-05-05 |  |  |  | 3/22/2021 Proposal accepted
35217271 |  | 1 | 35217271 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 1 | No | 8131 | 0 | HB |  |  |  | RFP Revision |  |  |  |  | 4/1/2021 sent proposal to [Redacted] for approveal. 3/30/2021 sent revised scope to [REDACTED].
35220895 |  | 1 | 35220895 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 1 | No | 10190 | 1162 | HB |  |  |  | INPR |  |  |  |  | 3/31/2021 approval received
35227030 |  | 1 | missing |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 1 | Yes | 7287 | 1796 | HB |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35227031 |  | 1 | missing |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 1 | Yes | 8184 | 2546 | HB |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35174478 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 1 | Yes | 5491 | 0 |  |  |  |  | INPR | 2021-06-12
35174501 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 1 | Yes | 21597 | 0 |  |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35192282 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 1 | Yes | 10771 | 0 |  |  |  |  | INPR | 2021-05-30 |  |  |  | 3/31/2021 approval received
35226873 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 1 | Yes | 5488 | 0 |  |  |  |  | INPR | 2021-05-30
35226878 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 1 | Yes | 3109 | 0 |  |  |  |  | INPR | 2021-05-30
35227001 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 1 | Yes | 3809 | 0 |  |  |  |  | INPR | 2021-05-30
35227002 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 1 | Yes | 2286 | 0 |  |  |  |  | INPR | 2021-05-30
35227003 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 1 | Yes | 3067 | 0 |  |  |  |  | INPR | 2021-05-30
35227004 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 1 | Yes | 1839 | 0 |  |  |  |  | INPR | 2021-05-30
35227007 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 1 | Yes | 15183 | 0 |  |  |  |  | INPR | 2021-05-25
35227025 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 1 | Yes | 2900 | 0 |  |  |  |  | INPR | 2021-05-25
35227160 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 1 | Yes | 8405 | 0 | HB |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35227162 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 1 | Yes | 1711 | 0 | HB |  |  |  | INPR | 2021-06-12 |  |  |  | 3/31/2021 approval received
35227165 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 1 | No | 9662.4 | 0 | HB |  |  |  | INPR | 2021-05-25 |  |  |  | 3/31/2021 approval received
35227167 |  | 1 |  |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 1 | No | 9504 | 0 |  |  |  |  | INPR | 2021-05-25 |  |  |  | 3/31/2021 approval received
35227168 |  | 1 |  |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 1 | No | 8290 | 0 |  |  |  |  | INPR | 2021-05-25 |  |  |  | 3/31/2021 approval received
35227864 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 1 | No | 3272 | 0 | HB |  |  |  | RFP |  |  |  |  | 3/30/2021 sent revised scope to [REDACTED].
35227868 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 1 | No | 2123 | 0 | HB |  |  |  | RFP |  |  |  |  | No docs
35228186 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 1 | No | 7850 | 0 | HB |  |  |  |  | 2021-05-25 |  |  |  | Sent proposal to [Redacted] for approval on 3-25-21
35229119 |  | 1 | missing |  |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 1 | No | 3221 | 0 | HB |  |  |  | COMP | 2021-03-18 | 2021-03-17
35219093 |  | 1 |  |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 | 4 | No | 6019 | 0 |  |  |  |  | Out to Bid | 2021-06-15 |  |  |  | 3/30/2021 COUNTY MAPPING OUT OF DATE NEED TO DO FULL MAPPING IN AREA
35219096 |  | 1 |  |  | 2021 | CWSP - KIRKER 2104442850 PH 1.1 | 4 | No | 8818 | 0 |  |  |  |  | Out to Bid | 2021-06-15 |  |  |  | 3/30/2021 COUNTY MAPPING OUT OF DATE NEED TO DO FULL MAPPING IN AREA 3-25-2021 Proposal sent to [Redacted] Control and 3D Model Needed; ask [Redacted] about county rep who provided Basemap
35226632 |  | 1 |  |  | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 1 | No | 792 | 0 | [9 empty] | Waiting for acquisition to talk with property owner
35226799 |  | 1 |  |  | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 2 | Yes | 1003 | 0 |  |  |  |  | NA | NA |  |  |  | OH harden NO mapping
35232650 |  | 1 |  |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 3 | No | 9028 | 0 |  |  |  |  | INPR | 2021-04-15
35223039 |  | 1 |  |  | 2021 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 3 | No | 4066 | 0 |  |  |  |  | INPR | 2021-04-30 |  |  |  | Coordinate L&M with [REDACTED]
35219281 |  | 1 |  |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 3 | No | 13200 | 0 |  |  |  |  | INPR | 2021-04-15
35231543 |  | 1 |  |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 | 4 | No | 6864 | [5 empty] | Out to Bid | 2021-06-15 |  |  |  | 3-24-2021 Proposal accepted
| 35174478 | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 1 | Yes | 5491 | [5 empty] | INPR | 2021-05-25
| 35174501 | 1 |  |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 1 | Yes | 21597 | [5 empty] | INPR | 2021-05-25
35226857 |  | 1 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 1 | Yes | 4488 | 0 |  |  |  |  | INPR | 2021-05-25
35191319 |  | 2 | 35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 4 | No | 6177.6 | 0 | NB |  |  |  | INPR | 2021-05-07 |  |  |  | Waiting for [Redacted] to approve SOW and cost
35219097 |  | 2 | 35219097 |  |  | CWSP - COARSEGOLD 2104CB PH 1.1 | 10 | Yes | 0 | 12473 | YO |  |  |  | NA |  |  |  |  | The sow has one hwy crossing with poles well out of r/w, provided est guidance of how far to stay away from hwy
35226848 |  | 2 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 3 | No | 0 | 15153 | SI |  |  |  | NA | NA |  |  |  | No UG; basemap no longer needed
35220896 |  | 2 | 35220896 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 1 | No | 1478 | 0 | HB |  |  |  | INPR | 2021-05-25 |  |  |  | 3/31/2021 approval received
35223037 |  | 3 | missing |  |  | PSPS - OAKHURST 1101 - OAKHURST | 10 | No | 105.6 | 0 | YO
35234756 | [5 empty] | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  |  | 14689 | 0 |  |  |  |  | INPR | 2021-05-25
35234758 | [5 empty] | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  |  | 3073 | 0 |  |  |  |  | INPR | 2021-05-25
35234862 | [5 empty] | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  |  | 422 | 0 |  |  |  |  | INPR | 2021-05-25
35234865 | [5 empty] | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  |  | 3419 | 0 |  |  |  |  | INPR | 2021-05-25
35217267 |  |  | 35217267 |  |  | CWSP - MARIPOSA 210197142 PH 2 | 10 | No |  |  | YO | [8 empty] | Need confirmation that Caltrans is NOT needed
35219587 | 35217267 |  | 35217267 |  |  | CWSP - MARIPOSA 2102440236 PH2 | 10 | No |  |  | YO | [8 empty] | Need confirmation that Caltrans is NOT needed
35219588 | 35217267 |  | 35217267 |  |  | CWSP - MARIPOSA 2102440236 PH3 | 10 | No |  |  | YO | [8 empty] | Need confirmation that Caltrans is NOT needed
35174501 | [5 empty] | Not Yet Approved by WFGC | 2 | [12 empty] | Question about where the work is located
35174478 | [5 empty] | Not Yet Approved by WFGC | [13 empty] | Question about where the work is located
35219098 | [5 empty] | Changed to OH Only | [8 empty] | NA | NA |  |  |  | Changed to OH; basemap no longer needed
35219099 | [5 empty] | Not Yet Approved by WFGC
35222045 | [5 empty] | Changed to OH Only | 1
35192282 | [5 empty] | Changed to OH Only | 1
35192281 | [5 empty] | Changed to OH Only | 1 | [12 empty] | waiting for [Redacted] to approve SOW and cost
35174479 | [5 empty] | Not Yet Approved by WFGC
35191937 | [5 empty] | Not Yet Approved by WFGC
35219260 | [5 empty] | Changed to OH Only
35219589 | [5 empty] | CWSP-WILDWOOD 1101-LR 1454-SHASTA CO. | 2 | Yes | [6 empty] | INPR | 2021-05-14 |  |  |  | OH only; mapping for two Hwy Xings
35224321 | [5 empty] | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH1 | 2 | Yes | [6 empty] | INPR | 2021-05-14 |  |  |  | OH replacement in Caltrans RW
35226798 | [5 empty] | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 2 | Yes | [6 empty] | INPR | 2021-05-14 |  |  |  | OH replacement in Caltrans RW
35226900 | [5 empty] | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | 2 | [7 empty] | INPR | 2021-05-14 |  |  |  | OH Removal; site specific for pole removal??
35223030 | [5 empty] | BANGOR 1101 - MICROGRID | 3 | No | [6 empty] | INPR | 2021-04-23
35219276 | [5 empty] | VACAVILLE 1104 PH 1.1 | 4 | [6 empty] | TBD | TBD |  |  |  |  | Main UG segment
35227651 | [5 empty] | VACAVILLE 1104 PH 1.2 | 4 | [6 empty] | NA | NA | NA |  |  |  | OH harden; No mapping per [Redacted]
35227652 | [5 empty] | VACAVILLE 1104 PH 1.3 | 4 | [6 empty] | TBD | TBD |  |  |  |  | small UG segment
35227654 | [5 empty] | VACAVILLE 1104 PH 1.5 | 4 | [6 empty] | NA | NA | NA |  |  |  | OH removal, Caltrans Xings NO mapping per [Redacted]
35224378 | [5 empty] | Not Yet Approved by WFGC
35192290 | [5 empty] | Changed to OH Only
35026643 | [5 empty] | Changed to OH Only
35054184 | [5 empty] | Not Yet Approved by WFGC
35217267 | [5 empty] | Changed to OH Only
35116385 | [5 empty] | CWSP - MI-WUK VILLAGE 1701 PH 1.4 | 10 | Yes | [6 empty] | INPR | TBD
35223036 | [5 empty] | PSPS - BRUNSWICK-Morgan Ranch Dr. (Grass Valley) |  | No | [6 empty] | INPR | 2021-04-30