## Project Status Report
Order | Order Text | WBS Element | Planning Order | User Status | Job Owner | County Cd | Main Work Center (PM | MaintActivityType | Authorized Amt. | Authorized Amt. | Contingency | Auth Amt (AJE) | Total Actual $ | Total Fcst $ | Total EAC $ | Variance $ (Auth Amt - EAC) | Variance $ (Auth Amt - Total Act) | Total Actual $ | Committed (Open Items) | Assigned (Act + Com) | Var (Auth- Assigned) | % Spent (Total Act $ /Auth Amt) | % Spent (Assigned/ Auth) | Apr to Apr Plan Cost | Apr to Apr Actual Cost | Apr to Apr Var Cost | Apr to Apr Var Cost % | 1995 to 2020 Actual Amt | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | 2021 YTD Act Amt | 2021 YTD Actuals + Remaining Plan | Jan 2022 Fcst Amt | Feb 2022 Fcst Amt | Mar 2022 Fcst Amt | Apr 2022 Fcst Amt | May 2022 Fcst Amt | Jun 2022 Fcst Amt | Jul 2022 Fcst Amt | Aug 2022 Fcst Amt | Sep 2022 Fcst Amt | Oct 2022 Fcst Amt | Nov 2022 Fcst Amt | Dec 2022 Fcst Amt | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt
Overall Result | [9 empty] | #VALUE! | #VALUE! | 111439231.25 | 68460469.45 | 86947949.97 | 155408419.42 | -43969188.17 | 42978761.8 | 68460469.45 | 1886605.56 | 70347075.01 | 41092156.24 | 61.43% | 63.13% | 1779655.11 | -223675.46 | 2003330.57 | 112.5685 | 64387813.55 | 1270810.72 | 786166.32 | 2239354.32 | -223675.46 | 125979.45 | 2092379.45 | 3101786.55 | 3916681.14 | 9087549.57 | 10885582.82 | 10316215.76 | 3990191.54 | 4072655.9 | 47589022.18 | 46251.77 | 3544.83 | 5908544.83 | 3544.83 | 3544.83 | 3544.83 | 3672.46 | 2276.5 | 880.54 | 476.77 | 36.5 | 37455265 | 43431583.69
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | ESTS |  | 009-El Dorado County | Placerville | 08W | USD 166,667.00 | 166667 | 0 | 166667 | 50474.29 | 1109.77 | 51584.06 | 115082.94 | 116192.71 | 50474.29 |  | 50474.29 | 116192.71 | 30.28% | 30.28% | 144.09 |  | 144.09 | 100 | 25469.95 | 34408.12 | -13457.4 | 4053.62 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 25004.34 | 26114.11
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | PEND |  | 009-El Dorado County | Placerville | 08W | USD 725,000.00 | 725000 | 0 | 725000 | 591126.85 |  | 591126.85 | 133873.15 | 133873.15 | 591126.85 |  | 591126.85 | 133873.15 | 81.53% | 81.53% | 5000 | 17.41 | 4982.59 | 99.6518 | 577162.85 | 3628.01 | 4866.92 | 5451.66 | 17.41 | [8 empty] | 13964 | 13964
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | ESTS |  | 009-El Dorado County | Placerville | 08W | USD 600,000.00 | 600000 | 0 | 600000 | 320626.81 |  | 320626.81 | 279373.19 | 279373.19 | 320626.81 |  | 320626.81 | 279373.19 | 53.44% | 53.44% | 5000 | 17.41 | 4982.59 | 99.6518 | 321943.44 | -8267.3 | 3069.14 | 3864.12 | 17.41 | [8 empty] | -1316.63 | -1316.63
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 | 5782534 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,201,494.00 | 3201494 | -0.39 | 3201494.39 | 2706370.01 |  | 2706370.01 | 495124.38 | 495124.38 | 2706370.01 |  | 2706370.01 | 495124.38 | 84.53% | 84.53% |  |  |  |  | 2706370.01
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | PEND |  | 009-El Dorado County | Placerville | 08W | USD 725,000.00 | 725000 | 0 | 725000 | 306635.06 | 41069.58 | 347704.64 | 377295.36 | 418364.94 | 306635.06 | 22840.75 | 329475.81 | 395524.19 | 42.29% | 45.44% | 7537.4 | 34.82 | 7502.58 | 99.538 | 249135.22 | 45821.1 | 9178.19 | 2465.73 | 34.82 | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 57499.84 | 78212.14 | 2694.9 | 2694.9 | 2694.9 | 2694.9 | 2694.9 | 2694.9 | 2791.92 | 1395.96 |  |  |  |  | 20357.28
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | FICL |  | 009-El Dorado County | Placerville | 08W | USD 4,515,047.00 | 4515047 | 955704.32 | 3559342.68 | 3103351.2 |  | 3103351.2 | 455991.48 | 455991.48 | 3103351.2 |  | 3103351.2 | 455991.48 | 87.19% | 87.19% |  | -782.84 | 782.84 |  | 3069330.35 | -59587.45 | 80652.78 | 13738.36 | -782.84 | [8 empty] | 34020.85 | 34020.85
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 4,711,641.00 | 4711641 | 1252143 | 3459498 | 2313662.14 | 1000232 | 3313894.14 | 145603.86 | 1145835.86 | 2313662.14 | 98569.13 | 2412231.27 | 1047266.73 | 66.88% | 69.73% | 132906.13 | -12698.1 | 145604.23 | 109.5542 | 2040317.39 | 20400.28 | 30760.85 | 234881.72 | -12698.1 |  |  |  |  | 500000 | 500232 |  |  | 273344.75 | 1273576.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 4,913,095.00 | 4913095 | 1023067.24 | 3890027.76 | 1677909.82 | 1718409 | 3396318.82 | 493708.94 | 2212117.94 | 1677909.82 | 452434.03 | 2130343.85 | 1759683.91 | 43.13% | 54.76% | 232432.8 | -12657.16 | 245089.96 | 105.4455 | 1480324.78 | 24395.47 | 110421.4 | 75425.33 | -12657.16 |  |  |  |  | 500000 | 500000 | 718409 |  | 197585.04 | 1915994.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 4,228,889.00 | 4228889 | 1038921.96 | 3189967.04 | 1978630.53 | 75000 | 2053630.53 | 1136336.51 | 1211336.51 | 1978630.53 |  | 1978630.53 | 1211336.51 | 62.03% | 62.03% |  |  |  |  | 1978641.48 |  |  | -10.95 | [8 empty] | 75000 | -10.95 | 74989.05
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | ESTS |  | 009-El Dorado County | Placerville | 08W | USD 900,000.00 | 900000 | 0 | 900000 | 617113.95 |  | 617113.95 | 282886.05 | 282886.05 | 617113.95 | 148634.68 | 765748.63 | 134251.37 | 68.57% | 85.08% | 5000 | 69.64 | 4930.36 | 98.6072 | 529344.32 | 80634.05 | 3532.97 | 3532.97 | 69.64 | [8 empty] | 87769.63 | 87769.63
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | FICL |  | 009-El Dorado County | Placerville | 08W | USD 3,529,311.00 | 3529311 | 743625.14 | 2785685.86 | 1945492.6 |  | 1945492.6 | 840193.26 | 840193.26 | 1945492.6 |  | 1945492.6 | 840193.26 | 69.84% | 69.84% |  |  |  |  | 1943877.83 | 504.63 | 605.55 | 504.59 | [9 empty] | 1614.77 | 1614.77
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 | 5785515 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,608,462.00 | 3608462 | 457433.19 | 3151028.81 | 2621459.58 |  | 2621459.58 | 529569.23 | 529569.23 | 2621459.58 |  | 2621459.58 | 529569.23 | 83.19% | 83.19% |  |  |  |  | 2621459.58
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 4,499,650.00 | 4499650 | -0.65 | 4499650.65 | 3786637.1 | 75000 | 3861637.1 | 638013.55 | 713013.55 | 3786637.1 |  | 3786637.1 | 713013.55 | 84.15% | 84.15% |  | -4985 | 4985 |  | 3786591.22 |  |  | 5030.88 | -4985 | [7 empty] | 75000 | 45.88 | 75045.88
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | ESTS |  | 009-El Dorado County | Placerville | 08W | USD 900,000.00 | 900000 | 0 | 900000 | 599887.87 | 3175.75 | 603063.62 | 296936.38 | 300112.13 | 599887.87 |  | 599887.87 | 300112.13 | 66.65% | 66.65% | 5882.74 | 17.41 | 5865.33 | 99.704 | 559107.68 | 33624.94 | 3432.13 | 3705.71 | 17.41 | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 40780.19 | 43955.94
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,530,637.00 | 3530637 | 0.63 | 3530636.37 | 3101220.78 | 42017 | 3143237.78 | 387398.59 | 429415.59 | 3101220.78 |  | 3101220.78 | 429415.59 | 87.84% | 87.84% |  |  |  |  | 3052145.09 | 16888.53 | 16093.58 | 16093.58 | [8 empty] | 42017 | 49075.69 | 91092.69
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 7,082,947.00 | 7082947 | 1602579 | 5480368 | 5379872.97 | 106865 | 5486737.97 | -6369.97 | 100495.03 | 5379872.97 |  | 5379872.97 | 100495.03 | 98.17% | 98.17% |  |  |  |  | 5039334.63 | 336335.63 | 6799.89 | -2597.18 | [8 empty] | 106865 | 340538.34 | 447403.34
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,123,544.00 | 3123544 | -0.1 | 3123544.1 | 2635581.04 | 177549 | 2813130.04 | 310414.06 | 487963.06 | 2635581.04 | 28251.72 | 2663832.76 | 459711.34 | 84.38% | 85.28% |  |  |  |  | 2738130.42 | -102549.38 | [7 empty] | 177549 |  |  |  | -102549.38 | 74999.62
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,044,150.00 | 3044150 | 1.98 | 3044148.02 | 2848313.16 | 75000 | 2923313.16 | 120834.86 | 195834.86 | 2848313.16 |  | 2848313.16 | 195834.86 | 93.57% | 93.57% |  |  |  |  | 2848313.16 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 3,172,299.00 | 3172299 | 1.23 | 3172297.77 | 2686391.99 | 75000 | 2761391.99 | 410905.78 | 485905.78 | 2686391.99 |  | 2686391.99 | 485905.78 | 84.68% | 84.68% |  |  |  |  | 2686391.99 | [6 empty] | 75000 | [6 empty] | 75000
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 5,804,263.00 | 5804263 | 0.93 | 5804262.07 | 4548604.36 | 74326 | 4622930.36 | 1181331.71 | 1255657.71 | 4548604.36 |  | 4548604.36 | 1255657.71 | 78.37% | 78.37% |  |  |  |  | 4447929.88 | 100674.48 | [6 empty] | 74326 |  |  |  |  | 100674.48 | 175000.48
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 4,009,924.00 | 4009924 | -0.5 | 4009924.5 | 3830827.63 | 75000 | 3905827.63 | 104096.87 | 179096.87 | 3830827.63 |  | 3830827.63 | 179096.87 | 95.53% | 95.53% |  |  |  |  | 3830827.63 | [5 empty] | 75000 | [7 empty] | 75000
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 2,287,663.00 | 2287663 | 11025 | 2276638 | 2058021.42 | 74251 | 2132272.42 | 144365.58 | 218616.58 | 2058021.42 |  | 2058021.42 | 218616.58 | 90.4% | 90.4% |  |  |  |  | 2057272.01 | 749.41 |  |  |  |  | 74251 | [6 empty] | 749.41 | 75000.41
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 4,477,708.00 | 4477708 | 5757.52 | 4471950.48 | 3634489.08 | 71973 | 3706462.08 | 765488.4 | 837461.4 | 3634489.08 |  | 3634489.08 | 837461.4 | 81.27% | 81.27% |  |  |  |  | 3631462.06 | 3027.02 | [5 empty] | 71973 | [5 empty] | 3027.02 | 75000.02
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 1,197,284.00 | 1197284 | 80818.38 | 1116465.62 | 898206.13 | 75000 | 973206.13 | 143259.49 | 218259.49 | 898206.13 |  | 898206.13 | 218259.49 | 80.45% | 80.45% |  |  |  |  | 898206.13 | [7 empty] | 75000 | [5 empty] | 75000
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | DOCC |  | 009-El Dorado County | Placerville | 08W | USD 5,238,478.00 | 5238478 | 2274925.68 | 2963552.32 | 2244138.27 |  | 2244138.27 | 719414.05 | 719414.05 | 2244138.27 |  | 2244138.27 | 719414.05 | 75.72% | 75.72% |  | -1234.7 | 1234.7 |  | 2168872.73 | 12643.16 | -25483.28 | 89340.36 | -1234.7 | [8 empty] | 75265.54 | 75265.54
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | FICL |  | 009-El Dorado County | Placerville | 08W | USD 5,585,619.00 | 5585619 | 1694081.11 | 3891537.89 | 2167262.09 | 19830 | 2187092.09 | 1704445.8 | 1724275.8 | 2167262.09 |  | 2167262.09 | 1724275.8 | 55.69% | 55.69% |  | -20 | 20 |  | 2112114.28 | 1287.84 | -72375.41 | 126255.38 | -20 | [7 empty] | 19830 | 55147.81 | 74977.81
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 5,273,989.00 | 5273989 | 1248322.62 | 4025666.38 | 1682481.92 | 1766414 | 3448895.92 | 576770.46 | 2343184.46 | 1682481.92 | 150892.46 | 1833374.38 | 2192292 | 41.79% | 45.54% | 79598.84 | -28967.15 | 108565.99 | 136.3914 | 1036914.83 | 138183.81 | 180505.04 | 355845.39 | -28967.15 |  |  |  |  | 1000000 | 766414 |  |  | 645567.09 | 2411981.09
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 3,591,121.00 | 3591121 | 911634.7 | 2679486.3 | 465310.92 | 1947556 | 2412866.92 | 266619.38 | 2214175.38 | 465310.92 | 141169.63 | 606480.55 | 2073005.75 | 17.37% | 22.63% | 225640.37 | -40980.28 | 266620.65 | 118.1618 | 450434.84 | 3022.85 | 2878.44 | 49955.07 | -40980.28 | [6 empty] | 1000000 | 947556 | 14876.08 | 1962432.08
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 4,734,585.00 | 4734585 | 1528234.31 | 3206350.69 | 830772.61 | 2503182 | 3333954.61 | -127603.92 | 2375578.08 | 830772.61 | 173038.37 | 1003810.98 | 2202539.71 | 25.91% | 31.31% | 213065.89 | -9592 | 222657.89 | 104.5019 | 476027.17 | 3294.16 | 31282.59 | 329760.69 | -9592 | [5 empty] | 1000000 | 1000000 | 503182 | 354745.44 | 2857927.44
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 3,872,109.00 | 3872109 | 1075736.75 | 2796372.25 | 1334779.32 | 2004457 | 3339236.32 | -542864.07 | 1461592.93 | 1334779.32 | 143959.17 | 1478738.49 | 1317633.76 | 47.73% | 52.88% | 230559.33 | 11897.7 | 218661.63 | 94.8396 | 973048.58 | 95427.33 | 63115.65 | 191290.06 | 11897.7 | [5 empty] | 1000000 | 1000000 | 4457 | 361730.74 | 2366187.74
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 5,778,810.00 | 5778810 | 1303102.98 | 4475707.02 | 2271249.76 | 1732683 | 4003932.76 | 471774.26 | 2204457.26 | 2271249.76 | 347292.4 | 2618542.16 | 1857164.86 | 50.75% | 58.51% | 240651.4 | -18509.84 | 259161.24 | 107.6916 | 1812907.5 | 122362.57 | 148848.29 | 205641.24 | -18509.84 | [5 empty] | 1000000 | 732683 |  | 458342.26 | 2191025.26
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | ESTS |  | 029-Nevada County | Grass Valley | 08W | USD 500,000.00 | 500000 | 0 | 500000 | 179078.92 | 3494.58 | 182573.5 | 317426.5 | 320921.08 | 179078.92 |  | 179078.92 | 320921.08 | 35.82% | 35.82% | 524.3 |  | 524.3 | 100 | 144473.49 | 32554.39 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 34605.43 | 38100.01
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 3,876,275.00 | 3876275 | 1124354 | 2751921 | 1557028.35 | 2012197 | 3569225.35 | -817304.35 | 1194892.65 | 1557028.35 | 123063.71 | 1680092.06 | 1071828.94 | 56.58% | 61.05% | 122848.72 | 16396.82 | 106451.9 | 86.6528 | 954359.95 | 168193.48 | 151055.17 | 267022.93 | 16396.82 | [6 empty] | 1000000 | 1012197 | 602668.4 | 2614865.4
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | PEND |  | 029-Nevada County | Grass Valley | 08W | USD 2,485,715.00 | 2485715 | 683214.72 | 1802500.28 | 442969.12 |  | 442969.12 | 1359531.16 | 1359531.16 | 442969.12 |  | 442969.12 | 1359531.16 | 24.58% | 24.58% |  | -20 | 20 |  | 435171.19 | 2595.63 | 2649.52 | 2572.78 | -20 | [8 empty] | 7797.93 | 7797.93
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | CONS |  | 029-Nevada County | Grass Valley | 08W | USD 1,844,178.00 | 1844178 | 737162 | 1107016 | 333671.78 | 39822.49 | 373494.27 | 733521.73 | 773344.22 | 333671.78 | 34489.51 | 368161.29 | 738854.71 | 30.14% | 33.26% | 28440.09 | 74.45 | 28365.64 | 99.7382 | 322359.92 | 6416.06 | 2067.19 | 2754.16 | 74.45 | 38742.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 11311.86 | 51134.35
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | PEND |  | 009-El Dorado County | Auburn | 08W | USD 500,000.00 | 500000 | 0 | 500000 | 157260.07 | 1193.96 | 158454.03 | 341545.97 | 342739.93 | 157260.07 | 9900 | 167160.07 | 332839.93 | 31.45% | 33.43% | 260.02 |  | 260.02 | 100 | 150941.25 | 4134.25 | 1285.33 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 6318.82 | 7512.78
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | PEND |  | 005-Calaveras County | Angels Camp | 08W | USD 5,959,167.00 | 5959167 | 1836977 | 4122190 | 269085.96 | 44306.84 | 313392.8 | 3808797.2 | 3853104.04 | 269085.96 | 12070 | 281155.96 | 3841034.04 | 6.528% | 6.821% | 10607.29 | 21779.46 | -11172.17 | -105.3254 | 187046.78 | 22610.37 | 30732.54 | 6916.81 | 21779.46 | 637.29 | 637.29 | 325.32 | [5 empty] | 82039.18 | 83639.08 | 42706.94 | [11 empty] | 42706.94
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | ESTS |  | 009-El Dorado County | Auburn | 08W | USD 166,667.00 | 166667 | 0 | 166667 | 22851.36 |  | 22851.36 | 143815.64 | 143815.64 | 22851.36 |  | 22851.36 | 143815.64 | 13.71% | 13.71% |  |  |  |  | 214.56 | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | ESTS |  | 009-El Dorado County | Auburn | 08W | USD 166,667.00 | 166667 | 0 | 166667 | 27131.3 | 14.01 | 27145.31 | 139521.69 | 139535.7 | 27131.3 |  | 27131.3 | 139535.7 | 16.28% | 16.28% | 2.49 |  | 2.49 | 100 | 608.93 | 46799.02 | -20431.72 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 26522.37 | 26536.38
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | UNSE |  | 009-El Dorado County | Placerville | 08W | USD 950,000.00 | 950000 | 0 | 950000 | 8444.7 | 3.76 | 8448.46 | 941551.54 | 941555.3 | 8444.7 |  | 8444.7 | 941555.3 | 0.8889% | 0.8889% | 0.82 |  | 0.82 | 100 | 8275.39 | 50.59 | 3891.36 | -3772.64 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | UNSE |  | 009-El Dorado County | Placerville | 08W | USD 950,000.00 | 950000 | 0 | 950000 | 19761.25 |  | 19761.25 | 930238.75 | 930238.75 | 19761.25 |  | 19761.25 | 930238.75 | 2.08% | 2.08% |  |  |  |  | 19398.23 | 118.54 | 3295.24 | -3050.76 | [9 empty] | 363.02 | 363.02
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | UNSE |  | 009-El Dorado County | Placerville | 08W | USD 950,000.00 | 950000 | 0 | 950000 | 12501.35 | 11.16 | 12512.51 | 937487.49 | 937498.65 | 12501.35 |  | 12501.35 | 937498.65 | 1.316% | 1.316% | 2.43 |  | 2.43 | 100 | 12283.16 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | UNSE |  | 032-Plumas County | Chico | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 21438.66 | 361623 | 383061.66 | -233061.66 | 128561.34 | 21438.66 |  | 21438.66 | 128561.34 | 14.29% | 14.29% |  | 487.48 | -487.48 |  | 604.67 | 15933.64 | 2441.83 | 1971.04 | 487.48 |  |  | 100000 | 130000 | 131623 |  |  |  | 20833.99 | 382456.99
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | UNSE |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 25600.52 | 1020046 | 1045646.52 | -895646.52 | 124399.48 | 25600.52 |  | 25600.52 | 124399.48 | 17.07% | 17.07% | 15150 | -24570 | 39720 | 262.1782 | 2467.61 | 14932.4 | 7721.95 | 25048.56 | -24570 | 2793 |  |  | 400000 | 67253 |  |  |  | 23132.91 | 493178.91 | [11 empty] | 550000 | 550000
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | ADER |  | 004-Butte County | Oroville | 08W | USD 300,000.00 | 300000 | 0 | 300000 | 58851.03 | 1451350 | 1510201.03 | -1210201.03 | 241148.97 | 58851.03 |  | 58851.03 | 241148.97 | 19.62% | 19.62% | 10000 |  | 10000 | 100 | 199.39 | 11297.45 | 409.58 | 46944.61 |  |  | 500000 | 500000 | 443055 | 8295 |  |  |  | 58651.64 | 1510001.64
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | UNSE |  | 004-Butte County | Oroville | 08W | USD 950,000.00 | 950000 | 0 | 950000 | 35982.42 | 1985972.09 | 2021954.51 | -1071954.51 | 914017.58 | 35982.42 |  | 35982.42 | 914017.58 | 3.788% | 3.788% | 20773.47 | 1840.7 | 18932.77 | 91.1392 |  | 237.15 | 12632.89 | 21271.68 | 1840.7 | 214.1 | 87344.1 | 100217.63 | 100217.63 | 100217.63 | 100217.63 | 217.63 | 217.63 | 35982.42 | 524846.4 | 219 | 219 | 219 | 219 | 219 | 219 | 226.89 | 226.89 | 226.89 | 113.44 |  | 1495000 | 1497108.11
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | UNSE |  | 004-Butte County | Oroville | 08W | USD 950,000.00 | 950000 | 0 | 950000 | 26846.89 | 5905000 | 5931846.89 | -4981846.89 | 923153.11 | 26846.89 |  | 26846.89 | 923153.11 | 2.826% | 2.826% | 20786.41 | 1453.85 | 19332.56 | 93.0058 |  | 330.92 | 10083.29 | 14978.83 | 1453.85 | [8 empty] | 26846.89 | 26846.89 |  |  | 5905000 | [9 empty] | 5905000
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | UNSE |  | 032-Plumas County | Chico | 08W | USD 400,000.00 | 400000 | 0 | 400000 | 5580.4 | 15641437.46 | 15647017.86 | -15247017.86 | 394419.6 | 5580.4 |  | 5580.4 | 394419.6 | 1.395% | 1.395% | 5733.88 |  | 5733.88 | 100 |  |  | 2617.64 | 2962.76 |  | 36664.02 | 273.52 | 276.38 | 276.38 | 350367.38 | 276.38 | 276.38 | 276.38 | 5580.4 | 394267.22 | 285.75 | 285.75 | 285.75 | 285.75 | 285.75 | 285.75 | 296.04 | 296.04 | 296.04 | 148.02 |  | 15250000 | 15252750.64
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | UNSE |  | 032-Plumas County | Chico | 08W | USD 400,000.00 | 400000 | 0 | 400000 | 2212.64 | 6299466.04 | 6301678.68 | -5901678.68 | 397787.36 | 2212.64 |  | 2212.64 | 397787.36 | 0.5532% | 0.5532% | 5966.7 |  | 5966.7 | 100 |  |  | 2094.12 | 118.52 |  | 36653.66 | 263.16 | 265.81 | 265.81 | 353575.81 | 265.81 | 265.81 | 265.81 | 2212.64 | 394034.32 | 274.71 | 274.71 | 274.71 | 274.71 | 274.71 | 274.71 | 284.6 | 284.6 | 284.6 | 142.3 |  | 5905000 | 5907644.36
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 100,000.00 | 100000 | 0 | 100000 | 12840.17 | 4824003 | 4836843.17 | -4736843.17 | 87159.83 | 12840.17 |  | 12840.17 | 87159.83 | 12.84% | 12.84% |  | 104.46 | -104.46 |  |  |  | 1996.34 | 10739.37 | 104.46 |  |  | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  | 12840.17 | 4836843.17
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | ESTS |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 1077.8 | 515568.48 | 516646.28 | -366646.28 | 148922.2 | 1077.8 |  | 1077.8 | 148922.2 | 0.7185% | 0.7185% | 10535.5 | -24570 | 35105.5 | 333.2115 |  |  |  | 25647.8 | -24570 | 67 | 250067 | 250068.02 | 14343.02 | 68.02 | 68.02 | 68.02 | 68.02 | 1077.8 | 515894.92 | 70.47 | 70.47 | 70.47 | 70.47 | 70.47 | 70.47 | 73.01 | 73.01 | 73.01 | 73.01 | 36.5 |  | 751.36
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | UNSE |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 898.31 | 2861404 | 2862302.31 | -2712302.31 | 149101.69 | 898.31 |  | 898.31 | 149101.69 | 0.5989% | 0.5989% | 11040 | -24570 | 35610 | 322.5543 |  |  | 261.78 | 25206.53 | -24570 | 1758 |  |  |  | 400000 | 89646 |  |  | 898.31 | 492302.31 | [11 empty] | 2370000 | 2370000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | UNSE |  | 045-Shasta County | Redding | 08W | USD 200,000.00 | 200000 | 0 | 200000 | 855 | 6048712 | 6049567 | -5849567 | 199145 | 855 |  | 855 | 199145 | 0.4275% | 0.4275% | 20264 | -24570 | 44834 | 221.2495 |  |  | 261.78 | 25163.22 | -24570 | 4066 |  |  |  |  | 400000 | 89646 |  | 855 | 494567 | [11 empty] | 5555000 | 5555000
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | ESTS |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 164.72 | 2660867 | 2661031.72 | -2511031.72 | 149835.28 | 164.72 |  | 164.72 | 149835.28 | 0.1098% | 0.1098% | 50400 | -24570 | 74970 | 148.75 |  |  |  | 24734.72 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 | 164.72 | 2661031.72
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | ESTS |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 | 1435.47 | 2846093 | 2847528.47 | -2697528.47 | 148564.53 | 1435.47 |  | 1435.47 | 148564.53 | 0.957% | 0.957% | 53900 | -24570 | 78470 | 145.5844 |  |  | 261.78 | 25743.69 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  | 1435.47 | 2847528.47
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | UNSE |  | 004-Butte County | Oroville | 08W | USD 650,000.00 | 650000 | 0 | 650000 |  | 1995265 | 1995265 | -1345265 | 650000 |  |  |  | 650000 |  |  | 9000 |  | 9000 | 100 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | [11 empty] | 1495265 | 1495265
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 100,000.00 | 100000 | 0 | 100000 |  | 4104000 | 4104000 | -4004000 | 100000 |  |  |  | 100000 | [14 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 |  | 3360000 | 3360000 | -3210000 | 150000 |  |  |  | 150000 | [14 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | [11 empty] | 2860000 | 2860000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 150,000.00 | 150000 | 0 | 150000 |  | 2200000 | 2200000 | -2050000 | 150000 |  |  |  | 150000 | [14 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | [11 empty] | 1700000 | 1700000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 125,000.00 | 125000 | 0 | 125000 |  | 400000 | 400000 | -275000 | 125000 |  |  |  | 125000 | [14 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | [11 empty] | 275000 | 275000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 75,000.00 | 75000 | 0 | 75000 |  | 665000 | 665000 | -590000 | 75000 |  |  |  | 75000 | [14 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 100,000.00 | 100000 | 0 | 100000 |  | 2945000 | 2945000 | -2845000 | 100000 |  |  |  | 100000 | [15 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | UNSE |  | 045-Shasta County | Redding | 08W | USD 100,000.00 | 100000 | 0 | 100000 |  | 3021000 | 3021000 | -2921000 | 100000 |  |  |  | 100000 | [14 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000

## PRJ002 - $$ Detail
Order | Order Text | WBS Element | Job Owner | User Status | Cost Element |  | Auth Amt (AJE) | Total Actual Amount | Total Forecast | Total EAC | Variance $ (Auth Amt - EAC) | 1995 to 2020 Actual Amt | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | 2021 YTD Act Amt | 2021 YTD Actuals + Remaining Plan | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt
Overall Result | [6 empty] | 111439231.25 | 68460469.45 | 86947949.97 | 155408419.42 | -43969188.17 | 64387813.55 | 1270810.72 | 786166.32 | 2239354.32 | -223675.46 | 125979.45 | 2092379.45 | 3101786.55 | 3916681.14 | 9087549.57 | 10885582.82 | 10316215.76 | 3990191.54 | 4072655.9 | 47589022.18 | 43431583.69
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 166667 |  | 1109.77 | 51584.06 | 115082.94 | 25469.95 | 34408.12 | -13457.4 | 4053.62 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 25004.34 | 26114.11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 166667 |  | 1109.77 | 51584.06 | 115082.94 | 25469.95 | 34408.12 | -13457.4 | 4053.62 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 25004.34 | 26114.11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 10530.42 | -10530.42 | 9299.87 |  |  | 1230.55 | [9 empty] | 1230.55 | 1230.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 10530.42 | -10530.42 | 9299.87 |  |  | 1230.55 | [9 empty] | 1230.55 | 1230.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 10530.42 | -10530.42 | 9299.87 |  |  | 1230.55 | [9 empty] | 1230.55 | 1230.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 9941.46 | -9941.46 | 8721.89 |  |  | 1219.57 | [9 empty] | 1219.57 | 1219.57
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Construction Overtime Services | 6603021 |  |  |  | 1219.57 | -1219.57 |  |  |  | 1219.57 | [9 empty] | 1219.57 | 1219.57
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 3208.26 | -3208.26 | 3208.26
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Technical Services | 6603058 |  |  |  | 4523.52 | -4523.52 | 4523.52
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Management Services | 6603076 |  |  |  | 109.4 | -109.4 | 109.4
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 195.2 | -195.2 | 195.2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Land Rights - Misc | 6603227 |  |  |  | 30.41 | -30.41 | 30.41
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Hours - Straight Time | 6608193 |  |  |  | 244.56 | -244.56 | 244.56
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Hours - Overtime | 6608194 |  |  |  | 176.04 | -176.04 | 176.04
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Hours - Doubletime | 6608195 |  |  |  | 234.5 | -234.5 | 234.5
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 588.96 | -588.96 | 577.98 |  |  | 10.98 | [9 empty] | 10.98 | 10.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Estimating-Internal | 6010076 |  |  |  | 577.98 | -577.98 | 577.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Mapping | 6010077 |  |  |  | 10.98 | -10.98 |  |  |  | 10.98 | [9 empty] | 10.98 | 10.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Contract Total | PGE1CONTRACT | 166667 |  |  | 22350.48 | 144316.52 | 1961.93 | 34153.17 | -13764.62 | [10 empty] | 20388.55 | 20388.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 166667 |  |  | 22350.48 | 144316.52 | 1961.93 | 34153.17 | -13764.62 | [10 empty] | 20388.55 | 20388.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Contracts | 5490000 | 166667 |  |  |  | 166667
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 20388.55 | -20388.55 |  | 34153.17 | -13764.62 | [10 empty] | 20388.55 | 20388.55
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Environmental Contract | 5490015 |  |  |  | 1961.93 | -1961.93 | 1961.93
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 1109.77 | 18703.16 | -18703.16 | 14208.15 | 254.95 | 307.22 | 2823.07 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 3385.24 | 4495.01
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  |  | 792.02 | -792.02 | 792.02
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 792.02 | -792.02 | 792.02
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Land Acquisition Services | 5501093 |  |  |  | 792.02 | -792.02 | 792.02
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  | 1109.77 | 17911.14 | -17911.14 | 13416.13 | 254.95 | 307.22 | 2823.07 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 3385.24 | 4495.01
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 3482.06 | -3482.06 | 3028.97 |  |  | 453.09 | [9 empty] | 453.09 | 453.09
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 3482.06 | -3482.06 | 3028.97 |  |  | 453.09 | [9 empty] | 453.09 | 453.09
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 7030.2 | -7030.2 | 5575.76 |  |  | 1454.44 | [9 empty] | 1454.44 | 1454.44
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 6202.81 | -6202.81 | 4881.58 |  |  | 1321.23 | [9 empty] | 1321.23 | 1321.23
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 1179.49 | -1179.49 | 931.66 |  |  | 247.83 | [9 empty] | 247.83 | 247.83
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 1659.21 | -1659.21 | 1242.06 |  |  | 417.15 | [9 empty] | 417.15 | 417.15
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 10.25 | -10.25 | 10.25
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Indirect Labor - IT | 6010111 |  |  |  | 153.95 | -153.95 | 153.95
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1830.2 | -1830.2 | 1452.67 |  |  | 377.53 | [9 empty] | 377.53 | 377.53
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 4.52 | -4.52 | 4.52
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Operation Mgmt & Support - IT | 6010119 |  |  |  | 181 | -181 | 181
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Fleet OH | 6010123 |  |  |  | 905.47 | -905.47 | 905.47
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Fleet OH - Elec | 6010125 |  |  |  | 278.72 | -278.72 |  |  |  | 278.72 | [9 empty] | 278.72 | 278.72
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 827.39 | -827.39 | 694.18 |  |  | 133.21 | [9 empty] | 133.21 | 133.21
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 534.78 | -534.78 | 449.8 |  |  | 84.98 | [9 empty] | 84.98 | 84.98
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | IT Device OH | 6010113 |  |  |  | 292.61 | -292.61 | 244.38 |  |  | 48.23 | [9 empty] | 48.23 | 48.23
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 3974.63 | -3974.63 | 3337.21 |  |  | 637.42 | [9 empty] | 637.42 | 637.42
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Benefits OH | 6010120 |  |  |  | 2900.03 | -2900.03 | 2429.88 |  |  | 470.15 | [9 empty] | 470.15 | 470.15
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 1074.6 | -1074.6 | 907.33 |  |  | 167.27 | [9 empty] | 167.27 | 167.27
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  | 1109.77 | 3424.25 | -3424.25 | 1474.19 | 254.95 | 307.22 | 278.12 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 840.29 | 1950.06
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  | 1109.77 | 2469.64 | -2469.64 | 1127.47 | 74.13 | 83.07 | 75.2 |  | 144.09 | 144.09 | 149.38 | 149.38 | 149.38 | 149.38 | 149.38 | 74.69 | 232.4 | 1342.17
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 954.61 | -954.61 | 346.72 | 180.82 | 224.15 | 202.92 | [9 empty] | 607.89 | 607.89
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 725000 |  |  | 591126.85 | 133873.15 | 577162.85 | 3628.01 | 4866.92 | 5451.66 | 17.41 | [8 empty] | 13964 | 13964
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 725000 |  |  | 591126.85 | 133873.15 | 577162.85 | 3628.01 | 4866.92 | 5451.66 | 17.41 | [8 empty] | 13964 | 13964
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  |  |  | 50027.49 | -50027.49 | 49297.21 | 36.79 |  | 676.08 | 17.41 | [8 empty] | 730.28 | 730.28
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  |  |  | 50027.49 | -50027.49 | 49297.21 | 36.79 |  | 676.08 | 17.41 | [8 empty] | 730.28 | 730.28
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 50027.49 | -50027.49 | 49297.21 | 36.79 |  | 676.08 | 17.41 | [8 empty] | 730.28 | 730.28
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 33202.26 | -33202.26 | 32478.01 | 36.79 |  | 670.05 | 17.41 | [8 empty] | 724.25 | 724.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Administration | 6603000 |  |  |  | 1539.31 | -1539.31 | 1539.31
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  |  | 670.05 | [9 empty] | 670.05 | 670.05
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Acquisition - Misc | 6603004 |  |  |  | 10416.58 | -10416.58 | 10416.58
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Analyst Services | 6603005 |  |  |  | 54.68 | -54.68 | 54.68
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Construction Overtime Services | 6603021 |  |  |  | 847.44 | -847.44 | 847.44
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Engineering/Mapping | 6603022 |  |  |  | 3719.7 | -3719.7 | 3719.7
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Environmental Services | 6603024 |  |  |  | 17.41 | -17.41 |  | 17.41 | [11 empty] | 17.41 | 17.41
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 214.93 | -214.93 | 197.52 |  |  |  | 17.41 | [8 empty] | 17.41 | 17.41
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 8687.45 | -8687.45 | 8671.25 | 16.2 | [11 empty] | 16.2 | 16.2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Management Services | 6603076 |  |  |  | 1200.69 | -1200.69 | 1200.69
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 692.92 | -692.92 | 692.92
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Administrative Services - OT | 6603150 |  |  |  | 1350.45 | -1350.45 | 1350.45
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Rights - Misc | 6603227 |  |  |  | 153.34 | -153.34 | 153.34
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Electric Estimating | 6603466 |  |  |  | 269.91 | -269.91 | 269.91
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Electric Estimating Overtime | 6603467 |  |  |  | 1961.86 | -1961.86 | 1958.68 | 3.18 | [11 empty] | 3.18 | 3.18
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Account Services | 6603730 |  |  |  | 440.49 | -440.49 | 440.49
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Manage L&EM | 6603823 |  |  |  | 889.34 | -889.34 | 889.34
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Analyst Svcs Overtime | 6603855 |  |  |  | 75.71 | -75.71 | 75.71
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 16825.23 | -16825.23 | 16819.2 |  |  | 6.03 | [9 empty] | 6.03 | 6.03
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Estimating-Internal | 6010076 |  |  |  | 15995.82 | -15995.82 | 15995.82
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Mapping | 6010077 |  |  |  | 829.41 | -829.41 | 823.38 |  |  | 6.03 | [9 empty] | 6.03 | 6.03
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Contract Total | PGE1CONTRACT | 725000 |  |  | 421554.58 | 303445.42 | 420054.58 |  | 1500 | [10 empty] | 1500 | 1500
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Consulting | PGE1CONSULTING |  |  |  | 2082.95 | -2082.95 | 2082.95
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Consulting Services - Environmental Perm | 5001237 |  |  |  | 82.95 | -82.95 | 82.95
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Consulting Services - Other | 5001250 |  |  |  | 2000 | -2000 | 2000
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 725000 |  |  | 419471.63 | 305528.37 | 417971.63 |  | 1500 | [10 empty] | 1500 | 1500
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Contracts | 5490000 | 725000 |  |  | 286899.08 | 438100.92 | 286899.08
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 112468.21 | -112468.21 | 112468.21
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Environmental Contract | 5490015 |  |  |  | 18604.34 | -18604.34 | 18604.34
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Traffic Control Contracts | 5490027 |  |  |  | 1500 | -1500 |  |  | 1500 | [10 empty] | 1500 | 1500
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER |  |  |  | 119544.78 | -119544.78 | 107811.06 | 3591.22 | 3366.92 | 4775.58 | [9 empty] | 11733.72 | 11733.72
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Other Cost Elements | PGE1OTHERCE |  |  |  | 3490.09 | -3490.09 | 3490.09
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 3490.09 | -3490.09 | 3490.09
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Cash Discount earned | 5006310 |  |  |  | -40 | 40 | -40
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Permits/Fees | 5501090 |  |  |  | 1750 | -1750 | 1750
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Acquisition Services | 5501093 |  |  |  | 2668.4 | -2668.4 | 2668.4
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Other Land Fees | 5501094 |  |  |  | 5559.98 | -5559.98 | 5559.98
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -6448.29 | 6448.29 | -6448.29
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Employee Related | PGE1EMPLREL |  |  |  | 602.57 | -602.57 | 602.57
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 482.86 | -482.86 | 482.86
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Reimbursed Mileage Expense | 5091140 |  |  |  | 482.86 | -482.86 | 482.86
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Meals | PGE1MEALS-EXP |  |  |  | 119.71 | -119.71 | 119.71
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Meals Expense | 5091100 |  |  |  | 119.71 | -119.71 | 119.71
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Order Overheads | PGE1OVERHEAD |  |  |  | 115452.12 | -115452.12 | 103718.4 | 3591.22 | 3366.92 | 4775.58 | [9 empty] | 11733.72 | 11733.72
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Capitalized A&G | PGE1CAPAG |  |  |  | 17206.32 | -17206.32 | 16943.85 | 13.54 |  | 248.93 | [9 empty] | 262.47 | 262.47
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Capitalized A&G | 6010050 |  |  |  | 17206.32 | -17206.32 | 16943.85 | 13.54 |  | 248.93 | [9 empty] | 262.47 | 262.47
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Labor Overheads | PGE1LABOROH |  |  |  | 49574.69 | -49574.69 | 48743 | 32.6 |  | 799.09 | [9 empty] | 831.69 | 831.69
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 44997.22 | -44997.22 | 44242.14 | 29.17 |  | 725.91 | [9 empty] | 755.08 | 755.08
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Paid Time Off | 6010100 |  |  |  | 8966.91 | -8966.91 | 8823.34 | 7.41 |  | 136.16 | [9 empty] | 143.57 | 143.57
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Indirect Labor - Electric | 6010106 |  |  |  | 8048.96 | -8048.96 | 7818.69 | 1.08 |  | 229.19 | [9 empty] | 230.27 | 230.27
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Indirect Labor - Environmental Land | 6010108 |  |  |  | 8188.7 | -8188.7 | 8176.83 | 11.87 | [11 empty] | 11.87 | 11.87
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Indirect Labor - Cust Care | 6010110 |  |  |  | 84.57 | -84.57 | 84.57
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 10164.12 | -10164.12 | 9955.72 | 0.98 |  | 207.42 | [9 empty] | 208.4 | 208.4
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 3669.76 | -3669.76 | 3662.65 | 7.11 | [11 empty] | 7.11 | 7.11
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 50.41 | -50.41 | 50.41
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Fleet OH | 6010123 |  |  |  | 5669.93 | -5669.93 | 5669.93
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Fleet OH - Elec | 6010125 |  |  |  | 153.86 | -153.86 |  | 0.72 |  | 153.14 | [9 empty] | 153.86 | 153.86
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 4577.47 | -4577.47 | 4500.86 | 3.43 |  | 73.18 | [9 empty] | 76.61 | 76.61
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Building Service Overhead | 6010112 |  |  |  | 2887.16 | -2887.16 | 2838.28 | 2.19 |  | 46.69 | [9 empty] | 48.88 | 48.88
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | IT Device OH | 6010113 |  |  |  | 1690.31 | -1690.31 | 1662.58 | 1.24 |  | 26.49 | [9 empty] | 27.73 | 27.73
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Other Overhead | PGE1OTHEROH |  |  |  | 24911.96 | -24911.96 | 24544.62 | 17.12 |  | 350.22 | [9 empty] | 367.34 | 367.34
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Benefits OH | 6010120 |  |  |  | 18554.25 | -18554.25 | 18283.13 | 12.81 |  | 258.31 | [9 empty] | 271.12 | 271.12
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Payroll Taxes OH | 6010121 |  |  |  | 6357.71 | -6357.71 | 6261.49 | 4.31 |  | 91.91 | [9 empty] | 96.22 | 96.22
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 23759.15 | -23759.15 | 13486.93 | 3527.96 | 3366.92 | 3377.34 | [9 empty] | 10272.22 | 10272.22
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | AFUDC-Borrowed | 5590030 |  |  |  | 14768.08 | -14768.08 | 11869.71 | 1074.81 | 910.37 | 913.19 | [9 empty] | 2898.37 | 2898.37
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | AFUDC-Equity | 5590031 |  |  |  | 8991.07 | -8991.07 | 1617.22 | 2453.15 | 2456.55 | 2464.15 | [9 empty] | 7373.85 | 7373.85
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 600000 |  |  | 320626.81 | 279373.19 | 321943.44 | -8267.3 | 3069.14 | 3864.12 | 17.41 | [8 empty] | -1316.63 | -1316.63
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 600000 |  |  | 320626.81 | 279373.19 | 321943.44 | -8267.3 | 3069.14 | 3864.12 | 17.41 | [8 empty] | -1316.63 | -1316.63
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 19056.87 | -19056.87 | 18364.13 | -0.75 |  | 676.08 | 17.41 | [8 empty] | 692.74 | 692.74
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 19056.87 | -19056.87 | 18364.13 | -0.75 |  | 676.08 | 17.41 | [8 empty] | 692.74 | 692.74
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 19056.87 | -19056.87 | 18364.13 | -0.75 |  | 676.08 | 17.41 | [8 empty] | 692.74 | 692.74
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 10602.42 | -10602.42 | 9914.96 |  |  | 670.05 | 17.41 | [8 empty] | 687.46 | 687.46
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Type Cost Adjustment | 5590045
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | GAS Activity Charge - Type A | 5590101 |  |  |  | 491.99 | -491.99 | 491.99
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Administration | 6603000 |  |  |  | 1772.85 | -1772.85 | 1772.85
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  |  | 670.05 | [9 empty] | 670.05 | 670.05
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Acquisition - Misc | 6603004 |  |  |  | 31.7 | -31.7 | 31.7
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Analyst Services | 6603005 |  |  |  | 115.65 | -115.65 | 115.65
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 3595.58 | -3595.58 | 3595.58
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Engineering Services | 6603023 |  |  |  | 285 | -285 | 285
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Environmental Services | 6603024 |  |  |  | 345.66 | -345.66 | 345.66
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 83.25 | -83.25 | 65.84 |  |  |  | 17.41 | [8 empty] | 17.41 | 17.41
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 63.39 | -63.39 | 63.39
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Management Services | 6603076 |  |  |  | 1200.69 | -1200.69 | 1200.69
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 395.26 | -395.26 | 395.26
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Administrative Services - OT | 6603150 |  |  |  | 280.71 | -280.71 | 280.71
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Rights - Misc | 6603227 |  |  |  | 30.41 | -30.41 | 30.41
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Project Management Overtime | 6603236 |  |  |  | 358.32 | -358.32 | 358.32
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Account Services | 6603730 |  |  |  | 448.62 | -448.62 | 448.62
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Hours - Straight Time | 6608193 |  |  |  | 433.29 | -433.29 | 433.29
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 8454.45 | -8454.45 | 8449.17 | -0.75 |  | 6.03 | [9 empty] | 5.28 | 5.28
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Estimating-Internal | 6010076 |  |  |  | 7749.18 | -7749.18 | 7749.18
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Mapping | 6010077 |  |  |  | 705.27 | -705.27 | 699.99 | -0.75 |  | 6.03 | [9 empty] | 5.28 | 5.28
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Contract Total | PGE1CONTRACT | 600000 |  |  | 254549.42 | 345450.58 | 264686.43 | -10137.01 | [11 empty] | -10137.01 | -10137.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Consulting | PGE1CONSULTING |  |  |  | 82.95 | -82.95 | 82.95
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 82.95 | -82.95 | 82.95
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 600000 |  |  | 254466.47 | 345533.53 | 264603.48 | -10137.01 | [11 empty] | -10137.01 | -10137.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Contracts | 5490000 | 600000 |  |  | 226939.42 | 373060.58 | 226939.42
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 17240.05 | -17240.05 | 27127.06 | -9887.01 | [11 empty] | -9887.01 | -9887.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Environmental Contract | 5490015 |  |  |  | 8787 | -8787 | 9037 | -250 | [11 empty] | -250 | -250
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Traffic Control Contracts | 5490027 |  |  |  | 1500 | -1500 | 1500
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  |  | 47020.52 | -47020.52 | 38892.88 | 1870.46 | 3069.14 | 3188.04 | [9 empty] | 8127.64 | 8127.64
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  |  | -1372.72 | 1372.72 | -2661.64 |  | 1288.92 | [10 empty] | 1288.92 | 1288.92
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | -1372.72 | 1372.72 | -2661.64 |  | 1288.92 | [10 empty] | 1288.92 | 1288.92
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Permits/Fees | 5501090 |  |  |  | 1288.92 | -1288.92 |  |  | 1288.92 | [10 empty] | 1288.92 | 1288.92
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Acquisition Services | 5501093 |  |  |  | 439.83 | -439.83 | 439.83
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -3101.47 | 3101.47 | -3101.47
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Employee Related | PGE1EMPLREL |  |  |  | 31.98 | -31.98 | 31.98
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 31.98 | -31.98 | 31.98
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Reimbursed Mileage Expense | 5091140 |  |  |  | 31.98 | -31.98 | 31.98
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  |  | 48361.26 | -48361.26 | 41522.54 | 1870.46 | 1780.22 | 3188.04 | [9 empty] | 6838.72 | 6838.72
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 6807.52 | -6807.52 | 6558.87 | -0.28 |  | 248.93 | [9 empty] | 248.65 | 248.65
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 6807.52 | -6807.52 | 6558.87 | -0.28 |  | 248.93 | [9 empty] | 248.65 | 248.65
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 21292.45 | -21292.45 | 20494.24 | -0.88 |  | 799.09 | [9 empty] | 798.21 | 798.21
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 19436.29 | -19436.29 | 18711.18 | -0.8 |  | 725.91 | [9 empty] | 725.11 | 725.11
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 3383.62 | -3383.62 | 3247.61 | -0.15 |  | 136.16 | [9 empty] | 136.01 | 136.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 4412.15 | -4412.15 | 4183.21 | -0.25 |  | 229.19 | [9 empty] | 228.94 | 228.94
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Indirect Labor - Gas | 6010107 |  |  |  | 250.6 | -250.6 | 250.6
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 983.33 | -983.33 | 983.33
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Indirect Labor - Cust Care | 6010110 |  |  |  | 101.38 | -101.38 | 101.38
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Indirect Labor - IT | 6010111 |  |  |  | 179.9 | -179.9 | 179.9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 5632.31 | -5632.31 | 5425.12 | -0.23 |  | 207.42 | [9 empty] | 207.19 | 207.19
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 404 | -404 | 404
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 378.46 | -378.46 | 378.46
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 34.37 | -34.37 | 34.37
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Operation Mgmt & Support - IT | 6010119 |  |  |  | 184.06 | -184.06 | 184.06
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Fleet OH | 6010123 |  |  |  | 3339.14 | -3339.14 | 3339.14
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Fleet OH - Elec | 6010125 |  |  |  | 152.97 | -152.97 |  | -0.17 |  | 153.14 | [9 empty] | 152.97 | 152.97
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 1856.16 | -1856.16 | 1783.06 | -0.08 |  | 73.18 | [9 empty] | 73.1 | 73.1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 1175.54 | -1175.54 | 1128.9 | -0.05 |  | 46.69 | [9 empty] | 46.64 | 46.64
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | IT Device OH | 6010113 |  |  |  | 680.62 | -680.62 | 654.16 | -0.03 |  | 26.49 | [9 empty] | 26.46 | 26.46
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 9876.18 | -9876.18 | 9526.36 | -0.4 |  | 350.22 | [9 empty] | 349.82 | 349.82
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Benefits OH | 6010120 |  |  |  | 7310.03 | -7310.03 | 7052.02 | -0.3 |  | 258.31 | [9 empty] | 258.01 | 258.01
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 2566.15 | -2566.15 | 2474.34 | -0.1 |  | 91.91 | [9 empty] | 91.81 | 91.81
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 10385.11 | -10385.11 | 4943.07 | 1872.02 | 1780.22 | 1789.8 | [9 empty] | 5442.04 | 5442.04
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  |  | 5640.76 | -5640.76 | 4120.71 | 554.76 | 481.35 | 483.94 | [9 empty] | 1520.05 | 1520.05
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 4744.35 | -4744.35 | 822.36 | 1317.26 | 1298.87 | 1305.86 | [9 empty] | 3921.99 | 3921.99
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3201494.39 |  |  | 2706370.01 | 495124.38 | 2706370.01
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3201494.39 |  |  | 2706370.01 | 495124.38 | 2706370.01
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 203955.39 |  |  | 194512.15 | 9443.24 | 194512.15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Activity Types | PGE1ACTVTYPES | 203955.39 |  |  | 194512.15 | 9443.24 | 194512.15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 203955.39 |  |  | 194512.15 | 9443.24 | 194512.15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 13920.39 |  |  | 9676.76 | 4243.63 | 9676.76
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Activity Type Cost Adjustment | 5590045 | -19578 |  |  |  | -19578
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Electric Activity Charge - Type A | 5590100 |  |  |  | -3324.64 | 3324.64 | -3324.64
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Administration | 6603000 | 532.8 |  |  | 1170.21 | -637.41 | 1170.21
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Acquisition - Misc | 6603004 | 1654.02 |  |  | 456.15 | 1197.87 | 456.15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Engineering/Mapping | 6603022 | 7040.85 |  |  | 3342.57 | 3698.28 | 3342.57
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Environmental Services | 6603024 |  |  |  | 49.38 | -49.38 | 49.38
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 65.84 | -65.84 | 65.84
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Management Services | 6603076 |  |  |  | 3602.07 | -3602.07 | 3602.07
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 242.46 | -242.46 | 242.46
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Maintain & Operate Services | 6603083 | 18832.32 |  |  | 1494.41 | 17337.91 | 1494.41
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Field Services | 6603099 | 5438.4 |  |  |  | 5438.4
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Administrative Services - OT | 6603150 |  |  |  | 85.83 | -85.83 | 85.83
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 139.21 | -139.21 | 139.21
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | SCADA Services | 6603671 |  |  |  | 147.12 | -147.12 | 147.12
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Account Services | 6603730 |  |  |  | 1236.86 | -1236.86 | 1236.86
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Hours - Straight Time | 6608193 |  |  |  | 361.11 | -361.11 | 361.11
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Hours - Overtime | 6608194 |  |  |  | 608.18 | -608.18 | 608.18
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 190035 |  |  | 184835.39 | 5199.61 | 184835.39
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Service Planning - Planning Only | 5501163 | 190035 |  |  |  | 190035
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 181736.9 | -181736.9 | 181736.9
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Mapping | 6010077 |  |  |  | 3098.49 | -3098.49 | 3098.49
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material Total | PGE1MATTOTAL | 354808 |  |  | 355906.4 | -1098.4 | 355906.4
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material related expenses | PGE1MATERIAL | 326132 |  |  | 327086.11 | -954.11 | 327086.11
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 1306.8 | -1306.8 | 1306.8
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 2011.62 | -2011.62 | 2011.62
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 93513.86 | -93513.86 | 93513.86
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Electrical Specialties | 5300140 | 326132 |  |  | 43714.87 | 282417.13 | 43714.87
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Gas & Water Specialties | 5300160 |  |  |  | 251.79 | -251.79 | 251.79
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 155028.33 | -155028.33 | 155028.33
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 6846.24 | -6846.24 | 6846.24
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Communication & Signaling Equipment | 5300230 |  |  |  | 2006.19 | -2006.19 | 2006.19
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Transformers, Regulators & Capacitors | 5300260 |  |  |  | 964.72 | -964.72 | 964.72
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 21192.61 | -21192.61 | 21192.61
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 249.08 | -249.08 | 249.08
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material Burden | PGE1MATBURD | 28676 |  |  | 28820.29 | -144.29 | 28820.29
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material Burden - Planning Only | 5501150 | 37497 |  |  |  | 37497
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material Burden Adjustment | 5590076 | -8821 |  |  |  | -8821
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Material Burden | 6010000 |  |  |  | 28820.29 | -28820.29 | 28820.29
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Contract Total | PGE1CONTRACT | 1839403 |  |  | 1776321.91 | 63081.09 | 1776321.91
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1839403 |  |  | 1776321.91 | 63081.09 | 1776321.91
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Contracts | 5490000 | 359968 |  |  | 359968.12 | -0.12 | 359968.12
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Electric Construction Contract | 5490001 | 1361414 |  |  | 1290572.49 | 70841.51 | 1290572.49
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Environmental Contract | 5490015 | 14796 |  |  | 12762.38 | 2033.62 | 12762.38
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Construction Inspection | 5490021 | 103225 |  |  | 113018.92 | -9793.92 | 113018.92
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Traffic Control Contracts | 5490027
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 803328 |  |  | 379629.55 | 423698.45 | 379629.55
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 803328 |  |  | -11768.98 | 815096.98 | -11768.98
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 803328 |  |  | -11768.98 | 815096.98 | -11768.98
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -9946.5 | 9946.5 | -9946.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Permits/Fees | 5501090
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 73.05 | -73.05 | 73.05
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -1895.53 | 1895.53 | -1895.53
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 803328 |  |  |  | 803328
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Contingency-Planned | 5592000
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 4788.84 | -4788.84 | 4788.84
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 262.36 | -262.36 | 262.36
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 262.36 | -262.36 | 262.36
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 4526.48 | -4526.48 | 4526.48
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 4526.48 | -4526.48 | 4526.48
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 386609.69 | -386609.69 | 386609.69
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 36346.52 | -36346.52 | 36346.52
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 36346.52 | -36346.52 | 36346.52
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 216555.03 | -216555.03 | 216555.03
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 196769.94 | -196769.94 | 196769.94
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 33047.43 | -33047.43 | 33047.43
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 68126.9 | -68126.9 | 68126.9
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 620.36 | -620.36 | 620.36
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 261.78 | -261.78 | 261.78
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Indirect Labor - IT | 6010111 |  |  |  | 394 | -394 | 394
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 57799.43 | -57799.43 | 57799.43
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 272.35 | -272.35 | 272.35
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 71.04 | -71.04 | 71.04
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Operation Mgmt & Support - IT | 6010119 |  |  |  | 282.36 | -282.36 | 282.36
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Fleet OH | 6010123 |  |  |  | 35894.29 | -35894.29 | 35894.29
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 19785.09 | -19785.09 | 19785.09
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 13265 | -13265 | 13265
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | IT Device OH | 6010113 |  |  |  | 6520.09 | -6520.09 | 6520.09
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 130631.09 | -130631.09 | 130631.09
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Benefits OH | 6010120 |  |  |  | 78357.27 | -78357.27 | 78357.27
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 26353.4 | -26353.4 | 26353.4
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 25920.42 | -25920.42 | 25920.42
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 3077.05 | -3077.05 | 3077.05
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 3398.29 | -3398.29 | 3398.29
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -321.24 | 321.24 | -321.24
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Billing Credits | PGE1BILLCR
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Billing Credit - CIAC Non Taxable | 5590051
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 725000 |  | 41069.58 | 347704.64 | 377295.36 | 249135.22 | 45821.1 | 9178.19 | 2465.73 | 34.82 | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 57499.84 | 78212.14 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 725000 |  | 41069.58 | 347704.64 | 377295.36 | 249135.22 | 45821.1 | 9178.19 | 2465.73 | 34.82 | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 57499.84 | 78212.14 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  |  |  | 45364.71 | -45364.71 | 44598.12 | 55.69 |  | 676.08 | 34.82 | [8 empty] | 766.59 | 766.59
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  |  |  | 45364.71 | -45364.71 | 44598.12 | 55.69 |  | 676.08 | 34.82 | [8 empty] | 766.59 | 766.59
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 45241.99 | -45241.99 | 44475.4 | 55.69 |  | 676.08 | 34.82 | [8 empty] | 766.59 | 766.59
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 41205.17 | -41205.17 | 40444.61 | 55.69 |  | 670.05 | 34.82 | [8 empty] | 760.56 | 760.56
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | GAS Activity Charge - Type A | 5590101 |  |  |  | 362.52 | -362.52 | 362.52
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Administration | 6603000 |  |  |  | 1264.91 | -1264.91 | 1264.91
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  |  | 670.05 | [9 empty] | 670.05 | 670.05
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Acquisition - Misc | 6603004 |  |  |  | 258.49 | -258.49 | 258.49
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Analyst Services | 6603005 |  |  |  | 274.41 | -274.41 | 218.72 | 55.69 | [11 empty] | 55.69 | 55.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Construction Overtime Services | 6603021 |  |  |  | 1506.56 | -1506.56 | 1506.56
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Engineering/Mapping | 6603022 |  |  |  | 2333.36 | -2333.36 | 2333.36
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Environmental Services | 6603024 |  |  |  | 217.09 | -217.09 | 217.09
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 769.91 | -769.91 | 735.09 |  |  |  | 34.82 | [8 empty] | 34.82 | 34.82
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 24436.87 | -24436.87 | 24436.87
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Management Services | 6603076 |  |  |  | 1753.98 | -1753.98 | 1753.98
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Administrative Services - OT | 6603150 |  |  |  | 6071.46 | -6071.46 | 6071.46
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Rights - Misc | 6603227 |  |  |  | 60.82 | -60.82 | 60.82
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Project Management Overtime | 6603236 |  |  |  | 477.76 | -477.76 | 477.76
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Account Services | 6603730 |  |  |  | 602.93 | -602.93 | 602.93
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Hours - Overtime | 6608194 |  |  |  | 144.05 | -144.05 | 144.05
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 4036.82 | -4036.82 | 4030.79 |  |  | 6.03 | [9 empty] | 6.03 | 6.03
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Estimating-Internal | 6010076 |  |  |  | 3957.7 | -3957.7 | 3957.7
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Mapping | 6010077 |  |  |  | 79.12 | -79.12 | 73.09 |  |  | 6.03 | [9 empty] | 6.03 | 6.03
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Types - Contractors | PGE1ACTV-CONTR |  |  |  | 122.72 | -122.72 | 122.72
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C |  |  |  | 122.72 | -122.72 | 122.72
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Contractor Consultant | 6608158 |  |  |  | 122.72 | -122.72 | 122.72
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Material Total | PGE1MATTOTAL |  |  |  | 82176.15 | -82176.15 | 82176.15
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Material related expenses | PGE1MATERIAL |  |  |  | 87048.35 | -87048.35 | 87048.35
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Materials Not Otherwise Classified | 5300000 |  |  |  | -6831.25 | 6831.25 | -6831.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Construction Supplies | 5300110 |  |  |  | -1389.02 | 1389.02 | -1389.02
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 46589.55 | -46589.55 | 46589.55
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Electrical Specialties | 5300140 |  |  |  | 45433.38 | -45433.38 | 45433.38
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Fuels, Lubricants & Oils | 5300150 |  |  |  | 2712.98 | -2712.98 | 2712.98
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 19.72 | -19.72 | 19.72
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | -6930.71 | 6930.71 | -6930.71
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Electl & Electronic Equipment Component | 5300200 |  |  |  | 2295.84 | -2295.84 | 2295.84
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Measuring Instruments | 5300220 |  |  |  | 974.32 | -974.32 | 974.32
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Communication & Signaling Equipment | 5300230 |  |  |  | 1265.86 | -1265.86 | 1265.86
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Transformers, Regulators & Capacitors | 5300260 |  |  |  | 976.24 | -976.24 | 976.24
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Fabricated Structures | 5300270 |  |  |  | 1861.16 | -1861.16 | 1861.16
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 70.28 | -70.28 | 70.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Material Burden | PGE1MATBURD |  |  |  | -4872.2 | 4872.2 | -4872.2
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Material Burden | 6010000 |  |  |  | -4872.2 | 4872.2 | -4872.2
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Contract Total | PGE1CONTRACT | 725000 |  |  | 82365.12 | 642634.88 | 32260.43 | 44019.23 | 7448 | -1362.54 | [9 empty] | 50104.69 | 50104.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Consulting | PGE1CONSULTING |  |  |  | 52.32 | -52.32 | 52.32
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Consulting Services - Environmental Perm | 5001237 |  |  |  | 52.32 | -52.32 | 52.32
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 725000 |  |  | 82312.8 | 642687.2 | 32208.11 | 44019.23 | 7448 | -1362.54 | [9 empty] | 50104.69 | 50104.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Contracts | 5490000 | 725000 |  |  | 3645.5 | 721354.5 | 3645.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 46006.18 | -46006.18 | 3349.49 | 44019.23 |  | -1362.54 | [9 empty] | 42656.69 | 42656.69
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Environmental Contract | 5490015 |  |  |  | 25213.12 | -25213.12 | 25213.12
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Traffic Control Contracts | 5490027 |  |  |  | 7448 | -7448 |  |  | 7448 | [10 empty] | 7448 | 7448
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER |  |  | 41069.58 | 137798.66 | -137798.66 | 90100.52 | 1746.18 | 1730.19 | 3152.19 |  | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 6628.56 | 27340.86 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Other Cost Elements | PGE1OTHERCE |  |  |  | 943.98 | -943.98 | 943.98
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 943.98 | -943.98 | 943.98
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Acquisition Services | 5501093 |  |  |  | 1472.17 | -1472.17 | 1472.17
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -528.19 | 528.19 | -528.19
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Employee Related | PGE1EMPLREL |  |  |  | 170.54 | -170.54 | 170.54
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 170.54 | -170.54 | 170.54
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Reimbursed Mileage Expense | 5091140 |  |  |  | 170.54 | -170.54 | 170.54
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Overheads | PGE1OVERHEAD |  |  | 41069.58 | 136684.14 | -136684.14 | 88986 | 1746.18 | 1730.19 | 3152.19 |  | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 6628.56 | 27340.86 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Capitalized A&G | PGE1CAPAG |  |  |  | 16941.49 | -16941.49 | 16672.05 | 20.51 |  | 248.93 | [9 empty] | 269.44 | 269.44
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Capitalized A&G | 6010050 |  |  |  | 16941.49 | -16941.49 | 16672.05 | 20.51 |  | 248.93 | [9 empty] | 269.44 | 269.44
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Labor Overheads | PGE1LABOROH |  |  |  | 38855.53 | -38855.53 | 38008.64 | 47.8 |  | 799.09 | [9 empty] | 846.89 | 846.89
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 35223.41 | -35223.41 | 34454.82 | 42.68 |  | 725.91 | [9 empty] | 768.59 | 768.59
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Paid Time Off | 6010100 |  |  |  | 7352.52 | -7352.52 | 7205.14 | 11.22 |  | 136.16 | [9 empty] | 147.38 | 147.38
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Indirect Labor - Electric | 6010106 |  |  |  | 2815.49 | -2815.49 | 2586.3 |  |  | 229.19 | [9 empty] | 229.19 | 229.19
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Indirect Labor - Gas | 6010107 |  |  |  | 96.47 | -96.47 | 96.47
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Indirect Labor - Environmental Land | 6010108 |  |  |  | 11410.33 | -11410.33 | 11390.65 | 19.68 | [11 empty] | 19.68 | 19.68
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Indirect Labor - Cust Care | 6010110 |  |  |  | 134.09 | -134.09 | 134.09
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Indirect Labor - IT | 6010111 |  |  |  | 59.81 | -59.81 | 59.81
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 4677.03 | -4677.03 | 4469.61 |  |  | 207.42 | [9 empty] | 207.42 | 207.42
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 150.84 | -150.84 | 150.84
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 5869.68 | -5869.68 | 5857.9 | 11.78 | [11 empty] | 11.78 | 11.78
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 29.79 | -29.79 | 29.79
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Operation Mgmt & Support - IT | 6010119 |  |  |  | 33.51 | -33.51 | 33.51
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Fleet OH | 6010123 |  |  |  | 2440.71 | -2440.71 | 2440.71
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Fleet OH - Elec | 6010125 |  |  |  | 153.14 | -153.14 |  |  |  | 153.14 | [9 empty] | 153.14 | 153.14
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 3632.12 | -3632.12 | 3553.82 | 5.12 |  | 73.18 | [9 empty] | 78.3 | 78.3
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Building Service Overhead | 6010112 |  |  |  | 2322.44 | -2322.44 | 2272.48 | 3.27 |  | 46.69 | [9 empty] | 49.96 | 49.96
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | IT Device OH | 6010113 |  |  |  | 1309.68 | -1309.68 | 1281.34 | 1.85 |  | 26.49 | [9 empty] | 28.34 | 28.34
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Other Overhead | PGE1OTHEROH |  |  |  | 20802.76 | -20802.76 | 20427.01 | 25.53 |  | 350.22 | [9 empty] | 375.75 | 375.75
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Benefits OH | 6010120 |  |  |  | 14609.63 | -14609.63 | 14332.24 | 19.08 |  | 258.31 | [9 empty] | 277.39 | 277.39
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Payroll Taxes OH | 6010121 |  |  |  | 5038.98 | -5038.98 | 4940.62 | 6.45 |  | 91.91 | [9 empty] | 98.36 | 98.36
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Minor Material OH | 6010122 |  |  |  | 1154.15 | -1154.15 | 1154.15
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR |  |  | 41069.58 | 60084.36 | -60084.36 | 13878.3 | 1652.34 | 1730.19 | 1753.95 |  | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 5136.48 | 25848.78 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | AFUDC-Borrowed | 5590030 |  |  | 41069.58 | 56529.54 | -56529.54 | 14018.24 | 499.66 | 467.82 | 474.24 |  | 2552.4 | 2552.4 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 2601.25 | 1441.72 | 22154.02 | 20357.28
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | AFUDC-Equity | 5590031 |  |  |  | 3554.82 | -3554.82 | -139.94 | 1152.68 | 1262.37 | 1279.71 | [9 empty] | 3694.76 | 3694.76
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Order Financial Costs | PGE1ORDFIN | 3559342.68 |  |  | 3103351.2 | 455991.48 | 3069330.35 | -59587.45 | 80652.78 | 13738.36 | -782.84 | [8 empty] | 34020.85 | 34020.85
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3559342.68 |  |  | 3103351.2 | 455991.48 | 3069330.35 | -59587.45 | 80652.78 | 13738.36 | -782.84 | [8 empty] | 34020.85 | 34020.85
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Activity Type Total | PGE1ACTV-TOT | 406941.68 |  |  | 153483.54 | 253458.14 | 153072.3 | -229.33 | 263.87 | 376.7 | [9 empty] | 411.24 | 411.24
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Activity Types | PGE1ACTVTYPES | 406941.68 |  |  | 153483.54 | 253458.14 | 153072.3 | -229.33 | 263.87 | 376.7 | [9 empty] | 411.24 | 411.24
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Activity Types - Internal | PGE1ACTV-INT | 406941.68 |  |  | 153483.54 | 253458.14 | 153072.3 | -229.33 | 263.87 | 376.7 | [9 empty] | 411.24 | 411.24
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 406941.68 |  |  | 18384.21 | 388557.47 | 17937.51 |  | 74.45 | 372.25 | [9 empty] | 446.7 | 446.7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Electric Activity Charge - Type A | 5590100 |  |  |  | 516.98 | -516.98 | 516.98
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Internal Services - Budget | 5600000 | 399452 |  |  |  | 399452
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Administration | 6603000 | 1019.25 |  |  | 2807.14 | -1787.89 | 2807.14
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Engineering/Mapping | 6603022 | 2654.11 |  |  | 3084.32 | -430.21 | 2637.62 |  | 74.45 | 372.25 | [9 empty] | 446.7 | 446.7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Environmental Services | 6603024 | 203.85 |  |  | 197.52 | 6.33 | 197.52
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Environmental Planning & Permitting-Misc | 6603027 | 407.7 |  |  | 698.31 | -290.61 | 698.31
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Switching Operator Service | 6603068 |  |  |  | 578.11 | -578.11 | 578.11
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Management Services | 6603076 |  |  |  | 1200.69 | -1200.69 | 1200.69
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Maintain & Operate Overtime Services | 6603082 |  |  |  | 464.38 | -464.38 | 464.38
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Maintain & Operate Services | 6603083 | 1449.6 |  |  | 2174.59 | -724.99 | 2174.59
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Field Services Overtime | 6603098 |  |  |  | 99.4 | -99.4 | 99.4
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Field Services | 6603099 | 1504.33 |  |  | 228.31 | 1276.02 | 228.31
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Maint & Operate Doubletime Services | 6603181 |  |  |  | 2976.83 | -2976.83 | 2976.83
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Field Services Doubletime | 6603184 |  |  |  | 1263.72 | -1263.72 | 1263.72
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Switching Operation Svcs. - Overtime | 6603222 |  |  |  | 869.19 | -869.19 | 869.19
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Switching Oprn Svcs. - Doubletime | 6603223 |  |  |  | 664.39 | -664.39 | 664.39
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Land Rights - Misc | 6603227 | 63.75 |  |  | 379.08 | -315.33 | 379.08
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Account Services | 6603730 | 119.14 |  |  | 115.41 | 3.73 | 115.41
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Manage L&EM | 6603823 | 67.95 |  |  | 65.84 | 2.11 | 65.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 135099.33 | -135099.33 | 135134.79 | -229.33 | 189.42 | 4.45 | [9 empty] | -35.46 | -35.46
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Estimating-Internal | 6010076 |  |  |  | 130327.98 | -130327.98 | 130327.98
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Mapping | 6010077 |  |  |  | 4771.35 | -4771.35 | 4806.81 | -229.33 | 189.42 | 4.45 | [9 empty] | -35.46 | -35.46
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Material Total | PGE1MATTOTAL | 159431 |  |  | 292855.97 | -133424.97 | 292855.97
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Material related expenses | PGE1MATERIAL | 159431 |  |  | 255535.68 | -96104.68 | 255535.68
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Materials Not Otherwise Classified | 5300000 |  |  |  | 6412.1 | -6412.1 | 6412.1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Construction Supplies | 5300110 |  |  |  | 3716.96 | -3716.96 | 3716.96
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 90959.26 | -90959.26 | 90959.26
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Electrical Specialties | 5300140 | 159431 |  |  | 7006.7 | 152424.3 | 7006.7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 131618.47 | -131618.47 | 131618.47
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Electl & Electronic Equipment Component | 5300200 |  |  |  | 6846.29 | -6846.29 | 6846.29
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Fabricated Structures | 5300270 |  |  |  | 8677.51 | -8677.51 | 8677.51
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 298.39 | -298.39 | 298.39
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Material Burden | PGE1MATBURD |  |  |  | 37320.29 | -37320.29 | 37320.29
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Material Burden | 6010000 |  |  |  | 37320.29 | -37320.29 | 37320.29
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Contract Total | PGE1CONTRACT | 2177037 |  |  | 2228124.96 | -51087.96 | 2240728.62 | -76445.87 | 63140.77 | 1484.28 | -782.84 | [8 empty] | -12603.66 | -12603.66
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Consulting | PGE1CONSULTING | 5000 |  |  | 413.37 | 4586.63 | 370.32 |  | 43.05 | 32.84 | -32.84 | [8 empty] | 43.05 | 43.05
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Consulting Services - Engineering | 5001230 |  |  |  | 413.37 | -413.37 | 370.32 |  | 43.05 | 32.84 | -32.84 | [8 empty] | 43.05 | 43.05
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Consulting Services - Environmental Perm | 5001237 | 5000 |  |  |  | 5000
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Other Contract | PGE1OTHCONTRAC | 2172037 |  |  | 2227711.59 | -55674.59 | 2240358.3 | -76445.87 | 63097.72 | 1451.44 | -750 | [8 empty] | -12646.71 | -12646.71
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Contracts | 5490000 | 415764 |  |  | 484842.3 | -69078.3 | 421842.3 |  | 63000 | [10 empty] | 63000 | 63000
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Electric Construction Contract | 5490001 | 1256250 |  |  | 562722.53 | 693527.47 | 639560.43 | -76837.9 | [11 empty] | -76837.9 | -76837.9
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Gas Construction Contract | 5490002 |  |  |  | 634431.6 | -634431.6 | 634431.6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 400000 |  |  | 155266.42 | 244733.58 | 155266.42
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Environmental Contract | 5490015 | 24648 |  |  | 22427.36 | 2220.64 | 21236.17 | 392.03 | 97.72 | 1451.44 | -750 | [8 empty] | 1191.19 | 1191.19
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Construction Inspection | 5490021 | 75375 |  |  | 60957.5 | 14417.5 | 60957.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Helicopter Contract | 6608176 |  |  |  | 307063.88 | -307063.88 | 307063.88
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Order Other Costs | PGE1ORD-OTHER | 815933 |  |  | 428886.73 | 387046.27 | 382673.46 | 17087.75 | 17248.14 | 11877.38 | [9 empty] | 46213.27 | 46213.27
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Other Cost Elements | PGE1OTHERCE | 815388 |  |  | -69281.64 | 884669.64 | -63515.15 |  |  | -5766.49 | [9 empty] | -5766.49 | -5766.49
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 815388 |  |  | -69281.64 | 884669.64 | -63515.15 |  |  | -5766.49 | [9 empty] | -5766.49 | -5766.49
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Cash Discount earned | 5006310 |  |  |  | -5766.49 | 5766.49 |  |  |  | -5766.49 | [9 empty] | -5766.49 | -5766.49
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Permits/Fees | 5501090 | 320175 |  |  |  | 320175
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Land Acquisition Services | 5501093 | 213 |  |  | 799.61 | -586.61 | 799.61
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 495000 |  |  | -64314.76 | 559314.76 | -64314.76
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Employee Related | PGE1EMPLREL | 72 |  |  | 131.3 | -59.3 | 131.3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Travel / Lodging | PGE1TRVL-LODGE | 50 |  |  | 109.23 | -59.23 | 109.23
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Reimbursed Mileage Expense | 5091140 | 50 |  |  | 109.23 | -59.23 | 109.23
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Meals | PGE1MEALS-EXP | 22 |  |  | 22.07 | -0.07 | 22.07
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Meals Expense | 5091100 | 22 |  |  | 22.07 | -0.07 | 22.07
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Order Overheads | PGE1OVERHEAD | 473 |  |  | 498037.07 | -497564.07 | 446057.31 | 17087.75 | 17248.14 | 17643.87 | [9 empty] | 51979.76 | 51979.76
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Capitalized A&G | PGE1CAPAG |  |  |  | 58338.15 | -58338.15 | 58186.74 | -84.44 | 97.15 | 138.7 | [9 empty] | 151.41 | 151.41
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Capitalized A&G | 6010050 |  |  |  | 58338.15 | -58338.15 | 58186.74 | -84.44 | 97.15 | 138.7 | [9 empty] | 151.41 | 151.41
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Labor Overheads | PGE1LABOROH |  |  |  | 194106.81 | -194106.81 | 193620.75 | -271.06 | 311.87 | 445.25 | [9 empty] | 486.06 | 486.06
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 175860.02 | -175860.02 | 175418.46 | -246.22 | 283.31 | 404.47 | [9 empty] | 441.56 | 441.56
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Paid Time Off | 6010100 |  |  |  | 30655.43 | -30655.43 | 30572.61 | -46.18 | 53.13 | 75.87 | [9 empty] | 82.82 | 82.82
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Indirect Labor - Electric | 6010106 |  |  |  | 48562.11 | -48562.11 | 48422.7 | -77.74 | 89.45 | 127.7 | [9 empty] | 139.41 | 139.41
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1517.28 | -1517.28 | 1517.28
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Indirect Labor - Cust Care | 6010110 |  |  |  | 40.73 | -40.73 | 40.73
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 59300.98 | -59300.98 | 59174.8 | -70.36 | 80.96 | 115.58 | [9 empty] | 126.18 | 126.18
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 642.86 | -642.86 | 642.86
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 17.2 | -17.2 | 17.2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Fleet OH | 6010123 |  |  |  | 35030.28 | -35030.28 | 35030.28
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Fleet OH - Elec | 6010125 |  |  |  | 93.15 | -93.15 |  | -51.94 | 59.77 | 85.32 | [9 empty] | 93.15 | 93.15
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 18246.79 | -18246.79 | 18202.29 | -24.84 | 28.56 | 40.78 | [9 empty] | 44.5 | 44.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Building Service Overhead | 6010112 |  |  |  | 11044.43 | -11044.43 | 11016.04 | -15.84 | 18.21 | 26.02 | [9 empty] | 28.39 | 28.39
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | IT Device OH | 6010113 |  |  |  | 7202.36 | -7202.36 | 7186.25 | -9 | 10.35 | 14.76 | [9 empty] | 16.11 | 16.11
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Other Overhead | PGE1OTHEROH |  |  |  | 126317.65 | -126317.65 | 126103.96 | -123.46 | 142.03 | 195.12 | [9 empty] | 213.69 | 213.69
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Benefits OH | 6010120 |  |  |  | 75441.03 | -75441.03 | 75283.23 | -92.28 | 106.17 | 143.91 | [9 empty] | 157.8 | 157.8
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Payroll Taxes OH | 6010121 |  |  |  | 25246.45 | -25246.45 | 25190.56 | -31.18 | 35.86 | 51.21 | [9 empty] | 55.89 | 55.89
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Minor Material OH | 6010122 |  |  |  | 25630.17 | -25630.17 | 25630.17
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | AFUDC Costs | PGE1AFUDCDIR | 473 |  |  | 119274.46 | -118801.46 | 68145.86 | 17566.71 | 16697.09 | 16864.8 | [9 empty] | 51128.6 | 51128.6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | AFUDC-Borrowed | 5590030 |  |  |  | 75471.69 | -75471.69 | 61039.29 | 5357.73 | 4514.66 | 4560.01 | [9 empty] | 14432.4 | 14432.4
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | AFUDC-Equity | 5590031 | 473 |  |  | 43802.77 | -43329.77 | 7106.57 | 12208.98 | 12182.43 | 12304.79 | [9 empty] | 36696.2 | 36696.2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Financial Costs | PGE1ORDFIN | 3459498 |  | 1000232 | 3313894.14 | 145603.86 | 2040317.39 | 20400.28 | 30760.85 | 234881.72 | -12698.1 |  |  |  |  | 500000 | 500232 |  |  | 273344.75 | 1273576.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3459498 |  | 1000232 | 3313894.14 | 145603.86 | 2040317.39 | 20400.28 | 30760.85 | 234881.72 | -12698.1 |  |  |  |  | 500000 | 500232 |  |  | 273344.75 | 1273576.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 385550 |  |  | 399363.75 | -13813.75 | 330278.02 | 1468.22 | 5812.1 | 58943.89 | 2861.52 | [8 empty] | 69085.73 | 69085.73
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Types | PGE1ACTVTYPES | 385550 |  |  | 399363.75 | -13813.75 | 330278.02 | 1468.22 | 5812.1 | 58943.89 | 2861.52 | [8 empty] | 69085.73 | 69085.73
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 385550 |  |  | 399363.75 | -13813.75 | 330278.02 | 1468.22 | 5812.1 | 58943.89 | 2861.52 | [8 empty] | 69085.73 | 69085.73
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 385550 |  |  | 336300 | 49250 | 267820.64 | 1458.84 | 5772.24 | 58386.76 | 2861.52 | [8 empty] | 68479.36 | 68479.36
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Internal Services - Budget | 5600000 | 385550 |  |  |  | 385550
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Administration | 6603000 |  |  |  | 4915.81 | -4915.81 | 4706.89 |  | 139.28 | 69.64 | [9 empty] | 208.92 | 208.92
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction | 6603001 |  |  |  | 257508.02 | -257508.02 | 213451.52 | 1042.3 | 3553.4 | 36780.6 | 2680.2 | [8 empty] | 44056.5 | 44056.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Acquisition - Misc | 6603004 |  |  |  | 4251.36 | -4251.36 | 4056.96 |  |  | 194.4 | [9 empty] | 194.4 | 194.4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 31125.4 | -31125.4 | 21215.32 |  | 133.86 | 9776.22 | [9 empty] | 9910.08 | 9910.08
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Engineering/Mapping | 6603022 |  |  |  | 8613.33 | -8613.33 | 7572.42 |  | 74.45 | 854.78 | 111.68 | [8 empty] | 1040.91 | 1040.91
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Engineering Services | 6603023
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 2778.27 | -2778.27 | 2308.2 | 174.1 |  | 226.33 | 69.64 | [8 empty] | 470.07 | 470.07
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 855.78 | -855.78 | 855.78
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Management Services | 6603076 |  |  |  | 3364.54 | -3364.54 | 3008.34 |  |  | 356.2 | [9 empty] | 356.2 | 356.2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Maintain & Operate Overtime Services | 6603082 |  |  |  | 1782.78 | -1782.78 | 1112.5 | 54.08 | 508.04 | 108.16 | [9 empty] | 670.28 | 670.28
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Maintain & Operate Services | 6603083 |  |  |  | 2236.72 | -2236.72 | 1245.98 | 57.1 | 753.94 | 179.7 | [9 empty] | 990.74 | 990.74
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 102.46 | -102.46 | 102.46
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Administrative Services - OT | 6603150 |  |  |  | 303.27 | -303.27 | 107.65 |  |  | 195.62 | [9 empty] | 195.62 | 195.62
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction Doubletime Services | 6603180 |  |  |  | 14848.44 | -14848.44 | 5616.4 |  |  | 9232.04 | [9 empty] | 9232.04 | 9232.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Maint & Operate Doubletime Services | 6603181 |  |  |  | 1473.79 | -1473.79 | 994.69 |  | 262.92 | 216.18 | [9 empty] | 479.1 | 479.1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | SCADA Services | 6603671 |  |  |  | 280.72 | -280.72 |  |  | 280.72 | [10 empty] | 280.72 | 280.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Account Services | 6603730 |  |  |  | 1450.27 | -1450.27 | 1056.49 | 131.26 | 65.63 | 196.89 | [9 empty] | 393.78 | 393.78
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Manage L&EM | 6603823 |  |  |  | 164.48 | -164.48 | 164.48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Hours - Straight Time | 6608193 |  |  |  | 244.56 | -244.56 | 244.56
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 63063.75 | -63063.75 | 62457.38 | 9.38 | 39.86 | 557.13 | [9 empty] | 606.37 | 606.37
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 59297.06 | -59297.06 | 59297.06
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Mapping | 6010077 |  |  |  | 3766.69 | -3766.69 | 3160.32 | 9.38 | 39.86 | 557.13 | [9 empty] | 606.37 | 606.37
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Material Total | PGE1MATTOTAL | 283112 |  |  | 394164 | -111052 | 384397.13 |  | 8443.07 | 1323.8 | [9 empty] | 9766.87 | 9766.87
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Material related expenses | PGE1MATERIAL | 283112 |  |  | 344727.12 | -61615.12 | 336204.54 |  | 7367.43 | 1155.15 | [9 empty] | 8522.58 | 8522.58
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Materials Not Otherwise Classified | 5300000 |  |  |  | 3034.52 | -3034.52 | 3034.52
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction Supplies | 5300110 |  |  |  | 6641.43 | -6641.43 | 6641.43
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 119777.24 | -119777.24 | 118622.09 |  |  | 1155.15 | [9 empty] | 1155.15 | 1155.15
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Electrical Specialties | 5300140 | 283112 |  |  | 39769.3 | 243342.7 | 39769.3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 139365.82 | -139365.82 | 139365.82
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Electl & Electronic Equipment Component | 5300200 |  |  |  | 17638.68 | -17638.68 | 10271.25 |  | 7367.43 | [10 empty] | 7367.43 | 7367.43
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Transformers, Regulators & Capacitors | 5300260 |  |  |  | 242.77 | -242.77 | 242.77
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 17246.91 | -17246.91 | 17246.91
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Tools, First Aid & Safety Supplies | 5300280 |  |  |  | 1007.33 | -1007.33 | 1007.33
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 3.12 | -3.12 | 3.12
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 49436.88 | -49436.88 | 48192.59 |  | 1075.64 | 168.65 | [9 empty] | 1244.29 | 1244.29
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Material Burden | 6010000 |  |  |  | 49436.88 | -49436.88 | 48192.59 |  | 1075.64 | 168.65 | [9 empty] | 1244.29 | 1244.29
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Contract Total | PGE1CONTRACT | 1286815 |  |  | 623132.61 | 663682.39 | 571392.83 | 15768.66 | 3540.76 | 48091.1 | -15660.74 | [8 empty] | 51739.78 | 51739.78
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 84.49 | -84.49 | 60.74 |  |  | 23.75 | [9 empty] | 23.75 | 23.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Consulting Services - Engineering | 5001230 |  |  |  | 23.75 | -23.75 |  |  |  | 23.75 | [9 empty] | 23.75 | 23.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Consulting Services - Computer | 5001240 |  |  |  | 60.74 | -60.74 | 60.74
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Contract | PGE1OTHCONTRAC | 1286815 |  |  | 623048.12 | 663766.88 | 571332.09 | 15768.66 | 3540.76 | 48067.35 | -15660.74 | [8 empty] | 51716.03 | 51716.03
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Contracts | 5490000 | 1200198 |  |  | 325065.27 | 875132.73 | 320263.65 |  |  | 4801.62 | [9 empty] | 4801.62 | 4801.62
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Electric Construction Contract | 5490001 |  |  |  | 66545.37 | -66545.37 | 54943.77 |  | 2452.72 | 12809.62 | -3660.74 | [8 empty] | 11601.6 | 11601.6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 71661.55 | -71661.55 | 56832.89 | 14828.66 | [11 empty] | 14828.66 | 14828.66
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Environmental Contract | 5490015 | 6617 |  |  | 22880.08 | -16263.08 | 22858.04 |  | -227.96 | 250 | [9 empty] | 22.04 | 22.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction Inspection | 5490021 |  |  |  | 457.11 | -457.11 |  |  |  | 457.11 | [9 empty] | 457.11 | 457.11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Traffic Control Contracts | 5490027 | 80000 |  |  | 136438.74 | -56438.74 | 116433.74 | 940 | 1316 | 29749 | -12000 | [8 empty] | 20005 | 20005
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 1504021 |  | 1000232 | 1897233.78 | -393212.78 | 754249.41 | 3163.4 | 12964.92 | 126522.93 | 101.12 |  |  |  |  | 500000 | 500232 |  |  | 142752.37 | 1142984.37
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Cost Elements | PGE1OTHERCE | 1503523 |  | 1000232 | 979297.55 | 524225.45 | -26172.77 | -18.8 |  | 5156 | 101.12 |  |  |  |  | 500000 | 500232 |  |  | 5238.32 | 1005470.32
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1503523 |  | 1000232 | 979297.55 | 524225.45 | -26172.77 | -18.8 |  | 5156 | 101.12 |  |  |  |  | 500000 | 500232 |  |  | 5238.32 | 1005470.32
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -4287.05 | 4287.05 | -4145.65 | -18.8 |  | -94 | -28.6 | [8 empty] | -141.4 | -141.4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Rents | 5007000 | 20000 |  |  |  | 20000
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Vehicle Lease | 5010503 |  |  |  | 10.95 | -10.95 | 10.95
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Permits/Fees | 5501090 | 1481699 |  |  | 2687.16 | 1479011.84 | 2557.44 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Acquisition Services | 5501093 | 1824 |  |  | 2684.02 | -860.02 | 2684.02
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Postage | 5510010 |  |  |  | 31 | -31 | 31
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1000232 | 970339.11 | -970339.11 | -29892.89 | [8 empty] | 500000 | 500232 |  |  |  | 1000232
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Expenses | 5591000 |  |  |  | 2582.36 | -2582.36 | 2582.36
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Employee Related | PGE1EMPLREL |  |  |  | 64.03 | -64.03 | 64.03
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 64.03 | -64.03 | 64.03
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Reimbursed Mileage Expense | 5091140 |  |  |  | 64.03 | -64.03 | 64.03
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Overheads | PGE1OVERHEAD | 498 |  |  | 917872.2 | -917374.2 | 780358.15 | 3182.2 | 12964.92 | 121366.93 | [9 empty] | 137514.05 | 137514.05
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 145435.19 | -145435.19 | 121051.44 | 540.59 | 2140.02 | 21703.14 | [9 empty] | 24383.75 | 24383.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 145435.19 | -145435.19 | 121051.44 | 540.59 | 2140.02 | 21703.14 | [9 empty] | 24383.75 | 24383.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 475062.92 | -475062.92 | 397504.33 | 1594.35 | 6838.36 | 69125.88 | [9 empty] | 77558.59 | 77558.59
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 431887.68 | -431887.68 | 361523.98 | 1442.39 | 6157.39 | 62763.92 | [9 empty] | 70363.7 | 70363.7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Paid Time Off | 6010100 |  |  |  | 87127.83 | -87127.83 | 73861.99 | 295.7 | 1170.57 | 11799.57 | [9 empty] | 13265.84 | 13265.84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 130635.57 | -130635.57 | 108778.59 | 394.21 | 1900.84 | 19561.93 | [9 empty] | 21856.98 | 21856.98
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - Gas | 6010107
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 4840.34 | -4840.34 | 4487.26 | 61.51 | 49.21 | 242.36 | [9 empty] | 353.08 | 353.08
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 346.03 | -346.03 | 244.09 | 33.98 | 16.99 | 50.97 | [9 empty] | 101.94 | 101.94
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - IT | 6010111 |  |  |  | 92.83 | -92.83 | 92.83
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 125353.02 | -125353.02 | 105462.84 | 356.77 | 1720.29 | 17813.12 | [9 empty] | 19890.18 | 19890.18
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operation Mgmt & Support - Gas | 6010115
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 2073.44 | -2073.44 | 1861.98 | 36.84 | 29.47 | 145.15 | [9 empty] | 211.46 | 211.46
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operation Mgmt & Support - IT | 6010119 |  |  |  | 39.42 | -39.42 | 39.42
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Fleet OH | 6010123 |  |  |  | 66694.98 | -66694.98 | 66694.98
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 14684.22 | -14684.22 |  | 263.38 | 1270.02 | 13150.82 | [9 empty] | 14684.22 | 14684.22
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Fleet OH - Gas | 6010126
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 43175.24 | -43175.24 | 35980.35 | 151.96 | 680.97 | 6361.96 | [9 empty] | 7194.89 | 7194.89
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 26750.2 | -26750.2 | 22160.35 | 96.94 | 434.41 | 4058.5 | [9 empty] | 4589.85 | 4589.85
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | IT Device OH | 6010113 |  |  |  | 16425.04 | -16425.04 | 13820 | 55.02 | 246.56 | 2303.46 | [9 empty] | 2605.04 | 2605.04
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 259683.09 | -259683.09 | 224403.1 | 755.54 | 3986.54 | 30537.91 | [9 empty] | 35279.99 | 35279.99
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Benefits OH | 6010120 |  |  |  | 170792.24 | -170792.24 | 145241.9 | 564.74 | 2531.07 | 22454.53 | [9 empty] | 25550.34 | 25550.34
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 57508.9 | -57508.9 | 48473.67 | 190.8 | 855.17 | 7989.26 | [9 empty] | 9035.23 | 9035.23
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Minor Material OH | 6010122 |  |  |  | 31381.95 | -31381.95 | 30687.53 |  | 600.3 | 94.12 | [9 empty] | 694.42 | 694.42
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | AFUDC Costs | PGE1AFUDCDIR | 498 |  |  | 37691 | -37193 | 37399.28 | 291.72 | [11 empty] | 291.72 | 291.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 36504.95 | -36504.95 | 36213.23 | 291.72 | [11 empty] | 291.72 | 291.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | AFUDC-Equity | 5590031 | 498 |  |  | 1186.05 | -688.05 | 1186.05
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Financial Costs | PGE1ORDFIN | 3890027.76 |  | 1718409 | 3396318.82 | 493708.94 | 1480324.78 | 24395.47 | 110421.4 | 75425.33 | -12657.16 |  |  |  |  | 500000 | 500000 | 718409 |  | 197585.04 | 1915994.04
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3890027.76 |  | 1718409 | 3396318.82 | 493708.94 | 1480324.78 | 24395.47 | 110421.4 | 75425.33 | -12657.16 |  |  |  |  | 500000 | 500000 | 718409 |  | 197585.04 | 1915994.04
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 691364.76 |  |  | 173840.4 | 517524.36 | 115792.62 | 4031.94 | 32157.04 | 13669.21 | 8189.59 | [8 empty] | 58047.78 | 58047.78
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Types | PGE1ACTVTYPES | 691364.76 |  |  | 173840.4 | 517524.36 | 115792.62 | 4031.94 | 32157.04 | 13669.21 | 8189.59 | [8 empty] | 58047.78 | 58047.78
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 691364.76 |  |  | 173840.4 | 517524.36 | 115792.62 | 4031.94 | 32157.04 | 13669.21 | 8189.59 | [8 empty] | 58047.78 | 58047.78
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 691364.76 |  |  | 126266.51 | 565098.25 | 68669 | 3997.88 | 31867.95 | 13542.09 | 8189.59 | [8 empty] | 57597.51 | 57597.51
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Internal Services - Budget | 5600000 | 293727 |  |  |  | 293727
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Administration | 6603000 | 2038.5 |  |  | 1478.63 | 559.87 | 1408.99 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Construction | 6603001 | 369553.25 |  |  | 103266.56 | 266286.69 | 53900.94 | 3407 | 29981.6 | 10571.22 | 5405.8 | [8 empty] | 49365.62 | 49365.62
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Acquisition - Misc | 6603004 | 1848.75 |  |  | 237.72 | 1611.03 | 237.72
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 6785.37 | -6785.37 | 1966.69 | 223.1 | 1383.22 | 535.44 | 2676.92 | [8 empty] | 4818.68 | 4818.68
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Engineering/Mapping | 6603022 | 14679.84 |  |  | 3881.09 | 10798.75 | 3121.8 |  | 306.24 | 415.82 | 37.23 | [8 empty] | 759.29 | 759.29
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Engineering Services | 6603023
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 679.5 |  |  | 293.17 | 386.33 | 84.25 |  |  | 139.28 | 69.64 | [8 empty] | 208.92 | 208.92
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 316.96 | -316.96 | 316.96
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Management Services | 6603076 | 5347.31 |  |  | 3314.13 | 2033.18 | 3271.83 | 42.3 | [11 empty] | 42.3 | 42.3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Maintain & Operate Overtime Services | 6603082 |  |  |  | 236.93 | -236.93 |  |  |  | 236.93 | [9 empty] | 236.93 | 236.93
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Maintain & Operate Services | 6603083 |  |  |  | 717.48 | -717.48 |  |  |  | 717.48 | [9 empty] | 717.48 | 717.48
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Engineering/Mapping Services Overtime | 6603106 | 372.1 |  |  | 468.81 | -96.71 | 468.81
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Administrative Services - OT | 6603150 |  |  |  | 315.42 | -315.42 | 315.42
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Rights - Misc | 6603227 | 63.75 |  |  | 921.28 | -857.53 | 824.08 |  |  | 97.2 | [9 empty] | 97.2 | 97.2
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electric Estimating | 6603466 |  |  |  | 509.83 | -509.83 | 509.83
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electric Estimating Overtime | 6603467 |  |  |  | 256.54 | -256.54 | 255.48 | 1.06 | [11 empty] | 1.06 | 1.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Account Services | 6603730 | 3054.76 |  |  | 2623.15 | 431.61 | 1918.81 | 244.93 | 196.89 | 262.52 | [9 empty] | 704.34 | 704.34
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Manage L&EM | 6603823 |  |  |  | 67.39 | -67.39 | 67.39
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Analyst Svcs Overtime | 6603855 |  |  |  | 79.49 | -79.49 |  | 79.49 | [11 empty] | 79.49 | 79.49
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Hours - Straight Time | 6608193 |  |  |  | 496.56 | -496.56 |  |  |  | 496.56 | [9 empty] | 496.56 | 496.56
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 47573.89 | -47573.89 | 47123.62 | 34.06 | 289.09 | 127.12 | [9 empty] | 450.27 | 450.27
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 44668.04 | -44668.04 | 44668.04
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Mapping | 6010077 |  |  |  | 2905.85 | -2905.85 | 2455.58 | 34.06 | 289.09 | 127.12 | [9 empty] | 450.27 | 450.27
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Total | PGE1MATTOTAL | 332127 |  |  | 244733.84 | 87393.16 | 233303.87 | 2285.27 | 21.26 | 9123.44 | [9 empty] | 11429.97 | 11429.97
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material related expenses | PGE1MATERIAL | 332127 |  |  | 214427.33 | 117699.67 | 204305.18 | 1994.13 | 18.55 | 8109.47 | [9 empty] | 10122.15 | 10122.15
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Materials Not Otherwise Classified | 5300000 |  |  |  | 1597.2 | -1597.2 | 1597.2
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Construction Supplies | 5300110 |  |  |  | 1291.29 | -1291.29 | 1291.29
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 42405.42 | -42405.42 | 42405.42
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electrical Specialties | 5300140 | 332127 |  |  | 37241.9 | 294885.1 | 32101.84 |  |  | 5140.06 | [9 empty] | 5140.06 | 5140.06
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Gas & Water Specialties | 5300160 |  |  |  | 132.35 | -132.35 | 132.35
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 114889.87 | -114889.87 | 111157.91 | 1994.13 | 18.55 | 1719.28 | [9 empty] | 3731.96 | 3731.96
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electl & Electronic Equipment Component | 5300200 |  |  |  | 36.45 | -36.45 | 36.45
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Communication & Signaling Equipment | 5300230 |  |  |  | 1857.26 | -1857.26 | 607.13 |  |  | 1250.13 | [9 empty] | 1250.13 | 1250.13
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Transformers, Regulators & Capacitors | 5300260 |  |  |  | 2451.82 | -2451.82 | 2451.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 12375.47 | -12375.47 | 12375.47
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 148.3 | -148.3 | 148.3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 30306.51 | -30306.51 | 28998.69 | 291.14 | 2.71 | 1013.97 | [9 empty] | 1307.82 | 1307.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Burden | 6010000 |  |  |  | 30306.51 | -30306.51 | 28998.69 | 291.14 | 2.71 | 1013.97 | [9 empty] | 1307.82 | 1307.82
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Contract Total | PGE1CONTRACT | 1019050 |  |  | 807233.12 | 211816.88 | 816291.02 | 464.81 | 2271.03 | 9053.01 | -20846.75 | [8 empty] | -9057.9 | -9057.9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 52.31 | -52.31 | 52.31
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 52.31 | -52.31 | 52.31
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Contract | PGE1OTHCONTRAC | 1019050 |  |  | 807180.81 | 211869.19 | 816238.71 | 464.81 | 2271.03 | 9053.01 | -20846.75 | [8 empty] | -9057.9 | -9057.9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Contracts | 5490000 | 599550 |  |  | 720483.3 | -120933.3 | 739457.46 |  |  |  | -18974.16 | [8 empty] | -18974.16 | -18974.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electric Construction Contract | 5490001 | 369500 |  |  | 14302.42 | 355197.58 | 8494.57 |  | 1200 | 5087.85 | -480 | [8 empty] | 5807.85 | 5807.85
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 40284.47 | -40284.47 | 40284.47
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Environmental Contract | 5490015 | 20000 |  |  | 32110.62 | -12110.62 | 28002.21 | 464.81 | 1071.03 | 3965.16 | -1392.59 | [8 empty] | 4108.41 | 4108.41
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Traffic Control Contracts | 5490027 | 30000 |  |  |  | 30000
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 1847486 |  | 1718409 | 2170511.46 | -323025.46 | 314937.27 | 17613.45 | 75972.07 | 43579.67 | [5 empty] | 500000 | 500000 | 718409 |  | 137165.19 | 1855574.19
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Cost Elements | PGE1OTHERCE | 1847413 |  | 1718409 | 1747485.77 | 99927.23 | 23734.17 | 129.72 | -37.12 | 5250 | [5 empty] | 500000 | 500000 | 718409 |  | 5342.6 | 1723751.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1847413 |  | 1718409 | 1747485.77 | 99927.23 | 23734.17 | 129.72 | -37.12 | 5250 | [5 empty] | 500000 | 500000 | 718409 |  | 5342.6 | 1723751.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -1446.32 | 1446.32 | -1409.2 |  | -37.12 | [10 empty] | -37.12 | -37.12
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Permits/Fees | 5501090 | 1816980 |  |  | 648.6 | 1816331.4 | 518.88 | 129.72 | [11 empty] | 129.72 | 129.72
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Permits/Fees - Environmental | 5501091 |  |  |  | 199.67 | -199.67 | 199.67
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Acquisition Services | 5501093 | 433 |  |  | 1074.1 | -641.1 | 1074.1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Land Fees | 5501094 | 30000 |  |  | 35250 | -5250 | 30000 |  |  | 5250 | [9 empty] | 5250 | 5250
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Postage | 5510010 |  |  |  | 46.4 | -46.4 | 46.4
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1718409 | 1711713.32 | -1711713.32 | -6695.68 | [8 empty] | 500000 | 500000 | 718409 |  |  | 1718409
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Employee Related | PGE1EMPLREL | 73 |  |  | 144.36 | -71.36 | 144.36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Travel / Lodging | PGE1TRVL-LODGE | 59 |  |  | 130.53 | -71.53 | 130.53
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Reimbursed Mileage Expense | 5091140 | 59 |  |  | 130.53 | -71.53 | 130.53
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Meals | PGE1MEALS-EXP | 14 |  |  | 13.83 | 0.17 | 13.83
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Meals Expense | 5091100 | 14 |  |  | 13.83 | 0.17 | 13.83
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 422881.33 | -422881.33 | 291058.74 | 17483.73 | 76009.19 | 38329.67 | [9 empty] | 131822.59 | 131822.59
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 62948.74 | -62948.74 | 44590.98 | 1484.55 | 11840.22 | 5032.99 | [9 empty] | 18357.76 | 18357.76
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 62948.74 | -62948.74 | 44590.98 | 1484.55 | 11840.22 | 5032.99 | [9 empty] | 18357.76 | 18357.76
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 196724.97 | -196724.97 | 138400.62 | 4549.17 | 37881 | 15894.18 | [9 empty] | 58324.35 | 58324.35
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 178924.18 | -178924.18 | 126031.7 | 4108.99 | 34406.23 | 14377.26 | [9 empty] | 52892.48 | 52892.48
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Paid Time Off | 6010100 |  |  |  | 34450.54 | -34450.54 | 24417.61 | 803.51 | 6476.43 | 2752.99 | [9 empty] | 10032.93 | 10032.93
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 53028.25 | -53028.25 | 36797.22 | 1242.51 | 10834.49 | 4154.03 | [9 empty] | 16231.03 | 16231.03
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - Gas | 6010107 |  |  |  | 126.71 | -126.71 |  |  |  | 126.71 | [9 empty] | 126.71 | 126.71
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1326.96 | -1326.96 | 1190.73 | 28.08 |  | 108.15 | [9 empty] | 136.23 | 136.23
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 665.98 | -665.98 | 483.63 | 63.41 | 50.97 | 67.97 | [9 empty] | 182.35 | 182.35
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - IT | 6010111 |  |  |  | 185.22 | -185.22 |  |  |  | 185.22 | [9 empty] | 185.22 | 185.22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 54579.45 | -54579.45 | 39890.12 | 1124.49 | 9805.37 | 3759.47 | [9 empty] | 14689.33 | 14689.33
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 194.3 | -194.3 |  |  |  | 194.3 | [9 empty] | 194.3 | 194.3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 575.84 | -575.84 | 494.24 | 16.82 |  | 64.78 | [9 empty] | 81.6 | 81.6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 9.16 | -9.16 | 9.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - IT | 6010119 |  |  |  | 79.7 | -79.7 |  |  |  | 79.7 | [9 empty] | 79.7 | 79.7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Fleet OH | 6010123 |  |  |  | 22748.99 | -22748.99 | 22748.99
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 10844.62 | -10844.62 |  | 830.17 | 7238.97 | 2775.48 | [9 empty] | 10844.62 | 10844.62
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Fleet OH - Gas | 6010126 |  |  |  | 108.46 | -108.46 |  |  |  | 108.46 | [9 empty] | 108.46 | 108.46
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 17800.79 | -17800.79 | 12368.92 | 440.18 | 3474.77 | 1516.92 | [9 empty] | 5431.87 | 5431.87
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 11472.29 | -11472.29 | 8007.13 | 280.81 | 2216.66 | 967.69 | [9 empty] | 3465.16 | 3465.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | IT Device OH | 6010113 |  |  |  | 6328.5 | -6328.5 | 4361.79 | 159.37 | 1258.11 | 549.23 | [9 empty] | 1966.71 | 1966.71
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 106783.55 | -106783.55 | 79243.9 | 2351.3 | 17280.6 | 7907.75 | [9 empty] | 27539.65 | 27539.65
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Benefits OH | 6010120 |  |  |  | 67598.92 | -67598.92 | 47693.24 | 1636.06 | 12915.53 | 5354.09 | [9 empty] | 19905.68 | 19905.68
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 23697.02 | -23697.02 | 16875.73 | 552.76 | 4363.56 | 1904.97 | [9 empty] | 6821.29 | 6821.29
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Minor Material OH | 6010122 |  |  |  | 15487.61 | -15487.61 | 14674.93 | 162.48 | 1.51 | 648.69 | [9 empty] | 812.68 | 812.68
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 56424.07 | -56424.07 | 28823.24 | 9098.71 | 9007.37 | 9494.75 | [9 empty] | 27600.83 | 27600.83
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 32359.53 | -32359.53 | 24581.99 | 2774.82 | 2435.47 | 2567.25 | [9 empty] | 7777.54 | 7777.54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 24064.54 | -24064.54 | 4241.25 | 6323.89 | 6571.9 | 6927.5 | [9 empty] | 19823.29 | 19823.29
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3189967.04 |  | 75000 | 2053630.53 | 1136336.51 | 1978641.48 |  |  | -10.95 | [8 empty] | 75000 | -10.95 | 74989.05
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3376573.04 |  | 75000 | 2053630.53 | 1322942.51 | 1978641.48 |  |  | -10.95 | [8 empty] | 75000 | -10.95 | 74989.05
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 207310.04 |  |  | 135240.04 | 72070 | 135240.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Activity Types | PGE1ACTVTYPES | 207310.04 |  |  | 135240.04 | 72070 | 135240.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 207310.04 |  |  | 135240.04 | 72070 | 135240.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 207310.04 |  |  | 10485.68 | 196824.36 | 10485.68
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Internal Services - Budget | 5600000 | 200914 |  |  |  | 200914
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Administration | 6603000 | 3130.2 |  |  | 1595.66 | 1534.54 | 1595.66
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Acquisition - Misc | 6603004 | 122.52 |  |  | 91.23 | 31.29 | 91.23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Project Management Services | 6603013 |  |  |  | 114.46 | -114.46 | 114.46
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 470.8 | -470.8 | 470.8
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Engineering/Mapping | 6603022 | 68.49 |  |  | 2815.35 | -2746.86 | 2815.35
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Environmental Services | 6603024 |  |  |  | 82.3 | -82.3 | 82.3
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 133.2 |  |  | 131.68 | 1.52 | 131.68
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059 | 61.26 |  |  | 30.42 | 30.84 | 30.42
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Management Services | 6603076 |  |  |  | 2267.97 | -2267.97 | 2267.97
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Maintain & Operate Services | 6603083 |  |  |  | 279.04 | -279.04 | 279.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Vegetation Management - Misc | 6603097 | 1899.06 |  |  | 121.64 | 1777.42 | 121.64
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 102.46 | -102.46 | 102.46
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Administrative Services - OT | 6603150 | 66.6 |  |  | 93.57 | -26.97 | 93.57
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 278.42 | -278.42 | 278.42
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Account Services | 6603730 | 728.38 |  |  | 1810.7 | -1082.32 | 1810.7
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Hours - Straight Time | 6608193 | 186.33 |  |  | 199.98 | -13.65 | 199.98
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 124754.36 | -124754.36 | 124754.36
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 121192.26 | -121192.26 | 121192.26
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Mapping | 6010077 |  |  |  | 3562.1 | -3562.1 | 3562.1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Material Total | PGE1MATTOTAL | 118141 |  |  | 71989.58 | 46151.42 | 71972.38 |  |  | 17.2 | [9 empty] | 17.2 | 17.2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Material related expenses | PGE1MATERIAL | 118141 |  |  | 65397.36 | 52743.64 | 65382.35 |  |  | 15.01 | [9 empty] | 15.01 | 15.01
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Materials Not Otherwise Classified | 5300000 | 201 |  |  | 201.18 | -0.18 | 201.18
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Construction Supplies | 5300110 | 90 |  |  | 89.52 | 0.48 | 89.52
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 | 797 |  |  | 14417.43 | -13620.43 | 14417.43
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Electrical Specialties | 5300140 | 114626 |  |  | 23.27 | 114602.73 | 23.27
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 1836.06 | -1836.06 | 1836.06
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 | 2315 |  |  | 48718.04 | -46403.04 | 48703.03 |  |  | 15.01 | [9 empty] | 15.01 | 15.01
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Electl & Electronic Equipment Component | 5300200 | 6 |  |  | 6.22 | -0.22 | 6.22
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 | 106 |  |  | 105.64 | 0.36 | 105.64
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 6592.22 | -6592.22 | 6590.03 |  |  | 2.19 | [9 empty] | 2.19 | 2.19
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Material Burden | 6010000 |  |  |  | 6592.22 | -6592.22 | 6590.03 |  |  | 2.19 | [9 empty] | 2.19 | 2.19
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Contract Total | PGE1CONTRACT | 2419114 |  |  | 1521870.22 | 897243.78 | 1521870.22
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Consulting | PGE1CONSULTING | 35000 |  |  | 170.75 | 34829.25 | 170.75
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Consulting Services - Engineering | 5001230 |  |  |  | 88.72 | -88.72 | 88.72
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 35000 |  |  | 82.03 | 34917.97 | 82.03
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 2384114 |  |  | 1521699.47 | 862414.53 | 1521699.47
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Contracts | 5490000 | 903131 |  |  | 125326.71 | 777804.29 | 125326.71
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Electric Construction Contract | 5490001 | 1269786 |  |  | 1153164.89 | 116621.11 | 1153164.89
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 133824 |  |  | 105475.07 | 28348.93 | 105475.07
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Environmental Contract | 5490015 | 1185 |  |  | 39483.86 | -38298.86 | 39483.86
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Construction Inspection | 5490021 | 76188 |  |  | 46077.33 | 30110.67 | 46077.33
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Helicopter Contract | 6608176 |  |  |  | 52171.61 | -52171.61 | 52171.61
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 632008 |  | 75000 | 324530.69 | 307477.31 | 249558.84 |  |  | -28.15 | [8 empty] | 75000 | -28.15 | 74971.85
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 632008 |  | 75000 | 14951.5 | 617056.5 | -60018.46 |  |  | -30.04 | [8 empty] | 75000 | -30.04 | 74969.96
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 632008 |  | 75000 | 14951.5 | 617056.5 | -60018.46 |  |  | -30.04 | [8 empty] | 75000 | -30.04 | 74969.96
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Cash Discount earned | 5006310 | -581 |  |  | -1813.84 | 1232.84 | -1783.8 |  |  | -30.04 | [9 empty] | -30.04 | -30.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Permits/Fees | 5501090 | 632589 |  |  |  | 632589
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 633.13 | -633.13 | 633.13
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Postage | 5510010 |  |  |  | 2 | -2 | 2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 75000 | 18700.77 | -18700.77 | -56299.23 | [11 empty] | 75000 |  | 75000
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Contingency-Planned | 5592000
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 4.15 | -4.15 | 4.15
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 309575.04 | -309575.04 | 309573.15 |  |  | 1.89 | [9 empty] | 1.89 | 1.89
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 50527.72 | -50527.72 | 50527.72
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 50527.72 | -50527.72 | 50527.72
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 170685.16 | -170685.16 | 170685.05 |  |  | 0.11 | [9 empty] | 0.11 | 0.11
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 156052.54 | -156052.54 | 156052.54
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 22428.84 | -22428.84 | 22428.84
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 39429.9 | -39429.9 | 39429.9
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 744.13 | -744.13 | 744.13
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 382.59 | -382.59 | 382.59
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Indirect Labor - IT | 6010111 |  |  |  | 83.03 | -83.03 | 83.03
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 59627.61 | -59627.61 | 59627.61
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 333.42 | -333.42 | 333.42
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 113.86 | -113.86 | 113.86
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Operation Mgmt & Support - IT | 6010119 |  |  |  | 46.52 | -46.52 | 46.52
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Fleet OH | 6010123 |  |  |  | 32862.64 | -32862.64 | 32862.64
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 14632.62 | -14632.62 | 14632.51 |  |  | 0.11 | [9 empty] | 0.11 | 0.11
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 8942.28 | -8942.28 | 8942.21 |  |  | 0.07 | [9 empty] | 0.07 | 0.07
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | IT Device OH | 6010113 |  |  |  | 5690.34 | -5690.34 | 5690.3 |  |  | 0.04 | [9 empty] | 0.04 | 0.04
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 87780.01 | -87780.01 | 87778.23 |  |  | 1.78 | [9 empty] | 1.78 | 1.78
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Benefits OH | 6010120 |  |  |  | 61032.39 | -61032.39 | 61031.99 |  |  | 0.4 | [9 empty] | 0.4 | 0.4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 20553.54 | -20553.54 | 20553.39 |  |  | 0.15 | [9 empty] | 0.15 | 0.15
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 6194.08 | -6194.08 | 6192.85 |  |  | 1.23 | [9 empty] | 1.23 | 1.23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 582.15 | -582.15 | 582.15
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 663.74 | -663.74 | 663.74
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -81.59 | 81.59 | -81.59
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE | -186606 |  |  |  | -186606
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Billing Credits | PGE1BILLCR | -186606 |  |  |  | -186606
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -186606 |  |  |  | -186606
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 900000 |  |  | 617113.95 | 282886.05 | 529344.32 | 80634.05 | 3532.97 | 3532.97 | 69.64 | [8 empty] | 87769.63 | 87769.63
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 900000 |  |  | 617113.95 | 282886.05 | 529344.32 | 80634.05 | 3532.97 | 3532.97 | 69.64 | [8 empty] | 87769.63 | 87769.63
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 30641.28 | -30641.28 | 30571.64 |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 30641.28 | -30641.28 | 30571.64 |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 30641.28 | -30641.28 | 30571.64 |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 11077.3 | -11077.3 | 11007.66 |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | GAS Activity Charge - Type A | 5590101 |  |  |  | 51.79 | -51.79 | 51.79
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Administration | 6603000 |  |  |  | 1126.26 | -1126.26 | 1126.26
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Acquisition - Misc | 6603004 |  |  |  | 77.32 | -77.32 | 77.32
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Construction Overtime Services | 6603021 |  |  |  | 1035.76 | -1035.76 | 1035.76
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 2215.56 | -2215.56 | 2215.56
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Environmental Services | 6603024 |  |  |  | 131.68 | -131.68 | 131.68
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 69.64 | -69.64 |  |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 3042.72 | -3042.72 | 3042.72
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Management Services | 6603076 |  |  |  | 1220.34 | -1220.34 | 1220.34
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 204.92 | -204.92 | 204.92
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Administrative Services - OT | 6603150 |  |  |  | 430.6 | -430.6 | 430.6
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Rights - Misc | 6603227 |  |  |  | 30.41 | -30.41 | 30.41
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Account Services | 6603730 |  |  |  | 1440.3 | -1440.3 | 1440.3
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 19563.98 | -19563.98 | 19563.98
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Estimating-Internal | 6010076 |  |  |  | 18467.03 | -18467.03 | 18467.03
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Mapping | 6010077 |  |  |  | 1096.95 | -1096.95 | 1096.95
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Contract Total | PGE1CONTRACT | 900000 |  |  | 508768.56 | 391231.44 | 431594.48 | 77174.08 | [11 empty] | 77174.08 | 77174.08
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Consulting | PGE1CONSULTING |  |  |  | 83.07 | -83.07 | 83.07
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 83.07 | -83.07 | 83.07
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 900000 |  |  | 508685.49 | 391314.51 | 431511.41 | 77174.08 | [11 empty] | 77174.08 | 77174.08
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Contracts | 5490000 | 900000 |  |  | 399815.8 | 500184.2 | 399815.8
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 105874.6 | -105874.6 | 28700.52 | 77174.08 | [11 empty] | 77174.08 | 77174.08
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Environmental Contract | 5490015 |  |  |  | 2995.09 | -2995.09 | 2995.09
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  |  | 77704.11 | -77704.11 | 67178.2 | 3459.97 | 3532.97 | 3532.97 | [9 empty] | 10525.91 | 10525.91
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  |  | -7021.26 | 7021.26 | -7021.26
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | -7021.26 | 7021.26 | -7021.26
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Permits/Fees | 5501090 |  |  |  | 271.55 | -271.55 | 271.55
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Acquisition Services | 5501093 |  |  |  | 1576.1 | -1576.1 | 1576.1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -8868.91 | 8868.91 | -8868.91
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Employee Related | PGE1EMPLREL |  |  |  | 106.81 | -106.81 | 106.81
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 106.81 | -106.81 | 106.81
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Reimbursed Mileage Expense | 5091140 |  |  |  | 106.81 | -106.81 | 106.81
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  |  | 84618.56 | -84618.56 | 74092.65 | 3459.97 | 3532.97 | 3532.97 | [9 empty] | 10525.91 | 10525.91
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 11200.71 | -11200.71 | 11200.71
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 11200.71 | -11200.71 | 11200.71
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 34906.74 | -34906.74 | 34906.74
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 31852.65 | -31852.65 | 31852.65
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 6017.88 | -6017.88 | 6017.88
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 7452.97 | -7452.97 | 7452.97
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Indirect Labor - Gas | 6010107 |  |  |  | 13.78 | -13.78 | 13.78
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1800.35 | -1800.35 | 1800.35
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Indirect Labor - Cust Care | 6010110 |  |  |  | 318.09 | -318.09 | 318.09
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 9745.83 | -9745.83 | 9745.83
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 21.55 | -21.55 | 21.55
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 682.2 | -682.2 | 682.2
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 89.36 | -89.36 | 89.36
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Fleet OH | 6010123 |  |  |  | 5710.64 | -5710.64 | 5710.64
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 3054.09 | -3054.09 | 3054.09
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 1880.95 | -1880.95 | 1880.95
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | IT Device OH | 6010113 |  |  |  | 1173.14 | -1173.14 | 1173.14
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 16962.81 | -16962.81 | 16962.81
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Benefits OH | 6010120 |  |  |  | 12673.6 | -12673.6 | 12673.6
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 4289.21 | -4289.21 | 4289.21
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 21548.3 | -21548.3 | 11022.39 | 3459.97 | 3532.97 | 3532.97 | [9 empty] | 10525.91 | 10525.91
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  |  | 12594.59 | -12594.59 | 9637.79 | 1046.26 | 955.27 | 955.27 | [9 empty] | 2956.8 | 2956.8
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 8953.71 | -8953.71 | 1384.6 | 2413.71 | 2577.7 | 2577.7 | [9 empty] | 7569.11 | 7569.11
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Order Financial Costs | PGE1ORDFIN | 2785685.86 |  |  | 1945492.6 | 840193.26 | 1943877.83 | 504.63 | 605.55 | 504.59 | [9 empty] | 1614.77 | 1614.77
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2986293.86 |  |  | 1945492.6 | 1040801.26 | 1943877.83 | 504.63 | 605.55 | 504.59 | [9 empty] | 1614.77 | 1614.77
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Activity Type Total | PGE1ACTV-TOT | 20244.86 |  |  | 83289.61 | -63044.75 | 83284.81 | 1.5 | 1.8 | 1.5 | [9 empty] | 4.8 | 4.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Activity Types | PGE1ACTVTYPES | 20244.86 |  |  | 83289.61 | -63044.75 | 83284.81 | 1.5 | 1.8 | 1.5 | [9 empty] | 4.8 | 4.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Activity Types - Internal | PGE1ACTV-INT | 20244.86 |  |  | 83289.61 | -63044.75 | 83284.81 | 1.5 | 1.8 | 1.5 | [9 empty] | 4.8 | 4.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 20244.86 |  |  | 2106.51 | 18138.35 | 2106.51
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Activity Type Cost Adjustment | 5590045
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Electric Activity Charge - Type A | 5590100 |  |  |  | -4242.08 | 4242.08 | -4242.08
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Administration | 6603000 | 1265.4 |  |  | 829.2 | 436.2 | 829.2
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Project Management Services | 6603013 |  |  |  | 114.46 | -114.46 | 114.46
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Construction Overtime Services | 6603021 | 619.11 |  |  | 847.44 | -228.33 | 847.44
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Engineering/Mapping | 6603022 | 5931.36 |  |  | 2042.76 | 3888.6 | 2042.76
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Environmental Services | 6603024 |  |  |  | 115.22 | -115.22 | 115.22
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Environmental Planning & Permitting-Misc | 6603027 | 66.6 |  |  | 164.6 | -98 | 164.6
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Management Services | 6603076 |  |  |  | 37.05 | -37.05 | 37.05
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Maintain & Operate Overtime Services | 6603082 |  |  |  | 22.83 | -22.83 | 22.83
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Maintain & Operate Services | 6603083 | 8048 |  |  | 75.49 | 7972.51 | 75.49
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Field Services | 6603099 | 4120 |  |  |  | 4120
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Engineering/Mapping Services Overtime | 6603106 | 71.35 |  |  | 102.46 | -31.11 | 102.46
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Account Services | 6603730 | 123.04 |  |  | 1997.08 | -1874.04 | 1997.08
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 81183.1 | -81183.1 | 81178.3 | 1.5 | 1.8 | 1.5 | [9 empty] | 4.8 | 4.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Estimating-Internal | 6010076 |  |  |  | 77095.5 | -77095.5 | 77095.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Mapping | 6010077 |  |  |  | 4087.6 | -4087.6 | 4082.8 | 1.5 | 1.8 | 1.5 | [9 empty] | 4.8 | 4.8
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Material Total | PGE1MATTOTAL | 559536 |  |  | 185531.06 | 374004.94 | 185531.06
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Material related expenses | PGE1MATERIAL | 559536 |  |  | 171131.43 | 388404.57 | 171131.43
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Materials Not Otherwise Classified | 5300000 |  |  |  | 1653.33 | -1653.33 | 1653.33
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Construction Supplies | 5300110 |  |  |  | 773.45 | -773.45 | 773.45
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 45810.99 | -45810.99 | 45810.99
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Electrical Specialties | 5300140 | 559536 |  |  | 17977.13 | 541558.87 | 17977.13
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 30.04 | -30.04 | 30.04
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 92251.94 | -92251.94 | 92251.94
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Electl & Electronic Equipment Component | 5300200 |  |  |  | 107.07 | -107.07 | 107.07
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Fabricated Structures | 5300270 |  |  |  | 12394.26 | -12394.26 | 12394.26
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 133.22 | -133.22 | 133.22
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Material Burden | PGE1MATBURD |  |  |  | 14399.63 | -14399.63 | 14399.63
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Material Burden | 6010000 |  |  |  | 14399.63 | -14399.63 | 14399.63
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Contract Total | PGE1CONTRACT | 1860616 |  |  | 1540385.79 | 320230.21 | 1538785.79 | 500 | 600 | 500 | [9 empty] | 1600 | 1600
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Consulting | PGE1CONSULTING |  |  |  | 227.07 | -227.07 | 227.07
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Consulting Services - Environmental Perm | 5001237 |  |  |  | 227.07 | -227.07 | 227.07
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Other Contract | PGE1OTHCONTRAC | 1860616 |  |  | 1540158.72 | 320457.28 | 1538558.72 | 500 | 600 | 500 | [9 empty] | 1600 | 1600
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Contracts | 5490000 | 412000 |  |  | 97846.19 | 314153.81 | 97846.19
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Electric Construction Contract | 5490001 | 1366616 |  |  | 1325718.11 | 40897.89 | 1325718.11
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Environmental Contract | 5490015 |  |  |  | 65946.31 | -65946.31 | 64346.31 | 500 | 600 | 500 | [9 empty] | 1600 | 1600
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Construction Inspection | 5490021 | 82000 |  |  | 46018.84 | 35981.16 | 46018.84
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Paving Contracts | 5490500 |  |  |  | 4629.27 | -4629.27 | 4629.27
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Order Other Costs | PGE1ORD-OTHER | 545897 |  |  | 136286.14 | 409610.86 | 136276.17 | 3.13 | 3.75 | 3.09 | [9 empty] | 9.97 | 9.97
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Other Cost Elements | PGE1OTHERCE | 545897 |  |  | -2273.49 | 548170.49 | -2273.49
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 545897 |  |  | -2273.49 | 548170.49 | -2273.49
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Cash Discount earned | 5006310 |  |  |  | -3681.34 | 3681.34 | -3681.34
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Rents | 5007000 | 3500 |  |  |  | 3500
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Permits/Fees | 5501090 | 542397 |  |  |  | 542397
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Land Acquisition Services | 5501093 |  |  |  | 1002.16 | -1002.16 | 1002.16
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Postage | 5510010 |  |  |  | 405.69 | -405.69 | 405.69
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Employee Related | PGE1EMPLREL |  |  |  | 9768.15 | -9768.15 | 9768.15
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 9764 | -9764 | 9764
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Other Employee Related Expense | 5091200 |  |  |  | 9764 | -9764 | 9764
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Order Overheads | PGE1OVERHEAD |  |  |  | 128791.48 | -128791.48 | 128781.51 | 3.13 | 3.75 | 3.09 | [9 empty] | 9.97 | 9.97
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Capitalized A&G | PGE1CAPAG |  |  |  | -5177.56 | 5177.56 | -5179.32 | 0.55 | 0.66 | 0.55 | [9 empty] | 1.76 | 1.76
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Capitalized A&G | 6010050 |  |  |  | -5177.56 | 5177.56 | -5179.32 | 0.55 | 0.66 | 0.55 | [9 empty] | 1.76 | 1.76
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Labor Overheads | PGE1LABOROH |  |  |  | 75079.22 | -75079.22 | 75073.56 | 1.77 | 2.12 | 1.77 | [9 empty] | 5.66 | 5.66
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 66569.63 | -66569.63 | 66564.48 | 1.61 | 1.93 | 1.61 | [9 empty] | 5.15 | 5.15
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Paid Time Off | 6010100 |  |  |  | 17894.57 | -17894.57 | 17893.61 | 0.3 | 0.36 | 0.3 | [9 empty] | 0.96 | 0.96
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Indirect Labor - Electric | 6010106 |  |  |  | 33015.02 | -33015.02 | 33013.39 | 0.51 | 0.61 | 0.51 | [9 empty] | 1.63 | 1.63
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Indirect Labor - Environmental Land | 6010108 |  |  |  | 387.24 | -387.24 | 387.24
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Indirect Labor - Cust Care | 6010110 |  |  |  | 445.73 | -445.73 | 445.73
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 5931.64 | -5931.64 | 5930.17 | 0.46 | 0.55 | 0.46 | [9 empty] | 1.47 | 1.47
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 165.2 | -165.2 | 165.2
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 133.22 | -133.22 | 133.22
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Fleet OH | 6010123 |  |  |  | 8595.92 | -8595.92 | 8595.92
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Fleet OH - Elec | 6010125 |  |  |  | 1.09 | -1.09 |  | 0.34 | 0.41 | 0.34 | [9 empty] | 1.09 | 1.09
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 8509.59 | -8509.59 | 8509.08 | 0.16 | 0.19 | 0.16 | [9 empty] | 0.51 | 0.51
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Building Service Overhead | 6010112 |  |  |  | 5757.95 | -5757.95 | 5757.63 | 0.1 | 0.12 | 0.1 | [9 empty] | 0.32 | 0.32
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | IT Device OH | 6010113 |  |  |  | 2751.64 | -2751.64 | 2751.45 | 0.06 | 0.07 | 0.06 | [9 empty] | 0.19 | 0.19
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Other Overhead | PGE1OTHEROH |  |  |  | 55114.84 | -55114.84 | 55112.29 | 0.81 | 0.97 | 0.77 | [9 empty] | 2.55 | 2.55
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Benefits OH | 6010120 |  |  |  | 33626.65 | -33626.65 | 33624.74 | 0.61 | 0.73 | 0.57 | [9 empty] | 1.91 | 1.91
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Payroll Taxes OH | 6010121 |  |  |  | 9231.73 | -9231.73 | 9231.09 | 0.2 | 0.24 | 0.2 | [9 empty] | 0.64 | 0.64
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Minor Material OH | 6010122 |  |  |  | 12256.46 | -12256.46 | 12256.46
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 3774.98 | -3774.98 | 3774.98
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | AFUDC-Borrowed | 5590030 |  |  |  | 4372.47 | -4372.47 | 4372.47
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | AFUDC-Equity | 5590031 |  |  |  | -597.49 | 597.49 | -597.49
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Billing Credits and Reimbursements | PGE1REIMBURSE | -200608 |  |  |  | -200608
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Billing Credits | PGE1BILLCR | -200608 |  |  |  | -200608
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -200608 |  |  |  | -200608
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3151028.81 |  |  | 2621459.58 | 529569.23 | 2621459.58
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3347930.81 |  |  | 2621459.58 | 726471.23 | 2621459.58
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 137466.81 |  |  | 347694.16 | -210227.35 | 347694.16
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Activity Types | PGE1ACTVTYPES | 137466.81 |  |  | 347694.16 | -210227.35 | 347694.16
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 137466.81 |  |  | 347694.16 | -210227.35 | 347694.16
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 137466.81 |  |  | 6913.51 | 130553.3 | 6913.51
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Internal Services - Budget | 5600000 | 118750 |  |  |  | 118750
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Administration | 6603000 | 199.8 |  |  | 725.02 | -525.22 | 725.02
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 564.96 | -564.96 | 564.96
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Engineering/Mapping | 6603022 | 4545.28 |  |  | 1417.92 | 3127.36 | 1417.92
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Environmental Services | 6603024 |  |  |  | 16.46 | -16.46 | 16.46
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 65.84 | -65.84 | 65.84
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059 | 61.26 |  |  | 30.41 | 30.85 | 30.41
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Management Services | 6603076 |  |  |  | 2267.97 | -2267.97 | 2267.97
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Maintain & Operate Services | 6603083 | 9657.6 |  |  | 374.31 | 9283.29 | 374.31
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Field Services | 6603099 | 4120 |  |  |  | 4120
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Engineering/Mapping Services Overtime | 6603106 | 71.35 |  |  | 102.46 | -31.11 | 102.46
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Account Services | 6603730 | 61.52 |  |  | 1348.16 | -1286.64 | 1348.16
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 340780.65 | -340780.65 | 340780.65
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 341185.88 | -341185.88 | 341185.88
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Mapping | 6010077 |  |  |  | -405.23 | 405.23 | -405.23
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Material Total | PGE1MATTOTAL | 595899 |  |  | 137122.68 | 458776.32 | 137122.68
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Material related expenses | PGE1MATERIAL | 595899 |  |  | 125502.06 | 470396.94 | 125502.06
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 1601.84 | -1601.84 | 1601.84
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 822.23 | -822.23 | 822.23
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 29939.14 | -29939.14 | 29939.14
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Electrical Specialties | 5300140 | 595899 |  |  | 23101.11 | 572797.89 | 23101.11
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 72130.68 | -72130.68 | 72130.68
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 64.12 | -64.12 | 64.12
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | -2300.56 | 2300.56 | -2300.56
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 143.5 | -143.5 | 143.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 11620.62 | -11620.62 | 11620.62
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Material Burden | 6010000 |  |  |  | 11620.62 | -11620.62 | 11620.62
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Contract Total | PGE1CONTRACT | 1873636 |  |  | 1358194.69 | 515441.31 | 1358194.69
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Consulting | PGE1CONSULTING |  |  |  | 51.28 | -51.28 | 51.28
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Consulting Services - Environmental Perm | 5001237 |  |  |  | 51.28 | -51.28 | 51.28
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1873636 |  |  | 1358143.41 | 515492.59 | 1358143.41
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Contracts | 5490000 | 450000 |  |  | 185987.54 | 264012.46 | 185987.54
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Electric Construction Contract | 5490001 | 1343052 |  |  | 1127010.86 | 216041.14 | 1127010.86
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Environmental Contract | 5490015 |  |  |  | 10500.65 | -10500.65 | 10500.65
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Construction Inspection | 5490021 | 80584 |  |  | 34644.36 | 45939.64 | 34644.36
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 740929 |  |  | 778448.05 | -37519.05 | 778448.05
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 740929 |  |  | -3209.2 | 744138.2 | -3209.2
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 740929 |  |  | -3209.2 | 744138.2 | -3209.2
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -3814.29 | 3814.29 | -3814.29
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Permits/Fees | 5501090 | 440929 |  |  |  | 440929
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 605.09 | -605.09 | 605.09
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 300000 |  |  |  | 300000
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Contingency-Planned | 5592000
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 9832.97 | -9832.97 | 9832.97
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 9828.82 | -9828.82 | 9828.82
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 9828.82 | -9828.82 | 9828.82
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 771824.28 | -771824.28 | 771824.28
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 127073.79 | -127073.79 | 127073.79
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 127073.79 | -127073.79 | 127073.79
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 448163.03 | -448163.03 | 448163.03
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 416406.63 | -416406.63 | 416406.63
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 42731.82 | -42731.82 | 42731.82
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 108706.72 | -108706.72 | 108706.72
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 321.49 | -321.49 | 321.49
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 324.11 | -324.11 | 324.11
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 182610.19 | -182610.19 | 182610.19
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 113.25 | -113.25 | 113.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 68.75 | -68.75 | 68.75
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Fleet OH | 6010123 |  |  |  | 81530.3 | -81530.3 | 81530.3
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 31756.4 | -31756.4 | 31756.4
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 21666.31 | -21666.31 | 21666.31
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | IT Device OH | 6010113 |  |  |  | 10090.09 | -10090.09 | 10090.09
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 182754.74 | -182754.74 | 182754.74
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Benefits OH | 6010120 |  |  |  | 124162.05 | -124162.05 | 124162.05
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 49404.19 | -49404.19 | 49404.19
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 9188.5 | -9188.5 | 9188.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 13832.72 | -13832.72 | 13832.72
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 15538.08 | -15538.08 | 15538.08
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1705.36 | 1705.36 | -1705.36
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE | -196902 |  |  |  | -196902
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Billing Credits | PGE1BILLCR | -196902 |  |  |  | -196902
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -196902 |  |  |  | -196902
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 4499650.65 |  | 75000 | 3861637.1 | 638013.55 | 3786591.22 |  |  | 5030.88 | -4985 | [7 empty] | 75000 | 45.88 | 75045.88
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4499650.65 |  | 75000 | 3861637.1 | 638013.55 | 3786591.22 |  |  | 5030.88 | -4985 | [7 empty] | 75000 | 45.88 | 75045.88
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 288283.65 |  |  | 232900.92 | 55382.73 | 232885.96 |  |  | 14.96 | [9 empty] | 14.96 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Activity Types | PGE1ACTVTYPES | 288283.65 |  |  | 232900.92 | 55382.73 | 232885.96 |  |  | 14.96 | [9 empty] | 14.96 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 288283.65 |  |  | 232900.92 | 55382.73 | 232885.96 |  |  | 14.96 | [9 empty] | 14.96 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 13354.65 |  |  | 7602.37 | 5752.28 | 7602.37
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Activity Type Cost Adjustment | 5590045 | 1597 |  |  |  | 1597
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | GAS Activity Charge - Type A | 5590101 | 104 |  |  | 103.58 | 0.42 | 103.58
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Administration | 6603000 | 333 |  |  | 1199.07 | -866.07 | 1199.07
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Construction | 6603001 |  |  |  | 798.72 | -798.72 | 798.72
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Acquisition - Misc | 6603004 |  |  |  | 221.87 | -221.87 | 221.87
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 249.9 | -249.9 | 249.9
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Engineering/Mapping | 6603022 | 4274.66 |  |  | 1979.42 | 2295.24 | 1979.42
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Management Services | 6603076 |  |  |  | 1237.74 | -1237.74 | 1237.74
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Maintain & Operate Services | 6603083 | 2012 |  |  |  | 2012
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Field Services | 6603099 | 4532 |  |  |  | 4532
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Engineering/Mapping Services Overtime | 6603106 | 71.35 |  |  | 102.46 | -31.11 | 102.46
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 69.61 | -69.61 | 69.61
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Account Services | 6603730 | 430.64 |  |  | 1640 | -1209.36 | 1640
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 274929 |  |  | 225298.55 | 49630.45 | 225283.59 |  |  | 14.96 | [9 empty] | 14.96 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Service Planning - Planning Only | 5501163 | 274929 |  |  |  | 274929
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 218620.39 | -218620.39 | 218620.39
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Mapping | 6010077 |  |  |  | 6678.16 | -6678.16 | 6663.2 |  |  | 14.96 | [9 empty] | 14.96 | 14.96
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Material Total | PGE1MATTOTAL | 488638 |  |  | 359828.66 | 128809.34 | 359828.66
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Material related expenses | PGE1MATERIAL | 438979 |  |  | 327068.06 | 111910.94 | 327068.06
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 2332.48 | -2332.48 | 2332.48
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 1340.38 | -1340.38 | 1340.38
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 42745.31 | -42745.31 | 42745.31
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Electrical Specialties | 5300140 | 438979 |  |  | 20459.37 | 418519.63 | 20459.37
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | -4516.6 | 4516.6 | -4516.6
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 243440.99 | -243440.99 | 243440.99
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 124.88 | -124.88 | 124.88
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 20813.59 | -20813.59 | 20813.59
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 327.66 | -327.66 | 327.66
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Material Burden | PGE1MATBURD | 49659 |  |  | 32760.6 | 16898.4 | 32760.6
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Material Burden Adjustment | 5590076 | 49659 |  |  |  | 49659
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Material Burden | 6010000 |  |  |  | 32760.6 | -32760.6 | 32760.6
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Contract Total | PGE1CONTRACT | 2994185 |  |  | 2693904.36 | 300280.64 | 2693904.36 |  |  | 4985 | -4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Consulting | PGE1CONSULTING | 183 |  |  | 183.31 | -0.31 | 183.31
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Consulting Services - Engineering | 5001230 | 132 |  |  | 132.03 | -0.03 | 132.03
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 51 |  |  | 51.28 | -0.28 | 51.28
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 2994002 |  |  | 2693721.05 | 300280.95 | 2693721.05 |  |  | 4985 | -4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Contracts | 5490000 | 925600 |  |  | 535136.07 | 390463.93 | 535136.07
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Electric Construction Contract | 5490001 | 1966998 |  |  | 1893700.71 | 73297.29 | 1893700.71 |  |  | 4985 | -4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 167628.25 | -167628.25 | 167628.25
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Environmental Contract | 5490015 | 10590 |  |  | 11442.37 | -852.37 | 11442.37
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Construction Inspection | 5490021 | 75400 |  |  | 70399.94 | 5000.06 | 70399.94
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Traffic Control Contracts | 5490027
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Helicopter Contract | 6608176 | 15414 |  |  | 15413.71 | 0.29 | 15413.71
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 728544 |  | 75000 | 575003.16 | 153540.84 | 499972.24 |  |  | 30.92 | [8 empty] | 75000 | 30.92 | 75030.92
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 728528 |  | 75000 | -16607.89 | 745135.89 | -91607.89 | [11 empty] | 75000 |  | 75000
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 728528 |  | 75000 | -16607.89 | 745135.89 | -91607.89 | [11 empty] | 75000 |  | 75000
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | 7812.36 | -7812.36 | 7812.36
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Permits/Fees | 5501090
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 1243.37 | -1243.37 | 1243.37
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 728528 |  | 75000 | -23093.06 | 751621.06 | -98093.06 | [11 empty] | 75000 |  | 75000
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Contingency-Planned | 5592000
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 60.14 | -60.14 | 60.14
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 60.14 | -60.14 | 60.14
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 60.14 | -60.14 | 60.14
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Order Overheads | PGE1OVERHEAD | 16 |  |  | 591550.91 | -591534.91 | 591519.99 |  |  | 30.92 | [9 empty] | 30.92 | 30.92
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 91259.57 | -91259.57 | 91254.06 |  |  | 5.51 | [9 empty] | 5.51 | 5.51
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 91259.57 | -91259.57 | 91254.06 |  |  | 5.51 | [9 empty] | 5.51 | 5.51
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 305427.45 | -305427.45 | 305409.78 |  |  | 17.67 | [9 empty] | 17.67 | 17.67
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 278974.69 | -278974.69 | 278958.63 |  |  | 16.06 | [9 empty] | 16.06 | 16.06
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 36103.97 | -36103.97 | 36100.96 |  |  | 3.01 | [9 empty] | 3.01 | 3.01
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 66440.02 | -66440.02 | 66434.95 |  |  | 5.07 | [9 empty] | 5.07 | 5.07
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Indirect Labor - Gas | 6010107 |  |  |  | 408.21 | -408.21 | 408.21
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 515.39 | -515.39 | 515.39
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 376.99 | -376.99 | 376.99
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 113367.67 | -113367.67 | 113363.08 |  |  | 4.59 | [9 empty] | 4.59 | 4.59
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 622.98 | -622.98 | 622.98
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 212.2 | -212.2 | 212.2
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 105.63 | -105.63 | 105.63
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Fleet OH | 6010123 |  |  |  | 60818.24 | -60818.24 | 60818.24
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Fleet OH - Elec | 6010125 |  |  |  | 3.39 | -3.39 |  |  |  | 3.39 | [9 empty] | 3.39 | 3.39
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 26452.76 | -26452.76 | 26451.15 |  |  | 1.61 | [9 empty] | 1.61 | 1.61
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 16219.8 | -16219.8 | 16218.77 |  |  | 1.03 | [9 empty] | 1.03 | 1.03
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | IT Device OH | 6010113 |  |  |  | 10232.96 | -10232.96 | 10232.38 |  |  | 0.58 | [9 empty] | 0.58 | 0.58
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 180876.34 | -180876.34 | 180868.6 |  |  | 7.74 | [9 empty] | 7.74 | 7.74
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Benefits OH | 6010120 |  |  |  | 111015.37 | -111015.37 | 111009.66 |  |  | 5.71 | [9 empty] | 5.71 | 5.71
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 37925.09 | -37925.09 | 37923.06 |  |  | 2.03 | [9 empty] | 2.03 | 2.03
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 31935.88 | -31935.88 | 31935.88
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR | 16 |  |  | 13987.55 | -13971.55 | 13987.55
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 15617.61 | -15617.61 | 15617.61
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | AFUDC-Equity | 5590031 | 16 |  |  | -1630.06 | 1646.06 | -1630.06
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Billing Credits | PGE1BILLCR
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 900000 |  | 3175.75 | 603063.62 | 296936.38 | 559107.68 | 33624.94 | 3432.13 | 3705.71 | 17.41 | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 40780.19 | 43955.94
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 900000 |  | 3175.75 | 603063.62 | 296936.38 | 559107.68 | 33624.94 | 3432.13 | 3705.71 | 17.41 | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 40780.19 | 43955.94
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 38250.24 | -38250.24 | 38144.01 |  |  | 88.82 | 17.41 | [8 empty] | 106.23 | 106.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 38250.24 | -38250.24 | 38144.01 |  |  | 88.82 | 17.41 | [8 empty] | 106.23 | 106.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 38004.8 | -38004.8 | 37898.57 |  |  | 88.82 | 17.41 | [8 empty] | 106.23 | 106.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 6214.57 | -6214.57 | 6108.34 |  |  | 88.82 | 17.41 | [8 empty] | 106.23 | 106.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Type Cost Adjustment | 5590045
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | GAS Activity Charge - Type A | 5590101 |  |  |  | 51.79 | -51.79 | 51.79
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 136.65 | -136.65 | 136.65
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Administration | 6603000 |  |  |  | 1642.72 | -1642.72 | 1642.72
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Acquisition - Misc | 6603004 |  |  |  | 31.7 | -31.7 | 31.7
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 443.08 | -443.08 | 443.08
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 17.41 | -17.41 |  |  |  |  | 17.41 | [8 empty] | 17.41 | 17.41
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 190.17 | -190.17 | 190.17
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Management Services | 6603076 |  |  |  | 1106.58 | -1106.58 | 1106.58
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 102.46 | -102.46 | 102.46
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Rights - Misc | 6603227 |  |  |  | 30.41 | -30.41 | 30.41
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Electric Estimating | 6603466 |  |  |  | 1888.23 | -1888.23 | 1799.41 |  |  | 88.82 | [9 empty] | 88.82 | 88.82
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Account Services | 6603730 |  |  |  | 573.37 | -573.37 | 573.37
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 31790.23 | -31790.23 | 31790.23
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Estimating-Internal | 6010076 |  |  |  | 30791.2 | -30791.2 | 30791.2
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Mapping | 6010077 |  |  |  | 999.03 | -999.03 | 999.03
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Types - Contractors | PGE1ACTV-CONTR |  |  |  | 245.44 | -245.44 | 245.44
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Other Contractor Activity Types | PGE1ACTV-OTH-C |  |  |  | 245.44 | -245.44 | 245.44
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Contractor Consultant | 6608158 |  |  |  | 245.44 | -245.44 | 245.44
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Contract Total | PGE1CONTRACT | 900000 |  |  | 470201.63 | 429798.37 | 440077.65 | 30123.98 | -0.14 | 0.14 | [9 empty] | 30123.98 | 30123.98
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Consulting | PGE1CONSULTING |  |  |  | 113.19 | -113.19 | 113.19
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 82.95 | -82.95 | 82.95
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Consulting Services - Other | 5001250 |  |  |  | 30.24 | -30.24 | 30.24
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 900000 |  |  | 470088.44 | 429911.56 | 439964.46 | 30123.98 | -0.14 | 0.14 | [9 empty] | 30123.98 | 30123.98
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Contracts | 5490000 | 900000 |  |  | 378182.44 | 521817.56 | 378182.44
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 86398.3 | -86398.3 | 56274.32 | 30123.98 | -0.14 | 0.14 | [9 empty] | 30123.98 | 30123.98
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Environmental Contract | 5490015 |  |  |  | 5507.7 | -5507.7 | 5507.7
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 3175.75 | 94611.75 | -94611.75 | 80886.02 | 3500.96 | 3432.27 | 3616.75 |  | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 10549.98 | 13725.73
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  |  | -14044.36 | 14044.36 | -14044.36
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | -14044.36 | 14044.36 | -14044.36
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Acquisition Services | 5501093 |  |  |  | 819.52 | -819.52 | 819.52
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -14863.88 | 14863.88 | -14863.88
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  | 3175.75 | 108656.11 | -108656.11 | 94930.38 | 3500.96 | 3432.27 | 3616.75 |  | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 10549.98 | 13725.73
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 14331.14 | -14331.14 | 14298.44 |  |  | 32.7 | [9 empty] | 32.7 | 32.7
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 14331.14 | -14331.14 | 14298.44 |  |  | 32.7 | [9 empty] | 32.7 | 32.7
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 46416.22 | -46416.22 | 46311.22 |  |  | 105 | [9 empty] | 105 | 105
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 42461.97 | -42461.97 | 42366.6 |  |  | 95.37 | [9 empty] | 95.37 | 95.37
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 7750.29 | -7750.29 | 7732.4 |  |  | 17.89 | [9 empty] | 17.89 | 17.89
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 11334.41 | -11334.41 | 11304.3 |  |  | 30.11 | [9 empty] | 30.11 | 30.11
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Indirect Labor - Gas | 6010107 |  |  |  | 13.78 | -13.78 | 13.78
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 687.41 | -687.41 | 687.41
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Indirect Labor - Cust Care | 6010110 |  |  |  | 165.95 | -165.95 | 165.95
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 13921.41 | -13921.41 | 13894.16 |  |  | 27.25 | [9 empty] | 27.25 | 27.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 21.55 | -21.55 | 21.55
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 287.15 | -287.15 | 287.15
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 27.51 | -27.51 | 27.51
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Fleet OH | 6010123 |  |  |  | 8232.39 | -8232.39 | 8232.39
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Fleet OH - Elec | 6010125 |  |  |  | 20.12 | -20.12 |  |  |  | 20.12 | [9 empty] | 20.12 | 20.12
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 3954.25 | -3954.25 | 3944.62 |  |  | 9.63 | [9 empty] | 9.63 | 9.63
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 2415.53 | -2415.53 | 2409.39 |  |  | 6.14 | [9 empty] | 6.14 | 6.14
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | IT Device OH | 6010113 |  |  |  | 1538.72 | -1538.72 | 1535.23 |  |  | 3.49 | [9 empty] | 3.49 | 3.49
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 21790.03 | -21790.03 | 21744.04 |  |  | 45.99 | [9 empty] | 45.99 | 45.99
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Benefits OH | 6010120 |  |  |  | 16295.29 | -16295.29 | 16261.37 |  |  | 33.92 | [9 empty] | 33.92 | 33.92
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 5494.74 | -5494.74 | 5482.67 |  |  | 12.07 | [9 empty] | 12.07 | 12.07
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  | 3175.75 | 26118.72 | -26118.72 | 12576.68 | 3500.96 | 3432.27 | 3433.06 |  | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 10366.29 | 13542.04
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  | 3175.75 | 17350.23 | -17350.23 | 11257.45 | 1060.74 | 928.04 | 928.25 |  | 897.74 | 897.74 | 920.18 | 460.09 |  |  |  |  | 2917.03 | 6092.78
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 8768.49 | -8768.49 | 1319.23 | 2440.22 | 2504.23 | 2504.81 | [9 empty] | 7449.26 | 7449.26
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3530636.37 |  | 42017 | 3143237.78 | 387398.59 | 3052145.09 | 16888.53 | 16093.58 | 16093.58 | [8 empty] | 42017 | 49075.69 | 91092.69
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3530636.37 |  | 42017 | 3143237.78 | 387398.59 | 3052145.09 | 16888.53 | 16093.58 | 16093.58 | [8 empty] | 42017 | 49075.69 | 91092.69
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 186353.37 |  |  | 176225.97 | 10127.4 | 176225.97
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Activity Types | PGE1ACTVTYPES | 186353.37 |  |  | 176225.97 | 10127.4 | 176225.97
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 186353.37 |  |  | 176225.97 | 10127.4 | 176225.97
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 9292.37 |  |  | 5301.74 | 3990.63 | 5301.74
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Activity Type Cost Adjustment | 5590045 | -1271 |  |  |  | -1271
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Administration | 6603000 | 271.8 |  |  | 312.74 | -40.94 | 312.74
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Engineering/Mapping | 6603022 | 4526.72 |  |  | 602.64 | 3924.08 | 602.64
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Environmental Services | 6603024 |  |  |  | 16.46 | -16.46 | 16.46
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 131.68 | -131.68 | 131.68
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Management Services | 6603076 |  |  |  | 2440.68 | -2440.68 | 2440.68
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Maintain & Operate Services | 6603083 | 2718 |  |  |  | 2718
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Field Services | 6603099 | 2920.17 |  |  |  | 2920.17
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Account Services | 6603730 | 126.68 |  |  | 1797.54 | -1670.86 | 1797.54
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 177061 |  |  | 170924.23 | 6136.77 | 170924.23
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Service Planning - Planning Only | 5501163 | 177061 |  |  |  | 177061
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 165407.76 | -165407.76 | 165407.76
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Mapping | 6010077 |  |  |  | 5516.47 | -5516.47 | 5516.47
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Material Total | PGE1MATTOTAL | 271456 |  |  | 273049.15 | -1593.15 | 273049.15
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Material related expenses | PGE1MATERIAL | 248798 |  |  | 250181.87 | -1383.87 | 250181.87
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 3419.38 | -3419.38 | 3419.38
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 2076.54 | -2076.54 | 2076.54
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 54251.9 | -54251.9 | 54251.9
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Electrical Specialties | 5300140 | 248798 |  |  | 22034.91 | 226763.09 | 22034.91
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 33.91 | -33.91 | 33.91
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 143007.82 | -143007.82 | 143007.82
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 48.93 | -48.93 | 48.93
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 24899.5 | -24899.5 | 24899.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 408.98 | -408.98 | 408.98
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Material Burden | PGE1MATBURD | 22658 |  |  | 22867.28 | -209.28 | 22867.28
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Material Burden Adjustment | 5590076 | 22658 |  |  |  | 22658
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Material Burden | 6010000 |  |  |  | 22867.28 | -22867.28 | 22867.28
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Contract Total | PGE1CONTRACT | 2029165 |  |  | 2184164.26 | -154999.26 | 2184164.26
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 2029165 |  |  | 2184164.26 | -154999.26 | 2184164.26
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Contracts | 5490000 | 658223 |  |  | 659462.44 | -1239.44 | 659462.44
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Electric Construction Contract | 5490001 | 1258538 |  |  | 1229100.5 | 29437.5 | 1229100.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 148659.03 | -148659.03 | 148659.03
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Environmental Contract | 5490015 | 24022 |  |  | 4292.73 | 19729.27 | 4292.73
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Construction Inspection | 5490021 | 88382 |  |  | 68381.7 | 20000.3 | 68381.7
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Paving Contracts | 5490500 |  |  |  | 74267.86 | -74267.86 | 74267.86
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 1043662 |  | 42017 | 509798.4 | 533863.6 | 418705.71 | 16888.53 | 16093.58 | 16093.58 | [8 empty] | 42017 | 49075.69 | 91092.69
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 1043662 |  | 42017 | -58539.37 | 1102201.37 | -100556.37 | [11 empty] | 42017 |  | 42017
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1043662 |  | 42017 | -58539.37 | 1102201.37 | -100556.37 | [11 empty] | 42017 |  | 42017
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -16332.72 | 16332.72 | -16332.72
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 1182.08 | -1182.08 | 1182.08
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 1043662 |  | 42017 | -40818.17 | 1084480.17 | -82835.17 | [11 empty] | 42017 |  | 42017
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 43.25 | -43.25 | 43.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 43.25 | -43.25 | 43.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 43.25 | -43.25 | 43.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 568294.52 | -568294.52 | 519218.83 | 16888.53 | 16093.58 | 16093.58 | [9 empty] | 49075.69 | 49075.69
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 67848.9 | -67848.9 | 67848.9
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 67848.9 | -67848.9 | 67848.9
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 227001.04 | -227001.04 | 227001.04
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 206915.75 | -206915.75 | 206915.75
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 28960.65 | -28960.65 | 28960.65
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 51526.73 | -51526.73 | 51526.73
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 163.18 | -163.18 | 163.18
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 408.22 | -408.22 | 408.22
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 81151.96 | -81151.96 | 81151.96
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 66.04 | -66.04 | 66.04
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 43.54 | -43.54 | 43.54
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Fleet OH | 6010123 |  |  |  | 44595.43 | -44595.43 | 44595.43
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 20085.29 | -20085.29 | 20085.29
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 12195.48 | -12195.48 | 12195.48
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | IT Device OH | 6010113 |  |  |  | 7889.81 | -7889.81 | 7889.81
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 134830.77 | -134830.77 | 134830.77
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Benefits OH | 6010120 |  |  |  | 84188.44 | -84188.44 | 84188.44
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 28222.93 | -28222.93 | 28222.93
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 22419.4 | -22419.4 | 22419.4
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 138613.81 | -138613.81 | 89538.12 | 16888.53 | 16093.58 | 16093.58 | [9 empty] | 49075.69 | 49075.69
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 99647.05 | -99647.05 | 85797.66 | 5146.43 | 4351.48 | 4351.48 | [9 empty] | 13849.39 | 13849.39
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | 38966.76 | -38966.76 | 3740.46 | 11742.1 | 11742.1 | 11742.1 | [9 empty] | 35226.3 | 35226.3
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 5480368 |  | 106865 | 5486737.97 | -6369.97 | 5039334.63 | 336335.63 | 6799.89 | -2597.18 | [8 empty] | 106865 | 340538.34 | 447403.34
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5480368 |  | 106865 | 5486737.97 | -6369.97 | 5039334.63 | 336335.63 | 6799.89 | -2597.18 | [8 empty] | 106865 | 340538.34 | 447403.34
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 749259 |  |  | 312831.25 | 436427.75 | 311808.15 | 1019.95 |  | 3.15 | [9 empty] | 1023.1 | 1023.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Activity Types | PGE1ACTVTYPES | 749259 |  |  | 312831.25 | 436427.75 | 311808.15 | 1019.95 |  | 3.15 | [9 empty] | 1023.1 | 1023.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 749259 |  |  | 312831.25 | 436427.75 | 311808.15 | 1019.95 |  | 3.15 | [9 empty] | 1023.1 | 1023.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 749259 |  |  | 13482.45 | 735776.55 | 13482.45
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | GAS Activity Charge - Type A | 5590101 | 207 |  |  | 207.15 | -0.15 | 207.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Internal Services - Budget | 5600000 | 749052 |  |  |  | 749052
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Administration | 6603000 |  |  |  | 1838.51 | -1838.51 | 1838.51
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Construction | 6603001 |  |  |  | 1397.76 | -1397.76 | 1397.76
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Acquisition - Misc | 6603004 |  |  |  | 2131.27 | -2131.27 | 2131.27
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Project Management Services | 6603013 |  |  |  | 114.46 | -114.46 | 114.46
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 339.15 | -339.15 | 339.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Engineering/Mapping | 6603022 |  |  |  | 549.4 | -549.4 | 549.4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 362.12 | -362.12 | 362.12
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 838.24 | -838.24 | 838.24
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Management Services | 6603076 |  |  |  | 2458.08 | -2458.08 | 2458.08
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 52.21 | -52.21 | 52.21
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Maintain & Operate Services | 6603083 |  |  |  | 139.52 | -139.52 | 139.52
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Administrative Services - OT | 6603150 |  |  |  | 46.79 | -46.79 | 46.79
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Construction Doubletime Services | 6603180 |  |  |  | 475.6 | -475.6 | 475.6
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 139.22 | -139.22 | 139.22
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Rights - Misc | 6603227 |  |  |  | 62.11 | -62.11 | 62.11
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Account Services | 6603730 |  |  |  | 1991.33 | -1991.33 | 1991.33
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Manage L&EM | 6603823 |  |  |  | 339.53 | -339.53 | 339.53
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 299348.8 | -299348.8 | 298325.7 | 1019.95 |  | 3.15 | [9 empty] | 1023.1 | 1023.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 289749.48 | -289749.48 | 289749.48
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Mapping | 6010077 |  |  |  | 9599.32 | -9599.32 | 8576.22 | 1019.95 |  | 3.15 | [9 empty] | 1023.1 | 1023.1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Material Total | PGE1MATTOTAL | 696023 |  |  | 639038.64 | 56984.36 | 642441.98 |  |  | -3403.34 | [9 empty] | -3403.34 | -3403.34
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Material related expenses | PGE1MATERIAL | 696023 |  |  | 553257.66 | 142765.34 | 556627.3 |  |  | -3369.64 | [9 empty] | -3369.64 | -3369.64
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 975.55 | -975.55 | 975.55
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 2037.72 | -2037.72 | 2037.72
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 47733.9 | -47733.9 | 47733.9
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Electrical Specialties | 5300140 | 696023 |  |  | 49194.39 | 646828.61 | 49194.39
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 469135.39 | -469135.39 | 469135.39
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 60.7 | -60.7 | 60.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | -16236.7 | 16236.7 | -12867.06 |  |  | -3369.64 | [9 empty] | -3369.64 | -3369.64
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 356.71 | -356.71 | 356.71
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 85780.98 | -85780.98 | 85814.68 |  |  | -33.7 | [9 empty] | -33.7 | -33.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Material Burden | 6010000 |  |  |  | 85780.98 | -85780.98 | 85814.68 |  |  | -33.7 | [9 empty] | -33.7 | -33.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Contract Total | PGE1CONTRACT | 3035426 |  |  | 3789433.07 | -754007.07 | 3448398.94 | 339985.46 |  | 1048.67 | [9 empty] | 341034.13 | 341034.13
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Consulting | PGE1CONSULTING | 30000 |  |  | 227.01 | 29772.99 | 227.01
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Consulting Services - Engineering | 5001230 |  |  |  | 227.01 | -227.01 | 227.01
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 30000 |  |  |  | 30000
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 3005426 |  |  | 3789206.06 | -783780.06 | 3448171.93 | 339985.46 |  | 1048.67 | [9 empty] | 341034.13 | 341034.13
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Contracts | 5490000 | 819041 |  |  | 960962.78 | -141921.78 | 959914.11 |  |  | 1048.67 | [9 empty] | 1048.67 | 1048.67
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Electric Construction Contract | 5490001 | 2014034 |  |  | 2387524.81 | -373490.81 | 2047539.35 | 339985.46 | [11 empty] | 339985.46 | 339985.46
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 92430 |  |  | 241842.83 | -149412.83 | 241842.83
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Environmental Contract | 5490015 | 11521 |  |  | 25839.62 | -14318.62 | 25839.62
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Construction Inspection | 5490021 |  |  |  | 159533.45 | -159533.45 | 159533.45
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Traffic Control Contracts | 5490027 | 68400 |  |  |  | 68400
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Helicopter Contract | 6608176 |  |  |  | 13502.57 | -13502.57 | 13502.57
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 999660 |  | 106865 | 745435.01 | 254224.99 | 636685.56 | -4669.78 | 6799.89 | -245.66 | [8 empty] | 106865 | 1884.45 | 108749.45
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 999590 |  | 106865 | -55063.04 | 1054653.04 | -161928.04 | -6799.89 | 6799.89 | [9 empty] | 106865 |  | 106865
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 999590 |  | 106865 | -55063.04 | 1054653.04 | -161928.04 | -6799.89 | 6799.89 | [9 empty] | 106865 |  | 106865
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -19371.29 | 19371.29 | -19371.29 | -6799.89 | 6799.89
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Permits/Fees | 5501090 | 201152 |  |  |  | 201152
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Permits/Fees - Environmental | 5501091 |  |  |  | 214.35 | -214.35 | 214.35
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Acquisition Services | 5501093 | 1476 |  |  | 1668.62 | -192.62 | 1668.62
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Other Land Fees | 5501094 |  |  |  | 500 | -500 | 500
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -1722.96 | 1722.96 | -1722.96
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 796962 |  | 106865 | -36359.96 | 833321.96 | -143224.96 | [11 empty] | 106865 |  | 106865
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Other Expenses | 5591000 |  |  |  | 8.2 | -8.2 | 8.2
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Employee Related | PGE1EMPLREL | 70 |  |  | 107.15 | -37.15 | 107.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE | 70 |  |  | 107.15 | -37.15 | 107.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Reimbursed Mileage Expense | 5091140 | 70 |  |  | 107.15 | -37.15 | 107.15
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 800390.9 | -800390.9 | 798506.45 | 2130.11 |  | -245.66 | [9 empty] | 1884.45 | 1884.45
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 119403.63 | -119403.63 | 119026.93 | 375.54 |  | 1.16 | [9 empty] | 376.7 | 376.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 119403.63 | -119403.63 | 119026.93 | 375.54 |  | 1.16 | [9 empty] | 376.7 | 376.7
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 403300.61 | -403300.61 | 402093.12 | 1205.54 |  | 1.95 | [9 empty] | 1207.49 | 1207.49
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 365341.75 | -365341.75 | 364243.25 | 1095.12 |  | 3.38 | [9 empty] | 1098.5 | 1098.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 55046.25 | -55046.25 | 54840.2 | 205.42 |  | 0.63 | [9 empty] | 206.05 | 206.05
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 92971.85 | -92971.85 | 92625.01 | 345.77 |  | 1.07 | [9 empty] | 346.84 | 346.84
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Indirect Labor - Gas | 6010107 |  |  |  | 858.27 | -858.27 | 858.27
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1979.19 | -1979.19 | 1979.19
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 439.86 | -439.86 | 439.86
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 135100.66 | -135100.66 | 134786.77 | 312.92 |  | 0.97 | [9 empty] | 313.89 | 313.89
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 1309.72 | -1309.72 | 1309.72
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 848.31 | -848.31 | 848.31
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 78.13 | -78.13 | 78.13
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Fleet OH | 6010123 |  |  |  | 76477.79 | -76477.79 | 76477.79
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Fleet OH - Elec | 6010125 |  |  |  | 231.72 | -231.72 |  | 231.01 |  | 0.71 | [9 empty] | 231.72 | 231.72
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 37958.86 | -37958.86 | 37849.87 | 110.42 |  | -1.43 | [9 empty] | 108.99 | 108.99
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 22971.01 | -22971.01 | 22901.48 | 70.44 |  | -0.91 | [9 empty] | 69.53 | 69.53
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | IT Device OH | 6010113 |  |  |  | 14987.85 | -14987.85 | 14948.39 | 39.98 |  | -0.52 | [9 empty] | 39.46 | 39.46
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 266818.25 | -266818.25 | 266517.99 | 549.03 |  | -248.77 | [9 empty] | 300.26 | 300.26
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Benefits OH | 6010120 |  |  |  | 158743.88 | -158743.88 | 158338.51 | 410.38 |  | -5.01 | [9 empty] | 405.37 | 405.37
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 53102.99 | -53102.99 | 52966.12 | 138.65 |  | -1.78 | [9 empty] | 136.87 | 136.87
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 54971.38 | -54971.38 | 55213.36 |  |  | -241.98 | [9 empty] | -241.98 | -241.98
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 10868.41 | -10868.41 | 10868.41
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 12128.8 | -12128.8 | 12128.8
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1260.39 | 1260.39 | -1260.39
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3123544.1 |  | 177549 | 2813130.04 | 310414.06 | 2738130.42 | -102549.38 | [7 empty] | 177549 |  |  |  | -102549.38 | 74999.62
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3123544.1 |  | 177549 | 2813130.04 | 310414.06 | 2738130.42 | -102549.38 | [7 empty] | 177549 |  |  |  | -102549.38 | 74999.62
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 299384.1 |  |  | 312458.77 | -13074.67 | 312763.59 | -304.82 | [11 empty] | -304.82 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Activity Types | PGE1ACTVTYPES | 299384.1 |  |  | 312458.77 | -13074.67 | 312763.59 | -304.82 | [11 empty] | -304.82 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 299384.1 |  |  | 312458.77 | -13074.67 | 312763.59 | -304.82 | [11 empty] | -304.82 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 11393.1 |  |  | 8305.7 | 3087.4 | 8305.7
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Activity Type Cost Adjustment | 5590045 | -15668 |  |  |  | -15668
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Administration | 6603000 | 199.8 |  |  | 2130.32 | -1930.52 | 2130.32
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Acquisition - Misc | 6603004 | 245.04 |  |  | 212.87 | 32.17 | 212.87
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Project Management Services | 6603013 | 172.38 |  |  | 400.54 | -228.16 | 400.54
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Engineering/Mapping | 6603022 | 3301.92 |  |  | 248.08 | 3053.84 | 248.08
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Environmental Services | 6603024 |  |  |  | 263.36 | -263.36 | 263.36
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 66.6 |  |  | 893.49 | -826.89 | 893.49
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Management Services | 6603076 |  |  |  | 1467.51 | -1467.51 | 1467.51
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Maintain & Operate Services | 6603083 | 18832.32 |  |  | 120.78 | 18711.54 | 120.78
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Vegetation Management - Misc | 6603097 |  |  |  | 425.74 | -425.74 | 425.74
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Field Services | 6603099 | 4120 |  |  |  | 4120
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Administrative Services - OT | 6603150 |  |  |  | 93.57 | -93.57 | 93.57
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 122.27 | -122.27 | 122.27
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Account Services | 6603730 | 123.04 |  |  | 1861.33 | -1738.29 | 1861.33
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Manage L&EM | 6603823 |  |  |  | 65.84 | -65.84 | 65.84
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 287991 |  |  | 304153.07 | -16162.07 | 304457.89 | -304.82 | [11 empty] | -304.82 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Service Planning - Planning Only | 5501163 | 287991 |  |  |  | 287991
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 303398.79 | -303398.79 | 303398.79
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Mapping | 6010077 |  |  |  | 754.28 | -754.28 | 1059.1 | -304.82 | [11 empty] | -304.82 | -304.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Material Total | PGE1MATTOTAL | 263798 |  |  | 263798.18 | -0.18 | 263798.18
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Material related expenses | PGE1MATERIAL | 243241 |  |  | 243241.25 | -0.25 | 243241.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 2037.44 | -2037.44 | 2037.44
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 1744.89 | -1744.89 | 1744.89
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 69990.14 | -69990.14 | 69990.14
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Electrical Specialties | 5300140 | 243241 |  |  | 56940.96 | 186300.04 | 56940.96
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 92404.77 | -92404.77 | 92404.77
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 3423.12 | -3423.12 | 3423.12
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 16485.94 | -16485.94 | 16485.94
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 213.99 | -213.99 | 213.99
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Material Burden | PGE1MATBURD | 20557 |  |  | 20556.93 | 0.07 | 20556.93
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Material Burden Adjustment | 5590076 | 20557 |  |  |  | 20557
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Material Burden | 6010000 |  |  |  | 20556.93 | -20556.93 | 20556.93
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Contract Total | PGE1CONTRACT | 1347261 |  |  | 1352942.77 | -5681.77 | 1454550.73 | -101607.96 | [11 empty] | -101607.96 | -101607.96
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Consulting | PGE1CONSULTING | 31 |  |  | 30.75 | 0.25 | 30.75
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 31 |  |  | 30.75 | 0.25 | 30.75
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1347230 |  |  | 1352912.02 | -5682.02 | 1454519.98 | -101607.96 | [11 empty] | -101607.96 | -101607.96
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Contracts | 5490000 | 232153 |  |  | 288363.22 | -56210.22 | 288363.22
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Electric Construction Contract | 5490001 | 905608 |  |  | 828658.92 | 76949.08 | 931766.5 | -103107.58 | [11 empty] | -103107.58 | -103107.58
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 14651.84 | -14651.84 | 14651.84
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Environmental Contract | 5490015 | 52747 |  |  | 57980.66 | -5233.66 | 57980.66
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Construction Inspection | 5490021 | 74478 |  |  | 81013.3 | -6535.3 | 79513.68 | 1499.62 | [11 empty] | 1499.62 | 1499.62
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Helicopter Contract | 6608176 | 82244 |  |  | 82244.08 | -0.08 | 82244.08
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 1213101 |  | 177549 | 883930.32 | 329170.68 | 707017.92 | -636.6 | [7 empty] | 177549 |  |  |  | -636.6 | 176912.4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 1213101 |  | 177549 | 155263.08 | 1057837.92 | -22285.92 | [8 empty] | 177549 |  |  |  |  | 177549
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1213101 |  | 177549 | 155263.08 | 1057837.92 | -22285.92 | [8 empty] | 177549 |  |  |  |  | 177549
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -9390.69 | 9390.69 | -9390.69
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Permits/Fees | 5501090
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 2773.6 | -2773.6 | 2773.6
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 1213101 |  | 177549 | 164450.73 | 1048650.27 | -13098.27 | [8 empty] | 177549 |  |  |  |  | 177549
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Contingency-Planned | 5592000
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 3459.78 | -3459.78 | 3459.78
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 96.2 | -96.2 | 96.2
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 96.2 | -96.2 | 96.2
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 3363.58 | -3363.58 | 3363.58
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 3363.58 | -3363.58 | 3363.58
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 725207.46 | -725207.46 | 725844.06 | -636.6 | [11 empty] | -636.6 | -636.6
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 132664.22 | -132664.22 | 132776.45 | -112.23 | [11 empty] | -112.23 | -112.23
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 132664.22 | -132664.22 | 132776.45 | -112.23 | [11 empty] | -112.23 | -112.23
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 398513.39 | -398513.39 | 398873.67 | -360.28 | [11 empty] | -360.28 | -360.28
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 368451.07 | -368451.07 | 368778.35 | -327.28 | [11 empty] | -327.28 | -327.28
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 40518.98 | -40518.98 | 40580.37 | -61.39 | [11 empty] | -61.39 | -61.39
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 92018.34 | -92018.34 | 92121.67 | -103.33 | [11 empty] | -103.33 | -103.33
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1471.01 | -1471.01 | 1471.01
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 455.82 | -455.82 | 455.82
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 156682.51 | -156682.51 | 156776.03 | -93.52 | [11 empty] | -93.52 | -93.52
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 593.25 | -593.25 | 593.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 168.8 | -168.8 | 168.8
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Fleet OH | 6010123 |  |  |  | 76611.4 | -76611.4 | 76611.4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Fleet OH - Elec | 6010125 |  |  |  | -69.04 | 69.04 |  | -69.04 | [11 empty] | -69.04 | -69.04
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 30062.32 | -30062.32 | 30095.32 | -33 | [11 empty] | -33 | -33
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 20017.33 | -20017.33 | 20038.38 | -21.05 | [11 empty] | -21.05 | -21.05
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | IT Device OH | 6010113 |  |  |  | 10044.99 | -10044.99 | 10056.94 | -11.95 | [11 empty] | -11.95 | -11.95
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 184037.26 | -184037.26 | 184201.35 | -164.09 | [11 empty] | -164.09 | -164.09
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Benefits OH | 6010120 |  |  |  | 118892.63 | -118892.63 | 119015.28 | -122.65 | [11 empty] | -122.65 | -122.65
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 47418.01 | -47418.01 | 47459.45 | -41.44 | [11 empty] | -41.44 | -41.44
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 17726.62 | -17726.62 | 17726.62
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 9992.59 | -9992.59 | 9992.59
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 11243.9 | -11243.9 | 11243.9
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1251.31 | 1251.31 | -1251.31
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Billing Credits | PGE1BILLCR
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3044148.02 |  | 75000 | 2923313.16 | 120834.86 | 2848313.16 | [6 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3044148.02 |  | 75000 | 2923313.16 | 120834.86 | 2848313.16 | [6 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 409024.02 |  |  | 391766.57 | 17257.45 | 391766.57
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Activity Types | PGE1ACTVTYPES | 409024.02 |  |  | 391766.57 | 17257.45 | 391766.57
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 409024.02 |  |  | 391766.57 | 17257.45 | 391766.57
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 10048.02 |  |  | 7218.65 | 2829.37 | 7218.65
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Activity Type Cost Adjustment | 5590045 | -18217 |  |  |  | -18217
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Administration | 6603000 | 399.6 |  |  | 959.33 | -559.73 | 959.33
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Construction | 6603001 |  |  |  | 186.2 | -186.2 | 186.2
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Acquisition - Misc | 6603004 | 306.3 |  |  | 273.69 | 32.61 | 273.69
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Engineering/Mapping | 6603022 | 4545.28 |  |  | 744.4 | 3800.88 | 744.4
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Environmental Services | 6603024 |  |  |  | 213.98 | -213.98 | 213.98
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Management Services | 6603076 |  |  |  | 3602.07 | -3602.07 | 3602.07
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Maintain & Operate Services | 6603083 | 18832.32 |  |  |  | 18832.32
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Field Services | 6603099 | 4120 |  |  |  | 4120
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Account Services | 6603730 | 61.52 |  |  | 1238.98 | -1177.46 | 1238.98
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 398976 |  |  | 384547.92 | 14428.08 | 384547.92
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Service Planning - Planning Only | 5501163 | 398976 |  |  |  | 398976
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 384724.44 | -384724.44 | 384724.44
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Mapping | 6010077 |  |  |  | -176.52 | 176.52 | -176.52
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Material Total | PGE1MATTOTAL | 222663 |  |  | 223213.15 | -550.15 | 223213.15
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Material related expenses | PGE1MATERIAL | 205644 |  |  | 206121.64 | -477.64 | 206121.64
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 1948.37 | -1948.37 | 1948.37
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 1093.46 | -1093.46 | 1093.46
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 32374.69 | -32374.69 | 32374.69
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Electrical Specialties | 5300140 | 205644 |  |  | 32900.08 | 172743.92 | 32900.08
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 115718.45 | -115718.45 | 115718.45
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 3479.6 | -3479.6 | 3479.6
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 18381.92 | -18381.92 | 18381.92
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 225.07 | -225.07 | 225.07
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Material Burden | PGE1MATBURD | 17019 |  |  | 17091.51 | -72.51 | 17091.51
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Material Burden Adjustment | 5590076 | 17019 |  |  |  | 17019
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Material Burden | 6010000 |  |  |  | 17091.51 | -17091.51 | 17091.51
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Contract Total | PGE1CONTRACT | 1447694 |  |  | 1316666.56 | 131027.44 | 1316666.56
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Consulting | PGE1CONSULTING | 61 |  |  | 61.5 | -0.5 | 61.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 61 |  |  | 61.5 | -0.5 | 61.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1447633 |  |  | 1316605.06 | 131027.94 | 1316605.06
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Contracts | 5490000 | 141519 |  |  | 141671.17 | -152.17 | 141671.17
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Electric Construction Contract | 5490001 | 1161600 |  |  | 1069184.22 | 92415.78 | 1069184.22
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Environmental Contract | 5490015 | 29296 |  |  | 10531.64 | 18764.36 | 10531.64
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Construction Inspection | 5490021 | 115218 |  |  | 95218.03 | 19999.97 | 95218.03
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 964767 |  | 75000 | 991666.88 | -26899.88 | 916666.88 | [6 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 964767 |  | 75000 | 70338.56 | 894428.44 | -4661.44 | [6 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 964767 |  | 75000 | 70338.56 | 894428.44 | -4661.44 | [6 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -4862.32 | 4862.32 | -4862.32
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Permits/Fees | 5501090
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 200.88 | -200.88 | 200.88
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 964767 |  | 75000 | 75000 | 889767 | [7 empty] | 75000 | [6 empty] | 75000
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 2358.37 | -2358.37 | 2358.37
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 2354.22 | -2354.22 | 2354.22
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 2354.22 | -2354.22 | 2354.22
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 918969.95 | -918969.95 | 918969.95
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 181717.3 | -181717.3 | 181717.3
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 181717.3 | -181717.3 | 181717.3
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 506914.22 | -506914.22 | 506914.22
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 470277.72 | -470277.72 | 470277.72
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 44579.62 | -44579.62 | 44579.62
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 110824.31 | -110824.31 | 110824.31
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Indirect Labor - Gas | 6010107 |  |  |  | 49.55 | -49.55 | 49.55
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 525.72 | -525.72 | 525.72
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 263.74 | -263.74 | 263.74
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 212122.26 | -212122.26 | 212122.26
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 77.48 | -77.48 | 77.48
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 209.37 | -209.37 | 209.37
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 64.17 | -64.17 | 64.17
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Fleet OH | 6010123 |  |  |  | 101561.5 | -101561.5 | 101561.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 36636.5 | -36636.5 | 36636.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 24765 | -24765 | 24765
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | IT Device OH | 6010113 |  |  |  | 11871.5 | -11871.5 | 11871.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 219451.92 | -219451.92 | 219451.92
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Benefits OH | 6010120 |  |  |  | 144032.76 | -144032.76 | 144032.76
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 60503.47 | -60503.47 | 60503.47
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 14915.69 | -14915.69 | 14915.69
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 10886.51 | -10886.51 | 10886.51
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 12216.67 | -12216.67 | 12216.67
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1330.16 | 1330.16 | -1330.16
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Billing Credits | PGE1BILLCR
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 3172297.77 |  | 75000 | 2761391.99 | 410905.78 | 2686391.99 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3172297.77 |  | 75000 | 2761391.99 | 410905.78 | 2686391.99 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 337360.77 |  |  | 303044.57 | 34316.2 | 303044.57
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Activity Types | PGE1ACTVTYPES | 337360.77 |  |  | 303044.57 | 34316.2 | 303044.57
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 337360.77 |  |  | 303044.57 | 34316.2 | 303044.57
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 16006.77 |  |  | 11762.66 | 4244.11 | 11762.66
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Activity Type Cost Adjustment | 5590045 | 5027 |  |  |  | 5027
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Electric Activity Charge - Type A | 5590100
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Administration | 6603000 |  |  |  | 1818.35 | -1818.35 | 1818.35
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Acquisition - Misc | 6603004 | 127.5 |  |  | 121.64 | 5.86 | 121.64
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Project Management Services | 6603013 |  |  |  | 57.23 | -57.23 | 57.23
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Engineering/Mapping | 6603022 | 4526.72 |  |  | 673.52 | 3853.2 | 673.52
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Environmental Services | 6603024 |  |  |  | 148.14 | -148.14 | 148.14
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 67.95 |  |  | 493.8 | -425.85 | 493.8
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Management Services | 6603076 |  |  |  | 2401.38 | -2401.38 | 2401.38
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 52.21 | -52.21 | 52.21
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Maintain & Operate Services | 6603083 | 2718 |  |  | 383.68 | 2334.32 | 383.68
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Vegetation Management - Misc | 6603097 |  |  |  | 304.1 | -304.1 | 304.1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Field Services Overtime | 6603098 |  |  |  | 1445.87 | -1445.87 | 1445.87
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Field Services | 6603099 | 3539.6 |  |  | 465.28 | 3074.32 | 465.28
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 1461.71 | -1461.71 | 1461.71
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Field Services Doubletime | 6603184 |  |  |  | 568.8 | -568.8 | 568.8
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Account Services | 6603730 |  |  |  | 1301.11 | -1301.11 | 1301.11
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Manage L&EM | 6603823 |  |  |  | 65.84 | -65.84 | 65.84
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 321354 |  |  | 291281.91 | 30072.09 | 291281.91
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Service Planning - Planning Only | 5501163 | 321354 |  |  |  | 321354
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 290769.73 | -290769.73 | 290769.73
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Mapping | 6010077 |  |  |  | 512.18 | -512.18 | 512.18
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Material Total | PGE1MATTOTAL | 191197 |  |  | 192846.09 | -1649.09 | 192846.09
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Material related expenses | PGE1MATERIAL | 176441 |  |  | 177873.68 | -1432.68 | 177873.68
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 1896.88 | -1896.88 | 1896.88
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 1318.47 | -1318.47 | 1318.47
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 31435.27 | -31435.27 | 31435.27
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Electrical Specialties | 5300140 | 176441 |  |  | 19305.68 | 157135.32 | 19305.68
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 106013.61 | -106013.61 | 106013.61
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 3466.66 | -3466.66 | 3466.66
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 14199.39 | -14199.39 | 14199.39
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 194.93 | -194.93 | 194.93
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Freight | 5300320 |  |  |  | 25 | -25 | 25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Purchasing Card | 5300330 |  |  |  | 17.79 | -17.79 | 17.79
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Material Burden | PGE1MATBURD | 14756 |  |  | 14972.41 | -216.41 | 14972.41
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Material Burden Adjustment | 5590076 | 14756 |  |  |  | 14756
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Material Burden | 6010000 |  |  |  | 14972.41 | -14972.41 | 14972.41
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Contract Total | PGE1CONTRACT | 1887844 |  |  | 1525209.69 | 362634.31 | 1525209.69
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Consulting | PGE1CONSULTING | 106 |  |  | 105.5 | 0.5 | 105.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Consulting Services - Engineering | 5001230 | 44 |  |  | 44 |  | 44
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 62 |  |  | 61.5 | 0.5 | 61.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1887738 |  |  | 1525104.19 | 362633.81 | 1525104.19
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Contracts | 5490000 | 689613 |  |  | 446905.57 | 242707.43 | 446905.57
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Electric Construction Contract | 5490001 | 1021822 |  |  | 890578.89 | 131243.11 | 890578.89
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Environmental Contract | 5490015 | 26250 |  |  | 39768.92 | -13518.92 | 39768.92
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Construction Inspection | 5490021 | 54635 |  |  | 52433.03 | 2201.97 | 52433.03
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Helicopter Contract | 6608176 | 95418 |  |  | 95417.78 | 0.22 | 95417.78
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 755896 |  | 75000 | 740291.64 | 15604.36 | 665291.64 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 755896 |  | 75000 | 61554.35 | 694341.65 | -13445.65 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 755896 |  | 75000 | 61554.35 | 694341.65 | -13445.65 | [6 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -13131.17 | 13131.17 | -13131.17
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 2256.08 | -2256.08 | 2256.08
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 755896 |  | 75000 | 75000 | 680896 | [7 empty] | 75000 | [6 empty] | 75000
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 5922.39 | -5922.39 | 5922.39
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 75.32 | -75.32 | 75.32
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 75.32 | -75.32 | 75.32
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 5847.07 | -5847.07 | 5847.07
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 5847.07 | -5847.07 | 5847.07
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 672814.9 | -672814.9 | 672814.9
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 100431.7 | -100431.7 | 100431.7
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 100431.7 | -100431.7 | 100431.7
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 391376.78 | -391376.78 | 391376.78
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 362920.41 | -362920.41 | 362920.41
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 38632.91 | -38632.91 | 38632.91
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 95390.99 | -95390.99 | 95390.99
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1086.2 | -1086.2 | 1086.2
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 284.43 | -284.43 | 284.43
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 157461.77 | -157461.77 | 157461.77
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 420.47 | -420.47 | 420.47
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 66.46 | -66.46 | 66.46
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Fleet OH | 6010123 |  |  |  | 69577.18 | -69577.18 | 69577.18
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 28456.37 | -28456.37 | 28456.37
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 19153.16 | -19153.16 | 19153.16
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | IT Device OH | 6010113 |  |  |  | 9303.21 | -9303.21 | 9303.21
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 168361.35 | -168361.35 | 168361.35
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Benefits OH | 6010120 |  |  |  | 112772.9 | -112772.9 | 112772.9
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 42723.19 | -42723.19 | 42723.19
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 12865.26 | -12865.26 | 12865.26
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 12645.07 | -12645.07 | 12645.07
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 14218.81 | -14218.81 | 14218.81
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1573.74 | 1573.74 | -1573.74
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 5804262.07 |  | 74326 | 4622930.36 | 1181331.71 | 4447929.88 | 100674.48 | [6 empty] | 74326 |  |  |  |  | 100674.48 | 175000.48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 6103261.07 |  | 74326 | 4522930.36 | 1580330.71 | 4447929.88 | 674.48 | [6 empty] | 74326 |  |  |  |  | 674.48 | 75000.48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 131529.07 |  |  | 552114.43 | -420585.36 | 551819.09 | 295.34 | [11 empty] | 295.34 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Activity Types | PGE1ACTVTYPES | 131529.07 |  |  | 552114.43 | -420585.36 | 551819.09 | 295.34 | [11 empty] | 295.34 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 131529.07 |  |  | 552114.43 | -420585.36 | 551819.09 | 295.34 | [11 empty] | 295.34 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 131529.07 |  |  | 8816.02 | 122713.05 | 8520.68 | 295.34 | [11 empty] | 295.34 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Internal Services - Budget | 5600000 | 118750 |  |  |  | 118750
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Administration | 6603000 | 203.85 |  |  | 579.2 | -375.35 | 579.2
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Engineering/Mapping | 6603022 | 4526.72 |  |  | 1063.52 | 3463.2 | 1063.52
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Management Services | 6603076 |  |  |  | 2401.38 | -2401.38 | 2401.38
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 228.3 | -228.3 | 228.3
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Maintain & Operate Services | 6603083 | 3624 |  |  | 301.95 | 3322.05 | 301.95
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Vegetation Management - Misc | 6603097 |  |  |  | 121.64 | -121.64 | 121.64
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Field Services Overtime | 6603098 |  |  |  | 349.83 | -349.83 | 349.83
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Field Services | 6603099 | 4424.5 |  |  | 985.63 | 3438.87 | 985.63
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 305.68 | -305.68 | 305.68
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Field Services Doubletime | 6603184 |  |  |  | 812.13 | -812.13 | 812.13
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Account Services | 6603730 |  |  |  | 1666.76 | -1666.76 | 1371.42 | 295.34 | [11 empty] | 295.34 | 295.34
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 543298.41 | -543298.41 | 543298.41
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 542810.35 | -542810.35 | 542810.35
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Mapping | 6010077 |  |  |  | 488.06 | -488.06 | 488.06
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Material Total | PGE1MATTOTAL | 379027 |  |  | 459309.72 | -80282.72 | 459309.72
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Material related expenses | PGE1MATERIAL | 379027 |  |  | 424652.93 | -45625.93 | 424652.93
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 2871.17 | -2871.17 | 2871.17
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 6180.08 | -6180.08 | 6180.08
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 87801.32 | -87801.32 | 87801.32
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Electrical Specialties | 5300140 | 379027 |  |  | 63064.14 | 315962.86 | 63064.14
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 212208.08 | -212208.08 | 212208.08
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 6886.9 | -6886.9 | 6886.9
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 45054.89 | -45054.89 | 45054.89
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 586.35 | -586.35 | 586.35
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 34656.79 | -34656.79 | 34656.79
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Material Burden | 6010000 |  |  |  | 34656.79 | -34656.79 | 34656.79
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Contract Total | PGE1CONTRACT | 5098980 |  |  | 2154507.78 | 2944472.22 | 2154507.78
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Consulting | PGE1CONSULTING | 1500 |  |  | 30.75 | 1469.25 | 30.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 1500 |  |  | 30.75 | 1469.25 | 30.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 5097480 |  |  | 2154477.03 | 2943002.97 | 2154477.03
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Contracts | 5490000 | 3795318 |  |  | 777116.94 | 3018201.06 | 777116.94
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Electric Construction Contract | 5490001 | 1228162 |  |  | 1285701.89 | -57539.89 | 1285701.89
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Environmental Contract | 5490015 |  |  |  | 5615.09 | -5615.09 | 5615.09
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Construction Inspection | 5490021 | 74000 |  |  | 86043.11 | -12043.11 | 86043.11
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 493725 |  | 74326 | 1356998.43 | -863273.43 | 1282293.29 | 379.14 | [6 empty] | 74326 |  |  |  |  | 379.14 | 74705.14
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 493725 |  | 74326 | 57772 | 435953 | -16554 | [7 empty] | 74326 | [5 empty] | 74326
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 493725 |  | 74326 | 57772 | 435953 | -16554 | [7 empty] | 74326 | [5 empty] | 74326
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -17170.77 | 17170.77 | -17170.77
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Permits/Fees | 5501090 | 493725 |  |  |  | 493725
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 616.77 | -616.77 | 616.77
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 74326 | 74326 | -74326 | [8 empty] | 74326 | [5 empty] | 74326
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 14559.89 | -14559.89 | 14559.89
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 14559.89 | -14559.89 | 14559.89
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 14559.89 | -14559.89 | 14559.89
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 1284666.54 | -1284666.54 | 1284287.4 | 379.14 | [11 empty] | 379.14 | 379.14
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 239464.26 | -239464.26 | 239355.52 | 108.74 | [11 empty] | 108.74 | 108.74
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 239464.26 | -239464.26 | 239355.52 | 108.74 | [11 empty] | 108.74 | 108.74
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 715480.26 | -715480.26 | 715321.81 | 158.45 | [11 empty] | 158.45 | 158.45
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 663098.98 | -663098.98 | 662963.04 | 135.94 | [11 empty] | 135.94 | 135.94
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 64796.29 | -64796.29 | 64736.81 | 59.48 | [11 empty] | 59.48 | 59.48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 161510.04 | -161510.04 | 161510.04
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 250.49 | -250.49 | 250.49
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 405.92 | -405.92 | 329.46 | 76.46 | [11 empty] | 76.46 | 76.46
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 296181.83 | -296181.83 | 296181.83
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 103.85 | -103.85 | 103.85
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 38.96 | -38.96 | 38.96
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Fleet OH | 6010123 |  |  |  | 139811.6 | -139811.6 | 139811.6
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 52381.28 | -52381.28 | 52358.77 | 22.51 | [11 empty] | 22.51 | 22.51
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 35292.16 | -35292.16 | 35277.8 | 14.36 | [11 empty] | 14.36 | 14.36
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | IT Device OH | 6010113 |  |  |  | 17089.12 | -17089.12 | 17080.97 | 8.15 | [11 empty] | 8.15 | 8.15
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 322138.96 | -322138.96 | 322027.01 | 111.95 | [11 empty] | 111.95 | 111.95
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Benefits OH | 6010120 |  |  |  | 206457.71 | -206457.71 | 206374.03 | 83.68 | [11 empty] | 83.68 | 83.68
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 84365.39 | -84365.39 | 84337.12 | 28.27 | [11 empty] | 28.27 | 28.27
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 31315.86 | -31315.86 | 31315.86
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 7583.06 | -7583.06 | 7583.06
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 8603.61 | -8603.61 | 8603.61
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1020.55 | 1020.55 | -1020.55
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE | -298999 |  |  | 100000 | -398999 |  | 100000 | [11 empty] | 100000 | 100000
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Billing Credits | PGE1BILLCR | -298999 |  |  | 100000 | -398999 |  | 100000 | [11 empty] | 100000 | 100000
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Billing Credit - CIAC Non Taxable | 5590051 |  |  |  | 100000 | -100000 |  | 100000 | [11 empty] | 100000 | 100000
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -298999 |  |  |  | -298999
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 4009924.5 |  | 75000 | 3905827.63 | 104096.87 | 3830827.63 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4009924.5 |  | 75000 | 3905827.63 | 104096.87 | 3830827.63 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 428250.5 |  |  | 413204.6 | 15045.9 | 413204.6
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Activity Types | PGE1ACTVTYPES | 428250.5 |  |  | 413204.6 | 15045.9 | 413204.6
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 428250.5 |  |  | 413204.6 | 15045.9 | 413204.6
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 10039.5 |  |  | 6165.91 | 3873.59 | 6165.91
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Activity Type Cost Adjustment | 5590045 | -10412 |  |  |  | -10412
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Administration | 6603000 |  |  |  | 842.56 | -842.56 | 842.56
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Design Services | 6603017 |  |  |  | 179.94 | -179.94 | 179.94
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Engineering/Mapping | 6603022 | 5503.2 |  |  |  | 5503.2
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Environmental Services | 6603024 | 999 |  |  |  | 999
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Management Services | 6603076 |  |  |  | 3505.71 | -3505.71 | 3505.71
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Maintain & Operate Services | 6603083 | 6438.4 |  |  |  | 6438.4
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Vegetation Management - Misc | 6603097 |  |  |  | 121.64 | -121.64 | 121.64
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Field Services | 6603099 | 6592 |  |  |  | 6592
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Land Rights - Misc | 6603227 | 918.9 |  |  |  | 918.9
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Account Services | 6603730 |  |  |  | 1516.06 | -1516.06 | 1516.06
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 418211 |  |  | 407038.69 | 11172.31 | 407038.69
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Service Planning - Planning Only | 5501163 | 418211 |  |  |  | 418211
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 404396.71 | -404396.71 | 404396.71
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Mapping | 6010077 |  |  |  | 2641.98 | -2641.98 | 2641.98
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Material Total | PGE1MATTOTAL | 336774 |  |  | 301187.67 | 35586.33 | 301187.67
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Material related expenses | PGE1MATERIAL | 306362 |  |  | 271405.09 | 34956.91 | 271405.09
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 2682.76 | -2682.76 | 2682.76
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 12714.29 | -12714.29 | 12714.29
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 | 306362 |  |  | 45650.48 | 260711.52 | 45650.48
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Electrical Specialties | 5300140 |  |  |  | 38640.65 | -38640.65 | 38640.65
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 165861.75 | -165861.75 | 165861.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 44.51 | -44.51 | 44.51
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 5487.27 | -5487.27 | 5487.27
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 323.38 | -323.38 | 323.38
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Material Burden | PGE1MATBURD | 30412 |  |  | 29782.58 | 629.42 | 29782.58
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Material Burden Adjustment | 5590076 | 30412 |  |  |  | 30412
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Material Burden | 6010000 |  |  |  | 29782.58 | -29782.58 | 29782.58
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Contract Total | PGE1CONTRACT | 2187702 |  |  | 2155603.66 | 32098.34 | 2155603.66
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Consulting | PGE1CONSULTING | 31 |  |  | 30.75 | 0.25 | 30.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 31 |  |  | 30.75 | 0.25 | 30.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 2187671 |  |  | 2155572.91 | 32098.09 | 2155572.91
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Contracts | 5490000 | 301148 |  |  | 301299.82 | -151.82 | 301299.82
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Electric Construction Contract | 5490001 | 1772990 |  |  | 1664391.12 | 108598.88 | 1664391.12
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 74264.54 | -74264.54 | 74264.54
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Environmental Contract | 5490015 | 5007 |  |  | 5903.69 | -896.69 | 5903.69
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Construction Inspection | 5490021 | 108526 |  |  | 109713.74 | -1187.74 | 109713.74
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Traffic Control Contracts | 5490027
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 1057198 |  | 75000 | 1035831.7 | 21366.3 | 960831.7 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 1057198 |  | 75000 | 23300.64 | 1033897.36 | -51699.36 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1057198 |  | 75000 | 23300.64 | 1033897.36 | -51699.36 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -8968.88 | 8968.88 | -8968.88
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Permits/Fees | 5501090
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 338.38 | -338.38 | 338.38
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 1057198 |  | 75000 | 34501.7 | 1022696.3 | -40498.3 | [5 empty] | 75000 | [7 empty] | 75000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Contingency-Planned | 5592000
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 72.1 | -72.1 | 72.1
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 72.1 | -72.1 | 72.1
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 72.1 | -72.1 | 72.1
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 1012458.96 | -1012458.96 | 1012458.96
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 189279.51 | -189279.51 | 189279.51
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 189279.51 | -189279.51 | 189279.51
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 538358.3 | -538358.3 | 538358.3
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 497660.06 | -497660.06 | 497660.06
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 50802.29 | -50802.29 | 50802.29
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 116629.91 | -116629.91 | 116629.91
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 331.53 | -331.53 | 331.53
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 369.29 | -369.29 | 369.29
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 221101.7 | -221101.7 | 221101.7
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 145.44 | -145.44 | 145.44
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 80.41 | -80.41 | 80.41
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Fleet OH | 6010123 |  |  |  | 108199.49 | -108199.49 | 108199.49
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 40698.24 | -40698.24 | 40698.24
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 26738.78 | -26738.78 | 26738.78
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | IT Device OH | 6010113 |  |  |  | 13959.46 | -13959.46 | 13959.46
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 258995.07 | -258995.07 | 258995.07
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Benefits OH | 6010120 |  |  |  | 162909.72 | -162909.72 | 162909.72
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 65144.38 | -65144.38 | 65144.38
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 30940.97 | -30940.97 | 30940.97
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 25826.08 | -25826.08 | 25826.08
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 28809.54 | -28809.54 | 28809.54
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -2983.46 | 2983.46 | -2983.46
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Billing Credits | PGE1BILLCR
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 2276638 |  | 74251 | 2132272.42 | 144365.58 | 2057272.01 | 749.41 |  |  |  |  | 74251 | [6 empty] | 749.41 | 75000.41
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2276638 |  | 74251 | 2132272.42 | 144365.58 | 2057272.01 | 749.41 |  |  |  |  | 74251 | [6 empty] | 749.41 | 75000.41
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 168161 |  |  | 131412.81 | 36748.19 | 131084.66 | 328.15 | [11 empty] | 328.15 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Activity Types | PGE1ACTVTYPES | 168161 |  |  | 131412.81 | 36748.19 | 131084.66 | 328.15 | [11 empty] | 328.15 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 168161 |  |  | 131412.81 | 36748.19 | 131084.66 | 328.15 | [11 empty] | 328.15 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 28245 |  |  | 5020.74 | 23224.26 | 4692.59 | 328.15 | [11 empty] | 328.15 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Activity Type Cost Adjustment | 5590045 | 7769 |  |  |  | 7769
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Internal Services - Budget | 5600000 | 20476 |  |  |  | 20476
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Administration | 6603000 |  |  |  | 819.72 | -819.72 | 819.72
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 376.64 | -376.64 | 376.64
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Engineering/Mapping | 6603022 |  |  |  | 1701.6 | -1701.6 | 1701.6
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Management Services | 6603076 |  |  |  | 1220.34 | -1220.34 | 1220.34
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Account Services | 6603730 |  |  |  | 902.44 | -902.44 | 574.29 | 328.15 | [11 empty] | 328.15 | 328.15
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 139916 |  |  | 126392.07 | 13523.93 | 126392.07
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Service Planning - Planning Only | 5501163 | 139916 |  |  |  | 139916
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 122576.52 | -122576.52 | 122576.52
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Mapping | 6010077 |  |  |  | 3815.55 | -3815.55 | 3815.55
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Material Total | PGE1MATTOTAL | 145464 |  |  | 127374.11 | 18089.89 | 127374.11
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Material related expenses | PGE1MATERIAL | 127802 |  |  | 110476.48 | 17325.52 | 110476.48
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 1039.56 | -1039.56 | 1039.56
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 917.35 | -917.35 | 917.35
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 21012.98 | -21012.98 | 21012.98
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Electrical Specialties | 5300140 | 127802 |  |  | 16698.16 | 111103.84 | 16698.16
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 72261.71 | -72261.71 | 72261.71
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 76.43 | -76.43 | 76.43
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | -1666.96 | 1666.96 | -1666.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 137.25 | -137.25 | 137.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Material Burden | PGE1MATBURD | 17662 |  |  | 16897.63 | 764.37 | 16897.63
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Material Burden Adjustment | 5590076 | 17662 |  |  |  | 17662
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Material Burden | 6010000 |  |  |  | 16897.63 | -16897.63 | 16897.63
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Contract Total | PGE1CONTRACT | 1603888 |  |  | 1541576.27 | 62311.73 | 1541576.27
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1603888 |  |  | 1541576.27 | 62311.73 | 1541576.27
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Contracts | 5490000 | 431369 |  |  | 402309.95 | 29059.05 | 402309.95
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Electric Construction Contract | 5490001 | 1112895 |  |  | 971737.78 | 141157.22 | 971737.78
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 108212.7 | -108212.7 | 108212.7
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Environmental Contract | 5490015 | 5105 |  |  | 7028.42 | -1923.42 | 7028.42
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Construction Inspection | 5490021 | 40986 |  |  | 41134.86 | -148.86 | 41134.86
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Helicopter Contract | 6608176 | 13533 |  |  | 11152.56 | 2380.44 | 11152.56
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 359125 |  | 74251 | 331909.23 | 27215.77 | 257236.97 | 421.26 |  |  |  |  | 74251 | [6 empty] | 421.26 | 74672.26
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 359067 |  | 74251 | 6043.18 | 353023.82 | -68207.82 | [5 empty] | 74251 | [7 empty] | 74251
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 359067 |  | 74251 | 6043.18 | 353023.82 | -68207.82 | [5 empty] | 74251 | [7 empty] | 74251
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Cash Discount earned | 5006310 | -6572 |  |  | -7693.38 | 1121.38 | -7693.38
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Land Acquisition Services | 5501093 | 1784 |  |  | 1784.36 | -0.36 | 1784.36
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -1722.96 | 1722.96 | -1722.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 363855 |  | 74251 | 13675.16 | 350179.84 | -60575.84 | [5 empty] | 74251 | [7 empty] | 74251
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Employee Related | PGE1EMPLREL | 58 |  |  | 69.17 | -11.17 | 69.17
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE | 58 |  |  | 69.17 | -11.17 | 69.17
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Reimbursed Mileage Expense | 5091140 | 58 |  |  | 69.17 | -11.17 | 69.17
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 325796.88 | -325796.88 | 325375.62 | 421.26 | [11 empty] | 421.26 | 421.26
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 50838.86 | -50838.86 | 50718.04 | 120.82 | [11 empty] | 120.82 | 120.82
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 50838.86 | -50838.86 | 50718.04 | 120.82 | [11 empty] | 120.82 | 120.82
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 170458 | -170458 | 170281.94 | 176.06 | [11 empty] | 176.06 | 176.06
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 155388.67 | -155388.67 | 155237.62 | 151.05 | [11 empty] | 151.05 | 151.05
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 21671.82 | -21671.82 | 21605.73 | 66.09 | [11 empty] | 66.09 | 66.09
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 38502.93 | -38502.93 | 38502.93
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 292.41 | -292.41 | 292.41
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 200.37 | -200.37 | 115.41 | 84.96 | [11 empty] | 84.96 | 84.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 61064.51 | -61064.51 | 61064.51
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 134.49 | -134.49 | 134.49
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 11.46 | -11.46 | 11.46
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Fleet OH | 6010123 |  |  |  | 33510.68 | -33510.68 | 33510.68
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 15069.33 | -15069.33 | 15044.32 | 25.01 | [11 empty] | 25.01 | 25.01
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 9124.15 | -9124.15 | 9108.19 | 15.96 | [11 empty] | 15.96 | 15.96
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | IT Device OH | 6010113 |  |  |  | 5945.18 | -5945.18 | 5936.13 | 9.05 | [11 empty] | 9.05 | 9.05
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 95582.62 | -95582.62 | 95458.24 | 124.38 | [11 empty] | 124.38 | 124.38
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Benefits OH | 6010120 |  |  |  | 63354.28 | -63354.28 | 63261.31 | 92.97 | [11 empty] | 92.97 | 92.97
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 21261.45 | -21261.45 | 21230.04 | 31.41 | [11 empty] | 31.41 | 31.41
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 10966.89 | -10966.89 | 10966.89
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 8917.4 | -8917.4 | 8917.4
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 9958.9 | -9958.9 | 9958.9
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -1041.5 | 1041.5 | -1041.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 4471950.48 |  | 71973 | 3706462.08 | 765488.4 | 3631462.06 | 3027.02 | [5 empty] | 71973 | [5 empty] | 3027.02 | 75000.02
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4862842.48 |  | 71973 | 3706462.08 | 1156380.4 | 3631462.06 | 3027.02 | [5 empty] | 71973 | [5 empty] | 3027.02 | 75000.02
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 278454.48 |  |  | 428173.85 | -149719.37 | 428164.85 | 9 | [11 empty] | 9 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Activity Types | PGE1ACTVTYPES | 278454.48 |  |  | 428173.85 | -149719.37 | 428164.85 | 9 | [11 empty] | 9 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 278454.48 |  |  | 428173.85 | -149719.37 | 428164.85 | 9 | [11 empty] | 9 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 278454.48 |  |  | 10909 | 267545.48 | 10909
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Internal Services - Budget | 5600000 | 264580 |  |  |  | 264580
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Administration | 6603000 | 865.8 |  |  | 592.56 | 273.24 | 592.56
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Acquisition - Misc | 6603004 | 612.6 |  |  | 91.23 | 521.37 | 91.23
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 941.6 | -941.6 | 941.6
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Engineering/Mapping | 6603022 | 3872.8 |  |  | 907.01 | 2965.79 | 907.01
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Environmental Services | 6603024 | 66.6 |  |  | 65.84 | 0.76 | 65.84
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 66.6 |  |  | 65.84 | 0.76 | 65.84
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Management Services | 6603076 |  |  |  | 3639.12 | -3639.12 | 3639.12
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 345.8 | -345.8 | 345.8
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Maintain & Operate Services | 6603083 | 4024 |  |  | 1116.49 | 2907.51 | 1116.49
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Field Services Overtime | 6603098 |  |  |  | 237.03 | -237.03 | 237.03
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Field Services | 6603099 | 4120 |  |  | 499.75 | 3620.25 | 499.75
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Maint & Operate Doubletime Services | 6603181 |  |  |  | 1239.65 | -1239.65 | 1239.65
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Account Services | 6603730 | 246.08 |  |  | 1167.08 | -921 | 1167.08
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 417264.85 | -417264.85 | 417255.85 | 9 | [11 empty] | 9 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 415560.59 | -415560.59 | 415560.59
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Mapping | 6010077 |  |  |  | 1704.26 | -1704.26 | 1695.26 | 9 | [11 empty] | 9 | 9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Material Total | PGE1MATTOTAL | 1073062 |  |  | 261830.16 | 811231.84 | 261830.16
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Material related expenses | PGE1MATERIAL | 1073062 |  |  | 232974.96 | 840087.04 | 232974.96
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 2055.53 | -2055.53 | 2055.53
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 2270.96 | -2270.96 | 2270.96
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 52020.04 | -52020.04 | 52020.04
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Electrical Specialties | 5300140 | 1073062 |  |  | 36732.09 | 1036329.91 | 36732.09
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 141794.39 | -141794.39 | 141794.39
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 3576.66 | -3576.66 | 3576.66
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | -5740.79 | 5740.79 | -5740.79
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 266.08 | -266.08 | 266.08
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 28855.2 | -28855.2 | 28855.2
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Material Burden | 6010000 |  |  |  | 28855.2 | -28855.2 | 28855.2
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Contract Total | PGE1CONTRACT | 2959667 |  |  | 1919682.39 | 1039984.61 | 1916683.15 | 2999.24 | [11 empty] | 2999.24 | 2999.24
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Consulting | PGE1CONSULTING | 25000 |  |  | 105.5 | 24894.5 | 105.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Consulting Services - Engineering | 5001230 |  |  |  | 44 | -44 | 44
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 25000 |  |  | 61.5 | 24938.5 | 61.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 2934667 |  |  | 1919576.89 | 1015090.11 | 1916577.65 | 2999.24 | [11 empty] | 2999.24 | 2999.24
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Contracts | 5490000 | 1157015 |  |  | 292708.56 | 864306.44 | 292708.56
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Electric Construction Contract | 5490001 | 1616972 |  |  | 1459956.93 | 157015.07 | 1459956.93
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 45750.34 | -45750.34 | 45750.34
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Environmental Contract | 5490015 | 1262 |  |  | 8648.73 | -7386.73 | 8648.73
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Construction Inspection | 5490021 | 97018 |  |  | 112512.33 | -15494.33 | 109513.09 | 2999.24 | [11 empty] | 2999.24 | 2999.24
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Traffic Control Contracts | 5490027 | 62400 |  |  |  | 62400
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 551659 |  | 71973 | 1096775.68 | -545116.68 | 1024783.9 | 18.78 | [5 empty] | 71973 | [5 empty] | 18.78 | 71991.78
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 551659 |  | 71973 | 40813.18 | 510845.82 | -31159.82 | [6 empty] | 71973 | [6 empty] | 71973
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 551659 |  | 71973 | 40813.18 | 510845.82 | -31159.82 | [6 empty] | 71973 | [6 empty] | 71973
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -5584.86 | 5584.86 | -5584.86
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Permits/Fees | 5501090 | 551659 |  |  |  | 551659
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 2168.41 | -2168.41 | 2168.41
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -2570.56 | 2570.56 | -2570.56
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 71973 | 46800.19 | -46800.19 | -25172.81 | [6 empty] | 71973 | [6 empty] | 71973
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Contingency-Planned | 5592000
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 9889.13 | -9889.13 | 9889.13
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL |  |  |  | 9884.98 | -9884.98 | 9884.98
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Other Employee Related Expense | 5091200 |  |  |  | 9884.98 | -9884.98 | 9884.98
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 1046073.37 | -1046073.37 | 1046054.59 | 18.78 | [11 empty] | 18.78 | 18.78
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 197434.38 | -197434.38 | 197431.07 | 3.31 | [11 empty] | 3.31 | 3.31
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 197434.38 | -197434.38 | 197431.07 | 3.31 | [11 empty] | 3.31 | 3.31
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 558863.93 | -558863.93 | 558853.3 | 10.63 | [11 empty] | 10.63 | 10.63
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 517287.12 | -517287.12 | 517277.46 | 9.66 | [11 empty] | 9.66 | 9.66
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 51572.65 | -51572.65 | 51570.84 | 1.81 | [11 empty] | 1.81 | 1.81
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 121021.1 | -121021.1 | 121018.05 | 3.05 | [11 empty] | 3.05 | 3.05
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 282.76 | -282.76 | 282.76
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 266.46 | -266.46 | 266.46
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 231591.41 | -231591.41 | 231588.65 | 2.76 | [11 empty] | 2.76 | 2.76
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 118.73 | -118.73 | 118.73
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 87.28 | -87.28 | 87.28
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Fleet OH | 6010123 |  |  |  | 112344.69 | -112344.69 | 112344.69
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Fleet OH - Elec | 6010125 |  |  |  | 2.04 | -2.04 |  | 2.04 | [11 empty] | 2.04 | 2.04
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 41576.81 | -41576.81 | 41575.84 | 0.97 | [11 empty] | 0.97 | 0.97
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 27558.69 | -27558.69 | 27558.07 | 0.62 | [11 empty] | 0.62 | 0.62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | IT Device OH | 6010113 |  |  |  | 14018.12 | -14018.12 | 14017.77 | 0.35 | [11 empty] | 0.35 | 0.35
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 263568.1 | -263568.1 | 263563.26 | 4.84 | [11 empty] | 4.84 | 4.84
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Benefits OH | 6010120 |  |  |  | 165646.87 | -165646.87 | 165643.25 | 3.62 | [11 empty] | 3.62 | 3.62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 67374.99 | -67374.99 | 67373.77 | 1.22 | [11 empty] | 1.22 | 1.22
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 30546.24 | -30546.24 | 30546.24
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 26206.96 | -26206.96 | 26206.96
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 29234.34 | -29234.34 | 29234.34
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | -3027.38 | 3027.38 | -3027.38
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE | -390892 |  |  |  | -390892
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Billing Credits | PGE1BILLCR | -390892 |  |  |  | -390892
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -390892 |  |  |  | -390892
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 1116465.62 |  | 75000 | 973206.13 | 143259.49 | 898206.13 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 1163646.62 |  | 75000 | 973206.13 | 190440.49 | 898206.13 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 125969.62 |  |  | 112426.62 | 13543 | 112426.62
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Activity Types | PGE1ACTVTYPES | 125969.62 |  |  | 112426.62 | 13543 | 112426.62
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 125969.62 |  |  | 112426.62 | 13543 | 112426.62
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 125969.62 |  |  | 7856.22 | 118113.4 | 7856.22
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Activity Type Cost Adjustment | 5590045
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Internal Services - Budget | 5600000 | 118750 |  |  |  | 118750
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Administration | 6603000 | 266.4 |  |  | 1252.51 | -986.11 | 1252.51
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Construction | 6603001 |  |  |  | 996.64 | -996.64 | 996.64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Acquisition - Misc | 6603004 | 122.52 |  |  | 212.87 | -90.35 | 212.87
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Engineering/Mapping | 6603022 | 4781.12 |  |  | 212.64 | 4568.48 | 212.64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Environmental Services | 6603024 |  |  |  | 197.52 | -197.52 | 197.52
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 133.2 |  |  | 757.16 | -623.96 | 757.16
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 15.21 | -15.21 | 15.21
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Management Services | 6603076 |  |  |  | 2401.38 | -2401.38 | 2401.38
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Maintain & Operate Services | 6603083 | 804.8 |  |  |  | 804.8
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Vegetation Management - Misc | 6603097 |  |  |  | 364.92 | -364.92 | 364.92
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Field Services | 6603099 | 988.8 |  |  |  | 988.8
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Administrative Services - OT | 6603150 | 61.26 |  |  | 85.83 | -24.57 | 85.83
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Rights - Misc | 6603227 |  |  |  | 60.82 | -60.82 | 60.82
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Account Services | 6603730 | 61.52 |  |  | 1265.8 | -1204.28 | 1265.8
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Manage L&EM | 6603823 |  |  |  | 32.92 | -32.92 | 32.92
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 104570.4 | -104570.4 | 104570.4
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 104137.75 | -104137.75 | 104137.75
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Mapping | 6010077 |  |  |  | 432.65 | -432.65 | 432.65
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Material Total | PGE1MATTOTAL | 83430 |  |  | 57500.85 | 25929.15 | 57500.85
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Material related expenses | PGE1MATERIAL | 83430 |  |  | 52696.13 | 30733.87 | 52696.13
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 730.64 | -730.64 | 730.64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 788.61 | -788.61 | 788.61
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 8232.57 | -8232.57 | 8232.57
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Electrical Specialties | 5300140 | 83430 |  |  | 6009.53 | 77420.47 | 6009.53
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 33916.44 | -33916.44 | 33916.44
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 4.02 | -4.02 | 4.02
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | 2968.56 | -2968.56 | 2968.56
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 45.76 | -45.76 | 45.76
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 4804.72 | -4804.72 | 4804.72
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Material Burden | 6010000 |  |  |  | 4804.72 | -4804.72 | 4804.72
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Contract Total | PGE1CONTRACT | 523256 |  |  | 478067.9 | 45188.1 | 478067.9
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Consulting | PGE1CONSULTING |  |  |  | 44 | -44 | 44
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Consulting Services - Engineering | 5001230 |  |  |  | 44 | -44 | 44
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 523256 |  |  | 478023.9 | 45232.1 | 478023.9
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Contracts | 5490000 | 10000 |  |  | 39735.9 | -29735.9 | 39735.9
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Electric Construction Contract | 5490001 | 484256 |  |  | 401094.92 | 83161.08 | 401094.92
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 11851.36 | -11851.36 | 11851.36
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Environmental Contract | 5490015 |  |  |  | 15819.4 | -15819.4 | 15819.4
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Construction Inspection | 5490021 | 29000 |  |  | 9522.32 | 19477.68 | 9522.32
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 430991 |  | 75000 | 325210.76 | 105780.24 | 250210.76 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 430985 |  | 75000 | 64877.03 | 366107.97 | -10122.97 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 430985 |  | 75000 | 64877.03 | 366107.97 | -10122.97 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -1075.44 | 1075.44 | -1075.44
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Rents | 5007000 | 27000 |  |  |  | 27000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Permits/Fees | 5501090 | 129362 |  |  |  | 129362
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Acquisition Services | 5501093 |  |  |  | 2021.44 | -2021.44 | 2021.44
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Cost Adjustments | 5590042 |  |  |  | -4466.09 | 4466.09 | -4466.09
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 274623 |  | 75000 | 68397.12 | 206225.88 | -6602.88 | [7 empty] | 75000 | [5 empty] | 75000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Contingency-Planned | 5592000
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Employee Related | PGE1EMPLREL |  |  |  | 4.15 | -4.15 | 4.15
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 4.15 | -4.15 | 4.15
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 4.15 | -4.15 | 4.15
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Order Overheads | PGE1OVERHEAD | 6 |  |  | 260329.58 | -260323.58 | 260329.58
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 51288.09 | -51288.09 | 51288.09
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 51288.09 | -51288.09 | 51288.09
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 143664.25 | -143664.25 | 143664.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 132911.67 | -132911.67 | 132911.67
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 13368.6 | -13368.6 | 13368.6
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 29744.37 | -29744.37 | 29744.37
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Indirect Labor - Gas | 6010107 |  |  |  | 298.99 | -298.99 | 298.99
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1098.37 | -1098.37 | 1098.37
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 284.73 | -284.73 | 284.73
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 58584.6 | -58584.6 | 58584.6
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 329.09 | -329.09 | 329.09
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 415.39 | -415.39 | 415.39
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 84.79 | -84.79 | 84.79
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Fleet OH | 6010123 |  |  |  | 28702.74 | -28702.74 | 28702.74
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 10752.58 | -10752.58 | 10752.58
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 7113.64 | -7113.64 | 7113.64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | IT Device OH | 6010113 |  |  |  | 3638.94 | -3638.94 | 3638.94
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 64545.42 | -64545.42 | 64545.42
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Benefits OH | 6010120 |  |  |  | 42876.07 | -42876.07 | 42876.07
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 17310.16 | -17310.16 | 17310.16
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 4359.19 | -4359.19 | 4359.19
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR | 6 |  |  | 831.82 | -825.82 | 831.82
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 937.24 | -937.24 | 937.24
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | AFUDC-Equity | 5590031 | 6 |  |  | -105.42 | 111.42 | -105.42
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE | -47181 |  |  |  | -47181
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Billing Credits | PGE1BILLCR | -47181 |  |  |  | -47181
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055 | -47181 |  |  |  | -47181
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN | 2963552.32 |  |  | 2244138.27 | 719414.05 | 2168872.73 | 12643.16 | -25483.28 | 89340.36 | -1234.7 | [8 empty] | 75265.54 | 75265.54
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2963552.32 |  |  | 2244138.27 | 719414.05 | 2168872.73 | 12643.16 | -25483.28 | 89340.36 | -1234.7 | [8 empty] | 75265.54 | 75265.54
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT | 887131.32 |  |  | 135494.27 | 751637.05 | 134695.04 | -0.6 | -38.05 | 763.43 | 74.45 | [8 empty] | 799.23 | 799.23
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Types | PGE1ACTVTYPES | 887131.32 |  |  | 135494.27 | 751637.05 | 134695.04 | -0.6 | -38.05 | 763.43 | 74.45 | [8 empty] | 799.23 | 799.23
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT | 887131.32 |  |  | 135494.27 | 751637.05 | 134695.04 | -0.6 | -38.05 | 763.43 | 74.45 | [8 empty] | 799.23 | 799.23
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 887131.32 |  |  | 33790.51 | 853340.81 | 33104.72 |  | 74.45 | 536.89 | 74.45 | [8 empty] | 685.79 | 685.79
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Type Cost Adjustment | 5590045
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Electric Activity Charge - Type A | 5590100 |  |  |  | 933.4 | -933.4 | 933.4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Internal Services - Budget | 5600000 | 870652 |  |  |  | 870652
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Administration | 6603000 | 815.4 |  |  | 2069.72 | -1254.32 | 2053.26 |  |  | 16.46 | [9 empty] | 16.46 | 16.46
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Construction | 6603001 |  |  |  | 199.68 | -199.68 | 199.68
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Construction Overtime Services | 6603021 |  |  |  | 107.1 | -107.1 | 107.1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Engineering/Mapping | 6603022 | 520.94 |  |  | 2533.54 | -2012.6 | 1864.21 |  | 74.45 | 520.43 | 74.45 | [8 empty] | 669.33 | 669.33
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Environmental Services | 6603024 | 67.95 |  |  | 82.3 | -14.35 | 82.3
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Environmental Planning & Permitting-Misc | 6603027 | 203.85 |  |  | 197.52 | 6.33 | 197.52
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operating Services | 6603045 |  |  |  | 295.84 | -295.84 | 295.84
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Switching Operator Service | 6603068 |  |  |  | 578.1 | -578.1 | 578.1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Management Services | 6603076 |  |  |  | 1219.21 | -1219.21 | 1219.21
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Maintain & Operate Overtime Services | 6603082 |  |  |  | 1726.97 | -1726.97 | 1726.97
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Maintain & Operate Services | 6603083 | 6613.8 |  |  | 6336.56 | 277.24 | 6336.56
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Field Services Overtime | 6603098 |  |  |  | 2435.3 | -2435.3 | 2435.3
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Field Services | 6603099 | 7167.69 |  |  | 1312.76 | 5854.93 | 1312.76
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 107.47 | -107.47 | 107.47
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Maint & Operate Doubletime Services | 6603181 | 90.6 |  |  | 6211.47 | -6120.87 | 6211.47
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Field Services Doubletime | 6603184 |  |  |  | 4204.61 | -4204.61 | 4204.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | SCADA Services | 6603671 |  |  |  | 1324.08 | -1324.08 | 1324.08
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Account Services | 6603730 | 223.2 |  |  | 330.03 | -106.83 | 330.03
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Apprentice | 6603844 | 310.6 |  |  |  | 310.6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Hours - Straight Time | 6608193 | 265.88 |  |  | 1058.7 | -792.82 | 1058.7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Hours - Overtime | 6608194 | 199.41 |  |  | 526.15 | -326.74 | 526.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 101703.76 | -101703.76 | 101590.32 | -0.6 | -112.5 | 226.54 | [9 empty] | 113.44 | 113.44
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Estimating-Internal | 6010076 |  |  |  | 98300.61 | -98300.61 | 98300.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Mapping | 6010077 |  |  |  | 3403.15 | -3403.15 | 3289.71 | -0.6 | -112.5 | 226.54 | [9 empty] | 113.44 | 113.44
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Material Total | PGE1MATTOTAL | 340035 |  |  | 377102.85 | -37067.85 | 377102.85
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Material related expenses | PGE1MATERIAL | 340035 |  |  | 326507.49 | 13527.51 | 326507.49
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Materials Not Otherwise Classified | 5300000 |  |  |  | 4308.71 | -4308.71 | 4308.71
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Construction Supplies | 5300110 |  |  |  | 1346.22 | -1346.22 | 1346.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 79163.39 | -79163.39 | 79163.39
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Electrical Specialties | 5300140 | 340035 |  |  | 27962.43 | 312072.57 | 27962.43
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Gas & Water Specialties | 5300160 |  |  |  | -9381.05 | 9381.05 | -9381.05
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 210945.07 | -210945.07 | 210945.07
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Electl & Electronic Equipment Component | 5300200 |  |  |  | 14969.2 | -14969.2 | 14969.2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Communication & Signaling Equipment | 5300230 |  |  |  | 1220.5 | -1220.5 | 1220.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Transformers, Regulators & Capacitors | 5300260 |  |  |  | 6361.8 | -6361.8 | 6361.8
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Fabricated Structures | 5300270 |  |  |  | -10726.53 | 10726.53 | -10726.53
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 337.75 | -337.75 | 337.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Material Burden | PGE1MATBURD |  |  |  | 50595.36 | -50595.36 | 50595.36
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Material Burden | 6010000 |  |  |  | 50595.36 | -50595.36 | 50595.36
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Contract Total | PGE1CONTRACT | 1657255 |  |  | 1334743.79 | 322511.21 | 1296931.57 | -200 | -37501 | 75513.22 | [9 empty] | 37812.22 | 37812.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Consulting | PGE1CONSULTING | 61500 |  |  | 563.31 | 60936.69 | 563.31
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Consulting Services - Engineering | 5001230 |  |  |  | 279.65 | -279.65 | 279.65
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Consulting Services - Environmental Perm | 5001237 | 61500 |  |  |  | 61500
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Consulting Services - Other | 5001250 |  |  |  | 283.66 | -283.66 | 283.66
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC | 1595755 |  |  | 1334180.48 | 261574.52 | 1296368.26 | -200 | -37501 | 75513.22 | [9 empty] | 37812.22 | 37812.22
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Contracts | 5490000 | 427161 |  |  | 463760.37 | -36599.37 | 463760.37
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Electric Construction Contract | 5490001 | 658274 |  |  | 582812.54 | 75461.46 | 545055.93 |  | -37756.61 | 75513.22 | [9 empty] | 37756.61 | 37756.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Gas Construction Contract | 5490002 |  |  |  | 126153.9 | -126153.9 | 126153.9
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 364000 |  |  | 88642.51 | 275357.49 | 88642.51
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Environmental Contract | 5490015 | 67328 |  |  | 30260.06 | 37067.94 | 30204.45 | -200 | 255.61 | [10 empty] | 55.61 | 55.61
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Construction Inspection | 5490021 | 78992 |  |  | 42551.1 | 36440.9 | 42551.1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER | 79131 |  |  | 396797.36 | -317666.36 | 360143.27 | 12843.76 | 12055.77 | 13063.71 | -1309.15 | [8 empty] | 36654.09 | 36654.09
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE | 79123 |  |  | -47897.95 | 127020.95 | -45833.67 |  |  | -755.13 | -1309.15 | [8 empty] | -2064.28 | -2064.28
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 79123 |  |  | -47897.95 | 127020.95 | -45833.67 |  |  | -755.13 | -1309.15 | [8 empty] | -2064.28 | -2064.28
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Cash Discount earned | 5006310 |  |  |  | -2103 | 2103 | -38.72 |  |  | -755.13 | -1309.15 | [8 empty] | -2064.28 | -2064.28
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Permits/Fees | 5501090 | 78330 |  |  |  | 78330
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Land Acquisition Services | 5501093 | 793 |  |  | 816.38 | -23.38 | 816.38
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -46611.33 | 46611.33 | -46611.33
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Employee Related | PGE1EMPLREL | 8 |  |  | 31.65 | -23.65 | 31.65
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 24.15 | -24.15 | 24.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Reimbursed Mileage Expense | 5091140 |  |  |  | 24.15 | -24.15 | 24.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Meals | PGE1MEALS-EXP | 8 |  |  | 7.5 | 0.5 | 7.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Meals Expense | 5091100 | 8 |  |  | 7.5 | 0.5 | 7.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Order Overheads | PGE1OVERHEAD |  |  |  | 444663.66 | -444663.66 | 405945.29 | 12843.76 | 12055.77 | 13818.84 | [9 empty] | 38718.37 | 38718.37
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Capitalized A&G | PGE1CAPAG |  |  |  | 51501.15 | -51501.15 | 51234.29 | -0.22 | -14.01 | 281.09 | [9 empty] | 266.86 | 266.86
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Capitalized A&G | 6010050 |  |  |  | 51501.15 | -51501.15 | 51234.29 | -0.22 | -14.01 | 281.09 | [9 empty] | 266.86 | 266.86
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Labor Overheads | PGE1LABOROH |  |  |  | 174093.58 | -174093.58 | 173242.29 | -0.7 | -44.99 | 896.98 | [9 empty] | 851.29 | 851.29
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 157117.52 | -157117.52 | 156344.41 | -0.64 | -40.87 | 814.62 | [9 empty] | 773.11 | 773.11
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Paid Time Off | 6010100 |  |  |  | 26787.92 | -26787.92 | 26641.96 | -0.12 | -7.67 | 153.75 | [9 empty] | 145.96 | 145.96
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Indirect Labor - Electric | 6010106 |  |  |  | 41878.36 | -41878.36 | 41638.24 | -0.2 | -12.9 | 253.22 | [9 empty] | 240.12 | 240.12
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Indirect Labor - Gas | 6010107 |  |  |  | 111.36 | -111.36 | 111.36
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Indirect Labor - Environmental Land | 6010108 |  |  |  | 857.51 | -857.51 | 851.69 |  |  | 5.82 | [9 empty] | 5.82 | 5.82
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Indirect Labor - Cust Care | 6010110 |  |  |  | 92.58 | -92.58 | 92.58
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Indirect Labor - IT | 6010111 |  |  |  | 618.46 | -618.46 | 618.46
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 53918.28 | -53918.28 | 53700.97 | -0.18 | -11.68 | 229.17 | [9 empty] | 217.31 | 217.31
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 169.65 | -169.65 | 169.65
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 356.96 | -356.96 | 353.48 |  |  | 3.48 | [9 empty] | 3.48 | 3.48
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 38.27 | -38.27 | 38.27
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operation Mgmt & Support - IT | 6010119 |  |  |  | 280.37 | -280.37 | 280.37
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Fleet OH | 6010123 |  |  |  | 31847.38 | -31847.38 | 31847.38
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Fleet OH - Elec | 6010125 |  |  |  | 160.42 | -160.42 |  | -0.14 | -8.62 | 169.18 | [9 empty] | 160.42 | 160.42
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 16976.06 | -16976.06 | 16897.88 | -0.06 | -4.12 | 82.36 | [9 empty] | 78.18 | 78.18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Building Service Overhead | 6010112 |  |  |  | 10317.48 | -10317.48 | 10267.6 | -0.04 | -2.63 | 52.55 | [9 empty] | 49.88 | 49.88
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | IT Device OH | 6010113 |  |  |  | 6658.58 | -6658.58 | 6630.28 | -0.02 | -1.49 | 29.81 | [9 empty] | 28.3 | 28.3
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Other Overhead | PGE1OTHEROH |  |  |  | 127657.88 | -127657.88 | 127284.52 | -0.32 | -20.5 | 394.18 | [9 empty] | 373.36 | 373.36
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Benefits OH | 6010120 |  |  |  | 70822.02 | -70822.02 | 70546.85 | -0.24 | -15.32 | 290.73 | [9 empty] | 275.17 | 275.17
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Payroll Taxes OH | 6010121 |  |  |  | 23741.74 | -23741.74 | 23643.55 | -0.08 | -5.18 | 103.45 | [9 empty] | 98.19 | 98.19
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Minor Material OH | 6010122 |  |  |  | 33094.12 | -33094.12 | 33094.12
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 91411.05 | -91411.05 | 54184.19 | 12845 | 12135.27 | 12246.59 | [9 empty] | 37226.86 | 37226.86
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | AFUDC-Borrowed | 5590030 |  |  |  | 60278.08 | -60278.08 | 49772.44 | 3913.12 | 3281.21 | 3311.31 | [9 empty] | 10505.64 | 10505.64
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | AFUDC-Equity | 5590031 |  |  |  | 31132.97 | -31132.97 | 4411.75 | 8931.88 | 8854.06 | 8935.28 | [9 empty] | 26721.22 | 26721.22
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Order Financial Costs | PGE1ORDFIN | 3891537.89 |  | 19830 | 2187092.09 | 1704445.8 | 2112114.28 | 1287.84 | -72375.41 | 126255.38 | -20 | [7 empty] | 19830 | 55147.81 | 74977.81
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3891537.89 |  | 19830 | 2187092.09 | 1704445.8 | 2112114.28 | 1287.84 | -72375.41 | 126255.38 | -20 | [7 empty] | 19830 | 55147.81 | 74977.81
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Activity Type Total | PGE1ACTV-TOT | 451471.89 |  |  | 118320.28 | 333151.61 | 117407.96 | 324 | -141.44 | 729.76 | [9 empty] | 912.32 | 912.32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Activity Types | PGE1ACTVTYPES | 451471.89 |  |  | 118320.28 | 333151.61 | 117407.96 | 324 | -141.44 | 729.76 | [9 empty] | 912.32 | 912.32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Activity Types - Internal | PGE1ACTV-INT | 451349.17 |  |  | 118142.04 | 333207.13 | 117289.96 | 324 | -141.44 | 669.52 | [9 empty] | 852.08 | 852.08
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 451349.17 |  |  | 12667.91 | 438681.26 | 11981.31 | 324 | 74.45 | 288.15 | [9 empty] | 686.6 | 686.6
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Activity Type Cost Adjustment | 5590045
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Internal Services - Budget | 5600000 | 439352 |  |  |  | 439352
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Administration | 6603000 | 3227.63 |  |  | 3088.32 | 139.31 | 3088.32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Construction | 6603001 |  |  |  | 199.68 | -199.68 | 199.68
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Acquisition - Misc | 6603004 |  |  |  | 2575.13 | -2575.13 | 2218.73 | 291.6 |  | 64.8 | [9 empty] | 356.4 | 356.4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Construction Overtime Services | 6603021 |  |  |  | 249.9 | -249.9 | 249.9
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Engineering/Mapping | 6603022 | 148.84 |  |  | 442.77 | -293.93 | 144.97 |  | 74.45 | 223.35 | [9 empty] | 297.8 | 297.8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Environmental Planning & Permitting-Misc | 6603027 | 67.95 |  |  | 453.38 | -385.43 | 453.38
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 1220.3 | -1220.3 | 1220.3
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Switching Operator Service | 6603068 | 1209.76 |  |  |  | 1209.76
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Management Services | 6603076 |  |  |  | 1200.69 | -1200.69 | 1200.69
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Maintain & Operate Services | 6603083 | 3352.2 |  |  | 366.24 | 2985.96 | 366.24
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Field Services | 6603099 | 3628.09 |  |  |  | 3628.09
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Administrative Services - OT | 6603150 |  |  |  | 322.95 | -322.95 | 322.95
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Maint & Operate Doubletime Services | 6603181 |  |  |  | 313.22 | -313.22 | 313.22
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Rights - Misc | 6603227 |  |  |  | 824.84 | -824.84 | 792.44 | 32.4 | [11 empty] | 32.4 | 32.4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Account Services | 6603730 | 362.7 |  |  | 770.28 | -407.58 | 770.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Manage L&EM | 6603823 |  |  |  | 640.21 | -640.21 | 640.21
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 105474.13 | -105474.13 | 105308.65 |  | -215.89 | 381.37 | [9 empty] | 165.48 | 165.48
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Estimating-Internal | 6010076 |  |  |  | 101516.43 | -101516.43 | 101516.43
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Mapping | 6010077 |  |  |  | 3957.7 | -3957.7 | 3792.22 |  | -215.89 | 381.37 | [9 empty] | 165.48 | 165.48
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Activity Types - Contractors | PGE1ACTV-CONTR | 122.72 |  |  | 178.24 | -55.52 | 118 |  |  | 60.24 | [9 empty] | 60.24 | 60.24
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Contractor Activity Types | PGE1ACTV-OTH-C | 122.72 |  |  | 178.24 | -55.52 | 118 |  |  | 60.24 | [9 empty] | 60.24 | 60.24
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Contractor Consultant | 6608158 | 122.72 |  |  | 178.24 | -55.52 | 118 |  |  | 60.24 | [9 empty] | 60.24 | 60.24
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Material Total | PGE1MATTOTAL | 275292 |  |  | 219246.08 | 56045.92 | 219246.08
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Material related expenses | PGE1MATERIAL | 275292 |  |  | 191596.95 | 83695.05 | 191596.95
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Materials Not Otherwise Classified | 5300000 |  |  |  | 1603.58 | -1603.58 | 1603.58
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Construction Supplies | 5300110 |  |  |  | 1794.38 | -1794.38 | 1794.38
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 32722.21 | -32722.21 | 32722.21
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Electrical Specialties | 5300140 | 275292 |  |  | 22043.74 | 253248.26 | 22043.74
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas & Water Specialties | 5300160 |  |  |  | -243.32 | 243.32 | -243.32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 114255.73 | -114255.73 | 114255.73
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Electl & Electronic Equipment Component | 5300200 |  |  |  | 10328.35 | -10328.35 | 10328.35
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Fabricated Structures | 5300270 |  |  |  | 8836.68 | -8836.68 | 8836.68
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 255.6 | -255.6 | 255.6
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Material Burden | PGE1MATBURD |  |  |  | 27649.13 | -27649.13 | 27649.13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Material Burden | 6010000 |  |  |  | 27649.13 | -27649.13 | 27649.13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Contract Total | PGE1CONTRACT | 2810036 |  |  | 1568048.31 | 1241987.69 | 1512887.61 |  | -71963.24 | 127123.94 | [9 empty] | 55160.7 | 55160.7
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Consulting | PGE1CONSULTING | 26697 |  |  | 357.72 | 26339.28 | 357.72
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Consulting Services - Engineering | 5001230 |  |  |  | 43.31 | -43.31 | 43.31
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Consulting Services - Environmental Perm | 5001237 | 26697 |  |  | 30.75 | 26666.25 | 30.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Consulting Services - Other | 5001250 |  |  |  | 283.66 | -283.66 | 283.66
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Contract | PGE1OTHCONTRAC | 2783339 |  |  | 1567690.59 | 1215648.41 | 1512529.89 |  | -71963.24 | 127123.94 | [9 empty] | 55160.7 | 55160.7
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Contracts | 5490000 | 1278000 |  |  | 397073.08 | 880926.92 | 397073.08
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Electric Construction Contract | 5490001 | 1376019 |  |  | 947660.1 | 428358.9 | 892271.44 |  | -71985.28 | 127373.94 | [9 empty] | 55388.66 | 55388.66
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas Construction Contract | 5490002 |  |  |  | 37591.2 | -37591.2 | 37591.2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 105769.23 | -105769.23 | 105769.23
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Environmental Contract | 5490015 | 6472 |  |  | 17199.18 | -10727.18 | 17427.14 |  | 22.04 | -250 | [9 empty] | -227.96 | -227.96
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Construction Inspection | 5490021 | 82848 |  |  | 62397.8 | 20450.2 | 62397.8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Traffic Control Contracts | 5490027 | 40000 |  |  |  | 40000
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Order Other Costs | PGE1ORD-OTHER | 354738 |  | 19830 | 281477.42 | 73260.58 | 262572.63 | 963.84 | -270.73 | -1598.32 | -20 | [7 empty] | 19830 | -925.21 | 18904.79
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Cost Elements | PGE1OTHERCE | 354688 |  | 19830 | -14530.03 | 369218.03 | -31820.31 | 417.82 | 24.68 | -2962.22 | -20 | [7 empty] | 19830 | -2539.72 | 17290.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 354688 |  | 19830 | -14530.03 | 369218.03 | -31820.31 | 417.82 | 24.68 | -2962.22 | -20 | [7 empty] | 19830 | -2539.72 | 17290.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Cash Discount earned | 5006310 |  |  |  | -4749.92 | 4749.92 | -1712.7 |  |  | -3037.22 | [9 empty] | -3037.22 | -3037.22
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Permits/Fees | 5501090 | 1999 |  |  |  | 1999
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Acquisition Services | 5501093 | 247 |  |  | 11271.14 | -11024.14 | 10773.64 | 417.82 | 24.68 | 75 | -20 | [8 empty] | 497.5 | 497.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Land Fees | 5501094 |  |  |  | 11245.95 | -11245.95 | 11245.95
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Cost Adjustments | 5590042 |  |  |  | -1722.96 | 1722.96 | -1722.96
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 352442 |  | 19830 | -30574.24 | 383016.24 | -50404.24 | [11 empty] | 19830 |  | 19830
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Employee Related | PGE1EMPLREL |  |  |  | 268.07 | -268.07 | 268.07
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 268.07 | -268.07 | 268.07
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Reimbursed Mileage Expense | 5091140 |  |  |  | 268.07 | -268.07 | 268.07
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Order Overheads | PGE1OVERHEAD | 50 |  |  | 295739.38 | -295689.38 | 294124.87 | 546.02 | -295.41 | 1363.9 | [9 empty] | 1614.51 | 1614.51
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Capitalized A&G | PGE1CAPAG |  |  |  | 45429.81 | -45429.81 | 45114.79 | 119.3 | -52.08 | 247.8 | [9 empty] | 315.02 | 315.02
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Capitalized A&G | 6010050 |  |  |  | 45429.81 | -45429.81 | 45114.79 | 119.3 | -52.08 | 247.8 | [9 empty] | 315.02 | 315.02
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Labor Overheads | PGE1LABOROH |  |  |  | 149168.3 | -149168.3 | 148283.8 | 278.17 | -167.19 | 773.52 | [9 empty] | 884.5 | 884.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 135188.04 | -135188.04 | 134392.7 | 248.28 | -151.88 | 698.94 | [9 empty] | 795.34 | 795.34
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Paid Time Off | 6010100 |  |  |  | 20824.57 | -20824.57 | 20652.97 | 65.25 | -28.49 | 134.84 | [9 empty] | 171.6 | 171.6
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Indirect Labor - Electric | 6010106 |  |  |  | 32659.65 | -32659.65 | 32502.59 |  | -47.95 | 205.01 | [9 empty] | 157.06 | 157.06
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Indirect Labor - Gas | 6010107 |  |  |  | 163.2 | -163.2 | 163.2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Indirect Labor - Environmental Land | 6010108 |  |  |  | 3297.66 | -3297.66 | 3160.3 | 114.47 |  | 22.89 | [9 empty] | 137.36 | 137.36
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Indirect Labor - Cust Care | 6010110 |  |  |  | 221.23 | -221.23 | 221.23
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 48796.41 | -48796.41 | 48654.29 |  | -43.4 | 185.52 | [9 empty] | 142.12 | 142.12
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 248.61 | -248.61 | 248.61
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 1422.66 | -1422.66 | 1340.39 | 68.56 |  | 13.71 | [9 empty] | 82.27 | 82.27
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 46.18 | -46.18 | 46.18
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Fleet OH | 6010123 |  |  |  | 27402.94 | -27402.94 | 27402.94
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Fleet OH - Elec | 6010125 |  |  |  | 104.93 | -104.93 |  |  | -32.04 | 136.97 | [9 empty] | 104.93 | 104.93
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 13980.26 | -13980.26 | 13891.1 | 29.89 | -15.31 | 74.58 | [9 empty] | 89.16 | 89.16
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Building Service Overhead | 6010112 |  |  |  | 8456.1 | -8456.1 | 8399.22 | 19.07 | -9.77 | 47.58 | [9 empty] | 56.88 | 56.88
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | IT Device OH | 6010113 |  |  |  | 5524.16 | -5524.16 | 5491.88 | 10.82 | -5.54 | 27 | [9 empty] | 32.28 | 32.28
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Overhead | PGE1OTHEROH |  |  |  | 97345.48 | -97345.48 | 96930.49 | 148.55 | -76.14 | 342.58 | [9 empty] | 414.99 | 414.99
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Benefits OH | 6010120 |  |  |  | 58556.25 | -58556.25 | 58249.45 | 111.03 | -56.91 | 252.68 | [9 empty] | 306.8 | 306.8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Payroll Taxes OH | 6010121 |  |  |  | 19592.92 | -19592.92 | 19484.73 | 37.52 | -19.23 | 89.9 | [9 empty] | 108.19 | 108.19
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Minor Material OH | 6010122 |  |  |  | 19196.31 | -19196.31 | 19196.31
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | AFUDC Costs | PGE1AFUDCDIR | 50 |  |  | 3795.79 | -3745.79 | 3795.79
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | AFUDC-Borrowed | 5590030 |  |  |  | 4241.52 | -4241.52 | 4241.52
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | AFUDC-Equity | 5590031 | 50 |  |  | -445.73 | 495.73 | -445.73
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Financial Costs | PGE1ORDFIN | 4025666.38 |  | 1766414 | 3448895.92 | 576770.46 | 1036914.83 | 138183.81 | 180505.04 | 355845.39 | -28967.15 |  |  |  |  | 1000000 | 766414 |  |  | 645567.09 | 2411981.09
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4025666.38 |  | 1766414 | 3448895.92 | 576770.46 | 1036914.83 | 138183.81 | 180505.04 | 355845.39 | -28967.15 |  |  |  |  | 1000000 | 766414 |  |  | 645567.09 | 2411981.09
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 444934.38 |  |  | 240807.55 | 204126.83 | 81934.9 | 38755.91 | 36834.19 | 81197.94 | 2084.61 | [8 empty] | 158872.65 | 158872.65
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Types | PGE1ACTVTYPES | 444934.38 |  |  | 240807.55 | 204126.83 | 81934.9 | 38755.91 | 36834.19 | 81197.94 | 2084.61 | [8 empty] | 158872.65 | 158872.65
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 444934.38 |  |  | 240807.55 | 204126.83 | 81934.9 | 38755.91 | 36834.19 | 81197.94 | 2084.61 | [8 empty] | 158872.65 | 158872.65
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 444934.38 |  |  | 215167.71 | 229766.67 | 57975.81 | 38411.96 | 36353.64 | 80341.69 | 2084.61 | [8 empty] | 157191.9 | 157191.9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Internal Services - Budget | 5600000 | 357852 |  |  |  | 357852
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Administration | 6603000 | 407.7 |  |  | 1082.74 | -675.04 | 943.46 | 139.28 | [11 empty] | 139.28 | 139.28
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction | 6603001 | 1131.68 |  |  | 165176.03 | -164044.35 | 44874.86 | 33933.72 | 32025.8 | 54341.65 | [9 empty] | 120301.17 | 120301.17
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Analyst Services | 6603005 |  |  |  | 55.69 | -55.69 |  | 55.69 | [11 empty] | 55.69 | 55.69
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 27820.77 | -27820.77 | 8501.55 | 4283.27 | 4327.84 | 10708.11 | [9 empty] | 19319.22 | 19319.22
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Engineering/Mapping | 6603022 | 17146.18 |  |  | 14068.19 | 3077.99 | 592.72 |  |  | 11390.86 | 2084.61 | [8 empty] | 13475.47 | 13475.47
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Engineering Services | 6603023
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Environmental Services | 6603024 | 8154 |  |  |  | 8154
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 67.95 |  |  | 153.88 | -85.93 | 84.24 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Management Services | 6603076 | 2668.2 |  |  | 2668.2 |  | 2668.2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Maintain & Operate Services | 6603083 | 16579.8 |  |  |  | 16579.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Field Services | 6603099 | 16193.67 |  |  |  | 16193.67
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Engineering/Mapping Services Overtime | 6603106 | 74.42 |  |  | 107.47 | -33.05 | 107.47
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction Doubletime Services | 6603180 |  |  |  | 3831.43 | -3831.43 |  |  |  | 3831.43 | [9 empty] | 3831.43 | 3831.43
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Land Rights - Misc | 6603227 | 16256.25 |  |  |  | 16256.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Account Services | 6603730 | 8402.53 |  |  | 203.31 | 8199.22 | 203.31
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Apprentice OT | 6603845
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 25639.84 | -25639.84 | 23959.09 | 343.95 | 480.55 | 856.25 | [9 empty] | 1680.75 | 1680.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 21950.73 | -21950.73 | 21950.73
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Mapping | 6010077 |  |  |  | 3689.11 | -3689.11 | 2008.36 | 343.95 | 480.55 | 856.25 | [9 empty] | 1680.75 | 1680.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Material Total | PGE1MATTOTAL | 259580 |  |  | 225394.54 | 34185.46 | 203648.92 | 10906.02 | 7764.99 | 3074.61 | [9 empty] | 21745.62 | 21745.62
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Material related expenses | PGE1MATERIAL | 259580 |  |  | 197954.36 | 61625.64 | 178979.12 | 9516.6 | 6775.73 | 2682.91 | [9 empty] | 18975.24 | 18975.24
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Materials Not Otherwise Classified | 5300000 |  |  |  | 1320.51 | -1320.51 | 1320.51
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction Supplies | 5300110 |  |  |  | 3301.23 | -3301.23 | 610.15 | 2691.08 | [11 empty] | 2691.08 | 2691.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 33476.92 | -33476.92 | 29285.09 | 208.42 | 3983.41 | [10 empty] | 4191.83 | 4191.83
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Electrical Specialties | 5300140 | 259580 |  |  | 21356.11 | 238223.89 | 19300.59 | 465.02 | 1590.5 | [10 empty] | 2055.52 | 2055.52
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 97.9 | -97.9 | 97.9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 121650.98 | -121650.98 | 111614.17 | 6152.08 | 1201.82 | 2682.91 | [9 empty] | 10036.81 | 10036.81
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Electl & Electronic Equipment Component | 5300200 |  |  |  | 29.3 | -29.3 | 29.3
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 16640.88 | -16640.88 | 16640.88
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 80.53 | -80.53 | 80.53
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 27440.18 | -27440.18 | 24669.8 | 1389.42 | 989.26 | 391.7 | [9 empty] | 2770.38 | 2770.38
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Material Burden | 6010000 |  |  |  | 27440.18 | -27440.18 | 24669.8 | 1389.42 | 989.26 | 391.7 | [9 empty] | 2770.38 | 2770.38
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Contract Total | PGE1CONTRACT | 2338404 |  |  | 676420.36 | 1661983.64 | 566821.28 |  | 51122.26 | 89658.3 | -31181.48 | [8 empty] | 109599.08 | 109599.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 52.31 | -52.31 | 52.31
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 52.31 | -52.31 | 52.31
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Contract | PGE1OTHCONTRAC | 2338404 |  |  | 676368.05 | 1662035.95 | 566768.97 |  | 51122.26 | 89658.3 | -31181.48 | [8 empty] | 109599.08 | 109599.08
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Contracts | 5490000 | 523382 |  |  | 519984.83 | 3397.17 | 519756.11 |  |  | 1378.72 | -1150 | [8 empty] | 228.72 | 228.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Electric Construction Contract | 5490001 | 1708200 |  |  | 99109.79 | 1609090.21 |  |  | 51053.41 | 70337.86 | -22281.48 | [8 empty] | 99109.79 | 99109.79
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 35471.98 | -35471.98 | 35471.98
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Environmental Contract | 5490015 | 4330 |  |  | 6469.04 | -2139.04 | 6400.19 |  | 68.85 | 250 | -250 | [8 empty] | 68.85 | 68.85
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction Inspection | 5490021 | 102492 |  |  | 1491.97 | 101000.03 |  |  |  | 1491.97 | [9 empty] | 1491.97 | 1491.97
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Traffic Control Contracts | 5490027 |  |  |  | 8524.44 | -8524.44 | 5140.69 |  |  | 10883.75 | -7500 | [8 empty] | 3383.75 | 3383.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Paving Contracts | 5490500 |  |  |  | 5316 | -5316 |  |  |  | 5316 | [9 empty] | 5316 | 5316
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 982748 |  | 1766414 | 2306273.47 | -1323525.47 | 184509.73 | 88521.88 | 84783.6 | 181914.54 | 129.72 |  |  |  |  | 1000000 | 766414 |  |  | 355349.74 | 2121763.74
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Cost Elements | PGE1OTHERCE | 982748 |  | 1766414 | 1760050.42 | -777302.42 | -11675.63 |  | -33.83 | 5216.16 | 129.72 |  |  |  |  | 1000000 | 766414 |  |  | 5312.05 | 1771726.05
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 982748 |  | 1766414 | 1760050.42 | -777302.42 | -11675.63 |  | -33.83 | 5216.16 | 129.72 |  |  |  |  | 1000000 | 766414 |  |  | 5312.05 | 1771726.05
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -1423.29 | 1423.29 | -1355.62 |  | -33.83 | -33.84 | [9 empty] | -67.67 | -67.67
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Permits/Fees | 5501090 | 982315 |  |  | 389.16 | 981925.84 | 259.44 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Land Acquisition Services | 5501093 | 433 |  |  | 527.85 | -94.85 | 527.85
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1766414 | 1755306.7 | -1755306.7 | -11107.3 | [8 empty] | 1000000 | 766414 |  |  |  | 1766414
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 546223.05 | -546223.05 | 196185.36 | 88521.88 | 84817.43 | 176698.38 | [9 empty] | 350037.69 | 350037.69
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 87641.47 | -87641.47 | 29912.11 | 14269.93 | 13562.35 | 29897.08 | [9 empty] | 57729.36 | 57729.36
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 87641.47 | -87641.47 | 29912.11 | 14269.93 | 13562.35 | 29897.08 | [9 empty] | 57729.36 | 57729.36
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 281428.86 | -281428.86 | 96054.69 | 45816.88 | 43587.71 | 95969.58 | [9 empty] | 185374.17 | 185374.17
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 255843.23 | -255843.23 | 87581.26 | 41552.28 | 39548.87 | 87160.82 | [9 empty] | 168261.97 | 168261.97
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Paid Time Off | 6010100 |  |  |  | 51607.89 | -51607.89 | 20030.78 | 7805.44 | 7418.4 | 16353.27 | [9 empty] | 31577.11 | 31577.11
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 82740.17 | -82740.17 | 29678.74 | 13072.16 | 12486.79 | 27502.48 | [9 empty] | 53061.43 | 53061.43
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Indirect Labor - Gas | 6010107
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 491.61 | -491.61 | 398.12 | 68.89 |  | 24.6 | [9 empty] | 93.49 | 93.49
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 48.43 | -48.43 | 48.43
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 69764.9 | -69764.9 | 21743.51 | 11830.49 | 11300.73 | 24890.17 | [9 empty] | 48021.39 | 48021.39
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Operation Mgmt & Support - Gas | 6010115
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 217.3 | -217.3 | 161.31 | 41.25 |  | 14.74 | [9 empty] | 55.99 | 55.99
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Fleet OH | 6010123 |  |  |  | 15520.37 | -15520.37 | 15520.37
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 35452.56 | -35452.56 |  | 8734.05 | 8342.95 | 18375.56 | [9 empty] | 35452.56 | 35452.56
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Fleet OH - Gas | 6010126
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 25585.63 | -25585.63 | 8473.43 | 4264.6 | 4038.84 | 8808.76 | [9 empty] | 17112.2 | 17112.2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 16441.31 | -16441.31 | 5524.89 | 2720.53 | 2576.51 | 5619.38 | [9 empty] | 10916.42 | 10916.42
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | IT Device OH | 6010113 |  |  |  | 9144.32 | -9144.32 | 2948.54 | 1544.07 | 1462.33 | 3189.38 | [9 empty] | 6195.78 | 6195.78
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 139737.42 | -139737.42 | 54747.74 | 21982.28 | 20636.21 | 42371.19 | [9 empty] | 84989.68 | 84989.68
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Benefits OH | 6010120 |  |  |  | 92871.46 | -92871.46 | 30917.2 | 15851.41 | 15012.21 | 31090.64 | [9 empty] | 61954.26 | 61954.26
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 32506.82 | -32506.82 | 11017.51 | 5355.45 | 5071.91 | 11061.95 | [9 empty] | 21489.31 | 21489.31
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Minor Material OH | 6010122 |  |  |  | 14359.14 | -14359.14 | 12813.03 | 775.42 | 552.09 | 218.6 | [9 empty] | 1546.11 | 1546.11
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 37415.3 | -37415.3 | 15470.82 | 6452.79 | 7031.16 | 8460.53 | [9 empty] | 21944.48 | 21944.48
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 18624.1 | -18624.1 | 12489.31 | 1946.05 | 1901.13 | 2287.61 | [9 empty] | 6134.79 | 6134.79
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 18791.2 | -18791.2 | 2981.51 | 4506.74 | 5130.03 | 6172.92 | [9 empty] | 15809.69 | 15809.69
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Financial Costs | PGE1ORDFIN | 2679486.3 |  | 1947556 | 2412866.92 | 266619.38 | 450434.84 | 3022.85 | 2878.44 | 49955.07 | -40980.28 | [6 empty] | 1000000 | 947556 | 14876.08 | 1962432.08
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2679486.3 |  | 1947556 | 2412866.92 | 266619.38 | 450434.84 | 3022.85 | 2878.44 | 49955.07 | -40980.28 | [6 empty] | 1000000 | 947556 | 14876.08 | 1962432.08
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 488986.3 |  |  | 13687.09 | 475299.21 | 13201.07 | 196.34 | 0.75 | 288.93 | [9 empty] | 486.02 | 486.02
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Activity Types | PGE1ACTVTYPES | 488986.3 |  |  | 13687.09 | 475299.21 | 13201.07 | 196.34 | 0.75 | 288.93 | [9 empty] | 486.02 | 486.02
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 488986.3 |  |  | 13687.09 | 475299.21 | 13201.07 | 196.34 | 0.75 | 288.93 | [9 empty] | 486.02 | 486.02
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 488986.3 |  |  | 10056.78 | 478929.52 | 9571.51 | 197.09 |  | 288.18 | [9 empty] | 485.27 | 485.27
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Internal Services - Budget | 5600000 | 196175 |  |  |  | 196175
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Administration | 6603000 | 2174.4 |  |  | 1354.55 | 819.85 | 1145.63 | 139.28 |  | 69.64 | [9 empty] | 208.92 | 208.92
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Construction | 6603001 | 252930.48 |  |  | 1284.59 | 251645.89 | 1284.59
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Acquisition - Misc | 6603004 | 127.5 |  |  | 95.1 | 32.4 | 95.1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Analyst Services | 6603005 |  |  |  | 55.69 | -55.69 |  | 55.69 | [11 empty] | 55.69 | 55.69
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Engineering/Mapping | 6603022 | 9946.48 |  |  | 1260.25 | 8686.23 | 1111.35 |  |  | 148.9 | [9 empty] | 148.9 | 148.9
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Environmental Services | 6603024 | 4552.65 |  |  | 269.56 | 4283.09 | 269.56
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 67.95 |  |  | 103.34 | -35.39 | 33.7 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Management Services | 6603076 | 5469.81 |  |  | 2801.61 | 2668.2 | 2801.61
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Maintain & Operate Services | 6603083 | 2899.2 |  |  |  | 2899.2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Field Services | 6603099 | 3097.15 |  |  |  | 3097.15
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Engineering/Mapping Services Overtime | 6603106 | 74.42 |  |  | 107.47 | -33.05 | 107.47
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Land Rights - Misc | 6603227 | 7522.5 |  |  |  | 7522.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Electric Estimating | 6603466 |  |  |  | 1529.49 | -1529.49 | 1529.49
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Electric Estimating Overtime | 6603467 |  |  |  | 683.4 | -683.4 | 681.28 | 2.12 | [11 empty] | 2.12 | 2.12
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Account Services | 6603730 | 3880.81 |  |  | 444.34 | 3436.47 | 444.34
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Manage L&EM | 6603823 | 67.95 |  |  | 67.39 | 0.56 | 67.39
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 3630.31 | -3630.31 | 3629.56 | -0.75 | 0.75 | 0.75 | [9 empty] | 0.75 | 0.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 2545.34 | -2545.34 | 2545.34
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Mapping | 6010077 |  |  |  | 1084.97 | -1084.97 | 1084.22 | -0.75 | 0.75 | 0.75 | [9 empty] | 0.75 | 0.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Total | PGE1MATTOTAL | 177450 |  |  |  | 177450
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material related expenses | PGE1MATERIAL | 177450 |  |  |  | 177450
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Electrical Specialties | 5300140 | 177450 |  |  |  | 177450
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Burden | PGE1MATBURD
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Burden | 6010000
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Contract Total | PGE1CONTRACT | 860347 |  |  | 404770.64 | 455576.36 | 404770.64 | -250 | 250 | 41110 | -41110
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 104.63 | -104.63 | 104.63
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 104.63 | -104.63 | 104.63
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Contract | PGE1OTHCONTRAC | 860347 |  |  | 404666.01 | 455680.99 | 404666.01 | -250 | 250 | 41110 | -41110
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Contracts | 5490000 | 519847 |  |  | 374685.71 | 145161.29 | 374685.71
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Gas Construction Contract | 5490002 | 240000 |  |  |  | 240000
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 21991.94 | -21991.94 | 21991.94 |  |  | 40860 | -40860
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Environmental Contract | 5490015 | 40000 |  |  | 7988.36 | 32011.64 | 7988.36 | -250 | 250 | 250 | -250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Traffic Control Contracts | 5490027 | 30500 |  |  |  | 30500
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Paving Contracts | 5490500 | 30000 |  |  |  | 30000
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 1152703 |  | 1947556 | 1994409.19 | -841706.19 | 32463.13 | 3076.51 | 2627.69 | 8556.14 | 129.72 | [6 empty] | 1000000 | 947556 | 14390.06 | 1961946.06
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Cost Elements | PGE1OTHERCE | 1152703 |  | 1947556 | 1952998.7 | -800295.7 | 62.98 |  |  | 5250 | 129.72 | [6 empty] | 1000000 | 947556 | 5379.72 | 1952935.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1152703 |  | 1947556 | 1952998.7 | -800295.7 | 62.98 |  |  | 5250 | 129.72 | [6 empty] | 1000000 | 947556 | 5379.72 | 1952935.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Rents | 5007000 | 40000 |  |  |  | 40000
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Permits/Fees | 5501090 | 1112056 |  |  | 778.32 | 1111277.68 | 648.6 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Land Acquisition Services | 5501093 | 647 |  |  | 694.1 | -47.1 | 694.1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Postage | 5510010 |  |  |  | 8.25 | -8.25 | 8.25
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1947556 | 1946268.03 | -1946268.03 | -1287.97 | [10 empty] | 1000000 | 947556 |  | 1947556
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 41410.49 | -41410.49 | 32400.15 | 3076.51 | 2627.69 | 3306.14 | [9 empty] | 9010.34 | 9010.34
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 5064.46 | -5064.46 | 4885.51 | 72.29 | 0.28 | 106.38 | [9 empty] | 178.95 | 178.95
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 5064.46 | -5064.46 | 4885.51 | 72.29 | 0.28 | 106.38 | [9 empty] | 178.95 | 178.95
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 14517.82 | -14517.82 | 14051.47 | 169 | 0.88 | 296.47 | [9 empty] | 466.35 | 466.35
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 13223.52 | -13223.52 | 12804.41 | 150.89 | 0.8 | 267.42 | [9 empty] | 419.11 | 419.11
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Paid Time Off | 6010100 |  |  |  | 2286.08 | -2286.08 | 2188.18 | 39.55 | 0.15 | 58.2 | [9 empty] | 97.9 | 97.9
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 2812.61 | -2812.61 | 2761.16 | 0.47 | 0.25 | 50.73 | [9 empty] | 51.45 | 51.45
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 709.66 | -709.66 | 591.57 | 68.89 |  | 49.2 | [9 empty] | 118.09 | 118.09
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 133.39 | -133.39 | 133.39
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 4305.23 | -4305.23 | 4258.67 | 0.42 | 0.23 | 45.91 | [9 empty] | 46.56 | 46.56
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 326 | -326 | 255.27 | 41.25 |  | 29.48 | [9 empty] | 70.73 | 70.73
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Fleet OH | 6010123 |  |  |  | 2616.17 | -2616.17 | 2616.17
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 34.38 | -34.38 |  | 0.31 | 0.17 | 33.9 | [9 empty] | 34.38 | 34.38
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 1294.3 | -1294.3 | 1247.06 | 18.11 | 0.08 | 29.05 | [9 empty] | 47.24 | 47.24
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 803.87 | -803.87 | 773.73 | 11.56 | 0.05 | 18.53 | [9 empty] | 30.14 | 30.14
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | IT Device OH | 6010113 |  |  |  | 490.43 | -490.43 | 473.33 | 6.55 | 0.03 | 10.52 | [9 empty] | 17.1 | 17.1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 7011.03 | -7011.03 | 6781.52 | 90.13 | 0.4 | 138.98 | [9 empty] | 229.51 | 229.51
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Benefits OH | 6010120 |  |  |  | 5242.95 | -5242.95 | 5072.8 | 67.36 | 0.3 | 102.49 | [9 empty] | 170.15 | 170.15
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 1768.08 | -1768.08 | 1708.72 | 22.77 | 0.1 | 36.49 | [9 empty] | 59.36 | 59.36
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Minor Material OH | 6010122
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 14817.18 | -14817.18 | 6681.65 | 2745.09 | 2626.13 | 2764.31 | [9 empty] | 8135.53 | 8135.53
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 7666.69 | -7666.69 | 5379.04 | 830.15 | 710.07 | 747.43 | [9 empty] | 2287.65 | 2287.65
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 7150.49 | -7150.49 | 1302.61 | 1914.94 | 1916.06 | 2016.88 | [9 empty] | 5847.88 | 5847.88
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Financial Costs | PGE1ORDFIN | 3206350.69 |  | 2503182 | 3333954.61 | -127603.92 | 476027.17 | 3294.16 | 31282.59 | 329760.69 | -9592 | [5 empty] | 1000000 | 1000000 | 503182 | 354745.44 | 2857927.44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 3206350.69 |  | 2503182 | 3333954.61 | -127603.92 | 476027.17 | 3294.16 | 31282.59 | 329760.69 | -9592 | [5 empty] | 1000000 | 1000000 | 503182 | 354745.44 | 2857927.44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 636346.69 |  |  | 46822.48 | 589524.21 | 17325.98 | 56.74 | 8.15 | 22141.57 | 7290.04 | [8 empty] | 29496.5 | 29496.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Types | PGE1ACTVTYPES | 636346.69 |  |  | 46822.48 | 589524.21 | 17325.98 | 56.74 | 8.15 | 22141.57 | 7290.04 | [8 empty] | 29496.5 | 29496.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 636346.69 |  |  | 46822.48 | 589524.21 | 17325.98 | 56.74 | 8.15 | 22141.57 | 7290.04 | [8 empty] | 29496.5 | 29496.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 636346.69 |  |  | 36127.76 | 600218.93 | 6858.48 | 55.69 |  | 21923.55 | 7290.04 | [8 empty] | 29269.28 | 29269.28
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 136.65 | -136.65 | 136.65
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Internal Services - Budget | 5600000 | 357852 |  |  |  | 357852
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Administration | 6603000 | 2310.3 |  |  | 882.82 | 1427.48 | 673.9 |  |  | 208.92 | [9 empty] | 208.92 | 208.92
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Construction | 6603001 | 237329.14 |  |  | 24048.96 | 213280.18 | 1216.98 |  |  | 16017.98 | 6814 | [8 empty] | 22831.98 | 22831.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Acquisition - Misc | 6603004 | 1912.5 |  |  | 540.24 | 1372.26 | 475.44 |  |  | 64.8 | [9 empty] | 64.8 | 64.8
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Analyst Services | 6603005 |  |  |  | 55.69 | -55.69 |  | 55.69 | [11 empty] | 55.69 | 55.69
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 5889.33 | -5889.33 |  |  |  | 5487.75 | 401.58 | [8 empty] | 5889.33 | 5889.33
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Engineering/Mapping | 6603022 | 15007.04 |  |  | 445.28 | 14561.76 | 296.36 |  |  | 74.46 | 74.46 | [8 empty] | 148.92 | 148.92
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Engineering Services | 6603023
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Environmental Services | 6603024 | 1155.15 |  |  |  | 1155.15
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 203.85 |  |  | 356.05 | -152.2 | 286.41 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Switching Operator Service | 6603068 | 739.62 |  |  |  | 739.62
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Management Services | 6603076 | 4185.39 |  |  | 2575.81 | 1609.58 | 2575.81
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Maintain & Operate Services | 6603083 | 3533.4 |  |  |  | 3533.4
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Field Services | 6603099 | 3805.07 |  |  |  | 3805.07
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Engineering/Mapping Services Overtime | 6603106 | 74.42 |  |  | 107.47 | -33.05 | 107.47
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Rights - Misc | 6603227 |  |  |  | 126.78 | -126.78 | 126.78
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Account Services | 6603730 | 8170.86 |  |  | 895.29 | 7275.57 | 895.29
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Manage L&EM | 6603823 | 67.95 |  |  | 67.39 | 0.56 | 67.39
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 10694.72 | -10694.72 | 10467.5 | 1.05 | 8.15 | 218.02 | [9 empty] | 227.22 | 227.22
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 9379.91 | -9379.91 | 9379.91
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Mapping | 6010077 |  |  |  | 1314.81 | -1314.81 | 1087.59 | 1.05 | 8.15 | 218.02 | [9 empty] | 227.22 | 227.22
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material Total | PGE1MATTOTAL | 393746 |  |  | 233646.08 | 160099.92 |  |  | 23244.22 | 222521.03 | -12119.17 | [8 empty] | 233646.08 | 233646.08
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material related expenses | PGE1MATERIAL | 393746 |  |  | 204720.6 | 189025.4 |  |  | 20372.29 | 196467.48 | -12119.17 | [8 empty] | 204720.6 | 204720.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Construction Supplies | 5300110 |  |  |  | 1317.15 | -1317.15 |  |  | 102.14 | 1215.01 | [9 empty] | 1317.15 | 1317.15
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 46083.45 | -46083.45 |  |  | 589.24 | 57613.38 | -12119.17 | [8 empty] | 46083.45 | 46083.45
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Electrical Specialties | 5300140 |  |  |  | 33025.75 | -33025.75 |  |  | 13850.32 | 19175.43 | [9 empty] | 33025.75 | 33025.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Gas & Water Specialties | 5300160 |  |  |  | 372.53 | -372.53 |  |  | 372.53 | [10 empty] | 372.53 | 372.53
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 | 393746 |  |  | 103823.29 | 289922.71 |  |  | 4703.01 | 99120.28 | [9 empty] | 103823.29 | 103823.29
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Electl & Electronic Equipment Component | 5300200 |  |  |  | 1.9 | -1.9 |  |  | 1.9 | [10 empty] | 1.9 | 1.9
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 20096.53 | -20096.53 |  |  | 753.15 | 19343.38 | [9 empty] | 20096.53 | 20096.53
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 28925.48 | -28925.48 |  |  | 2871.93 | 26053.55 | [9 empty] | 28925.48 | 28925.48
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material Burden | 6010000 |  |  |  | 28925.48 | -28925.48 |  |  | 2871.93 | 26053.55 | [9 empty] | 28925.48 | 28925.48
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Contract Total | PGE1CONTRACT | 880097 |  |  | 425212.73 | 454884.27 | 418885.09 | 348.98 | 2716.74 | 8154.51 | -4892.59 | [8 empty] | 6327.64 | 6327.64
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 267.73 | -267.73 | 104.63 |  | 118.75 | 44.35 | [9 empty] | 163.1 | 163.1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Consulting Services - Engineering | 5001230 |  |  |  | 163.1 | -163.1 |  |  | 118.75 | 44.35 | [9 empty] | 163.1 | 163.1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 104.63 | -104.63 | 104.63
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Contract | PGE1OTHCONTRAC | 880097 |  |  | 424945 | 455152 | 418780.46 | 348.98 | 2597.99 | 8110.16 | -4892.59 | [8 empty] | 6164.54 | 6164.54
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Contracts | 5490000 | 508597 |  |  | 383414.14 | 125182.86 | 383414.14
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Electric Construction Contract | 5490001 |  |  |  | 2162 | -2162 |  |  |  | 2162 | [9 empty] | 2162 | 2162
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Gas Construction Contract | 5490002 | 181500 |  |  |  | 181500
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 28211.33 | -28211.33 | 28211.33
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Environmental Contract | 5490015 | 30000 |  |  | 11157.53 | 18842.47 | 7154.99 | 348.98 | 2597.99 | 5948.16 | -4892.59 | [8 empty] | 4002.54 | 4002.54
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Traffic Control Contracts | 5490027 | 130000 |  |  |  | 130000
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Paving Contracts | 5490500 | 30000 |  |  |  | 30000
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 1296161 |  | 2503182 | 2628273.32 | -1332112.32 | 39816.1 | 2888.44 | 5313.48 | 76943.58 | 129.72 | [5 empty] | 1000000 | 1000000 | 503182 | 85275.22 | 2588457.22
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Cost Elements | PGE1OTHERCE | 1296161 |  | 2503182 | 2504873.46 | -1208712.46 | -2302.52 |  |  | 3864.26 | 129.72 | [5 empty] | 1000000 | 1000000 | 503182 | 3993.98 | 2507175.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1296161 |  | 2503182 | 2504873.46 | -1208712.46 | -2302.52 |  |  | 3864.26 | 129.72 | [5 empty] | 1000000 | 1000000 | 503182 | 3993.98 | 2507175.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -1385.74 | 1385.74 |  |  |  | -1385.74 | [9 empty] | -1385.74 | -1385.74
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Permits/Fees | 5501090 | 1295467 |  |  | 1816.08 | 1293650.92 | 1686.36 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Acquisition Services | 5501093 | 694 |  |  | 741.6 | -47.6 | 741.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Postage | 5510010 |  |  |  | 15.85 | -15.85 | 15.85
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2503182 | 2498435.67 | -2498435.67 | -4746.33 | [9 empty] | 1000000 | 1000000 | 503182 |  | 2503182
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 123399.86 | -123399.86 | 42118.62 | 2888.44 | 5313.48 | 73079.32 | [9 empty] | 81281.24 | 81281.24
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 14666.12 | -14666.12 | 6489.69 | 20.9 | 3.01 | 8152.52 | [9 empty] | 8176.43 | 8176.43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 14666.12 | -14666.12 | 6489.69 | 20.9 | 3.01 | 8152.52 | [9 empty] | 8176.43 | 8176.43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 46505.76 | -46505.76 | 18878.06 | 49.04 | 159.53 | 27419.13 | [9 empty] | 27627.7 | 27627.7
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 40901.21 | -40901.21 | 17180.79 | 43.81 | 8.75 | 23667.86 | [9 empty] | 23720.42 | 23720.42
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Paid Time Off | 6010100 |  |  |  | 7584.63 | -7584.63 | 3112.24 | 11.43 | 1.64 | 4459.32 | [9 empty] | 4472.39 | 4472.39
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 11534.5 | -11534.5 | 4141.78 | 0.36 | 2.76 | 7389.6 | [9 empty] | 7392.72 | 7392.72
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 723.5 | -723.5 | 582.52 | 19.68 |  | 121.3 | [9 empty] | 140.98 | 140.98
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 308.6 | -308.6 | 308.6
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 12147.93 | -12147.93 | 5457.42 | 0.32 | 2.5 | 6687.69 | [9 empty] | 6690.51 | 6690.51
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 344.24 | -344.24 | 259.8 | 11.78 |  | 72.66 | [9 empty] | 84.44 | 84.44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Fleet OH | 6010123 |  |  |  | 3318.43 | -3318.43 | 3318.43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 4939.38 | -4939.38 |  | 0.24 | 1.85 | 4937.29 | [9 empty] | 4939.38 | 4939.38
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 5604.55 | -5604.55 | 1697.27 | 5.23 | 150.78 | 3751.27 | [9 empty] | 3907.28 | 3907.28
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 3524.4 | -3524.4 | 1031.82 | 3.34 | 96.19 | 2393.05 | [9 empty] | 2492.58 | 2492.58
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | IT Device OH | 6010113 |  |  |  | 2080.15 | -2080.15 | 665.45 | 1.89 | 54.59 | 1358.22 | [9 empty] | 1414.7 | 1414.7
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 45411.51 | -45411.51 | 9210.82 | 26.1 | 2402.5 | 33772.09 | [9 empty] | 36200.69 | 36200.69
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Benefits OH | 6010120 |  |  |  | 20721.83 | -20721.83 | 6901.78 | 19.5 | 560.49 | 13240.06 | [9 empty] | 13820.05 | 13820.05
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 7215.77 | -7215.77 | 2309.04 | 6.6 | 189.35 | 4710.78 | [9 empty] | 4906.73 | 4906.73
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Minor Material OH | 6010122 |  |  |  | 17473.91 | -17473.91 |  |  | 1652.66 | 15821.25 | [9 empty] | 17473.91 | 17473.91
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 16816.47 | -16816.47 | 7540.05 | 2792.4 | 2748.44 | 3735.58 | [9 empty] | 9276.42 | 9276.42
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 8842.24 | -8842.24 | 6242.67 | 846.38 | 743.14 | 1010.05 | [9 empty] | 2599.57 | 2599.57
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 7974.23 | -7974.23 | 1297.38 | 1946.02 | 2005.3 | 2725.53 | [9 empty] | 6676.85 | 6676.85
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Financial Costs | PGE1ORDFIN | 2796372.25 |  | 2004457 | 3339236.32 | -542864.07 | 973048.58 | 95427.33 | 63115.65 | 191290.06 | 11897.7 | [5 empty] | 1000000 | 1000000 | 4457 | 361730.74 | 2366187.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2796372.25 |  | 2004457 | 3339236.32 | -542864.07 | 973048.58 | 95427.33 | 63115.65 | 191290.06 | 11897.7 | [5 empty] | 1000000 | 1000000 | 4457 | 361730.74 | 2366187.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 588123.25 |  |  | 196000.03 | 392123.22 | 79063.53 | 25908.43 | 17558.72 | 58012.24 | 15457.11 | [8 empty] | 116936.5 | 116936.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Types | PGE1ACTVTYPES | 588123.25 |  |  | 196000.03 | 392123.22 | 79063.53 | 25908.43 | 17558.72 | 58012.24 | 15457.11 | [8 empty] | 116936.5 | 116936.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 588123.25 |  |  | 196000.03 | 392123.22 | 79063.53 | 25908.43 | 17558.72 | 58012.24 | 15457.11 | [8 empty] | 116936.5 | 116936.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 588123.25 |  |  | 189909.25 | 398214 | 73720.37 | 25726.89 | 17494.99 | 57509.89 | 15457.11 | [8 empty] | 116188.88 | 116188.88
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 273.31 | -273.31 | 273.31
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Electric Activity Charge - Non-Type A | 5590107 |  |  |  | -91.45 | 91.45 | -91.45
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Internal Services - Budget | 5600000 | 338615 |  |  |  | 338615
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Administration | 6603000 | 2038.5 |  |  | 1282.66 | 755.84 | 1213.02 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction | 6603001 | 181563.91 |  |  | 128714.08 | 52849.83 | 53782.78 | 17035 | 2725.6 | 42224.1 | 12946.6 | [8 empty] | 74931.3 | 74931.3
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Acquisition - Misc | 6603004 | 2040 |  |  | 31.7 | 2008.3 | 31.7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Analyst Services | 6603005 |  |  |  | 55.69 | -55.69 |  | 55.69 | [11 empty] | 55.69 | 55.69
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction Overtime Services | 6603021 | 636.57 |  |  | 19517.63 | -18881.06 | 1742.49 |  | 3452.99 | 12269.67 | 2052.48 | [8 empty] | 17775.14 | 17775.14
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Engineering/Mapping | 6603022 | 15602.4 |  |  | 33291.48 | -17689.08 | 12817.71 | 8636.2 | 11316.4 | 372.26 | 148.91 | [8 empty] | 20473.77 | 20473.77
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Engineering Services | 6603023
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Environmental Services | 6603024 |  |  |  | 269.56 | -269.56 | 269.56
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 679.5 |  |  | 103.34 | 576.16 | 33.7 |  |  |  | 69.64 | [8 empty] | 69.64 | 69.64
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Switching Operator Service | 6603068 | 528.88 |  |  |  | 528.88
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Management Services | 6603076 | 5336.4 |  |  | 2934.08 | 2402.32 | 2934.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Maintain & Operate Services | 6603083 | 16579.8 |  |  |  | 16579.8
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Field Services | 6603099 | 16193.67 |  |  |  | 16193.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Engineering/Mapping Services Overtime | 6603106 | 74.42 |  |  | 107.47 | -33.05 | 107.47
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction Doubletime Services | 6603180 |  |  |  | 2813.7 | -2813.7 |  |  |  | 2574.22 | 239.48 | [8 empty] | 2813.7 | 2813.7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Account Services | 6603730 | 8234.2 |  |  | 606 | 7628.2 | 606
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 6090.78 | -6090.78 | 5343.16 | 181.54 | 63.73 | 502.35 | [9 empty] | 747.62 | 747.62
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 3343.77 | -3343.77 | 3343.77
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Mapping | 6010077 |  |  |  | 2747.01 | -2747.01 | 1999.39 | 181.54 | 63.73 | 502.35 | [9 empty] | 747.62 | 747.62
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Material Total | PGE1MATTOTAL | 359835 |  |  | 167683.93 | 192151.07 | 167683.93
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Material related expenses | PGE1MATERIAL | 359835 |  |  | 146999.89 | 212835.11 | 146999.89
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Materials Not Otherwise Classified | 5300000 |  |  |  | 176.25 | -176.25 | 176.25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction Supplies | 5300110 |  |  |  | 543.57 | -543.57 | 543.57
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 23190.97 | -23190.97 | 23190.97
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Electrical Specialties | 5300140 |  |  |  | 14792.08 | -14792.08 | 14792.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Gas & Water Specialties | 5300160 |  |  |  | 248.25 | -248.25 | 248.25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 122.39 | -122.39 | 122.39
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 | 359835 |  |  | 94247.76 | 265587.24 | 94247.76
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 13609.43 | -13609.43 | 13609.43
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 69.19 | -69.19 | 69.19
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 20684.04 | -20684.04 | 20684.04
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Material Burden | 6010000 |  |  |  | 20684.04 | -20684.04 | 20684.04
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Contract Total | PGE1CONTRACT | 100000 |  |  | 562396.53 | -462396.53 | 552595.89 | 9407.03 | 2710.92 | 1242.1 | -3559.41 | [8 empty] | 9800.64 | 9800.64
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 388.14 | -388.14 | 303.89 |  | 43.05 | 82.28 | -41.08 | [8 empty] | 84.25 | 84.25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Consulting Services - Engineering | 5001230 |  |  |  | 126.56 | -126.56 | 42.31 |  | 43.05 | 82.28 | -41.08 | [8 empty] | 84.25 | 84.25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 261.58 | -261.58 | 261.58
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Contract | PGE1OTHCONTRAC | 100000 |  |  | 562008.39 | -462008.39 | 552292 | 9407.03 | 2667.87 | 1159.82 | -3518.33 | [8 empty] | 9716.39 | 9716.39
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Contracts | 5490000 | 100000 |  |  | 493550.71 | -393550.71 | 491254.87 | 9200 |  | -6904.16 | [9 empty] | 2295.84 | 2295.84
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Electric Construction Contract | 5490001 |  |  |  | 9868.76 | -9868.76 | 7520.58 |  | 1388.18 | 1620.74 | -660.74 | [8 empty] | 2348.18 | 2348.18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 39526.38 | -39526.38 | 39526.38
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Environmental Contract | 5490015 |  |  |  | 15913.54 | -15913.54 | 13990.17 | 207.03 | 1279.69 | 1444.24 | -1007.59 | [8 empty] | 1923.37 | 1923.37
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Traffic Control Contracts | 5490027 |  |  |  | 3149 | -3149 |  |  |  | 4999 | -1850 | [8 empty] | 3149 | 3149
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 1748414 |  | 2004457 | 2413155.83 | -664741.83 | 173705.23 | 60111.87 | 42846.01 | 132035.72 | [6 empty] | 1000000 | 1000000 | 4457 | 234993.6 | 2239450.6
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Cost Elements | PGE1OTHERCE | 1748414 |  | 2004457 | 2007417.12 | -259003.12 | -2289.88 |  |  | 5250 | [6 empty] | 1000000 | 1000000 | 4457 | 5250 | 2009707
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 1748414 |  | 2004457 | 2007417.12 | -259003.12 | -2289.88 |  |  | 5250 | [6 empty] | 1000000 | 1000000 | 4457 | 5250 | 2009707
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -1131.51 | 1131.51 | -1131.51
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Permits/Fees | 5501090 | 1748147 |  |  |  | 1748147
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Permits/Fees - Environmental | 5501091 |  |  |  | 199.67 | -199.67 | 199.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Land Acquisition Services | 5501093 | 267 |  |  | 266.6 | 0.4 | 266.6
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Postage | 5510010 |  |  |  | 14.85 | -14.85 | 14.85
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2004457 | 2002817.51 | -2002817.51 | -1639.49 | [9 empty] | 1000000 | 1000000 | 4457 |  | 2004457
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Employee Related | PGE1EMPLREL |  |  |  | 129.32 | -129.32 | 129.32
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 114.14 | -114.14 | 114.14
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Reimbursed Mileage Expense | 5091140 |  |  |  | 114.14 | -114.14 | 114.14
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Meals | PGE1MEALS-EXP |  |  |  | 15.18 | -15.18 | 15.18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Meals Expense | 5091100 |  |  |  | 15.18 | -15.18 | 15.18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 405609.39 | -405609.39 | 175865.79 | 60111.87 | 42846.01 | 126785.72 | [9 empty] | 229743.6 | 229743.6
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 65439.66 | -65439.66 | 28074.95 | 9539.49 | 6465.11 | 21360.11 | [9 empty] | 37364.71 | 37364.71
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 65439.66 | -65439.66 | 28074.95 | 9539.49 | 6465.11 | 21360.11 | [9 empty] | 37364.71 | 37364.71
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 207864.92 | -207864.92 | 87962.12 | 30604.42 | 20753.51 | 68544.87 | [9 empty] | 119902.8 | 119902.8
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 189392.07 | -189392.07 | 80472.13 | 27800.79 | 18852.82 | 62266.33 | [9 empty] | 108919.94 | 108919.94
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Paid Time Off | 6010100 |  |  |  | 40523.57 | -40523.57 | 20085.61 | 5217.96 | 3536.33 | 11683.67 | [9 empty] | 20437.96 | 20437.96
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 61072.16 | -61072.16 | 26713.11 | 8764.09 | 5952.41 | 19642.55 | [9 empty] | 34359.05 | 34359.05
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Indirect Labor - Gas | 6010107
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 628.69 | -628.69 | 584.41 | 19.68 |  | 24.6 | [9 empty] | 44.28 | 44.28
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 261.63 | -261.63 | 261.63
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 49920.32 | -49920.32 | 18824.87 | 7931.63 | 5387.03 | 17776.79 | [9 empty] | 31095.45 | 31095.45
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Operation Mgmt & Support - Gas | 6010115
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 270.35 | -270.35 | 243.83 | 11.78 |  | 14.74 | [9 empty] | 26.52 | 26.52
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Fleet OH | 6010123 |  |  |  | 13758.67 | -13758.67 | 13758.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 22956.68 | -22956.68 |  | 5855.65 | 3977.05 | 13123.98 | [9 empty] | 22956.68 | 22956.68
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Fleet OH - Gas | 6010126
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 18472.85 | -18472.85 | 7489.99 | 2803.63 | 1900.69 | 6278.54 | [9 empty] | 10982.86 | 10982.86
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 12027.81 | -12027.81 | 5021.52 | 1788.53 | 1212.5 | 4005.26 | [9 empty] | 7006.29 | 7006.29
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | IT Device OH | 6010113 |  |  |  | 6445.04 | -6445.04 | 2468.47 | 1015.1 | 688.19 | 2273.28 | [9 empty] | 3976.57 | 3976.57
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 99487.61 | -99487.61 | 46049.6 | 13941.72 | 9451.66 | 30044.63 | [9 empty] | 53438.01 | 53438.01
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Benefits OH | 6010120 |  |  |  | 65111.9 | -65111.9 | 25466.04 | 10420.94 | 7064.79 | 22160.13 | [9 empty] | 39645.86 | 39645.86
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 23746.74 | -23746.74 | 9954.59 | 3520.78 | 2386.87 | 7884.5 | [9 empty] | 13792.15 | 13792.15
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Minor Material OH | 6010122 |  |  |  | 10628.97 | -10628.97 | 10628.97
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 32817.2 | -32817.2 | 13779.12 | 6026.24 | 6175.73 | 6836.11 | [9 empty] | 19038.08 | 19038.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 16171.37 | -16171.37 | 10830.7 | 1822.45 | 1669.83 | 1848.39 | [9 empty] | 5340.67 | 5340.67
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 16645.83 | -16645.83 | 2948.42 | 4203.79 | 4505.9 | 4987.72 | [9 empty] | 13697.41 | 13697.41
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Financial Costs | PGE1ORDFIN | 4475707.02 |  | 1732683 | 4003932.76 | 471774.26 | 1812907.5 | 122362.57 | 148848.29 | 205641.24 | -18509.84 | [5 empty] | 1000000 | 732683 |  | 458342.26 | 2191025.26
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4475707.02 |  | 1732683 | 4003932.76 | 471774.26 | 1812907.5 | 122362.57 | 148848.29 | 205641.24 | -18509.84 | [5 empty] | 1000000 | 732683 |  | 458342.26 | 2191025.26
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 876581.02 |  |  | 321778.73 | 554802.29 | 195781.34 | 30520.69 | 40618.51 | 47449.08 | 7409.11 | [8 empty] | 125997.39 | 125997.39
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Types | PGE1ACTVTYPES | 876581.02 |  |  | 321778.73 | 554802.29 | 195781.34 | 30520.69 | 40618.51 | 47449.08 | 7409.11 | [8 empty] | 125997.39 | 125997.39
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 876581.02 |  |  | 321778.73 | 554802.29 | 195781.34 | 30520.69 | 40618.51 | 47449.08 | 7409.11 | [8 empty] | 125997.39 | 125997.39
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 876581.02 |  |  | 265435.79 | 611145.23 | 140637.49 | 30249.76 | 40226.14 | 46913.29 | 7409.11 | [8 empty] | 124798.3 | 124798.3
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Internal Services - Budget | 5600000 | 445000 |  |  |  | 445000
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Administration | 6603000 | 883.35 |  |  | 2588.07 | -1704.72 | 1264.91 |  | 557.12 | 766.04 | [9 empty] | 1323.16 | 1323.16
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction | 6603001 | 414402.64 |  |  | 233659.22 | 180743.42 | 122641.73 | 28372.75 | 32896.5 | 42934.24 | 6814 | [8 empty] | 111017.49 | 111017.49
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 19934.42 | -19934.42 | 9226.13 | 1561.7 | 6514.02 | 2186.37 | 446.2 | [8 empty] | 10708.29 | 10708.29
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Engineering/Mapping | 6603022 | 223.26 |  |  | 3212.55 | -2989.29 | 2465.92 |  | 74.45 | 523.27 | 148.91 | [8 empty] | 746.63 | 746.63
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Engineering Services | 6603023
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Environmental Services | 6603024 | 2718 |  |  |  | 2718
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 | 67.95 |  |  | 423.46 | -355.51 | 353.82 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Surveying & Engineering Supprt-Misc | 6603059 | 63.75 |  |  | 30.41 | 33.34 | 30.41
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Management Services | 6603076 | 2935.02 |  |  | 2935.02 |  | 2935.02
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Maintain & Operate Services | 6603083 | 3895.8 |  |  |  | 3895.8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Field Services | 6603099 | 4159.03 |  |  |  | 4159.03
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction Doubletime Services | 6603180 |  |  |  | 888.86 | -888.86 | 888.86
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Rights - Misc | 6603227 | 1912.5 |  |  | 95.09 | 1817.41 | 95.09
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Electric Estimating | 6603466 |  |  |  | 593.64 | -593.64 | 119.96 | 118.42 | 118.42 | 236.84 | [9 empty] | 473.68 | 473.68
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Account Services | 6603730 | 120.07 |  |  | 812.05 | -691.98 | 352.64 | 196.89 | 65.63 | 196.89 | [9 empty] | 459.41 | 459.41
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Manage L&EM | 6603823 | 199.65 |  |  | 263 | -63.35 | 263
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 56342.94 | -56342.94 | 55143.85 | 270.93 | 392.37 | 535.79 | [9 empty] | 1199.09 | 1199.09
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 51396.65 | -51396.65 | 51396.65
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Mapping | 6010077 |  |  |  | 4946.29 | -4946.29 | 3747.2 | 270.93 | 392.37 | 535.79 | [9 empty] | 1199.09 | 1199.09
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Material Total | PGE1MATTOTAL | 210000 |  |  | 246562.13 | -36562.13 | 244968.77 | 1593.36 | [11 empty] | 1593.36 | 1593.36
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Material related expenses | PGE1MATERIAL | 210000 |  |  | 216501.67 | -6501.67 | 215111.3 | 1390.37 | [11 empty] | 1390.37 | 1390.37
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Materials Not Otherwise Classified | 5300000 |  |  |  | 128.07 | -128.07 | 128.07
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction Supplies | 5300110 |  |  |  | 1031.93 | -1031.93 | 588.1 | 443.83 | [11 empty] | 443.83 | 443.83
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 36910.49 | -36910.49 | 36759.24 | 151.25 | [11 empty] | 151.25 | 151.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Electrical Specialties | 5300140 | 210000 |  |  | 18494.62 | 191505.38 | 18494.62
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 140826.31 | -140826.31 | 140031.02 | 795.29 | [11 empty] | 795.29 | 795.29
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Electl & Electronic Equipment Component | 5300200 |  |  |  | 370.93 | -370.93 | 370.93
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 18739.32 | -18739.32 | 18739.32
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Material Burden | PGE1MATBURD |  |  |  | 30060.46 | -30060.46 | 29857.47 | 202.99 | [11 empty] | 202.99 | 202.99
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Material Burden | 6010000 |  |  |  | 30060.46 | -30060.46 | 29857.47 | 202.99 | [11 empty] | 202.99 | 202.99
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Contract Total | PGE1CONTRACT | 1248546 |  |  | 991018.4 | 257527.6 | 945935.35 | 15335.75 | 12559.5 | 43236.47 | -26048.67 | [8 empty] | 45083.05 | 45083.05
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Consulting | PGE1CONSULTING | 1500 |  |  | 260.87 | 1239.13 | 176.62 |  | 43.05 | 82.28 | -41.08 | [8 empty] | 84.25 | 84.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Consulting Services - Engineering | 5001230 |  |  |  | 260.87 | -260.87 | 176.62 |  | 43.05 | 82.28 | -41.08 | [8 empty] | 84.25 | 84.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Consulting Services - Environmental Perm | 5001237 | 1500 |  |  |  | 1500
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Contract | PGE1OTHCONTRAC | 1247046 |  |  | 990757.53 | 256288.47 | 945758.73 | 15335.75 | 12516.45 | 43154.19 | -26007.59 | [8 empty] | 44998.8 | 44998.8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Contracts | 5490000 | 1204532 |  |  | 859690.07 | 344841.93 | 858342.51 |  |  | 1347.56 | [9 empty] | 1347.56 | 1347.56
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Electric Construction Contract | 5490001 |  |  |  | 34547.01 | -34547.01 | 7834.9 |  | 12079.72 | 39632.39 | -25000 | [8 empty] | 26712.11 | 26712.11
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 81214.17 | -81214.17 | 66385.45 | 14828.72 | [11 empty] | 14828.72 | 14828.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Environmental Contract | 5490015 | 2514 |  |  | 15306.28 | -12792.28 | 13195.87 | 507.03 | 436.73 | 2174.24 | -1007.59 | [8 empty] | 2110.41 | 2110.41
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Traffic Control Contracts | 5490027 | 40000 |  |  |  | 40000
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 2140580 |  | 1732683 | 2444573.5 | -303993.5 | 426222.04 | 74912.77 | 95670.28 | 114955.69 | 129.72 | [5 empty] | 1000000 | 732683 |  | 285668.46 | 2018351.46
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Cost Elements | PGE1OTHERCE | 2140017 |  | 1732683 | 1712089.46 | 427927.54 | -25973.26 |  |  | 5250 | 129.72 | [5 empty] | 1000000 | 732683 |  | 5379.72 | 1738062.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 2140017 |  | 1732683 | 1712089.46 | 427927.54 | -25973.26 |  |  | 5250 | 129.72 | [5 empty] | 1000000 | 732683 |  | 5379.72 | 1738062.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -2087.85 | 2087.85 | -2087.85
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Rents | 5007000 | 27000 |  |  |  | 27000
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Permits/Fees | 5501090 | 2112749 |  |  | 1556.64 | 2111192.36 | 1426.92 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Permits/Fees - Environmental | 5501091 |  |  |  | 199.67 | -199.67 | 199.67
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Acquisition Services | 5501093 | 268 |  |  | 481.25 | -213.25 | 481.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Postage | 5510010 |  |  |  | 14 | -14 | 14
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1732683 | 1706675.75 | -1706675.75 | -26007.25 | [9 empty] | 1000000 | 732683 |  |  | 1732683
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Employee Related | PGE1EMPLREL | 183 |  |  | 176.76 | 6.24 | 176.76
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Travel / Lodging | PGE1TRVL-LODGE | 183 |  |  | 149.79 | 33.21 | 149.79
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Reimbursed Mileage Expense | 5091140 | 183 |  |  | 149.79 | 33.21 | 149.79
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Meals | PGE1MEALS-EXP |  |  |  | 26.97 | -26.97 | 26.97
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Meals Expense | 5091100 |  |  |  | 26.97 | -26.97 | 26.97
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Overheads | PGE1OVERHEAD | 380 |  |  | 732307.28 | -731927.28 | 452018.54 | 74912.77 | 95670.28 | 109705.69 | [9 empty] | 280288.74 | 280288.74
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 112724.65 | -112724.65 | 69060.45 | 11237.72 | 14955.73 | 17470.75 | [9 empty] | 43664.2 | 43664.2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 112724.65 | -112724.65 | 69060.45 | 11237.72 | 14955.73 | 17470.75 | [9 empty] | 43664.2 | 43664.2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 370055.16 | -370055.16 | 230607.33 | 35957.35 | 47786.38 | 55704.1 | [9 empty] | 139447.83 | 139447.83
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 336823.72 | -336823.72 | 210187.23 | 32649.28 | 43400.58 | 50586.63 | [9 empty] | 126636.49 | 126636.49
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Paid Time Off | 6010100 |  |  |  | 72148.85 | -72148.85 | 48265.19 | 6146.86 | 8180.57 | 9556.23 | [9 empty] | 23883.66 | 23883.66
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 108892.91 | -108892.91 | 69336.83 | 10279.77 | 13558.56 | 15717.75 | [9 empty] | 39556.08 | 39556.08
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Indirect Labor - Gas | 6010107 |  |  |  | 18.62 | -18.62 |  |  |  | 18.62 | [9 empty] | 18.62 | 18.62
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1293.94 | -1293.94 | 801.87 |  | 196.83 | 295.24 | [9 empty] | 492.07 | 492.07
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 220.08 | -220.08 | 101.15 | 50.97 | 16.99 | 50.97 | [9 empty] | 118.93 | 118.93
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 91042.88 | -91042.88 | 55244.03 | 9303.34 | 12270.7 | 14224.81 | [9 empty] | 35798.85 | 35798.85
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 28.54 | -28.54 |  |  |  | 28.54 | [9 empty] | 28.54 | 28.54
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 573.24 | -573.24 | 278.51 |  | 117.89 | 176.84 | [9 empty] | 294.73 | 294.73
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Fleet OH | 6010123 |  |  |  | 36159.65 | -36159.65 | 36159.65
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 26429.07 | -26429.07 |  | 6868.34 | 9059.04 | 10501.69 | [9 empty] | 26429.07 | 26429.07
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Fleet OH - Gas | 6010126 |  |  |  | 15.94 | -15.94 |  |  |  | 15.94 | [9 empty] | 15.94 | 15.94
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 33231.44 | -33231.44 | 20420.1 | 3308.07 | 4385.8 | 5117.47 | [9 empty] | 12811.34 | 12811.34
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 21177.36 | -21177.36 | 13004.62 | 2110.31 | 2797.83 | 3264.6 | [9 empty] | 8172.74 | 8172.74
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | IT Device OH | 6010113 |  |  |  | 12054.08 | -12054.08 | 7415.48 | 1197.76 | 1587.97 | 1852.87 | [9 empty] | 4638.6 | 4638.6
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 183110.75 | -183110.75 | 120249.18 | 16563.5 | 21809.48 | 24488.59 | [9 empty] | 62861.57 | 62861.57
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Benefits OH | 6010120 |  |  |  | 125145.19 | -125145.19 | 78485.23 | 12295.98 | 16301.86 | 18062.12 | [9 empty] | 46659.96 | 46659.96
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 42406.04 | -42406.04 | 26317.72 | 4154.23 | 5507.62 | 6426.47 | [9 empty] | 16088.32 | 16088.32
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Minor Material OH | 6010122 |  |  |  | 15559.52 | -15559.52 | 15446.23 | 113.29 | [11 empty] | 113.29 | 113.29
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | AFUDC Costs | PGE1AFUDCDIR | 380 |  |  | 66416.72 | -66036.72 | 32101.58 | 11154.2 | 11118.69 | 12042.25 | [9 empty] | 34315.14 | 34315.14
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 36617.29 | -36617.29 | 26969.24 | 3385.65 | 3006.34 | 3256.06 | [9 empty] | 9648.05 | 9648.05
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | AFUDC-Equity | 5590031 | 380 |  |  | 29799.43 | -29419.43 | 5132.34 | 7768.55 | 8112.35 | 8786.19 | [9 empty] | 24667.09 | 24667.09
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Billing Credits and Reimbursements | PGE1REIMBURSE
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Billing Credits | PGE1BILLCR
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Billing Credit - CIAC Non Taxable | 5590051
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 500000 |  | 3494.58 | 182573.5 | 317426.5 | 144473.49 | 32554.39 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 34605.43 | 38100.01
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 500000 |  | 3494.58 | 182573.5 | 317426.5 | 144473.49 | 32554.39 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 34605.43 | 38100.01
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 41448.11 | -41448.11 | 41448.11
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 41448.11 | -41448.11 | 41448.11
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 41448.11 | -41448.11 | 41448.11
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 39337.18 | -39337.18 | 39337.18
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 136.65 | -136.65 | 136.65
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Env & Land Activity Charge - Type A | 5590105 |  |  |  | 989.89 | -989.89 | 989.89
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Administration | 6603000 |  |  |  | 790.08 | -790.08 | 790.08
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Acquisition - Misc | 6603004 |  |  |  | 10771.16 | -10771.16 | 10771.16
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Construction Overtime Services | 6603021 |  |  |  | 380.76 | -380.76 | 380.76
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 1084.07 | -1084.07 | 1084.07
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Environmental Services | 6603024 |  |  |  | 329.2 | -329.2 | 329.2
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 8399.25 | -8399.25 | 8399.25
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Administrative Services - OT | 6603150 |  |  |  | 2971.14 | -2971.14 | 2971.14
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Rights - Misc | 6603227 |  |  |  | 13248.52 | -13248.52 | 13248.52
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Account Services | 6603730 |  |  |  | 236.46 | -236.46 | 236.46
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 2110.93 | -2110.93 | 2110.93
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Estimating-Internal | 6010076 |  |  |  | 2069.76 | -2069.76 | 2069.76
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Mapping | 6010077 |  |  |  | 41.17 | -41.17 | 41.17
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Contract Total | PGE1CONTRACT | 500000 |  |  | 51664.63 | 448335.37 | 20083.19 | 31581.44 | [11 empty] | 31581.44 | 31581.44
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 500000 |  |  | 51664.63 | 448335.37 | 20083.19 | 31581.44 | [11 empty] | 31581.44 | 31581.44
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Contracts | 5490000 | 500000 |  |  | 18577.33 | 481422.67 | 18577.33
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 33087.3 | -33087.3 | 1505.86 | 31581.44 | [11 empty] | 31581.44 | 31581.44
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 3494.58 | 89460.76 | -89460.76 | 82942.19 | 972.95 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 3023.99 | 6518.57
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  |  | 9166.19 | -9166.19 | 9166.19
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 9166.19 | -9166.19 | 9166.19
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Permits/FeesLand Surveying Services | 5501092 |  |  |  | 6202.41 | -6202.41 | 6202.41
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Acquisition Services | 5501093 |  |  |  | 470.25 | -470.25 | 470.25
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Cost Adjustments | 5590042 |  |  |  | 2493.53 | -2493.53 | 2493.53
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Employee Related | PGE1EMPLREL |  |  |  | 11.18 | -11.18 | 11.18
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Meals | PGE1MEALS-EXP |  |  |  | 11.18 | -11.18 | 11.18
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Meals Expense | 5091100 |  |  |  | 11.18 | -11.18 | 11.18
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  | 3494.58 | 80283.39 | -80283.39 | 73764.82 | 972.95 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 3023.99 | 6518.57
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 15740.74 | -15740.74 | 15740.74
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 15740.74 | -15740.74 | 15740.74
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 36300.29 | -36300.29 | 36300.29
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 32939.93 | -32939.93 | 32939.93
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 9299.14 | -9299.14 | 9299.14
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 1042.74 | -1042.74 | 1042.74
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 14264.97 | -14264.97 | 14264.97
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Indirect Labor - Cust Care | 6010110 |  |  |  | 105.12 | -105.12 | 105.12
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1855.42 | -1855.42 | 1855.42
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 5430.01 | -5430.01 | 5430.01
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Operation Mgmt & Support - Cust Care | 6010118 |  |  |  | 9.17 | -9.17 | 9.17
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Fleet OH | 6010123 |  |  |  | 933.36 | -933.36 | 933.36
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 3360.36 | -3360.36 | 3360.36
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 2154.02 | -2154.02 | 2154.02
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | IT Device OH | 6010113 |  |  |  | 1206.34 | -1206.34 | 1206.34
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 17467.01 | -17467.01 | 17467.01
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Benefits OH | 6010120 |  |  |  | 12852.79 | -12852.79 | 12852.79
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 4614.22 | -4614.22 | 4614.22
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  | 3494.58 | 10775.35 | -10775.35 | 4256.78 | 972.95 | 1025.52 | 1025.52 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 3023.99 | 6518.57
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  | 3494.58 | 7343.13 | -7343.13 | 3002.14 | 291.83 | 277.29 | 277.29 |  | 524.3 | 524.3 | 543.55 | 543.55 | 543.55 | 543.55 | 271.78 |  | 846.41 | 4340.99
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 3432.22 | -3432.22 | 1254.64 | 681.12 | 748.23 | 748.23 | [9 empty] | 2177.58 | 2177.58
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Financial Costs | PGE1ORDFIN | 2751921 |  | 2012197 | 3569225.35 | -817304.35 | 954359.95 | 168193.48 | 151055.17 | 267022.93 | 16396.82 | [6 empty] | 1000000 | 1012197 | 602668.4 | 2614865.4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2751921 |  | 2012197 | 3569225.35 | -817304.35 | 954359.95 | 168193.48 | 151055.17 | 267022.93 | 16396.82 | [6 empty] | 1000000 | 1012197 | 602668.4 | 2614865.4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 695568 |  |  | 220740.42 | 474827.58 | 43476.66 | 50740.86 | 45573.58 | 69030.09 | 11919.23 | [8 empty] | 177263.76 | 177263.76
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Types | PGE1ACTVTYPES | 695568 |  |  | 220740.42 | 474827.58 | 43476.66 | 50740.86 | 45573.58 | 69030.09 | 11919.23 | [8 empty] | 177263.76 | 177263.76
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 695568 |  |  | 220619.96 | 474948.04 | 43356.2 | 50740.86 | 45573.58 | 69030.09 | 11919.23 | [8 empty] | 177263.76 | 177263.76
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 579624 |  |  | 215688.63 | 363935.37 | 39977.97 | 50296.75 | 45167.74 | 68326.94 | 11919.23 | [8 empty] | 175710.66 | 175710.66
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Type Cost Adjustment | 5590045 | 221772 |  |  |  | 221772
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 273.31 | -273.31 | 273.31
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Internal Services - Budget | 5600000 | 357852 |  |  |  | 357852
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Administration | 6603000 |  |  |  | 676.15 | -676.15 | 606.51 |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction | 6603001 |  |  |  | 137874.85 | -137874.85 | 20163 | 43200.76 | 27937.4 | 40781.79 | 5791.9 | [8 empty] | 117711.85 | 117711.85
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Acquisition - Misc | 6603004 |  |  |  | 348.66 | -348.66 | 348.66
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Analyst Services | 6603005 |  |  |  | 165.05 | -165.05 | 109.36 | 55.69 | [11 empty] | 55.69 | 55.69
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 57952.87 | -57952.87 | 13604.9 | 6112.34 | 8744.79 | 23512.42 | 5978.42 | [8 empty] | 44347.97 | 44347.97
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Engineering/Mapping | 6603022 |  |  |  | 2206.35 | -2206.35 | 1304.49 | 153.12 | 74.45 | 525.38 | 148.91 | [8 empty] | 901.86 | 901.86
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Engineering Services | 6603023
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 50.55 | -50.55 | 50.55
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Management Services | 6603076 |  |  |  | 41.02 | -41.02 | 41.02
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Design Overtime Services | 6603103 |  |  |  | 468.38 | -468.38 | 468.38
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction Doubletime Services | 6603180 |  |  |  | 11434.34 | -11434.34 |  |  | 8411.1 | 3023.24 | [9 empty] | 11434.34 | 11434.34
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Land Rights - Misc | 6603227 |  |  |  | 63.39 | -63.39 | 63.39
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Design Services Double Time | 6603337 |  |  |  | 1750.5 | -1750.5 | 1745.4 | 5.1 | [11 empty] | 5.1 | 5.1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Electric Estimating | 6603466 |  |  |  | 1184.21 | -1184.21 |  | 769.74 |  | 414.47 | [9 empty] | 1184.21 | 1184.21
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Account Services | 6603730 |  |  |  | 1199 | -1199 | 1199
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Apprentice OT | 6603845
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 115944 |  |  | 4931.33 | 111012.67 | 3378.23 | 444.11 | 405.84 | 703.15 | [9 empty] | 1553.1 | 1553.1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Service Planning - Planning Only | 5501163 | 115944 |  |  |  | 115944
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 1245.59 | -1245.59 | 1245.59
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Mapping | 6010077 |  |  |  | 3685.74 | -3685.74 | 2132.64 | 444.11 | 405.84 | 703.15 | [9 empty] | 1553.1 | 1553.1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Types - Contractors | PGE1ACTV-CONTR |  |  |  | 120.46 | -120.46 | 120.46
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Contractor Activity Types | PGE1ACTV-OTH-C |  |  |  | 120.46 | -120.46 | 120.46
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Contractor Consultant | 6608158 |  |  |  | 120.46 | -120.46 | 120.46
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Material Total | PGE1MATTOTAL | 274482 |  |  | 155758.18 | 118723.82 | 152208.96 |  | 1974.78 | 1574.44 | [9 empty] | 3549.22 | 3549.22
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Material related expenses | PGE1MATERIAL | 238473 |  |  | 136877.29 | 101595.71 | 133780.24 |  | 1723.19 | 1373.86 | [9 empty] | 3097.05 | 3097.05
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction Supplies | 5300110 |  |  |  | 546.35 | -546.35 | 546.35
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  |  |  | 22583.39 | -22583.39 | 22583.39
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Electrical Specialties | 5300140 | 238473 |  |  | 17251.25 | 221221.75 | 17251.25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170 |  |  |  | 220.29 | -220.29 | 220.29
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 83707.92 | -83707.92 | 80610.87 |  | 1723.19 | 1373.86 | [9 empty] | 3097.05 | 3097.05
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Fabricated Structures | 5300270 |  |  |  | 12504.91 | -12504.91 | 12504.91
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300 |  |  |  | 63.18 | -63.18 | 63.18
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Material Burden | PGE1MATBURD | 36009 |  |  | 18880.89 | 17128.11 | 18428.72 |  | 251.59 | 200.58 | [9 empty] | 452.17 | 452.17
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Material Burden Adjustment | 5590076 | 36009 |  |  |  | 36009
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Material Burden | 6010000 |  |  |  | 18880.89 | -18880.89 | 18428.72 |  | 251.59 | 200.58 | [9 empty] | 452.17 | 452.17
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Contract Total | PGE1CONTRACT | 899485 |  |  | 705636.31 | 193848.69 | 653056.4 | 5547 | 1931 | 40684.99 | 4416.92 | [8 empty] | 52579.91 | 52579.91
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 356.58 | -356.58 | 261.58 | 95 | [11 empty] | 95 | 95
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Consulting Services - Engineering | 5001230 |  |  |  | 95 | -95 |  | 95 | [11 empty] | 95 | 95
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 261.58 | -261.58 | 261.58
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Contract | PGE1OTHCONTRAC | 899485 |  |  | 705279.73 | 194205.27 | 652794.82 | 5452 | 1931 | 40684.99 | 4416.92 | [8 empty] | 52484.91 | 52484.91
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Contracts | 5490000 | 702600 |  |  | 613808.13 | 88791.87 | 609987.86 |  |  | 2725 | 1095.27 | [8 empty] | 3820.27 | 3820.27
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Electric Construction Contract | 5490001 |  |  |  | 30867.32 | -30867.32 |  |  |  | 28677.67 | 2189.65 | [8 empty] | 30867.32 | 30867.32
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 33096.7 | -33096.7 | 33096.7
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Environmental Contract | 5490015 | 38885 |  |  | 8792.26 | 30092.74 | 8792.26
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction Inspection | 5490021 |  |  |  | 1026.32 | -1026.32 |  |  |  | 1026.32 | [9 empty] | 1026.32 | 1026.32
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Traffic Control Contracts | 5490027 | 158000 |  |  | 17689 | 140311 | 918 | 5452 | 1931 | 8256 | 1132 | [8 empty] | 16771 | 16771
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 882386 |  | 2012197 | 2487090.44 | -1604704.44 | 105617.93 | 111905.62 | 101575.81 | 155733.41 | 60.67 | [6 empty] | 1000000 | 1012197 | 369275.51 | 2381472.51
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Cost Elements | PGE1OTHERCE | 882386 |  | 2012197 | 2016311.83 | -1133925.83 | -673.84 | -18.36 | -393.82 | 5140.18 | 60.67 | [6 empty] | 1000000 | 1012197 | 4788.67 | 2016985.67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 882386 |  | 2012197 | 2016311.83 | -1133925.83 | -673.84 | -18.36 | -393.82 | 5140.18 | 60.67 | [6 empty] | 1000000 | 1012197 | 4788.67 | 2016985.67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -1350.1 | 1350.1 | -759.05 | -18.36 | -393.82 | -109.82 | -69.05 | [8 empty] | -591.05 | -591.05
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Permits/Fees | 5501090 |  |  |  | 259.44 | -259.44 | 129.72 |  |  |  | 129.72 | [8 empty] | 129.72 | 129.72
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Land Acquisition Services | 5501093 |  |  |  | 574.22 | -574.22 | 574.22
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Land Fees | 5501094 |  |  |  | 5250 | -5250 |  |  |  | 5250 | [9 empty] | 5250 | 5250
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Postage | 5510010 |  |  |  | 11.55 | -11.55 | 11.55
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 882386 |  | 2012197 | 2011566.72 | -1129180.72 | -630.28 | [10 empty] | 1000000 | 1012197 |  | 2012197
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  |  | 470778.61 | -470778.61 | 106291.77 | 111923.98 | 101969.63 | 150593.23 | [9 empty] | 364486.84 | 364486.84
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 77361.8 | -77361.8 | 16481.93 | 18682.79 | 16780.19 | 25416.89 | [9 empty] | 60879.87 | 60879.87
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 77361.8 | -77361.8 | 16481.93 | 18682.79 | 16780.19 | 25416.89 | [9 empty] | 60879.87 | 60879.87
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 245773.81 | -245773.81 | 50362.23 | 59955 | 53878.68 | 81577.9 | [9 empty] | 195411.58 | 195411.58
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 223775.81 | -223775.81 | 46283.86 | 54463.36 | 48932.35 | 74096.24 | [9 empty] | 177491.95 | 177491.95
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Paid Time Off | 6010100 |  |  |  | 44839.72 | -44839.72 | 11539.32 | 10219.22 | 9178.52 | 13902.66 | [9 empty] | 33300.4 | 33300.4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 71874.32 | -71874.32 | 15864.99 | 17182.27 | 15449.45 | 23377.61 | [9 empty] | 56009.33 | 56009.33
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Indirect Labor - Gas | 6010107
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 463.6 | -463.6 | 419.32 | 19.68 |  | 24.6 | [9 empty] | 44.28 | 44.28
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 439.68 | -439.68 | 439.68
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 60486.27 | -60486.27 | 9797.01 | 15550.21 | 13981.97 | 21157.08 | [9 empty] | 50689.26 | 50689.26
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Operation Mgmt & Support - Gas | 6010115
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 216.52 | -216.52 | 190 | 11.78 |  | 14.74 | [9 empty] | 26.52 | 26.52
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Fleet OH | 6010123 |  |  |  | 8033.54 | -8033.54 | 8033.54
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 37422.16 | -37422.16 |  | 11480.2 | 10322.41 | 15619.55 | [9 empty] | 37422.16 | 37422.16
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Fleet OH - Gas | 6010126
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 21998 | -21998 | 4078.37 | 5491.64 | 4946.33 | 7481.66 | [9 empty] | 17919.63 | 17919.63
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 14259.4 | -14259.4 | 2827.9 | 3503.29 | 3155.42 | 4772.79 | [9 empty] | 11431.5 | 11431.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | IT Device OH | 6010113 |  |  |  | 7738.6 | -7738.6 | 1250.47 | 1988.35 | 1790.91 | 2708.87 | [9 empty] | 6488.13 | 6488.13
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 115852.67 | -115852.67 | 27892.75 | 27308.67 | 24737.35 | 35913.9 | [9 empty] | 87959.92 | 87959.92
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Benefits OH | 6010120 |  |  |  | 78029.58 | -78029.58 | 12825.3 | 20412.31 | 18385.39 | 26406.58 | [9 empty] | 65204.28 | 65204.28
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 27996.79 | -27996.79 | 5493.5 | 6896.36 | 6211.55 | 9395.38 | [9 empty] | 22503.29 | 22503.29
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Minor Material OH | 6010122 |  |  |  | 9826.3 | -9826.3 | 9573.95 |  | 140.41 | 111.94 | [9 empty] | 252.35 | 252.35
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 31790.33 | -31790.33 | 11554.86 | 5977.52 | 6573.41 | 7684.54 | [9 empty] | 20235.47 | 20235.47
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | AFUDC-Borrowed | 5590030 |  |  |  | 14245.45 | -14245.45 | 8590.5 | 1799.8 | 1777.36 | 2077.79 | [9 empty] | 5654.95 | 5654.95
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 17544.88 | -17544.88 | 2964.36 | 4177.72 | 4796.05 | 5606.75 | [9 empty] | 14580.52 | 14580.52
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Order Financial Costs | PGE1ORDFIN | 1802500.28 |  |  | 442969.12 | 1359531.16 | 435171.19 | 2595.63 | 2649.52 | 2572.78 | -20 | [8 empty] | 7797.93 | 7797.93
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 1802500.28 |  |  | 442969.12 | 1359531.16 | 435171.19 | 2595.63 | 2649.52 | 2572.78 | -20 | [8 empty] | 7797.93 | 7797.93
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Activity Type Total | PGE1ACTV-TOT | 250051.28 |  |  | 9668.76 | 240382.52 | 9603.96 |  | 64.8 | [10 empty] | 64.8 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Activity Types | PGE1ACTVTYPES | 250051.28 |  |  | 9668.76 | 240382.52 | 9603.96 |  | 64.8 | [10 empty] | 64.8 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Activity Types - Internal | PGE1ACTV-INT | 249928.56 |  |  | 9607.4 | 240321.16 | 9542.6 |  | 64.8 | [10 empty] | 64.8 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 249928.56 |  |  | 7559.77 | 242368.79 | 7494.97 |  | 64.8 | [10 empty] | 64.8 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 68.33 | -68.33 | 68.33
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Internal Services - Budget | 5600000 | 107485 |  |  |  | 107485
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Administration | 6603000 | 475.65 |  |  | 606.51 | -130.86 | 606.51
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Construction | 6603001 | 108710 |  |  |  | 108710
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Acquisition - Misc | 6603004 | 191.25 |  |  | 413.46 | -222.21 | 348.66 |  | 64.8 | [10 empty] | 64.8 | 64.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Engineering/Mapping | 6603022 | 9574.38 |  |  | 1378.58 | 8195.8 | 1378.58
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 | 679.5 |  |  | 33.7 | 645.8 | 33.7
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Surveying & Engineering Supprt-Misc | 6603059 | 2996.25 |  |  | 1822.49 | 1173.76 | 1822.49
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Switching Operator Service | 6603068 | 167.78 |  |  |  | 167.78
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Management Services | 6603076 |  |  |  | 20.51 | -20.51 | 20.51
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Maintain & Operate Services | 6603083 | 1721.4 |  |  |  | 1721.4
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Field Services | 6603099 | 10707.29 |  |  |  | 10707.29
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Engineering/Mapping Services Overtime | 6603106 | 5507.08 |  |  | 107.47 | 5399.61 | 107.47
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Administrative Services - OT | 6603150 | 63.75 |  |  | 86.12 | -22.37 | 86.12
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Rights - Misc | 6603227 | 63.75 |  |  | 79.24 | -15.49 | 79.24
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Electric Estimating | 6603466 | 1186.02 |  |  | 2429.19 | -1243.17 | 2429.19
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Electric Estimating Overtime | 6603467 | 263.56 |  |  | 319.35 | -55.79 | 319.35
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Account Services | 6603730 |  |  |  | 60.04 | -60.04 | 60.04
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Manage L&EM | 6603823 | 135.9 |  |  | 134.78 | 1.12 | 134.78
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 2047.63 | -2047.63 | 2047.63
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Estimating-Internal | 6010076 |  |  |  | 804.17 | -804.17 | 804.17
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Mapping | 6010077 |  |  |  | 1243.46 | -1243.46 | 1243.46
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Activity Types - Contractors | PGE1ACTV-CONTR | 122.72 |  |  | 61.36 | 61.36 | 61.36
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C | 122.72 |  |  | 61.36 | 61.36 | 61.36
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Contractor Consultant | 6608158 | 122.72 |  |  | 61.36 | 61.36 | 61.36
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Material Total | PGE1MATTOTAL | 150000 |  |  |  | 150000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Material related expenses | PGE1MATERIAL | 150000 |  |  |  | 150000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Electrical Specialties | 5300140 | 150000 |  |  |  | 150000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Contract Total | PGE1CONTRACT | 716382 |  |  | 391581.25 | 324800.75 | 391581.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Consulting | PGE1CONSULTING |  |  |  | 261.58 | -261.58 | 261.58
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Consulting Services - Environmental Perm | 5001237 |  |  |  | 261.58 | -261.58 | 261.58
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Contract | PGE1OTHCONTRAC | 716382 |  |  | 391319.67 | 325062.33 | 391319.67
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Contracts | 5490000 | 608385 |  |  | 385087.91 | 223297.09 | 385087.91
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Gas Construction Contract | 5490002 | 30000 |  |  |  | 30000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 1219.31 | -1219.31 | 1219.31
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Environmental Contract | 5490015 | 37997 |  |  | 5012.45 | 32984.55 | 5012.45
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Traffic Control Contracts | 5490027 | 40000 |  |  |  | 40000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Order Other Costs | PGE1ORD-OTHER | 686067 |  |  | 41719.11 | 644347.89 | 33985.98 | 2595.63 | 2584.72 | 2572.78 | -20 | [8 empty] | 7733.13 | 7733.13
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Cost Elements | PGE1OTHERCE | 686067 |  |  | 10950.49 | 675116.51 | 10873.99 |  |  | 96.5 | -20 | [8 empty] | 76.5 | 76.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 686067 |  |  | 10950.49 | 675116.51 | 10873.99 |  |  | 96.5 | -20 | [8 empty] | 76.5 | 76.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Rents | 5007000 | 12000 |  |  |  | 12000
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Vehicle Lease | 5010503 | 71 |  |  | 71.25 | -0.25 | 71.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Permits/Fees | 5501090 | 665397 |  |  | 129.72 | 665267.28 | 129.72
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Acquisition Services | 5501093 | 8599 |  |  | 6119.94 | 2479.06 | 6079.94 |  |  | 60 | -20 | [8 empty] | 40 | 40
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Land Fees | 5501094 |  |  |  | 5036.5 | -5036.5 | 5000 |  |  | 36.5 | [9 empty] | 36.5 | 36.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  |  | -406.92 | 406.92 | -406.92
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Order Overheads | PGE1OVERHEAD |  |  |  | 30768.62 | -30768.62 | 23111.99 | 2595.63 | 2584.72 | 2476.28 | [9 empty] | 7656.63 | 7656.63
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Capitalized A&G | PGE1CAPAG |  |  |  | 3423.96 | -3423.96 | 3400.1 |  | 23.86 | [10 empty] | 23.86 | 23.86
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Capitalized A&G | 6010050 |  |  |  | 3423.96 | -3423.96 | 3400.1 |  | 23.86 | [10 empty] | 23.86 | 23.86
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Labor Overheads | PGE1LABOROH |  |  |  | 9716.79 | -9716.79 | 9661.16 |  | 55.63 | [10 empty] | 55.63 | 55.63
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 8837.32 | -8837.32 | 8787.67 |  | 49.65 | [10 empty] | 49.65 | 49.65
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Paid Time Off | 6010100 |  |  |  | 2067.31 | -2067.31 | 2054.26 |  | 13.05 | [10 empty] | 13.05 | 13.05
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Indirect Labor - Electric | 6010106 |  |  |  | 2132.63 | -2132.63 | 2132.63
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Indirect Labor - Environmental Land | 6010108 |  |  |  | 1175.05 | -1175.05 | 1152.16 |  | 22.89 | [10 empty] | 22.89 | 22.89
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Indirect Labor - Cust Care | 6010110 |  |  |  | 37.96 | -37.96 | 37.96
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1772.8 | -1772.8 | 1772.8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 462.45 | -462.45 | 448.74 |  | 13.71 | [10 empty] | 13.71 | 13.71
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Fleet OH | 6010123 |  |  |  | 1189.12 | -1189.12 | 1189.12
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 879.47 | -879.47 | 873.49 |  | 5.98 | [10 empty] | 5.98 | 5.98
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Building Service Overhead | 6010112 |  |  |  | 554.62 | -554.62 | 550.8 |  | 3.82 | [10 empty] | 3.82 | 3.82
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | IT Device OH | 6010113 |  |  |  | 324.85 | -324.85 | 322.69 |  | 2.16 | [10 empty] | 2.16 | 2.16
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Overhead | PGE1OTHEROH |  |  |  | 4576.28 | -4576.28 | 4546.57 |  | 29.71 | [10 empty] | 29.71 | 29.71
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Benefits OH | 6010120 |  |  |  | 3409.25 | -3409.25 | 3387.04 |  | 22.21 | [10 empty] | 22.21 | 22.21
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Payroll Taxes OH | 6010121 |  |  |  | 1167.03 | -1167.03 | 1159.53 |  | 7.5 | [10 empty] | 7.5 | 7.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 13051.59 | -13051.59 | 5504.16 | 2595.63 | 2475.52 | 2476.28 | [9 empty] | 7547.43 | 7547.43
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | AFUDC-Borrowed | 5590030 |  |  |  | 6207.21 | -6207.21 | 4078.49 | 789.82 | 669.35 | 669.55 | [9 empty] | 2128.72 | 2128.72
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | AFUDC-Equity | 5590031 |  |  |  | 6844.38 | -6844.38 | 1425.67 | 1805.81 | 1806.17 | 1806.73 | [9 empty] | 5418.71 | 5418.71
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Financial Costs | PGE1ORDFIN | 1107016 |  | 39822.49 | 373494.27 | 733521.73 | 322359.92 | 6416.06 | 2067.19 | 2754.16 | 74.45 | 38742.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 11311.86 | 51134.35
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 1107016 |  | 39822.49 | 373494.27 | 733521.73 | 322359.92 | 6416.06 | 2067.19 | 2754.16 | 74.45 | 38742.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 11311.86 | 51134.35
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 390395 |  |  | 7445.38 | 382949.62 | 6985.29 | 13.39 | 74.45 | 297.8 | 74.45 | [8 empty] | 460.09 | 460.09
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Types | PGE1ACTVTYPES | 390395 |  |  | 7445.38 | 382949.62 | 6985.29 | 13.39 | 74.45 | 297.8 | 74.45 | [8 empty] | 460.09 | 460.09
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 390395 |  |  | 7384.02 | 383010.98 | 6923.93 | 13.39 | 74.45 | 297.8 | 74.45 | [8 empty] | 460.09 | 460.09
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 330256 |  |  | 5462.19 | 324793.81 | 5015.49 |  | 74.45 | 297.8 | 74.45 | [8 empty] | 446.7 | 446.7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Type Cost Adjustment | 5590045 | 122361 |  |  |  | 122361
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Cust. Care Activity Charge - Type A | 5590104 |  |  |  | 136.65 | -136.65 | 136.65
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Internal Services - Budget | 5600000 | 207895 |  |  |  | 207895
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Administration | 6603000 |  |  |  | 741.29 | -741.29 | 741.29
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Acquisition - Misc | 6603004 |  |  |  | 570.52 | -570.52 | 570.52
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Construction Overtime Services | 6603021 |  |  |  | 666.33 | -666.33 | 666.33
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Engineering/Mapping | 6603022 |  |  |  | 1332.57 | -1332.57 | 885.87 |  | 74.45 | 297.8 | 74.45 | [8 empty] | 446.7 | 446.7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 67.39 | -67.39 | 67.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 107.47 | -107.47 | 107.47
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Land Rights - Misc | 6603227 |  |  |  | 824.08 | -824.08 | 824.08
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Electric Estimating Overtime | 6603467 |  |  |  | 170.32 | -170.32 | 170.32
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Account Services | 6603730 |  |  |  | 778.18 | -778.18 | 778.18
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Manage L&EM | 6603823 |  |  |  | 67.39 | -67.39 | 67.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 60139 |  |  | 1921.83 | 58217.17 | 1908.44 | 13.39 | [11 empty] | 13.39 | 13.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Service Planning - Planning Only | 5501163 | 60139 |  |  |  | 60139
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Estimating-Internal | 6010076 |  |  |  | 1142.05 | -1142.05 | 1142.05
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Mapping | 6010077 |  |  |  | 779.78 | -779.78 | 766.39 | 13.39 | [11 empty] | 13.39 | 13.39
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Types - Contractors | PGE1ACTV-CONTR |  |  |  | 61.36 | -61.36 | 61.36
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Other Contractor Activity Types | PGE1ACTV-OTH-C |  |  |  | 61.36 | -61.36 | 61.36
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Contractor Consultant | 6608158 |  |  |  | 61.36 | -61.36 | 61.36
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Material Total | PGE1MATTOTAL | 144905 |  |  | 33648.61 | 111256.39 | 33648.61
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Material related expenses | PGE1MATERIAL | 133580 |  |  | 29234.24 | 104345.76 | 29234.24
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Electrical Specialties | 5300140 | 133580 |  |  |  | 133580
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 |  |  |  | 29234.24 | -29234.24 | 29234.24
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Material Burden | PGE1MATBURD | 11325 |  |  | 4414.37 | 6910.63 | 4414.37
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Material Burden Adjustment | 5590076 | 11325 |  |  |  | 11325
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Material Burden | 6010000 |  |  |  | 4414.37 | -4414.37 | 4414.37
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Contract Total | PGE1CONTRACT | 371145 |  |  | 267813.14 | 103331.86 | 263350.22 | 4462.92 | [11 empty] | 4462.92 | 4462.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Consulting | PGE1CONSULTING |  |  |  | 156.94 | -156.94 | 156.94
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Consulting Services - Environmental Perm | 5001237 |  |  |  | 156.94 | -156.94 | 156.94
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Other Contract | PGE1OTHCONTRAC | 371145 |  |  | 267656.2 | 103488.8 | 263193.28 | 4462.92 | [11 empty] | 4462.92 | 4462.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Contracts | 5490000 | 273307 |  |  | 236787.64 | 36519.36 | 232324.72 | 4462.92 | [11 empty] | 4462.92 | 4462.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 23559.06 | -23559.06 | 23559.06
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Environmental Contract | 5490015 | 49638 |  |  | 7309.5 | 42328.5 | 7309.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Traffic Control Contracts | 5490027 | 48200 |  |  |  | 48200
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 200571 |  | 39822.49 | 64587.14 | 135983.86 | 18375.8 | 1939.75 | 1992.74 | 2456.36 |  | 38742.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 6388.85 | 46211.34
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Other Cost Elements | PGE1OTHERCE | 200571 |  | 38583 | 37603.59 | 162967.41 | -979.41 |  |  |  |  | 38583 | [8 empty] | 38583
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 200571 |  | 38583 | 37603.59 | 162967.41 | -979.41 |  |  |  |  | 38583 | [8 empty] | 38583
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Cash Discount earned | 5006310 |  |  |  | -539.27 | 539.27 | -539.27
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Land Acquisition Services | 5501093 |  |  |  | 137.75 | -137.75 | 137.75
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 200571 |  | 38583 | 38005.11 | 162565.89 | -577.89 |  |  |  |  | 38583 | [8 empty] | 38583
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Overheads | PGE1OVERHEAD |  |  | 1239.49 | 26983.55 | -26983.55 | 19355.21 | 1939.75 | 1992.74 | 2456.36 |  | 159.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 6388.85 | 7628.34
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Capitalized A&G | PGE1CAPAG |  |  |  | 2696.04 | -2696.04 | 2554.05 | 4.93 | 27.41 | 109.65 | [9 empty] | 141.99 | 141.99
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Capitalized A&G | 6010050 |  |  |  | 2696.04 | -2696.04 | 2554.05 | 4.93 | 27.41 | 109.65 | [9 empty] | 141.99 | 141.99
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Labor Overheads | PGE1LABOROH |  |  |  | 7887.26 | -7887.26 | 7431.45 | 15.83 | 87.99 | 351.99 | [9 empty] | 455.81 | 455.81
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 7003.16 | -7003.16 | 6589.1 | 14.38 | 79.93 | 319.75 | [9 empty] | 414.06 | 414.06
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Paid Time Off | 6010100 |  |  |  | 1700.21 | -1700.21 | 1622.54 | 2.7 | 14.99 | 59.98 | [9 empty] | 77.67 | 77.67
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Indirect Labor - Electric | 6010106 |  |  |  | 1391.49 | -1391.49 | 1260.76 | 4.54 | 25.24 | 100.95 | [9 empty] | 130.73 | 130.73
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 844.18 | -844.18 | 844.18
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Indirect Labor - Cust Care | 6010110 |  |  |  | 273.46 | -273.46 | 273.46
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1527.16 | -1527.16 | 1408.84 | 4.11 | 22.84 | 91.37 | [9 empty] | 118.32 | 118.32
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 339.4 | -339.4 | 339.4
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Fleet OH | 6010123 |  |  |  | 839.92 | -839.92 | 839.92
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Fleet OH - Elec | 6010125 |  |  |  | 87.34 | -87.34 |  | 3.03 | 16.86 | 67.45 | [9 empty] | 87.34 | 87.34
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 884.1 | -884.1 | 842.35 | 1.45 | 8.06 | 32.24 | [9 empty] | 41.75 | 41.75
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Building Service Overhead | 6010112 |  |  |  | 560.49 | -560.49 | 533.85 | 0.93 | 5.14 | 20.57 | [9 empty] | 26.64 | 26.64
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | IT Device OH | 6010113 |  |  |  | 323.61 | -323.61 | 308.5 | 0.52 | 2.92 | 11.67 | [9 empty] | 15.11 | 15.11
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Other Overhead | PGE1OTHEROH |  |  |  | 6608.12 | -6608.12 | 6406.58 | 7.21 | 40.08 | 154.25 | [9 empty] | 201.54 | 201.54
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Benefits OH | 6010120 |  |  |  | 3331.88 | -3331.88 | 3182.76 | 5.39 | 29.96 | 113.77 | [9 empty] | 149.12 | 149.12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Payroll Taxes OH | 6010121 |  |  |  | 1159.74 | -1159.74 | 1107.32 | 1.82 | 10.12 | 40.48 | [9 empty] | 52.42 | 52.42
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Minor Material OH | 6010122 |  |  |  | 2116.5 | -2116.5 | 2116.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | AFUDC Costs | PGE1AFUDCDIR |  |  | 1239.49 | 9792.13 | -9792.13 | 2963.13 | 1911.78 | 1837.26 | 1840.47 |  | 159.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 5589.51 | 6829
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | AFUDC-Borrowed | 5590030 |  |  | 1239.49 | 4631.84 | -4631.84 | 1816.95 | 580.99 | 496.77 | 497.64 |  | 159.09 | 159.09 | 167.51 | 167.51 | 167.51 | 167.51 | 167.51 | 83.76 | 1575.4 | 2814.89
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | AFUDC-Equity | 5590031 |  |  |  | 5160.29 | -5160.29 | 1146.18 | 1330.79 | 1340.49 | 1342.83 | [9 empty] | 4014.11 | 4014.11
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 500000 |  | 1193.96 | 158454.03 | 341545.97 | 150941.25 | 4134.25 | 1285.33 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 6318.82 | 7512.78
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 500000 |  | 1193.96 | 158454.03 | 341545.97 | 150941.25 | 4134.25 | 1285.33 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 6318.82 | 7512.78
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  |  |  | 21545.79 | -21545.79 | 20727.35 | 679.16 | 139.28 | [10 empty] | 818.44 | 818.44
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  |  |  | 21545.79 | -21545.79 | 20727.35 | 679.16 | 139.28 | [10 empty] | 818.44 | 818.44
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 21427.59 | -21427.59 | 20609.15 | 679.16 | 139.28 | [10 empty] | 818.44 | 818.44
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 21084.85 | -21084.85 | 20266.41 | 679.16 | 139.28 | [10 empty] | 818.44 | 818.44
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Administration | 6603000 |  |  |  | 5207.03 | -5207.03 | 4649.91 | 417.84 | 139.28 | [10 empty] | 557.12 | 557.12
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Acquisition - Misc | 6603004 |  |  |  | 2541.25 | -2541.25 | 2282.05 | 259.2 | [11 empty] | 259.2 | 259.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Analyst Services | 6603005 |  |  |  | 218.72 | -218.72 | 218.72
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Engineering/Mapping | 6603022 |  |  |  | 3356.3 | -3356.3 | 3356.3
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Environmental Services | 6603024 |  |  |  | 16.85 | -16.85 | 16.85
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 640.24 | -640.24 | 640.24
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 808.24 | -808.24 | 808.24
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Management Services | 6603076 |  |  |  | 591.12 | -591.12 | 591.12
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Electric Estimating | 6603466 |  |  |  | 6087.97 | -6087.97 | 6087.97
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Electric Estimating Overtime | 6603467 |  |  |  | 938.88 | -938.88 | 936.76 | 2.12 | [11 empty] | 2.12 | 2.12
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Manage L&EM | 6603823 |  |  |  | 602.54 | -602.54 | 602.54
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Analyst Svcs Overtime | 6603855 |  |  |  | 75.71 | -75.71 | 75.71
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 342.74 | -342.74 | 342.74
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Estimating-Internal | 6010076 |  |  |  | 281.3 | -281.3 | 281.3
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Mapping | 6010077 |  |  |  | 61.44 | -61.44 | 61.44
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Activity Types - Contractors | PGE1ACTV-CONTR |  |  |  | 118.2 | -118.2 | 118.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C |  |  |  | 118.2 | -118.2 | 118.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Contractor Consultant | 6608158 |  |  |  | 118.2 | -118.2 | 118.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Material Total | PGE1MATTOTAL |  |  |  | 299.47 | -299.47 | 299.47
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Material related expenses | PGE1MATERIAL |  |  |  | 260.18 | -260.18 | 260.18
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Gas & Water Specialties | 5300160 |  |  |  | 260.18 | -260.18 | 260.18
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Material Burden | PGE1MATBURD |  |  |  | 39.29 | -39.29 | 39.29
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Material Burden | 6010000 |  |  |  | 39.29 | -39.29 | 39.29
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Contract Total | PGE1CONTRACT | 500000 |  |  | 90421.9 | 409578.1 | 89041.87 | 1380.03 | [11 empty] | 1380.03 | 1380.03
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 500000 |  |  | 90421.9 | 409578.1 | 89041.87 | 1380.03 | [11 empty] | 1380.03 | 1380.03
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Contracts | 5490000 | 500000 |  |  | 1553.58 | 498446.42 | 1553.58
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 6165.53 | -6165.53 | 4785.5 | 1380.03 | [11 empty] | 1380.03 | 1380.03
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Environmental Contract | 5490015 |  |  |  | 13838.93 | -13838.93 | 13838.93
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Construction Inspection | 5490021 |  |  |  | 5938.66 | -5938.66 | 5938.66
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Construction Management Contracts | 5490024 |  |  |  | 1806 | -1806 | 1806
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Traffic Control Contracts | 5490027 |  |  |  | 5100 | -5100 | 5100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | T&D Sewer Inspection | 5490028 |  |  |  | 56019.2 | -56019.2 | 56019.2
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER |  |  | 1193.96 | 46186.87 | -46186.87 | 40872.56 | 2075.06 | 1146.05 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 4120.35 | 5314.31
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Other Cost Elements | PGE1OTHERCE |  |  |  | 1726.97 | -1726.97 | 1726.97
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 1726.97 | -1726.97 | 1726.97
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Vehicle Lease | 5010503 |  |  |  | 61.81 | -61.81 | 61.81
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Acquisition Services | 5501093 |  |  |  | 1665.16 | -1665.16 | 1665.16
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Employee Related | PGE1EMPLREL |  |  |  | 26.55 | -26.55 | 13.33 |  | 13.22 | [10 empty] | 13.22 | 13.22
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 26.55 | -26.55 | 13.33 |  | 13.22 | [10 empty] | 13.22 | 13.22
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Reimbursed Mileage Expense | 5091140 |  |  |  | 26.55 | -26.55 | 13.33 |  | 13.22 | [10 empty] | 13.22 | 13.22
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Overheads | PGE1OVERHEAD |  |  | 1193.96 | 44433.35 | -44433.35 | 39132.26 | 2075.06 | 1132.83 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 4107.13 | 5301.09
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Capitalized A&G | PGE1CAPAG |  |  |  | 7721.84 | -7721.84 | 7420.49 | 250.07 | 51.28 | [10 empty] | 301.35 | 301.35
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Capitalized A&G | 6010050 |  |  |  | 7721.84 | -7721.84 | 7420.49 | 250.07 | 51.28 | [10 empty] | 301.35 | 301.35
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Labor Overheads | PGE1LABOROH |  |  |  | 21527.27 | -21527.27 | 20823.95 | 583.75 | 119.57 | [10 empty] | 703.32 | 703.32
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 19702.27 | -19702.27 | 19074.45 | 521.09 | 106.73 | [10 empty] | 627.82 | 627.82
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Paid Time Off | 6010100 |  |  |  | 4875.94 | -4875.94 | 4711.11 | 136.78 | 28.05 | [10 empty] | 164.83 | 164.83
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Indirect Labor - Electric | 6010106 |  |  |  | 3648.1 | -3648.1 | 3647.38 | 0.72 | [11 empty] | 0.72 | 0.72
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Indirect Labor - Environmental Land | 6010108 |  |  |  | 3892.26 | -3892.26 | 3603.85 | 239.2 | 49.21 | [10 empty] | 288.41 | 288.41
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 3172.87 | -3172.87 | 3172.22 | 0.65 | [11 empty] | 0.65 | 0.65
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 315.54 | -315.54 | 315.54
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 1502.94 | -1502.94 | 1330.21 | 143.26 | 29.47 | [10 empty] | 172.73 | 172.73
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Fleet OH | 6010123 |  |  |  | 2294.14 | -2294.14 | 2294.14
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Fleet OH - Elec | 6010125 |  |  |  | 0.48 | -0.48 |  | 0.48 | [11 empty] | 0.48 | 0.48
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 1825 | -1825 | 1749.5 | 62.66 | 12.84 | [10 empty] | 75.5 | 75.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Building Service Overhead | 6010112 |  |  |  | 1183.44 | -1183.44 | 1135.28 | 39.97 | 8.19 | [10 empty] | 48.16 | 48.16
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | IT Device OH | 6010113 |  |  |  | 641.56 | -641.56 | 614.22 | 22.69 | 4.65 | [10 empty] | 27.34 | 27.34
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Other Overhead | PGE1OTHEROH |  |  |  | 9036.94 | -9036.94 | 8661.53 | 311.55 | 63.86 | [10 empty] | 375.41 | 375.41
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Benefits OH | 6010120 |  |  |  | 6571.59 | -6571.59 | 6291 | 232.86 | 47.73 | [10 empty] | 280.59 | 280.59
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Payroll Taxes OH | 6010121 |  |  |  | 2439.57 | -2439.57 | 2344.75 | 78.69 | 16.13 | [10 empty] | 94.82 | 94.82
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Minor Material OH | 6010122 |  |  |  | 25.78 | -25.78 | 25.78
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR |  |  | 1193.96 | 6147.3 | -6147.3 | 2226.29 | 929.69 | 898.12 | 899.24 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 2727.05 | 3921.01
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | AFUDC-Borrowed | 5590030 |  |  | 1193.96 | 3723.15 | -3723.15 | 1761.17 | 282.04 | 242.84 | 243.14 |  | 260.02 | 260.02 | 269.57 | 269.57 | 134.78 |  |  |  | 768.02 | 1961.98
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | AFUDC-Equity | 5590031 |  |  |  | 2424.15 | -2424.15 | 465.12 | 647.65 | 655.28 | 656.1 | [9 empty] | 1959.03 | 1959.03
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 4122190 |  | 44306.84 | 313392.8 | 3808797.2 | 187046.78 | 22610.37 | 30732.54 | 6916.81 | 21779.46 | 637.29 | 637.29 | 325.32 | [5 empty] | 82039.18 | 83639.08 | 42706.94
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 4122190 |  | 44306.84 | 313392.8 | 3808797.2 | 187046.78 | 22610.37 | 30732.54 | 6916.81 | 21779.46 | 637.29 | 637.29 | 325.32 | [5 empty] | 82039.18 | 83639.08 | 42706.94
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT | 739831 |  | 2511.92 | 49003.94 | 690827.06 | 36534.25 | 5786.04 | 3025.1 | 1072.17 | 74.46 | [8 empty] | 9957.77 | 9957.77 | 2511.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Types | PGE1ACTVTYPES | 739831 |  | 2511.92 | 49003.94 | 690827.06 | 36534.25 | 5786.04 | 3025.1 | 1072.17 | 74.46 | [8 empty] | 9957.77 | 9957.77 | 2511.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT | 739831 |  | 2511.92 | 49003.94 | 690827.06 | 36534.25 | 5786.04 | 3025.1 | 1072.17 | 74.46 | [8 empty] | 9957.77 | 9957.77 | 2511.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 732686 |  | 2511.92 | 48425.54 | 684260.46 | 36040.99 | 5755.97 | 2980.72 | 1061.48 | 74.46 | [8 empty] | 9872.63 | 9872.63 | 2511.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Type Cost Adjustment | 5590045 | 188130 |  |  |  | 188130
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Internal Services - Budget | 5600000 | 544556 |  |  |  | 544556
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Administration | 6603000 |  |  |  | 2390.63 | -2390.63 | 67.39 | 663.78 | 1659.46 | [10 empty] | 2323.24 | 2323.24
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Construction | 6603001 |  |  |  | 996.25 | -996.25 |  |  | 670.05 | 326.2 | [9 empty] | 996.25 | 996.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Acquisition - Misc | 6603004 |  |  |  | 5429.72 | -5429.72 | 4976.12 | 453.6 | [11 empty] | 453.6 | 453.6
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Analyst Services | 6603005 |  |  |  | 656.16 | -656.16 | 656.16
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Engineering/Mapping | 6603022 |  |  | 2511.92 | 4307.67 | -4307.67 | 1516.49 |  | 167.57 | 37.23 | 74.46 | [8 empty] | 279.26 | 279.26 | 2511.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 2025.11 | -2025.11 | 1920.65 | 104.46 | [11 empty] | 104.46 | 104.46
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Technical Services | 6603058 |  |  |  | 5017.77 | -5017.77 |  | 4534.13 | 483.64 | [10 empty] | 5017.77 | 5017.77
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 16726.22 | -16726.22 | 16402.22 |  |  | 324 | [9 empty] | 324 | 324
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Management Services | 6603076 |  |  |  | 533.05 | -533.05 | 533.05
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Administrative Services - OT | 6603150 |  |  |  | 1957.4 | -1957.4 | 1583.35 |  |  | 374.05 | [9 empty] | 374.05 | 374.05
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Gas Estimating | 6603469 |  |  |  | 3658.78 | -3658.78 | 3658.78
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Analyst Svcs Overtime | 6603855 |  |  |  | 832.81 | -832.81 | 832.81
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Hours - Straight Time | 6608193 |  |  |  | 1253.37 | -1253.37 | 1253.37
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Hours - Overtime | 6608194 |  |  |  | 2640.6 | -2640.6 | 2640.6
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 7145 |  |  | 578.4 | 6566.6 | 493.26 | 30.07 | 44.38 | 10.69 | [9 empty] | 85.14 | 85.14
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Service Planning - Planning Only | 5501163 | 7145 |  |  |  | 7145
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Estimating-Internal | 6010076 |  |  |  | 389.75 | -389.75 | 389.75
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Mapping | 6010077 |  |  |  | 188.65 | -188.65 | 103.51 | 30.07 | 44.38 | 10.69 | [9 empty] | 85.14 | 85.14
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Material Total | PGE1MATTOTAL | 508502 |  |  |  | 508502
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Material related expenses | PGE1MATERIAL | 443719 |  |  |  | 443719
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Electrical Specialties | 5300140 | 443719 |  |  |  | 443719
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Material Burden | PGE1MATBURD | 64783 |  |  |  | 64783
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Material Burden Adjustment | 5590076 | 64783 |  |  |  | 64783
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Contract Total | PGE1CONTRACT | 2265593 |  |  | 119827.67 | 2145765.33 | 62389.05 | 10024.17 | 23123.33 | 2586.12 | 21705 | [8 empty] | 57438.62 | 57438.62
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Consulting | PGE1CONSULTING | 8077 |  |  | 4902.86 | 3174.14 | 3515.75 | 666.94 | 30 | 690.17 | [9 empty] | 1387.11 | 1387.11
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Consulting Services - Engineering | 5001230 |  |  |  | 71.25 | -71.25 |  | 71.25 | [11 empty] | 71.25 | 71.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Consulting Services - Environmental Perm | 5001237 | 8077 |  |  | 4831.61 | 3245.39 | 3515.75 | 595.69 | 30 | 690.17 | [9 empty] | 1315.86 | 1315.86
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 2257516 |  |  | 114924.81 | 2142591.19 | 58873.3 | 9357.23 | 23093.33 | 1895.95 | 21705 | [8 empty] | 56051.51 | 56051.51
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Contracts | 5490000 | 146001 |  |  | 55950.57 | 90050.43 | 14507.94 | 5472.8 | 12168.88 | 1895.95 | 21905 | [8 empty] | 41442.63 | 41442.63
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Electric Construction Contract | 5490001 | 499906 |  |  |  | 499906
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Gas Construction Contract | 5490002 | 1193069 |  |  |  | 1193069
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 29766 |  |  | 17695.7 | 12070.3 | 17895.7 |  |  |  | -200 | [8 empty] | -200 | -200
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Environmental Contract | 5490015 | 39665 |  |  | 20598.54 | 19066.46 | 16129.66 | 3884.43 | 584.45 | [10 empty] | 4468.88 | 4468.88
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Construction Inspection | 5490021 | 169265 |  |  |  | 169265
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Traffic Control Contracts | 5490027 | 140000 |  |  | 20680 | 119320 | 10340 |  | 10340 | [10 empty] | 10340 | 10340
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Paving Contracts | 5490500 | 39844 |  |  |  | 39844
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER | 608264 |  | 41794.92 | 144561.19 | 463702.81 | 88123.48 | 6800.16 | 4584.11 | 3258.52 |  | 637.29 | 637.29 | 325.32 | [5 empty] | 14642.79 | 16242.69 | 40195.02
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Other Cost Elements | PGE1OTHERCE | 608264 |  | 35000 | 57641.52 | 550622.48 | 21511.58 | 1129.94 | [11 empty] | 1129.94 | 1129.94 | 35000
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 608264 |  | 35000 | 57641.52 | 550622.48 | 21511.58 | 1129.94 | [11 empty] | 1129.94 | 1129.94 | 35000
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Cash Discount earned | 5006310 |  |  |  | -295.66 | 295.66 | -272.6 | -23.06 | [11 empty] | -23.06 | -23.06
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Vehicle Lease | 5010503 |  |  |  | 47.5 | -47.5 | 47.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Permits/Fees | 5501090 | 97182 |  |  |  | 97182
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Permits/FeesLand Surveying Services | 5501092 |  |  |  | 18022.4 | -18022.4 | 16869.4 | 1153 | [11 empty] | 1153 | 1153
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Acquisition Services | 5501093 |  |  |  | 1569.34 | -1569.34 | 1569.34
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Encroachment Permit Fees | 5501095 |  |  |  | 3279.4 | -3279.4 | 3279.4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 511082 |  | 35000 | 35000 | 476082 | [15 empty] | 35000
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Other Expenses | 5591000 |  |  |  | 18.54 | -18.54 | 18.54
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Employee Related | PGE1EMPLREL |  |  |  | 29.41 | -29.41 | 29.41
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 13.32 | -13.32 | 13.32
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Reimbursed Mileage Expense | 5091140 |  |  |  | 13.32 | -13.32 | 13.32
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Meals | PGE1MEALS-EXP |  |  |  | 16.09 | -16.09 | 16.09
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Meals Expense | 5091100 |  |  |  | 16.09 | -16.09 | 16.09
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Overheads | PGE1OVERHEAD |  |  | 6794.92 | 86890.26 | -86890.26 | 66582.49 | 5670.22 | 4584.11 | 3258.52 |  | 637.29 | 637.29 | 325.32 | [5 empty] | 13512.85 | 15112.75 | 5195.02
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Capitalized A&G | PGE1CAPAG |  |  | 924.89 | 18420.06 | -18420.06 | 13856.14 | 2130.42 | 1113.84 | 394.77 | [9 empty] | 3639.03 | 3639.03 | 924.89
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Capitalized A&G | 6010050 |  |  | 924.89 | 18420.06 | -18420.06 | 13856.14 | 2130.42 | 1113.84 | 394.77 | [9 empty] | 3639.03 | 3639.03 | 924.89
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Labor Overheads | PGE1LABOROH |  |  | 2968.97 | 37740.95 | -37740.95 | 31741.6 | 786 | 1202.89 | 1041.49 | [9 empty] | 3030.38 | 3030.38 | 2968.97
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  | 2697.05 | 33642.87 | -33642.87 | 28556.11 | 459.94 | 993.14 | 936.63 | [9 empty] | 2389.71 | 2389.71 | 2697.05
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Paid Time Off | 6010100 |  |  | 505.9 | 8138.93 | -8138.93 | 7120.99 | 118.46 | 177.63 | 215.95 | [9 empty] | 512.04 | 512.04 | 505.9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Indirect Labor - Electric | 6010106 |  |  | 851.54 | 3117.25 | -3117.25 | 1873.88 | 10.19 | 254.81 | 126.83 | [9 empty] | 391.83 | 391.83 | 851.54
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Indirect Labor - Gas | 6010107 |  |  |  | 47.16 | -47.16 |  |  | 47.16 | [10 empty] | 47.16 | 47.16
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Indirect Labor - Environmental Land | 6010108 |  |  |  | 9879.91 | -9879.91 | 9436.12 | 197.17 |  | 246.62 | [9 empty] | 443.79 | 443.79
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Indirect Labor - IT | 6010111 |  |  |  | 1478.14 | -1478.14 | 1478.14
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Operation Mgmt & Support - Electric | 6010114 |  |  | 770.66 | 3502.11 | -3502.11 | 2376.84 | 9.23 | 230.6 | 114.78 | [9 empty] | 354.61 | 354.61 | 770.66
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 72.31 | -72.31 |  |  | 72.31 | [10 empty] | 72.31 | 72.31
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 4543.23 | -4543.23 | 4277.44 | 118.08 |  | 147.71 | [9 empty] | 265.79 | 265.79
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Operation Mgmt & Support - IT | 6010119 |  |  |  | 590.32 | -590.32 | 590.32
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Fleet OH | 6010123 |  |  |  | 1402.38 | -1402.38 | 1402.38
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Fleet OH - Elec | 6010125 |  |  | 568.95 | 830.76 | -830.76 |  | 6.81 | 170.26 | 84.74 | [9 empty] | 261.81 | 261.81 | 568.95
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Fleet OH - Gas | 6010126 |  |  |  | 40.37 | -40.37 |  |  | 40.37 | [10 empty] | 40.37 | 40.37
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  | 271.92 | 4098.08 | -4098.08 | 3185.49 | 326.06 | 209.75 | 104.86 | [9 empty] | 640.67 | 640.67 | 271.92
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Building Service Overhead | 6010112 |  |  | 173.46 | 2527.04 | -2527.04 | 1944.86 | 208.01 | 133.81 | 66.9 | [9 empty] | 408.72 | 408.72 | 173.46
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | IT Device OH | 6010113 |  |  | 98.46 | 1571.04 | -1571.04 | 1240.63 | 118.05 | 75.94 | 37.96 | [9 empty] | 231.95 | 231.95 | 98.46
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Other Overhead | PGE1OTHEROH |  |  | 1301.16 | 21990.64 | -21990.64 | 17523.39 | 1621.32 | 1043.02 | 501.75 | [9 empty] | 3166.09 | 3166.09 | 1301.16
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Benefits OH | 6010120 |  |  | 959.7 | 16425.95 | -16425.95 | 13104.63 | 1211.89 | 779.63 | 370.1 | [9 empty] | 2361.62 | 2361.62 | 959.7
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Payroll Taxes OH | 6010121 |  |  | 341.46 | 5564.69 | -5564.69 | 4418.76 | 409.43 | 263.39 | 131.65 | [9 empty] | 804.47 | 804.47 | 341.46
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR |  |  | 1599.9 | 8738.61 | -8738.61 | 3461.36 | 1132.48 | 1224.36 | 1320.51 |  | 637.29 | 637.29 | 325.32 | [5 empty] | 3677.35 | 5277.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | AFUDC-Borrowed | 5590030 |  |  | 1599.9 | 5655.59 | -5655.59 | 3026.52 | 341.07 | 331.05 | 357.05 |  | 637.29 | 637.29 | 325.32 | [5 empty] | 1029.17 | 2629.07
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | AFUDC-Equity | 5590031 |  |  |  | 3083.02 | -3083.02 | 434.84 | 791.41 | 893.31 | 963.46 | [9 empty] | 2648.18 | 2648.18
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 166667 |  |  | 22851.36 | 143815.64 | 214.56 | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 166667 |  |  | 22851.36 | 143815.64 | 214.56 | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 74.09 | -74.09 | 74.09
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 74.09 | -74.09 | 74.09
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 74.09 | -74.09 | 74.09
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 74.09 | -74.09 | 74.09
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 74.09 | -74.09 | 74.09
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Contract Total | PGE1CONTRACT | 166667 |  |  | 22636.8 | 144030.2 |  | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 166667 |  |  | 22636.8 | 144030.2 |  | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Contracts | 5490000 | 166667 |  |  |  | 166667
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 22636.8 | -22636.8 |  | 37622.48 | -14985.68 | [10 empty] | 22636.8 | 22636.8
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  |  | 140.47 | -140.47 | 140.47
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  |  | 140.47 | -140.47 | 140.47
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 24.26 | -24.26 | 24.26
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 24.26 | -24.26 | 24.26
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 80.84 | -80.84 | 80.84
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 74.01 | -74.01 | 74.01
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 16.46 | -16.46 | 16.46
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 25.72 | -25.72 | 25.72
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 18.2 | -18.2 | 18.2
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Fleet OH | 6010123 |  |  |  | 13.63 | -13.63 | 13.63
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 6.83 | -6.83 | 6.83
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 4.46 | -4.46 | 4.46
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | IT Device OH | 6010113 |  |  |  | 2.37 | -2.37 | 2.37
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 35.37 | -35.37 | 35.37
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Benefits OH | 6010120 |  |  |  | 26.75 | -26.75 | 26.75
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 8.62 | -8.62 | 8.62
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 166667 |  | 14.01 | 27145.31 | 139521.69 | 608.93 | 46799.02 | -20431.72 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 26522.37 | 26536.38
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 166667 |  | 14.01 | 27145.31 | 139521.69 | 608.93 | 46799.02 | -20431.72 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 26522.37 | 26536.38
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 201.52 | -201.52 | 201.52
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 201.52 | -201.52 | 201.52
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 201.52 | -201.52 | 201.52
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 201.08 | -201.08 | 201.08
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Construction | 6603001 |  |  |  | 52.9 | -52.9 | 52.9
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Engineering/Mapping | 6603022 |  |  |  | 148.18 | -148.18 | 148.18
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 0.44 | -0.44 | 0.44
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Mapping | 6010077 |  |  |  | 0.44 | -0.44 | 0.44
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Contract Total | PGE1CONTRACT | 166667 |  |  | 26012.47 | 140654.53 |  | 46659.4 | -20646.93 | [10 empty] | 26012.47 | 26012.47
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 166667 |  |  | 26012.47 | 140654.53 |  | 46659.4 | -20646.93 | [10 empty] | 26012.47 | 26012.47
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Contracts | 5490000 | 166667 |  |  |  | 166667
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 26012.47 | -26012.47 |  | 46659.4 | -20646.93 | [10 empty] | 26012.47 | 26012.47
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 14.01 | 931.32 | -931.32 | 407.41 | 139.62 | 215.21 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 509.9 | 523.91
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  | 14.01 | 931.32 | -931.32 | 407.41 | 139.62 | 215.21 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 509.9 | 523.91
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 65.98 | -65.98 | 65.98
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 65.98 | -65.98 | 65.98
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 235.53 | -235.53 | 235.53
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 216.26 | -216.26 | 216.26
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 44.77 | -44.77 | 44.77
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 51.59 | -51.59 | 51.59
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Indirect Labor - Gas | 6010107 |  |  |  | 17.73 | -17.73 | 17.73
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 34.26 | -34.26 | 34.26
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Operation Mgmt & Support - Gas | 6010115 |  |  |  | 25.01 | -25.01 | 25.01
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Fleet OH | 6010123 |  |  |  | 42.9 | -42.9 | 42.9
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 19.27 | -19.27 | 19.27
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 12.57 | -12.57 | 12.57
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | IT Device OH | 6010113 |  |  |  | 6.7 | -6.7 | 6.7
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 96.97 | -96.97 | 96.97
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Benefits OH | 6010120 |  |  |  | 72.65 | -72.65 | 72.65
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 24.32 | -24.32 | 24.32
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  | 14.01 | 532.84 | -532.84 | 8.93 | 139.62 | 215.21 | 155.07 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 509.9 | 523.91
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  | 14.01 | 158.98 | -158.98 | 6.97 | 37.88 | 58.19 | 41.93 |  | 2.49 | 2.49 | 2.58 | 2.58 | 2.58 | 1.29 |  |  | 138 | 152.01
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 373.86 | -373.86 | 1.96 | 101.74 | 157.02 | 113.14 | [9 empty] | 371.9 | 371.9
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 950000 |  | 3.76 | 8448.46 | 941551.54 | 8275.39 | 50.59 | 3891.36 | -3772.64 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 950000 |  | 3.76 | 8448.46 | 941551.54 | 8275.39 | 50.59 | 3891.36 | -3772.64 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 55.27 | -55.27 | 55.27
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 55.27 | -55.27 | 55.27
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 55.27 | -55.27 | 55.27
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 31.7 | -31.7 | 31.7
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 31.7 | -31.7 | 31.7
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 23.57 | -23.57 | 23.57
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Mapping | 6010077 |  |  |  | 23.57 | -23.57 | 23.57
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Contract Total | PGE1CONTRACT | 950000 |  |  | 7367.79 | 942632.21 | 7367.79 |  | 3832 | -3832
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 950000 |  |  | 7367.79 | 942632.21 | 7367.79 |  | 3832 | -3832
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Contracts | 5490000 | 950000 |  |  | 3499.88 | 946500.12 | 3499.88
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | [7 empty] | 3832 | -3832
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 3867.91 | -3867.91 | 3867.91
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 3.76 | 1025.4 | -1025.4 | 852.33 | 50.59 | 59.36 | 59.36 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  |  | 663.75 | -663.75 | 663.75
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 663.75 | -663.75 | 663.75
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Land Acquisition Services | 5501093 |  |  |  | 663.75 | -663.75 | 663.75
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  | 3.76 | 361.65 | -361.65 | 188.58 | 50.59 | 59.36 | 59.36 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 18.1 | -18.1 | 18.1
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 18.1 | -18.1 | 18.1
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 50.69 | -50.69 | 50.69
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 46.03 | -46.03 | 46.03
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 12.76 | -12.76 | 12.76
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 8.28 | -8.28 | 8.28
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 11.85 | -11.85 | 11.85
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 5.08 | -5.08 | 5.08
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 4.44 | -4.44 | 4.44
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Fleet OH | 6010123 |  |  |  | 3.62 | -3.62 | 3.62
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 4.66 | -4.66 | 4.66
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 3.04 | -3.04 | 3.04
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 1.62 | -1.62 | 1.62
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 23.26 | -23.26 | 23.26
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 17.38 | -17.38 | 17.38
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 5.88 | -5.88 | 5.88
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  | 3.76 | 269.6 | -269.6 | 96.53 | 50.59 | 59.36 | 59.36 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 169.31 | 173.07
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  | 3.76 | 118.38 | -118.38 | 67.1 | 15.42 | 16.05 | 16.05 |  | 0.82 | 0.82 | 0.85 | 0.85 | 0.42 |  |  |  | 47.52 | 51.28
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 151.22 | -151.22 | 29.43 | 35.17 | 43.31 | 43.31 | [9 empty] | 121.79 | 121.79
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 950000 |  |  | 19761.25 | 930238.75 | 19398.23 | 118.54 | 3295.24 | -3050.76 | [9 empty] | 363.02 | 363.02
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 950000 |  |  | 19761.25 | 930238.75 | 19398.23 | 118.54 | 3295.24 | -3050.76 | [9 empty] | 363.02 | 363.02
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 356.94 | -356.94 | 356.94
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 356.94 | -356.94 | 356.94
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 356.94 | -356.94 | 356.94
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 300.73 | -300.73 | 300.73
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 148.18 | -148.18 | 148.18
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 67.39 | -67.39 | 67.39
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Design Overtime Services | 6603103 |  |  |  | 85.16 | -85.16 | 85.16
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 56.21 | -56.21 | 56.21
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Mapping | 6010077 |  |  |  | 56.21 | -56.21 | 56.21
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Contract Total | PGE1CONTRACT |  |  |  | 17566.47 | -17566.47 | 17566.47 |  | 3173 | -3173
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC |  |  |  | 17566.47 | -17566.47 | 17566.47 |  | 3173 | -3173
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Contracts | 5490000 |  |  |  | 14101.08 | -14101.08 | 14101.08
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | [7 empty] | 3173 | -3173
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 3465.39 | -3465.39 | 3465.39
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 950000 |  |  | 1837.84 | 948162.16 | 1474.82 | 118.54 | 122.24 | 122.24 | [9 empty] | 363.02 | 363.02
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE | 950000 |  |  | 593.75 | 949406.25 | 593.75
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 950000 |  |  | 593.75 | 949406.25 | 593.75
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Land Acquisition Services | 5501093 |  |  |  | 593.75 | -593.75 | 593.75
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 950000 |  |  |  | 950000
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 1244.09 | -1244.09 | 881.07 | 118.54 | 122.24 | 122.24 | [9 empty] | 363.02 | 363.02
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 127.27 | -127.27 | 127.27
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 127.27 | -127.27 | 127.27
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 365.63 | -365.63 | 365.63
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 338.92 | -338.92 | 338.92
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 80.31 | -80.31 | 80.31
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 104.23 | -104.23 | 104.23
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 25.19 | -25.19 | 25.19
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 64.58 | -64.58 | 64.58
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 9.44 | -9.44 | 9.44
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Fleet OH | 6010123 |  |  |  | 55.17 | -55.17 | 55.17
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 26.71 | -26.71 | 26.71
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 18.48 | -18.48 | 18.48
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 8.23 | -8.23 | 8.23
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 121.46 | -121.46 | 121.46
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 85.12 | -85.12 | 85.12
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 36.34 | -36.34 | 36.34
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 629.73 | -629.73 | 266.71 | 118.54 | 122.24 | 122.24 | [9 empty] | 363.02 | 363.02
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 304.82 | -304.82 | 202.62 | 36.1 | 33.05 | 33.05 | [9 empty] | 102.2 | 102.2
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 324.91 | -324.91 | 64.09 | 82.44 | 89.19 | 89.19 | [9 empty] | 260.82 | 260.82
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 950000 |  | 11.16 | 12512.51 | 937487.49 | 12283.16 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 950000 |  | 11.16 | 12512.51 | 937487.49 | 12283.16 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 201.47 | -201.47 | 201.47
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 201.47 | -201.47 | 201.47
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 201.47 | -201.47 | 201.47
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 166.48 | -166.48 | 166.48
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 134.78 | -134.78 | 134.78
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 31.7 | -31.7 | 31.7
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 34.99 | -34.99 | 34.99
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Mapping | 6010077 |  |  |  | 34.99 | -34.99 | 34.99
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Contract Total | PGE1CONTRACT | 950000 |  |  | 10934.44 | 939065.56 | 10934.44
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 950000 |  |  | 10934.44 | 939065.56 | 10934.44
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Contracts | 5490000 | 950000 |  |  | 7191.36 | 942808.64 | 7191.36
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 3743.08 | -3743.08 | 3743.08
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 11.16 | 1376.6 | -1376.6 | 1147.25 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  |  | 663.75 | -663.75 | 663.75
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  |  | 663.75 | -663.75 | 663.75
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Land Acquisition Services | 5501093 |  |  |  | 663.75 | -663.75 | 663.75
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  | 11.16 | 712.85 | -712.85 | 483.5 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 65.98 | -65.98 | 65.98
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 65.98 | -65.98 | 65.98
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 172.4 | -172.4 | 172.4
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 155.94 | -155.94 | 155.94
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 45.18 | -45.18 | 45.18
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 12.24 | -12.24 | 12.24
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 62.23 | -62.23 | 62.23
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 7.53 | -7.53 | 7.53
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 23.32 | -23.32 | 23.32
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Fleet OH | 6010123 |  |  |  | 5.44 | -5.44 | 5.44
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 16.46 | -16.46 | 16.46
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 10.75 | -10.75 | 10.75
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 5.71 | -5.71 | 5.71
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 84.01 | -84.01 | 84.01
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 63.23 | -63.23 | 63.23
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 20.78 | -20.78 | 20.78
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  | 11.16 | 390.46 | -390.46 | 161.11 | 75.09 | 71.55 | 71.55 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 218.19 | 229.35
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  | 11.16 | 192.09 | -192.09 | 119.34 | 22.89 | 19.35 | 19.35 |  | 2.43 | 2.43 | 2.52 | 2.52 | 1.26 |  |  |  | 61.59 | 72.75
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 198.37 | -198.37 | 41.77 | 52.2 | 52.2 | 52.2 | [9 empty] | 156.6 | 156.6
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 150000 |  | 361623 | 383061.66 | -233061.66 | 604.67 | 15933.64 | 2441.83 | 1971.04 | 487.48 |  |  | 100000 | 130000 | 131623 |  |  |  | 20833.99 | 382456.99
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 361623 | 383061.66 | -233061.66 | 604.67 | 15933.64 | 2441.83 | 1971.04 | 487.48 |  |  | 100000 | 130000 | 131623 |  |  |  | 20833.99 | 382456.99
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 2706.11 | -2706.11 | 173.18 | 463.3 | 1263.63 | 318.52 | 487.48 | [8 empty] | 2532.93 | 2532.93
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 2706.11 | -2706.11 | 173.18 | 463.3 | 1263.63 | 318.52 | 487.48 | [8 empty] | 2532.93 | 2532.93
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 2706.11 | -2706.11 | 173.18 | 463.3 | 1263.63 | 318.52 | 487.48 | [8 empty] | 2532.93 | 2532.93
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 2676.07 | -2676.07 | 173.18 | 446.51 | 1250.7 | 318.2 | 487.48 | [8 empty] | 2502.89 | 2502.89
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Administration | 6603000 |  |  |  | 522.3 | -522.3 |  |  |  | 243.74 | 278.56 | [8 empty] | 522.3 | 522.3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  | 670.05 | [10 empty] | 670.05 | 670.05
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 243.2 | -243.2 | 74.09 |  | 94.65 | 74.46 | [9 empty] | 169.11 | 169.11
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 415.59 | -415.59 | 67.39 | 139.28 |  |  | 208.92 | [8 empty] | 348.2 | 348.2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 486 | -486 |  |  | 486 | [10 empty] | 486 | 486
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 161.3 | -161.3 | 31.7 | 129.6 | [11 empty] | 129.6 | 129.6
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Electric Estimating | 6603466 |  |  |  | 177.63 | -177.63 |  | 177.63 | [11 empty] | 177.63 | 177.63
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 30.04 | -30.04 |  | 16.79 | 12.93 | 0.32 | [9 empty] | 30.04 | 30.04
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Mapping | 6010077 |  |  |  | 30.04 | -30.04 |  | 16.79 | 12.93 | 0.32 | [9 empty] | 30.04 | 30.04
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 150000 |  |  | 14170.23 | 135829.77 |  | 14561.3 | -1367.69 | 976.62 | [9 empty] | 14170.23 | 14170.23
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Consulting | PGE1CONSULTING |  |  |  | 118.75 | -118.75 |  | 95 | 23.75 | [10 empty] | 118.75 | 118.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Consulting Services - Engineering | 5001230 |  |  |  | 118.75 | -118.75 |  | 95 | 23.75 | [10 empty] | 118.75 | 118.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 150000 |  |  | 14051.48 | 135948.52 |  | 14466.3 | -1391.44 | 976.62 | [9 empty] | 14051.48 | 14051.48
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Contracts | 5490000 | 150000 |  |  |  | 150000
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 6170.53 | -6170.53 |  | 8967.12 | -3668.15 | 871.56 | [9 empty] | 6170.53 | 6170.53
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 7880.95 | -7880.95 |  | 5499.18 | 2276.71 | 105.06 | [9 empty] | 7880.95 | 7880.95
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 361623 | 366185.32 | -366185.32 | 431.49 | 909.04 | 2545.89 | 675.9 |  |  |  | 100000 | 130000 | 131623 |  |  |  | 4130.83 | 365753.83
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 361623 | 361789.25 | -361789.25 | 166.25 | [6 empty] | 100000 | 130000 | 131623 |  |  |  |  | 361623
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 361623 | 361789.25 | -361789.25 | 166.25 | [6 empty] | 100000 | 130000 | 131623 |  |  |  |  | 361623
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Land Acquisition Services | 5501093 |  |  |  | 166.25 | -166.25 | 166.25
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 361623 | 361623 | -361623 | [7 empty] | 100000 | 130000 | 131623 |  |  |  |  | 361623
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 4396.07 | -4396.07 | 265.24 | 909.04 | 2545.89 | 675.9 | [9 empty] | 4130.83 | 4130.83
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 830.96 | -830.96 | 77.81 | 170.59 | 465.27 | 117.29 | [9 empty] | 753.15 | 753.15
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 830.96 | -830.96 | 77.81 | 170.59 | 465.27 | 117.29 | [9 empty] | 753.15 | 753.15
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 2268.28 | -2268.28 | 173.64 | 460.63 | 1336.36 | 297.65 | [9 empty] | 2094.64 | 2094.64
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 2057.21 | -2057.21 | 167.98 | 414.79 | 1207.37 | 267.07 | [9 empty] | 1889.23 | 1889.23
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 451.65 | -451.65 | 39.71 | 93.3 | 254.49 | 64.15 | [9 empty] | 411.94 | 411.94
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 383.75 | -383.75 | 28.87 | 65.91 | 263.62 | 25.35 | [9 empty] | 354.88 | 354.88
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 400.41 | -400.41 | 47.6 | 95 | 171.7 | 86.11 | [9 empty] | 352.81 | 352.81
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 339.08 | -339.08 | 17.91 | 59.65 | 238.58 | 22.94 | [9 empty] | 321.17 | 321.17
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 225.19 | -225.19 | 13.88 | 56.89 | 102.84 | 51.58 | [9 empty] | 211.31 | 211.31
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Fleet OH | 6010123 |  |  |  | 20.01 | -20.01 | 20.01
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 237.12 | -237.12 |  | 44.04 | 176.14 | 16.94 | [9 empty] | 237.12 | 237.12
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 211.07 | -211.07 | 5.66 | 45.84 | 128.99 | 30.58 | [9 empty] | 205.41 | 205.41
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 136.68 | -136.68 | 5.66 | 29.24 | 82.28 | 19.5 | [9 empty] | 131.02 | 131.02
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 74.39 | -74.39 |  | 16.6 | 46.71 | 11.08 | [9 empty] | 74.39 | 74.39
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 1027.75 | -1027.75 | 12.12 | 227.95 | 641.4 | 146.28 | [9 empty] | 1015.63 | 1015.63
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 757.7 | -757.7 |  | 170.38 | 479.42 | 107.9 | [9 empty] | 757.7 | 757.7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 270.05 | -270.05 | 12.12 | 57.57 | 161.98 | 38.38 | [9 empty] | 257.93 | 257.93
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 269.08 | -269.08 | 1.67 | 49.87 | 102.86 | 114.68 | [9 empty] | 267.41 | 267.41
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 72.76 | -72.76 | 0.39 | 13.55 | 27.81 | 31.01 | [9 empty] | 72.37 | 72.37
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 196.32 | -196.32 | 1.28 | 36.32 | 75.05 | 83.67 | [9 empty] | 195.04 | 195.04
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 150000 |  | 1020046 | 1045646.52 | -895646.52 | 2467.61 | 14932.4 | 7721.95 | 25048.56 | -24570 | 2793 |  |  | 400000 | 67253 |  |  |  | 23132.91 | 493178.91 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 1020046 | 1045646.52 | -895646.52 | 2467.61 | 14932.4 | 7721.95 | 25048.56 | -24570 | 2793 |  |  | 400000 | 67253 |  |  |  | 23132.91 | 493178.91 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 3974.41 | -3974.41 | 896.82 | 629.96 | 2349.82 | 97.81 | [9 empty] | 3077.59 | 3077.59
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 3974.41 | -3974.41 | 896.82 | 629.96 | 2349.82 | 97.81 | [9 empty] | 3077.59 | 3077.59
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 3974.41 | -3974.41 | 896.82 | 629.96 | 2349.82 | 97.81 | [9 empty] | 3077.59 | 3077.59
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 3951.57 | -3951.57 | 896.82 | 613.71 | 2343.23 | 97.81 | [9 empty] | 3054.75 | 3054.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Acquisition - Misc | 6603004 |  |  |  | 194.4 | -194.4 |  |  | 194.4 | [10 empty] | 194.4 | 194.4
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 628.28 | -628.28 | 37.05 |  | 591.23 | [10 empty] | 591.23 | 591.23
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 69.64 | -69.64 |  | 69.64 | [11 empty] | 69.64 | 69.64
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 2417.37 | -2417.37 | 859.77 |  | 1557.6 | [10 empty] | 1557.6 | 1557.6
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Administrative Services - OT | 6603150 |  |  |  | 97.81 | -97.81 |  |  |  | 97.81 | [9 empty] | 97.81 | 97.81
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 129.6 | -129.6 |  | 129.6 | [11 empty] | 129.6 | 129.6
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Electric Estimating | 6603466 |  |  |  | 414.47 | -414.47 |  | 414.47 | [11 empty] | 414.47 | 414.47
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 22.84 | -22.84 |  | 16.25 | 6.59 | [10 empty] | 22.84 | 22.84
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Mapping | 6010077 |  |  |  | 22.84 | -22.84 |  | 16.25 | 6.59 | [10 empty] | 22.84 | 22.84
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 150000 |  | 2793 | 15818.27 | 134181.73 |  | 12605.34 | 419.93 | 24570 | -24570 | 2793 | [7 empty] | 13025.27 | 15818.27
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Consulting | PGE1CONSULTING |  |  |  | 71.25 | -71.25 |  | 47.5 | 23.75 | [10 empty] | 71.25 | 71.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Consulting Services - Engineering | 5001230 |  |  |  | 71.25 | -71.25 |  | 47.5 | 23.75 | [10 empty] | 71.25 | 71.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 150000 |  | 2793 | 15747.02 | 134252.98 |  | 12557.84 | 396.18 | 24570 | -24570 | 2793 | [7 empty] | 12954.02 | 15747.02
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Contracts | 5490000 | 150000 |  |  |  | 150000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  | 2793 | 8203.25 | -8203.25 |  | 7187.82 | -1777.57 | 24570 | -24570 | 2793 | [7 empty] | 5410.25 | 8203.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 7543.77 | -7543.77 |  | 5370.02 | 2173.75 | [10 empty] | 7543.77 | 7543.77
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 1017253 | 1025853.84 | -1025853.84 | 1570.79 | 1697.1 | 4952.2 | 380.75 |  |  |  |  | 400000 | 67253 |  |  |  | 7030.05 | 474283.05 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 1017253 | 1017704.25 | -1017704.25 | 47.5 | 403.75 | [6 empty] | 400000 | 67253 |  |  |  | 403.75 | 467656.75 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 1017253 | 1017704.25 | -1017704.25 | 47.5 | 403.75 | [6 empty] | 400000 | 67253 |  |  |  | 403.75 | 467656.75 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Land Acquisition Services | 5501093 |  |  |  | 451.25 | -451.25 | 47.5 | 403.75 | [11 empty] | 403.75 | 403.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1017253 | 1017253 | -1017253 | [8 empty] | 400000 | 67253 |  |  |  |  | 467253 | 550000
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 8149.59 | -8149.59 | 1523.29 | 1293.35 | 4952.2 | 380.75 | [9 empty] | 6626.3 | 6626.3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 1536.11 | -1536.11 | 402.94 | 231.95 | 865.21 | 36.01 | [9 empty] | 1133.17 | 1133.17
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 1536.11 | -1536.11 | 402.94 | 231.95 | 865.21 | 36.01 | [9 empty] | 1133.17 | 1133.17
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 4524.34 | -4524.34 | 1045.75 | 680.12 | 2714.48 | 83.99 | [9 empty] | 3478.59 | 3478.59
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 4167.36 | -4167.36 | 1014.03 | 615.14 | 2463.23 | 74.96 | [9 empty] | 3153.33 | 3153.33
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 825.46 | -825.46 | 205.64 | 126.87 | 473.25 | 19.7 | [9 empty] | 619.82 | 619.82
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 1226.1 | -1226.1 | 349.4 | 146.02 | 730.68 | [10 empty] | 876.7 | 876.7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 173.63 | -173.63 |  | 70.39 | 68.68 | 34.56 | [9 empty] | 173.63 | 173.63
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1010.18 | -1010.18 | 216.76 | 132.14 | 661.28 | [10 empty] | 793.42 | 793.42
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 104 | -104 |  | 42.16 | 41.14 | 20.7 | [9 empty] | 104 | 104
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Fleet OH | 6010123 |  |  |  | 242.23 | -242.23 | 242.23
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 585.76 | -585.76 |  | 97.56 | 488.2 | [10 empty] | 585.76 | 585.76
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 356.98 | -356.98 | 31.72 | 64.98 | 251.25 | 9.03 | [9 empty] | 325.26 | 325.26
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 239.22 | -239.22 | 31.72 | 41.46 | 160.28 | 5.76 | [9 empty] | 207.5 | 207.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 117.76 | -117.76 |  | 23.52 | 90.97 | 3.27 | [9 empty] | 117.76 | 117.76
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 1683.52 | -1683.52 | 67.79 | 323.22 | 1249.36 | 43.15 | [9 empty] | 1615.73 | 1615.73
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 1207.3 | -1207.3 |  | 241.6 | 933.87 | 31.83 | [9 empty] | 1207.3 | 1207.3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 476.22 | -476.22 | 67.79 | 81.62 | 315.49 | 11.32 | [9 empty] | 408.43 | 408.43
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 405.62 | -405.62 | 6.81 | 58.06 | 123.15 | 217.6 | [9 empty] | 398.81 | 398.81
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 109.68 | -109.68 | 1.58 | 15.96 | 33.3 | 58.84 | [9 empty] | 108.1 | 108.1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 295.94 | -295.94 | 5.23 | 42.1 | 89.85 | 158.76 | [9 empty] | 290.71 | 290.71
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Order Financial Costs | PGE1ORDFIN | 300000 |  | 1451350 | 1510201.03 | -1210201.03 | 199.39 | 11297.45 | 409.58 | 46944.61 |  |  | 500000 | 500000 | 443055 | 8295 |  |  |  | 58651.64 | 1510001.64
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 300000 |  | 1451350 | 1510201.03 | -1210201.03 | 199.39 | 11297.45 | 409.58 | 46944.61 |  |  | 500000 | 500000 | 443055 | 8295 |  |  |  | 58651.64 | 1510001.64
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Activity Type Total | PGE1ACTV-TOT |  |  |  | 3331.94 | -3331.94 | 74.09 | 2316.04 | 411.65 | 530.16 | [9 empty] | 3257.85 | 3257.85
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Activity Types | PGE1ACTVTYPES |  |  |  | 3331.94 | -3331.94 | 74.09 | 2316.04 | 411.65 | 530.16 | [9 empty] | 3257.85 | 3257.85
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 3331.94 | -3331.94 | 74.09 | 2316.04 | 411.65 | 530.16 | [9 empty] | 3257.85 | 3257.85
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 3321.55 | -3321.55 | 74.09 | 2315.97 | 401.33 | 530.16 | [9 empty] | 3247.46 | 3247.46
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Acquisition - Misc | 6603004 |  |  |  | 421.2 | -421.2 |  | 194.4 | 97.2 | 129.6 | [9 empty] | 421.2 | 421.2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Engineering/Mapping | 6603022 |  |  |  | 1603.18 | -1603.18 | 74.09 | 1148.4 | 304.13 | 76.56 | [9 empty] | 1529.09 | 1529.09
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 104.46 | -104.46 |  | 104.46 | [11 empty] | 104.46 | 104.46
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 324 | -324 |  |  |  | 324 | [9 empty] | 324 | 324
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 322.26 | -322.26 |  | 322.26 | [11 empty] | 322.26 | 322.26
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Administrative Services - OT | 6603150 |  |  |  | 352.05 | -352.05 |  | 352.05 | [11 empty] | 352.05 | 352.05
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Rights - Misc | 6603227 |  |  |  | 194.4 | -194.4 |  | 194.4 | [11 empty] | 194.4 | 194.4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 10.39 | -10.39 |  | 0.07 | 10.32 | [10 empty] | 10.39 | 10.39
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Mapping | 6010077 |  |  |  | 10.39 | -10.39 |  | 0.07 | 10.32 | [10 empty] | 10.39 | 10.39
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Contract Total | PGE1CONTRACT | 300000 |  |  | 49162.41 | 250837.59 |  | 4485.44 | -822.58 | 45499.55 | [9 empty] | 49162.41 | 49162.41
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Consulting | PGE1CONSULTING |  |  |  | 95 | -95 |  | 23.75 | 71.25 | [10 empty] | 95 | 95
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Consulting Services - Engineering | 5001230 |  |  |  | 95 | -95 |  | 23.75 | 71.25 | [10 empty] | 95 | 95
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Other Contract | PGE1OTHCONTRAC | 300000 |  |  | 49067.41 | 250932.59 |  | 4461.69 | -893.83 | 45499.55 | [9 empty] | 49067.41 | 49067.41
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Contracts | 5490000 | 300000 |  |  |  | 300000
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  |  | 45698.5 | -45698.5 |  | 4461.69 | -4262.74 | 45499.55 | [9 empty] | 45698.5 | 45698.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Environmental Contract | 5490015 |  |  |  | 3368.91 | -3368.91 |  |  | 3368.91 | [10 empty] | 3368.91 | 3368.91
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Order Other Costs | PGE1ORD-OTHER |  |  | 1451350 | 1457706.68 | -1457706.68 | 125.3 | 4495.97 | 820.51 | 914.9 |  |  | 500000 | 500000 | 443055 | 8295 |  |  |  | 6231.38 | 1457581.38
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Other Cost Elements | PGE1OTHERCE |  |  | 1451350 | 1451350 | -1451350 | [6 empty] | 500000 | 500000 | 443055 | 8295 |  |  |  |  | 1451350
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 1451350 | 1451350 | -1451350 | [6 empty] | 500000 | 500000 | 443055 | 8295 |  |  |  |  | 1451350
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1451350 | 1451350 | -1451350 | [6 empty] | 500000 | 500000 | 443055 | 8295 |  |  |  |  | 1451350
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Order Overheads | PGE1OVERHEAD |  |  |  | 6356.68 | -6356.68 | 125.3 | 4495.97 | 820.51 | 914.9 | [9 empty] | 6231.38 | 6231.38
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Capitalized A&G | PGE1CAPAG |  |  |  | 1232.83 | -1232.83 | 33.29 | 852.77 | 151.57 | 195.2 | [9 empty] | 1199.54 | 1199.54
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Capitalized A&G | 6010050 |  |  |  | 1232.83 | -1232.83 | 33.29 | 852.77 | 151.57 | 195.2 | [9 empty] | 1199.54 | 1199.54
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Labor Overheads | PGE1LABOROH |  |  |  | 3485.43 | -3485.43 | 86.4 | 2464.01 | 455.11 | 479.91 | [9 empty] | 3399.03 | 3399.03
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 3152.56 | -3152.56 | 83.78 | 2226.88 | 412.11 | 429.79 | [9 empty] | 3068.78 | 3068.78
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Paid Time Off | 6010100 |  |  |  | 673.11 | -673.11 | 16.99 | 466.45 | 82.9 | 106.77 | [9 empty] | 656.12 | 656.12
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Indirect Labor - Electric | 6010106 |  |  |  | 659.99 | -659.99 | 28.87 | 498.57 | 106.6 | 25.95 | [9 empty] | 631.12 | 631.12
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Indirect Labor - Environmental Land | 6010108 |  |  |  | 493.25 | -493.25 |  | 298.65 | 34.34 | 160.26 | [9 empty] | 493.25 | 493.25
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 589.1 | -589.1 | 17.91 | 451.22 | 96.48 | 23.49 | [9 empty] | 571.19 | 571.19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 295.42 | -295.42 |  | 178.87 | 20.57 | 95.98 | [9 empty] | 295.42 | 295.42
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Fleet OH | 6010123 |  |  |  | 20.01 | -20.01 | 20.01
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Fleet OH - Elec | 6010125 |  |  |  | 421.68 | -421.68 |  | 333.12 | 71.22 | 17.34 | [9 empty] | 421.68 | 421.68
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 332.87 | -332.87 | 2.62 | 237.13 | 43 | 50.12 | [9 empty] | 330.25 | 330.25
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Building Service Overhead | 6010112 |  |  |  | 213.29 | -213.29 | 2.62 | 151.27 | 27.43 | 31.97 | [9 empty] | 210.67 | 210.67
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | IT Device OH | 6010113 |  |  |  | 119.58 | -119.58 |  | 85.86 | 15.57 | 18.15 | [9 empty] | 119.58 | 119.58
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Other Overhead | PGE1OTHEROH |  |  |  | 1638.42 | -1638.42 | 5.61 | 1179.19 | 213.83 | 239.79 | [9 empty] | 1632.81 | 1632.81
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Benefits OH | 6010120 |  |  |  | 1218.14 | -1218.14 |  | 881.42 | 159.85 | 176.87 | [9 empty] | 1218.14 | 1218.14
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Payroll Taxes OH | 6010121 |  |  |  | 420.28 | -420.28 | 5.61 | 297.77 | 53.98 | 62.92 | [9 empty] | 414.67 | 414.67
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 950000 |  | 1985972.09 | 2021954.51 | -1071954.51 |  | 237.15 | 12632.89 | 21271.68 | 1840.7 | 214.1 | 87344.1 | 100217.63 | 100217.63 | 100217.63 | 100217.63 | 217.63 | 217.63 | 35982.42 | 524846.4 | 1497108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 950000 |  | 1985972.09 | 2021954.51 | -1071954.51 |  | 237.15 | 12632.89 | 21271.68 | 1840.7 | 214.1 | 87344.1 | 100217.63 | 100217.63 | 100217.63 | 100217.63 | 217.63 | 217.63 | 35982.42 | 524846.4 | 1497108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 11860.47 | -11860.47 |  | 76.56 | 3082.06 | 7248.21 | 1453.64 | [8 empty] | 11860.47 | 11860.47
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 11860.47 | -11860.47 |  | 76.56 | 3082.06 | 7248.21 | 1453.64 | [8 empty] | 11860.47 | 11860.47
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 11860.47 | -11860.47 |  | 76.56 | 3082.06 | 7248.21 | 1453.64 | [8 empty] | 11860.47 | 11860.47
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 11843.73 | -11843.73 |  | 76.56 | 3070.64 | 7242.89 | 1453.64 | [8 empty] | 11843.73 | 11843.73
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 153.12 | -153.12 |  | 76.56 | 76.56 | [10 empty] | 153.12 | 153.12
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 34.82 | -34.82 |  |  | 34.82 | [10 empty] | 34.82 | 34.82
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 7581.6 | -7581.6 |  |  | 1360.8 | 5119.2 | 1101.6 | [8 empty] | 7581.6 | 7581.6
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 1181.62 | -1181.62 |  |  | 1181.62 | [10 empty] | 1181.62 | 1181.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Engineering Services - OT | 6603148 |  |  |  | 55.44 | -55.44 |  |  |  | 55.44 | [9 empty] | 55.44 | 55.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Administrative Services - OT | 6603150 |  |  |  | 2772.33 | -2772.33 |  |  | 352.04 | 2068.25 | 352.04 | [8 empty] | 2772.33 | 2772.33
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 64.8 | -64.8 |  |  | 64.8 | [10 empty] | 64.8 | 64.8
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 16.74 | -16.74 |  |  | 11.42 | 5.32 | [9 empty] | 16.74 | 16.74
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Mapping | 6010077 |  |  |  | 16.74 | -16.74 |  |  | 11.42 | 5.32 | [9 empty] | 16.74 | 16.74
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 950000 |  |  | 5580.45 | 944419.55 |  |  | 3806.94 | 1773.51 | [9 empty] | 5580.45 | 5580.45
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Consulting | PGE1CONSULTING |  |  |  | 1068.75 | -1068.75 |  |  | 1068.75 | [10 empty] | 1068.75 | 1068.75
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Consulting Services - Engineering | 5001230 |  |  |  | 1068.75 | -1068.75 |  |  | 1068.75 | [10 empty] | 1068.75 | 1068.75
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 950000 |  |  | 4511.7 | 945488.3 |  |  | 2738.19 | 1773.51 | [9 empty] | 4511.7 | 4511.7
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Contracts | 5490000 | 950000 |  |  |  | 950000
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 4511.7 | -4511.7 |  |  | 2738.19 | 1773.51 | [9 empty] | 4511.7 | 4511.7
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 1985972.09 | 2004513.59 | -2004513.59 |  | 160.59 | 5743.89 | 12249.96 | 387.06 | 214.1 | 87344.1 | 100217.63 | 100217.63 | 100217.63 | 100217.63 | 217.63 | 217.63 | 18541.5 | 507405.48 | 1497108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 1982130 | 1982130 | -1982130 | [6 empty] | 87130 | 100000 | 100000 | 100000 | 100000 |  |  |  | 487130 | 1495000
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 1982130 | 1982130 | -1982130 | [6 empty] | 87130 | 100000 | 100000 | 100000 | 100000 |  |  |  | 487130 | 1495000
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1982130 | 1982130 | -1982130 | [6 empty] | 87130 | 100000 | 100000 | 100000 | 100000 |  |  |  | 487130 | 1495000
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Employee Related | PGE1EMPLREL |  |  |  | 387.06 | -387.06 |  |  |  |  | 387.06 | [8 empty] | 387.06 | 387.06
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 327.44 | -327.44 |  |  |  |  | 327.44 | [8 empty] | 327.44 | 327.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Lodging | 5091114 |  |  |  | 327.44 | -327.44 |  |  |  |  | 327.44 | [8 empty] | 327.44 | 327.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Meals | PGE1MEALS-EXP |  |  |  | 59.62 | -59.62 |  |  |  |  | 59.62 | [8 empty] | 59.62 | 59.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Meals Expense | 5091100 |  |  |  | 59.62 | -59.62 |  |  |  |  | 59.62 | [8 empty] | 59.62 | 59.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  | 3842.09 | 21996.53 | -21996.53 |  | 160.59 | 5743.89 | 12249.96 |  | 214.1 | 214.1 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 18154.44 | 19888.42 | 2108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 3831.8 | -3831.8 |  | 28.19 | 1134.82 | 2668.79 | [9 empty] | 3831.8 | 3831.8
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 3831.8 | -3831.8 |  | 28.19 | 1134.82 | 2668.79 | [9 empty] | 3831.8 | 3831.8
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 9389.33 | -9389.33 |  | 90.49 | 3056.6 | 6242.24 | [9 empty] | 9389.33 | 9389.33
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 8407.22 | -8407.22 |  | 82.2 | 2752.05 | 5572.97 | [9 empty] | 8407.22 | 8407.22
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 2095.94 | -2095.94 |  | 15.42 | 620.73 | 1459.79 | [9 empty] | 2095.94 | 2095.94
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 476.93 | -476.93 |  | 25.95 | 430.39 | 20.59 | [9 empty] | 476.93 | 476.93
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 3179.67 | -3179.67 |  |  | 640.34 | 2539.33 | [9 empty] | 3179.67 | 3179.67
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 431.64 | -431.64 |  | 23.49 | 389.51 | 18.64 | [9 empty] | 431.64 | 431.64
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 1904.38 | -1904.38 |  |  | 383.52 | 1520.86 | [9 empty] | 1904.38 | 1904.38
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 318.66 | -318.66 |  | 17.34 | 287.56 | 13.76 | [9 empty] | 318.66 | 318.66
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 982.11 | -982.11 |  | 8.29 | 304.55 | 669.27 | [9 empty] | 982.11 | 982.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 626.53 | -626.53 |  | 5.29 | 194.29 | 426.95 | [9 empty] | 626.53 | 626.53
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 355.58 | -355.58 |  | 3 | 110.26 | 242.32 | [9 empty] | 355.58 | 355.58
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 4758.26 | -4758.26 |  | 41.22 | 1514.41 | 3202.63 | [9 empty] | 4758.26 | 4758.26
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 3524.97 | -3524.97 |  | 30.81 | 1131.98 | 2362.18 | [9 empty] | 3524.97 | 3524.97
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 1233.29 | -1233.29 |  | 10.41 | 382.43 | 840.45 | [9 empty] | 1233.29 | 1233.29
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  | 3842.09 | 4017.14 | -4017.14 |  | 0.69 | 38.06 | 136.3 |  | 214.1 | 214.1 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 175.05 | 1909.03 | 2108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  | 3842.09 | 3889.42 | -3889.42 |  | 0.19 | 10.29 | 36.85 |  | 214.1 | 214.1 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 217.63 | 47.33 | 1781.31 | 2108.11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 127.72 | -127.72 |  | 0.5 | 27.77 | 99.45 | [9 empty] | 127.72 | 127.72
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 950000 |  | 5905000 | 5931846.89 | -4981846.89 |  | 330.92 | 10083.29 | 14978.83 | 1453.85 | [8 empty] | 26846.89 | 26846.89 | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 950000 |  | 5905000 | 5931846.89 | -4981846.89 |  | 330.92 | 10083.29 | 14978.83 | 1453.85 | [8 empty] | 26846.89 | 26846.89 | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 8438.38 | -8438.38 |  | 111.38 | 2354.39 | 4912.6 | 1060.01 | [8 empty] | 8438.38 | 8438.38
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 8438.38 | -8438.38 |  | 111.38 | 2354.39 | 4912.6 | 1060.01 | [8 empty] | 8438.38 | 8438.38
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 8438.38 | -8438.38 |  | 111.38 | 2354.39 | 4912.6 | 1060.01 | [8 empty] | 8438.38 | 8438.38
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 8422.62 | -8422.62 |  | 111.38 | 2343.86 | 4907.37 | 1060.01 | [8 empty] | 8422.62 | 8422.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 610.37 | -610.37 |  | 76.56 | 533.81 | [10 empty] | 610.37 | 610.37
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 69.64 | -69.64 |  | 34.82 | 34.82 | [10 empty] | 69.64 | 69.64
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 5994 | -5994 |  |  | 1522.8 | 3499.2 | 972 | [8 empty] | 5994 | 5994
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Administrative Services - OT | 6603150 |  |  |  | 1716.21 | -1716.21 |  |  | 220.03 | 1408.17 | 88.01 | [8 empty] | 1716.21 | 1716.21
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Rights - Misc | 6603227 |  |  |  | 32.4 | -32.4 |  |  | 32.4 | [10 empty] | 32.4 | 32.4
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 15.76 | -15.76 |  |  | 10.53 | 5.23 | [9 empty] | 15.76 | 15.76
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Mapping | 6010077 |  |  |  | 15.76 | -15.76 |  |  | 10.53 | 5.23 | [9 empty] | 15.76 | 15.76
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 950000 |  |  | 5255.52 | 944744.48 |  |  | 3510.58 | 1744.94 | [9 empty] | 5255.52 | 5255.52
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Consulting | PGE1CONSULTING |  |  |  | 261.25 | -261.25 |  |  | 261.25 | [10 empty] | 261.25 | 261.25
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Consulting Services - Engineering | 5001230 |  |  |  | 261.25 | -261.25 |  |  | 261.25 | [10 empty] | 261.25 | 261.25
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 950000 |  |  | 4994.27 | 945005.73 |  |  | 3249.33 | 1744.94 | [9 empty] | 4994.27 | 4994.27
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Contracts | 5490000 | 950000 |  |  |  | 950000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 4994.27 | -4994.27 |  |  | 3249.33 | 1744.94 | [9 empty] | 4994.27 | 4994.27
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 5905000 | 5918152.99 | -5918152.99 |  | 219.54 | 4218.32 | 8321.29 | 393.84 | [8 empty] | 13152.99 | 13152.99 | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 5905000 | 5905000 | -5905000 |  |  |  | 21.62 | -21.62 | [10 empty] | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 5905000 | 5905000 | -5905000 |  |  |  | 21.62 | -21.62 | [10 empty] | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 5905000 | 5905000 | -5905000 | [15 empty] | 5905000
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Expenses | 5591000 | [8 empty] | 21.62 | -21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Employee Related | PGE1EMPLREL |  |  |  | 415.46 | -415.46 |  |  |  |  | 415.46 | [8 empty] | 415.46 | 415.46
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Travel / Lodging | PGE1TRVL-LODGE |  |  |  | 348.58 | -348.58 |  |  |  |  | 348.58 | [8 empty] | 348.58 | 348.58
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Lodging | 5091114 |  |  |  | 348.58 | -348.58 |  |  |  |  | 348.58 | [8 empty] | 348.58 | 348.58
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Meals | PGE1MEALS-EXP |  |  |  | 66.88 | -66.88 |  |  |  |  | 66.88 | [8 empty] | 66.88 | 66.88
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Meals Expense | 5091100 |  |  |  | 66.88 | -66.88 |  |  |  |  | 66.88 | [8 empty] | 66.88 | 66.88
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 12737.53 | -12737.53 |  | 219.54 | 4218.32 | 8299.67 | [9 empty] | 12737.53 | 12737.53
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 2716.72 | -2716.72 |  | 41.01 | 866.89 | 1808.82 | [9 empty] | 2716.72 | 2716.72
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 2716.72 | -2716.72 |  | 41.01 | 866.89 | 1808.82 | [9 empty] | 2716.72 | 2716.72
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 6536.85 | -6536.85 |  | 120.38 | 2197.31 | 4219.16 | [9 empty] | 6536.85 | 6536.85
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 5846.49 | -5846.49 |  | 108.88 | 1971.5 | 3766.11 | [9 empty] | 5846.49 | 5846.49
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 1485.99 | -1485.99 |  | 22.43 | 474.17 | 989.39 | [9 empty] | 1485.99 | 1485.99
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 212.25 | -212.25 |  | 25.95 | 184.53 | 1.77 | [9 empty] | 212.25 | 212.25
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 2385.56 | -2385.56 |  | 12.3 | 639.49 | 1733.77 | [9 empty] | 2385.56 | 2385.56
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 192.09 | -192.09 |  | 23.49 | 167 | 1.6 | [9 empty] | 192.09 | 192.09
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 1428.78 | -1428.78 |  | 7.37 | 383.01 | 1038.4 | [9 empty] | 1428.78 | 1428.78
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 141.82 | -141.82 |  | 17.34 | 123.3 | 1.18 | [9 empty] | 141.82 | 141.82
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 690.36 | -690.36 |  | 11.5 | 225.81 | 453.05 | [9 empty] | 690.36 | 690.36
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 440.41 | -440.41 |  | 7.34 | 144.06 | 289.01 | [9 empty] | 440.41 | 440.41
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | IT Device OH | 6010113 |  |  |  | 249.95 | -249.95 |  | 4.16 | 81.75 | 164.04 | [9 empty] | 249.95 | 249.95
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 3348 | -3348 |  | 57.19 | 1122.92 | 2167.89 | [9 empty] | 3348 | 3348
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Benefits OH | 6010120 |  |  |  | 2481.07 | -2481.07 |  | 42.75 | 839.35 | 1598.97 | [9 empty] | 2481.07 | 2481.07
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 866.93 | -866.93 |  | 14.44 | 283.57 | 568.92 | [9 empty] | 866.93 | 866.93
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 135.96 | -135.96 |  | 0.96 | 31.2 | 103.8 | [9 empty] | 135.96 | 135.96
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 36.77 | -36.77 |  | 0.26 | 8.44 | 28.07 | [9 empty] | 36.77 | 36.77
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 99.19 | -99.19 |  | 0.7 | 22.76 | 75.73 | [9 empty] | 99.19 | 99.19
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 400000 |  | 15641437.46 | 15647017.86 | -15247017.86 |  |  | 2617.64 | 2962.76 |  | 36664.02 | 273.52 | 276.38 | 276.38 | 350367.38 | 276.38 | 276.38 | 276.38 | 5580.4 | 394267.22 | 15252750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 400000 |  | 15641437.46 | 15647017.86 | -15247017.86 |  |  | 2617.64 | 2962.76 |  | 36664.02 | 273.52 | 276.38 | 276.38 | 350367.38 | 276.38 | 276.38 | 276.38 | 5580.4 | 394267.22 | 15252750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 1972.08 | -1972.08 |  |  | 870.48 | 1101.6 | [9 empty] | 1972.08 | 1972.08
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 1972.08 | -1972.08 |  |  | 870.48 | 1101.6 | [9 empty] | 1972.08 | 1972.08
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 1972.08 | -1972.08 |  |  | 870.48 | 1101.6 | [9 empty] | 1972.08 | 1972.08
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 1966.05 | -1966.05 |  |  | 864.45 | 1101.6 | [9 empty] | 1966.05 | 1966.05
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  | 670.05 | [10 empty] | 670.05 | 670.05
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 1296 | -1296 |  |  | 194.4 | 1101.6 | [9 empty] | 1296 | 1296
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 6.03 | -6.03 |  |  | 6.03 | [10 empty] | 6.03 | 6.03
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Mapping | 6010077 |  |  |  | 6.03 | -6.03 |  |  | 6.03 | [10 empty] | 6.03 | 6.03
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Contract Total | PGE1CONTRACT | 400000 |  | 36500 | 36500 | 363500 | [5 empty] | 36500 | [8 empty] | 36500
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 400000 |  | 36500 | 36500 | 363500 | [5 empty] | 36500 | [8 empty] | 36500
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Contracts | 5490000 | 400000 |  |  |  | 400000
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  | 36500 | 36500 | -36500 | [5 empty] | 36500 | [8 empty] | 36500
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 15604937.46 | 15608545.78 | -15608545.78 |  |  | 1747.16 | 1861.16 |  | 164.02 | 273.52 | 276.38 | 276.38 | 350367.38 | 276.38 | 276.38 | 276.38 | 3608.32 | 355795.14 | 15252750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 15600091 | 15600091 | -15600091 | [9 empty] | 350091 |  |  |  |  | 350091 | 15250000
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 15600091 | 15600091 | -15600091 | [9 empty] | 350091 |  |  |  |  | 350091 | 15250000
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 15600091 | 15600091 | -15600091 | [9 empty] | 350091 |  |  |  |  | 350091 | 15250000
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  | 4846.46 | 8454.78 | -8454.78 |  |  | 1747.16 | 1861.16 |  | 164.02 | 273.52 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 3608.32 | 5704.14 | 2750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 726.12 | -726.12 |  |  | 320.51 | 405.61 | [9 empty] | 726.12 | 726.12
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 726.12 | -726.12 |  |  | 320.51 | 405.61 | [9 empty] | 726.12 | 726.12
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 1911.71 | -1911.71 |  |  | 965.98 | 945.73 | [9 empty] | 1911.71 | 1911.71
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 1719.04 | -1719.04 |  |  | 874.88 | 844.16 | [9 empty] | 1719.04 | 1719.04
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 397.17 | -397.17 |  |  | 175.31 | 221.86 | [9 empty] | 397.17 | 397.17
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 229.19 | -229.19 |  |  | 229.19 | [10 empty] | 229.19 | 229.19
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 457.88 | -457.88 |  |  | 68.68 | 389.2 | [9 empty] | 457.88 | 457.88
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 207.42 | -207.42 |  |  | 207.42 | [10 empty] | 207.42 | 207.42
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 274.24 | -274.24 |  |  | 41.14 | 233.1 | [9 empty] | 274.24 | 274.24
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 153.14 | -153.14 |  |  | 153.14 | [10 empty] | 153.14 | 153.14
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 192.67 | -192.67 |  |  | 91.1 | 101.57 | [9 empty] | 192.67 | 192.67
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 122.91 | -122.91 |  |  | 58.12 | 64.79 | [9 empty] | 122.91 | 122.91
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | IT Device OH | 6010113 |  |  |  | 69.76 | -69.76 |  |  | 32.98 | 36.78 | [9 empty] | 69.76 | 69.76
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 939.11 | -939.11 |  |  | 453.06 | 486.05 | [9 empty] | 939.11 | 939.11
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Benefits OH | 6010120 |  |  |  | 697.15 | -697.15 |  |  | 338.65 | 358.5 | [9 empty] | 697.15 | 697.15
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 241.96 | -241.96 |  |  | 114.41 | 127.55 | [9 empty] | 241.96 | 241.96
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  | 4846.46 | 4877.84 | -4877.84 |  |  | 7.61 | 23.77 |  | 164.02 | 273.52 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 31.38 | 2127.2 | 2750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  | 4846.46 | 4854.95 | -4854.95 |  |  | 2.06 | 6.43 |  | 164.02 | 273.52 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 276.38 | 8.49 | 2104.31 | 2750.64
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 22.89 | -22.89 |  |  | 5.55 | 17.34 | [9 empty] | 22.89 | 22.89
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 400000 |  | 6299466.04 | 6301678.68 | -5901678.68 |  |  | 2094.12 | 118.52 |  | 36653.66 | 263.16 | 265.81 | 265.81 | 353575.81 | 265.81 | 265.81 | 265.81 | 2212.64 | 394034.32 | 5907644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 400000 |  | 6299466.04 | 6301678.68 | -5901678.68 |  |  | 2094.12 | 118.52 |  | 36653.66 | 263.16 | 265.81 | 265.81 | 353575.81 | 265.81 | 265.81 | 265.81 | 2212.64 | 394034.32 | 5907644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 676.4 | -676.4 |  |  | 676.08 | 0.32 | [9 empty] | 676.4 | 676.4
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 676.4 | -676.4 |  |  | 676.08 | 0.32 | [9 empty] | 676.4 | 676.4
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 676.4 | -676.4 |  |  | 676.08 | 0.32 | [9 empty] | 676.4 | 676.4
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 670.05 | -670.05 |  |  | 670.05 | [10 empty] | 670.05 | 670.05
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Construction | 6603001 |  |  |  | 670.05 | -670.05 |  |  | 670.05 | [10 empty] | 670.05 | 670.05
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 6.35 | -6.35 |  |  | 6.03 | 0.32 | [9 empty] | 6.35 | 6.35
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Mapping | 6010077 |  |  |  | 6.35 | -6.35 |  |  | 6.03 | 0.32 | [9 empty] | 6.35 | 6.35
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Contract Total | PGE1CONTRACT | 400000 |  | 36500 | 36605.06 | 363394.94 |  |  |  | 105.06 |  | 36500 | [7 empty] | 105.06 | 36605.06
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 400000 |  | 36500 | 36605.06 | 363394.94 |  |  |  | 105.06 |  | 36500 | [7 empty] | 105.06 | 36605.06
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Contracts | 5490000 | 400000 |  |  |  | 400000
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  | 36500 | 36500 | -36500 | [5 empty] | 36500 | [8 empty] | 36500
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Environmental Contract | 5490015 |  |  |  | 105.06 | -105.06 |  |  |  | 105.06 | [9 empty] | 105.06 | 105.06
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 6262966.04 | 6264397.22 | -6264397.22 |  |  | 1418.04 | 13.14 |  | 153.66 | 263.16 | 265.81 | 265.81 | 353575.81 | 265.81 | 265.81 | 265.81 | 1431.18 | 356752.86 | 5907644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 6258310 | 6258310 | -6258310 | [9 empty] | 353310 |  |  |  |  | 353310 | 5905000
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 6258310 | 6258310 | -6258310 | [9 empty] | 353310 |  |  |  |  | 353310 | 5905000
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 6258310 | 6258310 | -6258310 | [9 empty] | 353310 |  |  |  |  | 353310 | 5905000
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  | 4656.04 | 6087.22 | -6087.22 |  |  | 1418.04 | 13.14 |  | 153.66 | 263.16 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 1431.18 | 3442.86 | 2644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 249.05 | -249.05 |  |  | 248.93 | 0.12 | [9 empty] | 249.05 | 249.05
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 249.05 | -249.05 |  |  | 248.93 | 0.12 | [9 empty] | 249.05 | 249.05
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 799.47 | -799.47 |  |  | 799.09 | 0.38 | [9 empty] | 799.47 | 799.47
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 726.25 | -726.25 |  |  | 725.91 | 0.34 | [9 empty] | 726.25 | 726.25
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 136.22 | -136.22 |  |  | 136.16 | 0.06 | [9 empty] | 136.22 | 136.22
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 229.3 | -229.3 |  |  | 229.19 | 0.11 | [9 empty] | 229.3 | 229.3
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 207.52 | -207.52 |  |  | 207.42 | 0.1 | [9 empty] | 207.52 | 207.52
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 153.21 | -153.21 |  |  | 153.14 | 0.07 | [9 empty] | 153.21 | 153.21
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 73.22 | -73.22 |  |  | 73.18 | 0.04 | [9 empty] | 73.22 | 73.22
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 46.71 | -46.71 |  |  | 46.69 | 0.02 | [9 empty] | 46.71 | 46.71
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | IT Device OH | 6010113 |  |  |  | 26.51 | -26.51 |  |  | 26.49 | 0.02 | [9 empty] | 26.51 | 26.51
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 364.11 | -364.11 |  |  | 363.94 | 0.17 | [9 empty] | 364.11 | 364.11
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Benefits OH | 6010120 |  |  |  | 272.16 | -272.16 |  |  | 272.03 | 0.13 | [9 empty] | 272.16 | 272.16
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 91.95 | -91.95 |  |  | 91.91 | 0.04 | [9 empty] | 91.95 | 91.95
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  | 4656.04 | 4674.59 | -4674.59 |  |  | 6.08 | 12.47 |  | 153.66 | 263.16 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 18.55 | 2030.23 | 2644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  | 4656.04 | 4661.05 | -4661.05 |  |  | 1.64 | 3.37 |  | 153.66 | 263.16 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 265.81 | 5.01 | 2016.69 | 2644.36
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 13.54 | -13.54 |  |  | 4.44 | 9.1 | [9 empty] | 13.54 | 13.54
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 100000 |  | 4824003 | 4836843.17 | -4736843.17 |  |  | 1996.34 | 10739.37 | 104.46 |  |  | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  | 12840.17 | 4836843.17
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 100000 |  | 4824003 | 4836843.17 | -4736843.17 |  |  | 1996.34 | 10739.37 | 104.46 |  |  | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  | 12840.17 | 4836843.17
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 4253.48 | -4253.48 |  |  | 644.52 | 3504.5 | 104.46 | [8 empty] | 4253.48 | 4253.48
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 4253.48 | -4253.48 |  |  | 644.52 | 3504.5 | 104.46 | [8 empty] | 4253.48 | 4253.48
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 4253.48 | -4253.48 |  |  | 644.52 | 3504.5 | 104.46 | [8 empty] | 4253.48 | 4253.48
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 4252.98 | -4252.98 |  |  | 644.52 | 3504 | 104.46 | [8 empty] | 4252.98 | 4252.98
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Construction Overtime Services | 6603021 |  |  |  | 55.44 | -55.44 |  |  |  | 55.44 | [9 empty] | 55.44 | 55.44
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Engineering/Mapping | 6603022 |  |  |  | 2449.92 | -2449.92 |  |  |  | 2449.92 | [9 empty] | 2449.92 | 2449.92
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 243.74 | -243.74 |  |  |  | 139.28 | 104.46 | [8 empty] | 243.74 | 243.74
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Engineering/Mapping Services Overtime | 6603106 |  |  |  | 1503.88 | -1503.88 |  |  | 644.52 | 859.36 | [9 empty] | 1503.88 | 1503.88
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH |  |  |  | 0.5 | -0.5 |  |  |  | 0.5 | [9 empty] | 0.5 | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Mapping | 6010077 |  |  |  | 0.5 | -0.5 |  |  |  | 0.5 | [9 empty] | 0.5 | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Contract Total | PGE1CONTRACT | 100000 |  |  |  | 100000
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 100000 |  |  |  | 100000
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Contracts | 5490000 | 100000 |  |  |  | 100000
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 4824003 | 4832589.69 | -4832589.69 |  |  | 1351.82 | 7234.87 |  |  |  | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  | 8586.69 | 4832589.69
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 4824003 | 4824003 | -4824003 | [7 empty] | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  |  | 4824003
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 4824003 | 4824003 | -4824003 | [7 empty] | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  |  | 4824003
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 4824003 | 4824003 | -4824003 | [7 empty] | 824003 | 1000000 | 1000000 | 1000000 | 1000000 |  |  | 4824003
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 8586.69 | -8586.69 |  |  | 1351.82 | 7234.87 | [9 empty] | 8586.69 | 8586.69
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 1527.66 | -1527.66 |  |  | 237.31 | 1290.35 | [9 empty] | 1527.66 | 1527.66
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 1527.66 | -1527.66 |  |  | 237.31 | 1290.35 | [9 empty] | 1527.66 | 1527.66
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 4858.88 | -4858.88 |  |  | 761.78 | 4097.1 | [9 empty] | 4858.88 | 4858.88
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 4411.98 | -4411.98 |  |  | 692.02 | 3719.96 | [9 empty] | 4411.98 | 4411.98
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 835.62 | -835.62 |  |  | 129.81 | 705.81 | [9 empty] | 835.62 | 835.62
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Indirect Labor - Electric | 6010106 |  |  |  | 1359.3 | -1359.3 |  |  | 218.49 | 1140.81 | [9 empty] | 1359.3 | 1359.3
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 49.21 | -49.21 |  |  |  | 49.21 | [9 empty] | 49.21 | 49.21
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 1230.18 | -1230.18 |  |  | 197.74 | 1032.44 | [9 empty] | 1230.18 | 1230.18
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 29.47 | -29.47 |  |  |  | 29.47 | [9 empty] | 29.47 | 29.47
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Fleet OH - Elec | 6010125 |  |  |  | 908.2 | -908.2 |  |  | 145.98 | 762.22 | [9 empty] | 908.2 | 908.2
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 446.9 | -446.9 |  |  | 69.76 | 377.14 | [9 empty] | 446.9 | 446.9
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 285.1 | -285.1 |  |  | 44.5 | 240.6 | [9 empty] | 285.1 | 285.1
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | IT Device OH | 6010113 |  |  |  | 161.8 | -161.8 |  |  | 25.26 | 136.54 | [9 empty] | 161.8 | 161.8
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 2151.6 | -2151.6 |  |  | 346.93 | 1804.67 | [9 empty] | 2151.6 | 2151.6
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Benefits OH | 6010120 |  |  |  | 1590.39 | -1590.39 |  |  | 259.32 | 1331.07 | [9 empty] | 1590.39 | 1590.39
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 561.21 | -561.21 |  |  | 87.61 | 473.6 | [9 empty] | 561.21 | 561.21
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 48.55 | -48.55 |  |  | 5.8 | 42.75 | [9 empty] | 48.55 | 48.55
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 13.13 | -13.13 |  |  | 1.57 | 11.56 | [9 empty] | 13.13 | 13.13
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 35.42 | -35.42 |  |  | 4.23 | 31.19 | [9 empty] | 35.42 | 35.42
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 150000 |  | 515568.48 | 516646.28 | -366646.28 |  |  |  | 25647.8 | -24570 | 67 | 250067 | 250068.02 | 14343.02 | 68.02 | 68.02 | 68.02 | 68.02 | 1077.8 | 515894.92 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 515568.48 | 516646.28 | -366646.28 |  |  |  | 25647.8 | -24570 | 67 | 250067 | 250068.02 | 14343.02 | 68.02 | 68.02 | 68.02 | 68.02 | 1077.8 | 515894.92 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 336.09 | -336.09 |  |  |  | 336.09 | [9 empty] | 336.09 | 336.09
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 336.09 | -336.09 |  |  |  | 336.09 | [9 empty] | 336.09 | 336.09
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 336.09 | -336.09 |  |  |  | 336.09 | [9 empty] | 336.09 | 336.09
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 336.09 | -336.09 |  |  |  | 336.09 | [9 empty] | 336.09 | 336.09
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 69.64 | -69.64 |  |  |  | 69.64 | [9 empty] | 69.64 | 69.64
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Electric Estimating | 6603466 |  |  |  | 266.45 | -266.45 |  |  |  | 266.45 | [9 empty] | 266.45 | 266.45
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Contract Total | PGE1CONTRACT | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Contracts | 5490000 | 150000 |  |  |  | 150000
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | [8 empty] | 24570 | -24570
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 515568.48 | 516310.19 | -516310.19 |  |  |  | 741.71 |  | 67 | 250067 | 250068.02 | 14343.02 | 68.02 | 68.02 | 68.02 | 68.02 | 741.71 | 515558.83 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  | 514275 | 514275 | -514275 | [6 empty] | 250000 | 250000 | 14275 | [5 empty] | 514275
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 514275 | 514275 | -514275 | [6 empty] | 250000 | 250000 | 14275 | [5 empty] | 514275
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 514275 | 514275 | -514275 | [6 empty] | 250000 | 250000 | 14275 | [5 empty] | 514275
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  | 1293.48 | 2035.19 | -2035.19 |  |  |  | 741.71 |  | 67 | 67 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 741.71 | 1283.83 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 123.75 | -123.75 |  |  |  | 123.75 | [9 empty] | 123.75 | 123.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 123.75 | -123.75 |  |  |  | 123.75 | [9 empty] | 123.75 | 123.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 374.73 | -374.73 |  |  |  | 374.73 | [9 empty] | 374.73 | 374.73
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 339.46 | -339.46 |  |  |  | 339.46 | [9 empty] | 339.46 | 339.46
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 67.69 | -67.69 |  |  |  | 67.69 | [9 empty] | 67.69 | 67.69
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 90.33 | -90.33 |  |  |  | 90.33 | [9 empty] | 90.33 | 90.33
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 24.6 | -24.6 |  |  |  | 24.6 | [9 empty] | 24.6 | 24.6
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 81.75 | -81.75 |  |  |  | 81.75 | [9 empty] | 81.75 | 81.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 14.74 | -14.74 |  |  |  | 14.74 | [9 empty] | 14.74 | 14.74
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Fleet OH - Elec | 6010125 |  |  |  | 60.35 | -60.35 |  |  |  | 60.35 | [9 empty] | 60.35 | 60.35
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 35.27 | -35.27 |  |  |  | 35.27 | [9 empty] | 35.27 | 35.27
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 22.49 | -22.49 |  |  |  | 22.49 | [9 empty] | 22.49 | 22.49
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | IT Device OH | 6010113 |  |  |  | 12.78 | -12.78 |  |  |  | 12.78 | [9 empty] | 12.78 | 12.78
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 168.75 | -168.75 |  |  |  | 168.75 | [9 empty] | 168.75 | 168.75
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Benefits OH | 6010120 |  |  |  | 124.46 | -124.46 |  |  |  | 124.46 | [9 empty] | 124.46 | 124.46
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 44.29 | -44.29 |  |  |  | 44.29 | [9 empty] | 44.29 | 44.29
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  | 1293.48 | 1367.96 | -1367.96 |  |  |  | 74.48 |  | 67 | 67 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 74.48 | 616.6 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  | 1293.48 | 1313.62 | -1313.62 |  |  |  | 20.14 |  | 67 | 67 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 68.02 | 20.14 | 562.26 | 751.36
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 54.34 | -54.34 |  |  |  | 54.34 | [9 empty] | 54.34 | 54.34
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 150000 |  | 2861404 | 2862302.31 | -2712302.31 |  |  | 261.78 | 25206.53 | -24570 | 1758 |  |  |  | 400000 | 89646 |  |  | 898.31 | 492302.31 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 2861404 | 2862302.31 | -2712302.31 |  |  | 261.78 | 25206.53 | -24570 | 1758 |  |  |  | 400000 | 89646 |  |  | 898.31 | 492302.31 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 307.8 | -307.8 |  |  | 97.2 | 210.6 | [9 empty] | 307.8 | 307.8
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 307.8 | -307.8 |  |  | 97.2 | 210.6 | [9 empty] | 307.8 | 307.8
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 307.8 | -307.8 |  |  | 97.2 | 210.6 | [9 empty] | 307.8 | 307.8
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 307.8 | -307.8 |  |  | 97.2 | 210.6 | [9 empty] | 307.8 | 307.8
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Acquisition - Misc | 6603004 |  |  |  | 194.4 | -194.4 |  |  | 97.2 | 97.2 | [9 empty] | 194.4 | 194.4
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 113.4 | -113.4 |  |  |  | 113.4 | [9 empty] | 113.4 | 113.4
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Mapping | 6010077
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Contract Total | PGE1CONTRACT | 150000 |  | 1758 | 1758 | 148242 |  |  |  | 24570 | -24570 | 1758 | [8 empty] | 1758
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 150000 |  | 1758 | 1758 | 148242 |  |  |  | 24570 | -24570 | 1758 | [8 empty] | 1758
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Contracts | 5490000 | 150000 |  |  |  | 150000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  | 1758 | 1758 | -1758 |  |  |  | 24570 | -24570 | 1758 | [8 empty] | 1758
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 2859646 | 2860236.51 | -2860236.51 |  |  | 164.58 | 425.93 | [5 empty] | 400000 | 89646 |  |  | 590.51 | 490236.51 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 2859646 | 2859646 | -2859646 | [9 empty] | 400000 | 89646 |  |  |  | 489646 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 2859646 | 2859646 | -2859646 | [9 empty] | 400000 | 89646 |  |  |  | 489646 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2859646 | 2859646 | -2859646 | [9 empty] | 400000 | 89646 |  |  |  | 489646 | 2370000
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 590.51 | -590.51 |  |  | 164.58 | 425.93 | [9 empty] | 590.51 | 590.51
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 113.33 | -113.33 |  |  | 35.79 | 77.54 | [9 empty] | 113.33 | 113.33
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 113.33 | -113.33 |  |  | 35.79 | 77.54 | [9 empty] | 113.33 | 113.33
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 264.24 | -264.24 |  |  | 83.46 | 180.78 | [9 empty] | 264.24 | 264.24
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 235.86 | -235.86 |  |  | 74.49 | 161.37 | [9 empty] | 235.86 | 235.86
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 61.99 | -61.99 |  |  | 19.58 | 42.41 | [9 empty] | 61.99 | 61.99
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Indirect Labor - Electric | 6010106
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 108.74 | -108.74 |  |  | 34.34 | 74.4 | [9 empty] | 108.74 | 108.74
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Operation Mgmt & Support - Electric | 6010114
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 65.13 | -65.13 |  |  | 20.57 | 44.56 | [9 empty] | 65.13 | 65.13
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Fleet OH - Elec | 6010125
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 28.38 | -28.38 |  |  | 8.97 | 19.41 | [9 empty] | 28.38 | 28.38
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 18.1 | -18.1 |  |  | 5.72 | 12.38 | [9 empty] | 18.1 | 18.1
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | IT Device OH | 6010113 |  |  |  | 10.28 | -10.28 |  |  | 3.25 | 7.03 | [9 empty] | 10.28 | 10.28
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 137.47 | -137.47 |  |  | 44.57 | 92.9 | [9 empty] | 137.47 | 137.47
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Benefits OH | 6010120 |  |  |  | 101.83 | -101.83 |  |  | 33.31 | 68.52 | [9 empty] | 101.83 | 101.83
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 35.64 | -35.64 |  |  | 11.26 | 24.38 | [9 empty] | 35.64 | 35.64
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 75.47 | -75.47 |  |  | 0.76 | 74.71 | [9 empty] | 75.47 | 75.47
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 20.41 | -20.41 |  |  | 0.21 | 20.2 | [9 empty] | 20.41 | 20.41
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 55.06 | -55.06 |  |  | 0.55 | 54.51 | [9 empty] | 55.06 | 55.06
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 200000 |  | 6048712 | 6049567 | -5849567 |  |  | 261.78 | 25163.22 | -24570 | 4066 |  |  |  |  | 400000 | 89646 |  | 855 | 494567 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 200000 |  | 6048712 | 6049567 | -5849567 |  |  | 261.78 | 25163.22 | -24570 | 4066 |  |  |  |  | 400000 | 89646 |  | 855 | 494567 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  |  |  | 291.6 | -291.6 |  |  | 97.2 | 194.4 | [9 empty] | 291.6 | 291.6
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Activity Types | PGE1ACTVTYPES |  |  |  | 291.6 | -291.6 |  |  | 97.2 | 194.4 | [9 empty] | 291.6 | 291.6
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 291.6 | -291.6 |  |  | 97.2 | 194.4 | [9 empty] | 291.6 | 291.6
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 291.6 | -291.6 |  |  | 97.2 | 194.4 | [9 empty] | 291.6 | 291.6
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Acquisition - Misc | 6603004 |  |  |  | 194.4 | -194.4 |  |  | 97.2 | 97.2 | [9 empty] | 194.4 | 194.4
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 97.2 | -97.2 |  |  |  | 97.2 | [9 empty] | 97.2 | 97.2
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Mapping | 6010077
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Contract Total | PGE1CONTRACT | 200000 |  | 4066 | 4066 | 195934 |  |  |  | 24570 | -24570 | 4066 | [8 empty] | 4066
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 200000 |  | 4066 | 4066 | 195934 |  |  |  | 24570 | -24570 | 4066 | [8 empty] | 4066
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Contracts | 5490000 | 200000 |  |  |  | 200000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  |  | 4066 | 4066 | -4066 |  |  |  | 24570 | -24570 | 4066 | [8 empty] | 4066
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 6044646 | 6045209.4 | -6045209.4 |  |  | 164.58 | 398.82 | [6 empty] | 400000 | 89646 |  | 563.4 | 490209.4 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 6044646 | 6044646 | -6044646 | [10 empty] | 400000 | 89646 |  |  | 489646 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 6044646 | 6044646 | -6044646 | [10 empty] | 400000 | 89646 |  |  | 489646 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 6044646 | 6044646 | -6044646 | [10 empty] | 400000 | 89646 |  |  | 489646 | 5555000
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Order Overheads | PGE1OVERHEAD |  |  |  | 563.4 | -563.4 |  |  | 164.58 | 398.82 | [9 empty] | 563.4 | 563.4
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Capitalized A&G | PGE1CAPAG |  |  |  | 107.37 | -107.37 |  |  | 35.79 | 71.58 | [9 empty] | 107.37 | 107.37
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Capitalized A&G | 6010050 |  |  |  | 107.37 | -107.37 |  |  | 35.79 | 71.58 | [9 empty] | 107.37 | 107.37
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Labor Overheads | PGE1LABOROH |  |  |  | 250.35 | -250.35 |  |  | 83.46 | 166.89 | [9 empty] | 250.35 | 250.35
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 223.46 | -223.46 |  |  | 74.49 | 148.97 | [9 empty] | 223.46 | 223.46
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Paid Time Off | 6010100 |  |  |  | 58.73 | -58.73 |  |  | 19.58 | 39.15 | [9 empty] | 58.73 | 58.73
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Indirect Labor - Electric | 6010106
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Indirect Labor - Environmental Land | 6010108 |  |  |  | 103.02 | -103.02 |  |  | 34.34 | 68.68 | [9 empty] | 103.02 | 103.02
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Operation Mgmt & Support - Electric | 6010114
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 61.71 | -61.71 |  |  | 20.57 | 41.14 | [9 empty] | 61.71 | 61.71
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Fleet OH - Elec | 6010125
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 26.89 | -26.89 |  |  | 8.97 | 17.92 | [9 empty] | 26.89 | 26.89
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Building Service Overhead | 6010112 |  |  |  | 17.15 | -17.15 |  |  | 5.72 | 11.43 | [9 empty] | 17.15 | 17.15
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | IT Device OH | 6010113 |  |  |  | 9.74 | -9.74 |  |  | 3.25 | 6.49 | [9 empty] | 9.74 | 9.74
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Other Overhead | PGE1OTHEROH |  |  |  | 130.33 | -130.33 |  |  | 44.57 | 85.76 | [9 empty] | 130.33 | 130.33
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Benefits OH | 6010120 |  |  |  | 96.57 | -96.57 |  |  | 33.31 | 63.26 | [9 empty] | 96.57 | 96.57
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Payroll Taxes OH | 6010121 |  |  |  | 33.76 | -33.76 |  |  | 11.26 | 22.5 | [9 empty] | 33.76 | 33.76
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 75.35 | -75.35 |  |  | 0.76 | 74.59 | [9 empty] | 75.35 | 75.35
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | AFUDC-Borrowed | 5590030 |  |  |  | 20.38 | -20.38 |  |  | 0.21 | 20.17 | [9 empty] | 20.38 | 20.38
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | AFUDC-Equity | 5590031 |  |  |  | 54.97 | -54.97 |  |  | 0.55 | 54.42 | [9 empty] | 54.97 | 54.97
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 150000 |  | 2660867 | 2661031.72 | -2511031.72 |  |  |  | 24734.72 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 | 164.72 | 2661031.72
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 2660867 | 2661031.72 | -2511031.72 |  |  |  | 24734.72 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 | 164.72 | 2661031.72
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 34.82 | -34.82 |  |  |  | 34.82 | [9 empty] | 34.82 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 34.82 | -34.82 |  |  |  | 34.82 | [9 empty] | 34.82 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 34.82 | -34.82 |  |  |  | 34.82 | [9 empty] | 34.82 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 34.82 | -34.82 |  |  |  | 34.82 | [9 empty] | 34.82 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  |  |  | 34.82 | -34.82 |  |  |  | 34.82 | [9 empty] | 34.82 | 34.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Contract Total | PGE1CONTRACT | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Contracts | 5490000 | 150000 |  |  |  | 150000
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | [8 empty] | 24570 | -24570
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 2660867 | 2660996.9 | -2660996.9 |  |  |  | 129.9 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 | 129.9 | 2660996.9
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  | 2660867 | 2660867 | -2660867 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 |  | 2660867
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 2660867 | 2660867 | -2660867 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 |  | 2660867
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2660867 | 2660867 | -2660867 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 160367 | 500 |  | 2660867
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  |  | 129.9 | -129.9 |  |  |  | 129.9 | [9 empty] | 129.9 | 129.9
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 12.82 | -12.82 |  |  |  | 12.82 | [9 empty] | 12.82 | 12.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 12.82 | -12.82 |  |  |  | 12.82 | [9 empty] | 12.82 | 12.82
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 29.89 | -29.89 |  |  |  | 29.89 | [9 empty] | 29.89 | 29.89
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 26.68 | -26.68 |  |  |  | 26.68 | [9 empty] | 26.68 | 26.68
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 7.01 | -7.01 |  |  |  | 7.01 | [9 empty] | 7.01 | 7.01
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 12.3 | -12.3 |  |  |  | 12.3 | [9 empty] | 12.3 | 12.3
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 7.37 | -7.37 |  |  |  | 7.37 | [9 empty] | 7.37 | 7.37
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 3.21 | -3.21 |  |  |  | 3.21 | [9 empty] | 3.21 | 3.21
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 2.05 | -2.05 |  |  |  | 2.05 | [9 empty] | 2.05 | 2.05
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | IT Device OH | 6010113 |  |  |  | 1.16 | -1.16 |  |  |  | 1.16 | [9 empty] | 1.16 | 1.16
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 15.36 | -15.36 |  |  |  | 15.36 | [9 empty] | 15.36 | 15.36
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Benefits OH | 6010120 |  |  |  | 11.33 | -11.33 |  |  |  | 11.33 | [9 empty] | 11.33 | 11.33
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 4.03 | -4.03 |  |  |  | 4.03 | [9 empty] | 4.03 | 4.03
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 71.83 | -71.83 |  |  |  | 71.83 | [9 empty] | 71.83 | 71.83
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  |  | 19.42 | -19.42 |  |  |  | 19.42 | [9 empty] | 19.42 | 19.42
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 52.41 | -52.41 |  |  |  | 52.41 | [9 empty] | 52.41 | 52.41
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 150000 |  | 2846093 | 2847528.47 | -2697528.47 |  |  | 261.78 | 25743.69 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  | 1435.47 | 2847528.47
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 2846093 | 2847528.47 | -2697528.47 |  |  | 261.78 | 25743.69 | -24570 |  | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  | 1435.47 | 2847528.47
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  |  |  | 482.36 | -482.36 |  |  | 97.2 | 385.16 | [9 empty] | 482.36 | 482.36
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Activity Types | PGE1ACTVTYPES |  |  |  | 482.36 | -482.36 |  |  | 97.2 | 385.16 | [9 empty] | 482.36 | 482.36
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  |  |  | 482.36 | -482.36 |  |  | 97.2 | 385.16 | [9 empty] | 482.36 | 482.36
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  |  |  | 482.36 | -482.36 |  |  | 97.2 | 385.16 | [9 empty] | 482.36 | 482.36
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Acquisition - Misc | 6603004 |  |  |  | 194.4 | -194.4 |  |  | 97.2 | 97.2 | [9 empty] | 194.4 | 194.4
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059 |  |  |  | 113.4 | -113.4 |  |  |  | 113.4 | [9 empty] | 113.4 | 113.4
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Electric Estimating Overtime | 6603467 |  |  |  | 174.56 | -174.56 |  |  |  | 174.56 | [9 empty] | 174.56 | 174.56
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Contract Total | PGE1CONTRACT | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 150000 |  |  |  | 150000 |  |  |  | 24570 | -24570
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Contracts | 5490000 | 150000 |  |  |  | 150000
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | [8 empty] | 24570 | -24570
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Order Other Costs | PGE1ORD-OTHER |  |  | 2846093 | 2847046.11 | -2847046.11 |  |  | 164.58 | 788.53 |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  | 953.11 | 2847046.11
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Other Cost Elements | PGE1OTHERCE |  |  | 2846093 | 2846093 | -2846093 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  |  | 2846093
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 2846093 | 2846093 | -2846093 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  |  | 2846093
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2846093 | 2846093 | -2846093 | [6 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 346093 |  |  | 2846093
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Order Overheads | PGE1OVERHEAD |  |  |  | 953.11 | -953.11 |  |  | 164.58 | 788.53 | [9 empty] | 953.11 | 953.11
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Capitalized A&G | PGE1CAPAG |  |  |  | 177.6 | -177.6 |  |  | 35.79 | 141.81 | [9 empty] | 177.6 | 177.6
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Capitalized A&G | 6010050 |  |  |  | 177.6 | -177.6 |  |  | 35.79 | 141.81 | [9 empty] | 177.6 | 177.6
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Labor Overheads | PGE1LABOROH |  |  |  | 470.57 | -470.57 |  |  | 83.46 | 387.11 | [9 empty] | 470.57 | 470.57
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT |  |  |  | 423.3 | -423.3 |  |  | 74.49 | 348.81 | [9 empty] | 423.3 | 423.3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Paid Time Off | 6010100 |  |  |  | 97.15 | -97.15 |  |  | 19.58 | 77.57 | [9 empty] | 97.15 | 97.15
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Indirect Labor - Electric | 6010106 |  |  |  | 59.18 | -59.18 |  |  |  | 59.18 | [9 empty] | 59.18 | 59.18
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Indirect Labor - Environmental Land | 6010108 |  |  |  | 108.74 | -108.74 |  |  | 34.34 | 74.4 | [9 empty] | 108.74 | 108.74
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Operation Mgmt & Support - Electric | 6010114 |  |  |  | 53.56 | -53.56 |  |  |  | 53.56 | [9 empty] | 53.56 | 53.56
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Operation Mgmt & Support - Environ Land | 6010116 |  |  |  | 65.13 | -65.13 |  |  | 20.57 | 44.56 | [9 empty] | 65.13 | 65.13
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Fleet OH - Elec | 6010125 |  |  |  | 39.54 | -39.54 |  |  |  | 39.54 | [9 empty] | 39.54 | 39.54
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH |  |  |  | 47.27 | -47.27 |  |  | 8.97 | 38.3 | [9 empty] | 47.27 | 47.27
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Building Service Overhead | 6010112 |  |  |  | 30.15 | -30.15 |  |  | 5.72 | 24.43 | [9 empty] | 30.15 | 30.15
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | IT Device OH | 6010113 |  |  |  | 17.12 | -17.12 |  |  | 3.25 | 13.87 | [9 empty] | 17.12 | 17.12
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Other Overhead | PGE1OTHEROH |  |  |  | 227.91 | -227.91 |  |  | 44.57 | 183.34 | [9 empty] | 227.91 | 227.91
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Benefits OH | 6010120 |  |  |  | 168.53 | -168.53 |  |  | 33.31 | 135.22 | [9 empty] | 168.53 | 168.53
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Payroll Taxes OH | 6010121 |  |  |  | 59.38 | -59.38 |  |  | 11.26 | 48.12 | [9 empty] | 59.38 | 59.38
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR |  |  |  | 77.03 | -77.03 |  |  | 0.76 | 76.27 | [9 empty] | 77.03 | 77.03
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | AFUDC-Borrowed | 5590030 |  |  |  | 20.83 | -20.83 |  |  | 0.21 | 20.62 | [9 empty] | 20.83 | 20.83
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | AFUDC-Equity | 5590031 |  |  |  | 56.2 | -56.2 |  |  | 0.55 | 55.65 | [9 empty] | 56.2 | 56.2
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 650000 |  | 1995265 | 1995265 | -1345265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 650000 |  | 1995265 | 1995265 | -1345265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Contract Total | PGE1CONTRACT | 650000 |  |  |  | 650000
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 650000 |  |  |  | 650000
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Contracts | 5490000 | 650000 |  |  |  | 650000
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 1995265 | 1995265 | -1995265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 1995265 | 1995265 | -1995265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 1995265 | 1995265 | -1995265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 1995265 | 1995265 | -1995265 | [6 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  |  |  | 500000 | 1495265
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 100000 |  | 4104000 | 4104000 | -4004000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 100000 |  | 4104000 | 4104000 | -4004000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Contract Total | PGE1CONTRACT | 100000 |  |  |  | 100000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 100000 |  |  |  | 100000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Contracts | 5490000 | 100000 |  |  |  | 100000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 4104000 | 4104000 | -4104000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 4104000 | 4104000 | -4104000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 4104000 | 4104000 | -4104000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 4104000 | 4104000 | -4104000 | [8 empty] | 104000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 4104000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 150000 |  | 3360000 | 3360000 | -3210000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 3360000 | 3360000 | -3210000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Contract Total | PGE1CONTRACT | 150000 |  |  |  | 150000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 150000 |  |  |  | 150000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Contracts | 5490000 | 150000 |  |  |  | 150000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 3360000 | 3360000 | -3360000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 3360000 | 3360000 | -3360000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 3360000 | 3360000 | -3360000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 3360000 | 3360000 | -3360000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 2860000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 150000 |  | 2200000 | 2200000 | -2050000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000 |  | 2200000 | 2200000 | -2050000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Contract Total | PGE1CONTRACT | 150000 |  |  |  | 150000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 150000 |  |  |  | 150000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Contracts | 5490000 | 150000 |  |  |  | 150000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 2200000 | 2200000 | -2200000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 2200000 | 2200000 | -2200000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 2200000 | 2200000 | -2200000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2200000 | 2200000 | -2200000 | [8 empty] | 100000 | 100000 | 100000 | 100000 | 100000 |  | 500000 | 1700000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 125000 |  | 400000 | 400000 | -275000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 125000 |  | 400000 | 400000 | -275000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Contract Total | PGE1CONTRACT | 125000 |  |  |  | 125000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 125000 |  |  |  | 125000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Contracts | 5490000 | 125000 |  |  |  | 125000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 400000 | 400000 | -400000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 400000 | 400000 | -400000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 400000 | 400000 | -400000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 400000 | 400000 | -400000 | [8 empty] | 50000 | 50000 | 25000 |  |  |  | 125000 | 275000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 75000 |  | 665000 | 665000 | -590000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 75000 |  | 665000 | 665000 | -590000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Contract Total | PGE1CONTRACT | 75000 |  |  |  | 75000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 75000 |  |  |  | 75000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Contracts | 5490000 | 75000 |  |  |  | 75000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 665000 | 665000 | -665000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 665000 | 665000 | -665000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 665000 | 665000 | -665000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 665000 | 665000 | -665000 | [8 empty] | 200000 | 200000 | 200000 | 65000 |  |  | 665000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 100000 |  | 2945000 | 2945000 | -2845000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 100000 |  | 2945000 | 2945000 | -2845000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Contract Total | PGE1CONTRACT | 100000 |  |  |  | 100000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 100000 |  |  |  | 100000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Contracts | 5490000 | 100000 |  |  |  | 100000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 2945000 | 2945000 | -2945000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 2945000 | 2945000 | -2945000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 2945000 | 2945000 | -2945000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 2945000 | 2945000 | -2945000 | [9 empty] | 945000 | 1000000 | 1000000 |  |  | 2945000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 100000 |  | 3021000 | 3021000 | -2921000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 100000 |  | 3021000 | 3021000 | -2921000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Contract Total | PGE1CONTRACT | 100000 |  |  |  | 100000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 100000 |  |  |  | 100000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Contracts | 5490000 | 100000 |  |  |  | 100000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Order Other Costs | PGE1ORD-OTHER |  |  | 3021000 | 3021000 | -3021000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  |  | 3021000 | 3021000 | -3021000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  |  | 3021000 | 3021000 | -3021000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 |  | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044 |  |  | 3021000 | 3021000 | -3021000 | [8 empty] | 21000 | 1000000 | 1000000 | 1000000 |  |  | 3021000

## PRJ002 - Hrs Detail
Order | Order Text | WBS Element | Job Owner | User Status | Partner CC |  | Partner Activity | Auth Hrs (AJE) | Total Actual Hours | Total Forecast | Total EAC | Jan 2021 Actual Hrs | Feb 2021 Actual Hrs | Mar 2021 Actual Hrs | Apr 2021 Actual Hrs | May 2021 Plan Hrs | Jun 2021 Plan Hrs | Jul 2021 Plan Hrs | Aug 2021 Plan Hrs | Sep 2021 Plan Hrs | Oct 2021 Plan Hrs | Nov 2021 Plan Hrs | Dec 2021 Plan Hrs | 2021 YTD Actuals + Remaining Plan | 2022 Fcst Hrs | 2023 Fcst Hrs | 2024 Fcst Hrs | Variance Hrs (Auth Hrs - EAC Hrs)
Overall Result | [7 empty] | 28157 | 25043.5 | 34 | 25077.5 | 2280.5 | 2620.5 | 5051.75 | 809.25 | [8 empty] | 10762 | 34 |  |  | 3079.5
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Result |  |  |  | 106.5 |  | 106.5 |  |  | 11 | [9 empty] | 11 |  |  |  | -106.5
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | PGE1/# | # | #
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Applied Technology Services | 12884 | TECHSV |  | 38 |  | 38 | [16 empty] | -38
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Capacity Planning | 13550 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Distribution Asset Management Several | 14459 | MANAGE |  | 1 |  | 1 | [16 empty] | -1
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | IT Telecom Maintenance | 13892 | Result |  | 8 |  | 8 | [16 empty] | -8
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | IT Telecom Maintenance | 13892 | HRSDT |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | IT Telecom Maintenance | 13892 | HRSOT |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | IT Telecom Maintenance | 13892 | HRSST |  | 4 |  | 4 | [16 empty] | -4
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Project Management & Controls | 14182 | CNSTOT |  | 11 |  | 11 |  |  | 11 | [9 empty] | 11 |  |  |  | -11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Reliability Planning | 13549 | Result |  | 44 |  | 44 | [16 empty] | -44
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 42 |  | 42 | [16 empty] | -42
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Reliability Planning | 13549 | ENGMPO |  | 2 |  | 2 | [16 empty] | -2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Result |  |  |  | 492.5 |  | 492.5 | 0.5 |  | 9 | 0.25 | [8 empty] | 9.75 |  |  |  | -492.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | PGE1/# | # | #
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Central Design North | 12974 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Central Design North | 12974 | EEST |  | 4.5 |  | 4.5 | [16 empty] | -4.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Central Design North | 12974 | EESTOT |  | 23 |  | 23 | [16 empty] | -23
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Facilities | 15154 | Result |  | 29.25 |  | 29.25 | 0.25 |  |  | 0.25 | [8 empty] | 0.5 |  |  |  | -29.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Facilities | 15154 | ADM-OT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Facilities | 15154 | ADMIN |  | 23.25 |  | 23.25 | [16 empty] | -23.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Facilities | 15154 | ENVPLN |  | 3.25 |  | 3.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -3.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | 0.25 | [11 empty] | 0.25 |  |  |  | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Enterprise Public Works Coordination | 15449 | Result |  | 2 |  | 2 | [16 empty] | -2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Acquisition | 12809 | Result |  | 166.25 |  | 166.25 | [16 empty] | -166.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Acquisition | 12809 | ACQLIT |  | 146.5 |  | 146.5 | [16 empty] | -146.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Acquisition | 12809 | ACQRIG |  | 10.75 |  | 10.75 | [16 empty] | -10.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Acquisition | 12809 | ADM-OT |  | 9 |  | 9 | [16 empty] | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Rights | 11929 | Result |  | 22 |  | 22 | [16 empty] | -22
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Rights | 11929 | ACQLIT |  | 19.5 |  | 19.5 | [16 empty] | -19.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Rights | 11929 | LNDRTS |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying | 12577 | Result |  | 148.25 |  | 148.25 | 0.25 | [11 empty] | 0.25 |  |  |  | -148.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying | 12577 | ACQLIT |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying | 12577 | ADM-OT |  | 4 |  | 4 | [16 empty] | -4
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying | 12577 | LNDENG |  | 140.75 |  | 140.75 | 0.25 | [11 empty] | 0.25 |  |  |  | -140.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Land Surveying | 12577 | MNGNCC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | LCE- Division Teams | 15789 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | LCE-Planning & Ops | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Project Management & Controls | 14182 | Result |  | 50 |  | 50 |  |  | 9 | [9 empty] | 9 |  |  |  | -50
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Project Management & Controls | 14182 | CNSTOT |  | 9 |  | 9 | [16 empty] | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Project Management & Controls | 14182 | ENGMAP |  | 32 |  | 32 | [16 empty] | -32
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Reliability Planning | 13549 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Reliability Planning | 13549 | ENGMAP |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Reliability Planning | 13549 | ENGMPO |  | 7 |  | 7 | [16 empty] | -7
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Result |  |  |  | 137 |  | 137 |  |  | 9 | 0.25 | [8 empty] | 9.25 |  |  |  | -137
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | PGE1/# | # | #
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Distribution Automation | 15346 | PRJMOT |  | 3 |  | 3 | [16 empty] | -3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | EM Facilities | 15154 | Result |  | 36.25 |  | 36.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -36.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | EM Facilities | 15154 | ADM-OT |  | 3 |  | 3 | [16 empty] | -3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | EM Facilities | 15154 | ADMIN |  | 26.75 |  | 26.75 | [16 empty] | -26.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | EM Facilities | 15154 | ENVPLN |  | 1.25 |  | 1.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -1.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | EM Facilities | 15154 | ENVSVC |  | 5.25 |  | 5.25 | [16 empty] | -5.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 2 |  | 2 | [16 empty] | -2
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | GC Gas Engr NO | 12688 | ENGSVC |  | 5 |  | 5 | [16 empty] | -5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | IT Telecom Maintenance | 13892 | HRSST |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Land Surveying | 12577 | LNDENG |  | 1 |  | 1 | [16 empty] | -1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | LCE- Division Teams | 15789 | ACTSVC |  | 6.75 |  | 6.75 | [16 empty] | -6.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | LCE-Planning & Ops | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Project Management & Controls | 14182 | Result |  | 37 |  | 37 |  |  | 9 | [9 empty] | 9 |  |  |  | -37
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Project Management & Controls | 14182 | ENGMAP |  | 28 |  | 28 | [16 empty] | -28
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Reliability Planning | 13549 | Result |  | 26.5 |  | 26.5 | [16 empty] | -26.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 22.5 |  | 22.5 | [16 empty] | -22.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Reliability Planning | 13549 | ENGMPO |  | 4 |  | 4 | [16 empty] | -4
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Result |  |  | 437 | 162.25 |  | 162.25 | [16 empty] | 274.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | PGE1/# | # | #
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Distribution Line Tech - SCADA | 15275 | Result |  | 16.5 |  | 16.5 | [16 empty] | -16.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Distribution Line Tech - SCADA | 15275 | MO |  | 15 |  | 15 | [16 empty] | -15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Distribution Operations Engineering | 14521 | ENGMAP | 13 | 3 |  | 3 | [16 empty] | 10
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | EM Facilities | 15154 | Result | 8 | 19.5 |  | 19.5 | [16 empty] | -11.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | EM Facilities | 15154 | ADMIN | 8 | 17.75 |  | 17.75 | [16 empty] | -9.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | EO&E E&T System Automation | 12148 | SCADSV |  | 2 |  | 2 | [16 empty] | -2
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | IT Telecom Maintenance | 13892 | Result |  | 12 |  | 12 | [16 empty] | -12
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | IT Telecom Maintenance | 13892 | HRSOT |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | IT Telecom Maintenance | 13892 | HRSST |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Land Surveying | 12577 | Result | 27 | 8.5 |  | 8.5 | [16 empty] | 18.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Land Surveying | 12577 | ACQLIT | 27 | 7.5 |  | 7.5 | [16 empty] | 19.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Land Surveying | 12577 | ADM-OT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 19.75 |  | 19.75 | [16 empty] | -19.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | North Distribution Control Center | 11890 | Result | 234 | 8 |  | 8 | [16 empty] | 226
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | North Distribution Control Center | 11890 | MO | 234 | 6 |  | 6 | [16 empty] | 228
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 88 | 24 |  | 24 | [16 empty] | 64
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 21 |  | 21 | [16 empty] | -21
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | SI Restoration | 14110 | FLDSVC | 66 | [19 empty] | 66
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Result |  |  |  | 588 |  | 588 | 1 |  | 9 | 0.5 | [8 empty] | 10.5 |  |  |  | -588
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | PGE1/# | # | #
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Distribution Automation | 15346 | PRJMOT |  | 4 |  | 4 | [16 empty] | -4
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Distribution Operations Engineering | 14521 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | EM Facilities | 15154 | Result |  | 33.75 |  | 33.75 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -33.75
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | EM Facilities | 15154 | ADMIN |  | 19 |  | 19 | [16 empty] | -19
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | EM Facilities | 15154 | ENVPLN |  | 11.5 |  | 11.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -11.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | EM Facilities | 15154 | ENVSVC |  | 3.25 |  | 3.25 | [16 empty] | -3.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYST |  | 5 |  | 5 | 1 | [11 empty] | 1 |  |  |  | -5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 1 |  | 1 | [16 empty] | -1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | IT Telecom Maintenance | 13892 | HRSOT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Rights | 11929 | Result |  | 3 |  | 3 | [16 empty] | -3
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Rights | 11929 | ACQLIT |  | 2 |  | 2 | [16 empty] | -2
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Surveying | 12577 | Result |  | 458.25 |  | 458.25 | [16 empty] | -458.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Surveying | 12577 | ACQLIT |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Surveying | 12577 | ADM-OT |  | 70.5 |  | 70.5 | [16 empty] | -70.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Land Surveying | 12577 | LNDENG |  | 385.5 |  | 385.5 | [16 empty] | -385.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | LCE- Division Teams | 15789 | ACTSVC |  | 8.5 |  | 8.5 | [16 empty] | -8.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | LCE-Planning & Ops | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Project Management & Controls | 14182 | Result |  | 25 |  | 25 |  |  | 9 | [9 empty] | 9 |  |  |  | -25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Project Management & Controls | 14182 | CNSTOT |  | 16 |  | 16 | [16 empty] | -16
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Reliability Planning | 13549 | ENGMAP |  | 29 |  | 29 | [16 empty] | -29
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | VP Elec Distribution Operations | 15443 | MANAGE |  | 13 |  | 13 | [16 empty] | -13
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Result |  |  | 97 | 216 |  | 216 |  | 1 | 5 | [9 empty] | 6 |  |  |  | -119
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | PGE1/# | # | #
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Apprentice - Training Coordinator | 12689 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Business Operations | 15495 | ACTSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Distribution Line Tech - SCADA | 15275 | Result |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Distribution Line Tech - SCADA | 15275 | MO |  | 8 |  | 8 | [16 empty] | -8
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Distribution Operations Engineering | 14521 | ENGMAP | 2 | 2 |  | 2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | EM Facilities | 15154 | Result | 24 | 55.5 |  | 55.5 | [16 empty] | -31.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | EM Facilities | 15154 | ADMIN | 15 | 42 |  | 42 | [16 empty] | -27
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | EM Facilities | 15154 | ENVPLN | 6 | 10.5 |  | 10.5 | [16 empty] | -4.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | EM Facilities | 15154 | ENVSVC | 3 | 3 |  | 3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Land Rights | 11929 | LNDRTS | 1 | 6 |  | 6 | [16 empty] | -5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | LCE- Division Teams | 15789 | ACTSVC | 1 | 0.75 |  | 0.75 | [16 empty] | 0.25
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | LCE-Planning & Ops | 15497 | ACTSVC | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | North Distribution Control Center | 11890 | Result | 16 | 37.75 |  | 37.75 | [16 empty] | -21.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | North Distribution Control Center | 11890 | MO | 16 | 16 |  | 16
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | North Distribution Control Center | 11890 | MO-DT |  | 18.75 |  | 18.75 | [16 empty] | -18.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | North Distribution Control Center | 11890 | MO-OT |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Project Management & Controls | 14182 | ENGMAP | 4 | 10 |  | 10 |  | 1 | 5 | [9 empty] | 6 |  |  |  | -6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Reliability Planning | 13549 | ENGMAP | 29 | 31 |  | 31 | [16 empty] | -2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | SI Restoration | 14110 | Result |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | SI Restoration | 14110 | FLDSDT |  | 9.75 |  | 9.75 | [16 empty] | -9.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | SI Restoration | 14110 | FLDSOT |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | SI Restoration | 14110 | FLDSVC |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | SI Restoration - NOT USE | 12044 | FLDSVC | 17 | [19 empty] | 17
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | South Distribution Control Center | 11797 | Result |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | South Distribution Control Center | 11797 | MO |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | South Distribution Control Center | 11797 | MO-DT |  | 2 |  | 2 | [16 empty] | -2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Substation Maintenance | 10472 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Substation Maintenance | 10472 | MO |  | 7 |  | 7 | [16 empty] | -7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Substation Maintenance | 10472 | SWTCHO |  | 10 |  | 10 | [16 empty] | -10
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Substation Maintenance | 10472 | SWTODT |  | 6 |  | 6 | [16 empty] | -6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Substation Maintenance | 10472 | SWTOOT |  | 10.5 |  | 10.5 | [16 empty] | -10.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Result |  |  |  | 4528.75 |  | 4528.75 | 19.75 | 76.25 | 749.25 | 38.5 | [8 empty] | 883.75 |  |  |  | -4528.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | PGE1/# | # | #
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Apprentice - Training Coordinator | 12689 | Result |  | 7 |  | 7 |  | 4 | 3 | [9 empty] | 7 |  |  |  | -7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Apprentice - Training Coordinator | 12689 | MO |  | 4 |  | 4 |  | 1 | 3 | [9 empty] | 4 |  |  |  | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Apprentice - Training Coordinator | 12689 | MO-DT |  | 3 |  | 3 |  | 3 | [10 empty] | 3 |  |  |  | -3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Business Operations | 15495 | ACTSVC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | CC Work Force Management | 11034 | MANAGE |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Asset Management Several | 14459 | MANAGE |  | 2 |  | 2 | [16 empty] | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | Result |  | 29.5 |  | 29.5 |  | 8 | [10 empty] | 8 |  |  |  | -29.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | MO |  | 16.5 |  | 16.5 |  | 6 | [10 empty] | 6 |  |  |  | -16.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | MO-DT |  | 3 |  | 3 | [16 empty] | -3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 10 |  | 10 |  | 2 | [10 empty] | 2 |  |  |  | -10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | EM Facilities | 15154 | Result |  | 107 |  | 107 | 2.5 | 2 | 6.25 | 1 | [8 empty] | 11.75 |  |  |  | -107
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | EM Facilities | 15154 | ADM-OT |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | EM Facilities | 15154 | ADMIN |  | 64 |  | 64 |  | 2 | 1 | [9 empty] | 3 |  |  |  | -64
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | EM Facilities | 15154 | ENVPLN |  | 41 |  | 41 | 2.5 |  | 3.25 | 1 | [8 empty] | 6.75 |  |  |  | -41
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | EM Projects | 15240 | BIOCUL |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec NV South | 15216 | Result |  | 260.5 |  | 260.5 |  |  | 260.5 | [9 empty] | 260.5 |  |  |  | -260.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec NV South | 15216 | CNSTDT |  | 48 |  | 48 |  |  | 48 | [9 empty] | 48 |  |  |  | -48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec NV South | 15216 | CNSTOT |  | 42.5 |  | 42.5 |  |  | 42.5 | [9 empty] | 42.5 |  |  |  | -42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec NV South | 15216 | CONSTR |  | 170 |  | 170 |  |  | 170 | [9 empty] | 170 |  |  |  | -170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SA | 11832 | Result |  | 114.5 |  | 114.5 |  |  | 114.5 | [9 empty] | 114.5 |  |  |  | -114.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SA | 11832 | CNSTDT |  | 14.5 |  | 14.5 |  |  | 14.5 | [9 empty] | 14.5 |  |  |  | -14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SA | 11832 | CNSTOT |  | 20 |  | 20 |  |  | 20 | [9 empty] | 20 |  |  |  | -20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SA | 11832 | CONSTR |  | 80 |  | 80 |  |  | 80 | [9 empty] | 80 |  |  |  | -80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SI North | 14632 | Result |  | 3479.5 |  | 3479.5 |  | 16.5 | 324.5 | [9 empty] | 341 |  |  |  | -3479.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SI North | 14632 | CNSTDT |  | 58.5 |  | 58.5 |  |  | 11 | [9 empty] | 11 |  |  |  | -58.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SI North | 14632 | CNSTOT |  | 276.5 |  | 276.5 |  | 1.5 | 43.5 | [9 empty] | 45 |  |  |  | -276.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec SI North | 14632 | CONSTR |  | 3144.5 |  | 3144.5 |  | 15 | 270 | [9 empty] | 285 |  |  |  | -3144.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec Sonoma | 11838 | Result |  | 15 |  | 15 |  |  | 15 | [9 empty] | 15 |  |  |  | -15
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec Sonoma | 11838 | CNSTDT |  | 2.5 |  | 2.5 |  |  | 2.5 | [9 empty] | 2.5 |  |  |  | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec Sonoma | 11838 | CNSTOT |  | 2.5 |  | 2.5 |  |  | 2.5 | [9 empty] | 2.5 |  |  |  | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | GC Elec Sonoma | 11838 | CONSTR |  | 10 |  | 10 |  |  | 10 | [9 empty] | 10 |  |  |  | -10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | IT Telecom Maintenance | 13892 | HRSST |  | 4 |  | 4 | [16 empty] | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Acquisition | 12809 | Result |  | 76.5 |  | 76.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -76.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Acquisition | 12809 | ACQLIT |  | 67 |  | 67 |  |  | 3 | [9 empty] | 3 |  |  |  | -67
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Acquisition | 12809 | ADMIN |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Surveying | 12577 | Result |  | 15.75 |  | 15.75 | [16 empty] | -15.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Surveying | 12577 | ADM-OT |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Surveying | 12577 | LNDENG |  | 13.5 |  | 13.5 | [16 empty] | -13.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | LCE- Division Teams | 15789 | ACTSVC |  | 20 |  | 20 | 2 | 1 | 3 | [9 empty] | 6 |  |  |  | -20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | LCE-Planning & Ops | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | North Distribution Control Center | 11890 | Result |  | 22 |  | 22 | 1.25 | 5.75 | 3 | [9 empty] | 10 |  |  |  | -22
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | North Distribution Control Center | 11890 | MO |  | 10 |  | 10 | 0.75 | 3 | 0.5 | [9 empty] | 4.25 |  |  |  | -10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | North Distribution Control Center | 11890 | MO-DT |  | 5.75 |  | 5.75 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -5.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | North Distribution Control Center | 11890 | MO-OT |  | 6.25 |  | 6.25 | 0.5 | 2.75 | 1 | [9 empty] | 4.25 |  |  |  | -6.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operations Systems | 10484 | SCADSV |  | 4 |  | 4 |  | 4 | [10 empty] | 4 |  |  |  | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Project Management & Controls | 14182 | Result |  | 263 |  | 263 | 14 | 35 | 6.5 | 37.5 | [8 empty] | 93 |  |  |  | -263
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Project Management & Controls | 14182 | CONSTR |  | 220 |  | 220 | 14 | 34 |  | 36 | [8 empty] | 84 |  |  |  | -220
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Project Management & Controls | 14182 | ENGMAP |  | 43 |  | 43 |  | 1 | 6.5 | 1.5 | [8 empty] | 9 |  |  |  | -43
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Reliability Planning | 13549 | Result |  | 75.5 |  | 75.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -75.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Reliability Planning | 13549 | ENGMAP |  | 74.5 |  | 74.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -74.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Safety Infrastructure Protection Team | 15937 | MANAGE |  | 5 |  | 5 |  |  | 5 | [9 empty] | 5 |  |  |  | -5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE |  | 20 |  | 20 | [16 empty] | -20
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Result |  |  | 5142 | 1721.5 |  | 1721.5 | 57.75 | 462.5 | 195.25 | 107.5 | [8 empty] | 823 |  |  |  | 3420.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | PGE1/# | # | #
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Business Operations | 15495 | ACTSVC | 22 | 3.25 |  | 3.25 | 0.75 | [11 empty] | 0.75 |  |  |  | 18.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | CC Work Force Management | 11034 | MANAGE | 26 | 1 |  | 1 | 0.5 | [11 empty] | 0.5 |  |  |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Central Design North | 12974 | Result |  | 11.5 |  | 11.5 | [16 empty] | -11.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Central Design North | 12974 | EEST |  | 8.5 |  | 8.5 | [16 empty] | -8.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Central Design North | 12974 | EESTOT |  | 3 |  | 3 | [16 empty] | -3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Distribution Asset Management Several | 14459 | MANAGE | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | Result |  | 11.25 |  | 11.25 |  |  | 11.25 | [9 empty] | 11.25 |  |  |  | -11.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | MO |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 2.25 |  | 2.25 |  |  | 2.25 | [9 empty] | 2.25 |  |  |  | -2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | EM Facilities | 15154 | Result | 40 | 28.75 |  | 28.75 |  |  | 3 | 1 | [8 empty] | 4 |  |  |  | 11.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | EM Facilities | 15154 | ADM-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | EM Facilities | 15154 | ADMIN | 30 | 22 |  | 22 |  |  | 1 | [9 empty] | 1 |  |  |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | EM Facilities | 15154 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | EM Facilities | 15154 | ENVPLN | 10 | 4.25 |  | 4.25 |  |  | 2 | 1 | [8 empty] | 3 |  |  |  | 5.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | GC Elec SI North | 14632 | Result |  | 1444.5 |  | 1444.5 | 52.5 | 455.5 | 156 | 70 | [8 empty] | 734 |  |  |  | -1444.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | GC Elec SI North | 14632 | CNSTOT |  | 74.5 |  | 74.5 | 2.5 | 15.5 | 6 | 30 | [8 empty] | 54 |  |  |  | -74.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | GC Elec SI North | 14632 | CONSTR |  | 1370 |  | 1370 | 50 | 440 | 150 | 40 | [8 empty] | 680 |  |  |  | -1370
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | GC Elec SI South | 11834 | CONSTR | 4741 | [19 empty] | 4741
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | IT Telecom Maintenance | 13892 | HRSST |  | 8 |  | 8 |  |  | 8 | [9 empty] | 8 |  |  |  | -8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Rights | 11929 | Result | 30 | 20.25 |  | 20.25 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | 9.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Rights | 11929 | ACQLIT | 29 | 3.75 |  | 3.75 | [16 empty] | 25.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Rights | 11929 | ADM-OT |  | 2 |  | 2 | [16 empty] | -2
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Rights | 11929 | LNDRTS | 1 | 14.5 |  | 14.5 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -13.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Land Surveying | 12577 | LNDENG |  | 5 |  | 5 | [16 empty] | -5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 25 | 35 |  | 35 | 3 | 3 | 4 | [9 empty] | 10 |  |  |  | -10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | LCE-Planning & Ops | 15497 | ACTSVC | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Project Management & Controls | 14182 | Result | 156 | 71 |  | 71 |  |  | 2.5 | 36.5 | [8 empty] | 39 |  |  |  | 85
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Project Management & Controls | 14182 | CONSTR | 20 | 60 |  | 60 |  |  |  | 36 | [8 empty] | 36 |  |  |  | -40
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Project Management & Controls | 14182 | ENGMAP | 136 | 11 |  | 11 |  |  | 2.5 | 0.5 | [8 empty] | 3 |  |  |  | 125
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Reliability Planning | 13549 | Result | 73 | 47 |  | 47 |  | 4 | 3 | [9 empty] | 7 |  |  |  | 26
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Reliability Planning | 13549 | ENGMAP | 68 | 42.5 |  | 42.5 |  | 4 | 3 | [9 empty] | 7 |  |  |  | 25.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Reliability Planning | 13549 | ENGMPO | 5 | 4.5 |  | 4.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | SI Gas Construction | 12055 | CONSTR |  | 6 |  | 6 |  |  | 6 | [9 empty] | 6 |  |  |  | -6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 23 | 23 |  | 23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Result |  |  | 100 | 137.75 |  | 137.75 | [16 empty] | -37.75
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | PGE1/# | # | #
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Business Operations | 15495 | ACTSVC | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | EM Facilities | 15154 | Result | 50 | 28.25 |  | 28.25 | [16 empty] | 21.75
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | EM Facilities | 15154 | ADM-OT | 1 | 1 |  | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | EM Facilities | 15154 | ADMIN | 47 | 24 |  | 24 | [16 empty] | 23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | EM Facilities | 15154 | ENVPLN | 2 | 2 |  | 2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | IT Telecom Maintenance | 13892 | HRSST | 3 | 3 |  | 3
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT | 31 | 2 |  | 2 | [16 empty] | 29
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Surveying | 12577 | Result | 3 | 2 |  | 2 | [16 empty] | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 11 | 25 |  | 25 | [16 empty] | -14
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 4 |  | 4 | [16 empty] | -4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | North Distribution Control Center | 11890 | Result |  | 6 |  | 6 | [16 empty] | -6
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | North Distribution Control Center | 11890 | MO |  | 4 |  | 4 | [16 empty] | -4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 2 |  | 2 | [16 empty] | -2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Project Management & Controls | 14182 | Result |  | 41 |  | 41 | [16 empty] | -41
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Project Management & Controls | 14182 | CNSTOT |  | 5 |  | 5 | [16 empty] | -5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Project Management & Controls | 14182 | ENGMAP |  | 36 |  | 36 | [16 empty] | -36
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Reliability Planning | 13549 | Result |  | 6 |  | 6 | [16 empty] | -6
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 5 |  | 5 | [16 empty] | -5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 17 |  | 17 | [16 empty] | -17
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Result |  |  |  | 153.25 |  | 153.25 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -153.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | PGE1/# | # | #
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | EM Facilities | 15154 | Result |  | 20 |  | 20 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -20
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | EM Facilities | 15154 | ADMIN |  | 17 |  | 17 | [16 empty] | -17
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | EM Facilities | 15154 | ENVSVC |  | 2 |  | 2 | [16 empty] | -2
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Surveying | 12577 | Result |  | 53.75 |  | 53.75 | [16 empty] | -53.75
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Surveying | 12577 | ACQLIT |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Surveying | 12577 | ADM-OT |  | 5 |  | 5 | [16 empty] | -5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Land Surveying | 12577 | LNDENG |  | 48 |  | 48 | [16 empty] | -48
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | LCE- Division Teams | 15789 | ACTSVC |  | 21.25 |  | 21.25 | [16 empty] | -21.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | LCE-Planning & Ops | 15497 | ACTSVC |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Project Management & Controls | 14182 | Result |  | 39 |  | 39 | [16 empty] | -39
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Project Management & Controls | 14182 | CNSTOT |  | 11 |  | 11 | [16 empty] | -11
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Project Management & Controls | 14182 | ENGMAP |  | 28 |  | 28 | [16 empty] | -28
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Reliability Planning | 13549 | Result |  | 7 |  | 7 | [16 empty] | -7
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 5 |  | 5 | [16 empty] | -5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Reliability Planning | 13549 | ENGMPO |  | 2 |  | 2 | [16 empty] | -2
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Result |  |  | 268 | 93 |  | 93 | [16 empty] | 175
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | PGE1/# | # | #
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Business Operations | 15495 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | EM Facilities | 15154 | Result | 20 | 16.75 |  | 16.75 | [16 empty] | 3.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | EM Facilities | 15154 | ADMIN | 19 | 12.5 |  | 12.5 | [16 empty] | 6.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | EM Facilities | 15154 | ENVPLN | 1 | 2.5 |  | 2.5 | [16 empty] | -1.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | EM Facilities | 15154 | ENVSVC |  | 1.75 |  | 1.75 | [16 empty] | -1.75
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | LCE- Division Teams | 15789 | ACTSVC | 2 | 30.25 |  | 30.25 | [16 empty] | -28.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | North Distribution Control Center | 11890 | Result | 100 | 1.5 |  | 1.5 | [16 empty] | 98.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | North Distribution Control Center | 11890 | MO | 100 | 1.25 |  | 1.25 | [16 empty] | 98.75
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | North Distribution Control Center | 11890 | MO-OT |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Project Management & Controls | 14182 | Result | 89 | 29 |  | 29 | [16 empty] | 60
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Project Management & Controls | 14182 | CNSTOT | 9 | 9 |  | 9
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Project Management & Controls | 14182 | ENGMAP | 80 | 20 |  | 20 | [16 empty] | 60
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Reliability Planning | 13549 | Result | 7 | 11 |  | 11 | [16 empty] | -4
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Reliability Planning | 13549 | ENGMAP | 6 | 10 |  | 10 | [16 empty] | -4
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 |  | FICL | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Result |  |  | 242 | 84.75 |  | 84.75 | [16 empty] | 157.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | PGE1/# | # | #
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | EM Facilities | 15154 | Result | 3 | 12.25 |  | 12.25 | [16 empty] | -9.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | EM Facilities | 15154 | ADMIN | 3 | 11 |  | 11 | [16 empty] | -8
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 1 | 21.5 |  | 21.5 | [16 empty] | -20.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | North Distribution Control Center | 11890 | MO | 120 | 5.5 |  | 5.5 | [16 empty] | 114.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Project Management & Controls | 14182 | Result | 64 | 22 |  | 22 | [16 empty] | 42
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Project Management & Controls | 14182 | CNSTOT |  | 6 |  | 6 | [16 empty] | -6
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 64 | 16 |  | 16 | [16 empty] | 48
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Reliability Planning | 13549 | Result | 3 | 6 |  | 6 | [16 empty] | -3
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 2 | 5 |  | 5 | [16 empty] | -3
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 17 |  | 17 | [16 empty] | -17
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Result |  |  | 155 | 108.5 |  | 108.5 | [16 empty] | 46.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | PGE1/# | # | #
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Capacity Planning | 13550 | ENGMAP | 2 | 2 |  | 2
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | EM Facilities | 15154 | ADMIN | 5 | 18 |  | 18 | [16 empty] | -13
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Gas Locate & Mark North | 15893 | Result |  | 19.5 |  | 19.5 | [16 empty] | -19.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Gas Locate & Mark North | 15893 | CNSTOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Gas Locate & Mark North | 15893 | CONSTR |  | 16 |  | 16 | [16 empty] | -16
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Land Rights | 11929 | ACQLIT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 7 | 20.5 |  | 20.5 | [16 empty] | -13.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | North Distribution Control Center | 11890 | Result | 25 | 0.5 |  | 0.5 | [16 empty] | 24.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | North Distribution Control Center | 11890 | MO | 25 | [19 empty] | 25
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 56 | 24 |  | 24 | [16 empty] | 32
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Reliability Planning | 13549 | Result | 5 | 4.5 |  | 4.5 | [16 empty] | 0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | SI Restoration | 14110 | FLDSVC | 55 | [19 empty] | 55
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Result |  |  |  | 87.75 |  | 87.75 |  |  | 1.5 | 0.25 | [8 empty] | 1.75 |  |  |  | -87.75
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | PGE1/# | # | #
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Central Design Contract Estimating | 11714 | EEST |  | 31.5 |  | 31.5 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -31.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | EM Facilities | 15154 | Result |  | 25 |  | 25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | EM Facilities | 15154 | ADMIN |  | 24.75 |  | 24.75 | [16 empty] | -24.75
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | EM Facilities | 15154 | ENVPLN |  | 0.25 |  | 0.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 2 |  | 2 | [16 empty] | -2
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Land Surveying | 12577 | LNDENG |  | 3 |  | 3 | [16 empty] | -3
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | LCE- Division Teams | 15789 | ACTSVC |  | 8.25 |  | 8.25 | [16 empty] | -8.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | LCE-Planning & Ops | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Project Management & Controls | 14182 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Reliability Planning | 13549 | Result |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | VP Elec Distribution Operations | 15443 | MANAGE |  | 8 |  | 8 | [16 empty] | -8
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Result |  |  | 133 | 63.25 |  | 63.25 | [16 empty] | 69.75
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | PGE1/# | # | #
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | EM Facilities | 15154 | Result | 4 | 7 |  | 7 | [16 empty] | -3
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | EM Facilities | 15154 | ADMIN | 4 | 4.75 |  | 4.75 | [16 empty] | -0.75
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | EM Facilities | 15154 | ENVPLN |  | 2 |  | 2 | [16 empty] | -2
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 2 | 26.5 |  | 26.5 | [16 empty] | -24.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | North Distribution Control Center | 11890 | MO | 30 | [19 empty] | 30
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 1 |  | 1 | [16 empty] | -1
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | SI Restoration | 14110 | FLDSVC | 33 | [19 empty] | 33
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Result |  |  |  | 191.75 |  | 191.75 | [16 empty] | -191.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | PGE1/# | # | #
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | EM Facilities | 15154 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | EM Facilities | 15154 | ADM-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | EM Facilities | 15154 | ADMIN |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | EM Facilities | 15154 | ENVPLN |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Gas Locate & Mark North | 15893 | Result |  | 37.75 |  | 37.75 | [16 empty] | -37.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Gas Locate & Mark North | 15893 | CNSTDT |  | 5 |  | 5 | [16 empty] | -5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Gas Locate & Mark North | 15893 | CNSTOT |  | 4.75 |  | 4.75 | [16 empty] | -4.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Gas Locate & Mark North | 15893 | CONSTR |  | 28 |  | 28 | [16 empty] | -28
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Acquisition | 12809 | Result |  | 35.5 |  | 35.5 | [16 empty] | -35.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Acquisition | 12809 | ACQLIT |  | 32 |  | 32 | [16 empty] | -32
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Acquisition | 12809 | ACQRIG |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Rights | 11929 | Result |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Rights | 11929 | ACQLIT |  | 3 |  | 3 | [16 empty] | -3
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Surveying | 12577 | Result |  | 14.75 |  | 14.75 | [16 empty] | -14.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Surveying | 12577 | LNDENG |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 21.75 |  | 21.75 | [16 empty] | -21.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 9 |  | 9 | [16 empty] | -9
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | North Distribution Control Center | 11890 | Result |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | North Distribution Control Center | 11890 | MO |  | 2 |  | 2 | [16 empty] | -2
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Project Management & Controls | 14182 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Result |  |  | 345 | 117.75 |  | 117.75 | [16 empty] | 227.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | PGE1/# | # | #
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Facilities | 15154 | Result | 4 | 50.75 |  | 50.75 | [16 empty] | -46.75
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Facilities | 15154 | ADM-OT |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Facilities | 15154 | ADMIN | 3 | 32.25 |  | 32.25 | [16 empty] | -29.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Facilities | 15154 | ENVPLN | 1 | 13.5 |  | 13.5 | [16 empty] | -12.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 4 |  | 4 | [16 empty] | -4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 7 |  | 7 | [16 empty] | -7
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Land Surveying | 12577 | ACQLIT | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 2 | 19 |  | 19 | [16 empty] | -17
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 11 |  | 11 | [16 empty] | -11
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | North Distribution Control Center | 11890 | Result | 234 | 3 |  | 3 | [16 empty] | 231
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | North Distribution Control Center | 11890 | MO | 234 | 2 |  | 2 | [16 empty] | 232
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 48 | [19 empty] | 48
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Substation Project Control Analyst | 15322 | PRJMGT | 1 | 1 |  | 1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | Vegetation Management | 11140 | PRJMGT | 2 | 6 |  | 6 | [16 empty] | -4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 11 |  | 11 | [16 empty] | -11
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Result |  |  | 362 | 83.75 |  | 83.75 | [16 empty] | 278.25
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | PGE1/# | # | #
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | EM Facilities | 15154 | Result | 6 | 17.75 |  | 17.75 | [16 empty] | -11.75
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | EM Facilities | 15154 | ADMIN | 6 | 14.5 |  | 14.5 | [16 empty] | -8.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 3.25 |  | 3.25 | [16 empty] | -3.25
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Gas Locate & Mark North | 15893 | CONSTR |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Land Rights | 11929 | ACQLIT | 3 | 3 |  | 3
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 1 | 18 |  | 18 | [16 empty] | -17
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | North Distribution Control Center | 11890 | MO | 234 | [19 empty] | 234
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 2 | 3 |  | 3 | [16 empty] | -1
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Result |  |  | 137 | 138 |  | 138 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | PGE1/# | # | #
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | EM Facilities | 15154 | Result | 1 | 37.25 |  | 37.25 | [16 empty] | -36.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | EM Facilities | 15154 | ADMIN |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | EM Facilities | 15154 | ENVPLN | 1 | 7.5 |  | 7.5 | [16 empty] | -6.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 5 |  | 5 | [16 empty] | -5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Land Rights | 11929 | ACQLIT | 2 | 2 |  | 2
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 20.75 |  | 20.75 | [16 empty] | -20.75
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | North Distribution Control Center | 11890 | Result | 30 | 16.5 |  | 16.5 | [16 empty] | 13.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | North Distribution Control Center | 11890 | MO | 30 | 5.5 |  | 5.5 | [16 empty] | 24.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 10.5 |  | 10.5 | [16 empty] | -10.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | SI Restoration | 14110 | Result | 40 | 26.5 |  | 26.5 | [16 empty] | 13.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | SI Restoration | 14110 | FLDSDT |  | 4.5 |  | 4.5 | [16 empty] | -4.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | SI Restoration | 14110 | FLDSOT |  | 15.25 |  | 15.25 | [16 empty] | -15.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | SI Restoration | 14110 | FLDSVC | 40 | 6.75 |  | 6.75 | [16 empty] | 33.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | Vegetation Management | 11140 | PRJMGT |  | 1 |  | 1 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Result |  |  | 157 | 103.75 |  | 103.75 | 4.5 | [11 empty] | 4.5 |  |  |  | 53.25
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | PGE1/# | # | #
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | EM Facilities | 15154 | ADMIN | 3 | 8.75 |  | 8.75 | [16 empty] | -5.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 2 |  | 2 | [16 empty] | -2
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 22.75 |  | 22.75 | 4.5 | [11 empty] | 4.5 |  |  |  | -22.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 4 |  | 4 | [16 empty] | -4
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | North Distribution Control Center | 11890 | Result | 40 | 10 |  | 10 | [16 empty] | 30
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | North Distribution Control Center | 11890 | MO | 40 | 5 |  | 5 | [16 empty] | 35
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 64 | 16 |  | 16 | [16 empty] | 48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | SI Restoration | 14110 | Result | 50 | 22.25 |  | 22.25 | [16 empty] | 27.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | SI Restoration | 14110 | FLDSDT |  | 6.25 |  | 6.25 | [16 empty] | -6.25
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | SI Restoration | 14110 | FLDSOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | SI Restoration | 14110 | FLDSVC | 50 | 12.5 |  | 12.5 | [16 empty] | 37.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Result |  |  | 270 | 68.5 |  | 68.5 | [16 empty] | 201.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | PGE1/# | # | #
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Central Design Contract Estimating | 11714 | DSGNSV |  | 3 |  | 3 | [16 empty] | -3
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | EM Facilities | 15154 | ADMIN |  | 12.75 |  | 12.75 | [16 empty] | -12.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | EM Projects | 15240 | ENVSVC | 15 | [19 empty] | 15
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Land Natural Resource Mgmt | 14178 | Result | 15 | 2 |  | 2 | [16 empty] | 13
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Land Natural Resource Mgmt | 14178 | LNDRTS | 15 | [19 empty] | 15
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 2 |  | 2 | [16 empty] | -2
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 23.75 |  | 23.75 | [16 empty] | -23.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | North Distribution Control Center | 11890 | MO | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | SI Restoration | 14110 | FLDSVC | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 26 |  | 26 | [16 empty] | -26
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Result |  |  |  | 65.75 |  | 65.75 | 5 | [11 empty] | 5 |  |  |  | -65.75
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | PGE1/# | # | #
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | EM Facilities | 15154 | ADMIN |  | 12.25 |  | 12.25 | [16 empty] | -12.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 9.25 |  | 9.25 | 5 | [11 empty] | 5 |  |  |  | -9.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 5 |  | 5 | [16 empty] | -5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Project Management & Controls | 14182 | Result |  | 28 |  | 28 | [16 empty] | -28
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Project Management & Controls | 14182 | CNSTOT |  | 4 |  | 4 | [16 empty] | -4
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Project Management & Controls | 14182 | ENGMAP |  | 24 |  | 24 | [16 empty] | -24
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | Reliability Planning | 13549 | ENGMAP |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Result |  |  | 185 | 123 |  | 123 | [16 empty] | 62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | PGE1/# | # | #
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Central Distribution Control Center | 12133 | MO-DT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | EM Facilities | 15154 | Result | 15 | 11 |  | 11 | [16 empty] | 4
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | EM Facilities | 15154 | ADMIN | 13 | 9 |  | 9 | [16 empty] | 4
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | EM Facilities | 15154 | ENVPLN | 1 | 1 |  | 1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | EM Facilities | 15154 | ENVSVC | 1 | 1 |  | 1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Land Surveying | 12577 | ACQLIT | 10 | 1.5 |  | 1.5 | [16 empty] | 8.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 4 | 16.5 |  | 16.5 | [16 empty] | -12.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | North Distribution Control Center | 11890 | Result | 50 | 30.75 |  | 30.75 | [16 empty] | 19.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | North Distribution Control Center | 11890 | MO | 50 | 17.75 |  | 17.75 | [16 empty] | 32.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | North Distribution Control Center | 11890 | MO-DT |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Project Management & Controls | 14182 | Result | 48 | 14 |  | 14 | [16 empty] | 34
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Project Management & Controls | 14182 | CNSTOT |  | 10 |  | 10 | [16 empty] | -10
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Project Management & Controls | 14182 | ENGMAP | 48 | 4 |  | 4 | [16 empty] | 44
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 8 | 9 |  | 9 | [16 empty] | -1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | SI Restoration | 14110 | Result | 50 | 9.75 |  | 9.75 | [16 empty] | 40.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | SI Restoration | 14110 | FLDSOT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | SI Restoration | 14110 | FLDSVC | 50 | 7.25 |  | 7.25 | [16 empty] | 42.75
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Result |  |  | 99 | 103 |  | 103 | [16 empty] | -4
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | PGE1/# | # | #
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | EM Facilities | 15154 | Result | 6 | 33.5 |  | 33.5 | [16 empty] | -27.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | EM Facilities | 15154 | ADMIN | 4 | 19 |  | 19 | [16 empty] | -15
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | EM Facilities | 15154 | ENVPLN | 2 | 11.5 |  | 11.5 | [16 empty] | -9.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | EM Facilities | 15154 | ENVSVC |  | 3 |  | 3 | [16 empty] | -3
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | EM Projects | 15240 | BIOCUL |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 6 |  | 6 | [16 empty] | -6
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Rights | 11929 | Result |  | 3 |  | 3 | [16 empty] | -3
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Rights | 11929 | ACQLIT |  | 2 |  | 2 | [16 empty] | -2
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Surveying | 12577 | Result | 3 | 2.75 |  | 2.75 | [16 empty] | 0.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Surveying | 12577 | ADM-OT | 1 | 1 |  | 1
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Land Surveying | 12577 | LNDENG |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC | 1 | 20.25 |  | 20.25 | [16 empty] | -19.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | North Distribution Control Center | 11890 | MO | 10 | [19 empty] | 10
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 67 | 3 |  | 3 | [16 empty] | 64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | SI Restoration | 14110 | FLDSVC | 12 | [19 empty] | 12
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | ST Gas Construction | 11938 | CONSTR |  | 16 |  | 16 | [16 empty] | -16
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Result |  |  | 193 | 374.5 |  | 374.5 |  | 1 | 7.25 | 1 | [8 empty] | 9.25 |  |  |  | -181.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | PGE1/# | # | #
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Distribution Line Tech - SCADA | 15275 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Distribution Line Tech - SCADA | 15275 | MO |  | 17.75 |  | 17.75 | [16 empty] | -17.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Distribution Line Tech - SCADA | 15275 | MO-DT |  | 3.75 |  | 3.75 | [16 empty] | -3.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 6 |  | 6 | [16 empty] | -6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Distribution Operations Engineering | 14521 | ENGMAP |  | 6 |  | 6 | [16 empty] | -6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | EM Facilities | 15154 | Result | 16 | 35.25 |  | 35.25 |  |  | 0.25 | [9 empty] | 0.25 |  |  |  | -19.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | EM Facilities | 15154 | ADMIN | 12 | 31 |  | 31 |  |  | 0.25 | [9 empty] | 0.25 |  |  |  | -19
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | EM Facilities | 15154 | ENVPLN | 3 | 3 |  | 3
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | EM Facilities | 15154 | ENVSVC | 1 | 1.25 |  | 1.25 | [16 empty] | -0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | EO&E E&T System Automation | 12148 | SCADSV |  | 18 |  | 18 | [16 empty] | -18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Gas Locate & Mark North | 15893 | Result |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Gas Locate & Mark North | 15893 | CNSTOT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Gas Locate & Mark North | 15893 | CONSTR |  | 4 |  | 4 | [16 empty] | -4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | IT Telecom Maintenance | 13892 | Result | 7 | 22.75 |  | 22.75 | [16 empty] | -15.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | IT Telecom Maintenance | 13892 | HRSOT | 3 | 5.75 |  | 5.75 | [16 empty] | -2.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | IT Telecom Maintenance | 13892 | HRSST | 4 | 17 |  | 17 | [16 empty] | -13
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 | [16 empty] | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | LCE-Planning & Ops | 15497 | ACTSVC | 4 | 4 |  | 4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | North Distribution Control Center | 11890 | Result | 74 | 110.75 |  | 110.75 | [16 empty] | -36.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | North Distribution Control Center | 11890 | MO | 73 | 59 |  | 59 | [16 empty] | 14
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | North Distribution Control Center | 11890 | MO-DT | 1 | 41 |  | 41 | [16 empty] | -40
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | North Distribution Control Center | 11890 | MO-OT |  | 10.75 |  | 10.75 | [16 empty] | -10.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | NV Electric Construction | 11894 | APRNST | 4 | [19 empty] | 4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Operations Systems | 10484 | OPERSV |  | 4 |  | 4 | [16 empty] | -4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Project Management & Controls | 14182 | ENGMAP |  | 7 |  | 7 |  | 1 | 5 | 1 | [8 empty] | 7 |  |  |  | -7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Reliability Planning | 13549 | Result | 7 | 23 |  | 23 |  |  | 2 | [9 empty] | 2 |  |  |  | -16
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Reliability Planning | 13549 | ENGMAP | 7 | 22 |  | 22 |  |  | 2 | [9 empty] | 2 |  |  |  | -15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | SI Restoration | 14110 | Result | 81 | 73.75 |  | 73.75 | [16 empty] | 7.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | SI Restoration | 14110 | FLDSDT |  | 32 |  | 32 | [16 empty] | -32
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | SI Restoration | 14110 | FLDSOT |  | 24.5 |  | 24.5 | [16 empty] | -24.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | SI Restoration | 14110 | FLDSVC | 81 | 17.25 |  | 17.25 | [16 empty] | 63.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Substation Maintenance | 10472 | Result |  | 26 |  | 26 | [16 empty] | -26
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Substation Maintenance | 10472 | MO |  | 16 |  | 16 | [16 empty] | -16
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Substation Maintenance | 10472 | SWTCHO |  | 10 |  | 10 | [16 empty] | -10
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Result |  |  | 152 | 184 |  | 184 | 5 | 1 | 4.5 | [9 empty] | 10.5 |  |  |  | -32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | PGE1/# | # | #
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | EM Facilities | 15154 | Result | 48.5 | 52.75 |  | 52.75 | [16 empty] | -4.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | EM Facilities | 15154 | ADMIN | 47.5 | 46 |  | 46 | [16 empty] | 1.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | EM Facilities | 15154 | ENVPLN | 1 | 6.75 |  | 6.75 | [16 empty] | -5.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | EM Projects | 15240 | BIOCUL |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas Distribution Projects Contract PCC | 15448 | XCON02 | 1 | 1 |  | 1
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas Locate & Mark North | 15893 | Result |  | 7.5 |  | 7.5 | [16 empty] | -7.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas Locate & Mark North | 15893 | CNSTOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Gas Locate & Mark North | 15893 | CONSTR |  | 4 |  | 4 | [16 empty] | -4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Grid System Operations | 14052 | SWTCHO | 16 | [19 empty] | 16
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Acquisition | 12809 | ACQLIT |  | 8 |  | 8 | 1 |  | 1 | [9 empty] | 2 |  |  |  | -8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Rights | 11929 | Result |  | 45.5 |  | 45.5 | 4 | [11 empty] | 4 |  |  |  | -45.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Rights | 11929 | ACQLIT |  | 32.5 |  | 32.5 | 3.5 | [11 empty] | 3.5 |  |  |  | -32.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Rights | 11929 | LNDRTS |  | 13 |  | 13 | 0.5 | [11 empty] | 0.5 |  |  |  | -13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Surveying | 12577 | Result |  | 23 |  | 23 | [16 empty] | -23
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Surveying | 12577 | ADM-OT |  | 3.75 |  | 3.75 | [16 empty] | -3.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Surveying | 12577 | LNDENG |  | 19.25 |  | 19.25 | [16 empty] | -19.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | LCE-Planning & Ops | 15497 | ACTSVC | 6.5 | 13.75 |  | 13.75 | [16 empty] | -7.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | North Distribution Control Center | 11890 | Result | 37 | 7.5 |  | 7.5 | [16 empty] | 29.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | North Distribution Control Center | 11890 | MO | 37 | 5.25 |  | 5.25 | [16 empty] | 31.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | North Distribution Control Center | 11890 | MO-DT |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Permitting G2 and CH2M | 15993 | XCON02 |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Project Management & Controls | 14182 | ENGMAP |  | 4 |  | 4 |  | 1 | 3 | [9 empty] | 4 |  |  |  | -4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Reliability Planning | 13549 | ENGMAP | 2 | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | SI Restoration | 14110 | FLDSVC | 41 | [19 empty] | 41
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Result |  |  | 1160 | 2923.25 |  | 2923.25 | 549 | 518.5 | 1103.5 | 28 | [8 empty] | 2199 |  |  |  | -1763.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | PGE1/# | # | #
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Business Operations | 15495 | ACTSVC | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | EM Facilities | 15154 | Result | 127 | 18.25 |  | 18.25 | 2 |  | 1 | [9 empty] | 3 |  |  |  | 108.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | EM Facilities | 15154 | ADMIN | 6 | 16 |  | 16 | 2 | [11 empty] | 2 |  |  |  | -10
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | EM Facilities | 15154 | ENVPLN | 1 | 2.25 |  | 2.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -1.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | EM Facilities | 15154 | ENVSVC | 120 | [19 empty] | 120
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec NV North | 11830 | Result |  | 92.5 |  | 92.5 |  |  | 92.5 | [9 empty] | 92.5 |  |  |  | -92.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec NV North | 11830 | CNSTDT |  | 30 |  | 30 |  |  | 30 | [9 empty] | 30 |  |  |  | -30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec NV North | 11830 | CNSTOT |  | 15 |  | 15 |  |  | 15 | [9 empty] | 15 |  |  |  | -15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec NV North | 11830 | CONSTR |  | 47.5 |  | 47.5 |  |  | 47.5 | [9 empty] | 47.5 |  |  |  | -47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI North | 14632 | Result |  | 2494.5 |  | 2494.5 | 546 | 518.5 | 769.5 | [9 empty] | 1834 |  |  |  | -2494.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI North | 14632 | APRNOT
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI North | 14632 | CNSTDT |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI North | 14632 | CNSTOT |  | 274.5 |  | 274.5 | 48 | 48.5 | 87.5 | [9 empty] | 184 |  |  |  | -274.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI North | 14632 | CONSTR |  | 2218 |  | 2218 | 498 | 470 | 680 | [9 empty] | 1648 |  |  |  | -2218
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI South | 11834 | Result |  | 87.5 |  | 87.5 |  |  | 87.5 | [9 empty] | 87.5 |  |  |  | -87.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI South | 11834 | CNSTOT |  | 17.5 |  | 17.5 |  |  | 17.5 | [9 empty] | 17.5 |  |  |  | -17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | GC Elec SI South | 11834 | CONSTR |  | 70 |  | 70 |  |  | 70 | [9 empty] | 70 |  |  |  | -70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Land Rights | 11929 | LNDRTS | 255 | [19 empty] | 255
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 130 | 1 |  | 1 | [16 empty] | 129
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | LCE-Planning & Ops | 15497 | ACTSVC | 2 | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | North Distribution Control Center | 11890 | MO | 183 | [19 empty] | 183
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Project Management & Controls | 14182 | Result | 250 | 197 |  | 197 |  |  | 153 | 28 | [8 empty] | 181 |  |  |  | 53
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Project Management & Controls | 14182 | CONSTR | 16 | 16 |  | 16
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Project Management & Controls | 14182 | ENGMAP | 234 | 181 |  | 181 |  |  | 153 | 28 | [8 empty] | 181 |  |  |  | 53
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Reliability Planning | 13549 | Result | 9 | 9 |  | 9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Reliability Planning | 13549 | ENGMAP | 8 | 8 |  | 8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | SI Restoration | 14110 | FLDSVC | 183 | [19 empty] | 183
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 20 | 20 |  | 20
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Result |  |  | 4108 | 127.75 |  | 127.75 | 3 |  | 4 | [9 empty] | 7 |  |  |  | 3980.25
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | PGE1/# | # | #
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Business Operations | 15495 | ACTSVC | 7 | 2.25 |  | 2.25 | [16 empty] | 4.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Central Design North | 12974 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Central Design North | 12974 | EEST |  | 25.5 |  | 25.5 | [16 empty] | -25.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Central Design North | 12974 | EESTOT |  | 8 |  | 8 | [16 empty] | -8
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | EM Facilities | 15154 | Result | 100 | 25.5 |  | 25.5 | 2 |  | 2 | [9 empty] | 4 |  |  |  | 74.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | EM Facilities | 15154 | ADMIN | 32 | 20 |  | 20 | 2 |  | 1 | [9 empty] | 3 |  |  |  | 12
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | EM Facilities | 15154 | ENVPLN | 1 | 1.5 |  | 1.5 |  |  | 1 | [9 empty] | 1 |  |  |  | -0.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | EM Facilities | 15154 | ENVSVC | 67 | 4 |  | 4 | [16 empty] | 63
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Land Rights | 11929 | Result | 120 | 1.5 |  | 1.5 | [16 empty] | 118.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Land Rights | 11929 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Land Rights | 11929 | LNDRTS | 118 | [19 empty] | 118
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 55 | 5 |  | 5 | [16 empty] | 50
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | North Distribution Control Center | 11890 | MO | 32 | [19 empty] | 32
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Project Management & Controls | 14182 | Result | 3704 | 21 |  | 21 |  |  | 2 | [9 empty] | 2 |  |  |  | 3683
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Project Management & Controls | 14182 | CONSTR | 3576 | 19 |  | 19 | [16 empty] | 3557
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Project Management & Controls | 14182 | ENGMAP | 128 | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | 126
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Reliability Planning | 13549 | Result | 13 | 16 |  | 16 | [16 empty] | -3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Reliability Planning | 13549 | ENGMAP | 12 | 15 |  | 15 | [16 empty] | -3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | SI Restoration | 14110 | FLDSVC | 35 | [19 empty] | 35
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 41 | 21 |  | 21 | [16 empty] | 20
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Result |  |  | 3612 | 486.75 |  | 486.75 | 1 |  | 298.5 | 105.5 | [8 empty] | 405 |  |  |  | 3125.25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | PGE1/# | # | #
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Business Operations | 15495 | ACTSVC |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | CC Work Force Management | 11034 | MANAGE | 21 | 0.5 |  | 0.5 | [16 empty] | 20.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | EM Facilities | 15154 | Result | 54 | 18.25 |  | 18.25 |  |  | 4 | [9 empty] | 4 |  |  |  | 35.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | EM Facilities | 15154 | ADMIN | 34 | 13 |  | 13 |  |  | 3 | [9 empty] | 3 |  |  |  | 21
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | EM Facilities | 15154 | ENVPLN | 3 | 5.25 |  | 5.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -2.25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | EM Facilities | 15154 | ENVSVC | 17 | [19 empty] | 17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | GC Elec SI North | 14632 | Result |  | 353 |  | 353 |  |  | 248.5 | 104.5 | [8 empty] | 353 |  |  |  | -353
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | GC Elec SI North | 14632 | CNSTOT |  | 66 |  | 66 |  |  | 61.5 | 4.5 | [8 empty] | 66 |  |  |  | -66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | GC Elec SI North | 14632 | CONSTR |  | 287 |  | 287 |  |  | 187 | 100 | [8 empty] | 287 |  |  |  | -287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | GC Elec SI South | 11834 | CONSTR | 3040 | [19 empty] | 3040
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Acquisition | 12809 | ACQLIT |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Rights | 11929 | Result | 30 | 9.5 |  | 9.5 | [16 empty] | 20.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Rights | 11929 | ACQLIT | 30 | 7.5 |  | 7.5 | [16 empty] | 22.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Land Rights | 11929 | LNDRTS |  | 2 |  | 2 | [16 empty] | -2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 129 | 11 |  | 11 | [16 empty] | 118
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | North Distribution Control Center | 11890 | MO | 39 | [19 empty] | 39
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Outage Coordinators & Planners | 12690 | SWTCHO | 9 | [19 empty] | 9
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Project Management & Controls | 14182 | Result | 146 | 64 |  | 64 |  |  | 45 | 1 | [8 empty] | 46 |  |  |  | 82
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Project Management & Controls | 14182 | CONSTR | 18 | 62 |  | 62 |  |  | 44 | [9 empty] | 44 |  |  |  | -44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Project Management & Controls | 14182 | ENGMAP | 128 | 2 |  | 2 |  |  | 1 | 1 | [8 empty] | 2 |  |  |  | 126
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Reliability Planning | 13549 | Result | 81 | 5 |  | 5 | [16 empty] | 76
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Reliability Planning | 13549 | ENGMAP | 80 | 4 |  | 4 | [16 empty] | 76
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | SI Restoration | 14110 | FLDSVC | 43 | [19 empty] | 43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 19 | 19 |  | 19
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Result |  |  | 3409 | 2547.75 |  | 2547.75 | 367 | 229 | 783 | 218 | [8 empty] | 1597 |  |  |  | 861.25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | PGE1/# | # | #
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Business Operations | 15495 | ACTSVC |  | 1.75 |  | 1.75 | [16 empty] | -1.75
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | EM Facilities | 15154 | Result | 40 | 24.5 |  | 24.5 |  |  | 1 | 1 | [8 empty] | 2 |  |  |  | 15.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | EM Facilities | 15154 | ADMIN | 30 | 19 |  | 19 |  |  | 1 | [9 empty] | 1 |  |  |  | 11
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | EM Facilities | 15154 | ENVPLN | 10 | 1.5 |  | 1.5 |  |  |  | 1 | [8 empty] | 1 |  |  |  | 8.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | EM Facilities | 15154 | ENVSVC |  | 4 |  | 4 | [16 empty] | -4
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | GC Elec SI South | 11834 | Result |  | 1998.5 |  | 1998.5 | 250 | 70 | 759 | 215 | [8 empty] | 1294 |  |  |  | -1998.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | GC Elec SI South | 11834 | CNSTDT |  | 23.5 |  | 23.5 |  |  | 21.5 | 2 | [8 empty] | 23.5 |  |  |  | -23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | GC Elec SI South | 11834 | CNSTOT |  | 190.5 |  | 190.5 |  | 30 | 137.5 | 23 | [8 empty] | 190.5 |  |  |  | -190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | GC Elec SI South | 11834 | CONSTR |  | 1784.5 |  | 1784.5 | 250 | 40 | 600 | 190 | [8 empty] | 1080 |  |  |  | -1784.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Land Rights | 11929 | ACQLIT | 32 | 0.5 |  | 0.5 | [16 empty] | 31.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 130 | 8 |  | 8 | [16 empty] | 122
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | North Distribution Control Center | 11890 | MO | 183 | [19 empty] | 183
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Project Management & Controls | 14182 | Result | 2704 | 486.5 |  | 486.5 | 116 | 159 | 23 | 2 | [8 empty] | 300 |  |  |  | 2217.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Project Management & Controls | 14182 | CNSTOT | 9 | 25 |  | 25 |  | 7 | [10 empty] | 7 |  |  |  | -16
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Project Management & Controls | 14182 | CONSTR | 2567 | 37 |  | 37 |  |  | 18 | [9 empty] | 18 |  |  |  | 2530
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Project Management & Controls | 14182 | ENGMAP | 128 | 424.5 |  | 424.5 | 116 | 152 | 5 | 2 | [8 empty] | 275 |  |  |  | -296.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Reliability Planning | 13549 | Result | 89 | 5 |  | 5 | [16 empty] | 84
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Reliability Planning | 13549 | ENGMAP | 88 | 4 |  | 4 | [16 empty] | 84
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Safety Infrastructure Protection Team | 15937 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | SI Restoration | 14110 | FLDSVC | 183 | [19 empty] | 183
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Substation Maintenance | 10472 | SWTCHO | 8 | [19 empty] | 8
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 40 | 21 |  | 21 | [16 empty] | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Result |  |  | 5549 | 3617 |  | 3617 | 437.5 | 565 | 677.5 | 107 | [8 empty] | 1787 |  |  |  | 1932
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | PGE1/# | # | #
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Business Operations | 15495 | ACTSVC | 1 | 1.75 |  | 1.75 | [16 empty] | -0.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Central Design Contract Estimating | 11714 | EEST |  | 10 |  | 10 | 2 | 2 | 4 | [9 empty] | 8 |  |  |  | -10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Facilities | 15154 | Result | 54 | 45.25 |  | 45.25 |  | 8 | 12 | [9 empty] | 20 |  |  |  | 8.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Facilities | 15154 | ADMIN | 13 | 38 |  | 38 |  | 8 | 11 | [9 empty] | 19 |  |  |  | -25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Facilities | 15154 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Facilities | 15154 | ENVPLN | 1 | 6.25 |  | 6.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -5.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Facilities | 15154 | ENVSVC | 40 | [19 empty] | 40
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | EM Projects | 15240 | BIOCUL | 2 | 2 |  | 2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Gas Locate & Mark North | 15893 | CONSTR |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Gas Locate & Mark South | 15288 | CONSTR | 20 | [19 empty] | 20
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec NV South | 15216 | Result |  | 91 |  | 91 | [16 empty] | -91
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec NV South | 15216 | CNSTDT |  | 7 |  | 7 | [16 empty] | -7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec NV South | 15216 | CNSTOT |  | 14 |  | 14 | [16 empty] | -14
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec NV South | 15216 | CONSTR |  | 70 |  | 70 | [16 empty] | -70
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec SI North | 14632 | Result | 5306 | 3146 |  | 3146 | 417.5 | 523 | 614.5 | 105 | [8 empty] | 1660 |  |  |  | 2160
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec SI North | 14632 | CNSTOT |  | 190 |  | 190 | 17.5 | 73 | 24.5 | 5 | [8 empty] | 120 |  |  |  | -190
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | GC Elec SI North | 14632 | CONSTR | 5306 | 2956 |  | 2956 | 400 | 450 | 590 | 100 | [8 empty] | 1540 |  |  |  | 2350
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Rights | 11929 | LNDRTS | 30 | 1.5 |  | 1.5 | [16 empty] | 28.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Surveying | 12577 | Result | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Land Surveying | 12577 | MNGNCC | 1 | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | LCE- Division Teams | 15789 | ACTSVC | 1 | 11 |  | 11 | 3 | 1 | 3 | [9 empty] | 7 |  |  |  | -10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | North Distribution Control Center | 11890 | MO | 43 | [19 empty] | 43
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Project Management & Controls | 14182 | Result | 18 | 275 |  | 275 | 15 | 31 | 42 | 2 | [8 empty] | 90 |  |  |  | -257
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Project Management & Controls | 14182 | CNSTOT |  | 10 |  | 10 | [16 empty] | -10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Project Management & Controls | 14182 | CONSTR | 18 | 229 |  | 229 | 15 | 30 | 36 | [9 empty] | 81 |  |  |  | -211
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Project Management & Controls | 14182 | ENGMAP |  | 36 |  | 36 |  | 1 | 6 | 2 | [8 empty] | 9 |  |  |  | -36
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Reliability Planning | 13549 | ENGMAP | 3 | 9 |  | 9 |  |  | 1 | [9 empty] | 1 |  |  |  | -6
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | SI Restoration | 14110 | FLDSVC | 47 | [19 empty] | 47
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | VP Elec Distribution Operations | 15443 | MANAGE | 22 | 22 |  | 22
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Result |  |  |  | 586 |  | 586 | [16 empty] | -586
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | PGE1/# | # | #
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | EM Facilities | 15154 | Result |  | 17 |  | 17 | [16 empty] | -17
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | EM Facilities | 15154 | ADMIN |  | 12 |  | 12 | [16 empty] | -12
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | EM Facilities | 15154 | ENVSVC |  | 5 |  | 5 | [16 empty] | -5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying | 12577 | Result |  | 545 |  | 545 | [16 empty] | -545
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying | 12577 | ACQLIT |  | 170 |  | 170 | [16 empty] | -170
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying | 12577 | ADM-OT |  | 34.5 |  | 34.5 | [16 empty] | -34.5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying | 12577 | LNDENG |  | 132.5 |  | 132.5 | [16 empty] | -132.5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Land Surveying | 12577 | LNDRTS |  | 208 |  | 208 | [16 empty] | -208
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | LCE- Division Teams | 15789 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | LCE-Planning & Ops | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Project Management & Controls | 14182 | CNSTOT |  | 4 |  | 4 | [16 empty] | -4
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 15 |  | 15 | [16 empty] | -15
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Result |  |  |  | 2832.75 |  | 2832.75 | 718.5 | 579.25 | 902.25 | 154 | [8 empty] | 2354 |  |  |  | -2832.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | PGE1/# | # | #
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Business Operations | 15495 | ACTSVC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Central Design Contract Estimating | 11714 | EEST |  | 20 |  | 20 | 13 |  | 7 | [9 empty] | 20 |  |  |  | -20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Central Design North | 12974 | Result |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Central Design North | 12974 | DSGNDT |  | 15 |  | 15 | [16 empty] | -15
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Central Design North | 12974 | DSGNOT |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | EM Facilities | 15154 | Result |  | 10.75 |  | 10.75 |  |  | 1 | [9 empty] | 1 |  |  |  | -10.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | EM Facilities | 15154 | ADMIN |  | 10 |  | 10 |  |  | 1 | [9 empty] | 1 |  |  |  | -10
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | EM Facilities | 15154 | ENVPLN |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Enterprise Public Works Coordination | 15449 | ANLYST |  | 3 |  | 3 | 1 | [11 empty] | 1 |  |  |  | -3
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | GC Elec SI South | 11834 | Result |  | 2720 |  | 2720 | 702.5 | 578.25 | 887.25 | 152 | [8 empty] | 2320 |  |  |  | -2720
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | GC Elec SI South | 11834 | APRNOT
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | GC Elec SI South | 11834 | CNSTDT |  | 95.5 |  | 95.5 |  | 70.25 | 25.25 | [9 empty] | 95.5 |  |  |  | -95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | GC Elec SI South | 11834 | CNSTOT |  | 637 |  | 637 | 68.5 | 98 | 263.5 | 67 | [8 empty] | 497 |  |  |  | -637
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | GC Elec SI South | 11834 | CONSTR |  | 1987.5 |  | 1987.5 | 634 | 410 | 598.5 | 85 | [8 empty] | 1727.5 |  |  |  | -1987.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Land Rights | 11929 | Result |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Land Rights | 11929 | ACQLIT |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | LCE- Division Teams | 15789 | ACTSVC |  | 7 |  | 7 | [16 empty] | -7
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | LCE-Planning & Ops | 15497 | ACTSVC |  | 11 |  | 11 | [16 empty] | -11
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Permitting G2 and CH2M | 15993 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Project Management & Controls | 14182 | ENGMAP |  | 12 |  | 12 |  | 1 | 5 | 2 | [8 empty] | 8 |  |  |  | -12
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Reliability Planning | 13549 | ENGMAP |  | 18 |  | 18 | 2 |  | 2 | [9 empty] | 4 |  |  |  | -18
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Result |  |  | 1845 | 115 |  | 115 |  | 1 | [10 empty] | 1 |  |  |  | 1730
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | PGE1/# | # | #
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Central Design Contract Estimating | 11714 | Result | 22 | 44.25 |  | 44.25 | [16 empty] | -22.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Central Design Contract Estimating | 11714 | EEST | 18 | 40.5 |  | 40.5 | [16 empty] | -22.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Central Design Contract Estimating | 11714 | EESTOT | 4 | 3.75 |  | 3.75 | [16 empty] | 0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | EM Facilities | 15154 | Result | 17 | 9.5 |  | 9.5 | [16 empty] | 7.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | EM Facilities | 15154 | ADMIN | 7 | 9 |  | 9 | [16 empty] | -2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | EM Facilities | 15154 | ENVPLN | 10 | 0.5 |  | 0.5 | [16 empty] | 9.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | EM Projects | 15240 | BIOCUL | 2 | 2 |  | 2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Gas Distribution Projects Contract PCC | 15448 | XCON02 | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | GC Elec SI South | 11834 | CONSTR | 1400 | [19 empty] | 1400
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Grid Operations System Dispatchers | 10481 | SWTCHO | 2 | [19 empty] | 2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Acquisition | 12809 | ACQLIT | 3 | 6.5 |  | 6.5 |  | 1 | [10 empty] | 1 |  |  |  | -3.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Rights | 11929 | LNDRTS | 1 | 1.25 |  | 1.25 | [16 empty] | -0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Surveying | 12577 | Result | 48 | 29.75 |  | 29.75 | [16 empty] | 18.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Surveying | 12577 | ADM-OT | 1 | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Surveying | 12577 | LNDENG | 47 | 28.75 |  | 28.75 | [16 empty] | 18.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | LCE- Division Teams | 15789 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | North Distribution Control Center | 11890 | MO | 19 | [19 empty] | 19
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Project Management & Controls | 14182 | ENGMAP | 128 | 4 |  | 4 | [16 empty] | 124
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Reliability Planning | 13549 | Result | 81 | 16 |  | 16 | [16 empty] | 65
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Reliability Planning | 13549 | ENGMAP | 7 | 15 |  | 15 | [16 empty] | -8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Reliability Planning | 13549 | ENGMPO | 74 | 1 |  | 1 | [16 empty] | 73
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | SI Restoration | 14110 | FLDSVC | 121 | [19 empty] | 121
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Result |  |  |  | 76.5 |  | 76.5 |  | 1 | 4 | 1 | [8 empty] | 6 |  |  |  | -76.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | PGE1/# | # | #
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Central Design North | 12974 | EESTOT |  | 2 |  | 2 | [16 empty] | -2
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | EM Facilities | 15154 | Result |  | 12 |  | 12 | [16 empty] | -12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | EM Facilities | 15154 | ADMIN |  | 11 |  | 11 | [16 empty] | -11
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Land Rights | 11929 | Result |  | 22 |  | 22 | [16 empty] | -22
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Land Rights | 11929 | ACQLIT |  | 9 |  | 9 | [16 empty] | -9
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Land Rights | 11929 | LNDRTS |  | 13 |  | 13 | [16 empty] | -13
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | LCE- Division Teams | 15789 | ACTSVC |  | 7 |  | 7 | [16 empty] | -7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | LCE-Planning & Ops | 15497 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Project Management & Controls | 14182 | Result |  | 13 |  | 13 |  | 1 | 4 | 1 | [8 empty] | 6 |  |  |  | -13
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Project Management & Controls | 14182 | CNSTOT |  | 7 |  | 7 | [16 empty] | -7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Project Management & Controls | 14182 | ENGMAP |  | 6 |  | 6 |  | 1 | 4 | 1 | [8 empty] | 6 |  |  |  | -6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Reliability Planning | 13549 | Result |  | 13 |  | 13 | [16 empty] | -13
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Reliability Planning | 13549 | ENGMAP |  | 12 |  | 12 | [16 empty] | -12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Result |  |  |  | 319 |  | 319 | 10 | 2 | [10 empty] | 12 |  |  |  | -319
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | PGE1/# | # | #
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Central Design North | 12974 | Result |  | 112.5 |  | 112.5 | [16 empty] | -112.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Central Design North | 12974 | EEST |  | 101.5 |  | 101.5 | [16 empty] | -101.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Central Design North | 12974 | EESTOT |  | 11 |  | 11 | [16 empty] | -11
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | EM Facilities | 15154 | Result |  | 94.75 |  | 94.75 | 6 | 2 | [10 empty] | 8 |  |  |  | -94.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | EM Facilities | 15154 | ADMIN |  | 77 |  | 77 | 6 | 2 | [10 empty] | 8 |  |  |  | -77
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | EM Facilities | 15154 | BIOCUL |  | 8 |  | 8 | [16 empty] | -8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | EM Facilities | 15154 | ENVPLN |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Enterprise Public Works Coordination | 15449 | Result |  | 5 |  | 5 | [16 empty] | -5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYST |  | 4 |  | 4 | [16 empty] | -4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Acquisition | 12809 | ACQLIT |  | 36.5 |  | 36.5 | 4 | [11 empty] | 4 |  |  |  | -36.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Rights | 11929 | ACQLIT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Surveying | 12577 | Result |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Surveying | 12577 | LNDENG |  | 12.75 |  | 12.75 | [16 empty] | -12.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Permitting G2 and CH2M | 15993 | XCON02 |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Project Management & Controls | 14182 | ENGMAP |  | 8 |  | 8 | [16 empty] | -8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Reliability Planning | 13549 | ENGMAP |  | 38 |  | 38 | [16 empty] | -38
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | T&D Construct Execution Ops | 15250 | MANAGE |  | 6 |  | 6 | [16 empty] | -6
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Result |  |  |  | 643.75 | 34 | 677.75 | 52 | 30.5 | 14.75 | 1 | [8 empty] | 98.25 | 34 |  |  | -677.75
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | PGE1/# | # | #
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Applied Technology Services | 12884 | TECHSV |  | 41.5 |  | 41.5 | 37.5 | 4 | [10 empty] | 41.5 |  |  |  | -41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Capacity Planning | 13550 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Central Design North | 12974 | GEST |  | 61 |  | 61 | [16 empty] | -61
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Distribution Operations Engineering | 14521 | ENGMAP |  |  | 34 | 34 | [13 empty] | 34 |  |  | -34
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | EM Facilities | 15154 | Result |  | 29.25 |  | 29.25 | 1.5 | [11 empty] | 1.5 |  |  |  | -29.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | EM Facilities | 15154 | ADM-OT |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | EM Facilities | 15154 | ADMIN |  | 1 |  | 1 | [16 empty] | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | EM Facilities | 15154 | ENVPLN |  | 27 |  | 27 | 1.5 | [11 empty] | 1.5 |  |  |  | -27
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | EM Projects | 15240 | ENVPLN |  | 3 |  | 3 | [16 empty] | -3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Enterprise Public Works Coordination | 15449 | Result |  | 23 |  | 23 | [16 empty] | -23
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 11 |  | 11 | [16 empty] | -11
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Enterprise Public Works Coordination | 15449 | ANLYST |  | 12 |  | 12 | [16 empty] | -12
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | GC & Contractor Construction Management | 15960 | CONSTR |  | 5 |  | 5 |  |  | 5 | [9 empty] | 5 |  |  |  | -5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | GC & Contractor Resource Management | 15976 | MANAGE |  | 5 |  | 5 | [16 empty] | -5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | GD Spvr Bishop Ranch | 15098 | ENGMAP |  | 2 |  | 2 |  | 2 | [10 empty] | 2 |  |  |  | -2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Integrated Public Affairs | 12245 | ADMIN |  | 21 |  | 21 | 6 | 15 | [10 empty] | 21 |  |  |  | -21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | IT Telecom Maintenance | 13892 | Result |  | 50.5 |  | 50.5 | [16 empty] | -50.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | IT Telecom Maintenance | 13892 | HRSOT |  | 30 |  | 30 | [16 empty] | -30
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | IT Telecom Maintenance | 13892 | HRSST |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Acquisition | 12809 | ACQLIT |  | 34.5 |  | 34.5 | 4 | [11 empty] | 4 |  |  |  | -34.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Rights | 11929 | ACQLIT |  | 1 |  | 1 | [16 empty] | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Surveying | 12577 | Result |  | 335 |  | 335 | 3 |  | 9.25 | [9 empty] | 12.25 |  |  |  | -335
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Surveying | 12577 | ACQLIT |  | 50 |  | 50 | 3 | [11 empty] | 3 |  |  |  | -50
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Surveying | 12577 | ADM-OT |  | 21.25 |  | 21.25 |  |  | 4.25 | [9 empty] | 4.25 |  |  |  | -21.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Land Surveying | 12577 | LNDENG |  | 263.75 |  | 263.75 |  |  | 5 | [9 empty] | 5 |  |  |  | -263.75
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Project Management & Controls | 14182 | Result |  | 11 |  | 11 |  | 9.5 | 0.5 | 1 | [8 empty] | 11 |  |  |  | -11
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  | 9 | [10 empty] | 9 |  |  |  | -9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Project Management & Controls | 14182 | ENGMAP |  | 2 |  | 2 |  | 0.5 | 0.5 | 1 | [8 empty] | 2 |  |  |  | -2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Reliability Planning | 13549 | ENGMAP |  | 19 |  | 19 | [16 empty] | -19
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Result |  |  |  | 1 |  | 1 | [16 empty] | -1
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | PGE1/# | # | #
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 1 |  | 1 | [16 empty] | -1
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Result |  |  |  | 3 |  | 3 | [16 empty] | -3
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | PGE1/# | # | #
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Gas Locate & Mark Bay Area | 15514 | CONSTR |  | 1 |  | 1 | [16 empty] | -1
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Result |  |  |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | PGE1/# | # | #
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Result |  |  |  | 4 |  | 4 | [16 empty] | -4
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | PGE1/# | # | #
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Central Design North | 12974 | DSGNOT |  | 1 |  | 1 | [16 empty] | -1
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Result |  |  |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | PGE1/# | # | #
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 2 |  | 2 | [16 empty] | -2
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Result |  |  |  | 38.75 |  | 38.75 | 7 | 17.75 | 4.5 | 7 | [8 empty] | 36.25 |  |  |  | -38.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | PGE1/# | # | #
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Central Design North | 12974 | EEST |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | EM Facilities | 15154 | Result |  | 12.5 |  | 12.5 | 2 |  | 3.5 | 7 | [8 empty] | 12.5 |  |  |  | -12.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | EM Facilities | 15154 | ADMIN |  | 7.5 |  | 7.5 |  |  | 3.5 | 4 | [8 empty] | 7.5 |  |  |  | -7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 5 |  | 5 | 2 |  |  | 3 | [8 empty] | 5 |  |  |  | -5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | EM Projects | 15240 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 2.5 |  | 2.5 | 2 | [11 empty] | 2 |  |  |  | -2.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 7.5 |  | 7.5 |  | 7.5 | [10 empty] | 7.5 |  |  |  | -7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Project Management & Controls | 14182 | Result |  | 10.5 |  | 10.5 |  | 9.5 | 1 | [9 empty] | 10.5 |  |  |  | -10.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  | 9 | [10 empty] | 9 |  |  |  | -9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Project Management & Controls | 14182 | ENGMAP |  | 1.5 |  | 1.5 |  | 0.5 | 1 | [9 empty] | 1.5 |  |  |  | -1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 1.75 |  | 1.75 |  | 0.75 | [10 empty] | 0.75 |  |  |  | -1.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Result |  |  |  | 44.75 |  | 44.75 | 10 | 25.25 | 1 | [9 empty] | 36.25 |  |  |  | -44.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | PGE1/# | # | #
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Central Design North | 12974 | EEST |  | 7 |  | 7 | 7 | [11 empty] | 7 |  |  |  | -7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | EM Facilities | 15154 | Result |  | 2 |  | 2 | 1 |  | 1 | [9 empty] | 2 |  |  |  | -2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | EM Facilities | 15154 | ADM-OT |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 2 |  | 2 | 2 | [11 empty] | 2 |  |  |  | -2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 3 | [10 empty] | 3 |  |  |  | -3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Reliability Planning | 13549 | Result |  | 29.75 |  | 29.75 |  | 21.25 | [10 empty] | 21.25 |  |  |  | -29.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 7.25 |  | 7.25 |  | 6.75 | [10 empty] | 6.75 |  |  |  | -7.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMPO |  | 22.5 |  | 22.5 |  | 14.5 | [10 empty] | 14.5 |  |  |  | -22.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Result |  |  |  | 44 |  | 44 | 29.5 | 5.5 | 8 | [9 empty] | 43 |  |  |  | -44
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | PGE1/# | # | #
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | EM Projects | 15240 | ENVPLN |  | 1.5 |  | 1.5 | 1.5 | [11 empty] | 1.5 |  |  |  | -1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Acquisition | 12809 | ACQLIT |  | 6.5 |  | 6.5 | 3 | 1.5 | 2 | [9 empty] | 6.5 |  |  |  | -6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Rights | 11929 | Result |  | 7 |  | 7 | 7 | [11 empty] | 7 |  |  |  | -7
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Rights | 11929 | ADM-OT |  | 4 |  | 4 | 4 | [11 empty] | 4 |  |  |  | -4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Rights | 11929 | LNDRTS |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Land Surveying | 12577 | LNDENG |  | 5 |  | 5 |  |  | 5 | [9 empty] | 5 |  |  |  | -5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Reliability Planning | 13549 | Result |  | 23 |  | 23 | 18 | 3 | 1 | [9 empty] | 22 |  |  |  | -23
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Reliability Planning | 13549 | ENGMAP |  | 20 |  | 20 | 15 | 3 | 1 | [9 empty] | 19 |  |  |  | -20
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Reliability Planning | 13549 | ENGMPO |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Result |  |  |  | 163.5 |  | 163.5 | 1 | 38.5 | 103 | 21 | [8 empty] | 163.5 |  |  |  | -163.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Surveying | 12577 | Result |  | 148.5 |  | 148.5 |  | 25 | 102.5 | 21 | [8 empty] | 148.5 |  |  |  | -148.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Surveying | 12577 | ADM-OT |  | 31.5 |  | 31.5 |  | 4 | 23.5 | 4 | [8 empty] | 31.5 |  |  |  | -31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 117 |  | 117 |  | 21 | 79 | 17 | [8 empty] | 117 |  |  |  | -117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Project Management & Controls | 14182 | ENG-OT |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Reliability Planning | 13549 | Result |  | 13 |  | 13 | 1 | 12 | [10 empty] | 13 |  |  |  | -13
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | 1 | 1 | [10 empty] | 2 |  |  |  | -2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMPO |  | 11 |  | 11 |  | 11 | [10 empty] | 11 |  |  |  | -11
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Result |  |  |  | 121.5 |  | 121.5 | 1.5 | 34 | 70 | 16 | [8 empty] | 121.5 |  |  |  | -121.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | EM Projects | 15240 | ENVPLN |  | 0.5 |  | 0.5 | 0.5 | [11 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Surveying | 12577 | Result |  | 112 |  | 112 |  | 26 | 70 | 16 | [8 empty] | 112 |  |  |  | -112
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Surveying | 12577 | ADM-OT |  | 19.5 |  | 19.5 |  | 2.5 | 16 | 1 | [8 empty] | 19.5 |  |  |  | -19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 92.5 |  | 92.5 |  | 23.5 | 54 | 15 | [8 empty] | 92.5 |  |  |  | -92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 7 |  | 7 | 1 | 6 | [10 empty] | 7 |  |  |  | -7
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Result |  |  |  | 29 |  | 29 |  | 12 | 17 | [9 empty] | 29 |  |  |  | -29
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | PGE1/# | # | #
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 20 |  | 20 |  | 3 | 17 | [9 empty] | 20 |  |  |  | -20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  | 9 | [10 empty] | 9 |  |  |  | -9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Result |  |  |  | 9 |  | 9 |  | 9 | [10 empty] | 9 |  |  |  | -9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | PGE1/# | # | #
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  | 9 | [10 empty] | 9 |  |  |  | -9
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Result |  |  |  | 50 |  | 50 |  | 6 | 42.5 | 1.5 | [8 empty] | 50 |  |  |  | -50
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | EM Facilities | 15154 | ENVPLN |  | 3.5 |  | 3.5 |  |  | 2 | 1.5 | [8 empty] | 3.5 |  |  |  | -3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Project Management & Controls | 14182 | CNSTOT |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Reliability Planning | 13549 | Result |  | 46 |  | 46 |  | 6 | 40 | [9 empty] | 46 |  |  |  | -46
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Reliability Planning | 13549 | ENGMAP |  | 32 |  | 32 |  |  | 32 | [9 empty] | 32 |  |  |  | -32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Reliability Planning | 13549 | ENGMPO |  | 14 |  | 14 |  | 6 | 8 | [9 empty] | 14 |  |  |  | -14
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Result |  |  |  | 5.5 |  | 5.5 |  |  | 5.5 | [9 empty] | 5.5 |  |  |  | -5.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | PGE1/# | # | #
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Central Design Contract Estimating | 11714 | EEST |  | 4.5 |  | 4.5 |  |  | 4.5 | [9 empty] | 4.5 |  |  |  | -4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Result |  |  |  | 4.75 |  | 4.75 |  | 1.5 | 3.25 | [9 empty] | 4.75 |  |  |  | -4.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | PGE1/# | # | #
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Land Surveying | 12577 | Result |  | 4.75 |  | 4.75 |  | 1.5 | 3.25 | [9 empty] | 4.75 |  |  |  | -4.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 1.75 |  | 1.75 |  |  | 1.75 | [9 empty] | 1.75 |  |  |  | -1.75
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Result |  |  |  | 4.5 |  | 4.5 |  | 1.5 | 3 | [9 empty] | 4.5 |  |  |  | -4.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | PGE1/# | # | #
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Land Surveying | 12577 | Result |  | 4.5 |  | 4.5 |  | 1.5 | 3 | [9 empty] | 4.5 |  |  |  | -4.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Land Surveying | 12577 | LNDENG |  | 1.5 |  | 1.5 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -1.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Result |  |  |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | PGE1/# | # | #
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Result |  |  |  | 6.75 |  | 6.75 |  | 1.5 | 5.25 | [9 empty] | 6.75 |  |  |  | -6.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | PGE1/# | # | #
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Central Design Contract Estimating | 11714 | EESTOT |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Land Surveying | 12577 | Result |  | 4.75 |  | 4.75 |  | 1.5 | 3.25 | [9 empty] | 4.75 |  |  |  | -4.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Land Surveying | 12577 | LNDENG |  | 1.75 |  | 1.75 |  |  | 1.75 | [9 empty] | 1.75 |  |  |  | -1.75

## PRJ001 - $$ Detail
Order | Order Text | WBS Element | Job Owner | User Status | Cost Element |  | Apr to Apr Plan Cost | Apr to Apr Actual Cost | Apr to Apr Var Cost | Apr to Apr Var Cost % | Apr to Apr Plan Hrs | Apr to Apr Actual Hrs | Apr to Apr Var Hrs | Apr to Apr Var Hrs %
Overall Result | [6 empty] | 1779655.11 | -223675.46 | 2003330.57 | 112.5685 | 4601 | 809.25 | 3791.75 | 82.4114
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 144.09 |  | 144.09 | 100
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 144.09 |  | 144.09 | 100
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Other Costs | PGE1ORD-OTHER | 144.09 |  | 144.09 | 100
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | Order Overheads | PGE1OVERHEAD | 144.09 |  | 144.09 | 100
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR | 144.09 |  | 144.09 | 100
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 |  | ESTS | AFUDC-Borrowed | 5590030 | 144.09 |  | 144.09 | 100
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 5000 | 17.41 | 4982.59 | 99.6518 |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5000 | 17.41 | 4982.59 | 99.6518 |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 5000 | 17.41 | 4982.59 | 99.6518 |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5000 | 17.41 | 4982.59 | 99.6518 |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Types | PGE1ACTVTYPES |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 7537.4 | 34.82 | 7502.58 | 99.538 |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 7537.4 | 34.82 | 7502.58 | 99.538 |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  | 34.82 | -34.82 |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  | 34.82 | -34.82 |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  | 34.82 | -34.82 |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 34.82 | -34.82 |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Environmental Planning & Permitting-Misc | 6603027 |  | 34.82 | -34.82 |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER | 2537.4 |  | 2537.4 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Order Overheads | PGE1OVERHEAD | 2537.4 |  | 2537.4 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR | 2537.4 |  | 2537.4 | 100
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | AFUDC-Borrowed | 5590030 | 2537.4 |  | 2537.4 | 100
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Order Financial Costs | PGE1ORDFIN |  | -782.84 | 782.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | -782.84 | 782.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Contract Total | PGE1CONTRACT |  | -782.84 | 782.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Consulting | PGE1CONSULTING |  | -32.84 | 32.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Consulting Services - Engineering | 5001230 |  | -32.84 | 32.84
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Other Contract | PGE1OTHCONTRAC |  | -750 | 750
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 |  | FICL | Environmental Contract | 5490015 |  | -750 | 750
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Financial Costs | PGE1ORDFIN | 132906.13 | -12698.1 | 145604.23 | 109.5542 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 132906.13 | -12698.1 | 145604.23 | 109.5542 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 38429.18 | 2861.52 | 35567.66 | 92.5538 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Types | PGE1ACTVTYPES | 38429.18 | 2861.52 | 35567.66 | 92.5538 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 38429.18 | 2861.52 | 35567.66 | 92.5538 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 38041.8 | 2861.52 | 35180.28 | 92.478 | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Construction | 6603001 | 38041.8 | 2680.2 | 35361.6 | 92.9546 | 470 | 36 | 434 | 92.3404
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Engineering/Mapping | 6603022 |  | 111.68 | -111.68 |  |  | 1.5 | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  | 69.64 | -69.64 |  |  | 1 | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 387.38 |  | 387.38 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Mapping | 6010077 | 387.38 |  | 387.38 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Contract Total | PGE1CONTRACT | 15000 | -15660.74 | 30660.74 | 204.4049
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Contract | PGE1OTHCONTRAC | 15000 | -15660.74 | 30660.74 | 204.4049
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Contracts | 5490000 | 15000 |  | 15000 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Electric Construction Contract | 5490001 |  | -3660.74 | 3660.74
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Traffic Control Contracts | 5490027 |  | -12000 | 12000
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 79476.95 | 101.12 | 79375.83 | 99.8728
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 101.12 | -101.12
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 101.12 | -101.12
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Cash Discount earned | 5006310 |  | -28.6 | 28.6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Order Overheads | PGE1OVERHEAD | 79476.95 |  | 79476.95 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Capitalized A&G | PGE1CAPAG | 14149.62 |  | 14149.62 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Capitalized A&G | 6010050 | 14149.62 |  | 14149.62 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Labor Overheads | PGE1LABOROH | 45421.25 |  | 45421.25 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 41261.41 |  | 41261.41 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Paid Time Off | 6010100 | 7739.64 |  | 7739.64 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Indirect Labor - Electric | 6010106 | 13027.49 |  | 13027.49 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 11790.07 |  | 11790.07 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Fleet OH - Elec | 6010125 | 8704.21 |  | 8704.21 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 4159.84 |  | 4159.84 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Building Service Overhead | 6010112 | 2653.69 |  | 2653.69 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | IT Device OH | 6010113 | 1506.15 |  | 1506.15 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Other Overhead | PGE1OTHEROH | 19906.08 |  | 19906.08 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Benefits OH | 6010120 | 14682.21 |  | 14682.21 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Payroll Taxes OH | 6010121 | 5223.87 |  | 5223.87 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Financial Costs | PGE1ORDFIN | 232432.8 | -12657.16 | 245089.96 | 105.4455 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 232432.8 | -12657.16 | 245089.96 | 105.4455 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 61251.35 | 8189.59 | 53061.76 | 86.6295 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Types | PGE1ACTVTYPES | 61251.35 | 8189.59 | 53061.76 | 86.6295 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 61251.35 | 8189.59 | 53061.76 | 86.6295 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 60705 | 8189.59 | 52515.41 | 86.5092 | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Construction | 6603001 | 60705 | 5405.8 | 55299.2 | 91.095 | 750 | 76 | 674 | 89.8667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Construction Overtime Services | 6603021 |  | 2676.92 | -2676.92 |  |  | 30 | -30
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Engineering/Mapping | 6603022 |  | 37.23 | -37.23 |  |  | 0.5 | -0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  | 69.64 | -69.64 |  |  | 1 | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 546.35 |  | 546.35 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Mapping | 6010077 | 546.35 |  | 546.35 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Total | PGE1MATTOTAL | 40110 |  | 40110 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material related expenses | PGE1MATERIAL | 35000 |  | 35000 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Poles, Insulators & Hardware Bushing & B | 5300180 | 35000 |  | 35000 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Burden | PGE1MATBURD | 5110 |  | 5110 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Material Burden | 6010000 | 5110 |  | 5110 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Contract Total | PGE1CONTRACT |  | -20846.75 | 20846.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Contract | PGE1OTHCONTRAC |  | -20846.75 | 20846.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Contracts | 5490000 |  | -18974.16 | 18974.16
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Electric Construction Contract | 5490001 |  | -480 | 480
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Environmental Contract | 5490015 |  | -1392.59 | 1392.59
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 131071.45 |  | 131071.45 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Order Overheads | PGE1OVERHEAD | 131071.45 |  | 131071.45 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Capitalized A&G | PGE1CAPAG | 22552.75 |  | 22552.75 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Capitalized A&G | 6010050 | 22552.75 |  | 22552.75 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Labor Overheads | PGE1LABOROH | 72662.6 |  | 72662.6 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 65765.57 |  | 65765.57 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Paid Time Off | 6010100 | 12336.02 |  | 12336.02 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Indirect Labor - Electric | 6010106 | 20764.21 |  | 20764.21 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 18791.91 |  | 18791.91 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Fleet OH - Elec | 6010125 | 13873.43 |  | 13873.43 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 6897.03 |  | 6897.03 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Building Service Overhead | 6010112 | 4399.83 |  | 4399.83 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | IT Device OH | 6010113 | 2497.2 |  | 2497.2 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Other Overhead | PGE1OTHEROH | 35856.1 |  | 35856.1 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Benefits OH | 6010120 | 24343.09 |  | 24343.09 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Payroll Taxes OH | 6010121 | 8661.19 |  | 8661.19 | 100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Minor Material OH | 6010122 | 2851.82 |  | 2851.82 | 100
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 5000 | 69.64 | 4930.36 | 98.6072 |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5000 | 69.64 | 4930.36 | 98.6072 |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  | 69.64 | -69.64 |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Types | PGE1ACTVTYPES |  | 69.64 | -69.64 |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  | 69.64 | -69.64 |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 69.64 | -69.64 |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  | 69.64 | -69.64 |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN |  | -4985 | 4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | -4985 | 4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Contract Total | PGE1CONTRACT |  | -4985 | 4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Other Contract | PGE1OTHCONTRAC |  | -4985 | 4985
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 |  | DOCC | Electric Construction Contract | 5490001 |  | -4985 | 4985
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 5882.74 | 17.41 | 5865.33 | 99.704 |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5882.74 | 17.41 | 5865.33 | 99.704 |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Type Total | PGE1ACTV-TOT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Types | PGE1ACTVTYPES |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Activity Types - Internal | PGE1ACTV-INT |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Environmental Planning & Permitting-Misc | 6603027 |  | 17.41 | -17.41 |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Other Costs | PGE1ORD-OTHER | 882.74 |  | 882.74 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Order Overheads | PGE1OVERHEAD | 882.74 |  | 882.74 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR | 882.74 |  | 882.74 | 100
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | AFUDC-Borrowed | 5590030 | 882.74 |  | 882.74 | 100
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Order Financial Costs | PGE1ORDFIN |  | -1234.7 | 1234.7 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | -1234.7 | 1234.7 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Type Total | PGE1ACTV-TOT |  | 74.45 | -74.45 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Types | PGE1ACTVTYPES |  | 74.45 | -74.45 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Activity Types - Internal | PGE1ACTV-INT |  | 74.45 | -74.45 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 74.45 | -74.45 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Engineering/Mapping | 6603022 |  | 74.45 | -74.45 |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Order Other Costs | PGE1ORD-OTHER |  | -1309.15 | 1309.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Other Cost Elements | PGE1OTHERCE |  | -1309.15 | 1309.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | -1309.15 | 1309.15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Cash Discount earned | 5006310 |  | -1309.15 | 1309.15
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Order Financial Costs | PGE1ORDFIN |  | -20 | 20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | -20 | 20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Order Other Costs | PGE1ORD-OTHER |  | -20 | 20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Other Cost Elements | PGE1OTHERCE |  | -20 | 20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | -20 | 20
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 |  | FICL | Land Acquisition Services | 5501093 |  | -20 | 20
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Financial Costs | PGE1ORDFIN | 79598.84 | -28967.15 | 108565.99 | 136.3914 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 79598.84 | -28967.15 | 108565.99 | 136.3914 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 20462.12 | 2084.61 | 18377.51 | 89.8123 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Types | PGE1ACTVTYPES | 20462.12 | 2084.61 | 18377.51 | 89.8123 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 20462.12 | 2084.61 | 18377.51 | 89.8123 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 20235 | 2084.61 | 18150.39 | 89.698 | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Construction | 6603001 | 20235 |  | 20235 | 100 | 250 |  | 250 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Engineering/Mapping | 6603022 |  | 2084.61 | -2084.61 |  |  | 28 | -28
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 227.12 |  | 227.12 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Mapping | 6010077 | 227.12 |  | 227.12 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Contract Total | PGE1CONTRACT | 15000 | -31181.48 | 46181.48 | 307.8765
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Contract | PGE1OTHCONTRAC | 15000 | -31181.48 | 46181.48 | 307.8765
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Contracts | 5490000 | 15000 | -1150 | 16150 | 107.6667
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Electric Construction Contract | 5490001 |  | -22281.48 | 22281.48
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Environmental Contract | 5490015 |  | -250 | 250
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Traffic Control Contracts | 5490027 |  | -7500 | 7500
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 44136.72 | 129.72 | 44007 | 99.7061
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 129.72 | -129.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 129.72 | -129.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Order Overheads | PGE1OVERHEAD | 44136.72 |  | 44136.72 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Capitalized A&G | PGE1CAPAG | 7534.16 |  | 7534.16 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Capitalized A&G | 6010050 | 7534.16 |  | 7534.16 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Labor Overheads | PGE1LABOROH | 24185.14 |  | 24185.14 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 21970.18 |  | 21970.18 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Paid Time Off | 6010100 | 4121.07 |  | 4121.07 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Indirect Labor - Electric | 6010106 | 6936.66 |  | 6936.66 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 6277.78 |  | 6277.78 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Fleet OH - Elec | 6010125 | 4634.67 |  | 4634.67 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 2214.96 |  | 2214.96 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Building Service Overhead | 6010112 | 1413 |  | 1413 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | IT Device OH | 6010113 | 801.96 |  | 801.96 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Other Overhead | PGE1OTHEROH | 10599.27 |  | 10599.27 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Benefits OH | 6010120 | 7817.74 |  | 7817.74 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Payroll Taxes OH | 6010121 | 2781.53 |  | 2781.53 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | AFUDC Costs | PGE1AFUDCDIR | 1818.15 |  | 1818.15 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | AFUDC-Borrowed | 5590030 | 1818.15 |  | 1818.15 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Financial Costs | PGE1ORDFIN | 225640.37 | -40980.28 | 266620.65 | 118.1618
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 225640.37 | -40980.28 | 266620.65 | 118.1618
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Total | PGE1MATTOTAL | 203357.7 |  | 203357.7 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material related expenses | PGE1MATERIAL | 177450 |  | 177450 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Electrical Specialties | 5300140 | 177450 |  | 177450 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Burden | PGE1MATBURD | 25907.7 |  | 25907.7 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Material Burden | 6010000 | 25907.7 |  | 25907.7 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Contract Total | PGE1CONTRACT |  | -41110 | 41110
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Contract | PGE1OTHCONTRAC |  | -41110 | 41110
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 |  | -40860 | 40860
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Environmental Contract | 5490015 |  | -250 | 250
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 22282.67 | 129.72 | 22152.95 | 99.4178
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 129.72 | -129.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 129.72 | -129.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Order Overheads | PGE1OVERHEAD | 22282.67 |  | 22282.67 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Labor Overheads | PGE1LABOROH | 1352.39 |  | 1352.39 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 1352.39 |  | 1352.39 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Building Service Overhead | 6010112 | 862.73 |  | 862.73 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | IT Device OH | 6010113 | 489.66 |  | 489.66 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Other Overhead | PGE1OTHEROH | 20930.28 |  | 20930.28 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Benefits OH | 6010120 | 4773.24 |  | 4773.24 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Payroll Taxes OH | 6010121 | 1698.3 |  | 1698.3 | 100
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 |  | CONS | Minor Material OH | 6010122 | 14458.74 |  | 14458.74 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Financial Costs | PGE1ORDFIN | 213065.89 | -9592 | 222657.89 | 104.5019 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 213065.89 | -9592 | 222657.89 | 104.5019 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 61296.35 | 7290.04 | 54006.31 | 88.1069 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Types | PGE1ACTVTYPES | 61296.35 | 7290.04 | 54006.31 | 88.1069 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 61296.35 | 7290.04 | 54006.31 | 88.1069 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 60705 | 7290.04 | 53414.96 | 87.991 | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Construction | 6603001 | 60705 | 6814 | 53891 | 88.7752 | 750 | 100 | 650 | 86.6667
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Construction Overtime Services | 6603021 |  | 401.58 | -401.58 |  |  | 4.5 | -4.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Engineering/Mapping | 6603022 |  | 74.46 | -74.46 |  |  | 1 | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 591.35 |  | 591.35 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Mapping | 6010077 | 591.35 |  | 591.35 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material Total | PGE1MATTOTAL |  | -12119.17 | 12119.17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Material related expenses | PGE1MATERIAL |  | -12119.17 | 12119.17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Conductors, Cable & Wire Connectors | 5300120 |  | -12119.17 | 12119.17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Contract Total | PGE1CONTRACT | 25000 | -4892.59 | 29892.59 | 119.5704
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Contract | PGE1OTHCONTRAC | 25000 | -4892.59 | 29892.59 | 119.5704
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Contracts | 5490000 | 15000 |  | 15000 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Environmental Contract | 5490015 |  | -4892.59 | 4892.59
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Traffic Control Contracts | 5490027 | 10000 |  | 10000 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 126769.54 | 129.72 | 126639.82 | 99.8977
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 129.72 | -129.72
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 129.72 | -129.72
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Order Overheads | PGE1OVERHEAD | 126769.54 |  | 126769.54 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Capitalized A&G | PGE1CAPAG | 22569.32 |  | 22569.32 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Capitalized A&G | 6010050 | 22569.32 |  | 22569.32 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Labor Overheads | PGE1LABOROH | 72449.06 |  | 72449.06 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 65813.9 |  | 65813.9 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Paid Time Off | 6010100 | 12345.09 |  | 12345.09 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Indirect Labor - Electric | 6010106 | 20779.47 |  | 20779.47 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 18805.72 |  | 18805.72 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Fleet OH - Elec | 6010125 | 13883.62 |  | 13883.62 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 6635.16 |  | 6635.16 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Building Service Overhead | 6010112 | 4232.78 |  | 4232.78 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | IT Device OH | 6010113 | 2402.38 |  | 2402.38 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Other Overhead | PGE1OTHEROH | 31751.16 |  | 31751.16 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Benefits OH | 6010120 | 23418.83 |  | 23418.83 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Payroll Taxes OH | 6010121 | 8332.33 |  | 8332.33 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Financial Costs | PGE1ORDFIN | 230559.33 | 11897.7 | 218661.63 | 94.8396 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 230559.33 | 11897.7 | 218661.63 | 94.8396 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 73516.61 | 15457.11 | 58059.5 | 78.9747 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Types | PGE1ACTVTYPES | 73516.61 | 15457.11 | 58059.5 | 78.9747 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 73516.61 | 15457.11 | 58059.5 | 78.9747 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 72846 | 15457.11 | 57388.89 | 78.7811 | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction | 6603001 | 72846 | 12946.6 | 59899.4 | 82.2274 | 900 | 190 | 710 | 78.8889
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction Overtime Services | 6603021 |  | 2052.48 | -2052.48 |  |  | 23 | -23
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Engineering/Mapping | 6603022 |  | 148.91 | -148.91 |  |  | 2 | -2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Environmental Planning & Permitting-Misc | 6603027 |  | 69.64 | -69.64 |  |  | 1 | -1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Construction Doubletime Services | 6603180 |  | 239.48 | -239.48 |  |  | 2 | -2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 670.61 |  | 670.61 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Mapping | 6010077 | 670.61 |  | 670.61 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Contract Total | PGE1CONTRACT | 5000 | -3559.41 | 8559.41 | 171.1882
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Consulting | PGE1CONSULTING |  | -41.08 | 41.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Consulting Services - Engineering | 5001230 |  | -41.08 | 41.08
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Contract | PGE1OTHCONTRAC | 5000 | -3518.33 | 8518.33 | 170.3666
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Contracts | 5490000 | 5000 |  | 5000 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Electric Construction Contract | 5490001 |  | -660.74 | 660.74
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Environmental Contract | 5490015 |  | -1007.59 | 1007.59
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Traffic Control Contracts | 5490027 |  | -1850 | 1850
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 152042.72 |  | 152042.72 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Order Overheads | PGE1OVERHEAD | 152042.72 |  | 152042.72 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Capitalized A&G | PGE1CAPAG | 27068.82 |  | 27068.82 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Capitalized A&G | 6010050 | 27068.82 |  | 27068.82 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Labor Overheads | PGE1LABOROH | 86892.73 |  | 86892.73 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 78934.77 |  | 78934.77 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Paid Time Off | 6010100 | 14806.24 |  | 14806.24 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Indirect Labor - Electric | 6010106 | 24922.13 |  | 24922.13 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 22554.89 |  | 22554.89 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Fleet OH - Elec | 6010125 | 16651.51 |  | 16651.51 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 7957.96 |  | 7957.96 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Building Service Overhead | 6010112 | 5076.63 |  | 5076.63 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | IT Device OH | 6010113 | 2881.33 |  | 2881.33 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Other Overhead | PGE1OTHEROH | 38081.17 |  | 38081.17 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Benefits OH | 6010120 | 28087.67 |  | 28087.67 | 100
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Payroll Taxes OH | 6010121 | 9993.5 |  | 9993.5 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Financial Costs | PGE1ORDFIN | 240651.4 | -18509.84 | 259161.24 | 107.6916 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 240651.4 | -18509.84 | 259161.24 | 107.6916 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 73546.61 | 7409.11 | 66137.5 | 89.926 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Types | PGE1ACTVTYPES | 73546.61 | 7409.11 | 66137.5 | 89.926 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 73546.61 | 7409.11 | 66137.5 | 89.926 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 72846 | 7409.11 | 65436.89 | 89.8291 | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction | 6603001 | 72846 | 6814 | 66032 | 90.646 | 900 | 100 | 800 | 88.8889
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Construction Overtime Services | 6603021 |  | 446.2 | -446.2 |  |  | 5 | -5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Engineering/Mapping | 6603022 |  | 148.91 | -148.91 |  |  | 2 | -2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 700.61 |  | 700.61 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Mapping | 6010077 | 700.61 |  | 700.61 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Contract Total | PGE1CONTRACT | 15000 | -26048.67 | 41048.67 | 273.6578
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Consulting | PGE1CONSULTING |  | -41.08 | 41.08
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Consulting Services - Engineering | 5001230 |  | -41.08 | 41.08
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Contract | PGE1OTHCONTRAC | 15000 | -26007.59 | 41007.59 | 273.3839
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Contracts | 5490000 | 15000 |  | 15000 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Electric Construction Contract | 5490001 |  | -25000 | 25000
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Environmental Contract | 5490015 |  | -1007.59 | 1007.59
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 152104.79 | 129.72 | 151975.07 | 99.9147
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 129.72 | -129.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 129.72 | -129.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Order Overheads | PGE1OVERHEAD | 152104.79 |  | 152104.79 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Capitalized A&G | PGE1CAPAG | 27079.86 |  | 27079.86 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Capitalized A&G | 6010050 | 27079.86 |  | 27079.86 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Labor Overheads | PGE1LABOROH | 86928.21 |  | 86928.21 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 78966.99 |  | 78966.99 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Paid Time Off | 6010100 | 14812.28 |  | 14812.28 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Indirect Labor - Electric | 6010106 | 24932.3 |  | 24932.3 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 22564.1 |  | 22564.1 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Fleet OH - Elec | 6010125 | 16658.31 |  | 16658.31 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 7961.22 |  | 7961.22 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Building Service Overhead | 6010112 | 5078.71 |  | 5078.71 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | IT Device OH | 6010113 | 2882.51 |  | 2882.51 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Other Overhead | PGE1OTHEROH | 38096.72 |  | 38096.72 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Benefits OH | 6010120 | 28099.14 |  | 28099.14 | 100
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Payroll Taxes OH | 6010121 | 9997.58 |  | 9997.58 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 524.3 |  | 524.3 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 524.3 |  | 524.3 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Other Costs | PGE1ORD-OTHER | 524.3 |  | 524.3 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | Order Overheads | PGE1OVERHEAD | 524.3 |  | 524.3 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR | 524.3 |  | 524.3 | 100
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 |  | ESTS | AFUDC-Borrowed | 5590030 | 524.3 |  | 524.3 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Financial Costs | PGE1ORDFIN | 122848.72 | 16396.82 | 106451.9 | 86.6528 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 122848.72 | 16396.82 | 106451.9 | 86.6528 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Type Total | PGE1ACTV-TOT | 36780.81 | 11919.23 | 24861.58 | 67.5939 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Types | PGE1ACTVTYPES | 36780.81 | 11919.23 | 24861.58 | 67.5939 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Activity Types - Internal | PGE1ACTV-INT | 36780.81 | 11919.23 | 24861.58 | 67.5939 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 36423 | 11919.23 | 24503.77 | 67.2755 | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction | 6603001 | 36423 | 5791.9 | 30631.1 | 84.0982 | 450 | 85 | 365 | 81.1111
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Construction Overtime Services | 6603021 |  | 5978.42 | -5978.42 |  |  | 67 | -67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Engineering/Mapping | 6603022 |  | 148.91 | -148.91 |  |  | 2 | -2
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 357.81 |  | 357.81 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Mapping | 6010077 | 357.81 |  | 357.81 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Contract Total | PGE1CONTRACT | 10000 | 4416.92 | 5583.08 | 55.8308
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Contract | PGE1OTHCONTRAC | 10000 | 4416.92 | 5583.08 | 55.8308
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Contracts | 5490000 | 10000 | 1095.27 | 8904.73 | 89.0473
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Electric Construction Contract | 5490001 |  | 2189.65 | -2189.65
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Traffic Control Contracts | 5490027 |  | 1132 | -1132
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 76067.91 | 60.67 | 76007.24 | 99.9202
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Cost Elements | PGE1OTHERCE |  | 60.67 | -60.67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | 60.67 | -60.67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Cash Discount earned | 5006310 |  | -69.05 | 69.05
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Permits/Fees | 5501090 |  | 129.72 | -129.72
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Order Overheads | PGE1OVERHEAD | 76067.91 |  | 76067.91 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Capitalized A&G | PGE1CAPAG | 13542.7 |  | 13542.7 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Capitalized A&G | 6010050 | 13542.7 |  | 13542.7 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Labor Overheads | PGE1LABOROH | 43472.97 |  | 43472.97 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 39491.56 |  | 39491.56 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Paid Time Off | 6010100 | 7407.65 |  | 7407.65 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Indirect Labor - Electric | 6010106 | 12468.7 |  | 12468.7 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Operation Mgmt & Support - Electric | 6010114 | 11284.36 |  | 11284.36 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Fleet OH - Elec | 6010125 | 8330.85 |  | 8330.85 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 3981.41 |  | 3981.41 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Building Service Overhead | 6010112 | 2539.87 |  | 2539.87 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | IT Device OH | 6010113 | 1441.54 |  | 1441.54 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Other Overhead | PGE1OTHEROH | 19052.24 |  | 19052.24 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Benefits OH | 6010120 | 14052.43 |  | 14052.43 | 100
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Payroll Taxes OH | 6010121 | 4999.81 |  | 4999.81 | 100
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Order Financial Costs | PGE1ORDFIN |  | -20 | 20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | -20 | 20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Order Other Costs | PGE1ORD-OTHER |  | -20 | 20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Other Cost Elements | PGE1OTHERCE |  | -20 | 20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | -20 | 20
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 |  | PEND | Land Acquisition Services | 5501093 |  | -20 | 20
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Financial Costs | PGE1ORDFIN | 28440.09 | 74.45 | 28365.64 | 99.7382 |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 28440.09 | 74.45 | 28365.64 | 99.7382 |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Type Total | PGE1ACTV-TOT |  | 74.45 | -74.45 |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Types | PGE1ACTVTYPES |  | 74.45 | -74.45 |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Activity Types - Internal | PGE1ACTV-INT |  | 74.45 | -74.45 |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 74.45 | -74.45 |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Engineering/Mapping | 6603022 |  | 74.45 | -74.45 |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Other Costs | PGE1ORD-OTHER | 28440.09 |  | 28440.09 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Other Cost Elements | PGE1OTHERCE | 28281 |  | 28281 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 | 28281 |  | 28281 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044 | 28281 |  | 28281 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Order Overheads | PGE1OVERHEAD | 159.09 |  | 159.09 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | AFUDC Costs | PGE1AFUDCDIR | 159.09 |  | 159.09 | 100
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | AFUDC-Borrowed | 5590030 | 159.09 |  | 159.09 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 260.02 |  | 260.02 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 260.02 |  | 260.02 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER | 260.02 |  | 260.02 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | Order Overheads | PGE1OVERHEAD | 260.02 |  | 260.02 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR | 260.02 |  | 260.02 | 100
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 |  | PEND | AFUDC-Borrowed | 5590030 | 260.02 |  | 260.02 | 100
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Financial Costs | PGE1ORDFIN | 10607.29 | 21779.46 | -11172.17 | -105.3254 |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 10607.29 | 21779.46 | -11172.17 | -105.3254 |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Type Total | PGE1ACTV-TOT |  | 74.46 | -74.46 |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Types | PGE1ACTVTYPES |  | 74.46 | -74.46 |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Activity Types - Internal | PGE1ACTV-INT |  | 74.46 | -74.46 |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 74.46 | -74.46 |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Engineering/Mapping | 6603022 |  | 74.46 | -74.46 |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Contract Total | PGE1CONTRACT | 10000 | 21705 | -11705 | -117.05
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Other Contract | PGE1OTHCONTRAC | 10000 | 21705 | -11705 | -117.05
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Contracts | 5490000 |  | 21905 | -21905
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 10000 | -200 | 10200 | 102
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Other Costs | PGE1ORD-OTHER | 607.29 |  | 607.29 | 100
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Order Overheads | PGE1OVERHEAD | 607.29 |  | 607.29 | 100
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | AFUDC Costs | PGE1AFUDCDIR | 607.29 |  | 607.29 | 100
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | AFUDC-Borrowed | 5590030 | 607.29 |  | 607.29 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 2.49 |  | 2.49 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2.49 |  | 2.49 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Other Costs | PGE1ORD-OTHER | 2.49 |  | 2.49 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | Order Overheads | PGE1OVERHEAD | 2.49 |  | 2.49 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR | 2.49 |  | 2.49 | 100
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 |  | ESTS | AFUDC-Borrowed | 5590030 | 2.49 |  | 2.49 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 0.82 |  | 0.82 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 0.82 |  | 0.82 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 0.82 |  | 0.82 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | Order Overheads | PGE1OVERHEAD | 0.82 |  | 0.82 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR | 0.82 |  | 0.82 | 100
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 |  | UNSE | AFUDC-Borrowed | 5590030 | 0.82 |  | 0.82 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 2.43 |  | 2.43 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 2.43 |  | 2.43 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 2.43 |  | 2.43 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | Order Overheads | PGE1OVERHEAD | 2.43 |  | 2.43 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR | 2.43 |  | 2.43 | 100
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 |  | UNSE | AFUDC-Borrowed | 5590030 | 2.43 |  | 2.43 | 100
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 487.48 | -487.48 |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Administration | 6603000 |  | 278.56 | -278.56 |  |  | 4 | -4
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  | 208.92 | -208.92 |  |  | 3 | -3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 15150 | -24570 | 39720 | 262.1782
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 15150 | -24570 | 39720 | 262.1782
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 15150 | -24570 | 39720 | 262.1782
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 15150 | -24570 | 39720 | 262.1782
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 15150 | -24570 | 39720 | 262.1782
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Order Financial Costs | PGE1ORDFIN | 10000 |  | 10000 | 100
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 10000 |  | 10000 | 100
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Contract Total | PGE1CONTRACT | 10000 |  | 10000 | 100
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Other Contract | PGE1OTHCONTRAC | 10000 |  | 10000 | 100
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 |  | ADER | Contracts | 5490000 | 10000 |  | 10000 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 20773.47 | 1840.7 | 18932.77 | 91.1392 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 20773.47 | 1840.7 | 18932.77 | 91.1392 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT | 3977.81 | 1453.64 | 2524.17 | 63.4563 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES | 3977.81 | 1453.64 | 2524.17 | 63.4563 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT | 3977.81 | 1453.64 | 2524.17 | 63.4563 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 3977.81 | 1453.64 | 2524.17 | 63.4563 | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 | 3977.81 | 1101.6 | 2876.21 | 72.3064 | 61 | 17 | 44 | 72.1311
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Administrative Services - OT | 6603150 |  | 352.04 | -352.04 |  |  | 4 | -4
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 10000 |  | 10000 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 10000 |  | 10000 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 10000 |  | 10000 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 6795.66 | 387.06 | 6408.6 | 94.3043
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Employee Related | PGE1EMPLREL |  | 387.06 | -387.06
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Travel / Lodging | PGE1TRVL-LODGE |  | 327.44 | -327.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Lodging | 5091114 |  | 327.44 | -327.44
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Meals | PGE1MEALS-EXP |  | 59.62 | -59.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Meals Expense | 5091100 |  | 59.62 | -59.62
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD | 6795.66 |  | 6795.66 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG | 1464.63 |  | 1464.63 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Capitalized A&G | 6010050 | 1464.63 |  | 1464.63 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH | 3414.95 |  | 3414.95 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 3048.19 |  | 3048.19 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Paid Time Off | 6010100 | 801.13 |  | 801.13 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 | 1405.36 |  | 1405.36 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 | 841.7 |  | 841.7 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 366.76 |  | 366.76 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Building Service Overhead | 6010112 | 233.97 |  | 233.97 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | IT Device OH | 6010113 | 132.79 |  | 132.79 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH | 1755.04 |  | 1755.04 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Benefits OH | 6010120 | 1294.47 |  | 1294.47 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Payroll Taxes OH | 6010121 | 460.57 |  | 460.57 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR | 161.04 |  | 161.04 | 100
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | AFUDC-Borrowed | 5590030 | 161.04 |  | 161.04 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 20786.41 | 1453.85 | 19332.56 | 93.0058 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 20786.41 | 1453.85 | 19332.56 | 93.0058 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Type Total | PGE1ACTV-TOT | 4043.02 | 1060.01 | 2983.01 | 73.7817 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Types | PGE1ACTVTYPES | 4043.02 | 1060.01 | 2983.01 | 73.7817 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT | 4043.02 | 1060.01 | 2983.01 | 73.7817 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 4043.02 | 1060.01 | 2983.01 | 73.7817 | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 | 3977.81 | 972 | 3005.81 | 75.5644 | 61 | 15 | 46 | 75.4098
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Administrative Services - OT | 6603150 | 65.21 | 88.01 | -22.8 | -34.964 | 1 | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Contract Total | PGE1CONTRACT | 10000 |  | 10000 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 10000 |  | 10000 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 10000 |  | 10000 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 6743.39 | 393.84 | 6349.55 | 94.1596
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Cost Elements | PGE1OTHERCE |  | -21.62 | 21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1 |  | -21.62 | 21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Expenses | 5591000 |  | -21.62 | 21.62
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Employee Related | PGE1EMPLREL |  | 415.46 | -415.46
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Travel / Lodging | PGE1TRVL-LODGE |  | 348.58 | -348.58
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Lodging | 5091114 |  | 348.58 | -348.58
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Meals | PGE1MEALS-EXP |  | 66.88 | -66.88
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Meals Expense | 5091100 |  | 66.88 | -66.88
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Order Overheads | PGE1OVERHEAD | 6743.39 |  | 6743.39 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Capitalized A&G | PGE1CAPAG | 1488.64 |  | 1488.64 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Capitalized A&G | 6010050 | 1488.64 |  | 1488.64 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Labor Overheads | PGE1LABOROH | 3470.93 |  | 3470.93 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 3098.16 |  | 3098.16 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Paid Time Off | 6010100 | 814.26 |  | 814.26 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Indirect Labor - Environmental Land | 6010108 | 1428.4 |  | 1428.4 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 | 855.5 |  | 855.5 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 372.77 |  | 372.77 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Building Service Overhead | 6010112 | 237.8 |  | 237.8 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | IT Device OH | 6010113 | 134.97 |  | 134.97 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Other Overhead | PGE1OTHEROH | 1783.82 |  | 1783.82 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Benefits OH | 6010120 | 1315.69 |  | 1315.69 | 100
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Payroll Taxes OH | 6010121 | 468.13 |  | 468.13 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 5733.88 |  | 5733.88 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5733.88 |  | 5733.88 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Type Total | PGE1ACTV-TOT | 260.84 |  | 260.84 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Types | PGE1ACTVTYPES | 260.84 |  | 260.84 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT | 260.84 |  | 260.84 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 260.84 |  | 260.84 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059 | 260.84 |  | 260.84 | 100 | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 473.04 |  | 473.04 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Order Overheads | PGE1OVERHEAD | 473.04 |  | 473.04 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Capitalized A&G | PGE1CAPAG | 96.04 |  | 96.04 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Capitalized A&G | 6010050 | 96.04 |  | 96.04 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Labor Overheads | PGE1LABOROH | 223.92 |  | 223.92 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 199.87 |  | 199.87 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Paid Time Off | 6010100 | 52.53 |  | 52.53 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Indirect Labor - Environmental Land | 6010108 | 92.15 |  | 92.15 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Operation Mgmt & Support - Environ Land | 6010116 | 55.19 |  | 55.19 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 24.05 |  | 24.05 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Building Service Overhead | 6010112 | 15.35 |  | 15.35 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | IT Device OH | 6010113 | 8.7 |  | 8.7 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Other Overhead | PGE1OTHEROH | 115.07 |  | 115.07 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Benefits OH | 6010120 | 84.87 |  | 84.87 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Payroll Taxes OH | 6010121 | 30.2 |  | 30.2 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR | 38.01 |  | 38.01 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | AFUDC-Borrowed | 5590030 | 38.01 |  | 38.01 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 5966.7 |  | 5966.7 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 5966.7 |  | 5966.7 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Type Total | PGE1ACTV-TOT | 306.49 |  | 306.49 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Types | PGE1ACTVTYPES | 306.49 |  | 306.49 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT | 306.49 |  | 306.49 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 303.76 |  | 303.76 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Construction | 6603001 | 303.76 |  | 303.76 | 100 | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH | 2.73 |  | 2.73 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Mapping | 6010077 | 2.73 |  | 2.73 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Contract Total | PGE1CONTRACT | 5000 |  | 5000 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 5000 |  | 5000 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 5000 |  | 5000 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Other Costs | PGE1ORD-OTHER | 660.21 |  | 660.21 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Order Overheads | PGE1OVERHEAD | 660.21 |  | 660.21 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Capitalized A&G | PGE1CAPAG | 112.85 |  | 112.85 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Capitalized A&G | 6010050 | 112.85 |  | 112.85 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Labor Overheads | PGE1LABOROH | 362.26 |  | 362.26 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT | 329.08 |  | 329.08 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Paid Time Off | 6010100 | 61.73 |  | 61.73 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Indirect Labor - Electric | 6010106 | 103.9 |  | 103.9 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Operation Mgmt & Support - Electric | 6010114 | 94.03 |  | 94.03 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Fleet OH - Elec | 6010125 | 69.42 |  | 69.42 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH | 33.18 |  | 33.18 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Building Service Overhead | 6010112 | 21.17 |  | 21.17 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | IT Device OH | 6010113 | 12.01 |  | 12.01 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Other Overhead | PGE1OTHEROH | 158.77 |  | 158.77 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Benefits OH | 6010120 | 117.1 |  | 117.1 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Payroll Taxes OH | 6010121 | 41.67 |  | 41.67 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | AFUDC Costs | PGE1AFUDCDIR | 26.33 |  | 26.33 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | AFUDC-Borrowed | 5590030 | 26.33 |  | 26.33 | 100
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Type Total | PGE1ACTV-TOT |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Types | PGE1ACTVTYPES |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Activity Types - Internal | PGE1ACTV-INT |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Environmental Planning & Permitting-Misc | 6603027 |  | 104.46 | -104.46 |  |  | 1.5 | -1.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 10535.5 | -24570 | 35105.5 | 333.2115
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 10535.5 | -24570 | 35105.5 | 333.2115
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Contract Total | PGE1CONTRACT | 10500 | -24570 | 35070 | 334
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 10500 | -24570 | 35070 | 334
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 10500 | -24570 | 35070 | 334
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Other Costs | PGE1ORD-OTHER | 35.5 |  | 35.5 | 100
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | Order Overheads | PGE1OVERHEAD | 35.5 |  | 35.5 | 100
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | AFUDC Costs | PGE1AFUDCDIR | 35.5 |  | 35.5 | 100
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 |  | ESTS | AFUDC-Borrowed | 5590030 | 35.5 |  | 35.5 | 100
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 11040 | -24570 | 35610 | 322.5543
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 11040 | -24570 | 35610 | 322.5543
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Contract Total | PGE1CONTRACT | 11040 | -24570 | 35610 | 322.5543
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 11040 | -24570 | 35610 | 322.5543
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 11040 | -24570 | 35610 | 322.5543
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 20264 | -24570 | 44834 | 221.2495
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 20264 | -24570 | 44834 | 221.2495
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Contract Total | PGE1CONTRACT | 20264 | -24570 | 44834 | 221.2495
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 20264 | -24570 | 44834 | 221.2495
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 20264 | -24570 | 44834 | 221.2495
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 50400 | -24570 | 74970 | 148.75
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 50400 | -24570 | 74970 | 148.75
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Contract Total | PGE1CONTRACT | 50400 | -24570 | 74970 | 148.75
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 50400 | -24570 | 74970 | 148.75
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 50400 | -24570 | 74970 | 148.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Order Financial Costs | PGE1ORDFIN | 53900 | -24570 | 78470 | 145.5844
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 53900 | -24570 | 78470 | 145.5844
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Contract Total | PGE1CONTRACT | 53900 | -24570 | 78470 | 145.5844
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Other Contract | PGE1OTHCONTRAC | 53900 | -24570 | 78470 | 145.5844
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 |  | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 53900 | -24570 | 78470 | 145.5844
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Order Financial Costs | PGE1ORDFIN | 9000 |  | 9000 | 100
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 9000 |  | 9000 | 100
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Contract Total | PGE1CONTRACT | 9000 |  | 9000 | 100
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Other Contract | PGE1OTHCONTRAC | 9000 |  | 9000 | 100
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 |  | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003 | 9000 |  | 9000 | 100

## PRJ001 - Hrs Detail
Order | Order Text | WBS Element | Job Owner | User Status | Partner Cost Center | Partner Activity | Cost Element |  | Apr to Apr Plan Hrs | Apr to Apr Actual Hrs | Apr to Apr Var Hrs | Apr to Apr Var Hrs %
Overall Result | [8 empty] | 4601 | 809.25 | 3791.75 | 82.4114
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | Result |  |  |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | 15154 | Result |  |  |  | 0.25 | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 |  | PEND | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | Result |  |  |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | 15154 | Result |  |  |  | 0.25 | -0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 |  | ESTS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 0.25 | -0.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | Result |  |  |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | 15154 | Result |  |  |  | 0.5 | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 |  | PEND | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 0.5 | -0.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | Result |  |  |  | 470 | 38.5 | 431.5 | 91.8085
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 14182 | Result |  |  |  | 37.5 | -37.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 14182 | CONSTR | 6603001 | Construction |  | 36 | -36
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 1.5 | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 14632 | Result |  |  | 470 |  | 470 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 14632 | CONSTR | 6603001 | Construction | 470 |  | 470 | 100
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 15154 | Result |  |  |  | 1 | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 |  | CONS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 1 | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | Result |  |  |  | 750 | 107.5 | 642.5 | 85.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14182 | Result |  |  |  | 36.5 | -36.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14182 | CONSTR | 6603001 | Construction |  | 36 | -36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 0.5 | -0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14632 | Result |  |  | 750 | 70 | 680 | 90.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14632 | CNSTOT | 6603021 | Construction Overtime Services |  | 30 | -30
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 14632 | CONSTR | 6603001 | Construction | 750 | 40 | 710 | 94.6667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 15154 | Result |  |  |  | 1 | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 |  | CONS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | Result |  |  |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | 15154 | Result |  |  |  | 1 | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 |  | ESTS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 1 | -1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | Result |  |  |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | 15154 | Result |  |  |  | 0.25 | -0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 |  | ESTS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 0.25 | -0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | Result |  |  |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | 14182 | Result |  |  |  | 1 | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 |  | DOCC | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 1 | -1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | Result |  |  |  | 250 | 28 | 222 | 88.8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | 14182 | Result |  |  |  | 28 | -28
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 28 | -28
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | 14632 | Result |  |  | 250 |  | 250 | 100
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 |  | CONS | 14632 | CONSTR | 6603001 | Construction | 250 |  | 250 | 100
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | Result |  |  |  | 750 | 105.5 | 644.5 | 85.9333
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | 14182 | Result |  |  |  | 1 | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 1 | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | 14632 | Result |  |  | 750 | 104.5 | 645.5 | 86.0667
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | 14632 | CNSTOT | 6603021 | Construction Overtime Services |  | 4.5 | -4.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 |  | CONS | 14632 | CONSTR | 6603001 | Construction | 750 | 100 | 650 | 86.6667
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | Result |  |  |  | 900 | 218 | 682 | 75.7778
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 11834 | Result |  |  | 900 | 215 | 685 | 76.1111
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 11834 | CNSTDT | 6603180 | Construction Doubletime Services |  | 2 | -2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 11834 | CNSTOT | 6603021 | Construction Overtime Services |  | 23 | -23
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 11834 | CONSTR | 6603001 | Construction | 900 | 190 | 710 | 78.8889
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 14182 | Result |  |  |  | 2 | -2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 2 | -2
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 15154 | Result |  |  |  | 1 | -1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 |  | CONS | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 1 | -1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | Result |  |  |  | 900 | 107 | 793 | 88.1111
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | 14182 | Result |  |  |  | 2 | -2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 2 | -2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | 14632 | Result |  |  | 900 | 105 | 795 | 88.3333
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | 14632 | CNSTOT | 6603021 | Construction Overtime Services |  | 5 | -5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 |  | CONS | 14632 | CONSTR | 6603001 | Construction | 900 | 100 | 800 | 88.8889
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | Result |  |  |  | 450 | 154 | 296 | 65.7778
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | 11834 | Result |  |  | 450 | 152 | 298 | 66.2222
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | 11834 | CNSTOT | 6603021 | Construction Overtime Services |  | 67 | -67
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | 11834 | CONSTR | 6603001 | Construction | 450 | 85 | 365 | 81.1111
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | 14182 | Result |  |  |  | 2 | -2
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 2 | -2
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | Result |  |  |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | 14182 | Result |  |  |  | 1 | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 |  | CONS | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | Result |  |  |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | 14182 | Result |  |  |  | 1 | -1
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 |  | PEND | 14182 | ENGMAP | 6603022 | Engineering/Mapping |  | 1 | -1
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | Result |  |  |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | 15154 | Result |  |  |  | 7 | -7
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | 15154 | ADMIN | 6603000 | Administration |  | 4 | -4
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 |  | UNSE | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 3 | -3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | Result |  |  |  | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | 12577 | Result |  |  | 61 | 21 | 40 | 65.5738
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | 12577 | ADM-OT | 6603150 | Administrative Services - OT |  | 4 | -4
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 |  | UNSE | 12577 | LNDENG | 6603059 | Land Surveying & Engineering Supprt-Misc | 61 | 17 | 44 | 72.1311
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | Result |  |  |  | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | 12577 | Result |  |  | 62 | 16 | 46 | 74.1935
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | 12577 | ADM-OT | 6603150 | Administrative Services - OT | 1 | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 |  | UNSE | 12577 | LNDENG | 6603059 | Land Surveying & Engineering Supprt-Misc | 61 | 15 | 46 | 75.4098
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | Result |  |  |  | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | 12577 | Result |  |  | 4 |  | 4 | 100
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 |  | UNSE | 12577 | LNDENG | 6603059 | Land Surveying & Engineering Supprt-Misc | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | Result |  |  |  | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | 14182 | Result |  |  | 4 |  | 4 | 100
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 |  | UNSE | 14182 | CONSTR | 6603001 | Construction | 4 |  | 4 | 100
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | Result |  |  |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | 15154 | Result |  |  |  | 1.5 | -1.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 |  | UNSE | 15154 | ENVPLN | 6603027 | Environmental Planning & Permitting-Misc |  | 1.5 | -1.5

## PRJ004 - $$ Labor
[9 empty] | Jan Plan(PRJ) | Jan Actual | Feb Plan(PRJ) | Feb Actual | Mar Plan(PRJ) | Mar Actual | Apr Plan(PRJ) | Apr Actual | May Plan(PRJ) | May Actual | Jun Plan(PRJ) | Jun Actual | Jul Plan(PRJ) | Jul Actual | Aug Plan(PRJ) | Aug Actual | Sep Plan(PRJ) | Sep Actual | Oct Plan(PRJ) | Oct Actual | Nov Plan(PRJ) | Nov Actual | Dec Plan(PRJ) | Dec Actual | YTD Apr Plan(PRJ) | YTD Apr Actual | Jan - Dec Plan(PRJ) | Jan - Dec Actual
Order | Order Text | WBS Element | Planning Order | MaintActivityType | User Status | Job Owner | Partner Actv | Partner CC | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ |  | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $
Overall Result | [8 empty] | 1736.1579 | 1270.8107 | 768.6036 | 786.1663 | 1289.6088 | 2239.3543 | 1779.6551 | -223.6755 | 125.9794 |  | 2092.3794 |  | 3101.7865 |  | 3916.6811 |  | 9087.5496 |  | 10885.5828 |  | 10316.2158 |  | 3990.1915 |  | 5574.0254 | 4072.6559 | 49090.3916 | 4072.6559
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | Result |  | 0.14409 | 34.4081 | 0.14409 | -13.4574 | 0.14409 | 4.0536 | 0.14409 |  | 0.14409 |  | 0.14409 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.07469 |  | 0.57636 | 25.0043 | 1.6861 | 25.0043
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | Result | 0.14409 | 34.4081 | 0.14409 | -13.4574 | 0.14409 | 2.834 | 0.14409 |  | 0.14409 |  | 0.14409 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.07469 |  | 0.57636 | 23.7848 | 1.6861 | 23.7848
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | # | 0.14409 | 34.4081 | 0.14409 | -13.4574 | 0.14409 | 0.27812 | 0.14409 |  | 0.14409 |  | 0.14409 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.14938 |  | 0.07469 |  | 0.57636 | 21.2288 | 1.6861 | 21.2288
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 12002 | [5 empty] | 0.45309 | [19 empty] | 0.45309 |  | 0.45309
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 14646 | [5 empty] | 0.01098 | [19 empty] | 0.01098 |  | 0.01098
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16000 | [5 empty] | 0.24783 | [19 empty] | 0.24783 |  | 0.24783
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16006 | [5 empty] | 0.41715 | [19 empty] | 0.41715 |  | 0.41715
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16012 | [5 empty] | 0.08498 | [19 empty] | 0.08498 |  | 0.08498
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16013 | [5 empty] | 0.04823 | [19 empty] | 0.04823 |  | 0.04823
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16014 | [5 empty] | 0.37753 | [19 empty] | 0.37753 |  | 0.37753
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16032 | [5 empty] | 0.47015 | [19 empty] | 0.47015 |  | 0.47015
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16033 | [5 empty] | 0.16727 | [19 empty] | 0.16727 |  | 0.16727
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | # | 16035 | [5 empty] | 0.27872 | [19 empty] | 0.27872 |  | 0.27872
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | Result | [5 empty] | 1.2196 | [19 empty] | 1.2196 |  | 1.2196
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | [5 empty] | 1.2196 | [19 empty] | 1.2196 |  | 1.2196
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | Result |  | 1.1304 | 3.628 | 1.1304 | 4.8669 | 1.1304 | 5.4517 | 5 | 0.01741 | [16 empty] | 8.3913 | 13.964 | 8.3913 | 13.964
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | Result | 1.1304 | 3.5912 | 1.1304 | 4.8669 | 1.1304 | 4.7816 | 5 | [17 empty] | 8.3913 | 13.2398 | 8.3913 | 13.2398
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | # | 1.1304 | 3.528 | 1.1304 | 4.8669 | 1.1304 | 3.3773 | 5 | [17 empty] | 8.3913 | 11.7722 | 8.3913 | 11.7722
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 12002 |  | 0.01354 |  |  |  | 0.24893 | [19 empty] | 0.26247 |  | 0.26247
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 14646 | [5 empty] | 0.00603 | [19 empty] | 0.00603 |  | 0.00603
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16000 |  | 0.00741 |  |  |  | 0.13616 | [19 empty] | 0.14357 |  | 0.14357
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16006 |  | 0.00108 |  |  |  | 0.22919 | [19 empty] | 0.23027 |  | 0.23027
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16008 |  | 0.01187 | [23 empty] | 0.01187 |  | 0.01187
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16012 |  | 0.00219 |  |  |  | 0.04669 | [19 empty] | 0.04888 |  | 0.04888
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16013 |  | 0.00124 |  |  |  | 0.02649 | [19 empty] | 0.02773 |  | 0.02773
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16014 |  | 0.00098 |  |  |  | 0.20742 | [19 empty] | 0.2084 |  | 0.2084
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16020 |  | 0.00711 | [23 empty] | 0.00711 |  | 0.00711
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16032 |  | 0.01281 |  |  |  | 0.25831 | [19 empty] | 0.27112 |  | 0.27112
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16033 |  | 0.00431 |  |  |  | 0.09191 | [19 empty] | 0.09622 |  | 0.09622
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | # | 16035 |  | 0.00072 |  |  |  | 0.15314 | [19 empty] | 0.15386 |  | 0.15386
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | Result | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | EESTOT | Result |  | 0.00318 | [23 empty] | 0.00318 |  | 0.00318
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | EESTOT | 12974 |  | 0.00318 | [23 empty] | 0.00318 |  | 0.00318
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | Result | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | Result |  | 0.01741 | [23 empty] | 0.01741 |  | 0.01741
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 |  | 0.01741 | [23 empty] | 0.01741 |  | 0.01741
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | Result |  | 0.0162 | [23 empty] | 0.0162 |  | 0.0162
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 |  | 0.0162 | [23 empty] | 0.0162 |  | 0.0162
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | Result |  | 0.41759 | -8.2673 | 0.41759 | 3.0691 | 0.41759 | 3.8641 | 5 | 0.01741 | [16 empty] | 6.2528 | -1.3166 | 6.2528 | -1.3166
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | Result | 0.41759 | -8.2673 | 0.41759 | 3.0691 | 0.41759 | 3.1941 | 5 | [17 empty] | 6.2528 | -2.0041 | 6.2528 | -2.0041
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | # | 0.41759 | -8.265 | 0.41759 | 3.0691 | 0.41759 | 1.7898 | 5 | [17 empty] | 6.2528 | -3.4061 | 6.2528 | -3.4061
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 12002 |  | -0.00028 |  |  |  | 0.24893 | [19 empty] | 0.24865 |  | 0.24865
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 14646 |  | -0.00075 |  |  |  | 0.00603 | [19 empty] | 0.00528 |  | 0.00528
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16000 |  | -0.00015 |  |  |  | 0.13616 | [19 empty] | 0.13601 |  | 0.13601
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16006 |  | -0.00025 |  |  |  | 0.22919 | [19 empty] | 0.22894 |  | 0.22894
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16012 |  | -5e-05 |  |  |  | 0.04669 | [19 empty] | 0.04664 |  | 0.04664
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16013 |  | -3e-05 |  |  |  | 0.02649 | [19 empty] | 0.02646 |  | 0.02646
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16014 |  | -0.00023 |  |  |  | 0.20742 | [19 empty] | 0.20719 |  | 0.20719
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16032 |  | -0.0003 |  |  |  | 0.25831 | [19 empty] | 0.25801 |  | 0.25801
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16033 |  | -0.0001 |  |  |  | 0.09191 | [19 empty] | 0.09181 |  | 0.09181
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | # | 16035 |  | -0.00017 |  |  |  | 0.15314 | [19 empty] | 0.15297 |  | 0.15297
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | Result | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | Result | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | Result |  | 2.5654 | 45.8211 | 2.5654 | 9.1782 | 2.514 | 2.4657 | 7.5374 | 0.03482 | 2.5524 |  | 2.5524 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 15.1822 | 57.4998 | 35.8945 | 57.4998
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | Result | 2.5654 | 45.7654 | 2.5654 | 9.1782 | 2.514 | 1.7957 | 7.5374 |  | 2.5524 |  | 2.5524 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 15.1822 | 56.7393 | 35.8945 | 56.7393
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | # | 2.5654 | 45.6716 | 2.5654 | 9.1782 | 2.514 | 0.39141 | 7.5374 |  | 2.5524 |  | 2.5524 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 2.6012 |  | 15.1822 | 55.2412 | 35.8945 | 55.2412
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 12002 |  | 0.02051 |  |  |  | 0.24893 | [19 empty] | 0.26944 |  | 0.26944
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 14646 | [5 empty] | 0.00603 | [19 empty] | 0.00603 |  | 0.00603
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16000 |  | 0.01122 |  |  |  | 0.13616 | [19 empty] | 0.14738 |  | 0.14738
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16006 | [5 empty] | 0.22919 | [19 empty] | 0.22919 |  | 0.22919
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16008 |  | 0.01968 | [23 empty] | 0.01968 |  | 0.01968
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16012 |  | 0.00327 |  |  |  | 0.04669 | [19 empty] | 0.04996 |  | 0.04996
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16013 |  | 0.00185 |  |  |  | 0.02649 | [19 empty] | 0.02834 |  | 0.02834
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16014 | [5 empty] | 0.20742 | [19 empty] | 0.20742 |  | 0.20742
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16020 |  | 0.01178 | [23 empty] | 0.01178 |  | 0.01178
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16032 |  | 0.01908 |  |  |  | 0.25831 | [19 empty] | 0.27739 |  | 0.27739
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16033 |  | 0.00645 |  |  |  | 0.09191 | [19 empty] | 0.09836 |  | 0.09836
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | # | 16035 | [5 empty] | 0.15314 | [19 empty] | 0.15314 |  | 0.15314
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | Result |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | Result | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | [5 empty] | 0.67005 | [19 empty] | 0.67005 |  | 0.67005
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | Result | [7 empty] | 0.03482 | [17 empty] | 0.03482 |  | 0.03482
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | [7 empty] | 0.03482 | [17 empty] | 0.03482 |  | 0.03482
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | Result |  | -75.2941 | -59.5874 | 2.4337 | 80.6528 | 2.4337 | 13.7384 |  | -0.78284 | [16 empty] | -70.4268 | 34.0209 | -70.4268 | 34.0209
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | Result | -76.0666 | -59.5874 | 1.6611 | 80.5783 | 1.6611 | 13.3661 |  | -0.78284 | [16 empty] | -72.7443 | 33.5742 | -72.7443 | 33.5742
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | # | -77 | -58.8792 |  | 79.8379 |  | 12.5826 |  | -0.78284 | [16 empty] | -77 | 32.7585 | -77 | 32.7585
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 12002 | 0.19938 | -0.08444 | 0.28443 | 0.09715 | 0.28443 | 0.1387 | [18 empty] | 0.76824 | 0.15141 | 0.76824 | 0.15141
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 14646 | -0.231 | -0.22933 |  | 0.18942 |  | 0.00445 | [18 empty] | -0.231 | -0.03546 | -0.231 | -0.03546
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16000 | 0.10456 | -0.04618 | 0.14917 | 0.05313 | 0.14917 | 0.07587 | [18 empty] | 0.4029 | 0.08282 | 0.4029 | 0.08282
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16006 | 0.18357 | -0.07774 | 0.26188 | 0.08945 | 0.26188 | 0.1277 | [18 empty] | 0.70733 | 0.13941 | 0.70733 | 0.13941
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16012 | 0.03754 | -0.01584 | 0.05355 | 0.01821 | 0.05355 | 0.02602 | [18 empty] | 0.14464 | 0.02839 | 0.14464 | 0.02839
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16013 | 0.02131 | -0.009 | 0.0304 | 0.01035 | 0.0304 | 0.01476 | [18 empty] | 0.08211 | 0.01611 | 0.08211 | 0.01611
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16014 | 0.16613 | -0.07036 | 0.237 | 0.08096 | 0.237 | 0.11558 | [18 empty] | 0.64013 | 0.12618 | 0.64013 | 0.12618
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16032 | 0.24236 | -0.09228 | 0.34574 | 0.10617 | 0.34574 | 0.14391 | [18 empty] | 0.93384 | 0.1578 | 0.93384 | 0.1578
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16033 | 0.07794 | -0.03118 | 0.11119 | 0.03586 | 0.11119 | 0.05121 | [18 empty] | 0.30032 | 0.05589 | 0.30032 | 0.05589
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | # | 16035 | 0.13163 | -0.05194 | 0.18779 | 0.05977 | 0.18779 | 0.08532 | [18 empty] | 0.50721 | 0.09315 | 0.50721 | 0.09315
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | Result | 0.7725 |  | 0.7725 | 0.07445 | 0.7725 | 0.37225 | [18 empty] | 2.3175 | 0.4467 | 2.3175 | 0.4467
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | 0.7725 |  | 0.7725 |  | 0.7725 | [19 empty] | 2.3175 |  | 2.3175
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.37225 | [19 empty] | 0.4467 |  | 0.4467
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | Result |  | 120.7784 | 20.4003 | 1.215 | 30.7609 | 95.7 | 234.8817 | 132.9061 | -12.6981 | [8 empty] | 500 |  | 500.232 | [5 empty] | 350.5996 | 273.3447 | 1350.8316 | 273.3447
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | Result | 84.3554 | 18.9414 |  | 24.9886 | 65.4004 | 176.495 | 94.8643 | -15.5596 | [8 empty] | 500 |  | 500.232 | [5 empty] | 244.6201 | 204.8654 | 1244.8521 | 204.8654
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | # | 5 | 16.0416 |  | 10.9082 | 0.5 | 54.4023 | 15 | -15.5596 | [8 empty] | 500 |  | 500.232 | [5 empty] | 20.5 | 65.7924 | 1020.732 | 65.7924
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 11674 |  |  |  | 1.0756 |  | 0.16865 | [19 empty] | 1.2443 |  | 1.2443
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 12002 | 13.5317 | 0.54059 |  | 2.14 | 11.2502 | 21.7031 | 14.1496 | [17 empty] | 38.9315 | 24.3837 | 38.9315 | 24.3837
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 14646 | 0.32781 | 0.00938 |  | 0.03986 | 0.25496 | 0.55713 | 0.38738 | [17 empty] | 0.97015 | 0.60637 | 0.97015 | 0.60637
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16000 | 7.0966 | 0.2957 |  | 1.1706 | 6.1537 | 11.7996 | 7.7396 | [17 empty] | 20.9899 | 13.2658 | 20.9899 | 13.2658
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16006 | 12.4585 | 0.39421 |  | 1.9008 | 9.7491 | 19.5619 | 13.0275 | [17 empty] | 35.2351 | 21.857 | 35.2351 | 21.857
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | [19 empty] | 0.64988 |  | 0.64988
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16008 |  | 0.06151 |  | 0.04921 |  | 0.24236 | [19 empty] | 0.35308 |  | 0.35308
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16010 |  | 0.03398 |  | 0.01699 |  | 0.05097 | [19 empty] | 0.10194 |  | 0.10194
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16012 | 2.548 | 0.09694 |  | 0.43441 | 2.1311 | 4.0585 | 2.6537 | [17 empty] | 7.3328 | 4.5899 | 7.3328 | 4.5899
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16013 | 1.4461 | 0.05502 |  | 0.24656 | 1.2095 | 2.3035 | 1.5062 | [17 empty] | 4.1618 | 2.605 | 4.1618 | 2.605
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16014 | 11.2752 | 0.35677 |  | 1.7203 | 8.8231 | 17.8131 | 11.7901 | [17 empty] | 31.8883 | 19.8902 | 31.8883 | 19.8902
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | [19 empty] | 0.99656 |  | 0.99656
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16020 |  | 0.03684 |  | 0.02947 |  | 0.14515 | [19 empty] | 0.21146 |  | 0.21146
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16032 | 16.448 | 0.56474 |  | 2.5311 | 12.417 | 22.4545 | 14.6822 | [17 empty] | 43.5473 | 25.5503 | 43.5473 | 25.5503
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16033 | 5.2895 | 0.1908 |  | 0.85517 | 4.1951 | 7.9893 | 5.2239 | [17 empty] | 14.7085 | 9.0352 | 14.7085 | 9.0352
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16034 |  |  |  | 0.6003 |  | 0.09412 | [19 empty] | 0.69442 |  | 0.69442
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16035 | 8.9341 | 0.26338 |  | 1.27 | 6.5138 | 13.1508 | 8.7042 | [17 empty] | 24.1521 | 14.6842 | 24.1521 | 14.6842
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | [19 empty] | 0.5563 |  | 0.5563
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | Result | [5 empty] | 0.1944 | [19 empty] | 0.1944 |  | 0.1944
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | [5 empty] | 0.1944 | [19 empty] | 0.1944 |  | 0.1944
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | Result |  | 0.13126 |  | 0.06563 |  | 0.19689 | [19 empty] | 0.39378 |  | 0.39378
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 |  | 0.13126 |  | 0.06563 |  | 0.19689 | [19 empty] | 0.39378 |  | 0.39378
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | Result | [5 empty] | 0.19562 | [19 empty] | 0.19562 |  | 0.19562
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | [5 empty] | 0.19562 | [19 empty] | 0.19562 |  | 0.19562
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | Result |  |  |  | 0.13928 |  | 0.06964 | [19 empty] | 0.20892 |  | 0.20892
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 |  |  |  | 0.13928 |  | 0.06964 | [19 empty] | 0.20892 |  | 0.20892
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | Result | [5 empty] | 9.232 | [19 empty] | 9.232 |  | 9.232
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | [5 empty] | 1.7361 | [19 empty] | 1.7361 |  | 1.7361
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | [5 empty] | 0.29933 | [19 empty] | 0.29933 |  | 0.29933
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | [5 empty] | 1.3171 | [19 empty] | 1.3171 |  | 1.3171
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | [5 empty] | 5.8795 | [19 empty] | 5.8795 |  | 5.8795
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | Result |  |  |  | 0.13386 |  | 9.7762 | [19 empty] | 9.9101 |  | 9.9101
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | [5 empty] | 1.7846 | [19 empty] | 1.7846 |  | 1.7846
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | [5 empty] | 0.22308 | [19 empty] | 0.22308 |  | 0.22308
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 |  |  |  | 0.13386 |  | 3.8816 | [19 empty] | 4.0155 |  | 4.0155
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | [5 empty] | 3.8869 | [19 empty] | 3.8869 |  | 3.8869
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | Result | 36.423 | 1.0423 | 1.215 | 3.5534 | 28.329 | 36.7806 | 38.0418 | 2.6802 | [16 empty] | 104.0088 | 44.0565 | 104.0088 | 44.0565
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | [5 empty] | 5.4512 | [19 empty] | 5.4512 |  | 5.4512
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | [5 empty] | 0.6814 | [19 empty] | 0.6814 |  | 0.6814
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 |  | 1.0423 | 1.215 | 2.5313 |  |  |  | 2.6802 | [16 empty] | 1.215 | 6.2538 | 1.215 | 6.2538
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | 36.423 |  |  | 1.0221 | 28.329 | 18.3978 | 38.0418 | [17 empty] | 102.7938 | 19.4199 | 102.7938 | 19.4199
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | [5 empty] | 12.2502 | [19 empty] | 12.2502 |  | 12.2502
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | Result |  |  |  | 0.07445 |  | 0.85478 |  | 0.11168 | [17 empty] | 1.0409 |  | 1.0409
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | [5 empty] | 0.22968 | [19 empty] | 0.22968 |  | 0.22968
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.48394 |  | 0.11168 | [17 empty] | 0.67007 |  | 0.67007
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | [5 empty] | 0.14116 | [19 empty] | 0.14116 |  | 0.14116
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | Result |  | 0.1741 |  |  |  | 0.22633 |  | 0.06964 | [17 empty] | 0.47007 |  | 0.47007
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 |  | 0.1741 |  |  |  | 0.22633 |  | 0.06964 | [17 empty] | 0.47007 |  | 0.47007
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | Result | [5 empty] | 0.3562 | [19 empty] | 0.3562 |  | 0.3562
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | [5 empty] | 0.3562 | [19 empty] | 0.3562 |  | 0.3562
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | Result |  | 0.0571 |  | 0.75394 | 0.1744 | 0.1797 | [18 empty] | 0.1744 | 0.99074 | 0.1744 | 0.99074
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 |  | 0.0571 |  | 0.22841 |  | 0.03807 | [19 empty] | 0.32358 |  | 0.32358
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 |  |  |  | 0.04721 |  | 0.14163 | [19 empty] | 0.18884 |  | 0.18884
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 |  |  |  | 0.47832 | 0.1744 | [19 empty] | 0.1744 | 0.47832 | 0.1744 | 0.47832
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | Result |  |  |  | 0.26292 |  | 0.21618 | [19 empty] | 0.4791 |  | 0.4791
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | [5 empty] | 0.21618 | [19 empty] | 0.21618 |  | 0.21618
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 |  |  |  | 0.26292 | [21 empty] | 0.26292 |  | 0.26292
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | Result |  | 0.05408 |  | 0.50804 |  | 0.10816 | [19 empty] | 0.67028 |  | 0.67028
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 |  | 0.05408 |  | 0.29744 |  | 0.10816 | [19 empty] | 0.45968 |  | 0.45968
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 |  |  |  | 0.2106 | [21 empty] | 0.2106 |  | 0.2106
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | Result |  |  |  | 0.28072 | [21 empty] | 0.28072 |  | 0.28072
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 |  |  |  | 0.28072 | [21 empty] | 0.28072 |  | 0.28072
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | Result |  | 403.2386 | 24.3955 | 109.6241 | 110.4214 | 154.2471 | 75.4253 | 232.4328 | -12.6572 | [8 empty] | 500 |  | 500 |  | 718.409 |  |  |  | 899.5426 | 197.585 | 2617.9516 | 197.585
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | Result | 403.2386 | 20.3976 | 77.2481 | 78.5534 | 107.9338 | 61.8832 | 171.7278 | -20.8468 | [8 empty] | 500 |  | 500 |  | 718.409 |  |  |  | 760.1483 | 139.9875 | 2478.5573 | 139.9875
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | # | 403.2386 | 11.6874 | 8.6867 | 11.2598 | 9.0753 | 31.9072 | 35 | -20.8468 | [8 empty] | 500 |  | 500 |  | 718.409 |  |  |  | 456.0007 | 34.0077 | 2174.4097 | 34.0077
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 11674 |  | 0.29114 |  | 0.00271 |  | 1.014 | 5.11 | [17 empty] | 5.11 | 1.3078 | 5.11 | 1.3078
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 12002 |  | 1.4846 | 12.0336 | 11.8402 | 17.2078 | 5.033 | 22.5527 | [17 empty] | 51.7942 | 18.3578 | 51.7942 | 18.3578
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 14646 |  | 0.03406 | 0.30638 | 0.28909 | 0.42165 | 0.12712 | 0.54635 | [17 empty] | 1.2744 | 0.45027 | 1.2744 | 0.45027
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16000 |  | 0.80351 | 6.5822 | 6.4764 | 9.4124 | 2.753 | 12.336 | [17 empty] | 28.3307 | 10.0329 | 28.3307 | 10.0329
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16006 |  | 1.2425 | 11.0793 | 10.8345 | 15.2342 | 4.154 | 20.7642 | [17 empty] | 47.0777 | 16.231 | 47.0777 | 16.231
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | 0.12671 | [18 empty] | 0.64988 | 0.12671 | 0.64988 | 0.12671
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16008 |  | 0.02808 |  |  |  | 0.10815 | [19 empty] | 0.13623 |  | 0.13623
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16010 |  | 0.06341 |  | 0.05097 |  | 0.06797 | [19 empty] | 0.18235 |  | 0.18235
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16011 | [5 empty] | 0.18522 | [19 empty] | 0.18522 |  | 0.18522
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16012 |  | 0.28081 | 2.2569 | 2.2167 | 3.2484 | 0.96769 | 4.3998 | [17 empty] | 9.9051 | 3.4652 | 9.9051 | 3.4652
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16013 |  | 0.15937 | 1.2809 | 1.2581 | 1.8437 | 0.54923 | 2.4972 | [17 empty] | 5.6218 | 1.9667 | 5.6218 | 1.9667
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16014 |  | 1.1245 | 10.027 | 9.8054 | 13.7872 | 3.7595 | 18.7919 | [17 empty] | 42.6061 | 14.6893 | 42.6061 | 14.6893
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | 0.1943 | [18 empty] | 0.99656 | 0.1943 | 0.99656 | 0.1943
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16020 |  | 0.01682 |  |  |  | 0.06478 | [19 empty] | 0.0816 |  | 0.0816
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16029 | [5 empty] | 0.0797 | [19 empty] | 0.0797 |  | 0.0797
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16032 |  | 1.6361 | 13.1498 | 12.9155 | 18.9272 | 5.3541 | 24.3431 | [17 empty] | 56.4201 | 19.9057 | 56.4201 | 19.9057
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16033 |  | 0.55276 | 4.4427 | 4.3636 | 6.3946 | 1.905 | 8.6612 | [17 empty] | 19.4985 | 6.8213 | 19.4985 | 6.8213
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16034 |  | 0.16248 |  | 0.00151 |  | 0.64869 | 2.8518 | [17 empty] | 2.8518 | 0.81268 | 2.8518 | 0.81268
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16035 |  | 0.83017 | 7.4026 | 7.239 | 10.1786 | 2.7755 | 13.8734 | [17 empty] | 31.4546 | 10.8446 | 31.4546 | 10.8446
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | 0.10846 | [18 empty] | 0.5563 | 0.10846 | 0.5563 | 0.10846
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | Result |  | 0.24493 |  | 0.19689 |  | 0.26252 | [19 empty] | 0.70434 |  | 0.70434
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 |  | 0.04804 | [23 empty] | 0.04804 |  | 0.04804
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 |  | 0.19689 |  | 0.19689 |  | 0.26252 | [19 empty] | 0.6563 |  | 0.6563
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | Result |  | 0.07949 | [23 empty] | 0.07949 |  | 0.07949
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 |  | 0.07949 | [23 empty] | 0.07949 |  | 0.07949
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | Result |  | 0.2231 |  | 1.3832 |  | 0.53544 |  | 2.6769 | [17 empty] | 4.8187 |  | 4.8187
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 |  | 0.2231 |  | 1.3832 |  | 0.53544 |  | 2.6769 | [17 empty] | 4.8187 |  | 4.8187
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | Result |  | 3.407 | 32.376 | 29.9816 | 44.517 | 10.5712 | 60.705 | 5.4058 | [16 empty] | 137.598 | 49.3656 | 137.598 | 49.3656
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | [5 empty] | 0.35022 | [19 empty] | 0.35022 |  | 0.35022
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | [7 empty] | 2.6802 | [17 empty] | 2.6802 |  | 2.6802
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 |  | 3.407 | 32.376 | 29.9816 | 44.517 | 10.221 | 60.705 | 2.7256 | [16 empty] | 137.598 | 46.3352 | 137.598 | 46.3352
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | EESTOT | Result |  | 0.00106 | [23 empty] | 0.00106 |  | 0.00106
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | EESTOT | 12974 |  | 0.00106 | [23 empty] | 0.00106 |  | 0.00106
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | Result |  |  |  | 0.30624 |  | 0.41582 |  | 0.03723 | [17 empty] | 0.75929 |  | 0.75929
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 |  |  |  | 0.30624 |  | 0.22968 | [19 empty] | 0.53592 |  | 0.53592
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | [5 empty] | 0.18614 |  | 0.03723 | [17 empty] | 0.22337 |  | 0.22337
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | Result | [5 empty] | 0.13928 |  | 0.06964 | [17 empty] | 0.20892 |  | 0.20892
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | [5 empty] | 0.13928 |  | 0.06964 | [17 empty] | 0.20892 |  | 0.20892
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | Result | [5 empty] | 0.49656 | [19 empty] | 0.49656 |  | 0.49656
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | [5 empty] | 0.49656 | [19 empty] | 0.49656 |  | 0.49656
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | Result | [5 empty] | 0.0972 | [19 empty] | 0.0972 |  | 0.0972
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | [5 empty] | 0.0972 | [19 empty] | 0.0972 |  | 0.0972
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | Result |  | 0.0423 | [23 empty] | 0.0423 |  | 0.0423
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 |  | 0.0423 | [23 empty] | 0.0423 |  | 0.0423
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | Result | [5 empty] | 0.71748 | [19 empty] | 0.71748 |  | 0.71748
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | [5 empty] | 0.71748 | [19 empty] | 0.71748 |  | 0.71748
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | Result | [5 empty] | 0.23693 | [19 empty] | 0.23693 |  | 0.23693
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | [5 empty] | 0.23693 | [19 empty] | 0.23693 |  | 0.23693
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | Result | [6 empty] | -0.01095 | [16 empty] | 75 |  |  | -0.01095 | 75 | -0.01095
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | Result | [5 empty] | -0.01095 | [16 empty] | 75 |  |  | -0.01095 | 75 | -0.01095
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | # | [5 empty] | -0.01503 | [16 empty] | 75 |  |  | -0.01503 | 75 | -0.01503
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 11674 | [5 empty] | 0.00219 | [19 empty] | 0.00219 |  | 0.00219
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 16012 | [5 empty] | 7e-05 | [19 empty] | 7e-05 |  | 7e-05
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 16013 | [5 empty] | 4e-05 | [19 empty] | 4e-05 |  | 4e-05
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 16032 | [5 empty] | 0.0004 | [19 empty] | 0.0004 |  | 0.0004
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 16033 | [5 empty] | 0.00015 | [19 empty] | 0.00015 |  | 0.00015
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | 08W | DOCC |  | # | 16034 | [5 empty] | 0.00123 | [19 empty] | 0.00123 |  | 0.00123
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | Result |  | 0.68469 | 80.6341 | 0.68469 | 3.533 | 0.68469 | 3.533 | 5 | 0.06964 | [16 empty] | 7.0541 | 87.7696 | 7.0541 | 87.7696
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | # | Result | 0.68469 | 80.6341 | 0.68469 | 3.533 | 0.68469 | 3.533 | 5 | [17 empty] | 7.0541 | 87.7 | 7.0541 | 87.7
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | # | # | 0.68469 | 80.6341 | 0.68469 | 3.533 | 0.68469 | 3.533 | 5 | [17 empty] | 7.0541 | 87.7 | 7.0541 | 87.7
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | Result | [7 empty] | 0.06964 | [17 empty] | 0.06964 |  | 0.06964
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | [7 empty] | 0.06964 | [17 empty] | 0.06964 |  | 0.06964
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | Result |  |  | 0.50463 |  | 0.60555 |  | 0.50459 | [19 empty] | 1.6148 |  | 1.6148
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | Result |  | 0.50463 |  | 0.60555 |  | 0.50459 | [19 empty] | 1.6148 |  | 1.6148
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | # |  | 0.5 |  | 0.6 |  | 0.5 | [19 empty] | 1.6 |  | 1.6
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 12002 |  | 0.00055 |  | 0.00066 |  | 0.00055 | [19 empty] | 0.00176 |  | 0.00176
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 14646 |  | 0.0015 |  | 0.0018 |  | 0.0015 | [19 empty] | 0.0048 |  | 0.0048
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16000 |  | 0.0003 |  | 0.00036 |  | 0.0003 | [19 empty] | 0.00096 |  | 0.00096
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16006 |  | 0.00051 |  | 0.00061 |  | 0.00051 | [19 empty] | 0.00163 |  | 0.00163
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16012 |  | 0.0001 |  | 0.00012 |  | 0.0001 | [19 empty] | 0.00032 |  | 0.00032
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16013 |  | 6e-05 |  | 7e-05 |  | 6e-05 | [19 empty] | 0.00019 |  | 0.00019
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16014 |  | 0.00046 |  | 0.00055 |  | 0.00046 | [19 empty] | 0.00147 |  | 0.00147
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16032 |  | 0.00061 |  | 0.00073 |  | 0.00057 | [19 empty] | 0.00191 |  | 0.00191
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16033 |  | 0.0002 |  | 0.00024 |  | 0.0002 | [19 empty] | 0.00064 |  | 0.00064
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | 08W | FICL |  | # | 16035 |  | 0.00034 |  | 0.00041 |  | 0.00034 | [19 empty] | 0.00109 |  | 0.00109
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | Result | [6 empty] | 5.0309 |  | -4.985 | [14 empty] | 75 |  |  | 0.04588 | 75 | 0.04588
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | Result | [5 empty] | 5.0309 |  | -4.985 | [14 empty] | 75 |  |  | 0.04588 | 75 | 0.04588
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | # | [5 empty] | 4.985 |  | -4.985 | [14 empty] | 75 |  |  |  | 75
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 12002 | [5 empty] | 0.00551 | [19 empty] | 0.00551 |  | 0.00551
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 14646 | [5 empty] | 0.01496 | [19 empty] | 0.01496 |  | 0.01496
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16000 | [5 empty] | 0.00301 | [19 empty] | 0.00301 |  | 0.00301
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16006 | [5 empty] | 0.00507 | [19 empty] | 0.00507 |  | 0.00507
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16012 | [5 empty] | 0.00103 | [19 empty] | 0.00103 |  | 0.00103
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16013 | [5 empty] | 0.00058 | [19 empty] | 0.00058 |  | 0.00058
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16014 | [5 empty] | 0.00459 | [19 empty] | 0.00459 |  | 0.00459
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16032 | [5 empty] | 0.00571 | [19 empty] | 0.00571 |  | 0.00571
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16033 | [5 empty] | 0.00203 | [19 empty] | 0.00203 |  | 0.00203
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | 08W | DOCC |  | # | 16035 | [5 empty] | 0.00339 | [19 empty] | 0.00339 |  | 0.00339
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | Result |  | 0.85627 | 33.6249 | 0.85627 | 3.4321 | 0.85627 | 3.7057 | 5.8827 | 0.01741 | 0.89774 |  | 0.89774 |  | 0.92018 |  | 0.46009 | [9 empty] | 8.4515 | 40.7802 | 11.6273 | 40.7802
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | Result | 0.85627 | 33.6249 | 0.85627 | 3.4321 | 0.85627 | 3.6169 | 5.8827 |  | 0.89774 |  | 0.89774 |  | 0.92018 |  | 0.46009 | [9 empty] | 8.4515 | 40.674 | 11.6273 | 40.674
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | # | 0.85627 | 33.6249 | 0.85627 | 3.4321 | 0.85627 | 3.4332 | 5.8827 |  | 0.89774 |  | 0.89774 |  | 0.92018 |  | 0.46009 | [9 empty] | 8.4515 | 40.4903 | 11.6273 | 40.4903
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 12002 | [5 empty] | 0.0327 | [19 empty] | 0.0327 |  | 0.0327
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16000 | [5 empty] | 0.01789 | [19 empty] | 0.01789 |  | 0.01789
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16006 | [5 empty] | 0.03011 | [19 empty] | 0.03011 |  | 0.03011
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16012 | [5 empty] | 0.00614 | [19 empty] | 0.00614 |  | 0.00614
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16013 | [5 empty] | 0.00349 | [19 empty] | 0.00349 |  | 0.00349
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16014 | [5 empty] | 0.02725 | [19 empty] | 0.02725 |  | 0.02725
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16032 | [5 empty] | 0.03392 | [19 empty] | 0.03392 |  | 0.03392
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16033 | [5 empty] | 0.01207 | [19 empty] | 0.01207 |  | 0.01207
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | # | 16035 | [5 empty] | 0.02012 | [19 empty] | 0.02012 |  | 0.02012
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | Result | [5 empty] | 0.08882 | [19 empty] | 0.08882 |  | 0.08882
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | [5 empty] | 0.08882 | [19 empty] | 0.08882 |  | 0.08882
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | Result | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | [7 empty] | 0.01741 | [17 empty] | 0.01741 |  | 0.01741
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | 08W | DOCC |  | Result |  |  | 16.8885 |  | 16.0936 |  | 16.0936 | [16 empty] | 42.017 |  |  | 49.0757 | 42.017 | 49.0757
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | 08W | DOCC |  | # | Result |  | 16.8885 |  | 16.0936 |  | 16.0936 | [16 empty] | 42.017 |  |  | 49.0757 | 42.017 | 49.0757
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | 08W | DOCC |  | # | # |  | 16.8885 |  | 16.0936 |  | 16.0936 | [16 empty] | 42.017 |  |  | 49.0757 | 42.017 | 49.0757
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | Result |  | 353.9317 | 336.3356 |  | 6.7999 |  | -2.5972 | [16 empty] | 106.865 |  | 353.9317 | 340.5383 | 460.7967 | 340.5383
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | Result | 353.9317 | 336.3356 |  | 6.7999 |  | -2.5972 | [16 empty] | 106.865 |  | 353.9317 | 340.5383 | 460.7967 | 340.5383
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | # | 350.618 | 333.1856 |  | 6.7999 |  | -2.321 | [16 empty] | 106.865 |  | 350.618 | 337.6645 | 457.483 | 337.6645
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 11674 | [5 empty] | -0.0337 | [19 empty] | -0.0337 |  | -0.0337
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 12002 | 0.38729 | 0.37554 |  |  |  | 0.00116 | [18 empty] | 0.38729 | 0.3767 | 0.38729 | 0.3767
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 14646 | 1.0518 | 1.0199 |  |  |  | 0.00315 | [18 empty] | 1.0518 | 1.0231 | 1.0518 | 1.0231
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16000 | 0.20311 | 0.20542 |  |  |  | 0.00063 | [18 empty] | 0.20311 | 0.20605 | 0.20311 | 0.20605
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16006 | 0.35658 | 0.34577 |  |  |  | 0.00107 | [18 empty] | 0.35658 | 0.34684 | 0.35658 | 0.34684
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16012 | 0.07293 | 0.07044 |  |  |  | -0.00091 | [18 empty] | 0.07293 | 0.06953 | 0.07293 | 0.06953
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16013 | 0.04139 | 0.03998 |  |  |  | -0.00052 | [18 empty] | 0.04139 | 0.03946 | 0.04139 | 0.03946
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16014 | 0.32271 | 0.31292 |  |  |  | 0.00097 | [18 empty] | 0.32271 | 0.31389 | 0.32271 | 0.31389
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16032 | 0.47076 | 0.41038 |  |  |  | -0.00501 | [18 empty] | 0.47076 | 0.40537 | 0.47076 | 0.40537
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16033 | 0.15139 | 0.13865 |  |  |  | -0.00178 | [18 empty] | 0.15139 | 0.13687 | 0.15139 | 0.13687
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16034 | [5 empty] | -0.24198 | [19 empty] | -0.24198 |  | -0.24198
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | 08W | DOCC |  | # | 16035 | 0.2557 | 0.23101 |  |  |  | 0.00071 | [18 empty] | 0.2557 | 0.23172 | 0.2557 | 0.23172
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | Result |  |  | -102.5494 | [14 empty] | 177.549 | [8 empty] | -102.5494 | 177.549 | -102.5494
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | Result |  | -102.5494 | [14 empty] | 177.549 | [8 empty] | -102.5494 | 177.549 | -102.5494
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | # |  | -101.608 | [14 empty] | 177.549 | [8 empty] | -101.608 | 177.549 | -101.608
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 12002 |  | -0.11223 | [23 empty] | -0.11223 |  | -0.11223
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 14646 |  | -0.30482 | [23 empty] | -0.30482 |  | -0.30482
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16000 |  | -0.06139 | [23 empty] | -0.06139 |  | -0.06139
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16006 |  | -0.10333 | [23 empty] | -0.10333 |  | -0.10333
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16012 |  | -0.02105 | [23 empty] | -0.02105 |  | -0.02105
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16013 |  | -0.01195 | [23 empty] | -0.01195 |  | -0.01195
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16014 |  | -0.09352 | [23 empty] | -0.09352 |  | -0.09352
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16032 |  | -0.12265 | [23 empty] | -0.12265 |  | -0.12265
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16033 |  | -0.04144 | [23 empty] | -0.04144 |  | -0.04144
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | 08W | DOCC |  | # | 16035 |  | -0.06904 | [23 empty] | -0.06904 |  | -0.06904
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | 08W | DOCC |  | Result | [13 empty] | 75 | [13 empty] | 75
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | 08W | DOCC |  | # | Result | [12 empty] | 75 | [13 empty] | 75
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | 08W | DOCC |  | # | # | [12 empty] | 75 | [13 empty] | 75
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | 08W | DOCC |  | Result | [13 empty] | 75 | [13 empty] | 75
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | 08W | DOCC |  | # | Result | [12 empty] | 75 | [13 empty] | 75
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | 08W | DOCC |  | # | # | [12 empty] | 75 | [13 empty] | 75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | Result |  |  | 100.6745 | [12 empty] | 74.326 | [10 empty] | 100.6745 | 74.326 | 100.6745
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | Result |  | 100.3791 | [12 empty] | 74.326 | [10 empty] | 100.3791 | 74.326 | 100.3791
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | # |  | 100 | [12 empty] | 74.326 | [10 empty] | 100 | 74.326 | 100
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 12002 |  | 0.10874 | [23 empty] | 0.10874 |  | 0.10874
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16000 |  | 0.05948 | [23 empty] | 0.05948 |  | 0.05948
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16010 |  | 0.07646 | [23 empty] | 0.07646 |  | 0.07646
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16012 |  | 0.01436 | [23 empty] | 0.01436 |  | 0.01436
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16013 |  | 0.00815 | [23 empty] | 0.00815 |  | 0.00815
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16032 |  | 0.08368 | [23 empty] | 0.08368 |  | 0.08368
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | # | 16033 |  | 0.02827 | [23 empty] | 0.02827 |  | 0.02827
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | Result |  | 0.29534 | [23 empty] | 0.29534 |  | 0.29534
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 |  | 0.29534 | [23 empty] | 0.29534 |  | 0.29534
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | 08W | DOCC |  | Result | [11 empty] | 75 | [15 empty] | 75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | 08W | DOCC |  | # | Result | [10 empty] | 75 | [15 empty] | 75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | 08W | DOCC |  | # | # | [10 empty] | 75 | [15 empty] | 75
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | Result |  |  | 0.74941 | [8 empty] | 74.251 | [14 empty] | 0.74941 | 74.251 | 0.74941
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | Result |  | 0.42126 | [8 empty] | 74.251 | [14 empty] | 0.42126 | 74.251 | 0.42126
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | # | [10 empty] | 74.251 | [15 empty] | 74.251
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 12002 |  | 0.12082 | [23 empty] | 0.12082 |  | 0.12082
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16000 |  | 0.06609 | [23 empty] | 0.06609 |  | 0.06609
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16010 |  | 0.08496 | [23 empty] | 0.08496 |  | 0.08496
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16012 |  | 0.01596 | [23 empty] | 0.01596 |  | 0.01596
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16013 |  | 0.00905 | [23 empty] | 0.00905 |  | 0.00905
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16032 |  | 0.09297 | [23 empty] | 0.09297 |  | 0.09297
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | # | 16033 |  | 0.03141 | [23 empty] | 0.03141 |  | 0.03141
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | Result |  | 0.32815 | [23 empty] | 0.32815 |  | 0.32815
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 |  | 0.32815 | [23 empty] | 0.32815 |  | 0.32815
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | Result |  |  | 3.027 | [10 empty] | 71.973 | [12 empty] | 3.027 | 71.973 | 3.027
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | Result |  | 3.027 | [10 empty] | 71.973 | [12 empty] | 3.027 | 71.973 | 3.027
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | # |  | 2.9992 | [10 empty] | 71.973 | [12 empty] | 2.9992 | 71.973 | 2.9992
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 12002 |  | 0.00331 | [23 empty] | 0.00331 |  | 0.00331
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 14646 |  | 0.009 | [23 empty] | 0.009 |  | 0.009
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16000 |  | 0.00181 | [23 empty] | 0.00181 |  | 0.00181
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16006 |  | 0.00305 | [23 empty] | 0.00305 |  | 0.00305
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16012 |  | 0.00062 | [23 empty] | 0.00062 |  | 0.00062
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16013 |  | 0.00035 | [23 empty] | 0.00035 |  | 0.00035
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16014 |  | 0.00276 | [23 empty] | 0.00276 |  | 0.00276
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16032 |  | 0.00362 | [23 empty] | 0.00362 |  | 0.00362
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16033 |  | 0.00122 | [23 empty] | 0.00122 |  | 0.00122
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | 08W | DOCC |  | # | 16035 |  | 0.00204 | [23 empty] | 0.00204 |  | 0.00204
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | 08W | DOCC |  | Result | [15 empty] | 75 | [11 empty] | 75
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | 08W | DOCC |  | # | Result | [14 empty] | 75 | [11 empty] | 75
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | 08W | DOCC |  | # | # | [14 empty] | 75 | [11 empty] | 75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | Result |  | 39.7421 | 12.6432 | 2.3924 | -25.4833 | 2.3453 | 89.3404 |  | -1.2347 | [16 empty] | 44.4798 | 75.2655 | 44.4798 | 75.2655
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | Result | 38.9827 | 12.6432 | 1.633 | -25.5577 | 1.5859 | 88.8035 |  | -1.3092 | [16 empty] | 42.2016 | 74.5798 | 42.2016 | 74.5798
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | # | 37 | 12.645 |  | -25.3657 |  | 87.0047 |  | -1.3092 | [16 empty] | 37 | 72.9748 | 37 | 72.9748
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 12002 | 0.32048 | -0.00022 | 0.27961 | -0.01401 | 0.27961 | 0.28109 | [18 empty] | 0.8797 | 0.26686 | 0.8797 | 0.26686
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 14646 | 0.111 | -0.0006 |  | -0.1125 |  | 0.22654 | [18 empty] | 0.111 | 0.11344 | 0.111 | 0.11344
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16000 | 0.16807 | -0.00012 | 0.14664 | -0.00767 | 0.15294 | 0.15375 | [18 empty] | 0.46765 | 0.14596 | 0.46765 | 0.14596
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16006 | 0.29507 | -0.0002 | 0.25744 | -0.0129 | 0.25744 | 0.25322 | [18 empty] | 0.80995 | 0.24012 | 0.80995 | 0.24012
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16008 | [5 empty] | 0.00582 | [19 empty] | 0.00582 |  | 0.00582
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16012 | 0.06036 | -4e-05 | 0.05266 | -0.00263 | 0.05245 | 0.05255 | [18 empty] | 0.16547 | 0.04988 | 0.16547 | 0.04988
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16013 | 0.03425 | -2e-05 | 0.02988 | -0.00149 | 0.02976 | 0.02981 | [18 empty] | 0.09389 | 0.0283 | 0.09389 | 0.0283
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16014 | 0.26703 | -0.00018 | 0.23298 | -0.01168 | 0.23298 | 0.22917 | [18 empty] | 0.73299 | 0.21731 | 0.73299 | 0.21731
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16020 | [5 empty] | 0.00348 | [19 empty] | 0.00348 |  | 0.00348
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16032 | 0.38956 | -0.00024 | 0.33988 | -0.01532 | 0.30554 | 0.29073 | [18 empty] | 1.035 | 0.27517 | 1.035 | 0.27517
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16033 | 0.12527 | -8e-05 | 0.1093 | -0.00518 | 0.10323 | 0.10345 | [18 empty] | 0.3378 | 0.09819 | 0.3378 | 0.09819
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | # | 16035 | 0.21159 | -0.00014 | 0.18461 | -0.00862 | 0.172 | 0.16918 | [18 empty] | 0.5682 | 0.16042 | 0.5682 | 0.16042
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | Result | [5 empty] | 0.01646 | [19 empty] | 0.01646 |  | 0.01646
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | [5 empty] | 0.01646 | [19 empty] | 0.01646 |  | 0.01646
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | Result | 0.7594 |  | 0.7594 | 0.07445 | 0.7594 | 0.52043 |  | 0.07445 | [16 empty] | 2.2782 | 0.66933 | 2.2782 | 0.66933
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | [5 empty] | 0.14818 | [19 empty] | 0.14818 |  | 0.14818
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | 0.7594 |  | 0.7594 | 0.07445 | 0.7594 | 0.37225 |  | 0.07445 | [16 empty] | 2.2782 | 0.52115 | 2.2782 | 0.52115
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | Result |  | 75.1141 | 1.2878 | 2.4337 | -72.3754 | 2.3858 | 126.2554 |  | -0.02 | [14 empty] | 19.83 |  | 79.9336 | 55.1478 | 99.7636 | 55.1478
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | Result | 74.3416 | 0.96384 | 1.6611 | -72.4499 | 1.6133 | 125.907 |  | -0.02 | [14 empty] | 19.83 |  | 77.6161 | 54.401 | 97.4461 | 54.401
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | # | 72 | 0.41782 |  | -71.9386 |  | 124.1617 |  | -0.02 | [14 empty] | 19.83 |  | 72 | 52.621 | 91.83 | 52.621
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 12002 | 0.36396 | 0.1193 | 0.28443 | -0.05208 | 0.28443 | 0.2478 | [18 empty] | 0.93282 | 0.31502 | 0.93282 | 0.31502
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 14646 | 0.216 |  |  | -0.21589 |  | 0.38137 | [18 empty] | 0.216 | 0.16548 | 0.216 | 0.16548
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16000 | 0.19088 | 0.06525 | 0.14917 | -0.02849 | 0.15558 | 0.13484 | [18 empty] | 0.49563 | 0.1716 | 0.49563 | 0.1716
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16006 | 0.3351 |  | 0.26188 | -0.04795 | 0.26188 | 0.20501 | [18 empty] | 0.85886 | 0.15706 | 0.85886 | 0.15706
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16008 |  | 0.11447 |  |  |  | 0.02289 | [19 empty] | 0.13736 |  | 0.13736
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16012 | 0.06853 | 0.01907 | 0.05355 | -0.00977 | 0.05334 | 0.04758 | [18 empty] | 0.17542 | 0.05688 | 0.17542 | 0.05688
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16013 | 0.0389 | 0.01082 | 0.0304 | -0.00554 | 0.03028 | 0.027 | [18 empty] | 0.09958 | 0.03228 | 0.09958 | 0.03228
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16014 | 0.30327 |  | 0.237 | -0.0434 | 0.237 | 0.18552 | [18 empty] | 0.77727 | 0.14212 | 0.77727 | 0.14212
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16020 |  | 0.06856 |  |  |  | 0.01371 | [19 empty] | 0.08227 |  | 0.08227
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16032 | 0.44241 | 0.11103 | 0.34574 | -0.05691 | 0.31081 | 0.25268 | [18 empty] | 1.099 | 0.3068 | 1.099 | 0.3068
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16033 | 0.14227 | 0.03752 | 0.11119 | -0.01923 | 0.10502 | 0.0899 | [18 empty] | 0.35848 | 0.10819 | 0.35848 | 0.10819
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | # | 16035 | 0.2403 |  | 0.18779 | -0.03204 | 0.17497 | 0.13697 | [18 empty] | 0.60306 | 0.10493 | 0.60306 | 0.10493
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | Result |  | 0.2916 |  |  |  | 0.0648 | [19 empty] | 0.3564 |  | 0.3564
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 |  | 0.2268 | [23 empty] | 0.2268 |  | 0.2268
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 |  | 0.0648 |  |  |  | 0.0648 | [19 empty] | 0.1296 |  | 0.1296
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | Result | 0.7725 |  | 0.7725 | 0.07445 | 0.7725 | 0.22335 | [18 empty] | 2.3175 | 0.2978 | 2.3175 | 0.2978
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | 0.7725 |  | 0.7725 |  | 0.7725 | [19 empty] | 2.3175 |  | 2.3175
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.22335 | [19 empty] | 0.2978 |  | 0.2978
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | Result |  | 0.0324 | [23 empty] | 0.0324 |  | 0.0324
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 |  | 0.0324 | [23 empty] | 0.0324 |  | 0.0324
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | Result | [5 empty] | 0.06024 | [19 empty] | 0.06024 |  | 0.06024
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | [5 empty] | 0.06024 | [19 empty] | 0.06024 |  | 0.06024
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | Result |  | 601.4075 | 138.1838 | 128.4639 | 180.505 | 154.1319 | 355.8454 | 79.5988 | -28.9672 | [8 empty] | 1000 |  | 766.414 | [5 empty] | 963.6021 | 645.5671 | 2730.0161 | 645.5671
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | Result | 601.4075 | 99.7719 | 96.0879 | 144.1514 | 113.7962 | 275.5037 | 59.3638 | -31.0518 | [8 empty] | 1000 |  | 766.414 | [5 empty] | 870.6554 | 488.3752 | 2637.0694 | 488.3752
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | # | 601.4075 | 15.9694 | 27.3413 | 64.8953 | 27.84 | 106.0179 | 16.8181 | -31.0518 | [8 empty] | 1000 |  | 766.414 | [5 empty] | 673.4069 | 155.8308 | 2439.8209 | 155.8308
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 11674 |  | 1.3894 |  | 0.98926 |  | 0.3917 | [19 empty] | 2.7704 |  | 2.7704
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 12002 |  | 14.2699 | 12.0557 | 13.5624 | 14.9597 | 29.8971 | 7.5342 | [17 empty] | 34.5496 | 57.7294 | 34.5496 | 57.7294
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 14646 |  | 0.34395 | 0.36638 | 0.48055 | 0.29354 | 0.85625 | 0.22712 | [17 empty] | 0.88704 | 1.6807 | 0.88704 | 1.6807
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16000 |  | 7.8054 | 6.5943 | 7.4184 | 8.1827 | 16.3533 | 4.1211 | [17 empty] | 18.8981 | 31.5771 | 18.8981 | 31.5771
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16006 |  | 13.0722 | 11.0997 | 12.4868 | 13.1452 | 27.5025 | 6.9367 | [17 empty] | 31.1815 | 53.0614 | 31.1815 | 53.0614
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | [19 empty] | 0.64988 |  | 0.64988
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16008 |  | 0.06889 |  |  | 0.02001 | 0.0246 | [18 empty] | 0.02001 | 0.09349 | 0.02001 | 0.09349
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16012 |  | 2.7205 | 2.261 | 2.5765 | 2.8262 | 5.6194 | 1.413 | [17 empty] | 6.5002 | 10.9164 | 6.5002 | 10.9164
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16013 |  | 1.5441 | 1.2833 | 1.4623 | 1.6041 | 3.1894 | 0.80196 | [17 empty] | 3.6893 | 6.1958 | 3.6893 | 6.1958
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16014 |  | 11.8305 | 10.0454 | 11.3007 | 11.8966 | 24.8902 | 6.2778 | [17 empty] | 28.2197 | 48.0214 | 28.2197 | 48.0214
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | [19 empty] | 0.99656 |  | 0.99656
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16020 |  | 0.04125 |  |  | 0.01198 | 0.01474 | [18 empty] | 0.01198 | 0.05599 | 0.01198 | 0.05599
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16032 |  | 15.8514 | 13.1739 | 15.0122 | 16.4672 | 31.0906 | 7.8177 | [17 empty] | 37.4589 | 61.9543 | 37.4589 | 61.9543
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16033 |  | 5.3555 | 4.4508 | 5.0719 | 5.5635 | 11.0619 | 2.7815 | [17 empty] | 12.7958 | 21.4893 | 12.7958 | 21.4893
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16034 |  | 0.77542 |  | 0.55209 |  | 0.2186 | [19 empty] | 1.5461 |  | 1.5461
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16035 |  | 8.734 | 7.4162 | 8.343 | 8.7828 | 18.3756 | 4.6347 | [17 empty] | 20.8337 | 35.4526 | 20.8337 | 35.4526
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | [19 empty] | 0.5563 |  | 0.5563
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | Result |  | 0.13928 | [23 empty] | 0.13928 |  | 0.13928
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 |  | 0.13928 | [23 empty] | 0.13928 |  | 0.13928
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | Result |  | 0.05569 |  |  | 0.05663 | [19 empty] | 0.05663 | 0.05569 | 0.05663 | 0.05569
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 |  | 0.05569 |  |  | 0.05663 | [19 empty] | 0.05663 | 0.05569 | 0.05663 | 0.05569
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | Result | [5 empty] | 3.8314 | [19 empty] | 3.8314 |  | 3.8314
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | [5 empty] | 3.592 | [19 empty] | 3.592 |  | 3.592
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | [5 empty] | 0.23948 | [19 empty] | 0.23948 |  | 0.23948
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | Result |  | 4.2833 |  | 4.3278 |  | 10.7081 | [19 empty] | 19.3192 |  | 19.3192
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | [5 empty] | 1.3385 | [19 empty] | 1.3385 |  | 1.3385
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | [5 empty] | 1.5616 | [19 empty] | 1.5616 |  | 1.5616
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 |  | 4.2833 |  | 4.3278 |  | 7.808 | [19 empty] | 16.4191 |  | 16.4191
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | Result |  | 33.9337 | 32.376 | 32.0258 | 24.282 | 54.3417 | 20.235 | [17 empty] | 76.893 | 120.3012 | 76.893 | 120.3012
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | [5 empty] | 3.2367 | [19 empty] | 3.2367 |  | 3.2367
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | [5 empty] | 4.7698 | [19 empty] | 4.7698 |  | 4.7698
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 |  | 33.9337 | 32.376 | 32.0258 | 24.282 | 46.3352 | 20.235 | [17 empty] | 76.893 | 112.2947 | 76.893 | 112.2947
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | Result |  |  |  |  | 14.2008 | 11.3909 |  | 2.0846 | [16 empty] | 14.2008 | 13.4755 | 14.2008 | 13.4755
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 |  |  |  |  | 14.2008 | 11.3909 |  | 2.0846 | [16 empty] | 14.2008 | 13.4755 | 14.2008 | 13.4755
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | Result |  | 0.20875 | 3.0229 | 0.23468 | 2.8784 | 71.7411 | 49.9551 | 225.6404 | -40.9803 | [12 empty] | 1000 |  | 947.556 |  | 297.8249 | 14.8761 | 2245.3809 | 14.8761
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | Result | 0.20875 | 2.8258 | 0.23468 | 2.8784 | 71.7411 | 49.6669 | 225.6404 | -40.9803 | [12 empty] | 1000 |  | 947.556 |  | 297.8249 | 14.3908 | 2245.3809 | 14.3908
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | # | 0.20875 | 2.4951 | 0.23468 | 2.8761 | 71.7411 | 49.1243 | 177.45 | -40.9803 | [12 empty] | 1000 |  | 947.556 |  | 249.6345 | 13.5152 | 2197.1905 | 13.5152
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 11674 | [6 empty] | 25.9077 | [17 empty] | 25.9077 |  | 25.9077
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 12002 |  | 0.07229 |  | 0.00028 |  | 0.10638 | [19 empty] | 0.17895 |  | 0.17895
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 14646 |  | -0.00075 |  | 0.00075 |  | 0.00075 | [19 empty] | 0.00075 |  | 0.00075
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16000 |  | 0.03955 |  | 0.00015 |  | 0.0582 | [19 empty] | 0.0979 |  | 0.0979
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16006 |  | 0.00047 |  | 0.00025 |  | 0.05073 | [19 empty] | 0.05145 |  | 0.05145
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16008 |  | 0.06889 |  |  |  | 0.0492 | [19 empty] | 0.11809 |  | 0.11809
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16012 |  | 0.01156 |  | 5e-05 |  | 0.01853 | 0.86273 | [17 empty] | 0.86273 | 0.03014 | 0.86273 | 0.03014
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16013 |  | 0.00655 |  | 3e-05 |  | 0.01052 | 0.48966 | [17 empty] | 0.48966 | 0.0171 | 0.48966 | 0.0171
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16014 |  | 0.00042 |  | 0.00023 |  | 0.04591 | [19 empty] | 0.04656 |  | 0.04656
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16020 |  | 0.04125 |  |  |  | 0.02948 | [19 empty] | 0.07073 |  | 0.07073
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16032 |  | 0.06736 |  | 0.0003 |  | 0.10249 | 4.7732 | [17 empty] | 4.7732 | 0.17015 | 4.7732 | 0.17015
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16033 |  | 0.02277 |  | 0.0001 |  | 0.03649 | 1.6983 | [17 empty] | 1.6983 | 0.05936 | 1.6983 | 0.05936
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16034 | [6 empty] | 14.4587 | [17 empty] | 14.4587 |  | 14.4587
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | # | 16035 |  | 0.00031 |  | 0.00017 |  | 0.0339 | [19 empty] | 0.03438 |  | 0.03438
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | Result |  | 0.13928 |  |  |  | 0.06964 | [19 empty] | 0.20892 |  | 0.20892
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 |  | 0.13928 |  |  |  | 0.06964 | [19 empty] | 0.20892 |  | 0.20892
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | Result |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | EESTOT | Result |  | 0.00212 | [23 empty] | 0.00212 |  | 0.00212
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | EESTOT | 12974 |  | 0.00212 | [23 empty] | 0.00212 |  | 0.00212
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 0.1489 | [19 empty] | 0.1489 |  | 0.1489
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | [5 empty] | 0.1489 | [19 empty] | 0.1489 |  | 0.1489
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | Result |  | 0.28764 | 3.2942 | 91.2557 | 31.2826 | 231.8281 | 329.7607 | 213.0659 | -9.592 | [10 empty] | 1000 |  | 1000 |  | 503.182 |  | 536.4373 | 354.7454 | 3039.6193 | 354.7454
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | Result | 0.28764 | 3.2385 | 66.9737 | 31.2826 | 197.6558 | 307.8371 | 152.3609 | -16.882 | [10 empty] | 1000 |  | 1000 |  | 503.182 |  | 417.2781 | 325.4762 | 2920.4601 | 325.4762
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | # | 0.28764 | 3.1414 | 15.5874 | 25.8375 | 26.3682 | 212.2218 | 25 | -16.882 | [10 empty] | 1000 |  | 1000 |  | 503.182 |  | 67.2433 | 224.3186 | 2570.4253 | 224.3186
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 11674 |  |  |  | 2.8719 |  | 26.0536 | [19 empty] | 28.9255 |  | 28.9255
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 12002 |  | 0.0209 | 9.0211 | 0.00301 | 30.0703 | 8.1525 | 22.5693 | [17 empty] | 61.6608 | 8.1764 | 61.6608 | 8.1764
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 14646 |  | 0.00105 | 0.21854 | 0.00815 | 0.72846 | 0.21802 | 0.59135 | [17 empty] | 1.5384 | 0.22722 | 1.5384 | 0.22722
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16000 |  | 0.01143 | 4.9344 | 0.00164 | 16.448 | 4.4593 | 12.3451 | [17 empty] | 33.7275 | 4.4724 | 33.7275 | 4.4724
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16006 |  | 0.00036 | 8.3057 | 0.00276 | 27.6856 | 7.3896 | 20.7795 | [17 empty] | 56.7708 | 7.3927 | 56.7708 | 7.3927
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16008 |  | 0.01968 |  |  |  | 0.1213 | [19 empty] | 0.14098 |  | 0.14098
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16012 |  | 0.00334 | 1.6919 | 0.09619 | 5.6395 | 2.3931 | 4.2328 | [17 empty] | 11.5642 | 2.4926 | 11.5642 | 2.4926
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16013 |  | 0.00189 | 0.96025 | 0.05459 | 3.2008 | 1.3582 | 2.4024 | [17 empty] | 6.5635 | 1.4147 | 6.5635 | 1.4147
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16014 |  | 0.00032 | 7.5168 | 0.0025 | 25.0559 | 6.6877 | 18.8057 | [17 empty] | 51.3784 | 6.6905 | 51.3784 | 6.6905
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16020 |  | 0.01178 |  |  |  | 0.07266 | [19 empty] | 0.08444 |  | 0.08444
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16032 |  | 0.0195 | 9.8578 | 0.56049 | 32.8594 | 13.2401 | 23.4188 | [17 empty] | 66.136 | 13.8201 | 66.136 | 13.8201
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16033 |  | 0.0066 | 3.3305 | 0.18935 | 11.1016 | 4.7108 | 8.3323 | [17 empty] | 22.7645 | 4.9067 | 22.7645 | 4.9067
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16034 |  |  |  | 1.6527 |  | 15.8212 | [19 empty] | 17.4739 |  | 17.4739
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | # | 16035 |  | 0.00024 | 5.5494 | 0.00185 | 18.4979 | 4.9373 | 13.8836 | [17 empty] | 37.9309 | 4.9394 | 37.9309 | 4.9394
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | Result | [5 empty] | 0.0648 | [19 empty] | 0.0648 |  | 0.0648
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | [5 empty] | 0.0648 | [19 empty] | 0.0648 |  | 0.0648
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | Result | [5 empty] | 0.20892 | [19 empty] | 0.20892 |  | 0.20892
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | [5 empty] | 0.20892 | [19 empty] | 0.20892 |  | 0.20892
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | Result |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | Result | [5 empty] | 5.4878 |  | 0.40158 | [17 empty] | 5.8893 |  | 5.8893
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | [5 empty] | 5.4878 |  | 0.40158 | [17 empty] | 5.8893 |  | 5.8893
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | Result |  |  | 24.282 |  | 32.376 | 16.018 | 60.705 | 6.814 | [16 empty] | 117.363 | 22.832 | 117.363 | 22.832
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 |  |  | 24.282 |  | 32.376 | [19 empty] | 56.658 |  | 56.658
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | [5 empty] | 3.2758 | [19 empty] | 3.2758 |  | 3.2758
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | [5 empty] | 12.7422 | 60.705 | 6.814 | [16 empty] | 60.705 | 19.5562 | 60.705 | 19.5562
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 0.07446 |  | 0.07446 | [17 empty] | 0.14892 |  | 0.14892
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | [5 empty] | 0.07446 |  | 0.07446 | [17 empty] | 0.14892 |  | 0.14892
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | Result |  | 1.2132 | 95.4273 | 48.7472 | 63.1157 | 127.2758 | 191.2901 | 230.5593 | 11.8977 | [10 empty] | 1000 |  | 1000 |  | 4.457 |  | 407.7956 | 361.7307 | 2412.2526 | 361.7307
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | Result | 1.2132 | 69.7004 | 36.0652 | 45.6207 | 88.2972 | 133.7802 | 157.7133 | -3.5594 | [10 empty] | 1000 |  | 1000 |  | 4.457 |  | 283.2889 | 245.5419 | 2287.7459 | 245.5419
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | # | 1.2132 | 15.4333 | 9.4997 | 8.8866 | 5 | 13.3282 | 5 | -3.5594 | [10 empty] | 1000 |  | 1000 |  | 4.457 |  | 20.7128 | 34.0887 | 2025.1698 | 34.0887
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 12002 |  | 9.5395 | 4.6791 | 6.4651 | 14.4782 | 21.3601 | 27.0688 | [17 empty] | 46.226 | 37.3647 | 46.226 | 37.3647
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 14646 |  | 0.18154 | 0.02593 | 0.06373 | 0.34281 | 0.50235 | 0.67061 | [17 empty] | 1.0393 | 0.74762 | 1.0393 | 0.74762
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16000 |  | 5.218 | 2.5594 | 3.5363 | 7.9193 | 11.6837 | 14.8062 | [17 empty] | 25.2849 | 20.438 | 25.2849 | 20.438
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16006 |  | 8.7641 | 4.308 | 5.9524 | 12.721 | 19.6425 | 24.9221 | [17 empty] | 41.9511 | 34.3591 | 41.9511 | 34.3591
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | [19 empty] | 0.64988 |  | 0.64988
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16008 |  | 0.01968 |  |  |  | 0.0246 | [19 empty] | 0.04428 |  | 0.04428
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16012 |  | 1.7885 | 0.87753 | 1.2125 | 2.7365 | 4.0053 | 5.0766 | [17 empty] | 8.6907 | 7.0063 | 8.6907 | 7.0063
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16013 |  | 1.0151 | 0.49807 | 0.68819 | 1.5531 | 2.2733 | 2.8813 | [17 empty] | 4.9325 | 3.9766 | 4.9325 | 3.9766
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16014 |  | 7.9316 | 3.8988 | 5.387 | 11.5127 | 17.7768 | 22.5549 | [17 empty] | 37.9664 | 31.0954 | 37.9664 | 31.0954
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | [19 empty] | 0.99656 |  | 0.99656
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16020 |  | 0.01178 |  |  |  | 0.01474 | [19 empty] | 0.02652 |  | 0.02652
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16032 |  | 10.4209 | 5.1131 | 7.0648 | 15.9444 | 22.1601 | 28.0877 | [17 empty] | 49.1451 | 39.6459 | 49.1451 | 39.6459
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16033 |  | 3.5208 | 1.7275 | 2.3869 | 5.3869 | 7.8845 | 9.9935 | [17 empty] | 17.1078 | 13.7921 | 17.1078 | 13.7921
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16035 |  | 5.8556 | 2.8783 | 3.9771 | 8.4995 | 13.124 | 16.6515 | [17 empty] | 28.0293 | 22.9567 | 28.0293 | 22.9567
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | [19 empty] | 0.5563 |  | 0.5563
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | Result |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | Result | [5 empty] | 2.5742 |  | 0.23948 | [17 empty] | 2.8137 |  | 2.8137
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | [5 empty] | 2.5742 |  | 0.23948 | [17 empty] | 2.8137 |  | 2.8137
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | Result |  |  |  | 3.453 |  | 12.2697 |  | 2.0525 | [17 empty] | 17.7751 |  | 17.7751
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 |  |  |  | 2.6769 |  | 12.2697 |  | 2.0525 | [17 empty] | 16.9991 |  | 16.9991
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 |  |  |  | 0.77609 | [21 empty] | 0.77609 |  | 0.77609
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | Result |  | 17.035 |  | 2.7256 | 36.423 | 42.2241 | 72.846 | 12.9466 | [16 empty] | 109.269 | 74.9313 | 109.269 | 74.9313
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 |  | 17.035 |  | 2.7256 | 36.423 | 40.884 | 72.846 | 12.9466 | [16 empty] | 109.269 | 73.5912 | 109.269 | 73.5912
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | [5 empty] | 1.3401 | [19 empty] | 1.3401 |  | 1.3401
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | Result |  | 8.6362 | 12.682 | 11.3164 | 0.7594 | 0.37226 |  | 0.14891 | [16 empty] | 13.4414 | 20.4738 | 13.4414 | 20.4738
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 |  | 8.6362 | 12.682 | 11.3164 | 0.7594 | 0.37226 |  | 0.14891 | [16 empty] | 13.4414 | 20.4738 | 13.4414 | 20.4738
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 0.06964 | [17 empty] | 0.06964 |  | 0.06964
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | [7 empty] | 0.06964 | [17 empty] | 0.06964 |  | 0.06964
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | Result |  | 207.9742 | 122.3626 | 226.2317 | 148.8483 | 273.7493 | 205.6412 | 240.6514 | -18.5098 | [10 empty] | 1000 |  | 732.683 |  |  |  | 948.6066 | 458.3423 | 2681.2896 | 458.3423
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | Result | 146.3579 | 92.1128 | 157.027 | 108.6222 | 191.0131 | 158.7279 | 167.8054 | -25.9189 | [10 empty] | 1000 |  | 732.683 |  |  |  | 662.2034 | 333.544 | 2394.8864 | 333.544
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | # | 12 | 27.8803 | 10.5 | 23.6782 | 15.001 | 60.5287 | 15 | -25.9189 | [10 empty] | 1000 |  | 732.683 |  |  |  | 52.501 | 86.1683 | 1785.184 | 86.1683
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 11674 |  | 0.20299 | [23 empty] | 0.20299 |  | 0.20299
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 12002 | 22.9046 | 11.2377 | 25.7193 | 14.9557 | 30.7483 | 17.4707 | 27.0799 | [17 empty] | 106.452 | 43.6642 | 106.452 | 43.6642
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 14646 | 0.59055 | 0.27093 | 0.64684 | 0.39237 | 0.77346 | 0.53579 | 0.70061 | [17 empty] | 2.7115 | 1.1991 | 2.7115 | 1.1991
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16000 | 12.0121 | 6.1469 | 14.0681 | 8.1806 | 16.8189 | 9.5562 | 14.8123 | [17 empty] | 57.7114 | 23.8837 | 57.7114 | 23.8837
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16006 | 21.0881 | 10.2798 | 23.6796 | 13.5586 | 27.7009 | 15.7178 | 24.9323 | [17 empty] | 97.4009 | 39.5561 | 97.4009 | 39.5561
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | 0.01862 | [18 empty] | 0.64988 | 0.01862 | 0.64988 | 0.01862
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16008 |  |  |  | 0.19683 |  | 0.29524 | [19 empty] | 0.49207 |  | 0.49207
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16010 |  | 0.05097 |  | 0.01699 |  | 0.05097 | [19 empty] | 0.11893 |  | 0.11893
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16012 | 4.3128 | 2.1103 | 4.8235 | 2.7978 | 5.7879 | 3.2646 | 5.0787 | [17 empty] | 20.003 | 8.1727 | 20.003 | 8.1727
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16013 | 2.4478 | 1.1978 | 2.7377 | 1.588 | 3.285 | 1.8529 | 2.8825 | [17 empty] | 11.353 | 4.6386 | 11.353 | 4.6386
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16014 | 19.085 | 9.3033 | 21.4304 | 12.2707 | 25.0697 | 14.2248 | 22.5641 | [17 empty] | 88.1493 | 35.7989 | 88.1493 | 35.7989
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | 0.02854 | [18 empty] | 0.99656 | 0.02854 | 0.99656 | 0.02854
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16020 |  |  |  | 0.11789 |  | 0.17684 | [19 empty] | 0.29473 |  | 0.29473
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16032 | 27.841 | 12.296 | 28.1048 | 16.3019 | 33.7236 | 18.0621 | 28.0991 | [17 empty] | 117.7686 | 46.66 | 117.7686 | 46.66
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16033 | 8.9533 | 4.1542 | 9.4953 | 5.5076 | 11.3936 | 6.4265 | 9.9976 | [17 empty] | 39.8398 | 16.0883 | 39.8398 | 16.0883
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16034 |  | 0.11329 | [23 empty] | 0.11329 |  | 0.11329
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16035 | 15.1225 | 6.8683 | 15.8214 | 9.059 | 18.5081 | 10.5017 | 16.6583 | [17 empty] | 66.1102 | 26.4291 | 66.1102 | 26.4291
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | 0.01594 | [18 empty] | 0.5563 | 0.01594 | 0.5563 | 0.01594
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | Result |  | 0.19689 |  | 0.06563 |  | 0.19689 | [19 empty] | 0.45941 |  | 0.45941
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 |  | 0.19689 |  | 0.06563 |  | 0.19689 | [19 empty] | 0.45941 |  | 0.45941
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | Result |  |  |  | 0.55712 |  | 0.76604 | [19 empty] | 1.3232 |  | 1.3232
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 |  |  |  | 0.55712 |  | 0.76604 | [19 empty] | 1.3232 |  | 1.3232
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | Result |  | 1.5617 |  | 6.514 |  | 2.1864 |  | 0.4462 | [17 empty] | 10.7083 |  | 10.7083
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 |  | 1.5617 |  | 6.514 |  | 2.1864 |  | 0.4462 | [17 empty] | 10.7083 |  | 10.7083
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | Result | 61.6163 | 28.3727 | 69.2046 | 32.8965 | 80.94 | 42.9342 | 72.846 | 6.814 | [16 empty] | 284.6069 | 111.0175 | 284.6069 | 111.0175
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | 0.91128 | 1.1167 | 1.215 | 2.2335 |  | 2.6802 | [18 empty] | 2.1263 | 6.0305 | 2.1263 | 6.0305
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | 60.705 | 27.256 | 67.9896 | 30.663 | 80.94 | 40.2026 | 72.846 | 6.814 | [16 empty] | 282.4806 | 104.9356 | 282.4806 | 104.9356
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | [5 empty] | 0.05144 | [19 empty] | 0.05144 |  | 0.05144
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | Result |  | 0.11842 |  | 0.11842 |  | 0.23684 | [19 empty] | 0.47368 |  | 0.47368
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 |  | 0.11842 |  | 0.11842 |  | 0.23684 | [19 empty] | 0.47368 |  | 0.47368
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | Result |  |  |  | 0.07445 |  | 0.52327 |  | 0.14891 | [17 empty] | 0.74663 |  | 0.74663
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | [5 empty] | 0.07656 | [19 empty] | 0.07656 |  | 0.07656
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.44671 |  | 0.14891 | [17 empty] | 0.67007 |  | 0.67007
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | 08W | ESTS |  | Result |  | 0.5243 | 32.5544 | 0.5243 | 1.0255 | 0.5243 | 1.0255 | 0.5243 |  | 0.5243 |  | 0.5243 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.27178 |  |  |  | 2.0972 | 34.6054 | 5.5918 | 34.6054
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | 08W | ESTS |  | # | Result | 0.5243 | 32.5544 | 0.5243 | 1.0255 | 0.5243 | 1.0255 | 0.5243 |  | 0.5243 |  | 0.5243 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.27178 |  |  |  | 2.0972 | 34.6054 | 5.5918 | 34.6054
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | 08W | ESTS |  | # | # | 0.5243 | 32.5544 | 0.5243 | 1.0255 | 0.5243 | 1.0255 | 0.5243 |  | 0.5243 |  | 0.5243 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.54355 |  | 0.27178 |  |  |  | 2.0972 | 34.6054 | 5.5918 | 34.6054
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | Result |  | 0.37788 | 168.1935 | 136.9893 | 151.0552 | 104.7541 | 267.0229 | 122.8487 | 16.3968 | [12 empty] | 1000 |  | 1012.197 |  | 364.97 | 602.6684 | 2377.167 | 602.6684
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | Result | 0.37788 | 117.8967 | 96.1933 | 105.8874 | 74.6288 | 198.696 | 86.4257 | 4.4776 | [12 empty] | 1000 |  | 1012.197 |  | 257.6257 | 426.9577 | 2269.8227 | 426.9577
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | # | 0.37788 | 11.5062 | 10 | 9.8338 | 10 | 54.8836 | 10 | 4.4776 | [12 empty] | 1000 |  | 1012.197 |  | 30.3779 | 80.7011 | 2042.5749 | 80.7011
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 11674 |  |  |  | 0.25159 |  | 0.20058 | [19 empty] | 0.45217 |  | 0.45217
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 12002 |  | 18.6828 | 15.1552 | 16.7802 | 11.197 | 25.4169 | 13.5427 | [17 empty] | 39.895 | 60.8799 | 39.895 | 60.8799
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 14646 |  | 0.44411 | 0.36423 | 0.40584 | 0.28496 | 0.70315 | 0.35781 | [17 empty] | 1.007 | 1.5531 | 1.007 | 1.5531
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16000 |  | 10.2192 | 8.2897 | 9.1785 | 6.1246 | 13.9027 | 7.4077 | [17 empty] | 21.822 | 33.3004 | 21.822 | 33.3004
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16006 |  | 17.1823 | 13.8428 | 15.4495 | 9.7001 | 23.3776 | 12.4687 | [17 empty] | 36.0116 | 56.0093 | 36.0116 | 56.0093
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16007 |  |  |  |  | 0.64988 | [19 empty] | 0.64988 |  | 0.64988
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16008 |  | 0.01968 | 0.11519 |  |  | 0.0246 | [18 empty] | 0.11519 | 0.04428 | 0.11519 | 0.04428
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16012 |  | 3.5033 | 2.839 | 3.1554 | 2.1211 | 4.7728 | 2.5399 | [17 empty] | 7.5 | 11.4315 | 7.5 | 11.4315
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16013 |  | 1.9884 | 1.6113 | 1.7909 | 1.2039 | 2.7089 | 1.4415 | [17 empty] | 4.2567 | 6.4881 | 4.2567 | 6.4881
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16014 |  | 15.5502 | 12.528 | 13.982 | 8.7788 | 21.1571 | 11.2844 | [17 empty] | 32.5911 | 50.6893 | 32.5911 | 50.6893
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16017 |  |  |  |  | 0.99656 | [19 empty] | 0.99656 |  | 0.99656
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16020 |  | 0.01178 | 0.06899 |  |  | 0.01474 | [18 empty] | 0.06899 | 0.02652 | 0.06899 | 0.02652
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16032 |  | 20.4123 | 16.5414 | 18.3854 | 12.359 | 26.4066 | 14.0524 | [17 empty] | 42.9528 | 65.2043 | 42.9528 | 65.2043
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16033 |  | 6.8964 | 5.5886 | 6.2115 | 4.1755 | 9.3954 | 4.9998 | [17 empty] | 14.7639 | 22.5033 | 14.7639 | 22.5033
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16034 |  |  |  | 0.14041 |  | 0.11194 | [19 empty] | 0.25235 |  | 0.25235
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16035 |  | 11.4802 | 9.249 | 10.3224 | 6.4811 | 15.6196 | 8.3308 | [17 empty] | 24.0609 | 37.4222 | 24.0609 | 37.4222
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | # | 16036 |  |  |  |  | 0.5563 | [19 empty] | 0.5563 |  | 0.5563
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | Result |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 |  | 0.05569 | [23 empty] | 0.05569 |  | 0.05569
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | Result |  |  |  | 8.4111 |  | 3.0232 | [19 empty] | 11.4343 |  | 11.4343
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 |  |  |  | 8.4111 |  | 3.0232 | [19 empty] | 11.4343 |  | 11.4343
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | Result |  | 6.1123 |  | 8.7448 |  | 23.5124 |  | 5.9784 | [17 empty] | 44.348 |  | 44.348
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 |  | 6.1123 |  | 8.7448 |  | 23.5124 |  | 5.9784 | [17 empty] | 44.348 |  | 44.348
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | Result |  | 43.2008 | 40.47 | 27.9374 | 28.329 | 40.7818 | 36.423 | 5.7919 | [16 empty] | 105.222 | 117.7118 | 105.222 | 117.7118
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 |  | 43.2008 | 40.47 | 27.9374 | 28.329 | 40.7818 | 36.423 | 5.7919 | [16 empty] | 105.222 | 117.7118 | 105.222 | 117.7118
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | DSGNDT | Result |  | 0.0051 | [23 empty] | 0.0051 |  | 0.0051
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | DSGNDT | 12974 |  | 0.0051 | [23 empty] | 0.0051 |  | 0.0051
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | Result |  | 0.76974 |  |  |  | 0.41447 | [19 empty] | 1.1842 |  | 1.1842
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 |  | 0.76974 |  |  |  | 0.41447 | [19 empty] | 1.1842 |  | 1.1842
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | Result |  | 0.15312 |  | 0.07445 |  | 0.52538 |  | 0.14891 | [17 empty] | 0.90186 |  | 0.90186
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 |  | 0.15312 |  |  |  | 0.15312 | [19 empty] | 0.30624 |  | 0.30624
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.37226 |  | 0.14891 | [17 empty] | 0.59562 |  | 0.59562
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | Result |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 |  |  |  |  | 1.7962 | [19 empty] | 1.7962 |  | 1.7962
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | Result |  |  | 0.32605 | [21 empty] | 0.32605 |  | 0.32605
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 |  |  | 0.32605 | [21 empty] | 0.32605 |  | 0.32605
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | Result |  | 0.06803 | 2.5956 |  | 2.6495 |  | 2.5728 |  | -0.02 | [16 empty] | 0.06803 | 7.7979 | 0.06803 | 7.7979
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | Result | 0.06803 | 2.5956 |  | 2.5847 |  | 2.5728 |  | -0.02 | [16 empty] | 0.06803 | 7.7331 | 0.06803 | 7.7331
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | # | 0.06803 | 2.5956 |  | 2.4755 |  | 2.5728 |  | -0.02 | [16 empty] | 0.06803 | 7.6239 | 0.06803 | 7.6239
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 12002 |  |  |  | 0.02386 | [21 empty] | 0.02386 |  | 0.02386
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16000 |  |  |  | 0.01305 | [21 empty] | 0.01305 |  | 0.01305
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16008 |  |  |  | 0.02289 | [21 empty] | 0.02289 |  | 0.02289
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16012 |  |  |  | 0.00382 | [21 empty] | 0.00382 |  | 0.00382
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16013 |  |  |  | 0.00216 | [21 empty] | 0.00216 |  | 0.00216
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16020 |  |  |  | 0.01371 | [21 empty] | 0.01371 |  | 0.01371
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16032 |  |  |  | 0.02221 | [21 empty] | 0.02221 |  | 0.02221
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | # | 16033 |  |  |  | 0.0075 | [21 empty] | 0.0075 |  | 0.0075
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | Result |  |  |  | 0.0648 | [21 empty] | 0.0648 |  | 0.0648
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 |  |  |  | 0.0648 | [21 empty] | 0.0648 |  | 0.0648
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | Result |  |  | 6.4161 | 0.15909 | 2.0672 | 0.15909 | 2.7542 | 28.4401 | 0.07445 | 38.7421 |  | 0.15909 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.08376 |  | 28.7583 | 11.3119 | 68.5808 | 11.3119
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | Result |  | 6.4161 | 0.15909 | 1.9927 | 0.15909 | 2.4564 | 28.4401 |  | 38.7421 |  | 0.15909 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.08376 |  | 28.7583 | 10.8652 | 68.5808 | 10.8652
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | # |  | 6.3747 | 0.15909 | 1.8373 | 0.15909 | 1.8405 | 28.4401 |  | 38.7421 |  | 0.15909 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.16751 |  | 0.08376 |  | 28.7583 | 10.0524 | 68.5808 | 10.0524
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 12002 |  | 0.00493 |  | 0.02741 |  | 0.10965 | [19 empty] | 0.14199 |  | 0.14199
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 14646 |  | 0.01339 | [23 empty] | 0.01339 |  | 0.01339
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16000 |  | 0.0027 |  | 0.01499 |  | 0.05998 | [19 empty] | 0.07767 |  | 0.07767
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16006 |  | 0.00454 |  | 0.02524 |  | 0.10095 | [19 empty] | 0.13073 |  | 0.13073
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16012 |  | 0.00093 |  | 0.00514 |  | 0.02057 | [19 empty] | 0.02664 |  | 0.02664
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16013 |  | 0.00052 |  | 0.00292 |  | 0.01167 | [19 empty] | 0.01511 |  | 0.01511
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16014 |  | 0.00411 |  | 0.02284 |  | 0.09137 | [19 empty] | 0.11832 |  | 0.11832
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16032 |  | 0.00539 |  | 0.02996 |  | 0.11377 | [19 empty] | 0.14912 |  | 0.14912
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16033 |  | 0.00182 |  | 0.01012 |  | 0.04048 | [19 empty] | 0.05242 |  | 0.05242
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | # | 16035 |  | 0.00303 |  | 0.01686 |  | 0.06745 | [19 empty] | 0.08734 |  | 0.08734
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | Result |  |  |  | 0.07445 |  | 0.2978 |  | 0.07445 | [17 empty] | 0.4467 |  | 0.4467
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 |  |  |  | 0.07445 |  | 0.2978 |  | 0.07445 | [17 empty] | 0.4467 |  | 0.4467
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | Result |  | 0.26002 | 4.1342 | 0.26002 | 1.2853 | 0.26002 | 0.89924 | 0.26002 |  | 0.26002 |  | 0.26002 |  | 0.26957 |  | 0.26957 |  | 0.13478 | [7 empty] | 1.0401 | 6.3188 | 2.234 | 6.3188
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | Result | 0.26002 | 3.4551 | 0.26002 | 1.1461 | 0.26002 | 0.89924 | 0.26002 |  | 0.26002 |  | 0.26002 |  | 0.26957 |  | 0.26957 |  | 0.13478 | [7 empty] | 1.0401 | 5.5004 | 2.234 | 5.5004
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | # | 0.26002 | 2.3097 | 0.26002 | 0.91134 | 0.26002 | 0.89924 | 0.26002 |  | 0.26002 |  | 0.26002 |  | 0.26957 |  | 0.26957 |  | 0.13478 | [7 empty] | 1.0401 | 4.1203 | 2.234 | 4.1203
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 12002 |  | 0.25007 |  | 0.05128 | [21 empty] | 0.30135 |  | 0.30135
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16000 |  | 0.13678 |  | 0.02805 | [21 empty] | 0.16483 |  | 0.16483
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16006 |  | 0.00072 | [23 empty] | 0.00072 |  | 0.00072
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16008 |  | 0.2392 |  | 0.04921 | [21 empty] | 0.28841 |  | 0.28841
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16012 |  | 0.03997 |  | 0.00819 | [21 empty] | 0.04816 |  | 0.04816
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16013 |  | 0.02269 |  | 0.00465 | [21 empty] | 0.02734 |  | 0.02734
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16014 |  | 0.00065 | [23 empty] | 0.00065 |  | 0.00065
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16020 |  | 0.14326 |  | 0.02947 | [21 empty] | 0.17273 |  | 0.17273
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16032 |  | 0.23286 |  | 0.04773 | [21 empty] | 0.28059 |  | 0.28059
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16033 |  | 0.07869 |  | 0.01613 | [21 empty] | 0.09482 |  | 0.09482
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | # | 16035 |  | 0.00048 | [23 empty] | 0.00048 |  | 0.00048
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | Result |  | 0.2592 | [23 empty] | 0.2592 |  | 0.2592
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 |  | 0.2592 | [23 empty] | 0.2592 |  | 0.2592
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | Result |  | 0.41784 |  | 0.13928 | [21 empty] | 0.55712 |  | 0.55712
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 |  | 0.41784 |  | 0.13928 | [21 empty] | 0.55712 |  | 0.55712
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | EESTOT | Result |  | 0.00212 | [23 empty] | 0.00212 |  | 0.00212
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | EESTOT | 12974 |  | 0.00212 | [23 empty] | 0.00212 |  | 0.00212
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | Result |  | 0.52135 | 22.6104 | 11.8347 | 30.7325 | 11.8571 | 6.9168 | 10.6073 | 21.7795 | 0.63729 |  | 0.63729 |  | 0.32532 | [11 empty] | 34.8204 | 82.0392 | 36.4203 | 82.0392
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | Result | 0.52135 | 16.8544 | 8.1896 | 27.7518 | 8.212 | 5.8553 | 10.6073 | 21.705 | 0.63729 |  | 0.63729 |  | 0.32532 | [11 empty] | 27.5302 | 72.1666 | 29.1301 | 72.1666
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | # | 0.52135 | 12.2866 | 0.57697 | 24.3477 | 0.59937 | 3.9066 | 10.6073 | 21.705 | 0.63729 |  | 0.63729 |  | 0.32532 | [11 empty] | 12.305 | 62.2459 | 13.9049 | 62.2459
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 12002 |  | 2.1304 | 1.3421 | 1.1138 | 1.3421 | 0.39477 | [18 empty] | 2.6843 | 3.639 | 2.6843 | 3.639
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 14646 |  | 0.03007 |  | 0.04438 |  | 0.01069 | [19 empty] | 0.08514 |  | 0.08514
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16000 |  | 0.11846 | 0.73413 | 0.17763 | 0.73413 | 0.21595 | [18 empty] | 1.4683 | 0.51204 | 1.4683 | 0.51204
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16006 |  | 0.01019 | 1.2357 | 0.25481 | 1.2357 | 0.12683 | [18 empty] | 2.4714 | 0.39183 | 2.4714 | 0.39183
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16007 |  |  |  | 0.04716 | [21 empty] | 0.04716 |  | 0.04716
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16008 |  | 0.19717 |  |  |  | 0.24662 | [19 empty] | 0.44379 |  | 0.44379
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16012 |  | 0.20801 | 0.25171 | 0.13381 | 0.25171 | 0.0669 | [18 empty] | 0.50342 | 0.40872 | 0.50342 | 0.40872
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16013 |  | 0.11805 | 0.14286 | 0.07594 | 0.14286 | 0.03796 | [18 empty] | 0.28572 | 0.23195 | 0.28572 | 0.23195
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16014 |  | 0.00923 | 1.1183 | 0.2306 | 1.1183 | 0.11478 | [18 empty] | 2.2366 | 0.35461 | 2.2366 | 0.35461
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16017 |  |  |  | 0.07231 | [21 empty] | 0.07231 |  | 0.07231
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16020 |  | 0.11808 |  |  |  | 0.14771 | [19 empty] | 0.26579 |  | 0.26579
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16032 |  | 1.2119 | 1.4666 | 0.77963 | 1.4666 | 0.3701 | [18 empty] | 2.9332 | 2.3616 | 2.9332 | 2.3616
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16033 |  | 0.40943 | 0.4955 | 0.26339 | 0.4955 | 0.13165 | [18 empty] | 0.991 | 0.80447 | 0.991 | 0.80447
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16035 |  | 0.00681 | 0.82562 | 0.17026 | 0.82562 | 0.08474 | [18 empty] | 1.6512 | 0.26181 | 1.6512 | 0.26181
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | # | 16036 |  |  |  | 0.04037 | [21 empty] | 0.04037 |  | 0.04037
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | Result |  | 0.4536 | [23 empty] | 0.4536 |  | 0.4536
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 |  | 0.1944 | [23 empty] | 0.1944 |  | 0.1944
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 |  | 0.2592 | [23 empty] | 0.2592 |  | 0.2592
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | Result | [5 empty] | 0.37405 | [19 empty] | 0.37405 |  | 0.37405
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | [5 empty] | 0.37405 | [19 empty] | 0.37405 |  | 0.37405
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | Result |  | 0.66378 |  | 1.6595 | [21 empty] | 2.3232 |  | 2.3232
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 |  | 0.66378 |  | 1.6595 | [21 empty] | 2.3232 |  | 2.3232
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | Result |  |  |  | 0.67005 |  | 0.3262 | [19 empty] | 0.99625 |  | 0.99625
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 |  |  |  | 0.67005 | [21 empty] | 0.67005 |  | 0.67005
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | [5 empty] | 0.3262 | [19 empty] | 0.3262 |  | 0.3262
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | Result |  |  | 3.6451 | 0.16757 | 3.6451 | 0.03723 |  | 0.07446 | [16 empty] | 7.2902 | 0.27926 | 7.2902 | 0.27926
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 |  |  | 3.6451 | 0.03723 | 3.6451 | 0.03723 |  | 0.07446 | [16 empty] | 7.2902 | 0.14892 | 7.2902 | 0.14892
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 |  |  |  | 0.13034 | [21 empty] | 0.13034 |  | 0.13034
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | Result |  | 0.10446 | [23 empty] | 0.10446 |  | 0.10446
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 |  | 0.10446 | [23 empty] | 0.10446 |  | 0.10446
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | Result | [5 empty] | 0.324 | [19 empty] | 0.324 |  | 0.324
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | [5 empty] | 0.324 | [19 empty] | 0.324 |  | 0.324
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | Result |  | 4.5341 |  | 0.48364 | [21 empty] | 5.0178 |  | 5.0178
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 |  | 4.5341 |  | 0.48364 | [21 empty] | 5.0178 |  | 5.0178
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | 08W | ESTS |  | Result |  |  | 37.6225 |  | -14.9857 | [21 empty] | 22.6368 |  | 22.6368
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | 08W | ESTS |  | # | Result |  | 37.6225 |  | -14.9857 | [21 empty] | 22.6368 |  | 22.6368
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | 08W | ESTS |  | # | # |  | 37.6225 |  | -14.9857 | [21 empty] | 22.6368 |  | 22.6368
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | 08W | ESTS |  | Result |  | 0.00249 | 46.799 | 0.00249 | -20.4317 | 0.00249 | 0.15507 | 0.00249 |  | 0.00249 |  | 0.00249 |  | 0.00258 |  | 0.00258 |  | 0.00258 |  | 0.00129 | [5 empty] | 0.00996 | 26.5224 | 0.02397 | 26.5224
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | 08W | ESTS |  | # | Result | 0.00249 | 46.799 | 0.00249 | -20.4317 | 0.00249 | 0.15507 | 0.00249 |  | 0.00249 |  | 0.00249 |  | 0.00258 |  | 0.00258 |  | 0.00258 |  | 0.00129 | [5 empty] | 0.00996 | 26.5224 | 0.02397 | 26.5224
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | 08W | ESTS |  | # | # | 0.00249 | 46.799 | 0.00249 | -20.4317 | 0.00249 | 0.15507 | 0.00249 |  | 0.00249 |  | 0.00249 |  | 0.00258 |  | 0.00258 |  | 0.00258 |  | 0.00129 | [5 empty] | 0.00996 | 26.5224 | 0.02397 | 26.5224
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | 08W | UNSE |  | Result |  | 0.00082 | 0.05059 | 0.00082 | 3.8914 | 0.00082 | -3.7726 | 0.00082 |  | 0.00082 |  | 0.00082 |  | 0.00085 |  | 0.00085 |  | 0.00042 | [7 empty] | 0.00328 | 0.16931 | 0.00704 | 0.16931
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | 08W | UNSE |  | # | Result | 0.00082 | 0.05059 | 0.00082 | 3.8914 | 0.00082 | -3.7726 | 0.00082 |  | 0.00082 |  | 0.00082 |  | 0.00085 |  | 0.00085 |  | 0.00042 | [7 empty] | 0.00328 | 0.16931 | 0.00704 | 0.16931
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | 08W | UNSE |  | # | # | 0.00082 | 0.05059 | 0.00082 | 3.8914 | 0.00082 | -3.7726 | 0.00082 |  | 0.00082 |  | 0.00082 |  | 0.00085 |  | 0.00085 |  | 0.00042 | [7 empty] | 0.00328 | 0.16931 | 0.00704 | 0.16931
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | 08W | UNSE |  | Result |  |  | 0.11854 |  | 3.2952 |  | -3.0508 | [19 empty] | 0.36302 |  | 0.36302
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | 08W | UNSE |  | # | Result |  | 0.11854 |  | 3.2952 |  | -3.0508 | [19 empty] | 0.36302 |  | 0.36302
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | 08W | UNSE |  | # | # |  | 0.11854 |  | 3.2952 |  | -3.0508 | [19 empty] | 0.36302 |  | 0.36302
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | 08W | UNSE |  | Result |  | 0.00243 | 0.07509 | 0.00243 | 0.07155 | 0.00243 | 0.07155 | 0.00243 |  | 0.00243 |  | 0.00243 |  | 0.00252 |  | 0.00252 |  | 0.00126 | [7 empty] | 0.00972 | 0.21819 | 0.02088 | 0.21819
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | 08W | UNSE |  | # | Result | 0.00243 | 0.07509 | 0.00243 | 0.07155 | 0.00243 | 0.07155 | 0.00243 |  | 0.00243 |  | 0.00243 |  | 0.00252 |  | 0.00252 |  | 0.00126 | [7 empty] | 0.00972 | 0.21819 | 0.02088 | 0.21819
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | 08W | UNSE |  | # | # | 0.00243 | 0.07509 | 0.00243 | 0.07155 | 0.00243 | 0.07155 | 0.00243 |  | 0.00243 |  | 0.00243 |  | 0.00252 |  | 0.00252 |  | 0.00126 | [7 empty] | 0.00972 | 0.21819 | 0.02088 | 0.21819
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | Result |  |  | 15.9336 |  | 2.4418 |  | 1.971 |  | 0.48748 |  |  |  |  | 100 |  | 130 |  | 131.623 | [8 empty] | 20.834 | 361.623 | 20.834
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | Result |  | 15.4871 |  | 1.1911 |  | 1.6528 | [6 empty] | 100 |  | 130 |  | 131.623 | [8 empty] | 18.3311 | 361.623 | 18.3311
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | # |  | 14.6112 |  | -1.2648 |  | 1.0913 | [6 empty] | 100 |  | 130 |  | 131.623 | [8 empty] | 14.4376 | 361.623 | 14.4376
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 12002 |  | 0.17059 |  | 0.46527 |  | 0.11729 | [19 empty] | 0.75315 |  | 0.75315
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 14646 |  | 0.01679 |  | 0.01293 |  | 0.00032 | [19 empty] | 0.03004 |  | 0.03004
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16000 |  | 0.0933 |  | 0.25449 |  | 0.06415 | [19 empty] | 0.41194 |  | 0.41194
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16006 |  | 0.06591 |  | 0.26362 |  | 0.02535 | [19 empty] | 0.35488 |  | 0.35488
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16008 |  | 0.095 |  | 0.1717 |  | 0.08611 | [19 empty] | 0.35281 |  | 0.35281
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16012 |  | 0.02924 |  | 0.08228 |  | 0.0195 | [19 empty] | 0.13102 |  | 0.13102
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16013 |  | 0.0166 |  | 0.04671 |  | 0.01108 | [19 empty] | 0.07439 |  | 0.07439
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16014 |  | 0.05965 |  | 0.23858 |  | 0.02294 | [19 empty] | 0.32117 |  | 0.32117
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16020 |  | 0.05689 |  | 0.10284 |  | 0.05158 | [19 empty] | 0.21131 |  | 0.21131
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16032 |  | 0.17038 |  | 0.47942 |  | 0.1079 | [19 empty] | 0.7577 |  | 0.7577
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16033 |  | 0.05757 |  | 0.16198 |  | 0.03838 | [19 empty] | 0.25793 |  | 0.25793
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | # | 16035 |  | 0.04404 |  | 0.17614 |  | 0.01694 | [19 empty] | 0.23712 |  | 0.23712
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | Result | [5 empty] | 0.24374 |  | 0.27856 | [17 empty] | 0.5223 |  | 0.5223
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | [5 empty] | 0.24374 |  | 0.27856 | [17 empty] | 0.5223 |  | 0.5223
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | Result |  |  |  | 0.67005 | [21 empty] | 0.67005 |  | 0.67005
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 |  |  |  | 0.67005 | [21 empty] | 0.67005 |  | 0.67005
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | Result |  | 0.17763 | [23 empty] | 0.17763 |  | 0.17763
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 |  | 0.17763 | [23 empty] | 0.17763 |  | 0.17763
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | Result |  |  |  | 0.09465 |  | 0.07446 | [19 empty] | 0.16911 |  | 0.16911
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 |  |  |  | 0.05742 | [21 empty] | 0.05742 |  | 0.05742
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 |  |  |  | 0.03723 |  | 0.07446 | [19 empty] | 0.11169 |  | 0.11169
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | Result |  | 0.13928 | [5 empty] | 0.20892 | [17 empty] | 0.3482 |  | 0.3482
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 |  | 0.13928 | [5 empty] | 0.20892 | [17 empty] | 0.3482 |  | 0.3482
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | Result |  |  |  | 0.486 | [21 empty] | 0.486 |  | 0.486
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 |  |  |  | 0.486 | [21 empty] | 0.486 |  | 0.486
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | Result |  | 0.1296 | [23 empty] | 0.1296 |  | 0.1296
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 |  | 0.1296 | [23 empty] | 0.1296 |  | 0.1296
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | Result |  |  | 14.9324 |  | 7.7219 | 10.0927 | 25.0486 | 15.15 | -24.57 | 2.793 | [5 empty] | 400 |  | 67.253 | [7 empty] | 25.2427 | 23.1329 | 495.2887 | 23.1329
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | Result |  | 14.3187 |  | 5.3787 | 10.0927 | 24.9507 | 15.15 | -24.57 | 2.793 | [5 empty] | 400 |  | 67.253 | [7 empty] | 25.2427 | 20.0782 | 495.2887 | 20.0782
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | # |  | 13.0671 |  | 0.54308 | 10 | 24.7876 | 15.15 | -24.57 | 2.793 | [5 empty] | 400 |  | 67.253 | [7 empty] | 25.15 | 13.8278 | 495.196 | 13.8278
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 12002 |  | 0.23195 |  | 0.86521 | 0.01105 | 0.03601 | [18 empty] | 0.01105 | 1.1332 | 0.01105 | 1.1332
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 14646 |  | 0.01625 |  | 0.00659 | 0.03 | [19 empty] | 0.03 | 0.02284 | 0.03 | 0.02284
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16000 |  | 0.12687 |  | 0.47325 | 0.00604 | 0.0197 | [18 empty] | 0.00604 | 0.61982 | 0.00604 | 0.61982
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16006 |  | 0.14602 |  | 0.73068 | 0.01017 | [19 empty] | 0.01017 | 0.8767 | 0.01017 | 0.8767
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16008 |  | 0.07039 |  | 0.06868 |  | 0.03456 | [19 empty] | 0.17363 |  | 0.17363
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16012 |  | 0.04146 |  | 0.16028 | 0.00207 | 0.00576 | [18 empty] | 0.00207 | 0.2075 | 0.00207 | 0.2075
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16013 |  | 0.02352 |  | 0.09097 | 0.00118 | 0.00327 | [18 empty] | 0.00118 | 0.11776 | 0.00118 | 0.11776
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16014 |  | 0.13214 |  | 0.66128 | 0.0092 | [19 empty] | 0.0092 | 0.79342 | 0.0092 | 0.79342
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16020 |  | 0.04216 |  | 0.04114 |  | 0.0207 | [19 empty] | 0.104 |  | 0.104
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16032 |  | 0.2416 |  | 0.93387 | 0.01207 | 0.03183 | [18 empty] | 0.01207 | 1.2073 | 0.01207 | 1.2073
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16033 |  | 0.08162 |  | 0.31549 | 0.00408 | 0.01132 | [18 empty] | 0.00408 | 0.40843 | 0.00408 | 0.40843
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | # | 16035 |  | 0.09756 |  | 0.4882 | 0.0068 | [19 empty] | 0.0068 | 0.58576 | 0.0068 | 0.58576
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | Result |  |  |  | 0.1944 | [21 empty] | 0.1944 |  | 0.1944
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 |  |  |  | 0.1944 | [21 empty] | 0.1944 |  | 0.1944
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | Result | [5 empty] | 0.09781 | [19 empty] | 0.09781 |  | 0.09781
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | [5 empty] | 0.09781 | [19 empty] | 0.09781 |  | 0.09781
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | Result |  | 0.41447 | [23 empty] | 0.41447 |  | 0.41447
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 |  | 0.41447 | [23 empty] | 0.41447 |  | 0.41447
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | Result |  |  |  | 0.59123 | [21 empty] | 0.59123 |  | 0.59123
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 |  |  |  | 0.51678 | [21 empty] | 0.51678 |  | 0.51678
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 |  |  |  | 0.07445 | [21 empty] | 0.07445 |  | 0.07445
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | Result |  |  |  | 1.5576 | [21 empty] | 1.5576 |  | 1.5576
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 |  |  |  | 1.5576 | [21 empty] | 1.5576 |  | 1.5576
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | Result |  | 0.06964 | [23 empty] | 0.06964 |  | 0.06964
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 |  | 0.06964 | [23 empty] | 0.06964 |  | 0.06964
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | Result |  | 0.1296 | [23 empty] | 0.1296 |  | 0.1296
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 |  | 0.1296 | [23 empty] | 0.1296 |  | 0.1296
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | Result |  |  | 11.2974 |  | 0.40958 |  | 46.9446 | 10 |  |  |  | 500 |  | 500 |  | 443.055 |  | 8.295 | [7 empty] | 10 | 58.6516 | 1461.35 | 58.6516
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | Result |  | 8.9815 |  | 0.00825 |  | 46.4145 | 10 |  |  |  | 500 |  | 500 |  | 443.055 |  | 8.295 | [7 empty] | 10 | 55.4042 | 1461.35 | 55.4042
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | # |  | 4.4854 |  | -0.82258 |  | 45.4995 | 10 |  |  |  | 500 |  | 500 |  | 443.055 |  | 8.295 | [7 empty] | 10 | 49.1624 | 1461.35 | 49.1624
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 12002 |  | 0.85277 |  | 0.15157 |  | 0.1952 | [19 empty] | 1.1995 |  | 1.1995
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 14646 |  | 7e-05 |  | 0.01032 | [21 empty] | 0.01039 |  | 0.01039
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16000 |  | 0.46645 |  | 0.0829 |  | 0.10677 | [19 empty] | 0.65612 |  | 0.65612
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16006 |  | 0.49857 |  | 0.1066 |  | 0.02595 | [19 empty] | 0.63112 |  | 0.63112
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16008 |  | 0.29865 |  | 0.03434 |  | 0.16026 | [19 empty] | 0.49325 |  | 0.49325
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16012 |  | 0.15127 |  | 0.02743 |  | 0.03197 | [19 empty] | 0.21067 |  | 0.21067
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16013 |  | 0.08586 |  | 0.01557 |  | 0.01815 | [19 empty] | 0.11958 |  | 0.11958
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16014 |  | 0.45122 |  | 0.09648 |  | 0.02349 | [19 empty] | 0.57119 |  | 0.57119
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16020 |  | 0.17887 |  | 0.02057 |  | 0.09598 | [19 empty] | 0.29542 |  | 0.29542
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16032 |  | 0.88142 |  | 0.15985 |  | 0.17687 | [19 empty] | 1.2181 |  | 1.2181
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16033 |  | 0.29777 |  | 0.05398 |  | 0.06292 | [19 empty] | 0.41467 |  | 0.41467
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | # | 16035 |  | 0.33312 |  | 0.07122 |  | 0.01734 | [19 empty] | 0.42168 |  | 0.42168
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | Result |  | 0.1944 |  | 0.0972 |  | 0.1296 | [19 empty] | 0.4212 |  | 0.4212
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 |  | 0.1944 |  | 0.0972 |  | 0.1296 | [19 empty] | 0.4212 |  | 0.4212
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | Result |  | 0.35205 | [23 empty] | 0.35205 |  | 0.35205
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 |  | 0.35205 | [23 empty] | 0.35205 |  | 0.35205
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | Result |  | 1.1484 |  | 0.30413 |  | 0.07656 | [19 empty] | 1.5291 |  | 1.5291
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 |  | 1.1484 |  | 0.22968 |  | 0.07656 | [19 empty] | 1.4546 |  | 1.4546
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 |  |  |  | 0.07445 | [21 empty] | 0.07445 |  | 0.07445
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | Result |  | 0.32226 | [23 empty] | 0.32226 |  | 0.32226
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 |  | 0.32226 | [23 empty] | 0.32226 |  | 0.32226
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | Result |  | 0.10446 | [23 empty] | 0.10446 |  | 0.10446
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 |  | 0.10446 | [23 empty] | 0.10446 |  | 0.10446
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | Result | [5 empty] | 0.324 | [19 empty] | 0.324 |  | 0.324
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | [5 empty] | 0.324 | [19 empty] | 0.324 |  | 0.324
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | Result |  | 0.1944 | [23 empty] | 0.1944 |  | 0.1944
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 |  | 0.1944 | [23 empty] | 0.1944 |  | 0.1944
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | Result |  |  | 0.23715 |  | 12.6329 |  | 21.2717 | 20.7735 | 1.8407 | 0.2141 |  | 87.3441 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 0.21763 |  | 0.21763 |  | 20.7735 | 35.9824 | 509.6375 | 35.9824
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | Result |  | 0.16059 |  | 9.5623 |  | 14.0288 | 16.7957 | 0.38706 | 0.2141 |  | 87.3441 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 0.21763 |  | 0.21763 |  | 16.7957 | 24.1387 | 505.6596 | 24.1387
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | # |  | 0.00069 |  | 3.845 |  | 1.9098 | 10.161 | 0.38706 | 0.2141 |  | 87.3441 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 100.2176 |  | 0.21763 |  | 0.21763 |  | 10.161 | 6.1426 | 499.025 | 6.1426
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 12002 |  | 0.02819 |  | 1.1348 |  | 2.6688 | 1.4646 | [17 empty] | 1.4646 | 3.8318 | 1.4646 | 3.8318
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 14646 |  |  |  | 0.01142 |  | 0.00532 | [19 empty] | 0.01674 |  | 0.01674
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16000 |  | 0.01542 |  | 0.62073 |  | 1.4598 | 0.80113 | [17 empty] | 0.80113 | 2.0959 | 0.80113 | 2.0959
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16006 |  | 0.02595 |  | 0.43039 |  | 0.02059 | [19 empty] | 0.47693 |  | 0.47693
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16008 |  |  |  | 0.64034 |  | 2.5393 | 1.4054 | [17 empty] | 1.4054 | 3.1797 | 1.4054 | 3.1797
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16012 |  | 0.00529 |  | 0.19429 |  | 0.42695 | 0.23397 | [17 empty] | 0.23397 | 0.62653 | 0.23397 | 0.62653
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16013 |  | 0.003 |  | 0.11026 |  | 0.24232 | 0.13279 | [17 empty] | 0.13279 | 0.35558 | 0.13279 | 0.35558
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16014 |  | 0.02349 |  | 0.38951 |  | 0.01864 | [19 empty] | 0.43164 |  | 0.43164
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16020 |  |  |  | 0.38352 |  | 1.5209 | 0.8417 | [17 empty] | 0.8417 | 1.9044 | 0.8417 | 1.9044
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16032 |  | 0.03081 |  | 1.132 |  | 2.3622 | 1.2945 | [17 empty] | 1.2945 | 3.525 | 1.2945 | 3.525
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16033 |  | 0.01041 |  | 0.38243 |  | 0.84045 | 0.46057 | [17 empty] | 0.46057 | 1.2333 | 0.46057 | 1.2333
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | # | 16035 |  | 0.01734 |  | 0.28756 |  | 0.01376 | [19 empty] | 0.31866 |  | 0.31866
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | Result |  |  |  | 0.35204 |  | 2.0682 |  | 0.35204 | [17 empty] | 2.7723 |  | 2.7723
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 |  |  |  | 0.35204 |  | 2.0682 |  | 0.35204 | [17 empty] | 2.7723 |  | 2.7723
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | Result | [5 empty] | 0.05544 | [19 empty] | 0.05544 |  | 0.05544
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | [5 empty] | 0.05544 | [19 empty] | 0.05544 |  | 0.05544
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | Result |  | 0.07656 |  | 0.07656 | [21 empty] | 0.15312 |  | 0.15312
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 |  | 0.07656 |  | 0.07656 | [21 empty] | 0.15312 |  | 0.15312
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | Result |  |  |  | 1.1816 | [21 empty] | 1.1816 |  | 1.1816
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 |  |  |  | 1.1816 | [21 empty] | 1.1816 |  | 1.1816
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | Result |  |  |  | 0.03482 | [21 empty] | 0.03482 |  | 0.03482
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 |  |  |  | 0.03482 | [21 empty] | 0.03482 |  | 0.03482
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | Result |  |  |  | 1.3608 |  | 5.1192 | 3.9778 | 1.1016 | [16 empty] | 3.9778 | 7.5816 | 3.9778 | 7.5816
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 |  |  |  | 1.3608 |  | 5.1192 | 3.9778 | 1.1016 | [16 empty] | 3.9778 | 7.5816 | 3.9778 | 7.5816
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | Result |  |  |  | 0.0648 | [21 empty] | 0.0648 |  | 0.0648
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 |  |  |  | 0.0648 | [21 empty] | 0.0648 |  | 0.0648
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | Result |  |  | 0.33092 |  | 10.0833 |  | 14.9788 | 20.7864 | 1.4539 | [16 empty] | 20.7864 | 26.8469 | 20.7864 | 26.8469
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | Result |  | 0.21954 |  | 7.7394 |  | 10.0715 | 16.7434 | 0.39384 | [16 empty] | 16.7434 | 18.4243 | 16.7434 | 18.4243
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | # |  | 0.00096 |  | 3.5418 |  | 1.8704 | 10 | 0.39384 | [16 empty] | 10 | 5.8069 | 10 | 5.8069
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 12002 |  | 0.04101 |  | 0.86689 |  | 1.8088 | 1.4886 | [17 empty] | 1.4886 | 2.7167 | 1.4886 | 2.7167
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 14646 |  |  |  | 0.01053 |  | 0.00523 | [19 empty] | 0.01576 |  | 0.01576
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16000 |  | 0.02243 |  | 0.47417 |  | 0.98939 | 0.81426 | [17 empty] | 0.81426 | 1.486 | 0.81426 | 1.486
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16006 |  | 0.02595 |  | 0.18453 |  | 0.00177 | [19 empty] | 0.21225 |  | 0.21225
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16008 |  | 0.0123 |  | 0.63949 |  | 1.7338 | 1.4284 | [17 empty] | 1.4284 | 2.3856 | 1.4284 | 2.3856
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16012 |  | 0.00734 |  | 0.14406 |  | 0.28901 | 0.2378 | [17 empty] | 0.2378 | 0.44041 | 0.2378 | 0.44041
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16013 |  | 0.00416 |  | 0.08175 |  | 0.16404 | 0.13497 | [17 empty] | 0.13497 | 0.24995 | 0.13497 | 0.24995
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16014 |  | 0.02349 |  | 0.167 |  | 0.0016 | [19 empty] | 0.19209 |  | 0.19209
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16020 |  | 0.00737 |  | 0.38301 |  | 1.0384 | 0.8555 | [17 empty] | 0.8555 | 1.4288 | 0.8555 | 1.4288
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16032 |  | 0.04275 |  | 0.83935 |  | 1.599 | 1.3157 | [17 empty] | 1.3157 | 2.4811 | 1.3157 | 2.4811
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16033 |  | 0.01444 |  | 0.28357 |  | 0.56892 | 0.46813 | [17 empty] | 0.46813 | 0.86693 | 0.46813 | 0.86693
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | # | 16035 |  | 0.01734 |  | 0.1233 |  | 0.00118 | [19 empty] | 0.14182 |  | 0.14182
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | Result |  |  |  | 0.22003 |  | 1.4082 | 0.06521 | 0.08801 | [16 empty] | 0.06521 | 1.7162 | 0.06521 | 1.7162
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 |  |  |  | 0.22003 |  | 1.4082 | 0.06521 | 0.08801 | [16 empty] | 0.06521 | 1.7162 | 0.06521 | 1.7162
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | Result |  | 0.07656 |  | 0.53381 | [21 empty] | 0.61037 |  | 0.61037
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 |  | 0.07656 |  | 0.45936 | [21 empty] | 0.53592 |  | 0.53592
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 |  |  |  | 0.07445 | [21 empty] | 0.07445 |  | 0.07445
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | Result |  | 0.03482 |  | 0.03482 | [21 empty] | 0.06964 |  | 0.06964
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 |  |  |  | 0.03482 | [21 empty] | 0.03482 |  | 0.03482
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 |  | 0.03482 | [23 empty] | 0.03482 |  | 0.03482
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | Result |  |  |  | 1.5228 |  | 3.4992 | 3.9778 | 0.972 | [16 empty] | 3.9778 | 5.994 | 3.9778 | 5.994
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 |  |  |  | 1.5228 |  | 3.4992 | 3.9778 | 0.972 | [16 empty] | 3.9778 | 5.994 | 3.9778 | 5.994
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | Result |  |  |  | 0.0324 | [21 empty] | 0.0324 |  | 0.0324
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 |  |  |  | 0.0324 | [21 empty] | 0.0324 |  | 0.0324
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | Result |  |  |  |  | 2.6176 | 10.0927 | 2.9628 | 5.7339 |  | 36.664 |  | 0.27352 |  | 0.27638 |  | 0.27638 |  | 350.3674 |  | 0.27638 |  | 0.27638 |  | 0.27638 |  | 15.8265 | 5.5804 | 404.5134 | 5.5804
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | Result |  |  |  | 1.7532 | 10.0927 | 1.8612 | 5.473 |  | 36.664 |  | 0.27352 |  | 0.27638 |  | 0.27638 |  | 350.3674 |  | 0.27638 |  | 0.27638 |  | 0.27638 |  | 15.5657 | 3.6143 | 404.2525 | 3.6143
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | # |  |  |  | 0.00761 | 10 | 0.02377 | 5.038 |  | 36.664 |  | 0.27352 |  | 0.27638 |  | 0.27638 |  | 350.3674 |  | 0.27638 |  | 0.27638 |  | 0.27638 |  | 15.038 | 0.03138 | 403.7248 | 0.03138
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 12002 |  |  |  | 0.32051 | 0.01105 | 0.40561 | 0.09604 | [17 empty] | 0.10709 | 0.72612 | 0.10709 | 0.72612
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 14646 |  |  |  | 0.00603 | 0.03 | [19 empty] | 0.03 | 0.00603 | 0.03 | 0.00603
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16000 |  |  |  | 0.17531 | 0.00604 | 0.22186 | 0.05253 | [17 empty] | 0.05857 | 0.39717 | 0.05857 | 0.39717
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16006 |  |  |  | 0.22919 | 0.01017 | [19 empty] | 0.01017 | 0.22919 | 0.01017 | 0.22919
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16008 |  |  |  | 0.06868 |  | 0.3892 | 0.09215 | [17 empty] | 0.09215 | 0.45788 | 0.09215 | 0.45788
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16012 |  |  |  | 0.05812 | 0.00207 | 0.06479 | 0.01535 | [17 empty] | 0.01742 | 0.12291 | 0.01742 | 0.12291
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16013 |  |  |  | 0.03298 | 0.00118 | 0.03678 | 0.0087 | [17 empty] | 0.00988 | 0.06976 | 0.00988 | 0.06976
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16014 |  |  |  | 0.20742 | 0.0092 | [19 empty] | 0.0092 | 0.20742 | 0.0092 | 0.20742
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16020 |  |  |  | 0.04114 |  | 0.2331 | 0.05519 | [17 empty] | 0.05519 | 0.27424 | 0.05519 | 0.27424
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16032 |  |  |  | 0.33865 | 0.01207 | 0.3585 | 0.08487 | [17 empty] | 0.09694 | 0.69715 | 0.09694 | 0.69715
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16033 |  |  |  | 0.11441 | 0.00408 | 0.12755 | 0.0302 | [17 empty] | 0.03428 | 0.24196 | 0.03428 | 0.24196
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | # | 16035 |  |  |  | 0.15314 | 0.0068 | [19 empty] | 0.0068 | 0.15314 | 0.0068 | 0.15314
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | Result |  |  |  | 0.67005 | [21 empty] | 0.67005 |  | 0.67005
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 |  |  |  | 0.67005 | [21 empty] | 0.67005 |  | 0.67005
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | Result |  |  |  | 0.1944 |  | 1.1016 | 0.26084 | [17 empty] | 0.26084 | 1.296 | 0.26084 | 1.296
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 |  |  |  | 0.1944 |  | 1.1016 | 0.26084 | [17 empty] | 0.26084 | 1.296 | 0.26084 | 1.296
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | Result |  |  |  |  | 2.0941 | 10.0927 | 0.11852 | 5.9667 |  | 36.6537 |  | 0.26316 |  | 0.26581 |  | 0.26581 |  | 353.5758 |  | 0.26581 |  | 0.26581 |  | 0.26581 |  | 16.0594 | 2.2126 | 407.881 | 2.2126
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | Result |  |  |  | 1.4241 | 10.0927 | 0.11852 | 5.6629 |  | 36.6537 |  | 0.26316 |  | 0.26581 |  | 0.26581 |  | 353.5758 |  | 0.26581 |  | 0.26581 |  | 0.26581 |  | 15.7556 | 1.5426 | 407.5773 | 1.5426
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | # |  |  |  | 0.00608 | 10 | 0.11753 | 5.0263 |  | 36.6537 |  | 0.26316 |  | 0.26581 |  | 0.26581 |  | 353.5758 |  | 0.26581 |  | 0.26581 |  | 0.26581 |  | 15.0263 | 0.12361 | 406.848 | 0.12361
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 12002 |  |  |  | 0.24893 | 0.01105 | 0.00012 | 0.11285 | [17 empty] | 0.1239 | 0.24905 | 0.1239 | 0.24905
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 14646 |  |  |  | 0.00603 | 0.03 | 0.00032 | 0.00273 | [17 empty] | 0.03273 | 0.00635 | 0.03273 | 0.00635
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16000 |  |  |  | 0.13616 | 0.00604 | 6e-05 | 0.06173 | [17 empty] | 0.06777 | 0.13622 | 0.06777 | 0.13622
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16006 |  |  |  | 0.22919 | 0.01017 | 0.00011 | 0.1039 | [17 empty] | 0.11407 | 0.2293 | 0.11407 | 0.2293
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16012 |  |  |  | 0.04669 | 0.00207 | 2e-05 | 0.02117 | [17 empty] | 0.02324 | 0.04671 | 0.02324 | 0.04671
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16013 |  |  |  | 0.02649 | 0.00118 | 2e-05 | 0.01201 | [17 empty] | 0.01319 | 0.02651 | 0.01319 | 0.02651
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16014 |  |  |  | 0.20742 | 0.0092 | 0.0001 | 0.09403 | [17 empty] | 0.10323 | 0.20752 | 0.10323 | 0.20752
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16032 |  |  |  | 0.27203 | 0.01207 | 0.00013 | 0.1171 | [17 empty] | 0.12917 | 0.27216 | 0.12917 | 0.27216
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16033 |  |  |  | 0.09191 | 0.00408 | 4e-05 | 0.04167 | [17 empty] | 0.04575 | 0.09195 | 0.04575 | 0.09195
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | # | 16035 |  |  |  | 0.15314 | 0.0068 | 7e-05 | 0.06942 | [17 empty] | 0.07622 | 0.15321 | 0.07622 | 0.15321
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | Result |  |  |  | 0.67005 |  |  | 0.30376 | [17 empty] | 0.30376 | 0.67005 | 0.30376 | 0.67005
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 |  |  |  | 0.67005 |  |  | 0.30376 | [17 empty] | 0.30376 | 0.67005 | 0.30376 | 0.67005
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | Result |  |  |  |  | 1.9963 |  | 10.7394 |  | 0.10446 |  |  |  |  | 824.003 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  |  | 12.8402 | 4824.003 | 12.8402
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | Result |  |  |  | 1.3518 |  | 7.2354 | [6 empty] | 824.003 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  |  | 8.5872 | 4824.003 | 8.5872
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | # |  |  |  | 0.0058 |  | 0.04275 | [6 empty] | 824.003 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  |  | 0.04855 | 4824.003 | 0.04855
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 12002 |  |  |  | 0.23731 |  | 1.2904 | [19 empty] | 1.5277 |  | 1.5277
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 14646 | [5 empty] | 0.0005 | [19 empty] | 0.0005 |  | 0.0005
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16000 |  |  |  | 0.12981 |  | 0.70581 | [19 empty] | 0.83562 |  | 0.83562
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16006 |  |  |  | 0.21849 |  | 1.1408 | [19 empty] | 1.3593 |  | 1.3593
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16008 | [5 empty] | 0.04921 | [19 empty] | 0.04921 |  | 0.04921
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16012 |  |  |  | 0.0445 |  | 0.2406 | [19 empty] | 0.2851 |  | 0.2851
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16013 |  |  |  | 0.02526 |  | 0.13654 | [19 empty] | 0.1618 |  | 0.1618
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16014 |  |  |  | 0.19774 |  | 1.0324 | [19 empty] | 1.2302 |  | 1.2302
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16020 | [5 empty] | 0.02947 | [19 empty] | 0.02947 |  | 0.02947
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16032 |  |  |  | 0.25932 |  | 1.3311 | [19 empty] | 1.5904 |  | 1.5904
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16033 |  |  |  | 0.08761 |  | 0.4736 | [19 empty] | 0.56121 |  | 0.56121
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | # | 16035 |  |  |  | 0.14598 |  | 0.76222 | [19 empty] | 0.9082 |  | 0.9082
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | Result | [5 empty] | 0.05544 | [19 empty] | 0.05544 |  | 0.05544
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | [5 empty] | 0.05544 | [19 empty] | 0.05544 |  | 0.05544
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | Result | [5 empty] | 2.4499 | [19 empty] | 2.4499 |  | 2.4499
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | [5 empty] | 2.4499 | [19 empty] | 2.4499 |  | 2.4499
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | Result |  |  |  | 0.64452 |  | 0.85936 | [19 empty] | 1.5039 |  | 1.5039
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 |  |  |  | 0.64452 |  | 0.85936 | [19 empty] | 1.5039 |  | 1.5039
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | Result | [5 empty] | 0.13928 |  | 0.10446 | [17 empty] | 0.24374 |  | 0.24374
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | [5 empty] | 0.13928 |  | 0.10446 | [17 empty] | 0.24374 |  | 0.24374
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | Result | [6 empty] | 25.6478 | 10.5355 | -24.57 | 0.067 |  | 250.067 |  | 250.068 |  | 14.343 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 10.5355 | 1.0778 | 525.3526 | 1.0778
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | Result | [5 empty] | 25.3117 | 10.5355 | -24.57 | 0.067 |  | 250.067 |  | 250.068 |  | 14.343 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 10.5355 | 0.74171 | 525.3526 | 0.74171
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | # | [5 empty] | 24.6445 | 10.5355 | -24.57 | 0.067 |  | 250.067 |  | 250.068 |  | 14.343 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 0.06802 |  | 10.5355 | 0.07448 | 525.3526 | 0.07448
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 12002 | [5 empty] | 0.12375 | [19 empty] | 0.12375 |  | 0.12375
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16000 | [5 empty] | 0.06769 | [19 empty] | 0.06769 |  | 0.06769
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16006 | [5 empty] | 0.09033 | [19 empty] | 0.09033 |  | 0.09033
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16008 | [5 empty] | 0.0246 | [19 empty] | 0.0246 |  | 0.0246
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16012 | [5 empty] | 0.02249 | [19 empty] | 0.02249 |  | 0.02249
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16013 | [5 empty] | 0.01278 | [19 empty] | 0.01278 |  | 0.01278
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16014 | [5 empty] | 0.08175 | [19 empty] | 0.08175 |  | 0.08175
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16020 | [5 empty] | 0.01474 | [19 empty] | 0.01474 |  | 0.01474
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16032 | [5 empty] | 0.12446 | [19 empty] | 0.12446 |  | 0.12446
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16033 | [5 empty] | 0.04429 | [19 empty] | 0.04429 |  | 0.04429
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | # | 16035 | [5 empty] | 0.06035 | [19 empty] | 0.06035 |  | 0.06035
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | Result | [5 empty] | 0.26645 | [19 empty] | 0.26645 |  | 0.26645
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | [5 empty] | 0.26645 | [19 empty] | 0.26645 |  | 0.26645
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | Result | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | [5 empty] | 0.06964 | [19 empty] | 0.06964 |  | 0.06964
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | Result |  |  |  |  | 0.26178 | 10.0927 | 25.2065 | 11.04 | -24.57 | 1.758 | [7 empty] | 400 |  | 89.646 | [5 empty] | 21.1327 | 0.89831 | 512.5367 | 0.89831
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | Result |  |  |  | 0.16458 | 10.0927 | 24.9959 | 11.04 | -24.57 | 1.758 | [7 empty] | 400 |  | 89.646 | [5 empty] | 21.1327 | 0.59051 | 512.5367 | 0.59051
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | # |  |  |  | 0.00076 | 10 | 24.6447 | 11.04 | -24.57 | 1.758 | [7 empty] | 400 |  | 89.646 | [5 empty] | 21.04 | 0.07547 | 512.444 | 0.07547
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 12002 |  |  |  | 0.03579 | 0.01105 | 0.07754 | [18 empty] | 0.01105 | 0.11333 | 0.01105 | 0.11333
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 14646 |  |  |  |  | 0.03 | [19 empty] | 0.03 |  | 0.03
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16000 |  |  |  | 0.01958 | 0.00604 | 0.04241 | [18 empty] | 0.00604 | 0.06199 | 0.00604 | 0.06199
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16006 |  |  |  |  | 0.01017 | [19 empty] | 0.01017 |  | 0.01017
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16008 |  |  |  | 0.03434 |  | 0.0744 | [19 empty] | 0.10874 |  | 0.10874
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16012 |  |  |  | 0.00572 | 0.00207 | 0.01238 | [18 empty] | 0.00207 | 0.0181 | 0.00207 | 0.0181
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16013 |  |  |  | 0.00325 | 0.00118 | 0.00703 | [18 empty] | 0.00118 | 0.01028 | 0.00118 | 0.01028
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16014 |  |  |  |  | 0.0092 | [19 empty] | 0.0092 |  | 0.0092
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16020 |  |  |  | 0.02057 |  | 0.04456 | [19 empty] | 0.06513 |  | 0.06513
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16032 |  |  |  | 0.03331 | 0.01207 | 0.06852 | [18 empty] | 0.01207 | 0.10183 | 0.01207 | 0.10183
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16033 |  |  |  | 0.01126 | 0.00408 | 0.02438 | [18 empty] | 0.00408 | 0.03564 | 0.00408 | 0.03564
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | # | 16035 |  |  |  |  | 0.0068 | [19 empty] | 0.0068 |  | 0.0068
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | Result |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 0.1134 | [19 empty] | 0.1134 |  | 0.1134
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | [5 empty] | 0.1134 | [19 empty] | 0.1134 |  | 0.1134
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | Result |  |  |  |  | 0.26178 | 10.0927 | 25.1632 | 20.264 | -24.57 | 4.066 | [9 empty] | 400 |  | 89.646 |  |  |  | 30.3567 | 0.855 | 524.0687 | 0.855
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | Result |  |  |  | 0.16458 | 10.0927 | 24.9688 | 20.264 | -24.57 | 4.066 | [9 empty] | 400 |  | 89.646 |  |  |  | 30.3567 | 0.5634 | 524.0687 | 0.5634
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | # |  |  |  | 0.00076 | 10 | 24.6446 | 20.264 | -24.57 | 4.066 | [9 empty] | 400 |  | 89.646 |  |  |  | 30.264 | 0.07535 | 523.976 | 0.07535
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 12002 |  |  |  | 0.03579 | 0.01105 | 0.07158 | [18 empty] | 0.01105 | 0.10737 | 0.01105 | 0.10737
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 14646 |  |  |  |  | 0.03 | [19 empty] | 0.03 |  | 0.03
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16000 |  |  |  | 0.01958 | 0.00604 | 0.03915 | [18 empty] | 0.00604 | 0.05873 | 0.00604 | 0.05873
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16006 |  |  |  |  | 0.01017 | [19 empty] | 0.01017 |  | 0.01017
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16008 |  |  |  | 0.03434 |  | 0.06868 | [19 empty] | 0.10302 |  | 0.10302
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16012 |  |  |  | 0.00572 | 0.00207 | 0.01143 | [18 empty] | 0.00207 | 0.01715 | 0.00207 | 0.01715
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16013 |  |  |  | 0.00325 | 0.00118 | 0.00649 | [18 empty] | 0.00118 | 0.00974 | 0.00118 | 0.00974
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16014 |  |  |  |  | 0.0092 | [19 empty] | 0.0092 |  | 0.0092
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16020 |  |  |  | 0.02057 |  | 0.04114 | [19 empty] | 0.06171 |  | 0.06171
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16032 |  |  |  | 0.03331 | 0.01207 | 0.06326 | [18 empty] | 0.01207 | 0.09657 | 0.01207 | 0.09657
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16033 |  |  |  | 0.01126 | 0.00408 | 0.0225 | [18 empty] | 0.00408 | 0.03376 | 0.00408 | 0.03376
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | # | 16035 |  |  |  |  | 0.0068 | [19 empty] | 0.0068 |  | 0.0068
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | Result |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 0.0972 | [19 empty] | 0.0972 |  | 0.0972
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | [5 empty] | 0.0972 | [19 empty] | 0.0972 |  | 0.0972
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | Result | [6 empty] | 24.7347 | 50.4 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 160.367 |  | 0.5 |  | 50.4 | 0.16472 | 2711.267 | 0.16472
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | Result | [5 empty] | 24.6999 | 50.4 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 160.367 |  | 0.5 |  | 50.4 | 0.1299 | 2711.267 | 0.1299
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | # | [5 empty] | 24.6418 | 50.4 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 160.367 |  | 0.5 |  | 50.4 | 0.07183 | 2711.267 | 0.07183
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 12002 | [5 empty] | 0.01282 | [19 empty] | 0.01282 |  | 0.01282
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16000 | [5 empty] | 0.00701 | [19 empty] | 0.00701 |  | 0.00701
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16008 | [5 empty] | 0.0123 | [19 empty] | 0.0123 |  | 0.0123
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16012 | [5 empty] | 0.00205 | [19 empty] | 0.00205 |  | 0.00205
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16013 | [5 empty] | 0.00116 | [19 empty] | 0.00116 |  | 0.00116
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16020 | [5 empty] | 0.00737 | [19 empty] | 0.00737 |  | 0.00737
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16032 | [5 empty] | 0.01133 | [19 empty] | 0.01133 |  | 0.01133
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | # | 16033 | [5 empty] | 0.00403 | [19 empty] | 0.00403 |  | 0.00403
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | Result | [5 empty] | 0.03482 | [19 empty] | 0.03482 |  | 0.03482
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | [5 empty] | 0.03482 | [19 empty] | 0.03482 |  | 0.03482
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | Result |  |  |  |  | 0.26178 |  | 25.7437 | 53.9 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 346.093 |  |  |  | 53.9 | 1.4355 | 2899.993 | 1.4355
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | Result |  |  |  | 0.16458 |  | 25.3585 | 53.9 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 346.093 |  |  |  | 53.9 | 0.95311 | 2899.993 | 0.95311
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | # |  |  |  | 0.00076 |  | 24.6463 | 53.9 | -24.57 |  |  | 500 |  | 500 |  | 500 |  | 500 |  | 500 |  | 346.093 |  |  |  | 53.9 | 0.07703 | 2899.993 | 0.07703
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 12002 |  |  |  | 0.03579 |  | 0.14181 | [19 empty] | 0.1776 |  | 0.1776
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16000 |  |  |  | 0.01958 |  | 0.07757 | [19 empty] | 0.09715 |  | 0.09715
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16006 | [5 empty] | 0.05918 | [19 empty] | 0.05918 |  | 0.05918
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16008 |  |  |  | 0.03434 |  | 0.0744 | [19 empty] | 0.10874 |  | 0.10874
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16012 |  |  |  | 0.00572 |  | 0.02443 | [19 empty] | 0.03015 |  | 0.03015
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16013 |  |  |  | 0.00325 |  | 0.01387 | [19 empty] | 0.01712 |  | 0.01712
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16014 | [5 empty] | 0.05356 | [19 empty] | 0.05356 |  | 0.05356
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16020 |  |  |  | 0.02057 |  | 0.04456 | [19 empty] | 0.06513 |  | 0.06513
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16032 |  |  |  | 0.03331 |  | 0.13522 | [19 empty] | 0.16853 |  | 0.16853
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16033 |  |  |  | 0.01126 |  | 0.04812 | [19 empty] | 0.05938 |  | 0.05938
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | # | 16035 | [5 empty] | 0.03954 | [19 empty] | 0.03954 |  | 0.03954
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | Result |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 |  |  |  | 0.0972 |  | 0.0972 | [19 empty] | 0.1944 |  | 0.1944
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | Result | [5 empty] | 0.17456 | [19 empty] | 0.17456 |  | 0.17456
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | [5 empty] | 0.17456 | [19 empty] | 0.17456 |  | 0.17456
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | Result | [5 empty] | 0.1134 | [19 empty] | 0.1134 |  | 0.1134
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | [5 empty] | 0.1134 | [19 empty] | 0.1134 |  | 0.1134
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | 08W | UNSE |  | Result | [7 empty] | 9 |  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 | [5 empty] | 9 |  | 509
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | 08W | UNSE |  | # | Result | [6 empty] | 9 |  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 | [5 empty] | 9 |  | 509
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | 08W | UNSE |  | # | # | [6 empty] | 9 |  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 | [5 empty] | 9 |  | 509
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 104 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  | 4104
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 104 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  | 4104
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 104 |  | 1000 |  | 1000 |  | 1000 |  | 1000 |  |  |  | 4104
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  |  |  | 500
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 50 |  | 50 |  | 25 | [7 empty] | 125
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 50 |  | 50 |  | 25 | [7 empty] | 125
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 50 |  | 50 |  | 25 | [7 empty] | 125
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 200 |  | 200 |  | 200 |  | 65 | [5 empty] | 665
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 200 |  | 200 |  | 200 |  | 65 | [5 empty] | 665
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 200 |  | 200 |  | 200 |  | 65 | [5 empty] | 665
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | 08W | UNSE |  | Result | [17 empty] | 945 |  | 1000 |  | 1000 | [5 empty] | 2945
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | 08W | UNSE |  | # | Result | [16 empty] | 945 |  | 1000 |  | 1000 | [5 empty] | 2945
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | 08W | UNSE |  | # | # | [16 empty] | 945 |  | 1000 |  | 1000 | [5 empty] | 2945
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | 08W | UNSE |  | Result | [15 empty] | 21 |  | 1000 |  | 1000 |  | 1000 | [5 empty] | 3021
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | 08W | UNSE |  | # | Result | [14 empty] | 21 |  | 1000 |  | 1000 |  | 1000 | [5 empty] | 3021
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | 08W | UNSE |  | # | # | [14 empty] | 21 |  | 1000 |  | 1000 |  | 1000 | [5 empty] | 3021

## PRJ004 - Hrs Labor
[11 empty] | Jan Plan(PRJ) | Jan Actual | Feb Plan(PRJ) | Feb Actual | Mar Plan(PRJ) | Mar Actual | Apr Plan(PRJ) | Apr Actual | May Plan(PRJ) | May Actual | Jun Plan(PRJ) | Jun Actual | Jul Plan(PRJ) | Jul Actual | Aug Plan(PRJ) | Aug Actual | Sep Plan(PRJ) | Sep Actual | Oct Plan(PRJ) | Oct Actual | Nov Plan(PRJ) | Nov Actual | Dec Plan(PRJ) | Dec Actual | YTD Apr Plan(PRJ) | YTD Apr Actual | Jan - Dec Plan(PRJ) | Jan - Dec Actual
Order | Order Text | WBS Element | Planning Order | MaintActivityType | User Status | Job Owner | Partner Actv | Partner CC | Cost Element |  | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | HRS | [15 empty] | HRS | HRS | HRS | HRS
Overall Result | [10 empty] | 1242 | 2280.5 | 2722 | 2620.5 | 3853 | 5051.75 | 4601 | 809.25 | [16 empty] | 12418 | 10762 | 12418 | 10762
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | Result | [7 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | 08W | ESTS |  | CNSTOT | 14182 | 6603021 | Construction Overtime Services | [5 empty] | 11 | [19 empty] | 11 |  | 11
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | Result | [7 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | CONSTR | 14182 | 6603001 | Construction | [5 empty] | 9 | [19 empty] | 9 |  | 9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | Result | [9 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | Result |  |  |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ORDFIN | Order Financial Costs |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ACTVTYPES | Activity Types |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | ENVSVC | 15154 | 6603024 | Environmental Services |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | Result |  |  |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | 08W | PEND |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc |  | 0.25 | [23 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | Result | [7 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | CONSTR | 14182 | 6603001 | Construction | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | Result | [9 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | 08W | ESTS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 | [23 empty] | 1 |  | 1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | Result | [7 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | CONSTR | 14182 | 6603001 | Construction | [5 empty] | 9 | [19 empty] | 9 |  | 9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | Result | [9 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | 08W | PEND |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 0.5 | [17 empty] | 0.5 |  | 0.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | Result |  |  | 10 |  | 10 | 1 | 10 | 5 | [18 empty] | 30 | 6 | 30 | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | 08W | FICL |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 5 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | Result | [7 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | Result |  |  |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDFIN | Order Financial Costs |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TOT | Activity Type Total |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTVTYPES | Activity Types |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-INT | Activity Types - Internal |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ACTSVC | 15789 | 6603730 | Account Services |  | 2 |  | 1 |  | 3 | [19 empty] | 6 |  | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | Result | [7 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADM-OT | 15154 | 6603150 | Administrative Services - OT | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | Result | [5 empty] | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration |  |  |  | 2 |  | 1 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | Result | [7 empty] | 76 | [19 empty] | 76 |  | 76
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ACTVTYPES | Activity Types | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11832 | 6603180 | Construction Doubletime Services | [5 empty] | 14.5 | [19 empty] | 14.5 |  | 14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 11838 | 6603180 | Construction Doubletime Services | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTVTYPES | Activity Types | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 14632 | 6603180 | Construction Doubletime Services | [5 empty] | 11 | [19 empty] | 11 |  | 11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ACTVTYPES | Activity Types | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTDT | 15216 | 6603180 | Construction Doubletime Services | [5 empty] | 48 | [19 empty] | 48 |  | 48
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | Result | [5 empty] | 1.5 |  | 108.5 | [19 empty] | 110 |  | 110
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ACTVTYPES | Activity Types | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11832 | 6603021 | Construction Overtime Services | [5 empty] | 20 | [19 empty] | 20 |  | 20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 11838 | 6603021 | Construction Overtime Services | [5 empty] | 2.5 | [19 empty] | 2.5 |  | 2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTVTYPES | Activity Types |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 14632 | 6603021 | Construction Overtime Services |  |  |  | 1.5 |  | 43.5 | [19 empty] | 45 |  | 45
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ACTVTYPES | Activity Types | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CNSTOT | 15216 | 6603021 | Construction Overtime Services | [5 empty] | 42.5 | [19 empty] | 42.5 |  | 42.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | Result |  |  | 450 | 14 | 16 | 49 | 350 | 530 | 470 | 36 | [16 empty] | 1286 | 629 | 1286 | 629
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ACTVTYPES | Activity Types | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11832 | 6603001 | Construction | [5 empty] | 80 | [19 empty] | 80 |  | 80
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ACTVTYPES | Activity Types | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 11838 | 6603001 | Construction | [5 empty] | 10 | [19 empty] | 10 |  | 10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14182 | 6603001 | Construction |  | 14 | 16 | 34 |  |  |  | 36 | [16 empty] | 16 | 84 | 16 | 84
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDFIN | Order Financial Costs | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TOT | Activity Type Total | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTVTYPES | Activity Types | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-INT | Activity Types - Internal | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 14632 | 6603001 | Construction | 450 |  |  | 15 | 350 | 270 | 470 | [17 empty] | 1270 | 285 | 1270 | 285
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ACTVTYPES | Activity Types | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | CONSTR | 15216 | 6603001 | Construction | [5 empty] | 170 | [19 empty] | 170 |  | 170
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 1 |  | 11.5 |  | 1.5 | [17 empty] | 14 |  | 14
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | [5 empty] | 3 | [19 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 6.5 |  | 1.5 | [17 empty] | 9 |  | 9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGMAP | 14521 | 6603022 | Engineering/Mapping | [5 empty] | 2 | [19 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | Result |  |  |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  | 2.5 |  |  |  | 3.25 |  | 1 | [17 empty] | 6.75 |  | 6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | Result | [7 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ACTVTYPES | Activity Types | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MANAGE | 15937 | 6603076 | Management Services | [5 empty] | 5 | [19 empty] | 5 |  | 5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | Result |  |  |  | 0.75 |  | 10 | 2 | 3.5 | [18 empty] | 2 | 14.25 | 2 | 14.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ORDFIN | Order Financial Costs |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ACTV-TOT | Activity Type Total |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ACTVTYPES | Activity Types |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ACTV-INT | Activity Types - Internal |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 11890 | 6603083 | Maintain & Operate Services |  | 0.75 |  | 3 |  | 0.5 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 12689 | 6603083 | Maintain & Operate Services |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ORDFIN | Order Financial Costs |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ACTVTYPES | Activity Types |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO | 15275 | 6603083 | Maintain & Operate Services |  |  |  | 6 | 2 | [19 empty] | 2 | 6 | 2 | 6
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | Result | [5 empty] | 3 |  | 1.5 | [19 empty] | 4.5 |  | 4.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 11890 | 6603181 | Maint & Operate Doubletime Services | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ORDFIN | Order Financial Costs |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ACTVTYPES | Activity Types |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-DT | 12689 | 6603181 | Maint & Operate Doubletime Services |  |  |  | 3 | [21 empty] | 3 |  | 3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | Result |  |  |  | 0.5 |  | 4.75 |  | 1 | [19 empty] | 6.25 |  | 6.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ORDFIN | Order Financial Costs |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ACTV-TOT | Activity Type Total |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ACTVTYPES | Activity Types |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ACTV-INT | Activity Types - Internal |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 11890 | 6603082 | Maintain & Operate Overtime Services |  | 0.5 |  | 2.75 |  | 1 | [19 empty] | 4.25 |  | 4.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ORDFIN | Order Financial Costs |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTVTYPES | Activity Types |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | MO-OT | 15275 | 6603082 | Maintain & Operate Overtime Services |  |  |  | 2 | [21 empty] | 2 |  | 2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | Result | [5 empty] | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ORDFIN | Order Financial Costs |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ACTVTYPES | Activity Types |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 4 | [21 empty] | 4 |  | 4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | 08W | CONS |  | SCADSV | 10484 | 6603671 | SCADA Services |  |  |  | 4 | [21 empty] | 4 |  | 4
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | Result |  |  |  | 3.75 |  | 3 |  | 4 | [19 empty] | 10.75 |  | 10.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ORDFIN | Order Financial Costs |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ACTV-TOT | Activity Type Total |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ACTVTYPES | Activity Types |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ACTV-INT | Activity Types - Internal |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15495 | 6603730 | Account Services |  | 0.75 | [23 empty] | 0.75 |  | 0.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDFIN | Order Financial Costs |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TOT | Activity Type Total |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTVTYPES | Activity Types |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-INT | Activity Types - Internal |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ACTSVC | 15789 | 6603730 | Account Services |  | 3 |  | 3 |  | 4 | [19 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 1 | [19 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ANLYOT | 15449 | 6603855 | Analyst Svcs Overtime |  | 1 | [23 empty] | 1 |  | 1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | Result |  |  |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDFIN | Order Financial Costs |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TOT | Activity Type Total |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTVTYPES | Activity Types |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-INT | Activity Types - Internal |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CNSTOT | 14632 | 6603021 | Construction Overtime Services |  | 2.5 |  | 15.5 |  | 6 |  | 30 | [17 empty] | 54 |  | 54
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | Result |  |  |  | 50 | 400 | 440 | 550 | 156 | 750 | 76 | [16 empty] | 1700 | 722 | 1700 | 722
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ACTVTYPES | Activity Types | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 12055 | 6603001 | Construction | [5 empty] | 6 | [19 empty] | 6 |  | 6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14182 | 6603001 | Construction | [7 empty] | 36 | [17 empty] | 36 |  | 36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDFIN | Order Financial Costs |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TOT | Activity Type Total |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTVTYPES | Activity Types |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-INT | Activity Types - Internal |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | CONSTR | 14632 | 6603001 | Construction |  | 50 | 400 | 440 | 550 | 150 | 750 | 40 | [16 empty] | 1700 | 680 | 1700 | 680
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 4 |  | 5.5 |  | 0.5 | [17 empty] | 10 |  | 10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  |  |  | 4 |  | 3 | [19 empty] | 7 |  | 7
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping | [5 empty] | 2.5 |  | 0.5 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 2 |  | 1 | [17 empty] | 3 |  | 3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | Result | [7 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ACTVTYPES | Activity Types | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | HRSST | 13892 | 6608193 | Hours - Straight Time | [5 empty] | 8 | [19 empty] | 8 |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | Result | [7 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | Result |  |  |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ORDFIN | Order Financial Costs |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ACTV-TOT | Activity Type Total |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ACTVTYPES | Activity Types |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ACTV-INT | Activity Types - Internal |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MANAGE | 11034 | 6603076 | Management Services |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | Result | [7 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ACTVTYPES | Activity Types | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO | 15275 | 6603083 | Maintain & Operate Services | [5 empty] | 9 | [19 empty] | 9 |  | 9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | Result | [7 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | 08W | CONS |  | MO-OT | 15275 | 6603082 | Maintain & Operate Overtime Services | [5 empty] | 2.25 | [19 empty] | 2.25 |  | 2.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | Result | [9 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | 08W | ESTS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 1 | [17 empty] | 1 |  | 1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | Result | [7 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | EEST | 11714 | 6603466 | Electric Estimating | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | Result | [9 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | 08W | ESTS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 0.25 | [17 empty] | 0.25 |  | 0.25
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | Result |  |  |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ORDFIN | Order Financial Costs |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-TOT | Activity Type Total |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTVTYPES | Activity Types |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-INT | Activity Types - Internal |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | 08W | DOCC |  | ACTSVC | 15789 | 6603730 | Account Services |  | 4.5 | [23 empty] | 4.5 |  | 4.5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | Result |  |  |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ORDFIN | Order Financial Costs |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-TOT | Activity Type Total |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTVTYPES | Activity Types |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-INT | Activity Types - Internal |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 5 | [23 empty] | 5 |  | 5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | 08W | DOCC |  | ACTSVC | 15789 | 6603730 | Account Services |  | 5 | [23 empty] | 5 |  | 5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | Result | [7 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 0.25 | [19 empty] | 0.25 |  | 0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | Result |  |  | 10 |  | 10 | 1 | 10 | 7 |  | 1 | [16 empty] | 30 | 9 | 30 | 9
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | [5 empty] | 2 | [19 empty] | 2 |  | 2
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | 08W | DOCC |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping | 10 |  | 10 | 1 | 10 | 5 |  | 1 | [16 empty] | 30 | 7 | 30 | 7
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | Result |  |  |  | 4.5 |  |  |  | 1 | [19 empty] | 5.5 |  | 5.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ORDFIN | Order Financial Costs |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ACTVTYPES | Activity Types |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 11929 | 6603004 | Acquisition - Misc |  | 3.5 | [23 empty] | 3.5 |  | 3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc |  | 1 |  |  |  | 1 | [19 empty] | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | Result |  |  | 10 |  | 10 | 1 | 10 | 3 | [18 empty] | 30 | 4 | 30 | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | 10 |  | 10 |  | 10 | [19 empty] | 30 |  | 30
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 3 | [19 empty] | 4 |  | 4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | Result |  |  |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | Result | [7 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ACTVTYPES | Activity Types | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ACTV-CONTR | Activity Types - Contractors | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | PGE1ACTV-OTH-C | Other Contractor Activity Types | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | 08W | FICL |  | XCON02 | 15993 | 6608158 | Contractor Consultant | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | Result |  |  |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration |  | 2 | [23 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | Result |  |  |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 |  |  | 1 | [19 empty] | 1 | 1 | 1 | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | Result | [7 empty] | 32 | [19 empty] | 32 |  | 32
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ACTVTYPES | Activity Types | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 11830 | 6603180 | Construction Doubletime Services | [5 empty] | 30 | [19 empty] | 30 |  | 30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTDT | 14632 | 6603180 | Construction Doubletime Services | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | Result |  |  |  | 48 |  | 48.5 |  | 120 | [19 empty] | 216.5 |  | 216.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ACTVTYPES | Activity Types | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11830 | 6603021 | Construction Overtime Services | [5 empty] | 15 | [19 empty] | 15 |  | 15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTVTYPES | Activity Types | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 11834 | 6603021 | Construction Overtime Services | [5 empty] | 17.5 | [19 empty] | 17.5 |  | 17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDFIN | Order Financial Costs |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TOT | Activity Type Total |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTVTYPES | Activity Types |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-INT | Activity Types - Internal |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CNSTOT | 14632 | 6603021 | Construction Overtime Services |  | 48 |  | 48.5 |  | 87.5 | [19 empty] | 184 |  | 184
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | Result |  |  |  | 498 | 400 | 470 | 300 | 797.5 | 250 | [17 empty] | 950 | 1765.5 | 950 | 1765.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ACTVTYPES | Activity Types | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11830 | 6603001 | Construction | [5 empty] | 47.5 | [19 empty] | 47.5 |  | 47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTVTYPES | Activity Types | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 11834 | 6603001 | Construction | [5 empty] | 70 | [19 empty] | 70 |  | 70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDFIN | Order Financial Costs |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TOT | Activity Type Total |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTVTYPES | Activity Types |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-INT | Activity Types - Internal |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | CONSTR | 14632 | 6603001 | Construction |  | 498 | 400 | 470 | 300 | 680 | 250 | [17 empty] | 950 | 1648 | 950 | 1648
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | Result | [6 empty] | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  |  | 187 | 153 |  | 28 | [16 empty] | 187 | 181 | 187 | 181
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENGSVC | 14628 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | Result |  |  |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration |  | 2 |  |  |  | 1 | [19 empty] | 3 |  | 3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 | [23 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | Result | [7 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping | [5 empty] | 2 | [19 empty] | 2 |  | 2
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | Result | [7 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 3 | [19 empty] | 3 |  | 3
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 | [23 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | Result | [7 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTVTYPES | Activity Types | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CNSTOT | 14632 | 6603021 | Construction Overtime Services | [5 empty] | 61.5 |  | 4.5 | [17 empty] | 66 |  | 66
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | Result |  |  |  |  | 300 |  | 400 | 231 | 750 | 100 | [16 empty] | 1450 | 331 | 1450 | 331
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDFIN | Order Financial Costs |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TOT | Activity Type Total |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTVTYPES | Activity Types |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-INT | Activity Types - Internal |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 11834 | 6603001 | Construction |  |  | 300 |  | 400 | [19 empty] | 700 |  | 700
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14182 | 6603001 | Construction | [5 empty] | 44 | [19 empty] | 44 |  | 44
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTVTYPES | Activity Types | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | CONSTR | 14632 | 6603001 | Construction | [5 empty] | 187 | 750 | 100 | [16 empty] | 750 | 287 | 750 | 287
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | Result | [7 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping | [5 empty] | 1 |  | 1 | [17 empty] | 2 |  | 2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 1 | [19 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 | [23 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | Result | [7 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTVTYPES | Activity Types | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTDT | 11834 | 6603180 | Construction Doubletime Services | [5 empty] | 21.5 |  | 2 | [17 empty] | 23.5 |  | 23.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | Result | [5 empty] | 37 |  | 137.5 |  | 23 | [17 empty] | 197.5 |  | 197.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDFIN | Order Financial Costs |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTVTYPES | Activity Types |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 11834 | 6603021 | Construction Overtime Services |  |  |  | 30 |  | 137.5 |  | 23 | [17 empty] | 190.5 |  | 190.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CNSTOT | 14182 | 6603021 | Construction Overtime Services |  |  |  | 7 | [21 empty] | 7 |  | 7
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | Result |  |  |  | 250 |  | 40 | 450 | 618 | 900 | 190 | [16 empty] | 1350 | 1098 | 1350 | 1098
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDFIN | Order Financial Costs |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TOT | Activity Type Total |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTVTYPES | Activity Types |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-INT | Activity Types - Internal |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 11834 | 6603001 | Construction |  | 250 |  | 40 | 450 | 600 | 900 | 190 | [16 empty] | 1350 | 1080 | 1350 | 1080
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | CONSTR | 14182 | 6603001 | Construction | [5 empty] | 18 | [19 empty] | 18 |  | 18
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | Result |  |  |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  | 116 | 167 | 152 | 10 | 5 |  | 2 | [16 empty] | 177 | 275 | 177 | 275
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | Result | [9 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [7 empty] | 1 | [17 empty] | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [7 empty] | 1 | [17 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | Result |  |  |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDFIN | Order Financial Costs |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TOT | Activity Type Total |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTVTYPES | Activity Types |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-INT | Activity Types - Internal |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ACTSVC | 15789 | 6603730 | Account Services |  | 3 |  | 1 |  | 3 | [19 empty] | 7 |  | 7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | Result | [5 empty] | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration |  |  |  | 8 |  | 11 | [19 empty] | 19 |  | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | Result |  |  |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDFIN | Order Financial Costs |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TOT | Activity Type Total |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTVTYPES | Activity Types |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-INT | Activity Types - Internal |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CNSTOT | 14632 | 6603021 | Construction Overtime Services |  | 17.5 |  | 73 |  | 24.5 |  | 5 | [17 empty] | 120 |  | 120
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | Result |  |  | 762 | 415 | 856 | 480 | 1000 | 627 | 900 | 100 | [16 empty] | 3518 | 1622 | 3518 | 1622
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14182 | 6603001 | Construction | 12 | 15 | 16 | 30 |  | 36 | [18 empty] | 28 | 81 | 28 | 81
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDFIN | Order Financial Costs | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TOT | Activity Type Total | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTVTYPES | Activity Types | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-INT | Activity Types - Internal | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 14632 | 6603001 | Construction | 750 | 400 | 840 | 450 | 1000 | 590 | 900 | 100 | [16 empty] | 3490 | 1540 | 3490 | 1540
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | CONSTR | 15893 | 6603001 | Construction | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | Result |  |  |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ORDFIN | Order Financial Costs |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-TOT | Activity Type Total |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ACTVTYPES | Activity Types |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-INT | Activity Types - Internal |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | EEST | 11714 | 6603466 | Electric Estimating |  | 2 |  | 2 |  | 4 | [19 empty] | 8 |  | 8
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 1 |  | 7 |  | 2 | [17 empty] | 10 |  | 10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 6 |  | 2 | [17 empty] | 9 |  | 9
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | 08W | CONS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 1 | [19 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ANLYST | 15449 | 6603005 | Analyst Services |  | 1 | [23 empty] | 1 |  | 1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | Result | [5 empty] | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ORDFIN | Order Financial Costs |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTVTYPES | Activity Types |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTDT | 11834 | 6603180 | Construction Doubletime Services |  |  |  | 70.25 |  | 25.25 | [19 empty] | 95.5 |  | 95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | Result |  |  |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDFIN | Order Financial Costs |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TOT | Activity Type Total |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTVTYPES | Activity Types |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-INT | Activity Types - Internal |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CNSTOT | 11834 | 6603021 | Construction Overtime Services |  | 68.5 |  | 98 |  | 263.5 |  | 67 | [17 empty] | 497 |  | 497
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | Result |  |  |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDFIN | Order Financial Costs |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TOT | Activity Type Total |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTVTYPES | Activity Types |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-INT | Activity Types - Internal |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | CONSTR | 11834 | 6603001 | Construction |  | 634 | 500 | 410 | 350 | 598.5 | 450 | 85 | [16 empty] | 1300 | 1727.5 | 1300 | 1727.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | Result |  |  |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ORDFIN | Order Financial Costs |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-TOT | Activity Type Total |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ACTVTYPES | Activity Types |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-INT | Activity Types - Internal |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | EEST | 11714 | 6603466 | Electric Estimating |  | 13 |  |  |  | 7 | [19 empty] | 20 |  | 20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | Result |  |  |  | 2 |  | 1 |  | 7 |  | 2 | [17 empty] | 12 |  | 12
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  | 2 |  |  |  | 2 | [19 empty] | 4 |  | 4
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 5 |  | 2 | [17 empty] | 8 |  | 8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | Result | [6 empty] | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDFIN | Order Financial Costs |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TOT | Activity Type Total |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTVTYPES | Activity Types |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-INT | Activity Types - Internal |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | ENGSVC | 12688 | 6603023 | Engineering Services |  |  |  |  | 25 | [19 empty] | 25 |  | 25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | Result |  |  |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  | 5 | [21 empty] | 5 |  | 5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | 08W | CONS |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  |  | 5 | [21 empty] | 5 |  | 5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | Result | [5 empty] | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 | [21 empty] | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | 08W | PEND |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc |  |  |  | 1 | [21 empty] | 1 |  | 1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | Result | [5 empty] | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | 08W | CONS |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 |  | 4 |  | 1 | [17 empty] | 6 |  | 6
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | Result |  |  |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc |  | 4 | [23 empty] | 4 |  | 4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | Result |  |  |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | 08W | PEND |  | ADMIN | 15154 | 6603000 | Administration |  | 6 |  | 2 | [21 empty] | 8 |  | 8
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | Result |  |  |  | 7 | [23 empty] | 7 |  | 7
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ORDFIN | Order Financial Costs |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ACTV-TOT | Activity Type Total |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ACTVTYPES | Activity Types |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12577 | 6603004 | Acquisition - Misc |  | 3 | [23 empty] | 3 |  | 3
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc |  | 4 | [23 empty] | 4 |  | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | Result | [7 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADM-OT | 12577 | 6603150 | Administrative Services - OT | [5 empty] | 4.25 | [19 empty] | 4.25 |  | 4.25
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | Result |  |  |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ORDFIN | Order Financial Costs |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ACTV-TOT | Activity Type Total |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ACTVTYPES | Activity Types |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ACTV-INT | Activity Types - Internal |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ADMIN | 12245 | 6603000 | Administration |  | 6 |  | 15 | [21 empty] | 21 |  | 21
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | Result | [5 empty] | 9 |  | 5 | [19 empty] | 14 |  | 14
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 14182 | 6603001 | Construction |  |  |  | 9 | [21 empty] | 9 |  | 9
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ACTVTYPES | Activity Types | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | CONSTR | 15960 | 6603001 | Construction | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | Result |  |  |  |  | 48 | 2.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 4 | 96 | 4
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  | 48 | 0.5 | 48 | 0.5 |  | 1 | [16 empty] | 96 | 2 | 96 | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ORDFIN | Order Financial Costs |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ACTVTYPES | Activity Types |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENGMAP | 15098 | 6603022 | Engineering/Mapping |  |  |  | 2 | [21 empty] | 2 |  | 2
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | Result |  |  |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | Result | [7 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc | [5 empty] | 5 | [19 empty] | 5 |  | 5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | Result |  |  |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ORDFIN | Order Financial Costs |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ACTV-TOT | Activity Type Total |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ACTVTYPES | Activity Types |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ACTV-INT | Activity Types - Internal |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | 08W | PEND |  | TECHSV | 12884 | 6603058 | Technical Services |  | 37.5 |  | 4 | [21 empty] | 41.5 |  | 41.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | Result | [7 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ADMIN | 15154 | 6603000 | Administration | [5 empty] | 3.5 |  | 4 | [17 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | Result | [5 empty] | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | 6603001 | Construction |  |  |  | 9 | [21 empty] | 9 |  | 9
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | Result |  |  |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ORDFIN | Order Financial Costs |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-TOT | Activity Type Total |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ACTVTYPES | Activity Types |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-INT | Activity Types - Internal |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | EEST | 12974 | 6603466 | Electric Estimating |  | 3 | [23 empty] | 3 |  | 3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | Result | [5 empty] | 1.25 |  | 1 | [19 empty] | 2.25 |  | 2.25
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  |  |  | 0.75 | [21 empty] | 0.75 |  | 0.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 0.5 |  | 1 | [19 empty] | 1.5 |  | 1.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | Result |  |  |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  | 2 | [5 empty] | 3 | [17 empty] | 5 |  | 5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc |  |  |  | 7.5 | [21 empty] | 7.5 |  | 7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | Result |  |  |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 | [23 empty] | 2 |  | 2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | 08W | UNSE |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | Result | [5 empty] | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | 6603004 | Acquisition - Misc |  |  |  | 3 | [21 empty] | 3 |  | 3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ADM-OT | 15154 | 6603150 | Administrative Services - OT | [5 empty] | 1 | [19 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | Result |  |  |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ORDFIN | Order Financial Costs |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-TOT | Activity Type Total |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ACTVTYPES | Activity Types |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-INT | Activity Types - Internal |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | EEST | 12974 | 6603466 | Electric Estimating |  | 7 | [23 empty] | 7 |  | 7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | Result | [5 empty] | 7.75 | [21 empty] | 7.75 |  | 7.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  |  |  | 6.75 | [21 empty] | 6.75 |  | 6.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 | [21 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | Result | [5 empty] | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENGMPO | 13549 | 6603106 | Engineering/Mapping Services Overtime |  |  |  | 14.5 | [21 empty] | 14.5 |  | 14.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | Result |  |  |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  | 1 | [23 empty] | 1 |  | 1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | Result |  |  |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 2 | [23 empty] | 2 |  | 2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | 08W | UNSE |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  | 2 | [23 empty] | 2 |  | 2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | Result |  |  |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ORDFIN | Order Financial Costs |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ACTV-TOT | Activity Type Total |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ACTVTYPES | Activity Types |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ACTV-INT | Activity Types - Internal |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ACQLIT | 12809 | 6603004 | Acquisition - Misc |  | 3 |  | 1.5 |  | 2 | [19 empty] | 6.5 |  | 6.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | Result |  |  |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ORDFIN | Order Financial Costs |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ACTVTYPES | Activity Types |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ADM-OT | 11929 | 6603150 | Administrative Services - OT |  | 4 | [23 empty] | 4 |  | 4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | Result |  |  |  | 15 |  | 4 |  | 1 | [19 empty] | 20 |  | 20
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  | 15 |  | 3 |  | 1 | [19 empty] | 19 |  | 19
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 | [21 empty] | 1 |  | 1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | Result |  |  |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ORDFIN | Order Financial Costs |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ACTV-TOT | Activity Type Total |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ACTVTYPES | Activity Types |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ACTV-INT | Activity Types - Internal |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENGMPO | 13549 | 6603106 | Engineering/Mapping Services Overtime |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | Result |  |  |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ORDFIN | Order Financial Costs |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ACTV-TOT | Activity Type Total |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ACTVTYPES | Activity Types |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ACTV-INT | Activity Types - Internal |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | ENVPLN | 15240 | 6603027 | Environmental Planning & Permitting-Misc |  | 1.5 | [23 empty] | 1.5 |  | 1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | Result | [7 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc | [5 empty] | 5 | [19 empty] | 5 |  | 5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | Result |  |  |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 3 | [23 empty] | 3 |  | 3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | 08W | ADER |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  | 3 | [23 empty] | 3 |  | 3
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | Result | [5 empty] | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ADM-OT | 12577 | 6603150 | Administrative Services - OT |  |  |  | 4 |  | 23.5 |  | 4 | [17 empty] | 31.5 |  | 31.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | Result | [7 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENG-OT | 14182 | 6603148 | Engineering Services - OT | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | Result |  |  |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  | 1 |  | 1 | [21 empty] | 2 |  | 2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | Result | [5 empty] | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENGMPO | 13549 | 6603106 | Engineering/Mapping Services Overtime |  |  |  | 11 | [21 empty] | 11 |  | 11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | Result | [5 empty] | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc |  |  |  | 21 |  | 79 | 61 | 17 | [16 empty] | 61 | 117 | 61 | 117
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | Result | [5 empty] | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 | [21 empty] | 1 |  | 1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | 08W | UNSE |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | Result | [5 empty] | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ADM-OT | 12577 | 6603150 | Administrative Services - OT |  |  |  | 2.5 |  | 16 | 1 | 1 | [16 empty] | 1 | 19.5 | 1 | 19.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | Result |  |  |  | 1 |  | 7 | [21 empty] | 8 |  | 8
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping |  | 1 |  | 6 | [21 empty] | 7 |  | 7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENGMAP | 14182 | 6603022 | Engineering/Mapping |  |  |  | 1 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | Result |  |  |  | 0.5 |  | 0.5 | [21 empty] | 1 |  | 1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ORDFIN | Order Financial Costs |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ACTV-TOT | Activity Type Total |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ACTVTYPES | Activity Types |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ACTV-INT | Activity Types - Internal |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | ENVPLN | 15240 | 6603027 | Environmental Planning & Permitting-Misc |  | 0.5 | [23 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc |  |  |  | 23.5 |  | 54 | 61 | 15 | [16 empty] | 61 | 92.5 | 61 | 92.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | Result | [5 empty] | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDFIN | Order Financial Costs |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTVTYPES | Activity Types |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | 08W | UNSE |  | LNDRTS | 11929 | 6603227 | Land Rights - Misc |  |  |  | 0.5 | [21 empty] | 0.5 |  | 0.5
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | Result | [5 empty] | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | 6603001 | Construction |  |  |  | 9 | [21 empty] | 9 |  | 9
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | Result | [5 empty] | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc |  |  |  | 3 |  | 17 | 4 | [17 empty] | 4 | 20 | 4 | 20
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | Result | [5 empty] | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDFIN | Order Financial Costs |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTVTYPES | Activity Types |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | 08W | UNSE |  | CONSTR | 14182 | 6603001 | Construction |  |  |  | 9 |  |  | 4 | [17 empty] | 4 | 9 | 4 | 9
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | Result | [7 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ACTVTYPES | Activity Types | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | CNSTOT | 14182 | 6603021 | Construction Overtime Services | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | Result | [7 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTVTYPES | Activity Types | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMAP | 13549 | 6603022 | Engineering/Mapping | [5 empty] | 32 | [19 empty] | 32 |  | 32
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | Result | [5 empty] | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDFIN | Order Financial Costs |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTVTYPES | Activity Types |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENGMPO | 13549 | 6603106 | Engineering/Mapping Services Overtime |  |  |  | 6 |  | 8 | [19 empty] | 14 |  | 14
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | Result | [7 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | 08W | UNSE |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 2 |  | 1.5 | [17 empty] | 3.5 |  | 3.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | Result | [7 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ACTVTYPES | Activity Types | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | EEST | 11714 | 6603466 | Electric Estimating | [5 empty] | 4.5 | [19 empty] | 4.5 |  | 4.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | Result | [7 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 1 | [19 empty] | 1 |  | 1
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | Result | [5 empty] | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | 6603004 | Acquisition - Misc |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | Result | [7 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | Result | [5 empty] | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | ACQLIT | 12577 | 6603004 | Acquisition - Misc |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | Result | [7 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | 08W | UNSE |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc | [5 empty] | 1.5 | [19 empty] | 1.5 |  | 1.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | Result | [7 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTVTYPES | Activity Types | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | 08W | ESTS |  | ENVPLN | 15154 | 6603027 | Environmental Planning & Permitting-Misc | [5 empty] | 0.5 | [19 empty] | 0.5 |  | 0.5
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | Result | [5 empty] | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ORDFIN | Order Financial Costs |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ACTV-TOT | Activity Type Total |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ACTVTYPES | Activity Types |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ACTV-INT | Activity Types - Internal |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | ACQLIT | 12577 | 6603004 | Acquisition - Misc |  |  |  | 1.5 |  | 1.5 | [19 empty] | 3 |  | 3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | Result | [7 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ACTVTYPES | Activity Types | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | EESTOT | 11714 | 6603467 | Electric Estimating Overtime | [5 empty] | 2 | [19 empty] | 2 |  | 2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | Result | [7 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ORDFIN | Order Financial Costs | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ORDCOSTS | Orders Costs-Directs & Credits | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ACTV-TOT | Activity Type Total | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ACTVTYPES | Activity Types | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ACTV-INT | Activity Types - Internal | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | PGE1ACTV-TYPE | ActvTypE Ex Conver, Contractor & OH Actv | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | 08W | ESTS |  | LNDENG | 12577 | 6603059 | Land Surveying & Engineering Supprt-Misc | [5 empty] | 1.75 | [19 empty] | 1.75 |  | 1.75

## PRJ003
Order | Order Text | WBS Element | Auth Amt (AJE) | Total Actual $ | Committed (Open Items) | Assigned (Act + Com) | Var (Auth- Assigned) | % Spent (Total Act $ /Auth Amt) | Committed (GR Accrual) | % Spent (Assigned/ Auth)
Overall Result |  |  | 111439231.25 | 68460469.45 | 1886605.56 | 70347075.01 | 41092156.24 | 61.43% |  | 63.13%
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 166667 | 50474.29 |  | 50474.29 | 116192.71 | 30.28% |  | 30.28%
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 725000 | 591126.85 |  | 591126.85 | 133873.15 | 81.53% |  | 81.53%
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 600000 | 320626.81 |  | 320626.81 | 279373.19 | 53.44% |  | 53.44%
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 | 3201494.39 | 2706370.01 |  | 2706370.01 | 495124.38 | 84.53% |  | 84.53%
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 725000 | 306635.06 | 22840.75 | 329475.81 | 395524.19 | 42.29% |  | 45.44%
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 3559342.68 | 3103351.2 |  | 3103351.2 | 455991.48 | 87.19% |  | 87.19%
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 3459498 | 2313662.14 | 98569.13 | 2412231.27 | 1047266.73 | 66.88% |  | 69.73%
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 3890027.76 | 1677909.82 | 452434.03 | 2130343.85 | 1759683.91 | 43.13% |  | 54.76%
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 3189967.04 | 1978630.53 |  | 1978630.53 | 1211336.51 | 62.03% |  | 62.03%
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 900000 | 617113.95 | 148634.68 | 765748.63 | 134251.37 | 68.57% |  | 85.08%
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 2785685.86 | 1945492.6 |  | 1945492.6 | 840193.26 | 69.84% |  | 69.84%
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 | 3151028.81 | 2621459.58 |  | 2621459.58 | 529569.23 | 83.19% |  | 83.19%
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 4499650.65 | 3786637.1 |  | 3786637.1 | 713013.55 | 84.15% |  | 84.15%
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 900000 | 599887.87 |  | 599887.87 | 300112.13 | 66.65% |  | 66.65%
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 3530636.37 | 3101220.78 |  | 3101220.78 | 429415.59 | 87.84% |  | 87.84%
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5480368 | 5379872.97 |  | 5379872.97 | 100495.03 | 98.17% |  | 98.17%
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 3123544.1 | 2635581.04 | 28251.72 | 2663832.76 | 459711.34 | 84.38% |  | 85.28%
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 3044148.02 | 2848313.16 |  | 2848313.16 | 195834.86 | 93.57% |  | 93.57%
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 3172297.77 | 2686391.99 |  | 2686391.99 | 485905.78 | 84.68% |  | 84.68%
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5804262.07 | 4548604.36 |  | 4548604.36 | 1255657.71 | 78.37% |  | 78.37%
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 4009924.5 | 3830827.63 |  | 3830827.63 | 179096.87 | 95.53% |  | 95.53%
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 2276638 | 2058021.42 |  | 2058021.42 | 218616.58 | 90.4% |  | 90.4%
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 4471950.48 | 3634489.08 |  | 3634489.08 | 837461.4 | 81.27% |  | 81.27%
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 1116465.62 | 898206.13 |  | 898206.13 | 218259.49 | 80.45% |  | 80.45%
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 2963552.32 | 2244138.27 |  | 2244138.27 | 719414.05 | 75.72% |  | 75.72%
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 3891537.89 | 2167262.09 |  | 2167262.09 | 1724275.8 | 55.69% |  | 55.69%
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 4025666.38 | 1682481.92 | 150892.46 | 1833374.38 | 2192292 | 41.79% |  | 45.54%
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 2679486.3 | 465310.92 | 141169.63 | 606480.55 | 2073005.75 | 17.37% |  | 22.63%
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 3206350.69 | 830772.61 | 173038.37 | 1003810.98 | 2202539.71 | 25.91% |  | 31.31%
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 2796372.25 | 1334779.32 | 143959.17 | 1478738.49 | 1317633.76 | 47.73% |  | 52.88%
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 4475707.02 | 2271249.76 | 347292.4 | 2618542.16 | 1857164.86 | 50.75% |  | 58.51%
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 500000 | 179078.92 |  | 179078.92 | 320921.08 | 35.82% |  | 35.82%
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 2751921 | 1557028.35 | 123063.71 | 1680092.06 | 1071828.94 | 56.58% |  | 61.05%
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 1802500.28 | 442969.12 |  | 442969.12 | 1359531.16 | 24.58% |  | 24.58%
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 1107016 | 333671.78 | 34489.51 | 368161.29 | 738854.71 | 30.14% |  | 33.26%
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 500000 | 157260.07 | 9900 | 167160.07 | 332839.93 | 31.45% |  | 33.43%
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 4122190 | 269085.96 | 12070 | 281155.96 | 3841034.04 | 6.528% |  | 6.821%
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 166667 | 22851.36 |  | 22851.36 | 143815.64 | 13.71% |  | 13.71%
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 166667 | 27131.3 |  | 27131.3 | 139535.7 | 16.28% |  | 16.28%
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 950000 | 8444.7 |  | 8444.7 | 941555.3 | 0.8889% |  | 0.8889%
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 950000 | 19761.25 |  | 19761.25 | 930238.75 | 2.08% |  | 2.08%
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 950000 | 12501.35 |  | 12501.35 | 937498.65 | 1.316% |  | 1.316%
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 150000 | 21438.66 |  | 21438.66 | 128561.34 | 14.29% |  | 14.29%
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 150000 | 25600.52 |  | 25600.52 | 124399.48 | 17.07% |  | 17.07%
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 300000 | 58851.03 |  | 58851.03 | 241148.97 | 19.62% |  | 19.62%
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 950000 | 35982.42 |  | 35982.42 | 914017.58 | 3.788% |  | 3.788%
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 950000 | 26846.89 |  | 26846.89 | 923153.11 | 2.826% |  | 2.826%
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 400000 | 5580.4 |  | 5580.4 | 394419.6 | 1.395% |  | 1.395%
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 400000 | 2212.64 |  | 2212.64 | 397787.36 | 0.5532% |  | 0.5532%
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 100000 | 12840.17 |  | 12840.17 | 87159.83 | 12.84% |  | 12.84%
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 150000 | 1077.8 |  | 1077.8 | 148922.2 | 0.7185% |  | 0.7185%
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 150000 | 898.31 |  | 898.31 | 149101.69 | 0.5989% |  | 0.5989%
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 200000 | 855 |  | 855 | 199145 | 0.4275% |  | 0.4275%
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 150000 | 164.72 |  | 164.72 | 149835.28 | 0.1098% |  | 0.1098%
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 150000 | 1435.47 |  | 1435.47 | 148564.53 | 0.957% |  | 0.957%
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 650000 |  |  |  | 650000
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 100000 |  |  |  | 100000
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 150000 |  |  |  | 150000
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 150000 |  |  |  | 150000
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 125000 |  |  |  | 125000
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 75000 |  |  |  | 75000
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 100000 |  |  |  | 100000
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 100000 |  |  |  | 100000

## Project Partner
Order | Order Text | Planning Order | User Status | Main Work Center (PM | County Cd | Major Work Category | MaintActivityType | Job Owner | Estimator | WBS Element | ADE | Project Cont Analyst | Const Manager Civil | Const Manager Elec | Contract Specialist | Engineer of Record | Responsible Engineer | MC Engineer | Tline Civil Dsgn | Tline Civil Proj Eng | Tline Design Eng 1 | Sub Civil Proj Engin | Prot Engineer-Dist | Prot Engineer-Trans | Tline Proj Eng | Sub Project Engineer | Total Actual $
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 5782580 | ESTS | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015426.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 50474.29
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 5782532 | PEND | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015417.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 591126.85
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 5782533 | ESTS | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015416.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 320626.81
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 5782534 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2706370.01
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 5782535 | PEND | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015414.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 306635.06
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 5782588 | FICL | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015420.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 3103351.2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 5783070 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015569.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2313662.14
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 5783071 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015568.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1677909.82
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 5785512 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015417.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1978630.53
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 5785513 | ESTS | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015417.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 617113.95
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 5785514 | FICL | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015417.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1945492.6
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 5785515 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015417.05 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2621459.58
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 5785516 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015416.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 3786637.1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 5785517 | ESTS | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015416.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 599887.87
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 5785598 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015416.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 3101220.78
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 5785599 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015416.05 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 5379872.97
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 5785600 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2635581.04
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 5785601 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2848313.16
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 5785602 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2686391.99
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 5785603 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.05 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 4548604.36
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 5785604 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015415.06 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 3830827.63
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 5785605 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015414.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2058021.42
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 5785606 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015414.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 3634489.08
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 5785607 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015414.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 898206.13
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 5785652 | DOCC | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015420.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2244138.27
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 5785656 | FICL | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5015420.06 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2167262.09
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 5785721 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015568.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1682481.92
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 5785722 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015568.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 465310.92
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 5785723 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015568.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 830772.61
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 5785724 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015568.05 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1334779.32
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 5786518 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015567.06 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2271249.76
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 5786480 | ESTS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015531.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 179078.92
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 5788622 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015531.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1557028.35
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 5788623 | PEND | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015531.04 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 442969.12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 5788624 | CONS | Grass Valley | 029-Nevada County | 08 | 08W |  |  | E.5015531.05 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 333671.78
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 5788783 | PEND | Auburn | 009-El Dorado County | 08 | 08W |  |  | E.5025635.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 157260.07
35145540 | PSPS - FROGTOWN 1702 - CB | 5788779 | PEND | Angels Camp | 005-Calaveras County | 08 | 08W |  |  | E.5025634.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 269085.96
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 5539442 | ESTS | Auburn | 009-El Dorado County | 08 | 08W |  |  | E.5015426.02 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 22851.36
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 5790011 | ESTS | Auburn | 009-El Dorado County | 08 | 08W |  |  | E.5015426.03 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 27131.3
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 5790003 | UNSE | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5030964.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 8444.7
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 5790002 | UNSE | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5033921.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 19761.25
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 5790004 | UNSE | Placerville | 009-El Dorado County | 08 | 08W |  |  | E.5033920.01 |  |  |  |  | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 12501.35
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 5794208 | UNSE | Chico | 032-Plumas County | 08 | 08W |  |  | E.5034607.01.01 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 21438.66
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 5794204 | UNSE | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.01 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 25600.52
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 5543352 | ADER | Oroville | 004-Butte County | 08 | 08W |  |  | E.5034802.01.01 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 58851.03
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 5794981 | UNSE | Oroville | 004-Butte County | 08 | 08W |  |  | E.5034757.01.01 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 35982.42
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 5794987 | UNSE | Oroville | 004-Butte County | 08 | 08W |  |  | E.5034763.01.01 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 26846.89
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 5794208 | UNSE | Chico | 032-Plumas County | 08 | 08W |  |  | E.5034607.01.02 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 5580.4
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 5794208 | UNSE | Chico | 032-Plumas County | 08 | 08W |  |  | E.5034607.01.03 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 2212.64
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | 5794555 | UNSE | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034714.01.03 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 12840.17
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 5794204 | ESTS | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.02 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1077.8
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 5794204 | UNSE | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.03 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 898.31
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 5794204 | UNSE | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.04 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 855
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 5794204 | ESTS | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.05 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 164.72
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 5794204 | ESTS | Redding | 045-Shasta County | 08 | 08W |  |  | E.5034611.01.06 |  | # | # | # | # | # | # | # | # | # | # | # | # | # | Not assigned | # | 1435.47