## Spend Pivot
Row Labels | Order | Order Name | MAT | AJE | Actuals | Forecast | EAC | Sum of Variance $ (Auth Amt - EAC) | Sum of Jan 2021 Actual Amt | Sum of Feb 2021 Actual Amt | Sum of Mar 2021 Actual Amt | Sum of Apr 2021 Actual Amt | Sum of May 2021 Plan Amt | Sum of Jun 2021 Plan Amt | Sum of Jul 2021 Plan Amt | Sum of Aug 2021 Plan Amt | Sum of Sep 2021 Plan Amt | Sum of Oct 2021 Plan Amt | Sum of Nov 2021 Plan Amt | Sum of Dec 2021 Plan Amt
UNSE | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
ESTS | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W
Activity Type Total
Contract Total
Order Other Costs
| 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
PEND | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35145540 | PSPS - FROGTOWN 1702 - CB | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W
Activity Type Total
Material Total
Order Other Costs
| 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
CONS | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
DOCC | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W
Activity Type Total
Billing Credits and Reimbursements
Contract Total
Material Total
Order Other Costs
| 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB
Activity Type Total
Contract Total
Order Other Costs
MAPP | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
FICL | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
| 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W
Activity Type Total
Contract Total
Material Total
Order Other Costs
Grand Total

## Sheet1
PM | Status | 31365686 | Used
35112582 | #N/A | 35085549 | Used
35125688 | Used | 35094391 | Used
35135520 | #N/A | 35094396 | Used
35046211 | Used | 35120690 | Used
35050942 | Used | 35157845 | Used
35050951 | Used | 35094394 | Used
35085680 | #N/A | 35094397 | Used
35094389 | #N/A | 31157671 | Used
35094395 | #N/A | 31365686 | Used
31383064 | Used | 31383064 | Used
35026380 | Used | 35085549 | Used
35031040 | Used | 35117061 | Used
35042922 | Used | 35117061 | Used
35109821 | Used | 35120690 | Used
35112572 | #N/A | 35125414 | Used
35125414 | Used | 35125688 | Used
35125681 | #N/A | 35026380 | Used
35125687 | #N/A | 35031040 | Used
35145524 | #N/A | 35042922 | Used
35191385 | #N/A | 35046211 | Used
31157671 | Used | 35050942 | Used
31182216 | #N/A | 35050951 | Used
31276229 | #N/A | 35109821 | Used
31365686 | Used
31474477 | #N/A
35070591 | #N/A
35080162 | #N/A
35085549 | Used
35117061 | Used
31383321 | #N/A
31383323 | #N/A
31383324 | #N/A
35065174 | #N/A
35112581 | #N/A
35152630 | #N/A
31334291 | #N/A
35094391 | Used
35094396 | Used
31474256 | #N/A
31480124 | #N/A
31480127 | #N/A
35120690 | Used
35043296 | #N/A
35094394 | Used
35094397 | Used
35157845 | Used
31258120 | #N/A
31361965 | #N/A
31082390 | #N/A
35072146 | #N/A
35085393 | #N/A
35085532 | #N/A
35085534 | #N/A
35085535 | #N/A
35085536 | #N/A
35085537 | #N/A
35085539 | #N/A
35085681 | #N/A
35094390 | #N/A
74022390 | #N/A
35094388 | #N/A
35085533 | #N/A
35085538 | #N/A
35094392 | #N/A
35094393 | #N/A
31062191 | #N/A
31320428 | #N/A
31320429 | #N/A
35048122 | #N/A
35048276 | #N/A
74022385 | #N/A
35145525 | #N/A

## Summary - Act vs. Auth Amt
PRJ002-PS Forecast Report - Summary To Date
|  |  |  | Total Actual $ | Total Fcst $ | Total EAC $ | Auth Amt (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Total Act $ /Auth Amt) | Total Actual Hrs | Total Fcst Hrs | Total EAC Hrs | Auth Hrs (AJE) | Variance Hrs (Auth Hrs - EAC Hrs) | Variance %
WBS Element Level 2 | Order |  | Cost Element | $ | $ | $ | $ | $ | % | % | HRS | HRS | HRS | HRS | HRS | %
Overall Result | [10 empty] | 30700 | 10617.12 | 41317.12 | 28358 | -12959.12 | -45.6983
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Order Financial Costs | [7 empty] | 589 | 980.01 | 1569.01 |  | -1569.01 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 589 | 980.01 | 1569.01 |  | -1569.01 | X
|  |  | Activity Type Total | [7 empty] | 589 | 980.01 | 1569.01 |  | -1569.01 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Order Financial Costs | [7 empty] | 65.75 |  | 65.75 |  | -65.75 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 65.75 |  | 65.75 |  | -65.75 | X
|  |  | Activity Type Total | [7 empty] | 65.75 |  | 65.75 |  | -65.75 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Order Financial Costs | [7 empty] | 123 |  | 123 | 185 | 62 | 33.5135
|  |  | Orders Costs-Directs & Credits | [7 empty] | 123 |  | 123 | 185 | 62 | 33.5135
|  |  | Activity Type Total | [7 empty] | 123 |  | 123 | 185 | 62 | 33.5135
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Order Financial Costs | [7 empty] | 103 |  | 103 | 99 | -4 | -4.0404
|  |  | Orders Costs-Directs & Credits | [7 empty] | 103 |  | 103 | 99 | -4 | -4.0404
|  |  | Activity Type Total | [7 empty] | 103 |  | 103 | 99 | -4 | -4.0404
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Order Financial Costs | [7 empty] | 162.25 |  | 162.25 | 437 | 274.75 | 62.8719
|  |  | Orders Costs-Directs & Credits | [7 empty] | 162.25 |  | 162.25 | 437 | 274.75 | 62.8719
|  |  | Activity Type Total | [7 empty] | 162.25 |  | 162.25 | 437 | 274.75 | 62.8719
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Order Financial Costs | [7 empty] | 117.75 |  | 117.75 | 345 | 227.25 | 65.8696
|  |  | Orders Costs-Directs & Credits | [7 empty] | 117.75 |  | 117.75 | 345 | 227.25 | 65.8696
|  |  | Activity Type Total | [7 empty] | 117.75 |  | 117.75 | 345 | 227.25 | 65.8696
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Order Financial Costs | [7 empty] | 83.75 |  | 83.75 | 362 | 278.25 | 76.8646
|  |  | Orders Costs-Directs & Credits | [7 empty] | 83.75 |  | 83.75 | 362 | 278.25 | 76.8646
|  |  | Activity Type Total | [7 empty] | 83.75 |  | 83.75 | 362 | 278.25 | 76.8646
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Order Financial Costs | [7 empty] | 138 |  | 138 | 137 | -1 | -0.72993
|  |  | Orders Costs-Directs & Credits | [7 empty] | 138 |  | 138 | 137 | -1 | -0.72993
|  |  | Activity Type Total | [7 empty] | 138 |  | 138 | 137 | -1 | -0.72993
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Order Financial Costs | [7 empty] | 103.75 |  | 103.75 | 157 | 53.25 | 33.9172
|  |  | Orders Costs-Directs & Credits | [7 empty] | 103.75 |  | 103.75 | 157 | 53.25 | 33.9172
|  |  | Activity Type Total | [7 empty] | 103.75 |  | 103.75 | 157 | 53.25 | 33.9172
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Order Financial Costs | [7 empty] | 68.5 |  | 68.5 | 270 | 201.5 | 74.6296
|  |  | Orders Costs-Directs & Credits | [7 empty] | 68.5 |  | 68.5 | 270 | 201.5 | 74.6296
|  |  | Activity Type Total | [7 empty] | 68.5 |  | 68.5 | 270 | 201.5 | 74.6296
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Order Financial Costs | [7 empty] | 138 | 77.9 | 215.9 |  | -215.9 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 138 | 77.9 | 215.9 |  | -215.9 | X
|  |  | Activity Type Total | [7 empty] | 138 | 77.9 | 215.9 |  | -215.9 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Order Financial Costs | [7 empty] | 108.5 |  | 108.5 | 155 | 46.5 | 30
|  |  | Orders Costs-Directs & Credits | [7 empty] | 108.5 |  | 108.5 | 155 | 46.5 | 30
|  |  | Activity Type Total | [7 empty] | 108.5 |  | 108.5 | 155 | 46.5 | 30
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Order Financial Costs | [7 empty] | 90.25 | 77.85 | 168.1 |  | -168.1 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 90.25 | 77.85 | 168.1 |  | -168.1 | X
|  |  | Activity Type Total | [7 empty] | 90.25 | 77.85 | 168.1 |  | -168.1 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Order Financial Costs | [7 empty] | 63.25 |  | 63.25 | 133 | 69.75 | 52.4436
|  |  | Orders Costs-Directs & Credits | [7 empty] | 63.25 |  | 63.25 | 133 | 69.75 | 52.4436
|  |  | Activity Type Total | [7 empty] | 63.25 |  | 63.25 | 133 | 69.75 | 52.4436
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Order Financial Costs | [7 empty] | 191.75 |  | 191.75 |  | -191.75 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 191.75 |  | 191.75 |  | -191.75 | X
|  |  | Activity Type Total | [7 empty] | 191.75 |  | 191.75 |  | -191.75 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Order Financial Costs | [7 empty] | 493.5 | 40.01 | 533.51 |  | -533.51 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 493.5 | 40.01 | 533.51 |  | -533.51 | X
|  |  | Activity Type Total | [7 empty] | 493.5 | 40.01 | 533.51 |  | -533.51 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Order Financial Costs | [7 empty] | 137.75 |  | 137.75 | 100 | -37.75 | -37.75
|  |  | Orders Costs-Directs & Credits | [7 empty] | 137.75 |  | 137.75 | 100 | -37.75 | -37.75
|  |  | Activity Type Total | [7 empty] | 137.75 |  | 137.75 | 100 | -37.75 | -37.75
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Order Financial Costs | [7 empty] | 154.25 | 77.31 | 231.56 |  | -231.56 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 154.25 | 77.31 | 231.56 |  | -231.56 | X
|  |  | Activity Type Total | [7 empty] | 154.25 | 77.31 | 231.56 |  | -231.56 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Order Financial Costs | [7 empty] | 93 |  | 93 | 268 | 175 | 65.2985
|  |  | Orders Costs-Directs & Credits | [7 empty] | 93 |  | 93 | 268 | 175 | 65.2985
|  |  | Activity Type Total | [7 empty] | 93 |  | 93 | 268 | 175 | 65.2985
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Order Financial Costs | [7 empty] | 84.75 |  | 84.75 | 242 | 157.25 | 64.9793
|  |  | Orders Costs-Directs & Credits | [7 empty] | 84.75 |  | 84.75 | 242 | 157.25 | 64.9793
|  |  | Activity Type Total | [7 empty] | 84.75 |  | 84.75 | 242 | 157.25 | 64.9793
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Order Financial Costs | [7 empty] | 216 |  | 216 | 97 | -119 | -122.6804
|  |  | Orders Costs-Directs & Credits | [7 empty] | 216 |  | 216 | 97 | -119 | -122.6804
|  |  | Activity Type Total | [7 empty] | 216 |  | 216 | 97 | -119 | -122.6804
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Order Financial Costs | [7 empty] | 378.5 |  | 378.5 | 193 | -185.5 | -96.114
|  |  | Orders Costs-Directs & Credits | [7 empty] | 378.5 |  | 378.5 | 193 | -185.5 | -96.114
|  |  | Activity Type Total | [7 empty] | 378.5 |  | 378.5 | 193 | -185.5 | -96.114
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Order Financial Costs | [7 empty] | 184 |  | 184 | 152 | -32 | -21.0526
|  |  | Orders Costs-Directs & Credits | [7 empty] | 184 |  | 184 | 152 | -32 | -21.0526
|  |  | Activity Type Total | [7 empty] | 184 |  | 184 | 152 | -32 | -21.0526
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Order Financial Costs | [7 empty] | 106.5 | 78.2 | 184.7 |  | -184.7 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 106.5 | 78.2 | 184.7 |  | -184.7 | X
|  |  | Activity Type Total | [7 empty] | 106.5 | 78.2 | 184.7 |  | -184.7 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | Order Financial Costs | [7 empty] | 1 | 80 | 81 |  | -81 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 1 | 80 | 81 |  | -81 | X
|  |  | Activity Type Total | [7 empty] | 1 | 80 | 81 |  | -81 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Order Financial Costs | [7 empty] | 3 | 80 | 83 |  | -83 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 3 | 80 | 83 |  | -83 | X
|  |  | Activity Type Total | [7 empty] | 3 | 80 | 83 |  | -83 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Order Financial Costs | [7 empty] | 586 | 77.87 | 663.87 |  | -663.87 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 586 | 77.87 | 663.87 |  | -663.87 | X
|  |  | Activity Type Total | [7 empty] | 586 | 77.87 | 663.87 |  | -663.87 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Order Financial Costs | [7 empty] | 3580 |  | 3580 |  | -3580 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 3580 |  | 3580 |  | -3580 | X
|  |  | Activity Type Total | [7 empty] | 3580 |  | 3580 |  | -3580 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Order Financial Costs | [7 empty] | 115 | 39.99 | 154.99 | 1845 | 1690.01 | 91.5995
|  |  | Orders Costs-Directs & Credits | [7 empty] | 115 | 39.99 | 154.99 | 1845 | 1690.01 | 91.5995
|  |  | Activity Type Total | [7 empty] | 115 | 39.99 | 154.99 | 1845 | 1690.01 | 91.5995
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Order Financial Costs | [7 empty] | 80.5 |  | 80.5 |  | -80.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 80.5 |  | 80.5 |  | -80.5 | X
|  |  | Activity Type Total | [7 empty] | 80.5 |  | 80.5 |  | -80.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Order Financial Costs | [7 empty] | 4360.5 | 300 | 4660.5 | 5549 | 888.5 | 16.0119
|  |  | Orders Costs-Directs & Credits | [7 empty] | 4360.5 | 300 | 4660.5 | 5549 | 888.5 | 16.0119
|  |  | Activity Type Total | [7 empty] | 4360.5 | 300 | 4660.5 | 5549 | 888.5 | 16.0119
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
Billing Credits and Reimbursements
Billing Credits
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Order Financial Costs | [7 empty] | 2883 | 780 | 3663 | 5142 | 1479 | 28.7631
|  |  | Orders Costs-Directs & Credits | [7 empty] | 2883 | 780 | 3663 | 5142 | 1479 | 28.7631
|  |  | Activity Type Total | [7 empty] | 2883 | 780 | 3663 | 5142 | 1479 | 28.7631
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Order Financial Costs | [7 empty] | 3120.75 | 100 | 3220.75 | 1160 | -2060.75 | -177.6509
|  |  | Orders Costs-Directs & Credits | [7 empty] | 3120.75 | 100 | 3220.75 | 1160 | -2060.75 | -177.6509
|  |  | Activity Type Total | [7 empty] | 3120.75 | 100 | 3220.75 | 1160 | -2060.75 | -177.6509
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Order Financial Costs | [7 empty] | 142 | 380 | 522 | 4108 | 3586 | 87.2931
|  |  | Orders Costs-Directs & Credits | [7 empty] | 142 | 380 | 522 | 4108 | 3586 | 87.2931
|  |  | Activity Type Total | [7 empty] | 142 | 380 | 522 | 4108 | 3586 | 87.2931
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Order Financial Costs | [7 empty] | 1086.25 | 780 | 1866.25 | 3612 | 1745.75 | 48.3319
|  |  | Orders Costs-Directs & Credits | [7 empty] | 1086.25 | 780 | 1866.25 | 3612 | 1745.75 | 48.3319
|  |  | Activity Type Total | [7 empty] | 1086.25 | 780 | 1866.25 | 3612 | 1745.75 | 48.3319
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Order Financial Costs | [7 empty] | 3726.75 | 680 | 4406.75 | 3409 | -997.75 | -29.2681
|  |  | Orders Costs-Directs & Credits | [7 empty] | 3726.75 | 680 | 4406.75 | 3409 | -997.75 | -29.2681
|  |  | Activity Type Total | [7 empty] | 3726.75 | 680 | 4406.75 | 3409 | -997.75 | -29.2681
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Order Financial Costs | [7 empty] | 5182.75 | 400 | 5582.75 |  | -5582.75 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 5182.75 | 400 | 5582.75 |  | -5582.75 | X
|  |  | Activity Type Total | [7 empty] | 5182.75 | 400 | 5582.75 |  | -5582.75 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | Order Financial Costs | [7 empty] | 649.75 | 40 | 689.75 |  | -689.75 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 649.75 | 40 | 689.75 |  | -689.75 | X
|  |  | Activity Type Total | [7 empty] | 649.75 | 40 | 689.75 |  | -689.75 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Order Financial Costs | [7 empty] | 319 | 39.99 | 358.99 |  | -358.99 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 319 | 39.99 | 358.99 |  | -358.99 | X
|  |  | Activity Type Total | [7 empty] | 319 | 39.99 | 358.99 |  | -358.99 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Order Financial Costs | [7 empty] | 0.5 | 80 | 80.5 |  | -80.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 0.5 | 80 | 80.5 |  | -80.5 | X
|  |  | Activity Type Total | [7 empty] | 0.5 | 80 | 80.5 |  | -80.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Order Financial Costs | [7 empty] | 2.5 | 80 | 82.5 |  | -82.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 2.5 | 80 | 82.5 |  | -82.5 | X
|  |  | Activity Type Total | [7 empty] | 2.5 | 80 | 82.5 |  | -82.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Order Financial Costs | [7 empty] | 4 | 80 | 84 |  | -84 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 4 | 80 | 84 |  | -84 | X
|  |  | Activity Type Total | [7 empty] | 4 | 80 | 84 |  | -84 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Order Financial Costs | [7 empty] | 63.75 | 2256.77 | 2320.52 |  | -2320.52 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 63.75 | 2256.77 | 2320.52 |  | -2320.52 | X
|  |  | Activity Type Total | [7 empty] | 63.75 | 2256.77 | 2320.52 |  | -2320.52 | X
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Order Financial Costs | [7 empty] | 49 | 80.01 | 129.01 |  | -129.01 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 49 | 80.01 | 129.01 |  | -129.01 | X
|  |  | Activity Type Total | [7 empty] | 49 | 80.01 | 129.01 |  | -129.01 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Order Financial Costs | [7 empty] | 24.5 | 80.01 | 104.51 |  | -104.51 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 24.5 | 80.01 | 104.51 |  | -104.51 | X
|  |  | Activity Type Total | [7 empty] | 24.5 | 80.01 | 104.51 |  | -104.51 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Order Financial Costs | [7 empty] | 45.5 | 80 | 125.5 |  | -125.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 45.5 | 80 | 125.5 |  | -125.5 | X
|  |  | Activity Type Total | [7 empty] | 45.5 | 80 | 125.5 |  | -125.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Order Financial Costs | [7 empty] | 13 | 207.33 | 220.33 |  | -220.33 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 13 | 207.33 | 220.33 |  | -220.33 | X
|  |  | Activity Type Total | [7 empty] | 13 | 207.33 | 220.33 |  | -220.33 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Order Financial Costs | [7 empty] | 5 | 79.99 | 84.99 |  | -84.99 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 5 | 79.99 | 84.99 |  | -84.99 | X
|  |  | Activity Type Total | [7 empty] | 5 | 79.99 | 84.99 |  | -84.99 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Order Financial Costs | [7 empty] | 8.5 | 73.88 | 82.38 |  | -82.38 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 8.5 | 73.88 | 82.38 |  | -82.38 | X
|  |  | Activity Type Total | [7 empty] | 8.5 | 73.88 | 82.38 |  | -82.38 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
| 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Order Financial Costs | [7 empty] | 2.5 | 467 | 469.5 |  | -469.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 2.5 | 467 | 469.5 |  | -469.5 | X
|  |  | Activity Type Total | [7 empty] | 2.5 | 467 | 469.5 |  | -469.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Order Financial Costs | [7 empty] | 238 | 80 | 318 |  | -318 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 238 | 80 | 318 |  | -318 | X
|  |  | Activity Type Total | [7 empty] | 238 | 80 | 318 |  | -318 | X
Material Total
Contract Total
Order Other Costs
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Order Financial Costs | [7 empty] | 185.5 | 76 | 261.5 |  | -261.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 185.5 | 76 | 261.5 |  | -261.5 | X
|  |  | Activity Type Total | [7 empty] | 185.5 | 76 | 261.5 |  | -261.5 | X
Material Total
Contract Total
Order Other Costs
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Order Financial Costs | [7 empty] | 72.5 | 1787 | 1859.5 |  | -1859.5 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 72.5 | 1787 | 1859.5 |  | -1859.5 | X
|  |  | Activity Type Total | [7 empty] | 72.5 | 1787 | 1859.5 |  | -1859.5 | X
Material Total
|  |  | Contract Total | [12 empty] | X
Order Other Costs
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Order Financial Costs | [7 empty] | 8.75 |  | 8.75 |  | -8.75 | X
|  |  | Orders Costs-Directs & Credits | [7 empty] | 8.75 |  | 8.75 |  | -8.75 | X
|  |  | Activity Type Total | [7 empty] | 8.75 |  | 8.75 |  | -8.75 | X
Material Total
Order Other Costs
| 41812476 | LINE 172A MP31.46 EXPOSED PIPE | Order Financial Costs | [7 empty] | 145.5 |  | 145.5 | 201 | 55.5 | 27.6119
|  |  | Orders Costs-Directs & Credits | [7 empty] | 145.5 |  | 145.5 | 201 | 55.5 | 27.6119
|  |  | Activity Type Total | [7 empty] | 145.5 |  | 145.5 | 201 | 55.5 | 27.6119
Contract Total
Order Other Costs

## Monthly Detail - Dollars
PRJ002-PS Monthly Detail - Dollars
| Add Order Name |  |  |  | Add CE#
WBS Element Level 2 | Order | Order Name | MaintActivityType | User Status | Cost Element | CE# | Auth Amt (AJE) | Total Actual Amount | Total Forecast | Total EAC | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | Jan 2022 Fcst Amt | Feb 2022 Fcst Amt | Mar 2022 Fcst Amt | Apr 2022 Fcst Amt | May 2022 Fcst Amt | Jun 2022 Fcst Amt | Jul 2022 Fcst Amt | Sep 2022 Fcst Amt | Oct 2022 Fcst Amt | Nov 2022 Fcst Amt | Dec 2022 Fcst Amt | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt | Variance $ (Auth Amt - EAC)
Overall Result
E.5015414.01 | Result
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | GAS Activity Charge - Type A | 5590101
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Administration | 6603000
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Construction | 6603001
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Acquisition - Misc | 6603004
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Analyst Services | 6603005
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Construction Overtime Services | 6603021
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Engineering/Mapping | 6603022
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Environmental Services | 6603024
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Management Services | 6603076
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Maintain & Operate Services | 6603083
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Field Services | 6603099
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Administrative Services - OT | 6603150
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Land Rights - Misc | 6603227
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Project Management Overtime | 6603236
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Account Services | 6603730
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Hours - Overtime | 6608194
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Estimating-Internal | 6010076
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Mapping | 6010077
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Contractor Consultant | 6608158
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Materials Not Otherwise Classified | 5300000
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Construction Supplies | 5300110
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Electrical Specialties | 5300140
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Fuels, Lubricants & Oils | 5300150
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Electl & Electronic Equipment Component | 5300200
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Measuring Instruments | 5300220
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Communication & Signaling Equipment | 5300230
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Transformers, Regulators & Capacitors | 5300260
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Fabricated Structures | 5300270
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Material Burden | PGE1MATBURD
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Material Burden | 6010000
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Consulting | PGE1CONSULTING
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Consulting Services - Environmental Perm | 5001237
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Contracts | 5490000
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Electric Construction Contract | 5490001
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Environmental Contract | 5490015
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Construction Inspection | 5490021
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Traffic Control Contracts | 5490027
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Permits/Fees | 5501090
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Land Acquisition Services | 5501093
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Employee Related | PGE1EMPLREL
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Travel / Lodging | PGE1TRVL-LODGE
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Reimbursed Mileage Expense | 5091140
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Capitalized A&G | 6010050
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Paid Time Off | 6010100
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Indirect Labor - Gas | 6010107
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Indirect Labor - IT | 6010111
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Operation Mgmt & Support - Gas | 6010115
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Operation Mgmt & Support - Cust Care | 6010118
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Operation Mgmt & Support - IT | 6010119
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Fleet OH | 6010123
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Fleet OH - Elec | 6010125
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Building Service Overhead | 6010112
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | IT Device OH | 6010113
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Benefits OH | 6010120
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Payroll Taxes OH | 6010121
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | Minor Material OH | 6010122
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | 08W | PEND | AFUDC-Equity | 5590031
E.5015414.02 | Result
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Administration | 6603000
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Management Services | 6603076
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Account Services | 6603730
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Estimating-Internal | 6010076
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Mapping | 6010077
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Construction Supplies | 5300110
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Electrical Specialties | 5300140
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Fabricated Structures | 5300270
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Material Burden | 6010000
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Contracts | 5490000
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Environmental Contract | 5490015
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Construction Inspection | 5490021
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Helicopter Contract | 6608176
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Cash Discount earned | 5006310
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Cost Adjustments | 5590042
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Capitalized A&G | 6010050
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Paid Time Off | 6010100
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Fleet OH | 6010123
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Building Service Overhead | 6010112
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | IT Device OH | 6010113
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Benefits OH | 6010120
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | Minor Material OH | 6010122
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015414.03 | Result
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Administration | 6603000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Environmental Services | 6603024
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Management Services | 6603076
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Field Services Overtime | 6603098
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Field Services | 6603099
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Account Services | 6603730
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Estimating-Internal | 6010076
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Mapping | 6010077
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Construction Supplies | 5300110
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Electrical Specialties | 5300140
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Fabricated Structures | 5300270
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Material Burden | 6010000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Contracts | 5490000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Environmental Contract | 5490015
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Construction Inspection | 5490021
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Traffic Control Contracts | 5490027
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Cash Discount earned | 5006310
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Permits/Fees | 5501090
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Cost Adjustments | 5590042
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Contingency-Planned | 5592000
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Capitalized A&G | 6010050
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Paid Time Off | 6010100
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Fleet OH | 6010123
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Building Service Overhead | 6010112
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | IT Device OH | 6010113
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Benefits OH | 6010120
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Minor Material OH | 6010122
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015414.04 | Result
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Administration | 6603000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Construction | 6603001
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Environmental Services | 6603024
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Management Services | 6603076
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Field Services | 6603099
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Administrative Services - OT | 6603150
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Land Rights - Misc | 6603227
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Account Services | 6603730
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Manage L&EM | 6603823
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Estimating-Internal | 6010076
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Mapping | 6010077
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Construction Supplies | 5300110
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Electrical Specialties | 5300140
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Fabricated Structures | 5300270
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Material Burden | 6010000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Contracts | 5490000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Environmental Contract | 5490015
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Construction Inspection | 5490021
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Cash Discount earned | 5006310
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Rents | 5007000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Permits/Fees | 5501090
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Cost Adjustments | 5590042
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Contingency-Planned | 5592000
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Capitalized A&G | 6010050
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Paid Time Off | 6010100
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Indirect Labor - Gas | 6010107
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Operation Mgmt & Support - Gas | 6010115
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Fleet OH | 6010123
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Building Service Overhead | 6010112
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | IT Device OH | 6010113
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Benefits OH | 6010120
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Minor Material OH | 6010122
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015415.01 | Result
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Electric Activity Charge - Type A | 5590100
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Administration | 6603000
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Environmental Services | 6603024
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Management Services | 6603076
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Field Services | 6603099
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Administrative Services - OT | 6603150
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | SCADA Services | 6603671
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Account Services | 6603730
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Hours - Straight Time | 6608193
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Hours - Overtime | 6608194
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Mapping | 6010077
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Gas & Water Specialties | 5300160
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Communication & Signaling Equipment | 5300230
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Transformers, Regulators & Capacitors | 5300260
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material Burden - Planning Only | 5501150
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Material Burden | 6010000
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Contracts | 5490000
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Traffic Control Contracts | 5490027
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Permits/Fees | 5501090
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Cost Adjustments | 5590042
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Contingency-Planned | 5592000
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Indirect Labor - IT | 6010111
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Operation Mgmt & Support - IT | 6010119
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Fleet OH | 6010123
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | IT Device OH | 6010113
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Benefits OH | 6010120
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | 08W | DOCC | Billing Credit - CIAC Non Taxable | 5590051
E.5015415.02 | Result
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Administration | 6603000
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Project Management Services | 6603013
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Environmental Services | 6603024
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Management Services | 6603076
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Field Services | 6603099
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Administrative Services - OT | 6603150
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Account Services | 6603730
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Manage L&EM | 6603823
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Mapping | 6010077
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Material Burden | 6010000
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Contracts | 5490000
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Helicopter Contract | 6608176
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Permits/Fees | 5501090
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Cost Adjustments | 5590042
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Contingency-Planned | 5592000
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Fleet OH | 6010123
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | IT Device OH | 6010113
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Benefits OH | 6010120
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015415.03 | Result
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Administration | 6603000
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Construction | 6603001
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Environmental Services | 6603024
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Management Services | 6603076
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Field Services | 6603099
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Account Services | 6603730
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Mapping | 6010077
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Material Burden | 6010000
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Contracts | 5490000
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Permits/Fees | 5501090
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Indirect Labor - Gas | 6010107
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Operation Mgmt & Support - Gas | 6010115
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Fleet OH | 6010123
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | IT Device OH | 6010113
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Benefits OH | 6010120
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015415.04 | Result
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Electric Activity Charge - Type A | 5590100
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Administration | 6603000
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Project Management Services | 6603013
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Environmental Services | 6603024
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Management Services | 6603076
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Field Services Overtime | 6603098
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Field Services | 6603099
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Field Services Doubletime | 6603184
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Account Services | 6603730
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Manage L&EM | 6603823
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Mapping | 6010077
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Freight | 5300320
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Purchasing Card | 5300330
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Material Burden | 6010000
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Contracts | 5490000
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Helicopter Contract | 6608176
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Cost Adjustments | 5590042
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Fleet OH | 6010123
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | IT Device OH | 6010113
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Benefits OH | 6010120
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.05 | Result
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Administration | 6603000
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Management Services | 6603076
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Field Services Overtime | 6603098
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Field Services | 6603099
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Field Services Doubletime | 6603184
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Account Services | 6603730
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Mapping | 6010077
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Material Burden | 6010000
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Contracts | 5490000
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Permits/Fees | 5501090
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Fleet OH | 6010123
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | IT Device OH | 6010113
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Benefits OH | 6010120
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Billing Credit - CIAC Non Taxable | 5590051
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015415.06 | Result
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Administration | 6603000
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Design Services | 6603017
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Environmental Services | 6603024
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Management Services | 6603076
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Field Services | 6603099
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Land Rights - Misc | 6603227
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Account Services | 6603730
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Estimating-Internal | 6010076
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Mapping | 6010077
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Construction Supplies | 5300110
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Electrical Specialties | 5300140
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Fabricated Structures | 5300270
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Material Burden | 6010000
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Contracts | 5490000
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Environmental Contract | 5490015
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Construction Inspection | 5490021
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Traffic Control Contracts | 5490027
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Cash Discount earned | 5006310
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Permits/Fees | 5501090
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Cost Adjustments | 5590042
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Contingency-Planned | 5592000
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Capitalized A&G | 6010050
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Paid Time Off | 6010100
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Fleet OH | 6010123
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Building Service Overhead | 6010112
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | IT Device OH | 6010113
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Benefits OH | 6010120
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Minor Material OH | 6010122
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015416.01 | Result
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Activity Type Cost Adjustment | 5590045
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | GAS Activity Charge - Type A | 5590101
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Administration | 6603000
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Construction | 6603001
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Acquisition - Misc | 6603004
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Analyst Services | 6603005
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Engineering/Mapping | 6603022
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Engineering Services | 6603023
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Environmental Services | 6603024
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Management Services | 6603076
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Engineering/Mapping Services Overtime | 6603106
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Administrative Services - OT | 6603150
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Land Rights - Misc | 6603227
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Project Management Overtime | 6603236
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Electric Estimating | 6603466
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Account Services | 6603730
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Hours - Straight Time | 6608193
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Estimating-Internal | 6010076
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Mapping | 6010077
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Consulting | PGE1CONSULTING
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Consulting Services - Environmental Perm | 5001237
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Contracts | 5490000
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Environmental Contract | 5490015
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Traffic Control Contracts | 5490027
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Permits/Fees | 5501090
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Land Acquisition Services | 5501093
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Employee Related | PGE1EMPLREL
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Travel / Lodging | PGE1TRVL-LODGE
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Reimbursed Mileage Expense | 5091140
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Capitalized A&G | 6010050
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Paid Time Off | 6010100
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Indirect Labor - Gas | 6010107
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Indirect Labor - IT | 6010111
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Operation Mgmt & Support - Gas | 6010115
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Operation Mgmt & Support - Cust Care | 6010118
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Operation Mgmt & Support - IT | 6010119
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Fleet OH | 6010123
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Fleet OH - Elec | 6010125
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Building Service Overhead | 6010112
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | IT Device OH | 6010113
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Benefits OH | 6010120
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | Payroll Taxes OH | 6010121
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 08W | PEND | AFUDC-Equity | 5590031
E.5015416.02 | Result
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | GAS Activity Charge - Type A | 5590101
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Administration | 6603000
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Construction | 6603001
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Management Services | 6603076
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Field Services | 6603099
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Engineering/Mapping Services Overtime | 6603106
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Account Services | 6603730
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Estimating-Internal | 6010076
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Mapping | 6010077
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Construction Supplies | 5300110
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Electrical Specialties | 5300140
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Fabricated Structures | 5300270
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Material Burden | 6010000
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Contracts | 5490000
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Environmental Contract | 5490015
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Construction Inspection | 5490021
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Traffic Control Contracts | 5490027
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Helicopter Contract | 6608176
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Cash Discount earned | 5006310
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Permits/Fees | 5501090
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Cost Adjustments | 5590042
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Contingency-Planned | 5592000
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Capitalized A&G | 6010050
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Paid Time Off | 6010100
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Indirect Labor - Gas | 6010107
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Operation Mgmt & Support - Gas | 6010115
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Fleet OH | 6010123
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Building Service Overhead | 6010112
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | IT Device OH | 6010113
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Benefits OH | 6010120
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Minor Material OH | 6010122
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015416.03 | Result
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Activity Type Cost Adjustment | 5590045
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | GAS Activity Charge - Type A | 5590101
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Cust. Care Activity Charge - Type A | 5590104
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Administration | 6603000
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Construction | 6603001
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Acquisition - Misc | 6603004
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Management Services | 6603076
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Engineering/Mapping Services Overtime | 6603106
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Land Rights - Misc | 6603227
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Electric Estimating | 6603466
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Account Services | 6603730
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Estimating-Internal | 6010076
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Mapping | 6010077
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Contractor Consultant | 6608158
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Material Burden | 6010000
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Consulting | PGE1CONSULTING
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Consulting Services - Environmental Perm | 5001237
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Consulting Services - Other | 5001250
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Contracts | 5490000
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Environmental Contract | 5490015
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Land Acquisition Services | 5501093
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Capitalized A&G | 6010050
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Paid Time Off | 6010100
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Indirect Labor - Gas | 6010107
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Operation Mgmt & Support - Gas | 6010115
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Operation Mgmt & Support - Cust Care | 6010118
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Fleet OH | 6010123
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Building Service Overhead | 6010112
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | IT Device OH | 6010113
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Benefits OH | 6010120
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | Minor Material OH | 6010122
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | 08W | ESTS | AFUDC-Equity | 5590031
E.5015416.04 | Result
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Administration | 6603000
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Environmental Services | 6603024
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Management Services | 6603076
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Field Services | 6603099
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Account Services | 6603730
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Service Planning - Planning Only | 5501163
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Estimating-Internal | 6010076
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Mapping | 6010077
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Construction Supplies | 5300110
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Electrical Specialties | 5300140
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Fabricated Structures | 5300270
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Material Burden Adjustment | 5590076
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Material Burden | 6010000
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Contracts | 5490000
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Environmental Contract | 5490015
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Construction Inspection | 5490021
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Paving Contracts | 5490500
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Cash Discount earned | 5006310
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Cost Adjustments | 5590042
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Capitalized A&G | 6010050
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Paid Time Off | 6010100
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Fleet OH | 6010123
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Building Service Overhead | 6010112
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | IT Device OH | 6010113
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Benefits OH | 6010120
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | Minor Material OH | 6010122
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015416.05 | Result
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | GAS Activity Charge - Type A | 5590101
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Administration | 6603000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Construction | 6603001
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Project Management Services | 6603013
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Management Services | 6603076
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Administrative Services - OT | 6603150
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Construction Doubletime Services | 6603180
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Land Rights - Misc | 6603227
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Account Services | 6603730
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Manage L&EM | 6603823
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Estimating-Internal | 6010076
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Mapping | 6010077
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Construction Supplies | 5300110
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Electrical Specialties | 5300140
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Fabricated Structures | 5300270
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Material Burden | 6010000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Contracts | 5490000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Environmental Contract | 5490015
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Construction Inspection | 5490021
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Traffic Control Contracts | 5490027
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Helicopter Contract | 6608176
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Cash Discount earned | 5006310
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Permits/Fees | 5501090
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Permits/Fees - Environmental | 5501091
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Other Land Fees | 5501094
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Cost Adjustments | 5590042
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Other Expenses | 5591000
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Capitalized A&G | 6010050
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Paid Time Off | 6010100
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Indirect Labor - Gas | 6010107
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Operation Mgmt & Support - Gas | 6010115
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Fleet OH | 6010123
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Building Service Overhead | 6010112
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | IT Device OH | 6010113
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Benefits OH | 6010120
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | Minor Material OH | 6010122
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015417.01 | Result
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Administration | 6603000
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Construction | 6603001
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Acquisition - Misc | 6603004
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Analyst Services | 6603005
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Construction Overtime Services | 6603021
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Engineering/Mapping | 6603022
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Environmental Services | 6603024
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Management Services | 6603076
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Engineering/Mapping Services Overtime | 6603106
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Administrative Services - OT | 6603150
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Land Rights - Misc | 6603227
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Electric Estimating | 6603466
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Electric Estimating Overtime | 6603467
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Account Services | 6603730
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Manage L&EM | 6603823
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Analyst Svcs Overtime | 6603855
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Estimating-Internal | 6010076
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Mapping | 6010077
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Material Burden | PGE1MATBURD
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Material Burden | 6010000
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Consulting | PGE1CONSULTING
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Consulting Services - Environmental Perm | 5001237
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Consulting Services - Other | 5001250
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Contracts | 5490000
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Environmental Contract | 5490015
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Traffic Control Contracts | 5490027
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Cash Discount earned | 5006310
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Permits/Fees | 5501090
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Land Acquisition Services | 5501093
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Other Land Fees | 5501094
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Employee Related | PGE1EMPLREL
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Travel / Lodging | PGE1TRVL-LODGE
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Reimbursed Mileage Expense | 5091140
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Meals | PGE1MEALS-EXP
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Meals Expense | 5091100
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Capitalized A&G | 6010050
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Paid Time Off | 6010100
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Operation Mgmt & Support - Cust Care | 6010118
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Fleet OH | 6010123
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Fleet OH - Elec | 6010125
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Building Service Overhead | 6010112
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | IT Device OH | 6010113
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Benefits OH | 6010120
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Payroll Taxes OH | 6010121
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | Minor Material OH | 6010122
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 08W | PEND | AFUDC-Equity | 5590031
E.5015417.02 | Result
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Administration | 6603000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Acquisition - Misc | 6603004
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Project Management Services | 6603013
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Environmental Services | 6603024
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Management Services | 6603076
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Vegetation Management - Misc | 6603097
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Engineering/Mapping Services Overtime | 6603106
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Administrative Services - OT | 6603150
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Account Services | 6603730
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Hours - Straight Time | 6608193
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Estimating-Internal | 6010076
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Mapping | 6010077
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Construction Supplies | 5300110
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Electrical Specialties | 5300140
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Material Burden | 6010000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Contracts | 5490000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Environmental Contract | 5490015
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Construction Inspection | 5490021
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Helicopter Contract | 6608176
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Cash Discount earned | 5006310
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Permits/Fees | 5501090
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Postage | 5510010
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Cost Adjustments | 5590042
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Contingency-Planned | 5592000
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Capitalized A&G | 6010050
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Paid Time Off | 6010100
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Indirect Labor - IT | 6010111
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Operation Mgmt & Support - IT | 6010119
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Fleet OH | 6010123
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Building Service Overhead | 6010112
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | IT Device OH | 6010113
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Benefits OH | 6010120
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Minor Material OH | 6010122
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015417.03 | Result
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | GAS Activity Charge - Type A | 5590101
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Administration | 6603000
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Construction | 6603001
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Acquisition - Misc | 6603004
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Construction Overtime Services | 6603021
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Environmental Services | 6603024
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Management Services | 6603076
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Engineering/Mapping Services Overtime | 6603106
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Administrative Services - OT | 6603150
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Land Rights - Misc | 6603227
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Electric Estimating | 6603466
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Account Services | 6603730
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Estimating-Internal | 6010076
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Mapping | 6010077
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Material Burden | 6010000
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Consulting | PGE1CONSULTING
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Consulting Services - Environmental Perm | 5001237
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Contracts | 5490000
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Environmental Contract | 5490015
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Permits/Fees | 5501090
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Land Acquisition Services | 5501093
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Employee Related | PGE1EMPLREL
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Travel / Lodging | PGE1TRVL-LODGE
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Reimbursed Mileage Expense | 5091140
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Capitalized A&G | 6010050
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Paid Time Off | 6010100
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Indirect Labor - Gas | 6010107
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Gas | 6010115
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Cust Care | 6010118
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Fleet OH | 6010123
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Building Service Overhead | 6010112
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | IT Device OH | 6010113
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Benefits OH | 6010120
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | Minor Material OH | 6010122
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | 08W | ESTS | AFUDC-Equity | 5590031
E.5015417.04 | Result
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Electric Activity Charge - Type A | 5590100
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Administration | 6603000
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Project Management Services | 6603013
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Environmental Services | 6603024
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Management Services | 6603076
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Field Services | 6603099
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Engineering/Mapping Services Overtime | 6603106
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Account Services | 6603730
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Estimating-Internal | 6010076
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Mapping | 6010077
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Construction Supplies | 5300110
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Electrical Specialties | 5300140
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Fabricated Structures | 5300270
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Material Burden | 6010000
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Contracts | 5490000
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Environmental Contract | 5490015
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Construction Inspection | 5490021
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Paving Contracts | 5490500
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Cash Discount earned | 5006310
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Rents | 5007000
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Permits/Fees | 5501090
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Postage | 5510010
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Capitalized A&G | 6010050
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Paid Time Off | 6010100
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Fleet OH | 6010123
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Building Service Overhead | 6010112
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | IT Device OH | 6010113
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Benefits OH | 6010120
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Minor Material OH | 6010122
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015417.05 | Result
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Administration | 6603000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Environmental Services | 6603024
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Management Services | 6603076
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Field Services | 6603099
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Engineering/Mapping Services Overtime | 6603106
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Account Services | 6603730
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Estimating-Internal | 6010076
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Mapping | 6010077
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Construction Supplies | 5300110
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Electrical Specialties | 5300140
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Fabricated Structures | 5300270
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Material Burden | 6010000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Contracts | 5490000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Environmental Contract | 5490015
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Construction Inspection | 5490021
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Cash Discount earned | 5006310
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Permits/Fees | 5501090
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Oth Cst Element Contingency-5592000 | PGE1OTHERCE2
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Contingency-Planned | 5592000
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Other Employee & Related Costs | PGE1OTH-EMPL
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Other Employee Related Expense | 5091200
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Capitalized A&G | 6010050
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Paid Time Off | 6010100
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Fleet OH | 6010123
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Building Service Overhead | 6010112
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | IT Device OH | 6010113
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Benefits OH | 6010120
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Minor Material OH | 6010122
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Billing Credits | PGE1BILLCR
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | 08W | DOCC | Joint Pole Billing Credit - CIAC Non Tax | 5590055
E.5015420.01 | Result
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Order Financial Costs | PGE1ORDFIN
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Activity Type Total | PGE1ACTV-TOT
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Activity Types | PGE1ACTVTYPES
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Activity Types - Internal | PGE1ACTV-INT
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Electric Activity Charge - Type A | 5590100
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Internal Services - Budget | 5600000
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Administration | 6603000
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Engineering/Mapping | 6603022
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Environmental Services | 6603024
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Environmental Planning & Permitting-Misc | 6603027
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Switching Operator Service | 6603068
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Management Services | 6603076
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Maintain & Operate Overtime Services | 6603082
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Maintain & Operate Services | 6603083
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Field Services Overtime | 6603098
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Field Services | 6603099
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Maint & Operate Doubletime Services | 6603181
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Field Services Doubletime | 6603184
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Switching Operation Svcs. - Overtime | 6603222
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Switching Oprn Svcs. - Doubletime | 6603223
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Land Rights - Misc | 6603227
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Account Services | 6603730
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Manage L&EM | 6603823
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Estimating-Internal | 6010076
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Mapping | 6010077
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Material Total | PGE1MATTOTAL
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Material related expenses | PGE1MATERIAL
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Materials Not Otherwise Classified | 5300000
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Construction Supplies | 5300110
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Conductors, Cable & Wire Connectors | 5300120
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Electrical Specialties | 5300140
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Electl & Electronic Equipment Component | 5300200
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Fabricated Structures | 5300270
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Material Burden | PGE1MATBURD
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Material Burden | 6010000
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Contract Total | PGE1CONTRACT
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Consulting | PGE1CONSULTING
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Consulting Services - Engineering | 5001230
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Consulting Services - Environmental Perm | 5001237
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Other Contract | PGE1OTHCONTRAC
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Contracts | 5490000
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Electric Construction Contract | 5490001
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Gas Construction Contract | 5490002
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Environmental Contract | 5490015
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Construction Inspection | 5490021
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Helicopter Contract | 6608176
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Order Other Costs | PGE1ORD-OTHER
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Other Cost Elements | PGE1OTHERCE
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Cash Discount earned | 5006310
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Permits/Fees | 5501090
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Land Acquisition Services | 5501093
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Employee Related | PGE1EMPLREL
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Travel / Lodging | PGE1TRVL-LODGE
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Reimbursed Mileage Expense | 5091140
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Meals | PGE1MEALS-EXP
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Meals Expense | 5091100
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Order Overheads | PGE1OVERHEAD
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Capitalized A&G | PGE1CAPAG
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Capitalized A&G | 6010050
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Labor Overheads | PGE1LABOROH
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Paid Time Off | 6010100
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Indirect Labor - Electric | 6010106
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Indirect Labor - Environmental Land | 6010108
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Indirect Labor - Cust Care | 6010110
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Operation Mgmt & Support - Electric | 6010114
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Operation Mgmt & Support - Environ Land | 6010116
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Operation Mgmt & Support - Cust Care | 6010118
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Fleet OH | 6010123
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Fleet OH - Elec | 6010125
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Building Service Overhead | 6010112
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | IT Device OH | 6010113
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Other Overhead | PGE1OTHEROH
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Benefits OH | 6010120
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Payroll Taxes OH | 6010121
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | Minor Material OH | 6010122
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | AFUDC Costs | PGE1AFUDCDIR
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | AFUDC-Borrowed | 5590030
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | 08W | FICL | AFUDC-Equity | 5590031
E.5015420.02 | Result
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Order Financial Costs | PGE1ORDFIN
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Activity Type Total | PGE1ACTV-TOT
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Activity Types | PGE1ACTVTYPES
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Activity Types - Internal | PGE1ACTV-INT
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Activity Type Cost Adjustment | 5590045
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Electric Activity Charge - Type A | 5590100
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Internal Services - Budget | 5600000
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Administration | 6603000
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Construction | 6603001
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Construction Overtime Services | 6603021
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Engineering/Mapping | 6603022
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Environmental Services | 6603024
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Environmental Planning & Permitting-Misc | 6603027
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operating Services | 6603045
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Switching Operator Service | 6603068
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Management Services | 6603076
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Maintain & Operate Overtime Services | 6603082
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Maintain & Operate Services | 6603083
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Field Services Overtime | 6603098
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Field Services | 6603099
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Engineering/Mapping Services Overtime | 6603106
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Maint & Operate Doubletime Services | 6603181
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Field Services Doubletime | 6603184
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | SCADA Services | 6603671
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Account Services | 6603730
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Apprentice | 6603844
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Hours - Straight Time | 6608193
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Hours - Overtime | 6608194
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Estimating-Internal | 6010076
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Mapping | 6010077
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Material Total | PGE1MATTOTAL
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Material related expenses | PGE1MATERIAL
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Materials Not Otherwise Classified | 5300000
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Construction Supplies | 5300110
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Conductors, Cable & Wire Connectors | 5300120
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Electrical Specialties | 5300140
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Gas & Water Specialties | 5300160
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Electl & Electronic Equipment Component | 5300200
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Communication & Signaling Equipment | 5300230
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Transformers, Regulators & Capacitors | 5300260
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Fabricated Structures | 5300270
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Material Burden | PGE1MATBURD
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Material Burden | 6010000
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Contract Total | PGE1CONTRACT
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Consulting | PGE1CONSULTING
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Consulting Services - Engineering | 5001230
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Consulting Services - Environmental Perm | 5001237
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Consulting Services - Other | 5001250
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Other Contract | PGE1OTHCONTRAC
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Contracts | 5490000
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Electric Construction Contract | 5490001
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Gas Construction Contract | 5490002
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Environmental Contract | 5490015
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Construction Inspection | 5490021
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Order Other Costs | PGE1ORD-OTHER
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Other Cost Elements | PGE1OTHERCE
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Cash Discount earned | 5006310
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Permits/Fees | 5501090
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Land Acquisition Services | 5501093
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Employee Related | PGE1EMPLREL
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Travel / Lodging | PGE1TRVL-LODGE
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Reimbursed Mileage Expense | 5091140
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Meals | PGE1MEALS-EXP
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Meals Expense | 5091100
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Order Overheads | PGE1OVERHEAD
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Capitalized A&G | PGE1CAPAG
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Capitalized A&G | 6010050
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Labor Overheads | PGE1LABOROH
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Paid Time Off | 6010100
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Indirect Labor - Electric | 6010106
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Indirect Labor - Gas | 6010107
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Indirect Labor - Environmental Land | 6010108
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Indirect Labor - Cust Care | 6010110
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Indirect Labor - IT | 6010111
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operation Mgmt & Support - Electric | 6010114
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operation Mgmt & Support - Gas | 6010115
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operation Mgmt & Support - Environ Land | 6010116
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operation Mgmt & Support - Cust Care | 6010118
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Operation Mgmt & Support - IT | 6010119
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Fleet OH | 6010123
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Fleet OH - Elec | 6010125
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Building Service Overhead | 6010112
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | IT Device OH | 6010113
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Other Overhead | PGE1OTHEROH
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Benefits OH | 6010120
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Payroll Taxes OH | 6010121
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | Minor Material OH | 6010122
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | AFUDC Costs | PGE1AFUDCDIR
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | AFUDC-Borrowed | 5590030
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | 08W | DOCC | AFUDC-Equity | 5590031
E.5015420.06 | Result
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Order Financial Costs | PGE1ORDFIN
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Activity Type Total | PGE1ACTV-TOT
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Activity Types | PGE1ACTVTYPES
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Activity Types - Internal | PGE1ACTV-INT
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Activity Type Cost Adjustment | 5590045
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Internal Services - Budget | 5600000
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Administration | 6603000
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Construction | 6603001
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Acquisition - Misc | 6603004
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Construction Overtime Services | 6603021
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Engineering/Mapping | 6603022
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Environmental Planning & Permitting-Misc | 6603027
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Switching Operator Service | 6603068
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Management Services | 6603076
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Maintain & Operate Services | 6603083
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Field Services | 6603099
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Administrative Services - OT | 6603150
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Maint & Operate Doubletime Services | 6603181
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Land Rights - Misc | 6603227
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Account Services | 6603730
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Manage L&EM | 6603823
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Estimating-Internal | 6010076
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Mapping | 6010077
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Contractor Consultant | 6608158
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Material Total | PGE1MATTOTAL
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Material related expenses | PGE1MATERIAL
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Materials Not Otherwise Classified | 5300000
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Construction Supplies | 5300110
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Conductors, Cable & Wire Connectors | 5300120
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Electrical Specialties | 5300140
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Gas & Water Specialties | 5300160
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Electl & Electronic Equipment Component | 5300200
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Fabricated Structures | 5300270
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Material Burden | PGE1MATBURD
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Material Burden | 6010000
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Contract Total | PGE1CONTRACT
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Consulting | PGE1CONSULTING
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Consulting Services - Engineering | 5001230
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Consulting Services - Environmental Perm | 5001237
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Consulting Services - Other | 5001250
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Other Contract | PGE1OTHCONTRAC
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Contracts | 5490000
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Electric Construction Contract | 5490001
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Gas Construction Contract | 5490002
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Environmental Contract | 5490015
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Construction Inspection | 5490021
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Traffic Control Contracts | 5490027
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Order Other Costs | PGE1ORD-OTHER
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Other Cost Elements | PGE1OTHERCE
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Cash Discount earned | 5006310
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Permits/Fees | 5501090
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Land Acquisition Services | 5501093
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Other Land Fees | 5501094
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Cost Adjustments | 5590042
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Employee Related | PGE1EMPLREL
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Travel / Lodging | PGE1TRVL-LODGE
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Reimbursed Mileage Expense | 5091140
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Order Overheads | PGE1OVERHEAD
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Capitalized A&G | PGE1CAPAG
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Capitalized A&G | 6010050
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Labor Overheads | PGE1LABOROH
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Paid Time Off | 6010100
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Indirect Labor - Electric | 6010106
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Indirect Labor - Gas | 6010107
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Indirect Labor - Environmental Land | 6010108
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Indirect Labor - Cust Care | 6010110
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Operation Mgmt & Support - Electric | 6010114
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Operation Mgmt & Support - Gas | 6010115
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Operation Mgmt & Support - Environ Land | 6010116
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Operation Mgmt & Support - Cust Care | 6010118
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Fleet OH | 6010123
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Fleet OH - Elec | 6010125
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Building Service Overhead | 6010112
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | IT Device OH | 6010113
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Other Overhead | PGE1OTHEROH
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Benefits OH | 6010120
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Payroll Taxes OH | 6010121
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | Minor Material OH | 6010122
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | AFUDC Costs | PGE1AFUDCDIR
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | AFUDC-Borrowed | 5590030
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | 08W | FICL | AFUDC-Equity | 5590031
E.5015426.01 | Result
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Construction | 6603001
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Construction Overtime Services | 6603021
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Technical Services | 6603058
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Management Services | 6603076
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Engineering/Mapping Services Overtime | 6603106
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Land Rights - Misc | 6603227
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Electric Estimating | 6603466
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Hours - Straight Time | 6608193
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Hours - Overtime | 6608194
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Hours - Doubletime | 6608195
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Estimating-Internal | 6010076
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Mapping | 6010077
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Material Burden | 6010000
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Contracts | 5490000
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Environmental Contract | 5490015
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Land Acquisition Services | 5501093
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Capitalized A&G | 6010050
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Paid Time Off | 6010100
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Indirect Labor - IT | 6010111
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Operation Mgmt & Support - IT | 6010119
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Fleet OH | 6010123
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Building Service Overhead | 6010112
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | IT Device OH | 6010113
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Benefits OH | 6010120
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | Minor Material OH | 6010122
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | 08W | ESTS | AFUDC-Equity | 5590031
E.5015426.02 | Result
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Construction | 6603001
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Electric Estimating | 6603466
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Mapping | 6010077
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Material Burden | 6010000
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Contracts | 5490000
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Capitalized A&G | 6010050
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Paid Time Off | 6010100
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Fleet OH | 6010123
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Building Service Overhead | 6010112
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | IT Device OH | 6010113
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Benefits OH | 6010120
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | 08W | ESTS | Minor Material OH | 6010122
E.5015426.03 | Result
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Construction | 6603001
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Electric Estimating | 6603466
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Mapping | 6010077
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Material Burden | 6010000
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Contracts | 5490000
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Capitalized A&G | 6010050
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Paid Time Off | 6010100
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Indirect Labor - Gas | 6010107
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Operation Mgmt & Support - Gas | 6010115
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Fleet OH | 6010123
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Building Service Overhead | 6010112
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | IT Device OH | 6010113
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Benefits OH | 6010120
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | Minor Material OH | 6010122
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | 08W | ESTS | AFUDC-Equity | 5590031
E.5015531.02 | Result
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Cust. Care Activity Charge - Type A | 5590104
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Env & Land Activity Charge - Type A | 5590105
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Administration | 6603000
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Construction | 6603001
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Acquisition - Misc | 6603004
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Construction Overtime Services | 6603021
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Engineering/Mapping | 6603022
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Environmental Services | 6603024
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Administrative Services - OT | 6603150
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Land Rights - Misc | 6603227
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Electric Estimating | 6603466
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Account Services | 6603730
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Estimating-Internal | 6010076
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Mapping | 6010077
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Material Burden | 6010000
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Contracts | 5490000
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Permits/FeesLand Surveying Services | 5501092
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Land Acquisition Services | 5501093
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Cost Adjustments | 5590042
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Employee Related | PGE1EMPLREL
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Meals | PGE1MEALS-EXP
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Meals Expense | 5091100
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Capitalized A&G | 6010050
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Paid Time Off | 6010100
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Operation Mgmt & Support - Cust Care | 6010118
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Fleet OH | 6010123
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Building Service Overhead | 6010112
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | IT Device OH | 6010113
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Benefits OH | 6010120
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | Minor Material OH | 6010122
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | 08W | ESTS | AFUDC-Equity | 5590031
E.5015531.03 | Result
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Order Financial Costs | PGE1ORDFIN
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Activity Type Total | PGE1ACTV-TOT
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Activity Types | PGE1ACTVTYPES
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Activity Types - Internal | PGE1ACTV-INT
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Activity Type Cost Adjustment | 5590045
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Cust. Care Activity Charge - Type A | 5590104
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Internal Services - Budget | 5600000
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Administration | 6603000
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Construction | 6603001
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Acquisition - Misc | 6603004
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Analyst Services | 6603005
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Construction Overtime Services | 6603021
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Engineering/Mapping | 6603022
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Engineering Services | 6603023
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Environmental Planning & Permitting-Misc | 6603027
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Management Services | 6603076
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Design Overtime Services | 6603103
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Construction Doubletime Services | 6603180
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Land Rights - Misc | 6603227
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Design Services Double Time | 6603337
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Electric Estimating | 6603466
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Account Services | 6603730
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Service Planning - Planning Only | 5501163
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Estimating-Internal | 6010076
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Mapping | 6010077
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Contractor Consultant | 6608158
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Material Total | PGE1MATTOTAL
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Material related expenses | PGE1MATERIAL
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Construction Supplies | 5300110
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Conductors, Cable & Wire Connectors | 5300120
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Electrical Specialties | 5300140
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Fabricated Structures | 5300270
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Material Burden | PGE1MATBURD
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Material Burden Adjustment | 5590076
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Material Burden | 6010000
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Contract Total | PGE1CONTRACT
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Consulting | PGE1CONSULTING
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Consulting Services - Engineering | 5001230
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Consulting Services - Environmental Perm | 5001237
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Other Contract | PGE1OTHCONTRAC
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Contracts | 5490000
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Electric Construction Contract | 5490001
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Environmental Contract | 5490015
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Construction Inspection | 5490021
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Traffic Control Contracts | 5490027
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Order Other Costs | PGE1ORD-OTHER
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Other Cost Elements | PGE1OTHERCE
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Cash Discount earned | 5006310
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Permits/Fees | 5501090
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Land Acquisition Services | 5501093
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Other Land Fees | 5501094
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Postage | 5510010
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Order Overheads | PGE1OVERHEAD
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Capitalized A&G | PGE1CAPAG
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Capitalized A&G | 6010050
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Labor Overheads | PGE1LABOROH
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Paid Time Off | 6010100
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Indirect Labor - Electric | 6010106
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Indirect Labor - Gas | 6010107
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Indirect Labor - Environmental Land | 6010108
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Indirect Labor - Cust Care | 6010110
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Operation Mgmt & Support - Electric | 6010114
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Operation Mgmt & Support - Gas | 6010115
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Operation Mgmt & Support - Environ Land | 6010116
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Fleet OH | 6010123
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Fleet OH - Elec | 6010125
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Fleet OH - Gas | 6010126
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Building Service Overhead | 6010112
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | IT Device OH | 6010113
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Other Overhead | PGE1OTHEROH
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Benefits OH | 6010120
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Payroll Taxes OH | 6010121
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | Minor Material OH | 6010122
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | AFUDC Costs | PGE1AFUDCDIR
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | AFUDC-Borrowed | 5590030
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | 08W | MAPP | AFUDC-Equity | 5590031
E.5015531.04 | Result
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Cust. Care Activity Charge - Type A | 5590104
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Internal Services - Budget | 5600000
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Administration | 6603000
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Construction | 6603001
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Acquisition - Misc | 6603004
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Engineering/Mapping | 6603022
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Switching Operator Service | 6603068
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Management Services | 6603076
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Maintain & Operate Services | 6603083
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Field Services | 6603099
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Engineering/Mapping Services Overtime | 6603106
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Administrative Services - OT | 6603150
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Land Rights - Misc | 6603227
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Electric Estimating | 6603466
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Electric Estimating Overtime | 6603467
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Account Services | 6603730
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Manage L&EM | 6603823
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Estimating-Internal | 6010076
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Mapping | 6010077
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Contractor Consultant | 6608158
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Electrical Specialties | 5300140
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Material Burden | PGE1MATBURD
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Material Burden | 6010000
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Consulting | PGE1CONSULTING
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Consulting Services - Environmental Perm | 5001237
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Contracts | 5490000
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Gas Construction Contract | 5490002
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Environmental Contract | 5490015
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Traffic Control Contracts | 5490027
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Rents | 5007000
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Vehicle Lease | 5010503
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Permits/Fees | 5501090
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Land Acquisition Services | 5501093
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Other Land Fees | 5501094
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Capitalized A&G | 6010050
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Paid Time Off | 6010100
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Fleet OH | 6010123
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Fleet OH - Elec | 6010125
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Building Service Overhead | 6010112
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | IT Device OH | 6010113
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Benefits OH | 6010120
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Payroll Taxes OH | 6010121
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | Minor Material OH | 6010122
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | 08W | PEND | AFUDC-Equity | 5590031
E.5015531.05 | Result
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Activity Type Cost Adjustment | 5590045
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Cust. Care Activity Charge - Type A | 5590104
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Internal Services - Budget | 5600000
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Administration | 6603000
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Acquisition - Misc | 6603004
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Construction Overtime Services | 6603021
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Engineering/Mapping | 6603022
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Land Rights - Misc | 6603227
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Electric Estimating Overtime | 6603467
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Account Services | 6603730
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Manage L&EM | 6603823
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Service Planning - Planning Only | 5501163
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Estimating-Internal | 6010076
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Mapping | 6010077
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Activity Types - Contractors | PGE1ACTV-CONTR
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Contractor Consultant | 6608158
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Electrical Specialties | 5300140
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Material Burden Adjustment | 5590076
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Material Burden | 6010000
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Contracts | 5490000
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Environmental Contract | 5490015
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Cash Discount earned | 5006310
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Land Acquisition Services | 5501093
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Capitalized A&G | 6010050
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Paid Time Off | 6010100
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Fleet OH | 6010123
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Building Service Overhead | 6010112
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | IT Device OH | 6010113
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Benefits OH | 6010120
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | Minor Material OH | 6010122
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | 08W | CONS | AFUDC-Equity | 5590031
E.5015567.06 | Result
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Internal Services - Budget | 5600000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Administration | 6603000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Construction | 6603001
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Construction Overtime Services | 6603021
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Engineering/Mapping | 6603022
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Engineering Services | 6603023
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Environmental Services | 6603024
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Management Services | 6603076
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Field Services | 6603099
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Land Rights - Misc | 6603227
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Electric Estimating | 6603466
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Account Services | 6603730
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Manage L&EM | 6603823
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Estimating-Internal | 6010076
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Mapping | 6010077
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Construction Supplies | 5300110
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Electrical Specialties | 5300140
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Fabricated Structures | 5300270
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Material Burden | 6010000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Contracts | 5490000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Electric Construction Contract | 5490001
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Environmental Contract | 5490015
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Cash Discount earned | 5006310
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Rents | 5007000
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Permits/Fees | 5501090
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Permits/Fees - Environmental | 5501091
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Land Acquisition Services | 5501093
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Other Land Fees | 5501094
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Postage | 5510010
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Employee Related | PGE1EMPLREL
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Travel / Lodging | PGE1TRVL-LODGE
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Reimbursed Mileage Expense | 5091140
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Meals | PGE1MEALS-EXP
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Meals Expense | 5091100
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Capitalized A&G | 6010050
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Paid Time Off | 6010100
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Fleet OH | 6010123
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Building Service Overhead | 6010112
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | IT Device OH | 6010113
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Benefits OH | 6010120
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Minor Material OH | 6010122
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | AFUDC-Equity | 5590031
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Billing Credits and Reimbursements | PGE1REIMBURSE
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Billing Credits | PGE1BILLCR
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | 08W | CONS | Billing Credit - CIAC Non Taxable | 5590051
E.5015568.01 | Result
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Internal Services - Budget | 5600000
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Administration | 6603000
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Construction | 6603001
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Acquisition - Misc | 6603004
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Construction Overtime Services | 6603021
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Engineering/Mapping | 6603022
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Engineering Services | 6603023
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Management Services | 6603076
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Maintain & Operate Overtime Services | 6603082
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Administrative Services - OT | 6603150
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Land Rights - Misc | 6603227
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Electric Estimating | 6603466
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Electric Estimating Overtime | 6603467
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Account Services | 6603730
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Manage L&EM | 6603823
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Analyst Svcs Overtime | 6603855
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Hours - Straight Time | 6608193
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Estimating-Internal | 6010076
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Mapping | 6010077
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Construction Supplies | 5300110
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Electrical Specialties | 5300140
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Gas & Water Specialties | 5300160
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Communication & Signaling Equipment | 5300230
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Transformers, Regulators & Capacitors | 5300260
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Fabricated Structures | 5300270
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Material Burden | 6010000
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Contracts | 5490000
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Electric Construction Contract | 5490001
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Environmental Contract | 5490015
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Cash Discount earned | 5006310
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Permits/Fees | 5501090
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Permits/Fees - Environmental | 5501091
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Land Acquisition Services | 5501093
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Other Land Fees | 5501094
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Postage | 5510010
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Employee Related | PGE1EMPLREL
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Travel / Lodging | PGE1TRVL-LODGE
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Reimbursed Mileage Expense | 5091140
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Meals | PGE1MEALS-EXP
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Meals Expense | 5091100
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Capitalized A&G | 6010050
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Paid Time Off | 6010100
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Indirect Labor - IT | 6010111
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Operation Mgmt & Support - Cust Care | 6010118
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Operation Mgmt & Support - IT | 6010119
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Fleet OH | 6010123
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Building Service Overhead | 6010112
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | IT Device OH | 6010113
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Benefits OH | 6010120
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | Minor Material OH | 6010122
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | 08W | CONS | AFUDC-Equity | 5590031
E.5015568.02 | Result
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Internal Services - Budget | 5600000
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Administration | 6603000
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Construction | 6603001
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Analyst Services | 6603005
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Construction Overtime Services | 6603021
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Engineering/Mapping | 6603022
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Engineering Services | 6603023
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Environmental Services | 6603024
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Management Services | 6603076
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Field Services | 6603099
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Land Rights - Misc | 6603227
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Account Services | 6603730
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Estimating-Internal | 6010076
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Mapping | 6010077
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Construction Supplies | 5300110
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Electrical Specialties | 5300140
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Fabricated Structures | 5300270
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Material Burden | 6010000
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Contracts | 5490000
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Electric Construction Contract | 5490001
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Environmental Contract | 5490015
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Construction Inspection | 5490021
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Paving Contracts | 5490500
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Cash Discount earned | 5006310
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Permits/Fees | 5501090
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Land Acquisition Services | 5501093
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Other Land Fees | 5501094
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Capitalized A&G | 6010050
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Paid Time Off | 6010100
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Fleet OH | 6010123
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Building Service Overhead | 6010112
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | IT Device OH | 6010113
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Benefits OH | 6010120
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | Minor Material OH | 6010122
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | 08W | CONS | AFUDC-Equity | 5590031
E.5015568.03 | Result
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Internal Services - Budget | 5600000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Administration | 6603000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Construction | 6603001
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Acquisition - Misc | 6603004
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Analyst Services | 6603005
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Construction Overtime Services | 6603021
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Engineering/Mapping | 6603022
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Environmental Services | 6603024
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Management Services | 6603076
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Field Services | 6603099
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Land Rights - Misc | 6603227
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Electric Estimating | 6603466
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Electric Estimating Overtime | 6603467
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Account Services | 6603730
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Manage L&EM | 6603823
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Estimating-Internal | 6010076
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Mapping | 6010077
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Construction Supplies | 5300110
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Electrical Specialties | 5300140
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Fabricated Structures | 5300270
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Material Burden | 6010000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Contracts | 5490000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Gas Construction Contract | 5490002
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Environmental Contract | 5490015
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Paving Contracts | 5490500
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Cash Discount earned | 5006310
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Rents | 5007000
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Permits/Fees | 5501090
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Land Acquisition Services | 5501093
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Other Land Fees | 5501094
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Postage | 5510010
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Capitalized A&G | 6010050
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Paid Time Off | 6010100
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Fleet OH | 6010123
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Building Service Overhead | 6010112
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | IT Device OH | 6010113
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Benefits OH | 6010120
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | Minor Material OH | 6010122
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | 08W | CONS | AFUDC-Equity | 5590031
E.5015568.04 | Result
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Cust. Care Activity Charge - Type A | 5590104
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Internal Services - Budget | 5600000
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Administration | 6603000
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Construction | 6603001
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Acquisition - Misc | 6603004
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Analyst Services | 6603005
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Construction Overtime Services | 6603021
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Engineering/Mapping | 6603022
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Engineering Services | 6603023
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Environmental Services | 6603024
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Switching Operator Service | 6603068
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Management Services | 6603076
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Field Services | 6603099
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Land Rights - Misc | 6603227
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Account Services | 6603730
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Manage L&EM | 6603823
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Estimating-Internal | 6010076
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Mapping | 6010077
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Construction Supplies | 5300110
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Electrical Specialties | 5300140
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Gas & Water Specialties | 5300160
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Fabricated Structures | 5300270
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Material Burden | 6010000
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Contracts | 5490000
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Electric Construction Contract | 5490001
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Gas Construction Contract | 5490002
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Environmental Contract | 5490015
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Paving Contracts | 5490500
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Cash Discount earned | 5006310
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Permits/Fees | 5501090
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Land Acquisition Services | 5501093
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Other Land Fees | 5501094
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Postage | 5510010
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Capitalized A&G | 6010050
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Paid Time Off | 6010100
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Fleet OH | 6010123
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Building Service Overhead | 6010112
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | IT Device OH | 6010113
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Benefits OH | 6010120
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | Minor Material OH | 6010122
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | 08W | CONS | AFUDC-Equity | 5590031
E.5015568.05 | Result
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Cust. Care Activity Charge - Type A | 5590104
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Electric Activity Charge - Non-Type A | 5590107
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Internal Services - Budget | 5600000
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Administration | 6603000
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Construction | 6603001
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Acquisition - Misc | 6603004
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Analyst Services | 6603005
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Construction Overtime Services | 6603021
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Engineering/Mapping | 6603022
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Engineering Services | 6603023
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Environmental Services | 6603024
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Switching Operator Service | 6603068
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Management Services | 6603076
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Field Services | 6603099
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Account Services | 6603730
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Estimating-Internal | 6010076
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Mapping | 6010077
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Construction Supplies | 5300110
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Electrical Specialties | 5300140
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Gas & Water Specialties | 5300160
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Fabricated Structures | 5300270
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Material Burden | 6010000
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Consulting Services - Environmental Perm | 5001237
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Contracts | 5490000
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Electric Construction Contract | 5490001
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Environmental Contract | 5490015
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Cash Discount earned | 5006310
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Permits/Fees | 5501090
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Permits/Fees - Environmental | 5501091
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Land Acquisition Services | 5501093
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Other Land Fees | 5501094
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Postage | 5510010
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Employee Related | PGE1EMPLREL
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Travel / Lodging | PGE1TRVL-LODGE
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Reimbursed Mileage Expense | 5091140
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Meals | PGE1MEALS-EXP
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Meals Expense | 5091100
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Capitalized A&G | 6010050
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Paid Time Off | 6010100
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Fleet OH | 6010123
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Building Service Overhead | 6010112
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | IT Device OH | 6010113
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Benefits OH | 6010120
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | Minor Material OH | 6010122
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | 08W | CONS | AFUDC-Equity | 5590031
E.5015569.01 | Result
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Order Financial Costs | PGE1ORDFIN
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Activity Type Total | PGE1ACTV-TOT
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Activity Types | PGE1ACTVTYPES
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Activity Types - Internal | PGE1ACTV-INT
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Internal Services - Budget | 5600000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Administration | 6603000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Construction | 6603001
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Acquisition - Misc | 6603004
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Construction Overtime Services | 6603021
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Engineering/Mapping | 6603022
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Engineering Services | 6603023
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Environmental Planning & Permitting-Misc | 6603027
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Management Services | 6603076
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Maintain & Operate Overtime Services | 6603082
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Maintain & Operate Services | 6603083
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Engineering/Mapping Services Overtime | 6603106
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Administrative Services - OT | 6603150
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Construction Doubletime Services | 6603180
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Maint & Operate Doubletime Services | 6603181
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Land Rights - Misc | 6603227
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | SCADA Services | 6603671
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Account Services | 6603730
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Manage L&EM | 6603823
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Hours - Straight Time | 6608193
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Estimating-Internal | 6010076
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Mapping | 6010077
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Material Total | PGE1MATTOTAL
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Material related expenses | PGE1MATERIAL
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Materials Not Otherwise Classified | 5300000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Construction Supplies | 5300110
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Conductors, Cable & Wire Connectors | 5300120
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Electrical Specialties | 5300140
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Poles, Insulators & Hardware Bushing & B | 5300180
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Electl & Electronic Equipment Component | 5300200
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Transformers, Regulators & Capacitors | 5300260
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Fabricated Structures | 5300270
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Tools, First Aid & Safety Supplies | 5300280
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Purchasing Card | 5300330
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Material Burden | PGE1MATBURD
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Material Burden | 6010000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Contract Total | PGE1CONTRACT
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Consulting | PGE1CONSULTING
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Consulting Services - Engineering | 5001230
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Consulting Services - Computer | 5001240
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Other Contract | PGE1OTHCONTRAC
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Contracts | 5490000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Electric Construction Contract | 5490001
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Environmental Contract | 5490015
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Construction Inspection | 5490021
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Traffic Control Contracts | 5490027
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Order Other Costs | PGE1ORD-OTHER
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Other Cost Elements | PGE1OTHERCE
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Cash Discount earned | 5006310
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Rents | 5007000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Vehicle Lease | 5010503
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Permits/Fees | 5501090
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Land Acquisition Services | 5501093
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Other Land Fees | 5501094
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Postage | 5510010
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Other Expenses | 5591000
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Employee Related | PGE1EMPLREL
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Travel / Lodging | PGE1TRVL-LODGE
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Reimbursed Mileage Expense | 5091140
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Order Overheads | PGE1OVERHEAD
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Capitalized A&G | PGE1CAPAG
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Capitalized A&G | 6010050
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Labor Overheads | PGE1LABOROH
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Paid Time Off | 6010100
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Indirect Labor - Electric | 6010106
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Indirect Labor - Gas | 6010107
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Indirect Labor - Environmental Land | 6010108
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Indirect Labor - Cust Care | 6010110
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Indirect Labor - IT | 6010111
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Operation Mgmt & Support - Electric | 6010114
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Operation Mgmt & Support - Gas | 6010115
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Operation Mgmt & Support - Environ Land | 6010116
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Operation Mgmt & Support - IT | 6010119
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Fleet OH | 6010123
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Fleet OH - Elec | 6010125
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Fleet OH - Gas | 6010126
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Building Service Overhead | 6010112
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | IT Device OH | 6010113
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Other Overhead | PGE1OTHEROH
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Benefits OH | 6010120
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Payroll Taxes OH | 6010121
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | Minor Material OH | 6010122
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | AFUDC Costs | PGE1AFUDCDIR
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | AFUDC-Borrowed | 5590030
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | 08W | CONS | AFUDC-Equity | 5590031
E.5025634.01 | Result
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Activity Type Cost Adjustment | 5590045
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Internal Services - Budget | 5600000
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Administration | 6603000
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Construction | 6603001
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Acquisition - Misc | 6603004
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Analyst Services | 6603005
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Engineering/Mapping | 6603022
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Technical Services | 6603058
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Management Services | 6603076
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Administrative Services - OT | 6603150
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Administrative Services - Double Time | 6603253
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Gas Estimating | 6603469
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Analyst Svcs Overtime | 6603855
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Hours - Straight Time | 6608193
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Hours - Overtime | 6608194
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Service Planning - Planning Only | 5501163
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Estimating-Internal | 6010076
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Mapping | 6010077
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Material Total | PGE1MATTOTAL
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Electrical Specialties | 5300140
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Material Burden | PGE1MATBURD
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Material Burden Adjustment | 5590076
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Material Burden | 6010000
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Contract Total | PGE1CONTRACT
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Consulting | PGE1CONSULTING
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Consulting Services - Engineering | 5001230
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Consulting Services - Environmental Perm | 5001237
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Contracts | 5490000
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Electric Construction Contract | 5490001
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Gas Construction Contract | 5490002
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Environmental Contract | 5490015
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Construction Inspection | 5490021
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Traffic Control Contracts | 5490027
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Paving Contracts | 5490500
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Cash Discount earned | 5006310
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Vehicle Lease | 5010503
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Permits/Fees | 5501090
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Permits/FeesLand Surveying Services | 5501092
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Land Acquisition Services | 5501093
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Encroachment Permit Fees | 5501095
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Other Expenses | 5591000
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Employee Related | PGE1EMPLREL
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Travel / Lodging | PGE1TRVL-LODGE
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Reimbursed Mileage Expense | 5091140
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Meals | PGE1MEALS-EXP
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Meals Expense | 5091100
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Capitalized A&G | 6010050
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Paid Time Off | 6010100
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Indirect Labor - Electric | 6010106
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Indirect Labor - Gas | 6010107
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Indirect Labor - IT | 6010111
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Operation Mgmt & Support - Gas | 6010115
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Operation Mgmt & Support - IT | 6010119
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Fleet OH | 6010123
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Fleet OH - Elec | 6010125
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Fleet OH - Gas | 6010126
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Building Service Overhead | 6010112
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | IT Device OH | 6010113
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Benefits OH | 6010120
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Payroll Taxes OH | 6010121
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | Minor Material OH | 6010122
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | AFUDC-Borrowed | 5590030
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | 08W | PEND | AFUDC-Equity | 5590031
E.5025635.01 | Result
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Administration | 6603000
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Construction | 6603001
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Acquisition - Misc | 6603004
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Analyst Services | 6603005
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Engineering/Mapping | 6603022
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Environmental Services | 6603024
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Management Services | 6603076
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Electric Estimating | 6603466
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Electric Estimating Overtime | 6603467
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Manage L&EM | 6603823
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Analyst Svcs Overtime | 6603855
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Estimating-Internal | 6010076
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Mapping | 6010077
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Activity Types - Contractors | PGE1ACTV-CONTR
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Other Contractor Activity Types | PGE1ACTV-OTH-C
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Contractor Consultant | 6608158
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Material Total | PGE1MATTOTAL
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Gas & Water Specialties | 5300160
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Material Burden | PGE1MATBURD
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Material Burden | 6010000
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Contract Total | PGE1CONTRACT
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Contracts | 5490000
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Environmental Contract | 5490015
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Construction Inspection | 5490021
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Construction Management Contracts | 5490024
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Traffic Control Contracts | 5490027
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | T&D Sewer Inspection | 5490028
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Vehicle Lease | 5010503
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Land Acquisition Services | 5501093
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Employee Related | PGE1EMPLREL
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Travel / Lodging | PGE1TRVL-LODGE
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Reimbursed Mileage Expense | 5091140
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Capitalized A&G | 6010050
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Paid Time Off | 6010100
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Indirect Labor - Electric | 6010106
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Operation Mgmt & Support - Gas | 6010115
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Fleet OH | 6010123
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Fleet OH - Elec | 6010125
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Building Service Overhead | 6010112
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | IT Device OH | 6010113
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Benefits OH | 6010120
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Payroll Taxes OH | 6010121
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | Minor Material OH | 6010122
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | AFUDC-Borrowed | 5590030
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | 08W | PEND | AFUDC-Equity | 5590031
E.5030964.01 | Result
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Order Financial Costs | PGE1ORDFIN
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Activity Type Total | PGE1ACTV-TOT
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Activity Types | PGE1ACTVTYPES
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Activity Types - Internal | PGE1ACTV-INT
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Construction | 6603001
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Land Rights - Misc | 6603227
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Electric Estimating | 6603466
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Mapping | 6010077
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Material Total | PGE1MATTOTAL
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Material related expenses | PGE1MATERIAL
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Conductors, Cable & Wire Connectors | 5300120
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Material Burden | PGE1MATBURD
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Material Burden | 6010000
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Contract Total | PGE1CONTRACT
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Other Contract | PGE1OTHCONTRAC
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Contracts | 5490000
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Environmental Contract | 5490015
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Order Other Costs | PGE1ORD-OTHER
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Other Cost Elements | PGE1OTHERCE
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Land Acquisition Services | 5501093
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Order Overheads | PGE1OVERHEAD
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Capitalized A&G | PGE1CAPAG
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Capitalized A&G | 6010050
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Labor Overheads | PGE1LABOROH
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Paid Time Off | 6010100
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Indirect Labor - Electric | 6010106
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Indirect Labor - Environmental Land | 6010108
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Operation Mgmt & Support - Electric | 6010114
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Operation Mgmt & Support - Environ Land | 6010116
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Fleet OH | 6010123
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Fleet OH - Elec | 6010125
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Building Service Overhead | 6010112
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | IT Device OH | 6010113
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Other Overhead | PGE1OTHEROH
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Benefits OH | 6010120
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Payroll Taxes OH | 6010121
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | Minor Material OH | 6010122
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | AFUDC Costs | PGE1AFUDCDIR
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | AFUDC-Borrowed | 5590030
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | 08W | UNSE | AFUDC-Equity | 5590031
E.5033920.01 | Result
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Order Financial Costs | PGE1ORDFIN
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Activity Type Total | PGE1ACTV-TOT
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Activity Types | PGE1ACTVTYPES
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Activity Types - Internal | PGE1ACTV-INT
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Construction | 6603001
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Environmental Planning & Permitting-Misc | 6603027
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Land Rights - Misc | 6603227
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Electric Estimating | 6603466
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Mapping | 6010077
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Material Total | PGE1MATTOTAL
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Material related expenses | PGE1MATERIAL
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Conductors, Cable & Wire Connectors | 5300120
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Contract Total | PGE1CONTRACT
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Other Contract | PGE1OTHCONTRAC
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Contracts | 5490000
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Environmental Contract | 5490015
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Order Other Costs | PGE1ORD-OTHER
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Other Cost Elements | PGE1OTHERCE
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Land Acquisition Services | 5501093
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Order Overheads | PGE1OVERHEAD
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Capitalized A&G | PGE1CAPAG
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Capitalized A&G | 6010050
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Labor Overheads | PGE1LABOROH
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Paid Time Off | 6010100
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Indirect Labor - Electric | 6010106
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Indirect Labor - Environmental Land | 6010108
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Operation Mgmt & Support - Electric | 6010114
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Operation Mgmt & Support - Environ Land | 6010116
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Fleet OH | 6010123
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Building Service Overhead | 6010112
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | IT Device OH | 6010113
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Other Overhead | PGE1OTHEROH
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Benefits OH | 6010120
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | Payroll Taxes OH | 6010121
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | AFUDC Costs | PGE1AFUDCDIR
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | AFUDC-Borrowed | 5590030
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | 08W | UNSE | AFUDC-Equity | 5590031
E.5033921.01 | Result
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Order Financial Costs | PGE1ORDFIN
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Activity Type Total | PGE1ACTV-TOT
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Activity Types | PGE1ACTVTYPES
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Activity Types - Internal | PGE1ACTV-INT
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Construction | 6603001
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Engineering/Mapping | 6603022
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Environmental Planning & Permitting-Misc | 6603027
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Design Overtime Services | 6603103
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Electric Estimating | 6603466
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Mapping | 6010077
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Material Total | PGE1MATTOTAL
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Material related expenses | PGE1MATERIAL
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Conductors, Cable & Wire Connectors | 5300120
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Material Burden | PGE1MATBURD
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Material Burden | 6010000
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Contract Total | PGE1CONTRACT
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Other Contract | PGE1OTHCONTRAC
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Contracts | 5490000
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Environmental Contract | 5490015
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Order Other Costs | PGE1ORD-OTHER
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Other Cost Elements | PGE1OTHERCE
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Land Acquisition Services | 5501093
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Order Overheads | PGE1OVERHEAD
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Capitalized A&G | PGE1CAPAG
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Capitalized A&G | 6010050
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Labor Overheads | PGE1LABOROH
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Paid Time Off | 6010100
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Indirect Labor - Electric | 6010106
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Indirect Labor - Environmental Land | 6010108
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Operation Mgmt & Support - Electric | 6010114
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Operation Mgmt & Support - Environ Land | 6010116
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Fleet OH | 6010123
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Fleet OH - Elec | 6010125
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Building Service Overhead | 6010112
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | IT Device OH | 6010113
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Other Overhead | PGE1OTHEROH
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Benefits OH | 6010120
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Payroll Taxes OH | 6010121
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | Minor Material OH | 6010122
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | AFUDC Costs | PGE1AFUDCDIR
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | AFUDC-Borrowed | 5590030
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | 08W | UNSE | AFUDC-Equity | 5590031
E.5034607.01 | Result
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Administration | 6603000
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Construction | 6603001
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Project Management Services | 6603013
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Construction Overtime Services | 6603021
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Engineering/Mapping | 6603022
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Environmental Services | 6603024
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Land Rights - Misc | 6603227
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Substation Design Standard Time | 6603327
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Electric Estimating | 6603466
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Manage L&EM | 6603823
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Mapping | 6010077
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Consulting | PGE1CONSULTING
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Consulting Services - Engineering | 5001230
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Contracts | 5490000
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Environmental Contract | 5490015
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Land Acquisition Services | 5501093
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Capitalized A&G | 6010050
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Paid Time Off | 6010100
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Fleet OH | 6010123
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Building Service Overhead | 6010112
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | IT Device OH | 6010113
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Benefits OH | 6010120
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Construction | 6603001
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Electric Estimating | 6603466
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Account Services | 6603730
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Mapping | 6010077
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Material Burden | 6010000
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Consulting | PGE1CONSULTING
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Consulting Services - Environmental Perm | 5001237
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Contracts | 5490000
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Permits/FeesLand Surveying Services | 5501092
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Capitalized A&G | 6010050
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Paid Time Off | 6010100
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Building Service Overhead | 6010112
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | IT Device OH | 6010113
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Benefits OH | 6010120
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | Minor Material OH | 6010122
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034607.01 | 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Construction | 6603001
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Construction Overtime Services | 6603021
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Electric Estimating | 6603466
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Account Services | 6603730
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Mapping | 6010077
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Material Burden | 6010000
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Contracts | 5490000
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Environmental Contract | 5490015
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Permits/FeesLand Surveying Services | 5501092
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Capitalized A&G | 6010050
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Paid Time Off | 6010100
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Building Service Overhead | 6010112
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | IT Device OH | 6010113
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Benefits OH | 6010120
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | Minor Material OH | 6010122
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034607.01 | 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034611.01 | Result
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Construction | 6603001
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Acquisition - Misc | 6603004
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Engineering/Mapping | 6603022
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Engineering/Mapping Services Overtime | 6603106
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Administrative Services - OT | 6603150
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Land Rights - Misc | 6603227
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Electric Estimating | 6603466
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Mapping | 6010077
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Material Burden | 6010000
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Consulting | PGE1CONSULTING
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Consulting Services - Engineering | 5001230
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Contracts | 5490000
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Environmental Contract | 5490015
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Land Acquisition Services | 5501093
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Capitalized A&G | 6010050
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Paid Time Off | 6010100
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Fleet OH | 6010123
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Building Service Overhead | 6010112
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | IT Device OH | 6010113
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Benefits OH | 6010120
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | Minor Material OH | 6010122
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Construction | 6603001
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Engineering/Mapping | 6603022
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Maintain & Operate Services | 6603083
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Field Services | 6603099
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Electric Estimating | 6603466
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Electric Estimating Overtime | 6603467
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Account Services | 6603730
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Mapping | 6010077
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Electrical Specialties | 5300140
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Material Burden | PGE1MATBURD
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Material Burden | 6010000
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Contracts | 5490000
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Electric Construction Contract | 5490001
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Construction Inspection | 5490021
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Permits/Fees | 5501090
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Capitalized A&G | 6010050
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Paid Time Off | 6010100
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Fleet OH - Elec | 6010125
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Building Service Overhead | 6010112
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | IT Device OH | 6010113
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Benefits OH | 6010120
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Payroll Taxes OH | 6010121
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | Minor Material OH | 6010122
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5034611.01 | 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 08W | PEND | AFUDC-Equity | 5590031
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Construction | 6603001
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Acquisition - Misc | 6603004
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Administrative Services - OT | 6603150
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Electric Estimating | 6603466
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Mapping | 6010077
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Material Burden | 6010000
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Contracts | 5490000
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Capitalized A&G | 6010050
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Paid Time Off | 6010100
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Building Service Overhead | 6010112
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | IT Device OH | 6010113
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Benefits OH | 6010120
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | Minor Material OH | 6010122
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034611.01 | 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Construction | 6603001
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Acquisition - Misc | 6603004
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Administrative Services - OT | 6603150
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Electric Estimating | 6603466
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Account Services | 6603730
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Mapping | 6010077
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Material Burden | 6010000
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Contracts | 5490000
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Capitalized A&G | 6010050
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Paid Time Off | 6010100
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Indirect Labor - Cust Care | 6010110
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Building Service Overhead | 6010112
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | IT Device OH | 6010113
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Benefits OH | 6010120
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | Minor Material OH | 6010122
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034611.01 | 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 08W | ESTS | AFUDC-Equity | 5590031
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Construction | 6603001
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Engineering/Mapping | 6603022
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Maintain & Operate Services | 6603083
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Field Services | 6603099
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Electric Estimating | 6603466
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Account Services | 6603730
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Mapping | 6010077
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Electrical Specialties | 5300140
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Material Burden | PGE1MATBURD
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Material Burden | 6010000
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Consulting | PGE1CONSULTING
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Consulting Services - Engineering | 5001230
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Contracts | 5490000
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Electric Construction Contract | 5490001
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Construction Inspection | 5490021
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Capitalized A&G | 6010050
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Paid Time Off | 6010100
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Fleet OH - Elec | 6010125
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Building Service Overhead | 6010112
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | IT Device OH | 6010113
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Benefits OH | 6010120
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Payroll Taxes OH | 6010121
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | Minor Material OH | 6010122
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5034611.01 | 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 08W | PEND | AFUDC-Equity | 5590031
E.5034757.01 | Result
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Construction | 6603001
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Engineering/Mapping | 6603022
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Engineering/Mapping Services Overtime | 6603106
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Engineering Services - OT | 6603148
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Administrative Services - OT | 6603150
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Land Rights - Misc | 6603227
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Electric Estimating | 6603466
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Mapping | 6010077
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Material Burden | 6010000
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Consulting | PGE1CONSULTING
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Consulting Services - Engineering | 5001230
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Contracts | 5490000
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Environmental Contract | 5490015
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Employee Related | PGE1EMPLREL
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Travel / Lodging | PGE1TRVL-LODGE
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Lodging | 5091114
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Meals | PGE1MEALS-EXP
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Meals Expense | 5091100
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Capitalized A&G | 6010050
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Paid Time Off | 6010100
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Building Service Overhead | 6010112
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | IT Device OH | 6010113
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Benefits OH | 6010120
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | Minor Material OH | 6010122
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 08W | ESTS | AFUDC-Equity | 5590031
E.5034763.01 | Result
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Order Financial Costs | PGE1ORDFIN
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Activity Type Total | PGE1ACTV-TOT
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Activity Types | PGE1ACTVTYPES
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Activity Types - Internal | PGE1ACTV-INT
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Construction | 6603001
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Engineering/Mapping | 6603022
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Environmental Planning & Permitting-Misc | 6603027
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Administrative Services - OT | 6603150
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Land Rights - Misc | 6603227
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Electric Estimating | 6603466
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Mapping | 6010077
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Material Total | PGE1MATTOTAL
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Material related expenses | PGE1MATERIAL
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Conductors, Cable & Wire Connectors | 5300120
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Material Burden | PGE1MATBURD
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Material Burden | 6010000
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Contract Total | PGE1CONTRACT
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Consulting | PGE1CONSULTING
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Consulting Services - Engineering | 5001230
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Other Contract | PGE1OTHCONTRAC
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Contracts | 5490000
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Environmental Contract | 5490015
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Order Other Costs | PGE1ORD-OTHER
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Other Cost Elements | PGE1OTHERCE
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Other Expenses | 5591000
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Employee Related | PGE1EMPLREL
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Travel / Lodging | PGE1TRVL-LODGE
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Lodging | 5091114
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Meals | PGE1MEALS-EXP
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Meals Expense | 5091100
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Order Overheads | PGE1OVERHEAD
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Capitalized A&G | PGE1CAPAG
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Capitalized A&G | 6010050
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Labor Overheads | PGE1LABOROH
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Paid Time Off | 6010100
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Indirect Labor - Electric | 6010106
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Indirect Labor - Environmental Land | 6010108
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Operation Mgmt & Support - Electric | 6010114
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Operation Mgmt & Support - Environ Land | 6010116
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Fleet OH - Elec | 6010125
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Building Service Overhead | 6010112
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | IT Device OH | 6010113
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Other Overhead | PGE1OTHEROH
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Benefits OH | 6010120
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Payroll Taxes OH | 6010121
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | Minor Material OH | 6010122
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | AFUDC Costs | PGE1AFUDCDIR
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | AFUDC-Borrowed | 5590030
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 08W | ESTS | AFUDC-Equity | 5590031
E.5034802.01 | Result
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Administration | 6603000
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Construction | 6603001
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Acquisition - Misc | 6603004
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Analyst Services | 6603005
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Engineering/Mapping | 6603022
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Environmental Planning & Permitting-Misc | 6603027
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Maintain & Operate Services | 6603083
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Vegetation Management - Misc | 6603097
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Field Services | 6603099
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Engineering/Mapping Services Overtime | 6603106
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Administrative Services - OT | 6603150
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Land Rights - Misc | 6603227
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Account Services | 6603730
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Mapping | 6010077
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Electrical Specialties | 5300140
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Material Burden | PGE1MATBURD
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Material Burden | 6010000
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Contract Total | PGE1CONTRACT
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Consulting | PGE1CONSULTING
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Consulting Services - Engineering | 5001230
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Other Contract | PGE1OTHCONTRAC
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Contracts | 5490000
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Environmental Contract | 5490015
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Traffic Control Contracts | 5490027
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Permits/Fees | 5501090
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Other Expenses | 5591000
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Capitalized A&G | 6010050
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Paid Time Off | 6010100
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Fleet OH | 6010123
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Fleet OH - Elec | 6010125
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Building Service Overhead | 6010112
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | IT Device OH | 6010113
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Benefits OH | 6010120
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Payroll Taxes OH | 6010121
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 08W | PEND | Minor Material OH | 6010122
# | Result
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Order Financial Costs | PGE1ORDFIN
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Activity Types | PGE1ACTVTYPES
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Administration | 6603000
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Analyst Services | 6603005
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Engineering/Mapping | 6603022
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Environmental Services | 6603024
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Land Rights - Misc | 6603227
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Material Total | PGE1MATTOTAL
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Material related expenses | PGE1MATERIAL
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Materials Not Otherwise Classified | 5300000
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Construction Supplies | 5300110
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Electrical Specialties | 5300140
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Poles, Insulators & Hardware Bushing & B | 5300180
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Electl & Electronic Equipment Component | 5300200
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Fabricated Structures | 5300270
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Printed Matls, Signs, Off Suppl & Furn | 5300300
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Material Burden | PGE1MATBURD
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Material Burden | 6010000
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Cash Discount earned | 5006310
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Land Acquisition Services | 5501093
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Order Overheads | PGE1OVERHEAD
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Capitalized A&G | PGE1CAPAG
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Capitalized A&G | 6010050
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Labor Overheads | PGE1LABOROH
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Paid Time Off | 6010100
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Indirect Labor - Electric | 6010106
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Fleet OH | 6010123
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Fleet OH - Elec | 6010125
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Building Service Overhead | 6010112
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | IT Device OH | 6010113
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Other Overhead | PGE1OTHEROH
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Benefits OH | 6010120
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Payroll Taxes OH | 6010121
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | 08W | PEND | Minor Material OH | 6010122
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Order Financial Costs | PGE1ORDFIN
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Activity Type Total | PGE1ACTV-TOT
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Activity Types | PGE1ACTVTYPES
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Activity Types - Internal | PGE1ACTV-INT
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Internal Services - Budget | 5600000
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Construction | 6603001
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Analyst Services | 6603005
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Project Management Services | 6603013
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Engineering/Mapping | 6603022
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Engineering Services | 6603023
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Environmental Services | 6603024
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Estimating Services | 6603025
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Environmental Planning & Permitting-Misc | 6603027
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Planning Services | 6603048
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Technical Services | 6603058
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Estimating Overtime Services | 6603105
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Land Rights - Misc | 6603227
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Contract Total | PGE1CONTRACT
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Consulting | PGE1CONSULTING
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Consulting Services - Environmental Perm | 5001237
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Other Contract | PGE1OTHCONTRAC
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Environmental Contract | 5490015
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Order Other Costs | PGE1ORD-OTHER
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Order Overheads | PGE1OVERHEAD
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Labor Overheads | PGE1LABOROH
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Paid Time Off | 6010100
# | 41812476 | LINE 172A MP31.46 EXPOSED PIPE | JTB | DOCC | Indirect Labor - Gas | 6010107

## Labor Detail - Dollars
PRJ002-PS Labor Detail - Dollars
[5 empty] | 1995 to 2020 Actual Amt | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | 2021 YTD Act Amt | 2021 YTD Actuals + Remaining Plan | Jan 2022 Fcst Amt | Feb 2022 Fcst Amt | Mar 2022 Fcst Amt | Apr 2022 Fcst Amt | May 2022 Fcst Amt | Jun 2022 Fcst Amt | Jul 2022 Fcst Amt | Aug 2022 Fcst Amt | Sep 2022 Fcst Amt | Oct 2022 Fcst Amt | Nov 2022 Fcst Amt | Dec 2022 Fcst Amt | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt | 2025 to 2031 Forecast | Total Actual Amount | Total Forecast | Total EAC | Auth Amt (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Act Since Incep/Auth Amt) | 2021 YTD Plan Amt | YTD Variance (Plan - Act) | Variance %
WBS Element Level 2 | Order |  | Partner CC | Partner Activity | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ |  |  |  | $ | $ | $ | $ | $ | % | % | $ | $ | %
Overall Result
E.5015414.01 | 35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSOT
|  |  | 14110 | FLDSVC
|  |  | 14182 | CNSTOT
CONSTR
ENGMAP
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15346 | PRJMOT
|  |  | 15443 | MANAGE
|  |  | 15448 | XCON02
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015414.02 | 35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015414.03 | 35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 12002 | #
|  |  | 12133 | MO-DT
|  |  | 12577 | ACQLIT
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSOT
FLDSVC
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015414.04 | 35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 11938 | CONSTR
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14178 | VEGMGT
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015415.01 | 35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 12002 | #
|  |  | 12148 | SCADSV
|  |  | 12577 | ACQLIT
ADM-OT
|  |  | 13549 | ENGMAP
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSOT
HRSST
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15275 | MO
MO-OT
|  |  | 15443 | MANAGE
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015415.02 | 35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | # | #
|  |  | 11140 | PRJMGT
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14178 | VEGMGT
|  |  | 14182 | ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15322 | PRJMGT
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15931 | HELICS
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015415.03 | 35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015415.04 | 35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | # | #
|  |  | 11140 | PRJMGT
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSDT
FLDSOT
FLDSVC
|  |  | 14178 | VEGMGT
|  |  | 14182 | ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15789 | ACTSVC
|  |  | 15931 | HELICS
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015415.05 | 35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 12002 | #
|  |  | 14110 | FLDSDT
FLDSOT
FLDSVC
|  |  | 14178 | VEGMGT
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
|  |  | 15443 | MANAGE
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015415.06 | 35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11714 | DSGNSV
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 14110 | FLDSVC
|  |  | 14178 | LNDRTS
VEGMGT
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
|  |  | 15240 | ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015416.01 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | # | #
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 12688 | ENGSVC
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSST
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
ENVSVC
|  |  | 15346 | PRJMOT
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYST
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015416.02 | 35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13550 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CNSTOT
CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015416.03 | 35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11714 | EEST
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
|  |  | 15443 | MANAGE
|  |  | 15448 | XCON02
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015416.04 | 35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015416.05 | 35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | # | #
|  |  | 11034 | MANAGE
|  |  | 11140 | PRJMGT
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
MNGNCC
|  |  | 12809 | ACQLIT
ACQRIG
|  |  | 13549 | ENGMAP
|  |  | 14182 | ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CNSTDT
CNSTOT
CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015417.01 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | # | #
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
MNGNCC
|  |  | 12809 | ACQLIT
ACQRIG
ADM-OT
|  |  | 12845 | CONSTR
|  |  | 12974 | EEST
EESTOT
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13550 | ENGMAP
|  |  | 14182 | CNSTOT
CONSTR
ENGMAP
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYOT
ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015417.02 | 35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | # | #
|  |  | 11140 | PRJMGT
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
LNDENG
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSST
|  |  | 14178 | VEGMGT
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14418 | HELICS
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015417.03 | 35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015417.04 | 35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | # | #
|  |  | 11034 | MANAGE
|  |  | 11140 | PRJMGT
|  |  | 11674 | #
|  |  | 11890 | MO
MO-OT
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015417.05 | 35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015420.01 | 35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | # | #
|  |  | 10472 | MO
SWTCHO
SWTODT
SWTOOT
|  |  | 11674 | #
|  |  | 11797 | MO
MO-DT
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12044 | FLDSVC
|  |  | 12689 | MO-DT
|  |  | 13549 | ENGMAP
|  |  | 13550 | ENGMAP
|  |  | 14110 | FLDSDT
FLDSOT
FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14418 | HELICS
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15275 | MO
MO-OT
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015420.02 | 35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | # | #
|  |  | 10472 | MO
SWTCHO
|  |  | 10484 | OPERSV
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 11894 | APRNST
|  |  | 12002 | #
|  |  | 12148 | SCADSV
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13892 | HRSOT
HRSST
|  |  | 14110 | FLDSDT
FLDSOT
FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15275 | MO
MO-DT
MO-OT
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CNSTOT
CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015420.06 | 35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
MO-DT
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12809 | ACQLIT
|  |  | 13549 | ENGMAP
|  |  | 14052 | SWTCHO
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15448 | XCON02
|  |  | 15497 | ACTSVC
|  |  | 15893 | CNSTOT
CONSTR
|  |  | 15993 | XCON02
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015426.01 | 35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 12884 | TECHSV
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSDT
HRSOT
HRSST
|  |  | 14182 | CNSTOT
|  |  | 14459 | MANAGE
|  |  | 14521 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015426.02 | 35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14646 | #
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015426.03 | 35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14646 | #
|  |  | 15514 | CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015531.02 | 35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
LNDRTS
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14182 | CNSTOT
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015531.03 | 35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11714 | EEST
|  |  | 11834 | CNSTDT
CNSTOT
CONSTR
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12688 | ENGSVC
|  |  | 12974 | DSGNDT
DSGNOT
|  |  | 13549 | ENGMAP
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
|  |  | 15448 | XCON02
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15993 | XCON02
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015531.04 | 35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | # | #
|  |  | 10481 | SWTCHO
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11714 | EEST
EESTOT
|  |  | 11834 | CONSTR
|  |  | 11890 | MO
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12809 | ACQLIT
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
|  |  | 15240 | BIOCUL
|  |  | 15448 | XCON02
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015531.05 | 35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | # | #
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12974 | EESTOT
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14182 | CNSTOT
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
|  |  | 15240 | BIOCUL
|  |  | 15448 | XCON02
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5015567.06 | 35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | # | #
|  |  | 11674 | #
|  |  | 11714 | EEST
|  |  | 11890 | MO
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
MNGNCC
|  |  | 12688 | ENGSVC
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14182 | CNSTOT
CONSTR
ENGMAP
|  |  | 14632 | CNSTOT
CONSTR
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
BIOCUL
ENVPLN
ENVSVC
|  |  | 15216 | CNSTDT
CNSTOT
CONSTR
|  |  | 15240 | BIOCUL
|  |  | 15288 | CONSTR
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015568.01 | 35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11830 | CNSTDT
CNSTOT
CONSTR
|  |  | 11834 | CNSTDT
CNSTOT
CONSTR
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
ADM-OT
LNDRTS
|  |  | 12002 | #
|  |  | 12055 | CONSTR
|  |  | 12577 | LNDENG
|  |  | 12688 | ENGSVC
|  |  | 12845 | CONSTR
|  |  | 12974 | EEST
EESTOT
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13892 | HRSST
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14459 | MANAGE
|  |  | 14632 | CNSTDT
CNSTOT
CONSTR
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
BIOCUL
ENVPLN
|  |  | 15216 | CNSTDT
CNSTOT
CONSTR
|  |  | 15275 | MO
MO-OT
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYOT
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015568.02 | 35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | # | #
|  |  | 11674 | #
|  |  | 11830 | CNSTDT
CNSTOT
CONSTR
|  |  | 11834 | CNSTOT
CONSTR
|  |  | 11890 | MO
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12055 | CNSTOT
CONSTR
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14628 | ENGSVC
|  |  | 14632 | CNSTDT
CNSTOT
CONSTR
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015568.03 | 35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12055 | CONSTR
|  |  | 12845 | CONSTR
|  |  | 12974 | EEST
EESTOT
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CNSTOT
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015568.04 | 35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | # | #
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11834 | CONSTR
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12055 | CONSTR
|  |  | 12688 | ENGSVC
|  |  | 12690 | SWTCHO
|  |  | 12809 | ACQLIT
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14632 | CNSTDT
CNSTOT
CONSTR
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15240 | BIOCUL
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15893 | CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015568.05 | 35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | # | #
|  |  | 10472 | SWTCHO
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11834 | CNSTDT
CNSTOT
CONSTR
|  |  | 11890 | MO
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12688 | ENGSVC
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14182 | CNSTOT
CONSTR
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
ENVPLN
ENVSVC
|  |  | 15443 | MANAGE
|  |  | 15449 | ANLYST
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15937 | MANAGE
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5015569.01 | 35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | # | #
|  |  | 10484 | SCADSV
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11832 | CNSTDT
CNSTOT
CONSTR
|  |  | 11838 | CNSTDT
CNSTOT
CONSTR
|  |  | 11890 | MO
MO-DT
MO-OT
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ADM-OT
LNDENG
MNGNCC
|  |  | 12688 | ENGSVC
|  |  | 12689 | MO
MO-DT
|  |  | 12809 | ACQLIT
ADMIN
|  |  | 12845 | CONSTR
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 13892 | HRSST
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14459 | MANAGE
|  |  | 14521 | ENGMAP
|  |  | 14632 | CNSTDT
CNSTOT
CONSTR
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
|  |  | 15216 | CNSTDT
CNSTOT
CONSTR
|  |  | 15240 | BIOCUL
|  |  | 15275 | MO
MO-DT
MO-OT
|  |  | 15443 | MANAGE
|  |  | 15495 | ACTSVC
|  |  | 15497 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15937 | MANAGE
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5025634.01 | 35145540 | PSPS - FROGTOWN 1702 - CB | # | #
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12245 | ADMIN
|  |  | 12577 | ACQLIT
ADM-DT
ADM-OT
LNDENG
|  |  | 12809 | ACQLIT
|  |  | 12845 | CONSTR
|  |  | 12884 | TECHSV
|  |  | 12974 | GEST
|  |  | 13549 | ENGMAP
|  |  | 13550 | ENGMAP
|  |  | 13892 | HRSOT
HRSST
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15098 | ENGMAP
|  |  | 15154 | ADM-OT
ADMIN
ENVPLN
|  |  | 15240 | ENVPLN
|  |  | 15449 | ANLYOT
ANLYST
|  |  | 15960 | CONSTR
|  |  | 15976 | MANAGE
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16011 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16029 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5025635.01 | 35145522 | PSPS - CLARKSVILLE 2104 - CB UG | # | #
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12577 | LNDENG
MNGNCC
|  |  | 12809 | ACQLIT
|  |  | 12845 | CONSTR
|  |  | 12974 | EEST
EESTOT
|  |  | 13549 | ENGMAP
|  |  | 14182 | ENGMAP
|  |  | 14635 | #
|  |  | 14646 | #
|  |  | 15154 | ADMIN
BIOCUL
ENVPLN
ENVSVC
|  |  | 15250 | MANAGE
|  |  | 15449 | ANLYOT
ANLYST
|  |  | 15993 | XCON02
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
|  |  | 16036 | #
E.5030964.01 | 35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14646 | #
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5033920.01 | 35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | # | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16035 | #
E.5033921.01 | 35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 12974 | DSGNOT
|  |  | 13549 | ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5034607.01 | 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | # | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 12634 | ENVSVC
|  |  | 12712 | PRJMGT
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 12974 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14182 | CNSTOT
CONSTR
ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ADMIN
BIOCUL
ENVPLN
|  |  | 15171 | BIOCUL
|  |  | 15240 | ENVPLN
|  |  | 15909 | SUBDGN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16035 | #
| 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14182 | CONSTR
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14182 | CNSTOT
CONSTR
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5034611.01 | 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 12974 | EEST
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14182 | ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ADM-OT
ENVPLN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | # | #
|  |  | 11674 | #
|  |  | 11714 | EEST
EESTOT
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14646 | #
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | # | #
|  |  | 11674 | #
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 14646 | #
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5034757.01 | 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14182 | ENG-OT
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5034763.01 | 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 12847 | EEST
|  |  | 13549 | ENGMAP
|  |  | 14182 | ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ENVPLN
|  |  | 15240 | ENVPLN
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
E.5034802.01 | 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | # | #
|  |  | 11674 | #
|  |  | 11890 | MO
|  |  | 11929 | ADM-OT
LNDRTS
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 12809 | ACQLIT
|  |  | 13549 | ENGMAP
ENGMPO
|  |  | 14110 | FLDSVC
|  |  | 14178 | VEGMGT
|  |  | 14182 | CONSTR
ENGMAP
|  |  | 14646 | #
|  |  | 15154 | ADMIN
|  |  | 15240 | ENVPLN
|  |  | 15449 | ANLYST
|  |  | 15789 | ACTSVC
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
# | 35174085 | PSPS - FROGTOWN 1702 - LR 36870 | # | #
|  |  | 11674 | #
|  |  | 11929 | LNDRTS
|  |  | 12002 | #
|  |  | 13549 | ENGMAP
|  |  | 14182 | ENGMAP
|  |  | 15154 | ADMIN
ENVSVC
|  |  | 15449 | ANLYST
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
| 41812476 | LINE 172A MP31.46 EXPOSED PIPE | # | #
|  |  | 10267 | ESTMOT
ESTSVC
|  |  | 10268 | ENGSVC
|  |  | 10281 | ENGMAP
|  |  | 10283 | TECHSV
|  |  | 11831 | CONSTR
|  |  | 14407 | ENVPLN
|  |  | 14822 | PRJMGT
|  |  | 15046 | LNDRTS
|  |  | 15069 | ANLYST
|  |  | 15108 | PLANSV
|  |  | 15165 | ENVSVC
|  |  | 15167 | ENVPLN
|  |  | 16000 | #
|  |  | 16007 | #

## Summary - Act vs. Fcst
PRJ002-PS Forecast Report - Summary FAC
Order |  | User Status | Job Owner | MaintActivityType | WBS Element Level 2 | Planning Order | Total Actual $ | 2021 Remaining Plan $(PRJ) | FYR Fcst $(PRJ) 2022 | Total Fcst $ | Total EAC $ | Auth Amt (AJE) | Contingency | Auth Amt w/ Contin (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Total Act $ /Auth Amt) | Auth Hrs (AJE) | Total Actual Hrs | Total Fcst Hrs | Total EAC Hrs | Variance Hrs (Auth Hrs - EAC Hrs) | Variance %
Overall Result | [17 empty] | 28358 | 30700 | 10617.12 | 41317.12 | -12959.12 | -45.7% | #REF!
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | ESTS |  | 08W | E.5015426.01 | 5782580 | [12 empty] | 106.5 | 78.2 | 184.7 | -184.7 | X | #REF!
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | PEND |  | 08W | E.5015417.01 | 5782532 | [12 empty] | 493.5 | 40.01 | 533.51 | -533.51 | X | #REF!
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | PEND |  | 08W | E.5015416.01 | 5782533 | [12 empty] | 138 | 77.9 | 215.9 | -215.9 | X | #REF!
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | DOCC |  | 08W | E.5015415.01 | 5782534 | [11 empty] | 437 | 162.25 |  | 162.25 | 274.75 | 62.87% | #REF!
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | PEND |  | 08W | E.5015414.01 | 5782535 | [12 empty] | 589 | 980.01 | 1569.01 | -1569.01 | X | #REF!
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | FICL |  | 08W | E.5015420.01 | 5782588 | [11 empty] | 97 | 216 |  | 216 | -119 | -122.7% | #REF!
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | CONS |  | 08W | E.5015569.01 | 5783070 | [12 empty] | 5182.75 | 400 | 5582.75 | -5582.75 | X | #REF!
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | CONS |  | 08W | E.5015568.01 | 5783071 | [11 empty] | 5142 | 2883 | 780 | 3663 | 1479 | 28.76% | #REF!
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | DOCC |  | 08W | E.5015417.02 | 5785512 | [11 empty] | 100 | 137.75 |  | 137.75 | -37.75 | -37.75% | #REF!
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | ESTS |  | 08W | E.5015417.03 | 5785513 | [12 empty] | 154.25 | 77.31 | 231.56 | -231.56 | X | #REF!
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | DOCC |  | 08W | E.5015417.04 | 5785514 | [11 empty] | 268 | 93 |  | 93 | 175 | 65.3% | #REF!
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | DOCC |  | 08W | E.5015417.05 | 5785515 | [11 empty] | 242 | 84.75 |  | 84.75 | 157.25 | 64.98% | #REF!
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | DOCC |  | 08W | E.5015416.02 | 5785516 | [11 empty] | 155 | 108.5 |  | 108.5 | 46.5 | 30% | #REF!
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | ESTS |  | 08W | E.5015416.03 | 5785517 | [12 empty] | 90.25 | 77.85 | 168.1 | -168.1 | X | #REF!
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | DOCC |  | 08W | E.5015416.04 | 5785598 | [11 empty] | 133 | 63.25 |  | 63.25 | 69.75 | 52.44% | #REF!
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | DOCC |  | 08W | E.5015416.05 | 5785599 | [12 empty] | 191.75 |  | 191.75 | -191.75 | X | #REF!
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | DOCC |  | 08W | E.5015415.02 | 5785600 | [11 empty] | 345 | 117.75 |  | 117.75 | 227.25 | 65.87% | #REF!
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | DOCC |  | 08W | E.5015415.03 | 5785601 | [11 empty] | 362 | 83.75 |  | 83.75 | 278.25 | 76.86% | #REF!
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | DOCC |  | 08W | E.5015415.04 | 5785602 | [11 empty] | 137 | 138 |  | 138 | -1 | -0.7299% | #REF!
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | DOCC |  | 08W | E.5015415.05 | 5785603 | [11 empty] | 157 | 103.75 |  | 103.75 | 53.25 | 33.92% | #REF!
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | DOCC |  | 08W | E.5015415.06 | 5785604 | [11 empty] | 270 | 68.5 |  | 68.5 | 201.5 | 74.63% | #REF!
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | DOCC |  | 08W | E.5015414.02 | 5785605 | [12 empty] | 65.75 |  | 65.75 | -65.75 | X | #REF!
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | DOCC |  | 08W | E.5015414.03 | 5785606 | [11 empty] | 185 | 123 |  | 123 | 62 | 33.51% | #REF!
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | DOCC |  | 08W | E.5015414.04 | 5785607 | [11 empty] | 99 | 103 |  | 103 | -4 | -4.04% | #REF!
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | DOCC |  | 08W | E.5015420.02 | 5785652 | [11 empty] | 193 | 378.5 |  | 378.5 | -185.5 | -96.11% | #REF!
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | FICL |  | 08W | E.5015420.06 | 5785656 | [11 empty] | 152 | 184 |  | 184 | -32 | -21.05% | #REF!
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | CONS |  | 08W | E.5015568.02 | 5785721 | [11 empty] | 1160 | 3120.75 | 100 | 3220.75 | -2060.75 | -177.7% | #REF!
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | CONS |  | 08W | E.5015568.03 | 5785722 | [11 empty] | 4108 | 142 | 380 | 522 | 3586 | 87.29% | #REF!
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | CONS |  | 08W | E.5015568.04 | 5785723 | [11 empty] | 3612 | 1086.25 | 780 | 1866.25 | 1745.75 | 48.33% | #REF!
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | CONS |  | 08W | E.5015568.05 | 5785724 | [11 empty] | 3409 | 3726.75 | 680 | 4406.75 | -997.75 | -29.27% | #REF!
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | CONS |  | 08W | E.5015567.06 | 5786518 | [11 empty] | 5549 | 4360.5 | 300 | 4660.5 | 888.5 | 16.01% | #REF!
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | ESTS |  | 08W | E.5015531.02 | 5786480 | [12 empty] | 586 | 77.87 | 663.87 | -663.87 | X | #REF!
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | MAPP |  | 08W | E.5015531.03 | 5788622 | [12 empty] | 3580 |  | 3580 | -3580 | X | #REF!
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | PEND |  | 08W | E.5015531.04 | 5788623 | [11 empty] | 1845 | 115 | 39.99 | 154.99 | 1690.01 | 91.6% | #REF!
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | CONS |  | 08W | E.5015531.05 | 5788624 | [12 empty] | 80.5 |  | 80.5 | -80.5 | X | #REF!
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | PEND |  | 08W | E.5025635.01 | 5788783 | [12 empty] | 319 | 39.99 | 358.99 | -358.99 | X | #REF!
35145540 | PSPS - FROGTOWN 1702 - CB | PEND |  | 08W | E.5025634.01 | 5788779 | [12 empty] | 649.75 | 40 | 689.75 | -689.75 | X | #REF!
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | ESTS |  | 08W | E.5015426.02 | 5539442 | [12 empty] | 1 | 80 | 81 | -81 | X | #REF!
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | ESTS |  | 08W | E.5015426.03 | 5790011 | [12 empty] | 3 | 80 | 83 | -83 | X | #REF!
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | UNSE |  | 08W | E.5030964.01 | 5790003 | [12 empty] | 0.5 | 80 | 80.5 | -80.5 | X | #REF!
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | PEND |  | 08W | # | 5530176 | [12 empty] | 8.75 |  | 8.75 | -8.75 | X | #REF!
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | UNSE |  | 08W | E.5033921.01 | 5790002 | [12 empty] | 4 | 80 | 84 | -84 | X | #REF!
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | UNSE |  | 08W | E.5033920.01 | 5790004 | [12 empty] | 2.5 | 80 | 82.5 | -82.5 | X | #REF!
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | ESTS |  | 08W | E.5034607.01 | 5794208 | [12 empty] | 63.75 | 2256.77 | 2320.52 | -2320.52 | X | #REF!
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | ESTS |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 45.5 | 80 | 125.5 | -125.5 | X | #REF!
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | PEND |  | 08W | E.5034802.01 | 5543352 | [12 empty] | 72.5 | 1787 | 1859.5 | -1859.5 | X | #REF!
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | ESTS |  | 08W | E.5034757.01 | 5794981 | [12 empty] | 238 | 80 | 318 | -318 | X | #REF!
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | ESTS |  | 08W | E.5034763.01 | 5794987 | [12 empty] | 185.5 | 76 | 261.5 | -261.5 | X | #REF!
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | ESTS |  | 08W | E.5034607.01 | 5794208 | [12 empty] | 49 | 80.01 | 129.01 | -129.01 | X | #REF!
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | ESTS |  | 08W | E.5034607.01 | 5794208 | [12 empty] | 24.5 | 80.01 | 104.51 | -104.51 | X | #REF!
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | PEND |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 13 | 207.33 | 220.33 | -220.33 | X | #REF!
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | ESTS |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 5 | 79.99 | 84.99 | -84.99 | X
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | ESTS |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 8.5 | 73.88 | 82.38 | -82.38 | X
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | PEND |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 2.5 | 467 | 469.5 | -469.5 | X
41812476 | LINE 172A MP31.46 EXPOSED PIPE | DOCC |  | JTB | # | 5010515 | [11 empty] | 201 | 145.5 |  | 145.5 | 55.5 | 27.61%

## Labor Detail - Hrs
PRJ002 - PS Labor Detail - Hours
Order |  | Partner CC |  | Partner Activity | Auth Hrs (AJE) | Total Actual Hours | Total Forecast | Total EAC | Jan 2021 Actual Hrs | Feb 2021 Actual Hrs | Mar 2021 Actual Hrs | Apr 2021 Actual Hrs | May 2021 Plan Hrs | Jun 2021 Plan Hrs | Jul 2021 Plan Hrs | Aug 2021 Plan Hrs | Sep 2021 Plan Hrs | Oct 2021 Plan Hrs | Nov 2021 Plan Hrs | Dec 2021 Plan Hrs | 2021 YTD Actuals + Remaining Plan | 2022 Fcst Hrs | 2023 Fcst Hrs | 2024 Fcst Hrs | Variance Hrs (Auth Hrs - EAC Hrs)
Overall Result |  |  |  |  | 28358 | 30700 | 10617.12 | 41317.12 | 2280.5 | 2613 | 5004 | 6373.25 | 3850.96 | 845.93 | 1522.94 | 1359.97 | 671.37 | 814.94 | 525.52 | 112.25 | 25974.63 | 913.24 |  |  | -12959.12
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Result |  |  |  | 106.5 | 78.2 | 184.7 |  |  | 11 |  | 3.4 | 3.56 | 3.56 | 3.56 | 3.56 | 3.4 | 3.56 | 3.72 | 39.32 | 49.88 |  |  | -184.7
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | PGE1/# | # | #
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Applied Technology Services | 12884 | TECHSV |  | 38 |  | 38 | [16 empty] | -38
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Capacity Planning | 13550 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Distribution Asset Management Several | 14459 | MANAGE |  | 1 |  | 1 | [16 empty] | -1
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | IT Telecom Maintenance | 13892 | Result |  | 8 |  | 8 | [16 empty] | -8
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | IT Telecom Maintenance | 13892 | HRSDT |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | IT Telecom Maintenance | 13892 | HRSOT |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | IT Telecom Maintenance | 13892 | HRSST |  | 4 |  | 4 | [16 empty] | -4
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Project Management & Controls | 14182 | CNSTOT |  | 11 |  | 11 |  |  | 11 | [9 empty] | 11 |  |  |  | -11
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Reliability Planning | 13549 | Result |  | 44 |  | 44 | [16 empty] | -44
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Reliability Planning | 13549 | ENGMAP |  | 42 |  | 42 | [16 empty] | -42
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | Reliability Planning | 13549 | ENGMPO |  | 2 |  | 2 | [16 empty] | -2
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | SLSR:EST Estimating | 12847 | EEST |  |  | 38.2 | 38.2 |  |  |  |  | 3.4 | 3.56 | 3.56 | 3.56 | 3.56 | 3.4 | 3.56 | 3.72 | 28.32 | 9.88 |  |  | -38.2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Result |  |  |  | 493.5 | 40.01 | 533.51 | 0.5 |  | 9 | 1.25 | [8 empty] | 10.75 | 40.01 |  |  | -533.51
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | PGE1/# | # | #
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Central Design North | 12974 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Central Design North | 12974 | EEST |  | 4.5 |  | 4.5 | [16 empty] | -4.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Central Design North | 12974 | EESTOT |  | 23 |  | 23 | [16 empty] | -23
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Facilities | 15154 | Result |  | 29.75 |  | 29.75 | 0.25 |  |  | 0.75 | [8 empty] | 1 |  |  |  | -29.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Facilities | 15154 | ADM-OT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Facilities | 15154 | ADMIN |  | 23.25 |  | 23.25 | [16 empty] | -23.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Facilities | 15154 | ENVPLN |  | 3.75 |  | 3.75 |  |  |  | 0.75 | [8 empty] | 0.75 |  |  |  | -3.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | 0.25 | [11 empty] | 0.25 |  |  |  | -0.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Enterprise Public Works Coordination | 15449 | Result |  | 2 |  | 2 | [16 empty] | -2
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Acquisition | 12809 | Result |  | 166.25 |  | 166.25 | [16 empty] | -166.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Acquisition | 12809 | ACQLIT |  | 146.5 |  | 146.5 | [16 empty] | -146.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Acquisition | 12809 | ACQRIG |  | 10.75 |  | 10.75 | [16 empty] | -10.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Acquisition | 12809 | ADM-OT |  | 9 |  | 9 | [16 empty] | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Rights | 11929 | Result |  | 22 |  | 22 | [16 empty] | -22
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Rights | 11929 | ACQLIT |  | 19.5 |  | 19.5 | [16 empty] | -19.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Rights | 11929 | LNDRTS |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Surveying | 12577 | Result |  | 148.25 |  | 148.25 | 0.25 | [11 empty] | 0.25 |  |  |  | -148.25
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Surveying | 12577 | ACQLIT |  | 1 |  | 1 | [16 empty] | -1
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Surveying | 12577 | ADM-OT |  | 4 |  | 4 | [16 empty] | -4
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Surveying | 12577 | LNDENG |  | 140.75 |  | 140.75 | 0.25 | [11 empty] | 0.25 |  |  |  | -140.75
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Land Surveying | 12577 | MNGNCC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | LCE- Division Teams | 15789 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Project Management & Controls | 14182 | Result |  | 50.5 |  | 50.5 |  |  | 9 | 0.5 | [8 empty] | 9.5 |  |  |  | -50.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Project Management & Controls | 14182 | CNSTOT |  | 9 |  | 9 | [16 empty] | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Project Management & Controls | 14182 | ENGMAP |  | 32.5 |  | 32.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -32.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Reliability Planning | 13549 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Reliability Planning | 13549 | ENGMAP |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Reliability Planning | 13549 | ENGMPO |  | 7 |  | 7 | [16 empty] | -7
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40.01 | 40.01 | [13 empty] | 40.01 |  |  | -40.01
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Result |  |  |  | 138 | 77.9 | 215.9 |  |  | 9 | 1.25 | 4 | 4.19 | 4.19 | 4.19 | 4.19 | 4 | 4.19 | 4.38 | 43.58 | 44.57 |  |  | -215.9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | PGE1/# | # | #
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Distribution Automation | 15346 | PRJMOT |  | 3 |  | 3 | [16 empty] | -3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | EM Facilities | 15154 | Result |  | 36.75 |  | 36.75 |  |  |  | 0.75 | [8 empty] | 0.75 |  |  |  | -36.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | EM Facilities | 15154 | ADM-OT |  | 3 |  | 3 | [16 empty] | -3
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | EM Facilities | 15154 | ADMIN |  | 26.75 |  | 26.75 | [16 empty] | -26.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | EM Facilities | 15154 | ENVPLN |  | 1.75 |  | 1.75 |  |  |  | 0.75 | [8 empty] | 0.75 |  |  |  | -1.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | EM Facilities | 15154 | ENVSVC |  | 5.25 |  | 5.25 | [16 empty] | -5.25
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 2 |  | 2 | [16 empty] | -2
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | GC Gas Engr NO | 12688 | ENGSVC |  | 5 |  | 5 | [16 empty] | -5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | IT Telecom Maintenance | 13892 | HRSST |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Land Surveying | 12577 | LNDENG |  | 1 |  | 1 | [16 empty] | -1
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | LCE- Division Teams | 15789 | ACTSVC |  | 6.75 |  | 6.75 | [16 empty] | -6.75
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Project Management & Controls | 14182 | Result |  | 37.5 |  | 37.5 |  |  | 9 | 0.5 | [8 empty] | 9.5 |  |  |  | -37.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Project Management & Controls | 14182 | ENGMAP |  | 28.5 |  | 28.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -28.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Reliability Planning | 13549 | Result |  | 26.5 |  | 26.5 | [16 empty] | -26.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Reliability Planning | 13549 | ENGMAP |  | 22.5 |  | 22.5 | [16 empty] | -22.5
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Reliability Planning | 13549 | ENGMPO |  | 4 |  | 4 | [16 empty] | -4
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | SLSR:EST Estimating | 12847 | EEST |  |  | 37.9 | 37.9 |  |  |  |  | 4 | 4.19 | 4.19 | 4.19 | 4.19 | 4 | 4.19 | 4.38 | 33.33 | 4.57 |  |  | -37.9
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Result |  |  | 437 | 162.25 |  | 162.25 | [16 empty] | 274.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | PGE1/# | # | #
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Distribution Line Tech - SCADA | 15275 | Result |  | 16.5 |  | 16.5 | [16 empty] | -16.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Distribution Line Tech - SCADA | 15275 | MO |  | 15 |  | 15 | [16 empty] | -15
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Distribution Operations Engineering | 14521 | ENGMAP | 13 | 3 |  | 3 | [16 empty] | 10
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | EM Facilities | 15154 | Result | 8 | 19.5 |  | 19.5 | [16 empty] | -11.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | EM Facilities | 15154 | ADMIN | 8 | 17.75 |  | 17.75 | [16 empty] | -9.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | EM Facilities | 15154 | ENVSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | EO&E E&T System Automation | 12148 | SCADSV |  | 2 |  | 2 | [16 empty] | -2
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | IT Telecom Maintenance | 13892 | Result |  | 12 |  | 12 | [16 empty] | -12
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | IT Telecom Maintenance | 13892 | HRSOT |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | IT Telecom Maintenance | 13892 | HRSST |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Land Surveying | 12577 | Result | 27 | 8.5 |  | 8.5 | [16 empty] | 18.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Land Surveying | 12577 | ACQLIT | 27 | 7.5 |  | 7.5 | [16 empty] | 19.5
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Land Surveying | 12577 | ADM-OT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | LCE- Division Teams | 15789 | ACTSVC |  | 19.75 |  | 19.75 | [16 empty] | -19.75
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | North Distribution Control Center | 11890 | Result | 234 | 8 |  | 8 | [16 empty] | 226
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | North Distribution Control Center | 11890 | MO | 234 | 6 |  | 6 | [16 empty] | 228
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | North Distribution Control Center | 11890 | MO-OT |  | 1 |  | 1 | [16 empty] | -1
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Project Management & Controls | 14182 | ENGMAP | 88 | 24 |  | 24 | [16 empty] | 64
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | Reliability Planning | 13549 | ENGMAP |  | 21 |  | 21 | [16 empty] | -21
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | SI Restoration | 14110 | FLDSVC | 66 | [19 empty] | 66
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Result |  |  |  | 589 | 980.01 | 1569.01 | 1 |  | 9 | 1.5 |  | 220.83 | 229.17 | 134.17 | 134.17 | 133.75 | 127.92 |  | 991.51 |  |  |  | -1569.01
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | PGE1/# | # | #
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Capacity Planning | 13550 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Distribution Automation | 15346 | PRJMOT |  | 4 |  | 4 | [16 empty] | -4
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Distribution Operations Engineering | 14521 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | EM Facilities | 15154 | Result |  | 34.25 |  | 34.25 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -34.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | EM Facilities | 15154 | ADMIN |  | 19 |  | 19 | [16 empty] | -19
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | EM Facilities | 15154 | ENVPLN |  | 12 |  | 12 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -12
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | EM Facilities | 15154 | ENVSVC |  | 3.25 |  | 3.25 | [16 empty] | -3.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 5 |  | 5 | 1 | [11 empty] | 1 |  |  |  | -5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 1 |  | 1 | [16 empty] | -1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | IT Telecom Maintenance | 13892 | HRSOT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Rights | 11929 | Result |  | 3 |  | 3 | [16 empty] | -3
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Rights | 11929 | ACQLIT |  | 2 |  | 2 | [16 empty] | -2
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Surveying | 12577 | Result |  | 458.25 | 200 | 658.25 | [5 empty] | 100 | 100 | [5 empty] | 200 |  |  |  | -658.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Surveying | 12577 | ACQLIT |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Surveying | 12577 | ADM-OT |  | 70.5 |  | 70.5 | [16 empty] | -70.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Land Surveying | 12577 | LNDENG |  | 385.5 | 200 | 585.5 | [5 empty] | 100 | 100 | [5 empty] | 200 |  |  |  | -585.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | LCE- Division Teams | 15789 | ACTSVC |  | 8.5 | 40 | 48.5 | [5 empty] | 20 | 20 | [5 empty] | 40 |  |  |  | -48.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | North Distribution Control Center | 11890 | MO |  |  | 40 | 40 | [7 empty] | 10 | 10 | 10 | 10 |  | 40 |  |  |  | -40
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Project Management & Controls | 14182 | Result |  | 25.5 | 600 | 625.5 |  |  | 9 | 0.5 |  | 100 | 100 | 100 | 100 | 100 | 100 |  | 609.5 |  |  |  | -625.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Project Management & Controls | 14182 | CNSTOT |  | 16 |  | 16 | [16 empty] | -16
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Project Management & Controls | 14182 | CONSTR |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Project Management & Controls | 14182 | ENGMAP |  | 0.5 | 600 | 600.5 |  |  |  | 0.5 |  | 100 | 100 | 100 | 100 | 100 | 100 |  | 600.5 |  |  |  | -600.5
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Reliability Planning | 13549 | ENGMAP |  | 29 |  | 29 | [16 empty] | -29
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | SI Restoration | 14110 | FLDSVC |  |  | 60 | 60 | [7 empty] | 15 | 15 | 15 | 15 |  | 60 |  |  |  | -60
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40.01 | 40.01 | [5 empty] | 0.83 | 9.17 | 9.17 | 9.17 | 8.75 | 2.92 |  | 40.01 |  |  |  | -40.01
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 13 |  | 13 | [16 empty] | -13
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Result |  |  | 97 | 216 |  | 216 |  | 1 | 5 | [9 empty] | 6 |  |  |  | -119
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | PGE1/# | # | #
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Apprentice - Training Coordinator | 12689 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Business Operations | 15495 | ACTSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Distribution Line Tech - SCADA | 15275 | Result |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Distribution Line Tech - SCADA | 15275 | MO |  | 8 |  | 8 | [16 empty] | -8
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Distribution Operations Engineering | 14521 | ENGMAP | 2 | 2 |  | 2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | EM Facilities | 15154 | Result | 24 | 55.5 |  | 55.5 | [16 empty] | -31.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | EM Facilities | 15154 | ADMIN | 15 | 42 |  | 42 | [16 empty] | -27
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | EM Facilities | 15154 | ENVPLN | 6 | 10.5 |  | 10.5 | [16 empty] | -4.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | EM Facilities | 15154 | ENVSVC | 3 | 3 |  | 3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Land Rights | 11929 | LNDRTS | 1 | 6 |  | 6 | [16 empty] | -5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | LCE- Division Teams | 15789 | ACTSVC | 1 | 0.75 |  | 0.75 | [16 empty] | 0.25
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC | 1 | 1 |  | 1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | North Distribution Control Center | 11890 | Result | 16 | 37.75 |  | 37.75 | [16 empty] | -21.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | North Distribution Control Center | 11890 | MO | 16 | 16 |  | 16
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | North Distribution Control Center | 11890 | MO-DT |  | 18.75 |  | 18.75 | [16 empty] | -18.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | North Distribution Control Center | 11890 | MO-OT |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Project Management & Controls | 14182 | ENGMAP | 4 | 10 |  | 10 |  | 1 | 5 | [9 empty] | 6 |  |  |  | -6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Reliability Planning | 13549 | ENGMAP | 29 | 31 |  | 31 | [16 empty] | -2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SI Restoration | 14110 | Result |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SI Restoration | 14110 | FLDSDT |  | 9.75 |  | 9.75 | [16 empty] | -9.75
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SI Restoration | 14110 | FLDSOT |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SI Restoration | 14110 | FLDSVC |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | SI Restoration - NOT USE | 12044 | FLDSVC | 17 | [19 empty] | 17
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | South Distribution Control Center | 11797 | Result |  | 3 |  | 3 | [16 empty] | -3
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | South Distribution Control Center | 11797 | MO |  | 1 |  | 1 | [16 empty] | -1
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | South Distribution Control Center | 11797 | MO-DT |  | 2 |  | 2 | [16 empty] | -2
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Substation Maintenance | 10472 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Substation Maintenance | 10472 | MO |  | 7 |  | 7 | [16 empty] | -7
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Substation Maintenance | 10472 | SWTCHO |  | 10 |  | 10 | [16 empty] | -10
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Substation Maintenance | 10472 | SWTODT |  | 6 |  | 6 | [16 empty] | -6
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Substation Maintenance | 10472 | SWTOOT |  | 10.5 |  | 10.5 | [16 empty] | -10.5
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Result |  |  |  | 5182.75 | 400 | 5582.75 | 19.75 | 76.25 | 749.25 | 692.5 | 400 | [7 empty] | 1937.75 |  |  |  | -5582.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | PGE1/# | # | #
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Apprentice - Training Coordinator | 12689 | Result |  | 7 |  | 7 |  | 4 | 3 | [9 empty] | 7 |  |  |  | -7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Apprentice - Training Coordinator | 12689 | MO |  | 4 |  | 4 |  | 1 | 3 | [9 empty] | 4 |  |  |  | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Apprentice - Training Coordinator | 12689 | MO-DT |  | 3 |  | 3 |  | 3 | [10 empty] | 3 |  |  |  | -3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Business Operations | 15495 | ACTSVC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | CC Work Force Management | 11034 | MANAGE |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Asset Management Several | 14459 | MANAGE |  | 2 |  | 2 | [16 empty] | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Line Tech - SCADA | 15275 | Result |  | 29.5 |  | 29.5 |  | 8 | [10 empty] | 8 |  |  |  | -29.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Line Tech - SCADA | 15275 | MO |  | 16.5 |  | 16.5 |  | 6 | [10 empty] | 6 |  |  |  | -16.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Line Tech - SCADA | 15275 | MO-DT |  | 3 |  | 3 | [16 empty] | -3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 10 |  | 10 |  | 2 | [10 empty] | 2 |  |  |  | -10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Distribution Operations Engineering | 14521 | ENGMAP |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | EM Facilities | 15154 | Result |  | 116.25 |  | 116.25 | 2.5 | 2 | 6.25 | 10.25 | [8 empty] | 21 |  |  |  | -116.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | EM Facilities | 15154 | ADM-OT |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | EM Facilities | 15154 | ADMIN |  | 64 |  | 64 |  | 2 | 1 | [9 empty] | 3 |  |  |  | -64
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | EM Facilities | 15154 | ENVPLN |  | 50.25 |  | 50.25 | 2.5 |  | 3.25 | 10.25 | [8 empty] | 16 |  |  |  | -50.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | EM Projects | 15240 | BIOCUL |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec NV South | 15216 | Result |  | 431 |  | 431 |  |  | 260.5 | 170.5 | [8 empty] | 431 |  |  |  | -431
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec NV South | 15216 | CNSTDT |  | 86.5 |  | 86.5 |  |  | 48 | 38.5 | [8 empty] | 86.5 |  |  |  | -86.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec NV South | 15216 | CNSTOT |  | 64.5 |  | 64.5 |  |  | 42.5 | 22 | [8 empty] | 64.5 |  |  |  | -64.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec NV South | 15216 | CONSTR |  | 280 |  | 280 |  |  | 170 | 110 | [8 empty] | 280 |  |  |  | -280
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SA | 11832 | Result |  | 114.5 | 400 | 514.5 |  |  | 114.5 |  | 400 | [7 empty] | 514.5 |  |  |  | -514.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SA | 11832 | CNSTDT |  | 14.5 |  | 14.5 |  |  | 14.5 | [9 empty] | 14.5 |  |  |  | -14.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SA | 11832 | CNSTOT |  | 20 |  | 20 |  |  | 20 | [9 empty] | 20 |  |  |  | -20
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SA | 11832 | CONSTR |  | 80 | 400 | 480 |  |  | 80 |  | 400 | [7 empty] | 480 |  |  |  | -480
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SI North | 14632 | Result |  | 3942.5 |  | 3942.5 |  | 16.5 | 324.5 | 463 | [8 empty] | 804 |  |  |  | -3942.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SI North | 14632 | CNSTDT |  | 98 |  | 98 |  |  | 11 | 39.5 | [8 empty] | 50.5 |  |  |  | -98
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SI North | 14632 | CNSTOT |  | 330 |  | 330 |  | 1.5 | 43.5 | 53.5 | [8 empty] | 98.5 |  |  |  | -330
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec SI North | 14632 | CONSTR |  | 3514.5 |  | 3514.5 |  | 15 | 270 | 370 | [8 empty] | 655 |  |  |  | -3514.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec Sonoma | 11838 | Result |  | 15 |  | 15 |  |  | 15 | [9 empty] | 15 |  |  |  | -15
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec Sonoma | 11838 | CNSTDT |  | 2.5 |  | 2.5 |  |  | 2.5 | [9 empty] | 2.5 |  |  |  | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec Sonoma | 11838 | CNSTOT |  | 2.5 |  | 2.5 |  |  | 2.5 | [9 empty] | 2.5 |  |  |  | -2.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | GC Elec Sonoma | 11838 | CONSTR |  | 10 |  | 10 |  |  | 10 | [9 empty] | 10 |  |  |  | -10
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | IT Telecom Maintenance | 13892 | HRSST |  | 4 |  | 4 | [16 empty] | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Acquisition | 12809 | Result |  | 76.5 |  | 76.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -76.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Acquisition | 12809 | ACQLIT |  | 67 |  | 67 |  |  | 3 | [9 empty] | 3 |  |  |  | -67
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Acquisition | 12809 | ADMIN |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Rights | 11929 | LNDRTS |  | 3 |  | 3 |  |  |  | 3 | [8 empty] | 3 |  |  |  | -3
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Surveying | 12577 | Result |  | 15.75 |  | 15.75 | [16 empty] | -15.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Surveying | 12577 | ADM-OT |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Surveying | 12577 | LNDENG |  | 13.5 |  | 13.5 | [16 empty] | -13.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | LCE- Division Teams | 15789 | ACTSVC |  | 21 |  | 21 | 2 | 1 | 3 | 1 | [8 empty] | 7 |  |  |  | -21
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | North Distribution Control Center | 11890 | Result |  | 24.75 |  | 24.75 | 1.25 | 5.75 | 3 | 2.75 | [8 empty] | 12.75 |  |  |  | -24.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | North Distribution Control Center | 11890 | MO |  | 11 |  | 11 | 0.75 | 3 | 0.5 | 1 | [8 empty] | 5.25 |  |  |  | -11
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | North Distribution Control Center | 11890 | MO-DT |  | 7 |  | 7 |  |  | 1.5 | 1.25 | [8 empty] | 2.75 |  |  |  | -7
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | North Distribution Control Center | 11890 | MO-OT |  | 6.75 |  | 6.75 | 0.5 | 2.75 | 1 | 0.5 | [8 empty] | 4.75 |  |  |  | -6.75
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Operations Systems | 10484 | SCADSV |  | 4 |  | 4 |  | 4 | [10 empty] | 4 |  |  |  | -4
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Project Management & Controls | 14182 | Result |  | 267.5 |  | 267.5 | 14 | 35 | 6.5 | 42 | [8 empty] | 97.5 |  |  |  | -267.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Project Management & Controls | 14182 | CONSTR |  | 220 |  | 220 | 14 | 34 |  | 36 | [8 empty] | 84 |  |  |  | -220
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Project Management & Controls | 14182 | ENGMAP |  | 47.5 |  | 47.5 |  | 1 | 6.5 | 6 | [8 empty] | 13.5 |  |  |  | -47.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Reliability Planning | 13549 | Result |  | 75.5 |  | 75.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -75.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Reliability Planning | 13549 | ENGMAP |  | 74.5 |  | 74.5 |  |  | 3 | [9 empty] | 3 |  |  |  | -74.5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | Safety Infrastructure Protection Team | 15937 | MANAGE |  | 5 |  | 5 |  |  | 5 | [9 empty] | 5 |  |  |  | -5
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 | VP Elec Distribution Operations | 15443 | MANAGE |  | 20 |  | 20 | [16 empty] | -20
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Result |  |  | 5142 | 2883 | 780 | 3663 | 57.75 | 462.5 | 195.25 | 1269 | 780 | [7 empty] | 2764.5 |  |  |  | 1479
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | PGE1/# | # | #
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Business Operations | 15495 | ACTSVC | 22 | 3.25 |  | 3.25 | 0.75 | [11 empty] | 0.75 |  |  |  | 18.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | CC Work Force Management | 11034 | MANAGE | 26 | 1 |  | 1 | 0.5 | [11 empty] | 0.5 |  |  |  | 25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Central Design North | 12974 | Result |  | 11.5 |  | 11.5 | [16 empty] | -11.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Central Design North | 12974 | EEST |  | 8.5 |  | 8.5 | [16 empty] | -8.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Central Design North | 12974 | EESTOT |  | 3 |  | 3 | [16 empty] | -3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Distribution Asset Management Several | 14459 | MANAGE | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Distribution Line Tech - SCADA | 15275 | Result |  | 11.25 |  | 11.25 |  |  | 11.25 | [9 empty] | 11.25 |  |  |  | -11.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Distribution Line Tech - SCADA | 15275 | MO |  | 9 |  | 9 |  |  | 9 | [9 empty] | 9 |  |  |  | -9
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 2.25 |  | 2.25 |  |  | 2.25 | [9 empty] | 2.25 |  |  |  | -2.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | EM Facilities | 15154 | Result | 40 | 28.75 |  | 28.75 |  |  | 3 | 1 | [8 empty] | 4 |  |  |  | 11.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | EM Facilities | 15154 | ADM-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | EM Facilities | 15154 | ADMIN | 30 | 22 |  | 22 |  |  | 1 | [9 empty] | 1 |  |  |  | 8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | EM Facilities | 15154 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | EM Facilities | 15154 | ENVPLN | 10 | 4.25 |  | 4.25 |  |  | 2 | 1 | [8 empty] | 3 |  |  |  | 5.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV North | 11830 | Result |  | 15.5 |  | 15.5 |  |  |  | 15.5 | [8 empty] | 15.5 |  |  |  | -15.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV North | 11830 | CNSTDT |  | 3 |  | 3 |  |  |  | 3 | [8 empty] | 3 |  |  |  | -3
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV North | 11830 | CNSTOT |  | 2.5 |  | 2.5 |  |  |  | 2.5 | [8 empty] | 2.5 |  |  |  | -2.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV North | 11830 | CONSTR |  | 10 |  | 10 |  |  |  | 10 | [8 empty] | 10 |  |  |  | -10
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV South | 15216 | Result |  | 158 |  | 158 |  |  |  | 158 | [8 empty] | 158 |  |  |  | -158
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV South | 15216 | CNSTDT |  | 36 |  | 36 |  |  |  | 36 | [8 empty] | 36 |  |  |  | -36
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV South | 15216 | CNSTOT |  | 22 |  | 22 |  |  |  | 22 | [8 empty] | 22 |  |  |  | -22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec NV South | 15216 | CONSTR |  | 100 |  | 100 |  |  |  | 100 | [8 empty] | 100 |  |  |  | -100
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI North | 14632 | Result |  | 2262.5 | 700 | 2962.5 | 52.5 | 455.5 | 156 | 888 | 700 | [7 empty] | 2252 |  |  |  | -2962.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI North | 14632 | CNSTDT |  | 25 |  | 25 |  |  |  | 25 | [8 empty] | 25 |  |  |  | -25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI North | 14632 | CNSTOT |  | 167.5 |  | 167.5 | 2.5 | 15.5 | 6 | 123 | [8 empty] | 147 |  |  |  | -167.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI North | 14632 | CONSTR |  | 2070 | 700 | 2770 | 50 | 440 | 150 | 740 | 700 | [7 empty] | 2080 |  |  |  | -2770
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI South | 11834 | Result | 4741 | 167.5 |  | 167.5 |  |  |  | 167.5 | [8 empty] | 167.5 |  |  |  | 4573.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI South | 11834 | CNSTDT |  | 22 |  | 22 |  |  |  | 22 | [8 empty] | 22 |  |  |  | -22
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI South | 11834 | CNSTOT |  | 25.5 |  | 25.5 |  |  |  | 25.5 | [8 empty] | 25.5 |  |  |  | -25.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | GC Elec SI South | 11834 | CONSTR | 4741 | 120 |  | 120 |  |  |  | 120 | [8 empty] | 120 |  |  |  | 4621
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | IT Telecom Maintenance | 13892 | HRSST |  | 8 |  | 8 |  |  | 8 | [9 empty] | 8 |  |  |  | -8
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Land Rights | 11929 | Result | 30 | 20.25 |  | 20.25 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | 9.75
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Land Rights | 11929 | ACQLIT | 29 | 3.75 |  | 3.75 | [16 empty] | 25.25
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Land Rights | 11929 | ADM-OT |  | 2 |  | 2 | [16 empty] | -2
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Land Rights | 11929 | LNDRTS | 1 | 14.5 |  | 14.5 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -13.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Land Surveying | 12577 | LNDENG |  | 5 |  | 5 | [16 empty] | -5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | LCE- Division Teams | 15789 | ACTSVC | 25 | 36 |  | 36 | 3 | 3 | 4 | 1 | [8 empty] | 11 |  |  |  | -11
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | North Distribution Control Center | 11890 | MO |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Project Management & Controls | 14182 | Result | 156 | 71.5 |  | 71.5 |  |  | 2.5 | 37 | [8 empty] | 39.5 |  |  |  | 84.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Project Management & Controls | 14182 | CONSTR | 20 | 60 |  | 60 |  |  |  | 36 | [8 empty] | 36 |  |  |  | -40
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Project Management & Controls | 14182 | ENGMAP | 136 | 11.5 |  | 11.5 |  |  | 2.5 | 1 | [8 empty] | 3.5 |  |  |  | 124.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Reliability Planning | 13549 | Result | 73 | 47 |  | 47 |  | 4 | 3 | [9 empty] | 7 |  |  |  | 26
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Reliability Planning | 13549 | ENGMAP | 68 | 42.5 |  | 42.5 |  | 4 | 3 | [9 empty] | 7 |  |  |  | 25.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Reliability Planning | 13549 | ENGMPO | 5 | 4.5 |  | 4.5 | [16 empty] | 0.5
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | SI Gas Construction | 12055 | CONSTR |  | 6 |  | 6 |  |  | 6 | [9 empty] | 6 |  |  |  | -6
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 80 | 80 |  |  |  |  | 80 | [7 empty] | 80 |  |  |  | -80
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | VP Elec Distribution Operations | 15443 | MANAGE | 23 | 23 |  | 23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Result |  |  | 100 | 137.75 |  | 137.75 | [16 empty] | -37.75
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | PGE1/# | # | #
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Business Operations | 15495 | ACTSVC | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Capacity Planning | 13550 | ENGMAP | 1 | 1 |  | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | EM Facilities | 15154 | Result | 50 | 28.25 |  | 28.25 | [16 empty] | 21.75
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | EM Facilities | 15154 | ADM-OT | 1 | 1 |  | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | EM Facilities | 15154 | ADMIN | 47 | 24 |  | 24 | [16 empty] | 23
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | EM Facilities | 15154 | ENVPLN | 2 | 2 |  | 2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | EM Facilities | 15154 | ENVSVC |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | IT Telecom Maintenance | 13892 | HRSST | 3 | 3 |  | 3
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Land Natural Resource Mgmt | 14178 | VEGMGT | 31 | 2 |  | 2 | [16 empty] | 29
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Land Surveying | 12577 | Result | 3 | 2 |  | 2 | [16 empty] | 1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | LCE- Division Teams | 15789 | ACTSVC | 11 | 25 |  | 25 | [16 empty] | -14
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 4 |  | 4 | [16 empty] | -4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | North Distribution Control Center | 11890 | Result |  | 6 |  | 6 | [16 empty] | -6
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | North Distribution Control Center | 11890 | MO |  | 4 |  | 4 | [16 empty] | -4
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | North Distribution Control Center | 11890 | MO-DT |  | 2 |  | 2 | [16 empty] | -2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Project Management & Controls | 14182 | Result |  | 41 |  | 41 | [16 empty] | -41
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Project Management & Controls | 14182 | CNSTOT |  | 5 |  | 5 | [16 empty] | -5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Project Management & Controls | 14182 | ENGMAP |  | 36 |  | 36 | [16 empty] | -36
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Reliability Planning | 13549 | Result |  | 6 |  | 6 | [16 empty] | -6
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Reliability Planning | 13549 | ENGMAP |  | 5 |  | 5 | [16 empty] | -5
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | VP Elec Distribution Operations | 15443 | MANAGE |  | 17 |  | 17 | [16 empty] | -17
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Result |  |  |  | 154.25 | 77.31 | 231.56 |  |  |  | 2 | 5.09 | 5.33 | 5.33 | 5.33 | 5.33 | 5.09 | 5.33 | 0.48 | 39.31 | 40 |  |  | -231.56
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | PGE1/# | # | #
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | EM Facilities | 15154 | Result |  | 20.5 |  | 20.5 |  |  |  | 1.5 | [8 empty] | 1.5 |  |  |  | -20.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | EM Facilities | 15154 | ADMIN |  | 17 |  | 17 | [16 empty] | -17
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | EM Facilities | 15154 | ENVPLN |  | 1.5 |  | 1.5 |  |  |  | 1.5 | [8 empty] | 1.5 |  |  |  | -1.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | EM Facilities | 15154 | ENVSVC |  | 2 |  | 2 | [16 empty] | -2
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Surveying | 12577 | Result |  | 53.75 |  | 53.75 | [16 empty] | -53.75
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Surveying | 12577 | ACQLIT |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Surveying | 12577 | ADM-OT |  | 5 |  | 5 | [16 empty] | -5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Land Surveying | 12577 | LNDENG |  | 48 |  | 48 | [16 empty] | -48
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | LCE- Division Teams | 15789 | ACTSVC |  | 21.25 |  | 21.25 | [16 empty] | -21.25
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Project Management & Controls | 14182 | Result |  | 39.5 |  | 39.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -39.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Project Management & Controls | 14182 | CNSTOT |  | 11 |  | 11 | [16 empty] | -11
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Project Management & Controls | 14182 | ENGMAP |  | 28.5 |  | 28.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -28.5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Reliability Planning | 13549 | Result |  | 7 |  | 7 | [16 empty] | -7
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Reliability Planning | 13549 | ENGMAP |  | 5 |  | 5 | [16 empty] | -5
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Reliability Planning | 13549 | ENGMPO |  | 2 |  | 2 | [16 empty] | -2
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | SLSR:EST Estimating | 12847 | EEST |  |  | 37.31 | 37.31 |  |  |  |  | 5.09 | 5.33 | 5.33 | 5.33 | 5.33 | 5.09 | 5.33 | 0.48 | 37.31 |  |  |  | -37.31
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Result |  |  | 268 | 93 |  | 93 | [16 empty] | 175
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | PGE1/# | # | #
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Business Operations | 15495 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | EM Facilities | 15154 | Result | 20 | 16.75 |  | 16.75 | [16 empty] | 3.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | EM Facilities | 15154 | ADMIN | 19 | 12.5 |  | 12.5 | [16 empty] | 6.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | EM Facilities | 15154 | ENVPLN | 1 | 2.5 |  | 2.5 | [16 empty] | -1.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | EM Facilities | 15154 | ENVSVC |  | 1.75 |  | 1.75 | [16 empty] | -1.75
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | LCE- Division Teams | 15789 | ACTSVC | 2 | 30.25 |  | 30.25 | [16 empty] | -28.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | North Distribution Control Center | 11890 | Result | 100 | 1.5 |  | 1.5 | [16 empty] | 98.5
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | North Distribution Control Center | 11890 | MO | 100 | 1.25 |  | 1.25 | [16 empty] | 98.75
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | North Distribution Control Center | 11890 | MO-OT |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Project Management & Controls | 14182 | Result | 89 | 29 |  | 29 | [16 empty] | 60
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Project Management & Controls | 14182 | CNSTOT | 9 | 9 |  | 9
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Project Management & Controls | 14182 | ENGMAP | 80 | 20 |  | 20 | [16 empty] | 60
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Reliability Planning | 13549 | Result | 7 | 11 |  | 11 | [16 empty] | -4
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Reliability Planning | 13549 | ENGMAP | 6 | 10 |  | 10 | [16 empty] | -4
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Result |  |  | 242 | 84.75 |  | 84.75 | [16 empty] | 157.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | PGE1/# | # | #
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | EM Facilities | 15154 | Result | 3 | 12.25 |  | 12.25 | [16 empty] | -9.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | EM Facilities | 15154 | ADMIN | 3 | 11 |  | 11 | [16 empty] | -8
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | LCE- Division Teams | 15789 | ACTSVC | 1 | 21.5 |  | 21.5 | [16 empty] | -20.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | North Distribution Control Center | 11890 | MO | 120 | 5.5 |  | 5.5 | [16 empty] | 114.5
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Project Management & Controls | 14182 | Result | 64 | 22 |  | 22 | [16 empty] | 42
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Project Management & Controls | 14182 | CNSTOT |  | 6 |  | 6 | [16 empty] | -6
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Project Management & Controls | 14182 | ENGMAP | 64 | 16 |  | 16 | [16 empty] | 48
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Reliability Planning | 13549 | Result | 3 | 6 |  | 6 | [16 empty] | -3
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Reliability Planning | 13549 | ENGMAP | 2 | 5 |  | 5 | [16 empty] | -3
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | VP Elec Distribution Operations | 15443 | MANAGE |  | 17 |  | 17 | [16 empty] | -17
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Result |  |  | 155 | 108.5 |  | 108.5 | [16 empty] | 46.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | PGE1/# | # | #
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Capacity Planning | 13550 | ENGMAP | 2 | 2 |  | 2
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | EM Facilities | 15154 | ADMIN | 5 | 18 |  | 18 | [16 empty] | -13
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Gas Locate & Mark North | 15893 | Result |  | 19.5 |  | 19.5 | [16 empty] | -19.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Gas Locate & Mark North | 15893 | CNSTOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Gas Locate & Mark North | 15893 | CONSTR |  | 16 |  | 16 | [16 empty] | -16
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Land Rights | 11929 | ACQLIT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | LCE- Division Teams | 15789 | ACTSVC | 7 | 20.5 |  | 20.5 | [16 empty] | -13.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | North Distribution Control Center | 11890 | Result | 25 | 0.5 |  | 0.5 | [16 empty] | 24.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | North Distribution Control Center | 11890 | MO | 25 | [19 empty] | 25
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | North Distribution Control Center | 11890 | MO-DT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Project Management & Controls | 14182 | ENGMAP | 56 | 24 |  | 24 | [16 empty] | 32
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Reliability Planning | 13549 | Result | 5 | 4.5 |  | 4.5 | [16 empty] | 0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Reliability Planning | 13549 | ENGMAP | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | SI Restoration | 14110 | FLDSVC | 55 | [19 empty] | 55
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Result |  |  |  | 90.25 | 77.85 | 168.1 |  |  | 1.5 | 2.75 | 4.1 | 4.29 | 4.29 | 4.29 | 4.29 | 4.1 | 4.29 | 4.49 | 38.39 | 43.71 |  |  | -168.1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | PGE1/# | # | #
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Central Design Contract Estimating | 11714 | EEST |  | 33 |  | 33 |  |  | 1.5 | 1.5 | [8 empty] | 3 |  |  |  | -33
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | EM Facilities | 15154 | Result |  | 25.5 |  | 25.5 |  |  |  | 0.75 | [8 empty] | 0.75 |  |  |  | -25.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | EM Facilities | 15154 | ADMIN |  | 24.75 |  | 24.75 | [16 empty] | -24.75
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | EM Facilities | 15154 | ENVPLN |  | 0.75 |  | 0.75 |  |  |  | 0.75 | [8 empty] | 0.75 |  |  |  | -0.75
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 2 |  | 2 | [16 empty] | -2
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Land Rights | 11929 | Result |  | 1 |  | 1 | [16 empty] | -1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Land Rights | 11929 | ACQLIT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Land Surveying | 12577 | LNDENG |  | 3 |  | 3 | [16 empty] | -3
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | LCE- Division Teams | 15789 | ACTSVC |  | 8.25 |  | 8.25 | [16 empty] | -8.25
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Project Management & Controls | 14182 | ENGMAP |  | 4.5 |  | 4.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -4.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Reliability Planning | 13549 | Result |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Reliability Planning | 13549 | ENGMAP |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | SLSR:EST Estimating | 12847 | EEST |  |  | 37.85 | 37.85 |  |  |  |  | 4.1 | 4.29 | 4.29 | 4.29 | 4.29 | 4.1 | 4.29 | 4.49 | 34.14 | 3.71 |  |  | -37.85
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | VP Elec Distribution Operations | 15443 | MANAGE |  | 8 |  | 8 | [16 empty] | -8
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Result |  |  | 133 | 63.25 |  | 63.25 | [16 empty] | 69.75
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | PGE1/# | # | #
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Business Operations | 15495 | ACTSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | EM Facilities | 15154 | Result | 4 | 7 |  | 7 | [16 empty] | -3
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | EM Facilities | 15154 | ADMIN | 4 | 4.75 |  | 4.75 | [16 empty] | -0.75
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | EM Facilities | 15154 | ENVPLN |  | 2 |  | 2 | [16 empty] | -2
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | LCE- Division Teams | 15789 | ACTSVC | 2 | 26.5 |  | 26.5 | [16 empty] | -24.5
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | North Distribution Control Center | 11890 | MO | 30 | [19 empty] | 30
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Reliability Planning | 13549 | ENGMAP |  | 1 |  | 1 | [16 empty] | -1
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | SI Restoration | 14110 | FLDSVC | 33 | [19 empty] | 33
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Result |  |  |  | 191.75 |  | 191.75 | [16 empty] | -191.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | PGE1/# | # | #
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Business Operations | 15495 | ACTSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | CC Work Force Management | 11034 | MANAGE |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | EM Facilities | 15154 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | EM Facilities | 15154 | ADM-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | EM Facilities | 15154 | ADMIN |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | EM Facilities | 15154 | ENVPLN |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Gas Locate & Mark North | 15893 | Result |  | 37.75 |  | 37.75 | [16 empty] | -37.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Gas Locate & Mark North | 15893 | CNSTDT |  | 5 |  | 5 | [16 empty] | -5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Gas Locate & Mark North | 15893 | CNSTOT |  | 4.75 |  | 4.75 | [16 empty] | -4.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Gas Locate & Mark North | 15893 | CONSTR |  | 28 |  | 28 | [16 empty] | -28
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Acquisition | 12809 | Result |  | 35.5 |  | 35.5 | [16 empty] | -35.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Acquisition | 12809 | ACQLIT |  | 32 |  | 32 | [16 empty] | -32
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Acquisition | 12809 | ACQRIG |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Rights | 11929 | Result |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Rights | 11929 | ACQLIT |  | 3 |  | 3 | [16 empty] | -3
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Surveying | 12577 | Result |  | 14.75 |  | 14.75 | [16 empty] | -14.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Surveying | 12577 | LNDENG |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | LCE- Division Teams | 15789 | ACTSVC |  | 21.75 |  | 21.75 | [16 empty] | -21.75
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 9 |  | 9 | [16 empty] | -9
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | North Distribution Control Center | 11890 | Result |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | North Distribution Control Center | 11890 | MO |  | 2 |  | 2 | [16 empty] | -2
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | North Distribution Control Center | 11890 | MO-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Project Management & Controls | 14182 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Reliability Planning | 13549 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Vegetation Management | 11140 | PRJMGT |  | 2 |  | 2 | [16 empty] | -2
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Result |  |  | 345 | 117.75 |  | 117.75 | [16 empty] | 227.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | PGE1/# | # | #
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Business Operations | 15495 | ACTSVC |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Facilities | 15154 | Result | 4 | 50.75 |  | 50.75 | [16 empty] | -46.75
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Facilities | 15154 | ADM-OT |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Facilities | 15154 | ADMIN | 3 | 32.25 |  | 32.25 | [16 empty] | -29.25
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Facilities | 15154 | ENVPLN | 1 | 13.5 |  | 13.5 | [16 empty] | -12.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Facilities | 15154 | ENVSVC |  | 4 |  | 4 | [16 empty] | -4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 7 |  | 7 | [16 empty] | -7
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Land Surveying | 12577 | ACQLIT | 4 | 3.5 |  | 3.5 | [16 empty] | 0.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | LCE- Division Teams | 15789 | ACTSVC | 2 | 19 |  | 19 | [16 empty] | -17
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 11 |  | 11 | [16 empty] | -11
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | North Distribution Control Center | 11890 | Result | 234 | 3 |  | 3 | [16 empty] | 231
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | North Distribution Control Center | 11890 | MO | 234 | 2 |  | 2 | [16 empty] | 232
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | North Distribution Control Center | 11890 | MO-DT |  | 1 |  | 1 | [16 empty] | -1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Project Management & Controls | 14182 | ENGMAP | 48 | [19 empty] | 48
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Reliability Planning | 13549 | ENGMAP |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | T&S Project Control Analyst | 15322 | PRJMGT | 1 | 1 |  | 1
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Vegetation Management | 11140 | PRJMGT | 2 | 6 |  | 6 | [16 empty] | -4
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | VP Elec Distribution Operations | 15443 | MANAGE |  | 11 |  | 11 | [16 empty] | -11
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Result |  |  | 362 | 83.75 |  | 83.75 | [16 empty] | 278.25
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | PGE1/# | # | #
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | EM Facilities | 15154 | Result | 6 | 17.75 |  | 17.75 | [16 empty] | -11.75
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | EM Facilities | 15154 | ADMIN | 6 | 14.5 |  | 14.5 | [16 empty] | -8.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | EM Facilities | 15154 | ENVSVC |  | 3.25 |  | 3.25 | [16 empty] | -3.25
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Gas Locate & Mark North | 15893 | CONSTR |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Land Rights | 11929 | ACQLIT | 3 | 3 |  | 3
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | LCE- Division Teams | 15789 | ACTSVC | 1 | 18 |  | 18 | [16 empty] | -17
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | North Distribution Control Center | 11890 | MO | 234 | [19 empty] | 234
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Reliability Planning | 13549 | ENGMAP | 2 | 3 |  | 3 | [16 empty] | -1
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | SI Restoration | 14110 | FLDSVC | 50 | [19 empty] | 50
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Result |  |  | 137 | 138 |  | 138 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | PGE1/# | # | #
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | EM Facilities | 15154 | Result | 1 | 37.25 |  | 37.25 | [16 empty] | -36.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | EM Facilities | 15154 | ADMIN |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | EM Facilities | 15154 | ENVPLN | 1 | 7.5 |  | 7.5 | [16 empty] | -6.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | EM Facilities | 15154 | ENVSVC |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 5 |  | 5 | [16 empty] | -5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Land Rights | 11929 | ACQLIT | 2 | 2 |  | 2
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | LCE- Division Teams | 15789 | ACTSVC |  | 20.75 |  | 20.75 | [16 empty] | -20.75
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | North Distribution Control Center | 11890 | Result | 30 | 16.5 |  | 16.5 | [16 empty] | 13.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | North Distribution Control Center | 11890 | MO | 30 | 5.5 |  | 5.5 | [16 empty] | 24.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | North Distribution Control Center | 11890 | MO-DT |  | 10.5 |  | 10.5 | [16 empty] | -10.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | North Distribution Control Center | 11890 | MO-OT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Project Management & Controls | 14182 | ENGMAP | 64 | 8 |  | 8 | [16 empty] | 56
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | SI Restoration | 14110 | Result | 40 | 26.5 |  | 26.5 | [16 empty] | 13.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | SI Restoration | 14110 | FLDSDT |  | 4.5 |  | 4.5 | [16 empty] | -4.5
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | SI Restoration | 14110 | FLDSOT |  | 15.25 |  | 15.25 | [16 empty] | -15.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | SI Restoration | 14110 | FLDSVC | 40 | 6.75 |  | 6.75 | [16 empty] | 33.25
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Vegetation Management | 11140 | PRJMGT |  | 1 |  | 1 | [16 empty] | -1
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Result |  |  | 157 | 103.75 |  | 103.75 | 4.5 | [11 empty] | 4.5 |  |  |  | 53.25
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | PGE1/# | # | #
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | EM Facilities | 15154 | ADMIN | 3 | 8.75 |  | 8.75 | [16 empty] | -5.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 2 |  | 2 | [16 empty] | -2
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | LCE- Division Teams | 15789 | ACTSVC |  | 22.75 |  | 22.75 | 4.5 | [11 empty] | 4.5 |  |  |  | -22.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 4 |  | 4 | [16 empty] | -4
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | North Distribution Control Center | 11890 | Result | 40 | 10 |  | 10 | [16 empty] | 30
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | North Distribution Control Center | 11890 | MO | 40 | 5 |  | 5 | [16 empty] | 35
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | North Distribution Control Center | 11890 | MO-DT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | North Distribution Control Center | 11890 | MO-OT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Project Management & Controls | 14182 | ENGMAP | 64 | 16 |  | 16 | [16 empty] | 48
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | SI Restoration | 14110 | Result | 50 | 22.25 |  | 22.25 | [16 empty] | 27.75
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | SI Restoration | 14110 | FLDSDT |  | 6.25 |  | 6.25 | [16 empty] | -6.25
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | SI Restoration | 14110 | FLDSOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | SI Restoration | 14110 | FLDSVC | 50 | 12.5 |  | 12.5 | [16 empty] | 37.5
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Result |  |  | 270 | 68.5 |  | 68.5 | [16 empty] | 201.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | PGE1/# | # | #
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Central Design Contract Estimating | 11714 | DSGNSV |  | 3 |  | 3 | [16 empty] | -3
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | EM Facilities | 15154 | ADMIN |  | 12.75 |  | 12.75 | [16 empty] | -12.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | EM Projects | 15240 | ENVSVC | 15 | [19 empty] | 15
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Land Natural Resource Mgmt | 14178 | Result | 15 | 2 |  | 2 | [16 empty] | 13
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Land Natural Resource Mgmt | 14178 | LNDRTS | 15 | [19 empty] | 15
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 2 |  | 2 | [16 empty] | -2
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | LCE- Division Teams | 15789 | ACTSVC |  | 23.75 |  | 23.75 | [16 empty] | -23.75
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | North Distribution Control Center | 11890 | MO | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Project Management & Controls | 14182 | ENGMAP | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | SI Restoration | 14110 | FLDSVC | 80 | [19 empty] | 80
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | VP Elec Distribution Operations | 15443 | MANAGE |  | 26 |  | 26 | [16 empty] | -26
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Result |  |  |  | 65.75 |  | 65.75 | 5 | [11 empty] | 5 |  |  |  | -65.75
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | PGE1/# | # | #
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | EM Facilities | 15154 | ADMIN |  | 12.25 |  | 12.25 | [16 empty] | -12.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | LCE- Division Teams | 15789 | ACTSVC |  | 9.25 |  | 9.25 | 5 | [11 empty] | 5 |  |  |  | -9.25
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 5 |  | 5 | [16 empty] | -5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Project Management & Controls | 14182 | Result |  | 28 |  | 28 | [16 empty] | -28
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Project Management & Controls | 14182 | CNSTOT |  | 4 |  | 4 | [16 empty] | -4
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Project Management & Controls | 14182 | ENGMAP |  | 24 |  | 24 | [16 empty] | -24
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Reliability Planning | 13549 | ENGMAP |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Result |  |  | 185 | 123 |  | 123 | [16 empty] | 62
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | PGE1/# | # | #
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Central Distribution Control Center | 12133 | MO-DT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | EM Facilities | 15154 | Result | 15 | 11 |  | 11 | [16 empty] | 4
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | EM Facilities | 15154 | ADMIN | 13 | 9 |  | 9 | [16 empty] | 4
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | EM Facilities | 15154 | ENVPLN | 1 | 1 |  | 1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | EM Facilities | 15154 | ENVSVC | 1 | 1 |  | 1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Land Surveying | 12577 | ACQLIT | 10 | 1.5 |  | 1.5 | [16 empty] | 8.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | LCE- Division Teams | 15789 | ACTSVC | 4 | 16.5 |  | 16.5 | [16 empty] | -12.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | North Distribution Control Center | 11890 | Result | 50 | 30.75 |  | 30.75 | [16 empty] | 19.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | North Distribution Control Center | 11890 | MO | 50 | 17.75 |  | 17.75 | [16 empty] | 32.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | North Distribution Control Center | 11890 | MO-DT |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | North Distribution Control Center | 11890 | MO-OT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Project Management & Controls | 14182 | Result | 48 | 14 |  | 14 | [16 empty] | 34
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Project Management & Controls | 14182 | CNSTOT |  | 10 |  | 10 | [16 empty] | -10
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Project Management & Controls | 14182 | ENGMAP | 48 | 4 |  | 4 | [16 empty] | 44
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Reliability Planning | 13549 | ENGMAP | 8 | 9 |  | 9 | [16 empty] | -1
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | SI Restoration | 14110 | Result | 50 | 9.75 |  | 9.75 | [16 empty] | 40.25
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | SI Restoration | 14110 | FLDSOT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | SI Restoration | 14110 | FLDSVC | 50 | 7.25 |  | 7.25 | [16 empty] | 42.75
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | VP Elec Distribution Operations | 15443 | MANAGE |  | 27 |  | 27 | [16 empty] | -27
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Result |  |  | 99 | 103 |  | 103 | [16 empty] | -4
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | PGE1/# | # | #
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | EM Facilities | 15154 | Result | 6 | 33.5 |  | 33.5 | [16 empty] | -27.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | EM Facilities | 15154 | ADMIN | 4 | 19 |  | 19 | [16 empty] | -15
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | EM Facilities | 15154 | ENVPLN | 2 | 11.5 |  | 11.5 | [16 empty] | -9.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | EM Facilities | 15154 | ENVSVC |  | 3 |  | 3 | [16 empty] | -3
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | EM Projects | 15240 | BIOCUL |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Natural Resource Mgmt | 14178 | VEGMGT |  | 6 |  | 6 | [16 empty] | -6
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Rights | 11929 | Result |  | 3 |  | 3 | [16 empty] | -3
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Rights | 11929 | ACQLIT |  | 2 |  | 2 | [16 empty] | -2
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Surveying | 12577 | Result | 3 | 2.75 |  | 2.75 | [16 empty] | 0.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Surveying | 12577 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Surveying | 12577 | ADM-OT | 1 | 1 |  | 1
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Land Surveying | 12577 | LNDENG |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | LCE- Division Teams | 15789 | ACTSVC | 1 | 20.25 |  | 20.25 | [16 empty] | -19.25
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | North Distribution Control Center | 11890 | MO | 10 | [19 empty] | 10
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Reliability Planning | 13549 | ENGMAP | 67 | 3 |  | 3 | [16 empty] | 64
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | SI Restoration | 14110 | FLDSVC | 12 | [19 empty] | 12
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | ST Gas Construction | 11938 | CONSTR |  | 16 |  | 16 | [16 empty] | -16
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | VP Elec Distribution Operations | 15443 | MANAGE |  | 18 |  | 18 | [16 empty] | -18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Result |  |  | 193 | 378.5 |  | 378.5 |  | 1 | 7.25 | 5 | [8 empty] | 13.25 |  |  |  | -185.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | PGE1/# | # | #
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Business Operations | 15495 | ACTSVC |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Distribution Line Tech - SCADA | 15275 | Result |  | 27.5 |  | 27.5 | [16 empty] | -27.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Distribution Line Tech - SCADA | 15275 | MO |  | 17.75 |  | 17.75 | [16 empty] | -17.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Distribution Line Tech - SCADA | 15275 | MO-DT |  | 3.75 |  | 3.75 | [16 empty] | -3.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Distribution Line Tech - SCADA | 15275 | MO-OT |  | 6 |  | 6 | [16 empty] | -6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Distribution Operations Engineering | 14521 | ENGMAP |  | 6 |  | 6 | [16 empty] | -6
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | EM Facilities | 15154 | Result | 16 | 35.25 |  | 35.25 |  |  | 0.25 | [9 empty] | 0.25 |  |  |  | -19.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | EM Facilities | 15154 | ADMIN | 12 | 31 |  | 31 |  |  | 0.25 | [9 empty] | 0.25 |  |  |  | -19
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | EM Facilities | 15154 | ENVPLN | 3 | 3 |  | 3
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | EM Facilities | 15154 | ENVSVC | 1 | 1.25 |  | 1.25 | [16 empty] | -0.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | EO&E E&T System Automation | 12148 | SCADSV |  | 18 |  | 18 | [16 empty] | -18
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Gas Locate & Mark North | 15893 | Result |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Gas Locate & Mark North | 15893 | CNSTOT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Gas Locate & Mark North | 15893 | CONSTR |  | 4 |  | 4 | [16 empty] | -4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | IT Telecom Maintenance | 13892 | Result | 7 | 22.75 |  | 22.75 | [16 empty] | -15.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | IT Telecom Maintenance | 13892 | HRSOT | 3 | 5.75 |  | 5.75 | [16 empty] | -2.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | IT Telecom Maintenance | 13892 | HRSST | 4 | 17 |  | 17 | [16 empty] | -13
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 | [16 empty] | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC | 4 | 4 |  | 4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | North Distribution Control Center | 11890 | Result | 74 | 110.75 |  | 110.75 | [16 empty] | -36.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | North Distribution Control Center | 11890 | MO | 73 | 59 |  | 59 | [16 empty] | 14
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | North Distribution Control Center | 11890 | MO-DT | 1 | 41 |  | 41 | [16 empty] | -40
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | North Distribution Control Center | 11890 | MO-OT |  | 10.75 |  | 10.75 | [16 empty] | -10.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | NV Electric Construction | 11894 | APRNST | 4 | [19 empty] | 4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Operations Systems | 10484 | OPERSV |  | 4 |  | 4 | [16 empty] | -4
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Project Management & Controls | 14182 | ENGMAP |  | 11 |  | 11 |  | 1 | 5 | 5 | [8 empty] | 11 |  |  |  | -11
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Reliability Planning | 13549 | Result | 7 | 23 |  | 23 |  |  | 2 | [9 empty] | 2 |  |  |  | -16
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Reliability Planning | 13549 | ENGMAP | 7 | 22 |  | 22 |  |  | 2 | [9 empty] | 2 |  |  |  | -15
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | SI Restoration | 14110 | Result | 81 | 73.75 |  | 73.75 | [16 empty] | 7.25
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | SI Restoration | 14110 | FLDSDT |  | 32 |  | 32 | [16 empty] | -32
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | SI Restoration | 14110 | FLDSOT |  | 24.5 |  | 24.5 | [16 empty] | -24.5
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | SI Restoration | 14110 | FLDSVC | 81 | 17.25 |  | 17.25 | [16 empty] | 63.75
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Substation Maintenance | 10472 | Result |  | 26 |  | 26 | [16 empty] | -26
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Substation Maintenance | 10472 | MO |  | 16 |  | 16 | [16 empty] | -16
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Substation Maintenance | 10472 | SWTCHO |  | 10 |  | 10 | [16 empty] | -10
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Result |  |  | 152 | 184 |  | 184 | 5 | 1 | 4.5 | [9 empty] | 10.5 |  |  |  | -32
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | PGE1/# | # | #
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | EM Facilities | 15154 | Result | 48.5 | 52.75 |  | 52.75 | [16 empty] | -4.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | EM Facilities | 15154 | ADMIN | 47.5 | 46 |  | 46 | [16 empty] | 1.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | EM Facilities | 15154 | ENVPLN | 1 | 6.75 |  | 6.75 | [16 empty] | -5.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | EM Projects | 15240 | BIOCUL |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Gas Distribution Projects Contract PCC | 15448 | XCON02 | 1 | 1 |  | 1
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Gas Locate & Mark North | 15893 | Result |  | 7.5 |  | 7.5 | [16 empty] | -7.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Gas Locate & Mark North | 15893 | CNSTOT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Gas Locate & Mark North | 15893 | CONSTR |  | 4 |  | 4 | [16 empty] | -4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Grid System Operations | 14052 | SWTCHO | 16 | [19 empty] | 16
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Acquisition | 12809 | ACQLIT |  | 8 |  | 8 | 1 |  | 1 | [9 empty] | 2 |  |  |  | -8
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Rights | 11929 | Result |  | 45.5 |  | 45.5 | 4 | [11 empty] | 4 |  |  |  | -45.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Rights | 11929 | ACQLIT |  | 32.5 |  | 32.5 | 3.5 | [11 empty] | 3.5 |  |  |  | -32.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Rights | 11929 | LNDRTS |  | 13 |  | 13 | 0.5 | [11 empty] | 0.5 |  |  |  | -13
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Surveying | 12577 | Result |  | 23 |  | 23 | [16 empty] | -23
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Surveying | 12577 | ADM-OT |  | 3.75 |  | 3.75 | [16 empty] | -3.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Land Surveying | 12577 | LNDENG |  | 19.25 |  | 19.25 | [16 empty] | -19.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC | 6.5 | 13.75 |  | 13.75 | [16 empty] | -7.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | North Distribution Control Center | 11890 | Result | 37 | 7.5 |  | 7.5 | [16 empty] | 29.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | North Distribution Control Center | 11890 | MO | 37 | 5.25 |  | 5.25 | [16 empty] | 31.75
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | North Distribution Control Center | 11890 | MO-DT |  | 2.25 |  | 2.25 | [16 empty] | -2.25
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Permitting G2 and CH2M | 15993 | XCON02 |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Project Management & Controls | 14182 | ENGMAP |  | 4 |  | 4 |  | 1 | 3 | [9 empty] | 4 |  |  |  | -4
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Reliability Planning | 13549 | ENGMAP | 2 | 2 |  | 2
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | SI Restoration | 14110 | FLDSVC | 41 | [19 empty] | 41
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | VP Elec Distribution Operations | 15443 | MANAGE |  | 9 |  | 9 | [16 empty] | -9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Result |  |  | 1160 | 3120.75 | 100 | 3220.75 | 549 | 518.5 | 1103.5 | 225.5 | 100 | [7 empty] | 2496.5 |  |  |  | -2060.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | PGE1/# | # | #
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Business Operations | 15495 | ACTSVC | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | EM Facilities | 15154 | Result | 127 | 18.25 |  | 18.25 | 2 |  | 1 | [9 empty] | 3 |  |  |  | 108.75
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | EM Facilities | 15154 | ADMIN | 6 | 16 |  | 16 | 2 | [11 empty] | 2 |  |  |  | -10
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | EM Facilities | 15154 | ENVPLN | 1 | 2.25 |  | 2.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -1.25
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | EM Facilities | 15154 | ENVSVC | 120 | [19 empty] | 120
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec NV North | 11830 | Result |  | 92.5 |  | 92.5 |  |  | 92.5 | [9 empty] | 92.5 |  |  |  | -92.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec NV North | 11830 | CNSTDT |  | 30 |  | 30 |  |  | 30 | [9 empty] | 30 |  |  |  | -30
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec NV North | 11830 | CNSTOT |  | 15 |  | 15 |  |  | 15 | [9 empty] | 15 |  |  |  | -15
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec NV North | 11830 | CONSTR |  | 47.5 |  | 47.5 |  |  | 47.5 | [9 empty] | 47.5 |  |  |  | -47.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI North | 14632 | Result |  | 2686 | 100 | 2786 | 546 | 518.5 | 769.5 | 191.5 | 100 | [7 empty] | 2125.5 |  |  |  | -2786
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI North | 14632 | CNSTDT |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI North | 14632 | CNSTOT |  | 277 |  | 277 | 48 | 48.5 | 87.5 | 2.5 | [8 empty] | 186.5 |  |  |  | -277
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI North | 14632 | CONSTR |  | 2407 | 100 | 2507 | 498 | 470 | 680 | 189 | 100 | [7 empty] | 1937 |  |  |  | -2507
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI South | 11834 | Result |  | 87.5 |  | 87.5 |  |  | 87.5 | [9 empty] | 87.5 |  |  |  | -87.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI South | 11834 | CNSTOT |  | 17.5 |  | 17.5 |  |  | 17.5 | [9 empty] | 17.5 |  |  |  | -17.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | GC Elec SI South | 11834 | CONSTR |  | 70 |  | 70 |  |  | 70 | [9 empty] | 70 |  |  |  | -70
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Land Rights | 11929 | LNDRTS | 255 | [19 empty] | 255
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | LCE- Division Teams | 15789 | ACTSVC | 130 | 1 |  | 1 | [16 empty] | 129
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC | 2 | 2 |  | 2
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | North Distribution Control Center | 11890 | MO | 183 | [19 empty] | 183
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Project Management & Controls | 14182 | Result | 250 | 199.5 |  | 199.5 |  |  | 153 | 30.5 | [8 empty] | 183.5 |  |  |  | 50.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Project Management & Controls | 14182 | CONSTR | 16 | 16 |  | 16
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Project Management & Controls | 14182 | ENGMAP | 234 | 183.5 |  | 183.5 |  |  | 153 | 30.5 | [8 empty] | 183.5 |  |  |  | 50.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Reliability Planning | 13549 | Result | 9 | 9 |  | 9
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Reliability Planning | 13549 | ENGMAP | 8 | 8 |  | 8
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | SI Gas Construction | 12055 | Result |  | 3.5 |  | 3.5 |  |  |  | 3.5 | [8 empty] | 3.5 |  |  |  | -3.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | SI Gas Construction | 12055 | CNSTOT |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | SI Gas Construction | 12055 | CONSTR |  | 2.5 |  | 2.5 |  |  |  | 2.5 | [8 empty] | 2.5 |  |  |  | -2.5
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | SI Restoration | 14110 | FLDSVC | 183 | [19 empty] | 183
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | VP Elec Distribution Operations | 15443 | MANAGE | 20 | 20 |  | 20
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Result |  |  | 4108 | 142 | 380 | 522 | 3 |  | 4 | 14.25 | 300 | 80 | [6 empty] | 401.25 |  |  |  | 3586
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | PGE1/# | # | #
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Business Operations | 15495 | ACTSVC | 7 | 2.25 |  | 2.25 | [16 empty] | 4.75
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Central Design North | 12974 | Result |  | 33.5 |  | 33.5 | [16 empty] | -33.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Central Design North | 12974 | EEST |  | 25.5 |  | 25.5 | [16 empty] | -25.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Central Design North | 12974 | EESTOT |  | 8 |  | 8 | [16 empty] | -8
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | EM Facilities | 15154 | Result | 100 | 25.5 |  | 25.5 | 2 |  | 2 | [9 empty] | 4 |  |  |  | 74.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | EM Facilities | 15154 | ADMIN | 32 | 20 |  | 20 | 2 |  | 1 | [9 empty] | 3 |  |  |  | 12
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | EM Facilities | 15154 | ENVPLN | 1 | 1.5 |  | 1.5 |  |  | 1 | [9 empty] | 1 |  |  |  | -0.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | EM Facilities | 15154 | ENVSVC | 67 | 4 |  | 4 | [16 empty] | 63
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Gas Locate & Mark North | 15893 | CNSTOT |  | 7.25 |  | 7.25 |  |  |  | 7.25 | [8 empty] | 7.25 |  |  |  | -7.25
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Land Rights | 11929 | Result | 120 | 1.5 |  | 1.5 | [16 empty] | 118.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Land Rights | 11929 | ACQLIT | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Land Rights | 11929 | LNDRTS | 118 | [19 empty] | 118
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | LCE- Division Teams | 15789 | ACTSVC | 55 | 6 |  | 6 |  |  |  | 1 | [8 empty] | 1 |  |  |  | 49
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | North Distribution Control Center | 11890 | MO | 32 | [19 empty] | 32
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Project Management & Controls | 14182 | Result | 3704 | 23.5 | 300 | 323.5 |  |  | 2 | 2.5 | 300 | [7 empty] | 304.5 |  |  |  | 3380.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Project Management & Controls | 14182 | CONSTR | 3576 | 19 | 300 | 319 |  |  |  |  | 300 | [7 empty] | 300 |  |  |  | 3257
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Project Management & Controls | 14182 | ENGMAP | 128 | 4.5 |  | 4.5 |  |  | 2 | 2.5 | [8 empty] | 4.5 |  |  |  | 123.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Reliability Planning | 13549 | Result | 13 | 16 |  | 16 | [16 empty] | -3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Reliability Planning | 13549 | ENGMAP | 12 | 15 |  | 15 | [16 empty] | -3
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | SI Gas Construction | 12055 | CONSTR |  | 3.5 |  | 3.5 |  |  |  | 3.5 | [8 empty] | 3.5 |  |  |  | -3.5
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | SI Restoration | 14110 | FLDSVC | 35 | [19 empty] | 35
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 80 | 80 | [5 empty] | 80 | [6 empty] | 80 |  |  |  | -80
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | VP Elec Distribution Operations | 15443 | MANAGE | 41 | 21 |  | 21 | [16 empty] | 20
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Result |  |  | 3612 | 1086.25 | 780 | 1866.25 | 1 |  | 298.5 | 705 | 780 | [7 empty] | 1784.5 |  |  |  | 1745.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | PGE1/# | # | #
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Business Operations | 15495 | ACTSVC |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | CC Work Force Management | 11034 | MANAGE | 21 | 0.5 |  | 0.5 | [16 empty] | 20.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | EM Facilities | 15154 | Result | 54 | 18.25 |  | 18.25 |  |  | 4 | [9 empty] | 4 |  |  |  | 35.75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | EM Facilities | 15154 | ADMIN | 34 | 13 |  | 13 |  |  | 3 | [9 empty] | 3 |  |  |  | 21
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | EM Facilities | 15154 | ENVPLN | 3 | 5.25 |  | 5.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -2.25
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | EM Facilities | 15154 | ENVSVC | 17 | [19 empty] | 17
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | EM Projects | 15240 | BIOCUL | 1 | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Gas Locate & Mark North | 15893 | CONSTR |  | 0.5 |  | 0.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -0.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | GC Elec SI North | 14632 | Result |  | 915.5 | 700 | 1615.5 |  |  | 248.5 | 667 | 700 | [7 empty] | 1615.5 |  |  |  | -1615.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | GC Elec SI North | 14632 | CNSTDT |  | 5.5 |  | 5.5 |  |  |  | 5.5 | [8 empty] | 5.5 |  |  |  | -5.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | GC Elec SI North | 14632 | CNSTOT |  | 203 |  | 203 |  |  | 61.5 | 141.5 | [8 empty] | 203 |  |  |  | -203
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | GC Elec SI North | 14632 | CONSTR |  | 707 | 700 | 1407 |  |  | 187 | 520 | 700 | [7 empty] | 1407 |  |  |  | -1407
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | GC Elec SI South | 11834 | CONSTR | 3040 | [19 empty] | 3040
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Land Acquisition | 12809 | ACQLIT |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Land Rights | 11929 | Result | 30 | 9.5 |  | 9.5 | [16 empty] | 20.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Land Rights | 11929 | ACQLIT | 30 | 7.5 |  | 7.5 | [16 empty] | 22.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Land Rights | 11929 | LNDRTS |  | 2 |  | 2 | [16 empty] | -2
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | LCE- Division Teams | 15789 | ACTSVC | 129 | 11 |  | 11 | [16 empty] | 118
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | North Distribution Control Center | 11890 | MO | 39 | [19 empty] | 39
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Outage Coordinators & Planners | 12690 | SWTCHO | 9 | [19 empty] | 9
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Project Management & Controls | 14182 | Result | 146 | 96.5 |  | 96.5 |  |  | 45 | 33.5 | [8 empty] | 78.5 |  |  |  | 49.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Project Management & Controls | 14182 | CONSTR | 18 | 93 |  | 93 |  |  | 44 | 31 | [8 empty] | 75 |  |  |  | -75
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Project Management & Controls | 14182 | ENGMAP | 128 | 3.5 |  | 3.5 |  |  | 1 | 2.5 | [8 empty] | 3.5 |  |  |  | 124.5
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Reliability Planning | 13549 | Result | 81 | 5 |  | 5 | [16 empty] | 76
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Reliability Planning | 13549 | ENGMAP | 80 | 4 |  | 4 | [16 empty] | 76
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | SI Gas Construction | 12055 | CONSTR |  | 4 |  | 4 |  |  |  | 4 | [8 empty] | 4 |  |  |  | -4
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | SI Restoration | 14110 | FLDSVC | 43 | [19 empty] | 43
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 80 | 80 |  |  |  |  | 80 | [7 empty] | 80 |  |  |  | -80
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | VP Elec Distribution Operations | 15443 | MANAGE | 19 | 19 |  | 19
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Result |  |  | 3409 | 3726.75 | 680 | 4406.75 | 367 | 229 | 783 | 1397 | 680 | [7 empty] | 3456 |  |  |  | -997.75
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | PGE1/# | # | #
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Business Operations | 15495 | ACTSVC |  | 1.75 |  | 1.75 | [16 empty] | -1.75
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | EM Facilities | 15154 | Result | 40 | 24.5 |  | 24.5 |  |  | 1 | 1 | [8 empty] | 2 |  |  |  | 15.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | EM Facilities | 15154 | ADMIN | 30 | 19 |  | 19 |  |  | 1 | [9 empty] | 1 |  |  |  | 11
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | EM Facilities | 15154 | ENVPLN | 10 | 1.5 |  | 1.5 |  |  |  | 1 | [8 empty] | 1 |  |  |  | 8.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | EM Facilities | 15154 | ENVSVC |  | 4 |  | 4 | [16 empty] | -4
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | GC Elec SI South | 11834 | Result |  | 3136 | 600 | 3736 | 250 | 70 | 759 | 1352.5 | 600 | [7 empty] | 3031.5 |  |  |  | -3736
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | GC Elec SI South | 11834 | CNSTDT |  | 86 |  | 86 |  |  | 21.5 | 64.5 | [8 empty] | 86 |  |  |  | -86
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | GC Elec SI South | 11834 | CNSTOT |  | 295.5 |  | 295.5 |  | 30 | 137.5 | 128 | [8 empty] | 295.5 |  |  |  | -295.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | GC Elec SI South | 11834 | CONSTR |  | 2754.5 | 600 | 3354.5 | 250 | 40 | 600 | 1160 | 600 | [7 empty] | 2650 |  |  |  | -3354.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Land Rights | 11929 | ACQLIT | 32 | 0.5 |  | 0.5 | [16 empty] | 31.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | LCE- Division Teams | 15789 | ACTSVC | 130 | 9 |  | 9 |  |  |  | 1 | [8 empty] | 1 |  |  |  | 121
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | North Distribution Control Center | 11890 | MO | 183 | [19 empty] | 183
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Project Management & Controls | 14182 | Result | 2704 | 527 |  | 527 | 116 | 159 | 23 | 42.5 | [8 empty] | 340.5 |  |  |  | 2177
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Project Management & Controls | 14182 | CNSTOT | 9 | 25 |  | 25 |  | 7 | [10 empty] | 7 |  |  |  | -16
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Project Management & Controls | 14182 | CONSTR | 2567 | 73 |  | 73 |  |  | 18 | 36 | [8 empty] | 54 |  |  |  | 2494
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Project Management & Controls | 14182 | ENGMAP | 128 | 429 |  | 429 | 116 | 152 | 5 | 6.5 | [8 empty] | 279.5 |  |  |  | -301
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Reliability Planning | 13549 | Result | 89 | 5 |  | 5 | [16 empty] | 84
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Reliability Planning | 13549 | ENGMAP | 88 | 4 |  | 4 | [16 empty] | 84
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Reliability Planning | 13549 | ENGMPO | 1 | 1 |  | 1
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Safety Infrastructure Protection Team | 15937 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | SI Restoration | 14110 | FLDSVC | 183 | [19 empty] | 183
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 80 | 80 |  |  |  |  | 80 | [7 empty] | 80 |  |  |  | -80
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Substation Maintenance | 10472 | SWTCHO | 8 | [19 empty] | 8
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | VP Elec Distribution Operations | 15443 | MANAGE | 40 | 21 |  | 21 | [16 empty] | 19
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Result |  |  | 5549 | 4360.5 | 300 | 4660.5 | 437.5 | 565 | 677.5 | 850.5 | 300 | [7 empty] | 2830.5 |  |  |  | 888.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | PGE1/# | # | #
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Business Operations | 15495 | ACTSVC | 1 | 1.75 |  | 1.75 | [16 empty] | -0.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Central Design Contract Estimating | 11714 | EEST |  | 10 |  | 10 | 2 | 2 | 4 | [9 empty] | 8 |  |  |  | -10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Facilities | 15154 | Result | 54 | 45.25 |  | 45.25 |  | 8 | 12 | [9 empty] | 20 |  |  |  | 8.75
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Facilities | 15154 | ADMIN | 13 | 38 |  | 38 |  | 8 | 11 | [9 empty] | 19 |  |  |  | -25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Facilities | 15154 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Facilities | 15154 | ENVPLN | 1 | 6.25 |  | 6.25 |  |  | 1 | [9 empty] | 1 |  |  |  | -5.25
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Facilities | 15154 | ENVSVC | 40 | [19 empty] | 40
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | EM Projects | 15240 | BIOCUL | 2 | 2 |  | 2
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Gas Locate & Mark North | 15893 | CONSTR |  | 4 |  | 4 |  |  | 1 | 3 | [8 empty] | 4 |  |  |  | -4
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Gas Locate & Mark South | 15288 | CONSTR | 20 | [19 empty] | 20
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec NV South | 15216 | Result |  | 91 |  | 91 | [16 empty] | -91
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec NV South | 15216 | CNSTDT |  | 7 |  | 7 | [16 empty] | -7
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec NV South | 15216 | CNSTOT |  | 14 |  | 14 | [16 empty] | -14
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec NV South | 15216 | CONSTR |  | 70 |  | 70 | [16 empty] | -70
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec SI North | 14632 | Result | 5306 | 3854 | 300 | 4154 | 417.5 | 523 | 614.5 | 813 | 300 | [7 empty] | 2668 |  |  |  | 1152
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec SI North | 14632 | CNSTOT |  | 228 |  | 228 | 17.5 | 73 | 24.5 | 43 | [8 empty] | 158 |  |  |  | -228
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | GC Elec SI North | 14632 | CONSTR | 5306 | 3626 | 300 | 3926 | 400 | 450 | 590 | 770 | 300 | [7 empty] | 2510 |  |  |  | 1380
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Land Rights | 11929 | LNDRTS | 30 | 1.5 |  | 1.5 | [16 empty] | 28.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Land Surveying | 12577 | Result | 2 | 1.5 |  | 1.5 | [16 empty] | 0.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Land Surveying | 12577 | LNDENG | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Land Surveying | 12577 | MNGNCC | 1 | 1 |  | 1
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | LCE- Division Teams | 15789 | ACTSVC | 1 | 13 |  | 13 | 3 | 1 | 3 | 2 | [8 empty] | 9 |  |  |  | -12
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | North Distribution Control Center | 11890 | MO | 43 | [19 empty] | 43
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Project Management & Controls | 14182 | Result | 18 | 305.5 |  | 305.5 | 15 | 31 | 42 | 32.5 | [8 empty] | 120.5 |  |  |  | -287.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Project Management & Controls | 14182 | CNSTOT |  | 10 |  | 10 | [16 empty] | -10
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Project Management & Controls | 14182 | CONSTR | 18 | 256 |  | 256 | 15 | 30 | 36 | 27 | [8 empty] | 108 |  |  |  | -238
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Project Management & Controls | 14182 | ENGMAP |  | 39.5 |  | 39.5 |  | 1 | 6 | 5.5 | [8 empty] | 12.5 |  |  |  | -39.5
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Reliability Planning | 13549 | ENGMAP | 3 | 9 |  | 9 |  |  | 1 | [9 empty] | 1 |  |  |  | -6
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | SI Restoration | 14110 | FLDSVC | 47 | [19 empty] | 47
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | VP Elec Distribution Operations | 15443 | MANAGE | 22 | 22 |  | 22
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Result |  |  |  | 586 | 77.87 | 663.87 |  |  |  |  | 4.08 | 4.27 | 4.27 | 4.27 | 4.27 | 4.08 | 4.27 | 4.47 | 33.98 | 43.89 |  |  | -663.87
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | PGE1/# | # | #
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | EM Facilities | 15154 | Result |  | 17 |  | 17 | [16 empty] | -17
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | EM Facilities | 15154 | ADMIN |  | 12 |  | 12 | [16 empty] | -12
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | EM Facilities | 15154 | ENVSVC |  | 5 |  | 5 | [16 empty] | -5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Surveying | 12577 | Result |  | 545 |  | 545 | [16 empty] | -545
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Surveying | 12577 | ACQLIT |  | 170 |  | 170 | [16 empty] | -170
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Surveying | 12577 | ADM-OT |  | 34.5 |  | 34.5 | [16 empty] | -34.5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Surveying | 12577 | LNDENG |  | 132.5 |  | 132.5 | [16 empty] | -132.5
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Land Surveying | 12577 | LNDRTS |  | 208 |  | 208 | [16 empty] | -208
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | LCE- Division Teams | 15789 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 2 |  | 2 | [16 empty] | -2
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Project Management & Controls | 14182 | CNSTOT |  | 4 |  | 4 | [16 empty] | -4
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Reliability Planning | 13549 | ENGMAP |  | 15 |  | 15 | [16 empty] | -15
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40.01 | 40.01 | [13 empty] | 40.01 |  |  | -40.01
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | SLSR:EST Estimating | 12847 | EEST |  |  | 37.86 | 37.86 |  |  |  |  | 4.08 | 4.27 | 4.27 | 4.27 | 4.27 | 4.08 | 4.27 | 4.47 | 33.98 | 3.88 |  |  | -37.86
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Result |  |  |  | 3580 |  | 3580 | 718.5 | 579.25 | 902.25 | 901.25 | [8 empty] | 3101.25 |  |  |  | -3580
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | PGE1/# | # | #
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Business Operations | 15495 | ACTSVC |  | 2.5 |  | 2.5 | [16 empty] | -2.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Central Design Contract Estimating | 11714 | EEST |  | 20 |  | 20 | 13 |  | 7 | [9 empty] | 20 |  |  |  | -20
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Central Design North | 12974 | Result |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Central Design North | 12974 | DSGNDT |  | 15 |  | 15 | [16 empty] | -15
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Central Design North | 12974 | DSGNOT |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | EM Facilities | 15154 | Result |  | 10.75 |  | 10.75 |  |  | 1 | [9 empty] | 1 |  |  |  | -10.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | EM Facilities | 15154 | ADMIN |  | 10 |  | 10 |  |  | 1 | [9 empty] | 1 |  |  |  | -10
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | EM Facilities | 15154 | ENVPLN |  | 0.75 |  | 0.75 | [16 empty] | -0.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 3 |  | 3 | 1 | [11 empty] | 1 |  |  |  | -3
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | GC Elec SI South | 11834 | Result |  | 3425.25 |  | 3425.25 | 702.5 | 578.25 | 887.25 | 857.25 | [8 empty] | 3025.25 |  |  |  | -3425.25
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | GC Elec SI South | 11834 | CNSTDT |  | 95.5 |  | 95.5 |  | 70.25 | 25.25 | [9 empty] | 95.5 |  |  |  | -95.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | GC Elec SI South | 11834 | CNSTOT |  | 742.75 |  | 742.75 | 68.5 | 98 | 263.5 | 172.75 | [8 empty] | 602.75 |  |  |  | -742.75
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | GC Elec SI South | 11834 | CONSTR |  | 2587 |  | 2587 | 634 | 410 | 598.5 | 684.5 | [8 empty] | 2327 |  |  |  | -2587
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Land Rights | 11929 | Result |  | 6.5 |  | 6.5 | [16 empty] | -6.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Land Rights | 11929 | ACQLIT |  | 5.5 |  | 5.5 | [16 empty] | -5.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | LCE- Division Teams | 15789 | ACTSVC |  | 8 |  | 8 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -8
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 11 |  | 11 | [16 empty] | -11
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Permitting G2 and CH2M | 15993 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Project Management & Controls | 14182 | Result |  | 53 |  | 53 |  | 1 | 5 | 43 | [8 empty] | 49 |  |  |  | -53
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Project Management & Controls | 14182 | CONSTR |  | 36 |  | 36 |  |  |  | 36 | [8 empty] | 36 |  |  |  | -36
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Project Management & Controls | 14182 | ENGMAP |  | 17 |  | 17 |  | 1 | 5 | 7 | [8 empty] | 13 |  |  |  | -17
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Reliability Planning | 13549 | ENGMAP |  | 18 |  | 18 | 2 |  | 2 | [9 empty] | 4 |  |  |  | -18
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Result |  |  | 1845 | 115 | 39.99 | 154.99 |  | 1 | [9 empty] | 8.33 | 9.33 | 31.66 |  |  | 1690.01
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | PGE1/# | # | #
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Business Operations | 15495 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Central Design Contract Estimating | 11714 | Result | 22 | 44.25 |  | 44.25 | [16 empty] | -22.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Central Design Contract Estimating | 11714 | EEST | 18 | 40.5 |  | 40.5 | [16 empty] | -22.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Central Design Contract Estimating | 11714 | EESTOT | 4 | 3.75 |  | 3.75 | [16 empty] | 0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | EM Facilities | 15154 | Result | 17 | 9.5 |  | 9.5 | [16 empty] | 7.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | EM Facilities | 15154 | ADMIN | 7 | 9 |  | 9 | [16 empty] | -2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | EM Facilities | 15154 | ENVPLN | 10 | 0.5 |  | 0.5 | [16 empty] | 9.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | EM Projects | 15240 | BIOCUL | 2 | 2 |  | 2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Gas Distribution Projects Contract PCC | 15448 | XCON02 | 1 | 0.5 |  | 0.5 | [16 empty] | 0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | GC Elec SI South | 11834 | CONSTR | 1400 | [19 empty] | 1400
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Grid Operations System Dispatchers | 10481 | SWTCHO | 2 | [19 empty] | 2
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Land Acquisition | 12809 | ACQLIT | 3 | 6.5 |  | 6.5 |  | 1 | [10 empty] | 1 |  |  |  | -3.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Land Rights | 11929 | LNDRTS | 1 | 1.25 |  | 1.25 | [16 empty] | -0.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Land Surveying | 12577 | Result | 48 | 29.75 |  | 29.75 | [16 empty] | 18.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Land Surveying | 12577 | ADM-OT | 1 | 1 |  | 1
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Land Surveying | 12577 | LNDENG | 47 | 28.75 |  | 28.75 | [16 empty] | 18.25
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | LCE- Division Teams | 15789 | ACTSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | North Distribution Control Center | 11890 | MO | 19 | [19 empty] | 19
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Project Management & Controls | 14182 | ENGMAP | 128 | 4 |  | 4 | [16 empty] | 124
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Reliability Planning | 13549 | Result | 81 | 16 |  | 16 | [16 empty] | 65
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Reliability Planning | 13549 | ENGMAP | 7 | 15 |  | 15 | [16 empty] | -8
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Reliability Planning | 13549 | ENGMPO | 74 | 1 |  | 1 | [16 empty] | 73
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | SI Restoration | 14110 | FLDSVC | 121 | [19 empty] | 121
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 39.99 | 39.99 | [11 empty] | 8.33 | 8.33 | 31.66 |  |  | -39.99
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Result |  |  |  | 80.5 |  | 80.5 |  | 1 | 4 | 5 | [8 empty] | 10 |  |  |  | -80.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | PGE1/# | # | #
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Central Design North | 12974 | EESTOT |  | 2 |  | 2 | [16 empty] | -2
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | EM Facilities | 15154 | Result |  | 12 |  | 12 | [16 empty] | -12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | EM Facilities | 15154 | ADMIN |  | 11 |  | 11 | [16 empty] | -11
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | EM Projects | 15240 | BIOCUL |  | 1 |  | 1 | [16 empty] | -1
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Gas Distribution Projects Contract PCC | 15448 | XCON02 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Land Rights | 11929 | Result |  | 22 |  | 22 | [16 empty] | -22
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Land Rights | 11929 | ACQLIT |  | 9 |  | 9 | [16 empty] | -9
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Land Rights | 11929 | LNDRTS |  | 13 |  | 13 | [16 empty] | -13
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | LCE- Division Teams | 15789 | ACTSVC |  | 7 |  | 7 | [16 empty] | -7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | LCE-Engagement Str & Pgrms | 15497 | ACTSVC |  | 6 |  | 6 | [16 empty] | -6
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Project Management & Controls | 14182 | Result |  | 17 |  | 17 |  | 1 | 4 | 5 | [8 empty] | 10 |  |  |  | -17
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Project Management & Controls | 14182 | CNSTOT |  | 7 |  | 7 | [16 empty] | -7
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Project Management & Controls | 14182 | ENGMAP |  | 10 |  | 10 |  | 1 | 4 | 5 | [8 empty] | 10 |  |  |  | -10
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Reliability Planning | 13549 | Result |  | 13 |  | 13 | [16 empty] | -13
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Reliability Planning | 13549 | ENGMAP |  | 12 |  | 12 | [16 empty] | -12
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Reliability Planning | 13549 | ENGMPO |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Result |  |  |  | 319 | 39.99 | 358.99 | 10 | 2 | [10 empty] | 12 | 39.99 |  |  | -358.99
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | PGE1/# | # | #
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Central Design North | 12974 | Result |  | 112.5 |  | 112.5 | [16 empty] | -112.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Central Design North | 12974 | EEST |  | 101.5 |  | 101.5 | [16 empty] | -101.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Central Design North | 12974 | EESTOT |  | 11 |  | 11 | [16 empty] | -11
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | EM Facilities | 15154 | Result |  | 94.75 |  | 94.75 | 6 | 2 | [10 empty] | 8 |  |  |  | -94.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | EM Facilities | 15154 | ADMIN |  | 77 |  | 77 | 6 | 2 | [10 empty] | 8 |  |  |  | -77
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | EM Facilities | 15154 | BIOCUL |  | 8 |  | 8 | [16 empty] | -8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | EM Facilities | 15154 | ENVPLN |  | 9.5 |  | 9.5 | [16 empty] | -9.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Enterprise Public Works Coordination | 15449 | Result |  | 5 |  | 5 | [16 empty] | -5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Enterprise Public Works Coordination | 15449 | ANLYST |  | 4 |  | 4 | [16 empty] | -4
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Land Acquisition | 12809 | ACQLIT |  | 36.5 |  | 36.5 | 4 | [11 empty] | 4 |  |  |  | -36.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Land Rights | 11929 | ACQLIT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Land Surveying | 12577 | Result |  | 13.75 |  | 13.75 | [16 empty] | -13.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Land Surveying | 12577 | LNDENG |  | 12.75 |  | 12.75 | [16 empty] | -12.75
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Land Surveying | 12577 | MNGNCC |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Permitting G2 and CH2M | 15993 | XCON02 |  | 1 |  | 1 | [16 empty] | -1
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Project Management & Controls | 14182 | ENGMAP |  | 8 |  | 8 | [16 empty] | -8
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | Reliability Planning | 13549 | ENGMAP |  | 38 |  | 38 | [16 empty] | -38
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 39.99 | 39.99 | [13 empty] | 39.99 |  |  | -39.99
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | T&D Construct Execution Ops | 15250 | MANAGE |  | 6 |  | 6 | [16 empty] | -6
35145540 | PSPS - FROGTOWN 1702 - CB | Result |  |  |  | 649.75 | 40 | 689.75 | 52 | 30.5 | 14.75 | 7 | [8 empty] | 104.25 | 40 |  |  | -689.75
35145540 | PSPS - FROGTOWN 1702 - CB | PGE1/# | # | #
35145540 | PSPS - FROGTOWN 1702 - CB | Applied Technology Services | 12884 | TECHSV |  | 41.5 |  | 41.5 | 37.5 | 4 | [10 empty] | 41.5 |  |  |  | -41.5
35145540 | PSPS - FROGTOWN 1702 - CB | Capacity Planning | 13550 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35145540 | PSPS - FROGTOWN 1702 - CB | Central Design North | 12974 | GEST |  | 61 |  | 61 | [16 empty] | -61
35145540 | PSPS - FROGTOWN 1702 - CB | EM Facilities | 15154 | Result |  | 29.25 |  | 29.25 | 1.5 | [11 empty] | 1.5 |  |  |  | -29.25
35145540 | PSPS - FROGTOWN 1702 - CB | EM Facilities | 15154 | ADM-OT |  | 1.25 |  | 1.25 | [16 empty] | -1.25
35145540 | PSPS - FROGTOWN 1702 - CB | EM Facilities | 15154 | ADMIN |  | 1 |  | 1 | [16 empty] | -1
35145540 | PSPS - FROGTOWN 1702 - CB | EM Facilities | 15154 | ENVPLN |  | 27 |  | 27 | 1.5 | [11 empty] | 1.5 |  |  |  | -27
35145540 | PSPS - FROGTOWN 1702 - CB | EM Projects | 15240 | ENVPLN |  | 3 |  | 3 | [16 empty] | -3
35145540 | PSPS - FROGTOWN 1702 - CB | Enterprise Public Works Coordination | 15449 | Result |  | 23 |  | 23 | [16 empty] | -23
35145540 | PSPS - FROGTOWN 1702 - CB | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 11 |  | 11 | [16 empty] | -11
35145540 | PSPS - FROGTOWN 1702 - CB | Enterprise Public Works Coordination | 15449 | ANLYST |  | 12 |  | 12 | [16 empty] | -12
35145540 | PSPS - FROGTOWN 1702 - CB | GC & Contractor Construction Management | 15960 | CONSTR |  | 5 |  | 5 |  |  | 5 | [9 empty] | 5 |  |  |  | -5
35145540 | PSPS - FROGTOWN 1702 - CB | GC & Contractor Resource Management | 15976 | MANAGE |  | 5 |  | 5 | [16 empty] | -5
35145540 | PSPS - FROGTOWN 1702 - CB | GD Spvr Bishop Ranch | 15098 | ENGMAP |  | 2 |  | 2 |  | 2 | [10 empty] | 2 |  |  |  | -2
35145540 | PSPS - FROGTOWN 1702 - CB | Integrated Public Affairs | 12245 | ADMIN |  | 21 |  | 21 | 6 | 15 | [10 empty] | 21 |  |  |  | -21
35145540 | PSPS - FROGTOWN 1702 - CB | IT Telecom Maintenance | 13892 | Result |  | 50.5 |  | 50.5 | [16 empty] | -50.5
35145540 | PSPS - FROGTOWN 1702 - CB | IT Telecom Maintenance | 13892 | HRSOT |  | 30 |  | 30 | [16 empty] | -30
35145540 | PSPS - FROGTOWN 1702 - CB | IT Telecom Maintenance | 13892 | HRSST |  | 20.5 |  | 20.5 | [16 empty] | -20.5
35145540 | PSPS - FROGTOWN 1702 - CB | Land Acquisition | 12809 | ACQLIT |  | 34.5 |  | 34.5 | 4 | [11 empty] | 4 |  |  |  | -34.5
35145540 | PSPS - FROGTOWN 1702 - CB | Land Rights | 11929 | ACQLIT |  | 1 |  | 1 | [16 empty] | -1
35145540 | PSPS - FROGTOWN 1702 - CB | Land Surveying | 12577 | Result |  | 335.5 |  | 335.5 | 3 |  | 9.25 | 0.5 | [8 empty] | 12.75 |  |  |  | -335.5
35145540 | PSPS - FROGTOWN 1702 - CB | Land Surveying | 12577 | ACQLIT |  | 50 |  | 50 | 3 | [11 empty] | 3 |  |  |  | -50
35145540 | PSPS - FROGTOWN 1702 - CB | Land Surveying | 12577 | ADM-DT |  | 0.5 |  | 0.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -0.5
35145540 | PSPS - FROGTOWN 1702 - CB | Land Surveying | 12577 | ADM-OT |  | 21.25 |  | 21.25 |  |  | 4.25 | [9 empty] | 4.25 |  |  |  | -21.25
35145540 | PSPS - FROGTOWN 1702 - CB | Land Surveying | 12577 | LNDENG |  | 263.75 |  | 263.75 |  |  | 5 | [9 empty] | 5 |  |  |  | -263.75
35145540 | PSPS - FROGTOWN 1702 - CB | Project Management & Controls | 14182 | Result |  | 16.5 |  | 16.5 |  | 9.5 | 0.5 | 6.5 | [8 empty] | 16.5 |  |  |  | -16.5
35145540 | PSPS - FROGTOWN 1702 - CB | Project Management & Controls | 14182 | CONSTR |  | 13.5 |  | 13.5 |  | 9 |  | 4.5 | [8 empty] | 13.5 |  |  |  | -13.5
35145540 | PSPS - FROGTOWN 1702 - CB | Project Management & Controls | 14182 | ENGMAP |  | 3 |  | 3 |  | 0.5 | 0.5 | 2 | [8 empty] | 3 |  |  |  | -3
35145540 | PSPS - FROGTOWN 1702 - CB | Reliability Planning | 13549 | ENGMAP |  | 19 |  | 19 | [16 empty] | -19
35145540 | PSPS - FROGTOWN 1702 - CB | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | Result |  |  |  | 1 | 80 | 81 | [11 empty] | 8.31 | 8.31 | 71.69 |  |  | -81
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | PGE1/# | # | #
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | Reliability Planning | 13549 | ENGMAP |  | 1 |  | 1 | [16 empty] | -1
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [11 empty] | 8.31 | 8.31 | 31.69 |  |  | -40
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Result |  |  |  | 3 | 80 | 83 | [11 empty] | 21.33 | 21.33 | 58.67 |  |  | -83
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | PGE1/# | # | #
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Gas Locate & Mark Bay Area | 15514 | CONSTR |  | 1 |  | 1 | [16 empty] | -1
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [11 empty] | 21.33 | 21.33 | 18.67 |  |  | -40
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Result |  |  |  | 0.5 | 80 | 80.5 | [13 empty] | 80 |  |  | -80.5
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | PGE1/# | # | #
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Result |  |  |  | 8.75 |  | 8.75 |  |  |  | 6.5 | [8 empty] | 6.5 |  |  |  | -8.75
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | EM Facilities | 15154 | Result |  | 1.25 |  | 1.25 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1.25
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | EM Facilities | 15154 | ADMIN |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | EM Facilities | 15154 | ENVSVC |  | 0.25 |  | 0.25 | [16 empty] | -0.25
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Land Rights | 11929 | LNDRTS |  | 2.5 |  | 2.5 |  |  |  | 2.5 | [8 empty] | 2.5 |  |  |  | -2.5
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35174085 | PSPS - FROGTOWN 1702 - LR 36870 | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Result |  |  |  | 4 | 80 | 84 | [13 empty] | 80 |  |  | -84
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | PGE1/# | # | #
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Central Design North | 12974 | DSGNOT |  | 1 |  | 1 | [16 empty] | -1
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Result |  |  |  | 2.5 | 80 | 82.5 | [13 empty] | 80 |  |  | -82.5
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | PGE1/# | # | #
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | EM Facilities | 15154 | ENVPLN |  | 2 |  | 2 | [16 empty] | -2
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 | [16 empty] | -0.5
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Result |  |  |  | 63.75 | 2256.77 | 2320.52 | 7 | 17.75 | 4.5 | 32 | 296.76 | 296.77 | 272.05 | 229.85 | 375.56 | 522.67 | 263.11 |  | 2318.02 |  |  |  | -2320.52
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | PGE1/# | # | #
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | BLOCKED Proj Svcs - GED PM Concord | 12712 | PRJMGT |  |  | 562.62 | 562.62 |  |  |  |  | 140.66 | 154.72 | 154.72 | 112.52 |  |  |  |  | 562.62 |  |  |  | -562.62
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Central Design North | 12974 | EEST |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Facilities | 15154 | Result |  | 16.5 |  | 16.5 | 2 |  | 3.5 | 11 | [8 empty] | 16.5 |  |  |  | -16.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Facilities | 15154 | ADMIN |  | 7.5 |  | 7.5 |  |  | 3.5 | 4 | [8 empty] | 7.5 |  |  |  | -7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Facilities | 15154 | BIOCUL |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Facilities | 15154 | ENVPLN |  | 8 |  | 8 | 2 |  |  | 6 | [8 empty] | 8 |  |  |  | -8
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Generation | 15171 | BIOCUL |  | 0.5 |  | 0.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -0.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | EM Projects | 15240 | ENVPLN |  | 2 |  | 2 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -2
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Environmental Field Service - BLOCKED | 12634 | ENVSVC |  |  | 639.99 | 639.99 | [5 empty] | 64 | 117.33 | 117.33 | 96 | 224 | 21.33 |  | 639.99 |  |  |  | -639.99
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Land Rights | 11929 | LNDRTS |  | 2.5 |  | 2.5 | 2 | [11 empty] | 2 |  |  |  | -2.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Land Surveying | 12577 | LNDENG |  | 7.5 |  | 7.5 |  | 7.5 | [10 empty] | 7.5 |  |  |  | -7.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Project Management & Controls | 14182 | Result |  | 30 |  | 30 |  | 9.5 | 1 | 19.5 | [8 empty] | 30 |  |  |  | -30
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Project Management & Controls | 14182 | CNSTOT |  | 5 |  | 5 |  |  |  | 5 | [8 empty] | 5 |  |  |  | -5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Project Management & Controls | 14182 | CONSTR |  | 22.5 |  | 22.5 |  | 9 |  | 13.5 | [8 empty] | 22.5 |  |  |  | -22.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Project Management & Controls | 14182 | ENGMAP |  | 2.5 |  | 2.5 |  | 0.5 | 1 | 1 | [8 empty] | 2.5 |  |  |  | -2.5
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Reliability Planning | 13549 | ENGMAP |  | 1.75 |  | 1.75 |  | 0.75 | [10 empty] | 0.75 |  |  |  | -1.75
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 640.01 | 640.01 | [8 empty] | 99.56 | 298.67 | 241.78 |  | 640.01 |  |  |  | -640.01
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | SLSR:EST Estimating | 12847 | EEST |  |  | 234.15 | 234.15 |  |  |  |  | 156.1 | 78.05 | [6 empty] | 234.15 |  |  |  | -234.15
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | Substation Engineering - EA | 15909 | SUBDGN |  |  | 180 | 180 | [8 empty] | 180 |  |  |  | 180 |  |  |  | -180
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Result |  |  |  | 45.5 | 80 | 125.5 | 10 | 25.25 | 1 | 0.75 | 13.33 | 26.67 | [6 empty] | 77 | 40 |  |  | -125.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | PGE1/# | # | #
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Central Design North | 12974 | EEST |  | 7 |  | 7 | 7 | [11 empty] | 7 |  |  |  | -7
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | EM Facilities | 15154 | Result |  | 2 |  | 2 | 1 |  | 1 | [9 empty] | 2 |  |  |  | -2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | EM Facilities | 15154 | ADM-OT |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 | 1 | [11 empty] | 1 |  |  |  | -1
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Land Rights | 11929 | LNDRTS |  | 2 |  | 2 | 2 | [11 empty] | 2 |  |  |  | -2
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Land Surveying | 12577 | Result |  | 3.25 |  | 3.25 |  | 3 |  | 0.25 | [8 empty] | 3.25 |  |  |  | -3.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 3 | [10 empty] | 3 |  |  |  | -3
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Land Surveying | 12577 | ADM-OT |  | 0.25 |  | 0.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -0.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Project Management & Controls | 14182 | ENGMAP |  | 1.5 |  | 1.5 |  | 1 |  | 0.5 | [8 empty] | 1.5 |  |  |  | -1.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Reliability Planning | 13549 | Result |  | 29.75 |  | 29.75 |  | 21.25 | [10 empty] | 21.25 |  |  |  | -29.75
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Reliability Planning | 13549 | ENGMAP |  | 7.25 |  | 7.25 |  | 6.75 | [10 empty] | 6.75 |  |  |  | -7.25
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Reliability Planning | 13549 | ENGMPO |  | 22.5 |  | 22.5 |  | 14.5 | [10 empty] | 14.5 |  |  |  | -22.5
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [13 empty] | 40 |  |  | -40
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 |  |  |  |  | 13.33 | 26.67 | [6 empty] | 40 |  |  |  | -40
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Result |  |  |  | 72.5 | 1787 | 1859.5 | 29.5 | 5.5 | 8 | 28.5 | 20 | 40 | 849 | 858 | 20 |  |  |  | 1858.5 |  |  |  | -1859.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | PGE1/# | # | #
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | EM Facilities | 15154 | ADMIN |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | EM Projects | 15240 | ENVPLN |  | 1.5 |  | 1.5 | 1.5 | [11 empty] | 1.5 |  |  |  | -1.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Enterprise Public Works Coordination | 15449 | ANLYST |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Acquisition | 12809 | ACQLIT |  | 16.5 |  | 16.5 | 3 | 1.5 | 2 | 10 | [8 empty] | 16.5 |  |  |  | -16.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Natural Resource Mgmt | 14178 | VEGMGT |  |  | 20 | 20 | [7 empty] | 20 |  |  |  |  | 20 |  |  |  | -20
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Rights | 11929 | Result |  | 7 |  | 7 | 7 | [11 empty] | 7 |  |  |  | -7
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Rights | 11929 | ADM-OT |  | 4 |  | 4 | 4 | [11 empty] | 4 |  |  |  | -4
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Rights | 11929 | LNDRTS |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Land Surveying | 12577 | LNDENG |  | 14 |  | 14 |  |  | 5 | 9 | [8 empty] | 14 |  |  |  | -14
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | North Distribution Control Center | 11890 | MO |  |  | 26 | 26 | [6 empty] | 13 | 13 |  |  |  |  | 26 |  |  |  | -26
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Project Management & Controls | 14182 | Result |  | 5.5 | 1551 | 1556.5 |  | 1 |  | 4.5 |  |  | 781 | 770 |  |  |  |  | 1556.5 |  |  |  | -1556.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Project Management & Controls | 14182 | CONSTR |  | 4.5 | 1551 | 1555.5 |  |  |  | 4.5 |  |  | 781 | 770 |  |  |  |  | 1555.5 |  |  |  | -1555.5
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Reliability Planning | 13549 | Result |  | 23 | 160 | 183 | 18 | 3 | 1 |  | 20 | 40 | 40 | 40 | 20 |  |  |  | 182 |  |  |  | -183
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Reliability Planning | 13549 | ENGMAP |  | 20 | 160 | 180 | 15 | 3 | 1 |  | 20 | 40 | 40 | 40 | 20 |  |  |  | 179 |  |  |  | -180
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | Reliability Planning | 13549 | ENGMPO |  | 3 |  | 3 | 3 | [11 empty] | 3 |  |  |  | -3
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | SI Restoration | 14110 | FLDSVC |  |  | 30 | 30 | [6 empty] | 15 | 15 |  |  |  |  | 30 |  |  |  | -30
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Result |  |  |  | 238 | 80 | 318 | 1 | 38.5 | 103 | 95.5 |  | 16 | 24 |  |  | 7.92 | 9.17 | 9.58 | 304.67 | 13.33 |  |  | -318
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Land Rights | 11929 | LNDRTS |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Land Surveying | 12577 | Result |  | 223 |  | 223 |  | 25 | 102.5 | 95.5 | [8 empty] | 223 |  |  |  | -223
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Land Surveying | 12577 | ADM-OT |  | 37.5 |  | 37.5 |  | 4 | 23.5 | 10 | [8 empty] | 37.5 |  |  |  | -37.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Land Surveying | 12577 | LNDENG |  | 185.5 |  | 185.5 |  | 21 | 79 | 85.5 | [8 empty] | 185.5 |  |  |  | -185.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Project Management & Controls | 14182 | ENG-OT |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Reliability Planning | 13549 | Result |  | 13 |  | 13 | 1 | 12 | [10 empty] | 13 |  |  |  | -13
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Reliability Planning | 13549 | ENGMAP |  | 2 |  | 2 | 1 | 1 | [10 empty] | 2 |  |  |  | -2
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | Reliability Planning | 13549 | ENGMPO |  | 11 |  | 11 |  | 11 | [10 empty] | 11 |  |  |  | -11
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [9 empty] | 7.92 | 9.17 | 9.58 | 26.67 | 13.33 |  |  | -40
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [5 empty] | 16 | 24 | [5 empty] | 40 |  |  |  | -40
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Result |  |  |  | 185.5 | 76 | 261.5 | 1.5 | 34 | 70 | 80 | 36 |  | 7.08 | 9.17 | 9.17 | 8.75 | 5.83 |  | 261.5 |  |  |  | -261.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | EM Projects | 15240 | ENVPLN |  | 0.5 |  | 0.5 | 0.5 | [11 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Land Rights | 11929 | LNDRTS |  | 0.5 |  | 0.5 |  | 0.5 | [10 empty] | 0.5 |  |  |  | -0.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Land Surveying | 12577 | Result |  | 176 |  | 176 |  | 26 | 70 | 80 | [8 empty] | 176 |  |  |  | -176
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Land Surveying | 12577 | ADM-OT |  | 23.5 |  | 23.5 |  | 2.5 | 16 | 5 | [8 empty] | 23.5 |  |  |  | -23.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Land Surveying | 12577 | LNDENG |  | 152.5 |  | 152.5 |  | 23.5 | 54 | 75 | [8 empty] | 152.5 |  |  |  | -152.5
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Project Management & Controls | 14182 | ENGMAP |  | 1 |  | 1 |  | 1 | [10 empty] | 1 |  |  |  | -1
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Reliability Planning | 13549 | ENGMAP |  | 7 |  | 7 | 1 | 6 | [10 empty] | 7 |  |  |  | -7
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [6 empty] | 7.08 | 9.17 | 9.17 | 8.75 | 5.83 |  | 40 |  |  |  | -40
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | SLSR:EST Estimating | 12847 | EEST |  |  | 36 | 36 |  |  |  |  | 36 | [7 empty] | 36 |  |  |  | -36
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Result |  |  |  | 49 | 80.01 | 129.01 |  | 12 | 17 | 20 | 27.2 | 12.8 | [6 empty] | 89 | 40.01 |  |  | -129.01
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | PGE1/# | # | #
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | EM Facilities | 15154 | ENVPLN |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Land Surveying | 12577 | LNDENG |  | 20 |  | 20 |  | 3 | 17 | [9 empty] | 20 |  |  |  | -20
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | Project Management & Controls | 14182 | CONSTR |  | 26 |  | 26 |  | 9 |  | 17 | [8 empty] | 26 |  |  |  | -26
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40.01 | 40.01 | [13 empty] | 40.01 |  |  | -40.01
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 |  |  |  |  | 27.2 | 12.8 | [6 empty] | 40 |  |  |  | -40
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Result |  |  |  | 24.5 | 80.01 | 104.51 |  | 9 |  | 15.5 | 24 | 16 | [6 empty] | 64.5 | 40.01 |  |  | -104.51
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | PGE1/# | # | #
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | LCE- Division Teams | 15789 | ACTSVC |  | 1.5 |  | 1.5 |  |  |  | 1.5 | [8 empty] | 1.5 |  |  |  | -1.5
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Project Management & Controls | 14182 | Result |  | 22 |  | 22 |  | 9 |  | 13 | [8 empty] | 22 |  |  |  | -22
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Project Management & Controls | 14182 | CNSTOT |  | 4 |  | 4 |  |  |  | 4 | [8 empty] | 4 |  |  |  | -4
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | Project Management & Controls | 14182 | CONSTR |  | 18 |  | 18 |  | 9 |  | 9 | [8 empty] | 18 |  |  |  | -18
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40.01 | 40.01 | [13 empty] | 40.01 |  |  | -40.01
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 |  |  |  |  | 24 | 16 | [6 empty] | 40 |  |  |  | -40
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Result |  |  |  | 13 | 207.33 | 220.33 |  |  | 5.5 | 7.5 | 37.33 | 25 | 24 | 27.14 | 29.25 | 34.47 | 22.14 | 8 | 220.33 |  |  |  | -220.33
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | PGE1/# | # | #
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Central Design Contract Estimating | 11714 | Result |  | 11 | 37 | 48 |  |  | 4.5 | 6.5 |  | 13 | 12 | 12 |  |  |  |  | 48 |  |  |  | -48
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Central Design Contract Estimating | 11714 | EEST |  | 4.5 | 37 | 41.5 |  |  | 4.5 |  |  | 13 | 12 | 12 |  |  |  |  | 41.5 |  |  |  | -41.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Central Design Contract Estimating | 11714 | EESTOT |  | 6.5 |  | 6.5 |  |  |  | 6.5 | [8 empty] | 6.5 |  |  |  | -6.5
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | EM Facilities | 15154 | ENVPLN |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | North Distribution Control Center | 11890 | MO |  |  | 6 | 6 | [9 empty] | 3 | 3 |  | 6 |  |  |  | -6
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Project Management & Controls | 14182 | ENGMAP |  |  | 80 | 80 | [5 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 80 |  |  |  | -80
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | SI Restoration | 14110 | FLDSVC |  |  | 7 | 7 | [9 empty] | 3 | 4 |  | 7 |  |  |  | -7
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [7 empty] | 3.14 | 17.25 | 16.47 | 3.14 |  | 40 |  |  |  | -40
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | SLSR:EST Estimating | 12847 | EEST |  |  | 37.33 | 37.33 |  |  |  |  | 37.33 | [7 empty] | 37.33 |  |  |  | -37.33
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Result |  |  |  | 5 | 79.99 | 84.99 |  | 1.5 | 3.25 | 0.25 |  | 16 | 24 |  |  | 3.33 | 9.17 | 9.58 | 67.08 | 17.91 |  |  | -84.99
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | PGE1/# | # | #
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Land Surveying | 12577 | Result |  | 5 |  | 5 |  | 1.5 | 3.25 | 0.25 | [8 empty] | 5 |  |  |  | -5
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Land Surveying | 12577 | ADM-OT |  | 0.25 |  | 0.25 |  |  |  | 0.25 | [8 empty] | 0.25 |  |  |  | -0.25
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Land Surveying | 12577 | LNDENG |  | 1.75 |  | 1.75 |  |  | 1.75 | [9 empty] | 1.75 |  |  |  | -1.75
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 39.99 | 39.99 | [9 empty] | 3.33 | 9.17 | 9.58 | 22.08 | 17.91 |  |  | -39.99
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | SLSR:EST Estimating | 12847 | EEST |  |  | 40 | 40 | [5 empty] | 16 | 24 | [5 empty] | 40 |  |  |  | -40
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Result |  |  |  | 8.5 | 73.88 | 82.38 |  | 1.5 | 3 | 4 | 11.67 | 12.22 | 10 |  |  | 3.33 | 9.17 | 9.58 | 64.47 | 17.91 |  |  | -82.38
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | PGE1/# | # | #
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Land Surveying | 12577 | Result |  | 7.5 |  | 7.5 |  | 1.5 | 3 | 3 | [8 empty] | 7.5 |  |  |  | -7.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Land Surveying | 12577 | ADM-OT |  | 0.5 |  | 0.5 |  |  |  | 0.5 | [8 empty] | 0.5 |  |  |  | -0.5
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Land Surveying | 12577 | LNDENG |  | 4 |  | 4 |  |  | 1.5 | 2.5 | [8 empty] | 4 |  |  |  | -4
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 39.99 | 39.99 | [9 empty] | 3.33 | 9.17 | 9.58 | 22.08 | 17.91 |  |  | -39.99
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | SLSR:EST Estimating | 12847 | EEST |  |  | 33.89 | 33.89 |  |  |  |  | 11.67 | 12.22 | 10 | [5 empty] | 33.89 |  |  |  | -33.89
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Result |  |  |  | 2.5 | 467 | 469.5 |  |  | 0.5 | 2 | 24 | 62 | 62 | 80 | 81.58 | 80.05 | 57.37 | 20 | 469.5 |  |  |  | -469.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | PGE1/# | # | #
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | EM Facilities | 15154 | ENVPLN |  | 0.5 |  | 0.5 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -0.5
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | North Distribution Control Center | 11890 | MO |  |  | 28 | 28 | [7 empty] | 10 | 10 | 8 |  |  | 28 |  |  |  | -28
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Project Management & Controls | 14182 | ENGMAP |  |  | 320 | 320 | [5 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 20 | 320 |  |  |  | -320
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Reliability Planning | 13549 | ENGMAP |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | SI Restoration | 14110 | FLDSVC |  |  | 31 | 31 | [7 empty] | 10 | 10 | 11 |  |  | 31 |  |  |  | -31
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [7 empty] | 10 | 11.58 | 11.05 | 7.37 |  | 40 |  |  |  | -40
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | SLSR:EST Estimating | 12847 | EEST |  |  | 48 | 48 |  |  |  |  | 24 | 12 | 12 | [5 empty] | 48 |  |  |  | -48
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Result |  |  | 201 | 145.5 |  | 145.5 | [16 empty] | 55.5
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Engineering Operations Support 1 | 10283 | TECHSV |  | 1 |  | 1 | [16 empty] | -1
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Env Mgt Right of Way Encroach BLOCKED | 14407 | ENVPLN |  | 6 |  | 6 | [16 empty] | -6
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GC Gas NV | 11831 | CONSTR | 64 | [19 empty] | 64
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GT Corrosion/TIMP ILI Program Management | 14822 | PRJMGT | 20 | 7 |  | 7 | [16 empty] | 13
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GT Estimating | 10267 | Result | 45 | 13.75 |  | 13.75 | [16 empty] | 31.25
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GT Estimating | 10267 | ESTMOT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GT Estimating | 10267 | ESTSVC | 45 | 11.25 |  | 11.25 | [16 empty] | 33.75
41812476 | LINE 172A MP31.46 EXPOSED PIPE | GT Mapping - A | 10281 | ENGMAP |  | 0.5 |  | 0.5 | [16 empty] | -0.5
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Land Rights - North Valley - BLOCKED | 15046 | LNDRTS | 47 | [19 empty] | 47
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Local T&D Planning Northern, C. Valley | 15108 | PLANSV |  | 2 |  | 2 | [16 empty] | -2
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Pipeline/ILI | 10268 | ENGSVC | 25 | 2.75 |  | 2.75 | [16 empty] | 22.25
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Process&Systems Mgt | 15069 | ANLYST |  | 102 |  | 102 | [16 empty] | -102
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Supervisor GTS Air Water Haz - BLOCKED | 15165 | ENVSVC |  | 4.5 |  | 4.5 | [16 empty] | -4.5
41812476 | LINE 172A MP31.46 EXPOSED PIPE | Supervisor GTS Proj Plan Permit BLOCKED | 15167 | ENVPLN |  | 6 |  | 6 | [16 empty] | -6