## Spend Pivot
Row Labels | Order | Order Name | MAT | AJE | Actuals | Forecast | EAC | Sum of Variance $ (Auth Amt - EAC) | Sum of Jan 2021 Actual Amt | Sum of Feb 2021 Actual Amt | Sum of Mar 2021 Actual Amt | Sum of Apr 2021 Actual Amt | Sum of May 2021 Plan Amt | Sum of Jun 2021 Plan Amt | Sum of Jul 2021 Plan Amt | Sum of Aug 2021 Plan Amt | Sum of Sep 2021 Plan Amt | Sum of Oct 2021 Plan Amt | Sum of Nov 2021 Plan Amt | Sum of Dec 2021 Plan Amt
UNSE | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O |  |  |  | 632006.88 | -632006.88
|  |  | Activity Type Total |  |  |  | 162591.71 | -162591.71
|  |  | Contract Total |  |  |  | 284872.34 | -284872.34
|  |  | Material Total |  |  |  | 4281.63 | -4281.63
|  |  | Order Other Costs |  |  |  | 180261.2 | -180261.2
| 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R |  |  | 20000 | 1218696.08 | -1218696.08
|  |  | Activity Type Total |  |  |  | 126008.48 | -126008.48
|  |  | Contract Total |  |  | 20000 | 812449.77 | -812449.77
|  |  | Material Total |  |  |  | 21111.04 | -21111.04
|  |  | Order Other Costs |  |  |  | 259126.79 | -259126.79
| 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A |  |  | 105.55 | 5414.36 | -5414.36
|  |  | Activity Type Total |  |  |  | 1352.56 | -1352.56
|  |  | Contract Total |  |  |  | 226.04 | -226.04
|  |  | Order Other Costs |  |  | 105.55 | 3835.76 | -3835.76
PEND | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | 150000 |  | 3934687.61 | 3996067.65 | -3846067.65
|  |  | Activity Type Total |  |  | 43300.23 | 48028.2 | -48028.2
|  |  | Contract Total | 150000 |  | 3537740 | 3584459.36 | -3434459.36
|  |  | Material Total |  |  | 169973.58 | 169973.58 | -169973.58
|  |  | Order Other Costs |  |  | 183673.8 | 193606.51 | -193606.51
CONS | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R |  |  | 85000 | 2528867.24 | -2528867.24
|  |  | Activity Type Total |  |  |  | 515302.92 | -515302.92
|  |  | Contract Total |  |  | 85000 | 690027.27 | -690027.27
|  |  | Material Total |  |  |  | 74729.78 | -74729.78
|  |  | Order Other Costs |  |  |  | 1248807.27 | -1248807.27
DOCC | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | 15000 |  | 155000 | 814623.67 | -799623.67
|  |  | Activity Type Total | 15000 |  |  | 167455.49 | -152455.49
|  |  | Contract Total |  |  | 155000 | 332586.67 | -332586.67
|  |  | Material Total |  |  |  | 12860.95 | -12860.95
|  |  | Order Other Costs |  |  |  | 301720.56 | -301720.56
Grand Total |  |  |  | 165000 |  | 4194793.16 | 9195675.88 | -9030675.88

## Sheet1
PM | Status | 31365686 | Used
35112582 | #N/A | 35085549 | Used
35125688 | Used | 35094391 | Used
35135520 | #N/A | 35094396 | Used
35046211 | Used | 35120690 | Used
35050942 | Used | 35157845 | Used
35050951 | Used | 35094394 | Used
35085680 | #N/A | 35094397 | Used
35094389 | #N/A | 31157671 | Used
35094395 | #N/A | 31365686 | Used
31383064 | Used | 31383064 | Used
35026380 | Used | 35085549 | Used
35031040 | Used | 35117061 | Used
35042922 | Used | 35117061 | Used
35109821 | Used | 35120690 | Used
35112572 | #N/A | 35125414 | Used
35125414 | Used | 35125688 | Used
35125681 | #N/A | 35026380 | Used
35125687 | #N/A | 35031040 | Used
35145524 | #N/A | 35042922 | Used
35191385 | #N/A | 35046211 | Used
31157671 | Used | 35050942 | Used
31182216 | #N/A | 35050951 | Used
31276229 | #N/A | 35109821 | Used
31365686 | Used
31474477 | #N/A
35070591 | #N/A
35080162 | #N/A
35085549 | Used
35117061 | Used
31383321 | #N/A
31383323 | #N/A
31383324 | #N/A
35065174 | #N/A
35112581 | #N/A
35152630 | #N/A
31334291 | #N/A
35094391 | Used
35094396 | Used
31474256 | #N/A
31480124 | #N/A
31480127 | #N/A
35120690 | Used
35043296 | #N/A
35094394 | Used
35094397 | Used
35157845 | Used
31258120 | #N/A
31361965 | #N/A
31082390 | #N/A
35072146 | #N/A
35085393 | #N/A
35085532 | #N/A
35085534 | #N/A
35085535 | #N/A
35085536 | #N/A
35085537 | #N/A
35085539 | #N/A
35085681 | #N/A
35094390 | #N/A
74022390 | #N/A
35094388 | #N/A
35085533 | #N/A
35085538 | #N/A
35094392 | #N/A
35094393 | #N/A
31062191 | #N/A
31320428 | #N/A
31320429 | #N/A
35048122 | #N/A
35048276 | #N/A
74022385 | #N/A
35145525 | #N/A

## Summary - Act vs. Auth Amt
PRJ002-PS Forecast Report - Summary To Date
|  |  |  | Total Actual $ | Total Fcst $ | Total EAC $ | Auth Amt (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Total Act $ /Auth Amt) | Total Actual Hrs | Total Fcst Hrs | Total EAC Hrs | Auth Hrs (AJE) | Variance Hrs (Auth Hrs - EAC Hrs) | Variance %
WBS Element Level 2 | Order |  | Cost Element | $ | $ | $ | $ | $ | % | % | HRS | HRS | HRS |  | HRS
Overall Result | [9 empty] | 3030.838 | 12408.37 | 425 | 12833.37 |  | -12833.37 | X
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Order Financial Costs | [6 empty] | 40.92 | 65.25 | 425 | 490.25 |  | -490.25 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | 40.92 | 65.25 | 425 | 490.25 |  | -490.25 | X
|  |  | Activity Type Total | [6 empty] | X | 65.25 | 425 | 490.25 |  | -490.25 | X
Material Total
|  |  | Contract Total | [6 empty] | 31.1462 | [5 empty] | X
|  |  | Order Other Costs | [6 empty] | X
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Order Financial Costs | [6 empty] | X | 1822 |  | 1822 |  | -1822 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | X | 1822 |  | 1822 |  | -1822 | X
|  |  | Activity Type Total | [6 empty] | X | 1822 |  | 1822 |  | -1822 | X
|  |  | Material Total | [6 empty] | X
|  |  | Contract Total | [6 empty] | X | [5 empty] | X
|  |  | Order Other Costs | [6 empty] | X
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Order Financial Costs | [6 empty] | X | 1682.67 |  | 1682.67 |  | -1682.67 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | X | 1682.67 |  | 1682.67 |  | -1682.67 | X
|  |  | Activity Type Total | [6 empty] | X | 1682.67 |  | 1682.67 |  | -1682.67 | X
|  |  | Material Total | [6 empty] | X
|  |  | Contract Total | [6 empty] | X | [5 empty] | X
|  |  | Order Other Costs | [6 empty] | X
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | Order Financial Costs | [6 empty] | X | 21.5 |  | 21.5 |  | -21.5 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | X | 21.5 |  | 21.5 |  | -21.5 | X
|  |  | Activity Type Total | [6 empty] | X | 21.5 |  | 21.5 |  | -21.5 | X
|  |  | Contract Total | [6 empty] | X
|  |  | Order Other Costs | [6 empty] | X
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Order Financial Costs | [6 empty] | X | 6769.35 |  | 6769.35 |  | -6769.35 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | X | 6769.35 |  | 6769.35 |  | -6769.35 | X
|  |  | Activity Type Total | [6 empty] | X | 6769.35 |  | 6769.35 |  | -6769.35 | X
|  |  | Material Total | [6 empty] | X
|  |  | Contract Total | [6 empty] | X | [5 empty] | X
|  |  | Order Other Costs | [6 empty] | X
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Order Financial Costs | [6 empty] | 4397.4911 | 2047.6 |  | 2047.6 |  | -2047.6 | X
|  |  | Orders Costs-Directs & Credits | [6 empty] | 4397.4911 | 2047.6 |  | 2047.6 |  | -2047.6 | X
|  |  | Activity Type Total | [6 empty] | 1116.3699 | 2047.6 |  | 2047.6 |  | -2047.6 | X
|  |  | Material Total | [6 empty] | X | [5 empty] | X
|  |  | Contract Total | [6 empty] | X | [5 empty] | X
|  |  | Order Other Costs | [6 empty] | X | [5 empty] | X

## Monthly Detail - Dollars
PRJ002-PS Monthly Detail - Dollars
| Add Order Name |  |  |  | Add CE#
WBS Element Level 2 | Order | Order Name | MaintActivityType | User Status | Cost Element | CE# | Auth Amt (AJE) | Total Actual Amount | Total Forecast | Total EAC | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | Jan 2022 Fcst Amt | Feb 2022 Fcst Amt | Mar 2022 Fcst Amt | Apr 2022 Fcst Amt | May 2022 Fcst Amt | Jun 2022 Fcst Amt | Jul 2022 Fcst Amt | Sep 2022 Fcst Amt | Oct 2022 Fcst Amt | Nov 2022 Fcst Amt | Dec 2022 Fcst Amt | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt | Variance $ (Auth Amt - EAC)
Overall Result | [6 empty] | 165000 | 5000882.72 | 4194793.16 | 9195675.88 | 11992.92 | 56290.84 | 175224.23 | 515227.49 | 82176.03 | 85112.7 | 256458.65 | 1173061.6 | 1191874.59 | 1187304.34 | 169144.34 | 24660.91 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2000 | 1500 | 1500 | 1500 | 1500 | 25000 |  |  | -9030675.88
E.5034611.01 | Result | [5 empty] | 150000 | 61380.04 | 3934687.61 | 3996067.65 |  | 261.78 | 25743.69 | 35374.57 | 19146.28 | 22082.95 | 238427.95 | 1155046.25 | 1173874.59 | 1169304.34 | 152144.34 | 4660.91 | [14 empty] | -3846067.65
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Order Financial Costs | PGE1ORDFIN | 150000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 150000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Activity Type Total | PGE1ACTV-TOT
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Activity Types | PGE1ACTVTYPES
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Activity Types - Internal | PGE1ACTV-INT
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Construction | 6603001
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Acquisition - Misc | 6603004
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Engineering/Mapping | 6603022
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Land Surveying & Engineering Supprt-Misc | 6603059
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Maintain & Operate Services | 6603083
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Field Services | 6603099
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Electric Estimating | 6603466
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Electric Estimating Overtime | 6603467
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Account Services | 6603730
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Actv Types - T&D Overheads | PGE1ACTV-TY-OH
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Mapping | 6010077
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Material Total | PGE1MATTOTAL
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Material related expenses | PGE1MATERIAL
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Conductors, Cable & Wire Connectors | 5300120
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Electrical Specialties | 5300140
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Material Burden | PGE1MATBURD
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Material Burden | 6010000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Contract Total | PGE1CONTRACT | 150000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Other Contract | PGE1OTHCONTRAC | 150000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Contracts | 5490000 | 150000
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Electric Construction Contract | 5490001
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Construction Inspection | 5490021
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Order Other Costs | PGE1ORD-OTHER
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Other Cost Elements | PGE1OTHERCE
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Permits/Fees | 5501090
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Cost Adjustments Exclude A&G Overhead Bu | 5590044
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Order Overheads | PGE1OVERHEAD
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Capitalized A&G | PGE1CAPAG
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Capitalized A&G | 6010050
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Labor Overheads | PGE1LABOROH
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Paid Time Off | 6010100
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Indirect Labor - Electric | 6010106
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Indirect Labor - Environmental Land | 6010108
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Indirect Labor - Cust Care | 6010110
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Operation Mgmt & Support - Electric | 6010114
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Operation Mgmt & Support - Environ Land | 6010116
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Fleet OH - Elec | 6010125
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Building Service Overhead | 6010112
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | IT Device OH | 6010113
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Other Overhead | PGE1OTHEROH
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Benefits OH | 6010120
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Payroll Taxes OH | 6010121
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | Minor Material OH | 6010122
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | AFUDC Costs | PGE1AFUDCDIR
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | AFUDC-Borrowed | 5590030
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 08W | PEND | AFUDC-Equity | 5590031
N.0000365.01 | Result
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Order Financial Costs | PGE1ORDFIN
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Activity Type Total | PGE1ACTV-TOT
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Activity Types | PGE1ACTVTYPES
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Activity Types - Internal | PGE1ACTV-INT
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Activity Type Cost Adjustment | 5590045
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Env & Land Activity Charge - Type A | 5590105
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Administration | 6603000
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Construction | 6603001
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Acquisition - Misc | 6603004
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Analyst Services | 6603005
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Project Management Services | 6603013
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Construction Overtime Services | 6603021
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Engineering/Mapping | 6603022
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Engineering Services | 6603023
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Environmental Services | 6603024
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Estimating Services | 6603025
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Environmental Planning & Permitting-Misc | 6603027
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Planning Services | 6603048
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Management Services | 6603076
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Maintain & Operate Overtime Services | 6603082
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Maintain & Operate Services | 6603083
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Estimating Overtime Services | 6603105
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Engineering/Mapping Services Overtime | 6603106
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Monitoring/Controlling Services | 6603128
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Administrative Services - OT | 6603150
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Maint & Operate Doubletime Services | 6603181
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Corrosion Service | 6603195
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Land Rights - Misc | 6603227
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Account Services | 6603730
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Manage L&EM | 6603823
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Analyst Svcs Overtime | 6603855
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Activity Types - Contractors | PGE1ACTV-CONTR
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Other Contractor Activity Types | PGE1ACTV-OTH-C
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | PG&E Contractor 2 | 6603832
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contractor Consultant | 6608158
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contractor Engineering | 6608160
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contractor Project Mgmt | 6608163
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contractor Specialist/Services | 6608164
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Material Total | PGE1MATTOTAL
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Material related expenses | PGE1MATERIAL
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Construction Supplies | 5300110
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Gas & Water Specialties | 5300160
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Printed Matls, Signs, Off Suppl & Furn | 5300300
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Material Burden | PGE1MATBURD
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Material Burden | 6010000
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contract Total | PGE1CONTRACT
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Staff Augmentation | PGE1STAFF-AUG
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Staff Augmentation - Labor | 5400000
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Consulting | PGE1CONSULTING
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Consulting Services - Engineering | 5001230
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Consulting Services - Environmental Perm | 5001237
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Consulting Services - Other | 5001250
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Other Contract | PGE1OTHCONTRAC
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Contracts | 5490000
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Gas Construction Contract | 5490002
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Environmental Contract | 5490015
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Construction Inspection | 5490021
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Non Destructive Examination and Testing | 5490025
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Order Other Costs | PGE1ORD-OTHER
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Other Cost Elements | PGE1OTHERCE
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Cash Discount earned | 5006310
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Permits/Fees - Environmental | 5501091
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Other Land Fees | 5501094
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Postage | 5510010
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Employee Related | PGE1EMPLREL
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Travel / Lodging | PGE1TRVL-LODGE
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Employee Travel | 5091115
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Reimbursed Mileage Expense | 5091140
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Meals | PGE1MEALS-EXP
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Meals Expense | 5091100
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Order Overheads | PGE1OVERHEAD
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Capitalized A&G | PGE1CAPAG
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Capitalized A&G | 6010050
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Labor Overheads | PGE1LABOROH
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Paid Time Off | 6010100
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Indirect Labor - Gas | 6010107
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Indirect Labor - Environmental Land | 6010108
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Indirect Labor - Cust Care | 6010110
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Operation Mgmt & Support - Gas | 6010115
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Operation Mgmt & Support - Environ Land | 6010116
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Operation Mgmt & Support - Cust Care | 6010118
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Fleet OH | 6010123
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Building Service Overhead | 6010112
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | IT Device OH | 6010113
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Other Overhead | PGE1OTHEROH
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Benefits OH | 6010120
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Payroll Taxes OH | 6010121
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | Minor Material OH | 6010122
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | AFUDC Costs | PGE1AFUDCDIR
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | AFUDC-Borrowed | 5590030
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | 75O | UNSE | AFUDC-Equity | 5590031
N.0001882.01 | Result
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Order Financial Costs | PGE1ORDFIN
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Activity Type Total | PGE1ACTV-TOT
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Activity Types | PGE1ACTVTYPES
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Activity Types - Internal | PGE1ACTV-INT
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Activity Type Cost Adjustment | 5590045
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Cust. Care Activity Charge - Type A | 5590104
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Construction | 6603001
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Acquisition - Misc | 6603004
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Analyst Services | 6603005
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Project Management Services | 6603013
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Construction Overtime Services | 6603021
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engineering/Mapping | 6603022
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engineering Services | 6603023
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Environmental Services | 6603024
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Environmental Planning & Permitting-Misc | 6603027
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Planning Services | 6603048
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Management Services | 6603076
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Maintain & Operate Overtime Services | 6603082
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Maintain & Operate Services | 6603083
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engineering/Mapping Services Overtime | 6603106
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Monitoring/Controlling Services | 6603128
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engineering Services - OT | 6603148
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Administrative Services - OT | 6603150
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Account Services | 6603730
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Manage L&EM | 6603823
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Analyst Svcs Overtime | 6603855
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Activity Types - Contractors | PGE1ACTV-CONTR
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Contractor Activity Types | PGE1ACTV-OTH-C
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | PG&E Contractor 1 | 6603831
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contractor Consultant | 6608158
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contractor Project Mgmt | 6608163
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contractor Specialist/Services | 6608164
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contractor Inspector/Compliance | 6608192
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Material Total | PGE1MATTOTAL
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Material related expenses | PGE1MATERIAL
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Materials Not Otherwise Classified | 5300000
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Construction Supplies | 5300110
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Conductors, Cable & Wire Connectors | 5300120
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Electrical Specialties | 5300140
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Gas & Water Specialties | 5300160
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engines, Turbines & Waterwheels | 5300250
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Printed Matls, Signs, Off Suppl & Furn | 5300300
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Material Burden | PGE1MATBURD
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Material Burden | 6010000
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contract Total | PGE1CONTRACT
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Staff Augmentation | PGE1STAFF-AUG
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Staff Augmentation - Labor | 5400000
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Consulting | PGE1CONSULTING
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Consulting Services - Environmental Perm | 5001237
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Consulting Services - Other | 5001250
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Contract | PGE1OTHCONTRAC
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Contracts | 5490000
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Gas Construction Contract | 5490002
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Environmental Contract | 5490015
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Construction Inspection | 5490021
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Construction Management Contracts | 5490024
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Non Destructive Examination and Testing | 5490025
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Order Other Costs | PGE1ORD-OTHER
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Cost Elements | PGE1OTHERCE
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Cash Discount earned | 5006310
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Hazardous Waste - Waste Pick-Up Cost | 5040112
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Permits/Fees | 5501090
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Permits/Fees - Environmental | 5501091
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Land Acquisition Services | 5501093
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Land Fees | 5501094
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Postage | 5510010
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Expenses | 5591000
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Employee Related | PGE1EMPLREL
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Travel / Lodging | PGE1TRVL-LODGE
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Employee Travel | 5091115
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Reimbursed Mileage Expense | 5091140
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Lodging | 5091114
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Meals | PGE1MEALS-EXP
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Meals Expense | 5091100
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Order Overheads | PGE1OVERHEAD
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Capitalized A&G | PGE1CAPAG
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Capitalized A&G | 6010050
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Labor Overheads | PGE1LABOROH
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Paid Time Off | 6010100
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Indirect Labor - Gas | 6010107
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Indirect Labor - Environmental Land | 6010108
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Indirect Labor - Cust Care | 6010110
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Operation Mgmt & Support - Gas | 6010115
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Operation Mgmt & Support - Environ Land | 6010116
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Operation Mgmt & Support - Cust Care | 6010118
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Fleet OH | 6010123
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Fleet OH - Gas | 6010126
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Building Service Overhead | 6010112
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | IT Device OH | 6010113
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Other Overhead | PGE1OTHEROH
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Benefits OH | 6010120
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Payroll Taxes OH | 6010121
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | Minor Material OH | 6010122
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | AFUDC Costs | PGE1AFUDCDIR
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | AFUDC-Borrowed | 5590030
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | 75R | UNSE | AFUDC-Equity | 5590031
N.0003410.01 | Result
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Order Financial Costs | PGE1ORDFIN
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Orders Costs-Directs & Credits | PGE1ORDCOSTS
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Activity Type Total | PGE1ACTV-TOT
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Activity Types | PGE1ACTVTYPES
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Activity Types - Internal | PGE1ACTV-INT
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Engineering Services | 6603023
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Environmental Services | 6603024
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Estimating Services | 6603025
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Land Surveying & Engineering Supprt-Misc | 6603059
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Contract Total | PGE1CONTRACT
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Other Contract | PGE1OTHCONTRAC
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Contracts | 5490000
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Spoils & Other OH | PGE1ACTV-SP-OH
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Spoils & Other | 6010088
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Order Other Costs | PGE1ORD-OTHER
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Order Overheads | PGE1OVERHEAD
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Capitalized A&G | PGE1CAPAG
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Capitalized A&G | 6010050
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Labor Overheads | PGE1LABOROH
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Paid Time Off | 6010100
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Indirect Labor - Gas | 6010107
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Indirect Labor - Environmental Land | 6010108
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Operation Mgmt & Support - Gas | 6010115
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Operation Mgmt & Support - Environ Land | 6010116
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Fleet OH | 6010123
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Building Service Overhead | 6010112
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | IT Device OH | 6010113
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Other Overhead | PGE1OTHEROH
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Benefits OH | 6010120
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | Payroll Taxes OH | 6010121
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | AFUDC Costs | PGE1AFUDCDIR
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | AFUDC-Borrowed | 5590030
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | 83A | UNSE | AFUDC-Equity | 5590031
N.0003502.01 | Result
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Order Financial Costs | PGE1ORDFIN
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Orders Costs-Directs & Credits | PGE1ORDCOSTS
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Activity Type Total | PGE1ACTV-TOT
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Activity Types | PGE1ACTVTYPES
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Activity Types - Internal | PGE1ACTV-INT
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | GAS Activity Charge - Type A | 5590101
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Cust. Care Activity Charge - Type A | 5590104
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction | 6603001
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Acquisition - Misc | 6603004
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Analyst Services | 6603005
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Project Management Services | 6603013
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction Overtime Services | 6603021
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Engineering/Mapping | 6603022
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Engineering Services | 6603023
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Environmental Services | 6603024
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Environmental Planning & Permitting-Misc | 6603027
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Planning Services | 6603048
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Technical Services | 6603058
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Land Surveying & Engineering Supprt-Misc | 6603059
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Management Services | 6603076
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Maintain & Operate Overtime Services | 6603082
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Maintain & Operate Services | 6603083
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Planning Overtime Services | 6603114
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Monitoring/Controlling Services | 6603128
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Engineering Services - OT | 6603148
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Administrative Services - OT | 6603150
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction Doubletime Services | 6603180
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Maint & Operate Doubletime Services | 6603181
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Land Rights - Misc | 6603227
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Engineering Doubletime | 6603235
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Environmental Services - OT | 6603252
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Account Services | 6603730
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Manage L&EM | 6603823
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Analyst Svcs Overtime | 6603855
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Certification (Operating Systems) OT | 6603935
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Activity Types - Contractors | PGE1ACTV-CONTR
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Contractor Activity Types | PGE1ACTV-OTH-C
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contractor Activity Charges | 5590114
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contractor Consultant | 6608158
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contractor Project Mgmt | 6608163
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contractor Specialist/Services | 6608164
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contractor Inspector/Compliance | 6608192
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Material Total | PGE1MATTOTAL
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Material related expenses | PGE1MATERIAL
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Automotive | 5300100
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction Supplies | 5300110
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Gas & Water Specialties | 5300160
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Chemicals,Cleaners,Compounds & Lab Suppl | 5300170
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Power Plant Specialties | 5300240
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Tools, First Aid & Safety Supplies | 5300280
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Printed Matls, Signs, Off Suppl & Furn | 5300300
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Freight | 5300320
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Purchasing Card | 5300330
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Material Burden | PGE1MATBURD
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Material Burden | 6010000
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contract Total | PGE1CONTRACT
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Consulting | PGE1CONSULTING
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Consulting Services - Environmental Perm | 5001237
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Consulting Services - Other | 5001250
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Contract | PGE1OTHCONTRAC
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Contracts | 5490000
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Environmental Contract | 5490015
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction Inspection | 5490021
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | As Built Survey Contracts | 5490022
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Construction Management Contracts | 5490024
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Non Destructive Examination and Testing | 5490025
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Traffic Control Contracts | 5490027
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Paving Contracts | 5490500
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Order Other Costs | PGE1ORD-OTHER
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Cost Elements | PGE1OTHERCE
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Cash Discount earned | 5006310
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Rents | 5007000
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Hazardous Waste - Waste Pick-Up Cost | 5040112
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Land Acquisition Services | 5501093
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Land Fees | 5501094
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Postage | 5510010
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Expenses | 5591000
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Employee Related | PGE1EMPLREL
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Travel / Lodging | PGE1TRVL-LODGE
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Reimbursed Mileage Expense | 5091140
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Lodging | 5091114
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Meals | PGE1MEALS-EXP
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Meals Expense | 5091100
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Order Overheads | PGE1OVERHEAD
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Capitalized A&G | PGE1CAPAG
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Capitalized A&G | 6010050
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Labor Overheads | PGE1LABOROH
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Paid Time Off | 6010100
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Indirect Labor - Gas | 6010107
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Indirect Labor - Environmental Land | 6010108
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Indirect Labor - Cust Care | 6010110
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Operation Mgmt & Support - Gas | 6010115
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Operation Mgmt & Support - Environ Land | 6010116
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Operation Mgmt & Support - Cust Care | 6010118
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Fleet OH | 6010123
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Fleet OH - Gas | 6010126
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Building Service Overhead | 6010112
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | IT Device OH | 6010113
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Other Overhead | PGE1OTHEROH
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Benefits OH | 6010120
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Payroll Taxes OH | 6010121
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | Minor Material OH | 6010122
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | AFUDC Costs | PGE1AFUDCDIR
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | AFUDC-Borrowed | 5590030
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | 75R | CONS | AFUDC-Equity | 5590031
# | Result | [5 empty] | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Order Financial Costs | PGE1ORDFIN | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Orders Costs-Directs & Credits | PGE1ORDCOSTS | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Activity Type Total | PGE1ACTV-TOT | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Activity Types | PGE1ACTVTYPES | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Activity Types - Internal | PGE1ACTV-INT | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | ActvTypE Ex Conver, Contractor & OH Actv | PGE1ACTV-TYPE | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Internal Services - Budget | 5600000 | 15000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Administration | 6603000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction | 6603001
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Acquisition - Misc | 6603004
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Analyst Services | 6603005
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Design Drafting Services | 6603006
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Project Management Services | 6603013
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction Overtime Services | 6603021
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Engineering/Mapping | 6603022
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Engineering Services | 6603023
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Environmental Services | 6603024
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Estimating Services | 6603025
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Environmental Planning & Permitting-Misc | 6603027
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Planning Services | 6603048
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Land Surveying & Engineering Supprt-Misc | 6603059
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Management Services | 6603076
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Maintain & Operate Overtime Services | 6603082
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Maintain & Operate Services | 6603083
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Estimating Overtime Services | 6603105
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Engineering/Mapping Services Overtime | 6603106
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Design Drafting Services - Overtime | 6603107
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Monitoring/Controlling Services | 6603128
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Engineering Services - OT | 6603148
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Administrative Services - OT | 6603150
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction Doubletime Services | 6603180
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Corrosion Service | 6603195
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Land Rights - Misc | 6603227
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Environmental Services - OT | 6603252
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Account Services | 6603730
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Analyst Svcs Overtime | 6603855
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Activity Types - Contractors | PGE1ACTV-CONTR
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Other Contractor Activity Types | PGE1ACTV-OTH-C
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contractor Consultant | 6608158
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contractor Engineering | 6608160
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contractor Project Mgmt | 6608163
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contractor Specialist/Services | 6608164
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Material Total | PGE1MATTOTAL
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Material related expenses | PGE1MATERIAL
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Materials Not Otherwise Classified | 5300000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction Supplies | 5300110
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Conductors, Cable & Wire Connectors | 5300120
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Gas & Water Specialties | 5300160
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Material Burden | PGE1MATBURD
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Material Burden - Planning Only | 5501150
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Material Burden | 6010000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contract Total | PGE1CONTRACT
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Consulting | PGE1CONSULTING
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Consulting Services - Environmental Perm | 5001237
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Consulting Services - Computer | 5001240
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Consulting Services - Other | 5001250
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Other Contract | PGE1OTHCONTRAC
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Contracts | 5490000
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Engr/Dsgn and Engr, Proc & Constr Contra | 5490003
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Environmental Contract | 5490015
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction Inspection | 5490021
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | As Built Survey Contracts | 5490022
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Construction Management Contracts | 5490024
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Non Destructive Examination and Testing | 5490025
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Traffic Control Contracts | 5490027
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Order Other Costs | PGE1ORD-OTHER
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Other Cost Elements | PGE1OTHERCE
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Oth Cst Element excl Contingency-5592000 | PGE1OTHERCE1
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Cash Discount earned | 5006310
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Hazardous Waste - Waste Pick-Up Cost | 5040112
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Land Acquisition Services | 5501093
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Other Land Fees | 5501094
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Encroachment Permit Fees | 5501095
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Postage | 5510010
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Forecast Risk - Other Expenses - Plannin | 5591090
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Employee Related | PGE1EMPLREL
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Travel / Lodging | PGE1TRVL-LODGE
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Employee Travel | 5091115
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Reimbursed Mileage Expense | 5091140
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Lodging | 5091114
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Meals | PGE1MEALS-EXP
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Meals Expense | 5091100
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Order Overheads | PGE1OVERHEAD
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Capitalized A&G | PGE1CAPAG
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Capitalized A&G | 6010050
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Labor Overheads | PGE1LABOROH
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Labor Overheads Excl Bldg & IT | PGE1LABOR-XBIT
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Paid Time Off | 6010100
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Indirect Labor - Gas | 6010107
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Indirect Labor - Environmental Land | 6010108
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Indirect Labor - Cust Care | 6010110
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Operation Mgmt & Support - Gas | 6010115
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Operation Mgmt & Support - Environ Land | 6010116
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Fleet OH | 6010123
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Fleet OH - Gas | 6010126
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Building Svcs and IT Device Overheads | PGE1BLDG-IT-OH
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Building Service Overhead | 6010112
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | IT Device OH | 6010113
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Other Overhead | PGE1OTHEROH
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Benefits OH | 6010120
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Payroll Taxes OH | 6010121
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | Minor Material OH | 6010122
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | AFUDC Costs | PGE1AFUDCDIR
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | AFUDC-Borrowed | 5590030
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | 75O | DOCC | AFUDC-Equity | 5590031

## Labor Detail - Dollars
PRJ002-PS Labor Detail - Dollars
[5 empty] | 1995 to 2020 Actual Amt | Jan 2021 Actual Amt | Feb 2021 Actual Amt | Mar 2021 Actual Amt | Apr 2021 Actual Amt | May 2021 Plan Amt | Jun 2021 Plan Amt | Jul 2021 Plan Amt | Aug 2021 Plan Amt | Sep 2021 Plan Amt | Oct 2021 Plan Amt | Nov 2021 Plan Amt | Dec 2021 Plan Amt | 2021 YTD Act Amt | 2021 YTD Actuals + Remaining Plan | Jan 2022 Fcst Amt | Feb 2022 Fcst Amt | Mar 2022 Fcst Amt | Apr 2022 Fcst Amt | May 2022 Fcst Amt | Jun 2022 Fcst Amt | Jul 2022 Fcst Amt | Aug 2022 Fcst Amt | Sep 2022 Fcst Amt | Oct 2022 Fcst Amt | Nov 2022 Fcst Amt | Dec 2022 Fcst Amt | 2022 Fcst Amt | 2023 Fcst Amt | 2024 Fcst Amt | 2025 to 2031 Forecast | Total Actual Amount | Total Forecast | Total EAC | Auth Amt (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Act Since Incep/Auth Amt) | 2021 YTD Plan Amt | YTD Variance (Plan - Act) | Variance %
WBS Element Level 2 | Order |  | Partner CC | Partner Activity | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ | $ |  |  |  | $ | $ | $ | $ | $ | % | % | $ | $ | %
Overall Result
E.5034611.01 | 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | # | #
|  |  | 11674 | #
|  |  | 11714 | EEST
EESTOT
|  |  | 11890 | MO
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
LNDENG
|  |  | 12845 | CONSTR
|  |  | 14110 | FLDSVC
|  |  | 14182 | ENGMAP
|  |  | 14646 | #
|  |  | 15789 | ACTSVC
|  |  | 15960 | CONSTR
|  |  | 16000 | #
|  |  | 16006 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16014 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16035 | #
N.0000365.01 | 74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | # | #
|  |  | 10234 | PLANSV
|  |  | 10267 | ESTMOT
ESTSVC
|  |  | 10268 | ENGSVC
|  |  | 10281 | ENGMAP
ENGMPO
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12108 | MO
MO-DT
MO-OT
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12809 | ACQLIT
ACQRIG
|  |  | 12981 | ADM-OT
LNDRTS
|  |  | 14147 | MONTR
|  |  | 14798 | MANAGE
|  |  | 14799 | CORRSN
|  |  | 14939 | MANAGE
|  |  | 15014 | ENGMAP
|  |  | 15034 | MONTR
|  |  | 15069 | ANLYST
|  |  | 15071 | ENGMAP
|  |  | 15076 | XCON07
XCON08
|  |  | 15078 | CNSTOT
CONSTR
|  |  | 15105 | PCONT2
|  |  | 15142 | ENGSVC
|  |  | 15165 | ADM-OT
ADMIN
ENVSVC
|  |  | 15167 | ENVPLN
|  |  | 15176 | ACQLIT
ACQRIG
LNDRTS
|  |  | 15227 | ENGSVC
|  |  | 15228 | CONSTR
|  |  | 15240 | ADM-OT
ADMIN
ENVPLN
ENVSVC
|  |  | 15246 | ANLYOT
ANLYST
|  |  | 15247 | ANLYST
MANAGE
|  |  | 15249 | ENGSVC
PRJMGT
|  |  | 15287 | MO
|  |  | 15288 | CONSTR
|  |  | 15399 | XCON04
|  |  | 15446 | XCON02
|  |  | 15451 | XCON07
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15818 | ENGSVC
|  |  | 15850 | ADM-OT
LNDRTS
|  |  | 16000 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16036 | #
N.0001882.01 | 74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | # | #
|  |  | 10234 | PLANSV
|  |  | 10281 | ENGMAP
ENGMPO
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11778 | CNSTOT
CONSTR
|  |  | 11783 | MO
MO-OT
|  |  | 11929 | ACQLIT
|  |  | 12002 | #
|  |  | 12108 | MO-OT
|  |  | 12577 | LNDENG
|  |  | 12809 | ACQLIT
ACQRIG
|  |  | 14147 | MONTR
|  |  | 15014 | ENGMAP
ENGMPO
PCONT1
|  |  | 15034 | MONTR
|  |  | 15049 | ENG-OT
ENGSVC
|  |  | 15054 | ENGSVC
|  |  | 15071 | ENGMAP
|  |  | 15076 | XCON07
XCON08
XCON10
|  |  | 15078 | CNSTOT
CONSTR
|  |  | 15142 | ENGSVC
|  |  | 15227 | ENG-OT
ENGSVC
|  |  | 15228 | CNSTOT
CONSTR
|  |  | 15237 | MANAGE
|  |  | 15240 | ADM-OT
BIOCUL
ENVPLN
ENVSVC
|  |  | 15246 | ANLYOT
ANLYST
|  |  | 15249 | ENGSVC
PRJMGT
|  |  | 15446 | XCON02
|  |  | 15449 | ANLYOT
ANLYST
|  |  | 15451 | XCON07
|  |  | 15452 | XCON07
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15818 | ENG-OT
ENGSVC
|  |  | 15826 | ENGMAP
|  |  | 16000 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16036 | #
N.0003410.01 | 74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | # | #
|  |  | 10268 | ENGSVC
|  |  | 12002 | #
|  |  | 12577 | LNDENG
|  |  | 15227 | ENGSVC
|  |  | 15240 | ENVSVC
|  |  | 15361 | ESTSVC
|  |  | 15892 | #
|  |  | 16000 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16036 | #
N.0003502.01 | 74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | # | #
|  |  | 10234 | PLANSV
PLNGOT
|  |  | 10268 | ENGSVC
|  |  | 10281 | ENGMAP
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11843 | CNSTDT
CNSTOT
CONSTR
|  |  | 11929 | ACQLIT
LNDRTS
|  |  | 12002 | #
|  |  | 12209 | MO
MO-DT
MO-OT
|  |  | 12577 | ADM-OT
LNDENG
|  |  | 12809 | ACQLIT
ADM-OT
|  |  | 12884 | TECHSV
|  |  | 13696 | ENGSVC
|  |  | 14147 | MONTR
|  |  | 14861 | CONSTR
|  |  | 14862 | MANAGE
|  |  | 14944 | CONSTR
|  |  | 15018 | ENGSVC
|  |  | 15036 | TESTOT
|  |  | 15049 | ENGSVC
|  |  | 15053 | CNSTDT
CNSTOT
CONSTR
|  |  | 15071 | ENGMAP
|  |  | 15076 | XCON07
XCON08
XCON10
|  |  | 15098 | ENGMAP
|  |  | 15103 | CNSTOT
CONSTR
|  |  | 15184 | CNSTDT
CNSTOT
CONSTR
|  |  | 15227 | ENGSVC
|  |  | 15228 | CNSTDT
CNSTOT
CONSTR
|  |  | 15237 | MANAGE
|  |  | 15240 | ADM-OT
BIOCUL
ENVPLN
ENVSOT
ENVSVC
|  |  | 15245 | ENG-OT
ENGSVC
|  |  | 15246 | ANLYOT
ANLYST
|  |  | 15249 | ENGSVC
PRJMGT
|  |  | 15287 | MO
|  |  | 15301 | MANAGE
|  |  | 15352 | CNSTDT
CNSTOT
CONSTR
ENG-OT
ENGSVC
|  |  | 15446 | XCON02
|  |  | 15449 | ANLYST
|  |  | 15451 | XCON07
XCON08
|  |  | 15452 | XCON07
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15818 | ENG-DT
ENG-OT
ENGSVC
|  |  | 15826 | ENG-OT
ENGMAP
|  |  | 16000 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16026 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16036 | #
# | 30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | # | #
|  |  | 10234 | PLANSV
|  |  | 10267 | ESTMOT
ESTSVC
|  |  | 10268 | ENGSVC
|  |  | 10281 | ENGMAP
ENGMPO
|  |  | 11034 | MANAGE
|  |  | 11674 | #
|  |  | 11847 | CONSTR
|  |  | 11929 | ACQLIT
|  |  | 11937 | MO
MO-OT
|  |  | 12002 | #
|  |  | 12577 | ACQLIT
ADM-OT
LNDENG
LNDRTS
|  |  | 12809 | ACQLIT
|  |  | 13696 | ENGSVC
|  |  | 14147 | MONTR
|  |  | 14799 | CORRSN
|  |  | 14822 | PRJMGT
|  |  | 14861 | CNSTOT
CONSTR
|  |  | 15013 | MANAGE
|  |  | 15069 | ANLYST
|  |  | 15071 | ENGMAP
|  |  | 15076 | XCON08
|  |  | 15103 | CNSTOT
CONSTR
|  |  | 15167 | ENVPLN
|  |  | 15184 | CNSTDT
|  |  | 15227 | ENGSVC
|  |  | 15228 | CNSTOT
CONSTR
|  |  | 15240 | ADMIN
ENVPLN
ENVSOT
ENVSVC
|  |  | 15246 | ANLYOT
ANLYST
|  |  | 15249 | ENGSVC
|  |  | 15361 | DRFT
DRFTOT
|  |  | 15446 | XCON02
|  |  | 15449 | ANLYST
|  |  | 15451 | XCON04
XCON07
XCON08
|  |  | 15452 | XCON02
XCON07
|  |  | 15495 | ACTSVC
|  |  | 15789 | ACTSVC
|  |  | 15818 | ENG-OT
ENGSVC
|  |  | 16000 | #
|  |  | 16007 | #
|  |  | 16008 | #
|  |  | 16010 | #
|  |  | 16012 | #
|  |  | 16013 | #
|  |  | 16017 | #
|  |  | 16020 | #
|  |  | 16032 | #
|  |  | 16033 | #
|  |  | 16034 | #
|  |  | 16036 | #
|  |  | 18024 | ENG-OT
ENGSVC

## Summary - Act vs. Fcst
PRJ002-PS Forecast Report - Summary FAC
Order |  | User Status | Job Owner | MaintActivityType | WBS Element Level 2 | Planning Order | Total Actual $ | 2021 Remaining Plan $(PRJ) | FYR Fcst $(PRJ) 2022 | Total Fcst $ | Total EAC $ | Auth Amt (AJE) | Contingency | Auth Amt w/ Contin (AJE) | Variance $ (Auth Amt - EAC) | Variance % | % Spent (Total Act $ /Auth Amt) | Auth Hrs (AJE) | Total Actual Hrs | Total Fcst Hrs | Total EAC Hrs | Variance Hrs (Auth Hrs - EAC Hrs) | Variance %
Overall Result | [18 empty] | 12408.37 | 425 | 12833.37 | -12833.37 | X | #REF!
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | DOCC |  | 75O | # | 5751708 | [12 empty] | 2047.6 |  | 2047.6 | -2047.6 | X | #REF!
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | PEND |  | 08W | E.5034611.01 | 5794204 | [12 empty] | 65.25 | 425 | 490.25 | -490.25 | X | #REF!
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | UNSE |  | 75O | N.0000365.01 | 5771024 | [12 empty] | 1822 |  | 1822 | -1822 | X | #REF!
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | UNSE |  | 75R | N.0001882.01 | 5778230 | [12 empty] | 1682.67 |  | 1682.67 | -1682.67 | X | #REF!
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | UNSE |  | 83A | N.0003410.01 | 5784759 | [12 empty] | 21.5 |  | 21.5 | -21.5 | X | #REF!
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | CONS |  | 75R | N.0003502.01 | 5785089 | [12 empty] | 6769.35 |  | 6769.35 | -6769.35 | X | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Labor Detail - Hrs
PRJ002 - PS Labor Detail - Hours
Order |  | Partner CC |  | Partner Activity | Auth Hrs (AJE) | Total Actual Hours | Total Forecast | Total EAC | Jan 2021 Actual Hrs | Feb 2021 Actual Hrs | Mar 2021 Actual Hrs | Apr 2021 Actual Hrs | May 2021 Plan Hrs | Jun 2021 Plan Hrs | Jul 2021 Plan Hrs | Aug 2021 Plan Hrs | Sep 2021 Plan Hrs | Oct 2021 Plan Hrs | Nov 2021 Plan Hrs | Dec 2021 Plan Hrs | 2021 YTD Actuals + Remaining Plan | 2022 Fcst Hrs | 2023 Fcst Hrs | 2024 Fcst Hrs | Variance Hrs (Auth Hrs - EAC Hrs)
Overall Result | [5 empty] | 12408.37 | 425 | 12833.37 | 23.9 | 249.55 | 297.26 | 1316.01 |  | 50 | 50 | 80.77 | 86.92 | 82.31 | 55 | 20 | 2311.72 |  |  |  | -12833.37
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Result |  |  |  | 2047.6 |  | 2047.6 | 13.4 | 69.05 | 270.25 | 1256.5 | [8 empty] | 1609.2 |  |  |  | -2047.6
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | PGE1/# | # | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Benefits Overhead Credit | 16032 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Building Services OH Credit | 16012 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Business Operations | 15495 | ACTSVC |  | 3.75 |  | 3.75 |  |  | 3.75 | [9 empty] | 3.75 |  |  |  | -3.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | CC Work Force Management | 11034 | MANAGE |  | 1 |  | 1 |  |  | 1 | [9 empty] | 1 |  |  |  | -1
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | CM/Insp - Central Valley | 15103 | Result |  | 12 |  | 12 | 1 | 3 | [10 empty] | 4 |  |  |  | -12
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | CM/Insp - Central Valley | 15103 | CNSTOT |  | 3 |  | 3 |  | 3 | [10 empty] | 3 |  |  |  | -3
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | CM/Insp - Central Valley | 15103 | CONSTR |  | 9 |  | 9 | 1 | [11 empty] | 1 |  |  |  | -9
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Corrosion Engineering | 14799 | CORRSN |  | 2 |  | 2 | [16 empty] | -2
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | EM Projects | 15240 | Result |  | 24 |  | 24 | 2.5 | 0.5 | 8.5 | 5.25 | [8 empty] | 16.75 |  |  |  | -24
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | EM Projects | 15240 | ADMIN |  | 1 |  | 1 | [16 empty] | -1
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | EM Projects | 15240 | ENVPLN |  | 3 |  | 3 | [16 empty] | -3
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | EM Projects | 15240 | ENVSOT |  | 4.25 |  | 4.25 | 1 |  | 3.25 | [9 empty] | 4.25 |  |  |  | -4.25
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | EM Projects | 15240 | ENVSVC |  | 15.75 |  | 15.75 | 1.5 | 0.5 | 5.25 | 5.25 | [8 empty] | 12.5 |  |  |  | -15.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Encroachment Contractor - CH2M Hill | 15076 | XCON08 |  | 9.5 |  | 9.5 | [16 empty] | -9.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Engineering Operations Support 3 | 15013 | MANAGE |  | 19 |  | 19 | [16 empty] | -19
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Enterprise Public Works Coordination | 15449 | ANLYST |  | 12.25 |  | 12.25 |  |  |  | 8 | [8 empty] | 8 |  |  |  | -12.25
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Field Quality Control | 18024 | Result |  | 32 |  | 32 |  |  |  | 32 | [8 empty] | 32 |  |  |  | -32
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Field Quality Control | 18024 | ENG-OT |  | 1.5 |  | 1.5 |  |  |  | 1.5 | [8 empty] | 1.5 |  |  |  | -1.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Field Quality Control | 18024 | ENGSVC |  | 30.5 |  | 30.5 |  |  |  | 30.5 | [8 empty] | 30.5 |  |  |  | -30.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Gas Control Clearance Coordinators | 14147 | MONTR |  | 4.5 |  | 4.5 |  |  | 0.5 | 4 | [8 empty] | 4.5 |  |  |  | -4.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GC Gas YO | 11847 | CONSTR |  | 10 |  | 10 |  |  |  | 10 | [8 empty] | 10 |  |  |  | -10
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GD Map SF/San Raf | 15071 | ENGMAP |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Corrosion/TIMP ILI Program Management | 14822 | PRJMGT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Est - Strength Test | 15361 | Result |  | 20 |  | 20 |  | 2 | 5 | [9 empty] | 7 |  |  |  | -20
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Est - Strength Test | 15361 | DRFT |  | 15 |  | 15 |  | 1 | 3 | [9 empty] | 4 |  |  |  | -15
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Est - Strength Test | 15361 | DRFTOT |  | 5 |  | 5 |  | 1 | 2 | [9 empty] | 3 |  |  |  | -5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Estimating | 10267 | Result |  | 47 |  | 47 | [16 empty] | -47
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Estimating | 10267 | ESTMOT |  | 5 |  | 5 | [16 empty] | -5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Estimating | 10267 | ESTSVC |  | 42 |  | 42 | [16 empty] | -42
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Central Construction | 14861 | Result |  | 965 |  | 965 |  |  | 140 | 825 | [8 empty] | 965 |  |  |  | -965
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Central Construction | 14861 | CNSTOT |  | 147.5 |  | 147.5 |  |  | 20 | 127.5 | [8 empty] | 147.5 |  |  |  | -147.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Central Construction | 14861 | CONSTR |  | 817.5 |  | 817.5 |  |  | 120 | 697.5 | [8 empty] | 817.5 |  |  |  | -817.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Engineering | 15818 | Result |  | 123 |  | 123 |  | 7 | 5 | 111 | [8 empty] | 123 |  |  |  | -123
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Engineering | 15818 | ENG-OT |  | 23 |  | 23 |  |  | 5 | 18 | [8 empty] | 23 |  |  |  | -23
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT GC South Engineering | 15818 | ENGSVC |  | 100 |  | 100 |  | 7 |  | 93 | [8 empty] | 100 |  |  |  | -100
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT ILI Program Mgmt Contr | 15452 | Result |  | 23 |  | 23 |  |  |  | 23 | [8 empty] | 23 |  |  |  | -23
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT ILI Program Mgmt Contr | 15452 | XCON02 |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT ILI Program Mgmt Contr | 15452 | XCON07 |  | 22 |  | 22 |  |  |  | 22 | [8 empty] | 22 |  |  |  | -22
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Mapping - A | 10281 | Result |  | 2.75 |  | 2.75 |  |  | 0.75 | 2 | [8 empty] | 2.75 |  |  |  | -2.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Mapping - A | 10281 | ENGMAP |  | 0.75 |  | 0.75 |  |  | 0.75 | [9 empty] | 0.75 |  |  |  | -0.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Mapping - A | 10281 | ENGMPO |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Pipe Program Mgmt Contr | 15451 | Result |  | 217.6 |  | 217.6 | 0.9 | 40.3 | 44 | 24 | [8 empty] | 109.2 |  |  |  | -217.6
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Pipe Program Mgmt Contr | 15451 | XCON04 |  | 5 |  | 5 |  |  |  | 5 | [8 empty] | 5 |  |  |  | -5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Pipe Program Mgmt Contr | 15451 | XCON07 |  | 209 |  | 209 |  | 40 | 44 | 18 | [8 empty] | 102 |  |  |  | -209
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Pipe Program Mgmt Contr | 15451 | XCON08 |  | 3.6 |  | 3.6 | 0.9 | 0.3 |  | 1 | [8 empty] | 2.2 |  |  |  | -3.6
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GT Project Management | 15249 | ENGSVC |  | 6.5 |  | 6.5 |  | 1 | 0.5 | [9 empty] | 1.5 |  |  |  | -6.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | GTTapping Crews/Equipment/Trucks | 15184 | CNSTDT |  | 25 |  | 25 |  |  |  | 25 | [8 empty] | 25 |  |  |  | -25
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | IT Device OH Credit | 16013 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Acquisition | 12809 | ACQLIT |  | 13 |  | 13 | 4 | [11 empty] | 4 |  |  |  | -13
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Rights | 11929 | ACQLIT |  | 1 |  | 1 | [16 empty] | -1
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Surveying | 12577 | Result |  | 48 |  | 48 |  | 1.5 | [10 empty] | 1.5 |  |  |  | -48
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Surveying | 12577 | ACQLIT |  | 31 |  | 31 | [16 empty] | -31
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Surveying | 12577 | ADM-OT |  | 3.5 |  | 3.5 | [16 empty] | -3.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Surveying | 12577 | LNDENG |  | 8 |  | 8 |  | 1.5 | [10 empty] | 1.5 |  |  |  | -8
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Land Surveying | 12577 | LNDRTS |  | 5.5 |  | 5.5 | [16 empty] | -5.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | LCE- Division Teams | 15789 | ACTSVC |  | 4 |  | 4 |  |  | 3 | 1 | [8 empty] | 4 |  |  |  | -4
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | LT&D Planning | 10234 | PLANSV |  | 4.25 |  | 4.25 | 0.5 | 1.75 | 1.5 | [9 empty] | 3.75 |  |  |  | -4.25
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Materials Burden | 11674 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Measurement/Reg | 13696 | ENGSVC |  | 8 |  | 8 | [16 empty] | -8
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Minor Material Overhead Credit | 16034 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Payroll Taxes Overhead Credit | 16033 | #
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Pipeline Services | 15227 | ENGSVC |  | 3.5 |  | 3.5 |  |  | 1.5 | 0.5 | [8 empty] | 2 |  |  |  | -3.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Pipeline/ILI | 10268 | ENGSVC |  | 162.5 |  | 162.5 | 3 | 9 | 19 | 29 | [8 empty] | 60 |  |  |  | -162.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Process&Systems Mgt | 15069 | ANLYST |  | 9 |  | 9 | [16 empty] | -9
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | Result |  | 135.75 |  | 135.75 |  |  | 7.5 | 128.25 | [8 empty] | 135.75 |  |  |  | -135.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CNSTOT |  | 11.25 |  | 11.25 |  |  | 0.5 | 10.75 | [8 empty] | 11.25 |  |  |  | -11.25
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CONSTR |  | 124.5 |  | 124.5 |  |  | 7 | 117.5 | [8 empty] | 124.5 |  |  |  | -124.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Project Controls | 15246 | Result |  | 52.75 |  | 52.75 | 1.5 | 3 | 28.75 | [9 empty] | 33.25 |  |  |  | -52.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Project Controls | 15246 | ANLYOT |  | 9.75 |  | 9.75 | 1 | 1.5 | 5.25 | [9 empty] | 7.75 |  |  |  | -9.75
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Project Controls | 15246 | ANLYST |  | 43 |  | 43 | 0.5 | 1.5 | 23.5 | [9 empty] | 25.5 |  |  |  | -43
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Project Ctrl-Contr | 15446 | XCON02 |  | 11 |  | 11 |  |  |  | 5 | [8 empty] | 5 |  |  |  | -11
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | ST Gas T&R | 11937 | Result |  | 29.5 |  | 29.5 |  |  |  | 21.5 | [8 empty] | 21.5 |  |  |  | -29.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | ST Gas T&R | 11937 | MO |  | 24 |  | 24 |  |  |  | 16 | [8 empty] | 16 |  |  |  | -24
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | ST Gas T&R | 11937 | MO-OT |  | 5.5 |  | 5.5 |  |  |  | 5.5 | [8 empty] | 5.5 |  |  |  | -5.5
30931157 | A-294 GCUST 5843 DEACTIVATION DEL MONTE | Supervisor GTS Proj Plan Permit BLOCKED | 15167 | ENVPLN |  | 1 |  | 1 | [16 empty] | -1
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Result |  |  |  | 65.25 | 425 | 490.25 |  | 1.5 | 5.25 | 58.5 |  | 50 | 50 | 80.77 | 86.92 | 82.31 | 55 | 20 | 490.25 |  |  |  | -490.25
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | PGE1/# | # | #
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Central Design Contract Estimating | 11714 | Result |  | 57.5 |  | 57.5 |  |  | 2 | 55.5 | [8 empty] | 57.5 |  |  |  | -57.5
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Central Design Contract Estimating | 11714 | EEST |  | 39.5 |  | 39.5 |  |  |  | 39.5 | [8 empty] | 39.5 |  |  |  | -39.5
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Central Design Contract Estimating | 11714 | EESTOT |  | 18 |  | 18 |  |  | 2 | 16 | [8 empty] | 18 |  |  |  | -18
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | GC & Contractor Construction Management | 15960 | CONSTR |  | 2 |  | 2 |  |  |  | 2 | [8 empty] | 2 |  |  |  | -2
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Land Surveying | 12577 | Result |  | 4.75 |  | 4.75 |  | 1.5 | 3.25 | [9 empty] | 4.75 |  |  |  | -4.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Land Surveying | 12577 | ACQLIT |  | 3 |  | 3 |  | 1.5 | 1.5 | [9 empty] | 3 |  |  |  | -3
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Land Surveying | 12577 | LNDENG |  | 1.75 |  | 1.75 |  |  | 1.75 | [9 empty] | 1.75 |  |  |  | -1.75
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | LCE- Division Teams | 15789 | ACTSVC |  | 1 |  | 1 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -1
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | North Distribution Control Center | 11890 | MO |  |  | 31 | 31 | [7 empty] | 10 | 10 | 10 | 1 |  | 31 |  |  |  | -31
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Project Management & Controls | 14182 | ENGMAP |  |  | 320 | 320 | [5 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 20 | 320 |  |  |  | -320
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | SI Restoration | 14110 | FLDSVC |  |  | 34 | 34 | [7 empty] | 10 | 10 | 10 | 4 |  | 34 |  |  |  | -34
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | SLSR:D-GCE Dist GC Electric | 12845 | CONSTR |  |  | 40 | 40 | [7 empty] | 10.77 | 16.92 | 12.31 |  |  | 40 |  |  |  | -40
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Result |  |  |  | 1822 |  | 1822 | [16 empty] | -1822
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | PGE1/# | # | #
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Business Operations | 15495 | ACTSVC |  | 3 |  | 3 | [16 empty] | -3
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | CC Work Force Management | 11034 | MANAGE |  | 0.5 |  | 0.5 | [16 empty] | -0.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Central Land Services - BLOCKED | 15850 | Result |  | 2.5 |  | 2.5 | [16 empty] | -2.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Central Land Services - BLOCKED | 15850 | ADM-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Central Land Services - BLOCKED | 15850 | LNDRTS |  | 1 |  | 1 | [16 empty] | -1
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | CH2M Hill Contract - BLOCKED | 15399 | XCON04 |  | 3.5 |  | 3.5 | [16 empty] | -3.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | CM/Insp - Central Coast | 15078 | Result |  | 93.5 |  | 93.5 | [16 empty] | -93.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | CM/Insp - Central Coast | 15078 | CNSTOT |  | 9 |  | 9 | [16 empty] | -9
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | CM/Insp - Central Coast | 15078 | CONSTR |  | 84.5 |  | 84.5 | [16 empty] | -84.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Corrosion Engineering | 14799 | CORRSN |  | 2 |  | 2 | [16 empty] | -2
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | DA Gas T&R | 12108 | Result |  | 93.5 |  | 93.5 | [16 empty] | -93.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | DA Gas T&R | 12108 | MO |  | 70 |  | 70 | [16 empty] | -70
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | DA Gas T&R | 12108 | MO-DT |  | 4 |  | 4 | [16 empty] | -4
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | DA Gas T&R | 12108 | MO-OT |  | 19.5 |  | 19.5 | [16 empty] | -19.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | EM Projects | 15240 | Result |  | 61.5 |  | 61.5 | [16 empty] | -61.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | EM Projects | 15240 | ADM-OT |  | 4 |  | 4 | [16 empty] | -4
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | EM Projects | 15240 | ADMIN |  | 1 |  | 1 | [16 empty] | -1
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | EM Projects | 15240 | ENVPLN |  | 30 |  | 30 | [16 empty] | -30
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | EM Projects | 15240 | ENVSVC |  | 26.5 |  | 26.5 | [16 empty] | -26.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Encroachment Contractor - CH2M Hill | 15076 | Result |  | 50 |  | 50 | [16 empty] | -50
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Encroachment Contractor - CH2M Hill | 15076 | XCON07 |  | 41 |  | 41 | [16 empty] | -41
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Encroachment Contractor - CH2M Hill | 15076 | XCON08 |  | 9 |  | 9 | [16 empty] | -9
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Gas Control Clearance Coordinators | 14147 | MONTR |  | 3 |  | 3 | [16 empty] | -3
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Gas Corrosion South | 15287 | MO |  | 2 |  | 2 | [16 empty] | -2
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Gas Locate & Mark South | 15288 | CONSTR |  | 1 |  | 1 | [16 empty] | -1
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GD Map SF/San Raf | 15071 | ENGMAP |  | 2 |  | 2 | [16 empty] | -2
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GSO Strategy and Support | 15034 | MONTR |  | 1.75 |  | 1.75 | [16 empty] | -1.75
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT CM Inspection Contractor | 15105 | PCONT2 |  | 168 |  | 168 | [16 empty] | -168
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT E&D Director | 14798 | MANAGE |  | 1 |  | 1 | [16 empty] | -1
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Estimating | 10267 | Result |  | 98 |  | 98 | [16 empty] | -98
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Estimating | 10267 | ESTMOT |  | 18.5 |  | 18.5 | [16 empty] | -18.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Estimating | 10267 | ESTSVC |  | 79.5 |  | 79.5 | [16 empty] | -79.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT GC South Engineering | 15818 | ENGSVC |  | 5 |  | 5 | [16 empty] | -5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Mapping - A | 10281 | Result |  | 50.5 |  | 50.5 | [16 empty] | -50.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Mapping - A | 10281 | ENGMAP |  | 45.5 |  | 45.5 | [16 empty] | -45.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Mapping - A | 10281 | ENGMPO |  | 5 |  | 5 | [16 empty] | -5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Pipe Program Management | 15142 | ENGSVC |  | 2 |  | 2 | [16 empty] | -2
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Pipe Program Mgmt Contr | 15451 | XCON07 |  | 416 |  | 416 | [16 empty] | -416
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Project Management | 15249 | Result |  | 11 |  | 11 | [16 empty] | -11
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Project Management | 15249 | ENGSVC |  | 3 |  | 3 | [16 empty] | -3
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | GT Project Management | 15249 | PRJMGT |  | 8 |  | 8 | [16 empty] | -8
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Invest Plng T&D Dir | 14939 | MANAGE |  | 2.5 |  | 2.5 | [16 empty] | -2.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition | 12809 | Result |  | 57.75 |  | 57.75 | [16 empty] | -57.75
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition | 12809 | ACQLIT |  | 10 |  | 10 | [16 empty] | -10
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition | 12809 | ACQRIG |  | 47.75 |  | 47.75 | [16 empty] | -47.75
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition - Central - BLOCKED | 15176 | Result |  | 53.75 |  | 53.75 | [16 empty] | -53.75
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition - Central - BLOCKED | 15176 | ACQLIT |  | 37.5 |  | 37.5 | [16 empty] | -37.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition - Central - BLOCKED | 15176 | ACQRIG |  | 12.25 |  | 12.25 | [16 empty] | -12.25
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Acquisition - Central - BLOCKED | 15176 | LNDRTS |  | 4 |  | 4 | [16 empty] | -4
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Rights | 11929 | ACQLIT |  | 13.5 |  | 13.5 | [16 empty] | -13.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Rights - North Coast - BLOCKED | 12981 | Result |  | 7 |  | 7 | [16 empty] | -7
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Rights - North Coast - BLOCKED | 12981 | ADM-OT |  | 1 |  | 1 | [16 empty] | -1
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Rights - North Coast - BLOCKED | 12981 | LNDRTS |  | 6 |  | 6 | [16 empty] | -6
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Surveying | 12577 | Result |  | 25.5 |  | 25.5 | [16 empty] | -25.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Surveying | 12577 | ADM-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Land Surveying | 12577 | LNDENG |  | 24 |  | 24 | [16 empty] | -24
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | LCE- Division Teams | 15789 | ACTSVC |  | 17.25 |  | 17.25 | [16 empty] | -17.25
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | LT&D Planning | 10234 | PLANSV |  | 4 |  | 4 | [16 empty] | -4
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | PFL Build | 15014 | ENGMAP |  | 4 |  | 4 | [16 empty] | -4
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Pipeline Services | 15227 | ENGSVC |  | 4.5 |  | 4.5 | [16 empty] | -4.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Pipeline/ILI | 10268 | ENGSVC |  | 156.5 |  | 156.5 | [16 empty] | -156.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Pjts Stds & Gov | 15247 | Result |  | 17.5 |  | 17.5 | [16 empty] | -17.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Pjts Stds & Gov | 15247 | ANLYST |  | 6 |  | 6 | [16 empty] | -6
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Pjts Stds & Gov | 15247 | MANAGE |  | 11.5 |  | 11.5 | [16 empty] | -11.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Process&Systems Mgt | 15069 | ANLYST |  | 22 |  | 22 | [16 empty] | -22
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CONSTR |  | 7 |  | 7 | [16 empty] | -7
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Project Controls | 15246 | Result |  | 198 |  | 198 | [16 empty] | -198
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Project Controls | 15246 | ANLYOT |  | 38 |  | 38 | [16 empty] | -38
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Project Controls | 15246 | ANLYST |  | 160 |  | 160 | [16 empty] | -160
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Project Ctrl-Contr | 15446 | XCON02 |  | 103.5 |  | 103.5 | [16 empty] | -103.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Supervisor GTS Air Water Haz - BLOCKED | 15165 | Result |  | 51 |  | 51 | [16 empty] | -51
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Supervisor GTS Air Water Haz - BLOCKED | 15165 | ADM-OT |  | 9.5 |  | 9.5 | [16 empty] | -9.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Supervisor GTS Air Water Haz - BLOCKED | 15165 | ADMIN |  | 2.5 |  | 2.5 | [16 empty] | -2.5
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Supervisor GTS Air Water Haz - BLOCKED | 15165 | ENVSVC |  | 39 |  | 39 | [16 empty] | -39
74006107 | R-840 DFM-8832-01 0.15MI MP 0.02-0.12 RE | Supervisor GTS Proj Plan Permit BLOCKED | 15167 | ENVPLN |  | 5.5 |  | 5.5 | [16 empty] | -5.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Result |  |  |  | 1682.67 |  | 1682.67 |  | 127.75 | 20.01 | 1.01 | [8 empty] | 148.77 |  |  |  | -1682.67
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PGE1/# | # | #
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Business Operations | 15495 | ACTSVC |  | 5.75 |  | 5.75 | [16 empty] | -5.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | CC Work Force Management | 11034 | MANAGE |  | 2 |  | 2 | [16 empty] | -2
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | CM/Insp - Central Coast | 15078 | Result |  | 118 |  | 118 | [16 empty] | -118
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | CM/Insp - Central Coast | 15078 | CNSTOT |  | 5 |  | 5 | [16 empty] | -5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | CM/Insp - Central Coast | 15078 | CONSTR |  | 113 |  | 113 | [16 empty] | -113
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | DA Gas T&R | 12108 | MO-OT |  | 3 |  | 3 | [16 empty] | -3
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | EM Projects | 15240 | Result |  | 128 |  | 128 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -128
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | EM Projects | 15240 | ADM-OT |  | 1.5 |  | 1.5 | [16 empty] | -1.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | EM Projects | 15240 | BIOCUL |  | 17.5 |  | 17.5 | [16 empty] | -17.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | EM Projects | 15240 | ENVPLN |  | 53 |  | 53 | [16 empty] | -53
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | EM Projects | 15240 | ENVSVC |  | 56 |  | 56 |  |  | 0.5 | [9 empty] | 0.5 |  |  |  | -56
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Encroachment Contractor - CH2M Hill | 15076 | Result |  | 19.4 |  | 19.4 | [16 empty] | -19.4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON07 |  | 7.4 |  | 7.4 | [16 empty] | -7.4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON08 |  | 10 |  | 10 | [16 empty] | -10
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON10 |  | 2 |  | 2 | [16 empty] | -2
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Enterprise Public Works Coordination | 15449 | Result |  | 34 |  | 34 |  | 0.5 | 1.5 | [9 empty] | 2 |  |  |  | -34
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Enterprise Public Works Coordination | 15449 | ANLYOT |  | 0.5 |  | 0.5 | [16 empty] | -0.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Enterprise Public Works Coordination | 15449 | ANLYST |  | 33.5 |  | 33.5 |  | 0.5 | 1.5 | [9 empty] | 2 |  |  |  | -33.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Gas Control Clearance Coordinators | 14147 | MONTR |  | 5 |  | 5 | [16 empty] | -5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GD Map SF/San Raf | 15071 | ENGMAP |  | 4 |  | 4 |  |  |  | 1 | [8 empty] | 1 |  |  |  | -4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GIS Analytics & Scanning | 15826 | ENGMAP |  | 5.75 |  | 5.75 | [16 empty] | -5.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GSO Strategy and Support | 15034 | MONTR |  | 1 |  | 1 | [16 empty] | -1
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT GC North Eng | 15054 | ENGSVC |  | 20 |  | 20 | [16 empty] | -20
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT GC South Engineering | 15818 | Result |  | 32.5 |  | 32.5 | [16 empty] | -32.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT GC South Engineering | 15818 | ENG-OT |  | 10 |  | 10 | [16 empty] | -10
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT GC South Engineering | 15818 | ENGSVC |  | 22.5 |  | 22.5 | [16 empty] | -22.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT ILI Program Mgmt Contr | 15452 | XCON07 |  | 4 |  | 4 | [16 empty] | -4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Mapping - A | 10281 | Result |  | 24 |  | 24 |  |  | 14.75 | [9 empty] | 14.75 |  |  |  | -24
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Mapping - A | 10281 | ENGMAP |  | 22 |  | 22 |  |  | 12.75 | [9 empty] | 12.75 |  |  |  | -22
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Mapping - A | 10281 | ENGMPO |  | 2 |  | 2 |  |  | 2 | [9 empty] | 2 |  |  |  | -2
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Pipe Program Management | 15142 | ENGSVC |  | 1 |  | 1 | [16 empty] | -1
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Pipe Program Mgmt Contr | 15451 | XCON07 |  | 164 |  | 164 | [16 empty] | -164
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Project Management | 15249 | Result |  | 7.5 |  | 7.5 | [16 empty] | -7.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Project Management | 15249 | ENGSVC |  | 3.5 |  | 3.5 | [16 empty] | -3.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Project Management | 15249 | PRJMGT |  | 4 |  | 4 | [16 empty] | -4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Strength Test Engineering | 15049 | Result |  | 133.5 |  | 133.5 | [16 empty] | -133.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Strength Test Engineering | 15049 | ENG-OT |  | 0.25 |  | 0.25 | [16 empty] | -0.25
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | GT Strength Test Engineering | 15049 | ENGSVC |  | 133.25 |  | 133.25 | [16 empty] | -133.25
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Land Acquisition | 12809 | Result |  | 59.5 |  | 59.5 | [16 empty] | -59.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Land Acquisition | 12809 | ACQLIT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Land Acquisition | 12809 | ACQRIG |  | 57 |  | 57 | [16 empty] | -57
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Land Rights | 11929 | ACQLIT |  | 2 |  | 2 | [16 empty] | -2
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Land Surveying | 12577 | LNDENG |  | 15 |  | 15 | [16 empty] | -15
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | LCE- Division Teams | 15789 | ACTSVC |  | 33 |  | 33 | [16 empty] | -33
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | LT&D Planning | 10234 | PLANSV |  | 27 |  | 27 | [16 empty] | -27
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PFL Build | 15014 | Result |  | 125.52 |  | 125.52 |  | 122.25 | 3.26 | 0.01 | [8 empty] | 125.52 |  |  |  | -125.52
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PFL Build | 15014 | ENGMAP |  | 88 |  | 88 |  | 84.75 | 3.25 | [9 empty] | 88 |  |  |  | -88
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PFL Build | 15014 | ENGMPO |  | 37.5 |  | 37.5 |  | 37.5 | [10 empty] | 37.5 |  |  |  | -37.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PFL Build | 15014 | PCONT1 |  | 0.02 |  | 0.02 |  |  | 0.01 | 0.01 | [8 empty] | 0.02 |  |  |  | -0.02
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Pipeline Services | 15227 | Result |  | 29.75 |  | 29.75 | [16 empty] | -29.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Pipeline Services | 15227 | ENG-OT |  | 4 |  | 4 | [16 empty] | -4
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Pipeline Services | 15227 | ENGSVC |  | 25.75 |  | 25.75 | [16 empty] | -25.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas Construction | 11778 | Result |  | 10 |  | 10 | [16 empty] | -10
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas Construction | 11778 | CNSTOT |  | 2 |  | 2 | [16 empty] | -2
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas Construction | 11778 | CONSTR |  | 8 |  | 8 | [16 empty] | -8
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas T&R | 11783 | Result |  | 145.25 |  | 145.25 | [16 empty] | -145.25
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas T&R | 11783 | MO |  | 117.5 |  | 117.5 | [16 empty] | -117.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PN Gas T&R | 11783 | MO-OT |  | 27.75 |  | 27.75 | [16 empty] | -27.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | Result |  | 16.5 |  | 16.5 | [16 empty] | -16.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CNSTOT |  | 1 |  | 1 | [16 empty] | -1
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CONSTR |  | 15.5 |  | 15.5 | [16 empty] | -15.5
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Project Controls | 15246 | Result |  | 440.75 |  | 440.75 |  | 5 | [10 empty] | 5 |  |  |  | -440.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Project Controls | 15246 | ANLYOT |  | 21.75 |  | 21.75 | [16 empty] | -21.75
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Project Controls | 15246 | ANLYST |  | 419 |  | 419 |  | 5 | [10 empty] | 5 |  |  |  | -419
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | Project Ctrl-Contr | 15446 | XCON02 |  | 23 |  | 23 | [16 empty] | -23
74015828 | DREG4197 MP 0.02 - 0.03 REPLACE PIPE | T&D As-Built QC | 15237 | MANAGE |  | 43 |  | 43 | [16 empty] | -43
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | Result |  |  |  | 21.5 |  | 21.5 | [16 empty] | -21.5
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | EM Projects | 15240 | ENVSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | GT Est - Strength Test | 15361 | ESTSVC |  | 1 |  | 1 | [16 empty] | -1
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | Land Surveying | 12577 | LNDENG |  | 1 |  | 1 | [16 empty] | -1
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | Pipeline Services | 15227 | ENGSVC |  | 0.5 |  | 0.5 | [16 empty] | -0.5
74025173 | L-101 MP18.59-18.62 CASING EXTENSION WRO | Pipeline/ILI | 10268 | ENGSVC |  | 18.5 |  | 18.5 | [16 empty] | -18.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Result |  |  |  | 6769.35 |  | 6769.35 | 10.5 | 51.25 | 1.75 | [9 empty] | 63.5 |  |  |  | -6769.35
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | PGE1/# | # | #
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Applied Technology Services | 12884 | TECHSV |  | 79 |  | 79 | [16 empty] | -79
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Asset Knowledge Management | 15301 | MANAGE |  | 5 |  | 5 | [16 empty] | -5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Business Operations | 15495 | ACTSVC |  | 1.75 |  | 1.75 | [16 empty] | -1.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | CC Work Force Management | 11034 | MANAGE |  | 0.25 |  | 0.25 | [16 empty] | -0.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | CM/Insp - Central Valley | 15103 | Result |  | 11.5 |  | 11.5 | [16 empty] | -11.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | CM/Insp - Central Valley | 15103 | CNSTOT |  | 2 |  | 2 | [16 empty] | -2
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | CM/Insp - Central Valley | 15103 | CONSTR |  | 9.5 |  | 9.5 | [16 empty] | -9.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Concord Test Lab | 15036 | TESTOT |  | 16 |  | 16 | [16 empty] | -16
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | Result |  | 271.25 |  | 271.25 | 1 | [11 empty] | 1 |  |  |  | -271.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | ADM-OT |  | 2.5 |  | 2.5 | [16 empty] | -2.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | BIOCUL |  | 9 |  | 9 | [16 empty] | -9
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | ENVPLN |  | 205.75 |  | 205.75 | 1 | [11 empty] | 1 |  |  |  | -205.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | ENVSOT |  | 4.5 |  | 4.5 | [16 empty] | -4.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | EM Projects | 15240 | ENVSVC |  | 49.5 |  | 49.5 | [16 empty] | -49.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Encroachment Contractor - CH2M Hill | 15076 | Result |  | 78.5 |  | 78.5 | [16 empty] | -78.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON07 |  | 0.5 |  | 0.5 | [16 empty] | -0.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON08 |  | 27.5 |  | 27.5 | [16 empty] | -27.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Encroachment Contractor - CH2M Hill | 15076 | XCON10 |  | 50.5 |  | 50.5 | [16 empty] | -50.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Enterprise Public Works Coordination | 15449 | ANLYST |  | 4 |  | 4 | [16 empty] | -4
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Field Quality Control | 14862 | MANAGE |  | 5 |  | 5 | [16 empty] | -5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | FR Gas T&R | 12209 | Result |  | 465.5 |  | 465.5 | [16 empty] | -465.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | FR Gas T&R | 12209 | MO |  | 209.75 |  | 209.75 | [16 empty] | -209.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | FR Gas T&R | 12209 | MO-DT |  | 116.5 |  | 116.5 | [16 empty] | -116.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | FR Gas T&R | 12209 | MO-OT |  | 139.25 |  | 139.25 | [16 empty] | -139.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Gas Control Clearance Coordinators | 14147 | MONTR |  | 6 |  | 6 | [16 empty] | -6
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Gas Corrosion South | 15287 | MO |  | 18 |  | 18 | [16 empty] | -18
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GC Gas FR | 11843 | Result |  | 50 |  | 50 | [16 empty] | -50
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GC Gas FR | 11843 | CNSTDT |  | 11 |  | 11 | [16 empty] | -11
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GC Gas FR | 11843 | CNSTOT |  | 6 |  | 6 | [16 empty] | -6
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GC Gas FR | 11843 | CONSTR |  | 33 |  | 33 | [16 empty] | -33
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GD Map SF/San Raf | 15071 | ENGMAP |  | 8 |  | 8 | [16 empty] | -8
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GD Spvr Bishop Ranch | 15098 | ENGMAP |  | 9.5 |  | 9.5 | [16 empty] | -9.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GIS Analytics & Scanning | 15826 | Result |  | 2.25 |  | 2.25 |  | 0.25 | 1.75 | [9 empty] | 2 |  |  |  | -2.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GIS Analytics & Scanning | 15826 | ENG-OT |  | 1.75 |  | 1.75 |  |  | 1.5 | [9 empty] | 1.5 |  |  |  | -1.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GIS Analytics & Scanning | 15826 | ENGMAP |  | 0.5 |  | 0.5 |  | 0.25 | 0.25 | [9 empty] | 0.5 |  |  |  | -0.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South Central Construction | 14861 | CONSTR |  | 30 |  | 30 | [16 empty] | -30
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South East Construction | 15053 | Result |  | 2657 |  | 2657 | [16 empty] | -2657
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South East Construction | 15053 | CNSTDT |  | 24 |  | 24 | [16 empty] | -24
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South East Construction | 15053 | CNSTOT |  | 657.5 |  | 657.5 | [16 empty] | -657.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South East Construction | 15053 | CONSTR |  | 1975.5 |  | 1975.5 | [16 empty] | -1975.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South Engineering | 15818 | Result |  | 705.25 |  | 705.25 | 5.5 | [11 empty] | 5.5 |  |  |  | -705.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South Engineering | 15818 | ENG-DT |  | 4.75 |  | 4.75 | [16 empty] | -4.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South Engineering | 15818 | ENG-OT |  | 158.5 |  | 158.5 | 5.5 | [11 empty] | 5.5 |  |  |  | -158.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT GC South Engineering | 15818 | ENGSVC |  | 542 |  | 542 | [16 empty] | -542
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT ILI Program Mgmt Contr | 15452 | XCON07 |  | 21 |  | 21 | [16 empty] | -21
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Mapping - A | 10281 | ENGMAP |  | 13.25 |  | 13.25 |  | 10 | [10 empty] | 10 |  |  |  | -13.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Pipe Program Mgmt Contr | 15451 | Result |  | 248.1 |  | 248.1 |  | 36 | [10 empty] | 36 |  |  |  | -248.1
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Pipe Program Mgmt Contr | 15451 | XCON07 |  | 236.6 |  | 236.6 |  | 36 | [10 empty] | 36 |  |  |  | -236.6
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Pipe Program Mgmt Contr | 15451 | XCON08 |  | 11.5 |  | 11.5 | [16 empty] | -11.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Project Management | 15249 | ENGSVC |  | 19.5 |  | 19.5 | [16 empty] | -19.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Station Engineering | 15018 | ENGSVC |  | 6 |  | 6 | [16 empty] | -6
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GT Strength Test Engineering | 15049 | ENGSVC |  | 245.25 |  | 245.25 | [16 empty] | -245.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GTTapping Crews/Equipment/Trucks | 15184 | Result |  | 133 |  | 133 | [16 empty] | -133
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GTTapping Crews/Equipment/Trucks | 15184 | CNSTDT |  | 31.5 |  | 31.5 | [16 empty] | -31.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GTTapping Crews/Equipment/Trucks | 15184 | CNSTOT |  | 47 |  | 47 | [16 empty] | -47
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | GTTapping Crews/Equipment/Trucks | 15184 | CONSTR |  | 54.5 |  | 54.5 | [16 empty] | -54.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Acquisition | 12809 | Result |  | 152.25 |  | 152.25 | [16 empty] | -152.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Acquisition | 12809 | ACQLIT |  | 140 |  | 140 | [16 empty] | -140
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Acquisition | 12809 | ADM-OT |  | 12.25 |  | 12.25 | [16 empty] | -12.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Rights | 11929 | Result |  | 26.5 |  | 26.5 | [16 empty] | -26.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Rights | 11929 | ACQLIT |  | 23.5 |  | 23.5 | [16 empty] | -23.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Rights | 11929 | LNDRTS |  | 3 |  | 3 | [16 empty] | -3
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Surveying | 12577 | Result |  | 61.75 |  | 61.75 | [16 empty] | -61.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Surveying | 12577 | ADM-OT |  | 8.5 |  | 8.5 | [16 empty] | -8.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Land Surveying | 12577 | LNDENG |  | 53.25 |  | 53.25 | [16 empty] | -53.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LCE- Division Teams | 15789 | ACTSVC |  | 49.25 |  | 49.25 | [16 empty] | -49.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Engineering & Operations | 14944 | CONSTR |  | 9 |  | 9 | [16 empty] | -9
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | Result |  | 257 |  | 257 | [16 empty] | -257
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | CNSTDT |  | 10 |  | 10 | [16 empty] | -10
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | CNSTOT |  | 42 |  | 42 | [16 empty] | -42
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | CONSTR |  | 199 |  | 199 | [16 empty] | -199
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | ENG-OT |  | 2 |  | 2 | [16 empty] | -2
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LNG/CNG Operations | 15352 | ENGSVC |  | 4 |  | 4 | [16 empty] | -4
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LT&D Planning | 10234 | Result |  | 105.5 |  | 105.5 | [16 empty] | -105.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LT&D Planning | 10234 | PLANSV |  | 100 |  | 100 | [16 empty] | -100
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | LT&D Planning | 10234 | PLNGOT |  | 5.5 |  | 5.5 | [16 empty] | -5.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Measurement/Reg | 13696 | ENGSVC |  | 3.5 |  | 3.5 | [16 empty] | -3.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Pipeline Services | 15227 | ENGSVC |  | 17 |  | 17 | [16 empty] | -17
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Pipeline/ILI | 10268 | ENGSVC |  | 4.5 |  | 4.5 | [16 empty] | -4.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | Result |  | 417.75 |  | 417.75 | [16 empty] | -417.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CNSTDT |  | 13.75 |  | 13.75 | [16 empty] | -13.75
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CNSTOT |  | 74.5 |  | 74.5 | [16 empty] | -74.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | PROJECT CLEARANCE SUPPORT TEAM | 15228 | CONSTR |  | 329.5 |  | 329.5 | [16 empty] | -329.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Project Controls | 15246 | Result |  | 460 |  | 460 | 4 | 5 | [10 empty] | 9 |  |  |  | -460
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Project Controls | 15246 | ANLYOT |  | 72 |  | 72 | [16 empty] | -72
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Project Controls | 15246 | ANLYST |  | 388 |  | 388 | 4 | 5 | [10 empty] | 9 |  |  |  | -388
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | Project Ctrl-Contr | 15446 | XCON02 |  | 13 |  | 13 | [16 empty] | -13
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | SCADA Execution | 15245 | Result |  | 1.5 |  | 1.5 | [16 empty] | -1.5
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | SCADA Execution | 15245 | ENG-OT |  | 0.25 |  | 0.25 | [16 empty] | -0.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | SCADA Execution | 15245 | ENGSVC |  | 1.25 |  | 1.25 | [16 empty] | -1.25
74025713 | DFM 7212-01 MP6.36-6.56 REPL PIPE | T&D As-Built QC | 15237 | MANAGE |  | 81 |  | 81 | [16 empty] | -81