## Sheet1
Order | Parent order | Priority | Link to Materials | Project Manager | Project Forecasting Year | Project Name | Caltrans Dist. | Caltrans DSDD? | UG Ft. | OH Ft. | Division | ADE or Estimator | Land Surveyor | Survey Vendor | Basmap Status | ETA Prelim. Basemap COMP | Actual Deliv. Prelim. Basemap | Pothole Needed? | ETA Final Basemap COMP | ETA Basemap Return from Estimating for Caltrans | Site Specific CT permit Req? | SS permit submitted to inbox | Land Comments
35219268 |  | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 1 | 10 | No | 0 | 8553.6 | YO |  |  |  | COMP | 2021-03-12 | 2021-03-12 |  |  |  | Yes | 2021-03-31 | SS permit was submitted to CT inbox 3/31/21( we have survey info of crossings if needed)
35226241 | 35219268 | 1 | 35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 2 | 10 | No | 0 | 7920 | YO |  |  |  | COMP | 2021-03-12 | 2021-03-12 |  |  |  | yes | 2021-03-31 | SS permit was submitted to CT inbox 3/31/21( we have survey info of xings' if needed)
35145540 |  | 1 | missing |  | 2021 | PSPS - FROGTOWN 1702 - CB | 10 | Yes | 2846 | 3872 | ST |  |  |  | COMP | 2021-03-15 | 2021-03-15 |  |  |  | dsdd |  | project will need a DSDD if they can't get alternate option approved
35219266 |  | 1 | 35219266 |  | 2021 | CWSP - MARIPOSA 2102CB PH 1 | 10 | No | 0 | 13713 | YO |  |  |  | COMP | 2021-04-09 | 2021-04-09 |  |  |  | yes | 2021-05-04
35236662 |  | 1 |  |  | 2021 | CWSP - Oleta 1101 - FS 754718 Ph 1.2 | 10 | Yes |  | 9472 | ST |  |  |  | NA | NA | NA |  |  |  | no
35219587 | 35219267 | 1 | 35219267 |  | 2021 | CWSP - MARIPOSA 2102440236 PH2 | 10 | yes |  | 10718 | YO |  |  |  | TBD | [7 empty] | kickoff meeting 5/24,[REDACTED] reviewing for DSDD, 1-LOCATION NEEDS SURVEY TO DETERMINE IF DSDD
35226853 |  | 1 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 3 | No | 0 | 13889 | SI |  |  |  | NA | NA | NA
35227651 |  | 1 |  |  | 2021 | VACAVILLE 1104 PH 1.2 | 4 | No | 0 | 18216 | SA |  |  |  | NA | NA | NA
35227868 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 1 | No | 0 | 2112 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | Basemap no longer needed
35223037 |  | 1 | missing |  | 2021 | PSPS - OAKHURST 1101 - OAKHURST | 10 | No | 105.6 | 0 | YO |  |  |  | NA | NA | NA | [5 empty] | Basemap no longer needed
35094513 |  | 1 | missing |  | 2021 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10 | Yes | 428 | 9423 | ST |  |  |  | COMP | COMP | COMP |  |  |  | dsdd in process |  | BM HAS BEEN RESUBMITTED TO CT
35219260 |  | 1 |  |  | 2021 | Changed to OH Only |  |  | 4224 | 0 | NV |  |  |  | NA | NA | NA | [5 empty] | Basemap no longer needed
35219588 | 35219267 | 1 | 35219267 |  | 2021 | CWSP - MARIPOSA 2102440236 PH3 | 10 | yes |  | 7339 | YO |  |  |  | TBD | [7 empty] | kickoff meeting 5/24, [REDACTED] reviewing for DSDD, 1-LOCATION NEEDS SURVEY TO DETERMINE IF DSDD
35192292 |  | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 4 | No | 4224 | 0 | SO |  |  |  | COMP | 2021-03-19 | 2021-03-19
35225594 | 35192292 | 1 | 35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 4 | No | 2481.6 | 0 | SO |  |  |  | COMP | 2021-03-19 | 2021-03-19 | [5 empty] | BM REQUESTED FOR NEW POLE LINE PORTION
35062374 |  | 1 | 35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 3 | No | 8236.8 | 0 | SI |  |  |  | COMP | 2021-04-05 | 2021-04-06
35062375 |  | 1 | 35062375 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 3 | No | 5860 | 0 | SI |  |  |  | COMP | 2021-04-16 | 2021-04-14
35226849 |  | 1 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 3 | No | 9398 | 0 | SI |  |  |  | COMP | 2021-04-16 | 2021-04-14 | [5 empty] | NEED SOME MAPPING FOR NEW POLE LINE
35226700 |  | 1 | missing |  | 2021 | CWSP - WYANDOTTE 110932586 PH 1.2 | 3 | No | 3010 | 0 | NV |  |  |  | COMP | 2021-04-16 | 2021-04-14
35192291 |  | 1 | 35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 3 | No | 2534.4 | 0 | SI |  |  |  | COMP | 2021-04-19 | 2021-04-19 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35062376 |  | 1 | 35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 3 | No | 13358.4 | 0 | SI |  |  |  | COMP | 2021-04-19 | 2021-04-20 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35232650 |  | 1 |  |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 3 | No | 9028 | 0 |  |  |  |  | COMP | 2021-04-23 | 2021-04-22 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35219281 |  | 1 |  |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 3 | No | 13200 | 0 |  |  |  |  | COMP | 2021-04-23 | 2021-04-22 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35223039 |  | 1 |  |  | 2021 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 3 | No | 4066 | 0 |  |  |  |  | COMP | 2021-04-30 | 2021-04-30 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35224712 |  | 1 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 | 2 | Yes | 9134 | 0 | NV |  |  |  | COMP | 2021-05-07 | 2021-05-06 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal; Need to Acquire Easement from Tribe
35224713 |  | 1 | missing |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 | 2 | Yes | 9662.4 | 0 | NV |  |  |  | COMP | 2021-05-07 | 2021-05-06 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35217273 |  | 1 | 35217273 |  | 2021 | SH - UPPER LAKE 1101 CB | 1 | Yes | 0 | 5702.4 | HB |  |  |  | COMP | 2021-03-15 | 2021-03-16 | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35229119 |  | 1 | missing |  |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 1 | No | 3221 | 0 | HB |  |  |  | COMP | 2021-03-18 | 2021-03-17
35223024 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 4 | No | 11827.2 | 0 | NB |  |  |  | COMP | 2021-03-29 | 2021-04-06
35192284 |  | 1 | 35192284 |  | 2021 | ECOP - SILVERADO 2104 - H05-LR726 | 4 | No | 10929.6 | 0 | NB |  |  |  | COMP | 2021-03-29 | 2021-04-06 | [5 empty] | this portion will require easements
35223026 | 35192284 | 1 | missing |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 4 | No | 9504 | 0 | NB |  |  |  | COMP | 2021-03-29 | 2021-04-06 | [5 empty] | an Encroachment permit is required for TT to do survey work within CT r/w
35192280 |  | 1 | 35192280 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 | 4 | No | 7075.2 | 0 | DI |  |  |  | COMP | 2021-04-11 | 2021-04-02 | [5 empty] | Grass Valley restricting lane closure hours due to school traffic
35228186 |  | 1 | missing |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 1 | No | 7850 | 0 | HB |  |  |  | COMP | 2021-05-25 | 2021-05-06 | [5 empty] | Coordinate L&M with [REDACTED]
35220895 |  | 1 | 35220895 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 1 | No | 10190 | 1162 | HB |  |  |  | COMP | 2021-06-10 | 2021-05-06 | [5 empty] | Coordinate mobile lidar w Caltrans
35217270 |  | 1 | 35217270 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 | 1 | Yes | 0 | 2904 | HB |  |  |  | COMP | 2021-06-12 | 2021-05-06 | [5 empty] | Coordinate mobile lidar w Caltrans
35217275 |  | 1 | 35217275 |  | 2021 | FRRB - PN DIVISION SANTA CRUZ COUNTY | 4 | No | 0 | 15312 | PN |  |  |  | COMP | 2021-05-15 | 2021-04-28 | [5 empty] | OH replacement in Caltrans RW; Estimating will not need Basemap, Caltrans Site Specific Permits & DSDD form will
35217274 |  | 1 | 35217274 |  | 2021 | FRRB - PN DIVISION SAN MATEO COUNTY | 4 | No | 0 | 11774.4 | PN |  |  |  | COMP | 2021-05-15 | 2021-04-28 | [5 empty] | OH Removal; verifying if Caltrans Site Specific is need for Pole Removal - might need TCP Site Specific-[REDACTED] to verify
35217267 |  | 1 | 35217267 |  | 2021 | CWSP - MARIPOSA 210197142 PH 2 | 10 | No |  | 4752 | YO |  |  |  | NA | NA | NA |  |  |  | no |  | OH only; mapping for two Hwy Xings; Estimating will not need Basemap, Caltrans Site Specific Permits & DSDD form will
35191937 |  | 1 |  |  | 2021 | Pueblo 2102 PH1.3 |  | no | [14 empty] | OH only; mapping for two Hwy Xings; Estimating will not need Basemap, Caltrans Site Specific Permits & DSDD form will
35217272 |  | 2 | 35217272 |  | 2022 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 2 | No | 1584 | 0 | NV |  |  |  | COMP | 2021-05-01 | 2021-05-01 |  |  |  | no |  | small UG segment
35226628 | 35217272 | 2 | 35217272 |  | 2022 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 2 | No | 4330 | 0 | NV |  |  |  | COMP | 2021-05-01 | 2021-05-01 |  |  |  | no |  | Main UG segment
35226629 | 35217272 | 2 | 35217272 |  | 2022 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 2 | No | 23760 | 0 | NV |  |  |  | COMP | 2021-05-01 | 2021-05-01 |  |  |  | no
35223615 | 35191319 | 2 | 35191319 |  | 2022 | ECOP - LAS GALLINAS A 1105 PH 2 | 4 | No | 8606.4 | 0 | NB |  |  |  | COMP | 2021-05-07 | 2021-05-07 |  |  |  | no
35219591 |  | 2 |  |  | 2022 | CWSP - Oleta 1101 - FS 754718 Ph 1.1 | 10 | Yes |  | 6474 | ST |  |  |  | INPR | 2021-06-25 |  |  |  |  | dsdd |  | MT to provide utilities, Caltrans Hwys 49 & 193
35234526 |  | 2 |  |  | 2022 | Martell 1101 PH 1.3 (UG) |  | No | 3115 |  | ST |  |  |  | INPR | 2021-09-17 |  |  |  |  | no
35226798 |  | 2 |  |  | 2022 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 2 | Yes |  | 8395 | NV |  |  |  | COMP | 2021-05-19 | 2021-05-19 | [5 empty] | Basemap no longer needed
35226900 |  | 2 |  |  | 2022 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | 2 | No |  | 3643 | NV |  |  |  | COMP | 2021-05-19 | 2021-05-19 | [5 empty] | Caltrans Xing, confirm JUA, poles outside ROW
35227652 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 1.3 | 4 | Yes | 2904 |  | SA |  |  |  | INPR | 2021-06-04 | [6 empty] | Basemap no longer needed
35219276 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 1.1 | 4 | Yes | 14203 |  | SA |  |  |  | INPR | 2021-06-04 | [6 empty] | Basemap no longer needed
35219543 |  | 2 |  |  | 2022 | PLACERVILLE 1112 PSPS (WEST MAIN STREET) | 3 | No | 1267 |  | SI |  |  |  | COMP | 2021-05-24 | 2021-05-21 | [5 empty] | waiting for approval from PM
35219542 |  | 2 |  |  | 2022 | PLACERVILLE 1112 PSPS (ESKATON VILLAGE) | 3 | No | 733 |  | SI |  |  |  | INPR | 2021-05-26
35223032 |  | 2 |  |  | 2022 | MOUNTAIN QUARRIES 2101 - COOL (PSPS) | 3 | Yes | 2323 |  | SI |  |  |  | INPR | 2021-06-10
35227870 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 2.2 | 4 | No | 317 | 7181 | SA |  |  |  | INPR | 2021-06-11 | [6 empty] | No Caltrans for 1.3
35227656 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 2.3 | 4 | No | 3960 | 0 | SA |  |  |  | INPR | 2021-06-11 | [6 empty] | UG in Caltrans Hwy 299
35227658 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 2.5 | 4 | No | 1373 | 1478 | SA |  |  |  | INPR | 2021-06-11 | [6 empty] | UG in Caltrans Hwy 299
35224377 |  | 2 |  |  | 2022 | PLACERVILLE 2106 (GEORGETOWN) MICROGRID PH 1.1 | 3 | Yes | 739 | 0 | SI |  |  |  | INPR | 2021-06-18 | [6 empty] | UG in Caltrans Hwy 299
35233995 |  | 2 |  |  | 2022 | PLACERVILLE 2106 (GEORGETOWN) MICROGRID PH 1.2 | 3 | Yes | 2640 | 0 | SI |  |  |  | INPR | 2021-06-18 | [6 empty] | No UG
35233996 |  | 2 |  |  | 2022 | PLACERVILLE 2106 (GEORGETOWN) MICROGRID PH 1.3 | 3 | Yes | 3749 | 0 | SI |  |  |  | INPR | 2021-06-18 | [6 empty] | No UG; phases 2 & 3 will capture all mapping needs
35219289 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 1.1 | 2 | Yes | 22991 | 0 | NV |  |  |  | INPR | 2021-06-28 | [6 empty] | No UG
35233948 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 1.3 | 2 | Yes | 13660 | 0 | NV |  |  |  | INPR | 2021-06-28 | [6 empty] | OH harden NO mapping
35233950 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 1.5 | 2 | Yes | 14542 | 0 | NV |  |  |  | INPR | 2021-06-28 | [6 empty] | OH harden; No mapping per [REDACTED]
35231608 |  | 2 |  |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 3 | No | 0 | 1960 | SI |  |  |  | NA | NA | NA | [5 empty] | OH removal, Caltrans Xings NO mapping per [REDACTED]
35217268 |  | 2 |  |  | 2022 | CWSP - BUCKS CREEK 1101 CB PH 1 | 2 | Yes | 0 | 1056 | NV |  |  |  | NA | NA | NA | [5 empty] | No UG
35226799 |  | 2 |  |  | 2022 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 2 | Yes | 0 | 1015 | NV |  |  |  | NA | NA | NA | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35227654 |  | 2 |  |  | 2022 | VACAVILLE 1104 PH 1.5 | 4 | No | 0 | 2798 | SA |  |  |  | NA | NA | NA | [5 empty] | Need Basemap back from Estimating for Caltrans Submittal
35217269 |  | 2 | 35217269 |  | 2022 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 1 | Yes | 0 | 2270 | HB |  |  |  | RFP | 2021-05-25 | [6 empty] | Need Basemap back from Estimating for Caltrans Submittal
35227007 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 1 | Yes | 15183 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | Need Basemap back from Estimating for Caltrans Submittal
35227025 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 1 | Yes | 2900 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | Need Basemap back from Estimating for Caltrans Submittal
35227165 |  | 2 | missing |  | 2022 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 1 | No | 5333 | 0 | HB |  |  |  | INPR | 2021-05-25 | [6 empty] | Need Basemap back from Estimating for Caltrans Submittal
35227167 |  | 2 |  |  | 2022 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 1 | No | 9504 | 0 | HB |  |  |  | INPR | 2021-05-25 | [6 empty] | 3/22/2021 Proposal accepted
35227168 |  | 2 |  |  | 2022 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 1 | No | 8290 | 0 | HB |  |  |  | INPR | 2021-05-25
| 35174478 | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 1 | Yes | 5491 | 0 | HB |  |  |  | INPR | 2021-06-15
35226857 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 1 | Yes | 4488 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | 5/6/2021 DELIEVERED MAPPING TO [REDACTED] 3/31/2021 approval recieved
| 35174501 | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 1 | Yes | 21597 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | 3/31/2021 approval recieved
35192282 |  | 2 |  |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 1 | Yes | 10771 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | 3/31/2021 approval recieved
35226873 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 1 | Yes | 5488 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | Sent proposal to [REDACTED] for approval on 3-25-21
35226878 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 1 | Yes | 3109 | 0 | HB |  |  |  | INPR | 2021-06-15
35227001 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 1 | Yes | 3809 | 0 | HB |  |  |  | INPR | 2021-06-15
35227002 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 1 | Yes | 2286 | 0 | HB |  |  |  | INPR | 2021-06-15
35227003 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 1 | Yes | 3067 | 0 | HB |  |  |  | INPR | 2021-06-15
35227004 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 1 | Yes | 1839 | 0 | HB |  |  |  | INPR | 2021-06-15
35217271 |  | 2 | 35217271 |  | 2022 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 1 | No | 8131 | 0 | HB |  |  |  | INPR | 2021-06-10
35225589 |  | 2 |  |  | 2022 | CWSP - KONOCTI 1102 LR 965078 PH2 | 1 | Yes | 0 | 4699 | HB |  |  |  | INPR | 2021-06-12
35225591 |  | 2 |  |  | 2022 | CWSP - KONOCTI 1102 LR 965078 PH3 | 1 | Yes | 0 | 4224 | HB |  |  |  | INPR | 2021-06-12 | [6 empty] | 3/31/2021 approval recieved
35227030 |  | 2 | missing |  | 2022 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 1 | Yes | 7287 | 0 | HB |  |  |  | INPR | 2021-06-12 | [6 empty] | 3/31/2021 approval recieved
35227031 |  | 2 | missing |  | 2022 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 1 | Yes | 8184 | 0 | HB |  |  |  | INPR | 2021-06-12
35174478 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 1 | Yes | 5491 | 0 | HB |  |  |  | INPR | 2021-06-12
35174501 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 1 | Yes | 21597 | 0 | HB |  |  |  | INPR | 2021-06-12
35227160 |  | 2 | missing |  | 2022 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 1 | Yes | 6970 | 0 | HB |  |  |  | INPR | 2021-06-12 | [6 empty] | 5/6/2021 DELIEVERD MAPPING TO [REDACTED]
35227162 |  | 2 | missing |  | 2022 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 1 | Yes | 1690 | 0 | HB |  |  |  | INPR | 2021-06-12 | [6 empty] | 5/6/2021 DELIVERED MAPPING TO [REDACTED]
35227864 |  | 2 | missing |  | 2022 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 1 | No | 3274 | 0 | HB |  |  |  | INPR | 2021-06-15
35219093 |  | 2 |  |  | 2022 | CWSP - TIDEWATER 210614072 PH 1.1 | 4 | No | 6019 | 0 | DI |  |  |  | INPR | 2021-06-24 | [6 empty] | 4/2/2021 approval recieved
35219096 |  | 2 |  |  | 2022 | CWSP - KIRKER 2104442850 PH 1.1 | 4 | No | 8818 | 0 | DI |  |  |  | INPR | 2021-06-24 | [6 empty] | 3/31/2021 approval recieved
35231543 |  | 2 |  |  | 2022 | CWSP - TIDEWATER 210614072 PH 1.2 | 4 | No | 6864 |  | DI |  |  |  | INPR | 2021-06-24 | [6 empty] | still awaiting decision which option they are going to move forward on.
35226632 |  | 2 |  |  | 2022 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 1 | No | 560 | 0 | HB |  |  |  | INPR | 2021-07-29 | [6 empty] | 3/31/2021 approval recieved
35238567 | 35219268 | 2 |  |  | 2022 | CWSP - MARIPOSA 210197142 PH 1.4 | 10 | TBD | [6 empty] | COMP | 2021-03-12 | 2021-03-12 |  |  |  | dsdd ? |  | 3/31/2021 approval recieved
35223030 |  | 2 |  |  | 2022 | BANGOR 1101 - MICROGRID | 3 | No | [6 empty] | COMP | 2021-04-23 | 2021-04-21 | [5 empty] | 3/31/2021 approval recieved
35116385 |  | 2 |  |  | 2022 | CWSP - MI-WUK VILLAGE 1701 PH 1.4 | 10 | Yes | [6 empty] | COMP | 2021-04-30 | 2021-04-23
35223036 |  | 2 |  |  | 2022 | PSPS - BRUNSWICK-Morgan Ranch Dr. (Grass Valley) |  | No | [6 empty] | COMP | 2021-04-30 | 2021-04-27
35223038 |  | 2 |  |  | 2022 | Martell 1101 PH 1.1 (UG) |  | No | 3802 |  | ST |  |  |  | INPR | 2021-09-17 |  |  |  |  | no |  | 3/31/2021 approval recieved
35234284 |  | 2 |  |  | 2022 | Martell 1101 PH 1.2(oh) |  | No | 0 | 1742 | ST |  |  |  | INPR | 2021-09-17 |  |  |  |  | no |  | 3/31/2021 approval recieved
35219589 |  | 2 |  |  | 2022 | CWSP-WILDWOOD 1101-LR 1454-SHASTA CO. | 2 | Yes | 0 | 13622 | NV |  |  |  | COMP | 2021-05-19 | 2021-05-19 | [5 empty] | 3/31/2021 approval recieved
35224321 |  | 2 |  |  | 2022 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH1 | 2 | Yes | 0 | 12302 | NV |  |  |  | COMP | 2021-05-19 | 2021-05-19 | [5 empty] | 3/31/2021 approval recieved
35233953 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 2.3 | 2 | No | 4437 | 0 | NV |  |  |  | INPR | 2021-06-17 | [6 empty] | 5/8/2021 SENT [REDACTED]PROPOSAL REQUEST TO APPROVE.
35233955 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 2.4 | 2 | No | 2900 | 0 | NV |  |  |  | INPR | 2021-06-17 | [6 empty] | 4/13/2021 Recieved encrochemnet permit . 3/30/2021 COUNTY MAPPING OUT OF DATE NEED TO DO FULL MAPPING IN AREA
35233957 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 2.5 | 2 | No | 539 | 0 | NV |  |  |  | INPR | 2021-06-17 | [6 empty] | 4/13/2021 permitting missed this area on request working on new permit. 3/30/2021 COUNTY MAPPING OUT OF DATE NEED TO DO FULL MAPPING IN AREA
35234756 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | Yes | 14689 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | 3-24-2021 Proposal accepted
35234758 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | Yes | 3073 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | 1 OH Crossing only
35234862 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | Yes | 422 | 0 | HB |  |  |  | INPR | 2021-06-15
35234865 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | Yes | 3419 | 0 | HB |  |  |  | INPR | 2021-06-15 | [6 empty] | the sow has one hwy crossing with poles well out of r/w, provided est guidance of how far to stay away from hwy
35191319 |  | 2 | 35191319 |  | 2022 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 4 | No | 6178 | 0 | NB |  |  |  | comp | 2021-05-07 | 2021-05-07 |  |  |  | no
35219097 |  | 2 | 35219097 |  |  | CWSP - COARSEGOLD 2104CB PH 1.1 | 10 | No | 0 | 13091 | YO |  |  |  | NA | NA | NA |  |  |  | yes
35174501 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 2 | Yes | 21597 | 0 | HB |  |  |  | INPR | 2021-06-15
35226848 |  | 2 | missing |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 3 | No | 0 | 15153 | SI |  |  |  | NA | NA | NA | [5 empty] | 5/18/2021 sent proposal to [REDACTED] to confirm.
35220896 |  | 2 | 35220896 |  | 2022 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | 1 | No | 1478 | 0 | HB |  |  |  | INPR | 2021-05-25 | [6 empty] | 5/18/2021 sent proposal to [REDACTED] to confirm.
35174478 |  | 2 |  |  | 2022 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Yes | 5491 | 0 | HB | [11 empty] | 5/18/2021 sent proposal to [REDACTED] to confirm.
35223063 |  | 2 |  |  | 2022 | PSPS - DUNBAR 1101 - OAKMONT PH 1 U/G HWY 12 | 4 | YES | 1688 | 0 | SO |  |  |  | RFP | [7 empty] | 5/18/2021 sent proposal to [REDACTED] to confirm.
35228774 |  | 2 |  |  | 2022 | PSPS - DUNBAR 1101 - OAKMONT PH 2 U/G HWY 12 | 4 | YES | 5284 | 0 | SO |  |  |  | RFP
35228775 |  | 2 |  |  | 2022 | PSPS - DUNBAR 1101 - OAKMONT PH 3 U/G HWY 12 | 4 | YES | 4770 | 0 | SO |  |  |  | RFP
35227033 |  | 2 |  |  | 2022 | PUEBLO 2102 PH 1.3 |  | NO | 6936 | 0 | NB |  |  |  | RFP
35231620 |  | 2 |  |  | 2022 | HIGHLANDS 1102628 PH 2 U/G HWY 20 | 2 | YES | 14141 | 0 | HB |  |  |  | RFP
35231621 |  | 2 |  |  | 2022 | HIGHLANDS 1102628 PH 3 U/G HWY 20 | 2 | YES | 7210 | 0 | HB |  |  |  | RFP
35219099 |  | 2 |  |  | 2022 | HIGHLANDS 1102628 PH 1 U/G HWY 20 | 2 | YES | 14398 | 0 | HB |  |  |  | RFP
35225827 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 3.1 | 2 |  | 4465 | 0 | NV |  |  |  | INPR | 2021-06-25
35234383 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 3.6 | 2 |  | 6328 | 0 | NV |  |  |  | INPR | 2021-06-25
35225828 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 4.1 | 2 |  | 13366 | 0 | NV |  |  |  | INPR | 2021-06-30
35234399 |  | 2 |  |  | 2022 | OREGON TRAIL 1103 PH 6.3 | 2 |  | 2535 | 0 | NV |  |  |  | INPR | 2021-06-18
35219098 | [5 empty] | Changed to OH Only | [8 empty] | NA | NA | [6 empty] | SENT PROPOSAL OUT FOR BID 5/6/2021
35219099 | [5 empty] | Not Yet Approved by WFGC | [16 empty] | SENT PROPOSAL OUT FOR BID 5/6/2021
35222045 | [5 empty] | Changed to OH Only | 1 | [15 empty] | SENT PROPOSAL OUT FOR BID 5/6/2021
35192282 | [5 empty] | Changed to OH Only | 1 | [15 empty] | 5/10/2021 RECIEVED NOTICE OF UNDERGROUNDING FOR PROJCET ASKED FOR CLAIRFICATION.
35192281 | [5 empty] | Changed to OH Only | 1 | [15 empty] | SENT PROPOSAL OUT FOR BID 5/10/2021
35174479 | [5 empty] | Not Yet Approved by WFGC | [16 empty] | SENT PROPOSAL OUT FOR BID 5/10/2021
35191937 | [5 empty] | Not Yet Approved by WFGC
35224378 | [5 empty] | Not Yet Approved by WFGC |  |  | 0 | 16579
35192290 | [5 empty] | Changed to OH Only
35026643 | [5 empty] | Changed to OH Only | [16 empty] | no bm required oh only no ct
35054184 | [5 empty] | Not Yet Approved by WFGC
35220936 |  |  |  |  | No Date | FRRB - HMB 1103 6012 - PH1 BUTANO | No | No | 0 | 5016 | PN |  |  |  | INPR | 2021-07-15 |  |  |  |  | no |  | 5/25/2021 [REDACTED] accepted the proposal.