## TD Projects
[13 empty] | 21 | 15 | 7 | [6 empty] | 45 | 30 |  | 45 |  | 21 | 21
| Order Number | Description | Notes | O/H Units (miles) | U/G Units (miles) | Designed Units (miles) | 2021 Units (OH/UG) | 2022 Units (OH/UG) | 2023 and Beyond Units (OH/UG) | Construction Start | Construction End | Quick Bid Kick-Off | Cal Days for RFP Docs | Cal Days for Contractor RFP Period | Cal Days for RFP Submissions Review | Cal Days to Request Revised Submittals and Pricing & Execute Agreements | Agreement Execution Date | Base Map Ready Date | Engineering and Design Start | Cal Days to Estimate | EOD | Cal Days to Get ERTC | Cal Days to Get Encroachment Permits | Cal Days to Get Cal Trans/BLM Permits | Cal Days to Get Land Rights | Date Dependencies Cleared | Cal Days for Veg | Cal days to Mobilize Contractor | Winter Work Possible | Construction Days
PSPS | 35223030 | 35223030 (08W) - PSPS - BANGOR 1101 CB - MICROGRID | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
PSPS | 35223039 | 35223039 (08W) - PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | waiting for Tribe to respond to easement request | [6 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-28 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 35061206 | 35061206 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.1 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
| 35061212 | 35061212 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
| 35115151 | 35115151 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | No | 0
| 35115152 | 35115152 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | No | 0
| 35115153 | 35115153 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | No | 0
| 35115154 | 35115154 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | no city or county permit, on private property | [6 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
| 35117443 | 35117443 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
Remove | 35129767 | 35129767 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | [7 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-25 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
Keep | 35142826 | 35142826 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Remove | 35142827 | 35142827 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Remove | 35142828 | 35142828 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 35217268 | 35217268 (08W) - CWSP - BUCKS CREEK 1101 CB PH 1 | [REDACTED] will have updated drawing set and updated cost estimate | [6 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-30 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | No | 0
| 35224712 | 35224712 (08W) - CWSP - BUCKS CREEK 1101 CB PH 2 | EDRS approval for 2022 mob. | [6 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
| 35224713 | 35224713 (08W) - CWSP - BUCKS CREEK 1101 CB PH 3 | [7 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 35217272 | 35217272 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.1 | [7 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
| 35226627 | 35226627 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.2 | CMCS in route for BC to be approvedemail [REDACTED] and submit PO for it for vegreceived eRTC in mayMPP budget 2021 551K | [6 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 180 | 2022-01-19 | 21 | 21 | Yes | 0
| 35226628 | 35226628 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.3 | [7 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-18 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 180 | 2022-01-19 | 21 | 21 | No | 0
| 35226629 | 35226629 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.4
| 35226630 | 35226630 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.5 | CMCS in route for BC to be approved - review eRTC from [REDACTED] and set up a veg date and send out POemail [REDACTED] and submit PO for it for veg
| 35226631 | 35226631 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.6 | CMCS in route for BC to be approvedemail [REDACTED] and submit PO for it for vegBOR - no ground distrubance in BOR easement/land so via TEAMS, confirm no other ground distrubance was going to be distrurbed includng veg work7/1 eRTC date
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 35219260 | 35219260 (08W) - CWSP - WYANDOTTE 110932586 PH 1.1 | on track for 7/1 mob? Submit for Veg PO | [6 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
| 35226700 | 35226700 (08W) - CWSP - WYANDOTTE 110932586 PH 1.2 | waiting for Tribe to respond to permit request eRTC in reviewand will be sent ot be on 6/18 not planning to submit for veg PO until we have tribe easement request back | [6 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 180 | 2022-01-19 | 21 | 21 | Yes | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O/H | U/G | TOTAL | 2021 Miles | 2022 Miles | 2023 Miles
OVERALL MILEAGE |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Note on I4: NAME REDACTED:Recommend 2022 start due to late readiness and adjacent segments in CT RoW.
Note on I10: NAME REDACTED: Unlikely to have UG construction agreement in place for 2021 execution.
Note on I23: NAME REDACTED:Unlikely to have UG contract in place for 2021 work.

## BANGOR - MicroGrid
[5 empty] | Last Update: | 2021-06-16
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
#REF!
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | ED Order #:
Engineering and Estimating | [6 empty] | Project Name:
Y |  |  | Project Engineer - Electric Distribution Engineer |  |  |  | T-Line Order #: |  | needs a FFE PM suborder number to our ED project
Y |  |  | Internal Estimating and Design |  |  |  | Project Name:
Y |  |  | Supervisor of Project Engineer - Supervisor, Service Planning & Design
Y |  |  | Manager of Project Engineer - Manager, Internal Estimating & Design
Project Engineer- T-Line
Y |  |  | Supervisor, T-Line Estimating South
Y |  |  | ADE (Associate Distribution Engineer), ED | SBG5 | N/A |  | Last Update: | 2021-06-16
Y |  |  | ADE (Associate Distribution Engineer), T-Line (works under Fernando)
Y |  |  | System Planning Engineer |  |  | N/A
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
? |  |  | Land Planner |  |  | N/A
Environmental Field Specialist (EFS)
Y |  |  | Land Agent |  |  | N/A
? |  |  | Right of Way Agent |  |  | N/A
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Vegetation Manager
Operations
Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## WYANDOTTE - PSPS Casino
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
#REF!
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | Order #:
Engineering and Estimating | [6 empty] | Project Name:
Project Engineer - Wynadotte 1.1, 1.2
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
|  |  | ADE (Associate Distribution Engineer) - Bucks Creek |  |  |  | Last Update: | 2021-06-15
System Planning Engineer
Contract "Estimator"
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Land Agent
Y |  |  | Right of Way Agent
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Y |  |  | Corporate Sustainability Principal: Trib
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Operations
Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## WYANDOTTE - CWSP Casino
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
Y |  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
M |  |  | Manager, Internal Estimating & Design
Y |  |  | ADE (Associate Distribution Engineer) - Bucks Creek |  | N/A
Y |  |  | Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  | N/A | Last Update: | 2021-06-15
Y | [5 empty] | N/A
Y | [5 empty] | N/A
Y |  |  | CONT - Estimator - CAL ENG |  | N/A | N/A
Y |  |  | Supervisor, Contract Estimating (overseeomg Cal Eng) |  |  | N/A
M |  |  | CONT - Analyst |  | N/A | N/A
M |  |  | Manager, Contract Estimating
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Y |  |  | Senior Land Technician
Y |  |  | Sr. Right of Way Agent |  |  | N/A
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Land Agent
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Y |  |  | Corporate Sustainability Principal: Trib
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 1.2 ? |  |  | N/A
M |  |  | Supervisor, Construction Engineering (oversees FEs)
Clearance Supervisor
PI Inspector
M | [5 empty] | N/A
M | [5 empty] | N/A
M
M |  |  | Supvr, Elctrc Opr Work and Res Plng
M |  |  | Manager, Construction and Resource Mgt
Operations
Y |  |  | Vegetation Program Manager |  |  | N/A
Y |  |  | Sr. Manager of Vegetation Execution, North Valley Region
M |  |  | CONT - CNUC NVS Consult. Utility Forester
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento |  |  | N/A
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Y |  |  | Electric Contract Specialist for Pre-Construction Veg |  | N/A
Contract Specialist (Veg and Construction Contractor) 2 week lead time
K |  |  | Manager, Grid Design
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## BRUNSWICK - Zone
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Electric Distribution Engineer- System Planning Engineer
Contract "Estimator"
Contract "Estimator"
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Y |  |  | Land Planner
Y |  |  | CONT - Land Planner (AECOM) |  | N/A | N/A
Y |  |  | CONT - Land Planner |  | N/A | N/A
Y |  |  | CONT - Land Planner |  | N/A | N/A
Y |  |  | Land Consultant-EP&P, Senior
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 2.1 |  |  | N/A
Y |  |  | FE - PH 2.2
Y |  |  | FE - PH 2.3 |  |  | N/A
Y |  |  | FE - PH 2.4
Y |  |  | FE - PH 2.5 |  |  | N/A
Y |  |  | FE - PH 3.6 |  |  | N/A
Y |  |  | Sr. FE Technician - Hardening PH 2
Y |  |  | Supervisor, Construction Engineering (FE Supervisor for list above)
Y |  |  | Supervisor GC Elect Dist (Lineman Supervisor)
Operations
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento |  |  | N/A
Y |  |  | Supvr, Veg Pgm Mgr, Sierra N/ Sacramento |  |  | N/A
Y |  |  | Vegetation Program Manager |  |  | N/A
Y |  |  | Supervisor, Contract Management
? |  |  | CONT - Consulting Utility Forester |  | N/A | N/A
Y |  |  | Vegetation Management Contract Administrator |  | 925-523-1489 | N/A
Y |  |  | First Field Clerk
Other Support
City/County Permitter
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## BRUNSWICK - Hardenin
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Electric Distribution Engineer- System Planning Engineer
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Y |  |  | Land Planner
Y |  |  | CONT - Land Planner (AECOM) |  | N/A | N/A
Y |  |  | CONT - Land Planner |  | N/A | N/A
Y |  |  | CONT - Land Planner |  | N/A | N/A
Y |  |  | Land Consultant-EP&P, Senior
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 2.1 |  |  | N/A
Y |  |  | FE - PH 2.2
Y |  |  | FE - PH 2.3 |  |  | N/A
Y |  |  | FE - PH 2.4
Y |  |  | FE - PH 2.5 |  |  | N/A
Y |  |  | FE - PH 3.6 |  |  | N/A
Y |  |  | Sr. FE Technician - Hardening PH 2
Y |  |  | Supervisor, Construction Engineering (FE Supervisor for list above)
Y |  |  | Supervisor GC Elect Dist (Lineman Supervisor)
Operations
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento |  |  | N/A
Y |  |  | Supvr, Veg Pgm Mgr, Sierra N/ Sacramento |  |  | N/A
Y |  |  | Vegetation Program Manager |  |  | N/A
Y |  |  | Supervisor, Contract Management
Y |  |  | Vegetation Management Contract Administrator |  |  | N/A
Y |  |  | First Field Clerk
Other Support
Y |  |  | City/County Permitter |  |  | N/A
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## BUCKS CREEK
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
Y |  |  | Project Manager |  |  |  | PM Name:
Y |  |  | Project Controls Analyst (PCA) |  |  | N/A
Y |  |  | Project Controls Analyst (PCA) |  |  | N/A
Y |  |  | Scheduler |  |  | N/A
Y |  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Electric Distribution Engineer |  |  |  | Project Name:
Y |  |  | Sr Eng Est - Elec |  | N/A
K |  |  | Supervisor, Internal Estimating & Design (oversee's Aaron)
Supervisor of Project Engineer - Supervisor, Service Planning & Design
Design & Cost "Estimator"
Y |  |  | ADE (Associate Distribution Engineer - Assoc Dsbn Engr - Elec - Provisional |  | N/A
Y |  |  | ADE (Associate Distribution Engineer) - Bucks Creek |  | N/A
Y |  |  | Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  | N/A | Last Update: | 2021-06-15
Y |  |  | Contract "Estimator" (EEI) - PH 1
Y |  |  | Contract "Estimator" (EEI) - PH 2 |  |  | N/A
Y |  |  | Contract "Estimator" (EEI) - PH 3 |  | N/A
Y |  |  | PG&E Manager - Contract "Estimator"
M |  |  | Contract "Estimator" (EEI) - Support? |  | N/A
M |  |  | Manager of (EEI) Electrical Engineering and Design |  | N/A | N/A
M |  |  | Contract "Estimator" (EEI) - Support? |  | N/A
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Y |  |  | Principal, Land Planner |  | N/A | N/A
Y |  |  | Land Planner |  |  | N/A
Y |  |  | Manager - LP
Y |  |  | Senior Land Agent |  |  | N/A
Y |  |  | Land Agent |  | N/A
Y |  |  | Expert Land Consultant (PGE relations with CalTrans)
Y |  |  | Wildfire Safety & Extl Engagement, Chief
M |  |  | Manager, Land Rights
M |  |  | Manager, Land Rights
M |  |  | Director, Land Management
Y |  |  | Caltrans District 3 – (Encroachment) |  |  | N/A
Y |  |  | Caltrans District 2 – (Encroachment) |  |  | N/A
Caltrans would prefer that we lead the CUPA effort. – Angela Deiana should be consulted on this.
She thinks we likely don’ need a CUPA. She also said a CUPA would like turn this into a 3 – 5 year effort.
Right of Way Agent
Y |  |  | USDA Plumas Forest
Y |  |  | Land Surveryor (north of Modesto area)
Water Specialist
Y |  |  | Land Consultant-Property Mgmt, Principal |  |  | N/A
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Operations
? |  |  | Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
EEI = Energy Experts International
NV = North Valley
SI = Sierra

## KESWICK
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
|  |  | Project Controls Analyst (PCA) |  | N/A | N/A
|  |  | Project Controls Analyst (PCA) |  |  | N/A
|  |  | Scheduler |  |  | N/A
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
Y |  |  | Project Distribution Engineer - Electric Distribution Planning – North Valley |  |  |  | Project Name:
Y |  |  | Electric Distribution Engineer, Asc |  |  | N/A
M |  |  | Design & Cost "Estimator"
Y |  |  | ADE (Associate Distribution Engineer) |  | N/A | N/A
Y |  |  | ADE (Associate Distribution Engineer) |  | N/A | N/A
Y |  |  | Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  | N/A | Last Update: | 2021-06-15
Y |  |  | Contract "Estimator" (EN ENG) PH 1.2 (ejimenez@enengineering.com) |  |  | N/A
Y |  |  | Contract "Estimator" (EN ENG) PH 1.5 |  | N/A
Y |  |  | Contract "Estimator" (EN ENG) PH 1.6 |  | N/A | N/A
Y |  |  | Contract "Estimator" |  | N/A | N/A
Y |  |  | Supervisor, Contract Estimating -West Sa
Y |  |  | CONT - Analyst |  | N/A | N/A
M |  |  | Manager, Contract Estimating
Scoping
|  |  | Scoping - on a PM specialist assignment for Fire Rebuild |  |  | N/A
Land and Environmental Management
Y |  |  | Land Planner |  |  | N/A
Y |  |  | Storm Water |  |  | N/A
Y |  |  | Environmental Field Specialist (Project EFS) - Supervisor, Environmental
(Local EFS)
Right of Way Agent, Land Rights Lead
Y |  |  | CONT - Water Quality Specialist |  | N/A | N/A
Y |  |  | Cultural Resource Specialist, Senior
Y |  |  | Land Surveryor (South Valley)
Y |  |  | Terrestrial Biologist - ESC
Y |  |  | LCE
Y |  |  | HCP Administrator
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
|  |  | Construction Manager, Expert - PH 1, 3, 4 |  |  | N/A
|  |  | Construction Manager, Senior - PH 1, 3, 4 |  |  | N/A
Foreman
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Vegetation Manager
Operations
Y |  |  | Vegetation Program Manager |  |  | N/A
Vegetation Manager
Other Support
Y |  |  | City/County Permitter |  |  | N/A
Y |  |  | Contract Specialist, Expert
M |  |  | Supervisor, Contract Planning
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor |  |  | N/A
NV = North Valley
SI = Sierra

## Roster Example
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Contract "Estimator"
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Vegetation Manager
Operations
Vegetation Manager
Vegetation Manager
Vegetation Management (NV/SI)
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
PM Supervisor
NV = North Valley
SI = Sierra