## TD Projects
08W | 3 = Capital | 7 = capital
diff | 4 = Expense | 8 = expense | [12 empty] | 21 | 15 | 7 | [6 empty] | 45 | 30 |  | 45 |  | 21 | 21
| Order Number | Description | Notes | O/H Units (miles) | U/G Units (miles) | Designed Units (miles) | 2021 Units (OH/UG) | 2022 Units (OH/UG) | 2023 and Beyond Units (OH/UG) | CMCS Approved Date | CMCS EDRS Routing link | Construction Start Ready to Break Ground | Construction End | Quick Bid Kick-Off Pre ENG? | Cal Days for RFP Docs | Cal Days for Contractor RFP Period | Cal Days for RFP Submissions Review | Cal Days to Request Revised Submittals and Pricing & Execute Agreements | Agreement Execution Date | Base Map Ready Date | Engineering and Design Start | Cal Days to Estimate | EOD | Cal Days to Get ERTC | Cal Days to Get Encroachment Permits | Cal Days to Get Cal Trans/BLM Permits | Cal Days to Get Land Rights | Date Dependencies Cleared | Cal Days for Veg | Cal days to Mobilize Contractor | Winter Work Possible | Construction Days
PSPS | 35223030 | 35223030 (08W) - PSPS - BANGOR 1101 CB - MICROGRID | CMCS in email review. Not submitted in EDRS yet. Waiting for T-Line order number. 30% deliverables + KMZ, out 7/13, schedule walk for mid July | 0 | 0.57 |  | 0 | 0.57 | 0 | not submitted |  | 2021-10-29 | 2022-02-06 | 2021-03-22 | 21 | 15 | 7 | 28 | 2021-06-01 | 2021-04-23 | 2021-06-01 | 21 | 2021-06-22 | 45 | 30 | 0 | 45 | 2021-08-06 | 21 | 21 | IDK | 100
PSPS | 35223039 | 35223039 (08W) - PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | working on getting easement from tribe and when do we plan to schedule a walk down - no prelim 30% drawings. Go out for a preconstruction walk after 80%, nearby wyndotte 1.1 and 1.2 | 0 | 0.77 |  | 0 | 0.77 | 0 |  |  | 2021-08-17 | 2021-11-25 | 2021-03-31 | 21 | 15 | 7 | 28 | 2021-06-10 | 2021-06-28 | 2021-06-10 | 21 | 2021-07-01 | 45 | 30 | 180 | 45 | 2021-12-28 | 21 | 21 | No | 100
Totals |  |  |  | 0 | 1.34 | 0 | 0 | 1.34 | 0
| 35061206 | 35061206 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.1 | in construction | 1.73 | 0 |  | 1.73 | 0 | 0 |  |  | 2020-10-25 | 2020-12-16 | 2020-05-20 | 21 | 15 | 7 | 28 | 2020-07-30 | N/A | 2020-07-30 | 21 | 2020-08-20 | 45 | 30 | 0 | 45 | 2020-10-04 | 21 | 21 | Yes | 52
| 35061212 | 35061212 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | in construction | 1.7888 | 0 |  | 1.79 | 0 | 0 |  |  | 2021-09-27 | 2021-11-20 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 54
| 35115151 | 35115151 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | in construction | 1.8958 | 0 |  | 1.8958 | 0 | 0 |  |  | 2021-09-27 | 2021-11-23 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | No | 57
| 35115152 | 35115152 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | in construction | 1.6023 | 0 | 1.5665 | 1.6023 | 0 | 0 |  |  | 2021-10-02 11:35 | 2021-11-19 11:35 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 26.4827 | 2021-07-28 11:35 | 45 | 30 | 0 | 45 | 2021-09-11 11:35 | 21 | 21 | No | 48
| 35115153 | 35115153 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | in construction | 1.7947 | 0 | 1.7947 | 1.7947 | 0 | 0 |  |  | 2021-10-03 06:45 | 2021-11-26 06:45 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-17 | 2021-07-02 | 27.2814 | 2021-07-29 06:45 | 45 | 30 | 0 | 45 | 2021-09-12 06:45 | 21 | 21 | No | 54
| 35115154 | 35115154 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | in construction no city or county permit, on private property | 1.6462 | 0 | 1.6462 | 1.6462 | 0 | 0 |  |  | 2021-10-02 18:17 | 2021-11-20 18:17 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 26.7617 | 2021-07-28 18:17 | 45 | 30 | 0 | 45 | 2021-09-11 18:17 | 21 | 21 | Yes | 49
| 35117443 | 35117443 (08W) - CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | in construction | 2.16 | 0 |  | 2.16 | 0 | 0 |  |  | 2021-09-27 | 2021-12-01 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 65
Totals |  |  |  | 12.6178 | 0 | 5.0074 | 12.619 | 0 | 0
Remove | 35129767 | 35129767 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | [9 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-25 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
Keep | 35142826 | 35142826 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | in construction | 1.57 | 0 |  | 1.57 | 0 | 0 |  |  | 2021-09-27 | 2021-11-13 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 47
Remove | 35142827 | 35142827 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | [9 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Remove | 35142828 | 35142828 (08W) - CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | [9 empty] | 2021-09-27 | 2021-09-27 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 0
Totals |  |  |  | 1.57 | 0 | 0 | 1.57 | 0 | 0
| 35217268 | 35217268 (08W) - CWSP - BUCKS CREEK 1101 CB PH 1 | received 30% prelim drawings 6/17 and we have base map when do plan to get 30% for ph2 and ph3 move construction projects to 2023 | 0.2 | 0 | 0.09 | 0 | 0.2 | 0 | 2021-03-04 | http://www/edrs/pr/DisplayPR.asp?idEDR=1242775 | 2021-09-27 07:34 | 2021-10-03 07:34 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-30 | 2021-07-02 | 21.315 | 2021-07-23 07:34 | 45 | 30 | 0 | 45 | 2021-09-06 07:34 | 21 | 21 | No | 6
| 35224712 | 35224712 (08W) - CWSP - BUCKS CREEK 1101 CB PH 2 | EDRS approval for 2022 mob. Move construction projects to 2023 | 0 | 1.73 |  | 0 | 1.73 | 0 |  |  | 2021-09-27 | 2022-02-04 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 130
| 35224713 | 35224713 (08W) - CWSP - BUCKS CREEK 1101 CB PH 3 | move construction projects to 2023 | 0 | 1.83 |  | 0 | 1.83 | 0 |  |  | 2021-09-27 | 2022-02-11 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 45 | 2021-09-06 | 21 | 21 | Yes | 137
Totals |  |  | 6/21/21 - emailed design team to find out about joint pole tasks and SCADA units either N/A or how many - ? | 0.2 | 3.56 | 0.09 | 0 | 3.76 | 0
| 35217272 | 35217272 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.1 | site walk Drawings are out on 6/21 with a CMCS by 6/23 | [6 empty] | submitted on 6/22 | http://www.utility.pge.com/edrs/default.asp?id=1270892 | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
| 35226627 | 35226627 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.2 | CMCS in route for BC to be approvedreceived qyores from [REDACTED], submit POreceived eRTC in mayMPP budget 2021 551K | [6 empty] | 2021-06-14 | http://www.utility.pge.com/edrs/pr/DisplayPR.asp?idEDR=1253408 | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 180 | 2022-01-19 | 21 | 21 | Yes | 0
| 35226628 | 35226628 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.3 | site walk Drawings are out on 6/21 with a CMCS by 6/23 | [6 empty] | submitted on 6/22 | http://www.utility.pge.com/edrs/default.asp?id=1270890 | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | 2021-06-18 | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 180 | 2022-01-19 | 21 | 21 | No | 0
| 35226629 | 35226629 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.4 | site walk Drawings are out on 6/21 with a CMCS by 6/23 | [6 empty] | submitted on 6/22 | http://www.utility.pge.com/edrs/default.asp?id=1270891
| 35226630 | 35226630 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.5 | CMCS in route for BC to be approved - review eRTC from [REDACTED] and set up a veg date and send out POemail [REDACTED] and submit PO for it for veg material issue? - check email again | [6 empty] | 2021-06-18 | http://www.utility.pge.com/edrs/default.asp?id=1268498
| 35226631 | 35226631 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.6 | CMCS in route for BC to be approvedemail [REDACTED] and submit PO for it for vegBOR - no ground distrubance in BOR easement/land so via TEAMS, confirm no other ground distrubance was going to be distrurbed includng veg work7/1 eRTC date | [6 empty] | 2021-06-16 | http://www.utility.pge.com/edrs/pr/DisplayPR.asp?idEDR=1253424
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 35219260 | 35219260 (08W) - CWSP - WYANDOTTE 110932586 PH 1.1 | on track for 7/1 mob? Submit for Veg PO wait to resubmit BC, b/c drawing set is under ADE review still | [8 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 180 | 45 | 2022-01-19 | 21 | 21 | No | 0
| 35226700 | 35226700 (08W) - CWSP - WYANDOTTE 110932586 PH 1.2 | waiting for Tribe to respond to permit request not planning to submit for veg PO until we have tribe easement request back | [8 empty] | 2022-02-09 | 2022-02-09 | 2021-04-22 | 21 | 15 | 7 | 28 | 2021-07-02 | N/A | 2021-07-02 | 21 | 2021-07-23 | 45 | 30 | 0 | 180 | 2022-01-19 | 21 | 21 | Yes | 0
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | O/H | U/G | TOTAL | 2021 Miles | 2022 Miles | 2023 Miles
OVERALL MILEAGE |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Note on I23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: move out to 2023, will submit the 3 phases to CT as a permit package

## BANGOR - MicroGrid
[5 empty] | Last Update: | 2021-06-16
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
#REF!
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | ED Order #: | 35223030
Engineering and Estimating | [6 empty] | Project Name: | 35223030 (08W) - PSPS - BANGOR 1101 CB - MICROGRID
Y |  |  | Project Engineer - Electric Distribution Engineer |  |  |  | T-Line Order #: |  | needs a FFE PM suborder number to our ED project
Y |  |  | Internal Estimating and Design |  |  |  | Project Name:
Y |  |  | Supervisor of Project Engineer - Supervisor, Service Planning & Design
Y |  |  | Manager of Project Engineer - Manager, Internal Estimating & Design
Project Engineer- T-Line
Y |  |  | Supervisor, T-Line Estimating South
Y |  |  | ADE (Associate Distribution Engineer), ED |  |  |  | Last Update: | 2021-06-16
Y |  |  | ADE (Associate Distribution Engineer), T-Line (works under Fernando)
Y |  |  | System Planning Engineer
lead for WF resiliancy project
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
? |  |  | Land Planner
Environmental Field Specialist (EFS)
Y |  |  | Land Agent
? |  |  | Right of Way Agent
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Vegetation Manager
Operations
Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor

## WYANDOTTE - PSPS Casino
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
#REF!
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Order #: | 35223039
Engineering and Estimating | [6 empty] | Project Name: | 35223039 (08W) - PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE
Project Engineer - Wynadotte 1.1, 1.2
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
|  |  | ADE (Associate Distribution Engineer) - Bucks Creek |  |  |  | Last Update: | 2021-06-15
System Planning Engineer
Y |  |  | CONT - Estimator (Cal Eng) - ([REDACTED]) - PH 1.2
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Land Agent
Y |  |  | Right of Way Agent
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Y |  |  | Corporate Sustainability Principal: Trib
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Operations
Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor
Tribe Chairman

## WYANDOTTE - CWSP Casino
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
PM: [REDACTED] Project ID: (Order #: ) Project:
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
Y |  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
M |  |  | Manager, Internal Estimating & Design
Y |  |  | ADE (Associate Distribution Engineer) - Bucks Creek
Y |  |  | Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Contract "Estimator" - CAL Engineering Solutions ([REDACTED] ) PH 1.1
Y |  |  | CONT - Estimator (Cal Eng) - ([REDACTED]) - PH 1.2
Y |  |  | CONT - Estimator - CAL ENG - PH ???
Y |  |  | Supervisor, Contract Estimating (overseeomg Cal Eng)
M |  |  | CONT - Analyst
M |  |  | Manager, Contract Estimating
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Y |  |  | Senior Land Technician
Y |  |  | Sr. Right of Way Agent
Water Specialist
Y |  |  | Land Surveryor (north of Modesto area)
Land Agent
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Y |  |  | Corporate Sustainability Principal: Trib
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 1.2 ?
M |  |  | Supervisor, Construction Engineering (oversees FEs)
Clearance Supervisor
PI Inspector
M |  |  | Supervisor, Construction Business Operat (Reports to [REDACTED])
M |  |  | Work & Resource Analyst, Senior (Reports to [REDACTED])
M |  |  | Work & Resource Analyst, Senior (reports to [REDACTED], who reports to [REDACTED])
M |  |  | Supvr, Elctrc Opr Work and Res Plng
M |  |  | Manager, Construction and Resource Mgt
Operations
Y |  |  | Vegetation Program Manager
Y |  |  | Sr. Manager of Vegetation Execution, North Valley Region
M |  |  | CONT - CNUC NVS Consult. Utility Forester
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Y |  |  | Electric Contract Specialist for Pre-Construction Veg
Contract Specialist (Veg and Construction Contractor) 2 week lead time
K |  |  | Manager, Grid Design
Y |  |  | PM Supervisor
Tribe Chairman

## BRUNSWICK - Zone
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
PM: [REDACTED] Project ID: (Order #: ) Project:
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Electric Distribution Engineer- System Planning Engineer
Contract "Estimator"
Contract "Estimator"
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Y |  |  | Land Planner
Y |  |  | CONT - Land Planner (AECOM)
Y |  |  | CONT - Land Planner
Y |  |  | CONT - Land Planner
Y |  |  | Land Consultant-EP&P, Senior
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 2.1
Y |  |  | FE - PH 2.2
Y |  |  | FE - PH 2.3
Y |  |  | FE - PH 2.4
Y |  |  | FE - PH 2.5
Y |  |  | FE - PH 3.6
Y |  |  | Sr. FE Technician - Hardening PH 2
Y |  |  | Supervisor, Construction Engineering (FE Supervisor for list above)
Y |  |  | Supervisor GC Elect Dist (Lineman Supervisor)
Operations
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento
Y |  |  | Supvr, Veg Pgm Mgr, Sierra N/ Sacramento
Y |  |  | Vegetation Program Manager
Y |  |  | Supervisor, Contract Management
? |  |  | CONT - Consulting Utility Forester
Y |  |  | Vegetation Management Contract Administrator
Y |  |  | First Field Clerk
Other Support
City/County Permitter
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor

## BRUNSWICK - Hardenin
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
PM: [REDACTED] Project ID: (Order #: ) Project:
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Electric Distribution Engineer- System Planning Engineer
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Y |  |  | Land Planner
Y |  |  | CONT - Land Planner (AECOM)
Y |  |  | CONT - Land Planner
Y |  |  | CONT - Land Planner
Y |  |  | Land Consultant-EP&P, Senior
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Y |  |  | LCE SPO Program Manager, Expert
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Y |  |  | FE - PH 1.1
Y |  |  | FE - PH 2.1
Y |  |  | FE - PH 2.2
Y |  |  | FE - PH 2.3
Y |  |  | FE - PH 2.4
Y |  |  | FE - PH 2.5
Y |  |  | FE - PH 3.6
Y |  |  | Sr. FE Technician - Hardening PH 2
Y |  |  | Supervisor, Construction Engineering (FE Supervisor for list above)
Y |  |  | Supervisor GC Elect Dist (Lineman Supervisor)
Operations
Y |  |  | Vegetation Program Manager- EA Sierra North/Sacramento
Y |  |  | Supvr, Veg Pgm Mgr, Sierra N/ Sacramento
Y |  |  | Vegetation Program Manager
Y |  |  | Supervisor, Contract Management
Y |  |  | Vegetation Management Contract Administrator
Y |  |  | First Field Clerk
Other Support
Y |  |  | City/County Permitter
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor

## BUCKS CREEK
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
PM: [REDACTED] Project ID: (Order #: ) Project:
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
Y |  |  | Project Manager |  |  |  | PM Name:
Y |  |  | Project Controls Analyst (PCA)
Y |  |  | Project Controls Analyst (PCA)
Y |  |  | Scheduler
Y |  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Electric Distribution Engineer |  |  |  | Project Name:
Y |  |  | Sr Eng Est - Elec
K |  |  | Supervisor, Internal Estimating & Design (oversee's Aaron)
Supervisor of Project Engineer - Supervisor, Service Planning & Design
Design & Cost "Estimator"
Y |  |  | ADE (Associate Distribution Engineer - Assoc Dsbn Engr - Elec - Provisional
Y |  |  | ADE (Associate Distribution Engineer) - Bucks Creek
Y |  |  | Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Y |  |  | Contract "Estimator" (EEI) - PH 1
Y |  |  | Contract "Estimator" (EEI) - PH 2
Y |  |  | Contract "Estimator" (EEI) - PH 3
Y |  |  | PG&E Manager - Contract "Estimator"
M |  |  | Contract "Estimator" (EEI) - Support?
M |  |  | Manager of (EEI) Electrical Engineering and Design
M |  |  | Contract "Estimator" (EEI) - Support?
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Y |  |  | Principal, Land Planner
Y |  |  | Land Planner
Y |  |  | Manager - LP
Y |  |  | Senior Land Agent
Y |  |  | Land Agent
Y |  |  | Expert Land Consultant (PGE relations with CalTrans)
Y |  |  | Wildfire Safety & Extl Engagement, Chief
M |  |  | Manager, Land Rights
M |  |  | Manager, Land Rights
M |  |  | Director, Land Management
Y |  |  | Caltrans District 3 – (Encroachment)
Y |  |  | Caltrans District 2 – (Encroachment)
Caltrans would prefer that we lead the CUPA effort. – [REDACTED] should be consulted on this.
She thinks we likely don’ need a CUPA. She also said a CUPA would like turn this into a 3 – 5 year effort.
Right of Way Agent
Y |  |  | USDA Plumas Forest
Y |  |  | Land Surveryor (north of Modesto area)
Water Specialist
Y |  |  | Land Consultant-Property Mgmt, Principal
Biologist
Cultural Resouce Specialist
Y |  |  | LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Operations
? |  |  | Vegetation Manager
Vegetation Manager
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
Y |  |  | PM Supervisor

## KESWICK
[5 empty] | Last Update: | 2021-06-18
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
#REF!
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
Y |  |  | Project Manager |  |  |  | PM Name:
Y |  |  | Project Controls Analyst (PCA)
Y |  |  | Project Controls Analyst (PCA)
Y |  |  | Scheduler
Y |  |  | Program Manager for O8W |  |  |  | Project Name: | 35217272 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.1
Engineering and Estimating | [7 empty] | 35226627 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.2 | July mob
Y |  |  | Electric Distribution Planning – North Valley |  |  |  |  | 35226628 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.3
Y |  |  | Electric Distribution Engineer, Asc |  |  |  |  | 35226629 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.4
Y |  |  | Grid Designer - Electric Distribuiton Engineer, Senior - System Planning Engineer |  |  |  |  | 35226630 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.5 | July mob
M |  |  | Design & Cost "Estimator" |  |  |  |  | 35226631 (08W) - CWSP - KESWICK 1101 LR 1586 PH 1.6 | July mob
Y |  |  | ADE (Associate Distribution Engineer)
Y |  |  | ADE (Associate Distribution Engineer) |  |  |  | Last Update: | 2021-06-18
Y |  |  | Contract "Estimator" (EN ENG) PH 1.2 ([REDACTED])and for PH 1, 3, 4
Y |  |  | Contract "Estimator" (EN ENG) PH 1.5
Y |  |  | Contract "Estimator" (EN ENG) PH 1.6
Y |  |  | Contract "Estimator"
Y |  |  | Supervisor, Contract Estimating -West Sa
Y |  |  | CONT - Analyst
M |  |  | Manager, Contract Estimating
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Y |  |  | Land Planner
Y |  |  | Storm Water
Y |  |  | Environmental Field Specialist (Project EFS) - Supervisor, Environmental
Y |  |  | Utility Forester/Arborist (CONT - CNUC NVS Consult. Utility Forester)
(Local EFS)
Right of Way Agent, Land Rights Lead
Y |  |  | CONT - Water Quality Specialist
Y |  |  | Cultural Resource Specialist, Senior
Y |  |  | Land Surveryor (South Valley)
Y |  |  | Terrestrial Biologist - ESC
Y |  |  | LCE
Y |  |  | HCP Administrator
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Y |  |  | Construction Manager, Expert - PH 1, 3, 4 Site Walk
Y |  |  | Construction Manager, Expert - PH 1, 3, 4 Site Walk
Construction Manager, Expert - PH 2, 5, 6 Construction July 2021 - BC in review
PAR PM
PAR Superintendent
Operations
Y |  |  | Vegetation Program Manager
Vegetation Manager
Other Support
Y |  |  | City/County Permitter
Y |  |  | Contract Specialist, Expert
M |  |  | Supervisor, Contract Planning
Y |  |  | PM Supervisor

## Roster Example
[5 empty] | Last Update: | 2021-06-15
PROJECT TEAM RESOURCE ROSTER | [7 empty] | ENTER VALUES BELOW
PM: [REDACTED] Project ID: (Order #: ) Project:
# | First Name | Last Name | Position | LAN ID or Email | Mobile Phone | Office Phone
Project Management
|  |  | Project Manager |  |  |  | PM Name:
Project Controls Analyst (PCA)
Project Controls Analyst (PCA)
Scheduler
|  |  | Program Manager for O8W |  |  |  | Project ID:
Engineering and Estimating | [6 empty] | Order #:
|  |  | Project Engineer - Wynadotte 1.1, 1.2 |  |  |  | Project Name:
Design & Cost "Estimator"
ADE (Associate Distribution Engineer)
ADE (Associate Distribution Engineer) - Bucks Creek
|  |  | System Planning Engineer |  |  |  | Last Update: | 2021-06-15
Contract "Estimator"
Contract "Estimator"
Contract "Estimator"
Contract "Estimator" - PG&E Manager oversee EEI
Contract "Estimator" - PG&E Manager oversee EN ENG
Scoping
Scoping - on a PM specialist assignment for Fire Rebuild
Land and Environmental Management
Land Planner
Environmental Field Specialist (EFS)
Land Agent
Right of Way Agent
Water Specialist
Land Surveryor (north of Modesto area)
Land Surveryor (South Valley)
Land Surveryor (Coast & Bay Region/Solano County area)
Biologist
Cultural Resouce Specialist
LCE
Customer Impact and Government Relations
Local Customer Experience / Impact Specialist
Government Relations Specialist
Tribe Liason
Construction and Clearance Team
Construction Lead (Field Eng/Const Mgr)
Construction Contractor
Clearance Writer
Clearance Supervisor
PI Inspector
Vegetation Manager
Operations
Vegetation Manager
Vegetation Manager
Vegetation Management (NV/SI)
Other Support
City/County Permitter
City/County Permitter-Agency Liason for PGE
Safety Representative
Contract Specialist (Veg and Construction Contractor) 2 week lead time
PM Supervisor

## Sheet2
CRS Contacts