## 08W Mastersheet
[17 empty] | 32272 | 0 | 0 | 32272 | 6.1121 | 6.1121 | 0 | 0 | 6.1121 | 32272 | 0 | 6.1121 | 0 |  | 50141366 | 0 | 27175453 | 0 | 0 | 1029238.1 |  | 20594959.5 | 0 | 0 | 30808718 | 27659636 | 3149082 | 22501976 | 8306742 | 22501972.5 | 1691196 | 15845.7 | 1675350.3 | 0 | 0 | 0 | 1029238.5 | 0 | 0 | 0 | 3749 | 9613 | 456225 | 543806 | 1742653 | 5165415 | 6484765 | 2055607 | 9661228 | 1536580 | 0
Order# | Order Desc | WBS Element | Planning Order | User Status | MAT | Job Owner | Job Owner Desc | PCA LanID | PCA | Schedule PCA LanID | Schedule PCA | Project Reporting Year | Operative Year | Program | Work Center | Rec Cost Center Desc | UG Feet | OH Feet | Removal | Planned Circuit Feet | Planned Circuit Miles | 2021 Forecast Miles | 2022 Forecast Miles | Total Installed Miles | Remaining Planned Miles | SAP Plan Feet | SAP Actual Feet | SAP Plan Miles | SAP Actual Miles | Resource | Authorized Amount | Total Contingency | AJE Amt | Funded Contingency | Base Estimate | SinceIncepsion | Open Commitment | Project Remainning Budget | Project Budget Status | MPP Budget Status | MPP Approved Budget (2021) | 2021 EAC PRJ | 2021 MPP Budget - 2021 EAC PRJ | 2021 EAC PRM Version | 2021 MPP Budget - 2021 EAC PRM | EAC PRM | Current Month Plan | Current Month Actual | Current Month Variance | 2018 Actuals | 2019 Actuals | 2020 Actuals | 2021 Actuals to date | 2022 Forecast | 2023 Forecast | Jan2021 PRJ | Feb2021 PRJ | Mar2021 PRJ | Apr2021 PRJ | May2021 PRJ | Jun2021 PRJ | Jul2021 PRJ | Aug2021 PRJ | Sep2021 PRJ | Oct2021 PRJ | Nov2021 PRJ | Dec2021 PRJ | Data Date | Current Baseline ID | Baseline Type | Baseline Name | Baseline CreateDate | Finish Date - Estimating End Date "Pend-In" (DS18) | Milestone Status - Estimating End Date "Pend-In" (DS18) | Start Date - Prepare & Route Business Case/PA | Finish Date - Prepare & Route Business Case/PA | Milestone Status - PA/Business Case Approved | Finish Date - All Permits Received | Milestone Status - All Permits Received | Finish Date - PM Release to Construction | Milestone Status - PM Release to Construction | Start Date - Order Material | Finish Date - Order Material | Activity Status - Order Material | Start Date - Materials Received | Finish Date - Materials Received | Activity Status - Materials Received | Start Date - Veg Field Work | Finish Date - Veg Field Work | Activity Status - Veg Field Work | Finish Date - Construction Start | Milestone Status - Construction Start | Finish Date - Start of Civil Construction | Milestone Status - Start of Civil Construction | Finish Date - Civil Construction Complete | Milestone Status - Civil Construction Complete | Finish Date - Start of Electric Construction | Milestone Status - Start of Electric Construction | Finish Date - Electric Construction Complete | Milestone Status - Electric Construction Complete | Finish Date - Operative Date | Milestone Status -Operative Date | BL Finish Date - In-Service Date | Finish Date - In-Service Date | BL - Expected Finish Date for In Service Date | Schedule Status | Milestone Status In-Service Date | Start Date - Site Restoration | Finish Date - Site Restoration | Activity Status - Site Restoration | Finish Date - Project Close (CMPL) | Milestone Status - Project Close (CMPL)
31462406 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | 5783289 | ADER | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 | E.5015235.01 | 5783907 | ADER | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 7703 | 0 | 7703 | 1.4589 | 0 | 0 | 0 | 1.4589 | [5 empty] | 500000 | 250000 | 250000 |  |  | 183978.5 | 0 | 66021.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 30787 | -30787 | 30787 | -30787 | 2715635.8 | 323.9 | 0 | 323.9 | 0 | 32246.9 | 121772.5 | 29959 | 2530829.6 | 0 | 87 | 16259 | 11099 | 1103 | 1412 | 324 | 336 | 168 | 0 | 0 | 0 | 0 | 2021-06-18 | 154960 | BL-B | BL-B 35072361_CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-07 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-02-18 | Not Started | 2022-02-21 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-03-28 | Not Started | 2022-03-21 | 2022-04-01 | Not Started | 2022-06-06 | Not Started |  |  |  |  | 2022-06-06 | Not Started |  |  | 2022-08-15 | Not Started | 2022-09-14 | 2022-09-14 | 0 | On/ Ahead Schedule | Not Started | 2022-08-22 | 2022-09-05 | Not Started | 2022-11-04 | Not Started
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 | E.5014746.01 | 5785240 | ADER | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8931 | 0 | 8931 | 1.6915 | 0 | 0 | 0 | 1.6915 | [5 empty] | 250000 | 0 | 250000 |  |  | 64960.4 | 0 | 185039.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -108016 | 108016 | -108016 | 108016 | 86871.1 | 63.4 | 132 | -68.6 | 0 | 5729.7 | 167571.5 | -108340.8 | 21585.9 | 0 | -156559 | 46861 | 366 | 363 | 496 | 63 | 66 | 66 | 66 | 66 | 66 | 66 | 2021-06-18 |  |  |  |  | 2022-07-08 | Not Started | 2022-07-12 | 2022-07-12 | Not Started | 2021-06-18 | Not Started | 2022-07-26 | Not Started | 2022-07-13 | 2022-07-13 | Not Started | 2022-07-14 | 2022-07-14 | Not Started | 2021-06-21 | 2021-11-03 | Not Started | 2022-07-29 | Not Started |  |  |  |  | 2022-07-29 | Not Started | 2022-08-03 | Not Started | 2022-08-19 | Not Started | 2022-11-11 | 2022-11-11 | 0 | On/ Ahead Schedule | Not Started | 2022-11-14 | 2022-11-25 | Not Started | 2023-01-03 | Not Started
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 | E.5014721.01 | 5785223 | ADER | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 1027 | 8562 | 0 | 9589 | 1.8161 | 0 | 0 | 0 | 1.8161 | [5 empty] | 300000 | 0 | 300000 |  |  | 176967.1 | 0 | 123032.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 30119 | -30119 | 30119 | -30119 | 194229.1 | 286.2 | 0 | 286.2 | 0 | 10638.5 | 138253.5 | 28075 | 15217.9 | 0 | 908 | 13512 | 11664 | 996 | 996 | 286 | 293 | 293 | 293 | 293 | 293 | 293 | 2021-06-18 | 145823 | BL-A: | BL-A: 35094519_CWSP - ORO FINO 1102 - LR2560 PH 1.1_08W - June 2021 | 2020-07-24 | 2022-03-15 | Not Started | 2022-03-17 | 2022-03-30 | Not Started | 2022-03-15 | Not Started | 2022-03-30 | Not Started | 2022-04-13 | 2022-04-13 | Not Started | 2022-04-14 | 2022-07-06 | Not Started | 2022-03-16 | 2022-04-12 | Not Started | 2022-07-21 | Not Started |  |  |  |  | 2022-07-21 | Not Started | 2022-09-23 | Not Started | 2022-11-03 | Not Started | 2021-06-04 | 2023-01-13 | -588 | Behind Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-07 | Not Started
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 | E.5014720.01 | 5785224 | ADER | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8398 | 0 | 8398 | 1.5905 | 0 | 0 | 0 | 1.5905 | [5 empty] | 100000 | 0 | 100000 |  |  | 64956.4 | 0 | 35043.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 21807 | -21807 | 21807 | -21807 | 84539.1 | 726.9 | 132 | 594.9 | 0 | 10791.4 | 37404.6 | 16760.4 | 14535.8 | 0 | -4698 | 17888 | 2577 | 365 | 497 | 727 | 733 | 737 | 741 | 714 | 748 | 780 | 2021-06-18 |  |  |  |  | 2022-07-08 | Not Started | 2022-07-29 | 2022-08-04 | Not Started | 2022-07-28 | Not Started | 2022-08-11 | Not Started | 2022-07-11 | 2022-07-11 | Not Started | 2022-07-12 | 2022-07-18 | Not Started | 2022-07-29 | 2022-08-04 | Not Started | 2022-09-16 | Not Started |  |  |  |  | 2022-09-16 | Not Started | 2022-11-24 | Not Started | 2022-12-16 | Not Started | 2022-12-23 | 2022-12-23 | 0 | On/ Ahead Schedule | Not Started | 2022-12-26 | 2023-01-06 | Not Started | 2023-02-14 | Not Started
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | E.5014742.01 | 5785227 | ADER | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 953 | 5606 | 0 | 6559 | 1.2422 | 0 | 0 | 0 | 1.2422 | [5 empty] | 1 | -624999 | 625000 |  |  | 156300.3 | 0 | 468699.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 57948 | -57948 | 57948 | -57948 | 2851554.5 | 0 | 0 | 0 | 0 | 15732.5 | 82619.7 | 57948 | 2695254.2 | 0 | 59780 | -49191 | 45303 | 949 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154950 | BL-B | BL-B 35095163_CWSP - PINE GROVE 1102 - LR1222 - PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-27 | Not Started | 2022-01-31 | 2022-02-18 | Not Started | 2022-01-07 | Not Started | 2022-02-18 | Not Started | 2022-02-21 | 2022-02-22 | Not Started | 2022-02-23 | 2022-03-08 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-03-16 | Not Started |  |  |  |  | 2022-03-16 | Not Started | 2022-05-02 | Not Started | 2022-05-02 | Not Started | 2022-05-05 | 2022-05-05 | 0 | On/ Ahead Schedule | Not Started | 2022-05-10 | 2022-05-11 | Not Started | 2022-06-23 | Not Started
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | E.5014727.04 | 5786003 | ADER | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 9021 | 0 | 9021 | 1.7085 | 0 | 0 | 0 | 1.7085 | [5 empty] | 1 | -329999 | 330000 |  |  | 104573.4 | 0 | 225426.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -1729 | 1729 | -1729 | 1729 | 1785912.4 | 74 | 0 | 74 | 0 | 562.7 | 105813.7 | -1802.9 | 1681265 | 0 | 55730 | -59294 | 590 | 586 | 586 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154937 | BL-B | BL-B 35112974_CWSP - WEST POINT 1101 -LR 13444- PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-01-10 | Not Started | 2022-01-17 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-03-09 | Not Started |  |  |  |  | 2022-03-09 | Not Started | 2022-04-26 | Not Started | 2022-04-26 | Not Started | 2022-05-26 | 2022-05-26 | 0 | On/ Ahead Schedule | Not Started | 2022-05-04 | 2022-05-17 | Not Started | 2022-07-18 | Not Started
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | E.5014727.05 | 5786004 | ADER | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 7634 | 0 | 7634 | 1.4458 | 0 | 0 | 0 | 1.4458 | [5 empty] | 1 | -329999 | 330000 |  |  | 83671.5 | 0 | 246328.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -13842 | 13842 | -13842 | 13842 | 1698309.1 | 0 | 0 | 0 | 0 | 235.3 | 97278.1 | -13841.9 | 1614637.6 | 0 | 24564 | -39815 | 472 | 469 | 469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154938 | BL-B | BL-B 35112975_CWSP - WEST POINT 1101 -LR 13444- PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-25 | Not Started | 2021-11-26 | 2022-01-06 | Not Started | 2021-12-28 | Not Started | 2022-01-06 | Not Started | 2022-01-07 | 2022-01-07 | Not Started | 2022-01-10 | 2022-02-04 | Not Started | 2021-12-01 | 2021-12-14 | Not Started | 2022-03-11 | Not Started |  |  |  |  | 2022-03-11 | Not Started | 2022-05-16 | Not Started | 2022-05-16 | Not Started | 2022-06-15 | 2022-06-15 | 0 | On/ Ahead Schedule | Not Started | 2022-05-24 | 2022-06-06 | Not Started | 2022-08-05 | Not Started
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 | E.5014728.03 | 5786013 | ADER | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7001 | 0 | 7001 | 1.3259 | 0 | 0 | 0 | 1.3259 | [5 empty] | 1 | -249999 | 250000 |  |  | 94098.6 | 0 | 155901.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 56477 | -56477 | 56477 | -56477 | 2695411.1 | 0 | 0 | 0 | 0 | 580.3 | 37041.6 | 56476.7 | 2601312.5 | 0 | 87684 | -32797 | 532 | 529 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154943 | BL-B | BL-B 35113994_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-10 | Not Started | 2021-11-11 | 2021-12-22 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-20 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-02-18 | Not Started |  |  |  |  | 2022-02-18 | Not Started | 2022-04-18 | Not Started | 2022-04-18 | Not Started | 2022-05-18 | 2022-05-18 | 0 | On/ Ahead Schedule | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-07-08 | Not Started
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | E.5014742.08 | 5786137 | ADER | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 8212 | 0 | 8212 | 1.5553 | 0 | 0 | 0 | 1.5553 | [5 empty] | 1 | -624999 | 625000 |  |  | 73863.4 | 0 | 551136.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 22839 | -22839 | 22839 | -22839 | 1732572.2 | 236.8 | 0 | 236.8 | 0 | 235.3 | 51148.9 | 22479.3 | 1658349.3 | 0 | 30740 | -28105 | 19013 | 416 | 416 | 237 | 123 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154956 | BL-0 | BL-0 35114053_CWSP - PINE GROVE 1102 - LR1222 - PH 2.8_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-02-25 | Not Started | 2022-02-28 | 2022-03-25 | Not Started | 2022-04-28 | Not Started | 2022-04-29 | Not Started | 2022-03-28 | 2022-03-28 | Not Started | 2022-03-29 | 2022-04-25 | Not Started | 2022-04-29 | 2022-05-12 | Not Started | 2022-07-11 | Not Started |  |  |  |  | 2022-07-11 | Not Started | 2022-09-06 | Not Started | 2022-09-20 | Not Started | 2022-10-20 | 2022-10-20 | 0 | On/ Ahead Schedule | Not Started | 2022-10-21 | 2022-11-03 | Not Started | 2022-12-12 | Not Started
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | E.5014723.04 | 5785937 | ADER | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11352 | 0 | 11352 | 2.15 | 0 | 0 | 0 | 2.15 | [5 empty] | 250000 | 0 | 250000 |  |  | 174033.1 | 0 | 75966.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 142356 | -142356 | 142356 | -142356 | 3206370.3 | 76.9 | 0 | 76.9 | 0 | 560.9 | 32693.2 | 140778.9 | 3030760.3 | 0 | 200954 | -64682 | 976 | 2553 | 978 | 77 | 0 | 0 | 0 | 0 | 0 | 1500 | 2021-06-18 | 160672 | BL-A1 | BL-A1 35115048_CWSP - MIWUK 1701 - LR 10600 PH 1.4_08W - DD 210507 | 2021-05-13 | 2022-01-03 | Not Started | 2022-01-04 | 2022-01-17 | Not Started | 2022-02-28 | Not Started | 2022-03-01 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-15 | Not Started | 2022-01-25 | 2022-03-07 | Not Started | 2022-04-07 | Not Started |  |  |  |  | 2022-04-07 | Not Started | 2022-06-10 | Not Started | 2022-07-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-22 | Not Started
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | E.5014540.04 | 5786032 | ADER | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 6326 | 0 | 6326 | 1.1981 | 0 | 0 | 0 | 1.1981 | [5 empty] | 1 | -124999 | 125000 |  |  | 59187.9 | 0 | 65812.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -25486 | 25486 | -25486 | 25486 | 2007593.7 | 0 | -827.2 | 827.2 | 0 | 1898.5 | 83602.2 | -26312.8 | 1947578.6 | 0 | -40729 | 14230 | 340 | 337 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154909 | BL-B | BL-B 35116923_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2022-02-01 | Not Started | 2022-02-07 | 2022-03-18 | Not Started | 2022-02-01 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-02-08 | 2022-03-11 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started | 2022-06-15 | Not Started | 2022-06-29 | Not Started | 2022-08-30 | 2022-08-30 | 0 | On/ Ahead Schedule | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-10-20 | Not Started
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | E.5014540.06 | 5786034 | ADER | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 8968 | 0 | 8968 | 1.6985 | 0 | 0 | 0 | 1.6985 | [5 empty] | 1 | -124999 | 125000 |  |  | 72396.4 | 0 | 52603.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4409 | -4409 | 4409 | -4409 | 2298527.6 | 131.6 | 0 | 131.6 | 0 | 0 | 68187.2 | 4209.1 | 2225931.4 | 0 | -17964 | 20724 | 409 | 406 | 634 | 132 | 68 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154911 | BL-B | BL-B 35116925_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2022-02-02 | Not Started | 2022-02-07 | 2022-03-18 | Not Started | 2022-02-02 | Not Started | 2022-03-18 | Not Started | 2022-03-21 | 2022-03-21 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-02-02 | 2022-03-01 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started | 2022-07-04 | Not Started | 2022-07-18 | Not Started | 2022-09-16 | 2022-09-16 | 0 | On/ Ahead Schedule | Not Started | 2022-09-19 | 2022-09-30 | Not Started | 2022-11-08 | Not Started
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | E.5014721.02 | 5786759 | ADER | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 46 | 9382 | 0 | 9428 | 1.7856 | 0 | 0 | 0 | 1.7856 | [5 empty] | 100000 | -100000 | 200000 |  |  | 105215.3 | 0 | 94784.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16168 | -16168 | 16168 | -16168 | 119051.1 | 95.8 | 0 | 95.8 | 0 | 235.3 | 89499 | 15481.1 | 13148.9 | 0 | 547 | 13167 | 584 | 592 | 592 | 96 | 99 | 99 | 99 | 99 | 99 | 99 | 2021-06-18 | 160856 | BL-A2 | BL-A2: 35129304_CWSP - ORO FINO 1102 - LR2560 PH 1.2_08W - May 21 | 2021-05-18 | 2022-06-17 | Not Started | 2022-06-21 | 2022-07-04 | Not Started | 2022-05-27 | Not Started | 2022-07-04 | Not Started | 2022-07-05 | 2022-07-05 | Not Started | 2022-07-06 | 2022-09-27 | Not Started | 2022-06-03 | 2022-06-03 | Not Started | 2022-09-28 | Not Started |  |  |  |  | 2022-09-28 | Not Started | 2022-12-01 | Not Started | 2022-12-14 | Not Started | 2023-01-20 | 2023-02-03 | -14 | Behind Schedule | Not Started | 2023-02-06 | 2023-02-10 | Not Started | 2023-03-28 | Not Started
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | E.5014724.02 | 5786775 | ADER | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8596 | 0 | 8596 | 1.628 | 0 | 0 | 0 | 1.628 | [5 empty] | 250000 | 0 | 250000 |  |  | 81932.8 | 0 | 168067.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 70697 | -70697 | 70697 | -70697 | 110932.9 | 642.2 | 132 | 510.2 | 0 | 0 | 15683 | 66249.7 | 24552.6 | 0 | 105787 | -41181 | 462 | 459 | 591 | 642 | 647 | 651 | 654 | 630 | 662 | 694 | 2021-06-18 | 160789 | BL-A_ | BL-A_35129649_CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2_08W_May.2021 | 2021-05-17 | 2022-06-23 | Not Started | 2022-07-08 | 2022-07-14 | Not Started | 2022-07-07 | Not Started | 2022-07-21 | Not Started | 2022-06-24 | 2022-06-24 | Not Started | 2022-06-27 | 2022-09-16 | Not Started | 2022-07-08 | 2022-07-21 | Not Started | 2022-10-17 | Not Started |  |  |  |  | 2022-10-17 | Not Started | 2022-12-16 | Not Started | 2023-01-13 | Not Started | 2023-01-31 | 2023-02-14 | -14 | Behind Schedule | Not Started | 2023-02-15 | 2023-02-28 | Not Started | 2023-04-06 | Not Started
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | E.5014724.08 | 5786781 | ADER | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8397 | 0 | 8397 | 1.5903 | 0 | 0 | 0 | 1.5903 | [5 empty] | 250000 | 0 | 250000 |  |  | 81986.5 | 0 | 168013.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 71183 | -71183 | 71183 | -71183 | 112747.6 | 0 | 0 | 0 | 0 | 0 | 10803.6 | 71182.8 | 30761.1 | 0 | 116848 | -47049 | 464 | 460 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2022-06-16 | Not Started | 2022-06-20 | 2022-07-01 | Not Started | 2022-08-11 | Not Started | 2022-08-12 | Not Started | 2022-07-04 | 2022-07-04 | Not Started | 2022-07-05 | 2022-11-07 | Not Started | 2022-06-10 | 2022-06-23 | Not Started | 2022-12-16 | Not Started |  |  |  |  | 2022-12-16 | Not Started | 2023-03-08 | Not Started | 2023-04-06 | Not Started | 2023-05-04 | 2023-05-04 | 0 | On/ Ahead Schedule | Not Started | 2023-05-05 | 2023-05-18 | Not Started | 2023-06-26 | Not Started
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | E.5015549.02 | 5789698 | ADER | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 7561 | 0 | 7561 | 1.432 | 0 | 0 | 0 | 1.432 | [5 empty] | 250000 | 0 | 250000 |  |  | 97166.2 | 0 | 152833.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3317 | -3317 | 3317 | -3317 | 2824802 | 21.8 | 0 | 21.8 | 0 | 0 | 93949.9 | 3216.3 | 2727534.9 | 0 | 562 | 1013 | 550 | 546 | 546 | 22 | 23 | 23 | 23 | 11 | 0 | 0
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | E.5015549.03 | 5789699 | ADER | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 106 | 3432 | 0 | 3538 | 0.67008 | 0 | 0 | 0 | 0.67008 | [5 empty] | 250000 | 0 | 250000 |  |  | 91812.3 | 0 | 158187.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3394 | -3394 | 3394 | -3394 | 1390064.3 | 17.6 | 0 | 17.6 | 0 | 0 | 88517.9 | 3294.5 | 1298152.1 | 0 | 529 | 1214 | 520 | 516 | 516 | 18 | 18 | 18 | 18 | 18 | 9 | 0
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | E.5015549.08 | 5789704 | ADER | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 5910 | 5015 | 0 | 10925 | 2.0691 | 0 | 0 | 0 | 2.0691 | [5 empty] | 250000 | 0 | 250000 |  |  | 60567.2 | 0 | 189432.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 46693 | -46693 | 46693 | -46693 | 3847121.5 | 22.5 | 0 | 22.5 | 0 | 0 | 13978.6 | 46588.5 | 3786450.1 | 0 | 44678 | 885 | 344 | 341 | 341 | 23 | 23 | 23 | 23 | 12 | 0 | 0
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | E.5033918.01 | 5790119 | ADER | 08W | [6 empty] | 2022 |  | SH | CLRLAKE | Humboldt Division Assets | 0 | 3761 | 0 | 3761 | 0.71231 | 0 | 0.71231 | 0 | 0.71231 | 3567 | 0 | 0.67557 | 0 |  | 67857 | 0 | 67857 |  |  | 55943 | 0 | 11914 | On/Under Budget | Budget Allocated | 300000 | 18436 | 281564 | 18436 | 281564 | 33879.5 | 2258.2 | 27806.7 | -25548.5 | 0 | 0 | 13053 | 42890 | 2290 | 100.6 | 697 | 8560 | 2148 | 3520 | 159 | 2258 | 182 | 182 | 182 | 182 | 182 | 182 | 2021-06-18 | 159751 | BL-A: | BL-A: 35174479_ECOP-Middletown 1101-H12-LR548-Ph2_08W - Apr 21 | 2021-04-28 | 2022-03-21 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2022-03-22 | 2022-03-22 | Not Started | 2022-03-23 | 2022-04-12 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | E.5034355.01 | 5541305 | ADER | 08W | [6 empty] | 2022 |  | SH | SNRAFAEL | North Bay Assets | 6177.6 | 0 | 0 | 6177.6 | 1.17 | 0 | 1.1701 | 0 | 1.17 | 6767 | 0 | 1.2816 | 0 |  | 312500 | 0 | 312500 |  |  | 56034.1 | 0 | 256465.9 | On/Under Budget | Request 2021 Budget | 0 | 93601 | -93601 | 93601 | -93601 | 100996.3 | 20000 | -24962.2 | 44962.2 | 0 | 0 | 7395.4 | 48638.7 | 0 | 0 | 9868 | -329 | 1733 | 1762 | 60568 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 156498 | BL-A | BL-A 35191319_ECOP - LAS GALLINAS A 1105 - H01-LR99904_08W - DD 210219 Feb. 2021 | 2021-03-01 | 2021-07-07 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-09-17 | Not Started | 2021-09-20 | Not Started | 2021-07-08 | 2021-07-08 | Not Started | 2021-07-09 | 2021-07-29 | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-10-13 | Not Started | 2021-10-13 | Not Started | 2021-10-26 | Not Started | 2021-10-13 | Not Started | 2022-01-25 | Not Started | 2022-02-23 | Not Started | 2022-03-28 | 2022-03-01 | 27 | On/ Ahead Schedule | Not Started | 2022-03-10 | 2022-03-23 | Not Started | 2022-04-28 | Not Started
35219590 | CWSP - VACA DIXON 1105965390 | E.5034704.01.02 | 5794542 | ADER | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 8404 | 0 | 8404 | 1.5917 | 1.5917 | 0 | 0 | 1.5917 | 8536 | 0 | 1.6167 | 0 |  | 1 | -949999 | 950000 |  |  | 13215.7 | 0 | 936784.3 | On/Under Budget | Request 2021 Budget | 0 | 2181597 | -2181597 | 2181597 | -2181597 | 2181596.7 | 44913.6 | 38.3 | 44875.3 | 0 | 0 | 0 | 13215.7 | 0 | 0 | 0 | 705 | 9953 | 508 | 2012 | 44914 | 63572 | 128057 | 192228 | 650266 | 556032 | 533350 | 2021-06-18 | 161884 | BL-A | BL-A 35219590_VACA DIXON 1105965390_08W - DD 210618 | 2021-06-22 | 2021-06-30 | Not Started | 2021-07-01 | 2021-07-07 | Not Started | 2021-08-06 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-08-09 | 2021-08-20 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-10-12 | Not Started | 2021-10-13 | Not Started | 2021-12-20 | 2021-12-20 | 0 | On/ Ahead Schedule | Not Started | 2021-12-21 | 2022-01-03 | Not Started | 2022-02-16 | Not Started
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | E.5034784.01.01 | 5795128 | ADER | 08W | [6 empty] | 2022 | 2022 | SH | REDBLUFF | North Valley Assets | 0 | 12302.4 | 0 | 12302.4 | 2.33 | 0 | 2.3299 | 0 | 2.33 | 12701 | 0 | 2.4055 | 0 |  | 247500 | 0 | 247500 |  |  | 23007.3 | 0 | 224492.7 | On/Under Budget | Budget Allocated | 92967 | 188213 | -95246 | 188213 | -95246 | 4640788.4 | 2095.2 | -78606.7 | 80701.9 | 0 | 0 | 0 | 23007.3 | 4452575.6 | 0 | 1791 | 3190 | 28012 | 53407 | 15215 | 2095 | 63257 | 21246 | 0 | 0 | 0 | 0 | 2021-06-18 | 158351 | BL-A_ | BL-A_35224231_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH1_08W_Apr.2021 | 2021-04-01 | 2021-07-22 | Not Started | 2022-04-11 | 2022-04-15 | Not Started | 2022-04-08 | Not Started | 2022-05-06 | Not Started | 2021-07-23 | 2021-07-23 | Not Started | 2021-07-26 | 2021-08-13 | Not Started | 2021-08-06 | 2021-08-10 | Not Started | 2022-05-11 | Not Started | 2022-05-11 | Not Started | 2022-05-24 | Not Started | 2022-05-11 | Not Started | 2022-07-26 | Not Started | 2022-08-24 | Not Started | 2022-02-16 | 2022-10-19 | -245 | Behind Schedule | Not Started | 2022-10-20 | 2022-11-02 | Not Started | 2022-12-16 | Not Started
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | E.5034784.01.02 | 5795128 | ADER | 08W | [6 empty] | 2022 | 2022 | SH | REDBLUFF | North Valley Assets | 0 | 8395.2 | 0 | 8395.2 | 1.59 | 0 | 1.59 | 0 | 1.59 | [5 empty] | 247500 | 0 | 247500 |  |  | 68908 | 0 | 178592 | On/Under Budget | Budget Allocated | 63441 | 118584 | -55143 | 118584 | -55143 | 3294084.1 | 1957.4 | 12209.2 | -10251.8 | 0 | 0 | 0 | 68908 | 3175500.1 | 0 | 0 | 218 | 24322 | 29121 | 3038 | 1957 | 43832 | 14316 | 445 | 445 | 445 | 445 | 2021-06-18 | 158352 | BL-A_ | BL-A_35226798_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH2_08W_Apr.2021 | 2021-04-01 | 2021-07-22 | Not Started | 2022-05-19 | 2022-05-25 | Not Started | 2022-05-18 | Not Started | 2022-06-08 | Not Started | 2021-07-23 | 2021-07-23 | Not Started | 2021-07-26 | 2021-08-13 | Not Started | 2021-08-11 | 2021-08-24 | Not Started | 2022-07-01 | Not Started | 2022-07-01 | Not Started | 2022-07-14 | Not Started | 2022-07-01 | Not Started | 2022-10-13 | Not Started | 2022-11-11 | Not Started | 2022-02-16 | 2023-01-27 | -345 | Behind Schedule | Not Started | 2023-01-30 | 2023-02-10 | Not Started | 2023-03-28 | Not Started
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | E.5034804.01.03 | 5795299 | ADER | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 15153 | 0 | 15153 | 2.8699 | 2.8699 | 0 | 0 | 2.8699 | 29522 | 0 | 5.5913 | 0 |  | 1 | -99999 | 100000 |  |  | 89619.2 | 0 | 10380.8 | On/Under Budget | Request 2021 Budget | 0 | 4797272 | -4797272 | 4797272 | -4797272 | 4864156.9 | 39841.2 | -15050.6 | 54891.8 | 0 | 0 | 0 | 89619.3 | 66884.6 | 0 | 0 | 231 | 9299 | 2954 | 92186 | 39841 | 979514 | 1263688 | 1114375 | 1214078 | 41672 | 39434 | 2021-06-18 | 156276 | BL-A | BL-A 35226848_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.2_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-06-30 | Not Started | 2021-07-01 | 2021-07-07 | Not Started | 2021-08-13 | Not Started | 2021-08-25 | Not Started | 2021-08-13 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2021-08-16 | 2021-09-16 | Not Started | 2021-10-12 | Not Started | 2021-10-12 | Not Started | 2021-10-25 | Not Started | 2021-10-12 | Not Started | 2022-02-10 | Not Started | 2022-03-11 | Not Started | 2021-12-27 | 2022-04-28 | -122 | Behind Schedule | Not Started | 2022-04-29 | 2022-05-12 | Not Started | 2022-06-27 | Not Started
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | E.5034805.01.07 | 5795300 | ADER | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1724 | 0 | 1724 | 0.32652 | 0.32652 | 0 | 0 | 0.32652 | [5 empty] | 67857 | 0 | 67857 |  |  | 25516.6 | 0 | 42340.4 | On/Under Budget | Budget Allocated | 67857 | 35011 | 32846 | 35011 | 32846 | 37253.5 | 3317 | -4960.1 | 8277.1 | 0 | 0 | 0 | 25516.6 | 2148.5 | 94.4 | 0 | 0 | 2401 | 12323 | 15753 | 3317 | 203 | 203 | 203 | 203 | 203 | 203 | 2021-06-18 | 159748 | BL-A: | BL-A: 35226864_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3_08W - Apr 21 | 2021-04-28 | 2021-06-25 | Not Started | 2021-09-10 | 2021-09-16 | Not Started | 2021-09-09 | Not Started | 2021-10-07 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-07-19 | 2021-07-30 | Not Started | 2021-11-11 | Not Started |  |  |  |  | 2021-11-11 | Not Started | 2021-11-24 | Not Started | 2021-11-26 | Not Started | 2021-12-24 | 2022-01-27 | -34 | Behind Schedule | Not Started | 2022-01-28 | 2022-02-10 | Not Started | 2022-03-28 | Not Started
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | E.5034805.01.08 | 5795300 | ADER | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1243 | 0 | 1243 | 0.23542 | 0.23542 | 0 | 0 | 0.23542 | [5 empty] | 67857 | 0 | 67857 |  |  | 17227.9 | 0 | 50629.1 | On/Under Budget | Budget Allocated | 67857 | 24224 | 43633 | 24224 | 43633 | 25799.9 | 3254.9 | -2899.8 | 6154.7 | 0 | 0 | 0 | 17227.9 | 1509 | 66.3 | 0 | 0 | 2401 | 9216 | 8511 | 3255 | 140 | 140 | 140 | 140 | 140 | 140 | 2021-06-18 | 159767 | BL-A: | BL-A: 35226865_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4_08W - Apr 21 | 2021-04-28 | 2021-06-24 | Not Started | 2021-09-10 | 2021-09-16 | Not Started | 2021-09-09 | Not Started | 2021-10-07 | Not Started | 2021-06-24 | 2021-06-24 | Not Started | 2021-06-25 | 2021-07-15 | Not Started | 2021-07-26 | 2021-08-06 | Not Started | 2021-11-11 | Not Started |  |  |  |  | 2021-11-11 | Not Started | 2021-11-19 | Not Started | 2021-11-23 | Not Started | 2021-12-28 | 2022-01-24 | -27 | Behind Schedule | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-23 | Not Started
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | E.5034805.01.09 | 5795300 | ADER | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2736 | 0 | 2736 | 0.51818 | 0.51818 | 0 | 0 | 0.51818 | [5 empty] | 67857 | 0 | 67857 |  |  | 24334.4 | 0 | 43522.6 | On/Under Budget | Budget Allocated | 67857 | 34555 | 33302 | 34555 | 33302 | 36705.9 | 3314.4 | -5705 | 9019.4 | 0 | 0 | 0 | 24334.5 | 2060.6 | 90.5 | 0 | 0 | 1028 | 19104 | 9908 | 3314 | 200 | 200 | 200 | 200 | 200 | 200 | 2021-06-18 | 159758 | BL-A: | BL-A: 35226866_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5_08W - Apr 21 | 2021-04-28 | 2021-06-25 | Not Started | 2021-09-10 | 2021-09-16 | Not Started | 2021-09-09 | Not Started | 2021-10-07 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-08-04 | 2021-08-17 | Not Started | 2021-11-11 | Not Started |  |  |  |  | 2021-11-11 | Not Started | 2021-12-08 | Not Started | 2021-12-10 | Not Started | 2022-01-25 | 2022-02-10 | -16 | Behind Schedule | Not Started | 2022-02-11 | 2022-02-24 | Not Started | 2022-04-11 | Not Started
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | E.5034784.01.04 | 5795128 | ADER | 08W | [6 empty] | 2022 | 2022 | SH | REDBLUFF | North Valley Assets | 0 | 3643.2 | 0 | 3643.2 | 0.69 | 0 | 0.68996 | 0 | 0.69 | [5 empty] | 247500 | 0 | 247500 |  |  | 3721.6 | 0 | 243778.4 | On/Under Budget | Budget Allocated | 27531 | 50977 | -23446 | 50977 | -23446 | 1426919.7 | 25131.8 | -21014.4 | 46146.2 | 0 | 0 | 0 | 3721.5 | 1375942.6 | 0 | 0 | 0 | 25324 | -2346 | 1758 | 25132 | 185 | 185 | 185 | 185 | 185 | 185 | 2021-06-18 | 158354 | BL-A_ | BL-A_35226900_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH4_08W_Apr.2021 | 2021-04-01 | 2021-07-05 | Not Started | 2022-05-10 | 2022-05-16 | Not Started | 2022-05-09 | Not Started | 2022-06-06 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-08-03 | Not Started | 2021-08-10 | 2021-09-06 | Not Started | 2022-07-13 | Not Started | 2022-07-13 | Not Started | 2022-07-26 | Not Started | 2022-07-13 | Not Started | 2022-10-25 | Not Started | 2022-11-23 | Not Started | 2022-02-16 | 2023-02-09 | -358 | Behind Schedule | Not Started | 2023-02-10 | 2023-02-23 | Not Started | 2023-04-10 | Not Started
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | E.5034805.01.27 | 5795300 | ADER | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3168 | 0 | 3168 | 0.6 | 0.6 | 0 | 0 | 0.6 | 3606 | 0 | 0.68295 | 0 |  | 92500 | 0 | 92500 |  |  | 13291.1 | 0 | 79208.9 | On/Under Budget | Request 2021 Budget | 0 | 62873 | -62873 | 62873 | -62873 | 62964.1 | 20302.3 | -27095.2 | 47397.5 | 0 | 0 | 0 | 13291.1 | 90.7 | 0 | 0 | 0 | 849 | 14940 | 24598 | 20302 | 364 | 364 | 364 | 364 | 364 | 364 | 2021-06-18 | 157833 | BL-A | BL-A 35227028_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-08-10 | 2021-08-16 | Not Started | 2021-08-09 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-04-14 | -49 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | E.5034610.01.13 | 5794205 | ADER | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5174 | 0 | 5174 | 0.97992 | 0.97992 | 0 | 0 | 0.97992 | [5 empty] | 80000 | 0 | 80000 |  |  | 24102.7 | 0 | 55897.3 | On/Under Budget | Request 2021 Budget | 0 | 40804 | -40804 | 40804 | -40804 | 41177.2 | 20175.3 | 4892 | 15283.3 | 0 | 0 | 0 | 24102.7 | 373.3 | 0 | 0 | 8597 | -7822 | 42 | 18394 | 20175 | 236 | 236 | 236 | 236 | 236 | 236 | 2021-06-18 | 157822 | BL-A | BL-A 35227867_CWSP - Middletown 1103 - LR 830 PH1.8_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-12 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-13 | 2021-08-26 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-02-24 | 0 | On/ Ahead Schedule | Not Started | 2022-02-28 | 2022-03-11 | Not Started | 2022-04-25 | Not Started
35236986 | FRRB - KANAKA 1101 - K5 PH5.4 | E.5034572.01.43 | 5793918 | ADER | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 9293 | 0 | 9293 | 1.76 | 1.76 | 0 | 0 | 1.76 | [5 empty] | 237500 | 0 | 237500 |  |  | 19110.1 | 0 | 218389.9 | On/Under Budget | Budget Allocated | 3344072 | 3355409 | -11337 | 11057 | 3333015 | 11057.2 | 7000 | 15052.9 | -8052.9 | 0 | 0 | 0 | 19110.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4057 | 7046 | 67 | 1114757 | 1114758 | 1114725 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-06-15 | Not Started | 2021-07-23 | 2021-07-29 | Not Started | 2021-07-22 | Not Started | 2021-08-10 | Not Started | [6 empty] | 2021-07-23 | 2021-07-29 | Not Started | 2021-08-12 | Not Started | 2021-08-12 | Not Started | 2021-10-28 | Not Started | 2021-08-12 | Not Started | 2021-11-11 | Not Started | 2021-11-11 | Not Started | 2021-12-13 | 2021-12-13 | 0 | On/ Ahead Schedule | Not Started | 2021-12-13 | 2021-12-27 | Not Started | 2022-02-09 | Not Started
35245152 | FRRB - KANAKA 1101 - K4 PH 4.17 | E.5034572.01.33 | 5793918 | ADER | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 3019 | 0 | 3019 | 0.57178 | 0.57178 | 0 | 0 | 0.57178 | [5 empty] | 2871418 | 1297495 | 1573923 | 487540 | 1086383 | 18291.8 | 0 | 1555631.2 | On/Under Budget | Budget Allocated | 1573923 | 1099781 | 474142 | 1099781 | 474142 | 1099780.6 | 249027.4 | 5473 | 243554.4 | 0 | 0 | 0 | 18291.8 | 0 | 0 | 0 | 0 | 0 | 0 | 12819 | 249027 | 934 | 837000 | 0 | 0 | 0 | 0 | 2021-06-08 | 160089 | BL-A: | BL-A: 35245152 FRRB - KANAKA 1101 - K4 PH 4.17 - May 21 | 2021-05-03 | 2021-06-16 | Not Started | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-30 | Not Started | 2021-07-01 | Not Started | [6 empty] | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-03 | Not Started | 2021-08-20 | Not Started | 2021-09-03 | Not Started | 2021-08-03 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-12-15 | 2021-10-05 | 71 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | E.5015029.01 | 5782859 | APPR | 08W | [6 empty] | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 11422 | 1351 | 0 | 12773 | 2.4191 | 0 | 0 | 0 | 2.4191 | 14918 | 0 | 2.8254 | 0 |  | 999000 | 0 | 999000 | 0 | 999000 | 408520.5 | 0 | 590479.5 | On/Under Budget | Budget Allocated | 3379.1 | -495945 | 499324.1 | -495945 | 499324.1 | 760021.4 | -525761 | -525761.9 | 0.9 | 16471 | 138809.4 | 750685.7 | -497445.6 | 350000 | 0 | 5400 | 6072 | 5434 | 6104 | 5307 | -525761 | 0 | 0 | 0 | 0 | 1500 | 0 | 2021-06-18 | 160845 | BL-A1 | BL-A1: 74022385_CWSP Konocti - 1102 - LR 532 (UG)_08W - May 21 | 2021-05-18 | 2021-11-15 | Not Started | 2021-11-17 | 2021-11-17 | Not Started | 2022-03-01 | Not Started | 2022-03-02 | Not Started | 2021-11-18 | 2022-03-17 | Not Started | 2022-03-18 | 2022-03-18 | Not Started | 2020-07-01 | 2020-12-17 | Completed | 2022-03-21 | Not Started |  |  |  |  | 2022-03-21 | Not Started | 2022-05-30 | Not Started | 2022-06-02 | Not Started | 2022-07-01 | 2022-07-01 | 0 | On/ Ahead Schedule | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-07-15 | Not Started
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | 5783288 | APPR | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 6209 | -6209 | 6209 | -6209 | [10 empty] | 1218 | 1160 | 1524 | 1153 | 1153 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | E.5034610.01.18 | 5794205 | APPR | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1162 | 0 | 1162 | 0.22008 | 0.22008 | 0 | 0 | 0.22008 | 1067 | 0 | 0.20208 | 0 |  | 100000 | 0 | 100000 |  |  | 2851.7 | 0 | 97148.3 | On/Under Budget | Request 2021 Budget | 0 | 22783 | -22783 | 22783 | -22783 | 22993.7 | 20071.5 | 932.3 | 19139.2 | 0 | 0 | 0 | 2851.7 | 211.1 | 0 | 0 | 0 | 37 | 0 | 1882 | 20072 | 132 | 132 | 132 | 132 | 132 | 132 | 2021-06-18 | 159240 | BL-A | BL-A 35236661_CWSP - Middletown 1103 - LR 830 PH2.5_08W - DD 210402 | 2021-04-15 | 2021-08-10 | Not Started | 2021-08-11 | 2021-08-17 | Not Started | 2021-08-24 | Not Started | 2021-10-05 | Not Started | 2021-08-11 | 2021-08-11 | Not Started | 2021-08-12 | 2021-09-01 | Not Started | 2021-08-25 | 2021-09-07 | Not Started | 2021-10-28 | Not Started | 2021-10-28 | Not Started | 2021-11-10 | Not Started | 2021-10-28 | Not Started | 2022-01-26 | Not Started | 2022-02-24 | Not Started | 2022-04-06 | 2022-04-27 | -21 | Behind Schedule | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2022-06-24 | Not Started
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | E.5034610.01.10 | 5794205 | APPR | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4171 | 0 | 4171 | 0.78996 | 0.78996 | 0 | 0 | 0.78996 | 4196 | 0 | 0.7947 | 0 |  | 80000 | 0 | 80000 |  |  | 11918.1 | 0 | 68081.9 | On/Under Budget | Request 2021 Budget | 0 | 22224 | -22224 | 22224 | -22224 | 22567.2 | 20068.3 | 10534.9 | 9533.4 | 0 | 0 | 0 | 11918.1 | 343.4 | 0 | 0 | 0 | 799 | 303 | 281 | 20068 | 129 | 129 | 129 | 129 | 129 | 129 | 2021-06-18 | 157821 | BL-A | BL-A 35227863_CWSP - Middletown 1103 - LR 830 PH1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-12 | Not Started | 2021-07-13 | 2021-07-19 | Not Started | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-09-29 | Not Started | 2022-01-11 | Not Started | 2022-02-09 | Not Started | 2022-02-24 | 2022-02-11 | 13 | On/ Ahead Schedule | Not Started | 2022-02-24 | 2022-03-09 | Not Started | 2022-04-12 | Not Started
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | E.5034406.01 | 5792097 | APPR | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1426 | 0 | 1426 | 0.27008 | 0.27008 | 0 | 0 | 0.27008 | 1 | 0 | 0.00018939 | 0 |  | 90000 | 0 | 90000 |  |  | 36119.8 | 0 | 53880.2 | On/Under Budget | Request 2021 Budget | 0 | 67626 | -67626 | 67626 | -67626 | 75666.9 | 20373.2 | -16075.9 | 36449.1 | 0 | 0 | 7555.9 | 28564 | 485.5 | 0 | 10832 | 1196 | 2299 | 16696 | 13617 | 20373 | 435 | 435 | 435 | 435 | 435 | 435 | 2021-06-18 | 157813 | BL-A | BL-A 35192281_ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-10 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-11 | 2021-08-24 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-04-14 | -49 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35175131 | *CANC* - PLACERVILLE 2106 - LR1104 - PH2 |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35171354 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | 5530159 | CLSD | 08W | [6 empty] | 2020 |  | SH | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.00018939 | 0 |  | 37409.67 | 37409.67 | 0 |  |  | 39600.7 | 0 | -39600.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 39600.7 | 0 | 0 | 0 | 0 | 0 | 39600.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35172093 | *CANC* EL DORADO PH 2102 LR19542 P*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172094 | CWSP-EL DORADO PH 2102 LR19542 PH 1*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172521 | *CANC* EL DORADO PH 2102 LR19542 P*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35172522 | *CANC* CWSP-EL DORADO PH 2102 LR195*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | 5794986 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 161 | 6845 | -7006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | 5543349 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | LIVRMORE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1819 | 3802 | -5621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | 5543351 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | LIVRMORE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2342 | 5713 | -8055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35145523 | *CANC* PSPS - FULTON 1102 HARDENING |  | 5788784 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35144942 | *CANC* PSPS - PAUL SWEET 2105 - CB | E.5025647.01 | 5788789 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 116 | -116 | 116 | -116 | 0 | 0 | 0 | 0 | 0 | 2117.5 | -2117.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 33 | 33 | 17 | 0 | 0 | 0
35144940 | *CANC* PSPS - HICKS 2101 – CB | E.5025645.01 | 5788790 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | San Jose Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 230 | -230 | 230 | -230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 93 | 47 | 0 | 0 | 0 | 0
35121739 | *CANCEL* CENTERILLE REMOVAL - BUTTE 1105 |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35141837 | *CANC*BR-04-01-W (E) SUNSET DR PARB*CANC |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | -272305 | 272305 | -272305 | 272305 | [10 empty] | -199153 | 0 | -59092 | -14060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35147045 | *CANC* *DO NOT USE* PSPS - CASTRO V*CANC |  | 5530167 | CLSD | 08W | [6 empty] | Not in the WP |  |  | HAYWARD | Mission Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118701 | *CANC* BR-10-02-W (E) CIRCLEWOOD DR, PA |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208.5 | -208.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115149 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.4 | E.5015567.04 | 5785727 | CLSD | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 6692 | 0 | 6692 | 1.2674 | 0 | 0 | 1.2674 | 0 | 6500 | 6265 | 1.2311 | 1.1866 |  | 5030060 | 1695453.6 | 3334606.4 |  |  | 2837051.6 | 0 | 497554.8 | On/Under Budget | Project is not in the WP or in 2020 WP | -213318 | 0 | -213318 | 0 | -213318 | 2837051.6 | 0 | 0 | 0 | 0 | 96726.2 | 2740325.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | 5785728 | CLSD | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY |  | 0 | 6241 | 0 | 6241 | 1.182 | 0 | 0 | 1.182 | 0 | 6221 | 6353 | 1.1782 | 1.2032 | [10 empty] | Project is not in the WP or in 2020 WP | 37621 | 14621 | 23000 | 14621 | 23000 | [10 empty] | 14576 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115158 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.5 | E.5015569.05 | 5785720 | CLSD | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 11332 | 0 | 11332 | 2.1462 | 0 | 0 | 2.1462 | 0 | 11108 | 10413 | 2.1038 | 1.9722 |  | 1623614.28 | -2810332.02 | 4433946.3 |  |  | 3386933 | 0 | 1047013.3 | On/Under Budget | Project is not in the WP or in 2020 WP | -233648 | 0 | -233648 | 0 | -233648 | 3386933 | 0 | 0 | 0 | 0 | 2905.9 | 3384027.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116393 | CWSP - MIWUK 1702 - OCB - PH 1.3 | E.5014773.03 | 5785977 | CLSD | 08W | [6 empty] | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 13572 | 0 | 13572 | 2.5705 | 0 | 0 | 2.5705 | 0 | 13485 | 13742 | 2.554 | 2.6027 |  | 4302367 | -1 | 4302368 |  |  | 4301719 | 0 | 649 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 4301719 | 0 | 0 | 0 | 0 | 810426.6 | 3491292.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116394 | CWSP - MIWUK 1702 - OCB - PH 1.4 | E.5014773.04 | 5785978 | CLSD | 08W | [6 empty] | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 8858 | 0 | 8858 | 1.6777 | 0 | 0 | 1.6777 | -4.8231e-15 | 8790 | 8790 | 1.6648 | 1.6648 |  | 2102204 | 112129.2 | 1990074.8 |  |  | 1826412.3 | 0 | 163662.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1826412.3 | 0 | 0 | 0 | 0 | 130824.5 | 1695587.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | 5785971 | CLSD | 08W | [6 empty] | 2020 | 2020 | SH | SONORA |  | 0 | 4771 | 0 | 4771 | 0.9036 | 0 | 0 | 0.9036 | 0 | 4715 | 0 | 0.89299 | 0 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | -7655 | 7655 | -7655 | 7655 | [10 empty] | -4736 | -6129 | 1930 | 1289 | -10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145847 | BL-0: | BL-0: 35116390_CWSP - MIWUK 1701 - LR 8060 - PH 1.7_08W - Nov 2021 | 2020-07-24 | 2020-01-10 | Completed | 2020-03-17 | 2020-07-09 | Completed | 2020-08-03 | Completed | 2020-08-03 | Completed | 2020-09-08 | 2020-09-08 | Completed | 2020-09-09 | 2020-09-10 | Completed | 2020-08-19 | 2020-09-21 | Completed | 2020-10-05 | Completed |  |  |  |  | 2020-10-05 | Completed | 2020-10-12 | Completed | 2020-10-12 | Completed | 2020-11-09 | 2020-10-12 | 28 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-10-12 | Completed | 2021-06-08 | Completed
35114431 | CWSP - MORAGA 1101 - LR108540 - PH5 |  | 5786201 | CLSD | 08W | [6 empty] | 2020 |  | SH | CONCORD |  | 166 | 7421 | 0 | 7587 | 1.4369 | 0 | 0 | 1.4369 | -1.8948e-15 | 7673 | 6850 | 1.4532 | 1.2973 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115084 | *CANC* BR-01-11-W (E) MONTNA DR PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113952 | *CANC* BB1101-LR10296-PH1.4 |  | 5786126 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113953 | *CANC* BB1101-LR10296-PH1.5 | E.5014542.05 | 5786127 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113954 | *CANC* BB1101-LR10296-PH1.6 |  | 5786129 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113955 | *CANC* B1101-LR10296-PH1.7 |  | 5786130 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35113871 | SILVERADO 2104 RECONDUCTOR - PHASE 2 |  | 5786200 | CLSD | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA |  | 650 | 0 | 0 | 650 | 0.12311 | 0 | 0 | 0.12311 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-02 | Completed | 2019-08-06 | 2019-08-06 | Completed | 2019-09-12 | Completed | 2019-08-07 | Completed | 2019-08-08 | 2019-08-09 | Completed | 2019-09-23 | 2019-09-24 | Completed | 2019-09-19 | 2019-09-19 | Completed | 2019-10-01 | Completed |  |  |  |  | 2019-10-01 | Completed | 2020-06-01 | Completed | 2019-12-14 | Completed | 2019-12-16 | 2019-12-14 | 2 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-22 | Completed | 2020-08-25 | Completed
35113109 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.2 | E.5014535.02 | 5786055 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 681 | 0 | 681 | 0.12898 | 0 | 0 | 0.12898 | 0 | [5 empty] | 300000 | 0 | 300000 |  |  | 294673.1 | 0 | 5326.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 294673.1 | 0 | 0 | 0 | 0 | 270432.6 | 24240.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113103 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | E.5014319.03 | 5786050 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 1152 | 0 | 1152 | 0.21818 | 0 | 0 | 0.21818 | 0 | [5 empty] | 390567 | 26780 | 363787 |  |  | 319671.6 | 0 | 44115.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 319671.6 | 0 | 0 | 0 | 0 | 300581.7 | 19089.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113104 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.2 | E.5014319.02 | 5786049 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 1324.3 | 0 | 1324.3 | 0.25081 | 0 | 0 | 0.25081 | 0 | [5 empty] | 517390 | 100243 | 417147 |  |  | 414586.4 | 0 | 2560.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 414586.4 | 0 | 0 | 0 | 0 | 402136.5 | 12449.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 PH3 | E.5015491.03 | 5785302 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 7573 | 0 | 7573 | 1.4343 | 0 | 0 | 1.4343 | 0 | [5 empty] | 2438915 | 416398.7 | 2022516.3 |  |  | 1956173 | 0 | 66343.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1956173 | 0 | 0 | 0 | 0 | 2020497 | -64324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101875 | BR-01-10-W (E) BILLIE & LUCKY JOHN PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103324 | CWSP - ROSSMOOR 1102 - OCB | E.5014544.03 | 5785419 | CLSD | 08W | [6 empty] | 2020 |  | SH | WALNTCRK | Diablo Assets | 0 | 4046 | 0 | 4046 | 0.76629 | 0 | 0 | 0.76629 | 4.3063e-17 | 4046 | 4046 | 0.76629 | 0.76629 |  | 2510809 | 0 | 2510809 |  |  | 2486089.7 | 0 | 24719.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2486089.7 | 0 | 0 | 0 | 0 | 1818894.5 | 667195.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103325 | CWSP - MORAGA 1102 & 1104 - OCB | E.5014544.04 | 5785380 | CLSD | 08W | [6 empty] | 2020 |  | SH | WALNTCRK | Diablo Assets | 3755 | 3159 | 0 | 6914 | 1.3095 | 0 | 0 | 1.3095 | -1.7225e-16 | 6506 | 6916 | 1.2322 | 1.3098 |  | 6187462 | 751903.5 | 5435558.5 |  |  | 5043980.6 | 0 | 391577.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 5043980.6 | 0 | 0 | 0 | 0 | 1903394.3 | 3140586.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103942 | *CANC* BR-09-03-W (E) CONNIE CIR PA*CANC |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075591 | SILVERADO 2105 WIRE DOWN PH 1 (CANCEL) |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075594 | SILVERADO 2105 WIRE DOWN PH-2 (CANCEL) |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075647 | SILVERADO 2105 WIRE DOWN PH-3 (CANCEL) |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075650 | SILVERADO 2105 WIRE DOWN PH-4 (CANCEL) |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076062 | *CANC* RECONDUCTOR 17547 FT OF 4AC *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076064 | *CANC* 14184 FT OF 4ACSR&3363 FT OF 6CU |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35081748 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 | P.12007 | 5530159 | CLSD | 08W | [6 empty] | 2020 |  | SH | STCRUZ | Central Coast Assets | 0 | 850 | 0 | 850 | 0.16098 | 0 | 0 | 0.16098 | 0 | -1617 | 1425 | -0.30625 | 0.26989 |  | 713114 | 80294 | 632820 |  |  | 608138.6 | 0 | 24681.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 608138.6 | 0 | 0 | 0 | 0 | 597265 | 10873.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35089880 | OCGC PIH SILVERADO 2104 - ANGWIN UG_PH 2 |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 2117 | 0 | 0 | 2117 | 0.40095 | 0 | 0 | 0.40095 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35105656 | *CANC*BR-04-02-W (E) CASTLE DR PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110379 | BR-03-11-W (E) WHITAKER RD PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 2446 | -2446 | 2446 | -2446 | [10 empty] | 2446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | 5785611 | CLSD | 08W | [6 empty] | 2020 |  | SH | CHICO |  | 0 | 13964 | 0 | 13964 | 2.6447 | 0 | 0 | 2.6447 | 0 | 15053 | 13964 | 2.8509 | 2.6447 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 1708 | -1708 | 1708 | -1708 | [10 empty] | 1305 | 1708 | -1305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | 5785608 | CLSD | 08W | [6 empty] | 2020 |  | SH | CHICO |  | 0 | 11610 | 0 | 11610 | 2.1989 | 0 | 0 | 2.1989 | 0 | 10965 | 11549 | 2.0767 | 2.1873 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 10460 | -10460 | 10460 | -10460 | [10 empty] | 10056 | 3903 | -3499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110374 | *CANC*BR-03-06-W (E) LUNAR LN PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | -440 | 440 | -440 | 440 | [10 empty] | -311 | -129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35111500 | CWSP-RECON UPPER LAKE 01 HUNTERS PT RD |  | 5533649 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1850 | 0 | 1850 | 0.35038 | 0 | 0 | 0.35038 | 0 | [5 empty] | 425000 | 0 | 425000 |  |  | 418578.6 | 0 | 6421.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 418578.6 | 0 | 0 | 0 | 0 | 362979.3 | 55599.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112092 | BR-14-06 (E) BLUE DANUBE PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 4993 | -4993 | 4993 | -4993 | [10 empty] | 4993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112426 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.3 |  | 5785653 | CLSD | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE |  | 0 | 9077 | 0 | 9077 | 1.7191 | 0 | 0 | 1.7191 | -2.1639e-15 | 9368 | 9077 | 1.7742 | 1.7191 | [10 empty] | Project is not in the WP or in 2020 WP | -259218 | -259218 | 0 | -259218 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -259218
35112427 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | E.5015420.04 | 5785654 | CLSD | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 5069 | 0 | 5069 | 0.96004 | 0 | 0 | 0.96004 | 0 | 5117 | 5069 | 0.96913 | 0.96004 |  | 3306693 | 969939.2 | 2336753.8 |  |  | 1848367.1 | 0 | 488386.7 | On/Under Budget | Project is not in the WP or in 2020 WP | -231631 | 0 | -231631 | 0 | -231631 | 1848367.1 | 0 | 0 | 0 | 0 | 705528.7 | 1142838.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112428 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 |  | 5785655 | CLSD | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE |  | 0 | 8571 | 0 | 8571 | 1.6233 | 0 | 0 | 1.6233 | 0 | 8571 | 8571 | 1.6233 | 1.6233 | [10 empty] | Project is not in the WP or in 2020 WP | -340669 | 0 | -340669 | 0 | -340669 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112436 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 |  | 5785650 | CLSD | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE |  | 0 | 9529 | 0 | 9529 | 1.8047 | 0 | 0 | 1.8047 | 0 | 9210 | 9867 | 1.7443 | 1.8687 | [10 empty] | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000
35072362 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1913 |  | 5782526 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | FORTUNA |  | 0 | 14292 | 0 | 14292 | 2.7068 | 0 | 0 | 2.7068 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072363 | *CANC* RECOND 15 298 FT 6CU 4CU & | E.5014305.01 | 5782597 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | North Bay Assets | [14 empty] | 1 | -49999 | 50000 |  |  | 0 | 0 | 50000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35072720 | RPL OH WIRE ON GABILN 1101 17-0077248 | E.5015593.01 | 5783290 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | SALINAS | Central Coast Assets | 0 | 11745 | 0 | 11745 | 2.2244 | 0 | 0 | 2.2244 | 0 | [5 empty] | 1869000 | 321276 | 1547724 |  |  | 1076838.7 | 0 | 470885.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1076838.7 | 0 | 0 | 0 | 0 | 1009384.6 | 67454.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35065727 | *CANC* CAMP FIRE SOUTH SKYWAY EXTEN*CANC |  | 5533652 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35066745 | BIG BEND 1102 - BLOOMER HILL 08W PHS 2 |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | CHICO | North Valley Assets | 0 | 8900 | 0 | 8900 | 1.6856 | 0 | 0 | 1.6856 | 0 | [5 empty] | 3916190 | 1146536 | 2769654 |  |  | 3167514.9 | 0 | -397860.9 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 3167514.9 | 0 | 0 | 0 | 0 | 3118076.8 | 49438.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060229 | 2018 OH COND RPLC: FRUITLAND 42 C/O 7449 |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | GARBRVLE |  | 0 | 6529 | 0 | 6529 | 1.2366 | 0 | 0 | 1.2366 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | 5783072 | CLSD | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY |  | 0 | 7099 | 0 | 7099 | 1.3445 | 0 | 0 | 1.3445 | 0 | 7662 | 7702 | 1.4511 | 1.4587 | [10 empty] | Project is not in the WP or in 2020 WP | 36100 | 15091 | 21009 | 15091 | 21009 | [10 empty] | 14659 | 1440 | -757 | -252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35062173 | *CANC* CANCL FIRE PADSE 1105 INST N*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35056666 | *CANC* EST HILL 1101 LR 50486 HARDENING |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35058080 | *CANC* X-1104 OH RECOND SKYLINE *CANC |  | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | East Bay Assets | [14 empty] | 50000 | 50000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5097.1 | -5097.1 | 0 | 0 | 0 | 0
35060157 | CWSP- HENDRIX DEMO - LIVERMORE TRNG CNTR |  | 5530167 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LIVRMORE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060580 | *CANC*BIG BEND 1102 - BLOOMER *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259.5 | -259.5 | 0 | 0 | 0 | 0
35060581 | *CANC* RECONDUCT PT. MORETTI FROM 5043 |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060586 | *CANC* RECONDUCTOR 5885 FT ZACA *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407.3 | -2407.3 | 0 | 0 | 0 | 0
35060587 | *CANC* REPLACE~1.2MILES_MAINLINE_ *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2212.8 | -2212.8 | 0 | 0 | 0 | 0
35046366 | *CANC* CWSP BRUNSWICK 1105 LR-1030*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37*CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | -55330 | 55330 | -55330 | 55330 | [10 empty] | 98 | 0 | -56150 | 722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046383 | *CANC* CWSP - MIWUK 1701 LR11800 &*CANC |  | 5530178 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SONORA | Yosemite Assets | [14 empty] | 5000000 | 5000000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11991.4 | -11991.4 | 0 | 0 | 0 | 0
35046726 | *CANC* CWSP - LOS GATOS 1106 - LB4 *CANC |  | 5530160 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35046759 | *CANC* CWSP - VOLTA 1102 - LR 1648 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 500000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16904.5 | -16904.5 | 0 | 0 | 0 | 0
35046793 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | Stockton Assets | [14 empty] | 500000 | 500000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8645.6 | -8645.6 | 0 | 0 | 0 | 0
35046896 | *CANC* CWSP - FITCH MOUNTAIN 1113 *CANC |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047143 | *CANC*DO NOT USE* CWSP - VOLTA 1102*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047146 | REDBUD 1101 RELOCATE FUSE 4865 IN T*CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CLRLAKE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35044284 | *CANC* CWSP-KONOCTI 1102-LR 532 *CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LAKEPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35045959 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2413.4 | -2136.6 | -276.8 | 0 | 0 | 0
35047312 | *CANC*CWSP-CAMP EVERS 2106 - 5020 P*CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 500000 | 500000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13665 | -13665 | 0 | 0 | 0 | 0
35047402 | *CANC* CWSP-SALT SPRINGS 2102-LR31 *CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | Stockton Assets | [14 empty] | 500000 | 500000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2577.4 | -2577.4 | 0 | 0 | 0 | 0
35047414 | *CANC* CWSP - PARADISE 1106 - OCB *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047418 | *CANC*DO NOT USE* CWSP-EL DORADO PH*CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047419 | *CANC*CWSP-SHINGLE SPRINGS 2109-LR *CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35049913 | *CANC* CWSP - BRUNSWICK 1103 LR220 |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35048011 | *CANC* CWSP - EL DORADO PH 2101 LR |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35048058 | *CANC* CWSP-COLUMBIA HILL 1101-LR |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052121 | *CANC* ZAMORA 1105 WIRE DOWN LR 36762 |  | 5530171 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WOODLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052128 | *CANC*DO NOT USE* CWSP-STANISLAUS17*CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052129 | *CANC*DO NOT USE*CWSP-STANISLAUS170*CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35052718 | OCGC CWSP: ANGWIN OH TO UG DEMO - PH 2 |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 2265 | 0 | 0 | 2265 | 0.42898 | 0 | 0 | 0.42898 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31387895 | *CANC* REPL 17 500' OF 4AR & 4CU I *CANC | P.11909 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | North Bay Assets | [14 empty] | 50000 | 0 | 50000 |  |  | 0 | 0 | 50000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11731.7 | -11731.7 | 0 | 0 | 0 | 0
35008479 | R2 2019 AUBERRY 1101 RECONDUCTOR |  | 5530163 | CLSD | 08W | [6 empty] | Not in the WP | 2019 | SH | FRESNO |  | 0 | 1636.8 | 0 | 1636.8 | 0.31 | 0 | 0 | 0.31 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128544 | WSHP | WSHP 190307 - 35008479_Auberry 1101 Reconductor_08W - B1 | 2019-03-07 | 2019-03-04 | Completed |  |  | Completed | 2019-04-28 | Completed | 2019-05-03 | Completed | [6 empty] | 2019-05-29 | 2019-05-31 | Completed | 2019-06-03 | Completed |  |  |  |  | 2019-06-03 | Completed | 2019-06-07 | Completed | 2019-06-07 | Completed | 2019-05-16 | 2019-06-07 | -22 | Behind Schedule | Completed |  |  |  | 2020-05-31 | Completed
35015703 | *CANC* FOOTHILL 1101 LS CO9973 REP *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 1 | -49999 | 50000 |  |  | 0 | 0 | 50000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9135.1 | -9135.1 | 0 | 0 | 0 | 0
35015705 | *CANC* R2 OH RECONDUCTR ROB ROY 21*CANC |  | 5503108 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 50000 | 50000 | 0 |  |  | -0.1 | 0 | 0.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | -0.1 | 0 | 0 | 0 | 6170.7 | -6650.2 | 0 | 0 | 0 | 0
35015706 | *CANC* OH RECONDUCTOR - ROB ROY 210*CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 155000 | 155000 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2535.9 | -2919.4 | 0 | 0 | 0 | 0
35018620 | *CANC* RECON CAB 1104 17K FT LASAL *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 1 | 1 | 0 |  |  | 0.1 | 0 | -0.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 9836.8 | -10384.1 | 0 | 0 | 0 | 0
35018787 | HALSEY 1101 - S039NO112 HIGH SPLICE 08J |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 2854 | 0 | 2854 | 0.54053 | 0 | 0 | 0.54053 | 0 | [5 empty] | 873318 | 6743 | 866575 |  |  | 782303.1 | 0 | 84271.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 782303.1 | 0 | 0 | 0 | 3003.3 | 801800.7 | -23757.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018788 | APPLE HILL 1104 - S049NO119 HIGH SPLICE |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 0 | 6121 | 0 | 6121 | 1.1593 | 0 | 0 | 1.1593 | 0 | [5 empty] | 1995745 | 314578 | 1681167 |  |  | 1502307 | 0 | 178860 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1502307 | 0 | 0 | 0 | 30025.9 | 1560453.2 | -89428.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35018886 | *CANC* RPL OH WIRE ON GABILN 1101 *CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | Central Coast Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | -1471.3 | 0 | 0 | 0 | 0
35019006 | ROB ROY 2104 CO11865 REPLACE OH LINE |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 8607 | 918 | 9525 | 1.804 | 0 | 0 | 1.804 | 0 | [5 empty] | 1485645.6 | 326113.6 | 1159532 |  |  | 1016957.3 | 0 | 142574.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1016957.3 | 0 | 0 | 0 | 2188.6 | 1056388.5 | -41619.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31334292 | RECON 9-SPANS, AUSTIN CREEK RD |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 0 | 2493 | 0 | 2493 | 0.47216 | 0 | 0 | 0.47216 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31338871 | RELIAIBLITY RICHMOND-REPL #6 CU-UWF_PH2 | P.11717 | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | East Bay Assets | [14 empty] | 999938 | 121000 | 878938 |  |  | 654036.7 | 0 | 224901.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 654036.7 | 0 | 0 | 0 | 745161.1 | 4388 | -96695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31360766 | FROGTOWN 1701 RECOND 1153FTTO 1/0ACSR TW |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 1153 | 0 | 1153 | 0.21837 | 0 | 0 | 0.21837 | 0 | [5 empty] | 474763 | 57925 | 416838 |  |  | 400124.9 | 0 | 16713.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 400124.9 | 0 | 0 | 0 | 8463 | 429017.7 | -38997.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-12-18 | 130766 | BL-0 | BL-0 : Project Authorization 31360766_FROGTOWN 1701 RECOND 1080FT TO 2AR_08W - Apr. 2019 | 2019-04-16 | 2019-03-18 | Completed |  |  | Completed |  |  | 2019-04-29 | Completed | 2019-04-13 | 2019-05-10 | Completed |  |  |  | 2019-05-14 | 2019-05-14 | Completed | 2019-05-14 | Completed |  |  |  |  | 2019-05-14 | Completed | 2019-05-20 | Completed | 2019-06-18 | Completed | 2019-08-13 | 2019-06-18 | 56 | On/ Ahead Schedule | Completed |  |  |  | 2020-02-29 | Completed
31361488 | *CANC* RECOND 15 298 FT 6CU 4CU & *CANC |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31389448 | *CANC* SILVERADO 2104 RECONDUCTOR*CANC |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31392316 | *CANC* 2018MONTERIO1112/MOLINO1102WILDFI |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31207126 | MVWF PANORAMIC HWY, COUNTY, ALTO 1125 | P.11106 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 2185378 | 442809 | 1742569 |  |  | 1419528.5 | 0 | 323040.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1419528.5 | 0 | 0 | 0 | 1420647.1 | -56071.1 | 0 | 0 | 0 | 0
31207128 | *CANC* MVWF ALTO 1125 MUIR WOOD DR *CANC |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31207160 | +SANTA MARIA 1108 WD 15-076543 | P.11028 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | Los Padres Assets | [14 empty] | 156472 | -151528 | 308000 |  |  | 210979.8 | 0 | 97020.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 210979.8 | 0 | 0 | 0 | 1025 | 0 | 0 | 0 | 0 | 0
31206912 | X WDN 15-0073161 CE2103-OLD GRAHM HL R |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31207089 | ESA BOULEVARD ORNE AVE, LARKSPUR GB 1103 | P.11105 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1716807 | 406951 | 1309856 |  |  | 1092736.5 | 0 | 217119.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1092736.5 | 0 | 0 | 0 | 1074650.1 | -23957.5 | 0 | 0 | 0 | 0
31234871 | -RELIAIBLITY 2017 - UWF K1104/X1105/6 | P.11404 | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | East Bay Assets | [14 empty] | 2675733 | 619019 | 2056714 |  |  | 1751641.1 | 0 | 305072.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1751641.1 | 0 | 0 | 0 | 1696465.6 | -17601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31246140 | WY1105 - RECOND 3000 FT OF 4AR W 2ARTW | P.11732 | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 352805 | 42706 | 310099 |  |  | 293661 | 0 | 16438 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 293661 | 0 | 0 | 0 | 286300.5 | -1966 | 0 | 0 | 0 | 0
31248532 | CWSP HALF MOON BAY 1101 LS CO4063 |  | 5530170 | CLSD | 08W | [6 empty] | 2020 |  | SH | SNCARLOS |  | 0 | 3926 | 0 | 3926 | 0.74356 | 0 | 0 | 0.74356 | 0 | 4816 | 4816 | 0.91212 | 0.91212 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31255868 | R2ROB ROY 2104 HIGH SPLICE CABLE REPLACE | P.11386 | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | Central Coast Assets | [14 empty] | 452850 | 75475 | 377375 |  |  | 176947.9 | 0 | 200427.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 176947.9 | 0 | 0 | 0 | 200547.2 | -24934 | 0 | 0 | 0 | 0
31264915 | R7 RECONDUCTOR WILSON RD- RINCON 1103 |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31275384 | OCGC DUCTOR MAYS CANYON-MIRABEL 1101 |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31286361 | *CANC* FRUITLAND 42 C/O 7449 *CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GARBRVLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | -12259 | 12259 | -12259 | 12259 | [10 empty] | 0 | 0 | -12259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31286571 | *R4 EL DORADO PH 2102 HIGH SPLICE AREA | P.11874 | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [14 empty] | 310397 | 42422 | 267975 |  |  | 174335.6 | 0 | 93639.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 174335.6 | 0 | 0 | 0 | 172088.5 | 0 | 0 | 0 | 0 | 0
31286573 | APPLE HILL 2102 HIGH SPLICE AREA |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 0 | 3492 | 0 | 3492 | 0.66136 | 0 | 0 | 0.66136 | 0 | [5 empty] | 900307 | 326267 | 574040 |  |  | 543235.6 | 0 | 30804.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 543235.6 | 0 | 0 | 0 | 11238 | 547733.4 | -17889.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31278200 | +OCEANO 1102 S HALCYON & PINE RDGE | P.11685 | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | SNLUISOB | Los Padres Assets | 0 | 2059.2 | 0 | 2059.2 | 0.39 | 0 | 0 | 0.39 | -8.6126e-17 | [5 empty] | 496629 | 20000 | 476629 |  |  | 455075 | 0 | 21554 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 455075 | 0 | 0 | 0 | 31025.9 | 427685.7 | -5598.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31289238 | FRUITLAND 1142 INS TREE WIRE LR 6064 |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP | 2019 | SH | GARBRVLE |  | 0 | 6271 | 0 | 6271 | 1.1877 | 0 | 0 | 1.1877 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 118758 | BL-2: | BL-2: 31157672_R7 S.ROSA A 1103 RECONDUCTOR OUTLET - Aug. 18 | 2018-08-04 | 2019-06-07 | Completed |  |  | Completed | 2019-06-10 | Completed | 2019-07-15 | Completed | [6 empty] | 2019-07-08 | 2019-07-10 | Completed | 2019-07-15 | Completed |  |  |  |  | 2019-07-15 | Completed |  |  | 2019-07-26 | Completed | 2018-12-31 | 2019-07-26 | -207 | Behind Schedule | Completed |  |  |  | 2020-02-27 | Completed
31289354 | *CANC* BIG RIVER 1101 FUSE 5187 REC*CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FTBRAGG | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 986 | -986 | 986 | -986 | [10 empty] | 0 | 0 | 986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31290147 | OCCCR7 OLEMA 1101 REPLACE COND VISION RD |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | SNRAFAEL |  | 0 | 3174 | 0 | 3174 | 0.60114 | 0 | 0 | 0.60114 | -8.6126e-17 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31308015 | *CANC* SLO 1107 RECOND 3836 FT 10S *CANC |  | 5530166 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5489 | -7563.5 | 0 | 0 | 0 | 0
31316186 | *CANC* HMB1102 CO12457 #17-00290*CANC |  | 5530170 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31319444 | RECON 5-SPANS PORTER CRK RD-RINCON 1103 |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 0 | 1279 | 0 | 1279 | 0.24223 | 0 | 0 | 0.24223 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31326119 | WEIMAR 1101 - NATURE'S WAY RECONDUCTOR | P.11895 | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 2990 | 0 | 2990 | 0.56629 | 0 | 0 | 0.56629 | 0 | [5 empty] | 1325896 | 251591.5 | 1074304.5 |  |  | 997479.3 | 0 | 76825.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 997479.3 | 0 | 0 | 0 | 14191.4 | 914173.6 | 66731.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31330635 | FORESTHILL 1102 - SPRING GARDEN RD 08W | P.11870 | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | [14 empty] | 918095 | 82638 | 835457 |  |  | 581153.5 | 0 | 254303.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 581153.5 | 0 | 0 | 0 | 577793.5 | 2265.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | JACKSON |  | 0 | 686.4 | 0 | 686.4 | 0.13 | 0 | 0 | 0.13 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-01-08 | 128647 | BL-0: | BL-0: Project Authorization 35024926_MARTELL 1101 RECONDUCTOR 3,700FT_08W - Mar. 2019 | 2019-03-11 | 2019-02-21 | Completed |  |  | Completed | 2019-03-07 | Completed | 2019-03-11 | Completed | [6 empty] | 2019-03-18 | 2019-03-18 | Completed | 2019-03-18 | Completed |  |  |  |  | 2019-03-18 | Completed | 2019-03-30 | Completed | 2019-03-30 | Completed | 2019-06-03 | 2019-03-30 | 65 | On/ Ahead Schedule | Completed |  |  |  | 2021-05-05 | Completed
35026420 | *CANC*OAKLAND X-1104 OH RECOND SKYLINE |  | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35030654 | TW ON WOODSIDE1101 N/O 7573 |  | 5530170 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | SNCARLOS |  | 0 | 5271 | 0 | 5271 | 0.9983 | 0 | 0 | 0.9983 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35031139 | SHADY GLEN 1102 RECONDUCTOR BEYOND 6343 |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 8016 | 0 | 8016 | 1.5182 | 0 | 0 | 1.5182 | 0 | [5 empty] | 2668456 | 157254 | 2511202 |  |  | 2416634.1 | 0 | 94567.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2416634.1 | 0 | 0 | 0 | 14003.3 | 2277144.7 | 125486.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35031660 | *CANC* PH 1:REPL 14 000' OF 4AR IN *CANC |  | 5530160 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | De Anza Assets | [14 empty] | 50000 | 0 | 50000 |  |  | 0 | 0 | 50000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16135.7 | -16135.7 | 0 | 0 | 0 | 0
35039002 | OCGC 2018 CALISTOGA 1101 LEVEL 2 DEMO |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 6019.2 | 0 | 6019.2 | 1.14 | 0 | 0 | 1.14 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35039757 | *CANC* CWSP - BURNS 2101 - OCB - P*CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35039957 | *CANC* CWSP - STANISLAUS 1702 LR18 *CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040742 | OCGC - 2018 MONTE RIO 1112 OH TO UG DEMO |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 2798.4 | 0 | 0 | 2798.4 | 0.53 | 0 | 0 | 0.53 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040961 | CWSP: 2018 K-1102 OH TO UG DEMO |  | 5530161 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WALNTCRK | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35041202 | *TRSFR* 35052732 CWSP-BB 1101 - LR *CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35041205 | *CANC* WSP LOS GATOS 1106 LR 60116*CANC |  | 5530160 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040016 | *CANC* CWSP-SILVERADO 2104-LR 722 *CANC |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040225 | HIGGINS 1110 RECONDUCTOR |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 8584 | 0 | 8584 | 1.6258 | 0 | 0 | 1.6258 | 0 | [5 empty] | 2449837 | 0 | 2449837 |  |  | 2412478.7 | 0 | 37358.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2412478.7 | 0 | 0 | 0 | 6004 | 2626394.5 | -219919.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042417 | *TRSFR* 35052727 CWSP LG1106 LR6011*CANC |  | 5530160 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042612 | *CANC* CWSP-ORO FINO 1101 LR-2022 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.1 | -3395.5 | -363.6 | 0 | 0 | 0
35042631 | *CANC*DO NOT USE* CWSP-VOLTA 1102-L*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13869 | -11375.3 | -2493.7 | 0 | 0 | 0
35042647 | *TRSFR* 35052733 CWSP-BB 1101 - LR *CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042648 | *TRSFR* 35052734 CWSP-CE 2105 - LR *CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042719 | CWSP-AMGWIN STEEL POLE & TW DEMO PH |  | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 1275 | 0 | 1275 | 0.24148 | 0 | 0 | 0.24148 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042893 | *CANC* CWSP - BURNS 2101 - OCB - PH*CANC |  | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35042923 | *CANC* CWSP-ORO FINO 1101-LR 2022 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3979 | -3512.4 | -466.6 | 0 | 0 | 0
35043143 | *TRSFR* 35052728 CWSP LG1107 LR6009*CANC |  | 5530160 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043245 | *CANC* CWSP-ORO FINO 1101 OCB PH 1 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4179.9 | -3674.2 | -505.7 | 0 | 0 | 0
35043246 | *CANC* CWSP-ORO FINO 1101 OCB PH 2 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600.8 | -3185.6 | -415.2 | 0 | 0 | 0
35043247 | *CANC* CWSP-ORO FINO 1101 OCB PH 3 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.3 | -2518.3 | -344 | 0 | 0 | 0
35043280 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | 5782590 | CLSD | 08W | [6 empty] | 2020 |  | SH | JACKSON |  | 0 | 15172 | 0 | 15172 | 2.8735 | 0 | 0 | 2.8735 | 0 | 14920 | 14872 | 2.8258 | 2.8167 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | -22127 | 22127 | -22127 | 22127 | [10 empty] | -22127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043304 | *CANC* 2019 OH COND RPLC: EEL RIVE *CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FORTUNA | Humboldt Division Assets | [14 empty] | 100000 | 0 | 100000 |  |  | 0 | 0 | 100000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 827.7 | -827.7 | 0 | 0 | 0 | 0
35043385 | *CANC* CWSP - TASSAJARA 2112 - FUS *CANC |  | 5786801 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CONCORD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043586 | *CANC* PACIFICA 1102 WD: INS TREE W*CANC |  | 5530170 | CLSD | 08W | [6 empty] | Not in the WP |  |  | COLMA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043763 | *CANC* CWSP - MIDDLETOWN 1101-TS 1 *CANC |  | 5530164 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LAKEPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043949 | *CANC*DO NOT USE*CWSP-ORO FINO 1102*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 500000 | 0 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3582.6 | -1344 | -2238.6 | 0 | 0 | 0
35043953 | *CANC* CWSP-ORO FINO 1102 LR-2560 *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043954 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043955 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043956 | *CANC*DO NOT USE* CWSP-ORO FINO 110*CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35043986 | *CANC*DO NOT USE*CWSP-PINE GROVE 11*CANC |  | 5530176 | CLSD | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30948153 | OC2 REPLACE #6CU WITH 4AR, VASONA 1103 |  | 5513260 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30949571 | OC4 GRN VALLEY 2103 WIRE DOWN NEAR 1993 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30951870 | 2014 MALAGA 1102 RECONDUCTOR CENTRAL | P.06373 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | Fresno Assets | [14 empty] | 299128 | -3900 | 303028 |  |  | 301521.1 | 0 | 1506.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 301521.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30951871 | OC4 2014 MALAGA 1102 RECONDUCTOR AMERICA | P.06374 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | Fresno Assets | [14 empty] | 304087 | -28105 | 332192 |  |  | 320537.9 | 0 | 11654.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 320537.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30951993 | OC4 XSPRING VALLEY ROAD WIRE REPLACEMENT |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30965813 | OC4 +MESA 1102 WIREDOWN - C/O 8953 |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30967034 | OC4 LINE DOWN - DAVIS 1107 RECON-REFRAME |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WOODLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30968294 | OC2 2013, BAKERSFIELD 2104, RE-CONDUCTOR |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30971722 | OC4RECNDUCT 2 SP OF WIRE @ MAPLE & CEDAR |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30971802 | OC4 RECONDUCTOR INST FUSES VACA DIXON 11 |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972334 | OP-1101 RECOND_SAN PABLO & O'HATCH (R) |  | 5513262 | CLSD | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972547 | OCGC XDEL MONTE 2104 RECOND PORTOLA WD |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30972642 | WIREDOWN-RECOND-KERN OIL 1116 |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974004 | OC4 DIXON 1103 RECONDUCTOR |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974166 | +SLO 1107 WIREDOWN (BOB JONES TRAIL) | P.09170 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 235457 | -196493 | 431950 |  |  | 319906.2 | 0 | 112043.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 319906.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30974168 | OC4 LLAGAS 2101 RECONDUCTOR 4 SPANS |  | 5513274 | CLSD | 08W | [6 empty] | Not in the WP |  |  | EDENVALE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974722 | OC4 DEL MONTE 2102 ELM WIREDWN RECONDUCT |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974723 | OCGC DEL MONTE 2105 VAN BURN WIRE RECON |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974724 | OCGC DEL MNTE 2104 RECTR CORRAL TIERRA |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30974733 | OC2 XREPL COND, BEACH ROAD @ PALM BEACH |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975188 | OCGC+SLO 1103 WD @ 14125 - 12-70838 |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975601 | NEWARK 2103 CKT - RECONDUCTOR OH |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FREMONT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30975805 | OCGC XINDUSTRIAL WY ANNEALED COND,KC1102 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30976210 | OC4 WIREDOWN-RECOND-ELK HILLS 1106 |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30977168 | OC4 OCGC FRNCH CMP 1102 RECOND & RELOCA |  | 5513276 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STOCKTON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30978199 | OC4 HMB1102 CO5905 RECONDUCTOR 470 FT |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30978886 | OCGC RECONDUCTOR TO REMOVE SPLICES |  | 5513260 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979240 | OCGC XRECON 4 SPS OF WR GLEENWOOD-CE2106 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979241 | OCGC XRECON 2 SPN@GRNITE CRK/HWY17 S VLY |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979379 | +RECNDUCTR TO REMOVE SPLICES VASONA 110 |  | 5513260 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30979787 | OCGC2014 CASTLE CR RD RECONDUCTOR LW2224 | P.05925 | 5513261 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CONCORD | Diablo Assets | [14 empty] | 164688 | 0 | 164688 |  |  | 146850.9 | 0 | 17837.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 146850.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30980061 | *CANC* RECONDUCTOR 1 SP @ THOMPSON*CANC |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980068 | 285 LITTLEFIELD AVE SSF |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | COLMA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980069 | R1 MB-1106 RECONDUCTORING |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | COLMA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980443 | XRECOND 4433/23327 @ 105 RODGERS RD |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30980444 | OC4 XRECOND 310 FT 1-0C, LKHRN & CAST BL |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30981327 | OC4 RECON 800FT 4AR - BAKERSFIELD 1110 |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30981330 | 2015 MCFARLAND 1104 RECONDUCTOR | P.06393 | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WASCO | Kern Assets | [14 empty] | 332709 | -41560 | 374269 |  |  | 238873.5 | 0 | 135395.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 238873.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30981641 | RECOND 1608FT 2CU-SAN BERNARD 1101 | P.07966 | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | Kern Assets | [14 empty] | 116000 | 0 | 116000 |  |  | 66664 | 0 | 49336 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 66664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30981763 | OCGC 2014 LAMONT 1106 RECONDUCTOR | P.07498 | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | Kern Assets | [14 empty] | 407615 | 2238 | 405377 |  |  | 239261.4 | 0 | 166115.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 239261.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30982568 | OC4 LKVL1101RECOND3SPAN-BRWNSRDLKVLHW,PE |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30982640 | OC4 OCGC INSTREEW-5600MARSHALLPTLMA,OLEM |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | PETALUMA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30982694 | OCCC +Z DIVIDE 1102 WD 13-0006459 |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30984641 | OCLH PARL 1103 RECON 2 SPANS 800' OF 2CU |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30985803 | OCLH BARTON 1101 4 ACSR |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30989646 | OC4 E WEST SAC 1109 RECONDUCTOR 700 FEET |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WOODLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30989894 | OCGC ARCATA 1105 REMOVE EXCESS SPLICES |  | 5513264 | CLSD | 08W | [6 empty] | Not in the WP |  |  | EUREKA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30990258 | OCGC XKING CITY 1106 RECONDUCTORING |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30991832 | OCLH SCHINDLER 1105 - REPLACE 2 SPANS 4 |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | COALINGA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30992890 | OC4 XRECNDUCTOR 2 SPOF 4AR TW-PRESCOTT R |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993194 | MEN 402 REPL 630FT &3 PLS/219 ATHERTON A |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993279 | OCLHRECOND 5 SPANS 4AR,@ 50/52 NASHUA RD |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30993327 | OCLHR1 RECONDUCTOR 390' OHDUMBARTON 2111 |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FREMONT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997023 | OCGC RECONDUC TO REMOVE SPLICES LG1106 |  | 5513260 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997782 | *CANC* CAMBRIA LINE RECONFIG *CANC |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
30997783 | OC4+RECONDUCTOR FAIRWY 1107 AT FUCO 1219 |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31001492 | OC4 OCLH PLEASANTON RECONDUCTOR 2700' WI |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LIVRMORE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31002333 | MIDWAY 1104- INSTALL FUSE |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31006463 | OCLHXRECOND BV1102-HARKINS RD@BURTON AVE |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31007718 | *CANC* WIRE DOWN SERVICE REL JOB *CANC |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WOODLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31008212 | OC4 RECON 1/0A W/397A MERRIL ST-BV 1103- |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31008213 | XBUENA VISTA 1103 NUTTING 4AR |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31009249 | RPL 800' OH CONDUCTOR GREENBRAE 1101 | P.08623 | 5513268 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 195180 | 0 | 195180 |  |  | 157965.1 | 0 | 37214.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 157965.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31011324 | OCGC XREPL DETERIORTD COND SMITH RD WAT |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31016170 | OCGC XRECONDUCTORING PRI @ IVERSON RD |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31016636 | OC4 OCGC CORRAL 1101 RELOCAT 4ACSR (WIR | P.08226 | 5513276 | CLSD | 08W | [6 empty] | Not in the WP |  |  | VICTOR | Stockton Assets | [14 empty] | 222210 | -100902 | 323112 |  |  | 163783.7 | 0 | 159328.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 163783.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31017531 | OC4 OCGC KERN POWER 2103 4 SPANS RECONDU |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31017692 | *CANC* WD SISQUOC 1102 PHASE 3A RE*CANC |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31017694 | +BPO WD SANTA MARIA 1109 RECNDUCTR & FU |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31019802 | OC4 EP REPLACE DAMAGED CONDUCT , HICKORY |  | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WILLOWS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31021152 | OC4 OCGC R2 2014 DINUBA 1105 RECONDUCTOR | P.06833 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | DINUBA | Fresno Assets | [14 empty] | 1742700 | -25751 | 1768451 |  |  | 1571040.3 | 0 | 197410.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1571040.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31028173 | OC4 +OCEANO 1103 HWY 101 REC | P.06639 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | Los Padres Assets | [14 empty] | 215672 | -64702 | 280374 |  |  | 230317.2 | 0 | 50056.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 230317.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31036265 | R1128-RECNDUCTOR 3 SPANS,NSTALL CUT |  | 5513262 | CLSD | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31038431 | OC4 OCCC WD CABRILLO 1104 13-0056541 | P.08519 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BUELLTON | Los Padres Assets | [14 empty] | 566951 | -282289 | 849240 |  |  | 411819.9 | 0 | 437420.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 411819.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31039795 | MABURY 1102 WIRE DOWN 13-0077162 |  | 5513274 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CINNABAR | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31040925 | RECONDUCT #4ACSR_W.JACKSON_HAYWRD |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | HAYWARD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043129 | EB-RELIAIBLITY K1103-RECONDUT |  | 5513262 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043566 | OCGC XRECOND 500FT W. ZAYANTE RD CE 2105 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31043567 | OCGC XRECON W/675FT TW LOKHRT GL CE 2105 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31047513 | OCGC RECONDUCTOR 2 SPANS DIXON 1103 |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31048179 | OC4 OCGC SONOMA1105-WIREDWN-8TH ST EAST |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31048895 | OCGC RECONDUCT 1-SPAN -WILLITS 1103 |  | 5513264 | CLSD | 08W | [6 empty] | Not in the WP |  |  | UKIAH | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31053110 | MABURY 1102 WIRE DOWN 14-0004189 |  | 5513274 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CINNABAR | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31054897 | OCGC BH402 LS CO10192 REPL.2 SPANS OH LI |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 476 | -476 | 476 | -476 | [10 empty] | 476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31059794 | OCGC CLARKSVILLE 2104 RECONDUCTOR,PHASE1 | P.08456 | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [14 empty] | 549218 | -73294 | 622512 |  |  | 492416.2 | 0 | 130095.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 492416.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31060016 | OCCCRECO 1 SPAN LINE SIDE FU 1829 TW2107 |  | 5513261 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CONCORD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31062729 | LERDO 1103 RECONDUCTOR 1,700FT WD |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31063598 | WEEDPATCH 1106 RECOND WIRE DOWN |  | 5513265 | CLSD | 08W | [6 empty] | Not in the WP |  |  | BKRSFLD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31066529 | OCGC CEDAR CRK 1101-RECOND 3528' Y2015 | P.08120 | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | REDDING | North Valley Assets | [14 empty] | 547671 | -79420 | 627091 |  |  | 539968.5 | 0 | 87122.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 539968.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31067784 | OCGC XRECON 300' OF 4AR W/ 4/0A FORD ST |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31069570 | X-SPENCE 1121 WIREDOWN 3779 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31071681 | OCGC 1105-JEFFREY PINE RECON 600' |  | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OROVILLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31073205 | *CANC* R6 BUENA VISTA 1102 WD RECO*CANC |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31075442 | BORDEN 1103 RECONDUCTORING |  | 5513277 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MADERA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31079018 | *CANC* BIG BEND 1102 - BLOOMER HIL *CANC |  | 5530169 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OROVILLE | North Valley Assets | [14 empty] | 50000 | 50000 | 0 |  |  | 0.1 | 0 | -0.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 7037.7 | -10902.5 | 0 | 0 | 0 | 0
31082152 | OCCC XRECNDUCTR 2900' HRD TAP GNZLS 1104 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 0 | 1345 | 0 | 1345 | 0.25473 | 0 | 0 | 0.25473 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 128 | -128 | 128 | -128 | [10 empty] | 0 | 0 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31082394 | OCGC N SIX SPANS FRATI LN |  | 5530175 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31083701 | OCCC HMB-1103RECOND 400' OH PRI_INST C/O |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31085776 | SANTA MARIA 1109 (HWY166/E/O BLACK RD) |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31086638 | OCCC CABRILLO 1104 WIREDOWN 14-0036943 | P.08472 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | Los Padres Assets | [14 empty] | 114208 | -87382 | 201590 |  |  | 114425 | 0 | 87165 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 114425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31089385 | *CANC* R5WD REPL 1 SPAN WITH 4/0AL*CANC |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093073 | XSHELL RD, REPL 450' 6CU OH CONDUCTOR |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093074 | +SM 1109 RECON (HWY 166 / E/O SIMAS RD) |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31093779 | MABURY 1104 WIRE DOWN 14-0043849 |  | 5513274 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CINNABAR | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31094780 | OH WIRE DOWN REPLACEMENT ME1110 |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | HAYWARD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31095523 | OCGCELIAIBLITY -K1103, REPL #4ACSR W |  | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31097449 | XPRUNEDALE 1107 WD C/O 4485 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31097452 | XCAMPHORA 1101 WD FCO 7091 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098259 | OCCC SALINAS 1106 WIRE DOWN FCO56459 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098360 | OCCC XGONZALES 1104 WIRE DOWN FCO 5005 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31098626 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 |  | 5530173 | CLSD | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE |  | 0 | 8052 | 0 | 8052 | 1.525 | 0 | 0 | 1.525 | 0 | 8052 | 8052 | 1.525 | 1.525 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-04 | 140244 | BL-2: | BL-2: 31098626_CLARKSVILLE 2104 RECOND - PH 3 - Feb 2020 | 2020-02-15 | 2018-06-20 | Completed |  |  | Completed | [10 empty] | 2018-07-10 | 2018-07-13 | Completed | 2018-07-16 | Completed | [8 empty] | 2020-06-26 | Completed | 2021-07-05 | 2020-12-01 | 216 | On/ Ahead Schedule | Completed |  |  |  | 2021-06-04 | Not Started
31098634 | +MESA 1102 WIREDOWN (OSO FLACO TAP) | P.08609 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | Los Padres Assets | [14 empty] | 165745 | -39394 | 205139 |  |  | 131072.2 | 0 | 74066.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 131072.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31100467 | OCGC ZAMORA 1105 RECONDUCTOR 3 SPANS |  | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WOODLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31102548 | OC4 COTTONWOOD 1102-RECON 918' |  | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | REDDING | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31102963 | +SISQUOC 1104 WD (ORCUTT-GAREY RD) |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31109716 | 2016 GUERNSEY 1104 ANNEALED RECOND | P.09854 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LEMOORE | Fresno Assets | [14 empty] | 710000 | 0 | 710000 |  |  | 639358.4 | 0 | 70641.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 639358.4 | 0 | 0 | 0 | 0 | 0 | 787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31111367 | OCGC XR CONDCTR 4 SPANS @TROUT G&OSPREY |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31112500 | OCGC RECON 780FT OF 4ACSR MONTE RIO 1111 |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31113693 | OCCC DOLAN RD 1104 WIREDOWN COOPER RD |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31115088 | OCGC RECON 900FT 4CU/4/0ALTW FTROSS 1121 |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31115947 | EL NIDO 1103 REPLACE ANNEALTED 650FT |  | 5513277 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MERCED | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31119865 | OCCC BEL 403 REPLC200FT OH LINE INST C/O |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120755 | RECONDUCTOR ND2101 WIREDOWN |  | 5513267 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LIVRMORE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120911 | X-DOLN RD 1104 WIREDOWN BLNCO ARMSTRNG |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31120912 | X-DOLAN RD 1101 WIREDWN STRAWBRRY CYN |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31128279 | OCGC SPAULDING 1101 WIREDOWN SS OF 6607 |  | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31129830 | OCCC BIG TREES 402 _ 14-0076789 PHASE 1 | P.11076 | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 280000 | 0 | 280000 |  |  | 259437.4 | 0 | 20562.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 259437.4 | 0 | 0 | 0 | -20994 | 0 | 0 | 0 | 0 | 0
31132867 | HMB1101 REPLACE OH LINE SKYLINE BLVD | P.11476 | 5530170 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | Peninsula Assets | [14 empty] | 383497 | -1080857 | 1464354 |  |  | 715788.1 | 0 | 748565.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 715788.1 | 0 | 0 | 0 | 704662.5 | 0 | 0 | 0 | 0 | 0
31133991 | OCGC WIRE DOWN-RECONDUCTOR LIVE OAK 1102 |  | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MRYSVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31134351 | +MESA 1102 (JOSHUA ST & ORCHARD RD) |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31136738 | X-KING CITY 1102 WD 15-0009162 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31139913 | +SANTA MARIA 1110 ANNEALED RIVER X-ING |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31140055 | OCGC RECONDUCTOR PUEBLO 2103 AT SW 7927 | P.10252 | 5513268 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | North Bay Assets | [14 empty] | 81025 | -53135 | 134160 |  |  | 96664.3 | 0 | 37495.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 96664.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31143734 | 2016 REEDLEY 1104 WIRE DOWN RECONDUCT | P.09817 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | DINUBA | Fresno Assets | [14 empty] | 74642 | -159358 | 234000 |  |  | 112607.5 | 0 | 121392.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 112607.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31144558 | WDN 15-0013313 CE2105-HUBBARD GULCH | P.09907 | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 124617 | -133883 | 258500 |  |  | 158320 | 0 | 100180 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 158320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31144778 | OCGC TRINIDAD 1102 EXCESSIVE SPLICES |  | 5513264 | CLSD | 08W | [6 empty] | Not in the WP |  |  | EUREKA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31145622 | OCGC 2016 CORCORAN 1108 RECOND WIREDOWN |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | LEMOORE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31150684 | MORAGA 1103 RECNDUCTOR 350' (2SPANS) |  | 5513261 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CONCORD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31152787 | OCLH CLOVIS 2110 WIRE DOWN RECONDUCTOR |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31153724 | OCGC BANTA 1103 RECOND 968FT 6CU |  | 5513276 | CLSD | 08W | [6 empty] | Not in the WP |  |  | TRACY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31154886 | OCGC EP RECONDUCTOR ARBUCKLE 1102 -Y2016 |  | 5513271 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MRYSVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31156130 | SAN ARDO 1102 WD #15-0024843 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31157545 | OCGC HARDWICK 1102 WIRE DWN RECNDUCTOR |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SELMA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31157953 | RECON 1SPAN N/O FISH ROCK GUALALA1112 |  | 5513264 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FTBRAGG | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31163618 | SOLEDAD 2102 RECONDUCTORING JOB |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31163857 | X LOS OSITOS 2102 WDWN_15-0036239 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31169728 | 2017 GRIZZLY PEAK REPL #6 CU-UWF | P.11397 | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | East Bay Assets | [14 empty] | 1308187 | 380153 | 928034 |  |  | 718127 | 0 | 209907 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 718127 | 0 | 0 | 0 | 756435.6 | -94297.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31169729 | OCGCABILITY 2017 D1112/K1101 UWF |  | 5530162 | CLSD | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31170650 | X-SAN BENITO 2101 WIREDOWN 15-0039468 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | HOLLISTR | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31173660 | OCGC SANTA ROSA A 1108 RECOND 6SPANS |  | 5513275 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 677 | -677 | 677 | -677 | [10 empty] | 677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31175817 | +OCEANO 1108 WIREDOWN 15-0043519 | P.11011 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | Los Padres Assets | [14 empty] | 156541 | -30459 | 187000 |  |  | 87077 | 0 | 99923 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 87077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31204479 | RECOND 3 SPANS GARDEN TRACT |  | 5513262 | CLSD | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31204706 | MVWF THROCKMORTON LANE ALTO 1124 | P.11192 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 589459 | 0 | 589459 |  |  | 528490.1 | 0 | 60968.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 528490.1 | 0 | 0 | 0 | 406864.2 | 12026.9 | 0 | 0 | 0 | 0
31205198 | MVWF 206 REED ST, COUNTY, ALTO 1125 | P.11152 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1586740 | 338780 | 1247960 |  |  | 962856.9 | 0 | 285103.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 962856.9 | 0 | 0 | 0 | 919522.3 | 1597.9 | 0 | 0 | 0 | 0
31205343 | MVWF 388 SUMMIT AVE, CITY, ALTO 1124 | P.11151 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1873987 | 370716 | 1503271 |  |  | 1154944.1 | 0 | 348326.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1154944.1 | 0 | 0 | 0 | 1182715.1 | -74358.1 | 0 | 0 | 0 | 0
31205418 | MVWF BROOKLINE AVE, COUNTY, ALTO 1125 | P.11156 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1603391 | 277448 | 1325943 |  |  | 994666 | 0 | 331277 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 994666 | 0 | 0 | 0 | 937200.7 | 14323.4 | 0 | 0 | 0 | 0
31205937 | 109 HELENS LN,CITY/CNTY,ALTO | P.11155 | 5530168 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1925702 | 368352 | 1557350 |  |  | 1275048.9 | 0 | 282301.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1275048.9 | 0 | 0 | 0 | 1212911.2 | 2349.6 | 0 | 0 | 0 | 0
31121571 | REPL OH WIRE PORT CHICAGO W/O NICHOLS |  | 5513261 | CLSD | 08W | [6 empty] | Not in the WP |  |  | ANTIOCH | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31122088 | KINGSBRG 1114 600' RECOND WIREDOWN |  | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31122833 | OCCC BASALT 1106 WIRE DWN FUSE 1157 ZONE |  | 5513268 | CLSD | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31124815 | OCCC X-SLDD 1114 WREDWN RECND. S/O HY101 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31124819 | OCCC KING CITY 1106 WD 14-0067419 |  | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | KINGCITY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31125443 | OCLH PASO ROBLES 1103 WD 14-0066395 |  | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | TEMPLETN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31125646 | OCGC D 2350' EXCESS SLICES SW6041 |  | 5513264 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GARBRVLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31211274 | OCGC PINEDALE 2109 - RECONDUCTOR | P.11084 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | Fresno Assets | [14 empty] | 499000 | 44000 | 455000 |  |  | 446773.6 | 0 | 8226.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 446773.6 | 0 | 0 | 0 | 3874.3 | 0 | 0 | 0 | 0 | 0
31211275 | OCGC CANTUNA 1103 - RECONDUCTORING | P.11131 | 5513263 | CLSD | 08W | [6 empty] | Not in the WP |  |  | FRESNO | Fresno Assets | [14 empty] | 165000 | 5000 | 160000 |  |  | 142441 | 0 | 17559 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 142441 | 0 | 0 | 0 | 87472.4 | 0 | 0 | 0 | 0 | 0
31212864 | LP402 164 SELBY LN ATHERTON |  | 5513270 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNCARLOS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31212879 | OCGC RECONDUCTOR 6 CU ON E. NICOLAUS 11 |  | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MRYSVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31212922 | +SISQUOC 1104 WD-15-0070918 | P.11013 | 5513266 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STMARIA | Los Padres Assets | [14 empty] | 153852 | -172848 | 326700 |  |  | 158146.3 | 0 | 168553.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 158146.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31213040 | OCGC RECONDUCTOR 6 CU ON OLIVEHURST 1104 |  | 5513273 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MRYSVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31215474 | RECONDUCTOR ROB ROY 2104-MCDONALD RD | P.11413 | 5530159 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 2719 | 0 | 2719 | 0.51496 | 0 | 0 | 0.51496 | 0 | [5 empty] | 625339 | 81566 | 543773 |  |  | 541456.9 | 0 | 2316.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 541456.9 | 0 | 0 | 0 | 10066.8 | 516411.7 | 13098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31216725 | X BEN LOMOND401-RIDGE RD-FUSE6295 | P.11245 | 5519558 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 81280 | -117720 | 199000 |  |  | 176041 | 0 | 22959 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 176041 | 0 | 0 | 0 | -2446 | 0 | 0 | 0 | 0 | 0
31221409 | OCGC X TERMINOUS 1102 REPL. 800FT W/#2AR |  | 5513276 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STOCKTON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31222251 | X WDN_16-09640-212 CREST RD OTTER 1101 | P.11277 | 5513259 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | Central Coast Assets | [14 empty] | 62976 | -102456 | 165432 |  |  | 104557 | 0 | 60875 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 104557 | 0 | 0 | 0 | -6566 | 0 | 0 | 0 | 0 | 0
31229986 | OCGC JACINTO 1101 RECOND 9677'OF 3-6CU | P.11271 | 5513269 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 549035 | 0 | 549035 |  |  | 533892.6 | 0 | 15142.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 533892.6 | 0 | 0 | 0 | 13479.9 | 0 | 0 | 0 | 0 | 0
35228082 | *CANC* BR-14-04-W (E) ARROWHEAD DR PARB |  | 5786123 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35235703 | *CANC*KANAKA 1101 - K4 PH4.1 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 236 | -236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240469 | *CANC*KANAKA 1101 - K4 PH4.4 |  | 5797102 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240470 | *CANC* KANAKA 1101 - K4 PH4.5 |  | 5797102 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240472 | *CANC*ANAKA 1101 - K4 PH4.7 |  | 5797102 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240473 | *CANC*ANAKA 1101 - K4 PH4.8 |  | 5797102 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240474 | *CANC*ANAKA 1101 - K4 PH4.9 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240475 | *CANC*ANAKA 1101 - K4 PH4.10 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240476 | *CANC*KANAKA 1101 - K4 PH4.11 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240477 | *CANC*NAKA 1101 - K4 PH4.12 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
74022620 | *CANC* RPL OH WIRE ON OTTER-1101 S |  | 5794491 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 |  | 5782843 | CLSD | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 9937 | -9937 | 9937 | -9937 | [10 empty] | 9937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022387 | CWSP-MIDDLETOWN 1101-TS 1079 | E.5014744.01 | 5782842 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 20962 | 0 | 20962 | 3.9701 | 0 | 0 | 3.9701 | 0 | [5 empty] | 5829000 | 0 | 5829000 |  |  | 5591711.7 | 0 | 237288.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 5591711.7 | 0 | 0 | 0 | 98394.5 | 5533313.8 | -39996.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | 5537523 | CLSD | 08W | [6 empty] | 2020 | 2019 | SH | OAKPORT |  | 3810 | 0 | 0 | 3810 | 0.72159 | 0 | 0 | 0.72159 | 0 | 3677 | 8409 | 0.6964 | 1.5926 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 5914 | -5914 | 5914 | -5914 | [10 empty] | -5717 | 6771 | 4861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 152835 | BL-1 | BL-1 74022388_Oakland X 1104_08W - Dec. 2020 | 2020-12-29 | 2019-10-08 | Completed | 2019-12-16 | 2019-12-16 | Completed | 2020-01-15 | Completed | 2019-12-13 | Completed | 2019-12-19 | 2019-12-19 | Completed | 2019-12-19 | 2019-12-20 | Completed |  |  |  | 2020-02-14 | Completed | 2020-02-03 | Completed | 2020-05-15 | Completed | 2020-02-14 | Completed | 2020-07-10 | Completed | 2020-12-01 | Completed | 2020-12-01 | 2020-12-01 | 0 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-11-06 | Completed | 2021-04-23 | Completed
74022389 | *CANC* CWSP - PARADISE 1106 - OCB & LR 2 | E.5015532.01 | 5782907 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 500000 | 0 | 500000 |  |  | 0.1 | 0 | 499999.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 166.6 | 20318.9 | -20485.4 | 0 | 0 | 0
74022391 | *CANC* **DO NOT USE**CWSP - VOLTA 1102 | E.9999990.01 | 5782908 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11103.4 | 45576 | -56679.4 | 0 | 0 | 0
35249909 | DIAMOND SPRINGS 1105 - LR 2102 *CANC |  | 5530173 | CLSD | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74015668 | *CANC* RPL OH WIRE ON OTTER-1101 S |  | 5786638 | CLSD | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74021962 | *DO NOT USE* CWSP: DIABLO WILDFIRE HARDE | E.9999990.01 | 5782578 | CLSD | 08W | [6 empty] | Not in the WP |  |  | CONCORD | Diablo Assets | [14 empty] | 5344100 | 5344100 | 0 |  |  | 0 | 0 | 0 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166560.7 | -170924.2 | 4363.5 | 0 | 0 | 0
74022380 | *CANC* BRUNSWICK 1103 LR2200 | E.5015531.01 | 5782906 | CLSD | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | Sierra Assets | [14 empty] | 1 | -499999 | 500000 |  |  | 0 | 0 | 500000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7021.6 | 4337.6 | -11359.2 | 0 | 0 | 0
74022381 | *CANC* CWSP - CAMP EVERS 2106 - 50 | E.9999990.01 | 5782839 | CLSD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | [14 empty] | 500000 | 500000 | 0 |  |  | 0.1 | 0 | -0.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 7633.8 | -6737.6 | -896.1 | 0 | 0 | 0
74022382 | CWSP-COLUMBIA HILL 1101-LR 2212 PH1 |  | 5777898 | CLSD | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 12389 | 0 | 12389 | 2.3464 | 0 | 0 | 2.3464 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240479 | *CANC*NAKA 1101 - K4 PH4.14 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240540 | *CANC*ANAKA 1101 - K4 PH4.15 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 229 | -229 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240541 | *CANC*ANAKA 1101 - K4 PH4.16 |  | 5795419 | CLSD | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240471 | *CANC*KANAKA 1101 - K4 PH4.6 |  | 5797102 | CNCL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240467 | *CANC*ANAKA 1101 - K4 PH4.2 |  | 5797102 | CNCL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35240468 | *CANC*ANAKA 1101 - K4 PH4.3 |  | 5797102 | CNCL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35236988 | *CANC*FRRB - KANAKA 1101 - K4 PH4.19 |  | 5795419 | CNCL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 1221 | -1221 | 1221 | -1221 | [10 empty] | 0 | 0 | 0 | 667 | 546 | 2 | 2 | 2 | 2 | 1 | 0 | 0
35237895 | *CANC* WYANDOTTE 1103 -W3 PH3.7 |  | 5795419 | CNCL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Budget Allocated | 3533290 | 511 | 3532779 | 511 | 3532779 | [10 empty] | 0 | 0 | 0 | 13471 | -12960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 | 159049 | BL-A_ | BL-A_35237895_FRRB - Wyandotte 1103 - W3 Ph 3.7 - B1_Apr 21 | 2021-04-09 | 2021-06-18 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-01 | Not Started | 2021-08-12 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-11-01 | Not Started | 2021-08-16 | Not Started | 2021-11-15 | Not Started | 2021-11-15 | Not Started | 2021-11-09 | 2021-12-15 | -36 | Behind Schedule | Not Started | 2021-12-15 | 2021-12-29 | Not Started | 2022-02-11 | Not Started
35175132 | *CANC* - PLACERVILLE 2106 - LR1104 - PH |  | 5530173 | CNCL | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35193883 | BUCOCAMPTUG 622 PEARSON RD PARADISE |  | 5791246 | CONS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 181972 | -181972 | 181972 | -181972 | [10 empty] | 59690 | -59690 | 60305 | 121718 | -50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35200008 | BUCOCAMPTUG MOORE RD PARADISE UG SHORT |  | 5791246 | CONS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 150443 | -150443 | 150443 | -150443 | [10 empty] | 66332 | 353 | 83758 | -8368 | 8368 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 | E.5034391.01 | 5792082 | CONS | 08W | [6 empty] | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 11547 | 0 | 11547 | 2.1869 | 2.1869 | 0 | 2.1869 | 0 | 11569 | 0 | 2.1911 | 0 |  | 1877409.58 | -1371812.42 | 3249222 |  |  | 2233449.1 | 229124.4 | 786648.5 | On/Under Budget | Budget Allocated | 2843023 | 2397925 | 445098 | 2397925 | 445098 | 2404287.8 | 154772.1 | 4902.9 | 149869.2 | 0 | 0 | 6362.5 | 2227086.6 | 0 | 0 | 50073 | 1187832 | 294819 | 639026 | 50433 | 154772 | 6990 | 6990 | 6990 | 0 | 0 | 0 | 2021-06-18 | 156214 | BL-0 | BL-0 35192053_ECOP-OAKHURST 1103-LR 5120 PH1_08W - DD 210219 | 2021-02-23 | 2021-01-23 | Completed | 2021-02-25 | 2021-03-02 | Completed | 2021-03-02 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-08 | 2021-03-15 | Completed | 2021-02-08 | Completed |  |  |  |  | 2021-02-08 | Completed | 2021-03-15 | Completed | 2021-03-18 | Completed | 2021-07-12 | 2021-07-12 | 0 | On/ Ahead Schedule | Not Started | 2021-07-13 | 2021-07-26 | Not Started | 2021-09-14 | Not Started
35219275 | CWSP - PUTAH CREEK 110246012 | E.5034706.01.01 | 5543347 | CONS | 08W | [6 empty] | 2021 |  | SH | WOODLAND | Sacramento Assets | 0 | 5382 | 0 | 5382 | 1.0193 | 1.0193 | 0 | 0 | 1.0193 | 5382 | 0 | 1.0193 | 0 |  | 656614.03 | -293385.97 | 950000 | 0 | 950000 | 193713.4 | 135969 | 620317.6 | On/Under Budget | Budget Allocated | 950000 | 1392181 | -442181 | 1392797 | -442797 | 1452783.2 | 665745.4 | 54735 | 611010.4 | 0 | 0 | 0 | 193713.2 | 59986 | 0 | 2530 | 3445 | 11425 | 45343 | 76235 | 463065 | 638593 | 142287 | 4629 | 4629 | 0 | 0 | 2021-06-18 | 161218 | BL-0 | BL-0 35219275_CWSP - PUTAH CREEK 110246012_08W - DD 210521 | 2021-06-01 | 2021-03-05 | Completed | 2021-05-10 | 2021-05-12 | Completed | 2021-04-26 | Completed | 2021-05-26 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-05-17 | 2021-05-21 | Completed | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-07-22 | Not Started | 2021-07-20 | Not Started | 2021-08-16 | Not Started | 2021-08-17 | Not Started | 2021-09-03 | 2021-09-24 | -21 | Behind Schedule | Not Started | 2021-08-31 | 2021-09-13 | Not Started | 2021-11-23 | Not Started
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | E.5034709.01.01 | 5794548 | CONS | 08W | [6 empty] | 2021 |  | SH | UKIAH | Humboldt Division Assets | 0 | 8380 | 0 | 8380 | 1.5871 | 1.5871 | 0 | 0 | 1.5871 | [5 empty] | 929604.54 | 454604.54 | 475000 |  |  | 14827 | 0 | 460173 | On/Under Budget | Request 2021 Budget | 0 | 32734 | -32734 | 32734 | -32734 | 32832.6 | 20128.8 | 3358.9 | 16769.9 | 0 | 0 | 0 | 14826.9 | 98.2 | 0 | 2219 | 2183 | 961 | 1364 | 4741 | 20129 | 190 | 190 | 190 | 190 | 190 | 190 | 2021-06-18 | 157827 | BL-A | BL-A 35219280_CWSP - POTTER VALLEY PH 110564118 PH 1.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-03 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-07-27 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-02-24 | 2022-03-08 | -12 | Behind Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35217267 | SH - MARIPOSA 2102 LR 241564 | E.5034606.01.01 | 5794209 | CONS | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 4752 | 0 | 4752 | 0.9 | 0.9 | 0 | 0 | 0.9 | [5 empty] | 691633.47 | -112907.53 | 804541 |  |  | 226445.9 | 19475.8 | 558619.3 | On/Under Budget | Budget Allocated | 1220483 | 1035829 | 184654 | 1035829 | 184654 | 1038911.3 | 389365.8 | 121452.4 | 267913.4 | 0 | 0 | 3082.1 | 223363.7 | 0 | 0 | 4024 | 47690 | 31732 | 7283 | 11183 | 389366 | 270879 | 252471 | 13101 | 8101 | 0 | 0 | 2021-06-18 | 156027 | BL-A | BL-A 35217267_SH - MARIPOSA 2102 LR 241564_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-29 | Completed | 2021-05-06 | 2021-05-24 | Completed | 2021-04-28 | Completed | 2021-06-07 | Completed | 2021-06-21 | 2021-06-21 | Not Started | 2021-06-22 | 2021-07-12 | Not Started | 2021-05-04 | 2021-05-21 | Completed | 2021-07-14 | Not Started |  |  |  |  | 2021-07-14 | Not Started | 2021-08-17 | Not Started | 2021-08-18 | Not Started | 2021-12-08 | 2021-10-25 | 44 | On/ Ahead Schedule | Not Started | 2021-10-26 | 2021-11-08 | Not Started | 2021-12-22 | Not Started
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | E.5034825.01.77 | 5795419 | CONS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 19806 | 0 | 0 | 19806 | 3.7511 | 3.7511 | 0 | 0 | 3.7511 | 19806 | 0 | 3.7511 | 0 |  | 10700839 | 1186540 | 9514299 |  |  | 7166134.5 | 545944.2 | 1802220.3 | On/Under Budget | Budget Allocated | 9514299.24 | 9513210 | 1089.24 | 9514297 | 2.24 | 9514297.4 | 2015303 | 600610.1 | 1414692.9 | 0 | 0 | 0 | 7166134.5 | 0 | 0 | 1651 | 1009315 | 2018468 | 1827621 | 1708470 | 2013560 | 878117 | 54491 | 1012 | 506 | 0 | 0 | 2021-06-18 | 161072 | BL-0: | BL-0: 35223345_FRRB - Wyandotte 1103 ¿ Bald Rock Zone 3_08W - May 21 | 2021-05-25 | 2021-02-16 | Completed | 2021-02-16 | 2021-02-19 | Completed | 2021-02-17 | Completed | 2021-03-01 | Completed | 2021-02-16 | 2021-05-03 | Completed | 2021-05-03 | 2021-05-06 | Completed | 2020-11-23 | 2020-12-04 | Completed | 2021-02-16 | Completed | 2021-02-16 | Completed | 2021-06-21 | Not Started | 2021-05-17 | Completed | 2021-07-23 | Not Started | 2021-08-09 | Not Started | 2021-09-20 | 2021-09-20 | 0 | On/ Ahead Schedule | Not Started | 2021-09-21 | 2021-10-11 | Not Started | 2021-11-17 | Not Started
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | E.5034825.01.79 | 5795419 | CONS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 4798 | 0 | 0 | 4798 | 0.90871 | 0.90871 | 0 | 0.75152 | 0.1572 | 4798 | 0 | 0.90871 | 0 |  | 4380690 | 637422 | 3743268 |  |  | 2867312 | 73873.8 | 802082.2 | On/Under Budget | Budget Allocated | 3743276.52 | 3279781 | 463495.52 | 3743270 | 6.52 | 3743269.4 | 72612 | -112880.6 | 185492.6 | 0 | 0 | 0 | 2867312.1 | 0 | 0 | 94 | 69390 | 1064514 | 1278626 | 567568 | 72612 | 133705 | 64353 | 19279 | 9640 | 0 | 0 | 2021-06-18 | 161073 | BL-0: | BL-0: 35225822_FRRB - Wyandotte 1103 - Bald Rock Zone 6_08W - May 21 | 2021-05-25 | 2021-02-16 | Completed | 2021-03-01 | 2021-03-05 | Completed | 2021-02-18 | Completed | 2021-03-03 | Completed | 2021-03-01 | 2021-04-16 | Completed | 2021-04-16 | 2021-04-21 | Completed | 2020-11-10 | 2020-12-15 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-04-26 | Completed | 2021-04-20 | Completed | 2021-06-28 | Not Started | 2021-07-20 | Not Started | 2021-08-23 | 2021-08-23 | 0 | On/ Ahead Schedule | Not Started | 2021-08-24 | 2021-09-06 | Not Started | 2021-10-20 | Not Started
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | E.5034825.01.80 | 5795419 | CONS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 8431 | 0 | 0 | 8431 | 1.5968 | 1.5968 | 0 | 0 | 1.5968 | 8431 | 0 | 1.5968 | 0 |  | 6586891 | 1685778 | 4901113 | 987023 | 3914090 | 519822.5 | 3976025.6 | 405264.9 | On/Under Budget | Budget Allocated | 4901112 | 4901111 | 1 | 4901111 | 1 | 4901110.7 | 1169066.9 | 72904.9 | 1096162 | 0 | 0 | 0 | 519822.5 | 0 | 0 | 0 | 87486 | 85549 | 138419 | 135464 | 1169067 | 3139357 | 103140 | 28420 | 14210 | 0 | 0 | 2021-06-18 | 161074 | BL-0: | BL-0: 35225823_FRRB - Wyandotte 1103 - LR 1976 Zone 7_08W - May 21 | 2021-05-25 | 2021-02-02 | Completed | 2021-03-01 | 2021-03-12 | Completed | 2021-02-23 | Completed | 2021-02-23 | Completed | 2021-03-29 | 2021-05-03 | Completed | 2021-05-03 | 2021-05-03 | Completed | 2020-11-18 | 2020-12-18 | Completed | 2021-05-26 | Completed | 2021-05-26 | Completed | 2021-08-13 | Not Started | 2021-08-02 | Not Started | 2021-09-07 | Not Started | 2021-09-22 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-18 | 2021-12-03 | Not Started | 2022-01-14 | Not Started
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 | E.5034825.01.94 | 5795419 | CONS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 15567 | 0 | 0 | 15567 | 2.9483 | 2.9483 | 0 | 2.4078 | 0.54053 | 15567 | 0 | 2.9483 | 0 |  | 11016312 | 2921408 | 8094904 | 1014079 | 7080825 | 3877693.3 | 2266830.6 | 1950380.1 | On/Under Budget | Budget Allocated | 8094904 | 5266749 | 2828155 | 8094899 | 5 | 8094899.1 | 1019995.2 | 180991.4 | 839003.8 | 0 | 0 | 0 | 3877693.3 | 0 | 0 | 53850 | 514614 | 19392 | 1720467 | 1388379 | 1019995 | 534387 | 15664 | 0 | 0 | 0 | 0 | 2021-06-18 | 161075 | BL-0: | BL-0: 35225824_FRRB - Wyandotte 1103 HWY 162_08W - May 21 | 2021-05-25 | 2021-01-24 | Completed | 2021-02-26 | 2021-03-05 | Completed | 2021-01-25 | Completed | 2021-03-23 | Completed | 2021-01-22 | 2021-01-22 | Completed | 2021-02-08 | 2021-05-03 | Completed | 2020-12-14 | 2020-12-28 | Completed | 2021-04-05 | Completed | 2021-04-05 | Completed | 2021-06-14 | Completed | 2021-05-24 | Completed | 2021-06-18 | Not Started | 2021-07-12 | Not Started | 2021-09-20 | 2021-09-13 | 7 | On/ Ahead Schedule | Not Started | 2021-09-14 | 2021-09-27 | Not Started | 2021-11-10 | Not Started
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 | E.5014771.03 | 5785973 | CONS | 08W | [6 empty] | Not in the WP | 2020 | SH | SONORA | Yosemite Assets | 0 | 5484 | 0 | 5484 | 1.0386 | 0 | 0 | 0 | 1.0386 | [5 empty] | 2865068 | 1066735.5 | 1798332.5 |  |  | 92464.4 | 0 | 1705868.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16671 | -16671 | 16671 | -16671 | 1117512.3 | 0 | -42.6 | 42.6 | 0 | 398.5 | 75437.6 | 16628.2 | 1025005.3 | 0 | 11462 | 725 | 1204 | 1378 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 160679 | BL-1 | BL-1 35115051_CWSP - MIWUK 1701 - OCB - PH 1.3_08W - DD 210507 | 2021-05-13 | 2020-03-03 | Completed | 2020-06-17 | 2020-06-23 | Completed | 2020-03-03 | Completed | 2020-07-06 | Completed | 2020-09-04 | 2020-09-04 | Completed | 2020-09-08 | 2020-11-20 | Completed | 2020-08-04 | 2020-09-25 | Completed | 2022-01-05 | Not Started |  |  |  |  | 2022-01-05 | Not Started | 2022-02-08 | Not Started | 2022-03-01 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-23 | Not Started
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 | E.5014771.04 | 5785974 | CONS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 8551 | 0 | 8551 | 1.6195 | 0 | 0 | 0 | 1.6195 | [5 empty] | 4217803 | 1291313.2 | 2926489.8 |  |  | 403370.8 | 0 | 2523119 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 22989 | -22989 | 22989 | -22989 | 1794448.8 | 290.1 | -60 | 350.1 | 0 | 1234.8 | 381300.9 | 20835.1 | 1388924.1 | 0 | -906 | 7911 | 5964 | 8368 | -441 | 290 | 301 | 301 | 301 | 301 | 301 | 301 | 2021-06-18 | 160680 | BL-1 | BL-1 35115052_CWSP - MIWUK 1701 - OCB - PH 1.4_08W - DD 210507 | 2021-05-13 | 2020-07-31 | Completed | 2020-07-10 | 2020-07-10 | Completed | 2020-03-19 | Completed | 2020-08-04 | Completed | 2022-01-04 | 2022-01-04 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2020-09-28 | 2020-09-28 | Completed | 2022-01-06 | Not Started |  |  |  |  | 2022-01-06 | Not Started | 2022-02-16 | Not Started | 2022-03-09 | Not Started | 2022-04-08 | 2022-04-08 | 0 | On/ Ahead Schedule | Not Started | 2022-04-11 | 2022-04-22 | Not Started | 2022-05-31 | Not Started
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 | E.5014771.05 | 5785975 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9571 | 0 | 9571 | 1.8127 | 1.8127 | 0 | 0 | 1.8127 | 9083 | 0 | 1.7203 | 0 |  | 2296559 | 626143.5 | 1670415.5 |  |  | 852855.7 | 388791.7 | 428768.1 | On/Under Budget | Budget Allocated | 8996 | 223120 | -214124 | 223120 | -214124 | 856179.9 | 97925.2 | 105459.5 | -7534.3 | 0 | 468.6 | 632591.2 | 219796 | 0 | 0 | 14399 | 8567 | 39329 | 20637 | 31406 | 97925 | 8393 | 2466 | 0 | 0 | 0 | 0 | 2021-06-18 | 152832 | BL-1 | BL-1 35115053_CWSP - MIWUK 1701 - OCB - PH 1.5_08W - Dec. 2020 | 2020-12-29 | 2020-04-06 | Completed | 2020-04-24 | 2020-05-21 | Completed | 2020-04-08 | Completed | 2020-01-30 | Completed | 2020-10-30 | 2020-10-30 | Completed | 2020-11-02 | 2020-11-03 | Completed | 2020-02-26 | 2020-07-22 | Completed | 2020-08-11 | Completed |  |  |  |  | 2020-08-11 | Completed | 2021-08-13 | Not Started | 2021-09-09 | Not Started | 2021-04-20 | 2021-09-10 | -143 | Behind Schedule | Not Started | 2021-09-24 | 2021-10-07 | Not Started | 2021-11-01 | Not Started
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 | E.5015427.02 | 5785986 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 7523 | 0 | 7523 | 1.4248 | 1.4248 | 0 | 1.3915 | 0.033333 | 7529 | 0 | 1.4259 | 0 |  | 3789178 | 1306517 | 2482661 |  |  | 1538292 | 283655.3 | 660713.7 | On/Under Budget | Budget Allocated | 747161.7 | 628629 | 118532.7 | 628629 | 118532.7 | 1768745.6 | 361404.8 | 130951.2 | 230453.6 | 0 | 6442.2 | 1133674.4 | 398175.3 | 0 | 0 | 109609 | 47982 | -46364 | 35117 | 120881 | 361405 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161080 | BL-1 | BL-1 35115054_CWSP - MIWUK 1701 - OCB - PH 2.2_08W - DD 210521 | 2021-05-26 | 2020-02-18 | Completed | 2020-06-29 | 2020-07-30 | Completed | 2020-03-31 | Completed | 2020-07-02 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-08-03 | 2020-09-15 | Completed | 2020-08-24 | Completed |  |  |  |  | 2020-08-24 | Completed | 2021-05-28 | Completed | 2021-05-21 | Completed | 2021-07-29 | 2021-07-29 | 0 | On/ Ahead Schedule | Not Started | 2021-07-05 | 2021-07-16 | Not Started | 2021-12-23 | Not Started
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 | E.5015427.03 | 5785987 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | SONORA | Yosemite Assets | 0 | 11269 | 0 | 11269 | 2.1343 | 2.1343 | 0 | 2.3053 | -0.17102 | 11269 | 0 | 2.1343 | 0 |  | 3784068 | 882708.1 | 2901359.9 |  |  | 2210824.9 | 0 | 690535 | On/Under Budget | Budget Allocated | 1023108 | 1210830 | -187722 | 1210830 | -187722 | 1965857.6 | 0 | 244967.3 | -244967.3 | 0 | 0 | 755027.7 | 1455797.2 | 0 | 0 | 123991 | 148754 | 197550 | 222331 | 518204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 152685 | BL-1 | BL-1 35115055_CWSP - MIWUK 1701 - OCB - PH 2.3_08W - Dec. 2020 | 2020-12-21 | 2020-04-21 | Completed | 2020-05-21 | 2020-06-09 | Completed | 2020-03-17 | Completed | 2020-06-15 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-07-17 | 2020-08-06 | Completed | 2020-05-26 | 2020-07-20 | Completed | 2020-12-31 | Completed |  |  |  |  | 2020-12-31 | Completed | 2021-05-21 | Completed | 2021-06-18 | Not Started | 2021-04-26 | 2021-07-21 | -86 | Behind Schedule | Not Started | 2021-07-05 | 2021-07-16 | Not Started | 2021-09-10 | Not Started
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 | E.5015427.04 | 5785988 | CONS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9236 | 0 | 9236 | 1.7492 | 0 | 0 | 0 | 1.7492 | [5 empty] | 4578906 | 1309425.5 | 3269480.5 |  |  | 521742.3 | 0 | 2747738.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 41854 | -41854 | 41854 | -41854 | 2237672.9 | 570.8 | 1034.8 | -464 | 0 | 2309.8 | 480665.1 | 38767.4 | 1712843.7 | 0 | 7619 | 19478 | 8637 | -3349 | 5349 | 571 | 592 | 592 | 592 | 592 | 592 | 592 | 2021-06-18 | 160685 | BL-1 | BL-1 35115056_CWSP - MIWUK 1701 - OCB - PH 2.4_08W - DD 210507 | 2021-05-13 | 2020-07-07 | Completed | 2020-06-17 | 2020-06-23 | Completed | 2020-02-14 | Completed | 2020-07-08 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-09-18 | 2020-10-13 | Completed | 2020-08-03 | 2020-09-15 | Completed | 2022-02-09 | Not Started |  |  |  |  | 2022-02-09 | Not Started | 2022-04-07 | Not Started | 2022-04-22 | Not Started | 2022-06-07 | 2022-06-07 | 0 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-07-28 | Not Started
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | E.5015489.04 | 5786133 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 4147 | 0 | 4147 | 0.78542 | 0.62538 | 0 | 0.78542 | 0 | 4147 | 4011 | 0.78542 | 0.75966 |  | 1763594 | 310101.6 | 1453492.4 |  |  | 760595.2 | 149390.7 | 543506.5 | On/Under Budget | Budget Allocated | 428517.6 | 179709 | 248808.6 | 179709 | 248808.6 | 767079.6 | 7902.3 | 4031 | 3871.3 | 0 | 2114.2 | 585256.5 | 173224.5 | 0 | 0 | 21980 | 5799 | 7621 | 9365 | 124428 | 7902 | 2613 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157100 | BL-0 | BL-0 35114102_CWSP - Camp Evers 2106 - LR5020 - PH 2.4_08W - Mar. 2021 | 2021-03-07 | 2020-04-27 | Completed | 2020-05-07 | 2020-05-19 | Completed | 2020-03-16 | Completed | 2020-05-01 | Completed | 2020-04-28 | 2020-05-01 | Completed | 2020-05-01 | 2020-07-28 | Completed | 2020-05-19 | 2020-06-23 | Completed | 2020-08-04 | Completed |  |  |  |  | 2020-08-04 | Completed | 2021-05-21 | Completed | 2021-05-21 | Completed | 2021-11-17 | 2021-05-21 | 180 | On/ Ahead Schedule | Completed | 2021-05-24 | 2021-05-28 | Completed | 2021-08-09 | Not Started
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | E.5015489.05 | 5786203 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 6968 | 0 | 6968 | 1.3197 | 1.3197 | 0 | 1.3197 | 0 | 5963 | 5963 | 1.1294 | 1.1294 |  | 2335115 | 391451.6 | 1943663.4 |  |  | 1042761.2 | 134537.7 | 766364.5 | On/Under Budget | Budget Allocated | 506601.3 | 528343 | -21741.7 | 528343 | -21741.7 | 1047611.1 | 9181.8 | 7592.7 | 1589.1 | 0 | 1388.8 | 517879 | 523493.5 | 0 | 0 | 150007 | 24443 | 99772 | 78819 | 162859 | 9182 | 3261 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157102 | BL-0 | BL-0 35114103_CWSP - Camp Evers 2106 - LR5020 - PH 2.5_08W - Mar. 2021 | 2021-03-07 | 2020-07-03 | Completed | 2020-07-07 | 2020-07-16 | Completed | 2020-04-23 | Completed | 2020-07-16 | Completed | 2020-02-03 | 2020-07-17 | Completed | 2020-07-16 | 2020-07-31 | Completed | 2020-07-27 | 2020-10-31 | Completed | 2020-08-03 | Completed |  |  |  |  | 2020-08-03 | Completed | 2021-05-21 | Completed | 2021-05-21 | Completed | 2021-11-26 | 2021-05-21 | 189 | On/ Ahead Schedule | Completed | 2021-05-21 | 2021-05-28 | Completed | 2022-01-14 | Not Started
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | E.5014745.02 | 5785991 | CONS | 08W | [6 empty] | 2022 |  | SH | JACKSON | Stockton Assets | 477 | 7362 | 0 | 7839 | 1.4847 | 0 | 1.4847 | 0 | 1.4847 | 7860 | 0 | 1.4886 | 0 |  | 4232824 | 1125591.9 | 3107232.1 |  |  | 1240485.5 | 20400 | 1846346.6 | On/Under Budget | Budget Allocated | 1750000 | 1555229 | 194771 | 1555229 | 194771 | 2700965.1 | 9772.2 | -9990.1 | 19762.3 | 0 | 0 | 1145736.3 | 94749.3 | 0 | 0 | 65502 | 6711 | 11580 | 12251 | 8696 | 9772 | 705388 | 730700 | 2315 | 2315 | 0 | 0 | 2021-06-18 | 154955 | BL-0 | BL-0 35114040_CWSP - PINE GROVE 1102 - LR1222 - PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-04-24 | Completed | 2020-06-18 | 2020-07-06 | Completed | 2020-07-17 | Completed | 2020-07-07 | Completed | 2020-07-20 | 2020-07-20 | Completed | 2020-07-31 | 2020-08-06 | Completed | 2020-07-13 | 2020-07-31 | Completed | 2020-07-29 | Completed |  |  |  |  | 2020-07-29 | Completed | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-06-03 | 2021-09-01 | -90 | Behind Schedule | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-10-22 | Not Started
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | E.5014745.03 | 5785992 | CONS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6879 | 0 | 6879 | 1.3028 | 0 | 0 | 0 | 1.3028 | [5 empty] | 2760383 | 868839 | 1891544 |  |  | 394307.6 | 0 | 1497236.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16728 | -16728 | 16728 | -16728 | 1427426.4 | 0 | -11108.7 | 11108.7 | 0 | 633.3 | 388054.7 | 5619.6 | 1022010.1 | 0 | 5489 | 2291 | 3713 | 2948 | 2288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154915 | BL-0 | BL-0 35114041_CWSP - PINE GROVE 1102 - LR1222 - PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-17 | Completed | 2020-06-26 | 2020-07-16 | Completed | 2020-06-15 | Completed | 2020-07-16 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-07 | 2020-08-11 | Completed | 2020-07-27 | 2020-08-25 | Completed | 2022-03-07 | Not Started |  |  |  |  | 2022-03-07 | Not Started | 2022-05-03 | Not Started | 2022-05-03 | Not Started | 2022-06-14 | 2022-06-14 | 0 | On/ Ahead Schedule | Not Started | 2022-06-15 | 2022-06-28 | Not Started | 2022-08-04 | Not Started
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 | E.5014773.05 | 5785979 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 8992 | 0 | 8992 | 1.703 | 1.703 | 0 | 1.703 | 0 | 9032 | 9032 | 1.7106 | 1.7106 |  | 3714853 | 1234918.8 | 2479934.2 |  |  | 1442451.7 | 4418 | 1033064.5 | On/Under Budget | Budget Allocated | 134201.4 | 807595 | -673393.6 | 807595 | -673393.6 | 1417318 | 0 | 25133.7 | -25133.7 | 0 | 200.3 | 609523.2 | 832728.2 | 0 | 0 | 134721 | 157392 | 269781 | 209405 | 36295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159303 | BL-2 | BL-2 35116395_CWSP - MIWUK 1702 - OCB - PH 1.5_08W - DD 210416 | 2021-04-19 | 2020-05-22 | Completed | 2020-06-30 | 2020-07-16 | Completed | 2020-05-29 | Completed | 2020-07-06 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-08-04 | 2020-08-18 | Completed | 2020-07-22 | 2020-09-15 | Completed | 2021-01-11 | Completed | [6 empty] | 2021-04-16 | Completed | 2021-04-02 | Completed | 2021-05-17 | 2021-06-18 | -32 | Behind Schedule | Not Started | 2021-06-21 | 2021-07-02 | Not Started | 2021-11-12 | Not Started
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 | E.5014722.02 | 5785929 | CONS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11216 | 0 | 11216 | 2.1242 | 0 | 0 | 0 | 2.1242 | [5 empty] | 6123271 | 1791846.5 | 4331424.5 |  |  | 583190.4 | 0 | 3748234.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 35388 | -35388 | 35388 | -35388 | 3615717.7 | 625.3 | -3500 | 4125.3 | 0 | 2160.8 | 553655.6 | 27373.9 | 3024512.5 | 0 | 4225 | 9612 | 6609 | 5616 | 4813 | 625 | 648 | 648 | 648 | 648 | 648 | 648 | 2021-06-18 | 160665 | BL-B1 | BL-B1 35116396_CWSP - MIWUK 1702 - LR 8090 - PH 1.2_08W - DD 210507 | 2021-05-13 | 2020-05-30 | Completed | 2020-08-24 | 2020-09-14 | Completed | 2020-07-14 | Completed | 2020-07-15 | Completed | 2020-08-10 | 2020-11-06 | Completed | 2020-11-09 | 2020-11-09 | Completed |  |  |  | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-07-07 | Not Started | 2022-09-22 | Not Started | 2022-09-22 | 2022-09-22 | 0 | On/ Ahead Schedule | Not Started | 2022-07-29 | 2022-08-11 | Not Started | 2023-02-16 | Not Started
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | E.5014733.02 | 5785966 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 7319 | 0 | 7319 | 1.3862 | 1.3862 | 0 | 1.25 | 0.13617 | 7319 | 0 | 1.3862 | 0 |  | 3758449 | 1211428 | 2547021 |  |  | 1530460.5 | 107630.3 | 908930.2 | On/Under Budget | Budget Allocated | 850000 | 685917 | 164083 | 685917 | 164083 | 1683138.3 | 9025.9 | -8497 | 17522.9 | 0 | 15415.3 | 981805.6 | 533239.6 | 0 | 0 | 63385 | 23063 | 233860 | 186788 | 34641 | 9026 | 120455 | 9800 | 4900 | 0 | 0 | 0 | 2021-06-18 | 156215 | BL-2 | BL-2 35116383_CWSP - MIWUK 1701 - LR 8060 - PH 1.2_08W - DD 210219 Feb. 2021 | 2021-02-23 | 2019-12-02 | Completed | 2020-06-30 | 2020-06-30 | Completed | 2020-11-06 | Completed | 2020-06-30 | Completed | 2020-11-06 | 2020-11-06 | Completed | 2020-11-06 | 2020-11-09 | Completed | 2020-11-06 | 2020-11-12 | Completed | 2021-03-08 | Completed |  |  |  |  | 2021-03-08 | Completed | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-06-30 | 2021-09-30 | -92 | Behind Schedule | Not Started | 2021-10-01 | 2021-10-01 | Not Started | 2021-11-22 | Not Started
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | E.5014733.03 | 5785967 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 9700 | 0 | 9700 | 1.8371 | 1.8371 | 0 | 1.7788 | 0.058333 | 9700 | 0 | 1.8371 | 0 |  | 4624169 | 1384789.4 | 3239379.6 |  |  | 1028926.2 | 855356.2 | 1355097.2 | On/Under Budget | Budget Allocated | 3135435 | 1704249 | 1431186 | 1704249 | 1431186 | 1808196.7 | 294005.9 | -707725.8 | 1001731.7 | 0 | 202.9 | 103744.5 | 924978.9 | 0 | 0 | 19035 | 3272 | 466720 | 265104 | 878574 | 294006 | -108222 | -114240 | 0 | 0 | 0 | 0 | 2021-06-18 | 152833 | BL-1 | BL-1 35116384_CWSP - MIWUK 1701 - LR 8060 - PH 1.3_08W - Dec. 2020 | 2020-12-29 | 2020-05-08 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-06-22 | Completed | 2020-10-30 | Completed | 2020-11-02 | 2020-11-02 | Completed | 2021-04-06 | 2021-04-06 | Completed | 2020-09-01 | 2020-11-02 | Completed | 2021-04-15 | Completed |  |  |  |  | 2021-04-15 | Completed | 2021-05-24 | Completed | 2021-06-18 | Not Started | 2021-04-22 | 2021-08-05 | -105 | Behind Schedule | Not Started | 2021-06-23 | 2021-06-24 | Not Started | 2021-08-11 | Not Started
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | E.5015568.03 | 5785722 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 8460 | 0 | 8460 | 1.6023 | 1.6023 | 0 | 0 | 1.6023 | 8271 | 0 | 1.5665 | 0 |  | 3591121 | 911634.7 | 2679486.3 |  |  | 906660.2 | 354124.9 | 1418701.2 | On/Under Budget | Budget Allocated | 2229051.5 | 2258400 | -29348.5 | 2258400 | -29348.5 | 2708835 | 172243.6 | 48179.6 | 124064 | 0 | 0 | 450434.8 | 456225.5 | 0 | 0 | 3023 | 2878 | 49955 | 352870 | -680 | 172244 | 3111 | 0 | 0 | 0 | 1000000 | 675000 | 2021-06-18 | 159404 | BL-2_ | BL-2_35115152_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.3_08W_Apr.2021 | 2021-04-22 | 2020-08-25 | Completed | 2020-08-27 | 2020-09-14 | Completed | 2020-08-31 | Completed | 2020-09-17 | Completed | 2020-07-29 | 2020-07-29 | Completed | 2021-05-13 | 2021-05-13 | Completed | 2020-07-30 | 2020-09-01 | Completed | 2021-05-14 | Completed |  |  |  |  | 2021-05-14 | Completed | 2021-07-15 | Not Started | 2021-07-29 | Not Started | 2022-04-27 | 2021-09-29 | 210 | On/ Ahead Schedule | Not Started | 2021-09-30 | 2021-10-13 | Not Started | 2021-11-19 | Not Started
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | E.5015568.04 | 5785723 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9476 | 0 | 9476 | 1.7947 | 1.7947 | 0 | 0.62235 | 1.1723 | 9476 | 0 | 1.7947 | 0 |  | 4734585 | 1528234.3 | 3206350.7 |  |  | 1260255.1 | 193208.3 | 1752887.3 | On/Under Budget | Budget Allocated | 3080584.2 | 3012874 | 67710.2 | 3012874 | 67710.2 | 3488901.1 | 1571.3 | 72925.3 | -71354 | 0 | 0 | 476027.2 | 784228 | 0 | 0 | 3294 | 31283 | 329761 | 173334 | 173632 | 1571 | 0 | 0 | 0 | 1000000 | 1000000 | 300000 | 2021-06-18 | 157121 | BL-1 | BL-1 35115153_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.4_08W - Mar. 2021 | 2021-03-07 | 2020-06-30 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-06-05 | Completed | 2020-07-30 | Completed | 2020-07-23 | 2020-07-23 | Completed | 2020-08-21 | 2020-08-21 | Completed | 2020-07-13 | 2020-08-21 | Completed | 2021-03-08 | Completed |  |  |  |  | 2021-03-08 | Completed | 2021-07-09 | Not Started | 2021-07-06 | Not Started | 2021-08-11 | 2021-08-05 | 6 | On/ Ahead Schedule | Not Started | 2021-08-06 | 2021-08-19 | Not Started | 2021-09-27 | Not Started
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | E.5015568.05 | 5785724 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 8692 | 0 | 8692 | 1.6462 | 1.6462 | 0 | 1.6462 | 0 | 8692 | 0 | 1.6462 | 0 |  | 3872109 | 1075736.8 | 2796372.2 |  |  | 1987856.3 | 16780 | 791735.9 | On/Under Budget | Budget Allocated | 2584854.1 | 2583921 | 933.1 | 2583921 | 933.1 | 3556969.5 | 35474.4 | 21361.2 | 14113.2 | 0 | 3521.5 | 969527.1 | 1014807.7 | 0 | 0 | 95427 | 63116 | 191290 | 422832 | 220782 | 35474 | 0 | 0 | 0 | 1000000 | 555000 | 0 | 2021-06-18 | 157122 | BL-1 | BL-1 35115154_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.5_08W - Mar. 2021 | 2021-03-07 | 2020-06-30 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-06-05 | Completed | 2020-07-30 | Completed | 2020-07-23 | 2020-07-23 | Completed | 2020-08-20 | 2020-08-20 | Completed | 2020-07-22 | 2020-10-15 | Completed | 2021-03-17 | Completed |  |  |  |  | 2021-03-17 | Completed | 2021-07-07 | Not Started | 2021-07-26 | Not Started | 2021-08-06 | 2021-09-07 | -32 | Behind Schedule | Not Started | 2021-09-08 | 2021-09-21 | Not Started | 2021-10-28 | Not Started
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | E.5015235.03 | 5786023 | CONS | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 5916 | 0 | 5916 | 1.1205 | 0 | 0 | 0 | 1.1205 | [5 empty] | 868859.26 | -1269754.74 | 2138614 |  |  | 125707.1 | 807420 | 1205486.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 11569 | -11569 | 11569 | -11569 | 1168473 | 198 | -31931.7 | 32129.7 | 0 | 1552 | 145946.7 | -21791.7 | 1009404.8 | 0 | 4946 | 1016 | 1589 | 1800 | 790 | 198 | 205 | 205 | 205 | 205 | 205 | 205 | 2021-06-18 | 154962 | BL-0 | BL-0 35115854_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-15 | Completed | 2020-08-20 | 2020-08-21 | Completed | 2020-10-27 | Completed | 2020-08-31 | Completed | 2022-05-09 | 2022-05-09 | Not Started | 2022-05-10 | 2022-06-06 | Not Started | 2020-08-31 | 2020-10-24 | Completed | 2022-09-27 | Not Started |  |  |  |  | 2022-09-27 | Not Started | 2022-11-23 | Not Started | 2022-12-07 | Not Started | 2022-08-12 | 2023-01-06 | -147 | Behind Schedule | Not Started | 2023-01-09 | 2023-01-20 | Not Started | 2023-02-28 | Not Started
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | E.5014776.04 | 5785983 | CONS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10249 | 0 | 10249 | 1.9411 | 0 | 0 | 0 | 1.9411 | [5 empty] | 4826121 | 1480335.8 | 3345785.2 |  |  | 743937.5 | 0 | 2601847.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -61160 | 61160 | -61160 | 61160 | 945395 | 1021.7 | 0 | 1021.7 | 0 | 441.5 | 812043 | -68547 | 194070.6 | 0 | -7344 | -2957 | -55021 | -7624 | 4399 | 1022 | 1061 | 1061 | 1061 | 1061 | 1061 | 1061 | 2021-06-18 | 160683 | BL-1 | BL-1 35116443_CWSP - MIWUK 1702 - LR 38218 - PH 1.4_08W - DD 210507 | 2021-05-13 | 2020-04-16 | Completed | 2020-07-15 | 2020-07-20 | Completed | 2020-03-03 | Completed | 2020-07-27 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-11 | 2020-08-11 | Completed | 2020-08-03 | 2020-08-21 | Completed | 2020-09-01 | Completed |  |  |  |  | 2020-09-01 | Completed | 2022-03-23 | Not Started | 2022-04-07 | Not Started | 2022-05-06 | 2022-05-06 | 0 | On/ Ahead Schedule | Not Started | 2022-05-09 | 2022-05-20 | Not Started | 2022-06-28 | Not Started
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | E.5014776.05 | 5785984 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 11100 | 0 | 11100 | 2.1023 | 2.1023 | 0 | 0 | 2.1023 | 11100 | 0 | 2.1023 | 0 |  | 3531134 | 882956.8 | 2648177.2 |  |  | 884502.3 | 0 | 1763674.9 | On/Under Budget | Budget Allocated | 559463 | 707103 | -147640 | 707103 | -147640 | 1592726.5 | 166055.6 | -379 | 166434.6 | 0 | 1350.4 | 884272.9 | -1121 | 0 | 0 | 11765 | -93841 | 43402 | 27211 | 10721 | 166056 | 364743 | 177046 | 0 | 0 | 0 | 0 | 2021-06-18 | 151457 | BL-0 | BL-0 35116444_CWSP - MIWUK 1702 - LR 38218 - PH 1.5_08W - Nov. 2020 | 2020-11-12 | 2020-04-07 | Completed | 2020-04-27 | 2020-04-27 | Completed | 2020-03-31 | Completed | 2020-07-27 | Completed | 2020-07-15 | 2020-07-15 | Completed | 2020-10-30 | 2020-10-30 | Completed | 2020-03-30 | 2020-06-12 | Completed | 2020-08-04 | Completed |  |  |  |  | 2020-08-04 | Completed | 2021-08-03 | Not Started | 2021-08-18 | Not Started | 2021-04-15 | 2021-09-16 | -154 | Behind Schedule | Not Started | 2021-09-17 | 2021-09-30 | Not Started | 2021-11-08 | Not Started
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | E.5014730.03 | 5785962 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 580 | 6197 | 0 | 6777 | 1.2835 | 0.91345 | 0 | 1.0979 | 0.18561 | 6747 | 0 | 1.2778 | 0 |  | 3408934 | 1074988.8 | 2333945.2 |  |  | 1595065.9 | 397391.2 | 341488.1 | On/Under Budget | Budget Allocated | 441774.7 | 403644 | 38130.7 | 403644 | 38130.7 | 1790157.9 | 0 | -195092 | 195092 | 0 | 1320.5 | 1385193.6 | 208551.7 | 0 | 0 | 8464 | 14780 | 233318 | 78445 | 68638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161078 | BL-1 | BL-1 35116801_CWSP - MIWUK 1702 - LR 6018 - PH 1.3_08W - DD 210521 | 2021-05-26 | 2020-04-15 | Completed | 2020-06-22 | 2020-07-06 | Completed | 2020-05-05 | Completed | 2020-07-06 | Completed | [6 empty] | 2020-07-20 | 2020-07-27 | Completed | 2020-08-10 | Completed | [6 empty] | 2021-05-03 | Completed | 2021-05-21 | Completed | 2021-07-02 | 2021-07-02 | 0 | On/ Ahead Schedule | Not Started | 2021-06-21 | 2021-07-02 | Not Started | 2021-12-03 | Not Started
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | E.5015531.05 | 5788624 | CONS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 2600 | 0 | 2600 | 0.49242 | 0 | 0 | 0 | 0.49242 | [5 empty] | 1844178 | 737162 | 1107016 |  |  | 339002.6 | 6525.9 | 761487.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 20815 | -20815 | 20815 | -20815 | 343175.1 | 160.6 | 234 | -73.4 | 0 | 235.3 | 322124.6 | 16642.7 | 0 | 0 | 6416 | 2067 | 2754 | 2975 | 2196 | 161 | 167 | 167 | 167 | 167 | 167 | 3411
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | 5530169 | CONS | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 9316 | 0 | 9316 | 1.7644 | 0 | 0 | 1.7644 | 0 | 9316 | 0 | 1.7644 | 0 |  | 347534 | 0 | 347534 |  |  | 128509 | 0 | 219025 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3428 | -3428 | 3428 | -3428 | 128279.3 | 0 | 229.7 | -229.7 | 0 | 641.1 | 124210.3 | 3657.6 | 0 | 0 | 0 | 230 | 1142 | 1142 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145878 | BL-0 | BL-0 35135864_CWSP - GRAYS FLAT 401 FUSE 3079 ZONE_08W - Oct. 2020 | 2020-07-25 | 2020-02-07 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-03-26 | Completed | 2020-06-15 | Completed | 2020-02-28 | 2020-02-28 | Completed | 2020-04-16 | 2020-04-17 | Completed | 2019-10-29 | 2019-11-05 | Completed | 2020-05-26 | Completed |  |  |  |  | 2020-05-26 | Completed | 2020-08-05 | Completed | 2020-08-05 | Completed | 2020-10-14 | 2020-08-05 | 70 | On/ Ahead Schedule | Completed | 2020-08-10 | 2020-08-19 | Completed | 2021-07-26 | Not Started
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | 5784869 | CONS | 08W | [6 empty] | 2021 |  |  | NAPA | North Bay Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6693 | 0 | 1.2676 | 0 |  | 1800635 | 396300.6 | 1404334.4 |  |  | 432195.3 | 0 | 972139.1 | On/Under Budget | Request 2021 Budget | 0 | -475981 | 475981 | -475981 | 475981 | 0.3 | -432195 | 0 | -432195 | 0 | 0 | 475981 | -43785.7 | 0 | 0 | -33985 | -9801 | 1121565 | -1121565 | 0 | -432195 | 0 | 0 | 0 | 0 | 0 | 0
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | E.5014776.01 | 5785219 | CONS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11546 | 0 | 11546 | 2.1867 | 0 | 0 | 0 | 2.1867 | [5 empty] | 5180025 | 1156134.2 | 4023890.8 |  |  | 651068.5 | 117051 | 3255771.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -7928 | 7928 | -7928 | 7928 | 1898953.7 | 1002.3 | 0 | 1002.3 | 771.6 | 11640.1 | 653821.8 | -15165 | 1240648.4 | 0 | 3781 | -31931 | 5065 | 4290 | 3630 | 1002 | 1039 | 1039 | 1039 | 1039 | 1039 | 1039 | 2021-06-18 | 160681 | BL-1 | BL-1 35052739_CWSP - MIWUK 1702 - LR 38218 - PH 1.1_08W - DD 210507 | 2021-05-13 | 2020-04-13 | Completed | 2020-03-17 | 2020-03-17 | Completed | 2020-03-16 | Completed | 2020-06-26 | Completed | 2020-09-25 | 2020-10-01 | Completed | 2020-10-01 | 2020-10-01 | Completed | 2020-03-16 | 2020-04-21 | Completed | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started |  |  | 2022-03-21 | Not Started | 2022-04-01 | 2022-04-01 | 0 | On/ Ahead Schedule | Not Started | 2022-04-05 | 2022-04-18 | Not Started | 2022-05-24 | Not Started
35052821 | T2/T3-CWSP - MIWUK 1701 OCB - PH 1.1 | E.5014771.01 | 5784646 | CONS | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 11041 | 0 | 11041 | 2.0911 | 2.0911 | 0 | 2.0911 | 3.4451e-16 | 10953 | 0 | 2.0744 | 0 |  | 4765282 | 1442306.6 | 3322975.4 |  |  | 1172477.8 | 567878.6 | 1582619 | On/Under Budget | Budget Allocated | 1382243 | 976055 | 406188 | 976055 | 406188 | 1542191.6 | 85789.2 | -472953.6 | 558742.8 | 7486.6 | 9282.8 | 549366.9 | 606341.5 | 0 | 0 | 87990 | 10201 | 347327 | 601263 | 32515 | 85789 | 0 | -189029 | 0 | 0 | 0 | 0 | 2021-06-18 | 152831 | BL-1 | BL-1 35052821_CWSP - MIWUK 1701 - OCB - PH 1.1_08W - Dec. 2020 | 2020-12-29 | 2019-12-20 | Completed | 2020-07-10 | 2020-07-10 | Completed | 2020-06-02 | Completed | 2020-08-04 | Completed | 2020-08-24 | 2020-08-24 | Completed | 2020-08-04 | 2020-08-04 | Completed | 2020-09-28 | 2020-09-28 | Completed | 2020-08-31 | Completed |  |  |  |  | 2020-08-31 | Completed |  |  | 2021-04-16 | Completed | 2022-05-18 | 2021-08-06 | 285 | On/ Ahead Schedule | Not Started | 2021-08-09 | 2021-08-20 | Not Started | 2021-10-12 | Not Started
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | E.5014722.01 | 5785221 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 6168 | 0 | 6168 | 1.1682 | 1.1682 | 0 | 1.14 | 0.02822 | 6168 | 0 | 1.1682 | 0 |  | 3544410 | 1202119 | 2342291 |  |  | 921518.2 | 860828.7 | 559944.1 | On/Under Budget | Budget Allocated | 1048628 | 1164189 | -115561 | 1164189 | -115561 | 1639385 | 794127.2 | 78112.1 | 716015.1 | 422.3 | 9464.2 | 465309.1 | 446322.5 | 0 | 0 | 21195 | 3899 | 82035 | 43315 | 217766 | 794127 | 926 | 926 | 0 | 0 | 0 | 0 | 2021-06-18 | 145832 | BL-0: | BL-0: 35052825_CWSP - MIWUK 1702 - LR 8090 - PH 1.1_08W - Oct. 2020 | 2020-07-24 | 2020-04-29 | Completed | 2020-06-25 | 2020-07-14 | Completed | 2020-02-04 | Completed | 2020-07-14 | Completed | 2020-08-15 | 2020-08-18 | Completed | 2020-08-15 | 2020-09-09 | Completed | 2020-08-17 | 2020-10-16 | Completed | 2021-05-03 | Completed | [8 empty] | 2021-06-18 | Not Started | 2020-10-30 | 2021-08-19 | -293 | Behind Schedule | Not Started | 2021-08-20 | 2021-09-02 | Not Started | 2022-01-05 | Not Started
35061206 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH1.1 | E.5015569.01 | 5783070 | CONS | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 9111 | 0 | 9111 | 1.7256 | 1.7256 | 0 | 1.7256 | 0 | 9320 | 0 | 1.7652 | 0 |  | 4711641 | 1252143 | 3459498 |  |  | 2675597.9 | 127047.9 | 656852.2 | On/Under Budget | Budget Allocated | 1419181 | 1422284 | -3103 | 1422284 | -3103 | 3462601.5 | 3790.9 | 26787.3 | -22996.4 | 2773.6 | 14800.2 | 2022743.5 | 635280.6 | 0 | 0 | 20400 | 30761 | 234882 | 195427 | 127024 | 3791 | 0 | 0 | 500000 | 310000 | 0 | 0 | 2021-06-18 | 159408 | BL-2_ | BL-2_35061206_CWSP - Brunkswick 1103 LR50070 ZONE-PH1.1_08W_Apr.2021 | 2021-04-22 | 2020-05-20 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-05-22 | Completed | 2020-07-10 | Completed | 2020-05-20 | 2020-05-20 | Completed | 2020-05-26 | 2020-05-26 | Completed | 2020-06-10 | 2020-07-02 | Completed | 2020-06-15 | Completed |  |  |  |  | 2020-06-15 | Completed | 2021-05-27 | Completed | 2021-05-27 | Completed | 2021-06-23 | 2021-07-07 | -14 | Behind Schedule | Not Started | 2021-07-08 | 2021-07-21 | Not Started | 2021-08-13 | Not Started
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | E.5015568.01 | 5783071 | CONS | 08W | [6 empty] | 2021 |  | SH | GRSSVLLY | Sierra Assets | 0 | 9445 | 0 | 9445 | 1.7888 | 1.7888 | 0 | 1.5051 | 0.28371 | 10109 | 0 | 1.9146 | 0 |  | 4913095 | 1023067.2 | 3890027.8 |  |  | 2271614.1 | 355780.3 | 1262633.4 | On/Under Budget | Budget Allocated | 2161081.9 | 2158907 | 2174.9 | 2158907 | 2174.9 | 3639231.6 | 149245.6 | 7628.1 | 141617.5 | 2055 | 215821.4 | 1262448.4 | 791289.3 | 0 | 0 | 24396 | 110421 | 75425 | 391831 | 181588 | 149246 | 0 | 0 | 500000 | 500000 | 226000 | 0
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | E.5015236.01 | 5783906 | CONS | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 5541 | 0 | 5541 | 1.0494 | 0 | 0 | 0 | 1.0494 | [5 empty] | 2583069 | 651010.4 | 1932058.6 |  |  | 691127.8 | 0 | 1240930.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -61499 | 61499 | -61499 | 61499 | 1741046.7 | 0 | -58221.8 | 58221.8 | 0 | 28472 | 782376.5 | -119720.6 | 991697.1 | 0 | 8708 | -83791 | 5378 | 4319 | 3888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 160684 | BL-1 | BL-1 35072360_CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.1_08W - DD 210507 | 2021-05-13 | 2020-05-19 | Completed | 2020-07-09 | 2020-07-23 | Completed | 2020-07-07 | Completed | 2020-07-23 | Completed | 2020-08-26 | 2020-08-27 | Completed | 2020-09-11 | 2020-10-02 | Completed | 2020-07-02 | 2020-08-14 | Completed | 2022-01-11 | Not Started |  |  |  |  | 2022-01-11 | Not Started |  |  | 2022-02-25 | Not Started | 2022-03-29 | 2022-03-29 | 0 | On/ Ahead Schedule | Not Started | 2022-03-04 | 2022-03-18 | Not Started | 2022-05-03 | Not Started
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | E.5034804.01.13 | 5795299 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 8735 | 117 | 8852 | 1.6765 | 1.6765 | 0 | 0 | 1.6765 | 8735 | 0 | 1.6544 | 0 |  | 3699056 | 954330.7 | 2744725.3 | 0 | 2744725.3 | 334201.9 | 175218.8 | 2235304.6 | On/Under Budget | Budget Allocated | 2505000 | 2522281 | -17281 | 2522281 | -17281 | 2542664.5 | 919861 | 232411.3 | 687449.7 | 0 | 0 | 0 | 334201.9 | 20383.9 | 0 | 0 | 2297 | 5023 | 50750 | 43721 | 919861 | 471883 | 600206 | 106643 | 6828 | 56933 | 258136 | 2021-06-18 | 160054 | BL-0_ | BL-0_35231609_CWSP - SHINGLE SPRINGS 2109-LR9372-PH1.5_08W_May.2021 | 2021-04-30 | 2021-04-29 | Completed | 2021-04-26 | 2021-05-07 | Completed | 2021-05-20 | Completed | 2021-05-27 | Completed | 2021-05-21 | 2021-05-27 | Completed | 2021-05-27 | 2021-06-11 | Completed | 2021-06-03 | 2021-07-02 | In Progress | 2021-06-14 | Completed |  |  |  |  | 2021-06-14 | Completed | 2021-08-27 | Not Started | 2021-09-27 | Not Started | 2022-03-09 | 2021-10-28 | 132 | On/ Ahead Schedule | Not Started | 2021-10-29 | 2021-11-11 | Not Started | 2021-12-27 | Not Started
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | E.5034804.01.14 | 5795299 | CONS | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 3235 | 0 | 3235 | 0.61269 | 0.61269 | 0 | 0 | 0.61269 | 3235 | 0 | 0.61269 | 0 |  | 465706.54 | -432749.06 | 898455.6 | 0 | 898455.6 | 228595.9 | 75786.4 | 594073.3 | On/Under Budget | Budget Allocated | 667231 | 691026 | -23795 | 691026 | -23795 | 691026 | 484955.2 | 29460 | 455495.2 | 0 | 0 | 0 | 228595.9 | 0 | 0 | 0 | 1637 | 33033 | 57865 | 106602 | 484955 | 115549 | 8655 | 0 | -117269 | 0 | 0 | 2021-06-18 | 158759 | BL-0 | BL-0 35232280_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.6_08W - DD 210402 | 2021-04-06 | 2021-03-17 | Completed | 2021-04-01 | 2021-04-01 | Completed | 2021-04-13 | Completed | 2021-04-28 | Completed | 2021-04-26 | 2021-04-27 | Completed | 2021-05-01 | 2021-05-04 | Completed | 2021-04-21 | 2021-05-21 | Completed | 2021-06-09 | Completed |  |  |  |  | 2021-06-09 | Completed | 2021-07-23 | Not Started | 2021-08-02 | Not Started | 2021-09-07 | 2021-09-07 | 0 | On/ Ahead Schedule | Not Started | 2021-09-08 | 2021-09-21 | Not Started | 2021-11-04 | Not Started
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | 5795297 | CONS | 08W | [6 empty] | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 5016 | 0 | 5016 | 0.95 | 0.95 | 0 | 0.95 | 0 | 4355 | 0 | 0.82481 | 0 |  | 512371.91 | 512371.91 | 0 |  |  | 1268700.8 | 729124.4 | -1997825.2 | OverRun | Budget Allocated | 2080934 | 1519511 | 561423 | 1519511 | 561423 | 1519510.4 | 235485.5 | 3729.3 | 231756.2 | 0 | 0 | 0 | 1268700.9 | 0 | 0 | 6031 | 200462 | 646496 | 410197 | 1786 | 235486 | 9527 | 9527 | 0 | 0 | 0 | 0 | 2021-06-18 | 156212 | BL-0 | BL-0 35227201_ECOP-OAKHURST 1103-LR 5120 PH3_08W - DD 210219 | 2021-02-23 | 2021-01-23 | Completed | 2021-03-22 | 2021-03-25 | Completed | 2021-03-02 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-16 | 2021-03-15 | Completed | 2021-02-02 | Completed |  |  |  |  | 2021-02-02 | Completed | 2021-03-15 | Completed | 2021-02-16 | Completed | 2021-05-21 | 2021-07-12 | -52 | Behind Schedule | Not Started | 2021-07-13 | 2021-07-26 | Not Started | 2021-10-06 | Not Started
35227263 | CWSP - MARIPOSA 2102CB PH 2 | E.5034702.01.05 | 5794552 | CONS | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 1315.42 | 0 | 1315.42 | 0.24913 | 0.24905 | 0 | 0 | 0.24913 | [5 empty] | 1012126.18 | 1012126.18 | 0 |  |  | 274834.2 | 341700.8 | -616535 | OverRun | Budget Allocated | 1670921 | 1673026 | -2105 | 1673026 | -2105 | 1673025.6 | 700744.3 | 182434.6 | 518309.7 | 0 | 0 | 0 | 274834.3 | 0 | 0 | 0 | 29628 | 49432 | 9221 | 4119 | 700744 | 386523 | 281615 | 187834 | 19037 | 4873 | 0 | 2021-06-18 | 156029 | BL-A | BL-A 35227263_CWSP - MARIPOSA 2102CB PH 2_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-29 | Completed | 2021-05-26 | 2021-05-28 | Completed | 2021-05-14 | Completed | 2021-06-07 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-05-26 | 2021-06-11 | Completed | 2021-07-20 | Not Started |  |  |  |  | 2021-07-20 | Not Started | 2021-09-13 | Not Started | 2021-08-24 | Not Started | 2021-12-22 | 2021-11-12 | 40 | On/ Ahead Schedule | Not Started | 2021-11-15 | 2021-11-26 | Not Started | 2022-01-11 | Not Started
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | 5795297 | CONS | 08W | [6 empty] | 2021 |  | SH - Wind | OAKHURST | Yosemite Assets | 0 | 5755 | 0 | 5755 | 1.09 | 1.09 | 0 | 1.09 | 0 | 5598 | 0 | 1.0602 | 0 |  | 326951.18 | -2229453.22 | 2556404.4 |  |  | 1368958 | 729124.4 | 458322 | On/Under Budget | Budget Allocated | 2183706 | 1427108 | 756598 | 1427108 | 756598 | 1427107.9 | 8373.5 | 0 | 8373.5 | 0 | 0 | 0 | 1368958 | 0 | 0 | 10027 | 209324 | 650206 | 496564 | 2837 | 8374 | 8296 | 8296 | 8296 | 8296 | 8296 | 8296 | 2021-06-18 | 157021 | BL-0 | BL-0 35227201_ECOP-OAKHURST 1103-LR 5120 PH2_08W - DD 210305 | 2021-03-05 | 2021-01-24 | Completed | 2021-02-23 | 2021-03-18 | Completed | 2021-03-10 | Completed |  |  | 2021-02-04 | 2021-02-04 | Completed | 2021-02-04 | 2021-02-05 | Completed | 2021-02-08 | 2021-03-18 | Completed | 2021-02-22 | Completed |  |  |  |  | 2021-02-22 | Completed | 2021-03-18 | Completed | 2021-03-18 | Completed | 2021-05-31 | 2021-07-12 | -42 | Behind Schedule | Not Started | 2021-07-13 | 2021-07-26 | Not Started | 2021-09-22 | Not Started
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | E.5034804.01.09 | 5795299 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 10780 | 310 | 11090 | 2.1004 | 2.1004 | 0 | 0 | 2.1004 | 10780 | 0 | 2.0417 | 0 |  | 4710436 | 1179380.1 | 3531055.9 | 588000 | 2943055.9 | 156734 | 153667.2 | 3220654.7 | On/Under Budget | Budget Allocated | 3199346 | 3251502 | -52156 | 3251502 | -52156 | 3254004.2 | 109682 | 2797 | 106885 | 0 | 0 | 0 | 156733.9 | 2502.3 | 0 | 0 | 22400 | 77589 | 45163 | 8785 | 109682 | 1657414 | 477072 | 453702 | 26437 | 63897 | 309361 | 2021-06-18 | 160055 | BL-0_ | BL-0_35226854_CWSP - SHINGLE SPRINGS 2109-LR 9372PH3.4_08W_May.2021 | 2021-04-30 | 2021-04-29 | Completed | 2021-04-30 | 2021-05-06 | Completed | 2021-06-08 | Completed | 2021-06-16 | Completed | 2021-06-02 | 2021-06-02 | Completed | 2021-06-11 | 2021-06-11 | Completed | 2021-06-21 | 2021-07-19 | Not Started | 2021-07-01 | Not Started |  |  |  |  | 2021-07-01 | Not Started | 2021-09-30 | Not Started | 2021-10-07 | Not Started | 2022-02-24 | 2021-11-26 | 90 | On/ Ahead Schedule | Not Started | 2021-11-29 | 2021-12-10 | Not Started | 2022-02-14 | Not Started
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | E.5034804.01.01 | 5795299 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 7851 | 0 | 7851 | 1.4869 | 1.4869 | 0 | 0 | 1.4869 | 7851 | 0 | 1.4869 | 0 |  | 3178496 | 860724 | 2317772 | 0 | 2317772 | 306695.3 | 99678 | 1911398.7 | On/Under Budget | Budget Allocated | 2090271.93 | 2083643 | 6628.93 | 2083643 | 6628.93 | 2083642.4 | 668170.2 | 155086.2 | 513084 | 0 | 0 | 0 | 306695.4 | 0 | 0 | 0 | 1584 | 7793 | 70439 | 71794 | 668170 | 430536 | 393803 | 167391 | 14878 | 14878 | 242378 | 2021-06-18 | 161292 | BL-0: | BL-0: 35226846_CWSP - SHINGLE SPRINGS 2109-LR 9372PH1.2_08W - May 21 | 2021-06-02 | 2021-04-12 | Completed | 2021-04-22 | 2021-04-29 | Completed | 2021-04-07 | Completed | 2021-05-11 | Completed | 2021-05-14 | 2021-05-14 | Completed | 2021-05-14 | 2021-05-14 | Completed | 2021-05-24 | 2021-06-11 | Completed | 2021-06-07 | Completed |  |  |  |  | 2021-06-07 | Completed | 2021-08-24 | Not Started | 2021-08-31 | Not Started | 2021-10-22 | 2021-10-18 | 4 | On/ Ahead Schedule | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-15 | Not Started
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | E.5034804.01.02 | 5795299 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 6836 | 1189 | 8025 | 1.5199 | 1.5193 | 0 | 0 | 1.5199 | 6836 | 0 | 1.2947 | 0 |  | 3048485 | 773483 | 2275002 | 0 | 2275002 | 274151.9 | 305392.8 | 1695457.3 | On/Under Budget | Budget Allocated | 2124000 | 2146280 | -22280 | 2146280 | -22280 | 2164796.3 | 739757.5 | 169865.2 | 569892.3 | 0 | 0 | 0 | 274151.8 | 18516.8 | 0 | 0 | 1257 | 5359 | 57419 | 40251 | 739758 | 384760 | 443537 | 257859 | 14692 | 6944 | 194444 | 2021-06-18 | 158884 | BL-A_ | BL-A_35226847_CWSP - SHINGLE SPRINGS 2109-LR 9372PH1.3_08W_Apr.2021 | 2021-04-07 | 2021-04-29 | Completed | 2021-04-30 | 2021-05-06 | Completed | 2021-06-08 | Completed | 2021-05-14 | Completed | 2021-05-21 | 2021-06-04 | Completed | 2021-05-24 | 2021-05-24 | Completed | 2021-06-09 | 2021-07-01 | In Progress | 2021-06-07 | Completed |  |  |  |  | 2021-06-07 | Completed | 2021-08-26 | Not Started | 2021-09-02 | Not Started | 2022-02-18 | 2021-11-25 | 85 | On/ Ahead Schedule | Not Started | 2021-11-26 | 2021-12-09 | Not Started | 2022-01-24 | Not Started
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | E.5034804.01.05 | 5795299 | CONS | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 7748 | 0 | 7748 | 1.4674 | 1.4674 | 0 | 0 | 1.4674 | 7748 | 0 | 1.4674 | 0 |  | 3060229 | 1029543.8 | 2030685.2 | 0 | 2030685.2 | 374407.9 | 246553.1 | 1409724.2 | On/Under Budget | Budget Allocated | 1518941 | 1940537 | -421596 | 1940537 | -421596 | 1740450.6 | 454934.8 | 77325.6 | 377609.2 | 0 | 0 | 0 | 374407.9 | -200086 | 0 | 0 | 1947 | 8667 | 99948 | 186521 | 454935 | 705582 | 474143 | 8795 | 0 | 0 | 0 | 2021-06-18 | 156278 | BL-A | BL-A 35226850_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.4_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-04-09 | Completed | 2021-04-26 | 2021-04-26 | Completed | 2021-04-29 | Completed | 2021-05-04 | Completed | 2021-04-27 | 2021-05-03 | Completed | 2021-05-04 | 2021-05-04 | Completed | 2021-04-29 | 2021-05-27 | Completed | 2021-06-10 | Completed |  |  |  |  | 2021-06-10 | Completed | 2021-08-17 | Not Started | 2021-08-25 | Not Started | 2021-10-22 | 2021-10-25 | -3 | Behind Schedule | Not Started | 2021-10-26 | 2021-11-08 | Not Started | 2021-12-22 | Not Started
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | E.5034804.01.06 | 5795299 | CONS | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 11171 | 0 | 11171 | 2.1157 | 2.1157 | 0 | 0 | 2.1157 | 11171 | 0 | 2.1157 | 0 |  | 3783519 | 1262582.4 | 2520936.6 | 0 | 2520936.6 | 529340.2 | 293517.4 | 1698079 | On/Under Budget | Budget Allocated | 1871077 | 2547263 | -676186 | 2547263 | -676186 | 2281211.7 | 379145.1 | 88067 | 291078.1 | 0 | 0 | 0 | 529340.2 | -266051 | 0 | 0 | 1704 | 5101 | 108693 | 325776 | 379145 | 601121 | 726261 | 399463 | 0 | 0 | 0 | 2021-06-18 | 159854 | BL-0 | BL-0 35226851_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.5_08W - DD 210416 | 2021-04-29 | 2021-04-15 | Completed | 2021-04-26 | 2021-04-26 | Completed | 2021-05-04 | Completed | 2021-05-04 | Completed | 2021-05-04 | 2021-05-04 | Completed | 2021-05-05 | 2021-05-07 | Completed | 2021-05-19 | 2021-06-11 | Completed | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-09-06 | Not Started | 2021-09-21 | Not Started | 2021-11-22 | 2021-11-19 | 3 | On/ Ahead Schedule | Not Started | 2021-11-22 | 2021-12-03 | Not Started | 2022-01-18 | Not Started
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | E.5015487.01 | 5782860 | CONS | 08W | [6 empty] | 2021 | 2021 | SH | GYSRVLLE | Sonoma Assets | 0 | 29328 | 0 | 29328 | 5.5545 | 4.5945 | 0 | 5.1822 | 0.37235 | 28754 | 13252.8 | 5.4458 | 2.51 |  | 9998553 | 778830 | 9219723 |  |  | 8805665.1 | 0 | 414057.9 | On/Under Budget | Budget Allocated | 2395900 | 1984388 | 411512 | 1984388 | 411512 | 8808210.8 | 5704 | 15212.7 | -9508.7 | 8050.7 | 2983380.5 | 3832391.3 | 1981842.5 | 0 | 0 | 411887 | 391478 | 814767 | 262465 | 86033 | 5704 | 5027 | 4018 | 3009 | 0 | 0 | 0 | 2021-06-18 | 161450 | BL-2: | BL-2: 74022384_FITCH MOUNTAIN 1113 LR 24918_08W - June 21 | 2021-06-03 | 2019-06-06 | Completed |  |  | Completed | 2020-06-19 | Completed | 2020-06-02 | Completed | 2020-06-08 | 2020-06-10 | Completed | 2020-06-22 | 2020-06-23 | Completed | 2019-12-04 | 2021-03-19 | Completed | 2020-06-08 | Completed |  |  |  |  | 2020-06-08 | Completed | 2021-04-13 | Completed | 2020-11-18 | Completed | 2021-06-21 | 2021-07-19 | -28 | Behind Schedule | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-09-08 | Not Started
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | E.5014743.02 | 5782598 | CONS | 08W | [6 empty] | 2020 | 2020 | SH | STROSA | Sonoma Assets | 0 | 9716 | 0 | 9716 | 1.8402 | 0 | 0 | 1.8402 | 0 | 13421 | 0 | 2.5419 | 0 |  | 4467090 | -293297 | 4760387 |  |  | 4462143.4 | 0 | 298243.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 173177.8 | 502394 | -329216.2 | 502394 | -329216.2 | 4649356.6 | 7777.5 | 360.5 | 7417 | 0 | 664270.2 | 3482691.9 | 315181.2 | 0 | 0 | 10315 | 277958 | 11351 | 3534 | 11663 | 7778 | 136189 | 27960 | 12869 | 2778 | 0 | 0 | 2021-06-18 | 161672 | BL-1: | BL-1: 74028021_CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2_08W - Jun 21 | 2021-06-14 | 2020-01-30 | Completed | 2020-02-24 | 2020-02-25 | Completed | 2020-03-13 | Completed | 2020-03-16 | Completed | 2020-03-17 | 2020-03-18 | Completed | 2020-03-25 | 2020-04-20 | Completed | 2020-04-13 | 2020-04-14 | Completed | 2020-05-05 | Completed |  |  |  |  | 2020-05-05 | Completed | 2021-08-18 | Not Started | 2020-09-16 | Completed | 2021-09-01 | 2021-09-01 | 0 | On/ Ahead Schedule | Not Started | 2021-09-02 | 2021-09-15 | Not Started | 2021-11-24 | Not Started
35238088 | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | E.5034876.01.01 | 5544972 | DCNL | 08W | [6 empty] | 2021 |  | SH - Remote Grid | MARIPOSA | Yosemite Assets | 0 | 0 | 4435 | 4435 | 0.83996 | 0.83996 | 0 | 0 | 0.83996 | [5 empty] | 500000 | 0 | 500000 |  |  | 51005.1 | 0 | 448994.9 | On/Under Budget | Budget Allocated | 800000 | 44544 | 755456 | 44544 | 755456 | 44544 | 0 | 6461.1 | -6461.1 | 0 | 0 | 0 | 51005.1 | 0 | 0 | 0 | 0 | 7768 | 20268 | 16508 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - | E.5014745.01 | 5785659 | DCNL | 08W | [6 empty] | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 11057.2 | 0 | 11057.2 | 2.0942 | 0 | 0 | 2.0942 | 0 | 10648 | 11292 | 2.0167 | 2.1386 |  | 5851741 | 1219955.8 | 4631785.2 |  |  | 3467109.3 | 0 | 1164675.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4647 | -4647 | 4647 | -4647 | 3467109.3 | 0 | 0 | 0 | 0 | 10569.3 | 3451892.8 | 4647.2 | 0 | 0 | 0 | 0 | 50 | 4042 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-11-18 | Completed | 2020-01-22 | 2020-01-22 | Completed | 2020-03-31 | Completed | 2020-01-17 | Completed | 2020-01-16 | 2020-01-16 | Completed | 2020-02-06 | 2020-04-20 | Completed | 2020-02-10 | 2020-03-10 | Completed | 2020-02-19 | Completed |  |  |  |  | 2020-02-18 | Completed | 2020-05-09 | Completed | 2020-05-11 | Completed | 2020-05-29 | 2020-05-11 | 18 | On/ Ahead Schedule | Completed | 2020-05-12 | 2020-06-30 | Completed | 2021-06-25 | Not Started
35081660 | OH RECONDUCTOR - ROB ROY 2105 -S028CC119 |  | 5519546 | DCNL | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 | E.5014317.04 | 5784869 | DOCC | 08W | [6 empty] | Not in the WP |  |  | NAPA | North Bay Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2298281.08 | 2288281.08 | 10000 |  |  | 86186.2 | 0 | -76186.2 | OverRun | Project is not in the WP or in 2020 WP | 0 | -83753 | 83753 | -83753 | 83753 | 0.2 | -86186 | 0 | -86186 | 0 | 85677.5 | -1924.2 | 2432.9 | 0 | 0 | 507 | 483 | 483 | 480 | 480 | -86186 | 0 | 0 | 0 | 0 | 0 | 0
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | E.5015491.04 | 5785303 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 1770 | 0 | 1770 | 0.33523 | 0 | 0 | 0.33523 | 0 | 5642 | 5706 | 1.0686 | 1.0807 |  | 2927538 | 742038.8 | 2185499.2 |  |  | 1737904 | 0 | 447595.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 131088 | 134712 | -3624 | 134712 | -3624 | 1798084 | 0 | 372.3 | -372.3 | 0 | 35798.4 | 1627573.9 | 74531.7 | 0 | 0 | 8886 | 11599 | 44333 | 5369 | 3973 | 0 | 0 | 0 | 0 | 0 | 30276 | 30276 | 2021-06-18 | 151685 | BL-1 | BL-1 35098621_CWSP-COLUMBIA HILL 1101-LR 2212 PH4_08W - Nov. 2020 | 2020-11-24 | 2019-10-24 | Completed | 2020-05-05 | 2020-05-05 | Completed | 2020-05-25 | Completed | 2020-05-05 | Completed | 2020-05-05 | 2020-05-05 | Completed | 2020-05-01 | 2020-05-29 | Completed | 2020-05-15 | 2020-05-29 | Completed | 2020-06-01 | Completed |  |  |  |  | 2020-06-01 | Completed | 2020-09-29 | Completed | 2020-12-03 | Completed | 2021-01-29 | 2020-12-03 | 57 | On/ Ahead Schedule | Completed | 2021-03-01 | 2021-03-04 | Completed | 2021-06-21 | Not Started
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | E.5015687.01 | 5785218 | DOCC | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 7412 | 0 | 7412 | 1.4038 | 0 | 0 | 1.4038 | 0 | 7328 | 7419 | 1.3879 | 1.4051 |  | 3293522 | 894629.3 | 2398892.7 |  |  | 2121801.7 | 0 | 277091 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | -100 | 75100 | -100 | 75100 | 2121801.7 | 0 | 0 | 0 | 0 | 18146.5 | 2103755 | -99.8 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | E.5015417.02 | 5785512 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7065 | 0 | 7065 | 1.3381 | 0 | 0 | 1.3381 | 0 | 7492 | 7214 | 1.4189 | 1.3663 |  | 4228889 | 1038922 | 3189967 | 0 | 3189967 | 1978630.6 | 0 | 1211336.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 74989 | 11 | 74989 | 11 | 2053630.6 | 0 | 0 | 0 | 0 | 185160.1 | 1793481.4 | -10.9 | 0 | 0 | 0 | 0 | -11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 2021-06-18 | 145745 | BL-0: | BL-0: 35109540_CWSP - El Dorado 2101 - 19752 - Ph 1.2_08W - Feb. 2020 | 2020-07-23 | 2019-10-09 | Completed | 2019-09-09 | 2019-10-31 | Completed | 2019-08-29 | Completed | 2019-10-14 | Completed | 2019-10-08 | 2019-10-09 | Completed | 2019-10-01 | 2019-10-02 | Completed | 2019-10-16 | 2020-03-02 | Completed | 2019-10-16 | Completed |  |  |  |  | 2019-10-16 | Completed |  |  | 2020-02-18 | Completed | 2020-02-18 | 2020-02-18 | 0 | On/ Ahead Schedule | Completed | 2020-03-16 | 2020-04-29 | Completed | 2021-08-09 | Not Started
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 | E.5014759.04 | 5785581 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 12307 | 0 | 12307 | 2.3309 | 0 | 0 | 2.3309 | 0 | 12968 | 13119 | 2.4561 | 2.4847 |  | 6122412 | 1221200.5 | 4901211.5 |  |  | 4655544.9 | 0 | 245666.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8616 | -8616 | 8616 | -8616 | 4655544.9 | 0 | 0 | 0 | 0 | 1819984.5 | 2826944.7 | 8615.7 | 0 | 0 | 498 | 7324 | -1157 | 1951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145822 | BL-0: | BL-0: 35106331_CWSP - Volta 1102 - LR 1648 - Ph1.4_08W - May 2020 | 2020-07-24 | 2019-09-13 | Completed | 2020-02-13 | 2020-02-13 | Completed | 2019-09-04 | Completed | 2019-10-10 | Completed | 2019-10-02 | 2019-10-02 | Completed | 2019-10-22 | 2019-10-22 | Completed | 2019-11-15 | 2019-12-01 | Completed | 2019-11-22 | Completed |  |  |  |  | 2020-02-10 | Completed | 2020-05-28 | Completed | 2020-05-28 | Completed | 2020-05-28 | 2020-05-28 | 0 | On/ Ahead Schedule | Completed | 2020-06-23 | 2020-07-07 | Completed | 2021-08-09 | Not Started
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 | E.5015417.04 | 5785514 | DOCC | 08W | [6 empty] | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 9673 | 0 | 9673 | 1.832 | 0 | 0 | 1.832 | 0 | [5 empty] | 3529311 | 743625.1 | 2785685.9 |  |  | 2030480.2 | 64176.1 | 691029.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 86552 | -86552 | 86552 | -86552 | 2030430.2 | 0 | 50 | -50 | 0 | 2084656.3 | -140778.5 | 86602.4 | 0 | 0 | 505 | 606 | 505 | 505 | 84433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-23 | Completed | 2019-10-21 | 2019-10-24 | Completed | 2019-09-27 | Completed | 2019-09-16 | Completed | 2019-08-26 | 2019-08-26 | Completed | 2019-09-11 | 2019-09-11 | Completed | 2019-09-19 | 2020-03-13 | Completed | 2019-09-16 | Completed |  |  |  |  | 2019-09-20 | Completed |  |  | 2019-11-09 | Completed | 2020-05-18 | 2019-11-09 | 191 | On/ Ahead Schedule | Completed | 2019-11-11 | 2019-11-15 | Completed | 2021-08-09 | Not Started
35109543 | CWSP-EL DORADO 2101-19752- PHASE 1.5 | E.5015417.05 | 5785515 | DOCC | 08W | [6 empty] | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 8922 | 0 | 8922 | 1.6898 | 0 | 0 | 1.6898 | 0 | [5 empty] | 3608462 | 457433.2 | 3151028.8 | 0 | 3151028.8 | 2621518.6 | 0 | 529510.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6519 | -6519 | 6519 | -6519 | 2627978.6 | 0 | -6460 | 6460 | 0 | 3218762.5 | -597303 | 59.1 | 0 | 0 | 0 | 0 | 0 | 0 | 6519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-09-12 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-30 | Completed | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-30 | 2019-10-01 | Completed | 2019-10-16 | 2019-11-08 | Completed | 2019-10-03 | Completed |  |  |  |  | 2019-10-03 | Completed |  |  | 2020-03-06 | Completed | 2020-08-12 | 2020-03-06 | 159 | On/ Ahead Schedule | Completed | 2020-03-09 | 2020-03-27 | Completed | 2021-08-09 | Not Started
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | E.5015416.02 | 5785516 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 12821 | 0 | 12821 | 2.4282 | 0 | 0 | 2.4282 | -3.1006e-15 | 12857 | 12784 | 2.435 | 2.4212 |  | 4499650 | -0.7 | 4499650.7 | 0 | 4499650.7 | 3874123.1 | 0 | 625527.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 87532 | -12532 | 87532 | -12532 | 3874123.1 | 0 | 0 | 0 | 0 | 531278.5 | 3255312.7 | 87531.9 | 0 | 0 | 0 | 0 | 5031 | 0 | 82501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145747 | BL-0: | BL-0: 35109545_CWSP - El Dorado 2101 - 19752 - Ph 2.2_08W - April 2020 | 2020-07-23 | 2019-11-12 | Completed | 2019-11-11 | 2019-11-18 | Completed | 2019-09-23 | Completed | 2019-11-18 | Completed | 2019-11-18 | 2019-12-04 | Completed | 2019-11-27 | 2019-11-27 | Completed | 2019-11-19 | 2019-11-19 | Completed | 2019-12-02 | Completed |  |  |  |  | 2019-12-02 | Completed |  |  | 2020-04-17 | Completed | 2020-04-17 | 2020-04-17 | 0 | On/ Ahead Schedule | Completed | 2020-04-17 | 2020-04-30 | Completed | 2021-08-09 | Not Started
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 | E.5014544.02 | 5785418 | DOCC | 08W | [6 empty] | 2020 |  | SH | CONCORD | Diablo Assets | 0 | 5875 | 0 | 5875 | 1.1127 | 0 | 0 | 1.1127 | 0 | 6489 | 5368 | 1.229 | 1.0167 |  | 4408478 | 609832.1 | 3798645.9 |  |  | 3448674.2 | 0 | 349971.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 14624 | -14624 | 14624 | -14624 | 3448674.2 | 0 | 0 | 0 | 0 | 495114.1 | 2938936.4 | 14623.6 | 0 | 0 | 0 | 3449 | 4112 | 4340 | 2723 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 PH2 | E.5015491.02 | 5785301 | DOCC | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 9480 | 0 | 9480 | 1.7955 | 0 | 0 | 1.7955 | 0 | [5 empty] | 3550706 | -3550709.4 | 7101415.4 | 0 | 7101415.4 | 6981810 | 0 | 119605.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 6981810 | 0 | 0 | 0 | 0 | 6901150.6 | 80659.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | E.5015416.04 | 5785598 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 8058 | 0 | 8058 | 1.5261 | 0 | 0 | 1.5261 | 0 | 7660 | 8100 | 1.4508 | 1.5341 |  | 3530637 | 0.6 | 3530636.4 |  |  | 3060986.7 | 0 | 469649.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 18342 | 56658 | 18342 | 56658 | 3070486.7 | 0 | 0 | 0 | 0 | 275303 | 2776842 | 8841.8 | 0 | 0 | 16889 | 16094 | 16094 | 15979 | -56212 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 2021-06-18 | 145750 | BL-0: | BL-0: 35109547_CWSP - El Dorado 2101 - 19752 - Ph 2.4_08W - March 2020 | 2020-07-23 | 2019-10-16 | Completed | 2019-10-18 | 2019-10-18 | Completed | 2019-09-27 | Completed | 2019-10-22 | Completed | 2019-10-23 | 2019-10-24 | Completed | 2020-01-03 | 2020-01-03 | Completed | 2020-01-03 | 2020-01-03 | Completed | 2020-01-06 | Completed |  |  |  |  | 2020-01-06 | Completed |  |  | 2020-03-13 | Completed | 2020-03-13 | 2020-03-13 | 0 | On/ Ahead Schedule | Completed | 2020-03-13 | 2020-03-13 | Completed | 2021-08-09 | Not Started
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | E.5015416.05 | 5785599 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 15058 | 0 | 15058 | 2.8519 | 0 | 0 | 2.8519 | 0 | 15944 | 15069 | 3.0197 | 2.854 |  | 7082947 | 1602579 | 5480368 |  |  | 5383866.4 | 0 | 96501.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 450000 | 449532 | 468 | 449532 | 468 | 5488866.4 | 0 | 0 | 0 | 0 | 67826 | 4971508.6 | 344531.8 | 0 | 0 | 336336 | 6800 | -2597 | 3994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 2021-06-18 | 145751 | BL-0: | BL-0: 35109548_CWSP - El Dorado 2101 - 19752 - Ph 2.5_08W - May 2020 | 2020-07-23 | 2020-01-03 | Completed | 2020-01-14 | 2020-01-14 | Completed | 2019-08-17 | Completed | 2020-01-24 | Completed | 2020-01-20 | 2020-01-20 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2019-12-02 | 2019-12-13 | Completed | 2020-01-27 | Completed |  |  |  |  | 2020-01-27 | Completed |  |  | 2020-05-22 | Completed | 2020-05-22 | 2020-05-22 | 0 | On/ Ahead Schedule | Completed | 2020-05-22 | 2020-08-21 | Completed | 2021-08-09 | Not Started
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | E.5015415.02 | 5785600 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7062 | 0 | 7062 | 1.3375 | 0 | 0 | 1.3375 | 0 | 6933 | 7069 | 1.3131 | 1.3388 |  | 3123544 | -0.1 | 3123544.1 | 0 | 3123544.1 | 2719588.8 | 40670.7 | 363284.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75958 | -958 | 75958 | -958 | 2814088.8 | 0 | 0 | 0 | 0 | 2357709.6 | 380420.8 | -18541.6 | 0 | 0 | -102549 | 0 | 0 | 0 | 84008 | 0 | 0 | 0 | 0 | 0 | 0 | 94500 | 2021-06-18 | 145752 | BL-0: | BL-0: 35109549_CWSP - El Dorado 2101 - 19752 - Ph 3.2_08W - April 2020 | 2020-07-23 | 2019-09-18 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-09-30 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-02 | 2020-05-01 | Completed | 2019-10-04 | Completed |  |  |  |  | 2019-10-04 | Completed |  |  | 2020-04-17 | Completed | 2020-04-17 | 2020-04-17 | 0 | On/ Ahead Schedule | Completed | 2020-04-17 | 2020-04-30 | Completed | 2021-08-09 | Not Started
35109550 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | E.5015415.03 | 5785601 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 10111 | 0 | 10111 | 1.915 | 0 | 0 | 1.915 | 0 | 9563 | 10305 | 1.8112 | 1.9517 |  | 3044150 | 2 | 3044148 |  |  | 2846632.6 | 0 | 197515.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 73319 | 1681 | 73319 | 1681 | 2921632.6 | 0 | 0 | 0 | 0 | 3070771.7 | -222458.5 | -1680.6 | 0 | 0 | 0 | 0 | 0 | 0 | -1681 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145753 | BL-0: | BL-0: 35109550_CWSP - El Dorado 2101 - 19752 - Ph 3.3_08W - Jan. 2020 | 2020-07-23 | 2019-09-18 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-10-01 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-10-02 | 2019-10-03 | Completed | 2019-11-19 | 2019-12-13 | Completed | 2019-10-04 | Completed |  |  |  |  | 2019-10-04 | Completed |  |  | 2020-01-31 | Completed | 2020-01-31 | 2020-01-31 | 0 | On/ Ahead Schedule | Completed | 2020-02-03 | 2020-02-07 | Completed | 2021-08-09 | Not Started
35109551 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | E.5015415.04 | 5785602 | DOCC | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 7579 | 0 | 7579 | 1.4354 | 0 | 0 | 1.4354 | 0 | 7580 | 7684 | 1.4356 | 1.4553 |  | 3172299 | 1.2 | 3172297.8 |  |  | 2684862.2 | 0 | 487435.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 73470 | 1530 | 73470 | 1530 | 2759862.2 | 0 | 0 | 0 | 0 | 2714615.5 | -28223.5 | -1529.8 | 0 | 0 | 0 | 0 | 0 | 0 | -1530 | 0 | 75000 | 0 | 0 | 0 | 0 | 0
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | E.5015415.05 | 5785603 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 11175 | 0 | 11175 | 2.1165 | 0 | 0 | 2.1165 | 0 | 11274 | 11507 | 2.1352 | 2.1794 |  | 5804263 | 0.9 | 5804262.1 |  |  | 4548604.4 | 0 | 1255657.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 175000 | 175001 | -1 | 175001 | -1 | 4622930.4 | 0 | 0 | 0 | 0 | 4523869.9 | -75940 | 100674.5 | 0 | 0 | 100675 | 0 | 0 | 0 | 0 | 0 | 0 | 74326 | 0 | 0 | 0 | 0 | 2021-06-18 | 145755 | BL-0: | BL-0: 35109552_CWSP - El Dorado 2101 - 19752 - Ph 3.5_08W - Feb. 2020 | 2020-07-23 | 2019-09-25 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-08-29 | Completed | 2019-09-30 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-03 | 2019-10-04 | Completed | 2019-10-24 | 2019-10-24 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed |  |  | 2020-02-11 | Completed | 2020-02-11 | 2020-02-11 | 0 | On/ Ahead Schedule | Completed | 2020-02-17 | 2020-02-28 | Completed | 2021-08-09 | Not Started
35109553 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | E.5015415.06 | 5785604 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 14080 | 0 | 14080 | 2.6667 | 0 | 0 | 2.6667 | 0 | 14080 | 13725 | 2.6667 | 2.5994 |  | 4009924 | -0.5 | 4009924.5 | 0 | 4009924.5 | 3830827.7 | 0 | 179096.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 3905827.7 | 75000 | 0 | 75000 | 0 | 2545093.1 | 1285734.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145756 | BL-0: | BL-0: 35109553_CWSP - El Dorado 2101 - 19752 - Ph 3.6_08W - Jan 2020 | 2020-07-23 | 2019-09-26 | Completed | 2019-09-06 | 2019-09-06 | Completed | 2019-10-11 | Completed | 2020-02-03 | Completed | 2019-09-30 | 2019-09-30 | Completed | 2019-10-14 | 2019-10-14 | Completed | 2019-11-01 | 2020-01-13 | Completed | 2019-10-21 | Completed |  |  |  |  | 2019-10-21 | Completed |  |  | 2020-01-29 | Completed | 2020-01-29 | 2020-01-29 | 0 | On/ Ahead Schedule | Completed | 2020-01-20 | 2020-01-24 | Completed | 2021-08-09 | Not Started
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | E.5015414.02 | 5785605 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 6641 | 0 | 6641 | 1.2578 | 0 | 0 | 1.2578 | 0 | 6641 | 6661 | 1.2578 | 1.2616 |  | 2287663 | 11025 | 2276638 |  |  | 2142029.3 | 70541.3 | 64067.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 84757 | -9757 | 84757 | -9757 | 2142029.3 | 0 | 0 | 0 | 0 | 27262.3 | 2030009.8 | 84757.2 | 0 | 0 | 749 | 0 | 0 | 0 | 84008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145757 | BL-0: | BL-0: 35109554_CWSP - El Dorado 2101 - 19752 - Ph 4.2_08W - April 2020 | 2020-07-23 | 2020-01-17 | Completed | 2020-04-22 | 2020-04-23 | Completed | 2019-08-27 | Completed | 2020-02-20 | Completed | 2020-01-29 | 2020-01-29 | Completed | 2020-02-18 | 2020-02-18 | Completed | 2020-01-21 | 2020-04-17 | Completed | 2020-02-13 | Completed |  |  |  |  | 2020-02-13 | Completed |  |  | 2020-04-03 | Completed | 2020-04-03 | 2020-04-03 | 0 | On/ Ahead Schedule | Completed | 2020-04-03 | 2020-05-12 | Completed | 2021-08-09 | Not Started
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | E.5015414.03 | 5785606 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 11678 | 0 | 11678 | 2.2117 | 0 | 0 | 2.2117 | 0 | 11685 | 11318 | 2.2131 | 2.1436 |  | 4477708 | 5757.5 | 4471950.5 | 0 | 4471950.5 | 3634489.1 | 0 | 837461.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 3706462.1 | 0 | 0 | 0 | 0 | 2824429.5 | 807032.6 | 3027 | 0 | 0 | 3027 | 0 | 0 | 0 | 0 | 0 | 71973 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145758 | BL-0: | BL-0: 35109555_CWSP - El Dorado 2101 - 19752 - Ph 4.3_08W - Feb. 2020 | 2020-07-23 | 2019-11-08 | Completed | 2019-08-30 | 2019-09-05 | Completed | 2019-08-23 | Completed | 2019-12-19 | Completed | 2019-12-19 | 2019-12-19 | Completed | 2019-12-10 | 2019-12-10 | Completed | 2019-11-04 | 2020-02-28 | Completed | 2019-12-09 | Completed |  |  |  |  | 2019-12-09 | Completed |  |  | 2020-02-21 | Completed | 2020-02-21 | 2020-02-21 | 0 | On/ Ahead Schedule | Completed | 2020-02-21 | 2020-08-21 | Completed | 2021-08-09 | Not Started
35109556 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | E.5015414.04 | 5785607 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 1618 | 0 | 1618 | 0.30644 | 0 | 0 | 0.30644 | 0 | 1618 | 1618 | 0.30644 | 0.30644 |  | 1197284 | 80818.4 | 1116465.6 | 0 | 1116465.6 | 898206.2 | 0 | 218259.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 973206.2 | 0 | 0 | 0 | 0 | 689326.4 | 208879.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 0 | 0 | 0 | 0 | 2021-06-18 | 145759 | BL-0: | BL-0: 35109556_CWSP - El Dorado 2101 - 19752 - Ph 4.4_08W - March 2020 | 2020-07-23 | 2019-08-26 | Completed | 2019-10-16 | 2019-10-17 | Completed | 2019-09-03 | Completed | 2019-10-18 | Completed | 2019-10-17 | 2019-10-17 | Completed | 2019-10-18 | 2019-10-18 | Completed | 2019-10-16 | 2020-01-24 | Completed | 2019-10-21 | Completed |  |  |  |  | 2019-10-21 | Completed |  |  | 2020-03-06 | Completed | 2020-03-06 | 2020-03-06 | 0 | On/ Ahead Schedule | Completed | 2020-03-06 | 2021-06-18 | In Progress | 2021-08-09 | Not Started
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | E.5015687.08 | 5785651 | DOCC | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 14550 | 0 | 14550 | 2.7557 | 0 | 0 | 2.7557 | 0 | 14365 | 14550 | 2.7206 | 2.7557 |  | 5431839 | 2051191.3 | 3380647.7 |  |  | 2897587.7 | 0 | 483060 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 10744 | 64256 | 10744 | 64256 | 2897587.7 | 0 | 0 | 0 | 0 | 10725.9 | 2876117.5 | 10744.3 | 0 | 0 | 10997 | -252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | E.5015687.02 | 5785645 | DOCC | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 8117 | 0 | 8117 | 1.5373 | 0 | 0 | 1.5373 | 0 | 8118 | 8117 | 1.5375 | 1.5373 |  | 4166416 | 1153724.3 | 3012691.7 |  |  | 2515697.7 | 0 | 496994 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | -152 | 75152 | -152 | 75152 | 2515697.7 | 0 | 0 | 0 | 0 | 3439.9 | 2512410.1 | -152.3 | 0 | 0 | 47 | -199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | E.5015687.03 | 5785646 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 13228 | 0 | 13228 | 2.5053 | 0 | 0 | 2.5053 | 0 | 11193 | 13572 | 2.1199 | 2.5705 |  | 5345911 | 1865381.3 | 3480529.7 |  |  | 3207474.5 | 0 | 273055.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75944 | -944 | 75944 | -944 | 3281450.5 | 0 | 0 | 0 | 0 | 14247 | 3191259.9 | 1967.8 | 0 | 0 | 5735 | -4712 | 1891 | -1040 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 73976 | 2021-06-11 | 151661 | BL-2 | BL-2 35112432_CWSP - El Dorado 2102 - LR 19562 - Ph 1.2_08W - Nov. 2020 | 2020-11-24 | 2019-11-13 | Completed | 2020-03-06 | 2020-03-26 | Completed | 2020-03-02 | Completed | 2020-03-26 | Completed | 2020-03-06 | 2020-03-06 | Completed | 2020-04-03 | 2020-04-09 | Completed | 2020-04-13 | 2020-07-14 | Completed | 2020-05-08 | Completed |  |  |  |  | 2020-05-08 | Completed | 2020-11-18 | Completed | 2020-11-18 | Completed | 2020-11-18 | 2020-11-18 | 0 | On/ Ahead Schedule | Completed | 2020-11-20 | 2020-12-04 | Completed | 2021-08-02 | Not Started
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | E.5015687.04 | 5785647 | DOCC | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 10543 | 0 | 10543 | 1.9968 | 0 | 0 | 1.9968 | 0 | 10122 | 10205 | 1.917 | 1.9328 |  | 4151673 | 1283936.9 | 2867736.1 |  |  | 2700837.5 | 0 | 166898.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75000 | 0 | 75000 | 0 | 2775684.5 | 0 | 0 | 0 | 0 | 11601.3 | 2689083.6 | 152.6 | 0 | 0 | 0 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74847
35112089 | BR-01-05-W (E) MEYERS PARB |  | 5786123 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1477870.55 | 577870.55 | 900000 |  |  | 767660.9 | 0 | 132339.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 7744 | -7744 | 7744 | -7744 | 767660.9 | 0 | 0 | 0 | 0 | 248805.8 | 511111.1 | 7744 | 0 | 0 | 99 | 0 | 0 | 7645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112090 | BR-01-07-W (E) BILLE_REGIS PARB |  | 5786123 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1177537.75 | 927537.75 | 250000 |  |  | 154373.1 | 0 | 95626.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 154373.1 | 0 | 0 | 0 | 0 | 273378.9 | -119005.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112128 | BR-01-04-W (E) W. WAGSTAFF PARB |  | 5786123 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 991895.31 | -1499999.69 | 2491895 |  |  | 2005944.8 | 0 | 485950.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9525 | -9525 | 9525 | -9525 | 2004133.6 | 0 | 1811.2 | -1811.2 | 0 | 491215.8 | 1503392.7 | 11336.2 | 0 | 0 | 231 | 11122 | -1828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 | E.5015428.01 | 5782587 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11145 | 0 | 11145 | 2.1108 | 0 | 0 | 2.1108 | 0 | 11306 | 11145 | 2.1413 | 2.1108 |  | 5418545 | 333247 | 5085298 |  |  | 4719468.1 | 73361 | 292468.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3782 | -3782 | 3782 | -3782 | 4719468.1 | 0 | 0 | 0 | 13660.6 | 3995262 | 706763.3 | 3782.1 | 0 | 0 | 3102 | 1605 | -905 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145806 | BL-0: | BL-0: 35058905_CWSP - Volta 1102 - LR 1648 - Ph 4.1_08W - Jan 2020 | 2020-07-24 | 2019-08-30 | Completed | 2019-11-27 | 2019-11-27 | Completed | 2019-08-16 | Completed | 2019-10-14 | Completed | 2019-09-11 | 2019-09-11 | Completed | 2019-09-25 | 2019-09-25 | Completed | 2019-10-22 | 2019-10-22 | Completed | 2019-11-05 | Completed |  |  |  |  | 2019-11-19 | Completed |  |  | 2020-01-16 | Completed | 2020-01-16 | 2020-01-16 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-06-01 | Completed | 2021-08-09 | Not Started
35057017 | CWSP - EL DORADO 2101 - 19752 - PH 3.1 | E.5015415.01 | 5782534 | DOCC | 08W | [6 empty] | Not in the WP | 2019 | SH | PLCRVLLE | Sierra Assets | 0 | 9006 | 0 | 9006 | 1.7057 | 0 | 0 | 1.7057 | 0 | [5 empty] | 3201494 | -0.4 | 3201494.4 | 0 | 3201494.4 | 2706375.2 | 0 | 495119.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 588 | -588 | 588 | -588 | 2706957.6 | 0 | -582.4 | 582.4 | 3262.5 | 2815281.3 | -112173.9 | 5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-27 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-08-19 | Completed | 2019-09-18 | Completed | 2019-09-18 | 2019-09-18 | Completed | 2019-09-18 | 2019-09-18 | Completed | 2019-09-20 | 2020-03-20 | Completed | 2019-09-19 | Completed |  |  |  |  | 2019-09-19 | Completed |  |  | 2019-12-03 | Completed | 2020-05-18 | 2019-12-03 | 167 | On/ Ahead Schedule | Completed | 2020-03-20 | 2020-03-27 | Completed | 2021-08-09 | Not Started
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 | E.5014773.01 | 5785222 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | SONORA | Yosemite Assets | 0 | 10619 | 0 | 10619 | 2.0112 | 0 | 0 | 2.0112 | 0 | 10392 | 10392 | 1.9682 | 1.9682 |  | 3585097 | -331074.2 | 3916171.2 | 1457794 | 2458377.2 | 3285599.6 | 0 | 630571.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 272868 | 205177 | 67691 | 306834 | -33966 | 3551666.7 | 0 | 478.3 | -478.3 | 6248.5 | 14703.7 | 3223881 | 40766.4 | 0 | 0 | 0 | 40238 | 0 | 51 | 0 | 0 | 0 | 164889 | 0 | 0 | 0 | 0 | 2021-06-18 | 155987 | BL-1 | BL-1 35052820_CWSP - MIWUK 1702 - OCB - PH 1.1_08W - Feb. 2021 | 2021-02-16 | 2020-03-19 | Completed | 2020-03-16 | 2020-04-13 | Completed | 2019-12-13 | Completed | 2020-04-10 | Completed | 2020-04-15 | 2020-04-16 | Completed | 2020-04-20 | 2020-04-21 | Completed | 2020-02-20 | 2020-03-11 | Completed | 2020-04-24 | Completed |  |  |  |  | 2020-05-01 | Completed |  |  | 2020-06-11 | Completed | 2020-06-11 | 2020-06-11 | 0 | On/ Ahead Schedule | Completed | 2020-08-05 | 2020-08-08 | Completed | 2021-08-27 | Not Started
31157301 | X-RECNDUCTR-POINT M1101_2598 SMITH GRDE |  | 5513259 | DOCC | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 4063 | -4063 | 4063 | -4063 | [10 empty] | 0 | 0 | 0 | 4063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31121472 | +OCEANO 1104 WD 14-0067445 |  | 5513266 | DOCC | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30984775 | OCGC 93PL OH DET WIRE ON NAPA 1104 |  | 5513268 | DOCC | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35032266 | APPLE HILL 1104 RECONDUCTOR |  | 5530173 | DOCC | 08W | [6 empty] | Not in the WP |  | SH | AUBURN | Sierra Assets | 0 | 877 | 0 | 877 | 0.1661 | 0 | 0 | 0.1661 | 0 | [5 empty] | 368711 | -333701.4 | 702412.4 |  |  | 568537 | 0 | 133875.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 568537 | 0 | 0 | 0 | 24740.2 | 878948.8 | -335152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 | P.11381 | 5530159 | DOCC | 08W | [6 empty] | Not in the WP | 2022 | SH | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3066747 | 413254 | 2653493 |  |  | 2300168.7 | 0 | 353324.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10040 | -10040 | 10040 | -10040 | 2300094.2 | 0 | 74.5 | -74.5 | 9434.1 | 42266.6 | 2236195 | 10114.6 | 0 | 0 | 3785 | 1882 | 1371 | 2322 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 158220 | BL-0 | BL-0 31272374 CWSP PT. MORETTI FROM 5043 TO 5955 - Mar. 2021 | 2021-03-31 | 2019-02-15 | Completed |  |  | Completed | 2019-04-25 | Completed | 2021-02-06 | Completed | [6 empty] | 2020-03-07 | 2020-10-03 | Completed | 2020-08-31 | Completed |  |  |  |  | 2020-09-07 | Completed | 2020-08-31 | Completed | 2020-12-18 | Completed | 2020-12-18 | 2020-12-18 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-10-05 | Not Started
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | 5530161 | DOCC | 08W | [6 empty] | 2020 | 2020 | SH | CONCORD | Diablo Assets | 0 | 7959 | 0 | 7959 | 1.5074 | 0 | 0 | 1.5074 | 0 | 8023 | 8400 | 1.5195 | 1.5909 |  | 4611914 | 1613584.7 | 2998329.3 |  |  | 2688258.3 | 0 | 310071 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -62378 | 62378 | -62378 | 62378 | 2688258.3 | 0 | 0 | 0 | 12379 | 41700.6 | 2695147.8 | -62378.1 | 0 | 0 | 0 | -7204 | 0 | 0 | -55174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 147000 | BL-0 | BL-0 31343500_2019 ORINDA 401 HIGH SPLICE COUNT - MAY 2020 | 2020-08-11 | 2019-12-16 | Completed | 2020-03-02 | 2020-03-13 | Completed | 2020-02-10 | Completed | 2020-02-17 | Completed | 2020-02-10 | 2020-02-17 | Completed | 2020-02-25 | 2020-02-25 | Completed | 2020-02-14 | 2020-02-14 | Completed | 2020-02-24 | Completed |  |  |  |  | 2020-02-24 | Completed |  |  | 2020-05-13 | Completed | 2020-05-13 | 2020-05-13 | 0 | On/ Ahead Schedule | Completed | 2020-05-13 | 2020-05-14 | Completed | 2020-10-15 | Completed
31344015 | CNCL: 2019 CALISTOGA 1101 HIGH SPLICE CT |  | 5530168 | DOCC | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35023687 | R2RPL OH WIRE ON B LOMND 0401 17-0095503 | P.11844 | 5530159 | DOCC | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 0 | 7044 | 0 | 7044 | 1.3341 | 0 | 0 | 1.3341 | 0 | [5 empty] | 4004352 | 0 | 4004352 |  |  | 3907306.6 | 20000 | 77045.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 90687 | -90687 | 90687 | -90687 | 3997993.4 | 0 | 0 | 0 | 8068.7 | 3870173.7 | 29064.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90687 | 0 | 0 | 0 | 0 | 0
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | 5788785 | DOCC | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 635 | -635 | 635 | -635 | [10 empty] | 132 | 126 | 126 | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | 5790010 | DOCC | 08W | [6 empty] | 2021 | 2020 | SH | CHICO | North Valley Assets | 10150 | 0 | 0 | 10150 | 1.9223 | 0 | 0 | 1.9223 | 0 | 20644 | 10150 | 3.9098 | 1.9223 |  | 14251728 | 822083.8 | 13429644.2 |  |  | 12223344.2 | 0 | 1206300 | On/Under Budget | Request 2021 Budget | 0 | -9055 | 9055 | -9055 | 9055 | 12223447.4 | 0 | -103.2 | 103.2 | 0 | 11420292.3 | 812210.5 | -9158.6 | 0 | 0 | 558 | 148 | 294 | 101 | -10156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-10-24 | Completed | 2019-11-05 | 2019-11-26 | Completed | 2019-10-14 | Completed | 2019-10-11 | Completed | 2019-11-25 | 2019-11-25 | Completed | 2019-12-06 | 2019-12-06 | Completed |  |  |  | 2019-10-14 | Completed |  |  |  |  | 2019-12-02 | Completed | 2020-06-26 | Completed | 2020-06-26 | Completed | 2020-06-12 | 2020-06-26 | -14 | Behind Schedule | Completed | 2020-06-25 | 2020-06-26 | Completed | 2021-10-14 | Not Started
35117983 | BR-02-07-W (E) DOLORES DR, PARB |  | 5786123 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -4715572 | 4715573 |  |  | 4899352.6 | 0 | -183779.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 215073 | -215073 | 215073 | -215073 | 4911761.8 | 12409.2 | 0 | 12409.2 | 0 | 4235.7 | 4692453.4 | 202663.5 | 0 | 0 | 108076 | 17289 | 31452 | 32085 | 13762 | 12409 | 0 | 0 | 0 | 0 | 0 | 0
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 | E.5015235.04 | 5786024 | DOCC | 08W | [6 empty] | 2020 |  | SH | ANGLSCMP | Stockton Assets | 0 | 5727 | 0 | 5727 | 1.0847 | 0 | 0 | 1.0847 | 0 | 6672 | 0 | 1.2636 | 0 |  | 2958923 | 984908.3 | 1974014.7 |  |  | 1426191.5 | 66680.2 | 481143 | On/Under Budget | Project is not in the WP or in 2020 WP | -231006.4 | 41883 | -272889.4 | 41883 | -272889.4 | 1585808.7 | 0 | -159617.2 | 159617.2 | 0 | 398.5 | 1543526.9 | -117733.9 | 0 | 0 | 22857 | 2144 | 2184 | 3310 | 11389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154990 | BL-1 | BL-1 35115855_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.4_08W - Jan. 2021 | 2021-01-25 | 2020-01-15 | Completed | 2020-05-05 | 2020-05-06 | Completed | 2022-01-21 | Not Started | 2020-05-19 | Completed | 2020-07-03 | 2020-07-03 | Completed | 2020-07-06 | 2020-07-20 | Completed | 2020-06-05 | 2020-07-10 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2020-09-25 | Completed | 2020-10-26 | Completed | 2021-04-26 | 2020-10-01 | 207 | On/ Ahead Schedule | Completed | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-16 | Not Started
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | E.5014776.03 | 5785982 | DOCC | 08W | [6 empty] | 2021 | 2020 | SH | SONORA | Yosemite Assets | 0 | 12091 | 0 | 12091 | 2.29 | 0.5 | 0 | 2.29 | 0 | 12386 | 9451 | 2.3458 | 1.79 |  | 3849738 | 854907.6 | 2994830.4 |  |  | 1912860.3 | 92729.9 | 989240.2 | On/Under Budget | Budget Allocated | 201890 | 154630 | 47260 | 154630 | 47260 | 2006935.2 | 0 | -243 | 243 | 0 | 5552.2 | 1846752.8 | 60555.3 | 0 | 0 | 118993 | 18530 | -68155 | -10329 | 1759 | 0 | 93832 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 152683 | BL-1 | BL-1 35116442_CWSP - MIWUK 1702 - LR 38218 - PH 1.3_08W - Dec. 2020 | 2020-12-21 | 2020-02-27 | Completed | 2020-05-26 | 2020-06-05 | Completed | 2020-05-20 | Completed | 2020-06-05 | Completed | 2020-06-12 | 2020-06-12 | Completed | 2020-06-12 | 2020-07-06 | Completed | 2020-07-07 | 2020-07-31 | Completed | 2020-07-15 | Completed |  |  |  |  | 2020-07-15 | Completed | 2021-01-29 | Completed | 2020-12-15 | Completed | 2021-01-29 | 2021-01-18 | 11 | On/ Ahead Schedule | Completed | 2021-01-18 | 2021-02-09 | Completed | 2021-10-01 | Not Started
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | E.5015687.06 | 5785649 | DOCC | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 7006 | 0 | 7006 | 1.3269 | 0 | 0 | 1.3269 | 0 | 7873 | 7006 | 1.4911 | 1.3269 |  | 4061849 | 1187170.2 | 2874678.8 |  |  | 2389224.2 | 0 | 485454.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | -100 | 75100 | -100 | 75100 | 2389224.2 | 0 | 0 | 0 | 0 | 9454.8 | 2379869.2 | -99.8 | 0 | 0 | 0 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 | E.5014771.02 | 5785972 | DOCC | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 8554 | 0 | 8554 | 1.6201 | 1.6201 | 0 | 1.6201 | 0 | 8512 | 0 | 1.6121 | 0 |  | 4091239 | 1281646 | 2809593 |  |  | 1407904.5 | 385779.5 | 1015909 | On/Under Budget | Budget Allocated | 744758.2 | 661210 | 83548.2 | 661210 | 83548.2 | 1482212 | 0 | -74307.5 | 74307.5 | 0 | 3717.1 | 817284.8 | 586902.6 | 0 | 0 | 64715 | 11379 | 553277 | 229105 | -197266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 151440 | BL-0 | BL-0 35115050_CWSP - MIWUK 1701 - OCB - PH 1.2_08W - Nov 2020 | 2020-11-12 | 2020-02-13 | Completed | 2020-06-15 | 2020-06-23 | Completed | 2020-03-31 | Completed | 2020-07-02 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-07-27 | 2020-08-07 | Completed | 2020-07-23 | 2020-08-14 | Completed | 2020-08-10 | Completed |  |  |  |  | 2020-08-10 | Completed | 2021-04-23 | Completed | 2021-04-02 | Completed | 2021-04-30 | 2021-06-23 | -54 | Behind Schedule | Not Started | 2021-06-24 | 2021-07-07 | Not Started | 2021-11-17 | Not Started
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 | E.5014726.05 | 5786010 | DOCC | 08W | [6 empty] | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 10822 | 0 | 10822 | 2.0496 | 0 | 0 | 2.0496 | 0 | 10788 | 0 | 2.0432 | 0 |  | 2715235.15 | -412833.05 | 3128068.2 |  |  | 1098656 | 136704.1 | 1892708.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 69339 | -69339 | 69339 | -69339 | 1250235.4 | 0 | -91030.8 | 91030.8 | 0 | 2339.9 | 1178556.4 | -82240.4 | 0 | 0 | 7037 | 1013 | 992 | -252 | 0 | 0 | 0 | 60549 | 0 | 0 | 0 | 0
35225594 | CNCL ECOP FULTON 1107 - H02-LR604 PH 1.2 | E.5034792.01.01 | 5795144 | DOCC | 08W | [6 empty] | 2022 |  | SH | STROSA | Sonoma Assets | 2481.6 | 0 | 0 | 2481.6 | 0.47 | 0 | 0.47008 | 0 | 0.47 | [5 empty] | 1 | -249999 | 250000 |  |  | 24615.8 | 0 | 225384.2 | On/Under Budget | Budget Allocated | 200 | 24629 | -24429 | 24629 | -24429 | 25013.2 | 147.6 | 1033.5 | -885.9 | 0 | 0 | 0 | 24615.9 | 384 | 0 | 692 | 1621 | 614 | 20407 | 248 | 148 | 150 | 150 | 150 | 150 | 150 | 150 | 2021-06-04 | 155775 | BL- A | BL- A 35225594_ ECOP - FULTON 1107 - H02-LR604 Ph 1.2_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-08-20 | Not Started | 2021-08-23 | 2021-09-10 | Not Started | 2021-11-12 | Not Started | 2021-11-15 | Not Started | 2021-08-23 | 2021-08-23 | Not Started | 2021-08-24 | 2021-09-13 | Not Started | 2021-12-07 | 2022-01-17 | Not Started | 2022-01-18 | Not Started | 2022-01-18 | Not Started | 2022-04-04 | Not Started | 2022-01-18 | Not Started | 2022-04-04 | Not Started | 2022-04-05 | Not Started | 2022-05-03 | 2022-05-18 | -15 | Behind Schedule | Not Started | 2022-05-19 | 2022-06-01 | Not Started | 2022-07-15 | Not Started
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | E.5034825.01.76 | 5795419 | DOCC | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 10877 | 0 | 0 | 10877 | 2.06 | 2.06 | 0 | 2.06 | 0 | 9763 | 0 | 1.8491 | 0 |  | 10286697 | 3196882 | 7089815 | 764893 | 6324922 | 4834877.2 | 653983 | 1600954.8 | On/Under Budget | Budget Allocated | 6324922 | 5156512 | 1168410 | 6324926 | -4 | 6324926.2 | 445288.4 | 377369.6 | 67918.8 | 0 | 0 | 0 | 4834877.3 | 0 | 0 | 8992 | 1194571 | 2155286 | 1063544 | 35115 | 417291 | 216320 | 65392 | 0 | 1 | 0 | 0 | 2021-06-18 | 161071 | BL-0: | BL-0: 35223344_FRRB - Wyandotte 1103 ¿ Bald Rock Zone 2_08W - B1 | 2021-05-25 | 2021-01-26 | Completed | 2021-02-03 | 2021-02-05 | Completed | 2021-01-22 | Completed | 2021-02-12 | Completed | 2020-11-25 | 2020-11-25 | Completed | 2021-01-04 | 2021-01-04 | Completed | 2020-11-10 | 2020-12-16 | Completed | 2021-02-12 | Completed | 2021-02-12 | Completed | 2021-04-08 | Completed | 2021-03-29 | Completed | 2021-04-15 | Completed | 2021-04-15 | Completed | 2021-04-15 | 2021-04-15 | 0 | On/ Ahead Schedule | Completed | 2021-07-15 | 2021-08-04 | Not Started | 2021-08-30 | Not Started
35180088 | BUCOCAMPTUG 5507 ROCKFORD LN PARADISE |  | 5791246 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 19045 | -19045 | 19045 | -19045 | [10 empty] | 2158 | 17615 | -728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228449 | RIO DELL STORM REBUILD |  | 5795392 | DOCC | 08W | [6 empty] | 2021 |  | SH - Wind | FORTUNA | Humboldt Division Assets | 0 | 14816 | 0 | 14816 | 2.8061 | 2.8061 | 0 | 2.8061 | 0 | [5 empty] | 6518166 | 0 | 6518166 |  |  | 4059357.8 | 212547.7 | 2246260.5 | On/Under Budget | Budget Allocated | 3628388 | 3618714 | 9674 | 3618714 | 9674 | 3618714.5 | 76102 | 1493002.1 | -1416900.1 | 0 | 0 | 0 | 4059357.8 | 0 | 0 | 7814 | 871179 | 1302352 | 327526 | 57485 | 76102 | 15855 | 876392 | 21003 | 21003 | 21003 | 21003 | 2021-06-18 |  |  |  |  | 2021-02-01 | Completed | 2021-02-15 | 2021-02-19 | Completed | 2021-02-05 | Completed | 2021-02-19 | Completed | 2021-02-01 | 2021-03-02 | Completed | 2021-02-01 | 2021-02-05 | Completed | 2021-02-01 | 2021-02-05 | Completed | 2021-02-08 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-02-08 | Completed | 2021-03-01 | Completed | 2021-03-01 | Completed | 2021-05-05 | 2021-03-01 | 65 | On/ Ahead Schedule | Completed | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-23 | Not Started
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | 5783283 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 3204 | -3204 | 3204 | -3204 | [10 empty] | 247 | 235 | 235 | 233 | 2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 |  | 5783324 | DOCC | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | -246 | 246 | -246 | 246 | [10 empty] | -246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74021964 | X-1104 OH RECOND SKYLINE |  | 5513339 | DOCC | 08W | [6 empty] | Not in the WP |  |  | OAKPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE | E.5015036.01 | 5782835 | DOCC | 08W | [6 empty] | Not in the WP | 2019 | SH | GRSSVLLY | Sierra Assets | 0 | 25191 | 0 | 25191 | 4.771 | 0 | 0 | 4.771 | 0 | [5 empty] | 12463097 | 0 | 12463097 |  |  | 12396667.1 | 0 | 66429.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -33568 | 33568 | -33568 | 33568 | 12396667.1 | 0 | 0 | 0 | 371758.4 | 11704542.1 | 353934.4 | -33567.8 | 0 | 0 | 962 | 3329 | 0 | 0 | -37859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2019-06-12 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-04-29 | Completed | 2019-06-12 | Completed | 2019-06-14 | 2019-06-14 | Completed | 2019-04-29 | 2019-04-29 | Completed | 2019-05-06 | 2019-05-06 | Completed | 2019-05-06 | Completed |  |  |  |  | 2019-05-06 | Completed | 2019-07-19 | Completed | 2019-07-19 | Completed | 2019-07-19 | 2019-07-19 | 0 | On/ Ahead Schedule | Completed | 2019-07-01 | 2019-07-05 | Completed | 2021-09-08 | Not Started
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 | E.5015470.01 | 5782834 | DOCC | 08W | [6 empty] | Not in the WP | 2019 | SH | GRSSVLLY | Sierra Assets | 0 | 31023 | 0 | 31023 | 5.8756 | 0 | 0 | 5.8756 | 0 | [5 empty] | 15621955 | 0 | 15621955 |  |  | 15475726.8 | 19212.8 | 127015.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1943 | -1943 | 1943 | -1943 | 15475726.8 | 0 | 0 | 0 | 625617.3 | 15246154.8 | -397988 | 1942.7 | 0 | 0 | 147 | 1795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2019-06-11 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-03-15 | Completed | 2019-03-15 | Completed | 2019-03-01 | 2019-03-04 | Completed | 2019-03-05 | 2019-03-06 | Completed | 2019-01-25 | 2019-01-25 | Completed | 2019-01-25 | Completed |  |  |  |  | 2019-01-21 | Completed | 2019-06-10 | Completed | 2019-06-21 | Completed | 2019-07-24 | 2019-06-21 | 33 | On/ Ahead Schedule | Completed | 2019-06-28 | 2021-06-11 | In Progress | 2021-07-12 | Not Started
35243959 | BR-BP-02-W BIKE PATH PH II PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -699999 | 700000 |  |  | 936.8 | 0 | 699063.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4626 | -4626 | 4626 | -4626 | 4625.6 | 2542 | -986.1 | 3528.1 | 0 | 0 | 0 | 936.8 | 0 | 0 | 0 | 0 | 0 | 0 | 1923 | 2542 | 27 | 27 | 27 | 27 | 27 | 27
35246590 | BR-08-01-W (E) ALEXANDER PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 1173.6 | 0 | -1173.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 96 | -96 | 96 | -96 | 96.2 | 0 | 1077.4 | -1077.4 | 0 | 0 | 0 | 1173.6 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237894 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | E.5034825.01.63 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4540 | 0 | 0 | 4540 | 0.85985 | 0.85985 | 0 | 0 | 0.85985 | [5 empty] | 5974020 | 2195730 | 3778290 |  |  | 10339 | 0 | 3767951 | On/Under Budget | Budget Allocated | 3778290 | 3024631 | 753659 | 3024631 | 753659 | 3024631.2 | 3434.4 | 76.6 | 3357.8 | 0 | 0 | 0 | 10339 | 0 | 0 | 0 | 0 | 0 | 22940 | -12678 | 3434 | 1000934 | 1000000 | 1000000 | 10000 | 0 | 0 | 2021-05-21 | 159038 | BL-A_ | BL-A_35237894_FRRB - Wyandotte 1103 - W3 Ph 3.6 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35250343 | FRRB - KANAKA 1101CB - K2 SM1 | E.5034933.01.14 | 5796539 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1465 | 0 | 0 | 1465 | 0.27746 | 0.27746 | 0 | 0 | 0.27746 | [5 empty] | 75000 | 0 | 75000 |  |  | 76.6 | 0 | 74923.4 | On/Under Budget | Budget Allocated | 971117 | 1055663 | -84546 | 5000 | 966117 | 5000 | 5000 | 76.6 | 4923.4 | 0 | 0 | 0 | 76.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 525331 | 525332 | 0 | 0 | 2021-04-05 |  |  |  |  | 2021-04-29 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-24 | Not Started | [6 empty] | 2021-04-28 | 2021-05-04 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | 2021-09-13 | Not Started | 2021-06-28 | Not Started | 2021-09-27 | Not Started | 2021-09-27 | Not Started | 2021-10-27 | 2021-10-27 | 0 | On/ Ahead Schedule | Not Started | 2021-10-27 | 2021-11-10 | Not Started | 2021-12-24 | Not Started
35228083 | BR-14-05-W (E) HILLPARK LN DR PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | E.5034610.01.14 | 5794205 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2112 | 0 | 2112 | 0.4 | 0 | 0.4 | 0 | 0.4 | [5 empty] | 80000 | 0 | 80000 |  |  | 1270.7 | 0 | 78729.3 | On/Under Budget | Request 2021 Budget | 0 | 946 | -946 | 946 | -946 | 945.9 | 0 | 324.8 | -324.8 | 0 | 0 | 0 | 1270.7 | 0 | 0 | 0 | 0 | 898 | 43 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157823 | BL-A | BL-A 35227868_CWSP - Middletown 1103 - LR 830 PH1.9_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-06 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-09-10 | Not Started | 2021-10-01 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-10-26 | Not Started | 2021-10-26 | Not Started | 2021-11-08 | Not Started | 2021-10-26 | Not Started | 2022-02-07 | Not Started | 2022-03-08 | Not Started | 2022-02-24 | 2022-03-31 | -35 | Behind Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35227870 | CWSP - VACAVILLE 11046542 - PH 2.2 | E.5034707.01.07 | 5794545 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 316.8 | 7180.8 | 0 | 7497.6 | 1.42 | 0 | 1.4201 | 0 | 1.42 | [5 empty] | 1 | -228318 | 228319 |  |  | 15141 | 0 | 213178 | On/Under Budget | Request 2021 Budget | 0 | 186856 | -186856 | 186856 | -186856 | 2786340.9 | 5809.5 | -3005.6 | 8815.1 | 0 | 0 | 0 | 15141 | 2599485.3 | 0 | 0 | 0 | 0 | 1592 | 16555 | 5810 | 35749 | 39114 | 37965 | 16691 | 16691 | 16691 | 2021-06-18 |  |  |  |  | 2021-09-14 | Not Started | 2021-10-20 | 2021-10-26 | Not Started | 2021-10-19 | Not Started | 2021-11-16 | Not Started | 2021-09-15 | 2021-09-15 | Not Started | 2021-09-16 | 2021-10-06 | Not Started | 2021-10-20 | 2021-11-02 | Not Started | 2021-12-09 | Not Started | 2021-12-09 | Not Started | 2021-12-22 | Not Started | 2021-12-09 | Not Started | 2022-03-23 | Not Started | 2022-04-21 | Not Started | 2022-06-22 | 2022-06-22 | 0 | On/ Ahead Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-08-19 | Not Started
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | E.5034696.01.03 | 5794547 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 3093 | 0 | 0 | 3093 | 0.5858 | 0 | 0.5858 | 0 | 0.5858 | 3093 | 0 | 0.5858 | 0 |  | 409121.04 | -65878.96 | 475000 | 0 | 475000 | 57173.7 | 4000 | 413826.3 | On/Under Budget | Budget Allocated | 475000 | 450549 | 24451 | 450549 | 24451 | 450548.5 | 10512.1 | -17065.9 | 27578 | 0 | 0 | 0 | 57173.7 | 0 | 0 | 0 | 2465 | 19939 | 24261 | 27575 | 10512 | 509 | 509 | 363509 | 509 | 509 | 254 | 2021-06-18 | 159381 | BL-A: | BL-A: 35229119_CWSP - MIDDLETOWN 1101118494 Ph2_08W - B1_Apr 21 | 2021-04-21 | 2021-05-14 | Completed | 2021-09-16 | 2021-09-22 | Not Started | 2021-09-15 | Not Started | 2021-10-12 | Not Started | 2021-06-18 | 2021-09-20 | In Progress | 2021-09-21 | 2021-10-11 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-10-15 | Not Started | 2021-10-15 | Not Started | 2021-10-28 | Not Started | 2021-10-15 | Not Started | 2021-11-19 | Not Started | 2021-12-20 | Not Started | 2022-02-18 | 2022-02-18 | 0 | On/ Ahead Schedule | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-19 | Not Started
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | E.5034692.01.02 | 5794540 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | CONCORD | Diablo Assets | 6864 | 0 | 0 | 6864 | 1.3 | 0 | 1.3 | 0 | 1.3 | [5 empty] | 350000 | 0 | 350000 |  |  | 7745.2 | 0 | 342254.8 | On/Under Budget | Budget Allocated | 5000 | 7806 | -2806 | 7806 | -2806 | 5441005.6 | 28.9 | 144.1 | -115.2 | 0 | 0 | 0 | 7745.2 | 5433199.6 | 0 | 0 | 463 | 3035 | 3535 | 569 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 2021-06-18 | 160973 | BL-B: | BL-B: 35231543_CWSP - TIDEWATER 210614072 Ph2_08W - May 21 | 2021-05-20 | 2021-09-30 | Not Started | 2022-03-04 | 2022-03-10 | Not Started | 2022-03-03 | Not Started | 2022-03-31 | Not Started | 2021-10-01 | 2021-10-01 | Not Started | 2021-10-04 | 2021-10-22 | Not Started | 2022-03-04 | 2022-03-17 | Not Started | 2022-04-25 | Not Started | 2022-04-25 | Not Started | 2022-07-15 | Not Started | 2022-04-25 | Not Started | 2022-07-15 | Not Started | 2022-08-15 | Not Started | 2022-11-02 | 2022-10-14 | 19 | On/ Ahead Schedule | Not Started | 2022-10-17 | 2022-10-28 | Not Started | 2022-12-13 | Not Started
35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | E.5034710.01.02 | 5794551 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | AUBURN | Sierra Assets | 9028 | 0 | 0 | 9028 | 1.7098 | 0 | 1.7098 | 0 | 1.7098 | [5 empty] | 316667 | 0 | 316667 |  |  | 28808.4 | 0 | 287858.6 | On/Under Budget | Budget Allocated | 162264.96 | 181958 | -19693.04 | 197251 | -34986.04 | 5132186.5 | 25423.1 | -43153.7 | 68576.8 | 0 | 0 | 0 | 28808.4 | 4934936 | 0 | 0 | 0 | 0 | 36483 | 35479 | 24049 | 38235 | 28430 | 3520 | 3536 | 3551 | 8676 | 2021-06-18 | 158188 | BL-A_ | BL-A_35232650_CWSP - MOUNTAIN QUARRIES 21016953 Ph 1.2_08W_Apr.2021 | 2021-03-31 | 2022-01-14 | Not Started | 2022-02-21 | 2022-02-25 | Not Started | 2022-02-18 | Not Started | 2022-03-18 | Not Started | 2022-01-17 | 2022-01-17 | Not Started | 2022-01-18 | 2022-02-07 | Not Started | 2022-02-21 | 2022-03-04 | Not Started | 2022-04-12 | Not Started | 2022-04-12 | Not Started | 2022-04-25 | Not Started | 2022-04-12 | Not Started | 2022-07-25 | Not Started | 2022-08-23 | Not Started | 2022-04-12 | 2022-10-24 | -195 | Behind Schedule | Not Started | 2022-10-25 | 2022-11-07 | Not Started | 2022-12-21 | Not Started
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | E.5034713.01.03 | 5794554 | ESTS | 08W | [6 empty] | 2021 |  | SH | REDDING | North Valley Assets | 0 | 16251 | 0 | 16251 | 3.0778 | 3.0778 | 0 | 0 | 3.0778 | 15379 | 0 | 2.9127 | 0 |  | 190000 | 0 | 190000 |  |  | 9304.3 | 0 | 180695.7 | On/Under Budget | Budget Allocated | 5959798 | 6136656 | -176858 | 6136656 | -176858 | 6136656.2 | 86657.2 | 1372.5 | 85284.7 | 0 | 0 | 0 | 9304.4 | 0 | 0 | 0 | 0 | 2080 | 3397 | 2455 | 86657 | 2006929 | 1990043 | 2004396 | 39948 | 752 | 0
35231627 | CWSP - HIGHLANDS 1102628 PH 1.9 | E.5034697.01.09 | 5794549 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 2105 | 0 | 2105 | 0.39867 | 0 | 0.39867 | 0 | 0.39867 | [5 empty] | 73077 | 0 | 73077 |  |  | 468.1 | 0 | 72608.9 | On/Under Budget | Request 2021 Budget | 0 | 2898 | -2898 | 2898 | -2898 | 2898.4 | 2430.3 | 0 | 2430.3 | 0 | 0 | 0 | 468.1 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | E.5034608.01.02 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 10507 | 0 | 10507 | 1.99 | 0 | 1.99 | 0 | 1.99 | [5 empty] | 1 | 1 | 0 |  |  | 26388.2 | 0 | -26388.2 | OverRun | Request 2021 Budget | 0 | 61714 | -61714 | 61714 | -61714 | 62390.3 | 20295.6 | -12885.8 | 33181.4 | 0 | 0 | 0 | 26388.3 | 676.2 | 0 | 0 | 0 | 687 | 27233 | 11354 | 20296 | 357 | 357 | 357 | 357 | 357 | 357 | 2021-06-18 | 157793 | BL-A | BL-A 35226819_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-06 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-12-03 | Not Started | 2021-12-06 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-12-06 | 2021-12-17 | Not Started | 2021-12-29 | Not Started | 2021-12-29 | Not Started | 2022-01-11 | Not Started | 2021-12-29 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-07-08 | 2022-07-12 | -4 | Behind Schedule | Not Started | 2022-07-13 | 2022-07-26 | Not Started | 2022-09-08 | Not Started
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | E.5034804.01.04 | 5795299 | ESTS | 08W | [6 empty] | 2022 |  | SH | PLCRVLLE | Sierra Assets | 9398 | 0 | 0 | 9398 | 1.7799 | 0 | 1.7799 | 0 | 1.7799 | [5 empty] | 1 | -249999 | 250000 |  |  | 101597.9 | 0 | 148402.1 | On/Under Budget | Budget Allocated | 200 | 101888 | -101688 | 101888 | -101688 | 101991.7 | 41 | 0 | 41 | 0 | 0 | 0 | 101597.8 | 102.9 | 0 | 0 | 2225 | 1941 | 31417 | 66016 | 41 | 42 | 42 | 42 | 42 | 42 | 42 | 2021-06-18 | 156277 | BL-A | BL-A 35226849_CWSP - SHINGLE SPRINGS 2109-LR 9372PH2.3_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-06 | Not Started | 2021-10-20 | Not Started | 2021-10-21 | Not Started | 2021-08-02 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-10-21 | 2021-11-03 | Not Started | 2021-12-13 | Not Started | 2021-12-13 | Not Started | 2021-12-24 | Not Started | 2021-12-13 | Not Started | 2022-03-25 | Not Started | 2022-04-04 | Not Started | 2022-06-24 | 2022-06-02 | 22 | On/ Ahead Schedule | Not Started | 2022-06-03 | 2022-06-16 | Not Started | 2022-08-01 | Not Started
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | E.5034805.01.01 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 4488 | 0 | 0 | 4488 | 0.85 | 0 | 0.85 | 0 | 0.85 | [5 empty] | 155000 | 0 | 155000 |  |  | 27130.1 | 0 | 127869.9 | On/Under Budget | Budget Allocated | 500000 | 35531 | 464469 | 35531 | 464469 | 37184.5 | 2281.5 | -4884.2 | 7165.7 | 0 | 0 | 0 | 27130 | 1461.2 | 192.6 | 0 | 1042 | 922 | 22502 | 7548 | 2282 | 206 | 206 | 206 | 206 | 206 | 206 | 2021-06-18 | 159757 | BL-A: | BL-A: 35226857_ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-10-24 | 2022-10-28 | Not Started | 2022-10-21 | Not Started | 2022-11-18 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2023-01-09 | Not Started | 2023-01-09 | Not Started | 2023-01-20 | Not Started | 2023-01-09 | Not Started | 2023-02-27 | Not Started | 2023-03-28 | Not Started | 2023-04-05 | 2023-05-29 | -54 | Behind Schedule | Not Started | 2023-05-30 | 2023-06-12 | Not Started | 2023-07-26 | Not Started
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | E.5034805.01.15 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3809 | 0 | 0 | 3809 | 0.7214 | 0 | 0.7214 | 0 | 0.7214 | [5 empty] | 67857 | 0 | 67857 |  |  | 3925.5 | 0 | 63931.5 | On/Under Budget | Budget Allocated | 300000 | 6482 | 293518 | 6482 | 293518 | 6955.7 | 2460.4 | 129.6 | 2330.8 | 0 | 0 | 0 | 3925.5 | 454 | 19.9 | 0 | 0 | 2035 | 1389 | 372 | 2460 | 38 | 38 | 38 | 38 | 38 | 38 | 2021-06-18 | 159770 | BL-A: | BL-A: 35227001_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | E.5034805.01.16 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 2286 | 0 | 0 | 2286 | 0.43295 | 0 | 0.43295 | 0 | 0.43295 | [5 empty] | 67857 | 0 | 67857 |  |  | 4270.1 | 0 | 63586.9 | On/Under Budget | Budget Allocated | 200000 | 5208 | 194792 | 5208 | 194792 | 5709.5 | 829.5 | 129.6 | 699.9 | 0 | 0 | 0 | 4270.2 | 480.4 | 21.1 | 0 | 0 | 1688 | 1729 | 724 | 830 | 40 | 40 | 40 | 40 | 40 | 40 | 2021-06-18 | 159744 | BL-A: | BL-A: 35227002_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | E.5034805.01.17 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3067 | 0 | 0 | 3067 | 0.58087 | 0 | 0.58087 | 0 | 0.58087 | [5 empty] | 67857 | 0 | 67857 |  |  | 4537.1 | 0 | 63319.9 | On/Under Budget | Budget Allocated | 300000 | 7119 | 292881 | 7119 | 292881 | 7641.9 | 2464 | 129.6 | 2334.4 | 0 | 0 | 0 | 4537.1 | 500.8 | 22 | 0 | 0 | 2066 | 1616 | 726 | 2464 | 41 | 41 | 41 | 41 | 41 | 41 | 2021-06-18 | 159750 | BL-A: | BL-A: 35227003_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | E.5034805.01.18 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 1839 | 0 | 0 | 1839 | 0.3483 | 0 | 0.3483 | 0 | 0.3483 | [5 empty] | 67857 | 0 | 67857 |  |  | 4992.7 | 0 | 62864.3 | On/Under Budget | Budget Allocated | 300000 | 7594 | 292406 | 7594 | 292406 | 8153.1 | 2466.8 | 129.6 | 2337.2 | 0 | 0 | 0 | 4992.7 | 535.6 | 23.5 | 0 | 0 | 1719 | 2416 | 728 | 2467 | 44 | 44 | 44 | 44 | 44 | 44 | 2021-06-18 | 159755 | BL-A: | BL-A: 35227004_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | E.5034805.01.11 | 5795300 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 420 | 0 | 420 | 0.079545 | 0.079545 | 0 | 0 | 0.079545 | 1022 | 0 | 0.19356 | 0 |  | 59835.3 | -8021.7 | 67857 |  |  | 20169.2 | 0 | 47687.8 | On/Under Budget | Request 2021 Budget | 0 | 16841 | -16841 | 16841 | -16841 | 17647.6 | 3558.5 | 7472.8 | -3914.3 | 0 | 0 | 0 | 20169.2 | 773.2 | 34 | 0 | 0 | 1834 | 927 | 9935 | 3559 | 98 | 98 | 98 | 98 | 98 | 98 | 2021-06-18 | 159745 | BL-A: | BL-A: 35226871_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7_08W - Apr 21 | 2021-04-28 | 2021-06-25 | Not Started | 2021-07-26 | 2021-07-30 | Not Started | 2021-07-23 | Not Started | 2021-08-20 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-06-29 | 2021-07-06 | Not Started | 2021-09-24 | Not Started | 2021-09-24 | Not Started | 2021-10-07 | Not Started | 2021-09-24 | Not Started | 2021-11-12 | Not Started | 2021-12-13 | Not Started | 2023-03-21 | 2022-02-11 | 403 | On/ Ahead Schedule | Not Started | 2022-02-14 | 2022-02-25 | Not Started | 2022-04-12 | Not Started
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | E.5034805.01.13 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 5488 | 0 | 0 | 5488 | 1.0394 | 0 | 1.0394 | 0 | 1.0394 | [5 empty] | 67857 | 0 | 67857 |  |  | 4649.9 | 0 | 63207.1 | On/Under Budget | Budget Allocated | 300000 | 7958 | 292042 | 7958 | 292042 | 8538.9 | 3161.2 | 129.6 | 3031.6 | 0 | 0 | 0 | 4649.8 | 556.2 | 24.4 | 0 | 0 | 2630 | 1164 | 726 | 3161 | 46 | 46 | 46 | 46 | 46 | 46 | 2021-06-18 | 159754 | BL-A: | BL-A: 35226873_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | E.5034805.01.14 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3109 | 0 | 0 | 3109 | 0.58883 | 0 | 0.58883 | 0 | 0.58883 | [5 empty] | 67857 | 0 | 67857 |  |  | 4895.6 | 0 | 62961.4 | On/Under Budget | Budget Allocated | 500000 | 7493 | 492507 | 7493 | 492507 | 8044.1 | 2466.2 | 129.6 | 2336.6 | 0 | 0 | 0 | 4895.7 | 528.1 | 23.2 | 0 | 0 | 1345 | 2694 | 728 | 2466 | 43 | 43 | 43 | 43 | 43 | 43 | 2021-06-18 | 159775 | BL-A: | BL-A: 35226878_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | E.5034608.01.03 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 6970 | 0 | 0 | 6970 | 1.3201 | 0 | 1.3201 | 0 | 1.3201 | [5 empty] | 1 | 1 | 0 |  |  | 26965.9 | 0 | -26965.9 | OverRun | Request 2021 Budget | 0 | 40508 | -40508 | 40508 | -40508 | 40962 | 93.1 | -12885.8 | 12978.9 | 0 | 0 | 0 | 26965.8 | 453.6 | 0 | 0 | 0 | 768 | 27493 | 11590 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 2021-06-18 | 157794 | BL-A | BL-A 35227160_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-06 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-12-03 | Not Started | 2021-12-06 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-12-06 | 2021-12-17 | Not Started | 2021-12-29 | Not Started | 2021-12-29 | Not Started | 2022-01-11 | Not Started | 2021-12-29 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-07-29 | 2022-07-12 | 17 | On/ Ahead Schedule | Not Started | 2022-07-13 | 2022-07-26 | Not Started | 2022-09-08 | Not Started
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | E.5034608.01.04 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3907 | 0 | 3907 | 0.73996 | 0 | 0.73996 | 0 | 0.73996 | [5 empty] | 1 | 1 | 0 |  |  | 15574 | 0 | -15574 | OverRun | Request 2021 Budget | 0 | 30515 | -30515 | 30515 | -30515 | 31155.4 | 20116 | 6235.8 | 13880.2 | 0 | 0 | 0 | 15574.1 | 640.8 | 0 | 0 | 0 | 687 | 79 | 8572 | 20116 | 177 | 177 | 177 | 177 | 177 | 177 | 2021-06-18 | 157795 | BL-A | BL-A 35227161_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-11-18 | Not Started | 2021-11-19 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-11-19 | 2021-12-02 | Not Started | 2021-12-14 | Not Started | 2021-12-14 | Not Started | 2021-12-27 | Not Started | 2021-12-14 | Not Started | 2022-03-28 | Not Started | 2022-04-26 | Not Started | 2022-07-08 | 2022-06-27 | 11 | On/ Ahead Schedule | Not Started | 2022-06-28 | 2022-07-11 | Not Started | 2022-08-24 | Not Started
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | E.5034608.01.05 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 1690 | 0 | 0 | 1690 | 0.32008 | 0 | 0.32008 | 0 | 0.32008 | [5 empty] | 1 | 1 | 0 |  |  | 1275.4 | 0 | -1275.4 | OverRun | Request 2021 Budget | 0 | 1935 | -1935 | 1935 | -1935 | 2375.9 | 93.1 | 0 | 93.1 | 0 | 0 | 0 | 1275.3 | 440.5 | 0 | 0 | 0 | 768 | 426 | 81 | 93 | 95 | 95 | 95 | 95 | 95 | 95 | 2021-06-18 | 157796 | BL-A | BL-A 35227162_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-27 | Not Started | 2021-08-30 | 2021-09-03 | Not Started | 2021-12-03 | Not Started | 2021-12-06 | Not Started | 2021-08-30 | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-20 | Not Started | 2021-12-06 | 2021-12-17 | Not Started | 2021-12-29 | Not Started | 2021-12-29 | Not Started | 2022-01-11 | Not Started | 2021-12-29 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-07-08 | 2022-07-12 | -4 | Behind Schedule | Not Started | 2022-07-13 | 2022-07-26 | Not Started | 2022-09-08 | Not Started
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | E.5034608.01.06 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2429 | 0 | 2429 | 0.46004 | 0 | 0.46004 | 0 | 0.46004 | [5 empty] | 1 | 1 | 0 |  |  | 5757.7 | 0 | -5757.7 | OverRun | Request 2021 Budget | 0 | 26783 | -26783 | 26783 | -26783 | 27506.1 | 20094.6 | 0 | 20094.6 | 0 | 0 | 0 | 5757.7 | 723.1 | 0 | 0 | 0 | 687 | 79 | 4992 | 20095 | 155 | 155 | 155 | 155 | 155 | 155 | 2021-06-18 | 157797 | BL-A | BL-A 35227163_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-20 | Not Started | 2021-08-23 | 2021-08-27 | Not Started | 2021-12-03 | Not Started | 2021-12-06 | Not Started | 2021-08-23 | 2021-08-23 | Not Started | 2021-08-24 | 2021-09-13 | Not Started | 2021-12-06 | 2021-12-17 | Not Started | 2021-12-29 | Not Started | 2021-12-29 | Not Started | 2022-01-11 | Not Started | 2021-12-29 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-07-08 | 2022-07-12 | -4 | Behind Schedule | Not Started | 2022-07-13 | 2022-07-26 | Not Started | 2022-09-08 | Not Started
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | E.5034608.01.07 | 5794207 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4752 | 0 | 4752 | 0.9 | 0 | 0.9 | 0 | 0.9 | [5 empty] | 1 | 1 | 0 |  |  | 15087.4 | 0 | -15087.4 | OverRun | Request 2021 Budget | 0 | 31532 | -31532 | 31532 | -31532 | 32200.8 | 20121.9 | 4773.3 | 15348.6 | 0 | 0 | 0 | 15087.4 | 669.1 | 0 | 0 | 0 | 687 | 79 | 9548 | 20122 | 183 | 183 | 183 | 183 | 183 | 183 | 2021-06-18 | 157798 | BL-A | BL-A 35227164_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-11-05 | Not Started | 2021-11-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-11-08 | 2021-11-19 | Not Started | 2021-12-01 | Not Started | 2021-12-01 | Not Started | 2021-12-14 | Not Started | 2021-12-01 | Not Started | 2022-03-15 | Not Started | 2022-04-13 | Not Started | 2022-07-08 | 2022-06-14 | 24 | On/ Ahead Schedule | Not Started | 2022-06-15 | 2022-06-28 | Not Started | 2022-08-11 | Not Started
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | E.5034610.01.04 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 5333 | 0 | 0 | 5333 | 1.01 | 0 | 1.01 | 0 | 1.01 | [5 empty] | 1 | 1 | 0 |  |  | 3401.6 | 0 | -3401.6 | OverRun | Request 2021 Budget | 0 | 10945 | -10945 | 10945 | -10945 | 11410.7 | 95.4 | -6870.4 | 6965.8 | 0 | 0 | 0 | 3401.5 | 465.7 | 0 | 0 | 0 | 1381 | 12047 | -3156 | 95 | 96 | 96 | 96 | 96 | 96 | 96 | 2021-06-18 | 157803 | BL-A | BL-A 35227165_CWSP - MIDDLETOWN 1103 - LR 830 PH3.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-09-17 | Not Started | 2021-09-20 | 2021-09-24 | Not Started | 2022-01-14 | Not Started | 2022-01-17 | Not Started | 2021-09-20 | 2021-09-20 | Not Started | 2021-09-21 | 2021-10-11 | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-02-09 | Not Started | 2022-02-09 | Not Started | 2022-02-22 | Not Started | 2022-02-09 | Not Started | 2022-05-24 | Not Started | 2022-06-22 | Not Started | 2022-07-29 | 2022-08-23 | -25 | Behind Schedule | Not Started | 2022-08-24 | 2022-09-06 | Not Started | 2022-10-20 | Not Started
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | E.5034610.01.05 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 9504 | 0 | 0 | 9504 | 1.8 | 0 | 1.8 | 0 | 1.8 | [5 empty] | 1 | 1 | 0 |  |  | 2579.3 | 0 | -2579.3 | OverRun | Request 2021 Budget | 0 | 10109 | -10109 | 10109 | -10109 | 10560.2 | 93.4 | -6870.4 | 6963.8 | 0 | 0 | 0 | 2579.4 | 451.4 | 0 | 0 | 0 | 861 | 11749 | -3160 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 2021-06-18 | 157804 | BL-A | BL-A 35227167_CWSP - Middletown 1103 - LR 830 PH3.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-09-17 | Not Started | 2021-09-20 | 2021-09-24 | Not Started | 2022-01-14 | Not Started | 2022-01-17 | Not Started | 2021-09-20 | 2021-09-20 | Not Started | 2021-09-21 | 2021-10-11 | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-02-09 | Not Started | 2022-02-09 | Not Started | 2022-02-22 | Not Started | 2022-02-09 | Not Started | 2022-05-24 | Not Started | 2022-06-22 | Not Started | 2022-07-29 | 2022-08-23 | -25 | Behind Schedule | Not Started | 2022-08-24 | 2022-09-06 | Not Started | 2022-10-20 | Not Started
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | E.5034610.01.06 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 8290 | 0 | 0 | 8290 | 1.5701 | 0 | 1.5701 | 0 | 1.5701 | [5 empty] | 1 | 1 | 0 |  |  | 2416.1 | 0 | -2416.1 | OverRun | Request 2021 Budget | 0 | 9816 | -9816 | 9816 | -9816 | 10262.5 | 93.4 | -6740.8 | 6834.2 | 0 | 0 | 0 | 2416.1 | 446.5 | 0 | 0 | 0 | 861 | 11458 | -3162 | 93 | 94 | 94 | 94 | 94 | 94 | 94 | 2021-06-18 | 157805 | BL-A | BL-A 35227168_CWSP - Middletown 1103 - LR 830 PH3.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-09-17 | Not Started | 2021-09-20 | 2021-09-24 | Not Started | 2022-01-14 | Not Started | 2022-01-17 | Not Started | 2021-09-20 | 2021-09-20 | Not Started | 2021-09-21 | 2021-10-11 | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-02-09 | Not Started | 2022-02-09 | Not Started | 2022-02-22 | Not Started | 2022-02-09 | Not Started | 2022-05-24 | Not Started | 2022-06-22 | Not Started | 2022-07-29 | 2022-08-23 | -25 | Behind Schedule | Not Started | 2022-08-24 | 2022-09-06 | Not Started | 2022-10-20 | Not Started
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | E.5034805.01.26 | 5795300 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4171 | 0 | 4171 | 0.78996 | 0.78996 | 0 | 0 | 0.78996 | [5 empty] | 92500 | 0 | 92500 |  |  | 18209 | 0 | 74291 | On/Under Budget | Request 2021 Budget | 0 | 72704 | -72704 | 72704 | -72704 | 72804.2 | 20358.9 | -31609.2 | 51968.1 | 0 | 0 | 0 | 18209 | 100.7 | 0 | 0 | 0 | 849 | 24402 | 24568 | 20359 | 421 | 421 | 421 | 421 | 421 | 421 | 2021-06-18 | 157832 | BL-A | BL-A 35227027_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-12 | Not Started | 2021-07-13 | 2021-07-19 | Not Started | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-08-03 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-09-29 | Not Started | 2022-01-11 | Not Started | 2022-02-09 | Not Started | 2022-02-24 | 2022-04-12 | -47 | Behind Schedule | Not Started | 2022-04-13 | 2022-04-26 | Not Started | 2022-06-09 | Not Started
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | E.5034805.01.29 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 7287 | 0 | 0 | 7287 | 1.3801 | 0 | 1.3801 | 0 | 1.3801 | [5 empty] | 200000 | 0 | 200000 |  |  | 14566.9 | 0 | 185433.1 | On/Under Budget | Request 2021 Budget | 0 | 21927 | -21927 | 21927 | -21927 | 21979.9 | 102.3 | -6637.5 | 6739.8 | 0 | 0 | 0 | 14567.1 | 53.5 | 0 | 0 | 0 | 1821 | 11464 | 7920 | 102 | 103 | 103 | 103 | 103 | 103 | 103 | 2021-06-18 | 157835 | BL-A | BL-A 35227030_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-06 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-09-10 | Not Started | 2021-10-01 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-10-26 | Not Started | 2021-10-26 | Not Started | 2021-11-08 | Not Started | 2021-10-26 | Not Started | 2022-02-07 | Not Started | 2022-03-08 | Not Started | 2022-02-24 | 2022-03-31 | -35 | Behind Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35227651 | CWSP - VACAVILLE 11046542 PH 1.2 | E.5034707.01.03 | 5794545 | ESTS | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 18216 | 0 | 18216 | 3.45 | 3.45 | 0 | 0 | 3.45 | [5 empty] | 1 | -228463 | 228464 |  |  | 61472.8 | 0 | 166991.2 | On/Under Budget | Request 2021 Budget | 0 | 4075519 | -4075519 | 4075519 | -4075519 | 4075518.8 | 67995.4 | 23518.6 | 44476.8 | 0 | 0 | 0 | 61472.8 | 0 | 0 | 0 | 0 | 0 | 1736 | 36219 | 67995 | 70658 | 285481 | 1645127 | 630656 | 625551 | 712097 | 2021-06-18 | 158642 | BL-A | BL-A 35227651_CWSP - VACAVILLE 11046542 PH 1.2_08W - DD 210402 | 2021-04-05 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-04 | Not Started | 2021-09-10 | Not Started | 2021-09-13 | Not Started | 2021-07-29 | 2021-07-29 | Not Started | 2021-07-30 | 2021-08-19 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-09-27 | Not Started | 2021-09-27 | Not Started | 2021-10-08 | Not Started | 2021-09-27 | Not Started | 2021-12-09 | Not Started | 2021-12-10 | Not Started | 2021-12-30 | 2022-02-16 | -48 | Behind Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35227652 | CWSP - VACAVILLE 11046542 PH 1.3 | E.5034707.01.04 | 5794545 | ESTS | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 2904 | 0 | 0 | 2904 | 0.55 | 0 | 0.55 | 0 | 0.55 | [5 empty] | 1 | -182991 | 182992 |  |  | 7414.3 | 0 | 175577.7 | On/Under Budget | Request 2021 Budget | 0 | 3246279 | -3246279 | 3246279 | -3246279 | 3246278.8 | 39014.4 | -1665 | 40679.4 | 0 | 0 | 0 | 7414.3 | 0 | 0 | 0 | 0 | 0 | 1311 | 7768 | 39014 | 50697 | 218255 | 1225462 | 588844 | 591320 | 523607 | 2021-06-18 | 158643 | BL-A | BL-A 35227652_CWSP - VACAVILLE 11046542 PH 1.3_08W - DD 210402 | 2021-04-05 | 2021-07-19 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-09-17 | Not Started | 2021-09-20 | Not Started | 2021-07-20 | 2021-07-20 | Not Started | 2021-07-21 | 2021-08-10 | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-10-13 | Not Started | 2021-10-13 | Not Started | 2021-10-26 | Not Started | 2021-10-13 | Not Started | 2021-11-09 | Not Started | 2021-12-08 | Not Started | 2021-12-27 | 2022-02-08 | -43 | Behind Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-04-07 | Not Started
35227653 | CWSP - VACAVILLE 11046542 PH 1.4 | E.5034707.01.05 | 5794545 | ESTS | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 14414.4 | 0 | 14414.4 | 2.73 | 2.7299 | 0 | 0 | 2.73 | [5 empty] | 1 | -181652 | 181653 |  |  | 159541.8 | 0 | 22111.2 | On/Under Budget | Request 2021 Budget | 0 | 3245792 | -3245792 | 3245792 | -3245792 | 3255355.4 | 39016.2 | 35589.5 | 3426.7 | 0 | 0 | 0 | 159541.8 | 9564 | 0 | 0 | 0 | 0 | 1618 | 122335 | 39016 | 23229 | 192289 | 1199804 | 577202 | 580589 | 509710 | 2021-06-18 | 158644 | BL-A | BL-A 35227653_CWSP - VACAVILLE 11046542 PH 1.4_08W - DD 210402 | 2021-04-05 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-04 | Not Started | 2021-09-10 | Not Started | 2021-09-22 | Not Started | 2021-07-29 | 2021-07-29 | Not Started | 2021-07-30 | 2021-08-19 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-10-15 | Not Started | 2021-10-15 | Not Started | 2021-10-28 | Not Started | 2021-10-15 | Not Started | 2021-12-23 | Not Started | 2022-01-21 | Not Started | 2022-02-07 | 2022-03-24 | -45 | Behind Schedule | Not Started | 2022-03-25 | 2022-04-07 | Not Started | 2022-05-23 | Not Started
35227654 | CWSP - VACAVILLE 11046542 PH 1.5 | E.5034707.01.06 | 5794545 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 2798.4 | 0 | 2798.4 | 0.53 | 0 | 0.52992 | 0 | 0.53 | [5 empty] | 1 | -41389 | 41390 |  |  | 2824.4 | 0 | 38565.6 | On/Under Budget | Request 2021 Budget | 0 | 337762 | -337762 | 337762 | -337762 | 739880.2 | 27287.2 | -2245.4 | 29532.6 | 0 | 0 | 0 | 2824.5 | 402118.4 | 0 | 0 | 0 | 0 | 853 | 4217 | 27287 | 234073 | 47337 | 12463 | 4976 | 3274 | 3282 | 2021-06-18 | 158645 | BL-A | BL-A 35227654_CWSP - VACAVILLE 11046542 PH 1.5_08W - DD 210402 | 2021-04-05 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-04 | Not Started | 2022-03-25 | Not Started | 2022-03-28 | Not Started | 2021-07-29 | 2021-07-29 | Not Started | 2021-07-30 | 2021-08-19 | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2022-04-20 | Not Started | 2022-04-20 | Not Started | 2022-05-03 | Not Started | 2022-04-20 | Not Started | 2022-08-02 | Not Started | 2022-08-31 | Not Started | 2022-11-18 | 2022-11-01 | 17 | On/ Ahead Schedule | Not Started | 2022-11-02 | 2022-11-15 | Not Started | 2022-12-29 | Not Started
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | E.5034610.01.11 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3274 | 0 | 0 | 3274 | 0.62008 | 0 | 0.62008 | 0 | 0.62008 | [5 empty] | 200000 | 0 | 200000 |  |  | 9089.3 | 0 | 190910.7 | On/Under Budget | Request 2021 Budget | 0 | 12268 | -12268 | 12268 | -12268 | 12634.8 | 96.1 | -2500 | 2596.1 | 0 | 0 | 0 | 9089.3 | 367 | 0 | 0 | 0 | 1592 | 15448 | -5450 | 96 | 97 | 97 | 97 | 97 | 97 | 97 | 2021-06-18 | 157806 | BL-A | BL-A 35227864_CWSP - Middletown 1103 - LR 830 PH1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-12-10 | Not Started | 2021-12-13 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-12-13 | 2021-12-24 | Not Started | 2022-01-05 | Not Started | 2022-01-05 | Not Started | 2022-01-18 | Not Started | 2022-01-05 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-08 | 2022-07-19 | -11 | Behind Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-15 | Not Started
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | E.5034610.01.12 | 5794205 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2746 | 0 | 2746 | 0.52008 | 0.52008 | 0 | 0 | 0.52008 | [5 empty] | 75000 | 0 | 75000 |  |  | 42039.8 | 0 | 32960.2 | On/Under Budget | Request 2021 Budget | 0 | 51109 | -51109 | 51109 | -51109 | 51575.3 | 20234.6 | 12941.2 | 7293.4 | 0 | 0 | 0 | 42039.8 | 466.1 | 0 | 0 | 0 | 725 | 42 | 28333 | 20235 | 296 | 296 | 296 | 296 | 296 | 296 | 2021-06-18 | 157820 | BL-A | BL-A 35227866_CWSP - Middletown 1103 - LR 830 PH1.7_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-11 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-12 | 2021-08-25 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-03-10 | -14 | Behind Schedule | Not Started | 2022-03-11 | 2022-03-24 | Not Started | 2022-05-09 | Not Started
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | E.5034610.01.07 | 5794205 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1056 | 0 | 1056 | 0.2 | 0.2 | 0 | 0 | 0.2 | 1035 | 0 | 0.19602 | 0 |  | 64653.56 | -10346.44 | 75000 |  |  | 20351.4 | 0 | 54648.6 | On/Under Budget | Request 2021 Budget | 0 | 41070 | -41070 | 41070 | -41070 | 41193.4 | 20176.8 | 885.2 | 19291.6 | 0 | 0 | 0 | 20351.3 | 123.2 | 0 | 0 | 0 | 725 | 228 | 18514 | 20177 | 238 | 238 | 238 | 238 | 238 | 238 | 2021-06-18 | 157817 | BL-A | BL-A 35227860_CWSP - Middletown 1103 - LR 830 PH1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-10 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-16 | Not Started | 2021-07-19 | Not Started | 2021-07-13 | 2021-07-19 | Not Started | 2021-07-20 | 2021-08-09 | Not Started | 2021-07-19 | 2021-07-30 | Not Started | 2021-08-11 | Not Started | 2021-08-11 | Not Started | 2021-08-24 | Not Started | 2021-08-11 | Not Started | 2021-11-23 | Not Started | 2021-12-22 | Not Started | 2022-02-24 | 2022-02-22 | 2 | On/ Ahead Schedule | Not Started | 2022-02-23 | 2022-03-08 | Not Started | 2022-04-21 | Not Started
35227656 | CWSP - VACAVILLE 11046542 - PH 2.3 | E.5034707.01.08 | 5794545 | ESTS | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 3960 | 0 | 0 | 3960 | 0.75 | 0 | 0.75 | 0 | 0.75 | [5 empty] | 1 | -114166 | 114167 |  |  | 18990.1 | 0 | 95176.9 | On/Under Budget | Request 2021 Budget | 0 | 109926 | -109926 | 109926 | -109926 | 1400219.9 | 2097 | 2223.7 | -126.7 | 0 | 0 | 0 | 18990.1 | 1290293.8 | 0 | 0 | 0 | 0 | 1415 | 15352 | 2097 | 26253 | 27815 | 14031 | 9235 | 6864 | 6864 | 2021-06-18 |  |  |  |  | 2021-09-14 | Not Started | 2021-10-20 | 2021-10-26 | Not Started | 2021-10-19 | Not Started | 2021-11-16 | Not Started | 2021-09-15 | 2021-09-15 | Not Started | 2021-09-16 | 2021-10-06 | Not Started | 2021-10-20 | 2021-11-02 | Not Started | 2021-12-09 | Not Started | 2021-12-09 | Not Started | 2021-12-22 | Not Started | 2021-12-09 | Not Started | 2022-03-23 | Not Started | 2022-04-21 | Not Started | 2022-06-22 | 2022-06-22 | 0 | On/ Ahead Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-08-19 | Not Started
35227658 | CWSP - VACAVILLE 11046542 - PH 2.5 | E.5034707.01.10 | 5794545 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 1478.4 | 0 | 1478.4 | 0.28 | 0 | 0.27992 | 0 | 0.28 | [5 empty] | 1 | -59289 | 59290 |  |  | 2271.9 | 0 | 57018.1 | On/Under Budget | Request 2021 Budget | 0 | 56683 | -56683 | 56683 | -56683 | 720690.4 | 932 | 123.4 | 808.6 | 0 | 0 | 0 | 2272 | 664007.5 | 0 | 0 | 0 | 0 | 780 | 1368 | 932 | 15183 | 18629 | 4323 | 5156 | 5156 | 5156 | 2021-06-18 |  |  |  |  | 2021-09-28 | Not Started | 2021-11-03 | 2021-11-09 | Not Started | 2021-11-02 | Not Started | 2021-11-30 | Not Started | 2021-09-29 | 2021-09-29 | Not Started | 2021-09-30 | 2021-10-20 | Not Started | 2021-11-03 | 2021-11-16 | Not Started | 2021-12-23 | Not Started | 2021-12-23 | Not Started | 2022-01-05 | Not Started | 2021-12-23 | Not Started | 2022-04-06 | Not Started | 2022-05-05 | Not Started | 2022-07-06 | 2022-07-06 | 0 | On/ Ahead Schedule | Not Started | 2022-07-07 | 2022-07-20 | Not Started | 2022-09-02 | Not Started
35239098 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | E.5034825.01.69 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 7282 | 0 | 0 | 7282 | 1.3792 | 1.3792 | 0 | 0 | 1.3792 | [5 empty] | 8340020 | 2741730 | 5598290 | 768290 | 4830000 | 17017.1 | 0 | 5581272.9 | On/Under Budget | Budget Allocated | 5598290 | 4827024 | 771266 | 4827024 | 771266 | 4827024.2 | 106.4 | 495.6 | -389.2 | 0 | 0 | 0 | 17017.1 | 0 | 0 | 0 | 0 | 0 | 5199 | 11322 | 106 | 107 | 1500107 | 1500107 | 1000107 | 809967 | 0 | 2021-05-21 | 159067 | BL-A_ | BL-A_35239098_FRRB - WYANDOTTE 1103 - W4 PH 4.6 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-25 | 2021-12-21 | -26 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35237896 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | E.5034825.01.65 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5872 | 0 | 0 | 5872 | 1.1121 | 1.1121 | 0 | 0 | 1.1121 | [5 empty] | 7111520 | 2458230 | 4653290 |  |  | 6781.8 | 0 | 4646508.2 | On/Under Budget | Budget Allocated | 4653290 | 3896151 | 757139 | 3896151 | 757139 | 3896150.6 | 3434.4 | 0 | 3434.4 | 0 | 0 | 0 | 6781.8 | 0 | 0 | 0 | 0 | 0 | 15660 | -8878 | 3434 | 934 | 1000000 | 1000000 | 1000000 | 885000 | 0 | 2021-05-21 | 159036 | BL-A_ | BL-A_35237896_FRRB - Wyandotte 1103 - W3 Ph 3.8 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | E.5034825.01.51 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4100 | 0 | 0 | 4100 | 0.77652 | 0.77652 | 0 | 0 | 0.77652 | [5 empty] | 5610020 | 2111730 | 3498290 |  |  | 9280.6 | 0 | 3489009.4 | On/Under Budget | Budget Allocated | 3498290 | 2743573 | 754717 | 2743573 | 754717 | 2743572.8 | 3434.4 | 76.6 | 3357.8 | 0 | 0 | 0 | 9280.6 | 0 | 0 | 0 | 0 | 382 | 20537 | -11715 | 3434 | 934 | 1000000 | 1000000 | 730000 | 0 | 0 | 2021-05-21 | 159023 | BL-A_ | BL-A_35236990_FRRB - WYANDOTTE 1103 - W3 PH 3.9 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35236983 | FRRB - BIG BEND 1102 - B5 PH5.3 | E.5034825.01.45 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | CHICO | North Valley Assets | 2300 | 0 | 0 | 2300 | 0.43561 | 0.43561 | 0 | 0 | 0.43561 | [5 empty] | 4431245 | 1980095 | 2451150 | 911150 | 1540000 | 5672.2 | 0 | 2445477.8 | On/Under Budget | Budget Allocated | 2451150 | 1542168 | 908982 | 1542168 | 908982 | 1542168.1 | 0 | 3504.1 | -3504.1 | 0 | 0 | 0 | 5672.2 | 0 | 0 | 0 | 0 | 0 | 273 | 1896 | 0 | 40000 | 500000 | 500000 | 500000 | 0 | 0 | 2021-05-21 | 160645 | BL-A: | BL-A: 35236983 FRRB - BIG BEND 1102 - B5 PH 5.3 - May 21 | 2021-05-12 | 2021-06-23 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-12-14 | 2021-12-21 | -7 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35236662 | CWSP - OLETA 1101754718 PH 1.2 | E.5034721.01.02 | 5794611 | ESTS | 08W | [6 empty] | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 9472 | 0 | 9472 | 1.7939 | 1.7939 | 0 | 0 | 1.7939 | [5 empty] | 1 | -474999 | 475000 |  |  | 46136.5 | 0 | 428863.5 | On/Under Budget | Request 2021 Budget | 0 | 3157700 | -3157700 | 3157700 | -3157700 | 3157700.3 | 69040.8 | 12097.2 | 56943.6 | 0 | 0 | 0 | 46136.5 | 0 | 0 | 0 | 0 | 0 | 5020 | 29020 | 69041 | 54810 | 1125739 | 723813 | 494834 | 655424 | 0 | 2021-06-18 | 159257 | BL-A | BL-A 35236662_CWSP - OLETA 1101754718 PH 1.2_08W - DD 210402 | 2021-04-15 | 2021-06-30 | Not Started | 2021-07-01 | 2021-07-07 | Not Started | 2021-07-30 | Not Started | 2021-08-25 | Not Started | 2021-07-01 | 2021-07-01 | Not Started | 2021-07-02 | 2021-07-22 | Not Started | 2021-08-02 | 2021-09-10 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-11-11 | Not Started | 2021-11-12 | Not Started | 2021-12-02 | 2022-01-12 | -41 | Behind Schedule | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-03-11 | Not Started
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 | E.5034704.01.03 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 11352 | 0 | 11352 | 2.15 | 0 | 2.15 | 0 | 2.15 | [5 empty] | 1 | 1 | 0 |  |  | 792 | 0 | -792 | OverRun | Request 2021 Budget | 0 | 238 | -238 | 238 | -238 | 238.3 | 0 | 553.7 | -553.7 | 0 | 0 | 0 | 792.1 | 0 | 0 | 0 | 0 | 236 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 | E.5034704.01.04 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 21359 | 772 | 22131 | 4.1915 | 0 | 4.0453 | 0 | 4.1915 | [5 empty] | 1 | 1 | 0 |  |  | 1010.3 | 0 | -1010.3 | OverRun | Request 2021 Budget | 0 | 715 | -715 | 715 | -715 | 714.9 | 0 | 295.4 | -295.4 | 0 | 0 | 0 | 1010.3 | 0 | 0 | 0 | 0 | 707 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 | E.5034704.01.05 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 15893 | 0 | 15893 | 3.01 | 0 | 3.01 | 0 | 3.01 | [5 empty] | 1 | 1 | 0 |  |  | 1240 | 0 | -1240 | OverRun | Request 2021 Budget | 0 | 715 | -715 | 715 | -715 | 714.9 | 0 | 525.1 | -525.1 | 0 | 0 | 0 | 1240 | 0 | 0 | 0 | 0 | 707 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 | E.5034704.01.06 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 15154 | 0 | 15154 | 2.8701 | 0 | 2.8701 | 0 | 2.8701 | [5 empty] | 1 | 1 | 0 |  |  | 1286.9 | 0 | -1286.9 | OverRun | Request 2021 Budget | 0 | 953 | -953 | 953 | -953 | 953.2 | 0 | 333.7 | -333.7 | 0 | 0 | 0 | 1286.8 | 0 | 0 | 0 | 0 | 942 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237364 | CWSP - VACA DIXON 110540092 PH 1.6 | E.5034704.01.07 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 15998 | 0 | 15998 | 3.0299 | 0 | 3.0299 | 0 | 3.0299 | [5 empty] | 1 | 1 | 0 |  |  | 410.2 | 0 | -410.2 | OverRun | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410.2 | -410.2 | 0 | 0 | 0 | 410.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237365 | CWSP - VACA DIXON 110540092 PH 1.7 | E.5034704.01.08 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 13569 | 0 | 13569 | 2.5699 | 0 | 0 | 0 | 2.5699 | [5 empty] | 1 | 1 | 0 |  |  | 73.1 | 0 | -73.1 | OverRun | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.1 | -73.1 | 0 | 0 | 0 | 73.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237366 | CWSP - VACA DIXON 110540092 PH 1.8 | E.5034704.01.09 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 11774 | 0 | 11774 | 2.2299 | 0 | 0 | 0 | 2.2299 | [5 empty] | 1 | 1 | 0 |  |  | 73.1 | 0 | -73.1 | OverRun | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.1 | -73.1 | 0 | 0 | 0 | 73.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 | E.5034704.01.10 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 22123 | 0 | 22123 | 4.19 | 0 | 0 | 0 | 4.19 | [5 empty] | 1 | 1 | 0 |  |  | 588 | 0 | -588 | OverRun | Request 2021 Budget | 0 | 477 | -477 | 477 | -477 | 476.6 | 0 | 111.4 | -111.4 | 0 | 0 | 0 | 588 | 0 | 0 | 0 | 0 | 471 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 | E.5034704.01.11 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 16579 | 0 | 16579 | 3.14 | 0 | 0 | 0 | 3.14 | [5 empty] | 1 | 1 | 0 |  |  | 349.7 | 0 | -349.7 | OverRun | Request 2021 Budget | 0 | 238 | -238 | 238 | -238 | 238.3 | 0 | 111.4 | -111.4 | 0 | 0 | 0 | 349.8 | 0 | 0 | 0 | 0 | 236 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 | E.5034704.01.12 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 19958 | 0 | 19958 | 3.7799 | 0 | 0 | 0 | 3.7799 | [5 empty] | 1 | 1 | 0 |  |  | 549.7 | 0 | -549.7 | OverRun | Request 2021 Budget | 0 | 477 | -477 | 477 | -477 | 476.6 | 0 | 73.1 | -73.1 | 0 | 0 | 0 | 549.7 | 0 | 0 | 0 | 0 | 471 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 | E.5034704.01.13 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 1795 | 0 | 1795 | 0.33996 | 0 | 0 | 0 | 0.33996 | [5 empty] | 1 | 1 | 0 |  |  | 1226.3 | 0 | -1226.3 | OverRun | Request 2021 Budget | 0 | 1192 | -1192 | 1192 | -1192 | 1191.5 | 0 | 34.8 | -34.8 | 0 | 0 | 0 | 1226.3 | 0 | 0 | 0 | 0 | 1178 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | E.5034825.01.59 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 7220 | 0 | 0 | 7220 | 1.3674 | 1.3674 | 0 | 0 | 1.3674 | [5 empty] | 8294520 | 2731230 | 5563290 |  |  | 18266.2 | 0 | 5545023.8 | On/Under Budget | Budget Allocated | 5563290 | 4817558 | 745732 | 4817558 | 745732 | 4817558.4 | 3434.4 | 76.6 | 3357.8 | 0 | 0 | 0 | 18266.2 | 0 | 0 | 0 | 0 | 1020 | 31567 | -14397 | 3434 | 1000934 | 1000000 | 1000000 | 1000000 | 795000 | 0 | 2021-05-21 | 159033 | BL-A_ | BL-A_35237889_FRRB - Wyandotte 1103 - W3 Ph 3.2 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35236437 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | E.5034805.01.35 | 5795300 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1796 | 0 | 1796 | 0.34015 | 0.34015 | 0 | 0 | 0.34015 | [5 empty] | 90000 | 0 | 90000 |  |  | 268 | 0 | 89732 | On/Under Budget | Request 2021 Budget | 0 | 910 | -910 | 910 | -910 | 1053.1 | 91.1 | 0 | 91.1 | 0 | 0 | 0 | 267.9 | 142.8 | 0 | 0 | 0 | 0 | 266 | 2 | 91 | 92 | 92 | 92 | 92 | 92 | 92 | 2021-06-18 | 159241 | BL-A | BL-A 35236437_ECOP - MIDDLETOWN 1101-H16-LR48212 PH1.7_08W - DD 210402 | 2021-04-15 | 2021-07-27 | Not Started | 2021-07-28 | 2021-08-03 | Not Started | 2021-08-31 | Not Started | 2021-09-21 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-09-01 | 2021-09-14 | Not Started | 2021-10-14 | Not Started | 2021-10-14 | Not Started | 2021-10-27 | Not Started | 2021-10-14 | Not Started | 2022-01-12 | Not Started | 2022-02-10 | Not Started | 2022-04-06 | 2022-03-16 | 21 | On/ Ahead Schedule | Not Started | 2022-03-17 | 2022-03-30 | Not Started | 2022-05-13 | Not Started
35236438 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | E.5034805.01.36 | 5795300 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2534 | 0 | 2534 | 0.47992 | 0.47992 | 0 | 0 | 0.47992 | [5 empty] | 90000 | 0 | 90000 |  |  | 37.6 | 0 | 89962.4 | On/Under Budget | Request 2021 Budget | 0 | 673 | -673 | 673 | -673 | 814.6 | 90.1 | 0 | 90.1 | 0 | 0 | 0 | 37.5 | 141.3 | 0 | 0 | 0 | 0 | 37 | 0 | 90 | 91 | 91 | 91 | 91 | 91 | 91 | 2021-06-18 | 159242 | BL-A | BL-A 35236438_ECOP - MIDDLETOWN 1101-H16-LR48212 PH1.8_08W - DD 210402 | 2021-04-15 | 2021-09-07 | Not Started | 2021-09-08 | 2021-09-14 | Not Started | 2021-10-12 | Not Started | 2021-11-02 | Not Started | 2021-09-08 | 2021-09-08 | Not Started | 2021-09-09 | 2021-09-29 | Not Started | 2021-10-13 | 2021-10-26 | Not Started | 2021-11-25 | Not Started | 2021-11-25 | Not Started | 2021-12-08 | Not Started | 2021-11-25 | Not Started | 2022-02-23 | Not Started | 2022-03-24 | Not Started | 2022-04-06 | 2022-04-27 | -21 | Behind Schedule | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2022-06-24 | Not Started
35235673 | FRRB - WYANDOTTE 1103 - W3 PH3.10 | E.5034825.01.28 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3500 | 0 | 0 | 3500 | 0.66288 | 0.66288 | 0 | 0 | 0.66288 | [5 empty] | 5064020 | 1985730 | 3078290 |  |  | 4210.7 | 0 | 3074079.3 | On/Under Budget | Budget Allocated | 3078290 | 2318503 | 759787 | 2318503 | 759787 | 2318502.9 | 3434.4 | 76.6 | 3357.8 | 0 | 0 | 0 | 4210.7 | 0 | 0 | 0 | 0 | 0 | 229 | 3905 | 3434 | 500934 | 1000000 | 810000 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-23 | Not Started | 2021-04-12 | 2021-04-16 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-12-21 | 2021-12-21 | 0 | On/ Ahead Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | E.5034825.01.31 | 5795419 | ESTS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 12650 | 0 | 0 | 12650 | 2.3958 | 2.3958 | 0 | 0 | 2.3958 | [5 empty] | 13666223 | 4167460 | 9498763 | 1098759 | 8400004 | 48942.6 | 0 | 9449820.4 | On/Under Budget | Budget Allocated | 9498763 | 8400001 | 1098762 | 8400001 | 1098762 | 8400001 | 5080.1 | 1094.6 | 3985.5 | 0 | 0 | 0 | 48942.7 | 0 | 0 | 0 | 0 | 236 | 10617 | 36995 | 5080 | 2000096 | 2000096 | 2000096 | 2000096 | 346689 | 0 | 2021-05-25 |  |  |  |  | 2021-06-04 | Not Started | 2021-07-06 | 2021-07-12 | Not Started | 2021-07-05 | Not Started | 2021-07-30 | Not Started | [6 empty] | 2021-07-06 | 2021-07-12 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-10-19 | Not Started | 2021-08-03 | Not Started | 2021-11-02 | Not Started | 2021-11-02 | Not Started | 2021-12-02 | 2021-12-02 | 0 | On/ Ahead Schedule | Not Started | 2021-12-02 | 2021-12-16 | Not Started | 2022-01-31 | Not Started
35233166 | FRRB - BIG BEND 1102 - B5 PH5.2 | E.5034825.01.04 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5300 | 0 | 0 | 5300 | 1.0038 | 1.0038 | 0 | 0 | 1.0038 | [5 empty] | 6979245 | 2568095 | 4411150 | 911150 | 3500000 | 2054.9 | 0 | 4409095.1 | On/Under Budget | Budget Allocated | 4411150 | 3501608 | 909542 | 3501608 | 909542 | 3501608.2 | 0 | 446.7 | -446.7 | 0 | 0 | 0 | 2054.9 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 0 | 500000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 2021-05-21 | 160640 | BL-A: | BL-A: 35233166 FRRB - Big Bend 1102 - B5 PH 5.2 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35232960 | CWSP - DESCHUTES 11049718 PH1.2 | E.5034713.01.07 | 5794554 | ESTS | 08W | [6 empty] | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 15470 | 0 | 15470 | 2.9299 | 2.9299 | 0 | 0 | 2.9299 | 15081 | 0 | 2.8563 | 0 |  | 475000 | 0 | 475000 |  |  | 24764.1 | 0 | 450235.9 | On/Under Budget | Budget Allocated | 5669548 | 5789125 | -119577 | 5789125 | -119577 | 5789125.4 | 47258.2 | 1438.1 | 45820.1 | 0 | 0 | 0 | 24764.1 | 0 | 0 | 0 | 0 | 149 | 7898 | 15279 | 47258 | 1879541 | 1894087 | 1925076 | 19837 | 0 | 0 | 2021-06-18 | 158349 | BL-A_ | BL-A_35233960_CWSP - DESCHUTES 11049718 PH1.2_08W_Apr.2021 | 2021-04-01 | 2021-07-07 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-06-30 | Not Started | 2021-08-24 | Not Started | 2021-07-08 | 2021-07-08 | Not Started | 2021-07-09 | 2021-07-14 | Not Started | 2021-07-07 | 2021-07-26 | Not Started | 2021-09-16 | Not Started | 2021-09-16 | Not Started | 2021-09-29 | Not Started | 2021-09-16 | Not Started | 2021-11-10 | Not Started | 2021-12-09 | Not Started | 2022-02-16 | 2022-02-10 | 6 | On/ Ahead Schedule | Not Started | 2022-02-11 | 2022-02-24 | Not Started | 2022-04-11 | Not Started
35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | E.5034805.01.32 | 5795300 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3073 | 0 | 0 | 3073 | 0.58201 | 0 | 0.58201 | 0 | 0.58201 | [5 empty] | 300000 | 300000 | 0 |  |  | 271.6 | 0 | -271.6 | OverRun | Request 2021 Budget | 0 | 15317 | -15317 | 15317 | -15317 | 15316.6 | 797.4 | -14247.6 | 15045 | 0 | 0 | 0 | 271.6 | 0 | 0 | 0 | 0 | 0 | 229 | 14290 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | E.5034825.01.22 | 5795419 | ESTS | 08W | [6 empty] | 2021 | 2021 | FRRB - NCF | OROVILLE | North Valley Assets | 6962 | 0 | 0 | 6962 | 1.3186 | 1.3186 | 0 | 0 | 1.3186 | [5 empty] | 8555764 | 2912507 | 5643257 | 1023259 | 4619998 | 73959.3 | 144588.1 | 5424709.6 | On/Under Budget | Budget Allocated | 5643257 | 4619998 | 1023259 | 4619998 | 1023259 | 4619998.2 | 26730.3 | 8477.3 | 18253 | 0 | 0 | 0 | 73959.3 | 0 | 0 | 0 | 0 | 893 | 14799 | 49790 | 26730 | 526914 | 1000249 | 1000249 | 1000249 | 1000125 | 0 | 2021-05-25 |  |  |  |  | 2021-06-04 | Not Started | 2021-07-06 | 2021-07-12 | Not Started | 2021-07-05 | Not Started | 2021-07-30 | Not Started | [6 empty] | 2021-07-06 | 2021-07-12 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-10-19 | Not Started | 2021-08-03 | Not Started | 2021-11-02 | Not Started | 2021-11-02 | Not Started | 2021-12-02 | 2021-12-02 | 0 | On/ Ahead Schedule | Not Started | 2021-12-02 | 2021-12-16 | Not Started | 2022-01-31 | Not Started
35242428 | FRRB - BIG BEND 1102 - B4 PH4.2 | E.5034825.01.85 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4435 | 0 | 0 | 4435 | 0.83996 | 0.83996 | 0 | 0 | 0.83996 | [5 empty] | 200000 | 0 | 200000 |  |  | 3981.4 | 0 | 196018.6 | On/Under Budget | Budget Allocated | 3963125 | 2959255 | 1003870 | 2959255 | 1003870 | 2959254.9 | 5683.8 | -21090.9 | 26774.7 | 0 | 0 | 0 | 3981.4 | 0 | 0 | 0 | 0 | 0 | 0 | 25072 | 5684 | 3629 | 500000 | 1000000 | 1000000 | 424870 | 0 | 2021-06-18 | 161684 | BL-0: | BL-0: 35242428 FRRB - BIG BEND 1102 - B4 PH4.2 - Jun 21 | 2021-06-15 | 2021-06-30 | Not Started | 2021-07-30 | 2021-08-05 | Not Started | 2021-07-29 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-30 | 2021-08-05 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2022-01-10 | 2021-12-28 | 13 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242429 | FRRB - BIG BEND 1102 - B4 PH4.3 | E.5034825.01.86 | 5795419 | ESTS | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3432 | 0 | 0 | 3432 | 0.65 | 0.65 | 0 | 0 | 0.65 | [5 empty] | 200000 | 0 | 200000 |  |  | 225.1 | 0 | 199774.9 | On/Under Budget | Request 2021 Budget | 0 | 2294433 | -2294433 | 2294433 | -2294433 | 2294433.5 | 5683.8 | -24892.8 | 30576.6 | 0 | 0 | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 25118 | 5684 | 2684 | 500000 | 1000000 | 759847 | 1101 | 0 | 2021-06-18 | 161683 | BL-0: | BL-0: 35242429 FRRB - BIG BEND 1102 - B4 PH4.3 - Jun 21 | 2021-06-15 | 2021-06-30 | Not Started | 2021-07-30 | 2021-08-05 | Not Started | 2021-07-29 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-30 | 2021-08-05 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2022-01-10 | 2021-12-28 | 13 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | 5790907 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON |  | 0 | 13306 | 0 | 13306 | 2.5201 | 0 | 0 | 0 | 2.5201 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 198 | -198 | 198 | -198 | [10 empty] | 41 | 39 | 39 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | E.5033919.01 | 5790112 | ESTS | 08W | [6 empty] | 2022 |  | SH | CLRLAKE | Stockton Assets | 21597 | 0 | 0 | 21597 | 4.0903 | 0 | 4.0903 | 0 | 4.0903 | [5 empty] | 118750 | 0 | 118750 |  |  | 55361.5 | 0 | 63388.5 | On/Under Budget | Budget Allocated | 500000 | 51585 | 448415 | 51585 | 448415 | 65919.6 | 3128.7 | -1777.5 | 4906.2 | 0 | 0 | 10853.4 | 44508.1 | 3482 | 0 | 9924 | 3595 | 2583 | 32742 | -2559 | 3129 | 362 | 362 | 362 | 362 | 362 | 362 | 2021-06-18 | 159379 | BL-A: | BL-A: 35174501_ECOP-Middletown 1101-H12-LR548-Ph3_08W - B1_Apr 21 | 2021-04-21 | 2022-03-07 | Not Started | 2022-03-08 | 2022-03-14 | Not Started |  |  | 2022-04-04 | Not Started | 2022-09-20 | 2022-12-16 | Not Started | [6 empty] | 2023-01-17 | Not Started | 2023-01-17 | Not Started | 2023-02-13 | Not Started | 2023-01-17 | Not Started |  |  | 2023-03-07 | Not Started | 2023-01-17 | 2023-03-07 | -49 | Behind Schedule | Not Started |  |  |  | 2023-11-28 | Not Started
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | 5790106 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP |  | 0 | 31680 | 0 | 31680 | 6 | 0 | 0 | 0 | 6 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 57057 | -57057 | 57057 | -57057 | [10 empty] | 20 | 19 | 56332 | 343 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | 5790107 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP |  | 0 | 30202 | 0 | 30202 | 5.7201 | 0 | 0 | 0 | 5.7201 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 83 | -83 | 83 | -83 | [10 empty] | 17 | 17 | 17 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | 5790105 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON |  | 0 | 57446.4 | 0 | 57446.4 | 10.88 | 0 | 0 | 0 | 10.88 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 735 | -735 | 735 | -735 | [10 empty] | 153 | 146 | 146 | 145 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173387 | BR-09-01A-W (E) SKYWAY PH3 20A PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -1680568 | 1680569 |  |  | 0 | 0 | 1680569 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 103 | -103 | 103 | -103 | 102.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 1 | 1 | 1
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | 5790005 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON |  | 0 | 12038.4 | 0 | 12038.4 | 2.28 | 0 | 0 | 0 | 2.28 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1727204 | -1727204 | 1727204 | -1727204 | [10 empty] | 1305 | 5117 | 4020 | 376 | 376 | 736282 | 979729 | 0 | 0 | 0 | 0 | 0
35173959 | CWSP-MIWUK 1702-LR 38218-PH 1.6 |  | 5785985 | ESTS | 08W | [6 empty] | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 | E.5015426.02 | 5539442 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 0 | 5000 | 0 | 5000 | 0.94697 | 0 | 0 | 0 | 0.94697 | [5 empty] | 166667 | 0 | 166667 |  |  | 23115.4 | 0 | 143551.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 24440 | -24440 | 24440 | -24440 | 47339 | 0 | 132 | -132 | 0 | 0 | 214.6 | 22900.8 | 22684.4 | 0 | 37623 | -14986 | 0 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 1671 | 2021-06-18 | 154999 | BL-A | BL-A 35167136_CWSP - PLACERVILLE 2106 LR1104 PH 1.2_08W - Jan. 2021 | 2021-01-25 | 2022-03-28 | Not Started | 2022-03-29 | 2022-04-04 | Not Started | 2022-02-24 | Not Started | 2022-05-23 | Not Started | 2022-03-29 | 2022-03-29 | Not Started | 2022-03-30 | 2022-04-19 | Not Started | 2022-02-25 | 2022-03-10 | Not Started | 2022-05-25 | Not Started |  |  |  |  | 2022-05-25 | Not Started | 2022-09-06 | Not Started | 2022-10-05 | Not Started | 2022-12-06 | 2022-12-06 | 0 | On/ Ahead Schedule | Not Started | 2022-12-07 | 2022-12-20 | Not Started | 2023-01-26 | Not Started
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 | E.5015426.03 | 5790011 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 0 | 10745 | 0 | 10745 | 2.035 | 0 | 0 | 0 | 2.035 | [5 empty] | 166667 | 0 | 166667 |  |  | 27703.6 | 0 | 138963.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 31312 | -31312 | 31312 | -31312 | 60207.1 | 2.4 | 132 | -129.6 | 0 | 0 | 608.9 | 27094.7 | 28286 | 0 | 46799 | -20432 | 155 | 154 | 286 | 2 | 3 | 3 | 3 | 3 | 3 | 4334 | 2021-06-18 | 160844 | BL-A: | BL-A: 35167138_CWSP - PLACERVILLE 2106 LR1104 PH 1.3_08W - May 21 | 2021-05-18 | 2022-01-20 | Not Started | 2022-04-26 | 2022-05-02 | Not Started | 2022-04-25 | Not Started | 2022-05-23 | Not Started | 2022-01-21 | 2022-01-21 | Not Started | 2022-01-24 | 2022-02-11 | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-10-04 | Not Started | 2022-11-02 | Not Started | 2023-01-03 | 2023-01-03 | 0 | On/ Ahead Schedule | Not Started | 2023-01-04 | 2023-01-17 | Not Started | 2023-02-23 | Not Started
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  | 5539424 | ESTS | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 23137 | -23137 | 23137 | -23137 | [10 empty] | 40010 | -16873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  | 5539425 | ESTS | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 9853 | -9853 | 9853 | -9853 | [10 empty] | 17179 | -7326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | 5539426 | ESTS | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6557 | -6557 | 6557 | -6557 | [10 empty] | 11607 | -5051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  | 5539427 | ESTS | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 4222 | -4222 | 4222 | -4222 | [10 empty] | 6886 | -2664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 | E.5014755.07 | 5790364 | ESTS | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 271429 | 0 | 271429 |  |  | 15611.2 | 0 | 255817.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3901 | -3901 | 3901 | -3901 | 16113 | 26.9 | 0 | 26.9 | 0 | 0 | 11904.1 | 3707.1 | 307.7 | 0 | 72839 | -69418 | 115 | 86 | 86 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 2021-06-18 | 155003 | BL-A | BL-A 35170202_CWSP - ORO FINO-1101 - LR-2022 PH 2.7_08W - Jan. 2021 | 2021-01-25 | 2022-01-27 | Not Started | 2022-01-31 | 2022-02-11 | Not Started | 2022-04-14 | Not Started | 2022-04-15 | Not Started | 2022-02-14 | 2022-02-14 | Not Started | 2022-02-15 | 2022-03-07 | Not Started | 2022-02-11 | 2022-02-24 | Not Started | 2022-05-23 | Not Started |  |  |  |  | 2022-05-23 | Not Started | 2022-10-28 | Not Started | 2022-11-28 | Not Started | 2022-12-26 | 2022-12-26 | 0 | On/ Ahead Schedule | Not Started | 2022-12-27 | 2023-01-09 | Not Started | 2023-02-15 | Not Started
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | E.5015549.09 | 5789705 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 5500 | 0 | 5500 | 1.0417 | 0 | 0 | 0 | 1.0417 | [5 empty] | 250000 | 0 | 250000 |  |  | 60065.4 | 0 | 189934.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 52700 | -52700 | 52700 | -52700 | 1838614.9 | 23.6 | 0 | 23.6 | 0 | 0 | 7499.3 | 52566.2 | 1778415.7 | 0 | 49310 | 12974 | -10394 | 338 | 338 | 24 | 25 | 25 | 25 | 25 | 12 | 0
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 | E.5015550.02 | 5789706 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 1750 | 6415 | 0 | 8165 | 1.5464 | 0 | 0 | 0 | 1.5464 | [5 empty] | 71428 | 0 | 71428 |  |  | 35072.1 | 0 | 36355.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 30856 | -30856 | 30856 | -30856 | 35052.6 | 16.8 | 132 | -115.2 | 0 | 0 | 4196.4 | 30875.7 | 0 | 0 | 26 | 24 | 30165 | 198 | 331 | 17 | 17 | 17 | 17 | 17 | 17 | 9 | 2021-06-11 |  |  |  |  | 2023-01-02 | Not Started | 2023-02-14 | 2023-02-20 | Not Started | 2023-02-13 | Not Started | 2023-03-13 | Not Started | 2023-01-03 | 2023-01-03 | Not Started | 2023-01-04 | 2023-01-24 | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started |  |  |  |  | 2023-04-05 | Not Started | 2023-07-18 | Not Started | 2023-08-16 | Not Started | 2023-10-17 | 2023-10-17 | 0 | On/ Ahead Schedule | Not Started | 2023-10-18 | 2023-10-31 | Not Started | 2023-12-07 | Not Started
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 | E.5015550.03 | 5789707 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 5400 | 2440 | 0 | 7840 | 1.4848 | 0 | 0 | 0 | 1.4848 | [5 empty] | 71428 | 0 | 71428 |  |  | 58867.5 | 0 | 12560.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 53281 | -53281 | 53281 | -53281 | 58845.3 | 23.7 | 132 | -108.3 | 0 | 0 | 5564.5 | 53303 | 0 | 0 | 25882 | 183 | 26310 | 332 | 464 | 24 | 25 | 25 | 25 | 12 | 0 | 0 | 2021-06-11 |  |  |  |  | 2023-01-02 | Not Started | 2023-02-14 | 2023-02-20 | Not Started | 2023-02-13 | Not Started | 2023-03-13 | Not Started | 2023-01-03 | 2023-01-03 | Not Started | 2023-01-04 | 2023-01-24 | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started |  |  |  |  | 2023-04-05 | Not Started | 2023-07-18 | Not Started | 2023-08-16 | Not Started | 2023-10-17 | 2023-10-17 | 0 | On/ Ahead Schedule | Not Started | 2023-10-18 | 2023-10-31 | Not Started | 2023-12-07 | Not Started
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 | E.5015550.04 | 5789708 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 13875 | 0 | 13875 | 2.6278 | 0 | 0 | 0 | 2.6278 | [5 empty] | 60000 | 0 | 60000 |  |  | 36644.2 | 0 | 23355.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 35609 | -35609 | 35609 | -35609 | 36522.4 | 2.8 | 132 | -129.2 | 0 | 0 | 913.7 | 35730.4 | 0 | 0 | 43 | 6 | 34664 | 546 | 340 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2022-01-17 | Not Started | 2022-03-01 | 2022-03-07 | Not Started | 2022-02-28 | Not Started | 2022-03-14 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-08 | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-07-04 | Not Started | 2022-08-02 | Not Started | 2022-10-03 | 2022-10-03 | 0 | On/ Ahead Schedule | Not Started | 2022-10-04 | 2022-10-17 | Not Started | 2022-11-23 | Not Started
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 | E.5015550.05 | 5789709 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 14192 | 0 | 14192 | 2.6879 | 0 | 0 | 0 | 2.6879 | [5 empty] | 94284 | 0 | 94284 |  |  | 42325.3 | 0 | 51958.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 40931 | -40931 | 40931 | -40931 | 42208.8 | 4.3 | 132 | -127.7 | 0 | 0 | 1277.9 | 41047.4 | 0 | 0 | 39608 | 237 | 39837 | -39135 | 368 | 4 | 5 | 5 | 2 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2023-01-09 | Not Started | 2023-02-21 | 2023-02-27 | Not Started | 2023-02-20 | Not Started | 2023-03-06 | Not Started | 2023-01-10 | 2023-01-10 | Not Started | 2023-01-11 | 2023-01-31 | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-14 | Not Started |  |  |  |  | 2023-03-14 | Not Started | 2023-06-26 | Not Started | 2023-07-25 | Not Started | 2023-09-25 | 2023-09-25 | 0 | On/ Ahead Schedule | Not Started | 2023-09-26 | 2023-10-09 | Not Started | 2023-11-15 | Not Started
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 | E.5015550.06 | 5789710 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 0 | 17520 | 0 | 17520 | 3.3182 | 0 | 0 | 0 | 3.3182 | [5 empty] | 71428 | 0 | 71428 |  |  | 24646.5 | 0 | 46781.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 21270 | -21270 | 21270 | -21270 | 24568.3 | 15 | 132 | -117 | 0 | 0 | 3298.5 | 21348 | 0 | 0 | 20417 | 138 | 20534 | -20142 | 269 | 15 | 16 | 16 | 8 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2023-01-09 | Not Started | 2023-02-21 | 2023-02-27 | Not Started | 2023-02-20 | Not Started | 2023-03-06 | Not Started | 2023-01-10 | 2023-01-10 | Not Started | 2023-01-11 | 2023-01-31 | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-14 | Not Started |  |  |  |  | 2023-03-14 | Not Started | 2023-06-26 | Not Started | 2023-07-25 | Not Started | 2023-09-25 | 2023-09-25 | 0 | On/ Ahead Schedule | Not Started | 2023-09-26 | 2023-10-09 | Not Started | 2023-11-15 | Not Started
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 | E.5015550.07 | 5789711 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 2960 | 0 | 0 | 2960 | 0.56061 | 0 | 0 | 0 | 0.56061 | [5 empty] | 60000 | 0 | 60000 |  |  | 22728.5 | 0 | 37271.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 21637 | -21637 | 21637 | -21637 | 22609.1 | 3.5 | 132 | -128.5 | 0 | 0 | 972.7 | 21755.9 | 0 | 0 | 8512 | 55 | 12670 | 127 | 260 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2022-01-06 | Not Started | 2022-02-18 | 2022-02-24 | Not Started | 2022-02-17 | Not Started | 2022-03-03 | Not Started | 2022-01-07 | 2022-01-07 | Not Started | 2022-01-10 | 2022-01-28 | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-03-11 | Not Started |  |  |  |  | 2022-03-11 | Not Started | 2022-06-23 | Not Started | 2022-07-22 | Not Started | 2022-09-22 | 2022-09-22 | 0 | On/ Ahead Schedule | Not Started | 2022-09-23 | 2022-10-06 | Not Started | 2022-11-14 | Not Started
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | E.5034400.01 | 5792091 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | CONCORD | Diablo Assets | 7075.2 | 0 | 0 | 7075.2 | 1.34 | 0 | 1.34 | 0 | 1.34 | [5 empty] | 550000 | 0 | 550000 |  |  | 162546.9 | 0 | 387453.1 | On/Under Budget | Budget Allocated | 852800 | 143665 | 709135 | 143665 | 709135 | 5664184.8 | 0 | 10077.5 | -10077.5 | 0 | 0 | 8804.8 | 153742.1 | 5511715.4 | 0 | 7595 | 21330 | 5663 | 55120 | 53957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157128 | BL-A | BL-A ECOP - CLAYTON 2212 - H01-LR2951 - Mar. 2021 | 2021-03-07 | 2021-07-30 | Not Started | 2022-03-11 | 2022-03-17 | Not Started | 2022-03-10 | Not Started | 2022-04-07 | Not Started | 2021-08-02 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2022-04-08 | 2022-04-28 | Not Started | 2022-05-09 | Not Started | 2022-05-09 | Not Started | 2022-08-03 | Not Started | 2022-05-09 | Not Started | 2022-08-03 | Not Started | 2022-08-10 | Not Started | 2023-01-20 | 2022-12-07 | 44 | On/ Ahead Schedule | Not Started | 2022-12-08 | 2022-12-21 | Not Started | 2023-03-01 | Not Started
35192284 | ECOP - SILVERADO 2104 - H05-LR726 | E.5034416.01 | 5792107 | ESTS | 08W | [6 empty] | 2022 |  | SH | NAPA | North Bay Assets | 10929.6 | 0 | 0 | 10929.6 | 2.07 | 0 | 2.0701 | 0 | 2.07 | [5 empty] | 400000 | 0 | 400000 | 0 | 400000 | 172084.7 | 0 | 227915.3 | On/Under Budget | Budget Allocated | 380000 | 379743 | 257 | 379743 | 257 | 390218.4 | 31946.4 | 6371 | 25575.4 | 0 | 0 | 9858.5 | 162226.1 | 616.6 | 0 | 3969 | 3217 | 33711 | 77632 | 37327 | 31946 | 4669 | 1207 | 1207 | 2429 | 1215 | 181215 | 2021-06-18 | 159384 | BL-A: | BL-A: 35192284_ECOP - SILVERADO 2104 - H05-LR726_08W - B1_Apr 21 | 2021-04-21 | 2021-07-14 | Not Started | 2021-11-11 | 2021-11-17 | Not Started | 2021-11-10 | Not Started | 2021-12-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-12-10 | 2021-12-23 | Not Started | 2022-01-10 | Not Started | 2022-01-10 | Not Started | 2022-01-21 | Not Started | 2022-01-10 | Not Started | 2022-02-28 | Not Started | 2022-03-29 | Not Started | 2022-06-01 | 2022-05-30 | 2 | On/ Ahead Schedule | Not Started | 2022-05-31 | 2022-06-13 | Not Started | 2022-07-27 | Not Started
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | 5790005 | ESTS | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 27306 | -27306 | 27306 | -27306 | [10 empty] | 10804 | 11012 | 5163 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | E.5034401.01 | 5792092 | ESTS | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 26400 | 0 | 26400 | 5 | 5 | 0 | 0 | 5 | [5 empty] | 1 | -949999 | 950000 |  |  | 210736.1 | 1500 | 737763.9 | On/Under Budget | Request 2021 Budget | 0 | 6812772 | -6812772 | 6812772 | -6812772 | 6814727.2 | 14180.5 | -35845.2 | 50025.7 | 0 | 0 | 1955.2 | 208780.9 | 0 | 0 | 5326 | 5451 | 174389 | 50579 | 8882 | 14181 | 14266 | 1931314 | 2101069 | 1027613 | 775140 | 704564 | 2021-06-18 | 156209 | BL-A | BL-A 35192290_ECOP - DIAMOND SPRINGS 1107 - H01-LR1402_08W - DD 210205 Feb. 2021 | 2021-02-23 | 2021-06-29 | Not Started | 2021-06-30 | 2021-07-06 | Not Started | 2021-07-16 | Not Started | 2021-08-24 | Not Started | 2021-08-04 | 2021-08-10 | Not Started | 2021-08-11 | 2021-09-14 | Not Started | 2021-07-21 | 2021-08-10 | Not Started | 2021-09-16 | Not Started | 2021-09-16 | Not Started | 2021-09-29 | Not Started | 2021-09-16 | Not Started | 2021-12-01 | Not Started | 2021-12-23 | Not Started | 2021-12-30 | 2022-02-08 | -40 | Behind Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-04-07 | Not Started
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | E.5034402.01 | 5792093 | ESTS | 08W | [6 empty] | 2022 |  | SH | PLCRVLLE | Sierra Assets | 2534.4 | 0 | 0 | 2534.4 | 0.48 | 0 | 0.47992 | 0 | 0.48 | [5 empty] | 1 | -499999 | 500000 |  |  | 115720.3 | 0 | 384279.7 | On/Under Budget | Budget Allocated | 267945.29 | 298994 | -31048.71 | 298994 | -31048.71 | 1671450.4 | 81111.1 | 12413.9 | 68697.2 | 0 | 0 | 1755.2 | 113965.1 | 1370701.3 | 0 | 5236 | 12170 | 19859 | -8237 | 72523 | 81111 | 6439 | 7733 | 6218 | 17351 | 75193 | 3398 | 2021-06-18 | 156210 | BL-A | BL-A 35192291_ECOP - DIAMOND SPRINGS 1107 - H02-LR1402_08W - DD 210205 Feb. 2021 | 2021-02-23 | 2021-07-27 | Not Started | 2021-07-28 | 2021-08-03 | Not Started | 2021-09-20 | Not Started | 2021-09-21 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-09-21 | 2021-10-04 | Not Started | 2021-12-16 | Not Started | 2021-12-30 | Not Started | 2022-01-26 | Not Started | 2021-12-16 | Not Started | 2022-02-16 | Not Started | 2022-03-17 | Not Started | 2022-07-07 | 2022-04-22 | 76 | On/ Ahead Schedule | Not Started | 2022-04-25 | 2022-05-06 | Not Started | 2022-06-21 | Not Started
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | E.5034403.01 | 5792094 | ESTS | 08W | [6 empty] | 2022 |  | SH | STROSA | Sonoma Assets | 4224 | 0 | 0 | 4224 | 0.8 | 0 | 0.8 | 0 | 0.8 | [5 empty] | 950000 | 700000 | 250000 |  |  | 85627 | 0 | 164373 | On/Under Budget | Budget Allocated | 200 | 67254 | -67054 | 67254 | -67054 | 84072.9 | 487.5 | 6617.8 | -6130.3 | 0 | 0 | 15197.1 | 70429.8 | 1621.9 | 0 | 14439 | 25367 | -9814 | 10611 | 23210 | 488 | 492 | 492 | 492 | 492 | 492 | 492 | 2021-06-18 | 155774 | BL- A | BL- A 35192292_ECOP - FULTON 1107 - H02-LR604 Ph 1.1_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-08-18 | Not Started | 2021-08-19 | 2021-09-08 | Not Started | 2021-11-10 | Not Started | 2021-11-11 | Not Started | 2021-08-19 | 2021-08-19 | Not Started | 2021-08-20 | 2021-09-09 | Not Started | 2021-11-11 | 2021-12-22 | Not Started | 2021-12-23 | Not Started | 2021-12-23 | Not Started | 2022-03-09 | Not Started | 2021-12-23 | Not Started | 2022-03-09 | Not Started | 2022-03-10 | Not Started | 2022-05-03 | 2022-04-22 | 11 | On/ Ahead Schedule | Not Started | 2022-04-25 | 2022-05-06 | Not Started | 2022-06-21 | Not Started
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | E.5033917.01 | 5790111 | ESTS | 08W | [6 empty] | 2022 |  | SH | CLRLAKE | Humboldt Division Assets | 5491.2 | 0 | 0 | 5491.2 | 1.04 | 0 | 1.04 | 0 | 1.04 | [5 empty] | 155000 | 0 | 155000 |  |  | 40543.8 | 0 | 114456.2 | On/Under Budget | Budget Allocated | 500000 | 49200 | 450800 | 49200 | 450800 | 51558.9 | 2360.2 | -4586.4 | 6946.6 | 0 | 0 | 0 | 40543.8 | 2358.7 | 0 | 0 | 9373 | 4319 | 23389 | 8050 | 2360 | 285 | 285 | 285 | 285 | 285 | 285 | 2021-06-18 | 159753 | BL-A: | BL-A: 35174478_ECOP-Middletown 1101-H12-LR548-Ph1_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2021-12-21 | 2021-12-27 | Not Started |  |  | 2022-03-14 | Not Started | 2022-07-05 | 2022-07-05 | Not Started | [6 empty] | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-28 | Not Started | 2022-11-01 | Not Started |  |  | 2022-12-20 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2023-09-12 | Not Started
35191553 | BR-13-01-W (E) LIGHTFOOT WAY PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 8239 | 0 | -8239 | OverRun | Project is not in the WP or in 2020 WP | 0 | 235 | -235 | 235 | -235 | 8239 | 0 | 0 | 0 | 0 | 0 | 8004.2 | 234.7 | 0 | 0 | 49 | 47 | 47 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | E.5034372.01 | 5792064 | ESTS | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 7718 | 0 | 7718 | 1.4617 | 1.4617 | 0 | 0 | 1.4617 | [5 empty] | 237833 | 0 | 237833 |  |  | 44023.1 | 0 | 193809.9 | On/Under Budget | Budget Allocated | 237833 | 225878 | 11955 | 225878 | 11955 | 229755.7 | 18258.3 | 14171.6 | 4086.7 | 0 | 0 | 3878 | 40145.1 | 0 | 0 | 7740 | 4122 | 2174 | 6776 | 5161 | 18258 | 0 | 0 | 161463 | 20183 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-07-16 | Not Started | 2021-09-01 | 2021-09-07 | Not Started | 2021-08-31 | Not Started | 2021-09-28 | Not Started | 2021-07-19 | 2021-07-19 | Not Started | 2021-07-20 | 2021-08-09 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-18 | Not Started
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | E.5034785.01 | 5795129 | ESTS | 08W | [6 empty] | 2022 |  | SH | SNRAFAEL | North Bay Assets | 8606.4 | 0 | 0 | 8606.4 | 1.63 | 0 | 1.6299 | 0 | 1.63 | [5 empty] | 312500 | 0 | 312500 |  |  | 28694.2 | 0 | 283805.8 | On/Under Budget | Request 2021 Budget | 0 | 87287 | -87287 | 87287 | -87287 | 87727.5 | 20442.9 | -35116.6 | 55559.5 | 0 | 0 | 0 | 28694.1 | 440.7 | 0 | 0 | 698 | 2187 | 537 | 60389 | 20443 | 506 | 506 | 506 | 506 | 506 | 506 | 2021-06-18 | 156499 | BL-A | BL-A 35223615_ECOP - LAS GALLINAS A 1105 Ph 2_08W - DD 210219 Feb. 2021 | 2021-03-01 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-04 | Not Started | 2021-10-01 | Not Started | 2021-10-04 | Not Started | 2021-07-29 | 2021-07-29 | Not Started | 2021-07-30 | 2021-08-19 | Not Started | 2021-10-04 | 2021-10-15 | Not Started | 2021-10-27 | Not Started | 2021-10-27 | Not Started | 2021-11-09 | Not Started | 2021-10-27 | Not Started | 2022-02-08 | Not Started | 2022-03-09 | Not Started | 2022-03-28 | 2022-03-22 | 6 | On/ Ahead Schedule | Not Started | 2022-03-24 | 2022-04-06 | Not Started | 2022-05-19 | Not Started
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | E.5034607.01.02 | 5794208 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | CHICO | North Valley Assets | 9134.4 | 0 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 1.73 | [5 empty] | 400000 | 0 | 400000 |  |  | 46249.2 | 0 | 353750.8 | On/Under Budget | Budget Allocated | 500000 | 499509 | 491 | 458818 | 41182 | 15734070.9 | 2890.3 | -7728.7 | 10619 | 0 | 0 | 0 | 46249.3 | 15275253.6 | 0 | 0 | 2618 | 2963 | 54543 | -6146 | 2906 | 341 | 341 | 400432 | 341 | 341 | 40828 | 2021-06-18 | 161669 | BL-A2 | BL-A2_35224712_SH - BUCKS CREEK 1101 CB PH 2_08W_Jun.2021 | 2021-06-14 | 2021-07-23 | Not Started | 2023-01-02 | 2023-01-27 | Not Started | 2022-12-30 | Not Started | 2023-02-17 | Not Started | 2021-07-26 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-05-01 | Not Started | 2023-05-01 | Not Started | 2023-05-12 | Not Started | 2023-05-01 | Not Started | 2023-08-18 | Not Started | 2023-11-03 | Not Started | 2022-12-30 | 2024-01-15 | -381 | Behind Schedule | Not Started | 2024-01-16 | 2024-01-29 | Not Started | 2024-03-13 | Not Started
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | E.5034607.01.03 | 5794208 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | CHICO | North Valley Assets | 9662.4 | 0 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 1.83 | [5 empty] | 400000 | 0 | 400000 |  |  | 37409.3 | 0 | 362590.7 | On/Under Budget | Budget Allocated | 500000 | 497412 | 2588 | 452063 | 47937 | 6381959.9 | 3520.8 | -3868 | 7388.8 | 0 | 0 | 0 | 37409.3 | 5929897 | 0 | 0 | 2094 | 119 | 53399 | -14334 | 3475 | 269 | 269 | 405769 | 269 | 269 | 45816 | 2021-06-18 | 157968 | BL-A1 | BL-A1_35224713_SH - BUCKS CREEK 1101 CB PH 3_08W_Mar.2021 | 2021-03-23 | 2021-12-30 | Not Started | 2023-02-20 | 2023-03-17 | Not Started | 2023-02-17 | Not Started | 2023-04-07 | Not Started | 2021-12-31 | 2021-12-31 | Not Started | 2023-04-10 | 2023-04-28 | Not Started | 2023-05-01 | 2023-05-12 | Not Started | 2023-05-15 | Not Started | 2023-05-15 | Not Started | 2023-05-26 | Not Started | 2023-05-15 | Not Started | 2023-08-25 | Not Started | 2023-09-25 | Not Started | 2022-12-16 | 2023-10-13 | -301 | Behind Schedule | Not Started | 2023-10-16 | 2023-10-27 | Not Started | 2023-12-12 | Not Started
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | E.5034609.01.02 | 5794206 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4699.2 | 0 | 4699.2 | 0.89 | 0 | 0.88996 | 0 | 0.89 | [5 empty] | 316666 | 0 | 316666 |  |  | 3097 | 0 | 313569 | On/Under Budget | Request 2021 Budget | 0 | 42828 | -42828 | 42828 | -42828 | 43231.9 | 3624.6 | -31647.5 | 35272.1 | 0 | 0 | 0 | 3097 | 404.2 | 0 | 0 | 31740 | -4856 | 7550 | 310 | 3625 | 3647 | 162 | 162 | 162 | 162 | 162 | 2021-06-18 | 157800 | BL-A | BL-A 35225589_CWSP - KONOCTI 1102 LR 965078 PH2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-22 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-11-22 | 2021-12-03 | Not Started | 2021-12-15 | Not Started | 2021-12-15 | Not Started | 2021-12-28 | Not Started | 2021-12-15 | Not Started | 2022-03-29 | Not Started | 2022-04-27 | Not Started | 2022-06-03 | 2022-06-28 | -25 | Behind Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-08-25 | Not Started
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | E.5034609.01.03 | 5794206 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4224 | 0 | 4224 | 0.8 | 0 | 0.8 | 0 | 0.8 | [5 empty] | 316666 | 0 | 316666 |  |  | 11103.1 | 0 | 305562.9 | On/Under Budget | Request 2021 Budget | 0 | 47670 | -47670 | 47670 | -47670 | 47670.2 | 3645.6 | -28533 | 32178.6 | 0 | 0 | 0 | 11103.1 | 0 | 0 | 0 | 28530 | -2137 | 13432 | -189 | 3646 | 3668 | 160 | 160 | 160 | 160 | 80 | 2021-06-18 | 157815 | BL-A | BL-A 35225591_CWSP - KONOCTI 1102 LR 965078 PH3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-23 | Not Started | 2021-08-24 | 2021-08-30 | Not Started | 2021-09-27 | Not Started | 2021-10-18 | Not Started | 2021-08-24 | 2021-08-24 | Not Started | 2021-08-25 | 2021-09-14 | Not Started | 2021-09-28 | 2021-10-11 | Not Started | 2021-11-10 | Not Started | 2021-11-10 | Not Started | 2021-11-23 | Not Started | 2021-11-10 | Not Started | 2022-02-22 | Not Started | 2022-03-23 | Not Started | 2022-02-03 | 2022-04-14 | -70 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | E.5034762.01.01 | 5794986 | ESTS | 08W | [6 empty] | 2022 |  | SH | NAPA | North Bay Assets | 950.4 | 0 | 0 | 950.4 | 0.18 | 0 | 0.17992 | 0 | 0.18 | [5 empty] | 1 | -499999 | 500000 |  |  | 11637 | 0 | 488363 | On/Under Budget | Request 2021 Budget | 0 | 30838 | -30838 | 30838 | -30838 | 31115.2 | 20117.9 | 1988.8 | 18129.1 | 0 | 0 | 0 | 11637 | 277.5 | 0 | 665 | 6325 | 646 | 554 | 1459 | 20118 | 179 | 179 | 179 | 179 | 179 | 179 | 2021-06-18 | 159245 | BL-A | BL-A 35223062_PSPS - Calistoga 1102 - W/O Napa River_08W - DD 210402 | 2021-04-15 | 2021-08-27 | Not Started | 2021-08-30 | 2021-09-03 | Not Started | 2021-09-10 | Not Started | 2021-10-22 | Not Started | 2021-08-30 | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-20 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-11-16 | Not Started | 2021-11-16 | Not Started | 2021-11-29 | Not Started | 2021-11-16 | Not Started | 2022-02-14 | Not Started | 2022-03-15 | Not Started | 2022-03-18 | 2022-05-16 | -59 | Behind Schedule | Not Started | 2022-05-17 | 2022-05-30 | Not Started | 2022-07-13 | Not Started
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | E.5034763.01.01 | 5794987 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | OROVILLE | North Valley Assets | 4065.6 | 0 | 0 | 4065.6 | 0.77 | 0 | 0.77008 | 0 | 0.77 | [5 empty] | 950000 | 0 | 950000 |  |  | 62163 | 0 | 887837 | On/Under Budget | Budget Allocated | 500000 | 513941 | -13941 | 513941 | -13941 | 6418941.4 | 300.8 | 0 | 300.8 | 0 | 0 | 0 | 62163 | 5905000 | 0 | 331 | 10083 | 14979 | 15617 | 21153 | 301 | 2089 | 2626 | 3813 | 5292 | 1657 | 436000 | 2021-06-18 | 158071 | BL-A_ | BL-A_35223039_PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE_08W_Mar.2021 | 2021-03-29 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-02 | Not Started | 2021-06-18 | Not Started | 2021-08-23 | Not Started | 2021-07-29 | 2021-07-29 | Not Started | 2021-07-30 | 2021-08-11 | Not Started | 2021-07-09 | 2021-07-20 | Not Started | 2021-09-15 | Not Started | 2021-09-15 | Not Started | 2021-09-28 | Not Started | 2021-09-15 | Not Started | 2021-12-28 | Not Started | 2022-01-26 | Not Started | 2022-01-19 | 2022-03-01 | -41 | Behind Schedule | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-04-28 | Not Started
35223030 | PSPS - BANGOR 1101 CB - MICROGRID | E.5034757.01.01 | 5794981 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | OROVILLE | North Valley Assets | 3009.6 | 0 | 0 | 3009.6 | 0.57 | 0 | 0.57008 | 0 | 0.57 | [5 empty] | 950000 | 0 | 950000 |  |  | 59610.6 | 0 | 890389.4 | On/Under Budget | Budget Allocated | 500000 | 506963 | -6963 | 506963 | -6963 | 2008159.6 | 8426.4 | 5776.8 | 2649.6 | 0 | 0 | 0 | 59610.5 | 1501196.1 | 0 | 237 | 12633 | 21272 | 19066 | 626 | 8426 | 55072 | 100229 | 100229 | 102225 | 82552 | 4397 | 2021-06-18 | 157966 | BL-A_ | BL-A_35223030_PSPS - BANGOR 1101 CB - MICROGRID_08W_Mar.2021 | 2021-03-23 | 2021-08-06 | Not Started | 2021-08-30 | 2021-09-03 | Not Started | 2021-08-27 | Not Started | 2021-09-24 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-08-17 | 2021-08-30 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-01 | Not Started | 2021-10-19 | Not Started | 2022-01-31 | Not Started | 2022-03-01 | Not Started | 2022-12-30 | 2022-05-02 | 242 | On/ Ahead Schedule | Not Started | 2022-05-03 | 2022-05-16 | Not Started | 2022-06-29 | Not Started
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | E.5034758.01.01 | 5794982 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | AUBURN | Sierra Assets | 2323.2 | 0 | 0 | 2323.2 | 0.44 | 0 | 0.44 | 0 | 0.44 | [5 empty] | 500000 | 0 | 500000 |  |  | 48242.8 | 0 | 451757.2 | On/Under Budget | Budget Allocated | 136000 | 137095 | -1095 | 137095 | -1095 | 1513884.2 | 48631.4 | -874.8 | 49506.2 | 0 | 0 | 0 | 48242.9 | 1376789.4 | 0 | 371 | 8951 | 659 | 1559 | 37577 | 48631 | 19165 | 3252 | 3268 | 3283 | 3298 | 7080 | 2021-06-18 | 158882 | BL-A_ | BL-A_35223032_PSPS - MOUNTAIN QUARRIES 2101 - COOL_08W_Apr.2021 | 2021-04-07 | 2022-01-10 | Not Started | 2022-02-15 | 2022-02-21 | Not Started | 2022-02-14 | Not Started | 2022-03-14 | Not Started | 2022-01-11 | 2022-01-11 | Not Started | 2022-01-12 | 2022-02-01 | Not Started | 2022-02-15 | 2022-02-28 | Not Started | 2022-04-06 | Not Started | 2022-04-06 | Not Started | 2022-04-19 | Not Started | 2022-04-06 | Not Started | 2022-07-19 | Not Started | 2022-08-17 | Not Started | 2022-04-19 | 2022-10-18 | -182 | Behind Schedule | Not Started | 2022-10-19 | 2022-11-01 | Not Started | 2022-12-15 | Not Started
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | E.5034759.01.01 | 5794983 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | GRSSVLLY | Sierra Assets | 264 | 0 | 0 | 264 | 0.05 | 0 | 0.05 | 0 | 0.05 | [5 empty] | 500000 | 0 | 500000 |  |  | 13219.6 | 0 | 486780.4 | On/Under Budget | Budget Allocated | 120000 | 131564 | -11564 | 131564 | -11564 | 340118 | 26508.9 | 1172.4 | 25336.5 | 0 | 0 | 0 | 13219.6 | 208554.2 | 0 | 275 | 4563 | 1378 | 16794 | -10962 | 26509 | 65360 | 14051 | 2096 | 2525 | 4426 | 4551 | 2021-06-18 | 158193 | BL-A_ | BL-A_35223036_PSPS - BRUNSWICK 1110 - MORGAN RANCH DR_08W_Apr.2021 | 2021-03-31 | 2021-09-10 | Not Started | 2021-10-18 | 2021-10-22 | Not Started | 2021-10-15 | Not Started | 2021-11-12 | Not Started | 2021-09-13 | 2021-09-13 | Not Started | 2021-09-14 | 2021-10-04 | Not Started | 2021-10-18 | 2021-10-29 | Not Started | 2021-12-07 | Not Started | 2021-12-07 | Not Started | 2021-12-20 | Not Started | 2021-12-07 | Not Started | 2022-03-21 | Not Started | 2022-04-19 | Not Started | 2022-01-18 | 2022-06-20 | -153 | Behind Schedule | Not Started | 2022-06-21 | 2022-07-04 | Not Started | 2022-08-17 | Not Started
35219589 | CWSP - WILDWOOD 11011454 | E.5034719.01.01 | 5794561 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | REDBLUFF | North Valley Assets | 0 | 13622.4 | 0 | 13622.4 | 2.58 | 0 | 2.5799 | 0 | 2.58 | 14762 | 0 | 2.7958 | 0 |  | 950000 | 0 | 950000 |  |  | 77586.7 | 0 | 872413.3 | On/Under Budget | Budget Allocated | 102942 | 265866 | -162924 | 265866 | -162924 | 5260621.3 | 3138.9 | -88865.9 | 92004.8 | 0 | 0 | 0 | 77586.8 | 4994755.3 | 0 | 7244 | 3572 | 26499 | 106343 | 22795 | 3139 | 69410 | 23379 | 871 | 871 | 871 | 871 | 2021-06-18 | 158350 | BL-A_ | BL-A_35219589_CWSP - WILDWOOD 11011454_08W_Apr.2021 | 2021-04-01 | 2021-06-22 | Not Started | 2021-06-23 | 2021-06-29 | Not Started | 2022-04-08 | Not Started | 2022-04-11 | Not Started | 2021-06-23 | 2021-06-23 | Not Started | 2021-06-24 | 2021-07-14 | Not Started | 2021-08-02 | 2021-08-10 | Not Started | 2022-04-20 | Not Started | 2022-04-20 | Not Started | 2022-05-03 | Not Started | 2022-04-20 | Not Started | 2022-07-12 | Not Started | 2022-08-10 | Not Started | 2022-02-16 | 2022-09-21 | -217 | Behind Schedule | Not Started | 2022-09-22 | 2022-10-05 | Not Started | 2022-11-18 | Not Started
35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | E.5034767.01.01 | 5794998 | ESTS | 08W | [6 empty] | 2022 |  | SH | NAPA | North Bay Assets | 11827.2 | 0 | 0 | 11827.2 | 2.24 | 0 | 2.24 | 0 | 2.24 | [5 empty] | 190000 | 0 | 190000 |  |  | 60405.4 | 0 | 129594.6 | On/Under Budget | Budget Allocated | 180000 | 187745 | -7745 | 187745 | -7745 | 187744.9 | 28158.9 | 9419.2 | 18739.7 | 0 | 0 | 0 | 60405.4 | 0 | 0 | 0 | 0 | 0 | 32813 | 18174 | 28159 | 863 | 1470 | 877 | 102588 | 1739 | 1063 | 2021-06-18 | 159382 | BL-A: | BL-A: 35223024_ECOP - SILVERADO 2104 - H05 - LR726 PH2_08W - B1_Apr 21 | 2021-04-21 | 2021-07-14 | Not Started |  |  | Not Started | 2021-10-29 | Not Started | 2021-11-10 | Not Started | [9 empty] | 2022-03-01 | Not Started | [8 empty] | 2022-04-29 | Not Started | 2022-02-01 | 2022-05-09 | -97 | Behind Schedule | Not Started | 2022-05-03 | 2022-05-09 | Not Started | 2023-01-12 | Not Started
35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | E.5034767.01.02 | 5794998 | ESTS | 08W | [6 empty] | 2022 |  | SH | NAPA | North Bay Assets | 9504 | 0 | 0 | 9504 | 1.8 | 0 | 1.8 | 0 | 1.8 | [5 empty] | 190000 | 0 | 190000 |  |  | 28264 | 0 | 161736 | On/Under Budget | Budget Allocated | 180000 | 173429 | 6571 | 173429 | 6571 | 173428.9 | 26949.3 | 3255 | 23694.3 | 0 | 0 | 0 | 28264 | 0 | 0 | 0 | 0 | 0 | 4164 | 20845 | 26949 | 1473 | 1480 | 1487 | 113199 | 2167 | 1666 | 2021-06-18 | 159387 | BL-A: | BL-A: 35223026_ECOP - SILVERADO 2104 - H05 - LR726 PH3_08W - B1_Apr 21 | 2021-04-21 | 2021-07-14 | Not Started |  |  | Not Started | 2021-07-23 | Not Started | 2021-11-10 | Not Started | [9 empty] | 2022-05-02 | Not Started | [8 empty] | 2022-07-01 | Not Started | 2022-01-18 | 2022-07-11 | -174 | Behind Schedule | Not Started | 2022-07-05 | 2022-07-11 | Not Started | 2023-03-16 | Not Started
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | E.5034610.01.02 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 10190 | 0 | 0 | 10190 | 1.9299 | 0 | 1.9299 | 0 | 1.9299 | [5 empty] | 250000 | 0 | 250000 |  |  | 26009.8 | 0 | 223990.2 | On/Under Budget | Request 2021 Budget | 0 | 53931 | -53931 | 53931 | -53931 | 54353.9 | 20250.8 | -5796.9 | 26047.7 | 0 | 0 | 0 | 26009.8 | 422.4 | 0 | 8384 | 5522 | 3080 | 21496 | -6674 | 20251 | 312 | 312 | 312 | 312 | 312 | 312 | 2021-06-18 | 157816 | BL-A | BL-A 35220895_CWSP - MIDDLETOWN 1103 - LR 830 PH2.1_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-08-20 | Not Started | 2021-08-23 | 2021-08-27 | Not Started | 2021-09-03 | Not Started | 2021-10-15 | Not Started | 2021-08-23 | 2021-08-23 | Not Started | 2021-08-24 | 2021-09-13 | Not Started | 2021-09-06 | 2021-09-17 | Not Started | 2021-11-09 | Not Started | 2021-11-09 | Not Started | 2021-11-22 | Not Started | 2021-11-09 | Not Started | 2022-02-21 | Not Started | 2022-03-22 | Not Started | 2022-02-24 | 2022-04-14 | -49 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | E.5034610.01.03 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 1478 | 0 | 0 | 1478 | 0.27992 | 0 | 0.27992 | 0 | 0.27992 | [5 empty] | 1 | 1 | 0 |  |  | 9930.7 | 0 | -9930.7 | OverRun | Request 2021 Budget | 0 | 17472 | -17472 | 17472 | -17472 | 17999.1 | 108.7 | -6773.2 | 6881.9 | 0 | 0 | 0 | 9930.7 | 527.3 | 0 | 3718 | 3546 | 1076 | 12025 | -3661 | 109 | 110 | 110 | 110 | 110 | 110 | 110 | 2021-06-18 | 157802 | BL-A | BL-A 35220896_CWSP - MIDDLETOWN 1103 - LR 830 PH3.1_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-08-27 | Not Started | 2021-08-30 | 2021-09-03 | Not Started | 2021-12-24 | Not Started | 2021-12-27 | Not Started | 2021-08-30 | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-20 | Not Started | 2021-12-27 | 2022-01-07 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-07-29 | 2022-08-02 | -4 | Behind Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO | E.5034613.01.02 | 5794202 | ESTS | 08W | [6 empty] | Not in the WP |  | FRRB | SNCARLOS | Peninsula Assets | 0 | 5016 | 0 | 5016 | 0.95 | 0 | 0.95 | 0 | 0.95 | [5 empty] | 1 | 1 | 0 |  |  | 37518.1 | 39559 | -77077.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 40944 | -40944 | 40944 | -40944 | 40943.7 | 25000 | 21574.4 | 3425.6 | 0 | 0 | 0 | 37518.1 | 0 | 0 | 4295 | 3298 | 504 | 2736 | 5111 | 25000 | 0 | 0 | 0 | 0 | 0 | 0
35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | E.5034802.01.02 | 5543352 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | OROVILLE | North Valley Assets | 3010 | 0 | 0 | 3010 | 0.57008 | 0 | 0.57008 | 0 | 0.57008 | [5 empty] | 650000 | 0 | 650000 |  |  | 0 | 0 | 650000 | On/Under Budget | Budget Allocated | 500000 | 3010 | 496990 | 3010 | 496990 | 3010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3010 | 2021-06-18 | 158090 | BL-A_ | BL-A_35226700_CWSP - WYANDOTTE 110932586 PH 2_08W_Mar.2021 | 2021-03-30 | 2021-07-08 | Not Started | 2021-08-20 | 2022-06-09 | Not Started | 2021-08-19 | Not Started | 2022-06-30 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-08-20 | 2021-09-02 | Not Started | 2022-07-21 | Not Started | 2022-07-21 | Not Started | 2022-08-03 | Not Started | 2022-07-21 | Not Started | 2022-11-02 | Not Started | 2022-12-05 | Not Started | 2022-12-30 | 2022-12-30 | 0 | On/ Ahead Schedule | Not Started | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-28 | Not Started
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | E.5034611.01.03 | 5794204 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | REDDING | North Valley Assets | 4329.6 | 0 | 0 | 4329.6 | 0.82 | 0 | 0.82008 | 0 | 0.82 | [5 empty] | 150000 | 0 | 150000 |  |  | 10533.1 | 0 | 139466.9 | On/Under Budget | Budget Allocated | 500000 | 502694 | -2694 | 502694 | -2694 | 2882985.3 | 3252 | -19662.6 | 22914.6 | 0 | 0 | 0 | 10533.1 | 2380291.5 | 0 | 0 | 262 | 25207 | -4698 | 9426 | 3252 | 4896 | 52 | 400052 | 59392 | 2369 | 2486 | 2021-06-18 | 158088 | BL-A_ | BL-A_35226628_SH - KESWICK 1101 LR 1586 PH 1.3_08W_Mar.2021 | 2021-03-30 | 2021-07-27 | Not Started | 2021-08-05 | 2021-08-11 | Not Started | 2021-08-04 | Not Started | 2021-09-21 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-08-05 | 2021-08-18 | Not Started | 2021-10-14 | Not Started | 2021-10-14 | Not Started | 2021-10-27 | Not Started | 2021-10-14 | Not Started | 2022-01-26 | Not Started | 2022-02-24 | Not Started | 2023-01-13 | 2022-04-27 | 261 | On/ Ahead Schedule | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2022-06-24 | Not Started
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | E.5034611.01.04 | 5794204 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | REDDING | North Valley Assets | 23760 | 0 | 0 | 23760 | 4.5 | 0 | 4.5 | 0 | 4.5 | [5 empty] | 200000 | 0 | 200000 |  |  | 27899.6 | 0 | 172100.4 | On/Under Budget | Budget Allocated | 500000 | 511642 | -11642 | 511642 | -11642 | 6101982.9 | 2524.9 | -104182.6 | 106707.5 | 0 | 0 | 0 | 27899.5 | 5590340.7 | 0 | 0 | 262 | 25163 | 84518 | 22139 | 2525 | 2089 | 71 | 71 | 300911 | 71388 | 2505 | 2021-06-18 | 158089 | BL-A_ | BL-A_35226629_SH - KESWICK 1101 LR 1586 PH 1.4_08W_Mar.2021 | 2021-03-30 | 2021-07-27 | Not Started | 2021-08-05 | 2021-08-11 | Not Started | 2021-08-04 | Not Started | 2021-09-21 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-08-05 | 2021-08-18 | Not Started | 2021-10-14 | Not Started | 2021-10-14 | Not Started | 2021-10-27 | Not Started | 2021-10-14 | Not Started | 2022-01-26 | Not Started | 2022-02-24 | Not Started | 2023-01-13 | 2022-04-27 | 261 | On/ Ahead Schedule | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2022-06-24 | Not Started
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | E.5034794.01.02 | 5795152 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4013 | 0 | 4013 | 0.76004 | 0.76004 | 0 | 0 | 0.76004 | [5 empty] | 150000 | 0 | 150000 |  |  | 3595.2 | 0 | 146404.8 | On/Under Budget | Request 2021 Budget | 0 | 53735 | -53735 | 53735 | -53735 | 53807.4 | 20249.7 | -28022.6 | 48272.3 | 0 | 0 | 0 | 3595.3 | 72.6 | 0 | 0 | 0 | 706 | 4013 | 26898 | 20250 | 311 | 311 | 311 | 311 | 311 | 311 | 2021-06-18 | 157829 | BL-A | BL-A 35226622_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-06 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-09 | 2021-08-20 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-04-14 | -49 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | E.5034794.01.03 | 5795152 | ESTS | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 6072 | 0 | 6072 | 1.15 | 1.15 | 0 | 0 | 1.15 | [5 empty] | 150000 | 0 | 150000 |  |  | 1183.7 | 0 | 148816.3 | On/Under Budget | Request 2021 Budget | 0 | 61914 | -61914 | 61914 | -61914 | 62264.9 | 20296.8 | -38281.4 | 58578.2 | 0 | 0 | 0 | 1183.7 | 351.6 | 0 | 0 | 0 | 687 | 41 | 38737 | 20297 | 359 | 359 | 359 | 359 | 359 | 359 | 2021-06-18 | 157830 | BL-A | BL-A 35226623_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-20 | Not Started | 2021-08-23 | 2021-08-27 | Not Started | 2021-09-03 | Not Started | 2021-10-15 | Not Started | 2021-08-23 | 2021-08-23 | Not Started | 2021-08-24 | 2021-09-13 | Not Started | 2021-09-06 | 2021-09-17 | Not Started | 2021-11-09 | Not Started | 2021-11-09 | Not Started | 2021-11-22 | Not Started | 2021-11-09 | Not Started | 2022-02-21 | Not Started | 2022-03-22 | Not Started | 2022-02-24 | 2022-04-14 | -49 | Behind Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-13 | Not Started
35192683 | BR-05-15-W CLARK-5 PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 71061.9 | 0 | -71061.9 | OverRun | Project is not in the WP or in 2020 WP | 0 | 5059 | -5059 | 5059 | -5059 | 74050.8 | 414.2 | 0 | 414.2 | 0 | 0 | 68991.4 | 2070.5 | 0 | 0 | 468 | 402 | 402 | 399 | 399 | 414 | 429 | 429 | 429 | 429 | 429 | 429
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | E.5034609.01.01 | 5794206 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2904 | 0 | 2904 | 0.55 | 0 | 0.55 | 0 | 0.55 | 2516 | 0 | 0.47652 | 0 |  | 316666 | 0 | 316666 |  |  | 41448.2 | 0 | 275217.8 | On/Under Budget | Request 2021 Budget | 0 | 88917 | -88917 | 88917 | -88917 | 94759.8 | 23977.5 | -21072.8 | 45050.3 | 0 | 0 | 4345.2 | 37103.2 | 1498.4 | 0 | 11436 | 20605 | 7770 | 20409 | -2044 | 23978 | 4062 | 540 | 540 | 540 | 540 | 540 | 2021-06-18 | 157799 | BL-A | BL-A 35217270_CWSP - KONOCTI 1102 LR 965078 PH1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-10 | Not Started | 2021-08-11 | 2021-08-17 | Not Started | 2021-11-16 | Not Started | 2021-11-17 | Not Started | 2021-08-11 | 2021-08-11 | Not Started | 2021-08-12 | 2021-09-01 | Not Started | 2021-11-17 | 2021-11-30 | Not Started | 2021-12-10 | Not Started | 2021-12-10 | Not Started | 2021-12-23 | Not Started | 2021-12-10 | Not Started | 2022-03-24 | Not Started | 2022-04-22 | Not Started | 2022-07-01 | 2022-06-23 | 8 | On/ Ahead Schedule | Not Started | 2022-06-24 | 2022-07-07 | Not Started | 2022-08-22 | Not Started
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | E.5034610.01.01 | 5794205 | ESTS | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 8131 | 0 | 0 | 8131 | 1.54 | 0 | 1.54 | 0 | 1.54 | [5 empty] | 200000 | 0 | 200000 |  |  | 61512.4 | 0 | 138487.6 | On/Under Budget | Request 2021 Budget | 0 | 46439 | -46439 | 46439 | -46439 | 65539.6 | 160.5 | -2240.8 | 2401.3 | 0 | 0 | 18452.7 | 43059.7 | 648.1 | 0 | 31986 | -2611 | 1249 | 20490 | -5813 | 161 | 163 | 163 | 163 | 163 | 163 | 163 | 2021-06-18 | 157801 | BL-A | BL-A 35217271_CWSP - MIDDLETOWN 1103 LR 830 PH 1.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-12-10 | Not Started | 2021-12-13 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-12-13 | 2021-12-24 | Not Started | 2022-01-05 | Not Started | 2022-01-05 | Not Started | 2022-01-18 | Not Started | 2022-01-05 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-08 | 2022-07-19 | -11 | Behind Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-15 | Not Started
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | E.5034611.01.01 | 5794204 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | REDDING | North Valley Assets | 1584 | 0 | 0 | 1584 | 0.3 | 0 | 0.3 | 0 | 0.3 | [5 empty] | 150000 | 0 | 150000 |  |  | 37365.4 | 0 | 112634.6 | On/Under Budget | Budget Allocated | 500000 | 502688 | -2688 | 502688 | -2688 | 1068391.9 | 5495.4 | -7012.6 | 12508 | 0 | 0 | 2467.6 | 34897.8 | 563236.2 | 0 | 14932 | 7722 | 25049 | -16250 | 10458 | 5495 | 114 | 400114 | 54714 | 114 | 114 | 114 | 2021-06-18 | 157965 | BL-A_ | BL-A_35217272_SH - KESWICK 1101 LR 1586 PH 1.1_08W_Mar.2021 | 2021-03-23 | 2021-07-27 | Not Started | 2022-03-11 | 2022-03-17 | Not Started | 2022-03-10 | Not Started | 2022-04-07 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-07-27 | 2021-08-09 | Not Started | 2022-05-02 | Not Started | 2022-05-02 | Not Started | 2022-05-13 | Not Started | 2022-05-02 | Not Started | 2022-08-12 | Not Started | 2022-09-12 | Not Started | 2022-12-30 | 2022-10-28 | 63 | On/ Ahead Schedule | Not Started | 2022-10-31 | 2022-11-11 | Not Started | 2022-12-27 | Not Started
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | E.5034613.01.01 | 5794202 | ESTS | 08W | [6 empty] | 2021 |  | FRRB | SNCARLOS | Peninsula Assets | 11774 | 0 | 0 | 11774 | 2.2299 | 2.23 | 0 | 0 | 2.2299 | [5 empty] | 500000 | 0 | 500000 |  |  | 58174.1 | 28215.2 | 413610.7 | On/Under Budget | Budget Allocated | 7805000 | 7773207 | 31793 | 7773207 | 31793 | 7776375.7 | -81033.9 | 1181.8 | -82215.7 | 0 | 0 | 3168.7 | 55005.5 | 0 | 0 | 5554 | 9407 | 5227 | 23184 | 10453 | -81034 | 1298139 | 1301139 | 1301139 | 1300000 | 1300000 | 1300000 | 2021-04-16 |  |  |  |  | 2021-10-22 | Not Started | 2022-08-16 | 2022-08-22 | Not Started | 2022-08-15 | Not Started | 2022-09-12 | Not Started | 2021-10-25 | 2021-10-25 | Not Started | 2021-10-26 | 2021-11-15 | Not Started | 2022-08-16 | 2022-08-29 | Not Started | 2022-10-05 | Not Started | 2022-10-05 | Not Started | 2022-11-14 | Not Started | 2022-10-05 | Not Started | 2023-01-17 | Not Started | 2023-02-15 | Not Started | 2023-04-18 | 2023-04-18 | 0 | On/ Ahead Schedule | Not Started | 2023-04-19 | 2023-05-02 | Not Started | 2023-06-15 | Not Started
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | E.5034614.01.01 | 5794201 | ESTS | 08W | [6 empty] | 2021 |  | FRRB | SNCARLOS | Peninsula Assets | 15312 | 0 | 0 | 15312 | 2.9 | 2.9 | 0 | 0 | 2.9 | [5 empty] | 500000 | 0 | 500000 |  |  | 186736.9 | 69088.5 | 244174.6 | On/Under Budget | Budget Allocated | 10150000 | 10193235 | -43235 | 10193235 | -43235 | 10194738.3 | -92612.9 | 51300 | -143912.9 | 0 | 0 | 1503 | 185233.9 | 0 | 0 | 7021 | 10246 | 5055 | 141356 | -29743 | -92613 | 1601139 | 1601139 | 1601139 | 1600000 | 1850000 | 1898497 | 2021-04-16 |  |  |  |  | 2021-10-08 | Not Started | 2022-08-02 | 2022-08-08 | Not Started | 2022-08-01 | Not Started | 2022-08-29 | Not Started | 2021-10-11 | 2021-10-11 | Not Started | 2021-10-12 | 2021-11-01 | Not Started | 2022-08-02 | 2022-08-15 | Not Started | 2022-09-21 | Not Started | 2022-09-21 | Not Started | 2022-10-31 | Not Started | 2022-09-21 | Not Started | 2023-01-03 | Not Started | 2023-02-01 | Not Started | 2023-04-04 | 2023-04-04 | 0 | On/ Ahead Schedule | Not Started | 2023-04-05 | 2023-04-18 | Not Started | 2023-06-01 | Not Started
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | E.5034710.01.01 | 5794551 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | AUBURN | Sierra Assets | 13200 | 0 | 0 | 13200 | 2.5 | 0 | 2.5 | 0 | 2.5 | [5 empty] | 316666 | 0 | 316666 |  |  | 58395.9 | 0 | 258270.1 | On/Under Budget | Budget Allocated | 201100.86 | 245311 | -44210.14 | 245311 | -44210.14 | 7233033.5 | 25630 | -63693.9 | 89323.9 | 0 | 0 | 0 | 58395.8 | 6987721.9 | 0 | 6788 | 12048 | 1904 | 53166 | 48184 | 25630 | 48114 | 28774 | 3865 | 3882 | 3899 | 9058 | 2021-06-18 | 158187 | BL-A_ | BL-A_35219281_CWSP - MOUNTAIN QUARRIES 21016953 Ph 1.1_08W_Apr.2021 | 2021-03-31 | 2022-01-04 | Not Started | 2022-02-09 | 2022-02-15 | Not Started | 2022-02-08 | Not Started | 2022-03-08 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-01-26 | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-03-31 | Not Started | 2022-03-31 | Not Started | 2022-04-13 | Not Started | 2022-03-31 | Not Started | 2022-07-13 | Not Started | 2022-08-11 | Not Started | 2022-04-21 | 2022-10-12 | -174 | Behind Schedule | Not Started | 2022-10-13 | 2022-10-26 | Not Started | 2022-12-09 | Not Started
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 | E.5034707.01.01 | 5794545 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 14203.2 | 0 | 0 | 14203.2 | 2.69 | 0 | 2.69 | 0 | 2.69 | [5 empty] | 1 | -315500 | 315501 |  |  | 63665.2 | 0 | 251835.8 | On/Under Budget | Request 2021 Budget | 0 | 334363 | -334363 | 334363 | -334363 | 5623240.7 | 5949.7 | -10309.4 | 16259.1 | 0 | 0 | 799.7 | 62865.6 | 5288077.9 | 0 | 5966 | 23991 | 2489 | 69703 | -28973 | 5950 | 46396 | 50040 | 52704 | 60540 | 26170 | 19390 | 2021-06-18 | 158640 | BL-A | BL-A 35219276_CWSP - VACAVILLE 11046542 PH 1.1_08W- DD 210402 | 2021-04-05 | 2021-10-22 | Not Started | 2021-10-25 | 2021-10-29 | Not Started | 2022-04-22 | Not Started | 2022-04-25 | Not Started | 2021-10-25 | 2021-10-25 | Not Started | 2021-10-26 | 2021-11-15 | Not Started | 2021-10-18 | 2021-10-29 | Not Started | 2022-07-01 | Not Started | 2022-07-01 | Not Started | 2022-07-14 | Not Started | 2022-07-01 | Not Started | 2022-10-13 | Not Started | 2022-11-11 | Not Started | 2022-12-14 | 2023-01-12 | -29 | Behind Schedule | Not Started | 2023-01-13 | 2023-01-26 | Not Started | 2023-03-13 | Not Started
35219267 | CWSP - MARIPOSA 2102440236 PH1.1 | E.5034702.01.02 | 5794552 | ESTS | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 8817.6 | 0 | 8817.6 | 1.67 | 1.6701 | 0 | 0 | 1.67 | [5 empty] | 1 | 1 | 0 |  |  | 42687.3 | 0 | -42687.3 | OverRun | Request 2021 Budget | 0 | 31899 | -31899 | 31899 | -31899 | 31899.1 | 0 | 10788.2 | -10788.2 | 0 | 0 | 0 | 42687.3 | 0 | 0 | 5881 | 2586 | 12986 | 4108 | 6338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-06 | Not Started | 2021-08-13 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | 2021-08-27 | Not Started | 2021-08-30 | 2021-09-17 | Not Started | 2021-08-16 | 2021-08-27 | Not Started | 2021-09-21 | Not Started | 2021-09-21 | Not Started | 2021-09-21 | Not Started | 2021-09-21 | Not Started | 2021-11-08 | Not Started | 2021-11-09 | Not Started | 2022-01-14 | 2022-01-14 | 0 | On/ Ahead Schedule | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-03-15 | Not Started
35219269 | CWSP - VACA DIXON 110540092 PH 1.1 | E.5034704.01.01 | 5794542 | ESTS | 08W | [6 empty] | 2022 |  | SH | VACAVLLE | Sacramento Assets | 0 | 11299 | 0 | 11299 | 2.14 | 0 | 2.14 | 0 | 2.14 | [5 empty] | 950000 | 0 | 950000 |  |  | 27191.5 | 0 | 922808.5 | On/Under Budget | Request 2021 Budget | 0 | 26293 | -26293 | 26293 | -26293 | 26293.3 | 0 | 898.2 | -898.2 | 0 | 0 | 0 | 27191.4 | 0 | 0 | 3083 | 4752 | 17534 | 775 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-07-30 | Not Started | 2021-09-06 | 2021-09-10 | Not Started | 2021-09-03 | Not Started | 2021-10-01 | Not Started | 2021-08-02 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-09-06 | 2021-09-17 | Not Started | 2021-10-26 | Not Started | 2021-10-26 | Not Started | 2021-11-08 | Not Started | 2021-10-26 | Not Started | 2022-02-07 | Not Started | 2022-03-08 | Not Started | 2022-05-09 | 2022-05-09 | 0 | On/ Ahead Schedule | Not Started | 2022-05-10 | 2022-05-23 | Not Started | 2022-07-06 | Not Started
35219286 | CWSP - DESCHUTES 11049718 PH1.1 | E.5034713.01.01 | 5794554 | ESTS | 08W | [6 empty] | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 15365 | 0 | 15365 | 2.91 | 2.91 | 0 | 0 | 2.91 | [5 empty] | 475000 | 0 | 475000 |  |  | 35149.6 | 0 | 439850.4 | On/Under Budget | Budget Allocated | 5630850 | 5769056 | -138206 | 5769056 | -138206 | 5787177.1 | 50112.9 | 284.1 | 49828.8 | 0 | 0 | 0 | 35149.7 | 18121.5 | 0 | 8315 | 9352 | 5628 | 4161 | 7411 | 50113 | 1866377 | 1877536 | 1888696 | 34312 | 17156 | 0 | 2021-06-18 | 160446 | BL-A- | BL-A-35219286_CWSP - DESCHUTES 11049718 PH1.1_08W_May.2021 | 2021-05-06 | 2021-07-12 | Not Started | 2021-08-02 | 2021-08-06 | Not Started | 2021-07-30 | Not Started | 2021-09-06 | Not Started | 2021-07-13 | 2021-07-13 | Not Started | 2021-07-14 | 2021-07-14 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-09-29 | Not Started | 2021-12-21 | Not Started | 2021-12-30 | Not Started | 2022-02-25 | 2022-02-10 | 15 | On/ Ahead Schedule | Not Started | 2022-02-11 | 2022-02-24 | Not Started | 2022-04-11 | Not Started
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | E.5034715.01.01 | 5543321 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 733 | 0 | 0 | 733 | 0.13883 | 0 | 0.13883 | 0 | 0.13883 | [5 empty] | 500000 | 0 | 500000 |  |  | 25067.2 | 0 | 474932.8 | On/Under Budget | Budget Allocated | 105000 | 117060 | -12060 | 117060 | -12060 | 843643.4 | 28804.3 | -4548.7 | 33353 | 0 | 0 | 0 | 25067.2 | 726583.5 | 0 | 94 | 7128 | 989 | 4540 | 16866 | 28804 | 45910 | 2546 | 2546 | 2546 | 2546 | 2546 | 2021-05-07 |  |  |  |  | 2022-08-05 | Not Started | 2022-09-12 | 2022-09-16 | Not Started | 2022-09-09 | Not Started | 2022-10-07 | Not Started | 2022-08-08 | 2022-08-08 | Not Started | 2022-08-09 | 2022-08-29 | Not Started | 2022-09-12 | 2022-09-23 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2023-02-13 | Not Started | 2023-03-14 | Not Started | 2023-05-15 | 2023-05-15 | 0 | On/ Ahead Schedule | Not Started | 2023-05-16 | 2023-05-29 | Not Started | 2023-07-12 | Not Started
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | E.5034715.01.02 | 5543321 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 1267.2 | 0 | 0 | 1267.2 | 0.24 | 0 | 0.24 | 0 | 0.24 | [5 empty] | 500000 | 0 | 500000 |  |  | 16179.7 | 0 | 483820.3 | On/Under Budget | Budget Allocated | 177000 | 188948 | -11948 | 188948 | -11948 | 788801.3 | 26892.8 | -11776.7 | 38669.5 | 0 | 0 | 0 | 16179.7 | 599853.5 | 0 | 457 | 3448 | 1820 | 5275 | 16957 | 26893 | 85930 | 25369 | 2546 | 10451 | 4850 | 4953 | 2021-06-18 | 158826 | BL-A_ | BL-A_35219543_PSPS - W.MAIN ST/RES ST-PLACVIL1112Ph1.1_08W_Apr.2021 | 2021-04-07 | 2021-10-07 | Not Started | 2021-10-12 | 2021-11-08 | Not Started | 2021-10-11 | Not Started | 2021-12-06 | Not Started | 2021-12-07 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-11 | Not Started | 2021-10-12 | 2021-11-15 | Not Started | 2022-01-13 | Not Started | 2022-01-13 | Not Started | 2022-01-26 | Not Started | 2022-01-13 | Not Started | 2022-04-27 | Not Started | 2022-05-26 | Not Started | 2022-04-19 | 2022-07-27 | -99 | Behind Schedule | Not Started | 2022-07-28 | 2022-08-10 | Not Started | 2022-09-23 | Not Started
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C | E.5014534.03 | 5786053 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 2875 | 0 | 2875 | 0.54451 | 0 | 0 | 0 | 0.54451 | [5 empty] | 1 | -99999 | 100000 |  |  | 5999.9 | 0 | 94000.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 336 | -336 | 336 | -336 | 308077.3 | 35.8 | 0 | 35.8 | 0 | 327.6 | 5426.7 | 245.7 | 301987.3 | 0 | 110 | 34 | 34 | 34 | 34 | 36 | 36 | 18 | 0 | 0 | 0 | 0
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | E.5014727.06 | 5786005 | ESTS | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 9652 | 0 | 9652 | 1.828 | 0 | 0 | 0 | 1.828 | [5 empty] | 1 | -299999 | 300000 |  |  | 89432.1 | 0 | 210567.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 74379 | -74379 | 74379 | -74379 | 1874077.5 | 102.8 | 0 | 102.8 | 0 | 705.8 | 14503.2 | 74223.2 | 1784489.3 | 0 | 106535 | -33824 | 506 | 503 | 503 | 103 | 53 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154939 | BL-B | BL-B 35112976_CWSP - WEST POINT 1101 -LR 13444- PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-23 | Not Started | 2021-11-25 | 2022-01-05 | Not Started | 2021-12-27 | Not Started | 2022-01-05 | Not Started | 2022-01-06 | 2022-01-06 | Not Started | 2022-01-07 | 2022-02-03 | Not Started | 2021-12-29 | 2022-01-11 | Not Started | 2022-03-10 | Not Started |  |  |  |  | 2022-03-10 | Not Started | 2022-04-28 | Not Started | 2022-04-28 | Not Started | 2022-05-30 | 2022-05-30 | 0 | On/ Ahead Schedule | Not Started | 2022-05-06 | 2022-05-19 | Not Started | 2022-07-20 | Not Started
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | E.5014727.02 | 5786001 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6650 | 0 | 6650 | 1.2595 | 0 | 0 | 0 | 1.2595 | [5 empty] | 1 | -299999 | 300000 |  |  | 77794 | 0 | 222206 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 49738 | -49738 | 49738 | -49738 | 1904928.1 | 0 | 0 | 0 | 0 | 562.7 | 27493.6 | 49737.8 | 1827134.1 | 0 | 68833 | -20410 | 440 | 437 | 437 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154935 | BL-B | BL-B 35112972_CWSP - WEST POINT 1101 -LR 13444- PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-14 | Not Started | 2021-12-15 | 2022-01-11 | Not Started | 2022-01-24 | Not Started | 2022-01-25 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-01-26 | Not Started | 2022-01-25 | 2022-01-25 | Not Started | 2022-03-16 | Not Started |  |  |  |  | 2022-03-16 | Not Started | 2022-05-11 | Not Started | 2022-05-11 | Not Started | 2022-06-10 | 2022-06-10 | 0 | On/ Ahead Schedule | Not Started | 2022-05-19 | 2022-06-01 | Not Started | 2022-08-02 | Not Started
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 | E.5014728.02 | 5786012 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11177.9 | 0 | 11177.9 | 2.117 | 0 | 0 | 0 | 2.117 | [5 empty] | 1 | -249999 | 250000 |  |  | 25690.4 | 0 | 224309.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 14133 | -14133 | 14133 | -14133 | 3505858.1 | 461.1 | 0 | 461.1 | 0 | 580.3 | 15603.7 | 9506.3 | 3475540.6 | 0 | 13913 | -4841 | 145 | 144 | 144 | 461 | 1579 | 2587 | 0 | 0 | 0 | 0 | 2021-06-18 | 154942 | BL-B | BL-B 35113993_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-05-02 | Not Started | 2022-05-03 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-04-19 | 2022-04-19 | Not Started | 2022-06-09 | Not Started |  |  |  |  | 2022-06-09 | Not Started | 2022-08-19 | Not Started | 2022-08-19 | Not Started | 2022-09-20 | 2022-09-20 | 0 | On/ Ahead Schedule | Not Started | 2022-08-29 | 2022-09-09 | Not Started | 2022-11-10 | Not Started
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | E.5014723.05 | 5785958 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11880 | 0 | 11880 | 2.25 | 0 | 0 | 0 | 2.25 | [5 empty] | 250000 | 0 | 250000 |  |  | 237061 | 0 | 12939 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16110 | -16110 | 16110 | -16110 | 4071845.2 | 163.3 | 0 | 163.3 | 0 | 1031.4 | 221098.4 | 14931.2 | 3833605.1 | 0 | 1710 | 1376 | 3919 | 6746 | 1181 | 163 | 169 | 169 | 169 | 169 | 169 | 169 | 2021-06-18 | 160673 | BL-A1 | BL-A1 35115049_CWSP - MIWUK 1701 - LR 10600 PH 1.5_08W - DD 210507 | 2021-05-13 | 2022-01-10 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2020-12-07 | Completed | 2022-01-12 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-09 | Not Started | 2022-01-12 | 2022-01-25 | Not Started | 2022-02-11 | Not Started |  |  |  |  | 2022-02-11 | Not Started | 2022-04-18 | Not Started | 2022-05-09 | Not Started | 2022-06-08 | 2022-06-08 | 0 | On/ Ahead Schedule | Not Started | 2022-06-09 | 2022-06-22 | Not Started | 2022-07-29 | Not Started
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | E.5014728.08 | 5786134 | ESTS | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 8940 | 0 | 8940 | 1.6932 | 0 | 0 | 0 | 1.6932 | [5 empty] | 1 | -249999 | 250000 |  |  | 108385.7 | 0 | 141614.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 85739 | -85739 | 85739 | -85739 | 1862515.4 | 30.9 | 0 | 30.9 | 0 | 0 | 22678.1 | 85707.6 | 1754098.8 | 0 | 137181 | -53304 | 613 | 609 | 609 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154949 | BL-B | BL-B 35113999_CWSP-WEST POINT 1101-OCB&LR12256-PH1.8_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-12-07 | Not Started | 2021-12-08 | 2022-01-04 | Not Started | 2022-01-24 | Not Started | 2022-01-25 | Not Started | 2022-01-05 | 2022-01-05 | Not Started | 2022-01-06 | 2022-02-02 | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-09 | Not Started |  |  |  |  | 2022-03-09 | Not Started | 2022-05-05 | Not Started | 2022-05-05 | Not Started | 2022-06-06 | 2022-06-06 | 0 | On/ Ahead Schedule | Not Started | 2022-05-13 | 2022-05-26 | Not Started | 2022-07-27 | Not Started
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | E.5014733.06 | 5785970 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9970 | 0 | 9970 | 1.8883 | 0 | 0 | 0 | 1.8883 | [5 empty] | 500000 | 0 | 500000 |  |  | 195909.2 | 0 | 304090.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 33670 | -33670 | 33670 | -33670 | 1884413.4 | 173.1 | 0 | 173.1 | 0 | 202.9 | 162479 | 33227.3 | 1688062 | 0 | 88299 | -58401 | 1107 | 1123 | 1099 | 173 | 179 | 90 | 0 | 0 | 0 | 0 | 2021-06-18 | 160678 | BL-A1 | BL-A1 35116389_CWSP - MIWUK 1701 - LR 8060 - PH 1.6_08W - DD 210507 | 2021-05-13 | 2022-01-05 | Not Started | 2022-01-07 | 2022-04-05 | Not Started | 2022-01-04 | Not Started | 2022-04-05 | Not Started | 2022-04-06 | 2022-04-06 | Not Started | 2022-04-07 | 2022-05-04 | Not Started | 2022-01-05 | 2022-01-18 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-07-29 | Not Started | 2022-08-19 | Not Started | 2022-09-20 | 2022-09-20 | 0 | On/ Ahead Schedule | Not Started | 2022-09-21 | 2022-10-04 | Not Started | 2022-11-10 | Not Started
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | E.5014722.06 | 5785933 | ESTS | 08W | [6 empty] | 2022 |  | SH | SONORA | Yosemite Assets | 0 | 9980 | 0 | 9980 | 1.8902 | 0 | 0 | 0 | 1.8902 | [5 empty] | 275000 | 0 | 275000 |  |  | 148948.1 | 0 | 126051.9 | On/Under Budget | Budget Allocated | 1392.3 | 701 | 691.3 | 701 | 691.3 | 3717583.5 | 213.6 | 49.2 | 164.4 | 0 | 106.8 | 148415.9 | 425.5 | 3568360.3 | 0 | 55748 | -57882 | 841 | 835 | 835 | 214 | 111 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145959 | BL-A | BL-A 35116440_CWSP - MIWUK 1702 - LR 8090 - PH 1.6_08W - MAR 2022 | 2020-07-26 | 2022-01-05 | Not Started | 2023-01-13 | 2023-02-02 | Not Started | 2022-02-15 | Not Started | 2023-02-02 | Not Started | 2023-02-03 | 2023-02-23 | Not Started | 2023-02-24 | 2023-03-02 | Not Started | 2022-02-16 | 2022-02-22 | Not Started | 2023-05-16 | Not Started |  |  |  |  | 2023-05-16 | Not Started | 2023-07-14 | Not Started | 2023-07-24 | Not Started | 2022-03-04 | 2023-08-23 | -537 | Behind Schedule | Not Started | 2023-08-24 | 2023-08-25 | Not Started | 2023-08-29 | Not Started
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 | E.5014776.02 | 5785981 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12015 | 0 | 12015 | 2.2756 | 0 | 0 | 0 | 2.2756 | [5 empty] | 250000 | 0 | 250000 |  |  | 166755.8 | 0 | 83244.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 119881 | -119881 | 119881 | -119881 | 6446858.4 | 203.9 | 0 | 203.9 | 0 | 426.4 | 47921.2 | 118408.3 | 6278630.1 | 0 | 113951 | 1634 | 946 | 939 | 939 | 204 | 211 | 211 | 211 | 211 | 211 | 211 | 2021-06-18 | 160682 | BL-A2 | BL-A2 35116441_CWSP - MIWUK 1702 - LR 38218 - PH 1.2_08W - DD 210507 | 2021-05-13 | 2020-12-03 | Completed | 2021-12-13 | 2021-12-24 | Not Started | 2021-12-10 | Not Started | 2021-12-24 | Not Started | 2021-12-27 | 2021-12-27 | Not Started | 2021-12-28 | 2021-12-29 | Not Started | 2022-01-11 | 2022-01-12 | Not Started | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started | 2022-03-04 | Not Started | 2022-03-18 | Not Started | 2022-07-21 | 2022-07-21 | 0 | On/ Ahead Schedule | Not Started | 2022-07-22 | 2022-08-04 | Not Started | 2022-09-12 | Not Started
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | E.5014722.04 | 5785931 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9730 | 0 | 9730 | 1.8428 | 0 | 0 | 0 | 1.8428 | [5 empty] | 83333 | -275000 | 358333 |  |  | 224215.6 | 0 | 134117.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 185229 | -185229 | 185229 | -185229 | 4525404.3 | 135.4 | 0 | 135.4 | 0 | 206.2 | 39758.5 | 184250.8 | 4300211 | 0 | 284860 | -104864 | 1736 | 1260 | 1260 | 135 | 140 | 140 | 140 | 140 | 140 | 140 | 2021-06-18 | 160667 | BL-B2 | BL-B2 35116398_CWSP - MIWUK 1702 - LR 8090 - PH 1.4_08W - DD 210507 | 2021-05-13 | 2022-03-02 | Not Started | 2023-02-13 | 2023-02-21 | Not Started | 2022-02-02 | Not Started | 2023-02-21 | Not Started | 2023-02-22 | 2023-02-22 | Not Started | 2023-02-23 | 2023-02-24 | Not Started | 2022-02-02 | 2022-02-03 | Not Started | 2023-03-30 | Not Started |  |  |  |  | 2023-03-30 | Not Started | 2023-06-12 | Not Started | 2023-06-15 | Not Started | 2023-07-13 | 2023-07-13 | 0 | On/ Ahead Schedule | Not Started | 2023-07-14 | 2023-07-14 | Not Started | 2023-09-07 | Not Started
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | E.5015236.02 | 5786018 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 9566 | 0 | 9566 | 1.8117 | 0 | 0 | 0 | 1.8117 | [5 empty] | 1 | -249999 | 250000 |  |  | 103656.5 | 0 | 146343.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 44408 | -44408 | 44408 | -44408 | 2914876.2 | 0 | 0 | 0 | 0 | 0 | 59248.7 | 44407.9 | 2811219.7 | 0 | 21636 | 13113 | 8491 | 584 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154966 | BL-0 | BL-0 35115847_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-14 | Not Started | 2022-01-17 | 2022-02-11 | Not Started | 2022-04-07 | Not Started | 2022-04-08 | Not Started | 2022-02-14 | 2022-02-14 | Not Started | 2022-02-15 | 2022-03-14 | Not Started | 2022-04-11 | 2022-04-22 | Not Started | 2022-06-28 | Not Started |  |  |  |  | 2022-06-28 | Not Started | 2022-08-24 | Not Started | 2022-09-07 | Not Started | 2022-10-07 | 2022-10-07 | 0 | On/ Ahead Schedule | Not Started | 2022-10-10 | 2022-10-21 | Not Started | 2022-11-29 | Not Started
35117986 | BR-02-08/09 W (E) OAK WAY PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118438 | BR-11-01-W (E) FOSTER RD, PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 3470.8 | 0 | -3470.8 | OverRun | Project is not in the WP or in 2020 WP | 0 | 88 | -88 | 88 | -88 | 3102.9 | 0 | 367.9 | -367.9 | 0 | 2908.1 | 106.4 | 456.3 | 0 | 0 | 18 | 18 | 18 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118502 | BR-06-01-W (E) DELIA WAY, PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 87510.3 | 0 | -87510.3 | OverRun | Project is not in the WP or in 2020 WP | 0 | 2493 | -2493 | 2493 | -2493 | 87510.3 | 0 | 0 | 0 | 0 | 399.3 | 84617.8 | 2493.2 | 0 | 0 | 519 | 495 | 495 | 492 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118504 | BR-06-02-W (E) COPELAND RD PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 | E.5014724.01 | 5786327 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8402 | 0 | 8402 | 1.5913 | 0 | 0 | 0 | 1.5913 | [5 empty] | 305556 | 0 | 305556 |  |  | 57927.9 | 0 | 247628.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 43469 | -43469 | 43469 | -43469 | 89996.7 | 48.9 | 0 | 48.9 | 0 | 4246.6 | 10562.8 | 43118.4 | 9479.4 | 22238.8 | 71319 | -29179 | 328 | 325 | 325 | 49 | 50 | 50 | 50 | 50 | 50 | 50 | 2021-06-18 |  |  |  |  | 2022-03-04 | Not Started | 2022-03-08 | 2022-03-21 | Not Started | 2022-03-10 | Not Started | 2022-04-07 | Not Started | 2022-03-22 | 2022-03-22 | Not Started | 2022-03-23 | 2022-06-14 | Not Started | 2022-03-07 | 2022-03-18 | Not Started | 2022-09-05 | Not Started |  |  |  |  | 2022-09-05 | Not Started | 2022-11-24 | Not Started | 2022-12-23 | Not Started | 2023-01-24 | 2023-01-24 | 0 | On/ Ahead Schedule | Not Started | 2023-01-25 | 2023-02-07 | Not Started | 2023-03-16 | Not Started
35117398 | BR-01-12-W (E) MYRTLE WAY, PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 9194 | 0 | -9194 | OverRun | Project is not in the WP or in 2020 WP | 0 | 262 | -262 | 262 | -262 | 9194 | 0 | 0 | 0 | 0 | 8516.3 | 415.7 | 262 | 0 | 0 | 55 | 52 | 52 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35117540 | BR-02-01-W (E) CLARK RD & SAN JOSE PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -2497421 | 2497422 |  |  | 0 | 0 | 2497422 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 102 | -102 | 102 | -102 | 101.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 1
35118700 | BR-10-01-W (E) STARLIGHT CT PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 | E.5014755.06 | 5786743 | ESTS | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6429 | 0 | 6429 | 1.2176 | 0 | 0 | 0 | 1.2176 | [5 empty] | 271429 | 0 | 271429 |  |  | 47872.4 | 0 | 223556.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 37555 | -37555 | 37555 | -37555 | 66499.7 | 13.7 | 0 | 13.7 | 0 | 0 | 10416.1 | 37456.3 | 18469 | 59.3 | 36374 | 272 | 272 | 270 | 270 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 2021-06-18 | 160788 | BL-A_ | BL-A_35129647_CWSP - ORO FINO 1101 - LR2022 PH 2.6_08W_May.2021 | 2021-05-17 | 2022-10-20 | Not Started | 2022-10-24 | 2022-10-25 | Not Started | 2021-09-09 | Not Started | 2022-12-01 | Not Started | 2022-10-26 | 2022-10-26 | Not Started | 2022-10-27 | 2022-10-28 | Not Started | 2021-06-22 | 2021-06-25 | Not Started | 2022-12-13 | Not Started |  |  |  |  | 2022-12-13 | Not Started | 2023-01-06 | Not Started | 2023-01-24 | Not Started | 2023-04-18 | 2023-04-18 | 0 | On/ Ahead Schedule | Not Started | 2023-04-19 | 2023-05-02 | Not Started | 2023-06-08 | Not Started
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | E.5015030.02 | 5786744 | ESTS | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6113 | 0 | 6113 | 1.1578 | 0 | 0 | 0 | 1.1578 | [5 empty] | 250000 | 0 | 250000 |  |  | 68134.6 | 0 | 181865.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 55137 | -55137 | 55137 | -55137 | 96510.6 | 12.9 | 0 | 12.9 | 0 | 0 | 13092 | 55042.6 | 28281.3 | 0 | 87286 | -33394 | 385 | 383 | 383 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 2021-06-18 | 155009 | BL-A | BL-A 35129648_CWSP - ORO FINO 1101 - LR2022 PH 3.2._08W - Jan. 2021 | 2021-01-25 | 2021-12-29 | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2021-07-15 | Not Started | 2022-02-09 | Not Started | 2022-01-14 | 2022-01-14 | Not Started | 2022-01-17 | 2022-02-04 | Not Started | 2021-07-12 | 2021-07-16 | Not Started | 2022-03-21 | Not Started |  |  |  |  | 2022-03-21 | Not Started | 2022-06-07 | Not Started | 2022-07-06 | Not Started | 2022-08-05 | 2022-08-05 | 0 | On/ Ahead Schedule | Not Started | 2022-08-08 | 2022-08-19 | Not Started | 2022-09-27 | Not Started
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | E.5014724.09 | 5786782 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 7516 | 0 | 7516 | 1.4235 | 0 | 0 | 0 | 1.4235 | [5 empty] | 250000 | 0 | 250000 |  |  | 53818.5 | 0 | 196181.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 44770 | -44770 | 44770 | -44770 | 84438.5 | 35 | 122.9 | -87.9 | 0 | 0 | 9177.1 | 44641.4 | 30185.2 | 306.5 | 73594 | -29982 | 304 | 302 | 302 | 35 | 36 | 36 | 36 | 36 | 36 | 36 | 2021-06-18 |  |  |  |  | 2022-06-16 | Not Started | 2022-06-20 | 2022-07-01 | Not Started | 2022-08-11 | Not Started | 2022-08-12 | Not Started | 2022-07-04 | 2022-07-04 | Not Started | 2022-07-05 | 2022-11-07 | Not Started | 2022-06-10 | 2022-06-23 | Not Started | 2022-12-16 | Not Started |  |  |  |  | 2022-12-16 | Not Started | 2023-03-07 | Not Started | 2023-04-05 | Not Started | 2023-05-03 | 2023-05-03 | 0 | On/ Ahead Schedule | Not Started | 2023-05-04 | 2023-05-17 | Not Started | 2023-06-23 | Not Started
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | E.5015531.02 | 5786480 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 12455 | 1245 | 0 | 13700 | 2.5947 | 0 | 0 | 0 | 2.5947 | [5 empty] | 500000 | 0 | 500000 |  |  | 181379.7 | 0 | 318620.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 46008 | -46008 | 46008 | -46008 | 218714.1 | 1421.5 | 132 | 1289.5 | 0 | 20886.7 | 123586.8 | 36906.2 | 28232.5 | 0 | 32554 | 1026 | 1026 | 1018 | 1151 | 1422 | 1438 | 1444 | 1449 | 1415 | 1162 | 905
35118517 | BR-07-05-W (E) FLICKER LN, PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -7388299 | 7388300 |  |  | 4767931.5 | 0 | 2620368.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1115628 | -1115628 | 1115628 | -1115628 | 4763233.1 | -4698.4 | 0 | -4698.4 | 0 | 23.9 | 3647580.9 | 1120326.8 | 0 | 0 | 106054 | 343498 | 210205 | 305853 | 154717 | -4698 | 0 | 0 | 0 | 0 | 0 | 0
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | E.5014720.02 | 5786763 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8778 | 0 | 8778 | 1.6625 | 0 | 0 | 0 | 1.6625 | [5 empty] | 100000 | 0 | 100000 |  |  | 55540.2 | 0 | 44459.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9682 | -9682 | 9682 | -9682 | 87378 | 12.6 | 0 | 12.6 | 0 | 235.3 | 45714.6 | 9590.2 | 31745.8 | 0 | -8434 | 18307 | -909 | 313 | 313 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 2021-06-18 | 159214 | BL-A_ | BL-A_35129308_CWSP - ORO FINO 1102 - LR2560 PH 2.2_08W_Apr.2021 | 2021-04-14 | 2022-05-13 | Not Started | 2022-05-16 | 2022-05-27 | Not Started | 2022-07-28 | Not Started | 2022-07-29 | Not Started | 2022-05-30 | 2022-05-30 | Not Started | 2022-05-31 | 2022-06-06 | Not Started | 2022-05-13 | 2022-06-23 | Not Started | 2022-08-09 | Not Started |  |  |  |  | 2022-08-09 | Not Started | 2022-10-24 | Not Started | 2022-11-21 | Not Started | 2023-01-06 | 2023-01-20 | -14 | Behind Schedule | Not Started | 2023-01-23 | 2023-02-03 | Not Started | 2023-03-14 | Not Started
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | E.5015549.04 | 5789700 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 6494 | 0 | 6494 | 1.2299 | 0 | 0 | 0 | 1.2299 | [5 empty] | 250000 | 0 | 250000 |  |  | 45792.6 | 0 | 204207.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 38698 | -38698 | 38698 | -38698 | 2092035.3 | 18.9 | 0 | 18.9 | 0 | 0 | 7182.3 | 38610.3 | 2046155.3 | 0 | 37473 | 362 | 260 | 258 | 258 | 19 | 20 | 20 | 20 | 10 | 0 | 0
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | E.5015549.05 | 5789701 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 6312 | 0 | 6312 | 1.1955 | 0 | 0 | 0 | 1.1955 | [5 empty] | 250000 | 0 | 250000 |  |  | 45607 | 0 | 204393 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 24970 | -24970 | 24970 | -24970 | 2332120.8 | 18.9 | 0 | 18.9 | 0 | 0 | 20744.4 | 24862.6 | 2286406.7 | 0 | 23832 | 259 | 259 | 257 | 257 | 19 | 20 | 20 | 20 | 20 | 10 | 0
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | E.5015549.06 | 5789702 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 2376 | 7022 | 0 | 9398 | 1.7799 | 0 | 0 | 0 | 1.7799 | [5 empty] | 250000 | 0 | 250000 |  |  | 64616.4 | 0 | 185383.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 57635 | -57635 | 57635 | -57635 | 3568539 | 20.8 | 0 | 20.8 | 0 | 0 | 7099.3 | 57517.2 | 3503804.7 | 0 | 52742 | 12992 | -8945 | 364 | 364 | 21 | 22 | 22 | 22 | 22 | 11 | 0
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | E.5015549.07 | 5789703 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 4646 | 686 | 0 | 5332 | 1.0098 | 0 | 0 | 0 | 1.0098 | [5 empty] | 250000 | 0 | 250000 |  |  | 72417.6 | 0 | 177582.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 63918 | -63918 | 63918 | -63918 | 1990505.2 | 23.2 | 0 | 23.2 | 0 | 0 | 8631.3 | 63786.3 | 1917956.1 | 0 | 58733 | 13035 | -8798 | 408 | 408 | 23 | 24 | 24 | 24 | 24 | 12 | 0
35134806 | BR-03-14-W (E) PENTZ RD, PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | 5530166 | ESTS | 08W | [6 empty] | Not in the WP | 2022 |  | SNLUISOB | Los Padres Assets | 0 | 3100 | 0 | 3100 | 0.58712 | 0 | 0 | 0 | 0.58712 | [5 empty] | 150000 | 0 | 150000 |  |  | 123940.1 | 0 | 26059.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15272 | -15272 | 15272 | -15272 | 2283272.2 | 1443.9 | 0 | 1443.9 | 22865.3 | 62935.5 | 30842 | 5164.9 | 2149224.6 | 0 | 2075 | 1380 | 457 | 800 | 454 | 1444 | 1444 | 1444 | 1444 | 1444 | 1444 | 1444 | 2021-06-18 | 161145 | BL-B: | BL-B: 31291639_FH 1101 O'CONNOR WY RECOND 12 SPANS, SLO - May 21 | 2021-05-28 | 2022-11-22 | Not Started |  |  | Not Started |  |  | 2023-01-31 | Not Started | 2023-02-01 | 2023-02-01 | Not Started |  |  |  | 2022-12-28 | 2023-01-17 | Not Started | 2023-02-09 | Not Started |  |  |  |  | 2023-02-09 | Not Started |  |  | 2023-03-03 | Not Started | 2023-03-01 | 2023-03-24 | -23 | Behind Schedule | Not Started | 2023-03-24 | 2023-04-07 | Not Started | 2023-08-29 | Not Started
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 | E.5014535.01 | 5780842 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 3643 | 0 | 0 | 3643 | 0.68996 | 0 | 0 | 0 | 0.68996 | [5 empty] | 10000 | -50000 | 60000 |  |  | 45931.8 | 0 | 14068.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1384 | -1384 | 1384 | -1384 | 3500884.4 | 0 | 0 | 0 | 19599.1 | 16376 | 8573.2 | 1383.5 | 3454952.6 | 0 | 348 | 260 | 260 | 258 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31540451 | DIAM.SPRINGS1105-LR 2102-TLINE SUBORDER |  | 5530173 | ESTS | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | [14 empty] | 100000 | 100000 | 0 |  |  | 8149.4 | 0 | -8149.4 | OverRun | Project is not in the WP or in 2020 WP | 0 | 4186 | -4186 | 4186 | -4186 | 4186.4 | 0 | 3963 | -3963 | 0 | 0 | 0 | 8149.4 | 0 | 0 | 0 | 0 | 0 | 0 | 4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | 5530173 | ESTS | 08W | [6 empty] | 2021 | 2025 | SH | AUBURN | Sierra Assets | 0 | 8553.6 | 0 | 8553.6 | 1.62 | 0 | 1.6201 | 0 | 1.62 | [5 empty] | 100000 | 0 | 100000 |  |  | 93855.3 | 0 | 6144.7 | On/Under Budget | Request 2021 Budget | 0 | 1471509 | -1471509 | 1471509 | -1471509 | 1518616.3 | 7122.6 | 2337.3 | 4785.3 | 6886.9 | 8874.5 | 31345.8 | 46748.2 | 0 | 0 | 10031 | 2328 | -518 | 4444 | 28126 | 7123 | 209440 | 471442 | 571693 | 160287 | 4743 | 2371 | 2021-06-18 | 160462 | BL-1_ | BL-1_35026643_CWSP - Diamond Springs 1105_08W_May.2021 | 2021-05-06 | 2022-09-08 | Not Started | 2022-09-09 | 2022-09-22 | Not Started | 2022-09-16 | Not Started | 2022-09-22 | Not Started | 2022-10-07 | 2022-10-07 | Not Started |  |  |  | 2022-09-22 | 2022-10-05 | Not Started | 2022-10-11 | Not Started |  |  |  |  | 2022-10-11 | Not Started |  |  | 2022-11-29 | Not Started | 2022-12-30 | 2023-01-25 | -26 | Behind Schedule | Not Started | 2023-01-26 | 2023-02-08 | Not Started | 2023-03-17 | Not Started
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 | E.5014728.01 | 5784647 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11665.4 | 0 | 11665.4 | 2.2094 | 0 | 0 | 0 | 2.2094 | [5 empty] | 40000 | -710000 | 750000 |  |  | 58428 | 0 | 691572 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 24597 | -24597 | 24597 | -24597 | 3446326.2 | 219.5 | 0 | 219.5 | 3457 | 16449.9 | 15167.5 | 23353.6 | 3386654.4 | 0 | 38572 | -16205 | 331 | 328 | 328 | 220 | 228 | 228 | 228 | 228 | 114 | 0 | 2021-06-18 | 154941 | BL-B | BL-B 35043421_CWSP - WEST POINT 1101-OCB&LR12256-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2022-01-10 | Not Started | 2022-01-11 | 2022-01-31 | Not Started | 2022-05-12 | Not Started | 2022-05-13 | Not Started | 2022-06-28 | 2022-07-04 | Not Started | 2022-07-05 | 2022-08-01 | Not Started | 2022-05-13 | 2022-05-13 | Not Started | 2022-08-02 | Not Started |  |  |  |  | 2022-08-02 | Not Started |  |  | 2022-10-24 | Not Started | 2022-11-23 | 2022-11-23 | 0 | On/ Ahead Schedule | Not Started | 2022-11-24 | 2022-12-07 | Not Started | 2023-01-27 | Not Started
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | E.5014727.01 | 5785229 | ESTS | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 11037 | 0 | 11037 | 2.0903 | 0 | 0 | 0 | 2.0903 | [5 empty] | 500000 | 200000 | 300000 |  |  | 141051.2 | 0 | 158948.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 97089 | -97089 | 97089 | -97089 | 2094924.4 | 193.8 | 0 | 193.8 | 1645.5 | 11906.6 | 30704.6 | 96794.5 | 1953578.9 | 0 | 131709 | -37299 | 799 | 793 | 793 | 194 | 101 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154934 | BL-B | BL-B 35043422_CWSP - WEST POINT 1101 -LR 13444- PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2021-11-29 | Not Started | 2021-12-01 | 2022-01-11 | Not Started | 2022-01-07 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-09 | Not Started | 2022-01-31 | 2022-02-11 | Not Started | 2022-03-03 | Not Started |  |  |  |  | 2022-03-03 | Not Started |  |  | 2022-04-15 | Not Started | 2022-05-17 | 2022-05-17 | 0 | On/ Ahead Schedule | Not Started | 2022-05-18 | 2022-05-31 | Not Started | 2022-07-07 | Not Started
35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 |  | 5793703 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ |  | 0 | 38438.4 | 0 | 38438.4 | 7.28 | 0 | 0 | 0 | 7.28 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | 5530173 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 3309 | 0 | 0 | 3309 | 0.6267 | 0 | 0 | 0 | 0.6267 | [5 empty] | 245000 | 0 | 245000 |  |  | 123618.6 | 12258.7 | 109122.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 20360 | -20360 | 20360 | -20360 | 5898128.6 | 253 | -6827.2 | 7080.2 | 228.6 | 12223.7 | 99460.4 | 11705.9 | 5765856 | 0 | 3833 | 1702 | 1842 | 2402 | 8754 | 253 | 262 | 262 | 262 | 262 | 262 | 262 | 2021-06-11 |  |  |  |  | 2021-06-11 | Not Started | 2021-12-03 | 2021-12-09 | Not Started | 2021-08-09 | Not Started | 2021-12-30 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-24 | Not Started | 2021-12-03 | 2021-12-23 | Not Started | 2022-01-24 | Not Started |  |  |  |  | 2022-01-24 | Not Started | 2022-06-03 | Not Started | 2022-07-04 | Not Started | 2022-09-02 | 2022-09-02 | 0 | On/ Ahead Schedule | Not Started | 2022-09-05 | 2022-09-16 | Not Started | 2022-10-25 | Not Started
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 | E.5015426.01 | 5782580 | ESTS | 08W | [6 empty] | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 5981 | 0 | 5981 | 1.1328 | 0 | 0 | 0 | 1.1328 | [5 empty] | 166667 | 0 | 166667 |  |  | 51312.7 | 0 | 115354.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 32094 | -32094 | 32094 | -32094 | 79687 | 895.9 | 132 | 763.9 | 9079.7 | 12375.8 | 4014.4 | 25842.8 | 22123.5 | 0 | 34408 | -13457 | 4054 | 287 | 419 | 896 | 904 | 908 | 912 | 884 | 921 | 958 | 2021-06-18 | 154998 | BL-A | BL-A 35056387_CWSP - Placerville 2106 - LR 1104 - Ph 1_08W - Jan. 2021 | 2021-01-25 | 2022-03-28 | Not Started | 2022-04-01 | 2022-04-07 | Not Started | 2022-03-31 | Not Started | 2022-05-23 | Not Started | 2022-03-29 | 2022-03-29 | Not Started | 2022-03-30 | 2022-04-19 | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-07-20 | Not Started |  |  |  |  | 2022-07-20 | Not Started | 2022-11-01 | Not Started | 2022-11-30 | Not Started | 2023-01-31 | 2023-01-31 | 0 | On/ Ahead Schedule | Not Started | 2023-02-01 | 2023-02-14 | Not Started | 2023-03-23 | Not Started
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 | E.5014319.01 | 5782536 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 7868 | 0 | 0 | 7868 | 1.4902 | 0 | 0 | 0 | 1.4902 | [5 empty] | 350000 | 0 | 350000 |  |  | 221023.7 | 642.1 | 128334.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 56181 | -56181 | 56181 | -56181 | 221023.7 | 0 | 0 | 0 | 0 | 43093.3 | 121749.7 | 56180.7 | 0 | 0 | 1120 | 51318 | 1253 | 1244 | 1244 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 | E.5015550.01 | 5783061 | ESTS | 08W | [6 empty] | Not in the WP | 2023 | SH | GRSSVLLY | Sierra Assets | 5545 | 0 | 0 | 5545 | 1.0502 | 0 | 0 | 0 | 1.0502 | [5 empty] | 71432 | 0 | 71432 |  |  | 51961.3 | 0 | 19470.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 39277 | -39277 | 39277 | -39277 | 52085.4 | 71.3 | 132 | -60.7 | 411.1 | 7646.6 | 4750.7 | 39152.9 | 0 | 0 | 16343 | 169 | 21792 | 293 | 425 | 71 | 74 | 74 | 37 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2022-12-13 | Not Started | 2023-01-24 | 2023-01-30 | Not Started | 2023-01-23 | Not Started | 2023-02-20 | Not Started | 2022-12-13 | 2022-12-13 | Not Started | 2022-12-14 | 2023-01-03 | Not Started | 2023-01-24 | 2023-02-06 | Not Started | 2023-03-15 | Not Started |  |  |  |  | 2023-03-15 | Not Started | 2023-06-27 | Not Started | 2023-07-26 | Not Started | 2023-09-26 | 2023-09-26 | 0 | On/ Ahead Schedule | Not Started | 2023-09-27 | 2023-10-10 | Not Started | 2023-11-16 | Not Started
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | E.5015549.01 | 5783060 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 2698 | 3009 | 0 | 5707 | 1.0809 | 0 | 0 | 0 | 1.0809 | [5 empty] | 250000 | 0 | 250000 |  |  | 142895.6 | 0 | 107104.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 107179 | -107179 | 107179 | -107179 | 2177115.5 | 194.5 | 725.5 | -531 | 1524.6 | 23533.8 | 10833.5 | 107003.7 | 2034045 | 0 | 88154 | 1185 | 8115 | 6026 | 2799 | 195 | 202 | 202 | 202 | 101 | 0 | 0
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | E.5015572.01 | 5783067 | ESTS | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 8106 | 0 | 0 | 8106 | 1.5352 | 0 | 1.5352 | 0 | 1.5352 | [5 empty] | 451282 | 0 | 451282 |  |  | 117353.2 | 0 | 333928.8 | On/Under Budget | Budget Allocated | 231000 | 230731 | 269 | 230731 | 269 | 4742758.4 | 5942.7 | -883.5 | 6826.2 | 23416.9 | 1241.9 | 3363.4 | 89331 | 4484005.6 | 0 | 12840 | 12150 | 57710 | 19495 | -11981 | 5943 | 37578 | 33918 | 26090 | 4173 | 16365 | 16450 | 2021-06-18 | 158192 | BL-A_ | BL-A_35062374_CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1_08W | 2021-03-31 | 2022-03-31 | Not Started | 2022-05-20 | 2022-05-26 | Not Started | 2022-05-19 | Not Started | 2022-06-16 | Not Started | 2022-04-01 | 2022-04-01 | Not Started | 2022-04-04 | 2022-04-22 | Not Started | 2022-05-20 | 2022-06-02 | Not Started | 2022-07-11 | Not Started | 2022-07-11 | Not Started | 2022-07-22 | Not Started | 2022-07-11 | Not Started | 2022-10-21 | Not Started | 2022-11-21 | Not Started | 2022-04-08 | 2023-01-13 | -280 | Behind Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-14 | Not Started
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | E.5015571.01 | 5783068 | ESTS | 08W | [6 empty] | 2022 |  | SH | PLCRVLLE | Sierra Assets | 5860 | 0 | 0 | 5860 | 1.1098 | 0 | 1.1098 | 0 | 1.1098 | [5 empty] | 1 | -199999 | 200000 |  |  | 77418.8 | 0 | 122581.2 | On/Under Budget | Budget Allocated | 200 | 72137 | -71937 | 72137 | -71937 | 77344.9 | 0 | 73.9 | -73.9 | 2301.1 | 1702.9 | 1203.9 | 72210.9 | 0 | 0 | 15840 | 11458 | 123309 | -48017 | -30452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 156275 | BL-A | BL-A 35062375_CWSP - Shingle Springs 2109 - LR 9372_08W - DD 210219 Feb. 2021 | 2021-02-25 | 2021-06-30 | Not Started | 2021-07-01 | 2021-07-07 | Not Started | 2021-10-12 | Not Started | 2021-10-13 | Not Started | 2021-07-01 | 2021-07-01 | Not Started | 2021-07-02 | 2021-07-22 | Not Started | 2021-10-13 | 2021-12-14 | Not Started | 2022-01-07 | Not Started | 2022-01-07 | Not Started | 2022-01-20 | Not Started | 2022-01-07 | Not Started | 2022-03-17 | Not Started | 2022-04-15 | Not Started | 2022-06-13 | 2022-06-16 | -3 | Behind Schedule | Not Started | 2022-06-17 | 2022-06-30 | Not Started | 2022-08-15 | Not Started
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | E.5015570.01 | 5783069 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 22892 | 0 | 0 | 22892 | 4.3356 | 0 | 4.3356 | 0 | 4.3356 | [5 empty] | 309269 | -27 | 309296 |  |  | 69002.9 | 0 | 240293.1 | On/Under Budget | Budget Allocated | 402000 | 442682 | -40682 | 442682 | -40682 | 13062906.7 | 30517.2 | -500 | 31017.2 | 1438.6 | 76.4 | 397.4 | 67090.6 | 12618312.1 | 0 | 14536 | 6818 | 3086 | 136745 | -93595 | 30517 | 81063 | 105296 | 54643 | 58442 | 12261 | 32870 | 2021-06-18 | 158881 | BL-A_ | BL-A_35062376_CWSP - SHINGLE SPRINGS 2109-LR 9372PH3.1_08W_Apr.2021 | 2021-04-07 | 2021-09-14 | Not Started | 2022-02-16 | 2022-02-22 | Not Started | 2022-02-15 | Not Started | 2022-03-15 | Not Started | 2021-09-15 | 2021-09-15 | Not Started | 2021-09-16 | 2021-10-06 | Not Started | 2021-11-17 | 2021-11-30 | Not Started | 2022-04-07 | Not Started | 2022-04-07 | Not Started | 2022-04-20 | Not Started | 2022-04-07 | Not Started | 2022-06-20 | Not Started | 2022-06-29 | Not Started | 2022-02-21 | 2022-09-06 | -197 | Behind Schedule | Not Started | 2022-09-07 | 2022-09-20 | Not Started | 2022-11-03 | Not Started
35110556 | BR-04-12-W (E) SUBSTATION/PATH PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 42053.6 | 0 | -42053.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 1613 | -1613 | 1613 | -1613 | 41506.4 | 0 | 547.2 | -547.2 | 0 | 31152.6 | 8740.9 | 2160.1 | 0 | 0 | 345 | 236 | 357 | 354 | 322 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | E.5015416.03 | 5785517 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 1664 | 12975 | 0 | 14639 | 2.7725 | 0 | 2.7725 | 0 | 2.7725 | 14639 | 0 | 2.7725 | 0 |  | 900000 | 0 | 900000 |  |  | 654519.1 | 0 | 245480.9 | On/Under Budget | Budget Allocated | 6469.4 | 170160 | -163690.6 | 170160 | -163690.6 | 769270.4 | 46746 | 39684.8 | 7061.2 | 0 | 15178.2 | 543929.5 | 95411.2 | 40002.1 | 0 | 33625 | 3432 | 3706 | 3966 | 10998 | 46746 | 58768 | 1773 | 1779 | 1745 | 1789 | 1835 | 2021-06-18 | 158113 | BL-A_ | BL-A_35109546_CWSP - El Dorado 2101 - 19752 - Ph 2.3_08W_Mar.2021 | 2021-03-30 | 2021-08-12 | Not Started | 2021-09-10 | 2022-04-14 | Not Started | 2021-09-09 | Not Started | 2022-05-05 | Not Started | 2021-08-13 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2020-05-21 | 2020-06-19 | Completed | 2022-08-03 | Not Started |  |  |  |  | 2022-08-03 | Not Started | 2022-11-15 | Not Started | 2022-12-14 | Not Started | 2023-01-03 | 2023-01-27 | -24 | Behind Schedule | Not Started | 2023-01-30 | 2023-02-10 | Not Started | 2023-03-21 | Not Started
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | E.5015417.03 | 5785513 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 1279 | 12807 | 0 | 14086 | 2.6678 | 0 | 2.6678 | 0 | 2.6678 | 14086 | 0 | 2.6678 | 0 |  | 900000 | 0 | 900000 |  |  | 624909.7 | 0 | 275090.3 | On/Under Budget | Budget Allocated | 4463.1 | 162107 | -157643.9 | 162107 | -157643.9 | 727015.2 | 46783.3 | 132 | 46651.3 | 0 | 21750.3 | 507594 | 95565.5 | 35564.1 | 0 | 80634 | 3533 | 3533 | 3902 | 3832 | 46783 | 11805 | 1811 | 1818 | 1775 | 1830 | 852 | 2021-06-18 | 158112 | BL-A1 | BL-A1_35109541_CWSP - El Dorado 2101 - 19752 - Ph 1.3_08W_Mar.2021 | 2021-03-30 | 2021-08-12 | Not Started | 2021-10-08 | 2021-12-01 | Not Started | 2021-10-07 | Not Started | 2021-12-22 | Not Started | 2021-08-13 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2020-05-04 | 2020-05-20 | Completed | 2022-04-28 | Not Started |  |  |  |  | 2022-04-28 | Not Started | 2022-08-10 | Not Started | 2022-11-18 | Not Started | 2022-12-30 | 2023-01-27 | -28 | Behind Schedule | Not Started | 2023-01-30 | 2023-02-10 | Not Started | 2023-03-21 | Not Started
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 | E.5014755.01 | 5785243 | ESTS | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8723 | 0 | 8723 | 1.6521 | 0 | 0 | 0 | 1.6521 | [5 empty] | 271429 | 0 | 271429 |  |  | 12084.8 | 0 | 259344.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1010 | -1010 | 1010 | -1010 | 44118.1 | 52.9 | 0 | 52.9 | 0 | 7347.2 | 4104.1 | 633.4 | 31656.3 | 0 | -475 | 64 | 64 | 63 | 918 | 53 | 54 | 54 | 54 | 54 | 54 | 54 | 2021-06-18 |  |  |  |  | 2022-12-08 | Not Started | 2022-12-12 | 2022-12-23 | Not Started | 2023-01-06 | Not Started | 2023-01-09 | Not Started | 2022-12-26 | 2022-12-26 | Not Started | 2022-12-27 | 2023-01-16 | Not Started | 2022-12-09 | 2023-01-12 | Not Started | 2023-01-31 | Not Started |  |  |  |  | 2023-01-31 | Not Started | 2023-02-28 | Not Started | 2023-03-10 | Not Started | 2023-06-02 | 2023-06-02 | 0 | On/ Ahead Schedule | Not Started | 2023-06-05 | 2023-06-16 | Not Started | 2023-07-25 | Not Started
35104252 | BR-05-03-W (E) CLARK PH II PARB |  | 5786123 | ESTS | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -299999 | 300000 |  |  | 6741.7 | 0 | 293258.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6405 | -6405 | 6405 | -6405 | 6405.3 | 479.4 | 815.8 | -336.4 | 0 | 0 | 0 | 6741.8 | 0 | 0 | 0 | 0 | 0 | 0 | 5926 | 479 | 0 | 0 | 0 | 0 | 0 | 0
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | 5530168 | ESTS | 08W | [6 empty] | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 1876 | 0 | 1876 | 0.3553 | 0 | 0 | 0.3553 | 0 | [5 empty] | 613848 | 0 | 613848 |  |  | 601913.5 | 0 | 11934.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2314 | -2314 | 2314 | -2314 | 602056 | 0 | -142.5 | 142.5 | 0 | 92441.4 | 507300.7 | 2171.4 | 0 | 0 | 2069 | 0 | 5172 | -2157 | -2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 | E.5015029.03 | 5785159 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 3000 | 200 | 0 | 3200 | 0.60606 | 0 | 0 | 0 | 0.60606 | 2741 | 0 | 0.51913 | 0 |  | 85000 | 0 | 85000 |  |  | 77552.9 | 0 | 7447.1 | On/Under Budget | Budget Allocated | 5220 | 4348 | 872 | 4348 | 872 | 77552.9 | 0 | 0 | 0 | 0 | 36650.6 | 36553.7 | 4348.4 | 0 | 0 | 529 | 464 | 1458 | 1461 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159684 | BL-A2 | BL-A2: 35094389_CWSP - KONOCTI 1102-LR 532 PH 2_08W - Apr 21 | 2021-04-26 | 2022-02-28 | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-07-15 | Not Started | 2022-07-18 | Not Started | 2022-03-16 | 2022-06-07 | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-07-18 | 2022-08-12 | Not Started | 2022-08-19 | Not Started |  |  |  |  | 2022-08-19 | Not Started | 2022-09-16 | Not Started | 2022-09-21 | Not Started | 2023-05-08 | 2022-11-21 | 168 | On/ Ahead Schedule | Not Started | 2022-11-22 | 2022-12-05 | Not Started | 2023-01-11 | Not Started
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 | E.5015029.09 | 5785165 | ESTS | 08W | [6 empty] | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 6245 | 1055 | 0 | 7300 | 1.3826 | 0 | 0 | 0 | 1.3826 | [5 empty] | 75000 | 0 | 75000 |  |  | 60351.4 | 0 | 14648.6 | On/Under Budget | Budget Allocated | 7364 | 7534 | -170 | 7534 | -170 | 65358.4 | 360.1 | 0 | 360.1 | 0 | 50869.1 | 4494.7 | 4987.6 | 2460.6 | 0 | 1376 | 547 | 1361 | 1364 | 339 | 360 | 364 | 364 | 364 | 364 | 364 | 364 | 2021-06-18 | 159685 | BL-A2 | BL-A2: 35094395_CWSP - KONOCTI 1102-LR 532 PH 8_08W - Apr 21 | 2021-04-26 | 2022-02-28 | Not Started | 2022-03-02 | 2022-03-03 | Not Started | 2022-07-15 | Not Started | 2022-07-18 | Not Started | 2022-03-04 | 2022-09-16 | Not Started | 2022-09-19 | 2022-09-20 | Not Started | 2022-07-18 | 2022-07-18 | Not Started | 2022-10-19 | Not Started |  |  |  |  | 2022-10-19 | Not Started | 2023-01-10 | Not Started | 2023-01-13 | Not Started | 2023-06-30 | 2023-03-15 | 107 | On/ Ahead Schedule | Not Started | 2023-03-16 | 2023-03-29 | Not Started | 2023-05-05 | Not Started
35094392 | OCGC CWSP-KONOCTI 1102-LR 532 PH 5 | E.5015029.06 | 5785162 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 1956 | 0 | 1956 | 0.37045 | 0 | 0 | 0.37045 | 0 | [5 empty] | 270000 | 0 | 270000 |  |  | 260347.4 | 0 | 9652.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 260347.4 | 0 | 0 | 0 | 0 | 264079.1 | -3731.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-29 | Completed | 2019-08-16 | 2019-08-19 | Completed | 2019-10-22 | Completed | 2019-08-20 | Completed | 2019-10-02 | 2019-12-03 | Completed | 2019-10-24 | 2019-10-24 | Completed | 2019-09-04 | 2019-09-05 | Completed | 2019-10-28 | Completed |  |  |  |  | 2019-10-28 | Completed | 2019-11-11 | Completed | 2019-12-04 | Completed | 2020-02-10 | 2019-12-04 | 68 | On/ Ahead Schedule | Completed | 2019-12-16 | 2019-12-27 | Completed | 2021-06-18 | Not Started
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) | E.5015029.07 | 5785163 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | LAKEPORT | Humboldt Division Assets | 0 | 10641 | 0 | 10641 | 2.0153 | 0 | 0 | 2.0153 | 3.4451e-16 | 10642 | 0 | 2.0155 | 0 |  | 3335231 | 520198.9 | 2815032.1 |  |  | 1763244.6 | 0 | 1051787.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -34488 | 34488 | -34488 | 34488 | 1763244.6 | 0 | 0 | 0 | 0 | 3208.6 | 1794523.7 | -34487.7 | 0 | 0 | -34488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145836 | BL-0: | BL-0: 35094393_CWSP - KONOCTI 1102-LR 532 PH 6_08W - Oct 2020 | 2020-07-24 | 2019-12-19 | Completed | 2020-02-17 | 2020-02-18 | Completed | 2020-01-29 | Completed | 2020-02-13 | Completed | 2020-02-24 | 2020-02-25 | Completed | 2020-05-04 | 2020-06-02 | Completed | 2020-04-24 | 2020-04-24 | Completed | 2020-06-01 | Completed |  |  |  |  | 2020-06-01 | Completed | 2020-08-05 | Completed | 2020-08-20 | Completed | 2020-10-14 | 2020-08-20 | 55 | On/ Ahead Schedule | Completed |  |  |  | 2021-06-18 | Not Started
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 | E.5015029.08 | 5785164 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | LAKEPORT | Humboldt Division Assets | 0 | 7765 | 0 | 7765 | 1.4706 | 0 | 0 | 1.4706 | 0 | 7765 | 0 | 1.4706 | 0 |  | 1708101 | 37446.7 | 1670654.3 |  |  | 1480078.6 | 0 | 190575.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 8937.4 | 2337 | 6600.4 | 2337 | 6600.4 | 1480078.6 | 0 | 0 | 0 | 0 | 3645.6 | 1474096.1 | 2336.8 | 0 | 0 | 2337 | 252 | -252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145837 | BL-0: | BL-0: 35094394_CWSP - KONOCTI 1102-LR 532 PH 7 _08W - Oct 2020 | 2020-07-24 | 2019-12-11 | Completed | 2019-11-06 | 2019-11-08 | Completed | 2020-01-13 | Completed | 2019-11-06 | Completed | 2019-11-11 | 2019-11-13 | Completed | 2020-02-10 | 2020-02-11 | Completed | 2020-02-07 | 2020-03-20 | Completed | 2020-03-09 | Completed |  |  |  |  | 2020-03-09 | Completed | 2020-11-19 | Completed | 2020-11-19 | Completed | 2020-10-07 | 2020-11-19 | -43 | Behind Schedule | Completed | 2021-06-18 | 2021-07-01 | Not Started | 2021-07-01 | Not Started
35094390 | CWSP-KONOCTI 1102-LR 532 PH 3 | E.5015029.04 | 5785160 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 2881 | 0 | 2881 | 0.54564 | 0 | 0 | 0.54564 | 0 | [5 empty] | 900000 | -0.3 | 900000.3 |  |  | 879982.2 | 0 | 20018.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 879982.2 | 0 | 0 | 0 | 0 | 837365.2 | 42617 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-07-26 | Completed | 2019-08-29 | 2019-08-29 | Completed | 2019-08-28 | Completed | 2019-08-28 | Completed | 2019-08-29 | 2019-08-29 | Completed | 2019-09-20 | 2019-09-20 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-11-21 | Completed |  |  |  |  | 2019-11-21 | Completed | 2019-11-27 | Completed | 2019-12-16 | Completed | 2020-06-18 | 2018-12-16 | 550 | On/ Ahead Schedule | Completed | 2020-01-06 | 2020-01-10 | Completed | 2021-08-09 | Not Started
35085681 | SILVERADO 2105 WIRE DOWN - PH 4 | E.5014317.05 | 5784870 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 2934 | 0 | 2934 | 0.55568 | 0 | 0 | 0.55568 | 0 | [5 empty] | 500000 | -0.5 | 500000.5 |  |  | 482640.4 | 0 | 17360.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2188 | -2188 | 2188 | -2188 | 482640.4 | 0 | 0 | 0 | 0 | 426337.6 | 54114.9 | 2188 | 0 | 0 | 0 | 0 | 0 | 3290 | -1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-06-07 | Completed | 2019-08-15 | 2019-08-16 | Completed | 2019-08-26 | Completed | 2019-08-14 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-08-22 | 2019-08-23 | Completed | 2019-09-06 | Completed |  |  |  |  | 2019-09-06 | Completed |  |  | 2019-09-24 | Completed | 2020-05-18 | 2019-09-24 | 237 | On/ Ahead Schedule | Completed | 2019-09-30 | 2019-10-04 | Completed | 2021-08-09 | Not Started
35085393 | CWSP - SILVERADO 2104 - LR722 PH 1B | E.5014772.02 | 5784860 | FICL | 08W | [6 empty] | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 1871 | 0 | 1871 | 0.35436 | 0 | 0 | 0.35436 | 0 | [5 empty] | 1300000 | 0.5 | 1299999.5 |  |  | 1239931.9 | 0 | 60067.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1239931.9 | 0 | 0 | 0 | 0 | 1516898.2 | -276966.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35085532 | CWSP - SILVERADO 2104 - LR722 PH 1C | E.5014772.03 | 5784861 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 5948 | 0 | 5948 | 1.1265 | 0 | 0 | 1.1265 | 0 | [5 empty] | 2100000 | 0.2 | 2099999.8 |  |  | 2033156.3 | 0 | 66843.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2033156.3 | 0 | 0 | 0 | 0 | 1405402.1 | 627754.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-06-10 | Completed |  |  | Completed | 2019-07-15 | Completed | 2019-09-06 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-09-09 | 2019-09-09 | Completed | 2019-07-08 | 2019-09-13 | Completed | 2019-09-13 | Completed |  |  |  |  | 2019-09-06 | Completed | 2019-10-17 | Completed | 2020-01-15 | Completed | 2020-01-15 | 2020-01-15 | 0 | On/ Ahead Schedule | Completed | 2020-01-20 | 2020-01-24 | Completed | 2021-06-18 | Not Started
35085533 | CWSP - SILVERADO 2104 - LR722 PH 1D | E.5014772.04 | 5784862 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 5365 | 0 | 5365 | 1.0161 | 0 | 0 | 1.0161 | 0 | [5 empty] | 2100000 | 0 | 2100000 |  |  | 2014171.4 | 0 | 85828.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2014171.4 | 0 | 0 | 0 | 0 | 1791769.8 | 222401.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-09-10 | Completed |  |  | Completed | 2019-09-10 | Completed | 2019-09-06 | Completed | 2019-08-26 | 2019-08-27 | Completed | 2019-09-02 | 2019-09-17 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-09-23 | Completed |  |  |  |  | 2019-09-23 | Completed |  |  | 2019-10-08 | Completed | 2020-05-19 | 2019-10-08 | 224 | On/ Ahead Schedule | Completed | 2019-10-14 | 2019-10-18 | Completed | 2021-06-18 | Not Started
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E | E.5014772.05 | 5784863 | FICL | 08W | [6 empty] | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 4191 | 0 | 4191 | 0.79375 | 0 | 0 | 0.79375 | 0 | 4191 | 4191 | 0.79375 | 0.79375 |  | 2118490 | 0.2 | 2118489.8 |  |  | 1679560.4 | 0 | 438929.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1070 | -1070 | 1070 | -1070 | 1679560.4 | 0 | 0 | 0 | 0 | 361963.8 | 1316527 | 1069.6 | 0 | 0 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-16 | Completed |  |  | Completed | 2019-09-02 | Completed | 2019-10-01 | Completed | 2019-10-02 | 2019-10-03 | Completed | 2019-10-03 | 2019-10-04 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-11-20 | Completed |  |  |  |  | 2019-11-20 | Completed |  |  | 2020-05-01 | Completed | 2020-05-18 | 2020-05-01 | 17 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-15 | Completed | 2021-08-09 | Not Started
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F | E.5014772.06 | 5784864 | FICL | 08W | [6 empty] | 2020 |  | SH | NAPA | North Bay Assets | 0 | 8793 | 0 | 8793 | 1.6653 | 0 | 0 | 1.6653 | 0 | 8793 | 8793 | 1.6653 | 1.6653 |  | 2979682 | 16050.9 | 2963631.1 |  |  | 2503791.3 | 0 | 459839.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1909 | -1909 | 1909 | -1909 | 2503791.3 | 0 | 0 | 0 | 0 | 523283.4 | 1978598.6 | 1909.3 | 0 | 0 | 1150 | 0 | 303 | 457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-07-31 | Completed | 2020-03-02 | 2020-03-11 | Completed | 2019-09-02 | Completed | 2020-02-21 | Completed | 2019-07-31 | 2020-02-21 | Completed | 2019-10-08 | 2019-11-05 | Completed | 2021-07-09 | 2021-07-22 | Not Started | 2020-01-06 | Completed | 2020-01-06 | Completed | 2020-01-17 | Completed | 2020-01-06 | Completed | 2020-02-21 | Completed | 2020-11-05 | Completed | 2022-05-03 | 2020-05-01 | 732 | On/ Ahead Schedule | Completed |  |  |  | 2021-09-20 | Not Started
35085536 | CWSP - SILVERADO 2104 - LR722 PH 1G | E.5014772.07 | 5784865 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 7010 | 0 | 7010 | 1.3277 | 0 | 0 | 1.3277 | 0 | [5 empty] | 1950000 | 0.4 | 1949999.6 |  |  | 1863426.2 | 0 | 86573.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1863426.2 | 0 | 0 | 0 | 0 | 1738811.2 | 124615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-13 | Completed | 2019-08-26 | 2019-08-27 | Completed | 2019-08-30 | Completed | 2019-08-23 | Completed | 2019-09-03 | 2019-09-04 | Completed | 2019-09-09 | 2019-09-10 | Completed | 2019-08-20 | 2019-08-22 | Completed | 2019-10-14 | Completed |  |  |  |  | 2019-10-14 | Completed |  |  | 2019-12-09 | Completed | 2020-05-18 | 2019-12-09 | 161 | On/ Ahead Schedule | Completed | 2019-12-12 | 2019-12-20 | Completed | 2021-08-09 | Not Started
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H | E.5014772.08 | 5784866 | FICL | 08W | [6 empty] | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 3752 | 0 | 3752 | 0.71061 | 0 | 0 | 0.71061 | 0 | 3442 | 3442 | 0.65189 | 0.65189 |  | 1350000 | -0.2 | 1350000.2 |  |  | 1281090.8 | 0 | 68909.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 34570 | -34570 | 34570 | -34570 | 1281090.8 | 0 | 0 | 0 | 0 | 1089162.2 | 157358.8 | 34569.8 | 0 | 0 | 0 | 0 | 34570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-07-09 | Completed | 2019-08-16 | 2019-08-29 | Completed | 2019-08-08 | Completed | 2019-08-14 | Completed | 2019-09-03 | 2019-09-04 | Completed | 2019-08-12 | 2019-08-14 | Completed | 2019-08-12 | 2019-08-16 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed |  |  | 2020-01-17 | Completed | 2020-06-02 | 2020-01-17 | 137 | On/ Ahead Schedule | Completed | 2020-01-27 | 2020-01-31 | Completed | 2021-08-09 | Not Started
35085538 | SILVERADO 2105 WIRE DOWN - PH 1 | E.5014317.02 | 5784867 | FICL | 08W | [6 empty] | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 10413 | 0 | 10413 | 1.9722 | 0 | 0 | 1.9722 | 0 | 9520 | 10413 | 1.803 | 1.9722 |  | 2950000 | -0.4 | 2950000.4 |  |  | 2775454.4 | 0 | 174546 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 2775454.4 | 0 | 0 | 0 | 0 | 1453170.1 | 1322284.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 |  |  |  |  | 2019-08-01 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-08-16 | Completed | 2019-08-16 | Completed | 2019-08-22 | 2019-08-23 | Completed | 2019-10-01 | 2019-10-01 | Completed | 2019-09-20 | 2019-09-20 | Completed | 2019-10-07 | Completed |  |  |  |  | 2019-10-07 | Completed | 2019-10-25 | Completed | 2020-05-18 | Completed | 2020-06-02 | 2020-05-18 | 15 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-01-26 | Completed
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 | E.5014317.03 | 5784868 | FICL | 08W | [6 empty] | 2020 | 2019 | SH | NAPA | North Bay Assets | 0 | 10260 | 0 | 10260 | 1.9432 | 0 | 0 | 1.9432 | 0 | 34020 | 34020 | 6.4432 | 6.4432 |  | 2570000 | 0.2 | 2569999.8 |  |  | 2451383.3 | 0 | 118616.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 80324 | -80324 | 80324 | -80324 | 2451383.3 | 0 | 0 | 0 | 0 | 1271059.9 | 1099999.1 | 80324.3 | 0 | 0 | 0 | 0 | 80324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-08-09 | Completed | 2019-08-26 | 2019-12-02 | Completed | 2019-08-30 | Completed | 2019-08-22 | Completed | 2019-08-28 | 2019-08-29 | Completed | 2019-10-02 | 2019-10-07 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-11-08 | Completed |  |  |  |  | 2019-11-08 | Completed | 2019-11-15 | Completed | 2020-05-21 | Completed | 2020-06-02 | 2020-05-21 | 12 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-07-19 | Not Started
35105646 | BR-03-05-W (E) DEAN RD, PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 2833115.5 | 2521030.5 | 312085 |  |  | 390195.1 | 35086 | -113196.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | -18953 | 18953 | -18953 | 18953 | 392751.7 | 4245.6 | 1689 | 2556.6 | 0 | 1831.2 | 409873.7 | -21509.7 | 0 | 0 | 51613 | -324833 | 215836 | 91328 | -57142 | 4246 | 0 | 0 | 0 | 0 | 0 | 0
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 | E.5015491.05 | 5785304 | FICL | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 13101 | 0 | 13101 | 2.4813 | 0 | 0 | 2.4813 | 0 | [5 empty] | 4936253 | 781728.6 | 4154524.4 | 0 | 4154524.4 | 4031718.1 | 0 | 122806.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -6823 | 6823 | -6823 | 6823 | 4034957.1 | 0 | -3239 | 3239 | 0 | 3885676.6 | 156103.3 | -10061.9 | 0 | 0 | 1514 | 0 | 0 | -3698 | -4639 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101876 | BR-01-08-W (E) MADRONE_BILLE_GRAHAM PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 910483.14 | 560483.14 | 350000 |  |  | 205370.2 | 0 | 144629.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -4220 | 4220 | -4220 | 4220 | 205370.2 | 0 | 0 | 0 | 0 | 928157.5 | -718567.3 | -4220 | 0 | 0 | 0 | 0 | 0 | -4220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35101877 | BR-01-06-W (E) THOMASSON LN PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1213012.83 | 113012.83 | 1100000 |  |  | 966943.7 | 0 | 133056.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -910 | 910 | -910 | 910 | 966943.7 | 0 | 0 | 0 | 0 | 2343712.4 | -1375858.3 | -910.4 | 0 | 0 | -910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 | E.5014544.01 | 5786325 | FICL | 08W | [6 empty] | 2020 |  | SH | CONCORD | Diablo Assets | 0 | 12599 | 0 | 12599 | 2.3862 | 0 | 0 | 2.3862 | 0 | 12588 | 12151 | 2.3841 | 2.3013 |  | 5151555 | -1.1 | 5151556.1 |  |  | 5086162.3 | 0 | 65393.8 | On/Under Budget | Project is not in the WP or in 2020 WP | -37865.9 | -36512 | -1353.9 | -36512 | -1353.9 | 5086162.3 | 0 | 0 | 0 | 0 | 4895315.5 | 227358.4 | -36511.5 | 0 | 0 | -37760 | 0 | 0 | 264 | 984 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | E.5015029.11 | 5785167 | FICL | 08W | [6 empty] | 2021 | 2021 | SH | LAKEPORT | Humboldt Division Assets | 0 | 5605.9 | 0 | 5605.9 | 1.0617 | 1.0617 | 0 | 1.0617 | 0 | 5621 | 0 | 1.0646 | 0 |  | 1733017 | 294030.4 | 1438986.6 |  |  | 1305344 | 0 | 133642.6 | On/Under Budget | Budget Allocated | 260000 | 250655 | 9345 | 250655 | 9345 | 1305344 | 0 | 0 | 0 | 0 | 4708.5 | 1049980.8 | 250654.7 | 0 | 0 | 250292 | 8520 | -7831 | -75 | -252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145838 | BL-0: | BL-0: 35094397_CWSP - KONOCTI 1102-LR 532 PH 10_08W - Nov 2020 | 2020-07-24 | 2019-12-26 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-05-29 | Completed | 2020-02-21 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-05-29 | 2020-05-29 | Completed | 2020-04-17 | 2020-04-17 | Completed | 2020-06-02 | Completed |  |  |  |  | 2020-06-02 | Completed | 2021-01-13 | Completed | 2020-11-09 | Completed | 2020-11-06 | 2021-01-14 | -69 | Behind Schedule | Completed |  |  |  | 2021-06-18 | Not Started
35094388 | CWSP-KONOCTI 1102-LR 532 PH 1 | E.5015029.02 | 5785158 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | LAKEPORT | Humboldt Division Assets | 0 | 2241 | 0 | 2241 | 0.42443 | 0 | 0 | 0.42443 | 0 | [5 empty] | 400000 | -0.2 | 400000.2 |  |  | 390843.6 | 0 | 9156.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 390843.6 | 0 | 0 | 0 | 0 | 445783 | -54939.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-07-03 | Completed | 2019-07-23 | 2019-08-01 | Completed | 2019-09-16 | Completed | 2019-08-01 | Completed | 2019-08-05 | 2019-08-06 | Completed | 2018-08-13 | 2019-08-13 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-09-16 | Completed |  |  |  |  | 2019-09-16 | Completed | 2019-09-06 | Completed | 2019-09-23 | Completed | 2020-04-01 | 2019-09-23 | 191 | On/ Ahead Schedule | Completed | 2020-03-09 | 2020-03-09 | Completed | 2021-06-18 | Not Started
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 | E.5015704.01 | 5785228 | FICL | 08W | [6 empty] | Not in the WP |  | SH | CHICO | North Valley Assets | 0 | 3666 | 0 | 3666 | 0.69432 | 0 | 0 | 0.69432 | 0 | [5 empty] | 3514354 | 162325.5 | 3352028.5 | 0 | 3352028.5 | 3093747.3 | 6093.4 | 252187.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 905 | -905 | 905 | -905 | 3093747.3 | 0 | 0 | 0 | 0 | 3083316.7 | 9525.6 | 905 | 0 | 0 | 905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 | E.5014759.01 | 5785578 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 8626 | 0 | 8626 | 1.6337 | 0 | 0 | 1.6337 | 0 | 8626 | 8610 | 1.6337 | 1.6307 |  | 4120715 | 188080.5 | 3932634.5 | 0 | 3932634.5 | 3620849 | 0 | 311785.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1423 | -1423 | 1423 | -1423 | 3620849 | 0 | 0 | 0 | 0 | 1935238.5 | 1684187.5 | 1423 | 0 | 0 | 921 | 1407 | -905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145819 | BL-0: | BL-0: 35107688_CWSP - VOLTA 1102 - LR 1648 -PH1.1_08W - April 2020 | 2020-07-24 | 2019-11-04 | Completed | 2019-11-08 | 2019-11-08 | Completed | 2019-08-27 | Completed | 2019-11-04 | Completed | 2019-11-07 | 2019-11-07 | Completed | 2019-11-21 | 2019-11-21 | Completed | 2019-11-04 | 2019-11-06 | Completed | 2020-01-07 | Completed |  |  |  |  | 2020-02-17 | Completed | 2020-04-10 | Completed | 2020-04-10 | Completed | 2020-04-10 | 2020-04-10 | 0 | On/ Ahead Schedule | Completed | 2020-04-30 | 2020-05-15 | Completed | 2021-06-18 | Not Started
35105649 | BR-14-02-W (E) DRENDEL PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1966056.89 | 1066056.89 | 900000 |  |  | 783442.5 | 0 | 116557.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16511 | -16511 | 16511 | -16511 | 790232.6 | 0 | -6790.1 | 6790.1 | 0 | 259117.9 | 514604.3 | 9720.4 | 0 | 0 | 9881 | -223 | 6853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 | E.5014759.02 | 5785579 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 9606 | 0 | 9606 | 1.8193 | 0 | 0 | 1.8193 | 0 | 9606 | 9607 | 1.8193 | 1.8195 |  | 4524488 | 191615.9 | 4332872.1 | 0 | 4332872.1 | 4040877.6 | 0 | 291994.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 914 | -914 | 914 | -914 | 4040877.6 | 0 | 0 | 0 | 0 | 2974123.8 | 1065839.7 | 914.1 | 0 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145820 | BL-0: | BL-0: 35106042_CWSP - VOLTA 1102 - LR 1648 - PH 1.2_08W - May 2020 | 2020-07-24 | 2019-08-27 | Completed | 2019-10-30 | 2019-12-19 | Completed | 2019-10-07 | Completed | 2019-11-01 | Completed | 2019-10-31 | 2019-10-31 | Completed | 2019-11-04 | 2019-11-04 | Completed | 2019-10-21 | 2019-11-06 | Completed | 2019-11-14 | Completed |  |  |  |  | 2019-11-14 | Completed | 2020-05-14 | Completed | 2020-05-14 | Completed | 2020-05-14 | 2020-05-14 | 0 | On/ Ahead Schedule | Completed | 2020-06-10 | 2020-06-24 | Completed | 2021-06-18 | Not Started
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 | E.5014759.03 | 5785580 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 9489 | 0 | 9489 | 1.7972 | 0 | 0 | 1.7972 | 0 | 10118 | 9489 | 1.9163 | 1.7972 |  | 4257794 | 515791.4 | 3742002.6 |  |  | 3560775.3 | 0 | 181227.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 12831 | -12831 | 12831 | -12831 | 3560775.3 | 0 | 0 | 0 | 0 | 1884904.9 | 1663039 | 12831.4 | 0 | 0 | 905 | 0 | 11926 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 | E.5015533.06 | 5785612 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 11791 | 0 | 11791 | 2.2331 | 0 | 0 | 2.2331 | 0 | 11790 | 11791 | 2.233 | 2.2331 |  | 4651895 | 430668 | 4221227 | 0 | 4221227 | 3294883.6 | 0 | 926343.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 300 | -300 | 300 | -300 | 3294883.6 | 0 | 0 | 0 | 0 | 418997.1 | 2875586.1 | 300.4 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145811 | BL-0: | BL-0: 35110441_CWSP - Volta 1102 - LR 1648 - Ph2.6_08W -May 2020 | 2020-07-24 | 2019-10-03 | Completed | 2019-10-16 | 2019-10-16 | Completed | 2019-09-18 | Completed | 2019-10-17 | Completed | 2019-10-07 | 2019-10-07 | Completed | 2019-10-21 | 2019-10-21 | Completed | 2019-10-22 | 2020-01-05 | Completed | 2020-02-01 | Completed |  |  |  |  | 2020-02-17 | Completed |  |  | 2020-05-04 | Completed | 2020-05-04 | 2020-05-04 | 0 | On/ Ahead Schedule | Completed | 2020-05-11 | 2020-05-28 | Completed | 2021-06-18 | Not Started
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 | E.5015704.02 | 5785613 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 7155 | 0 | 7155 | 1.3551 | 0 | 0 | 1.3551 | 0 | 7155 | 7126 | 1.3551 | 1.3496 |  | 4820085 | 175070.8 | 4645014.2 | 0 | 4645014.2 | 4399835.4 | 0 | 245178.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4291 | -4291 | 4291 | -4291 | 4399835.4 | 0 | 0 | 0 | 0 | 5652989.3 | -1257445.1 | 4291.2 | 0 | 0 | 905 | 1308 | -905 | 0 | 2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 | E.5015704.03 | 5785614 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 6630 | 0 | 6630 | 1.2557 | 0 | 0 | 1.2557 | 0 | 6468 | 6433 | 1.225 | 1.2184 |  | 4241038 | 212599.6 | 4028438.4 | 0 | 4028438.4 | 3712360.4 | 0 | 316078 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 201 | -201 | 201 | -201 | 3712360.4 | 0 | 0 | 0 | 0 | 3633268.9 | 78890.1 | 201.4 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 | E.5015704.04 | 5785615 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 7783 | 0 | 7783 | 1.4741 | 0 | 0 | 1.4741 | 0 | 7757 | 7728 | 1.4691 | 1.4636 |  | 4551984 | 182845.1 | 4369138.9 |  |  | 3593144 | 55095.4 | 720899.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 502 | -502 | 502 | -502 | 3593144 | 0 | 0 | 0 | 0 | 3069940.6 | 522701.5 | 501.9 | 0 | 0 | 0 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 | E.5015428.02 | 5785616 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 8668 | 0 | 8668 | 1.6417 | 0 | 0 | 1.6417 | 0 | 10160 | 9066 | 1.9242 | 1.717 |  | 5440290 | 0.9 | 5440289.1 | 0 | 5440289.1 | 4619951.6 | 34797.6 | 785539.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 37717 | -37717 | 37717 | -37717 | 4619342.4 | 0 | 609.2 | -609.2 | 0 | 4039029.7 | 542595.4 | 38326.4 | 0 | 0 | 31047 | 403 | 3763 | 1252 | 1251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145814 | BL-0: | BL-0: 35110445_CWSP - Volta 1102 - LR 1648 - Ph4.2_08W - Dec 2019 | 2020-07-24 | 2019-08-27 | Completed | 2019-09-10 | 2019-09-11 | Completed | 2019-08-14 | Completed | 2019-08-27 | Completed | 2019-09-12 | 2019-09-12 | Completed | 2019-09-26 | 2019-09-26 | Completed | 2019-09-09 | 2019-11-05 | Completed | 2019-10-16 | Completed |  |  |  |  | 2019-10-16 | Completed |  |  | 2019-12-26 | Completed | 2019-12-26 | 2019-12-26 | 0 | On/ Ahead Schedule | Completed | 2020-05-12 | 2020-05-29 | Completed | 2021-07-19 | Not Started
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 | E.5015428.03 | 5785617 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 11401 | 0 | 11401 | 2.1593 | 0 | 0 | 2.1593 | 0 | 11030 | 11009 | 2.089 | 2.085 |  | 4988877 | 176720 | 4812157 |  |  | 4263899.6 | 0 | 548257.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 502 | -502 | 502 | -502 | 4263899.6 | 0 | 0 | 0 | 0 | 1730351.5 | 2533046.2 | 501.9 | 0 | 0 | 0 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 | E.5015428.04 | 5785618 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 6198 | 0 | 6198 | 1.1739 | 0 | 0 | 1.1739 | 0 | 6201 | 6190 | 1.1744 | 1.1723 |  | 4129566 | 0.4 | 4129565.6 |  |  | 4013101.3 | 0 | 116464.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1869 | -1869 | 1869 | -1869 | 4013101.3 | 0 | 0 | 0 | 0 | 2016413.2 | 1994819.5 | 1868.6 | 0 | 0 | 1466 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 | E.5015428.05 | 5785619 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 10503 | 0 | 10503 | 1.9892 | 0 | 0 | 1.9892 | 0 | 10301 | 10620 | 1.9509 | 2.0114 |  | 6475096 | 923719.7 | 5551376.3 |  |  | 4621706.6 | 0 | 929669.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5151 | -5151 | 5151 | -5151 | 4621706.6 | 0 | 0 | 0 | 0 | 2017962.8 | 2598592.8 | 5151 | 0 | 0 | 0 | 0 | 3200 | 1951 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145817 | BL-0: | BL-0: 35110448_CWSP - Volta 1102 - LR 1648 - Ph4.5_08W - May 2020 | 2020-07-24 | 2019-09-23 | Completed | 2020-02-05 | 2020-02-06 | Completed | 2019-10-08 | Completed | 2019-10-18 | Completed | 2019-09-24 | 2019-09-24 | Completed | 2019-10-08 | 2019-10-08 | Completed | 2019-11-15 | 2020-01-05 | Completed | 2020-02-03 | Completed |  |  |  |  | 2020-04-06 | Completed |  |  | 2020-05-28 | Completed | 2020-05-28 | 2020-05-28 | 0 | On/ Ahead Schedule | Completed | 2020-06-01 | 2020-12-12 | Completed | 2021-06-23 | Not Started
35111486 | BR-04-03-W (E) EDWARDS & RIPLEY PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | -8542 | 8542 | -8542 | 8542 | [10 empty] | 5827 | -735 | 0 | -13634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110377 | BR-03-10-W (E) SHAY LN PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 2448690.3 | -651309.7 | 3100000 |  |  | 2999963.9 | 0 | 100036.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 13164 | -13164 | 13164 | -13164 | 2999963.9 | 0 | 0 | 0 | 0 | 2546046.2 | 440753.3 | 13164.4 | 0 | 0 | 0 | 11229 | 0 | 0 | 1936 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 | E.5015533.03 | 5785609 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 10959 | 0 | 10959 | 2.0756 | 0 | 0 | 2.0756 | 0 | 10903 | 10732 | 2.065 | 2.0326 |  | 4773512 | 289328.9 | 4484183.1 | 0 | 4484183.1 | 4189309.9 | 0 | 294873.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9 | -9 | 9 | -9 | 4189309.9 | 0 | 0 | 0 | 0 | 2069988.1 | 2119312.7 | 9.1 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 | E.5015533.04 | 5785610 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CHICO | North Valley Assets | 0 | 12344 | 0 | 12344 | 2.3379 | 0 | 0 | 2.3379 | 0 | 13219 | 12081 | 2.5036 | 2.2881 |  | 5748253 | 225417.1 | 5522835.9 |  |  | 5295742.1 | 0 | 227093.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 702 | -702 | 702 | -702 | 5295742.1 | 0 | 0 | 0 | 0 | 3494061.7 | 1800978.5 | 701.8 | 0 | 0 | 200 | 702 | -200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145809 | BL-0: | BL-0: 35109739_CWSP - Volta 1102 - LR 1648 - Ph2.4_08W - Jan 2020 | 2020-07-24 | 2019-09-20 | Completed | 2019-09-13 | 2019-09-13 | Completed | 2019-08-20 | Completed | 2019-09-20 | Completed | 2019-12-23 | 2019-12-23 | Completed | 2020-01-10 | 2020-01-10 | Completed | 2019-09-25 | 2019-10-15 | Completed | 2019-10-19 | Completed |  |  |  |  | 2019-10-19 | Completed |  |  | 2020-01-23 | Completed | 2020-01-23 | 2020-01-23 | 0 | On/ Ahead Schedule | Completed | 2020-05-04 | 2020-05-19 | Completed | 2021-06-18 | Not Started
35109832 | BR-03-01-W (E) GATE LN PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1762328.04 | 1662328.04 | 100000 |  |  | -164567 | 0 | 264567 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | -164567 | 0 | 0 | 0 | 0 | 931673.9 | -1096240.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112091 | BR-01-09-W (E) FERN PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 951433.29 | 551433.29 | 400000 |  |  | 396097.8 | 0 | 3902.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 24743 | -24743 | 24743 | -24743 | 396097.8 | 0 | 0 | 0 | 0 | 167841.7 | 203513.5 | 24742.6 | 0 | 0 | 8257 | 0 | 16453 | 67 | -33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112876 | BR-04-02-W (E) CASTLE_CLIFF DR PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 2273956.11 | 1573956.11 | 700000 |  |  | -789489.5 | 0 | 1489489.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 48 | -48 | 48 | -48 | -789489.5 | 0 | 0 | 0 | 0 | 464356.1 | -1253894 | 48.4 | 0 | 0 | 8 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | E.5015420.06 | 5785656 | FICL | 08W | [6 empty] | 2020 |  | SH | PLCRVLLE | Sierra Assets | 0 | 7341 | 0 | 7341 | 1.3903 | 0 | 0 | 1.3903 | 0 | 7341 | 0 | 1.3903 | 0 |  | 5585619 | 1694081.1 | 3891537.9 |  |  | 2167526 | 0 | 1724011.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 75130 | -130 | 75130 | -130 | 2187244 | 0 | 132 | -132 | 0 | 15536.1 | 2096578.1 | 55411.8 | 0 | 0 | 1288 | -72375 | 126255 | -20 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 19850
35112220 | BR-04-06-W (E) VALLEY RIDGE PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1030719.49 | 800200.49 | 230519 |  |  | 114504.1 | 0 | 116014.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -258224 | 258224 | -258224 | 258224 | 73080.8 | 0.4 | 41423.7 | -41423.3 | 0 | 66867.5 | 264437.7 | -216801 | 0 | 0 | -19842 | -221294 | -34477 | 16475 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112249 | BR-04-07-W (E) CRESTMOOR PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1977495.99 | -3000000.01 | 4977496 |  |  | 4287754.4 | 0 | 689741.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 4287754.4 | 0 | 0 | 0 | 0 | 1450348.1 | 2837406.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | 5783065 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 12142 | 0 | 12142 | 2.2996 | 0 | 0 | 2.2996 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 34327 | -34327 | 34327 | -34327 | [10 empty] | 14133 | 13463 | 6731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128543 | WSHP | WSHP 190307 - 35064793_Cabrillo 1104 Reconductoring - B1 | 2019-03-07 | 2019-02-25 | Completed |  |  | Completed | 2019-08-23 | Completed | 2019-05-29 | Completed | 2019-05-31 | 2019-06-18 | Completed |  |  |  | 2019-06-17 | 2019-07-05 | Completed | 2019-07-12 | Completed |  |  |  |  | 2019-08-05 | Completed |  |  | 2019-08-26 | Completed | 2019-10-04 | 2019-08-26 | 39 | On/ Ahead Schedule | Completed |  |  |  | 2020-10-30 | Not Started
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 | E.5014317.01 | 5782595 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 3684 | 0 | 3684 | 0.69773 | 0 | 0 | 0.69773 | 0 | [5 empty] | 2410000 | -0.1 | 2410000.1 |  |  | 2113454 | 0 | 296546.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 136522 | -136522 | 136522 | -136522 | 2202675.6 | 12680.7 | 0 | 12680.7 | 0 | 2117114.6 | -50960.7 | 47300.1 | 0 | 0 | 0 | 0 | 47300 | 0 | 0 | 12681 | 12757 | 12757 | 12757 | 12757 | 12757 | 12757 | 2021-06-18 | 128627 | WSHP | WSHP 190307 - 35072146_SILVERADO 2105 WIRE DOWN_08W - B1 | 2019-03-07 | 2019-06-12 | Completed |  |  | Completed | 2019-08-16 | Completed | 2019-06-26 | Completed | 2019-07-27 | 2019-07-27 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-11-15 | Completed |  |  |  |  | 2019-11-15 | Completed |  |  | 2019-12-17 | Completed | 2020-01-07 | 2019-12-17 | 21 | On/ Ahead Schedule | Completed | 2019-12-20 | 2019-12-23 | Completed | 2021-08-09 | Not Started
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 | E.5015427.01 | 5782537 | FICL | 08W | [6 empty] | 2021 |  | SH | SONORA | Yosemite Assets | 0 | 10707 | 0 | 10707 | 2.0278 | 2.0278 | 0 | 2.0278 | 0 | 10737 | 0 | 2.0335 | 0 |  | 3642331 | 691429 | 2950902 |  |  | 1257442.5 | 143941.2 | 1549518.3 | On/Under Budget | Budget Allocated | 1257187 | 1024585 | 232602 | 1024585 | 232602 | 1395879.7 | 145256.1 | 6818.9 | 138437.2 | 7046 | 16234.6 | 348014 | 886148 | 0 | 0 | 6426 | 5916 | 228934 | 580414 | 57639 | 145256 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161079 | BL-1 | BL-1 35056746_CWSP - MIWUK 1701 - OCB - PH 2.1_08W - DD 210521 | 2021-05-26 | 2020-03-30 | Completed | 2020-07-06 | 2020-07-23 | Completed | 2020-06-29 | Completed | 2020-07-31 | Completed | 2020-07-31 | 2020-08-06 | Completed | 2020-08-07 | 2020-08-27 | Completed | 2020-08-21 | 2020-09-01 | Completed | 2020-09-14 | Completed |  |  |  |  | 2020-09-14 | Completed |  |  | 2021-05-21 | Completed | 2021-07-07 | 2021-05-10 | 58 | On/ Ahead Schedule | Completed | 2021-05-08 | 2021-05-14 | Completed | 2021-06-25 | Not Started
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | E.5015420.01 | 5782588 | FICL | 08W | [6 empty] | Not in the WP |  | SH | PLCRVLLE | Sierra Assets | 0 | 6215 | 0 | 6215 | 1.1771 | 0 | 0 | 1.1771 | 0 | [5 empty] | 4515047 | 955704.3 | 3559342.7 |  |  | 3061415.4 | 0 | 497927.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -7915 | 7915 | -7915 | 7915 | 3061415.4 | 0 | 0 | 0 | 5264.2 | 34636.1 | 3029430.1 | -7914.9 | 0 | 0 | -59587 | 80653 | 13738 | 15943 | -58662 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060582 | SLO 1107 RECOD 3884 FT WITH 2CU TW |  | 5530166 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 3884 | 0 | 3884 | 0.73561 | 0 | 0 | 0.73561 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128540 | WSHP | WSHP 190307 - 35060582_SLO 1107 SQUIRE CYN WILDFIRE RESIL - B1 | 2019-03-07 | 2019-03-06 | Completed |  |  | Completed | 2019-01-08 | Completed | 2019-05-24 | Completed | 2019-07-02 | 2019-07-26 | Completed |  |  |  | 2019-07-18 | 2019-08-12 | Completed | 2019-08-13 | Completed |  |  |  |  | 2019-08-30 | Completed |  |  | 2019-09-26 | Completed | 2019-08-28 | 2019-09-26 | -29 | Behind Schedule | Completed | 2019-09-27 | 2019-10-09 | Completed | 2019-11-22 | Completed
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 | E.5014753.01 | 5782586 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CONCORD | Diablo Assets | 0 | 31174 | 0 | 31174 | 5.9042 | 0 | 0 | 5.9042 | 0 | 31276 | 31276 | 5.9235 | 5.9235 |  | 9709000 | 0 | 9709000 |  |  | 9418091.5 | 0 | 290908.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 368855 | 88383 | 280472 | 88383 | 280472 | 9417120.2 | 0 | 971.3 | -971.3 | 4338.7 | 778748.6 | 8545650 | 89354.2 | 0 | 0 | 54187 | 12073 | 14559 | 2521 | 5042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 140140 | BL- 0 | BL- 0: 35053033_CWSP - TASSAJARA 2112 - FUSE 18053_08W - Feb 20 | 2020-02-12 | 2019-07-26 | Completed |  |  | Completed | 2019-11-21 | Completed | 2019-11-21 | Completed |  |  |  | 2019-12-09 | 2019-12-13 | Completed |  |  |  | 2019-12-03 | Completed |  |  |  |  | 2019-12-03 | Completed |  |  | 2020-06-04 | Completed | 2021-03-05 | 2020-06-04 | 274 | On/ Ahead Schedule | Completed |  |  |  | 2021-06-18 | Not Started
35043303 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1909 |  | 5530164 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | FORTUNA |  | 0 | 8140 | 0 | 8140 | 1.5417 | 0 | 0 | 1.5417 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 13535 | -13535 | 13535 | -13535 | [10 empty] | 0 | 0 | 0 | 14226 | -691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 128576 | WSHP | WSHP 190307 - 35043303_EEL RIVER 1102 FU 1909_08W - B1 | 2019-03-07 | 2019-06-04 | Completed | 2019-06-27 | 2019-06-27 | Completed |  |  | 2019-08-02 | Completed | 2019-07-05 | 2019-07-08 | Completed |  |  |  | 2019-07-01 | 2019-07-02 | Completed | 2019-08-12 | Completed |  |  |  |  | 2019-08-12 | Completed |  |  | 2019-09-19 | Completed | 2019-12-03 | 2019-09-19 | 75 | On/ Ahead Schedule | Completed |  |  |  | 2021-08-09 | Not Started
35031662 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | E.5014534.01 | 5780841 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 511 | 2467 | 0 | 2978 | 0.56402 | 0 | 0 | 0.56402 | 5.1676e-16 | 2978 | 2978 | 0.56402 | 0.56402 |  | 1363100.7 | 253111.7 | 1109989 |  |  | 1026578.3 | 0 | 83410.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 19394.1 | 0 | 19394.1 | 0 | 19394.1 | 1026578.3 | 0 | 0 | 0 | 17817.8 | 32969.5 | 975791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 159258 | BL-0_ | BL-0_35031662_CWSP - Los Gatos 1106 -LB44 - Ph 2.1 - B1_Apr 21 (Post) | 2021-04-15 | 2019-10-07 | Completed | 2020-01-15 | 2020-02-18 | Completed | 2020-01-13 | Completed | 2020-01-13 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2020-01-21 | 2020-01-21 | Completed | 2020-01-20 | 2020-03-25 | Completed | 2020-02-12 | Completed |  |  |  |  | 2020-02-12 | Completed |  |  | 2020-03-25 | Completed | 2020-03-25 | 2020-03-25 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | 5530166 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 6386 | 0 | 6386 | 1.2095 | 0 | 0 | 1.2095 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128570 | WSHP | WSHP 190307 - 31278200_OCEANO 1108 S HALCYON & PINE RDGE_08J - B1 | 2019-03-07 | 2019-03-07 | Completed | 2018-07-30 | 2018-08-06 | Completed |  |  | 2018-08-07 | Completed | 2019-03-08 | 2019-06-07 | Completed |  |  |  | 2019-03-11 | 2019-03-11 | Completed | 2019-03-11 | Completed |  |  |  |  | 2019-03-11 | Completed |  |  | 2019-03-21 | Completed | 2019-03-28 | 2019-03-21 | 7 | On/ Ahead Schedule | Completed |  |  |  | 2019-10-01 | Completed
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS |  | 5530166 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 6386 | 0 | 6386 | 1.2095 | 0 | 0 | 1.2095 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128538 | WSHP | WSHP 190307 - 31269259_ZACA 1101 FOXEN CYN RD, LOS OLIVOS_08W - B1 | 2019-03-07 | 2019-04-01 | Completed | 2019-04-02 | 2019-05-09 | Completed | 2019-05-30 | Completed | 2019-05-24 | Completed | 2019-05-20 | 2019-05-23 | Completed |  |  |  | 2019-05-17 | 2019-05-20 | Completed | 2019-05-23 | Completed |  |  |  |  | 2019-05-23 | Completed |  |  | 2019-06-30 | Completed | 2019-05-13 | 2019-06-30 | -48 | Behind Schedule | Completed |  |  |  | 2019-10-01 | Completed
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | P.11104 | 5530168 | FICL | 08W | [6 empty] | 2020 |  | SH | SNRAFAEL | North Bay Assets | 0 | 9487 | 0 | 9487 | 1.7968 | 0 | 0 | 1.7968 | 3.1006e-15 | 6861 | 6500 | 1.2994 | 1.2311 |  | 3537680 | 0 | 3537680 | 71361 | 3466319 | 3526686.6 | 0 | 10993.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 100000 | 95383 | 4617 | 95383 | 4617 | 3537680.2 | 0 | 44006.4 | -44006.4 | 7077.1 | 53566.5 | 3328524.8 | 84389.3 | 0 | 0 | 40383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55000 | 0
31209950 | R7 RECON POTTER VLY 1105 ( VAN ARSDALE) | P.11913 | 5530164 | FICL | 08W | [6 empty] | Not in the WP |  | SH | UKIAH | Humboldt Division Assets | 0 | 3008 | 0 | 3008 | 0.5697 | 0 | 0 | 0.5697 | 0 | [5 empty] | 273660 | -943257.9 | 1216917.9 |  |  | 1221056.9 | 0 | -4139 | OverRun | Project is not in the WP or in 2020 WP | 0 | 8239 | -8239 | 8239 | -8239 | 1221056.9 | 0 | 0 | 0 | 18719.9 | 1454401.9 | -261375.4 | 8239 | 0 | 0 | 0 | 0 | 0 | 1454 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE | P.11939 | 5530168 | FICL | 08W | [6 empty] | Not in the WP |  | SH | NAPA | North Bay Assets | 0 | 6705.6 | 0 | 6705.6 | 1.27 | 0 | 0 | 1.27 | 0 | [5 empty] | 3937382 | 0 | 3937382 |  |  | 3918024.8 | 0 | 19357.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16906 | -16906 | 16906 | -16906 | 3918024.8 | 0 | 0 | 0 | 689101.9 | 2636266.8 | 575750.5 | 16905.6 | 0 | 0 | 0 | 16906 | 0 | 1102 | -1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31290145 | R7 SAN RAFAEL 1107 COND REPLACEMENT |  | 5530168 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNRAFAEL |  | 0 | 801 | 0 | 801 | 0.1517 | 0 | 0 | 0.1517 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 128629 | WSHP | WSHP 190307 - 31290145_SAN RAFAEL 1107_08W - B1 | 2019-03-07 | 2019-03-11 | Completed | 2019-03-08 | 2019-04-12 | Completed | 2019-04-09 | Completed | 2019-03-18 | Completed | 2019-03-18 | 2019-03-18 | Completed | 2019-08-06 | 2019-08-06 | Completed | 2019-08-06 | 2019-08-07 | Completed | 2019-08-07 | Completed |  |  |  |  | 2019-08-07 | Completed |  |  | 2019-08-12 | Completed | 2019-05-28 | 2019-08-12 | -76 | Behind Schedule | Completed | 2019-09-23 | 2019-10-07 | Completed | 2020-01-02 | Completed
31361965 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 |  | 5530175 | FICL | 08W | [6 empty] | 2021 | 2022 | SH | STROSA | Sonoma Assets | 0 | 2367 | 0 | 2367 | 0.4483 | 0.4483 | 0 | 0.4483 | 0 | 2367 | 0 | 0.4483 | 0 |  | 1245293 | 0 | 1245293 | 0 | 1245293 | 529136.9 | 0 | 716156.1 | On/Under Budget | Budget Allocated | 273723 | 272528 | 1195 | 272528 | 1195 | 559680.3 | 13.2 | 0 | 13.2 | 12035.3 | 383036.2 | -107919 | 241984.3 | 0 | 0 | 5896 | 5344 | 71351 | 123209 | 36184 | 13 | 265 | 265 | 0 | 0 | 30000 | 0 | 2021-06-18 | 159681 | BL-B2 | BL-B2: 31361965_Dunbar 1101 - Nuns Canyon_08W - Apr 21 | 2021-04-26 | 2019-06-19 | Completed | 2019-03-08 | 2019-06-21 | Completed | 2020-07-22 | Completed | 2020-07-24 | Completed | 2020-11-10 | 2021-03-05 | Completed | 2021-03-05 | 2021-03-12 | Completed | 2020-09-28 | 2020-11-30 | Completed | 2021-03-16 | Completed |  |  |  |  | 2021-03-16 | Completed |  |  | 2021-04-27 | Completed | 2021-06-03 | 2021-04-24 | 40 | On/ Ahead Schedule | Completed | 2021-04-24 | 2021-04-27 | Completed | 2021-06-18 | Not Started
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ |  | 5530166 | FICL | 08W | [6 empty] | Not in the WP | 2019 | SH | SNLUISOB |  | 0 | 5851 | 0 | 5851 | 1.1081 | 0 | 0 | 1.1081 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2020-10-30 | 128537 | WSHP | WSHP 190307 - 31232280_ZACA 1102 LONG CYN RD, SANTA YNEZ_08W - B2 | 2019-03-07 | 2019-04-01 | Completed | 2019-04-01 | 2019-05-09 | Completed | 2019-04-25 | Completed | 2019-05-24 | Completed | 2019-05-20 | 2019-05-23 | Completed |  |  |  | 2019-05-17 | 2019-05-22 | Completed | 2019-05-23 | Completed |  |  |  |  | 2019-05-23 | Completed |  |  | 2019-06-30 | Completed | 2019-05-15 | 2019-06-30 | -46 | Behind Schedule | Completed |  |  |  | 2019-11-02 | Completed
31206678 | MVWF SEQUOIA VLY RD CTY/CNTY AL1125/1124 | P.11109 | 5530168 | FICL | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | North Bay Assets | [14 empty] | 1689113 | 357692 | 1331421 |  |  | 920278.5 | 0 | 411142.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 920278.5 | 0 | 0 | 0 | 817684.9 | 55949.4 | -6940.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35141419 | BR-03-07-W (E) TIMBER WALK PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 261420.05 | -288579.95 | 550000 |  |  | 441599.4 | 0 | 108400.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 52 | -52 | 52 | -52 | 441599.4 | 0 | 0 | 0 | 0 | 234659.2 | 206888.5 | 51.7 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | E.5015531.03 | 5788622 | FICL | 08W | [6 empty] | 2021 |  | SH | GRSSVLLY | Sierra Assets | 0 | 8269 | 0 | 8269 | 1.5661 | 1.5661 | 0 | 1.5661 | 0 | 8412 | 0 | 1.5932 | 0 |  | 3876275 | 1124354 | 2751921 |  |  | 1801146.3 | 92074.3 | 858700.4 | On/Under Budget | Budget Allocated | 2721318.8 | 2719055 | 2263.8 | 2719055 | 2263.8 | 3673414.6 | 5550.3 | 3282 | 2268.3 | 0 | 235.3 | 954124.7 | 846786.3 | 0 | 0 | 168194 | 151055 | 267023 | 242082 | 15151 | 5550 | 0 | 0 | 0 | 0 | 1000000 | 870000
35118663 | BR-01-01-W (E) HEAVENS GATE PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  | BUCOCAMP | CHICO | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1772954.66 | 857663.66 | 915291 |  |  | 994177.1 | 2423 | -81309.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 183532 | -183532 | 183532 | -183532 | 991581.5 | 0 | 2595.6 | -2595.6 | 0 | 4747.7 | 803302.1 | 186127.3 | 0 | 0 | 32313 | -1563 | 128969 | 17813 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 | E.5015489.01 | 5786658 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | STCRUZ | Central Coast Assets | 0 | 5683 | 0 | 5683 | 1.0763 | 0 | 0 | 1.0763 | 0 | 5683 | 5642 | 1.0763 | 1.0686 |  | 2570791 | 435989 | 2134802 |  |  | 1632068.8 | 0 | 502733.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 58664.8 | 18619 | 40045.8 | 18619 | 40045.8 | 1630868.8 | 0 | 1200 | -1200 | 0 | 29415.8 | 1582833.7 | 19819.3 | 0 | 0 | -1820 | 10188 | 7105 | 1769 | 1378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 128566 | WSHP | WSHP 190307 - 74022381_CWSP - CAMP EVERS 2106 - 5020 - PHASE - BL0 | 2019-03-07 | 2019-12-04 | Completed |  |  | Completed | 2020-02-18 | Completed | 2020-02-20 | Completed | [6 empty] | 2020-03-09 | 2020-05-13 | Completed | 2020-03-12 | Completed |  |  |  |  | 2020-03-12 | Completed |  |  | 2020-05-07 | Completed | 2020-05-16 | 2020-05-07 | 9 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35119966 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | E.5014534.06 | 5786603 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 4325 | 0 | 4325 | 0.81913 | 0 | 0 | 0.81913 | 0 | 4325 | 4309 | 0.81913 | 0.8161 |  | 1552000 | 416000 | 1136000 |  |  | 811677.3 | 0 | 324322.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 811677.3 | 0 | 0 | 0 | 0 | 585.8 | 811091.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141309 | BL-0: | BL-0: 35119966_CWSP Los Gatos 1106-LB44 Ph2.6F _08W - Mar 2020 | 2020-03-10 | 2019-11-22 | Completed |  |  | Completed | 2020-01-21 | Completed | 2020-01-21 | Completed | 2020-01-27 | 2020-01-27 | Completed | 2020-02-11 | 2020-02-20 | Completed | 2020-02-18 | 2020-03-27 | Completed | 2020-02-14 | Completed |  |  |  |  | 2020-02-14 | Completed | 2020-03-04 | Completed | 2020-03-10 | Completed | 2020-05-29 | 2020-03-10 | 80 | On/ Ahead Schedule | Completed |  |  |  | 2021-02-02 | Completed
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 | E.5015493.02 | 5786588 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 6777 | 0 | 6777 | 1.2835 | 0 | 0 | 1.2835 | 0 | 6777 | 0 | 1.2835 | 0 |  | 2027153 | 0 | 2027153 |  |  | 1662759 | 0 | 364394 | On/Under Budget | Project is not in the WP or in 2020 WP | 2392.4 | -5104 | 7496.4 | -5104 | 7496.4 | 1662759 | 0 | 0 | 0 | 0 | 4382 | 1663480.6 | -5103.7 | 0 | 0 | 972 | 3209 | -9813 | 511 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141386 | BL-0: | BL-0: 35119969_CWSP Los Gatos 1106-LB44 Ph 4.2_08W - Mar 20 | 2020-03-16 | 2019-12-02 | Completed | 2020-02-25 | 2020-03-03 | Completed | 2020-01-17 | Completed | 2020-01-22 | Completed | 2020-03-18 | 2020-04-10 | Completed | 2020-03-13 | 2020-04-10 | Completed | 2020-03-20 | 2020-06-03 | Completed | 2020-04-04 | Completed |  |  |  |  | 2020-04-04 | Completed | 2020-08-14 | Completed | 2020-08-14 | Completed | 2020-08-14 | 2020-08-14 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-03-17 | Completed
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 | E.5015493.03 | 5786587 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 3090 | 0 | 3090 | 0.58523 | 0 | 0 | 0.58523 | 0 | 3090 | 0 | 0.58523 | 0 |  | 1850000 | 20000.3 | 1829999.7 |  |  | 1825133.9 | 0 | 4865.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5254 | -5254 | 5254 | -5254 | 1825133.9 | 0 | 0 | 0 | 0 | 1604.7 | 1818275.5 | 5253.7 | 0 | 0 | 444 | 688 | 2021 | 2084 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-12-17 | 141387 | BL-0: | BL-0: 35119970_CWSP Los Gatos 1106-LB44 Ph 4.3_08W - Mar 20 | 2020-03-16 | 2019-12-03 | Completed | 2020-02-14 | 2020-03-27 | Completed | 2020-01-17 | Completed | 2020-01-21 | Completed | 2019-12-03 | 2019-12-03 | Completed | 2020-02-10 | 2020-02-28 | Completed | 2020-03-20 | 2020-03-30 | Completed | 2020-02-22 | Completed |  |  |  |  | 2020-02-22 | Completed | 2020-08-09 | Completed | 2020-08-09 | Completed | 2020-07-06 | 2020-08-09 | -34 | Behind Schedule | Completed | 2020-08-10 | 2020-11-20 | Completed | 2021-01-21 | Completed
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 | E.5014730.02 | 5785961 | FICL | 08W | [6 empty] | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 7320 | 0 | 7320 | 1.3864 | 0.6464 | 0 | 1.3864 | 0 | 7525 | 0 | 1.4252 | 0 |  | 2704457 | 0.1 | 2704456.9 | 0 | 2704456.9 | 1460911.6 | 0 | 1243545.3 | On/Under Budget | Budget Allocated | 397410 | 392132 | 5278 | 392132 | 5278 | 1702142.5 | 63946.3 | 59365.4 | 4580.9 | 0 | 313 | 1309697.1 | 150901.4 | 0 | 0 | 13260 | 8106 | 41819 | 22958 | 5394 | 63946 | 236650 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 152819 | BL-1 | BL-1 35116800_CWSP - MIWUK 1702 - LR 6018 - PH 1.2_08W - Dec. 2020 | 2020-12-29 | 2020-03-12 | Completed | 2020-03-31 | 2020-03-31 | Completed | 2020-04-13 | Completed | 2020-07-22 | Completed | 2020-07-16 | 2020-07-16 | Completed | 2020-07-16 | 2020-07-29 | Completed | 2020-08-03 | 2020-08-03 | Completed | 2020-08-10 | Completed |  |  |  |  | 2020-08-10 | Completed | 2021-01-08 | Completed | 2021-01-08 | Completed | 2021-04-07 | 2021-02-04 | 62 | On/ Ahead Schedule | Completed |  |  |  | 2021-11-03 | Not Started
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 | E.5015533.01 | 5786479 | FICL | 08W | [6 empty] | 2020 |  | SH | CHICO | North Valley Assets | 0 | 12656 | 0 | 12656 | 2.397 | 0 | 0 | 2.397 | -3.1006e-15 | 12656 | 12656 | 2.397 | 2.397 |  | 6272666 | 1474481.8 | 4798184.2 |  |  | 4355392 | 51818.9 | 390973.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1421 | -1421 | 1421 | -1421 | 4379076.4 | 0 | -23684.4 | 23684.4 | 0 | 1210655.5 | 3167000 | -22263.5 | 0 | 0 | 51 | 1726 | -1390 | 864 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | E.5014730.04 | 5785963 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | SONORA | Yosemite Assets | 0 | 11704 | 0 | 11704 | 2.2167 | 0 | 0 | 2.2167 | 0 | 11739 | 1260 | 2.2233 | 0.23864 |  | 2559279 | -288433.8 | 2847712.8 |  |  | 2462861.1 | 0 | 384851.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 53034.5 | 51876 | 1158.5 | 51876 | 1158.5 | 2507479.6 | 0 | -143.9 | 143.9 | 0 | 331.3 | 2455272.4 | 7257.6 | 0 | 0 | 368 | 700 | 1748 | 3167 | 1420 | 0 | 44475 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 152750 | BL-1 | BL-1 35116802_CWSP - MIWUK 1702 - LR 6018 - PH 1.4_08W - Dec. 2020 | 2020-12-22 | 2020-02-20 | Completed | 2020-02-21 | 2020-03-17 | Completed | 2020-03-31 | Completed | 2020-06-10 | Completed | 2020-05-11 | 2020-05-11 | Completed | 2020-05-11 | 2020-05-29 | Completed | 2020-06-08 | 2020-06-19 | Completed | 2020-06-16 | Completed |  |  |  |  | 2020-06-16 | Completed | 2020-09-17 | Completed | 2020-09-17 | Completed | 2020-09-17 | 2020-09-17 | 0 | On/ Ahead Schedule | Completed | 2020-09-30 | 2020-09-30 | Completed | 2021-11-09 | Not Started
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | E.5014730.06 | 5785965 | FICL | 08W | [6 empty] | 2020 |  | SH | SONORA | Yosemite Assets | 0 | 5368 | 0 | 5368 | 1.0167 | 0 | 0 | 1.0167 | 0 | 5387 | 5340 | 1.0203 | 1.0114 |  | 1868187 | -1868186.6 | 3736373.6 |  |  | 2915885.8 | 0 | 820487.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 37382 | 39853 | -2471 | 39853 | -2471 | 2943855.6 | 0 | -6808 | 6808 | 0 | 3300.2 | 2900702.4 | 11883.2 | 0 | 0 | 0 | 15790 | 2901 | 0 | 0 | 0 | 0 | 21162 | 0 | 0 | 0 | 0
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | E.5015568.02 | 5785721 | FICL | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 10010 | 0 | 10010 | 1.8958 | 1.8958 | 0 | 1.6667 | 0.22917 | 10013 | 0 | 1.8964 | 0 |  | 5273989 | 1248322.6 | 4025666.4 |  |  | 1786831.8 | 64163.7 | 2174670.9 | On/Under Budget | Budget Allocated | 2520547.9 | 2501241 | 19306.9 | 2501241 | 19306.9 | 3538155.5 | 1 | -1322.7 | 1323.7 | 0 | 0 | 1036914.8 | 749916.9 | 0 | 0 | 138184 | 180505 | 355845 | 68390 | 8316 | 1 | 0 | 0 | 1000000 | 750000 | 0 | 0 | 2021-06-18 | 157117 | BL-1 | BL-1 35115151_CWSP - Brunkswick 1103 LR50070 ZONE-PH2.2_08W - Mar. 2021 | 2021-03-07 | 2020-05-29 | Completed | 2020-07-09 | 2020-07-18 | Completed | 2020-06-05 | Completed | 2020-07-21 | Completed | 2020-07-24 | 2020-07-24 | Completed | 2020-07-27 | 2020-07-28 | Completed | 2020-06-29 | 2020-07-31 | Completed | 2020-08-17 | Completed |  |  |  |  | 2020-08-17 | Completed | 2021-04-15 | Completed | 2021-04-15 | Completed | 2021-07-05 | 2021-05-20 | 46 | On/ Ahead Schedule | Completed | 2021-06-17 | 2021-07-19 | In Progress | 2021-08-25 | Not Started
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | E.5015569.02 | 5785657 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | GRSSVLLY | Fire Risk Mitigation Memo Account | 0 | 9416 | 0 | 9416 | 1.7833 | 0 | 0 | 1.7833 | 0 | [5 empty] | 5231108 | 1374305.6 | 3856802.4 |  |  | 3166565.9 | 14890.5 | 675346 | On/Under Budget | Project is not in the WP or in 2020 WP | 88800 | 91126 | -2326 | 91126 | -2326 | 3196687.4 | 0 | -1863.8 | 1863.8 | 0 | 145465.8 | 2960095.5 | 61004.7 | 0 | 0 | 38607 | 10193 | 9213 | 2140 | 2716 | 0 | 0 | 0 | 0 | 0 | 14129 | 14129 | 2021-06-18 | 151680 | BL-2 | BL-2 35115155_CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 - Nov. 2020 | 2020-11-24 | 2019-11-14 | Completed | 2019-12-17 | 2020-01-15 | Completed | 2019-12-29 | Completed | 2020-03-13 | Completed | 2020-03-13 | 2020-03-13 | Completed | 2020-01-13 | 2020-01-24 | Completed | 2020-01-06 | 2020-05-26 | Completed | 2020-01-13 | Completed |  |  |  |  | 2020-01-13 | Completed | 2020-02-28 | Completed | 2020-02-06 | Completed | 2021-02-26 | 2021-02-25 | 1 | On/ Ahead Schedule | Completed | 2021-04-02 | 2021-04-15 | Completed | 2021-08-16 | Not Started
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | E.5015569.03 | 5785718 | FICL | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 10035 | 0 | 10035 | 1.9006 | 0 | 0 | 1.9006 | 0 | 10244 | 9844 | 1.9402 | 1.8644 |  | 1357699.57 | -3130976.63 | 4488676.2 |  |  | 3207846.6 | 0 | 1280829.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 37751 | 37617 | 134 | 37617 | 134 | 3225204.9 | 0 | 0 | 0 | 0 | 290688.2 | 2896900 | 20258.4 | 0 | 0 | 15232 | 2518 | 7554 | -5046 | 0 | 0 | 0 | 0 | 0 | 0 | 8679 | 8679
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | E.5015569.04 | 5785719 | FICL | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY | Sierra Assets | 0 | 9456 | 0 | 9456 | 1.7909 | 0 | 0 | 1.7909 | 0 | 15728 | 10162 | 2.9788 | 1.9246 |  | 1580553.38 | -2668498.02 | 4249051.4 |  |  | 3814674.9 | 0 | 434376.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 34847 | 34526 | 321 | 34526 | 321 | 3834354.4 | 0 | 0 | 0 | 0 | 1985 | 3797843.4 | 14846.6 | 0 | 0 | 14829 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9840 | 9840
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 | E.5014773.02 | 5785976 | FICL | 08W | [6 empty] | 2021 | 2021 | SH | SONORA | Yosemite Assets | 0 | 11036 | 0 | 11036 | 2.0902 | 0.70606 | 0 | 2.0902 | 0 | 10932 | 0 | 2.0705 | 0 |  | 3920203 | -52067.2 | 3972270.2 |  |  | 1923067.5 | 0 | 2049202.7 | On/Under Budget | Budget Allocated | 435000 | 432766 | 2234 | 432766 | 2234 | 1966605.3 | 70195.9 | 64943.9 | 5252 | 0 | 1425.3 | 1532414.3 | 389228 | 0 | 0 | 210049 | 28962 | 43611 | 28048 | 13615 | 70196 | 4650 | 33636 | 0 | 0 | 0 | 0 | 2021-06-18 | 152817 | BL-2 | BL-2 35116391_CWSP - MIWUK 1702 - OCB - PH 1.2_08W - Dec 2020 | 2020-12-29 | 2020-02-25 | Completed | 2020-02-28 | 2020-03-20 | Completed | 2020-04-20 | Completed | 2020-04-20 | Completed | 2020-06-01 | 2020-07-01 | Completed | 2020-06-15 | 2020-06-22 | Completed | 2020-03-27 | 2020-04-21 | Completed | 2020-06-22 | Completed |  |  |  |  | 2020-06-22 | Completed | 2021-01-15 | Completed | 2021-02-04 | Completed | 2021-04-01 | 2021-01-15 | 76 | On/ Ahead Schedule | Completed | 2021-01-15 | 2021-01-15 | Completed | 2021-10-28 | Not Started
35114048 | OCGC CWSP - PINE GROVE 1102 - LR1222 | E.5014742.03 | 5785997 | FICL | 08W | [6 empty] | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 7344 | 0 | 7344 | 1.3909 | 1.3909 | 0 | 1.3909 | 0 | 7344 | 7344 | 1.3909 | 1.3909 |  | 4178929 | 1045029.6 | 3133899.4 |  |  | 1289910.8 | 123994.4 | 1719994.2 | On/Under Budget | Budget Allocated | 1810131 | 494319 | 1315812 | 494319 | 1315812 | 1414382.8 | 0 | -124472 | 124472 | 0 | 0 | 920063.8 | 369847.1 | 0 | 0 | 102650 | 69494 | 120786 | 61749 | 139641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154913 | BL-0 | BL-0 35114048_CWSP - PINE GROVE 1102 - LR1222 - PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-02 | Completed | 2020-06-26 | 2020-07-16 | Completed | 2020-06-08 | Completed | 2020-07-16 | Completed | 2020-07-28 | 2020-07-31 | Completed | 2020-07-31 | 2020-08-11 | Completed | 2020-07-21 | 2020-10-03 | Completed | 2020-08-14 | Completed |  |  |  |  | 2020-08-12 | Completed | 2021-05-05 | Completed | 2021-04-20 | Completed | 2021-05-07 | 2021-05-06 | 1 | On/ Ahead Schedule | Completed | 2021-05-12 | 2021-06-18 | Completed | 2021-06-16 | Completed
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | E.5014742.04 | 5785998 | FICL | 08W | [6 empty] | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 8389 | 0 | 8389 | 1.5888 | 0.82992 | 0 | 1.5888 | 0 | 8392 | 8392 | 1.5894 | 1.5894 |  | 2193681.27 | -1129156.03 | 3322837.3 |  |  | 1119066.5 | 59534 | 2144236.8 | On/Under Budget | Budget Allocated | 1168197.9 | 157697 | 1010500.9 | 157697 | 1010500.9 | 1195026.1 | 0 | -75959.6 | 75959.6 | 0 | 470.6 | 1036858.3 | 81737.7 | 0 | 0 | 4201 | 7561 | 8918 | 129472 | 7545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154914 | BL-0 | BL-0 35114049_CWSP - PINE GROVE 1102 - LR1222 - PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-04-24 | Completed | 2020-05-22 | 2020-06-09 | Completed | 2020-06-08 | Completed | 2020-06-29 | Completed | 2020-07-02 | 2020-07-02 | Completed | 2020-07-03 | 2020-07-24 | Completed | 2020-06-30 | 2020-07-22 | Completed | 2020-07-21 | Completed |  |  |  |  | 2020-07-21 | Completed | 2021-04-22 | Completed | 2020-08-18 | Completed | 2021-03-01 | 2021-04-23 | -53 | Behind Schedule | Completed | 2021-05-03 | 2021-05-07 | Completed | 2021-06-16 | Completed
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | E.5014745.04 | 5785993 | FICL | 08W | [6 empty] | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 6188 | 0 | 6188 | 1.172 | 0 | 0 | 1.172 | 0 | 7126 | 7126 | 1.3496 | 1.3496 |  | 2867650 | 828308.7 | 2039341.3 |  |  | 1314329.6 | 0 | 725011.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 20929 | -20929 | 20929 | -20929 | 1314329.6 | 0 | 0 | 0 | 0 | 676.8 | 1292723.3 | 20929.4 | 0 | 0 | 24841 | -192 | 1466 | -1040 | -4146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-03-19 | 154916 | BL-0 | BL-0 35114042_CWSP - PINE GROVE 1102 - LR1222 - PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-04-08 | Completed | 2020-05-04 | 2020-05-19 | Completed | 2020-04-13 | Completed | 2020-05-19 | Completed | 2020-06-05 | 2020-06-12 | Completed | 2020-06-12 | 2020-06-17 | Completed | 2020-06-03 | 2020-06-26 | Completed | 2020-06-18 | Completed |  |  |  |  | 2020-06-19 | Completed | 2020-08-25 | Completed | 2020-08-25 | Completed | 2020-08-25 | 2020-08-25 | 0 | On/ Ahead Schedule | Completed | 2020-08-25 | 2020-09-01 | Completed | 2021-03-18 | Completed
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 | E.5014745.05 | 5785994 | FICL | 08W | [6 empty] | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 5542 | 0 | 5542 | 1.0496 | 0 | 0 | 1.0496 | 0 | 5998 | 5998 | 1.136 | 1.136 |  | 2617141 | 669630.6 | 1947510.4 |  |  | 838536.1 | 0 | 1108974.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 33831 | -33831 | 33831 | -33831 | 870861.5 | 0 | -32325.4 | 32325.4 | 0 | 213.7 | 836816.5 | 1505.9 | 0 | 0 | 68 | 11592 | 19812 | 2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-03-19 | 154959 | BL-0 | BL-0 35114043_CWSP - PINE GROVE 1102 - LR1222 - PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-04-24 | Completed | 2020-05-18 | 2020-05-19 | Completed | 2020-05-13 | Completed | 2020-06-10 | Completed | 2020-06-05 | 2020-06-05 | Completed | 2020-06-11 | 2020-06-19 | Completed | 2020-06-12 | 2020-07-10 | Completed | 2020-06-17 | Completed |  |  |  |  | 2020-06-17 | Completed | 2020-08-14 | Completed | 2020-08-14 | Completed | 2020-08-14 | 2020-08-14 | 0 | On/ Ahead Schedule | Completed | 2020-08-14 | 2020-08-28 | Completed | 2021-03-24 | Completed
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | E.5014745.06 | 5785995 | FICL | 08W | [6 empty] | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 5790 | 0 | 5790 | 1.0966 | 1.0966 | 0 | 1.0966 | 0 | 6126 | 6126 | 1.1602 | 1.1602 |  | 3012702 | 776765.3 | 2235936.7 |  |  | 1121203 | 0 | 1114733.7 | On/Under Budget | Budget Allocated | 20105.2 | 64830 | -44724.8 | 64830 | -44724.8 | 1136188.6 | 0 | -14985.6 | 14985.6 | 0 | 213.7 | 1071144.6 | 49844.7 | 0 | 0 | 2717 | 4860 | 56356 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154889 | BL-1 | BL-1 35114044_CWSP - PINE GROVE 1102 - LR1222 - PH 1.6_08W - DD 210108 Feb. 2021 | 2021-01-22 | 2020-04-15 | Completed | 2020-06-02 | 2020-07-16 | Completed | 2020-05-13 | Completed | 2020-07-16 | Completed | 2020-07-29 | 2020-07-29 | Completed | 2020-07-29 | 2020-08-28 | Completed | 2020-07-20 | 2020-09-03 | Completed | 2020-08-12 | Completed |  |  |  |  | 2020-08-12 | Completed | 2021-02-24 | Completed | 2020-08-26 | Completed | 2021-02-23 | 2021-02-25 | -2 | Behind Schedule | Completed | 2021-03-04 | 2021-03-05 | Completed | 2021-06-25 | Not Started
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 | E.5015489.06 | 5786204 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 7775 | 0 | 7775 | 1.4725 | 0 | 0 | 1.4725 | 0 | 7619 | 7962 | 1.443 | 1.508 |  | 3424639 | 486127 | 2938512 |  |  | 2008695.5 | 0 | 929816.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 143225.4 | 61577 | 81648.4 | 61577 | 81648.4 | 2008687.2 | 0 | 8.3 | -8.3 | 0 | 2239.3 | 1944870.8 | 61585.4 | 0 | 0 | 20063 | 35213 | 1601 | 5156 | -457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 | 141388 | BL-0: | BL-0: 35114104_CWSP - Camp Evers 2106 - LR5020 - PH 2.6_08W - Mar 20 | 2020-03-16 | 2019-10-29 | Completed | 2019-12-31 | 2020-01-16 | Completed | 2020-02-06 | Completed | 2020-02-06 | Completed | 2020-01-06 | 2020-02-20 | Completed | 2020-01-16 | 2020-02-20 | Completed | 2020-02-14 | 2020-06-26 | Completed | 2020-02-14 | Completed |  |  |  |  | 2020-02-14 | Completed | 2020-06-11 | Completed | 2020-06-11 | Completed | 2020-07-31 | 2020-06-11 | 50 | On/ Ahead Schedule | Completed | 2020-06-19 | 2020-06-19 | Completed | 2021-05-21 | Not Started
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 | E.5015489.03 | 5786132 | FICL | 08W | [6 empty] | 2020 |  | SH | SALINAS | Central Coast Assets | 0 | 6873 | 0 | 6873 | 1.3017 | 0 | 0 | 1.3017 | 0 | 6873 | 0 | 1.3017 | 0 |  | 2641148 | 424112.4 | 2217035.6 |  |  | 1277987.9 | 0 | 939047.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 50472.6 | 496 | 49976.6 | 496 | 49976.6 | 1277987.9 | 0 | 0 | 0 | 0 | 633.6 | 1276858.1 | 496.1 | 0 | 0 | -599 | 915 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | E.5015567.02 | 5785725 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 6478 | 0 | 6478 | 1.2269 | 0 | 0 | 1.2269 | 0 | 7076 | 6200 | 1.3402 | 1.1742 |  | 5398830 | 1783865.7 | 3614964.3 |  |  | 1602705.2 | 0 | 2012259.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 34829 | 34508 | 321 | 34508 | 321 | 1622384.7 | 0 | 0 | 0 | 0 | 2731.2 | 1585145.3 | 14828.7 | 0 | 0 | 14829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9840 | 9840 | 2021-06-18 | 145891 | BL-0 | BL-0 35115147_CWSP - BRUNSWICK 1103 LR50070 ZONE-PH 3.2_08W - SEPT 2020 | 2020-07-26 | 2020-02-25 | Completed | 2020-03-18 | 2020-06-18 | Completed | 2020-03-06 | Completed | 2020-03-16 | Completed | 2020-03-24 | 2020-03-24 | Completed | 2020-05-15 | 2020-05-15 | Completed | 2020-05-29 | 2020-06-04 | Completed | 2020-05-05 | Completed |  |  |  |  | 2020-05-05 | Completed | 2020-08-12 | Completed | 2020-08-13 | Completed | 2020-09-15 | 2020-08-13 | 33 | On/ Ahead Schedule | Completed | 2020-08-13 | 2020-08-20 | Completed | 2021-02-08 | Completed
35110372 | BR-03-04-W (E) SWEETBRIAR PARB |  | 5786123 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 558171.9 | -491828.1 | 1050000 |  |  | 958292.8 | 0 | 91707.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -1953 | 1953 | -1953 | 1953 | 962387.8 | 0 | -4095 | 4095 | 0 | 521430.4 | 442909.9 | -6047.5 | 0 | 0 | 0 | 0 | 0 | 0 | -1953 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | E.5014534.04 | 5786054 | FICL | 08W | [6 empty] | 2021 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 3807 | 0 | 3807 | 0.72102 | 0.72102 | 0 | 0.72102 | 0 | 3807 | 4013 | 0.72102 | 0.76004 |  | 2054719 | 474898 | 1579821 |  |  | 1363310.1 | 0 | 216510.9 | On/Under Budget | Budget Allocated | 183849 | 402430 | -218581 | 402430 | -218581 | 1363002.1 | 0 | 308 | -308 | 0 | 1516.3 | 959055.8 | 402738 | 0 | 0 | 32512 | 108870 | 115647 | 140861 | 4540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 156104 | BL-A | BL-A 35113108_CWSP - Los Gatos 1106 - LB44 - Phase 2.4D_08W - Feb. 2021 | 2021-02-20 | 2019-10-31 | Completed | 2020-04-02 | 2020-04-30 | Completed | 2020-02-24 | Completed | 2020-02-24 | Completed | 2020-03-25 | 2020-05-08 | Completed | 2020-04-01 | 2020-08-06 | Completed | 2020-04-21 | 2020-06-03 | Completed | 2020-08-03 | Completed |  |  |  |  | 2020-08-03 | Completed | 2021-04-15 | Completed | 2021-04-13 | Completed | 2021-06-30 | 2021-04-15 | 76 | On/ Ahead Schedule | Completed | 2021-04-19 | 2021-04-23 | Completed | 2021-06-04 | Completed
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | E.5014319.04 | 5786051 | FICL | 08W | [6 empty] | 2020 |  | SH | CUPRTINO | De Anza Assets | 0 | 3782 | 0 | 3782 | 0.71629 | 0 | 0 | 0.71629 | 0 | 3582 | 3782 | 0.67841 | 0.71629 |  | 1425671 | 0 | 1425671 |  |  | 1401897.3 | 0 | 23773.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 11000 | 5894 | 5106 | 5894 | 5106 | 1401897.3 | 0 | 0 | 0 | 0 | 171437.1 | 1224566.2 | 5894 | 0 | 0 | 52 | 735 | 4570 | 511 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212401 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 369.6 | 0 | 369.6 | 0.07 | 0 | 0 | 0.07 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | -62161121 | 62161121 | -62161121 | 62161121 | [10 empty] | -62998113 | 39521433 | -5565360 | -8138345 | -24980737 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212402 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 20644.8 | 0 | 20644.8 | 3.91 | 0 | 0 | 3.91 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 479519 | -479519 | 479519 | -479519 | [10 empty] | 15984 | 15595 | 46325 | 15660 | 385956 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212403 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 24288 | 0 | 24288 | 4.6 | 0 | 0 | 4.6 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 564140 | -564140 | 564140 | -564140 | [10 empty] | 18805 | 18347 | 54500 | 18424 | 454066 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212404 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 33369.6 | 0 | 33369.6 | 6.32 | 0 | 0 | 6.32 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 775080 | -775080 | 775080 | -775080 | [10 empty] | 25836 | 25207 | 74878 | 25313 | 623847 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212405 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 69062.4 | 0 | 69062.4 | 13.08 | 0 | 0 | 13.08 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1604121 | -1604121 | 1604121 | -1604121 | [10 empty] | 53470 | 52168 | 154968 | 52387 | 1291127 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212406 | FRRB MONTICELLO1101-SETTLEMENT RULE ONLY |  | 5793892 | FICL | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 1.55 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 190091 | -190091 | 190091 | -190091 | [10 empty] | 6336 | 6182 | 18364 | 6208 | 153001 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35181924 | BUCOCAMPTUG ROE RD/WILSON LN PARADISE |  | 5791246 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 1788 | -1788 | 1788 | -1788 | [10 empty] | 15131 | -13344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35179069 | BUCOCAMPTUG WILDWOOD LN PARADISE |  | 5791246 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 114310 | -114310 | 114310 | -114310 | [10 empty] | 32740 | 48587 | -32738 | 32986 | 32736 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35179328 | BUCOCAMPTUG SUN RIVER CT PARADISE |  | 5791246 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 172556 | -172556 | 172556 | -172556 | [10 empty] | 27480 | 147640 | -3149 | 585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35181318 | BUCOCAMPTUG 6650 WHITTALL LN PARADISE |  | 5791246 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 37285 | -37285 | 37285 | -37285 | [10 empty] | 2135 | 36695 | -2011 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35181319 | BUCOCAMPTUG STINSON LN PARADISE |  | 5791246 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 90750 | -90750 | 90750 | -90750 | [10 empty] | 0 | 74372 | 16378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240478 | *CANC*ANAKA 1101 - K4 PH4.13 |  | 5797102 | FICL | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
74022040 | 2019 CALISTOGA 1101 HIGH SPLICE COUNT |  | 5782596 | FICL | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 6652.8 | 0 | 6652.8 | 1.26 | 0 | 0 | 1.26 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74021963 | CWSP - OAKLAND K 1102 OCB ZONE | E.5014543.01 | 5782579 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | OAKLAND | East Bay Assets | 0 | 14577.5 | 0 | 14577.5 | 2.7609 | 0 | 0 | 2.7609 | 0 | 15088 | 14748 | 2.8576 | 2.7932 |  | 8217834 | 0 | 8217834 |  |  | 8063207.4 | 0 | 154626.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -168393 | 168393 | -168393 | 168393 | 8063207.4 | 0 | 0 | 0 | 310407.9 | 7141950.5 | 779241.7 | -168392.7 | 0 | 0 | -171798 | -1771 | 4404 | 0 | 772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 147017 | BL-0 | BL-0 74021963_Oakland K 1102_08W - JULY 2020 | 2020-08-11 | 2019-05-20 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-04-28 | Completed | 2019-09-16 | Completed | 2019-08-12 | 2019-08-12 | Completed |  |  |  | 2019-09-03 | 2019-09-20 | Completed | 2019-08-26 | Completed |  |  |  |  | 2019-08-26 | Completed |  |  | 2020-04-06 | Completed | 2020-07-31 | 2020-06-02 | 59 | On/ Ahead Schedule | Completed |  |  |  | 2021-06-18 | Not Started
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | 5783322 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 2530 | -2530 | 2530 | -2530 | [10 empty] | 528 | 503 | 503 | 499 | 499 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | 5783286 | FICL | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 526 | -526 | 526 | -526 | [10 empty] | 110 | 105 | 105 | 104 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A | E.5014772.01 | 5782858 | FICL | 08W | [6 empty] | 2020 | 2020 | SH | NAPA | North Bay Assets | 0 | 5108 | 0 | 5108 | 0.96742 | 0 | 0 | 0.96742 | 0 | 5124 | 5124 | 0.97045 | 0.97045 |  | 2850000 | 0.4 | 2849999.6 |  |  | 2692677.1 | 0 | 157322.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 114558 | -114558 | 114558 | -114558 | 2692677.1 | 0 | 0 | 0 | 15808.3 | 309965.1 | 2252345.5 | 114558.3 | 0 | 0 | 1150 | 0 | 113409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161782 | BL-A: | BL-A: 74022390_CWSP - SILVERADO 2104- LR722-PH 1A_08W - Jun 21 | 2021-06-21 | 2019-08-08 | Completed | 2019-08-20 | 2019-08-21 | Completed | 2019-09-02 | Completed | 2019-08-19 | Completed | 2019-08-23 | 2019-08-26 | Completed | 2019-10-01 | 2019-10-02 | Completed | 2019-09-17 | 2019-09-17 | Completed | 2019-12-02 | Completed |  |  |  |  | 2019-12-02 | Completed | 2019-12-04 | Completed | 2020-05-21 | Completed | 2020-05-21 | 2020-05-21 | 0 | On/ Ahead Schedule | Completed | 2020-05-25 | 2020-05-29 | Completed | 2021-06-18 | Not Started
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT | E.5019956.01 | 5743253 | MAPP | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA | North Bay Assets | 0 | 13780 | 0 | 13780 | 2.6098 | 0 | 0 | 2.6098 | 0 | [5 empty] | 1714904 | 1714904 | 0 |  |  | 3308298 | 0 | -3308298 | OverRun | Project is not in the WP or in 2020 WP | 0 | 2992 | -2992 | 2992 | -2992 | 3308290.9 | 0 | 7.1 | -7.1 | 0 | 3260744.3 | 44554.5 | 2999.2 | 0 | 0 | 1845 | 7 | 7 | 1126 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161710 | B1 - | B1 - 74024171_Calistoga 1101 - Petrified Forest Rd._08W - 06162021 | 2021-06-16 | 2019-06-10 | Completed | 2019-08-13 | 2019-08-14 | Completed | 2019-08-23 | Completed | 2019-08-14 | Completed | 2019-08-15 | 2019-08-15 | Completed | 2019-08-21 | 2019-08-21 | Completed | 2019-08-20 | 2019-08-20 | Completed | 2019-09-03 | Completed |  |  |  |  | 2019-09-03 | Completed |  |  | 2020-05-13 | Completed | 2020-05-13 | 2020-05-13 | 0 | On/ Ahead Schedule | Completed |  |  |  | 2021-07-19 | Not Started
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | 5539479 | MAPP | 08W | [6 empty] | 2021 |  | SH - Remote Grid | OAKHURST | Yosemite Assets | 0 | 430 | 0 | 430 | 0.081439 | 0.081439 | 0 | 0.081439 | 0 | [5 empty] | 1676000 | 103000 | 1573000 |  |  | 1477805.2 | 79569.8 | 15625 | On/Under Budget | Budget Allocated | 1400000 | 1388967 | 11033 | 1388967 | 11033 | 1572773.1 | 25939 | -69028.9 | 94967.9 | 0 | 0 | 183806.2 | 1293999.1 | 0 | 0 | 76344 | 63893 | 473947 | 96965 | 651879 | 25939 | 0 | 0 | 0 | 0 | 0 | 0
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 | E.5014726.06 | 5786011 | MAPP | 08W | [6 empty] | 2020 |  | SH | JACKSON | Stockton Assets | 0 | 11757 | 0 | 11757 | 2.2267 | 0 | 0 | 2.2267 | 0 | 11757 | 0 | 2.2267 | 0 |  | 4620298 | 1421971 | 3198327 |  |  | 1072865.7 | 0 | 2125461.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -17890 | 17890 | -17890 | 17890 | 1105873.1 | 0 | -33007.4 | 33007.4 | 0 | 1292.8 | 1122470.1 | -50897.2 | 0 | 0 | 4139 | 1610 | 1418 | -25283 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154933 | BL-0 | BL-0 35113102_CWSP - WEST POINT 1101 -LR 13444- PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-03-20 | Completed | 2020-05-01 | 2020-05-19 | Completed | 2020-05-13 | Completed | 2020-05-19 | Completed | 2020-07-31 | 2020-07-31 | Completed | 2020-07-31 | 2020-08-21 | Completed | 2020-07-10 | 2020-07-17 | Completed | 2020-08-24 | Completed |  |  |  |  | 2020-08-24 | Completed | 2020-10-03 | Completed | 2020-09-10 | Completed | 2020-10-03 | 2020-10-03 | 0 | On/ Ahead Schedule | Completed | 2020-10-03 | 2020-10-03 | Completed | 2021-06-18 | Not Started
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | E.5015420.02 | 5785652 | MAPP | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 6871 | 0 | 6871 | 1.3013 | 0 | 0 | 1.3013 | 0 | 6653 | 0 | 1.26 | 0 |  | 5238478 | 2274925.7 | 2963552.3 |  |  | 2214930.1 | 0 | 748622.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 46057 | 28943 | 46057 | 28943 | 2214930.1 | 0 | 0 | 0 | 0 | 58059.4 | 2110813.4 | 46057.3 | 0 | 0 | 12643 | -25483 | 89340 | 12207 | -42650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157115 | BL-1 | BL-1 35112425_CWSP - El Dorado 2101 - OCB Zone - Ph 1.2_08W - Mar. 2021 | 2021-03-07 | 2019-10-23 | Completed | 2020-02-10 | 2020-02-19 | Completed | 2020-01-03 | Completed | 2020-01-03 | Completed | 2020-03-02 | 2020-03-02 | Completed | 2020-03-09 | 2020-06-04 | Completed | 2020-02-28 | 2020-07-23 | Completed | 2020-05-04 | Completed |  |  |  |  | 2020-05-05 | Completed | 2020-07-13 | Completed | 2020-07-13 | Completed | 2020-07-21 | 2020-07-21 | 0 | On/ Ahead Schedule | Completed | 2020-08-21 | 2020-08-21 | Completed | 2021-07-01 | Not Started
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 | E.5015489.02 | 5786131 | MAPP | 08W | [6 empty] | 2021 | 2020 | SH | SALINAS | Central Coast Assets | 0 | 5020 | 0 | 5020 | 0.95076 | 0.95076 | 0 | 0.95076 | 0 | 5487 | 5487 | 1.0392 | 1.0392 |  | 2501285 | 556888.1 | 1944396.9 |  |  | 694736.3 | 49498 | 1200162.6 | On/Under Budget | Budget Allocated | 298329.3 | 296259 | 2070.3 | 296259 | 2070.3 | 697164.2 | 3293.1 | 865.2 | 2427.9 | 0 | 7067.3 | 393838.1 | 293830.9 | 0 | 0 | 16145 | 9339 | 5573 | 119260 | 142648 | 3293 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157099 | BL-0 | BL-0 35114100_CWSP - Camp Evers 2106 - LR5020 - PH 2.2_08W - Mar. 2021 | 2021-03-07 | 2020-05-18 | Completed | 2020-05-20 | 2020-05-28 | Completed | 2020-06-12 | Completed | 2020-06-26 | Completed | 2020-05-29 | 2020-07-14 | Completed | 2020-06-15 | 2020-07-24 | Completed | 2020-06-01 | 2020-11-30 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2021-05-11 | Completed | 2021-05-11 | Completed | 2021-11-17 | 2021-05-11 | 190 | On/ Ahead Schedule | Completed | 2021-05-12 | 2021-05-14 | Completed | 2021-11-10 | Not Started
35114051 | OCGC PINE GROVE 1102 - LR1222 - PH | E.5014742.06 | 5786000 | MAPP | 08W | [6 empty] | 2021 |  | SH | JACKSON | Stockton Assets | 0 | 7698 | 0 | 7698 | 1.458 | 1.458 | 0 | 1.4371 | 0.020833 | 7698 | 7698 | 1.458 | 1.458 |  | 5342998 | 1393320.2 | 3949677.8 |  |  | 1165030.5 | 5715.3 | 2778932 | On/Under Budget | Budget Allocated | 2575321 | 669391 | 1905930 | 669391 | 1905930 | 1271979.8 | 68200.3 | -7366.2 | 75566.5 | 0 | 470.6 | 602117.9 | 562442 | 0 | 0 | 4524 | 20701 | 136934 | 153807 | 253844 | 68200 | 25133 | 2083 | 2083 | 2083 | 0 | 0 | 2021-06-18 | 154954 | BL-0 | BL-0 35114051_CWSP - PINE GROVE 1102 - LR1222 - PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-19 | Completed | 2020-07-14 | 2020-07-27 | Completed | 2020-07-28 | Completed | 2020-07-29 | Completed | 2020-08-31 | 2020-08-31 | Completed | 2020-09-01 | 2020-11-30 | Completed | 2020-08-25 | 2020-10-10 | Completed | 2020-10-02 | Completed |  |  |  |  | 2020-10-02 | Completed | 2021-05-19 | Completed | 2021-05-20 | Completed | 2022-06-14 | 2021-05-26 | 384 | On/ Ahead Schedule | Completed | 2021-06-21 | 2021-06-28 | Not Started | 2021-06-28 | Not Started
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | E.5015567.06 | 5786518 | MAPP | 08W | [6 empty] | 2021 | 2020 | SH | GRSSVLLY | Sierra Assets | 0 | 11395 | 0 | 11395 | 2.1581 | 2.1581 | 0 | 2.0606 | 0.097538 | 11395 | 0 | 2.1581 | 0 |  | 5778810 | 1303103 | 4475707 |  |  | 2694939.7 | 35343.4 | 1745423.9 | On/Under Budget | Budget Allocated | 2450191 | 2448638 | 1553 | 2448638 | 1553 | 4261545.9 | 8073.2 | 15467 | -7393.8 | 0 | 4056.8 | 1808850.8 | 882032.1 | 0 | 0 | 122363 | 148848 | 205641 | 243868 | 145845 | 8073 | 0 | 0 | 0 | 1000000 | 574000 | 0 | 2021-06-18 | 159407 | BL-2_ | BL-2_35117443_CWSP - Brunkswick 1103 LR50070 ZONE-PH3.6_08W_Apr.2021 | 2021-04-22 | 2020-06-23 | Completed | 2020-07-07 | 2020-07-08 | Completed | 2020-07-10 | Completed | 2020-07-08 | Completed | 2020-07-08 | 2020-07-08 | Completed | 2020-07-15 | 2020-07-15 | Completed | 2020-07-06 | 2020-07-10 | Completed | 2020-07-28 | Completed |  |  |  |  | 2020-07-28 | Completed | 2021-04-13 | Completed | 2020-12-03 | Completed | 2021-07-12 | 2021-04-13 | 90 | On/ Ahead Schedule | Completed | 2021-05-14 | 2021-06-30 | In Progress | 2021-11-03 | Not Started
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | 5530175 | MAPP | 08W | [6 empty] | Not in the WP | 2019 | SH | STROSA | Sonoma Assets | 0 | 2580 | 0 | 2580 | 0.48864 | 0 | 0 | 0.48864 | 0 | [5 empty] | 1092540 | 317223.4 | 775316.6 |  |  | 657653.9 | 0 | 117662.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 13144 | -13144 | 13144 | -13144 | 664758.5 | 7222.2 | 117.6 | 7104.6 | 34250.3 | 847580.9 | -230698.4 | 6039.8 | 0 | 0 | 407 | 0 | 0 | 2970 | 2546 | 7222 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 128631 | WSHP | WSHP 190307 - 31275658_DUNBAR 1102_08W - B1 | 2019-03-07 | 2019-03-13 | Completed | 2019-03-08 | 2019-03-21 | Completed | 2019-04-25 | Completed | 2019-09-26 | Completed | 2019-09-26 | 2019-09-27 | Completed | 2019-04-10 | 2019-04-15 | Completed | 2019-08-05 | 2019-08-05 | Completed | 2019-08-06 | Completed |  |  |  |  | 2019-08-06 | Completed |  |  | 2019-08-30 | Completed | 2019-07-29 | 2019-08-30 | -32 | Behind Schedule | Completed | 2019-06-28 | 2019-07-12 | Completed | 2021-07-19 | Not Started
35043299 | CWSP-OH COND RPLC: EEL RIVER 1102 FU1907 |  | 5533649 | MAPP | 08W | [6 empty] | Not in the WP | 2019 | SH | FORTUNA | Humboldt Division Assets | 0 | 6376 | 0 | 6376 | 1.2076 | 0 | 0 | 1.2076 | 0 | [5 empty] | 1224411 | 0.4 | 1224410.6 |  |  | 1211548.4 | 0 | 12862.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1211548.4 | 0 | 0 | 0 | 928 | 1200028.6 | 10591.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 128577 | WSHP | WSHP 190307 - 35043299_EEL RIVER 1102 FU1907_08W - B1 | 2019-03-07 | 2019-06-20 | Completed | 2019-07-03 | 2019-07-04 | Completed | 2019-07-26 | Completed | 2019-07-11 | Completed | 2019-09-05 | 2019-09-06 | Completed |  |  |  | 2019-09-04 | 2019-09-04 | Completed | 2019-09-09 | Completed |  |  |  |  | 2019-09-09 | Completed |  |  | 2019-11-27 | Completed | 2019-10-07 | 2019-11-27 | -51 | Behind Schedule | Completed |  |  |  | 2021-08-09 | Not Started
35061709 | SILVERADO 2104 RECONDUCTOR PROJECT |  | 5786199 | MAPP | 08W | [6 empty] | Not in the WP | 2019 | SH | NAPA |  | 0 | 8003 | 0 | 8003 | 1.5157 | 0 | 0 | 1.5157 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1104 | -1104 | 1104 | -1104 | [10 empty] | 0 | 0 | 0 | 0 | 1104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2019-02-26 | Completed | 2019-04-26 | 2019-04-26 | Completed | 2019-06-03 | Completed | 2019-08-13 | Completed | 2019-08-19 | 2019-08-20 | Completed | 2019-10-21 | 2019-10-22 | Completed | 2019-10-11 | 2019-10-11 | Completed | 2019-10-23 | Completed |  |  |  |  | 2019-10-23 | Completed |  |  | 2019-12-14 | Completed | 2020-06-02 | 2019-12-14 | 171 | On/ Ahead Schedule | Completed | 2021-07-20 | 2021-08-02 | Not Started | 2021-09-08 | Not Started
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | E.5015687.05 | 5785648 | MAPP | 08W | [6 empty] | 2020 | 2020 | SH | PLCRVLLE | Sierra Assets | 0 | 7924 | 0 | 7924 | 1.5008 | 0 | 0 | 1.5008 | 0 | 7924 | 7924 | 1.5008 | 1.5008 |  | 3756886 | 1013726 | 2743160 |  |  | 2250576.8 | 0 | 492583.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 75000 | 76299 | -1299 | 76299 | -1299 | 2313538.8 | 0 | 132 | -132 | 0 | 3552.1 | 2233688.1 | 13336.6 | 0 | 0 | 2812 | 9093 | 252 | 915 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 63094 | 2021-06-11 | 145865 | BL-0 | BL-0 35112434_CWSP - El Dorado 2102 - LR 19562 - Ph 1.4_08W - Nov 2020 | 2020-07-25 | 2020-04-10 | Completed | 2020-05-05 | 2020-05-20 | Completed | 2020-03-02 | Completed | 2020-05-20 | Completed | 2021-06-11 | 2021-06-11 | Not Started | 2020-05-26 | 2020-06-12 | Completed | 2020-06-24 | 2020-08-20 | Completed | 2020-07-27 | Completed |  |  |  |  | 2020-07-27 | Completed | 2020-10-02 | Completed | 2020-10-02 | Completed | 2020-11-02 | 2020-10-02 | 31 | On/ Ahead Schedule | Completed | 2020-10-12 | 2020-10-16 | Completed | 2021-08-03 | Not Started
35112076 | OCGC FULTON 1107-OH TO UG MARK W SPG |  | 5786045 | MAPP | 08W | [6 empty] | 2020 |  | SH | STROSA |  | 3657 | 7969 | 0 | 11626 | 2.2019 | 0 | 0 | 2.2019 | 3.4451e-16 | 11799 | 11799 | 2.2347 | 2.2347 | [10 empty] | Project is not in the WP or in 2020 WP | 0 | 2220 | -2220 | 2220 | -2220 | [10 empty] | 0 | 0 | 0 | 2220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35110369 | BR-03-03-W (E) GINNY_SUNRISE PARB |  | 5786123 | MAPP | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1081333.96 | -758871.04 | 1840205 |  |  | 1718830.7 | 0 | 121374.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1718830.7 | 0 | 0 | 0 | 0 | 784828.4 | 934002.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35099654 | BR-04-01-W (E) SUNSET DR PARB |  | 5786123 | MAPP | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 527505.94 | 27505.94 | 500000 |  |  | 408676.2 | 0 | 91323.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 278974 | -278974 | 278974 | -278974 | 404444.1 | 0 | 4232.1 | -4232.1 | 0 | 626349 | -500878.2 | 283205.6 | 0 | 0 | 199153 | 14463 | 65358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35105647 | BR-03-09-W (E) MERRILL RD PARB |  | 5786123 | MAPP | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1294583.67 | -355416.33 | 1650000 |  |  | 1597585.5 | 0 | 52414.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1595820.9 | 0 | 1764.6 | -1764.6 | 0 | 1382657.9 | 213163 | 1764.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103617 | BR-07-09-W (E) WOODGLEN PARB |  | 5786123 | PEND | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 4528627.2 | 60605.2 | 4468022 |  |  | 1142816.1 | 0 | 3325205.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2021095 | -2021095 | 2021095 | -2021095 | 2021094.8 | 273391.7 | 122407.2 | 150984.5 | 0 | 0 | 0 | 1142816.1 | 0 | 0 | 0 | 0 | 34521 | 386204 | 599684 | 273392 | 251486 | 248962 | 226846 | 0 | 0 | 0
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 | E.5015394.01 | 5785246 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5899 | 0 | 5899 | 1.1172 | 0 | 0 | 0 | 1.1172 | [5 empty] | 1059112.65 | -1306840.45 | 2365953.1 |  |  | 110078.7 | 561723.2 | 1694151.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4853 | -4853 | 4853 | -4853 | 1455751.1 | 99.8 | -24310.8 | 24410.6 | 0 | 16758.1 | 112878.7 | -19558.1 | 1321261.8 | 0 | 311 | 2072 | 718 | 713 | 940 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154917 | BL-0 | BL-0 35095167_CWSP - STANISLAUS 1702 - LR1888 - PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-07 | Completed | 2020-07-30 | 2020-08-13 | Completed | 2022-02-22 | Not Started | 2022-02-23 | Not Started | 2022-02-02 | 2022-02-02 | Not Started | 2022-02-03 | 2022-02-16 | Not Started | 2020-11-05 | 2022-02-07 | In Progress | 2022-03-14 | Not Started |  |  |  |  | 2022-03-14 | Not Started | 2022-04-19 | Not Started | 2022-05-03 | Not Started | 2022-05-09 | 2022-05-09 | 0 | On/ Ahead Schedule | Not Started | 2022-05-18 | 2022-05-31 | Not Started | 2022-06-29 | Not Started
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 | E.5015701.01 | 5785247 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6718 | 0 | 6718 | 1.2723 | 0 | 0 | 0 | 1.2723 | [5 empty] | 1296538.52 | 1046538.52 | 250000 |  |  | 116939.2 | 0 | 133060.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -21670 | 21670 | -21670 | 21670 | 1954897.2 | 0 | -12674.1 | 12674.1 | 0 | 14217.5 | 137065.6 | -34343.9 | 1825283.9 | 0 | -24856 | 688 | 901 | 685 | 912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154922 | BL-B | BL-B 35095168_CWSP - STANISLAUS 1702 - LR1888 - PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-11 | Completed | 2020-10-28 | 2022-02-07 | Not Started | 2022-02-07 | Not Started | 2022-02-08 | Not Started | 2022-02-08 | 2022-02-08 | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2020-10-23 | 2022-02-07 | In Progress | 2022-03-02 | Not Started |  |  |  |  | 2022-03-02 | Not Started | 2022-04-21 | Not Started | 2022-05-05 | Not Started | 2022-08-05 | 2022-08-05 | 0 | On/ Ahead Schedule | Not Started | 2022-08-08 | 2022-08-19 | Not Started | 2022-09-27 | Not Started
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | E.5014540.01 | 5785245 | PEND | 08W | [6 empty] | 2022 |  | SH | ANGLSCMP | Stockton Assets | 172 | 9383 | 0 | 9555 | 1.8097 | 0 | 1.8097 | 0 | 1.8097 | 10124 | 0 | 1.9174 | 0 |  | 3142865.56 | 2892865.56 | 250000 |  |  | 210751.3 | 0 | 39248.7 | On/Under Budget | Budget Allocated | 500000 | 49381 | 450619 | 49381 | 450619 | 3623850.3 | 2031.9 | 0 | 2031.9 | 0 | 27301.9 | 147122.6 | 36326.8 | 3400045 | 0 | 11009 | 15688 | 3812 | 3983 | 1835 | 2032 | 2050 | 2058 | 2067 | 2075 | 2083 | 690 | 2021-06-18 | 154906 | BL-B | BL-B 35094513_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-29 | Completed | 2021-02-08 | 2021-03-04 | Completed | 2021-10-05 | Not Started | 2021-10-06 | Not Started | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2021-12-22 | Not Started | 2021-10-20 | 2021-11-30 | Not Started | 2021-12-30 | Not Started |  |  |  |  | 2021-12-30 | Not Started | 2022-03-08 | Not Started | 2022-03-09 | Not Started | 2021-10-07 | 2022-05-09 | -214 | Behind Schedule | Not Started | 2022-05-10 | 2022-05-23 | Not Started | 2022-06-27 | Not Started
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | E.5014760.01 | 5785244 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6756 | 0 | 6756 | 1.2795 | 0 | 0 | 0 | 1.2795 | [5 empty] | 262500 | 0 | 262500 |  |  | 68716 | 0 | 193784 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4621 | -4621 | 4621 | -4621 | 88611.6 | 82.7 | 0 | 82.7 | 0 | 9725.4 | 54961.6 | 4028.9 | 19303.5 | 0 | 395 | 377 | 377 | 2267 | 613 | 83 | 85 | 85 | 85 | 85 | 85 | 85 | 2021-06-18 |  |  |  |  | 2020-08-04 | Completed | 2021-12-02 | 2021-12-02 | Not Started | 2021-06-18 | Not Started | 2021-12-09 | Not Started | 2021-12-02 | 2021-12-02 | Not Started | 2021-12-03 | 2021-12-23 | Not Started | 2021-07-09 | 2021-07-16 | Not Started | 2022-01-13 | Not Started |  |  |  |  | 2022-01-13 | Not Started | 2022-04-01 | Not Started | 2022-05-02 | Not Started | 2022-07-01 | 2022-07-01 | 0 | On/ Ahead Schedule | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-08-23 | Not Started
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 | E.5014748.01 | 5785242 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10300 | 0 | 10300 | 1.9508 | 0 | 0 | 0 | 1.9508 | [5 empty] | 250000 | 0 | 250000 |  |  | 477119.2 | 0 | -227119.2 | OverRun | Project is not in the WP or in 2020 WP | 0 | 425058 | -425058 | 425058 | -425058 | 512063.5 | 134.3 | 132 | 2.3 | 0 | 14805.1 | 38082.2 | 424231.8 | 34118 | 0 | 20624 | 1493 | -19846 | 88675 | 333154 | 134 | 137 | 137 | 137 | 137 | 137 | 137 | 2021-06-18 | 155000 | BL-A | BL-A 35094516_CWSP - ORO FINO 1101 OCB PH 1.1_08W - Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2022-06-24 | 2022-06-30 | Not Started | 2021-07-16 | Not Started | 2022-06-30 | Not Started | 2022-07-01 | 2022-07-01 | Not Started | 2022-07-04 | 2022-07-08 | Not Started | 2021-07-02 | 2021-07-02 | Not Started | 2022-07-18 | Not Started |  |  |  |  | 2022-07-18 | Not Started | 2022-08-11 | Not Started | 2022-08-23 | Not Started | 2022-11-15 | 2022-11-15 | 0 | On/ Ahead Schedule | Not Started | 2022-11-16 | 2022-11-29 | Not Started | 2023-01-05 | Not Started
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 | E.5014747.01 | 5785241 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7634 | 0 | 7634 | 1.4458 | 0 | 0 | 0 | 1.4458 | [5 empty] | 333333 | 0 | 333333 |  |  | 81583.6 | 0 | 251749.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5903 | -5903 | 5903 | -5903 | 104753.8 | 249.6 | 132 | 117.6 | 0 | 7879.9 | 69449.3 | 4254.4 | 21522.2 | 0 | 40598 | -38026 | 428 | 564 | 558 | 250 | 255 | 255 | 255 | 255 | 255 | 255 | 2021-06-18 | 155001 | BL-A | BL-A 35094517_CWSP - ORO FINO 1101 OCB PH 2.1_08W - Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2022-06-17 | 2022-06-17 | Not Started | 2021-07-01 | Not Started | 2022-06-20 | Not Started | 2022-06-20 | 2022-06-20 | Not Started | 2022-06-21 | 2022-06-21 | Not Started | 2021-06-21 | 2021-06-21 | Not Started | 2022-06-29 | Not Started |  |  |  |  | 2022-06-29 | Not Started | 2022-07-04 | Not Started | 2022-07-13 | Not Started | 2022-07-15 | 2022-07-15 | 0 | On/ Ahead Schedule | Not Started | 2022-07-18 | 2022-07-22 | Not Started | 2022-09-06 | Not Started
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | E.5014719.01 | 5785225 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 132 | 3625 | 0 | 3757 | 0.71155 | 0 | 0 | 0 | 0.71155 | [5 empty] | 250000 | 0 | 250000 |  |  | 106262.6 | 0 | 143737.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4268 | -4268 | 4268 | -4268 | 122850.6 | 104.8 | 132 | -27.2 | 0 | 9178.3 | 93436.1 | 3648.2 | 15968.3 | 0 | 796 | 659 | 599 | 735 | 728 | 105 | 108 | 108 | 108 | 108 | 108 | 108 | 2021-06-18 |  |  |  |  | 2020-08-01 | Completed | 2022-07-08 | 2022-07-14 | Not Started | 2022-07-01 | Not Started | 2022-07-21 | Not Started | 2022-07-08 | 2022-07-08 | Not Started | 2022-07-11 | 2022-09-30 | Not Started | 2022-07-05 | 2022-07-06 | Not Started | 2022-10-31 | Not Started |  |  |  |  | 2022-10-31 | Not Started | 2022-11-09 | Not Started | 2022-12-09 | Not Started | 2023-01-03 | 2023-01-03 | 0 | On/ Ahead Schedule | Not Started | 2023-01-04 | 2023-01-17 | Not Started | 2023-02-23 | Not Started
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 | E.5014718.01 | 5785226 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 6398 | 0 | 6398 | 1.2117 | 0 | 0 | 0 | 1.2117 | [5 empty] | 1563870.91 | 1313870.91 | 250000 |  |  | 150677.1 | 0 | 99322.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8976 | -8976 | 8976 | -8976 | 181816.9 | 932.2 | 0 | 932.2 | 0 | 13737.6 | 134610.1 | 2329.5 | 24493.2 | 0 | -1429 | 851 | 851 | 984 | 1073 | 932 | 943 | 947 | 951 | 924 | 958 | 993 | 2021-06-18 |  |  |  |  | 2022-07-07 | Not Started | 2022-07-22 | 2022-07-28 | Not Started | 2022-07-21 | Not Started | 2022-08-04 | Not Started | 2022-07-08 | 2022-07-08 | Not Started | 2022-07-11 | 2022-09-30 | Not Started | 2022-07-22 | 2022-07-28 | Not Started | 2022-10-31 | Not Started |  |  |  |  | 2022-10-31 | Not Started | 2022-12-30 | Not Started | 2023-01-19 | Not Started | 2023-01-24 | 2023-01-24 | 0 | On/ Ahead Schedule | Not Started | 2023-01-27 | 2023-02-09 | Not Started | 2023-03-16 | Not Started
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | P.12006 | 5533644 | PEND | 08W | [6 empty] | 2022 |  | SH | STCRUZ | Central Coast Assets | 0 | 4470 | 0 | 4470 | 0.84659 | 0 | 0.84659 | 0 | 0.84659 | 4555 | 0 | 0.86269 | 0 |  | 5136422 | 2235896 | 2900526 |  |  | 86400.3 | 0 | 2814125.7 | On/Under Budget | Budget Allocated | 1353842.8 | 1439319 | -85476.2 | 1439319 | -85476.2 | 1513804.8 | 7446.2 | 489 | 6957.2 | 0 | 38211 | 36274.8 | 11914.5 | 0 | 0 | 1248 | 2389 | 493 | 4213 | 3083 | 7446 | 407930 | 1002923 | 2399 | 2399 | 2399 | 2399 | 2021-06-18 | 128557 | WSHP | WSHP 190307 - 35015705_R2 OH RECONDUCTR ROB ROY 2105 -S027CC118_08W - B1 | 2019-03-07 | 2019-06-25 | Completed |  |  | Completed | 2022-09-30 | Not Started | 2022-10-20 | Not Started | [6 empty] | 2019-12-13 | 2019-12-13 | Completed | 2022-10-21 | Not Started |  |  |  |  | 2019-08-05 | Completed |  |  | 2023-02-08 | Not Started | 2021-06-04 | 2023-06-16 | -742 | Behind Schedule | Not Started |  |  |  | 2023-08-17 | Not Started
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 | E.5015029.05 | 5785161 | PEND | 08W | [6 empty] | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 0 | 3625 | 0 | 3625 | 0.68655 | 0 | 0 | 0 | 0.68655 | [5 empty] | 45454 | 0 | 45454 |  |  | 30540 | 0 | 14914 | On/Under Budget | Budget Allocated | 2756 | 2919 | -163 | 2919 | -163 | 30540 | 0 | 0 | 0 | 0 | 2170.7 | 25450.1 | 2919.1 | 0 | 0 | 1234 | 1196 | 164 | 163 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159687 | BL-A2 | BL-A2: 35094391_CWSP - KONOCTI 1102-LR 532 PH 4_08W - Apr 21 | 2021-04-26 | 2020-01-10 | Completed | 2022-01-10 | 2022-01-21 | Not Started | 2020-01-16 | Completed | 2022-01-21 | Not Started | 2022-01-24 | 2022-01-24 | Not Started | 2022-01-25 | 2022-01-26 | Not Started | 2022-03-03 | 2022-03-16 | Not Started | 2022-04-04 | Not Started |  |  |  |  | 2022-04-04 | Not Started | 2022-04-15 | Not Started | 2022-04-20 | Not Started | 2022-06-20 | 2022-06-20 | 0 | On/ Ahead Schedule | Not Started | 2022-06-21 | 2022-07-04 | Not Started | 2022-08-10 | Not Started
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 | E.5015029.10 | 5785166 | PEND | 08W | [6 empty] | 2022 | 2022 | SH | LAKEPORT | Humboldt Division Assets | 0 | 4961 | 0 | 4961 | 0.93958 | 0 | 0 | 0 | 0.93958 | 4351 | 0 | 0.82405 | 0 |  | 687082.4 | 641628.4 | 45454 | 0 | 45454 | 34263.2 | 0 | 11190.8 | On/Under Budget | Budget Allocated | 11339 | 11339 | 0 | 11339 | 0 | 43183.5 | 0 | 0 | 0 | 0 | 736.1 | 30188.3 | 3338.8 | 920.3 | 0 | 1288 | 1459 | -30 | 216 | 406 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 2021-06-18 | 159688 | BL-A2 | BL-A2: 35094396_CWSP - KONOCTI 1102-LR 532 PH 9_08W - Apr 21 | 2021-04-26 | 2020-03-21 | Completed | 2021-06-18 | 2021-06-18 | Not Started | 2020-12-04 | Completed | 2021-06-18 | Not Started | 2021-06-21 | 2021-06-21 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-03-03 | 2022-03-14 | Not Started | 2022-04-05 | Not Started |  |  |  |  | 2022-04-05 | Not Started | 2022-04-28 | Not Started | 2022-05-03 | Not Started | 2022-08-18 | 2022-07-01 | 48 | On/ Ahead Schedule | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-08-23 | Not Started
35105653 | BR-14-01-W (E) SALIDA WAY, PARB |  | 5786123 | PEND | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 2505596.45 | -738101.55 | 3243698 |  |  | 2320584.7 | 0 | 923113.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1039368 | -1039368 | 1039368 | -1039368 | 2428026.6 | 108375.9 | 934 | 107441.9 | 0 | 5529.9 | 1383128.3 | 931926.4 | 0 | 0 | 319194 | 235349 | 222832 | -67300 | 220918 | 108376 | 0 | 0 | 0 | 0 | 0 | 0
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | E.5015417.01 | 5782532 | PEND | 08W | [6 empty] | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 1930 | 9322 | 0 | 11252 | 2.1311 | 0 | 2.1311 | 0 | 2.1311 | 8064 | 0 | 1.5273 | 0 |  | 725000 | 0 | 725000 |  |  | 598537.3 | 0 | 126462.7 | On/Under Budget | Budget Allocated | 6217.2 | 134342 | -128124.8 | 134342 | -128124.8 | 745119.2 | 1139.7 | 132 | 1007.7 | 5457.6 | 78836.1 | 492869.2 | 21374.4 | 33615 | 0 | 3628 | 4867 | 5452 | 3614 | 3682 | 1140 | 1160 | 1160 | 1160 | 1160 | 1160 | 106160 | 2021-06-18 | 158110 | BL-A_ | BL-A_35056733_CWSP - El Dorado 2101 - 19752 - Ph 1.1_08W_Mar.2021 | 2021-03-30 | 2020-08-31 | Completed | 2021-08-17 | 2022-03-21 | Not Started | 2021-08-16 | Not Started | 2022-04-11 | Not Started | 2021-07-27 | 2021-07-27 | Not Started | 2021-07-28 | 2021-08-17 | Not Started | 2021-08-10 | 2021-09-06 | Not Started | 2022-05-04 | Not Started |  |  |  |  | 2022-05-04 | Not Started | 2022-09-06 | Not Started | 2022-10-05 | Not Started | 2022-11-23 | 2022-12-21 | -28 | Behind Schedule | Not Started | 2022-12-22 | 2023-01-04 | Not Started | 2023-02-10 | Not Started
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | E.0000106.01 | 5782594 | PEND | 08W | [6 empty] | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 24027 | 0 | 24027 | 4.5506 | 0 | 0 | 0 | 4.5506 | [5 empty] | 176000 | 0 | 176000 |  |  | 91339 | 0 | 84661 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2617 | -2617 | 2617 | -2617 | 9291734.9 | 0 | 0 | 0 | 9826.4 | 32607.8 | 46287.6 | 2617.1 | 9200395.9 | 0 | 507 | 484 | 521 | 623 | 482 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | E.5015416.01 | 5782533 | PEND | 08W | [6 empty] | 2022 | 2022 | SH | PLCRVLLE | Sierra Assets | 3135 | 3779 | 0 | 6914 | 1.3095 | 0 | 1.3095 | 0 | 1.3095 | 7084 | 0 | 1.3417 | 0 |  | 3411094.96 | 2811094.96 | 600000 |  |  | 330938.5 | 0 | 269061.5 | On/Under Budget | Budget Allocated | 3587.9 | 4764 | -1176.1 | 4764 | -1176.1 | 337161.1 | 276.5 | 6166.1 | -5889.6 | 4921.4 | 31408.1 | 285613.9 | 8995.1 | 10453.5 | 0 | -8267 | 3069 | 3864 | 2037 | 2126 | 277 | 277 | 277 | 277 | 264 | 277 | 289 | 2021-06-18 | 158111 | BL-A1 | BL-A1_35057010_CWSP - El Dorado 2101 - 19752 - Ph 2.1_08W_Mar.2021 | 2021-03-30 | 2021-05-06 | Completed | 2021-06-18 | 2021-09-13 | Not Started | 2021-06-18 | Not Started | 2021-10-04 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2020-07-07 | 2020-07-17 | Completed | 2021-11-24 | Not Started |  |  |  |  | 2021-11-24 | Not Started | 2022-03-08 | Not Started | 2022-04-06 | Not Started | 2022-12-30 | 2022-06-07 | 206 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-07-28 | Not Started
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | E.5015414.01 | 5782535 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | PLCRVLLE | Sierra Assets | 12966 | 0 | 0 | 12966 | 2.4557 | 2.4557 | 0 | 0 | 2.4557 | 25090 | 0 | 4.7519 | 0 |  | 725000 | 0 | 725000 |  |  | 322885.3 | 22840.7 | 379274 | On/Under Budget | Budget Allocated | 16722.2 | 10475166 | -10458443.8 | 10501203 | -10484480.8 | 10750338.4 | 2933700.2 | 9808.1 | 2923892.1 | 4114.5 | 386046.8 | -141026.1 | 73750 | 0 | 0 | 45821 | 9178 | 2466 | 1487 | 4990 | 26786 | 29047 | 2940522 | 2050347 | 1735453 | 1739436 | 1889634 | 2021-06-18 | 158109 | BL-A_ | BL-A_35057018_CWSP - El Dorado 2101 - 19752 - Ph 4.1_08W_Mar.2021 | 2021-03-30 | 2020-07-17 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-07-15 | Not Started | 2021-08-12 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2021-07-09 | 2021-07-22 | Not Started | 2021-08-31 | Not Started |  |  |  |  | 2021-08-31 | Not Started | 2021-12-13 | Not Started | 2022-01-11 | Not Started | 2021-12-30 | 2022-01-27 | -28 | Behind Schedule | Not Started | 2022-01-28 | 2022-02-10 | Not Started | 2022-03-21 | Not Started
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | E.5014733.01 | 5785238 | PEND | 08W | [6 empty] | 2022 |  | SH | SONORA | Yosemite Assets | 0 | 8605 | 0 | 8605 | 1.6297 | 0 | 1.6297 | 0 | 1.6297 | 8378 | 0 | 1.5867 | 0 |  | 2768676 | 708455.8 | 2060220.2 |  |  | 129438.9 | 200 | 1930581.3 | On/Under Budget | Budget Allocated | 44404 | 45131 | -727 | 45131 | -727 | 1975892.6 | 318.7 | 420.2 | -101.5 | 2635.1 | 7757.3 | 74639.8 | 44406.6 | 1845729.3 | 0 | 3826 | 20393 | 392 | 18409 | 966 | 319 | 330 | 330 | 165 | 0 | 0 | 0 | 2021-06-18 | 151438 | BL-1 | BL-1 35052737_CWSP - MIWUK 1701 - LR 8060 - PH 1.1_08W - Nov. 2020 | 2020-11-12 | 2020-01-03 | Completed | 2020-05-07 | 2020-06-10 | Completed | 2021-10-05 | Not Started | 2020-05-12 | Completed | 2021-10-06 | 2021-10-07 | Not Started | 2021-10-08 | 2021-10-11 | Not Started | 2021-10-06 | 2021-11-02 | Not Started | 2022-01-04 | Not Started |  |  |  |  | 2022-01-04 | Not Started |  |  | 2022-03-01 | Not Started | 2021-10-25 | 2022-03-30 | -156 | Behind Schedule | Not Started | 2022-03-31 | 2022-04-13 | Not Started | 2022-05-20 | Not Started
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | E.5014726.01 | 5785230 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5885 | 0 | 5885 | 1.1146 | 0 | 0 | 0 | 1.1146 | [5 empty] | 1561814.97 | 1311814.97 | 250000 |  |  | 69294.9 | 0 | 180705.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8222 | -8222 | 8222 | -8222 | 1623149.6 | 0 | 0 | 0 | 2459 | 8746.7 | 49866.7 | 8222.4 | 1553854.7 | 0 | 2358 | 4693 | 392 | 390 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154928 | BL-B | BL-B 35043423_CWSP - WEST POINT 1101 -LR 13444- PH 2.1_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-05 | Completed | 2021-11-17 | 2021-12-28 | Not Started | 2022-02-04 | Not Started | 2022-02-07 | Not Started | 2021-12-29 | 2021-12-29 | Not Started | 2021-12-30 | 2021-12-31 | Not Started | 2021-11-19 | 2021-11-19 | Not Started | 2022-02-11 | Not Started |  |  |  |  | 2022-02-11 | Not Started |  |  | 2022-04-04 | Not Started | 2022-04-08 | 2022-04-08 | 0 | On/ Ahead Schedule | Not Started | 2022-04-07 | 2022-04-08 | Not Started | 2022-04-22 | Not Started
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | 5530164 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | WLLWCRK | Humboldt Division Assets | 0 | 6698 | 0 | 6698 | 1.2686 | 0 | 0 | 0 | 1.2686 | 6722 | 0 | 1.2731 | 0 |  | 776346.19 | 0.19 | 776346 |  |  | 153962.1 | 0 | 622383.9 | On/Under Budget | Request 2021 Budget | 0 | 3219 | -3219 | 624936 | -624936 | 776221.6 | 0 | 0 | 0 | 1784.2 | 20519.3 | 128982.3 | 2676.3 | 0 | 0 | 1050 | 1252 | 0 | 374 | 0 | 0 | 261 | 282 | 0 | 0 | 0 | 0 | 2021-06-18 | 159682 | BL-B2 | BL-B2: 35043296_Willow Creek_08W - Apr 21 | 2021-04-26 | 2020-05-22 | Completed | 2021-06-18 | 2021-07-01 | Not Started | 2019-07-16 | Completed | 2021-07-22 | Not Started | [6 empty] | 2022-01-03 | 2022-01-28 | Not Started | 2022-02-03 | Not Started |  |  |  |  | 2022-02-03 | Not Started |  |  | 2022-03-21 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2022-05-10 | Not Started
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | 5531041 | PEND | 08W | [6 empty] | Not in the WP | 2022 |  | HMOONBAY | Peninsula Assets | 838 | 3852 | 0 | 4690 | 0.88826 | 0 | 0 | 0 | 0.88826 | [5 empty] | 100000 | 0 | 100000 |  |  | 77930.3 | 0 | 22069.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 17946 | -17946 | 17946 | -17946 | 867944.7 | 1443.9 | 49.2 | 1394.7 | 16333.3 | 28294.6 | 25414.2 | 7888.1 | 779956.1 | 0 | 1618 | 3590 | 736 | 1066 | 829 | 1444 | 1444 | 1444 | 1444 | 1444 | 1444 | 1444 | 2021-06-18 | 161146 | BL-B: | BL-B: 35030568_TW ON HALF MOON BAY1101 FUCO 4141 - May 21 | 2021-05-28 | 2019-12-31 | Completed |  |  | Not Started | 2021-06-18 | Not Started | 2021-06-18 | Not Started | 2021-06-18 | 2021-06-18 | Not Started |  |  |  | 2021-12-28 | 2022-02-07 | Not Started | 2022-04-19 | Not Started |  |  |  |  | 2022-04-19 | Not Started |  |  | 2022-07-14 | Not Started | 2022-08-15 | 2022-08-15 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2022-11-09 | Not Started
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | 5782594 | PEND | 08W | [6 empty] | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 163000 | 0 | 163000 |  |  | 102904.2 | 0 | 60095.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2867 | -2867 | 2867 | -2867 | 510466.7 | 0 | 0 | 0 | 0 | 45023.6 | 55013.7 | 2866.9 | 407562.5 | 0 | 745 | 532 | 532 | 529 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | 5530164 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | FTBRAGG | Humboldt Division Assets | 0 | 2710 | 0 | 2710 | 0.51326 | 0.51326 | 0 | 0 | 0.51326 | 2710 | 0 | 0.51326 | 0 |  | 1115282 | 0 | 1115282 |  |  | 367272.9 | 0 | 748009.1 | On/Under Budget | Budget Allocated | 755085 | 757515 | -2430 | 757515 | -2430 | 1113243.1 | 215.8 | 253.4 | -37.6 | 3499 | 219550.1 | 131905.9 | 11544.4 | 0 | 0 | 2122 | 920 | 2672 | 3619 | 1959 | 216 | 220 | 215 | 247246 | 252292 | 246035 | 0 | 2021-06-18 | 159680 | BL-B2 | BL-B2: 31334291_Fort Brag 1101_08W - Apr 21 | 2021-04-26 | 2019-10-18 | Completed | 2019-03-08 | 2019-03-29 | Completed | 2021-01-22 | Completed | 2021-07-30 | Not Started | 2019-03-29 | 2019-04-05 | Completed | 2019-04-08 | 2019-04-12 | Completed | 2021-09-01 | 2021-09-14 | Not Started | 2021-10-01 | Not Started |  |  |  |  | 2021-10-01 | Not Started |  |  | 2021-11-01 | Not Started | 2021-09-15 | 2021-11-15 | -61 | Behind Schedule | Not Started | 2021-11-16 | 2021-11-29 | Not Started | 2022-01-05 | Not Started
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | 5530159 | PEND | 08W | [6 empty] | 2022 |  | SH | STCRUZ | Central Coast Assets | 0 | 5300 | 0 | 5300 | 1.0038 | 0 | 1.0038 | 0 | 1.0038 | 5300 | 0 | 1.0038 | 0 |  | 99000 | 0 | 99000 |  |  | 64512.7 | 0 | 34487.3 | On/Under Budget | Budget Allocated | 1196.1 | 1013609 | -1012412.9 | 1013609 | -1012412.9 | 1072429.9 | 7446.2 | 0 | 7446.2 | 3047.5 | 19106.1 | 36101.6 | 5691.5 | 0 | 0 | 117 | 218 | 633 | 2100 | 2624 | 7446 | 447393 | 543483 | 2399 | 2399 | 2399 | 2399 | 2021-06-18 | 128558 | WSHP | WSHP 190307 - 35015704_OH RECONDUCTR ROB ROY 2105 -S026CC117_08W - B1 | 2019-03-07 | 2019-04-11 | Completed |  |  | Not Started | 2019-03-21 | Completed | 2021-11-22 | Not Started | [6 empty] | 2019-12-13 | 2019-12-13 | Completed | 2022-01-04 | Not Started |  |  |  |  | 2022-01-04 | Not Started |  |  | 2022-01-18 | Not Started | 2021-05-11 | 2022-02-16 | -281 | Behind Schedule | Not Started |  |  |  | 2022-04-15 | Not Started
30977613 | WDDB OTTER 1102 PHASE 3 | P.06570 | 5530159 | PEND | 08W | [6 empty] | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 3637 | 0 | 3637 | 0.68883 | 0 | 0 | 0 | 0.68883 | [5 empty] | 355200 | 0 | 355200 |  |  | 300649.4 | 0 | 54550.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -6700 | 6700 | -6700 | 6700 | 1230469.4 | 0 | 0 | 0 | 19392.6 | 77331.5 | 199091.9 | -6700.3 | 929820 | 0 | 5361 | 0 | 0 | -12061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | E.5014540.07 | 5786035 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 7711 | 0 | 7711 | 1.4604 | 0 | 0 | 0 | 1.4604 | [5 empty] | 1575778.82 | 1450778.82 | 125000 |  |  | 74377.5 | 0 | 50622.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5793 | -5793 | 5793 | -5793 | 2161313.7 | 0 | 0 | 0 | 0 | 0 | 68584.3 | 5793.3 | 2086936.2 | 0 | 390 | 4008 | 391 | 389 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154912 | BL-B | BL-B 35116926_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-16 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-08 | Not Started | 2022-03-15 | Not Started | 2022-03-23 | 2022-03-23 | Not Started | 2022-03-24 | 2022-04-06 | Not Started | 2022-03-30 | 2022-04-26 | Not Started | 2022-04-11 | Not Started |  |  |  |  | 2022-04-11 | Not Started | 2022-06-07 | Not Started | 2022-06-21 | Not Started | 2022-08-22 | 2022-08-22 | 0 | On/ Ahead Schedule | Not Started | 2022-08-23 | 2022-09-05 | Not Started | 2022-10-12 | Not Started
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | E.5014540.02 | 5786030 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 8059 | 0 | 8059 | 1.5263 | 0 | 0 | 0 | 1.5263 | [5 empty] | 1152639.46 | 902639.46 | 250000 |  |  | 110317.1 | 0 | 139682.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8740 | -8740 | 8740 | -8740 | 2178813.9 | 153.1 | 0 | 153.1 | 0 | 0 | 101809.6 | 8507.5 | 2068264.3 | 0 | 2540 | 3879 | 886 | 617 | 586 | 153 | 79 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154907 | BL-B | BL-B 35116921_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-27 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-23 | Not Started | 2022-03-15 | Not Started | 2022-06-02 | 2022-06-02 | Not Started | 2022-06-03 | 2022-06-30 | Not Started | 2022-02-23 | 2022-04-05 | Not Started | 2022-07-08 | Not Started |  |  |  |  | 2022-07-08 | Not Started | 2022-09-05 | Not Started | 2022-09-19 | Not Started | 2022-11-18 | 2022-11-18 | 0 | On/ Ahead Schedule | Not Started | 2022-11-21 | 2022-12-02 | Not Started | 2023-01-10 | Not Started
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | E.5014540.03 | 5786031 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 6121 | 0 | 6121 | 1.1593 | 0 | 0 | 0 | 1.1593 | [5 empty] | 966585.11 | 841585.11 | 125000 |  |  | 71406.7 | 0 | 53593.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5662 | -5662 | 5662 | -5662 | 1573767.3 | 0 | 0 | 0 | 0 | 0 | 65744.7 | 5661.9 | 1502360.6 | 0 | 367 | 4184 | 372 | 369 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154908 | BL-B | BL-B 35116922_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-18 | Completed | 2020-10-30 | 2022-02-08 | Not Started | 2022-02-07 | Not Started | 2022-02-08 | Not Started | 2022-02-09 | 2022-02-09 | Not Started | 2022-02-10 | 2022-02-23 | Not Started | 2022-02-08 | 2022-03-07 | Not Started | 2022-04-08 | Not Started |  |  |  |  | 2022-04-08 | Not Started | 2022-05-30 | Not Started | 2022-05-30 | Not Started | 2022-09-28 | 2022-09-28 | 0 | On/ Ahead Schedule | Not Started | 2022-09-29 | 2022-10-12 | Not Started | 2022-11-18 | Not Started
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | E.5014540.05 | 5786033 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STOCKTON | Stockton Assets | 0 | 9910 | 0 | 9910 | 1.8769 | 0 | 0 | 0 | 1.8769 | [5 empty] | 1835218.36 | 1585218.36 | 250000 |  |  | 95288 | 0 | 154712 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2473 | -2473 | 2473 | -2473 | 2736495.2 | 0 | 0 | 0 | 0 | 605.7 | 92209.4 | 2472.8 | 2641207.2 | 0 | 524 | 489 | 489 | 486 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154910 | BL-B | BL-B 35116924_CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-12-08 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-01 | Not Started | 2022-03-15 | Not Started | 2022-03-16 | 2022-03-16 | Not Started | 2022-03-17 | 2022-03-30 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-04-07 | Not Started |  |  |  |  | 2022-04-07 | Not Started | 2022-06-03 | Not Started | 2022-06-17 | Not Started | 2022-08-18 | 2022-08-18 | 0 | On/ Ahead Schedule | Not Started | 2022-08-19 | 2022-09-01 | Not Started | 2022-10-10 | Not Started
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 | E.5014730.05 | 5785964 | PEND | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12083 | 0 | 12083 | 2.2884 | 0 | 0 | 0 | 2.2884 | [5 empty] | 200000 | 0 | 200000 |  |  | 170592.9 | 0 | 29407.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10533 | -10533 | 10533 | -10533 | 3042023.1 | 179.5 | 0 | 179.5 | 0 | 0 | 161356.2 | 9236.8 | 2870134.3 | 0 | 955 | 5513 | 927 | 921 | 921 | 180 | 186 | 186 | 186 | 186 | 186 | 186 | 2021-06-18 | 160675 | BL-A1 | BL-A1 35116803_CWSP - MIWUK 1702 - LR 6018 - PH 1.5_08W_ 2020 RESERVE - DD 210507 | 2021-05-13 | 2020-08-24 | Completed | 2022-01-24 | 2022-01-24 | Not Started | 2020-10-23 | Completed | 2022-01-24 | Not Started | 2022-01-24 | 2022-01-24 | Not Started | 2022-01-24 | 2022-01-24 | Not Started | 2022-01-31 | 2022-03-04 | Not Started | 2022-03-07 | Not Started |  |  |  |  | 2022-03-07 | Not Started | 2022-05-16 | Not Started | 2022-06-14 | Not Started | 2022-07-26 | 2022-07-26 | 0 | On/ Ahead Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-12-20 | Not Started
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 | E.5015394.03 | 5786042 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 2381 | 6855 | 0 | 9236 | 1.7492 | 0 | 0 | 0 | 1.7492 | [5 empty] | 1578304.87 | 1453304.87 | 125000 |  |  | 107344 | 0 | 17656 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 7974 | -7974 | 7974 | -7974 | 3037703.8 | 159.6 | 0 | 159.6 | 0 | 743.1 | 98869.6 | 7731.2 | 2930117.4 | 0 | 1073 | 3872 | 1206 | 601 | 980 | 160 | 83 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154919 | BL-B | BL-B 35116512_CWSP - STANISLAUS 1702 - LR1888 - PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-07-23 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-07 | Not Started | 2022-03-15 | Not Started | 2022-05-31 | 2022-05-31 | Not Started | 2022-06-01 | 2022-06-28 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-07-06 | Not Started |  |  |  |  | 2022-07-06 | Not Started | 2022-09-08 | Not Started | 2022-09-22 | Not Started | 2022-11-23 | 2022-11-23 | 0 | On/ Ahead Schedule | Not Started | 2022-11-24 | 2022-12-07 | Not Started | 2023-01-13 | Not Started
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 | E.5015394.04 | 5786043 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 11249 | 0 | 11249 | 2.1305 | 0 | 0 | 0 | 2.1305 | [5 empty] | 908863.93 | 783863.93 | 125000 |  |  | 90961.9 | 0 | 34038.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5456 | -5456 | 5456 | -5456 | 2894854.4 | 48.7 | 0 | 48.7 | 0 | 0 | 85630.4 | 5331.5 | 2803768.1 | 0 | 1689 | 1973 | 477 | 717 | 475 | 49 | 51 | 25 | 0 | 0 | 0 | 0 | 2021-06-18 | 154920 | BL-B | BL-B 35116513_CWSP - STANISLAUS 1702 - LR1888 - PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-10-01 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-02 | Not Started | 2020-10-12 | Completed | 2022-05-04 | 2022-05-04 | Not Started | 2022-05-05 | 2022-06-15 | Not Started | 2022-02-23 | 2022-03-29 | Not Started | 2022-08-10 | Not Started |  |  |  |  | 2022-08-10 | Not Started | 2022-10-06 | Not Started | 2022-10-20 | Not Started | 2022-12-21 | 2022-12-21 | 0 | On/ Ahead Schedule | Not Started | 2022-12-22 | 2023-01-04 | Not Started | 2023-02-10 | Not Started
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 | E.5015394.05 | 5786044 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10852 | 0 | 10852 | 2.0553 | 0 | 0 | 0 | 2.0553 | [5 empty] | 964490.61 | 839490.61 | 125000 |  |  | 109214.5 | 0 | 15785.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8422 | -8422 | 8422 | -8422 | 2919961.1 | 67.3 | 0 | 67.3 | 0 | 0 | 101034.8 | 8179.7 | 2810504.9 | 0 | 3912 | 2076 | 1005 | 609 | 578 | 67 | 70 | 70 | 35 | 0 | 0 | 0 | 2021-06-18 | 154921 | BL-B | BL-B 35116514_CWSP - STANISLAUS 1702 - LR1888 - PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-09-22 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-03-22 | Not Started | 2022-03-23 | Not Started | 2022-04-13 | 2022-04-13 | Not Started | 2022-04-14 | 2022-05-11 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-08-05 | Not Started |  |  |  |  | 2022-08-05 | Not Started | 2022-10-10 | Not Started | 2022-10-24 | Not Started | 2022-12-23 | 2022-12-23 | 0 | On/ Ahead Schedule | Not Started | 2022-12-26 | 2023-01-06 | Not Started | 2023-02-14 | Not Started
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 | E.5015701.03 | 5786037 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4825 | 0 | 4825 | 0.91383 | 0 | 0 | 0 | 0.91383 | [5 empty] | 1532501.31 | -706521.99 | 2239023.3 |  |  | 119433.1 | 0 | 2119590.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4731 | -4731 | 4731 | -4731 | 1538591.3 | 0 | -42969.3 | 42969.3 | 0 | 0 | 157671.6 | -38238.6 | 1376188.9 | 0 | 929 | 892 | 1105 | 918 | 887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154924 | BL-0 | BL-0 35116516_CWSP - STANISLAUS 1702 - LR1888 - PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-06-09 | Completed | 2020-07-23 | 2020-08-06 | Completed | 2020-06-16 | Completed | 2022-02-07 | Not Started | 2022-02-02 | 2022-02-02 | Not Started | 2022-02-03 | 2022-02-04 | Not Started | 2020-08-17 | 2022-02-07 | In Progress | 2022-02-22 | Not Started |  |  |  |  | 2022-02-22 | Not Started | 2022-04-04 | Not Started | 2022-04-18 | Not Started | 2022-08-12 | 2022-08-12 | 0 | On/ Ahead Schedule | Not Started | 2022-08-15 | 2022-08-26 | Not Started | 2022-10-04 | Not Started
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 | E.5015701.05 | 5786039 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 12677 | 0 | 12677 | 2.4009 | 0 | 0 | 0 | 2.4009 | [5 empty] | 2688006.56 | 2438006.56 | 250000 |  |  | 119228 | 0 | 130772 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 14934 | -14934 | 14934 | -14934 | 3119311.8 | 0 | 0 | 0 | 0 | 0 | 104294 | 14934 | 3000083.8 | 0 | 1708 | 11094 | 844 | 659 | 628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154926 | BL-B | BL-B 35116517_CWSP - STANISLAUS 1702 - LR1888 - PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-24 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-11 | Not Started | 2022-03-15 | Not Started | 2022-03-16 | 2022-03-16 | Not Started | 2022-03-17 | 2022-04-06 | Not Started | 2022-02-16 | 2022-03-30 | Not Started | 2022-04-14 | Not Started |  |  |  |  | 2022-04-14 | Not Started | 2022-06-17 | Not Started | 2022-07-01 | Not Started | 2022-10-21 | 2022-10-21 | 0 | On/ Ahead Schedule | Not Started | 2022-10-24 | 2022-11-04 | Not Started | 2022-12-13 | Not Started
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 | E.5015701.06 | 5786040 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10922 | 0 | 10922 | 2.0686 | 0 | 0 | 0 | 2.0686 | [5 empty] | 1631980.57 | 1381980.57 | 250000 |  |  | 121972.3 | 0 | 128027.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9724 | -9724 | 9724 | -9724 | 2778122.5 | 87.5 | 0 | 87.5 | 0 | 0 | 112335.5 | 9636.9 | 2656062.7 | 0 | 1468 | 6228 | 640 | 666 | 635 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154927 | BL-B | BL-B 35116518_CWSP - STANISLAUS 1702 - LR1888 - PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-10-29 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-03-01 | Not Started | 2022-03-15 | Not Started | 2022-05-11 | 2022-05-11 | Not Started | 2022-05-12 | 2022-06-08 | Not Started | 2022-02-23 | 2022-03-22 | Not Started | 2022-06-22 | Not Started |  |  |  |  | 2022-06-22 | Not Started | 2022-08-18 | Not Started | 2022-09-01 | Not Started | 2022-11-02 | 2022-11-02 | 0 | On/ Ahead Schedule | Not Started | 2022-11-03 | 2022-11-16 | Not Started | 2022-12-23 | Not Started
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 | E.5015701.04 | 5786038 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 9268 | 0 | 9268 | 1.7553 | 0 | 0 | 0 | 1.7553 | [5 empty] | 2253896.9 | 2003896.9 | 250000 |  |  | 85366 | 0 | 164634 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 26353 | -26353 | 26353 | -26353 | 2233003.7 | 0 | 0 | 0 | 0 | 0 | 59012.9 | 26353.1 | 2147637.7 | 0 | 22930 | 1979 | 484 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154925 | BL-B | BL-B 35116519_CWSP - STANISLAUS 1702 - LR1888 - PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-27 | Completed | 2020-10-28 | 2022-02-25 | Not Started | 2022-02-01 | Not Started | 2022-02-25 | Not Started | 2022-02-28 | 2022-02-28 | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2020-10-23 | 2022-02-07 | In Progress | 2022-03-22 | Not Started |  |  |  |  | 2022-03-22 | Not Started | 2022-05-13 | Not Started | 2022-05-13 | Not Started | 2022-09-28 | 2022-09-28 | 0 | On/ Ahead Schedule | Not Started | 2022-09-29 | 2022-10-12 | Not Started | 2022-11-18 | Not Started
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | E.5014733.04 | 5785968 | PEND | 08W | [6 empty] | 2022 |  | SH | SONORA | Yosemite Assets | 0 | 8005 | 0 | 8005 | 1.5161 | 0 | 1.5161 | 0 | 1.5161 | 7376 | 0 | 1.397 | 0 |  | 3489624 | 674982 | 2814642 |  |  | 124084 | 0 | 2690558 | On/Under Budget | Budget Allocated | 2815000 | 48520 | 2766480 | 48520 | 2766480 | 1656467.2 | 0 | -2219.5 | 2219.5 | 0 | 380.2 | 77402.9 | 46300.9 | 1530163.7 | 0 | 1624 | -1095 | 942 | 20825 | 26225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 145856 | BL-A: | BL-A: 35116385_CWSP - MIWUK 1701 - LR 8060 - PH 1.4_08W - Feb 2021 | 2020-07-24 | 2020-05-27 | Completed | 2022-05-24 | 2022-05-30 | Not Started | 2021-06-21 | Not Started | 2022-05-30 | Not Started | 2022-05-31 | 2022-05-31 | Not Started | 2022-06-01 | 2022-06-02 | Not Started | 2021-06-21 | 2021-07-16 | Not Started | 2022-09-23 | Not Started |  |  |  |  | 2022-09-23 | Not Started | 2022-11-08 | Not Started | 2022-12-06 | Not Started | 2021-02-05 | 2022-12-13 | -676 | Behind Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-01-03 | Not Started
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | E.5014733.05 | 5785969 | PEND | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 13109 | 0 | 13109 | 2.4828 | 0 | 0 | 0 | 2.4828 | [5 empty] | 1767022.83 | -2668338.97 | 4435361.8 |  |  | 456078.1 | 0 | 3979283.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 50720 | -50720 | 50720 | -50720 | 2652595.7 | 623.5 | 0 | 623.5 | 0 | 409.3 | 409455.9 | 46213 | 2192010.8 | 0 | 2799 | 8597 | 29687 | 2565 | 2565 | 624 | 647 | 647 | 647 | 647 | 647 | 647 | 2021-06-18 | 160677 | BL-1 | BL-1 35116388_CWSP - MIWUK 1701 - LR 8060 - PH 1.5_08W - DD 210507 | 2021-05-13 | 2020-05-06 | Completed | 2020-07-17 | 2020-07-17 | Completed | 2020-06-22 | Completed | 2020-08-04 | Completed | 2020-09-14 | 2020-09-14 | Completed | 2020-09-29 | 2020-09-29 | Completed | 2020-08-10 | 2020-11-02 | Completed | 2022-01-04 | Not Started |  |  |  |  | 2022-01-04 | Not Started | 2022-02-16 | Not Started | 2022-03-09 | Not Started | 2022-03-23 | 2022-03-23 | 0 | On/ Ahead Schedule | Not Started | 2022-03-24 | 2022-04-06 | Not Started | 2022-05-13 | Not Started
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | E.5014722.03 | 5785930 | PEND | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10614 | 0 | 10614 | 2.0102 | 0 | 0 | 0 | 2.0102 | [5 empty] | 5174348 | 1534666.2 | 3639681.8 |  |  | 65873 | 0 | 3573808.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8667 | -8667 | 8667 | -8667 | 2525524.4 | 79.3 | 0 | 79.3 | 0 | 206.2 | 57572.2 | 8094.6 | 2459078.7 | 0 | 513 | 6540 | 349 | 346 | 346 | 79 | 82 | 82 | 82 | 82 | 82 | 82 | 2021-06-18 | 160666 | BL-B1 | BL-B1 35116397_CWSP - MIWUK 1702 - LR 8090 - PH 1.3_08W - DD 210507 | 2021-05-13 | 2020-06-15 | Completed | 2020-08-25 | 2020-09-21 | Completed | 2020-08-06 | Completed | 2022-02-02 | Not Started | 2022-02-02 | 2022-02-15 | Not Started | 2022-02-16 | 2022-02-28 | Not Started | 2020-10-12 | 2020-12-04 | Completed | 2022-03-08 | Not Started |  |  |  |  | 2022-03-08 | Not Started | 2022-05-23 | Not Started | 2022-05-31 | Not Started | 2022-06-01 | 2022-06-01 | 0 | On/ Ahead Schedule | Not Started | 2022-06-03 | 2022-06-03 | Not Started | 2022-07-04 | Not Started
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 | E.5015235.06 | 5786026 | PEND | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6445 | 0 | 6445 | 1.2206 | 0 | 0 | 0 | 1.2206 | [5 empty] | 1602218.96 | 1352218.96 | 250000 |  |  | 64096.8 | 0 | 185903.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6092 | -6092 | 6092 | -6092 | 2660038.5 | 100 | 0 | 100 | 0 | 0 | 58726.8 | 5370.1 | 2595219.4 | 0 | 3353 | 360 | 937 | 360 | 360 | 100 | 104 | 104 | 104 | 104 | 104 | 104 | 2021-06-18 | 154964 | BL-B | BL-B 35115857_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-15 | Completed | 2022-05-09 | 2022-06-03 | Not Started | 2022-06-17 | Not Started | 2022-06-20 | Not Started | 2022-06-06 | 2022-06-06 | Not Started | 2022-06-07 | 2022-07-04 | Not Started | 2022-07-04 | 2022-07-15 | Not Started | 2022-08-09 | Not Started |  |  |  |  | 2022-08-09 | Not Started | 2022-10-05 | Not Started | 2022-10-19 | Not Started | 2022-06-24 | 2022-11-18 | -147 | Behind Schedule | Not Started | 2022-11-21 | 2022-12-02 | Not Started | 2023-01-10 | Not Started
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | E.5015236.04 | 5786020 | PEND | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 9186 | 0 | 9186 | 1.7398 | 0 | 0 | 0 | 1.7398 | [5 empty] | 3838828 | 916420.8 | 2922407.2 |  |  | 727841.8 | 0 | 2194565.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 30417 | -30417 | 30417 | -30417 | 1598129.6 | 782.7 | -91471.8 | 92254.5 | 0 | 0 | 790085.1 | -62243.4 | 777627.6 | 0 | 10274 | 4634 | 5140 | 4351 | 4830 | 783 | 406 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154968 | BL-0 | BL-0 35115849_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-04-24 | Completed | 2020-06-23 | 2020-07-16 | Completed | 2022-01-21 | Not Started | 2020-07-16 | Completed | 2020-08-26 | 2022-01-14 | In Progress | 2020-09-11 | 2020-10-02 | Completed | 2020-07-22 | 2020-09-04 | Completed | 2022-01-25 | Not Started |  |  |  |  | 2022-01-25 | Not Started | 2022-03-30 | Not Started | 2022-03-30 | Not Started | 2022-04-21 | 2022-04-29 | -8 | Behind Schedule | Not Started | 2022-05-02 | 2022-05-13 | Not Started | 2022-06-21 | Not Started
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | E.5015236.06 | 5786028 | PEND | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6354 | 0 | 6354 | 1.2034 | 0 | 0 | 0 | 1.2034 | [5 empty] | 1197165.97 | 947165.97 | 250000 |  |  | 104911 | 0 | 145089 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 22144 | -22144 | 22144 | -22144 | 2594345.1 | 135.8 | 0 | 135.8 | 0 | 398.5 | 82715.3 | 21797.3 | 2489087 | 0 | 13893 | 5189 | 1086 | 587 | 1043 | 136 | 141 | 70 | 0 | 0 | 0 | 0 | 2021-06-18 | 154970 | BL-B | BL-B 35115851_CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-09 | Completed | 2022-01-10 | 2022-02-04 | Not Started | 2022-02-23 | Not Started | 2022-02-24 | Not Started | 2022-02-07 | 2022-02-07 | Not Started | 2022-02-08 | 2022-03-07 | Not Started | 2022-03-07 | 2022-03-18 | Not Started | 2022-05-24 | Not Started |  |  |  |  | 2022-05-24 | Not Started | 2022-07-20 | Not Started | 2022-08-03 | Not Started | 2022-09-02 | 2022-09-02 | 0 | On/ Ahead Schedule | Not Started | 2022-09-05 | 2022-09-16 | Not Started | 2022-10-25 | Not Started
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | E.5014742.02 | 5785996 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 235 | 6519 | 0 | 6754 | 1.2792 | 0 | 0 | 0 | 1.2792 | [5 empty] | 1161832.82 | 536832.82 | 625000 |  |  | 266554.9 | 175228.8 | 183216.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 139577 | -139577 | 139577 | -139577 | 2105795.7 | 0 | -110239.9 | 110239.9 | 0 | 235.3 | 236982.3 | 29337.3 | 1729000.9 | 0 | 1295 | -22134 | 94975 | 46162 | 19279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154952 | BL-B | BL-B 35114046_CWSP - PINE GROVE 1102 - LR1222 - PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-11-17 | Completed | 2021-09-28 | 2021-10-25 | Not Started | 2022-01-31 | Not Started | 2022-02-01 | Not Started | 2021-10-26 | 2021-10-26 | Not Started | 2021-10-27 | 2021-11-23 | Not Started | 2021-10-19 | 2021-10-19 | Not Started | 2022-03-10 | Not Started |  |  |  |  | 2022-03-10 | Not Started | 2022-04-29 | Not Started | 2022-04-29 | Not Started | 2022-05-31 | 2022-05-31 | 0 | On/ Ahead Schedule | Not Started | 2022-05-09 | 2022-05-20 | Not Started | 2022-07-21 | Not Started
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | E.5014723.03 | 5785936 | PEND | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 11880 | 0 | 11880 | 2.25 | 0 | 0 | 0 | 2.25 | [5 empty] | 250000 | 0 | 250000 |  |  | 187350.3 | 0 | 62649.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 7346 | -7346 | 7346 | -7346 | 3723862.1 | 0 | 0 | 0 | 0 | 761.1 | 180743.5 | 5845.6 | 3535011.8 | 0 | 1168 | 1288 | 1059 | 1051 | 1279 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 2021-06-18 | 160671 | BL-A1 | BL-A1 35115047_CWSP - MIWUK 1701 - LR 10600 PH 1.3_08W - DD 210507 | 2021-05-13 | 2020-08-05 | Completed | 2020-11-20 | 2020-12-03 | Not Started | 2020-10-07 | Completed | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-20 | Not Started | 2021-12-23 | 2022-01-05 | Not Started | 2022-03-03 | Not Started |  |  |  |  | 2022-03-03 | Not Started | 2022-05-06 | Not Started | 2022-05-27 | Not Started | 2022-06-28 | 2022-06-28 | 0 | On/ Ahead Schedule | Not Started | 2022-06-29 | 2022-07-12 | Not Started | 2022-09-01 | Not Started
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | E.5014727.03 | 5786002 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4248 | 0 | 4248 | 0.80455 | 0 | 0 | 0 | 0.80455 | [5 empty] | 434937.21 | 89937.21 | 345000 |  |  | 94515.8 | 0 | 250484.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5785 | -5785 | 5785 | -5785 | 1556100.1 | 0 | 0 | 0 | 0 | 562.7 | 88168.5 | 5784.7 | 1461584.3 | 0 | 1351 | 2771 | 481 | 477 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154936 | BL-B | BL-B 35112973_CWSP - WEST POINT 1101 -LR 13444- PH 1.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-15 | Completed | 2021-12-09 | 2022-01-19 | Not Started | 2021-11-23 | Not Started | 2022-01-19 | Not Started | 2022-01-20 | 2022-01-20 | Not Started | 2022-01-21 | 2022-02-17 | Not Started | 2021-12-15 | 2021-12-15 | Not Started | 2022-02-25 | Not Started |  |  |  |  | 2022-02-25 | Not Started | 2022-04-15 | Not Started | 2022-04-15 | Not Started | 2022-05-17 | 2022-05-17 | 0 | On/ Ahead Schedule | Not Started | 2022-04-25 | 2022-05-06 | Not Started | 2022-07-07 | Not Started
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | E.5014727.07 | 5786006 | PEND | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6072 | 0 | 6072 | 1.15 | 0 | 0 | 0 | 1.15 | [5 empty] | 592701.09 | 247701.09 | 345000 |  |  | 76182.4 | 0 | 268817.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 62085 | -62085 | 62085 | -62085 | 1450609.9 | 51.5 | 0 | 51.5 | 0 | 0 | 14149.5 | 62033 | 1374376 | 0 | 43 | 1415 | 59805 | 386 | 386 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154940 | BL-B | BL-B 35112977_CWSP - WEST POINT 1101 -LR 13444- PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-29 | Completed | 2021-12-07 | 2022-01-17 | Not Started | 2022-01-10 | Not Started | 2022-01-17 | Not Started | 2022-01-18 | 2022-01-18 | Not Started | 2022-01-19 | 2022-02-15 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-02-23 | Not Started |  |  |  |  | 2022-02-23 | Not Started | 2022-04-19 | Not Started | 2022-04-19 | Not Started | 2022-05-19 | 2022-05-19 | 0 | On/ Ahead Schedule | Not Started | 2022-04-27 | 2022-05-10 | Not Started | 2022-07-11 | Not Started
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | E.5014726.02 | 5786007 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 8477 | 0 | 8477 | 1.6055 | 0 | 0 | 0 | 1.6055 | [5 empty] | 1609077.23 | 1239567.23 | 369510 |  |  | 71301 | 0 | 298209 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -8240 | 8240 | -8240 | 8240 | 1946473.9 | 0 | -6182.3 | 6182.3 | 0 | 427.4 | 85295.7 | -14422 | 1868990.6 | 0 | -10209 | 437 | 437 | 434 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154929 | BL-B | BL-B 35112978_CWSP - WEST POINT 1101 -LR 13444- PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-27 | Completed | 2021-11-01 | 2021-11-26 | Not Started | 2021-10-14 | Not Started | 2021-11-26 | Not Started | 2021-11-29 | 2021-11-29 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2021-11-05 | 2021-11-05 | Not Started | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-21 | Not Started | 2022-02-21 | Not Started | 2022-03-23 | 2022-03-23 | 0 | On/ Ahead Schedule | Not Started | 2022-03-01 | 2022-03-14 | Not Started | 2022-05-13 | Not Started
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | E.5014726.03 | 5786008 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 5331 | 0 | 5331 | 1.0097 | 0 | 0 | 0 | 1.0097 | [5 empty] | 634232.73 | 264722.73 | 369510 |  |  | 74173.8 | 0 | 295336.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 132 | -132 | 132 | -132 | 1410234.7 | 0 | -32091.3 | 32091.3 | 0 | 213.7 | 105919.4 | -31959.4 | 1303969.6 | 0 | -1873 | 531 | 531 | 191 | 753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154930 | BL-B | BL-B 35112979_CWSP - WEST POINT 1101 -LR 13444- PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-08-20 | Completed | 2021-08-26 | 2021-10-06 | Not Started | 2021-08-10 | Not Started | 2021-10-06 | Not Started | 2021-10-07 | 2021-10-07 | Not Started | 2021-10-08 | 2021-11-04 | Not Started | 2021-09-01 | 2021-09-14 | Not Started | 2022-01-06 | Not Started |  |  |  |  | 2022-01-06 | Not Started | 2022-02-28 | Not Started | 2022-02-28 | Not Started | 2022-03-30 | 2022-03-30 | 0 | On/ Ahead Schedule | Not Started | 2022-03-08 | 2022-03-21 | Not Started | 2022-05-20 | Not Started
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | E.5014726.04 | 5786009 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 10233 | 0 | 10233 | 1.9381 | 0 | 0 | 0 | 1.9381 | [5 empty] | 2254170.42 | 1884660.42 | 369510 |  |  | 114049.8 | 0 | 255460.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -2508 | 2508 | -2508 | 2508 | 2377329.8 | 0 | -13675.8 | 13675.8 | 0 | 0 | 130233.6 | -16183.7 | 2249604.2 | 0 | 39378 | 983 | -47844 | 4034 | 941 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154931 | BL-B | BL-B 35113100_CWSP - WEST POINT 1101 -LR 13444- PH 2.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-08 | Completed | 2021-10-15 | 2021-11-25 | Not Started | 2021-09-30 | Not Started | 2021-11-25 | Not Started | 2021-11-26 | 2021-11-26 | Not Started | 2021-11-29 | 2021-12-24 | Not Started | 2021-10-22 | 2021-10-22 | Not Started | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-23 | Not Started | 2022-02-23 | Not Started | 2022-03-25 | 2022-03-25 | 0 | On/ Ahead Schedule | Not Started | 2022-03-03 | 2022-03-16 | Not Started | 2022-05-17 | Not Started
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 | E.5014728.04 | 5786014 | PEND | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7448.1 | 0 | 7448.1 | 1.4106 | 0 | 0 | 0 | 1.4106 | [5 empty] | 838375.56 | 588375.56 | 250000 |  |  | 46687 | 0 | 203313 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10115 | -10115 | 10115 | -10115 | 2551649.8 | 0 | 0 | 0 | 0 | 580.3 | 35992 | 10114.7 | 2504962.8 | 0 | 5229 | 934 | 222 | 433 | 3298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154944 | BL-B | BL-B 35113995_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-10-28 | Completed | 2021-12-13 | 2022-01-07 | Not Started | 2022-02-11 | Not Started | 2022-02-14 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-01-11 | 2022-02-07 | Not Started | 2022-02-14 | 2022-02-14 | Not Started | 2022-03-23 | Not Started |  |  |  |  | 2022-03-23 | Not Started | 2022-05-19 | Not Started | 2022-05-19 | Not Started | 2022-06-20 | 2022-06-20 | 0 | On/ Ahead Schedule | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-08-10 | Not Started
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 | E.5014728.05 | 5786015 | PEND | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6270 | 0 | 6270 | 1.1875 | 0 | 0 | 0 | 1.1875 | [5 empty] | 841954.09 | 591954.09 | 250000 |  |  | 97238.9 | 0 | 152761.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3873 | -3873 | 3873 | -3873 | 1718621 | 0 | 0 | 0 | 0 | 0 | 93366.1 | 3872.7 | 1621382.1 | 0 | 1205 | 1185 | 497 | 493 | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154945 | BL-B | BL-B 35113996_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-18 | Completed | 2021-11-24 | 2021-12-21 | Not Started | 2022-01-11 | Not Started | 2022-01-12 | Not Started | 2021-12-22 | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-19 | Not Started | 2022-01-12 | 2022-01-25 | Not Started | 2022-02-18 | Not Started |  |  |  |  | 2022-02-18 | Not Started | 2022-04-07 | Not Started | 2022-04-07 | Not Started | 2022-05-09 | 2022-05-09 | 0 | On/ Ahead Schedule | Not Started | 2022-04-15 | 2022-04-28 | Not Started | 2022-06-29 | Not Started
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | E.5014728.06 | 5786016 | PEND | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 0 | 6460 | 0 | 6460 | 1.2235 | 0 | 0 | 0 | 1.2235 | [5 empty] | 771395.95 | 521395.95 | 250000 |  |  | 75278.3 | 0 | 174721.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3314 | -3314 | 3314 | -3314 | 1556265.6 | 0 | 0 | 0 | 0 | 0 | 71964.6 | 3313.8 | 1480987.3 | 0 | 1094 | 1072 | 384 | 382 | 382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154946 | BL-B | BL-B 35113997_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.6_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-15 | Completed | 2021-11-23 | 2021-12-20 | Not Started | 2022-01-10 | Not Started | 2022-01-11 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-18 | Not Started | 2022-01-11 | 2022-01-24 | Not Started | 2022-03-31 | Not Started |  |  |  |  | 2022-03-31 | Not Started | 2022-05-25 | Not Started | 2022-05-25 | Not Started | 2022-06-24 | 2022-06-24 | 0 | On/ Ahead Schedule | Not Started | 2022-06-02 | 2022-06-15 | Not Started | 2022-08-16 | Not Started
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | E.5014728.07 | 5786017 | PEND | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | 120 | 5787 | 0 | 5907 | 1.1187 | 0 | 0 | 0 | 1.1187 | [5 empty] | 1129039.96 | 879039.96 | 250000 |  |  | 126181 | 0 | 123819 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4609 | -4609 | 4609 | -4609 | 1654762.1 | 0 | 0 | 0 | 0 | 0 | 121571.7 | 4609.2 | 1528581.1 | 0 | -2993 | 5668 | 648 | 643 | 643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154947 | BL-B | BL-B 35113998_CWSP-WEST POINT 1101-OCB&LR12256-PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-09-29 | Completed | 2021-11-08 | 2021-12-03 | Not Started | 2022-01-07 | Not Started | 2022-01-10 | Not Started | 2021-12-06 | 2021-12-06 | Not Started | 2021-12-07 | 2022-01-03 | Not Started | 2022-01-10 | 2022-01-21 | Not Started | 2022-02-16 | Not Started |  |  |  |  | 2022-02-16 | Not Started | 2022-04-08 | Not Started | 2022-04-08 | Not Started | 2022-05-10 | 2022-05-10 | 0 | On/ Ahead Schedule | Not Started | 2022-04-18 | 2022-04-29 | Not Started | 2022-06-30 | Not Started
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | E.5014534.05 | 5786602 | PEND | 08W | [6 empty] | 2022 | 2020 | SH | CUPRTINO | De Anza Assets | 0 | 4483 | 0 | 4483 | 0.84905 | 0 | 0.84905 | 0 | 0.84905 | 4483 | 0 | 0.84905 | 0 |  | 1924210 | 488785 | 1435425 |  |  | 877829.7 | 212251.1 | 345344.2 | On/Under Budget | Budget Allocated | 406653.3 | 603027 | -196373.7 | 603027 | -196373.7 | 1349175.5 | 9252 | 1560.4 | 7691.6 | 0 | 454.5 | 745693.8 | 131681.4 | 0 | 0 | 36195 | 18566 | -8519 | 52319 | 31560 | 9252 | 30617 | 5371 | 423729 | 3938 | 0 | 0 | 2021-06-18 | 156105 | BL-A | BL-A 35119965_CWSP Los Gatos 1106-LB44 Ph 2.5E_08W - Feb. 2021 | 2021-02-20 | 2019-12-13 | Completed | 2020-04-13 | 2020-04-23 | Completed | 2021-10-05 | Not Started | 2021-10-06 | Not Started | 2020-03-12 | 2020-04-08 | Completed | 2020-04-08 | 2020-04-10 | Completed | 2021-10-15 | 2021-11-04 | Not Started | 2020-07-13 | Completed |  |  |  |  | 2020-06-29 | Completed | 2022-01-17 | Not Started | 2022-03-16 | Not Started | 2021-11-05 | 2022-03-16 | -131 | Behind Schedule | Not Started | 2022-03-31 | 2022-04-13 | Not Started | 2022-07-06 | Not Started
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | E.5014724.03 | 5786776 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 7291 | 0 | 7291 | 1.3809 | 0 | 0 | 0 | 1.3809 | [5 empty] | 305556 | 0 | 305556 |  |  | 100525.5 | 0 | 205030.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2939 | -2939 | 2939 | -2939 | 114948.1 | 21.7 | 0 | 21.7 | 0 | 0 | 97746 | 2779.3 | 14262.7 | 0 | 775 | 503 | 503 | 499 | 499 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | 2021-06-18 |  |  |  |  | 2020-09-30 | Completed | 2021-12-27 | 2022-01-07 | Not Started | 2022-01-14 | Not Started | 2022-01-17 | Not Started | 2022-01-10 | 2022-01-10 | Not Started | 2022-03-22 | 2022-04-11 | Not Started | 2022-01-10 | 2022-01-21 | Not Started | 2022-07-25 | Not Started |  |  |  |  | 2022-07-25 | Not Started | 2022-10-14 | Not Started | 2022-11-14 | Not Started | 2022-12-12 | 2022-12-12 | 0 | On/ Ahead Schedule | Not Started | 2022-12-13 | 2022-12-26 | Not Started | 2023-02-01 | Not Started
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | E.5014724.04 | 5786777 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 5493 | 0 | 5493 | 1.0403 | 0 | 0 | 0 | 1.0403 | [5 empty] | 305556 | 0 | 305556 |  |  | 86249.7 | 0 | 219306.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3974 | -3974 | 3974 | -3974 | 104082.9 | 26.6 | 0 | 26.6 | 0 | 0 | 82469.8 | 3780 | 17448.9 | 190 | 1942 | 461 | 461 | 458 | 458 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 2021-06-18 | 160790 | BL-A_ | BL-A_35129652_CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4_08W_May.2021 | 2021-05-17 | 2020-10-05 | Completed | 2022-06-17 | 2022-06-30 | Not Started | 2022-06-16 | Not Started | 2022-06-30 | Not Started | 2022-07-01 | 2022-07-01 | Not Started | 2022-07-04 | 2022-07-22 | Not Started | 2022-07-08 | 2022-07-21 | Not Started | 2023-01-06 | Not Started |  |  |  |  | 2023-01-06 | Not Started | 2023-02-03 | Not Started | 2023-03-17 | Not Started | 2023-04-04 | 2023-04-18 | -14 | Behind Schedule | Not Started | 2023-04-19 | 2023-05-02 | Not Started | 2023-06-08 | Not Started
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | E.5014724.05 | 5786778 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 6678 | 0 | 6678 | 1.2648 | 0 | 0 | 0 | 1.2648 | [5 empty] | 1351444.1 | 1101444.1 | 250000 |  |  | 4532.5 | 0 | 245467.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 120 | -120 | 120 | -120 | 33325.7 | 2.2 | 0 | 2.2 | 0 | 0 | 4428.2 | 104.4 | 58.9 | 28718.7 | -3061 | 3093 | 24 | 24 | 24 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2021-06-18 |  |  |  |  | 2020-11-04 | Completed | 2022-07-01 | 2022-07-14 | Not Started | 2022-07-28 | Not Started | 2022-07-29 | Not Started | 2022-07-15 | 2022-07-15 | Not Started | 2022-07-18 | 2022-08-05 | Not Started | 2022-07-25 | 2022-08-05 | Not Started | 2022-12-30 | Not Started |  |  |  |  | 2022-12-30 | Not Started | 2023-03-20 | Not Started | 2023-04-18 | Not Started | 2023-05-16 | 2023-05-16 | 0 | On/ Ahead Schedule | Not Started | 2023-05-17 | 2023-05-30 | Not Started | 2023-07-06 | Not Started
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | E.5014724.06 | 5786779 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10499 | 0 | 10499 | 1.9884 | 0 | 0 | 0 | 1.9884 | [5 empty] | 305556 | 0 | 305556 |  |  | 130257.2 | 0 | 175298.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10636 | -10636 | 10636 | -10636 | 149351.3 | 96 | 0 | 96 | 0 | 0 | 120312.1 | 9945 | 18403.5 | 0 | 7007 | 737 | 737 | 732 | 732 | 96 | 99 | 99 | 99 | 99 | 99 | 99 | 2021-06-18 |  |  |  |  | 2020-10-21 | Completed | 2022-05-13 | 2022-05-26 | Not Started | 2022-05-19 | Not Started | 2022-05-26 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-06-17 | Not Started | 2022-06-03 | 2022-06-16 | Not Started | 2022-11-11 | Not Started |  |  |  |  | 2022-11-11 | Not Started | 2023-02-02 | Not Started | 2023-03-03 | Not Started | 2023-03-31 | 2023-03-31 | 0 | On/ Ahead Schedule | Not Started | 2023-04-03 | 2023-04-14 | Not Started | 2023-05-23 | Not Started
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | E.5014724.07 | 5786780 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 9273 | 0 | 9273 | 1.7563 | 0 | 0 | 0 | 1.7563 | [5 empty] | 999695.19 | 749695.19 | 250000 |  |  | 20526.5 | 0 | 229473.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3117 | -3117 | 3117 | -3117 | 52979.9 | 13.2 | 0 | 13.2 | 0 | 0 | 17504.5 | 3022.1 | 18455.3 | 13903.1 | 2587 | 109 | 109 | 108 | 108 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 2021-06-18 |  |  |  |  | 2020-10-23 | Completed | 2022-06-24 | 2022-07-07 | Not Started | 2022-06-24 | Not Started | 2022-07-07 | Not Started | 2022-07-08 | 2022-07-08 | Not Started | 2022-07-11 | 2022-11-11 | Not Started | 2022-07-15 | 2022-07-28 | Not Started | 2022-12-23 | Not Started |  |  |  |  | 2022-12-23 | Not Started | 2023-03-15 | Not Started | 2023-04-13 | Not Started | 2023-05-11 | 2023-05-11 | 0 | On/ Ahead Schedule | Not Started | 2023-05-12 | 2023-05-25 | Not Started | 2023-07-03 | Not Started
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | E.5014721.04 | 5786761 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 7772 | 0 | 7772 | 1.472 | 0 | 0 | 0 | 1.472 | [5 empty] | 300000 | 0 | 300000 |  |  | 41614 | 0 | 258386 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1546 | -1546 | 1546 | -1546 | 50399.3 | 54.2 | 0 | 54.2 | 0 | 235.3 | 40220.4 | 1158.3 | 8397.7 | 0 | 248 | 245 | 223 | 221 | 221 | 54 | 56 | 56 | 56 | 56 | 56 | 56 | 2021-06-18 | 160858 | BL-A1 | BL-A1: 35129306_CWSP - ORO FINO 1102 - LR2560 PH 1.4_08W - May 21 | 2021-05-18 | 2020-09-04 | Completed | 2022-04-22 | 2022-06-02 | Not Started | 2022-04-21 | Not Started | 2022-06-02 | Not Started | 2022-06-24 | 2022-06-24 | Not Started | 2022-06-27 | 2022-08-12 | Not Started | 2022-05-13 | 2022-06-16 | Not Started | 2022-08-22 | Not Started |  |  |  |  | 2022-08-22 | Not Started | 2022-10-18 | Not Started | 2022-12-05 | Not Started | 2023-01-20 | 2023-02-03 | -14 | Behind Schedule | Not Started | 2023-02-06 | 2023-02-17 | Not Started | 2023-03-28 | Not Started
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | E.5014720.03 | 5786764 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 8902 | 0 | 8902 | 1.686 | 0 | 0 | 0 | 1.686 | [5 empty] | 100000 | 0 | 100000 |  |  | 38550.3 | 0 | 61449.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3187 | -3187 | 3187 | -3187 | 60232.6 | 19.4 | 132 | -112.6 | 0 | 235.3 | 35135.9 | 3179.1 | 21674.1 | 0 | 2051 | 217 | 217 | 215 | 348 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 2021-06-18 | 160745 | BL-A_ | BL-A_35129309_CWSP - ORO FINO 1102 - LR2560 PH 2.3_08W_May.2021 | 2021-05-17 | 2020-07-30 | Completed | 2022-05-27 | 2022-06-02 | Not Started | 2022-05-26 | Not Started | 2022-06-09 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-02 | Not Started | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-10-14 | Not Started | 2022-11-25 | Not Started | 2022-12-13 | 2022-12-27 | -14 | Behind Schedule | Not Started | 2022-12-28 | 2023-01-10 | Not Started | 2023-02-16 | Not Started
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | E.5014720.04 | 5786765 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10110 | 0 | 10110 | 1.9148 | 0 | 0 | 0 | 1.9148 | [5 empty] | 100000 | 0 | 100000 |  |  | 45069.3 | 0 | 54930.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2084 | -2084 | 2084 | -2084 | 79351.9 | 38.4 | 0 | 38.4 | 0 | 235.3 | 43025.7 | 1808.4 | 34007.3 | 0 | 843 | 259 | 237 | 235 | 235 | 38 | 40 | 40 | 40 | 40 | 40 | 40 | 2021-06-18 | 159215 | BL-A_ | BL-A_35129310_CWSP - ORO FINO 1102 - LR2560 PH 2.4_08W_May.2021 | 2021-04-14 | 2020-08-24 | Completed | 2022-03-18 | 2022-04-28 | Not Started | 2022-03-17 | Not Started | 2022-04-28 | Not Started | 2022-04-29 | 2022-04-29 | Not Started | 2022-05-02 | 2022-07-22 | Not Started | 2022-03-18 | 2022-03-31 | Not Started | 2022-07-25 | Not Started |  |  |  |  | 2022-07-25 | Not Started | 2022-10-28 | Not Started | 2022-12-16 | Not Started | 2022-12-30 | 2023-01-13 | -14 | Behind Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-07 | Not Started
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | E.5014720.05 | 5786766 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10500 | 0 | 10500 | 1.9886 | 0 | 0 | 0 | 1.9886 | [5 empty] | 1977294.19 | 1877294.19 | 100000 |  |  | 50141.4 | 0 | 49858.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6157 | -6157 | 6157 | -6157 | 82058 | 658.6 | 132 | 526.6 | 0 | 0 | 48549.8 | 1591.6 | 27351.7 | 0 | 281 | 263 | 263 | 261 | 393 | 659 | 664 | 667 | 671 | 648 | 678 | 710 | 2021-06-18 | 160746 | BL-A- | BL-A-35129311_CWSP - ORO FINO 1102 - LR2560 PH 2.5_08W_May.2021 | 2021-05-17 | 2022-06-30 | Not Started | 2022-07-01 | 2022-07-07 | Not Started | 2022-06-02 | Not Started | 2022-07-14 | Not Started | 2022-07-01 | 2022-07-01 | Not Started | 2022-07-04 | 2022-07-22 | Not Started | 2022-06-24 | 2022-07-07 | Not Started | 2022-09-02 | Not Started |  |  |  |  | 2022-09-02 | Not Started | 2022-11-24 | Not Started | 2022-12-09 | Not Started | 2022-12-27 | 2023-01-10 | -14 | Behind Schedule | Not Started | 2023-01-11 | 2023-01-24 | Not Started | 2023-03-02 | Not Started
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 | E.5014719.02 | 5786767 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10670 | 0 | 10670 | 2.0208 | 0 | 0 | 0 | 2.0208 | [5 empty] | 1281508.77 | 1031508.77 | 250000 |  |  | 200275.1 | 0 | 49724.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8221 | -8221 | 8221 | -8221 | 228080.2 | 200.3 | 132 | 68.3 | 0 | 235.3 | 193124.2 | 6915.5 | 25648.9 | 850.7 | 25886 | 1270 | -22749 | 1122 | 1255 | 200 | 206 | 206 | 206 | 206 | 206 | 206 | 2021-06-18 | 160747 | BL-A_ | BL-A_35129434_CWSP - ORO FINO 1102 - LR76008 PH 1.2_08W_May.2021 | 2021-05-17 | 2020-11-09 | Completed | 2022-07-08 | 2022-07-14 | Not Started | 2022-07-07 | Not Started | 2022-08-04 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-06-03 | Not Started | 2022-07-08 | 2022-07-14 | Not Started | 2022-11-18 | Not Started |  |  |  |  | 2022-11-18 | Not Started | 2023-01-19 | Not Started | 2023-02-09 | Not Started | 2023-03-29 | 2023-04-12 | -14 | Behind Schedule | Not Started | 2023-04-13 | 2023-04-26 | Not Started | 2023-06-02 | Not Started
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | E.5014719.03 | 5786768 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10796 | 0 | 10796 | 2.0447 | 0 | 0 | 0 | 2.0447 | [5 empty] | 1701197.29 | 1451197.29 | 250000 |  |  | 142071.6 | 0 | 107928.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9521 | -9521 | 9521 | -9521 | 168137.1 | 121.8 | 132 | -10.2 | 0 | 235.3 | 133058 | 8778.3 | 25322.5 | 0 | 22114 | 1268 | -16392 | 762 | 894 | 122 | 126 | 126 | 126 | 126 | 126 | 126 | 2021-06-18 | 160748 | BL-A_ | BL-A_35129435_CWSP - ORO FINO 1102 - LR76008 PH 1.3_08W_May.2021 | 2021-05-17 | 2020-10-08 | Completed | 2022-05-27 | 2022-06-02 | Not Started | 2022-05-26 | Not Started | 2022-07-21 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-09-26 | Not Started |  |  |  |  | 2022-09-26 | Not Started | 2022-11-25 | Not Started | 2022-12-08 | Not Started | 2022-12-26 | 2023-01-09 | -14 | Behind Schedule | Not Started | 2023-01-10 | 2023-01-23 | Not Started | 2023-03-01 | Not Started
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | E.5014719.04 | 5786769 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10179 | 0 | 10179 | 1.9278 | 0 | 0 | 0 | 1.9278 | [5 empty] | 250000 | 0 | 250000 |  |  | 132047.9 | 0 | 117952.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 22474 | -22474 | 22474 | -22474 | 155670.4 | 31.6 | 132 | -100.4 | 0 | 235.3 | 109438.9 | 22373.6 | 23522.1 | 0 | 18699 | 1251 | 723 | 718 | 851 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 2021-06-18 | 160749 | BL-A_ | BL-A_35129436_CWSP - ORO FINO 1102 - LR76008 PH 1.4_08W_May.2021 | 2021-05-17 | 2020-09-04 | Completed | 2022-06-24 | 2022-06-30 | Not Started | 2022-06-23 | Not Started | 2022-07-07 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-02 | Not Started | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-11-18 | Not Started | 2022-12-07 | Not Started | 2022-12-23 | 2023-01-06 | -14 | Behind Schedule | Not Started | 2023-01-09 | 2023-01-20 | Not Started | 2023-02-28 | Not Started
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | E.5014719.05 | 5786770 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 10708 | 0 | 10708 | 2.028 | 0 | 0 | 0 | 2.028 | [5 empty] | 250000 | 0 | 250000 |  |  | 120472.9 | 0 | 129527.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4017 | -4017 | 4017 | -4017 | 145021.4 | 54.4 | 132 | -77.6 | 0 | 235.3 | 116483.8 | 3753.9 | 24285.8 | 0 | 778 | 680 | 680 | 675 | 808 | 54 | 57 | 57 | 57 | 57 | 57 | 57 | 2021-06-18 | 160751 | BL-A_ | BL-A_35129437_CWSP - ORO FINO 1102 - LR76008 PH 1.5_08W_May.2021 | 2021-05-17 | 2020-08-13 | Completed | 2022-05-27 | 2022-06-02 | Not Started | 2022-05-27 | Not Started | 2022-06-09 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-02 | Not Started | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-11-11 | Not Started | 2022-11-29 | Not Started | 2022-12-15 | 2022-12-29 | -14 | Behind Schedule | Not Started | 2022-12-30 | 2023-01-12 | Not Started | 2023-02-20 | Not Started
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | E.5014718.02 | 5786771 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 9150 | 0 | 9150 | 1.733 | 0 | 0 | 0 | 1.733 | [5 empty] | 1182381.93 | 932381.93 | 250000 |  |  | 168015.6 | 0 | 81984.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 13423 | -13423 | 13423 | -13423 | 198145.2 | 685.1 | 0 | 685.1 | 0 | 235.3 | 159248.7 | 8531.6 | 25238.7 | 0 | 24987 | 988 | -19375 | 1059 | 873 | 685 | 691 | 695 | 699 | 673 | 707 | 741 | 2021-06-18 | 160752 | BL-A_ | BL-A_35129438_CWSP - ORO FINO 1102 - LR76008 PH 2.2_08W_May.2021 | 2021-05-17 | 2022-06-09 | Not Started | 2022-06-10 | 2022-06-16 | Not Started | 2022-05-26 | Not Started | 2022-06-23 | Not Started | 2022-06-10 | 2022-06-10 | Not Started | 2022-06-13 | 2022-09-02 | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-10-03 | Not Started |  |  |  |  | 2022-10-03 | Not Started | 2022-12-02 | Not Started | 2022-12-26 | Not Started | 2023-01-11 | 2023-01-25 | -14 | Behind Schedule | Not Started | 2023-01-26 | 2023-02-08 | Not Started | 2023-03-17 | Not Started
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | E.5014718.03 | 5786772 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 9792 | 0 | 9792 | 1.8545 | 0 | 0 | 0 | 1.8545 | [5 empty] | 250000 | 0 | 250000 |  |  | 149854.7 | 0 | 100145.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 23094 | -23094 | 23094 | -23094 | 172700.4 | 18.3 | 0 | 18.3 | 0 | 235.3 | 126664.2 | 22955.3 | 22706.7 | 0 | 19437 | 848 | 848 | 981 | 842 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 2021-06-18 | 160753 | BL-A_ | BL-A_35129439_CWSP - ORO FINO 1102 - LR76008 PH 2.3_08W_May.2021 | 2021-05-17 | 2020-09-11 | Completed | 2022-05-27 | 2022-06-02 | Not Started | 2022-05-26 | Not Started | 2022-06-09 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-09 | Not Started | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-11-18 | Not Started | 2022-12-01 | Not Started | 2022-12-19 | 2023-01-02 | -14 | Behind Schedule | Not Started | 2023-01-03 | 2023-01-16 | Not Started | 2023-02-22 | Not Started
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | E.5014718.04 | 5786773 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 6062 | 0 | 6062 | 1.1481 | 0 | 0 | 0 | 1.1481 | [5 empty] | 250000 | 0 | 250000 |  |  | 121155.4 | 0 | 128844.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 18903 | -18903 | 18903 | -18903 | 127804.7 | 30.3 | 0 | 30.3 | 0 | 235.3 | 102239.7 | 18680.5 | 6427.2 | 0 | 16151 | 635 | 635 | 630 | 630 | 30 | 32 | 32 | 32 | 32 | 32 | 32 | 2021-06-18 | 160754 | BL-A_ | BL-A_35129600_CWSP - ORO FINO 1102 - LR76008 PH 2.4_08W_May.2021 | 2021-05-17 | 2020-09-11 | Completed | 2022-05-27 | 2022-06-02 | Not Started | 2022-05-26 | Not Started | 2022-06-09 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2022-05-27 | 2022-06-02 | Not Started | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-10-21 | Not Started | 2022-11-07 | Not Started | 2022-11-23 | 2022-12-07 | -14 | Behind Schedule | Not Started | 2022-12-08 | 2022-12-21 | Not Started | 2023-01-27 | Not Started
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | E.5014718.05 | 5786774 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 7408 | 0 | 7408 | 1.403 | 0 | 0 | 0 | 1.403 | [5 empty] | 3374618 | 870869.7 | 2503748.3 |  |  | 186447.8 | 0 | 2317300.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6422 | -6422 | 6422 | -6422 | 205952.5 | 40.2 | 132 | -91.8 | 0 | 0 | 180084.2 | 6363.5 | 19446.4 | 0 | 1878 | 1076 | 1054 | 1046 | 1179 | 40 | 43 | 43 | 43 | 22 | 0 | 0 | 2021-06-18 | 160755 | BL-A_ | BL-A_35129601_CWSP - ORO FINO 1102 - LR76008 PH 2.5_08W_May.2021 | 2021-05-17 | 2020-07-07 | Completed | 2020-09-04 | 2020-09-05 | Completed | 2022-05-26 | Not Started | 2022-06-02 | Not Started | 2022-05-27 | 2022-05-27 | Not Started | 2022-05-30 | 2022-08-19 | Not Started | 2020-11-13 | 2022-05-27 | In Progress | 2022-09-19 | Not Started |  |  |  |  | 2022-09-19 | Not Started | 2022-11-04 | Not Started | 2022-11-18 | Not Started | 2022-12-06 | 2022-12-20 | -14 | Behind Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 | E.5014748.02 | 5786745 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5722 | 0 | 5722 | 1.0837 | 0 | 0 | 0 | 1.0837 | [5 empty] | 4600257 | 0 | 4600257 |  |  | 69004.5 | 0 | 4531252.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 45629 | -45629 | 45629 | -45629 | 86723.4 | 39.5 | 132 | -92.5 | 0 | 0 | 23526.5 | 45478 | 17568 | 0 | 20624 | 256 | -20260 | 44239 | 488 | 40 | 41 | 41 | 41 | 41 | 41 | 41 | 2021-06-18 | 160756 | BL-A_ | BL-A_35129602_CWSP - ORO FINO 1101 - OCB PH 1.2_08W_May.2021 | 2021-05-17 | 2020-07-06 | Completed | 2020-10-14 | 2020-10-14 | Completed | 2021-06-18 | Not Started | 2022-09-30 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-24 | 2021-06-24 | Not Started | 2022-10-12 | Not Started |  |  |  |  | 2022-10-12 | Not Started | 2022-11-02 | Not Started | 2022-11-15 | Not Started | 2023-02-07 | 2023-01-10 | 28 | On/ Ahead Schedule | Not Started | 2023-01-11 | 2023-01-24 | Not Started | 2023-03-02 | Not Started
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 | E.5014748.03 | 5786746 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 1.3201 | [5 empty] | 250000 | 0 | 250000 |  |  | 78832.3 | 0 | 171167.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 46001 | -46001 | 46001 | -46001 | 98242.3 | 33.8 | 132 | -98.2 | 0 | 0 | 32942.3 | 45889.9 | 19298.9 | 0 | 35228 | 367 | -34675 | 44293 | 545 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 2021-06-18 | 160757 | BL-A_ | BL-A_35129603_CWSP - ORO FINO 1101 - OCB PH 1.3_08W_May.2021 | 2021-05-17 | 2020-05-06 | Completed | 2022-10-28 | 2022-10-28 | Not Started | 2021-06-18 | Not Started | 2022-10-28 | Not Started | 2022-10-28 | 2022-10-28 | Not Started | 2022-10-31 | 2022-11-01 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-11-09 | Not Started |  |  |  |  | 2022-11-09 | Not Started | 2022-12-01 | Not Started | 2022-12-08 | Not Started | 2023-02-01 | 2023-02-01 | 0 | On/ Ahead Schedule | Not Started | 2023-02-02 | 2023-02-15 | Not Started | 2023-03-24 | Not Started
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 | E.5014748.04 | 5786747 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7682 | 0 | 7682 | 1.4549 | 0 | 0 | 0 | 1.4549 | [5 empty] | 250000 | 0 | 250000 |  |  | 69278.3 | 0 | 180721.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 45623 | -45623 | 45623 | -45623 | 89448.7 | 33.6 | 132 | -98.4 | 0 | 0 | 23764.1 | 45514.1 | 20061.4 | 0 | 20997 | 246 | -20612 | 44249 | 503 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 2021-06-18 | 160758 | BL-A_ | BL-A_35129604_CWSP - ORO FINO 1101 - OCB PH 1.4_08W_May.2021 | 2021-05-17 | 2020-08-06 | Completed | 2022-10-27 | 2022-10-27 | Not Started | 2021-06-18 | Not Started | 2022-10-28 | Not Started | 2022-10-27 | 2022-10-27 | Not Started | 2022-10-28 | 2022-10-31 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-11-08 | Not Started |  |  |  |  | 2022-11-08 | Not Started | 2022-12-05 | Not Started | 2022-12-21 | Not Started | 2023-02-16 | 2023-02-15 | 1 | On/ Ahead Schedule | Not Started | 2023-02-16 | 2023-03-01 | Not Started | 2023-04-07 | Not Started
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 | E.5014748.05 | 5786748 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8342 | 0 | 8342 | 1.5799 | 0 | 0 | 0 | 1.5799 | [5 empty] | 250000 | 0 | 250000 |  |  | 68408.2 | 0 | 181591.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 45793 | -45793 | 45793 | -45793 | 100222.4 | 58.1 | 132 | -73.9 | 0 | 0 | 22898.5 | 45509.6 | 31531.2 | 0 | 22032 | 248 | -21648 | 44245 | 500 | 58 | 60 | 60 | 60 | 60 | 60 | 60 | 2021-06-18 | 160759 | BL-A_ | BL-A_35129605_CWSP - ORO FINO 1101 - OCB PH 1.5_08W_May.2021 | 2021-05-17 | 2020-08-06 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-07 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2022-10-21 | Not Started |  |  |  |  | 2022-10-21 | Not Started | 2022-11-18 | Not Started | 2022-12-06 | Not Started | 2022-12-07 | 2022-12-07 | 0 | On/ Ahead Schedule | Not Started | 2022-12-09 | 2022-12-22 | Not Started | 2023-01-26 | Not Started
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 | E.5014748.06 | 5786749 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5223 | 0 | 5223 | 0.9892 | 0 | 0 | 0 | 0.9892 | [5 empty] | 250000 | 0 | 250000 |  |  | 94129 | 0 | 155871 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 66434 | -66434 | 66434 | -66434 | 111348.5 | 29.8 | 132 | -102.2 | 0 | 0 | 27777 | 66352.1 | 17137.4 | 0 | 20874 | 271 | -20442 | 44275 | 21243 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 2021-06-18 | 160760 | BL-A_ | BL-A_35129606_CWSP - ORO FINO 1101 - OCB PH 1.6_08W_May.2021 | 2021-05-17 | 2020-06-24 | Completed | 2022-09-30 | 2022-10-13 | Not Started | 2020-09-28 | Completed | 2022-10-13 | Not Started | 2022-10-14 | 2022-10-14 | Not Started | 2022-10-17 | 2022-10-18 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-26 | Not Started |  |  |  |  | 2022-10-26 | Not Started | 2022-11-18 | Not Started | 2022-12-06 | Not Started | 2023-02-28 | 2023-02-28 | 0 | On/ Ahead Schedule | Not Started | 2023-03-01 | 2023-03-14 | Not Started | 2023-04-20 | Not Started
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 | E.5014748.07 | 5786750 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7972 | 0 | 7972 | 1.5098 | 0 | 0 | 0 | 1.5098 | [5 empty] | 250000 | 0 | 250000 |  |  | 68427.7 | 0 | 181572.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 48049 | -48049 | 48049 | -48049 | 79297.2 | 47.5 | 0 | 47.5 | 0 | 0 | 20719.9 | 47707.8 | 10528.5 | 0 | 81752 | 2461 | -81082 | 44231 | 346 | 48 | 49 | 49 | 49 | 49 | 49 | 49 | 2021-06-18 | 160761 | BL-A_ | BL-A_35129607_CWSP - ORO FINO 1101 - OCB PH 1.7_08W_May.2021 | 2021-05-17 | 2020-08-14 | Completed | 2021-12-02 | 2021-12-02 | Not Started | 2021-06-18 | Not Started | 2022-05-20 | Not Started | 2021-12-02 | 2021-12-02 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-06-21 | 2021-06-21 | Not Started | 2022-05-31 | Not Started |  |  |  |  | 2022-05-31 | Not Started | 2022-06-28 | Not Started | 2022-07-07 | Not Started | 2022-09-29 | 2022-09-29 | 0 | On/ Ahead Schedule | Not Started | 2022-09-30 | 2022-10-13 | Not Started | 2022-11-21 | Not Started
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 | E.5014747.02 | 5786751 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7762 | 0 | 7762 | 1.4701 | 0 | 0 | 0 | 1.4701 | [5 empty] | 333333 | 0 | 333333 |  |  | 38174 | 0 | 295159 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1365 | -1365 | 1365 | -1365 | 68353.6 | 27.3 | 132 | -104.7 | 0 | 0 | 36874.3 | 1299.8 | 30114.7 | 0 | 18684 | -18207 | 187 | 186 | 318 | 27 | 28 | 28 | 28 | 28 | 28 | 28 | 2021-06-18 | 160762 | BL-A_ | BL-A_35129608_CWSP - ORO FINO 1101 - OCB PH 2.2_08W_May.2021 | 2021-05-17 | 2020-09-28 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-03 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-03 | Not Started | 2021-06-21 | 2021-06-21 | Not Started | 2022-10-11 | Not Started |  |  |  |  | 2022-10-11 | Not Started | 2022-10-12 | Not Started | 2022-10-21 | Not Started | 2023-01-13 | 2023-01-13 | 0 | On/ Ahead Schedule | Not Started | 2023-01-16 | 2023-01-27 | Not Started | 2023-03-07 | Not Started
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 | E.5014747.03 | 5786752 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5626 | 0 | 5626 | 1.0655 | 0 | 0 | 0 | 1.0655 | [5 empty] | 333333 | 0 | 333333 |  |  | 86662.4 | 0 | 246670.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 7021 | -7021 | 7021 | -7021 | 104437.4 | 48.7 | 132 | -83.3 | 0 | 0 | 79861.9 | 6800.5 | 17554.9 | 0 | 41749 | -36550 | 448 | 445 | 577 | 49 | 51 | 51 | 51 | 51 | 51 | 51 | 2021-06-18 | 160763 | BL-A_ | BL-A_35129609_CWSP - ORO FINO 1101 - OCB PH 2.3_08W_May.2021 | 2021-05-17 | 2020-06-05 | Completed | 2020-09-23 | 2020-10-09 | Completed | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-07 | Not Started | 2022-11-18 | Not Started | 2023-02-10 | 2023-02-10 | 0 | On/ Ahead Schedule | Not Started | 2023-02-13 | 2023-02-24 | Not Started | 2023-04-04 | Not Started
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 | E.5014747.04 | 5786753 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8284 | 0 | 8284 | 1.5689 | 0 | 0 | 0 | 1.5689 | [5 empty] | 333333 | 0 | 333333 |  |  | 48040 | 0 | 285293 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2220 | -2220 | 2220 | -2220 | 79343.3 | 33.9 | 132 | -98.1 | 0 | 0 | 45934 | 2106 | 31189.7 | 0 | 66155 | -65225 | 268 | 266 | 510 | 34 | 35 | 35 | 35 | 35 | 35 | 35 | 2021-06-18 | 160764 | BL-A_ | BL-A_35129610_CWSP - ORO FINO 1101 - OCB PH 2.4_08W_May.2021 | 2021-05-17 | 2020-10-28 | Completed | 2022-09-30 | 2022-10-03 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-10-04 | 2022-10-04 | Not Started | 2022-10-05 | 2022-10-06 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-15 | Not Started | 2022-12-01 | Not Started | 2023-02-23 | 2023-02-23 | 0 | On/ Ahead Schedule | Not Started | 2023-02-24 | 2023-03-09 | Not Started | 2023-04-17 | Not Started
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 | E.5014747.05 | 5786754 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6878 | 0 | 6878 | 1.3027 | 0 | 0 | 0 | 1.3027 | [5 empty] | 333333 | 0 | 333333 |  |  | 37012.4 | 0 | 296320.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2014 | -2014 | 2014 | -2014 | 66555.7 | 36.4 | 132 | -95.6 | 0 | 0 | 35127 | 1885.4 | 29414.4 | 0 | 835 | 214 | 192 | 190 | 323 | 36 | 37 | 37 | 37 | 37 | 37 | 37 | 2021-06-18 | 160767 | BL-A_ | BL-A_35129611_CWSP - ORO FINO 1101 - OCB PH 2.5_08W_May.2021 | 2021-05-17 | 2020-08-10 | Completed | 2022-09-30 | 2022-10-13 | Not Started | 2021-06-18 | Not Started | 2022-10-13 | Not Started | 2022-10-14 | 2022-10-14 | Not Started | 2022-10-17 | 2022-10-18 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-26 | Not Started |  |  |  |  | 2022-10-26 | Not Started | 2022-11-21 | Not Started | 2022-12-07 | Not Started | 2023-03-01 | 2023-03-01 | 0 | On/ Ahead Schedule | Not Started | 2023-03-02 | 2023-03-15 | Not Started | 2023-04-21 | Not Started
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 | E.5014747.06 | 5786755 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5997 | 0 | 5997 | 1.1358 | 0 | 0 | 0 | 1.1358 | [5 empty] | 333333 | 0 | 333333 |  |  | 36203.8 | 0 | 297129.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1408 | -1408 | 1408 | -1408 | 54654.6 | 42.8 | 132 | -89.2 | 0 | 0 | 34970.4 | 1233.3 | 18276.3 | 0 | 195 | 211 | 189 | 187 | 320 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 2021-06-18 | 160768 | BL-A_ | BL-A_35129612_CWSP - ORO FINO 1101 - OCB PH 2.6_08W_May.2021 | 2021-05-17 | 2020-07-17 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-11 | Not Started | 2022-11-29 | Not Started | 2023-02-21 | 2023-02-21 | 0 | On/ Ahead Schedule | Not Started | 2023-02-22 | 2023-03-07 | Not Started | 2023-04-13 | Not Started
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 | E.5014746.02 | 5786756 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7303 | 0 | 7303 | 1.3831 | 0 | 0 | 0 | 1.3831 | [5 empty] | 250000 | 125000 | 125000 |  |  | 42014.5 | 0 | 82985.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -58088 | 58088 | -58088 | 58088 | 61811.3 | 24.8 | 132 | -107.2 | 0 | 0 | 100151.8 | -58137.2 | 19748.3 | 0 | -59281 | 221 | 221 | 219 | 351 | 25 | 26 | 26 | 26 | 26 | 26 | 26 | 2021-06-18 | 160770 | BL-A_ | BL-A_35129613_CWSP - ORO FINO 1101 - OCB PH 3.2_08W_May.2021 | 2021-05-17 | 2020-09-17 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-07-01 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-14 | Not Started | 2022-11-30 | Not Started | 2023-02-22 | 2023-02-22 | 0 | On/ Ahead Schedule | Not Started | 2023-02-23 | 2023-03-08 | Not Started | 2023-04-14 | Not Started
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 | E.5014746.03 | 5786757 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8896 | 0 | 8896 | 1.6848 | 0 | 0 | 0 | 1.6848 | [5 empty] | 250000 | 0 | 250000 |  |  | 45738.8 | 0 | 204261.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -76943 | 76943 | -76943 | 76943 | 68196.7 | 58.6 | 132 | -73.4 | 0 | 0 | 122971.2 | -77232.5 | 22168.1 | 0 | -80434 | 2172 | 256 | 254 | 387 | 59 | 61 | 61 | 61 | 61 | 61 | 61 | 2021-06-18 | 160771 | BL-A_ | BL-A_35129614_CWSP - ORO FINO 1101 - OCB PH 3.3_08W_May.2021 | 2021-05-17 | 2020-10-05 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-15 | Not Started | 2022-12-01 | Not Started | 2023-02-23 | 2023-02-23 | 0 | On/ Ahead Schedule | Not Started | 2023-02-24 | 2023-03-09 | Not Started | 2023-04-17 | Not Started
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 | E.5014746.04 | 5786758 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10990 | 0 | 10990 | 2.0814 | 0 | 0 | 0 | 2.0814 | [5 empty] | 125000 | -125000 | 250000 |  |  | 91473.5 | 0 | 158526.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -149439 | 149439 | -149439 | 149439 | 125907.2 | 34.6 | 132 | -97.4 | 0 | 0 | 241035.8 | -149562.3 | 34310.2 | 0 | -153302 | 3843 | -1445 | 608 | 602 | 35 | 37 | 37 | 37 | 37 | 37 | 37 | 2021-06-18 | 160772 | BL-A_ | BL-A_35129615_CWSP - ORO FINO 1101 - OCB PH 3.4_08W_May.2021 | 2021-05-17 | 2020-11-02 | Completed | 2022-09-30 | 2022-10-03 | Not Started | 2021-07-01 | Not Started | 2022-10-07 | Not Started | 2022-10-04 | 2022-10-04 | Not Started | 2022-10-05 | 2022-10-06 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-17 | Not Started | 2022-12-05 | Not Started | 2023-02-27 | 2023-02-27 | 0 | On/ Ahead Schedule | Not Started | 2023-02-28 | 2023-03-13 | Not Started | 2023-04-19 | Not Started
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | E.5014760.02 | 5786672 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8577 | 0 | 8577 | 1.6244 | 0 | 0 | 0 | 1.6244 | [5 empty] | 262500 | 0 | 262500 |  |  | 47221.6 | 0 | 215278.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4528 | -4528 | 4528 | -4528 | 68782.1 | 37 | 0 | 37 | 0 | 470.6 | 42489.1 | 4261.9 | 21294.5 | 0 | 1843 | 259 | 259 | 1634 | 266 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 2021-06-18 | 160773 | BL-A_ | BL-A_35129616_CWSP - ORO FINO 1101 - LR2022 PH 1.2_08W_May.2021 | 2021-05-17 | 2020-08-13 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-06-18 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-29 | Not Started | 2021-12-30 | 2022-01-19 | Not Started | 2021-07-09 | 2021-08-27 | Not Started | 2022-01-27 | Not Started |  |  |  |  | 2022-01-27 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-19 | 2022-07-19 | 0 | On/ Ahead Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-08 | Not Started
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | E.5014760.03 | 5786673 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10289 | 0 | 10289 | 1.9487 | 0 | 0 | 0 | 1.9487 | [5 empty] | 262500 | 0 | 262500 |  |  | 112938.4 | 0 | 149561.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4513 | -4513 | 4513 | -4513 | 147599.6 | 80.7 | 0 | 80.7 | 0 | 0 | 109006 | 3932.4 | 34080.7 | 0 | 539 | 634 | 634 | 1490 | 635 | 81 | 83 | 83 | 83 | 83 | 83 | 83 | 2021-06-18 | 160774 | BL-A_ | BL-A_35129617_CWSP - ORO FINO 1101 - LR2022 PH 1.3_08WMay.2021 | 2021-05-17 | 2020-09-03 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-06 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-08-27 | Not Started | 2022-10-13 | Not Started |  |  |  |  | 2022-10-13 | Not Started | 2022-11-08 | Not Started | 2022-11-15 | Not Started | 2023-01-16 | 2023-01-16 | 0 | On/ Ahead Schedule | Not Started | 2023-01-17 | 2023-01-18 | Not Started | 2023-02-13 | Not Started
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | E.5014760.04 | 5786674 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10520 | 0 | 10520 | 1.9924 | 0 | 0 | 0 | 1.9924 | [5 empty] | 262500 | 0 | 262500 |  |  | 98237.1 | 0 | 164262.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 69298 | -69298 | 69298 | -69298 | 132422.6 | 42.8 | 0 | 42.8 | 0 | 235.3 | 29011.9 | 68989.9 | 33877.4 | 0 | 64694 | 514 | 514 | 2747 | 522 | 43 | 44 | 44 | 44 | 44 | 44 | 44 | 2021-06-18 | 160776 | BL-A_ | BL-A_35129618_CWSP - ORO FINO 1101 - LR2022 PH 1.4_08W_May.2021 | 2021-05-17 | 2020-10-20 | Completed | 2021-12-02 | 2021-12-15 | Not Started | 2021-06-18 | Not Started | 2021-12-15 | Not Started | 2021-12-16 | 2021-12-16 | Not Started | 2021-12-17 | 2022-01-06 | Not Started | 2021-07-09 | 2021-07-16 | Not Started | 2022-01-20 | Not Started |  |  |  |  | 2022-01-20 | Not Started | 2022-03-16 | Not Started | 2022-04-14 | Not Started | 2022-05-16 | 2022-05-16 | 0 | On/ Ahead Schedule | Not Started | 2022-05-17 | 2022-05-30 | Not Started | 2022-07-06 | Not Started
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | E.5014760.05 | 5786675 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8750 | 0 | 8750 | 1.6572 | 0 | 0 | 0 | 1.6572 | [5 empty] | 262500 | 0 | 262500 |  |  | 86554.1 | 0 | 175945.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6442 | -6442 | 6442 | -6442 | 118359.2 | 32.4 | 0 | 32.4 | 0 | 0 | 80347.1 | 6207 | 31569.6 | 0 | 2072 | 477 | 477 | 1334 | 1847 | 32 | 34 | 34 | 34 | 34 | 34 | 34 | 2021-06-18 | 160777 | BL-A_ | BL-A_35129619_CWSP - ORO FINO 1101 - LR2022 PH 1.5_08W_May.2021 | 2021-05-17 | 2020-09-11 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-06-18 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-13 | Not Started | 2021-07-09 | 2021-09-16 | Not Started | 2022-01-27 | Not Started |  |  |  |  | 2022-01-27 | Not Started | 2022-04-19 | Not Started | 2022-05-18 | Not Started | 2022-07-19 | 2022-07-19 | 0 | On/ Ahead Schedule | Not Started | 2022-07-20 | 2022-08-02 | Not Started | 2022-09-08 | Not Started
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | E.5014760.06 | 5786676 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 8536 | 0 | 8536 | 1.6167 | 0 | 0 | 0 | 1.6167 | [5 empty] | 262500 | 0 | 262500 |  |  | 16773.8 | 0 | 245726.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1699 | -1699 | 1699 | -1699 | 48290.4 | 30 | 87.6 | -57.6 | 0 | 0 | 15201.9 | 1572.1 | 31389.8 | 0 | 93 | 89 | 89 | 1121 | 94 | 30 | 31 | 31 | 31 | 31 | 31 | 31 | 2021-06-18 | 160778 | BL-A_ | BL-A_35129640_CWSP - ORO FINO 1101 - LR2022 PH 1.6_08W_May.2021 | 2021-05-17 | 2020-06-25 | Completed | 2021-12-02 | 2021-12-15 | Not Started | 2021-06-18 | Not Started | 2021-12-15 | Not Started | 2021-12-16 | 2021-12-16 | Not Started | 2021-12-17 | 2022-01-06 | Not Started | 2021-07-09 | 2021-09-16 | Not Started | 2022-01-20 | Not Started |  |  |  |  | 2022-01-20 | Not Started | 2022-04-12 | Not Started | 2022-05-11 | Not Started | 2022-06-10 | 2022-06-10 | 0 | On/ Ahead Schedule | Not Started | 2022-06-13 | 2022-06-24 | Not Started | 2022-08-02 | Not Started
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | E.5014760.07 | 5786677 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 7019 | 0 | 7019 | 1.3294 | 0 | 0 | 0 | 1.3294 | [5 empty] | 262500 | 0 | 262500 |  |  | 43693.9 | 0 | 218806.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5849 | -5849 | 5849 | -5849 | 54614.2 | 43.5 | 0 | 43.5 | 0 | 0 | 38158.2 | 5535.6 | 10607.6 | 0 | 43513 | 2851 | -42160 | 238 | 1093 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 2021-06-18 | 160779 | BL-A_ | BL-A_35129641_CWSP - ORO FINO 1101 - LR2022 PH 1.7_08W_May.2021 | 2021-05-17 | 2020-09-08 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-07-01 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-02 | Not Started | 2021-07-09 | 2021-10-06 | Not Started | 2022-02-10 | Not Started |  |  |  |  | 2022-02-10 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-06-29 | 2022-06-29 | 0 | On/ Ahead Schedule | Not Started | 2022-06-30 | 2022-07-13 | Not Started | 2022-08-19 | Not Started
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | E.5014760.08 | 5786738 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6255 | 0 | 6255 | 1.1847 | 0 | 0 | 0 | 1.1847 | [5 empty] | 262500 | 0 | 262500 |  |  | 53333.3 | 0 | 209166.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 38648 | -38648 | 38648 | -38648 | 71730.2 | 23 | 0 | 23 | 0 | 0 | 14850.4 | 38482.9 | 18231.5 | 0 | 32223 | 5356 | 303 | 301 | 301 | 23 | 24 | 24 | 24 | 24 | 24 | 24 | 2021-06-18 | 160781 | BL-A_ | BL-A_35129642_CWSP - ORO FINO 1101 - LR2022 PH 1.8_08W_May.2021 | 2021-05-17 | 2020-10-30 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-06-18 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2022-01-12 | Not Started | 2022-01-13 | 2022-02-02 | Not Started | 2021-07-09 | 2021-10-28 | Not Started | 2022-02-10 | Not Started |  |  |  |  | 2022-02-10 | Not Started | 2022-04-29 | Not Started | 2022-05-30 | Not Started | 2022-06-29 | 2022-06-29 | 0 | On/ Ahead Schedule | Not Started | 2022-06-30 | 2022-07-13 | Not Started | 2022-08-19 | Not Started
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 | E.5014755.02 | 5786739 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 10869 | 0 | 10869 | 2.0585 | 0 | 0 | 0 | 2.0585 | [5 empty] | 271429 | 0 | 271429 |  |  | 68560.3 | 0 | 202868.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6098 | -6098 | 6098 | -6098 | 97954.9 | 59.7 | 221.7 | -162 | 0 | 0 | 62668.8 | 5891.4 | 29187.7 | 0 | 387 | 4128 | 387 | 384 | 384 | 60 | 62 | 62 | 62 | 62 | 62 | 62 | 2021-06-18 | 160782 | BL-A_ | BL-A_35129643_CWSP - ORO FINO 1101 - LR2022 PH 2.2_08W_May.2021 | 2021-05-17 | 2020-09-23 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-10 | Not Started | 2022-11-21 | Not Started | 2023-02-13 | 2023-02-13 | 0 | On/ Ahead Schedule | Not Started | 2023-02-14 | 2023-02-27 | Not Started | 2023-04-05 | Not Started
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 | E.5014755.03 | 5786740 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 5214 | 0 | 5214 | 0.9875 | 0 | 0 | 0 | 0.9875 | [5 empty] | 271429 | 0 | 271429 |  |  | 57310.8 | 0 | 214118.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6411 | -6411 | 6411 | -6411 | 74446 | 43.5 | 221.7 | -178.2 | 0 | 0 | 50990.8 | 6319.9 | 17044.4 | 0 | 4610 | 413 | 313 | 450 | 311 | 44 | 45 | 45 | 45 | 45 | 45 | 45 | 2021-06-18 | 160784 | BL-A_ | BL-A_35129644_CWSP - ORO FINO 1101 - LR2022 PH 2.3_08W_May.2021 | 2021-05-17 | 2020-07-31 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-22 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-10 | Not Started | 2022-11-28 | Not Started | 2023-02-20 | 2023-02-20 | 0 | On/ Ahead Schedule | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-04-12 | Not Started
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 | E.5014755.04 | 5786741 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6367 | 0 | 6367 | 1.2059 | 0 | 0 | 0 | 1.2059 | [5 empty] | 271429 | 0 | 271429 |  |  | 35563.6 | 0 | 235865.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8891 | -8891 | 8891 | -8891 | 53550.5 | 19.1 | 443.5 | -424.4 | 0 | 0 | 26367 | 9196.5 | 18292.7 | 0 | 7861 | 189 | 189 | 327 | 188 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 2021-06-18 | 160785 | BL-A_ | BL-A_35129645_CWSP - ORO FINO 1101 - LR2022 PH 2.4_08W_May.2021 | 2021-05-17 | 2020-08-06 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-07 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-25 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-11 | Not Started | 2022-11-29 | Not Started | 2023-02-21 | 2023-02-21 | 0 | On/ Ahead Schedule | Not Started | 2023-02-22 | 2023-03-07 | Not Started | 2023-04-13 | Not Started
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 | E.5014755.05 | 5786742 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 0 | 6644 | 0 | 6644 | 1.2583 | 0 | 0 | 0 | 1.2583 | [5 empty] | 271429 | 0 | 271429 |  |  | 44730 | 0 | 226699 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 4176 | -4176 | 4176 | -4176 | 63786.6 | 37.1 | 0 | 37.1 | 0 | 0 | 40820.1 | 3909.9 | 18790.2 | 0 | 237 | 457 | 1373 | 1377 | 466 | 37 | 38 | 38 | 38 | 38 | 38 | 38 | 2021-06-18 | 160787 | BL_A: | BL_A: 35129646_CWSP - ORO FINO 1101 - LR2022 PH 2.5_08W_May.2021 | 2021-05-17 | 2020-07-14 | Completed | 2022-09-30 | 2022-09-30 | Not Started | 2021-06-18 | Not Started | 2022-10-06 | Not Started | 2022-09-30 | 2022-09-30 | Not Started | 2022-10-03 | 2022-10-04 | Not Started | 2021-06-22 | 2021-06-25 | Not Started | 2022-10-18 | Not Started |  |  |  |  | 2022-10-18 | Not Started | 2022-11-11 | Not Started | 2022-11-29 | Not Started | 2023-02-21 | 2023-02-21 | 0 | On/ Ahead Schedule | Not Started | 2023-02-22 | 2023-03-07 | Not Started | 2023-04-13 | Not Started
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | E.5015531.04 | 5788623 | PEND | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 4793 | 0 | 4793 | 0.90777 | 0 | 0 | 0 | 0.90777 | [5 empty] | 2485715 | 683214.7 | 1802500.3 |  |  | 448398.7 | 0 | 1354101.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15189 | -15189 | 15189 | -15189 | 464389 | 0 | 132 | -132 | 0 | 235.3 | 434935.9 | 13227.5 | 14028.6 | 0 | 2596 | 2650 | 2573 | 2459 | 2819 | 0 | 0 | 0 | 0 | 0 | 0 | 2094
35145540 | PSPS - FROGTOWN 1702 - CB | E.5025634.01 | 5788779 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | ANGLSCMP | Stockton Assets | 2846 | 3872 | 0 | 6718 | 1.2723 | 0 | 1.2723 | 0 | 1.2723 | 6718 | 0 | 1.2723 | 0 |  | 5959167 | 1836977 | 4122190 |  |  | 275350.6 | 7471 | 3839368.4 | On/Under Budget | Budget Allocated | 500000 | 488856 | 11144 | 488856 | 11144 | 698665.4 | 582.6 | -1420.1 | 2002.7 | 0 | 0 | 187046.8 | 88303.7 | 22762.6 | 0 | 22610 | 30733 | 6917 | 24838 | 4626 | 583 | 592 | 592 | 592 | 592 | 592 | 395592 | 2021-06-18 | 158094 | BL-0_ | BL-0_35145540_PSPS - Frogtown 1702 - CB_08W_Mar.2021 | 2021-03-30 | 2020-09-02 | Completed | 2021-02-01 | 2021-02-19 | Completed | 2021-09-01 | Not Started | 2021-09-02 | Not Started | 2021-09-29 | 2021-10-05 | Not Started | 2021-10-06 | 2021-10-26 | Not Started | 2021-02-01 | 2021-02-12 | Completed | 2021-10-28 | Not Started |  |  |  |  | 2021-10-28 | Not Started | 2022-01-26 | Not Started | 2022-02-24 | Not Started | 2022-09-13 | 2022-04-27 | 139 | On/ Ahead Schedule | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2022-06-17 | Not Started
35145006 | PSPS - STAFFORD 1101 LR 1298 | E.5025644.01 | 5788788 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | SNRAFAEL | North Bay Assets | 1426 | 0 | 0 | 1426 | 0.27008 | 0 | 0 | 0 | 0.27008 | [5 empty] | 1039463.18 | 539463.18 | 500000 |  |  | 136551.5 | 0 | 363448.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9165 | -9165 | 9165 | -9165 | 1122349.5 | 344.7 | 223.3 | 121.4 | 0 | 1411.7 | 128240.8 | 6898.9 | 983532.3 | 0 | 1919 | 912 | 986 | 747 | 2112 | 345 | 357 | 357 | 357 | 357 | 357 | 357 | 2021-06-18 | 147036 | BL-A | BL-A 35145006_CWSP - STAFFORD 1101 LR 1298_08W - JUNE 2021 | 2020-08-12 | 2022-01-04 | Not Started | 2022-01-06 | 2022-01-19 | Not Started |  |  | 2022-02-15 | Not Started | [9 empty] | 2022-05-19 | Not Started |  |  |  |  | 2022-05-19 | Not Started | 2022-07-13 | Not Started | 2022-07-13 | Not Started | 2021-06-29 | 2022-07-13 | -379 | Behind Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2023-01-16 | Not Started
35145522 | PSPS - CLARKSVILLE 2104 - CB UG | E.5025635.01 | 5788783 | PEND | 08W | [6 empty] | Not in the WP | 2022 | SH | AUBURN | Sierra Assets | 20830 | 0 | 0 | 20830 | 3.9451 | 0 | 3.9451 | 0 | 3.9451 | [5 empty] | 500000 | 0 | 500000 |  |  | 159310 | 0 | 340690 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10364 | -10364 | 10364 | -10364 | 228604.6 | 297.8 | 132 | 165.8 | 0 | 0 | 150941.2 | 8368.7 | 67299.5 | 0 | 4134 | 1285 | 899 | 893 | 1025 | 298 | 305 | 305 | 305 | 305 | 305 | 305 | 2021-06-18 | 160838 | BL-A: | BL-A: 35145522_PSPS - Clarksville 2104 - CB_08W - May 21 | 2021-05-18 | 2020-06-16 | Completed | 2022-02-18 | 2022-02-24 | Not Started | 2021-12-02 | Not Started | 2022-03-17 | Not Started | 2021-12-03 | 2021-12-03 | Not Started | 2021-12-06 | 2021-12-24 | Not Started |  |  |  | 2022-04-11 | Not Started |  |  |  |  | 2022-04-11 | Not Started | 2022-09-05 | Not Started | 2022-10-04 | Not Started | 2022-12-05 | 2022-12-05 | 0 | On/ Ahead Schedule | Not Started | 2022-12-06 | 2022-12-19 | Not Started | 2023-01-25 | Not Started
35144941 | *CANC* PAUL SWEET 2105 - CB PH 1 | E.5025646.01 | 5788792 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 3859 | 9792 | 0 | 13651 | 2.5854 | 0 | 0 | 0 | 2.5854 | [5 empty] | 500000 | 0 | 500000 |  |  | 233585.3 | 0 | 266414.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 48741 | -48741 | 48380 | -48380 | 6158310.8 | 1366.4 | 83.2 | 1283.2 | 0 | 5881.9 | 188977.4 | 38726 | 5897072.8 | 17998.4 | 8725 | 21953 | 2661 | 2595 | 2708 | 1633 | 1411 | 1411 | 1411 | 1411 | 1411 | 1411
35144943 | *CANC* ROB ROY 2105 - CB | E.5025648.01 | 5788791 | PEND | 08W | [6 empty] | Not in the WP |  | SH | STCRUZ | Central Coast Assets | 3326 | 0 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0.62992 | [5 empty] | 687880.23 | 187880.23 | 500000 |  |  | 113917.9 | 0 | 386082.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 19101 | -19101 | 21223 | -21223 | 1744727.8 | 1074.1 | 83.2 | 990.9 | 0 | 2588 | 97677.2 | 13652.8 | 1623239.6 | 0 | 5126 | 2722 | 1541 | 2299 | 1881 | 1384 | 691 | 691 | 691 | 691 | 691 | 691
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | 5530170 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | SNMATEO | Peninsula Assets | 1348 | 0 | 0 | 1348 | 0.2553 | 0 | 0.2553 | 0 | 0.2553 | 1385 | 0 | 0.26231 | 0 |  | 500000 | 0 | 500000 |  |  | 135546.1 | 0 | 364453.9 | On/Under Budget | Budget Allocated | 8662.9 | 20300 | -11637.1 | 20300 | -11637.1 | 1514041.5 | 718.8 | 66.6 | 652.2 | 0 | 1643.5 | 118567.7 | 15334.8 | 1373530.5 | 0 | 671 | 1415 | 1628 | 6729 | 4826 | 719 | 719 | 719 | 719 | 719 | 719 | 719 | 2021-06-18 | 161148 | BL-B: | BL-B: 35144944_PSPS - SNEATH LANE 1107 - LR 48338 - May 21 | 2021-05-28 | 2020-05-29 | Completed | 2020-10-06 | 2022-04-15 | Not Started | 2022-05-19 | Not Started | 2022-05-20 | Not Started | 2022-05-17 | 2022-05-17 | Not Started | 2022-05-18 | 2022-06-07 | Not Started | 2022-02-18 | 2022-02-24 | Not Started | 2022-06-15 | Not Started |  |  |  |  | 2022-06-15 | Not Started | 2022-07-01 | Not Started | 2022-07-22 | Not Started | 2022-08-19 | 2022-08-19 | 0 | On/ Ahead Schedule | Not Started | 2022-08-22 | 2022-09-02 | Not Started | 2022-10-11 | Not Started
35145001 | PSPS - CLAYTON 2215 - CB | E.5025639.01 | 5788778 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | CONCORD | Diablo Assets | 9720 | 375 | 0 | 10095 | 1.9119 | 0 | 1.9119 | 0 | 1.9119 | [5 empty] | 500000 | 0 | 500000 |  |  | 210535.5 | 0 | 289464.5 | On/Under Budget | Budget Allocated | 26497.1 | 52340 | -25842.9 | 52340 | -25842.9 | 8135353.8 | 2264.6 | 570.7 | 1693.9 | 0 | 5411.3 | 170533.4 | 34590.8 | 7835517.9 | 71551 | 4275 | 3050 | 17493 | 5605 | 3596 | 2265 | 1997 | 2014 | 758 | 758 | 758 | 9771 | 2021-06-18 | 161149 | BL-B: | BL-B: 35145001_CWSP - CLAYTON 2215 - CB May 21 | 2021-05-28 | 2020-10-14 | Completed | 2021-09-10 | 2021-09-23 | Not Started | 2021-03-03 | Completed | 2022-01-14 | Not Started | 2022-01-24 | 2022-02-04 | Not Started | 2022-02-07 | 2022-02-11 | Not Started | 2022-01-24 | 2022-02-11 | Not Started | 2022-02-21 | Not Started | 2022-02-14 | Not Started | 2022-06-07 | Not Started |  |  | 2022-08-10 | Not Started | 2022-09-06 | Not Started | 2023-05-22 | 2022-10-04 | 230 | On/ Ahead Schedule | Not Started | 2022-10-05 | 2022-10-18 | Not Started | 2022-11-24 | Not Started
35145002 | PSPS - IGNACIO 1101 - CB | E.5025640.01 | 5788780 | PEND | 08W | [6 empty] | Not in the WP | 2021 | SH | SNRAFAEL | North Bay Assets | 6847 | 0 | 0 | 6847 | 1.2968 | 0 | 0 | 0 | 1.2968 | [5 empty] | 2311410.91 | 1811410.91 | 500000 |  |  | 124844.2 | 0 | 375155.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6070 | -6070 | 6070 | -6070 | 125522.8 | 317.2 | 273 | 44.2 | 0 | 4235 | 115218 | 5391.2 | 0 | 0 | 1189 | 929 | 1382 | 923 | 695 | 317 | 317 | 317 | 0 | 0 | 0 | 0 | 2021-06-18 | 161313 | BL-A1 | BL-A1: 35145002_CWSP - IGNACIO 1101 - CB_08W (On-Hold) - May 21 | 2021-06-02 | 2020-11-02 | Completed | 2021-06-18 | 2021-07-01 | Not Started | 2021-07-15 | Not Started | 2021-07-16 | Not Started | 2021-06-18 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | [6 empty] | 2021-12-06 | Not Started | 2022-01-28 | Not Started | 2022-01-28 | Not Started | 2022-11-07 | 2022-01-31 | 280 | On/ Ahead Schedule | Not Started | 2022-01-31 | 2022-02-11 | Not Started | 2022-03-22 | Not Started
35145003 | PSPS CWSP - MORAGA 1103 - CB | E.5025641.01 | 5788781 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | WALNTCRK | Diablo Assets | 1268 | 420 | 0 | 1688 | 0.3197 | 0.3197 | 0 | 0 | 0.3197 | [5 empty] | 500000 | 0 | 500000 |  |  | 105158.7 | 0 | 394841.3 | On/Under Budget | Budget Allocated | 14308.2 | 16695 | -2386.8 | 16695 | -2386.8 | 1168093.5 | 1161.7 | 963.4 | 198.3 | 0 | 5176.1 | 90599.8 | 9382.8 | 1055622.6 | 0 | 1135 | 1811 | 1818 | 1828 | 1827 | 1162 | 1175 | 1179 | 1184 | 1188 | 1192 | 1196 | 2021-06-18 | 161150 | BL-B: | BL-B: 35145003_CWSP - MORAGA 1103 - CB - May 21 | 2021-05-28 | 2020-06-03 | Completed |  |  | Not Started | 2021-07-02 | Not Started | 2021-07-15 | Not Started |  |  |  | 2021-08-10 | 2021-08-16 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-08-24 | Not Started |  |  |  |  | 2021-09-07 | Not Started | 2021-10-07 | Not Started | 2021-11-02 | Not Started | 2022-08-26 | 2021-11-30 | 269 | On/ Ahead Schedule | Not Started | 2021-12-01 | 2021-12-14 | Not Started | 2022-04-19 | Not Started
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB | E.5025642.01 | 5788782 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | WALNTCRK | Diablo Assets | 3073 | 1965 | 0 | 5038 | 0.95417 | 0.95417 | 0 | 0 | 0.95417 | [5 empty] | 500000 | 0 | 500000 |  |  | 104614.9 | 0 | 395385.1 | On/Under Budget | Budget Allocated | 13613.7 | 16984 | -3370.3 | 16984 | -3370.3 | 2504066.6 | 1103.5 | 893.7 | 209.8 | 0 | 4705.5 | 89894.3 | 10015 | 2392483.2 | 0 | 1533 | 2060 | 1904 | 1813 | 1812 | 1104 | 1116 | 1120 | 1124 | 1129 | 1133 | 1137 | 2021-06-18 | 161151 | BL-B: | BL-B: 35145004_CWSP - ROSSMOOR 1106 - CB - May 21 | 2021-05-28 | 2020-07-13 | Completed | 2021-06-18 | 2021-07-15 | Not Started | 2021-07-26 | Not Started | 2021-07-27 | Not Started |  |  |  | 2021-07-09 | 2021-08-19 | Not Started | 2021-09-07 | 2021-09-07 | Not Started | 2021-11-09 | Not Started |  |  |  |  | 2021-11-30 | Not Started | 2021-12-27 | Not Started | 2022-02-01 | Not Started | 2023-11-17 | 2022-03-01 | 626 | On/ Ahead Schedule | Not Started | 2022-03-02 | 2022-03-15 | Not Started | 2022-07-19 | Not Started
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | E.5034352.01 | 5541303 | PEND | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 11721.6 | 0 | 11721.6 | 2.22 | 2.2201 | 0 | 0 | 2.22 | [5 empty] | 959851.78 | 277451.78 | 682400 | 0 | 682400 | 132297.4 | 0 | 550102.6 | On/Under Budget | Request 2021 Budget | 0 | 4979840 | -4979840 | 647581 | -647581 | 656838.1 | 3494.9 | 2449.1 | 1045.8 | 0 | 0 | 9257.6 | 123039.9 | 0 | 0 | 4209 | 15753 | 45330 | 42047 | 13252 | 12908 | 160855 | 160855 | 1530716 | 1422378 | 1455400 | 116137 | 2021-06-18 | 161696 | BL-B: | BL-B: 35191318_ECOP - SILVERADO 2102 - H02-LR58626_08W - Jun 21 | 2021-06-16 | 2021-04-29 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-02 | Completed | 2021-08-12 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2021-09-01 | 2021-09-14 | Not Started | 2021-09-16 | Not Started | 2021-09-16 | Not Started | 2021-09-29 | Not Started | 2021-09-16 | Not Started | 2021-11-01 | Not Started | 2021-11-30 | Not Started | 2022-01-31 | 2022-01-31 | 0 | On/ Ahead Schedule | Not Started | 2022-02-01 | 2022-02-14 | Not Started | 2022-03-30 | Not Started
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | E.5034359.01 | 5541309 | PEND | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 7542 | 0 | 7542 | 1.4284 | 1.4284 | 0 | 0 | 1.4284 | 7542 | 0 | 1.4284 | 0 |  | 614000 | 0 | 614000 | 0 | 614000 | 88350.9 | 0 | 525649.1 | On/Under Budget | Request 2021 Budget | 0 | 3326619 | -3326619 | 580018 | -580018 | 584207.6 | 13563.3 | 1178.5 | 12384.8 | 0 | 0 | 4189.8 | 84161 | 0 | 0 | 4944 | 17876 | 30146 | 14791 | 15226 | 13563 | 231668 | 973106 | 974368 | 986421 | 47637 | 16874 | 2021-06-18 |  |  |  |  | 2021-03-31 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-12 | Not Started | 2021-06-18 | 2021-07-22 | Not Started | 2021-07-23 | 2021-08-05 | Not Started | 2021-07-15 | 2021-07-28 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-08-27 | Not Started | 2021-08-16 | Not Started | 2021-09-30 | Not Started | 2021-10-29 | Not Started | 2021-12-30 | 2021-12-30 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2022-02-28 | Not Started
35219272 | CWSP - MIDDLETOWN 1101481876 | E.5034696.01.02 | 5794547 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4857.6 | 0 | 4857.6 | 0.92 | 0.92 | 0 | 0 | 0.92 | 4698 | 0 | 0.88977 | 0 |  | 184734.86 | -765265.14 | 950000 |  |  | 10770.5 | 0 | 939229.5 | On/Under Budget | Request 2021 Budget | 0 | 100177 | -100177 | 100177 | -100177 | 100278.6 | 20517.1 | -65408.4 | 85925.5 | 0 | 0 | 0 | 10770.6 | 101.5 | 0 | 5392 | 3419 | 22338 | 17659 | 27372 | 20517 | 580 | 580 | 580 | 580 | 580 | 580 | 2021-06-18 | 157826 | BL-A | BL-A 35219272_CWSP - MIDDLETOWN 1101481876_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-18 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-07-19 | 2021-07-30 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-01-18 | 2022-01-12 | 6 | On/ Ahead Schedule | Not Started | 2022-01-20 | 2022-02-02 | Not Started | 2022-03-11 | Not Started
35219273 | CWSP - VOLTA 110149742 | E.5034705.01.01 | 5794543 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | REDBLUFF | North Valley Assets | 0 | 18123 | 0 | 18123 | 3.4324 | 0 | 3.4324 | 0 | 3.4324 | 18123 | 0 | 3.4324 | 0 |  | 633229.22 | -316770.78 | 950000 |  |  | 219071.8 | 0 | 730928.2 | On/Under Budget | Request 2021 Budget | 0 | 258089 | -258089 | 258089 | -258089 | 1966009.2 | 5139.6 | 626.3 | 4513.3 | 0 | 0 | 0 | 219071.9 | 1707920 | 0 | 5873 | 3463 | 124591 | 48137 | 36382 | 5140 | 3547 | 1735 | 4769 | 24453 | 0 | 0 | 2021-06-18 | 156055 | BL-A | BL-A _35219273_ CWSP - VOLTA 110149742_ Feb.2021 | 2021-02-18 | 2021-07-05 | Not Started | 2021-07-30 | 2021-08-05 | Not Started | 2021-07-29 | Not Started | 2021-09-14 | Not Started | 2021-07-06 | 2021-07-06 | Not Started | 2021-07-07 | 2021-07-19 | Not Started | 2021-07-30 | 2021-08-06 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-09-30 | Not Started | 2021-09-17 | Not Started | 2021-11-04 | Not Started | 2021-11-23 | Not Started | 2022-02-01 | 2022-02-15 | -14 | Behind Schedule | Not Started | 2022-02-16 | 2022-03-01 | Not Started | 2022-04-14 | Not Started
35219268 | CWSP - MARIPOSA 210197142 PH 1 | E.5034703.01.01 | 5794541 | PEND | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 8553.6 | 0 | 8553.6 | 1.62 | 1.6201 | 0 | 0 | 1.62 | 10425 | 0 | 1.9744 | 0 |  | 1289702.13 | 339702.13 | 950000 |  |  | 199188.7 | 0 | 750811.3 | On/Under Budget | Budget Allocated | 1670921 | 1721567 | -50646 | 199390 | 1471531 | 199390.4 | 0 | -201.7 | 201.7 | 0 | 0 | 0 | 199188.6 | 0 | 0 | 2025 | 104547 | 42116 | 20485 | 30218 | 67740 | 102833 | 719480 | 310589 | 289152 | 16454 | 15929 | 2021-06-18 | 156030 | BL-A | BL-A 35219268_CWSP - MARIPOSA 210197142 PH 1_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-25 | Completed | 2021-06-14 | 2021-06-16 | Not Started | 2021-08-19 | Not Started | 2021-08-20 | Not Started | 2021-08-06 | 2021-08-06 | Not Started | 2021-08-09 | 2021-09-10 | Not Started | 2021-05-03 | 2021-05-14 | Completed | 2021-09-14 | Not Started |  |  |  |  | 2021-09-14 | Not Started | 2021-11-08 | Not Started | 2021-11-15 | Not Started | 2021-12-21 | 2022-01-14 | -24 | Behind Schedule | Not Started | 2022-01-17 | 2022-01-28 | Not Started | 2022-03-15 | Not Started
35217273 | SH - UPPER LAKE 1101 CB | E.5034612.01.01 | 5794203 | PEND | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5702.4 | 0 | 5702.4 | 1.08 | 1.08 | 0 | 0 | 1.08 | 5690 | 0 | 1.0777 | 0 |  | 360825.19 | -139174.81 | 500000 |  |  | 44898.8 | 0 | 455101.2 | On/Under Budget | Request 2021 Budget | 0 | 68772 | -68772 | 68772 | -68772 | 71314.2 | 23790.6 | 3519.3 | 20271.3 | 0 | 0 | 2331.9 | 42566.9 | 210.9 | 0 | 7023 | 5513 | 653 | 2279 | 23580 | 23791 | 3873 | 412 | 412 | 412 | 412 | 412 | 2021-06-18 | 156046 | BL-A | BL-A 35217273 _SH - UPPER LAKE 1101 CB_08W - Feb. 2021 | 2021-02-17 | 2021-07-27 | Not Started | 2021-07-28 | 2021-08-03 | Not Started | 2021-11-01 | Not Started | 2021-11-02 | Not Started | 2021-07-28 | 2021-07-28 | Not Started | 2021-07-29 | 2021-08-18 | Not Started | 2021-10-01 | 2021-10-15 | Not Started | 2021-11-25 | Not Started | 2021-11-25 | Not Started | 2021-12-08 | Not Started | 2021-11-25 | Not Started | 2022-01-12 | Not Started | 2022-02-10 | Not Started | 2022-04-01 | 2022-04-05 | -4 | Behind Schedule | Not Started | 2022-04-06 | 2022-04-19 | Not Started | 2022-06-02 | Not Started
35219266 | CWSP - MARIPOSA 2102CB PH 1 | E.5034702.01.01 | 5794552 | PEND | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 13713 | 0 | 13713 | 2.5972 | 2.5972 | 0 | 0 | 2.5972 | 15653 | 0 | 2.9646 | 0 |  | 1304482.44 | 354482.44 | 950000 |  |  | 184822.4 | 0 | 765177.6 | On/Under Budget | Request 2021 Budget | 0 | 2645783 | -2645783 | 180054 | -180054 | 183136 | 0 | 1686.4 | -1686.4 | 0 | 0 | 3082.1 | 181740.5 | 0 | 0 | 5965 | 68524 | 76968 | 24809 | 3789 | 120811 | 757540 | 775288 | 741216 | 24108 | 21143 | 25624 | 2021-06-18 | 156028 | BL-A | BL-A 35219266_CWSP - MARIPOSA 2102CB PH 1_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-04-01 | Completed | 2021-06-07 | 2021-06-17 | Not Started | 2021-08-18 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | 2021-08-19 | Not Started | 2021-08-20 | 2021-09-09 | Not Started | 2021-06-08 | 2021-06-21 | In Progress | 2021-09-13 | Not Started |  |  |  |  | 2021-09-13 | Not Started | 2021-11-05 | Not Started | 2021-11-08 | Not Started | 2021-11-23 | 2022-01-06 | -44 | Behind Schedule | Not Started | 2022-01-07 | 2022-01-20 | Not Started | 2022-03-07 | Not Started
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | E.5034802.01.01 | 5543352 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | OROVILLE | North Valley Assets | 0 | 4224 | 0 | 4224 | 0.8 | 0.8 | 0 | 0 | 0.8 | 6951 | 0 | 1.3165 | 0 |  | 516372.27 | 216372.27 | 300000 |  |  | 83083.3 | 0 | 216916.7 | On/Under Budget | Budget Allocated | 1520000 | 929347 | 590653 | 932118 | 587882 | 932317.7 | 211868.7 | 3193.7 | 208675 | 0 | 0 | 199.4 | 82883.9 | 0 | 0 | 11297 | 410 | 46945 | 28070 | -7032 | 29919 | 421629 | 296406 | 101702 | 0 | 0 | 0 | 2021-06-18 | 160959 | BL-A_ | BL-A_35219260_CWSP - WYANDOTTE 110932586 PH 1_08W_May.2021 | 2021-05-20 | 2021-04-16 | Completed |  |  | Not Started | 2021-04-22 | Completed | 2021-06-30 | Not Started | 2021-07-01 | 2021-07-01 | Not Started | 2021-07-02 | 2021-07-05 | Not Started | 2021-07-05 | 2021-07-19 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-07-20 | Not Started | 2021-07-07 | Not Started | 2021-08-23 | Not Started | 2021-08-30 | Not Started | 2021-11-19 | 2021-11-26 | -7 | Behind Schedule | Not Started | 2021-11-29 | 2021-12-10 | Not Started | 2022-01-25 | Not Started
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | E.5034607.01.01 | 5794208 | PEND | 08W | [6 empty] | 2022 |  | SH | CHICO | North Valley Assets | 0 | 1056 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0.2 | 453 | 0 | 0.085795 | 0 |  | 150000 | 0 | 150000 |  |  | 38605.7 | 0 | 111394.3 | On/Under Budget | Budget Allocated | 380000 | 596087 | -216087 | 596087 | -216087 | 596691.5 | 16091.7 | 685.2 | 15406.5 | 0 | 0 | 604.7 | 38001 | 0 | 0 | 15934 | 2442 | 1971 | 13425 | 3544 | 16092 | 100342 | 110342 | 192349 | 76008 | 62115 | 1525
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | E.5034695.01.01 | 5794546 | PEND | 08W | [6 empty] | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 13091 | 0 | 13091 | 2.4794 | 2.4794 | 0 | 0 | 2.4794 | 13091 | 0 | 2.4794 | 0 |  | 1648337.84 | 1373337.84 | 275000 |  |  | 166611.1 | 92969.3 | 15419.6 | On/Under Budget | Request 2021 Budget | 0 | 3636630 | -3636630 | 3636630 | -3636630 | 3636630 | 221188.9 | 583.6 | 220605.3 | 0 | 0 | 0 | 166611.1 | 0 | 0 | 6123 | 21026 | 52664 | 75487 | 10728 | 221189 | 634351 | 1234892 | 1219696 | 94088 | 44238 | 22149 | 2021-06-18 |  |  |  |  | 2021-04-30 | Completed | 2021-05-26 | 2021-06-02 | Completed | 2021-07-21 | Not Started | 2021-07-21 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-15 | 2021-08-11 | Not Started | 2021-06-22 | 2021-07-09 | Not Started | 2021-08-13 | Not Started |  |  |  |  | 2021-08-13 | Not Started | 2021-10-21 | Not Started | 2021-10-22 | Not Started | 2021-12-29 | 2021-12-29 | 0 | On/ Ahead Schedule | Not Started | 2021-12-30 | 2022-01-12 | Not Started | 2022-02-25 | Not Started
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | E.5034696.01.01 | 5794547 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3710 | 0 | 3710 | 0.70265 | 0.70265 | 0 | 0 | 0.70265 | 3710 | 0 | 0.70265 | 0 |  | 198553.88 | -276446.12 | 475000 |  |  | 41787.8 | 0 | 433212.2 | On/Under Budget | Request 2021 Budget | 0 | 1750658 | -1750658 | 468973 | -468973 | 468972.9 | 13437.7 | -57541.6 | 70979.3 | 0 | 0 | 0 | 41787.7 | 0 | 0 | 6820 | 8059 | 60767 | 14742 | 8942 | 13438 | 758977 | 702379 | 30906 | 31034 | 76711 | 37885 | 2021-06-18 | 159393 | BL-A: | BL-A: 35219098_CWSP - MIDDLETOWN 1101118494 Ph1_08W - B1_Apr 21 | 2021-04-21 | 2021-04-30 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-05-25 | Completed | 2021-07-08 | Not Started | 2021-06-18 | 2021-07-30 | In Progress | 2021-08-02 | 2021-08-05 | Not Started | 2021-06-01 | 2021-06-15 | Completed | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-08-27 | Not Started | 2021-08-16 | Not Started | 2021-09-15 | Not Started | 2021-10-14 | Not Started | 2022-02-03 | 2021-12-15 | 50 | On/ Ahead Schedule | Not Started | 2021-12-16 | 2021-12-29 | Not Started | 2022-02-11 | Not Started
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | E.5034794.01.04 | 5795152 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 7709 | 0 | 7709 | 1.46 | 1.46 | 0 | 0 | 1.46 | 3943 | 0 | 0.74678 | 0 |  | 302731.26 | 152731.26 | 150000 |  |  | 1356.1 | 0 | 148643.9 | On/Under Budget | Request 2021 Budget | 0 | 47438 | -47438 | 47438 | -47438 | 47507.4 | 20213.5 | -24220.2 | 44433.7 | 0 | 0 | 0 | 1356.2 | 69.2 | 0 | 0 | 0 | 687 | 7778 | 17111 | 20214 | 275 | 275 | 275 | 275 | 275 | 275 | 2021-06-18 | 157831 | BL-A | BL-A 35226624_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-12 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-13 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-09-07 | Not Started | 2021-09-07 | Not Started | 2021-09-20 | Not Started | 2021-09-07 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-02-24 | 2022-03-21 | -25 | Behind Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-18 | Not Started
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 | E.5034707.01.02 | 5794545 | PEND | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 16579.2 | 0 | 16579.2 | 3.14 | 3.14 | 0 | 0 | 3.14 | 14924 | 0 | 2.8265 | 0 |  | 1015064.91 | 615064.91 | 400000 |  |  | 92789.2 | 89306.6 | 217904.2 | On/Under Budget | Request 2021 Budget | 0 | 5123367 | -5123367 | 5123367 | -5123367 | 5151326.1 | 111870.8 | -31839 | 143709.8 | 0 | 0 | 0 | 92789.3 | 27959.3 | 0 | 1384 | 13305 | 509 | 1565 | 107866 | 111871 | 333239 | 1547034 | 1406983 | 786717 | 649955 | 162941 | 2021-06-18 | 161877 | BL-A | BL-A 35224378_CWSP - VACAVILLE 1104 LR 6542 PH 2.1_08W - DD 210618 | 2021-06-22 | 2021-06-21 | Completed | 2021-06-21 | 2021-07-02 | Not Started | 2021-08-20 | Not Started | 2021-08-23 | Not Started | 2021-08-17 | 2021-08-23 | Not Started | 2021-08-24 | 2021-09-13 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-09-15 | Not Started | 2021-09-15 | Not Started | 2021-09-15 | Not Started | 2021-09-15 | Not Started | 2021-11-16 | Not Started | 2021-11-17 | Not Started | 2022-02-15 | 2022-01-24 | 22 | On/ Ahead Schedule | Not Started | 2022-01-25 | 2022-02-07 | Not Started | 2022-03-23 | Not Started
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | E.5034611.01.02 | 5794204 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 1677 | 0 | 1677 | 0.31761 | 0.31761 | 0 | 0 | 0.31761 | 1677 | 0 | 0.31761 | 0 |  | 150000 | 0 | 150000 |  |  | 17292.5 | 0 | 132707.5 | On/Under Budget | Budget Allocated | 551000 | 853122 | -302122 | 853122 | -302122 | 853121.8 | 5920.7 | 865.7 | 5055 | 0 | 0 | 0 | 17292.5 | 0 | 0 | 0 | 0 | 25648 | -13084 | 3863 | 5921 | 5726 | 72998 | 71267 | 348397 | 330523 | 1864 | 2021-06-18 | 158023 | BL_A- | BL_A-35226627_SH - KESWICK 1101 LR 1586 PH 1.2_08W_Mar.2021 | 2021-03-26 | 2021-04-28 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-30 | Not Started | 2021-07-01 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-25 | 2021-07-15 | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-07-26 | Not Started |  |  |  |  | 2021-07-26 | Not Started | 2021-09-17 | Not Started | 2021-09-30 | Not Started | 2021-12-30 | 2021-11-05 | 55 | On/ Ahead Schedule | Not Started | 2021-11-08 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | E.5034611.01.05 | 5794204 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 7603.2 | 0 | 7603.2 | 1.44 | 1.4409 | 0 | 0 | 1.44 | 7390 | 0 | 1.3996 | 0 |  | 497898.74 | 347898.74 | 150000 |  |  | 80485.1 | 0 | 69514.9 | On/Under Budget | Budget Allocated | 2736000 | 3338024 | -602024 | 3340094 | -604094 | 3340094.3 | 261735.7 | 25076.6 | 236659.1 | 0 | 0 | 0 | 80485.1 | 0 | 0 | 0 | 0 | 24735 | 26091 | 4583 | 82871 | 424184 | 873692 | 882207 | 890877 | 124125 | 4660 | 2021-06-18 | 158024 | BL-A_ | BL-A_35226630_)SH - KESWICK 1101 LR 1586 PH 1.5_08W_Mar.2021 | 2021-03-26 | 2021-05-18 | Completed | 2021-06-10 | 2021-07-13 | Not Started | 2021-06-18 | Not Started | 2021-08-03 | Not Started | 2021-08-04 | 2021-08-04 | Not Started | 2021-08-05 | 2021-08-05 | Not Started | 2021-07-02 | 2021-07-15 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-08-20 | Not Started | 2021-08-09 | Not Started | 2021-10-22 | Not Started | 2021-11-22 | Not Started | 2021-12-30 | 2021-12-30 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2022-02-28 | Not Started
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | E.5034611.01.06 | 5794204 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | REDDING | North Valley Assets | 0 | 8131.2 | 0 | 8131.2 | 1.54 | 1.54 | 0 | 0 | 1.54 | 8132 | 0 | 1.5402 | 0 |  | 765014.63 | 615014.63 | 150000 |  |  | 55612 | 0 | 94388 | On/Under Budget | Budget Allocated | 2926000 | 3969988 | -1043988 | 3969988 | -1043988 | 3969987.6 | 22083 | 1165.8 | 20917.2 | 0 | 0 | 0 | 55612.1 | 0 | 0 | 0 | 262 | 25744 | 35375 | -6934 | 22083 | 238428 | 1155046 | 1173875 | 1169304 | 152144 | 4661 | 2021-06-18 | 158025 | BL-A_ | BL-A_35226631_SH - KESWICK 1101 LR 1586 PH 1.6_08W_Mar.2021 | 2021-03-26 | 2021-05-03 | Completed | 2021-06-22 | 2021-06-22 | Not Started | 2021-06-21 | Not Started | 2021-06-25 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2021-07-09 | 2021-07-22 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started |  |  | 2021-07-23 | Not Started | 2021-09-03 | Not Started | 2021-10-15 | Not Started | 2021-12-30 | 2021-11-29 | 31 | On/ Ahead Schedule | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-26 | Not Started
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | E.5034709.01.02 | 5794548 | PEND | 08W | [6 empty] | 2022 |  | SH | UKIAH | Humboldt Division Assets | 560 | 0 | 0 | 560 | 0.10606 | 0 | 0.10606 | 0 | 0.10606 | [5 empty] | 132166.93 | -342833.07 | 475000 |  |  | 10369.4 | 0 | 464630.6 | On/Under Budget | Request 2021 Budget | 0 | 57654 | -57654 | 57654 | -57654 | 58038.6 | 20272.3 | -25008.7 | 45281 | 0 | 0 | 0 | 10369.3 | 384.8 | 0 | 0 | 922 | 941 | 347 | 33168 | 20272 | 334 | 334 | 334 | 334 | 334 | 334 | 2021-06-18 | 157809 | BL-A | BL-A 35226632_CWSP - POTTER VALLEY PH 110564118 PH 1.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-07 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-10-22 | Not Started | 2021-10-25 | Not Started | 2021-10-25 | 2021-10-25 | Not Started | 2021-10-26 | 2021-11-15 | Not Started | 2021-10-25 | 2021-11-05 | Not Started | 2021-11-17 | Not Started | 2021-11-17 | Not Started | 2021-11-30 | Not Started | 2021-11-17 | Not Started | 2022-03-01 | Not Started | 2022-03-30 | Not Started | 2022-07-29 | 2022-05-31 | 59 | On/ Ahead Schedule | Not Started | 2022-06-01 | 2022-06-14 | Not Started | 2022-07-28 | Not Started
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | E.5034784.01.03 | 5795128 | PEND | 08W | [6 empty] | 2021 | 2022 | SH | REDBLUFF | North Valley Assets | 0 | 1015 | 0 | 1015 | 0.19223 | 0 | 0.19223 | 0 | 0.19223 | 1015 | 0 | 0.19223 | 0 |  | 71683.95 | -135816.05 | 207500 |  |  | 1136.7 | 0 | 206363.3 | On/Under Budget | Budget Allocated | 371000 | 17204 | 353796 | 17204 | 353796 | 403567.2 | 18.9 | -5604 | 5622.9 | 0 | 0 | 0 | 1136.6 | 386363.2 | 0 | 0 | 0 | 24321 | -19607 | 2027 | 19 | 10049 | 79 | 79 | 79 | 79 | 79 | 2021-06-18 | 158353 | BL-A_ | BL-A_35226799_CWSP - WILDWOOD 1101 LR 1454TEHAMACO PH3_08W_Apr.2021 | 2021-04-01 | 2021-07-01 | Not Started | 2022-05-06 | 2022-05-12 | Not Started | 2022-05-05 | Not Started | 2022-06-02 | Not Started | 2021-07-02 | 2021-07-02 | Not Started | 2021-07-05 | 2021-07-23 | Not Started | 2021-08-06 | 2021-09-02 | Not Started | 2022-07-11 | Not Started | 2022-07-11 | Not Started | 2022-07-22 | Not Started | 2022-07-11 | Not Started | 2022-10-21 | Not Started | 2022-11-21 | Not Started | 2022-02-16 | 2023-02-07 | -356 | Behind Schedule | Not Started | 2023-02-08 | 2023-02-21 | Not Started | 2023-04-06 | Not Started
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | E.5034792.01.02 | 5795144 | PEND | 08W | [6 empty] | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 4425 | 0 | 4425 | 0.83807 | 0.83807 | 0 | 0 | 0.83807 | 4425 | 0 | 0.83807 | 0 |  | 327628.41 | 177628.41 | 150000 |  |  | 115339.2 | 69156.5 | -34495.7 | OverRun | Request 2021 Budget | 0 | 2065038 | -2065038 | 2065038 | -2065038 | 2065037.6 | 8016.7 | 2683.3 | 5333.4 | 0 | 0 | 0 | 115339.3 | 0 | 0 | 461 | 1271 | 14923 | 46261 | 49741 | 8017 | 54154 | 26361 | 566749 | 665082 | 632019 | 0 | 2021-06-18 | 155776 | BL- A | BL- A 35225595_ECOP - FULTON 1107 - H02-LR604 Ph 1.3_08W - DD 210205 Feb.2021 | 2021-02-08 | 2021-05-28 | Completed | 2021-06-28 | 2021-07-09 | Not Started | 2021-09-10 | Not Started | 2021-09-13 | Not Started | 2021-09-07 | 2021-09-13 | Not Started | 2021-09-14 | 2021-10-04 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-11-19 | Not Started | 2021-11-22 | Not Started | 2021-12-27 | 2021-12-21 | 6 | On/ Ahead Schedule | Not Started | 2021-12-22 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | E.5034792.01.03 | 5795144 | PEND | 08W | [6 empty] | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 4190 | 0 | 4190 | 0.79356 | 0.79356 | 0 | 0 | 0.79356 | 4190 | 0 | 0.79356 | 0 |  | 355578.08 | 205578.08 | 150000 |  |  | 82573.9 | 60511.9 | 6914.2 | On/Under Budget | Request 2021 Budget | 0 | 1058385 | -1058385 | 1256755 | -1256755 | 1256755.2 | 6171.6 | 2063.6 | 4108 | 0 | 0 | 0 | 82574 | 0 | 0 | 461 | 2193 | 43824 | 24705 | 9327 | 6287 | 288025 | 322777 | 351528 | 4629 | 4629 | 0 | 2021-06-18 | 155777 | BL- A | BL- A 35225597_ ECOP - FULTON 1107 - H02-LR604 Ph 1.4_08W - DD 210205 Feb. 2021 | 2021-02-08 | 2021-04-27 | Completed | 2021-06-28 | 2021-07-09 | Not Started | 2021-05-24 | Completed | 2021-07-30 | Not Started | 2021-07-12 | 2021-07-16 | Not Started | 2021-07-19 | 2021-08-20 | Not Started | 2021-07-26 | 2021-08-06 | Not Started | 2021-08-24 | Not Started | 2021-08-24 | Not Started | 2021-08-24 | Not Started | 2021-08-24 | Not Started | 2021-10-07 | Not Started | 2021-10-08 | Not Started | 2021-12-27 | 2021-11-08 | 49 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-22 | Not Started | 2022-01-05 | Not Started
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | E.5034792.01.04 | 5795144 | PEND | 08W | [6 empty] | 2021 |  | SH | STROSA | Sonoma Assets | 0 | 4780 | 0 | 4780 | 0.9053 | 0.9053 | 0 | 0 | 0.9053 | 4780 | 0 | 0.9053 | 0 |  | 448488.21 | 298488.21 | 150000 |  |  | 84450.5 | 60511.9 | 5037.6 | On/Under Budget | Request 2021 Budget | 0 | 1207550 | -1207550 | 1757521 | -1757521 | 1757520.7 | 7993.7 | 4376.5 | 3617.2 | 0 | 0 | 0 | 84450.4 | 0 | 0 | 461 | 1963 | 6282 | 48485 | 22882 | 7909 | 75709 | 210844 | 390561 | 434047 | 8405 | 0 | 2021-06-18 | 155778 | BL- A | BL- A 35225598_ECOP - FULTON 1107 - H02-LR604 Ph 1.5_08W - DD 210205 Feb. 2021 | 2021-02-08 | 2021-05-16 | Completed | 2021-06-28 | 2021-07-09 | Not Started | 2021-07-02 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | 2021-07-30 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-07-12 | 2021-07-23 | Not Started | 2021-08-24 | Not Started | 2021-08-24 | Not Started | 2021-09-06 | Not Started | 2021-08-24 | Not Started | 2021-10-07 | Not Started | 2021-10-08 | Not Started | 2021-12-27 | 2021-11-08 | 49 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-22 | Not Started | 2022-01-05 | Not Started
35225821 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | E.5034825.01.78 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3346 | 0 | 0 | 3346 | 0.63371 | 0.63371 | 0 | 0 | 0.63371 | 6261 | 0 | 1.1858 | 0 |  | 5417838 | 2176586 | 3241252 | 1023259 | 2217993 | 98338.4 | 24978.5 | 3117935.1 | On/Under Budget | Budget Allocated | 3241252 | 3490163 | -248911 | 3490163 | -248911 | 3490163 | 18005.4 | 7749.7 | 10255.7 | 0 | 0 | 0 | 98338.3 | 0 | 0 | 1032 | 47934 | 1359 | 16432 | 23832 | 18005 | 1003193 | 1000523 | 137703 | 1240150 | 0 | 0 | 2021-06-11 | 161682 | BL-0: | BL-0: 35225821 FRRB - BIG BEND - LAKE MADRONE Ph 2 - Jun 21 | 2021-06-15 | 2021-06-10 | Completed | 2021-06-25 | 2021-07-08 | Not Started | 2021-06-24 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-06-11 | 2021-06-11 | Completed | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-12-02 | 2021-11-17 | 15 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35226240 | CWSP - MARIPOSA 210197142 PH 3 | E.5034703.01.03 | 5794541 | PEND | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 7526.4 | 0 | 7526.4 | 1.4255 | 1.4254 | 0 | 0 | 1.4255 | [5 empty] | 655862.69 | 655862.69 | 0 |  |  | 142860.1 | 0 | -142860.1 | OverRun | Budget Allocated | 1365471 | 1329848 | 35623 | 1329848 | 35623 | 1329847.9 | 88105.9 | 54413.5 | 33692.4 | 0 | 0 | 0 | 142860.2 | 0 | 0 | 0 | 54865 | 7073 | 10505 | 16004 | 88106 | 378515 | 533279 | 234557 | 6944 | 0 | 0 | 2021-06-18 | 161101 | BL-0 | BL-0 35226240_CWSP - MARIPOSA 210197142 PH 3_08W - DD 210521 | 2021-05-26 | 2021-02-27 | Completed | 2021-04-14 | 2021-04-20 | Completed | 2021-07-01 | Not Started | 2021-07-02 | Not Started | 2021-07-05 | 2021-07-05 | Not Started | 2021-07-06 | 2021-07-19 | Not Started | 2021-04-27 | 2021-05-07 | Completed | 2021-07-21 | Not Started |  |  |  |  | 2021-07-21 | Not Started | 2021-09-14 | Not Started | 2021-10-13 | Not Started | 2021-11-02 | 2021-12-14 | -42 | Behind Schedule | Not Started | 2021-12-15 | 2021-12-28 | Not Started | 2022-01-04 | Not Started
35226241 | CWSP - MARIPOSA 210197142 PH 2 | E.5034703.01.02 | 5794541 | PEND | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 7920 | 0 | 7920 | 1.5 | 1.5 | 0 | 0 | 1.5 | 6651 | 0 | 1.2597 | 0 |  | 485124.83 | 485124.83 | 0 |  |  | 83120.3 | 0 | -83120.3 | OverRun | Budget Allocated | 1218823 | 1220539 | -1716 | 1220539 | -1716 | 1220538.5 | 19905.3 | 475.3 | 19430 | 0 | 0 | 0 | 83120.4 | 0 | 0 | 0 | 44762 | 16855 | 12798 | 8231 | 19905 | 521286 | 96020 | 295492 | 192427 | 8104 | 4660 | 2021-06-18 | 156031 | BL-A | BL-A 35226241_CWSP - MARIPOSA 210197142 PH 2_08W - DD 210205 Feb. 2021 | 2021-02-17 | 2021-03-26 | Completed | 2021-05-25 | 2021-06-01 | Completed | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-07-19 | 2021-07-19 | Not Started | 2021-07-20 | 2021-08-23 | Not Started | 2021-06-14 | 2021-06-16 | Completed | 2021-08-25 | Not Started |  |  |  |  | 2021-08-25 | Not Started | 2021-10-19 | Not Started | 2021-10-20 | Not Started | 2021-12-22 | 2021-12-27 | -5 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-10 | Not Started | 2022-02-23 | Not Started
35225825 | CWSP - DESCHUTES 11049718 PH2.1 | E.5034713.01.02 | 5794554 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 8270 | 0 | 8270 | 1.5663 | 1.5663 | 0 | 0 | 1.5663 | 8100 | 0 | 1.5341 | 0 |  | 2167192 | 567557 | 1599635 | 0 | 1599635 | 66991.4 | 0 | 1532643.6 | On/Under Budget | Budget Allocated | 2167192 | 1454468 | 712724 | 1454468 | 712724 | 1454467.5 | 144.2 | 42966.1 | -42821.9 | 0 | 0 | 0 | 66991.4 | 0 | 0 | 0 | 8957 | 8577 | 1918 | 4574 | 144 | 426385 | 693099 | 17449 | 293365 | 0 | 0 | 2021-06-18 | 158344 | BL-A_ | BL-A_35225825_CWSP - DESCHUTES 11049718 PH2.1_08W_Apr.2021 | 2021-04-01 | 2021-06-02 | Completed |  |  | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-06-02 | 2021-06-02 | Completed | 2021-06-18 | 2021-07-08 | Not Started | 2021-08-02 | 2021-08-20 | Not Started | 2021-08-09 | Not Started |  |  |  |  | 2021-08-09 | Not Started | 2021-09-10 | Not Started | 2021-09-27 | Not Started | 2022-02-16 | 2021-10-11 | 128 | On/ Ahead Schedule | Not Started | 2021-10-12 | 2021-10-25 | Not Started | 2021-12-08 | Not Started
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 | E.5034741.01.01 | 5794898 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4699 | 0 | 4699 | 0.88996 | 0.88996 | 0 | 0 | 0.88996 | 4829 | 0 | 0.91458 | 0 |  | 1 | -720999 | 721000 |  |  | 31729.4 | 0 | 689270.6 | On/Under Budget | Request 2021 Budget | 0 | 50627 | -50627 | 50627 | -50627 | 51386.4 | 20231.8 | 3093.5 | 17138.3 | 0 | 0 | 0 | 31729.3 | 759.4 | 0 | 2859 | 3391 | 1844 | 1035 | 19508 | 20232 | 293 | 293 | 293 | 293 | 293 | 293 | 2021-06-18 | 157828 | BL-A | BL-A 35222045_SH - MIDDLTOWN 1103 - LR 830 PH4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-09 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-02-21 | 3 | On/ Ahead Schedule | Not Started | 2022-02-28 | 2022-03-11 | Not Started | 2022-04-20 | Not Started
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | E.5034767.01.03 | 5794998 | PEND | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 9219 | 0 | 9219 | 1.746 | 1.746 | 0 | 0 | 1.746 | 9219 | 0 | 1.746 | 0 |  | 728980.87 | 538980.87 | 190000 | 0 | 190000 | 99775.8 | 0 | 90224.2 | On/Under Budget | Request 2021 Budget | 0 | 4407576 | -4407576 | 178990 | -178990 | 187489.3 | 4070.2 | 1800.2 | 2270 | 0 | 0 | 0 | 99775.8 | 8499.4 | 0 | 0 | 17012 | 47392 | 21936 | 11636 | 6817 | 181247 | 978498 | 813917 | 819865 | 748408 | 760848 | 2021-06-18 | 159389 | BL-A: | BL-A: 35223027_ECOP - SILVERADO 2104 - H05 - LR726 PH4_08W - B1_Apr 21 | 2021-04-21 | 2021-04-21 | Completed |  |  | Not Started | 2021-05-03 | Completed | 2021-07-08 | Not Started | [9 empty] | 2021-08-23 | Not Started | [8 empty] | 2021-12-20 | Not Started | 2021-12-22 | 2021-12-28 | -6 | Behind Schedule | Not Started | 2021-12-21 | 2021-12-28 | Not Started | 2022-09-06 | Not Started
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | 5794998 | PEND | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 5230 | 0 | 5230 | 0.99053 | 0.99053 | 0 | 0 | 0.99053 | 5230 | 0 | 0.99053 | 0 |  | 380810.72 | 190810.72 | 190000 | 0 | 190000 | 146146.7 | 0 | 43853.3 | On/Under Budget | Request 2021 Budget | 0 | 2594032 | -2594032 | 190255 | -190255 | 190254.9 | 16590.5 | 430.6 | 16159.9 | 0 | 0 | 0 | 146146.6 | 0 | 0 | 0 | 687 | 31039 | 76259 | 37731 | 17542 | 1179460 | 1043246 | 45929 | 54600 | 45812 | 61728 | 2021-06-18 | 159391 | BL-A: | BL-A: 35223028_ECOP - SILVERADO 2104 - H05 - LR726 PH 5_08W - B1_Apr 21 | 2021-04-21 | 2021-04-27 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-02 | Completed | 2021-08-10 | Not Started | 2021-06-18 | 2021-08-02 | In Progress | 2021-08-03 | 2021-08-10 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2021-08-27 | Not Started | 2021-08-16 | Not Started | 2021-09-16 | Not Started | 2021-10-15 | Not Started | 2022-02-01 | 2021-12-16 | 47 | On/ Ahead Schedule | Not Started | 2021-12-17 | 2021-12-30 | Not Started | 2022-02-14 | Not Started
35219291 | CWSP - VACA DIXON 1101126774 |  | 5543350 | PEND | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 2082 | 0 | 2082 | 0.39432 | 0.39432 | 0 | 0 | 0.39432 | 2082 | 0 | 0.39432 | 0 |  | 165125.99 | -784874.01 | 950000 |  |  | 59067.6 | 73247.2 | 817685.2 | On/Under Budget | Budget Allocated | 1265910 | 509203 | 756707 | 509203 | 756707 | 509203 | 108467.9 | -5523.3 | 113991.2 | 0 | 0 | 0 | 59067.7 | 0 | 0 | 6285 | 5478 | 7391 | 20368 | 25069 | 108468 | 325722 | 10443 | 2371 | -8759 | 3996 | 2371 | 2021-06-18 | 156236 | BL-A | BL-A 35219291_VACA DIXON 1101 - LR 126774_08W - DD 210219 Feb. 2021 | 2021-02-24 | 2021-03-10 | Completed | 2021-06-11 | 2021-06-12 | Not Started | 2021-04-26 | Completed | 2021-07-02 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-30 | Not Started | 2021-07-05 | 2021-07-16 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-25 | Not Started | 2021-08-27 | Not Started | 2021-08-31 | 2021-09-27 | -27 | Behind Schedule | Not Started | 2021-09-28 | 2021-10-11 | Not Started | 2021-11-24 | Not Started
35223037 | PSPS - OAKHURST 1101 - OAKHURST | E.5034765.01.01 | 5794989 | PEND | 08W | [6 empty] | 2021 |  | SH | OAKHURST | Yosemite Assets | 105.6 | 0 | 0 | 105.6 | 0.02 | 0.020076 | 0 | 0 | 0.02 | [5 empty] | 124376.18 | -375623.82 | 500000 |  |  | 31245.2 | 58611.9 | 410142.9 | On/Under Budget | Request 2021 Budget | 0 | 408681 | -408681 | 408681 | -408681 | 408680.8 | 95847.3 | 5429.8 | 90417.5 | 0 | 0 | 0 | 31245.2 | 0 | 0 | 1098 | 4833 | 13862 | 2965 | 3058 | 95847 | 252265 | 17281 | 6161 | 5756 | 2778 | 2778 | 2021-06-18 |  |  |  |  | 2021-03-18 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-05-17 | Completed | 2021-07-16 | Not Started | 2021-07-19 | 2021-07-19 | Not Started | 2021-07-20 | 2021-08-09 | Not Started | 2021-05-18 | 2021-05-21 | Completed | 2021-08-11 | Not Started | 2021-08-11 | Not Started | 2021-08-24 | Not Started | 2021-08-11 | Not Started | 2021-08-24 | Not Started | 2021-08-25 | Not Started | 2021-11-01 | 2021-11-01 | 0 | On/ Ahead Schedule | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-29 | Not Started
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | E.5034791.01 | 5544143 | PEND | 08W | [6 empty] | 2022 | 2022 | SH | CONCORD | Diablo Assets | 0 | 5544 | 0 | 5544 | 1.05 | 0 | 1.05 | 0 | 1.05 | 6032 | 0 | 1.1424 | 0 |  | 621258.86 | 221258.86 | 400000 |  |  | 192945.9 | 0 | 207054.1 | On/Under Budget | Request 2021 Budget | 0 | 202075 | -202075 | 202075 | -202075 | 2193498.5 | 2161.8 | 3841.8 | -1680 | 0 | 0 | 0 | 192945.8 | 1991423.4 | 0 | 0 | 27895 | 81147 | 33752 | 46311 | 2162 | 2162 | 2162 | 2162 | 2162 | 2162 | 0 | 2021-06-18 | 161152 | BL-B: | BL-B: 35225593_ECOP - CLAYTON 2212 - H01-LR2951 PH2_08W - May 21 | 2021-05-28 | 2021-05-20 | Completed | 2022-04-04 | 2022-04-08 | Not Started | 2022-04-01 | Not Started | 2022-04-29 | Not Started | 2022-05-09 | 2022-05-09 | Not Started | 2022-05-10 | 2022-05-30 | Not Started | 2022-05-30 | 2022-06-10 | Not Started | 2022-06-13 | Not Started |  |  |  |  | 2022-06-13 | Not Started | 2022-08-05 | Not Started | 2022-08-12 | Not Started | 2022-10-13 | 2022-10-13 | 0 | On/ Ahead Schedule | Not Started | 2022-10-14 | 2022-10-27 | Not Started | 2023-01-05 | Not Started
35223343 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | E.5034825.01.75 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5373 | 0 | 0 | 5373 | 1.0176 | 1.0176 | 0 | 0 | 1.0176 | 5373 | 0 | 1.0176 | 0 |  | 5929383 | 1913461 | 4015922 | 1040259 | 2975663 | 318710.6 | 1512022.4 | 2185189 | On/Under Budget | Budget Allocated | 4015922 | 3490211 | 525711 | 3490211 | 525711 | 3490210.7 | 470190.9 | 88832.7 | 381358.2 | 0 | 0 | 0 | 318710.6 | 0 | 0 | 375 | 52222 | 49416 | 134929 | -7065 | 470191 | 1006941 | 1004271 | 489724 | 134006 | 17787 | 137414 | 2021-06-11 | 161679 | BL-0: | BL-0: 35223343 FRRB - BIG BEND - LAKE MADRONE Ph 1 - Jun 21 | 2021-06-15 | 2021-05-24 | Completed | 2021-06-16 | 2021-06-17 | Not Started | 2021-06-17 | Not Started | 2021-06-18 | Not Started | [6 empty] | 2021-06-14 | 2021-06-14 | Not Started | 2021-06-21 | Not Started | 2021-06-21 | Not Started | 2021-08-20 | Not Started | 2021-06-21 | Not Started | 2021-09-06 | Not Started | 2021-09-06 | Not Started | 2021-10-27 | 2021-10-05 | 22 | On/ Ahead Schedule | Not Started | 2021-10-06 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
35244330 | FRRB - WYANDOTTE 11031974 - W1 SM1 | E.5034933.01.09 | 5796539 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 423 | 0 | 0 | 423 | 0.080114 | 0.080114 | 0 | 0 | 0.080114 | 423 | 0 | 0.080114 | 0 |  | 98000 | 0 | 98000 |  |  | 1087.1 | 0 | 96912.9 | On/Under Budget | Budget Allocated | 98000 | 337142 | -239142 | 337142 | -239142 | 337142.1 | 5000 | 385 | 4615 | 0 | 0 | 0 | 1087.1 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 5000 | 0 | 331440 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-08 | Not Started | 2021-07-23 | 2021-07-29 | Not Started | 2021-07-22 | Not Started | 2021-09-02 | Not Started | [6 empty] | 2021-07-13 | 2021-07-19 | Not Started | 2021-09-06 | Not Started | 2021-09-06 | Not Started | 2021-11-22 | Not Started | 2021-09-06 | Not Started | 2021-12-06 | Not Started | 2021-12-06 | Not Started | 2022-01-05 | 2022-01-05 | 0 | On/ Ahead Schedule | Not Started | 2022-01-05 | 2022-01-19 | Not Started | 2022-03-04 | Not Started
35248770 | FRRB - WYANDOTTE 11031974 - W1 SM2 | E.5034933.01.12 | 5796539 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 789 | 0 | 0 | 789 | 0.14943 | 0.14943 | 0 | 0 | 0.14943 | 789 | 0 | 0.14943 | 0 |  | 92000 | 0 | 92000 |  |  | 1087.1 | 0 | 90912.9 | On/Under Budget | Budget Allocated | 92000 | 337042 | -245042 | 151535 | -59535 | 151535.1 | 5000 | 385 | 4615 | 0 | 0 | 0 | 1087.1 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 5000 | 0 | 331340 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-08 | Not Started | 2021-07-23 | 2021-07-29 | Not Started | 2021-07-22 | Not Started | 2021-09-02 | Not Started | [6 empty] | 2021-07-13 | 2021-07-19 | Not Started | 2021-09-06 | Not Started | 2021-09-06 | Not Started | 2021-11-22 | Not Started | 2021-09-06 | Not Started | 2021-12-06 | Not Started | 2021-12-06 | Not Started | 2022-01-05 | 2022-01-05 | 0 | On/ Ahead Schedule | Not Started | 2022-01-05 | 2022-01-19 | Not Started | 2022-03-04 | Not Started
35249161 | FRRB – WYANDOTTE 11031974 – W3 SM3 | E.5034933.01.13 | 5796539 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1393 | 0 | 0 | 1393 | 0.26383 | 0.26383 | 0 | 0 | 0.26383 | 1393 | 0 | 0.26383 | 0 |  | 100000 | 0 | 100000 |  |  | 694.2 | 0 | 99305.8 | On/Under Budget | Budget Allocated | 795454.5455 | 800923 | -5468.4545 | 800923 | -5468.4545 | 800923 | 5000 | 226.2 | 4773.8 | 0 | 0 | 0 | 694.3 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 5000 | 0 | 295455 | 500000 | 0 | 0 | 0
35240542 | FRRB - KANAKA 1101 - K4 PH 4.19 | E.5034572.01.15 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 4796 | 0 | 4796 | 0.90833 | 0.90833 | 0 | 0 | 0.90833 | 4796 | 0 | 0.90833 | 0 |  | 3122627 | 1355466 | 1767161 | 487540 | 1279621 | 28824.3 | 0 | 1738336.7 | On/Under Budget | Budget Allocated | 1767161 | 1805092 | -37931 | 1805092 | -37931 | 1805091.6 | 342146.9 | 7480.8 | 334666.1 | 0 | 0 | 0 | 28824.3 | 0 | 0 | 0 | 0 | 0 | 0 | 21344 | 342147 | 100715 | 604506 | 384127 | 352253 | 0 | 0 | 2021-06-11 | 158995 | BL-A_ | BL-A_35240542 FRRB - KANAKA 1101 - K4 PH 4.17 - B1_ Apr 21 | 2021-04-09 | 2021-06-28 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | [6 empty] | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-12 | Not Started | 2021-08-30 | Not Started | 2021-09-13 | Not Started | 2021-08-12 | Not Started | 2021-09-13 | Not Started | 2021-09-13 | Not Started |  | 2021-10-13 |  | Behind Schedule | Not Started | 2021-10-13 | 2021-10-27 | Not Started | 2021-12-10 | Not Started
35240543 | FRRB - KANAKA 1101 - K4 PH 4.18 | E.5034572.01.16 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 6372 | 0 | 6372 | 1.2068 | 1.2068 | 0 | 0 | 1.2068 | 6372 | 0 | 1.2068 | 0 |  | 4451656 | 1662165 | 2789491 | 487540 | 2301951 | 33790.6 | 0 | 2755700.4 | On/Under Budget | Budget Allocated | 2789491 | 2359874 | 429617 | 2359874 | 429617 | 2359874.3 | 330918.4 | 7720.1 | 323198.3 | 0 | 0 | 0 | 33790.6 | 0 | 0 | 0 | 0 | 0 | 0 | 26071 | 330918 | 934 | 1000000 | 301951 | 700000 | 0 | 0 | 2021-06-11 | 158996 | BL-A_ | BL-A_35240543 FRRB - KANAKA 1101 - K4 PH 4.18 - B1_Apr 21 | 2021-04-09 | 2021-06-28 | Not Started | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | [6 empty] | 2021-06-28 | 2021-07-09 | Not Started | 2021-08-12 | Not Started | 2021-08-30 | Not Started | 2021-09-13 | Not Started | 2021-08-12 | Not Started | 2021-09-13 | Not Started | 2021-09-13 | Not Started |  | 2021-10-13 |  | Behind Schedule | Not Started | 2021-10-13 | 2021-10-27 | Not Started | 2021-12-10 | Not Started
35240546 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | E.5034825.01.90 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 691 | 0 | 0 | 691 | 0.13087 | 0.13087 | 0 | 0 | 0.13087 | 691 | 0 | 0.13087 | 0 |  | 2470520 | 1387230 | 1083290 | 768290 | 315000 | 14957.1 | 5390.9 | 1062942 | On/Under Budget | Budget Allocated | 1083290 | 319272 | 764018 | 319272 | 764018 | 319271.6 | 269.4 | -3827.3 | 4096.7 | 0 | 0 | 0 | 14957.1 | 0 | 0 | 0 | 0 | 0 | 236 | 18549 | 269 | 100087 | 100087 | 100044 | 0 | 0 | 0 | 2021-05-21 | 159025 | BL-A_ | BL-A_35240546_FRRB - WYANDOTTE 1103 - W2 PH 2.13 - B1_Apr 21 | 2021-04-09 | 2021-05-06 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-05-26 | Not Started | 2021-05-26 | Not Started | [6 empty] | 2021-05-28 | 2021-06-03 | Not Started | 2021-06-04 | Not Started | 2021-06-04 | Not Started | 2021-08-20 | Not Started | 2021-06-04 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-10-21 | 2021-10-05 | 16 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
35239523 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | E.5034825.01.72 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1300 | 0 | 0 | 1300 | 0.24621 | 0.24621 | 0 | 0 | 0.24621 | 1300 | 0 | 0.24621 | 0 |  | 3198520 | 1555230 | 1643290 | 768290 | 875000 | 31188.6 | 5390.9 | 1606710.5 | On/Under Budget | Budget Allocated | 1643290 | 897072 | 746218 | 897072 | 746218 | 897072.3 | 87.7 | -5736.7 | 5824.4 | 0 | 0 | 0 | 31188.7 | 0 | 0 | 0 | 0 | 0 | 573 | 36352 | 88 | 186927 | 273089 | 200044 | 200000 | 0 | 0 | 2021-05-21 | 159047 | BL-A_ | BL-A_35239523_FRRB - WYANDOTTE 1103 - W2 PH 2.10 - B1_Apr 21 | 2021-04-09 | 2021-05-20 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-05-21 | Not Started | 2021-05-21 | Not Started | [6 empty] | 2021-05-25 | 2021-05-31 | Not Started | 2021-06-01 | Not Started | 2021-06-01 | Not Started | 2021-08-17 | Not Started | 2021-06-01 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-09-20 | 2021-09-30 | -10 | Behind Schedule | Not Started | 2021-09-30 | 2021-10-14 | Not Started | 2021-11-29 | Not Started
35239937 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | E.5034825.01.73 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2585 | 0 | 0 | 2585 | 0.48958 | 0.48958 | 0 | 0 | 0.48958 | 2585 | 0 | 0.48958 | 0 |  | 4746246 | 1912230 | 2834016 | 768290 | 2065726 | 60761.1 | 9835 | 2763419.9 | On/Under Budget | Budget Allocated | 2834016.47 | 2097499 | 736517.47 | 2097499 | 736517.47 | 2097499 | 327.2 | 11882 | -11554.8 | 0 | 0 | 0 | 60761 | 0 | 0 | 0 | 0 | 0 | 2818 | 46061 | 327 | 500099 | 500099 | 500050 | 548045 | 0 | 0 | 2021-05-21 | 159042 | BL-A_ | BL-A_35239937_FRRB - WYANDOTTE 1103 - W2 PH 2.11 - B1_Apr 21 | 2021-04-09 | 2021-04-26 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-05-26 | Not Started | 2021-05-26 | Not Started | [6 empty] | 2021-05-28 | 2021-06-03 | Not Started | 2021-06-04 | Not Started | 2021-06-04 | Not Started | 2021-08-20 | Not Started | 2021-06-04 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-10-21 | 2021-10-05 | 16 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
35241078 | FRRB - BIG BEND 1102 - B1 PH1.2 | E.5034572.01.35 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 964 | 0 | 964 | 0.18258 | 0.18258 | 0 | 0 | 0.18258 | 964 | 0 | 0.18258 | 0 |  | 237500 | 0 | 237500 |  |  | 9482.8 | 0 | 228017.2 | On/Under Budget | Budget Allocated | 408885.89 | 364904 | 43981.89 | 364904 | 43981.89 | 364903.8 | 5000 | 431 | 4569 | 0 | 0 | 0 | 9482.8 | 0 | 0 | 0 | 0 | 0 | 2780 | 6272 | 5000 | 350852 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-05-26 | Completed | 2021-05-24 | 2021-07-15 | Not Started | 2021-07-08 | Not Started | 2021-07-29 | Not Started | [6 empty] | 2021-07-09 | 2021-07-15 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-08-05 | Not Started | 2021-08-02 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-09-06 | 2021-09-06 | 0 | On/ Ahead Schedule | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-11-03 | Not Started
35241079 | FRRB - BIG BEND 1102 - B1 PH1.3 | E.5034572.01.36 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 394 | 0 | 394 | 0.074621 | 0.074621 | 0 | 0 | 0.074621 | 394 | 0 | 0.074621 | 0 |  | 237500 | 0 | 237500 |  |  | 11896.6 | 0 | 225603.4 | On/Under Budget | Budget Allocated | 180007.89 | 134753 | 45254.89 | 134753 | 45254.89 | 134753.2 | 5000 | 1253.4 | 3746.6 | 0 | 0 | 0 | 11896.7 | 0 | 0 | 0 | 0 | 0 | 2740 | 7904 | 5000 | 119110 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-06-04 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-07-14 | Not Started | [6 empty] | 2021-06-23 | 2021-06-29 | Not Started | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-07-19 | Not Started | 2021-07-16 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-08-18 | 2021-08-18 | 0 | On/ Ahead Schedule | Not Started | 2021-08-19 | 2021-09-01 | Not Started | 2021-10-15 | Not Started
35244696 | FRRB - KANAKA 1101 - K4 PH 4.1 | E.5034572.01.17 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1567 | 0 | 1567 | 0.29678 | 0.29678 | 0 | 0 | 0.29678 | 1567 | 0 | 0.29678 | 0 |  | 2190296 | 1140313 | 1049983 | 487540 | 562443 | 14236.7 | 0 | 1035746.3 | On/Under Budget | Budget Allocated | 1049983 | 582242 | 467741 | 582242 | 467741 | 582241.9 | 130055.4 | 1306.6 | 128748.8 | 0 | 0 | 0 | 14236.7 | 0 | 0 | 0 | 0 | 0 | 0 | 12930 | 130055 | 934 | 438322 | 0 | 0 | 0 | 0 | 2021-06-08 | 160077 | BL-A: | BL-A: 35244696 FRRB - KANAKA 1101 - K4 PH 4.1 - May 21 | 2021-05-03 | 2021-05-28 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-05-27 | 2021-07-01 | In Progress | 2021-07-12 | Not Started | 2021-07-12 | Not Started | 2021-08-12 | Not Started | 2021-07-12 | Not Started | 2021-08-12 | Not Started | 2021-08-12 | Not Started | 2022-01-05 | 2021-09-13 | 114 | On/ Ahead Schedule | Not Started | 2021-09-13 | 2021-09-27 | Not Started | 2021-11-10 | Not Started
35244697 | FRRB - KANAKA 1101 - K4 PH 4.2 | E.5034572.01.18 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 655 | 0 | 655 | 0.12405 | 0.12405 | 0 | 0 | 0.12405 | [5 empty] | 1762257 | 1041535 | 720722 | 487540 | 233182 | 5967.5 | 28847.6 | 685906.9 | On/Under Budget | Budget Allocated | 720722 | 239937 | 480785 | 239937 | 480785 | 239937.2 | 32958.4 | 276.1 | 32682.3 | 0 | 0 | 0 | 5967.5 | 0 | 0 | 0 | 0 | 0 | 0 | 5691 | 32958 | 934 | 0 | 200353 | 0 | 0 | 0 | 2021-06-08 | 160078 | BL-A: | BL-A: 35244697 FRRB - KANAKA 1101 - K4 PH 4.2 - May 21 | 2021-05-03 | 2021-05-14 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-12-07 | 2021-09-01 | 97 | On/ Ahead Schedule | Not Started | 2021-09-02 | 2021-09-15 | Not Started | 2021-10-29 | Not Started
35244698 | FRRB - KANAKA 1101 - K4 PH 4.3 | E.5034572.01.19 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 477 | 0 | 477 | 0.090341 | 0.090341 | 0 | 0 | 0.090341 | 477 | 0 | 0.090341 | 0 |  | 1693957 | 1025773 | 668184 | 487540 | 180644 | 2605.7 | 19426.8 | 646151.5 | On/Under Budget | Budget Allocated | 668184 | 183992 | 484192 | 183992 | 484192 | 183992.1 | 38964.4 | 341.4 | 38623 | 0 | 0 | 0 | 2605.7 | 0 | 0 | 0 | 0 | 0 | 0 | 2264 | 38964 | 934 | 141829 | 0 | 0 | 0 | 0 | 2021-06-08 | 160079 | BL-A: | BL-A: 35244698 FRRB - KANAKA 1101 - K4 PH 4.3 - May 21 | 2021-05-03 | 2021-05-19 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-08-02 | Not Started | 2021-12-15 | 2021-09-01 | 105 | On/ Ahead Schedule | Not Started | 2021-09-02 | 2021-09-15 | Not Started | 2021-10-29 | Not Started
35244699 | FRRB - KANAKA 1101 - K4 PH 4.4 | E.5034572.01.20 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 423 | 0 | 423 | 0.080114 | 0.080114 | 0 | 0 | 0.080114 | 423 | 0 | 0.080114 | 0 |  | 1606478 | 1005586 | 600892 | 487540 | 113352 | 18128.4 | 20012.1 | 562751.5 | On/Under Budget | Budget Allocated | 600892 | 132395 | 468497 | 132395 | 468497 | 132395.3 | 53979.4 | 148.9 | 53830.5 | 0 | 0 | 0 | 18128.4 | 0 | 0 | 0 | 0 | 0 | 0 | 17980 | 53979 | 934 | 59502 | 0 | 0 | 0 | 0 | 2021-06-08 | 160080 | BL-A: | BL-A: 35244699 FRRB - KANAKA 1101 - K4 PH 4.4 - May 21 | 2021-05-03 | 2021-05-26 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-04 | Not Started | 2021-08-04 | Not Started | 2022-01-05 | 2021-09-03 | 124 | On/ Ahead Schedule | Not Started | 2021-09-06 | 2021-09-17 | Not Started | 2021-11-02 | Not Started
35245140 | FRRB - KANAKA 1101 - K4 PH 4.5 | E.5034572.01.21 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1435 | 0 | 1435 | 0.27178 | 0.27178 | 0 | 0 | 0.27178 | 1435 | 0 | 0.27178 | 0 |  | 2115915 | 1123148 | 992767 | 487540 | 505227 | 15809.4 | 0 | 976957.6 | On/Under Budget | Budget Allocated | 992767 | 521951 | 470816 | 521951 | 470816 | 521951.3 | 8934.4 | 148.9 | 8785.5 | 0 | 0 | 0 | 15809.4 | 0 | 0 | 0 | 0 | 0 | 0 | 15661 | 8934 | 497356 | 0 | 0 | 0 | 0 | 0 | 2021-06-08 | 160081 | BL-A: | BL-A: 35245140 FRRB - KANAKA 1101 - K4 PH 4.5 - May 21 | 2021-05-03 | 2021-05-28 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-16 | Not Started | 2021-08-16 | Not Started | 2022-01-05 | 2021-09-15 | 112 | On/ Ahead Schedule | Not Started | 2021-09-16 | 2021-09-29 | Not Started | 2021-11-12 | Not Started
35245141 | FRRB - KANAKA 1101 - K4 PH 4.6 | E.5034572.01.22 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 288 | 0 | 288 | 0.054545 | 0.054545 | 0 | 0 | 0.054545 | 288 | 0 | 0.054545 | 0 |  | 1561101 | 995114 | 565987 | 487540 | 78447 | 5361.1 | 23262.6 | 537363.3 | On/Under Budget | Budget Allocated | 565987 | 87524 | 478463 | 87524 | 478463 | 87523.5 | 12938.4 | 348.4 | 12590 | 0 | 0 | 0 | 5361.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5013 | 12938 | 934 | 68638 | 0 | 0 | 0 | 0 | 2021-06-08 | 160082 | BL-A: | BL-A: 35245141 FRRB - KANAKA 1101 - K4 PH 4.6 - May 21 | 2021-05-03 | 2021-05-14 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started | 2021-07-23 | Not Started | 2021-12-15 | 2021-08-24 | 113 | On/ Ahead Schedule | Not Started | 2021-08-25 | 2021-09-07 | Not Started | 2021-10-21 | Not Started
35245142 | FRRB - KANAKA 1101 - K4 PH 4.7 | E.5034572.01.23 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 300 | 0 | 300 | 0.056818 | 0.056818 | 0 | 0 | 0.056818 | 300 | 0 | 0.056818 | 0 |  | 1585427 | 1000728 | 584699 | 487540 | 97159 | 4434.8 | 18524 | 561740.2 | On/Under Budget | Budget Allocated | 584699 | 103167 | 481532 | 103167 | 481532 | 103166.7 | 20946.4 | 148.9 | 20797.5 | 0 | 0 | 0 | 4434.8 | 0 | 0 | 0 | 0 | 0 | 0 | 4286 | 20946 | 934 | 77000 | 0 | 0 | 0 | 0 | 2021-06-08 | 160083 | BL-A: | BL-A: 35245142 FRRB - KANAKA 1101 - K4 PH 4.7 - May 21 | 2021-05-03 | 2021-05-26 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-12-15 | 2021-08-10 | 127 | On/ Ahead Schedule | Not Started | 2021-08-11 | 2021-08-24 | Not Started | 2021-10-07 | Not Started
35245143 | FRRB - KANAKA 1101 - K4 PH 4.8 | E.5034572.01.24 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1367 | 0 | 1367 | 0.2589 | 0.2589 | 0 | 0 | 0.2589 | 1367 | 0 | 0.2589 | 0 |  | 2067264 | 1111921 | 955343 | 487540 | 467803 | 9405.6 | 0 | 945937.4 | On/Under Budget | Budget Allocated | 955343 | 478409 | 476934 | 478409 | 476934 | 478409.1 | 81112.4 | 648.3 | 80464.1 | 0 | 0 | 0 | 9405.6 | 0 | 0 | 0 | 0 | 0 | 0 | 8757 | 81112 | 934 | 387605 | 0 | 0 | 0 | 0 | 2021-06-08 | 160084 | BL-A: | BL-A: 35245143 FRRB - KANAKA 1101 - K4 PH 4.8 - May 21 | 2021-05-03 | 2021-06-04 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-05-27 | 2021-06-08 | In Progress | 2021-06-29 | Not Started | 2021-06-29 | Not Started | 2021-07-08 | Not Started | 2021-06-29 | Not Started | 2021-07-08 | Not Started | 2021-07-08 | Not Started | 2022-01-05 | 2021-08-09 | 149 | On/ Ahead Schedule | Not Started | 2021-08-10 | 2021-08-23 | Not Started | 2021-10-06 | Not Started
35245144 | FRRB - KANAKA 1101 - K4 PH 4.9 | E.5034572.01.25 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1314 | 0 | 1314 | 0.24886 | 0.24886 | 0 | 0 | 0.24886 | 1314 | 0 | 0.24886 | 0 |  | 2078491 | 1114512 | 963979 | 487540 | 476439 | 13112.1 | 0 | 950866.9 | On/Under Budget | Budget Allocated | 963979 | 487658 | 476321 | 487658 | 476321 | 487657.6 | 46826.4 | 3762.3 | 43064.1 | 0 | 0 | 0 | 13112.1 | 0 | 0 | 0 | 0 | 0 | 0 | 9350 | 46826 | 934 | 430547 | 0 | 0 | 0 | 0 | 2021-06-08 | 160085 | BL-A: | BL-A: 35245144 FRRB - KANAKA 1101 - K4 PH 4.9 - May 21 | 2021-05-03 | 2021-06-16 | Not Started | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-30 | Not Started | 2021-07-01 | Not Started | [6 empty] | 2021-06-18 | 2021-07-01 | Not Started | 2021-08-03 | Not Started | 2021-08-20 | Not Started | 2021-09-03 | Not Started | 2021-08-03 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2022-01-05 | 2021-10-05 | 92 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
35245145 | FRRB - KANAKA 1101 - K4 PH 4.10 | E.5034572.01.26 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 504 | 0 | 504 | 0.095455 | 0.095455 | 0 | 0 | 0.095455 | 504 | 0 | 0.095455 | 0 |  | 1697232 | 1026529 | 670703 | 487540 | 183163 | 12418.2 | 47677.5 | 610607.3 | On/Under Budget | Budget Allocated | 670703 | 197197 | 473506 | 197197 | 473506 | 197196.6 | 24950.4 | 253.4 | 24697 | 0 | 0 | 0 | 12418.2 | 0 | 0 | 0 | 0 | 0 | 0 | 12165 | 24950 | 934 | 159147 | 0 | 0 | 0 | 0 | 2021-06-08 | 160086 | BL-A: | BL-A: 35245145 FRRB - KANAKA 1101 - K4 PH 4.10 - May 21 | 2021-05-03 | 2021-05-09 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-09 | Not Started | 2021-07-12 | Not Started | 2021-07-12 | Not Started | 2021-12-15 | 2021-08-11 | 126 | On/ Ahead Schedule | Not Started | 2021-08-12 | 2021-08-25 | Not Started | 2021-10-08 | Not Started
35245146 | FRRB - KANAKA 1101 - K4 PH 4.11 | E.5034572.01.27 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 725 | 0 | 725 | 0.13731 | 0.13731 | 0 | 0 | 0.13731 | 725 | 0 | 0.13731 | 0 |  | 1799681 | 1050171 | 749510 | 487540 | 261970 | 5398 | 32303 | 711809 | On/Under Budget | Budget Allocated | 749510 | 268984 | 480526 | 268984 | 480526 | 268983.4 | 21947.4 | 253.4 | 21694 | 0 | 0 | 0 | 5398.1 | 0 | 0 | 0 | 0 | 0 | 0 | 5145 | 21947 | 934 | 240957 | 0 | 0 | 0 | 0 | 2021-06-08 | 160087 | BL-A: | BL-A: 35245146 FRRB - KANAKA 1101 - K4 PH 4.11 - May 21 | 2021-05-03 | 2021-05-14 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-18 | Not Started | 2021-08-18 | Not Started | 2022-01-05 | 2021-09-17 | 110 | On/ Ahead Schedule | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-11-16 | Not Started
35245147 | FRRB - KANAKA 1101 - K4 PH 4.12 | E.5034572.01.28 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 2072 | 0 | 2072 | 0.39242 | 0.39242 | 0 | 0 | 0.39242 | 2072 | 0 | 0.39242 | 0 |  | 2433087 | 1196342 | 1236745 | 487540 | 749205 | 17912.4 | 0 | 1218832.6 | On/Under Budget | Budget Allocated | 1236745 | 768251 | 468494 | 768251 | 468494 | 768250.8 | 177983.4 | 784.4 | 177199 | 0 | 0 | 0 | 17912.4 | 0 | 0 | 0 | 0 | 0 | 1447 | 15681 | 177983 | 934 | 249205 | 323000 | 0 | 0 | 0 | 2021-06-11 | 160091 | BL-A: | BL-A: 35245147 FRRB - KANAKA 1101 - K4 PH 4.12 - May 21 | 2021-05-03 | 2021-06-28 | Not Started | 2021-04-14 | 2021-05-20 | Not Started | 2021-07-09 | Not Started | 2021-07-12 | Not Started | [6 empty] | 2021-05-27 | 2021-06-03 | Completed | 2021-08-12 | Not Started | 2021-08-30 | Not Started | 2021-09-13 | Not Started | 2021-08-12 | Not Started | 2021-09-13 | Not Started | 2021-09-13 | Not Started | 2022-01-05 | 2021-10-13 | 84 | On/ Ahead Schedule | Not Started | 2021-10-13 | 2021-10-27 | Not Started | 2021-12-10 | Not Started
35245148 | FRRB - KANAKA 1101 - K4 PH 4.13 | E.5034572.01.29 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1082 | 0 | 1082 | 0.20492 | 0.20492 | 0 | 0 | 0.20492 | 1082 | 0 | 0.20492 | 0 |  | 1979318 | 1091626 | 887692 | 487540 | 400152 | 4775.7 | 0 | 882916.3 | On/Under Budget | Budget Allocated | 887692 | 404477 | 483215 | 404477 | 483215 | 404476.8 | 44196.4 | 2167.7 | 42028.7 | 0 | 0 | 0 | 4775.7 | 0 | 0 | 0 | 0 | 0 | 0 | 2608 | 44196 | 934 | 356738 | 0 | 0 | 0 | 0 | 2021-06-08 | 160088 | BL-A: | BL-A: 35245148 FRRB - KANAKA 1101 - K4 PH 4.13 - May 21 | 2021-05-03 | 2021-06-04 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-05-27 | 2021-07-01 | In Progress | 2021-07-20 | Not Started | 2021-08-06 | Not Started | 2021-08-20 | Not Started | 2021-07-20 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2022-01-05 | 2021-09-21 | 106 | On/ Ahead Schedule | Not Started | 2021-09-21 | 2021-10-05 | Not Started | 2021-11-18 | Not Started
35245149 | FRRB - KANAKA 1101 - K4 PH 4.14 | E.5034572.01.30 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1420 | 0 | 1420 | 0.26894 | 0.26894 | 0 | 0 | 0.26894 | 1420 | 0 | 0.26894 | 0 |  | 2127143 | 1125739 | 1001404 | 487540 | 513864 | 6197.4 | 0 | 995206.6 | On/Under Budget | Budget Allocated | 1001404 | 521677 | 479727 | 521677 | 479727 | 521676.8 | 125217.4 | 253.4 | 124964 | 0 | 0 | 0 | 6197.4 | 0 | 0 | 0 | 0 | 0 | 0 | 5944 | 125217 | 934 | 389581 | 0 | 0 | 0 | 0 | 2021-06-08 | 160093 | BL-A: | BL-A: 35245149 FRRB - KANAKA 1101 - K4 PH 4.14 - May 21 | 2021-05-03 | 2021-05-14 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | Not Started | 2021-08-19 | Not Started | 2021-08-23 | Not Started | 2021-08-23 | Not Started | 2022-01-05 | 2021-09-22 | 105 | On/ Ahead Schedule | Not Started | 2021-09-23 | 2021-10-06 | Not Started | 2021-11-19 | Not Started
35245150 | FRRB - KANAKA 1101 - K4 PH 4.15 | E.5034572.01.31 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 663 | 0 | 663 | 0.12557 | 0.12557 | 0 | 0 | 0.12557 | 663 | 0 | 0.12557 | 0 |  | 1776758 | 1044881 | 731877 | 487540 | 244337 | 6856 | 41577.1 | 683443.9 | On/Under Budget | Budget Allocated | 731877 | 252655 | 479222 | 252655 | 479222 | 252655.3 | 48753.4 | 225.5 | 48527.9 | 0 | 0 | 0 | 6856 | 0 | 0 | 0 | 0 | 0 | 0 | 6631 | 48753 | 934 | 196337 | 0 | 0 | 0 | 0 | 2021-06-08 | 160092 | BL-A: | BL-A: 35245150 FRRB - KANAKA 1101 - K4 PH 4.15 - May 21 | 2021-05-03 | 2021-05-21 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-21 | Not Started | 2021-06-22 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-20 | Not Started | 2021-07-20 | Not Started | 2021-07-22 | Not Started | 2021-07-20 | Not Started | 2021-07-22 | Not Started | 2021-07-22 | Not Started | 2021-12-15 | 2021-08-23 | 114 | On/ Ahead Schedule | Not Started | 2021-08-24 | 2021-09-06 | Not Started | 2021-10-20 | Not Started
35245151 | FRRB - KANAKA 1101 - K4 PH 4.16 | E.5034572.01.32 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 816 | 0 | 816 | 0.15455 | 0.15455 | 0 | 0 | 0.15455 | 816 | 0 | 0.15455 | 0 |  | 1779097 | 1045421 | 733676 | 487540 | 246136 | 8019.4 | 26774.3 | 698882.3 | On/Under Budget | Budget Allocated | 733676 | 255710 | 477966 | 255710 | 477966 | 255710.3 | 24950.4 | 329.9 | 24620.5 | 0 | 0 | 0 | 8019.4 | 0 | 0 | 0 | 0 | 0 | 0 | 7690 | 24950 | 934 | 222136 | 0 | 0 | 0 | 0 | 2021-06-08 | 160090 | BL-A: | BL-A: 35245151 FRRB - KANAKA 1101 - K4 PH 4.16 - May 21 | 2021-05-03 | 2021-05-14 | Completed | 2021-04-14 | 2021-05-20 | Not Started | 2021-06-08 | Not Started | 2021-06-15 | Not Started | [6 empty] | 2021-06-08 | 2021-06-21 | Not Started | 2021-07-13 | Not Started | 2021-07-13 | Not Started | 2021-07-13 | Not Started | 2021-07-13 | Not Started | 2021-07-14 | Not Started | 2021-07-14 | Not Started | 2021-12-15 | 2021-08-13 | 124 | On/ Ahead Schedule | Not Started | 2021-08-16 | 2021-08-27 | Not Started | 2021-10-12 | Not Started
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | E.5034825.01.23 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1300 | 0 | 0 | 1300 | 0.24621 | 0.24621 | 0 | 0 | 0.24621 | 1300 | 0 | 0.24621 | 0 |  | 6611020 | 2342730 | 4268290 |  |  | 38433.3 | 0 | 4229856.7 | On/Under Budget | Budget Allocated | 4268290 | 3533348 | 734942 | 3533348 | 734942 | 3533347.4 | 1003434.4 | 9454.7 | 993979.7 | 0 | 0 | 0 | 38433.4 | 0 | 0 | 0 | 0 | 3271 | 23912 | 1797 | 1003434 | 1000934 | 1000000 | 500000 | 0 | 0 | 0 | 2021-05-31 | 159017 | BL-A_ | BL-A_35235320_FRRB - Wyandotte 1103 - W3 Ph 3.1 - B1_Apr 21 | 2021-04-09 | 2021-05-21 | Completed | 2021-03-29 | 2021-04-07 | Completed | 2021-07-09 | Not Started | 2021-07-23 | Not Started | [6 empty] | 2021-07-12 | 2021-07-16 | Not Started | 2021-07-27 | Not Started | 2021-07-27 | Not Started | 2021-10-12 | Not Started | 2021-07-27 | Not Started | 2021-10-26 | Not Started | 2021-10-26 | Not Started | 2021-11-09 | 2021-11-25 | -16 | Behind Schedule | Not Started | 2021-11-25 | 2021-12-09 | Not Started | 2022-01-24 | Not Started
35235669 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | E.5034825.01.24 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2216 | 0 | 0 | 2216 | 0.4197 | 0.4197 | 0 | 0 | 0.4197 | 2216 | 0 | 0.4197 | 0 |  | 3927014 | 1722556 | 2204458 | 768290 | 1436168 | 55274.5 | 0 | 2149183.5 | On/Under Budget | Budget Allocated | 2204458 | 1502275 | 702183 | 1502275 | 702183 | 1502274.7 | 116.6 | -33238.6 | 33355.2 | 0 | 0 | 0 | 55274.5 | 0 | 0 | 0 | 0 | 2296 | 5798 | 80420 | 117 | 118 | 500118 | 500118 | 413233 | 59 | 0 | 2021-05-21 | 159018 | BL-A_ | BL-A_35235669_FRRB - WYANDOTTE 1103 - W4 PH 4.1 - B1_Apr 21 | 2021-04-09 | 2021-05-17 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-05 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-10-25 | Not Started | 2021-08-09 | Not Started | 2021-11-08 | Not Started | 2021-11-08 | Not Started | 2021-11-25 | 2021-12-08 | -13 | Behind Schedule | Not Started | 2021-12-08 | 2021-12-22 | Not Started | 2022-02-04 | Not Started
35235677 | FRRB - BIG BEND 1102 - B4 PH4.1 | E.5034825.01.32 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 30432 | 0 | 0 | 30432 | 5.7636 | 5.7636 | 0 | 0 | 5.7636 | 30432 | 0 | 5.7636 | 0 |  | 14162767.73 | 13612767.73 | 550000 |  |  | 452025.2 | 0 | 97974.8 | On/Under Budget | Budget Allocated | 18298258 | 17526601 | 771657 | 15891854 | 2406404 | 15891854 | 576934.4 | 391274.8 | 185659.6 | 0 | 0 | 0 | 452025.3 | 0 | 0 | 0 | 0 | 236 | 1 | 60514 | 601553 | 833463 | 1306570 | 4491766 | 6298368 | 3882391 | 51739 | 2021-06-18 |  |  |  |  | 2021-06-17 | Completed | 2021-05-21 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-07-13 | Not Started | [6 empty] | 2021-06-04 | 2021-06-04 | Completed | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-11-19 | Not Started | 2021-09-01 | Not Started | 2021-11-30 | Not Started | 2021-11-30 | Not Started | 2021-12-30 | 2021-12-30 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2022-02-28 | Not Started
35235674 | FRRB - BIG BEND 1102 - B1 PH1.1 | E.5034572.01.34 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 585 | 0 | 585 | 0.1108 | 0.1108 | 0 | 0 | 0.1108 | 585 | 0 | 0.1108 | 0 |  | 237500 | 0 | 237500 |  |  | 11368.7 | 0 | 226131.3 | On/Under Budget | Budget Allocated | 263588.3 | 222667 | 40921.3 | 222667 | 40921.3 | 222667.2 | 5000 | 2053.5 | 2946.5 | 0 | 0 | 0 | 11368.8 | 0 | 0 | 0 | 0 | 236 | 1514 | 7566 | 5000 | 208352 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-06-03 | Completed | 2021-07-02 | 2021-07-05 | Not Started | 2021-07-01 | Not Started | 2021-07-13 | Not Started | [6 empty] | 2021-07-01 | 2021-07-07 | Not Started | 2021-07-15 | Not Started | 2021-07-15 | Not Started | 2021-07-16 | Not Started | 2021-07-15 | Not Started | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-08-17 | 2021-08-17 | 0 | On/ Ahead Schedule | Not Started | 2021-08-18 | 2021-08-31 | Not Started | 2021-10-14 | Not Started
35235671 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | E.5034825.01.26 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3504 | 0 | 0 | 3504 | 0.66364 | 0.66364 | 0 | 0 | 0.66364 | 3504 | 0 | 0.66364 | 0 |  | 4290520 | 1807230 | 2483290 | 768290 | 1715000 | 51502.8 | 0 | 2431787.2 | On/Under Budget | Budget Allocated | 2483290 | 1710728 | 772562 | 1710728 | 772562 | 1710727.7 | 92.9 | 39877.5 | -39784.6 | 0 | 0 | 0 | 51502.8 | 0 | 0 | 0 | 0 | 0 | 1614 | 10012 | 93 | 93 | 500093 | 500093 | 698685 | 46 | 0 | 2021-05-21 | 159019 | BL-A_ | BL-A_35235671_FRRB - WYANDOTTE 1103 - W4 PH 4.2 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-25 | 2021-12-21 | -26 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35235704 | FRRB - KANAKA 1101 - K5 PH5.1 | E.5034572.01.40 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 998 | 0 | 998 | 0.18902 | 0.18902 | 0 | 0 | 0.18902 | 998 | 0 | 0.18902 | 0 |  | 187374.83 | -50125.17 | 237500 |  |  | 11583.1 | 0 | 225916.9 | On/Under Budget | Budget Allocated | 359129 | 375962 | -16833 | 679712 | -320583 | 679712.2 | 7000 | 1749.9 | 5250.1 | 0 | 0 | 0 | 11583.1 | 0 | 0 | 0 | 0 | 471 | 3 | 9359 | 7000 | 0 | 179564 | 179565 | 0 | 0 | 0 | 2021-03-01 |  |  |  |  | 2021-04-29 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-24 | Not Started | [6 empty] | 2021-04-28 | 2021-05-04 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | 2021-09-13 | Not Started | 2021-06-28 | Not Started | 2021-09-27 | Not Started | 2021-09-27 | Not Started | 2021-10-27 | 2021-10-27 | 0 | On/ Ahead Schedule | Not Started | 2021-10-27 | 2021-11-10 | Not Started | 2021-12-24 | Not Started
35235700 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | E.5034825.01.35 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 7436 | 0 | 0 | 7436 | 1.4083 | 1.4083 | 0 | 0 | 1.4083 | 7436 | 0 | 1.4083 | 0 |  | 7794107 | 2615730 | 5178377 | 768290 | 4410087 | 90735.8 | 0 | 5087641.2 | On/Under Budget | Budget Allocated | 5178377 | 4401377 | 777000 | 4401377 | 777000 | 4401376.7 | 98.9 | 81740.5 | -81641.6 | 0 | 0 | 0 | 90735.8 | 0 | 0 | 0 | 0 | 0 | 3414 | 5582 | 99 | 100 | 1500100 | 1500100 | 1000100 | 391883 | 0 | 2021-05-21 |  |  |  |  | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-12-21 | 2021-12-21 | 0 | On/ Ahead Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | E.5034825.01.60 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5759 | 0 | 0 | 5759 | 1.0907 | 1.0907 | 0 | 0 | 1.0907 | 6454 | 0 | 1.2223 | 0 |  | 5746520 | 2143230 | 3603290 |  |  | 85034.3 | 0 | 3518255.7 | On/Under Budget | Budget Allocated | 3603290 | 2883053 | 720237 | 2883053 | 720237 | 2883052.9 | 3434.4 | 41350.2 | -37915.8 | 0 | 0 | 0 | 85034.3 | 0 | 0 | 0 | 0 | 1275 | 22721 | 19688 | 3434 | 1000934 | 1000000 | 835000 | 0 | 0 | 0 | 2021-05-21 | 159029 | BL-A_ | BL-A_35237890_FRRB - Wyandotte 1103 - W3 Ph 3.3 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35237891 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | E.5034825.01.61 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2200 | 0 | 0 | 2200 | 0.41667 | 0.41667 | 0 | 0 | 0.41667 | 2492 | 0 | 0.47197 | 0 |  | 4154020 | 1775730 | 2378290 |  |  | 29391 | 0 | 2348899 | On/Under Budget | Budget Allocated | 2378290 | 1618422 | 759868 | 1618422 | 759868 | 1618421.6 | 3434.4 | 25338.2 | -21903.8 | 0 | 0 | 0 | 29391 | 0 | 0 | 0 | 0 | 0 | 15437 | -11384 | 3434 | 500934 | 500000 | 610000 | 0 | 0 | 0 | 2021-05-21 | 159034 | BL-A_ | BL-A_35237891_FRRB - Wyandotte 1103 - W3 Ph 3.4 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-03-29 | 2021-04-07 | Completed | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-09 | 2021-12-21 | -42 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35237893 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | E.5034825.01.62 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4360 | 0 | 0 | 4360 | 0.82576 | 0.82576 | 0 | 0 | 0.82576 | 4206 | 0 | 0.79659 | 0 |  | 3380520 | 1597230 | 1783290 |  |  | 53415.3 | 0 | 1729874.7 | On/Under Budget | Budget Allocated | 1783290 | 1120288 | 663002 | 1120288 | 663002 | 1120287.9 | 3434.4 | -47503.8 | 50938.2 | 0 | 0 | 0 | 53415.2 | 0 | 0 | 0 | 0 | 0 | 17939 | 82980 | 3434 | 500934 | 500000 | 15000 | 0 | 0 | 0 | 2021-05-21 | 159046 | BL-A_ | BL-A_35237893_FRRB - Wyandotte 1103 - W3 Ph 3.5 - B1_Apr 21 | 2021-04-09 | 2021-05-17 | Completed | 2021-03-29 | 2021-04-07 | Completed | 2021-07-01 | Not Started | 2021-08-05 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-10-25 | Not Started | 2021-08-09 | Not Started | 2021-11-08 | Not Started | 2021-11-08 | Not Started | 2021-11-09 | 2021-12-08 | -29 | Behind Schedule | Not Started | 2021-12-08 | 2021-12-22 | Not Started | 2022-02-04 | Not Started
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | E.5034825.01.41 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3903 | 0 | 0 | 3903 | 0.7392 | 0.7392 | 0 | 0 | 0.7392 | 3903 | 0 | 0.7392 | 0 |  | 7339020 | 2510730 | 4828290 | 768290 | 4060000 | 61792.7 | 12839.8 | 4753657.5 | On/Under Budget | Budget Allocated | 4828290 | 4090292 | 737998 | 4090292 | 737998 | 4090292.4 | 96.2 | 14540.2 | -14444 | 0 | 0 | 0 | 61792.7 | 0 | 0 | 0 | 0 | 229 | 2445 | 44579 | 96 | 1000097 | 1000097 | 1000049 | 1042701 | 0 | 0 | 2021-05-21 | 159006 | BL-A_ | BL-A_35235706_FRRB - WYANDOTTE 1103 - W2 PH 2.7 - B1_Apr 21 | 2021-04-09 | 2021-04-26 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | E.5034825.01.42 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5430 | 0 | 0 | 5430 | 1.0284 | 1.0284 | 0 | 0 | 1.0284 | 5430 | 0 | 1.0284 | 0 |  | 6383520 | 2290230 | 4093290 | 768290 | 3325000 | 82367.2 | 38519.3 | 3972403.5 | On/Under Budget | Budget Allocated | 4093290 | 3445301 | 647989 | 3445301 | 647989 | 3445300.7 | 105.8 | -58232.8 | 58338.6 | 0 | 0 | 0 | 82367.1 | 0 | 0 | 0 | 0 | 828 | 5176 | 134596 | 106 | 100107 | 204328 | 1000107 | 1000053 | 1000000 | 0 | 2021-05-21 | 159007 | BL-A_ | BL-A_35235707_FRRB - WYANDOTTE 1103 - W2 PH 2.8 - B1_Apr 21 | 2021-04-09 | 2021-05-04 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35236989 | FRRB - KANAKA 1101 - K2 PH2.2 | E.5034572.01.39 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 2710 | 0 | 2710 | 0.51326 | 0.51326 | 0 | 0 | 0.51326 | 2700 | 0 | 0.51136 | 0 |  | 400000 | 0 | 400000 |  |  | 1768.6 | 0 | 398231.4 | On/Under Budget | Budget Allocated | 975189 | 403437 | 571752 | 981563 | -6374 | 981563 | 5000 | 395.6 | 4604.4 | 0 | 0 | 0 | 1768.6 | 0 | 0 | 0 | 0 | 394 | 200 | 779 | 6184 | 2989 | 286498 | 101642 | 3551 | 1199 | 0 | 2021-06-11 |  |  |  |  | 2021-06-18 | Not Started | 2021-07-23 | 2021-07-29 | Not Started | 2021-07-22 | Not Started | 2021-08-13 | Not Started | [6 empty] | 2021-07-23 | 2021-07-29 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-11-02 | Not Started | 2021-08-17 | Not Started | 2021-11-16 | Not Started | 2021-11-16 | Not Started | 2021-12-16 | 2021-12-16 | 0 | On/ Ahead Schedule | Not Started | 2021-12-16 | 2021-12-30 | Not Started | 2022-02-14 | Not Started
35236991 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | E.5034825.01.52 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 6661 | 0 | 0 | 6661 | 1.2616 | 1.2616 | 0 | 0 | 1.2616 | 6661 | 0 | 1.2616 | 0 |  | 7834694 | 2625116 | 5209578 | 768290 | 4441288 | 6501.1 | 0 | 5203076.9 | On/Under Budget | Budget Allocated | 5209578 | 4430318 | 779260 | 4430318 | 779260 | 4430317.8 | 96.4 | 448.8 | -352.4 | 0 | 0 | 0 | 6501.1 | 0 | 0 | 0 | 0 | 0 | 2736 | 3316 | 96 | 97 | 2000097 | 1500097 | 500097 | 423780 | 0 | 2021-05-21 | 159021 | BL-A_ | BL-A_35236991_FRRB - WYANDOTTE 1103 - W4 PH 4.8 - B1_Apr 21 | 2021-04-09 | 2021-06-09 | Not Started | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-04 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-06 | Not Started | 2021-08-06 | Not Started | 2021-10-22 | Not Started | 2021-08-06 | Not Started | 2021-11-05 | Not Started | 2021-11-05 | Not Started | 2021-11-25 | 2021-12-07 | -12 | Behind Schedule | Not Started | 2021-12-07 | 2021-12-21 | Not Started | 2022-02-03 | Not Started
35236993 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | E.5034825.01.54 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2535 | 0 | 0 | 2535 | 0.48011 | 0.48011 | 0 | 0 | 0.48011 | 2535 | 0 | 0.48011 | 0 |  | 3881421 | 1712731 | 2168690 | 768290 | 1400400 | 27952.4 | 0 | 2140737.6 | On/Under Budget | Budget Allocated | 2168690 | 1391220 | 777470 | 1391220 | 777470 | 1391220 | 86.4 | 22457.9 | -22371.5 | 0 | 0 | 0 | 27952.4 | 0 | 0 | 0 | 0 | 394 | 2 | 5098 | 86 | 87 | 500087 | 500087 | 385334 | 44 | 0 | 2021-05-21 | 159022 | BL-A_ | BL-A_35236993_FRRB - WYANDOTTE 1103 - W4 PH 4.9 - B1_Apr 21 | 2021-04-09 | 2021-06-30 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-11-25 | 2021-12-28 | -33 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35236995 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | E.5034825.01.55 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 12063 | 0 | 0 | 12063 | 2.2847 | 2.2847 | 0 | 0 | 2.2847 | 12063 | 0 | 2.2847 | 0 |  | 11024453 | 3361072 | 7663381 | 768290 | 6895091 | 120834 | 0 | 7542547 | On/Under Budget | Budget Allocated | 7663381 | 6885708 | 777673 | 6885708 | 777673 | 6885708.5 | 101.7 | 110691.4 | -110589.7 | 0 | 0 | 0 | 120834 | 0 | 0 | 0 | 0 | 531 | 4702 | 4910 | 102 | 103 | 2000103 | 2000103 | 1500103 | 1375053 | 0 | 2021-05-21 | 159028 | BL-A_ | BL-A_35236995_FRRB - WYANDOTTE 1103 - W4 PH 4.10 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-25 | 2021-12-21 | -26 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35236999 | FRRB - KANAKA 1101 - K5 PH5.2 | E.5034572.01.41 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 924 | 0 | 924 | 0.175 | 0.175 | 0 | 0 | 0.175 | 924 | 0 | 0.175 | 0 |  | 101106 | -136394 | 237500 |  |  | 1720.3 | 0 | 235779.7 | On/Under Budget | Budget Allocated | 332500 | 338576 | -6076 | 882402 | -549902 | 882402.2 | 5000 | 644.1 | 4355.9 | 0 | 0 | 0 | 1720.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1076 | 5000 | 0 | 166250 | 166250 | 0 | 0 | 0 | 2021-03-01 |  |  |  |  | 2021-04-29 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-24 | Not Started | [6 empty] | 2021-04-28 | 2021-05-04 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | 2021-09-13 | Not Started | 2021-06-28 | Not Started | 2021-09-27 | Not Started | 2021-09-27 | Not Started | 2021-10-27 | 2021-10-27 | 0 | On/ Ahead Schedule | Not Started | 2021-10-27 | 2021-11-10 | Not Started | 2021-12-24 | Not Started
35237020 | FRRB - KANAKA 1101 - K5 PH5.3 | E.5034572.01.42 | 5793918 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 2640 | 0 | 2640 | 0.5 | 0.5 | 0 | 0 | 0.5 | [5 empty] | 207149.33 | -30350.67 | 237500 |  |  | 126.5 | 0 | 237373.5 | On/Under Budget | Budget Allocated | 950000 | 955251 | -5251 | 5127 | 944873 | 5126.5 | 5000 | 0 | 5000 | 0 | 0 | 0 | 126.5 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 5016 | 31 | 475031 | 475031 | 16 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-02 | Not Started | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-07-28 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-10-15 | Not Started | 2021-07-30 | Not Started | 2021-10-29 | Not Started | 2021-10-29 | Not Started | 2021-11-30 | 2021-11-30 | 0 | On/ Ahead Schedule | Not Started | 2021-11-30 | 2021-12-14 | Not Started | 2022-01-27 | Not Started
35239099 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | E.5034825.01.70 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2357 | 0 | 0 | 2357 | 0.4464 | 0.4464 | 0 | 0 | 0.4464 | 2357 | 0 | 0.4464 | 0 |  | 5064020 | 1985730 | 3078290 | 768290 | 2310000 | 31506.9 | 0 | 3046783.1 | On/Under Budget | Budget Allocated | 3078290 | 2336848 | 741442 | 2336848 | 741442 | 2336847.7 | 85.4 | -9617.6 | 9703 | 0 | 0 | 0 | 31506.9 | 0 | 0 | 0 | 0 | 0 | 0 | 41125 | 85 | 86 | 1000086 | 500086 | 500086 | 295293 | 0 | 2021-05-21 | 159035 | BL-A_ | BL-A_35239099_FRRB - WYANDOTTE 1103 - W4 PH 4.7 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-25 | 2021-12-21 | -26 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35239095 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | E.5034825.01.66 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 8701 | 0 | 0 | 8701 | 1.6479 | 1.6479 | 0 | 0 | 1.6479 | 8701 | 0 | 1.6479 | 0 |  | 7202520 | 2479230 | 4723290 | 768290 | 3955000 | 129317.9 | 0 | 4593972.1 | On/Under Budget | Budget Allocated | 4723290 | 4011977 | 711313 | 4011977 | 711313 | 4011976.8 | 97 | 55430.1 | -55333.1 | 0 | 0 | 0 | 129317.9 | 0 | 0 | 0 | 0 | 0 | 2622 | 71266 | 97 | 97 | 1000097 | 1000097 | 1000097 | 937605 | 0 | 2021-05-21 | 159040 | BL-A_ | BL-A_35239095_FRRB - WYANDOTTE 1103 - W4 PH 4.3 - B1_Apr 21 | 2021-04-09 | 2021-05-18 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-05 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-10-25 | Not Started | 2021-08-09 | Not Started | 2021-11-08 | Not Started | 2021-11-08 | Not Started | 2021-11-25 | 2021-12-08 | -13 | Behind Schedule | Not Started | 2021-12-08 | 2021-12-22 | Not Started | 2022-02-04 | Not Started
35239096 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | E.5034825.01.67 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5060 | 0 | 0 | 5060 | 0.95833 | 0.95833 | 0 | 0 | 0.95833 | 5060 | 0 | 0.95833 | 0 |  | 6065020 | 2216730 | 3848290 | 768290 | 3080000 | 72048.8 | 0 | 3776241.2 | On/Under Budget | Budget Allocated | 3848290 | 3108829 | 739461 | 3108829 | 739461 | 3108828.5 | 91 | 27546.7 | -27455.7 | 0 | 0 | 0 | 72048.7 | 0 | 0 | 0 | 0 | 0 | 1390 | 43112 | 91 | 92 | 1000092 | 1080092 | 900092 | 83868 | 0 | 2021-05-21 | 159066 | BL-A_ | BL-A_35239096_FRRB - WYANDOTTE 1103 - W4 PH 4.4 - B1_Apr 21 | 2021-04-09 | 2021-05-17 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-05 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-10-25 | Not Started | 2021-08-09 | Not Started | 2021-11-08 | Not Started | 2021-11-08 | Not Started | 2021-11-25 | 2021-12-08 | -13 | Behind Schedule | Not Started | 2021-12-08 | 2021-12-22 | Not Started | 2022-02-04 | Not Started
35239097 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | E.5034825.01.68 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 6107 | 0 | 0 | 6107 | 1.1566 | 1.1566 | 0 | 0 | 1.1566 | 6107 | 0 | 1.1566 | 0 |  | 6656520 | 2353230 | 4303290 | 768290 | 3535000 | 78147.1 | 0 | 4225142.9 | On/Under Budget | Budget Allocated | 4303290 | 3539876 | 763414 | 3539876 | 763414 | 3539876.1 | 93.1 | 63318 | -63224.9 | 0 | 0 | 0 | 78147 | 0 | 0 | 0 | 0 | 0 | 1909 | 12920 | 93 | 94 | 1535094 | 1000094 | 989625 | 47 | 0 | 2021-05-21 | 159031 | BL-A_ | BL-A_35239097_FRRB - WYANDOTTE 1103 - W4 PH 4.5 - B1_Apr 21 | 2021-04-09 | 2021-06-23 | Not Started | 2021-07-08 | 2021-07-14 | Not Started | 2021-07-07 | Not Started | 2021-08-18 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-11-05 | Not Started | 2021-08-20 | Not Started | 2021-11-19 | Not Started | 2021-11-19 | Not Started | 2021-11-25 | 2021-12-21 | -26 | Behind Schedule | Not Started | 2021-12-21 | 2022-01-04 | Not Started | 2022-02-17 | Not Started
35238098 | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 | E.5034767.01.05 | 5794998 | PEND | 08W | [6 empty] | 2022 |  | SH | NAPA | North Bay Assets | 0 | 2531 | 0 | 2531 | 0.47936 | 0 | 0.47936 | 0 | 0.47936 | 2531 | 0 | 0.47936 | 0 |  | 211465.05 | 21465.05 | 190000 | 0 | 190000 | 42824.2 | 0 | 147175.8 | On/Under Budget | Budget Allocated | 189000 | 185882 | 3118 | 185882 | 3118 | 185881.7 | 3208.1 | 705.6 | 2502.5 | 0 | 0 | 0 | 42824.2 | 0 | 0 | 0 | 0 | 0 | 20847 | 21272 | 3208 | 926 | 926 | 926 | 135926 | 926 | 926 | 2021-06-18 |  |  |  |  | 2021-05-24 | Completed | 2022-05-03 | 2022-05-09 | Not Started | 2022-05-02 | Not Started | 2022-05-30 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2022-05-03 | 2022-05-16 | Not Started | 2022-07-01 | Not Started | 2022-07-01 | Not Started | 2022-07-14 | Not Started | 2022-07-01 | Not Started | 2022-08-01 | Not Started | 2022-08-30 | Not Started | 2022-10-31 | 2022-10-31 | 0 | On/ Ahead Schedule | Not Started | 2022-11-01 | 2022-11-14 | Not Started | 2022-12-28 | Not Started
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 | E.5034703.01.04 | 5794541 | PEND | 08W | [6 empty] | 2022 |  | SH | MARIPOSA | Yosemite Assets | 0 | 288 | 0 | 288 | 0.054545 | 0 | 0.054545 | 0 | 0.054545 | 551 | 0 | 0.10436 | 0 |  | 138166.52 | 138166.52 | 0 |  |  | 7620.8 | 0 | -7620.8 | OverRun | Request 2021 Budget | 0 | 5254 | -5254 | 5254 | -5254 | 5254.1 | 0 | 2366.7 | -2366.7 | 0 | 0 | 0 | 7620.7 | 0 | 0 | 0 | 0 | 1631 | 9 | 3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 161882 | BL-A | BL-A 35238567_CWSP - MARIPOSA 210197142 PH 1.4_08W - DD 210618 | 2021-06-22 | 2021-06-12 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-09-07 | Not Started | 2021-09-07 | Not Started | 2021-09-20 | Not Started | 2021-09-07 | Not Started | 2021-09-27 | Not Started | 2021-10-26 | Not Started | 2021-12-27 | 2021-12-27 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-10 | Not Started | 2022-02-23 | Not Started
35227659 | CWSP - VACAVILLE 11046542 - PH 2.6 | E.5034707.01.11 | 5794545 | PEND | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 1620 | 0 | 1620 | 0.30682 | 0.30682 | 0 | 0 | 0.30682 | 1620 | 0 | 0.30682 | 0 |  | 216928.1 | 174735.1 | 42193 |  |  | 15250.5 | 0 | 26942.5 | On/Under Budget | Request 2021 Budget | 0 | 467090 | -467090 | 329636 | -329636 | 329635.7 | 8160.6 | 2596.4 | 5564.2 | 0 | 0 | 0 | 15250.5 | 0 | 0 | 0 | 0 | 0 | 1125 | 11530 | 15815 | 120442 | 206698 | 79304 | 29772 | 2405 | 0 | 2021-06-18 | 161880 | BL-A | BL-A 35227659_CWSP - VACAVILLE 1104 LR 6542 PH 2.6_08W - DD 210618 | 2021-06-22 | 2021-05-28 | Completed | 2021-06-21 | 2021-07-02 | Not Started | 2021-07-19 | Not Started | 2021-07-23 | Not Started | 2021-07-19 | 2021-07-23 | Not Started | 2021-07-26 | 2021-08-13 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-09-13 | Not Started | 2021-09-14 | Not Started | 2021-11-19 | 2021-11-19 | 0 | On/ Ahead Schedule | Not Started | 2021-11-22 | 2021-12-03 | Not Started | 2022-01-18 | Not Started
35227657 | CWSP - VACAVILLE 11046542 - PH 2.4 | E.5034707.01.09 | 5794545 | PEND | 08W | [6 empty] | 2021 |  | SH | VACAVLLE | Sacramento Assets | 0 | 2333 | 0 | 2333 | 0.44186 | 0.44186 | 0 | 0 | 0.44186 | 2333 | 0 | 0.44186 | 0 |  | 257767.11 | 151736.11 | 106031 |  |  | 10986.9 | 0 | 95044.1 | On/Under Budget | Request 2021 Budget | 0 | 629244 | -629244 | 1295182 | -1295182 | 1295182 | 44332.1 | 1222 | 43110.1 | 0 | 0 | 0 | 10986.9 | 0 | 0 | 0 | 0 | 0 | 780 | 8985 | 14035 | 131790 | 250529 | 177859 | 34733 | 7534 | 3000 | 2021-06-18 | 161878 | BL-A | BL-A 35227657_CWSP - VACAVILLE 1104 LR 6542 PH 2.4_08W - DD 210618 | 2021-06-22 | 2021-05-27 | Completed | 2021-06-21 | 2021-07-02 | Not Started | 2021-07-19 | Not Started | 2021-07-23 | Not Started | 2021-07-09 | 2021-07-09 | Not Started | 2021-07-12 | 2021-07-30 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-03 | Not Started | 2021-08-30 | Not Started | 2021-08-31 | Not Started | 2021-11-05 | 2021-11-05 | 0 | On/ Ahead Schedule | Not Started | 2021-11-08 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | E.5034610.01.08 | 5794205 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 8026 | 0 | 8026 | 1.5201 | 1.5201 | 0 | 0 | 1.5201 | 7992 | 0 | 1.5136 | 0 |  | 404711.27 | 324711.27 | 80000 |  |  | 41304.4 | 0 | 38695.6 | On/Under Budget | Request 2021 Budget | 0 | 62805 | -62805 | 62805 | -62805 | 63370.9 | 20301.9 | 983.1 | 19318.8 | 0 | 0 | 0 | 41304.4 | 565.3 | 0 | 0 | 0 | 725 | 24385 | 15212 | 20302 | 364 | 364 | 364 | 364 | 364 | 364 | 2021-06-18 | 157818 | BL-A | BL-A 35227861_CWSP - Middletown 1103 - LR 830 PH1.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-30 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-03-02 | -6 | Behind Schedule | Not Started | 2022-03-03 | 2022-03-16 | Not Started | 2022-04-29 | Not Started
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | E.5034610.01.09 | 5794205 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5755 | 0 | 5755 | 1.09 | 1.09 | 0 | 0 | 1.09 | [5 empty] | 400710.04 | 320710.04 | 80000 |  |  | 30252.1 | 0 | 49747.9 | On/Under Budget | Request 2021 Budget | 0 | 51370 | -51370 | 51370 | -51370 | 51837.9 | 20236.1 | 903.1 | 19333 | 0 | 0 | 0 | 30252.1 | 467.7 | 0 | 0 | 0 | 799 | 20682 | 7867 | 20236 | 298 | 298 | 298 | 298 | 298 | 298 | 2021-06-18 | 157819 | BL-A | BL-A 35227862_CWSP - Middletown 1103 - LR 830 PH1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-06-08 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-07-27 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-23 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-02-24 | 2022-03-08 | -12 | Behind Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | E.5034806.01.01 | 5795301 | PEND | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 0 | 4600 | 0 | 4600 | 0.87121 | 0.87121 | 0 | 0 | 0.87121 | [5 empty] | 201909.68 | -35923.32 | 237833 | 0 | 237833 | 49157.4 | 0 | 188675.6 | On/Under Budget | Budget Allocated | 237833 | 231801 | 6032 | 231801 | 6032 | 232021.6 | 19759.3 | 1610.1 | 18149.2 | 0 | 0 | 0 | 49157.5 | 221 | 0 | 0 | 343 | 995 | 13098 | 33111 | 19759 | 1565 | 1572 | 156579 | 1586 | 1593 | 1600 | 2021-06-18 | 159375 | BL-A: | BL-A: 35227032_ECOP - PUEBLO 2102 - H01-LR792 PH 2_08W - B1_Apr 21 | 2021-04-21 | 2021-06-08 | Completed | 2021-08-17 | 2021-08-23 | Not Started | 2021-08-16 | Not Started | 2021-08-30 | Not Started | 2021-06-18 | 2021-09-06 | In Progress | 2021-09-07 | 2021-09-15 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-03-21 | 2022-03-21 | 0 | On/ Ahead Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-18 | Not Started
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | E.5034805.01.06 | 5795300 | PEND | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2786 | 0 | 2786 | 0.52765 | 0.52765 | 0 | 0 | 0.52765 | 0 | 3348 | 0 | 0.63409 |  | 338825.78 | 270968.78 | 67857 |  |  | 50499.2 | 0 | 17357.8 | On/Under Budget | Budget Allocated | 67857 | 51192 | 16665 | 51192 | 16665 | 54768.2 | 1322.7 | 2482.5 | -1159.8 | 0 | 0 | 0 | 50499.2 | 3426.2 | 150.5 | 0 | 0 | 2401 | 20953 | 24663 | 1323 | 309 | 309 | 309 | 309 | 309 | 309 | 2021-06-25 | 159769 | BL-A: | BL-A: 35226863_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2_08W - Apr 21 | 2021-04-28 | 2021-06-16 | Completed | 2021-08-02 | 2021-08-06 | Not Started | 2021-07-30 | Not Started | 2021-08-27 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-10-01 | Not Started |  |  |  |  | 2021-10-01 | Not Started | 2021-10-21 | Not Started | 2021-10-25 | Not Started | 2022-01-14 | 2021-12-24 | 21 | On/ Ahead Schedule | Not Started | 2021-12-27 | 2022-01-07 | Not Started | 2022-02-22 | Not Started
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | E.5034805.01.28 | 5795300 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5491 | 0 | 5491 | 1.04 | 1.04 | 0 | 0 | 1.04 | 6301 | 0 | 1.1934 | 0 |  | 447830.94 | 352830.94 | 95000 |  |  | 13638.9 | 0 | 81361.1 | On/Under Budget | Request 2021 Budget | 0 | 79095 | -79095 | 79095 | -79095 | 79188.5 | 20395.7 | -42311.3 | 62707 | 0 | 0 | 0 | 13639 | 94.1 | 0 | 0 | 0 | 774 | 29670 | 25507 | 20396 | 458 | 458 | 458 | 458 | 458 | 458 | 2021-06-18 | 157834 | BL-A | BL-A 35227029_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-05-27 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-07-30 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | 2021-08-13 | Not Started | 2021-08-16 | 2021-09-03 | Not Started | 2021-08-02 | 2021-08-13 | Not Started | 2021-09-07 | Not Started | 2021-09-07 | Not Started | 2021-09-20 | Not Started | 2021-09-07 | Not Started | 2021-12-20 | Not Started | 2022-01-18 | Not Started | 2022-02-10 | 2022-03-21 | -39 | Behind Schedule | Not Started | 2022-03-22 | 2022-04-04 | Not Started | 2022-05-18 | Not Started
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | E.5034805.01.12 | 5795300 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1168 | 0 | 1168 | 0.22121 | 0.22121 | 0 | 0 | 0.22121 | [5 empty] | 159527.53 | 91670.53 | 67857 |  |  | 32347.7 | 0 | 35509.3 | On/Under Budget | Request 2021 Budget | 0 | 79494 | -79494 | 79494 | -79494 | 82082.5 | 1485.6 | -42825.1 | 44310.7 | 0 | 0 | 0 | 32347.6 | 2479.6 | 108.9 | 0 | 0 | 2181 | 1158 | 71834 | 1486 | 473 | 473 | 473 | 473 | 473 | 473 | 2021-06-25 | 159774 | BL-A: | BL-A: 35226872_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8_08W - Apr 21 | 2021-04-28 | 2021-06-18 | Completed | 2021-07-26 | 2021-07-30 | Not Started | 2021-07-23 | Not Started | 2021-08-20 | Not Started | 2021-06-25 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-07-05 | 2021-07-12 | Not Started | 2021-09-24 | Not Started | 2021-09-24 | Not Started | 2021-10-07 | Not Started | 2021-09-24 | Not Started | 2021-11-12 | Not Started | 2021-12-13 | Not Started | 2023-03-21 | 2022-02-11 | 403 | On/ Ahead Schedule | Not Started | 2022-02-14 | 2022-02-25 | Not Started | 2022-04-12 | Not Started
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | E.5034805.01.10 | 5795300 | PEND | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2215 | 0 | 2215 | 0.41951 | 0.41951 | 0 | 0 | 0.41951 | [5 empty] | 204489.16 | 136632.16 | 67857 |  |  | 27523.5 | 8800 | 31533.5 | On/Under Budget | Budget Allocated | 67857 | 34000 | 33857 | 34000 | 33857 | 36539.1 | 7118.9 | 1824.1 | 5294.8 | 0 | 0 | 0 | 27523.5 | 2431.9 | 106.8 | 0 | 0 | 1718 | 15541 | 8441 | 7119 | 197 | 197 | 197 | 197 | 197 | 197 | 2021-06-18 | 159772 | BL-A: | BL-A: 35226870_ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6_08W - Apr 21 | 2021-04-28 | 2021-05-13 | Completed | 2021-07-14 | 2021-07-20 | Not Started | 2021-07-13 | Not Started | 2021-08-12 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-09 | Not Started | 2021-07-05 | 2021-07-12 | Not Started | 2021-09-10 | Not Started |  |  |  |  | 2021-09-10 | Not Started | 2021-10-01 | Not Started | 2021-10-05 | Not Started | 2021-12-29 | 2021-12-06 | 23 | On/ Ahead Schedule | Not Started | 2021-12-07 | 2021-12-20 | Not Started | 2022-02-02 | Not Started
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | E.5034804.01.07 | 5795299 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 12523 | 0 | 12523 | 2.3718 | 0 | 2.3718 | 0 | 2.3718 | 12523 | 0 | 2.3718 | 0 |  | 1313564.84 | 1131064.84 | 182500 |  |  | 118950.7 | 0 | 63549.3 | On/Under Budget | Budget Allocated | 153000 | 162613 | -9613 | 162613 | -9613 | 4478897.9 | 3222.5 | 1492 | 1730.5 | 0 | 0 | 0 | 118950.8 | 4312780.4 | 3504.9 | 0 | 5287 | 57079 | 49100 | 5992 | 3223 | 6264 | 6762 | 11710 | 5703 | 5732 | 5761 | 2021-06-18 | 158885 | BL-A_ | BL-A_35226852_CWSP - SHINGLE SPRINGS 2109-LR 9372PH3.2_08W_Apr.2021 | 2021-04-07 | 2021-04-30 | Completed | 2022-07-25 | 2022-07-25 | Not Started | 2022-08-05 | Not Started | 2022-08-08 | Not Started | 2022-08-09 | 2022-08-09 | Not Started | 2022-08-10 | 2022-08-30 | Not Started | 2022-08-16 | 2022-08-29 | Not Started | 2022-09-01 | Not Started |  |  |  |  | 2022-09-01 | Not Started | 2022-12-14 | Not Started | 2022-12-21 | Not Started | 2022-02-18 | 2023-01-03 | -319 | Behind Schedule | Not Started | 2023-01-05 | 2023-01-18 | Not Started | 2023-03-02 | Not Started
35231630 | CWSP - HIGHLANDS 1102628 PH 1.12 | E.5034697.01.12 | 5794549 | PEND | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 1918 | 0 | 1918 | 0.36326 | 0.36345 | 0 | 0 | 0.36326 | 1883 | 0 | 0.35663 | 0 |  | 73077 | 0 | 73077 |  |  | 29892.8 | 0 | 43184.2 | On/Under Budget | Request 2021 Budget | 0 | 29699 | -29699 | 29699 | -29699 | 29698.9 | 2430.3 | 2624.2 | -193.9 | 0 | 0 | 0 | 29892.8 | 0 | 0 | 0 | 0 | 0 | 0 | 27269 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-06-02 | Completed | 2021-07-30 | 2021-08-05 | Not Started | 2021-07-29 | Not Started | 2021-08-26 | Not Started | 2021-06-18 | 2021-08-18 | In Progress | 2021-08-19 | 2021-08-25 | Not Started | 2021-07-30 | 2021-08-12 | Not Started | 2021-09-20 | Not Started | 2021-09-20 | Not Started | 2021-10-01 | Not Started | 2021-09-20 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-03-08 | 2022-03-08 | 0 | On/ Ahead Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | E.5034610.01.16 | 5794205 | PEND | 08W | [6 empty] | 2021 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3326 | 0 | 3326 | 0.62992 | 0.62992 | 0 | 0 | 0.62992 | 3042 | 0 | 0.57614 | 0 |  | 482466.54 | 382466.54 | 100000 |  |  | 21254.9 | 0 | 78745.1 | On/Under Budget | Request 2021 Budget | 0 | 40871 | -40871 | 40871 | -40871 | 41493.7 | 20175.7 | 1980.2 | 18195.5 | 0 | 0 | 0 | 21254.9 | 623.1 | 0 | 0 | 0 | 799 | 303 | 18172 | 20176 | 237 | 237 | 237 | 237 | 237 | 237 | 2021-06-18 | 157824 | BL-A | BL-A 35228187_CWSP - Middletown 1103 - LR 830 PH2.3_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-14 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-08-13 | Not Started | 2021-09-08 | Not Started | 2021-07-15 | 2021-07-15 | Not Started | 2021-07-16 | 2021-08-05 | Not Started | 2021-08-16 | 2021-08-27 | Not Started | 2021-10-01 | Not Started | 2021-10-01 | Not Started | 2021-10-14 | Not Started | 2021-10-01 | Not Started | 2022-01-13 | Not Started | 2022-02-11 | Not Started | 2022-02-24 | 2022-02-22 | 2 | On/ Ahead Schedule | Not Started | 2022-02-28 | 2022-03-11 | Not Started | 2022-04-21 | Not Started
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | E.5034804.01.12 | 5795299 | PEND | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 1960 | 0 | 1960 | 0.37121 | 0 | 0.37121 | 0 | 0.37121 | 1960 | 0 | 0.37121 | 0 |  | 209584 | 0 | 209584 |  |  | 16553.4 | 0 | 193030.6 | On/Under Budget | Budget Allocated | 62873 | 62319 | 554 | 62319 | 554 | 786862.6 | 4161.8 | 670.1 | 3491.7 | 0 | 0 | 0 | 16553.4 | 724543.6 | 0 | 0 | 1861 | -1730 | 8688 | 7064 | 4162 | 4944 | 4973 | 5003 | 5032 | 9110 | 13212 | 2021-06-18 | 158184 | BL-A_ | BL-A_35231608_CWSP - SHINGLE SPRINGS 2109-LR9372-PH1.6_08W_Apr.2021 | 2021-03-31 | 2021-04-26 | Completed | 2022-06-02 | 2022-06-08 | Not Started | 2022-06-29 | Not Started | 2022-06-30 | Not Started | 2022-06-30 | 2022-06-30 | Not Started | 2022-07-01 | 2022-07-21 | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-07-25 | Not Started |  |  |  |  | 2022-07-25 | Not Started | 2022-11-04 | Not Started | 2022-11-11 | Not Started | 2022-01-31 | 2022-11-18 | -291 | Behind Schedule | Not Started | 2022-11-28 | 2022-12-09 | Not Started | 2023-01-17 | Not Started
35231626 | CWSP - HIGHLANDS 1102628 PH 1.8 | E.5034697.01.08 | 5794549 | PEND | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 3607 | 0 | 3607 | 0.68314 | 0.68314 | 0 | 0 | 0.68314 | 4041 | 0 | 0.76534 | 0 |  | 73077 | 0 | 73077 |  |  | 57403.3 | 0 | 15673.7 | On/Under Budget | Request 2021 Budget | 0 | 59722 | -59722 | 59722 | -59722 | 59722.2 | 2430.3 | 111.4 | 2318.9 | 0 | 0 | 0 | 57403.3 | 0 | 0 | 0 | 0 | 0 | 0 | 57292 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-05-31 | Completed | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-07-29 | Not Started | 2021-06-18 | 2021-08-16 | In Progress | 2021-08-17 | 2021-08-23 | Not Started | 2021-07-02 | 2021-07-15 | Not Started | 2021-08-25 | Not Started | 2021-08-25 | Not Started | 2021-09-07 | Not Started | 2021-08-25 | Not Started | 2021-12-07 | Not Started | 2022-01-05 | Not Started | 2022-03-08 | 2022-03-08 | 0 | On/ Ahead Schedule | Not Started | 2022-03-09 | 2022-03-22 | Not Started | 2022-05-05 | Not Started
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | E.5034713.01.04 | 5794554 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 5468 | 0 | 5468 | 1.0356 | 1.0356 | 0 | 0 | 1.0356 | 5329 | 0 | 1.0093 | 0 |  | 1351751 | 418066 | 933685 | 0 | 933685 | 48042.6 | 0 | 885642.4 | On/Under Budget | Budget Allocated | 1351751 | 794595 | 557156 | 794595 | 557156 | 794595.2 | 47910.4 | -759.1 | 48669.5 | 0 | 0 | 0 | 48042.6 | 0 | 0 | 0 | 0 | 2080 | 2948 | 43773 | 47910 | 436421 | 84192 | 168560 | 6854 | 1856 | 0 | 2021-06-18 | 158346 | BL-A_ | BL-A_35232443_CWSP - DESCHUTES 11049718 PH2.3_08W_Apr.2021 | 2021-04-01 | 2021-05-18 | Completed | 2021-05-20 | 2021-06-23 | Not Started | 2021-06-18 | Not Started | 2021-07-16 | Not Started | 2021-05-18 | 2021-05-18 | Completed | 2021-06-18 | 2021-07-08 | Not Started | 2021-07-30 | 2021-08-03 | Not Started | 2021-08-10 | Not Started |  |  |  |  | 2021-08-10 | Not Started | 2021-09-09 | Not Started | 2021-09-16 | Not Started | 2022-02-16 | 2021-10-28 | 111 | On/ Ahead Schedule | Not Started | 2021-10-29 | 2021-11-11 | Not Started | 2021-12-27 | Not Started
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | E.5034713.01.05 | 5794554 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 18648 | 0 | 18648 | 3.5318 | 3.5318 | 0 | 0 | 3.5318 | 18101 | 0 | 3.4282 | 0 |  | 1475573.09 | 1285573.09 | 190000 |  |  | 8343 | 0 | 181657 | On/Under Budget | Budget Allocated | 6830548 | 7068897 | -238349 | 7068897 | -238349 | 7068896.5 | 97738.3 | 1391.2 | 96347.1 | 0 | 0 | 0 | 8343.1 | 0 | 0 | 0 | 0 | 689 | 2791 | 3472 | 97738 | 2300372 | 2280562 | 2317902 | 44522 | 20849 | 0 | 2021-06-18 | 158347 | BL-A_ | BL-A_35232444_CWSP - DESCHUTES 11049718 PH2.4_08W_Apr.2021 | 2021-04-01 | 2021-08-11 | Not Started | 2021-08-12 | 2021-08-18 | Not Started | 2021-07-27 | Not Started | 2021-10-06 | Not Started | 2021-08-12 | 2021-08-12 | Not Started | 2021-08-13 | 2021-08-26 | Not Started | 2021-07-28 | 2021-08-10 | Not Started | 2021-10-22 | Not Started | 2021-10-22 | Not Started | 2021-11-04 | Not Started | 2021-10-22 | Not Started | 2021-12-15 | Not Started | 2021-12-24 | Not Started | 2022-02-16 | 2022-02-10 | 6 | On/ Ahead Schedule | Not Started | 2022-02-11 | 2022-02-24 | Not Started | 2022-04-11 | Not Started
35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | E.5034713.01.06 | 5794554 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | REDDING | North Valley Assets | 0 | 13784 | 0 | 13784 | 2.6106 | 2.6106 | 0 | 0 | 2.6106 | 13747 | 0 | 2.6036 | 0 |  | 3055462 | 699508 | 2355954 | 0 | 2355954 | 94433.3 | 0 | 2261520.7 | On/Under Budget | Budget Allocated | 3055462 | 2203287 | 852175 | 2203287 | 852175 | 2203286.5 | 6.6 | 18842.4 | -18835.8 | 0 | 0 | 0 | 94433.4 | 0 | 0 | 0 | 0 | 0 | 1092 | 74499 | 7 | 1129982 | 508881 | 30557 | 453360 | 4910 | 0 | 2021-06-18 | 158348 | BL-A_ | BL-A_35232445_CWSP - DESCHUTES 11049718 PH2.5_08W_Apr.2021 | 2021-04-01 | 2021-05-25 | Completed |  |  | Not Started | 2021-06-18 | Not Started | 2021-07-07 | Not Started | 2021-05-25 | 2021-05-25 | Completed | 2021-06-18 | 2021-07-08 | Not Started | 2021-07-19 | 2021-08-09 | Not Started | 2021-08-02 | Not Started |  |  |  |  | 2021-08-02 | Not Started | 2021-10-04 | Not Started | 2021-10-11 | Not Started | 2022-02-16 | 2021-12-29 | 49 | On/ Ahead Schedule | Not Started | 2021-12-30 | 2022-01-12 | Not Started | 2022-02-25 | Not Started
35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | E.5034710.01.03 | 5794551 | PEND | 08W | [6 empty] | 2021 | 2021 | SH | AUBURN | Sierra Assets | 0 | 9072 | 0 | 9072 | 1.7182 | 1.7182 | 0 | 0 | 1.7182 | 9072 | 0 | 1.7182 | 0 |  | 916452.02 | 599785.02 | 316667 |  |  | 129303.2 | 0 | 187363.8 | On/Under Budget | Budget Allocated | 3458896 | 3476704 | -17808 | 3476704 | -17808 | 3540864.2 | 54041.6 | 5655 | 48386.6 | 0 | 0 | 0 | 129303.3 | 64160.8 | 0 | 0 | 0 | 0 | 15527 | 108122 | 54042 | 1121306 | 1140505 | 960034 | 24031 | 24688 | 28449 | 2021-06-18 | 158189 | BL-A_ | BL-A_35232651_CWSP - MOUNTAIN QUARRIES 21016953 Ph 1.3_08W_Apr.2021 | 2021-03-31 | 2021-06-12 | Completed | 2021-07-07 | 2021-07-13 | Not Started | 2021-07-06 | Not Started | 2021-08-03 | Not Started | 2021-08-04 | 2021-08-04 | Not Started | 2021-08-05 | 2021-08-25 | Not Started | 2021-07-19 | 2021-08-20 | Not Started | 2021-08-27 | Not Started |  |  |  |  | 2021-08-27 | Not Started | 2021-12-09 | Not Started | 2021-12-16 | Not Started | 2022-04-21 | 2022-02-16 | 64 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-02 | Not Started | 2022-04-15 | Not Started
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | E.5034825.01.02 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1519 | 0 | 0 | 1519 | 0.28769 | 0.28769 | 0 | 0 | 0.28769 | 1519 | 0 | 0.28769 | 0 |  | 3159481 | 1545356 | 1614125 | 768290 | 845835 | 105713.8 | 0 | 1508411.2 | On/Under Budget | Budget Allocated | 1614125 | 1614127 | -2 | 1109311 | 504814 | 1109311.2 | 934.4 | 7514.6 | -6580.2 | 0 | 0 | 0 | 105713.8 | 0 | 0 | 0 | 3749 | 6284 | 21798 | 66369 | 3274 | 519068 | 75536 | 4138 | 913912 | 0 | 0 | 2021-05-31 | 158211 | BL-A | BL-A 35232298_FRRB - WYANDOTTE 1103 - W1 Ph 1.1 - Mar. 2021 | 2021-03-31 | 2021-04-29 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-09 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-09-09 | Not Started | 2021-09-29 | Not Started | 2021-10-04 | Not Started | 2021-10-04 | Not Started | 2021-08-27 | 2021-11-03 | -68 | Behind Schedule | Not Started | 2021-11-04 | 2021-11-17 | Not Started | 2021-12-31 | Not Started
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | E.5034825.01.18 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3630 | 0 | 0 | 3630 | 0.6875 | 0.6875 | 0 | 0 | 0.6875 | 3630 | 0 | 0.6875 | 0 |  | 7748520 | 2605230 | 5143290 | 768290 | 4375000 | 66314.2 | 17283.8 | 5059692 | On/Under Budget | Budget Allocated | 5143290 | 4450280 | 693010 | 4450280 | 693010 | 4450280.2 | 93.2 | -25202.6 | 25295.8 | 0 | 0 | 0 | 66314.3 | 0 | 0 | 0 | 0 | 685 | 1268 | 89564 | 93 | 1000094 | 1000094 | 1000094 | 1358388 | 0 | 0 | 2021-05-21 | 159000 | BL-A_ | BL-A_35233311_FRRB - WYANDOTTE 1103 - W2 PH 2.2 - B1_Apr 21 | 2021-04-09 | 2021-05-14 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | E.5034825.01.19 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4360 | 0 | 0 | 4360 | 0.82576 | 0.82576 | 0 | 0 | 0.82576 | 4360 | 0 | 0.82576 | 0 |  | 7066020 | 2447730 | 4618290 | 768290 | 3850000 | 93225.4 | 8559.8 | 4516504.8 | On/Under Budget | Budget Allocated | 4618290 | 3962881 | 655409 | 3962881 | 655409 | 3962881.4 | 99.6 | -31337.6 | 31437.2 | 0 | 0 | 0 | 93225.3 | 0 | 0 | 0 | 0 | 229 | 3400 | 120934 | 100 | 101 | 1000101 | 1000101 | 1000050 | 837867 | 0 | 2021-05-21 | 159002 | BL-A_ | BL-A_35233312_FRRB - WYANDOTTE 1103 - W2 PH 2.3 - B1_Apr 21 | 2021-04-09 | 2021-05-07 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | E.5034825.01.20 | 5795419 | PEND | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 13057 | 0 | 0 | 13057 | 2.4729 | 2.4729 | 0 | 0 | 2.4729 | 13057 | 0 | 2.4729 | 0 |  | 9341020 | 2972730 | 6368290 | 768290 | 5600000 | 80106.3 | 89588 | 6198595.7 | On/Under Budget | Budget Allocated | 6368290 | 5627308 | 740982 | 5627308 | 740982 | 5627308.1 | 109 | 32619.5 | -32510.5 | 0 | 0 | 0 | 80106.3 | 0 | 0 | 0 | 0 | 3881 | 1999 | 41608 | 109 | 1000110 | 1000110 | 1000110 | 1000055 | 1000000 | 579327 | 2021-05-21 | 159003 | BL-A_ | BL-A_35233314_FRRB - WYANDOTTE 1103 - W2 PH 2.4 - B1_Apr 21 | 2021-04-09 | 2021-05-17 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | 5783287 | POST | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 1604 | -1604 | 1604 | -1604 | [10 empty] | 334 | 319 | 319 | 316 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | 5783284 | POST | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 16 | -16 | 16 | -16 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | 5785726 | PREC | 08W | [6 empty] | 2020 |  | SH | GRSSVLLY |  | 0 | 10627 | 0 | 10627 | 2.0127 | 0 | 0 | 2.0127 | 0 | 11210 | 0 | 2.1231 | 0 | [10 empty] | Project is not in the WP or in 2020 WP | 59744 | 41468 | 18276 | 41468 | 18276 | [10 empty] | 39740 | 4 | 1725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31126827 | OCGC EP RECONDUCTOR WILLIAMS 1102- Y2016 | P.10692 | 5513271 | PREC | 08W | [6 empty] | Not in the WP |  |  | MRYSVLLE | Sacramento Assets | [14 empty] | 285956 | -35997 | 321953 |  |  | 274437.2 | 0 | 47515.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 274437.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31272375 | *CANC*CWSP PT. MORETTI BEYOND 5995 | P.11379 | 5530159 | PROD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | Central Coast Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 55000 | 0 | 55000 |  |  | 82588.3 | 0 | -27588.3 | OverRun | Project is not in the WP or in 2020 WP | 0 | 1772 | -1772 | 1772 | -1772 | 82588.3 | 0 | 0 | 0 | 8996.6 | 33418.5 | 34898.2 | 1771.7 | 0 | 0 | 1735 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35040505 | *CANC*CWSP - BIG BASIN 1101 - LR 10296 |  | 5530159 | PROD | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 |  | 5785972 | UNSC | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 29765 | -29765 | 29765 | -29765 | [10 empty] | 0 | 0 | 0 | 10407 | 19358 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31434881 | 0P 3100 SKYWAY RD PARADISE TUSCAN RIDGE |  | 5791419 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | CHICO |  | 17735 | 0 | 0 | 17735 | 3.3589 | 0 | 0 | 3.3589 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30977614 | WDDB OTTER 1102 PHASE 4 | P.06571 | 5530159 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 3681 | 0 | 3681 | 0.69716 | 0 | 0 | 0 | 0.69716 | [5 empty] | 326400 | 0 | 326400 |  |  | 239641.3 | 0 | 86758.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -39108 | 39108 | -39108 | 39108 | 1096678.4 | 0 | 0 | 0 | 26157.1 | 60844.3 | 180102.1 | -39107.8 | 857037.1 | 0 | 1128 | 0 | 0 | -40236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30977615 | WDDB OTTER 1102 PHASE 5 | P.06572 | 5530159 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | MONTEREY | Central Coast Assets | 0 | 2664 | 0 | 2664 | 0.50455 | 0 | 0 | 0 | 0.50455 | [5 empty] | 245198 | 5198 | 240000 |  |  | 208899.6 | 2096 | 29004.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -16536 | 16536 | -16536 | 16536 | 1022747.8 | 0 | 0 | 0 | 19685.7 | 50312 | 145733.4 | -16535.6 | 813848.2 | 0 | 1035 | 0 | 0 | -17570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | E.5014723.01 | 5783905 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 10641 | 0 | 10641 | 2.0153 | 0 | 0 | 0 | 2.0153 | [5 empty] | 250000 | 0 | 250000 |  |  | 175292.7 | 0 | 74707.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8061 | -8061 | 8061 | -8061 | 3065544.3 | 239.8 | 0 | 239.8 | 205.5 | 23989.3 | 146272.5 | 4825.3 | 2887015.7 | 0 | 957 | 660 | 1418 | 655 | 1134 | 240 | 249 | 249 | 249 | 249 | 249 | 1753 | 2021-06-18 | 160669 | BL-A1 | BL-A1 35052735_CWSP - MIWUK 1701 - LR 10600 PH 1.1_08W - DD 210507 | 2021-05-13 | 2020-07-14 | Completed | 2020-10-30 | 2020-12-03 | Not Started | 2020-09-04 | Completed | 2022-01-03 | Not Started | 2020-11-17 | 2020-11-17 | Completed | 2022-01-04 | 2022-01-10 | Not Started | 2022-01-04 | 2022-01-13 | Not Started | 2022-02-22 | Not Started |  |  |  |  | 2022-02-22 | Not Started |  |  | 2022-05-26 | Not Started | 2022-08-11 | 2022-08-11 | 0 | On/ Ahead Schedule | Not Started | 2022-08-12 | 2022-08-25 | Not Started | 2022-10-17 | Not Started
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | 5531041 | UNSC | 08W | [6 empty] | Not in the WP | 2021 | SH | SNCARLOS | Peninsula Assets | 0 | 5597 | 0 | 5597 | 1.06 | 0 | 0 | 0 | 1.06 | [5 empty] | 190000 | 0 | 190000 |  |  | 113149.6 | 0 | 76850.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 13214 | -13214 | 13214 | -13214 | 1483776.8 | 722 | 49.2 | 672.8 | 5447.9 | 42969.5 | 56522.8 | 8209.4 | 1365622.7 | 0 | 3626 | 1609 | 824 | 1273 | 829 | 722 | 722 | 722 | 722 | 722 | 722 | 722 | 2021-06-18 | 161147 | BL-B: | BL-B: 35053429__CWSP - HALF MOON BAY 1102 - FUCO 12457 REPL OH - May 21 | 2021-05-28 | 2019-06-13 | Completed |  |  | Not Started | 2020-10-16 | Completed | 2022-07-14 | Not Started | 2022-07-29 | 2022-07-29 | Not Started | 2022-08-19 | 2022-08-25 | Not Started | 2022-07-18 | 2022-08-05 | Not Started | 2022-08-26 | Not Started |  |  |  |  | 2022-08-29 | Not Started | 2022-10-04 | Not Started | 2022-10-04 | Not Started | 2022-09-26 | 2022-10-24 | -28 | Behind Schedule | Not Started | 2022-12-13 | 2022-12-26 | Not Started | 2023-04-17 | Not Started
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 | E.5014730.01 | 5791727 | UNSC | 08W | [6 empty] | Not in the WP | 2021 | SH | SONORA | Yosemite Assets | 0 | 8100 | 0 | 8100 | 1.5341 | 0 | 0 | 0 | 1.5341 | [5 empty] | 6133206 | 1783746 | 4349460 |  |  | 110943.5 | 694817.6 | 3543698.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 18670 | -18670 | 18670 | -18670 | 2633634.3 | 158.5 | 0 | 158.5 | 205.5 | 6602.9 | 86609.2 | 17525.9 | 2521546.7 | 0 | 10707 | 4820 | 594 | 589 | 817 | 159 | 164 | 164 | 164 | 164 | 164 | 164 | 2021-06-18 | 160674 | BL-B1 | BL-B1 35052823_CWSP - MIWUK 1702 - LR 6018 - PH 1.1_08W - DD 210507 | 2021-05-13 | 2020-07-03 | Completed |  |  | Completed | 2020-07-30 | Completed | 2020-10-23 | Completed | 2022-02-02 | 2022-02-04 | Not Started | 2022-02-07 | 2022-02-25 | Not Started | 2020-09-04 | 2020-09-30 | Completed | 2022-02-25 | Not Started | [8 empty] | 2022-04-07 | Not Started | 2022-04-25 | 2022-04-25 | 0 | On/ Ahead Schedule | Not Started | 2022-04-26 | 2022-05-09 | Not Started | 2022-08-02 | Not Started
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | E.5014542.01 | 5782530 | UNSC | 08W | [6 empty] | 2022 | 2021 | SH | STCRUZ | Central Coast Assets | 0 | 7779 | 0 | 7779 | 1.4733 | 1 | 0.4733 | 0 | 1.4733 | 7779 | 0 | 1.4733 | 0 |  | 4994628 | 1603586.6 | 3391041.4 |  |  | 243345.8 | 2058639.2 | 1089056.4 | On/Under Budget | Budget Allocated | 2129616.4 | 2596668 | -467051.6 | 2596668 | -467051.6 | 2737424.6 | 657118.4 | 38029.5 | 619088.9 | 8061.7 | 11208.2 | 121487.2 | 102588.7 | 0 | 0 | 9460 | 4061 | 26810 | 15050 | 9179 | 657118 | 920473 | 452030 | 0 | 502487 | 0 | 0 | 2021-06-18 | 128567 | WSHP | WSHP 190307 - 35052731_CWSP - BIG BASIN 1101 - 10296 ZONE P June 23 2020 | 2019-03-07 | 2020-08-01 | Completed |  |  | Completed | 2021-10-05 | Not Started | 2020-08-18 | Completed | [6 empty] | 2021-05-25 | 2021-07-23 | In Progress | 2021-06-21 | Not Started |  |  |  |  | 2021-08-02 | Not Started |  |  | 2022-02-16 | Not Started | 2020-10-27 | 2022-02-17 | -478 | Behind Schedule | Not Started |  |  |  | 2022-09-27 | Not Started
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | 5530176 | UNSC | 08W | [6 empty] | 2021 |  | SH | ANGLSCMP | Stockton Assets | 0 | 3362 | 0 | 3362 | 0.63674 | 0.63674 | 0 | 0 | 0.63674 | 3362 | 0 | 0.63674 | 0 |  | 403045.55 | -448718.05 | 851763.6 | 131250 | 720513.6 | 177477.9 | 253982.3 | 420303.4 | On/Under Budget | Budget Allocated | 490994.6 | 645653 | -154658.4 | 645653 | -154658.4 | 649373.7 | 157797.8 | 2118 | 155679.8 | 0 | 3720.4 | 0 | 173757.5 | 0 | 0 | 33322 | 63698 | 7241 | 9953 | 57425 | 157798 | 200946 | 111631 | 593 | 1368 | 1295 | 383 | 2021-06-18 | 161091 | BL-0 | BL-0 35075103_FROGTOWN 1701 RECOND_08W - DD 210521 | 2021-05-26 | 2021-03-11 | Completed | 2021-05-14 | 2021-05-20 | Completed | 2021-06-15 | Completed | 2021-05-26 | Completed | 2021-06-23 | 2021-06-23 | Not Started | 2021-06-24 | 2021-06-24 | Not Started | 2021-04-15 | 2021-05-15 | Completed | 2021-06-28 | Not Started |  |  |  |  | 2021-06-28 | Not Started | 2021-07-30 | Not Started | 2021-08-02 | Not Started | 2021-09-09 | 2021-09-20 | -11 | Behind Schedule | Not Started | 2021-09-21 | 2021-09-27 | Not Started | 2021-11-10 | Not Started
35095246 | BUCOCAMP - ERIKA DRIVE, PARADISE |  | 5786123 | UNSC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 89554.6 | -410445.4 | 500000 |  |  | 145545.9 | 0 | 354454.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 45 | -45 | 45 | -45 | 145545.9 | 0 | 0 | 0 | 0 | 121763.3 | 23737.2 | 45.4 | 0 | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | E.5015030.01 | 5785239 | UNSC | 08W | [6 empty] | Not in the WP | 2021 | SH | CHICO | North Valley Assets | 610 | 9619 | 0 | 10229 | 1.9373 | 0 | 0 | 0 | 1.9373 | [5 empty] | 250000 | 0 | 250000 |  |  | 191790.5 | 0 | 58209.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 6000 | -6000 | 6000 | -6000 | 225973.4 | 73.6 | 0 | 73.6 | 0 | 5537.1 | 180788.7 | 5464.7 | 33647.2 | 0 | 1139 | 1085 | 1085 | 1078 | 1078 | 74 | 77 | 77 | 77 | 77 | 77 | 77 | 2021-06-18 |  |  |  |  | 2020-08-12 | Completed | 2021-12-02 | 2021-12-22 | Not Started | 2021-06-18 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | 2021-12-23 | Not Started | 2021-12-24 | 2022-01-13 | Not Started | 2021-07-09 | 2021-08-06 | Not Started | 2022-01-31 | Not Started |  |  |  |  | 2022-01-31 | Not Started | 2022-04-22 | Not Started | 2022-05-23 | Not Started | 2022-06-22 | 2022-06-22 | 0 | On/ Ahead Schedule | Not Started | 2022-06-23 | 2022-07-06 | Not Started | 2022-08-12 | Not Started
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | E.5014723.02 | 5785935 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 12936 | 0 | 12936 | 2.45 | 0 | 0 | 0 | 2.45 | [5 empty] | 250000 | 0 | 250000 |  |  | 210487.9 | 0 | 39512.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8992 | -8992 | 8992 | -8992 | 5082806 | 104.4 | 0 | 104.4 | 0 | 973 | 202781.6 | 6733.3 | 4870059.6 | 0 | 1316 | 1418 | 1189 | 1402 | 1409 | 104 | 108 | 108 | 108 | 108 | 108 | 1613 | 2021-06-18 | 160670 | BL-A1 | BL-A1 35115046_CWSP - MIWUK 1701 - LR 10600 PH 1.2_08W - DD 210507 | 2021-05-13 | 2020-08-13 | Completed | 2020-11-04 | 2020-12-03 | Not Started | 2020-10-07 | Completed | 2021-12-22 | Not Started | 2022-01-31 | 2022-02-04 | Not Started | 2022-02-07 | 2022-03-04 | Not Started | 2021-12-23 | 2022-01-05 | Not Started | 2022-04-08 | Not Started |  |  |  |  | 2022-04-08 | Not Started | 2022-06-23 | Not Started | 2022-07-21 | Not Started | 2022-08-22 | 2022-08-22 | 0 | On/ Ahead Schedule | Not Started | 2022-08-23 | 2022-09-05 | Not Started | 2022-10-12 | Not Started
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 | E.5015427.05 | 5785989 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 13653 | 0 | 13653 | 2.5858 | 0 | 0 | 0 | 2.5858 | [5 empty] | 4165227 | 870173 | 3295054 |  |  | 214683.9 | 0 | 3080370.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 9893 | -9893 | 9893 | -9893 | 2936804.7 | 0 | 69.6 | -69.6 | 0 | 0 | 204721.6 | 9962.3 | 2722190.4 | 0 | 4569 | 1542 | 1114 | 1106 | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 160686 | BL-A1 | BL-A1: 35115057_CWSP - MIWUK 1701 - OCB - PH2.5 - DD 210507 | 2021-05-13 | 2020-07-24 | Completed | 2020-09-14 | 2020-09-22 | Completed | 2020-08-31 | Completed | 2022-01-03 | Not Started | 2022-01-04 | 2022-01-10 | Not Started | 2022-01-11 | 2022-01-13 | Not Started | 2020-10-01 | 2020-11-03 | Completed | 2022-01-18 | Not Started |  |  |  |  | 2022-01-18 | Not Started | 2022-03-15 | Not Started | 2022-03-31 | Not Started | 2022-05-10 | 2022-05-10 | 0 | On/ Ahead Schedule | Not Started | 2022-05-11 | 2022-05-12 | Not Started | 2022-05-16 | Not Started
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | E.5014742.07 | 5786136 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 4291 | 0 | 4291 | 0.81269 | 0 | 0 | 0 | 0.81269 | [5 empty] | 1801039.27 | -221572.73 | 2022612 |  |  | 104874 | 0 | 1917738 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 18736 | -18736 | 18736 | -18736 | 1266678.3 | 163.3 | -26836.8 | 27000.1 | 0 | 235.3 | 113919.2 | -9280.4 | 1133788.2 | 0 | 6097 | 8828 | 1225 | 464 | 943 | 163 | 169 | 169 | 169 | 169 | 169 | 169 | 2021-06-18 | 154957 | BL-0 | BL-0 35114052_CWSP - PINE GROVE 1102 - LR1222 - PH 2.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-12 | Completed | 2020-08-20 | 2020-08-31 | Completed | 2020-07-30 | Completed | 2020-08-31 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-08-13 | 2020-09-25 | Completed | 2022-02-24 | Not Started |  |  |  |  | 2022-02-24 | Not Started | 2022-04-01 | Not Started | 2022-04-15 | Not Started | 2022-06-16 | 2022-06-16 | 0 | On/ Ahead Schedule | Not Started | 2022-06-17 | 2022-06-30 | Not Started | 2022-08-08 | Not Started
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | E.5014745.07 | 5786135 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7602 | 0 | 7602 | 1.4398 | 0 | 0 | 0 | 1.4398 | [5 empty] | 2273638.04 | -748307.96 | 3021946 |  |  | 263717.7 | 0 | 2758228.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 16669 | -16669 | 16669 | -16669 | 2243737 | 202.3 | -135664.7 | 135867 | 0 | 213.7 | 383960.5 | -120456.5 | 1842894.2 | 0 | -1016 | 2874 | 3445 | 7607 | 2299 | 202 | 210 | 210 | 210 | 210 | 210 | 210 | 2021-06-18 | 154958 | BL-0 | BL-0 35114045_CWSP - PINE GROVE 1102 - LR1222 - PH 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-18 | Completed | 2020-08-17 | 2020-08-17 | Completed | 2020-06-01 | Completed | 2020-08-17 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-08-20 | 2020-10-02 | Completed | 2022-02-24 | Not Started |  |  |  |  | 2022-02-24 | Not Started | 2022-04-28 | Not Started | 2022-05-12 | Not Started | 2022-06-13 | 2022-06-13 | 0 | On/ Ahead Schedule | Not Started | 2022-06-14 | 2022-06-27 | Not Started | 2022-08-03 | Not Started
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | E.5014742.05 | 5785999 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 7377.2 | 0 | 7377.2 | 1.3972 | 0 | 0 | 0 | 1.3972 | [5 empty] | 4089518 | 1107840.4 | 2981677.6 |  |  | 208188.3 | 0 | 2773489.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 37337 | -37337 | 37337 | -37337 | 2423711.1 | 0 | -85576 | 85576 | 0 | 235.3 | 256192.1 | -48239 | 2129946.8 | 0 | 11679 | 16671 | 5923 | 1292 | 1771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154953 | BL-0 | BL-0 35114050_CWSP - PINE GROVE 1102 - LR1222 - PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-06-15 | Completed | 2020-07-20 | 2020-07-27 | Completed | 2020-06-01 | Completed | 2020-07-28 | Completed | 2021-11-26 | 2021-11-26 | Not Started | 2021-11-29 | 2021-12-17 | Not Started | 2020-08-13 | 2021-12-02 | In Progress | 2022-01-03 | Not Started |  |  |  |  | 2022-01-03 | Not Started | 2022-02-24 | Not Started | 2022-02-24 | Not Started | 2022-03-28 | 2022-03-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-04 | 2022-03-17 | Not Started | 2022-05-18 | Not Started
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | E.5014542.02 | 5786124 | UNSC | 08W | [6 empty] | 2022 | 2022 | SH | STCRUZ | Central Coast Assets | 0 | 18848 | 0 | 18848 | 3.5697 | 2.64 | 0.92973 | 0 | 3.5697 | 18848 | 0 | 3.5697 | 0 |  | 7087268 | 1963144.7 | 5124123.3 |  |  | 190676 | 2362520.8 | 2570926.5 | On/Under Budget | Budget Allocated | 900000 | 1731878 | -831878 | 1731878 | -831878 | 4330691.3 | 31267.7 | 1919.8 | 29347.9 | 0 | 128.7 | 128603.3 | 61944.1 | 2470081.2 | 0 | 1823 | 780 | 29096 | 27260 | 1066 | 31268 | 822808 | 817778 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2020-08-01 | Completed | 2020-07-29 | 2020-08-04 | Completed | 2021-09-07 | Not Started | 2021-05-25 | Completed | 2021-06-18 | 2021-06-18 | Not Started | 2020-08-03 | 2021-07-09 | In Progress | 2021-09-08 | 2021-09-08 | Not Started | 2021-06-15 | In Progress |  |  |  |  | 2021-10-04 | Not Started | 2021-12-13 | Not Started | 2022-01-25 | Not Started | 2022-01-25 | 2022-01-25 | 0 | On/ Ahead Schedule | Not Started | 2022-02-09 | 2022-02-22 | Not Started | 2022-08-23 | Not Started
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | E.5014542.03 | 5786125 | UNSC | 08W | [6 empty] | 2022 | 2022 | SH | STCRUZ | Central Coast Assets | 0 | 12799 | 0 | 12799 | 2.4241 | 1.9299 | 0.49413 | 0 | 2.4241 | 13637 | 0 | 2.5828 | 0 |  | 6920313 | 1931699.3 | 4988613.7 |  |  | 191121.2 | 1872096.4 | 2925396.1 | On/Under Budget | Budget Allocated | 900000 | 1429916 | -529916 | 1429916 | -529916 | 2480822.4 | 21223.3 | 1682.6 | 19540.7 | 0 | 192.2 | 128049.6 | 62879.4 | 922664.2 | 0 | 782 | 747 | 14836 | 37188 | 7643 | 21223 | 855378 | 492118 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2020-08-17 | Completed | 2020-07-31 | 2020-08-27 | Completed | 2021-10-06 | Not Started | 2020-09-03 | Completed | 2021-06-18 | 2021-06-18 | Not Started | 2021-06-21 | 2021-07-13 | Not Started | 2021-06-21 | 2021-10-06 | In Progress | 2021-07-01 | Not Started |  |  |  |  | 2021-10-29 | Not Started | 2021-11-25 | Not Started | 2021-12-02 | Not Started | 2022-03-28 | 2022-03-28 | 0 | On/ Ahead Schedule | Not Started | 2022-03-29 | 2022-04-11 | Not Started | 2022-10-24 | Not Started
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | E.5015236.07 | 5786029 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8454 | 0 | 8454 | 1.6011 | 0 | 0 | 0 | 1.6011 | [5 empty] | 2621905.68 | -724952.32 | 3346858 |  |  | 130664.8 | 0 | 3216193.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 8668 | -8668 | 8668 | -8668 | 2224364.2 | 153.8 | -46303.7 | 46457.5 | 0 | 37.8 | 169373.2 | -38746.3 | 2046285 | 0 | 3516 | 957 | 957 | 950 | 1178 | 154 | 160 | 160 | 160 | 160 | 160 | 160 | 2021-06-18 | 154971 | BL-0 | BL-0 35115852_CWSP-SALT SPRINGS 2102-LR3142ZONE-PH 2.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-05-28 | Completed | 2020-09-10 | 2020-09-22 | Completed | 2020-10-19 | Completed | 2021-12-10 | Not Started | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-10 | Not Started | 2020-08-13 | 2020-10-16 | Completed | 2022-05-03 | Not Started |  |  |  |  | 2022-05-03 | Not Started | 2022-06-29 | Not Started | 2022-07-13 | Not Started | 2022-10-13 | 2022-10-13 | 0 | On/ Ahead Schedule | Not Started | 2022-10-14 | 2022-10-27 | Not Started | 2022-12-05 | Not Started
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | E.5015235.02 | 5786022 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8473 | 0 | 8473 | 1.6047 | 0 | 0 | 0 | 1.6047 | [5 empty] | 1924559.32 | -1534628.18 | 3459187.5 |  |  | 241877.4 | 0 | 3217310.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15616 | -15616 | 15616 | -15616 | 2212262.5 | 0 | -64739.8 | 64739.8 | 0 | 1583.2 | 289417.9 | -49123.6 | 1905645.3 | 0 | 4090 | 6121 | 1734 | 1722 | 1949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154961 | BL-B | BL-B 35115853_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.2_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-01 | Completed | 2020-07-24 | 2020-07-30 | Completed | 2020-07-29 | Completed | 2020-07-30 | Completed | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-03 | Not Started | 2020-08-03 | 2020-09-04 | Completed | 2022-02-02 | Not Started |  |  |  |  | 2022-02-02 | Not Started | 2022-03-31 | Not Started | 2022-04-14 | Not Started | 2022-05-05 | 2022-05-05 | 0 | On/ Ahead Schedule | Not Started | 2022-05-06 | 2022-05-19 | Not Started | 2022-05-26 | Not Started
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | E.5015236.05 | 5786021 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6787 | 0 | 6787 | 1.2854 | 0 | 0 | 0 | 1.2854 | [5 empty] | 1424587.78 | -1278855.22 | 2703443 |  |  | 158812.4 | 0 | 2544630.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 11289 | -11289 | 11289 | -11289 | 2005270.1 | 146.1 | -48310.3 | 48456.4 | 0 | 0 | 196888.4 | -38076 | 1797092.6 | 0 | 5470 | 1095 | 1266 | 1088 | 1315 | 146 | 152 | 152 | 152 | 152 | 152 | 152 | 2021-06-18 | 154969 | BL-B | BL-B 35115850_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-08-24 | Completed | 2020-10-01 | 2020-10-01 | Not Started | 2020-06-16 | Completed | 2021-12-07 | Not Started | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-10-23 | 2020-11-17 | Completed | 2022-04-20 | Not Started |  |  |  |  | 2022-04-20 | Not Started | 2022-06-16 | Not Started | 2022-06-30 | Not Started | 2022-08-31 | 2022-08-31 | 0 | On/ Ahead Schedule | Not Started | 2022-09-01 | 2022-09-14 | Not Started | 2022-10-21 | Not Started
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | E.5015235.07 | 5786027 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 6883 | 0 | 6883 | 1.3036 | 0 | 0 | 0 | 1.3036 | [5 empty] | 1190982.71 | -1022674.29 | 2213657 |  |  | 152012 | 0 | 2061645 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 10011 | -10011 | 10011 | -10011 | 1185907.4 | 785.5 | -70861.4 | 71646.9 | 0 | 1326.6 | 217207.8 | -66522.4 | 957362.3 | 0 | -22280 | 6070 | 17656 | 1723 | 1170 | 786 | 814 | 814 | 814 | 814 | 814 | 814 | 2021-06-18 | 154965 | BL-0 | BL-0 35115858_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.7_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-03 | Completed | 2020-08-27 | 2020-09-14 | Completed | 2020-07-30 | Completed | 2021-12-10 | Not Started | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-03 | Not Started | 2022-02-07 | 2022-02-25 | Not Started | 2022-05-03 | Not Started |  |  |  |  | 2022-05-03 | Not Started | 2022-06-13 | Not Started | 2022-05-31 | Not Started | 2022-07-29 | 2022-07-29 | 0 | On/ Ahead Schedule | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-20 | Not Started
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | E.5015235.05 | 5786025 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 10943 | 0 | 10943 | 2.0725 | 0 | 0 | 0 | 2.0725 | [5 empty] | 2167732.82 | -1323323.18 | 3491056 |  |  | 251947.7 | 0 | 3239108.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 21797 | -21797 | 21797 | -21797 | 2078589.2 | 599.7 | -70522.1 | 71121.8 | 0 | 346.1 | 304656.3 | -53054.7 | 1751789.4 | 0 | 3697 | 6997 | 1818 | 2918 | 2039 | 600 | 622 | 622 | 622 | 622 | 622 | 622 | 2021-06-18 | 154963 | BL-0 | BL-0 35115856_CWSP-SALT SPRINGS 2102-LR3142&L491-PHA 1.5_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-07 | Completed | 2020-09-01 | 2020-09-29 | Completed | 2020-10-27 | Completed | 2020-09-29 | Completed | 2021-12-13 | 2021-12-13 | Not Started | 2021-12-14 | 2022-01-10 | Not Started | 2022-02-07 | 2022-02-18 | Not Started | 2022-04-26 | Not Started |  |  |  |  | 2022-04-26 | Not Started | 2022-06-22 | Not Started | 2022-07-06 | Not Started | 2022-10-06 | 2022-10-06 | 0 | On/ Ahead Schedule | Not Started | 2022-10-07 | 2022-10-20 | Not Started | 2022-11-28 | Not Started
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | E.5015236.03 | 5786019 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP | Stockton Assets | 0 | 8697 | 0 | 8697 | 1.6472 | 0 | 0 | 0 | 1.6472 | [5 empty] | 1308258.35 | -1364352.65 | 2672611 |  |  | 204419.1 | 1175651 | 1292540.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15409 | -15409 | 15409 | -15409 | 1521386.2 | 712.9 | -95206.6 | 95919.5 | 0 | 0 | 289364.1 | -84944.8 | 1216613.3 | 0 | 3122 | 1537 | 1537 | 2082 | 1984 | 713 | 739 | 739 | 739 | 739 | 739 | 739 | 2021-06-18 | 154967 | BL-0 | BL-0 35115848_CWSP-SALT SPRINGS 2102-LR3142 ZONE-PH 2.3_08W - DD 210122 Jan. 2021 | 2021-01-25 | 2020-07-08 | Completed | 2020-08-31 | 2020-08-31 | Completed | 2020-10-29 | Completed | 2020-08-31 | Completed | 2021-12-08 | 2021-12-08 | Not Started | 2021-12-09 | 2022-01-05 | Not Started | 2020-09-25 | 2020-11-13 | Completed | 2022-05-04 | Not Started |  |  |  |  | 2022-05-04 | Not Started | 2022-06-30 | Not Started | 2022-07-22 | Not Started | 2022-09-22 | 2022-09-22 | 0 | On/ Ahead Schedule | Not Started | 2022-09-23 | 2022-10-06 | Not Started | 2022-11-14 | Not Started
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | E.5014722.05 | 5785932 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | SONORA | Yosemite Assets | 0 | 9687 | 0 | 9687 | 1.8347 | 0 | 0 | 0 | 1.8347 | [5 empty] | 300000 | 0 | 300000 |  |  | 209415 | 0 | 90585 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 13821 | -13821 | 13821 | -13821 | 4550411.5 | 128.9 | 0 | 128.9 | 0 | 0 | 196524.8 | 12890.2 | 4340065.8 | 0 | 2952 | 6616 | 1113 | 1105 | 1105 | 129 | 134 | 134 | 134 | 134 | 134 | 134 | 2021-06-18 | 160668 | BL-A1 | BL-A1 35116399_CWSP - MIWUK 1702 - LR 8090 - PH 1.5_08W - DD 210507 | 2021-05-13 | 2020-08-21 | Completed | 2022-02-10 | 2022-02-23 | Not Started | 2020-09-01 | Completed | 2022-02-23 | Not Started | 2022-02-24 | 2022-02-24 | Not Started | 2022-02-25 | 2022-02-28 | Not Started | 2020-11-03 | 2020-11-19 | Completed | 2022-06-10 | Not Started |  |  |  |  | 2022-06-10 | Not Started | 2022-08-16 | Not Started | 2022-09-14 | Not Started | 2022-10-26 | 2022-10-26 | 0 | On/ Ahead Schedule | Not Started | 2022-10-27 | 2022-11-09 | Not Started | 2023-03-22 | Not Started
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 | E.5015701.02 | 5786036 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 9222 | 0 | 9222 | 1.7466 | 0 | 0 | 0 | 1.7466 | [5 empty] | 4438411 | 1235376.3 | 3203034.7 |  |  | 165616.3 | 0 | 3037418.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 7919 | -7919 | 7919 | -7919 | 2036000.4 | 168.6 | -45691.6 | 45860.2 | 0 | 0 | 204605.6 | -38989.3 | 1823475.5 | 0 | 1193 | 1147 | 1360 | 1859 | 1144 | 169 | 175 | 175 | 175 | 175 | 175 | 175 | 2021-06-18 | 154923 | BL-0 | BL-0 35116515_CWSP - STANISLAUS 1702 - LR1888 - PH 1.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-05-29 | Completed | 2020-07-16 | 2020-07-27 | Completed | 2020-06-15 | Completed | 2022-01-14 | Not Started | 2022-04-21 | 2022-04-27 | Not Started | 2022-04-28 | 2022-05-11 | Not Started | 2020-08-17 | 2020-10-16 | Completed | 2022-05-19 | Not Started |  |  |  |  | 2022-05-19 | Not Started | 2022-07-20 | Not Started | 2022-07-20 | Not Started | 2022-07-07 | 2022-09-26 | -81 | Behind Schedule | Not Started | 2022-09-27 | 2022-10-10 | Not Started | 2022-11-16 | Not Started
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 | E.5015394.02 | 5786041 | UNSC | 08W | [6 empty] | Not in the WP |  | SH | JACKSON | Stockton Assets | 0 | 6348 | 0 | 6348 | 1.2023 | 0 | 0 | 0 | 1.2023 | [5 empty] | 1026224.53 | 901224.53 | 125000 |  |  | 89820.9 | 0 | 35179.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 5958 | -5958 | 5958 | -5958 | 1647538.7 | 0 | 0 | 0 | 0 | 3475.9 | 80387.4 | 5957.7 | 1557717.8 | 0 | 511 | 3929 | 509 | 505 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 154918 | BL-B | BL-B 35116511_CWSP - STANISLAUS 1702 - LR1888 - PH 2.2_08W - DD 210122 Jan. 2021 | 2021-01-22 | 2020-08-04 | Completed | 2022-02-02 | 2022-03-15 | Not Started | 2022-02-11 | Not Started | 2022-03-15 | Not Started | 2022-03-18 | 2022-03-18 | Not Started | 2022-03-21 | 2022-04-08 | Not Started | 2022-02-09 | 2022-03-29 | Not Started | 2022-04-12 | Not Started |  |  |  |  | 2022-04-12 | Not Started | 2022-06-08 | Not Started | 2022-06-22 | Not Started | 2022-08-23 | 2022-08-23 | 0 | On/ Ahead Schedule | Not Started | 2022-08-24 | 2022-09-06 | Not Started | 2022-10-13 | Not Started
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | E.5025637.01 | 5788786 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | STROSA | Sonoma Assets | 9175 | 0 | 0 | 9175 | 1.7377 | 1.7377 | 0 | 0 | 1.7377 | 12175 | 0 | 2.3059 | 0 |  | 8431936 | 2011978 | 6419958 | 0 | 6419958 | 1323964.8 | 1781181.3 | 3314811.9 | On/Under Budget | Budget Allocated | 12006359 | 6262403 | 5743956 | 5224714 | 6781645 | 5384601.6 | 1833600.6 | -500375.7 | 2333976.3 | 0 | 705.8 | 159181.9 | 1164077.2 | 0 | 0 | 8174 | 8906 | 52165 | 449096 | 1146113 | 1833601 | 673245 | 280648 | 251236 | 3472 | 1552277 | 3472 | 2021-06-18 | 159333 | BL-0: | BL-0: 35145524_PSPS - Rincon 1101 and 1103- CB_08W - B1_Apr 21 | 2021-04-20 | 2020-11-02 | Completed | 2021-02-12 | 2021-03-08 | Completed | 2021-02-12 | Completed | 2021-03-06 | Completed | 2021-03-09 | 2021-03-10 | Completed | 2021-03-10 | 2021-03-10 | Completed | 2021-03-01 | 2021-03-03 | Completed | 2021-04-26 | Completed |  |  |  |  | 2021-06-28 | Not Started | 2021-07-30 | Not Started | 2021-08-30 | Not Started | 2021-11-09 | 2021-10-29 | 11 | On/ Ahead Schedule | Not Started | 2021-11-01 | 2021-11-12 | Not Started | 2021-12-21 | Not Started
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | E.5025638.01 | 5788787 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | STROSA | Sonoma Assets | 7819 | 1056 | 0 | 8875 | 1.6809 | 1.6809 | 0 | 0 | 1.6809 | 7760 | 0 | 1.4697 | 0 |  | 7914493 | 2012705.6 | 5901787.4 | 0 | 5901787.4 | 1929077.8 | 1692440.8 | 2280268.8 | On/Under Budget | Budget Allocated | 5901787 | 5745493 | 156294 | 4933904 | 967883 | 5089402.3 | 2383100.3 | 204094.9 | 2179005.4 | 0 | 470.6 | 144612.4 | 1783994.8 | 10415.6 | 0 | 8172 | 8841 | 9185 | 489163 | 1064538 | 2383100 | 240601 | 16448 | 3472 | 3472 | 1515028 | 3472 | 2021-06-18 | 159335 | BL-0: | BL-0: 35145525_PSPS - Rincon 1102 and 1104 - CB_08W - B1_Apr 21 | 2021-04-20 | 2020-10-25 | Completed | 2021-02-12 | 2021-03-02 | Completed | 2021-02-18 | Completed | 2021-03-03 | Completed | 2021-02-19 | 2021-03-19 | Completed | 2021-02-19 | 2021-03-24 | Completed | 2021-02-22 | 2021-03-01 | Completed | 2021-04-19 | Completed |  |  |  |  | 2021-05-05 | Completed | 2021-07-20 | Not Started | 2021-08-18 | Not Started | 2021-10-01 | 2021-10-19 | -18 | Behind Schedule | Not Started | 2021-10-20 | 2021-11-02 | Not Started | 2021-12-09 | Not Started
35142198 | BR-03-08-W (E) BELLEVIEW PARB |  | 5786123 | UNSC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 848291.05 | 0.05 | 848291 |  |  | 743391.9 | 0 | 104899.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 26804 | -26804 | 26804 | -26804 | 743391.9 | 0 | 0 | 0 | 0 | 948.3 | 715640.1 | 26803.5 | 0 | 0 | 1276 | 0 | 25527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | 5530164 | UNSC | 08W | [6 empty] | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 2824 | 0 | 2824 | 0.53485 | 0.53485 | 0 | 0 | 0.53485 | 2075 | 0 | 0.39299 | 0 |  | 1075765 | 435886 | 639879 | 0 | 639879 | 69556.8 | 16000 | 554322.2 | On/Under Budget | Budget Allocated | 608708 | 608708 | 0 | 608708 | 0 | 627186.6 | 54142.4 | -13224 | 67366.4 | 0 | 212.4 | 9426.3 | 59918.1 | 8840.1 | 0 | 460 | 24347 | 10478 | 12273 | 25584 | 54142 | 227410 | 169027 | 2320 | 2320 | 75485 | 4860 | 2021-06-18 | 161784 | BL-0: | BL-0: 35137590_CWSP-ECOP-MIDDLETOWN 1101-OCB-H02_08W - Jun 21 | 2021-06-21 | 2021-04-06 | Completed | 2021-05-26 | 2021-06-02 | Completed | 2021-05-07 | Completed | 2021-06-02 | Completed | 2021-04-06 | 2021-06-24 | In Progress | 2021-06-25 | 2021-07-01 | Not Started | 2021-05-10 | 2021-05-17 | Completed | 2021-07-05 | Not Started |  |  |  |  | 2021-07-05 | Not Started | 2021-08-04 | Not Started | 2021-09-02 | Not Started | 2021-11-03 | 2021-11-03 | 0 | On/ Ahead Schedule | Not Started | 2021-11-04 | 2021-11-17 | Not Started | 2021-12-24 | Not Started
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | 5530164 | UNSC | 08W | [6 empty] | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 7437 | 0 | 7437 | 1.4085 | 1.4085 | 0 | 0 | 1.4085 | 7437 | 0 | 1.4085 | 0 |  | 1536846 | 506100 | 1030746 | 0 | 1030746 | 112687.2 | 16700 | 901358.8 | On/Under Budget | Budget Allocated | 1023712 | 1023712 | 0 | 1023712 | 0 | 1029586.2 | 103182.2 | -12334.6 | 115516.8 | 0 | 212.4 | 5661.5 | 106813.3 | 0 | 0 | 5214 | 28693 | 29172 | 28076 | 27993 | 103182 | 463860 | 308782 | 3049 | 1897 | 21897 | 1897 | 2021-06-18 | 161783 | BL-0: | BL-0: 35137593_CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07_08W - Jun 21 | 2021-06-21 | 2021-04-07 | Completed | 2021-05-26 | 2021-06-02 | Completed | 2021-04-13 | Completed | 2021-06-02 | Completed | 2021-04-06 | 2021-06-24 | In Progress | 2021-06-25 | 2021-06-29 | Not Started | 2021-05-10 | 2021-05-21 | Completed | 2021-07-01 | Not Started |  |  |  |  | 2021-07-01 | Not Started | 2021-08-16 | Not Started | 2021-09-07 | Not Started | 2021-11-08 | 2021-11-08 | 0 | On/ Ahead Schedule | Not Started | 2021-11-09 | 2021-11-22 | Not Started | 2021-12-29 | Not Started
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | 5530164 | UNSC | 08W | [6 empty] | 2021 | 2020 | SH | CLRLAKE | Humboldt Division Assets | 0 | 5341 | 0 | 5341 | 1.0116 | 1.0116 | 0 | 0 | 1.0116 | 5341 | 0 | 1.0116 | 0 |  | 1356094 | 477826 | 878268 | 0 | 878268 | 143370.6 | 11400 | 723497.4 | On/Under Budget | Budget Allocated | 855208 | 855208 | 0 | 855208 | 0 | 859053.8 | 53309.8 | 34999.4 | 18310.4 | 0 | 0 | 3845.7 | 139525 | 0 | 0 | 460 | 13540 | 47204 | 20838 | 22485 | 53310 | 357188 | 261024 | 1897 | 1897 | 72996 | 2371 | 2021-06-18 | 161785 | BL-0: | BL-0: 35137596_CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08_08W - Jun 21 | 2021-06-21 | 2021-03-22 | Completed | 2021-05-26 | 2021-06-02 | Completed | 2021-05-07 | Completed | 2021-06-02 | Completed | 2021-04-06 | 2021-06-24 | In Progress | 2021-06-25 | 2021-06-29 | Not Started | 2021-05-11 | 2021-05-14 | Completed | 2021-07-01 | Not Started |  |  |  |  | 2021-07-01 | Not Started | 2021-07-30 | Not Started | 2021-08-30 | Not Started | 2021-10-29 | 2021-10-29 | 0 | On/ Ahead Schedule | Not Started | 2021-11-01 | 2021-11-12 | Not Started | 2021-12-21 | Not Started
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | E.5014721.05 | 5786762 | UNSC | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 9325 | 0 | 9325 | 1.7661 | 0 | 0 | 0 | 1.7661 | [5 empty] | 3319922 | 771603.4 | 2548318.6 |  |  | 164753.1 | 43350.1 | 2340215.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -160256 | 160256 | -160256 | 160256 | 178494.3 | 147 | 0 | 147 | 0 | 235.3 | 325841 | -161323.1 | 12674.6 | 0 | 1992 | 2275 | 1902 | -168397 | 906 | 147 | 153 | 153 | 153 | 153 | 153 | 153 | 2021-06-18 | 160859 | BL-1: | BL-1: 35129307_CWSP - ORO FINO 1102 - LR2560 PH 1.5_08W - May 21 | 2021-05-18 | 2020-07-13 | Completed | 2020-07-28 | 2020-07-28 | Completed | 2020-08-11 | Completed | 2020-08-07 | Completed | 2020-07-27 | 2020-07-27 | Completed | 2022-05-27 | 2022-06-09 | Not Started | 2020-08-17 | 2020-11-06 | Completed | 2022-06-10 | Not Started |  |  |  |  | 2022-06-10 | Not Started | 2022-06-09 | Not Started | 2022-06-15 | Not Started | 2022-07-01 | 2022-07-15 | -14 | Behind Schedule | Not Started | 2022-07-18 | 2022-07-29 | Not Started | 2022-09-06 | Not Started
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | E.5014721.03 | 5786760 | UNSC | 08W | [6 empty] | Not in the WP | 2022 | SH | CHICO | North Valley Assets | 0 | 4373 | 0 | 4373 | 0.82822 | 0 | 0 | 0 | 0.82822 | [5 empty] | 1594611 | 394996.3 | 1199614.7 |  |  | 203282.8 | 0 | 996331.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 109630 | -109630 | 109630 | -109630 | 210334.7 | 83.4 | 0 | 83.4 | 0 | 235.3 | 94018 | 109029.5 | 6452.2 | 0 | 587 | 89684 | 1067 | 1059 | 16633 | 83 | 86 | 86 | 86 | 86 | 86 | 86 | 2021-06-18 | 160857 | BL-2: | BL-2: 35129305_CWSP - ORO FINO 1102 - LR2560 PH 1.3_08W - May 21 | 2021-05-18 | 2020-07-01 | Completed | 2020-07-28 | 2020-07-28 | Completed | 2020-07-07 | Completed | 2020-08-07 | Completed | 2020-07-29 | 2020-07-29 | Completed | 2022-07-22 | 2022-08-04 | Not Started | 2020-08-10 | 2020-10-05 | Completed | 2022-09-05 | Not Started |  |  |  |  | 2022-09-05 | Not Started | 2022-10-27 | Not Started | 2022-11-16 | Not Started | 2023-01-20 | 2023-02-03 | -14 | Behind Schedule | Not Started | 2023-02-06 | 2023-02-17 | Not Started | 2023-03-28 | Not Started
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | 5787047 | UNSC | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 2021 | -2021 | 2021 | -2021 | [10 empty] | 421 | 402 | 402 | 399 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226367 | BR-04-13-W (E) SUBSTATION/PATH PARB |  | 5786123 | UNSC | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 4619564.55 | 450304.55 | 4169260 |  |  | 909606.1 | 70021.6 | 3189632.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 1680862 | -1680862 | 1680862 | -1680862 | 1680862.3 | 56013.8 | 96960 | -40946.2 | 0 | 0 | 0 | 909606 | 0 | 0 | 2306 | 13 | 14291 | 42556 | 753479 | 56014 | 54102 | 9786 | 361155 | 363283 | 14066 | 9810
35212407 | FRRB - SILVERADO 2102 LR 636 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 3537.6 | 0 | 3537.6 | 0.67 | 0 | 0 | 0.67 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 137043 | -137043 | 137043 | -137043 | [10 empty] | 2082 | 2031 | 62669 | 2366 | 67895 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 9873.6 | 0 | 9873.6 | 1.87 | 0 | 0 | 1.87 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 382488 | -382488 | 382488 | -382488 | [10 empty] | 5801 | 5660 | 174902 | 6595 | 189530 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212409 | FRRB - SILVERADO 2104 LR 645 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 913275 | -913275 | 913275 | -913275 | [10 empty] | 0 | 0 | 407268 | 2349 | 503659 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212410 | FRRB - SILVERADO 2104 LR 708 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 3907.2 | 0 | 3907.2 | 0.74 | 0 | 0 | 0.74 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 151358 | -151358 | 151358 | -151358 | [10 empty] | 2295 | 2239 | 69212 | 2609 | 75003 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212411 | FRRB - SILVERADO 2104 LR 722 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 771210 | -771210 | 771210 | -771210 | [10 empty] | 0 | 0 | 343915 | 1983 | 425312 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 26136 | 0 | 26136 | 4.95 | 0 | 0 | 4.95 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1012471 | -1012471 | 1012471 | -1012471 | [10 empty] | 15362 | 14987 | 462982 | 17464 | 501676 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 10697.28 | 0 | 10697.28 | 2.026 | 0 | 0 | 2.026 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 414396 | -414396 | 414396 | -414396 | [10 empty] | 6285 | 6132 | 189493 | 7146 | 205339 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 2513.28 | 0 | 2513.28 | 0.476 | 0 | 0 | 0.476 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 97360 | -97360 | 97360 | -97360 | [10 empty] | 1476 | 1440 | 44520 | 1678 | 48245 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 12672 | 0 | 12672 | 2.4 | 0 | 0 | 2.4 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 490896 | -490896 | 490896 | -490896 | [10 empty] | 7450 | 7269 | 224478 | 8469 | 243230 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 7920 | 0 | 7920 | 1.5 | 0 | 0 | 1.5 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 306809 | -306809 | 306809 | -306809 | [10 empty] | 4654 | 4540 | 140296 | 5291 | 152028 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | 5793892 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | NAPA |  | 0 | 20856 | 0 | 20856 | 3.95 | 0 | 0 | 3.95 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 807932 | -807932 | 807932 | -807932 | [10 empty] | 12259 | 11961 | 369452 | 13937 | 400324 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | GYSRVLLE |  | 0 | 72336 | 0 | 72336 | 13.7 | 0 | 0 | 13.7 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1586503 | -1586503 | 1586503 | -1586503 | [10 empty] | 30934 | 30180 | 56805 | 30118 | 1438465 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 12355.2 | 0 | 12355.2 | 2.34 | 0 | 0 | 2.34 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 283177 | -283177 | 283177 | -283177 | [10 empty] | 2727 | 7944 | 14570 | 3672 | 254263 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212460 | FRRB - RINCON 1101 LR 14605 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 69854.4 | 0 | 69854.4 | 13.23 | 0 | 0 | 13.23 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1600567 | -1600567 | 1600567 | -1600567 | [10 empty] | 14501 | 44017 | 81483 | 19873 | 1440693 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212461 | FRRB - RINCON 1101 LR 663641 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 3115.2 | 0 | 3115.2 | 0.59 | 0 | 0 | 0.59 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 71442 | -71442 | 71442 | -71442 | [10 empty] | 771 | 2085 | 3755 | 1007 | 63824 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212462 | FRRB - RINCON 1103 LR 198 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 13728 | 0 | 13728 | 2.6 | 0 | 0 | 2.6 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 314499 | -314499 | 314499 | -314499 | [10 empty] | 2753 | 8556 | 15919 | 3812 | 283459 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212463 | FRRB - RINCON 1103 LR 474 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 87595.2 | 0 | 87595.2 | 16.59 | 0 | 0 | 16.59 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2007170 | -2007170 | 2007170 | -2007170 | [10 empty] | 18399 | 55405 | 102387 | 25128 | 1805851 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212464 | FRRB - CALISTOGA 1101 LR 886282 |  | 5793893 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 0 | 5016 | 0 | 5016 | 0.95 | 0 | 0 | 0.95 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 107074 | -107074 | 107074 | -107074 | [10 empty] | 0 | 0 | 0 | 0 | 107074 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212465 | FRRB-ACAVILLE1108 SETLLEMENT RULES ONLY |  | 5793894 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | VACAVLLE |  | 0 | 33475.2 | 0 | 33475.2 | 6.34 | 0 | 0 | 6.34 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 761877 | -761877 | 761877 | -761877 | [10 empty] | 24297 | 23705 | 58664 | 23737 | 631473 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | 5793894 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | VACAVLLE |  | 0 | 47203.2 | 0 | 47203.2 | 8.94 | 0 | 0 | 8.94 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1074318 | -1074318 | 1074318 | -1074318 | [10 empty] | 34261 | 33426 | 82722 | 33472 | 890437 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212467 | FRRB - LAURELES 1111 LR 2020 |  | 5793895 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | MONTEREY |  | 0 | 6441.6 | 0 | 6441.6 | 1.22 | 0 | 0 | 1.22 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 136342 | -136342 | 136342 | -136342 | [10 empty] | 17156 | 16738 | 6759 | 16560 | 79130 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 13411.2 | 0 | 13411.2 | 2.54 | 0 | 0 | 2.54 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 389344 | -389344 | 389344 | -389344 | [10 empty] | 18007 | 17568 | 111682 | 17985 | 224102 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 11668.8 | 0 | 11668.8 | 2.21 | 0 | 0 | 2.21 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 338760 | -338760 | 338760 | -338760 | [10 empty] | 15667 | 15286 | 97173 | 15853 | 194782 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 2745.6 | 0 | 2745.6 | 0.52 | 0 | 0 | 0.52 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 79708 | -79708 | 79708 | -79708 | [10 empty] | 3686 | 3597 | 22864 | 3682 | 45879 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212475 | FRRB - BIG BASIN 1101 CB |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 16315.2 | 0 | 16315.2 | 3.09 | 0 | 0 | 3.09 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 473651 | -473651 | 473651 | -473651 | [10 empty] | 21906 | 21372 | 135866 | 21879 | 272628 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 7233.6 | 0 | 7233.6 | 1.37 | 0 | 0 | 1.37 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 210001 | -210001 | 210001 | -210001 | [10 empty] | 9712 | 9476 | 60238 | 9701 | 120874 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | 5793896 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 3115.2 | 0 | 3115.2 | 0.59 | 0 | 0 | 0.59 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 109251 | -109251 | 109251 | -109251 | [10 empty] | 4183 | 4081 | 25942 | 4178 | 70868 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212478 | FRRB - SWIFT 2110 XR332 |  | 5793897 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | CINNABAR |  | 0 | 44616 | 0 | 44616 | 8.45 | 0 | 0 | 8.45 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1066220 | -1066220 | 1066220 | -1066220 | [10 empty] | 34153 | 33321 | -21926 | 32764 | 987908 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212479 | FRRB - BIG BEND 1102 CB |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | CHICO |  | 0 | 21331.2 | 0 | 21331.2 | 4.04 | 0 | 0 | 4.04 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1107178 | -1107178 | 1107178 | -1107178 | [10 empty] | 30264 | 361488 | 42845 | 326126 | 346456 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212480 | FRRB - BIG BEND 1102 LR1972 |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 21436.8 | 0 | 21436.8 | 4.06 | 0 | 0 | 4.06 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1112644 | -1112644 | 1112644 | -1112644 | [10 empty] | 30388 | 363252 | 43031 | 327714 | 348260 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 52377.6 | 0 | 52377.6 | 9.92 | 0 | 0 | 9.92 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2597135 | -2597135 | 2597135 | -2597135 | [10 empty] | -47030 | 887330 | 104919 | 800398 | 851518 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 42081.6 | 0 | 42081.6 | 7.97 | 0 | 0 | 7.97 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2184061 | -2184061 | 2184061 | -2184061 | [10 empty] | 59847 | 713273 | 84663 | 643287 | 682991 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212486 | FRRB - KANAKA 1101 CB |  | 5795419 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 16262.4 | 0 | 16262.4 | 3.08 | 0 | 0 | 3.08 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 854904 | -854904 | 3903049 | -3903049 | [10 empty] | 44533 | 296527 | 53602 | 269244 | 190998 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212487 | FRRB - KANAKA 1101 LR1034 |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 14150.4 | 0 | 14150.4 | 2.68 | 0 | 0 | 2.68 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 736132 | -736132 | 736132 | -736132 | [10 empty] | 23628 | 243264 | 31887 | 219629 | 217725 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212488 | FRRB - KANAKA 1101 LR1406 |  | 5793918 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OROVILLE |  | 0 | 47044.8 | 0 | 47044.8 | 8.91 | 0 | 0 | 8.91 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2445982 | -2445982 | 2445982 | -2445982 | [10 empty] | 75855 | 806128 | 103379 | 727571 | 733050 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212489 | FRRB - GIRVAN 1101 LR1330 |  | 5793919 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | REDDING |  | 0 | 16104 | 0 | 16104 | 3.05 | 0 | 0 | 3.05 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 871901 | -871901 | 871901 | -871901 | [10 empty] | 112 | 44734 | 130770 | 355704 | 340583 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212490 | FRRB - GIRVAN 1101 LR323094 |  | 5793919 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | REDDING |  | 0 | 28934.4 | 0 | 28934.4 | 5.48 | 0 | 0 | 5.48 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1566563 | -1566563 | 1566563 | -1566563 | [10 empty] | 198 | 80372 | 234955 | 639098 | 611940 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | 5793920 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | OAKHURST |  | 0 | 5068.8 | 0 | 5068.8 | 0.96 | 0 | 0 | 0.96 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 154224 | -154224 | 154224 | -154224 | [10 empty] | 9261 | 9036 | 9467 | 8973 | 117487 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212492 | FRRB - AUBERRY 1101 R2845 |  | 5793921 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | FRESNO |  | 0 | 10084.8 | 0 | 10084.8 | 1.91 | 0 | 0 | 1.91 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 231365 | -231365 | 231365 | -231365 | [10 empty] | 3341 | 2326 | 3339 | 3232 | 219128 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212493 | FRRB - AUBERRY 1101 R324 |  | 5793921 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | FRESNO |  | 0 | 34003.2 | 0 | 34003.2 | 6.44 | 0 | 0 | 6.44 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 728644 | -728644 | 728644 | -728644 | [10 empty] | 11042 | 7624 | 11038 | 10679 | 688261 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212494 | FRRB - AUBERRY 1101 LR37536 |  | 5793921 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | FRESNO |  | 0 | 13833.6 | 0 | 13833.6 | 2.62 | 0 | 0 | 2.62 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 296368 | -296368 | 296368 | -296368 | [10 empty] | 4359 | 2972 | 4361 | 4216 | 280459 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212495 | FRRB - AUBERRY 1101 LR233716 |  | 5793921 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | FRESNO |  | 0 | 45672 | 0 | 45672 | 8.65 | 0 | 0 | 8.65 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 978639 | -978639 | 978639 | -978639 | [10 empty] | 14730 | 10142 | 14727 | 14246 | 924795 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212496 | FRRB - HB TRINITY COUNTY |  | 5793922 | UNSC | 08W | [6 empty] | Not in the WP |  | FRRB | FORTUNA |  | 0 | 11932.8 | 0 | 11932.8 | 2.26 | 0 | 0 | 2.26 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 346084 | -346084 | 346084 | -346084 | [10 empty] | 14971 | 14606 | 27607 | 18840 | 270060 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174085 | PSPS - FROGTOWN 1702 - LR 36870 |  | 5530176 | UNSC | 08W | [6 empty] | 2022 | 2021 | SH | ANGLSCMP | Stockton Assets | 0 | 503 | 0 | 503 | 0.095265 | 0.095265 | 0 | 0 | 0.095265 | 503 | 503 | 0.095265 | 0.095265 |  | 63132.37 | 63132.37 | 0 |  |  | 51460.8 | 31324.7 | -82785.5 | OverRun | Request 2021 Budget | 0 | 161030 | -161030 | 156975 | -156975 | 173515.6 | 19778.3 | 28663.9 | -8885.6 | 0 | 0 | 16540.3 | 34920.5 | 0 | 0 | 3800 | 0 | 0 | 1144 | 1313 | 130747 | 22020 | 1115 | 892 | 0 | 0 | 0 | 2021-06-18 | 161714 | BL-0 | BL-0 35174085_PSPS - FROGTOWN - 1702 - LR 36870_08W - DD 210406 | 2021-06-17 | 2020-09-02 | Completed | 2021-04-29 | 2021-06-09 | Completed | 2021-05-25 | Completed | 2021-06-11 | Completed | [6 empty] | 2021-02-01 | 2021-02-12 | Completed | 2021-06-22 | Not Started |  |  |  |  | 2021-06-22 | Not Started | 2021-09-20 | Not Started | 2021-10-19 | Not Started | 2022-01-10 | 2021-12-20 | 21 | On/ Ahead Schedule | Not Started | 2021-12-21 | 2022-01-03 | Not Started | 2022-02-09 | Not Started
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 | E.5014743.01 | 5782833 | UNSC | 08W | [6 empty] | Not in the WP | 2019 | SH | STROSA | Sonoma Assets | 0 | 25170 | 0 | 25170 | 4.767 | 0 | 0 | 4.767 | 0 | [5 empty] | 6996439 | 0 | 6996439 |  |  | 20427027.3 | 0 | -13430588.3 | OverRun | Project is not in the WP or in 2020 WP | 0 | 48773 | -48773 | 48773 | -48773 | 20709018.6 | 6943.8 | 297.8 | 6646 | 525900.5 | 21564746 | -1430401.1 | -233218.1 | 0 | 0 | 1094 | -261851 | 17556 | 5602 | 4085 | 6944 | 0 | 0 | 0 | 93782 | 93782 | 87782 | 2021-06-18 |  |  |  |  | 2019-05-06 | Completed | 2019-01-11 | 2019-02-08 | Completed | 2019-02-06 | Completed | 2019-04-10 | Completed | 2019-04-01 | 2019-04-01 | Completed | 2019-04-01 | 2019-04-11 | Completed | 2019-04-11 | 2019-12-06 | Completed | 2019-04-11 | Completed |  |  |  |  | 2019-04-11 | Completed | 2019-10-07 | Completed | 2019-10-07 | Completed | 2021-01-22 | 2019-10-07 | 473 | On/ Ahead Schedule | Completed | 2019-10-08 | 2019-10-22 | Completed | 2022-03-21 | Not Started
35240545 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | E.5034825.01.89 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 769 | 0 | 0 | 769 | 0.14564 | 0.14564 | 0 | 0 | 0.14564 | 769 | 0 | 0.14564 | 0 |  | 2561702 | 1408230 | 1153472 | 768290 | 385182 | 17793 | 4279.9 | 1131399.1 | On/Under Budget | Budget Allocated | 1153472.39 | 391980 | 761492.39 | 391980 | 761492.39 | 391979.9 | 88.6 | -4082.7 | 4171.3 | 0 | 0 | 0 | 17793 | 0 | 0 | 0 | 0 | 0 | 797 | 21079 | 89 | 100089 | 100089 | 169837 | 0 | 0 | 0 | 2021-05-21 | 159026 | BL-A_ | BL-A_35240545_FRRB - WYANDOTTE 1103 - W2 PH 2.12 - B1_Apr 21 | 2021-04-09 | 2021-05-05 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-05-26 | Not Started | 2021-05-26 | Not Started | [6 empty] | 2021-05-28 | 2021-06-03 | Not Started | 2021-06-04 | Not Started | 2021-06-04 | Not Started | 2021-08-20 | Not Started | 2021-06-04 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-10-21 | 2021-10-05 | 16 | On/ Ahead Schedule | Not Started | 2021-10-05 | 2021-10-19 | Not Started | 2021-12-02 | Not Started
35248294 | BR-09-01-W (E) SKYWAY PH3.5 20A PARB |  | 5786123 | UNSC | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | E.5034825.01.21 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4247 | 0 | 0 | 4247 | 0.80436 | 0.80436 | 0 | 0 | 0.80436 | 4247 | 0 | 0.80436 | 0 |  | 6429020 | 2300730 | 4128290 | 768290 | 3360000 | 53682.8 | 15061.8 | 4059545.4 | On/Under Budget | Budget Allocated | 4128290 | 3392156 | 736134 | 3392156 | 736134 | 3392155.4 | 91.9 | 5629.2 | -5537.3 | 0 | 0 | 0 | 53682.8 | 0 | 0 | 0 | 0 | 573 | 1041 | 46439 | 92 | 343871 | 1000093 | 1000046 | 1000000 | 0 | 0 | 2021-05-21 | 159004 | BL-A_ | BL-A_35233315_FRRB - WYANDOTTE 1103 - W2 PH 2.5 - B1_Apr 21 | 2021-04-09 | 2021-04-22 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-15 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-19 | Not Started | 2021-07-19 | Not Started | 2021-10-04 | Not Started | 2021-07-19 | Not Started | 2021-10-18 | Not Started | 2021-10-18 | Not Started | 2021-11-17 | 2021-11-17 | 0 | On/ Ahead Schedule | Not Started | 2021-11-17 | 2021-12-01 | Not Started | 2022-01-14 | Not Started
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | E.5034825.01.03 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2414 | 0 | 0 | 2414 | 0.4572 | 0.4572 | 0 | 0 | 0.4572 | 2414 | 0 | 0.4572 | 0 |  | 4335155 | 1816866 | 2518289 | 768290 | 1749999 | 80358.9 | 14114.9 | 2423815.2 | On/Under Budget | Budget Allocated | 2518289.22 | 1798361 | 719928.22 | 1798361 | 719928.22 | 1798360.7 | 86.1 | 5365.9 | -5279.8 | 0 | 0 | 0 | 80358.9 | 0 | 0 | 0 | 2879 | 7372 | 12279 | 52463 | 86 | 500087 | 500044 | 723151 | 0 | 0 | 0 | 2021-06-11 | 158998 | BL-A_ | BL-A_35232718_FRRB - WYANDOTTE 1103 - W2 PH 2.1 - B1_Apr 21 | 2021-04-09 | 2021-04-19 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-06-11 | Not Started | 2021-06-11 | Not Started | [6 empty] | 2021-06-15 | 2021-07-15 | Not Started | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-07-29 | Not Started | 2021-09-24 | Not Started | 2021-09-30 | Not Started | 2021-09-30 | Not Started | 2021-09-22 | 2021-11-01 | -40 | Behind Schedule | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-29 | Not Started
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | E.5034692.01.03 | 5794540 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | CONCORD | Diablo Assets | 0 | 5813 | 0 | 5813 | 1.1009 | 1.1009 | 0 | 0 | 1.1009 | 5813 | 0 | 1.1009 | 0 |  | 565748.51 | -1137395.49 | 1703144 |  |  | 71890.3 | 89990 | 1541263.7 | On/Under Budget | Request 2021 Budget | 0 | 1555956 | -1555956 | 1553290 | -1553290 | 1553289.8 | 111364.4 | 43251.7 | 68112.7 | 0 | 0 | 0 | 71890.3 | 0 | 0 | 0 | 463 | 1198 | 15682 | 11295 | 138410 | 538750 | 430877 | 405372 | 9716 | 4192 | 0 | 2021-06-18 | 160974 | BL-B: | BL-B: 35231544_CWSP - TIDEWATER 210614072 Ph3_08W - May 21 | 2021-05-20 | 2021-04-27 | Completed | 2021-06-18 | 2021-06-24 | Not Started | 2021-06-18 | Not Started | 2021-07-08 | Not Started | 2021-06-04 | 2021-06-04 | Completed | 2021-06-18 | 2021-07-08 | Not Started | 2021-06-18 | 2021-06-18 | Not Started | 2021-07-19 | Not Started |  |  |  |  | 2021-07-19 | Not Started | 2021-09-03 | Not Started | 2021-09-10 | Not Started | 2021-11-01 | 2021-11-11 | -10 | Behind Schedule | Not Started | 2021-11-12 | 2021-11-25 | Not Started | 2022-01-10 | Not Started
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | E.5034804.01.11 | 5795299 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 7441 | 0 | 7441 | 1.4093 | 1.4093 | 0 | 0 | 1.4093 | 7441 | 0 | 1.4093 | 0 |  | 3032237 | 836555 | 2195682 | 0 | 2195682 | 327817.3 | 92481.6 | 1775383.1 | On/Under Budget | Budget Allocated | 1974000 | 1993505 | -19505 | 1993505 | -19505 | 1993505.3 | 631026.7 | 237228.1 | 393798.6 | 0 | 0 | 0 | 327817.4 | 0 | 0 | 0 | 1475 | 6648 | 82293 | 173 | 631027 | 426517 | 384081 | 59245 | 10795 | 156343 | 234907 | 2021-06-18 | 160986 | BL-0_ | BL-0_35231607_CWSP - SHINGLE SPRINGS 2109-LR9372-PH1.4_08W_May.2021 | 2021-05-21 | 2021-04-22 | Completed | 2021-04-23 | 2021-05-03 | Completed | 2021-06-03 | Completed | 2021-05-14 | Completed | 2021-05-14 | 2021-05-14 | Completed | 2021-06-02 | 2021-06-02 | Completed | 2021-06-03 | 2021-07-02 | In Progress | 2021-06-22 | Not Started |  |  |  |  | 2021-06-22 | Not Started | 2021-08-30 | Not Started | 2021-09-06 | Not Started | 2021-12-30 | 2021-11-22 | 38 | On/ Ahead Schedule | Not Started | 2021-11-23 | 2021-12-06 | Not Started | 2022-01-19 | Not Started
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | E.5034804.01.08 | 5795299 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 13889 | 356 | 14245 | 2.6979 | 2.6979 | 0 | 0 | 2.6979 | 13889 | 0 | 2.6305 | 0 |  | 5538787 | 1429363.7 | 4109423.3 | 777316 | 3332107.3 | 217725.8 | 112144.8 | 3779552.7 | On/Under Budget | Budget Allocated | 3709152 | 3731538 | -22386 | 3731538 | -22386 | 3743110.7 | 60231.5 | 2342.4 | 57889.1 | 0 | 0 | 0 | 217725.8 | 11573 | 0 | 0 | 11683 | 55357 | 98985 | 49358 | 60232 | 1645043 | 756896 | 613515 | 20424 | 24084 | 395962 | 2021-06-18 | 161003 | BL-0_ | BL-0_35226853_CWSP - SHINGLE SPRINGS 2109-LR 9372PH3.3_08W_May.2021 | 2021-05-21 | 2021-04-30 | Completed | 2021-05-06 | 2021-05-07 | Completed | 2021-06-17 | Completed | 2021-06-17 | Completed | 2021-06-17 | 2021-07-14 | In Progress | 2021-07-15 | 2021-07-28 | Not Started | 2021-06-28 | 2021-07-22 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-08-19 | Not Started | 2021-07-30 | Not Started | 2021-10-14 | Not Started | 2021-11-12 | Not Started | 2021-12-31 | 2021-12-30 | 1 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-13 | Not Started | 2022-02-28 | Not Started
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | E.5034803.01.01 | 5795298 | UNSC | 08W | [6 empty] | 2021 |  | SH | PLCRVLLE | Sierra Assets | 0 | 9829 | 0 | 9829 | 1.8616 | 1.8616 | 0 | 0 | 1.8616 | 9829 | 0 | 1.8616 | 0 |  | 1101405.78 | -1417881.32 | 2519287.1 |  |  | 126203.4 | 951264.6 | 1441819.1 | On/Under Budget | Budget Allocated | 2519287 | 2245396 | 273891 | 2245396 | 273891 | 2037206.2 | 431802.1 | 1437.9 | 430364.2 | 0 | 0 | 0 | 126203.4 | -208190 | 0 | 0 | 7535 | 50065 | 43428 | 23737 | 431802 | 818102 | 706912 | 94307 | 51093 | 11471 | 6944 | 2021-06-18 | 161088 | BL-0 | BL-0 35226845_ECOP -DIAMOND SPRINGS 1107-H02-LR1402PH2_08W - DD 210521 | 2021-05-26 | 2021-04-29 | Completed | 2021-05-10 | 2021-05-20 | Completed | 2021-05-17 | Completed | 2021-05-26 | Completed | 2021-06-21 | 2021-06-21 | Not Started | 2021-06-22 | 2021-07-02 | Not Started | 2021-06-14 | 2021-06-25 | In Progress | 2021-07-06 | Not Started | 2021-07-06 | Not Started | 2021-07-19 | Not Started | 2021-07-06 | Not Started | 2021-09-20 | Not Started | 2021-09-14 | Not Started | 2021-11-11 | 2021-11-11 | 0 | On/ Ahead Schedule | Not Started | 2021-11-12 | 2021-11-25 | Not Started | 2022-01-10 | Not Started
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | E.5034804.01.10 | 5795299 | UNSC | 08W | [6 empty] | 2021 | 2021 | SH | PLCRVLLE | Sierra Assets | 0 | 5775 | 0 | 5775 | 1.0938 | 1.0938 | 0 | 0 | 1.0938 | 5771 | 0 | 1.093 | 0 |  | 2418866 | 604877.4 | 1813988.6 | 340400 | 1473588.6 | 128574.1 | 126952.8 | 1558461.7 | On/Under Budget | Budget Allocated | 1640040 | 1659792 | -19752 | 1659792 | -19752 | 1663530.7 | 87037.5 | 2542.3 | 84495.2 | 0 | 0 | 0 | 128574.1 | 3738.8 | 0 | 0 | 3865 | 15951 | 34587 | 71630 | 87038 | 597683 | 331493 | 323935 | 7499 | 2995 | 183118 | 2021-06-18 | 161013 | BL-0_ | BL-0_35226856_CWSP - SHINGLE SPRINGS 2109-LR 9372PH3.5_08W_May.2021 | 2021-05-21 | 2021-04-26 | Completed | 2021-04-29 | 2021-05-20 | Completed | 2021-06-17 | Completed | 2021-06-16 | Completed | 2021-06-17 | 2021-06-17 | Completed | 2021-06-17 | 2021-07-02 | In Progress | 2021-06-21 | 2021-07-19 | Not Started | 2021-07-15 | Not Started |  |  |  |  | 2021-07-15 | Not Started | 2021-09-30 | Not Started | 2021-10-07 | Not Started | 2021-12-06 | 2022-01-07 | -32 | Behind Schedule | Not Started | 2022-01-10 | 2022-01-21 | Not Started | 2022-03-08 | Not Started
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | E.5034695.01.02 | 5794546 | UNSC | 08W | [6 empty] | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 12501 | 0 | 12501 | 2.3676 | 2.3676 | 0 | 0 | 2.3676 | 12501 | 0 | 2.3676 | 0 |  | 955916.43 | 680916.43 | 275000 |  |  | 149430.2 | 164531.1 | -38961.3 | OverRun | Request 2021 Budget | 0 | 2667836 | -2667836 | 2667836 | -2667836 | 2667836.5 | 144151.9 | 19543.8 | 124608.1 | 0 | 0 | 0 | 149430 | 0 | 0 | 0 | 692 | 29669 | 90653 | 8873 | 144152 | 906023 | 672812 | 626869 | 101987 | 59874 | 26234 | 2021-06-18 | 161065 | BL-0 | BL-0 35227260_CWSP - COARSEGOLD 2104CB PH 2_08W - DD 210521 | 2021-05-25 | 2021-04-16 | Completed | 2021-05-26 | 2021-06-03 | Completed | 2021-05-26 | Completed | 2021-06-16 | Completed | 2021-06-21 | 2021-06-21 | Not Started | 2021-06-22 | 2021-07-12 | Not Started | 2021-06-07 | 2021-06-18 | Completed | 2021-07-14 | Not Started |  |  |  |  | 2021-07-14 | Not Started | 2021-09-21 | Not Started | 2021-09-22 | Not Started | 2021-12-07 | 2021-11-29 | 8 | On/ Ahead Schedule | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-26 | Not Started
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | E.5034695.01.03 | 5794546 | UNSC | 08W | [6 empty] | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 9130 | 0 | 9130 | 1.7292 | 1.7292 | 0 | 0 | 1.7292 | 9130 | 0 | 1.7292 | 0 |  | 747358.84 | 497358.84 | 250000 |  |  | 131958.2 | 0 | 118041.8 | On/Under Budget | Request 2021 Budget | 0 | 2520324 | -2520324 | 2520324 | -2520324 | 2520324.3 | 479469.1 | 40920.9 | 438548.2 | 0 | 0 | 0 | 131958.1 | 0 | 0 | 0 | 13053 | 48463 | 23538 | 5983 | 479469 | 614387 | 692558 | 402132 | 121082 | 96145 | 23514 | 2021-06-18 | 161067 | BL-0 | BL-0 35227261_CWSP - COARSEGOLD 2104CB PH 3_08W - DD 210521 | 2021-05-25 | 2021-04-11 | Completed | 2021-05-26 | 2021-06-03 | Completed | 2021-05-17 | Completed | 2021-06-16 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-23 | Not Started | 2021-05-24 | 2021-06-04 | Completed | 2021-07-27 | Not Started |  |  |  |  | 2021-07-27 | Not Started | 2021-09-13 | Not Started | 2021-09-14 | Not Started | 2021-11-05 | 2021-11-19 | -14 | Behind Schedule | Not Started | 2021-11-22 | 2021-12-03 | Not Started | 2022-01-18 | Not Started
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | E.5034695.01.04 | 5794546 | UNSC | 08W | [6 empty] | 2021 |  | SH | OAKHURST | Yosemite Assets | 0 | 9162 | 0 | 9162 | 1.7352 | 1.7352 | 0 | 0 | 1.7352 | 9162 | 0 | 1.7352 | 0 |  | 886518.78 | 736518.78 | 150000 |  |  | 142614.1 | 0 | 7385.9 | On/Under Budget | Request 2021 Budget | 0 | 2838596 | -2838596 | 2838596 | -2838596 | 2838596.3 | 447213.4 | 26139.1 | 421074.3 | 0 | 0 | 0 | 142614.1 | 0 | 0 | 0 | 13137 | 58190 | 7632 | 37516 | 447213 | 752267 | 650800 | 795261 | 49888 | 12806 | 13888 | 2021-06-18 | 161068 | BL-0 | BL-0 35227262_CWSP - COARSEGOLD 2104CB PH 4_08W - DD 210521 | 2021-05-25 | 2021-03-31 | Completed | 2021-05-24 | 2021-06-03 | Completed | 2021-05-10 | Completed | 2021-06-16 | Completed | 2021-06-21 | 2021-06-25 | Not Started | 2021-06-28 | 2021-07-16 | Not Started | 2021-05-17 | 2021-05-31 | Completed | 2021-07-20 | Not Started |  |  |  |  | 2021-07-20 | Not Started | 2021-09-20 | Not Started | 2021-09-21 | Not Started | 2021-11-22 | 2021-11-26 | -4 | Behind Schedule | Not Started | 2021-11-29 | 2021-12-10 | Not Started | 2022-01-25 | Not Started
35239522 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | E.5034825.01.71 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1840 | 0 | 0 | 1840 | 0.34848 | 0.34848 | 0 | 0 | 0.34848 | 1840 | 0 | 0.34848 | 0 |  | 3198520 | 1555230 | 1643290 | 768290 | 875000 | 27015.5 | 13003.8 | 1603270.7 | On/Under Budget | Budget Allocated | 1643290 | 902860 | 740430 | 902860 | 740430 | 902859.6 | 88.7 | -15934.7 | 16023.4 | 0 | 0 | 0 | 27015.4 | 0 | 0 | 0 | 0 | 0 | 809 | 42141 | 89 | 186687 | 273090 | 200045 | 200000 | 0 | 0 | 2021-05-21 | 159041 | BL-A_ | BL-A_35239522_FRRB - WYANDOTTE 1103 - W2 PH 2.9 - B1_Apr 21 | 2021-04-09 | 2021-05-05 | Completed | 2021-03-19 | 2021-04-12 | Completed | 2021-05-21 | Not Started | 2021-05-21 | Not Started | [6 empty] | 2021-05-25 | 2021-05-31 | Not Started | 2021-06-01 | Not Started | 2021-06-01 | Not Started | 2021-08-17 | Not Started | 2021-06-01 | Not Started | 2021-08-31 | Not Started | 2021-08-31 | Not Started | 2021-09-20 | 2021-09-30 | -10 | Behind Schedule | Not Started | 2021-09-30 | 2021-10-14 | Not Started | 2021-11-29 | Not Started
35235701 | FRRB - KANAKA 1101 - K2 PH2.1 | E.5034572.01.38 | 5793918 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 576 | 0 | 576 | 0.10909 | 0.10909 | 0 | 0 | 0.10909 | 576 | 0 | 0.10909 | 0 |  | 400000 | 0 | 400000 |  |  | 4008.7 | 0 | 395991.3 | On/Under Budget | Budget Allocated | 207273 | 299057 | -91784 | 9085 | 198188 | 9085.1 | 6000 | 923.6 | 5076.4 | 0 | 0 | 0 | 4008.7 | 0 | 0 | 0 | 0 | 0 | 750 | 2335 | 1157 | 37444 | 148495 | 107719 | 1157 | 0 | 0 | 2021-04-05 |  |  |  |  | 2021-04-29 | Not Started | 2021-05-14 | 2021-05-20 | Not Started | 2021-05-13 | Not Started | 2021-06-24 | Not Started | [6 empty] | 2021-04-28 | 2021-05-04 | Not Started | 2021-06-28 | Not Started | 2021-06-28 | Not Started | 2021-09-13 | Not Started | 2021-06-28 | Not Started | 2021-09-27 | Not Started | 2021-09-27 | Not Started | 2021-10-27 | 2021-10-27 | 0 | On/ Ahead Schedule | Not Started | 2021-10-27 | 2021-11-10 | Not Started | 2021-12-24 | Not Started
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | E.5034825.01.40 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 9182 | 0 | 0 | 9182 | 1.739 | 1.739 | 0 | 0 | 1.739 | 9182 | 0 | 1.739 | 0 |  | 8067020 | 2678730 | 5388290 | 768290 | 4620000 | 169422 | 33456.6 | 5185411.4 | On/Under Budget | Budget Allocated | 5388290 | 4647955 | 740335 | 4647955 | 740335 | 4647955.1 | 99.3 | 123746.8 | -123647.5 | 0 | 0 | 0 | 169422 | 0 | 0 | 0 | 0 | 229 | 3202 | 42244 | 99 | 1000100 | 1000100 | 1000100 | 1000050 | 601830 | 0 | 2021-05-21 | 159005 | BL-A_ | BL-A_35235705_FRRB - WYANDOTTE 1103 - W2 PH 2.6 - B1_Apr 21 | 2021-04-09 | 2021-05-31 | Not Started | 2021-03-19 | 2021-04-12 | Completed | 2021-07-01 | Not Started | 2021-07-26 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-28 | Not Started | 2021-07-28 | Not Started | 2021-10-13 | Not Started | 2021-07-28 | Not Started | 2021-10-27 | Not Started | 2021-10-27 | Not Started | 2021-11-17 | 2021-11-26 | -9 | Behind Schedule | Not Started | 2021-11-26 | 2021-12-10 | Not Started | 2022-01-25 | Not Started
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | E.5034825.01.05 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2771 | 0 | 0 | 2771 | 0.52481 | 0.52481 | 0 | 0 | 0.52481 | 2771 | 0 | 0.52481 | 0 |  | 3118378 | 1536736 | 1581642 | 768290 | 813352 | 91338.7 | 911837.5 | 578465.8 | On/Under Budget | Budget Allocated | 3163284 | 1581639 | 1581645 | 1532914 | 1630370 | 1532913.5 | 557609.4 | 376.2 | 557233.2 | 0 | 0 | 0 | 91338.7 | 0 | 0 | 0 | 0 | 809 | 75004 | 15150 | 566681 | 361205 | 131834 | 0 | 430957 | 0 | 0 | 2021-05-31 | 158210 | BL-A | BL-A 35233038_FRRB - WYANDOTTE 1103 - W1 PH 1.2 - Mar. 2021 | 2021-03-31 | 2021-04-14 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-04 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-06-14 | Not Started | 2021-06-14 | Not Started | 2021-07-06 | Not Started | 2021-08-02 | Not Started | 2021-08-05 | Not Started | 2021-08-05 | Not Started | 2021-08-27 | 2021-09-06 | -10 | Behind Schedule | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-11-03 | Not Started
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | E.5034825.01.06 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2446 | 0 | 0 | 2446 | 0.46326 | 0.46326 | 0 | 0 | 0.46326 | 2446 | 0 | 0.46326 | 0 |  | 3729353 | 1677730 | 2051623 | 768290 | 1283333 | 61803.9 | 2222 | 1987597.1 | On/Under Budget | Budget Allocated | 4103246 | 2051624 | 2051622 | 1880348 | 2222898 | 1880347.9 | 934.4 | 427 | 507.4 | 0 | 0 | 0 | 61803.8 | 0 | 0 | 0 | 0 | 229 | 1791 | 59357 | 3053 | 51343 | 904817 | 259695 | 771339 | 0 | 0 | 2021-05-31 | 158209 | BL-A | BL-A 35233039_FRRB - WYANDOTTE 1103 - W1 PH 1.3 - Mar. 2021 | 2021-03-31 | 2021-04-23 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-09 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-09-15 | Not Started | 2021-10-01 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-08-27 | 2021-11-05 | -70 | Behind Schedule | Not Started | 2021-11-08 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | E.5034825.01.07 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2000 | 0 | 0 | 2000 | 0.37879 | 0.37879 | 0 | 0 | 0.37879 | 2000 | 0 | 0.37879 | 0 |  | 3535462 | 1632986 | 1902476 | 768290 | 1134186 | 62808.5 | 628163 | 1211504.5 | On/Under Budget | Budget Allocated | 1902476 | 1902477 | -1 | 1468595 | 433881 | 1468594.7 | 934.4 | 191.8 | 742.6 | 0 | 0 | 0 | 62808.4 | 0 | 0 | 0 | 0 | 229 | 1877 | 60511 | 3061 | 688518 | 2254 | 188869 | 188869 | 768290 | 0 | 2021-05-31 | 158208 | BL-A | BL-A 35233300_FRRB - WYANDOTTE 1103 - W1 PH 1.4 - Mar. 2021 | 2021-03-31 | 2021-04-28 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-08 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-07-16 | Not Started | 2021-07-16 | Not Started | 2021-07-30 | Not Started | 2021-08-13 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-27 | 2021-09-16 | -20 | Behind Schedule | Not Started | 2021-09-17 | 2021-09-30 | Not Started | 2021-11-15 | Not Started
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | E.5034825.01.08 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 754 | 0 | 0 | 754 | 0.1428 | 0.1428 | 0 | 0 | 0.1428 | 754 | 0 | 0.1428 | 0 |  | 3715565 | 1674548 | 2041017 | 768290 | 1272727 | 37110.4 | 2222 | 2001684.6 | On/Under Budget | Budget Allocated | 2041017 | 2041018 | -1 | 1296287 | 744730 | 1296286.8 | 934.4 | 94.6 | 839.8 | 0 | 0 | 0 | 37110.4 | 0 | 0 | 0 | 0 | 229 | 1788 | 34999 | 2907 | 399763 | 2627 | 415865 | 414550 | 768290 | 0 | 2021-05-31 | 158207 | BL-A | BL-A 35233301_FRRB - WYANDOTTE 1103 - W1 PH 1.5 - Mar. 2021 | 2021-03-31 | 2021-04-28 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-06-01 | Not Started | 2021-06-10 | Not Started | [6 empty] | 2021-06-03 | 2021-06-09 | Not Started | 2021-08-20 | Not Started | 2021-08-20 | Not Started | 2021-08-30 | Not Started | 2021-09-15 | Not Started | 2021-09-17 | Not Started | 2021-09-17 | Not Started | 2021-08-27 | 2021-10-19 | -53 | Behind Schedule | Not Started | 2021-10-20 | 2021-11-02 | Not Started | 2021-12-16 | Not Started
35233302 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | E.5034825.01.09 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 798 | 0 | 0 | 798 | 0.15114 | 0.15114 | 0 | 0 | 0.15114 | 798 | 0 | 0.15114 | 0 |  | 2622014 | 1422190 | 1199824 | 768290 | 431534 | 34947.8 | 2222 | 1162654.2 | On/Under Budget | Budget Allocated | 1199824 | 1199824 | 0 | 612901 | 586923 | 612901.2 | 934.4 | 94.6 | 839.8 | 0 | 0 | 0 | 34947.8 | 0 | 0 | 0 | 0 | 0 | 27849 | 7004 | 2894 | 27514 | 395712 | 2752 | 736098 | 0 | 0 | 2021-05-31 | 158206 | BL-A | BL-A 35233302_FRRB - WYANDOTTE 1103 - W1 PH 1.6 - Mar. 2021 | 2021-03-31 | 2021-04-06 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-09 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-09-22 | Not Started | 2021-09-22 | Not Started | 2021-09-30 | Not Started | 2021-10-06 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-08-20 | 2021-11-09 | -81 | Behind Schedule | Not Started | 2021-11-10 | 2021-11-23 | Not Started | 2022-01-06 | Not Started
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | E.5034825.01.10 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 396 | 0 | 0 | 396 | 0.075 | 0.075 | 0 | 0 | 0.075 | 396 | 0 | 0.075 | 0 |  | 2470520 | 1387230 | 1083290 | 768290 | 315000 | 37554.3 | 159419.6 | 886316.1 | On/Under Budget | Budget Allocated | 1083290 | 1083290 | 0 | 521912 | 561378 | 521911.7 | 1130 | 59.8 | 1070.2 | 0 | 0 | 0 | 37554.4 | 0 | 0 | 0 | 0 | 229 | 19160 | 18105 | 3441 | 210596 | 750 | 62719 | 768290 | 0 | 0 | 2021-05-31 | 158223 | BL-A | BL-A 35233303_FRRB - WYANDOTTE 1103 - W1 PH 1.7 - Mar. 2021 | 2021-03-31 | 2021-04-14 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-08 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-07-26 | Not Started | 2021-07-26 | Not Started | 2021-07-30 | Not Started | 2021-08-12 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | Not Started | 2021-08-27 | 2021-09-14 | -18 | Behind Schedule | Not Started | 2021-09-14 | 2021-09-28 | Not Started | 2021-11-11 | Not Started
35233304 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | E.5034825.01.11 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2023 | 0 | 0 | 2023 | 0.38314 | 0.38314 | 0 | 0 | 0.38314 | 2023 | 0 | 0.38314 | 0 |  | 3444978 | 1612105 | 1832873 | 768290 | 1064583 | 57740.9 | 10781.9 | 1764350.2 | On/Under Budget | Budget Allocated | 1832873 | 1832872 | 1 | 1749562 | 83311 | 1749561.4 | 934.4 | 122.5 | 811.9 | 0 | 0 | 0 | 57741 | 0 | 0 | 0 | 0 | 0 | 27465 | 30154 | 3031 | 947111 | 6025 | 26905 | 792182 | 0 | 0 | 2021-05-31 | 158205 | BL-A | BL-A 35233304_FRRB - WYANDOTTE 1103 - W1 PH 1.8 - Mar. 2021 | 2021-03-31 | 2021-04-27 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-04 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-08-20 | Not Started | 2021-08-30 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-08-27 | 2021-10-01 | -35 | Behind Schedule | Not Started | 2021-10-04 | 2021-10-15 | Not Started | 2021-11-30 | Not Started
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | E.5034825.01.12 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3273 | 0 | 0 | 3273 | 0.61989 | 0.61989 | 0 | 0 | 0.61989 | 3273 | 0 | 0.61989 | 0 |  | 3378623 | 1596792 | 1781831 | 768290 | 1013541 | 87848.2 | 1111 | 1692871.8 | On/Under Budget | Budget Allocated | 1781831 | 1781831 | 0 | 1944884 | -163053 | 1944883.5 | 934.4 | 187.7 | 746.7 | 0 | 0 | 0 | 87848.3 | 0 | 0 | 0 | 0 | 573 | 76836 | 10251 | 3211 | 6794 | 1256768 | 4048 | 423350 | 0 | 0 | 2021-05-31 | 158204 | BL-A | BL-A 35233305_FRRB - WYANDOTTE 1103 - W1 PH 1.9 - Mar. 2021 | 2021-03-31 | 2021-04-14 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-09 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-07-30 | Not Started | 2021-07-30 | Not Started | 2021-08-30 | Not Started | 2021-09-09 | Not Started | 2021-09-15 | Not Started | 2021-09-15 | Not Started | 2021-08-27 | 2021-10-15 | -49 | Behind Schedule | Not Started | 2021-10-18 | 2021-10-29 | Not Started | 2021-12-14 | Not Started
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | E.5034825.01.13 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1869 | 0 | 0 | 1869 | 0.35398 | 0.35398 | 0 | 0 | 0.35398 | 1869 | 0 | 0.35398 | 0 |  | 3246777 | 1566366 | 1680411 | 768290 | 912121 | 57982.3 | 14114.9 | 1608313.8 | On/Under Budget | Budget Allocated | 1680411 | 1680409 | 2 | 1138177 | 542234 | 1138176.4 | 965.3 | 222.5 | 742.8 | 0 | 0 | 0 | 57982.4 | 0 | 0 | 0 | 0 | 229 | 28232 | 29299 | 3032 | 6614 | 893661 | 5744 | 713599 | 0 | 0 | 2021-05-31 | 158203 | BL-A | BL-A 35233306_FRRB - WYANDOTTE 1103 - W1 PH 1.10 - Mar. 2021 | 2021-03-31 | 2021-04-19 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-06-01 | Not Started | 2021-06-10 | Not Started | [6 empty] | 2021-06-03 | 2021-06-09 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-09-22 | Not Started | 2021-09-23 | Not Started | 2021-10-07 | Not Started | 2021-10-07 | Not Started | 2021-08-27 | 2021-11-08 | -73 | Behind Schedule | Not Started | 2021-11-08 | 2021-11-22 | Not Started | 2022-01-05 | Not Started
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | E.5034825.01.14 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2216 | 0 | 0 | 2216 | 0.4197 | 0.4197 | 0 | 0 | 0.4197 | 2216 | 0 | 0.4197 | 0 |  | 4778094 | 1919747 | 2858347 | 768290 | 2090057 | 91796.5 | 948101.6 | 1818448.9 | On/Under Budget | Budget Allocated | 2858347 | 2858349 | -2 | 3513658 | -655311 | 3513657.6 | 546397.3 | 4971.3 | 541426 | 0 | 0 | 0 | 91796.6 | 0 | 0 | 0 | 0 | 229 | 75926 | 10670 | 555277 | 584735 | 531047 | 332176 | 768290 | 0 | 0 | 2021-05-31 | 158202 | BL-A | BL-A 35233307_FRRB - WYANDOTTE 1103 - W1 PH 1.11 - Mar. 2021 | 2021-03-31 | 2021-04-12 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-11 | Not Started | [6 empty] | 2021-05-31 | 2021-06-04 | Not Started | 2021-06-14 | Not Started | 2021-06-14 | Not Started | 2021-07-26 | Not Started | 2021-08-06 | Not Started | 2021-08-12 | Not Started | 2021-08-12 | Not Started | 2021-08-27 | 2021-09-13 | -17 | Behind Schedule | Not Started | 2021-09-14 | 2021-09-27 | Not Started | 2021-11-10 | Not Started
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | E.5034825.01.15 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 7417 | 0 | 0 | 7417 | 1.4047 | 1.4047 | 0 | 0 | 1.4047 | 7417 | 0 | 1.4047 | 0 |  | 6280110 | 2266366 | 4013744 | 768290 | 3245454 | 163450.4 | 2847438.2 | 1002855.4 | On/Under Budget | Budget Allocated | 4013744 | 4013742 | 2 | 2401371 | 1612373 | 2401370.6 | 566653 | 435.4 | 566217.6 | 0 | 0 | 0 | 163450.4 | 0 | 0 | 0 | 0 | 229 | 29801 | 132985 | 576601 | 476670 | 742508 | 643329 | 1411619 | 0 | 0 | 2021-05-31 | 158201 | BL-A | BL-A 35233308_FRRB - WYANDOTTE 1103 - W1 PH 1.12 - Mar. 2021 | 2021-03-31 | 2021-04-29 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-07 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-06-14 | Not Started | 2021-06-14 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-08-30 | Not Started | 2021-08-30 | Not Started | 2021-08-27 | 2021-09-29 | -33 | Behind Schedule | Not Started | 2021-09-30 | 2021-10-13 | Not Started | 2021-11-26 | Not Started
35233309 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | E.5034825.01.16 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1981 | 0 | 0 | 1981 | 0.37519 | 0.37519 | 0 | 0 | 0.37519 | 1981 | 0 | 0.37519 | 0 |  | 3728491 | 1677531 | 2050960 | 768290 | 1282670 | 87374.8 | 10781.9 | 1952803.3 | On/Under Budget | Budget Allocated | 2050960 | 2050958 | 2 | 1934801 | 116159 | 1934800.7 | 934.4 | 58.1 | 876.3 | 0 | 0 | 0 | 87374.9 | 0 | 0 | 0 | 0 | 0 | 29059 | 58258 | 3209 | 878922 | 107304 | 104407 | 869799 | 0 | 0 | 2021-05-31 | 158200 | BL- A | BL- A 35233309_FRRB - WYANDOTTE 1103 - W1 PH 1.13 - Mar. 2021 | 2021-03-31 | 2021-04-12 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-05-31 | Not Started | 2021-06-09 | Not Started | [6 empty] | 2021-06-02 | 2021-06-08 | Not Started | 2021-08-17 | Not Started | 2021-08-17 | Not Started | 2021-09-03 | Not Started | 2021-09-03 | Not Started | 2021-09-09 | Not Started | 2021-09-09 | Not Started | 2021-08-27 | 2021-10-11 | -45 | Behind Schedule | Not Started | 2021-10-12 | 2021-10-25 | Not Started | 2021-12-08 | Not Started
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | E.5034825.01.17 | 5795419 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1597 | 0 | 0 | 1597 | 0.30246 | 0.30246 | 0 | 0 | 0.30246 | 1597 | 0 | 0.30246 | 0 |  | 2743520 | 1450230 | 1293290 | 768290 | 525000 | 49593.4 | 12839.8 | 1230856.8 | On/Under Budget | Budget Allocated | 1293290 | 1293292 | -2 | 908578 | 384712 | 908578.1 | 965.8 | 319.6 | 646.2 | 0 | 0 | 0 | 49593.4 | 0 | 0 | 0 | 0 | 344 | 39639 | 9290 | 2981 | 6562 | 771142 | 4960 | 458374 | 0 | 0 | 2021-05-31 | 158199 | BL-A | BL-A 35233310_FRRB - WYANDOTTE 1103 - W1 PH 1.14 - Mar. 2021 | 2021-03-31 | 2021-04-15 | Completed | 2021-03-18 | 2021-03-22 | Completed | 2021-06-01 | Not Started | 2021-06-10 | Not Started | [6 empty] | 2021-06-03 | 2021-06-09 | Not Started | 2021-09-09 | Not Started | 2021-09-09 | Not Started | 2021-09-23 | Not Started | 2021-10-08 | Not Started | 2021-10-13 | Not Started | 2021-10-13 | Not Started | 2021-08-27 | 2021-11-12 | -77 | Behind Schedule | Not Started | 2021-11-15 | 2021-11-26 | Not Started | 2022-01-11 | Not Started
35242420 | FRRB - BIG BEND 1102 - B1 PH1.4 | E.5034572.01.37 | 5793918 | UNSC | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 500 | 0 | 500 | 0.094697 | 0.094697 | 0 | 0 | 0.094697 | 500 | 0 | 0.094697 | 0 |  | 237500 | 0 | 237500 |  |  | 4380.6 | 0 | 233119.4 | On/Under Budget | Budget Allocated | 219294.16 | 174911 | 44383.16 | 174911 | 44383.16 | 174910.7 | 5000 | 719.9 | 4280.1 | 0 | 0 | 0 | 4380.6 | 0 | 0 | 0 | 0 | 0 | 0 | 3661 | 5000 | 166250 | 0 | 0 | 0 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-06-18 | Not Started | 2021-07-23 | 2021-07-29 | Not Started | 2021-07-22 | Not Started | 2021-08-04 | Not Started | [6 empty] | 2021-07-23 | 2021-07-29 | Not Started | 2021-08-06 | Not Started | 2021-08-06 | Not Started | 2021-08-09 | Not Started | 2021-08-06 | Not Started | 2021-08-09 | Not Started | 2021-08-09 | Not Started | 2021-09-08 | 2021-09-08 | 0 | On/ Ahead Schedule | Not Started | 2021-09-09 | 2021-09-22 | Not Started | 2021-11-05 | Not Started
35242421 | FRRB - BIG BEND 1102 - B6 PH6.2 | E.5034825.01.97 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3960 | 0 | 0 | 3960 | 0.75 | 0.75 | 0 | 0 | 0.75 | 3960 | 0 | 0.75 | 0 |  | 5841745 | 2305595 | 3536150 | 911150 | 2625000 | 4040.7 | 0 | 3532109.3 | On/Under Budget | Budget Allocated | 3536150 | 2628375 | 907775 | 2628375 | 907775 | 2628374.7 | 0 | 666 | -666 | 0 | 0 | 0 | 4040.6 | 0 | 0 | 0 | 0 | 0 | 702 | 2673 | 0 | 300000 | 1000000 | 1000000 | 325000 | 0 | 0 | 2021-05-21 | 160646 | BL-A: | BL-A: 35242421 FRRB - BIG BEND 1102 - B6 PH 6.2 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242422 | FRRB - BIG BEND 1102 - B6 PH6.3 | E.5034825.01.98 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3326 | 0 | 0 | 3326 | 0.62992 | 0.62992 | 0 | 0 | 0.62992 | 3326 | 0 | 0.62992 | 0 |  | 5295819 | 2179595 | 3116224 | 911150 | 2205074 | 5857.2 | 0 | 3110366.8 | On/Under Budget | Budget Allocated | 3116224 | 2210411 | 905813 | 2210411 | 905813 | 2210410.5 | 0 | 446.7 | -446.7 | 0 | 0 | 0 | 5857.2 | 0 | 0 | 0 | 0 | 0 | 2527 | 2884 | 0 | 205000 | 1000000 | 500000 | 500000 | 0 | 0 | 2021-05-21 | 160649 | BL-A: | BL-A: 35242422 FRRB - BIG BEND 1102 - B6 PH 6.3 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242423 | FRRB - BIG BEND 1102 - B6 PH6.4 | E.5034825.01.99 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 5702 | 0 | 0 | 5702 | 1.0799 | 1.0799 | 0 | 0 | 1.0799 | 5702 | 0 | 1.0799 | 0 |  | 7343245 | 2652095 | 4691150 | 911150 | 3780000 | 16117.3 | 0 | 4675032.7 | On/Under Budget | Budget Allocated | 4691150 | 3795671 | 895479 | 3795671 | 895479 | 3795670.6 | 0 | 446.7 | -446.7 | 0 | 0 | 0 | 16117.3 | 0 | 0 | 0 | 0 | 0 | 2152 | 13519 | 0 | 280000 | 1000000 | 1500000 | 1000000 | 0 | 0 | 2021-05-21 | 160642 | BL-A: | BL-A: 35242423 FRRB - BIG BEND 1102 - B6 PH 6.4 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242424 | FRRB - BIG BEND 1102 - B6 PH6.5 | E.5034825.01.81 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2218 | 0 | 0 | 2218 | 0.42008 | 0.42008 | 0 | 0 | 0.42008 | [5 empty] | 118750 | -2262400 | 2381150 | 911150 | 1470000 | 6677.2 | 0 | 2374472.8 | On/Under Budget | Budget Allocated | 2381150 | 703807 | 1677343 | 703807 | 1677343 | 703807.3 | 3934.4 | 446.7 | 3487.7 | 0 | 0 | 0 | 6677.2 | 0 | 0 | 0 | 0 | 0 | 3788 | 2442 | 3934 | 500934 | 192708 | 0 | 0 | 0 | 0 | 2021-05-21 | 160652 | BL-A: | BL-A: 35242424 FRRB - BIG BEND 1102 - B6 PH 6.5 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242425 | FRRB - BIG BEND 1102 - B6 PH6.6 | E.5034825.01.82 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 6019 | 0 | 0 | 6019 | 1.14 | 1.14 | 0 | 0 | 1.14 | [5 empty] | 118750 | -4782400 | 4901150 | 911150 | 3990000 | 6053.6 | 0 | 4895096.4 | On/Under Budget | Budget Allocated | 4901150 | 673355 | 4227795 | 673355 | 4227795 | 673354.7 | 3934.4 | 446.7 | 3487.7 | 0 | 0 | 0 | 6053.6 | 0 | 0 | 0 | 0 | 0 | 2903 | 2704 | 3934 | 500934 | 162879 | 0 | 0 | 0 | 0 | 2021-05-21 | 160651 | BL-A: | BL-A: 35242425 FRRB - BIG BEND 1102 - B6 PH 6.6 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242426 | FRRB - BIG BEND 1102 - B6 PH6.7 | E.5034825.01.83 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3010 | 0 | 0 | 3010 | 0.57008 | 0.57008 | 0 | 0 | 0.57008 | [5 empty] | 118750 | -2787400 | 2906150 | 911150 | 1995000 | 4051.9 | 0 | 2902098.1 | On/Under Budget | Budget Allocated | 2906150 | 913379 | 1992771 | 913379 | 1992771 | 913378.4 | 3934.4 | 372.3 | 3562.1 | 0 | 0 | 0 | 4052 | 0 | 0 | 0 | 0 | 0 | 403 | 3276 | 3934 | 500934 | 404830 | 0 | 0 | 0 | 0 | 2021-05-21 | 160644 | BL-A: | BL-A: 35242426 FRRB - BIG BEND 1102 - B6 PH 6.7 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242427 | FRRB - BIG BEND 1102 - B6 PH6.8 | E.5034825.01.84 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 4435 | 0 | 0 | 4435 | 0.83996 | 0.83996 | 0 | 0 | 0.83996 | [5 empty] | 118750 | -3732400 | 3851150 | 911150 | 2940000 | 8719.8 | 0 | 3842430.2 | On/Under Budget | Budget Allocated | 3851150 | 5253405 | -1402255 | 5253405 | -1402255 | 2313405.3 | 3934.4 | 372.3 | 3562.1 | 0 | 0 | 0 | 8719.8 | 0 | 0 | 0 | 0 | 0 | 1614 | 6734 | 3934 | 1440934 | 2000000 | 1300189 | 500000 | 0 | 0 | 2021-05-21 | 160641 | BL-A: | BL-A: 35242427 FRRB - BIG BEND 1102 - B6 PH 6.8 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35242553 | FRRB - WYANDOTTE 1103 - W3 PH3.10 |  | 0000000 | UNSE | 08W | [6 empty] | 2021 |  |  | OROVILLE | [24 empty] | Budget Allocated | 3078290 | 0 | 3078290 | 0 | 3078290
35243440 | PSPS-OREGON TRAIL 1103 CB & 35002-PH7 |  | 5794555 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 2270 | 0 | 0 | 2270 | 0.42992 | 0 | 0 | 0 | 0.42992 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 234 | -234 | 234 | -234 | [10 empty] | 0 | 0 | 0 | 0 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243441 | REMG - CHALLENGE 11025462 |  | 5796590 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | OROVILLE |  | 0 | 12302.4 | 0 | 12302.4 | 2.33 | 0 | 0 | 0 | 2.33 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3116 | -3116 | 3116 | -3116 | [10 empty] | 0 | 0 | 0 | 0 | 3116 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243442 | REMG - PIKE CITY 1102CB |  | 5796591 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 44404.8 | 0 | 44404.8 | 8.41 | 0 | 0 | 0 | 8.41 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1648 | -1648 | 1648 | -1648 | [10 empty] | 0 | 0 | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243443 | REMG - TIVY VALLEY 1107869946 |  | 5796592 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | DINUBA |  | 0 | 49051.2 | 0 | 49051.2 | 9.29 | 0 | 0 | 0 | 9.29 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1505 | -1505 | 1505 | -1505 | [10 empty] | 0 | 0 | 0 | 0 | 1505 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243444 | REMG - VOLTA 11011568 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 5280 | 0 | 5280 | 1 | 0 | 0 | 0 | 1 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35243445 | REMG - OLEMA 1101602 MURPHY RANCH |  | 5796593 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | SNRAFAEL |  | 0 | 7656 | 0 | 7656 | 1.45 | 0 | 0 | 0 | 1.45 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1666 | -1666 | 1666 | -1666 | [10 empty] | 0 | 0 | 0 | 0 | 1666 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243446 | REMG - OLEMA 110150396 MT. VISION |  | 5796593 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | SNRAFAEL |  | 0 | 2112 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0.4 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2424 | -2424 | 2424 | -2424 | [10 empty] | 0 | 0 | 0 | 0 | 2424 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243447 | CWSP - DESCHUTES 11041370 PH 2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 12160 | -12160 | 12160 | -12160 | [10 empty] | 0 | 0 | 0 | 0 | 12160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243448 | CWSP - DESCHUTES 110449024 PH 2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 13389 | -13389 | 13389 | -13389 | [10 empty] | 0 | 0 | 0 | 0 | 13389 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243452 | CWSP - COARSEGOLD 210410030 - PH1.1 |  | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST |  | 0 | 17754 | 0 | 17754 | 3.3625 | 0 | 0 | 0 | 3.3625 | [14 empty] | Request 2021 Budget | 0 | 11107 | -11107 | 11107 | -11107 | [10 empty] | 0 | 0 | 0 | 1558 | 9549 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35243453 | CWSP - VOLTA 11011596 - PH1 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 22017.6 | 0 | 22017.6 | 4.17 | 0 | 0 | 0 | 4.17 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 12477 | -12477 | 12477 | -12477 | [10 empty] | 0 | 0 | 0 | 484 | 11993 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240160 | CWSP - COARSEGOLD 21045310 PH 1.1 | E.5034895.01.01 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 23148 | 0 | 23148 | 4.3841 | 0 | 0 | 0 | 4.3841 | [5 empty] | 317000 | 0 | 317000 |  |  | 17540.6 | 0 | 299459.4 | On/Under Budget | Request 2021 Budget | 0 | 17541 | -17541 | 17541 | -17541 | 17540.6 | 0 | 0 | 0 | 0 | 0 | 0 | 17540.7 | 0 | 0 | 0 | 0 | 0 | 4804 | 12736 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240162 | CWSP - COARSEGOLD 21045310 PH 2.1 | E.5034895.01.02 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 11221 | 0 | 11221 | 2.1252 | 0 | 0 | 0 | 2.1252 | [5 empty] | 317000 | 0 | 317000 |  |  | 9059 | 0 | 307941 | On/Under Budget | Request 2021 Budget | 0 | 9059 | -9059 | 9059 | -9059 | 9059 | 0 | 0 | 0 | 0 | 0 | 0 | 9059 | 0 | 0 | 0 | 0 | 0 | 2005 | 7054 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240163 | CWSP - COARSEGOLD 21045310 PH 3.1 | E.5034895.01.03 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 11697 | 0 | 11697 | 2.2153 | 0 | 2.2153 | 0 | 2.2153 | [5 empty] | 317000 | 0 | 317000 |  |  | 11447.8 | 0 | 305552.2 | On/Under Budget | Request 2021 Budget | 0 | 11448 | -11448 | 11448 | -11448 | 11447.8 | 0 | 0 | 0 | 0 | 0 | 0 | 11447.8 | 0 | 0 | 0 | 0 | 0 | 2699 | 8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240164 | CWSP - COARSEGOLD 2104570682 PH 1 | E.5034895.01.04 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 11077 | 0 | 11077 | 2.0979 | 0 | 0 | 0 | 2.0979 | [5 empty] | 800000 | 0 | 800000 |  |  | 13285.1 | 0 | 786714.9 | On/Under Budget | Request 2021 Budget | 0 | 13285 | -13285 | 13285 | -13285 | 13285.1 | 0 | 0 | 0 | 0 | 0 | 0 | 13285.1 | 0 | 0 | 0 | 0 | 0 | 5475 | 7810 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240165 | CWSP - COARSEGOLD 21046210 PH 1.1 | E.5034895.01.05 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 20327 | 0 | 20327 | 3.8498 | 0 | 0 | 0 | 3.8498 | [5 empty] | 237500 | 0 | 237500 |  |  | 10185 | 0 | 227315 | On/Under Budget | Request 2021 Budget | 0 | 10130 | -10130 | 10130 | -10130 | 10129.6 | 0 | 55.4 | -55.4 | 0 | 0 | 0 | 10185 | 0 | 0 | 0 | 0 | 0 | 2553 | 7576 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240166 | CWSP - VOLTA 1101CB PH 1.1 | E.5034896.01.01 | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF | North Valley Assets | 0 | 7497.6 | 0 | 7497.6 | 1.42 | 0 | 0 | 0 | 1.42 | [5 empty] | 1 | 1 | 0 |  |  | 18325.1 | 0 | -18325.1 | OverRun | Request 2021 Budget | 0 | 17535 | -17535 | 17535 | -17535 | 17535.1 | 0 | 790 | -790 | 0 | 0 | 0 | 18325 | 0 | 0 | 0 | 0 | 0 | 2365 | 15170 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240167 | CWSP - VOLTA 1101CB PH 2.1 | E.5034897.01.01 | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF | North Valley Assets | 2164.8 | 2180.64 | 0 | 4345.44 | 0.823 | 0 | 0 | 0 | 0.823 | [5 empty] | 1 | 1 | 0 |  |  | 13304.5 | 0 | -13304.5 | OverRun | Request 2021 Budget | 0 | 12704 | -12704 | 12704 | -12704 | 12704.4 | 0 | 600.1 | -600.1 | 0 | 0 | 0 | 13304.5 | 0 | 0 | 0 | 0 | 0 | 817 | 11887 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240168 | CWSP - VOLTA 110153118 PH 1.1 | E.5034897.01.02 | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF | North Valley Assets | 0 | 7920 | 0 | 7920 | 1.5 | 0 | 0.00028409 | 0 | 1.5 | [5 empty] | 1 | 1 | 0 |  |  | 15132.1 | 0 | -15132.1 | OverRun | Request 2021 Budget | 0 | 13513 | -13513 | 13513 | -13513 | 13513.4 | 0 | 1618.7 | -1618.7 | 0 | 0 | 0 | 15132.1 | 0 | 0 | 0 | 0 | 0 | 777 | 12737 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240169 | CWSP - VOLTA 11011568 PH 1 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 122020.8 | 0 | 122020.8 | 23.11 | 0 | 0 | 0 | 23.11 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 18801 | -18801 | 18801 | -18801 | [10 empty] | 0 | 0 | 0 | 4078 | 14724 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240170 | CWSP - VOLTA 11011568 PH 2 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 13836 | -13836 | 13836 | -13836 | [10 empty] | 0 | 0 | 0 | 170 | 13666 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240171 | CWSP - VOLTA 11011568 PH 3 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 7672 | -7672 | 7672 | -7672 | [10 empty] | 0 | 0 | 0 | 257 | 7416 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240173 | CWSP - PUTAH CREEK 11028352 PH 1 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 33792 | 0 | 33792 | 6.4 | 0 | 0 | 0 | 6.4 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6022 | -6022 | 6022 | -6022 | [10 empty] | 0 | 0 | 0 | 61 | 5962 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240174 | CWSP - PUTAH CREEK 11028352 PH 2 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6212 | -6212 | 6212 | -6212 | [10 empty] | 0 | 0 | 0 | 242 | 5969 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240175 | CWSP - PUTAH CREEK 110267858 PH 1 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 60297.6 | 0 | 60297.6 | 11.42 | 0 | 0 | 0 | 11.42 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 10258 | -10258 | 10258 | -10258 | [10 empty] | 0 | 0 | 0 | 2841 | 7417 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240176 | CWSP - PUTAH CREEK 110264044 PH 1 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 31680 | 0 | 31680 | 6 | 0 | 0 | 0 | 6 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3868 | -3868 | 3868 | -3868 | [10 empty] | 0 | 0 | 0 | 121 | 3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240177 | CWSP - PUTAH CREEK 110264044 PH 2 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 4148 | -4148 | 4148 | -4148 | [10 empty] | 0 | 0 | 0 | 0 | 4148 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240178 | CWSP - PUTAH CREEK 1102710384 PH 1 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 28195.2 | 0 | 28195.2 | 5.34 | 0 | 0 | 0 | 5.34 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2734 | -2734 | 2734 | -2734 | [10 empty] | 0 | 0 | 0 | 61 | 2673 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240179 | CWSP - SANTA YNEZ 1104CB, 0.58 MILES |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 2006.4 | 0 | 2006.4 | 0.38 | 0 | 0 | 0 | 0.38 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3964 | -3964 | 3964 | -3964 | [10 empty] | 0 | 0 | 0 | 1143 | 2821 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240220 | CWSP - SANTA YNEZ 1104Y04 PH 1, 8.2MILES |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 82632 | 0 | 82632 | 15.65 | 0 | 0 | 0 | 15.65 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 13298 | -13298 | 13298 | -13298 | [10 empty] | 0 | 0 | 0 | 8200 | 5098 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240221 | CWSP - SANTA YNEZ 1104Y04 PH 2, 7.6MILES |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2308 | -2308 | 2308 | -2308 | [10 empty] | 0 | 0 | 0 | 61 | 2248 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240222 | CWSP - SANTA YNEZ 1104Y66 PH 1, 7.8MILES |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 89443.2 | 0 | 89443.2 | 16.94 | 0 | 0 | 0 | 16.94 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3671 | -3671 | 3671 | -3671 | [10 empty] | 0 | 0 | 0 | 1565 | 2106 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240223 | CWSP - SANTA YNEZ 1104Y66 PH 2 8.5MILES |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1718 | -1718 | 1718 | -1718 | [10 empty] | 0 | 0 | 0 | 50 | 1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35240224 | CWSP - SANTA YNEZ 110477098 PH 1, 11.9MI |  | 5796385 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STMARIA |  | 0 | 63148.8 | 0 | 63148.8 | 11.96 | 0 | 0 | 0 | 11.96 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3577 | -3577 | 3577 | -3577 | [10 empty] | 0 | 0 | 0 | 1724 | 1853 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241060 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | E.5034917.01.01 | 5796493 | UNSE | 08W | [6 empty] | Not in the WP |  | SH - Remote Grid | OAKHURST | Yosemite Assets | 0 | 0 | 7920 | 7920 | 1.5 | 1.5 | 0 | 0 | 1.5 | [5 empty] | 500000 | 0 | 500000 |  |  | 49079.7 | 0 | 450920.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 54114 | -54114 | 54114 | -54114 | 54114.1 | 0 | -5034.4 | 5034.4 | 0 | 0 | 0 | 49079.7 | 0 | 0 | 0 | 0 | 0 | 23452 | 30663 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241071 | CWSP - DESCHUTES 11041582 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 33792 | 0 | 33792 | 6.4 | 0 | 0 | 0 | 6.4 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 5249 | -5249 | 5249 | -5249 | [10 empty] | 0 | 0 | 0 | 606 | 4643 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241072 | CWSP - DESCHUTES 11041370 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 71755.2 | 0 | 71755.2 | 13.59 | 0 | 0 | 0 | 13.59 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6976 | -6976 | 6976 | -6976 | [10 empty] | 0 | 0 | 0 | 1945 | 5032 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241073 | CWSP - DESCHUTES 110449024 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 87648 | 0 | 87648 | 16.6 | 0 | 0 | 0 | 16.6 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6207 | -6207 | 6207 | -6207 | [10 empty] | 0 | 0 | 0 | 1510 | 4697 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35241075 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | E.5034825.01.91 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 370 | 0 | 0 | 370 | 0.070076 | 0.070076 | 0 | 0 | 0.070076 | [5 empty] | 190000 | 0 | 190000 |  |  | 15.2 | 0 | 189984.8 | On/Under Budget | Request 2021 Budget | 0 | 5015 | -5015 | 5015 | -5015 | 5015.2 | 5000 | 0 | 5000 | 0 | 0 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-05 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-07-19 | Not Started | 2021-08-30 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-11-17 | Not Started | 2021-09-01 | Not Started | 2021-12-01 | Not Started | 2021-12-01 | Not Started | 2021-12-31 | 2021-12-31 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-14 | Not Started | 2022-03-01 | Not Started
35241076 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | E.5034825.01.92 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 581 | 0 | 0 | 581 | 0.11004 | 0.11004 | 0 | 0 | 0.11004 | [5 empty] | 190000 | 0 | 190000 |  |  | 159.3 | 0 | 189840.7 | On/Under Budget | Request 2021 Budget | 0 | 5015 | -5015 | 5015 | -5015 | 5015.2 | 5000 | 144.1 | 4855.9 | 0 | 0 | 0 | 159.3 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-05 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-07-19 | Not Started | 2021-08-30 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-11-17 | Not Started | 2021-09-01 | Not Started | 2021-12-01 | Not Started | 2021-12-01 | Not Started | 2021-12-31 | 2021-12-31 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-14 | Not Started | 2022-03-01 | Not Started
35241077 | FRRB - WYANDOTTE 1103 W5 PH5.4 FUTURE SM | E.5034825.01.93 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1637 | 0 | 0 | 1637 | 0.31004 | 0.31004 | 0 | 0 | 0.31004 | [5 empty] | 190000 | 0 | 190000 |  |  | 89.6 | 0 | 189910.4 | On/Under Budget | Request 2021 Budget | 0 | 5015 | -5015 | 5015 | -5015 | 5015.1 | 5000 | 74.5 | 4925.5 | 0 | 0 | 0 | 89.7 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-05 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-07-19 | Not Started | 2021-08-30 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-11-17 | Not Started | 2021-09-01 | Not Started | 2021-12-01 | Not Started | 2021-12-01 | Not Started | 2021-12-31 | 2021-12-31 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-14 | Not Started | 2022-03-01 | Not Started
35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | E.5034805.01.33 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 422 | 0 | 0 | 422 | 0.079924 | 0 | 0.079924 | 0 | 0.079924 | [5 empty] | 300000 | 300000 | 0 |  |  | 365.7 | 0 | -365.7 | OverRun | Request 2021 Budget | 0 | 4623 | -4623 | 4623 | -4623 | 4623 | 2430.3 | -1827 | 4257.3 | 0 | 0 | 0 | 365.6 | 0 | 0 | 0 | 0 | 0 | 229 | 1964 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | E.5034805.01.34 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 3419 | 0 | 0 | 3419 | 0.64754 | 0 | 0.64754 | 0 | 0.64754 | [5 empty] | 300000 | 300000 | 0 |  |  | 518.5 | 0 | -518.5 | OverRun | Request 2021 Budget | 0 | 17038 | -17038 | 17038 | -17038 | 17038 | 797.4 | -15722.1 | 16519.5 | 0 | 0 | 0 | 518.5 | 0 | 0 | 0 | 0 | 0 | 341 | 15900 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35235670 | FRRB - WYANDOTTE 1103 W5 PH5.1 FUTURE SM | E.5034825.01.25 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 581 | 0 | 0 | 581 | 0.11004 | 0.11004 | 0 | 0 | 0.11004 | [5 empty] | 190000 | 0 | 190000 |  |  | 5130.7 | 0 | 184869.3 | On/Under Budget | Request 2021 Budget | 0 | 10056 | -10056 | 10056 | -10056 | 10056.2 | 5000 | 74.5 | 4925.5 | 0 | 0 | 0 | 5130.8 | 0 | 0 | 0 | 0 | 236 | 4400 | 420 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-07-05 | Not Started | 2021-07-20 | 2021-07-26 | Not Started | 2021-07-19 | Not Started | 2021-08-30 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-09-01 | Not Started | 2021-09-01 | Not Started | 2021-11-17 | Not Started | 2021-09-01 | Not Started | 2021-12-01 | Not Started | 2021-12-01 | Not Started | 2021-12-31 | 2021-12-31 | 0 | On/ Ahead Schedule | Not Started | 2021-12-31 | 2022-01-14 | Not Started | 2022-03-01 | Not Started
35235702 | FRRB - KANAKA 1101 - K3 PH 3 | E.5034825.01.37 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 7603.2 | 0 | 0 | 7603.2 | 1.44 | 1.44 | 0 | 0 | 1.44 | [5 empty] | 950000 | 0 | 950000 |  |  | 51641.8 | 74627.5 | 823730.7 | On/Under Budget | Budget Allocated | 6050630 | 5103944 | 946686 | 5103944 | 946686 | 5103943.7 | 58221.1 | 45919.2 | 12301.9 | 0 | 0 | 0 | 51641.9 | 0 | 0 | 0 | 0 | 236 | 1906 | 3581 | 58221 | 40000 | 1000000 | 1500000 | 1500000 | 1000000 | 0 | 2021-05-21 |  |  |  |  | 2021-06-16 | Not Started | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-11 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | Not Started | 2021-10-29 | Not Started | 2021-08-13 | Not Started | 2021-11-12 | Not Started | 2021-11-12 | Not Started | 2021-12-14 | 2021-12-14 | 0 | On/ Ahead Schedule | Not Started | 2021-12-14 | 2021-12-28 | Not Started | 2022-02-10 | Not Started
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | E.5034805.01.37 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 5914 | 0 | 0 | 5914 | 1.1201 | 0 | 1.1201 | 0 | 1.1201 | [5 empty] | 67857 | 0 | 67857 |  |  | 1153.4 | 0 | 66703.6 | On/Under Budget | Request 2021 Budget | 0 | 3584 | -3584 | 3584 | -3584 | 3583.7 | 2430.3 | 0 | 2430.3 | 0 | 0 | 0 | 1153.4 | 0 | 0 | 0 | 0 | 229 | 918 | 7 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159743 | BL-A: | BL-A: ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 - Apr 21 | 2021-04-28 | 2021-09-27 | Not Started | 2021-11-02 | 2021-11-08 | Not Started | 2021-11-01 | Not Started | 2021-11-29 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-01-18 | 2022-07-05 | -168 | Behind Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | E.5034805.01.38 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 2534 | 0 | 0 | 2534 | 0.47992 | 0 | 0.47992 | 0 | 0.47992 | [5 empty] | 67857 | 0 | 67857 |  |  | 1154 | 0 | 66703 | On/Under Budget | Request 2021 Budget | 0 | 3338 | -3338 | 3338 | -3338 | 3338.2 | 2096.3 | 0 | 2096.3 | 0 | 0 | 0 | 1154 | 0 | 0 | 0 | 0 | 229 | 918 | 7 | 2096 | 20 | 20 | 20 | 20 | 10 | 0 | 2021-06-18 |  |  |  |  | 2021-09-27 | Not Started | 2021-11-02 | 2021-11-08 | Not Started | 2021-11-01 | Not Started | 2021-11-29 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-07-05 | 2022-07-05 | 0 | On/ Ahead Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35235672 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | E.5034825.01.27 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1600 | 0 | 0 | 1600 | 0.30303 | 0.30303 | 0 | 0 | 0.30303 | [5 empty] | 237500 | 0 | 237500 |  |  | 924.3 | 0 | 236575.7 | On/Under Budget | Request 2021 Budget | 0 | 5924 | -5924 | 5924 | -5924 | 5924.3 | 5000 | 0 | 5000 | 0 | 0 | 0 | 924.3 | 0 | 0 | 0 | 0 | 0 | 465 | 460 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-30 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-28 | 2021-12-28 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35235675 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | E.5034825.01.30 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 600 | 0 | 0 | 600 | 0.11364 | 0.11364 | 0 | 0 | 0.11364 | [5 empty] | 237500 | 0 | 237500 |  |  | 260.8 | 0 | 237239.2 | On/Under Budget | Request 2021 Budget | 0 | 5261 | -5261 | 5261 | -5261 | 5260.8 | 5000 | 0 | 5000 | 0 | 0 | 0 | 260.8 | 0 | 0 | 0 | 0 | 0 | 229 | 32 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-30 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-28 | 2021-12-28 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35235678 | FRRB - BIG BEND 1102 - B5 PH5.1 | E.5034825.01.33 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 2200 | 0 | 0 | 2200 | 0.41667 | 0.41667 | 0 | 0 | 0.41667 | [5 empty] | 4340396 | 1959095 | 2381301 | 911150 | 1470151 | 11144.7 | 0 | 2370156.3 | On/Under Budget | Budget Allocated | 2381301 | 1480320 | 900981 | 1480320 | 900981 | 1480320.1 | 0 | 824.6 | -824.6 | 0 | 0 | 0 | 11144.8 | 0 | 0 | 0 | 0 | 0 | 465 | 9856 | 0 | 0 | 470000 | 500000 | 500000 | 0 | 0 | 2021-06-11 | 160647 | BL-A: | BL-A: 35235678 FRRB - Big Bend 1102 - B5 PH 5.1 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-22 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-23 | 2021-07-29 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35235679 | FRRB - BIG BEND 1102 - B6 PH6.1 | E.5034825.01.34 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3485 | 0 | 0 | 3485 | 0.66004 | 0.66004 | 0 | 0 | 0.66004 | 3485 | 0 | 0.66004 | 0 |  | 5075596 | 1987345 | 3088251 | 777400 | 2310851 | 13696.4 | 0 | 3074554.6 | On/Under Budget | Budget Allocated | 3088251 | 2322245 | 766006 | 2322245 | 766006 | 2322245.1 | 0 | 1451.3 | -1451.3 | 0 | 0 | 0 | 13696.4 | 0 | 0 | 0 | 0 | 0 | 6161 | 6084 | 0 | 150000 | 1000000 | 660000 | 500000 | 0 | 0 | 2021-05-21 | 160648 | BL-A: | BL-A: 35235679 FRRB - Big Bend 1102 - B6 PH 6.0 - May 21 | 2021-05-12 | 2021-06-30 | Not Started | 2021-04-19 | 2021-04-23 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-14 | 2021-12-28 | -14 | Behind Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35239094 | FRRB - DUNBAR 1101416 |  | 5545079 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | STROSA |  | 6177 | 0 | 0 | 6177 | 1.1699 | 0 | 1.1699 | 0 | 1.1699 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35237021 | FRRB - WYANDOTTE 1103 W7 PH7.4 FUTURE SM | E.5034825.01.43 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1300 | 0 | 0 | 1300 | 0.24621 | 0.24621 | 0 | 0 | 0.24621 | [5 empty] | 237500 | 0 | 237500 |  |  | 15.2 | 0 | 237484.8 | On/Under Budget | Request 2021 Budget | 0 | 5015 | -5015 | 5015 | -5015 | 5015.2 | 5000 | 0 | 5000 | 0 | 0 | 0 | 15.2 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-30 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-28 | 2021-12-28 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35238087 | REMG - OAKHURST 110110090 |  | 0000000 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OAKHURST | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35236997 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | E.5034825.01.56 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 1500 | 0 | 0 | 1500 | 0.28409 | 0.28409 | 0 | 0 | 0.28409 | [5 empty] | 237500 | 0 | 237500 |  |  | 3726.1 | 0 | 233773.9 | On/Under Budget | Request 2021 Budget | 0 | 8155 | -8155 | 8155 | -8155 | 8154.7 | 5000 | 571.4 | 4428.6 | 0 | 0 | 0 | 3726.1 | 0 | 0 | 0 | 0 | 531 | 1298 | 1326 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-05-21 |  |  |  |  | 2021-06-30 | Not Started | 2021-07-15 | 2021-07-21 | Not Started | 2021-07-14 | Not Started | 2021-08-25 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-27 | Not Started | 2021-08-27 | Not Started | 2021-11-12 | Not Started | 2021-08-27 | Not Started | 2021-11-26 | Not Started | 2021-11-26 | Not Started | 2021-12-28 | 2021-12-28 | 0 | On/ Ahead Schedule | Not Started | 2021-12-28 | 2022-01-11 | Not Started | 2022-02-24 | Not Started
35236992 | FRRB - KANAKA 1101 - K1 PH 1.2 | E.5034825.01.53 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 3514 | 0 | 0 | 3514 | 0.66553 | 0.66553 | 0 | 0 | 0.66553 | [5 empty] | 475000 | 0 | 475000 |  |  | 4401 | 0 | 470599 | On/Under Budget | Budget Allocated | 2988215 | 2329355 | 658860 | 2329355 | 658860 | 2329355 | 5000 | 0 | 5000 | 0 | 0 | 0 | 4401 | 0 | 0 | 0 | 0 | 0 | 1721 | 2680 | 5000 | 0 | 319954 | 1000000 | 1000000 | 0 | 0 | 2021-06-11 |  |  |  |  | 2021-08-20 | Not Started | 2021-09-06 | 2021-09-10 | Not Started | 2021-09-03 | Not Started | 2021-10-15 | Not Started | [6 empty] | 2021-07-29 | 2021-08-04 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2022-01-04 | Not Started | 2021-10-19 | Not Started | 2022-01-18 | Not Started | 2022-01-18 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35236984 | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | E.5034825.01.46 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 10402 | 0 | 0 | 10402 | 1.9701 | 1.9701 | 0 | 0 | 1.9701 | [5 empty] | 190000 | 0 | 190000 |  |  | 47598.1 | 74627.5 | 67774.4 | On/Under Budget | Budget Allocated | 7991552 | 6894999 | 1096553 | 6894999 | 1096553 | 6894998.5 | 58403.9 | 46248.8 | 12155.1 | 0 | 0 | 0 | 47598.1 | 0 | 0 | 0 | 0 | 0 | 197 | 1152 | 58404 | 359 | 833991 | 2000359 | 2000359 | 2000179 | 0 | 2021-05-21 |  |  |  |  | 2021-06-16 | Not Started | 2021-07-02 | 2021-07-08 | Not Started | 2021-07-01 | Not Started | 2021-08-11 | Not Started | [6 empty] | 2021-07-02 | 2021-07-08 | Not Started | 2021-08-13 | Not Started | 2021-08-13 | Not Started | 2021-10-29 | Not Started | 2021-08-13 | Not Started | 2021-11-12 | Not Started | 2021-11-12 | Not Started | 2021-12-14 | 2021-12-14 | 0 | On/ Ahead Schedule | Not Started | 2021-12-14 | 2021-12-28 | Not Started | 2022-02-10 | Not Started
35236985 | FRRB - KANAKA 1101 - K1 PH 1.1 | E.5034825.01.47 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 8447 | 0 | 0 | 8447 | 1.5998 | 1.5998 | 0 | 0 | 1.5998 | [5 empty] | 475000 | 0 | 475000 |  |  | 7811.6 | 0 | 467188.4 | On/Under Budget | Budget Allocated | 6688147 | 5599337 | 1088810 | 5599337 | 1088810 | 5599337.2 | 5000 | 297.4 | 4702.6 | 0 | 0 | 0 | 7811.6 | 0 | 0 | 0 | 0 | 394 | 2490 | 4630 | 5000 | 0 | 2000000 | 1500000 | 1500000 | 586823 | 0 | 2021-06-11 |  |  |  |  | 2021-08-20 | Not Started | 2021-09-06 | 2021-09-10 | Not Started | 2021-09-03 | Not Started | 2021-10-15 | Not Started | [6 empty] | 2021-07-29 | 2021-08-04 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2022-01-04 | Not Started | 2021-10-19 | Not Started | 2022-01-18 | Not Started | 2022-01-18 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-17 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35236982 | FRRB - KANAKA 1101 - K6 PH6 | E.5034825.01.44 | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 10296 | 0 | 0 | 10296 | 1.95 | 1.95 | 0 | 0 | 1.95 | [5 empty] | 950000 | 0 | 950000 |  |  | 3680 | 0 | 946320 | On/Under Budget | Request 2021 Budget | 0 | 8231 | -8231 | 8231 | -8231 | 8230.4 | 5000 | 449.6 | 4550.4 | 0 | 0 | 0 | 3680.1 | 0 | 0 | 0 | 0 | 471 | 706 | 2053 | 5000 | 0 | 0 | 0 | 0 | 0 | 0
35227204 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.5 |  | 5795126 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 6864 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 1.3 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35227655 | CWSP - KIRKER 2104442850 PH 1.2 | E.5034694.01.02 | 5794544 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - Remote Grid | ANTIOCH | Diablo Assets | 0 | 0 | 19906 | 19906 | 3.7701 | 0 | 3.7701 | 0 | 3.7701 | [5 empty] | 450000 | 0 | 450000 |  |  | 1671.2 | 0 | 448328.8 | On/Under Budget | Request 2021 Budget | 0 | 101702 | -101702 | 101702 | -101702 | 2009502.3 | 949.2 | 74.5 | 874.7 | 0 | 0 | 0 | 1671.2 | 1907800.5 | 0 | 0 | 116 | 712 | 692 | 76 | 949 | 955 | 10178 | 23540 | 5599 | 6226 | 52658 | 2021-06-18 | 157131 | BL-A | BL-A CWSP - KIRKER 2104442850 PH 2 - Mar. 2021 | 2021-03-07 | 2022-01-20 | Not Started | 2022-04-15 | 2022-04-21 | Not Started | 2022-04-14 | Not Started | 2022-05-12 | Not Started | 2022-01-21 | 2022-01-21 | Not Started | 2022-01-24 | 2022-02-11 | Not Started | 2022-04-15 | 2022-05-05 | Not Started | 2022-06-06 | Not Started |  |  |  |  | 2022-06-06 | Not Started | 2022-10-31 | Not Started | 2022-11-07 | Not Started | 2023-01-06 | 2023-01-06 | 0 | On/ Ahead Schedule | Not Started | 2023-02-21 | 2023-03-06 | Not Started | 2023-03-31 | Not Started
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | E.5034806.01.02 | 5795301 | UNSE | 08W | [6 empty] | 2021 |  | SH | NAPA | North Bay Assets | 6936 | 0 | 0 | 6936 | 1.3136 | 1.3136 | 0 | 0 | 1.3136 | [5 empty] | 237833 | 0 | 237833 | 0 | 237833 | 35422.8 | 0 | 202410.2 | On/Under Budget | Budget Allocated | 237833 | 233932 | 3901 | 233932 | 3901 | 234100.9 | 15105.4 | 469.1 | 14636.3 | 0 | 0 | 0 | 35422.8 | 169.1 | 0 | 0 | 0 | 993 | 1894 | 32066 | 15105 | 1461 | 1468 | 176475 | 1482 | 1489 | 1496 | 2021-06-18 | 159374 | BL-A: | BL-A: 35227033_ECOP - PUEBLO 2102 - H01-LR792 PH 3_08W - B1_Apr 21 | 2021-04-21 | 2021-09-03 | Not Started | 2021-10-18 | 2021-10-22 | Not Started | 2021-10-15 | Not Started | 2021-11-12 | Not Started | 2021-09-06 | 2021-11-12 | Not Started | 2021-11-15 | 2021-11-29 | Not Started | 2021-11-05 | 2021-11-18 | Not Started | 2021-11-30 | Not Started | 2021-11-30 | Not Started | 2021-12-13 | Not Started | 2021-11-30 | Not Started | 2022-01-31 | Not Started | 2022-03-01 | Not Started | 2022-03-22 | 2022-05-02 | -41 | Behind Schedule | Not Started | 2022-05-03 | 2022-05-16 | Not Started | 2022-06-29 | Not Started
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | E.5034805.01.30 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 8184 | 0 | 0 | 8184 | 1.55 | 0 | 1.55 | 0 | 1.55 | [5 empty] | 200000 | 0 | 200000 |  |  | 14262.5 | 0 | 185737.5 | On/Under Budget | Request 2021 Budget | 0 | 22011 | -22011 | 22011 | -22011 | 22065.5 | 103.9 | -7015.5 | 7119.4 | 0 | 0 | 0 | 14262.5 | 54.3 | 0 | 0 | 0 | 2199 | 11509 | 7570 | 104 | 105 | 105 | 105 | 105 | 105 | 105 | 2021-06-18 | 157836 | BL-A | BL-A 35227031_ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-06 | Not Started | 2021-08-09 | 2021-08-13 | Not Started | 2021-09-10 | Not Started | 2021-10-01 | Not Started | 2021-08-09 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-30 | Not Started | 2021-09-13 | 2021-09-24 | Not Started | 2021-10-26 | Not Started | 2021-10-26 | Not Started | 2021-11-08 | Not Started | 2021-10-26 | Not Started | 2022-02-07 | Not Started | 2022-03-08 | Not Started | 2022-02-24 | 2022-03-31 | -35 | Behind Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | E.5034805.01.02 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2006.4 | 0 | 2006.4 | 0.38 | 0 | 0.37992 | 0 | 0.38 | [5 empty] | 155000 | 0 | 155000 |  |  | 25951.7 | 0 | 129048.3 | On/Under Budget | Budget Allocated | 300000 | 32919 | 267081 | 32919 | 267081 | 32919 | 2083.1 | -4884.2 | 6967.3 | 0 | 0 | 0 | 25951.7 | 0 | 0 | 0 | 343 | 918 | 23073 | 6501 | 2083 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159756 | BL-A: | BL-A: 35226858_ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-10-24 | 2022-10-28 | Not Started | 2022-10-21 | Not Started | 2022-11-18 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-12-23 | Not Started | 2022-12-23 | Not Started | 2023-01-05 | Not Started | 2022-12-23 | Not Started | 2023-02-10 | Not Started | 2023-03-13 | Not Started | 2023-03-21 | 2023-05-12 | -52 | Behind Schedule | Not Started | 2023-05-15 | 2023-05-26 | Not Started | 2023-07-11 | Not Started
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | E.5034805.01.03 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 4646.4 | 0 | 4646.4 | 0.88 | 0 | 0.87992 | 0 | 0.88 | [5 empty] | 155000 | 0 | 155000 |  |  | 25835.7 | 0 | 129164.3 | On/Under Budget | Budget Allocated | 300000 | 39241 | 260759 | 39241 | 260759 | 40678.3 | 2302.8 | -9738.2 | 12041 | 0 | 0 | 0 | 25835.7 | 1377.4 | 60.5 | 0 | 343 | 2099 | 22049 | 11083 | 2303 | 227 | 227 | 227 | 227 | 227 | 227 | 2021-06-18 | 159759 | BL-A: | BL-A: 35226859_ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2021-12-21 | Not Started | 2021-12-22 | 2022-01-11 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | E.5034805.01.04 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3484.8 | 0 | 3484.8 | 0.66 | 0 | 0.66004 | 0 | 0.66 | [5 empty] | 155000 | 0 | 155000 |  |  | 26200.8 | 0 | 128799.2 | On/Under Budget | Budget Allocated | 300000 | 34923 | 265077 | 34923 | 265077 | 36398.6 | 2624.1 | -4884.2 | 7508.3 | 0 | 0 | 0 | 26200.7 | 1413.7 | 62.1 | 0 | 343 | 2178 | 22966 | 5598 | 2624 | 202 | 202 | 202 | 202 | 202 | 202 | 2021-06-18 | 159752 | BL-A: | BL-A: 35226861_ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | E.5034805.01.05 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 3062.4 | 0 | 3062.4 | 0.58 | 0 | 0.57992 | 0 | 0.58 | [5 empty] | 155000 | 0 | 155000 |  |  | 25620.3 | 0 | 129379.7 | On/Under Budget | Budget Allocated | 300000 | 32685 | 267315 | 32685 | 267315 | 34114.4 | 987.7 | -4884.2 | 5871.9 | 0 | 0 | 0 | 25620.3 | 1369.3 | 60.2 | 0 | 343 | 1832 | 22734 | 5594 | 988 | 199 | 199 | 199 | 199 | 199 | 199 | 2021-06-18 | 159746 | BL-A: | BL-A: 35226862_ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6_08W - Apr 21 | 2021-04-28 | 2021-12-20 | Not Started | 2022-08-31 | 2022-09-06 | Not Started | 2022-08-30 | Not Started | 2022-09-27 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-01 | Not Started | 2022-11-01 | Not Started | 2022-11-14 | Not Started | 2022-11-01 | Not Started | 2022-12-20 | Not Started | 2023-01-18 | Not Started | 2023-03-21 | 2023-03-21 | 0 | On/ Ahead Schedule | Not Started | 2023-03-22 | 2023-04-04 | Not Started | 2023-05-18 | Not Started
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | E.5034805.01.19 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 15183 | 0 | 0 | 15183 | 2.8756 | 0 | 2.8756 | 0 | 2.8756 | [5 empty] | 118750 | 0 | 118750 |  |  | 28298.6 | 0 | 90451.4 | On/Under Budget | Budget Allocated | 500000 | 34547 | 465453 | 34547 | 465453 | 36351.9 | 2622 | -2425.5 | 5047.5 | 0 | 0 | 0 | 28298.6 | 1594.9 | 210.2 | 0 | 237 | 1433 | 31156 | -2102 | 2622 | 200 | 200 | 200 | 200 | 200 | 200 | 2021-06-18 | 159385 | BL-A: | BL-A: 35227007_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2_08W - B1_Apr 21 | 2021-04-21 | 2022-03-07 | Not Started | 2022-11-16 | 2022-11-22 | Not Started | 2022-11-15 | Not Started | 2022-12-13 | Not Started | 2022-03-08 | 2022-03-08 | Not Started | 2022-03-09 | 2022-03-29 | Not Started | 2022-11-16 | 2022-11-29 | Not Started | 2023-01-17 | Not Started | 2023-01-17 | Not Started | 2023-01-30 | Not Started | 2023-01-17 | Not Started | 2023-03-07 | Not Started | 2023-04-05 | Not Started | 2023-04-18 | 2023-06-06 | -49 | Behind Schedule | Not Started | 2023-06-07 | 2023-06-20 | Not Started | 2023-08-03 | Not Started
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | E.5034805.01.20 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 834 | 0 | 834 | 0.15795 | 0 | 0.15795 | 0 | 0.15795 | [5 empty] | 118750 | 0 | 118750 |  |  | 27453.2 | 0 | 91296.8 | On/Under Budget | Budget Allocated | 300000 | 32111 | 267889 | 32111 | 267889 | 33848.8 | 984.4 | -2500 | 3484.4 | 0 | 0 | 0 | 27453.2 | 1536 | 202.4 | 0 | 474 | 2272 | 30014 | -2807 | 984 | 196 | 196 | 196 | 196 | 196 | 196 | 2021-06-18 | 159383 | BL-A: | BL-A: 35227010_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3_08W - B1_Apr 21 | 2021-04-21 | 2022-03-21 | Not Started | 2022-11-30 | 2022-12-06 | Not Started | 2022-11-29 | Not Started | 2022-12-27 | Not Started | 2022-03-22 | 2022-12-09 | Not Started | 2022-12-12 | 2022-12-30 | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-31 | Not Started | 2023-01-31 | Not Started | 2023-02-13 | Not Started | 2023-01-31 | Not Started | 2023-03-21 | Not Started | 2023-04-19 | Not Started | 2023-04-18 | 2023-06-20 | -63 | Behind Schedule | Not Started | 2023-06-21 | 2023-07-04 | Not Started | 2023-08-17 | Not Started
35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | E.5034805.01.21 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 168 | 0 | 168 | 0.031818 | 0 | 0.031818 | 0 | 0.031818 | [5 empty] | 118750 | 0 | 118750 |  |  | 23958 | 0 | 94792 | On/Under Budget | Budget Allocated | 300000 | 30101 | 269899 | 30101 | 269899 | 31536.8 | 2596.4 | -2500 | 5096.4 | 0 | 0 | 0 | 23957.9 | 1269 | 167.2 | 0 | 0 | 0 | 28708 | -2250 | 2596 | 174 | 174 | 174 | 174 | 174 | 174 | 2021-06-18 | 159392 | BL-A: | BL-A: 35227013_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4_08W - B1_Apr 21 | 2021-04-21 | 2022-03-21 | Not Started | 2022-11-30 | 2022-12-06 | Not Started | 2022-11-29 | Not Started | 2022-12-27 | Not Started | 2022-03-22 | 2022-12-09 | Not Started | 2022-12-12 | 2022-12-30 | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-31 | Not Started | 2023-01-31 | Not Started | 2023-02-13 | Not Started | 2023-01-31 | Not Started | 2023-03-21 | Not Started | 2023-04-19 | Not Started | 2023-04-18 | 2023-06-20 | -63 | Behind Schedule | Not Started | 2023-06-21 | 2023-07-04 | Not Started | 2023-08-17 | Not Started
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | E.5034805.01.22 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 5106 | 0 | 5106 | 0.96705 | 0 | 0.96705 | 0 | 0.96705 | [5 empty] | 118750 | 0 | 118750 |  |  | 1527.1 | 0 | 117222.9 | On/Under Budget | Budget Allocated | 300000 | 4117 | 295883 | 4117 | 295883 | 4434.9 | 2446.8 | 0 | 2446.8 | 0 | 0 | 0 | 1527.1 | 280.7 | 37 | 0 | 0 | 911 | 607 | 9 | 2447 | 24 | 24 | 24 | 24 | 24 | 24 | 2021-06-18 | 159386 | BL-A: | BL-A: 35227015_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5_08W - B1_Apr 21 | 2021-04-21 | 2022-03-21 | Not Started | 2022-11-30 | 2022-12-06 | Not Started | 2022-11-29 | Not Started | 2022-12-27 | Not Started | 2022-03-22 | 2022-03-22 | Not Started | 2022-03-23 | 2022-04-12 | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-31 | Not Started | 2023-01-31 | Not Started | 2023-02-13 | Not Started | 2023-01-31 | Not Started | 2023-03-21 | Not Started | 2023-04-19 | Not Started | 2023-04-18 | 2023-06-20 | -63 | Behind Schedule | Not Started | 2023-06-21 | 2023-07-04 | Not Started | 2023-08-17 | Not Started
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | E.5034805.01.23 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 6312 | 0 | 6312 | 1.1955 | 0 | 1.1955 | 0 | 1.1955 | [5 empty] | 118750 | 0 | 118750 |  |  | 2314.1 | 0 | 116435.9 | On/Under Budget | Budget Allocated | 300000 | 4937 | 295063 | 4937 | 295063 | 5323.2 | 2451.5 | 0 | 2451.5 | 0 | 0 | 0 | 2314.2 | 340.9 | 44.9 | 0 | 593 | 1240 | 469 | 13 | 2452 | 29 | 29 | 29 | 29 | 29 | 29 | 2021-06-18 | 159377 | BL-A: | BL-A: 35227018_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6_08W - B1_Apr 21 | 2021-04-21 | 2022-03-21 | Not Started | 2022-11-30 | 2022-12-06 | Not Started | 2022-11-29 | Not Started | 2022-12-27 | Not Started | 2022-03-22 | 2022-12-09 | Not Started | 2022-12-12 | 2022-12-30 | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-31 | Not Started | 2023-01-31 | Not Started | 2023-02-13 | Not Started | 2023-01-31 | Not Started | 2023-03-21 | Not Started | 2023-04-19 | Not Started | 2023-04-18 | 2023-06-20 | -63 | Behind Schedule | Not Started | 2023-06-21 | 2023-07-04 | Not Started | 2023-08-17 | Not Started
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | E.5034805.01.24 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 1144 | 0 | 1144 | 0.21667 | 0 | 0.21667 | 0 | 0.21667 | [5 empty] | 118750 | 0 | 118750 |  |  | 25249.7 | 0 | 93500.3 | On/Under Budget | Budget Allocated | 300000 | 31447 | 268553 | 31447 | 268553 | 32994.7 | 2604.1 | -2500 | 5104.1 | 0 | 0 | 0 | 25249.7 | 1367.7 | 180.2 | 0 | 593 | 574 | 29403 | -2819 | 2604 | 182 | 182 | 182 | 182 | 182 | 182 | 2021-06-18 | 159388 | BL-A: | BL-A: 35227021_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7_08W - B1_Apr 21 | 2021-04-21 | 2022-03-21 | Not Started | 2022-11-30 | 2022-12-06 | Not Started | 2022-11-29 | Not Started | 2022-12-27 | Not Started | 2022-03-22 | 2022-12-09 | Not Started | 2022-12-12 | 2022-12-30 | Not Started | 2022-11-30 | 2022-12-13 | Not Started | 2023-01-31 | Not Started | 2023-01-31 | Not Started | 2023-02-13 | Not Started | 2023-01-31 | Not Started | 2023-03-21 | Not Started | 2023-04-19 | Not Started | 2023-04-18 | 2023-06-20 | -63 | Behind Schedule | Not Started | 2023-06-21 | 2023-07-04 | Not Started | 2023-08-17 | Not Started
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | E.5034805.01.25 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 2900 | 0 | 0 | 2900 | 0.54924 | 0 | 0.54924 | 0 | 0.54924 | [5 empty] | 118750 | 0 | 118750 |  |  | 26102.5 | 0 | 92647.5 | On/Under Budget | Budget Allocated | 500000 | 32200 | 467800 | 32200 | 467800 | 33685.9 | 2608.4 | -2370.4 | 4978.8 | 0 | 0 | 0 | 26102.5 | 1422.9 | 62.5 | 0 | 237 | 572 | 29779 | -2115 | 2608 | 187 | 187 | 187 | 187 | 187 | 187 | 2021-06-18 | 159376 | BL-A: | BL-A: 35227025_ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8_08W - B1_Apr 21 | 2021-04-21 | 2021-12-20 | Not Started | 2022-09-22 | 2022-09-28 | Not Started | 2022-09-21 | Not Started | 2022-10-19 | Not Started | 2021-12-21 | 2022-09-09 | Not Started | 2022-09-12 | 2022-09-30 | Not Started | 2022-08-31 | 2022-09-13 | Not Started | 2022-11-23 | Not Started | 2022-11-23 | Not Started | 2022-12-06 | Not Started | 2022-11-23 | Not Started | 2023-01-11 | Not Started | 2023-02-09 | Not Started | 2023-03-21 | 2023-04-12 | -22 | Behind Schedule | Not Started | 2023-04-13 | 2023-04-26 | Not Started | 2023-06-09 | Not Started
35231620 | CWSP - HIGHLANDS 1102628 PH 1.2 | E.5034697.01.02 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 14141 | 0 | 0 | 14141 | 2.6782 | 0 | 2.6782 | 0 | 2.6782 | [5 empty] | 73077 | 0 | 73077 |  |  | 3146.3 | 33269 | 36661.7 | On/Under Budget | Request 2021 Budget | 0 | 4711 | -4711 | 4711 | -4711 | 4711 | 2430.3 | 865.6 | 1564.7 | 0 | 0 | 0 | 3146.3 | 0 | 0 | 0 | 0 | 0 | 867 | 1414 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231621 | CWSP - HIGHLANDS 1102628 PH 1.3 | E.5034697.01.03 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 7210 | 0 | 0 | 7210 | 1.3655 | 0 | 1.3655 | 0 | 1.3655 | [5 empty] | 73077 | 0 | 73077 |  |  | 2964.1 | 121427 | -51314.1 | OverRun | Request 2021 Budget | 0 | 4487 | -4487 | 4487 | -4487 | 4487.2 | 2430.3 | 907.2 | 1523.1 | 0 | 0 | 0 | 2964 | 0 | 0 | 0 | 0 | 0 | 644 | 1413 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231622 | CWSP - HIGHLANDS 1102628 PH 1.4 | E.5034697.01.04 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH - Remote Grid | LAKEPORT | Yosemite Assets | 24499 | 0 | 24499 | 48998 | 9.2799 | 0 | 9.2799 | 0 | 9.2799 | [5 empty] | 73077 | 0 | 73077 |  |  | 2966.1 | 158496 | -88385.1 | OverRun | Request 2021 Budget | 0 | 4531 | -4531 | 4531 | -4531 | 4530.8 | 2430.3 | 865.6 | 1564.7 | 0 | 0 | 0 | 2966.1 | 0 | 0 | 0 | 0 | 0 | 688 | 1413 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231623 | CWSP - HIGHLANDS 1102628 PH 1.5 | E.5034697.01.05 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH - Remote Grid | LAKEPORT | Yosemite Assets | 0 | 1078 | 14963 | 16041 | 3.0381 | 0 | 3.0381 | 0 | 3.0381 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 797 | -797 | 797 | -797 | 797.4 | 797.4 | 0 | 797.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231624 | CWSP - HIGHLANDS 1102628 PH 1.6 | E.5034697.01.06 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 4096 | 0 | 4096 | 0.77576 | 0 | 0.77576 | 0 | 0.77576 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 797 | -797 | 797 | -797 | 797.4 | 797.4 | 0 | 797.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231625 | CWSP - HIGHLANDS 1102628 PH 1.7 | E.5034697.01.07 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH - Remote Grid | LAKEPORT | Yosemite Assets | 0 | 0 | 1000 | 1000 | 0.18939 | 0 | 0.18939 | 0 | 0.18939 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 797 | -797 | 797 | -797 | 797.4 | 797.4 | 0 | 797.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | E.5034610.01.15 | 5794205 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 7867 | 0 | 0 | 7867 | 1.49 | 0 | 1.49 | 0 | 1.49 | [5 empty] | 250000 | 0 | 250000 |  |  | 2875.3 | 0 | 247124.7 | On/Under Budget | Request 2021 Budget | 0 | 9984 | -9984 | 9984 | -9984 | 10334.7 | 95.7 | -6434.4 | 6530.1 | 0 | 0 | 0 | 2875.3 | 350.1 | 0 | 0 | 0 | 898 | 18427 | -10015 | 96 | 97 | 97 | 97 | 97 | 97 | 97 | 2021-06-18 | 157807 | BL-A | BL-A 35228186_CWSP - Middletown 1103 - LR 830 PH2.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-07-23 | Not Started | 2021-07-26 | 2021-07-30 | Not Started | 2021-11-12 | Not Started | 2021-11-15 | Not Started | 2021-07-26 | 2021-07-26 | Not Started | 2021-07-27 | 2021-08-16 | Not Started | 2021-11-15 | 2021-11-26 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-07-08 | 2022-06-21 | 17 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35228774 | PSPS - DUNBAR 1101 - OAKMONT PH 2 | E.5034761.01.02 | 5794985 | UNSE | 08W | [6 empty] | 2021 |  | SH | STROSA | Sierra Assets | 5284 | 0 | 0 | 5284 | 1.0008 | 0 | 1.0008 | 0 | 1.0008 | [5 empty] | 1 | 1 | 0 |  |  | 339.8 | 0 | -339.8 | OverRun | Request 2021 Budget | 0 | 112 | -112 | 112 | -112 | 111.7 | 0 | 228.1 | -228.1 | 0 | 0 | 0 | 339.8 | 0 | 0 | 0 | 0 | 0 | 37 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-27 | Not Started | 2021-11-02 | 2021-11-08 | Not Started | 2021-11-01 | Not Started | 2021-11-29 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-07-05 | 2022-07-05 | 0 | On/ Ahead Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35228775 | PSPS - DUNBAR 1101 - OAKMONT PH 3 | E.5034761.01.03 | 5794985 | UNSE | 08W | [6 empty] | 2021 |  | SH | STROSA | Sierra Assets | 4770 | 0 | 0 | 4770 | 0.90341 | 0 | 0.90341 | 0 | 0.90341 | [5 empty] | 1 | 1 | 0 |  |  | 637.6 | 0 | -637.6 | OverRun | Request 2021 Budget | 0 | 112 | -112 | 112 | -112 | 111.7 | 0 | 525.9 | -525.9 | 0 | 0 | 0 | 637.6 | 0 | 0 | 0 | 0 | 0 | 37 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-27 | Not Started | 2021-12-14 | 2021-12-20 | Not Started | 2021-12-13 | Not Started | 2022-01-10 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-12-14 | 2021-12-27 | Not Started | 2022-02-02 | Not Started | 2022-02-02 | Not Started | 2022-02-15 | Not Started | 2022-02-02 | Not Started | 2022-05-17 | Not Started | 2022-06-15 | Not Started | 2022-08-16 | 2022-08-16 | 0 | On/ Ahead Schedule | Not Started | 2022-08-17 | 2022-08-30 | Not Started | 2022-10-13 | Not Started
35229043 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 |  | 5795419 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE |  | 1935 | 0 | 0 | 1935 | 0.36648 | 0.36648 | 0 | 0.36648 | 0 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS | E.5034827.01.01 | 5795612 | UNSE | 08W | [6 empty] | 2021 |  | SH - Remote Grid | REDBLUFF | North Valley Assets | 0 | 0 | 16051 | 16051 | 3.04 | 3.04 | 0 | 0 | 3.04 | [5 empty] | 950000 | 0 | 950000 |  |  | 62036.8 | 0 | 887963.2 | On/Under Budget | Budget Allocated | 1000000 | 57813 | 942187 | 57813 | 942187 | 57813 | 0 | 4223.8 | -4223.8 | 0 | 0 | 0 | 62036.8 | 0 | 0 | 0 | 6794 | 11832 | 21410 | 17777 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | E.5034610.01.17 | 5794205 | UNSE | 08W | [6 empty] | 2021 |  | SH - Remote Grid | LAKEPORT | Humboldt Division Assets | 0 | 0 | 19694 | 19694 | 3.7299 | 0 | 3.7299 | 0 | 3.7299 | [5 empty] | 250000 | 0 | 250000 |  |  | 957.9 | 0 | 249042.1 | On/Under Budget | Request 2021 Budget | 0 | 958 | -958 | 958 | -958 | 957.9 | 0 | 0 | 0 | 0 | 0 | 0 | 957.9 | 0 | 0 | 0 | 0 | 725 | 228 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157825 | BL-A | BL-A 35228188_CWSP - Middletown 1103 - LR 830 PH2.4_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-02 | Not Started | 2021-08-03 | 2021-08-09 | Not Started | 2021-09-06 | Not Started | 2021-09-27 | Not Started | 2021-08-03 | 2021-08-03 | Not Started | 2021-08-04 | 2021-08-24 | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-10-20 | Not Started | 2021-10-20 | Not Started | 2021-11-02 | Not Started | 2021-10-20 | Not Started | 2022-02-01 | Not Started | 2022-03-02 | Not Started | 2022-02-08 | 2022-03-15 | -35 | Behind Schedule | Not Started | 2022-03-17 | 2022-03-30 | Not Started | 2022-05-12 | Not Started
35231631 | CWSP - HIGHLANDS 1102628 PH 1.13 | E.5034697.01.13 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 2465 | 0 | 2465 | 0.46686 | 0 | 0.46686 | 0 | 0.46686 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 2430 | -2430 | 2430 | -2430 | 2430.3 | 2430.3 | 0 | 2430.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231628 | CWSP - HIGHLANDS 1102628 PH 1.10 | E.5034697.01.10 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH - Remote Grid | LAKEPORT | Yosemite Assets | 0 | 0 | 7861 | 7861 | 1.4888 | 0 | 1.4888 | 0 | 1.4888 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 2430 | -2430 | 2430 | -2430 | 2430.3 | 2430.3 | 0 | 2430.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35231629 | CWSP - HIGHLANDS 1102628 PH 1.11 | E.5034697.01.11 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH - Remote Grid | LAKEPORT | Yosemite Assets | 0 | 0 | 902 | 902 | 0.17083 | 0 | 0.17083 | 0 | 0.17083 | [5 empty] | 73077 | 0 | 73077 |  |  | 0 | 0 | 73077 | On/Under Budget | Request 2021 Budget | 0 | 2430 | -2430 | 2430 | -2430 | 2430.3 | 2430.3 | 0 | 2430.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35233947 | CWSP - OREGON TRAIL 110335002 PH1.2 | E.5034714.01.38 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 9734 | 0 | 9734 | 1.8436 | 0 | 1.8436 | 0 | 1.8436 | [5 empty] | 125000 | 125000 | 0 |  |  | 2734.4 | 0 | -2734.4 | OverRun | Budget Allocated | 500000 | 2048 | 497952 | 2048 | 497952 | 2048.1 | 0 | 686.3 | -686.3 | 0 | 0 | 0 | 2734.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233948 | CWSP - OREGON TRAIL 110335002 PH1.3 | E.5034714.01.39 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 13660 | 0 | 0 | 13660 | 2.5871 | 0 | 2.5871 | 0 | 2.5871 | [5 empty] | 175000 | 175000 | 0 |  |  | 24712.5 | 0 | -24712.5 | OverRun | Budget Allocated | 500000 | 85126 | 414874 | 85126 | 414874 | 85125.6 | 29000 | -2413.1 | 31413.1 | 0 | 0 | 0 | 24712.4 | 0 | 0 | 0 | 0 | 0 | 0 | 27126 | 29000 | 29000 | 0 | 0 | 0 | 0 | 0
35233949 | CWSP - OREGON TRAIL 110335002 PH1.4 | E.5034714.01.40 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 10438 | 0 | 10438 | 1.9769 | 0 | 1.9769 | 0 | 1.9769 | [5 empty] | 125000 | 125000 | 0 |  |  | 4564.3 | 0 | -4564.3 | OverRun | Budget Allocated | 500000 | 3894 | 496106 | 3894 | 496106 | 3894.2 | 0 | 670.1 | -670.1 | 0 | 0 | 0 | 4564.3 | 0 | 0 | 0 | 0 | 0 | 2062 | 1832 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233950 | CWSP - OREGON TRAIL 110335002 PH1.5 | E.5034714.01.41 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 14542 | 0 | 0 | 14542 | 2.7542 | 0 | 2.7542 | 0 | 2.7542 | [5 empty] | 175000 | 175000 | 0 |  |  | 22664.3 | 0 | -22664.3 | OverRun | Budget Allocated | 500000 | 83608 | 416392 | 83608 | 416392 | 83607.8 | 29265.2 | -2413.1 | 31678.3 | 0 | 0 | 0 | 22664.2 | 0 | 0 | 0 | 0 | 0 | 0 | 25077 | 29265 | 29265 | 0 | 0 | 0 | 0 | 0
35233951 | CWSP - OREGON TRAIL 110335002 PH1.6 | E.5034714.01.42 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 8262 | 0 | 8262 | 1.5648 | 0 | 1.5648 | 0 | 1.5648 | [5 empty] | 125000 | 125000 | 0 |  |  | 1042.3 | 0 | -1042.3 | OverRun | Budget Allocated | 428000 | 0 | 428000 | 0 | 428000 | 0 | 0 | 1042.3 | -1042.3 | 0 | 0 | 0 | 1042.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233952 | CWSP - OREGON TRAIL 110335002 PH2.2 | E.5034714.01.08 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 11413 | 0 | 11413 | 2.1616 | 2.1616 | 0 | 0 | 2.1616 | [5 empty] | 100000 | 0 | 100000 |  |  | 2196.5 | 0 | 97803.5 | On/Under Budget | Budget Allocated | 4104000 | 20828 | 4083172 | 20828 | 4083172 | 20827.8 | 2344.3 | 0 | 2344.3 | 0 | 0 | 0 | 2196.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2197 | 2344 | 576 | 158 | 482 | 1299 | 12831 | 942 | 2021-06-18 |  |  |  |  | 2021-09-07 | Not Started | 2021-09-29 | 2021-10-05 | Not Started | 2021-09-28 | Not Started | 2021-11-02 | Not Started | 2021-09-08 | 2021-09-08 | Not Started | 2021-09-09 | 2021-09-29 | Not Started | 2021-09-15 | 2021-09-28 | Not Started | 2021-11-25 | Not Started | 2021-11-25 | Not Started | 2021-12-08 | Not Started | 2021-11-25 | Not Started | 2022-01-19 | Not Started | 2022-02-17 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35233953 | CWSP - OREGON TRAIL 110335002 PH2.3 | E.5034714.01.09 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH - EPC | REDDING | North Valley Assets | 4437 | 0 | 0 | 4437 | 0.84034 | 0 | 0.84034 | 0 | 0.84034 | [5 empty] | 150000 | 0 | 150000 |  |  | 31097.6 | 0 | 118902.4 | On/Under Budget | Budget Allocated | 500000 | 94571 | 405429 | 94571 | 405429 | 94805.6 | 26857.6 | 445.3 | 26412.3 | 0 | 0 | 0 | 31097.6 | 235 | 0 | 0 | 0 | 0 | 520 | 30132 | 26858 | 26507 | 537 | 915 | 1679 | 6208 | 1215 | 2021-06-18 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-05 | 2021-10-11 | Not Started | 2021-10-04 | Not Started | 2021-11-01 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-11-24 | Not Started | 2021-11-24 | Not Started | 2021-12-07 | Not Started | 2021-11-24 | Not Started | 2022-01-18 | Not Started | 2022-02-16 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35233954 | CWSP - OREGON TRAIL 110335002 PH3.2 | E.5034714.01.15 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 1120 | 0 | 1120 | 0.21212 | 0.21212 | 0 | 0 | 0.21212 | [5 empty] | 75000 | 75000 | 0 |  |  | 2048.2 | 0 | -2048.2 | OverRun | Budget Allocated | 400000 | 2048 | 397952 | 2048 | 397952 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233955 | CWSP - OREGON TRAIL 110335002 PH2.4 | E.5034714.01.10 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH - EPC | REDDING | North Valley Assets | 2900 | 0 | 0 | 2900 | 0.54924 | 0 | 0.54924 | 0 | 0.54924 | [5 empty] | 150000 | 0 | 150000 |  |  | 20852.6 | 0 | 129147.4 | On/Under Budget | Budget Allocated | 500000 | 64515 | 435485 | 64515 | 435485 | 64514.8 | 14294 | 250.9 | 14043.1 | 0 | 0 | 0 | 20852.6 | 0 | 0 | 0 | 0 | 0 | 0 | 20602 | 14294 | 14380 | 1753 | 3221 | 6432 | 3645 | 188 | 2021-06-18 |  |  |  |  | 2021-08-02 | Not Started | 2021-08-31 | 2021-09-06 | Not Started | 2021-08-30 | Not Started | 2021-09-13 | Not Started | 2021-08-03 | 2021-08-03 | Not Started | 2021-08-04 | 2021-08-24 | Not Started | 2021-08-31 | 2021-09-13 | Not Started | 2021-10-19 | Not Started | 2021-10-19 | Not Started | 2021-11-01 | Not Started | 2021-10-19 | Not Started | 2022-01-03 | Not Started | 2022-02-01 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35233956 | CWSP - OREGON TRAIL 110335002 PH3.3 | E.5034714.01.16 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 1344 | 0 | 1344 | 0.25455 | 0.25455 | 0 | 0 | 0.25455 | [5 empty] | 75000 | 75000 | 0 |  |  | 2048.2 | 0 | -2048.2 | OverRun | Budget Allocated | 475000 | 2048 | 472952 | 2048 | 472952 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233957 | CWSP - OREGON TRAIL 110335002 PH2.5 | E.5034714.01.11 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH - EPC | REDDING | North Valley Assets | 539 | 0 | 0 | 539 | 0.10208 | 0 | 0.10208 | 0 | 0.10208 | [5 empty] | 125000 | 0 | 125000 |  |  | 5809.2 | 0 | 119190.8 | On/Under Budget | Budget Allocated | 125000 | 33331 | 91669 | 33331 | 91669 | 33330.7 | 12727 | 250.9 | 12476.1 | 0 | 0 | 0 | 5809.2 | 0 | 0 | 0 | 0 | 0 | 0 | 5558 | 12727 | 10173 | 603 | 1310 | 1822 | 1004 | 134 | 2021-06-18 |  |  |  |  | 2021-09-01 | Not Started | 2021-09-09 | 2021-09-15 | Not Started | 2021-09-08 | Not Started | 2021-10-13 | Not Started | 2021-09-02 | 2021-09-02 | Not Started | 2021-09-03 | 2021-09-23 | Not Started | 2021-09-09 | 2021-09-22 | Not Started | 2021-10-22 | Not Started | 2021-10-22 | Not Started | 2021-11-04 | Not Started | 2021-10-22 | Not Started | 2021-12-23 | Not Started | 2022-01-21 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35233958 | CWSP - OREGON TRAIL 110335002 PH3.4 | E.5034714.01.17 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 1099 | 0 | 1099 | 0.20814 | 0.20814 | 0 | 0 | 0.20814 | [5 empty] | 75000 | 75000 | 0 |  |  | 2048.2 | 0 | -2048.2 | OverRun | Budget Allocated | 400000 | 2048 | 397952 | 2048 | 397952 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35233959 | CWSP - OREGON TRAIL 110335002 PH2.6 | E.5034714.01.12 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 1827 | 0 | 1827 | 0.34602 | 0.34602 | 0 | 0 | 0.34602 | [5 empty] | 75000 | 0 | 75000 |  |  | 2048.2 | 0 | 72951.8 | On/Under Budget | Budget Allocated | 665000 | 11020 | 653980 | 11020 | 653980 | 11019.7 | 2770.5 | 0 | 2770.5 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2771 | 158 | 158 | 943 | 2005 | 2450 | 488 | 2021-06-18 |  |  |  |  | 2021-08-25 | Not Started | 2021-09-23 | 2021-09-29 | Not Started | 2021-09-22 | Not Started | 2021-10-20 | Not Started | 2021-08-26 | 2021-08-26 | Not Started | 2021-08-27 | 2021-09-16 | Not Started | 2021-09-23 | 2021-10-06 | Not Started | 2021-11-12 | Not Started | 2021-11-12 | Not Started | 2021-11-25 | Not Started | 2021-11-12 | Not Started | 2022-01-10 | Not Started | 2022-02-08 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35233995 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | E.5034778.01.02 | 5795018 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 2640 | 0 | 0 | 2640 | 0.5 | 0 | 0.5 | 0 | 0.5 | [5 empty] | 315000 | 0 | 315000 |  |  | 6426.7 | 0 | 308573.3 | On/Under Budget | Budget Allocated | 219000 | 218777 | 223 | 218777 | 223 | 1631577.9 | 54546 | -15507.1 | 70053.1 | 0 | 0 | 0 | 6426.8 | 1412801.3 | 0 | 0 | 0 | 0 | 140 | 21794 | 54546 | 65787 | 38018 | 4861 | 12481 | 12481 | 8671 | 2021-05-07 |  |  |  |  | 2022-06-17 | Not Started | 2022-07-25 | 2022-07-29 | Not Started | 2022-07-22 | Not Started | 2022-08-19 | Not Started | 2022-06-20 | 2022-06-20 | Not Started | 2022-06-21 | 2022-07-11 | Not Started | 2022-07-25 | 2022-08-05 | Not Started | 2022-09-13 | Not Started | 2022-09-13 | Not Started | 2022-09-26 | Not Started | 2022-09-13 | Not Started | 2022-12-26 | Not Started | 2023-01-24 | Not Started | 2023-03-27 | 2023-03-27 | 0 | On/ Ahead Schedule | Not Started | 2023-03-28 | 2023-04-10 | Not Started | 2023-05-24 | Not Started
35233996 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | E.5034778.01.03 | 5795018 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 3749.8 | 0 | 0 | 3749.8 | 0.71019 | 0 | 0.71019 | 0 | 0.71019 | [5 empty] | 315000 | 0 | 315000 |  |  | 13450.9 | 0 | 301549.1 | On/Under Budget | Budget Allocated | 255000 | 254808 | 192 | 254808 | 192 | 2252912.8 | 55546 | -16854 | 72400 | 0 | 0 | 0 | 13450.9 | 1998104.6 | 0 | 0 | 0 | 0 | 140 | 30165 | 55546 | 67481 | 53638 | 33257 | 4861 | 4861 | 4861 | 2021-05-07 |  |  |  |  | 2022-06-17 | Not Started | 2022-07-25 | 2022-07-29 | Not Started | 2022-07-22 | Not Started | 2022-08-19 | Not Started | 2022-06-20 | 2022-06-20 | Not Started | 2022-06-21 | 2022-07-11 | Not Started | 2022-07-25 | 2022-08-05 | Not Started | 2022-09-13 | Not Started | 2022-09-13 | Not Started | 2022-09-26 | Not Started | 2022-09-13 | Not Started | 2022-12-26 | Not Started | 2023-01-24 | Not Started | 2023-03-27 | 2023-03-27 | 0 | On/ Ahead Schedule | Not Started | 2023-03-28 | 2023-04-10 | Not Started | 2023-05-24 | Not Started
35234284 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | E.5034764.01.02 | 5794988 | UNSE | 08W | [6 empty] | 2022 |  | SH | JACKSON | Stockton Assets | 0 | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0.32992 | 0 | 0.33 | [5 empty] | 1 | -349999 | 350000 |  |  | 10312.6 | 0 | 339687.4 | On/Under Budget | Request 2021 Budget | 0 | 603692 | -603692 | 603692 | -603692 | 605401.3 | 5.5 | 8571.6 | -8566.1 | 0 | 0 | 0 | 10312.6 | 1709.2 | 0 | 0 | 0 | 0 | 1381 | 360 | 6 | 1408 | 206780 | 188395 | 198335 | 3514 | 3514 | 2021-06-18 | 160556 | BL-A | BL-A 35234284_PSPS - Martell 1101 Ph 1.2_08W - DD 210507 | 2021-05-10 | 2021-09-10 | Not Started | 2021-09-13 | 2021-09-17 | Not Started | 2021-11-26 | Not Started | 2021-11-29 | Not Started | 2021-09-13 | 2021-09-13 | Not Started | 2021-09-14 | 2021-10-04 | Not Started | 2021-11-29 | 2021-12-17 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2021-12-23 | Not Started | 2021-12-22 | Not Started | 2022-01-18 | Not Started | 2022-02-16 | Not Started | 2022-05-03 | 2022-04-19 | 14 | On/ Ahead Schedule | Not Started | 2022-04-20 | 2022-05-03 | Not Started | 2022-06-16 | Not Started
35234380 | CWSP - OREGON TRAIL 110335002 PH3.5 | E.5034714.01.18 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 11837 | 0 | 11837 | 2.2419 | 2.2419 | 0 | 0 | 2.2419 | [5 empty] | 150000 | 150000 | 0 |  |  | 2252.8 | 0 | -2252.8 | OverRun | Budget Allocated | 3500000 | 2253 | 3497747 | 2253 | 3497747 | 2252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2252.8 | 0 | 0 | 0 | 0 | 0 | 0 | 2253 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234381 | CWSP - OREGON TRAIL 110335002 PH2.7 | E.5034714.01.13 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 8167 | 0 | 8167 | 1.5468 | 1.5468 | 0 | 0 | 1.5468 | [5 empty] | 100000 | 0 | 100000 |  |  | 2048.2 | 0 | 97951.8 | On/Under Budget | Budget Allocated | 2945000 | 17162 | 2927838 | 17162 | 2927838 | 17162.3 | 2422 | 0 | 2422 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2422 | 158 | 258 | 1259 | 9427 | 1311 | 280 | 2021-06-18 |  |  |  |  | 2021-08-19 | Not Started | 2021-09-24 | 2021-09-30 | Not Started | 2021-09-23 | Not Started | 2021-10-21 | Not Started | 2021-08-20 | 2021-08-20 | Not Started | 2021-08-23 | 2021-09-10 | Not Started | 2021-09-24 | 2021-10-07 | Not Started | 2021-11-01 | Not Started | 2021-11-01 | Not Started | 2021-11-12 | Not Started | 2021-11-01 | Not Started | 2021-12-31 | Not Started | 2022-01-31 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35234382 | CWSP - OREGON TRAIL 110335002 PH2.8 | E.5034714.01.14 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 8382 | 0 | 8382 | 1.5875 | 1.5875 | 0 | 0 | 1.5875 | [5 empty] | 100000 | 0 | 100000 |  |  | 3868.8 | 0 | 96131.2 | On/Under Budget | Budget Allocated | 3021000 | 19553 | 3001447 | 19553 | 3001447 | 19553 | 2770.5 | 0 | 2770.5 | 0 | 0 | 0 | 3868.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3869 | 2771 | 158 | 308 | 1260 | 9644 | 1263 | 282 | 2021-06-18 |  |  |  |  | 2021-08-25 | Not Started | 2021-09-23 | 2021-09-29 | Not Started | 2021-09-22 | Not Started | 2021-10-20 | Not Started | 2021-08-26 | 2021-08-26 | Not Started | 2021-08-27 | 2021-09-16 | Not Started | 2021-09-23 | 2021-10-06 | Not Started | 2021-10-29 | Not Started | 2021-10-29 | Not Started | 2021-11-11 | Not Started | 2021-10-29 | Not Started | 2021-12-30 | Not Started | 2022-01-28 | Not Started | 2022-03-31 | 2022-03-31 | 0 | On/ Ahead Schedule | Not Started | 2022-04-01 | 2022-04-14 | Not Started | 2022-05-30 | Not Started
35234383 | CWSP - OREGON TRAIL 110335002 PH3.6 | E.5034714.01.19 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 6328 | 0 | 0 | 6328 | 1.1985 | 0 | 1.1985 | 0 | 1.1985 | [5 empty] | 150000 | 150000 | 0 |  |  | 48154.9 | 0 | -48154.9 | OverRun | Budget Allocated | 500000 | 98754 | 401246 | 98754 | 401246 | 98754 | 30000 | 9400.9 | 20599.1 | 0 | 0 | 0 | 48154.9 | 0 | 0 | 0 | 0 | 0 | 0 | 38754 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0
35234384 | CWSP - OREGON TRAIL 110335002 PH3.7 | E.5034714.01.20 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 307 | 0 | 307 | 0.058144 | 0.058144 | 0 | 0 | 0.058144 | [5 empty] | 75000 | 75000 | 0 |  |  | 2048.2 | 0 | -2048.2 | OverRun | Budget Allocated | 150000 | 2048 | 147952 | 2048 | 147952 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234385 | CWSP - OREGON TRAIL 110335002 PH3.8 | E.5034714.01.21 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 3561 | 0 | 3561 | 0.67443 | 0.67443 | 0 | 0 | 0.67443 | [5 empty] | 100000 | 100000 | 0 |  |  | 3868.8 | 0 | -3868.8 | OverRun | Budget Allocated | 1273000 | 3869 | 1269131 | 3869 | 1269131 | 3868.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3868.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234386 | CWSP - OREGON TRAIL 110335002 PH3.9 | E.5034714.01.22 | 5794555 | UNSE | 08W | [6 empty] | 2021 |  | SH - EPC | REDDING | North Valley Assets | 0 | 4529 | 0 | 4529 | 0.85777 | 0.85777 | 0 | 0 | 0.85777 | [5 empty] | 100000 | 100000 | 0 |  |  | 2064.4 | 0 | -2064.4 | OverRun | Budget Allocated | 1634000 | 2048 | 1631952 | 2048 | 1631952 | 2048.2 | 0 | 16.2 | -16.2 | 0 | 0 | 0 | 2064.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234387 | CWSP - OREGON TRAIL 110335002 PH4.2 | E.5034714.01.23 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 4963 | 0 | 4963 | 0.93996 | 0.93996 | 0 | 0 | 0.93996 | [5 empty] | 125000 | 0 | 125000 |  |  | 2048.2 | 0 | 122951.8 | On/Under Budget | Request 2021 Budget | 0 | 13747 | -13747 | 13747 | -13747 | 13746.8 | 2247.5 | 0 | 2247.5 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2248 | 158 | 591 | 1355 | 6305 | 787 | 256 | 2021-06-04 |  |  |  |  | 2021-08-04 | Not Started | 2021-08-05 | 2021-08-11 | Not Started | 2021-07-28 | Not Started | 2021-09-29 | Not Started | 2021-08-05 | 2021-08-05 | Not Started | 2021-08-06 | 2021-08-19 | Not Started | 2021-08-19 | 2021-09-01 | Not Started | 2021-10-08 | Not Started | 2021-10-08 | Not Started | 2021-10-21 | Not Started | 2021-10-08 | Not Started | 2021-12-02 | Not Started | 2021-12-31 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35234388 | CWSP - OREGON TRAIL 110335002 PH4.3 | E.5034714.01.24 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 10772 | 0 | 10772 | 2.0402 | 2.0402 | 0 | 0 | 2.0402 | [5 empty] | 125000 | 0 | 125000 |  |  | 2048.2 | 0 | 122951.8 | On/Under Budget | Request 2021 Budget | 0 | 19517 | -19517 | 19517 | -19517 | 19517.2 | 2072.9 | 0 | 2072.9 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2073 | 158 | 728 | 2645 | 11265 | 300 | 300 | 2021-06-04 |  |  |  |  | 2021-08-03 | Not Started | 2021-08-04 | 2021-08-10 | Not Started | 2021-07-20 | Not Started | 2021-09-28 | Not Started | 2021-08-04 | 2021-08-04 | Not Started | 2021-08-05 | 2021-08-18 | Not Started | 2021-08-11 | 2021-08-24 | Not Started | 2021-10-07 | Not Started | 2021-10-07 | Not Started | 2021-10-20 | Not Started | 2021-10-07 | Not Started | 2021-12-01 | Not Started | 2021-12-17 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35234389 | CWSP - OREGON TRAIL 110335002 PH4.4 | E.5034714.01.25 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 4752 | 0 | 4752 | 0.9 | 0.9 | 0 | 0 | 0.9 | [5 empty] | 125000 | 0 | 125000 |  |  | 2048.2 | 0 | 122951.8 | On/Under Budget | Request 2021 Budget | 0 | 13627 | -13627 | 13627 | -13627 | 13627.5 | 2068.1 | 0 | 2068.1 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2068 | 419 | 688 | 1940 | 5725 | 486 | 254 | 2021-06-04 |  |  |  |  | 2021-08-23 | Not Started | 2021-08-24 | 2021-08-30 | Not Started | 2021-08-16 | Not Started | 2021-10-04 | Not Started | 2021-08-24 | 2021-08-24 | Not Started | 2021-08-25 | 2021-08-31 | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-10-07 | Not Started | 2021-10-07 | Not Started | 2021-10-20 | Not Started | 2021-10-07 | Not Started | 2021-12-01 | Not Started | 2021-12-23 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35234390 | CWSP - OREGON TRAIL 110335002 PH4.5 | E.5034714.01.26 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 2746 | 0 | 2746 | 0.52008 | 0.52008 | 0 | 0 | 0.52008 | [5 empty] | 125000 | 0 | 125000 |  |  | 2048.2 | 0 | 122951.8 | On/Under Budget | Request 2021 Budget | 0 | 12014 | -12014 | 12014 | -12014 | 12013.7 | 2060 | 0 | 2060 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2060 | 855 | 746 | 2015 | 3638 | 412 | 239 | 2021-06-04 |  |  |  |  | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-06 | Not Started | 2021-08-23 | Not Started | 2021-09-27 | Not Started | 2021-08-31 | 2021-08-31 | Not Started | 2021-09-01 | 2021-09-21 | Not Started | 2021-09-14 | 2021-09-27 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-19 | Not Started | 2021-10-06 | Not Started | 2021-11-30 | Not Started | 2021-12-22 | Not Started | 2022-02-15 | 2022-02-15 | 0 | On/ Ahead Schedule | Not Started | 2022-02-16 | 2022-03-01 | Not Started | 2022-04-14 | Not Started
35234391 | CWSP - OREGON TRAIL 110335002 PH4.6 | E.5034714.01.27 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 6653 | 0 | 6653 | 1.26 | 1.26 | 0 | 0 | 1.26 | [5 empty] | 125000 | 0 | 125000 |  |  | 2048.2 | 0 | 122951.8 | On/Under Budget | Request 2021 Budget | 0 | 16001 | -16001 | 16001 | -16001 | 16001.1 | 2060 | 0 | 2060 | 0 | 0 | 0 | 2048.2 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 2060 | 855 | 746 | 2799 | 6782 | 442 | 269 | 2021-06-04 |  |  |  |  | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-06 | Not Started | 2021-08-23 | Not Started | 2021-09-27 | Not Started | 2021-08-31 | 2021-08-31 | Not Started | 2021-09-01 | 2021-09-21 | Not Started | 2021-09-14 | 2021-09-27 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-10-19 | Not Started | 2021-10-06 | Not Started | 2021-11-30 | Not Started | 2021-12-22 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35234392 | CWSP - OREGON TRAIL 110335002 PH4.7 | E.5034714.01.28 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 8765 | 0 | 8765 | 1.66 | 1.66 | 0 | 0 | 1.66 | [5 empty] | 125000 | 0 | 125000 |  |  | 3868.8 | 0 | 121131.2 | On/Under Budget | Request 2021 Budget | 0 | 19591 | -19591 | 19591 | -19591 | 19591.4 | 2068.1 | 0 | 2068.1 | 0 | 0 | 0 | 3868.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3869 | 2068 | 419 | 969 | 7521 | 4016 | 444 | 285 | 2021-06-04 |  |  |  |  | 2021-08-23 | Not Started | 2021-08-24 | 2021-08-30 | Not Started | 2021-08-16 | Not Started | 2021-09-20 | Not Started | 2021-08-24 | 2021-08-24 | Not Started | 2021-08-25 | 2021-09-07 | Not Started | 2021-09-07 | 2021-09-20 | Not Started | 2021-09-29 | Not Started | 2021-09-29 | Not Started | 2021-10-12 | Not Started | 2021-09-29 | Not Started | 2021-11-23 | Not Started | 2021-12-22 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35234393 | CWSP - OREGON TRAIL 110335002 PH5.2 | E.5034714.01.29 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 12778 | 0 | 12778 | 2.4201 | 0 | 2.4201 | 0 | 2.4201 | [5 empty] | 158334 | 0 | 158334 |  |  | 0 | 0 | 158334 | On/Under Budget | Budget Allocated | 500000 | 5531 | 494469 | 5531 | 494469 | 25474 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 0 | 19942.6 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35234394 | CWSP - OREGON TRAIL 110335002 PH5.3 | E.5034714.01.30 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 9451 | 0 | 9451 | 1.79 | 0 | 1.79 | 0 | 1.79 | [5 empty] | 158334 | 0 | 158334 |  |  | 0 | 0 | 158334 | On/Under Budget | Budget Allocated | 364000 | 5531 | 358469 | 5531 | 358469 | 21849.8 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 0 | 16318.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35234395 | CWSP - OREGON TRAIL 110335002 PH5.4 | E.5034714.01.31 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 14309 | 0 | 14309 | 2.71 | 0 | 2.71 | 0 | 2.71 | [5 empty] | 158334 | 0 | 158334 |  |  | 0 | 0 | 158334 | On/Under Budget | Budget Allocated | 536000 | 5531 | 530469 | 5531 | 530469 | 27141.7 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 0 | 21610.3 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35234396 | CWSP - OREGON TRAIL 110335002 PH5.5 | E.5034714.01.32 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 8923 | 0 | 8923 | 1.69 | 0 | 1.69 | 0 | 1.69 | [5 empty] | 158334 | 0 | 158334 |  |  | 0 | 0 | 158334 | On/Under Budget | Budget Allocated | 404000 | 5531 | 398469 | 5531 | 398469 | 21274.6 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 0 | 15743.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35234397 | CWSP - OREGON TRAIL 110335002 PH5.6 | E.5034714.01.33 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 3802 | 0 | 3802 | 0.72008 | 0 | 0.72008 | 0 | 0.72008 | [5 empty] | 158334 | 0 | 158334 |  |  | 0 | 0 | 158334 | On/Under Budget | Budget Allocated | 352000 | 5531 | 346469 | 5531 | 346469 | 15696.1 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 0 | 10164.7 | 0 | 0 | 0 | 0 | 0 | 0 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35234398 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | E.5034714.01.34 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 15061 | 0 | 15061 | 2.8525 | 0 | 2.8525 | 0 | 2.8525 | [5 empty] | 180000 | 0 | 180000 |  |  | 2064.4 | 0 | 177935.6 | On/Under Budget | Budget Allocated | 660000 | 2048 | 657952 | 2048 | 657952 | 2048.2 | 0 | 16.2 | -16.2 | 0 | 0 | 0 | 2064.4 | 0 | 0 | 0 | 0 | 0 | 0 | 2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234399 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | E.5034714.01.35 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 2535 | 0 | 0 | 2535 | 0.48011 | 0 | 0.48011 | 0 | 0.48011 | [5 empty] | 230000 | 0 | 230000 |  |  | 41127.7 | 0 | 188872.3 | On/Under Budget | Budget Allocated | 382000 | 75530 | 306470 | 75530 | 306470 | 75529.5 | 25228.6 | 16055.4 | 9173.2 | 0 | 0 | 0 | 41127.7 | 0 | 0 | 0 | 0 | 0 | 0 | 25072 | 25229 | 25229 | 0 | 0 | 0 | 0 | 0
35234400 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | E.5034714.01.36 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 7339 | 0 | 7339 | 1.39 | 0 | 1.39 | 0 | 1.39 | [5 empty] | 180000 | 0 | 180000 |  |  | 909.6 | 0 | 179090.4 | On/Under Budget | Budget Allocated | 424000 | 0 | 424000 | 0 | 424000 | 0 | 0 | 909.6 | -909.6 | 0 | 0 | 0 | 909.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234401 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | E.5034714.01.37 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 9768 | 0 | 9768 | 1.85 | 0 | 1.85 | 0 | 1.85 | [5 empty] | 180000 | 0 | 180000 |  |  | 909.6 | 0 | 179090.4 | On/Under Budget | Budget Allocated | 560000 | 0 | 560000 | 0 | 560000 | 0 | 0 | 909.6 | -909.6 | 0 | 0 | 0 | 909.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35234526 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | E.5034764.01.03 | 5794988 | UNSE | 08W | [6 empty] | 2022 |  | SH | JACKSON | Stockton Assets | 3115.2 | 0 | 0 | 3115.2 | 0.59 | 0 | 0.58996 | 0 | 0.59 | [5 empty] | 1 | -299999 | 300000 |  |  | 31299.4 | 0 | 268700.6 | On/Under Budget | Budget Allocated | 100000 | 1101672 | -1001672 | 1101672 | -1001672 | 1111022.3 | 5.5 | 29564.8 | -29559.3 | 0 | 0 | 0 | 31299.4 | 9350.6 | 0 | 0 | 0 | 0 | 1375 | 360 | 6 | 23740 | 346249 | 356822 | 355638 | 11064 | 6418 | 2021-06-18 | 160557 | BL-A | BL-A 35234526_PSPS - Martell 1101 Ph 1.3_08W - DD 210507 | 2021-05-10 | 2021-09-10 | Not Started | 2021-09-13 | 2021-09-17 | Not Started | 2021-11-26 | Not Started | 2021-11-29 | Not Started | 2021-09-13 | 2021-09-13 | Not Started | 2021-09-14 | 2021-10-04 | Not Started | 2021-11-29 | 2021-12-17 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-02-22 | Not Started | 2022-03-23 | Not Started | 2022-06-20 | 2022-05-24 | 27 | On/ Ahead Schedule | Not Started | 2022-05-25 | 2022-06-07 | Not Started | 2022-07-21 | Not Started
35234527 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.2 |  | 5794984 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234528 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.3 |  | 0000000 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234529 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.4 |  | 5794984 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | E.5034805.01.31 | 5795300 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 14689 | 0 | 0 | 14689 | 2.782 | 0 | 2.782 | 0 | 2.782 | [5 empty] | 300000 | 300000 | 0 |  |  | 779.5 | 0 | -779.5 | OverRun | Request 2021 Budget | 0 | 71313 | -71313 | 71313 | -71313 | 71313.3 | 2430.3 | -68103.5 | 70533.8 | 0 | 0 | 0 | 779.6 | 0 | 0 | 0 | 0 | 0 | 229 | 68654 | 2430 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-20 | Not Started | 2021-11-30 | 2021-12-06 | Not Started | 2021-11-29 | Not Started | 2021-12-27 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-11-30 | 2021-12-13 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-08-02 | 2022-08-02 | 0 | On/ Ahead Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35244573 | FRRB - WYANDOTTE 11031974 - W3 SM1 | E.5034933.01.10 | 5796539 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 700 | 0 | 0 | 700 | 0.13258 | 0.13258 | 0 | 0 | 0.13258 | [5 empty] | 100000 | 0 | 100000 |  |  | 1695.6 | 0 | 98304.4 | On/Under Budget | Budget Allocated | 464015.1515 | 465666 | -1650.8485 | 470666 | -6650.8485 | 470665.6 | 5006.5 | 74.5 | 4932 | 0 | 0 | 0 | 1695.7 | 0 | 0 | 0 | 0 | 0 | 1612 | 9 | 7 | 7 | 464022 | 7 | 3 | 0 | 0 | 2021-03-08 |  |  |  |  | 2021-05-10 | Not Started | 2021-05-25 | 2021-05-31 | Not Started | 2021-05-24 | Not Started | 2021-07-05 | Not Started | [6 empty] | 2021-05-07 | 2021-05-13 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-09-22 | Not Started | 2021-07-07 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-11-05 | 2021-11-05 | 0 | On/ Ahead Schedule | Not Started | 2021-11-05 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35244574 | FRRB - WYANDOTTE 11031974 - W3 SM2 | E.5034933.01.11 | 5796539 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 350 | 0 | 0 | 350 | 0.066288 | 0.066288 | 0 | 0 | 0.066288 | [5 empty] | 100000 | 0 | 100000 |  |  | 0 | 0 | 100000 | On/Under Budget | Budget Allocated | 232007.5758 | 237008 | -5000.4242 | 237008 | -5000.4242 | 237008 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 232008 | 0 | 0 | 0 | 0 | 2021-03-08 |  |  |  |  | 2021-05-10 | Not Started | 2021-05-25 | 2021-05-31 | Not Started | 2021-05-24 | Not Started | 2021-07-05 | Not Started | [6 empty] | 2021-05-07 | 2021-05-13 | Not Started | 2021-07-07 | Not Started | 2021-07-07 | Not Started | 2021-09-22 | Not Started | 2021-07-07 | Not Started | 2021-10-06 | Not Started | 2021-10-06 | Not Started | 2021-11-05 | 2021-11-05 | 0 | On/ Ahead Schedule | Not Started | 2021-11-05 | 2021-11-19 | Not Started | 2022-01-04 | Not Started
35246219 | BR-08-03-W (E) NOORWOOD PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 89.2 | 0 | -89.2 | OverRun | Project is not in the WP or in 2020 WP | 0 | 184 | -184 | 184 | -184 | 184.2 | 0 | -95 | 95 | 0 | 0 | 0 | 89.2 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246309 | BR-05-01-W (E) SKYWAY PH 4 PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 1047.1 | 0 | -1047.1 | OverRun | Project is not in the WP or in 2020 WP | 0 | 1050 | -1050 | 1050 | -1050 | 1049.6 | 0 | -2.5 | 2.5 | 0 | 0 | 0 | 1047 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246316 | BR-11-08-W (E) WAYLAND PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 1893.6 | 0 | -1893.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 96 | -96 | 96 | -96 | 96.2 | 0 | 1797.4 | -1797.4 | 0 | 0 | 0 | 1893.6 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246501 | REMG - FULTON1107604 |  | 5796874 | UNSE | 08W | [6 empty] | Not in the WP |  | SH - Remote Grid | STROSA |  | 0 | 0 | 3802 | 3802 | 0.72008 | 0 | 0.72008 | 0 | 0.72008 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35246589 | BR-05-06 W (E) KLING CT PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 2233.6 | 0 | -2233.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 96 | -96 | 96 | -96 | 96.2 | 0 | 2137.4 | -2137.4 | 0 | 0 | 0 | 2233.6 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249871 | CWSP - COARSEGOLD 21045310 PH 1.2 | E.5034895.01.07 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 10658 | 0 | 10658 | 2.0186 | 0 | 0 | 0 | 2.0186 | [5 empty] | 317000 | 0 | 317000 |  |  | 0 | 0 | 317000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249872 | CWSP - COARSEGOLD 21045310 PH 1.3 | E.5034895.01.08 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 14388 | 0 | 14388 | 2.725 | 0 | 0 | 0 | 2.725 | [5 empty] | 316000 | 0 | 316000 |  |  | 0 | 0 | 316000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249873 | CWSP - COARSEGOLD 21045310 PH 3.2 | E.5034895.01.09 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 20546 | 0 | 20546 | 3.8913 | 0 | 0 | 0 | 3.8913 | [5 empty] | 317000 | 0 | 317000 |  |  | 0 | 0 | 317000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249874 | CWSP - COARSEGOLD 21045310 PH 3.3 | E.5034895.01.10 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 20023 | 0 | 20023 | 3.7922 | 0 | 0 | 0 | 3.7922 | [5 empty] | 316000 | 0 | 316000 |  |  | 0 | 0 | 316000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249875 | CWSP - COARSEGOLD 21046210 PH 1.2 | E.5034895.01.11 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 13936 | 0 | 13936 | 2.6394 | 0 | 0 | 0 | 2.6394 | [5 empty] | 237500 | 0 | 237500 |  |  | 0 | 0 | 237500 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249876 | CWSP - COARSEGOLD 21046210 PH 1.3 | E.5034895.01.12 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 19263 | 0 | 19263 | 3.6483 | 0 | 0 | 0 | 3.6483 | [5 empty] | 237500 | 0 | 237500 |  |  | 0 | 0 | 237500 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35249877 | CWSP - COARSEGOLD 21046210 PH 1.4 | E.5034895.01.13 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 2952 | 0 | 2952 | 0.55909 | 0 | 0 | 0 | 0.55909 | [5 empty] | 237500 | 0 | 237500 |  |  | 0 | 0 | 237500 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35244025 | BR-11-08-W PINTAIL CT PARB |  | 0000000 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35244027 | BR-01-16-W (E) SKYWAY PH 6 PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35244220 | BR-09-04-W HONEY RUN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 29179.7 | 0 | -29179.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 833 | -833 | 833 | -833 | 832.9 | 0 | 28346.8 | -28346.8 | 0 | 0 | 0 | 29179.7 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246591 | BR-12-02-W (E) OAK KNOLL PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 33.6 | 0 | -33.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 96 | -96 | 96 | -96 | 96.2 | 0 | -62.6 | 62.6 | 0 | 0 | 0 | 33.6 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246592 | BR-12-04-W (E) AMERICAN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 1.2 | 0 | -1.2 | OverRun | Project is not in the WP or in 2020 WP | 0 | 96 | -96 | 96 | -96 | 96.2 | 0 | -95 | 95 | 0 | 0 | 0 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246593 | BR-09-06 W (E) BOQUEST PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 385.7 | 0 | -385.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 481 | -481 | 481 | -481 | 480.7 | 0 | -95 | 95 | 0 | 0 | 0 | 385.8 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246594 | BR-11-04 W (E) ROSEHILL PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 366.8 | 0 | -366.8 | OverRun | Project is not in the WP or in 2020 WP | 0 | 481 | -481 | 481 | -481 | 480.8 | 0 | -114 | 114 | 0 | 0 | 0 | 366.8 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246595 | BR-01-15-W (E) SKYWAY PH 5 PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 289.8 | 0 | -289.8 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289.8 | -289.8 | 0 | 0 | 0 | 289.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246596 | BR-14-09-W (E) WILDERNESS PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 271.7 | 0 | -271.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 481 | -481 | 481 | -481 | 480.7 | 0 | -209 | 209 | 0 | 0 | 0 | 271.8 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35246598 | BR-MG-14-W (E) SKYWAY PH 7 PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35249996 | CWSP - COARSEGOLD 210410030 PH 1.2 |  | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST |  | 0 | 10315 | 0 | 10315 | 1.9536 | 0 | 0 | 0 | 1.9536 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35249997 | CWSP - COARSEGOLD 210410030 PH 1.3 |  | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST |  | 0 | 11167 | 0 | 11167 | 2.115 | 0 | 0 | 0 | 2.115 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35249998 | CWSP - COARSEGOLD 210410030 PH 1.4 |  | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST |  | 0 | 19416 | 0 | 19416 | 3.6773 | 0 | 0 | 0 | 3.6773 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35249999 | CWSP - COARSEGOLD 210410030 PH 1.5 |  | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST |  | 0 | 10923 | 0 | 10923 | 2.0688 | 0 | 0 | 0 | 2.0688 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
74022302 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | 5786461 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | 5782840 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 59136 | 0 | 59136 | 11.2 | 0 | 0 | 0 | 11.2 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3372 | -3372 | 3372 | -3372 | [10 empty] | 205 | 195 | 195 | 193 | 193 | 331 | 343 | 343 | 343 | 343 | 343 | 343
74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD |  | 5783285 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74024660 | 2019 CALISTOGA 1101 SUB ORDER |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
74024661 | CWSP-BRUNSWICK 1105 LR32536 PH1 SUBORDER |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35250570 | CWSP - MARIPOSA 2101 LR 35244 PH1 |  | 5797067 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | MARIPOSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250571 | CWSP - MARIPOSA 2101 LR 35244 PH2 |  | 5797067 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | MARIPOSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250572 | CWSP - MARIPOSA 2101 LR 309438 |  | 5797068 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | MARIPOSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250573 | CWSP - MARIPOSA 2101 CB |  | 5797069 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | MARIPOSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250574 | CWSP - HARTLEY 1101 LR 336932 |  | 5797070 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250575 | CWSP - HARTLEY 1101 LR 789752 |  | 5797071 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250576 | CWSP - HARTLEY 1101 LR 698 |  | 5797072 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250577 | CWSP - STANISLAUS 1702 CB |  | 5797073 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 215 | -215 | 215 | -215 | [10 empty] | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250578 | CWSP - STANISLAUS 1701 CB |  | 5797074 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 215 | -215 | 215 | -215 | [10 empty] | 0 | 0 | 0 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250579 | CWSP - POTTER VALLEY PH 1104 LR 95878 |  | 5797075 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 315 | -315 | 315 | -315 | [10 empty] | 0 | 0 | 0 | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250737 | CWSP - COARSEGOLD 21045310 PH 2.2 | E.5034895.01.18 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 15082 | 0 | 15082 | 2.8564 | 0 | 0 | 0 | 2.8564 | [5 empty] | 317000 | 0 | 317000 |  |  | 0 | 0 | 317000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35250738 | CWSP - COARSEGOLD 21045310 PH 2.3 | E.5034895.01.19 | 5796380 | UNSE | 08W | [6 empty] | 2022 |  | SH | OAKHURST | Yosemite Assets | 0 | 18404 | 0 | 18404 | 3.4856 | 0 | 0 | 0 | 3.4856 | [5 empty] | 316000 | 0 | 316000 |  |  | 0 | 0 | 316000 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35253173 | FRRB – KANAKA 1101CB – K4 SM1 | E.5034572.01.44 | 5793918 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 476 | 0 | 476 | 0.090152 | 0.090152 | 0 | 0 | 0.090152 | [5 empty] | 475000 | -1 | 475001 |  |  | 0 | 0 | 475001 | On/Under Budget | Request 2021 Budget | 0 | 176317 | -176317 | 5000 | -5000 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5029 | 0 | 0 | 171288 | 0 | 0 | 0
35253174 | FRRB – KANAKA 1101CB – K4 SM2 | E.5034572.01.45 | 5793918 | UNSE | 08W | [6 empty] | 2021 |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 1400 | 0 | 1400 | 0.26515 | 0.26515 | 0 | 0 | 0.26515 | [5 empty] | 475000 | -1 | 475001 |  |  | 0 | 0 | 475001 | On/Under Budget | Request 2021 Budget | 0 | 508788 | -508788 | 5000 | -5000 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 251894 | 251894 | 0 | 0
35254067 | CWSP - MOUNTAIN QUARRIES 2101 CB PH1 |  | 5797205 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254068 | CWSP - MOUNTAIN QUARRIES 2101 CB PH2 |  | 5797205 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254069 | CWSP - MOUNTAIN QUARRIES 2101 CB PH3 |  | 5797205 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254070 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH1 |  | 5797206 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254071 | CWSP-MOUNTAIN QUARRIES 2101 LR 1350 PH2 |  | 5797206 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254072 | CWSP - HIGHLANDS 1102 LR 623120 |  | 5797207 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | LAKEPORT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254073 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH1 |  | 5797209 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254074 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH2 |  | 5797209 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254075 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH3 |  | 5797209 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254076 | CWSP - POTTER VALLEY PH 1105 LR 1904 PH4 |  | 5797208 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254077 | CWSP - POTTER VALLEY PH 1105 LR 37476 |  | 5797210 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254078 | CWSP - AUBERRY 1101 CB PH1 |  | 5797211 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254079 | CWSP - AUBERRY 1101 CB PH2 |  | 5797211 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254177 | CWSP - PUTAH CREEK 110264044 PH 2.2 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254178 | CWSP - PUTAH CREEK 110267858 PH 1.3 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254240 | CWSP - AUBERRY 1101 LR R2839 PH1 |  | 5797212 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254241 | CWSP - AUBERRY 1101 LR R2839 PH2 |  | 5797212 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254242 | CWSP - AUBERRY 1101 LR 49122 |  | 5797213 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254243 | CWSP - AUBERRY 1101 LR R2578 PH1 |  | 5797214 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254244 | CWSP - AUBERRY 1101 LR R2578 PH2 |  | 5797214 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254245 | CWSP - AUBERRY 1101 LR R2578 PH3 |  | 5797214 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254246 | CWSP - AUBERRY 1101 LR R2578 PH4 |  | 5797214 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254247 | CWSP - AUBERRY 1101 LR R2578 PH5 |  | 5797214 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | FRESNO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254248 | CWSP - PASO ROBLES 1103 LR N58 |  | 5797215 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35254249 | CWSP - PASO ROBLES 1103 LR N54 PH1 |  | 5797216 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254250 | CWSP - PASO ROBLES 1103 LR N54 PH2 |  | 5797216 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254251 | CWSP - PASO ROBLES 1103 LR 59763 |  | 5797217 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254252 | CWSP - PASO ROBLES 1103 LR N52 |  | 5797238 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254253 | CWSP - PASO ROBLES 1103 LR N50 |  | 5797239 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254254 | CWSP - PASO ROBLES 1103 LR 2731 |  | 5797240 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | TEMPLETN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254258 | CWSP - VOLTA 1101CB PH 1.2 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 7656 | 0 | 7656 | 1.45 | 0 | 0 | 0 | 1.45 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254259 | CWSP - VOLTA 1101CB PH 1.3 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 4488 | 0 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0.85 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254260 | CWSP - PUTAH CREEK 110267858 PH 1.6 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254261 | CWSP - PUTAH CREEK 110267858 PH 1.5 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254262 | CWSP - PUTAH CREEK 110267858 PH 1.4 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254263 | CWSP - PUTAH CREEK 1102710384 PH 1.2 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254264 | CWSP - PUTAH CREEK 11028352 PH 1.2 |  | 5796383 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254265 | CWSP - PUTAH CREEK 11028352 PH 2.2 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254266 | CWSP - PUTAH CREEK 11028352 PH 2.3 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254560 | CWSP - PUTAH CREEK 110267858 PH 1.2 |  | 5796384 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | WOODLAND |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254640 | CWSP - VOLTA 1101CB PH 1.4 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 7656 | 0 | 7656 | 1.45 | 0 | 0 | 0 | 1.45 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254641 | CWSP - VOLTA 1101CB PH 1.5 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 1879.68 | 401.28 | 3537.6 | 5818.56 | 1.102 | 0 | 0 | 0 | 1.102 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254642 | CWSP - VOLTA 1101CB PH 1.6 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 6072 | 0 | 6072 | 1.15 | 0 | 0 | 0 | 1.15 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254643 | CWSP - VOLTA 1101CB PH 1.7 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 6388.8 | 0 | 5797.44 | 12186.24 | 2.308 | 0 | 0 | 0 | 2.308 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254644 | CWSP - VOLTA 1101CB PH 1.8 |  | 5796381 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 2164.8 | 0 | 2164.8 | 0.41 | 0 | 0 | 0 | 0.41 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254645 | CWSP - VOLTA 1101CB PH 2.2 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 5892.47 | 5913.6 | 0 | 11806.07 | 2.236 | 0 | 0 | 0 | 2.236 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254646 | CWSP - VOLTA 1101CB PH 2.3 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 0 | 1816.32 | 1816.32 | 0.344 | 0 | 0 | 0 | 0.344 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254647 | CWSP - VOLTA 1101CB PH 2.4 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 2671.68 | 2671.68 | 0 | 5343.36 | 1.012 | 0 | 0 | 0 | 1.012 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254648 | CWSP - VOLTA 1101CB PH 2.5 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 2560.8 | 2560.8 | 0 | 5121.6 | 0.97 | 0 | 0 | 0 | 0.97 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254649 | CWSP - VOLTA 110153118 PH 1.2 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 3643 | 0 | 0 | 3643 | 0.68996 | 0 | 0.00013068 | 0 | 0.68996 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254650 | CWSP - VOLTA 110153118 PH 1.3 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 1901 | 0 | 0 | 1901 | 0.36004 | 0 | 6.8182e-05 | 0 | 0.36004 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254651 | CWSP - VOLTA 110153118 PH 1.4 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 12878 | 0 | 12878 | 2.439 | 0 | 0.00046212 | 0 | 2.439 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254652 | CWSP - VOLTA 110153118 PH 1.5 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 10212 | 0 | 10212 | 1.9341 | 0 | 0.00036553 | 0 | 1.9341 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254653 | CWSP - VOLTA 110153118 PH 1.6 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 10708 | 0 | 10708 | 2.028 | 0 | 0.00038447 | 0 | 2.028 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254654 | CWSP - VOLTA 110153118 PH 1.7 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 797 | 0 | 797 | 0.15095 | 0 | 0 | 0 | 0.15095 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254655 | CWSP - VOLTA 110153118 PH 1.8 |  | 5796382 | UNSE | 08W | [6 empty] | 2022 |  | SH | REDBLUFF |  | 0 | 3020 | 0 | 3020 | 0.57197 | 0 | 0.00010795 | 0 | 0.57197 | [14 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35254656 | CWSP - VOLTA 11011568 PH 1.2 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254657 | CWSP - VOLTA 11011568 PH 1.3 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254658 | CWSP - VOLTA 11011568 PH 1.4 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254659 | CWSP - VOLTA 11011568 PH 1.5 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254695 | FRRB - KANAKA 1101CB - K2 SM2 | E.5034933.01.15 | 5796539 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB - NCF | OROVILLE | North Valley Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 75000 | 0 | 75000 |  |  | 0 | 0 | 75000 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 232008 | -232008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 232008 | 0 | 0 | 0
35254720 | CWSP - VOLTA 11011568 PH 1.6 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254721 | CWSP - VOLTA 11011568 PH 1.7 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254738 | CWSP - VOLTA 11011568 PH 2.2 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254739 | CWSP - VOLTA 11011568 PH 2.3 |  | 5796381 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254940 | CWSP - VOLTA 11011568 PH 3.2 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254941 | CWSP - VOLTA 11011568 PH 3.3 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254942 | CWSP - VOLTA 11011568 PH 3.4 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254943 | CWSP - VOLTA 11011568 PH 3.5 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254944 | CWSP - VOLTA 11011596 - PH1.2 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254945 | CWSP - VOLTA 11011596 - PH1.3 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254946 | CWSP - VOLTA 11011596 - PH1.4 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254947 | CWSP - VOLTA 11011596 - PH1.5 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35254948 | CWSP - VOLTA 11011596 - PH1.6 |  | 5796382 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDBLUFF |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35256082 | CWSP - UPPER LAKE 11011276 PH 1 |  | 5797341 | UNSE | 08W | [6 empty] | Not in the WP |  |  | LAKEPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35256083 | CWSP - UPPER LAKE 11011276 PH 2 |  | 5797341 | UNSE | 08W | [6 empty] | Not in the WP |  |  | LAKEPORT | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259511 | CWSP - DESCHUTES 11041370 PH 2.2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259512 | CWSP - DESCHUTES 11041370 PH 2.3 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259513 | CWSP - DESCHUTES 1104499024 PH 2.2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259514 | CWSP - DESCHUTES 11041582 PH1.2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259515 | CWSP - DESCHUTES 11041370 PH 1.2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259516 | CWSP - DESCHUTES 11041370 PH 1.3 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35259517 | CWSP - DESCHUTES 110449024 PH1.2 |  | 5794554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | REDDING |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35260649 | CWSP - PASO ROBLES 1103N04 PH 1 |  | 5797460 | UNSE | 08W | [6 empty] | Not in the WP |  |  | TEMPLETN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | E.0000088.01 | 5775246 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | Sierra Assets | [14 empty] | 1 | -199999 | 200000 |  |  | 108115.8 | 0 | 91884.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3081 | -3081 | 3081 | -3081 | 665810.5 | 0 | 0 | 0 | 17840.5 | 25084.5 | 3830.8 | 3080.8 | 557694.7 | 0 | 642 | 612 | 612 | 608 | 608 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | 5777380 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 404 | -404 | 404 | -404 | [10 empty] | 84 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174174 | ECOP-STANISLAUS 1702-H03-LR1850 |  | 5539421 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | ANGLSCMP |  | 0 | 3168 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0.6 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 | E.5033921.01 | 5790002 | UNSE | 08W | [6 empty] | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 47520 | 0 | 47520 | 9 | 0 | 0 | 0 | 9 | [5 empty] | 950000 | 0 | 950000 |  |  | 20297.5 | 0 | 929702.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 759 | -759 | 759 | -759 | 99729.1 | 5.2 | 179.5 | -174.3 | 0 | 0 | 19398.2 | 899.2 | 79572.6 | 0 | 119 | 3295 | -3051 | 112 | 245 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 2021-06-18 | 160847 | BL-A: | BL-A: 35174465_ECOP - El Dorado 2101-H02-LR6852-Ph1_08W - May 21 | 2021-05-18 | 2022-03-14 | Not Started | 2022-04-19 | 2022-04-25 | Not Started | 2022-04-18 | Not Started | 2022-05-16 | Not Started | 2022-03-15 | 2022-03-15 | Not Started | 2022-03-16 | 2022-04-05 | Not Started | 2022-04-19 | 2022-05-02 | Not Started | 2022-06-08 | Not Started |  |  |  |  | 2022-06-08 | Not Started | 2022-09-20 | Not Started | 2022-10-19 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 | E.5033920.01 | 5790004 | UNSE | 08W | [6 empty] | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 38808 | 0 | 38808 | 7.35 | 0 | 0 | 0 | 7.35 | [5 empty] | 950000 | 0 | 950000 |  |  | 12907.8 | 0 | 937092.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 514 | -514 | 514 | -514 | 58478.3 | 2.9 | 132 | -129.1 | 0 | 0 | 12283.2 | 624.7 | 45681.3 | 0 | 75 | 72 | 72 | 71 | 203 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2021-06-18 | 160846 | BL-A: | BL-A: 35174466_ECOP - El Dorado 2101-H02-LR6852-Ph3_08W - May 21 | 2021-05-18 | 2022-03-08 | Not Started | 2022-04-13 | 2022-04-19 | Not Started | 2022-04-12 | Not Started | 2022-05-10 | Not Started | 2022-03-09 | 2022-03-09 | Not Started | 2022-03-10 | 2022-03-30 | Not Started | 2022-04-13 | 2022-04-26 | Not Started | 2022-06-02 | Not Started |  |  |  |  | 2022-06-02 | Not Started | 2022-09-14 | Not Started | 2022-10-13 | Not Started | 2022-12-14 | 2022-12-14 | 0 | On/ Ahead Schedule | Not Started | 2022-12-15 | 2022-12-28 | Not Started | 2023-02-03 | Not Started
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 | E.5030964.01 | 5790003 | UNSE | 08W | [6 empty] | Not in the WP | 2022 | SH | PLCRVLLE | Sierra Assets | 0 | 47520 | 0 | 47520 | 9 | 0 | 0 | 0 | 9 | [5 empty] | 950000 | 0 | 950000 |  |  | 8804.8 | 0 | 941195.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 406 | -406 | 406 | -406 | 88210.5 | 1.1 | 132 | -130.9 | 0 | 0 | 8275.4 | 529.5 | 79529.3 | 0 | 51 | 3891 | -3773 | 48 | 180 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2021-06-18 |  |  |  |  | 2022-03-14 | Not Started | 2022-04-19 | 2022-04-25 | Not Started | 2022-04-18 | Not Started | 2022-05-16 | Not Started | 2022-03-15 | 2022-03-15 | Not Started | 2022-03-16 | 2022-04-05 | Not Started | 2022-04-19 | 2022-05-02 | Not Started | 2022-06-08 | Not Started |  |  |  |  | 2022-06-08 | Not Started | 2022-09-20 | Not Started | 2022-10-19 | Not Started | 2022-12-20 | 2022-12-20 | 0 | On/ Ahead Schedule | Not Started | 2022-12-21 | 2023-01-03 | Not Started | 2023-02-09 | Not Started
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 | E.5030956.01 | 5790001 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 33264 | 0 | 33264 | 6.3 | 0 | 0 | 0 | 6.3 | [5 empty] | 884000 | 0 | 884000 |  |  | 25192.5 | 0 | 858807.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 717 | -717 | 717 | -717 | 12100246.5 | 0 | 0 | 0 | 0 | 0 | 24476 | 716.7 | 12075054 | 0 | 148 | 143 | 143 | 142 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 | E.5015574.03 | 5790582 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 |  |  | 518.1 | 0 | 99481.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | 518.1 | 0 | 0 | 0 | 0 | 0 | 503.4 | 14.7 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 | E.5015574.02 | 5790581 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 |  |  | 1561 | 0 | 98439 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 45 | -45 | 45 | -45 | 1561 | 0 | 0 | 0 | 0 | 0 | 1516.5 | 44.5 | 0 | 0 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 | E.5015574.05 | 5790538 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 |  |  | 518.1 | 0 | 99481.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | 518.1 | 0 | 0 | 0 | 0 | 0 | 503.4 | 14.7 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 | E.5015574.04 | 5790539 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 |  |  | 518.1 | 0 | 99481.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | 518.1 | 0 | 0 | 0 | 0 | 0 | 503.4 | 14.7 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35167137 | CANCEL DUPLICATE ORDER |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35171705 | BR-03-12-W (E) PENTZ RD SRTS PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -3894675 | 3894676 |  |  | 3938110.9 | 0 | -43434.9 | OverRun | Project is not in the WP or in 2020 WP | 0 | 142753 | -142753 | 142753 | -142753 | 3938110.9 | 0 | 0 | 0 | 0 | 0 | 3795358.1 | 142752.8 | 0 | 0 | 18763 | 36770 | 24166 | 29904 | 33150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35181576 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH1 |  | 5791419 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174993 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.2 |  | 5790541 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | 5790008 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 0 | 13728 | 0 | 13728 | 2.6 | 0 | 0 | 0 | 2.6 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 245 | -245 | 245 | -245 | [10 empty] | 51 | 49 | 49 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174471 | ECOP-MONTE RIO 1113-H07-LR180 |  | 5539421 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | STROSA |  | 0 | 5280 | 0 | 5280 | 1 | 0 | 0 | 0 | 1 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | 5790006 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 9979.2 | 0 | 9979.2 | 1.89 | 0 | 0 | 0 | 1.89 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 622 | -622 | 622 | -622 | [10 empty] | 89 | 278 | 86 | 85 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | 5790007 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 9610 | 0 | 9610 | 1.8201 | 0 | 0 | 0 | 1.8201 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2064 | -2064 | 2064 | -2064 | [10 empty] | 78 | 1736 | 84 | 83 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | 5790104 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 23232 | 0 | 23232 | 4.4 | 0 | 0 | 0 | 4.4 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 518 | -518 | 518 | -518 | [10 empty] | 108 | 103 | 103 | 102 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | 5790108 | UNSE | 08W | [6 empty] | 2022 |  |  | NAPA |  | 0 | 15628.8 | 0 | 15628.8 | 2.96 | 0 | 2.96 | 0 | 2.96 | [14 empty] | Request 2021 Budget | 0 | 139 | -139 | 139 | -139 | [10 empty] | 29 | 28 | 28 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | 5790109 | UNSE | 08W | [6 empty] | 2022 |  |  | STROSA |  | 0 | 46358.4 | 0 | 46358.4 | 8.78 | 0 | 8.78 | 0 | 8.78 | [14 empty] | Request 2021 Budget | 0 | 149 | -149 | 149 | -149 | [10 empty] | 31 | 30 | 30 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | 5790110 | UNSE | 08W | [6 empty] | 2022 |  |  | NAPA |  | 0 | 50318.4 | 0 | 50318.4 | 9.53 | 0 | 9.53 | 0 | 9.53 | [14 empty] | Request 2021 Budget | 0 | 166 | -166 | 166 | -166 | [10 empty] | 35 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175549 | BR-05-07-W (E) HIGH SCHOOL MAXWELL PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 254.4 | 0 | -254.4 | OverRun | Project is not in the WP or in 2020 WP | 0 | 7 | -7 | 7 | -7 | 254.4 | 0 | 0 | 0 | 0 | 0 | 247.1 | 7.1 | 0 | 0 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175843 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.2 |  | 5790545 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175844 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.3 |  | 5790546 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175845 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.4 |  | 5790547 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175846 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.5 |  | 5790548 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | 5790549 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 105 | -105 | 105 | -105 | [10 empty] | 22 | 21 | 21 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175848 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.3 |  | 5790550 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175849 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.4 |  | 5790551 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175850 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.5 |  | 5790552 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175852 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.2 |  | 5790553 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175853 | REMG #650 PLACERVILLE 2106 RINGTAIL | E.5015422.03 | 5790554 | UNSE | 08W | [6 empty] | Not in the WP |  | SH - Remote Grid | AUBURN | Sierra Assets | 0 | 0 | 3600 | 3600 | 0.68182 | 0.68182 | 0 | 0 | 0.68182 | [5 empty] | 1 | 1 | 0 |  |  | 34333.6 | 0 | -34333.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 32212 | -32212 | 32212 | -32212 | 32212.3 | 0 | 2121.3 | -2121.3 | 0 | 0 | 0 | 34333.5 | 0 | 0 | 0 | 6306 | 12526 | 8813 | 4568 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175854 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.4 |  | 5790555 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175855 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.5 |  | 5790556 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | 5790557 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3 | -3 | 3 | -3 | [10 empty] | 490 | -488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35175857 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.3 |  | 5790578 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175858 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.4 |  | 5790579 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35175859 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.5 |  | 5790580 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176209 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.3 |  | 5790542 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176210 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.4 |  | 5790543 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176211 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.5 |  | 5790544 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35176497 | ECOP-STANISLAUS 1702-H03-LR1850 |  | 5539421 | UNSE | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35176549 | ECOP-MONTE RIO 1113-H07-LR180 |  | 5539421 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35177107 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.6 |  | 5540299 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177108 | CWSP - PLACERVILLE 2106 - LR1104 - PH3.7 |  | 5540300 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177109 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.6 |  | 5540306 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177110 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.7 |  | 5540307 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35177111 | CWSP - PLACERVILLE 2106 - LR1104 - PH2.8 |  | 5791027 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | 5792083 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OAKHURST | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 172 | -172 | 172 | -172 | [10 empty] | 36 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | 5792085 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 53 | -53 | 53 | -53 | [10 empty] | 11 | 11 | 11 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | 5792086 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 64 | -64 | 64 | -64 | [10 empty] | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | 5792087 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 53 | -53 | 53 | -53 | [10 empty] | 11 | 11 | 11 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | 5792088 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 53 | -53 | 53 | -53 | [10 empty] | 11 | 11 | 11 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | 5792089 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | E.5034407.01 | 5792098 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 10771 | 0 | 0 | 10771 | 2.04 | 0 | 2.04 | 0 | 2.04 | [5 empty] | 250000 | 0 | 250000 |  |  | 67716.5 | 0 | 182283.5 | On/Under Budget | Request 2021 Budget | 0 | 66959 | -66959 | 66959 | -66959 | 75420.4 | 131.3 | -6707.3 | 6838.6 | 0 | 0 | 8393.2 | 59323.3 | 68.8 | 0 | 8265 | 4650 | 938 | 42262 | 9914 | 131 | 133 | 133 | 133 | 133 | 133 | 133 | 2021-06-18 | 157814 | BL-A | BL-A 35192282_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-09 | Not Started | 2021-08-10 | 2021-08-16 | Not Started | 2021-09-13 | Not Started | 2021-10-04 | Not Started | 2021-08-10 | 2021-08-10 | Not Started | 2021-08-11 | 2021-08-31 | Not Started | 2021-09-14 | 2021-09-27 | Not Started | 2021-10-27 | Not Started | 2021-10-27 | Not Started | 2021-11-09 | Not Started | 2021-10-27 | Not Started | 2022-02-08 | Not Started | 2022-03-09 | Not Started | 2022-03-28 | 2022-05-10 | -43 | Behind Schedule | Not Started | 2022-05-11 | 2022-05-24 | Not Started | 2022-07-07 | Not Started
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | 5792090 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | 5792513 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 79 | -79 | 79 | -79 | [10 empty] | 4149 | -4102 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35206134 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 |  | 5793703 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206135 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 |  | 5793703 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206136 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 |  | 5793703 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35206138 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 |  | 5793703 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | 5792100 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | 5792101 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | 5792104 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | 5792102 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 50 | -50 | 50 | -50 | [10 empty] | 11 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | 5792103 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 50 | -50 | 50 | -50 | [10 empty] | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | 5792105 | UNSE | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | 5792106 | UNSE | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | 5792108 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 57 | -57 | 57 | -57 | [10 empty] | 12 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | 5792109 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | 5792110 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | 5792095 | UNSE | 08W | [6 empty] | Not in the WP |  |  | MARIPOSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | 5792096 | UNSE | 08W | [6 empty] | Not in the WP |  |  | MARIPOSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | 5792099 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | 5792062 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 134 | -134 | 134 | -134 | [10 empty] | 28 | 27 | 27 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | 5792063 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 97 | -97 | 97 | -97 | [10 empty] | 20 | 19 | 19 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191380 | ECOP - MIWUK 1702 - H02-LR9270 |  | 5541306 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191381 | ECOP - MIWUK 1702 - H03-LR9270 |  | 5541307 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191382 | ECOP - MORAGA 1105 - H01-CB |  | 5541308 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WALNTCRK | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 |  | 5791278 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OROVILLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35185714 | WDDB - OTTER 1102 - LR 2002 |  | 5791660 | UNSE | 08W | [6 empty] | Not in the WP |  |  | MONTEREY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 53 | -53 | 53 | -53 | [10 empty] | 11 | 11 | 11 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | 5792200 | UNSE | 08W | [6 empty] | 2022 |  |  | NAPA |  | 0 | 42768 | 0 | 42768 | 8.1 | 0 | 8.1 | 0 | 8.1 | [14 empty] | Request 2021 Budget | 0 | 202 | -202 | 202 | -202 | [10 empty] | 42 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 |  | 5541300 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191313 | ECOP - MONTE RIO 1113 - H06-LR8299 |  | 5541301 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191316 | ECOP - OAKHURST 1103 - H01-LR10190 |  | 5541302 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OAKHURST | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | 5541304 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | 5792071 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 304 | -304 | 304 | -304 | [10 empty] | 1135 | -1008 | 59 | 59 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | 5792058 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 85 | -85 | 85 | -85 | [10 empty] | 18 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | 5792059 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | 5792060 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 58 | -58 | 58 | -58 | [10 empty] | 12 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | 5792070 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 112 | -112 | 112 | -112 | [10 empty] | 23 | 22 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | 5792076 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 64 | -64 | 64 | -64 | [10 empty] | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | 5792065 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 46 | -46 | 46 | -46 | [10 empty] | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | 5792069 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 122 | -122 | 122 | -122 | [10 empty] | 26 | 24 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | 5792078 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 216 | -216 | 216 | -216 | [10 empty] | 45 | 43 | 43 | 43 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | 5792080 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 69 | -69 | 69 | -69 | [10 empty] | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | 5792084 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 64 | -64 | 64 | -64 | [10 empty] | 13 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | 5792061 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 214 | -214 | 214 | -214 | [10 empty] | 45 | 43 | 43 | 42 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | 5792066 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 126 | -126 | 126 | -126 | [10 empty] | 26 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | 5792067 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 136 | -136 | 136 | -136 | [10 empty] | 28 | 27 | 27 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | 5792068 | UNSE | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 102 | -102 | 102 | -102 | [10 empty] | 21 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | 5792072 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 149 | -149 | 149 | -149 | [10 empty] | 31 | 30 | 30 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | 5792073 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 167 | -167 | 167 | -167 | [10 empty] | 35 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | 5792074 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 156 | -156 | 156 | -156 | [10 empty] | 33 | 31 | 31 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | 5792075 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 144 | -144 | 144 | -144 | [10 empty] | 30 | 29 | 29 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | 5792077 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 53 | -53 | 53 | -53 | [10 empty] | 11 | 11 | 11 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | 5792079 | UNSE | 08W | [6 empty] | Not in the WP |  |  | ANGLSCMP | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 69 | -69 | 69 | -69 | [10 empty] | 14 | 14 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | 5792081 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 61 | -61 | 61 | -61 | [10 empty] | 13 | 12 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212468 | FRRB - POINT MORETTI 1101 LR36516 |  | 5793896 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 5016 | 0 | 5016 | 0.95 | 0 | 0 | 0.95 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 107383 | -107383 | 107383 | -107383 | [10 empty] | 0 | 0 | 0 | 0 | 107383 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212469 | FRRB - POINT MORETTI 1101 LR12122 |  | 5793896 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 24393.6 | 0 | 24393.6 | 4.62 | 0 | 0 | 4.62 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 522221 | -522221 | 522221 | -522221 | [10 empty] | 0 | 0 | 0 | 0 | 522221 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212470 | FRRB - POINT MORETTI 1101 LR83716 |  | 5793896 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0.77 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 87037 | -87037 | 87037 | -87037 | [10 empty] | 0 | 0 | 0 | 0 | 87037 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35212471 | FRRB - POINT MORETTI 1101 LR5076 |  | 5793896 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | STCRUZ |  | 0 | 8976 | 0 | 8976 | 1.7 | 0 | 0 | 1.7 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 192159 | -192159 | 192159 | -192159 | [10 empty] | 0 | 0 | 0 | 0 | 192159 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 | E.5034697.01.01 | 5794549 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Yosemite Assets | 0 | 14398 | 0 | 14398 | 2.7269 | 0 | 2.7269 | 0 | 2.7269 | [5 empty] | 73076 | 0 | 73076 |  |  | 109826.4 | 49779 | -86529.4 | OverRun | Request 2021 Budget | 0 | 34547 | -34547 | 34547 | -34547 | 34546.6 | 797.4 | 76077.2 | -75279.8 | 0 | 0 | 0 | 109826.5 | 0 | 0 | 3012 | 23005 | 435 | 3487 | 3809 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-08-30 | Not Started | 2021-10-05 | 2021-10-11 | Not Started | 2021-10-04 | Not Started | 2021-11-01 | Not Started | 2021-08-31 | 2021-08-31 | Not Started | 2021-09-01 | 2021-09-21 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-11-24 | Not Started | 2021-11-24 | Not Started | 2021-12-07 | Not Started | 2021-11-24 | Not Started | 2022-03-08 | Not Started | 2022-04-06 | Not Started | 2022-06-07 | 2022-06-07 | 0 | On/ Ahead Schedule | Not Started | 2022-06-08 | 2022-06-21 | Not Started | 2022-08-04 | Not Started
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | E.5034608.01.01 | 5794207 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 0 | 2270 | 0 | 2270 | 0.42992 | 0 | 0.42992 | 0 | 0.42992 | [5 empty] | 1 | 1 | 0 |  |  | 48755.7 | 0 | -48755.7 | OverRun | Request 2021 Budget | 0 | 59819 | -59819 | 59819 | -59819 | 62973.3 | 120.6 | -12756.2 | 12876.8 | 0 | 0 | 2545.5 | 46210.3 | 608.7 | 0 | 10793 | 2530 | 779 | 30323 | 14542 | 121 | 122 | 122 | 122 | 122 | 122 | 122 | 2021-06-18 | 157792 | BL-A | BL-A 35217269_CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 - DD 210305 Mar.2021 | 2021-03-19 | 2021-08-27 | Not Started | 2021-08-30 | 2021-09-03 | Not Started | 2021-12-24 | Not Started | 2021-12-27 | Not Started | 2021-08-30 | 2021-08-30 | Not Started | 2021-08-31 | 2021-09-20 | Not Started | 2021-12-27 | 2022-01-07 | Not Started | 2022-01-19 | Not Started | 2022-01-19 | Not Started | 2022-02-01 | Not Started | 2022-01-19 | Not Started | 2022-05-03 | Not Started | 2022-06-01 | Not Started | 2022-07-08 | 2022-08-02 | -25 | Behind Schedule | Not Started | 2022-08-03 | 2022-08-16 | Not Started | 2022-09-29 | Not Started
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | 5794550 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | BKRSFLD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 3039 | -3039 | 3039 | -3039 | [10 empty] | 880 | 2083 | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219265 | CWSP - CRESTA 1101546650 |  | 5543353 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CHICO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 4763 | -4763 | 4763 | -4763 | [10 empty] | 3820 | 716 | 0 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | 5794539 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | BKRSFLD |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 4686 | -4686 | 4686 | -4686 | [10 empty] | 1530 | 3063 | 31 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | E.5034692.01.01 | 5794540 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH | CONCORD | Diablo Assets | 6019 | 0 | 0 | 6019 | 1.14 | 0 | 1.14 | 0 | 1.14 | [5 empty] | 350000 | 0 | 350000 |  |  | 48906.3 | 0 | 301093.7 | On/Under Budget | Budget Allocated | 8255 | 42486 | -34231 | 42486 | -34231 | 4817819 | 44.9 | 6738.5 | -6693.6 | 0 | 0 | 0 | 48906.3 | 4775332.5 | 0 | 4102 | 3385 | 11919 | 13609 | 9153 | 45 | 46 | 46 | 46 | 46 | 46 | 46 | 2021-06-18 | 160972 | BL-B: | BL-B: 35219093_CWSP - TIDEWATER 210614072 Ph1_08W - May 21 | 2021-05-20 | 2021-09-30 | Not Started | 2022-03-04 | 2022-03-10 | Not Started | 2022-03-03 | Not Started | 2022-03-31 | Not Started | 2021-10-01 | 2021-10-01 | Not Started | 2021-10-04 | 2021-10-22 | Not Started | 2022-03-04 | 2022-03-17 | Not Started | 2022-04-25 | Not Started | 2022-04-25 | Not Started | 2022-07-04 | Not Started | 2022-04-25 | Not Started | 2022-07-06 | Not Started | 2022-08-04 | Not Started | 2022-10-24 | 2022-10-05 | 19 | On/ Ahead Schedule | Not Started | 2022-10-06 | 2022-10-19 | Not Started | 2022-12-02 | Not Started
35219094 | CNCL CWSP - VACA DIXON 1101126774 |  | 5543350 | UNSE | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219096 | CWSP - KIRKER 2104442850 PH 1.1 | E.5034694.01.01 | 5794544 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH | ANTIOCH | Diablo Assets | 8817.6 | 0 | 0 | 8817.6 | 1.67 | 0 | 1.6701 | 0 | 1.67 | [5 empty] | 500000 | 0 | 500000 |  |  | 16036.6 | 0 | 483963.4 | On/Under Budget | Budget Allocated | 8302 | 16023 | -7721 | 16023 | -7721 | 5230192.4 | 33.5 | 250.9 | -217.4 | 0 | 0 | 0 | 16036.6 | 5214169.6 | 0 | 1726 | 5404 | 2303 | 2646 | 3707 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 2021-06-18 | 157130 | BL-A | BL-A CWSP - KIRKER 2104442850 PH 1 - Mar. 2021 | 2021-03-07 | 2021-12-09 | Not Started | 2022-03-04 | 2022-03-10 | Not Started | 2022-03-03 | Not Started | 2022-03-31 | Not Started | 2021-12-10 | 2021-12-10 | Not Started | 2021-12-13 | 2021-12-31 | Not Started | 2022-03-04 | 2022-03-17 | Not Started | 2022-04-25 | Not Started | 2022-04-25 | Not Started | 2022-08-05 | Not Started | 2022-04-25 | Not Started | 2022-08-05 | Not Started | 2022-09-05 | Not Started | 2023-01-20 | 2023-01-09 | 11 | On/ Ahead Schedule | Not Started | 2023-01-10 | 2023-01-23 | Not Started | 2023-04-03 | Not Started
35219279 | CWSP - VACAVILLE 11088762 |  | 5543348 | UNSE | 08W | [6 empty] | Not in the WP |  |  | VACAVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35219587 | CWSP - MARIPOSA 2102440236 PH1.2 | E.5034702.01.03 | 5794552 | UNSE | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 10718.4 | 0 | 10718.4 | 2.03 | 2.0299 | 0 | 0 | 2.03 | [5 empty] | 1 | 1 | 0 |  |  | 18391 | 0 | -18391 | OverRun | Request 2021 Budget | 0 | 15859 | -15859 | 15859 | -15859 | 15858.7 | 0 | 2532.3 | -2532.3 | 0 | 0 | 0 | 18391 | 0 | 0 | 0 | 1246 | 6708 | 4785 | 3120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-09-17 | Not Started | 2021-09-20 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-10-13 | Not Started | 2021-10-13 | Not Started | 2021-10-26 | Not Started | 2021-10-13 | Not Started | 2022-01-25 | Not Started | 2022-02-23 | Not Started | 2022-04-26 | 2022-04-26 | 0 | On/ Ahead Schedule | Not Started | 2022-04-27 | 2022-05-10 | Not Started | 2022-06-23 | Not Started
35219588 | CWSP - MARIPOSA 2102440236 PH1.3 | E.5034702.01.04 | 5794552 | UNSE | 08W | [6 empty] | 2021 |  | SH | MARIPOSA | Yosemite Assets | 0 | 7339.2 | 0 | 7339.2 | 1.39 | 1.39 | 0 | 0 | 1.39 | [5 empty] | 1 | 1 | 0 |  |  | 16233 | 0 | -16233 | OverRun | Request 2021 Budget | 0 | 13881 | -13881 | 13881 | -13881 | 13881.3 | 0 | 2351.7 | -2351.7 | 0 | 0 | 0 | 16233 | 0 | 0 | 0 | 683 | 6226 | 4665 | 2307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2021-09-17 | Not Started | 2021-10-08 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2021-09-20 | 2021-10-01 | Not Started | 2021-11-02 | Not Started | 2021-11-02 | Not Started | 2021-11-15 | Not Started | 2021-11-02 | Not Started | 2022-02-14 | Not Started | 2022-03-15 | Not Started | 2022-05-16 | 2022-05-16 | 0 | On/ Ahead Schedule | Not Started | 2022-05-17 | 2022-05-30 | Not Started | 2022-07-13 | Not Started
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | E.5034714.01.01 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 0 | 12652 | 0 | 12652 | 2.3962 | 0 | 2.3962 | 0 | 2.3962 | [5 empty] | 180000 | 180000 | 0 |  |  | 20389.7 | 0 | -20389.7 | OverRun | Budget Allocated | 540000 | 20342 | 519658 | 20342 | 519658 | 20342.2 | 0 | 47.5 | -47.5 | 0 | 0 | 0 | 20389.6 | 0 | 0 | 2222 | 7793 | 1407 | 6324 | 2596 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 | E.5034714.01.02 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 22991 | 0 | 0 | 22991 | 4.3544 | 0 | 4.3544 | 0 | 4.3544 | [5 empty] | 225000 | 225000 | 0 |  |  | 58944.5 | 0 | -58944.5 | OverRun | Budget Allocated | 500000 | 142089 | 357911 | 142089 | 357911 | 142089.2 | 40365.8 | -2413.1 | 42778.9 | 0 | 0 | 0 | 58944.3 | 0 | 0 | 12933 | -5459 | 6417 | 20146 | 27321 | 40366 | 40366 | 0 | 0 | 0 | 0 | 0
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | E.5034794.01.01 | 5795152 | UNSE | 08W | [6 empty] | 2022 |  | SH | LAKEPORT | Humboldt Division Assets | 8184 | 0 | 0 | 8184 | 1.55 | 0 | 1.55 | 0 | 1.55 | [5 empty] | 250000 | 0 | 250000 |  |  | 43360 | 0 | 206640 | On/Under Budget | Request 2021 Budget | 0 | 50909 | -50909 | 50909 | -50909 | 51351.6 | 94 | -6885.8 | 6979.8 | 0 | 0 | 0 | 43360.1 | 442.4 | 0 | 0 | 0 | 935 | 40233 | 9077 | 94 | 95 | 95 | 95 | 95 | 95 | 95 | 2021-06-18 | 157811 | BL-A | BL-A 35226621_ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2_08W - DD 210305 Mar.2021 | 2021-03-19 | 2021-09-03 | Not Started | 2021-09-06 | 2021-09-10 | Not Started | 2021-12-31 | Not Started | 2022-01-03 | Not Started | 2021-09-06 | 2021-09-06 | Not Started | 2021-09-07 | 2021-09-27 | Not Started | 2022-01-03 | 2022-01-14 | Not Started | 2022-01-26 | Not Started | 2022-01-26 | Not Started | 2022-02-08 | Not Started | 2022-01-26 | Not Started | 2022-05-10 | Not Started | 2022-06-08 | Not Started | 2022-07-29 | 2022-08-09 | -11 | Behind Schedule | Not Started | 2022-08-10 | 2022-08-23 | Not Started | 2022-10-06 | Not Started
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 | E.5034714.01.03 | 5794555 | UNSE | 08W | [6 empty] | 2021 | 2021 | SH - EPC | REDDING | North Valley Assets | 0 | 13424 | 0 | 13424 | 2.5424 | 2.5424 | 0 | 0 | 2.5424 | [5 empty] | 100000 | 0 | 100000 |  |  | 17733.2 | 0 | 82266.8 | On/Under Budget | Budget Allocated | 4825999.3 | 21966 | 4804033.3 | 21966 | 4804033.3 | 42612.6 | 1172.4 | 1298.3 | -125.9 | 0 | 0 | 0 | 17733.2 | 20646.3 | 0 | 0 | 1996 | 10739 | 950 | 2749 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-18 |  |  |  |  | 2021-09-27 | Not Started | 2021-11-02 | 2021-11-08 | Not Started | 2021-11-01 | Not Started | 2021-11-29 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-07-05 | 2022-07-05 | 0 | On/ Ahead Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 | E.5034714.01.04 | 5794555 | UNSE | 08W | [6 empty] | 2022 |  | SH - EPC | REDDING | North Valley Assets | 4465 | 0 | 0 | 4465 | 0.84564 | 0 | 0.84564 | 0 | 0.84564 | [5 empty] | 150000 | 150000 | 0 |  |  | 37730.1 | 0 | -37730.1 | OverRun | Budget Allocated | 500000 | 91883 | 408117 | 91883 | 408117 | 91883 | 30274.3 | 6395.7 | 23878.6 | 0 | 0 | 0 | 37730 | 0 | 0 | 0 | 1186 | 601 | 5922 | 23626 | 30274 | 30274 | 0 | 0 | 0 | 0 | 0
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 | E.5034714.01.05 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH - EPC | REDDING | North Valley Assets | 13366 | 0 | 0 | 13366 | 2.5314 | 0 | 2.5314 | 0 | 2.5314 | [5 empty] | 200000 | 0 | 200000 |  |  | 45715.7 | 0 | 154284.3 | On/Under Budget | Budget Allocated | 500000 | 195597 | 304403 | 195597 | 304403 | 195597.3 | 60000 | -13247.6 | 73247.6 | 0 | 0 | 0 | 45715.7 | 0 | 0 | 0 | 1140 | 414 | 5065 | 52345 | 60000 | 60000 | 1125 | 14545 | 964 | 0 | 0 | 2021-06-04 |  |  |  |  | 2021-07-16 | Not Started | 2021-07-19 | 2021-07-23 | Not Started | 2021-07-16 | Not Started | 2021-09-10 | Not Started | 2021-07-19 | 2021-07-19 | Not Started | 2021-07-20 | 2021-08-02 | Not Started | 2021-08-09 | 2021-08-20 | Not Started | 2021-09-21 | Not Started | 2021-09-21 | Not Started | 2021-10-04 | Not Started | 2021-09-21 | Not Started | 2021-11-15 | Not Started | 2021-12-14 | Not Started | 2022-02-17 | 2022-02-17 | 0 | On/ Ahead Schedule | Not Started | 2022-02-18 | 2022-03-03 | Not Started | 2022-04-18 | Not Started
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 | E.5034714.01.06 | 5794555 | UNSE | 08W | [6 empty] | 2022 | 2022 | SH - EPC | REDDING | North Valley Assets | 0 | 11563 | 0 | 11563 | 2.19 | 0 | 2.19 | 0 | 2.19 | [5 empty] | 158330 | 0 | 158330 |  |  | 7555.4 | 0 | 150774.6 | On/Under Budget | Budget Allocated | 500000 | 13087 | 486913 | 13087 | 486913 | 31705.8 | 1172.4 | 0 | 1172.4 | 0 | 0 | 0 | 7555.4 | 18619 | 0 | 0 | 711 | 412 | 6276 | 156 | 1172 | 1727 | 158 | 158 | 432 | 919 | 966 | 2021-06-04 |  |  |  |  | 2021-09-13 | Not Started | 2021-10-19 | 2021-10-25 | Not Started | 2021-10-18 | Not Started | 2021-11-15 | Not Started | 2021-09-14 | 2021-09-14 | Not Started | 2021-09-15 | 2021-10-05 | Not Started | 2021-10-19 | 2021-11-01 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-06-21 | 2022-06-21 | 0 | On/ Ahead Schedule | Not Started | 2022-06-22 | 2022-07-05 | Not Started | 2022-08-18 | Not Started
35226720 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.3 |  | 5795126 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 2745.6 | 0 | 2745.6 | 0.52 | 0 | 0 | 0 | 0.52 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35226723 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.4 |  | 5795126 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 4065.6 | 1425.6 | 0 | 5491.2 | 1.04 | 0 | 0 | 0 | 1.04 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35226659 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.2 |  | 5795126 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 4382.4 | 5544 | 0 | 9926.4 | 1.88 | 0 | 0 | 0 | 1.88 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | E.5034778.01.01 | 5795018 | UNSE | 08W | [6 empty] | 2022 | 2021 | SH | PLCRVLLE | Sierra Assets | 739 | 0 | 0 | 739 | 0.13996 | 0 | 0.13996 | 0 | 0.13996 | [5 empty] | 320000 | 0 | 320000 |  |  | 18775.1 | 0 | 301224.9 | On/Under Budget | Budget Allocated | 179000 | 178393 | 607 | 178393 | 607 | 1490279.6 | 15546 | -4340.2 | 19886.2 | 0 | 0 | 0 | 18775.2 | 1311886.9 | 0 | 94 | 3944 | 2509 | 6674 | 9895 | 15546 | 61018 | 46018 | 4861 | 11929 | 11045 | 4861 | 2021-05-07 |  |  |  |  | 2022-08-01 | Not Started | 2022-09-06 | 2022-09-12 | Not Started | 2022-09-05 | Not Started | 2022-10-03 | Not Started | 2022-08-02 | 2022-08-02 | Not Started | 2022-08-03 | 2022-08-23 | Not Started | 2022-09-06 | 2022-09-19 | Not Started | 2022-10-26 | Not Started | 2022-10-26 | Not Started | 2022-11-08 | Not Started | 2022-10-26 | Not Started | 2023-02-07 | Not Started | 2023-03-08 | Not Started | 2023-05-09 | 2023-05-09 | 0 | On/ Ahead Schedule | Not Started | 2023-05-10 | 2023-05-23 | Not Started | 2023-07-06 | Not Started
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | 5795150 | UNSE | 08W | [6 empty] | Not in the WP |  | FRRB | WILLOWS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 6480 | -6480 | 6480 | -6480 | [10 empty] | 0 | 1289 | 1635 | 115 | 3440 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 | E.5034796.01.01 | 5795151 | UNSE | 08W | [6 empty] | Not in the WP |  | SH - Remote Grid | GYSRVLLE | Sonoma Assets | 0 | 0 | 21120 | 21120 | 4 | 4 | 0 | 0 | 4 | [5 empty] | 1 | -149999 | 150000 |  |  | 3233824.7 | 0 | -3083824.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 3232259 | -3232259 | 3232259 | -3232259 | 3232259 | 0 | 1565.7 | -1565.7 | 0 | 0 | 0 | 3233824.6 | 0 | 0 | 5111 | 2969 | 4689 | 3198184 | 21306 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | 5795062 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 347 | -347 | 347 | -347 | [10 empty] | 0 | 0 | 118 | 1 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223038 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | E.5034764.01.01 | 5794988 | UNSE | 08W | [6 empty] | 2022 |  | SH | JACKSON | Stockton Assets | 3801.6 | 0 | 0 | 3801.6 | 0.72 | 0 | 0.72008 | 0 | 0.72 | [5 empty] | 1 | -349999 | 350000 |  |  | 35231.6 | 0 | 314768.4 | On/Under Budget | Budget Allocated | 350000 | 1366547 | -1016547 | 1366547 | -1016547 | 1401149.4 | 28.6 | 22629.6 | -22601 | 0 | 0 | 0 | 35231.6 | 34602.6 | 0 | 827 | 8126 | 52 | 2610 | 988 | 29 | 44094 | 435854 | 378274 | 473349 | 14425 | 7921 | 2021-06-18 | 160555 | BL-A | BL-A 35223038_PSPS - Martell 1101 Ph 1.1_08W - DD 210507 | 2021-05-10 | 2021-09-10 | Not Started | 2021-09-13 | 2021-09-17 | Not Started | 2021-11-26 | Not Started | 2021-11-29 | Not Started | 2021-09-13 | 2021-09-13 | Not Started | 2021-09-14 | 2021-10-04 | Not Started | 2021-11-29 | 2021-12-17 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-04-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-08-01 | 2022-07-05 | 27 | On/ Ahead Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | 5794984 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 9187.2 | 0 | 0 | 9187.2 | 1.74 | 0 | 0 | 0 | 1.74 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 5166 | -5166 | 5166 | -5166 | [10 empty] | 183 | 4895 | 30 | 29 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35223063 | PSPS - DUNBAR 1101 - OAKMONT | E.5034761.01.01 | 5794985 | UNSE | 08W | [6 empty] | 2021 |  | SH | STROSA | Sierra Assets | 1688 | 0 | 0 | 1688 | 0.3197 | 0 | 0.3197 | 0 | 0.3197 | [5 empty] | 1 | 1 | 0 |  |  | 7191.7 | 0 | -7191.7 | OverRun | Request 2021 Budget | 0 | 6028 | -6028 | 6028 | -6028 | 6028.3 | 0 | 1163.4 | -1163.4 | 0 | 0 | 0 | 7191.7 | 0 | 0 | 1038 | 3518 | 26 | 818 | 628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 |  |  |  |  | 2021-09-27 | Not Started | 2021-11-02 | 2021-11-08 | Not Started | 2021-11-01 | Not Started | 2021-11-29 | Not Started | 2021-09-28 | 2021-09-28 | Not Started | 2021-09-29 | 2021-10-19 | Not Started | 2021-11-02 | 2021-11-15 | Not Started | 2021-12-22 | Not Started | 2021-12-22 | Not Started | 2022-01-04 | Not Started | 2021-12-22 | Not Started | 2022-04-05 | Not Started | 2022-05-04 | Not Started | 2022-07-05 | 2022-07-05 | 0 | On/ Ahead Schedule | Not Started | 2022-07-06 | 2022-07-19 | Not Started | 2022-09-01 | Not Started
35219591 | CWSP - OLETA 1101754718 PH1.1 | E.5034721.01.01 | 5794611 | UNSE | 08W | [6 empty] | 2022 |  | SH | JACKSON | Stockton Assets | 0 | 6474 | 0 | 6474 | 1.2261 | 0 | 1.2261 | 0 | 1.2261 | [5 empty] | 1 | -474999 | 475000 |  |  | 64129.1 | 0 | 410870.9 | On/Under Budget | Request 2021 Budget | 0 | 25320 | -25320 | 25320 | -25320 | 25320.1 | 0 | 38809 | -38809 | 0 | 0 | 0 | 64129.2 | 0 | 0 | 0 | 3363 | 8339 | 7116 | 6502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159256 | BL-A | BL-A 35219591_CWSP - OLETA 1101754718 PH 1.1_08W - DD 210402 | 2021-04-15 | 2021-08-13 | Not Started | 2021-08-16 | 2021-08-20 | Not Started | 2022-04-15 | Not Started | 2022-04-18 | Not Started | 2021-08-16 | 2021-08-16 | Not Started | 2021-08-17 | 2021-09-06 | Not Started | 2022-04-18 | 2022-04-29 | Not Started | 2022-05-11 | Not Started | 2022-05-11 | Not Started | 2022-05-24 | Not Started | 2022-05-11 | Not Started | 2022-08-23 | Not Started | 2022-09-21 | Not Started | 2022-11-07 | 2022-11-22 | -15 | Behind Schedule | Not Started | 2022-11-23 | 2022-12-06 | Not Started | 2023-01-19 | Not Started
35222233 | NULL PM |  | 5794900 | UNSE | 08W | [6 empty] | Not in the WP |  |  | DINUBA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35222234 | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN |  | 5543982 | UNSE | 08W | [6 empty] | 2021 |  |  | OAKHURST |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Budget Allocated | 1000000 | 0 | 1000000 | 0 | 1000000
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | E.5034754.01.01 | 5794900 | UNSE | 08W | [6 empty] | 2021 |  | SH - Remote Grid | DINUBA | Fresno Assets | 0 | 0 | 13728 | 13728 | 2.6 | 0 | 2.6 | 0 | 2.6 | 13728 | 0 | 2.6 | 0 |  | 500000 | 0 | 500000 |  |  | 58569.2 | 0 | 441430.8 | On/Under Budget | Budget Allocated | 625000 | 54800 | 570200 | 54800 | 570200 | 54799.5 | 0 | 3769.7 | -3769.7 | 0 | 0 | 0 | 58569.3 | 0 | 0 | 3228 | 8965 | 15617 | 17375 | 9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35222236 | MARIPOSA 2101 - #531 SLAUGHTER HOUSE |  | 5543983 | UNSE | 08W | [6 empty] | 2021 |  |  | MARIPOSA | [24 empty] | Request 2021 Budget | 0 | 0 | 0 | 0 | 0
35118702 | BR-11-03-W (E) GREGS WAY, PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -4471274 | 4471275 |  |  | 3905882.8 | 0 | 565392.2 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 2388345 | -2388345 | 2388345 | -2388345 | 4387521.5 | 481638.7 | 0 | 481638.7 | 0 | 399.3 | 1998776.9 | 1906706.7 | 0 | 0 | 316958 | 42613 | 955656 | 298144 | 293336 | 481639 | 0 | 0 | 0 | 0 | 0 | 0
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 | E.5015493.01 | 5786589 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | SNJOSE | De Anza Assets | 8554 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 1.6201 | [5 empty] | 500000 | 400000 | 100000 |  |  | 79294.5 | 0 | 20705.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | -46646 | 46646 | -46646 | 46646 | 79294.5 | 0 | 0 | 0 | 0 | 35907.9 | 90032.3 | -46645.9 | 0 | 0 | 953 | -48931 | 446 | 443 | 443 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | E.5014535.05 | 5786605 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4593.6 | 0 | 4593.6 | 0.87 | 0 | 0 | 0 | 0.87 | [5 empty] | 10000 | 0 | 10000 |  |  | 4925.4 | 0 | 5074.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 253 | -253 | 253 | -253 | 4925.4 | 0 | 0 | 0 | 0 | 153.8 | 4519.2 | 252.5 | 0 | 0 | 141 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | E.5014535.06 | 5786604 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 2164.8 | 0 | 2164.8 | 0.41 | 0 | 0 | 0 | 0.41 | [5 empty] | 10000 | 0 | 10000 |  |  | 5777.7 | 0 | 4222.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 277 | -277 | 277 | -277 | 5777.7 | 0 | 0 | 0 | 0 | 250.8 | 5250.2 | 276.7 | 0 | 0 | 146 | 33 | 33 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118671 | BR-MG-1A-W SHAW CIR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118673 | BR-MG-4A-W S PARK DR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118674 | BR-MG-05-W GLENDALE DR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118675 | BR-MG-05-W SHAW CIR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118518 | BR-07-06-W (E) NIELSEN DR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -3251331 | 3251332 |  |  | 1049.5 | 0 | 3250282.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 175 | -175 | 175 | -175 | 1195.1 | 6.1 | 0 | 6.1 | 0 | 0 | 1019.6 | 29.8 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 107 | 7 | 7
35118519 | BR-07-08-W (E) FOLAND RD PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 2009.2 | 0 | -2009.2 | OverRun | Project is not in the WP or in 2020 WP | 0 | 615 | -615 | 615 | -615 | 687.2 | 0 | 1322 | -1322 | 0 | 0 | 72.2 | 1937 | 0 | 0 | 151 | 1 | 1 | 1 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118662 | BR-11-07-W (E) APPLE LN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CLRLAKE | Humboldt Division Assets | 0 | 6828 | 0 | 6828 | 1.2932 | 0 | 0 | 0 | 1.2932 | [5 empty] | 80000 | 0 | 80000 |  |  | 7951.9 | 0 | 72048.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 11267 | -11267 | 11267 | -11267 | 15128.3 | 3588.2 | 0 | 3588.2 | 0 | 0 | 3861.1 | 4090.8 | 0 | 0 | 460 | 2644 | 0 | 760 | 227 | 3588 | 3588 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 157812 | BL-A | BL-A 35137599_CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11_08W - DD 210305 Mar. 2021 | 2021-03-19 | 2021-09-20 | Not Started | 2021-09-21 | 2021-09-27 | Not Started | 2021-10-04 | Not Started | 2021-11-15 | Not Started | 2021-09-21 | 2021-09-21 | Not Started | 2021-09-22 | 2021-10-12 | Not Started | 2021-10-05 | 2021-10-18 | Not Started | 2021-12-08 | Not Started | 2021-12-08 | Not Started | 2021-12-21 | Not Started | 2021-12-08 | Not Started | 2022-03-22 | Not Started | 2022-04-20 | Not Started | 2022-02-24 | 2022-04-28 | -63 | Behind Schedule | Not Started | 2022-05-05 | 2022-05-18 | Not Started | 2022-06-27 | Not Started
35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP | 2022 |  | SNRAFAEL | North Bay Assets | [14 empty] | 50000 | 0 | 50000 |  |  | 8238.3 | 0 | 41761.7 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 1063653.9 | 0 | 0 | 0 | 0 | 7358.6 | 879.7 | 0 | 1055415.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 147261 | BL-A | BL-A 35135005_MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH_08W - AUG 2021 | 2020-08-19 | 2022-06-08 | Not Started |  |  | Not Started | 2022-07-14 | Not Started | 2022-07-14 | Not Started | [9 empty] | 2022-08-26 | Not Started | [8 empty] | 2022-12-21 | Not Started | 2021-08-04 | 2022-12-21 | -504 | Behind Schedule | Not Started |  |  |  | 2023-08-10 | Not Started
35144588 | PSPS MITIGATION - ROSSMOOR 1106 |  | 5530161 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WALNTCRK | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144589 | PSPS MITIGATION - MORAGA 1103 |  | 5530161 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WALNTCRK | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144591 | PSPS MITIGATION - STAFFORD 1101 - PH1 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35144592 | PSPS MITIGATION - STAFFORD 1101 - PH2 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35148272 | CREATED IN ERROR |  | 5785220 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | 5789366 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6990 | 0 | 6990 | 1.3239 | 0 | 0 | 0 | 1.3239 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 36 | -36 | 36 | -36 | [10 empty] | 8 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | 5789378 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 1335 | 0 | 1335 | 0.25284 | 0 | 0 | 0 | 0.25284 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 22 | -22 | [10 empty] | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | 5789379 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 1930 | 0 | 1930 | 0.36553 | 0 | 0 | 0 | 0.36553 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | 5789380 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6550 | 0 | 6550 | 1.2405 | 0 | 0 | 0 | 1.2405 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 65 | -65 | 65 | -65 | [10 empty] | 14 | 13 | 13 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | 5789381 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3288 | 0 | 3288 | 0.62273 | 0 | 0 | 0 | 0.62273 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | 5789382 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3780 | 0 | 3780 | 0.71591 | 0 | 0 | 0 | 0.71591 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | 5789383 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3240 | 0 | 3240 | 0.61364 | 0 | 0 | 0 | 0.61364 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | 5789384 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 8886 | 0 | 8886 | 1.683 | 0 | 0 | 0 | 1.683 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | 5789385 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2961 | 0 | 2961 | 0.5608 | 0 | 0 | 0 | 0.5608 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | 5789386 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 4900 | 0 | 4900 | 0.92803 | 0 | 0 | 0 | 0.92803 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | 5789387 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5082 | 0 | 5082 | 0.9625 | 0 | 0 | 0 | 0.9625 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | 5789388 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3010 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0.57008 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | 5789389 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5268 | 0 | 5268 | 0.99773 | 0 | 0 | 0 | 0.99773 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | 5789390 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6100 | 0 | 6100 | 1.1553 | 0 | 0 | 0 | 1.1553 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 9 | -9 | 9 | -9 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | 5789391 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5900 | 0 | 5900 | 1.1174 | 0 | 0 | 0 | 1.1174 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | 5789392 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5465 | 0 | 5465 | 1.035 | 0 | 0 | 0 | 1.035 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 14 | -14 | 14 | -14 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | 5789393 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2440 | 0 | 2440 | 0.46212 | 0 | 0 | 0 | 0.46212 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 22 | -22 | [10 empty] | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | 5789394 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2080 | 0 | 2080 | 0.39394 | 0 | 0 | 0 | 0.39394 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | 5789395 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6332 | 0 | 6332 | 1.1992 | 0 | 0 | 0 | 1.1992 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | 5789396 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2415 | 0 | 2415 | 0.45739 | 0 | 0 | 0 | 0.45739 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155740 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.07 |  | 5789397 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3636 | 0 | 3636 | 0.68864 | 0 | 0 | 0 | 0.68864 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | 5789398 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 890 | 0 | 890 | 0.16856 | 0 | 0 | 0 | 0.16856 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 8 | -8 | 8 | -8 | [10 empty] | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | 5789399 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6100 | 0 | 6100 | 1.1553 | 0 | 0 | 0 | 1.1553 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 22 | -22 | [10 empty] | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155743 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.10 |  | 5789400 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3692 | 0 | 3692 | 0.69924 | 0 | 0 | 0 | 0.69924 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155744 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.11 |  | 5789401 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2671 | 0 | 2671 | 0.50587 | 0 | 0 | 0 | 0.50587 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | 5789402 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5910 | 0 | 5910 | 1.1193 | 0 | 0 | 0 | 1.1193 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155747 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.13 |  | 5789403 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 4025 | 0 | 4025 | 0.76231 | 0 | 0 | 0 | 0.76231 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155748 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.14 |  | 5789404 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2740 | 0 | 2740 | 0.51894 | 0 | 0 | 0 | 0.51894 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155749 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.15 |  | 5789405 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2662 | 0 | 2662 | 0.50417 | 0 | 0 | 0 | 0.50417 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | 5789406 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 8872 | 0 | 8872 | 1.6803 | 0 | 0 | 0 | 1.6803 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 15 | -15 | 15 | -15 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | 5789407 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2627 | 0 | 2627 | 0.49754 | 0 | 0 | 0 | 0.49754 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 22 | -22 | [10 empty] | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | 5789408 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2727 | 0 | 2727 | 0.51648 | 0 | 0 | 0 | 0.51648 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 7 | -7 | 7 | -7 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | 5789409 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 5611 | 0 | 5611 | 1.0627 | 0 | 0 | 0 | 1.0627 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 23 | -23 | 23 | -23 | [10 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | 5789410 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 6626 | 0 | 6626 | 1.2549 | 0 | 0 | 0 | 1.2549 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 16 | -16 | 16 | -16 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | 5789411 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 1431 | 0 | 1431 | 0.27102 | 0 | 0 | 0 | 0.27102 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 7 | -7 | 7 | -7 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | 5789412 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 9214 | 0 | 9214 | 1.7451 | 0 | 0 | 0 | 1.7451 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 54 | -54 | 54 | -54 | [10 empty] | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155757 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.07 |  | 5789413 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2913 | 0 | 2913 | 0.5517 | 0 | 0 | 0 | 0.5517 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | 5789414 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3510 | 0 | 3510 | 0.66477 | 0 | 0 | 0 | 0.66477 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 16 | -16 | 16 | -16 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155759 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.09 |  | 5789415 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 3500 | 0 | 3500 | 0.66288 | 0 | 0 | 0 | 0.66288 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155840 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.10 |  | 5789416 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2596 | 0 | 2596 | 0.49167 | 0 | 0 | 0 | 0.49167 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | 5789417 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 4491 | 0 | 4491 | 0.85057 | 0 | 0 | 0 | 0.85057 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 23 | -23 | 23 | -23 | [10 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | 5789418 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 808 | 0 | 808 | 0.15303 | 0 | 0 | 0 | 0.15303 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 14 | -14 | 14 | -14 | [10 empty] | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35117455 | BR-02-04-W (E) HERMAN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 423.9 | 0 | -423.9 | OverRun | Project is not in the WP or in 2020 WP | 0 | 1118 | -1118 | 1118 | -1118 | 1117.6 | 481.6 | -190 | 671.6 | 0 | 0 | 0 | 423.9 | 0 | 0 | 0 | 0 | 132 | 1 | 482 | 482 | 4 | 4 | 4 | 4 | 4 | 4
35118511 | BR-06-03-W (E) DEL MAR AVE PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -4752802 | 4752803 |  |  | 0 | 0 | 4752803 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 102 | -102 | 102 | -102 | 101.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1 | 1
35118513 | BR-06-04-W (E) HEAVENLY PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -4796148 | 4796149 |  |  | 0 | 0 | 4796149 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118515 | BR-07-02-W (E) YOUNG AVE PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 10638.7 | 0 | -10638.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 10639 | -10639 | 10639 | -10639 | 10638.7 | 0 | 0 | 0 | 0 | 0 | 0 | 10638.7 | 0 | 0 | 0 | 0 | 0 | 10578 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118516 | BR-07-04/03 W (E) PECK LN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -3213348 | 3213349 |  |  | 1036167.1 | 0 | 2177181.9 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3089104 | -3089104 | 3089104 | -3089104 | 3089563.5 | 467730.1 | 0 | 467730.1 | 0 | 0 | 459.7 | 1035707.4 | 0 | 0 | 3 | 3 | 3 | 398851 | 636849 | 467730 | 410223 | 212023 | 514123 | 416823 | 14471 | 18002
35118422 | BR-02-13-W (E) LANCASTER DR PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35118425 | BR-04-04-W (E) VALLEY VIEW PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 213.7 | 0 | -213.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 6 | -6 | 6 | -6 | 213.7 | 0 | 0 | 0 | 0 | 0 | 207.6 | 6.1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35118433 | BR-04-10/11-W (E) CRESTVIEW PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 129.6 | 0 | -129.6 | OverRun | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129.6 | -129.6 | 0 | 0 | 0 | 129.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 | E.5014535.03 | 5786056 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 7920 | 0 | 7920 | 1.5 | 0 | 0 | 0 | 1.5 | [5 empty] | 10000 | 0 | 10000 |  |  | 5570.2 | 0 | 4429.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 454 | -454 | 454 | -454 | 5570.2 | 0 | 0 | 0 | 0 | 327.6 | 4788.1 | 454.4 | 0 | 0 | 106 | 30 | 30 | 30 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 | E.5014535.04 | 5786057 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0 | 0.77 | [5 empty] | 10000 | 0 | 10000 |  |  | 5273.4 | 0 | 4726.6 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 484 | -484 | 484 | -484 | 5273.4 | 0 | 0 | 0 | 0 | 292.8 | 4497.2 | 483.5 | 0 | 0 | 142 | 29 | 29 | 28 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | 5786218 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 81 | -81 | 81 | -81 | [10 empty] | 17 | 16 | 16 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | 5786219 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OROVILLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 25 | -25 | 25 | -25 | [10 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | 5786220 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 55 | -55 | 55 | -55 | [10 empty] | 12 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B | E.5014534.02 | 5786052 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CUPRTINO | De Anza Assets | 0 | 4588 | 0 | 4588 | 0.86894 | 0 | 0 | 0 | 0.86894 | [5 empty] | 1 | -99999 | 100000 |  |  | 5704.2 | 0 | 94295.8 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 395 | -395 | 395 | -395 | 307811.6 | 34 | 0 | 34 | 0 | 362.4 | 5067.2 | 274.7 | 301987.3 | 0 | 146 | 32 | 32 | 32 | 32 | 34 | 34 | 34 | 17 | 0 | 0 | 0
35115080 | BR-02-10-W (E) HARVEY RD PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 2825.5 | 0 | -2825.5 | OverRun | Project is not in the WP or in 2020 WP | 0 | 2382 | -2382 | 2382 | -2382 | 2382 | 0 | 443.5 | -443.5 | 0 | 0 | 0 | 2825.5 | 0 | 0 | 0 | 2341 | 14 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35103619 | BR-10-03-W (E) FILBERT PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35099603 | MORRO BAY 1102 RECON 4728 FT W TW |  | 5530166 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | E.5020288.01 | 5784648 | UNSE | 08W | [6 empty] | Not in the WP |  |  | JACKSON | Stockton Assets | [14 empty] | 50000 | 0 | 50000 |  |  | 2947.5 | 0 | 47052.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 84 | -84 | 84 | -84 | 1265558.4 | 0 | 0 | 0 | 0 | 2766.5 | 97 | 84.1 | 1262610.9 | 0 | 18 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN |  | 5530162 | UNSE | 08W | [6 empty] | Not in the WP |  |  | RICHMOND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 |  | 5784105 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35076130 | TAMARACK 1101 WD 19-0011942 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | 5784376 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 26 | -26 | 26 | -26 | [10 empty] | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35105650 | BR-08-06-W (E) FICKETT LN PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | -6790955 | 6790956 |  |  | 4054538.6 | 0 | 2736417.4 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 3418438 | -3418438 | 3418438 | -3418438 | 4149813.7 | 95275.1 | 0 | 95275.1 | 0 | 8755 | 722620.4 | 3323163.2 | 0 | 0 | 411157 | 68424 | 1102436 | 852802 | 888345 | 95275 | 0 | 0 | 0 | 0 | 0 | 0
35112157 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112158 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112159 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | 5786098 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNMATEO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 49 | -49 | 49 | -49 | [10 empty] | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35112340 | *CANC*CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35112126 | BR-01-03-W (E) PARAGALIA PARB |  | 5786123 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | North Valley Assets | [14 empty] | 1 | 1 | 0 |  |  | 5.7 | 0 | -5.7 | OverRun | Project is not in the WP or in 2020 WP | 0 | 979 | -979 | 979 | -979 | 978.8 | 480.8 | -475 | 955.8 | 0 | 0 | 0 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 481 | 3 | 3 | 3 | 3 | 3 | 3
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 418 | -418 | 418 | -418 | [10 empty] | 87 | 83 | 83 | 83 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 172 | -172 | 172 | -172 | [10 empty] | 36 | 34 | 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 384 | -384 | 384 | -384 | [10 empty] | 80 | 76 | 76 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 850 | -850 | 850 | -850 | [10 empty] | 177 | 169 | 169 | 168 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 550 | -550 | 550 | -550 | [10 empty] | 115 | 109 | 109 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 658 | -658 | 658 | -658 | [10 empty] | 137 | 131 | 131 | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052729 | CWSP - BURNS 2101 - PH 1 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 409 | -409 | 409 | -409 | [10 empty] | 85 | 81 | 81 | 81 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052730 | CWSP - BURNS 2101- PH 2 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 187 | -187 | 187 | -187 | [10 empty] | 39 | 37 | 37 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052327 | CWSP-PARADISE 1101 OCB ZONE |  | 5530169 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052328 | CALISTOGA 1101 WIRE DOWN 18-0052856 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35048613 | CWSP - PARADISE 1106 - LR 2084 |  | 5530169 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 36960 | 0 | 36960 | 7 | 0 | 0 | 0 | 7 | [5 empty] | 500000 | 0 | 500000 |  |  | 15606.5 | 0 | 484393.5 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 13400928 | 0 | 0 | 0 | 6012.1 | 0 | 9594.4 | 0 | 13385321.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35049537 | CWSP - BIG BASIN 1102 - 9741 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35049538 | CWSP - BIG BASIN 1102 - 12758 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | 5786460 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 7 | -7 | 7 | -7 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | 5793711 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 17 | -17 | 17 | -17 | [10 empty] | 4 | 4 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | 5795126 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY |  | 0 | 4804.8 | 0 | 4804.8 | 0.91 | 0 | 0 | 0 | 0.91 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 18953 | -18953 | 18953 | -18953 | [10 empty] | 15922 | 2862 | -89 | 129 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052736 | CWSP - MIWUK 1701 LR11800 |  | 5784645 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 1506 | -1506 | 1506 | -1506 | [10 empty] | 139 | 132 | 132 | 131 | 131 | 182 | 188 | 188 | 188 | 94 | 0 | 0
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 284 | -284 | 284 | -284 | [10 empty] | 59 | 56 | 56 | 56 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 322 | -322 | 322 | -322 | [10 empty] | 67 | 64 | 64 | 64 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35052738 | CWSP-CURTIS1705-TS843-PHASE1 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT |  | 5530164 | UNSE | 08W | [6 empty] | 2022 | 2022 |  | GARBRVLE | Humboldt Division Assets | 0 | 9000 | 0 | 9000 | 1.7045 | 0 | 0 | 0 | 1.7045 | [5 empty] | 95000 | 0 | 95000 |  |  | 13257.7 | 0 | 81742.3 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 94257.7 | 0 | 0 | 0 | 2135.4 | 5409.6 | 5712.7 | 0 | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 130715 | WSHP | WSHP 190307 - 35050942_GARBERVILLE 1101 HENDRIX PILOT_08W - B1 | 2019-04-15 | 2022-07-29 | Not Started | 2022-08-02 | 2022-08-15 | Not Started | 2022-09-05 | Not Started | 2022-09-06 | Not Started | 2022-08-16 | 2022-08-16 | Not Started | 2022-08-17 | 2022-08-23 | Not Started | 2023-01-02 | 2023-01-31 | Not Started | 2023-02-01 | Not Started |  |  |  |  | 2023-02-01 | Not Started |  |  | 2023-04-03 | Not Started | 2019-11-04 | 2023-05-03 | -1276 | Behind Schedule | Not Started | 2023-05-04 | 2023-05-17 | Not Started | 2023-06-23 | Not Started
35050945 | CWSP - BRUNSWICK 1106 - 2143 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35050947 | CWSP - BRUNSWICK 1106 - 2794 - PH 1 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 1750 | -1750 | 1750 | -1750 | [10 empty] | 0 | 0 | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35050949 | CWSP - BRUNSWICK 1106 - 2794 - PH 2 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35050950 | CWSP - BRUNSWICK 1106 - 2794 - PH 3 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | 5530175 | UNSE | 08W | [6 empty] | 2022 | 2022 |  | STROSA | Sonoma Assets | 0 | 7400 | 0 | 7400 | 1.4015 | 0 | 0 | 0 | 1.4015 | [5 empty] | 95000 | 0 | 95000 |  |  | 25859.4 | 0 | 69140.6 | On/Under Budget | Request 2021 Budget | 0 | 2060 | -2060 | 2060 | -2060 | 94859.4 | 0 | 0 | 0 | 8053.2 | 6619.1 | 9127 | 2060.1 | 69000 | 0 | 1035 | 0 | 112 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 159683 | BL-B2 | BL-B2: 35050951_Monte Rio 1113 Hendrix_08W - Apr 21 | 2021-04-26 | 2022-07-29 | Not Started |  |  | Not Started | 2022-07-29 | Not Started | 2022-09-02 | Not Started | 2022-09-12 | 2022-09-12 | Not Started |  |  |  | 2023-01-03 | 2023-01-18 | Not Started | 2023-02-01 | Not Started |  |  |  |  | 2023-02-01 | Not Started |  |  | 2023-03-30 | Not Started | 2023-03-30 | 2023-03-30 | 0 | On/ Ahead Schedule | Not Started |  |  |  | 2023-05-22 | Not Started
35051252 | CWSP - PLACERVILLE 2106 - LR 1104 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  |  | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 351 | -351 | 351 | -351 | [10 empty] | 73 | 70 | 70 | 69 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 110 | -110 | 110 | -110 | [10 empty] | 23 | 22 | 22 | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047420 | CWSP - BRUNSWICK 1106 - LR 51486 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047422 | CWSP - PLACERVILLE 2106 - LR 1104 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  |  | UKIAH |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 368 | -368 | 368 | -368 | [10 empty] | 77 | 73 | 73 | 73 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047557 | *CANCEL*CWSP-BRUNSWICK 1105 LR-32536 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | GRSSVLLY | Sierra Assets | 0 | 46358.4 | 0 | 46358.4 | 8.78 | 0 | 0 | 0 | 8.78 | [5 empty] | 500000 | 0 | 500000 |  |  | 19712.7 | 0 | 480287.3 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 16776600.9 | 0 | 0 | 0 | 4101.4 | 0 | 15611.3 | 0 | 16756888.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35048009 | CWSP - APPLE HILL 2102 LR97982 HARDENING |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT |  | 5530164 | UNSE | 08W | [6 empty] | 2022 | 2022 |  | GARBRVLE | Humboldt Division Assets | 0 | 4000 | 0 | 4000 | 0.75758 | 0 | 0 | 0 | 0.75758 | [5 empty] | 95000 | 0 | 95000 |  |  | 23788.8 | 0 | 71211.2 | On/Under Budget | Request 2021 Budget | 0 | 0 | 0 | 0 | 0 | 94788.8 | 0 | 0 | 0 | 3303 | 16284.3 | 4201.5 | 0 | 71000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2021-06-18 | 130720 | WSHP | WSHP 190307 - 35046211_GARBERVILLE 1102 HENDRIX PILOT_08W - B1 | 2019-04-15 | 2022-07-29 | Not Started | 2022-08-01 | 2022-08-12 | Not Started | 2022-09-05 | Not Started | 2022-09-05 | Not Started | 2022-09-13 | 2022-09-13 | Not Started |  |  |  | 2023-01-02 | 2023-01-13 | Not Started | 2023-02-01 | Not Started |  |  |  |  | 2023-02-01 | Not Started |  |  | 2023-02-10 | Not Started | 2019-10-09 | 2023-02-14 | -1224 | Behind Schedule | Not Started |  |  |  | 2023-04-06 | Not Started
35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35047311 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 1 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | 5782531 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 169 | -169 | 169 | -169 | [10 empty] | 35 | 34 | 34 | 33 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | NAPA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 39 | -39 | 39 | -39 | [10 empty] | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | 5530174 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 234 | -234 | 234 | -234 | [10 empty] | 49 | 46 | 46 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | 5782589 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 182 | -182 | 182 | -182 | [10 empty] | 38 | 36 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | 5782592 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 86 | -86 | 86 | -86 | [10 empty] | 18 | 17 | 17 | 17 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 | E.5015425.01 | 5782581 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 1 | 0 |  |  | 21522.3 | 0 | -21522.3 | OverRun | Project is not in the WP or in 2020 WP | 0 | 613 | -613 | 613 | -613 | 21522.3 | 0 | 0 | 0 | 5694.8 | 9046.4 | 6167.9 | 613.2 | 0 | 0 | 128 | 122 | 122 | 121 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | 5782582 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 501 | -501 | 501 | -501 | [10 empty] | 105 | 100 | 100 | 99 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | 5782583 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2313 | -2313 | 2313 | -2313 | [10 empty] | 305 | 400 | 1386 | 111 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | 5782584 | UNSE | 08W | [6 empty] | 2021 |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Budget Allocated | 775000 | 2202 | 772798 | 2202 | 772798 | [10 empty] | 78 | 75 | 75 | 532 | 1442 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | 5782585 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 349 | -349 | 349 | -349 | [10 empty] | 73 | 69 | 69 | 69 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | 5783062 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 4562 | 0 | 4562 | 0.86402 | 0 | 0 | 0 | 0.86402 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 587 | -587 | 587 | -587 | [10 empty] | 122 | 117 | 117 | 116 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | 5783063 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2465 | 0 | 2465 | 0.46686 | 0 | 0 | 0 | 0.46686 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 480 | -480 | 480 | -480 | [10 empty] | 100 | 95 | 95 | 95 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | 5783064 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY |  | 0 | 2534 | 0 | 2534 | 0.47992 | 0 | 0 | 0 | 0.47992 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 1052 | -1052 | 1052 | -1052 | [10 empty] | 219 | 209 | 209 | 208 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | 5782527 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 195 | -195 | 195 | -195 | [10 empty] | 41 | 39 | 39 | 39 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | 5782528 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 99 | -99 | 99 | -99 | [10 empty] | 21 | 20 | 20 | 19 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | 5782529 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PLCRVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 135 | -135 | 135 | -135 | [10 empty] | 28 | 27 | 27 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | 5782841 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 22 | -22 | 22 | -22 | [10 empty] | 5 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060027 | CWSP-PARADISE 1104-TS 1571 |  | 5530169 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CHICO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  |  | FORTUNA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | 5782761 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 7 | -7 | 7 | -7 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | 5782591 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 50 | -50 | 50 | -50 | [10 empty] | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | 5783289 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB |  | 0 | 10900 | 0 | 10900 | 2.0644 | 0 | 0 | 0 | 2.0644 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 2620 | -2620 | 2620 | -2620 | [10 empty] | 1363 | 316 | 316 | 313 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35073059 | SONOMA1104 WIREDOWN |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | 5784143 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 32 | -32 | 32 | -32 | [10 empty] | 7 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | 5783177 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 133 | -133 | 133 | -133 | [10 empty] | 28 | 26 | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 | E.5015574.01 | 5783198 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | Sierra Assets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100000 | 0 | 100000 |  |  | 7332.9 | 0 | 92667.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 209 | -209 | 209 | -209 | 7332.9 | 0 | 0 | 0 | 3336.1 | 3311.4 | 476.4 | 209 | 0 | 0 | 44 | 42 | 42 | 41 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | 5783199 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 189 | -189 | 189 | -189 | [10 empty] | 39 | 38 | 38 | 37 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | 5783059 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GRSSVLLY | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 54 | -54 | 54 | -54 | [10 empty] | 11 | 11 | 11 | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | 5782762 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 188 | -188 | 188 | -188 | [10 empty] | 3 | 2 | 176 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35060383 | WDDB - FRUITLAND 1142CB C/O 1679 |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  |  | GARBRVLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO |  | 5513264 | UNSE | 08W | [6 empty] | Not in the WP |  |  | FTBRAGG | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31089263 | MOVE FUSE 1179/RECON WITH TREE WIRE |  | 5530161 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | CONCORD |  | 0 | 400 | 0 | 400 | 0.075758 | 0 | 0 | 0 | 0.075758 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31361969 | RECON 9,400 FT - POINT ARENA 1101 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW |  | 5530166 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31374249 | 14184 FT OF 4ACSR&3363 FT OF 6CUW 2CU TW |  | 5530166 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNRAFAEL | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | 5530168 | UNSE | 08W | [6 empty] | Not in the WP |  | SH | NAPA |  | 7180.8 | 316.8 | 0 | 7497.6 | 1.42 | 0 | 0 | 0 | 1.42 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 4586 | -4586 | 4586 | -4586 | [10 empty] | 1285 | 3301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SALINAS | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35024647 | RR 2104 RECOND 1051 ZONE W TW |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WTSNVLLE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SALINAS | Central Coast Assets | [14 empty] | 1 | -49999 | 50000 |  |  | 8820.9 | 0 | 41179.1 | On/Under Budget | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | 8820.9 | 0 | 0 | 0 | 2339.3 | 6481.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY |  | 5530161 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CONCORD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PTARENA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW |  | 5530166 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNLUISOB | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31334290 | RECON 24 SPANS -ALBION RIDGE RD |  | 5533649 | UNSE | 08W | [6 empty] | Not in the WP |  |  | FTBRAGG | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | PTARENA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 1371 | -1371 | 1371 | -1371 | [10 empty] | 0 | 0 | 1371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31288039 | HOOPA 1101 RCOND WITH TREE WIRE |  | 5530164 | UNSE | 08W | [6 empty] | Not in the WP |  |  | WLLWCRK | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042421 | CWSP - MIWUK 1701 - LR 8050 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 |  | 5530173 | UNSE | 08W | [6 empty] | Not in the WP |  |  | AUBURN | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0
35040017 | CWSP - OAK K 1102 OCB LVL 1 HARDENING |  | 5530162 | UNSE | 08W | [6 empty] | Not in the WP |  |  | OAKLAND | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35040018 | CWSP - MORAGA 1101 (VARIOUS) - OCB |  | 5530161 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CONCORD | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35040118 | CWSP: MIWUK 1701_OCB WILDFIRE HARDENING |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042365 | CWSP - CAMP EVERS 2106 - LR 60124 - PH 5 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042366 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 4 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042367 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 3 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042368 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 2 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35042369 | CWSP - CAMP EVERS 2106 - 60124 - PHASE 1 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35039982 | CWSP: MIWUK 1702_OCB WILDFIRE HARDENING |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35039748 | CWSP-MIWUK 1702-LR 38218 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW |  | 5530174 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SNJOSE | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043311 | CWSP - MIWUK 1701- LR8060 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043381 | CWSP-MIWUK 1702-LR 6018-PHASE 1 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043384 | CWSP-CURTIS 1705 - TS843 & 10590 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043604 | CWSP - MIWUK 1702 - LR6018 - PHASE 2 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043950 | CWSP - MIWUK 1701 - LR 10600 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043952 | CWSP - MIWUK 1702 - LR 8090 |  | 5530178 | UNSE | 08W | [6 empty] | Not in the WP |  |  | SONORA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043830 | CWSP - MIRABEL 02 /MONTE RIO 13 - LR 652 |  | 5530175 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STROSA | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 267 | -267 | 267 | -267 | [10 empty] | 56 | 53 | 53 | 53 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 241 | -241 | 241 | -241 | [10 empty] | 50 | 48 | 48 | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35044115 | CWSP - ROB ROY 2105 - LR 5166 |  | 5530159 | UNSE | 08W | [6 empty] | Not in the WP |  |  | STCRUZ | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 |  | 5530160 | UNSE | 08W | [6 empty] | Not in the WP |  |  | CUPRTINO | [24 empty] | Project is not in the WP or in 2020 WP | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B771: [REDACTED]: move it to 2022 and request budget for 2021 and $500k and the rest is 2022

## DOT_Changes
Change ID | Change Request Type | Order | Notification | Order Description | Change Request Status | MAT | Sub-Category | Updated Sub-Category | Civil Resource | Electric Resource | New Civil Resource | New Electric Resource | Business Justification | Work Plan Date | Updated Work Plan Date | Est Const Hours | Authorized Amount | Initial Funding Year | New Construction Complete Year | Updated New Construction Complete Year | MPP Approved Budget (2020) | MPP Approved Budget (2021) | Requested Budget for 2020 | Requested Budget for 2021 | Requested Budget for 2022 | Requested Budget for 2023 | Req End Date | User Status | CN24 Out Date | CSTRT Finish Date (P6) | Job Owner | Job Owner Name | Strike Force Population | Exclusions | Updated Strike Force Population | Updated Exclusions | Past Due Reason | Estimating Review | Estimating Comments | Construction Review | Construction Comments | Program Manager | Program Manager Review | Program Manager Comments | Warning Message | Portfolio Manager Review | Portfolio Manager Comments | Last Changed By | Last Changed On | Last Changed Name | Created By | Created On | Creator Name | Updated Order Number | Project Reporting Year | MPP Work Plan
102642 | Budget change | 35226627 |  | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Portfolio Mgr. Review | 08W | [6 empty] | More accurate forecast available | [10 empty] | 855000 |  |  |  | PEND | [20 empty] | 2021-06-22 15:25 |  |  | 2021-06-22 15:25 |  |  |  | Not in Work Plan
102643 | Budget change | 35226630 |  | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Portfolio Mgr. Review | 08W | [6 empty] | More accurate forecast available | [10 empty] | 3400000 |  |  |  | PEND | [20 empty] | 2021-06-22 15:25 |  |  | 2021-06-22 15:25 |  |  |  | Not in Work Plan
102644 | Budget change | 35226631 |  | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Portfolio Mgr. Review | 08W | [6 empty] | More accurate forecast available | [10 empty] | 3975000 |  |  |  | PEND | [20 empty] | 2021-06-22 15:25 |  |  | 2021-06-22 15:25 |  |  |  | Not in Work Plan
102645 | Budget change | 35217268 |  | CWSP - BUCKS CREEK 1101 CB PH 1 | Portfolio Mgr. Review | 08W | [6 empty] | More accurate forecast available | [10 empty] | 600000 |  |  |  | PEND | [20 empty] | 2021-06-22 15:25 |  |  | 2021-06-22 15:25 |  |  |  | Not in Work Plan
102641 | Budget change | 35129767 |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Portfolio Mgr. Review | 08W | [6 empty] | More accurate forecast available | [10 empty] | 46000 |  |  |  | ESTS | [20 empty] | 2021-06-22 15:24 |  |  | 2021-06-22 15:24 |  |  |  | Not in Work Plan
102639 | Defer project | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Estimating Review | 08W | [6 empty] | Project requires redesign due to other substation work conflicting our scope along with acquiring an easement. | 2021-10-15 | 2022-07-14 | 1371.6 | 409121.04 | 2021 |  | 2022 |  | 475000 |  | 300000 |  |  | 2021-12-31 | ESTS |  | 2021-10-15 | [18 empty] | 2021-06-22 15:00 |  |  | 2021-06-22 15:00 |  |  | 2021 | Order and Notification
102554 | Budget change | 74022384 | 114753320 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Portfolio Mgr. Review | 08W | 220 Mile Plan | [5 empty] | Decrease 2021 MPP Budget for completed project going through closing | 2020-06-08 |  | 8146.3 | 9998553 | 2020 | 2021 |  | 3838756.17 | 2395900 |  | 2050000 |  |  | 2020-12-31 | CONS |  | 2020-06-08 | [18 empty] | 2021-06-21 16:28 |  |  | 2021-06-21 16:28 |  |  | 2021 | Order and Notification
102553 | Budget change | 74028021 | 117755928 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 | Portfolio Mgr. Review | 08W | 220 Mile Plan | [5 empty] | Increase 2021 MPP Budget to cover additional veg costs | 2020-05-05 |  | 4918 | 4467090 | 2020 |  |  | 107290.2 | 173177.8 |  | 502394 |  |  | 2020-12-15 | CONS |  | 2020-05-05 | [18 empty] | 2021-06-21 16:27 |  |  | 2021-06-21 16:27 |  |  | 2020 | Order and Notification
102549 | Budget change | 35227655 | 120462115 | CWSP - KIRKER 2104442850 PH 1.2 | Portfolio Mgr. Review | 08W | [6 empty] | Set 2021 MPP Budget to complete design and clear dependencies. Project defered to 2022 | 2022-06-06 |  | 80 | 450000 | 2021 | 2022 |  |  |  |  | 102800 |  |  | 2021-12-31 | UNSE |  | 2022-06-06 | [18 empty] | 2021-06-21 16:15 |  |  | 2021-06-21 16:15 |  |  | 2022 | Order and Notification
102548 | Budget change | 35144944 | 118261958 | PSPS - SNEATH LANE 1107 - LR 48338 | Portfolio Mgr. Review | 08W | [6 empty] | Increase 2021 MPP Budget for project approved by WGSC to be built in 2022 | 2022-06-15 |  | 768.8 | 500000 | 2022 |  |  | 1712227.1 | 8662.9 |  | 21300 |  |  | 2020-12-30 | PEND |  | 2022-06-15 | [18 empty] | 2021-06-21 16:14 |  |  | 2021-06-21 16:14 |  |  | 2022 | Order and Notification
102547 | Budget change | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Portfolio Mgr. Review | 08W | [6 empty] | Set 2021 MPP Budget to complete design and clear dependencies. Project defered to 2022 | 2022-06-13 |  | 1068.1 | 621258.86 | 2021 | 2022 |  |  |  |  | 203000 |  |  | 2021-12-31 | PEND |  | 2022-06-13 | [18 empty] | 2021-06-21 16:12 |  |  | 2021-06-21 16:12 |  |  | 2022 | Order and Notification
102546 | Budget change | 35219093 | 120141622 | CWSP - TIDEWATER 210614072 PH 1.1 | Portfolio Mgr. Review | 08W | [6 empty] | Increase 2021 MPP Budget to complete design. Project defered to 2022 | 2022-04-25 |  | 80 | 350000 | 2021 | 2022 |  |  | 8255 |  | 52500 |  |  | 2021-12-31 | UNSE |  | 2022-04-25 | [18 empty] | 2021-06-21 16:11 |  |  | 2021-06-21 16:11 |  |  | 2022 | Order and Notification
102545 | Budget change | 35231543 | 120504099 | CWSP - TIDEWATER 210614072 PH 1.2 | Portfolio Mgr. Review | 08W | [6 empty] | Increase 2021 MPP Budget to complete design. Project defered to 2022 | 2022-04-25 |  | 80 | 350000 | 2021 | 2022 |  |  | 5000 |  | 8806 |  |  | 2021-12-31 | ESTS |  | 2022-04-25 | [18 empty] | 2021-06-21 16:08 |  |  | 2021-06-21 16:08 |  |  | 2022 | Order and Notification
102544 | Budget change | 35231544 | 120504131 | CWSP - TIDEWATER 210614072 PH 1.3 | Portfolio Mgr. Review | 08W | [6 empty] | Set 2021 MPP Budget to complete project this year. BC approved | 2021-07-19 |  | 2052.9 | 565748.51 | 2021 | [5 empty] | 1555955.5 |  |  | 2021-12-31 | UNSC |  | 2021-07-19 | [18 empty] | 2021-06-21 16:08 |  |  | 2021-06-21 16:08 |  |  | 2021 | Order and Notification
102543 | Budget change | 35219096 | 120141671 | CWSP - KIRKER 2104442850 PH 1.1 | Portfolio Mgr. Review | 08W | [6 empty] | Increase 2021 MPP Budget to complete design. Project defered to 2022 | 2022-04-25 |  | 80 | 500000 | 2021 | 2022 |  |  | 8302 |  | 16800 |  |  | 2021-12-31 | UNSE |  | 2022-04-25 | [18 empty] | 2021-06-21 16:05 |  |  | 2021-06-21 16:05 |  |  | 2022 | Order and Notification
102542 | Budget change | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Portfolio Mgr. Review | 08W | [6 empty] | Decrease 2021 MPP Budget for defered project to 2022 | 2022-05-09 |  | 180 | 550000 | 2021 | 2022 |  |  | 852800 |  | 157000 |  |  | 2023-12-31 | ESTS |  | 2022-05-09 | [18 empty] | 2021-06-21 16:04 |  |  | 2021-06-21 16:04 |  |  | 2022 | Order and Notification
102541 | Budget change | 35053033 | 114688204 | CWSP - TASSAJARA 2112 - FUSE 18053 | Portfolio Mgr. Review | 08W | 220 Mile Plan | [5 empty] | Returning 2021 MPP Budget for completed project in FICL | 2019-12-03 |  | 11746.9 | 9709000 | 2020 |  |  | 8728000 | 368855 |  | 88383 |  |  | 2019-12-31 | FICL | 2021-01-13 | 2019-12-03 | [18 empty] | 2021-06-21 16:00 |  |  | 2021-06-21 16:00 |  |  | 2020 | Order and Notification
101999 | Budget change | 35219268 | 120142035 | CWSP - MARIPOSA 210197142 PH 1 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-09-14 |  | 3531.3 | 1289702.13 | 2021 |  |  |  | 1670921 |  | 1670921 |  |  | 2021-12-31 | PEND |  | 2021-09-14 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 11:12 |  |  | 2021 | Order and Notification
101996 | Budget change | 35225825 | 120426401 | CWSP - DESCHUTES 11049718 PH2.1 | Approved | 08W | [6 empty] | Business case has been approved and forecast has been updated. | 2021-08-09 |  | 2973.4 | 2167192 | 2021 |  |  |  | 2167192 |  | 2167192 |  |  | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:50 |  |  | 2021 | Order and Notification
101995 | Budget change | 35232445 | 120528752 | CWSP - DESCHUTES 11049718 PH 2.5 | Approved | 08W | [6 empty] | Business case has been approved and forecast has been updated | 2021-08-02 |  | 3721.2 | 3055462 | 2021 |  |  |  | 3055462 |  | 3055462 |  |  | 2021-12-31 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:49 |  |  | 2021 | Order and Notification
101993 | Budget change | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP approved budget with 2021 CY EAC | 2021-10-15 |  | 1371.6 | 409121.04 | 2021 |  |  |  | 475000 |  | 475000 |  |  | 2021-12-31 | ESTS |  | 2021-10-15 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:21 |  |  | 2021 | Order and Notification
101992 | Budget change | 35227033 | 120449807 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP approved budget with 2021 CY EAC | 2021-11-30 |  | 80 | 237833 | 2021 |  |  |  | 237833 |  | 237833 |  |  | 2021-12-31 | UNSE |  | 2021-11-30 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:21 |  |  | 2021 | Order and Notification
101991 | Budget change | 35227032 | 120449806 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP approved budget with 2021 CY EAC | 2021-10-01 |  | 522 | 201909.68 | 2021 |  |  |  | 237833 |  | 237833 |  |  | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:21 |  |  | 2021 | Order and Notification
101990 | Budget change | 35191937 | 119553837 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP approved budget with 2021 CY EAC | 2021-10-01 |  | 0 | 237833 | 2021 |  |  |  | 237833 |  | 237833 |  |  | 2022-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 10:21 |  |  | 2021 | Order and Notification
101981 | Budget change | 35235677 | 120598407 | FRRB - BIG BEND 1102 - B4 PH4.1 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget $15M for this job. The scope of this job is UG with 6 miles | 2021-07-19 |  | 2092.8 | 14162767.73 | 2021 |  |  |  | 18298258 | 0 | 15000000 | 0 | 0 | 2022-05-07 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 07:50 |  |  | 2021 | Order and Notification
101977 | Budget change | 35242428 | 120753070 | FRRB - BIG BEND 1102 - B4 PH4.2 | Approved | 08W | [6 empty] | requesting budget for 2021 | 2021-08-27 |  | 0 | 200000 | 2021 |  |  |  | 3963125 | 0 | 3963125 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 07:46 |  |  | 2021 | Order and Notification
101978 | Budget change | 35235677 | 120598407 | FRRB - BIG BEND 1102 - B4 PH4.1 | Approved | 08W | [6 empty] | requesting budget for 2021 | 2021-07-19 |  | 2092.8 | 14162767.73 | 2021 |  |  |  | 18298258 | 0 | 3298258 | 0 | 0 | 2022-05-07 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-17 13:57 |  |  | 2021-06-17 07:44 |  |  | 2021 | Order and Notification
101730 | Budget change | 35250343 | 121318070 | FRRB - KANAKA 1101CB - K2 SM1 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with forecast | 2021-06-28 |  | 0 | 1 | 2021 |  |  |  | 971117 | 0 | 971117 | 0 | 0 | 2022-05-13 | ESTS |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:12 |  |  | 2021 | Order and Notification
101723 | Budget change | 35236989 | 120627501 | FRRB - KANAKA 1101 - K2 PH2.2 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-08-17 |  | 217.9 | 297255.39 | 2021 |  |  |  | 975189 | 0 | 975189 | 0 | 0 | 2022-05-07 | PEND |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:02 |  |  | 2021 | Order and Notification
101722 | Budget change | 35236999 | 120627599 | FRRB - KANAKA 1101 - K5 PH5.2 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-06-28 |  | 204.6 | 101106 | 2021 |  |  |  | 332500 | 0 | 332500 | 0 | 0 | 2022-06-30 | PEND |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:01 |  |  | 2021 | Order and Notification
101721 | Budget change | 35235701 | 120599070 | FRRB - KANAKA 1101 - K2 PH2.1 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-06-28 |  | 154.8 | 475000 | 2021 |  |  |  | 207273 | 0 | 207273 | 0 | 0 | 2022-05-07 | UNSC |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:01 |  |  | 2021 | Order and Notification
101720 | Budget change | 35236986 | 120627456 | FRRB - KANAKA 1101 - K5 PH5.4 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-08-12 |  | 0 | 237500 | 2021 |  |  |  | 3344072 | 0 | 3344072 | 0 | 0 | 2022-05-07 | ADER |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:01 |  |  | 2021 | Order and Notification
101719 | Budget change | 35237020 | 120627702 | FRRB - KANAKA 1101 - K5 PH5.3 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-07-30 |  | 409.9 | 207149.33 | 2021 |  |  |  | 950000 | 0 | 950000 | 0 | 0 | 2022-06-30 | PEND |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:01 |  |  | 2021 | Order and Notification
101718 | Budget change | 35235704 | 120599076 | FRRB - KANAKA 1101 - K5 PH5.1 | Approved | 08W | [6 empty] | requesting 2021 MPP budget to align with forecast | 2021-06-28 |  | 217.3 | 187374.83 | 2021 |  |  |  | 359129 | 0 | 359129 | 0 | 0 | 2022-05-07 | PEND |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-16 11:01 |  |  | 2021 | Order and Notification
101042 | Budget change | 35226856 | 120449149 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W | [6 empty] | Business Case approved via EDRS 2021-33451. | 2021-07-15 |  | 847.8 | 2418866 | 2021 |  |  |  | 1640040 |  | 1640040 | 3749 |  | 2021-12-31 | UNSC |  | 2021-07-15 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:34 |  |  | 2021 | Order and Notification
101041 | Budget change | 35236983 | 120627452 | FRRB - BIG BEND 1102 - B5 PH5.3 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-20 |  | 80 | 4431245 | 2021 |  |  |  | 2451150 | 0 | 2451150 | 0 | 0 | 2022-05-07 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:28 |  |  | 2021 | Order and Notification
101040 | Budget change | 35235678 | 120598535 | FRRB - BIG BEND 1102 - B5 PH5.1 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 4340396 | 2021 |  |  |  | 2381301 | 0 | 2381301 | 0 | 0 | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:28 |  |  | 2021 | Order and Notification
101039 | Budget change | 35235679 | 120598623 | FRRB - BIG BEND 1102 - B6 PH6.1 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 5075596 | 2021 |  |  |  | 3088251 | 0 | 3088251 | 0 | 0 | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:27 |  |  | 2021 | Order and Notification
101038 | Budget change | 35233166 | 120541098 | FRRB - BIG BEND 1102 - B5 PH5.2 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 6979245 | 2021 |  |  |  | 4411150 | 0 | 4411150 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:27 |  |  | 2021 | Order and Notification
101037 | Budget change | 35242426 | 120753018 | FRRB - BIG BEND 1102 - B6 PH6.7 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 2906150 | 0 | 2906150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:27 |  |  | 2021 | Order and Notification
101036 | Budget change | 35242425 | 120753017 | FRRB - BIG BEND 1102 - B6 PH6.6 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 4901150 | 0 | 4901150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:27 |  |  | 2021 | Order and Notification
101035 | Budget change | 35242427 | 120753019 | FRRB - BIG BEND 1102 - B6 PH6.8 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 3851150 | 0 | 3851150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:27 |  |  | 2021 | Order and Notification
101034 | Budget change | 35242422 | 120753013 | FRRB - BIG BEND 1102 - B6 PH6.3 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 5295819 | 2021 |  |  |  | 3116224 | 0 | 3116224 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:26 |  |  | 2021 | Order and Notification
101033 | Budget change | 35242423 | 120753015 | FRRB - BIG BEND 1102 - B6 PH6.4 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 7343245 | 2021 |  |  |  | 4691150 | 0 | 4691150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:26 |  |  | 2021 | Order and Notification
101032 | Budget change | 35242424 | 120753016 | FRRB - BIG BEND 1102 - B6 PH6.5 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 2381150 | 0 | 2381150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:26 |  |  | 2021 | Order and Notification
101031 | Budget change | 35242421 | 120753012 | FRRB - BIG BEND 1102 - B6 PH6.2 | Approved | 08W | [6 empty] | requesting MPP budget to align with expected case number | 2021-08-27 |  | 80 | 5841745 | 2021 |  |  |  | 3536150 | 0 | 3536150 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 16:26 |  |  | 2021 | Order and Notification
100880 | Budget change | 35249161 | 120950640 | FRRB - WYANDOTTE 11031974 - W3 SM3 | Approved | 08W | [6 empty] | requesting budget for 2021 workplan | 2021-07-15 |  | 354.6 | 100000 | 2021 |  |  |  | 795454.5455 | 0 | 795454.5455 | 0 | 0 | 2022-05-07 | PEND | [17 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 14:23 |  |  | 2021 | Order and Notification
100879 | Budget change | 35244573 | 120830881 | FRRB - WYANDOTTE 11031974 - W3 SM1 | Approved | 08W | [6 empty] | requesting budget for 2021 workplan | 2021-07-07 |  | 80 | 100000 | 2021 |  |  |  | 464015.1515 | 0 | 464015.1515 | 0 | 0 | 2022-04-16 | UNSE |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 14:22 |  |  | 2021 | Order and Notification
100878 | Budget change | 35244574 | 120830887 | FRRB - WYANDOTTE 11031974 - W3 SM2 | Approved | 08W | [6 empty] | requesting budget for 2021 workplan | 2021-07-07 |  | 80 | 100000 | 2021 |  |  |  | 232007.5758 | 0 | 232007.5758 | 0 | 0 | 2022-04-16 | UNSE |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 14:22 |  |  | 2021 | Order and Notification
100875 | Budget change | 35235673 | 120594874 | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Approved | 08W | [6 empty] | requesting 2021 budget to align with expected case number | 2021-08-20 |  | 80 | 5064020 | 2021 |  |  |  | 3078290 | 0 | 3078290 | 0 | 0 | 2022-05-03 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:30 |  |  | 2021 | Order and Notification
100873 | Budget change | 35244698 | 120849797 | FRRB - KANAKA 1101 - K4 PH 4.3 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-02 |  | 62.5 | 1693957 | 2021 |  |  |  | 668184 | 0 | 668184 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:21 |  |  | 2021 | Order and Notification
100872 | Budget change | 35244699 | 120849798 | FRRB - KANAKA 1101 - K4 PH 4.4 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-03 |  | 38.4 | 1606478 | 2021 |  |  |  | 600892 | 0 | 600892 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100871 | Budget change | 35244697 | 120849796 | FRRB - KANAKA 1101 - K4 PH 4.2 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-30 |  | 77 | 1762257 | 2021 |  |  |  | 720722 | 0 | 720722 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100870 | Budget change | 35244696 | 120849795 | FRRB - KANAKA 1101 - K4 PH 4.1 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-12 |  | 223.5 | 2190296 | 2021 |  |  |  | 1049983 | 0 | 1049983 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-12 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100869 | Budget change | 35240543 | 120720968 | FRRB - KANAKA 1101 - K4 PH 4.18 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-12 |  | 651.7 | 4451656 | 2021 |  |  |  | 2789491 | 0 | 2789491 | 0 | 0 | 2022-05-07 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100868 | Budget change | 35240542 | 120720967 | FRRB - KANAKA 1101 - K4 PH 4.19 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-12 |  | 704.4 | 3122627 | 2021 |  |  |  | 1767161 | 0 | 1767161 | 0 | 0 | 2022-05-07 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100867 | Budget change | 35245144 | 120850156 | FRRB - KANAKA 1101 - K4 PH 4.9 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-03 |  | 123.4 | 2078491 | 2021 |  |  |  | 963979 | 0 | 963979 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100866 | Budget change | 35245149 | 120850485 | FRRB - KANAKA 1101 - K4 PH 4.14 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-19 |  | 111.7 | 2127143 | 2021 |  |  |  | 1001404 | 0 | 1001404 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100865 | Budget change | 35245152 | 120850488 | FRRB - KANAKA 1101 - K4 PH 4.17 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-03 |  | 3 | 2871418 | 2021 |  |  |  | 1573923 | 0 | 1573923 | 0 | 0 | 2022-04-20 | ADER |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:20 |  |  | 2021 | Order and Notification
100864 | Budget change | 35245146 | 120850158 | FRRB - KANAKA 1101 - K4 PH 4.11 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-17 |  | 85 | 1799681 | 2021 |  |  |  | 749510 | 0 | 749510 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100863 | Budget change | 35245148 | 120850482 | FRRB - KANAKA 1101 - K4 PH 4.13 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-20 |  | 176.9 | 1979318 | 2021 |  |  |  | 887692 | 0 | 887692 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100862 | Budget change | 35245145 | 120850157 | FRRB - KANAKA 1101 - K4 PH 4.10 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-09 |  | 76.6 | 1697232 | 2021 |  |  |  | 670703 | 0 | 670703 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100861 | Budget change | 35245141 | 120850151 | FRRB - KANAKA 1101 - K4 PH 4.6 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-23 |  | 58.6 | 1561101 | 2021 |  |  |  | 565987 | 0 | 565987 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-23 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100860 | Budget change | 35245147 | 120850159 | FRRB - KANAKA 1101 - K4 PH 4.12 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-12 |  | 245.3 | 2433087 | 2021 |  |  |  | 1236745 | 0 | 1236745 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100859 | Budget change | 35245142 | 120850154 | FRRB - KANAKA 1101 - K4 PH 4.7 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-09 |  | 52.3 | 1585427 | 2021 |  |  |  | 584699 | 0 | 584699 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100858 | Budget change | 35245150 | 120850486 | FRRB - KANAKA 1101 - K4 PH 4.15 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-20 |  | 92.1 | 1776758 | 2021 |  |  |  | 731877 | 0 | 731877 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100857 | Budget change | 35245151 | 120850487 | FRRB - KANAKA 1101 - K4 PH 4.16 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-07-13 |  | 77.2 | 1779097 | 2021 |  |  |  | 733676 | 0 | 733676 | 0 | 0 | 2022-04-20 | PEND |  | 2021-07-13 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:19 |  |  | 2021 | Order and Notification
100856 | Budget change | 35245143 | 120850155 | FRRB - KANAKA 1101 - K4 PH 4.8 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-06-29 |  | 188.9 | 2067264 | 2021 |  |  |  | 955343 | 0 | 955343 | 0 | 0 | 2022-04-20 | PEND |  | 2021-06-29 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:18 |  |  | 2021 | Order and Notification
100855 | Budget change | 35245140 | 120850150 | FRRB - KANAKA 1101 - K4 PH 4.5 | Approved | 08W | [6 empty] | Requesting to have MPP Budget align with Expected case figure | 2021-08-05 |  | 277.1 | 2115915 | 2021 |  |  |  | 992767 | 0 | 992767 | 0 | 0 | 2022-04-20 | PEND |  | 2021-08-05 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:18 |  |  | 2021 | Order and Notification
100854 | Budget change | 35242420 | 120751312 | FRRB - BIG BEND 1102 - B1 PH1.4 | Approved | 08W | [6 empty] | requeting budget for 2021 | 2021-08-06 |  | 135.7 | 237500 | 2021 |  |  |  | 219294.16 | 0 | 219294.16 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:16 |  |  | 2021 | Order and Notification
100853 | Budget change | 35241079 | 120751310 | FRRB - BIG BEND 1102 - B1 PH1.3 | Approved | 08W | [6 empty] | requeting budget for 2021 | 2021-07-16 |  | 129.3 | 237500 | 2021 |  |  |  | 180007.89 | 0 | 180007.89 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:15 |  |  | 2021 | Order and Notification
100852 | Budget change | 35241078 | 120751299 | FRRB - BIG BEND 1102 - B1 PH1.2 | Approved | 08W | [6 empty] | requeting budget for 2021 | 2021-08-02 |  | 177.9 | 237500 | 2021 |  |  |  | 408885.89 | 0 | 408885.89 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:15 |  |  | 2021 | Order and Notification
100851 | Budget change | 35235674 | 120596259 | FRRB - BIG BEND 1102 - B1 PH1.1 | Approved | 08W | [6 empty] | requeting budget for 2021 | 2021-07-15 |  | 153.4 | 237500 | 2021 |  |  |  | 263588.3 | 0 | 263588.3 | 0 | 0 | 2022-01-03 | PEND |  | 2021-07-15 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 13:14 |  |  | 2021 | Order and Notification
100850 | Budget change | 35239522 | 120695185 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-06-01 |  | 594.5 | 3198520 | 2021 |  |  |  | 1643290 | 0 | 1643290 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:59 |  |  | 2021 | Order and Notification
100849 | Budget change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 1647.2 | 6383520 | 2021 |  |  |  | 4093290 | 0 | 4093290 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:58 |  |  | 2021 | Order and Notification
100848 | Budget change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 1062.1 | 7339020 | 2021 |  |  |  | 4828290 | 0 | 4828290 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:58 |  |  | 2021 | Order and Notification
100847 | Budget change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-28 |  | 4409.1 | 8067020 | 2021 |  |  |  | 5388290 | 0 | 5388290 | 0 | 0 | 2022-03-03 | UNSC |  | 2021-07-28 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:57 |  |  | 2021 | Order and Notification
100846 | Budget change | 35240546 | 120723697 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-06-04 |  | 401.7 | 2470520 | 2021 |  |  |  | 1083290 | 0 | 1083290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:56 |  |  | 2021 | Order and Notification
100845 | Budget change | 35240545 | 120723696 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-06-04 |  | 652.9 | 2561702 | 2021 |  |  |  | 1153472.39 | 0 | 1153472.39 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:55 |  |  | 2021 | Order and Notification
100844 | Budget change | 35239937 | 120711267 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-06-04 |  | 1628.5 | 4746246 | 2021 |  |  |  | 2834016.47 | 0 | 2834016.47 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:55 |  |  | 2021 | Order and Notification
100843 | Budget change | 35239523 | 120695189 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-06-01 |  | 973.8 | 3198520 | 2021 |  |  |  | 1643290 | 0 | 1643290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:50 |  |  | 2021 | Order and Notification
100842 | Budget change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-16 |  | 1433.2 | 4335155 | 2021 |  |  |  | 2518289.22 | 0 | 2518289.22 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:49 |  |  | 2021 | Order and Notification
100841 | Budget change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 1103.5 | 6429020 | 2021 |  |  |  | 4128290 | 0 | 4128290 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:47 |  |  | 2021 | Order and Notification
100840 | Budget change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 5336.9 | 9341020 | 2021 |  |  |  | 6368290 | 0 | 6368290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:46 |  |  | 2021 | Order and Notification
100839 | Budget change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 2405 | 7066020 | 2021 |  |  |  | 4618290 | 0 | 4618290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:44 |  |  | 2021 | Order and Notification
100838 | Budget change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [6 empty] | Requesting 2021 MPP budget to align with expected case number | 2021-07-19 |  | 1673 | 7748520 | 2021 |  |  |  | 5143290 | 0 | 5143290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:43 |  |  | 2021 | Order and Notification
100837 | Budget change | 35236995 | 120627597 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 3342.6 | 11024453 | 2021 |  |  |  | 7663381 | 0 | 7663381 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100836 | Budget change | 35239097 | 120685508 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 2382.4 | 6656520 | 2021 |  |  |  | 4303290 | 0 | 4303290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100835 | Budget change | 35236993 | 120627595 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-27 |  | 910.4 | 3881421 | 2021 |  |  |  | 2168690 | 0 | 2168690 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100834 | Budget change | 35239098 | 120685590 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 80 | 8340020 | 2021 |  |  |  | 5598290 | 0 | 5598290 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100833 | Budget change | 35239096 | 120685505 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-09 |  | 1698.8 | 6065020 | 2021 |  |  |  | 3848290 | 0 | 3848290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100832 | Budget change | 35236991 | 120627593 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-06 |  | 2464.7 | 7834694 | 2021 |  |  |  | 5209578 | 0 | 5209578 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:27 |  |  | 2021 | Order and Notification
100831 | Budget change | 35239099 | 120685592 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 1483 | 5064020 | 2021 |  |  |  | 3078290 | 0 | 3078290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:26 |  |  | 2021 | Order and Notification
100830 | Budget change | 35239095 | 120685501 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-09 |  | 2634.3 | 7202520 | 2021 |  |  |  | 4723290 | 0 | 4723290 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:26 |  |  | 2021 | Order and Notification
100829 | Budget change | 35235700 | 120598982 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 2023.7 | 7794107 | 2021 |  |  |  | 5178377 | 0 | 5178377 | 0 | 0 | 2022-05-07 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:26 |  |  | 2021 | Order and Notification
100828 | Budget change | 35235671 | 120594872 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-20 |  | 1773.7 | 4290520 | 2021 |  |  |  | 2483290 | 0 | 2483290 | 0 | 0 | 2022-05-03 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:26 |  |  | 2021 | Order and Notification
100827 | Budget change | 35235669 | 120594870 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | Approved | 08W | [6 empty] | Requesting to have MPP budget align with Expected case | 2021-08-09 |  | 1270.1 | 3927014 | 2021 |  |  |  | 2204458 | 0 | 2204458 | 0 | 0 | 2022-05-03 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 12:26 |  |  | 2021 | Order and Notification
100823 | Budget change | 35232443 | 120528712 | CWSP - DESCHUTES 11049718 PH 2.3 | Approved | 08W | [6 empty] | Business case has been approved and the forecast has been updated. | 2021-08-06 |  | 1292.4 | 1351751 | 2021 |  |  |  | 1351751 |  | 1351751 |  |  | 2021-12-31 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-06-16 17:56 |  |  | 2021-06-15 11:11 |  |  | 2021 | Order and Notification
100643 | Budget change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-09-09 |  | 742.6 | 2743520 | 2021 |  |  |  | 1293290 | 0 | 1293290 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-09-09 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:53 |  |  | 2021 | Order and Notification
100642 | Budget change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-08-17 |  | 1051.6 | 3728491 | 2021 |  |  |  | 2050960 | 0 | 2050960 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:53 |  |  | 2021 | Order and Notification
100641 | Budget change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-06-14 |  | 2886.6 | 6280110 | 2021 |  |  |  | 4013744 | 0 | 4013744 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:52 |  |  | 2021 | Order and Notification
100640 | Budget change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-06-14 |  | 1328.6 | 4778094 | 2021 |  |  |  | 2858347 | 0 | 2858347 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:52 |  |  | 2021 | Order and Notification
100639 | Budget change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-09-03 |  | 932 | 3246777 | 2021 |  |  |  | 1680411 | 0 | 1680411 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-09-03 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:52 |  |  | 2021 | Order and Notification
100638 | Budget change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-07-30 |  | 979.2 | 3378623 | 2021 |  |  |  | 1781831 | 0 | 1781831 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:52 |  |  | 2021 | Order and Notification
100637 | Budget change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-07-30 |  | 909 | 3444978 | 2021 |  |  |  | 1832873 | 0 | 1832873 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:51 |  |  | 2021 | Order and Notification
100636 | Budget change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-07-26 |  | 351.3 | 2470520 | 2021 |  |  |  | 1083290 | 0 | 1083290 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:51 |  |  | 2021 | Order and Notification
100635 | Budget change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-09-22 |  | 487.4 | 2622014 | 2021 |  |  |  | 1199824 | 0 | 1199824 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-09-22 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:51 |  |  | 2021 | Order and Notification
100634 | Budget change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-08-20 |  | 552.9 | 3715565 | 2021 |  |  |  | 2041017 | 0 | 2041017 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:51 |  |  | 2021 | Order and Notification
100633 | Budget change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-07-16 |  | 994.5 | 3535462 | 2021 |  |  |  | 1902476 | 0 | 1902476 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:51 |  |  | 2021 | Order and Notification
100632 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 | 0 | 2051623 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:50 |  |  | 2021 | Order and Notification
100631 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | Requesting MPP budget to align with Expected case figure | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 | 0 | 1581642 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 10:50 |  |  | 2021 | Order and Notification
100621 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | Reqesting Budget for 2021 to align with expected case figure | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 | 0 | 2051623 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 08:54 |  |  | 2021 | Order and Notification
100620 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | Reqesting Budget for 2021 to align with expected case figure | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 | 0 | 1581642 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 08:54 |  |  | 2021 | Order and Notification
100618 | Budget change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | requesting budget for 2021 to align with expected case figure | 2021-08-27 |  | 723.9 | 3159481 | 2021 |  |  |  | 1614125 | 0 | 1614125 | 0 | 0 | 2022-01-01 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-06-14 14:12 |  |  | 2021-06-14 08:44 |  |  | 2021 | Order and Notification
99709 | Add project | 35145004 |  | PSPS CWSP - ROSSMOOR 1106 - CB | Approved | 08W | [6 empty] | WGSC approved on 5/28/21 to proceed with construction. Bring back into workplan | 2021-08-01 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-16 16:06 |  |  | 2021-06-10 14:55 |  |  |  | Not in Work Plan
99708 | Add project | 35145003 |  | PSPS CWSP - MORAGA 1103 - CB | Approved | 08W | [6 empty] | WGSC approved on 5/28/21 to proceed with construction. Bring back into workplan | 2021-08-01 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-16 16:06 |  |  | 2021-06-10 14:54 |  |  |  | Not in Work Plan
99707 | Add project | 35145001 |  | PSPS - CLAYTON 2215 - CB | Approved | 08W | [6 empty] | WGSC approved on 5/28/21 to proceed with construction. Bring back into workplan | 2022-06-01 |  |  |  | 2021 | 2022 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-16 16:06 |  |  | 2021-06-10 14:54 |  |  |  | Not in Work Plan
99599 | Resource change | 35250343 | 121318070 | FRRB - KANAKA 1101CB - K2 SM1 | Approved | 08W | [6 empty] | [REDACTED] - SH | 2021-06-28 |  | 0 | 1 | 2021 |  |  |  | 971117 |  |  |  |  | 2022-05-13 | ESTS |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-06-10 19:30 |  |  | 2021-06-10 13:19 |  |  | 2021 | Order and Notification
99600 | Resource change | 35253174 | 121394703 | FRRB - KANAKA 1101CB - K4 SM2 | Approved | 08W | [6 empty] | [REDACTED] - SH | 2021-08-15 |  | 0 |  | 2021 | [8 empty] | 2022-05-25 | UNSE | [17 empty] | Approved |  |  | 2021-06-10 19:30 |  |  | 2021-06-10 13:19 |  |  | 2021 | Order and Notification
99601 | Resource change | 35253173 | 121394932 | FRRB - KANAKA 1101CB - K4 SM1 | Approved | 08W | [6 empty] | [REDACTED] - SH | 2021-08-15 |  | 0 |  | 2021 | [8 empty] | 2022-05-25 | UNSE | [17 empty] | Approved |  |  | 2021-06-10 19:30 |  |  | 2021-06-10 13:19 |  |  | 2021 | Order and Notification
99598 | Resource change | 35249161 | 120950640 | FRRB - WYANDOTTE 11031974 - W3 SM3 | Approved | 08W | [6 empty] | [REDACTED] - SH | 2021-07-15 |  | 354.6 | 100000 | 2021 |  |  |  | 795454.5455 |  |  |  |  | 2022-05-07 | PEND | [17 empty] | Approved |  |  | 2021-06-10 19:30 |  |  | 2021-06-10 13:19 |  |  | 2021 | Order and Notification
98728 | Budget change | 35235676 | 120598345 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Approved | 08W | [6 empty] | requesting budget to align with expected case figure | 2021-08-03 |  | 80 | 13666223 | 2021 |  |  |  | 9498763 | 0 | 9498763 | 0 | 0 | 2022-05-07 | ESTS |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:43 |  |  | 2021 | Order and Notification
98727 | Budget change | 35235139 | 120582960 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Approved | 08W | [6 empty] | requesting budget to align with expected case figure | 2021-08-03 |  | 80 | 8555764 | 2021 |  |  |  | 5643257 | 0 | 5643257 | 0 | 0 | 2022-03-01 | ESTS |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:36 |  |  | 2021 | Order and Notification
98726 | Budget change | 35225821 | 120424578 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | Approved | 08W | [6 empty] | requesting budget to align with expected case figure | 2021-07-19 |  | 1284.4 | 5417838 | 2021 |  |  |  | 3241252 | 0 | 3241252 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:32 |  |  | 2021 | Order and Notification
98725 | Budget change | 35223343 | 120255838 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | Approved | 08W | [6 empty] | requesting budget to align with expected case figure | 2021-06-21 |  | 1360.3 | 5929383 | 2021 |  |  |  | 4015922 | 0 | 4015922 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-21 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:27 |  |  | 2021 | Order and Notification
98724 | Budget change | 35235702 | 120599072 | FRRB - KANAKA 1101 - K3 PH 3 | Approved | 08W | [6 empty] | requesting budget to allign with expected case figure | 2021-08-13 |  | 80 | 950000 | 2021 |  |  |  | 6050630 | 0 | 6050630 | 0 | 0 | 2022-05-07 | UNSE |  | 2021-08-13 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:21 |  |  | 2021 | Order and Notification
98723 | Budget change | 35236984 | 120627454 | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | Approved | 08W | [6 empty] | Requesting budget to allign with expected case figure | 2021-08-13 |  | 80 | 190000 | 2021 |  |  |  | 7991552 | 0 | 7991552 | 0 | 0 | 2022-05-07 | UNSE |  | 2021-08-13 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:18 |  |  | 2021 | Order and Notification
98722 | Budget change | 35236992 | 120627594 | FRRB - KANAKA 1101 - K1 PH 1.2 | Approved | 08W | [6 empty] | Requesting Budget to allign with expect case figure | 2021-10-19 |  | 80 | 475000 | 2021 |  |  |  | 2988215 | 0 | 2988215 | 0 | 0 | 2022-06-30 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:10 |  |  | 2021 | Order and Notification
98720 | Budget change | 35236985 | 120627455 | FRRB - KANAKA 1101 - K1 PH 1.1 | Approved | 08W | [6 empty] | Requesting Budget to Allign with Expected Case figure | 2021-10-19 |  | 80 | 475000 | 2021 |  |  |  | 6688147 | 0 | 6688147 | 0 | 0 | 2022-05-07 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 12:07 |  |  | 2021 | Order and Notification
97244 | Resource change | 35219590 | 120165232 | CWSP - VACA DIXON 1105965390 | Approved | 08W | [7 empty] | 2021-09-01 |  | 0 | 1 | 2021 | [8 empty] | 2021-12-31 | ADER |  | 2021-09-01 | [15 empty] | Approved |  |  | 2021-06-10 19:30 |  |  | 2021-06-10 10:42 |  |  | 2021 | Order and Notification
97239 | Budget change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W | [6 empty] | PCR to align 2021 MPP budget with 2021 CY EAC | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 |  | 6260070 |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 10:08 |  |  | 2021 | Order and Notification
97236 | Budget change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W | [6 empty] | PCR to align 2021 MPP approved budget with CY EAC 2021 | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 |  | 5746289 |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-10 09:42 |  |  | 2021 | Order and Notification
94680 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Post construction veg work identified | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 435000 |  |  | 433000 |  | 2019-12-27 | FICL | 2021-02-12 | 2020-06-22 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-08 13:15 |  |  | 2021 | Order and Notification
92923 | Add project | 35254648 |  | CWSP - VOLTA 1101CB PH 2.5 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92924 | Add project | 35240168 |  | CWSP - VOLTA 110153118 PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92925 | Add project | 35254649 |  | CWSP - VOLTA 110153118 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92926 | Add project | 35254650 |  | CWSP - VOLTA 110153118 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92927 | Add project | 35254651 |  | CWSP - VOLTA 110153118 PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92928 | Add project | 35254652 |  | CWSP - VOLTA 110153118 PH 1.5 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92929 | Add project | 35254653 |  | CWSP - VOLTA 110153118 PH 1.6 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92930 | Add project | 35254654 |  | CWSP - VOLTA 110153118 PH 1.7 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92931 | Add project | 35254655 |  | CWSP - VOLTA 110153118 PH 1.8 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92907 | Add project | 35240166 |  | CWSP - VOLTA 1101CB PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92908 | Add project | 35254258 |  | CWSP - VOLTA 1101CB PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92909 | Add project | 35254259 |  | CWSP - VOLTA 1101CB PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92910 | Add project | 35254640 |  | CWSP - VOLTA 1101CB PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92911 | Add project | 35254641 |  | CWSP - VOLTA 1101CB PH 1.5 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92912 | Add project | 35254642 |  | CWSP - VOLTA 1101CB PH 1.6 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92913 | Add project | 35254643 |  | CWSP - VOLTA 1101CB PH 1.7 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92914 | Add project | 35254644 |  | CWSP - VOLTA 1101CB PH 1.8 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92915 | Add project | 35240165 |  | CWSP - COARSEGOLD 21046210 PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92916 | Add project | 35249875 |  | CWSP - COARSEGOLD 21046210 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92917 | Add project | 35249876 |  | CWSP - COARSEGOLD 21046210 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92918 | Add project | 35249877 |  | CWSP - COARSEGOLD 21046210 PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92919 | Add project | 35240167 |  | CWSP - VOLTA 1101CB PH 2.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92920 | Add project | 35254645 |  | CWSP - VOLTA 1101CB PH 2.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92921 | Add project | 35254646 |  | CWSP - VOLTA 1101CB PH 2.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
92922 | Add project | 35254647 |  | CWSP - VOLTA 1101CB PH 2.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-10 19:51 |  |  | 2021-06-07 18:28 |  |  |  | Not in Work Plan
90252 | Budget change | 35094389 | 117130852 | CWSP-KONOCTI 1102-LR 532 PH 2 | Approved | 08W | [6 empty] | PCR to align 2021 MPP Budget with 2021 CY EAC | 2022-08-19 |  | 816 | 85000 | 2022 |  |  | 997290.6 | 5220 |  | 5220 |  |  | 2020-11-30 | ESTS |  | 2022-08-19 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-07 11:45 |  |  | 2022 | Order and Notification
90251 | Budget change | 35137596 | 118127757 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | Approved | 08W | [6 empty] | BC approved on 06/02/2021. PCR to align 2021 MPP Budget with 2021 CY EAC | 2021-07-01 |  | 507.7 | 1356094 | 2021 |  |  | 737.5 | 855208 |  | 855208 |  |  | 2020-12-31 | UNSC |  | 2021-07-01 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-07 11:31 |  |  | 2021 | Order and Notification
90250 | Budget change | 35137593 | 118125945 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | Approved | 08W | [6 empty] | BC approved on 06/02/2021. PCR to align 2021 MPP Budget with 2021 CY EAC | 2021-07-01 |  | 801.3 | 1536846 | 2021 |  |  | 1000 | 1023712 |  | 1023712 |  |  | 2020-12-31 | UNSC |  | 2021-07-01 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-07 11:31 |  |  | 2021 | Order and Notification
90249 | Budget change | 35137590 | 118093216 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | Approved | 08W | [6 empty] | BC approved on 06/02/2021. PCR to align 2021 MPP Budget with 2021 CY EAC | 2021-07-05 |  | 369.8 | 1075765 | 2021 |  |  | 534.3 | 608708 |  | 608708 |  |  | 2020-12-31 | UNSC |  | 2021-07-05 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-07 11:30 |  |  | 2021 | Order and Notification
90248 | Budget change | 35094396 | 117130859 | CWSP-KONOCTI 1102-LR 532 PH 9 | Approved | 08W | [6 empty] | PCR to align 2021 MPP budget with 2021 CY EAC | 2022-04-05 |  | 2754.1 | 687082.4 | 2022 |  |  | 11365.3 | 11339 |  | 11339 |  |  | 2020-11-30 | PEND |  | 2022-04-05 | [15 empty] | Approved |  |  | 2021-06-10 19:48 |  |  | 2021-06-07 11:27 |  |  | 2022 | Order and Notification
90143 | Budget change | 35226845 | 120448987 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W | [6 empty] | BC approved with 2021 funding | 2021-07-06 |  | 2256.4 | 1101405.78 | 2021 |  |  |  | 2519287 |  | 2519287 |  |  | 2021-12-31 | UNSC |  | 2021-07-06 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-06-04 09:59 |  |  | 2021 | Order and Notification
89974 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Post Construction Veg work to be completed | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 435000 |  | 435000 |  |  | 2019-12-27 | FICL | 2021-02-12 | 2020-06-22 | [15 empty] | Approved |  |  | 2021-06-04 12:38 |  |  | 2021-06-03 14:14 |  |  | 2021 | Order and Notification
89965 | Budget change | 35226853 | 120449146 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W | [6 empty] | Business Case approved via EDRS 2021-33449. | 2021-07-30 |  | 3342.2 | 5538787 | 2021 |  |  |  | 3709152 |  | 3709152 | 11650 |  | 2021-12-31 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-06-03 12:17 |  |  | 2021 | Order and Notification
89667 | Budget change | 35248770 | 120942639 | FRRB - WYANDOTTE 11031974 - W1 SM2 | Approved | 08W | [6 empty] | Requesting 2021 budget to allign with approved PA | 2021-09-06 |  | 389.2 | 92000 | 2021 |  |  |  | 92000 | 0 | 92000 | 0 | 0 | 2022-05-06 | PEND |  | 2021-09-06 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89666 | Budget change | 35244330 | 120827953 | FRRB - WYANDOTTE 11031974 - W1 SM1 | Approved | 08W | [6 empty] | Requesting 2021 budget to allign with approved PA | 2021-09-06 |  | 317.2 | 98000 | 2021 |  |  |  | 98000 | 0 | 98000 | 0 | 0 | 2022-04-16 | PEND |  | 2021-09-06 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89702 | Resource change | 35234400 | 120564154 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 180000 | 2021 | 2022 |  |  | 424000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89703 | Resource change | 35234401 | 120564155 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 180000 | 2021 | 2022 |  |  | 560000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89704 | Resource change | 35233947 | 120564156 | CWSP - OREGON TRAIL 110335002 PH1.2 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 125000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89705 | Resource change | 35233948 | 120564181 | CWSP - OREGON TRAIL 110335002 PH1.3 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 175000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89706 | Resource change | 35233949 | 120564182 | CWSP - OREGON TRAIL 110335002 PH1.4 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 125000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89707 | Resource change | 35233950 | 120564183 | CWSP - OREGON TRAIL 110335002 PH1.5 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 175000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89708 | Resource change | 35233951 | 120564184 | CWSP - OREGON TRAIL 110335002 PH1.6 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 |  | 2021 | 2022 |  |  | 428000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89676 | Resource change | 35233955 | 120564050 | CWSP - OREGON TRAIL 110335002 PH2.4 | Approved | 08W | [7 empty] | 2021-10-19 |  | 80 | 150000 | 2022 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89677 | Resource change | 35233957 | 120564051 | CWSP - OREGON TRAIL 110335002 PH2.5 | Approved | 08W | [7 empty] | 2021-10-22 |  | 80 | 125000 | 2022 |  |  |  | 125000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-10-22 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89674 | Resource change | 35233952 | 120563958 | CWSP - OREGON TRAIL 110335002 PH2.2 | Approved | 08W | [7 empty] | 2021-11-25 |  | 80 | 100000 | 2021 |  |  |  | 4104000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-25 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89675 | Resource change | 35233953 | 120563959 | CWSP - OREGON TRAIL 110335002 PH2.3 | Approved | 08W | [7 empty] | 2021-11-24 |  | 80 | 150000 | 2022 |  |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-24 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89678 | Resource change | 35233959 | 120564052 | CWSP - OREGON TRAIL 110335002 PH2.6 | Approved | 08W | [7 empty] | 2021-11-12 |  | 80 | 75000 | 2021 |  |  |  | 665000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-12 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89679 | Resource change | 35234381 | 120564055 | CWSP - OREGON TRAIL 110335002 PH2.7 | Approved | 08W | [7 empty] | 2021-11-01 |  | 80 | 100000 | 2021 |  |  |  | 2945000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-01 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89680 | Resource change | 35234382 | 120564057 | CWSP - OREGON TRAIL 110335002 PH2.8 | Approved | 08W | [7 empty] | 2021-10-29 |  | 80 | 100000 | 2021 |  |  |  | 3021000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-10-29 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89681 | Resource change | 35233954 | 120564059 | CWSP - OREGON TRAIL 110335002 PH3.2 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 400000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89682 | Resource change | 35233956 | 120564070 | CWSP - OREGON TRAIL 110335002 PH3.3 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 475000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89683 | Resource change | 35233958 | 120564071 | CWSP - OREGON TRAIL 110335002 PH3.4 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 400000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89684 | Resource change | 35234380 | 120564073 | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 150000 | 2021 | 2022 |  |  | 3500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89685 | Resource change | 35234383 | 120564074 | CWSP - OREGON TRAIL 110335002 PH3.6 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89688 | Resource change | 35234386 | 120564078 | CWSP - OREGON TRAIL 110335002 PH3.9 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 100000 | 2021 |  |  |  | 1634000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89689 | Resource change | 35234387 | 120564102 | CWSP - OREGON TRAIL 110335002 PH4.2 | Approved | 08W | [7 empty] | 2021-10-08 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89690 | Resource change | 35234388 | 120564104 | CWSP - OREGON TRAIL 110335002 PH4.3 | Approved | 08W | [7 empty] | 2021-10-07 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-07 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89691 | Resource change | 35234389 | 120564107 | CWSP - OREGON TRAIL 110335002 PH4.4 | Approved | 08W | [7 empty] | 2021-10-07 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-07 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89692 | Resource change | 35234390 | 120564108 | CWSP - OREGON TRAIL 110335002 PH4.5 | Approved | 08W | [7 empty] | 2021-10-06 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-06 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89693 | Resource change | 35234391 | 120564120 | CWSP - OREGON TRAIL 110335002 PH4.6 | Approved | 08W | [7 empty] | 2021-10-06 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-06 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89694 | Resource change | 35234392 | 120564121 | CWSP - OREGON TRAIL 110335002 PH4.7 | Approved | 08W | [7 empty] | 2021-09-29 |  | 80 | 125000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89695 | Resource change | 35234393 | 120564122 | CWSP - OREGON TRAIL 110335002 PH5.2 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158334 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89686 | Resource change | 35234384 | 120564075 | CWSP - OREGON TRAIL 110335002 PH3.7 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 150000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89687 | Resource change | 35234385 | 120564076 | CWSP - OREGON TRAIL 110335002 PH3.8 | Approved | 08W | [7 empty] | 2021-12-31 |  | 0 | 100000 | 2021 |  |  |  | 1273000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89696 | Resource change | 35234394 | 120564123 | CWSP - OREGON TRAIL 110335002 PH5.3 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158334 | 2021 | 2022 |  |  | 364000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89697 | Resource change | 35234395 | 120564126 | CWSP - OREGON TRAIL 110335002 PH5.4 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158334 | 2021 | 2022 |  |  | 536000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89698 | Resource change | 35234396 | 120564127 | CWSP - OREGON TRAIL 110335002 PH5.5 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158334 | 2021 | 2022 |  |  | 404000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89699 | Resource change | 35234397 | 120564129 | CWSP - OREGON TRAIL 110335002 PH5.6 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158334 | 2021 | 2022 |  |  | 352000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89700 | Resource change | 35234398 | 120564152 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 180000 | 2021 | 2022 |  |  | 660000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89701 | Resource change | 35234399 | 120564153 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 230000 | 2021 | 2022 |  |  | 382000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89669 | Resource change | 35219289 | 120142359 | CWSP - OREGON TRAIL 110335002 PH1.1 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 225000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89670 | Resource change | 35225826 | 120426402 | CWSP - OREGON TRAIL 110335002 PH2.1 | Approved | 08W | [7 empty] | 2021-12-22 |  | 80 | 100000 | 2021 |  |  |  | 4825999.3 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2021 | Order and Notification
89671 | Resource change | 35225827 | 120426404 | CWSP - OREGON TRAIL 110335002 PH3.1 | Approved | 08W | [7 empty] | 2022-05-02 |  | 0 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89672 | Resource change | 35225828 | 120426405 | CWSP - OREGON TRAIL 110335002 PH4.1 | Approved | 08W | [7 empty] | 2021-09-21 |  | 80 | 200000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-09-21 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89673 | Resource change | 35225829 | 120426406 | CWSP - OREGON TRAIL 110335002 PH5.1 | Approved | 08W | [7 empty] | 2021-12-08 |  | 80 | 158330 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:16 |  |  | 2022 | Order and Notification
89668 | Resource change | 35219287 | 120142356 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Approved | 08W | [7 empty] | 2022-06-01 |  | 0 | 180000 | 2021 | 2022 |  |  | 540000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-06-02 15:15 |  |  | 2022 | Order and Notification
89659 | Add project | 35253174 |  | FRRB - KANAKA 1101CB - K4 SM2 | Approved | 08W | [6 empty] | Adding this project as part of NCFR | 2021-08-15 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-04 12:40 |  |  | 2021-06-02 14:20 |  |  |  | Not in Work Plan
89658 | Add project | 35253173 |  | FRRB - KANAKA 1101CB - K4 SM1 | Approved | 08W | [6 empty] | Adding this project as part of NCFR | 2021-08-15 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-06-04 12:40 |  |  | 2021-06-02 14:20 |  |  |  | Not in Work Plan
89618 | Budget change | 35226241 | 120431331 | CWSP - MARIPOSA 210197142 PH 2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-08-25 |  | 1742.6 | 485124.83 | 2021 |  |  |  | 1218823 |  | 1218823 |  |  | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-06-01 16:26 |  |  | 2021 | Order and Notification
89467 | Resource change | 35226799 | 120450944 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [7 empty] | 2022-07-11 |  | 203 | 71683.95 | 2021 | 2021 |  |  | 371000 |  |  |  |  | 2021-12-31 | PEND |  | 2022-07-11 | [15 empty] | Approved |  |  | 2021-06-04 12:23 |  |  | 2021-05-28 16:45 |  |  | 2021 | Order and Notification
89222 | Budget change | 35227263 | 120457435 | CWSP - MARIPOSA 2102CB PH 2 | Approved | 08W | [6 empty] | 08W System Hardening Project | 2021-07-20 |  | 2088.9 | 1012126.18 | 2021 |  |  |  | 1670921 |  | 1670921 |  |  | 2021-12-31 | CONS |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-06-04 12:37 |  |  | 2021-05-28 08:55 |  |  | 2021 | Order and Notification
88926 | Budget change | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv | [5 empty] | 08W Fire Hardening Project | 2022-01-04 |  | 2163 | 2768676 | 2021 | 2022 |  | 4086056.3 | 44404 |  | 44404 | 1845729 |  | 2021-07-12 | PEND |  | 2022-01-04 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-27 13:57 |  |  | 2022 | Order and Notification
88922 | Budget change | 35217267 | 120047657 | SH - MARIPOSA 2102 LR 241564 | Approved | 08W | [6 empty] | 08W System Hardening Project | 2021-07-14 |  | 1268.6 | 691633.47 | 2021 |  |  |  | 1220483 |  | 1220483 |  |  | 2021-12-31 | CONS |  | 2021-07-14 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-27 13:48 |  |  | 2021 | Order and Notification
88878 | Pull-in Project from Future Year | 35226799 | 120450944 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [6 empty] | Project is in PEND - Need to Complete in 2021. Move project and budget back into 2021 work plan | 2022-07-11 | 2021-08-01 | 203 | 71683.95 | 2021 | 2021 | 2021 |  | 371000 |  | 371000 |  |  | 2021-12-31 | PEND |  | 2022-07-11 | [9 empty] | Approved | Pull in project from future year approved |  | Approved |  |  | Approved |  |  | 2021-06-04 12:29 |  |  | 2021-05-27 08:18 |  |  | 2021 | Order and Notification
88664 | Budget change | 35226854 | 120449147 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W | [6 empty] | EDRS 2021-33450 business case approved. | 2021-07-01 |  | 1852.6 | 4710436 | 2021 |  |  |  | 3199346 |  | 3199346 | 37709 |  | 2021-12-31 | CONS |  | 2021-07-01 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-26 15:06 |  |  | 2021 | Order and Notification
88629 | Add project | 35240164 |  | CWSP - COARSEGOLD 2104570682 PH 1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88630 | Add project | 35240163 |  | CWSP - COARSEGOLD 21045310 PH 3.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88631 | Add project | 35249873 |  | CWSP - COARSEGOLD 21045310 PH 3.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88632 | Add project | 35249874 |  | CWSP - COARSEGOLD 21045310 PH 3.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88633 | Add project | 35240162 |  | CWSP - COARSEGOLD 21045310 PH 2.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88634 | Add project | 35250737 |  | CWSP - COARSEGOLD 21045310 PH 2.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88635 | Add project | 35250738 |  | CWSP - COARSEGOLD 21045310 PH 2.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88636 | Add project | 35240160 |  | CWSP - COARSEGOLD 21045310 PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88637 | Add project | 35249871 |  | CWSP - COARSEGOLD 21045310 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88638 | Add project | 35249872 |  | CWSP - COARSEGOLD 21045310 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88639 | Add project | 35219269 |  | CWSP - VACA DIXON 110540092 PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88640 | Add project | 35237258 |  | CWSP - VACA DIXON 110540092 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88641 | Add project | 35237259 |  | CWSP - VACA DIXON 110540092 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88642 | Add project | 35237360 |  | CWSP - VACA DIXON 110540092 PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88643 | Add project | 35237361 |  | CWSP - VACA DIXON 110540092 PH 1.5 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88644 | Add project | 35237364 |  | CWSP - VACA DIXON 110540092 PH 1.6 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88645 | Add project | 35237365 |  | CWSP - VACA DIXON 110540092 PH 1.7 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88646 | Add project | 35237366 |  | CWSP - VACA DIXON 110540092 PH 1.8 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88647 | Add project | 35237368 |  | CWSP - VACA DIXON 110540092 PH 1.9 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88648 | Add project | 35237369 |  | CWSP - VACA DIXON 110540092 PH 1.10 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88649 | Add project | 35237370 |  | CWSP - VACA DIXON 110540092 PH 1.11 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88650 | Add project | 35237371 |  | CWSP - VACA DIXON 110540092 PH 1.12 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88651 | Add project | 35243452 |  | CWSP - COARSEGOLD 210410030 - PH1.1 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88652 | Add project | 35249996 |  | CWSP - COARSEGOLD 210410030 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88653 | Add project | 35249997 |  | CWSP - COARSEGOLD 210410030 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88654 | Add project | 35249998 |  | CWSP - COARSEGOLD 210410030 PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88655 | Add project | 35249999 |  | CWSP - COARSEGOLD 210410030 PH 1.5 | Approved | 08W | [6 empty] | Project recently approved by the WFGC to be added to the workplan. Workplan year is a placeholder until the project managers replace it when a schedule is completed | 2022-08-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved | Changed to appropriate year 2022 |  | Approved |  |  | 2021-06-04 13:20 |  |  | 2021-05-26 08:37 |  |  |  | Not in Work Plan
88585 | Budget change | 35094395 | 117130858 | CWSP-KONOCTI 1102-LR 532 PH 8 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP budget with 2021 CY EAC | 2022-10-19 |  | 131 | 75000 | 2022 |  |  | 3948.6 | 7364 |  | 7364 |  |  | 2020-11-30 | ESTS |  | 2022-10-19 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-25 16:09 |  |  | 2022 | Order and Notification
88584 | Budget change | 35094391 | 117130854 | CWSP-KONOCTI 1102-LR 532 PH 4 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP budget with 2021 CY EAC | 2022-04-04 |  | 1696.6 | 45454 | 2022 |  |  | 6426.8 | 2756 |  | 2756 |  |  | 2020-11-30 | PEND |  | 2022-04-04 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-25 16:09 |  |  | 2022 | Order and Notification
88583 | Budget change | 35094389 | 117130852 | CWSP-KONOCTI 1102-LR 532 PH 2 | Approved | 08W | [6 empty] | PCR to align the 2021 MPP budget with 2021 CY EAC | 2022-08-19 |  | 816 | 85000 | 2022 |  |  | 997290.6 | 5220 |  | 3913 |  |  | 2020-11-30 | ESTS |  | 2022-08-19 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-25 16:08 |  |  | 2022 | Order and Notification
88581 | Budget change | 35226846 | 120448989 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W | [6 empty] | Business case approved via EDRS 2021-28356 | 2021-06-07 |  | 1531.1 | 3178496 | 2021 |  |  |  | 2090271.93 |  | 2090271.93 |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-25 15:21 |  |  | 2021 | Order and Notification
88467 | Budget change | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [6 empty] | PCR to align MPP Budget 2021 with CY EAC 2021 | 2021-10-01 |  | 428 | 1115282 | 2021 |  |  | 150000 | 755085 |  | 755085 |  |  | 2018-12-28 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-21 13:20 |  |  | 2021 | Order and Notification
88460 | Resource change | 35219267 | 120142033 | CWSP - MARIPOSA 2102440236 PH1.1 | Approved | 08W | [7 empty] | 2021-10-19 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-21 10:27 |  |  | 2021 | Order and Notification
88461 | Resource change | 35219587 | 120165147 | CWSP - MARIPOSA 2102440236 PH1.2 | Approved | 08W | [7 empty] | 2021-10-13 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-10-13 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-21 10:27 |  |  | 2021 | Order and Notification
88462 | Resource change | 35219588 | 120165148 | CWSP - MARIPOSA 2102440236 PH1.3 | Approved | 08W | [7 empty] | 2021-11-02 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-11-02 | [15 empty] | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-21 10:27 |  |  | 2021 | Order and Notification
88436 | Resource change | 35248770 | 120942639 | FRRB - WYANDOTTE 11031974 - W1 SM2 | Approved | 08W | [7 empty] | 2021-09-06 |  | 389.2 | 92000 | 2021 |  |  |  | 92000 |  |  |  |  | 2022-05-06 | PEND |  | 2021-09-06 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:34 |  |  | 2021 | Order and Notification
88435 | Resource change | 35244574 | 120830887 | FRRB - WYANDOTTE 11031974 - W3 SM2 | Approved | 08W | [7 empty] | 2021-07-07 |  | 80 | 100000 | 2021 |  |  |  | 232007.5758 |  |  |  |  | 2022-04-16 | UNSE |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:34 |  |  | 2021 | Order and Notification
88434 | Resource change | 35244573 | 120830881 | FRRB - WYANDOTTE 11031974 - W3 SM1 | Approved | 08W | [7 empty] | 2021-07-07 |  | 80 | 100000 | 2021 |  |  |  | 464015.1515 |  |  |  |  | 2022-04-16 | UNSE |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:34 |  |  | 2021 | Order and Notification
88433 | Resource change | 35244330 | 120827953 | FRRB - WYANDOTTE 11031974 - W1 SM1 | Approved | 08W | [7 empty] | 2021-09-06 |  | 317.2 | 98000 | 2021 |  |  |  | 98000 |  |  |  |  | 2022-04-16 | PEND |  | 2021-09-06 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:33 |  |  | 2021 | Order and Notification
88432 | Resource change | 35237021 | 120627369 | FRRB - WYANDOTTE 1103 W7 PH7.4 FUTURE SM | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 237500 | 2021 | [8 empty] | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:33 |  |  | 2021 | Order and Notification
88431 | Resource change | 35236997 | 120627598 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 237500 | 2021 | [8 empty] | 2022-06-30 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:32 |  |  | 2021 | Order and Notification
88430 | Resource change | 35236983 | 120627452 | FRRB - BIG BEND 1102 - B5 PH5.3 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 4431245 | 2021 |  |  |  | 2451150 |  |  |  |  | 2022-05-07 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:32 |  |  | 2021 | Order and Notification
88429 | Resource change | 35236982 | 120627450 | FRRB - KANAKA 1101 - K6 PH6 | Approved | 08W | [7 empty] | 2021-09-01 |  | 80 | 950000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:31 |  |  | 2021 | Order and Notification
88428 | Resource change | 35235678 | 120598535 | FRRB - BIG BEND 1102 - B5 PH5.1 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 4340396 | 2021 |  |  |  | 2381301 |  |  |  |  | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:31 |  |  | 2021 | Order and Notification
88427 | Resource change | 35229043 | 120493696 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 | Approved | 08W | [7 empty] | 2021-07-01 |  | 0 |  | 2021 | [8 empty] | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:30 |  |  | 2021 | Order and Notification
88426 | Resource change | 35245152 | 120850488 | FRRB - KANAKA 1101 - K4 PH 4.17 | Approved | 08W | [7 empty] | 2021-08-03 |  | 3 | 2871418 | 2021 |  |  |  | 1573923 |  |  |  |  | 2022-04-20 | ADER |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:30 |  |  | 2021 | Order and Notification
88425 | Resource change | 35245151 | 120850487 | FRRB - KANAKA 1101 - K4 PH 4.16 | Approved | 08W | [7 empty] | 2021-07-13 |  | 77.2 | 1779097 | 2021 |  |  |  | 733676 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-13 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:30 |  |  | 2021 | Order and Notification
88424 | Resource change | 35245150 | 120850486 | FRRB - KANAKA 1101 - K4 PH 4.15 | Approved | 08W | [7 empty] | 2021-07-20 |  | 92.1 | 1776758 | 2021 |  |  |  | 731877 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:29 |  |  | 2021 | Order and Notification
88423 | Resource change | 35245149 | 120850485 | FRRB - KANAKA 1101 - K4 PH 4.14 | Approved | 08W | [7 empty] | 2021-08-19 |  | 111.7 | 2127143 | 2021 |  |  |  | 1001404 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-19 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:29 |  |  | 2021 | Order and Notification
88422 | Resource change | 35245148 | 120850482 | FRRB - KANAKA 1101 - K4 PH 4.13 | Approved | 08W | [7 empty] | 2021-07-20 |  | 176.9 | 1979318 | 2021 |  |  |  | 887692 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:28 |  |  | 2021 | Order and Notification
88421 | Resource change | 35245147 | 120850159 | FRRB - KANAKA 1101 - K4 PH 4.12 | Approved | 08W | [7 empty] | 2021-08-12 |  | 245.3 | 2433087 | 2021 |  |  |  | 1236745 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:28 |  |  | 2021 | Order and Notification
88420 | Resource change | 35245146 | 120850158 | FRRB - KANAKA 1101 - K4 PH 4.11 | Approved | 08W | [7 empty] | 2021-08-17 |  | 85 | 1799681 | 2021 |  |  |  | 749510 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:28 |  |  | 2021 | Order and Notification
88419 | Resource change | 35245145 | 120850157 | FRRB - KANAKA 1101 - K4 PH 4.10 | Approved | 08W | [7 empty] | 2021-07-09 |  | 76.6 | 1697232 | 2021 |  |  |  | 670703 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:21 |  |  | 2021 | Order and Notification
88418 | Resource change | 35245144 | 120850156 | FRRB - KANAKA 1101 - K4 PH 4.9 | Approved | 08W | [7 empty] | 2021-08-03 |  | 123.4 | 2078491 | 2021 |  |  |  | 963979 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:21 |  |  | 2021 | Order and Notification
88417 | Resource change | 35245143 | 120850155 | FRRB - KANAKA 1101 - K4 PH 4.8 | Approved | 08W | [7 empty] | 2021-06-29 |  | 188.9 | 2067264 | 2021 |  |  |  | 955343 |  |  |  |  | 2022-04-20 | PEND |  | 2021-06-29 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:20 |  |  | 2021 | Order and Notification
88416 | Resource change | 35245142 | 120850154 | FRRB - KANAKA 1101 - K4 PH 4.7 | Approved | 08W | [7 empty] | 2021-07-09 |  | 52.3 | 1585427 | 2021 |  |  |  | 584699 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:20 |  |  | 2021 | Order and Notification
88415 | Resource change | 35245141 | 120850151 | FRRB - KANAKA 1101 - K4 PH 4.6 | Approved | 08W | [7 empty] | 2021-07-23 |  | 58.6 | 1561101 | 2021 |  |  |  | 565987 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-23 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:20 |  |  | 2021 | Order and Notification
88414 | Resource change | 35245140 | 120850150 | FRRB - KANAKA 1101 - K4 PH 4.5 | Approved | 08W | [7 empty] | 2021-08-05 |  | 277.1 | 2115915 | 2021 |  |  |  | 992767 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-05 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:19 |  |  | 2021 | Order and Notification
88413 | Resource change | 35244699 | 120849798 | FRRB - KANAKA 1101 - K4 PH 4.4 | Approved | 08W | [7 empty] | 2021-08-03 |  | 38.4 | 1606478 | 2021 |  |  |  | 600892 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:19 |  |  | 2021 | Order and Notification
88412 | Resource change | 35244698 | 120849797 | FRRB - KANAKA 1101 - K4 PH 4.3 | Approved | 08W | [7 empty] | 2021-08-02 |  | 62.5 | 1693957 | 2021 |  |  |  | 668184 |  |  |  |  | 2022-04-20 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:19 |  |  | 2021 | Order and Notification
88411 | Resource change | 35244697 | 120849796 | FRRB - KANAKA 1101 - K4 PH 4.2 | Approved | 08W | [7 empty] | 2021-07-30 |  | 77 | 1762257 | 2021 |  |  |  | 720722 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:17 |  |  | 2021 | Order and Notification
88410 | Resource change | 35244696 | 120849795 | FRRB - KANAKA 1101 - K4 PH 4.1 | Approved | 08W | [7 empty] | 2021-07-12 |  | 223.5 | 2190296 | 2021 |  |  |  | 1049983 |  |  |  |  | 2022-04-20 | PEND |  | 2021-07-12 | [15 empty] | Approved |  |  | 2021-05-20 21:41 |  |  | 2021-05-20 17:17 |  |  | 2021 | Order and Notification
88330 | Resource change | 35226872 | 120449236 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Approved | 08W | [7 empty] | 2022-11-01 |  | 403.7 | 159527.53 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:29 |  |  | 2021 | Order and Notification
88329 | Resource change | 35226871 | 120449235 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Approved | 08W | [7 empty] | 2022-11-01 |  | 0.5 | 59835.3 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:28 |  |  | 2021 | Order and Notification
88328 | Resource change | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [7 empty] | 2021-11-05 |  | 433.2 | 204489.16 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | PEND |  | 2021-11-05 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:28 |  |  | 2022 | Order and Notification
88327 | Resource change | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:28 |  |  | 2022 | Order and Notification
88326 | Resource change | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:27 |  |  | 2022 | Order and Notification
88325 | Resource change | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:27 |  |  | 2022 | Order and Notification
88324 | Resource change | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [7 empty] | 2021-11-11 |  | 648.8 | 338825.78 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | PEND |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 18:27 |  |  | 2022 | Order and Notification
88317 | Resource change | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan | [6 empty] | 2020-07-29 |  | 4154.9 | 4232824 | 2020 | 2022 |  | 1150000 | 1750000 |  |  |  |  | 2019-12-06 | CONS |  | 2020-07-29 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 15:31 |  |  | 2022 | Order and Notification
88305 | Resource change | 35223037 | 120242694 | PSPS - OAKHURST 1101 - OAKHURST | Approved | 08W | [7 empty] | 2021-08-11 |  | 366 | 124376.18 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-11 | [15 empty] | Approved |  |  | 2021-05-20 14:12 |  |  | 2021-05-19 15:28 |  |  | 2021 | Order and Notification
88049 | Add project | 35250343 |  | FRRB - KANAKA 1101CB - K2 SM1 | Approved | 08W | [6 empty] | Adding this project to WP as part of NCFR | 2021-06-28 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-20 13:48 |  |  | 2021-05-19 13:58 |  |  |  | Not in Work Plan
88047 | Budget change | 35219542 | 120135655 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Approved | 08W | [6 empty] | EDRS 2021-01718 approved. | 2022-11-01 |  | 0 | 500000 | 2021 | 2022 |  |  | 105000 |  | 105000 |  |  | 2021-12-31 | ESTS |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-06-21 14:18 |  |  | 2021-05-19 12:11 |  |  | 2022 | Order and Notification
88031 | Add project | 35249161 |  | FRRB - WYANDOTTE 11031974 - W3 SM3 | Approved | 08W | [6 empty] | adding this project as part of NFCR | 2021-07-15 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-20 13:48 |  |  | 2021-05-18 15:50 |  |  |  | Not in Work Plan
87989 | Budget change | 35231609 | 120504096 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W | [6 empty] | Adjust to reflect forecast. | 2021-06-14 |  | 2057.5 | 3699056 | 2021 |  |  |  | 2505000 |  | 2505000 |  |  | 2021-12-31 | CONS |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 14:07 |  |  | 2021 | Order and Notification
87988 | Budget change | 35231607 | 120504093 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W | [6 empty] | Adjust to reflect forecast. | 2021-06-22 |  | 1226.4 | 3032237 | 2021 |  |  |  | 1974000 |  | 1974000 |  |  | 2021-12-31 | UNSC |  | 2021-06-22 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 14:06 |  |  | 2021 | Order and Notification
87987 | Budget change | 35226847 | 120449140 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W | [6 empty] | EDRS 2021-30912 business case approved and applied to forecast. | 2021-06-07 |  | 1439.4 | 3048485 | 2021 |  |  |  | 2124000 |  | 2124000 |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 14:04 |  |  | 2021 | Order and Notification
87915 | Budget change | 35219543 | 120135657 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-01-13 |  | 80 | 500000 | 2021 | 2022 |  |  | 177000 |  | 177000 |  |  | 2021-12-31 | ESTS |  | 2022-01-13 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 12:19 |  |  | 2022 | Order and Notification
87912 | Budget change | 35233996 | 120563933 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-09-13 |  | 0 | 315000 | 2021 | 2022 |  |  | 255000 |  | 255000 |  |  | 2021-12-31 | UNSE |  | 2022-09-13 | [15 empty] | Approved |  |  | 2021-05-20 14:01 |  |  | 2021-05-18 12:18 |  |  | 2022 | Order and Notification
87911 | Budget change | 35233995 | 120563909 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-09-13 |  | 0 | 315000 | 2021 | 2022 |  |  | 219000 |  | 219000 |  |  | 2021-12-31 | UNSE |  | 2022-09-13 | [15 empty] | Approved |  |  | 2021-05-20 14:01 |  |  | 2021-05-18 12:17 |  |  | 2022 | Order and Notification
87913 | Budget change | 35224377 | 120360607 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-10-26 |  | 0 | 320000 | 2021 | 2022 |  |  | 179000 |  | 179000 |  |  | 2021-12-31 | UNSE |  | 2022-10-26 | [15 empty] | Approved |  |  | 2021-05-20 14:01 |  |  | 2021-05-18 12:09 |  |  | 2022 | Order and Notification
87910 | Budget change | 35223032 | 120242546 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-04-06 |  | 83 | 500000 | 2021 | 2022 |  |  | 136000 |  | 136000 |  |  | 2021-12-31 | ESTS |  | 2022-04-06 | [15 empty] | Approved |  |  | 2021-06-21 14:17 |  |  | 2021-05-18 12:07 |  |  | 2022 | Order and Notification
87909 | Budget change | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2021-12-07 |  | 80 | 500000 | 2021 | 2022 |  |  | 120000 |  | 120000 |  |  | 2021-12-31 | ESTS |  | 2021-12-07 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 12:06 |  |  | 2022 | Order and Notification
87905 | Budget change | 35116383 | 117604600 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Reduced contract cost | 2021-03-08 |  | 1953 | 3758449 | 2020 | 2021 |  | 1077436 | 850000 |  | 850000 |  |  | 2021-06-30 | CONS |  | 2021-03-08 | [15 empty] | Approved |  |  | 2021-05-20 13:51 |  |  | 2021-05-18 12:06 |  |  | 2021 | Order and Notification
87908 | Budget change | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W | [6 empty] | Additional hours required for estimating. | 2022-04-07 |  | 131.1 | 309269 | 2021 | 2022 |  | 22.4 | 402000 |  | 402000 |  |  | 2020-12-31 | ESTS |  | 2022-04-07 | [15 empty] | Approved |  |  | 2021-05-20 14:01 |  |  | 2021-05-18 12:05 |  |  | 2022 | Order and Notification
87914 | Budget change | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Adjust to reflect 2021 forecast. | 2022-09-01 |  | 2438.1 | 1313564.84 | 2021 | 2022 |  |  | 153000 |  | 153000 |  |  | 2021-12-31 | PEND |  | 2022-09-01 | [15 empty] | Approved |  |  | 2021-06-21 14:16 |  |  | 2021-05-18 12:05 |  |  | 2022 | Order and Notification
87907 | Budget change | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W | [6 empty] | Additional hours required for estimating. | 2022-07-11 |  | 111.1 | 451282 | 2021 | 2022 |  | 365.3 | 231000 |  | 231000 |  |  | 2020-12-31 | ESTS |  | 2022-07-11 | [15 empty] | Approved |  |  | 2021-05-20 14:01 |  |  | 2021-05-18 11:42 |  |  | 2022 | Order and Notification
87374 | Resource change | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [7 empty] | 2022-01-05 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [15 empty] | Approved |  |  | 2021-05-14 18:34 |  |  | 2021-05-13 17:23 |  |  | 2022 | Order and Notification
87369 | Resource change | 35227870 | 120462116 | CWSP - VACAVILLE 11046542 - PH 2.2 | Approved | 08W | [7 empty] | 2021-12-09 |  | 4000.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-09 | [15 empty] | Approved |  |  | 2021-05-14 18:34 |  |  | 2021-05-13 16:47 |  |  | 2022 | Order and Notification
87370 | Resource change | 35227656 | 120462117 | CWSP - VACAVILLE 11046542 - PH 2.3 | Approved | 08W | [7 empty] | 2021-12-09 |  | 2200.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-12-09 | [15 empty] | Approved |  |  | 2021-05-14 18:34 |  |  | 2021-05-13 16:47 |  |  | 2021 | Order and Notification
87371 | Resource change | 35227658 | 120462182 | CWSP - VACAVILLE 11046542 - PH 2.5 | Approved | 08W | [7 empty] | 2021-12-23 |  | 1000.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-23 | [15 empty] | Approved |  |  | 2021-05-14 18:34 |  |  | 2021-05-13 16:47 |  |  | 2022 | Order and Notification
87368 | Resource change | 35219276 | 120142212 | CWSP - VACAVILLE 11046542 PH 1.1 | Approved | 08W | [7 empty] | 2022-07-01 |  | 7040 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-07-01 | [15 empty] | Approved |  |  | 2021-05-14 18:34 |  |  | 2021-05-13 16:47 |  |  | 2022 | Order and Notification
86396 | Resource change | 35227652 | 120462111 | CWSP - VACAVILLE 11046542 PH 1.3 | Approved | 08W | [7 empty] | 2021-10-13 |  | 1080 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-13 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 13:56 |  |  | 2021 | Order and Notification
86397 | Resource change | 35227653 | 120462112 | CWSP - VACAVILLE 11046542 PH 1.4 | Approved | 08W | [7 empty] | 2021-10-15 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-15 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 13:56 |  |  | 2021 | Order and Notification
86395 | Resource change | 35227651 | 120462109 | CWSP - VACAVILLE 11046542 PH 1.2 | Approved | 08W | [7 empty] | 2021-09-27 |  | 80 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-27 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 13:56 |  |  | 2021 | Order and Notification
86246 | Resource change | 35227657 | 120462180 | CWSP - VACAVILLE 11046542 - PH 2.4 | Approved | 08W | [7 empty] | 2021-08-03 |  | 1320 | 257767.11 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2021 | Order and Notification
86247 | Resource change | 35227659 | 120462184 | CWSP - VACAVILLE 11046542 - PH 2.6 | Approved | 08W | [7 empty] | 2021-08-17 |  | 928.8 | 216928.1 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2021 | Order and Notification
86236 | Resource change | 35231623 | 120504160 | CWSP - HIGHLANDS 1102628 PH 1.5 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86237 | Resource change | 35231624 | 120504163 | CWSP - HIGHLANDS 1102628 PH 1.6 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86233 | Resource change | 35231620 | 120504137 | CWSP - HIGHLANDS 1102628 PH 1.2 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86234 | Resource change | 35231621 | 120504138 | CWSP - HIGHLANDS 1102628 PH 1.3 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86235 | Resource change | 35231622 | 120504139 | CWSP - HIGHLANDS 1102628 PH 1.4 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86238 | Resource change | 35231625 | 120504164 | CWSP - HIGHLANDS 1102628 PH 1.7 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86239 | Resource change | 35231626 | 120504165 | CWSP - HIGHLANDS 1102628 PH 1.8 | Approved | 08W | [7 empty] | 2021-08-25 |  | 407.2 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86240 | Resource change | 35231627 | 120504167 | CWSP - HIGHLANDS 1102628 PH 1.9 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86241 | Resource change | 35231628 | 120504170 | CWSP - HIGHLANDS 1102628 PH 1.10 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86242 | Resource change | 35231629 | 120504175 | CWSP - HIGHLANDS 1102628 PH 1.11 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86243 | Resource change | 35231630 | 120504176 | CWSP - HIGHLANDS 1102628 PH 1.12 | Approved | 08W | [7 empty] | 2021-09-20 |  | 400.6 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-09-20 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86244 | Resource change | 35231631 | 120504177 | CWSP - HIGHLANDS 1102628 PH 1.13 | Approved | 08W | [7 empty] | 2022-01-19 |  | 80 | 73077 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2022 | Order and Notification
86245 | Resource change | 35224378 | 120406213 | CWSP - VACAVILLE 11046542 - PH 2.1 | Approved | 08W | [7 empty] | 2021-09-15 |  | 5781 | 1015064.91 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-15 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:40 |  |  | 2021 | Order and Notification
86232 | Resource change | 35219099 | 120141849 | CWSP - HIGHLANDS 1102628 PH 1.1 | Approved | 08W | [7 empty] | 2021-11-24 |  | 80 | 73076 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | [15 empty] | Approved |  |  | 2021-05-13 16:50 |  |  | 2021-05-13 09:39 |  |  | 2022 | Order and Notification
86201 | Budget change | 31361965 | 113751296 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [6 empty] | PCR to return unused $ back to the program | 2021-03-16 |  | 660.1 | 1245293 | 2021 |  |  | 287153 | 273723 | 287153 | 273723 |  |  | 2019-12-27 | FICL | 2021-04-24 | 2021-03-16 | [15 empty] | Approved |  |  | 2021-05-13 16:31 |  |  | 2021-05-12 16:24 |  |  | 2021 | Order and Notification
86202 | Budget change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Approved | 08W | [6 empty] | PCR to return unused $ back to the program | 2021-02-08 |  | 2388.1 | 6518166 | 2021 |  |  |  | 3628388 |  | 3628388 |  |  | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | [15 empty] | Approved |  |  | 2021-05-13 16:31 |  |  | 2021-05-12 16:21 |  |  | 2021 | Order and Notification
86200 | Budget change | 35094397 | 117131100 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Approved | 08W | 220 Mile Plan | [5 empty] | PCR to return unused $ back to the program | 2020-06-02 |  | 1994.6 | 1733017 | 2020 | 2021 |  | 1054689 | 260000 | 1054689 | 260000 |  |  | 2020-11-30 | FICL | 2021-01-14 | 2020-06-02 | [15 empty] | Approved |  |  | 2021-05-13 16:31 |  |  | 2021-05-12 16:18 |  |  | 2021 | Order and Notification
85997 | Defer project | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Can't be constructed until Phase 3.1 mainline is transferred underground next year. | 2022-09-01 | 2022-08-16 | 2438.1 | 1313564.84 | 2021 | 2022 | 2022 |  | 153000 |  | 163000 | 4310000 | 3500 | 2021-12-31 | PEND |  | 2022-09-01 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:57 |  |  | 2021-05-12 11:45 |  |  | 2022 | Order and Notification
85994 | Add project | 35248770 |  | FRRB - WYANDOTTE 11031974 - W1 SM2 | Approved | 08W | [6 empty] | adding this project to WP as part of NCFR | 2021-07-01 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-20 13:48 |  |  | 2021-05-12 10:54 |  |  |  | Not in Work Plan
85908 | Add project | 35174475 |  | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 | Approved | 08W | [6 empty] | Per email exchange between [REDACTED] and [REDACTED], adding this project to 2022 | 2022-06-01 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [17 empty] | Approved |  |  | 2021-05-21 10:56 |  |  | 2021-05-11 16:42 |  |  |  | Not in Work Plan
85909 | Add project | 35174476 |  | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 | Approved | 08W | [6 empty] | Per email exchange between [REDACTED] and [REDACTED], adding this project to 2022 | 2022-06-01 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [17 empty] | Approved |  |  | 2021-05-21 10:56 |  |  | 2021-05-11 16:42 |  |  |  | Not in Work Plan
85910 | Add project | 35174477 |  | ECOP-CALISTOGA 1101-H01-LR736-PH3 | Approved | 08W | [6 empty] | Per email exchange between [REDACTED] and [REDACTED], adding this project to 2022 | 2022-06-01 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [17 empty] | Approved |  |  | 2021-05-21 10:56 |  |  | 2021-05-11 16:42 |  |  |  | Not in Work Plan
85911 | Add project | 35191130 |  | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 | Approved | 08W | [6 empty] | Per email exchange between [REDACTED] and [REDACTED], adding this project to 2022 | 2022-06-01 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [17 empty] | Approved |  |  | 2021-05-21 10:56 |  |  | 2021-05-11 16:42 |  |  |  | Not in Work Plan
81596 | Pull-in Project from Future Year | 35219291 | 120141627 | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2021 | 2021-08-03 | 2021-06-01 | 421.2 | 165125.99 | 2021 | 2022 | 2021 |  | 1265910 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-03 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:18 |  |  | 2021 | Order and Notification
81703 | Pull-in Project from Future Year | 35234380 | 120564073 | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2021 | 2022-05-02 | 2021-06-01 | 0 | 150000 | 2021 | 2022 | 2021 |  | 3500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:18 |  |  | 2022 | Order and Notification
81715 | Defer project | 35234395 | 120564126 | CWSP - OREGON TRAIL 110335002 PH5.4 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158334 | 2021 | 2022 | 2022 |  | 536000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81707 | Defer project | 35234393 | 120564122 | CWSP - OREGON TRAIL 110335002 PH5.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158334 | 2021 | 2022 | 2022 |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81730 | Defer project | 35234399 | 120564153 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 230000 | 2021 | 2022 | 2022 |  | 382000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED]email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81719 | Defer project | 35234396 | 120564127 | CWSP - OREGON TRAIL 110335002 PH5.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158334 | 2021 | 2022 | 2022 |  | 404000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81726 | Defer project | 35234398 | 120564152 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 180000 | 2021 | 2022 | 2022 |  | 660000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81722 | Defer project | 35234397 | 120564129 | CWSP - OREGON TRAIL 110335002 PH5.6 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158334 | 2021 | 2022 | 2022 |  | 352000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81711 | Defer project | 35234394 | 120564123 | CWSP - OREGON TRAIL 110335002 PH5.3 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158334 | 2021 | 2022 | 2022 |  | 364000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81696 | Defer project | 35233951 | 120564184 | CWSP - OREGON TRAIL 110335002 PH1.6 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 |  | 2021 | 2022 | 2022 |  | 428000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81734 | Defer project | 35234400 | 120564154 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 180000 | 2021 | 2022 | 2022 |  | 424000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81692 | Defer project | 35233947 | 120564156 | CWSP - OREGON TRAIL 110335002 PH1.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 125000 | 2021 | 2022 | 2022 |  | 500000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81738 | Defer project | 35234401 | 120564155 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 180000 | 2021 | 2022 | 2022 |  | 560000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81742 | Defer project | 35234526 | 120574717 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-22 | 2022-06-01 | 80 | 1 | 2021 | 2022 | 2022 |  | 100000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81626 | Defer project | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-09-01 | 2022-06-01 | 2438.1 | 1313564.84 | 2021 | 2022 | 2022 |  | 153000 |  |  |  |  | 2021-12-31 | PEND |  | 2022-09-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81634 | Defer project | 35227658 | 120462182 | CWSP - VACAVILLE 11046542 - PH 2.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-23 | 2022-06-01 | 1000.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-23 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81638 | Defer project | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-05 | 2022-06-01 | 110.1 | 200000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81642 | Defer project | 35227870 | 120462116 | CWSP - VACAVILLE 11046542 - PH 2.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-09 | 2022-06-01 | 4000.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-09 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81630 | Defer project | 35227654 | 120462113 | CWSP - VACAVILLE 11046542 PH 1.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-04-20 | 2022-06-01 | 80 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-04-20 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81699 | Defer project | 35234284 | 120539923 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-22 | 2022-06-01 | 80 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81684 | Defer project | 35231630 | 120504176 | CWSP - HIGHLANDS 1102628 PH 1.12 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-09-20 | 2022-06-01 | 400.6 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-09-20 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81673 | Defer project | 35231627 | 120504167 | CWSP - HIGHLANDS 1102628 PH 1.9 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81680 | Defer project | 35231629 | 120504175 | CWSP - HIGHLANDS 1102628 PH 1.11 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81688 | Defer project | 35231631 | 120504177 | CWSP - HIGHLANDS 1102628 PH 1.13 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81676 | Defer project | 35231628 | 120504170 | CWSP - HIGHLANDS 1102628 PH 1.10 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81669 | Defer project | 35231626 | 120504165 | CWSP - HIGHLANDS 1102628 PH 1.8 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-08-25 | 2022-06-01 | 407.2 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81653 | Defer project | 35231622 | 120504139 | CWSP - HIGHLANDS 1102628 PH 1.4 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81646 | Defer project | 35231620 | 120504137 | CWSP - HIGHLANDS 1102628 PH 1.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81661 | Defer project | 35231624 | 120504163 | CWSP - HIGHLANDS 1102628 PH 1.6 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81650 | Defer project | 35231621 | 120504138 | CWSP - HIGHLANDS 1102628 PH 1.3 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81657 | Defer project | 35231623 | 120504160 | CWSP - HIGHLANDS 1102628 PH 1.5 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81665 | Defer project | 35231625 | 120504164 | CWSP - HIGHLANDS 1102628 PH 1.7 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-01-19 | 2022-06-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81599 | Defer project | 35219542 | 120135655 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-11-01 | 2022-06-01 | 0 | 500000 | 2021 | 2022 | 2022 |  | 105000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-11-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81614 | Defer project | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-13 | 2022-06-01 | 1068.1 | 621258.86 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2022-06-13 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81622 | Defer project | 35225829 | 120426406 | CWSP - OREGON TRAIL 110335002 PH5.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-08 | 2022-06-01 | 80 | 158330 | 2021 | 2022 | 2022 |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81618 | Defer project | 35225828 | 120426405 | CWSP - OREGON TRAIL 110335002 PH4.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-09-21 | 2022-06-01 | 80 | 200000 | 2021 | 2022 | 2022 |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-09-21 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81602 | Defer project | 35223032 | 120242546 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-04-06 | 2022-06-01 | 83 | 500000 | 2021 | 2022 | 2022 |  | 136000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-04-06 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81610 | Defer project | 35223062 | 120242676 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-11-16 | 2022-06-01 | 80 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-11-16 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81606 | Defer project | 35223038 | 120242693 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-22 | 2022-06-01 | 80 | 1 | 2021 | 2022 | 2022 |  | 350000 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81591 | Defer project | 35219287 | 120142356 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-06-01 | 2022-06-01 | 0 | 180000 | 2021 | 2022 | 2022 |  | 540000 |  |  |  |  | 2021-12-31 | UNSE | [17 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81583 | Defer project | 35219273 | 120142173 | CWSP - VOLTA 110149742 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-09-17 | 2022-06-01 | 2734.5 | 633229.22 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-09-17 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81587 | Defer project | 35219276 | 120142212 | CWSP - VACAVILLE 11046542 PH 1.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2022-07-01 | 2022-06-01 | 7040 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-07-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81579 | Defer project | 35219099 | 120141849 | CWSP - HIGHLANDS 1102628 PH 1.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-11-24 | 2022-06-01 | 80 | 73076 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81575 | Defer project | 35174085 | 118944585 | PSPS - FROGTOWN 1702 - LR 36870 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-06-22 | 2022-06-01 | 304 | 63132.37 | 2020 | 2022 | 2022 | [6 empty] | 2020-10-31 | UNSC |  | 2021-06-22 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81556 | Defer project | 35052731 | 114607365 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-06-21 | 2022-06-01 | 3503.2 | 4994628 | 2020 | 2022 | 2022 | 220000 | 2129616.4 |  |  |  |  | 2020-09-30 | UNSC |  | 2021-06-21 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81560 | Defer project | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-30 | 2022-06-01 | 1781.5 | 3142865.56 | 2021 | 2022 | 2022 | 48176.5 | 500000 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81544 | Pull-in Project from Future Year | 35046211 | 114730956 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2023-02-01 | 2022-06-01 | 3 | 95000 | 2022 |  | 2022 | 1475029.2 | [5 empty] | 2019-10-25 | UNSE |  | 2023-02-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81548 | Pull-in Project from Future Year | 35050942 | 114848297 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2023-02-01 | 2022-06-01 | 3 | 95000 | 2022 |  | 2022 | 3133811.9 | [5 empty] | 2019-10-25 | UNSE |  | 2023-02-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81552 | Pull-in Project from Future Year | 35050951 | 114848376 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2023-02-01 | 2022-06-01 | 2001.1 | 95000 | 2022 |  | 2022 | 1542801.8 | [5 empty] | 2019-12-31 | UNSE |  | 2023-02-01 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81567 | Defer project | 35113951 | 117560047 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-12-29 | 2022-06-01 | 4240.3 | 6920313 | 2021 | 2022 | 2022 | 200000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-12-29 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81571 | Defer project | 35119965 | 117721840 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E | Approved | 08W | 220 Mile Plan | [5 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2020-07-13 | 2022-06-01 | 2149 | 1924210 | 2020 | 2022 | 2022 | 946010.2 | 406653.3 |  |  |  |  | 2020-12-31 | PEND |  | 2020-07-13 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
81563 | Defer project | 35113950 | 117560045 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [6 empty] | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 | 2021-07-09 | 2022-06-01 | 6002.2 | 7087268 | 2021 | 2022 | 2022 | 180000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-07-09 | [15 empty] | Approved | Per [REDACTED] email exchange with [REDACTED], moving this project to 2022 |  | 2021-05-11 15:58 |  |  | 2021-05-11 15:17 |  |  | 2022 | Order and Notification
79584 | Defer project | 35238098 | 120658775 | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 | Approved | 08W | [6 empty] | scope of work dependent on completion of multiple UG work scheduled in 2022 (Silverado Circuit). | 2022-07-01 | 2022-08-10 | 424.7 | 211465.05 | 2021 | 2022 | 2022 |  | 189000 |  | 189000 | 1000 |  | 2021-12-31 | PEND |  | 2022-07-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 13:45 |  |  | 2022 | Order and Notification
84165 | Add project | 35116388 | 117930543 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Denied | 08W | [6 empty] | 2022 Work Plan Tags | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | PEND | [14 empty] | Denied | Change Requested entered in error |  | Denied | Denied by Program Manager |  | 2021-05-20 13:42 |  |  | 2021-05-11 12:41 |  |  |  | Not in Work Plan
79364 | Budget change | 35113105 | 117492229 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | DRS 2021-28615 for contingency release approved 5/11/2021 EAC for 2021 is approx $11000 | 2020-03-23 |  | 2910 | 1425671 | 2020 |  |  | 858091 | 11000 |  | 11000 |  |  | 2020-12-31 | FICL | 2020-11-15 | [16 empty] | Approved |  |  | 2021-05-13 16:31 |  |  | 2021-05-11 11:50 |  |  | 2020 | Order and Notification
79344 | Budget change | 35161152 | 118677953 | OCT2019 BRICEBURG FIRE REBUILD | Approved | 08W | [6 empty] | Fire Hardening / Approved FCO's | 2021-01-11 |  | 200 | 1676000 | 2021 |  |  | 375186 | 1400000 |  | 1400000 | 0 |  |  | MAPP | 2021-05-20 | 2021-01-11 | [15 empty] | Approved |  |  | 2021-05-13 16:31 |  |  | 2021-05-11 09:44 |  |  | 2021 | Order and Notification
79343 | Defer project | 35113951 | 117560047 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [6 empty] | Per [REDACTED] email, project will complete in 2022. | 2021-12-29 | 2021-11-04 | 4240.3 | 6920313 | 2021 | 2022 | 2022 | 200000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-05-11 10:44 |  |  | 2021-05-11 09:35 |  |  | 2022 | Order and Notification
79342 | Defer project | 35113950 | 117560045 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [6 empty] | Per [REDACTED] email, project will complete in 2022. | 2021-07-09 | 2021-06-22 | 6002.2 | 7087268 | 2021 | 2022 | 2022 | 180000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-05-11 10:44 |  |  | 2021-05-11 09:34 |  |  | 2022 | Order and Notification
79341 | Defer project | 35052731 | 114607365 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Per [REDACTED] email, project to complete in 2022 | 2021-06-21 | 2021-06-01 | 3503.2 | 4994628 | 2020 | 2022 | 2022 | 220000 | 2129616.4 |  |  |  |  | 2020-09-30 | UNSC |  | 2021-06-21 | [15 empty] | Approved |  |  | 2021-05-11 10:44 |  |  | 2021-05-11 09:31 |  |  | 2022 | Order and Notification
79332 | Defer project | 35234401 | 120564155 | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Approved | 08W | [6 empty] | Other 4 phases of project deferred to 2022, Cannot build standalone due to OH/UG transitions. | 2022-06-01 | 2022-10-21 | 0 | 180000 | 2021 | 2022 | 2022 |  | 560000 | 0 | 560000 | 240000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:35 |  |  | 2022 | Order and Notification
79331 | Defer project | 35234400 | 120564154 | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2022-06-01 | 2022-10-21 | 0 | 180000 | 2021 | 2022 | 2022 |  | 424000 | 0 | 424000 | 1800000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:35 |  |  | 2022 | Order and Notification
79330 | Defer project | 35234399 | 120564153 | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Approved | 08W | [6 empty] | Cannot secure easement in time for 2021 construct | 2022-06-01 | 2022-10-21 | 0 | 230000 | 2021 | 2022 | 2022 |  | 382000 | 0 | 382000 | 1250000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:34 |  |  | 2022 | Order and Notification
79329 | Defer project | 35234398 | 120564152 | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Approved | 08W | [6 empty] | Cannot secure easement in time for 2021 construct | 2022-06-01 | 2022-10-21 | 0 | 180000 | 2021 | 2022 | 2022 |  | 660000 | 0 | 660000 | 3900000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:34 |  |  | 2022 | Order and Notification
79328 | Defer project | 35219287 | 120142356 | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2022-06-01 | 2022-10-21 | 0 | 180000 | 2021 | 2022 | 2022 |  | 540000 | 0 | 540000 | 3300000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:34 |  |  | 2022 | Order and Notification
79327 | Defer project | 35234397 | 120564129 | CWSP - OREGON TRAIL 110335002 PH5.6 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158334 | 2021 | 2022 | 2022 |  | 352000 | 0 | 352000 | 800000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79326 | Defer project | 35234396 | 120564127 | CWSP - OREGON TRAIL 110335002 PH5.5 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158334 | 2021 | 2022 | 2022 |  | 404000 | 0 | 404000 | 2300000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79325 | Defer project | 35234395 | 120564126 | CWSP - OREGON TRAIL 110335002 PH5.4 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158334 | 2021 | 2022 | 2022 |  | 536000 | 0 | 536000 | 3800000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79324 | Defer project | 35234394 | 120564123 | CWSP - OREGON TRAIL 110335002 PH5.3 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158334 | 2021 | 2022 | 2022 |  | 364000 | 0 | 364000 | 2500000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79323 | Defer project | 35234393 | 120564122 | CWSP - OREGON TRAIL 110335002 PH5.2 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158334 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 3372000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79322 | Defer project | 35225829 | 120426406 | CWSP - OREGON TRAIL 110335002 PH5.1 | Approved | 08W | [6 empty] | DSDD (Cal Trans) permitting not achievable in 2021 | 2021-12-08 | 2022-10-21 | 80 | 158330 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 3000000 | 0 | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:20 |  |  | 2022 | Order and Notification
79321 | Defer project | 35225828 | 120426405 | CWSP - OREGON TRAIL 110335002 PH4.1 | Approved | 08W | [6 empty] | All Oregon Trail UG work deferred to 2022 in favor of OH hardening. | 2021-09-21 | 2022-09-16 | 80 | 200000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 8100000 | 0 | 2021-12-31 | UNSE |  | 2021-09-21 | [7 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 08:19 |  |  | 2022 | Order and Notification
79320 | Pull-in Project from Future Year | 35234380 | 120564073 | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [6 empty] | Project identified as constructable via EPC process. | 2022-05-02 | 2021-10-31 | 0 | 150000 | 2021 | 2022 | 2021 |  | 3500000 | 0 | 3500000 | 0 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Pull in project from future approved |  | Approved |  |  | Approved |  |  | 2021-05-27 20:41 |  |  | 2021-05-11 07:57 |  |  | 2022 | Order and Notification
79319 | Defer project | 35233951 | 120564184 | CWSP - OREGON TRAIL 110335002 PH1.6 | Approved | 08W | [6 empty] | Project is part of a phase primarily composed of underground work in Cal Trans RoW. | 2022-06-01 | 2022-09-16 | 0 |  | 2021 | 2022 | 2022 |  | 428000 | 0 | 428000 | 1000000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 07:46 |  |  | 2022 | Order and Notification
79318 | Defer project | 35233947 | 120564156 | CWSP - OREGON TRAIL 110335002 PH1.2 | Approved | 08W | [6 empty] | Project is part of a phase primarily composed of underground work in Cal Trans RoW. | 2022-06-01 | 2022-09-16 | 0 | 125000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 1100000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved | All OREGON TRAIL went to EPC | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-11 07:46 |  |  | 2022 | Order and Notification
79228 | Pull-in Project from Future Year | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan | [5 empty] | Job completed in 2020 | 2020-06-01 | 2020-12-03 | 2558.5 | 2927538 | 2020 |  | 2020 | 1900000 | 131088 |  |  |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [18 empty] | 2021-05-10 13:52 |  |  | 2021-05-10 13:52 |  |  | 2020 | Order and Notification
79227 | Pull-in Project from Future Year | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Job completed in 2020 | 2020-06-02 | 2020-11-20 | 3236.8 | 5062019 | 2020 |  | 2020 | 4762461.3 | 59744 |  |  |  |  | 2020-12-31 | PREC | 2020-11-20 | [19 empty] | 2021-05-10 13:52 |  |  | 2021-05-10 13:52 |  |  | 2020 | Order and Notification
79222 | Pull-in Project from Future Year | 35120949 | 117755982 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Approved | 08W | [6 empty] | Job completed in 2020 | 2019-10-14 | 2020-06-25 | 7588.6 | 14251728 | 2020 | 2021 | 2020 | 947568.2 | [5 empty] | 2020-02-28 | DOCC | 2020-06-25 | 2019-10-14 | [18 empty] | 2021-05-10 13:52 |  |  | 2021-05-10 13:52 |  |  | 2021 | Order and Notification
79023 | Defer project | 35223026 | 120245190 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Approved | 08W | [6 empty] | Project's EOD pushed causing units to be recognized in 2022 | 2022-05-02 | 2022-05-01 | 640 | 190000 | 2021 | 2022 | 2022 |  | 180000 | 0 | 180000 | 10000 |  | 2021-12-31 | ESTS |  | 2022-05-02 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-07 14:08 |  |  | 2022 | Order and Notification
79025 | Defer project | 35223024 | 120245076 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Approved | 08W | [6 empty] | Project's EOD pushed causing units to be recognized in 2022 | 2022-03-01 | 2022-03-01 | 640 | 190000 | 2021 | 2022 | 2022 |  | 180000 | 0 | 180000 | 10000 |  | 2021-12-31 | ESTS |  | 2022-03-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-07 14:07 |  |  | 2022 | Order and Notification
79024 | Defer project | 35192284 | 119556691 | ECOP - SILVERADO 2104 - H05-LR726 | Approved | 08W | [6 empty] | Project's EOD pushed causing units to be recognized in 2022 | 2022-01-10 | 2022-01-10 | 80 | 400000 | 2021 | 2022 | 2022 | 9859 | 380000 | 9859 | 380000 | 10000 |  | 2023-12-31 | ESTS |  | 2022-01-10 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-07 14:06 |  |  | 2022 | Order and Notification
78828 | Unassign Resource | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W | [7 empty] | 2021-10-28 |  | 4313.1 | 5959167 | 2021 | 2022 |  | 300000 | 500000 |  |  |  |  | 2020-09-30 | PEND |  | 2021-10-28 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 14:08 |  |  | 2022 | Order and Notification
78825 | Unassign Resource | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W | [7 empty] | 2022-05-09 |  | 180 | 550000 | 2021 | 2022 |  |  | 852800 |  |  |  |  | 2023-12-31 | ESTS |  | 2022-05-09 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 14:08 |  |  | 2022 | Order and Notification
78822 | Unassign Resource | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [7 empty] | 2022-06-13 |  | 1068.1 | 621258.86 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2022-06-13 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 14:08 |  |  | 2022 | Order and Notification
78823 | Unassign Resource | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv | [6 empty] | 2022-01-04 |  | 2163 | 2768676 | 2021 | 2022 |  | 4086056.3 | 44404 |  |  |  |  | 2021-07-12 | PEND |  | 2022-01-04 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 14:08 |  |  | 2022 | Order and Notification
78820 | Unassign Resource | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [7 empty] | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 | 2022 |  | 48176.5 | 500000 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 14:07 |  |  | 2022 | Order and Notification
78806 | Resource change | 35222045 | 120233319 | SH - MIDDLTOWN 1103 - LR 830 PH4 | Approved | 08W | [7 empty] | 2021-10-01 |  | 83 | 1 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 13:45 |  |  | 2021 | Order and Notification
78807 | Resource change | 35236661 | 120617883 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Approved | 08W | [7 empty] | 2021-10-28 |  | 80 | 100000 | 2021 | [8 empty] | 2021-12-31 | APPR |  | 2021-10-28 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 13:45 |  |  | 2021 | Order and Notification
78777 | Resource change | 35236438 | 120617839 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | Approved | 08W | [7 empty] | 2021-11-25 |  | 80 | 90000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-11-25 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 13:33 |  |  | 2021 | Order and Notification
78776 | Resource change | 35236437 | 120617837 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | Approved | 08W | [7 empty] | 2021-10-14 |  | 80 | 90000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 13:33 |  |  | 2021 | Order and Notification
78011 | Resource change | 35236662 | 120618060 | CWSP - OLETA 1101754718 PH 1.2 | Approved | 08W | [7 empty] | 2021-09-17 |  | 0 | 1 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-17 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 09:09 |  |  | 2021 | Order and Notification
78010 | Resource change | 35219591 | 120173637 | CWSP - OLETA 1101754718 PH1.1 | Approved | 08W | [7 empty] | 2022-05-11 |  | 240 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-05-11 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-06 09:07 |  |  | 2022 | Order and Notification
76328 | Resource change | 35113950 | 117560045 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [7 empty] | 2021-07-09 |  | 6002.2 | 7087268 | 2021 | 2022 |  | 180000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-07-09 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-05 14:29 |  |  | 2022 | Order and Notification
76329 | Resource change | 35113951 | 117560047 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [7 empty] | 2021-12-29 |  | 4240.3 | 6920313 | 2021 | 2022 |  | 200000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-05 14:29 |  |  | 2022 | Order and Notification
76226 | Resource change | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W | [7 empty] | 2022-01-26 |  | 111.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-26 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:37 |  |  | 2022 | Order and Notification
76225 | Resource change | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W | [7 empty] | 2021-10-27 |  | 110.1 | 250000 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2021-10-27 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:36 |  |  | 2022 | Order and Notification
76224 | Budget change | 35235700 | 120598982 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 2023.7 | 7794107 | 2021 |  |  |  | 5178377 | 0 | 4410087.05 | 0 | 0 | 2022-05-07 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:12 |  |  | 2021 | Order and Notification
76215 | Budget change | 35236995 | 120627597 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 3342.6 | 11024453 | 2021 |  |  |  | 7663381 | 0 | 6895091.34 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:12 |  |  | 2021 | Order and Notification
76223 | Budget change | 35236993 | 120627595 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-27 |  | 910.4 | 3881421 | 2021 |  |  |  | 2168690 | 0 | 1400399.7 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:12 |  |  | 2021 | Order and Notification
76222 | Budget change | 35236991 | 120627593 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-06 |  | 2464.7 | 7834694 | 2021 |  |  |  | 5209578 | 0 | 4441288 | 0 | 0 | 2022-06-30 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:11 |  |  | 2021 | Order and Notification
76221 | Budget change | 35239099 | 120685592 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 1483 | 5064020 | 2021 |  |  |  | 3078290 | 0 | 2310000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:11 |  |  | 2021 | Order and Notification
76220 | Budget change | 35239098 | 120685590 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 80 | 8340020 | 2021 |  |  |  | 5598290 | 0 | 4830000 | 0 | 0 | 2021-12-31 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:11 |  |  | 2021 | Order and Notification
76219 | Budget change | 35239097 | 120685508 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 2382.4 | 6656520 | 2021 |  |  |  | 4303290 | 0 | 3535000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:11 |  |  | 2021 | Order and Notification
76218 | Budget change | 35239096 | 120685505 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-09 |  | 1698.8 | 6065020 | 2021 |  |  |  | 3848290 | 0 | 3080000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:10 |  |  | 2021 | Order and Notification
76217 | Budget change | 35239095 | 120685501 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-09 |  | 2634.3 | 7202520 | 2021 |  |  |  | 4723290 | 0 | 3955000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:10 |  |  | 2021 | Order and Notification
76216 | Budget change | 35235671 | 120594872 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-20 |  | 1773.7 | 4290520 | 2021 |  |  |  | 2483290 | 0 | 1715000 | 0 | 0 | 2022-05-03 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:10 |  |  | 2021 | Order and Notification
76214 | Budget change | 35235669 | 120594870 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | Approved | 08W | [6 empty] | requesting 2021 Budget to allign with CY EAC in the BC | 2021-08-09 |  | 1270.1 | 3927014 | 2021 |  |  |  | 2204458 | 0 | 1436167.61 | 0 | 0 | 2022-05-03 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 14:08 |  |  | 2021 | Order and Notification
76204 | Budget change | 35240546 | 120723697 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-06-04 |  | 401.7 | 2470520 | 2021 |  |  |  | 1083290 | 0 | 315000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:04 |  |  | 2021 | Order and Notification
76203 | Budget change | 35240545 | 120723696 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-06-04 |  | 652.9 | 2561702 | 2021 |  |  |  | 1153472.39 | 0 | 385182.39 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:04 |  |  | 2021 | Order and Notification
76202 | Budget change | 35239937 | 120711267 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-06-04 |  | 1628.5 | 4746246 | 2021 |  |  |  | 2834016.47 | 0 | 2065726.47 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:04 |  |  | 2021 | Order and Notification
76201 | Budget change | 35239523 | 120695189 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-06-01 |  | 973.8 | 3198520 | 2021 |  |  |  | 1643290 | 0 | 875000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:03 |  |  | 2021 | Order and Notification
76208 | Budget change | 35239522 | 120695185 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-06-01 |  | 594.5 | 3198520 | 2021 |  |  |  | 1643290 | 0 | 875000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:03 |  |  | 2021 | Order and Notification
76207 | Budget change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 1647.2 | 6383520 | 2021 |  |  |  | 4093290 | 0 | 3325000 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:03 |  |  | 2021 | Order and Notification
76206 | Budget change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 1062.1 | 7339020 | 2021 |  |  |  | 4828290 | 0 | 4060000 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:03 |  |  | 2021 | Order and Notification
76205 | Budget change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-28 |  | 4409.1 | 8067020 | 2021 |  |  |  | 5388290 | 0 | 4620000 | 0 | 0 | 2022-03-03 | UNSC |  | 2021-07-28 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:02 |  |  | 2021 | Order and Notification
76199 | Budget change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 1103.5 | 6429020 | 2021 |  |  |  | 4128290 | 0 | 3360000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:02 |  |  | 2021 | Order and Notification
76198 | Budget change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 5336.9 | 9341020 | 2021 |  |  |  | 6368290 | 0 | 5600000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:02 |  |  | 2021 | Order and Notification
76197 | Budget change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 2405 | 7066020 | 2021 |  |  |  | 4618290 | 0 | 3850000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:02 |  |  | 2021 | Order and Notification
76200 | Budget change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-16 |  | 1433.2 | 4335155 | 2021 |  |  |  | 2518289.22 | 0 | 1749999.22 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 13:01 |  |  | 2021 | Order and Notification
76196 | Budget change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Denied | 08W | [6 empty] | Requesting 2021 Budget to match the approved CY EAC in the BC | 2021-07-19 |  | 1673 | 7748520 | 2021 |  |  |  | 5143290 | 0 | 4375000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Denied | Requested budget is the same as the current MPP approved budget for 2021 |  | 2021-05-06 17:22 |  |  | 2021-05-04 13:01 |  |  | 2021 | Order and Notification
76195 | Unassign Resource | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [7 empty] | 2022-01-05 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 12:01 |  |  | 2022 | Order and Notification
76189 | Resource change | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2022 | Order and Notification
76190 | Resource change | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2022 | Order and Notification
76191 | Resource change | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [7 empty] | 2021-11-11 |  | 80 | 67857 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2022 | Order and Notification
76192 | Resource change | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [7 empty] | 2021-11-05 |  | 433.2 | 204489.16 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | PEND |  | 2021-11-05 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2022 | Order and Notification
76193 | Resource change | 35226871 | 120449235 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Approved | 08W | [7 empty] | 2022-11-01 |  | 0.5 | 59835.3 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2021 | Order and Notification
76194 | Resource change | 35226872 | 120449236 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Approved | 08W | [7 empty] | 2022-11-01 |  | 403.7 | 159527.53 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:58 |  |  | 2021 | Order and Notification
76188 | Resource change | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [7 empty] | 2021-11-11 |  | 648.8 | 338825.78 | 2021 | 2022 |  |  | 67857 |  |  |  |  | 2021-12-31 | PEND |  | 2021-11-11 | [15 empty] | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-04 11:56 |  |  | 2022 | Order and Notification
76173 | Budget change | 35116804 |  | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Denied | 08W | [6 empty] | Reduce Budget to $18,694 Duplicate Change ID 69598 Processed in error | [10 empty] | 18691 |  |  |  | FICL | 2020-08-22 | [16 empty] | Denied | Jobs completed in 2020, closing costs do not require a 2021 budget. This project should not be on the scorecard. |  | 2021-05-06 17:14 |  |  | 2021-05-04 08:26 |  |  |  | Not in Work Plan
76170 | Budget change | 35052820 |  | CWSP - MIWUK 1702 - OCB - PH 1.1 | Denied | 08W | [6 empty] | Reduce Budget to $136,434 Duplicate Change ID 69599 Processed in error | [10 empty] | 136434 |  |  |  | DOCC | 2020-08-04 | [16 empty] | Denied | Jobs completed in 2020, closing costs do not require a 2021 budget. This project should not be on the scorecard. |  | 2021-05-06 17:14 |  |  | 2021-05-04 08:15 |  |  |  | Not in Work Plan
76108 | Defer project | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [6 empty] | Project Deferring to 2022 | 2022-01-05 | 2022-11-30 | 110.1 | 200000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-03 13:21 |  |  | 2022 | Order and Notification
76105 | Defer project | 35223062 | 120242676 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Approved | 08W | [6 empty] | Project Deferring to 2022 | 2021-11-16 | 2022-09-20 | 80 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-11-16 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:54 |  |  | 2021-05-03 13:10 |  |  | 2022 | Order and Notification
76082 | Add project | 35229043 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 | Approved | 08W | [6 empty] | adding this job as part of NCFR program | 2021-07-01 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-05-03 11:06 |  |  |  | Not in Work Plan
75974 | Defer project | 35219542 | 120135655 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Approved | 08W | [6 empty] | All mileage in 2022 | 2022-11-01 | 2022-07-07 | 0 | 500000 | 2021 | 2022 | 2022 |  | 105000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:57 |  |  | 2021-04-30 10:22 |  |  | 2022 | Order and Notification
75973 | Defer project | 35219542 | 120135655 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Approved | 08W | [6 empty] | All mileage in 2022. | 2022-11-01 | 2022-11-01 | 0 | 500000 | 2021 | 2022 | 2022 |  | 105000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-05-20 13:57 |  |  | 2021-04-30 10:14 |  |  | 2022 | Order and Notification
75967 | Add project | 35244574 |  | FRRB - WYANDOTTE 11031974 - W3 SM2 | Approved | 08W | [6 empty] | adding this project as part of NCFR Program | 2021-09-01 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-04-30 08:56 |  |  |  | Not in Work Plan
75966 | Add project | 35244573 |  | FRRB - WYANDOTTE 11031974 - W3 SM1 | Approved | 08W | [6 empty] | adding this project as part of NCFR Program | 2021-09-01 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-04-30 08:56 |  |  |  | Not in Work Plan
75965 | Add project | 35244330 |  | FRRB - WYANDOTTE 11031974 - W1 SM1 | Approved | 08W | [6 empty] | adding this project as part of NCFR Program | 2021-09-01 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-04-30 08:56 |  |  |  | Not in Work Plan
75964 | Add project | 35236982 |  | FRRB - KANAKA 1101 - K6 PH6 | Approved | 08W | [6 empty] | adding this project as part of NCFR Program | 2021-09-01 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-04-30 08:56 |  |  |  | Not in Work Plan
75960 | Budget change | 35226851 | 120449144 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Approved | 08W | [6 empty] | Phase Gate 3 Review complete and Business Case Routing ; Approved EAC | 2021-07-07 |  | 1753.7 | 3783519 | 2021 |  |  |  | 1871077 | 0 | 1871077 | 0 | 0 | 2021-12-31 | CONS |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-29 16:32 |  |  | 2021 | Order and Notification
75959 | Budget change | 35226850 | 120449143 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Approved | 08W | [6 empty] | Phase Gate 3 Review approved and Business Case routing for approval. | 2021-06-10 |  | 1473.4 | 3060229 | 2021 |  |  |  | 1518941 | 0 | 1518941 | 0 | 0 | 2021-12-31 | CONS |  | 2021-06-10 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-29 16:27 |  |  | 2021 | Order and Notification
75958 | Budget change | 35232280 | 120527401 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Approved | 08W | [6 empty] | Business Case approved - EAC increase | 2021-06-09 |  | 741 | 465706.54 | 2021 |  |  |  | 667231 |  | 667231 | 0 |  | 2021-12-31 | CONS |  | 2021-06-09 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-29 16:20 |  |  | 2021 | Order and Notification
75957 | Defer project | 35223038 | 120242693 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | Approved | 08W | [6 empty] | Per PM, project deferred to 2022 This is a new OH project, but dependent on UG phases and UG dependencies will not be completed this year. | 2021-12-22 | 2022-09-21 | 80 | 1 | 2021 | 2022 | 2022 |  | 350000 |  | 350000 | 750000 |  | 2021-12-31 | UNSE |  | 2021-12-22 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-29 16:11 |  |  | 2022 | Order and Notification
75956 | Defer project | 35234526 | 120574717 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Approved | 08W | [6 empty] | Per PM, project deferred to 2022 This is a new OH project, but dependent on UG phases and UG dependencies will not be completed this year. | 2021-12-22 | 2022-09-21 | 80 | 1 | 2021 | 2022 | 2022 |  | 100000 |  | 100000 | 1032000 | 0 | 2021-12-31 | UNSE |  | 2021-12-22 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-29 16:03 |  |  | 2022 | Order and Notification
75751 | Budget change | 35226900 | 120450946 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022. estimating hitting in 21 and construction in 22 | 2022-07-13 |  | 80 | 247500 | 2021 | 2022 |  |  | 27531 |  | 27531 | 1311000 |  | 2021-12-31 | ADER |  | 2022-07-13 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 13:15 |  |  | 2022 | Order and Notification
75757 | Budget change | 35226799 | 120450944 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022. estimating hitting in 21 and construction in 22 | 2022-07-11 |  | 203 | 71683.95 | 2021 | 2021 |  |  | 371000 |  | 10000 | 361000 |  | 2021-12-31 | PEND |  | 2022-07-11 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 13:14 |  |  | 2021 | Order and Notification
75756 | Budget change | 35226798 | 120450942 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022. estimating hitting in 21 and construction in 22 | 2022-07-01 |  | 80 | 247500 | 2021 | 2022 |  |  | 63441 |  | 63441 | 3021000 |  | 2021-12-31 | ADER |  | 2022-07-01 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 13:14 |  |  | 2022 | Order and Notification
75752 | Budget change | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022. estimating hitting in 21 and construction in 22 | 2022-05-11 |  | 330.1 | 247500 | 2021 | 2022 |  |  | 92967 |  | 92967 | 4426998 |  | 2021-12-31 | ADER |  | 2022-05-11 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 13:06 |  |  | 2022 | Order and Notification
75759 | Budget change | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022. estimating hitting in 21 and construction in 22 | 2022-04-20 |  | 2080.1 | 950000 | 2021 | 2022 |  |  | 102942 |  | 102942 | 4902000 |  | 2021-12-31 | ESTS |  | 2022-04-20 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 13:05 |  |  | 2022 | Order and Notification
75754 | Budget change | 35219286 | 120142352 | CWSP - DESCHUTES 11049718 PH1.1 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-09-29 |  | 3290 | 475000 | 2021 |  |  |  | 5630850 |  | 5630850 |  |  | 2021-12-31 | ESTS |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:56 |  |  | 2021 | Order and Notification
75753 | Budget change | 35232445 | 120528752 | CWSP - DESCHUTES 11049718 PH 2.5 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-08-02 |  | 3721.2 | 3055462 | 2021 |  |  |  | 3055462 |  | 5050350 |  |  | 2021-12-31 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:56 |  |  | 2021 | Order and Notification
75758 | Budget change | 35232442 | 120528704 | CWSP - DESCHUTES 11049718 PH 2.2 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-12-31 |  | 3040 | 190000 | 2021 |  |  |  | 5959798 |  | 5959798 |  |  | 2021-12-31 | ESTS | [17 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:56 |  |  | 2021 | Order and Notification
75755 | Budget change | 35232444 | 120528751 | CWSP - DESCHUTES 11049718 PH 2.4 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-10-22 |  | 5695.2 | 1475573.09 | 2021 |  |  |  | 6830548 |  | 6830548 |  |  | 2021-12-31 | PEND |  | 2021-10-22 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:56 |  |  | 2021 | Order and Notification
75761 | Budget change | 35232960 | 120537723 | CWSP - DESCHUTES 11049718 PH1.2 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-09-16 |  | 3040 | 475000 | 2021 |  |  |  | 5669548 |  | 5669548 |  |  | 2021-12-31 | ESTS |  | 2021-09-16 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:55 |  |  | 2021 | Order and Notification
75760 | Budget change | 35232443 | 120528712 | CWSP - DESCHUTES 11049718 PH 2.3 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-08-06 |  | 1292.4 | 1351751 | 2021 |  |  |  | 1351751 |  | 2012398 |  |  | 2021-12-31 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:55 |  |  | 2021 | Order and Notification
75762 | Budget change | 35225825 | 120426401 | CWSP - DESCHUTES 11049718 PH2.1 | Approved | 08W | [6 empty] | Requesting budget for 2021 | 2021-08-09 |  | 2973.4 | 2167192 | 2021 |  |  |  | 2167192 |  | 3037999 |  |  | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-29 12:28 |  |  | 2021 | Order and Notification
75646 | Pull-in Project from Future Year | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-01-13 | 2020-01-13 | 2123.7 | 5231108 | 2020 | 2021 | 2020 | 3150000 | 88800 |  |  |  |  | 2020-12-31 | FICL | 2021-02-25 | 2020-01-13 | [9 empty] | Approved | Pull in project from future approved |  | Approved |  |  | Approved |  |  | 2021-05-13 15:08 |  |  | 2021-04-29 10:32 |  |  | 2020 | Order and Notification
75645 | Pull-in Project from Future Year | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-06-01 | 2020-06-01 | 2558.5 | 2927538 | 2020 | 2021 | 2020 | 1900000 | 131088 |  |  |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [9 empty] | Approved | Pull in project from future approved |  | Approved |  |  | Approved |  |  | 2021-05-13 15:08 |  |  | 2021-04-29 10:32 |  |  | 2020 | Order and Notification
75644 | Pull-in Project from Future Year | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-06-02 | 2020-06-02 | 3236.8 | 5062019 | 2020 | 2021 | 2020 | 4762461.3 | 59744 |  |  |  |  | 2020-12-31 | PREC | 2020-11-20 | [10 empty] | Approved | Pull in project from future approved |  | Approved |  |  | Approved |  |  | 2021-05-13 15:08 |  |  | 2021-04-29 10:32 |  |  | 2020 | Order and Notification
75577 | Resource change | 35235700 | 120598982 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | Approved | 08W | [7 empty] | 2021-08-20 |  | 2023.7 | 7794107 | 2021 |  |  |  | 5178377 |  |  |  |  | 2022-05-07 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:27 |  |  | 2021 | Order and Notification
75605 | Resource change | 35236982 | 120627450 | FRRB - KANAKA 1101 - K6 PH6 | Denied | 08W | [7 empty] | 2021-09-01 |  | 80 | 950000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Denied | Resource change cannot be applied to project that is not on the work plan |  | 2021-04-30 12:40 |  |  | 2021-04-28 17:25 |  |  | 2021 | Order and Notification
75606 | Resource change | 35229043 | 120493696 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 1 | Denied | 08W | [7 empty] | 2021-07-01 |  | 0 |  | 2021 | [8 empty] | 2021-12-31 | UNSE | [17 empty] | Denied | Resource change cannot be applied to project that is not on the work plan |  | 2021-04-30 12:40 |  |  | 2021-04-28 17:25 |  |  | 2021 | Order and Notification
75638 | Resource change | 35235675 | 120596615 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 237500 | 2021 | [8 empty] | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:16 |  |  | 2021 | Order and Notification
75637 | Resource change | 35235672 | 120594873 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 237500 | 2021 | [8 empty] | 2022-05-03 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:15 |  |  | 2021 | Order and Notification
75636 | Resource change | 35236984 | 120627454 | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | Approved | 08W | [7 empty] | 2021-08-13 |  | 80 | 190000 | 2021 |  |  |  | 7991552 |  |  |  |  | 2022-05-07 | UNSE |  | 2021-08-13 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:14 |  |  | 2021 | Order and Notification
75635 | Resource change | 35241077 | 120751251 | FRRB - WYANDOTTE 1103 W5 PH5.4 FUTURE SM | Approved | 08W | [7 empty] | 2021-09-01 |  | 80 | 190000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:11 |  |  | 2021 | Order and Notification
75634 | Resource change | 35241076 | 120751207 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Approved | 08W | [7 empty] | 2021-09-01 |  | 80 | 190000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:10 |  |  | 2021 | Order and Notification
75633 | Resource change | 35241075 | 120751204 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Approved | 08W | [7 empty] | 2021-09-01 |  | 80 | 190000 | 2021 | [8 empty] | 2021-12-31 | UNSE |  | 2021-09-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:08 |  |  | 2021 | Order and Notification
75632 | Resource change | 35235670 | 120594871 | FRRB - WYANDOTTE 1103 W5 PH5.1 FUTURE SM | Approved | 08W | [7 empty] | 2021-09-01 |  | 80 | 190000 | 2021 | [8 empty] | 2022-05-03 | UNSE |  | 2021-09-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:07 |  |  | 2021 | Order and Notification
75631 | Resource change | 35236993 | 120627595 | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | Approved | 08W | [7 empty] | 2021-08-27 |  | 910.4 | 3881421 | 2021 |  |  |  | 2168690 |  |  |  |  | 2022-06-30 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:06 |  |  | 2021 | Order and Notification
75630 | Resource change | 35236991 | 120627593 | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | Approved | 08W | [7 empty] | 2021-08-06 |  | 2464.7 | 7834694 | 2021 |  |  |  | 5209578 |  |  |  |  | 2022-06-30 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:05 |  |  | 2021 | Order and Notification
75629 | Resource change | 35235671 | 120594872 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | Approved | 08W | [7 empty] | 2021-08-20 |  | 1773.7 | 4290520 | 2021 |  |  |  | 2483290 |  |  |  |  | 2022-05-03 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:04 |  |  | 2021 | Order and Notification
75628 | Resource change | 35236995 | 120627597 | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | Approved | 08W | [7 empty] | 2021-08-20 |  | 3342.6 | 11024453 | 2021 |  |  |  | 7663381 |  |  |  |  | 2022-06-30 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 17:00 |  |  | 2021 | Order and Notification
75627 | Resource change | 35235669 | 120594870 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | Approved | 08W | [7 empty] | 2021-08-09 |  | 1270.1 | 3927014 | 2021 |  |  |  | 2204458 |  |  |  |  | 2022-05-03 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:59 |  |  | 2021 | Order and Notification
75626 | Resource change | 35239099 | 120685592 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | Approved | 08W | [7 empty] | 2021-08-20 |  | 1483 | 5064020 | 2021 |  |  |  | 3078290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:59 |  |  | 2021 | Order and Notification
75625 | Resource change | 35239098 | 120685590 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 8340020 | 2021 |  |  |  | 5598290 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:58 |  |  | 2021 | Order and Notification
75624 | Resource change | 35239097 | 120685508 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | Approved | 08W | [7 empty] | 2021-08-20 |  | 2382.4 | 6656520 | 2021 |  |  |  | 4303290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:58 |  |  | 2021 | Order and Notification
75623 | Resource change | 35239096 | 120685505 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | Approved | 08W | [7 empty] | 2021-08-09 |  | 1698.8 | 6065020 | 2021 |  |  |  | 3848290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:48 |  |  | 2021 | Order and Notification
75622 | Resource change | 35239095 | 120685501 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | Approved | 08W | [7 empty] | 2021-08-09 |  | 2634.3 | 7202520 | 2021 |  |  |  | 4723290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:46 |  |  | 2021 | Order and Notification
75621 | Resource change | 35236990 | 120627591 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Approved | 08W | [7 empty] | 2021-08-20 |  | 0 | 5610020 | 2021 |  |  |  | 3498290 |  |  |  |  | 2022-06-30 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:45 |  |  | 2021 | Order and Notification
75620 | Resource change | 35237896 | 120647450 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 7111520 | 2021 |  |  |  | 4653290 |  |  |  |  | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:45 |  |  | 2021 | Order and Notification
75619 | Resource change | 35237895 | 120647408 | *CANC* WYANDOTTE 1103 -W3 PH3.7 | Approved | 08W | [7 empty] | 2021-08-16 |  | 80 | 5655520 | 2021 |  |  |  | 3533290 |  |  |  |  | 2022-06-01 | CNCL |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:44 |  |  | 2021 | Order and Notification
75618 | Resource change | 35237894 | 120647406 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 5974020 | 2021 |  |  |  | 3778290 |  |  |  |  | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:44 |  |  | 2021 | Order and Notification
75617 | Resource change | 35237893 | 120647405 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | Approved | 08W | [7 empty] | 2021-08-09 |  | 1927.3 | 3380520 | 2021 |  |  |  | 1783290 |  |  |  |  | 2022-06-01 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:43 |  |  | 2021 | Order and Notification
75616 | Resource change | 35237891 | 120647404 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Approved | 08W | [7 empty] | 2021-08-20 |  | 1191.6 | 4154020 | 2021 |  |  |  | 2378290 |  |  |  |  | 2022-06-01 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:43 |  |  | 2021 | Order and Notification
75615 | Resource change | 35237890 | 120647402 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Approved | 08W | [7 empty] | 2021-08-20 |  | 2835.1 | 5746520 | 2021 |  |  |  | 3603290 |  |  |  |  | 2022-06-01 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:42 |  |  | 2021 | Order and Notification
75614 | Resource change | 35237889 | 120647269 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 8294520 | 2021 |  |  |  | 5563290 |  |  |  |  | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:42 |  |  | 2021 | Order and Notification
75613 | Resource change | 35235673 | 120594874 | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Approved | 08W | [7 empty] | 2021-08-20 |  | 80 | 5064020 | 2021 |  |  |  | 3078290 |  |  |  |  | 2022-05-03 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:41 |  |  | 2021 | Order and Notification
75612 | Resource change | 35235320 | 120582839 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Approved | 08W | [7 empty] | 2021-07-27 |  | 812.3 | 6611020 | 2021 |  |  |  | 4268290 |  |  |  |  | 2022-03-01 | PEND |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:41 |  |  | 2021 | Order and Notification
75611 | Resource change | 35239522 | 120695185 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | Approved | 08W | [7 empty] | 2021-06-01 |  | 594.5 | 3198520 | 2021 |  |  |  | 1643290 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:40 |  |  | 2021 | Order and Notification
75610 | Resource change | 35240546 | 120723697 | FRRB - WYANDOTTE 1103 - W2 PH2.13 | Approved | 08W | [7 empty] | 2021-06-04 |  | 401.7 | 2470520 | 2021 |  |  |  | 1083290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:39 |  |  | 2021 | Order and Notification
75609 | Resource change | 35240545 | 120723696 | FRRB - WYANDOTTE 1103 - W2 PH2.12 | Approved | 08W | [7 empty] | 2021-06-04 |  | 652.9 | 2561702 | 2021 |  |  |  | 1153472.39 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:39 |  |  | 2021 | Order and Notification
75608 | Resource change | 35239937 | 120711267 | FRRB - WYANDOTTE 1103 - W2 PH2.11 | Approved | 08W | [7 empty] | 2021-06-04 |  | 1628.5 | 4746246 | 2021 |  |  |  | 2834016.47 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-04 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:34 |  |  | 2021 | Order and Notification
75607 | Resource change | 35239523 | 120695189 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Approved | 08W | [7 empty] | 2021-06-01 |  | 973.8 | 3198520 | 2021 |  |  |  | 1643290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-01 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:30 |  |  | 2021 | Order and Notification
75604 | Resource change | 35236986 | 120627456 | FRRB - KANAKA 1101 - K5 PH5.4 | Approved | 08W | [7 empty] | 2021-08-12 |  | 0 | 237500 | 2021 |  |  |  | 3344072 |  |  |  |  | 2022-05-07 | ADER |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:26 |  |  | 2021 | Order and Notification
75603 | Resource change | 35237020 | 120627702 | FRRB - KANAKA 1101 - K5 PH5.3 | Approved | 08W | [7 empty] | 2021-07-30 |  | 409.9 | 207149.33 | 2021 |  |  |  | 950000 |  |  |  |  | 2022-06-30 | PEND |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:25 |  |  | 2021 | Order and Notification
75602 | Resource change | 35236999 | 120627599 | FRRB - KANAKA 1101 - K5 PH5.2 | Approved | 08W | [7 empty] | 2021-06-28 |  | 204.6 | 101106 | 2021 |  |  |  | 332500 |  |  |  |  | 2022-06-30 | PEND |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:24 |  |  | 2021 | Order and Notification
75601 | Resource change | 35235704 | 120718423 | FRRB - KANAKA 1101 - K5 PH5.1 | Approved | 08W | [21 empty] | PEND | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:24 |  |  |  | Not in Work Plan
75600 | Resource change | 35240474 | 120718423 | FRRB - KANAKA 1101 - K4 PH4.9 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:16 |  |  | 2021 | Order and Notification
75599 | Resource change | 35240473 | 120718396 | FRRB - KANAKA 1101 - K4 PH4.8 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:15 |  |  | 2021 | Order and Notification
75598 | Resource change | 35240472 | 120718265 | FRRB - KANAKA 1101 - K4 PH4.7 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:15 |  |  | 2021 | Order and Notification
75597 | Resource change | 35240471 | 120718227 | *CANC*KANAKA 1101 - K4 PH4.6 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [16 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:14 |  |  | 2021 | Order and Notification
75596 | Resource change | 35240470 | 120718221 | FRRB - KANAKA 1101 - K4 PH4.5 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:13 |  |  | 2021 | Order and Notification
75595 | Resource change | 35240469 | 120718198 | FRRB - KANAKA 1101 - K4 PH4.4 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:11 |  |  | 2021 | Order and Notification
75594 | Resource change | 35240468 | 120718168 | *CANC*ANAKA 1101 - K4 PH4.3 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [16 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:09 |  |  | 2021 | Order and Notification
75593 | Resource change | 35240467 | 120718162 | *CANC*ANAKA 1101 - K4 PH4.2 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [16 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:09 |  |  | 2021 | Order and Notification
75592 | Resource change | 35236988 | 120627500 | *CANC*FRRB - KANAKA 1101 - K4 PH4.19 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | CNCL | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 16:08 |  |  | 2021 | Order and Notification
75591 | Resource change | 35240543 | 120720968 | FRRB - KANAKA 1101 - K4 PH 4.18 | Approved | 08W | [7 empty] | 2021-08-12 |  | 651.7 | 4451656 | 2021 |  |  |  | 2789491 |  |  |  |  | 2022-05-07 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:58 |  |  | 2021 | Order and Notification
75590 | Resource change | 35240542 | 120720967 | FRRB - KANAKA 1101 - K4 PH 4.19 | Approved | 08W | [7 empty] | 2021-08-12 |  | 704.4 | 3122627 | 2021 |  |  |  | 1767161 |  |  |  |  | 2022-05-07 | PEND |  | 2021-08-12 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:57 |  |  | 2021 | Order and Notification
75589 | Resource change | 35240541 | 120720949 | FRRB - KANAKA 1101 - K4 PH4.16 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:55 |  |  | 2021 | Order and Notification
75588 | Resource change | 35240540 | 120720944 | FRRB - KANAKA 1101 - K4 PH4.15 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:55 |  |  | 2021 | Order and Notification
75587 | Resource change | 35240479 | 120720922 | FRRB - KANAKA 1101 - K4 PH4.14 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:54 |  |  | 2021 | Order and Notification
75586 | Resource change | 35240478 | 120720899 | *CANC*ANAKA 1101 - K4 PH4.13 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | FICL | 2021-05-05 | [16 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:15 |  |  | 2021 | Order and Notification
75585 | Resource change | 35240477 | 120720896 | FRRB - KANAKA 1101 - K4 PH4.12 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:14 |  |  | 2021 | Order and Notification
75584 | Resource change | 35240476 | 120720854 | FRRB - KANAKA 1101 - K4 PH4.11 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:14 |  |  | 2021 | Order and Notification
75583 | Resource change | 35240475 | 120720749 | FRRB - KANAKA 1101 - K4 PH4.10 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:09 |  |  | 2021 | Order and Notification
75582 | Resource change | 35235703 | 120599073 | FRRB - KANAKA 1101 - K4 PH4.1 | Approved | 08W | [7 empty] | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [17 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:07 |  |  | 2021 | Order and Notification
75581 | Resource change | 35235702 | 120599072 | FRRB - KANAKA 1101 - K3 PH 3 | Approved | 08W | [7 empty] | 2021-08-13 |  | 80 | 950000 | 2021 |  |  |  | 6050630 |  |  |  |  | 2022-05-07 | UNSE |  | 2021-08-13 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 15:05 |  |  | 2021 | Order and Notification
75580 | Resource change | 35236989 | 120627501 | FRRB - KANAKA 1101 - K2 PH2.2 | Approved | 08W | [7 empty] | 2021-08-17 |  | 217.9 | 297255.39 | 2021 |  |  |  | 975189 |  |  |  |  | 2022-05-07 | PEND |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:55 |  |  | 2021 | Order and Notification
75579 | Resource change | 35235701 | 120599070 | FRRB - KANAKA 1101 - K2 PH2.1 | Approved | 08W | [7 empty] | 2021-06-28 |  | 154.8 | 475000 | 2021 |  |  |  | 207273 |  |  |  |  | 2022-05-07 | UNSC |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:54 |  |  | 2021 | Order and Notification
75578 | Resource change | 35236992 | 120627594 | FRRB - KANAKA 1101 - K1 PH 1.2 | Approved | 08W | [7 empty] | 2021-10-19 |  | 80 | 475000 | 2021 |  |  |  | 2988215 |  |  |  |  | 2022-06-30 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:53 |  |  | 2021 | Order and Notification
75576 | Resource change | 35236985 | 120627455 | FRRB - KANAKA 1101 - K1 PH 1.1 | Approved | 08W | [7 empty] | 2021-10-19 |  | 80 | 475000 | 2021 |  |  |  | 6688147 |  |  |  |  | 2022-05-07 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:51 |  |  | 2021 | Order and Notification
75575 | Resource change | 35242427 | 120753019 | FRRB - BIG BEND 1102 - B6 PH6.8 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 3851150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:48 |  |  | 2021 | Order and Notification
75574 | Resource change | 35242426 | 120753018 | FRRB - BIG BEND 1102 - B6 PH6.7 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 2906150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:48 |  |  | 2021 | Order and Notification
75573 | Resource change | 35242425 | 120753017 | FRRB - BIG BEND 1102 - B6 PH6.6 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 4901150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:46 |  |  | 2021 | Order and Notification
75572 | Resource change | 35242424 | 120753016 | FRRB - BIG BEND 1102 - B6 PH6.5 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 118750 | 2021 |  |  |  | 2381150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:44 |  |  | 2021 | Order and Notification
75571 | Resource change | 35242423 | 120753015 | FRRB - BIG BEND 1102 - B6 PH6.4 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 7343245 | 2021 |  |  |  | 4691150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:42 |  |  | 2021 | Order and Notification
75570 | Resource change | 35242422 | 120753013 | FRRB - BIG BEND 1102 - B6 PH6.3 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 5295819 | 2021 |  |  |  | 3116224 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:41 |  |  | 2021 | Order and Notification
75569 | Resource change | 35242421 | 120753012 | FRRB - BIG BEND 1102 - B6 PH6.2 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 5841745 | 2021 |  |  |  | 3536150 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:40 |  |  | 2021 | Order and Notification
75568 | Resource change | 35235679 | 120598623 | FRRB - BIG BEND 1102 - B6 PH6.1 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 5075596 | 2021 |  |  |  | 3088251 |  |  |  |  | 2022-05-07 | UNSE |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:39 |  |  | 2021 | Order and Notification
75567 | Resource change | 35233166 | 120541098 | FRRB - BIG BEND 1102 - B5 PH5.2 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 6979245 | 2021 |  |  |  | 4411150 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:34 |  |  | 2021 | Order and Notification
75566 | Resource change | 35242429 | 120753071 | FRRB - BIG BEND 1102 - B4 PH4.3 | Approved | 08W | [7 empty] | 2021-08-27 |  | 80 | 200000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:33 |  |  | 2021 | Order and Notification
75565 | Resource change | 35242428 | 120753070 | FRRB - BIG BEND 1102 - B4 PH4.2 | Approved | 08W | [7 empty] | 2021-08-27 |  | 0 | 200000 | 2021 |  |  |  | 3963125 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:31 |  |  | 2021 | Order and Notification
75564 | Resource change | 35235677 | 120598407 | FRRB - BIG BEND 1102 - B4 PH4.1 | Approved | 08W | [7 empty] | 2021-07-19 |  | 2092.8 | 14162767.73 | 2021 |  |  |  | 18298258 |  |  |  |  | 2022-05-07 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:28 |  |  | 2021 | Order and Notification
75563 | Resource change | 35242420 | 120751312 | FRRB - BIG BEND 1102 - B1 PH1.4 | Approved | 08W | [7 empty] | 2021-08-06 |  | 135.7 | 237500 | 2021 |  |  |  | 219294.16 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:27 |  |  | 2021 | Order and Notification
75562 | Resource change | 35241079 | 120751310 | FRRB - BIG BEND 1102 - B1 PH1.3 | Approved | 08W | [7 empty] | 2021-07-16 |  | 129.3 | 237500 | 2021 |  |  |  | 180007.89 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:24 |  |  | 2021 | Order and Notification
75561 | Resource change | 35241078 | 120751299 | FRRB - BIG BEND 1102 - B1 PH1.2 | Approved | 08W | [7 empty] | 2021-08-02 |  | 177.9 | 237500 | 2021 |  |  |  | 408885.89 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:23 |  |  | 2021 | Order and Notification
75560 | Resource change | 35235674 | 120596259 | FRRB - BIG BEND 1102 - B1 PH1.1 | Approved | 08W | [7 empty] | 2021-07-15 |  | 153.4 | 237500 | 2021 |  |  |  | 263588.3 |  |  |  |  | 2022-01-03 | PEND |  | 2021-07-15 | [15 empty] | Approved |  |  | 2021-04-30 12:36 |  |  | 2021-04-28 14:22 |  |  | 2021 | Order and Notification
75550 | Defer project | 35231624 | 120504163 | CWSP - HIGHLANDS 1102628 PH 1.6 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75556 | Defer project | 35231625 | 120504164 | CWSP - HIGHLANDS 1102628 PH 1.7 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75557 | Defer project | 35231621 | 120504138 | CWSP - HIGHLANDS 1102628 PH 1.3 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75552 | Defer project | 35231620 | 120504137 | CWSP - HIGHLANDS 1102628 PH 1.2 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75553 | Defer project | 35231622 | 120504139 | CWSP - HIGHLANDS 1102628 PH 1.4 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75558 | Defer project | 35231623 | 120504160 | CWSP - HIGHLANDS 1102628 PH 1.5 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75551 | Defer project | 35231626 | 120504165 | CWSP - HIGHLANDS 1102628 PH 1.8 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2021-08-25 | 2022-05-01 | 407.2 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75547 | Defer project | 35231627 | 120504167 | CWSP - HIGHLANDS 1102628 PH 1.9 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75554 | Defer project | 35231628 | 120504170 | CWSP - HIGHLANDS 1102628 PH 1.10 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75555 | Defer project | 35231629 | 120504175 | CWSP - HIGHLANDS 1102628 PH 1.11 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75548 | Defer project | 35231631 | 120504177 | CWSP - HIGHLANDS 1102628 PH 1.13 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2022-01-19 | 2022-05-01 | 80 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75549 | Defer project | 35219099 | 120141849 | CWSP - HIGHLANDS 1102628 PH 1.1 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2021-11-24 | 2022-05-01 | 80 | 73076 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-11-24 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75546 | Defer project | 35231630 | 120504176 | CWSP - HIGHLANDS 1102628 PH 1.12 | Approved | 08W | [6 empty] | Permit delays, BLM, CalTrans | 2021-09-20 | 2022-05-01 | 400.6 | 73077 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-09-20 | [7 empty] | Approved |  | Approved | Defer approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:16 |  |  | 2021-04-28 13:47 |  |  | 2022 | Order and Notification
75545 | Add project | 35222045 |  | SH - MIDDLTOWN 1103 - LR 830 PH4 | Approved | 08W | [6 empty] | Mileage forecasted for 2021 | 2021-08-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-28 13:39 |  |  |  | Not in Work Plan
75509 | Update work plan date | 35223062 | 120242676 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Denied | 08W | [6 empty] | Mileage forecasted in FY2022 | 2021-11-16 | 2022-09-20 | 80 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-16 | [7 empty] | Approved | [7 empty] | Denied | Project is currently planned for 2021, use "Defer project" request type to move to 2022 |  | 2021-04-30 20:55 |  |  | 2021-04-28 11:25 |  |  | 2022 | Order and Notification
75493 | Update work plan date | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Denied | 08W | [6 empty] | Mileage forecasted in FY 2022 | 2022-01-05 | 2022-11-30 | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [7 empty] | Approved | [7 empty] | Denied | Dupicate of Change ID 75490 |  | 2021-04-30 12:40 |  |  | 2021-04-28 08:50 |  |  | 2022 | Order and Notification
75490 | Update work plan date | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Denied | 08W | [6 empty] | Mileage forecasted in FY 2022 | 2022-01-05 | 1905-07-14 | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [7 empty] | Approved | [7 empty] | Denied | Project is currently planned for 2021, use "Defer project" request type to move to 2022 with a valid date |  | 2021-04-30 20:56 |  |  | 2021-04-28 08:30 |  |  | 2022 | Order and Notification
75467 | Add project | 35245146 |  | FRRB - KANAKA 1101 - K4 PH 4.11 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75479 | Add project | 35245142 |  | FRRB - KANAKA 1101 - K4 PH 4.7 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75470 | Add project | 35245149 |  | FRRB - KANAKA 1101 - K4 PH 4.14 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75473 | Add project | 35245152 |  | FRRB - KANAKA 1101 - K4 PH 4.17 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75474 | Add project | 35244697 |  | FRRB - KANAKA 1101 - K4 PH 4.2 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75465 | Add project | 35244696 |  | FRRB - KANAKA 1101 - K4 PH 4.1 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75477 | Add project | 35245140 |  | FRRB - KANAKA 1101 - K4 PH 4.5 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75475 | Add project | 35244698 |  | FRRB - KANAKA 1101 - K4 PH 4.3 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75472 | Add project | 35245151 |  | FRRB - KANAKA 1101 - K4 PH 4.16 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75471 | Add project | 35245150 |  | FRRB - KANAKA 1101 - K4 PH 4.15 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75466 | Add project | 35245145 |  | FRRB - KANAKA 1101 - K4 PH 4.10 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75468 | Add project | 35245147 |  | FRRB - KANAKA 1101 - K4 PH 4.12 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75469 | Add project | 35245148 |  | FRRB - KANAKA 1101 - K4 PH 4.13 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75476 | Add project | 35244699 |  | FRRB - KANAKA 1101 - K4 PH 4.4 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75481 | Add project | 35245144 |  | FRRB - KANAKA 1101 - K4 PH 4.9 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75478 | Add project | 35245141 |  | FRRB - KANAKA 1101 - K4 PH 4.6 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75480 | Add project | 35245143 |  | FRRB - KANAKA 1101 - K4 PH 4.8 | Approved | 08W | [6 empty] | the Project has been already added in th WP with different PM#. The scope of this job has been changed from UG to OH. This new PM# has been created with new Planning Order and new WBS#. The current PM# will be cancelled and also, there is a change request has been submitted to remove the current PM# from the WP. | 2021-07-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-27 16:16 |  |  |  | Not in Work Plan
75464 | Remove project | 35240467 | 120718162 | *CANC*ANAKA 1101 - K4 PH4.2 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [8 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75463 | Remove project | 35240468 | 120718168 | *CANC*ANAKA 1101 - K4 PH4.3 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [8 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75462 | Remove project | 35240478 | 120720899 | *CANC*ANAKA 1101 - K4 PH4.13 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | FICL | 2021-05-05 | [8 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75461 | Remove project | 35240476 | 120720854 | *CANC*KANAKA 1101 - K4 PH4.11 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75460 | Remove project | 35240471 | 120718227 | *CANC*KANAKA 1101 - K4 PH4.6 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | 2021-05-05 | [8 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75459 | Remove project | 35236988 | 120627500 | *CANC*FRRB - KANAKA 1101 - K4 PH4.19 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:53 |  |  | 2021 | Order and Notification
75458 | Remove project | 35240474 | 120718423 | *CANC*ANAKA 1101 - K4 PH4.9 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:52 |  |  | 2021 | Order and Notification
75457 | Remove project | 35240473 | 120718396 | *CANC*ANAKA 1101 - K4 PH4.8 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | FICL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:52 |  |  | 2021 | Order and Notification
75456 | Remove project | 35235703 | 120599073 | *CANC*KANAKA 1101 - K4 PH4.1 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:52 |  |  | 2021 | Order and Notification
75455 | Remove project | 35240477 | 120720896 | *CANC*NAKA 1101 - K4 PH4.12 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:52 |  |  | 2021 | Order and Notification
75454 | Remove project | 35240469 | 120718198 | *CANC*KANAKA 1101 - K4 PH4.4 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | PREC | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:52 |  |  | 2021 | Order and Notification
75453 | Remove project | 35240472 | 120718265 | *CANC*ANAKA 1101 - K4 PH4.7 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | FICL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75452 | Remove project | 35240479 | 120720922 | *CANC*NAKA 1101 - K4 PH4.14 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75451 | Remove project | 35240470 | 120718221 | *CANC* KANAKA 1101 - K4 PH4.5 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | FICL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75450 | Remove project | 35240540 | 120720944 | *CANC*ANAKA 1101 - K4 PH4.15 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | UNSE | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75449 | Remove project | 35240541 | 120720949 | *CANC*ANAKA 1101 - K4 PH4.16 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 | 50000 | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75448 | Remove project | 35240475 | 120720749 | *CANC*ANAKA 1101 - K4 PH4.10 | Approved | 08W | [6 empty] | Please remove this Order from the WP. The scope of this project has been changed from UG to OH. New PM# has been created with new Planning Order and new WBS as per EDRS# 2021-27792. The New PM# will be added to the WP. The curent PM# will be cancelled | 2021-07-01 |  | 80 |  | 2021 | [8 empty] | 2022-05-07 | CNCL | [9 empty] | Approved |  | Approved | Remove approved, work not scheduled |  | Approved |  |  | Approved |  |  | 2021-05-13 15:47 |  |  | 2021-04-27 15:51 |  |  | 2021 | Order and Notification
75446 | Budget change | 35234284 | 120539923 | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | Approved | 08W | [6 empty] | Per PM move this project to 2022. It is a new OH but dependent on the UG phases | 2021-12-22 | 2022-09-21 | 80 | 1 | 2021 | 2022 | 2022 |  |  |  |  | 950000 |  | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved |  |  | 2021-04-29 14:20 |  |  | 2021-04-27 15:39 |  |  | 2022 | Order and Notification
75421 | Budget change | 35231608 | 120504095 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W | [6 empty] | Project scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2022-07-25 |  | 310.3 | 209584 | 2021 | 2022 |  |  | 62873 |  | 62873 |  |  | 2021-12-31 | PEND |  | 2022-07-25 | [15 empty] | Approved |  |  | 2021-04-27 17:26 |  |  | 2021-04-27 11:59 |  |  | 2022 | Order and Notification
75419 | Budget change | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Approved | 08W | [6 empty] | Update to Match BC EDRS Routing 2021-09884 | 2021-04-19 |  | 1.1 | 7914493 | 2021 |  |  | 145083 | 5901787 |  | 5901787 |  |  | 2020-12-01 | UNSC |  | 2021-04-19 | [15 empty] | Approved |  |  | 2021-04-27 17:26 |  |  | 2021-04-27 10:37 |  |  | 2021 | Order and Notification
75418 | Budget change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W | [6 empty] | Update budget match BC EDRS routing 2021-09845 | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 |  | 6919958 |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | [15 empty] | Approved |  |  | 2021-04-27 17:26 |  |  | 2021-04-27 10:34 |  |  | 2021 | Order and Notification
75408 | Add project | 35113951 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [6 empty] | Safety-DSDD Pilot | 2021-06-01 |  |  |  | 2020 | [5 empty] | 900000 | 600000 |  |  | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-26 20:22 |  |  |  | Not in Work Plan
75407 | Add project | 35113950 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [6 empty] | Safety-DSDD Pilot | 2021-06-01 |  |  |  | 2020 | [5 empty] | 900000 | 600000 |  |  | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-26 20:22 |  |  |  | Not in Work Plan
75395 | Add project | 35219590 |  | CWSP - VACA DIXON 1105965390 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and not currently on the MPP workplan. Requesting to add to the 2021 workplan with place holder workplan date until schedule is built out. | 2021-12-31 |  |  |  | 2021 | [9 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-26 11:38 |  |  |  | Not in Work Plan
73624 | Defer project | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [6 empty] | Need to defer OH project to 2022. To be constructed after UG job 35192280 is built and requires design change | 2022-06-13 | 2022-06-27 | 1068.1 | 621258.86 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2022-06-13 | [7 empty] | Approved |  | Approved | Defer approved, [REDACTED], scheduling and PM notified |  | Approved |  |  | Approved |  |  | 2021-05-06 16:51 |  |  | 2021-04-22 15:37 |  |  | 2022 | Order and Notification
73614 | Add project | 35235700 |  | FRRB - WYANDOTTE 1103 - W4 PH4.11 | Approved | 08W | [6 empty] | adding this project as part of NCFR program | 2021-07-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-29 14:24 |  |  | 2021-04-22 13:58 |  |  |  | Not in Work Plan
73595 | Pull-in Project from Future Year | 35058273 |  | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Denied | 08W | [6 empty] | Construction completed in July. Date needed to be updated. |  | 2020-07-20 |  |  |  |  | 2020 | [7 empty] | FICL | 2020-07-20 | [10 empty] | Approved | Pull in project from future approved |  | Approved |  |  | Denied | Job order is not on MPP work plan. Therefore, it's not possible to pull this forward. |  | 2021-05-13 15:11 |  |  | 2021-04-22 12:23 |  |  |  | Not in Work Plan
72829 | Defer project | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Denied | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-01-13 | 2020-01-13 | 2123.7 | 5231108 | 2020 | 2021 | 2020 | 3150000 | 88800 |  |  |  |  | 2020-12-31 | FICL | 2021-02-25 | 2020-01-13 | [9 empty] | Approved | Defer approved |  | Denied | Not Approved. Please change Request Type to "Pull-in project from future year" |  | Denied | Defer project moves expected completion year to furture years. Please use "pull-in project from future year" request type |  | 2021-05-06 17:00 |  |  | 2021-04-21 14:32 |  |  | 2020 | Order and Notification
72830 | Defer project | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Denied | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-06-02 | 2020-06-02 | 3236.8 | 5062019 | 2020 | 2021 | 2020 | 4762461.3 | 59744 |  |  |  |  | 2020-12-31 | PREC | 2020-11-20 | [10 empty] | Approved | Defer approved |  | Denied | Not Approved. Please change Request Type to "Pull-in project from future year" |  | Denied | Defer project moves expected completion year to furture years. Please use "pull-in project from future year" request type |  | 2021-05-06 17:00 |  |  | 2021-04-21 14:28 |  |  | 2020 | Order and Notification
72828 | Defer project | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Denied | 08W | 220 Mile Plan | [5 empty] | All mileage completed in 2020. | 2020-06-01 | 2020-06-01 | 2558.5 | 2927538 | 2020 | 2021 | 2020 | 1900000 | 131088 |  |  |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [9 empty] | Approved | Defer approved |  | Denied | Not Approved. Please change Request Type to "Pull-in project from future year" |  | Denied | Defer project moves expected completion year to furture years. Please use "pull-in project from future year" request type |  | 2021-05-06 17:00 |  |  | 2021-04-21 14:28 |  |  | 2020 | Order and Notification
72570 | Add project | 35235673 |  | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Approved | 08W | [6 empty] | Please change the Order# 35242553 to 35235673 as this is the correct order#. where the planning Engineer create 2 order numbers for this job. Please remove the first one from the WP. This job part of NCFR program | 2021-07-23 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-25 09:36 |  |  | 2021-04-21 09:05 |  |  |  | Not in Work Plan
71873 | Add project | 35219588 |  | CWSP - MARIPOSA 2102440236 PH1.3 | Approved | 08W | [6 empty] | Project Scope was recently approved by the WFGC to be added to the workplan. WP Date is currently a place holder date and will be superceded once the project is a assigned and schedule is completed. As of 4/20/21 not on current MPP Workplan. | 2021-08-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-22 16:24 |  |  | 2021-04-20 11:54 |  |  |  | Not in Work Plan
71872 | Add project | 35219587 |  | CWSP - MARIPOSA 2102440236 PH1.2 | Approved | 08W | [6 empty] | Project Scope was recently approved by the WFGC to be added to the workplan. WP Date is currently a place holder date and will be superceded once the project is a assigned and schedule is completed. As of 4/20/21 not on current MPP Workplan. | 2021-08-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-22 16:24 |  |  | 2021-04-20 11:54 |  |  |  | Not in Work Plan
71871 | Add project | 35219267 |  | CWSP - MARIPOSA 2102440236 PH1.1 | Approved | 08W | [6 empty] | Project Scope was recently approved by the WFGC to be added to the workplan. WP Date is currently a place holder date and will be superceded once the project is a assigned and schedule is completed. As of 4/20/21 not on current MPP Workplan. | 2021-08-31 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-22 16:24 |  |  | 2021-04-20 11:54 |  |  |  | Not in Work Plan
71864 | Budget change | 35242553 | 120762946 | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Approved | 08W | [6 empty] | requesting budget to 2021 to allign with BC (expected case figure) | 2021-07-20 |  | 0 |  | 2021 |  |  |  | 3078290 | 0 | 3078290 | 0 | 0 | 2022-06-30 | UNSE | [17 empty] | Approved |  |  | 2021-04-22 16:13 |  |  | 2021-04-20 08:03 |  |  | 2021 | Order and Notification
71556 | Budget change | 35226240 | 120431332 | CWSP - MARIPOSA 210197142 PH 3 | Approved | 08W | [6 empty] | 08W Wildfire Hardening | 2021-07-21 |  | 1336.8 | 655862.69 | 2021 |  |  |  | 1365471 |  | 1365471 |  |  | 2021-12-31 | PEND |  | 2021-07-21 | [15 empty] | Approved |  |  | 2021-04-22 16:13 |  |  | 2021-04-19 07:40 |  |  | 2021 | Order and Notification
71526 | Add project | 35236999 |  | FRRB - KANAKA 1101 - K5 PH5.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71529 | Add project | 35241075 |  | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71513 | Add project | 35235670 |  | FRRB - WYANDOTTE 1103 W5 PH5.1 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71517 | Add project | 35235701 |  | FRRB - KANAKA 1101 - K2 PH2.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71527 | Add project | 35237020 |  | FRRB - KANAKA 1101 - K5 PH5.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71528 | Add project | 35237021 |  | FRRB - WYANDOTTE 1103 W7 PH7.4 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71534 | Add project | 35242420 |  | FRRB - BIG BEND 1102 - B1 PH1.4 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71519 | Add project | 35235704 |  | FRRB - KANAKA 1101 - K5 PH5.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71525 | Add project | 35236997 |  | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71522 | Add project | 35236986 |  | FRRB - KANAKA 1101 - K5 PH5.4 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71533 | Add project | 35241079 |  | FRRB - BIG BEND 1102 - B1 PH1.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71520 | Add project | 35236984 |  | FRRB - WYANDOTTE 1103 - W5 PH 5.5 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71531 | Add project | 35241077 |  | FRRB - WYANDOTTE 1103 W5 PH5.4 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71532 | Add project | 35241078 |  | FRRB - BIG BEND 1102 - B1 PH1.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71521 | Add project | 35236985 |  | FRRB - KANAKA 1101 - K1 PH 1.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71515 | Add project | 35235674 |  | FRRB - BIG BEND 1102 - B1 PH1.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71524 | Add project | 35236992 |  | FRRB - KANAKA 1101 - K1 PH 1.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71530 | Add project | 35241076 |  | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71514 | Add project | 35235672 |  | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71516 | Add project | 35235675 |  | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71518 | Add project | 35235702 |  | FRRB - KANAKA 1101 - K3 PH 3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71523 | Add project | 35236989 |  | FRRB - KANAKA 1101 - K2 PH2.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR Program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 20:45 |  |  |  | Not in Work Plan
71511 | Resource change | 35161152 | 118677953 | OCT2019 BRICEBURG FIRE REBUILD | Approved | 08W | [7 empty] | 2021-01-11 |  | 200 | 1676000 | 2021 |  |  | 375186 | 1400000 | [5 empty] | MAPP | 2021-05-20 | 2021-01-11 | [15 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 16:17 |  |  | 2021 | Order and Notification
71282 | Add project | 35236983 |  | FRRB - BIG BEND 1102 - B5 PH5.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71253 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71283 | Add project | 35235679 |  | FRRB - BIG BEND 1102 - B6 PH6.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71254 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71284 | Add project | 35242421 |  | FRRB - BIG BEND 1102 - B6 PH6.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71255 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71285 | Add project | 35242422 |  | FRRB - BIG BEND 1102 - B6 PH6.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71256 |  | 2021-04-25 09:43 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71286 | Add project | 35242423 |  | FRRB - BIG BEND 1102 - B6 PH6.4 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71257 |  | 2021-04-25 09:43 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71287 | Add project | 35242424 |  | FRRB - BIG BEND 1102 - B6 PH6.5 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71258 |  | 2021-04-25 09:43 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71288 | Add project | 35242425 |  | FRRB - BIG BEND 1102 - B6 PH6.6 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71259 |  | 2021-04-25 09:43 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71289 | Add project | 35242426 |  | FRRB - BIG BEND 1102 - B6 PH6.7 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71260 |  | 2021-04-25 09:44 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71290 | Add project | 35242427 |  | FRRB - BIG BEND 1102 - B6 PH6.8 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71261 |  | 2021-04-25 09:44 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71277 | Add project | 35235677 |  | FRRB - BIG BEND 1102 - B4 PH4.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71248 |  | 2021-04-25 09:41 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71278 | Add project | 35242428 |  | FRRB - BIG BEND 1102 - B4 PH4.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71249 |  | 2021-04-25 09:41 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71279 | Add project | 35242429 |  | FRRB - BIG BEND 1102 - B4 PH4.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71250 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71280 | Add project | 35233166 |  | FRRB - BIG BEND 1102 - B5 PH5.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71251 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71281 | Add project | 35235678 |  | FRRB - BIG BEND 1102 - B5 PH5.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved | Duplicate of change ID 71252 |  | 2021-04-25 09:42 |  |  | 2021-04-15 15:04 |  |  |  | Not in Work Plan
71275 | Budget change | 35234386 | 120564078 | CWSP - OREGON TRAIL 110335002 PH3.9 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 100000 | 2021 |  |  |  | 1634000 |  | 1634000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:59 |  |  | 2021 | Order and Notification
71262 | Budget change | 35234385 | 120564076 | CWSP - OREGON TRAIL 110335002 PH3.8 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 100000 | 2021 |  |  |  | 1273000 | 0 | 1273000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:59 |  |  | 2021 | Order and Notification
71271 | Defer project | 35234383 | 120564074 | CWSP - OREGON TRAIL 110335002 PH3.6 | Approved | 08W | [6 empty] | Underground, not in estimating yet | 2022-05-02 | 2022-05-02 | 0 | 150000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 3700000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:57 |  |  | 2022 | Order and Notification
71272 | Budget change | 35234384 | 120564075 | CWSP - OREGON TRAIL 110335002 PH3.7 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 150000 | 0 | 150000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:55 |  |  | 2021 | Order and Notification
71257 | Add project | 35242423 |  | FRRB - BIG BEND 1102 - B6 PH6.4 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71258 | Add project | 35242424 |  | FRRB - BIG BEND 1102 - B6 PH6.5 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71259 | Add project | 35242425 |  | FRRB - BIG BEND 1102 - B6 PH6.6 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71256 | Add project | 35242422 |  | FRRB - BIG BEND 1102 - B6 PH6.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71255 | Add project | 35242421 |  | FRRB - BIG BEND 1102 - B6 PH6.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71254 | Add project | 35235679 |  | FRRB - BIG BEND 1102 - B6 PH6.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71260 | Add project | 35242426 |  | FRRB - BIG BEND 1102 - B6 PH6.7 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71261 | Add project | 35242427 |  | FRRB - BIG BEND 1102 - B6 PH6.8 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:50 |  |  |  | Not in Work Plan
71250 | Add project | 35242429 |  | FRRB - BIG BEND 1102 - B4 PH4.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:48 |  |  |  | Not in Work Plan
71251 | Add project | 35233166 |  | FRRB - BIG BEND 1102 - B5 PH5.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:48 |  |  |  | Not in Work Plan
71253 | Add project | 35236983 |  | FRRB - BIG BEND 1102 - B5 PH5.3 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:48 |  |  |  | Not in Work Plan
71252 | Add project | 35235678 |  | FRRB - BIG BEND 1102 - B5 PH5.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:48 |  |  |  | Not in Work Plan
71248 | Add project | 35235677 |  | FRRB - BIG BEND 1102 - B4 PH4.1 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:44 |  |  |  | Not in Work Plan
71249 | Add project | 35242428 |  | FRRB - BIG BEND 1102 - B4 PH4.2 | Approved | 08W | [6 empty] | adding this project to 2021 WP as part of NCFR program | 2021-06-28 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-21 15:32 |  |  | 2021-04-15 14:44 |  |  |  | Not in Work Plan
71276 | Defer project | 35234380 | 120564073 | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [6 empty] | Project size, not in estimating yet | 2022-05-02 | 2022-05-02 | 0 | 150000 | 2021 | 2022 | 2022 |  | 3500000 | 0 | 500000 | 3756000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:42 |  |  | 2022 | Order and Notification
71267 | Budget change | 35233958 | 120564071 | CWSP - OREGON TRAIL 110335002 PH3.4 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 400000 | 0 | 400000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:39 |  |  | 2021 | Order and Notification
71273 | Budget change | 35233956 | 120564070 | CWSP - OREGON TRAIL 110335002 PH3.3 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 475000 | 0 | 475000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:37 |  |  | 2021 | Order and Notification
71265 | Budget change | 35233954 | 120564059 | CWSP - OREGON TRAIL 110335002 PH3.2 | Approved | 08W | [6 empty] | Set baseline budget | 2021-12-31 |  | 0 | 75000 | 2021 |  |  |  | 400000 | 0 | 400000 | 0 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:36 |  |  | 2021 | Order and Notification
71274 | Budget change | 35233951 | 120564184 | CWSP - OREGON TRAIL 110335002 PH1.6 | Approved | 08W | [6 empty] | Set baseline budget and split project costs between years | 2022-06-01 |  | 0 |  | 2021 | 2022 |  |  | 428000 | 0 | 1428000 | 1555000 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:33 |  |  | 2022 | Order and Notification
71268 | Defer project | 35233950 | 120564183 | CWSP - OREGON TRAIL 110335002 PH1.5 | Approved | 08W | [6 empty] | Cal Trans, underground, project size, not in estimating | 2022-05-02 | 2022-05-02 | 0 | 175000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 9125000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:24 |  |  | 2022 | Order and Notification
71269 | Defer project | 35233949 | 120564182 | CWSP - OREGON TRAIL 110335002 PH1.4 | Approved | 08W | [6 empty] | Project size, not in estimating yet, set baseline budget | 2022-05-02 | 2022-05-02 | 0 | 125000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 3262000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:21 |  |  | 2022 | Order and Notification
71270 | Defer project | 35233948 | 120564181 | CWSP - OREGON TRAIL 110335002 PH1.3 | Approved | 08W | [6 empty] | Cal Trans, underground, project size, not in estimating yet | 2022-05-02 | 2022-05-02 | 0 | 175000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 8565000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:17 |  |  | 2022 | Order and Notification
71263 | Defer project | 35225827 | 120426404 | CWSP - OREGON TRAIL 110335002 PH3.1 | Approved | 08W | [6 empty] | Cal Trans, underground, not in estimating yet | 2022-05-02 | 2022-05-02 | 0 | 150000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 2475000 | 0 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:17 |  |  | 2022 | Order and Notification
71266 | Budget change | 35233947 | 120564156 | CWSP - OREGON TRAIL 110335002 PH1.2 | Approved | 08W | [6 empty] | Set baseline budget and split project costs between years | 2022-06-01 |  | 0 | 125000 | 2021 | 2022 |  |  | 500000 | 0 | 1600000 | 1916000 | 0 | 2021-12-31 | UNSE | [17 empty] | Approved |  |  | 2021-04-16 14:28 |  |  | 2021-04-15 14:15 |  |  | 2022 | Order and Notification
71264 | Defer project | 35219289 | 120142359 | CWSP - OREGON TRAIL 110335002 PH1.1 | Approved | 08W | [6 empty] | Cal Trans, underground, project size, not in estimating yet | 2022-05-02 | 2022-05-02 | 0 | 225000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 8360000 | 6365000 | 2021-12-31 | UNSE | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approved; subcategory of 2022 removed |  | 2021-04-25 09:23 |  |  | 2021-04-15 14:10 |  |  | 2022 | Order and Notification
71223 | Resource change | 31361965 | 113751296 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [7 empty] | 2021-03-16 |  | 660.1 | 1245293 | 2021 |  |  | 287153 | 273723 |  |  |  |  | 2019-12-27 | FICL | 2021-04-24 | 2021-03-16 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-15 12:21 |  |  | 2021 | Order and Notification
71222 | Resource change | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [7 empty] | 2021-10-01 |  | 428 | 1115282 | 2021 |  |  | 150000 | 755085 |  |  |  |  | 2018-12-28 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-15 12:21 |  |  | 2021 | Order and Notification
69813 | Defer project | 35233996 | 120563933 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Approved | 08W | [6 empty] | Underground project | 2022-09-13 | 2022-07-01 | 0 | 315000 | 2021 | 2022 | 2022 |  | 255000 |  | 50000 | 2149605.4 |  | 2021-12-31 | UNSE |  | 2022-09-13 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-22 16:14 |  |  | 2021-04-15 08:41 |  |  | 2022 | Order and Notification
69812 | Defer project | 35233995 | 120563909 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Approved | 08W | [6 empty] | Underground project | 2022-09-13 | 2022-07-01 | 0 | 315000 | 2021 | 2022 | 2022 |  | 219000 |  | 50000 | 1513807 |  | 2021-12-31 | UNSE |  | 2022-09-13 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-22 16:14 |  |  | 2021-04-15 08:39 |  |  | 2022 | Order and Notification
69811 | Defer project | 35224377 | 120360607 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Approved | 08W | [6 empty] | Underground project | 2022-10-26 | 2022-07-01 | 0 | 320000 | 2021 | 2022 | 2022 |  | 179000 |  | 56547 | 1513807 |  | 2021-12-31 | UNSE |  | 2022-10-26 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-22 16:14 |  |  | 2021-04-15 08:28 |  |  | 2022 | Order and Notification
69609 | Add project | 35242553 |  | FRRB - WYANDOTTE 1103 - W3 PH3.10 | Approved | 08W | [6 empty] | adding project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-14 14:01 |  |  |  | Not in Work Plan
69608 | Defer project | 35236439 | 120617881 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Approved | 08W | [6 empty] | Defer project to 2022. UG project that requires surveying and base map | 2021-12-22 | 2022-12-31 | 80 | 67857 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-22 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-22 16:14 |  |  | 2021-04-14 13:36 |  |  | 2022 | Order and Notification
69607 | Defer project | 35236660 | 120617882 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Approved | 08W | [6 empty] | Defer project to 2022. UG project that requires surveying and base map. | 2021-12-22 | 2022-12-31 | 80 | 67857 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-22 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-22 16:14 |  |  | 2021-04-14 13:36 |  |  | 2022 | Order and Notification
69582 | Update work plan date | 35219591 | 120173637 | CWSP - OLETA 1101754718 PH1.1 | Denied | 08W | [6 empty] | Per PM - Move project into 2022 Work Plan Year | 2022-05-11 | 2022-10-07 | 240 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-05-11 | [7 empty] | Approved | [7 empty] | Denied | Denied, duplicate of change ID 69581, Change ID 69581 updated to "Defer project" request type and approved |  | 2021-04-16 14:54 |  |  | 2021-04-14 09:55 |  |  | 2022 | Order and Notification
69581 | Defer project | 35219591 | 120173637 | CWSP - OLETA 1101754718 PH1.1 | Approved | 08W | [6 empty] | Per PM - Move project into 2022 Work Plan Year | 2022-05-11 | 2022-10-07 | 240 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-05-11 | [7 empty] | Approved | [7 empty] | Approved | Change request type to Defer project and approved |  | 2021-04-17 16:18 |  |  | 2021-04-14 09:52 |  |  | 2022 | Order and Notification
69588 | Budget change | 35116804 | 117605269 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Pending Windy Tree PO submitted post construction/project close out | 2020-04-28 |  | 2072.2 | 1868187 | 2020 |  |  | 1659078.9 | 37382 |  | 18691 |  |  | 2020-12-31 | FICL | 2020-08-22 | [16 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-14 08:41 |  |  | 2020 | Order and Notification
69598 | Budget change | 35116804 | 117605269 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Pending Windy Tree PO submitted post construction/project close out | 2020-04-28 |  | 2072.2 | 1868187 | 2020 |  |  | 1659078.9 | 37382 |  | 18691 |  |  | 2020-12-31 | FICL | 2020-08-22 | [16 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-14 08:41 |  |  | 2020 | Order and Notification
69589 | Budget change | 35052820 | 114580704 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Post construction veg work required, [REDACTED] line support required | 2020-04-24 |  | 4109.5 | 3585097 | 2020 |  |  | 3516246 | 272868 |  | 136434 |  |  | 2020-12-31 | DOCC | 2020-08-04 | 2020-04-24 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-14 08:22 |  |  | 2020 | Order and Notification
69599 | Budget change | 35052820 | 114580704 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Post construction veg work required, [REDACTED] line support required | 2020-04-24 |  | 4109.5 | 3585097 | 2020 |  |  | 3516246 | 272868 |  | 136434 |  |  | 2020-12-31 | DOCC | 2020-08-04 | 2020-04-24 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-14 08:22 |  |  | 2020 | Order and Notification
69570 | Resource change | 35219273 | 120142173 | CWSP - VOLTA 110149742 | Approved | 08W | [7 empty] | 2021-09-17 |  | 2734.5 | 633229.22 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-09-17 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2022 | Order and Notification
69571 | Resource change | 35226627 | 120445375 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W | [7 empty] | 2021-07-26 |  | 111.1 | 150000 | 2021 |  |  |  | 551000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2021 | Order and Notification
69575 | Resource change | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W | [7 empty] | 2022-05-02 |  | 110.1 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-05-02 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2022 | Order and Notification
69572 | Resource change | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W | [7 empty] | 2021-10-14 |  | 111.1 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2022 | Order and Notification
69573 | Resource change | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W | [7 empty] | 2021-10-14 |  | 111.1 | 200000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2022 | Order and Notification
69574 | Resource change | 35226631 | 120445423 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W | [7 empty] | 2021-07-27 |  | 2283.6 | 765014.63 | 2021 |  |  |  | 2926000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2021 | Order and Notification
69569 | Resource change | 35226630 | 120445421 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W | [7 empty] | 2021-08-10 |  | 2407.9 | 497898.74 | 2021 |  |  |  | 2736000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-10 | [15 empty] | Approved |  |  | 2021-04-15 15:22 |  |  | 2021-04-13 19:27 |  |  | 2021 | Order and Notification
69554 | Budget change | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Approved | 08W | [6 empty] | BC approved for $5,901,787 (High Case $7,914,493) | 2021-04-19 |  | 1.1 | 7914493 | 2021 |  |  | 145083 | 5901787 | 145083 | 5656704 | 100000 |  | 2020-12-01 | UNSC |  | 2021-04-19 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 16:16 |  |  | 2021 | Order and Notification
69553 | Budget change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W | [6 empty] | BC approved for $6,919,958 (High Case $8,431,936) | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 | 159888 | 6660070 | 100000 |  | 2020-12-01 | UNSC |  | 2021-04-26 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 16:14 |  |  | 2021 | Order and Notification
69555 | Budget change | 31207090 | 111104615 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 | Approved | 08W | 220 Mile Plan | [5 empty] | DOCC Project recently assigned to J1E1 with insufficient funding. Leadership requeseted to close out. Requesting $ to reauth and then closeout. | 2020-06-28 |  | 3938.6 | 3537680 | 2020 |  |  | 3442297 | 100000 | 3442297 | 100000 | 0 | 0 | 2017-12-31 | FICL | 2020-05-08 | [16 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 16:12 |  |  | 2020 | Order and Notification
68661 | Budget change | 35236990 | 120627591 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 0 | 5610020 | 2021 |  |  |  | 3498290 | 0 | 3498290 | 0 | 0 | 2022-06-30 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:16 |  |  | 2021 | Order and Notification
68663 | Budget change | 35237896 | 120647450 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 80 | 7111520 | 2021 |  |  |  | 4653290 | 0 | 4653290 | 0 | 0 | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:14 |  |  | 2021 | Order and Notification
68667 | Budget change | 35237895 | 120647408 | *CANC* WYANDOTTE 1103 -W3 PH3.7 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-16 |  | 80 | 5655520 | 2021 |  |  |  | 3533290 | 0 | 3533290 | 0 | 0 | 2022-06-01 | CNCL |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:12 |  |  | 2021 | Order and Notification
68666 | Budget change | 35237894 | 120647406 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 80 | 5974020 | 2021 |  |  |  | 3778290 | 0 | 3778290 | 0 | 0 | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:10 |  |  | 2021 | Order and Notification
68665 | Budget change | 35237893 | 120647405 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-09 |  | 1927.3 | 3380520 | 2021 |  |  |  | 1783290 | 0 | 1783290 | 0 | 0 | 2022-06-01 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:08 |  |  | 2021 | Order and Notification
68662 | Budget change | 35237891 | 120647404 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 1191.6 | 4154020 | 2021 |  |  |  | 2378290 | 0 | 2378290 | 0 | 0 | 2022-06-01 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:04 |  |  | 2021 | Order and Notification
68660 | Budget change | 35237890 | 120647402 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 2835.1 | 5746520 | 2021 |  |  |  | 3603290 | 0 | 3603290 | 0 | 0 | 2022-06-01 | PEND |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 09:02 |  |  | 2021 | Order and Notification
68664 | Budget change | 35237889 | 120647269 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-08-20 |  | 80 | 8294520 | 2021 |  |  |  | 5563290 | 0 | 5563290 | 0 | 0 | 2022-06-01 | ESTS |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 08:59 |  |  | 2021 | Order and Notification
68668 | Budget change | 35235320 | 120582839 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Approved | 08W | [6 empty] | Requesting to adjust 2021 Budget to allign with BC approval (Expected Case Figure) | 2021-07-27 |  | 812.3 | 6611020 | 2021 |  |  |  | 4268290 | 0 | 4268290 | 0 | 0 | 2022-03-01 | PEND |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-04-15 15:38 |  |  | 2021-04-13 08:56 |  |  | 2021 | Order and Notification
67042 | Add project | 35228775 |  | PSPS - DUNBAR 1101 - OAKMONT PH 3 | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67040 | Add project | 35223063 |  | PSPS - DUNBAR 1101 - OAKMONT | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67041 | Add project | 35228774 |  | PSPS - DUNBAR 1101 - OAKMONT PH 2 | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67045 | Add project | 35222236 |  | MARIPOSA 2101 - #531 SLAUGHTER HOUSE | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67044 | Add project | 35234526 |  | PSPS - MARTELL 1101 - SUTTER CREEK PH1.3 | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67043 | Add project | 35234284 |  | PSPS - MARTELL 1101 - SUTTER CREEK PH1.2 | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:04 |  |  |  | Not in Work Plan
67039 | Add project | 35223038 |  | PSPS - MARTELL 1101 - SUTTER CREEK PH1.1 | Approved | 08W | [6 empty] | Requesting projects to be added to MPP Workplan that were recently approved by the WFGC. Workplan date is placeholder and will be superceded with p6 schedule dates. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-15 15:54 |  |  | 2021-04-12 12:03 |  |  |  | Not in Work Plan
67038 | Budget change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Project slated for 2021 const. | 2021-04-15 |  | 2558 | 4624169 | 2020 | 2021 |  | 103947 | 3135435 | 103947 | 3135435 | 0 | 0 | 2020-12-25 | CONS |  | 2021-04-15 | [15 empty] | Approved |  |  | 2021-04-12 12:52 |  |  | 2021-04-12 11:59 |  |  | 2021 | Order and Notification
66750 | Resource change | 35114051 | 117502234 | OCGC PINE GROVE 1102 - LR1222 - PH | Denied | 08W | [6 empty] | Resource Discrepancy - Assigned to [REDACTED]. Need to updated MPP WP with the correct Resource | 2020-10-02 |  | 4307.5 | 5342998 | 2021 |  |  | 3949678 | 2575321 |  |  |  |  | 2019-12-31 | MAPP | 2021-05-26 | 2020-10-02 | [15 empty] | Denied | Requested resource matches the resource on the work plan |  | 2021-04-12 12:51 |  |  | 2021-04-09 16:00 |  |  | 2021 | Order and Notification
66667 | Defer project | 35226900 | 120450946 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Approved | 08W | [6 empty] | Push phase due to other phase having DSDD | 2022-07-13 | 2022-05-01 | 80 | 247500 | 2021 | 2022 | 2022 |  | 27531 |  |  |  |  | 2021-12-31 | ADER |  | 2022-07-13 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-08 15:33 |  |  | 2022 | Order and Notification
66668 | Defer project | 35226799 | 120450944 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [6 empty] | Phase needs to push due to larger phases having DSDD. | 2022-07-11 | 2022-05-01 | 203 | 71683.95 | 2021 | 2021 | 2022 |  | 371000 |  |  |  |  | 2021-12-31 | PEND |  | 2022-07-11 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-08 15:32 |  |  | 2021 | Order and Notification
66665 | Defer project | 35226798 | 120450942 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Approved | 08W | [6 empty] | Due to DSDD. Push project to 2022 | 2022-07-01 | 2022-05-01 | 80 | 247500 | 2021 | 2022 | 2022 |  | 63441 |  |  |  |  | 2021-12-31 | ADER |  | 2022-07-01 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-08 14:42 |  |  | 2022 | Order and Notification
66664 | Budget change | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W | [6 empty] | requesting budget for 2021 and 2022 | 2021-10-14 |  | 111.1 | 200000 | 2021 | 2022 |  |  | 500000 | 0 | 500000 | 5555000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-04-08 14:34 |  |  | 2021-04-08 14:34 |  |  | 2022 | Order and Notification
66656 | Budget change | 35233957 | 120564051 | CWSP - OREGON TRAIL 110335002 PH2.5 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-10-22 |  | 80 | 125000 | 2022 |  |  |  | 125000 | 0 | 125000 | 275000 | 0 | 2021-12-31 | UNSE |  | 2021-10-22 | [15 empty] | Approved |  |  | 2021-04-08 14:21 |  |  | 2021-04-08 14:21 |  |  | 2022 | Order and Notification
66662 | Budget change | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-10-14 |  | 111.1 | 150000 | 2021 | 2022 |  |  | 500000 | 0 | 500000 | 2370000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-04-08 14:21 |  |  | 2021-04-08 14:21 |  |  | 2022 | Order and Notification
66661 | Budget change | 35233955 | 120564050 | CWSP - OREGON TRAIL 110335002 PH2.4 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-10-19 |  | 80 | 150000 | 2022 |  |  |  | 500000 | 0 | 500000 | 1700000 | 0 | 2021-12-31 | UNSE |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-04-08 14:20 |  |  | 2021-04-08 14:20 |  |  | 2022 | Order and Notification
66657 | Budget change | 35226700 | 14272795 | CWSP - WYANDOTTE 110932586 PH 1.2 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2022-06-13 |  |  |  | 2021 | 2022 |  |  |  | 0 | 500000 | 1495265 | 0 |  | ESTS | [17 empty] | Approved |  |  | 2021-04-08 14:19 |  |  | 2021-04-08 14:19 |  |  |  | Not in Work Plan
66660 | Budget change | 35223030 | 120242544 | PSPS - BANGOR 1101 CB - MICROGRID | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-10-19 |  | 80 | 950000 | 2021 | 2022 |  |  | 500000 | 0 | 500000 | 1497108 | 0 | 2021-12-31 | ESTS |  | 2021-10-19 | [15 empty] | Approved |  |  | 2021-04-08 14:19 |  |  | 2021-04-08 14:19 |  |  | 2022 | Order and Notification
66659 | Budget change | 35233953 | 120563959 | CWSP - OREGON TRAIL 110335002 PH2.3 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-11-24 |  | 80 | 150000 | 2022 |  |  |  | 500000 | 0 | 500000 | 2860000 | 0 | 2021-12-31 | UNSE |  | 2021-11-24 | [15 empty] | Approved |  |  | 2021-04-08 14:17 |  |  | 2021-04-08 14:17 |  |  | 2022 | Order and Notification
66658 | Budget change | 35223039 | 120242691 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2021-09-15 |  | 80 | 950000 | 2021 | 2022 |  |  | 500000 | 0 | 500000 | 5905000 | 0 | 2021-12-31 | ESTS |  | 2021-09-15 | [15 empty] | Approved |  |  | 2021-04-08 14:15 |  |  | 2021-04-08 14:15 |  |  | 2022 | Order and Notification
66655 | Budget change | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W | [6 empty] | Requesting budget for 2021 and 2022 | 2022-05-02 |  | 110.1 | 150000 | 2021 | 2022 |  |  | 500000 | 0 | 500000 | 550000 | 0 | 2021-12-31 | ESTS |  | 2022-05-02 | [15 empty] | Approved |  |  | 2021-04-08 14:11 |  |  | 2021-04-08 14:11 |  |  | 2022 | Order and Notification
66635 | Add project | 35238567 |  | CWSP - MARIPOSA 210197142 PH 1.4 | Approved | 08W | [6 empty] | Fire Hardening Project | 2022-01-01 |  |  |  | 2022 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 12:33 |  |  |  | Not in Work Plan
66391 | Defer project | 35223032 | 120242546 | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Approved | 08W | [6 empty] | Underground project. | 2022-04-06 | 2022-10-06 | 83 | 500000 | 2021 | 2022 | 2022 |  | 136000 |  | 59980.99 | 1320000 |  | 2021-12-31 | ESTS |  | 2022-04-06 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved | Revised "Updated Work Plan Date" to 2022 |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-08 10:20 |  |  | 2022 | Order and Notification
66390 | Defer project | 35219543 | 120135657 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Approved | 08W | [6 empty] | Underground project. | 2022-01-13 | 2022-10-06 | 80 | 500000 | 2021 | 2022 | 2022 |  | 177000 |  | 55724.43 | 730000 |  | 2021-12-31 | ESTS |  | 2022-01-13 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved | Revised "Updated Work Plan Date" to 2022 |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-08 10:12 |  |  | 2022 | Order and Notification
66379 | Add project | 35236995 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.10 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66378 | Add project | 35236993 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.9 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66377 | Add project | 35236991 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.8 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66376 | Add project | 35239099 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66375 | Add project | 35239098 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66374 | Add project | 35239097 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66373 | Add project | 35239096 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66372 | Add project | 35239095 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66371 | Add project | 35235671 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66370 | Add project | 35235669 |  | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | Approved | 08W | [6 empty] | Adding this project to 2021 NCFR program | 2021-07-20 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-09 09:15 |  |  | 2021-04-08 09:56 |  |  |  | Not in Work Plan
66322 | Resource change | 35235676 | 120598345 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Approved | 08W | [7 empty] | 2021-08-03 |  | 80 | 13666223 | 2021 |  |  |  | 9498763 |  |  |  |  | 2022-05-07 | ESTS |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:23 |  |  | 2021 | Order and Notification
66321 | Resource change | 35235139 | 120582960 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Approved | 08W | [7 empty] | 2021-08-03 |  | 80 | 8555764 | 2021 |  |  |  | 5643257 |  |  |  |  | 2022-03-01 | ESTS |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:22 |  |  | 2021 | Order and Notification
66319 | Resource change | 35232651 | 120529255 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Approved | 08W | [7 empty] | 2021-08-27 |  | 1584 | 916452.02 | 2021 |  |  |  | 3458896 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:19 |  |  | 2021 | Order and Notification
66320 | Resource change | 35232960 | 120537723 | CWSP - DESCHUTES 11049718 PH1.2 | Approved | 08W | [7 empty] | 2021-09-16 |  | 3040 | 475000 | 2021 |  |  |  | 5669548 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-09-16 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:18 |  |  | 2021 | Order and Notification
66318 | Resource change | 35232445 | 120528752 | CWSP - DESCHUTES 11049718 PH 2.5 | Approved | 08W | [7 empty] | 2021-08-02 |  | 3721.2 | 3055462 | 2021 |  |  |  | 3055462 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-02 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:17 |  |  | 2021 | Order and Notification
66316 | Resource change | 35232443 | 120528712 | CWSP - DESCHUTES 11049718 PH 2.3 | Approved | 08W | [7 empty] | 2021-08-06 |  | 1292.4 | 1351751 | 2021 |  |  |  | 1351751 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-06 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:17 |  |  | 2021 | Order and Notification
66317 | Resource change | 35232444 | 120528751 | CWSP - DESCHUTES 11049718 PH 2.4 | Approved | 08W | [7 empty] | 2021-10-22 |  | 5695.2 | 1475573.09 | 2021 |  |  |  | 6830548 |  |  |  |  | 2021-12-31 | PEND |  | 2021-10-22 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:17 |  |  | 2021 | Order and Notification
66315 | Resource change | 35232442 | 120528704 | CWSP - DESCHUTES 11049718 PH 2.2 | Approved | 08W | [7 empty] | 2021-12-31 |  | 3040 | 190000 | 2021 |  |  |  | 5959798 |  |  |  |  | 2021-12-31 | ESTS | [17 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:16 |  |  | 2021 | Order and Notification
66314 | Resource change | 35225825 | 120426401 | CWSP - DESCHUTES 11049718 PH2.1 | Approved | 08W | [7 empty] | 2021-08-09 |  | 2973.4 | 2167192 | 2021 |  |  |  | 2167192 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-09 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:16 |  |  | 2021 | Order and Notification
66313 | Resource change | 35219286 | 120142352 | CWSP - DESCHUTES 11049718 PH1.1 | Approved | 08W | [7 empty] | 2021-09-29 |  | 3290 | 475000 | 2021 |  |  |  | 5630850 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:11 |  |  | 2021 | Order and Notification
66312 | Resource change | 35114051 | 117502234 | OCGC PINE GROVE 1102 - LR1222 - PH | Approved | 08W | [7 empty] | 2020-10-02 |  | 4307.5 | 5342998 | 2021 |  |  | 3949678 | 2575321 |  |  |  |  | 2019-12-31 | MAPP | 2021-05-26 | 2020-10-02 | [15 empty] | Approved |  |  | 2021-04-08 15:24 |  |  | 2021-04-08 06:10 |  |  | 2021 | Order and Notification
66308 | Update work plan date | 35232960 |  | CWSP - DESCHUTES 11049718 PH1.2 | Denied | 08W | [6 empty] | Test |  | 2022-01-01 |  |  |  |  | 2022 | [7 empty] | ESTS | [17 empty] | Denied | Test entry |  | 2021-04-07 16:22 |  |  | 2021-04-07 16:18 |  |  |  | Not in Work Plan
66307 | Update work plan date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W | [6 empty] | Due to dependencies. |  | 2022-05-01 |  |  |  |  | 2022 | [7 empty] | PEND | [17 empty] | Denied | Test entry |  | 2021-04-07 16:22 |  |  | 2021-04-07 16:14 |  |  |  | Not in Work Plan
66306 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W | [6 empty] | Due to DSDD required, push to 5/22. |  | 2022-05-01 |  |  |  |  | 2022 | [7 empty] | ADER | [17 empty] | Denied | Test entry |  | 2021-04-07 16:09 |  |  | 2021-04-07 16:05 |  |  |  | Not in Work Plan
66304 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W | [6 empty] | Test |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | ADER | [17 empty] | Denied | Test entry |  | 2021-04-07 16:00 |  |  | 2021-04-07 15:53 |  |  |  | Not in Work Plan
66303 | Update Work Plan Date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W | [6 empty] | Defer project due to DSDD requirements. Please move project to 2022. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied |  |  | 2021-04-09 09:36 |  |  | 2021-04-07 15:41 |  |  |  | Not in Work Plan
66282 | Resource change | 35057018 | 114987363 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Approved | 08W | [7 empty] | 2021-08-31 |  | 14407.1 | 725000 | 2021 |  |  | 381374.4 | 16722.2 |  |  |  |  | 2020-12-30 | PEND |  | 2021-08-31 | [15 empty] | Approved |  |  | 2021-04-08 11:13 |  |  | 2021-04-07 13:05 |  |  | 2021 | Order and Notification
66276 | Update Work Plan Date | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD Requirments on other phases this 0.19 OH replacment phase should be completed with the other 7.20 miles in 2022. |  | 2022-05-31 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied |  |  | 2021-04-09 09:36 |  |  | 2021-04-07 12:04 |  |  |  | Not in Work Plan
66275 | Update Work Plan Date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD Requirments on other phases this 0.69 OH replacment phase should be completed with the other 6.69 miles in 2022. |  | 2022-05-31 |  |  |  |  | 2022 | [7 empty] | PEND | [9 empty] | Approved | [7 empty] | Denied |  |  | 2021-04-09 09:36 |  |  | 2021-04-07 12:04 |  |  |  | Not in Work Plan
66274 | Update Work Plan Date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD Requirments. Please defer project to 2022. |  | 2022-05-31 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied |  |  | 2021-04-09 09:36 |  |  | 2021-04-07 12:04 |  |  |  | Not in Work Plan
66227 | Add project | 35240546 |  | FRRB - WYANDOTTE 1103 - W2 PH2.13 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-19 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-07 08:47 |  |  |  | Not in Work Plan
66226 | Add project | 35240545 |  | FRRB - WYANDOTTE 1103 - W2 PH2.12 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-19 |  |  |  | 2021 | [9 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-07 08:47 |  |  |  | Not in Work Plan
66225 | Add project | 35239937 |  | FRRB - WYANDOTTE 1103 - W2 PH2.11 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-19 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-07 08:47 |  |  |  | Not in Work Plan
66193 | Add project | 35240468 |  | *CANC*ANAKA 1101 - K4 PH4.3 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | CNCL | 2021-05-05 | [13 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66192 | Add project | 35240467 |  | *CANC*ANAKA 1101 - K4 PH4.2 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | CNCL | 2021-05-05 | [13 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66191 | Add project | 35235703 |  | FRRB - KANAKA 1101 - K4 PH4.1 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66209 | Add project | 35236988 |  | *CANC*FRRB - KANAKA 1101 - K4 PH4.19 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | CNCL | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66208 | Add project | 35240543 |  | FRRB - KANAKA 1101 - K4 PH 4.18 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66207 | Add project | 35240542 |  | FRRB - KANAKA 1101 - K4 PH 4.19 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66206 | Add project | 35240541 |  | FRRB - KANAKA 1101 - K4 PH4.16 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66205 | Add project | 35240540 |  | FRRB - KANAKA 1101 - K4 PH4.15 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:40 |  |  |  | Not in Work Plan
66204 | Add project | 35240479 |  | FRRB - KANAKA 1101 - K4 PH4.14 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66203 | Add project | 35240478 |  | *CANC*ANAKA 1101 - K4 PH4.13 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | FICL | 2021-05-05 | [13 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66202 | Add project | 35240477 |  | FRRB - KANAKA 1101 - K4 PH4.12 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66201 | Add project | 35240476 |  | FRRB - KANAKA 1101 - K4 PH4.11 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66200 | Add project | 35240475 |  | FRRB - KANAKA 1101 - K4 PH4.10 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66199 | Add project | 35240474 |  | FRRB - KANAKA 1101 - K4 PH4.9 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:39 |  |  |  | Not in Work Plan
66198 | Add project | 35240473 |  | FRRB - KANAKA 1101 - K4 PH4.8 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:35 |  |  |  | Not in Work Plan
66197 | Add project | 35240472 |  | FRRB - KANAKA 1101 - K4 PH4.7 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:34 |  |  |  | Not in Work Plan
66195 | Add project | 35240470 |  | FRRB - KANAKA 1101 - K4 PH4.5 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:33 |  |  |  | Not in Work Plan
66194 | Add project | 35240469 |  | FRRB - KANAKA 1101 - K4 PH4.4 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:32 |  |  |  | Not in Work Plan
66196 | Add project | 35240471 |  | *CANC*KANAKA 1101 - K4 PH4.6 | Approved | 08W | [6 empty] | Part of NCFR Program | 2021-07-01 |  |  |  | 2021 | [9 empty] | CNCL | 2021-05-05 | [13 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-06 15:30 |  |  |  | Not in Work Plan
66145 | Defer project | 35227655 | 120462115 | CWSP - KIRKER 2104442850 PH 1.2 | Approved | 08W |  | SH |  |  |  |  | OH removal for proposed remote grid project planned for 2022. | 2022-06-06 | 2022-06-01 | 80 | 450000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-06-06 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-06 11:23 |  |  | 2022 | Order and Notification
66017 | Add project | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Approved | 08W | [6 empty] | Projects were approved by the WFGC and Segements in this order are to allocate part of original scoped miles. Workplan date is placeholder for 2022 and will be superceded once project schedule is completed | 2022-01-31 |  |  |  | 2022 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-05 10:54 |  |  |  | Not in Work Plan
66018 | Add project | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Approved | 08W | [6 empty] | Projects were approved by the WFGC and Segements in this order are to allocate part of original scoped miles. Workplan date is placeholder for 2022 and will be superceded once project schedule is completed | 2022-01-31 |  |  |  | 2022 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-05 10:54 |  |  |  | Not in Work Plan
66001 | Resource change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [7 empty] | 2021-07-19 |  | 5336.9 | 9341020 | 2021 |  |  |  | 6368290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:20 |  |  | 2021 | Order and Notification
66000 | Resource change | 35226624 | 120445228 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W | [7 empty] | 2021-09-07 |  | 672.1 | 302731.26 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-07 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:19 |  |  | 2021 | Order and Notification
65999 | Resource change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [7 empty] | 2021-07-28 |  | 4409.1 | 8067020 | 2021 |  |  |  | 5388290 |  |  |  |  | 2022-03-03 | UNSC |  | 2021-07-28 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:18 |  |  | 2021 | Order and Notification
65998 | Resource change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1673 | 7748520 | 2021 |  |  |  | 5143290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:17 |  |  | 2021 | Order and Notification
65997 | Resource change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [7 empty] | 2021-07-16 |  | 1433.2 | 4335155 | 2021 |  |  |  | 2518289.22 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:12 |  |  | 2021 | Order and Notification
65996 | Resource change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1062.1 | 7339020 | 2021 |  |  |  | 4828290 |  |  |  |  | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:06 |  |  | 2021 | Order and Notification
65995 | Resource change | 35226623 | 120445227 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W | [7 empty] | 2021-11-09 |  | 111.1 | 150000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-11-09 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:05 |  |  | 2021 | Order and Notification
65994 | Resource change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [7 empty] | 2021-07-19 |  | 2405 | 7066020 | 2021 |  |  |  | 4618290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:04 |  |  | 2021 | Order and Notification
65993 | Resource change | 35227029 | 120449800 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W | [7 empty] | 2021-09-07 |  | 998.8 | 447830.94 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-07 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:01 |  |  | 2021 | Order and Notification
65992 | Resource change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1103.5 | 6429020 | 2021 |  |  |  | 4128290 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 18:00 |  |  | 2021 | Order and Notification
65991 | Resource change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1647.2 | 6383520 | 2021 |  |  |  | 4093290 |  |  |  |  | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:56 |  |  | 2021 | Order and Notification
65990 | Resource change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [7 empty] | 2021-06-14 |  | 2886.6 | 6280110 | 2021 |  |  |  | 4013744 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:55 |  |  | 2021 | Order and Notification
65989 | Resource change | 35219272 | 120142171 | CWSP - MIDDLETOWN 1101481876 | Approved | 08W | [7 empty] | 2021-08-25 |  | 483.8 | 184734.86 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:53 |  |  | 2021 | Order and Notification
65988 | Resource change | 35227027 | 120449717 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W | [7 empty] | 2021-09-29 |  | 110.1 | 92500 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:53 |  |  | 2021 | Order and Notification
65987 | Resource change | 35226622 | 120445225 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 111.1 | 150000 | 2021 | [8 empty] | 2021-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:52 |  |  | 2021 | Order and Notification
65986 | Resource change | 35219098 | 120141805 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W | [7 empty] | 2021-08-16 |  | 514 | 198553.88 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:50 |  |  | 2021 | Order and Notification
65985 | Resource change | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W | [7 empty] | 2021-10-15 |  | 1371.6 | 409121.04 | 2021 |  |  |  | 475000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-15 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:49 |  |  | 2021 | Order and Notification
65984 | Resource change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [7 empty] | 2021-06-14 |  | 1328.6 | 4778094 | 2021 |  |  |  | 2858347 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:48 |  |  | 2021 | Order and Notification
65983 | Resource change | 35227028 | 120449719 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 92500 | 2021 | [8 empty] | 2021-12-31 | ADER |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:46 |  |  | 2021 | Order and Notification
65982 | Resource change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [7 empty] | 2021-08-17 |  | 1051.6 | 3728491 | 2021 |  |  |  | 2050960 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:46 |  |  | 2021 | Order and Notification
65981 | Resource change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [7 empty] | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:28 |  |  | 2021 | Order and Notification
65980 | Resource change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [7 empty] | 2021-08-20 |  | 552.9 | 3715565 | 2021 |  |  |  | 2041017 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:27 |  |  | 2021 | Order and Notification
65979 | Resource change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [7 empty] | 2021-07-16 |  | 994.5 | 3535462 | 2021 |  |  |  | 1902476 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:25 |  |  | 2021 | Order and Notification
65978 | Resource change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [7 empty] | 2021-07-30 |  | 909 | 3444978 | 2021 |  |  |  | 1832873 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:22 |  |  | 2021 | Order and Notification
65977 | Resource change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [7 empty] | 2021-07-30 |  | 979.2 | 3378623 | 2021 |  |  |  | 1781831 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:21 |  |  | 2021 | Order and Notification
65976 | Resource change | 35192281 | 119556250 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 90000 | 2021 | [8 empty] | 2023-12-31 | APPR |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:20 |  |  | 2021 | Order and Notification
65975 | Resource change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [7 empty] | 2021-09-03 |  | 932 | 3246777 | 2021 |  |  |  | 1680411 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-09-03 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:18 |  |  | 2021 | Order and Notification
65974 | Resource change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [7 empty] | 2021-08-27 |  | 723.9 | 3159481 | 2021 |  |  |  | 1614125 |  |  |  |  | 2022-01-01 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:15 |  |  | 2021 | Order and Notification
65973 | Resource change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [7 empty] | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:14 |  |  | 2021 | Order and Notification
65972 | Resource change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [7 empty] | 2021-09-22 |  | 487.4 | 2622014 | 2021 |  |  |  | 1199824 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-09-22 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:12 |  |  | 2021 | Order and Notification
65971 | Resource change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [7 empty] | 2021-09-09 |  | 742.6 | 2743520 | 2021 |  |  |  | 1293290 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-09-09 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 17:11 |  |  | 2021 | Order and Notification
65970 | Resource change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [7 empty] | 2021-07-26 |  | 351.3 | 2470520 | 2021 |  |  |  | 1083290 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-04-04 15:08 |  |  | 2021-04-02 16:28 |  |  | 2021 | Order and Notification
65934 | Add project | 35219542 |  | PSPS - ESKATON VILLAGE - PLACERVILLE 111 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65932 | Add project | 35219591 |  | CWSP - OLETA 1101754718 PH1.1 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65933 | Add project | 35236662 |  | CWSP - OLETA 1101754718 PH 1.2 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65928 | Add project | 35234398 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.2 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65929 | Add project | 35234399 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.3 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65930 | Add project | 35234400 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.4 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65931 | Add project | 35234401 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.5 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65927 | Add project | 35219287 |  | CWSP - OREGON TRAIL 110335002 PHASE 6.1 | Approved | 08W | [6 empty] | Projects was approved on 4/1/2021 by WFGC to bring into the workplan. Current submitted workplan dates are placeholder dates and will be superceded once project schedule is completed. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 13:04 |  |  |  | Not in Work Plan
65926 | Add project | 35238098 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 6 | Approved | 08W | [6 empty] | PM created as PH6 to avoid idle facilities on ML UG work | 2021-11-20 |  |  |  | 2021 | [5 empty] | 190000 |  |  |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-02 12:04 |  |  |  | Not in Work Plan
65909 | Defer project | 35231608 | 120504095 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W | [6 empty] | Updated Construction Completion year to match forecast. | 2022-07-25 | 2022-08-01 | 310.3 | 209584 | 2021 | 2022 | 2022 |  | 62873 |  |  |  |  | 2021-12-31 | PEND |  | 2022-07-25 | [7 empty] | Approved |  | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-01 13:46 |  |  | 2022 | Order and Notification
65905 | Update work plan date | 35227655 | 120462115 | CWSP - KIRKER 2104442850 PH 1.2 | Denied | 08W | [6 empty] | OH removal for proposed remote grid project planned for 2022. | 2022-06-06 | 2022-06-01 | 80 | 450000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-06-06 | [7 empty] | Approved | [7 empty] | Denied | Cannot update work plan date to 2022 , should be a defer project request type |  | 2021-04-04 15:12 |  |  | 2021-04-01 13:08 |  |  | 2022 | Order and Notification
65903 | Add project | 35144944 | 118261958 | PSPS - SNEATH LANE 1107 - LR 48338 | Approved | 08W | [6 empty] | Add project back into MPP workplan. Approved by WFGC on 3/24/21 | 2022-06-15 |  | 768.8 | 500000 | 2022 |  |  | 1712227.1 | 8662.9 |  |  |  |  | 2020-12-30 | PEND |  | 2022-06-15 | [12 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-01 12:33 |  |  | 2022 | Order and Notification
65901 | Defer project | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [6 empty] | CalTrans DSDD approval not expected until EOY 2021 or 2022 | 2021-12-30 | 2022-06-01 | 1781.5 | 3142865.56 | 2021 | 2022 | 2022 | 48176.5 | 500000 |  | 500000 | 3678901 |  | 2021-12-20 | PEND |  | 2021-12-30 | [9 empty] | Approved | 2022 Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-15 15:32 |  |  | 2021-04-01 11:57 |  |  | 2022 | Order and Notification
65669 | Add project | 35222234 |  | REMG 581 - OAKHURST 1101, MIAMI MOUNTAIN | Approved | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-08-31 |  |  |  | 2021 |  |  |  |  | 0 | 1000000 |  |  |  | UNSE | [6 empty] | Critical Work | [7 empty] | Approved | Changed work plan date to nominal 8/31/2021 |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-01 09:18 |  |  |  | Not in Work Plan
65668 | Add project | 35229051 |  | REMG 299/300 - CORNING 1102, TURRI ELLIS | Approved | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-08-31 |  |  |  | 2021 |  |  |  |  | 0 | 1000000 |  |  |  | UNSE | [6 empty] | Critical Work | [7 empty] | Approved | Changed work plan date to nominal 8/31/2021 |  | Approved |  |  | 2021-04-08 12:45 |  |  | 2021-04-01 09:18 |  |  |  | Not in Work Plan
65667 | Add project | 35056438 |  | REMG 650 - PLACERVILLE 2106, RINGTAIL | Approved | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-08-31 |  |  |  | 2021 |  |  |  |  | 0 | 775000 |  |  |  | UNSE | [6 empty] | Critical Work | [7 empty] | Approved | Changed work plan date to nominal 8/31/2021 |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-01 09:16 |  |  |  | Not in Work Plan
65665 | Add project | 35222235 |  | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT | Approved | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-08-31 |  |  |  | 2021 |  |  |  |  | 0 | 625000 |  |  |  | UNSE | [6 empty] | Critical Work | [7 empty] | Approved | Changed work plan date to nominal 8/31/2021 |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-01 09:02 |  |  |  | Not in Work Plan
65666 | Add project | 35238088 |  | REMG 531 - MARIPOSA 2101,SLAUGHTER HOUSE | Approved | 08W | [6 empty] | Adding 2021 Remote Grid Projects as requested | 2021-08-31 |  |  |  | 2021 |  |  |  |  | 0 | 800000 |  |  |  | DCNL | [6 empty] | Critical Work | [7 empty] | Approved | Changed work plan date to nominal 8/31/2021 |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-04-01 08:57 |  |  |  | Not in Work Plan
65647 | Update work plan date | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Denied | 08W | [6 empty] | Underground segements of Middletown LR548 that is now forecasted for execution in 2022. Requesting to defer from current year to 2022 execution. Workplan date not yet avaliable and provided WP date is placeholder to be superceded by P6 data |  | 2022-12-31 |  |  |  |  | 2022 | [7 empty] | UNSE | [9 empty] | Approved | [7 empty] | Denied | Job is not on workplan. To add job to work plan please submit and add job request. |  | 2021-04-01 13:02 |  |  | 2021-03-31 17:00 |  |  |  | Not in Work Plan
65646 | Update work plan date | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Denied | 08W | [6 empty] | Underground segements of Middletown LR548 that is now forecasted for execution in 2022. Requesting to defer from current year to 2022 execution. Workplan date not yet avaliable and provided WP date is placeholder to be superceded by P6 data |  | 2022-12-31 |  |  |  |  | 2022 | [7 empty] | UNSE | [9 empty] | Approved | [7 empty] | Denied | Job is not on workplan. To add job to work plan please submit and add job request. |  | 2021-04-01 13:02 |  |  | 2021-03-31 17:00 |  |  |  | Not in Work Plan
65645 | Resource change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [7 empty] | 2021-04-05 |  | 1354.7 | 11016312 | 2021 |  |  |  | 8094904 |  |  |  |  | 2021-12-31 | CONS |  | 2021-04-05 | [15 empty] | Approved |  |  | 2021-04-01 13:55 |  |  | 2021-03-31 16:54 |  |  | 2021 | Order and Notification
65644 | Resource change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W | [7 empty] | 2021-02-12 |  | 762.8 | 10286697 | 2021 |  |  |  | 6324922 |  |  |  |  | 2021-12-31 | DOCC | 2021-04-15 | 2021-02-12 | [15 empty] | Approved |  |  | 2021-04-01 13:55 |  |  | 2021-03-31 16:53 |  |  | 2021 | Order and Notification
65618 | Pull-in Project from Future Year | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2021-11-05 | 2021-11-20 | 433.2 | 204489.16 | 2021 | 2022 | 2021 |  | 67857 |  | 67857 |  |  | 2021-12-31 | PEND |  | 2021-11-05 | [7 empty] | Approved |  | Approved | Pull in project approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:33 |  |  | 2021-03-31 16:48 |  |  | 2022 | Order and Notification
65619 | Pull-in Project from Future Year | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2021-11-11 | 2021-11-20 | 80 | 67857 | 2021 | 2022 | 2021 |  | 67857 |  | 67857 |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Pull in project approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:33 |  |  | 2021-03-31 16:47 |  |  | 2022 | Order and Notification
65616 | Pull-in Project from Future Year | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2021-11-11 | 2021-11-20 | 80 | 67857 | 2021 | 2022 | 2021 |  | 67857 |  | 67857 |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Pull in project approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:33 |  |  | 2021-03-31 16:46 |  |  | 2022 | Order and Notification
65615 | Pull-in Project from Future Year | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2021-11-11 | 2021-11-20 | 80 | 67857 | 2021 | 2022 | 2021 |  | 67857 |  | 67857 |  |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Pull in project approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:33 |  |  | 2021-03-31 16:45 |  |  | 2022 | Order and Notification
65617 | Pull-in Project from Future Year | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [6 empty] | OH; base map n/a; 2021 possible execution | 2021-11-11 | 2021-11-20 | 648.8 | 338825.78 | 2021 | 2022 | 2021 |  | 67857 |  | 67857 |  |  | 2021-12-31 | PEND |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Pull in project approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:33 |  |  | 2021-03-31 16:43 |  |  | 2022 | Order and Notification
65568 | Add project | 35161152 | 118677953 | OCT2019 BRICEBURG FIRE REBUILD | Approved | 08W | [6 empty] | Fire Hardening 08W Remote Grid project | 2021-01-11 |  | 200 | 1676000 | 2021 |  |  | 375186 | 1400000 |  | 1200000 |  |  |  | MAPP | 2021-05-20 | 2021-01-11 | [12 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-31 16:19 |  |  | 2021 | Order and Notification
65567 | Add project | 31361965 |  | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [6 empty] | Construction & Program Mgmt requested to add to 2021 work plan | 2021-05-15 |  |  |  | 2021 | [5 empty] | 1245293 |  |  |  | FICL | 2021-04-24 | [13 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-31 15:26 |  |  |  | Not in Work Plan
65566 | Add project | 31334291 |  | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [6 empty] | Construction & Program Mgmt requested to add to 2021 work plan | 2021-11-20 |  |  |  | 2021 | [5 empty] | 1115282 |  |  |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-31 15:26 |  |  |  | Not in Work Plan
65546 | Budget change | 35233959 | 120564052 | CWSP - OREGON TRAIL 110335002 PH2.6 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-11-12 |  | 80 | 75000 | 2021 |  |  |  | 665000 | 0 | 665000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-11-12 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-31 11:46 |  |  | 2021 | Order and Notification
65545 | Budget change | 35233952 | 120563958 | CWSP - OREGON TRAIL 110335002 PH2.2 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-11-25 |  | 80 | 100000 | 2021 |  |  |  | 4104000 | 0 | 4104000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-11-25 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-31 11:45 |  |  | 2021 | Order and Notification
65544 | Budget change | 35234382 | 120564057 | CWSP - OREGON TRAIL 110335002 PH2.8 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-10-29 |  | 80 | 100000 | 2021 |  |  |  | 3021000 | 0 | 3021000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-10-29 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-31 11:45 |  |  | 2021 | Order and Notification
65543 | Budget change | 35234381 | 120564055 | CWSP - OREGON TRAIL 110335002 PH2.7 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-11-01 |  | 80 | 100000 | 2021 |  |  |  | 2945000 | 0 | 2945000 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-11-01 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-31 11:45 |  |  | 2021 | Order and Notification
65542 | Budget change | 35225826 | 120426402 | CWSP - OREGON TRAIL 110335002 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 Budget for this job using avarage cost $1.9M per mile | 2021-12-22 |  | 80 | 100000 | 2021 |  |  |  | 4825999.3 | 0 | 4825999.3 | 0 | 0 | 2021-12-31 | UNSE |  | 2021-12-22 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-31 11:44 |  |  | 2021 | Order and Notification
64319 | Defer project | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W |  | 2022 |  |  |  |  | the scope of this job is a span across a river. It will be exceuted with 2 UG projects ph2 and ph3 that planned to be in 2022 WP | 2022-03-01 | 2022-06-30 | 690.1 | 150000 | 2021 | 2022 | 2022 |  | 380000 | 0 | 0 | 0 | 0 | 2021-12-31 | PEND |  | 2022-03-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-31 09:37 |  |  | 2022 | Order and Notification
64318 | Update work plan date | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD requirements on other project phases and [REDACTED] completing all 5 phases. Then keeping this smaller 0.69 mile project is the same construction year would be best. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. |  | 2021-04-01 13:00 |  |  | 2021-03-31 08:23 |  |  |  | Not in Work Plan
64317 | Update work plan date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W |  | N/A |  |  |  |  | Due to DSDD requirements on other project phases and [REDACTED] completing all 5 phases. Then keeping this smaller 0.19 mile project is the same construction year would be best. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | PEND | [9 empty] | Approved | [7 empty] | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. |  | 2021-04-01 13:00 |  |  | 2021-03-31 08:23 |  |  |  | Not in Work Plan
64316 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W |  | N/A |  |  |  |  | DSDD Required - Due to dependencies deferring project to 2022. |  | 2022-06-01 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. |  | 2021-04-01 13:01 |  |  | 2021-03-31 08:23 |  |  |  | Not in Work Plan
64168 | Add project | 35057018 |  | CWSP - EL DORADO 2101 - 19752 - PH 4.1 | Approved | 08W | [6 empty] | Adding this job to 2021 WP as part of SH Program | 2021-07-13 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-30 12:48 |  |  |  | Not in Work Plan
64167 | Add project | 35109546 |  | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 | Approved | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-06-22 |  |  |  | 2022 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-30 12:47 |  |  |  | Not in Work Plan
64166 | Add project | 35109541 |  | CWSP - EL DORADO 2101 - 19752 - PH 1.3 | Approved | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-07-01 |  |  |  | 2022 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-30 12:47 |  |  |  | Not in Work Plan
64165 | Add project | 35056733 |  | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | Approved | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-03-30 |  |  |  | 2022 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-30 12:47 |  |  |  | Not in Work Plan
64164 | Add project | 35057010 |  | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | Approved | 08W | [6 empty] | Adding this job to 2022 WP as part of SH Program | 2022-06-20 |  |  |  | 2022 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-30 12:46 |  |  |  | Not in Work Plan
64129 | Defer project | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W |  | 2022 |  |  |  |  | Push this project to 2022 due to DSDD issue | 2021-10-28 | 2022-03-16 | 4313.1 | 5959167 | 2021 | 2022 | 2022 | 300000 | 500000 | 0 | 500000 | 3639275 | 0 | 2020-09-30 | PEND |  | 2021-10-28 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-30 11:47 |  |  | 2022 | Order and Notification
64071 | Budget change | 35227201 | 120457012 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-02 |  | 791.2 | 512371.91 | 2021 |  |  |  | 2080934 |  | 2080934 |  |  | 2021-12-31 | CONS |  | 2021-02-02 | [15 empty] | Approved |  |  | 2021-04-01 12:38 |  |  | 2021-03-30 08:14 |  |  | 2021 | Order and Notification
64050 | Add project | 35233996 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:21 |  |  |  | Not in Work Plan
64044 | Add project | 35231628 |  | CWSP - HIGHLANDS 1102628 PH 1.10 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64045 | Add project | 35231629 |  | CWSP - HIGHLANDS 1102628 PH 1.11 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64046 | Add project | 35231630 |  | CWSP - HIGHLANDS 1102628 PH 1.12 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64047 | Add project | 35231631 |  | CWSP - HIGHLANDS 1102628 PH 1.13 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64051 | Add project | 35219289 |  | CWSP - OREGON TRAIL 110335002 PH1.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64052 | Add project | 35233947 |  | CWSP - OREGON TRAIL 110335002 PH1.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64053 | Add project | 35233948 |  | CWSP - OREGON TRAIL 110335002 PH1.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64054 | Add project | 35233949 |  | CWSP - OREGON TRAIL 110335002 PH1.4 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64055 | Add project | 35233950 |  | CWSP - OREGON TRAIL 110335002 PH1.5 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64060 | Add project | 35234389 |  | CWSP - OREGON TRAIL 110335002 PH4.4 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64061 | Add project | 35234390 |  | CWSP - OREGON TRAIL 110335002 PH4.5 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64062 | Add project | 35234391 |  | CWSP - OREGON TRAIL 110335002 PH4.6 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64063 | Add project | 35234392 |  | CWSP - OREGON TRAIL 110335002 PH4.7 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64064 | Add project | 35225829 |  | CWSP - OREGON TRAIL 110335002 PH5.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64065 | Add project | 35234393 |  | CWSP - OREGON TRAIL 110335002 PH5.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64066 | Add project | 35234394 |  | CWSP - OREGON TRAIL 110335002 PH5.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64067 | Add project | 35234395 |  | CWSP - OREGON TRAIL 110335002 PH5.4 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64056 | Add project | 35233951 |  | CWSP - OREGON TRAIL 110335002 PH1.6 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64068 | Add project | 35234396 |  | CWSP - OREGON TRAIL 110335002 PH5.5 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64069 | Add project | 35234397 |  | CWSP - OREGON TRAIL 110335002 PH5.6 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64048 | Add project | 35224377 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64049 | Add project | 35233995 |  | PSPS - PLACERVILLE 2106 MICROGRID PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64030 | Add project | 35227870 |  | CWSP - VACAVILLE 11046542 - PH 2.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64031 | Add project | 35227656 |  | CWSP - VACAVILLE 11046542 - PH 2.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64032 | Add project | 35227657 |  | CWSP - VACAVILLE 11046542 - PH 2.4 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64033 | Add project | 35227658 |  | CWSP - VACAVILLE 11046542 - PH 2.5 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64034 | Add project | 35227659 |  | CWSP - VACAVILLE 11046542 - PH 2.6 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64057 | Add project | 35225828 |  | CWSP - OREGON TRAIL 110335002 PH4.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64058 | Add project | 35234387 |  | CWSP - OREGON TRAIL 110335002 PH4.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64059 | Add project | 35234388 |  | CWSP - OREGON TRAIL 110335002 PH4.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64035 | Add project | 35219099 |  | CWSP - HIGHLANDS 1102628 PH 1.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64036 | Add project | 35231620 |  | CWSP - HIGHLANDS 1102628 PH 1.2 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64037 | Add project | 35231621 |  | CWSP - HIGHLANDS 1102628 PH 1.3 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64038 | Add project | 35231622 |  | CWSP - HIGHLANDS 1102628 PH 1.4 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64039 | Add project | 35231623 |  | CWSP - HIGHLANDS 1102628 PH 1.5 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64040 | Add project | 35231624 |  | CWSP - HIGHLANDS 1102628 PH 1.6 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64041 | Add project | 35231625 |  | CWSP - HIGHLANDS 1102628 PH 1.7 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64042 | Add project | 35231626 |  | CWSP - HIGHLANDS 1102628 PH 1.8 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64043 | Add project | 35231627 |  | CWSP - HIGHLANDS 1102628 PH 1.9 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
64029 | Add project | 35224378 |  | CWSP - VACAVILLE 11046542 - PH 2.1 | Approved | 08W | [6 empty] | Project recently approved by WFGC thus requesting to project to be added to the MPP Workplan. Initial workplan year 2021 and workplan date of 12/31/21 is placeholder until schedule is avaliable at which point Workplan date will be superceded. | 2021-09-30 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-08 12:46 |  |  | 2021-03-29 21:12 |  |  |  | Not in Work Plan
62697 | Defer project | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Approved | 08W | [6 empty] | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-12-29 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:48 |  |  | 2022 | Order and Notification
62696 | Defer project | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Approved | 08W | [6 empty] | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-10-26 | 2022-08-13 | 110.1 | 200000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-10-26 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:48 |  |  | 2022 | Order and Notification
62698 | Defer project | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Approved | 08W | [6 empty] | Mileage forecasted for 2021;updating the project report year from 2021 to 2022 | 2021-12-14 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-14 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:48 |  |  | 2022 | Order and Notification
62687 | Defer project | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-17 | 2022-01-17 | 346.6 | 132166.93 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-11-17 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62693 | Defer project | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-02-09 | 2022-01-17 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62692 | Defer project | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-08 | 2022-12-27 | 110.1 | 250000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62691 | Defer project | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-10-13 | 2022-09-28 | 80 | 312500 | 2021 | 2022 | 2022 | [6 empty] | 2023-12-31 | ADER |  | 2021-10-13 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62689 | Defer project | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-01-19 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62690 | Defer project | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-10 | 2022-12-20 | 130.1 | 316666 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-10 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62686 | Defer project | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-25 | 2022-11-22 | 674.2 | 360825.19 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | PEND |  | 2021-11-25 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62694 | Defer project | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-12-15 | 2022-11-22 | 131.1 | 316666 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-15 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62688 | Defer project | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-10-27 | 2022-11-09 | 83 | 312500 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-10-27 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62695 | Defer project | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2021-11-09 | 2022-08-13 | 111.1 | 250000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-11-09 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:37 |  |  | 2022 | Order and Notification
62685 | Defer project | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022; updating the project report year from 2021 to 2022 | 2022-02-09 | 2022-01-17 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:36 |  |  | 2022 | Order and Notification
62684 | Defer project | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2022-02-09 | 2022-01-17 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62678 | Defer project | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-29 | 2022-01-17 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62682 | Defer project | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-29 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62677 | Defer project | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-01 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-01 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62681 | Defer project | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-10-26 | 2022-08-13 | 110.1 | 200000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2021-10-26 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62680 | Defer project | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-12-29 | 2022-12-27 | 110.1 | 1 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62679 | Defer project | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2022-01-05 | 2022-12-27 | 110.1 | 200000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62683 | Defer project | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-10-27 | 2022-09-14 | 110.1 | 250000 | 2021 | 2022 | 2022 | [6 empty] | 2023-12-31 | UNSE |  | 2021-10-27 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:14 |  |  | 2022 | Order and Notification
62676 | Defer project | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Approved | 08W | [6 empty] | Mileaage forecasted for 2022;updating the project report year from 2021 to 2022 | 2021-11-10 | 2022-07-23 | 131.1 | 316666 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | ESTS |  | 2021-11-10 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 10:12 |  |  | 2022 | Order and Notification
62675 | Defer project | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W | [6 empty] | Mileage forecasted for 2022;updating the project report year from 2021 to 2022 | 2022-01-26 | 2022-01-17 | 111.1 | 250000 | 2021 | 2022 | 2022 | [6 empty] | 2021-12-31 | UNSE |  | 2022-01-26 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-04-08 12:39 |  |  | 2021-03-29 09:50 |  |  | 2022 | Order and Notification
61317 | Add project | 35239522 |  | FRRB - WYANDOTTE 1103 - W2 PH2.9 | Approved | 08W | [6 empty] | addin this project to 2021 WP as part of NCFR program | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-01 11:26 |  |  | 2021-03-26 09:30 |  |  |  | Not in Work Plan
61318 | Add project | 35239523 |  | FRRB - WYANDOTTE 1103 - W2 PH2.10 | Approved | 08W | [6 empty] | addin this project to 2021 WP as part of NCFR program | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-04-01 11:26 |  |  | 2021-03-26 09:30 |  |  |  | Not in Work Plan
61308 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W | [7 empty] | 2022-10-11 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-10-11 | [15 empty] | Approved |  |  | 2021-03-26 10:59 |  |  | 2021-03-26 08:52 |  |  | 2021 | Order and Notification
61309 | Resource change | 35226845 | 120448987 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W | [7 empty] | 2021-07-06 |  | 2256.4 | 1101405.78 | 2021 |  |  |  | 2519287 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-06 | [15 empty] | Approved |  |  | 2021-03-26 10:59 |  |  | 2021-03-26 08:51 |  |  | 2021 | Order and Notification
61310 | Resource change | 35192290 | 119556075 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W | [7 empty] | 2021-09-16 |  | 80 | 1 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-09-16 | [15 empty] | Approved |  |  | 2021-03-26 10:59 |  |  | 2021-03-26 08:51 |  |  | 2021 | Order and Notification
61311 | Resource change | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W | [7 empty] | 2021-12-16 |  | 80 | 1 | 2021 | 2022 |  |  | 267945.29 |  |  |  |  | 2023-12-31 | ESTS |  | 2021-12-16 | [15 empty] | Approved |  |  | 2021-03-26 10:59 |  |  | 2021-03-26 08:51 |  |  | 2022 | Order and Notification
61287 | Update work plan date | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Denied | 08W | [6 empty] | [REDACTED] to complete 6.5 miles in 3 other phases om this circuit, but they require DSDD. It makes a good business decision to complete the 0.69 miles when the 6.5 miles is completed. |  | 2022-12-31 | [12 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be Deferral request |  | 2021-03-26 12:50 |  |  | 2021-03-25 14:19 |  |  |  | Not in Work Plan
61286 | Update work plan date | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Denied | 08W | [6 empty] | [REDACTED] to complete 6.5 miles in 3 other phases om this circuit, but they require DSDD. It makes a good business decision to complete the 0.19 miles when the 6.5 miles is completed. |  | 2022-12-31 | [12 empty] | PEND | [9 empty] | Approved | [7 empty] | Denied | Needs to be Deferral request |  | 2021-03-26 12:50 |  |  | 2021-03-25 14:19 |  |  |  | Not in Work Plan
60788 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W | [6 empty] | Push to 2022 due to dependencies clearing. |  | 2022-12-31 | [12 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be Deferral request |  | 2021-03-26 12:50 |  |  | 2021-03-25 10:41 |  |  |  | Not in Work Plan
60779 | Add project | 35235676 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-08-31 |  |  |  | 2021 | 2021 |  |  |  |  | 8400000 |  |  |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-25 08:47 |  |  |  | Not in Work Plan
60778 | Add project | 35235139 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-08-31 |  |  |  | 2021 | 2021 |  |  |  |  | 4620000 |  |  |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-25 08:47 |  |  |  | Not in Work Plan
60605 | Resource change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [7 empty] | 2021-08-27 |  | 723.9 | 3159481 | 2021 |  |  |  | 1614125 |  |  |  |  | 2022-01-01 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-26 10:57 |  |  | 2021-03-24 18:52 |  |  | 2021 | Order and Notification
60501 | Update work plan date | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Denied | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all the dependencies needed to be completed will need to be in 2022. |  | 2022-09-30 |  |  |  |  | 2022 | [7 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be Deferral request |  | 2021-03-26 12:50 |  |  | 2021-03-24 15:34 |  |  |  | Not in Work Plan
60500 | Budget change | 35115157 | 117492085 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-04-15 |  | 2628.1 | 1580553.38 | 2020 |  |  | 3900000 | 34847 |  | 34847 |  |  | 2020-12-31 | FICL | 2020-09-30 | [16 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:32 |  |  | 2020 | Order and Notification
60499 | Budget change | 35115156 | 117491998 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-06-12 |  | 1825.3 | 1357699.57 | 2020 |  |  | 5490339.7 | 37751 |  | 37751 |  |  | 2020-12-31 | FICL | 2020-07-03 | [16 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:32 |  |  | 2020 | Order and Notification
60498 | Budget change | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-01-13 |  | 2123.7 | 5231108 | 2020 |  |  | 3150000 | 88800 |  | 88800 |  |  | 2020-12-31 | FICL | 2021-02-25 | 2020-01-13 | [15 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:32 |  |  | 2020 | Order and Notification
60497 | Budget change | 35115150 | 117496277 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-07-08 |  | 2266.9 | 4212019 | 2020 |  |  | 2197037.6 | 37621 |  | 37621 |  |  | 2020-12-31 | PREC | [17 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:32 |  |  | 2020 | Order and Notification
60496 | Budget change | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-06-02 |  | 3236.8 | 5062019 | 2020 |  |  | 4762461.3 | 59744 |  | 59744 |  |  | 2020-12-31 | PREC | 2020-11-20 | [16 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:31 |  |  | 2020 | Order and Notification
60495 | Budget change | 35115147 | 117496196 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-05-05 |  | 1223.8 | 5398830 | 2020 |  |  | 2808776.3 | 34829 |  | 34829 |  |  | 2020-12-31 | FICL | 2020-08-13 | 2020-05-05 | [15 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:31 |  |  | 2020 | Order and Notification
60494 | Budget change | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-06-01 |  | 2558.5 | 2927538 | 2020 |  |  | 1900000 | 131088 |  | 131088 |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [15 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:31 |  |  | 2020 | Order and Notification
60493 | Budget change | 35061213 | 115106582 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 | Approved | 08W | 220 Mile Plan | [5 empty] | Adjusting budget to allign with 2021 EAC | 2020-07-24 |  | 3375.3 | 6076529 | 2020 |  |  | 3590381.7 | 36100 |  | 36100 |  |  | 2020-12-31 | FICL | [17 empty] | Approved |  |  | 2021-03-26 12:22 |  |  | 2021-03-24 15:30 |  |  | 2020 | Order and Notification
60490 | Add project | 35116440 |  | CWSP-MIWUK 1702-LR8090-PH 1.6 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-07-31 |  |  |  | 2022 | 2022 | [5 empty] | 3568368 |  |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:39 |  |  | 2021-03-24 14:26 |  |  |  | Not in Work Plan
60489 | Add project | 35116385 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Adding project back into work plan as 2021 per WFGC Committee approval | 2022-08-31 |  |  |  | 2021 | 2022 | [5 empty] | 1530167 |  |  | PEND | [14 empty] | Approved | Revised to 2021 dates per latest information after change request was initially submitted |  | Approved | 2022 per email from [REDACTED] |  | 2021-03-30 17:17 |  |  | 2021-03-24 14:22 |  |  |  | Not in Work Plan
60473 | Update work plan date | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Denied | 08W | [6 empty] | 08W Fire Hardening Project | 2021-12-16 | 2022-03-02 | 80 | 1 | 2021 | 2022 | 2022 |  | 267945.29 |  | 300000 | 1364659 |  | 2023-12-31 | ESTS |  | 2021-12-16 | [7 empty] | Approved | [7 empty] | Denied | Job is on 2021 work plan, if you want to move to 2022 you need to submit a deferral request. |  | 2021-04-01 13:00 |  |  | 2021-03-24 11:58 |  |  | 2022 | Order and Notification
60398 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60399 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60397 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2022 workplan. | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60400 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60027 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60401 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60028 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60402 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60029 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60396 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60023 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60395 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 61305 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
61306 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Adding this project as part of SH program | 2021-12-31 |  |  |  | 2021 | [9 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 61305 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-23 10:47 |  |  |  | Not in Work Plan
60363 | Budget change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W | [6 empty] | Requesting Addational $35,581 for 2021 to align with expected case number in the approved BC | 2021-05-26 |  | 4089.8 | 6586891 | 2021 |  |  |  | 4901112 | 0 | 4901112 | 0 | 0 | 2021-12-31 | CONS |  | 2021-05-26 | [15 empty] | Approved |  |  | 2021-03-26 12:21 |  |  | 2021-03-22 12:12 |  |  | 2021 | Order and Notification
60015 | Add project | 35223062 |  | PSPS - CALISTOGA 1102 - W/O NAPA RIVER | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:46 |  |  |  | Not in Work Plan
60016 | Add project | 35223032 |  | PSPS - MOUNTAIN QUARRIES 2101 - COOL | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:46 |  |  |  | Not in Work Plan
60017 | Add project | 35219276 |  | CWSP - VACAVILLE 11046542 PH 1.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:46 |  |  |  | Not in Work Plan
60019 | Add project | 35227652 |  | CWSP - VACAVILLE 11046542 PH 1.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60020 | Add project | 35227653 |  | CWSP - VACAVILLE 11046542 PH 1.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60021 | Add project | 35227654 |  | CWSP - VACAVILLE 11046542 PH 1.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60023 | Add project | 35233952 |  | CWSP - OREGON TRAIL 110335002 PH2.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60027 | Add project | 35233959 |  | CWSP - OREGON TRAIL 110335002 PH2.6 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60028 | Add project | 35234381 |  | CWSP - OREGON TRAIL 110335002 PH2.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60029 | Add project | 35234382 |  | CWSP - OREGON TRAIL 110335002 PH2.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60039 | Add project | 35236437 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60040 | Add project | 35236438 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60043 | Add project | 35236661 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | APPR | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
61305 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60041 | Add project | 35236439 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60042 | Add project | 35236660 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60030 | Add project | 35225827 |  | CWSP - OREGON TRAIL 110335002 PH3.1 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60031 | Add project | 35233954 |  | CWSP - OREGON TRAIL 110335002 PH3.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60032 | Add project | 35233956 |  | CWSP - OREGON TRAIL 110335002 PH3.3 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60033 | Add project | 35233958 |  | CWSP - OREGON TRAIL 110335002 PH3.4 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60034 | Add project | 35234380 |  | CWSP - OREGON TRAIL 110335002 PH3.5 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60035 | Add project | 35234383 |  | CWSP - OREGON TRAIL 110335002 PH3.6 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60036 | Add project | 35234384 |  | CWSP - OREGON TRAIL 110335002 PH3.7 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60037 | Add project | 35234385 |  | CWSP - OREGON TRAIL 110335002 PH3.8 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60038 | Add project | 35234386 |  | CWSP - OREGON TRAIL 110335002 PH3.9 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60044 | Add project | 35219543 |  | PSPS - WEST MAIN ST / RESERVOIR ST - PLA | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60024 | Add project | 35233953 |  | CWSP - OREGON TRAIL 110335002 PH2.3 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60397 |  | Denied |  |  | 2021-03-26 10:33 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60025 | Add project | 35233955 |  | CWSP - OREGON TRAIL 110335002 PH2.4 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60398 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60026 | Add project | 35233957 |  | CWSP - OREGON TRAIL 110335002 PH2.5 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 60399 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60022 | Add project | 35225826 |  | CWSP - OREGON TRAIL 110335002 PH2.1 | Denied | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-12-31 |  |  |  |  | 2021 | [8 empty] | UNSE | [14 empty] | Denied | Duplicate of Change ID 61305 |  | Denied |  |  | 2021-03-26 10:34 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60018 | Add project | 35227651 |  | CWSP - VACAVILLE 11046542 PH 1.2 | Approved | 08W | [6 empty] | Recent scope approvals by the WFGC. Order not currently in the MPP Workplan thus requesting to add to 2021 workplan. | 2021-08-31 |  |  |  | 2021 | 2021 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:36 |  |  | 2021-03-19 14:44 |  |  |  | Not in Work Plan
60014 | Add project | 74022385 | 114691436 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-03-21 |  | 9 | 999000 | 2022 | 2022 |  | 750000 | 3379.1 |  |  | 3523187 |  | 2020-11-30 | APPR |  | 2022-03-21 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60013 | Add project | 35094396 | 117130859 | CWSP-KONOCTI 1102-LR 532 PH 9 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-04-05 |  | 2754.1 | 687082.4 | 2022 | 2022 |  | 11365.3 | 11339 |  |  | 687082.4 |  | 2020-11-30 | PEND |  | 2022-04-05 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60012 | Add project | 35094395 | 117130858 | CWSP-KONOCTI 1102-LR 532 PH 8 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-10-19 |  | 131 | 75000 | 2022 | 2022 |  | 3948.6 | 7364 |  |  | 75000 |  | 2020-11-30 | ESTS |  | 2022-10-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60011 | Add project | 35094391 | 117130854 | CWSP-KONOCTI 1102-LR 532 PH 4 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-04-04 |  | 1696.6 | 45454 | 2022 | 2022 |  | 6426.8 | 2756 |  |  | 470100.69 |  | 2020-11-30 | PEND |  | 2022-04-04 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60010 | Add project | 35094389 | 117130852 | CWSP-KONOCTI 1102-LR 532 PH 2 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-08-19 |  | 816 | 85000 | 2022 | 2022 |  | 997290.6 | 5220 |  |  | 85000 |  | 2020-11-30 | ESTS |  | 2022-08-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60009 | Add project | 35050951 | 114848376 | CWSP: MONTE RIO 1113 HENDRIX CABLE | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2023-02-01 |  | 2001.1 | 95000 | 2022 | 2023 |  | 1542801.8 |  |  |  |  | 95000 | 2019-12-31 | UNSE |  | 2023-02-01 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60008 | Add project | 35050942 | 114848297 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2023-02-01 |  | 3 | 95000 | 2022 | 2023 |  | 3133811.9 |  |  |  |  | 95000 | 2019-10-25 | UNSE |  | 2023-02-01 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60007 | Add project | 35046211 | 114730956 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2023-02-01 |  | 3 | 95000 | 2022 | 2023 |  | 1475029.2 |  |  |  |  | 95000 | 2019-10-25 | UNSE |  | 2023-02-01 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:52 |  |  | 2022 | Order and Notification
60006 | Add project | 35043296 | 112191208 | WDDB - WILLOW CRK 1103 LR 3090 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-02-03 |  | 3255.1 | 776346.19 | 2022 | 2022 |  | 269830.7 |  |  |  | 776346 |  | 2018-10-10 | PEND |  | 2022-02-03 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-19 13:51 |  |  | 2022 | Order and Notification
60005 | Add project | 35234865 | 120581001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-01-19 |  | 80 | 300000 | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  | 2022-01-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:39 |  |  | 2021-03-19 13:51 |  |  | 2022 | Order and Notification
60004 | Add project | 35234862 | 120580959 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-01-19 |  | 80 | 300000 | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  | 2022-01-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:39 |  |  | 2021-03-19 13:51 |  |  | 2022 | Order and Notification
60003 | Add project | 35234758 | 120580957 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-01-19 |  | 80 | 300000 | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | ESTS |  | 2022-01-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:39 |  |  | 2021-03-19 13:51 |  |  | 2022 | Order and Notification
60002 | Add project | 35234756 | 120580906 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-01-19 |  | 80 | 300000 | 2022 | 2022 | [5 empty] | 300000 |  | 2021-12-31 | UNSE |  | 2022-01-19 | [12 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:39 |  |  | 2021-03-19 13:51 |  |  | 2022 | Order and Notification
59951 | Budget change | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2022-03-31 |  | 110.1 | 316666 | 2021 | 2022 |  |  | 201100.86 |  | 251101 | 7569490 |  | 2021-12-31 | ESTS |  | 2022-03-31 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-19 10:57 |  |  | 2022 | Order and Notification
59959 | Budget change | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2021-12-07 |  | 80 | 500000 | 2021 | 2022 |  |  | 120000 |  | 110970 | 201853 |  | 2021-12-31 | ESTS |  | 2021-12-07 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-19 10:56 |  |  | 2022 | Order and Notification
59954 | Budget change | 35232651 | 120529255 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan. | 2021-08-27 |  | 1584 | 916452.02 | 2021 |  |  |  | 3458896 |  | 3458896 |  |  | 2021-12-31 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-19 10:53 |  |  | 2021 | Order and Notification
59955 | Budget change | 35232650 | 120529254 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2022-04-12 |  | 80 | 316667 | 2021 | 2022 |  |  | 162264.96 |  | 212265 | 5177531 |  | 2021-12-31 | ESTS |  | 2022-04-12 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-19 10:52 |  |  | 2022 | Order and Notification
59948 | Budget change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [6 empty] | requesting additional $40,927 for 2021 MPP budget to allign with BC approval (Expected Case number) | 2021-04-05 |  | 1354.7 | 11016312 | 2021 |  |  |  | 8094904 | 0 | 8094904 | 0 | 0 | 2021-12-31 | CONS |  | 2021-04-05 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-19 08:57 |  |  | 2021 | Order and Notification
59944 | Defer project | 35062375 | 115323921 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2022-01-07 | 2022-11-24 | 131.1 | 1 | 2021 | 2022 | 2022 | 58.9 | 200 |  | 200 |  |  | 2022-12-31 | ESTS |  | 2022-01-07 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-19 07:54 |  |  | 2022 | Order and Notification
59945 | Defer project | 35192292 | 119556108 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Approved | 08W | [6 empty] | Defer to 2022, 08W ECOP 100% UG project dependencies will not be completed until 2022. | 2021-12-23 | 2022-11-24 | 50.1 | 950000 | 2021 | 2022 | 2022 |  | 200 |  | 200 |  |  | 2023-12-31 | ESTS |  | 2021-12-23 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-19 07:54 |  |  | 2022 | Order and Notification
59946 | Defer project | 35226849 | 120449142 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2021-12-13 | 2022-11-24 | 130.1 | 1 | 2021 | 2022 | 2022 |  | 200 |  | 200 |  |  | 2022-12-31 | ESTS |  | 2021-12-13 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-19 07:54 |  |  | 2022 | Order and Notification
59947 | Defer project | 35225594 | 120424183 | CNCL ECOP FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W | [6 empty] | Defer to 2022, 08W CWSP 100% UG project dependencies will not be completed until 2022. | 2022-01-18 | 2022-11-24 | 50.1 | 1 | 2021 | 2022 | 2022 |  | 200 |  | 200 |  |  | 2021-12-31 | DOCC |  | 2022-01-18 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-19 07:54 |  |  | 2022 | Order and Notification
59939 | Defer project | 35227025 | 120449714 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-23 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 500000 |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-23 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:45 |  |  | 2022 | Order and Notification
59935 | Defer project | 35227021 | 120449712 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-31 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:44 |  |  | 2022 | Order and Notification
59940 | Defer project | 35227018 | 120449711 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-31 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:43 |  |  | 2022 | Order and Notification
59923 | Defer project | 35227015 | 120449710 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-31 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:42 |  |  | 2022 | Order and Notification
59920 | Defer project | 35227013 | 120449539 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-31 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:41 |  |  | 2022 | Order and Notification
59919 | Defer project | 35227010 | 120449536 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-31 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:40 |  |  | 2022 | Order and Notification
59932 | Defer project | 35227007 | 120449533 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-17 | 2022-11-20 | 80 | 118750 | 2021 | 2022 | 2022 |  | 500000 |  | 500000 | 100000 |  | 2021-12-31 | UNSE |  | 2023-01-17 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:39 |  |  | 2022 | Order and Notification
59930 | Defer project | 35227004 | 120449457 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:38 |  |  | 2022 | Order and Notification
59928 | Defer project | 35227003 | 120449456 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:37 |  |  | 2022 | Order and Notification
59931 | Defer project | 35227002 | 120449455 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 200000 |  | 200000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:36 |  |  | 2022 | Order and Notification
59929 | Defer project | 35227001 | 120449454 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:35 |  |  | 2022 | Order and Notification
59936 | Defer project | 35226878 | 120449453 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 500000 |  | 500000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:34 |  |  | 2022 | Order and Notification
59924 | Defer project | 35226873 | 120449450 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2022-11-01 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:33 |  |  | 2022 | Order and Notification
59934 | Defer project | 35226870 | 120449231 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2021-11-05 | 2022-11-20 | 433.2 | 204489.16 | 2021 | 2022 | 2022 |  | 67857 |  | 200000 | 100000 |  | 2021-12-31 | PEND |  | 2021-11-05 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:31 |  |  | 2022 | Order and Notification
59926 | Defer project | 35226866 | 120449230 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2021-11-11 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 67857 |  | 200000 | 100000 |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:30 |  |  | 2022 | Order and Notification
59925 | Defer project | 35226865 | 120449208 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2021-11-11 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 67857 |  | 200000 | 100000 |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:30 |  |  | 2022 | Order and Notification
59941 | Defer project | 35226864 | 120449207 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2021-11-11 | 2022-11-20 | 80 | 67857 | 2021 | 2022 | 2022 |  | 67857 |  | 100000 | 100000 |  | 2021-12-31 | ADER |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:29 |  |  | 2022 | Order and Notification
59942 | Defer project | 35226863 | 120449205 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies | 2021-11-11 | 2022-11-20 | 648.8 | 338825.78 | 2021 | 2022 | 2022 |  | 67857 |  | 100000 | 100000 |  | 2021-12-31 | PEND |  | 2021-11-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:28 |  |  | 2022 | Order and Notification
59927 | Defer project | 35226862 | 120449204 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:27 |  |  | 2022 | Order and Notification
59922 | Defer project | 35226861 | 120449203 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:26 |  |  | 2022 | Order and Notification
59918 | Defer project | 35226859 | 120449202 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:25 |  |  | 2022 | Order and Notification
59933 | Defer project | 35226858 | 120449201 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-12-23 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  | 300000 |  | 300000 | 100000 |  | 2021-12-31 | UNSE |  | 2022-12-23 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:24 |  |  | 2022 | Order and Notification
59938 | Defer project | 35226857 | 120449200 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-09 | 2022-11-20 | 80 | 155000 | 2021 | 2022 | 2022 |  | 500000 |  | 500000 | 100000 |  | 2021-12-31 | ESTS |  | 2023-01-09 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:22 |  |  | 2022 | Order and Notification
59915 | Defer project | 35174501 | 118913026 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2023-01-17 | 2022-11-20 | 123 | 118750 | 2021 | 2022 | 2022 | 10000 | 500000 |  | 500000 | 100000 |  | 2021-12-31 | ESTS |  | 2023-01-17 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:21 |  |  | 2022 | Order and Notification
59917 | Defer project | 35174479 | 118913025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 83 | 67857 | 2021 | 2022 | 2022 | 15000 | 300000 |  | 300000 | 100000 |  | 2021-12-31 | ADER |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-18 21:20 |  |  | 2022 | Order and Notification
59916 | Defer project | 35174478 | 118913024 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [6 empty] | Defer to 2022 workplan due to long lead dependencies (i.e. Caltrans) | 2022-11-01 | 2022-11-20 | 123 | 155000 | 2021 | 2022 | 2022 | 10000 | 500000 | 0 | 500000 | 100000 |  | 2021-12-31 | ESTS |  | 2022-11-01 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-18 21:18 |  |  | 2022 | Order and Notification
59913 | Add project | 35220896 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Approved | 08W | [6 empty] | Fire hardening job needs to be added to work plan | 2022-12-31 |  |  |  | 2022 | 2022 | [8 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-26 10:40 |  |  | 2021-03-18 17:37 |  |  |  | Not in Work Plan
59912 | Update work plan date | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Denied | 08W | [6 empty] | Mileage forecasted for FY 2022; updating project report year from FY2021 to FY2022 | 2021-10-13 | 2022-09-14 | 80 | 312500 | 2021 | 2022 | [7 empty] | 2023-12-31 | ADER |  | 2021-10-13 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 17:02 |  |  | 2022 | Order and Notification
59902 | Update work plan date | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-29 | 2022-09-09 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:45 |  |  | 2022 | Order and Notification
59903 | Update work plan date | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-29 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:45 |  |  | 2022 | Order and Notification
59904 | Update work plan date | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-14 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-14 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:45 |  |  | 2022 | Order and Notification
59909 | Update work plan date | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-29 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:45 |  |  | 2022 | Order and Notification
59906 | Update work plan date | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-01 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-01 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:44 |  |  | 2022 | Order and Notification
59911 | Update work plan date | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-29 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:44 |  |  | 2022 | Order and Notification
59910 | Update work plan date | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:43 |  |  | 2022 | Order and Notification
59908 | Update work plan date | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59907 | Update work plan date | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-26 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-26 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59905 | Update work plan date | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59900 | Update work plan date | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-26 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-10-26 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59899 | Update work plan date | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-17 |  | 346.6 | 132166.93 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-11-17 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59901 | Update work plan date | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-26 |  | 111.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-26 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59898 | Update work plan date | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-05 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [7 empty] | Approved | [7 empty] | Denied | Looks like should be Deferral request. Also needs Update Work Plan Date and Updated Construction Complete Date |  | 2021-03-25 14:22 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59897 | Update work plan date | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-25 | 2022-11-15 | 674.2 | 360825.19 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-11-25 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:42 |  |  | 2022 | Order and Notification
59896 | Update work plan date | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-10 | 2022-07-27 | 131.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-10 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:41 |  |  | 2022 | Order and Notification
59895 | Update work plan date | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-10 | 2022-08-10 | 130.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-10 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:41 |  |  | 2022 | Order and Notification
59894 | Update work plan date | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-15 | 2022-07-27 | 131.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-15 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:41 |  |  | 2022 | Order and Notification
59893 | Update work plan date | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2022-01-19 | 2022-08-17 | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:41 |  |  | 2022 | Order and Notification
59892 | Update work plan date | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-12-08 | 2022-07-07 | 110.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-08 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:31 |  |  | 2022 | Order and Notification
59891 | Update work plan date | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-27 | 2022-09-14 | 83 | 312500 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-27 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:30 |  |  | 2022 | Order and Notification
59890 | Update work plan date | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-11-09 | 2022-07-07 | 111.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-09 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:29 |  |  | 2022 | Order and Notification
59889 | Update work plan date | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-27 | 2022-07-07 | 110.1 | 250000 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2021-10-27 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:28 |  |  | 2022 | Order and Notification
59888 | Update work plan date | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Denied | 08W | [6 empty] | Mileage forecasted for 2022; updating the project reporting year from 2021 to 2022 | 2021-10-13 | 2022-09-14 | 80 | 312500 | 2021 | 2022 | [7 empty] | 2023-12-31 | ADER |  | 2021-10-13 | [7 empty] | Approved | [7 empty] | Denied | Should be deferral request. Also, must provide Updated Construction Complete Date. |  | 2021-03-25 14:18 |  |  | 2021-03-18 16:27 |  |  | 2022 | Order and Notification
59856 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Denied | 08W | [7 empty] | 2022-10-11 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-10-11 | [15 empty] | Denied | Requested resource matches the current resource on the work plan |  | 2021-03-19 20:02 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59835 | Resource change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [7 empty] | 2021-09-03 |  | 932 | 3246777 | 2021 |  |  |  | 1680411 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-09-03 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59852 | Resource change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [7 empty] | 2021-07-28 |  | 4409.1 | 8067020 | 2021 |  |  |  | 5388290 |  |  |  |  | 2022-03-03 | UNSC |  | 2021-07-28 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59853 | Resource change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1062.1 | 7339020 | 2021 |  |  |  | 4828290 |  |  |  |  | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59854 | Resource change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1647.2 | 6383520 | 2021 |  |  |  | 4093290 |  |  |  |  | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59847 | Resource change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [7 empty] | 2021-07-30 |  | 979.2 | 3378623 | 2021 |  |  |  | 1781831 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59845 | Resource change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [7 empty] | 2021-07-26 |  | 351.3 | 2470520 | 2021 |  |  |  | 1083290 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59846 | Resource change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [7 empty] | 2021-07-30 |  | 909 | 3444978 | 2021 |  |  |  | 1832873 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59841 | Resource change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [7 empty] | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59843 | Resource change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [7 empty] | 2021-08-20 |  | 552.9 | 3715565 | 2021 |  |  |  | 2041017 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59844 | Resource change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [7 empty] | 2021-09-22 |  | 487.4 | 2622014 | 2021 |  |  |  | 1199824 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-09-22 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59840 | Resource change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [7 empty] | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59842 | Resource change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [7 empty] | 2021-07-16 |  | 994.5 | 3535462 | 2021 |  |  |  | 1902476 |  |  |  |  | 2022-01-01 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59838 | Resource change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [7 empty] | 2021-08-17 |  | 1051.6 | 3728491 | 2021 |  |  |  | 2050960 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59839 | Resource change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [7 empty] | 2021-09-09 |  | 742.6 | 2743520 | 2021 |  |  |  | 1293290 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-09-09 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59837 | Resource change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [7 empty] | 2021-06-14 |  | 2886.6 | 6280110 | 2021 |  |  |  | 4013744 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59836 | Resource change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [7 empty] | 2021-06-14 |  | 1328.6 | 4778094 | 2021 |  |  |  | 2858347 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59851 | Resource change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1103.5 | 6429020 | 2021 |  |  |  | 4128290 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59850 | Resource change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [7 empty] | 2021-07-19 |  | 5336.9 | 9341020 | 2021 |  |  |  | 6368290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59849 | Resource change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [7 empty] | 2021-07-19 |  | 2405 | 7066020 | 2021 |  |  |  | 4618290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59848 | Resource change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1673 | 7748520 | 2021 |  |  |  | 5143290 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-18 11:18 |  |  | 2021 | Order and Notification
59799 | Resource change | 35227033 | 120449807 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Denied | 08W | [7 empty] | 2021-11-30 |  | 80 | 237833 | 2021 |  |  |  | 237833 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-30 | [15 empty] | Denied | Requested resource matches the current resource on the work plan |  | 2021-03-19 20:02 |  |  | 2021-03-18 10:50 |  |  | 2021 | Order and Notification
59798 | Resource change | 35227032 | 120449806 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Denied | 08W | [7 empty] | 2021-10-01 |  | 522 | 201909.68 | 2021 |  |  |  | 237833 |  |  |  |  | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Denied | Requested resource matches the current resource on the work plan |  | 2021-03-19 20:02 |  |  | 2021-03-18 10:50 |  |  | 2021 | Order and Notification
59797 | Resource change | 35191937 | 119553837 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Denied | 08W | [7 empty] | 2021-10-01 |  | 0 | 237833 | 2021 |  |  |  | 237833 |  |  |  |  | 2022-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Denied | Requested resource matches the current resource on the work plan |  | 2021-03-19 20:02 |  |  | 2021-03-18 10:50 |  |  | 2021 | Order and Notification
59582 | Resource change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [7 empty] | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 | 2022 |  | 48176.5 | 500000 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | [15 empty] | Approved |  |  | 2021-03-17 15:57 |  |  | 2021-03-17 15:21 |  |  | 2022 | Order and Notification
59576 | Defer project | 35223030 | 120242544 | PSPS - BANGOR 1101 CB - MICROGRID | Approved | 08W |  | 2022 |  |  |  |  | Per project Manager, This will be a 2022 project due to the underground scope | 2021-10-19 | 2022-12-31 | 80 | 950000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 1495000 | 0 | 2021-12-31 | ESTS |  | 2021-10-19 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-17 10:21 |  |  | 2022 | Order and Notification
59567 | Add project | 35235320 |  | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3500000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59568 | Add project | 35237889 |  | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 4795000 | 0 | 0 |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59569 | Add project | 35237890 |  | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2835000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59570 | Add project | 35237891 |  | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 1610000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59571 | Add project | 35237893 |  | FRRB - WYANDOTTE 1103 - W3 PH3.5 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 1015000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59572 | Add project | 35237894 |  | FRRB - WYANDOTTE 1103 - W3 PH3.6 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3010000 | 0 | 0 |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59573 | Add project | 35237895 |  | *CANC* WYANDOTTE 1103 -W3 PH3.7 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2765000 | 0 | 0 |  | CNCL | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59574 | Add project | 35237896 |  | FRRB - WYANDOTTE 1103 - W3 PH3.8 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 3885000 | 0 | 0 |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59575 | Add project | 35236990 |  | FRRB - WYANDOTTE 1103 - W3 PH3.9 | Approved | 08W | [6 empty] | Adding this project to 2021 WP as part of NCFR Program | 2021-12-31 |  |  |  |  | 2021 |  |  |  | 0 | 2730000 | 0 | 0 |  | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-03-17 09:45 |  |  |  | Not in Work Plan
59465 | Resource change | 35219266 | 120141949 | CWSP - MARIPOSA 2102CB PH 1 | Approved | 08W | [7 empty] | 2021-09-13 |  | 4713.7 | 1304482.44 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-09-13 | [15 empty] | Approved |  |  | 2021-03-17 15:57 |  |  | 2021-03-16 19:22 |  |  | 2021 | Order and Notification
59466 | Resource change | 35227263 | 120457435 | CWSP - MARIPOSA 2102CB PH 2 | Approved | 08W | [7 empty] | 2021-07-20 |  | 2088.9 | 1012126.18 | 2021 |  |  |  | 1670921 |  |  |  |  | 2021-12-31 | CONS |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-03-17 15:57 |  |  | 2021-03-16 19:22 |  |  | 2021 | Order and Notification
53119 | Remove project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Order was originally reviewed by WFGC and approved based on information that 15 poles had been previously installed. Information related to previous construction however was incorrect and thus WFGC has retracted approval inlieu of more higher priority work. Requesting order be removed from MPP Workplan until further notice. | [14 empty] | UNSC | [11 empty] | Approved |  |  | Approved |  |  | Approved |  |  | 2021-03-19 19:56 |  |  | 2021-03-15 10:35 |  |  |  | Not in Work Plan
53066 | Resource change | 35026643 | 114258488 | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W | [7 empty] | 2022-10-11 |  | 35.1 | 100000 | 2021 |  |  | 10430.5 | [5 empty] | 2020-12-31 | ESTS |  | 2022-10-11 | [15 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-12 13:54 |  |  | 2021 | Order and Notification
53038 | Update work plan date | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-05-11 | 2022-09-30 | 330.1 | 247500 | 2021 | 2022 | 2022 |  | 92967 |  | 5000 |  |  | 2021-12-31 | ADER |  | 2022-05-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-06 09:38 |  |  | 2021-03-12 12:15 |  |  | 2022 | Order and Notification
53039 | Defer project | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-20 | 2022-09-30 | 2080.1 | 950000 | 2021 | 2022 | 2022 |  | 102942 |  | 10816 |  |  | 2021-12-31 | ESTS |  | 2022-04-20 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-04-06 09:37 |  |  | 2021-03-12 12:09 |  |  | 2022 | Order and Notification
53037 | Defer project | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-12-16 | 2022-06-30 | 80 | 1 | 2021 | 2022 | 2022 |  | 267945.29 |  | 267945.29 | 1364658.88 |  | 2023-12-31 | ESTS |  | 2021-12-16 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-12 12:06 |  |  | 2022 | Order and Notification
53045 | Defer project | 35231543 | 120504099 | CWSP - TIDEWATER 210614072 PH 1.2 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-25 | 2022-09-30 | 80 | 350000 | 2021 | 2022 | 2022 |  | 5000 |  | 5000 |  |  | 2021-12-31 | ESTS |  | 2022-04-25 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-12 12:04 |  |  | 2022 | Order and Notification
53047 | Defer project | 35219096 | 120141671 | CWSP - KIRKER 2104442850 PH 1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-25 | 2022-09-30 | 80 | 500000 | 2021 | 2022 | 2022 |  | 8302 |  | 8302 |  |  | 2021-12-31 | UNSE |  | 2022-04-25 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-12 12:02 |  |  | 2022 | Order and Notification
53046 | Defer project | 35219093 | 120141622 | CWSP - TIDEWATER 210614072 PH 1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-25 | 2022-09-30 | 80 | 350000 | 2021 | 2022 | 2022 |  | 8255 |  | 8255 |  |  | 2021-12-31 | UNSE |  | 2022-04-25 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-12 12:01 |  |  | 2022 | Order and Notification
53048 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-05-09 | 2022-09-30 | 180 | 550000 | 2021 | 2022 | 2022 |  | 852800 |  | 193996.68 |  |  | 2023-12-31 | ESTS |  | 2022-05-09 | [7 empty] | Denied | Per [REDACTED] | [6 empty] | Denied | Denied by Estimating |  | 2021-03-25 14:19 |  |  | 2021-03-12 11:59 |  |  | 2022 | Order and Notification
53041 | Defer project | 35232650 | 120529254 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-12 | 2022-07-07 | 80 | 316667 | 2021 | 2022 | 2022 |  | 162264.96 |  | 162264.96 | 5177530.95 |  | 2021-12-31 | ESTS |  | 2022-04-12 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-12 11:56 |  |  | 2022 | Order and Notification
53040 | Defer project | 35223036 | 120242599 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2021-12-07 | 2022-09-30 | 80 | 500000 | 2021 | 2022 | 2022 |  | 120000 |  | 85970 |  |  | 2021-12-31 | ESTS |  | 2021-12-07 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-12 11:54 |  |  | 2022 | Order and Notification
53044 | Defer project | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-03-31 | 2022-07-07 | 110.1 | 316666 | 2021 | 2022 | 2022 |  | 201100.86 |  | 201100.86 | 7569489.75 |  | 2021-12-31 | ESTS |  | 2022-03-31 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-12 11:52 |  |  | 2022 | Order and Notification
53042 | Defer project | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-04-07 | 2022-09-30 | 131.1 | 309269 | 2021 | 2022 | 2022 | 22.4 | 402000 |  | 364360.62 | 7660323.65 |  | 2020-12-31 | ESTS |  | 2022-04-07 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-12 11:46 |  |  | 2022 | Order and Notification
53043 | Defer project | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W |  | N/A |  |  |  |  | Due to the current status of this UG SH project and all of the dependencies needed to be completed the execution will need to be in 2022 | 2022-07-11 | 2022-07-29 | 111.1 | 451282 | 2021 | 2022 | 2022 | 365.3 | 231000 |  | 153434.85 | 4723361.6 |  | 2020-12-31 | ESTS |  | 2022-07-11 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-12 11:43 |  |  | 2022 | Order and Notification
53002 | Update work plan date | 35226857 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | ESTS | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
53003 | Update work plan date | 35227007 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | UNSE | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
53001 | Update work plan date | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Denied | 08W | [6 empty] | Underground work in CT ROW causing a shift to 2022 fulfillment. | 2021-12-01 | 2022-12-01 | [12 empty] | ESTS | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
52997 | Update work plan date | 35226864 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
52998 | Update work plan date | 35226865 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
52999 | Update work plan date | 35226866 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | ADER | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
53000 | Update work plan date | 35226870 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | PEND | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:09 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
52996 | Update work plan date | 35226863 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Denied | 08W | [6 empty] | later EOD's causing feasibility to construct in 2021 less likely due to high volume of work in same area for 2021 | 2021-12-01 | 2022-12-01 | [12 empty] | PEND | [9 empty] | Approved | [7 empty] | Denied | Needs to be defer request. And needs Construction Complete Date. |  | 2021-03-25 14:08 |  |  | 2021-03-12 08:26 |  |  |  | Not in Work Plan
52988 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Denied | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 2388716 | 75000 | 0 | 0 | 0 | 0 | 2019-12-31 | DOCC | 2020-08-21 | [16 empty] | Denied | Duplicate of change ID 52984 |  | 2021-03-16 18:00 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52984 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 2388716 | 75000 | 0 | 0 | 0 | 0 | 2019-12-31 | DOCC | 2020-08-21 | [16 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52987 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Denied | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-08-26 | [16 empty] | Denied | Duplicate of change ID 52983 |  | 2021-03-16 18:00 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52983 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Approved | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-08-26 | [16 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52982 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-10-02 | [16 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52986 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Denied | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-10-02 | [16 empty] | Denied | Duplicate of change ID 52982 |  | 2021-03-16 18:00 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52981 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2874679 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-09-04 | [16 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52985 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Denied | 08W | 220 Mile Plan | [5 empty] | Return $75k to the program since the project is closed now. Nothing spent in 2021 | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2874679 | 75000 | 0 | 0 | 0 | 0 | 2020-12-31 | DOCC | 2020-09-04 | [16 empty] | Denied | Duplicate of change ID 52981 |  | 2021-03-16 18:00 |  |  | 2021-03-11 13:32 |  |  | 2020 | Order and Notification
52961 | Resource change | 35191937 | 119553837 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Approved | 08W | [7 empty] | 2021-10-01 |  | 0 | 237833 | 2021 |  |  |  | 237833 |  |  |  |  | 2022-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:31 |  |  | 2021 | Order and Notification
52962 | Resource change | 35227032 | 120449806 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Approved | 08W | [7 empty] | 2021-10-01 |  | 522 | 201909.68 | 2021 |  |  |  | 237833 |  |  |  |  | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:31 |  |  | 2021 | Order and Notification
52963 | Resource change | 35227033 | 120449807 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Approved | 08W | [7 empty] | 2021-11-30 |  | 80 | 237833 | 2021 |  |  |  | 237833 |  |  |  |  | 2021-12-31 | UNSE |  | 2021-11-30 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:31 |  |  | 2021 | Order and Notification
52930 | Resource change | 35227007 | 120449533 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W | [7 empty] | 2023-01-17 |  | 80 | 118750 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-17 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52931 | Resource change | 35227010 | 120449536 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W | [7 empty] | 2023-01-31 |  | 80 | 118750 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52932 | Resource change | 35227013 | 120449539 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W | [7 empty] | 2023-01-31 |  | 80 | 118750 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52933 | Resource change | 35227015 | 120449710 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W | [7 empty] | 2023-01-31 |  | 80 | 118750 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52934 | Resource change | 35227018 | 120449711 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W | [7 empty] | 2023-01-31 |  | 80 | 118750 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52935 | Resource change | 35227021 | 120449712 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W | [7 empty] | 2023-01-31 |  | 80 | 118750 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2023-01-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52936 | Resource change | 35227025 | 120449714 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W | [7 empty] | 2022-11-23 |  | 80 | 118750 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-11-23 | [15 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52925 | Resource change | 35226857 | 120449200 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W | [7 empty] | 2023-01-09 |  | 80 | 155000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2023-01-09 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52926 | Resource change | 35226858 | 120449201 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W | [7 empty] | 2022-12-23 |  | 80 | 155000 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-12-23 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52927 | Resource change | 35226859 | 120449202 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W | [7 empty] | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52928 | Resource change | 35226861 | 120449203 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W | [7 empty] | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52929 | Resource change | 35226862 | 120449204 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W | [7 empty] | 2022-11-01 |  | 80 | 155000 | 2021 | 2022 |  |  | 300000 |  |  |  |  | 2021-12-31 | UNSE |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52920 | Resource change | 35174478 | 118913024 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [7 empty] | 2022-11-01 |  | 123 | 155000 | 2021 | 2022 |  | 10000 | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-11-01 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52921 | Resource change | 35174501 | 118913026 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [7 empty] | 2023-01-17 |  | 123 | 118750 | 2021 | 2022 |  | 10000 | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2023-01-17 | [15 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52946 | Resource change | 35219281 | 120142240 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W | [7 empty] | 2022-03-31 |  | 110.1 | 316666 | 2021 | 2022 |  |  | 201100.86 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-03-31 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52939 | Resource change | 35219589 | 120165231 | CWSP - WILDWOOD 11011454 | Approved | 08W | [7 empty] | 2022-04-20 |  | 2080.1 | 950000 | 2021 | 2022 |  |  | 102942 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-04-20 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52923 | Resource change | 35223343 | 120255838 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | Approved | 08W | [7 empty] | 2021-06-21 |  | 1360.3 | 5929383 | 2021 |  |  |  | 4015922 |  |  |  |  | 2021-12-31 | PEND |  | 2021-06-21 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2021 | Order and Notification
52940 | Resource change | 35224321 | 120401277 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W | [7 empty] | 2022-05-11 |  | 330.1 | 247500 | 2021 | 2022 |  |  | 92967 |  |  |  |  | 2021-12-31 | ADER |  | 2022-05-11 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 11:25 |  |  | 2022 | Order and Notification
52924 | Resource change | 35225821 | 120424578 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | Approved | 08W | [7 empty] | 2021-07-19 |  | 1284.4 | 5417838 | 2021 |  |  |  | 3241252 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 11:25 |  |  | 2021 | Order and Notification
52938 | Resource change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [7 empty] | 2021-05-14 |  | 1598.4 | 3591121 | 2021 |  |  | 370000 | 2229051.5 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-14 | [15 empty] | Approved |  |  | 2021-03-16 17:51 |  |  | 2021-03-11 11:25 |  |  | 2021 | Order and Notification
52903 | Resource change | 35231544 | 120504131 | CWSP - TIDEWATER 210614072 PH 1.3 | Approved | 08W | [7 empty] | 2021-07-19 |  | 2052.9 | 565748.51 | 2021 | [8 empty] | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-16 17:52 |  |  | 2021-03-11 09:40 |  |  | 2021 | Order and Notification
52900 | Defer project | 35226700 | 14272795 | CWSP - WYANDOTTE 110932586 PH 1.2 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-07-04 | 2022-12-31 |  |  | 2021 |  | 2022 |  |  | 0 | 500000 | 1495265 | 0 |  | ESTS | [9 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:20 |  |  | 2021-03-11 09:15 |  |  |  | Not in Work Plan
52883 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W | [6 empty] | Defer project to 2022. Project still in estimating and requires new land rights. | 2022-05-09 | 2022-05-01 | 180 | 550000 | 2021 | 2022 | 2022 |  | 852800 |  | 852800 | 2984800 | 426400 | 2023-12-31 | ESTS |  | 2022-05-09 | [7 empty] | Denied | Per [REDACTED] | [6 empty] | Denied | Denied by Estimating |  | 2021-03-25 14:19 |  |  | 2021-03-11 08:17 |  |  | 2022 | Order and Notification
52784 | Resource change | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [6 empty] | 3.10- [REDACTED] - added back to WP | 2021-10-01 |  | 428 | 1115282 | 2021 |  |  | 150000 | 755085 |  |  |  |  | 2018-12-28 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-03-11 00:04 |  |  | 2021-03-10 21:35 |  |  | 2021 | Order and Notification
52783 | Resource change | 31361965 | 113751296 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [6 empty] | 3.10- [REDACTED] - added back to WP | 2021-03-16 |  | 660.1 | 1245293 | 2021 |  |  | 287153 | 273723 |  |  |  |  | 2019-12-27 | FICL | 2021-04-24 | 2021-03-16 | [15 empty] | Approved |  |  | 2021-03-11 00:04 |  |  | 2021-03-10 21:34 |  |  | 2021 | Order and Notification
52594 | Budget change | 35192053 | 119554059 | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-08 |  | 3504.6 | 1877409.58 | 2021 |  |  |  | 2843023 |  | 2843023 |  |  | 2022-12-31 | CONS |  | 2021-02-08 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 15:43 |  |  | 2021 | Order and Notification
52593 | Budget change | 35227096 | 120457011 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 |  | 1203 | 326951.18 | 2021 |  |  |  | 2183706 |  | 2183706 |  |  | 2021-12-31 | CONS |  | 2021-02-22 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 15:25 |  |  | 2021 | Order and Notification
52592 | Defer project | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-10-14 | 2022-12-31 | 111.1 | 150000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 2370000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 15:03 |  |  | 2022 | Order and Notification
52591 | Defer project | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-05-02 | 2022-12-31 | 110.1 | 150000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 550000 | 0 | 2021-12-31 | ESTS |  | 2022-05-02 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 14:56 |  |  | 2022 | Order and Notification
61304 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-10-14 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5555000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [7 empty] | Approved |  |  |  |  | Denied | Duplicate of Change ID 52588 |  | Denied | Duplicate of Change ID 52588 |  | 2021-04-01 12:58 |  |  | 2021-03-10 14:31 |  |  | 2022 | Order and Notification
61303 | Update work plan date | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-10-14 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5555000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [7 empty] | Approved |  |  |  |  | Denied | Duplicate of Change ID 52588 |  | Denied | Duplicate of Change ID 52588 |  | 2021-04-01 12:58 |  |  | 2021-03-10 14:31 |  |  | 2022 | Order and Notification
52588 | Defer project | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-10-14 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5555000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 14:31 |  |  | 2022 | Order and Notification
52589 | Defer project | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Denied | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-10-14 | 2022-12-31 | 111.1 | 200000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5555000 | 0 | 2021-12-31 | ESTS |  | 2021-10-14 | [7 empty] | Approved |  | Approved | Defer project approved |  | Denied | Duplicate of Change ID 52588 |  | Denied |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 14:31 |  |  | 2022 | Order and Notification
52586 | Defer project | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-08-08 | 2022-12-31 | 132 | 400000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5905000 | 0 | 2021-12-31 | ESTS |  | 2022-08-08 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 14:18 |  |  | 2022 | Order and Notification
52584 | Defer project | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2022-04-29 | 2022-12-31 | 132 | 400000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 15250000 | 0 | 2021-12-31 | ESTS |  | 2022-04-29 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved |  |  | 2021-03-26 11:16 |  |  | 2021-03-10 14:05 |  |  | 2022 | Order and Notification
52582 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [6 empty] | this project pulled back to 2021 WP. Requesting $2,229,051.5 in 2021 to allign with BC figures | 2021-05-14 |  | 1598.4 | 3591121 | 2021 |  |  | 370000 | 2229051.5 | 0 | 2229051.5 | 0 | 0 | 2020-12-31 | CONS |  | 2021-05-14 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 13:43 |  |  | 2021 | Order and Notification
52583 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Denied | 08W | [6 empty] | this project pulled back to 2021 WP. Requesting $2,229,051.5 in 2021 to allign with BC figures | 2021-05-14 |  | 1598.4 | 3591121 | 2021 |  |  | 370000 | 2229051.5 | 0 | 2229051.5 | 0 | 0 | 2020-12-31 | CONS |  | 2021-05-14 | [15 empty] | Denied | Duplicate of change ID 52582 |  | 2021-03-11 00:03 |  |  | 2021-03-10 13:43 |  |  | 2021 | Order and Notification
52578 | Budget change | 35217275 | 120048103 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Approved | 08W | [6 empty] | Requesting 2021MPP $10,150,000. using Avarage cost for UG per mile $3.5M. The project mile is 2.90 | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 10150000 | 0 | 10150000 | 0 | 0 | 2021-12-31 | ESTS |  | 2022-09-21 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 11:30 |  |  | 2021 | Order and Notification
52577 | Budget change | 35217274 | 120048101 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Approved | 08W | [6 empty] | Requesting 2021MPP $7,805,000. using Avarage cost for UG per mile $3.5M. The project mile is 2.23 | 2022-10-05 |  | 80 | 500000 | 2021 |  |  |  | 7805000 | 0 | 7805000 | 0 | 0 | 2021-12-31 | ESTS |  | 2022-10-05 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 11:28 |  |  | 2021 | Order and Notification
52576 | Budget change | 35235707 | 120594569 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [6 empty] | Requesting 2021 Budget $3,325,000. project is 0.95 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 1647.2 | 6383520 | 2021 |  |  |  | 4093290 | 0 | 3325000 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 10:07 |  |  | 2021 | Order and Notification
52572 | Budget change | 35235706 | 120594568 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [6 empty] | Requesting 2021 Budget $4,060,000. project is 1.16 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 1062.1 | 7339020 | 2021 |  |  |  | 4828290 | 0 | 4060000 | 0 | 0 | 2022-03-03 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 10:05 |  |  | 2021 | Order and Notification
52571 | Budget change | 35235705 | 120594567 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [6 empty] | Requesting 2021 Budget $4,620,000. project is 1.32 mile. Using avarege cost $3.5M for UG | 2021-07-28 |  | 4409.1 | 8067020 | 2021 |  |  |  | 5388290 | 0 | 4620000 | 0 | 0 | 2022-03-03 | UNSC |  | 2021-07-28 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 10:02 |  |  | 2021 | Order and Notification
52569 | Budget change | 35233315 | 120541636 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [6 empty] | Requesting 2021 Budget $3,360,000. project is 0.96 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 1103.5 | 6429020 | 2021 |  |  |  | 4128290 | 0 | 3360000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 09:59 |  |  | 2021 | Order and Notification
52575 | Budget change | 35233314 | 120541635 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [6 empty] | Requesting 2021 Budget $5,600,000. project is 1.6 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 5336.9 | 9341020 | 2021 |  |  |  | 6368290 | 0 | 5600000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 09:57 |  |  | 2021 | Order and Notification
52574 | Budget change | 35233312 | 120541634 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [6 empty] | Requesting 2021 Budget $3,850,000. project is 1.1 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 2405 | 7066020 | 2021 |  |  |  | 4618290 | 0 | 3850000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 09:55 |  |  | 2021 | Order and Notification
52573 | Budget change | 35233311 | 120541633 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [6 empty] | Requesting 2021 Budget $4,375,000. project is 1.25 mile. Using avarege cost $3.5M for UG | 2021-07-19 |  | 1673 | 7748520 | 2021 |  |  |  | 5143290 | 0 | 4375000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 09:52 |  |  | 2021 | Order and Notification
52570 | Budget change | 35232718 | 120538803 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | Requesting 2021 Budget $4,200,000. project is 1.2 mile. Using avarege cost $3.5M for UG | 2021-07-16 |  | 1433.2 | 4335155 | 2021 |  |  |  | 2518289.22 | 0 | 4200000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-10 09:50 |  |  | 2021 | Order and Notification
52447 | Add project | 35219286 |  | CWSP - DESCHUTES 11049718 PH1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52443 | Add project | 35232442 |  | CWSP - DESCHUTES 11049718 PH 2.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52444 | Add project | 35232443 |  | CWSP - DESCHUTES 11049718 PH 2.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52445 | Add project | 35232444 |  | CWSP - DESCHUTES 11049718 PH 2.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52446 | Add project | 35232445 |  | CWSP - DESCHUTES 11049718 PH 2.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52448 | Add project | 35232960 |  | CWSP - DESCHUTES 11049718 PH1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:47 |  |  |  | Not in Work Plan
52442 | Add project | 35225825 |  | CWSP - DESCHUTES 11049718 PH2.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | 2021-12-31 |  |  |  | 2021 | [9 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 New construction Complete year |  | 2021-03-16 17:57 |  |  | 2021-03-10 08:46 |  |  |  | Not in Work Plan
52438 | Budget change | 35061206 | 115106231 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | inherited this project from [REDACTED].requesting 2021 budget$1,419,181 to allign with approved BC | 2020-06-15 |  | 2491.1 | 4711641 | 2020 | 2021 |  | 3596290.1 | 1419181 | 0 | 1419181 | 0 | 0 | 2020-12-31 | CONS |  | 2020-06-15 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 21:22 |  |  | 2021 | Order and Notification
52437 | Budget change | 35117443 | 117634567 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Approved | 08W | 220 Mile Plan | [5 empty] | this job inhertted from [REDACTED] Requesting $2,450,191 to allign with the approved BC | 2020-07-28 |  | 5134.2 | 5778810 | 2020 | 2021 |  | 4175407.8 | 2450191 | 0 | 2450191 | 0 | 0 | 2020-12-31 | MAPP | 2021-05-13 | 2020-07-28 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 21:12 |  |  | 2021 | Order and Notification
52436 | Budget change | 35226631 | 120445423 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W | [6 empty] | requesting $2,926,000 for 2021. project miles 1.54 | 2021-07-27 |  | 2283.6 | 765014.63 | 2021 |  |  |  | 2926000 | 0 | 2926000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 20:43 |  |  | 2021 | Order and Notification
52435 | Budget change | 35226630 | 120445421 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W | [6 empty] | requesting $2,736,000 for 2021. project miles is 1.44 | 2021-08-10 |  | 2407.9 | 497898.74 | 2021 |  |  |  | 2736000 | 0 | 2736000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-10 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 20:43 |  |  | 2021 | Order and Notification
52434 | Budget change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W | [6 empty] | requesting $551,000 for 2021. project miles 0.3 | 2022-03-01 |  | 690.1 | 150000 | 2021 | 2022 |  |  | 380000 | 0 | 380000 | 0 | 0 | 2021-12-31 | PEND |  | 2022-03-01 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 20:42 |  |  | 2022 | Order and Notification
52433 | Budget change | 35226627 | 120445375 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W | [6 empty] | requesting $551,000 for 2021. project miles 0.3 | 2021-07-26 |  | 111.1 | 150000 | 2021 |  |  |  | 551000 | 0 | 551000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 20:42 |  |  | 2021 | Order and Notification
52432 | Budget change | 35219260 | 120141880 | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W | [6 empty] | requesting $1.52M for 2021. using avarage cost per mile for 08W $1.9M. The project miles is 0.8 | 2021-07-20 |  | 0.6 | 564057.38 | 2021 |  |  |  | 1520000 | 0 | 1520000 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 20:31 |  |  | 2021 | Order and Notification
52431 | Defer project | 35223039 | 120242691 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Approved | 08W |  | 2022 |  |  |  |  | Per PM, this job is not going to be constructed in 2021 | 2021-09-15 | 2022-12-31 | 80 | 950000 | 2021 | 2022 | 2022 |  | 500000 | 0 | 500000 | 5905000 | 0 | 2021-12-31 | ESTS |  | 2021-09-15 | [7 empty] | Approved |  | Approved | Defer project approved |  | Approved |  |  | Approved | Approve so long as all info is provided |  | 2021-03-26 11:20 |  |  | 2021-03-09 15:59 |  |  | 2022 | Order and Notification
52425 | Budget change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-08-17 |  | 1051.6 | 3728491 | 2021 |  |  |  | 2050960 | 0 | 1282670.45 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52424 | Budget change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-07-30 |  | 909 | 3444978 | 2021 |  |  |  | 1832873 | 0 | 1064583.33 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52423 | Budget change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-07-30 |  | 979.2 | 3378623 | 2021 |  |  |  | 1781831 | 0 | 1013541.67 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52422 | Budget change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-08-27 |  | 723.9 | 3159481 | 2021 |  |  |  | 1614125 | 0 | 845833.33 | 0 | 0 | 2022-01-01 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52421 | Budget change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-08-20 |  | 552.9 | 3715565 | 2021 |  |  |  | 2041017 | 0 | 1272727.27 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52420 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 | 0 | 813352.27 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:51 |  |  | 2021 | Order and Notification
52419 | Budget change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-06-14 |  | 2886.6 | 6280110 | 2021 |  |  |  | 4013744 | 0 | 1761818.18 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:50 |  |  | 2021 | Order and Notification
52418 | Budget change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-06-14 |  | 1328.6 | 4778094 | 2021 |  |  |  | 2858347 | 0 | 2090056.82 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:50 |  |  | 2021 | Order and Notification
52417 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 | 0 | 1283333.33 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:50 |  |  | 2021 | Order and Notification
52416 | Budget change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | Per [REDACTED], requesting the MPP budget to allign with 2021 forecast not the AA approved amount. Using $1.9M avarege cost per mile for OH and $3.5M for UG. Multiplie the project mile by the respective rate. | 2021-07-16 |  | 994.5 | 3535462 | 2021 |  |  |  | 1902476 | 0 | 1134185.61 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-03-10 23:49 |  |  | 2021-03-09 14:50 |  |  | 2021 | Order and Notification
52134 | Pull-in Project from Future Year | 31334291 |  | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Denied | 08W | [6 empty] | Program requested project to move to 2021 workplan | 2021-06-30 |  |  |  |  | 2021 | [8 empty] | PEND | [11 empty] | Approved | [5 empty] | Denied | Project not on MPP work plan |  | 2021-03-18 09:55 |  |  | 2021-03-08 14:59 |  |  |  | Not in Work Plan
52133 | Pull-in Project from Future Year | 31361965 |  | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Denied | 08W | [6 empty] | Program requested project to move to 2021 workplan | 2021-03-31 |  |  |  |  | 2021 | [8 empty] | FICL | 2021-04-24 | [10 empty] | Approved | [5 empty] | Denied | Project not on MPP work plan |  | 2021-03-18 09:55 |  |  | 2021-03-08 14:59 |  |  |  | Not in Work Plan
51957 | Resource change | 35231609 | 120504096 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W | [7 empty] | 2021-06-14 |  | 2057.5 | 3699056 | 2021 |  |  |  | 2505000 |  |  |  |  | 2021-12-31 | CONS |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51955 | Resource change | 35231607 | 120504093 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W | [7 empty] | 2021-06-22 |  | 1226.4 | 3032237 | 2021 |  |  |  | 1974000 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-06-22 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51956 | Resource change | 35231608 | 120504095 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W | [7 empty] | 2022-07-25 |  | 310.3 | 209584 | 2021 | 2022 |  |  | 62873 |  |  |  |  | 2021-12-31 | PEND |  | 2022-07-25 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2022 | Order and Notification
51953 | Resource change | 35226630 | 120445421 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W | [7 empty] | 2021-08-10 |  | 2407.9 | 497898.74 | 2021 |  |  |  | 2736000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-10 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51951 | Resource change | 35226628 | 120445377 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W | [7 empty] | 2021-10-14 |  | 111.1 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2022 | Order and Notification
51952 | Resource change | 35226629 | 120445378 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W | [7 empty] | 2021-10-14 |  | 111.1 | 200000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-14 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2022 | Order and Notification
51954 | Resource change | 35226631 | 120445423 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W | [7 empty] | 2021-07-27 |  | 2283.6 | 765014.63 | 2021 |  |  |  | 2926000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51948 | Resource change | 35226845 | 120448987 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W | [7 empty] | 2021-07-06 |  | 2256.4 | 1101405.78 | 2021 |  |  |  | 2519287 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-06 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51950 | Resource change | 35226627 | 120445375 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W | [7 empty] | 2021-07-26 |  | 111.1 | 150000 | 2021 |  |  |  | 551000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51947 | Resource change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W | [7 empty] | 2021-05-26 |  | 4089.8 | 6586891 | 2021 |  |  |  | 4901112 |  |  |  |  | 2021-12-31 | CONS |  | 2021-05-26 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51946 | Resource change | 35225822 | 120424579 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W | [7 empty] | 2021-03-01 |  | 2971.5 | 4380690 | 2021 |  |  |  | 3743276.52 |  |  |  |  | 2021-12-31 | CONS |  | 2021-03-01 | [15 empty] | Approved |  |  | 2021-03-04 11:14 |  |  | 2021-03-04 10:47 |  |  | 2021 | Order and Notification
51873 | Budget change | 35233307 | 120541538 | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-06-14 |  | 1328.6 | 4778094 | 2021 |  |  |  | 2858347 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51872 | Budget change | 35233305 | 120542507 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-07-30 |  | 979.2 | 3378623 | 2021 |  |  |  | 1781831 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51870 | Budget change | 35233308 | 120541539 | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-06-14 |  | 2886.6 | 6280110 | 2021 |  |  |  | 4013744 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51866 | Budget change | 35233300 | 120542502 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-07-16 |  | 994.5 | 3535462 | 2021 |  |  |  | 1902476 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-16 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51868 | Budget change | 35233303 | 120542505 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-07-26 |  | 351.3 | 2470520 | 2021 |  |  |  | 1083290 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-26 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51871 | Budget change | 35233039 | 120542500 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-08-27 |  | 905.4 | 3729353 | 2021 |  |  |  | 4103246 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51867 | Budget change | 35232298 | 120532441 | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-08-27 |  | 723.9 | 3159481 | 2021 |  |  |  | 1614125 | 0 | 500000 | 0 | 0 | 2022-01-01 | PEND |  | 2021-08-27 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51869 | Budget change | 35233306 | 120541535 | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-09-03 |  | 932 | 3246777 | 2021 |  |  |  | 1680411 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-09-03 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51862 | Budget change | 35233038 | 120542278 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-06-14 |  | 1357.6 | 3118378 | 2021 |  |  |  | 3163284 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51863 | Budget change | 35233302 | 120542504 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-09-22 |  | 487.4 | 2622014 | 2021 |  |  |  | 1199824 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-09-22 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51864 | Budget change | 35233301 | 120542503 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-08-20 |  | 552.9 | 3715565 | 2021 |  |  |  | 2041017 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-08-20 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51860 | Budget change | 35233309 | 120541630 | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-08-17 |  | 1051.6 | 3728491 | 2021 |  |  |  | 2050960 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-08-17 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51861 | Budget change | 35233310 | 120541632 | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-09-09 |  | 742.6 | 2743520 | 2021 |  |  |  | 1293290 | 0 | 500000 | 0 | 0 | 2021-12-31 | UNSC |  | 2021-09-09 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51865 | Budget change | 35233304 | 120542506 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | requeting $500k to algin with AA budget for 2021 | 2021-07-30 |  | 909 | 3444978 | 2021 |  |  |  | 1832873 | 0 | 500000 | 0 | 0 | 2022-01-01 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 10:24 |  |  | 2021 | Order and Notification
51803 | Add project | 35233312 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51805 | Add project | 35233315 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51806 | Add project | 35235705 |  | FRRB - WYANDOTTE 1103 - W2 PH2.6 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51801 | Add project | 35232718 |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51808 | Add project | 35235707 |  | FRRB - WYANDOTTE 1103 - W2 PH2.8 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51804 | Add project | 35233314 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51802 | Add project | 35233311 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51807 | Add project | 35235706 |  | FRRB - WYANDOTTE 1103 - W2 PH2.7 | Approved | 08W | [6 empty] | requesting to add this project to the WP as part of NCFR program | 2021-12-31 | [5 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-04 09:14 |  |  |  | Not in Work Plan
51754 | Budget change | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2022-04-07 |  | 131.1 | 309269 | 2021 | 2022 |  | 22.4 | 402000 |  | 364360.62 | 7660323.65 |  | 2020-12-31 | ESTS |  | 2022-04-07 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-04 08:17 |  |  | 2022 | Order and Notification
51753 | Resource change | 35223037 | 120242694 | PSPS - OAKHURST 1101 - OAKHURST | Approved | 08W | [7 empty] | 2021-08-11 |  | 366 | 124376.18 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-11 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-04 08:17 |  |  | 2021 | Order and Notification
51749 | Resource change | 35219097 | 120141762 | CWSP - COARSEGOLD 2104CB PH 1.1 | Approved | 08W | [7 empty] | 2021-08-13 |  | 2777.3 | 1648337.84 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-13 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-04 08:17 |  |  | 2021 | Order and Notification
51750 | Resource change | 35227260 | 120457078 | CWSP - COARSEGOLD 2104CB PH 1.2 | Approved | 08W | [7 empty] | 2021-07-14 |  | 83.4 | 955916.43 | 2021 | [8 empty] | 2021-12-31 | UNSC |  | 2021-07-14 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-04 08:17 |  |  | 2021 | Order and Notification
51751 | Resource change | 35227261 | 120457111 | CWSP - COARSEGOLD 2104CB PH 1.3 | Approved | 08W | [7 empty] | 2021-07-27 |  | 1579.8 | 747358.84 | 2021 | [8 empty] | 2021-12-31 | UNSC |  | 2021-07-27 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-04 08:17 |  |  | 2021 | Order and Notification
51752 | Resource change | 35227262 | 120457115 | CWSP - COARSEGOLD 2104CB PH 1.4 | Approved | 08W | [7 empty] | 2021-07-20 |  | 1487.4 | 886518.78 | 2021 | [8 empty] | 2021-12-31 | UNSC |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-04 08:17 |  |  | 2021 | Order and Notification
51727 | Add project | 35085847 | 113255606 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | Approved | 08W | [6 empty] | Keep relations with regulators | 2022-10-21 |  | 1380.2 | 5136422 | 2022 |  | 2022 | 6463.1 | 1353842.8 |  |  |  |  | 2019-09-30 | PEND |  | 2022-10-21 | [12 empty] | Approved |  |  | Approved | Approved with 2022 completion year |  | 2021-03-08 15:19 |  |  | 2021-03-04 07:32 |  |  | 2022 | Order and Notification
51726 | Add project | 35015704 | 113255603 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | Approved | 08W | [6 empty] | Keep relations with regulators | 2022-01-04 |  | 1186.4 | 99000 | 2022 |  | 2022 | 5945.7 | 1196.1 |  |  |  |  | 2019-09-30 | PEND |  | 2022-01-04 | [12 empty] | Approved |  |  | Approved | Approved with 2022 completion year |  | 2021-03-08 15:19 |  |  | 2021-03-04 07:32 |  |  | 2022 | Order and Notification
51724 | Resource change | 35217271 | 120048017 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Approved | 08W | [7 empty] | 2022-01-05 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-03 20:35 |  |  | 2022 | Order and Notification
51723 | Resource change | 35217269 | 120048011 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Approved | 08W | [7 empty] | 2022-01-19 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-19 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-03 20:34 |  |  | 2022 | Order and Notification
51722 | Resource change | 35192282 | 119556300 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W | [7 empty] | 2021-10-27 |  | 110.1 | 250000 | 2021 | 2022 | [7 empty] | 2023-12-31 | UNSE |  | 2021-10-27 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-03 20:34 |  |  | 2022 | Order and Notification
51721 | Resource change | 35192281 | 119556250 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 90000 | 2021 | [8 empty] | 2023-12-31 | APPR |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-03-04 10:38 |  |  | 2021-03-03 20:34 |  |  | 2021 | Order and Notification
51755 | Budget change | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 & 2022 workplan. | 2022-07-11 |  | 111.1 | 451282 | 2021 | 2022 |  | 365.3 | 231000 |  | 153434.85 | 4723361.6 |  | 2020-12-31 | ESTS |  | 2022-07-11 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 16:21 |  |  | 2022 | Order and Notification
51672 | Budget change | 35226847 | 120449140 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-06-07 |  | 1439.4 | 3048485 | 2021 |  |  |  | 2124000 |  | 3812484.87 |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51675 | Budget change | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2022-09-01 |  | 2438.1 | 1313564.84 | 2021 | 2022 |  |  | 153000 |  | 7975840.77 |  |  | 2021-12-31 | PEND |  | 2022-09-01 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2022 | Order and Notification
51671 | Budget change | 35226853 | 120449146 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-30 |  | 3342.2 | 5538787 | 2021 |  |  |  | 3709152 |  | 5802223.75 |  |  | 2021-12-31 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51674 | Budget change | 35226856 | 120449149 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-15 |  | 847.8 | 2418866 | 2021 |  |  |  | 1640040 |  | 8862572.16 |  |  | 2021-12-31 | UNSC |  | 2021-07-15 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51673 | Budget change | 35226854 | 120449147 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-07-01 |  | 1852.6 | 4710436 | 2021 |  |  |  | 3199346 |  | 2086816.03 |  |  | 2021-12-31 | CONS |  | 2021-07-01 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51670 | Budget change | 35231607 | 120504093 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-06-22 |  | 1226.4 | 3032237 | 2021 |  |  |  | 1974000 |  | 2867422.68 |  |  | 2021-12-31 | UNSC |  | 2021-06-22 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51669 | Budget change | 35231609 | 120504096 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-06-14 |  | 2057.5 | 3699056 | 2021 |  |  |  | 2505000 |  | 2649841.53 |  |  | 2021-12-31 | CONS |  | 2021-06-14 | [15 empty] | Approved |  |  | 2021-03-04 15:14 |  |  | 2021-03-03 15:27 |  |  | 2021 | Order and Notification
51562 | Budget change | 35226846 | 120448989 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting MPP budget be added officially to the 2021 workplan | 2021-06-07 |  | 1531.1 | 3178496 | 2021 |  |  |  | 2090271.93 |  | 3089168.45 |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-03-03 17:48 |  |  | 2021-03-03 09:17 |  |  | 2021 | Order and Notification
51541 | Budget change | 35223343 | 120255838 | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | Approved | 08W | [6 empty] | Requesting 2021 Budget to cover the budget for UG construction for 2021 for North Complex Fire Rebuild | 2021-06-21 |  | 1360.3 | 5929383 | 2021 |  |  |  | 4015922 | 0 | 3490209.3 | 0 | 0 | 2021-12-31 | PEND |  | 2021-06-21 | [15 empty] | Approved |  |  | 2021-03-03 17:48 |  |  | 2021-03-02 14:44 |  |  | 2021 | Order and Notification
51540 | Budget change | 35225821 | 120424578 | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | Approved | 08W | [6 empty] | Requesting 2021 Budget to cover the budget for UG construction for 2021 for North Complex Fire Rebuild | 2021-07-19 |  | 1284.4 | 5417838 | 2021 |  |  |  | 3241252 | 0 | 3490167.5 | 0 | 0 | 2021-12-31 | PEND |  | 2021-07-19 | [15 empty] | Approved |  |  | 2021-03-03 17:48 |  |  | 2021-03-02 14:44 |  |  | 2021 | Order and Notification
51514 | Budget change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [6 empty] | Project pulled into the 2021 workplan, approved by Wildfire Governanace Ciommittee | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 | 2022 |  | 48176.5 | 500000 |  | 4178901 |  |  | 2021-12-20 | PEND |  | 2021-12-30 | [15 empty] | Approved |  |  | 2021-03-03 17:48 |  |  | 2021-03-02 11:50 |  |  | 2022 | Order and Notification
51396 | Update work plan date | 35174479 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | Request change in project work plan date as project was recently approved by the WFGC to pull into 2021. | 2022-12-31 | 2021-12-31 |  |  | 2021 | 2021 | [8 empty] | ADER | [9 empty] | Approved | [7 empty] | Approved |  |  | 2021-03-08 15:25 |  |  | 2021-03-01 20:01 |  |  |  | Not in Work Plan
51374 | Add project | 35114051 |  | OCGC PINE GROVE 1102 - LR1222 - PH | Approved | 08W | [6 empty] | Per [REDACTED], this project was approved to continue executing on 2/25/21. | 2021-06-30 | [5 empty] | 2021 |  |  |  | 2575321 |  |  |  | MAPP | 2021-05-26 | [13 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 |  |  | 2021-03-01 10:02 |  |  |  | Not in Work Plan
51211 | Defer project | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W | [6 empty] | 2021 not realistic with 1.64 miles of UG with new lands rights. Defer project to 2022 | 2022-05-09 | 2022-05-01 | 180 | 550000 | 2021 | 2022 | 2022 |  | 852800 |  | 852800 | 2984800 | 426400 | 2023-12-31 | ESTS |  | 2022-05-09 | [7 empty] | Approved |  | Approved | Defer approved, [REDACTED] notified |  | Approved |  |  | Approved |  |  | 2021-03-19 19:59 |  |  | 2021-02-25 14:53 |  |  | 2022 | Order and Notification
51073 | Resource change | 35192291 | 119556091 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W | [7 empty] | 2021-12-16 |  | 80 | 1 | 2021 | 2022 |  |  | 267945.29 |  |  |  |  | 2023-12-31 | ESTS |  | 2021-12-16 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51072 | Resource change | 35192290 | 119556075 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W | [7 empty] | 2021-09-16 |  | 80 | 1 | 2021 | [8 empty] | 2023-12-31 | ESTS |  | 2021-09-16 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51113 | Resource change | 35219260 | 120141880 | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W | [7 empty] | 2021-07-20 |  | 0.6 | 564057.38 | 2021 | 2021 |  |  | 1520000 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51129 | Resource change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [7 empty] | 2021-04-05 |  | 1354.7 | 11016312 | 2021 |  |  |  | 8094904 |  |  |  |  | 2021-12-31 | CONS |  | 2021-04-05 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51127 | Resource change | 35223345 | 120255982 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W | [7 empty] | 2021-02-16 |  | 5043.2 | 10700839 | 2021 |  |  |  | 9514299.24 |  |  |  |  | 2021-12-31 | CONS |  | 2021-02-16 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51078 | Resource change | 35226623 | 120445227 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W | [7 empty] | 2021-11-09 |  | 111.1 | 150000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51079 | Resource change | 35226624 | 120445228 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W | [7 empty] | 2021-09-07 |  | 672.1 | 302731.26 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-09-07 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51077 | Resource change | 35226622 | 120445225 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 111.1 | 150000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51076 | Resource change | 35226621 | 120445224 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W | [7 empty] | 2022-01-26 |  | 111.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2022-01-26 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51126 | Resource change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W | [7 empty] | 2021-02-12 |  | 762.8 | 10286697 | 2021 |  |  |  | 6324922 |  |  |  |  | 2021-12-31 | DOCC | 2021-04-15 | 2021-02-12 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51075 | Resource change | 35220895 | 120221891 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Approved | 08W | [7 empty] | 2021-11-09 |  | 111.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51071 | Resource change | 35219273 | 120142173 | CWSP - VOLTA 110149742 | Approved | 08W | [7 empty] | 2021-09-17 |  | 2734.5 | 633229.22 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-09-17 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51074 | Resource change | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W | [7 empty] | 2022-07-11 |  | 111.1 | 451282 | 2021 | 2022 |  | 365.3 | 231000 |  |  |  |  | 2020-12-31 | ESTS |  | 2022-07-11 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51080 | Resource change | 35227027 | 120449717 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W | [7 empty] | 2021-09-29 |  | 110.1 | 92500 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51083 | Resource change | 35227030 | 120449801 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Approved | 08W | [7 empty] | 2021-10-26 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-26 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51081 | Resource change | 35227028 | 120449719 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 92500 | 2021 | 2021 | [7 empty] | 2021-12-31 | ADER |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51082 | Resource change | 35227029 | 120449800 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W | [7 empty] | 2021-09-07 |  | 998.8 | 447830.94 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-09-07 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51084 | Resource change | 35227031 | 120449802 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Approved | 08W | [7 empty] | 2021-10-26 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-10-26 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51085 | Resource change | 35226819 | 120456652 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Approved | 08W | [7 empty] | 2021-12-29 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51090 | Resource change | 35227164 | 120456658 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Approved | 08W | [7 empty] | 2021-12-01 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51091 | Resource change | 35227165 | 120456740 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Approved | 08W | [7 empty] | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51088 | Resource change | 35227162 | 120456655 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Approved | 08W | [7 empty] | 2021-12-29 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51089 | Resource change | 35227163 | 120456657 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Approved | 08W | [7 empty] | 2021-12-29 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51087 | Resource change | 35227161 | 120456654 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Approved | 08W | [7 empty] | 2021-12-14 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-14 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51086 | Resource change | 35227160 | 120456653 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Approved | 08W | [7 empty] | 2021-12-29 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51105 | Resource change | 35229119 | 120496477 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W | [7 empty] | 2021-10-15 |  | 1371.6 | 409121.04 | 2021 | 2021 |  |  | 475000 |  |  |  |  | 2021-12-31 | ESTS |  | 2021-10-15 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51103 | Resource change | 35228187 | 120475324 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 733.5 | 482466.54 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51104 | Resource change | 35228188 | 120475326 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Approved | 08W | [7 empty] | 2021-10-20 |  | 110.1 | 250000 | 2021 | 2021 | [7 empty] | 2021-12-31 | UNSE |  | 2021-10-20 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51099 | Resource change | 35227866 | 120462238 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 75000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51100 | Resource change | 35227867 | 120462241 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Approved | 08W | [7 empty] | 2021-10-01 |  | 110.1 | 80000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ADER |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51101 | Resource change | 35227868 | 120462242 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Approved | 08W | [7 empty] | 2021-10-26 |  | 110.1 | 80000 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-26 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51102 | Resource change | 35228186 | 120475322 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Approved | 08W | [7 empty] | 2021-12-08 |  | 110.1 | 250000 | 2021 | 2022 | [7 empty] | 2021-12-31 | UNSE |  | 2021-12-08 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51092 | Resource change | 35227167 | 120456741 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Approved | 08W | [7 empty] | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51093 | Resource change | 35227168 | 120456742 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Approved | 08W | [7 empty] | 2022-02-09 |  | 110.1 | 1 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-02-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51094 | Resource change | 35227860 | 120462186 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Approved | 08W | [7 empty] | 2021-08-11 |  | 80.4 | 64653.56 | 2021 | 2021 | [7 empty] | 2021-12-31 | ESTS |  | 2021-08-11 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51095 | Resource change | 35227861 | 120462188 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Approved | 08W | [7 empty] | 2021-10-01 |  | 822.4 | 404711.27 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-10-01 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51096 | Resource change | 35227862 | 120462232 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Approved | 08W | [7 empty] | 2021-08-25 |  | 913.3 | 400710.04 | 2021 | 2021 | [7 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51097 | Resource change | 35227863 | 120462233 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Approved | 08W | [7 empty] | 2021-09-29 |  | 110.1 | 80000 | 2021 | 2021 | [7 empty] | 2021-12-31 | APPR |  | 2021-09-29 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51098 | Resource change | 35227864 | 120462234 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [7 empty] | 2022-01-05 |  | 110.1 | 200000 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2022-01-05 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51116 | Resource change | 35232280 | 120527401 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Approved | 08W | [7 empty] | 2021-06-09 |  | 741 | 465706.54 | 2021 | 2021 |  |  | 667231 |  |  |  |  | 2021-12-31 | CONS |  | 2021-06-09 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2021 | Order and Notification
51058 | Resource change | 35217272 | 120048018 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W | [7 empty] | 2022-05-02 |  | 110.1 | 150000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-05-02 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:22 |  |  | 2022 | Order and Notification
51045 | Resource change | 35191319 | 119518398 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Approved | 08W | [7 empty] | 2021-10-13 |  | 80 | 312500 | 2021 | 2022 | [7 empty] | 2023-12-31 | ADER |  | 2021-10-13 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:11 |  |  | 2022 | Order and Notification
51046 | Resource change | 35223615 | 120401360 | ECOP - LAS GALLINAS A 1105 PH 2 | Approved | 08W | [7 empty] | 2021-10-27 |  | 83 | 312500 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-10-27 | [15 empty] | Approved |  |  | 2021-02-25 11:22 |  |  | 2021-02-25 10:11 |  |  | 2022 | Order and Notification
50828 | Budget change | 35219275 | 120142210 | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [6 empty] | Respectfully request MPP Budget Approved 2021 for $950k. This project is currently on the WP 2021. | 2021-07-20 |  | 832.6 | 656614.03 | 2021 |  |  |  | 950000 | 0 | 950000 | 0 | 0 | 2021-12-31 | CONS |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-02-25 16:22 |  |  | 2021-02-24 15:34 |  |  | 2021 | Order and Notification
50827 | Budget change | 35219291 | 120141627 | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Respectfully request MPP Budget Approved 2021 for $1.2M. This project is currently on the WP 2021. Business case to be routed next month. | 2021-08-03 |  | 421.2 | 165125.99 | 2021 |  |  |  | 1265910 | 0 | 1265910 | 0 | 0 | 2021-12-31 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-02-25 16:22 |  |  | 2021-02-24 15:34 |  |  | 2021 | Order and Notification
50654 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | adding this project to 2021 as part of NCFR | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 14:12 |  |  |  | Not in Work Plan
50650 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 14:06 |  |  |  | Not in Work Plan
50652 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 14:06 |  |  |  | Not in Work Plan
50653 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 14:06 |  |  |  | Not in Work Plan
50651 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | adding this project as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 14:06 |  |  |  | Not in Work Plan
50634 | Add project | 35232298 |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50637 | Add project | 35233300 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50639 | Add project | 35233302 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50641 | Add project | 35233304 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50642 | Add project | 35233305 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50635 | Add project | 35233038 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50636 | Add project | 35233039 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50644 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50638 | Add project | 35233301 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50640 | Add project | 35233303 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50643 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50646 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50647 | Add project | 35233310 |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50645 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | Adding this project to the workplan as part of North Complex Fire Rebuild | 2021-12-31 | [13 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-23 13:48 |  |  |  | Not in Work Plan
50625 | Budget change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W | [6 empty] | Requesting $150k for 2021 to cover Estimating and dependency work | 2022-03-01 |  | 690.1 | 150000 | 2021 | 2022 |  |  | 380000 | 0 | 150000 | 0 | 0 | 2021-12-31 | PEND |  | 2022-03-01 | [15 empty] | Approved |  |  | 2021-02-25 16:22 |  |  | 2021-02-23 11:16 |  |  | 2022 | Order and Notification
50624 | Budget change | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W | [6 empty] | Requesting $400k for 2021 to cover Estimating and dependency work | 2022-08-08 |  | 132 | 400000 | 2021 | 2022 |  |  | 500000 | 0 | 400000 | 0 | 0 | 2021-12-31 | ESTS |  | 2022-08-08 | [15 empty] | Approved |  |  | 2021-02-25 16:22 |  |  | 2021-02-23 11:15 |  |  | 2022 | Order and Notification
50623 | Budget change | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W | [6 empty] | Requesting $400k for 2021 to cover Estimating and dependency work | 2022-04-29 |  | 132 | 400000 | 2021 | 2022 |  |  | 500000 | 0 | 400000 | 0 | 0 | 2021-12-31 | ESTS |  | 2022-04-29 | [15 empty] | Approved |  |  | 2021-02-25 16:22 |  |  | 2021-02-23 11:15 |  |  | 2022 | Order and Notification
50586 | Budget change | 35116443 |  | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Respectfully request $22k to be moved into the MPP Approved Budget 2021, due to a late invoice coming in. | [9 empty] | 0 | 22000 | 194071 |  |  | CONS | [17 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-22 09:09 |  |  |  | Not in Work Plan
50567 | Add project | 35174501 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50578 | Add project | 35223039 |  | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50573 | Add project | 35227021 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50583 | Add project | 35231544 |  | CWSP - TIDEWATER 210614072 PH 1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50579 | Add project | 35219096 |  | CWSP - KIRKER 2104442850 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50582 | Add project | 35231543 |  | CWSP - TIDEWATER 210614072 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50576 | Add project | 35227032 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50580 | Add project | 35227655 |  | CWSP - KIRKER 2104442850 PH 1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50564 | Add project | 35226859 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50570 | Add project | 35227013 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50574 | Add project | 35227025 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50566 | Add project | 35226862 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50563 | Add project | 35226858 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50569 | Add project | 35227010 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50562 | Add project | 35226857 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50571 | Add project | 35227015 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50577 | Add project | 35227033 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50581 | Add project | 35219093 |  | CWSP - TIDEWATER 210614072 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50565 | Add project | 35226861 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50568 | Add project | 35227007 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50572 | Add project | 35227018 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50575 | Add project | 35191937 |  | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50561 | Add project | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [6 empty] | Project was recently approved by the WFGC and requesting to pull into 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-20 15:21 |  |  |  | Not in Work Plan
50501 | Resource change | 35226241 | 120431331 | CWSP - MARIPOSA 210197142 PH 2 | Approved | 08W | [7 empty] | 2021-08-25 |  | 1742.6 | 485124.83 | 2021 |  |  |  | 1218823 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 14:02 |  |  | 2021 | Order and Notification
50502 | Resource change | 35226240 | 120431332 | CWSP - MARIPOSA 210197142 PH 3 | Approved | 08W | [7 empty] | 2021-07-21 |  | 1336.8 | 655862.69 | 2021 |  |  |  | 1365471 |  |  |  |  | 2021-12-31 | PEND |  | 2021-07-21 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 14:02 |  |  | 2021 | Order and Notification
50498 | Resource change | 35217267 | 120047657 | SH - MARIPOSA 2102 LR 241564 | Approved | 08W | [7 empty] | 2021-07-14 |  | 1268.6 | 691633.47 | 2021 |  |  |  | 1220483 |  |  |  |  | 2021-12-31 | CONS |  | 2021-07-14 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 14:02 |  |  | 2021 | Order and Notification
50500 | Resource change | 35219268 | 120142035 | CWSP - MARIPOSA 210197142 PH 1 | Approved | 08W | [7 empty] | 2021-09-14 |  | 3531.3 | 1289702.13 | 2021 |  |  |  | 1670921 |  |  |  |  | 2021-12-31 | PEND |  | 2021-09-14 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 14:02 |  |  | 2021 | Order and Notification
50376 | Budget change | 35103065 | 114592041 | CWSP - MORAGA 1101 - LR 108540 PH 1 | Approved | 08W | 220 Mile Plan | [5 empty] | Negative 2021 budget not correct. Updating to $1 for 2020 project (couldn't use $0) | 2019-12-18 |  | 2738.3 | 5151555 | 2020 |  |  | 241010.3 | -37865.9 |  | 0 | 1 |  | 2020-12-31 | FICL | 2019-12-18 | [16 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 10:34 |  |  | 2020 | Order and Notification
50374 | Budget change | 74022384 | 114753320 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Approved | 08W | 220 Mile Plan | [5 empty] | Updating 2021 Budget to complete project and close out. | 2020-06-08 |  | 8146.3 | 9998553 | 2020 | 2021 |  | 3838756.17 | 2395900 |  | 2395900 | 1 |  | 2020-12-31 | CONS |  | 2020-06-08 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 10:34 |  |  | 2021 | Order and Notification
50377 | Budget change | 35053033 | 114688204 | CWSP - TASSAJARA 2112 - FUSE 18053 | Approved | 08W | 220 Mile Plan | [5 empty] | Updating 2021 Budget for project close out. | 2019-12-03 |  | 11746.9 | 9709000 | 2020 |  |  | 8728000 | 368855 |  | 368855 | 1 |  | 2019-12-31 | FICL | 2021-01-13 | 2019-12-03 | [15 empty] | Approved |  |  | 2021-02-22 14:11 |  |  | 2021-02-19 10:22 |  |  | 2020 | Order and Notification
50375 | Update work plan date | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Denied | 08W | [6 empty] | 2021 not realistic with 1.64 miles of UG with new lands rights | 2022-05-09 | 2021-05-01 | 180 | 550000 | 2021 | 2022 |  |  | 852800 |  |  |  |  | 2023-12-31 | ESTS |  | 2022-05-09 | [7 empty] | Approved | [7 empty] | Denied | Hi My-Linh and Merih, There is update date request in queue for the 08W job below. I'm not clear on the ask: note says "2021 not realistic with 1.64 miles of UG with new lands rights" and updated work plan date is earlier in 2021 than previous date. Please reply back with: 1. Correct Updated Work Plan Date 2. Construction Complete Year Order Notification Order Description 35192280 119556070 ECOP - CLAYTON 2212 - H01-LR2951 Going forward, please ensure that the notes align with the request and the minimum info above is provided. Thanks, Bret |  | 2021-03-08 16:53 |  |  | 2021-02-19 10:20 |  |  | 2022 | Order and Notification
50371 | Add project | 35219291 |  | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Add to MPP | 2022-02-23 | [13 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-18 16:55 |  |  |  | Not in Work Plan
50370 | Add project | 35219275 |  | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [6 empty] | Add project to MPP | 2021-12-09 | [13 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-25 16:47 |  |  | 2021-02-18 16:49 |  |  |  | Not in Work Plan
50329 | Resource change | 35192292 | 119556108 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Approved | 08W | [7 empty] | 2021-12-23 |  | 50.1 | 950000 | 2021 | 2022 |  |  | 200 |  |  |  |  | 2023-12-31 | ESTS |  | 2021-12-23 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50280 | Resource change | 35217268 | 120047659 | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W | [7 empty] | 2022-03-01 |  | 690.1 | 150000 | 2021 | 2022 |  |  | 380000 |  |  |  |  | 2021-12-31 | PEND |  | 2022-03-01 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50271 | Resource change | 35217270 | 120048013 | CWSP - KONOCTI 1102 LR 965078 PH1 | Approved | 08W | [7 empty] | 2021-12-10 |  | 130.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-10 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50276 | Resource change | 35219272 | 120142171 | CWSP - MIDDLETOWN 1101481876 | Approved | 08W | [7 empty] | 2021-08-25 |  | 483.8 | 184734.86 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50275 | Resource change | 35219098 | 120141805 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W | [7 empty] | 2021-08-16 |  | 514 | 198553.88 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50288 | Resource change | 35219291 | 120141627 | CWSP - VACA DIXON 1101126774 | Approved | 08W | [7 empty] | 2021-08-03 |  | 421.2 | 165125.99 | 2021 |  |  |  | 1265910 |  |  |  |  | 2021-12-31 | PEND |  | 2021-08-03 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50279 | Resource change | 35217273 | 120048019 | SH - UPPER LAKE 1101 CB | Approved | 08W | [7 empty] | 2021-11-25 |  | 674.2 | 360825.19 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-11-25 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50281 | Resource change | 35224712 | 120427328 | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W | [7 empty] | 2022-04-29 |  | 132 | 400000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-04-29 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50282 | Resource change | 35224713 | 120427329 | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W | [7 empty] | 2022-08-08 |  | 132 | 400000 | 2021 | 2022 |  |  | 500000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-08-08 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50272 | Resource change | 35225589 | 120423768 | CWSP - KONOCTI 1102 LR 965078 PH2 | Approved | 08W | [7 empty] | 2021-12-15 |  | 131.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-12-15 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50273 | Resource change | 35225591 | 120423769 | CWSP - KONOCTI 1102 LR 965078 PH3 | Approved | 08W | [7 empty] | 2021-11-10 |  | 131.1 | 316666 | 2021 | 2022 | [7 empty] | 2021-12-31 | ESTS |  | 2021-11-10 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50330 | Resource change | 35225594 | 120424183 | CNCL ECOP FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W | [7 empty] | 2022-01-18 |  | 50.1 | 1 | 2021 | 2022 |  |  | 200 |  |  |  |  | 2021-12-31 | DOCC |  | 2022-01-18 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50331 | Resource change | 35225595 | 120424186 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Approved | 08W | [7 empty] | 2021-10-06 |  | 664.8 | 327628.41 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-10-06 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50332 | Resource change | 35225597 | 120424187 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Approved | 08W | [7 empty] | 2021-08-24 |  | 571.8 | 355578.08 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-24 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50333 | Resource change | 35225598 | 120424188 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Approved | 08W | [7 empty] | 2021-08-24 |  | 762.2 | 448488.21 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-24 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50289 | Resource change | 35219275 | 120142210 | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [7 empty] | 2021-07-20 |  | 832.6 | 656614.03 | 2021 |  |  |  | 950000 |  |  |  |  | 2021-12-31 | CONS |  | 2021-07-20 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50277 | Resource change | 35219280 | 120142216 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Approved | 08W | [7 empty] | 2021-08-25 |  | 1792.2 | 929604.54 | 2021 | [8 empty] | 2021-12-31 | CONS |  | 2021-08-25 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50315 | Resource change | 35062375 | 115323921 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W | [7 empty] | 2022-01-07 |  | 131.1 | 1 | 2021 | 2022 |  | 58.9 | 200 |  |  |  |  | 2022-12-31 | ESTS |  | 2022-01-07 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50316 | Resource change | 35062376 | 115323922 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W | [7 empty] | 2022-04-07 |  | 131.1 | 309269 | 2021 | 2022 |  | 22.4 | 402000 |  |  |  |  | 2020-12-31 | ESTS |  | 2022-04-07 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50318 | Resource change | 35226846 | 120448989 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W | [7 empty] | 2021-06-07 |  | 1531.1 | 3178496 | 2021 |  |  |  | 2090271.93 |  |  |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50322 | Resource change | 35226850 | 120449143 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Approved | 08W | [7 empty] | 2021-06-10 |  | 1473.4 | 3060229 | 2021 |  |  |  | 1518941 |  |  |  |  | 2021-12-31 | CONS |  | 2021-06-10 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50323 | Resource change | 35226851 | 120449144 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Approved | 08W | [7 empty] | 2021-07-07 |  | 1753.7 | 3783519 | 2021 |  |  |  | 1871077 |  |  |  |  | 2021-12-31 | CONS |  | 2021-07-07 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50319 | Resource change | 35226847 | 120449140 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W | [7 empty] | 2021-06-07 |  | 1439.4 | 3048485 | 2021 |  |  |  | 2124000 |  |  |  |  | 2021-12-31 | CONS |  | 2021-06-07 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50320 | Resource change | 35226848 | 120449141 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Approved | 08W | [7 empty] | 2021-10-12 |  | 130.1 | 1 | 2021 | [8 empty] | 2021-12-31 | ADER |  | 2021-10-12 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50321 | Resource change | 35226849 | 120449142 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W | [7 empty] | 2021-12-13 |  | 130.1 | 1 | 2021 | 2022 |  |  | 200 |  |  |  |  | 2022-12-31 | ESTS |  | 2021-12-13 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50278 | Resource change | 35226632 | 120445424 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Approved | 08W | [7 empty] | 2021-11-17 |  | 346.6 | 132166.93 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2021-11-17 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50326 | Resource change | 35226854 | 120449147 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W | [7 empty] | 2021-07-01 |  | 1852.6 | 4710436 | 2021 |  |  |  | 3199346 |  |  |  |  | 2021-12-31 | CONS |  | 2021-07-01 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50327 | Resource change | 35226856 | 120449149 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W | [7 empty] | 2021-07-15 |  | 847.8 | 2418866 | 2021 |  |  |  | 1640040 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-15 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50324 | Resource change | 35226852 | 120449145 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [7 empty] | 2022-09-01 |  | 2438.1 | 1313564.84 | 2021 | 2022 |  |  | 153000 |  |  |  |  | 2021-12-31 | PEND |  | 2022-09-01 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2022 | Order and Notification
50325 | Resource change | 35226853 | 120449146 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W | [7 empty] | 2021-07-30 |  | 3342.2 | 5538787 | 2021 |  |  |  | 3709152 |  |  |  |  | 2021-12-31 | UNSC |  | 2021-07-30 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:18 |  |  | 2021 | Order and Notification
50167 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Denied | 08W | [7 empty] | 2021-02-08 |  | 2388.1 | 6518166 | 2021 |  |  |  | 3628388 |  |  |  |  | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | [15 empty] | Denied | Duplicate of Change ID 50144 |  | 2021-02-19 00:07 |  |  | 2021-02-18 10:07 |  |  | 2021 | Order and Notification
50152 | Resource change | 35223026 | 120245190 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Denied | 08W | [7 empty] | 2022-05-02 |  | 640 | 190000 | 2021 | 2022 |  |  | 180000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-05-02 | [15 empty] | Denied | Duplicate of Change ID 50129 |  | 2021-02-19 00:07 |  |  | 2021-02-18 10:07 |  |  | 2022 | Order and Notification
50154 | Resource change | 35223028 | 120245193 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Denied | 08W | [7 empty] | 2021-08-16 |  | 660.2 | 380810.72 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-16 | [15 empty] | Denied | Duplicate of Change ID 50131 |  | 2021-02-19 00:07 |  |  | 2021-02-18 10:07 |  |  | 2021 | Order and Notification
50151 | Resource change | 35223024 | 120245076 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Denied | 08W | [7 empty] | 2022-03-01 |  | 640 | 190000 | 2021 | 2022 |  |  | 180000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-03-01 | [15 empty] | Denied | Duplicate of Change ID 50128 |  | 2021-02-19 00:07 |  |  | 2021-02-18 10:07 |  |  | 2022 | Order and Notification
50153 | Resource change | 35223027 | 120245192 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Denied | 08W | [7 empty] | 2021-08-23 |  | 1926.9 | 728980.87 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-23 | [15 empty] | Denied | Duplicate of Change ID 50130 |  | 2021-02-19 00:07 |  |  | 2021-02-18 10:07 |  |  | 2021 | Order and Notification
50150 | Resource change | 35192284 | 119556691 | ECOP - SILVERADO 2104 - H05-LR726 | Denied | 08W | [7 empty] | 2022-01-10 |  | 80 | 400000 | 2021 | 2022 |  | 9859 | 380000 |  |  |  |  | 2023-12-31 | ESTS |  | 2022-01-10 | [15 empty] | Denied | Duplicate of Change ID 50127 |  | 2021-02-19 00:08 |  |  | 2021-02-18 10:07 |  |  | 2022 | Order and Notification
50155 | Resource change | 35191318 | 119518390 | ECOP - SILVERADO 2102 - H02-LR58626 | Denied | 08W | [7 empty] | 2021-09-16 |  | 1909.7 | 959851.78 | 2021 | [8 empty] | 2022-12-31 | PEND |  | 2021-09-16 | [15 empty] | Denied | Duplicate of Change ID 50132 |  | 2021-02-19 00:08 |  |  | 2021-02-18 10:07 |  |  | 2021 | Order and Notification
50156 | Resource change | 35191383 | 119518528 | ECOP - SILVERADO 2102 - H01-LR58626 | Denied | 08W | [7 empty] | 2021-08-16 |  | 869.7 | 614000 | 2021 | [8 empty] | 2023-12-31 | PEND |  | 2021-08-16 | [15 empty] | Denied | Duplicate of Change ID 50133 |  | 2021-02-19 00:08 |  |  | 2021-02-18 10:07 |  |  | 2021 | Order and Notification
50133 | Resource change | 35191383 | 119518528 | ECOP - SILVERADO 2102 - H01-LR58626 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2021-08-16 |  | 869.7 | 614000 | 2021 | [8 empty] | 2023-12-31 | PEND |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2021 | Order and Notification
50132 | Resource change | 35191318 | 119518390 | ECOP - SILVERADO 2102 - H02-LR58626 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2021-09-16 |  | 1909.7 | 959851.78 | 2021 | [8 empty] | 2022-12-31 | PEND |  | 2021-09-16 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2021 | Order and Notification
50127 | Resource change | 35192284 | 119556691 | ECOP - SILVERADO 2104 - H05-LR726 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2022-01-10 |  | 80 | 400000 | 2021 | 2022 |  | 9859 | 380000 |  |  |  |  | 2023-12-31 | ESTS |  | 2022-01-10 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2022 | Order and Notification
50131 | Resource change | 35223028 | 120245193 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2021-08-16 |  | 660.2 | 380810.72 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-16 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2021 | Order and Notification
50130 | Resource change | 35223027 | 120245192 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2021-08-23 |  | 1926.9 | 728980.87 | 2021 | [8 empty] | 2021-12-31 | PEND |  | 2021-08-23 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2021 | Order and Notification
50129 | Resource change | 35223026 | 120245190 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2022-05-02 |  | 640 | 190000 | 2021 | 2022 |  |  | 180000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-05-02 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2022 | Order and Notification
50128 | Resource change | 35223024 | 120245076 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2022-03-01 |  | 640 | 190000 | 2021 | 2022 |  |  | 180000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-03-01 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2022 | Order and Notification
50144 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Approved | 08W | [6 empty] | 2.18 Resource Updates | 2021-02-08 |  | 2388.1 | 6518166 | 2021 |  |  |  | 3628388 |  |  |  |  | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-18 10:00 |  |  | 2021 | Order and Notification
49792 | Resource change | 35227201 | 120457012 | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [7 empty] | 2021-02-02 |  | 791.2 | 512371.91 | 2021 |  |  |  | 2080934 |  |  |  |  | 2021-12-31 | CONS |  | 2021-02-02 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-17 21:11 |  |  | 2021 | Order and Notification
49791 | Resource change | 35227096 | 120457011 | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [7 empty] | 2021-02-22 |  | 1203 | 326951.18 | 2021 |  |  |  | 2183706 |  |  |  |  | 2021-12-31 | CONS |  | 2021-02-22 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-17 21:11 |  |  | 2021 | Order and Notification
49790 | Resource change | 35192053 | 119554059 | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [7 empty] | 2021-02-08 |  | 3504.6 | 1877409.58 | 2021 |  |  |  | 2843023 |  |  |  |  | 2022-12-31 | CONS |  | 2021-02-08 | [15 empty] | Approved |  |  | 2021-02-19 00:05 |  |  | 2021-02-17 21:11 |  |  | 2021 | Order and Notification
49702 | Add project | 35232280 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | Approved | 08W | [6 empty] | Approved Scope from WFGC and part of segment for original project order 35062375. | [6 empty] | 2021 | [7 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-17 10:09 |  |  |  | Not in Work Plan
49434 | Add project | 35227201 |  | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 12:41 |  |  |  | Not in Work Plan
49433 | Add project | 35227096 |  | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 12:41 |  |  |  | Not in Work Plan
49432 | Add project | 35192053 |  | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [6 empty] | 08W Fire Hardening Project | 2021-02-22 | [5 empty] | 2021 | [7 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 12:41 |  |  |  | Not in Work Plan
49396 | Add project | 35217269 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49390 | Add project | 35217272 |  | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49386 | Add project | 35226621 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49409 | Add project | 35227261 |  | CWSP - COARSEGOLD 2104CB PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49380 | Add project | 35227027 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49421 | Add project | 35227867 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49411 | Add project | 35219260 |  | CWSP - WYANDOTTE 110932586 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49397 | Add project | 35226819 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49383 | Add project | 35227030 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49399 | Add project | 35227161 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49417 | Add project | 35227862 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49418 | Add project | 35227863 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | APPR | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49424 | Add project | 35228186 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49426 | Add project | 35228188 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49385 | Add project | 35192282 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49407 | Add project | 35219097 |  | CWSP - COARSEGOLD 2104CB PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49389 | Add project | 35226624 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49395 | Add project | 35226631 |  | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49412 | Add project | 35226700 |  | CWSP - WYANDOTTE 110932586 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | 2022-07-21 |  | 111.1 | 650000 | 2021 | 2022 | 2021 |  | 500000 | [5 empty] | ESTS |  | 2022-07-21 | [12 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  | 2022 | Order Only
49398 | Add project | 35227160 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49402 | Add project | 35227164 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49419 | Add project | 35227864 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49423 | Add project | 35220895 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49406 | Add project | 35223037 |  | PSPS - OAKHURST 1101 - OAKHURST | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49381 | Add project | 35227028 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49405 | Add project | 35227168 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49392 | Add project | 35226628 |  | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49401 | Add project | 35227163 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49403 | Add project | 35227165 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49404 | Add project | 35227167 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49408 | Add project | 35227260 |  | CWSP - COARSEGOLD 2104CB PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49410 | Add project | 35227262 |  | CWSP - COARSEGOLD 2104CB PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49416 | Add project | 35227861 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49422 | Add project | 35227868 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49388 | Add project | 35226623 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49391 | Add project | 35226627 |  | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49382 | Add project | 35227029 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49420 | Add project | 35227866 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49414 | Add project | 35217271 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49427 | Add project | 35026643 |  | DIAMOND SPRINGS 1105 - LR 2102 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49384 | Add project | 35227031 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | UNSE | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49415 | Add project | 35227860 |  | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49387 | Add project | 35226622 |  | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49393 | Add project | 35226629 |  | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49394 | Add project | 35226630 |  | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49425 | Add project | 35228187 |  | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49400 | Add project | 35227162 |  | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49379 | Add project | 35192281 |  | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | Approved | 08W | [6 empty] | Project scope recently approved through the WFGC and requesting to be added to current year workplan. | [6 empty] | 2021 | [7 empty] | APPR | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-16 10:10 |  |  |  | Not in Work Plan
49364 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Insufficient funds to complete project. Additional funds needed to complete project in 2021, per work plan | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 435000 |  | 378038 | 0 | 0 | 2019-12-27 | FICL | 2021-02-12 | 2020-06-22 | [15 empty] | Approved |  |  | 2021-02-16 21:51 |  |  | 2021-02-16 00:21 |  |  | 2021 | Order and Notification
49363 | Budget change | 35116391 | 117605551 | CWSP - MIWUK 1702 - OCB - PH 1.2 | Denied | 08W | 220 Mile Plan | [5 empty] | Insufficient funds to complete project. Additional funds needed to complete project in 2021, per work plan | 2020-06-22 |  | 2329 | 3920203 | 2020 | 2021 |  | 4125714.8 | 435000 |  | 367484 | 0 | 0 | 2019-12-27 | FICL | 2021-02-12 | 2020-06-22 | [15 empty] | Denied | corrected budget on change ID 49364 |  | 2021-02-16 21:55 |  |  | 2021-02-16 00:13 |  |  | 2021 | Order and Notification
49106 | Resource change | 35217274 | 120048101 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY | Approved | 08W | [7 empty] | 2022-10-05 |  | 80 | 500000 | 2021 |  |  |  | 7805000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-10-05 | [15 empty] | Approved |  |  | 2021-02-16 21:51 |  |  | 2021-02-12 16:12 |  |  | 2021 | Order and Notification
49107 | Resource change | 35217275 | 120048103 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY | Approved | 08W | [7 empty] | 2022-09-21 |  | 80 | 500000 | 2021 |  |  |  | 10150000 |  |  |  |  | 2021-12-31 | ESTS |  | 2022-09-21 | [15 empty] | Approved |  |  | 2021-02-16 21:51 |  |  | 2021-02-12 16:12 |  |  | 2021 | Order and Notification
49101 | Resource change | 35075103 | 116475141 | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 | Approved | 08W | [7 empty] | 2021-06-28 |  | 686.3 | 403045.55 | 2021 |  |  |  | 490994.6 |  |  |  |  | 2020-12-30 | UNSC |  | 2021-06-28 | [15 empty] | Approved |  |  | 2021-02-16 21:51 |  |  | 2021-02-12 12:02 |  |  | 2021 | Order and Notification
49096 | Resource change | 35225593 | 120424181 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [7 empty] | 2022-06-13 |  | 1068.1 | 621258.86 | 2021 | 2022 | [7 empty] | 2021-12-31 | PEND |  | 2022-06-13 | [15 empty] | Approved |  |  | 2021-02-16 21:51 |  |  | 2021-02-12 11:52 |  |  | 2022 | Order and Notification
49071 | Add project | 35231608 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-11 13:20 |  |  |  | Not in Work Plan
49072 | Add project | 35231609 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-11 13:20 |  |  |  | Not in Work Plan
49070 | Add project | 35231607 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | Approved | 08W | [6 empty] | Additonal suborders created for WFGC approved segements under CWSP - SHINGLE SPRINGS 2109-LR 9372. Requesting to add to 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-11 13:20 |  |  |  | Not in Work Plan
48887 | Add project | 35229119 |  | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Approved | 08W | [6 empty] | Project is a segement of order 35219098 which was previously approved by the WFGC and requesting to add to current year workplan. | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-19 00:11 |  |  | 2021-02-11 10:02 |  |  |  | Not in Work Plan
48877 | Resource change | 35228449 | 120481753 | RIO DELL STORM REBUILD | Approved | 08W | [7 empty] | 2021-02-08 |  | 2388.1 | 6518166 | 2021 |  |  |  | 3628388 |  |  |  |  | 2021-06-30 | DOCC | 2021-03-01 | 2021-02-08 | [15 empty] | Approved |  |  | 2021-02-11 16:10 |  |  | 2021-02-10 22:55 |  |  | 2021 | Order and Notification
47375 | Budget change | 35225824 | 120424703 | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [6 empty] | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-04-05 |  | 1354.7 | 11016312 | 2021 |  |  |  | 8094904 | 0 | 8053977.27 | 0 | 0 | 2021-12-31 | CONS |  | 2021-04-05 | [15 empty] | Approved |  |  | 2021-02-09 11:28 |  |  | 2021-02-08 13:28 |  |  | 2021 | Order and Notification
47374 | Budget change | 35225823 | 120424672 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W | [6 empty] | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-05-26 |  | 4089.8 | 6586891 | 2021 |  |  |  | 4901112 | 0 | 4865530.3 | 0 | 0 | 2021-12-31 | CONS |  | 2021-05-26 | [15 empty] | Approved |  |  | 2021-02-09 11:28 |  |  | 2021-02-08 13:28 |  |  | 2021 | Order and Notification
47373 | Budget change | 35225822 | 120424579 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W | [6 empty] | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-03-01 |  | 2971.5 | 4380690 | 2021 |  |  |  | 3743276.52 | 0 | 3743276.52 | 0 | 0 | 2021-12-31 | CONS |  | 2021-03-01 | [15 empty] | Approved |  |  | 2021-02-09 11:28 |  |  | 2021-02-08 13:27 |  |  | 2021 | Order and Notification
47372 | Budget change | 35223345 | 120255982 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W | [6 empty] | Requesting 2021 Budget for UG main line under North Complex Fire Rebuild | 2021-02-16 |  | 5043.2 | 10700839 | 2021 |  |  |  | 9514299.24 | 0 | 9514299.24 | 0 | 0 | 2021-12-31 | CONS |  | 2021-02-16 | [15 empty] | Approved |  |  | 2021-02-09 11:28 |  |  | 2021-02-08 13:27 |  |  | 2021 | Order and Notification
47371 | Budget change | 35223344 | 120255980 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W | [6 empty] | request Budget for 2021 to match with 2021 EAC in BC | 2021-02-12 |  | 762.8 | 10286697 | 2021 |  |  |  | 6324922 | 0 | 6324922 | 0 | 0 | 2021-12-31 | DOCC | 2021-04-15 | 2021-02-12 | [15 empty] | Approved |  |  | 2021-02-09 11:28 |  |  | 2021-02-08 13:20 |  |  | 2021 | Order and Notification
47369 | Add project | 35142828 |  | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Denied | 08W | [6 empty] | Project is deffered but still accuring charges that budget is needed to cover | [14 empty] | CONS | [14 empty] | Approved |  |  | Denied | cannot be added to the plan without approvals from wildfire committee |  | 2021-02-11 20:26 |  |  | 2021-02-08 12:52 |  |  |  | Not in Work Plan
47368 | Add project | 35115152 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Denied | 08W | [6 empty] | Project is deffered but still accuring charges that budget is needed to cover | [14 empty] | CONS | [14 empty] | Approved |  |  | Denied | cannot be added to the plan without approvals from wildfire committee |  | 2021-02-11 20:26 |  |  | 2021-02-08 12:52 |  |  |  | Not in Work Plan
47367 | Add project | 35112425 |  | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 | Approved | 08W | [6 empty] | Close out costs | 2020-05-04 | [9 empty] | 75000 |  |  |  | MAPP | 2020-07-21 | [13 empty] | Approved |  |  | Approved |  |  | 2021-02-17 20:41 |  |  | 2021-02-08 12:48 |  |  |  | Not in Work Plan
45744 | Add project | 35228449 |  | RIO DELL STORM REBUILD | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | DOCC | 2021-03-01 | [13 empty] | Approved |  |  | Approved |  |  | 2021-02-11 16:10 |  |  | 2021-02-05 11:08 |  |  |  | Not in Work Plan
45743 | Add project | 35227096 |  | STRM - OAKHURST 1103 - LR 5120 PH 2 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-11 16:10 |  |  | 2021-02-05 11:08 |  |  |  | Not in Work Plan
45742 | Add project | 35227201 |  | STRM - OAKHURST 1103 - LR 5120 PH 3 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-11 16:10 |  |  | 2021-02-05 11:08 |  |  |  | Not in Work Plan
45741 | Add project | 35192053 |  | STRM-OAKHURST 1103-LR 5120 PH1 | Approved | 08W | [6 empty] | 08W Rebuild projects related to recent windstorm event that meets system hardening criteria for 2021 credit currently under construction. Requesting to be added to 2021 workplan. | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-11 16:10 |  |  | 2021-02-05 11:08 |  |  |  | Not in Work Plan
44818 | Resource change | 35094513 | 114567769 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | Approved | 08W | [7 empty] | 2021-12-30 |  | 1781.5 | 3142865.56 | 2021 | 2022 |  | 48176.5 | 500000 |  |  |  |  | 2021-12-20 | PEND |  | 2021-12-30 | [15 empty] | Approved |  |  | 2021-02-06 15:26 |  |  | 2021-02-04 08:04 |  |  | 2022 | Order and Notification
44667 | Add project | 35225593 |  | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44668 | Add project | 35217268 |  | CWSP - BUCKS CREEK 1101 CB PH 1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44669 | Add project | 35224712 |  | CWSP - BUCKS CREEK 1101 CB PH 2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44670 | Add project | 35224713 |  | CWSP - BUCKS CREEK 1101 CB PH 3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44671 | Add project | 35192290 |  | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44672 | Add project | 35192291 |  | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44673 | Add project | 35226845 |  | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44674 | Add project | 35062374 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44675 | Add project | 35226846 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44676 | Add project | 35226847 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44677 | Add project | 35062375 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44678 | Add project | 35226848 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ADER | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44679 | Add project | 35226849 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44680 | Add project | 35226850 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44681 | Add project | 35226851 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44682 | Add project | 35062376 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44683 | Add project | 35226852 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44684 | Add project | 35226853 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44685 | Add project | 35226854 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44686 | Add project | 35226856 |  | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44687 | Add project | 35075103 |  | FROGTOWN 1701 TIER 2 RECOND - FUSE L2969 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44688 | Add project | 35219098 |  | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44689 | Add project | 35219272 |  | CWSP - MIDDLETOWN 1101481876 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44690 | Add project | 35219280 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44691 | Add project | 35226632 |  | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44692 | Add project | 35219273 |  | CWSP - VOLTA 110149742 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44693 | Add project | 35219291 |  | CWSP - VACA DIXON 1101126774 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44694 | Add project | 35219266 |  | CWSP - MARIPOSA 2102CB PH 1 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44695 | Add project | 35227263 |  | CWSP - MARIPOSA 2102CB PH 2 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
44666 | Add project | 35192280 |  | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W | [6 empty] | Project Scope recently approved by WFGC and requesting project to be added officially to the 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-06 15:25 |  |  | 2021-02-03 21:27 |  |  |  | Not in Work Plan
35671 | Add project | 35225821 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH2 | Approved | 08W | [6 empty] | UG Mainline North Complex Fire Rebuild | 2021-05-19 | [8 empty] | 0 | 3500000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:40 |  |  |  | Not in Work Plan
35670 | Add project | 35223343 |  | FRRB - BIG BEND 1102 - LAKE MADRONE PH1 | Approved | 08W | [6 empty] | UG Mainline North Complex Fire Rebuild | 2021-05-19 | [8 empty] | 0 | 3500000 | 0 | 0 |  | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:40 |  |  |  | Not in Work Plan
35663 | Add project | 35223345 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-05-03 | [8 empty] | 0 | 9514299.24 | 0 | 0 |  | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:30 |  |  |  | Not in Work Plan
35664 | Add project | 35225823 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-07-01 | [8 empty] | 0 | 4865530.3 | 0 | 0 |  | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:30 |  |  |  | Not in Work Plan
35665 | Add project | 35225822 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-07-01 | [8 empty] | 0 | 3743276.52 | 0 | 0 |  | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:30 |  |  |  | Not in Work Plan
35666 | Add project | 35225824 |  | FRRB - WYANDOTTE 1103 - HWY 162 | Approved | 08W | [6 empty] | UG Mainline part of North Complex Fire Rebuild | 2021-04-29 | [8 empty] | 0 | 8053977.27 | 0 | 0 |  | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:30 |  |  |  | Not in Work Plan
35662 | Add project | 35223344 |  | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 | Approved | 08W | [6 empty] | UG main line under North Complex Fire Rebuild | 2021-03-10 | [8 empty] | 0 | 6000000 | 0 | 0 |  | DOCC | 2021-04-15 | [13 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-02-01 13:23 |  |  |  | Not in Work Plan
32219 | Add project | 35223615 |  | ECOP - LAS GALLINAS A 1105 PH 2 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 21:18 |  |  |  | Not in Work Plan
32221 | Add project | 35225589 |  | CWSP - KONOCTI 1102 LR 965078 PH2 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 21:18 |  |  |  | Not in Work Plan
32222 | Add project | 35225591 |  | CWSP - KONOCTI 1102 LR 965078 PH3 | Approved | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 21:18 |  |  |  | Not in Work Plan
32220 | Update work plan date | 35217270 |  | CWSP - KONOCTI 1102 LR 965078 PH1 | Withdrawn | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 |  | 2021-02-02 16:55 |  |  | 2021-01-28 21:18 |  |  |  | Not in Work Plan
32218 | Update work plan date | 35191319 |  | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | Withdrawn | 08W | [6 empty] | Add project recently approved by WFGC to bring into 2021 workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 |  | 2021-02-02 16:55 |  |  | 2021-01-28 21:18 |  |  |  | Not in Work Plan
32214 | Add project | 35223024 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 20:58 |  |  |  | Not in Work Plan
32215 | Add project | 35223026 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | ESTS | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 20:58 |  |  |  | Not in Work Plan
32216 | Add project | 35223027 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 20:58 |  |  |  | Not in Work Plan
32217 | Add project | 35223028 |  | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | Approved | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-02-02 16:58 |  |  | 2021-01-28 20:58 |  |  |  | Not in Work Plan
32213 | Update work plan date | 35192284 |  | ECOP - SILVERADO 2104 - H05-LR726 | Withdrawn | 08W | [6 empty] | Add projects recently approved by the WFGC to the 2021 Workplan |  | 2021-06-01 |  |  |  |  | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Withdrawn | submitted as add project, changed to update work plan date to move back to 2021 |  | 2021-02-02 16:55 |  |  | 2021-01-28 20:58 |  |  |  | Not in Work Plan
31287 | Add project | 35225598 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31286 | Add project | 35225597 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31285 | Add project | 35225595 |  | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31284 | Add project | 35225594 |  | CNCL ECOP FULTON 1107 - H02-LR604 PH 1.2 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | DOCC | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31281 | Add project | 35226241 |  | CWSP - MARIPOSA 210197142 PH 2 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31282 | Add project | 35226240 |  | CWSP - MARIPOSA 210197142 PH 3 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31283 | Add project | 35192292 |  | ECOP - FULTON 1107 - H02-LR604 PH1.1 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | ESTS | [14 empty] | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 |  | 2021-01-28 18:22 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31288 | Add project | 35191318 |  | ECOP - SILVERADO 2102 - H02-LR58626 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 |  | 2021-01-28 18:22 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31289 | Add project | 35191383 |  | ECOP - SILVERADO 2102 - H01-LR58626 | Withdrawn | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 |  | 2021-01-28 18:22 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31280 | Add project | 35219268 |  | CWSP - MARIPOSA 210197142 PH 1 | Approved | 08W | [6 empty] | Requesting project to be added to 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | PEND | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:26 |  |  |  | Not in Work Plan
31279 | Add project | 35219275 |  | CWSP - PUTAH CREEK 110246012 | Approved | 08W | [6 empty] | Requesting project to be added to the 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | CONS | [14 empty] | Approved |  |  | Approved |  |  | 2021-01-28 18:17 |  |  | 2021-01-25 14:16 |  |  |  | Not in Work Plan
31278 | Add project | 35217267 |  | SH - MARIPOSA 2102 LR 241564 | Withdrawn | 08W | [6 empty] | Requesting project to be added to the 2021 MPP workplan based on risk model updates and recent scope approval by WFM committee. | [14 empty] | CONS | [14 empty] | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 |  | 2021-01-28 18:21 |  |  | 2021-01-25 14:16 |  |  |  | Not in Work Plan
31277 | Add project | 35217273 |  | SH - UPPER LAKE 1101 CB | Withdrawn | 08W | [6 empty] | Project to be added to 2021 workplan based on Risk model updates and approved by WFM committee | [14 empty] | PEND | [14 empty] | Approved |  |  | Withdrawn | job already on work plan, manually changed work plan year to 2021 |  | 2021-01-28 18:22 |  |  | 2021-01-25 14:04 |  |  |  | Not in Work Plan
30522 | Budget change | 35109552 | 117348827 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting addational $100k to cover Sierra Springs Owners Association (SSOA) Road Repairs | 2019-10-07 |  | 2699 | 5804263 | 2020 |  |  | 1092828.8 | 175000 | 0 | 175000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-11 | 2019-10-07 | [15 empty] | Approved |  |  | 2021-01-20 23:35 |  |  | 2021-01-20 14:05 |  |  | 2020 | Order and Notification
29293 | Defer project | 35114044 | 117502841 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-08-12 | 2021-12-31 | 2524.7 | 3012702 | 2020 | 2021 | 2021 | 2235937 | 20105.2 |  |  |  |  | 2019-12-06 | FICL | 2021-02-25 | 2020-08-12 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29301 | Defer project | 35113108 | 117492255 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-08-03 | 2021-12-31 | 1934 | 2054719 | 2020 | 2021 | 2021 | 1139777.4 | 183849 |  |  |  |  | 2020-12-31 | FICL | 2021-04-15 | 2020-08-03 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29300 | Defer project | 35114103 | 117560686 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-08-03 | 2021-12-31 | 1753 | 2335115 | 2020 | 2021 | 2021 | 2491580.1 | 506601.3 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-03 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29299 | Defer project | 35114102 | 117545619 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-08-04 | 2021-12-31 | 1233 | 1763594 | 2020 | 2021 | 2021 | 1166533.7 | 428517.6 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-04 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29298 | Defer project | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-07-21 | 2021-12-31 | 1883.9 | 2193681.27 | 2020 | 2021 | 2021 | 3322836 | 1168197.9 |  |  |  |  | 2021-12-31 | FICL | 2021-04-23 | 2020-07-21 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29297 | Defer project | 35116801 | 117605266 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-08-10 | 2021-12-31 | 3312 | 3408934 | 2020 | 2021 | 2021 | 3741713.1 | 441774.7 |  |  |  |  | 2020-12-31 | CONS |  | 2020-08-10 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:12 |  |  | 2021 | Order and Notification
29294 | Defer project | 35157845 | 118548863 | SILVERADO 2105 WIRE DOWN - PH 3 | Approved | 08W | 220 Mile Plan | [5 empty] | Approved by Wildfire Governance Committee for 2021 | 2020-05-07 | 2021-12-31 | 875.3 | 1800635 | 2020 | 2021 | 2021 | 1717.8 | [5 empty] | 2020-12-31 | CONS | [11 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:11 |  |  | 2021 | Order and Notification
29295 | Defer project | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan |  | GC Gas |  |  |  | Delayed by Caltrans DSDD Permit | 2020-07-29 | 2022-12-31 | 4154.9 | 4232824 | 2020 | 2022 | 2022 | 1150000 | 1750000 |  |  |  |  | 2019-12-06 | CONS |  | 2020-07-29 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:06 |  |  | 2022 | Order and Notification
29296 | Defer project | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv | [5 empty] | Delayed by Caltrans DSDD permit | 2022-01-04 | 2022-12-31 | 2163 | 2768676 | 2021 | 2022 | 2022 | 4086056.3 | 44404 |  |  |  |  | 2021-07-12 | PEND |  | 2022-01-04 | [9 empty] | Approved | Defer approved |  | Approved |  |  | Approved |  |  | 2021-01-20 09:45 |  |  | 2021-01-14 09:05 |  |  | 2022 | Order and Notification
27633 | Budget change | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W | [6 empty] | Carry over from 2020 | 2021-10-28 |  | 4313.1 | 5959167 | 2021 | 2022 |  | 300000 | 500000 |  | 4139274.6 | 0 | 0 | 2020-09-30 | PEND |  | 2021-10-28 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:31 |  |  | 2022 | Order and Notification
27632 | Budget change | 35142826 | 118218639 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Approved | 08W | 2020 Rsrv | [5 empty] | Carry over from 2020 | 2020-10-20 |  | 2611.8 | 3876275 | 2021 |  |  | 2721318.8 | 2721318.8 |  | 2721318.8 | 0 | 0 | 2020-12-31 | FICL | 2021-04-12 | 2020-10-20 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:30 |  |  | 2021 | Order and Notification
27631 | Budget change | 35115154 | 117496036 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Carry over from 2020 | 2021-03-17 |  | 3093.3 | 3872109 | 2020 | 2021 |  | 725000 | 2584854.1 |  | 2584854.1 | 0 | 0 | 2020-12-31 | CONS |  | 2021-03-17 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:30 |  |  | 2021 | Order and Notification
27630 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Carry over from 2020 | 2021-03-08 |  | 2455.4 | 4734585 | 2020 | 2021 |  | 3595900 | 3080584.2 |  | 3080584.2 | 0 | 0 | 2020-12-31 | CONS |  | 2021-03-08 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:29 |  |  | 2021 | Order and Notification
27629 | Budget change | 35115151 | 117493857 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Carry over from 2020 | 2020-08-17 |  | 1832.1 | 5273989 | 2020 | 2021 |  | 4025666.85 | 2520547.9 |  | 2520547.9 | 0 | 0 | 2020-12-31 | FICL | 2021-05-27 | 2020-08-17 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:29 |  |  | 2021 | Order and Notification
27628 | Budget change | 35112429 | 117467966 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2020-06-20 |  | 4175 | 5585619 | 2020 |  |  | 2122911.2 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | FICL | 2020-07-18 | [16 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:28 |  |  | 2020 | Order and Notification
27627 | Budget change | 35109556 | 117348368 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-21 |  | 525.7 | 1197284 | 2020 |  |  | 539895.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-03-06 | 2019-10-21 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:28 |  |  | 2020 | Order and Notification
27626 | Budget change | 35109555 | 117348367 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-12-09 |  | 3331.1 | 4477708 | 2020 |  |  | 1377445.6 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-21 | 2019-12-09 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:28 |  |  | 2020 | Order and Notification
27625 | Budget change | 35109554 | 117348366 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2020-02-13 |  | 1515 | 2287663 | 2020 |  |  | 2052799.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-03 | 2020-02-13 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:27 |  |  | 2020 | Order and Notification
27624 | Budget change | 35109553 | 117348828 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-21 |  | 2781.7 | 4009924 | 2020 |  |  | 2010425.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-01-29 | 2019-10-21 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:27 |  |  | 2020 | Order and Notification
27623 | Budget change | 35109552 | 117348827 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-07 |  | 2699 | 5804263 | 2020 |  |  | 1092828.8 | 175000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-11 | 2019-10-07 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:27 |  |  | 2020 | Order and Notification
27619 | Budget change | 35109548 | 117349073 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2020-01-27 |  | 4055.7 | 7082947 | 2020 |  |  | 5761350.2 | 450000 |  | 450000 | 0 | 0 | 2020-12-30 | DOCC | 2020-05-22 | 2020-01-27 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:26 |  |  | 2020 | Order and Notification
27620 | Budget change | 35109549 | 117348822 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-04 |  | 1629 | 3123544 | 2020 |  |  | 1170998.5 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | 2019-10-04 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:26 |  |  | 2020 | Order and Notification
27622 | Budget change | 35109551 | 117348824 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2020-03-20 |  | 439.4 | 3172299 | 2020 |  |  | 372852.5 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | [16 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:26 |  |  | 2020 | Order and Notification
27621 | Budget change | 35109550 | 117348823 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-04 |  | 1821.7 | 3044150 | 2020 |  |  | 627012.7 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-01-31 | 2019-10-04 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:26 |  |  | 2020 | Order and Notification
27618 | Budget change | 35109547 | 117349072 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2020-01-06 |  | 2120.4 | 3530637 | 2020 |  |  | 2778156 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-03-13 | 2020-01-06 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:24 |  |  | 2020 | Order and Notification
27617 | Budget change | 35109545 | 117349070 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-12-02 |  | 2430 | 4499650 | 2020 |  |  | 4126337.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-04-17 | 2019-12-02 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:01 |  |  | 2020 | Order and Notification
27616 | Budget change | 35109540 | 117348505 | CWSP-EL DORADO 2101-19752- PHASE 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Carryover/closeout costs | 2019-10-16 |  | 1065 | 4228889 | 2020 |  |  | 1838510.1 | 75000 |  | 75000 | 0 | 0 | 2020-12-30 | DOCC | 2020-02-18 | 2019-10-16 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:00 |  |  | 2020 | Order and Notification
27615 | Budget change | 35061212 | 115106486 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Carry over from 2020 | 2020-08-20 |  | 1692.7 | 4913095 | 2020 | 2021 |  | 3641406.7 | 2161081.9 |  | 2161081.9 | 0 | 0 | 2020-12-31 | CONS |  | 2020-08-20 | [15 empty] | Approved |  |  | 2021-01-13 10:56 |  |  | 2021-01-12 12:00 |  |  | 2021 | Order and Notification
27374 | Budget change | 35112432 | 117472387 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-08 |  | 2667.8 | 5345911 | 2020 |  |  | 4912207.3 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-11-18 | 2020-05-08 | [15 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27375 | Budget change | 35112433 | 117472388 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-06-09 |  | 2274 | 4151673 | 2020 |  |  | 4707102.8 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-06-11 | [16 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27376 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 3110193 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | MAPP | 2020-10-02 | 2020-07-27 | [15 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27380 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-08-06 |  | 4104 | 3293522 | 2020 |  |  | 2388716 | 75000 |  | 75000 | 0 | 0 | 2019-12-31 | DOCC | 2020-08-21 | [16 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27377 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-31 |  | 5177.2 | 4061849 | 2020 |  |  | 2874679 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-09-04 | [16 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27378 | Budget change | 35112436 | 117472563 | CWSP - EL DORADO 2102 - LR19562 - PH 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-06-07 |  | 2454.5 | 3899347 | 2020 |  |  | 2566326.4 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | MAPP | [17 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27379 | Budget change | 35112437 | 117472564 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-07-08 |  | 2578.5 | 5431839 | 2020 |  |  | 5750872.5 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-08-26 | [16 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27373 | Budget change | 35112431 | 117472384 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $75,000 for closing out fee and any unexpected charges that might hit the project | 2020-05-27 |  | 2000.4 | 4166416 | 2020 |  |  | 2992595.4 | 75000 |  | 75000 | 0 | 0 | 2020-12-31 | DOCC | 2020-10-02 | [16 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-11 11:05 |  |  | 2020 | Order and Notification
27341 | RCR - Add and Assign Resource | 35161152 | 118677878 | OCT2019 BRICEBURG FIRE REBUILD | Denied | 08W | [6 empty] | [REDACTED] has reviewed and orderd mtls. | [13 empty] | 2021-02-26 | MAPP | 2021-05-20 | [10 empty] | Approved | WK3 2021 |  |  |  |  | Denied | Order and Notification don't match |  | 2021-01-11 16:25 |  |  | 2021-01-08 15:04 |  |  |  | Not in Work Plan
25906 | Resource change | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Approved | 08W | [6 empty] | Civil work to be completed by [REDACTED]. | 2021-04-19 |  | 1.1 | 7914493 | 2021 |  |  | 145083 | 5901787 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-19 | [15 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-07 11:53 |  |  | 2021 | Order and Notification
25905 | Resource change | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Approved | 08W | [6 empty] | Civil work to be completed by [REDACTED]. | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | [15 empty] | Approved |  |  | 2021-01-11 22:39 |  |  | 2021-01-07 11:53 |  |  | 2021 | Order and Notification
25869 | Add project | 35145525 | 118266592 | PSPS - RINCON 1102 1104 SYSTEM HARDENING | Denied | 08W | [6 empty] | Civil work to be completed by [REDACTED]. | 2021-04-19 |  | 1.1 | 7914493 | 2021 |  |  | 145083 | 5901787 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-19 | [12 empty] | Approved |  |  | Denied | job is already on the work plan |  | 2021-01-20 09:57 |  |  | 2021-01-06 16:24 |  |  | 2021 | Order and Notification
25868 | Add project | 35145524 | 118266591 | PSPS - RINCON 1101 1103 SYSTEM HARDENING | Denied | 08W | [6 empty] | Civil work to be completed by [REDACTED]. | 2021-04-26 |  | 2651.2 | 8431936 | 2021 |  |  | 159888 | 12006359 |  |  |  |  | 2020-12-01 | UNSC |  | 2021-04-26 | [12 empty] | Approved |  |  | Denied | job is already on the work plan |  | 2021-01-20 09:57 |  |  | 2021-01-06 16:24 |  |  | 2021 | Order and Notification
21389 | Resource change | 35192280 | 119556070 | ECOP - CLAYTON 2212 - H01-LR2951 | Approved | 08W | [6 empty] | 12.18 Resource Updates | 2022-05-09 |  | 180 | 550000 | 2021 | 2022 |  |  | 852800 |  |  |  |  | 2023-12-31 | ESTS |  | 2022-05-09 | [15 empty] | Approved |  |  | 2020-12-21 20:35 |  |  | 2020-12-21 15:08 |  |  | 2022 | Order and Notification
20604 | Resource change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | 12.18 Resource Updates | 2021-05-03 |  | 1833.1 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-03 | [15 empty] | Approved |  |  | 2020-12-21 14:39 |  |  | 2020-12-21 12:11 |  |  | 2021 | Order and Notification
20603 | Resource change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | 12.18 Resource Updates | 2021-04-15 |  | 2558 | 4624169 | 2020 | 2021 |  | 103947 | 3135435 |  |  |  |  | 2020-12-25 | CONS |  | 2021-04-15 | [15 empty] | Approved |  |  | 2020-12-21 14:39 |  |  | 2020-12-21 12:11 |  |  | 2021 | Order and Notification
20304 | Defer project | 35115053 |  | CWSP - MIWUK 1701_OCB - PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed into 2021. | 2020-08-11 | 2021-04-20 | 1878 | 2296559 | 2020 | 2021 | 2021 | 823352 | 8996 | 823352 | 8996 |  |  |  | CONS |  | 2020-08-11 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  |  | 2020-12-29 11:30 |  |  | 2020-12-15 13:17 |  |  | 2021 | Order Only
20303 | Defer project | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed into 2021. | 2021-04-15 | 2021-04-22 | 2558 | 4624169 | 2020 | 2021 | 2021 | 103947 | 3135435 | 64331 | 2026268 |  |  | 2020-12-25 | CONS |  | 2021-04-15 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  |  | 2020-12-29 11:31 |  |  | 2020-12-15 13:14 |  |  | 2021 | Order and Notification
20302 | Defer project | 35116444 | 117605182 | CWSP-MIWUK 1702-LR 38218-PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed into 2021. | 2020-08-04 | 2021-04-15 | 3164 | 3531134 | 2020 | 2021 | 2021 | 920437 | 559463 | 920437 | 559463 |  |  | 2020-12-31 | CONS |  | 2020-08-04 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  |  | 2020-12-29 11:31 |  |  | 2020-12-15 13:10 |  |  | 2021 | Order and Notification
20301 | Defer project | 35052821 | 114593976 | T2/T3-CWSP - MIWUK 1701 OCB - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed into 2021. | 2020-08-31 | 2021-01-05 | 1492 | 4765282 | 2020 | 2021 | 2021 | 798819 | 1382243 | 798819 | 1382243 |  |  | 2020-12-31 | CONS |  | 2020-08-31 | [7 empty] | Approved |  | Approved | Defer approved |  | Approved | Temporaily until this can be owned by program managers themselves in DOT |  | Approved |  |  | 2020-12-29 11:30 |  |  | 2020-12-15 13:03 |  |  | 2021 | Order and Notification
19647 | RCR - Add and Assign Resource | 31334291 | 112994395 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [7 empty] | 2021-10-01 |  | 428 | 1115282 | 2021 |  |  | 150000 | 755085 |  |  |  |  | 2018-12-28 | PEND |  | 2021-10-01 | [9 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:45 |  |  | 2020-12-14 17:03 |  |  | 2021 | Order and Notification
19648 | RCR - Add and Assign Resource | 31361965 | 113751296 | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [7 empty] | 2021-03-16 |  | 660.1 | 1245293 | 2021 |  |  | 287153 | 273723 |  |  |  |  | 2019-12-27 | FICL | 2021-04-24 | 2021-03-16 | [9 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:45 |  |  | 2020-12-14 17:03 |  |  | 2021 | Order and Notification
19709 | RCR - Change or Assign Resource | 35031662 | 114474310 | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 | Approved | 08W | 220 Mile Plan | [6 empty] | 2020-02-12 |  | 1767.5 | 1363100.7 | 2020 |  |  | 1012978.8 | 19394.1 |  |  |  |  | 2020-08-31 | FICL | 2020-03-25 | 2020-02-12 | [9 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:38 |  |  | 2020-12-14 17:03 |  |  | 2020 | Order and Notification
19775 | RCR - Change or Assign Resource | 35145004 | 118263746 | PSPS CWSP - ROSSMOOR 1106 - CB | Approved | 08W | [7 empty] | 2022-04-12 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:45 |  |  | 2020-12-14 17:03 |  |  |  | Not in Work Plan
19776 | RCR - Change or Assign Resource | 35144941 | 118261469 | *CANC* PAUL SWEET 2105 - CB PH 1 | Approved | 08W | [7 empty] | 2022-03-16 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:45 |  |  | 2020-12-14 17:03 |  |  |  | Not in Work Plan
20090 | RCR - Change or Assign Resource | 35145522 | 118265394 | PSPS - CLARKSVILLE 2104 - CB UG | Approved | 08W | [7 empty] | 2022-04-11 |  |  |  | 2021 | [8 empty] | 2020-12-31 | PEND | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:45 |  |  | 2020-12-14 16:55 |  |  |  | Not in Work Plan
20086 | RCR - Change or Assign Resource | 74022388 | 114266765 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan | [6 empty] | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 | [5 empty] | 2020-03-01 | DOCC |  | 2020-02-14 | [9 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:38 |  |  | 2020-12-14 16:55 |  |  | 2020 | Order and Notification
20087 | RCR - Change or Assign Resource | 74022388 | 114266765 | OCGC CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan | [6 empty] | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 | [5 empty] | 2020-03-01 | DOCC |  | 2020-02-14 | [9 empty] | Approved | [5 empty] | Approved |  |  | 2020-12-15 11:38 |  |  | 2020-12-14 16:55 |  |  | 2020 | Order and Notification
19249 | Defer project | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Project deferred into 2021. | 2020-07-15 | 2021-01-18 | 2736 | 3849738 | 2020 | 2021 | 2021 | 1894612 | 201890 | 1894612 | 201890 | 0 |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | [15 empty] | Approved |  |  | 2020-12-14 13:37 |  |  | 2020-12-11 15:34 |  |  | 2021 | Order and Notification
19183 | Defer project | 35056746 |  | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | [6 empty] | Add Project to MPP | 2021-02-15 | [13 empty] | FICL | 2021-05-10 | [16 empty] | Approved | Changed to deferral, project on 2020 work plan |  | 2020-12-11 15:22 |  |  | 2020-12-10 14:30 |  |  |  | Not in Work Plan
19182 | Add project | 35115057 |  | CWSP - MIWUK 1701 - OCB - PH2.5 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-31 | [13 empty] | UNSC | [17 empty] | Denied | Project removed from work plan due to new risk model |  | 2020-12-11 15:23 |  |  | 2020-12-10 14:29 |  |  |  | Not in Work Plan
19181 | Add project | 35115051 |  | CWSP - MIWUK 1701_OCB - PH 1.3 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-01 | [13 empty] | CONS | [17 empty] | Denied | Project removed from work plan due to new risk model |  | 2020-12-11 15:23 |  |  | 2020-12-10 13:02 |  |  |  | Not in Work Plan
19180 | Add project | 35052739 |  | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Denied | 08W | [6 empty] | Add Project to MPP | 2022-03-09 | [13 empty] | CONS | [17 empty] | Denied | Project removed from work plan due to new risk model |  | 2020-12-11 15:21 |  |  | 2020-12-10 12:26 |  |  |  | Not in Work Plan
18937 | Defer project | 35116383 | 117604600 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed out into 2021; delay due to fire rebuild | 2021-03-08 | 2021-01-26 | 1953 | 3758449 | 2020 | 2021 | 2021 | 1077436 | 850000 | 1077436 | 1035343 |  |  | 2021-06-30 | CONS |  | 2021-03-08 | [7 empty] | Approved | [7 empty] | Approved | See EDRS 2020-83277 |  | 2020-12-11 14:51 |  |  | 2020-12-09 14:33 |  |  | 2021 | Order and Notification
18936 | Defer project | 35115055 | 117490481 | CWSP - MIWUK 1701 - OCB - PH 2.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed out into 2021; delay due to fire rebuild | 2020-12-31 | 2021-03-15 | 1504 | 3784068 | 2020 | 2021 | 2021 | 986382 | 1023108 | 986382 | 1023108 |  |  | 2020-12-04 | CONS |  | 2020-12-31 | [7 empty] | Approved | [7 empty] | Approved | See EDRS 2020-83277 |  | 2020-12-11 14:51 |  |  | 2020-12-09 14:30 |  |  | 2021 | Order and Notification
18935 | Defer project | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Project has been pushed out into 2021; delay due to fire rebuild | 2020-09-14 | 2021-02-15 | 1376 | 3642331 | 2020 | 2021 | 2021 | 544498 | 1257187 | 544498 | 1257187 |  |  | 2020-12-01 | FICL | 2021-05-10 | 2020-09-14 | [7 empty] | Approved | [7 empty] | Approved | See EDRS 2020-83277 |  | 2020-12-11 14:51 |  |  | 2020-12-09 14:26 |  |  | 2021 | Order and Notification
18736 | Budget change | 35145002 |  | PSPS - IGNACIO 1101 - CB | Approved | 08W | [6 empty] | More accurate estimate and forecast available | [9 empty] | 120000 | 2556721.57 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-12-08 12:53 |  |  | 2020-12-07 16:57 |  |  |  | Not in Work Plan
17723 | Resource change | 35113950 | 117560045 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [7 empty] | 2021-07-09 |  | 6002.2 | 7087268 | 2021 | 2022 |  | 180000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-07-09 | [15 empty] | Approved |  |  | 2020-11-22 20:36 |  |  | 2020-11-20 12:32 |  |  | 2022 | Order and Notification
17722 | Resource change | 35113951 | 117560047 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [7 empty] | 2021-12-29 |  | 4240.3 | 6920313 | 2021 | 2022 |  | 200000 | 900000 |  |  |  |  | 2020-12-31 | UNSC |  | 2021-12-29 | [15 empty] | Approved |  |  | 2020-11-22 20:36 |  |  | 2020-11-20 12:31 |  |  | 2022 | Order and Notification
17721 | Resource change | 35052731 | 114607365 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | 220 Mile Plan | [6 empty] | 2021-06-21 |  | 3503.2 | 4994628 | 2020 | 2022 |  | 220000 | 2129616.4 |  |  |  |  | 2020-09-30 | UNSC |  | 2021-06-21 | [15 empty] | Approved |  |  | 2020-11-22 20:36 |  |  | 2020-11-20 12:31 |  |  | 2022 | Order and Notification
17133 | RCR - Change or Assign Resource | 35145004 | 118263746 | PSPS CWSP - ROSSMOOR 1106 - CB | Approved | 08W | [6 empty] | [REDACTED] was awarded civil contract on Rossmoor 1109/PM# 74008802. Rossmoor 1109 is installing spare ducts for Rossmoor 1106. There is a small portion of civil work on Rossmoor 1106 project that is outside scope of Rossmoor 1109 (~150k/300 hours). Requestig | 2021-02-04 |  |  |  | 2021 | [8 empty] | 2021-03-31 | PEND | [11 empty] | Approved | Civil only reqeust |  |  |  |  | Approved |  |  | 2020-11-19 19:42 |  |  | 2020-11-17 12:28 |  |  |  | Not in Work Plan
15700 | Defer project | 35112427 | 117467963 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-11-14 | 2020-11-14 | 2279.8 | 3306693 | 2020 |  | 2020 | 1425167.6 | -231631 |  |  |  |  | 2020-12-31 | MAPP | [9 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:09 |  |  | 2020-11-13 10:41 |  |  | 2020 | Order and Notification
15699 | Defer project | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-01-13 | 2020-11-14 | 2123.7 | 5231108 | 2020 |  | 2021 | 3150000 | 88800 |  |  |  |  | 2020-12-31 | FICL | 2021-02-25 | 2020-01-13 | [7 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:11 |  |  | 2020-11-13 10:41 |  |  | 2020 | Order and Notification
15698 | Defer project | 35117443 | 117634567 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-07-28 | 2020-11-14 | 5134.2 | 5778810 | 2020 | 2021 | 2021 | 4175407.8 | 2450191 |  |  |  |  | 2020-12-31 | MAPP | 2021-05-13 | 2020-07-28 | [7 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:09 |  |  | 2020-11-13 10:41 |  |  | 2021 | Order and Notification
15697 | Defer project | 35115148 | 117496270 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-06-02 | 2020-11-14 | 3236.8 | 5062019 | 2020 |  | 2021 | 4762461.3 | 59744 |  |  |  |  | 2020-12-31 | PREC | 2020-11-20 | [8 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:10 |  |  | 2020-11-13 10:41 |  |  | 2020 | Order and Notification
15696 | Defer project | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-06-01 | 2020-11-14 | 2558.5 | 2927538 | 2020 |  | 2021 | 1900000 | 131088 |  |  |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [7 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:11 |  |  | 2020-11-13 10:40 |  |  | 2020 | Order and Notification
15695 | Defer project | 35061206 | 115106231 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Reprioritization of workplan for 08W | 2020-06-15 | 2020-11-14 | 2491.1 | 4711641 | 2020 | 2021 | 2021 | 3596290.1 | 1419181 |  |  |  |  | 2020-12-31 | CONS |  | 2020-06-15 | [7 empty] | Approved | [7 empty] | Approved | BISD Extension approved in EDRS 2020-76744 |  | 2020-11-23 10:11 |  |  | 2020-11-13 10:40 |  |  | 2021 | Order and Notification
15688 | Budget change | 35053429 | 114921419 | CWSP HALF MOON BAY 1102 FUCO 12457 | Approved | 08W | [6 empty] | Requet update to 2021 Optimized Budget before routing business case. | 2021-01-20 |  |  |  | 2021 |  |  |  |  | 138035 | 1672108 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-11-20 14:19 |  |  | 2020-11-13 09:05 |  |  |  | Not in Work Plan
15692 | Defer project | 74022384 | 114753320 | CWSP - FITCH MOUNTAIN 1113 LR 24918 | Approved | 08W | 220 Mile Plan | [5 empty] | Sonoma [REDACTED] crews pulled off project in mid-August to assist with fire restoration. Has not been able to return to jobsite and not likely until next year. | 2020-06-08 | 2021-05-31 | 8146.3 | 9998553 | 2020 | 2021 | 2021 | 3838756.17 | 2395900 | 3838756.17 | 3032683 |  |  | 2020-12-31 | CONS |  | 2020-06-08 | [7 empty] | Approved |  | Approved | Deferrals approved, start dates subject to 2021 work plan priorities TBD |  |  |  |  | Approved | Confirmed this job is approved to work |  | 2020-12-07 10:29 |  |  | 2020-11-13 08:58 |  |  | 2021 | Order and Notification
15480 | Budget change | 35060994 | 115101557 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-05-31 |  |  |  | 2021 |  |  |  |  | 150000 | 2034045 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15479 | Budget change | 35160098 | 118532430 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-01 |  |  |  | 2021 |  |  |  |  | 150000 | 1778415.6 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15474 | Budget change | 35160095 | 118532315 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-29 |  |  |  | 2021 |  |  |  |  | 150000 | 3503804.7 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15473 | Budget change | 35160096 | 118532317 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 1917956.1 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15476 | Budget change | 35160097 | 118532318 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-15 |  |  |  | 2021 |  |  |  |  | 150000 | 3786450 |  |  |  | ADER | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15477 | Budget change | 35158717 | 118531819 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-05-31 |  |  |  | 2021 |  |  |  |  | 150000 | 2727534.9 |  |  |  | ADER | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15475 | Budget change | 35160091 | 118532310 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 1298152.2 |  |  |  | ADER | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15472 | Budget change | 35160093 | 118532312 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 | Approved | 08W | [6 empty] | Additional estimating costs. | 2021-06-02 |  |  |  | 2021 |  |  |  |  | 150000 | 2046155.4 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:38 |  |  |  | Not in Work Plan
15424 | Budget change | 35112428 | 117467964 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | Cover unexpected construction costs | 2020-02-13 |  | 1611.4 | 3809898 | 2020 |  |  | 2279000 | -340669 | 2279000 | 0 |  |  | 2020-12-31 | DOCC | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:20 |  |  | 2020 | Order and Notification
15423 | Budget change | 35098621 | 117177530 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 | Approved | 08W | 220 Mile Plan | [5 empty] | Cover unexpected construction costs | 2020-06-01 |  | 2558.5 | 2927538 | 2020 |  |  | 1900000 | 131088 | 1900000 | 0 |  |  | 2020-11-30 | DOCC | 2020-12-03 | 2020-06-01 | [15 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:20 |  |  | 2020 | Order and Notification
15425 | Budget change | 35115155 | 117491298 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Cover unexpected construction costs | 2020-01-13 |  | 2123.7 | 5231108 | 2020 |  |  | 3150000 | 88800 | 3150000 | 0 |  |  | 2020-12-31 | FICL | 2021-02-25 | 2020-01-13 | [15 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:19 |  |  | 2020 | Order and Notification
15426 | Budget change | 35115157 | 117492085 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Cover unexpected construction costs | 2020-04-15 |  | 2628.1 | 1580553.38 | 2020 |  |  | 3900000 | 34847 | 3900000 | 0 |  |  | 2020-12-31 | FICL | 2020-09-30 | [16 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:14 |  |  | 2020 | Order and Notification
15427 | Budget change | 35160094 | 118532313 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 | Approved | 08W | [6 empty] | Cover estimating costs and overheads. | 2021-06-28 |  |  |  | 2021 |  |  |  |  | 150000 | 2286407 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 11:09 |  |  |  | Not in Work Plan
15422 | Budget change | 35145006 | 118263874 | PSPS - STAFFORD 1101 LR 1298 | Approved | 08W | [6 empty] | Additional budget for estimating/OH dollars. | 2021-05-17 |  |  |  | 2021 |  |  |  |  | 150000 | 2723214 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-12 09:56 |  |  |  | Not in Work Plan
13574 | Budget change | 35145540 | 118259180 | PSPS - FROGTOWN 1702 - CB | Approved | 08W | [6 empty] | Coverage of current year spend in addition to forecasted remaining spend which includes Veg-scope | 2021-10-28 | 2021-04-01 | 4313.1 | 5959167 | 2021 | 2022 |  | 300000 | 500000 | 300000 | 3888521 |  |  | 2020-09-30 | PEND |  | 2021-10-28 | [15 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-09 10:47 |  |  | 2022 | Order and Notification
13573 | Budget change | 35145522 | 118265394 | PSPS - CLARKSVILLE 2104 - CB UG | Approved | 08W | [6 empty] | Coverage of current and future expected charges in 2020 | 2021-03-19 | 2021-03-19 |  |  | 2021 |  |  |  |  | 210000 | 17803529 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-12 19:47 |  |  | 2020-11-09 10:42 |  |  |  | Not in Work Plan
12266 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-06-25 | 2021-04-23 |  |  | 2021 |  |  |  |  | 352872 | 2673326 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-06 17:06 |  |  | 2020-11-04 14:18 |  |  |  | Not in Work Plan
12268 | Budget change | 35116922 | 117605456 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-07-22 | 2021-06-24 |  |  | 2021 |  |  |  |  | 356755 | 2149979 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-06 17:06 |  |  | 2020-11-04 14:13 |  |  |  | Not in Work Plan
12267 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Approved | 08W | [6 empty] | 2021 CWSP Wildfire Hardening Project BC EDRS routing | 2021-08-10 | 2021-06-15 |  |  | 2021 |  |  |  |  | 487522 | 3021306 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-06 17:06 |  |  | 2020-11-04 14:11 |  |  |  | Not in Work Plan
12260 | Defer project | 35094397 | 117165917 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 | Approved | 08W | [6 empty] | Crew resources deferred to 2021 |  | 2021-04-04 |  |  | 2022 |  |  |  |  | 900000 | 833017 |  |  |  | FICL | 2021-01-14 | [8 empty] | Approved |  | Approved | Deferrals approved, start dates subject to 2021 work plan priorities TBD |  |  |  |  | Approved | Confirmed this job is approved to work |  | 2020-12-07 10:24 |  |  | 2020-11-03 09:38 |  |  |  | Not in Work Plan
12220 | Defer project | 35116443 | 117605181 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Deferred due to wild fire impact | 2021-01-12 | 2021-06-25 |  |  | 2020 | [9 empty] | CONS | [9 empty] | Approved |  | Approved | Impacted by resource pulled for fire response |  |  |  |  | Approved |  |  | 2020-11-12 19:29 |  |  | 2020-10-30 12:59 |  |  |  | Not in Work Plan
12218 | Budget change | 35129652 | 117873102 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $103,113 for 2020. Requesting $1,860,548 for 2021. Per phase gate review. | 2021-12-16 | 2021-12-16 |  |  | 2021 |  |  |  |  | 103113 | 1860547.5 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 12:12 |  |  |  | Not in Work Plan
12217 | Budget change | 35129600 | 117873031 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 | Approved | 08W | [6 empty] | Requesting budget of $113,375 for 2020. Requesting $2,001,194 for 2021. Per phase gate review. | 2021-11-12 | 2021-11-12 |  |  | 2021 |  |  |  |  | 113375 | 2001193.57 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 12:08 |  |  |  | Not in Work Plan
12216 | Budget change | 35129439 | 117873030 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 | Approved | 08W | [6 empty] | Requesting budget of $180,355 for 2020. Requesting $3,307,746 for 2021. Per phase gate review. | 2021-09-13 | 2021-09-13 |  |  | 2021 |  |  |  |  | 180355 | 3307745.54 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 12:03 |  |  |  | Not in Work Plan
12215 | Budget change | 35129438 | 117873019 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 | Approved | 08W | [6 empty] | Requesting budget of $164,470 for 2020. Requesting $2,917,462 for 2021. Per phase gate review. | 2021-12-24 | 2021-12-24 |  |  | 2021 |  |  |  |  | 164470 | 2917462.33 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:59 |  |  |  | Not in Work Plan
12214 | Budget change | 35129437 | 117873018 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 | Approved | 08W | [6 empty] | Requesting budget of $226,132 for 2020. Requesting $3,865,175 for 2021. Per phase gate review. | 2021-07-23 | 2021-07-23 |  |  | 2021 |  |  |  |  | 226132 | 3865175.43 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:55 |  |  |  | Not in Work Plan
12213 | Budget change | 35129436 | 117873017 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $193,892 for 2020. Requesting $3,361,536 for 2021. Per phase gate review. | 2021-10-18 | 2021-10-18 |  |  | 2021 |  |  |  |  | 193892 | 3361535.78 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:50 |  |  |  | Not in Work Plan
12212 | Budget change | 35129435 | 117873016 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 | Approved | 08W | [6 empty] | Requesting budget of $225,846 for 2020. Requesting $3,655,621 for 2021. Per phase gate review. | 2021-07-27 | 2021-07-27 |  |  | 2021 |  |  |  |  | 225846 | 3655621.16 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:45 |  |  |  | Not in Work Plan
12211 | Budget change | 35129311 | 117873013 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | Approved | 08W | [6 empty] | Requesting budget of $1,028,872 for 2020. Requesting $3,528,928 for 2021. Per phase gate review. | 2021-09-20 | 2021-09-20 |  |  | 2021 |  |  |  |  | 1028872 | 3528928 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:41 |  |  |  | Not in Work Plan
12210 | Budget change | 35129310 | 117873012 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | Approved | 08W | [6 empty] | Requesting budget of $861,191 for 2020. Requesting $2,822,841 for 2021. Per phase gate review. | 2021-08-13 | 2021-08-13 |  |  | 2021 |  |  |  |  | 861191.35 | 2822841.45 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:35 |  |  |  | Not in Work Plan
12209 | Budget change | 35129309 | 117873011 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | Approved | 08W | [6 empty] | Requesting budget of $235,647 for 2020. Requesting $2866907 for 2021. Per phase gate review. | 2021-10-20 | 2021-10-20 |  |  | 2021 |  |  |  |  | 235647 | 2866906.81 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:23 |  |  |  | Not in Work Plan
12208 | Budget change | 35129306 | 117872787 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | Approved | 08W | [6 empty] | Requesting budget of $605,702 for 2020. Requesting $1,293,508 for 2021. Per phase gate review. | 2021-06-30 | 2021-06-30 |  |  | 2021 |  |  |  |  | 605702 | 1293508 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 11:09 |  |  |  | Not in Work Plan
12207 | Budget change | 35095161 | 114708383 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Approved | 08W | [6 empty] | Requesting budget of $117,609 for 2020. Requesting $1,995,462 for 2021. Per phase gate review. | 2021-06-11 | 2021-06-11 |  |  | 2021 |  |  |  |  | 117609 | 1995461.65 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 10:47 |  |  |  | Not in Work Plan
12206 | Budget change | 35095161 | 114708383 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 | Approved | 08W | [6 empty] | Requesting budget of $117,609 for 2020. Requesting $1,995,462 for 2021. As per phase gate review meeting. | 2021-06-11 | 2021-06-11 |  |  | 2021 |  |  |  |  | 117609 | 1995461.65 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-30 10:43 |  |  |  | Not in Work Plan
11642 | Budget change | 35058273 | 114987127 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Approved | 08W | [6 empty] | Need to cover Veg PO increase | 2020-06-26 | 2020-12-31 |  |  | 2020 |  |  |  |  | 2678180 | 0 |  |  |  | FICL | 2020-07-20 | [16 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-29 08:02 |  |  |  | Not in Work Plan
11640 | Budget change | 35115049 | 117497752 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-10-06 |  |  |  | 2021 |  |  |  |  | 33000 | 4700000 |  |  |  | ESTS | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11639 | Budget change | 35115048 | 117497751 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-10-06 |  |  |  | 2021 |  |  |  |  | 18500 | 3550000 |  |  |  | ADER | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11638 | Budget change | 35115047 | 117496281 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-06-11 |  |  |  | 2021 |  |  |  |  | 163000 | 4100000 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11637 | Budget change | 35115046 | 117496177 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-09-08 |  |  |  | 2021 |  |  |  |  | 22500 | 4900000 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11636 | Budget change | 35115057 | 117489824 | CWSP - MIWUK 1701 - OCB - PH2.5 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-03-23 |  |  |  | 2021 |  |  |  |  | 127500 | 2750000 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11635 | Budget change | 35052735 | 114706118 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Approved | 08W | [6 empty] | True-up of 2020 RES per instruction from [REDACTED] and [REDACTED] | 2021-04-02 |  |  |  | 2021 |  |  |  |  | 140000 | 2600000 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-28 12:06 |  |  |  | Not in Work Plan
11633 | Budget change | 35058273 | 114987127 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 | Withdrawn | 08W | [6 empty] | CO associated with Veg PO needs additional budget to cover | 2020-06-26 | 2020-12-31 |  |  | 2020 |  |  |  |  | 2686180 | 0 |  |  |  | FICL | 2020-07-20 | [16 empty] | Withdrawn | Withdrawn by PM Request |  | 2020-11-03 11:35 |  |  | 2020-10-28 11:24 |  |  |  | Not in Work Plan
11576 | Budget change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Due to contract resources working on fire rebuild project schedule has slipped to 2021 | 2021-05-03 | 2021-06-30 | 1833.1 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 | 288570 | 1048628 |  |  | 2020-12-31 | CONS |  | 2021-05-03 | [15 empty] | Approved |  |  | 2020-11-01 17:41 |  |  | 2020-10-27 07:31 |  |  | 2021 | Order and Notification
11574 | Defer project | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Due to fire rebuild resources have been moved off this project resulting in construction being defered until 2021 | 2021-05-03 | 2021-05-31 | 1833.1 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-03 | [7 empty] | Approved |  | Approved | Resource impacted due to fire |  |  |  |  | Approved |  |  | 2020-11-12 19:29 |  |  | 2020-10-27 07:10 |  |  | 2021 | Order and Notification
11387 | Budget change | 35095167 | 114832579 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-04-16 | 2021-05-31 |  |  | 2021 |  |  |  |  | 282834 | 2083119 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 13:26 |  |  |  | Not in Work Plan
11385 | Budget change | 35116516 | 117608020 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-06-04 | 2021-06-04 |  |  | 2021 |  |  |  |  | 387975 | 1851047 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 13:26 |  |  |  | Not in Work Plan
11384 | Budget change | 35116515 | 117607998 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | CWSP 2020 Activated Reserve pushed into 2021. | 2021-07-07 | 2021-07-07 |  |  | 2021 |  |  |  |  | 517463 | 2685572 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 13:26 |  |  |  | Not in Work Plan
11388 | Budget change | 35114041 | 117500692 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Approved | 08W | [6 empty] | [REDACTED] pulled for fire restoration, construction continue Q1 2021. | 2021-01-22 | 2021-03-31 |  |  | 2020 |  |  |  |  | 554619 | 1156148 |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 13:24 |  |  |  | Not in Work Plan
11386 | Budget change | 35114048 | 117499466 | OCGC CWSP - PINE GROVE 1102 - LR1222 | Approved | 08W | 220 Mile Plan | [5 empty] | [REDACTED] pulled for fire restoration, construction continue Q1 2021. | 2020-08-14 | 2021-02-28 | 1748 | 4178929 | 2020 | 2021 |  | 1323768 | 1810131 | 1323768 | 1810131 |  |  | 2021-12-31 | FICL | 2021-05-06 | 2020-08-14 | [15 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 13:20 |  |  | 2021 | Order and Notification
11383 | Defer project | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Project involves Caltrans DSDD. Land is in the process of preparing basemap to revise drawings. | 2020-07-29 | 2021-04-30 | 4154.9 | 4232824 | 2020 | 2022 |  | 1150000 | 1750000 | 1150000 | 1750000 |  |  | 2019-12-06 | CONS |  | 2020-07-29 | [7 empty] | Approved |  | Approved | LAND in process |  |  |  |  | Approved |  |  | 2020-11-12 19:29 |  |  | 2020-10-22 12:42 |  |  | 2022 | Order and Notification
11291 | Budget change | 31098626 | 108895192 | CLARKSVILLE 2104 RECONDUCTOR -PH 3 Y2018 | Approved | 08W | 220 Mile Plan | [5 empty] | DO Calendar closed due to fires & PSPS | 2018-07-16 | 2020-12-31 | 2526.2 | 1543425 | 2020 |  |  | 775000 |  | 775000 | 0 |  |  | 2017-12-29 | CONS |  | 2018-07-16 | [15 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-22 11:55 |  |  | 2020 | Order and Notification
11255 | Budget change | 35113103 | 117492227 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.3 | Approved | 08W | [6 empty] | Contingency Release $50,000 due to over-run of Contracts and associated overheads |  | 2020-10-30 | [7 empty] | 48205 | 0 | [21 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-21 23:30 |  |  |  | Not in Work Plan
11252 | Budget change | 35103324 | 117251430 | CWSP - ROSSMOOR 1102 - OCB | Approved | 08W | 220 Mile Plan | [5 empty] | Unexpected estimating charges | 2020-10-30 | 2020-10-30 | 1360.6 | 2510809 | 2020 |  |  | 654743 |  | 654743 |  |  |  | 2020-12-31 | FICL | [17 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-21 20:22 |  |  | 2020 | Order and Notification
11253 | Budget change | 35116802 | 117605267 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Increase in overhead costs, vegetation costs, and unexpected estimating charges. | 2020-06-16 | 2020-10-30 | 2139.5 | 2559279 | 2020 |  |  | 2446652 | 53034.5 | 2446652 |  |  |  | 2020-12-31 | FICL | 2020-12-15 | 2020-06-16 | [15 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-21 20:21 |  |  | 2020 | Order and Notification
11205 | RCR - Change or Assign Resource | 35144941 | 118261469 | *CANC* PAUL SWEET 2105 - CB PH 1 | Approved | 08W | [6 empty] | PSPS Mitigation project, commitment to finish by 8/31/21 (before fire season). There could be summer load restrictions that would require this project be completed by 6/30/21. Requesting that civil work be completed by [REDACTED] to meet deadline. | 2021-04-12 |  |  |  | 2021 | [8 empty] | 2021-04-30 | PEND | [11 empty] | Approved | Per 11/19/2020 discussion with [REDACTED], [REDACTED] will be the electric assigned resource for 2021,must complete before 8/2021 |  |  |  |  | Approved |  |  | 2020-11-19 19:42 |  |  | 2020-10-19 11:07 |  |  |  | Not in Work Plan
11196 | Resource change | 35145001 | 118259181 | PSPS - CLAYTON 2215 - CB | Approved | 08W | [6 empty] | Timing - +/- 10,000' of trenching = +/- 8000 MH Civil | 2021-09-07 |  |  |  | 2021 | [9 empty] | PEND | [11 empty] | Approved | Civil request, Electric to follow, [REDACTED] noted as the electric resource |  |  |  |  | Approved |  |  | 2020-10-23 07:41 |  |  | 2020-10-19 10:14 |  |  |  | Not in Work Plan
10919 | RCR - Change or Assign Resource | 35118663 | 117670940 | BR-01-01-W (E) HEAVENS GATE PARB | Approved | 08W | [21 empty] | FICL | 2020-10-20 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-16 09:27 |  |  |  | Not in Work Plan
10917 | RCR - Change or Assign Resource | 35105646 | 117306439 | BR-03-05-W (E) DEAN RD, PARB | Approved | 08W | [21 empty] | FICL | 2021-03-22 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-16 09:27 |  |  |  | Not in Work Plan
10918 | RCR - Change or Assign Resource | 35110556 | 117402466 | BR-04-12-W (E) SUBSTATION/PATH PARB | Approved | 08W | [21 empty] | ESTS | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-16 09:27 |  |  |  | Not in Work Plan
10921 | RCR - Change or Assign Resource | 35112220 | 117463683 | BR-04-06-W (E) VALLEY RIDGE PARB | Approved | 08W | [21 empty] | FICL | 2021-02-17 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-23 16:53 |  |  | 2020-10-16 09:27 |  |  |  | Not in Work Plan
10525 | Budget change | 35112076 | 117440386 | OCGC FULTON 1107-OH TO UG MARK W SPG | Approved | 08W | 220 Mile Plan | [5 empty] | Addition dollars to cover estimating correction and closeout | 2020-03-23 |  | 3025.9 | 5750000 | 2020 |  |  | 950000 |  | 950000 |  |  |  | 2019-11-30 | MAPP | 2020-04-06 | [16 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-15 10:37 |  |  | 2020 | Order and Notification
10524 | Defer project | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Approved | 08W | [6 empty] | Moving 08W project to 2021 due to budget and crew constraints | 2021-02-09 | 2021-03-01 |  |  | 2020 | [5 empty] | 2922407 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-15 09:13 |  |  |  | Not in Work Plan
10520 | Defer project | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Fire rebuild has taken away resources | 2021-05-03 | 2021-06-30 | 1833.1 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 | 300000 | 1250000 |  |  | 2020-12-31 | CONS |  | 2021-05-03 | [7 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-15 06:04 |  |  | 2021 | Order and Notification
10446 | Budget change | 35145006 | 118263874 | PSPS - STAFFORD 1101 LR 1298 | Approved | 08W | [6 empty] | Additional funds needed to cover estimating, dependency costs in 2020 | 2021-06-29 | 2021-06-29 |  |  | 2021 |  |  |  |  | 120000 |  |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-14 13:34 |  |  |  | Not in Work Plan
10434 | Add project | 35206138 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.5 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE | [17 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-14 08:45 |  |  |  | Not in Work Plan
10433 | Add project | 35206136 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.4 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE | [17 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-14 08:45 |  |  |  | Not in Work Plan
10432 | Add project | 35206135 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.3 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE | [17 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-14 08:45 |  |  |  | Not in Work Plan
10431 | Add project | 35206134 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | [13 empty] | UNSE | [17 empty] | Approved |  |  | 2020-10-16 13:46 |  |  | 2020-10-14 08:44 |  |  |  | Not in Work Plan
10430 | Defer project | 35051472 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3 | Approved | 08W | [6 empty] | Add to 2022 work plan | 2022-12-31 | 2022-12-31 | [7 empty] | 0 | 0 |  |  |  | ESTS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 13:46 |  |  | 2020-10-14 08:32 |  |  |  | Not in Work Plan
10422 | Defer project | 35174474 |  | ECOP-CALISTOGA 1101-H01-LR736 PH1 | Approved | 08W | [6 empty] | 2032 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 20000 | 480000 |  |  |  | UNSE | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10423 | Defer project | 35173756 |  | ECOP-EL DORADO 2101-H02-LR6852-PH2 | Approved | 08W | [6 empty] | 2033 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10424 | Defer project | 35174466 |  | ECOP-EL DORADO 2101-H02-LR6852-PH3 | Approved | 08W | [6 empty] | 2034 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 15000 | 485000 |  |  |  | UNSE | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10425 | Defer project | 35174478 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | Approved | 08W | [6 empty] | 2035 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | ESTS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10426 | Defer project | 35174479 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | Approved | 08W | [6 empty] | 2036 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 15000 | 485000 |  |  |  | ADER | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10427 | Defer project | 35174501 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | Approved | 08W | [6 empty] | 2037 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | ESTS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10411 | Defer project | 35129618 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.4 | Approved | 08W | [6 empty] | 2021 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10412 | Defer project | 35129642 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.8 | Approved | 08W | [6 empty] | 2022 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10413 | Defer project | 35129648 |  | CWSP - ORO FINO 1101 - LR2022 PH 3.2 | Approved | 08W | [6 empty] | 2023 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | ESTS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10414 | Defer project | 35129616 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.2 | Approved | 08W | [6 empty] | 2024 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 45000 | 455000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10415 | Defer project | 35129617 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.3 | Approved | 08W | [6 empty] | 2025 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10416 | Defer project | 35129619 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.5 | Approved | 08W | [6 empty] | 2026 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10417 | Defer project | 35129640 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.6 | Approved | 08W | [6 empty] | 2027 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 30000 | 470000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10418 | Defer project | 35129641 |  | CWSP - ORO FINO 1101 - LR2022 PH 1.7 | Approved | 08W | [6 empty] | 2028 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 45000 | 455000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10419 | Defer project | 35094514 |  | CWSP-ORO FINO 1101 LR-2022 PH 1.1 | Approved | 08W | [6 empty] | 2029 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 75000 | 425000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10420 | Defer project | 35095164 |  | CWSP-ORO FINO 1101 LR-2022 PH 3.1 | Approved | 08W | [6 empty] | 2030 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 200000 | 300000 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10421 | Defer project | 35173754 |  | ECOP-BRUNSWICK 1106-H08-LR51486 | Approved | 08W | [6 empty] | 2031 work deferred to 2021 due to fire rebuild work requires 2021 deferrals into 2022 | 2021-12-31 | 2022-12-31 | [7 empty] | 10000 | 490000 |  |  |  | UNSE | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10410 | Defer project | 35046371 |  | ECOP - STANISLAUS 1702 LR 37276 | Approved | 08W | [6 empty] | defining as 2022 at assett managments request |  | 2022-12-31 | [7 empty] | 30000 | 470000 | [13 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-10-16 14:30 |  |  | 2020-10-13 15:54 |  |  |  | Not in Work Plan
10098 | Budget change | 35052739 | 114567186 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Approved | 08W | [6 empty] | Legacy approved Budget | 2020-11-19 |  |  |  | 2020 |  |  |  |  | 5180025 |  |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-10-11 23:50 |  |  | 2020-10-11 23:45 |  |  |  | Not in Work Plan
10053 | RCR - Change or Assign Resource | 35105646 | 117306439 | BR-03-05-W (E) DEAN RD, PARB | Approved | 08W | [21 empty] | FICL | 2021-03-22 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-09 09:53 |  |  |  | Not in Work Plan
10057 | RCR - Change or Assign Resource | 35112220 | 117463683 | BR-04-06-W (E) VALLEY RIDGE PARB | Approved | 08W | [21 empty] | FICL | 2021-02-17 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-09 09:53 |  |  |  | Not in Work Plan
10048 | RCR - Change or Assign Resource | 35095246 | 117164122 | BUCOCAMP - ERIKA DRIVE, PARADISE | Approved | 08W | [21 empty] | UNSC | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-09 09:53 |  |  |  | Not in Work Plan
10058 | RCR - Change or Assign Resource | 35118663 | 117670940 | BR-01-01-W (E) HEAVENS GATE PARB | Approved | 08W | [21 empty] | FICL | 2020-10-20 | [10 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-09 09:53 |  |  |  | Not in Work Plan
10081 | RCR - Change or Assign Resource | 35141837 | 118195513 | BR-04-01-W (E) SUNSET DR PARB | Approved | 08W | [21 empty] | PEND | [11 empty] | Approved | [5 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-09 09:53 |  |  |  | Not in Work Plan
9206 | Add project | 35161152 |  | OCT2019 BRICEBURG FIRE REBUILD | Approved | 08W | [6 empty] | Wild Fire Rebuild | 2021-04-01 | [8 empty] | 375186 | 1138733 |  |  |  | MAPP | 2021-05-20 | [16 empty] | Approved |  |  | 2020-10-09 16:31 |  |  | 2020-10-02 11:54 |  |  |  | Not in Work Plan
8637 | Budget change | 35112435 | 117472561 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting addational $805,821 due to realse contingency | 2020-05-31 | 2020-12-31 | 5177.2 | 4061849 | 2020 |  |  | 2874679 | 75000 | 2874679 |  |  |  | 2020-12-31 | DOCC | 2020-09-04 | [16 empty] | Approved |  |  | 2020-09-25 15:28 |  |  | 2020-09-23 11:49 |  |  | 2020 | Order and Notification
8631 | Defer project | 35115154 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 725000 | 399656.8 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:36 |  |  |  | Not in Work Plan
8629 | Defer project | 35115152 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 370000 | 1188363.6 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:34 |  |  |  | Not in Work Plan
8627 | Defer project | 35114041 |  | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 325000 | 1090171.7 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:32 |  |  |  | Not in Work Plan
8626 | Defer project | 35115853 |  | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1189127.5 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:31 |  |  |  | Not in Work Plan
8625 | Defer project | 35115153 |  | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | [6 empty] | Defer due to fire rebuild work | 2020-06-29 | 2021-12-31 | [7 empty] | 410000 | 1491841.1 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:30 |  |  |  | Not in Work Plan
8621 | Defer project | 35052739 |  | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 620000 | 1101941.4 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:27 |  |  |  | Not in Work Plan
8630 | Defer project | 35116388 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 2483533.4 |  |  |  | PEND | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:01 |  |  |  | Not in Work Plan
8628 | Defer project | 35115052 |  | CWSP - MIWUK 1701_OCB - PH 1.4 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1664060 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:01 |  |  |  | Not in Work Plan
8624 | Defer project | 35113951 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 200000 | 1582293.6 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:01 |  |  |  | Not in Work Plan
8623 | Defer project | 35115051 |  | CWSP - MIWUK 1701_OCB - PH 1.3 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 180000 | 1042881.3 |  |  |  | CONS | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:01 |  |  |  | Not in Work Plan
8622 | Defer project | 35113950 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 180000 | 2226592 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 15:01 |  |  |  | Not in Work Plan
8620 | Defer project | 35052731 |  | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 220000 | 2129616.4 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 14:50 |  |  |  | Not in Work Plan
8619 | Defer project | 31361965 |  | OCGC 2300 FT - NUNS CANYON -DUNBAR 1101 | Approved | 08W | [6 empty] | Defer due to fire rebuild work |  | 2021-12-31 | [7 empty] | 250000 | 986551.1 |  |  |  | FICL | 2021-04-24 | [8 empty] | Approved |  | Approved | Project defered as identified in business justification |  |  |  |  | Approved | Does not require WRFR approval |  | 2020-09-29 09:44 |  |  | 2020-09-22 14:50 |  |  |  | Not in Work Plan
8579 | Resource change | 35129601 | 117873032 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Approved | 08W | [7 empty] | 2021-11-09 |  |  |  | 2021 | [9 empty] | PEND | [17 empty] | Approved |  |  | 2020-09-18 14:57 |  |  | 2020-09-18 10:53 |  |  |  | Not in Work Plan
8580 | Resource change | 35129609 | 117873070 | CWSP - ORO FINO 1101 - OCB PH 2.3 | Approved | 08W | [7 empty] | 2021-11-05 |  |  |  | 2021 | [9 empty] | PEND | [17 empty] | Approved |  |  | 2020-09-18 14:57 |  |  | 2020-09-18 10:53 |  |  |  | Not in Work Plan
8516 | Budget change | 35095166 | 114742467 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 | Approved | 08W | 220 Mile Plan | [5 empty] | requesting $850,379 addational budget to be allocated in 2020 due to release contingency. | 2020-08-06 | 2020-12-31 | 4104 | 3293522 | 2020 |  |  | 2388716 | 75000 | 2388716 |  |  |  | 2019-12-31 | DOCC | 2020-08-21 | [16 empty] | Approved |  |  | 2020-09-18 14:57 |  |  | 2020-09-17 09:36 |  |  | 2020 | Order and Notification
8513 | Add project | 35112972 | 117491267 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | Approved | 08W | [6 empty] | Connection of 3rd phase for segment 3 on PM# 35112973 is not possible without first constructing segment 2 on PM# 35112972 | 2021-07-31 | [9 empty] | 1614773 |  |  |  | ESTS | [17 empty] | Approved | 2021 project, confirmed with [REDACTED] |  | 2020-09-18 15:30 |  |  | 2020-09-16 11:28 |  |  |  | Not in Work Plan
8429 | Budget change | 35115852 | 117602171 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-07-16 | 2021-07-16 |  |  | 2021 |  |  |  |  | 0 | 3346858.76 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-09-18 14:57 |  |  | 2020-09-15 13:51 |  |  |  | Not in Work Plan
8285 | Budget change | 35115057 | 117489824 | CWSP - MIWUK 1701 - OCB - PH2.5 | Approved | 08W | [7 empty] | 2021-03-23 |  |  |  | 2021 |  |  |  |  | 30000 | 2996000 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-09-11 15:12 |  |  | 2020-09-08 13:40 |  |  |  | Not in Work Plan
8265 | Budget change | 35129601 | 117873032 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 | Approved | 08W | [6 empty] | requesting additional budget $546,369 for veg work after phase gate review meeting | 2021-10-29 |  |  |  | 2021 |  |  |  |  | 546863 |  |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-09-11 15:12 |  |  | 2020-09-04 13:58 |  |  |  | Not in Work Plan
7894 | Resource change | 35144944 |  | PSPS - SNEATH LANE 1107 - LR 48338 | Approved | 08W | [21 empty] | PEND | [17 empty] | Approved |  |  | 2020-09-04 14:21 |  |  | 2020-09-03 17:09 |  |  |  | Not in Work Plan
7770 | Budget change | 35115856 | 117601688 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized budget request | 2021-03-15 | 2020-12-18 | [7 empty] | 3491056 |  |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-09-03 11:05 |  |  | 2020-09-01 08:38 |  |  |  | Not in Work Plan
7752 | Budget change | 35116396 | 117604756 | CWSP-MIWUK 1702-LR8090-PH 1.2 | Approved | 08W | [6 empty] | Need adjustment for vegetation management contract in 2020 | 2021-11-23 | 2020-09-01 | [7 empty] | 875000 | 3457000 |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-09-03 11:05 |  |  | 2020-08-31 09:26 |  |  |  | Not in Work Plan
7541 | Budget change | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [6 empty] | Change Request will be submitted to reduce 2020 MPP budget by $943,013.01 to be $2,611,485.99. Also, CR will be submitted to increse 2021 MPP budget by $67,999,.82 | 2021-05-14 | 2020-12-31 | 1598.4 | 3591121 | 2021 |  |  | 370000 | 2229051.5 | 2611485.99 | 67999.82 |  |  | 2020-12-31 | CONS |  | 2021-05-14 | [15 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-26 13:27 |  |  | 2021 | Order and Notification
7539 | Budget change | 35142827 | 118218951 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Approved | 08W | [6 empty] | Returning $206,728.59 to align with 2020 forecast per Gateway Review Meeting held 8/24/2020, and shifting $43,741 to 2021 budget. | 2021-03-30 | 2020-12-31 | [7 empty] | 1758524.99 | 43741.12 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-25 09:37 |  |  |  | Not in Work Plan
7537 | Budget change | 35115858 | 117601885 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-02-11 | 2021-11-20 | [7 empty] | 2216657 |  |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-24 15:56 |  |  |  | Not in Work Plan
7536 | Budget change | 35115848 | 117602057 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-06-22 | 2020-11-20 | [7 empty] | 2672610 |  |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-24 15:54 |  |  |  | Not in Work Plan
7534 | Budget change | 35115854 | 117601685 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Ree\quest | 2021-03-04 | [8 empty] | 2138614 | 0 |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-24 15:51 |  |  |  | Not in Work Plan
7531 | Budget change | 35114045 | 117502843 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Optimized Budget Request | 2021-03-10 | [8 empty] | 0 | 3021946 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-24 15:49 |  |  |  | Not in Work Plan
7529 | Budget change | 35114052 | 117502368 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | Approved | 08W | [6 empty] | 08W Fire Hardening Project optimized budget Request | 2021-03-19 | 2021-03-19 | [7 empty] | 0 | 2022612 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-08-28 18:59 |  |  | 2020-08-24 15:47 |  |  |  | Not in Work Plan
7054 | Budget change | 35116385 | 117604609 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Bids received and reduced project cost | 2022-09-23 | 2021-02-05 | 1631.8 | 3489624 | 2022 |  |  | 3808029.1 | 2815000 | 0 | 2815000 |  |  | 2020-12-25 | PEND |  | 2022-09-23 | [15 empty] | Approved |  |  | 2020-08-24 08:22 |  |  | 2020-08-18 11:50 |  |  | 2022 | Order and Notification
6998 | Resource change | 35052735 | 114706118 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | Approved | 08W | [7 empty] | 2021-04-02 | [13 empty] | UNSC | [17 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-14 12:01 |  |  |  | Not in Work Plan
5928 | Resource change | 35103065 |  | CWSP - MORAGA 1101 - LR 108540 PH 1 | Approved | 08W | [6 empty] | Carry over projects from 2019 to [REDACTED] | [14 empty] | FICL | 2019-12-18 | [16 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-13 19:14 |  |  |  | Not in Work Plan
5929 | Resource change | 35110442 |  | CWSP-VOLTA 1102-LR 1648-PH3.2 | Approved | 08W | [6 empty] | Carry over projects from 2019 to [REDACTED] | [14 empty] | FICL | 2020-05-28 | [16 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-13 19:14 |  |  |  | Not in Work Plan
5930 | Resource change | 35110445 |  | CWSP-VOLTA 1102-LR 1648-PH4.2 | Approved | 08W | [6 empty] | Carry over projects from 2019 to [REDACTED] | [14 empty] | FICL | 2020-07-01 | [16 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-13 19:14 |  |  |  | Not in Work Plan
5931 | Resource change | 35112426 |  |  | Approved | 08W | [6 empty] | Carry over projects from 2019 to [REDACTED] | [32 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-13 19:14 |  |  |  | Not in Work Plan
5838 | Budget change | 35053033 | 114688204 | CWSP - TASSAJARA 2112 - FUSE 18053 | Approved | 08W | 220 Mile Plan | [5 empty] | Request additional $608,000 required for reauthorization. Environmental remediation and monitoring through fall/winter in reseeding areas needed. This is the only work that is remaining. | 2019-12-03 | 2020-11-01 | 11746.9 | 9709000 | 2020 |  |  | 8728000 | 368855 | 8728000 | 0 |  |  | 2019-12-31 | FICL | 2021-01-13 | 2019-12-03 | [15 empty] | Approved |  |  | 2020-08-14 17:25 |  |  | 2020-08-10 08:28 |  |  | 2020 | Order and Notification
5837 | Defer project | 30977615 | 106691315 | WDDB OTTER 1102 PHASE 5 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 146307 | 974597 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | [5 empty] | Approved | Confirmed with [REDACTED] 08.24.20 |  | 2020-08-24 09:55 |  |  | 2020-08-07 17:11 |  |  |  | Not in Work Plan
5836 | Defer project | 30977614 | 106691314 | WDDB OTTER 1102 PHASE 4 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 182209 | 1035817 |  |  |  | UNSC | [9 empty] | Approved |  | Approved | [5 empty] | Approved | Confirmed with [REDACTED] 08.24.20 |  | 2020-08-24 09:55 |  |  | 2020-08-07 17:08 |  |  |  | Not in Work Plan
5835 | Defer project | 30977613 | 106691313 | WDDB OTTER 1102 PHASE 3 | Approved | 08W | [6 empty] | Due to numerous site constraints impacting all 3 Otter projects e.g. The Forest Service stated new LZ/Staging Yard location has cultural concerns, Right of Entry process with State Parks and request to perform a valuation to assist with determining a Rent value for staging of the Generators and potential cost for noise output of the Generators, location of temporary pole/line runs, trailer staging areas, vehicle staging areas, equipment staging areas etc. If reopening to tours occurs prior to or at any time mid-stage during PG&E occupying the site then PG&E to compensate for lost tour revenue. | 2019-12-15 | 2020-10-29 | [7 empty] | 177310 | 1905941 |  |  |  | PEND | [9 empty] | Approved |  | Approved | [5 empty] | Approved | Confirmed with [REDACTED] 08.24.20 |  | 2020-08-24 09:55 |  |  | 2020-08-07 16:59 |  |  |  | Not in Work Plan
5547 | Budget change | 35052820 | 114580704 | CWSP - MIWUK 1702 - OCB - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Contengency release | 2020-04-24 |  | 4109.5 | 3585097 | 2020 |  |  | 3516246 | 272868 | 3516246 |  |  |  | 2020-12-31 | DOCC | 2020-08-04 | 2020-04-24 | [15 empty] | Approved |  |  | 2020-08-07 16:37 |  |  | 2020-08-05 08:23 |  |  | 2020 | Order and Notification
5539 | Defer project | 31334291 | 117065226 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | Approved | 08W | [6 empty] | Job requires coastal commission permit (6 month lead time) causing a job ready date of 2021. | 2020-03-31 | 2021-02-05 | [7 empty] | 150000 | 741459 |  |  |  | PEND | [9 empty] | Approved |  | Approved | [5 empty] | Approved | Already implemented |  | 2020-09-03 09:49 |  |  | 2020-08-03 13:46 |  |  |  | Not in Work Plan
5529 | Budget change | 35095167 | 114832579 | CWSP - STANISLAUS 1702 - LR1888 - PH 2.1 | Approved | 08W | [6 empty] | 08W CWSP 2020 Activated Reserve Wildfire Hardening. | 2020-12-29 | [8 empty] | 2365953 |  |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-08-01 16:32 |  |  | 2020-07-30 15:19 |  |  |  | Not in Work Plan
5311 | Resource change | 35112128 | 117462629 | BR-01-04-W (E) W. WAGSTAFF PARB | Approved | 08W | [21 empty] | DOCC | [17 empty] | Approved |  |  | 2020-08-01 16:32 |  |  | 2020-07-30 11:45 |  |  |  | Not in Work Plan
4937 | Resource change | 35120949 | 117755982 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 | Denied | 08W | [6 empty] | Work identified as not having had resource updated to date | 2019-10-14 |  | 7588.6 | 14251728 | 2020 | 2021 |  | 947568.2 | [5 empty] | 2020-02-28 | DOCC | 2020-06-25 | 2019-10-14 | [15 empty] | Denied | Job removed from work plan |  | 2020-08-01 16:31 |  |  | 2020-07-30 11:45 |  |  | 2021 | Order and Notification
4816 | Budget change | 35116516 | 117608020 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.3 | Approved | 08W | [6 empty] | Wildfire Hardening, project moved from 2020 Reserve to 2020 Activated Reserve plan. | 2020-11-25 | [8 empty] | 2239022 | 0 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-08-01 16:32 |  |  | 2020-07-29 15:11 |  |  |  | Not in Work Plan
4805 | Defer project | 35116385 | 117604609 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | Approved | 08W | [6 empty] | Caltrans permitting delay. | 2022-09-23 | 2021-01-02 | 1631.8 | 3489624 | 2022 |  |  | 3808029.1 | 2815000 | 0 | 2750000 |  |  | 2020-12-25 | PEND |  | 2022-09-23 | [7 empty] | Approved |  | Approved | [5 empty] | Approved | Deferred 7/29/20; [REDACTED] and [REDACTED] signed-off |  | 2020-08-16 23:01 |  |  | 2020-07-27 12:52 |  |  | 2022 | Order and Notification
4261 | Budget change | 35115853 | 117601683 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 | Approved | 08W | [6 empty] | 08W Fire Hardening Project Budget Adjustment | 2020-09-06 | 2020-09-25 | [7 empty] | 3459188 |  |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-22 13:59 |  |  |  | Not in Work Plan
4259 | Budget change | 35114050 | 117499593 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | Approved | 08W | [6 empty] | 2020 Activated Reserve | 2020-11-02 | [8 empty] | 2981678 |  |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-22 11:12 |  |  |  | Not in Work Plan
4260 | Budget change | 35114051 | 117502234 | OCGC PINE GROVE 1102 - LR1222 - PH | Approved | 08W | [6 empty] | 2020 Activated Reserve | 2020-10-02 |  | 4307.5 | 5342998 | 2021 |  |  | 3949678 | 2575321 | 3949678 |  |  |  | 2019-12-31 | MAPP | 2021-05-26 | 2020-10-02 | [15 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-22 10:53 |  |  | 2021 | Order and Notification
4256 | Budget change | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan | [5 empty] | 2020 Work plan | 2020-09-14 | 2020-09-15 | 1376 | 3642331 | 2020 | 2021 |  | 544498 | 1257187 | 2950902 | 0 |  |  | 2020-12-01 | FICL | 2021-05-10 | 2020-09-14 | [15 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-21 11:06 |  |  | 2021 | Order and Notification
4255 | Budget change | 35056746 | 114996821 | CWSP - MIWUK 1701 OCB PHASE 2.1 | Approved | 08W | 220 Mile Plan | [5 empty] | 2020 work plan | 2020-09-14 | 2020-09-15 | 1376 | 3642331 | 2020 | 2021 |  | 544498 | 1257187 | 2950902 | 0 |  |  | 2020-12-01 | FICL | 2021-05-10 | 2020-09-14 | [15 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-21 11:03 |  |  | 2021 | Order and Notification
4253 | Budget change | 74022388 | 114266765 | CWSP: X-1104 OH RECOND SKYLINE | Approved | 08W | 220 Mile Plan | [6 empty] | 2020-02-14 |  | 6713 | 5476214 | 2020 |  |  | 5268810 |  | 5268810 |  |  |  | 2020-03-01 | CONS |  | 2020-02-14 | [15 empty] | Approved |  |  | 2020-07-23 22:32 |  |  | 2020-07-20 13:58 |  |  | 2020 | Order and Notification
4205 | Budget change | 35116388 | 117604672 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-07-30 | 2020-09-01 | [7 empty] | 4458163 | 0 |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-17 11:02 |  |  |  | Not in Work Plan
3923 | Budget change | 35116515 | 117607998 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Wildfire Hardening, project moved from 2020 Reserve to 2020 Activated Reserve plan. | 2020-12-07 | [8 empty] | 3203035 | 0 |  |  |  | UNSC | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 14:31 |  |  |  | Not in Work Plan
3921 | Budget change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Wildfire Hardening | 2021-04-15 | 2020-09-09 | 2558 | 4624169 | 2020 | 2021 |  | 103947 | 3135435 | 3239382 | 0 |  |  | 2020-12-25 | CONS |  | 2021-04-15 | [15 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 13:06 |  |  | 2021 | Order and Notification
3868 | Resource change | 35129767 | 114810960 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 | Approved | 08W | [7 empty] | 2020-10-31 | [13 empty] | ESTS | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 12:57 |  |  |  | Not in Work Plan
3870 | Resource change | 35142828 | 118218953 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 | Approved | 08W | [7 empty] | 2020-10-28 | [13 empty] | CONS | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 12:57 |  |  |  | Not in Work Plan
3869 | Resource change | 35142827 | 118218951 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 | Approved | 08W | [7 empty] | 2020-11-04 | [13 empty] | PEND | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 12:57 |  |  |  | Not in Work Plan
3896 | Resource change | 35142826 | 118218639 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 | Approved | 08W | 2020 Rsrv | [6 empty] | 2020-10-20 |  | 2611.8 | 3876275 | 2021 |  |  | 2721318.8 | 2721318.8 |  |  |  |  | 2020-12-31 | FICL | 2021-04-12 | 2020-10-20 | [15 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-16 12:57 |  |  | 2021 | Order and Notification
3652 | Budget change | 35116443 | 117605181 | CWSP-MIWUK 1702-LR 38218-PH 1.4 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-06-28 | 2020-08-18 | [7 empty] | 3345785 | 0 |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-14 13:25 |  |  |  | Not in Work Plan
3651 | Budget change | 35115052 | 117496040 | CWSP - MIWUK 1701_OCB - PH 1.4 | Approved | 08W | [6 empty] | Wildfire Hardening | 2020-06-22 | 2020-08-26 | [7 empty] | 2920492 | 0 |  |  |  | CONS | [17 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-14 13:19 |  |  |  | Not in Work Plan
3650 | Budget change | 35052821 | 114593976 | T2/T3-CWSP - MIWUK 1701 OCB - PH 1.1 | Approved | 08W | 220 Mile Plan | [5 empty] | Critical Fire Hardening work; $301/ft | 2020-08-31 | 2020-08-31 | 1492 | 4765282 | 2020 | 2021 |  | 798819 | 1382243 | 3323925 | 0 |  |  | 2020-12-31 | CONS |  | 2020-08-31 | [15 empty] | Approved |  |  | 2020-07-18 19:35 |  |  | 2020-07-14 11:15 |  |  | 2021 | Order and Notification
2941 | Budget change | 35115151 | 117493857 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Increse MPP budget by $472,747.85 to align with 2020 budget year per gate review meeting | 2020-08-17 | 2020-08-25 | 1832.1 | 5273989 | 2020 | 2021 |  | 4025666.85 | 2520547.9 | 4025666.85 |  |  |  | 2020-12-31 | FICL | 2021-05-27 | 2020-08-17 | [15 empty] | Approved | Project on 220 mile plan |  | 2020-07-10 18:18 |  |  | 2020-07-09 11:02 |  |  | 2021 | Order and Notification
2939 | Defer project | 35052737 | 114675474 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Approved | 08W | 2021 Rsrv | [5 empty] | Due to Caltrans permitting delay, project will not be started in 2020 | 2022-01-04 | 2021-01-01 | 2163 | 2768676 | 2021 | 2022 |  | 4086056.3 | 44404 | 0 | 1876271 |  |  | 2021-07-12 | PEND |  | 2022-01-04 | [7 empty] | Approved |  | Approved | [REDACTED] has now been informed of project deferral. |  |  |  |  | Approved | Deferred 7/29/20; [REDACTED] and [REDACTED] signed-off |  | 2020-08-16 22:59 |  |  | 2020-07-09 07:57 |  |  | 2022 | Order and Notification
2937 | Defer project | 35052737 |  | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 | Denied | 08W | [6 empty] | Due to Caltrans permitting delays. Project will not be completed in 2020 and should be removed from the 2020 work plan |  | 2021-01-01 | [7 empty] | 0 | 3500000 |  |  |  | PEND | [9 empty] | Approved |  | Approved | [5 empty] | Denied | Duplicate of Change ID 3061 |  | 2020-08-28 12:30 |  |  | 2020-07-09 07:51 |  |  |  | Not in Work Plan
2932 | Budget change | 35072360 | 114754229 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | Approved | 08W | [6 empty] | 08W fire hardening project adjust budget | 2020-09-12 | 2020-08-27 | [7 empty] | 1932059 | 0 |  |  |  | CONS | [17 empty] | Approved | Project part of 220 Mile Plan |  | 2020-07-09 10:41 |  |  | 2020-07-07 14:54 |  |  |  | Not in Work Plan
1926 | Budget change | 35114048 | 117499466 | OCGC CWSP - PINE GROVE 1102 - LR1222 | Approved | 08W | 220 Mile Plan | [5 empty] | System Hardening work. Amount requested based on final Job Estimate and Constructability Review. | 2020-08-14 | 2020-12-15 | 1748 | 4178929 | 2020 | 2021 |  | 1323768 | 1810131 | 3133899 |  |  |  | 2021-12-31 | FICL | 2021-05-06 | 2020-08-14 | [15 empty] | Approved |  |  | 2020-07-06 12:58 |  |  | 2020-06-29 14:55 |  |  | 2021 | Order and Notification
1916 | Budget change | 35114044 | 117502841 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 | Approved | 08W | 220 Mile Plan | [5 empty] | 08W Fire Hardening Project adjust CBP to match | 2020-08-12 | 2020-08-01 | 2524.7 | 3012702 | 2020 | 2021 |  | 2235937 | 20105.2 | 2235937 |  |  |  | 2019-12-06 | FICL | 2021-02-25 | 2020-08-12 | [15 empty] | Approved |  |  | 2020-06-27 18:19 |  |  | 2020-06-26 13:35 |  |  | 2021 | Order and Notification
1634 | Resource change | 35145522 | 117639249 | PSPS - CLARKSVILLE 2104 - CB UG | Denied | 08W | [6 empty] | RCR update process - Project Added and Resource Updated | [14 empty] | PEND | [17 empty] | Denied | Resubmit. Notification and Order do not match. |  | 2020-06-27 18:16 |  |  | 2020-06-26 11:00 |  |  |  | Not in Work Plan
1354 | Defer project | 74022385 | 114691436 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 | Approved | 08W | [6 empty] | Project still in design phase; CT impasse hindering final design; pushing out to 2021. No estimate available yet due to this. | 2022-03-21 | 2021-06-01 | 9 | 999000 | 2022 |  |  | 750000 | 3379.1 | 750000 |  |  |  | 2020-11-30 | APPR |  | 2022-03-21 | [7 empty] | Approved |  | Approved | [REDACTED] reviewed and confirmed no issues |  |  |  |  | Approved | Reviewed by [REDACTED] |  | 2020-07-28 09:52 |  |  | 2020-06-25 11:57 |  |  | 2022 | Order and Notification
1352 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Denied | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP to match Final Estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2922407 |  |  |  |  | PEND | [17 empty] | Denied | Duplicate |  | 2020-06-27 18:16 |  |  | 2020-06-24 10:00 |  |  |  | Not in Work Plan
1351 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Denied | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP budget to match final estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2466182 |  |  |  |  | PEND | [17 empty] | Denied | Duplicate |  | 2020-06-27 18:16 |  |  | 2020-06-24 08:25 |  |  |  | Not in Work Plan
1350 | Budget change | 35115849 | 117602058 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 | Approved | 08W | [6 empty] | 08W Fire Hardening Project adjust CBP to final estimate | 2020-11-21 | 2020-12-14 | [7 empty] | 2922407 |  |  |  |  | PEND | [17 empty] | Approved |  |  | 2020-06-27 18:19 |  |  | 2020-06-24 08:09 |  |  |  | Not in Work Plan
1348 | Budget change | 35116394 | 117605556 | CWSP - MIWUK 1702 - OCB - PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Contingency release due to unexpected overhead cost increases. | 2020-06-07 | 2020-06-23 | 4778 | 2102204 | 2020 |  |  | 1990076 |  | 1990076 |  |  |  | 2019-12-27 | CONS | [17 empty] | Approved |  |  | 2020-06-27 18:19 |  |  | 2020-06-23 16:55 |  |  | 2020 | Order and Notification
1342 | Budget change | 35116383 | 117604600 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | Updated constructability review after phase gate call to include risks discussed and veg est at $300k/mile | 2021-03-08 | 2020-08-17 | 1953 | 3758449 | 2020 | 2021 |  | 1077436 | 850000 | 2531607.33 |  |  |  | 2021-06-30 | CONS |  | 2021-03-08 | [15 empty] | Approved |  |  | 2020-06-27 18:19 |  |  | 2020-06-23 10:04 |  |  | 2021 | Order and Notification
365 | Budget change | 35115051 | 117495949 | CWSP - MIWUK 1701_OCB - PH 1.3 | Denied | 08W | [6 empty] | Requesting budget to cover project work in 2020 | 2020-07-28 | 2020-07-28 | [7 empty] | 1623456.19 |  |  |  |  | CONS | [17 empty] | Denied | MPP Approved Budget sufficient |  | 2020-07-09 10:46 |  |  | 2020-06-15 21:06 |  |  |  | Not in Work Plan
362 | Budget change | 35103324 | 117251430 | CWSP - ROSSMOOR 1102 - OCB | Approved | 08W | 220 Mile Plan | [5 empty] | Increase in overhead costs. | 2020-10-30 | 2020-06-30 | 1360.6 | 2510809 | 2020 |  |  | 654743 |  | 654743 |  |  |  | 2020-12-31 | DOCC | [17 empty] | Approved |  |  | 2020-06-19 18:22 |  |  | 2020-06-15 15:27 |  |  | 2020 | Order and Notification
358 | Budget change | 35115050 | 117495948 | CWSP - MIWUK 1701_OCB - PH 1.2 | Denied | 08W | 220 Mile Plan | [5 empty] | Requesting Budget for 2020 year | 2020-08-10 | 2020-08-04 | 2728 | 4091239 | 2020 | 2021 |  | 5030586.4 | 744758.2 | 2507646.03 |  |  |  | 2021-04-30 | DOCC |  | 2020-08-10 | [15 empty] | Denied | MPP Approved Budget sufficient |  | 2020-07-09 10:46 |  |  | 2020-06-15 12:00 |  |  | 2021 | Order and Notification
357 | Budget change | 35115050 | 119073950 | CWSP - MIWUK 1701_OCB - PH 1.2 | Denied | 08W | [6 empty] | Requesting Budget for 2020 |  | 2020-08-04 | [7 empty] | 2507646.03 |  |  |  |  | DOCC | [17 empty] | Denied | MPP Approved Budget sufficient |  | 2020-07-09 10:46 |  |  | 2020-06-15 11:23 |  |  |  | Not in Work Plan
326 | Budget change | 35114040 | 117500499 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 | Approved | 08W | 220 Mile Plan | [5 empty] | System Hardening work. Amount requested based on final Job Estimate and Constructability Review. | 2020-07-29 | 2020-10-19 | 4154.9 | 4232824 | 2020 | 2022 |  | 1150000 | 1750000 | 3110000 |  |  |  | 2019-12-06 | CONS |  | 2020-07-29 | [15 empty] | Approved | Budget is sufficient. On 220 Mile Plan. |  | 2020-06-12 11:55 |  |  | 2020-06-12 09:49 |  |  | 2022 | Order and Notification
10131 | Budget change | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-07-21 |  | 1883.9 | 2193681.27 | 2020 | 2021 |  | 3322836 | 1168197.9 | 3322836 |  |  |  | 2021-12-31 | FICL | 2021-04-23 | 2020-07-21 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2021 | Order and Notification
10182 | Budget change | 35114049 | 117499469 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-07-21 |  | 1883.9 | 2193681.27 | 2020 | 2021 |  | 3322836 | 1168197.9 | 3322836 |  |  |  | 2021-12-31 | FICL | 2021-04-23 | 2020-07-21 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2021 | Order and Notification
10154 | Budget change | 35114042 | 117500694 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-06-18 |  | 2597.2 | 2867650 | 2020 |  |  | 2084370 |  | 2084370 |  |  |  | 2020-10-23 | FICL | 2020-08-25 | 2020-06-18 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2020 | Order and Notification
10103 | Budget change | 35114042 | 117500694 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-06-18 |  | 2597.2 | 2867650 | 2020 |  |  | 2084370 |  | 2084370 |  |  |  | 2020-10-23 | FICL | 2020-08-25 | 2020-06-18 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2020 | Order and Notification
51506 | Add project | 35115152 | 117495855 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 | Approved | 08W | [6 empty] | WGC (Wildfire Governance Committee) agreed to pull this project back into the 2021 work plan. | 2021-05-14 |  | 1598.4 | 3591121 | 2021 |  | 2021 | 370000 | 2229051.5 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-14 | [12 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [5 empty] | 2021 | Order and Notification
10146 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2021-03-08 |  | 2455.4 | 4734585 | 2020 | 2021 |  | 3595900 | 3080584.2 | 3595900 |  |  |  | 2020-12-31 | CONS |  | 2021-03-08 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2021 | Order and Notification
10197 | Budget change | 35115153 | 117495859 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2021-03-08 |  | 2455.4 | 4734585 | 2020 | 2021 |  | 3595900 | 3080584.2 | 3595900 |  |  |  | 2020-12-31 | CONS |  | 2021-03-08 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2021 | Order and Notification
10172 | Budget change | 35114431 | 117572146 | CWSP - MORAGA 1101 - LR108540 - PH5 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-03-31 |  | 4180.7 | 5279014 | 2020 |  |  | 3868379 |  | 3868379 |  |  |  | 2020-12-30 | DOCC | [17 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2020 | Order and Notification
10121 | Budget change | 35114431 | 117572146 | CWSP - MORAGA 1101 - LR108540 - PH5 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-03-31 |  | 4180.7 | 5279014 | 2020 |  |  | 3868379 |  | 3868379 |  |  |  | 2020-12-30 | DOCC | [17 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2020 | Order and Notification
10129 | Budget change | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-07-15 |  | 2736 | 3849738 | 2020 | 2021 |  | 1894612 | 201890 | 2989278 |  |  |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2021 | Order and Notification
10180 | Budget change | 35116442 | 117605169 | CWSP-MIWUK 1702-LR 38218-PH 1.3 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-07-15 |  | 2736 | 3849738 | 2020 | 2021 |  | 1894612 | 201890 | 2989278 |  |  |  | 2020-12-31 | DOCC | 2021-02-04 | 2020-07-15 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2021 | Order and Notification
51393 | Resource change | 35116384 | 117604604 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 | Approved | 08W | 220 Mile Plan | [6 empty] | 2021-04-15 |  | 2558 | 4624169 | 2020 | 2021 |  | 103947 | 3135435 |  |  |  |  | 2020-12-25 | CONS |  | 2021-04-15 | [15 empty] | Approved |  |  | 2021-03-03 17:48 | [5 empty] | 2021 | Order and Notification
10117 | Budget change | 35116390 | 117604678 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-10-05 |  | 1222.2 | 1195542 | 2020 |  |  | 935005 |  | 935005 |  |  |  | 2020-12-25 | UNSC |  | 2020-10-05 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2020 | Order and Notification
10168 | Budget change | 35116390 | 117604678 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-10-05 |  | 1222.2 | 1195542 | 2020 |  |  | 935005 |  | 935005 |  |  |  | 2020-12-25 | UNSC |  | 2020-10-05 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2020 | Order and Notification
10148 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-08-10 |  |  |  | 2021 |  |  |  |  | 1992384 |  |  |  |  | PEND | [17 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [6 empty] | Not in Work Plan
10199 | Budget change | 35116519 | 117608026 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.4 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-08-10 |  |  |  | 2021 |  |  |  |  | 1992384 |  |  |  |  | PEND | [17 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [6 empty] | Not in Work Plan
10118 | Budget change | 35119966 | 117721841 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-02-14 |  | 1106 | 1552000 | 2020 |  |  | 1136736 |  | 1136736 |  |  |  | 2020-12-31 | FICL | 2020-03-10 | 2020-02-14 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2020 | Order and Notification
10169 | Budget change | 35119966 | 117721841 | CWSP - LOS GATOS 1106 - LB44 - PH 2.6F | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-02-14 |  | 1106 | 1552000 | 2020 |  |  | 1136736 |  | 1136736 |  |  |  | 2020-12-31 | FICL | 2020-03-10 | 2020-02-14 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2020 | Order and Notification
10125 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Withdrawn | 08W | 220 Mile Plan | [5 empty] | Legacy approved Budget | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 3110193 | 75000 | 3110193 |  |  |  | 2020-12-31 | MAPP | 2020-10-02 | 2020-07-27 | [15 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [5 empty] | 2020 | Order and Notification
10176 | Budget change | 35112434 | 117472389 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 | Approved | 08W | 220 Mile Plan | [5 empty] | Legacy Buget approved | 2020-07-27 |  | 3098.1 | 3756886 | 2020 |  |  | 3110193 | 75000 | 3110193 |  |  |  | 2020-12-31 | MAPP | 2020-10-02 | 2020-07-27 | [15 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [5 empty] | 2020 | Order and Notification
10167 | Budget change | 35043423 | 114678726 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-04-09 |  |  |  | 2021 |  |  |  |  | 1638834 |  |  |  |  | PEND | [17 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [6 empty] | Not in Work Plan
10116 | Budget change | 35043423 | 114678726 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-04-09 |  |  |  | 2021 |  |  |  |  | 1638834 |  |  |  |  | PEND | [17 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [6 empty] | Not in Work Plan
51392 | Resource change | 35052825 | 114701195 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 | Approved | 08W | 220 Mile Plan | [6 empty] | 2021-05-03 |  | 1833.1 | 3544410 | 2021 | 2021 |  | 288570 | 1048628 |  |  |  |  | 2020-12-31 | CONS |  | 2021-05-03 | [15 empty] | Approved |  |  | 2021-03-03 17:48 | [5 empty] | 2021 | Order and Notification
10147 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Withdrawn | 08W | [6 empty] | Legacy approved Budget | 2021-05-19 |  |  |  | 2021 |  |  |  |  | 1474118 |  |  |  |  | PEND | [17 empty] | Withdrawn | duplicate budget change request |  | 2020-10-12 00:11 | [6 empty] | Not in Work Plan
10198 | Budget change | 35095168 | 114832575 | CWSP - STANISLAUS 1702 - LR1888 - PH 1.1 | Approved | 08W | [6 empty] | Legacy Buget approved | 2021-05-19 |  |  |  | 2021 |  |  |  |  | 1474118 |  |  |  |  | PEND | [17 empty] | Approved | Legacy budget approvals |  | 2020-10-12 00:17 | [6 empty] | Not in Work Plan
51433 | Add project | 35233315 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.5 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Denied | Duplicate of change ID 51805 |  | 2021-03-08 15:23 | [6 empty] | Not in Work Plan
51437 | Add project | 35232718 |  | FRRB - WYANDOTTE 1103 - W2 PH2.1 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | UNSC | [14 empty] | Approved |  |  | Denied | Duplicate of change ID 51801 |  | 2021-03-08 15:23 | [6 empty] | Not in Work Plan
51418 | Add project | 35233039 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51426 | Add project | 35233307 |  | FRRB - WYANDOTTE 1103 - W1 PH1.11 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51403 | Add project | 35226872 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51405 | Add project | 35226878 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51434 | Add project | 35219281 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51548 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Denied | 08W | [6 empty] | Pulling project back into 2021, per Asset Manager | 2021-09-01 | [8 empty] | 517463 | 2685572 |  |  |  | UNSC | [14 empty] | Denied |  |  | Denied | Duplicate |  | 2021-03-04 10:51 | [6 empty] | Not in Work Plan
51549 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Approved | 08W | [6 empty] | Pulling project back in 2021 per Asset Manager | 2021-09-01 | [8 empty] | 517463 | 2685572 |  |  |  | UNSC | [14 empty] | Approved |  |  | Approved |  |  | 2021-03-04 10:50 | [6 empty] | Not in Work Plan
51539 | Add project | 35116515 |  | CWSP - STANISLAUS 1702 - LR1888 - PH 1.2 | Denied | 08W | [6 empty] | Project pulled back into 2021 work plan. Approved by Wildfire Governance Committee | 2021-09-01 | [9 empty] | 2685572 |  |  |  | UNSC | [14 empty] | Denied |  |  | Denied | Duplicate |  | 2021-03-04 10:51 | [6 empty] | Not in Work Plan
51397 | Add project | 35226863 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51399 | Add project | 35226865 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51400 | Add project | 35226866 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51402 | Add project | 35226871 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51435 | Add project | 35232650 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51411 | Add project | 35223030 |  | PSPS - BANGOR 1101 CB - MICROGRID | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51412 | Add project | 35224321 |  | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51398 | Add project | 35226864 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51409 | Add project | 35227004 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51420 | Add project | 35233301 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51422 | Add project | 35233303 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51425 | Add project | 35233306 |  | FRRB - WYANDOTTE 1103 - W1 PH1.10 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51427 | Add project | 35233308 |  | FRRB - WYANDOTTE 1103 - W1 PH1.12 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51413 | Add project | 35226798 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51401 | Add project | 35226870 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51407 | Add project | 35227002 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51438 | Add project | 35219589 |  | CWSP - WILDWOOD 11011454 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51436 | Add project | 35232651 |  | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51430 | Add project | 35233311 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.2 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Denied | Duplicate of change ID 51802 |  | 2021-03-08 15:23 | [6 empty] | Not in Work Plan
51432 | Add project | 35233314 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.4 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Denied | Duplicate of change ID 51804 |  | 2021-03-08 15:23 | [6 empty] | Not in Work Plan
51410 | Add project | 35223036 |  | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51404 | Add project | 35226873 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51414 | Add project | 35226799 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51429 | Add project | 35233310 |  | FRRB - WYANDOTTE 1103 - W1 PH1.14 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51431 | Add project | 35233312 |  | FRRB - WYANDOTTE 1103 - W2 - PH2.3 | Denied | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [14 empty] | PEND | [14 empty] | Approved |  |  | Denied | Duplicate of change ID 51803 |  | 2021-03-08 15:23 | [6 empty] | Not in Work Plan
51415 | Add project | 35226900 |  | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ADER | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51406 | Add project | 35227001 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51408 | Add project | 35227003 |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | ESTS | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51416 | Add project | 35232298 |  | FRRB - WYANDOTTE 1103 - W1 PH1.1 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | PEND | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51417 | Add project | 35233038 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51419 | Add project | 35233300 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51421 | Add project | 35233302 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51423 | Add project | 35233304 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51424 | Add project | 35233305 |  | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan
51428 | Add project | 35233309 |  | FRRB - WYANDOTTE 1103 - W1 PH1.13 | Approved | 08W | [6 empty] | WFGC recently approved scope for project to pull into 2021 workplan | [6 empty] | 2021 | [7 empty] | UNSC | [14 empty] | Approved |  |  | Approved | Approved with 2021 completion year |  | 2021-03-08 15:18 | [6 empty] | Not in Work Plan

## NCFR - Suborder Tables
Name | Date modified | Date created | Custom.Name | Column1 | Custom.Data.Column1 | Custom.Data.Column2 | Custom.Data.Column3 | Custom.Data.Column4 | Custom.Data.Column5 | Custom.Data.Column6 | Custom.Data.Column7 | Custom.Data.Column8 | Custom.Data.Column9 | Custom.Data.Column10 | Custom.Data.Column11 | Custom.Data.Column12 | Custom.Data.Column13 | Custom.Data.Column14 | Custom.Data.Column15 | Custom.Item | Custom.Kind | Custom.Hidden
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM K4 |  | WBS Level 1 or Project Definition | WBS Level 3 | Name | Address | Notification | PM Order | Order Type | Planning Order | MAT Code | OH Footage | UG Footage | DER Footage |  |  |  | SM K4 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM K2 |  | WBS Level 1 or Project Definition | WBS Level 3 | Name | Address | Notification | PM Order | Order Type | Planning Order | MAT Code | OH Footage | UG Footage | DER Footage |  |  |  | SM K2 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W3 |  | WBS Level 1 or Project Definition | WBS Level 3 | Name | Address | Notification | PM Order | Order Type | Planning Order | MAT Code | OH Footage | UG Footage | DER Footage |  |  |  | SM W3 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W1 |  | WBS Level 1 or Project Definition | WBS Level 4 | Name | Address | Notification | PM Order | Order Type | Planning Order | MAT Code | OH Footage | UG Footage | DER Footage |  |  |  | SM W1 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W1 |  | E.5034933 | E.5034933.01.09 | FRRB – Wyandotte 11031974 – W1 SM1 |  | 120827953 | 35244330 | E470 | 5796539 | 08W |  | 500 |  |  |  |  | SM W1 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W3 |  | E.5034933 | E.50334933.01.11 | FRRB – Wyandotte 11031974 – W3 SM2 |  | 120830887 | 35244574 | E470 | 5796539 | 08W |  | 350 |  |  |  |  | SM W3 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W3 |  | E.5034933 | E.5034933.01.10 | FRRB – Wyandotte 11031974 – W3 SM1 |  | 120830881 | 35244573 | E470 | 5796539 | 08W |  | 700 |  |  |  |  | SM W3 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W3 |  | E.5034933 | E.5034933.01.13 | FRRB – Wyandotte 11031974 – W3 SM3 |  | 120950640 | 35249161 | E470 | 5796539 | 08W |  | 1200 |  |  | 0.22727 | 795454.5455 | SM W3 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM W1 |  | E.5034933 | E.5034933.01.12 | FRRB – Wyandotte 11031974 – W1 SM2 |  | 120942639 | 35248770 | E470 | 5796539 | 08W |  | 220 |  |  |  |  | SM W1 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM K2 |  | E.5034933 | E.5034933.01.15 | FRRB - KANAKA 1101CB - K2 SM2 |  | 121445613 | 35254695 | E470 | 5796539 | 08W |  | 350 |  |  |  |  | SM K2 | Sheet | FALSE
Suborder Table - Short Mainline.xlsx | 2021-06-22 17:53 | 2021-04-16 22:03 | SM K2 |  | E.5034933 | E.5034933.01.14 | FRRB - KANAKA 1101CB - K2 SM1 |  | 121318070 | 35250343 | E470 | 5796539 | 08W |  | 1585 |  |  |  |  | SM K2 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Feet UG |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.12 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 | REMOVAL 66 | 120542507 | 35233305 | E470 | 5795419 | 08W |  | 0.56951 | 3007 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.13 | FRRB - WYANDOTTE 1103 - W1 PH 1.10 | REMOVAL 67 | 120541535 | 35233306 | E470 | 5795419 | 08W |  | 0.35909 | 1896 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.14 | FRRB - WYANDOTTE 1103 - W1 PH 1.11 | REMOVAL 68 | 120541538 | 35233307 | E470 | 5795419 | 08W |  | 0.4197 | 2216 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.16 | FRRB - WYANDOTTE 1103 - W1 PH 1.13 | REMOVAL 64 | 120541630 | 35233309 | E470 | 5795419 | 08W |  | 0.37519 | 1981 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.15 | FRRB - WYANDOTTE 1103 - W1 PH 1.12 | REMOVAL 70 | 120541539 | 35233308 | E470 | 5795419 | 08W |  | 1.4047 | 7417 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.17 | FRRB - WYANDOTTE 1103 - W1 PH 1.14 | REMOVAL 71 | 120541632 | 35233310 | E470 | 5795419 | 08W |  | 0.30246 | 1597 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.07 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 | REMOVAL 61 | 120542502 | 35233300 | E470 | 5795419 | 08W |  | 0.36004 | 1901 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.09 | FRRB - WYANDOTTE 1103 - W1 PH 1.6 | REMOVAL 60 | 120542504 | 35233302 | E470 | 5795419 | 08W |  | 0.15114 | 798 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.06 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 | REMOVAL 59 | 120542500 | 35233039 | E470 | 5795419 | 08W |  | 0.46326 | 2446 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.11 | FRRB - WYANDOTTE 1103 - W1 PH 1.8 | REMOVAL 65 | 120542506 | 35233304 | E470 | 5795419 | 08W |  | 0.38314 | 2023 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.10 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 | REMOVAL 63 | 120542505 | 35233303 | E470 | 5795419 | 08W |  | 0.075 | 396 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.02 | FRRB - WYANDOTTE 1103 - W1 PH 1.1 | REMOVAL 58 | 120532441 | 35232298 | E470 | 5795419 | 08W |  | 0.26875 | 1419 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.08 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 | REMOVAL 62 | 120542503 | 35233301 | E470 | 5795419 | 08W |  | 0.1428 | 754 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232295 W1.xlsx | 2021-06-08 18:09 | 2021-02-19 20:48 | Sheet1 |  | E.5034825 | E.5034825.01.05 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 | REMOVAL 56 | 120542278 | 35233038 | E470 | 5795419 | 08W |  | 0.49508 | 2614 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Footage UG | Footage DER |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.72 | FRRB - WYANDOTTE 1103 - W2 PH2.10 | REMOVAL 77 | 120695189 | 35239523 | E470 | 5795419 | 08W | 1300 |  | 0.24621 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.73 | FRRB - WYANDOTTE 1103 W2 PH 2.11 | REMOVAL 48 & 49 | 120711267 | 35239937 | E470 | 5795419 | 08W | 2585 |  | 0.48958 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.40 | FRRB - WYANDOTTE 1103 - W2 PH2.6 | REMOVAL 116, FH-45T, REMOVAL 117, REMOVAL 111, REMOVAL 87 | 120594567 | 35235705 | E470 | 5795419 | 08W | 9182 |  | 1.739 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.90 | FRRB - WYANDOTTE 1103 W2 PH 2.13 | REMOVAL 103 | 120723697 | 35240546 | E470 | 5795419 | 08W | 691 |  | 0.13087 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.89 | FRRB - WYANDOTTE 1103 W2 PH 2.12 | FH-58T, REMOVAL 102 | 120723696 | 35240545 | E470 | 5795419 | 08W | 769 |  | 0.14564 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.71 | FRRB - WYANDOTTE 1103 - W2 PH2.9 | REMOVAL 76 | 120695185 | 35239522 | E470 | 5795419 | 08W | 1840 |  | 0.34848 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.20 | FRRB - WYANDOTTE 1103 - W2 PH2.4 | FH-43T, REMOVAL 47, REMOVAL 81, REMOVA 83, REMOVAL 113 | 120541635 | 35233314 | E470 | 5795419 | 08W | 13057 |  | 2.4729 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.18 | FRRB - WYANDOTTE 1103 - W2 PH2.2 | REMOVAL 79, FH-42T, REMOVAL 226, REMOVAL 74 | 120541633 | 35233311 | E470 | 5795419 | 08W | 3633 |  | 0.68807 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.03 | FRRB - WYANDOTTE 1103 - W2 PH2.1 | included in KMZ | 120538803 | 35232718 | E470 | 5795419 | 08W | 2414 |  | 0.4572 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.42 | FRRB - WYANDOTTE 1103 - W2 PH2.8 | REMOVAL 112 | 120594569 | 35235707 | E470 | 5795419 | 08W | 5430 | 0 | 1.0284 | 0 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.41 | FRRB - WYANDOTTE 1103 - W2 PH2.7 | REMOVAL 114 | 120594568 | 35235706 | E470 | 5795419 | 08W | 3907 |  | 0.73996 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.21 | FRRB - WYANDOTTE 1103 - W2 PH2.5 | REMOVAL 224, REMOVAL 72 | 120541636 | 35233315 | E470 | 5795419 | 08W | 4247 |  | 0.80436 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35232718 W2.xlsx | 2021-06-02 20:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.19 | FRRB - WYANDOTTE 1103 - W2 PH2.3 | FH-96T, FH-78T, REMOVAL 225, REMOVAL 82 | 120541634 | 35233312 | E470 | 5795419 | 08W | 4360 |  | 0.82576 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Footage UG |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.59 | FRRB - WYANDOTTE 1103 - W3 PH3.2 | Removal 123 A, 125, FH-85T | 120647269 | 35237889 | E470 | 5795419 | 08W |  | 1.3674 | 7220 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.60 | FRRB - WYANDOTTE 1103 - W3 PH3.3 | Removal 126 | 120647402 | 35237890 | E470 | 5795419 | 08W |  | 1.0907 | 5759 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.51 | FRRB - WYANDOTTE 1103 - W3 PH3.9 | FH-54T, FH-100T, Removal 97, 98 | 120627591 | 35236990 | E470 | 5795419 | 08W |  | 0.85303 | 4504 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.23 | FRRB - WYANDOTTE 1103 - W3 PH3.1 | Removal 86, 205 | 120582839 | 35235320 | E470 | 5795419 | 08W |  | 0.24621 | 1300 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.64 | FRRB - WYANDOTTE 1103 - W3 PH3.7 (CANCEL) | Removal 122 - NO LONGER NEEDED | 120647408 | 35237895 | E470 | 5795419 | 08W |  | 0.78939 | 4168 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.65 | FRRB - WYANDOTTE 1103 - W3 PH3.8 | FH-95T, Removal 99, 171, 173, 174, | 120647450 | 35237896 | E470 | 5795419 | 08W |  | 1.1121 | 5872 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.63 | FRRB - WYANDOTTE 1103 - W3 PH3.6 | FH-54T, FH-94T, FH-95T, Removal 174 | 120647406 | 35237894 | E470 | 5795419 | 08W |  | 1.2672 | 6691 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.61 | FRRB - WYANDOTTE 1103 - W3 PH3.4 | Removal 57, 171, 172 | 120647404 | 35237891 | E470 | 5795419 | 08W |  | 0.41667 | 2200 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235320 W3.xlsx | 2021-06-23 16:31 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.62 | FRRB - WYANDOTTE 1103 - W3 PH3.5 | Removal 146, 147, 170 | 120647405 | 35237893 | E470 | 5795419 | 08W |  | 0.82576 | 4360 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Footage OH | Footage UG | Footage DER |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.69 | FRRB - WYANDOTTE 1103 - W4 PH 4.6 | REMOVAL 106, 107, 87, 117 | 120685590 | 35239098 | E470 | 5795419 | 08W |  | 12278 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.52 | FRRB - WYANDOTTE 1103 - W4 PH4.8 | REMOVAL 119, 120 | 120627593 | 35236991 | E470 | 5795419 | 08W |  | 6631 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.70 | FRRB - WYANDOTTE 1103 - W4 PH 4.7 | REMOVAL 118 | 120685592 | 35239099 | E470 | 5795419 | 08W |  | 2238 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.67 | FRRB - WYANDOTTE 1103 - W4 PH 4.4 | REMOVAL 91 | 120685505 | 35239096 | E470 | 5795419 | 08W |  | 4456 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.66 | FRRB - WYANDOTTE 1103 - W4 PH 4.3 | REMOVAL 104,144,177 | 120685501 | 35239095 | E470 | 5795419 | 08W | 50 | 8616 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.68 | FRRB - WYANDOTTE 1103 - W4 PH 4.5 | REMOVAL 92 | 120685508 | 35239097 | E470 | 5795419 | 08W |  | 5704 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.55 | FRRB - WYANDOTTE 1103 - W4 PH4.10 | REMOVAL 90, 93, 94 | 120627597 | 35236995 | E470 | 5795419 | 08W |  |  | 10412 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.35 | FRRB - WYANDOTTE 1103 - W4 PH4.11 | REMOVAL 119, end of REMOVAL 122, South of REMOVAL 146 | 120598982 | 35235700 | E470 | 5795419 | 08W | 178 | 7258 | 0 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.24 | FRRB - WYANDOTTE 1103 - W4 PH 4.1 | REMOVAL 84 | 120594870 | 35235669 | E470 | 5795419 | 08W |  | 2216 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.54 | FRRB - WYANDOTTE 1103 - W4 PH4.9 | REMOVAL 108 | 120627595 | 35236993 | E470 | 5795419 | 08W |  | 2530 | 0 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235669 W4.xlsx | 2021-06-11 18:55 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.26 | FRRB - WYANDOTTE 1103 - W4 PH 4.2 | REMOVAL 85 | 120594872 | 35235671 | E470 | 5795419 | 08W |  | 3504 |  |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Miles RG | UG Footage | RG Footage |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.25 | FRRB - WYANDOTTE 1103 W5 PH5.1 FUTURE SM | Removal 143 | 120594871 | 35235670 | E470 | 5795419 | 08W |  | 0.11 |  | 580.8 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.92 | FRRB - WYANDOTTE 1103 W5 PH5.3 FUTURE SM | Removal 141 | 120751207 | 35241076 | E470 | 5795419 | 08W |  | 0.11 |  | 580.8 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.91 | FRRB - WYANDOTTE 1103 W5 PH5.2 FUTURE SM | Removal 214, FH-98T | 120751204 | 35241075 | E470 | 5795419 | 08W |  | 0.07 |  | 369.6 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.93 | FRRB - WYANDOTTE 1103 W5 PH5.4 FUTURE SM | Removal 142 | 120751251 | 35241077 | E470 | 5795419 | 08W |  | 0.31 |  | 1636.8 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235670 W5.xlsx | 2021-06-11 18:13 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.46 | FRRB - WYANDOTTE 1103 - W5 PH5.5 | Removal 95, 96 | 120627454 | 35236984 | E470 | 5795419 | 08W |  |  | 1.97 |  | 10401.6 |  | Sheet1 | Sheet | FALSE
Suborder Table 35235672 W7.xlsx | 2021-06-11 18:33 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | UG Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235672 W7.xlsx | 2021-06-11 18:33 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.43 | FRRB - WYANDOTTE 1103 W7 PH7.4 FUTURE SM | Removal 139 | 120627369 | 35237021 | E470 | 5795419 | 08W |  | 0.24621 | 1300 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235672 W7.xlsx | 2021-06-11 18:33 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.27 | FRRB - WYANDOTTE 1103 W7 PH7.1 FUTURE SM | Removal 140 | 120594873 | 35235672 | E470 | 5795419 | 08W |  | 0.30303 | 1600 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235672 W7.xlsx | 2021-06-11 18:33 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.56 | FRRB - WYANDOTTE 1103 W7 PH7.2 FUTURE SM | Removal 52 | 120627598 | 35236997 | E470 | 5795419 | 08W |  | 0.28409 | 1500 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235672 W7.xlsx | 2021-06-11 18:33 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.30 | FRRB - WYANDOTTE 1103 W7 PH7.3 FUTURE SM | Removal 51 | 120596615 | 35235675 | E470 | 5795419 | 08W |  | 0.11364 | 600 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235674 B1.xlsx | 2021-06-11 17:14 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | OH Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235674 B1.xlsx | 2021-06-11 17:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.35 | FRRB - BIG BEND 1102 - B1 PH1.2 | Removal 45 | 120751299 | 35241078 | E470 | 573918 | 08W | 0.18258 |  | 964 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235674 B1.xlsx | 2021-06-11 17:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.34 | FRRB - BIG BEND 1102 - B1 PH1.1 | FH-29T | 120596259 | 35235674 | E470 | 573918 | 08W | 0.1108 |  | 585 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235674 B1.xlsx | 2021-06-11 17:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.37 | FRRB - BIG BEND 1102 - B1 PH1.4 | Removal 38 | 120751312 | 35242420 | E470 | 573918 | 08W | 0.094697 |  | 500 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235674 B1.xlsx | 2021-06-11 17:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.36 | FRRB - BIG BEND 1102 - B1 PH1.3 | Removal 46 | 120751310 | 35241079 | E470 | 573918 | 08W | 0.074621 |  | 394 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235676 B3.xlsx | 2021-06-02 20:14 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | UG Footage | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table 35235676 B3.xlsx | 2021-06-02 20:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.31 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | 120598345 | 35235676 | E470 | 5795419 | 08W | 12650 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table 35235676 B3.xlsx | 2021-06-02 20:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.22 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | 120582960 | 35235139 | E470 | 5795419 | 08W | 6962 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table 35235676 B3.xlsx | 2021-06-02 20:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.75 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | 120255838 | 35223343 | E470 | 5795419 | 08W | 5373 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table 35235676 B3.xlsx | 2021-06-02 20:14 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.78 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | 120424578 | 35225821 | E470 | 5795419 | 08W | 3346 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table 35235677 B4.xlsx | 2021-06-17 20:32 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | ` | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | UG Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235677 B4.xlsx | 2021-06-17 20:32 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.85 | FRRB - BIG BEND 1102 - B4 PH4.2 | Removal 167 | 120753070 | 35242428 | E470 | 5795419 | 08W |  | 0.84 | 4435.2 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235677 B4.xlsx | 2021-06-17 20:32 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.86 | FRRB - BIG BEND 1102 - B4 PH4.3 | Removal 128 | 120753071 | 35242429 | E470 | 5795419 | 08W |  | 0.65 | 3432 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235677 B4.xlsx | 2021-06-17 20:32 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.32 | FRRB - BIG BEND 1102 - B4 PH4.1 | FH-69UG, 70UG, 71UG, 72UG, removal 217, 218, 219 | 120598407 | 35235677 | E470 | 5795419 | 08W |  | 5.8884 | 31091 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235678 B5.xlsx | 2021-05-27 00:59 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Miles RG | OH Footage | UG Footage | DER Footage | Sheet1 | Sheet | FALSE
Suborder Table 35235678 B5.xlsx | 2021-05-27 00:59 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.33 | FRRB - BIG BEND 1102 - B5 PH5.1 | FH-73T or FH-74T | 120598535 | 35235678 | E470 | 5795419 | 08W |  |  |  | 998 | 0 | 0 | Sheet1 | Sheet | FALSE
Suborder Table 35235678 B5.xlsx | 2021-05-27 00:59 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.04 | FRRB - BIG BEND 1102 - B5 PH5.2 | REMOVAL 129 | 120541098 | 35233166 | E470 | 5795419 | 08W |  |  |  | 1322 | 0 | 0 | Sheet1 | Sheet | FALSE
Suborder Table 35235678 B5.xlsx | 2021-05-27 00:59 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.45 | FRRB - BIG BEND 1102 - B5 PH5.3 | FH-74T | 120627452 | 35236983 | E470 | 5795419 | 08W |  |  |  | 2640 | 0 | 0 | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | UG Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034933 | E.5034933.01.02 | FRRB - BIG BEND 1102 - B6 PH6.6 | FH-74T, 75T | 120753017 | 35242425 | E470 | 5796539 | 08W |  | 1.14 | 6019.2 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034933 | E.5034933.01.04 | FRRB - BIG BEND 1102 - B6 PH6.8 | Removal 135 | 120753019 | 35242427 | E470 | 5796539 | 08W |  | 0.84 | 4435.2 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034933 | E.5034933.01.03 | FRRB - BIG BEND 1102 - B6 PH6.7 | Removal 134 | 120753018 | 35242426 | E470 | 5796539 | 08W |  | 0.57 | 3009.6 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034933 | E.5034933.01.01 | FRRB - BIG BEND 1102 - B6 PH6.5 | FH-73T, Removal 132 | 120753016 | 35242424 | E470 | 5796539 | 08W |  | 0.42 | 2217.6 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.98 | FRRB - BIG BEND 1102 - B6 PH6.3 | TPL-24, Removal 136 | 120753013 | 35242422 | E470 | 5795419 | 08W |  | 0.63 | 3326.4 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.99 | FRRB - BIG BEND 1102 - B6 PH6.4 | Removal 137 | 120753015 | 35242423 | E470 | 5795419 | 08W |  | 1.08 | 5702.4 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.34 | FRRB - BIG BEND 1102 - B6 PH6.1 | FH-76T, Removal 130, 131 | 120598623 | 35235679 | E470 | 5795419 | 08W |  | 0.66 | 3484.8 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235679 B6.xlsx | 2021-04-26 22:49 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.97 | FRRB - BIG BEND 1102 - B6 PH6.2 | FH-77T | 120753012 | 35242421 | E470 | 5795419 | 08W |  | 0.75 | 3960 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235700 K1.xlsx | 2021-06-11 17:58 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | DER Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235700 K1.xlsx | 2021-06-11 17:58 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.07 | FRRB - KANAKA 1101 - K1 PH1.1 | Removal 28, 105,150 | 120627455 | 35236985 | E470 | 5795419 | 08W |  |  | 8447 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235700 K1.xlsx | 2021-06-11 17:58 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.53 | FRRB - KANAKA 1101 - K1 PH1.2 | Removal 24 | 120627594 | 35236992 | E470 | 5795419 | 08W |  |  | 3514 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235701 K2.xlsx | 2021-06-22 20:57 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Miles RG | OH Footage | DER Footage |  | Sheet1 | Sheet | FALSE
Suborder Table 35235701 K2.xlsx | 2021-06-22 20:57 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.39 | FRRB - KANAKA 1101 - K2 PH2.2 | Removal 1 | 120627501 | 35236989 | E470 | 5793918 | 08W | 0.51326 |  | 0 | 2710 | 0 |  | Sheet1 | Sheet | FALSE
Suborder Table 35235701 K2.xlsx | 2021-06-22 20:57 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.38 | FRRB - KANAKA 1101 - K2 PH2.1 | FH-4T | 120599070 | 35235701 | E470 | 5793918 | 08W | 0.10909 |  |  | 576 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235702 K3.xlsx | 2021-06-11 20:44 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | UG Footage |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235702 K3.xlsx | 2021-06-11 20:44 | 2021-03-12 22:19 | Sheet1 |  | E.5034825 | E.5034825.01.37 | FRRB - KANAKA 1101 - K3 PH3.1 | FH-47M, REMOVAL 3 | 1205990782 | 35235702 | E470 | 5795419 | 08W |  | 1.44 | 7603.2 |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | OH Footage | UG Footage | DER Footage | miles |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.19 | FRRB - KANAKA 1101 - K4 PH 4.3 | REMOVAL 14 | 120849797 | 35244698 | E470 | 5793918 | 08W | 477 |  |  | 0.090341 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.20 | FRRB - KANAKA 1101 - K4 PH 4.4 | REMOVAL 15 | 120849798 | 35244699 | E470 | 5793918 | 08W | 423 |  |  | 0.080114 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.22 | FRRB - KANAKA 1101 - K4 PH 4.6 | REMOVAL 17 | 120850151 | 35245141 | E470 | 5793918 | 08W | 218 |  |  | 0.041288 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.21 | FRRB - KANAKA 1101 - K4 PH 4.5 | REMOVAL 163 | 120850150 | 35245140 | E470 | 5793918 | 08W | 1404 |  |  | 0.26591 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.16 | FRRB - KANAKA 1101 - K4 PH 4.18 | REMOVAL 8 | 120720968 | 35240543 | E470 | 5793918 | 08W | 6519 |  |  | 1.2347 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.25 | FRRB - KANAKA 1101 - K4 PH 4.9 | REMOVAL 30 | 120850156 | 35245144 | E470 | 5793918 | 08W | 1314 |  |  | 0.24886 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.18 | FRRB - KANAKA 1101 - K4 PH 4.2 | REMOVAL 13 | 120849796 | 35244697 | E470 | 5793918 | 08W | 655 |  |  | 0.12405 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.17 | FRRB - KANAKA 1101 - K4 PH 4.1 | REMOVAL 12 | 120849795 | 35244696 | E470 | 5793918 | 08W | 1563 |  |  | 0.29602 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.29 | FRRB - KANAKA 1101 - K4 PH 4.13 | REMOVAL 39 | 120850482 | 35245148 | E470 | 5793918 | 08W | 1082 |  |  | 0.20492 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.28 | FRRB - KANAKA 1101 - K4 PH 4.12 | REMOVAL 36 | 120850159 | 35245147 | E470 | 5793918 | 08W | 2072 |  |  | 0.39242 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.30 | FRRB - KANAKA 1101 - K4 PH 4.14 | REMOVAL 4 | 120850485 | 35245149 | E470 | 5793918 | 08W | 1420 |  |  | 0.26894 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.32 | FRRB - KANAKA 1101 - K4 PH 4.16 | REMOVAL 42 | 120850487 | 35245151 | E470 | 5793918 | 08W | 816 |  |  | 0.15455 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.31 | FRRB - KANAKA 1101 - K4 PH 4.15 | REMOVAL 40 | 120850486 | 35245150 | E470 | 5793918 | 08W | 663 |  |  | 0.12557 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.24 | FRRB - KANAKA 1101 - K4 PH 4.8 | REMOVAL 19 | 120850155 | 35245143 | E470 | 5793918 | 08W | 1367 |  |  | 0.2589 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.23 | FRRB - KANAKA 1101 - K4 PH 4.7 | REMOVAL 18 | 120850154 | 35245142 | E470 | 5793918 | 08W | 300 |  |  | 0.056818 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.33 | FRRB - KANAKA 1101 - K4 PH 4.17 | REMOVAL 43 | 120850488 | 35245152 | E470 | 5793918 | 08W | 2541 |  |  | 0.48125 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.27 | FRRB - KANAKA 1101 - K4 PH 4.11 | REMOVAL 32 | 120850158 | 35245146 | E470 | 5793918 | 08W | 728 |  |  | 0.13788 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.26 | FRRB - KANAKA 1101 - K4 PH 4.10 | REMOVAL 31 | 120850157 | 35245145 | E470 | 5793918 | 08W | 504 |  |  | 0.095455 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235703 K4.xlsx | 2021-06-17 21:33 | 2021-04-20 18:46 | Sheet1 |  | E.5034572 | E.5034572.01.15 | FRRB - KANAKA 1101 - K4 PH 4.19 | REMOVAL 9 | 120720967 | 35240542 | E470 | 5793918 | 08W | 4829 |  |  | 0.91458 |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35235704 K5.xlsx | 2021-06-23 23:04 | 2021-03-12 22:19 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Miles RG |  |  | Footage OH | Sheet1 | Sheet | FALSE
Suborder Table 35235704 K5.xlsx | 2021-06-23 23:04 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.41 | FRRB - KANAKA 1101 - K5 PH5.2 | Removal 10 | 120627599 | 35236999 | E470 | 573918 | 08W | 0.175 |  |  |  |  | 924 | Sheet1 | Sheet | FALSE
Suborder Table 35235704 K5.xlsx | 2021-06-23 23:04 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.40 | FRRB - KANAKA 1101 - K5 PH5.1 | Removal 11 | 120599076 | 35235704 | E470 | 573918 | 08W | 0.18902 |  |  |  |  | 998 | Sheet1 | Sheet | FALSE
Suborder Table 35235704 K5.xlsx | 2021-06-23 23:04 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.43 | FRRB - KANAKA 1101 - K5 PH5.4 | Removal 5 | 120627456 | 35236986 | E470 | 573918 | 08W | 1.9945 |  | 0 |  |  | 10531 | Sheet1 | Sheet | FALSE
Suborder Table 35235704 K5.xlsx | 2021-06-23 23:04 | 2021-03-12 22:19 | Sheet1 |  | E.5034572 | E.5034572.01.42 | FRRB - KANAKA 1101 - K5 PH5.3 | Removal 50 | 120627702 | 35237020 | E470 | 573918 | 08W | 0.5 |  | 0 |  |  | 2640 | Sheet1 | Sheet | FALSE
Suborder Table 35236982 K6.xlsx | 2021-06-11 16:18 | 2021-04-02 17:34 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Line Segment | Notification | PM Order | Order Type | Planning Order | MAT Code | Miles OH | Miles UG | Miles RG |  |  |  | Sheet1 | Sheet | FALSE
Suborder Table 35236982 K6.xlsx | 2021-06-11 16:18 | 2021-04-02 17:34 | Sheet1 |  | E.5034825 | E.5034825.01.44 | FRRB - KANAKA 1101 - K6 PH6 | FH-6T | 120627450 | 35236982 | E470 | 5795419 | 08W |  |  | 1.95 | 10296 |  |  | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | WBS Level 1 or Project Definition | WBS Level 2 | Name | Notification | PM Order | Order Type | Planning Order | MAT Code | Removal Length | Polygon | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.55 | NCF - RG - W1103 - Removal 90, 91, 92, 93, 94 | 120627597 | 35236995 | E470 | 5795419 | 08W | 21,024 | W4 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.45 | NCF - RG - BB1102 - FH-73T (Partial) | 120627452 | 35236983 | E470 | 5795419 | 08W | 1,600 | B5/B6 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.44 | NCF - RG - K1101 - Removal 33 | 120627450 | 35236982 | E470 | 5795419 | 08W | 10,163 | K6 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.58 | NCF - RG - K1101 - Removal 50 | 120627702 | 35237020 | E470 | 5795419 | 08W | 2,100 | K5 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.50 | NCF - RG - K1101 - Removal 1 | 120627501 | 35236989 | E470 | 5795419 | 08W | 2,493 | K2 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.56 | NCF - RG - BB1102 - Removal 134, 135 | 120627598 | 35236997 | E470 | 5795419 | 08W | 8,745 | B6 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.57 | NCF - RG - K1101 - Removal 3 | 120627599 | 35236999 | E470 | 5795419 | 08W | 5,300 | K3 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.51 | NCF - RG - W1103 - Removal 72 | 120627591 | 35236990 | E470 | 5795419 | 08W | 1,998 | W2 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.54 | NCF - RG - W1103 - Removal 108 | 120627595 | 35236993 | E470 | 5795419 | 08W | 2,100 | W4 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.53 | NCF - RG - K1101 - Removal 24 | 120627594 | 35236992 | E470 | 5795419 | 08W | 3,100 | K1 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.52 | NCF - RG - W1103 - Removal 118, 119, 120 | 120627593 | 35236991 | E470 | 5795419 | 08W | 8,805 | W4 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.47 | NCF - RG - K1101- Removal 28, 105,150 | 120627455 | 35236985 | E470 | 5795419 | 08W | 8,401 | K1 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.46 | NCF - RG - W1103- Removal 95, 96 | 120627454 | 35236984 | E470 | 5795419 | 08W | 9,799 | W5 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.49 | NCF - RG - K1101 - Removal 4 | 120627500 | 35236988 | E470 | 5795419 | 08W | 1,293 | K4 | [5 empty] | Sheet1 | Sheet | FALSE
Suborder Table Remote Grid.xlsx | 2021-03-12 22:21 | 2021-03-12 22:21 | Sheet1 |  | E.5034825 | E.5034825.01.48 | NCF - RG - K1101 - Removal 5 | 120627456 | 35236986 | E470 | 5795419 | 08W | 8,315 | K5 | [5 empty] | Sheet1 | Sheet | FALSE