## Sheet1
Order | KEEP | Status | Priority | Planned Units (SAP EST) | Residual Miles (SAP EST) | Primary Planned Year | Miles Primary Year | Miles Secondary Year | Completed Units (SAP ACT) | Actual Cost ($) | Order Status | Circuit | Circuit Name | Circuit Protection Zone | Pixel(s) | Total HFTD Zone Miles | Mean MAVF Core Risk Rank | Total MAVF Core Risk Value | Mean MAVF Core Risk Value | mavf_consequence_rank | Risk Reduction Per Project | CPZ Rank | HFTD Tier | Project Type | City | County | Division | Region | Planning Order | WBS Element | Notification | Order | Short Text | OH | UG | Remove | Remote Grid | Prelim Scope (Link) | AA (Link) | Targeted Units (ckt Ft) | Targeted Units (miles) | Unit Cost (Class 5) | Field Scoping (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | Scoped Units (ckt ft) | Scoped (miles) | Unit Cost (Class 5) | CMCS (Link) | BC (Link) | Removal (ckt ft) | UG (ckt ft) | OH (ckt ft) | PLANNED Units (SAP EST) | Planned Units (miles) | Expected Case (Class 2) | High Case (Class 2) | Unit Cost (per ft) | Cont. Release (Link) | Re-auth (Link) | Re-Auth (SK) | Completed Units (SAP ACT) | Actuals ($K) | Final Unit Cost
31246787 |  |  |  |  | 0 |  |  |  |  | 2500.01 | UNSE | 14101105 | ALHAMBRA 1105 | ALHAMBRA 110581514 | 65 | 2.9716 | 2593 | 0.08141 | 0.0012525 | 2556 | #DIV/0! | 2465 | Tier 2 | WDDB | MARTINEZ | Contra Costa | San Francisco | Bay Area | 5788780 |  | 111710769 | 31246787 | RECONDUCTOR 4 SPANS - 100 DEODARA WAY | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35074009 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 42031124 | ALTO 1124 | ALTO 1124432 | 72 | 7.8461 | 1714 | 1.2765 | 0.017729 | 1841 | 0 | 904 | Tier 3 | WDDB | MILL VALLEY | Marin | North Bay | Bay Area | 5530168 |  | 115826672 | 35074009 | ALTO 1124 WIRE DOWN ILIS 18-0109573 | 5000 | 0 | 0 | 0 |  | 2017-99508 | 5000 | 0.94697 | 500000 |  |  |  |  | 0 | 0
35135005 |  |  |  |  | 0 |  |  |  |  | 8238.33 | UNSE | 42031125 | ALTO 1125 | ALTO 1125902 | 83 | 12.0907 | 1654 | 1.7351 | 0.020905 | 1592 | #DIV/0! | 970 | Tier 3 | WDDB | MILL VALLEY | Marin | North Bay | Bay Area | 5530168 | P.11644 | 111104641 | 35135005 | MVWF ALTO 1125 MUIR WOOD DR,MUIR BEACH | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35192034 |  |  |  | 2.2 | 2.2 |  |  |  |  | 2114.63 | UNSE | 153661104 | APPLE HILL 1104 | APPLE HILL 110413512 | 345 | 28.4598 | 1284 | 14.2801 | 0.041392 | 1642 | 0.81453 | 99 | Tier 3 | ECOP | CAMINO | El Dorado | Sierra | Northern | 5792076 | E.5034384.01 | 119554053 | 35192034 | ECOP-APPLE HILL 1104-H01-LR13512 | 9552 | 2161 | 395 | 0 |  | 2020-62101 | 11616 | 2.2 | 3151833 | -
35058794 |  |  |  | 8.75 | 8.75 |  |  |  |  | 6043.18 | UNSE | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | 267 | 22.9542 | 1505 | 7.351 | 0.027532 | 1509 | 1.8774 | 226 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782527 | E.5015413.01 | 115036667 | 35058794 | CWSP-APPLE HILL 2102-7502-PH1.1 | 46200 | 0 | 0 | 0 | 2018-79712 | 2018-82583 | 46200 | 8.75 | 9389440 |  |  |  |  | 0 | 0
35058795 |  |  |  | 7.52 | 7.52 |  |  |  |  | 3038.44 | UNSE | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | 267 | 22.9542 | 1505 | 7.351 | 0.027532 | 1509 | 1.6135 | 226 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782528 | E.5015412.01 | 115036706 | 35058795 | CWSP-APPLE HILL 2102-7502-PH2.1 | 39705.6 | 0 | 0 | 0 | 2018-79720 | 2018-82593 | 39705.6 | 7.52 | 8093720 |  |  |  |  | 0 | 0
35058797 |  |  |  | 8.72 | 8.72 |  |  |  |  | 4168.61 | UNSE | 153662102 | APPLE HILL 2102 | APPLE HILL 21027502 | 267 | 22.9542 | 1505 | 7.351 | 0.027532 | 1509 | 1.871 | 226 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782529 | E.5015411.01 | 115036771 | 35058797 | CWSP-APPLE HILL 2102-7502-PH3.1 | 46041.6 | 0 | 0 | 0 | 2018-79722 | 2018-82604 | 46041.6 | 8.72 | 9342780 |  |  |  |  | 0 | 0
35048009 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 153662102 | APPLE HILL 2102 | APPLE HILL 210297982 | 104 | 9.6617 | 1847 | 1.3407 | 0.012892 | 1666 | 0 | 255 | Tier 3 | PRE | SOMERSET | El Dorado | Sierra | Northern | 5530173 | # | 114790791 | 35048009 | CWSP-APPLE HILL 2102-LR97982-PH1.1 | 53856 | 0 | 0 | 0 |  | 2018-56997 | 53856 | 10.2 | 10900000 |  |  |  |  | 0 | 0
35052731 |  |  |  | 1.47 | 1.47 |  |  |  |  | 138203.39 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.026827 | 354 | Tier 3 | PRE | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5782530 | E.5014542.01 | 114607365 | 35052731 | CWSP-BIG BASIN 1101-LR10296-PH 1.1 | 7779 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A |  |  |  | 0 | 0 |  | 2020-46872 | 2020-54946 | 0 | 0 | 7779 | 7779 | 1.4733 | 3391041 | 4994628 | 435.9225
35113950 |  |  |  | 3.57 | 3.57 |  |  |  |  | 127393.13 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.065151 | 354 | Tier 3 | PRE | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5786124 | E.5014542.02 | 117560045 | 35113950 | CWSP-BIG BASIN 1101-LR10296-PH 1.2 | 20148 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A |  |  |  | 0 | 0 |  | 2020-46874 | 2020-51798 | 0 | 0 | 20148 | 20148 | 3.8159 | 5124123 | 7080521 | 254.3242
35113951 |  |  |  | 2.58 | 2.58 |  |  |  |  | 126661.6 | UNSC | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.047084 | 354 | Tier 3 | PRE | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5786125 | E.5014542.03 | 117560047 | 35113951 | CWSP-BIG BASIN 1101-LR10296-PH 1.3 | 12799 | 0 | 0 | 0 |  | 2018-42216 | 12830.4 | 2.43 | 3837000 | N/A |  |  |  | 0 | 0 |  | 2020-46882 | 2020-52364 | 0 | 0 | 12799 | 12799 | 2.4241 | 4988614 | 6920313 | 389.7659
35052733 |  |  |  | 7.2 | 7.2 |  |  |  |  | 5747.16 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 110110296 | 181 | 14.4211 | 2456 | 0.3928 | 0.0021702 | 2657 | 0.1314 | 354 | Tier 3 | PRE | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114646897 | 35052733 | CWSP-BIG BASIN 1101-LR10296-PH2.1 | 38016 | 0 | 0 | 0 |  | 2018-45493 | 38016 | 7.2 | 13027000 |  |  |  |  | 0 | 0
35052732 |  |  |  | 7.4 | 7.4 |  |  |  |  | 13904.7 | UNSE | 82841101 | BIG BASIN 1101 | BIG BASIN 11015028 | 59 | 5.0266 | 2968 | 0.0010925 | 1.8516e-05 | 3056 | 0.0010776 | 1012 | Tier 3 | PRE | BOULDER CREEK | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114623764 | 35052732 | CWSP-BIG BASIN 1101-LR5028-PH1.1 | 39072 | 0 | 0 | 0 |  | 2018-46250 | 39072 | 7.4 | 9725100 |  |  |  |  | 0 | 0
35049538 |  |  |  |  | 0 |  |  |  |  | 8388.56 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 110212758 | 70 | 5.982 | 2358 | 0.20629 | 0.002947 | 2611 | 0 | 537 | Tier 3 | PRE | BOULDER CREEK | Santa Clara | Central Coast | Central Coast | 5792090 |  | 114832089 | 35049538 | CWSP-BIG BASIN 1102-LR12758-PH1.1 | 44088 | 0 | 0 | 0 | 2018-62221 | 2018-66371 | 44088 | 8.35 | 9003540 |  |  |  |  | 0 | 0
35049537 |  |  |  |  | 0 |  |  |  |  | 5617.41 | UNSE | 82841102 | BIG BASIN 1102 | BIG BASIN 11029741 | 10 | 0.64417 | 2967 | 0.00018794 | 1.8794e-05 | 3057 | 0 | 419 | Tier 3 | PRE | BOULDER CREEK | Santa Clara | Central Coast | Central Coast | 5530159 |  | 114832083 | 35049537 | CWSP-BIG BASIN 1102-LR9741-PH1.1 | 29568 | 0 | 0 | 0 | 2018-62943 | 2018-68017 | 29568 | 5.6 | 5948800 |  |  |  |  | 0 | 0
35060387 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 43081101 | BIG RIVER 1101 | BIG RIVER 11013002 | 76 | 7.2444 | 2564 | 0.11126 | 0.001464 | 2610 | #DIV/0! | 1540 | Tier 2 | WDDB | MENDOCINO | Mendocino | Humboldt | Northern | 5513264 |  | 112404866 | 35060387 | WDDB BIG RIVER 1101 FUSE 5187 RECONDUCTO | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35047318 |  |  |  | 10.6 | 10.6 |  |  |  |  | 5576.75 | UNSE | 83050402 | BIG TREES 0402 | BIG TREES 0402CB | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 943 | Tier 3 | PRE | FELTON | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114761016 | 35047318 | CWSP - CAMPEVERS2105 - BT402CB - 4KV PH6 | 55968 | 0 | 0 | 0 |  | 2018-83741 | 55968 | 10.6 | 11830900 |  |  |  |  | 0 | 0
35113945 |  |  |  | 44.07 | 44.07 |  |  |  |  | 2617.71 | UNSE | 152481102 | BRUNSWICK 1102 | BRUNSWICK 11021010 | 479 | 44.3718 | 1649 | 10.1396 | 0.021168 | 1708 | 6.7473 | 6 | Tier 3 | RISK | GRASS VALLEY | Nevada | Sierra | Northern | 5786218 | E.5024241.01 | 117557031 | 35113945 | CWSP-BRUNSWICK 1102-LR1010-PH1.1 | 232689.6 | 0 | 0 | 0 |  | 2019-44754 | 232689.6 | 44.07 | 44070000 |  |  |  |  | 0 | 0
35129767 |  |  |  | 2.59 | 2.59 |  |  |  |  | 141797.37 | ESTS | 152481103 | BRUNSWICK 1103 | BRUNSWICK 11032200 | 64 | 5.5723 | 2521 | 0.10808 | 0.0016888 | 2484 | 0.033658 | 117 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5746480 | E.5015531.02 | 114810960 | 35129767 | CWSP-BRUNSWICK 1103-LR2200-PH1 | 13700 | 0 | 0 | 0 |  | 2018-65949 | 7392 | 1.4 | 1477500 |  | 0 | 0 | 13700 | 13700 | 2.5947 | 4981818.1818
35142827 |  |  |  | 0.91 | 0.91 |  |  |  |  | 429667.03 | PEND | 152481103 | BRUNSWICK 1103 | BRUNSWICK 11032200 | 64 | 5.5723 | 2521 | 0.10808 | 0.0016888 | 2484 | 0.011826 | 117 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5788623 | E.5015531.04 | 118218951 | 35142827 | CWSP-BRUNSWICK 1103-LR2200-PH3 | 4547 | 0 | 0 | 0 |  | 2018-65949 | 7392 | 1.4 | 1477500 |  | 0 | 0 | 4547 | 4547 | 0.86117 | 1653454.5455 | 2020-59377 | 2020-57891 | 0 | 0 | 4547 | 4547 | 0.86117 | 1802501 | 2485715 | 396.4154 |  | 2020-54386
35115152 |  |  |  | 1.57 | 1.57 |  |  |  |  | 498323.16 | UNSC | 152481103 | BRUNSWICK 1103 | BRUNSWICK 110350070 | 201 | 17.7473 | 2144 | 1.2469 | 0.0062036 | 2255 | 0.073907 | 7 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5785722 | E.5015568.03 | 117495855 | 35115152 | CWSP-BRUNSWICK 1103-LR50070-PH 2.3 | 8271 | 0 | 0 | 0 |  | 2018-85027 | 11880 | 2.25 | 2383450 | 2019-76348 |  |  |  | 0 | 0 | 0 | 2020-55781 | 2020-58697 | 0 | 0 | 8271 | 8271 | 1.5665 | 2679486 | 3591121 | 323.9616
35060992 |  |  |  | 0.48 | 0.48 |  |  |  |  | 34544.18 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.024118 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783064 | E.5015548.01 | 115101918 | 35060992 | CWSP-BRUNSWICK 1105-LR2140-PH 1.01 | 2534 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 2534 | 2534 | 0.47992 | 921454.5455
35155680 |  |  |  | 1.324 | 1.324 |  |  |  |  | 1209.45 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.066526 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789366 | E.5030694.01 | 118499588 | 35155680 | CWSP-BRUNSWICK 1105-LR2140-PH 1.02 | 6990 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 6990 | 6990 | 1.3239 | 2541818.1818
35155681 |  |  |  | 0.253 | 0.253 |  |  |  |  | 733.75 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.012712 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789378 | E.5030695.01 | 118501195 | 35155681 | CWSP-BRUNSWICK 1105-LR2140-PH 1.03 | 1335 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 1335 | 1335 | 0.25284 | 485454.5455
35155682 |  |  |  | 0.366 | 0.366 |  |  |  |  | 489.15 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.01839 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789379 | E.5030696.01 | 118501438 | 35155682 | CWSP-BRUNSWICK 1105-LR2140-PH 1.04 | 1930 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 1930 | 1930 | 0.36553 | 701818.1818
35155683 |  |  |  | 1.241 | 1.241 |  |  |  |  | 2174.37 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.062355 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789380 | E.5030697.01 | 118501439 | 35155683 | CWSP-BRUNSWICK 1105-LR2140-PH 1.05 | 6550 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 6550 | 6550 | 1.2405 | 2381818.1818
35155684 |  |  |  | 0.623 | 0.623 |  |  |  |  | 489.15 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.031303 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789381 | E.5030698.01 | 118501730 | 35155684 | CWSP-BRUNSWICK 1105-LR2140-PH 1.06 | 3288 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 3288 | 3288 | 0.62273 | 1195636.3636
35155685 |  |  |  | 0.716 | 0.716 |  |  |  |  | 489.15 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.035976 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789382 | E.5030699.01 | 118501731 | 35155685 | CWSP-BRUNSWICK 1105-LR2140-PH 1.07 | 3780 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 3780 | 3780 | 0.71591 | 1374545.4545
35155686 |  |  |  | 0.614 | 0.614 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.030851 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789383 | E.5030700.01 | 118501733 | 35155686 | CWSP-BRUNSWICK 1105-LR2140-PH 1.08 | 3240 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 3240 | 3240 | 0.61364 | 1178181.8182
35155687 |  |  |  | 1.683 | 1.683 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.084564 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789384 | E.5030701.01 | 118501735 | 35155687 | CWSP-BRUNSWICK 1105-LR2140-PH 1.09 | 8886 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 8886 | 8886 | 1.683 | 3231272.7273
35155688 |  |  |  | 0.561 | 0.561 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.028188 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789385 | E.5030702.01 | 118501736 | 35155688 | CWSP-BRUNSWICK 1105-LR2140-PH 1.10 | 2961 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 2961 | 2961 | 0.5608 | 1076727.2727
35155689 |  |  |  | 0.928 | 0.928 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.046628 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789386 | E.5030703.01 | 118501737 | 35155689 | CWSP-BRUNSWICK 1105-LR2140-PH 1.11 | 4900 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 4900 | 4900 | 0.92803 | 1781818.1818
35155690 |  |  |  | 0.963 | 0.963 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.048387 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789387 | E.5030704.01 | 118501738 | 35155690 | CWSP-BRUNSWICK 1105-LR2140-PH 1.12 | 5082 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 5082 | 5082 | 0.9625 | 1848000
35155691 |  |  |  | 0.57 | 0.57 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.02864 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789388 | E.5030705.01 | 118501739 | 35155691 | CWSP-BRUNSWICK 1105-LR2140-PH 1.13 | 3010 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 3010 | 3010 | 0.57008 | 1094545.4545
35155692 |  |  |  | 0.998 | 0.998 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.050146 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789389 | E.5030706.01 | 118501873 | 35155692 | CWSP-BRUNSWICK 1105-LR2140-PH 1.14 | 5268 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 5268 | 5268 | 0.99773 | 1915636.3636
35155693 |  |  |  | 1.155 | 1.155 |  |  |  |  | 311.2 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.058034 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789390 | E.5030707.01 | 118501874 | 35155693 | CWSP-BRUNSWICK 1105-LR2140-PH 1.15 | 6100 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 6100 | 6100 | 1.1553 | 2218181.8182
35155694 |  |  |  | 1.117 | 1.117 |  |  |  |  | 244.59 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.056125 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789391 | E.5030708.01 | 118501875 | 35155694 | CWSP-BRUNSWICK 1105-LR2140-PH 1.16 | 5900 | 0 | 0 | 0 |  | 2018-84805 | 4435.2 | 0.84 | 897506 | 2020-21904 | 0 | 0 | 5900 | 5900 | 1.1174 | 2145454.5455
35060991 |  |  |  | 0.467 | 0.467 |  |  |  |  | 15685.31 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.023465 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783063 | E.5015547.01 | 115101979 | 35060991 | CWSP-BRUNSWICK 1105-LR2140-PH2.01 | 2465 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2465 | 2465 | 0.46686 | 896363.6364
35155695 |  |  |  | 1.035 | 1.035 |  |  |  |  | 459.15 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.052005 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789392 | E.5030709.01 | 118502200 | 35155695 | CWSP-BRUNSWICK 1105-LR2140-PH2.02 | 5465 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 5465 | 5465 | 1.035 | 1987272.7273
35155696 |  |  |  | 0.462 | 0.462 |  |  |  |  | 725.36 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.023214 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789393 | E.5030710.01 | 118502205 | 35155696 | CWSP-BRUNSWICK 1105-LR2140-PH2.03 | 2440 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2440 | 2440 | 0.46212 | 887272.7273
35155697 |  |  |  | 0.394 | 0.394 |  |  |  |  | 247.12 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.019797 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789394 | E.5030711.01 | 118502207 | 35155697 | CWSP-BRUNSWICK 1105-LR2140-PH2.04 | 2080 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2080 | 2080 | 0.39394 | 756363.6364
35155698 |  |  |  | 1.199 | 1.199 |  |  |  |  | 247.12 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.060245 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789395 | E.5030712.01 | 118502208 | 35155698 | CWSP-BRUNSWICK 1105-LR2140-PH2.05 | 6332 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 6332 | 6332 | 1.1992 | 2302545.4545
35155699 |  |  |  | 0.457 | 0.457 |  |  |  |  | 247.12 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.022962 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789396 | E.5030713.01 | 118502271 | 35155699 | CWSP-BRUNSWICK 1105-LR2140-PH2.06 | 2415 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2415 | 2415 | 0.45739 | 878181.8182
35155740 |  |  |  | 0.689 | 0.689 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.03462 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789397 | E.5030714.01 | 118502272 | 35155740 | CWSP-BRUNSWICK 1105-LR2140-PH2.07 | 3636 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 3636 | 3636 | 0.68864 | 1322181.8182
35155741 |  |  |  | 0.169 | 0.169 |  |  |  |  | 247.12 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.0084916 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789398 | E.5030715.01 | 118502273 | 35155741 | CWSP-BRUNSWICK 1105-LR2140-PH2.08 | 890 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 890 | 890 | 0.16856 | 323636.3636
35155742 |  |  |  | 1.155 | 1.155 |  |  |  |  | 725.36 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.058034 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789399 | E.5030716.01 | 118502274 | 35155742 | CWSP-BRUNSWICK 1105-LR2140-PH2.09 | 6100 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 6100 | 6100 | 1.1553 | 2218181.8182
35155743 |  |  |  | 0.699 | 0.699 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.035122 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789400 | E.5030717.01 | 118502275 | 35155743 | CWSP-BRUNSWICK 1105-LR2140-PH2.10 | 3692 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 3692 | 3692 | 0.69924 | 1342545.4545
35155744 |  |  |  | 0.506 | 0.506 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.025425 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789401 | E.5030718.01 | 118502276 | 35155744 | CWSP-BRUNSWICK 1105-LR2140-PH2.11 | 2671 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2671 | 2671 | 0.50587 | 971272.7273
35155746 |  |  |  | 1.119 | 1.119 |  |  |  |  | 494.23 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.056225 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789402 | E.5030719.01 | 118502277 | 35155746 | CWSP-BRUNSWICK 1105-LR2140-PH2.12 | 5910 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 5910 | 5910 | 1.1193 | 2149090.9091
35155747 |  |  |  | 0.762 | 0.762 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.038288 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789403 | E.5030720.01 | 118502279 | 35155747 | CWSP-BRUNSWICK 1105-LR2140-PH2.13 | 4025 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 4025 | 4025 | 0.76231 | 1463636.3636
35155748 |  |  |  | 0.519 | 0.519 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.026078 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789404 | E.5030721.01 | 118502451 | 35155748 | CWSP-BRUNSWICK 1105-LR2140-PH2.14 | 2740 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2740 | 2740 | 0.51894 | 996363.6364
35155749 |  |  |  | 0.504 | 0.504 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.025324 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789405 | E.5030722.01 | 118502453 | 35155749 | CWSP-BRUNSWICK 1105-LR2140-PH2.15 | 2662 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2662 | 2662 | 0.50417 | 968000
35155750 |  |  |  | 1.68 | 1.68 |  |  |  |  | 494.23 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.084413 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789406 | E.5030723.01 | 118502455 | 35155750 | CWSP-BRUNSWICK 1105-LR2140-PH2.16 | 8872 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 8872 | 8872 | 1.6803 | 3226181.8182
35155751 |  |  |  | 0.498 | 0.498 |  |  |  |  | 725.36 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.025023 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789407 | E.5030724.01 | 118502456 | 35155751 | CWSP-BRUNSWICK 1105-LR2140-PH2.17 | 2627 | 0 | 0 | 0 |  | 2018-84808 | 3748.8 | 0.71 | 756111 | 2020-21909 | 0 | 0 | 2627 | 2627 | 0.49754 | 955272.7273
35060990 |  |  |  | 0.864 | 0.864 |  |  |  |  | 19227.08 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.043413 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783062 | E.5015546.01 | 115102251 | 35060990 | CWSP-BRUNSWICK 1105-LR2140-PH3.01 | 4562 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 4562 | 4562 | 0.86402 | 1658909.0909
35155752 |  |  |  | 0.516 | 0.516 |  |  |  |  | 214.56 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.025927 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789408 | E.5030725.01 | 118502580 | 35155752 | CWSP-BRUNSWICK 1105-LR2140-PH3.02 | 2727 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 2727 | 2727 | 0.51648 | 991636.3636
35155753 |  |  |  | 1.063 | 1.063 |  |  |  |  | 770.34 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.053412 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789409 | E.5030726.01 | 118502582 | 35155753 | CWSP-BRUNSWICK 1105-LR2140-PH3.03 | 5611 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 5611 | 5611 | 1.0627 | 2040363.6364
35155754 |  |  |  | 1.255 | 1.255 |  |  |  |  | 525.75 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.063059 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789410 | E.5030727.01 | 118502583 | 35155754 | CWSP-BRUNSWICK 1105-LR2140-PH3.04 | 6626 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 6626 | 6626 | 1.2549 | 2409454.5455
35155755 |  |  |  | 0.271 | 0.271 |  |  |  |  | 214.56 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.013617 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789411 | E.5030728.01 | 118502584 | 35155755 | CWSP-BRUNSWICK 1105-LR2140-PH3.05 | 1431 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 1431 | 1431 | 0.27102 | 520363.6364
35155756 |  |  |  | 1.745 | 1.745 |  |  |  |  | 1809.66 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.087679 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789412 | E.5030730.01 | 118502585 | 35155756 | CWSP-BRUNSWICK 1105-LR2140-PH3.06 | 9214 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 9214 | 9214 | 1.7451 | 3350545.4545
35155757 |  |  |  | 0.552 | 0.552 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.027736 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789413 | E.5030731.01 | 118502586 | 35155757 | CWSP-BRUNSWICK 1105-LR2140-PH3.07 | 2913 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 2913 | 2913 | 0.5517 | 1059272.7273
35155758 |  |  |  | 0.665 | 0.665 |  |  |  |  | 525.75 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.033414 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789414 | E.5030732.01 | 118502587 | 35155758 | CWSP-BRUNSWICK 1105-LR2140-PH3.08 | 3510 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 3510 | 3510 | 0.66477 | 1276363.6364
35155759 |  |  |  | 0.663 | 0.663 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.033313 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789415 | E.5030733.01 | 118502588 | 35155759 | CWSP-BRUNSWICK 1105-LR2140-PH3.09 | 3500 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 3500 | 3500 | 0.66288 | 1272727.2727
35155840 |  |  |  | 0.49 | 0.49 |  |  |  |  | 0 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.024621 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789416 | E.5030734.01 | 118502589 | 35155840 | CWSP-BRUNSWICK 1105-LR2140-PH3.10 | 2596 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 2596 | 2596 | 0.49167 | 944000
35155841 |  |  |  | 0.85 | 0.85 |  |  |  |  | 770.34 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.042709 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789417 | E.5030735.01 | 118502690 | 35155841 | CWSP-BRUNSWICK 1105-LR2140-PH3.11 | 4491 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 4491 | 4491 | 0.85057 | 1633090.9091
35155842 |  |  |  | 0.15 | 0.15 |  |  |  |  | 475.72 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052140 | 373 | 34.5738 | 2096 | 2.5928 | 0.0069513 | 2015 | 0.0075369 | 22 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789418 | E.5030736.01 | 118502691 | 35155842 | CWSP-BRUNSWICK 1105-LR2140-PH3.12 | 808 | 0 | 0 | 0 |  | 2018-84820 | 4065.6 | 0.77 | 818566 | 2020-21919 | 0 | 0 | 808 | 808 | 0.15303 | 293818.1818
35060994 |  |  |  | 1.07 | 1.07 |  |  |  |  | 121819.79 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.12525 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783060 | E.5015549.01 | 115101557 | 35060994 | CWSP-BRUNSWICK 1105-LR 2210-PH1.1 | 2755 | 2890 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 2890 | 2755 | 5645 | 1.0691 | 3297360
35158717 |  |  |  | 1.43 | 1.43 |  |  |  |  | 93528.89 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.1345 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789698 | E.5015549.02 | 118531819 | 35158717 | CWSP-BRUNSWICK 1105-LR 2210-PH1.2 | 7561 | 0 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 0 | 7561 | 7561 | 1.432 | 2749454.5455
35160091 |  |  |  | 0.68 | 0.68 |  |  |  |  | 88122.68 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.094507 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789699 | E.5015549.03 | 118532310 | 35160091 | CWSP-BRUNSWICK 1105-LR 2210-PH1.3 | 0 | 3600 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 3600 | 0 | 3600 | 0.68182 | 2863636.3636
35160093 |  |  |  | 1.07 | 1.07 |  |  |  |  | 43975.29 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.10064 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789700 | E.5015549.04 | 118532312 | 35160093 | CWSP-BRUNSWICK 1105-LR 2210-PH1.4 | 5667 | 0 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 0 | 5667 | 5667 | 1.0733 | 2060727.2727
35160094 |  |  |  | 1.2 | 1.2 |  |  |  |  | 44182.89 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.11287 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789701 | E.5015549.05 | 118532313 | 35160094 | CWSP-BRUNSWICK 1105-LR 2210-PH1.5 | 6312 | 0 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 0 | 6312 | 6312 | 1.1955 | 2295272.7273
35160095 |  |  |  | 1.83 | 1.83 |  |  |  |  | 59185.12 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.19169 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789702 | E.5015549.06 | 118532315 | 35160095 | CWSP-BRUNSWICK 1105-LR 2210-PH1.6 | 7364 | 2300 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 2300 | 7364 | 9664 | 1.8303 | 4494000
35160096 |  |  |  | 0.99 | 0.99 |  |  |  |  | 66928.01 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.13759 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789703 | E.5015549.07 | 118532317 | 35160096 | CWSP-BRUNSWICK 1105-LR 2210-PH1.7 | 0 | 5204 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 5204 | 0 | 5204 | 0.98561 | 4139545.4545
35160097 |  |  |  | 1.99 | 1.99 |  |  |  |  | 55171.77 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.18717 | 21 | Tier 2 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789704 | E.5015549.08 | 118532318 | 35160097 | CWSP-BRUNSWICK 1105-LR 2210-PH1.8 | 10504 | 0 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 0 | 10504 | 10504 | 1.9894 | 3819636.3636
35160098 |  |  |  | 1.04 | 1.04 |  |  |  |  | 56492.12 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.14454 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789705 | E.5015549.09 | 118532430 | 35160098 | CWSP-BRUNSWICK 1105-LR 2210-PH1.9 | 0 | 5500 | 0 | 0 |  | 2018-84687 | 6758.4 | 1.28 | 1353622.22 | 2020-08007 | 0 | 5500 | 0 | 5500 | 1.0417 | 4375000
35060993 |  |  |  | 1.05 | 1.05 |  |  |  |  | 12393.3 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.13803 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783061 | E.5015550.01 | 115101776 | 35060993 | CWSP-BRUNSWICK 1105-LR 2210-PH2.1 | 925 | 4600 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 4600 | 925 | 5525 | 1.0464 | 3982800
35160341 |  |  |  | 1.55 | 1.55 |  |  |  |  | 4154.91 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.1607 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789706 | E.5015550.02 | 118532433 | 35160341 | CWSP-BRUNSWICK 1105-LR 2210-PH2.2 | 6494 | 1770 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 1770 | 6494 | 8264 | 1.5652 | 3768600
35160342 |  |  |  | 1.48 | 1.48 |  |  |  |  | 5512.76 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.18891 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789707 | E.5015550.03 | 118532435 | 35160342 | CWSP-BRUNSWICK 1105-LR 2210-PH2.3 | 1848 | 5472 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 5472 | 1848 | 7320 | 1.3864 | 5023200
35160343 |  |  |  | 2.63 | 2.63 |  |  |  |  | 902.05 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.24737 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789708 | E.5015550.04 | 118532436 | 35160343 | CWSP-BRUNSWICK 1105-LR 2210-PH2.4 | 14092 | 0 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 0 | 14092 | 14092 | 2.6689 | 5124363.6364
35160344 |  |  |  | 2.69 | 2.69 |  |  |  |  | 1265.47 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.25302 | 21 | Tier 2 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789709 | E.5015550.05 | 118532438 | 35160344 | CWSP-BRUNSWICK 1105-LR 2210-PH2.5 | 14202 | 0 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 0 | 14202 | 14202 | 2.6898 | 5164363.6364
35160345 |  |  |  | 3.32 | 3.32 |  |  |  |  | 3267.43 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.31227 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789710 | E.5015550.06 | 118532570 | 35160345 | CWSP-BRUNSWICK 1105-LR 2210-PH2.6 | 18633 | 0 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 0 | 18633 | 18633 | 3.529 | 6775636.3636
35160346 |  |  |  | 0.56 | 0.56 |  |  |  |  | 964.12 | ESTS | 152481105 | BRUNSWICK 1105 | BRUNSWICK 11052210 | 280 | 22.9574 | 1902 | 3.2229 | 0.01151 | 2032 | 0.077829 | 21 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5789711 | E.5015550.07 | 118532571 | 35160346 | CWSP-BRUNSWICK 1105-LR 2210-PH2.7 | 0 | 2953 | 0 | 0 |  | 2018-84704 | 8923.2 | 1.69 | 1787214.29 | 2020-08025 | 0 | 2953 | 0 | 2953 | 0.55928 | 2348977.2727
35047601 |  |  |  | 8.78 | 8.78 |  |  |  |  | 19712.7 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 110532536 | 144 | 10.8995 | 2734 | 0.072262 | 0.00050182 | 2690 | 0.039001 | 9 | Tier 3 | ECOP | NEVADA CITY | Nevada | Sierra | Northern | 5530173 |  | 114780214 | 35047601 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH2 | 46200 | 0 | 0 | 0 | 2018-57214 | 2018-63030 | 46358.4 | 8.78 | 9389300 | 2020-07-23 | 0 | 0 | 46358.4 | 46358.4 | 8.78 | 16857600
35048678 |  |  |  | 7 | 7 |  |  |  |  | 15606.46 | UNSE | 152481105 | BRUNSWICK 1105 | BRUNSWICK 110532536 | 144 | 10.8995 | 2734 | 0.072262 | 0.00050182 | 2690 | 0.031094 | 9 | Tier 3 | ECOP | NEVADA CITY | Nevada | Sierra | Northern | 5530173 |  | 114819747 | 35048678 | ECOP-BRUNSWICK 1105-H01-LR32536 ZONE PH3 | 43824 | 0 | 0 | 0 | 2018-58721 | 2018-80474 | 43824 | 8.3 | 9664900 | 2020-07-23 | 0 | 6864 | 36960 | 43824 | 8.3 | 15936000
35060995 |  |  |  | 9.7 | 9.7 |  |  |  |  | 1662.55 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062104 | 123 | 9.8261 | 2157 | 0.72777 | 0.0059169 | 2456 | 0.48135 | 222 | Tier 3 | PRE | NEVADA CITY | Nevada | Sierra | Northern | 5783059 | E.5015551.01 | 115101457 | 35060995 | CWSP-BRUNSWICK 1106-LR2104-PH1.1 | 51216 | 0 | 0 | 0 |  | 2018-84603 | 51216 | 9.7 | 10292300 |  |  |  |  | 0 | 0
35192288 |  |  |  | 2.26 | 2.26 |  |  |  |  | 1529.29 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062416 | 360 | 28.9391 | 1638 | 7.7569 | 0.021547 | 1760 | 0.40587 | 1049 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5792088 | E.5034397.01 | 119555953 | 35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 | 11932.8 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35192285 |  |  |  | 10 | 10 |  |  |  |  | 1529.29 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062796 | 253 | 19.8767 | 2685 | 0.17585 | 0.00069507 | 2691 | 0.059276 | 180 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5792085 | E.5034393.01 | 119555791 | 35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 - PH 1 | 52800 | 0 | 0 | 0 | [5 empty] | -
35192286 |  |  |  | 9.87 | 9.87 |  |  |  |  | 1529.29 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11062796 | 253 | 19.8767 | 2685 | 0.17585 | 0.00069507 | 2691 | 0.058506 | 180 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5792086 | E.5034394.01 | 119555811 | 35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 - PH 2 | 52113.6 | 0 | 0 | 0 | [5 empty] | -
35191317 |  |  |  | 1.36 | 1.36 |  |  |  |  | 1529.29 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 11064639 | 44 | 3.2493 | 2891 | 0.0029871 | 6.7888e-05 | 2885 | 0.00083765 | 833 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5541304 | E.5034353.01 | 119518394 | 35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 | 7180.8 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35192289 |  |  |  | 1.81 | 1.81 |  |  |  |  | 0 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651484 | 195 | 15.3771 | 1154 | 10.1812 | 0.052211 | 1333 | 0.80293 | 1503 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5792089 | E.5034398.01 | 119555969 | 35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 | 9556.8 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35050945 |  |  |  | 13.55 | 13.55 |  |  |  |  | 8324.37 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 1.5546 | 35 | Tier 3 | PRE | GRASS VALLEY | Nevada | Sierra | Northern | 5530173 |  | 114848718 | 35050945 | CWSP-BRUNSWICK 1106-LR2143-PH1.1 | 71544 | 0 | 0 | 0 | 2018-62377 | 2018-67227 | 71544 | 13.55 | 14381400
35050947 |  |  |  | 9.54 | 9.54 |  |  |  |  | 11345.91 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 1.0945 | 35 | Tier 3 | PRE | GRASS VALLEY | Nevada | Sierra | Northern | 5530173 |  | 114848737 | 35050947 | CWSP-BRUNSWICK 1106-LR2794-PH1.1 | 50160 | 0 | 0 | 0 | 2018-63464 | 2018-67239 | 50160 | 9.5 | 10259800
35050949 |  |  |  | 9.38 | 9.38 |  |  |  |  | 10092.63 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 1.0762 | 35 | Tier 3 | PRE | GRASS VALLEY | Nevada | Sierra | Northern | 5530173 |  | 114848761 | 35050949 | CWSP-BRUNSWICK 1106-LR2794-PH2.1 | 49526.4 | 0 | 0 | 0 | 2018-69716 | 2018-82514 | 49526.4 | 9.38 | 10081780
35050950 |  |  |  | 8.84 | 8.84 |  |  |  |  | 5245.58 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 1.0142 | 35 | Tier 3 | PRE | GRASS VALLEY | Nevada | Sierra | Northern | 5530173 |  | 114848764 | 35050950 | CWSP-BRUNSWICK 1106-LR2794-PH3.1 | 46675.2 | 0 | 0 | 0 | 2018-70261 | 2018-82519 | 46675.2 | 8.84 | 9617520
35047420 |  |  |  | 8.77 | 8.77 |  |  |  |  | 10117.41 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 1.0062 | 35 | Tier 3 | PRE | GRASS VALLEY | Nevada | Sierra | Northern | 5530173 |  | 114742521 | 35047420 | CWSP-BRUNSWICK 1106-LR51486-PH1.1 | 46305.6 | 0 | 0 | 0 | 2018-60393 | 2018-67208 | 46305.6 | 8.77 | 9289200
35173754 |  |  |  | 6.3 | 6.3 |  |  |  |  | 24276.37 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 110651486 | 656 | 56.6847 | 1788 | 9.7068 | 0.014797 | 1860 | 0.79738 | 35 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5790001 | E.5030956.01 | 118911473 | 35173754 | ECOP - BRUNSWICK 1106 - H08 - LR51486 | 48669 | 13408 | 0 | 0 | 2020-53961 | 2020-54186 | 49632 | 9.4 | 12334900 | 2020-09-20 | 0 | 11368 | 38441 | 49809 | 9.4335 | 18112363.6364
35192287 |  |  |  | 2.28 | 2.28 |  |  |  |  | 1529.29 | UNSE | 152481106 | BRUNSWICK 1106 | BRUNSWICK 1106CB | 88 | 8.7425 | 1876 | 1.0703 | 0.012162 | 2253 | 0.18701 | 292 | Tier 3 | ECOP | GRASS VALLEY | Nevada | Sierra | Northern | 5792087 | E.5034395.01 | 119555883 | 35192287 | ECOP - BRUNSWICK 1106 - H02 - CB | 12038.4 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35052729 |  |  |  |  | 0 |  |  |  |  | 13476.34 | UNSE | 183582101 | BURNS 2101 | BURNS 2101CB | 19 | 1.7044 | 2946 | 0.00051453 | 2.7081e-05 | 3078 | 0 | 308 | Tier 3 | PRE | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114573040 | 35052729 | CWSP-BURNS 2101-OCB-PH1.1 | 38332.8 | 2587.2 | 0 | 0 |  | 2018-42418 | 40920 | 7.75 | 12514500 |  |  |  |  | 0 | 0
35052730 |  |  |  | 3.7 | 3.7 |  |  |  |  | 6231.19 | UNSE | 183582101 | BURNS 2101 | BURNS 2101CB | 19 | 1.7044 | 2946 | 0.00051453 | 2.7081e-05 | 3078 | 0.00074839 | 308 | Tier 3 | PRE | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114661267 | 35052730 | CWSP-BURNS 2101-OCB-PH2.1 | 19536 | 0 | 0 | 0 |  | 2018-48078 | 19536 | 3.7 | 3710394 |  |  |  |  | 0 | 0
35077348 |  |  |  | 3.323 | 3.323 |  |  |  |  | 821.37 | UNSE | 183101103 | CABRILLO 1103 | CABRILLO 1103Y46 | 277 | 31.4816 | 998 | 18.7037 | 0.067522 | 626 | 1.3227 | 1637 | Tier 2 | WDDB | LOMPOC | Santa Barbara | Los Padres | Central Coast | 5784376 | E.5019979.01 | 116579004 | 35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW | 17547 | 0 | 0 | 0 |  | 2019-10594 | 17547 | 3.3233 | 2642050 |  |  |  |  | 0 | 0
35192283 |  |  |  | 1.98 | 1.98 |  |  |  |  | 1529.29 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 11011087 | 22 | 1.9622 | 1082 | 1.2681 | 0.05764 | 1170 | 0.85733 | 523 | Tier 3 | ECOP | CALISTOGA | Napa | North Bay | Bay Area | 5792090 | E.5034399.01 | 119556064 | 35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 | 10454.4 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35174472 |  |  |  | 1.89 | 1.89 |  |  |  |  | 14323.58 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | 107 | 7.7836 | 1005 | 7.1532 | 0.066852 | 1252 | 1.4654 | 34 | Tier 3 | ECOP | CALISTOGA | Napa | North Bay | Bay Area | 5790006 | E.5031114.01 | 118912499 | 35174472 | ECOP - CALISTOGA 1101 - H02 - LR43924 | 5560 | 6600 | 0 | 0 | 2020-48878 | 2020-48885 | 12144 | 2.3 | 3600500 | - | 0 | 6600 | 5544 | 12144 | 2.3 | 4416000
35174473 |  |  |  | 1.82 | 1.82 |  |  |  |  | 12564.98 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 110143924 | 107 | 7.7836 | 1005 | 7.1532 | 0.066852 | 1252 | 1.1206 | 34 | Tier 3 | ECOP | CALISTOGA | Napa | North Bay | Bay Area | 5790007 | E.5031276.01 | 118912760 | 35174473 | ECOP - CALISTOGA 1101 - H03 - LR43924 | 20340 | 0 | 0 | 0 | 2020-51344 | 2020-51348 | 20328 | 3.85 | 5430755 | - | 0 | 0 | 20328 | 20328 | 3.85 | 7392000
35174474 |  |  |  | 4.4 | 4.4 |  |  |  |  | 17427.81 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 350 | 34.6626 | 833 | 31.0945 | 0.088841 | 1030 | 2.6665 | 24 | Tier 3 | ECOP | CALISTOGA | Napa | North Bay | Bay Area | 5790104 | E.5033913.01 | 118912987 | 35174474 | ECOP - CALISTOGA 1101 - H01 - LR736 | 20952 | 0 | 360 | 0 | 2020-53201 | 2020-53202 | 20961.6 | 3.97 | 5652193 | - | 0 | 0 | 23443.2 | 23443.2 | 4.44 | 8524800
35174477 |  |  |  | 9.53 | 9.53 |  |  |  |  | 5592.11 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 350 | 34.6626 | 833 | 31.0945 | 0.088841 | 1030 | 5.8891 | 24 | Tier 3 | ECOP | CALISTOGA | Sonoma | North Bay | Bay Area | 5790110 | E.5033916.01 | 118913023 | 35174477 | ECOP - CALISTOGA 1101 - H01 - LR736 - Ph3 | 44692 | 2800 | 0 | 0 | 2020-53484 | 2020-53592 | 50318 | 9.5299 | 10675200 | - | 0 | 2851.2 | 44563.2 | 47414.4 | 8.98 | 17241600
35191130 |  |  |  | 8.1 | 8.1 |  |  |  |  | 6801.17 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 350 | 34.6626 | 833 | 31.0945 | 0.088841 | 1030 | 4.8684 | 24 | Tier 3 | ECOP | CALISTOGA | Sonoma | North Bay | Bay Area | 5792200 | E.5034420.01 | 119536531 | 35191130 | ECOP - CALISTOGA 1101 - H01 - LR736 - Ph5 | 42057 | 0 | 0 | 0 | 2020-53492 | 2020-53600 | 42768 | 8.1 | 9026120 | - | 0 | 0 | 42768 | 42768 | 8.1 | 15552000
35174476 |  |  |  | 8.78 | 8.78 |  |  |  |  | 5008.76 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 350 | 34.6626 | 833 | 31.0945 | 0.088841 | 1030 | 5.2771 | 24 | Tier 3 | ECOP | CALISTOGA | Sonoma | Sonoma | Bay Area | 5790109 | E.5033915.01 | 118913020 | 35174476 | ECOP - CALISTOGA 1101 - H01 - LR736- S_O 208157 | 47367 | 0 | 0 | 0 | 2020-53487 | 2020-53599 | 46358 | 8.7799 | 10265300 | - | 0 | 0 | 46358.4 | 46358.4 | 8.78 | 16857600
35174475 |  |  |  | 2.96 | 2.96 |  |  |  |  | 4688.7 | UNSE | 42711101 | CALISTOGA 1101 | CALISTOGA 1101736 | 350 | 34.6626 | 833 | 31.0945 | 0.088841 | 1030 | 1.7791 | 24 | Tier 3 | ECOP | CALISTOGA | Napa | North Bay | Bay Area | 5790108 | E.5033914.01 | 118912988 | 35174475 | ECOP-CALISTOGA 1101-H01-LR736- E_O CO3807 | 14993 | 0 | 0 | 0 | 2020-53203 | 2020-53204 | 15628 | 2.9598 | 3963102 | - | 0 | 0 | 15628.8 | 15628.8 | 2.96 | 5683200
74014860 |  |  |  | 3.596 | 3.596 |  |  |  |  | 12197.44 | UNSE | 83622104 | CAMP EVERS 2104 | CAMP EVERS 210410442 | 133 | 5.6589 | 2686 | 0.092361 | 0.00069444 | 2786 | 0.039323 | 1246 | Tier 3 | WDDB | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5777380 | E.0000101.01 | 113241363 | 74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 | 18989 | 0 | 0 | 0 |  | 2017-107922 | 18989 | 3.5964 | 2482735 |  |  |  |  | 0 | 0
35047314 |  |  |  | 8.45 | 8.45 |  |  |  |  | 7785.31 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210510294 | 95 | 8.3915 | 2167 | 0.54194 | 0.0057046 | 2416 | 0.36563 | 147 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114760861 | 35047314 | CWSP - CAMPEVERS2105 - LR10294 - 4KV PH1 | 44616 | 0 | 0 | 0 |  | 2018-77626 | 44616 | 8.45 | 9154000 |  |  |  |  | 0 | 0
35047315 |  |  |  | 10.9 | 10.9 |  |  |  |  | 8980.88 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210511010 | 26 | 2.176 | 2039 | 0.21641 | 0.0083235 | 2340 | 0.72629 | 441 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114760946 | 35047315 | CWSP: CAMPEVERS 2105 - LR11010 - 4KV PH2 | 57552 | 0 | 0 | 0 |  | 2018-79183 | 57552 | 10.9 | 11762100 |  |  |  |  | 0 | 0
35043994 |  |  |  | 8.6 | 8.6 |  |  |  |  | 7317.74 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210511384 | 59 | 5.2222 | 2964 | 0.0011342 | 1.9223e-05 | 3069 | 0.0012514 | 425 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114678021 | 35043994 | CWSP-CAMP EVERS 2105-LR11384-PH1.1 | 45408 | 0 | 0 | 0 | 2018-49004 | 2018-54192 | 45408 | 8.6 | 9044000 |  |  |  |  | 0 | 0
35057802 |  |  |  | 10.9 | 10.9 |  |  |  |  | 5220.14 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210512590 | 69 | 5.1174 | 2570 | 0.09844 | 0.0014267 | 2671 | 0.14048 | 1194 | Tier 3 | PRE | FELTON | Santa Cruz | Central Coast | Central Coast | 5782531 | E.5015418.01 | 115019871 | 35057802 | CWSP-CAMPEVERS2105-LR12590-4KV-PH5.1 | 57552 | 0 | 0 | 0 |  | 2018-83739 | 57552 | 10.9 | 11902500 |  |  |  |  | 0 | 0
35047316 |  |  |  | 11.6 | 11.6 |  |  |  |  | 9809.56 | UNSE | 43432104 | BEN LOMOND 0401 | CAMP EVERS 21055206 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! |  | Tier 3 | PRE | BEN LOMOND | Santa Cruz | Central Coast | Central Coast | 5786126 | # | 114760990 | 35047316 | CWSP - CAMPEVERS2105 - LR 5206 - 4KV PH3 | 61248 | 0 | 0 | 0 |  | 2018-81731 | 61248 | 11.6 | 12469100 |  |  |  |  | 0 | 0
35052734 |  |  |  | 7.5 | 7.5 |  |  |  |  | 12757.98 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055232 | 50 | 4.5152 | 2985 | 0.00086284 | 1.7257e-05 | 3065 | 0.00096027 | 1079 | Tier 3 | PRE | FELTON | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114646899 | 35052734 | CWSP-CAMP EVERS 2105-LR5232-PH1.1 | 39600 | 0 | 0 | 0 |  | 2018-50134 | 39600 | 7.5 | 7752300 |  |  |  |  | 0 | 0
35047317 |  |  |  | 10.2 | 10.2 |  |  |  |  | 4737.11 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 21055300 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! |  | Tier 3 | PRE | FELTON | Santa Cruz | Central Coast | Central Coast |  |  | 114760995 | 35047317 | CWSP - CAMPEVERS2105 - LR 5300 - 4KV PH7 | 53856 | 0 | 0 | 0 |  | 2018-83742 | 53856 | 10.2 | 11084200 |  |  |  |  | 0 | 0
35043993 |  |  |  | 7.4 | 7.4 |  |  |  |  | 8183.38 | UNSE | 83622105 | CAMP EVERS 2105 | CAMP EVERS 210574170 | 43 | 3.5755 | 2990 | 0.00072063 | 1.6759e-05 | 3071 | 0.00099928 | 118 | Tier 3 | PRE | BEN LOMOND | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114677896 | 35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 | 39072 | 0 | 0 | 0 |  | 2018-81770 | 39072 | 7.4 | 7943900
35075365 |  |  |  | 0.323 | 0.323 |  |  |  |  | 2531.22 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210610718 | 98 | 8.4677 | 2733 | 0.050195 | 0.0005122 | 2842 | 0.0012828 | 1043 | Tier 2 | WDDB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 116490172 | 35075365 | RPL OH.COND.CAMP EVERS 2106 19-0015630 | 1706 | 0 | 0 | 0 |  | 2019-14486 | 1706 | 0.32311 | 386320 |  |  |  |  | 0 | 0
35051472 |  |  |  | 0.867 | 0.867 |  |  |  |  | 23859.71 | ESTS | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.01516 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 | E.5015682.01.01 | 114865601 | 35051472 | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.1 | 4577 | 0 | 0 | 0 | 2018-63027 | 2018-64528 | 7708.8 | 1.46 | 1560056 | N/A | 0 | 0 | 4577 | 4577 | 0.86686 | 1664363.6364
|  |  |  | 0.442 | 0.442 |  |  |  |  | #N/A | #N/A | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.0077289 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 | E.5015682.01.02 | 119896242 |  | CWSP - CAMP EVERS 2106 - LR5020 - PH 3.2 | 2335 | 0 | 0 | 0 |  | 2018-64528 | 7708.8 | 1.46 | 1560056 | N/A | 0 | 0 | 2335 | 2335 | 0.44223 | 849090.9091
|  |  |  | 1.586 | 1.586 |  |  |  |  | #N/A | #N/A | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.027733 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 | E.5015682.01.03 | 119896249 |  | CWSP - CAMP EVERS 2106 -LR5020 - PH 3.3 | 8375 | 0 | 0 | 0 |  | 2018-64528 | 7708.8 | 1.46 | 1560056 | N/A | 0 | 0 | 8375 | 8375 | 1.5862 | 3045454.5455
|  |  |  | 1.948 | 1.948 |  |  |  |  | #N/A | #N/A | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.034063 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 | E.5015682.01.04 | 119896480 |  | CWSP - CAMP EVERS 2106 -LR5020 - PH 3.4 | 10284 | 0 | 0 | 0 |  | 2018-64528 | 7708.8 | 1.46 | 1560056 | N/A | 0 | 0 | 10284 | 10284 | 1.9477 | 3739636.3636
|  |  |  | 1.9 | 1.9 |  |  |  |  | #N/A | #N/A | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.033224 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 | E.5015682.01.05 | 119896482 |  | CWSP - CAMP EVERS 2106 -LR5020 - PH 3.5 | 10033 | 0 | 0 | 0 |  | 2018-64528 | 7708.8 | 1.46 | 1560056 | N/A | 0 | 0 | 10033 | 10033 | 1.9002 | 3648363.6364
35047311 |  |  |  | 8.87 | 8.87 |  |  |  |  | 22141.8 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 21065020 | 185 | 15.0734 | 2464 | 0.3934 | 0.0021265 | 2540 | 0.1551 | 46 | Tier 3 | PRE | SCOTTS VALLEY | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114758053 | 35047311 | CWSP-CAMP EVERS 2106-LR5020-PH1.1 | 46833.6 | 0 | 0 | 0 | 2018-56530 | 2018-58912 | 46833.6 | 8.87 | 9176000
35042367 |  |  |  | 7.46 | 7.46 |  |  |  |  | 22274.16 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660120 | 42 | 4.3466 | 2268 | 0.16006 | 0.0038109 | 2403 | 0.18405 | 296 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5530160 |  | 114640938 | 35042367 | CWSP-CAMP EVERS 2106-LR60124-PH3.1 | 39388.8 | 0 | 0 | 0 | 2018-46207 | 2018-51616 | 39388.8 | 7.46 | 8096500 |  |  |  |  | 0 | 0
35042369 |  |  |  | 7.13 | 7.13 |  |  |  |  | 10824.51 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 267 | 22.4613 | 2243 | 1.1389 | 0.0042657 | 2296 | 0.24223 | 57 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5530160 |  | 114640931 | 35042369 | CWSP-CAMP EVERS 2106-LR60124-PH1.1 | 37646.4 | 0 | 0 | 0 | 2018-43257 | 2018-45681 | 37646.4 | 7.13 | 11070000
35042368 |  |  |  | 7.36 | 7.36 |  |  |  |  | 7726.66 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 267 | 22.4613 | 2243 | 1.1389 | 0.0042657 | 2296 | 0.25005 | 57 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5530160 |  | 114640937 | 35042368 | CWSP-CAMP EVERS 2106-LR60124-PH2.1 | 38860.8 | 0 | 0 | 0 | 2018-43450 | 2018-46493 | 38860.8 | 7.36 | 11692500
35042366 |  |  |  | 7.21 | 7.21 |  |  |  |  | 7261.21 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 267 | 22.4613 | 2243 | 1.1389 | 0.0042657 | 2296 | 0.24495 | 57 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5530160 |  | 114640939 | 35042366 | CWSP-CAMP EVERS 2106-LR60124-PH4.1 | 38068.8 | 0 | 0 | 0 | 2018-46209 | 2018-53264 | 38068.8 | 7.21 | 7574500
35042365 |  |  |  | 8.98 | 8.98 |  |  |  |  | 8089.18 | UNSE | 83622106 | CAMP EVERS 2106 | CAMP EVERS 210660124 | 267 | 22.4613 | 2243 | 1.1389 | 0.0042657 | 2296 | 0.30508 | 57 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5530160 |  | 114641001 | 35042365 | CWSP-CAMP EVERS 2106-LR60124-PH5.1 | 47414.4 | 0 | 0 |  | 2018-46210 | 2018-54997 | 47414.4 | 8.98 | 10457000
35192031 |  |  |  | 4.04 | 4.04 |  |  |  |  | 3787 | UNSE | 152471101 | COLUMBIA HILL 1101 | COLUMBIA HILL 110135424 | 147 | 13.8646 | 1580 | 3.4923 | 0.023757 | 1711 | 0.6818 | 62 | Tier 3 | ECOP | NORTH SAN JUAN | Nevada | Sierra | Northern | 5792070 | E.5034378.01 | 119553917 | 35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 | 15234 | 0 | 0 | 0 | [5 empty] | -
35052738 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 163351705 | CURTIS 1705 | CURTIS 1705843 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 149 | Tier 3 | PRE | SONORA | Tuolumne | Yosemite | Central Valley | 5530178 |  | 114688224 | 35052738 | CWSP-CURTIS 1705-TS843-PH1.1 | 0 | 0 | 0 | 0
35042603 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 152261103 | DIAMOND SPRINGS 1103 | DIAMOND SPRINGS 1103CB | 109 | 0.55038 | 2815 | 0.026412 | 0.00024231 | 2841 | #DIV/0! | 1387 | Tier 3 | WDDB | PLACERVILLE | El Dorado | Sierra | Northern | 5530173 |  | 114628116 | 35042603 | DIAMOND SPRINGS 1103 RECOND 18-0029738 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35076129 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 152261105 | DIAMOND SPRINGS 1105 | DIAMOND SPRINGS 1105CB | 47 | 2.0698 | 2707 | 0.028118 | 0.00059825 | 2851 | #DIV/0! | 898 | Tier 3 | WDDB | EL DORADO | El Dorado | Sierra | Northern | 5784105 | E.5019947.01 | 116489047 | 35076129 | DIAMOND SPRINGS 1105 RECOND WD18-0105867 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
74011865 |  |  |  | 2.083 | 2.083 |  |  |  |  | 90798.31 | UNSE | 158031101 | ECHO SUMMIT 1101 | ECHO SUMMIT 1101344250 | 10 | 0.8075 | 2461 | 0.021484 | 0.0021484 | 2290 | 0.037132 | 2789 | Tier 3 | WDDB | ECHO LAKE | El Dorado | Sierra | Northern | 5530166 | E.0000088.01 | 112804948 | 74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' | 11000 | 0 | 0 | 0 |  | 2017-43109 | 11000 | 2.0833 | 3600000 |  |  |  |  | 0 | 0
35060228 |  |  |  | 0.947 | 0.947 |  |  |  |  | 0 | UNSE | 192381102 | EEL RIVER 1102 | EEL RIVER 11021902 | 43 | 6.5648 | 1615 | 0.97115 | 0.022585 | 1834 | 0.093862 | 1894 | Tier 3 | WDDB | FERNDALE | Humboldt | Humboldt | Northern | 5530164 |  | 113663476 | 35060228 | 2019 OH COND RPLC: EEL RIVER 1102 FU1903 | 5000 | 0 | 0 | 0 |  | 2017-99508 | 5000 | 0.94697 | 500000 |  |  |  |  | 0 | 0
35061810 |  |  |  |  | 0 |  |  |  |  | 4129.82 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119612 | 102 | 9.1294 | 2037 | 0.85418 | 0.0083743 | 2313 | #DIV/0! | 238 | Tier 2 | PRE | EL DORADO | El Dorado | Sierra | Northern | 5783177 | E.5015573.01 | 115217232 | 35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35056733 |  |  |  | 2.13 | 2.13 |  |  |  |  | 563675.92 | PEND | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.17548 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782532 | E.5015417.01 | 114987201 | 35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 | 11246.4 | 0 | 0 | 0 |  | 2018-78760 | 27482.4 | 5.205 | 5577870 | 2019-32231 | 0 | 0 | 11246.4 | 11246.4 | 2.13 | 4089600 | 2020-50008 | 2019-55678 | [9 empty] | 2020-33819
35057010 |  |  |  | 1.31 | 1.31 |  |  |  |  | 306863.36 | ESTS | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.10793 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782533 | E.5015416.01 | 114987251 | 35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 | 57446 | 0 | 0 | 0 |  | 2018-78870 | 9556.8 | 1.81 | 1856290 | 2019-52013 | 0 | 0 | 57446 | 57446 | 10.8799 | 20889454.5455 | 2020-60830 | [10 empty] | 2020-35209
35109546 |  |  |  | 2.77 | 2.77 |  |  |  |  | 522531 | ADER | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.22821 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5785517 | E.5015416.03 | 117349071 | 35109546 | CWSP - EL DORADO 2101 - 19752 - PH 2.3 | 14625 | 0 | 0 | 0 |  | 2018-78870 | 9556.8 | 1.81 | 1856290 | 2019-52013 | 0 | 0 | 14625.6 | 14625.6 | 2.77 | 5318400 | 2020-61719
35109541 |  |  |  | 2.67 | 2.67 |  |  |  |  | 518321.93 | ESTS | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.21997 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5785513 | E.5015417.03 | 117348508 | 35109541 | CWSP - EL DORADO 2101 - LR19752 - PH 1.3 | 14097.6 | 0 | 0 | 0 |  | 2018-78760 | 27482.4 | 5.205 | 5577870 | 2019-32231 | 0 | 0 | 14097.6 | 14097.6 | 2.67 | 5126400 | 2019-67211
35057018 |  |  |  | 2.01 | 2.01 |  |  |  |  | 235256.92 | PEND | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210119752 | 436 | 36.5225 | 1946 | 4.4909 | 0.0103 | 1929 | 0.24131 | 13 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782535 | E.5015414.01 | 114987363 | 35057018 | CWSP - EL DORADO 2101 - LR19752 - PH4.1 | 507 | 11379 | 0 | 0 |  | 2018-78881 | 37118.4 | 7.03 | 7593680 | 2019-32237 | 0 | 11379 | 507 | 11886 | 2.2511 | 9246720 | 2019-54822 | [10 empty] | 2020-35302
35051356 |  |  |  | 10.47 | 10.47 |  |  |  |  | 3369.78 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | 339 | 34.3764 | 2252 | 1.3974 | 0.0041222 | 2212 | 0.28516 | 67 | Tier 3 | PRE | GRIZZLY FLATS | El Dorado | Sierra | Northern | 5530173 |  | 114861944 | 35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 | 55300 | 0 | 0 | 0 |  | 2018-78870 | 9556.8 | 1.81 | 1856290 | 2019-52013 | 0 | 0 | 55300 | 55300 | 10.4735 | 20109090.9091
35065842 |  |  |  |  | 0 |  |  |  |  | 1547.88 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | 339 | 34.3764 | 2252 | 1.3974 | 0.0041222 | 2212 | #DIV/0! | 67 | Tier 3 | PRE | EL DORADO | El Dorado | Sierra | Northern | 5782591 | E.5015430.01 | 115417043 | 35065842 | CWSP-EL DORADO 2101-LR26000-PH3.1 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
74022383 |  |  |  | 11.92 | 11.92 |  |  |  |  | 31047.96 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210126000 | 339 | 34.3764 | 2252 | 1.3974 | 0.0041222 | 2212 | 0.32466 | 67 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782840 | E.5015490.01 | 114791963 | 74022383 | CWSP-EL DORADO PH 2101-LR26000-PH 1 | 62937.6 | 0 | 0 | 0 |  | 2018-62798 | 62937.6 | 11.92 | 11952400 |  |  |  |  | 0 | 0
35058026 |  |  |  | 0.57 | 0.57 |  |  |  |  | 109771.86 | ESTS | 152762101 | EL DORADO PH 2101 | EL DORADO PH 210163464 | 70 | 13.6239 | 1138 | 3.7492 | 0.05356 | 1053 | 0.1051 | 1639 | Tier 3 | PRE | PACIFIC HOUSE | El Dorado | Sierra | Northern | 5530173 |  | 115027447 | 35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG | 3009.6 | 0 | 0 | 0 |  | 2018-77803 | 3000 | 0.56818 | 900000 | N/A | 0 | 0 | 3009.6 | 3009.6 | 0.57 | 1094400
35174465 |  |  |  | 9 | 9 |  |  |  |  | 19131.52 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 21016852 | 309 | 25.2481 | 2028 | 2.6354 | 0.0085289 | 1808 | 0.78957 | 18 | Tier 3 | ECOP | POLLOCK PINES | El Dorado | Sierra | Northern | 5790002 | E.5033921.01 | 118911790 | 35174465 | ECOP - EL DORADO 2101 - H02 - LR6852-Ph1 | 28394 | 32374 | 0 | 0 | 2020-54634 | 2020-54635 | 62673.6 | 11.87 | 21358418 | 2020-09-29 | 0 | 42028.8 | 28406.4 | 70435.2 | 13.34 | 25612800
35173756 |  |  |  | 9 | 9 |  |  |  |  | 8178.86 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 21016852 | 309 | 25.2481 | 2028 | 2.6354 | 0.0085289 | 1808 | 0.63745 | 18 | Tier 3 | ECOP | POLLOCK PINES | El Dorado | Sierra | Northern | 5790003 | E.5030964.01 | 118911791 | 35173756 | ECOP - EL DORADO 2101 - H02 - LR6852-PH2 | 48525 | 0 | 1291 | 0 | 2020-51435 | 2020-51436 | 48523 | 9.19 | 12794491 | 2020-09-29 | 0 | 0 | 47520 | 47520 | 9 | 17280000
35174466 |  |  |  | 7.35 | 7.35 |  |  |  |  | 12122.05 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 21016852 | 309 | 25.2481 | 2028 | 2.6354 | 0.0085289 | 1808 | 0.51402 | 18 | Tier 3 | ECOP | POLLOCK PINES | El Dorado | Sierra | Northern | 5790004 | E.5033920.01 | 118911793 | 35174466 | ECOP - EL DORADO 2101 - H02 - LR6852-PH3 | 32300 | 0 | 0 | 0 | 2020-51902 | 2020-51953 | 32577 | 6.1699 | 8664332 | 2020-09-29 | 0 | 0 | 38808 | 38808 | 7.35 | 14112000
35058272 |  |  |  | 10.25 | 10.25 |  |  |  |  | 5637.12 | UNSE | 152762101 | EL DORADO PH 2101 | EL DORADO PH 2101CB | 74 | 7.4577 | 2250 | 0.3064 | 0.0041406 | 2350 | 0.28215 | 76 | Tier 3 | PRE | POLLOCK PINES | El Dorado | Sierra | Northern | 5782589 | E.5015419.01 | 114987334 | 35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 | 54120 | 0 | 0 | 0 | 2018-78694 | 2018-81386 | 54120 | 10.25 | 11380340 |  |  |  |  | 0 | 0
35061811 |  |  |  | 9.44 | 9.44 |  |  |  |  | 6674.54 | UNSE | 152762102 | EL DORADO PH 2102 | EL DORADO PH 210219542 | 111 | 9.5212 | 2512 | 0.19285 | 0.0017374 | 2550 | 0.12811 | 41 | Tier 3 | PRE | EL DORADO | El Dorado | Sierra | Northern | 5783198 | E.5015574.01 | 115217237 | 35061811 | CWSP-EL DORADO PH 2102-LR19542 | 49843 | 0 | 0 | 0 |  | 2019-64816 | 49632 | 9.4 | 10245100 | 2020-22355 | 0 | 0 | 49843 | 49843 | 9.44 | 18124727.2727
35061812 |  |  |  | 3.22 | 3.22 |  |  |  |  | 5867.15 | UNSE | 152762101 | EL DORADO PH 2102 | EL DORADO PH 21026645 | 52 | 4.2184 | 2469 | 0.10851 | 0.0020868 | 2386 | 0.055496 | 121 | Tier 3 | PRE | EL DORADO | El Dorado | Sierra | Northern | 5783199 | E.5015575.01 | 115221464 | 35061812 | CWSP-EL DORADO PH 2102-LR6645-PH1 | 17001.6 | 0 | 0 | 0 |  | 2018-93741 | 17001.6 | 3.22 | 3461800
31334290 |  |  |  | 1.515 | 1.515 |  |  |  |  | 1413.82 | UNSE | 42981101 | ELK 1101 | ELK 11011272 | 236 | 22.0935 | 2587 | 0.29926 | 0.0012681 | 2487 | 0.013749 | 1312 | Tier 3 | WDDB | ALBION | Mendocino | Humboldt | Northern | 5533649 |  | 112994612 | 31334290 | RECON 24 SPANS -ALBION RIDGE RD | 8000 | 0 | 0 | 0 |  | 2018-11420 | 8000 | 1.5152 | 880000 |  |  |  |  | 0 | 0
35093737 |  |  |  |  | 0 |  |  |  |  | 560 | UNSE | 13432207 | FAIRVIEW 2207 | FAIRVIEW 2207P142 | 41 | 1.2204 | 3346 | 0.00015757 | 3.8432e-06 | 3351 | #DIV/0! | 2961 | Tier 3 | WDDB | CROCKETT | Contra Costa | Diablo | Bay Area | 5530164 | # | 117123046 | 35093737 | FAIRVIEW 2207-CROCKETT BLVD-WIRE DOWN | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
31291639 |  |  |  | 0.587 | 0.587 |  |  |  |  | 118961.07 | ESTS | 182951101 | FOOTHILL 1101 | FOOTHILL 1101CB | 149 | 13.3962 | 908 | 11.8181 | 0.079316 | 698 | 0.34696 | 668 | Tier 3 | WDDB | SAN LUIS OBISPO | San Luis Obispo | Los Padres | Central Coast | 5530166 |  | 112443196 | 31291639 | FH 1101 O'CONNOR WY RECOND 12 SPANS, SLO | 3100 | 0 | 0 | 0 |  | 2017-02976 | 3100 | 0.58712 | 374000 |  |  |  |  | 0 | 0 |  | 2018-64266
35066622 |  |  |  | 2.064 | 2.064 |  |  |  |  | 50019.24 | UNSE | 182951101 | FOOTHILL 1101 | FOOTHILL 1101CB | 149 | 13.3962 | 908 | 11.8181 | 0.079316 | 698 | 1.22 | 668 | Tier 3 | WDDB | SAN LUIS OBISPO | San Luis Obispo | Los Padres | Central Coast | 5783289 | E.5015594.01 | 113245749 | 35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO | 10900 | 0 | 0 | 0 |  | 2018-02855 | 10900 | 2.0644 | 1031140 |  |  |  |  | 0 | 0
31364228 |  |  |  | 0.85 | 0.85 |  |  |  |  | 645.06 | UNSE | 182951101 | FOOTHILL 1101 | FOOTHILL 1101CB | 149 | 13.3962 | 908 | 11.8181 | 0.079316 | 698 | 0.50241 | 668 | Tier 1 | WDDB | SAN LUIS OBISPO | San Luis Obispo | Los Padres | Central Coast | 5530166 |  | 113782453 | 31364228 | RECOND 4490FT OF 4ACSR WITH 2CU TW | 4490 | 0 | 0 | 0 |  | 2018-89198 | 4490 | 0.85038 | 673500 |  |  |  |  | 0 | 0
35192025 |  |  |  | 8.18 | 8.18 |  |  |  |  | 2843.76 | UNSE | 152181101 | FORESTHILL 1101 | FORESTHILL 11011802 | 259 | 22.2318 | 1865 | 3.2365 | 0.012496 | 2049 | 0.81068 | 29 | Tier 3 | ECOP | FORESTHILL | Placer | Sierra | Northern | 5792058 | E.5034366.01 | 119550890 | 35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 - PH 1 | 37463 | 0 | 1264 | 0 | [5 empty] | -
35192028 |  |  |  | 7 | 7 |  |  |  |  | 1529.29 | UNSE | 152181101 | FORESTHILL 1101 | FORESTHILL 11011802 | 259 | 22.2318 | 1865 | 3.2365 | 0.012496 | 2049 | 0.68276 | 29 | Tier 3 | ECOP | FORESTHILL | Placer | Sierra | Northern | 5792059 | E.5034367.01 | 119550898 | 35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 - PH 2 | 44405 | 0 | 0 | 0 | [5 empty] | -
35192029 |  |  |  | 7 | 7 |  |  |  |  | 1957.71 | UNSE | 152181101 | FORESTHILL 1101 | FORESTHILL 11011802 | 259 | 22.2318 | 1865 | 3.2365 | 0.012496 | 2049 | 0.69695 | 29 | Tier 3 | ECOP | FORESTHILL | Placer | Sierra | Northern | 5792060 | E.5034368.01 | 119551168 | 35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 - PH 3 | 36474 | 0 | 1606 | 0 | [5 empty] | -
35056732 |  |  |  | 12.2 | 12.2 |  |  |  |  | 2664.39 | UNSE | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | 163 | 11.6759 | 2270 | 0.61325 | 0.0037623 | 2261 | 0.42932 | 42 | Tier 3 | PRE | FORESTHILL | Placer | Sierra | Northern | 5782592 | E.5015429.01 | 114988838 | 35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING | 64416 | 0 | 0 | 0 |  | 2018-72763 | 64416 | 12.2 | 13155800
35200127 |  |  |  | 2.11 | 2.11 |  |  |  |  | 1857.37 | UNSE | 152181101 | FORESTHILL 1101 | FORESTHILL 110150486 | 163 | 11.6759 | 2270 | 0.61325 | 0.0037623 | 2261 | 0.074251 | 42 | Tier 3 | ECOP | FORESTHILL | Placer | Sierra | Northern | 5792513 | E.5034527.01 | 119768637 | 35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 | 11515 | 0 | 0 | 0 | [5 empty] | -
31334291 |  |  |  | 0.51 | 0.51 |  |  |  |  | 355815.68 | PEND | 42761101 | FORT BRAGG A 1101 | FORT BRAGG A 11013113 | 68 | 10.0269 | 2140 | 0.42396 | 0.0062347 | 2061 | 0.014448 | 2292 | Tier 3 | WDDB | FORT BRAGG | Mendocino | Humboldt | Northern | 5530164 |  | 112994395 | 31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG | 2710 | 0 | 0 | 0 |  | 2018-10393 | 1920 | 0.36364 | 212000 | N/A | 0 | 0 | 2692.8 | 2692.8 | 0.51 | 979200 |  | 2019-31651 | 0 | 0 | 2710 | 2710 | 0.51326 | 688000 | 1115000 | 253.8745 |  | 2019-19275
35060383 |  |  |  | 0.627 | 0.627 |  |  |  |  | 0 | UNSE | 192311142 | FRUITLAND 1142 | FRUITLAND 1142CB | 116 | 10.504 | 1105 | 6.5332 | 0.056321 | 1552 | 0.26128 | 671 | Tier 2 | WDDB | MYERS FLAT | Humboldt | Humboldt | Northern | 5530164 |  | 112190914 | 35060383 | WDDB - FRUITLAND 1142CB C/O 1679 | 3310 | 0 | 0 | 0 |  | 2016-120488 | 3310 | 0.62689 | 365000 |  |  |  |  | 0 | 0
35050942 |  |  |  | 1.7 | 1.7 |  |  |  |  | 13257.76 | UNSE | 192221101 | GARBERVILLE 1101 | GARBERVILLE 11011514 | 123 | 14.7717 | 1628 | 2.7266 | 0.022168 | 2239 | 0.21024 | 2062 | Tier 3 | PRE | GARBERVILLE | Humboldt | Humboldt | Northern | 5530164 |  | 114848297 | 35050942 | CWSP: GARBERVILLE 1101 HENDRIX PILOT | 8976 | 0 | 0 | 0 |  | 2018-61143 | 8976 | 1.7 | 1890000 |  |  |  |  | 0 | 0
35046211 |  |  |  | 0.758 | 0.758 |  |  |  |  | 23788.8 | UNSE | 192221102 | GARBERVILLE 1102 | GARBERVILLE 11021510 | 107 | 13.1584 | 1476 | 3.1476 | 0.029417 | 2047 | 0.12148 | 1630 | Tier 3 | PRE | REDWAY | Humboldt | Humboldt | Northern | 5530164 |  | 114730956 | 35046211 | CWSP - GARBERVILLE 1102 HENDRIX PILOT | 4000 | 0 | 0 | 0 |  | 2018-51792 | 4000 | 0.75758 | 800000 |  |  |  |  | 0 | 0
35013233 |  |  |  | 0.604 | 0.604 |  |  |  |  | 4558.76 | UNSE | 182131101 | GONZALES 1101 | GONZALES 11013094 | 63 | 4.0888 | 1873 | 0.77477 | 0.012298 | 1568 | 0.076681 | 2160 | Tier 3 | WDDB | GONZALES | Monterey | Central Coast | Central Coast | 5530159 | P.11990 | 113244215 | 35013233 | R2RPL OH WIRE ON GONZALS-1101 17-0063084 | 3187 | 0 | 0 | 0 |  | 2017-100348 | 3187 | 0.6036 | 361570 |  |  |  |  | 0 | 0
35074388 |  |  |  | 1.9 | 1.9 |  |  |  |  | 1017.22 | UNSE | 83192101 | GREEN VALLEY 2101 | GREEN VALLEY 210112106 | 139 | 0.34608 | 2884 | 0.011248 | 8.0919e-05 | 2905 | 0.041373 | 2108 | Tier 2 | WDDB | CORRALITOS | Santa Cruz | Central Coast | Central Coast | 5784143 | E.5019931.01 | 116157025 | 35074388 | RECOND GV2101 FUSE 12347 ZONE | 10032 | 0 | 0 | 0 |  | 2019-30870 | 10032 | 1.9 | 1672770 |  |  |  |  | 0 | 0
31297273 |  |  |  | 0.758 | 0.758 |  |  |  |  | 1263.81 | UNSE | 42841111 | GUALALA 1111 | GUALALA 1111445166 | 71 | 7.5601 | 2446 | 0.15871 | 0.0022354 | 2359 | 0.010662 | 2157 | Tier 2 | WDDB | GUALALA | Mendocino | Sonoma | Northern | 5530175 |  | 112523454 | 31297273 | RECOND HWY1 (BY SW 92493)- GUALALA 1111 | 4000 | 0 | 0 | 0 |  | 2018-10311 | 4000 | 0.75758 | 440000 |  |  |  |  | 0 | 0
31289812 |  |  |  | 0.436 | 0.436 |  |  |  |  | 0 | UNSE | 42841112 | GUALALA 1112 | GUALALA 11121294 | 234 | 19.8593 | 2179 | 1.2961 | 0.0055387 | 2054 | 0.019064 | 1069 | Tier 2 | WDDB | POINT ARENA | Mendocino | Sonoma | Northern | 5530175 |  | 112409713 | 31289812 | RECOND TAP W TW - LCO 5265 GUALALA 1112 | 2300 | 0 | 0 | 0 |  | 2018-12431 | 2300 | 0.43561 | 253000 |  |  |  |  | 0 | 0
35030568 |  |  |  | 0.888 | 0.888 |  |  |  |  | 70058.49 | PEND | 24101101 | HALF MOON BAY 1101 | HALF MOON BAY 1101CB | 80 | 1.5982 | 2409 | 0.20127 | 0.0025158 | 2057 | 0.074925 | 1132 | Tier 2 | WDDB | HALF MOON BAY | San Mateo | Peninsula | Central Coast | 5531041 |  | 114435598 | 35030568 | TW ON HALF MOON BAY1101 FUCO 4141 | 4690 | 0 | 0 | 0 | 2019-21707 | 2018-25302 | 4690 | 0.88826 | 445000 |  |  |  |  | 0 | 0
35053429 |  |  |  | 1.06 | 1.06 |  |  |  |  | 105334.94 | PEND | 24101102 | Half Moon Bay 1102 | HALF MOON BAY 11022032 | 103 | 0.56279 | 2874 | 0.010949 | 0.0001063 | 2894 | 0.013817 | 1589 | Tier 3 | WDDB | HALF MOON BAY | San Mateo | Peninsula | Central Coast | 5531041 |  | 114921419 | 35053429 | HALF MOON BAY 1102 - FUCO 12457 REPL OH | 4012.8 | 0 | 0 | 0 |  | 2019-15587 | 4000 | 0.75758 | 560000 | N/A | 0 | 0 | 4012.8 | 4012.8 | 0.76 | 1459200 | 2019-33097
31288039 |  |  |  | 0.568 | 0.568 |  |  |  |  | 795.32 | UNSE | 192401101 | HOOPA 1101 | HOOPA 11013304 | 88 | 17.341 | 1679 | 1.7148 | 0.019486 | 2081 | 0.037632 | 1582 | Tier 3 | WDDB | HOOPA | Humboldt | Humboldt | Northern | 5530164 |  | 112390862 | 31288039 | HOOPA 1101 RCOND WITH TREE WIRE | 3000 | 0 | 0 | 0 |  | 2016-123213 | 3000 | 0.56818 | 330000 |  |  |  |  | 0 | 0
35094389 |  |  |  | 0.52 | 0.52 |  |  |  |  | 71054.77 | ESTS | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.040218 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785159 | E.5015029.03 | 117130852 | 35094389 | CWSP - KONOCTI 1102 - LR 532 - PH2 | 2741 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 2741 | 2741 | 0.51913 | 996727.2727
35094391 |  |  |  | 0.78 | 0.78 |  |  |  |  | 27375.07 | UNSC | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.060327 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785161 | E.5015029.05 | 117130854 | 35094391 | CWSP - KONOCTI 1102 - LR 532 - PH4 | 4117 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 4117 | 4117 | 0.77973 | 1497090.9091
35094395 |  |  |  | 0.59 | 0.59 |  |  |  |  | 53172.86 | ESTS | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.045632 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785165 | E.5015029.09 | 117130858 | 35094395 | CWSP - KONOCTI 1102 - LR 532 - PH8 | 3132 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 3132 | 3132 | 0.59318 | 1138909.0909
35094396 |  |  |  | 0.82 | 0.82 |  |  |  |  | 30622.54 | UNSC | 43311102 | KONOCTI 1102 | KONOCTI 1102532 | 124 | 9.7315 | 1999 | 1.1234 | 0.0090595 | 2215 | 0.063421 | 153 | Tier 3 | PRE | KELSEYVILLE | Lake | Humboldt | Northern | 5785166 | E.5015029.10 | 117130859 | 35094396 | CWSP - KONOCTI 1102 - LR 532 - PH9 | 4351 | 0 | 0 | 0 |  | 2018-50209 | 4593.6 | 0.87 | 930690 | N/A | 0 | 0 | 4351 | 4351 | 0.82405 | 1582181.8182
35052726 |  |  |  |  | 0 |  |  |  |  | 27219.3 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 110660116 | 151 | 12.2027 | 2646 | 0.14421 | 0.00095505 | 2757 | #DIV/0! | 917 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114623448 | 35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35052727 |  |  |  |  | 0 |  |  |  |  | 18340.76 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 110660116 | 151 | 12.2027 | 2646 | 0.14421 | 0.00095505 | 2757 | #DIV/0! | 917 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114642563 | 35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 | 0 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35072147 |  |  |  | 1.49 | 1.49 |  |  |  |  | 159464.49 | ESTS | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.13733 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5782536 | E.5014319.01 | 114474286 | 35072147 | CWSP - LOS GATOS 1106 - LB44 - PH 1.1 | 7867.2 | 0 | 0 | 0 |  | 2018-30241 |  | 0 |  | N/A | 0 | 0 | 7867.2 | 7867.2 | 1.49 | 2860800
35113106 |  |  |  | 0.87 | 0.87 |  |  |  |  | 5361.99 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.080184 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786052 | E.5014534.02 | 117492252 | 35113106 | CWSP - LOS GATOS 1106 - LB44 - PH 2.2B | 4593.6 | 0 | 0 | 0 |  | 2018-31656 | 12116 | 2.2947 | 1355000 | N/A | 0 | 0 | 4593.6 | 4593.6 | 0.87 | 1670400
35113107 |  |  |  | 0.53 | 0.53 |  |  |  |  | 5681.53 | ESTS | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.048847 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786053 | E.5014534.03 | 117492254 | 35113107 | CWSP - LOS GATOS 1106 - LB44 - PH 2.3C | 2798.4 | 0 | 0 | 0 |  | 2018-31656 | 12116 | 2.2947 | 1355000 | N/A | 0 | 0 | 2798.4 | 2798.4 | 0.53 | 1017600
35031663 |  |  |  | 0.69 | 0.69 |  |  |  |  | 41251.34 | ESTS | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.063594 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5780842 | E.5014535.01 | 114474316 | 35031663 | CWSP - LOS GATOS 1106 - LB44 - PH 3.1 | 3643.2 | 0 | 0 | 0 |  | 2018-31688 | 4800 | 0.90909 | 543400 | N/A | 0 | 0 | 3643.2 | 3643.2 | 0.69 | 1324800
35113110 |  |  |  | 1.5 | 1.5 |  |  |  |  | 5055.8 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.13825 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786056 | E.5014535.03 | 117492259 | 35113110 | CWSP - LOS GATOS 1106 - LB44 - PH 3.3 | 7920 | 0 | 0 | 0 |  | 2018-31688 | 4800 | 0.90909 | 543400 | N/A | 0 | 0 | 7920 | 7920 | 1.5 | 2880000
35113111 |  |  |  | 0.77 | 0.77 |  |  |  |  | 4735.39 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.070967 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786057 | E.5014535.04 | 117492280 | 35113111 | CWSP - LOS GATOS 1106 - LB44 - PH 3.4 | 4065.6 | 0 | 0 | 0 |  | 2018-31688 | 4800 | 0.90909 | 543400 | N/A | 0 | 0 | 4065.6 | 4065.6 | 0.77 | 1478400
35119967 |  |  |  | 0.87 | 0.87 |  |  |  |  | 4623.3 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.080184 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786605 | E.5014535.05 | 117721746 | 35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 | 4593.6 | 0 | 0 | 0 |  | 2018-31688 | 4800 | 0.90909 | 543400 | N/A | 0 | 0 | 4593.6 | 4593.6 | 0.87 | 1670400
35119968 |  |  |  | 0.41 | 0.41 |  |  |  |  | 5437.96 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.037788 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786604 | E.5014535.06 | 117721842 | 35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 | 2164.8 | 0 | 0 | 0 |  | 2018-31688 | 4800 | 0.90909 | 543400 | N/A | 0 | 0 | 2164.8 | 2164.8 | 0.41 | 787200
35119972 |  |  |  | 1.62 | 1.62 |  |  |  |  | 122932.02 | UNSE | 82021106 | LOS GATOS 1106 | LOS GATOS 1106LB44 | 213 | 19.3536 | 1864 | 2.6623 | 0.012499 | 1950 | 0.14931 | 841 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5786589 | E.5015493.01 | 114749460 | 35119972 | CWSP - LOS GATOS 1106 - LB44 - PH 4.1 | 8553.6 | 0 | 0 | 0 |  | 2018-56407 | 23971.2 | 4.54 | 4835000 | N/A | 0 | 0 | 8553.6 | 8553.6 | 1.62 | 3110400
35113947 |  |  |  | 24.33 | 24.33 |  |  |  |  | 1789.4 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760014 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 15 | Tier 3 | PRE | LOS GATOS | Santa Cruz | De Anza | Central Coast | 5786220 | E.5024243.01 | 117557035 | 35113947 | CWSP - LOS GATOS 1107 – LR 60114 | 128462.4 | 0 | 0 | 0 |  | 2019-44202 | 128462.4 | 24.33 | 24330000
35046280 |  |  |  | 7.06 | 7.06 |  |  |  |  | 3944.54 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.020413 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114720436 | 35046280 | CWSP - LOS GATOS 1107 - LR60092 PH 6 | 37276.8 | 0 | 0 | 0 |  | 2018-61234 | 37276.8 | 7.06 | 7256258 |  |  |  |  | 0 | 0
35052728 |  |  |  | 7.6 | 7.6 |  |  |  |  | 21890.4 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.021975 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114670659 | 35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 | 40128 | 0 | 0 | 0 |  |  | 40128 | 7.6 | [5 empty] | 0 | 0
35046279 |  |  |  | 7.7 | 7.7 |  |  |  |  | 9620.4 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.022264 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114720434 | 35046279 | CWSP - LOS GATOS 1107-LR60092 PH 5 | 40656 | 0 | 0 | 0 |  | 2018-59191 | 40656 | 7.7 | 7831508 |  |  |  |  | 0 | 0
35046276 |  |  |  | 6.5 | 6.5 |  |  |  |  | 13883.46 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.018794 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114720357 | 35046276 | CWSP LOS GATOS 1107-LR60092 PH 3 | 34320 | 0 | 0 | 0 |  | 2018-55675 | 34320 | 6.5 | 7037300 |  |  |  |  | 0 | 0
35046278 |  |  |  | 7.9 | 7.9 |  |  |  |  | 1943.01 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.022842 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114720429 | 35046278 | CWSP LOS GATOS 1107-LR60092 PH 4 | 41712 | 0 | 0 | 0 |  | 2018-58098 | 41712 | 7.9 | 8096129 |  |  |  |  | 0 | 0
35044117 |  |  |  | 8.8 | 8.8 |  |  |  |  | 23349.97 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 110760092 | 108 | 9.7136 | 2767 | 0.041919 | 0.00038814 | 2813 | 0.025444 | 1150 | Tier 3 | PRE | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 114713255 | 35044117 | CWSP: LOS GATOS 1107 - LR60092 PH 2 | 46464 | 0 | 0 | 0 |  | 2018-54199 | 46464 | 8.8 | 9503250 |  |  |  |  | 0 | 0
35073637 |  |  |  | 0.72 | 0.72 |  |  |  |  | 415.55 | UNSE | 82021107 | LOS GATOS 1107 | LOS GATOS 1107CB | 192 | 15.2993 | 2606 | 0.22088 | 0.0011504 | 2636 | 0.0069645 | 1602 | Tier 3 | WDDB | LOS GATOS | Santa Clara | De Anza | Central Coast | 5530160 |  | 115783880 | 35073637 | LOS GATOS 1107 RECOND FUSE 468855 ZONE | 3801.6 | 0 | 0 | 0 |  | 2019-07307 | 3801.6 | 0.72 | 602840 |  |  |  |  | 0 | 0
35192303 |  |  |  | 8.31 | 8.31 |  |  |  |  | 1529.29 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210110170 | 149 | 16.3165 | 1809 | 2.1297 | 0.014293 | 1532 | 0.81707 | 44 | Tier 3 | ECOP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5792095 | E.5034404.01.01 | 119556206 | 35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 - PH 1 | 30514 | 10736 | 0 | 0 | [5 empty] | -
35192304 |  |  |  | 8 | 8 |  |  |  |  | 1529.29 | UNSE | 254452101 | MARIPOSA 2101 | MARIPOSA 210110170 | 149 | 16.3165 | 1809 | 2.1297 | 0.014293 | 1532 | 0.73218 | 44 | Tier 3 | ECOP | MARIPOSA | Mariposa | Yosemite | Central Valley | 5792096 | E.5034405.01 | 119556233 | 35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 - PH 2 | 39543 | 4270 | 0 | 0 | [5 empty] | -
35081862 |  |  |  | 1.522 | 1.522 |  |  |  |  | 2669.48 | UNSE | 163011101 | MARTELL 1101 | MARTELL 110191216 | 380 | 40.579 | 1936 | 4.0231 | 0.010587 | 1795 | 0.1011 | 1307 | Tier 3 | WDDB | SUTTER CREEK | Amador | Stockton | Central Valley | 5784648 | E.5020288.01 | 116833412 | 35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW | 8034 | 0 | 0 | 0 |  | 2019-20628 | 8034 | 1.5216 | 1606800 |  |  |  |  | 0 | 0
35137599 |  |  |  | 1.29 | 1.29 |  |  |  |  | 3861.12 | UNSE | 43141101 | MIDDLETOWN 1101 | MIDDLETOWN 1101614 | 18 | 1.3814 | 2060 | 0.13857 | 0.0076984 | 2196 | 0.086697 | 152 | Tier 3 | ECOP | KELSEYVILLE | Lake | Humboldt | Northern | 5530164 |  | 118142262 | 35137599 | ECOP-MIDDLETOWN 1101-H11-LR614 | 6811.2 | 0 | 0 | 0 |  | 2019-73308 | 6811 | 1.29 | 1365600 | 2020-03-04 | 0 | 0 | 6811.2 | 6811.2 | 1.29 | 2476800
35192035 |  |  |  | 2.3 | 2.3 |  |  |  |  | 1529.29 | UNSE | 42091101 | MIRABEL 1101 | MIRABEL 1101298 | 123 | 12.5878 | 1732 | 2.1202 | 0.017238 | 1892 | 0.25956 | 43 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5792065 | E.5034373.01 | 119553910 | 35192035 | ECOP - MIRABEL 1101 - H01-LR298 | 21898 | 0 | 0 | 0 | [5 empty] | -
35052735 |  |  |  | 2.02 | 2.02 |  |  |  |  | 166611.22 | UNSC | 163661701 | MIWUK 1701 | MIWUK 170110600 | 161 | 13.2797 | 2690 | 0.10996 | 0.000683 | 2662 | 0.011207 | 1 | Tier 3 | PRE | MIWUK VILLAGE | Tuolumne | Yosemite | Central Valley | 5783905 | E.5014723.01 | 114706118 | 35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 | 10296 | 0 | 0 | 0 |  | 2018-61433 | 13305.6 | 2.52 | 2730940 | 2019-35884 | 0 | 0 | 10296 | 10296 | 1.95 | 3744000 | 2020-07085 | [10 empty] | 2020-60207
35115046 |  |  |  | 2.45 | 2.45 |  |  |  |  | 201803.29 | UNSC | 163661701 | MIWUK 1701 | MIWUK 170110600 | 161 | 13.2797 | 2690 | 0.10996 | 0.000683 | 2662 | 0.013593 | 1 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785935 | E.5014723.02 | 117496177 | 35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 | 12936 | 0 | 0 | 0 |  | 2018-61433 | 13305.6 | 2.52 | 2730940 | 2019-35884 | 0 | 0 | 12936 | 12936 | 2.45 | 4704000 | 2020-20280
35115047 |  |  |  | 2.25 | 2.25 |  |  |  |  | 179037.82 | PEND | 163661701 | MIWUK 1701 | MIWUK 170110600 | 161 | 13.2797 | 2690 | 0.10996 | 0.000683 | 2662 | 0.012483 | 1 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785936 | E.5014723.03 | 117496281 | 35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 | 11880 | 0 | 0 | 0 |  | 2018-61433 | 13305.6 | 2.52 | 2730940 | 2019-35884 | 0 | 0 | 11880 | 11880 | 2.25 | 4320000 | 2019-57241
35115048 |  |  |  | 2.15 | 2.15 |  |  |  |  | 32839.33 | ESTS | 163661701 | MIWUK 1701 | MIWUK 170110600 | 161 | 13.2797 | 2690 | 0.10996 | 0.000683 | 2662 | 0.011928 | 1 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785937 | E.5014723.04 | 117497751 | 35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 | 11352 | 0 | 0 | 0 |  | 2018-61433 | 13305.6 | 2.52 | 2730940 | 2019-35884 | 0 | 0 | 11352 | 11352 | 2.15 | 4128000 | 2019-65924
35115049 |  |  |  | 2.25 | 2.25 |  |  |  |  | 220122.6 | ESTS | 163661701 | MIWUK 1701 | MIWUK 170110600 | 161 | 13.2797 | 2690 | 0.10996 | 0.000683 | 2662 | 0.012483 | 1 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785958 | E.5014723.05 | 117497752 | 35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 | 11880 | 0 | 0 | 0 |  | 2018-61433 | 13305.6 | 2.52 | 2730940 | 2019-35884 | 0 | 0 | 11880 | 11880 | 2.25 | 4320000
35052736 |  |  |  | 9.5 | 9.5 |  |  |  |  | 21435.46 | UNSE | 163661701 | MIWUK 1701 | MIWUK 170111800 | 116 | 9.5248 | 1887 | 1.3764 | 0.011866 | 1561 | 0.91979 | 139 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5784645 | E.5015037.01 | 114708583 | 35052736 | CWSP - MIWUK 1701 LR11800 | 50160 | 0 | 0 | 0 |  | 2018-59741 | 50160 | 9.5 | 10492800 |  |  |  |  | 0 | 0
35052822 |  |  |  | 11.8 | 11.8 |  |  |  |  | 566.77 | UNSE | 163661701 | MIWUK 1701 | MIWUK 17018050 | 137 | 12.1121 | 1569 | 3.3307 | 0.024311 | 1454 | #DIV/0! | 45 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5530178 |  | 114637561 | 35052822 | CWSP - MIWUK 1701 - LR 8050 | 0 | 0 | 0 | 0
35116385 |  |  |  | 1.4 | 1.4 |  |  |  |  | 76706.29 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.039853 | 12 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785968 | E.5014733.04 | 117604609 | 35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 | 7376 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8005 | 8005 | 1.5161 | 2910909.0909 | 2019-53233 | 2020-50944 | 0 | 0 | 7376 | 7376 | 1.397 | 2814642 | 3489624 | 381.5946
35116388 |  |  |  | 2.48 | 2.48 |  |  |  |  | 405329.31 | ESTS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.070596 | 12 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785969 | E.5014733.05 | 117604672 | 35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 | 13109 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 11220 | 11220 | 2.125 | 4080000 | 2019-66576 | 2020-47446 | 0 | 0 | 13109 | 13109 | 2.4828 | 4435363 | 6131696 | 338.3449
35116389 |  |  |  | 1.89 | 1.89 |  |  |  |  | 78397.35 | ESTS | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.053801 | 12 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785970 | E.5014733.06 | 117604676 | 35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 | 9970 | 0 | 0 | 0 |  | 2018-59382 | 62304 | 11.8 | 12757300 | 2019-35887 | 0 | 0 | 9970 | 9970 | 1.8883 | 3625454.5455 | 2020-01521
35052737 |  |  |  | 1.587 | 1.587 |  |  |  |  | 83049.6 | PEND | 163661701 | MIWUK 1701 | MIWUK 1701953336 | 132 | 11.8581 | 2267 | 0.50381 | 0.0038168 | 2336 | 0.045176 | 12 | Tier 3 | PRE | LONG BARN | Tuolumne | Yosemite | Central Valley | 5785238 | E.5014733.01 | 114675474 | 35052737 | CWSP-MIWUK 1701-LR8060-PH 1.1 | 8378 | 0 | 0 | 0 |  | 2018-59382 | 10401.6 | 1.97 | 2126216 | 2019-35887 | 0 | 0 | 8605 | 8605 | 1.6297 | 3129090.9091 | 2019-63683 | 2020-27366 | 0 | 0 | 8378 | 8378 | 1.5867 | 2060222 | 2768676 | 245.9086
35115057 |  |  |  | 2.59 | 2.59 |  |  |  |  | 203922.71 | UNSC | 163661701 | MIWUK 1701 | MIWUK 1701CB | 187 | 16.2494 | 2353 | 0.55914 | 0.0029901 | 2128 | 0.059712 | 2 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785989 | E.5015427.05 | 117489824 | 35115057 | CWSP-MIWUK 1701-OCB-PH 2.5 | 13653 | 0 | 0 | 0 |  | 2018-83316 | 10348.8 | 1.96 | 2137840 | 2019-35903 | 0 | 0 | 10875 | 10875 | 2.0597 | 3954545.4545 | 2020-32401 | 2020-59181 | 0 | 0 | 13653 | 13653 | 2.5858 | 2995054 | 3865227 | 219.3697
35116441 |  |  |  | 2.28 | 2.28 |  |  |  |  | 47451.97 | ESTS | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.013766 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785981 | E.5014776.02 | 117605164 | 35116441 | CWSP-MIWUK 1702-LR38218-PH1.2 | 12015 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 12015 | 12015 | 2.2756 | 4369090.9091 | 2019-65015
35173959 |  |  |  | 2.19 | 2.19 |  |  |  |  | 0 | ADER | 163661702 | MIWUK 1702 | MIWUK 170238218 | 132 | 10.9416 | 2678 | 0.098599 | 0.00074696 | 2665 | 0.013222 | 32 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785985 |  | 118940594 | 35173959 | CWSP-MIWUK 1702-LR38218-PH1.6 | 11546 | 0 | 0 | 0 |  | 2018-60918 | 9768 | 1.85 | 1963016 | 2019-35889 | 0 | 0 | 4261 | 4261 | 0.80701 | 1549454.5455 | 2020-29263 | 2020-17350 | 0 | 0 | 11546 | 11546 | 2.1867 | 4023891 | 5180025 | 348.5095
35116397 |  |  |  | 2.01 | 2.01 |  |  |  |  | 57175.58 | PEND | 163661702 | MIWUK 1702 | MIWUK 17028090 | 53 | 4.0407 | 2829 | 0.011216 | 0.00021162 | 2848 | 0.0037381 | 102 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785930 | E.5014722.03 | 117604668 | 35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 | 10855 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 10855 | 10855 | 2.0559 | 3947272.7273 | 2019-64385 | 2020-58976 | 0 | 0 | 10614 | 10614 | 2.0102 | 3639682 | 5174348 | 342.9133
35116398 |  |  |  | 1.84 | 1.84 |  |  |  |  | 39375.89 | ESTS | 163661702 | MIWUK 1702 | MIWUK 17028090 | 53 | 4.0407 | 2829 | 0.011216 | 0.00021162 | 2848 | 0.0034219 | 102 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785931 | E.5014722.04 | 117604615 | 35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 | 9730 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 9730 | 9730 | 1.8428 | 3538181.8182 | 2020-62924
35116399 |  |  |  | 1.83 | 1.83 |  |  |  |  | 194596.61 | UNSC | 163661702 | MIWUK 1702 | MIWUK 17028090 | 53 | 4.0407 | 2829 | 0.011216 | 0.00021162 | 2848 | 0.0034033 | 102 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785932 | E.5014722.05 | 117604337 | 35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 | 9185 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 9185 | 9185 | 1.7396 | 3340000
35116440 |  |  |  | 1.89 | 1.89 |  |  |  |  | 67132.58 | ADER | 163661702 | MIWUK 1702 | MIWUK 17028090 | 53 | 4.0407 | 2829 | 0.011216 | 0.00021162 | 2848 | 0.0035149 | 102 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785933 | E.5014722.06 | 117604512 | 35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 | 9980 | 0 | 0 | 0 |  | 2018-63127 | 10296 | 1.95 | 2134266 | 2019-35902 | 0 | 0 | 9980 | 9980 | 1.8902 | 3629090.9091 | 2019-70479
35052823 |  |  |  | 1.53 | 1.53 |  |  |  |  | 92406.22 | UNSC | 163661702 | MIWUK 1702 | MIWUK 17028130 | 123 | 9.9199 | 2217 | 0.5855 | 0.0047602 | 2080 | 0.060504 | 83 | Tier 2 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5791727 | E.5014730.01 | 114678857 | 35052823 | CWSP-MIWUK 1702-LR6018-PH 1.1 | 8100 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 7835 | 7835 | 1.4839 | 2849090.9091 | 2020-37595 | 2020-49472 | 0 | 0 | 8100 | 8100 | 1.5341 | 4349460 | 6133206 | 536.9704
35192305 |  |  |  | 9.88 | 9.88 |  |  |  |  | 1529.29 | UNSE | 163661702 | MIWUK 1702 | MIWUK 17028130 | 123 | 9.9199 | 2217 | 0.5855 | 0.0047602 | 2080 | 0.39071 | 83 | Tier 3 | ECOP | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5792099 | E.5034408.01 | 119556333 | 35192305 | ECOP - MIWUK 1702 - H01-LR8130 | 52166 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35052824 |  |  |  | 11.6 | 11.6 |  |  |  |  | 203.59 | UNSE | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.22836 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5786460 | E.5014725.01 | 114697826 | 35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 | 61248 | 0 | 0 | 0
35116803 |  |  |  | 2.29 | 2.29 |  |  |  |  | 159586.79 | PEND | 163661702 | MIWUK 1702 | MIWUK 1702823548 | 231 | 19.7318 | 2411 | 0.57976 | 0.0025098 | 2266 | 0.045081 | 23 | Tier 3 | PRE | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5785964 | E.5014730.05 | 117605268 | 35116803 | CWSP-MIWUK 1702-LR 6018-PH1.5 | 12028 | 0 | 0 | 0 |  | 2018-55685 | 9398.4 | 1.78 | 1921966 | 2019-35900 | 0 | 0 | 10795 | 10795 | 2.0445 | 3925454.5455 | 2020-51473 | 2020-64943 | 0 | 0 | 12028 | 12028 | 2.278 | 3402146 | 5119550 | 282.8522
35191380 |  |  |  | 1.01 | 1.01 |  |  |  |  | 1529.29 | UNSE | 163661702 | MIWUK 1702 | MIWUK 17029270 | 68 | 5.8239 | 2745 | 0.03101 | 0.00045602 | 2714 | 0.0036031 | 206 | Tier 3 | ECOP | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5541306 | E.5034356.01 | 119518524 | 35191380 | ECOP - MIWUK 1702 - H02-LR9270 | 5381 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35191381 |  |  |  | 1.2 | 1.2 |  |  |  |  | 1529.29 | UNSE | 163661702 | MIWUK 1702 | MIWUK 17029270 | 68 | 5.8239 | 2745 | 0.03101 | 0.00045602 | 2714 | 0.0042809 | 206 | Tier 3 | ECOP | TWAIN HARTE | Tuolumne | Yosemite | Central Valley | 5541307 | E.5034356.01 | 119518525 | 35191381 | ECOP - MIWUK 1702 - H03-LR9270 | 6461 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35174470 |  |  |  | 2.6 | 2.6 |  |  |  |  | 8244.43 | UNSE | 42571102 | MOLINO 1102 | MOLINO 1102318 | 228 | 19.3375 | 1669 | 4.5821 | 0.020097 | 1688 | 0.4322 | 39 | Tier 3 | ECOP | OCCIDENTAL | Sonoma | Sonoma | Northern | 5790008 | E.5033908.01 | 118912761 | 35174470 | ECOP - MOLINO 1102 - H01 - LR318 | 12700 | 1388 | 0 | 0 | 2020-50404 | 2020-50488 | 14097.6 | 2.67 | 3468300 | 2020-09-24 | 0 | 1372.8 | 12724.8 | 14097.6 | 2.67 | 5126400
35192293 |  |  |  | 8.13 | 8.13 |  |  |  |  | 1529.29 | UNSE | 42571102 | MOLINO 1102 | MOLINO 1102396 | 182 | 16.102 | 802 | 17.099 | 0.093951 | 1129 | 5.7844 | 161 | Tier 3 | ECOP | OCCIDENTAL | Sonoma | Sonoma | Northern | 5792100 | E.5034409.01 | 119556357 | 35192293 | ECOP - MOLINO 1102 - H03-LR396 - PH 1 | 42926.4 | 0 | 0 | 0 | [5 empty] | -
35192294 |  |  |  | 8 | 8 |  |  |  |  | 1529.29 | UNSE | 42571102 | MOLINO 1102 | MOLINO 1102396 | 182 | 16.102 | 802 | 17.099 | 0.093951 | 1129 | 5.7351 | 161 | Tier 3 | ECOP | OCCIDENTAL | Sonoma | Sonoma | Northern | 5792101 | E.5034410.01 | 119556373 | 35192294 | ECOP - MOLINO 1102 - H03-LR396 - PH 2 | 44993 | 481 | 238 | 0 | [5 empty] | -
35051485 |  |  |  |  | 0 |  |  |  |  | 9929.56 | UNSE | 42811111 | MONTE RIO 1111 | MONTE RIO 11111701 | 18 | 1.3978 | 2818 | 0.0042401 | 0.00023556 | 2819 | 0 | 276 | Tier 3 | PRE | CAZADERO | Sonoma | Sonoma | Northern | 5530175 |  | 114779853 | 35051485 | CWSP - MONTE RIO 1111 - 1701 | 52852.8 | 0 | 0 | 0 | 2018-73854 | 2018-73855 | 52852.8 | 10.01 | 11106500 |  |  |  |  | 0 | 0
35191313 |  |  |  | 1.25 | 1.25 |  |  |  |  | 2569 | UNSE | 42811111 | MONTE RIO 1111 | MONTE RIO 111164758 | 97 | 10.4662 | 2014 | 0.8528 | 0.0087918 | 2270 | 0.068241 | 101 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5541301 | E.5034350.01 | 119518128 | 35191313 | ECOP - MONTE RIO 1111 - H01-LR64758 | 6574 | 0 | 0 | 0 | 2020-62191 | 2020-62260 | 6600 | 1.25 | 1423418 | -
35067619 |  |  |  | 6.4 | 6.4 |  |  |  |  | 210.2 | UNSE | 42811112 | MONTE RIO 1112 | MONTE RIO 1112120 | 67 | 6.4178 | 1517 | 1.788 | 0.026687 | 1989 | 1.1947 | 54 | Tier 3 | PRE | MONTE RIO | Sonoma | Sonoma | Northern | 5782761 | E.5015480.01 | 115098949 | 35067619 | CWSP – MONTE RIO 1112 – LR 120 | 33792 | 0 | 0 | 0 |  | 2018-98601 | 33792 | 6.4 | 6866200
35061041 |  |  |  | 5.8 | 5.8 |  |  |  |  | 375.58 | UNSE | 42811112 | MONTE RIO 1112 | MONTE RIO 111215401 | 11 | 0.86276 | 2698 | 0.0070561 | 0.00064146 | 2694 | 0.031782 | 204 | Tier 3 | PRE | MONTE RIO | Sonoma | Sonoma | Northern | 5782762 | E.5015479.01 | 115099028 | 35061041 | CWSP – MONTE RIO 1112 – TS 15401 | 30624 | 0 | 0 | 0 |  | 2018-84954 | 30624 | 5.8 | 6183400
35176549 |  |  |  | 1 | 1 |  |  |  |  | 7406.84 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 1113180 | 28 | 1.9628 | 2019 | 0.24298 | 0.0086779 | 2293 | 0.082942 | 142 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5539421 | E.5033909.01 | 118912762 | 35176549 | ECOP - MONTE RIO 1113 - H07 - LR180 | 5117 | 0 | 0 | 0 | 2020-48022 | 2020-48307 | 5121 | 0.96989 | 1334148 | 2020-09-24 | 0 | 0 | 5280 | 5280 | 1 | 1920000
35174471 |  |  |  | 1 | 1 |  |  |  |  | 0 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 1113180 | 28 | 1.9628 | 2019 | 0.24298 | 0.0086779 | 2293 | 0.082942 | 142 | Tier 3 | ECOP |  | Sonoma | Sonoma | Northern | 5539421 | E.9999990.01 | 13869444 | 35174471 | ECOP-MONTE RIO 1113-H07-LR180 | 5280 | 0 | 0 | 0 | [5 empty] | -
35192039 |  |  |  | 2.72 | 2.72 |  |  |  |  | 2310.68 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 1113320 | 29 | 2.7766 | 2061 | 0.22308 | 0.0076924 | 2339 | 0.14642 | 138 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5792080 | E.5034389.01 | 119554057 | 35192039 | ECOP - MONTE RIO 1113 - H04-LR320 | 14364 | 0 | 0 | 0 | 2020-56611 | 2020-56759 | 14364 | 2.7205 | 3048240 | -
35192040 |  |  |  | 1.82 | 1.82 |  |  |  |  | 2148.36 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 1113477 | 25 | 1.8313 | 2410 | 0.062875 | 0.002515 | 2513 | 0.041865 | 639 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5792084 | E.5034392.01 | 119554091 | 35192040 | ECOP - MONTE RIO 1113 - H08-LR477 | 9943 | 0 | 0 | 0 | [5 empty] | -
|  |  |  | 6.27 | 6.27 |  |  |  |  | #N/A | #N/A | 42811113 | MONTE RIO 1113 | MONTE RIO 1113524 | 76 | 6.2639 | 2286 | 0.2749 | 0.0036171 | 2467 | #DIV/0! | 17 | Tier 3 | PRE | GUERNEVILLE | Sonoma | North Coast | Northern | [5 empty] | 0 | 0 | 0 | 0
35051484 |  |  |  | 10.72 | 10.72 |  |  |  |  | 8742.15 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 11138299 | 13 | 1.2021 | 2514 | 0.02235 | 0.0017192 | 2537 | 0.13354 | 92 | Tier 3 | PRE | GUERNEVILLE | Sonoma | Sonoma | Northern | 5530175 |  | 114779852 | 35051484 | CWSP - MONTE RIO 1113 - 8299 | 56601.6 | 0 | 0 | 0 |  | 2018-73857 | 56601.6 | 10.72 | 11713900 | 2018-73856
35191311 |  |  |  | 1.2 | 1.2 |  |  |  |  | 1554.09 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 11138299 | 13 | 1.2021 | 2514 | 0.02235 | 0.0017192 | 2537 | 0.014948 | 92 | Tier 3 | ECOP | GUERNEVILLE | Sonoma | North Coast | Northern | 5541300 | E.5034349.01 | 119518125 | 35191311 | ECOP - MONTE RIO 1113 - H06-LR8299 | 6247 | 0 | 0 | 0 | [5 empty] | -
35050951 |  |  |  | 1.4 | 1.4 |  |  |  |  | 23799.23 | UNSE | 42811113 | MONTE RIO 1113 | MONTE RIO 1113CB | 49 | 4.5284 | 2477 | 0.098667 | 0.0020136 | 2702 | 0.020437 | 163 | Tier 3 | PRE | GUERNEVILLE | Sonoma | Sonoma | Northern | 5530175 |  | 114848376 | 35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE | 7392 | 0 | 0 | 0 |  | 2018-62087 | 7392 | 1.4 | 1540000
35191382 |  |  |  | 1.49 | 1.49 |  |  |  |  | 1529.29 | UNSE | 13801105 | MORAGA 1105 | MORAGA 1105CB | 121 | 5.7453 | 2619 | 0.13044 | 0.001078 | 2417 | 0.022665 | 234 | Tier 2 | ECOP | CANYON | Contra Costa | Diablo | Bay Area | 5541308 | E.5034358.01 | 119518526 | 35191382 | ECOP - MORAGA 1105 - H01-CB | 7867.2 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35029270 |  |  |  | 0.619 | 0.619 |  |  |  |  | 4262.79 | UNSE | 83242111 | MORGAN HILL 2111 | MORGAN HILL 2111XR398 | 341 | 37.7039 | 891 | 27.5412 | 0.080766 | 864 | 0.30294 | 995 | Tier 3 | WDDB | MORGAN HILL | Santa Clara | San Jose | Central Coast | 5530174 |  | 114352762 | 35029270 | MORGAN HILL 2111 RECOND 13-SPANS W TW | 3270 | 0 | 0 | 0 |  | 2018-20294 | 3270 | 0.61932 | 359700 |  |  |  |  | 0 | 0
35099603 |  |  |  | 0.895 | 0.895 |  |  |  |  | 0 | UNSE | 183011102 | MORRO BAY 1102 | MORRO BAY 1102W22 | 85 | 2.5943 | 3594 | 8.1495e-05 | 9.5877e-07 | 3323 | 1.8837e-05 | 1763 | Tier 3 | WDDB | SAN LUIS OBISPO | San Luis Obispo | Los Padres | Central Coast | 5530166 |  | 117211021 | 35099603 | MORRO BAY 1102 RECON 4728 FT W TW | 4728 | 0 | 0 | 0 |  | 2019-31175 | 4728 | 0.89545 | 780120 |  |  |  |  | 0 | 0
35191316 |  |  |  | 1.03 | 1.03 |  |  |  |  | 2763.86 | UNSE | 254421103 | OAKHURST 1103 | OAKHURST 110310190 | 61 | 8.4469 | 2508 | 0.10725 | 0.0017583 | 2355 | 0.0087624 | 123 | Tier 3 | ECOP | FISH CAMP | Mariposa | Yosemite | Central Valley | 5541302 | E.5034351.01 | 119518129 | 35191316 | ECOP - OAKHURST 1103 - H01-LR10190 | 11304 | 0 | 0 | 0 | [5 empty] | -
35192053 |  |  |  | 3.99 | 3.99 |  |  |  |  | 6282.17 | UNSE | 254421103 | OAKHURST 1103 | OAKHURST 11035120 | 19 | 6.1606 | 1975 | 0.18333 | 0.0096488 | 1809 | 0.088064 | 404 | Tier 3 | ECOP | FISH CAMP | Mariposa | Yosemite | Central Valley | 5792082 | E.5034391.01 | 119554059 | 35192053 | ECOP - OAKHURST 1103 - LR 5120 | 36121 | 0 | 0 | 10428 | [5 empty] | -
35192054 |  |  |  | 9.64 | 9.64 |  |  |  |  | 5786.9 | UNSE | 254421103 | OAKHURST 1103 | OAKHURST 11035470 | 104 | 9.3162 | 2158 | 0.61457 | 0.0059093 | 1973 | 0.42607 | 415 | Tier 3 | ECOP | FISH CAMP | Mariposa | Yosemite | Central Valley | 5792083 | E.5034364.01.01 | 119554090 | 35192054 | ECOP - OAKHURST 1103 - LR 5470 | 59746 | 0 | 0 | 0 | [5 empty] | -
31344017 |  |  |  | 0.172 | 0.172 |  |  |  |  | 1088.43 | UNSE | 42291101 | OLEMA 1101 | OLEMA 11011318 | 113 | 8.5105 | 2583 | 0.14661 | 0.0012974 | 2664 | 0.0019852 | 476 | Tier 3 | WDDB | POINT REYES STATION | Marin | North Bay | Bay Area | 5530168 |  | 113163271 | 31344017 | 2019 OLEMA 1101 HIGH SPLICE CNT_2 | 910 | 0 | 0 | 0 |  | 2017-104655 | 910 | 0.17235 | 91000 |  |  |  |  | 0 | 0
31344016 |  |  |  | 1.155 | 1.155 |  |  |  |  | 818.88 | UNSE | 42291101 | OLEMA 1101 | OLEMA 110150396 | 162 | 12.9443 | 2644 | 0.15566 | 0.00096084 | 2597 | 0.0093056 | 357 | Tier 3 | WDDB | INVERNESS | Marin | North Bay | Bay Area | 5530168 |  | 113163270 | 31344016 | 2019 OLEMA 1101 HIGH SPLICE CNT_1 | 6100 | 0 | 0 | 0 |  | 2017-121180 | 6100 | 1.1553 | 610000 |  |  |  |  | 0 | 0
31361489 |  |  |  | 1.61 | 1.61 |  |  |  |  | 870.75 | UNSE | 42291101 | OLEMA 1101 | OLEMA 110150396 | 162 | 12.9443 | 2644 | 0.15566 | 0.00096084 | 2597 | 0.012971 | 357 | Tier 3 | WDDB | INVERNESS | Marin | North Bay | Bay Area | 5530168 |  | 113745486 | 31361489 | OLEMA 1101 HIGH SPLICE COUNT 3 | 8501 | 0 | 0 | 0 |  | 2017-104662 | 8501 | 1.61 | 850100 |  |  |  |  | 0 | 0
35094514 |  |  |  | 1.28 | 1.28 |  |  |  |  | 63513.5 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.02671 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785244 | E.5014760.01 | 114655579 | 35094514 | CWSP-ORO FINO 1101-LR2022-PH 1.1 | 6756 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 6756 | 6756 | 1.2795 | 2456727.2727 | 2020-52006
35129616 |  |  |  | 1.62 | 1.62 |  |  |  |  | 42327.01 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.033805 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786672 | E.5014760.02 | 117873077 | 35129616 | CWSP-ORO FINO 1101-LR2022-PH 1.2 | 8577 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 8577 | 8577 | 1.6244 | 3118909.0909 | 2020-02408
35129617 |  |  |  | 1.95 | 1.95 |  |  |  |  | 108334.18 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.040692 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786673 | E.5014760.03 | 117873078 | 35129617 | CWSP-ORO FINO 1101-LR2022-PH 1.3 | 10289 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 10289 | 10289 | 1.9487 | 3741454.5455 | 2020-45318
35129618 |  |  |  | 1.99 | 1.99 |  |  |  |  | 28851.57 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.041526 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786674 | E.5014760.04 | 117873079 | 35129618 | CWSP-ORO FINO 1101-LR2022-PH 1.4 | 10520 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 10520 | 10520 | 1.9924 | 3825454.5455 | 2020-00249
35129619 |  |  |  | 1.66 | 1.66 |  |  |  |  | 79451.22 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.03464 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786675 | E.5014760.05 | 117873090 | 35129619 | CWSP-ORO FINO 1101-LR2022-PH 1.5 | 8750 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 8750 | 8750 | 1.6572 | 3181818.1818 | 2020-60535
35129640 |  |  |  | 1.62 | 1.62 |  |  |  |  | 14934.95 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.033805 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786676 | E.5014760.06 | 117873091 | 35129640 | CWSP-ORO FINO 1101-LR2022-PH 1.6 | 8536 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 8536 | 8536 | 1.6167 | 3104000 | 2020-00116
35129641 |  |  |  | 1.33 | 1.33 |  |  |  |  | 38061.16 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.027754 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786677 | E.5014760.07 | 117873092 | 35129641 | CWSP-ORO FINO 1101-LR2022-PH 1.7 | 7019 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 7019 | 7019 | 1.3294 | 2552363.6364 | 2020-00247
35129642 |  |  |  | 1.18 | 1.18 |  |  |  |  | 11185.13 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.024624 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786738 | E.5014760.08 | 117873093 | 35129642 | CWSP-ORO FINO 1101-LR2022-PH 1.8 | 6255 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 6255 | 6255 | 1.1847 | 2274545.4545 | 2020-02362
35094515 |  |  |  | 1.65 | 1.65 |  |  |  |  | 10467.66 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.034431 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785243 | E.5014755.01 | 114656547 | 35094515 | CWSP-ORO FINO 1101-LR2022-PH 2.1 | 8723 | 0 | 0 | 0 |  | 2018-47836 | 7619.04 | 1.443 | 1575750 | 2019-76198 | 0 | 0 | 8723 | 8723 | 1.6521 | 3172000 | 2020-58944
35129643 |  |  |  | 2.06 | 2.06 |  |  |  |  | 61974.22 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.042987 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786739 | E.5014755.02 | 117873094 | 35129643 | CWSP-ORO FINO 1101-LR2022-PH 2.2 | 10869 | 0 | 0 | 0 |  | 2018-47836 | 7619.04 | 1.443 | 1575750 | 2019-76198 | 0 | 0 | 10869 | 10869 | 2.0585 | 3952363.6364 | 2020-59750
35129644 |  |  |  | 0.99 | 0.99 |  |  |  |  | 50617.75 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.020659 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786740 | E.5014755.03 | 117873095 | 35129644 | CWSP-ORO FINO 1101-LR2022-PH 2.3 | 5214 | 0 | 0 | 0 |  | 2018-47836 | 7619.04 | 1.443 | 1575750 | 2019-76198 | 0 | 0 | 5214 | 5214 | 0.9875 | 1896000 | 2019-82268
35129645 |  |  |  | 1.21 | 1.21 |  |  |  |  | 26642.96 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.02525 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786741 | E.5014755.04 | 117873096 | 35129645 | CWSP-ORO FINO 1101-LR2022-PH 2.4 | 6367 | 0 | 0 | 0 |  | 2018-47836 | 7619.04 | 1.443 | 1575750 | 2019-76198 | 0 | 0 | 6367 | 6367 | 1.2059 | 2315272.7273 | 2020-47835
35129647 |  |  |  | 1.22 | 1.22 |  |  |  |  | 10240.32 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.025458 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786743 | E.5014755.06 | 117873098 | 35129647 | CWSP-ORO FINO 1101-LR2022-PH 2.6 | 6429 | 0 | 0 | 0 |  | 2018-47836 | 7619.04 | 1.443 | 1575750 | 2019-76198 | 0 | 0 | 6429 | 6429 | 1.2176 | 2337818.1818 | 2020-01101
35095164 |  |  |  | 1.94 | 1.94 |  |  |  |  | 183732.89 | UNSC | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.040483 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785239 | E.5015030.01 | 114723712 | 35095164 | CWSP-ORO FINO 1101-LR2022-PH 3.1 | 10157 | 0 | 0 | 0 |  | 2018-53504 | 7920 | 1.5 | 1750050 | 2019-76204 | 0 | 0 | 10157 | 10157 | 1.9237 | 3693454.5455 | 2020-54043
35129648 |  |  |  | 1.16 | 1.16 |  |  |  |  | 9517.94 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 11012022 | 207 | 16.0901 | 2420 | 0.50113 | 0.0024209 | 2547 | 0.024206 | 10 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786744 | E.5015030.02 | 117873099 | 35129648 | CWSP-ORO FINO 1101-LR2022-PH 3.2 | 6113 | 0 | 0 | 0 |  | 2018-53504 | 7920 | 1.5 | 1750050 | 2019-76204 | 0 | 0 | 6113 | 6113 | 1.1578 | 2222909.0909 | 2020-43084
35094516 |  |  |  | 1.95 | 1.95 |  |  |  |  | 50577.19 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.056745 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785242 | E.5014748.01 | 114668686 | 35094516 | CWSP-ORO FINO 1101-OCB-PH 1.1 | 10300 | 0 | 0 | 0 |  | 2018-47822 | 7233.6 | 1.37 | 1520311.11 | 2019-73903 | 0 | 0 | 10300 | 10300 | 1.9508 | 3745454.5455 | 2020-37077
35129602 |  |  |  | 1.08 | 1.08 |  |  |  |  | 23224.8 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.031428 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786745 | E.5014748.02 | 117873033 | 35129602 | CWSP-ORO FINO 1101-OCB-PH 1.2 | 5722 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 5722 | 5722 | 1.0837 | 2080727.2727 | 2020-02657
35129603 |  |  |  | 1.32 | 1.32 |  |  |  |  | 32635.8 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.038412 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786746 | E.5014748.03 | 117873034 | 35129603 | CWSP-ORO FINO 1101-OCB-PH 1.3 | 6970 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 6970 | 6970 | 1.3201 | 2534545.4545 | 2020-22793
35129604 |  |  |  | 1.45 | 1.45 |  |  |  |  | 23439.57 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.042195 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786747 | E.5014748.04 | 117873035 | 35129604 | CWSP-ORO FINO 1101-OCB-PH 1.4 | 7682 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 7682 | 7682 | 1.4549 | 2793454.5455 | 2020-52799
35129605 |  |  |  | 1.58 | 1.58 |  |  |  |  | 22443.37 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.045978 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786748 | E.5014748.05 | 117873036 | 35129605 | CWSP-ORO FINO 1101-OCB-PH 1.5 | 8342 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 8342 | 8342 | 1.5799 | 3033454.5455 | 2020-09940
35129606 |  |  |  | 0.99 | 0.99 |  |  |  |  | 27449.55 | UNSC | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.028809 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786749 | E.5014748.06 | 117873037 | 35129606 | CWSP-ORO FINO 1101-OCB-PH 1.6 | 5223 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 5223 | 5223 | 0.9892 | 1899272.7273 | 2020-22794
35129607 |  |  |  | 1.51 | 1.51 |  |  |  |  | 20213.73 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.043941 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786750 | E.5014748.07 | 117873038 | 35129607 | CWSP-ORO FINO 1101-OCB-PH 1.7 | 7972 | 0 | 0 | 0 |  | 2018-47846 | 7434.24 | 1.408 | 1546850 | 2019-76212 | 0 | 0 | 7972 | 7972 | 1.5098 | 2898909.0909 | 2020-11589
35094517 |  |  |  | 1.45 | 1.45 |  |  |  |  | 76159.51 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.042195 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785241 | E.5014747.01 | 114668689 | 35094517 | CWSP-ORO FINO 1101-OCB-PH 2.1 | 7634 | 0 | 0 | 0 |  | 2018-47848 | 7022.4 | 1.33 | 1469033.33 | 2019-76219 | 0 | 0 | 7634 | 7634 | 1.4458 | 2776000 | 2020-34187
35129608 |  |  |  | 1.47 | 1.47 |  |  |  |  | 36565.78 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.042777 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786751 | E.5014747.02 | 117873039 | 35129608 | CWSP-ORO FINO 1101-OCB-PH 2.2 | 7812 | 0 | 0 | 0 |  | 2018-47848 | 7022.4 | 1.33 | 1469033.33 | 2019-76219 | 0 | 0 | 7812 | 7812 | 1.4795 | 2840727.2727 | 2020-62009
35129609 |  |  |  | 1.07 | 1.07 |  |  |  |  | 83303.02 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.031137 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786752 | E.5014747.03 | 117873070 | 35129609 | CWSP-ORO FINO 1101-OCB-PH 2.3 | 5626 | 0 | 0 | 0 |  | 2020-60320 | 9247 | 1.7513 | 2090000 | 2019-76219 | 0 | 0 | 5626 | 5626 | 1.0655 | 2045818.1818 | 2020-26542
35129610 |  |  |  | 1.57 | 1.57 |  |  |  |  | 44843.82 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.045687 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786753 | E.5014747.04 | 117873071 | 35129610 | CWSP-ORO FINO 1101-OCB-PH 2.4 | 8284 | 0 | 0 | 0 |  | 2018-47848 | 7022.4 | 1.33 | 1469033.33 | 2019-76219 | 0 | 0 | 8284 | 8284 | 1.5689 | 3012363.6364 | 2020-44455
35129611 |  |  |  | 1.3 | 1.3 |  |  |  |  | 35412.67 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.03783 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786754 | E.5014747.05 | 117873072 | 35129611 | CWSP-ORO FINO 1101-OCB-PH 2.5 | 6878 | 0 | 0 | 0 |  | 2018-47848 | 7022.4 | 1.33 | 1469033.33 | 2019-76219 | 0 | 0 | 6878 | 6878 | 1.3027 | 2501090.9091 | 2020-34450
35129612 |  |  |  | 1.14 | 1.14 |  |  |  |  | 34708.06 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.033174 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786755 | E.5014747.06 | 117873073 | 35129612 | CWSP-ORO FINO 1101-OCB-PH 2.6 | 5997 | 0 | 0 | 0 |  | 2018-47848 | 7022.4 | 1.33 | 1469033.33 | 2019-76219 | 0 | 0 | 5997 | 5997 | 1.1358 | 2180727.2727 | 2020-44454
35094518 |  |  |  | 1.69 | 1.69 |  |  |  |  | 15245.06 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.049179 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785240 | E.5014746.01 | 114668862 | 35094518 | CWSP-ORO FINO 1101-OCB-PH 3.1 | 8931 | 0 | 0 | 0 |  | 2018-47850 | 9108 | 1.725 | 1880350 | 2019-76221 | 0 | 0 | 8931 | 8931 | 1.6915 | 3247636.3636 | 2020-61825
35129613 |  |  |  | 1.38 | 1.38 |  |  |  |  | 39699.39 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.040158 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786756 | E.5014746.02 | 117873074 | 35129613 | CWSP-ORO FINO 1101-OCB-PH 3.2 | 7303 | 0 | 0 | 0 |  | 2018-47850 | 9108 | 1.725 | 1880350 | 2019-76221 | 0 | 0 | 7303 | 7303 | 1.3831 | 2655636.3636 | 2020-60446
35129614 |  |  |  | 1.68 | 1.68 |  |  |  |  | 39247.66 | PEND | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.048888 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786757 | E.5014746.03 | 117873075 | 35129614 | CWSP-ORO FINO 1101-OCB-PH 3.3 | 8896 | 0 | 0 | 0 |  | 2018-47850 | 9108 | 1.725 | 1880350 | 2019-76221 | 0 | 0 | 8896 | 8896 | 1.6848 | 3234909.0909 | 2020-55903
35129615 |  |  |  | 2.08 | 2.08 |  |  |  |  | 79143.74 | ESTS | 103031101 | ORO FINO 1101 | ORO FINO 1101CB | 271 | 22.3304 | 2289 | 0.96987 | 0.0035789 | 2257 | 0.060528 | 3 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786758 | E.5014746.04 | 117873076 | 35129615 | CWSP-ORO FINO 1101-OCB-PH 3.4 | 10990 | 0 | 0 | 0 |  | 2018-47850 | 9108 | 1.725 | 1880350 | 2019-76221 | 0 | 0 | 10990 | 10990 | 2.0814 | 3996363.6364
35117007 |  |  |  | 1.59 | 1.59 |  |  |  |  | 14527.91 | ESTS | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.029978 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786327 | E.5014724.01 | 114708276 | 35117007 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.1 | 8402 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 8402 | 8402 | 1.5913 | 3055272.7273 | 2020-54146
35129649 |  |  |  | 1.63 | 1.63 |  |  |  |  | 15142.49 | ESTS | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.030732 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786775 | E.5014724.02 | 117873100 | 35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 | 8596 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 8596 | 8596 | 1.628 | 3125818.1818 | 2020-21600
35129650 |  |  |  | 1.38 | 1.38 |  |  |  |  | 96923.39 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.026019 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786776 | E.5014724.03 | 117873101 | 35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 | 7291 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 7291 | 7291 | 1.3809 | 2651272.7273 | 2020-41167
35129652 |  |  |  | 1.04 | 1.04 |  |  |  |  | 81871.8 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.019608 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786777 | E.5014724.04 | 117873102 | 35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 | 5493 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 5493 | 5493 | 1.0403 | 1997454.5455
35129653 |  |  |  | 1.26 | 1.26 |  |  |  |  | 1273.65 | ESTS | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.023756 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786778 | E.5014724.05 | 117873103 | 35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 | 6678 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 6678 | 6678 | 1.2648 | 2428363.6364
35129654 |  |  |  | 1.99 | 1.99 |  |  |  |  | 119094.28 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.03752 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786779 | E.5014724.06 | 117873104 | 35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 | 10499 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 10499 | 10499 | 1.9884 | 3817818.1818 | 2020-52958
35129655 |  |  |  | 1.76 | 1.76 |  |  |  |  | 17263.2 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.033183 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786780 | E.5014724.07 | 117873105 | 35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 | 9273 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 9273 | 9273 | 1.7563 | 3372000 | 2020-29003
35129656 |  |  |  | 1.59 | 1.59 |  |  |  |  | 452.07 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.029978 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786781 | E.5014724.08 | 117873106 | 35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 | 8397 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 8397 | 8397 | 1.5903 | 3053454.5455 | 2020-50884
35129657 |  |  |  | 1.42 | 1.42 |  |  |  |  | 9011.91 | ESTS | 103031102 | ORO FINO 1102 | ORO FINO 11022090 | 183 | 14.7459 | 2440 | 0.41496 | 0.0022675 | 2438 | 0.026773 | 72 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786782 | E.5014724.09 | 117873107 | 35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 | 7516 | 0 | 0 | 0 |  | 2018-62075 | 7972.8 | 1.51 | 1624822.22 | 2019-76266 | 0 | 0 | 7516 | 7516 | 1.4235 | 2733090.9091 | 2020-34810
35094519 |  |  |  | 1.82 | 1.82 |  |  |  |  | 146803.5 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.14241 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785223 | E.5014721.01 | 114708278 | 35094519 | CWSP - ORO FINO 1102 - LR2560 PH 1.1 | 9589 | 0 | 0 | 0 |  | 2018-67838 | 8162.88 | 1.546 | 1646520 | 2019-76226 | 0 | 0 | 9589 | 9589 | 1.8161 | 3486909.0909 | 2019-81463
35129304 |  |  |  | 1.79 | 1.79 |  |  |  |  | 88564.72 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.14006 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786759 | E.5014721.02 | 117872785 | 35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 | 9428 | 0 | 0 | 0 |  | 2018-67838 | 8162.88 | 1.546 | 1646520 | 2019-76226 | 0 | 0 | 9428 | 9428 | 1.7856 | 3428363.6364
35129305 |  |  |  | 0.83 | 0.83 |  |  |  |  | 92325.02 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.064943 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786760 | E.5014721.03 | 117872786 | 35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 | 2947 | 0 | 0 | 0 |  | 2018-67838 | 8162.88 | 1.546 | 1646520 | 2019-76226 | 0 | 0 | 4373 | 4373 | 0.82822 | 1590181.8182 | 2020-33978 | 2020-51195 | 0 | 0 | 2947 | 2947 | 0.55814 | 1195101 | 1594611 | 405.5314
35129306 |  |  |  | 1.47 | 1.47 |  |  |  |  | 39970.96 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.11502 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786761 | E.5014721.04 | 117872787 | 35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 | 7772 | 0 | 0 | 0 |  | 2018-67838 | 8162.88 | 1.546 | 1646520 | 2019-76226 | 0 | 0 | 7772 | 7772 | 1.472 | 2826181.8182 | 2020-60187
35129307 |  |  |  | 1.77 | 1.77 |  |  |  |  | 321554.53 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.13849 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786762 | E.5014721.05 | 117872788 | 35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 | 8419 | 0 | 0 | 0 |  | 2018-67838 | 8162.88 | 1.546 | 1646520 | 2019-76226 | 0 | 0 | 9325 | 9325 | 1.7661 | 3390909.0909 | 2020-36267 | 2020-51201 | 0 | 0 | 8419 | 8419 | 1.5945 | 2537383 | 3319922 | 301.3877
35095160 |  |  |  | 1.59 | 1.59 |  |  |  |  | 42254.02 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.12441 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785224 | E.5014720.01 | 114708381 | 35095160 | CWSP - ORO FINO 1102 - LR2560 PH 2.1 | 8398 | 0 | 0 | 0 |  | 2018-67940 | 9472.32 | 1.794 | 1899860 | 2019-76255 | 0 | 0 | 8398 | 8398 | 1.5905 | 3053818.1818 | 2020-03703
35129308 |  |  |  | 1.66 | 1.66 |  |  |  |  | 36735.16 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.12989 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786763 | E.5014720.02 | 117873010 | 35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 | 8778 | 0 | 0 | 0 |  | 2018-67940 | 9472.32 | 1.794 | 1899860 | 2019-76255 | 0 | 0 | 8778 | 8778 | 1.6625 | 3192000 | 2020-02029
35129309 |  |  |  | 1.69 | 1.69 |  |  |  |  | 35031.78 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.13223 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786764 | E.5014720.03 | 117873011 | 35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 | 8902 | 0 | 0 | 0 |  | 2018-67940 | 9472.32 | 1.794 | 1899860 | 2019-76255 | 0 | 0 | 8902 | 8902 | 1.686 | 3237090.9091 | 2020-07233
35129310 |  |  |  | 1.91 | 1.91 |  |  |  |  | 43500.71 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.14945 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786765 | E.5014720.04 | 117873012 | 35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 | 10718 | 0 | 0 | 0 |  | 2018-67940 | 9472.32 | 1.794 | 1899860 | 2019-76255 | 0 | 0 | 10718 | 10718 | 2.0299 | 3897454.5455 | 2020-52952
35129311 |  |  |  | 1.99 | 1.99 |  |  |  |  | 48131.89 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 11022560 | 179 | 16.7269 | 1921 | 1.9534 | 0.010913 | 1829 | 0.15571 | 61 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786766 | E.5014720.05 | 117873013 | 35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 | 10500 | 0 | 0 | 0 |  | 2018-67940 | 9472.32 | 1.794 | 1899860 | 2019-76255 | 0 | 0 | 10500 | 10500 | 1.9886 | 3818181.8182 | 2020-52615
35095161 |  |  |  | 0.71 | 0.71 |  |  |  |  | 101025.41 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0020325 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785225 | E.5014719.01 | 114708383 | 35095161 | CWSP-ORO FINO 1102-LR76008-PH1.1 | 3757 | 0 | 0 | 0 |  | 2018-71370 | 9271.68 | 1.756 | 1884880 | 2019-76257 | 0 | 0 | 3757 | 3757 | 0.71155 | 1366181.8182 | 2020-02250 | [10 empty] | 2020-62992
35129434 |  |  |  | 2.02 | 2.02 |  |  |  |  | 167840.28 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0057827 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786767 | E.5014719.02 | 117873015 | 35129434 | CWSP-ORO FINO 1102-LR76008-PH1.2 | 10670 | 0 | 0 | 0 |  | 2018-71370 | 9271.68 | 1.756 | 1884880 | 2019-76257 | 0 | 0 | 10670 | 10670 | 2.0208 | 3880000 | 2020-01696
35129435 |  |  |  | 2.04 | 2.04 |  |  |  |  | 116786.95 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.00584 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786768 | E.5014719.03 | 117873016 | 35129435 | CWSP-ORO FINO 1102-LR76008-PH1.3 | 10796 | 0 | 0 | 0 |  | 2018-71370 | 9271.68 | 1.756 | 1884880 | 2019-76257 | 0 | 0 | 10796 | 10796 | 2.0447 | 3925818.1818 | 2020-55835
35129436 |  |  |  | 1.93 | 1.93 |  |  |  |  | 110481.57 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0055251 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786769 | E.5014719.04 | 117873017 | 35129436 | CWSP-ORO FINO 1102-LR76008-PH1.4 | 10179 | 0 | 0 | 0 |  | 2018-71370 | 9271.68 | 1.756 | 1884880 | 2019-76257 | 0 | 0 | 10179 | 10179 | 1.9278 | 3701454.5455 | 2019-79838
35129437 |  |  |  | 2.03 | 2.03 |  |  |  |  | 115211.85 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0058113 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786770 | E.5014719.05 | 117873018 | 35129437 | CWSP-ORO FINO 1102-LR76008-PH1.5 | 10708 | 0 | 0 | 0 |  | 2018-71370 | 9271.68 | 1.756 | 1884880 | 2019-76257 | 0 | 0 | 10708 | 10708 | 2.028 | 3893818.1818 | 2020-42700
35095162 |  |  |  | 1.21 | 1.21 |  |  |  |  | 143462.18 | ADER | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0034639 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5785226 | E.5014718.01 | 114708386 | 35095162 | CWSP-ORO FINO 1102-LR76008-PH2.1 | 6398 | 0 | 0 | 0 |  | 2018-71377 | 7751.04 | 1.468 | 1591420 | 2019-76261 | 0 | 0 | 6398 | 6398 | 1.2117 | 2326545.4545 | 2020-63881 | [10 empty] | 2020-62964
35129438 |  |  |  | 1.73 | 1.73 |  |  |  |  | 139239.59 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0049525 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786771 | E.5014718.02 | 117873019 | 35129438 | CWSP-ORO FINO 1102-LR76008-PH2.2 | 9150 | 0 | 0 | 0 |  | 2018-71377 | 7751.04 | 1.468 | 1591420 | 2019-76261 | 0 | 0 | 9150 | 9150 | 1.733 | 3327272.7273 | 2020-04474
35129439 |  |  |  | 1.85 | 1.85 |  |  |  |  | 123786.74 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0052961 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786772 | E.5014718.03 | 117873030 | 35129439 | CWSP-ORO FINO 1102-LR76008-PH2.3 | 9792 | 0 | 0 | 0 |  | 2018-71377 | 7751.04 | 1.468 | 1591420 | 2019-76261 | 0 | 0 | 9792 | 9792 | 1.8545 | 3560727.2727 | 2020-04294
35129600 |  |  |  | 1.15 | 1.15 |  |  |  |  | 101337.04 | PEND | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0032921 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786773 | E.5014718.04 | 117873031 | 35129600 | CWSP-ORO FINO 1102-LR76008-PH2.4 | 6062 | 0 | 0 | 0 |  | 2018-71377 | 7751.04 | 1.468 | 1591420 | 2019-76261 | 0 | 0 | 6062 | 6062 | 1.1481 | 2204363.6364 | 2020-01164
35129601 |  |  |  | 1.4 | 1.4 |  |  |  |  | 178856.25 | UNSC | 103031102 | ORO FINO 1102 | ORO FINO 110276008 | 170 | 15.9545 | 2763 | 0.068169 | 0.000401 | 2775 | 0.0040078 | 27 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5786774 | E.5014718.05 | 117873032 | 35129601 | CWSP-ORO FINO 1102-LR76008-PH2.5 | 7829 | 0 | 0 | 0 |  | 2018-71377 | 7751.04 | 1.468 | 1591420 | 2019-76261 | 0 | 0 | 7408 | 7408 | 1.403 | 2693818.1818 | 2020-00218 | 2020-60126 | 0 | 0 | 7829 | 7829 | 1.4828 | 2503748 | 3374618 | 319.8043
35060584 |  |  |  | 2.85 | 2.85 |  |  |  |  | 85170.22 | PEND | 182941101 | OTTER 1101 | OTTER 11017611 | 42 | 4.3928 | 2523 | 0.070701 | 0.0016834 | 2291 | 0.030733 | 1092 | Tier 2 | WDDB | CARMEL | Monterey | Central Coast | Central Coast | 5782594 | E.0000106.01 | 113743255 | 35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 | 15048 | 0 | 0 | 0 |  | 2017-106107 | 23884 | 4.5235 | 2649240 | N/A | 0 | 0 | 15048 | 15048 | 2.85 | 5472000 | 2020-07474
30977613 |  |  |  | 0.69 | 0.69 |  |  |  |  | 312568.75 | PEND | 182941102 | OTTER 1102 | OTTER 1102CB | 40 | 6.7693 | 1162 | 2.0626 | 0.051564 | 965 | 0.14086 | 1425 | Tier 3 | WDDB | BIG SUR | Monterey | Central Coast | Central Coast | 5530159 | P.06570 | 106691313 | 30977613 | R2 OTTER 1102 DETERIORTD CNDUCTR PHASE 3 | 3637 | 0 | 0 | 0 |  | 2017-106107 | 7961 | 1.5078 | 883080 | N/A |  |  |  | 0 | 0 |  | 2019-10148 | 2013-14402 | [9 empty] | 2020-54981
30977614 |  |  |  | 0.7 | 0.7 |  |  |  |  | 279118.97 | UNSC | 182941102 | OTTER 1102 | OTTER 1102CB | 40 | 6.7693 | 1162 | 2.0626 | 0.051564 | 965 | 0.1429 | 1425 | Tier 3 | WDDB | BIG SUR | Monterey | Central Coast | Central Coast | 5530159 | P.06571 | 106691314 | 30977614 | R2 OTTER 1102 DETERIORTD CNDUCTR PHASE 4 | 3681 | 0 | 0 | 0 |  | 2017-106107 | 7961 | 1.5078 | 883080 | N/A |  |  |  | 0 | 0 |  | 2019-10446 | 2013-14411
30977615 |  |  |  | 0.5 | 0.5 |  |  |  |  | 225770.28 | UNSC | 182941102 | OTTER 1102 | OTTER 1102CB | 40 | 6.7693 | 1162 | 2.0626 | 0.051564 | 965 | 0.10207 | 1425 | Tier 3 | WDDB | BIG SUR | Monterey | Central Coast | Central Coast | 5530159 | P.06572 | 106691315 | 30977615 | R2 OTTER 1102 DETERIORTD CNDUCTR PHASE 5 | 2664 | 0 | 0 | 0 |  | 2017-106107 | 7961 | 1.5078 | 883080 | N/A |  |  |  | 0 | 0 |  | 2019-08041 | 2013-14414
35185714 |  |  |  | 2.38 | 2.38 |  |  |  |  | 1774.77 | UNSE | 182941102 | OTTER 1102 | OTTER 1102LR2002 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 2728 | Tier 2 | WDDB | BIG SUR | Monterey | Central Coast | Central Coast | 5791660 | E.5034242.01 | 119231992 | 35185714 | WDDB - OTTER 1102 - LR 2002 | 12566.4 | 0 | 0 | 0 |  | 2020-50489 | 12566.4 | 2.38 | 4452594
35052327 |  |  |  |  | 0 |  |  |  |  | 2807.79 | UNSE | 102831101 | PARADISE 1101 | PARADISE 1101CB | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 328 | Tier 3 | PRE | PARADISE | Butte | North Valley | Northern | 5530169 |  | 114884306 | 35052327 | CWSP-PARADISE 1101-OCB | 12095 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0
35173387 |  |  |  | 3.38 | 3.38 |  |  |  |  | 0 | ESTS | 102831103 | PARADISE 1103 | PARADISE 110343008 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 1606 | Tier 3 | BUTTE | PARADISE | Butte | North Valley | Northern | 5786123 |  | 118935079 | 35173387 | CWSP - Paradise 1103 - Zone LR 43008 - Skyway Road (Phase 3) | 17846.4 | 0 | 0 | 0 |  | 2020-27418 | 17846.4 | 3.38 | 7174300 |  |  |  |  | 0 | 0
35060027 |  |  |  |  | 0 |  |  |  |  | 171.99 | UNSE | 102831104 | PARADISE 1104 | PARADISE 11041571 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 484 | Tier 3 | PRE | PARADISE | Butte | North Valley | Northern | 5530169 |  | 115079333 | 35060027 | CWSP-PARADISE 1104-TS 1571 | 5808 | 0 | 0 | 0 |  | 2018-82456 | 5808 | 1.1 | 1195800 |  |  |  |  | 0 | 0
35048613 |  |  |  | 11.4 | 11.4 |  |  |  |  | 11828.05 | UNSE | 102831106 | PARADISE 1106 | PARADISE 11062084 | 0 | 0 | 0 | 0 | 0 | #N/A | #DIV/0! | 14 | Tier 3 | PRE | MAGALIA | Butte | North Valley | Northern | 5530169 |  | 114819461 | 35048613 | CWSP - PARADISE 1106 - LR 2084 | 60192 | 0 | 0 | 0 | 2018-65289 | 2018-71031 | 60192 | 11.4 | 12717100 |  |  |  |  | 0 | 0
74022389 |  |  |  | 13.39 | 13.39 |  |  |  |  | 1940.74 | UNSE | 102831106 | PARADISE 1106 | PARADISE 11062234 | 0 | 0 | 0 | 0 | 0 | #N/A | #VALUE! | 28 | Tier 3 | PRE | PARADISE | Butte | North Valley | Northern | 5782907 | E.5015532.01 | 114742450 | 74022389 | CWSP - PARADISE 1106 - OCB & LR 2234 | - | - | - | -
74022614 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 102831105 | PARADISE 1105 | PARADISE 1106CB | 53 | 4.6443 | 2813 | 0.013022 | 0.0002457 | 2896 | #VALUE! | 219 | Tier 3 | BUTTE | PARADISE | Butte | North Valley | Northern | 5783285 | E.5015606.01 | 115340065 | 74022614 | CWSP - CAMP FIRE PADSE 1105 QUAIL RD | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
74022723 |  |  |  |  | 0 |  |  |  |  | 55789.49 | PEND | 102831106 | PARADISE 1106 | PARADISE 1106CB | 53 | 4.6443 | 2813 | 0.013022 | 0.0002457 | 2896 | #VALUE! | 219 | Tier 3 | BUTTE | PARADISE | Butte | North Valley | Northern | 5783287 | E.5015604.01 | 115342359 | 74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35114045 |  |  |  | 1.44 | 1.44 |  |  |  |  | 379842.09 | UNSC | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.047816 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786135 | E.5014745.07 | 117502843 | 35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 | 6917 | 0 | 685 | 0 |  | 2018-49722 | 10982.4 | 2.08 | 2269920 | 2019-35977 | 0 | 0 | 7259 | 7259 | 1.3748 | 2639636.3636 | 2019-75127 | 2020-55041 | 685 | 0 | 6917 | 7602 | 1.4398 | 3021946 | 3968570 | 397.5199
35095163 |  |  |  | 1.24 | 1.24 |  |  |  |  | 96410.41 | ADER | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.039425 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785227 | E.5014742.01 | 114708366 | 35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 | 6559 | 0 | 0 | 0 |  | 2020-58296 | 58608 | 11.1 | 2806785 | 2019-35972 | 0 | 0 | 6559 | 6559 | 1.2422 | 2385090.9091 | 2020-00360
35114046 |  |  |  | 1.23 | 1.23 |  |  |  |  | 146097.54 | ESTS | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.039107 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785996 | E.5014742.02 | 117499462 | 35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 | 6113 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 6113 | 6113 | 1.1578 | 2222909.0909 | 2020-21513
35114050 |  |  |  | 1.4 | 1.4 |  |  |  |  | 251268.75 | UNSC | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.044512 | 20 | Tier 2 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785999 | E.5014742.05 | 117499593 | 35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 | 6564 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 7377 | 7377 | 1.3972 | 2682545.4545 | 2020-27470 | 2020-48710 | 0 | 0 | 6564 | 6564 | 1.2432 | 2981678 | 4089518 | 454.2471
35114052 |  |  |  | 0.81 | 0.81 |  |  |  |  | 111915.44 | UNSC | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.025753 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786136 | E.5014742.07 | 117502368 | 35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 | 4291 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 4399 | 4399 | 0.83314 | 1599636.3636 | 2019-80891 | 2020-55156 | 0 | 0 | 4291 | 4291 | 0.81269 | 2022612 | 2882815 | 471.3615
35114053 |  |  |  | 1.56 | 1.56 |  |  |  |  | 50546.18 | ADER | 163751102 | PINE GROVE 1102 | PINE GROVE 11021222 | 218 | 17.2598 | 2271 | 0.81905 | 0.0037571 | 2414 | 0.049599 | 20 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786137 | E.5014742.08 | 117502416 | 35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 | 8212 | 0 | 0 | 0 |  | 2018-54633 | 83964.72 | 1.59 | 1718171.43 | 2019-35972 | 0 | 0 | 8212 | 8212 | 1.5553 | 2986181.8182 | 2019-80903
35192043 |  |  |  | 7.682 | 7.682 |  |  |  |  | 4226.54 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 110213438 | 172 | 16.5438 | 2136 | 1.1008 | 0.0063999 | 2096 | 0.34246 | 49 | Tier 3 | ECOP | VOLCANO | Amador | Stockton | Central Valley | 5792066 | E.5034374.01 | 119553911 | 35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 - PH 1 | 39345 | 0 | 0 | 0 | 2020-56129 | 2020-56130 | 40560 | 7.6818 | 8449933 | - | 0 | 0 | 40560.96 | 40560.96 | 7.682 | 14749440
35192044 |  |  |  | 8.836 | 8.836 |  |  |  |  | 4594.15 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 110213438 | 172 | 16.5438 | 2136 | 1.1008 | 0.0063999 | 2096 | 0.39391 | 49 | Tier 3 | ECOP | VOLCANO | Amador | Stockton | Central Valley | 5792067 | E.5034375.01 | 119553912 | 35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 - PH 2 | 46653 | 0 | 0 | 0 | 2020-56131 | 2020-56132 | 46653 | 8.8358 | 9863973 | -
35192046 |  |  |  | 10.21 | 10.21 |  |  |  |  | 5019.02 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 11023172 | 448 | 37.6855 | 1592 | 10.4588 | 0.023346 | 2161 | 2.1309 | 80 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792072 | E.5034380.01.01 | 119553919 | 35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 - PH 1 | 42851 | 14770 | 0 | 0 | 2020-57401 | 2020-57402 | 53908.8 | 10.21 | 14064723 | -
35192047 |  |  |  | 7.133 | 7.133 |  |  |  |  | 5607.59 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 11023172 | 448 | 37.6855 | 1592 | 10.4588 | 0.023346 | 2161 | 1.3263 | 80 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792073 | E.5034381.01 | 119554050 | 35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 - PH 2 | 35983 | 0 | 0 | 0 | 2020-57403 | 2020-57404 | 377193.04 | 7.133 | 8274662 | -
35192048 |  |  |  | 10.21 | 10.21 |  |  |  |  | 5240.08 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 11023172 | 448 | 37.6855 | 1592 | 10.4588 | 0.023346 | 2161 | 1.8985 | 80 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792074 | E.5034382.01 | 119554051 | 35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 - PH 3 | 50517 | 0 | 0 | 0 | 2020-57405 | 2020-57406 | 53908.8 | 10.21 | 10970526 | -
35192049 |  |  |  | 8.73 | 8.73 |  |  |  |  | 4822.85 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 11023172 | 448 | 37.6855 | 1592 | 10.4588 | 0.023346 | 2161 | 1.6233 | 80 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792075 | E.5034383.01 | 119554052 | 35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 - PH 4 | 46106 | 0 | 0 | 0 | 2020-57407 | 2020-57408 | 46094.4 | 8.73 | 10002143 | -
35174469 |  |  |  | 10.88 | 10.88 |  |  |  |  | 24788.7 | ESTS | 163751102 | PINE GROVE 1102 | PINE GROVE 110245292 | 132 | 10.7835 | 2447 | 0.29501 | 0.002235 | 2304 | 0.21241 | 5 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5790105 | E.5033910.01 | 118912983 | 35174469 | ECOP - PINE GROVE 1102 - H01 -LR45292 | 49190 | 6337 | 1373 | 0 | 2020-51138 | 2020-51139 | 55545.6 | 10.52 | 15552044 | 2020-09-22 | 0 | 6336 | 49209.6 | 55545.6 | 10.52 | 20198400
35192296 |  |  |  | 8.1 | 8.1 |  |  |  |  | 1686.54 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 110283098 | 104 | 7.9173 | 1668 | 2.0942 | 0.020137 | 1378 | 1.4355 | 167 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792102 | E.5034411.01 | 119556406 | 35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 | 42265 | 0 | 0 | 0 | [5 empty] | -
35192297 |  |  |  | 3.12 | 3.12 |  |  |  |  | 1686.54 | UNSE | 163751102 | PINE GROVE 1102 | PINE GROVE 1102CB | 136 | 10.8527 | 1920 | 1.4895 | 0.010952 | 1746 | 0.28691 | 388 | Tier 3 | ECOP | PINE GROVE | Amador | Stockton | Central Valley | 5792103 | E.5034412.01 | 119556415 | 35192297 | ECOP - PINE GROVE 1102 - H07-CB | 23461 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35056387 |  |  |  | 1.13 | 1.13 |  |  |  |  | 23995.76 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.045557 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782580 | E.5015426.01 | 114985530 | 35056387 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.1 | 5981 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 5981 | 5981 | 1.1328 | 2174909.0909
35167136 |  |  |  | 0.95 | 0.95 |  |  |  |  | 214.56 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.0383 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5539442 | E.5015426.02 | 118729469 | 35167136 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.2 | 5000 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 5000 | 5000 | 0.94697 | 1818181.8182
35167138 |  |  |  | 2.04 | 2.04 |  |  |  |  | 600 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.082244 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790011 | E.5015426.03 | 118729544 | 35167138 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.3 | 10745 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 10745 | 10745 | 2.035 | 3907272.7273
35168820 |  |  |  | 1.36 | 1.36 |  |  |  |  | 0 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.054829 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5539424 | E.5015426.04 | 118738238 | 35168820 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.4 | 7173 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 7173 | 7173 | 1.3585 | 2608363.6364
35168821 |  |  |  | 0.86 | 0.86 |  |  |  |  | 412.71 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.034671 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5539425 | E.5015426.05 | 118738363 | 35168821 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.5 | 4525 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 4525 | 4525 | 0.85701 | 1645454.5455 | 2020-55388
35168822 |  |  |  | 0.49 | 0.49 |  |  |  |  | 0 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.019755 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5539426 | E.5015426.06 | 118738366 | 35168822 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.6 | 2583 | 0 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 0 | 2583 | 2583 | 0.4892 | 939272.7273
35168823 |  |  |  | 0.31 | 0.31 |  |  |  |  | 220.94 | ESTS | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.018467 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5539427 | E.5015426.07 | 118738440 | 35168823 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 1.7 | 0 | 1615 | 0 | 0 |  | 2018-83825 | 5649.6 | 1.07 | 1163600 | 2020-08079 | 0 | 1615 | 0 | 1615 | 0.30587 | 1284659.0909
35056433 |  |  |  | 1.3 | 1.3 |  |  |  |  | 19774.61 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.05241 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782581 | E.5015425.01 | 114985551 | 35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.1 | 6883 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 6883 | 6883 | 1.3036 | 2502909.0909
35174993 |  |  |  | 0.79 | 0.79 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.031849 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790541 | E.5015425.02 | 118964445 | 35174993 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.2 | 4180 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 4180 | 4180 | 0.79167 | 1520000
35176209 |  |  |  | 0.81 | 0.81 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.032656 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790542 | E.5015425.03 | 118964446 | 35176209 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.3 | 4266 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 4266 | 4266 | 0.80795 | 1551272.7273
35176210 |  |  |  | 1.39 | 1.39 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.056039 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790543 | E.5015425.04 | 118964447 | 35176210 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.4 | 7339 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 7339 | 7339 | 1.39 | 2668727.2727
35176211 |  |  |  | 0.99 | 0.99 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.039912 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790544 | E.5015425.05 | 118964448 | 35176211 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.5 | 5211 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 5211 | 5211 | 0.98693 | 1894909.0909
35177109 |  |  |  | 0.66 | 0.66 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.026608 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5540306 | E.5015425.06 | 119021498 | 35177109 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.6 | 3493 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 3493 | 3493 | 0.66155 | 1270181.8182
35177110 |  |  |  | 1.42 | 1.42 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.057248 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5540307 | E.5015425.07 | 119021499 | 35177110 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.7 | 7507 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 7507 | 7507 | 1.4218 | 2729818.1818
35177111 |  |  |  | 1.67 | 1.67 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.067327 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5791027 | E.5015425.08 | 119021511 | 35177111 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2.8 | 8807 | 0 | 0 | 0 |  | 2018-83913 | 5940 | 1.125 | 1196525 | 2020-22211 | 0 | 0 | 8807 | 8807 | 1.668 | 3202545.4545
35056434 |  |  |  | 1.1 | 1.1 |  |  |  |  | 16104.86 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.044347 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782582 | E.5015424.01 | 114985557 | 35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.1 | 5827 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 5827 | 5827 | 1.1036 | 2118909.0909
35175843 |  |  |  | 0.407 | 0.407 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.016408 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790545 | E.5015424.02 | 118981826 | 35175843 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.2 | 2150 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 2150 | 2150 | 0.4072 | 781818.1818
35175844 |  |  |  | 0.885 | 0.885 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.035679 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790546 | E.5015424.03 | 118981828 | 35175844 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.3 | 4673 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 4673 | 4673 | 0.88504 | 1699272.7273
35175845 |  |  |  | 2.344 | 2.344 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.0945 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790547 | E.5015424.04 | 118981829 | 35175845 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.4 | 12378 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 12378 | 12378 | 2.3443 | 4501090.9091
35175846 |  |  |  | 1.89 | 1.89 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.076197 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790548 | E.5015424.05 | 118981890 | 35175846 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.5 | 9976 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 9976 | 9976 | 1.8894 | 3627636.3636
35177107 |  |  |  | 0.37 | 0.37 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.014917 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5540299 | E.5015424.06 | 119021512 | 35177107 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.6 | 1947 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 1947 | 1947 | 0.36875 | 708000
35177108 |  |  |  | 0.19 | 0.19 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.00766 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5540300 | E.5015424.07 | 119021513 | 35177108 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3.7 | 1022 | 0 | 0 | 0 |  | 2018-83959 | 6283.2 | 1.19 | 1268314.29 | 2020-22224 | 0 | 0 | 1022 | 1022 | 0.19356 | 371636.3636
35056435 |  |  |  | 1.86 | 1.86 |  |  |  |  | 16531.08 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.074987 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782583 | E.5015423.01 | 114985560 | 35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4.1 | 9808 | 0 | 0 | 0 |  | 2018-83984 | 9187.2 | 1.74 | 1837700 | 2020-22301 | 0 | 0 | 9808 | 9808 | 1.8576 | 3566545.4545
35175847 |  |  |  | 1.98 | 1.98 |  |  |  |  | 3490.18 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.079825 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790549 | E.5015423.02 | 118981893 | 35175847 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4.2 | 10429 | 0 | 0 | 0 |  | 2018-83984 | 9187.2 | 1.74 | 1837700 | 2020-22301 | 0 | 0 | 10429 | 10429 | 1.9752 | 3792363.6364
35175848 |  |  |  | 1.27 | 1.27 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.051201 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790550 | E.5015423.03 | 118981896 | 35175848 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4.3 | 6725 | 0 | 0 | 0 |  | 2018-83984 | 9187.2 | 1.74 | 1837700 | 2020-22301 | 0 | 0 | 6725 | 6725 | 1.2737 | 2445454.5455
35175849 |  |  |  | 1.77 | 1.77 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.071359 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790551 | E.5015423.04 | 118981897 | 35175849 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4.4 | 9343 | 0 | 0 | 0 |  | 2018-83984 | 9187.2 | 1.74 | 1837700 | 2020-22301 | 0 | 0 | 9343 | 9343 | 1.7695 | 3397454.5455
35175850 |  |  |  | 1.14 | 1.14 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.04596 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790552 | E.5015423.05 | 118981898 | 35175850 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4.5 | 6040 | 0 | 0 | 0 |  | 2018-83984 | 9187.2 | 1.74 | 1837700 | 2020-22301 | 0 | 0 | 6040 | 6040 | 1.1439 | 2196363.6364
35056438 |  |  |  | 2.15 | 2.15 |  |  |  |  | 12060.56 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.086679 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782584 | E.5015422.01 | 114985561 | 35056438 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5.1 | 11374 | 0 | 0 | 0 |  | 2018-84079 | 9187.2 | 1.74 | 1864520 | 2020-22336 | 0 | 0 | 11374 | 11374 | 2.1542 | 4136000
35175852 |  |  |  | 1.75 | 1.75 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.070552 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790553 | E.5015422.02 | 118981899 | 35175852 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5.2 | 9247 | 0 | 0 | 0 |  | 2018-84079 | 9187.2 | 1.74 | 1864520 | 2020-22336 | 0 | 0 | 9247 | 9247 | 1.7513 | 3362545.4545
35175853 |  |  |  | 0.66 | 0.66 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.026608 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790554 | E.5015422.03 | 118981960 | 35175853 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5.3 | 3483 | 0 | 0 | 0 |  | 2018-84079 | 9187.2 | 1.74 | 1864520 | 2020-22336 | 0 | 0 | 3483 | 3483 | 0.65966 | 1266545.4545
35175854 |  |  |  | 1.94 | 1.94 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.078212 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790555 | E.5015422.04 | 118981961 | 35175854 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5.4 | 10236 | 0 | 0 | 0 |  | 2018-84079 | 9187.2 | 1.74 | 1864520 | 2020-22336 | 0 | 0 | 10236 | 10236 | 1.9386 | 3722181.8182
35175855 |  |  |  | 1.99 | 1.99 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.080228 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790556 | E.5015422.05 | 118981962 | 35175855 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 5.5 | 10487 | 0 | 0 | 0 |  | 2018-84079 | 9187.2 | 1.74 | 1864520 | 2020-22336 | 0 | 0 | 10487 | 10487 | 1.9862 | 3813454.5455
35056439 |  |  |  | 1.56 | 1.56 |  |  |  |  | 11163.21 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.062892 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5782585 | E.5015421.01 | 114985621 | 35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6.1 | 8243 | 0 | 0 | 0 |  | 2018-84110 | 8342.4 | 1.58 | 1679100 | 2020-22335 | 0 | 0 | 8243 | 8243 | 1.5612 | 2997454.5455
35175856 |  |  |  | 1.59 | 1.59 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.064102 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790557 | E.5015421.02 | 118981963 | 35175856 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6.2 | 8397 | 0 | 0 | 0 |  | 2018-84110 | 8342.4 | 1.58 | 1679100 | 2020-22335 | 0 | 0 | 8397 | 8397 | 1.5903 | 3053454.5455
35175857 |  |  |  | 1.42 | 1.42 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.057248 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790578 | E.5015421.03 | 118981964 | 35175857 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6.3 | 7521 | 0 | 0 | 0 |  | 2018-84110 | 8342.4 | 1.58 | 1679100 | 2020-22335 | 0 | 0 | 7521 | 7521 | 1.4244 | 2734909.0909
35175858 |  |  |  | 1.01 | 1.01 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.040719 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790579 | E.5015421.04 | 118981965 | 35175858 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6.4 | 5348 | 0 | 0 | 0 |  | 2018-84110 | 8342.4 | 1.58 | 1679100 | 2020-22335 | 0 | 0 | 5348 | 5348 | 1.0129 | 1944727.2727
35175859 |  |  |  | 2.18 | 2.18 |  |  |  |  | 0 | UNSE | 153082106 | PLACERVILLE 2106 | PLACERVILLE 21061104 | 462 | 49.4989 | 2131 | 2.9785 | 0.0064469 | 2171 | 0.087888 | 16 | Tier 3 | PRE | GEORGETOWN | El Dorado | Sierra | Northern | 5790580 | E.5015421.05 | 118981966 | 35175859 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6.5 | 11495 | 0 | 0 | 0 |  | 2018-84110 | 8342.4 | 1.58 | 1679100 | 2020-22335 | 0 | 0 | 11495 | 11495 | 2.1771 | 4180000
31361969 |  |  |  |  | 0 |  |  |  |  | 1200.31 | UNSE | 43381101 | POINT ARENA 1101 | POINT ARENA 11013702 | 35 | 4.8876 | 1490 | 0.99668 | 0.028477 | 1152 | 0 | 2712 | Tier 3 | WDDB | POINT ARENA | Mendocino | Sonoma | Northern | 5530159 | # | 113752520 | 31361969 | RECON 9,400 FT - POINT ARENA 1101 | 7700 | 0 | 0 | 0 |  | 2018-12829 | 7700 | 1.4583 | 847000 |  |  |  |  | 0 | 0
31272375 |  |  |  |  | 0 |  |  |  |  | 81044.21 | PEND | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110112122 | 63 | 6.5695 | 2199 | 0.32133 | 0.0051004 | 2205 | 0 | 2707 | Tier 3 | WDDB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5530159 | P.11379 | 111973967 | 31272375 | R2 RECONDUCT PT. MORETTI BEYOND 5995 | 5150 | 0 | 0 | 0 |  | 2016-95735 | 5150 | 0.97538 | 566500 |  |  |  |  | 0 | 0
31280506 |  |  |  | 1.856 | 1.856 |  |  |  |  | 22941.03 | UNSE | 82931101 | POINT MORETTI 1101 | POINT MORETTI 110136514 | 64 | 6.8677 | 2062 | 0.4904 | 0.0076624 | 2141 | 0.088795 | 992 | Tier 3 | WDDB | SANTA CRUZ | Santa Cruz | Central Coast | Central Coast | 5530159 | P.11376 | 112115009 | 31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 | 9800 | 0 | 0 | 0 |  | 2016-107917 | 9800 | 1.8561 | 1078000 |  |  |  |  | 0 | 0
31272374 |  |  |  |  | 0 |  |  |  |  | 2290054.06 | PEND | 82931101 | POINT MORETTI 1101 | POINT MORETTI 11015076 | 67 | 7.4948 | 1393 | 2.2618 | 0.033758 | 1508 | 0 | 2568 | Tier 3 | WDDB | DAVENPORT | Santa Cruz | Central Coast | Central Coast | 5788791 | P.11381 | 111973964 | 31272374 | R2RECONDUCT PT.MORETTI FROM 5043 TO 5955 | 8500 | 0 | 0 | 0 |  | 2016-95694 | 8500 | 1.6098 | 946000 |  |  |  |  | 0 | 0
35057921 |  |  |  |  | 0 |  |  |  |  | 1232.06 | UNSE | 43292103 | PUEBLO 2103 | PUEBLO 2103678 | 325 | 35.3374 | 1224 | 14.9751 | 0.046077 | 1204 | 0 | 760 | Tier 3 | WDDB | NAPA | Napa | North Bay | Bay Area | 5530168 |  | 115025758 | 35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 | 9600 | 0 | 0 | 0 |  | 2019-24780 | 9600 | 1.8182 | 1960000 |  |  |  |  | 0 | 0
35019004 |  |  |  |  | 0 |  |  |  |  | 8820.84 | UNSE | 182971101 | PURISIMA 1101 | PURISIMA 110149394 | 111 | 1.1416 | 2443 | 0.24985 | 0.0022509 | 2160 | 0 | 2713 | Tier 3 | WDDB | LOMPOC, CA 93436 | San Luis Obispo | Central Coast | Central Coast | 5530175 | # | 113677313 | 35019004 | PURISIMA 1101 LS SW8139 REPL OH LINE | 3610 | 0 | 0 | 0 |  | 2018-33029 | 3610 | 0.68371 | 397100 |  |  |  |  | 0 | 0
35071495 |  |  |  |  | 0 |  |  |  |  | 1860.7 | UNSE | 182731102 | RESERVATION ROAD 1102 | RESERVATION ROAD 11023032 | 84 | 3.6042 | 2804 | 0.023638 | 0.00028141 | 2716 | 0 | 2831 | Tier 2 | WDDB | SALINAS | Monterey | Central Coast | Central Coast | 5775246 | P.11988 | 115700424 | 35071495 | RPL OH.CON.RESERVATION RD.1102 18-011072 | 6016 | 0 | 0 | 0 |  | 2019-11873 | 6016 | 1.1394 | 1378520 |  |  |  |  | 0 | 0
35192295 |  |  |  | 6.46 | 6.46 |  |  |  |  | 1529.29 | UNSE | 43321103 | RINCON 1103 | RINCON 1103198 | 62 | 6.4238 | 1618 | 1.3987 | 0.02256 | 1658 | 0.94242 | 205 | Tier 3 | ECOP | SANTA ROSA | Sonoma | Sonoma | Northern | 5792104 | E.5034413.01 | 119556481 | 35192295 | ECOP - RINCON 1103 - H02-LR198 | 34108.8 | 0 | 0 | 0 | [5 empty] | -
35192036 |  |  |  | 10.7 | 10.7 |  |  |  |  | 4112.83 | UNSE | 43321103 | RINCON 1103 | RINCON 1103474 | 174 | 18.3351 | 1342 | 6.4055 | 0.036813 | 1399 | 2.5045 | 60 | Tier 3 | ECOP | SANTA ROSA | Sonoma | North Coast | Northern | 5792069 | E.5034377.01 | 119553915 | 35192036 | ECOP - RINCON 1103 - H01-LR474 | 56496 | 0 | 0 | 0 |  |  |  | 0 |  | -
35024647 |  |  |  | 0.515 | 0.515 |  |  |  |  | 326.51 | UNSE | 83692104 | ROB ROY 2104 | ROB ROY 210410714 | 212 | 14.1675 | 2362 | 0.61141 | 0.002884 | 2308 | 0.014891 | 1419 | Tier 2 | WDDB | WATSONVILLE | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 113820887 | 35024647 | RR 2104 RECOND 1051 ZONE W TW | 2717 | 0 | 0 | 0 |  | 2018-12870 | 2717 | 0.51458 | 257028 |  |  |  |  | 0 | 0
35085847 |  |  |  |  | 0 |  |  |  |  | 74625.01 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 0 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5530169 | P.12006 | 113255606 | 35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 | 4555 | 0 | 0 | 0 |  |  |  | 0 | [5 empty] | 0 | 0 |  |  | 2020-66516 | 0 | 0 | 4555 | 4555 | 0.86269 | 2900525 | 5126422 | 636.7783
35015704 |  |  |  |  | 0 |  |  |  |  | 58821.19 | PEND | 83692105 | ROB ROY 2105 | ROB ROY 210512474 | 105 | 3.4104 | 3283 | 0.00048831 | 4.6505e-06 | 3333 | 0 | 2523 | Tier 3 | WDDB | APTOS | Santa Cruz | Central Coast | Central Coast | 5533644 |  | 113255603 | 35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 | 5300 | 0 | 0 | 0 |  | 2017-105215 | 5300 | 1.0038 | 502000 |  |  |  |  | 0 | 0
35040506 |  |  |  |  | 0 |  |  |  |  | 2868.14 | UNSE | 83692105 | ROB ROY 2105 | ROB ROY 21055090 | 245 | 21.267 | 2679 | 0.18191 | 0.00074249 | 2689 | 0 | 844 | Tier 2 | PRE | APTOS | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114607613 | 35040506 | RR2105 RESILIENCE - 5090 ZONE STEEL & TW | 11445 | 0 | 0 | 0 |  | 2018-40032 | 11445 | 2.1676 | 2529345 |  |  |  |  | 0 | 0
35044115 |  |  |  | 7 | 7 |  |  |  |  | 7487.87 | UNSE | 83692105 | ROB ROY 2105 | ROB ROY 21055166 | 81 | 5.4945 | 2801 | 0.023482 | 0.00028991 | 2788 | 0.020044 | 264 | Tier 3 | PRE | APTOS | Santa Cruz | Central Coast | Central Coast | 5530159 |  | 114712175 | 35044115 | CWSP - ROB ROY 2105 - LR 5166 | 36960 | 0 | 0 | 0 | 2018-49179 | 2018-52991 | 36960 | 7 | 7335000 |  |  |  |  | 0 | 0
35072361 |  |  |  | 1.46 | 1.46 |  |  |  |  | 147879.19 | ADER | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.012014 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5783907 | E.5015235.01 | 114754228 | 35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH1.1 | 7703 | 0 | 0 | 0 |  | 2018-60530 | 10644.48 | 2.016 | 2201000 | 2019-35969 | 0 | 0 | 7703 | 7703 | 1.4589 | 2801090.9091 | 2020-47401
35115853 |  |  |  | 2 | 2 |  |  |  |  | 285372.2 | ESTS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.016457 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786022 | E.5015235.02 | 117601683 | 35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH1.2 | 10559 | 0 | 0 | 0 |  | 2018-60530 | 26611.2 | 5.04 | 5502500 | 2019-35969 | 0 | 0 | 8473 | 8473 | 1.6047 | 3081090.9091 | 2020-43982 | 2020-49868 | 0 | 0 | 10559 | 10559 | 1.9998 | 3459188 | 4406185 | 327.6056
35115856 |  |  |  | 2.07 | 2.07 |  |  |  |  | 328942.91 | UNSC | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.017033 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786025 | E.5015235.05 | 117601688 | 35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH1.5 | 10616 | 0 | 0 | 0 |  | 2018-60530 | 10644.48 | 2.016 | 2201000 | 2019-35969 | 0 | 0 | 10943 | 10943 | 2.0725 | 3979272.7273 | 2020-43397 | 2020-57886 | 0 | 0 | 10616 | 10616 | 2.0106 | 3491056 | 4640865 | 328.8485
35115857 |  |  |  | 1.22 | 1.22 |  |  |  |  | 58758.05 | PEND | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.010039 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786026 | E.5015235.06 | 117601884 | 35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH1.6 | 6445 | 0 | 0 | 0 |  | 2018-60530 | 10644.48 | 2.016 | 2201000 | 2019-35969 | 0 | 0 | 6445 | 6445 | 1.2206 | 2343636.3636 | 2020-41727
35115858 |  |  |  | 1.3 | 1.3 |  |  |  |  | 216917.88 | UNSC | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.010697 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786027 | E.5015235.07 | 117601885 | 35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH1.7 | 6883 | 0 | 0 | 0 |  | 2018-60530 | 10644.48 | 2.016 | 2201000 | 2019-35969 | 0 | 0 | 6507 | 6507 | 1.2324 | 2366181.8182 | 2020-44131 | 2020-57655 | 0 | 0 | 6883 | 6883 | 1.3036 | 2213657 | 3153772 | 321.6122
35115847 |  |  |  | 1.81 | 1.81 |  |  |  |  | 79670.25 | ESTS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.014894 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786018 | E.5015236.02 | 117602056 | 35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 | 9566 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 9566 | 9566 | 1.8117 | 3478545.4545 | 2019-65615
35115848 |  |  |  | 1.645 | 1.645 |  |  |  |  | 287346.77 | UNSC | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.013536 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786019 | E.5015236.03 | 117602057 | 35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 | 8685 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 8697 | 8697 | 1.6472 | 3162545.4545 | 2019-59916 | 2020-57586 | 0 | 0 | 8685 | 8685 | 1.6449 | 2672611 | 3806940 | 307.7272
35115850 |  |  |  | 1.29 | 1.29 |  |  |  |  | 196238.38 | UNSC | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.010615 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786021 | E.5015236.05 | 117602059 | 35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 | 6787 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 6787 | 6787 | 1.2854 | 2468000 | 2019-54838
35115851 |  |  |  | 1.2 | 1.2 |  |  |  |  | 92518.53 | PEND | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.0098744 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786028 | E.5015236.06 | 117602170 | 35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 | 6354 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 6354 | 6354 | 1.2034 | 2310545.4545 | 2019-54859
35115852 |  |  |  | 1.6 | 1.6 |  |  |  |  | 167833.44 | PEND | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.016425 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786029 | E.5015236.07 | 117602171 | 35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 | 8497 | 93 | 8497 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 8454 | 8454 | 1.6011 | 3074181.8182 | 2020-35298 | 2020-61246 | 8497 | 93 | 8497 | 8590 | 1.6269 | 3346859 | 4512982 | 389.6227
35192298 |  |  |  | 6.99 | 6.99 |  |  |  |  | 1529.29 | UNSE | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 210237300 | 41 | 6.9662 | 2301 | 0.14002 | 0.0034152 | 2278 | 0.094136 | 227 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5792105 | E.5034414.01 | 119556492 | 35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 | 36907.2 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35192051 |  |  |  | 7.18 | 7.18 |  |  |  |  | 2305.86 | UNSE | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21024796 | 114 | 7.1917 | 2563 | 0.16766 | 0.0014707 | 2524 | 0.11215 | 133 | Tier 3 | ECOP | CAMP CONNELL | Calaveras | Stockton | Central Valley | 5792079 | E.5034388.01 | 119554056 | 35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 | 41065 | 0 | 0 | 0 |  | 2020-60448 | 41606.4 | 7.88 | 9117346 | -
35192299 |  |  |  | 5.09 | 5.09 |  |  |  |  | 1529.29 | UNSE | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 210297924 | 49 | 5.1507 | 2620 | 0.052198 | 0.0010653 | 2507 | 0.044316 | 290 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5792106 | E.5034415.01 | 119556522 | 35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 | 5536 | 8000 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
31319329 |  |  |  | 0.694 | 0.694 |  |  |  |  | 610.78 | UNSE | 182631103 | SAN LUIS OBISPO 1103 | SAN LUIS OBISPO 1103V82 | 174 | 8.7819 | 1504 | 4.7975 | 0.027572 | 1404 | 0.25402 | 2182 | Tier 2 | WDDB | SAN LUIS OBISPO | San Luis Obispo | Los Padres | Central Coast | 5530166 |  | 112762682 | 31319329 | SAN LUIS OBISP1103 - RECOND WITH 2CU TW | 3663 | 0 | 0 | 0 |  | 2018-84374 | 3663 | 0.69375 | 604395 |  |  |  |  | 0 | 0
35192021 |  |  |  | 2.21 | 2.21 |  |  |  |  | 8862.98 | UNSE | 43432104 | SILVERADO 2104 | SILVERADO 210478268 | 114 | 9.7249 | 1254 | 4.9171 | 0.043133 | 1445 | 0.74868 | 64 | Tier 3 | ECOP | ANGWIN | Napa | North Bay | Bay Area | 5792071 | E.5034379.01 | 119553918 | 35192021 | ECOP - SILVERADO 2104 - H02-LR78268 | 11614 | 0 | 0 | 0 | 2020-56825 | 2020-56839 | 11668.8 | 2.21 | 2104150 | -
35192037 |  |  |  | 1.94 | 1.94 |  |  |  |  | 7267.98 | UNSE | 43432105 | SILVERADO 2105 | SILVERADO 2105167360 | 70 | 9.5796 | 2174 | 0.39281 | 0.0056116 | 2203 | 0.053298 | 125 | Tier 3 | ECOP | SANTA ROSA | Sonoma | North Bay | Northern | 5792078 | E.5034387.01 | 119554055 | 35192037 | ECOP - SILVERADO 2105 - H01-LR1421 | 10935 | 0 | 0 | 0 | 2020-56802 | 2020-56843 | 10929.6 | 2.07 | 2020550 | -
35073059 |  |  |  |  | 0 |  |  |  |  | 3724.58 | UNSE | 42721104 | SONOMA 1104 | SONOMA 110478372 | 198 | 16.6264 | 1334 | 7.3862 | 0.037304 | 1270 | #VALUE! | 1476 | Tier 2 | WDDB | SONOMA | Sonoma | Sonoma | Northern | 5530175 |  | 115768648 | 35073059 | SONOMA1104 WIREDOWN | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35094513 |  |  |  | 1.92 | 1.92 |  |  |  |  | 171280.87 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.010685 | 19 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5785245 | E.5014540.01 | 114567769 | 35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 | 10091 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 10091 | 10091 | 1.9112 | 3669454.5455 | 2020-43006
35116921 |  |  |  | 1.53 | 1.53 |  |  |  |  | 100418.57 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.0085146 | 19 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786030 | E.5014540.02 | 117605453 | 35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 | 8460 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 8460 | 8460 | 1.6023 | 3076363.6364 | 2020-44626
35116924 |  |  |  | 1.88 | 1.88 |  |  |  |  | 91260.82 | ADER | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.010462 | 19 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786033 | E.5014540.05 | 117605550 | 35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 | 9910 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 9910 | 9910 | 1.8769 | 3603636.3636 | 2020-46904
35116925 |  |  |  | 1.7 | 1.7 |  |  |  |  | 45510.72 | ESTS | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.0094606 | 19 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786034 | E.5014540.06 | 117605552 | 35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 | 8968 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 8968 | 8968 | 1.6985 | 3261090.9091 | 2019-73793
35116926 |  |  |  | 1.46 | 1.46 |  |  |  |  | 67602.25 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021804 | 118 | 8.3797 | 2712 | 0.069602 | 0.00058985 | 2706 | 0.008125 | 19 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786035 | E.5014540.07 | 117605553 | 35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 | 7880 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 7880 | 7880 | 1.4924 | 2865454.5455 | 2020-47571
35176497 |  |  |  | 0.6 | 0.6 |  |  |  |  | 17631.69 | UNSE | 162821702 | STANISLAUS 1702 | STANISLAUS 17021850 | 182 | 13.4625 | 2651 | 0.16988 | 0.00093342 | 2745 | 0.0054766 | 66 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5539421 | E.5030966.01 | 118911798 | 35176497 | ECOP - STANISLAUS 1702 - H03 - LR1850 | 3180 | 636 | 0 | 0 | 2020-49973 | 2020-49974 | 3801.6 | 0.72 | 1378925 | 2020-09-22 | 0 | 633.6 | 3168 | 3801.6 | 0.72 | 1382400 | 2020-49973
35174174 |  |  |  | 0.6 | 0.6 |  |  |  |  | 0 | UNSE | 162821702 | STANISLAUS 1702 | STANISLAUS 17021850 | 182 | 13.4625 | 2651 | 0.16988 | 0.00093342 | 2745 | 0.0050728 | 66 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5539421 | E.9999990.01 | 13867552 | 35174174 | ECOP-STANISLAUS 1702-H03-LR1850 | 3168 | 0 | 0 | 0 | [5 empty] | -
35095168 |  |  |  | 1.27 | 1.27 |  |  |  |  | 148823.83 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.027902 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5785247 | E.5015701.01 | 114832575 | 35095168 | CWSP–STANISLAUS 1702-LR1888-PH 1.1 | 6461 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 6461 | 6461 | 1.2237 | 2349454.5455 | 2020-29753
35116515 |  |  |  | 1.75 | 1.75 |  |  |  |  | 202371.41 | UNSC | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.038447 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786036 | E.5015701.02 | 117607998 | 35116515 | CWSP–STANISLAUS 1702-LR1888-PH 1.2 | 9222 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 8765 | 8765 | 1.66 | 3187272.7273 | 2019-69359 | 2020-48497 | 0 | 0 | 9222 | 9222 | 1.7466 | 3203035 | 4438411 | 347.3254
35116516 |  |  |  | 0.91 | 0.91 |  |  |  |  | 155785.13 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.019993 | 4 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786037 | E.5015701.03 | 117608020 | 35116516 | CWSP–STANISLAUS 1702-LR1888-PH 1.3 | 4825 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 4528 | 4528 | 0.85758 | 1646545.4545 | 2020-30061 | 2020-50281 | 0 | 0 | 4825 | 4825 | 0.91383 | 2239022 | 3210873 | 464.046
35116519 |  |  |  | 1.76 | 1.76 |  |  |  |  | 58121.02 | UNSC | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.038667 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786038 | E.5015701.04 | 117608026 | 35116519 | CWSP–STANISLAUS 1702-LR1888-PH 1.4 | 9579 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 9579 | 9579 | 1.8142 | 3483272.7273 | 2019-71107
35116517 |  |  |  | 2.4 | 2.4 |  |  |  |  | 103212.89 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.052728 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786039 | E.5015701.05 | 117608185 | 35116517 | CWSP–STANISLAUS 1702-LR1888-PH 1.5 | 10921 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 10921 | 10921 | 2.0684 | 3971272.7273 | 2019-69686
35116518 |  |  |  | 2.07 | 2.07 |  |  |  |  | 53881.43 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.045478 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786040 | E.5015701.06 | 117608188 | 35116518 | CWSP–STANISLAUS 1702-LR1888-PH 1.6 | 10922 | 0 | 0 | 0 |  | 2018-78320 | 8764.8 | 1.66 | 1793000 | 2019-35975 | 0 | 0 | 10922 | 10922 | 2.0686 | 3971636.3636 | 2019-69862
35095167 |  |  |  | 1.12 | 1.12 |  |  |  |  | 126187.53 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.024606 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5785246 | E.5015394.01 | 114832579 | 35095167 | CWSP–STANISLAUS 1702-LR1888-PH 2.1 | 5899 | 0 | 0 | 0 | N/A | 2018-67963 | 8659.2 | 1.64 | 1768880 | 2019-35973 | 0 | 0 | 5833 | 5833 | 1.1047 | 2121090.9091 | 2020-38020 | 2020-51849 | 0 | 0 | 5899 | 5899 | 1.1172 | 2365952 | 3732876 | 401.0768
35116511 |  |  |  | 1.2 | 1.2 |  |  |  |  | 82759.03 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.026364 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786041 | E.5015394.02 | 117608780 | 35116511 | CWSP–STANISLAUS 1702-LR1888-PH 2.2 | 6934 | 0 | 0 | 0 | N/A | 2018-67963 | 8659.2 | 1.64 | 1768880 | 2019-35973 | 0 | 0 | 6934 | 6934 | 1.3133 | 2521454.5455 | 2019-71058
35116512 |  |  |  | 1.75 | 1.75 |  |  |  |  | 98259.2 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.038447 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 6786042 | E.5015394.03 | 117608788 | 35116512 | CWSP–STANISLAUS 1702-LR1888-PH 2.3 | 9387 | 0 | 0 | 0 | N/A | 2018-67963 | 8659.2 | 1.64 | 1768880 | 2019-35973 | 0 | 0 | 9387 | 9387 | 1.7778 | 3413454.5455 | 2020-40526
35116513 |  |  |  | 2.13 | 2.13 |  |  |  |  | 51636.01 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.046796 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 6786043 | E.5015394.04 | 117608814 | 35116513 | CWSP–STANISLAUS 1702-LR1888-PH 2.4 | 11249 | 0 | 0 | 0 | N/A | 2018-67963 | 8659.2 | 1.64 | 1768880 | 2019-35973 | 0 | 0 | 11249 | 11249 | 2.1305 | 4090545.4545 | 2019-70798
35116514 |  |  |  | 2.06 | 2.06 |  |  |  |  | 53747.61 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17021888 | 231 | 18.9186 | 2386 | 0.62036 | 0.0026855 | 2198 | 0.045258 | 4 | Tier 2 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 6786044 | E.5015394.05 | 117608818 | 35116514 | CWSP–STANISLAUS 1702-LR1888-PH 2.5 | 10882 | 0 | 0 | 0 | N/A | 2018-67963 | 8659.2 | 1.64 | 1768880 | 2019-35973 | 0 | 0 | 10882 | 10882 | 2.061 | 3957090.9091 | 2020-44614
35174467 |  |  |  | 6 | 6 |  |  |  |  | 3175.4 | ESTS | 162821702 | STANISLAUS 1702 | STANISLAUS 170237276 | 168 | 11.651 | 2825 | 0.037039 | 0.00022047 | 2839 | 0.01278 | 37 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5790106 | E.5033911.01 | 118912984 | 35174467 | CWSP - STANISLAUS 1702 LR 37276 PH1.2 ECOP - STANISLAUS 1702 - H01 - LR37276-Ph1 | 34056 | 0 | 0 | 0 |  | 2018-61549 | 34056 | 6.45 | 6949300 | - | 0 | 0 | 34056 | 34056 | 6.45 | 12384000
35174468 |  |  |  | 5.72 | 5.72 |  |  |  |  | 2800.77 | ESTS | 162821702 | STANISLAUS 1702 | STANISLAUS 170237276 | 168 | 11.651 | 2825 | 0.037039 | 0.00022047 | 2839 | 0.012183 | 37 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5790107 | E.5033912.01 | 118912985 | 35174468 | CWSP - STANISLAUS 1702 LR 37276 PH1.3 ECOP - STANISLAUS 1702 - H01 - LR37276-Ph2 | 34056 | 0 | 0 | 0 |  | 2018-61549 | 34056 | 6.45 | 6949300 | - | 0 | 0 | 34056 | 34056 | 6.45 | 12384000
35046371 |  |  |  | 12.92 | 12.92 |  |  |  |  | 55329.72 | UNSE | 162821702 | STANISLAUS 1702 | STANISLAUS 170237276 | 168 | 11.651 | 2825 | 0.037039 | 0.00022047 | 2839 | 0.027519 | 37 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5530176 |  | 114712085 | 35046371 | ECOP - STANISLAUS 1702 LR 37276 | 68112 | 0 | 0 | 0 | 2018-53474 | 2018-61549 | 68112 | 12.9 | 13898600 | 2020-09-22 | 0 | 0 | 68204 | 68204 | 12.9174 | 24801454.5455
35116922 |  |  |  | 1.16 | 1.16 |  |  |  |  | 64959.87 | PEND | 162821702 | STANISLAUS 1702 | STANISLAUS 17024905 | 35 | 2.3021 | 2766 | 0.01361 | 0.00038885 | 2710 | 0.0045947 | 82 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786031 | E.5014540.03 | 117605456 | 35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 | 6221 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 6221 | 6221 | 1.1782 | 2262181.8182 | 2020-37229
35116923 |  |  |  | 1.2 | 1.2 |  |  |  |  | 78749.66 | ADER | 162821702 | STANISLAUS 1702 | STANISLAUS 17024905 | 35 | 2.3021 | 2766 | 0.01361 | 0.00038885 | 2710 | 0.0047531 | 82 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5786032 | E.5014540.04 | 117605459 | 35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 | 6326 | 0 | 0 | 0 |  | 2018-52369 | 8131.2 | 1.54 | 1660057.143 | 2019-35971 | 0 | 0 | 6326 | 6326 | 1.1981 | 2300363.6364 | 2019-70283
35192045 |  |  |  | 5.4 | 5.4 |  |  |  |  | 3418.02 | UNSE | 162821702 | STANISLAUS 1702 | STANISLAUS 170275348 | 77 | 5.3029 | 2878 | 0.0073521 | 9.5481e-05 | 2874 | 0.0050161 | 53 | Tier 3 | ECOP | ARNOLD | Calaveras | Stockton | Central Valley | 5792068 | E.5034376.01 | 119553913 | 35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 | 28512 | 0 | 0 | 0 | 2020-54851 | 2020-54852 | 27984 | 5.3 | 7605052 | -
35024428 |  |  |  |  | 0 |  |  |  |  | 220.19 | UNSE | 152591101 | SUMMIT 1101 | SUMMIT 110148632 | 38 | 2.7294 | 1529 | 1.0003 | 0.026323 | 1895 | #VALUE! | 2032 | Tier 2 | WDDB | SODA SPRINGS | Placer | Sierra | Northern | 5530173 |  | 114127299 | 35024428 | SUMMIT 1101 RECONDUCTOR W TREE WIRE | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35058060 |  |  |  | 1.704 | 1.704 |  |  |  |  | 7515.31 | UNSE | 83392110 | Swift 2110 | SWIFT 2110XR366 | 129 | 8.4324 | 877 | 10.6874 | 0.082848 | 822 | 1.447 | 1392 | Tier 2 | WDDB | SAN JOSE | Santa Clara | San Jose | Central Coast | 5530174 |  | 115029437 | 35058060 | SWIFT 2110 - CONDUCTOR REPL | 8995 | 0 | 0 | 0 |  | 2018-78893 | 8995 | 1.7036 | 1921600 |  |  |  |  | 0 | 0
35076130 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 152291101 | Tamarack 1101 | TAMARACK 1101CB | 148 | 17.479 | 2630 | 0.14896 | 0.0010065 | 2552 | #VALUE! | 1169 | Tier 2 | WDDB | SODA SPRINGS | Nevada | Sierra | Northern | 5530173 |  | 116489079 | 35076130 | TAMARACK 1101 WD 19-0011942 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35043421 |  |  |  | 2.21 | 2.21 |  |  |  |  | 33453.57 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.024807 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5784647 | E.5014728.01 | 114676761 | 35043421 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.1 | 11665 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35906 | 0 | 0 | 11665 | 11665 | 2.2093 | 4241818.1818
35113993 |  |  |  | 2.12 | 2.12 |  |  |  |  | 15841.94 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.023796 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786012 | E.5014728.02 | 117501693 | 35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.2 | 11178 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 11178 | 11178 | 2.117 | 4064727.2727 | 2020-04093
35113994 |  |  |  | 1.33 | 1.33 |  |  |  |  | 30909.87 | ADER | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.014929 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786013 | E.5014728.03 | 117501694 | 35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.3 | 7001 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 7001 | 7001 | 1.3259 | 2545818.1818 | 2020-25739
35113995 |  |  |  | 1.41 | 1.41 |  |  |  |  | 35279.54 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.015827 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786014 | E.5014728.04 | 117501695 | 35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.4 | 7448 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 7448 | 7448 | 1.4106 | 2708363.6364 | 2020-56628
35113996 |  |  |  | 1.188 | 1.188 |  |  |  |  | 92385.72 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.013335 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786015 | E.5014728.05 | 117501697 | 35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.5 | 6270 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 6270 | 6270 | 1.1875 | 2280000 | 2020-08230
35113997 |  |  |  | 1.223 | 1.223 |  |  |  |  | 71196.78 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.013728 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786016 | E.5014728.06 | 117500608 | 35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 | 6460 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 6460 | 6460 | 1.2235 | 2349090.9091 | 2020-23988
35113998 |  |  |  | 1.119 | 1.119 |  |  |  |  | 109812.59 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.01256 | 96 | Tier 2 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786017 | E.5014728.07 | 117500659 | 35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 | 5907 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 5907 | 5907 | 1.1187 | 2148000 | 2020-33083
35113999 |  |  |  | 1.693 | 1.693 |  |  |  |  | 17525.47 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110112256 | 86 | 6.4793 | 2589 | 0.10855 | 0.0012622 | 2453 | 0.019003 | 96 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786134 | E.5014728.08 | 117500661 | 35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 | 8940 | 0 | 0 | 0 |  | 2018-57103 | 7128 | 1.35 | 1455162 | 2019-35877 | 0 | 0 | 8940 | 8940 | 1.6932 | 3250909.0909 | 2020-06771
35112972 |  |  |  | 1.26 | 1.26 |  |  |  |  | 27511.56 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.038646 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786001 | E.5014727.02 | 117491267 | 35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 | 7761 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881 | 0 | 0 | 7761 | 7761 | 1.4699 | 2822181.8182 | 2020-64148
35112973 |  |  |  | 0.8 | 0.8 |  |  |  |  | 87779.68 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.024537 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786002 | E.5014727.03 | 117491412 | 35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 | 7761 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881 | 0 | 0 | 7761 | 7761 | 1.4699 | 2822181.8182 | 2020-58627
35112974 |  |  |  | 2.61 | 2.61 |  |  |  |  | 25228.93 | ADER | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.080052 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786003 | E.5014727.04 | 117491414 | 35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 | 13780.8 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881 | [6 empty] | 2019-78879
35112975 |  |  |  | 1.45 | 1.45 |  |  |  |  | 16470.05 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.044474 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786004 | E.5014727.05 | 117491771 | 35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 | 7656 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881 | [6 empty] | 2019-80056
35112976 |  |  |  | 1.83 | 1.83 |  |  |  |  | 11288.46 | ADER | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.056129 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786005 | E.5014727.06 | 117491849 | 35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 | 9662.4 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881
35112977 |  |  |  | 1.15 | 1.15 |  |  |  |  | 13120.08 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.035272 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786006 | E.5014727.07 | 117491910 | 35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 | 6072 | 0 | 0 | 0 |  | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881
35043423 |  |  |  | 1.11 | 1.11 |  |  |  |  | 60907.71 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.034045 | 63 | Tier 3 | PRE | VOLCANO | Amador | Stockton | Central Valley | 5785230 | E.5014726.01 | 114678726 | 35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 | 5885 | 0 | 0 | 0 |  | 2018-83494 | 8870.4 | 1.68 | 1814983 | 2019-35882 | 0 | 0 | 5885 | 5885 | 1.1146 | 2140000 | 2020-36196
35112978 |  |  |  | 1.61 | 1.61 |  |  |  |  | 84719.9 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.049381 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786007 | E.5014726.02 | 117493902 | 35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 | 8477 | 0 | 0 | 0 |  | 2018-83494 | 8870.4 | 1.68 | 1814983 | 2019-35882 | 0 | 0 | 8477 | 8477 | 1.6055 | 3082545.4545 | 2019-65776
35112979 |  |  |  | 1.01 | 1.01 |  |  |  |  | 105266.62 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.030978 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786008 | E.5014726.03 | 117494010 | 35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 | 5331 | 0 | 0 | 0 |  | 2018-83494 | 8870.4 | 1.68 | 1814983 | 2019-35882 | 0 | 0 | 5331 | 5331 | 1.0097 | 1938545.4545 | 2019-71481
35113100 |  |  |  | 1.94 | 1.94 |  |  |  |  | 129315.53 | PEND | 163201101 | WEST POINT 1101 | WEST POINT 110113444 | 221 | 17.021 | 2293 | 0.77919 | 0.0035258 | 2268 | 0.059503 | 63 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5786009 | E.5014726.04 | 117494051 | 35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 | 10233 | 0 | 0 | 0 |  | 2018-83494 | 8870.4 | 1.68 | 1814983 | 2019-35882 | 0 | 0 | 10233 | 10233 | 1.9381 | 3721090.9091 | 2020-44079
35173755 |  |  |  | 2.28 | 2.28 |  |  |  |  | 55261.81 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110136674 | 125 | 9.4121 | 2389 | 0.33299 | 0.0026639 | 2361 | 0.055004 | 38 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5790005 | E.5034447.01.01 | 118911674 | 35173755 | ECOP - WEST POINT 1101 - H02 - LR36674 PH1 | 7774 | 300 | 0 | 0 | 2020-33883 | 2020-36163 | 11774.4 | 2.23 | 3367686 | 2020-61635 | 0 | 5016 | 6758.4 | 11774.4 | 2.23 | 4281600
35199560 |  |  |  | 0.85 | 0.85 |  |  |  |  | 1739.89 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 110136674 | 125 | 9.4121 | 2389 | 0.33299 | 0.0026639 | 2361 | 0.02913 | 38 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5790005 | E.5034447.01.02 | 119666808 | 35199560 | ECOP - WEST POINT 1101 - H02 - LR36674 PH2 | 335 | 4694 | 0 | 0 | 2020-33883 | 2020-36163 | 11774.4 | 2.23 | 3367686 | 2020-61635 | 0 | 0 | 4488 | 4488 | 0.85 | 1632000
35192041 |  |  |  | 3.24 | 3.24 |  |  |  |  | 7195.17 | UNSE | 163201101 | WEST POINT 1101 | WEST POINT 11014706 | 138 | 11.4541 | 2468 | 0.28923 | 0.0020959 | 2390 | 0.057924 | 31 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5792061 | E.5034369.01 | 119552184 | 35192041 | ECOP - WEST POINT 1101 - H01-LR4706 | 17201 | 2317 | 0 | 0 |  |  |  | 0 |  | -
35043422 |  |  |  | 10.28 | 10.28 |  |  |  |  | 37061 | ADER | 182941102 | WEST POINT 1101 | WEST POINT 1101L2219 | 41 | 3.3854 | 2757 | 0.017329 | 0.00042266 | 2687 | 0.035256 | 137 | Tier 3 | PRE | PIONEER | Amador | Stockton | Central Valley | 5785229 | E.5014727.01 | 114678720 | 35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 | 54278 | 0 | 0 | 0 | 2018-61566 | 2018-70913 | 7761.6 | 1.47 | 1573714 | 2019-35881 | 0 | 0 | 54278 | 54278 | 10.2799 | 19737454.5455 | 2020-01879
35192300 |  |  |  | 2.22 | 2.22 |  |  |  |  | 1921.66 | UNSE | 163201101 | WEST POINT 1101 | WEST POINT 1101L3355 | 27 | 2.2487 | 1956 | 0.2728 | 0.010104 | 2102 | 0.18044 | 176 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5792108 | E.5034417.01 | 119556696 | 35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 | 11960 | 0 | 0 | 0 | [5 empty] | -
35181199 |  |  |  | 2.52 | 2.52 |  |  |  |  | 6669.42 | ESTS | 163201101 | WEST POINT 1101 | WEST POINT 1101L373 | 93 | 7.3956 | 2260 | 0.36311 | 0.0039044 | 2136 | 0.082897 | 69 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5790907 | E.5034007.01 | 118991252 | 35181199 | ECOP - WEST POINT 1101 - H03-TSL373 | 42184 | 0 | 0 | 0 | 2020-56868 | 2020-56877 | 42184 | 7.9894 | 8825795 | - | 0 | 0 | 42184 | 42184 | 7.9894 | 15339636.3636
35192050 |  |  |  | 3.62 | 3.62 |  |  |  |  | 1772.57 | UNSE | 163201102 | WEST POINT 1102 | WEST POINT 11021303 | 146 | 15.6665 | 2021 | 1.2651 | 0.0086648 | 1912 | 0.19585 | 114 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5792077 | E.5034385.01 | 119554054 | 35192050 | ECOP - WEST POINT 1102 - H01-TS1303 | 18935 | 0 | 0 | 0 |  |  |  | 0 |  | -
35192052 |  |  |  | 2.18 | 2.18 |  |  |  |  | 2025.89 | UNSE | 163201102 | WEST POINT 1102 | WEST POINT 110234416 | 113 | 10.4546 | 1633 | 2.466 | 0.021823 | 1510 | 0.39422 | 194 | Tier 3 | ECOP | WEST POINT | Calaveras | Stockton | Central Valley | 5792081 | E.5034390.01 | 119554058 | 35192052 | ECOP - WEST POINT 1102 - H05-LR34416 | 10910 | 4720 | 0 | 0 |  |  |  | 0 |  | -
35192301 |  |  |  | 1.6 | 1.6 |  |  |  |  | 1529.29 | UNSE | 163201102 | WEST POINT 1102 | WEST POINT 110236676 | 173 | 16.9707 | 1530 | 4.5232 | 0.026145 | 1376 | 0.28572 | 249 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5792109 | E.5034418.01 | 119556698 | 35192301 | ECOP - WEST POINT 1102 - H06-LR36676 | 8950 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35192302 |  |  |  | 2.2 | 2.2 |  |  |  |  | 1529.29 | UNSE | 163201102 | WEST POINT 1102 | WEST POINT 110293116 | 453 | 42.3267 | 1909 | 5.1406 | 0.011348 | 1875 | 0.17902 | 310 | Tier 3 | ECOP | PIONEER | Amador | Stockton | Central Valley | 5792110 | E.5034419.01 | 119556928 | 35192302 | ECOP - WEST POINT 1102 - H07-LR93116 | 27139 | 0 | 0 | 0 |  |  |  | 0 |  | - |  |  |  | 0 | 0
35051268 |  |  |  | 12.43 | 12.43 |  |  |  |  | 10840.14 | UNSE | 42661104 | WILLITS 1104 | WILLITS 110434008 | 259 | 22.9249 | 1988 | 2.4408 | 0.0094239 | 1998 | 0.88668 | 50 | Tier 3 | PRE | WILLITS | Mendocino | Humboldt | Northern | 5530164 |  | 114848768 | 35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 | 65683.2 | 0 | 0 | 0 |  | 2018-79942 | 65683.2 | 12.44 | 13336500
35047429 |  |  |  | 11.52 | 11.52 |  |  |  |  | 11274.6 | UNSE | 42661104 | WILLITS 1104 | WILLITS 110434008 | 259 | 22.9249 | 1988 | 2.4408 | 0.0094239 | 1998 | 0.82177 | 50 | Tier 3 | PRE | WILLITS | Mendocino | Humboldt | Northern | 5530164 |  | 114742614 | 35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 | 60825.6 | 0 | 0 | 0 |  | 2018-70062 | 60825.6 | 11.52 | 12577100
35043296 |  |  |  | 1.27 | 1.27 |  |  |  |  | 151285.81 | UNSC | 192171103 | WILLOW CREEK 1103 | WILLOW CREEK 11033090 | 58 | 10.8102 | 1598 | 1.3443 | 0.023177 | 1798 | 0.10581 | 2204 | Tier 2 | WDDB | WILLOW CREEK | Humboldt | Humboldt | Northern | 5530164 |  | 112191208 | 35043296 | WDDB - WILLOW CRK 1103 LR 3090 | 6300 | 0 | 0 | 0 |  | 2016-120186 | 6300 | 1.1932 | 704000 | 2019-24940 | 0 | 0 | 6300 | 6300 | 1.1932 | 2290909.0909 | 2020-30698
35191930 |  |  |  | 6.42 | 6.42 |  |  |  |  | 4512.41 | UNSE | 43021101 | WOODACRE 1101 | WOODACRE 1101404 | 152 | 12.4146 | 2189 | 0.81576 | 0.0053668 | 2372 | 0.28264 | 33 | Tier 3 | ECOP | SAN GERONIMO | Marin | North Bay | Northern | 5792062 | E.5034370.01 | 119553788 | 35191930 | ECOP - WOODACRE 1101 - H01-LR404 - PH 1 | 35425 | 0 | 0 | 0 |  |  |  | 0 |  | -
35191934 |  |  |  | 6 | 6 |  |  |  |  | 3249.83 | UNSE | 43021101 | WOODACRE 1101 | WOODACRE 1101404 | 152 | 12.4146 | 2189 | 0.81576 | 0.0053668 | 2372 | 0.26415 | 33 | Tier 3 | ECOP | SAN GERONIMO | Marin | North Bay | Northern | 5792063 | E.5034371.01 | 119553797 | 35191934 | ECOP - WOODACRE 1101 - H01-LR404 - PH 2 | 28742 | 0 | 0 | 0 | [5 empty] | -
35112968 |  |  |  | 2.7 | 2.7 |  |  |  |  | 1587.18 | UNSE | 24251101 | WOODSIDE 1101 | WOODSIDE 11018974 | 149 | 13.2248 | 1145 | 7.8956 | 0.05299 | 1406 | 1.08 | 59 | Tier 2 | WDDB | WOODSIDE | San Mateo | Peninsula | Central Coast | 5786098 | E.5024111.01 | 117474195 | 35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE | 14256 | 0 | 0 | 0 |  | 2019-42293 | 14256 | 2.7 | 2987000
35181939 |  |  |  |  | 0 |  |  |  |  | 0 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031508 | 249 | 27.2173 | 1176 | 12.4656 | 0.050062 | 1498 | #VALUE! | 1086 | Tier 3 | WDDB | BERRY CREEK | Butte | North Valley | Northern | 5791278 | E.5034174.01 | 119146963 | 35181939 | WD RECONDUCTORING ON WYANDOTTE 1103 | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
35113946 |  |  |  | 22.84 | 22.84 |  |  |  |  | 795.29 | UNSE | 102911103 | WYANDOTTE 1103 | WYANDOTTE 11031974 | 259 | 22.4168 | 1849 | 3.3188 | 0.012814 | 1756 | 2.2656 | 11 | Tier 3 | PRE | BERRY CREEK | Butte | North Valley | Northern | 5786219 | E.5024242.01 | 117557032 | 35113946 | CWSP - WYANDOTTE 1103 – LR 1974 | 120595 | 0 | 0 | 0 |  | 2019-44589 | 120595.2 | 22.84 | 22840000
35059696 |  |  |  |  | 0 |  |  |  |  | 675.26 | UNSE | 158031101 | ECHO SUMMIT 1101 |  | 0 | 0 | 0 | 0 | 0 | #N/A | #VALUE! |  | Tier 3 | PRE | LITTLE NORWAY | El Dorado | Sierra | Northern | 5786461 |  | 115061014 | 35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH | - | - | - | - |  |  |  | 0 | [5 empty] | 0 | 0
31361965 |  | HOLD | 2021777 | 0.45 | 0.45 | 2021 |  |  |  | 287952.24 | CONS | 43071101 | DUNBAR 1101 | DUNBAR 110147964 | 68 | 6.5107 | 1794 | 0.99704 | 0.014662 | 1845 | 0.068224 | 1151 | Tier 3 | WDDB | KENWOOD | Sonoma | Sonoma | Northern | 5530175 |  | 113751296 | 31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | 2367 | 0 | 0 | 0 | 2018-69430 | 2300 | 0.43561 | 345000 | N/A |  |  |  | 0 | 0 | 0 | 2019-35371 | 2019-34365 | 0 | 0 | 2367 | 2367 | 0.4483 | 797947 | 1245293 | 337.1132
35145522 |  | HOLD |  | 3.95 | 3.95 | 2021 |  |  |  | 150355.25 | PEND | 153612104 | CLARKSVILLE 2104 | CLARKSVILLE 2104CB | 107 | 8.8028 | 134 | 32.5187 | 0.30391 | 385 | 14.4458 | 541 | Tier 3 | PSPS | El Dorado Hills | El Dorado | Sierra | Northern | 5788783 | E.5025635.01 | 118265394 | 35145522 | PSPS - Clarksville 2104 - CB | 0 | 13464 | 0 | 0 |  | 2019-80671 | 13464 | 2.55 | 23720000 | N/A | 0 | 13464 | 0 | 13464 | 2.55 | 10710000 | 2020-38602
35145001 |  | HOLD |  | 1.6 | 1.6 | 2021 |  |  |  | 173293.88 | PEND | 12022215 | CLAYTON 2215 | CLAYTON 2215184604 | 106 | 2.0891 | 1739 | 1.7951 | 0.016935 | 1716 | 1.3512 | 1165 | Tier 3 | PSPS | CONCORD | CONTRA COSTA | Diablo | Bay Area | 5788778 | E.5025639 | 118259181 | 35145001 | PSPS - Clayton 2215 – CB | 475.2 | 20592 | 0 | 0 |  | 2019-79149 | 11616 | 2.2 | 19530000 | N/A | 0 | 20592 | 475.2 | 21067.2 | 3.99 | 16758000
35145002 |  | HOLD |  | 0.68 | 0.68 | 2021 |  |  |  | 116667.86 | APPR | 42481101 | IGNACIO 1101 | IGNACIO 1101CB | 19 | 1.6722 | 2448 | 0.042331 | 0.0022279 | 2447 | 0.017042 | 2421 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788780 | E.5025640 | 118262844 | 35145002 | PSPS - Ignacio 1101 - CB | 0 | 3590.4 | 0 | 0 |  | 2019-78952 | 3585.12 | 0.679 | 2194800 | N/A | 0 | 3590.4 | 0 | 3590.4 | 0.68 | 2856000
35145003 |  | HOLD |  | 0.28 | 0.28 | 2021 |  |  |  | 93712.22 | PEND | 13801103 | MORAGA 1103 | MORAGA 1103CB | 82 | 1.3309 | 2631 | 0.082476 | 0.0010058 | 2698 | 0.017178 | 2231 | Tier 3 | PSPS | ORINDA | CONTRA COSTA | Diablo | Bay Area | 5788781 | E.5025641 | 118263229 | 35145003 | PSPS - Moraga 1103 - CB | 0 | 1161.6 | 0 | 0 |  | 2019-78960 | 1161.6 | 0.22 | 2050000 | N/A | 0 | 1161.6 | 0 | 1161.6 | 0.22 | 924000 | 2020-33628
35144941 |  | HOLD |  | 2.59 | 2.59 | 2021 |  |  |  | 192514.61 | ADER | 83252105 | PAUL SWEET 2105 | PAUL SWEET 2105CB | 86 | 7.4461 | 2633 | 0.086208 | 0.0010024 | 2727 | 0.020645 | 1376 | Tier 3 | PSPS | SANTA CRUZ | SANTA CRUZ | Central Coast | Central Coast | 5788792 | E.5025646 | 118261469 | 35144941 | PSPS - Paul Sweet 2105 - CB PH 1 | 17212.8 | 1056 | 0 | 0 |  | 2020-07355 | 16737.6 | 3.17 | 4786588 | N/A | 0 | 1056 | 17212.8 | 18268.8 | 3.46 | 14532000 | 2020-45854
35144943 |  | HOLD |  | 0.63 | 0.63 | 2021 |  |  |  | 98806.73 | ESTS | 83692105 | ROB ROY 2105 | ROB ROY 2105CB | 17 | 0.73407 | 2781 | 0.0058961 | 0.00034683 | 2817 | 0.0050096 | 2564 | Tier 3 | PSPS | APTOS | SANTA CRUZ | Central Coast | Central Coast | 5788791 | E.5025648 | 118261587 | 35144943 | PSPS - Rob Roy 2105 - CB | 0 | 2851.2 | 0 | 0 |  | 2020-03578 | 3326.4 | 0.63 | 1574100 | N/A | 0 | 2851.2 | 0 | 2851.2 | 0.54 | 2268000
35145004 |  | HOLD |  | 0.62 | 0.62 | 2021 |  |  |  | 92878.97 | PEND | 14161106 | ROSSMOOR 1106 | ROSSMOOR 1106CB | 60 | 1.8254 | 3259 | 0.00030957 | 5.1594e-06 | 2856 | 0.00010409 | 1372 | Tier 3 | PSPS | LAFAYETTE | CONTRA COSTA | Diablo | Bay Area | 5788782 | E.5025642 | 118263746 | 35145004 | PSPS - Rossmoor 1106 – CB | 0 | 4171.2 | 0 | 0 |  | 2019-79022 | 2112 | 0.4 | 3720000 | N/A | 0 | 4171.2 | 0 | 4171.2 | 0.79 | 3318000 | 2020-31291
35072360 |  | HOLD |  | 1.05 | 1.05 | 2021 |  |  |  | 795742.36 | CONS | 163692102 | SALT SPRINGS 2102 | SALT SPRINGS 21023142 | 256 | 17.9625 | 2659 | 0.22061 | 0.00086175 | 2600 | 0.0086401 | 8 | Tier 3 | PRE | ARNOLD | Calaveras | Stockton | Central Valley | 5783906 | E.5015236.01 | 114754229 | 35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 | 5541 | 0 | 0 | 0 |  | 2018-60542 | 7708.8 | 1.46 | 1574171 | 2019-35904 | 0 | 0 | 5305 | 5305 | 1.0047 | 1929090.9091 | 2019-64378 | 2020-45688 | 0 | 0 | 5541 | 5541 | 1.0494 | 1932059 | 2583069 | 348.6842
35144944 |  | HOLD |  | 0.26 | 0.26 | 2021 |  |  |  | 120321.05 | PEND | 22721107 | SNEATH LANE 1107 | SNEATH LANE 1107CB | 45 | 1.0038 | 2336 | 0.14045 | 0.003121 | 2144 | 0.036015 | 2845 | Tier 3 | PSPS | SOUTH SAN FRANCISO | SAN MATEO | Peninsula | Central Coast | 5530170 |  | 118261958 | 35144944 | PSPS – Sneath Lane 1107 – CB | 0 | 739.2 | 0 | 0 |  | 2019-78877 | 739.2 | 0.14 | 738936 | N/A | 0 | 739.2 | 0 | 739.2 | 0.14 | 588000 | 2020-18832
35145006 |  | HOLD |  | 0.27 | 0.27 | 2021 |  |  |  | 127463.52 | ESTS | 43201101 | STAFFORD 1101 | STAFFORD 1101902998 | 81 | 1.0766 | 3483 | 0.00018615 | 2.2981e-06 | 3428 | 4.6216e-05 | 2388 | Tier 3 | PSPS | NOVATO | MARIN | North Bay | Bay Area | 5788788 | E.5025644 | 118263874 | 35145006 | PSPS - Stafford 1101 - LR 1298 | 0 | 1425.6 | 0 | 0 |  | 2019-79042 | 1425.6 | 0.27 | 2500000 | N/A | 0 | 1425.6 | 0 | 1425.6 | 0.27 | 1134000 | 2020-51115
Note on A424: [REDACTED]: PM# initially created for ECOP. However, found out ECOP project overlaps with CWSP PM# 35046371.Keeping this as ECOP to drive for 2021 construction.
Note on AG424: [REDACTED]: PM# initially created for ECOP. However, found out ECOP project overlaps with CWSP PM# 35046371.Keeping this as ECOP to drive for 2021 construction.
Note on A425: [REDACTED]: PM# initially created for ECOP. However, found out ECOP project overlaps with CWSP PM# 35046371.Keeping this as ECOP to drive for 2021 construction.
Note on AG425: [REDACTED]: PM# initially created for ECOP. However, found out ECOP project overlaps with CWSP PM# 35046371.Keeping this as ECOP to drive for 2021 construction.