## Summary
Values
Job Owner Name | Order | Order Description | Project Reporting Year | Pre-Eng. Complete | Pre-Eng. Mtg Date | Base Map Status | Expected Base Map Complete | Sum of UG Feet | Sum of OH Feet
| 35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 | 2021 | Y | 44245 | N/A |  | 0 | 4752
| 35219266 | CWSP - MARIPOSA 2102CB PH 1 | 2021 | Y | 44249 | N/A | 44286 | 0 | 13713
| 35219268 | CWSP - MARIPOSA 210197142 PH 1 | 2021 | Y | 44235 | In Progress | 44267 | 0 | 8553.6
| 35226241 | CWSP - MARIPOSA 210197142 PH 2 | 2021 | Y | 44235 | In Progress | 44267 | 0 | 7920
| 35227263 | CWSP - MARIPOSA 2102CB PH 2 | 2021 | Y | 44249 | N/A |  | 0 | 1315.42
[8 empty] | 0 | 36254.02
| 35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | 2021 | N | 44300 | In Progress | 44298 | 8106 | 0
| 35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 | 2021 | N | 44307 | In Progress | 44305 | 22892 | 0
| 35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 | 2021 | N | 44348 | In Progress |  | 13200 | 0
| 35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR | 2021 | N | 44348 |  |  | 264 | 0
| 35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 | 2021 | Y | 44245 | N/A |  | 0 | 9153
| 35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 | 2021 | Y | 44245 | N/A |  | 0 | 10475
| 35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 | 2021 | Y | 44256 | N/A |  | 0 | 13164
| 35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 | 2021 | Y | 44256 | N/A | 44305 | 0 | 14807
| 35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 | 2021 | Y | 44256 | N/A |  | 0 | 5438.4
| 35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 | 2021 | Y | 44256 | N/A |  | 0 | 10262
| 35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 | 2021 | Y | 44245 | N/A |  | 0 | 8691
| 35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 | 2021 |  |  | In Progress | 44298 | 1742.4 | 0
| 35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 | 2021 | Y | 44245 | N/A |  | 0 | 7023
| 35232650 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 | 2021 | N | 44348 | In Progress | 44301 | 9028 | 0
| 35232651 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 | 2021 | N | 44348 | N/A |  | 0 | 9187.2
[8 empty] | 55232.4 | 88200.6
| 35192280 | ECOP - CLAYTON 2212 - H01-LR2951 | 2021 | Y | 44253 | In Progress | 44297 | 7075.2 | 0
| 35219093 | CWSP - TIDEWATER 210614072 PH 1.1 | 2021 | Y | 44253 | In Progress |  | 6019 | 0
| 35219096 | CWSP - KIRKER 2104442850 PH 1.1 | 2021 | Y | 44253 | In Progress |  | 8817.6 | 0
| 35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 | 2021 | Y | 44253 | N/A |  | 0 | 5544
| 35231543 | CWSP - TIDEWATER 210614072 PH 1.2 | 2021 | Y | 44253 | In Progress |  | 6864 | 0
| 35231544 | CWSP - TIDEWATER 210614072 PH 1.3 | 2021 | Y | 44253 | N/A |  | 0 | 6336
[8 empty] | 28775.8 | 11880
| 35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 | 2021 | Y | 44253 | N/A |  | 0 | 26400
| 35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 | 2021 | N | 44295 | In Progress | 44305 | 2534.4 | 0
| 35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 | 2021 | Y | 44253 | N/A |  | 0 | 12473
| 35223037 | PSPS - OAKHURST 1101 - OAKHURST | 2021 | Y | 44253 | N/A |  | 105.6 | 0
| 35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 | 2021 | Y | 44253 | N/A |  | 0 | 13833.6
| 35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 | 2021 | Y | 44253 | N/A |  | 0 | 12443
| 35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 | 2021 | Y | 44253 | N/A |  | 0 | 11421
| 35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 | 2021 | Y | 44253 | N/A |  | 0 | 6152
| 35026643 | DIAMOND SPRINGS 1105 - LR 2102 | 2021 | N | 44278 | N/A |  | 0 | 8553.6
[8 empty] | 2640 | 91276.2
| 35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 | 2021 | Y | 44249 | In Progress | 44298 | 5860 | 0
| 35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 | 2021 | Y | 44238 | In Progress | 44274 | 4224 | 0
| 35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 | 2021 | Y | 44238 | In Progress | 44274 | 2481.6 | 0
| 35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 | 2021 | Y | 44238 | N/A |  | 0 | 5860
| 35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 | 2021 | Y | 44238 | N/A |  | 0 | 3907.2
| 35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 | 2021 | Y | 44238 | N/A |  | 0 | 4857.6
| 35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 | 2021 | Y | 44249 | N/A |  | 0 | 15153
| 35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 | 2021 | Y | 44249 | In Progress | 44298 | 9398 | 0
| 35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 | 2021 | Y | 44249 | N/A |  | 0 | 9187
| 35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 | 2021 | Y | 44249 | N/A |  | 0 | 11563
| 35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 | 2021 | Y | 44249 | N/A |  | 0 | 3168
[8 empty] | 21963.6 | 53695.8
| 35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 | 2021 | N | 44316 | In Progress |  | 6177.6 | 0
| 35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 | 2021 | N | 44286 |  |  | 0 | 1426
| 35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 | 2021 | N | 44316 |  |  | 10771 | 0
| 35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | 2021 | N | 44316 | In Progress |  | 0 | 2270
| 35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 | 2021 | N | 44316 | In Progress |  | 0 | 2904
| 35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | 2021 | N | 44316 | In Progress |  | 8131 | 0
| 35217273 | SH - UPPER LAKE 1101 CB | 2021 | N |  | In Progress | 44270 | 0 | 5702.4
| 35219272 | CWSP - MIDDLETOWN 1101481876 | 2021 | Y | 44253 |  |  | 0 | 4857.6
| 35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 | 2021 | N | 44286 |  |  | 0 | 8870
| 35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | 2021 | N | 44286 | In Progress |  | 10190 | 1162
| 35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | N | 44316 | In Progress |  | 1478 | 0
| 35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | N | 44286 |  |  | 0 | 4699
| 35223615 | ECOP - LAS GALLINAS A 1105 PH 2 | 2021 | N | 44316 | In Progress |  | 8606.4 | 0
| 35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 | 2021 | N | 44316 | In Progress |  | 0 | 4699.2
| 35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 | 2021 | N | 44286 | In Progress |  | 0 | 4224
| 35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 | 2021 | N | 44316 |  |  | 8184 | 0
| 35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 | 2021 | N | 44286 |  |  | 0 | 4013
| 35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 | 2021 | N | 44286 |  |  | 0 | 6072
| 35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 | 2021 | N | 44286 |  |  | 0 | 7709
| 35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 | 2021 | N | 44316 |  |  | 792 | 0
| 35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | 2021 | N | 44316 |  |  | 0 | 10507
| 35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 | 2021 | N | 44286 |  |  | 0 | 4171
| 35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 | 2021 | N | 44286 |  |  | 0 | 3168
| 35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 | 2021 | N | 44286 |  |  | 0 | 5491
| 35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 | 2021 | N | 44286 | In Progress |  | 7287 | 1796
| 35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 | 2021 | N | 44286 | In Progress |  | 8184 | 2534
| 35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | 2021 | N | 44316 | In Progress |  | 6970 | 0
| 35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | 2021 | N | 44316 |  |  | 0 | 3907
| 35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | 2021 | N | 44316 | In Progress |  | 1690 | 0
| 35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | 2021 | N | 44316 |  |  | 0 | 2429
| 35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | 2021 | N | 44316 |  |  | 0 | 4752
| 35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | 2021 | N | 44316 | In Progress |  | 5333 | 0
| 35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | 2021 | N | 44316 |  |  | 9504 | 0
| 35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | 2021 | N | 44316 |  |  | 8290 | 0
| 35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | 2021 | N | 44286 |  |  | 0 | 1056
| 35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | 2021 | N | 44286 |  |  | 0 | 8026
| 35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | 2021 | N | 44286 |  |  | 0 | 5755
| 35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | 2021 | N | 44286 |  |  | 0 | 4171
| 35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | 2021 | N | 44316 | In Progress |  | 3274 | 0
| 35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | 2021 | N | 44286 |  |  | 0 | 2746
| 35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | 2021 | N | 44286 |  |  | 0 | 5174
| 35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | 2021 | N | 44286 | In Progress |  | 0 | 2112
| 35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | 2021 | N | 44316 | In Progress |  | 7867 | 0
| 35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | 2021 | N | 44286 |  |  | 0 | 3326
[8 empty] | 112729 | 129729.2
| 35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 | 2021 | Y | 44259 | N/A |  | 0 | 2824
| 35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 | 2021 | Y | 44263 | N/A |  | 0 | 7273
| 35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 | 2021 | Y | 44259 | N/A |  | 0 | 5131
| 35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 | 2021 | N |  |  |  | 5491.2 | 0
| 35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 | 2021 | N |  |  |  | 0 | 3761
| 35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 | 2021 | N |  |  |  | 21597 | 0
| 35191318 | ECOP - SILVERADO 2102 - H02-LR58626 | 2021 | Y | 44253 | N/A |  | 0 | 11721.6
| 35191383 | ECOP - SILVERADO 2102 - H01-LR58626 | 2021 | Y | 44253 | N/A |  | 0 | 7075.2
| 35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 | 2021 | N |  | N/A |  | 0 | 7718
| 35192284 | ECOP - SILVERADO 2104 - H05-LR726 | 2021 | N |  | In Progress | 44284 | 10929.6 | 0
| 35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 | 2021 | Y | 44245 | N/A |  | 0 | 3774
| 35223024 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 | 2021 | N |  | In Progress | 44284 | 11827.2 | 0
| 35223026 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 | 2021 | N |  | In Progress | 44284 | 9504 | 0
| 35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 | 2021 | Y | 44253 | N/A |  | 0 | 10190
| 35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 | 2021 | Y | 44259 | N/A |  | 0 | 8026
| 35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 | 2021 | N |  |  |  | 4488 | 0
| 35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 | 2021 | N |  |  |  | 0 | 2006.4
| 35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 | 2021 | N |  |  |  | 0 | 4646.4
| 35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 | 2021 | N |  |  |  | 0 | 3484.8
| 35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 | 2021 | N |  |  |  | 0 | 3062.4
| 35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 | 2021 | N |  | N/A |  | 0 | 2786
| 35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 | 2021 | N |  | N/A |  | 0 | 1724
| 35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 | 2021 | N |  | N/A |  | 0 | 1243
| 35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 | 2021 | N |  | N/A |  | 0 | 2736
| 35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 | 2021 | N |  | N/A |  | 0 | 2215
| 35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 | 2021 | N |  |  |  | 5488 | 0
| 35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 | 2021 | N |  |  |  | 3109 | 0
| 35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 | 2021 | N |  |  |  | 3809 | 0
| 35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 | 2021 | N |  |  |  | 2286 | 0
| 35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 | 2021 | N |  |  |  | 3067 | 0
| 35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 | 2021 | N |  |  |  | 1839 | 0
| 35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 | 2021 | N |  |  |  | 15183 | 0
| 35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 | 2021 | N |  |  |  | 0 | 834
| 35227013 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 | 2021 | N |  |  |  | 0 | 168
| 35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 | 2021 | N |  |  |  | 0 | 5106
| 35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 | 2021 | N |  |  |  | 0 | 6312
| 35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 | 2021 | N |  |  |  | 0 | 1144
| 35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 | 2021 | N |  |  |  | 2900 | 0
| 35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 | 2021 | N |  | N/A |  | 0 | 4600
| 35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 | 2021 | N |  | N/A |  | 0 | 6936
| 35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 | 2021 | Y | 44245 | In Progress | 44267 | 3221 | 0
| 35234756 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | N |  |  |  | 14689 | 0
| 35234758 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | N |  |  |  | 3073 | 0
| 35234862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | N |  |  |  | 422 | 0
| 35234865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | N |  |  |  | 3419 | 0
[8 empty] | 126342 | 116497.8
| 35219273 | CWSP - VOLTA 110149742 | 2021 | Y | 44253 | N/A |  | 0 | 15470
| 35219589 | CWSP - WILDWOOD 11011454 | 2021 |  |  |  |  | 0 | 13622.4
| 35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO | 2021 |  |  |  |  | 0 | 12302.4
| 35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 | 2021 |  |  |  |  | 0 | 8395.2
| 35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 | 2021 |  |  |  |  | 1003.2 | 0
[8 empty] | 1003.2 | 49790
| 35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 | 2021 |  |  |  |  | 6124 | 420
| 35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 | 2021 |  |  |  |  | 2552 | 1168
[8 empty] | 8676 | 1588
| 35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 | 2021 |  |  | In Progress | 44323 | 0 | 1056
| 35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 | 2021 |  |  | In Progress |  | 1584 | 0
| 35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 | 2021 | Y | 44253 |  |  | 0 | 4224
| 35223030 | PSPS - BANGOR 1101 CB - MICROGRID | 2021 |  |  |  |  | 3009.6 | 0
| 35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE | 2021 |  |  | In Progress |  | 4065.6 | 0
| 35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 | 2021 |  |  | In Progress | 44323 | 9134.4 | 0
| 35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 | 2021 |  |  | In Progress | 44323 | 9662.4 | 0
| 35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 | 2021 |  |  | N/A |  | 0 | 1531.2
| 35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 | 2021 |  |  | In Progress |  | 4329.6 | 0
| 35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 | 2021 |  |  | In Progress |  | 23760 | 0
| 35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 | 2021 |  |  | N/A |  | 0 | 7603.2
| 35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 | 2021 |  |  | N/A |  | 0 | 8131.2
| 35226700 | CWSP - WYANDOTTE 110932586 PH 1.2 | 2021 |  |  | In Progress |  | 3010 | 0
[8 empty] | 58555.6 | 22545.6
| 35219286 | CWSP - DESCHUTES 11049718 PH1.1 | [5 empty] | 0 | 18241
[8 empty] | 0 | 18241
| 35225825 | CWSP - DESCHUTES 11049718 PH2.1 | [5 empty] | 0 | 8217
| 35232442 | CWSP - DESCHUTES 11049718 PH 2.2 | [5 empty] | 0 | 16251
| 35232443 | CWSP - DESCHUTES 11049718 PH 2.3 | [5 empty] | 0 | 5468
| 35232444 | CWSP - DESCHUTES 11049718 PH 2.4 | [5 empty] | 0 | 18648
| 35232445 | CWSP - DESCHUTES 11049718 PH 2.5 | [5 empty] | 0 | 13748
| 35232960 | CWSP - DESCHUTES 11049718 PH1.2 | [5 empty] | 0 | 16057
[8 empty] | 0 | 78389
[8 empty] | 415917.6 | 698087.22

## Data
Order | Job Owner Name | Project Reporting Year | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | 2023 Forecast Feet | 2023 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Program | Ready to Break Ground | Pre-Eng. Mtg Date | Pre-Eng. Complete | EOD Forecast | Previous EOD Forecast | Prelim Dwg Forecast | Previous Prelim Dwg Forecast | Prelim Dwg Out | PEND IN Date | --1 | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Base Map Status | Expected Base Map Complete | Base Map Vendor | Surveyor | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | --2 | Expected Permit Date | Permits Complete | --3 | Veg Complete | Veg Completed | Veg Start | --4 | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | 2021 Feet Installed | 2021 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | --5 | Auth Amt without Contingency (Expected Case) | Total EAC | --6 | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Circuit Protection Zone | Risk Rank | Segmentation ID# | Project Type | Last Edited By | Last Edited Date | Blank 1
35026643 |  | 2021 | DIAMOND SPRINGS 1105 - LR 2102 |  | Scoped | UNSE | 7400 | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2022-06-10 17:00 | 2021-03-23 | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-06-10 17:00 |  | INPR | 2022-06-29 11:00 |  | 100000 | 1882335.5 |  | 22 |  | Still need to be scoped / table topped | [7 empty] | El Dorado | El Dorado | 0 | 0 | 35026643 | MX | OH |  | 999 |  |  |  |  | DIAMOND SPRINGS 11052102 | 666 |  | WDDB |  | 2021-03-11 17:02
35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Scoped | UNSE |  | 8106 | 0 | 8106 | 1.5352 | 0 | 0 | 0 | 0 | 8106 | 1.5352 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-04-14 | N | 2021-05-31 | [13 empty] | In Progress | 2021-04-12 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5352 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-29 08:00 |  | 220000 | 4904599.4 |  |  |  | Site survey requested 3/9/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-11 16:34
35062375 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Scoped | UNSE |  | 5860 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-10-14 17:00 | 2021-02-22 | Y | 2021-05-31 | [13 empty] | In Progress | 2021-04-12 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-14 17:00 |  | INPR | 2022-01-10 08:00 | [14 empty] | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-11 16:26
35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Scoped | UNSE |  | 22892 | 0 | 22892 | 4.3356 | 0 | 0 | 0 | 0 | 22892 | 4.3356 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-04-21 | N | [14 empty] | In Progress | 2021-04-19 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.3356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 220000 | 8027019.4 |  |  |  | Site survey requested 2/25/2021 |  | Prioritized |  |  | SCADA |  |  | Shingle Springs | El Dorado | 0 | 0 | [10 empty] | 159 | 35062376 | PRE |  | 2021-03-11 10:00
35137590 |  | 2021 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Scoped | ESTS | 2824 | 0 | 2824 | 2824 | 0.53485 | 0 | 0 | 2824 | 0.53485 | 0 | 0 | 0 | 0 | 1.5152e-10 |  |  | HB | 08W | SH | 2021-04-15 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | [10 empty] | 2021-04-05 | 2021-03-31 | N/A |  |  |  |  | 2021-04-05 | 2021-03-31 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.53485 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-29 17:00 |  | N/A | 2021-11-08 08:00 |  | 80000 | 50802.7 |  |  |  |  | Complete | Prioritized | [5 empty] | Middletown | Lake | 38.7927 | -122.6592 | 35137590 |  |  | 2021-056 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 1101CB | 86 |  | ECOP |  | 2021-03-11 14:14
35137593 |  | 2021 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Scoped | ESTS | 7273 | 0 | 7273 | 7273 | 1.3775 | 0 | 0 | 7273 | 1.3775 | 0 | 0 | 0 | 0 | -2.1212e-10 |  |  | HB | 08W | SH | 2021-04-27 17:00 | 2021-03-08 | Y | 2021-04-15 | 2021-04-15 | [10 empty] | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3775 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-04-27 17:00 |  | N/A | 2021-10-14 08:00 |  | 80000 | 56474.5 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137593 |  |  | 2021-054 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 11014646 | 328 |  | ECOP |  | 2021-03-11 14:14
35137596 |  | 2021 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Scoped | ESTS | 5131 | 0 | 5131 | 5131 | 0.97178 | 0 | 0 | 5131 | 0.97178 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-23 | 2021-03-04 | Y | 2021-04-15 | 2021-04-15 | [10 empty] | 2021-04-23 |  | N/A |  |  |  |  | 2021-04-23 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97178 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-03-30 17:00 |  | N/A | 2021-10-26 08:00 |  | 80000 | 37548.6 |  |  |  |  | Complete | Prioritized | [5 empty] | Cobb | Lake | 38.7927 | -122.6592 | 35137596 |  |  | 2021-055 | 2021 |  |  |  | 2020-09-01 | MIDDLETOWN 11014646 | 328 |  | ECOP |  | 2021-03-11 14:14
35174478 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Scoped | UNSE |  | 5491.2 | 0 | 5491.2 | 1.04 | 0 | 0 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2022-01-17 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-061 | 2021 |  |  |  |  | MIDDLETOWN 1101548 | 474 | 35174478 | ECOP |  | 2021-03-11 13:58
35174479 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Scoped | UNSE |  | 0 | 3761 | 3761 | 0.71231 | 0 | 0 | 0 | 0 | 3761 | 0.71231 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71231 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7576 | -122.6358 |  |  |  | 2021-063 | 2021 | [5 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 13:59
35174501 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Scoped | UNSE |  | 21597 | 0 | 21597 | 4.0903 | 0 | 0 | 0 | 0 | 21597 | 4.0903 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-01-17 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.0903 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.3526 | -122.5226 |  |  |  | 2021-065 | 2021 | [5 empty] | 474 | 35174501 | ECOP |  | 2021-03-11 13:59
35191318 |  | 2021 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Scoped | ESTS |  | 0 | 11721.6 | 11721.6 | 2.22 | 0 | 0 | 11722 | 2.2201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-06-11 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.22 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-11 17:00 |  | N/A | 2021-07-01 08:00 |  | 682400 | 45162.4 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5095 | -122.386 | [10 empty] | 663 |  | ECOP |  | 2021-03-12 09:13
35191319 |  | 2021 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Scoped | UNSE |  | 6177.6 | 0 | 6177.6 | 1.17 | 0 | 0 | 0 | 0 | 6178 | 1.1701 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.17 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 |  | 312500 | [12 empty] | Nicasio | Marin | 38.046 | -122.646 | [10 empty] | 215 | 35191319 | ECOP |  | 2021-03-11 10:43
35191383 |  | 2021 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Scoped | ESTS |  | 0 | 7075.2 | 7075.2 | 1.34 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH | 2021-06-07 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-07 17:00 |  | N/A | 2021-08-16 08:00 |  | 614000 | 34923.2 | [5 empty] | Prioritized | [5 empty] | Saint Helena | Napa | 38.5057 | -122.401 | [10 empty] | 663 |  | ECOP |  | 2021-03-12 09:13
35191937 |  | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Scoped | UNSE |  | 0 | 7718 | 7718 | 1.4617 | 0 | 0 | 0 | 0 | 7718 | 1.4617 | 0 | 0 | 0 |  |  | NB | 08W | SH |  |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4617 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 237833 | [12 empty] | Napa | Napa | 38.4108 | -122.4506 | [10 empty] | 951 | 35191937 | ECOP |  | 2021-03-11 14:15
35192280 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Scoped | UNSE |  | 7075.2 | 0 | 7075.2 | 1.34 | 0 | 0 | 0 | 0 | 7075 | 1.34 | 0 | 0 | 3.7879e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress | 2021-04-11 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.34 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 550000 | 91561.9 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8682 | -121.8573 | [10 empty] | 377 | 35192280 | ECOP |  | 2021-03-11 12:49
35192281 |  | 2021 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Scoped | UNSE |  | 0 | 1426 | 1426 | 0.27008 | 0 | 0 | 1426 | 0.27008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-03-31 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-11 10:41
35192282 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Scoped | UNSE |  | 10771 | 0 | 10771 | 2.04 | 0 | 0 | 0 | 0 | 10771 | 2.04 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7238 | -122.6197 | [10 empty] | 468 | 35192282 | ECOP |  | 2021-03-11 10:43
35192284 |  | 2021 | ECOP - SILVERADO 2104 - H05-LR726 |  | Scoped | UNSE |  | 10929.6 | 0 | 10929.6 | 2.07 | 0 | 0 | 10930 | 2.0701 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | NB | 08W | SH | 2021-07-28 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.07 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-28 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | 155254 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6154 | -122.4315 | [10 empty] | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35192290 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Scoped | ADER |  | 0 | 26400 | 26400 | 5 | 0 | 0 | 26400 | 5 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-07-01 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-12 | 2021-03-04 | [11 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | INPR | 2021-07-26 08:00 |  | 950000 | 6927773.6 | [11 empty] | Placerville | El Dorado | 38.739 | -120.9057 |  | MX | OH | [7 empty] | 811 |  | ECOP |  | 2021-03-11 16:21
35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Scoped | UNSE |  | 2534.4 | 0 | 2534.4 | 0.48 | 0 | 0 | 0 | 0 | 2534 | 0.47992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-11-10 17:00 | 2021-04-09 | N | 2021-04-30 | 2021-04-30 | [12 empty] | In Progress | 2021-04-19 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-10 17:00 |  | INPR | 2022-02-04 08:00 |  | 500000 | 1628399 | [11 empty] | Placerville | El Dorado | 38.7215 | -120.8714 |  | MX | MX | [7 empty] | 811 | 35192291 | ECOP |  | 2021-03-11 15:56
35192292 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Scoped | UNSE |  | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-11-16 17:00 | 2021-02-11 | Y | [14 empty] | In Progress | 2021-03-19 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-16 17:00 |  | INPR | 2022-01-19 08:00 |  | 250000 | [6 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.5527 | -122.7132 |  | ML | UG | [7 empty] | 637 | 35192292 | ECOP |  | 2021-03-05 14:52
35217267 |  | 2021 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Scoped | ESTS |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-14 17:00 | 2021-02-18 | Y | 2021-03-31 | 2021-03-12 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-14 17:00 |  | N/A | 2021-06-28 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.4871 | -119.9619 | [10 empty] | 10 |  | CWSP |  | 2021-03-11 10:16
35217268 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 453 | 0.085795 | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 |  |  |  | 2021-04-22 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | 145304.2 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP |  | 2021-03-03 12:30
35217269 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Scoped | UNSE |  | 0 | 2270 | 2270 | 0.42992 | 0 | 0 | 0 | 0 | 2270 | 0.42992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-11 10:39
35217270 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Scoped | ESTS |  | 0 | 2904 | 2904 | 0.55 | 0 | 0 | 0 | 0 | 2904 | 0.55 | 0 | 0 | 0 | 2516 | 0.47652 | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 31399.3 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.9301 | -122.7429 | [10 empty] | 9 | 35217270 | CWSP |  | 2021-03-11 10:40
35217271 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Scoped | UNSE |  | 8131 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-11 10:40
35217272 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Scoped | UNSE |  | 1584 | 0 | 1584 | 0.3 | 0 | 0 | 0 | 0 | 1584 | 0.3 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35217273 |  | 2021 | SH - UPPER LAKE 1101 CB |  | Scoped | UNSE |  | 0 | 5702.4 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 5702.4 | 1.08 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-10-14 17:00 |  | N | [14 empty] | In Progress | 2021-03-15 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-14 17:00 |  | N/A | 2021-11-15 08:00 |  | 500000 | 30132.8 | [5 empty] | Prioritized | [5 empty] | Upper Lake | Lake | 39.353 | -122.7722 | [10 empty] | 6 |  | CWSP |  | 2021-03-11 16:51
35219093 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Scoped | UNSE |  | 6019 | 0 | 6019 | 1.14 | 0 | 0 | 0 | 0 | 6019 | 1.14 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 350000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35219096 |  | 2021 | CWSP - KIRKER 2104442850 PH 1.1 |  | Scoped | UNSE |  | 8817.6 | 0 | 8817.6 | 1.67 | 0 | 0 | 0 | 0 | 8818 | 1.6701 | 0 | 0 | -7.5758e-05 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 500000 | 7818.8 | [11 empty] | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | 21 | 35219096 | CWSP |  | 2021-03-11 12:49
35219097 |  | 2021 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Scoped | ESTS |  | 0 | 12473 | 12473 | 2.3623 | 0 | 0 | 12473 | 2.3623 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-02 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3623 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-02 17:00 |  | INPR | 2021-07-13 08:00 |  | 275000 | 2096158.8 | [11 empty] | Coarsegold | Madera | 37.2276 | -119.6896 |  | ML | OH | [7 empty] | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35219098 |  | 2021 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Scoped | UNSE |  | 0 | 3774 | 3774 | 0.71477 | 0 | 0 | 3774 | 0.71477 | 0 | 0 | 0 | 0 | 0 | 3709 | 0.70246 | HB | 08W | SH | 2021-09-13 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71477 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-09-13 17:00 |  | N/A | 2021-10-15 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | 23 | 35219098 | CWSP |  | 2021-03-11 16:54
35219260 |  | 2021 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-04-02 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Feather Falls | Butte | 39.4631 | -121.5149 | [10 empty] | 29 | 35219260 | CWSP |  | 2021-03-12 09:13
35219266 |  | 2021 | CWSP - MARIPOSA 2102CB PH 1 |  | Scoped | ESTS |  | 0 | 13713 | 13713 | 2.5972 | 0 | 0 | 13713 | 2.5972 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-05-17 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | 2021-03-31 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5972 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-17 17:00 |  | N/A | 2021-06-09 08:00 | [14 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | 35 | 35219266 | CWSP |  | 2021-03-11 10:28
35219268 |  | 2021 | CWSP - MARIPOSA 210197142 PH 1 |  | Scoped | ESTS |  | 0 | 8553.6 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [10 empty] | 2021-04-19 |  | In Progress | 2021-03-12 |  |  |  | 2021-04-19 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  |  | 2021-08-31 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | 36 | 35219268 | CWSP |  | 2021-03-11 10:06
35219272 |  | 2021 | CWSP - MIDDLETOWN 1101481876 |  | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4857.6 | 0.92 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-16 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 950000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7628 | -122.6133 | [10 empty] | 38 |  | CWSP |  | 2021-03-12 09:14
35219273 |  | 2021 | CWSP - VOLTA 110149742 |  | Scoped | ADER |  | 0 | 15470 | 15470 | 2.9299 | 0 | 0 | 15470 | 2.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-07-01 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-12 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-01 17:00 |  | N/A | 2021-07-26 08:00 | [8 empty] | Prioritized | [5 empty] | Manton | Tehama | 40.4305 | -121.8716 | [10 empty] | 39 |  | CWSP |  | 2021-03-12 09:14
35219280 |  | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Scoped | UNSE |  | 0 | 8870 | 8870 | 1.6799 | 0 | 0 | 8870 | 1.6799 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | 2021-04-30 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | 43 | 35219280 | CWSP |  | 2021-03-11 10:42
35219281 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Scoped | UNSE |  | 13200 | 0 | 13200 | 2.5 | 0 | 0 | 0 | 0 | 13200 | 2.5 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | [12 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP |  | 2021-03-11 10:09
35219286 |  |  | CWSP - DESCHUTES 11049718 PH1.1 |  | Scoped | UNSE |  | 0 | 18241 | 18241 | 3.4547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4547 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35219286 | CWSP |  | 2021-03-09 17:18
35219589 |  | 2021 | CWSP - WILDWOOD 11011454 |  | Scoped | UNSE |  | 0 | 13622.4 | 13622.4 | 2.58 | 0 | 0 | 0 | 0 | 13622 | 2.5799 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 |  | CWSP |  | 2021-03-11 09:28
35220895 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Scoped | UNSE |  | 10190 | 1162 | 11352 | 2.15 | 0 | 0 | 1162 | 0.22008 | 10190 | 1.9299 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | 14 | 35220895 | CWSP |  | 2021-03-11 10:42
35220896 |  |  | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Scoped | UNSE |  | 1478 | 0 | 1478 | 0.27992 | 0 | 0 | 0 | 0 | 1478 | 0.27992 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | 14 | 35220896 | CWSP |  | 2021-03-05 11:42
35222045 |  |  | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Scoped | UNSE |  | 0 | 4699 | 4699 | 0.88996 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Pope Valley | Napa | 38.7569 | -122.607 | [10 empty] | 14 | 35222045 | CWSP |  | 2021-03-05 11:43
35223024 |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 2 |  | Scoped | UNSE |  | 11827.2 | 0 | 11827.2 | 2.24 | 0 | 0 | 11827 | 2.24 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NB | 08W | SH | 2021-06-08 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.24 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-08 17:00 |  | N/A | 2021-08-16 08:00 |  | 190000 | [6 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35223026 |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 3 |  | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-07-07 17:00 |  | N | [14 empty] | In Progress | 2021-03-29 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-07 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | [6 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP |  | 2021-03-11 13:59
35223027 |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Scoped | ESTS |  | 0 | 10190 | 10190 | 1.9299 | 0 | 0 | 10190 | 1.9299 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-05-21 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-21 17:00 |  | N/A | 2021-08-17 08:00 |  | 190000 | 34848.7 | [5 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP |  | 2021-03-12 09:14
35223028 |  | 2021 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Scoped | ESTS |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2021-04-30 | 2021-03-04 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [9 empty] | Prioritized | [5 empty] | Pope Valley | Napa | 38.6152 | -122.4293 | [10 empty] | 279 | 35192284 | ECOP |  | 2021-03-11 14:16
35223030 |  | 2021 | PSPS - BANGOR 1101 CB - MICROGRID |  | Scoped | UNSE |  | 3009.6 | 0 | 3009.6 | 0.57 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 950000 | [12 empty] | Bangor | Butte | 39.3878 | -121.4038 | [10 empty] | 355 |  | PSPS |  | 2021-03-11 09:29
35223036 |  | 2021 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Scoped | UNSE |  | 264 | 0 | 264 | 0.05 | 0 | 0 | 0 | 0 | 264 | 0.05 | 0 | 0 | 0 |  |  | SI | 08W | SH |  | 2021-06-01 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 500000 | [12 empty] | Grass Valley | Nevada | 39.2376 | -121.0592 | [10 empty] | 2134 |  | PSPS |  | 2021-03-11 09:59
35223037 |  | 2021 | PSPS - OAKHURST 1101 - OAKHURST |  | Scoped | ESTS |  | 105.6 | 0 | 105.6 | 0.02 | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | INPR |  |  | 500000 | 280281.3 | [11 empty] | Oakhurst | Madera | 37.3227 | -119.6344 |  | ML | UG | [7 empty] | 847 |  | PSPS |  | 2021-03-11 15:59
35223039 |  | 2021 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Scoped | UNSE |  | 4065.6 | 0 | 4065.6 | 0.77 | 0 | 0 | 0 | 0 | 4066 | 0.77008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 950000 | [12 empty] | Oroville | Butte | 39.4738 | -121.5307 | [10 empty] | 218 |  | PSPS |  | 2021-03-11 10:10
35223615 |  | 2021 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Scoped | UNSE |  | 8606.4 | 0 | 8606.4 | 1.63 | 0 | 0 | 0 | 0 | 8606 | 1.6299 | 0 | 0 | 7.5758e-05 |  |  | NB | 08W | SH | 2021-08-20 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.63 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | N/A | 2021-09-14 08:00 |  | 312500 | 1320.1 | [11 empty] | San Rafael | Marin | 38.0443 | -122.6155 | [10 empty] | 215 | 35191319 | ECOP |  | 2021-03-05 11:43
35224321 |  | 2021 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Scoped | ESTS |  | 0 | 12302.4 | 12302.4 | 2.33 | 0 | 0 | 0 | 0 | 12302 | 2.3299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP |  | 2021-03-11 09:28
35224712 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Scoped | UNSE |  | 9134.4 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 0 | 9134 | 1.7299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.73 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 390621.4 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP |  | 2021-03-03 09:26
35224713 |  | 2021 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Scoped | UNSE |  | 9662.4 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 0 | 9662 | 1.8299 | 0 | 0 | 7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | 2021-05-07 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 389909.1 | [5 empty] | Prioritized | [5 empty] | Belden | Plumas | 0 | 0 | [10 empty] | 11 | 35217268 | CWSP |  | 2021-03-03 09:26
35225589 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Scoped | UNSE |  | 0 | 4699.2 | 4699.2 | 0.89 | 0 | 0 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 14484.8 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | 9 | 35217270 | CWSP |  | 2021-03-05 11:44
35225591 |  | 2021 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Scoped | ESTS |  | 0 | 4224 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-03-31 | 2021-03-12 | [12 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316666 | 14378.3 | [5 empty] | Prioritized | [5 empty] | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | 9 | 35217270 | CWSP |  | 2021-03-11 10:44
35225593 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Scoped | ADER |  | 0 | 5544 | 5544 | 1.05 | 0 | 0 | 5544 | 1.05 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH | 2021-03-31 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.05 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 400000 | 44099.7 | [5 empty] | Prioritized | [5 empty] | Clayton | Contra Costa | 37.8879 | -121.8676 | [10 empty] | 377 | 35192280 | ECOP |  | 2021-03-11 12:49
35225594 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Scoped | UNSE |  | 2481.6 | 0 | 2481.6 | 0.47 | 0 | 0 | 0 | 0 | 2482 | 0.47008 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-11-02 17:00 | 2021-02-11 | Y | [14 empty] | In Progress | 2021-03-19 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-11-02 17:00 |  | INPR | 2022-01-05 08:00 |  | 250000 | [6 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | ML | UG | [7 empty] | 637 | 35192292 | ECOP |  | 2021-03-05 14:52
35225595 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Scoped | UNSE |  | 0 | 5860 | 5860 | 1.1098 | 0 | 0 | 5860 | 1.1098 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | SH | 2021-08-20 17:00 | 2021-02-11 | Y | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-20 17:00 |  | INPR | 2021-09-14 08:00 |  | 150000 | [6 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP |  | 2021-03-11 14:35
35225597 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Scoped | ESTS |  | 0 | 3907.2 | 3907.2 | 0.74 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SO | 08W | SH | 2021-07-28 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-28 17:00 |  | INPR | 2021-08-20 08:00 |  | 150000 | [6 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP |  | 2021-03-11 14:34
35225598 |  | 2021 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Scoped | ESTS |  | 0 | 4857.6 | 4857.6 | 0.92 | 0 | 0 | 4858 | 0.92008 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | SH | 2021-08-06 17:00 | 2021-02-11 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.92 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | INPR | 2021-08-31 08:00 |  | 150000 | [6 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | TL | OH | [7 empty] | 637 | 35192292 | ECOP |  | 2021-03-11 14:34
35225825 |  |  | CWSP - DESCHUTES 11049718 PH2.1 |  | Scoped | UNSE |  | 0 | 8217 | 8217 | 1.5562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5562 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35226241 |  | 2021 | CWSP - MARIPOSA 210197142 PH 2 |  | Scoped | ESTS |  | 0 | 7920 | 7920 | 1.5 | 0 | 0 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-08-06 17:00 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [10 empty] | 2021-04-20 |  | In Progress | 2021-03-12 |  |  |  | 2021-04-20 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-06 17:00 |  | N/A | 2021-08-31 08:00 | [8 empty] | Prioritized | [5 empty] | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | 36 | 35219268 | CWSP |  | 2021-03-11 10:06
35226621 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Scoped | UNSE |  | 8184 | 0 | 8184 | 1.55 | 0 | 0 | 0 | 0 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-04-30 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.55 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP |  | 2021-03-11 10:40
35226622 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Scoped | UNSE |  | 0 | 4013 | 4013 | 0.76004 | 0 | 0 | 4013 | 0.76004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.76004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226623 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Scoped | UNSE |  | 0 | 6072 | 6072 | 1.15 | 0 | 0 | 6072 | 1.15 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226624 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Scoped | UNSE |  | 0 | 7709 | 7709 | 1.46 | 0 | 0 | 7709 | 1.46 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 | 2021-03-31 | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.46 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192282 | ECOP |  | 2021-03-05 11:45
35226627 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Scoped | UNSE |  | 0 | 1531.2 | 1531.2 | 0.29 | 0 | 0 | 1531 | 0.28996 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226628 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Scoped | UNSE |  | 4329.6 | 0 | 4329.6 | 0.82 | 0 | 0 | 0 | 0 | 4330 | 0.82008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35226629 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Scoped | UNSE |  | 23760 | 0 | 23760 | 4.5 | 0 | 0 | 0 | 0 | 23760 | 4.5 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 200000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-04 09:51
35226630 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Scoped | UNSE |  | 0 | 7603.2 | 7603.2 | 1.44 | 0 | 0 | 7608 | 1.4409 | 0 | 0 | 0 | 0 | -0.00090909 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226631 |  | 2021 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Scoped | UNSE |  | 0 | 8131.2 | 8131.2 | 1.54 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 150000 | [12 empty] | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | 7 | 35217272 | CWSP |  | 2021-03-11 10:12
35226632 |  | 2021 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Scoped | UNSE |  | 792 | 0 | 792 | 0.15 | 0 | 0 | 0 | 0 | 792 | 0.15 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | 2021-04-30 | 2021-04-30 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | 43 | 35219280 | CWSP |  | 2021-03-10 16:57
35226700 |  | 2021 | CWSP - WYANDOTTE 110932586 PH 1.2 |  | Scoped | UNSE |  | 3010 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | 0 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 650000 | [26 empty] | 29 | 35219260 | CWSP |  | 2021-03-04 09:59
35226798 |  | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Scoped | UNSE |  | 0 | 8395.2 | 8395.2 | 1.59 | 0 | 0 | 0 | 0 | 8395 | 1.59 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.59 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP |  | 2021-03-11 09:30
35226799 |  | 2021 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | Scoped | UNSE |  | 1003.2 | 0 | 1003.2 | 0.19 | 0 | 0 | 0 | 0 | 1003 | 0.18996 | 0 | 0 | 3.7879e-05 |  |  | NV | 08W | SH | 2021-06-30 |  |  | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Platina | Shasta | 40.3595 | -122.8928 | [10 empty] | 52 | 35224321 | CWSP |  | 2021-03-11 09:30
35226819 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Scoped | UNSE |  | 0 | 10507 | 10507 | 1.99 | 0 | 0 | 0 | 0 | 10507 | 1.99 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:46
35226845 |  | 2021 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Scoped | ESTS |  | 0 | 13833.6 | 13833.6 | 2.62 | 0 | 0 | 13834 | 2.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | SI | 08W | SH | 2021-06-30 17:00 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.62 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-30 17:00 |  | INPR | 2021-07-23 08:00 |  | 450000 | 2311825 | [11 empty] | Placerville | El Dorado | 38.7201 | -120.861 |  | TL | OH | [7 empty] | 811 | 35192291 | ECOP |  | 2021-03-11 15:59
35226846 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Scoped | ESTS |  | 0 | 9153 | 9153 | 1.7335 | 0 | 0 | 9153 | 1.7335 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7335 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 3054367.7 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-11 10:07
35226847 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Scoped | ESTS |  | 0 | 10475 | 10475 | 1.9839 | 0 | 0 | 10475 | 1.9839 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-20 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9839 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 3777833 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-11 10:07
35226848 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Scoped | ESTS |  | 0 | 15153 | 15153 | 2.8699 | 0 | 0 | 15153 | 2.8699 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-11 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-26 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8699 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-11 17:00 |  | INPR | 2021-08-03 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-11 10:21
35226849 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Scoped | UNSE |  | 9398 | 0 | 9398 | 1.7799 | 0 | 0 | 0 | 0 | 9398 | 1.7799 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-08-27 17:00 | 2021-02-22 | Y | 2021-05-31 | [13 empty] | In Progress | 2021-04-12 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7799 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-27 17:00 |  | INPR | 2021-10-19 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-05 14:57
35226850 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Scoped | ESTS |  | 0 | 9187 | 9187 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-09 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-11 14:33
35226851 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Scoped | ESTS |  | 0 | 11563 | 11563 | 2.19 | 0 | 0 | 11563 | 2.19 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-12 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.19 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-25 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-11 10:20
35226852 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Scoped | ESTS |  | 0 | 13164 | 13164 | 2.4932 | 0 | 0 | 13164 | 2.4932 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4932 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 7914215.7 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE |  | 2021-03-11 10:07
35226853 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Scoped | ESTS |  | 0 | 14807 | 14807 | 2.8044 | 0 | 0 | 14807 | 2.8044 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-30 | 2021-04-16 | [12 empty] | N/A | 2021-04-19 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8044 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 5739276.8 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226854 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Scoped | ESTS |  | 0 | 5438.4 | 5438.4 | 1.03 | 0 | 0 | 5438 | 1.0299 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.03 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 2069574.7 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226856 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Scoped | ESTS |  | 0 | 10262 | 10262 | 1.9436 | 0 | 0 | 10262 | 1.9436 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-03-01 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9436 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 8797079.2 | [5 empty] | Prioritized |  |  | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 159 | 35062376 | PRE |  | 2021-03-11 10:06
35226857 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Scoped | UNSE |  | 4488 | 0 | 4488 | 0.85 | 0 | 0 | 0 | 0 | 4488 | 0.85 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP |  | 2021-03-11 13:59
35226858 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Scoped | UNSE |  | 0 | 2006.4 | 2006.4 | 0.38 | 0 | 0 | 0 | 0 | 2006 | 0.37992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226859 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Scoped | UNSE |  | 0 | 4646.4 | 4646.4 | 0.88 | 0 | 0 | 0 | 0 | 4646 | 0.87992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.88 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226861 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Scoped | UNSE |  | 0 | 3484.8 | 3484.8 | 0.66 | 0 | 0 | 0 | 0 | 3485 | 0.66004 | 0 | 0 | -3.7879e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.66 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226862 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Scoped | UNSE |  | 0 | 3062.4 | 3062.4 | 0.58 | 0 | 0 | 0 | 0 | 3062 | 0.57992 | 0 | 0 | 7.5758e-05 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 155000 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174478 | ECOP |  | 2021-02-26 12:06
35226863 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Scoped | UNSE |  | 0 | 2786 | 2786 | 0.52765 | 0 | 0 | 0 | 0 | 2786 | 0.52765 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52765 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226864 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Scoped | UNSE |  | 0 | 1724 | 1724 | 0.32652 | 0 | 0 | 0 | 0 | 1724 | 0.32652 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226865 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Scoped | UNSE |  | 0 | 1243 | 1243 | 0.23542 | 0 | 0 | 0 | 0 | 1243 | 0.23542 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.23542 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 14:16
35226866 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Scoped | UNSE |  | 0 | 2736 | 2736 | 0.51818 | 0 | 0 | 0 | 0 | 2736 | 0.51818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.51818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 14:17
35226870 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Scoped | UNSE |  | 0 | 2215 | 2215 | 0.41951 | 0 | 0 | 0 | 0 | 2215 | 0.41951 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-04-30 |  | N | 2021-04-30 | [13 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41951 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-11 14:17
35226871 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Scoped | UNSE |  | 6124 | 420 | 6544 | 1.2394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-01 13:46
35226872 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Scoped | UNSE |  | 2552 | 1168 | 3720 | 0.70455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 |  |  | HB | 08W | SH | 2021-04-30 |  |  | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70455 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-01 13:46
35226873 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Scoped | UNSE |  | 5488 | 0 | 5488 | 1.0394 | 0 | 0 | 0 | 0 | 5488 | 1.0394 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0394 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35226878 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Scoped | UNSE |  | 3109 | 0 | 3109 | 0.58883 | 0 | 0 | 0 | 0 | 3109 | 0.58883 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58883 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227001 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Scoped | UNSE |  | 3809 | 0 | 3809 | 0.7214 | 0 | 0 | 0 | 0 | 3809 | 0.7214 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7214 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227002 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Scoped | UNSE |  | 2286 | 0 | 2286 | 0.43295 | 0 | 0 | 0 | 0 | 2286 | 0.43295 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.43295 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227003 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Scoped | UNSE |  | 3067 | 0 | 3067 | 0.58087 | 0 | 0 | 0 | 0 | 3067 | 0.58087 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58087 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:27
35227004 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Scoped | UNSE |  | 1839 | 0 | 1839 | 0.3483 | 0 | 0 | 0 | 0 | 1839 | 0.3483 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3483 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 67857 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174479 | ECOP |  | 2021-03-09 14:28
35227007 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Scoped | UNSE |  | 15183 | 0 | 15183 | 2.8756 | 0 | 0 | 0 | 0 | 15183 | 2.8756 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8756 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-02-26 12:06
35227010 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Scoped | UNSE |  | 0 | 834 | 834 | 0.15795 | 0 | 0 | 0 | 0 | 834 | 0.15795 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15795 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-02-26 13:16
35227013 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.4 |  | Scoped | UNSE |  | 0 | 168 | 168 | 0.031818 | 0 | 0 | 0 | 0 | 168 | 0.031818 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.031818 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-02-26 13:17
35227015 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Scoped | UNSE |  | 0 | 5106 | 5106 | 0.96705 | 0 | 0 | 0 | 0 | 5106 | 0.96705 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96705 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-02-26 12:06
35227018 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Scoped | UNSE |  | 0 | 6312 | 6312 | 1.1955 | 0 | 0 | 0 | 0 | 6312 | 1.1955 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1955 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-11 14:00
35227021 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Scoped | UNSE |  | 0 | 1144 | 1144 | 0.21667 | 0 | 0 | 0 | 0 | 1144 | 0.21667 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21667 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-02-26 13:18
35227025 |  | 2021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Scoped | UNSE |  | 2900 | 0 | 2900 | 0.54924 | 0 | 0 | 0 | 0 | 2900 | 0.54924 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2022-09-27 17:00 |  | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-09-27 17:00 |  | N/A | 2022-11-01 08:00 |  | 118750 | [12 empty] | Middletown | Lake | 38.7577 | -122.6359 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-04 09:07
35227027 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | 2021-04-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-05 11:46
35227028 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Scoped | UNSE |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-05 11:46
35227029 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Scoped | UNSE |  | 0 | 5491 | 5491 | 1.04 | 0 | 0 | 5491 | 1.04 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.04 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227030 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Scoped | UNSE |  | 7287 | 1796 | 9083 | 1.7203 | 0 | 0 | 1796 | 0.34015 | 7287 | 1.3801 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7203 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227031 |  | 2021 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Scoped | UNSE |  | 8184 | 2534 | 10718 | 2.0299 | 0 | 0 | 2534 | 0.47992 | 8184 | 1.55 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-30 | 2021-03-31 | N | 2021-06-30 | [13 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0299 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7249 | -122.6186 | [10 empty] | 468 | 35192281 | ECOP |  | 2021-03-05 11:47
35227032 |  | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Scoped | UNSE |  | 0 | 4600 | 4600 | 0.87121 | 0 | 0 | 0 | 0 | 4600 | 0.87121 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2022-01-17 17:00 |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.87121 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-02-04 08:00 |  | 237833 | [12 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | 951 | 35191937 | ECOP |  | 2021-03-11 14:18
35227033 |  | 2021 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Scoped | UNSE |  | 0 | 6936 | 6936 | 1.3136 | 0 | 0 | 0 | 0 | 6936 | 1.3136 | 0 | 0 | 0 |  |  | NB | 08W | SH | 2022-01-17 17:00 |  | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3136 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2022-01-17 17:00 |  | N/A | 2022-02-04 08:00 |  | 237833 | [12 empty] | Napa | Napa | 38.433 | -122.4021 | [10 empty] | 951 | 35191937 | ECOP |  | 2021-02-26 12:07
35227160 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Scoped | UNSE |  | 6970 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-08-17 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-08-17 17:00 |  | N/A | 2021-09-09 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:48
35227161 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Scoped | UNSE |  | 0 | 3907 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:48
35227162 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Scoped | UNSE |  | 1690 | 0 | 1690 | 0.32008 | 0 | 0 | 0 | 0 | 1690 | 0.32008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227163 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Scoped | UNSE |  | 0 | 2429 | 2429 | 0.46004 | 0 | 0 | 0 | 0 | 2429 | 0.46004 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227164 |  | 2021 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Scoped | UNSE |  | 0 | 4752 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-07-23 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-23 17:00 |  | N/A | 2021-08-17 08:00 | [14 empty] | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | 8 | 35217269 | CWSP |  | 2021-03-05 11:49
35227165 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Scoped | UNSE |  | 5333 | 0 | 5333 | 1.01 | 0 | 0 | 0 | 0 | 5333 | 1.01 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227167 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Scoped | UNSE |  | 9504 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227168 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Scoped | UNSE |  | 8290 | 0 | 8290 | 1.5701 | 0 | 0 | 0 | 0 | 8290 | 1.5701 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220896 | CWSP |  | 2021-03-05 11:50
35227260 |  | 2021 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Scoped | ESTS |  | 0 | 12443 | 12443 | 2.3566 | 0 | 0 | 12443 | 2.3566 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-16 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3566 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-16 17:00 |  | INPR | 2021-07-13 08:00 |  | 275000 | 2050512.1 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35227261 |  | 2021 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Scoped | ESTS |  | 0 | 11421 | 11421 | 2.1631 | 0 | 0 | 11421 | 2.1631 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-06-18 17:00 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1631 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-18 17:00 |  | INPR | 2021-07-13 08:00 |  | 250000 | 2053204 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP |  | 2021-03-11 15:59
35227262 |  | 2021 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Scoped | ESTS |  | 0 | 6152 | 6152 | 1.1652 | 0 | 0 | 6152 | 1.1652 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | SH | 2021-07-02 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1652 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-02 17:00 |  | INPR | 2021-07-27 08:00 |  | 150000 | 1888154.3 | [11 empty] | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | 22 | 35219097 | CWSP |  | 2021-03-11 16:00
35227263 |  | 2021 | CWSP - MARIPOSA 2102CB PH 2 |  | Scoped | ESTS |  | 0 | 1315.42 | 1315.42 | 0.24913 | 0 | 0 | 1315 | 0.24905 | 0 | 0 | 0 | 0 | 7.9545e-05 |  |  | YO | 08W | SH | 2021-05-25 17:00 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24913 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-25 17:00 |  | N/A | 2021-06-22 08:00 | [14 empty] | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | 35 | 35219266 | CWSP |  | 2021-03-11 10:08
35227860 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Scoped | UNSE |  | 0 | 1056 | 1056 | 0.2 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:50
35227861 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Scoped | UNSE |  | 0 | 8026 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227862 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Scoped | UNSE |  | 0 | 5755 | 5755 | 1.09 | 0 | 0 | 5755 | 1.09 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227863 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Scoped | UNSE |  | 0 | 4171 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227864 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Scoped | UNSE |  | 3274 | 0 | 3274 | 0.62008 | 0 | 0 | 0 | 0 | 3274 | 0.62008 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227866 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Scoped | UNSE |  | 0 | 2746 | 2746 | 0.52008 | 0 | 0 | 2746 | 0.52008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:51
35227867 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Scoped | UNSE |  | 0 | 5174 | 5174 | 0.97992 | 0 | 0 | 5174 | 0.97992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:52
35227868 |  | 2021 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Scoped | UNSE |  | 0 | 2112 | 2112 | 0.4 | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35217271 | CWSP |  | 2021-03-05 11:52
35228186 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Scoped | UNSE |  | 7867 | 0 | 7867 | 1.49 | 0 | 0 | 0 | 0 | 7867 | 1.49 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-04-30 | N | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220895 | CWSP |  | 2021-03-05 11:52
35228187 |  | 2021 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Scoped | UNSE |  | 0 | 3326 | 3326 | 0.62992 | 0 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-06-14 17:00 | 2021-03-31 | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 | [14 empty] | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | 14 | 35220895 | CWSP |  | 2021-03-05 11:52
35229119 |  | 2021 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Scoped | UNSE |  | 3221 | 0 | 3221 | 0.61004 | 0 | 0 | 3221 | 0.61004 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | SH | 2021-10-12 17:00 | 2021-02-18 | Y | 2021-04-30 | [13 empty] | In Progress | 2021-03-12 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.61004 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-10-12 17:00 |  | N/A | 2021-10-15 08:00 |  | 475000 | [6 empty] | Prioritized | [5 empty] | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | 23 | 35219098 | CWSP |  | 2021-03-11 11:36
35231543 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Scoped | UNSE |  | 6864 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 6864 | 1.3 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | In Progress | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 350000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35231544 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Scoped | UNSE |  | 0 | 6336 | 6336 | 1.2 | 0 | 0 | 6336 | 1.2 | 0 | 0 | 0 | 0 | 0 |  |  | DI | 08W | SH |  | 2021-02-26 | Y | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A |  |  | 181000 | [12 empty] | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | 18 | 35219093 | CWSP |  | 2021-03-11 12:49
35231607 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Scoped | ESTS |  | 0 | 8691 | 8691 | 1.646 | 0 | 0 | 8691 | 1.646 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-22 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-02 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.646 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-22 17:00 |  | N/A | 2021-07-15 08:00 |  | 70000 | 2836423.6 | [8 empty] | No SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-11 10:06
35231608 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Scoped | UNSE |  | 1742.4 | 0 | 1742.4 | 0.33 | 0 | 0 | 0 | 0 | 1742 | 0.32992 | 0 | 0 | 7.5758e-05 |  |  | SI | 08W | SH | 2021-06-29 17:00 |  |  | 2021-04-30 | [13 empty] | In Progress | 2021-04-12 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-29 17:00 |  | N/A | 2021-07-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-04 09:43
35231609 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Scoped | ESTS |  | 0 | 7023 | 7023 | 1.3301 | 0 | 0 | 7023 | 1.3301 | 0 | 0 | 0 | 0 | 0 | 8783 | 1.6634 | SI | 08W | SH | 2021-07-22 17:00 | 2021-02-18 | Y | 2021-03-31 | 2021-04-02 | [12 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3301 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-07-22 17:00 |  | N/A | 2021-08-16 08:00 |  | 70000 | 2615040.7 |  |  |  | Site survey requested 3/9/2021 |  |  |  |  | SCADA |  |  | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062374 | PRE |  | 2021-03-11 10:02
35232280 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Scoped | ESTS |  | 0 | 3168 | 3168 | 0.6 | 0 | 0 | 3168 | 0.6 | 0 | 0 | 0 | 0 | 0 | 3235 | 0.61269 | SI | 08W | SH | 2021-05-24 17:00 | 2021-02-22 | Y | 2021-04-30 | 2021-04-09 | [10 empty] | 2021-04-13 | 2021-04-13 | N/A |  |  |  |  | 2021-04-13 | 2021-04-13 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.6 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-05-24 17:00 |  | INPR | 2021-06-22 08:00 | [14 empty] | Shingle Springs | El Dorado | 38.7138 | -120.9394 | [10 empty] | 227 | 35062375 | PRE |  | 2021-03-11 14:33
35232442 |  |  | CWSP - DESCHUTES 11049718 PH 2.2 |  | Scoped | UNSE |  | 0 | 16251 | 16251 | 3.0778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0778 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:23
35232443 |  |  | CWSP - DESCHUTES 11049718 PH 2.3 |  | Scoped | UNSE |  | 0 | 5468 | 5468 | 1.0356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0356 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35232444 |  |  | CWSP - DESCHUTES 11049718 PH 2.4 |  | Scoped | UNSE |  | 0 | 18648 | 18648 | 3.5318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5318 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:23
35232445 |  |  | CWSP - DESCHUTES 11049718 PH 2.5 |  | Scoped | UNSE |  | 0 | 13748 | 13748 | 2.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6038 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35225825 | CWSP |  | 2021-03-09 17:24
35232650 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 |  | Scoped | UNSE |  | 9028 | 0 | 9028 | 1.7098 | 0 | 0 | 0 | 0 | 9028 | 1.7098 | 0 | 0 | 0 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | In Progress | 2021-04-15 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7098 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316667 | [12 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP |  | 2021-03-11 10:30
35232651 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.3 |  | Scoped | UNSE |  | 0 | 9187.2 | 9187.2 | 1.74 | 0 | 0 | 9187 | 1.74 | 0 | 0 | 0 | 0 | 3.7879e-05 |  |  | SI | 08W | SH | 2021-06-14 17:00 | 2021-06-01 | N | [14 empty] | N/A | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.74 | 0 | 0 |  | 0 | 0 | 0 |  | Keep | 2021-06-14 17:00 |  | N/A | 2021-07-07 08:00 |  | 316667 | [12 empty] | Cool | El Dorado | 38.8983 | -120.9827 | [10 empty] | 45 | 35219281 | CWSP |  | 2021-03-11 10:01
35232960 |  |  | CWSP - DESCHUTES 11049718 PH1.2 |  | Scoped | UNSE |  | 0 | 16057 | 16057 | 3.0411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 |  |  | NV | 08W | SH | [39 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0411 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Palo Cedro | Shasta | 40.535 | -122.2392 | [10 empty] | 48 | 35219286 | CWSP |  | 2021-03-09 17:18
35234756 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.9 |  | Scoped | UNSE |  | 14689 | 0 | 14689 | 2.782 | 0 | 0 | 0 | 0 | 14689 | 2.782 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.782 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-11 14:00
35234758 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.10 |  | Scoped | UNSE |  | 3073 | 0 | 3073 | 0.58201 | 0 | 0 | 0 | 0 | 3073 | 0.58201 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.58201 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-05 11:41
35234862 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.11 |  | Scoped | UNSE |  | 422 | 0 | 422 | 0.079924 | 0 | 0 | 0 | 0 | 422 | 0.079924 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.079924 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-05 11:42
35234865 |  |  | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.12 |  | Scoped | UNSE |  | 3419 | 0 | 3419 | 0.64754 | 0 | 0 | 0 | 0 | 3419 | 0.64754 | 0 | 0 | 0 |  |  | HB | 08W | SH |  |  | N | [36 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64754 | 0 | 0 |  | 0 | 0 | 0 |  | Keep |  |  | N/A | [15 empty] | Middletown | Lake | 38.7576 | -122.6358 | [10 empty] | 474 | 35174501 | ECOP |  | 2021-03-05 11:42
Note on I2: [REDACTED]:This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on J2: [REDACTED]:This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.

## Move to 2022
Order | Job Owner Name | Project Reporting Year | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet
35062374 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Scoped | UNSE |  | 8106 | 0
35062376 |  | 2021 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Scoped | UNSE |  | 22892 | 0
35219281 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Scoped | UNSE |  | 13200 | 0
35223036 |  | 2021 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Scoped | UNSE |  | 264 | 0
35232650 |  | 2021 | CWSP - MOUNTAIN QUARRIES 21016953 PH 1.2 |  | Scoped | UNSE |  | 9028 | 0
35192280 |  | 2021 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Scoped | UNSE |  | 7075.2 | 0
35219093 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Scoped | ESTS |  | 6019 | 0
35219096 |  | 2021 | CWSP - KIRKER 2104442850 PH 1.1 |  | Scoped | UNSE |  | 8817.6 | 0
35231543 |  | 2021 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Scoped | ESTS |  | 6864 | 0
35192291 |  | 2021 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Scoped | UNSE |  | 2534.4 | 0
35219589 |  | 2021 | CWSP - WILDWOOD 11011454 |  | Scoped | UNSE |  | 0 | 13622.4
35224321 |  | 2021 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Scoped | UNSE |  | 0 | 12302.4
Total | [7 empty] | 84800.2 | 25924.8
Note on I1: [REDACTED]:This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on J1: [REDACTED]:This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.

## Sheet4
Change Request Type | Order | Notification | Order Description | Updated Sub-Category | Business Justification | Updated Work Plan Date | Updated New Construction Complete Year | Requested Budget for 2020 | Requested Budget for 2021 | Requested Budget for 2022 | Requested Budget for 2023
Defer project | 35062374 | 115323920 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 | N/A