## Summary
System Hardening 2021 Financial Review
amounts in 1,000s
| Mar |  |  |  | YTD |  |  |  | EOY
| Act | Forecast (PRJ) | Var | % of Var | Act | Budget | Var | % of Var | Run Rate | Forecast (Act+ PRJ) | Budget | Var | % of Var
System Hardening | 18491.1826 | 19983.4005 | 1492.2179 | 7.467% | 15450.5839 | 107826.0352 | 92375.4513 | 85.67% | 61802.3358 | 554043.2958 | 640246.4953 | 86203.1996 | 13.46%
update North Complex review as well. have ready for monthly meeting

## Forecast
System Hardening 2021
$ amount in thousands
|  | Actuals |  |  | Forecast
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 08W hardened miles | 3.6 | 6.1 | 14.3 | 15 | 20 | 25 | 25 | 30 | 30 | 17 | 12 | 6
2AF idle facilities |  | Actuals Jan: 1.5; Actuals Feb: 0; Actuals Mar: 0
| Total Miles | 5.1 | 6.1 | 14.3 | 15 | 20 | 25 | 25 | 30 | 30 | 17 | 12 | 6
Total Charges |  | -55177.2964 | 52136.6978 | 18491.1826 | 33309.5204 | 68372.0725 | 48288.7917 | 79784.6031 | 78975.855 | 77507.6145 | 58944.9378 | 49375.6234 | 37861.4416
Cumulative Miles |  | 5.1 | 11.2 | 25.5 | 40.5 | 60.5 | 85.5 | 110.5 | 140.5 | 170.5 | 187.5 | 199.5 | 205.5
Cumulative Costs |  | -55177.2964 | -3040.5987 | 15450.5839 | 48760.1044 | 117132.1769 | 165420.9686 | 245205.5718 | 324181.4268 | 401689.0413 | 460633.9792 | 510009.6025 | 547871.0441
Cumulative Unit Cost
data pulled on 4/05
Version | Overall Result | 001/2021 | 002/2021 | 003/2021 | 004/2021 | 005/2021 | 006/2021 | 007/2021 | 008/2021 | 009/2021 | 010/2021 | 011/2021 | 012/2021
Act | 15450.5839 | Actuals Jan: -55177.2964; Actuals Feb: 52136.6978; Actuals Mar: 18491.1826
DET | 640246.4953 | 38955.8793 | 32804.3138 | 36065.8422 | 33309.5204 | 68372.0725 | 48288.7917 | 79784.6031 | 78975.855 | 77507.6145 | 58944.9378 | 49375.6234 | 37861.4416
PRJ |  | 5865.2357 | 13501.8008 | 19983.4005 | 26095.4924 | 34460.4448 | 34502.317 | 85539.3035 | 89463.4532 | 83456.6229 | 77060.3795 | 58598.9477 | 49415.7509
PRM |  | 6512.8753 | 7525.0554 | 22594.6181 | 21745.0599 | 27403.7394 | 28657.3597 | 64225.1738 | 66781.6194 | 59564.7393 | 53022.5193 | 43543.6248 | 40454.8241
RET | 640246.5103 | -54924.5581 | 52216.5349 | 18391.4524 | 35000 | 105245.6349 | 79250.0753 | 92606.1512 | 88021.5687 | 82371.5502 | 59826.7931 | 48187.3008 | 34054.007
PRJ Act plus forecast | 554043.2958 | -55177.2964 | 52136.6978 | 18491.1826 | 26095.4924 | 34460.4448 | 34502.317 | 85539.3035 | 89463.4532 | 83456.6229 | 77060.3795 | 58598.9477 | 49415.7509
PRM Act plus forecast | 420849.2436 | -55177.2964 | 52136.6978 | 18491.1826 | 21745.0599 | 27403.7394 | 28657.3597 | 64225.1738 | 66781.6194 | 59564.7393 | 53022.5193 | 43543.6248 | 40454.8241
Jan Notes
January - reversal of accruals, additional costs have not been JEd over yet
should have re accrued in Jan
new accruals will need to be recalculated to account for any costs that have actually hit
at some point we have to assume all costs have hit and they may be different from the accrued amount
readiness may exceed execution
1100 miles to get ready for 2022 and 2023
PRJ will only include cost for current projects
Feb Notes
original DET based on 358 miles, 20 miles in Jan & Feb
Original DET forecasted $30M to hit in Jan and Feb, for 40 miles to be completed in March
delta of Contracts accrual credit, when actuals hit in 2020 |  | Forecast Jun: 10
delta of Material accrual credit, when actuals hit in 2020 |  | Forecast Jun: 2
$3.2M of Pure Hardening in CEMA should have been JE over, and was missed (Glass Fire) |  | Forecast Jun: 3.2
$200k of comingled costs still sitting in CEMA |  | Forecast Jun: 0.2
[6 empty] | total | 15.4
$1.8M of contract credits on other orders not associated with accrual |  | Forecast Jun: 1.8; Forecast Jul: leave out
$200k of material credits on other orders not associated with accrual |  | Forecast Jun: 0.2; Forecast Jul: leave out
March Notes

## Order Costs
| Fiscal year | Overall Result | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2021
| Period/Year |  | Result | 001/2019 | 002/2019 | 003/2019 | 004/2019 | 005/2019 | 006/2019 | 007/2019 | 008/2019 | 009/2019 | 010/2019 | 011/2019 | 012/2019 | Result | 001/2020 | 002/2020 | 003/2020 | 004/2020 | 005/2020 | 006/2020 | 007/2020 | 008/2020 | 009/2020 | 010/2020 | 011/2020 | 012/2020 | Result | 001/2021 | 002/2021 | 003/2021 | 004/2021
Program | CE Mjr Resource Grp | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $ | * 1,000 $
System Hardening | Result | 719978.1406 | 281059.7753 | 1582.4611 | 7313.7969 | -1140.3883 | 4255.5908 | 14398.5306 | 10930.3735 | 29523.3696 | 17803.1175 | 41111.531 | 20606.5898 | 25377.1694 | 109297.6334 | 460142.0956 | 20416.445 | 42332.8513 | 40351.3224 | 20294.4875 | 31684.484 | 20149.5278 | 20659.1091 | 25563.684 | 20012.027 | 10193.1686 | 37818.3138 | 170666.6751 | -21223.7303 | -55177.2964 | 52136.6978 | 18491.1826 | -36674.3142
System Hardening | Contract
System Hardening | Labor External
System Hardening | Labor Internal
System Hardening | Materials
System Hardening | Other
Order Costs

## data for pivot
Order | Order Desc | CE Mjr Resource Grp | Cost Element | Vendor | Fiscal year/period | $
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
1014895 | Contract Estimating 08W Planning |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
1014895 | Contract Estimating 08W Planning |  | Cash Discount earned |  | 002/2021
1014895 | Contract Estimating 08W Planning |  | Cash Discount earned |  | 001/2021
1014895 | Contract Estimating 08W Planning |  | Cash Discount earned |  | 002/2021
1014895 | Contract Estimating 08W Planning |  | Cash Discount earned |  | 003/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | Consulting Services - Other |  | 001/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | Consulting Services - Other |  | 002/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | Consulting Services - Other |  | 003/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Borrowed |  | 001/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Borrowed |  | 002/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Borrowed |  | 003/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Equity |  | 001/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Equity |  | 002/2021
7093505 | 08W - WILDFIRE RESILIENCY PMO |  | AFUDC-Equity |  | 003/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Borrowed |  | 001/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Borrowed |  | 002/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Borrowed |  | 003/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Equity |  | 001/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Equity |  | 002/2021
7094406 | 08W - CWSP Materials |  | AFUDC-Equity |  | 003/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Contracts |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Environmental Planning & Permitting-Misc |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Indirect Labor - Electric |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Indirect Labor - Environmental Land |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Mapping |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Paid Time Off |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Benefits OH |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Building Service Overhead |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Capitalized A&G |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Fleet OH - Elec |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | IT Device OH |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Operation Mgmt & Support - Electric |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
30977613 | WDDB OTTER 1102 PHASE 3 |  | Payroll Taxes OH |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Engineering/Mapping |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Environmental Planning & Permitting-Misc |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Indirect Labor - Electric |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Indirect Labor - Environmental Land |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Paid Time Off |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Benefits OH |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Building Service Overhead |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Capitalized A&G |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Fleet OH - Elec |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | IT Device OH |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Operation Mgmt & Support - Electric |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
30977614 | WDDB OTTER 1102 PHASE 4 |  | Payroll Taxes OH |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Engineering/Mapping |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Indirect Labor - Electric |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Paid Time Off |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Benefits OH |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Building Service Overhead |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Capitalized A&G |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Fleet OH - Elec |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | IT Device OH |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Operation Mgmt & Support - Electric |  | 001/2021
30977615 | WDDB OTTER 1102 PHASE 5 |  | Payroll Taxes OH |  | 001/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Construction Overtime Services |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Indirect Labor - Electric |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Indirect Labor - Gas |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Mapping |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Paid Time Off |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Benefits OH |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Building Service Overhead |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Capitalized A&G |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Fleet OH - Elec |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Fleet OH - Gas |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | IT Device OH |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Operation Mgmt & Support - Electric |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Operation Mgmt & Support - Gas |  | 003/2021
31082393 | RECON THREE SPANS CHERRY RIDGE RD |  | Payroll Taxes OH |  | 003/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Contracts |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Indirect Labor - Electric |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Mapping |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Paid Time Off |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Benefits OH |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Building Service Overhead |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Capitalized A&G |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Fleet OH - Elec |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | IT Device OH |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Operation Mgmt & Support - Electric |  | 001/2021
31207090 | MVWF VIEWPOINT RD TENNVLY CNTY ALTO 1125 |  | Payroll Taxes OH |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Environmental Contract |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Environmental Contract |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Construction |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Construction |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Engineering/Mapping |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Environmental Planning & Permitting-Misc |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Indirect Labor - Electric |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Indirect Labor - Electric |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Indirect Labor - Electric |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Indirect Labor - Environmental Land |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Mapping |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Mapping |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Paid Time Off |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Paid Time Off |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Paid Time Off |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Benefits OH |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Benefits OH |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Benefits OH |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Building Service Overhead |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Building Service Overhead |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Building Service Overhead |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Capitalized A&G |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Capitalized A&G |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Capitalized A&G |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Fleet OH - Elec |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Fleet OH - Elec |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Fleet OH - Elec |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | IT Device OH |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | IT Device OH |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | IT Device OH |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Operation Mgmt & Support - Electric |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Operation Mgmt & Support - Electric |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Operation Mgmt & Support - Electric |  | 003/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Payroll Taxes OH |  | 001/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Payroll Taxes OH |  | 002/2021
31272374 | CWSP PT. MORETTI FROM 5043 TO 5955 |  | Payroll Taxes OH |  | 003/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Environmental Contract |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Construction |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Construction Overtime Services |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Indirect Labor - Electric |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Mapping |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Paid Time Off |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Benefits OH |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Building Service Overhead |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Capitalized A&G |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Fleet OH - Elec |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | IT Device OH |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Operation Mgmt & Support - Electric |  | 001/2021
31272375 | CWSP PT. MORETTI BEYOND 5995 |  | Payroll Taxes OH |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Construction |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Indirect Labor - Electric |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Mapping |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Paid Time Off |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Benefits OH |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Building Service Overhead |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Capitalized A&G |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Fleet OH - Elec |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | IT Device OH |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Operation Mgmt & Support - Electric |  | 001/2021
31275658 | R7 DUNBAR 1102 RECOND OH BEYOND CO 1285 |  | Payroll Taxes OH |  | 001/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Engineering/Mapping |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Indirect Labor - Electric |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Paid Time Off |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Benefits OH |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Building Service Overhead |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Capitalized A&G |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Fleet OH - Elec |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | IT Device OH |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Operation Mgmt & Support - Electric |  | 003/2021
31280506 | R2 RECONDUCT PT. MORETTI BEYOND 8981 |  | Payroll Taxes OH |  | 003/2021
31286361 | *CANC* FRUITLAND 42 C/O 7449 *CANC |  | Canceled Capital Order |  | 003/2021
31289354 | *CANC* BIG RIVER 1101 FUSE 5187 REC*CANC |  | Canceled Capital Order |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Construction |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Engineering/Mapping |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Engineering/Mapping |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Engineering/Mapping |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Indirect Labor - Electric |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Indirect Labor - Electric |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Indirect Labor - Electric |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Mapping |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Paid Time Off |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Paid Time Off |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Paid Time Off |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Benefits OH |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Benefits OH |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Benefits OH |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Building Service Overhead |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Building Service Overhead |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Building Service Overhead |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Capitalized A&G |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Capitalized A&G |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Capitalized A&G |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Fleet OH - Elec |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Fleet OH - Elec |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Fleet OH - Elec |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | IT Device OH |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | IT Device OH |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | IT Device OH |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Operation Mgmt & Support - Electric |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Operation Mgmt & Support - Electric |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Operation Mgmt & Support - Electric |  | 003/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Payroll Taxes OH |  | 001/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Payroll Taxes OH |  | 002/2021
31291639 | CWSP FH 1101 O'CONNOR WY RECOND 12 SPANS |  | Payroll Taxes OH |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Environmental Contract |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Account Services |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Account Services |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Administration |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Engineering/Mapping |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Environmental Services |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Environmental Services |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Environmental Services |  | 004/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Cust Care |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Cust Care |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Electric |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Electric |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Electric |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Environmental Land |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Indirect Labor - Environmental Land |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Mapping |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Paid Time Off |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Paid Time Off |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Paid Time Off |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Project Management Services |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Benefits OH |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Benefits OH |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Benefits OH |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Building Service Overhead |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Building Service Overhead |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Building Service Overhead |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Capitalized A&G |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Capitalized A&G |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Capitalized A&G |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Fleet OH - Elec |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Fleet OH - Elec |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Fleet OH - Elec |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | IT Device OH |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | IT Device OH |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | IT Device OH |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Operation Mgmt & Support - Electric |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Operation Mgmt & Support - Electric |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Operation Mgmt & Support - Electric |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Operation Mgmt & Support - Environ Land |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Operation Mgmt & Support - Environ Land |  | 003/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Payroll Taxes OH |  | 001/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Payroll Taxes OH |  | 002/2021
31334291 | RECON-6 SPANS CAMP ONE TEN MILE FT BRAGG |  | Payroll Taxes OH |  | 003/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Material Burden |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Benefits OH |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Building Service Overhead |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | IT Device OH |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Minor Material OH |  | 002/2021
31343500 | CWSP ORINDA 401 HIGH SPLICE COUNT |  | Payroll Taxes OH |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Environmental Contract |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Administration |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Engineering/Mapping |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Environmental Planning & Permitting-Misc |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Indirect Labor - Electric |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Indirect Labor - Electric |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Indirect Labor - Environmental Land |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Mapping |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Paid Time Off |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Paid Time Off |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Benefits OH |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Benefits OH |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Building Service Overhead |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Building Service Overhead |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Capitalized A&G |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Capitalized A&G |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Fleet OH - Elec |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Fleet OH - Elec |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | IT Device OH |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | IT Device OH |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Operation Mgmt & Support - Electric |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Operation Mgmt & Support - Electric |  | 002/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Operation Mgmt & Support - Environ Land |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Payroll Taxes OH |  | 001/2021
31354988 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Payroll Taxes OH |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Contracts |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Account Services |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Account Services |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Account Services |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Acquisition - Misc |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Acquisition - Misc |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Acquisition - Misc |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Administration |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Construction |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Construction Doubletime Services |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Construction Overtime Services |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Engineering/Mapping |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Environmental Planning & Permitting-Misc |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Cust Care |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Cust Care |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Cust Care |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Electric |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Electric |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Electric |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Environmental Land |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Environmental Land |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Environmental Land |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Indirect Labor - Gas |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Land Rights - Misc |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Management Services |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Management Services |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Management Services |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Mapping |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Paid Time Off |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Paid Time Off |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Paid Time Off |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Project Management Services |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Project Management Services |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Project Management Services |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Material Burden |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Benefits OH |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Benefits OH |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Benefits OH |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Building Service Overhead |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Building Service Overhead |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Building Service Overhead |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Capitalized A&G |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Capitalized A&G |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Capitalized A&G |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Cash Discount earned |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Fleet OH - Elec |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Fleet OH - Elec |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Fleet OH - Elec |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Fleet OH - Gas |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | IT Device OH |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | IT Device OH |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | IT Device OH |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Minor Material OH |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Electric |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Electric |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Electric |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Operation Mgmt & Support - Gas |  | 003/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Other Land Fees |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Payroll Taxes OH |  | 001/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Payroll Taxes OH |  | 002/2021
31361965 | RECON 2300 FT - NUNS CANYON -DUNBAR 1101 |  | Payroll Taxes OH |  | 003/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Electric Construction Contract |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Indirect Labor - Electric |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Mapping |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Paid Time Off |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Benefits OH |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Building Service Overhead |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Capitalized A&G |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Fleet OH - Elec |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | IT Device OH |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Operation Mgmt & Support - Electric |  | 002/2021
31389447 | PUEBLO 1105 RECONDUCTOR W TREE WIRE |  | Payroll Taxes OH |  | 002/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Environmental Planning & Permitting-Misc |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Indirect Labor - Environmental Land |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Paid Time Off |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Borrowed |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Borrowed |  | 002/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Borrowed |  | 003/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Equity |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Equity |  | 002/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | AFUDC-Equity |  | 003/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Benefits OH |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Building Service Overhead |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Capitalized A&G |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | IT Device OH |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Operation Mgmt & Support - Environ Land |  | 001/2021
31429487 | OTTER-1101 S030CC121 – TRANS POLES |  | Payroll Taxes OH |  | 001/2021
31478906 | RAISE T-LINE H-FRAME DONNELS-MI WUK 18/2 |  | Fabricated Structures |  | 004/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Environmental Contract |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Consulting Services - Engineering |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Consulting Services - Environmental Perm |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Consulting Services - Environmental Perm |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Analyst Services |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Indirect Labor - Electric |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Indirect Labor - Electric |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Indirect Labor - Electric |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Indirect Labor - Environmental Land |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Mapping |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Mapping |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Mapping |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Paid Time Off |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Paid Time Off |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Paid Time Off |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Benefits OH |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Benefits OH |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Benefits OH |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Building Service Overhead |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Building Service Overhead |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Building Service Overhead |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Capitalized A&G |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Capitalized A&G |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Capitalized A&G |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Fleet OH - Elec |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Fleet OH - Elec |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Fleet OH - Elec |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | IT Device OH |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | IT Device OH |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | IT Device OH |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Operation Mgmt & Support - Electric |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Operation Mgmt & Support - Electric |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Operation Mgmt & Support - Electric |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Payroll Taxes OH |  | 001/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Payroll Taxes OH |  | 002/2021
35015704 | OH RECONDUCTR ROB ROY 2105 -S026CC117 |  | Payroll Taxes OH |  | 003/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Environmental Contract |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Administrative Services - OT |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Design Overtime Services |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Design Services |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Design Services Double Time |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Electric Estimating |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Engineering/Mapping |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Indirect Labor - Electric |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Indirect Labor - Electric |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Indirect Labor - Environmental Land |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Land Rights - Misc |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Mapping |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Paid Time Off |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Paid Time Off |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Benefits OH |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Benefits OH |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Building Service Overhead |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Building Service Overhead |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Capitalized A&G |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Capitalized A&G |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Fleet OH - Elec |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Fleet OH - Elec |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | IT Device OH |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | IT Device OH |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Operation Mgmt & Support - Electric |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Operation Mgmt & Support - Electric |  | 002/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Payroll Taxes OH |  | 001/2021
35026643 | DIAMOND SPRINGS 1105 - LR 2102 |  | Payroll Taxes OH |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Construction Inspection |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Consulting Services - Environmental Perm |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Account Services |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Account Services |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Account Services |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Acquisition - Misc |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Construction |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Construction |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Engineering/Mapping |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Engineering/Mapping |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Engineering/Mapping |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Cust Care |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Cust Care |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Cust Care |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Electric |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Electric |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Electric |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Environmental Land |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Indirect Labor - Environmental Land |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Mapping |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Mapping |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Paid Time Off |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Paid Time Off |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Paid Time Off |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Benefits OH |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Benefits OH |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Benefits OH |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Building Service Overhead |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Building Service Overhead |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Building Service Overhead |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Capitalized A&G |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Capitalized A&G |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Capitalized A&G |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Fleet OH - Elec |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Fleet OH - Elec |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Fleet OH - Elec |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | IT Device OH |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | IT Device OH |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | IT Device OH |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Operation Mgmt & Support - Electric |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Operation Mgmt & Support - Electric |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Operation Mgmt & Support - Electric |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Payroll Taxes OH |  | 001/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Payroll Taxes OH |  | 002/2021
35030568 | CWSP HALF MOON BAY 1101 FUCO 4141 |  | Payroll Taxes OH |  | 003/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Account Services |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Indirect Labor - Cust Care |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Paid Time Off |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Borrowed |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Borrowed |  | 002/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Borrowed |  | 003/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Equity |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Equity |  | 002/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | AFUDC-Equity |  | 003/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Benefits OH |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Building Service Overhead |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Capitalized A&G |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | IT Device OH |  | 001/2021
35031663 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.1 |  | Payroll Taxes OH |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Contracts |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Contracts |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Mapping |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Paid Time Off |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Benefits OH |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Building Service Overhead |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Capitalized A&G |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | IT Device OH |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35043291 | OCGC CWSP- PINE GROVE 1102 LR9145 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Consulting Services - Environmental Perm |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Consulting Services - Environmental Perm |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Engineering/Mapping |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Engineering/Mapping |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Indirect Labor - Electric |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Indirect Labor - Electric |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Indirect Labor - Environmental Land |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Mapping |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Mapping |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Paid Time Off |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Paid Time Off |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Benefits OH |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Benefits OH |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Building Service Overhead |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Building Service Overhead |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Capitalized A&G |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Capitalized A&G |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Fleet OH - Elec |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Fleet OH - Elec |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | IT Device OH |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | IT Device OH |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Operation Mgmt & Support - Electric |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Operation Mgmt & Support - Electric |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Payroll Taxes OH |  | 001/2021
35043296 | WDDB - WILLOW CRK 1103 LR 3090 |  | Payroll Taxes OH |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Engineering/Mapping |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Engineering/Mapping |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Paid Time Off |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Paid Time Off |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Equity |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Equity |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | AFUDC-Equity |  | 003/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Benefits OH |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Benefits OH |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Building Service Overhead |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Building Service Overhead |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Capitalized A&G |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Capitalized A&G |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Fleet OH - Elec |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | IT Device OH |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | IT Device OH |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Payroll Taxes OH |  | 001/2021
35043421 | CWSP-WEST POINT 1101-OCB&LR12256 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engineering/Mapping |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Engineering/Mapping |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Paid Time Off |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Paid Time Off |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Equity |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Equity |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | AFUDC-Equity |  | 003/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Benefits OH |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Benefits OH |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Building Service Overhead |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Building Service Overhead |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Capitalized A&G |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Capitalized A&G |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | IT Device OH |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | IT Device OH |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35043422 | CWSP - WEST POINT 1101 -LR 13444- PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Traffic Control Contracts |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Construction |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Engineering/Mapping |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Engineering/Mapping |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Indirect Labor - Electric |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Mapping |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Paid Time Off |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Paid Time Off |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Material Burden |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Equity |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Equity |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | AFUDC-Equity |  | 003/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Benefits OH |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Benefits OH |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Building Service Overhead |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Building Service Overhead |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Capitalized A&G |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Capitalized A&G |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Cash Discount earned |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Fleet OH - Elec |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | IT Device OH |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | IT Device OH |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Minor Material OH |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35043423 | CWSP - WEST POINT 1101 -LR 13444- PH 2.1 |  | Payroll Taxes OH |  | 002/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Borrowed |  | 001/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Borrowed |  | 002/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Borrowed |  | 003/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Equity |  | 001/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Equity |  | 002/2021
35043993 | CWSP - CAMPEVERS2105 - LR 74170 - 4KVPH4 |  | AFUDC-Equity |  | 003/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Borrowed |  | 001/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Borrowed |  | 002/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Borrowed |  | 003/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Equity |  | 001/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Equity |  | 002/2021
35043994 | CWSP - CAMP EVERS 2105 - LR 11384 ZONE |  | AFUDC-Equity |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Contracts |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Environmental Contract |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Electric Activity Charge - Type A |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Env & Land Activity Charge - Type A |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Indirect Labor - Electric |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Indirect Labor - Electric |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Indirect Labor - Environmental Land |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Mapping |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Mapping |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Paid Time Off |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Paid Time Off |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Benefits OH |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Benefits OH |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Building Service Overhead |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Building Service Overhead |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Capitalized A&G |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Capitalized A&G |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Cost Adjustments |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Fleet OH - Elec |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Fleet OH - Elec |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | IT Device OH |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | IT Device OH |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Operation Mgmt & Support - Electric |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Operation Mgmt & Support - Electric |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Payroll Taxes OH |  | 001/2021
35046371 | *CANC* ECOP - STANISLAUS 1702 LR 37276 |  | Payroll Taxes OH |  | 003/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Borrowed |  | 001/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Borrowed |  | 002/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Borrowed |  | 003/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Equity |  | 001/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Equity |  | 002/2021
35047429 | CWSP - WILLITS 1104 - LR 34008 PH 1 |  | AFUDC-Equity |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Account Services |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Engineering/Mapping |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Indirect Labor - Cust Care |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Indirect Labor - Electric |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Paid Time Off |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Paid Time Off |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Benefits OH |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Benefits OH |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Building Service Overhead |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Building Service Overhead |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Capitalized A&G |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Capitalized A&G |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Fleet OH - Elec |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | IT Device OH |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | IT Device OH |  | 003/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Operation Mgmt & Support - Electric |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Payroll Taxes OH |  | 001/2021
35050951 | CWSP: MONTE RIO 1113 HENDRIX CABLE |  | Payroll Taxes OH |  | 003/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Borrowed |  | 001/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Borrowed |  | 002/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Borrowed |  | 003/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Equity |  | 001/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Equity |  | 002/2021
35051268 | CWSP - WILLITS 1104 - LR 34008 - PH 2 |  | AFUDC-Equity |  | 003/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Borrowed |  | 001/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Borrowed |  | 002/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Borrowed |  | 003/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Equity |  | 001/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Equity |  | 002/2021
35051356 | CWSP - EL DORADO PH 2101 LR 26000 PH 2 |  | AFUDC-Equity |  | 003/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Borrowed |  | 001/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Borrowed |  | 002/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Borrowed |  | 003/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Equity |  | 001/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Equity |  | 002/2021
35051484 | CWSP - MONTE RIO 1113 - 8299 |  | AFUDC-Equity |  | 003/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Borrowed |  | 001/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Borrowed |  | 002/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Borrowed |  | 003/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Equity |  | 001/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Equity |  | 002/2021
35051485 | CWSP - MONTE RIO 1111 - 1701 |  | AFUDC-Equity |  | 003/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Borrowed |  | 001/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Borrowed |  | 002/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Borrowed |  | 003/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Equity |  | 001/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Equity |  | 002/2021
35052726 | CWSP - LOS GATOS 1106 LR 60116 PH1 |  | AFUDC-Equity |  | 003/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Borrowed |  | 001/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Borrowed |  | 002/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Borrowed |  | 003/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Equity |  | 001/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Equity |  | 002/2021
35052727 | CWSP LOS GATOS 1106 LR 1106 PHASE 2 |  | AFUDC-Equity |  | 003/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Borrowed |  | 001/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Borrowed |  | 002/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Borrowed |  | 003/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Equity |  | 001/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Equity |  | 002/2021
35052728 | CWSP - LOS GATOS 1107 LR 60092 PH1 |  | AFUDC-Equity |  | 003/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Borrowed |  | 001/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Borrowed |  | 002/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Borrowed |  | 003/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Equity |  | 001/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Equity |  | 002/2021
35052729 | CWSP - BURNS 2101 - PH 1 |  | AFUDC-Equity |  | 003/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Borrowed |  | 001/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Borrowed |  | 002/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Borrowed |  | 003/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Equity |  | 001/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Equity |  | 002/2021
35052730 | CWSP - BURNS 2101- PH 2 |  | AFUDC-Equity |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Contracts |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Environmental Contract |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Environmental Contract |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Consulting Services - Environmental Perm |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Consulting Services - Environmental Perm |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Account Services |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Analyst Services |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Electric Estimating |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Engineering/Mapping |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Engineering/Mapping |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Cust Care |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Mapping |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Mapping |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Mapping |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Paid Time Off |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Paid Time Off |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Paid Time Off |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Benefits OH |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Benefits OH |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Benefits OH |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | IT Device OH |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | IT Device OH |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | IT Device OH |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35052731 | CWSP - BIG BASIN 1101 - 10296 - PH 1.1 |  | Permits/FeesLand Surveying Services |  | 003/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Borrowed |  | 001/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Borrowed |  | 002/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Borrowed |  | 003/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Equity |  | 001/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Equity |  | 002/2021
35052732 | CWSP - BIG BASIN 1101 5028 ZONE |  | AFUDC-Equity |  | 003/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Borrowed |  | 001/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Borrowed |  | 002/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Borrowed |  | 003/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Equity |  | 001/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Equity |  | 002/2021
35052733 | CWSP - BIG BASIN 1101 - 10296 ZONE PH2 |  | AFUDC-Equity |  | 003/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Borrowed |  | 001/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Borrowed |  | 002/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Borrowed |  | 003/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Equity |  | 001/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Equity |  | 002/2021
35052734 | CWSP - CAMP EVERS 2105 - LR 5232-33542 |  | AFUDC-Equity |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Environmental Contract |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Environmental Contract |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Environmental Contract |  | 004/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Mapping |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Mapping |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Paid Time Off |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Paid Time Off |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Benefits OH |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Benefits OH |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Building Service Overhead |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Building Service Overhead |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Capitalized A&G |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Capitalized A&G |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | IT Device OH |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | IT Device OH |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052735 | CWSP - MIWUK 1701 - LR 10600 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Borrowed |  | 001/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Borrowed |  | 002/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Borrowed |  | 003/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Equity |  | 001/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Equity |  | 002/2021
35052736 | CWSP - MIWUK 1701 LR11800 |  | AFUDC-Equity |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Environmental Contract |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Environmental Contract |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Environmental Contract |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Consulting Services - Environmental Perm |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Account Services |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Account Services |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Acquisition - Misc |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Acquisition - Misc |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Acquisition - Misc |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Analyst Services |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Electric Estimating |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Electric Estimating |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Electric Estimating Overtime |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Cust Care |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Land Rights - Misc |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Mapping |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Mapping |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Mapping |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Paid Time Off |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Paid Time Off |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Paid Time Off |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Benefits OH |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Benefits OH |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Benefits OH |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | IT Device OH |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | IT Device OH |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | IT Device OH |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Permits/FeesLand Surveying Services |  | 002/2021
35052737 | CWSP - MIWUK 1701 - LR 8060 - PH 1.1 |  | Permits/FeesLand Surveying Services |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Environmental Contract |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Environmental Contract |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Environmental Contract |  | 004/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Engineering/Mapping |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Mapping |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Mapping |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Paid Time Off |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Paid Time Off |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Material Burden |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Benefits OH |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Benefits OH |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | IT Device OH |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | IT Device OH |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Minor Material OH |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052739 | CWSP - MIWUK 1702 - LR 38218 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Apprentice OT |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Construction |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Construction Doubletime Services |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Construction Overtime Services |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Mapping |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Paid Time Off |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Benefits OH |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | IT Device OH |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052820 | CWSP - MIWUK 1702 - OCB - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction Inspection |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction Inspection |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction Inspection |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction Inspection |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Contracts |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Contracts |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Construction Contract |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Construction Contract |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Construction Contract |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Construction Contract |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Construction Contract |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Contract |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Helicopter Contract |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Consulting Services - Engineering |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Account Services |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Analyst Services |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Construction Overtime Services |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Design Overtime Services |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Design Services Double Time |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Estimating |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Electric Estimating Overtime |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Engineering/Mapping |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Engineering/Mapping |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Indirect Labor - Gas |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Maint & Operate Doubletime Services |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Maintain & Operate Overtime Services |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Maintain & Operate Overtime Services |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Maintain & Operate Services |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Maintain & Operate Services |  | 004/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Mapping |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Mapping |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Mapping |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Paid Time Off |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Paid Time Off |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Paid Time Off |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Material Burden |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Material Burden |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Benefits OH |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Benefits OH |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Benefits OH |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Building Service Overhead |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Building Service Overhead |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Capitalized A&G |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Capitalized A&G |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Cash Discount earned |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Cash Discount earned |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Fleet OH - Gas |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | IT Device OH |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | IT Device OH |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | IT Device OH |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Minor Material OH |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Minor Material OH |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Operation Mgmt & Support - Gas |  | 003/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052821 | CWSP - MIWUK 1701 – OCB - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Borrowed |  | 001/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Borrowed |  | 002/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Borrowed |  | 003/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Equity |  | 001/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Equity |  | 002/2021
35052822 | CWSP - MIWUK 1701 - LR 8050 |  | AFUDC-Equity |  | 003/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Contracts |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Contracts |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Mapping |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Mapping |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Paid Time Off |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Paid Time Off |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Benefits OH |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Benefits OH |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | IT Device OH |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | IT Device OH |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35052823 | CWSP - MIWUK 1702 - LR 6018 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Borrowed |  | 001/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Borrowed |  | 002/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Borrowed |  | 003/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Equity |  | 001/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Equity |  | 002/2021
35052824 | CWSP - MIWUK 1702 - LR6018 - PH 2 |  | AFUDC-Equity |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Construction Inspection |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Contracts |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Electric Construction Contract |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Electric Construction Contract |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Electric Construction Contract |  | 004/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 004/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Contract |  | 004/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Consulting Services - Engineering |  | 004/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Account Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Administration |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Analyst Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Construction |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Construction Overtime Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Engineering/Mapping |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Engineering/Mapping |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Engineering/Mapping |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Indirect Labor - Gas |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Maint & Operate Doubletime Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Maintain & Operate Overtime Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Maintain & Operate Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Management Services |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Mapping |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Mapping |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Mapping |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Paid Time Off |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Paid Time Off |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Paid Time Off |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Benefits OH |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Benefits OH |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Benefits OH |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Fleet OH - Gas |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | IT Device OH |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | IT Device OH |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | IT Device OH |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Operation Mgmt & Support - Gas |  | 003/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35052825 | CWSP - MIWUK 1702 - LR 8090 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 004/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Environmental Contract |  | 004/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Traffic Control Contracts |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Consulting Services - Engineering |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Consulting Services - Engineering |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Consulting Services - Engineering |  | 004/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Construction |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Construction Overtime Services |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Engineering/Mapping |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Engineering/Mapping |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Engineering/Mapping |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Indirect Labor - Electric |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Indirect Labor - Electric |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Indirect Labor - Electric |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Maint & Operate Doubletime Services |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Maintain & Operate Overtime Services |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Mapping |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Mapping |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Mapping |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Paid Time Off |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Paid Time Off |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Paid Time Off |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Material Burden |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Transformers, Regulators & Capacitors |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Benefits OH |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Benefits OH |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Benefits OH |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Building Service Overhead |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Building Service Overhead |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Building Service Overhead |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Capitalized A&G |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Capitalized A&G |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Capitalized A&G |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Cash Discount earned |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Fleet OH - Elec |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Fleet OH - Elec |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Fleet OH - Elec |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | IT Device OH |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | IT Device OH |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | IT Device OH |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Minor Material OH |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Operation Mgmt & Support - Electric |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Operation Mgmt & Support - Electric |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Operation Mgmt & Support - Electric |  | 003/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Payroll Taxes OH |  | 001/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Payroll Taxes OH |  | 002/2021
35053033 | CWSP - TASSAJARA 2112 - FUSE 18053 |  | Payroll Taxes OH |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Environmental Contract |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Account Services |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Account Services |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Account Services |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Construction |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Construction |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Construction Overtime Services |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Engineering/Mapping |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Engineering/Mapping |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Engineering/Mapping |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Cust Care |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Cust Care |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Cust Care |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Electric |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Electric |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Electric |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Indirect Labor - Environmental Land |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Mapping |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Mapping |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Paid Time Off |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Paid Time Off |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Paid Time Off |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Benefits OH |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Benefits OH |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Benefits OH |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Building Service Overhead |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Building Service Overhead |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Building Service Overhead |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Capitalized A&G |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Capitalized A&G |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Capitalized A&G |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Fleet OH - Elec |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Fleet OH - Elec |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Fleet OH - Elec |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | IT Device OH |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | IT Device OH |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | IT Device OH |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Operation Mgmt & Support - Electric |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Operation Mgmt & Support - Electric |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Operation Mgmt & Support - Electric |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Payroll Taxes OH |  | 001/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Payroll Taxes OH |  | 002/2021
35053429 | CWSP HALF MOON BAY 1102 FUCO 12457 |  | Payroll Taxes OH |  | 003/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Environmental Contract |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Administrative Services - OT |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Design Overtime Services |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Design Services |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Design Services Double Time |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Electric Estimating |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Engineering/Mapping Services Overtime |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Mapping |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Mapping |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Paid Time Off |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Paid Time Off |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Benefits OH |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Benefits OH |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Building Service Overhead |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Building Service Overhead |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Capitalized A&G |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Capitalized A&G |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | IT Device OH |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | IT Device OH |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35054184 | CWSP-COLUMBIA HILL 1101-TS 8233 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Construction Overtime Services |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Mapping |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Paid Time Off |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Equity |  | 001/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Equity |  | 002/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | AFUDC-Equity |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Benefits OH |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Building Service Overhead |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Capitalized A&G |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Fleet OH - Elec |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | IT Device OH |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35056387 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.1 |  | Payroll Taxes OH |  | 003/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Borrowed |  | 001/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Borrowed |  | 002/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Borrowed |  | 003/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Equity |  | 001/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Equity |  | 002/2021
35056433 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 2 |  | AFUDC-Equity |  | 003/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Borrowed |  | 001/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Borrowed |  | 002/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Borrowed |  | 003/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Equity |  | 001/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Equity |  | 002/2021
35056434 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 3 |  | AFUDC-Equity |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Management Services |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Management Services |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Management Services |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Borrowed |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Borrowed |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Borrowed |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Equity |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Equity |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | AFUDC-Equity |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Benefits OH |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Benefits OH |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Benefits OH |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Building Service Overhead |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Building Service Overhead |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Building Service Overhead |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Capitalized A&G |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Capitalized A&G |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Capitalized A&G |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | IT Device OH |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | IT Device OH |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | IT Device OH |  | 003/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Payroll Taxes OH |  | 001/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Payroll Taxes OH |  | 002/2021
35056435 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 4 |  | Payroll Taxes OH |  | 003/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Borrowed |  | 001/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Borrowed |  | 002/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Borrowed |  | 003/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Equity |  | 001/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Equity |  | 002/2021
35056438 | REMG 650 - PLACERVILLE 2106, RINGTAIL |  | AFUDC-Equity |  | 003/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Borrowed |  | 001/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Borrowed |  | 002/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Borrowed |  | 003/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Equity |  | 001/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Equity |  | 002/2021
35056439 | CWSP - PLACERVILLE 2106 - LR 1104 - PH 6 |  | AFUDC-Equity |  | 003/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Borrowed |  | 001/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Borrowed |  | 002/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Borrowed |  | 003/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Equity |  | 001/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Equity |  | 002/2021
35056732 | CWSP FOREST HILL 1101 LR 50486 HARDENING |  | AFUDC-Equity |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Traffic Control Contracts |  | 002/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Construction |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Environmental Services |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Mapping |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Paid Time Off |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Paid Time Off |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Benefits OH |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Benefits OH |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | IT Device OH |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | IT Device OH |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35056733 | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Construction Inspection |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Construction Inspection |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Contracts |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Construction Contract |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Construction Contract |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Environmental Contract |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Consulting Services - Engineering |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Consulting Services - Engineering |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Consulting Services - Engineering |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Account Services |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Analyst Services |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Construction Overtime Services |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Estimating |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Estimating |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Estimating Overtime |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Electric Estimating Overtime |  | 004/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Engineering/Mapping |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Engineering/Mapping |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Engineering/Mapping |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Indirect Labor - Cust Care |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Indirect Labor - Electric |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Indirect Labor - Electric |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Indirect Labor - Electric |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Mapping |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Mapping |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Mapping |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Paid Time Off |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Paid Time Off |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Paid Time Off |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Borrowed |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Borrowed |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Borrowed |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Equity |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Equity |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | AFUDC-Equity |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Benefits OH |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Benefits OH |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Benefits OH |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Building Service Overhead |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Building Service Overhead |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Building Service Overhead |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Capitalized A&G |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Capitalized A&G |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Capitalized A&G |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Fleet OH - Elec |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Fleet OH - Elec |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Fleet OH - Elec |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | IT Device OH |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | IT Device OH |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | IT Device OH |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Payroll Taxes OH |  | 001/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Payroll Taxes OH |  | 002/2021
35056746 | CWSP - MIWUK 1701 OCB PHASE 2.1 |  | Payroll Taxes OH |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Environmental Contract |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Construction |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Indirect Labor - Electric |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Mapping |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Mapping |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Paid Time Off |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Paid Time Off |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Equity |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Equity |  | 002/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | AFUDC-Equity |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Benefits OH |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Benefits OH |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Building Service Overhead |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Building Service Overhead |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Capitalized A&G |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Capitalized A&G |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Fleet OH - Elec |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | IT Device OH |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | IT Device OH |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Payroll Taxes OH |  | 003/2021
35057010 | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Permits/Fees |  | 002/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Traffic Control Contracts |  | 002/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Analyst Services |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Construction |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Indirect Labor - Electric |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Mapping |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Paid Time Off |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Paid Time Off |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Borrowed |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Borrowed |  | 002/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Borrowed |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Equity |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Equity |  | 002/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | AFUDC-Equity |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Benefits OH |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Benefits OH |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Building Service Overhead |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Building Service Overhead |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Capitalized A&G |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Capitalized A&G |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Fleet OH - Elec |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | IT Device OH |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | IT Device OH |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Payroll Taxes OH |  | 001/2021
35057018 | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Payroll Taxes OH |  | 003/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Borrowed |  | 001/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Borrowed |  | 002/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Borrowed |  | 003/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Equity |  | 001/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Equity |  | 002/2021
35057802 | CWSP-CAMPEVERS2105 - LR 12590 - 4KV PH5 |  | AFUDC-Equity |  | 003/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Borrowed |  | 001/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Borrowed |  | 002/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Borrowed |  | 003/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Equity |  | 001/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Equity |  | 002/2021
35057921 | PUEBLO 2103 RECOND W TW PAST FUSE 2013 |  | AFUDC-Equity |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Contract |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Contract |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Account Services |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Administration |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Electric Estimating Overtime |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Planning & Permitting-Misc |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Planning & Permitting-Misc |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Planning & Permitting-Misc |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Environmental Planning & Permitting-Misc |  | 004/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Cust Care |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Electric |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Electric |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Environmental Land |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Environmental Land |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Indirect Labor - Environmental Land |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Mapping |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Mapping |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Paid Time Off |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Paid Time Off |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Paid Time Off |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Borrowed |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Borrowed |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Borrowed |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Equity |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Equity |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | AFUDC-Equity |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Benefits OH |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Benefits OH |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Benefits OH |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Building Service Overhead |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Building Service Overhead |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Building Service Overhead |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Capitalized A&G |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Capitalized A&G |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Capitalized A&G |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Fleet OH - Elec |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Fleet OH - Elec |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | IT Device OH |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | IT Device OH |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | IT Device OH |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Operation Mgmt & Support - Electric |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Operation Mgmt & Support - Electric |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Payroll Taxes OH |  | 001/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Payroll Taxes OH |  | 002/2021
35058026 | CWSP:EL DORADO PH 2101 LR 63464 OH TO UG |  | Payroll Taxes OH |  | 003/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Borrowed |  | 001/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Borrowed |  | 002/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Borrowed |  | 003/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Equity |  | 001/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Equity |  | 002/2021
35058060 | SWIFT 2110 - CONDUCTOR REPL |  | AFUDC-Equity |  | 003/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Borrowed |  | 001/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Borrowed |  | 002/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Borrowed |  | 003/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Equity |  | 001/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Equity |  | 002/2021
35058272 | CWSP- EL DORADO 2101 OCB ZONE PHASE 2 |  | AFUDC-Equity |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Contracts |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Electric Construction Contract |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Environmental Contract |  | 004/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Consulting Services - Engineering |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Consulting Services - Engineering |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Consulting Services - Engineering |  | 004/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Engineering/Mapping |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Engineering/Mapping |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Indirect Labor - Electric |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Indirect Labor - Electric |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Indirect Labor - Electric |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Mapping |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Mapping |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Mapping |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Paid Time Off |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Paid Time Off |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Paid Time Off |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Borrowed |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Borrowed |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Borrowed |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Equity |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Equity |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | AFUDC-Equity |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Benefits OH |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Benefits OH |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Benefits OH |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Building Service Overhead |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Building Service Overhead |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Building Service Overhead |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Capitalized A&G |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Capitalized A&G |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Capitalized A&G |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Cash Discount earned |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Fleet OH - Elec |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Fleet OH - Elec |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Fleet OH - Elec |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | IT Device OH |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | IT Device OH |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | IT Device OH |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Payroll Taxes OH |  | 001/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Payroll Taxes OH |  | 002/2021
35058273 | CWSP- EL DORADO 2101 OCB ZONE PHASE 1 |  | Payroll Taxes OH |  | 003/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Borrowed |  | 001/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Borrowed |  | 002/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Borrowed |  | 003/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Equity |  | 001/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Equity |  | 002/2021
35058794 | CWSP - APPLE HILL 2102 - 7502 - PHASE 1 |  | AFUDC-Equity |  | 003/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Borrowed |  | 001/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Borrowed |  | 002/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Borrowed |  | 003/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Equity |  | 001/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Equity |  | 002/2021
35058795 | CWSP - APPLE HILL 2102 - 7502 - PHASE 2 |  | AFUDC-Equity |  | 003/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Borrowed |  | 001/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Borrowed |  | 002/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Borrowed |  | 003/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Equity |  | 001/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Equity |  | 002/2021
35058797 | CWSP - APPLE HILL 2102 - 7502 - PHASE 3 |  | AFUDC-Equity |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Construction Inspection |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Construction Inspection |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Electric Construction Contract |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Electric Construction Contract |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Electric Construction Contract |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Electric Construction Contract |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Indirect Labor - Electric |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Indirect Labor - Electric |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Indirect Labor - Electric |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Mapping |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Mapping |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Mapping |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Paid Time Off |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Paid Time Off |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Paid Time Off |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Benefits OH |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Benefits OH |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Benefits OH |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Building Service Overhead |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Building Service Overhead |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Building Service Overhead |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Capitalized A&G |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Capitalized A&G |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Capitalized A&G |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Fleet OH - Elec |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Fleet OH - Elec |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Fleet OH - Elec |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | IT Device OH |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | IT Device OH |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | IT Device OH |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Payroll Taxes OH |  | 001/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Payroll Taxes OH |  | 002/2021
35058905 | CWSP - VOLTA 1102 - LR 1648 -PH 4.1 |  | Payroll Taxes OH |  | 003/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Borrowed |  | 001/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Borrowed |  | 002/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Borrowed |  | 003/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Equity |  | 001/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Equity |  | 002/2021
35059696 | ECHO SUMMIT 1101 – REPLACING TREE ATTACH |  | AFUDC-Equity |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Analyst Services |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Indirect Labor - Environmental Land |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Paid Time Off |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Borrowed |  | 001/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Borrowed |  | 002/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Borrowed |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Equity |  | 001/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Equity |  | 002/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | AFUDC-Equity |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Benefits OH |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Building Service Overhead |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Capitalized A&G |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | IT Device OH |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35060584 | RPL OH WIRE ON OTTER-1101 S030CC121 |  | Payroll Taxes OH |  | 003/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Borrowed |  | 001/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Borrowed |  | 002/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Borrowed |  | 003/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Equity |  | 001/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Equity |  | 002/2021
35060990 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH3.01 |  | AFUDC-Equity |  | 003/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Borrowed |  | 001/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Borrowed |  | 002/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Borrowed |  | 003/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Equity |  | 001/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Equity |  | 002/2021
35060991 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH2.01 |  | AFUDC-Equity |  | 003/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Borrowed |  | 001/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Borrowed |  | 002/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Borrowed |  | 003/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Equity |  | 001/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Equity |  | 002/2021
35060992 | CWSP-BRUNSWICK 1105 LR2140 ZONE-PH1.01 |  | AFUDC-Equity |  | 003/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Equity |  | 001/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Equity |  | 002/2021
35060993 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.1 |  | AFUDC-Equity |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Construction |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Engineering/Mapping |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Mapping |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Paid Time Off |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Paid Time Off |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Technical Services |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Benefits OH |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Benefits OH |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Benefits OH |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | IT Device OH |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | IT Device OH |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | IT Device OH |  | 003/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35060994 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Borrowed |  | 001/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Borrowed |  | 002/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Borrowed |  | 003/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Equity |  | 001/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Equity |  | 002/2021
35060995 | CWSP-BRUNSWICK 1106 LR-2104 ZONE |  | AFUDC-Equity |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Acquisition - Misc |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Indirect Labor - Environmental Land |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Paid Time Off |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Borrowed |  | 001/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Borrowed |  | 002/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Borrowed |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Equity |  | 001/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Equity |  | 002/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | AFUDC-Equity |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Benefits OH |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Building Service Overhead |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Capitalized A&G |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | IT Device OH |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35061041 | CWSP – MONTE RIO 1112 – TS 15401 |  | Payroll Taxes OH |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction Inspection |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Contracts |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Contracts |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electric Construction Contract |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electric Construction Contract |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electric Construction Contract |  | 004/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electric Construction Contract |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electric Construction Contract |  | 004/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Environmental Contract |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Environmental Contract |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Environmental Contract |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Traffic Control Contracts |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Traffic Control Contracts |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Traffic Control Contracts |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Traffic Control Contracts |  | 004/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Consulting Services - Engineering |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Account Services |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Account Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Account Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Acquisition - Misc |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Administration |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Administration |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Administrative Services - OT |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction Doubletime Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction Overtime Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Construction Overtime Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Engineering/Mapping |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Engineering/Mapping |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Cust Care |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Cust Care |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maint & Operate Doubletime Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maint & Operate Doubletime Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Overtime Services |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Overtime Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Overtime Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Services |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Maintain & Operate Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Management Services |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Mapping |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Mapping |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Mapping |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Paid Time Off |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Paid Time Off |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Paid Time Off |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | SCADA Services |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Electl & Electronic Equipment Component |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Material Burden |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Material Burden |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Benefits OH |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Benefits OH |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Benefits OH |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Building Service Overhead |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Building Service Overhead |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Building Service Overhead |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Capitalized A&G |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Capitalized A&G |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Capitalized A&G |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Cash Discount earned |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Cash Discount earned |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Fleet OH - Elec |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Fleet OH - Elec |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Fleet OH - Elec |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | IT Device OH |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | IT Device OH |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | IT Device OH |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Minor Material OH |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Minor Material OH |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Other Land Fees |  | 003/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Payroll Taxes OH |  | 001/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Payroll Taxes OH |  | 002/2021
35061206 | CWSP-BRUNKSWICK 1103 LR50070 ZONE-PH1.1 |  | Payroll Taxes OH |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Contracts |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electric Construction Contract |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electric Construction Contract |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electric Construction Contract |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electric Construction Contract |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Contract |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Account Services |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Account Services |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Account Services |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Administration |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Analyst Svcs Overtime |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction Overtime Services |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction Overtime Services |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction Overtime Services |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Construction Overtime Services |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electric Estimating Overtime |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Engineering/Mapping |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Engineering/Mapping |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Hours - Straight Time |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Cust Care |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Cust Care |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Cust Care |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Electric |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Electric |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - Gas |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Indirect Labor - IT |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Land Rights - Misc |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Maintain & Operate Overtime Services |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Maintain & Operate Services |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Management Services |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Mapping |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Mapping |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Mapping |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Paid Time Off |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Paid Time Off |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Paid Time Off |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Communication & Signaling Equipment |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Electrical Specialties |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Material Burden |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Material Burden |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Material Burden |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Equity |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Equity |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | AFUDC-Equity |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Benefits OH |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Benefits OH |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Benefits OH |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Building Service Overhead |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Building Service Overhead |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Building Service Overhead |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Capitalized A&G |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Capitalized A&G |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Capitalized A&G |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Cash Discount earned |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Fleet OH - Elec |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Fleet OH - Elec |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Fleet OH - Gas |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | IT Device OH |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | IT Device OH |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | IT Device OH |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Minor Material OH |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Minor Material OH |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Minor Material OH |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - Gas |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Operation Mgmt & Support - IT |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Other Land Fees |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Payroll Taxes OH |  | 002/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Payroll Taxes OH |  | 003/2021
35061212 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.1 |  | Permits/Fees |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Environmental Contract |  | 004/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Consulting Services - Engineering |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Indirect Labor - Electric |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Indirect Labor - Electric |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Indirect Labor - Electric |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Mapping |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Mapping |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Mapping |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Paid Time Off |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Paid Time Off |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Paid Time Off |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Benefits OH |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Benefits OH |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Benefits OH |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Building Service Overhead |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Building Service Overhead |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Building Service Overhead |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Capitalized A&G |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Capitalized A&G |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Capitalized A&G |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Fleet OH - Elec |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Fleet OH - Elec |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Fleet OH - Elec |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | IT Device OH |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | IT Device OH |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | IT Device OH |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Payroll Taxes OH |  | 001/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Payroll Taxes OH |  | 002/2021
35061213 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH3 |  | Payroll Taxes OH |  | 003/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Borrowed |  | 001/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Borrowed |  | 002/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Borrowed |  | 003/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Equity |  | 001/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Equity |  | 002/2021
35061810 | CWSP - EL DORADO PH 2101 ZONE 19612 |  | AFUDC-Equity |  | 003/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35061811 | CWSP-EL DORADO PH 2102 LR19542 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Borrowed |  | 001/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Borrowed |  | 002/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Borrowed |  | 003/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Equity |  | 001/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Equity |  | 002/2021
35061812 | CWSP - EL DORADO PH 2102 ZONE 6645 |  | AFUDC-Equity |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Environmental Contract |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Environmental Contract |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Environmental Contract |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Consulting Services - Engineering |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Consulting Services - Engineering |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Construction |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Design Overtime Services |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Design Services |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Design Services Double Time |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Engineering/Mapping |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Engineering/Mapping |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Hours - Overtime |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Hours - Straight Time |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Indirect Labor - IT |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Land Rights - Misc |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Management Services |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Mapping |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Mapping |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Mapping |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Paid Time Off |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Paid Time Off |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Paid Time Off |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Equity |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Equity |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | AFUDC-Equity |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Benefits OH |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Benefits OH |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Benefits OH |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Building Service Overhead |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Building Service Overhead |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Building Service Overhead |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Capitalized A&G |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Capitalized A&G |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Capitalized A&G |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Fleet OH - Elec |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Fleet OH - Elec |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Fleet OH - Elec |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | IT Device OH |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | IT Device OH |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | IT Device OH |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Operation Mgmt & Support - IT |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Payroll Taxes OH |  | 001/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Payroll Taxes OH |  | 002/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Payroll Taxes OH |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Permits/FeesLand Surveying Services |  | 003/2021
35062374 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.1 |  | Permits/FeesLand Surveying Services |  | 004/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Environmental Contract |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Environmental Contract |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Consulting Services - Engineering |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Consulting Services - Engineering |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Consulting Services - Engineering |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Account Services |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Acquisition - Misc |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Acquisition - Misc |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Acquisition - Misc |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Design Overtime Services |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Design Services |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Design Services Double Time |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engineering/Mapping |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engineering/Mapping |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engineering/Mapping |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Engineering/Mapping Services Overtime |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Hours - Straight Time |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Cust Care |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Electric |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Electric |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Indirect Labor - IT |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Land Rights - Misc |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Management Services |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Mapping |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Mapping |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Mapping |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Paid Time Off |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Paid Time Off |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Paid Time Off |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Borrowed |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Equity |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Equity |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | AFUDC-Equity |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Benefits OH |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Benefits OH |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Benefits OH |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Building Service Overhead |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Building Service Overhead |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Building Service Overhead |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Capitalized A&G |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Capitalized A&G |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Capitalized A&G |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Fleet OH - Elec |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Fleet OH - Elec |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Fleet OH - Elec |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | IT Device OH |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | IT Device OH |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | IT Device OH |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Operation Mgmt & Support - IT |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Payroll Taxes OH |  | 001/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Payroll Taxes OH |  | 002/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Payroll Taxes OH |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Permits/FeesLand Surveying Services |  | 003/2021
35062375 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.1 |  | Permits/FeesLand Surveying Services |  | 004/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Environmental Contract |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Environmental Contract |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Consulting Services - Engineering |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Consulting Services - Engineering |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Account Services |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Acquisition - Misc |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Construction |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Design Overtime Services |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Design Services |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engineering/Mapping |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engineering/Mapping |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engineering/Mapping |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Engineering/Mapping Services Overtime |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Hours - Straight Time |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Hours - Straight Time |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Cust Care |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Electric |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Electric |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Electric |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - IT |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Indirect Labor - IT |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Land Rights - Misc |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Management Services |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Mapping |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Mapping |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Mapping |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Paid Time Off |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Paid Time Off |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Paid Time Off |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Borrowed |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Borrowed |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Borrowed |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Equity |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Equity |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | AFUDC-Equity |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Benefits OH |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Benefits OH |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Benefits OH |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Building Service Overhead |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Building Service Overhead |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Building Service Overhead |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Capitalized A&G |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Capitalized A&G |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Capitalized A&G |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Fleet OH - Elec |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Fleet OH - Elec |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Fleet OH - Elec |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | IT Device OH |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | IT Device OH |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | IT Device OH |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Land Acquisition Services |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - IT |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Operation Mgmt & Support - IT |  | 003/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Payroll Taxes OH |  | 001/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Payroll Taxes OH |  | 002/2021
35062376 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.1 |  | Payroll Taxes OH |  | 003/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Borrowed |  | 001/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Borrowed |  | 002/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Borrowed |  | 003/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Equity |  | 001/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Equity |  | 002/2021
35064793 | LP RECONDUCTOR, CABRILLO 1104 S006CC102 |  | AFUDC-Equity |  | 003/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Borrowed |  | 001/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Borrowed |  | 002/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Borrowed |  | 003/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Equity |  | 001/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Equity |  | 002/2021
35065842 | CWSP-EL DORADO 2101 - LR 26000 - PH3 |  | AFUDC-Equity |  | 003/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Engineering/Mapping |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Indirect Labor - Electric |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Paid Time Off |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Borrowed |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Borrowed |  | 002/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Borrowed |  | 003/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Equity |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Equity |  | 002/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | AFUDC-Equity |  | 003/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Benefits OH |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Building Service Overhead |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Capitalized A&G |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Fleet OH - Elec |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | IT Device OH |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Operation Mgmt & Support - Electric |  | 001/2021
35066622 | FOOTHILL 1101 LS CO9973 RECONDUCTOR, SLO |  | Payroll Taxes OH |  | 001/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Borrowed |  | 001/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Borrowed |  | 002/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Borrowed |  | 003/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Equity |  | 001/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Equity |  | 002/2021
35067619 | CWSP – MONTE RIO 1112 – LR 120 |  | AFUDC-Equity |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Contracts |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Electric Construction Contract |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Indirect Labor - Electric |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Mapping |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Paid Time Off |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Benefits OH |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Building Service Overhead |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Capitalized A&G |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Fleet OH - Elec |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | IT Device OH |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Operation Mgmt & Support - Electric |  | 003/2021
35072146 | RPL 17,500' 4AR TIER 3 SILVERADO 2105 |  | Payroll Taxes OH |  | 003/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Account Services |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Engineering/Mapping |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Indirect Labor - Cust Care |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Indirect Labor - Electric |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Paid Time Off |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Paid Time Off |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Borrowed |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Borrowed |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Borrowed |  | 003/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Equity |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Equity |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | AFUDC-Equity |  | 003/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Benefits OH |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Benefits OH |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Building Service Overhead |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Building Service Overhead |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Capitalized A&G |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Capitalized A&G |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Fleet OH - Elec |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | IT Device OH |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | IT Device OH |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Payroll Taxes OH |  | 001/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Payroll Taxes OH |  | 002/2021
35072147 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.1 |  | Permits/FeesLand Surveying Services |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Contracts |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Contracts |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Environmental Contract |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Environmental Contract |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Environmental Contract |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Environmental Contract |  | 004/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Construction |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Construction Overtime Services |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Engineering/Mapping |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Engineering/Mapping |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Engineering/Mapping |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Indirect Labor - Electric |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Indirect Labor - Electric |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Mapping |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Mapping |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Mapping |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Paid Time Off |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Paid Time Off |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Paid Time Off |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Material Burden |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Material Burden |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Equity |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Equity |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | AFUDC-Equity |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Benefits OH |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Benefits OH |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Benefits OH |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Building Service Overhead |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Building Service Overhead |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Building Service Overhead |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Capitalized A&G |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Capitalized A&G |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Capitalized A&G |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Fleet OH - Elec |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Fleet OH - Elec |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | IT Device OH |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | IT Device OH |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | IT Device OH |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Minor Material OH |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Minor Material OH |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Payroll Taxes OH |  | 002/2021
35072360 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.1 |  | Payroll Taxes OH |  | 003/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Environmental Contract |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Mapping |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Paid Time Off |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Equity |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Equity |  | 002/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | AFUDC-Equity |  | 003/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Benefits OH |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Building Service Overhead |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Capitalized A&G |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | IT Device OH |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35072361 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.1 |  | Permits/FeesLand Surveying Services |  | 001/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Borrowed |  | 001/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Borrowed |  | 002/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Borrowed |  | 003/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Equity |  | 001/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Equity |  | 002/2021
35074388 | RECOND GV2101 FUSE 12347 ZONE |  | AFUDC-Equity |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Contracts |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Environmental Contract |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Environmental Contract |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Consulting Services - Engineering |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Consulting Services - Engineering |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Consulting Services - Engineering |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Administration |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Administration |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Administrative Services - OT |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Analyst Services |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Analyst Svcs Overtime |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Construction |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Design Drafting Services |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Design Drafting Services |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Design Drafting Services - Overtime |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Design Drafting Services - Overtime |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Design Services |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Drafting Doubletime |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Drafting Doubletime |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Engineering/Mapping |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Engineering/Mapping |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Electric |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Electric |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Electric |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Environmental Land |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Environmental Land |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Indirect Labor - Environmental Land |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Mapping |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Mapping |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Mapping |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Paid Time Off |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Paid Time Off |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Paid Time Off |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Benefits OH |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Benefits OH |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Benefits OH |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Building Service Overhead |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Building Service Overhead |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Building Service Overhead |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Capitalized A&G |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Capitalized A&G |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Capitalized A&G |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Fleet OH - Elec |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Fleet OH - Elec |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Fleet OH - Elec |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | IT Device OH |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | IT Device OH |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | IT Device OH |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Electric |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Electric |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Electric |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Payroll Taxes OH |  | 001/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Payroll Taxes OH |  | 002/2021
35075103 | FROGTOWN 1701 TIER 2 RECOND – FUSE L2969 |  | Payroll Taxes OH |  | 003/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Borrowed |  | 001/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Borrowed |  | 002/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Borrowed |  | 003/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Equity |  | 001/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Equity |  | 002/2021
35077348 | RECONDUCTOR 17547 FT OF 4ACSR W 2CU TW |  | AFUDC-Equity |  | 003/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Indirect Labor - Electric |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Paid Time Off |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Project Management Services |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Benefits OH |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Building Service Overhead |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Capitalized A&G |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Fleet OH - Elec |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | IT Device OH |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Operation Mgmt & Support - Electric |  | 001/2021
35080227 | CALISTOGA 1101 - BENNETT LN RECONDUCTOR |  | Payroll Taxes OH |  | 001/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Borrowed |  | 001/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Borrowed |  | 002/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Borrowed |  | 003/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Equity |  | 001/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Equity |  | 002/2021
35081862 | MARTELL 1101 RECOND. 4ACSR W/ 1/0AR TW |  | AFUDC-Equity |  | 003/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Hours - Straight Time |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Indirect Labor - Electric |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Indirect Labor - IT |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Maintain & Operate Overtime Services |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Paid Time Off |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Benefits OH |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Building Service Overhead |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Capitalized A&G |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Fleet OH - Elec |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | IT Device OH |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Operation Mgmt & Support - Electric |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Operation Mgmt & Support - IT |  | 002/2021
35085534 | CWSP - SILVERADO 2104 - LR722 PH 1E |  | Payroll Taxes OH |  | 002/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Electric Construction Contract |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Electric Construction Contract |  | 004/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Indirect Labor - Electric |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Indirect Labor - Electric |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Mapping |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Paid Time Off |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Paid Time Off |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Project Management Services |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Benefits OH |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Benefits OH |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Building Service Overhead |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Building Service Overhead |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Capitalized A&G |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Capitalized A&G |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Fleet OH - Elec |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Fleet OH - Elec |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | IT Device OH |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | IT Device OH |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Operation Mgmt & Support - Electric |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Operation Mgmt & Support - Electric |  | 003/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Payroll Taxes OH |  | 001/2021
35085535 | CWSP - SILVERADO 2104 - LR722 PH 1F |  | Payroll Taxes OH |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Contracts |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Electric Construction Contract |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Indirect Labor - Electric |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Mapping |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Paid Time Off |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Benefits OH |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Building Service Overhead |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Capitalized A&G |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Fleet OH - Elec |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | IT Device OH |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Operation Mgmt & Support - Electric |  | 003/2021
35085537 | CWSP - SILVERADO 2104 - LR722 PH 1H |  | Payroll Taxes OH |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Electric Construction Contract |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Indirect Labor - Electric |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Mapping |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Paid Time Off |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Benefits OH |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Building Service Overhead |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Capitalized A&G |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Fleet OH - Elec |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | IT Device OH |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35085539 | SILVERADO 2105 WIRE DOWN - PH 2 |  | Payroll Taxes OH |  | 003/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Borrowed |  | 001/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Borrowed |  | 002/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Borrowed |  | 003/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Equity |  | 001/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Equity |  | 002/2021
35085680 | SILVERADO 2105 WIRE DOWN - PH 3 |  | AFUDC-Equity |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Traffic Control Contracts |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Consulting Services - Engineering |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Consulting Services - Engineering |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Consulting Services - Environmental Perm |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Consulting Services - Environmental Perm |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Administrative Services - OT |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Indirect Labor - Electric |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Indirect Labor - Electric |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Indirect Labor - Environmental Land |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Indirect Labor - Environmental Land |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Mapping |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Mapping |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Paid Time Off |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Paid Time Off |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Paid Time Off |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Benefits OH |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Benefits OH |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Benefits OH |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Building Service Overhead |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Building Service Overhead |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Building Service Overhead |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Capitalized A&G |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Capitalized A&G |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Capitalized A&G |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Encroachment Permit Fees |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Fleet OH - Elec |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Fleet OH - Elec |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | IT Device OH |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | IT Device OH |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | IT Device OH |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Operation Mgmt & Support - Electric |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Operation Mgmt & Support - Electric |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Payroll Taxes OH |  | 001/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Payroll Taxes OH |  | 002/2021
35085847 | OH RECONDUCTOR - ROB ROY 2105 -S027CC118 |  | Payroll Taxes OH |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Account Services |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Account Services |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Electric Estimating Overtime |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Engineering/Mapping |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Indirect Labor - Cust Care |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Indirect Labor - Cust Care |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Indirect Labor - Electric |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Indirect Labor - Electric |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Paid Time Off |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Paid Time Off |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Paid Time Off |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Borrowed |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Borrowed |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Borrowed |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Equity |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Equity |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | AFUDC-Equity |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Benefits OH |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Benefits OH |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Benefits OH |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Building Service Overhead |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Building Service Overhead |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Building Service Overhead |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Capitalized A&G |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Capitalized A&G |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Capitalized A&G |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Fleet OH - Elec |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Fleet OH - Elec |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | IT Device OH |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | IT Device OH |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | IT Device OH |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Payroll Taxes OH |  | 001/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Payroll Taxes OH |  | 002/2021
35094389 | CWSP-KONOCTI 1102-LR 532 PH 2 |  | Payroll Taxes OH |  | 003/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Account Services |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Engineering/Mapping |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Engineering/Mapping |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Indirect Labor - Cust Care |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Indirect Labor - Electric |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Indirect Labor - Electric |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Paid Time Off |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Paid Time Off |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Borrowed |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Borrowed |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Borrowed |  | 003/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Equity |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Equity |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | AFUDC-Equity |  | 003/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Benefits OH |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Benefits OH |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Building Service Overhead |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Building Service Overhead |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Capitalized A&G |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Capitalized A&G |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Fleet OH - Elec |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Fleet OH - Elec |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | IT Device OH |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | IT Device OH |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Payroll Taxes OH |  | 001/2021
35094391 | CWSP-KONOCTI 1102-LR 532 PH 4 |  | Payroll Taxes OH |  | 002/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Electric Estimating Doubletime |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Electric Estimating Overtime |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Indirect Labor - Electric |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Paid Time Off |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Conductors, Cable & Wire Connectors |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Material Burden |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Benefits OH |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Building Service Overhead |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Capitalized A&G |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Fleet OH - Elec |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | IT Device OH |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Minor Material OH |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Operation Mgmt & Support - Electric |  | 001/2021
35094393 | OCGC KONOCTI - 1102 - LR 532 PH 6 (OH) |  | Payroll Taxes OH |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Environmental Contract |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Environmental Contract |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Account Services |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Indirect Labor - Cust Care |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Indirect Labor - Electric |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Indirect Labor - Electric |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Indirect Labor - Electric |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Mapping |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Mapping |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Paid Time Off |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Paid Time Off |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Paid Time Off |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Project Management Services |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Benefits OH |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Benefits OH |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Benefits OH |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Building Service Overhead |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Building Service Overhead |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Building Service Overhead |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Capitalized A&G |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Capitalized A&G |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Capitalized A&G |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Fleet OH - Elec |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Fleet OH - Elec |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Fleet OH - Elec |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | IT Device OH |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | IT Device OH |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | IT Device OH |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Payroll Taxes OH |  | 001/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Payroll Taxes OH |  | 002/2021
35094394 | OCGC CWSP-KONOCTI 1102-LR 532 PH 7 |  | Payroll Taxes OH |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Engineering/Mapping |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Engineering/Mapping |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Engineering/Mapping |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Indirect Labor - Electric |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Indirect Labor - Electric |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Indirect Labor - Electric |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Paid Time Off |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Paid Time Off |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Paid Time Off |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Borrowed |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Borrowed |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Borrowed |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Equity |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Equity |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | AFUDC-Equity |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Benefits OH |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Benefits OH |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Benefits OH |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Building Service Overhead |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Building Service Overhead |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Building Service Overhead |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Capitalized A&G |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Capitalized A&G |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Capitalized A&G |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Fleet OH - Elec |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Fleet OH - Elec |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Fleet OH - Elec |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | IT Device OH |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | IT Device OH |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | IT Device OH |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Payroll Taxes OH |  | 001/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Payroll Taxes OH |  | 002/2021
35094395 | CWSP-KONOCTI 1102-LR 532 PH 8 |  | Payroll Taxes OH |  | 003/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Account Services |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Account Services |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Engineering/Mapping |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Engineering/Mapping |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Indirect Labor - Cust Care |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Indirect Labor - Cust Care |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Indirect Labor - Electric |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Indirect Labor - Electric |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Paid Time Off |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Paid Time Off |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Borrowed |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Borrowed |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Borrowed |  | 003/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Equity |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Equity |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | AFUDC-Equity |  | 003/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Benefits OH |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Benefits OH |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Building Service Overhead |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Building Service Overhead |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Capitalized A&G |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Capitalized A&G |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Fleet OH - Elec |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Fleet OH - Elec |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | IT Device OH |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | IT Device OH |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Payroll Taxes OH |  | 001/2021
35094396 | CWSP-KONOCTI 1102-LR 532 PH 9 |  | Payroll Taxes OH |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Electric Construction Contract |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Environmental Contract |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Environmental Contract |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Environmental Contract |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Environmental Contract |  | 004/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Gas Construction Contract |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Traffic Control Contracts |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Traffic Control Contracts |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Administration |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Construction |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Construction Doubletime Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Construction Overtime Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Engineering/Mapping |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Engineering/Mapping |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Engineering/Mapping |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Field Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Indirect Labor - Electric |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Indirect Labor - Electric |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Indirect Labor - Electric |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Indirect Labor - Environmental Land |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Maint & Operate Doubletime Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Maintain & Operate Overtime Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Maintain & Operate Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Mapping |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Mapping |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Mapping |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Paid Time Off |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Paid Time Off |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Paid Time Off |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Project Management Services |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Project Management Services |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Material Burden |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Benefits OH |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Benefits OH |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Benefits OH |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Building Service Overhead |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Building Service Overhead |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Building Service Overhead |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Capitalized A&G |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Capitalized A&G |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Capitalized A&G |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Cash Discount earned |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Cash Discount earned |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Fleet OH - Elec |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Fleet OH - Elec |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Fleet OH - Elec |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | IT Device OH |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | IT Device OH |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | IT Device OH |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Minor Material OH |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Payroll Taxes OH |  | 001/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Payroll Taxes OH |  | 002/2021
35094397 | OCGC CWSP-KONOCTI 1102-LR 532 PH 10 |  | Payroll Taxes OH |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Construction Management Contracts |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Contract |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Contract |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Contract |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Contract |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Consulting Services - Environmental Perm |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Acquisition - Misc |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Acquisition - Misc |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Analyst Services |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Analyst Services |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Analyst Svcs Overtime |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Electric Estimating |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Electric Estimating |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Engineering/Mapping |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Engineering/Mapping |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Engineering/Mapping |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Manage L&EM |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Mapping |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Mapping |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Mapping |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Paid Time Off |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Paid Time Off |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Paid Time Off |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Equity |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Equity |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | AFUDC-Equity |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Benefits OH |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Benefits OH |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Benefits OH |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Building Service Overhead |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Building Service Overhead |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Building Service Overhead |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Capitalized A&G |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Capitalized A&G |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Capitalized A&G |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | IT Device OH |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | IT Device OH |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | IT Device OH |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35094513 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Permits/FeesLand Surveying Services |  | 002/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35094514 | CWSP-ORO FINO 1101 LR-2022 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Equity |  | 001/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Equity |  | 002/2021
35094515 | CWSP-ORO FINO 1101-LR 2022 PH 2.1 |  | AFUDC-Equity |  | 003/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Environmental Contract |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Mapping |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Paid Time Off |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Equity |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Equity |  | 002/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | AFUDC-Equity |  | 003/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Benefits OH |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Building Service Overhead |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Capitalized A&G |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | IT Device OH |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094516 | CWSP-ORO FINO 1101 OCB PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Environmental Contract |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Mapping |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Paid Time Off |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Equity |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Equity |  | 002/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | AFUDC-Equity |  | 003/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Benefits OH |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Building Service Overhead |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Capitalized A&G |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | IT Device OH |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35094517 | CWSP-ORO FINO 1101 OCB PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Borrowed |  | 001/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Borrowed |  | 002/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Borrowed |  | 003/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Equity |  | 001/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Equity |  | 002/2021
35094518 | CWSP-ORO FINO 1101 OCB PH 3.1 |  | AFUDC-Equity |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Consulting Services - Environmental Perm |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Indirect Labor - Electric |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Mapping |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Paid Time Off |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Borrowed |  | 001/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Borrowed |  | 002/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Borrowed |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Equity |  | 001/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Equity |  | 002/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | AFUDC-Equity |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Benefits OH |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Building Service Overhead |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Capitalized A&G |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Fleet OH - Elec |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | IT Device OH |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35094519 | CWSP-ORO FINO 1102 LR-2560 PH 1 |  | Payroll Taxes OH |  | 003/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Equity |  | 001/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Equity |  | 002/2021
35095160 | CWSP-ORO FINO 1102 LR-2560 PH 2.1 |  | AFUDC-Equity |  | 003/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Environmental Contract |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Environmental Contract |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Mapping |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Mapping |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Paid Time Off |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Paid Time Off |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Benefits OH |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Benefits OH |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Building Service Overhead |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Building Service Overhead |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Capitalized A&G |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Capitalized A&G |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | IT Device OH |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35095161 | CWSP-ORO FINO 1102 LR-76008 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Engineering/Mapping |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Paid Time Off |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Equity |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Equity |  | 002/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | AFUDC-Equity |  | 003/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Benefits OH |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Building Service Overhead |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Capitalized A&G |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | IT Device OH |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095162 | CWSP-ORO FINO 1102 LR-76008 PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Acquisition - Misc |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Engineering/Mapping |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Engineering/Mapping |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Indirect Labor - Electric |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Paid Time Off |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Paid Time Off |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Equity |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Equity |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | AFUDC-Equity |  | 003/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Benefits OH |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Benefits OH |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Building Service Overhead |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Building Service Overhead |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Capitalized A&G |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Capitalized A&G |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Fleet OH - Elec |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | IT Device OH |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | IT Device OH |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Payroll Taxes OH |  | 002/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Permits/FeesLand Surveying Services |  | 001/2021
35095163 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.1 |  | Permits/FeesLand Surveying Services |  | 002/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Borrowed |  | 001/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Borrowed |  | 002/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Borrowed |  | 003/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Equity |  | 001/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Equity |  | 002/2021
35095164 | CWSP-ORO FINO 1101 LR-2022 PH 3.1 |  | AFUDC-Equity |  | 003/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Electric Construction Contract |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Indirect Labor - Electric |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Mapping |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Paid Time Off |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Benefits OH |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Building Service Overhead |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Capitalized A&G |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Fleet OH - Elec |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | IT Device OH |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095165 | CWSP - VOLTA 1102 - LR 1648 -PH 3.1 |  | Payroll Taxes OH |  | 001/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Environmental Contract |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Indirect Labor - Electric |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Mapping |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Paid Time Off |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Benefits OH |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Building Service Overhead |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Capitalized A&G |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Fleet OH - Elec |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | IT Device OH |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Operation Mgmt & Support - Electric |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Payroll Taxes OH |  | 002/2021
35095166 | CWSP - EL DORADO 2102 - LR19562 - PH 1.0 |  | Permits/Fees |  | 002/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Engineering/Mapping |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Paid Time Off |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Equity |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Equity |  | 002/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | AFUDC-Equity |  | 003/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Benefits OH |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Building Service Overhead |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Capitalized A&G |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | IT Device OH |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095167 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Contracts |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Analyst Svcs Overtime |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Engineering/Mapping |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Mapping |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Paid Time Off |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Paid Time Off |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Equity |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Equity |  | 002/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | AFUDC-Equity |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Benefits OH |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Benefits OH |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Building Service Overhead |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Building Service Overhead |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Capitalized A&G |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Capitalized A&G |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | IT Device OH |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | IT Device OH |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35095168 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Contracts |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Electric Construction Contract |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Electric Construction Contract |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Environmental Contract |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Environmental Contract |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Environmental Contract |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Environmental Contract |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Gas Construction Contract |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Gas Construction Contract |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Consulting Services - Engineering |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Construction |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Construction |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Construction |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Engineering/Mapping |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Indirect Labor - Electric |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Indirect Labor - Electric |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Indirect Labor - Electric |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Indirect Labor - Environmental Land |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Indirect Labor - Environmental Land |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Land Rights - Misc |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Land Rights - Misc |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Mapping |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Mapping |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Mapping |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Paid Time Off |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Paid Time Off |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Paid Time Off |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | AFUDC-Borrowed |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Benefits OH |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Benefits OH |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Benefits OH |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Building Service Overhead |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Building Service Overhead |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Building Service Overhead |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Capitalized A&G |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Capitalized A&G |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Capitalized A&G |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Cash Discount earned |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Fleet OH - Elec |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Fleet OH - Elec |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Fleet OH - Elec |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | IT Device OH |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | IT Device OH |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | IT Device OH |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Payroll Taxes OH |  | 001/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Payroll Taxes OH |  | 002/2021
35098621 | CWSP-COLUMBIA HILL 1101-LR 2212 PH4 |  | Payroll Taxes OH |  | 003/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Contracts |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Contracts |  | 004/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Indirect Labor - Electric |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Mapping |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Paid Time Off |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Benefits OH |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Building Service Overhead |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Capitalized A&G |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Fleet OH - Elec |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | IT Device OH |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 PH5 |  | Payroll Taxes OH |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Electl & Electronic Equipment Component |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Material Burden |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Benefits OH |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Building Service Overhead |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | IT Device OH |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Minor Material OH |  | 001/2021
35103065 | CWSP - MORAGA 1101 - LR 108540 PH 1 |  | Payroll Taxes OH |  | 001/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Engineering/Mapping |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Engineering/Mapping |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Indirect Labor - Electric |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Indirect Labor - Electric |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Paid Time Off |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Paid Time Off |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Benefits OH |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Benefits OH |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Building Service Overhead |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Building Service Overhead |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Capitalized A&G |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Capitalized A&G |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Fleet OH - Elec |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Fleet OH - Elec |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | IT Device OH |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | IT Device OH |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Payroll Taxes OH |  | 002/2021
35103323 | CWSP - MORAGA 1101 - LR 108540 - PH 2 |  | Payroll Taxes OH |  | 003/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Electric Construction Contract |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Consulting Services - Environmental Perm |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Indirect Labor - Electric |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Mapping |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Paid Time Off |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Benefits OH |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Building Service Overhead |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Capitalized A&G |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Fleet OH - Elec |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | IT Device OH |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35106042 | CWSP - VOLTA 1102 - LR 1648 - PH1.2 |  | Payroll Taxes OH |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Contracts |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Electric Construction Contract |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Indirect Labor - Electric |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Indirect Labor - Electric |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Mapping |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Mapping |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Paid Time Off |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Paid Time Off |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Benefits OH |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Benefits OH |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Building Service Overhead |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Building Service Overhead |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Capitalized A&G |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Capitalized A&G |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Fleet OH - Elec |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Fleet OH - Elec |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | IT Device OH |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | IT Device OH |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Payroll Taxes OH |  | 001/2021
35106265 | CWSP - VOLTA 1102 - LR 1648 - PH1.3 |  | Payroll Taxes OH |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Electric Construction Contract |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Electric Construction Contract |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Electric Construction Contract |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Environmental Contract |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Environmental Contract |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Environmental Contract |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Indirect Labor - Electric |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Indirect Labor - Electric |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Indirect Labor - Electric |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Mapping |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Mapping |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Mapping |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Paid Time Off |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Paid Time Off |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Paid Time Off |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Benefits OH |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Benefits OH |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Benefits OH |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Building Service Overhead |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Building Service Overhead |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Building Service Overhead |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Capitalized A&G |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Capitalized A&G |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Capitalized A&G |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Fleet OH - Elec |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Fleet OH - Elec |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Fleet OH - Elec |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | IT Device OH |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | IT Device OH |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | IT Device OH |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Payroll Taxes OH |  | 001/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Payroll Taxes OH |  | 002/2021
35106331 | CWSP - VOLTA 1102 - LR 1648 - PH1.4 |  | Payroll Taxes OH |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Electric Construction Contract |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Electric Construction Contract |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Electric Construction Contract |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Consulting Services - Environmental Perm |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Mapping |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Mapping |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Mapping |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Paid Time Off |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Paid Time Off |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Paid Time Off |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Benefits OH |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Benefits OH |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Benefits OH |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Building Service Overhead |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Building Service Overhead |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Building Service Overhead |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Capitalized A&G |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Capitalized A&G |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Capitalized A&G |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Cellular Phone Use |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Fleet OH - Elec |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Fleet OH - Elec |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Fleet OH - Elec |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | IT Device OH |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | IT Device OH |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | IT Device OH |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Payroll Taxes OH |  | 001/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Payroll Taxes OH |  | 002/2021
35107688 | CWSP - VOLTA 1102 - LR 1648 -PH1.1 |  | Payroll Taxes OH |  | 003/2021
35107689 | OCGC CWSP - PINE GROVE 1102 - LR1222 - |  | Reimbursed Mileage Expense |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Material Burden |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Benefits OH |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Building Service Overhead |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Cash Discount earned |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | IT Device OH |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Minor Material OH |  | 003/2021
35109540 | CWSP-EL DORADO 2101-19752- PHASE 1.2 |  | Payroll Taxes OH |  | 003/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35109541 | CWSP - EL DORADO 2101 - 19752 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Environmental Contract |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Environmental Contract |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Environmental Contract |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Indirect Labor - Electric |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Indirect Labor - Electric |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Indirect Labor - Electric |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Mapping |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Mapping |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Mapping |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Paid Time Off |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Paid Time Off |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Paid Time Off |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Benefits OH |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Benefits OH |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Benefits OH |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Building Service Overhead |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Building Service Overhead |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Building Service Overhead |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Capitalized A&G |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Capitalized A&G |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Capitalized A&G |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Fleet OH - Elec |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Fleet OH - Elec |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Fleet OH - Elec |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | IT Device OH |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | IT Device OH |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | IT Device OH |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Payroll Taxes OH |  | 001/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Payroll Taxes OH |  | 002/2021
35109542 | CWSP-EL DORADO 2101-19752- PHASE 1.4 |  | Payroll Taxes OH |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Electric Construction Contract |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Electric Construction Contract |  | 004/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Indirect Labor - Electric |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Mapping |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Paid Time Off |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Benefits OH |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Building Service Overhead |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Capitalized A&G |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Fleet OH - Elec |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | IT Device OH |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109545 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.2 |  | Payroll Taxes OH |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Electric Estimating |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Indirect Labor - Electric |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Paid Time Off |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Borrowed |  | 001/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Borrowed |  | 002/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Borrowed |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Equity |  | 001/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Equity |  | 002/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | AFUDC-Equity |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Benefits OH |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Building Service Overhead |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Capitalized A&G |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Fleet OH - Elec |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | IT Device OH |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109546 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.3 |  | Payroll Taxes OH |  | 003/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Borrowed |  | 001/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Borrowed |  | 002/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Borrowed |  | 003/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Equity |  | 001/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Equity |  | 002/2021
35109547 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.4 |  | AFUDC-Equity |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Contracts |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Electric Construction Contract |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Electric Construction Contract |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Indirect Labor - Electric |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Indirect Labor - Electric |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Mapping |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Mapping |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Paid Time Off |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Paid Time Off |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Fabricated Structures |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Material Burden |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Benefits OH |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Benefits OH |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Building Service Overhead |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Building Service Overhead |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Capitalized A&G |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Capitalized A&G |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Cash Discount earned |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Cash Discount earned |  | 002/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Fleet OH - Elec |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Fleet OH - Elec |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | IT Device OH |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | IT Device OH |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Minor Material OH |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Payroll Taxes OH |  | 001/2021
35109548 | CWSP - EL DORADO 2101 - 19752 -PHASE 2.5 |  | Payroll Taxes OH |  | 003/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Construction Inspection |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Electric Construction Contract |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Electric Construction Contract |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Indirect Labor - Electric |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Mapping |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Paid Time Off |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Benefits OH |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Building Service Overhead |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Capitalized A&G |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Fleet OH - Elec |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | IT Device OH |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109549 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.2 |  | Payroll Taxes OH |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Account Services |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Indirect Labor - Cust Care |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Paid Time Off |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Benefits OH |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Billing Credit - CIAC Non Taxable |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Building Service Overhead |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Capitalized A&G |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | IT Device OH |  | 001/2021
35109552 | CWSP - EL DORADO 2101 - 19752 -PHASE 3.5 |  | Payroll Taxes OH |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Account Services |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Indirect Labor - Cust Care |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Paid Time Off |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Benefits OH |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Building Service Overhead |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Capitalized A&G |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | IT Device OH |  | 001/2021
35109554 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.2 |  | Payroll Taxes OH |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Construction Inspection |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Indirect Labor - Electric |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Mapping |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Paid Time Off |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Benefits OH |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Building Service Overhead |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Capitalized A&G |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Fleet OH - Elec |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | IT Device OH |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109555 | CWSP - EL DORADO 2101 - 19752 -PHASE 4.3 |  | Payroll Taxes OH |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Construction Inspection |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Construction Inspection |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Construction Inspection |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Contracts |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Electric Construction Contract |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Indirect Labor - Electric |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Indirect Labor - Electric |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Mapping |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Mapping |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Mapping |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Paid Time Off |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Paid Time Off |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Paid Time Off |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Benefits OH |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Benefits OH |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Benefits OH |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Building Service Overhead |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Building Service Overhead |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Building Service Overhead |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Capitalized A&G |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Capitalized A&G |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Capitalized A&G |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Fleet OH - Elec |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Fleet OH - Elec |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Fleet OH - Elec |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | IT Device OH |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | IT Device OH |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | IT Device OH |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Payroll Taxes OH |  | 001/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Payroll Taxes OH |  | 002/2021
35109737 | CWSP-VOLTA 1102-LR 1648-PH2.2 |  | Payroll Taxes OH |  | 003/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Consulting Services - Environmental Perm |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Indirect Labor - Electric |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Mapping |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Paid Time Off |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Benefits OH |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Capitalized A&G |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Fleet OH - Elec |  | 001/2021
35109738 | CWSP-VOLTA 1102-LR 1648-PH2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Construction Inspection |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Construction Inspection |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Construction Inspection |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Electric Construction Contract |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Indirect Labor - Electric |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Indirect Labor - Electric |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Mapping |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Mapping |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Mapping |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Paid Time Off |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Paid Time Off |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Paid Time Off |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Benefits OH |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Benefits OH |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Benefits OH |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Building Service Overhead |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Building Service Overhead |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Building Service Overhead |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Capitalized A&G |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Capitalized A&G |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Capitalized A&G |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Fleet OH - Elec |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Fleet OH - Elec |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Fleet OH - Elec |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | IT Device OH |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | IT Device OH |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | IT Device OH |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Payroll Taxes OH |  | 001/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Payroll Taxes OH |  | 002/2021
35109739 | CWSP-VOLTA 1102-LR 1648-PH2.4 |  | Payroll Taxes OH |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Construction Inspection |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Construction Inspection |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Construction Inspection |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Electric Construction Contract |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Electric Construction Contract |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Electric Construction Contract |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Indirect Labor - Electric |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Indirect Labor - Electric |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Indirect Labor - Electric |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Mapping |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Mapping |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Mapping |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Paid Time Off |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Paid Time Off |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Paid Time Off |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Benefits OH |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Benefits OH |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Benefits OH |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Building Service Overhead |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Building Service Overhead |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Building Service Overhead |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Capitalized A&G |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Capitalized A&G |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Capitalized A&G |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Fleet OH - Elec |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Fleet OH - Elec |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Fleet OH - Elec |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | IT Device OH |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | IT Device OH |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | IT Device OH |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Payroll Taxes OH |  | 001/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Payroll Taxes OH |  | 002/2021
35110440 | CWSP-VOLTA 1102-LR 1648-PH2.5 |  | Payroll Taxes OH |  | 003/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Electric Construction Contract |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Indirect Labor - Electric |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Mapping |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Paid Time Off |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Benefits OH |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Building Service Overhead |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Capitalized A&G |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Fleet OH - Elec |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | IT Device OH |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110441 | CWSP-VOLTA 1102-LR 1648-PH2.6 |  | Payroll Taxes OH |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Electric Construction Contract |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Electric Construction Contract |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Electric Construction Contract |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Indirect Labor - Electric |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Indirect Labor - Electric |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Indirect Labor - Electric |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Mapping |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Mapping |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Mapping |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Paid Time Off |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Paid Time Off |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Paid Time Off |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Benefits OH |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Benefits OH |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Benefits OH |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Building Service Overhead |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Building Service Overhead |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Building Service Overhead |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Capitalized A&G |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Capitalized A&G |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Capitalized A&G |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Fleet OH - Elec |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Fleet OH - Elec |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Fleet OH - Elec |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | IT Device OH |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | IT Device OH |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | IT Device OH |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Payroll Taxes OH |  | 001/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Payroll Taxes OH |  | 002/2021
35110442 | CWSP-VOLTA 1102-LR 1648-PH3.2 |  | Payroll Taxes OH |  | 003/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Electric Construction Contract |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Indirect Labor - Electric |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Mapping |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Paid Time Off |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Benefits OH |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Building Service Overhead |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Capitalized A&G |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Fleet OH - Elec |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | IT Device OH |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110443 | CWSP-VOLTA 1102-LR 1648-PH3.3 |  | Payroll Taxes OH |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Electric Construction Contract |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Indirect Labor - Electric |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Mapping |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Paid Time Off |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Benefits OH |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Building Service Overhead |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Capitalized A&G |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Fleet OH - Elec |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | IT Device OH |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110444 | CWSP-VOLTA 1102-LR 1648-PH3.4 |  | Payroll Taxes OH |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Construction Inspection |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Construction Inspection |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Electric Construction Contract |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Electric Construction Contract |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Construction |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Indirect Labor - Electric |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Indirect Labor - Electric |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Indirect Labor - Electric |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Mapping |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Mapping |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Mapping |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Paid Time Off |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Paid Time Off |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Paid Time Off |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Electrical Specialties |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Material Burden |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Materials Not Otherwise Classified |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Transformers, Regulators & Capacitors |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Benefits OH |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Benefits OH |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Benefits OH |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Building Service Overhead |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Building Service Overhead |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Building Service Overhead |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Capitalized A&G |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Capitalized A&G |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Capitalized A&G |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Cellular Phone Use |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Fleet OH - Elec |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Fleet OH - Elec |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Fleet OH - Elec |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | IT Device OH |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | IT Device OH |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | IT Device OH |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Minor Material OH |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Payroll Taxes OH |  | 001/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Payroll Taxes OH |  | 002/2021
35110445 | CWSP-VOLTA 1102-LR 1648-PH4.2 |  | Payroll Taxes OH |  | 003/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Electric Construction Contract |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Indirect Labor - Electric |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Mapping |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Paid Time Off |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Benefits OH |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Building Service Overhead |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Capitalized A&G |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Fleet OH - Elec |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | IT Device OH |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110446 | CWSP-VOLTA 1102-LR 1648-PH4.3 |  | Payroll Taxes OH |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Construction Inspection |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Electric Construction Contract |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Indirect Labor - Electric |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Indirect Labor - Electric |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Mapping |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Mapping |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Paid Time Off |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Paid Time Off |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Benefits OH |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Benefits OH |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Building Service Overhead |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Building Service Overhead |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Capitalized A&G |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Capitalized A&G |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Fleet OH - Elec |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Fleet OH - Elec |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | IT Device OH |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | IT Device OH |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Payroll Taxes OH |  | 001/2021
35110447 | CWSP-VOLTA 1102-LR 1648-PH4.4 |  | Payroll Taxes OH |  | 002/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Construction Inspection |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Indirect Labor - Electric |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Mapping |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Paid Time Off |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Benefits OH |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Building Service Overhead |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Capitalized A&G |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Fleet OH - Elec |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | IT Device OH |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35110448 | CWSP-VOLTA 1102-LR 1648-PH4.5 |  | Payroll Taxes OH |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Electric Construction Contract |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Environmental Contract |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Environmental Contract |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Environmental Contract |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Administration |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Engineering/Mapping |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Engineering/Mapping |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Mapping |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Mapping |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Mapping |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Paid Time Off |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Paid Time Off |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Paid Time Off |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Benefits OH |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Benefits OH |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Benefits OH |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Building Service Overhead |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Building Service Overhead |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Building Service Overhead |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Capitalized A&G |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Capitalized A&G |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Capitalized A&G |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Cash Discount earned |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Cash Discount earned |  | 004/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | IT Device OH |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | IT Device OH |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | IT Device OH |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35112425 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Electric Construction Contract |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Electric Construction Contract |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Electric Construction Contract |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Electric Construction Contract |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Environmental Contract |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Environmental Contract |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Contractor Consultant |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Acquisition - Misc |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Acquisition - Misc |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Engineering/Mapping |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Engineering/Mapping |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Indirect Labor - Electric |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Indirect Labor - Environmental Land |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Land Rights - Misc |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Mapping |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Mapping |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Paid Time Off |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Paid Time Off |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Paid Time Off |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Benefits OH |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Benefits OH |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Benefits OH |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Building Service Overhead |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Building Service Overhead |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Building Service Overhead |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Capitalized A&G |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Capitalized A&G |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Capitalized A&G |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Cash Discount earned |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Fleet OH - Elec |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | IT Device OH |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | IT Device OH |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | IT Device OH |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Land Acquisition Services |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Land Acquisition Services |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Land Acquisition Services |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Land Acquisition Services |  | 004/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35112429 | CWSP - EL DORADO 2101 - OCBZONE - PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Environmental Contract |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Mapping |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Paid Time Off |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Benefits OH |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Building Service Overhead |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Capitalized A&G |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Cellular Phone Use |  | 001/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Cellular Phone Use |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | IT Device OH |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112431 | CWSP - EL DORADO 2102 - LR19562 - PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Contracts |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Electric Construction Contract |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Contract |  | 004/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Gas Construction Contract |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Consulting Services - Engineering |  | 004/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Administration |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Administration |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Administration |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Mapping |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Mapping |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Mapping |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Paid Time Off |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Paid Time Off |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Paid Time Off |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Benefits OH |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Benefits OH |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Benefits OH |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Building Service Overhead |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Building Service Overhead |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Building Service Overhead |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Capitalized A&G |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Capitalized A&G |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Capitalized A&G |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Cash Discount earned |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | IT Device OH |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | IT Device OH |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | IT Device OH |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Permits/Fees |  | 002/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Postage |  | 001/2021
35112432 | CWSP - EL DORADO 2102 - LR19562 - PH 1.2 |  | Reimbursed Mileage Expense |  | 002/2021
35112433 | CWSP - EL DORADO 2102 - LR19562 - PH 1.3 |  | Permits/Fees |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Contracts |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Electric Construction Contract |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Environmental Contract |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Environmental Contract |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Environmental Contract |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Environmental Contract |  | 004/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Administration |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Indirect Labor - Environmental Land |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Mapping |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Mapping |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Mapping |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Paid Time Off |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Paid Time Off |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Paid Time Off |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Benefits OH |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Benefits OH |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Benefits OH |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Building Service Overhead |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Building Service Overhead |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Building Service Overhead |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Capitalized A&G |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Capitalized A&G |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Capitalized A&G |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | IT Device OH |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | IT Device OH |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | IT Device OH |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35112434 | CWSP - EL DORADO 2102 - LR19562 - PH 1.4 |  | Permits/Fees |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Environmental Contract |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Mapping |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Paid Time Off |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Benefits OH |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Building Service Overhead |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Capitalized A&G |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | IT Device OH |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35112435 | CWSP - EL DORADO 2102 - LR19562 - PH 1.5 |  | Permits/Fees |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Environmental Contract |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Mapping |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Paid Time Off |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Material Burden |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Benefits OH |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Benefits OH |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Building Service Overhead |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Building Service Overhead |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Capitalized A&G |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | IT Device OH |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | IT Device OH |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Minor Material OH |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35112437 | CWSP - EL DORADO 2102 - LR19562 - PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Borrowed |  | 001/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Borrowed |  | 002/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Borrowed |  | 003/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Equity |  | 001/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Equity |  | 002/2021
35112968 | WOODSIDE 1101 RECOND FUSE 1097 ZONE |  | AFUDC-Equity |  | 003/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Electric Estimating Overtime |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Engineering/Mapping |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Engineering/Mapping |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Paid Time Off |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Paid Time Off |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Equity |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Equity |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | AFUDC-Equity |  | 003/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Benefits OH |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Benefits OH |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Building Service Overhead |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Building Service Overhead |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Capitalized A&G |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Capitalized A&G |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | IT Device OH |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | IT Device OH |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35112972 | CWSP - WEST POINT 1101 -LR 13444- PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Environmental Contract |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Environmental Contract |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Traffic Control Contracts |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Electric Estimating Overtime |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Engineering/Mapping |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Engineering/Mapping |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Mapping |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Mapping |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Paid Time Off |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Paid Time Off |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Equity |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Equity |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | AFUDC-Equity |  | 003/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Benefits OH |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Benefits OH |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Building Service Overhead |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Building Service Overhead |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Capitalized A&G |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Capitalized A&G |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | IT Device OH |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | IT Device OH |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35112973 | CWSP - WEST POINT 1101 -LR 13444- PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Engineering/Mapping |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Engineering/Mapping |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Paid Time Off |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Paid Time Off |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Equity |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Equity |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | AFUDC-Equity |  | 003/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Benefits OH |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Benefits OH |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Building Service Overhead |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Building Service Overhead |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Capitalized A&G |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Capitalized A&G |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | IT Device OH |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | IT Device OH |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35112974 | CWSP - WEST POINT 1101 -LR 13444- PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Engineering/Mapping |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Engineering/Mapping |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Paid Time Off |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Paid Time Off |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Equity |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Equity |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | AFUDC-Equity |  | 003/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Benefits OH |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Benefits OH |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Building Service Overhead |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Building Service Overhead |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Capitalized A&G |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Capitalized A&G |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | IT Device OH |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | IT Device OH |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35112975 | CWSP - WEST POINT 1101 -LR 13444- PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Engineering/Mapping |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Engineering/Mapping |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Indirect Labor - Electric |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Paid Time Off |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Paid Time Off |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Equity |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Equity |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | AFUDC-Equity |  | 003/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Benefits OH |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Benefits OH |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Building Service Overhead |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Building Service Overhead |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Capitalized A&G |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Capitalized A&G |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Fleet OH - Elec |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | IT Device OH |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | IT Device OH |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35112976 | CWSP - WEST POINT 1101 -LR 13444- PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Engineering/Mapping |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Engineering/Mapping |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Paid Time Off |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Paid Time Off |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Equity |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Equity |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | AFUDC-Equity |  | 003/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Benefits OH |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Benefits OH |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Building Service Overhead |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Building Service Overhead |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Capitalized A&G |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Capitalized A&G |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | IT Device OH |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | IT Device OH |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35112977 | CWSP - WEST POINT 1101 -LR 13444- PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Contracts |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Engineering/Mapping |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Mapping |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Paid Time Off |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Equity |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Equity |  | 002/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | AFUDC-Equity |  | 003/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Benefits OH |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Building Service Overhead |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Capitalized A&G |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | IT Device OH |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112978 | CWSP - WEST POINT 1101 -LR 13444- PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Contracts |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Engineering/Mapping |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Mapping |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Paid Time Off |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Equity |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Equity |  | 002/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | AFUDC-Equity |  | 003/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Benefits OH |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Building Service Overhead |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Capitalized A&G |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | IT Device OH |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35112979 | CWSP - WEST POINT 1101 -LR 13444- PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Contracts |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Engineering/Mapping |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Mapping |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Paid Time Off |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Equity |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Equity |  | 002/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | AFUDC-Equity |  | 003/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Benefits OH |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Building Service Overhead |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Capitalized A&G |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | IT Device OH |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113100 | CWSP - WEST POINT 1101 -LR 13444- PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Contracts |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Contracts |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Contracts |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Contracts |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Electric Construction Contract |  | 004/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Environmental Contract |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Environmental Contract |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Environmental Contract |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Environmental Contract |  | 004/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Acquisition - Misc |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Electric Estimating Overtime |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Engineering/Mapping |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Engineering/Mapping |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Engineering/Mapping |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Indirect Labor - Environmental Land |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Mapping |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Mapping |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Mapping |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Paid Time Off |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Paid Time Off |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Paid Time Off |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Benefits OH |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Benefits OH |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Benefits OH |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Building Service Overhead |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Building Service Overhead |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Building Service Overhead |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Capitalized A&G |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Capitalized A&G |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Capitalized A&G |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | IT Device OH |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | IT Device OH |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | IT Device OH |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Payroll Taxes OH |  | 002/2021
35113101 | CWSP - WEST POINT 1101 -LR 13444- PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Contracts |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Contracts |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Electric Construction Contract |  | 004/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Environmental Contract |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Environmental Contract |  | 004/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Engineering/Mapping |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Engineering/Mapping |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Engineering/Mapping |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Indirect Labor - Electric |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Indirect Labor - Electric |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Indirect Labor - Electric |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Mapping |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Paid Time Off |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Paid Time Off |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Paid Time Off |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Benefits OH |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Benefits OH |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Benefits OH |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Building Service Overhead |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Building Service Overhead |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Building Service Overhead |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Capitalized A&G |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Capitalized A&G |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Capitalized A&G |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Fleet OH - Elec |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Fleet OH - Elec |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Fleet OH - Elec |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | IT Device OH |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | IT Device OH |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | IT Device OH |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Payroll Taxes OH |  | 001/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Payroll Taxes OH |  | 002/2021
35113102 | CWSP - WEST POINT 1101 -LR 13444- PH 2.6 |  | Payroll Taxes OH |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Contracts |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 004/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Environmental Contract |  | 004/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Consulting Services - Engineering |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Consulting Services - Engineering |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Consulting Services - Engineering |  | 004/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Indirect Labor - Electric |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Indirect Labor - Electric |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Indirect Labor - Electric |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Mapping |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Mapping |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Mapping |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Paid Time Off |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Paid Time Off |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Paid Time Off |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Benefits OH |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Benefits OH |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Benefits OH |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Building Service Overhead |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Building Service Overhead |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Capitalized A&G |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Capitalized A&G |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Capitalized A&G |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Cash Discount earned |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Fleet OH - Elec |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Fleet OH - Elec |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Fleet OH - Elec |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | IT Device OH |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | IT Device OH |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Payroll Taxes OH |  | 001/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Payroll Taxes OH |  | 002/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Payroll Taxes OH |  | 003/2021
35113105 | CWSP - LOS GATOS 1106 - LB44 - PHASE 1.4 |  | Postage |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Account Services |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Indirect Labor - Cust Care |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Paid Time Off |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Borrowed |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Borrowed |  | 002/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Borrowed |  | 003/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Equity |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Equity |  | 002/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | AFUDC-Equity |  | 003/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Benefits OH |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Building Service Overhead |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Capitalized A&G |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | IT Device OH |  | 001/2021
35113106 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.2B |  | Payroll Taxes OH |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Account Services |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Indirect Labor - Cust Care |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Paid Time Off |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Borrowed |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Borrowed |  | 002/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Borrowed |  | 003/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Equity |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Equity |  | 002/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | AFUDC-Equity |  | 003/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Benefits OH |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Building Service Overhead |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Capitalized A&G |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | IT Device OH |  | 001/2021
35113107 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.3C |  | Payroll Taxes OH |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Contracts |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Contracts |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Contracts |  | 004/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Contract |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Contract |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Contract |  | 004/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Contract |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Contract |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Traffic Control Contracts |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Account Services |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Account Services |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Account Services |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Acquisition - Misc |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Acquisition - Misc |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Administration |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice DT |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice DT |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice OT |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Apprentice OT |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction Doubletime Services |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction Doubletime Services |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction Overtime Services |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Construction Overtime Services |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Engineering/Mapping |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Engineering/Mapping |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Engineering/Mapping |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Engineering/Mapping |  | 004/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Environmental Planning & Permitting-Misc |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Cust Care |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Cust Care |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Cust Care |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Electric |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Electric |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Electric |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Environmental Land |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Indirect Labor - Environmental Land |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Maint & Operate Doubletime Services |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Mapping |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Mapping |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Mapping |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Paid Time Off |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Paid Time Off |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Paid Time Off |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Material Burden |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Material Burden |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Borrowed |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Borrowed |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Borrowed |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Equity |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Equity |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | AFUDC-Equity |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Benefits OH |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Benefits OH |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Benefits OH |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Building Service Overhead |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Building Service Overhead |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Building Service Overhead |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Capitalized A&G |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Capitalized A&G |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Capitalized A&G |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Fleet OH - Elec |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Fleet OH - Elec |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Fleet OH - Elec |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | IT Device OH |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | IT Device OH |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | IT Device OH |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Minor Material OH |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Minor Material OH |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Operation Mgmt & Support - Electric |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Operation Mgmt & Support - Electric |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Operation Mgmt & Support - Electric |  | 003/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Other Land Fees |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Payroll Taxes OH |  | 001/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Payroll Taxes OH |  | 002/2021
35113108 | CWSP - LOS GATOS 1106 - LB44 - PHASE2.4D |  | Payroll Taxes OH |  | 003/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Account Services |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Indirect Labor - Cust Care |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Paid Time Off |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Borrowed |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Borrowed |  | 002/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Borrowed |  | 003/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Equity |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Equity |  | 002/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | AFUDC-Equity |  | 003/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Benefits OH |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Building Service Overhead |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Capitalized A&G |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | IT Device OH |  | 001/2021
35113110 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.3 |  | Payroll Taxes OH |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Account Services |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Indirect Labor - Cust Care |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Paid Time Off |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Borrowed |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Borrowed |  | 002/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Borrowed |  | 003/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Equity |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Equity |  | 002/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | AFUDC-Equity |  | 003/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Benefits OH |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Building Service Overhead |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Capitalized A&G |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | IT Device OH |  | 001/2021
35113111 | CWSP - LOS GATOS 1106 - LB44 - PHASE 3.4 |  | Payroll Taxes OH |  | 001/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Borrowed |  | 001/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Borrowed |  | 002/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Borrowed |  | 003/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Equity |  | 001/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Equity |  | 002/2021
35113945 | CWSP - BRUNSWICK 1102 - LR 1010 |  | AFUDC-Equity |  | 003/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Borrowed |  | 001/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Borrowed |  | 002/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Borrowed |  | 003/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Equity |  | 001/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Equity |  | 002/2021
35113946 | CWSP - WYANDOTTE 1103 – LR 1974 |  | AFUDC-Equity |  | 003/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Borrowed |  | 001/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Borrowed |  | 002/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Borrowed |  | 003/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Equity |  | 001/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Equity |  | 002/2021
35113947 | CWSP - LOS GATOS 1107 – LR 60114 |  | AFUDC-Equity |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Contracts |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Acquisition - Misc |  | 004/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Administrative Services - OT |  | 004/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Engineering/Mapping |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Mapping |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Mapping |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Paid Time Off |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Paid Time Off |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Paid Time Off |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Benefits OH |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Benefits OH |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Benefits OH |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Building Service Overhead |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Building Service Overhead |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Capitalized A&G |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Capitalized A&G |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Capitalized A&G |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | IT Device OH |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | IT Device OH |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35113950 | CWSP - BIG BASIN 1101 - 10296 - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Contracts |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Consulting Services - Environmental Perm |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Acquisition - Misc |  | 004/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Administrative Services - OT |  | 004/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Mapping |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Paid Time Off |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Benefits OH |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Building Service Overhead |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Capitalized A&G |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | IT Device OH |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35113951 | CWSP - BIG BASIN 1101 - 10296 - PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Engineering/Mapping |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Engineering/Mapping |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Paid Time Off |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Paid Time Off |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Equity |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Equity |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | AFUDC-Equity |  | 003/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Benefits OH |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Benefits OH |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Building Service Overhead |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Building Service Overhead |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Capitalized A&G |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Capitalized A&G |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | IT Device OH |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | IT Device OH |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35113993 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engineering/Mapping |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Engineering/Mapping |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Paid Time Off |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Paid Time Off |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Equity |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Equity |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | AFUDC-Equity |  | 003/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Benefits OH |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Benefits OH |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Building Service Overhead |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Building Service Overhead |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Capitalized A&G |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Capitalized A&G |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | IT Device OH |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | IT Device OH |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35113994 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Environmental Contract |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Environmental Contract |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Engineering/Mapping |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Engineering/Mapping |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Mapping |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Mapping |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Paid Time Off |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Paid Time Off |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Equity |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Equity |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | AFUDC-Equity |  | 003/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Benefits OH |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Benefits OH |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Building Service Overhead |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Building Service Overhead |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Capitalized A&G |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Capitalized A&G |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | IT Device OH |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | IT Device OH |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35113995 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Engineering/Mapping |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Engineering/Mapping |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Paid Time Off |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Paid Time Off |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Equity |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Equity |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | AFUDC-Equity |  | 003/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Benefits OH |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Benefits OH |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Building Service Overhead |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Building Service Overhead |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Capitalized A&G |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Capitalized A&G |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | IT Device OH |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | IT Device OH |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35113996 | CWSP-WEST POINT 1101-OCB&LR12256-PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Electric Estimating Overtime |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Engineering/Mapping |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Engineering/Mapping |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Indirect Labor - Electric |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Indirect Labor - Electric |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Paid Time Off |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Paid Time Off |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Borrowed |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Borrowed |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Borrowed |  | 003/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Equity |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Equity |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | AFUDC-Equity |  | 003/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Benefits OH |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Benefits OH |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Building Service Overhead |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Building Service Overhead |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Capitalized A&G |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Capitalized A&G |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Fleet OH - Elec |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Fleet OH - Elec |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | IT Device OH |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | IT Device OH |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Payroll Taxes OH |  | 001/2021
35113997 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.6 |  | Payroll Taxes OH |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Engineering/Mapping |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Engineering/Mapping |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Indirect Labor - Electric |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Indirect Labor - Electric |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Paid Time Off |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Paid Time Off |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Borrowed |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Borrowed |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Borrowed |  | 003/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Equity |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Equity |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | AFUDC-Equity |  | 003/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Benefits OH |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Benefits OH |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Building Service Overhead |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Building Service Overhead |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Capitalized A&G |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Capitalized A&G |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Fleet OH - Elec |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Fleet OH - Elec |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | IT Device OH |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | IT Device OH |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Payroll Taxes OH |  | 001/2021
35113998 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.7 |  | Payroll Taxes OH |  | 002/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Engineering/Mapping |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Indirect Labor - Electric |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Paid Time Off |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Borrowed |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Borrowed |  | 002/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Borrowed |  | 003/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Equity |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Equity |  | 002/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | AFUDC-Equity |  | 003/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Benefits OH |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Building Service Overhead |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Capitalized A&G |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Fleet OH - Elec |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | IT Device OH |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Operation Mgmt & Support - Electric |  | 001/2021
35113999 | CWSP-WEST POINT 1101-OCB&LR12256-PH1.8 |  | Payroll Taxes OH |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Contracts |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Contracts |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 004/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Contract |  | 004/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Engineering |  | 004/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Environmental Perm |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Environmental Perm |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Consulting Services - Environmental Perm |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Acquisition - Misc |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Construction Overtime Services |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating |  | 004/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating Doubletime |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating Overtime |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Electric Estimating Overtime |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Engineering/Mapping |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Engineering/Mapping |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Engineering/Mapping |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Maintain & Operate Services |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Mapping |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Mapping |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Mapping |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Paid Time Off |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Paid Time Off |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Paid Time Off |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Conductors, Cable & Wire Connectors |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Material Burden |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Benefits OH |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Benefits OH |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Benefits OH |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Building Service Overhead |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Building Service Overhead |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Building Service Overhead |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Capitalized A&G |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Capitalized A&G |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Capitalized A&G |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | IT Device OH |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | IT Device OH |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | IT Device OH |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Minor Material OH |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Other Expenses |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Permits/FeesLand Surveying Services |  | 001/2021
35114040 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Permits/FeesLand Surveying Services |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Environmental Contract |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Environmental Contract |  | 004/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Engineering/Mapping |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Engineering/Mapping |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Engineering/Mapping |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Mapping |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Paid Time Off |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Paid Time Off |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Paid Time Off |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Benefits OH |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Benefits OH |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Benefits OH |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Building Service Overhead |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Building Service Overhead |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Building Service Overhead |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Capitalized A&G |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Capitalized A&G |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Capitalized A&G |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | IT Device OH |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | IT Device OH |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | IT Device OH |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35114041 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Contracts |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Contracts |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Environmental Contract |  | 004/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Security Services |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Security Services |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Traffic Control Contracts |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Consulting Services - Engineering |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Consulting Services - Engineering |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Consulting Services - Engineering |  | 004/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Mapping |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Mapping |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Mapping |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Paid Time Off |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Paid Time Off |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Paid Time Off |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Benefits OH |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Benefits OH |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Benefits OH |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Building Service Overhead |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Building Service Overhead |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Building Service Overhead |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Capitalized A&G |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Capitalized A&G |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Capitalized A&G |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Cash Discount earned |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Cash Discount earned |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | IT Device OH |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | IT Device OH |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | IT Device OH |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35114042 | OCGC PINE GROVE 1102 - LR1222 - PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Contracts |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Contracts |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Contracts |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Environmental Contract |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Environmental Contract |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Environmental Contract |  | 004/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Acquisition - Misc |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Analyst Services |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Analyst Services |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Construction |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Indirect Labor - Environmental Land |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Mapping |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Mapping |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Paid Time Off |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Paid Time Off |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Paid Time Off |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Benefits OH |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Benefits OH |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Benefits OH |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Building Service Overhead |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Building Service Overhead |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Building Service Overhead |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Capitalized A&G |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Capitalized A&G |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Capitalized A&G |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | IT Device OH |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | IT Device OH |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | IT Device OH |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35114043 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Construction Inspection |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Construction Inspection |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Contracts |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Contracts |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Contracts |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Contract |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Contract |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Contract |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Contract |  | 004/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Traffic Control Contracts |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Traffic Control Contracts |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Construction |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Construction Doubletime Services |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Construction Overtime Services |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Engineering/Mapping |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Engineering/Mapping |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Engineering/Mapping |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Indirect Labor - Electric |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Indirect Labor - Environmental Land |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Land Rights - Misc |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Maint & Operate Doubletime Services |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Maintain & Operate Overtime Services |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Maintain & Operate Services |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Maintain & Operate Services |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Mapping |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Mapping |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Mapping |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Paid Time Off |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Paid Time Off |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Paid Time Off |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Benefits OH |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Benefits OH |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Benefits OH |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Building Service Overhead |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Building Service Overhead |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Building Service Overhead |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Capitalized A&G |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Capitalized A&G |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Capitalized A&G |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Fleet OH - Elec |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | IT Device OH |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | IT Device OH |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | IT Device OH |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35114044 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Contracts |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Contracts |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Contracts |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Contracts |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Engineering/Mapping |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Mapping |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Mapping |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Mapping |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Paid Time Off |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Paid Time Off |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Paid Time Off |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Equity |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Equity |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | AFUDC-Equity |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Benefits OH |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Benefits OH |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Benefits OH |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Building Service Overhead |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Building Service Overhead |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Building Service Overhead |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Capitalized A&G |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Capitalized A&G |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Capitalized A&G |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | IT Device OH |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | IT Device OH |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | IT Device OH |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35114045 | CWSP - PINE GROVE 1102 - LR1222 - PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Contracts |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Security Services |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Security Services |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Security Services |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Security Services |  | 004/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engineering/Mapping |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Engineering/Mapping |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Indirect Labor - Electric |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Mapping |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Paid Time Off |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Paid Time Off |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Paid Time Off |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Equity |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Equity |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | AFUDC-Equity |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Benefits OH |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Benefits OH |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Benefits OH |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Building Service Overhead |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Building Service Overhead |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Building Service Overhead |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Capitalized A&G |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Capitalized A&G |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Capitalized A&G |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Cash Discount earned |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Fleet OH - Elec |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | IT Device OH |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | IT Device OH |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | IT Device OH |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Payroll Taxes OH |  | 002/2021
35114046 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Contracts |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Contracts |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Contracts |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Contracts |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Electric Construction Contract |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Environmental Contract |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Environmental Contract |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Environmental Contract |  | 004/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction Doubletime Services |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction Overtime Services |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction Overtime Services |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Construction Overtime Services |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engineering Services - OT |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engineering/Mapping |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engineering/Mapping |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Engineering/Mapping |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Indirect Labor - Electric |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Indirect Labor - Gas |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Maintain & Operate Overtime Services |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Maintain & Operate Services |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Maintain & Operate Services |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Mapping |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Mapping |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Mapping |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Paid Time Off |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Paid Time Off |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Paid Time Off |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Electrical Specialties |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Material Burden |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Material Burden |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Equity |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Equity |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | AFUDC-Equity |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Benefits OH |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Benefits OH |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Benefits OH |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Building Service Overhead |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Building Service Overhead |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Building Service Overhead |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Capitalized A&G |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Capitalized A&G |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Capitalized A&G |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Cash Discount earned |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Fleet OH - Elec |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Fleet OH - Gas |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | IT Device OH |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | IT Device OH |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | IT Device OH |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Meals Expense |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Minor Material OH |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Minor Material OH |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Operation Mgmt & Support - Gas |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Other Expenses |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Other Expenses |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Payroll Taxes OH |  | 002/2021
35114048 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.3 |  | Payroll Taxes OH |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Construction Inspection |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Contracts |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Contracts |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Contracts |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Contracts |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 004/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Environmental Contract |  | 004/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Consulting Services - Engineering |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Consulting Services - Engineering |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Consulting Services - Engineering |  | 004/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Construction |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Engineering/Mapping |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Engineering/Mapping |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Engineering/Mapping |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Indirect Labor - Electric |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Mapping |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Mapping |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Mapping |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Paid Time Off |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Paid Time Off |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Paid Time Off |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Benefits OH |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Benefits OH |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Benefits OH |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Building Service Overhead |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Building Service Overhead |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Building Service Overhead |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Capitalized A&G |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Capitalized A&G |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Capitalized A&G |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Fleet OH - Elec |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | IT Device OH |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | IT Device OH |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | IT Device OH |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Payroll Taxes OH |  | 002/2021
35114049 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Contracts |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Contracts |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Contracts |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Environmental Contract |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Environmental Contract |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Environmental Contract |  | 004/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Design Drafting Services - Overtime |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Engineering/Mapping |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Engineering/Mapping |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Mapping |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Mapping |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Mapping |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Paid Time Off |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Paid Time Off |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Paid Time Off |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Equity |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Equity |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | AFUDC-Equity |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Benefits OH |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Benefits OH |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Benefits OH |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Building Service Overhead |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Building Service Overhead |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Building Service Overhead |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Capitalized A&G |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Capitalized A&G |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Capitalized A&G |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | IT Device OH |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | IT Device OH |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | IT Device OH |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Payroll Taxes OH |  | 002/2021
35114050 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Contracts |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Environmental Contract |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Environmental Contract |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Traffic Control Contracts |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Consulting Services - Engineering |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Consulting Services - Environmental Perm |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Consulting Services - Environmental Perm |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Consulting Services - Environmental Perm |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Construction |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Construction Overtime Services |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Electric Estimating Overtime |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Engineering/Mapping |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Engineering/Mapping |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Engineering/Mapping |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Indirect Labor - Electric |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Indirect Labor - Electric |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Indirect Labor - Electric |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Indirect Labor - Gas |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Mapping |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Mapping |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Mapping |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Paid Time Off |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Paid Time Off |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Paid Time Off |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Electrical Specialties |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Material Burden |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Borrowed |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Borrowed |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Borrowed |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Equity |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Equity |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | AFUDC-Equity |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Benefits OH |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Benefits OH |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Benefits OH |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Building Service Overhead |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Building Service Overhead |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Building Service Overhead |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Building-utilities |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Capitalized A&G |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Capitalized A&G |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Capitalized A&G |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Fleet OH - Elec |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Fleet OH - Elec |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Fleet OH - Elec |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Fleet OH - Gas |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | IT Device OH |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | IT Device OH |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | IT Device OH |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Minor Material OH |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Operation Mgmt & Support - Gas |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Other Expenses |  | 003/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Payroll Taxes OH |  | 001/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Payroll Taxes OH |  | 002/2021
35114051 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.6 |  | Payroll Taxes OH |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Contracts |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Contracts |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Contracts |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Environmental Contract |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Environmental Contract |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Environmental Contract |  | 004/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Engineering/Mapping |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Indirect Labor - Electric |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Indirect Labor - Electric |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Indirect Labor - Electric |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Mapping |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Mapping |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Mapping |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Paid Time Off |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Paid Time Off |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Paid Time Off |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Borrowed |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Borrowed |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Borrowed |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Equity |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Equity |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | AFUDC-Equity |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Benefits OH |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Benefits OH |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Benefits OH |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Building Service Overhead |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Building Service Overhead |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Building Service Overhead |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Capitalized A&G |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Capitalized A&G |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Capitalized A&G |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Fleet OH - Elec |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Fleet OH - Elec |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Fleet OH - Elec |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | IT Device OH |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | IT Device OH |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | IT Device OH |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Payroll Taxes OH |  | 001/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Payroll Taxes OH |  | 002/2021
35114052 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.7 |  | Payroll Taxes OH |  | 003/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Engineering/Mapping |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Indirect Labor - Electric |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Paid Time Off |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Borrowed |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Borrowed |  | 002/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Borrowed |  | 003/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Equity |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Equity |  | 002/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | AFUDC-Equity |  | 003/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Benefits OH |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Building Service Overhead |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Capitalized A&G |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Fleet OH - Elec |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | IT Device OH |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114053 | CWSP - PINE GROVE 1102 - LR1222 - PH 2.8 |  | Payroll Taxes OH |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Contracts |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 004/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Environmental Contract |  | 004/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Administration |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Administration |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Construction |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Construction Overtime Services |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Construction Overtime Services |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Engineering/Mapping |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Engineering/Mapping |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Engineering/Mapping |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Engineering/Mapping |  | 004/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Indirect Labor - Electric |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Indirect Labor - Gas |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Mapping |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Mapping |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Mapping |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Paid Time Off |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Paid Time Off |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Paid Time Off |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Equity |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Equity |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | AFUDC-Equity |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Benefits OH |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Benefits OH |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Benefits OH |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Building Service Overhead |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Building Service Overhead |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Building Service Overhead |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Capitalized A&G |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Capitalized A&G |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Capitalized A&G |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Fleet OH - Elec |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Fleet OH - Gas |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | IT Device OH |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | IT Device OH |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | IT Device OH |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Operation Mgmt & Support - Gas |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Payroll Taxes OH |  | 002/2021
35114100 | XCWSP - CAMP EVERS 2106 - LR5020 PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Environmental Contract |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Environmental Contract |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Environmental Contract |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Environmental Contract |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Consulting Services - Engineering |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Mapping |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Mapping |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Paid Time Off |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Paid Time Off |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Benefits OH |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Benefits OH |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Building Service Overhead |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Building Service Overhead |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Capitalized A&G |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Capitalized A&G |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | IT Device OH |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | IT Device OH |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35114101 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.3 |  | Payroll Taxes OH |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 004/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 004/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Environmental Contract |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Traffic Control Contracts |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Consulting Services - Engineering |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Consulting Services - Engineering |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Consulting Services - Engineering |  | 004/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Construction |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Construction Overtime Services |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Construction Overtime Services |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Engineering/Mapping |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Engineering/Mapping |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Engineering/Mapping |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Indirect Labor - Electric |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Indirect Labor - Gas |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Mapping |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Mapping |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Mapping |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Paid Time Off |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Paid Time Off |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Paid Time Off |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Equity |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Equity |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | AFUDC-Equity |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Benefits OH |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Benefits OH |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Benefits OH |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Building Service Overhead |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Building Service Overhead |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Building Service Overhead |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Capitalized A&G |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Capitalized A&G |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Capitalized A&G |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Cellular Phone Use |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Fleet OH - Elec |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Fleet OH - Gas |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | IT Device OH |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | IT Device OH |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | IT Device OH |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Operation Mgmt & Support - Gas |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Payroll Taxes OH |  | 002/2021
35114102 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Contracts |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Contracts |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Contracts |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 004/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Environmental Contract |  | 004/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Traffic Control Contracts |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Traffic Control Contracts |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Consulting Services - Engineering |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Consulting Services - Engineering |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Consulting Services - Engineering |  | 004/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Account Services |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Account Services |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Account Services |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction Doubletime Services |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction Overtime Services |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Construction Overtime Services |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Engineering/Mapping |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Engineering/Mapping |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Engineering/Mapping |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Cust Care |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Cust Care |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Cust Care |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Gas |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Indirect Labor - Gas |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Maint & Operate Doubletime Services |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Maintain & Operate Overtime Services |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Maintain & Operate Services |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Maintain & Operate Services |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Mapping |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Mapping |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Mapping |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Paid Time Off |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Paid Time Off |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Paid Time Off |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Equity |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Equity |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | AFUDC-Equity |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Benefits OH |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Benefits OH |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Benefits OH |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Building Service Overhead |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Building Service Overhead |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Building Service Overhead |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Capitalized A&G |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Capitalized A&G |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Capitalized A&G |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Cash Discount earned |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Fleet OH - Gas |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Fleet OH - Gas |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | IT Device OH |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | IT Device OH |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | IT Device OH |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Operation Mgmt & Support - Gas |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Operation Mgmt & Support - Gas |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Payroll Taxes OH |  | 002/2021
35114103 | CWSP - CAMP EVERS 2106 - LR5020 - PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Contracts |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Contracts |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 004/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Environmental Contract |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Traffic Control Contracts |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Account Services |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Construction |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Construction |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Construction Doubletime Services |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Construction Overtime Services |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Engineering/Mapping |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Engineering/Mapping |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Engineering/Mapping |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Indirect Labor - Cust Care |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Indirect Labor - Electric |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Indirect Labor - Electric |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Indirect Labor - Electric |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Maintain & Operate Services |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Mapping |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Mapping |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Mapping |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Paid Time Off |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Paid Time Off |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Paid Time Off |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Benefits OH |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Benefits OH |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Benefits OH |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Building Service Overhead |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Building Service Overhead |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Building Service Overhead |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Capitalized A&G |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Capitalized A&G |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Capitalized A&G |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Fleet OH - Elec |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Fleet OH - Elec |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Fleet OH - Elec |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | IT Device OH |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | IT Device OH |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | IT Device OH |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Payroll Taxes OH |  | 001/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Payroll Taxes OH |  | 002/2021
35114104 | XCWSP - CAMP EVERS 2106 - LR5020 -PH 2.6 |  | Payroll Taxes OH |  | 003/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Electric Estimating Overtime |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Engineering/Mapping |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Paid Time Off |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Paid Time Off |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Benefits OH |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Benefits OH |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Building Service Overhead |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Building Service Overhead |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Capitalized A&G |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Capitalized A&G |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | IT Device OH |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | IT Device OH |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35115046 | CWSP - MIWUK 1701 - LR 10600 PH 1.2 |  | Reimbursed Mileage Expense |  | 001/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Engineering/Mapping |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Paid Time Off |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Benefits OH |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Building Service Overhead |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Capitalized A&G |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | IT Device OH |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35115047 | CWSP - MIWUK 1701 - LR 10600 PH 1.3 |  | Reimbursed Mileage Expense |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Environmental Contract |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Electric Estimating Overtime |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Engineering/Mapping |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Mapping |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Paid Time Off |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Paid Time Off |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Benefits OH |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Benefits OH |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Building Service Overhead |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Building Service Overhead |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Capitalized A&G |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Capitalized A&G |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | IT Device OH |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | IT Device OH |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35115048 | CWSP - MIWUK 1701 - LR 10600 PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Environmental Contract |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Construction |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Electric Estimating Overtime |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Engineering/Mapping |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Mapping |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Mapping |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Paid Time Off |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Paid Time Off |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Paid Time Off |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Benefits OH |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Benefits OH |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Benefits OH |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Building Service Overhead |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Building Service Overhead |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Building Service Overhead |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Capitalized A&G |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Capitalized A&G |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Capitalized A&G |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | IT Device OH |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | IT Device OH |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | IT Device OH |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35115049 | CWSP - MIWUK 1701 - LR 10600 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction Inspection |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction Inspection |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction Inspection |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction Inspection |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Contracts |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Electric Construction Contract |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Environmental Contract |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Consulting Services - Environmental Perm |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Consulting Services - Environmental Perm |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Administration |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Construction Overtime Services |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Engineering/Mapping |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Engineering/Mapping |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Engineering/Mapping |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Engineering/Mapping Services Overtime |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services Doubletime |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services Doubletime |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services Overtime |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Field Services Overtime |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maint & Operate Doubletime Services |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maint & Operate Doubletime Services |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maint & Operate Doubletime Services |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Overtime Services |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Overtime Services |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Overtime Services |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Overtime Services |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Services |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Services |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Services |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Maintain & Operate Services |  | 004/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Mapping |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Mapping |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Mapping |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Paid Time Off |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Paid Time Off |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Paid Time Off |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Switching Operation Svcs. - Overtime |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Switching Operator Service |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Material Burden |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Material Burden |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Benefits OH |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Benefits OH |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Benefits OH |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Building Service Overhead |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Building Service Overhead |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Building Service Overhead |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Capitalized A&G |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Capitalized A&G |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Capitalized A&G |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | IT Device OH |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | IT Device OH |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | IT Device OH |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Land Acquisition Services |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Minor Material OH |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Minor Material OH |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35115050 | CWSP - MIWUK 1701_OCB - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Contracts |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Contracts |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Engineering/Mapping |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Mapping |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Mapping |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Paid Time Off |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Paid Time Off |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Paid Time Off |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Material Burden |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Benefits OH |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Benefits OH |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Benefits OH |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Building Service Overhead |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Building Service Overhead |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Building Service Overhead |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Capitalized A&G |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Capitalized A&G |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Capitalized A&G |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | IT Device OH |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | IT Device OH |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | IT Device OH |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Minor Material OH |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35115051 | CWSP - MIWUK 1701_OCB - PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Environmental Contract |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Environmental Contract |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Environmental Contract |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Environmental Contract |  | 004/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Engineering/Mapping |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Engineering/Mapping |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Mapping |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Mapping |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Mapping |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Paid Time Off |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Paid Time Off |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Paid Time Off |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Electl & Electronic Equipment Component |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Electrical Specialties |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Material Burden |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Equity |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Equity |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | AFUDC-Equity |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Benefits OH |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Benefits OH |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Benefits OH |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Building Service Overhead |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Building Service Overhead |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Building Service Overhead |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Capitalized A&G |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Capitalized A&G |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Capitalized A&G |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | IT Device OH |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | IT Device OH |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | IT Device OH |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Minor Material OH |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35115052 | CWSP - MIWUK 1701_OCB - PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Contracts |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 004/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Contract |  | 004/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Consulting Services - Engineering |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Consulting Services - Engineering |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Consulting Services - Engineering |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Consulting Services - Engineering |  | 004/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Account Services |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Account Services |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Construction |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Construction |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Construction Overtime Services |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Engineering/Mapping |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Engineering/Mapping |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Engineering/Mapping |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Cust Care |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Cust Care |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Environmental Land |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Gas |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Indirect Labor - Gas |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Manage L&EM |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Mapping |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Mapping |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Mapping |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Paid Time Off |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Paid Time Off |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Paid Time Off |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Equity |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Equity |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | AFUDC-Equity |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Benefits OH |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Benefits OH |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Benefits OH |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Building Service Overhead |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Building Service Overhead |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Building Service Overhead |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Capitalized A&G |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Capitalized A&G |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Capitalized A&G |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Fleet OH - Gas |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Fleet OH - Gas |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | IT Device OH |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | IT Device OH |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | IT Device OH |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Gas |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Operation Mgmt & Support - Gas |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Other Land Fees |  | 003/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35115053 | CWSP - MIWUK 1701_OCB - PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Inspection |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Inspection |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Contracts |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Electric Construction Contract |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Electric Construction Contract |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Electric Construction Contract |  | 004/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 004/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Contract |  | 004/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Consulting Services - Engineering |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Consulting Services - Engineering |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Consulting Services - Engineering |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Consulting Services - Engineering |  | 004/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Consulting Services - Environmental Perm |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Analyst Services |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Overtime Services |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Overtime Services |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Overtime Services |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Engineering/Mapping |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Engineering/Mapping |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Hours - Straight Time |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - Electric |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - Gas |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Indirect Labor - IT |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Maintain & Operate Services |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Mapping |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Mapping |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Mapping |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Paid Time Off |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Paid Time Off |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Paid Time Off |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Communication & Signaling Equipment |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Conductors, Cable & Wire Connectors |  | 004/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Supplies |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Construction Supplies |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Electrical Specialties |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Fabricated Structures |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Material Burden |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Material Burden |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Materials Not Otherwise Classified |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Equity |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Equity |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | AFUDC-Equity |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Benefits OH |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Benefits OH |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Benefits OH |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Building Service Overhead |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Building Service Overhead |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Building Service Overhead |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Capitalized A&G |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Capitalized A&G |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Capitalized A&G |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Cash Discount earned |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Cellular Phone Use |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Cellular Phone Use |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Fleet OH - Elec |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Fleet OH - Gas |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | IT Device OH |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | IT Device OH |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | IT Device OH |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Minor Material OH |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Minor Material OH |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - Gas |  | 003/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Operation Mgmt & Support - IT |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Payroll Taxes OH |  | 002/2021
35115054 | CWSP - MIWUK 1701 – OCB - PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction Inspection |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Contracts |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Contracts |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Electric Construction Contract |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Contract |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Gas Construction Contract |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Traffic Control Contracts |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Traffic Control Contracts |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Traffic Control Contracts |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Consulting Services - Engineering |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Acquisition - Misc |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Administration |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Administrative Services - OT |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction Overtime Services |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction Overtime Services |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction Overtime Services |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Construction Overtime Services |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Engineering/Mapping |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Engineering/Mapping |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Engineering/Mapping |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Electric |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Environmental Land |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Indirect Labor - Gas |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Manage L&EM |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Manage L&EM |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Mapping |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Mapping |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Mapping |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Paid Time Off |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Paid Time Off |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Paid Time Off |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Material Burden |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Equity |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Equity |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | AFUDC-Equity |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Benefits OH |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Benefits OH |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Benefits OH |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Building Service Overhead |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Building Service Overhead |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Building Service Overhead |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Capitalized A&G |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Capitalized A&G |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Capitalized A&G |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Cash Discount earned |  | 004/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Fleet OH - Elec |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Fleet OH - Gas |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | IT Device OH |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | IT Device OH |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | IT Device OH |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Minor Material OH |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Operation Mgmt & Support - Gas |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Other Land Fees |  | 003/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Payroll Taxes OH |  | 002/2021
35115055 | CWSP - MIWUK 1701 – OCB - PH 2.3 |  | Payroll Taxes OH |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Contracts |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Contracts |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Contracts |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 004/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Environmental Contract |  | 004/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Engineering/Mapping |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Engineering/Mapping |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Indirect Labor - Electric |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Mapping |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Mapping |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Mapping |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Paid Time Off |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Paid Time Off |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Paid Time Off |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Equity |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Equity |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | AFUDC-Equity |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Benefits OH |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Benefits OH |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Benefits OH |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Building Service Overhead |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Building Service Overhead |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Building Service Overhead |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Capitalized A&G |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Capitalized A&G |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Capitalized A&G |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Cash Discount earned |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Fleet OH - Elec |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | IT Device OH |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | IT Device OH |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | IT Device OH |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Payroll Taxes OH |  | 002/2021
35115056 | CWSP - MIWUK 1701 – OCB - PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Contracts |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Environmental Contract |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Environmental Contract |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Engineering/Mapping |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Indirect Labor - Electric |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Indirect Labor - Electric |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Mapping |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Mapping |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Paid Time Off |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Paid Time Off |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Borrowed |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Borrowed |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Equity |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Equity |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | AFUDC-Equity |  | 003/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Benefits OH |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Benefits OH |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Building Service Overhead |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Building Service Overhead |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Capitalized A&G |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Capitalized A&G |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Fleet OH - Elec |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Fleet OH - Elec |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | IT Device OH |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | IT Device OH |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Payroll Taxes OH |  | 001/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Payroll Taxes OH |  | 002/2021
35115057 | CWSP - MIWUK 1701 - OCB - PH2.5 |  | Reimbursed Mileage Expense |  | 001/2021
35115147 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Electric Construction Contract |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Electric Construction Contract |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Account Services |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Construction |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Indirect Labor - Cust Care |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Indirect Labor - Electric |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Indirect Labor - Electric |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Mapping |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Mapping |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Paid Time Off |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Paid Time Off |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Benefits OH |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Benefits OH |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Building Service Overhead |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Building Service Overhead |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Capitalized A&G |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Capitalized A&G |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Fleet OH - Elec |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Fleet OH - Elec |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | IT Device OH |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | IT Device OH |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Payroll Taxes OH |  | 001/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Payroll Taxes OH |  | 003/2021
35115148 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.3 |  | Postage |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Environmental Contract |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Environmental Contract |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Indirect Labor - Electric |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Indirect Labor - Electric |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Mapping |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Mapping |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Paid Time Off |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Paid Time Off |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Benefits OH |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Benefits OH |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Building Service Overhead |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Capitalized A&G |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Capitalized A&G |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Fleet OH - Elec |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Fleet OH - Elec |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | IT Device OH |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Payroll Taxes OH |  | 001/2021
35115150 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.5 |  | Payroll Taxes OH |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Inspection |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Contracts |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Contracts |  | 004/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electric Construction Contract |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electric Construction Contract |  | 004/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electric Construction Contract |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electric Construction Contract |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electric Construction Contract |  | 004/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Environmental Contract |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Environmental Contract |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Environmental Contract |  | 004/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Paving Contracts |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Traffic Control Contracts |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Traffic Control Contracts |  | 004/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Administration |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Analyst Services |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Doubletime Services |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Overtime Services |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Overtime Services |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Overtime Services |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Engineering/Mapping |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Indirect Labor - Electric |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Mapping |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Mapping |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Mapping |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Paid Time Off |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Paid Time Off |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Paid Time Off |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Conductors, Cable & Wire Connectors |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Construction Supplies |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electrical Specialties |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Electrical Specialties |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Material Burden |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Material Burden |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Material Burden |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Equity |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Equity |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | AFUDC-Equity |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Benefits OH |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Benefits OH |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Benefits OH |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Building Service Overhead |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Building Service Overhead |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Building Service Overhead |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Capitalized A&G |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Capitalized A&G |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Capitalized A&G |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Cash Discount earned |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Cash Discount earned |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Fleet OH - Elec |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | IT Device OH |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | IT Device OH |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | IT Device OH |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Minor Material OH |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Minor Material OH |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Minor Material OH |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Other Land Fees |  | 003/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Payroll Taxes OH |  | 002/2021
35115151 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Environmental Contract |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Environmental Contract |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Environmental Contract |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Environmental Contract |  | 004/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Administration |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Administration |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Analyst Services |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Electric Estimating Overtime |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Engineering/Mapping |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Indirect Labor - Electric |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Indirect Labor - Environmental Land |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Mapping |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Mapping |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Mapping |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Paid Time Off |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Paid Time Off |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Paid Time Off |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Equity |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Equity |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | AFUDC-Equity |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Benefits OH |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Benefits OH |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Benefits OH |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Building Service Overhead |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Building Service Overhead |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Building Service Overhead |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Capitalized A&G |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Capitalized A&G |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Capitalized A&G |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Fleet OH - Elec |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | IT Device OH |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | IT Device OH |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | IT Device OH |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Other Land Fees |  | 003/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Payroll Taxes OH |  | 002/2021
35115152 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.3 |  | Payroll Taxes OH |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Electric Construction Contract |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 004/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Contract |  | 004/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Consulting Services - Engineering |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Consulting Services - Engineering |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Consulting Services - Engineering |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Acquisition - Misc |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Administration |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Analyst Services |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction |  | 004/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction Overtime Services |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction Overtime Services |  | 004/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Engineering/Mapping |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Indirect Labor - Electric |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Indirect Labor - Environmental Land |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Mapping |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Mapping |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Mapping |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Paid Time Off |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Paid Time Off |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Paid Time Off |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Conductors, Cable & Wire Connectors |  | 004/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction Supplies |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Construction Supplies |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Electl & Electronic Equipment Component |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Electrical Specialties |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Electrical Specialties |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Electrical Specialties |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Fabricated Structures |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Fabricated Structures |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Gas & Water Specialties |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Material Burden |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Material Burden |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Equity |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Equity |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | AFUDC-Equity |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Benefits OH |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Benefits OH |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Benefits OH |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Building Service Overhead |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Building Service Overhead |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Building Service Overhead |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Capitalized A&G |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Capitalized A&G |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Capitalized A&G |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Cash Discount earned |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Fleet OH - Elec |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | IT Device OH |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | IT Device OH |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | IT Device OH |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Minor Material OH |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Minor Material OH |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Other Land Fees |  | 003/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Payroll Taxes OH |  | 002/2021
35115153 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Contracts |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Contracts |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Contracts |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Electric Construction Contract |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Electric Construction Contract |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Electric Construction Contract |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Contract |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Traffic Control Contracts |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Traffic Control Contracts |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Consulting Services - Engineering |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Consulting Services - Engineering |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Consulting Services - Engineering |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Administration |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Analyst Services |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction Doubletime Services |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction Doubletime Services |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction Overtime Services |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction Overtime Services |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Construction Overtime Services |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Engineering/Mapping |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Engineering/Mapping |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Engineering/Mapping |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Indirect Labor - Environmental Land |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Mapping |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Mapping |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Mapping |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Paid Time Off |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Paid Time Off |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Paid Time Off |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Equity |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Equity |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | AFUDC-Equity |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Benefits OH |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Benefits OH |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Benefits OH |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Building Service Overhead |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Building Service Overhead |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Building Service Overhead |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Capitalized A&G |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Capitalized A&G |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Capitalized A&G |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | IT Device OH |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | IT Device OH |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | IT Device OH |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Other Land Fees |  | 003/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Payroll Taxes OH |  | 002/2021
35115154 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Contracts |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Contracts |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Contracts |  | 004/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 004/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Environmental Contract |  | 004/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Consulting Services - Engineering |  | 004/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Account Services |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Account Services |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Account Services |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Construction |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Construction |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Engineering/Mapping |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Engineering/Mapping |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Cust Care |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Cust Care |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Maint & Operate Doubletime Services |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Maint & Operate Doubletime Services |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Maintain & Operate Services |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Maintain & Operate Services |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Mapping |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Mapping |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Mapping |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Paid Time Off |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Paid Time Off |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Paid Time Off |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Benefits OH |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Benefits OH |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Benefits OH |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Building Service Overhead |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Building Service Overhead |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Building Service Overhead |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Capitalized A&G |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Capitalized A&G |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Capitalized A&G |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | IT Device OH |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | IT Device OH |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | IT Device OH |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35115155 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Environmental Contract |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Environmental Contract |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Environmental Contract |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Environmental Contract |  | 004/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Mapping |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Mapping |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Mapping |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Paid Time Off |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Paid Time Off |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Paid Time Off |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Benefits OH |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Benefits OH |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Benefits OH |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Building Service Overhead |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Building Service Overhead |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Building Service Overhead |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Capitalized A&G |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Capitalized A&G |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Capitalized A&G |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | IT Device OH |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | IT Device OH |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | IT Device OH |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35115156 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115157 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 1.4 |  | Postage |  | 002/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Electric Estimating Overtime |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Paid Time Off |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Equity |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Equity |  | 002/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | AFUDC-Equity |  | 003/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Benefits OH |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Building Service Overhead |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Capitalized A&G |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | IT Device OH |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115847 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Contracts |  | 003/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Contracts |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Contracts |  | 003/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Engineering/Mapping |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Mapping |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Paid Time Off |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Equity |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Equity |  | 002/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | AFUDC-Equity |  | 003/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Benefits OH |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Building Service Overhead |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Capitalized A&G |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | IT Device OH |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115848 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Contracts |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Contracts |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Environmental Contract |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Environmental Contract |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Environmental Contract |  | 004/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Construction |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Engineering/Mapping |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Mapping |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Mapping |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Paid Time Off |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Paid Time Off |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Equity |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Equity |  | 002/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | AFUDC-Equity |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Benefits OH |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Benefits OH |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Building Service Overhead |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Building Service Overhead |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Capitalized A&G |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Capitalized A&G |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | IT Device OH |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | IT Device OH |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35115849 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Contracts |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Contracts |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Engineering/Mapping |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Mapping |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Mapping |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Paid Time Off |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Paid Time Off |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Equity |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Equity |  | 002/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | AFUDC-Equity |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Benefits OH |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Benefits OH |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Building Service Overhead |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Building Service Overhead |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Capitalized A&G |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Capitalized A&G |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | IT Device OH |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | IT Device OH |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35115850 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Environmental Contract |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Traffic Control Contracts |  | 002/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Analyst Services |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Indirect Labor - Electric |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Mapping |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Paid Time Off |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Paid Time Off |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Borrowed |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Borrowed |  | 002/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Borrowed |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Equity |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Equity |  | 002/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | AFUDC-Equity |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Benefits OH |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Benefits OH |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Building Service Overhead |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Building Service Overhead |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Capitalized A&G |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Capitalized A&G |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Fleet OH - Elec |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | IT Device OH |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | IT Device OH |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Payroll Taxes OH |  | 001/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Payroll Taxes OH |  | 003/2021
35115851 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.6 |  | Reimbursed Mileage Expense |  | 003/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Contracts |  | 003/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Contracts |  | 003/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Engineering/Mapping |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Indirect Labor - Electric |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Paid Time Off |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Borrowed |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Borrowed |  | 002/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Borrowed |  | 003/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Equity |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Equity |  | 002/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | AFUDC-Equity |  | 003/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Benefits OH |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Building Service Overhead |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Capitalized A&G |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Fleet OH - Elec |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | IT Device OH |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115852 | CWSP-SALT SPRINGS 2102-LR3142-PH 2.7 |  | Payroll Taxes OH |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Contracts |  | 003/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Contracts |  | 003/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Engineering/Mapping |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Paid Time Off |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Equity |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Equity |  | 002/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | AFUDC-Equity |  | 003/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Benefits OH |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Building Service Overhead |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Capitalized A&G |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | IT Device OH |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115853 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Construction Overtime Services |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Engineering/Mapping |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Engineering/Mapping |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Engineering/Mapping |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Mapping |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Paid Time Off |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Paid Time Off |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Paid Time Off |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Equity |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Equity |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | AFUDC-Equity |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Benefits OH |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Benefits OH |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Benefits OH |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Building Service Overhead |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Building Service Overhead |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Building Service Overhead |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Capitalized A&G |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Capitalized A&G |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Capitalized A&G |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | IT Device OH |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | IT Device OH |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | IT Device OH |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35115854 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Construction Inspection |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Contracts |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Contracts |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Contracts |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Electric Construction Contract |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Electric Construction Contract |  | 004/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Electric Construction Contract |  | 004/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Environmental Contract |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Environmental Contract |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Environmental Contract |  | 004/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Construction |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Construction |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Construction Overtime Services |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Engineering/Mapping |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Engineering/Mapping |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Engineering/Mapping |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Indirect Labor - Gas |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Indirect Labor - Gas |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Maint & Operate Doubletime Services |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Maintain & Operate Overtime Services |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Maintain & Operate Services |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Maintain & Operate Services |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Mapping |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Mapping |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Mapping |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Paid Time Off |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Paid Time Off |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Paid Time Off |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Benefits OH |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Benefits OH |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Benefits OH |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Building Service Overhead |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Building Service Overhead |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Building Service Overhead |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Capitalized A&G |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Capitalized A&G |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Capitalized A&G |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Fleet OH - Gas |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Fleet OH - Gas |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | IT Device OH |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | IT Device OH |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | IT Device OH |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Operation Mgmt & Support - Gas |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Operation Mgmt & Support - Gas |  | 003/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35115855 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Contracts |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Contracts |  | 003/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Contracts |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Contracts |  | 003/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Traffic Control Contracts |  | 002/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Engineering/Mapping |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Mapping |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Paid Time Off |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Equity |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Equity |  | 002/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | AFUDC-Equity |  | 003/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Benefits OH |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Building Service Overhead |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Capitalized A&G |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | IT Device OH |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115856 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Analyst Svcs Overtime |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Electric Estimating |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Engineering/Mapping |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Paid Time Off |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Paid Time Off |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Equity |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Equity |  | 002/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | AFUDC-Equity |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Benefits OH |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Benefits OH |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Building Service Overhead |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Building Service Overhead |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Capitalized A&G |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Capitalized A&G |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | IT Device OH |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | IT Device OH |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35115857 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Contracts |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Contracts |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Traffic Control Contracts |  | 002/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Analyst Services |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Engineering/Mapping |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Indirect Labor - Environmental Land |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Mapping |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Mapping |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Paid Time Off |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Paid Time Off |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Equity |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Equity |  | 002/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | AFUDC-Equity |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Benefits OH |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Benefits OH |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Building Service Overhead |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Building Service Overhead |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Capitalized A&G |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Capitalized A&G |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | IT Device OH |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | IT Device OH |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35115858 | CWSP-SALT SPRINGS 2102-LR3142L491-PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction Inspection |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction Inspection |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction Inspection |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Contracts |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Environmental Contract |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Environmental Contract |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Environmental Contract |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Environmental Contract |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Gas Construction Contract |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Consulting Services - Environmental Perm |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Account Services |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Account Services |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Account Services |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Construction Overtime Services |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Engineering/Mapping |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Engineering/Mapping |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Engineering/Mapping |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Hours - Straight Time |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Cust Care |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Cust Care |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Gas |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - Gas |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Indirect Labor - IT |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Land Rights - Misc |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Land Rights - Misc |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maint & Operate Doubletime Services |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maint & Operate Doubletime Services |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Overtime Services |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Overtime Services |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Overtime Services |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Overtime Services |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Services |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Services |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Maintain & Operate Services |  | 004/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Management Services |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Mapping |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Mapping |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Mapping |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Paid Time Off |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Paid Time Off |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Paid Time Off |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Communication & Signaling Equipment |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Conductors, Cable & Wire Connectors |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electl & Electronic Equipment Component |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electrical Specialties |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Electrical Specialties |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Material Burden |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Material Burden |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Transformers, Regulators & Capacitors |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Benefits OH |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Benefits OH |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Benefits OH |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Building Service Overhead |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Building Service Overhead |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Building Service Overhead |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Capitalized A&G |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Capitalized A&G |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Capitalized A&G |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Cellular Phone Use |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Fleet OH - Gas |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Fleet OH - Gas |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | IT Device OH |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | IT Device OH |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | IT Device OH |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Minor Material OH |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Minor Material OH |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Gas |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - Gas |  | 003/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Operation Mgmt & Support - IT |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35116383 | CWSP - MIWUK 1701 - LR 8060 - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Contracts |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Contracts |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Construction |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Engineering/Mapping |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Engineering/Mapping |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Engineering/Mapping |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Mapping |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Mapping |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Paid Time Off |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Paid Time Off |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Paid Time Off |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Conductors, Cable & Wire Connectors |  | 004/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Construction Supplies |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Electl & Electronic Equipment Component |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Electrical Specialties |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Fabricated Structures |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Material Burden |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Materials Not Otherwise Classified |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Benefits OH |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Benefits OH |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Benefits OH |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Building Service Overhead |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Building Service Overhead |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Building Service Overhead |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Capitalized A&G |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Capitalized A&G |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Capitalized A&G |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | IT Device OH |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | IT Device OH |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | IT Device OH |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Minor Material OH |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35116384 | CWSP - MIWUK 1701 - LR 8060 - PH 1.3 |  | Reimbursed Mileage Expense |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Traffic Control Contracts |  | 001/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Engineering/Mapping |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Paid Time Off |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Paid Time Off |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Equity |  | 001/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Equity |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | AFUDC-Equity |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Benefits OH |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Benefits OH |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Building Service Overhead |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Building Service Overhead |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Capitalized A&G |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Capitalized A&G |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | IT Device OH |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | IT Device OH |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Permits/FeesLand Surveying Services |  | 001/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Permits/FeesLand Surveying Services |  | 002/2021
35116385 | CWSP - MIWUK 1701 - LR 8060 - PH 1.4 |  | Reimbursed Mileage Expense |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Contracts |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Contracts |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Contracts |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Mapping |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Mapping |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Mapping |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Paid Time Off |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Paid Time Off |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Paid Time Off |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Benefits OH |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Benefits OH |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Benefits OH |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Building Service Overhead |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Building Service Overhead |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Building Service Overhead |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Capitalized A&G |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Capitalized A&G |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Capitalized A&G |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | IT Device OH |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | IT Device OH |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | IT Device OH |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35116388 | CWSP - MIWUK 1701 - LR 8060 - PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Environmental Contract |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Environmental Contract |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Indirect Labor - Electric |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Mapping |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Mapping |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Paid Time Off |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Paid Time Off |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Equity |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Equity |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | AFUDC-Equity |  | 003/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Benefits OH |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Benefits OH |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Building Service Overhead |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Building Service Overhead |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Capitalized A&G |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Capitalized A&G |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Fleet OH - Elec |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | IT Device OH |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | IT Device OH |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35116389 | CWSP - MIWUK 1701 - LR 8060 - PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Electric Construction Contract |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Electric Construction Contract |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Environmental Contract |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Environmental Contract |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Environmental Contract |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Environmental Contract |  | 004/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Consulting Services - Environmental Perm |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Engineering/Mapping |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Engineering/Mapping |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Engineering/Mapping |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Mapping |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Mapping |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Mapping |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Paid Time Off |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Paid Time Off |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Paid Time Off |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Benefits OH |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Benefits OH |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Benefits OH |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Building Service Overhead |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Building Service Overhead |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Building Service Overhead |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Capitalized A&G |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Capitalized A&G |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Capitalized A&G |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | IT Device OH |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | IT Device OH |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | IT Device OH |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35116390 | CWSP - MIWUK 1701 - LR 8060 - PH 1.7 |  | Reimbursed Mileage Expense |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction Inspection |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction Inspection |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 004/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Contracts |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Electric Construction Contract |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Electric Construction Contract |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 004/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Contract |  | 004/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Helicopter Contract |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Consulting Services - Engineering |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Consulting Services - Engineering |  | 004/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Construction |  | 004/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Engineering/Mapping |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Engineering/Mapping |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Engineering/Mapping |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Mapping |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Mapping |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Mapping |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Paid Time Off |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Paid Time Off |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Paid Time Off |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Material Burden |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Benefits OH |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Benefits OH |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Benefits OH |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Building Service Overhead |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Building Service Overhead |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Building Service Overhead |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Capitalized A&G |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Capitalized A&G |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Capitalized A&G |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | IT Device OH |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | IT Device OH |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | IT Device OH |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Minor Material OH |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35116391 | CWSP - MIWUK 1702 - OCB - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Contracts |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Contract |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Traffic Control Contracts |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Consulting Services - Engineering |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Consulting Services - Engineering |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Consulting Services - Engineering |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Consulting Services - Engineering |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Account Services |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Account Services |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Administration |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Administration |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Administration |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Apprentice |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Apprentice OT |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction Doubletime Services |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction Doubletime Services |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction Overtime Services |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction Overtime Services |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Construction Overtime Services |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Engineering/Mapping |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Engineering/Mapping |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Cust Care |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Cust Care |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Environmental Land |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Maintain & Operate Services |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Manage L&EM |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Mapping |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Mapping |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Mapping |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Paid Time Off |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Paid Time Off |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Paid Time Off |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Benefits OH |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Benefits OH |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Benefits OH |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Building Service Overhead |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Building Service Overhead |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Building Service Overhead |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Capitalized A&G |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Capitalized A&G |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Capitalized A&G |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Cash Discount earned |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Cash Discount earned |  | 004/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | IT Device OH |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | IT Device OH |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | IT Device OH |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Other Land Fees |  | 003/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35116395 | CWSP - MIWUK 1702 - OCB - PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Contracts |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Contracts |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Contracts |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Engineering/Mapping |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Engineering/Mapping |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Mapping |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Mapping |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Mapping |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Paid Time Off |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Paid Time Off |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Paid Time Off |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Equity |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Equity |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | AFUDC-Equity |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Benefits OH |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Benefits OH |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Benefits OH |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Building Service Overhead |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Building Service Overhead |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Building Service Overhead |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Capitalized A&G |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Capitalized A&G |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Capitalized A&G |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | IT Device OH |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | IT Device OH |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | IT Device OH |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35116396 | CWSP-MIWUK 1702-LR8090-PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Contracts |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Engineering/Mapping |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Mapping |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Paid Time Off |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Paid Time Off |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Equity |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Equity |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | AFUDC-Equity |  | 003/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Benefits OH |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Benefits OH |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Building Service Overhead |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Building Service Overhead |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Capitalized A&G |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Capitalized A&G |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | IT Device OH |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | IT Device OH |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35116397 | CWSP-MIWUK 1702-LR8090-PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Environmental Contract |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Environmental Contract |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Electric Estimating Overtime |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Engineering/Mapping |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Mapping |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Mapping |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Paid Time Off |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Paid Time Off |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Equity |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Equity |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | AFUDC-Equity |  | 003/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Benefits OH |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Benefits OH |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Building Service Overhead |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Building Service Overhead |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Capitalized A&G |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Capitalized A&G |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | IT Device OH |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | IT Device OH |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35116398 | CWSP-MIWUK 1702-LR8090-PH 1.4 |  | Permits/Fees |  | 003/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Contracts |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Electric Estimating Overtime |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Engineering/Mapping |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Mapping |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Paid Time Off |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Paid Time Off |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Benefits OH |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Benefits OH |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Building Service Overhead |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Building Service Overhead |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Capitalized A&G |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Capitalized A&G |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | IT Device OH |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | IT Device OH |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116399 | CWSP-MIWUK 1702-LR8090-PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Environmental Contract |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Electric Estimating Overtime |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Engineering/Mapping |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Indirect Labor - Electric |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Mapping |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Paid Time Off |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Paid Time Off |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Equity |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Equity |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | AFUDC-Equity |  | 003/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Benefits OH |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Benefits OH |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Building Service Overhead |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Building Service Overhead |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Capitalized A&G |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Capitalized A&G |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Fleet OH - Elec |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | IT Device OH |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | IT Device OH |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Permits/Fees |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Permits/Fees |  | 001/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Permits/Fees |  | 002/2021
35116440 | CWSP-MIWUK 1702-LR8090-PH 1.6 |  | Permits/FeesLand Surveying Services |  | 001/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Engineering/Mapping |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Indirect Labor - Electric |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Paid Time Off |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Borrowed |  | 001/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Borrowed |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Borrowed |  | 003/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Equity |  | 001/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Equity |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | AFUDC-Equity |  | 003/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Benefits OH |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Building Service Overhead |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Capitalized A&G |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Fleet OH - Elec |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | IT Device OH |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116441 | CWSP-MIWUK 1702-LR 38218-PH1.2 |  | Payroll Taxes OH |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Construction Inspection |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Construction Inspection |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Contracts |  | 004/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Electric Construction Contract |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Electric Construction Contract |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Electric Construction Contract |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 004/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Environmental Contract |  | 004/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Construction |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Engineering/Mapping |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Engineering/Mapping |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Engineering/Mapping |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Field Services |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Hours - Straight Time |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Indirect Labor - Gas |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Indirect Labor - IT |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Maintain & Operate Overtime Services |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Maintain & Operate Services |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Maintain & Operate Services |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Mapping |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Mapping |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Mapping |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Paid Time Off |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Paid Time Off |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Paid Time Off |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Conductors, Cable & Wire Connectors |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Material Burden |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Material Burden |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | AFUDC-Equity |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Benefits OH |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Benefits OH |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Benefits OH |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Building Service Overhead |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Building Service Overhead |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Building Service Overhead |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Capitalized A&G |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Capitalized A&G |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Capitalized A&G |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Cellular Phone Use |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Cellular Phone Use |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Cellular Phone Use |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Fleet OH - Gas |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | IT Device OH |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | IT Device OH |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | IT Device OH |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Minor Material OH |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Minor Material OH |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Operation Mgmt & Support - Gas |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Operation Mgmt & Support - IT |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35116442 | CWSP-MIWUK 1702-LR 38218-PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Construction Inspection |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Contracts |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Contracts |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Contracts |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Contracts |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Electric Construction Contract |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Electric Construction Contract |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Electric Construction Contract |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Environmental Contract |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Environmental Contract |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Environmental Contract |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Environmental Contract |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Environmental Contract |  | 004/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Engineering/Mapping |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Engineering/Mapping |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Mapping |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Mapping |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Mapping |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Paid Time Off |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Paid Time Off |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Paid Time Off |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Material Burden |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Equity |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Equity |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | AFUDC-Equity |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Benefits OH |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Benefits OH |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Benefits OH |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Building Service Overhead |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Building Service Overhead |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Building Service Overhead |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Capitalized A&G |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Capitalized A&G |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Capitalized A&G |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | IT Device OH |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | IT Device OH |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | IT Device OH |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Minor Material OH |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35116443 | CWSP-MIWUK 1702-LR 38218-PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Contracts |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 004/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Contract |  | 004/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Consulting Services - Engineering |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Analyst Svcs Overtime |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Construction |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Engineering/Mapping |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Engineering/Mapping |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Engineering/Mapping |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Indirect Labor - Environmental Land |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Manage L&EM |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Mapping |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Mapping |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Mapping |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Paid Time Off |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Paid Time Off |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Paid Time Off |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Benefits OH |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Benefits OH |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Benefits OH |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Building Service Overhead |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Building Service Overhead |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Building Service Overhead |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Capitalized A&G |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Capitalized A&G |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Capitalized A&G |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | IT Device OH |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | IT Device OH |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | IT Device OH |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Other Land Fees |  | 003/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35116444 | CWSP-MIWUK 1702-LR 38218-PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | Traffic Control Contracts |  | 002/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Equity |  | 001/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Equity |  | 002/2021
35116511 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.2 |  | AFUDC-Equity |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Construction Management Contracts |  | 002/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Traffic Control Contracts |  | 002/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Acquisition - Misc |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Indirect Labor - Environmental Land |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Rights - Misc |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Paid Time Off |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Paid Time Off |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Equity |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Equity |  | 002/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | AFUDC-Equity |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Benefits OH |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Benefits OH |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Building Service Overhead |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Building Service Overhead |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Capitalized A&G |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Capitalized A&G |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | IT Device OH |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | IT Device OH |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Acquisition Services |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Acquisition Services |  | 002/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Acquisition Services |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Land Acquisition Services |  | 004/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Other Land Fees |  | 003/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35116512 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.3 |  | Payroll Taxes OH |  | 003/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | Traffic Control Contracts |  | 002/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Equity |  | 001/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Equity |  | 002/2021
35116513 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.4 |  | AFUDC-Equity |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Environmental Contract |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Traffic Control Contracts |  | 002/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Analyst Svcs Overtime |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Mapping |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Paid Time Off |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Paid Time Off |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Equity |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Equity |  | 002/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | AFUDC-Equity |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Benefits OH |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Benefits OH |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Building Service Overhead |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Building Service Overhead |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Capitalized A&G |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Capitalized A&G |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | IT Device OH |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | IT Device OH |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35116514 | CWSP – STANISLAUS 1702 - LR1888 - PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Analyst Svcs Overtime |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Paid Time Off |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Benefits OH |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Building Service Overhead |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Capitalized A&G |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | IT Device OH |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116515 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Analyst Svcs Overtime |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Paid Time Off |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Benefits OH |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Building Service Overhead |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Capitalized A&G |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | IT Device OH |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116516 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Environmental Contract |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Environmental Contract |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Traffic Control Contracts |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Analyst Svcs Overtime |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Engineering/Mapping |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Mapping |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Mapping |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Paid Time Off |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Paid Time Off |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Paid Time Off |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Benefits OH |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Benefits OH |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Benefits OH |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Building Service Overhead |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Building Service Overhead |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Building Service Overhead |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Capitalized A&G |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Capitalized A&G |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Capitalized A&G |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | IT Device OH |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | IT Device OH |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | IT Device OH |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35116517 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Traffic Control Contracts |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Analyst Services |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Analyst Svcs Overtime |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Engineering/Mapping |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Indirect Labor - Environmental Land |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Paid Time Off |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Paid Time Off |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Equity |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Equity |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | AFUDC-Equity |  | 003/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Benefits OH |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Benefits OH |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Building Service Overhead |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Building Service Overhead |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Capitalized A&G |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Capitalized A&G |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | IT Device OH |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | IT Device OH |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35116518 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Traffic Control Contracts |  | 002/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Engineering/Mapping |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Paid Time Off |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Equity |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Equity |  | 002/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | AFUDC-Equity |  | 003/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Benefits OH |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Building Service Overhead |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Capitalized A&G |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | IT Device OH |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116519 | CWSP – STANISLAUS 1702 - LR1888 - PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Construction Inspection |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Contracts |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Contracts |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Contracts |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Contracts |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Contracts |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Electric Construction Contract |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Electric Construction Contract |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Electric Construction Contract |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Electric Construction Contract |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 004/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Environmental Contract |  | 004/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Construction |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Construction |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Construction |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Construction |  | 004/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Engineering/Mapping |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Engineering/Mapping |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Engineering/Mapping |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Indirect Labor - Electric |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Indirect Labor - Electric |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Indirect Labor - Electric |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Indirect Labor - Gas |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Mapping |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Mapping |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Mapping |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Paid Time Off |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Paid Time Off |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Paid Time Off |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | AFUDC-Equity |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Benefits OH |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Benefits OH |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Benefits OH |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Building Service Overhead |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Building Service Overhead |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Building Service Overhead |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Capitalized A&G |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Capitalized A&G |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Capitalized A&G |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Fleet OH - Elec |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Fleet OH - Elec |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Fleet OH - Elec |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Fleet OH - Gas |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | IT Device OH |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | IT Device OH |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | IT Device OH |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Operation Mgmt & Support - Gas |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Payroll Taxes OH |  | 001/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Payroll Taxes OH |  | 002/2021
35116800 | CWSP-MIWUK 1702-LR 6018-PHASE 1.2 |  | Payroll Taxes OH |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Construction Inspection |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Contracts |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Contracts |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Construction Contract |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Construction Contract |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Construction Contract |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Construction Contract |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Construction Contract |  | 004/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 004/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Contract |  | 004/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Consulting Services - Engineering |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Consulting Services - Engineering |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Consulting Services - Engineering |  | 004/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Construction |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Construction Overtime Services |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Estimating |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electric Estimating Overtime |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Engineering/Mapping |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Engineering/Mapping |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Electric |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Electric |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Electric |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Environmental Land |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Indirect Labor - Gas |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Maint & Operate Doubletime Services |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Maintain & Operate Services |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Mapping |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Mapping |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Mapping |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Paid Time Off |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Paid Time Off |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Paid Time Off |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Construction Supplies |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electl & Electronic Equipment Component |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Electrical Specialties |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Material Burden |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Borrowed |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Borrowed |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Equity |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Equity |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | AFUDC-Equity |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Benefits OH |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Benefits OH |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Benefits OH |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Building Service Overhead |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Building Service Overhead |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Building Service Overhead |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Capitalized A&G |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Capitalized A&G |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Capitalized A&G |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Cash Discount earned |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Fleet OH - Elec |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Fleet OH - Elec |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Fleet OH - Elec |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Fleet OH - Gas |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | IT Device OH |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | IT Device OH |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | IT Device OH |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Minor Material OH |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Operation Mgmt & Support - Gas |  | 003/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Payroll Taxes OH |  | 001/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Payroll Taxes OH |  | 002/2021
35116801 | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Payroll Taxes OH |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 004/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Environmental Contract |  | 004/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Consulting Services - Engineering |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Consulting Services - Engineering |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Consulting Services - Engineering |  | 004/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Indirect Labor - Electric |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Indirect Labor - Electric |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Indirect Labor - Electric |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Mapping |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Mapping |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Mapping |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Paid Time Off |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Paid Time Off |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Paid Time Off |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Benefits OH |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Benefits OH |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Benefits OH |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Building Service Overhead |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Building Service Overhead |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Building Service Overhead |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Capitalized A&G |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Capitalized A&G |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Capitalized A&G |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Cash Discount earned |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Fleet OH - Elec |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Fleet OH - Elec |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Fleet OH - Elec |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | IT Device OH |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | IT Device OH |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | IT Device OH |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Payroll Taxes OH |  | 001/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Payroll Taxes OH |  | 002/2021
35116802 | CWSP-MIWUK 1702-LR 6018-PHASE 1.4 |  | Payroll Taxes OH |  | 003/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Design Drafting Services - Overtime |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Electric Estimating Overtime |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Engineering/Mapping |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Indirect Labor - Electric |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Paid Time Off |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Paid Time Off |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Equity |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Equity |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | AFUDC-Equity |  | 003/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Benefits OH |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Benefits OH |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Building Service Overhead |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Building Service Overhead |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Capitalized A&G |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Capitalized A&G |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Fleet OH - Elec |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Fleet OH - Elec |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | IT Device OH |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | IT Device OH |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Payroll Taxes OH |  | 001/2021
35116803 | CWSP-MIWUK 1702-LR 6018-PHASE 1.5 |  | Payroll Taxes OH |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Contracts |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Contracts |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Contracts |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Contracts |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Contracts |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Indirect Labor - Electric |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Indirect Labor - Electric |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Mapping |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Mapping |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Paid Time Off |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Paid Time Off |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Benefits OH |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Benefits OH |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Building Service Overhead |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Building Service Overhead |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Capitalized A&G |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Capitalized A&G |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Fleet OH - Elec |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Fleet OH - Elec |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | IT Device OH |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | IT Device OH |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Payroll Taxes OH |  | 002/2021
35116804 | CWSP-MIWUK 1702-LR 6018-PHASE 1.6 |  | Payroll Taxes OH |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Environmental Contract |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Traffic Control Contracts |  | 002/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Analyst Services |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Engineering/Mapping |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Mapping |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Paid Time Off |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Paid Time Off |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Equity |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Equity |  | 002/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | AFUDC-Equity |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Benefits OH |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Benefits OH |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Building Service Overhead |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Building Service Overhead |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Capitalized A&G |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Capitalized A&G |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | IT Device OH |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | IT Device OH |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35116921 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | Traffic Control Contracts |  | 002/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Equity |  | 001/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Equity |  | 002/2021
35116922 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.3 |  | AFUDC-Equity |  | 003/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Contracts |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Mapping |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Paid Time Off |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Equity |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Equity |  | 002/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | AFUDC-Equity |  | 003/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Benefits OH |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Building Service Overhead |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Capitalized A&G |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | IT Device OH |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116923 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Electric Estimating Overtime |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Paid Time Off |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Equity |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Equity |  | 002/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | AFUDC-Equity |  | 003/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Benefits OH |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Building Service Overhead |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Capitalized A&G |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | IT Device OH |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116924 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Construction Inspection |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Mapping |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Paid Time Off |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Equity |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Equity |  | 002/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | AFUDC-Equity |  | 003/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Benefits OH |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Building Service Overhead |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Capitalized A&G |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | IT Device OH |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35116925 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | Traffic Control Contracts |  | 002/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Equity |  | 001/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Equity |  | 002/2021
35116926 | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.7 |  | AFUDC-Equity |  | 003/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35117007 | CWSP-ORO FINO 1102 OCB & LR2090 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Contracts |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Construction Contract |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Construction Contract |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Construction Contract |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Construction Contract |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Construction Contract |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Contract |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Consulting Services - Engineering |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Consulting Services - Engineering |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Consulting Services - Engineering |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Account Services |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Account Services |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Account Services |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Administration |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Administration |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction Overtime Services |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction Overtime Services |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction Overtime Services |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction Overtime Services |  | 004/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Estimating |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Estimating |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Electric Estimating |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Engineering/Mapping |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Engineering/Mapping |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Cust Care |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Cust Care |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Cust Care |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Electric |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Electric |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Electric |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Indirect Labor - Gas |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Mapping |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Mapping |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Mapping |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Paid Time Off |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Paid Time Off |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Paid Time Off |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Conductors, Cable & Wire Connectors |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Construction Supplies |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Material Burden |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Borrowed |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Borrowed |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Borrowed |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Equity |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Equity |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | AFUDC-Equity |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Benefits OH |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Benefits OH |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Benefits OH |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Building Service Overhead |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Building Service Overhead |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Building Service Overhead |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Capitalized A&G |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Capitalized A&G |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Capitalized A&G |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Fleet OH - Elec |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Fleet OH - Elec |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Fleet OH - Elec |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Fleet OH - Gas |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | IT Device OH |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | IT Device OH |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | IT Device OH |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Minor Material OH |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Operation Mgmt & Support - Gas |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Other Land Fees |  | 003/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Payroll Taxes OH |  | 001/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Payroll Taxes OH |  | 002/2021
35117443 | CWSP-BRUNSWICK 1103 LR50070 ZONE-PH 3.6 |  | Payroll Taxes OH |  | 003/2021
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 |  | Land Acquisition Services |  | 001/2021
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 |  | Land Acquisition Services |  | 002/2021
35117444 | CWSP - VOLTA 1102 LR 1648 PH 2.1 |  | Land Acquisition Services |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 004/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Environmental Contract |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Indirect Labor - Electric |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Indirect Labor - Electric |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Indirect Labor - Electric |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Mapping |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Mapping |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Mapping |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Paid Time Off |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Paid Time Off |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Paid Time Off |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Benefits OH |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Benefits OH |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Benefits OH |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Building Service Overhead |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Building Service Overhead |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Building Service Overhead |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Capitalized A&G |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Capitalized A&G |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Capitalized A&G |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Fleet OH - Elec |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Fleet OH - Elec |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Fleet OH - Elec |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | IT Device OH |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | IT Device OH |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | IT Device OH |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Payroll Taxes OH |  | 001/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Payroll Taxes OH |  | 002/2021
35119401 | CWSP - CAMP EVERS 2106 - 5020 - PHASE 2 |  | Payroll Taxes OH |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Contracts |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Environmental Contract |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Consulting Services - Environmental Perm |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Account Services |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Account Services |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Account Services |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Acquisition - Misc |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Administration |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Design Drafting Services |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Design Drafting Services - Overtime |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Electric Estimating |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Engineering/Mapping |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Engineering/Mapping |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Engineering/Mapping |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Environmental Planning & Permitting-Misc |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Cust Care |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Cust Care |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Cust Care |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Electric |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Electric |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Electric |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Environmental Land |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Environmental Land |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Indirect Labor - Environmental Land |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Mapping |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Paid Time Off |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Paid Time Off |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Paid Time Off |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Material Burden |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Material Burden |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Borrowed |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Borrowed |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Borrowed |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Equity |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Equity |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | AFUDC-Equity |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Benefits OH |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Benefits OH |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Benefits OH |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Building Service Overhead |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Building Service Overhead |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Building Service Overhead |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Capitalized A&G |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Capitalized A&G |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Capitalized A&G |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Fleet OH - Elec |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Fleet OH - Elec |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Fleet OH - Elec |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | IT Device OH |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | IT Device OH |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | IT Device OH |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Minor Material OH |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Minor Material OH |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Electric |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Electric |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Electric |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Other Land Fees |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Payroll Taxes OH |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Payroll Taxes OH |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Payroll Taxes OH |  | 003/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Permits/FeesLand Surveying Services |  | 001/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Permits/FeesLand Surveying Services |  | 002/2021
35119965 | CWSP - LOS GATOS 1106 - LB44 - PH 2.5E |  | Permits/FeesLand Surveying Services |  | 003/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Account Services |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Indirect Labor - Cust Care |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Paid Time Off |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Borrowed |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Borrowed |  | 002/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Borrowed |  | 003/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Equity |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Equity |  | 002/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | AFUDC-Equity |  | 003/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Benefits OH |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Building Service Overhead |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Capitalized A&G |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | IT Device OH |  | 001/2021
35119967 | CWSP - LOS GATOS 1106 - LB44 - PH 3.5 |  | Payroll Taxes OH |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Account Services |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Indirect Labor - Cust Care |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Paid Time Off |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Borrowed |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Borrowed |  | 002/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Borrowed |  | 003/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Equity |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Equity |  | 002/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | AFUDC-Equity |  | 003/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Benefits OH |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Building Service Overhead |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Capitalized A&G |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | IT Device OH |  | 001/2021
35119968 | CWSP - LOS GATOS 1106 - LB44 - PH 3.6 |  | Payroll Taxes OH |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 004/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Environmental Contract |  | 004/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Consulting Services - Engineering |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Consulting Services - Engineering |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Consulting Services - Engineering |  | 004/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Administrative Services - OT |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Engineering/Mapping |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Electric |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Electric |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Electric |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Environmental Land |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Land Rights - Misc |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Land Rights - Misc |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Land Rights - Misc |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Mapping |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Mapping |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Mapping |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Paid Time Off |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Paid Time Off |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Paid Time Off |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Material Burden |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Benefits OH |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Benefits OH |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Benefits OH |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Building Service Overhead |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Building Service Overhead |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Building Service Overhead |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Capitalized A&G |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Capitalized A&G |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Capitalized A&G |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Fleet OH - Elec |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Fleet OH - Elec |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Fleet OH - Elec |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | IT Device OH |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | IT Device OH |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | IT Device OH |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Minor Material OH |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Payroll Taxes OH |  | 001/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Payroll Taxes OH |  | 002/2021
35119969 | CWSP - LOS GATOS 1106 - LB44 - PH 4.2 |  | Payroll Taxes OH |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 004/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Environmental Contract |  | 004/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Consulting Services - Engineering |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Consulting Services - Engineering |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Consulting Services - Engineering |  | 004/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Indirect Labor - Electric |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Indirect Labor - Electric |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Indirect Labor - Electric |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Mapping |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Mapping |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Mapping |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Paid Time Off |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Paid Time Off |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Paid Time Off |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Benefits OH |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Benefits OH |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Benefits OH |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Building Service Overhead |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Building Service Overhead |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Building Service Overhead |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Capitalized A&G |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Capitalized A&G |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Capitalized A&G |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Fleet OH - Elec |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Fleet OH - Elec |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Fleet OH - Elec |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | IT Device OH |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | IT Device OH |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | IT Device OH |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Payroll Taxes OH |  | 001/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Payroll Taxes OH |  | 002/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Payroll Taxes OH |  | 003/2021
35119970 | CWSP - LOS GATOS 1106 - LB44 - PH 4.3 |  | Postage |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Account Services |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Indirect Labor - Cust Care |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Paid Time Off |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Borrowed |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Borrowed |  | 002/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Borrowed |  | 003/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Equity |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Equity |  | 002/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | AFUDC-Equity |  | 003/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Benefits OH |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Building Service Overhead |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Capitalized A&G |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | IT Device OH |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Payroll Taxes OH |  | 001/2021
35119972 | CWSP - LOS GATOS 1106 - LB44 - PHASE 4 |  | Permits/FeesLand Surveying Services |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Environmental Contract |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Environmental Contract |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Environmental Contract |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Environmental Contract |  | 004/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Consulting Services - Engineering |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Consulting Services - Engineering |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Consulting Services - Engineering |  | 004/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Indirect Labor - Electric |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Indirect Labor - Electric |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Indirect Labor - Electric |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Mapping |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Mapping |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Mapping |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Paid Time Off |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Paid Time Off |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Paid Time Off |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Benefits OH |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Benefits OH |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Benefits OH |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Building Service Overhead |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Building Service Overhead |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Building Service Overhead |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Capitalized A&G |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Capitalized A&G |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Capitalized A&G |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Cellular Phone Use |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Cellular Phone Use |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Cellular Phone Use |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Fleet OH - Elec |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Fleet OH - Elec |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Fleet OH - Elec |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | IT Device OH |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | IT Device OH |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | IT Device OH |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Payroll Taxes OH |  | 001/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Payroll Taxes OH |  | 002/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Payroll Taxes OH |  | 003/2021
35120949 | CWSP- BUCOCAMP - SKYWAY PARADISE TIE PH2 |  | Permits/Fees - Environmental |  | 001/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35129304 | CWSP - ORO FINO 1102 - LR2560 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Contracts |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Mapping |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Paid Time Off |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Benefits OH |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Building Service Overhead |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Capitalized A&G |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | IT Device OH |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129305 | CWSP - ORO FINO 1102 - LR2560 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Environmental Contract |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Electric Estimating Overtime |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Mapping |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Paid Time Off |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Paid Time Off |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Benefits OH |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Benefits OH |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Building Service Overhead |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Capitalized A&G |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Capitalized A&G |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | IT Device OH |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129306 | CWSP - ORO FINO 1102 - LR2560 PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Contracts |  | 004/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Administration |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Indirect Labor - Environmental Land |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Paid Time Off |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Benefits OH |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Building Service Overhead |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Capitalized A&G |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | IT Device OH |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35129307 | CWSP - ORO FINO 1102 - LR2560 PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Equity |  | 001/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Equity |  | 002/2021
35129308 | CWSP - ORO FINO 1102 - LR2560 PH 2.2 |  | AFUDC-Equity |  | 003/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Construction Inspection |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Mapping |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Paid Time Off |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Equity |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Equity |  | 002/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | AFUDC-Equity |  | 003/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Benefits OH |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Building Service Overhead |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Capitalized A&G |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | IT Device OH |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129309 | CWSP - ORO FINO 1102 - LR2560 PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Contracts |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Environmental Contract |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Electric Estimating Overtime |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Indirect Labor - Electric |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Mapping |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Mapping |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Paid Time Off |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Paid Time Off |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Equity |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Equity |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | AFUDC-Equity |  | 003/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Benefits OH |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Benefits OH |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Building Service Overhead |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Capitalized A&G |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Capitalized A&G |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Fleet OH - Elec |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | IT Device OH |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129310 | CWSP - ORO FINO 1102 - LR2560 PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Electric Estimating Overtime |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Paid Time Off |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Equity |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Equity |  | 002/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | AFUDC-Equity |  | 003/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Benefits OH |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Building Service Overhead |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Capitalized A&G |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | IT Device OH |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129311 | CWSP - ORO FINO 1102 - LR2560 PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Contracts |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Mapping |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Paid Time Off |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Benefits OH |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Building Service Overhead |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Capitalized A&G |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | IT Device OH |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129434 | CWSP - ORO FINO 1102 - LR76008 PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Contracts |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Contracts |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Environmental Contract |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Administration |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Construction |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Indirect Labor - Environmental Land |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Mapping |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Mapping |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Paid Time Off |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Paid Time Off |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Benefits OH |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Benefits OH |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Building Service Overhead |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Building Service Overhead |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Capitalized A&G |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Capitalized A&G |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | IT Device OH |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | IT Device OH |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35129435 | CWSP - ORO FINO 1102 - LR76008 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Contracts |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Contracts |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Environmental Contract |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Construction |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Mapping |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Mapping |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Paid Time Off |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Paid Time Off |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Benefits OH |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Benefits OH |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Building Service Overhead |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Building Service Overhead |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Capitalized A&G |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Capitalized A&G |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | IT Device OH |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | IT Device OH |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35129436 | CWSP - ORO FINO 1102 - LR76008 PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Electric Estimating Doubletime |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Electric Estimating Overtime |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Paid Time Off |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Benefits OH |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Building Service Overhead |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Capitalized A&G |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | IT Device OH |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129437 | CWSP - ORO FINO 1102 - LR76008 PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Contracts |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Environmental Contract |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Consulting Services - Environmental Perm |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Consulting Services - Environmental Perm |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Mapping |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Mapping |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Paid Time Off |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Paid Time Off |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Equity |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Equity |  | 002/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | AFUDC-Equity |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Benefits OH |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Benefits OH |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Building Service Overhead |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Building Service Overhead |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Capitalized A&G |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Capitalized A&G |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | IT Device OH |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35129438 | CWSP - ORO FINO 1102 - LR76008 PH 2.2 |  | Permits/FeesLand Surveying Services |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Environmental Contract |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Mapping |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Paid Time Off |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Equity |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Equity |  | 002/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | AFUDC-Equity |  | 003/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Benefits OH |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Building Service Overhead |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Capitalized A&G |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | IT Device OH |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129439 | CWSP - ORO FINO 1102 - LR76008 PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Construction Inspection |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Environmental Contract |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Mapping |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Paid Time Off |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Equity |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Equity |  | 002/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | AFUDC-Equity |  | 003/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Benefits OH |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Building Service Overhead |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Capitalized A&G |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | IT Device OH |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129600 | CWSP - ORO FINO 1102 - LR76008 PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Contracts |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Environmental Contract |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Mapping |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Mapping |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Paid Time Off |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Paid Time Off |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Equity |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Equity |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | AFUDC-Equity |  | 003/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Benefits OH |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Benefits OH |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Building Service Overhead |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Capitalized A&G |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Capitalized A&G |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | IT Device OH |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129601 | CWSP - ORO FINO 1102 - LR76008 PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Environmental Contract |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Mapping |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Paid Time Off |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Equity |  | 001/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Equity |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | AFUDC-Equity |  | 003/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Benefits OH |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Capitalized A&G |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35129602 | CWSP - ORO FINO 1101 - OCB PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Equity |  | 001/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Equity |  | 002/2021
35129603 | CWSP - ORO FINO 1101 - OCB PH 1.3 |  | AFUDC-Equity |  | 003/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Electric Estimating Overtime |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Paid Time Off |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Equity |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Equity |  | 002/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | AFUDC-Equity |  | 003/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Benefits OH |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Building Service Overhead |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Capitalized A&G |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | IT Device OH |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129604 | CWSP - ORO FINO 1101 - OCB PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Electric Estimating Overtime |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Paid Time Off |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Equity |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Equity |  | 002/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | AFUDC-Equity |  | 003/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Benefits OH |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Building Service Overhead |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Capitalized A&G |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | IT Device OH |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129605 | CWSP - ORO FINO 1101 - OCB PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Equity |  | 001/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Equity |  | 002/2021
35129606 | CWSP - ORO FINO 1101 - OCB PH 1.6 |  | AFUDC-Equity |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Electric Construction Contract |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Electric Construction Contract |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Electric Construction Contract |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Electric Estimating Overtime |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Field Services Overtime |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Field Services Overtime |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Mapping |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Mapping |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Mapping |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Paid Time Off |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Paid Time Off |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Paid Time Off |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Equity |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Equity |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | AFUDC-Equity |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Benefits OH |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Benefits OH |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Benefits OH |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Building Service Overhead |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Building Service Overhead |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Building Service Overhead |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Capitalized A&G |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Capitalized A&G |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Capitalized A&G |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | IT Device OH |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | IT Device OH |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | IT Device OH |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35129607 | CWSP - ORO FINO 1101 - OCB PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Equity |  | 001/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Equity |  | 002/2021
35129608 | CWSP - ORO FINO 1101 - OCB PH 2.2 |  | AFUDC-Equity |  | 003/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Contracts |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Contracts |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Environmental Contract |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Mapping |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Mapping |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Paid Time Off |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Paid Time Off |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Equity |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Equity |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | AFUDC-Equity |  | 003/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Benefits OH |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Benefits OH |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Building Service Overhead |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Capitalized A&G |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Capitalized A&G |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | IT Device OH |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129609 | CWSP - ORO FINO 1101 - OCB PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Equity |  | 001/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Equity |  | 002/2021
35129610 | CWSP - ORO FINO 1101 - OCB PH 2.4 |  | AFUDC-Equity |  | 003/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Contracts |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Environmental Contract |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Indirect Labor - Electric |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Indirect Labor - Environmental Land |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Mapping |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Mapping |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Paid Time Off |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Paid Time Off |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Equity |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Equity |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | AFUDC-Equity |  | 003/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Benefits OH |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Benefits OH |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Building Service Overhead |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Capitalized A&G |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Capitalized A&G |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Fleet OH - Elec |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | IT Device OH |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35129611 | CWSP - ORO FINO 1101 - OCB PH 2.5 |  | Payroll Taxes OH |  | 001/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Environmental Contract |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Indirect Labor - Electric |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Mapping |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Paid Time Off |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Borrowed |  | 001/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Borrowed |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Borrowed |  | 003/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Equity |  | 001/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Equity |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | AFUDC-Equity |  | 003/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Benefits OH |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Capitalized A&G |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Fleet OH - Elec |  | 002/2021
35129612 | CWSP - ORO FINO 1101 - OCB PH 2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Environmental Contract |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Indirect Labor - Electric |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Mapping |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Paid Time Off |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Borrowed |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Borrowed |  | 002/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Borrowed |  | 003/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Equity |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Equity |  | 002/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | AFUDC-Equity |  | 003/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Benefits OH |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Building Service Overhead |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Capitalized A&G |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Fleet OH - Elec |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | IT Device OH |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129613 | CWSP - ORO FINO 1101 - OCB PH 3.2 |  | Payroll Taxes OH |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Construction Inspection |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Construction Inspection |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Environmental Contract |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Electric Estimating Overtime |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Indirect Labor - Electric |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Indirect Labor - Electric |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Mapping |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Mapping |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Paid Time Off |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Paid Time Off |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Borrowed |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Borrowed |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Borrowed |  | 003/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Equity |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Equity |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | AFUDC-Equity |  | 003/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Benefits OH |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Benefits OH |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Building Service Overhead |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Building Service Overhead |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Capitalized A&G |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Capitalized A&G |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Fleet OH - Elec |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Fleet OH - Elec |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | IT Device OH |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | IT Device OH |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Payroll Taxes OH |  | 001/2021
35129614 | CWSP - ORO FINO 1101 - OCB PH 3.3 |  | Payroll Taxes OH |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Electric Construction Contract |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Electric Construction Contract |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Electric Construction Contract |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Environmental Contract |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Administration |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Indirect Labor - Electric |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Indirect Labor - Electric |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Indirect Labor - Electric |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Indirect Labor - Environmental Land |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Mapping |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Mapping |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Mapping |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Paid Time Off |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Paid Time Off |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Paid Time Off |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Borrowed |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Borrowed |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Borrowed |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Equity |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Equity |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | AFUDC-Equity |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Benefits OH |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Benefits OH |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Benefits OH |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Building Service Overhead |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Building Service Overhead |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Building Service Overhead |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Capitalized A&G |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Capitalized A&G |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Capitalized A&G |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Fleet OH - Elec |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Fleet OH - Elec |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Fleet OH - Elec |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | IT Device OH |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | IT Device OH |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | IT Device OH |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Payroll Taxes OH |  | 001/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Payroll Taxes OH |  | 002/2021
35129615 | CWSP - ORO FINO 1101 - OCB PH 3.4 |  | Payroll Taxes OH |  | 003/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Construction Inspection |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Mapping |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Paid Time Off |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Benefits OH |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Building Service Overhead |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Capitalized A&G |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | IT Device OH |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129616 | CWSP - ORO FINO 1101 - LR2022 PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Electric Estimating Doubletime |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Electric Estimating Overtime |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Paid Time Off |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Benefits OH |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Building Service Overhead |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Capitalized A&G |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | IT Device OH |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129617 | CWSP - ORO FINO 1101 - LR2022 PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35129618 | CWSP - ORO FINO 1101 - LR2022 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Construction Inspection |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Mapping |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Paid Time Off |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Benefits OH |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Building Service Overhead |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Capitalized A&G |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | IT Device OH |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129619 | CWSP - ORO FINO 1101 - LR2022 PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Equity |  | 001/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Equity |  | 002/2021
35129640 | CWSP - ORO FINO 1101 - LR2022 PH 1.6 |  | AFUDC-Equity |  | 003/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Construction Inspection |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Contracts |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Indirect Labor - Electric |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Mapping |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Mapping |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Paid Time Off |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Paid Time Off |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Equity |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Equity |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | AFUDC-Equity |  | 003/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Benefits OH |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Benefits OH |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Building Service Overhead |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Building Service Overhead |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Capitalized A&G |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Capitalized A&G |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Fleet OH - Elec |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | IT Device OH |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | IT Device OH |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35129641 | CWSP - ORO FINO 1101 - LR2022 PH 1.7 |  | Payroll Taxes OH |  | 002/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Environmental Contract |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Indirect Labor - Electric |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Mapping |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Paid Time Off |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Borrowed |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Borrowed |  | 002/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Borrowed |  | 003/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Equity |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Equity |  | 002/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | AFUDC-Equity |  | 003/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Benefits OH |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Building Service Overhead |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Capitalized A&G |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Fleet OH - Elec |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | IT Device OH |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129642 | CWSP - ORO FINO 1101 - LR2022 PH 1.8 |  | Payroll Taxes OH |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Construction Inspection |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Electric Estimating Overtime |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Indirect Labor - Electric |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Indirect Labor - Electric |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Mapping |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Paid Time Off |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Paid Time Off |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Equity |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Equity |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | AFUDC-Equity |  | 003/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Benefits OH |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Benefits OH |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Building Service Overhead |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Building Service Overhead |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Capitalized A&G |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Capitalized A&G |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Fleet OH - Elec |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Fleet OH - Elec |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | IT Device OH |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | IT Device OH |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Payroll Taxes OH |  | 001/2021
35129643 | CWSP - ORO FINO 1101 - LR2022 PH 2.2 |  | Payroll Taxes OH |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Environmental Contract |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Environmental Contract |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Indirect Labor - Electric |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Indirect Labor - Electric |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Mapping |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Mapping |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Paid Time Off |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Paid Time Off |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Equity |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Equity |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | AFUDC-Equity |  | 003/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Benefits OH |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Benefits OH |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Building Service Overhead |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Building Service Overhead |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Capitalized A&G |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Capitalized A&G |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Fleet OH - Elec |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Fleet OH - Elec |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | IT Device OH |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | IT Device OH |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Payroll Taxes OH |  | 001/2021
35129644 | CWSP - ORO FINO 1101 - LR2022 PH 2.3 |  | Payroll Taxes OH |  | 002/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Contracts |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Environmental Contract |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Indirect Labor - Electric |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Mapping |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Paid Time Off |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Equity |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Equity |  | 002/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | AFUDC-Equity |  | 003/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Benefits OH |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Building Service Overhead |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Capitalized A&G |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Fleet OH - Elec |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | IT Device OH |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129645 | CWSP - ORO FINO 1101 - LR2022 PH 2.4 |  | Payroll Taxes OH |  | 001/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Engineering/Mapping |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Engineering/Mapping |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Indirect Labor - Electric |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Indirect Labor - Electric |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Paid Time Off |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Paid Time Off |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Equity |  | 001/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Equity |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | AFUDC-Equity |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Benefits OH |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Benefits OH |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Building Service Overhead |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Building Service Overhead |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Capitalized A&G |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Capitalized A&G |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Fleet OH - Elec |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Fleet OH - Elec |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | IT Device OH |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | IT Device OH |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Payroll Taxes OH |  | 002/2021
35129646 | CWSP - ORO FINO 1101 - LR2022 PH 2.5 |  | Payroll Taxes OH |  | 003/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Borrowed |  | 001/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Borrowed |  | 002/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Borrowed |  | 003/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Equity |  | 001/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Equity |  | 002/2021
35129647 | CWSP - ORO FINO 1101 - LR2022 PH 2.6 |  | AFUDC-Equity |  | 003/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Construction Inspection |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Indirect Labor - Electric |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Mapping |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Paid Time Off |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Borrowed |  | 001/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Borrowed |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Borrowed |  | 003/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Equity |  | 001/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Equity |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | AFUDC-Equity |  | 003/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Benefits OH |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Building Service Overhead |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Capitalized A&G |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Fleet OH - Elec |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | IT Device OH |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35129648 | CWSP - ORO FINO 1101 - LR2022 PH 3.2 |  | Payroll Taxes OH |  | 002/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35129649 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Environmental Contract |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Mapping |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Paid Time Off |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Benefits OH |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Building Service Overhead |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Capitalized A&G |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | IT Device OH |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129650 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Contracts |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Environmental Contract |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Mapping |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Paid Time Off |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Benefits OH |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Building Service Overhead |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Capitalized A&G |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | IT Device OH |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129652 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35129653 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Environmental Contract |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Administration |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Electric Estimating Overtime |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Indirect Labor - Environmental Land |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Mapping |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Paid Time Off |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Equity |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Equity |  | 002/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | AFUDC-Equity |  | 003/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Benefits OH |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Building Service Overhead |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Capitalized A&G |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | IT Device OH |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35129654 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Environmental Contract |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Administration |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Indirect Labor - Electric |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Indirect Labor - Environmental Land |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Mapping |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Paid Time Off |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Equity |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Equity |  | 002/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | AFUDC-Equity |  | 003/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Benefits OH |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Building Service Overhead |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Capitalized A&G |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Fleet OH - Elec |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | IT Device OH |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35129655 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.7 |  | Payroll Taxes OH |  | 001/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Borrowed |  | 001/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Borrowed |  | 002/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Borrowed |  | 003/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Equity |  | 001/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Equity |  | 002/2021
35129656 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.8 |  | AFUDC-Equity |  | 003/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Electric Estimating Overtime |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Indirect Labor - Electric |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Paid Time Off |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Borrowed |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Borrowed |  | 002/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Borrowed |  | 003/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Equity |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Equity |  | 002/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | AFUDC-Equity |  | 003/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Benefits OH |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Building Service Overhead |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Capitalized A&G |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Fleet OH - Elec |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | IT Device OH |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Operation Mgmt & Support - Electric |  | 001/2021
35129657 | CWSP - ORO FINO 1102 - OCB&LR2090 PH 1.9 |  | Payroll Taxes OH |  | 001/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Borrowed |  | 001/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Borrowed |  | 002/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Borrowed |  | 003/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Equity |  | 001/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Equity |  | 002/2021
35129767 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH1 |  | AFUDC-Equity |  | 003/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Borrowed |  | 001/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Borrowed |  | 002/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Borrowed |  | 003/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Equity |  | 001/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Equity |  | 002/2021
35129944 | SILVERADO 2105 - DIST.UNDERBUILD RECON |  | AFUDC-Equity |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Engineering/Mapping |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Engineering/Mapping |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Indirect Labor - Electric |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Indirect Labor - Electric |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Paid Time Off |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Paid Time Off |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Benefits OH |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Benefits OH |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Building Service Overhead |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Building Service Overhead |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Capitalized A&G |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Capitalized A&G |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Fleet OH - Elec |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Fleet OH - Elec |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | IT Device OH |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | IT Device OH |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Operation Mgmt & Support - Electric |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Operation Mgmt & Support - Electric |  | 003/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Payroll Taxes OH |  | 002/2021
35135864 | CWSP – GRAYS FLAT 401 FUSE 3079 ZONE |  | Payroll Taxes OH |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Environmental Contract |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Consulting Services - Engineering |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Account Services |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Administration |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Administration |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Electric Estimating |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Electric Estimating |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Electric Estimating Overtime |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Electric Estimating Overtime |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Engineering/Mapping |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Engineering/Mapping |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Environmental Services |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Cust Care |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Electric |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Electric |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Electric |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Environmental Land |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Indirect Labor - Environmental Land |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Mapping |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Paid Time Off |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Paid Time Off |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Paid Time Off |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Project Management Services |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Project Management Services |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Project Management Services |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Benefits OH |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Benefits OH |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Benefits OH |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Building Service Overhead |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Building Service Overhead |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Building Service Overhead |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Capitalized A&G |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Capitalized A&G |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Capitalized A&G |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Fleet OH - Elec |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Fleet OH - Elec |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Fleet OH - Elec |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | IT Device OH |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | IT Device OH |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | IT Device OH |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Operation Mgmt & Support - Electric |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Operation Mgmt & Support - Electric |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Operation Mgmt & Support - Electric |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Payroll Taxes OH |  | 001/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Payroll Taxes OH |  | 002/2021
35137590 | CWSP-ECOP-MIDDLETOWN 1101-OCB-H02 |  | Payroll Taxes OH |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Consulting Services - Engineering |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Account Services |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating |  | 004/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating Doubletime |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating Overtime |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating Overtime |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Electric Estimating Overtime |  | 004/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Engineering/Mapping |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Engineering/Mapping |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Indirect Labor - Cust Care |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Indirect Labor - Electric |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Indirect Labor - Electric |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Indirect Labor - Electric |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Indirect Labor - Environmental Land |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Land Rights - Misc |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Mapping |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Paid Time Off |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Paid Time Off |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Paid Time Off |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Project Management Services |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Project Management Services |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Project Management Services |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Benefits OH |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Benefits OH |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Benefits OH |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Building Service Overhead |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Building Service Overhead |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Building Service Overhead |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Capitalized A&G |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Capitalized A&G |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Capitalized A&G |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Fleet OH - Elec |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Fleet OH - Elec |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Fleet OH - Elec |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | IT Device OH |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | IT Device OH |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | IT Device OH |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Operation Mgmt & Support - Electric |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Operation Mgmt & Support - Electric |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Operation Mgmt & Support - Electric |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Payroll Taxes OH |  | 001/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Payroll Taxes OH |  | 002/2021
35137593 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H07 |  | Payroll Taxes OH |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Consulting Services - Engineering |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Account Services |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Administration |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Administrative Services - OT |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Electric Estimating |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Electric Estimating |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Electric Estimating Overtime |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Electric Estimating Overtime |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Engineering/Mapping |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Engineering/Mapping |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Indirect Labor - Cust Care |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Indirect Labor - Electric |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Indirect Labor - Electric |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Indirect Labor - Electric |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Indirect Labor - Environmental Land |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Mapping |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Paid Time Off |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Paid Time Off |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Paid Time Off |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Project Management Services |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Project Management Services |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Project Management Services |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Benefits OH |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Benefits OH |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Benefits OH |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Building Service Overhead |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Building Service Overhead |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Building Service Overhead |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Capitalized A&G |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Capitalized A&G |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Capitalized A&G |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Fleet OH - Elec |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Fleet OH - Elec |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Fleet OH - Elec |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | IT Device OH |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | IT Device OH |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | IT Device OH |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Operation Mgmt & Support - Electric |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Operation Mgmt & Support - Electric |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Operation Mgmt & Support - Electric |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Payroll Taxes OH |  | 001/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Payroll Taxes OH |  | 002/2021
35137596 | CWSP-ECOP-MIDDLETOWN 1101-LR 4646-H08 |  | Payroll Taxes OH |  | 003/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Engineering/Mapping |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Indirect Labor - Electric |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Indirect Labor - Electric |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Paid Time Off |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Paid Time Off |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Project Management Services |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Project Management Services |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Benefits OH |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Benefits OH |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Building Service Overhead |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Building Service Overhead |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Capitalized A&G |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Capitalized A&G |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Fleet OH - Elec |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Fleet OH - Elec |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | IT Device OH |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | IT Device OH |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Operation Mgmt & Support - Electric |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Operation Mgmt & Support - Electric |  | 002/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Payroll Taxes OH |  | 001/2021
35137599 | CWSP-ECOP-MIDDLETOWN 1101-LR 614-H11 |  | Payroll Taxes OH |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Inspection |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Contracts |  | 004/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Contracts |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Electric Construction Contract |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Electric Construction Contract |  | 004/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Traffic Control Contracts |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Traffic Control Contracts |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Traffic Control Contracts |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Traffic Control Contracts |  | 004/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Consulting Services - Engineering |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Administration |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Analyst Services |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction |  | 004/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Doubletime Services |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Doubletime Services |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Overtime Services |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Overtime Services |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Construction Overtime Services |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Design Services Double Time |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Electric Estimating |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Electric Estimating |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Engineering/Mapping |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Engineering/Mapping |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Engineering/Mapping |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Indirect Labor - Electric |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Indirect Labor - Electric |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Indirect Labor - Electric |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Indirect Labor - Environmental Land |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Indirect Labor - Environmental Land |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Mapping |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Mapping |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Mapping |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Paid Time Off |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Paid Time Off |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Paid Time Off |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Material Burden |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Material Burden |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Borrowed |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Borrowed |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Borrowed |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Equity |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Equity |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | AFUDC-Equity |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Benefits OH |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Benefits OH |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Benefits OH |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Building Service Overhead |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Building Service Overhead |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Building Service Overhead |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Capitalized A&G |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Capitalized A&G |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Capitalized A&G |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Cash Discount earned |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Cash Discount earned |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Cash Discount earned |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Cash Discount earned |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Fleet OH - Elec |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Fleet OH - Elec |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Fleet OH - Elec |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | IT Device OH |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | IT Device OH |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | IT Device OH |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Minor Material OH |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Minor Material OH |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Other Land Fees |  | 003/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Payroll Taxes OH |  | 001/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Payroll Taxes OH |  | 002/2021
35142826 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH2 |  | Payroll Taxes OH |  | 003/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Acquisition - Misc |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Indirect Labor - Environmental Land |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Paid Time Off |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Borrowed |  | 001/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Borrowed |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Borrowed |  | 003/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Equity |  | 001/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Equity |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | AFUDC-Equity |  | 003/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Benefits OH |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Building Service Overhead |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Capitalized A&G |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | IT Device OH |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Land Acquisition Services |  | 003/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Land Acquisition Services |  | 004/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Other Land Fees |  | 003/2021
35142827 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH3 |  | Payroll Taxes OH |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Contracts |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Engineering/Mapping |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Engineering/Mapping |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Indirect Labor - Electric |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Indirect Labor - Electric |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Indirect Labor - Electric |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Mapping |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Paid Time Off |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Paid Time Off |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Paid Time Off |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Borrowed |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Borrowed |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Borrowed |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Equity |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Equity |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | AFUDC-Equity |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Benefits OH |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Benefits OH |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Benefits OH |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Building Service Overhead |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Building Service Overhead |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Building Service Overhead |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Capitalized A&G |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Capitalized A&G |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Capitalized A&G |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Fleet OH - Elec |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Fleet OH - Elec |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Fleet OH - Elec |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | IT Device OH |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | IT Device OH |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | IT Device OH |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Payroll Taxes OH |  | 001/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Payroll Taxes OH |  | 002/2021
35142828 | CWSP-BRUNSWICK-1103-LR2200 HARDENING PH4 |  | Payroll Taxes OH |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Environmental Contract |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Environmental Contract |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Environmental Contract |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Traffic Control Contracts |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Account Services |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Construction |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Electric Estimating |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Engineering/Mapping |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Engineering/Mapping |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Engineering/Mapping |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Field Services |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Cust Care |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Electric |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Electric |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Electric |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Environmental Land |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Environmental Land |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Indirect Labor - Gas |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Mapping |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Mapping |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Mapping |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Paid Time Off |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Paid Time Off |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Paid Time Off |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Borrowed |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Borrowed |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Borrowed |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Equity |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Equity |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | AFUDC-Equity |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Benefits OH |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Benefits OH |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Benefits OH |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Building Service Overhead |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Building Service Overhead |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Building Service Overhead |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Capitalized A&G |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Capitalized A&G |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Capitalized A&G |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Fleet OH - Elec |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Fleet OH - Elec |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Fleet OH - Elec |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Fleet OH - Gas |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | IT Device OH |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | IT Device OH |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | IT Device OH |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Operation Mgmt & Support - Gas |  | 003/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Payroll Taxes OH |  | 001/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Payroll Taxes OH |  | 002/2021
35144941 | PSPS - PAUL SWEET 2105 - CB PH 1 |  | Payroll Taxes OH |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Construction Inspection |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Environmental Contract |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Environmental Contract |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Design Overtime Services |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Engineering/Mapping |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Engineering/Mapping |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Engineering/Mapping |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Environmental Planning & Permitting-Misc |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Indirect Labor - Electric |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Indirect Labor - Electric |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Indirect Labor - Electric |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Indirect Labor - Environmental Land |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Mapping |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Mapping |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Mapping |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Paid Time Off |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Paid Time Off |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Paid Time Off |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Borrowed |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Borrowed |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Borrowed |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Equity |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Equity |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | AFUDC-Equity |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Benefits OH |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Benefits OH |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Benefits OH |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Building Service Overhead |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Building Service Overhead |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Building Service Overhead |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Capitalized A&G |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Capitalized A&G |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Capitalized A&G |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Fleet OH - Elec |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Fleet OH - Elec |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Fleet OH - Elec |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | IT Device OH |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | IT Device OH |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | IT Device OH |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Payroll Taxes OH |  | 001/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Payroll Taxes OH |  | 002/2021
35144943 | PSPS - ROB ROY 2105 - CB |  | Payroll Taxes OH |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Account Services |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Account Services |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Account Services |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Construction |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Construction Overtime Services |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Engineering/Mapping |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Engineering/Mapping |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Engineering/Mapping |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Cust Care |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Cust Care |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Cust Care |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Electric |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Electric |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Electric |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Indirect Labor - Environmental Land |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Mapping |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Paid Time Off |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Paid Time Off |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Paid Time Off |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Benefits OH |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Benefits OH |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Benefits OH |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Building Service Overhead |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Building Service Overhead |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Building Service Overhead |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Capitalized A&G |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Capitalized A&G |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Capitalized A&G |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Fleet OH - Elec |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Fleet OH - Elec |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Fleet OH - Elec |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | IT Device OH |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | IT Device OH |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | IT Device OH |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Operation Mgmt & Support - Electric |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Operation Mgmt & Support - Electric |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Operation Mgmt & Support - Electric |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Payroll Taxes OH |  | 001/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Payroll Taxes OH |  | 002/2021
35144944 | PSPS – SNEATH LANE 1107 – LR 48338 |  | Payroll Taxes OH |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Environmental Contract |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Environmental Contract |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Environmental Contract |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Account Services |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Analyst Services |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Analyst Services |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Construction |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Construction Overtime Services |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Engineering/Mapping |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Engineering/Mapping Services Overtime |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Environmental Planning & Permitting-Misc |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Cust Care |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Electric |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Electric |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Electric |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Environmental Land |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Environmental Land |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Indirect Labor - Environmental Land |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Manage L&EM |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Management Services |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Mapping |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Mapping |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Mapping |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Paid Time Off |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Paid Time Off |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Paid Time Off |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Borrowed |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Borrowed |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Borrowed |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Equity |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Equity |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | AFUDC-Equity |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Benefits OH |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Benefits OH |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Benefits OH |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Building Service Overhead |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Building Service Overhead |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Building Service Overhead |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Capitalized A&G |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Capitalized A&G |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Capitalized A&G |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Cash Discount earned |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Fleet OH - Elec |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Fleet OH - Elec |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Fleet OH - Elec |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | IT Device OH |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | IT Device OH |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | IT Device OH |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Acquisition Services |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Acquisition Services |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Acquisition Services |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Land Acquisition Services |  | 004/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Other Land Fees |  | 003/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Payroll Taxes OH |  | 001/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Payroll Taxes OH |  | 002/2021
35145001 | PSPS - CLAYTON 2215 - CB |  | Payroll Taxes OH |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Consulting Services - Other |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Consulting Services - Other |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Electric Estimating Overtime |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Engineering/Mapping |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Engineering/Mapping |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Indirect Labor - Electric |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Indirect Labor - Electric |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Indirect Labor - Electric |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Paid Time Off |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Paid Time Off |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Paid Time Off |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Borrowed |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Borrowed |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Borrowed |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Equity |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Equity |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | AFUDC-Equity |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Benefits OH |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Benefits OH |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Benefits OH |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Building Service Overhead |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Building Service Overhead |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Building Service Overhead |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Capitalized A&G |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Capitalized A&G |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Capitalized A&G |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Fleet OH - Elec |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Fleet OH - Elec |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Fleet OH - Elec |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | IT Device OH |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | IT Device OH |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | IT Device OH |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Payroll Taxes OH |  | 001/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Payroll Taxes OH |  | 002/2021
35145002 | PSPS - IGNACIO 1101 - CB |  | Payroll Taxes OH |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Construction |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Construction Overtime Services |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Engineering/Mapping |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Engineering/Mapping |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Engineering/Mapping |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Indirect Labor - Electric |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Indirect Labor - Electric |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Indirect Labor - Electric |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Mapping |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Paid Time Off |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Paid Time Off |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Paid Time Off |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Borrowed |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Borrowed |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Borrowed |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Equity |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Equity |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | AFUDC-Equity |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Benefits OH |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Benefits OH |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Benefits OH |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Building Service Overhead |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Building Service Overhead |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Building Service Overhead |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Capitalized A&G |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Capitalized A&G |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Capitalized A&G |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Fleet OH - Elec |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Fleet OH - Elec |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Fleet OH - Elec |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | IT Device OH |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | IT Device OH |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | IT Device OH |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Payroll Taxes OH |  | 001/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Payroll Taxes OH |  | 002/2021
35145003 | PSPS CWSP - MORAGA 1103 - CB |  | Payroll Taxes OH |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Construction |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Construction |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Construction Overtime Services |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Engineering/Mapping |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Engineering/Mapping |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Engineering/Mapping |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Indirect Labor - Electric |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Indirect Labor - Electric |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Indirect Labor - Electric |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Indirect Labor - Environmental Land |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Mapping |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Mapping |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Paid Time Off |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Paid Time Off |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Paid Time Off |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Borrowed |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Borrowed |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Borrowed |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Equity |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Equity |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | AFUDC-Equity |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Benefits OH |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Benefits OH |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Benefits OH |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Building Service Overhead |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Building Service Overhead |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Building Service Overhead |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Capitalized A&G |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Capitalized A&G |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Capitalized A&G |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Fleet OH - Elec |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Fleet OH - Elec |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Fleet OH - Elec |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | IT Device OH |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | IT Device OH |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | IT Device OH |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Payroll Taxes OH |  | 001/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Payroll Taxes OH |  | 002/2021
35145004 | PSPS CWSP - ROSSMOOR 1106 - CB |  | Payroll Taxes OH |  | 003/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Borrowed |  | 001/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Borrowed |  | 002/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Borrowed |  | 003/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Equity |  | 001/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Equity |  | 002/2021
35145005 | *CANCELLED*CWSP - STAFFORD 1101 - CB PH1 |  | AFUDC-Equity |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Environmental Contract |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Account Services |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Engineering/Mapping |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Engineering/Mapping |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Indirect Labor - Cust Care |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Indirect Labor - Electric |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Indirect Labor - Electric |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Mapping |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Paid Time Off |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Paid Time Off |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Paid Time Off |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Borrowed |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Borrowed |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Borrowed |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Equity |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Equity |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | AFUDC-Equity |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Benefits OH |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Benefits OH |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Benefits OH |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Building Service Overhead |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Building Service Overhead |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Building Service Overhead |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Capitalized A&G |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Capitalized A&G |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Capitalized A&G |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Fleet OH - Elec |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Fleet OH - Elec |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | IT Device OH |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | IT Device OH |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | IT Device OH |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Operation Mgmt & Support - Electric |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Operation Mgmt & Support - Electric |  | 003/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Payroll Taxes OH |  | 001/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Payroll Taxes OH |  | 002/2021
35145006 | PSPS - STAFFORD 1101 LR 1298 |  | Payroll Taxes OH |  | 003/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Acquisition - Misc |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Administration |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Administration |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Electric Estimating Overtime |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Indirect Labor - Electric |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Indirect Labor - Environmental Land |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Indirect Labor - Environmental Land |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Paid Time Off |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Paid Time Off |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Borrowed |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Borrowed |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Borrowed |  | 003/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Equity |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Equity |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | AFUDC-Equity |  | 003/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Benefits OH |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Benefits OH |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Building Service Overhead |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Building Service Overhead |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Capitalized A&G |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Capitalized A&G |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Fleet OH - Elec |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | IT Device OH |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | IT Device OH |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Operation Mgmt & Support - Electric |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Payroll Taxes OH |  | 001/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Payroll Taxes OH |  | 002/2021
35145522 | PSPS - CLARKSVILLE 2104 - CB UG |  | Reimbursed Mileage Expense |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Construction Management Contracts |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Construction Management Contracts |  | 004/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Contract |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Contract |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Contract |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Contract |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Contract |  | 004/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Account Services |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Account Services |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Account Services |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Administration |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Administration |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Analyst Services |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Analyst Services |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Analyst Services |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Construction |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Electric Estimating Overtime |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Engineering/Mapping |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Engineering/Mapping |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Engineering/Mapping Services Overtime |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Planning & Permitting-Misc |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Environmental Planning & Permitting-Misc |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Indirect Labor - Gas |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Management Services |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Mapping |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Mapping |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Mapping |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Paid Time Off |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Paid Time Off |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Paid Time Off |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Project Management Overtime |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Project Management Services |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Project Management Services |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Project Management Services |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Conductors, Cable & Wire Connectors |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Construction Supplies |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Electl & Electronic Equipment Component |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Electrical Specialties |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Fabricated Structures |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Material Burden |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Equity |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Equity |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | AFUDC-Equity |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Benefits OH |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Benefits OH |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Benefits OH |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Building Service Overhead |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Building Service Overhead |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Building Service Overhead |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Capitalized A&G |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Capitalized A&G |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Capitalized A&G |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Encroachment Permit Fees |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Encroachment Permit Fees |  | 004/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Fleet OH - Elec |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Fleet OH - Elec |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Fleet OH - Elec |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Fleet OH - Gas |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | IT Device OH |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | IT Device OH |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | IT Device OH |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Minor Material OH |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Operation Mgmt & Support - Gas |  | 003/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Payroll Taxes OH |  | 001/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Payroll Taxes OH |  | 002/2021
35145524 | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Payroll Taxes OH |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Construction Management Contracts |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Construction Management Contracts |  | 004/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 004/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Contract |  | 004/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Traffic Control Contracts |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Account Services |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Account Services |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Account Services |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Acquisition - Misc |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Administration |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Analyst Services |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Analyst Services |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Analyst Services |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Electric Estimating |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Electric Estimating |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Electric Estimating Overtime |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Engineering/Mapping |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Engineering/Mapping |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Engineering/Mapping Services Overtime |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Planning & Permitting-Misc |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Environmental Planning & Permitting-Misc |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Cust Care |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Electric |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Indirect Labor - Environmental Land |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Mapping |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Mapping |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Mapping |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Paid Time Off |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Paid Time Off |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Paid Time Off |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Project Management Overtime |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Project Management Services |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Project Management Services |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Project Management Services |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Borrowed |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Equity |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Equity |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | AFUDC-Equity |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Benefits OH |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Benefits OH |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Benefits OH |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Building Service Overhead |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Building Service Overhead |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Building Service Overhead |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Capitalized A&G |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Capitalized A&G |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Capitalized A&G |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Fleet OH - Elec |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Fleet OH - Elec |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Fleet OH - Elec |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | IT Device OH |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | IT Device OH |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | IT Device OH |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Electric |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Payroll Taxes OH |  | 001/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Payroll Taxes OH |  | 002/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Payroll Taxes OH |  | 003/2021
35145525 | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Permits/FeesLand Surveying Services |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Contracts |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Environmental Contract |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Environmental Contract |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Environmental Contract |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Environmental Contract |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Traffic Control Contracts |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Consulting Services - Engineering |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Consulting Services - Environmental Perm |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Consulting Services - Environmental Perm |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Consulting Services - Environmental Perm |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Acquisition - Misc |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Administration |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Administration |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Administrative Services - OT |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Construction |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Construction |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Engineering/Mapping |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Engineering/Mapping |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Environmental Planning & Permitting-Misc |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Electric |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Electric |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Electric |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Environmental Land |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Environmental Land |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Indirect Labor - Gas |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Mapping |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Mapping |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Mapping |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Paid Time Off |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Paid Time Off |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Paid Time Off |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Technical Services |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Technical Services |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Borrowed |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Borrowed |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Borrowed |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Equity |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Equity |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | AFUDC-Equity |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Benefits OH |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Benefits OH |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Benefits OH |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Building Service Overhead |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Building Service Overhead |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Building Service Overhead |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Capitalized A&G |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Capitalized A&G |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Capitalized A&G |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Cash Discount earned |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Fleet OH - Elec |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Fleet OH - Elec |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Fleet OH - Elec |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Fleet OH - Gas |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | IT Device OH |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | IT Device OH |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | IT Device OH |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Operation Mgmt & Support - Gas |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Payroll Taxes OH |  | 001/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Payroll Taxes OH |  | 002/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Payroll Taxes OH |  | 003/2021
35145540 | PSPS - FROGTOWN 1702 - CB |  | Permits/FeesLand Surveying Services |  | 001/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Borrowed |  | 001/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Borrowed |  | 002/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Borrowed |  | 003/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Equity |  | 001/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Equity |  | 002/2021
35155680 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.02 |  | AFUDC-Equity |  | 003/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Borrowed |  | 001/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Borrowed |  | 002/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Borrowed |  | 003/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Equity |  | 001/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Equity |  | 002/2021
35155681 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.03 |  | AFUDC-Equity |  | 003/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Borrowed |  | 001/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Borrowed |  | 002/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Borrowed |  | 003/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Equity |  | 001/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Equity |  | 002/2021
35155682 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.04 |  | AFUDC-Equity |  | 003/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Borrowed |  | 001/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Borrowed |  | 002/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Borrowed |  | 003/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Equity |  | 001/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Equity |  | 002/2021
35155683 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.05 |  | AFUDC-Equity |  | 003/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Borrowed |  | 001/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Borrowed |  | 002/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Borrowed |  | 003/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Equity |  | 001/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Equity |  | 002/2021
35155684 | CWSP-BRUNSWICK 1105 LR2140 - PH 1.06 |  | AFUDC-Equity |  | 003/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Borrowed |  | 001/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Borrowed |  | 002/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Borrowed |  | 003/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Equity |  | 001/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Equity |  | 002/2021
35155685 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.07 |  | AFUDC-Equity |  | 003/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Borrowed |  | 001/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Borrowed |  | 002/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Borrowed |  | 003/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Equity |  | 001/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Equity |  | 002/2021
35155686 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.08 |  | AFUDC-Equity |  | 003/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Borrowed |  | 001/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Borrowed |  | 002/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Borrowed |  | 003/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Equity |  | 001/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Equity |  | 002/2021
35155687 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.09 |  | AFUDC-Equity |  | 003/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Borrowed |  | 001/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Borrowed |  | 002/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Borrowed |  | 003/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Equity |  | 001/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Equity |  | 002/2021
35155688 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.10 |  | AFUDC-Equity |  | 003/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Borrowed |  | 001/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Borrowed |  | 002/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Borrowed |  | 003/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Equity |  | 001/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Equity |  | 002/2021
35155689 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.11 |  | AFUDC-Equity |  | 003/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Borrowed |  | 001/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Borrowed |  | 002/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Borrowed |  | 003/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Equity |  | 001/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Equity |  | 002/2021
35155690 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.12 |  | AFUDC-Equity |  | 003/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Borrowed |  | 001/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Borrowed |  | 002/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Borrowed |  | 003/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Equity |  | 001/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Equity |  | 002/2021
35155691 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.13 |  | AFUDC-Equity |  | 003/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Borrowed |  | 001/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Borrowed |  | 002/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Borrowed |  | 003/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Equity |  | 001/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Equity |  | 002/2021
35155692 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.14 |  | AFUDC-Equity |  | 003/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Borrowed |  | 001/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Borrowed |  | 002/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Borrowed |  | 003/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Equity |  | 001/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Equity |  | 002/2021
35155693 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.15 |  | AFUDC-Equity |  | 003/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Borrowed |  | 001/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Borrowed |  | 002/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Borrowed |  | 003/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Equity |  | 001/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Equity |  | 002/2021
35155694 | CWSP - BRUNSWICK 1105 LR2140 - PH 1.16 |  | AFUDC-Equity |  | 003/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Borrowed |  | 001/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Borrowed |  | 002/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Borrowed |  | 003/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Equity |  | 001/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Equity |  | 002/2021
35155695 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.02 |  | AFUDC-Equity |  | 003/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Borrowed |  | 001/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Borrowed |  | 002/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Borrowed |  | 003/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Equity |  | 001/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Equity |  | 002/2021
35155696 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.03 |  | AFUDC-Equity |  | 003/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Borrowed |  | 001/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Borrowed |  | 002/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Borrowed |  | 003/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Equity |  | 001/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Equity |  | 002/2021
35155697 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.04 |  | AFUDC-Equity |  | 003/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Borrowed |  | 001/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Borrowed |  | 002/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Borrowed |  | 003/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Equity |  | 001/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Equity |  | 002/2021
35155698 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.05 |  | AFUDC-Equity |  | 003/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Borrowed |  | 001/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Borrowed |  | 002/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Borrowed |  | 003/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Equity |  | 001/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Equity |  | 002/2021
35155699 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.06 |  | AFUDC-Equity |  | 003/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Borrowed |  | 001/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Borrowed |  | 002/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Borrowed |  | 003/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Equity |  | 001/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Equity |  | 002/2021
35155741 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.08 |  | AFUDC-Equity |  | 003/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Borrowed |  | 001/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Borrowed |  | 002/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Borrowed |  | 003/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Equity |  | 001/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Equity |  | 002/2021
35155742 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.09 |  | AFUDC-Equity |  | 003/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Borrowed |  | 001/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Borrowed |  | 002/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Borrowed |  | 003/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Equity |  | 001/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Equity |  | 002/2021
35155746 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.12 |  | AFUDC-Equity |  | 003/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Borrowed |  | 001/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Borrowed |  | 002/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Borrowed |  | 003/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Equity |  | 001/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Equity |  | 002/2021
35155750 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.16 |  | AFUDC-Equity |  | 003/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Borrowed |  | 001/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Borrowed |  | 002/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Borrowed |  | 003/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Equity |  | 001/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Equity |  | 002/2021
35155751 | CWSP - BRUNSWICK 1105 LR2140 - PH 2.17 |  | AFUDC-Equity |  | 003/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Borrowed |  | 001/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Borrowed |  | 002/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Borrowed |  | 003/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Equity |  | 001/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Equity |  | 002/2021
35155752 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.02 |  | AFUDC-Equity |  | 003/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Borrowed |  | 001/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Borrowed |  | 002/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Borrowed |  | 003/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Equity |  | 001/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Equity |  | 002/2021
35155753 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.03 |  | AFUDC-Equity |  | 003/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Borrowed |  | 001/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Borrowed |  | 002/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Borrowed |  | 003/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Equity |  | 001/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Equity |  | 002/2021
35155754 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.04 |  | AFUDC-Equity |  | 003/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Borrowed |  | 001/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Borrowed |  | 002/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Borrowed |  | 003/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Equity |  | 001/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Equity |  | 002/2021
35155755 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.05 |  | AFUDC-Equity |  | 003/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Borrowed |  | 001/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Borrowed |  | 002/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Borrowed |  | 003/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Equity |  | 001/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Equity |  | 002/2021
35155756 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.06 |  | AFUDC-Equity |  | 003/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Borrowed |  | 001/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Borrowed |  | 002/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Borrowed |  | 003/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Equity |  | 001/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Equity |  | 002/2021
35155758 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.08 |  | AFUDC-Equity |  | 003/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Borrowed |  | 001/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Borrowed |  | 002/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Borrowed |  | 003/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Equity |  | 001/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Equity |  | 002/2021
35155841 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.11 |  | AFUDC-Equity |  | 003/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Borrowed |  | 001/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Borrowed |  | 002/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Borrowed |  | 003/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Equity |  | 001/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Equity |  | 002/2021
35155842 | CWSP - BRUNSWICK 1105 LR2140 - PH 3.12 |  | AFUDC-Equity |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Electric Construction Contract |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Electric Construction Contract |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Electric Construction Contract |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Traffic Control Contracts |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Construction |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Indirect Labor - Electric |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Indirect Labor - Electric |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Indirect Labor - Electric |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Mapping |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Mapping |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Mapping |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Paid Time Off |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Paid Time Off |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Paid Time Off |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Project Management Services |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Project Management Services |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Electl & Electronic Equipment Component |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Electrical Specialties |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Material Burden |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Material Burden |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Benefits OH |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Benefits OH |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Benefits OH |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Building Service Overhead |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Building Service Overhead |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Building Service Overhead |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Capitalized A&G |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Capitalized A&G |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Capitalized A&G |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Cash Discount earned |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Fleet OH - Elec |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Fleet OH - Elec |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Fleet OH - Elec |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | IT Device OH |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | IT Device OH |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | IT Device OH |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Minor Material OH |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Minor Material OH |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Payroll Taxes OH |  | 001/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Payroll Taxes OH |  | 002/2021
35157845 | SILVERADO 2105 WIRE DOWN - PH 3 |  | Payroll Taxes OH |  | 003/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Construction |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Mapping |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Paid Time Off |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Equity |  | 001/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Equity |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | AFUDC-Equity |  | 003/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Benefits OH |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Building Service Overhead |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Capitalized A&G |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | IT Device OH |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35158717 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Construction |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Mapping |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Paid Time Off |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Equity |  | 001/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Equity |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | AFUDC-Equity |  | 003/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Benefits OH |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Building Service Overhead |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Capitalized A&G |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | IT Device OH |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35160091 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Construction |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Mapping |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Paid Time Off |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Equity |  | 001/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Equity |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | AFUDC-Equity |  | 003/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Benefits OH |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Building Service Overhead |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Capitalized A&G |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | IT Device OH |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35160093 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Equity |  | 001/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Equity |  | 002/2021
35160094 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.5 |  | AFUDC-Equity |  | 003/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Engineering/Mapping |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Indirect Labor - Electric |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Paid Time Off |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Borrowed |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Equity |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Equity |  | 002/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | AFUDC-Equity |  | 003/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Benefits OH |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Building Service Overhead |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Capitalized A&G |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Fleet OH - Elec |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | IT Device OH |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Operation Mgmt & Support - Electric |  | 001/2021
35160095 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.6 |  | Payroll Taxes OH |  | 001/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Borrowed |  | 001/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Borrowed |  | 002/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Equity |  | 001/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Equity |  | 002/2021
35160096 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.7 |  | AFUDC-Equity |  | 003/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Borrowed |  | 001/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Borrowed |  | 002/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Borrowed |  | 003/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Equity |  | 001/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Equity |  | 002/2021
35160097 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.8 |  | AFUDC-Equity |  | 003/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Borrowed |  | 001/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Borrowed |  | 002/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Borrowed |  | 003/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Equity |  | 001/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Equity |  | 002/2021
35160098 | CWSP - BRUNSWICK 1105 LR2210 - PH 1.9 |  | AFUDC-Equity |  | 003/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Borrowed |  | 001/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Borrowed |  | 002/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Equity |  | 001/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Equity |  | 002/2021
35160341 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.2 |  | AFUDC-Equity |  | 003/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Borrowed |  | 001/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Borrowed |  | 002/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Equity |  | 001/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Equity |  | 002/2021
35160342 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.3 |  | AFUDC-Equity |  | 003/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Borrowed |  | 001/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Borrowed |  | 002/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Equity |  | 001/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Equity |  | 002/2021
35160343 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.4 |  | AFUDC-Equity |  | 003/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Borrowed |  | 001/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Borrowed |  | 002/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Borrowed |  | 003/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Equity |  | 001/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Equity |  | 002/2021
35160344 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.5 |  | AFUDC-Equity |  | 003/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Borrowed |  | 001/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Borrowed |  | 002/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Borrowed |  | 003/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Equity |  | 001/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Equity |  | 002/2021
35160345 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.6 |  | AFUDC-Equity |  | 003/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Borrowed |  | 001/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Borrowed |  | 002/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Borrowed |  | 003/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Equity |  | 001/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Equity |  | 002/2021
35160346 | CWSP - BRUNSWICK 1105 LR2210 - PH 2.7 |  | AFUDC-Equity |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Electric Construction Contract |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Electric Construction Contract |  | 004/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Environmental Contract |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Environmental Contract |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Gas Construction Contract |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Account Services |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Administrative Services - OT |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction DT |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction DT |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction OT |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction OT |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Civil Construction OT |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Construction |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Construction |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Construction Overtime Services |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Engineering/Mapping |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Engineering/Mapping |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Engineering/Mapping |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Indirect Labor - Cust Care |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Indirect Labor - Electric |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Indirect Labor - Electric |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Indirect Labor - Electric |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Indirect Labor - Environmental Land |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Management Services |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Management Services |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Management Services |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Mapping |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Mapping |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Mapping |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Paid Time Off |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Paid Time Off |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Paid Time Off |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Material Burden |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Borrowed |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Borrowed |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Borrowed |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Equity |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Equity |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | AFUDC-Equity |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Benefits OH |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Benefits OH |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Benefits OH |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Building Service Overhead |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Building Service Overhead |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Building Service Overhead |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Capitalized A&G |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Capitalized A&G |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Capitalized A&G |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Cash Discount earned |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Cash Discount earned |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Fleet OH - Elec |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Fleet OH - Elec |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Fleet OH - Elec |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | IT Device OH |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | IT Device OH |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | IT Device OH |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Minor Material OH |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Operation Mgmt & Support - Electric |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Operation Mgmt & Support - Electric |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Operation Mgmt & Support - Electric |  | 003/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Payroll Taxes OH |  | 001/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Payroll Taxes OH |  | 002/2021
35161152 | OCT2019 BRICEBURG FIRE REBUILD |  | Payroll Taxes OH |  | 003/2021
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35167136 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Borrowed |  | 001/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Borrowed |  | 002/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Borrowed |  | 003/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Equity |  | 001/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Equity |  | 002/2021
35167138 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.3 |  | AFUDC-Equity |  | 003/2021
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35168820 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35168821 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35168822 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35168823 | CWSP - PLACERVILLE 2106 - LR1104 - PH1.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Borrowed |  | 001/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Borrowed |  | 002/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Borrowed |  | 003/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Equity |  | 001/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Equity |  | 002/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | AFUDC-Equity |  | 003/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | Land Acquisition Services |  | 002/2021
35170202 | CWSP - ORO FINO 1101 - LR2022 PH2.7 |  | Land Acquisition Services |  | 003/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35173253 | CWSP-EL DORADO PH 2102 LR19542 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35173255 | CWSP-EL DORADO PH 2102 LR19542 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35173320 | CWSP-EL DORADO PH 2102 LR19542 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35173321 | CWSP-EL DORADO PH 2102 LR19542 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Borrowed |  | 001/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Borrowed |  | 002/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Borrowed |  | 003/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Equity |  | 001/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Equity |  | 002/2021
35173754 | ECOP-BRUNSWICK 1106-H08-LR51486 |  | AFUDC-Equity |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Administrative Services - OT |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Electric Estimating Overtime |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Indirect Labor - Electric |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Indirect Labor - Environmental Land |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Indirect Labor - Environmental Land |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Indirect Labor - Environmental Land |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Land Rights - Misc |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Land Rights - Misc |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Paid Time Off |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Paid Time Off |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Paid Time Off |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Borrowed |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Borrowed |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Borrowed |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Equity |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Equity |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | AFUDC-Equity |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Benefits OH |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Benefits OH |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Benefits OH |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Building Service Overhead |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Building Service Overhead |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Building Service Overhead |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Capitalized A&G |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Capitalized A&G |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Capitalized A&G |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Fleet OH - Elec |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | IT Device OH |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | IT Device OH |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | IT Device OH |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Lodging |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Meals Expense |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Operation Mgmt & Support - Electric |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Payroll Taxes OH |  | 001/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Payroll Taxes OH |  | 002/2021
35173755 | ECOP-WEST POINT 1101-H02-LR36674 |  | Payroll Taxes OH |  | 003/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Borrowed |  | 001/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Borrowed |  | 002/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Borrowed |  | 003/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Equity |  | 001/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Equity |  | 002/2021
35173756 | ECOP-EL DORADO 2101-H02-LR6852-PH2 |  | AFUDC-Equity |  | 003/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Material Burden |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Benefits OH |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Building Service Overhead |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Cash Discount earned |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | IT Device OH |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Minor Material OH |  | 001/2021
35174085 | PSPS - FIA320 - LR @ 101269978 |  | Payroll Taxes OH |  | 001/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Borrowed |  | 001/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Borrowed |  | 002/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Borrowed |  | 003/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Equity |  | 001/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Equity |  | 002/2021
35174465 | ECOP-EL DORADO 2101-H02-LR6852-PH1 |  | AFUDC-Equity |  | 003/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Borrowed |  | 001/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Borrowed |  | 002/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Borrowed |  | 003/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Equity |  | 001/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Equity |  | 002/2021
35174466 | ECOP-EL DORADO 2101-H02-LR6852-PH3 |  | AFUDC-Equity |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Contracts |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Electric Activity Charge - Type A |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Env & Land Activity Charge - Type A |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Indirect Labor - Electric |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Indirect Labor - Environmental Land |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Mapping |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Paid Time Off |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Borrowed |  | 001/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Borrowed |  | 002/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Borrowed |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Equity |  | 001/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Equity |  | 002/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | AFUDC-Equity |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Benefits OH |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Building Service Overhead |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Capitalized A&G |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Cost Adjustments |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Fleet OH - Elec |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | IT Device OH |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35174467 | ECOP-STANISLAUS 1702-H01-LR37276-PH1 |  | Payroll Taxes OH |  | 003/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Borrowed |  | 001/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Borrowed |  | 002/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Borrowed |  | 003/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Equity |  | 001/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Equity |  | 002/2021
35174468 | ECOP-STANISLAUS 1702-H01-LR37276-PH2 |  | AFUDC-Equity |  | 003/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Borrowed |  | 001/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Borrowed |  | 002/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Borrowed |  | 003/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Equity |  | 001/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Equity |  | 002/2021
35174469 | ECOP-PINE GROVE 1102-H01-LR45292 |  | AFUDC-Equity |  | 003/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Borrowed |  | 001/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Borrowed |  | 002/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Borrowed |  | 003/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Equity |  | 001/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Equity |  | 002/2021
35174470 | ECOP-MOLINO 1102-H01-LR318 |  | AFUDC-Equity |  | 003/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Environmental Contract |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Indirect Labor - Electric |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Mapping |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Paid Time Off |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Borrowed |  | 001/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Borrowed |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Borrowed |  | 003/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Equity |  | 001/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Equity |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | AFUDC-Equity |  | 003/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Benefits OH |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Building Service Overhead |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Capitalized A&G |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Fleet OH - Elec |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | IT Device OH |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Operation Mgmt & Support - Electric |  | 002/2021
35174472 | ECOP-CALISTOGA 1101-H02-LR43924 |  | Payroll Taxes OH |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Environmental Contract |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Indirect Labor - Electric |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Mapping |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Paid Time Off |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Borrowed |  | 001/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Borrowed |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Borrowed |  | 003/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Equity |  | 001/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Equity |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | AFUDC-Equity |  | 003/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Benefits OH |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Building Service Overhead |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Capitalized A&G |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Fleet OH - Elec |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | IT Device OH |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Operation Mgmt & Support - Electric |  | 002/2021
35174473 | ECOP-CALISTOGA 1101-H03-LR43924 |  | Payroll Taxes OH |  | 002/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Borrowed |  | 001/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Borrowed |  | 002/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Borrowed |  | 003/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Equity |  | 001/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Equity |  | 002/2021
35174474 | ECOP-CALISTOGA 1101-H01-LR736 PH1 |  | AFUDC-Equity |  | 003/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Borrowed |  | 001/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Borrowed |  | 002/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Borrowed |  | 003/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Equity |  | 001/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Equity |  | 002/2021
35174475 | ECOP-CALISTOGA 1101-H01-LR736-E_O CO3807 |  | AFUDC-Equity |  | 003/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Borrowed |  | 001/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Borrowed |  | 002/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Borrowed |  | 003/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Equity |  | 001/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Equity |  | 002/2021
35174476 | ECOP-CALISTOGA 1101-H01-LR736-S_O 208157 |  | AFUDC-Equity |  | 003/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Borrowed |  | 001/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Borrowed |  | 002/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Borrowed |  | 003/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Equity |  | 001/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Equity |  | 002/2021
35174477 | ECOP-CALISTOGA 1101-H01-LR736-PH3 |  | AFUDC-Equity |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Acquisition - Misc |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Administrative Services - OT |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Administrative Services - OT |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Engineering/Mapping |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Paid Time Off |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Paid Time Off |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Project Management Overtime |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Project Management Services |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | AFUDC-Equity |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | AFUDC-Equity |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Benefits OH |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Benefits OH |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Building Service Overhead |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Building Service Overhead |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Capitalized A&G |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Capitalized A&G |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Fleet OH - Elec |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Fleet OH - Elec |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | IT Device OH |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | IT Device OH |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Payroll Taxes OH |  | 002/2021
35174478 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.1 |  | Payroll Taxes OH |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Administrative Services - OT |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Electric Estimating |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Engineering/Mapping |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Indirect Labor - Electric |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Paid Time Off |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Paid Time Off |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Project Management Overtime |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Project Management Services |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Borrowed |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Equity |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Equity |  | 002/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | AFUDC-Equity |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Benefits OH |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Benefits OH |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Building Service Overhead |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Building Service Overhead |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Capitalized A&G |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Capitalized A&G |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Fleet OH - Elec |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Fleet OH - Elec |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | IT Device OH |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | IT Device OH |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Payroll Taxes OH |  | 001/2021
35174479 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.1 |  | Payroll Taxes OH |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Administrative Services - OT |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Electric Estimating |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Electric Estimating Doubletime |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Electric Estimating Overtime |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Engineering/Mapping |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Engineering/Mapping |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Engineering/Mapping Services Overtime |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Indirect Labor - Electric |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Indirect Labor - Electric |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Indirect Labor - Electric |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Paid Time Off |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Paid Time Off |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Paid Time Off |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Project Management Overtime |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Project Management Overtime |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Project Management Services |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Borrowed |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Borrowed |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Borrowed |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Equity |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Equity |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | AFUDC-Equity |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Benefits OH |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Benefits OH |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Benefits OH |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Building Service Overhead |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Building Service Overhead |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Building Service Overhead |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Capitalized A&G |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Capitalized A&G |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Capitalized A&G |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Fleet OH - Elec |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Fleet OH - Elec |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Fleet OH - Elec |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | IT Device OH |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | IT Device OH |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | IT Device OH |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Payroll Taxes OH |  | 001/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Payroll Taxes OH |  | 002/2021
35174501 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.1 |  | Payroll Taxes OH |  | 003/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Borrowed |  | 001/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Borrowed |  | 002/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Borrowed |  | 003/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Equity |  | 001/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Equity |  | 002/2021
35175847 | CWSP - PLACERVILLE 2106 - LR1104 - PH4.2 |  | AFUDC-Equity |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Account Services |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Acquisition - Misc |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Indirect Labor - Cust Care |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Indirect Labor - Environmental Land |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Management Services |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Management Services |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Paid Time Off |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Paid Time Off |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | AFUDC-Borrowed |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | AFUDC-Borrowed |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | AFUDC-Equity |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | AFUDC-Equity |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Benefits OH |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Benefits OH |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Building Service Overhead |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Building Service Overhead |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Capitalized A&G |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Capitalized A&G |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | IT Device OH |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | IT Device OH |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Payroll Taxes OH |  | 002/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Payroll Taxes OH |  | 003/2021
35175853 | CWSP - PLACERVILLE 2106 - LR1104 - PH5.3 |  | Reimbursed Mileage Expense |  | 003/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | AFUDC-Borrowed |  | 001/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | AFUDC-Borrowed |  | 002/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | AFUDC-Equity |  | 001/2021
35175856 | CWSP - PLACERVILLE 2106 - LR1104 - PH6.2 |  | AFUDC-Equity |  | 002/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Borrowed |  | 001/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Borrowed |  | 002/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Borrowed |  | 003/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Equity |  | 001/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Equity |  | 002/2021
35181199 | ECOP-WEST POINT 1101-H03-TS L373 |  | AFUDC-Equity |  | 003/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Borrowed |  | 001/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Borrowed |  | 002/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Borrowed |  | 003/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Equity |  | 001/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Equity |  | 002/2021
35185714 | WDDB - OTTER 1102 - LR 2002 |  | AFUDC-Equity |  | 003/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Borrowed |  | 001/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Borrowed |  | 002/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Borrowed |  | 003/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Equity |  | 001/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Equity |  | 002/2021
35191130 | ECOP - CALISTOGA 1101 - H01 - LR 736-PH5 |  | AFUDC-Equity |  | 003/2021
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191317 | ECOP - BRUNSWICK 1106 - H03 - LR4639 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Environmental Contract |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Design Drafting Services - Overtime |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating |  | 004/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating Overtime |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating Overtime |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Electric Estimating Overtime |  | 004/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engineering/Mapping |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Engineering/Mapping |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Indirect Labor - Electric |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Indirect Labor - Electric |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Indirect Labor - Electric |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Indirect Labor - Environmental Land |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Mapping |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Paid Time Off |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Paid Time Off |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Paid Time Off |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Project Management Services |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Project Management Services |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Benefits OH |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Benefits OH |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Benefits OH |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Building Service Overhead |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Building Service Overhead |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Building Service Overhead |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Capitalized A&G |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Capitalized A&G |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Capitalized A&G |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Fleet OH - Elec |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Fleet OH - Elec |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Fleet OH - Elec |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | IT Device OH |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | IT Device OH |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | IT Device OH |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Operation Mgmt & Support - Electric |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Operation Mgmt & Support - Electric |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Operation Mgmt & Support - Electric |  | 003/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Payroll Taxes OH |  | 001/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Payroll Taxes OH |  | 002/2021
35191318 | ECOP - SILVERADO 2102 - H02-LR58626 |  | Payroll Taxes OH |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Contracts |  | 004/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Environmental Contract |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Acquisition - Misc |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Acquisition - Misc |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Acquisition - Misc |  | 004/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Administrative Services - OT |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engineering/Mapping |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Engineering/Mapping |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Indirect Labor - Electric |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Indirect Labor - Electric |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Indirect Labor - Environmental Land |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Indirect Labor - Environmental Land |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Indirect Labor - Environmental Land |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Mapping |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Paid Time Off |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Paid Time Off |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Paid Time Off |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Benefits OH |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Benefits OH |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Benefits OH |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Building Service Overhead |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Building Service Overhead |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Building Service Overhead |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Capitalized A&G |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Capitalized A&G |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Capitalized A&G |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Fleet OH - Elec |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Fleet OH - Elec |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | IT Device OH |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | IT Device OH |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | IT Device OH |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Operation Mgmt & Support - Electric |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Operation Mgmt & Support - Electric |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Payroll Taxes OH |  | 001/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Payroll Taxes OH |  | 002/2021
35191319 | ECOP - LAS GALLINAS A 1105 - H01-LR99904 |  | Payroll Taxes OH |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Environmental Contract |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Design Drafting Services |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Design Drafting Services |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Design Drafting Services - Overtime |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Design Drafting Services - Overtime |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Drafting Doubletime |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Electric Estimating |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Electric Estimating |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Electric Estimating Overtime |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engineering/Mapping |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Engineering/Mapping |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Indirect Labor - Electric |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Indirect Labor - Electric |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Indirect Labor - Electric |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Indirect Labor - Environmental Land |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Mapping |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Paid Time Off |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Paid Time Off |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Paid Time Off |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Project Management Services |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Project Management Services |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Benefits OH |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Benefits OH |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Benefits OH |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Building Service Overhead |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Building Service Overhead |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Building Service Overhead |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Capitalized A&G |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Capitalized A&G |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Capitalized A&G |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Fleet OH - Elec |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Fleet OH - Elec |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Fleet OH - Elec |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | IT Device OH |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | IT Device OH |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | IT Device OH |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Operation Mgmt & Support - Electric |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Operation Mgmt & Support - Electric |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Operation Mgmt & Support - Electric |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Payroll Taxes OH |  | 001/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Payroll Taxes OH |  | 002/2021
35191383 | ECOP - SILVERADO 2102 - H01-LR58626 |  | Payroll Taxes OH |  | 003/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Borrowed |  | 001/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Borrowed |  | 002/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Borrowed |  | 003/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Equity |  | 001/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Equity |  | 002/2021
35191930 | ECOP - WOODACRE 1101 - H01-LR404 PH1 |  | AFUDC-Equity |  | 003/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Borrowed |  | 001/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Borrowed |  | 002/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Borrowed |  | 003/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Equity |  | 001/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Equity |  | 002/2021
35191934 | ECOP - WOODACRE 1101 - H01-LR404 PH2 |  | AFUDC-Equity |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Environmental Contract |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Environmental Contract |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Account Services |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Acquisition - Misc |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Acquisition - Misc |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Administration |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Electric Estimating |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Cust Care |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Manage L&EM |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Mapping |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Mapping |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Mapping |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Paid Time Off |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Paid Time Off |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Paid Time Off |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Project Management Overtime |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Project Management Services |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Benefits OH |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Benefits OH |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Benefits OH |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Building Service Overhead |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Building Service Overhead |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Building Service Overhead |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Capitalized A&G |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Capitalized A&G |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Capitalized A&G |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | IT Device OH |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | IT Device OH |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | IT Device OH |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Land Acquisition Services |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35191937 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Borrowed |  | 001/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Borrowed |  | 002/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Borrowed |  | 003/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Equity |  | 001/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Equity |  | 002/2021
35192021 | ECOP - SILVERADO 2104 - H02-LR78268 |  | AFUDC-Equity |  | 003/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Equity |  | 001/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Equity |  | 002/2021
35192025 | ECOP - FORESTHILL 1101 - H02-LR1802 PH1 |  | AFUDC-Equity |  | 003/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Equity |  | 001/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Equity |  | 002/2021
35192028 | ECOP - FORESTHILL 1101 - H02-LR1802 PH2 |  | AFUDC-Equity |  | 003/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Borrowed |  | 001/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Borrowed |  | 002/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Borrowed |  | 003/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Equity |  | 001/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Equity |  | 002/2021
35192029 | ECOP - FORESTHILL 1101 - H02-LR1802 PH3 |  | AFUDC-Equity |  | 003/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Borrowed |  | 001/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Borrowed |  | 002/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Borrowed |  | 003/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Equity |  | 001/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Equity |  | 002/2021
35192031 | ECOP - COLUMBIA HILL 1101 - H01-LR35424 |  | AFUDC-Equity |  | 003/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Borrowed |  | 001/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Borrowed |  | 002/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Borrowed |  | 003/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Equity |  | 001/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Equity |  | 002/2021
35192034 | ECOP-APPLE HILL 1104-H01-LR13512 |  | AFUDC-Equity |  | 003/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Borrowed |  | 001/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Borrowed |  | 002/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Borrowed |  | 003/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Equity |  | 001/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Equity |  | 002/2021
35192035 | ECOP - MIRABEL 1101 - H01-LR298 |  | AFUDC-Equity |  | 003/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Borrowed |  | 001/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Borrowed |  | 002/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Borrowed |  | 003/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Equity |  | 001/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Equity |  | 002/2021
35192036 | ECOP - RINCON 1103 - H01-LR474 |  | AFUDC-Equity |  | 003/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Borrowed |  | 001/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Borrowed |  | 002/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Borrowed |  | 003/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Equity |  | 001/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Equity |  | 002/2021
35192037 | ECOP - SILVERADO 2105 - H01-LR1421 |  | AFUDC-Equity |  | 003/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Borrowed |  | 001/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Borrowed |  | 002/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Borrowed |  | 003/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Equity |  | 001/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Equity |  | 002/2021
35192039 | ECOP - MONTE RIO 1113 - H04-LR320 |  | AFUDC-Equity |  | 003/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Borrowed |  | 001/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Borrowed |  | 002/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Borrowed |  | 003/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Equity |  | 001/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Equity |  | 002/2021
35192040 | ECOP - MONTE RIO 1113 - H08-LR477 |  | AFUDC-Equity |  | 003/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Borrowed |  | 001/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Borrowed |  | 002/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Borrowed |  | 003/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Equity |  | 001/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Equity |  | 002/2021
35192041 | ECOP - WEST POINT 1101 - H01-LR4706 |  | AFUDC-Equity |  | 003/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Equity |  | 001/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Equity |  | 002/2021
35192043 | ECOP - PINE GROVE 1102 - H03-LR13438 PH1 |  | AFUDC-Equity |  | 003/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Equity |  | 001/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Equity |  | 002/2021
35192044 | ECOP - PINE GROVE 1102 - H03-LR13438 PH2 |  | AFUDC-Equity |  | 003/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Borrowed |  | 001/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Borrowed |  | 002/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Borrowed |  | 003/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Equity |  | 001/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Equity |  | 002/2021
35192045 | ECOP - STANISLAUS 1702 - H02-LR75348 |  | AFUDC-Equity |  | 003/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Equity |  | 001/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Equity |  | 002/2021
35192046 | ECOP - PINE GROVE 1102 - H04-LR3172 PH1 |  | AFUDC-Equity |  | 003/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Equity |  | 001/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Equity |  | 002/2021
35192047 | ECOP - PINE GROVE 1102 - H04-LR3172 PH2 |  | AFUDC-Equity |  | 003/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Borrowed |  | 001/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Borrowed |  | 002/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Borrowed |  | 003/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Equity |  | 001/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Equity |  | 002/2021
35192048 | ECOP - PINE GROVE 1102 - H04-LR3172 PH3 |  | AFUDC-Equity |  | 003/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Borrowed |  | 001/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Borrowed |  | 002/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Borrowed |  | 003/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Equity |  | 001/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Equity |  | 002/2021
35192049 | ECOP - PINE GROVE 1102 - H04-LR3172 PH4 |  | AFUDC-Equity |  | 003/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Borrowed |  | 001/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Borrowed |  | 002/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Borrowed |  | 003/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Equity |  | 001/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Equity |  | 002/2021
35192050 | ECOP - WEST POINT 1102 - H01-TS1303 |  | AFUDC-Equity |  | 003/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Borrowed |  | 001/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Borrowed |  | 002/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Borrowed |  | 003/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Equity |  | 001/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Equity |  | 002/2021
35192051 | ECOP - SALT SPRINGS 2102 - H01-LR4796 |  | AFUDC-Equity |  | 003/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Borrowed |  | 001/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Borrowed |  | 002/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Borrowed |  | 003/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Equity |  | 001/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Equity |  | 002/2021
35192052 | ECOP - WEST POINT 1102 - H05-LR34416 |  | AFUDC-Equity |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction Inspection |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction Inspection |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Contracts |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Contracts |  | 004/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Contracts |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 004/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Contract |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Consulting Services - Environmental Perm |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Administration |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Administrative Services - OT |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Administrative Services - OT |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Administrative Services - OT |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction Doubletime Services |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction Doubletime Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Design Drafting Services |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Design Drafting Services - Overtime |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Design Overtime Services |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Design Services |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Design Services Double Time |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Drafting Doubletime |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electric Estimating |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electric Estimating Doubletime |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electric Estimating Overtime |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Engineering/Mapping |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Engineering/Mapping |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Engineering/Mapping |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Environmental Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Hours - Overtime |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Hours - Straight Time |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Hours - Straight Time |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Electric |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Electric |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Electric |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Environmental Land |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Environmental Land |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - Environmental Land |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - IT |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Indirect Labor - IT |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maint & Operate Doubletime Services |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maint & Operate Doubletime Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maintain & Operate Overtime Services |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maintain & Operate Overtime Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maintain & Operate Services |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Maintain & Operate Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Manage L&EM |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Manage L&EM |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Mapping |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Mapping |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operating Services |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Paid Time Off |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Paid Time Off |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Paid Time Off |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Communication & Signaling Equipment |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Conductors, Cable & Wire Connectors |  | 004/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Construction Supplies |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electl & Electronic Equipment Component |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electrical Specialties |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Electrical Specialties |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Fabricated Structures |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Material Burden |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Material Burden |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Materials Not Otherwise Classified |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Transformers, Regulators & Capacitors |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Equity |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Equity |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | AFUDC-Equity |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Benefits OH |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Benefits OH |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Benefits OH |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Building Service Overhead |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Building Service Overhead |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Building Service Overhead |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Capitalized A&G |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Capitalized A&G |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Capitalized A&G |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Cash Discount earned |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Fleet OH - Elec |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Fleet OH - Elec |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Fleet OH - Elec |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | IT Device OH |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | IT Device OH |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | IT Device OH |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Minor Material OH |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Minor Material OH |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - IT |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Operation Mgmt & Support - IT |  | 003/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Payroll Taxes OH |  | 001/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Payroll Taxes OH |  | 002/2021
35192053 | STRM-OAKHURST 1103-LR 5120 PH1 |  | Payroll Taxes OH |  | 003/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Borrowed |  | 001/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Borrowed |  | 002/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Borrowed |  | 003/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Equity |  | 001/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Equity |  | 002/2021
35192054 | ECOP-OAKHURST 1103-LR 5470 |  | AFUDC-Equity |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Environmental Contract |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Consulting Services - Engineering |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Consulting Services - Engineering |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Construction |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Design Overtime Services |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Electric Estimating |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Electric Estimating Doubletime |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Electric Estimating Overtime |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engineering/Mapping |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Engineering/Mapping |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Indirect Labor - Electric |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Indirect Labor - Electric |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Indirect Labor - Electric |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Indirect Labor - Environmental Land |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Indirect Labor - Environmental Land |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Land Rights - Misc |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Mapping |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Mapping |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Mapping |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Paid Time Off |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Paid Time Off |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Paid Time Off |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Borrowed |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Borrowed |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Borrowed |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Equity |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Equity |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | AFUDC-Equity |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Benefits OH |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Benefits OH |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Benefits OH |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Building Service Overhead |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Building Service Overhead |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Building Service Overhead |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Capitalized A&G |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Capitalized A&G |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Capitalized A&G |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Fleet OH - Elec |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Fleet OH - Elec |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Fleet OH - Elec |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | IT Device OH |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | IT Device OH |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | IT Device OH |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Payroll Taxes OH |  | 001/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Payroll Taxes OH |  | 002/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Payroll Taxes OH |  | 003/2021
35192280 | ECOP - CLAYTON 2212 - H01-LR2951 |  | Permits/FeesLand Surveying Services |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Environmental Contract |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Account Services |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Design Services |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Electric Estimating |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Electric Estimating |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Electric Estimating Overtime |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engineering/Mapping |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Engineering/Mapping |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Indirect Labor - Cust Care |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Indirect Labor - Electric |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Indirect Labor - Electric |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Indirect Labor - Electric |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Indirect Labor - Environmental Land |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Mapping |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Paid Time Off |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Paid Time Off |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Paid Time Off |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Equity |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Equity |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | AFUDC-Equity |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Benefits OH |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Benefits OH |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Benefits OH |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Building Service Overhead |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Building Service Overhead |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Building Service Overhead |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Capitalized A&G |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Capitalized A&G |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Capitalized A&G |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Fleet OH - Elec |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Fleet OH - Elec |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Fleet OH - Elec |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | IT Device OH |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | IT Device OH |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | IT Device OH |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Payroll Taxes OH |  | 001/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Payroll Taxes OH |  | 002/2021
35192281 | ECOP - MIDDLETOWN 1101 - H16-LR48212 PH1 |  | Payroll Taxes OH |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Environmental Contract |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Account Services |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Electric Estimating |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Electric Estimating Overtime |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engineering/Mapping |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Engineering/Mapping |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Indirect Labor - Cust Care |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Indirect Labor - Electric |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Indirect Labor - Electric |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Mapping |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Paid Time Off |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Paid Time Off |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Paid Time Off |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Borrowed |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Equity |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Equity |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | AFUDC-Equity |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Benefits OH |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Benefits OH |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Benefits OH |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Building Service Overhead |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Building Service Overhead |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Building Service Overhead |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Capitalized A&G |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Capitalized A&G |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Capitalized A&G |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Fleet OH - Elec |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Fleet OH - Elec |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Fleet OH - Elec |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | IT Device OH |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | IT Device OH |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | IT Device OH |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Payroll Taxes OH |  | 001/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Payroll Taxes OH |  | 002/2021
35192282 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.1 |  | Payroll Taxes OH |  | 003/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Borrowed |  | 001/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Borrowed |  | 002/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Borrowed |  | 003/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Equity |  | 001/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Equity |  | 002/2021
35192283 | ECOP - CALISTOGA 1101 - H04-LR1087 |  | AFUDC-Equity |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Environmental Contract |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Consulting Services - Engineering |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Administrative Services - OT |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Electric Estimating |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Electric Estimating |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Electric Estimating Overtime |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engineering/Mapping |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Engineering/Mapping |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Electric |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Electric |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Electric |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Environmental Land |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Environmental Land |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Indirect Labor - Environmental Land |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Mapping |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Mapping |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Paid Time Off |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Paid Time Off |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Paid Time Off |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Project Management Services |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Borrowed |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Borrowed |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Borrowed |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Equity |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Equity |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | AFUDC-Equity |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Benefits OH |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Benefits OH |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Benefits OH |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Building Service Overhead |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Building Service Overhead |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Building Service Overhead |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Capitalized A&G |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Capitalized A&G |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Capitalized A&G |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Fleet OH - Elec |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Fleet OH - Elec |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Fleet OH - Elec |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | IT Device OH |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | IT Device OH |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | IT Device OH |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Payroll Taxes OH |  | 001/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Payroll Taxes OH |  | 002/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Payroll Taxes OH |  | 003/2021
35192284 | ECOP - SILVERADO 2104 - H05-LR726 |  | Permits/FeesLand Surveying Services |  | 003/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Equity |  | 001/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Equity |  | 002/2021
35192285 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH1 |  | AFUDC-Equity |  | 003/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Equity |  | 001/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Equity |  | 002/2021
35192286 | ECOP - BRUNSWICK 1106 - H01 - LR2796 PH2 |  | AFUDC-Equity |  | 003/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Borrowed |  | 001/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Borrowed |  | 002/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Borrowed |  | 003/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Equity |  | 001/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Equity |  | 002/2021
35192287 | ECOP - BRUNSWICK 1106 - H02 - CB |  | AFUDC-Equity |  | 003/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Borrowed |  | 001/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Borrowed |  | 002/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Borrowed |  | 003/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Equity |  | 001/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Equity |  | 002/2021
35192288 | ECOP - BRUNSWICK 1106 - H04 - LR2416 |  | AFUDC-Equity |  | 003/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Borrowed |  | 001/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Borrowed |  | 002/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Borrowed |  | 003/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Equity |  | 001/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Equity |  | 002/2021
35192289 | ECOP - BRUNSWICK 1106 - H07 - LR 51484 |  | AFUDC-Equity |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Environmental Contract |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Environmental Contract |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Consulting Services - Engineering |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Consulting Services - Engineering |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Consulting Services - Engineering |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Administration |  | 004/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Construction |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Design Overtime Services |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Design Services |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engineering Services - OT |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engineering/Mapping |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engineering/Mapping |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Engineering/Mapping Services Overtime |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Indirect Labor - Electric |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Indirect Labor - Electric |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Indirect Labor - Electric |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Indirect Labor - Environmental Land |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Indirect Labor - Environmental Land |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Land Rights - Misc |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Mapping |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Mapping |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Mapping |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Paid Time Off |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Paid Time Off |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Paid Time Off |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Borrowed |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Borrowed |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Borrowed |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Equity |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Equity |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | AFUDC-Equity |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Benefits OH |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Benefits OH |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Benefits OH |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Building Service Overhead |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Building Service Overhead |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Building Service Overhead |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Capitalized A&G |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Capitalized A&G |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Capitalized A&G |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Fleet OH - Elec |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Fleet OH - Elec |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Fleet OH - Elec |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | IT Device OH |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | IT Device OH |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | IT Device OH |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Land Acquisition Services |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Payroll Taxes OH |  | 001/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Payroll Taxes OH |  | 002/2021
35192290 | ECOP - DIAMOND SPRINGS 1107 - H01-LR1402 |  | Payroll Taxes OH |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Environmental Contract |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Environmental Contract |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Consulting Services - Engineering |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Consulting Services - Engineering |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Consulting Services - Engineering |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Administrative Services - OT |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Design Overtime Services |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Design Services |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Electric Estimating |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Electric Estimating Overtime |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Engineering/Mapping |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Engineering/Mapping |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Electric |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Electric |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Electric |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Environmental Land |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Environmental Land |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Indirect Labor - Environmental Land |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Mapping |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Mapping |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Mapping |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Paid Time Off |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Paid Time Off |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Paid Time Off |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Borrowed |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Borrowed |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Borrowed |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Equity |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Equity |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | AFUDC-Equity |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Benefits OH |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Benefits OH |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Benefits OH |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Building Service Overhead |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Building Service Overhead |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Building Service Overhead |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Capitalized A&G |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Capitalized A&G |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Capitalized A&G |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Fleet OH - Elec |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Fleet OH - Elec |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Fleet OH - Elec |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | IT Device OH |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | IT Device OH |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | IT Device OH |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Land Acquisition Services |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Payroll Taxes OH |  | 001/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Payroll Taxes OH |  | 002/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Payroll Taxes OH |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Permits/FeesLand Surveying Services |  | 003/2021
35192291 | ECOP - DIAMOND SPRINGS 1107 - H02-LR1402 |  | Permits/FeesLand Surveying Services |  | 004/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Environmental Contract |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Environmental Contract |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Consulting Services - Engineering |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Consulting Services - Engineering |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Account Services |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Account Services |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Acquisition - Misc |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Electric Estimating Overtime |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Electric Estimating Overtime |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engineering/Mapping |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engineering/Mapping |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Engineering/Mapping |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Cust Care |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Mapping |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Mapping |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Mapping |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Paid Time Off |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Paid Time Off |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Paid Time Off |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Equity |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Equity |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | AFUDC-Equity |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Benefits OH |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Benefits OH |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Benefits OH |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Building Service Overhead |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Building Service Overhead |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Building Service Overhead |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Capitalized A&G |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Capitalized A&G |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Capitalized A&G |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Fleet OH - Elec |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Fleet OH - Elec |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | IT Device OH |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | IT Device OH |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | IT Device OH |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Payroll Taxes OH |  | 001/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Payroll Taxes OH |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Permits/FeesLand Surveying Services |  | 002/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Permits/FeesLand Surveying Services |  | 003/2021
35192292 | ECOP - FULTON 1107 - H02-LR604 PH1.1 |  | Permits/FeesLand Surveying Services |  | 004/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Equity |  | 001/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Equity |  | 002/2021
35192293 | ECOP - MOLINO 1102 - H03-LR396 PH1 |  | AFUDC-Equity |  | 003/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Equity |  | 001/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Equity |  | 002/2021
35192294 | ECOP - MOLINO 1102 - H03-LR396 PH2 |  | AFUDC-Equity |  | 003/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Borrowed |  | 001/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Borrowed |  | 002/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Borrowed |  | 003/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Equity |  | 001/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Equity |  | 002/2021
35192295 | ECOP - RINCON 1103 - H02-LR198 |  | AFUDC-Equity |  | 003/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Borrowed |  | 001/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Borrowed |  | 002/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Borrowed |  | 003/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Equity |  | 001/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Equity |  | 002/2021
35192296 | ECOP - PINE GROVE 1102 - H06-LR83098 |  | AFUDC-Equity |  | 003/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Borrowed |  | 001/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Borrowed |  | 002/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Borrowed |  | 003/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Equity |  | 001/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Equity |  | 002/2021
35192297 | ECOP - PINE GROVE 1102 - H07-CB |  | AFUDC-Equity |  | 003/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Borrowed |  | 001/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Borrowed |  | 002/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Borrowed |  | 003/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Equity |  | 001/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Equity |  | 002/2021
35192298 | ECOP - SALT SPRINGS 2102 - H02-LR37300 |  | AFUDC-Equity |  | 003/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Borrowed |  | 001/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Borrowed |  | 002/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Borrowed |  | 003/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Equity |  | 001/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Equity |  | 002/2021
35192299 | ECOP - SALT SPRINGS 2102 - H04-LR97924 |  | AFUDC-Equity |  | 003/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Borrowed |  | 001/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Borrowed |  | 002/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Borrowed |  | 003/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Equity |  | 001/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Equity |  | 002/2021
35192300 | ECOP - WEST POINT 1101 - H04-TSL3355 |  | AFUDC-Equity |  | 003/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Borrowed |  | 001/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Borrowed |  | 002/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Borrowed |  | 003/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Equity |  | 001/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Equity |  | 002/2021
35192301 | ECOP - WEST POINT 1102 - H06-LR36676 |  | AFUDC-Equity |  | 003/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Borrowed |  | 001/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Borrowed |  | 002/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Borrowed |  | 003/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Equity |  | 001/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Equity |  | 002/2021
35192302 | ECOP - WEST POINT 1102 - H07-LR93116 |  | AFUDC-Equity |  | 003/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Borrowed |  | 001/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Borrowed |  | 002/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Borrowed |  | 003/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Equity |  | 001/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Equity |  | 002/2021
35192303 | ECOP - MARIPOSA 2101 - H01-LR10170 PH1 |  | AFUDC-Equity |  | 003/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Borrowed |  | 001/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Borrowed |  | 002/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Borrowed |  | 003/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Equity |  | 001/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Equity |  | 002/2021
35192304 | ECOP - MARIPOSA 2101 - H01-LR10170 PH2 |  | AFUDC-Equity |  | 003/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Borrowed |  | 001/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Borrowed |  | 002/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Borrowed |  | 003/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Equity |  | 001/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Equity |  | 002/2021
35192305 | ECOP - MIWUK 1702 - H01-LR8130 |  | AFUDC-Equity |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Acquisition - Misc |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Administrative Services - OT |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Administrative Services - OT |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Indirect Labor - Environmental Land |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Indirect Labor - Environmental Land |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Indirect Labor - Environmental Land |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Rights - Misc |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Rights - Misc |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Rights - Misc |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Paid Time Off |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Paid Time Off |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Paid Time Off |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Borrowed |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Borrowed |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Borrowed |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Equity |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Equity |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | AFUDC-Equity |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Benefits OH |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Benefits OH |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Benefits OH |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Building Service Overhead |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Building Service Overhead |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Building Service Overhead |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Capitalized A&G |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Capitalized A&G |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Capitalized A&G |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | IT Device OH |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | IT Device OH |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | IT Device OH |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Lodging |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Meals Expense |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Payroll Taxes OH |  | 001/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Payroll Taxes OH |  | 002/2021
35199560 | ECOP-WEST POINT 1101-H02-LR36674-PH2 |  | Payroll Taxes OH |  | 003/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Borrowed |  | 001/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Borrowed |  | 002/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Borrowed |  | 003/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Equity |  | 001/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Equity |  | 002/2021
35200127 | ECOP - FORESTHILL 1101 - H03-LR50486 |  | AFUDC-Equity |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Contracts |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Contracts |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Contracts |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Contracts |  | 004/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Indirect Labor - Electric |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Indirect Labor - Electric |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Indirect Labor - Electric |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Mapping |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Mapping |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Mapping |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Paid Time Off |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Paid Time Off |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Paid Time Off |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Material Burden |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Material Burden |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Material Burden |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 004/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Borrowed |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Borrowed |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Borrowed |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Equity |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Equity |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | AFUDC-Equity |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Benefits OH |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Benefits OH |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Benefits OH |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Building Service Overhead |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Building Service Overhead |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Building Service Overhead |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Capitalized A&G |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Capitalized A&G |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Capitalized A&G |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Fleet OH - Elec |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Fleet OH - Elec |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Fleet OH - Elec |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | IT Device OH |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | IT Device OH |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | IT Device OH |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Minor Material OH |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Minor Material OH |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Minor Material OH |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Payroll Taxes OH |  | 001/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Payroll Taxes OH |  | 002/2021
35212401 | FRRB - MONTICELLO 1101 CB |  | Payroll Taxes OH |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Contracts |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Electric Activity Charge - Type A |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | GAS Activity Charge - Type A |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Indirect Labor - Electric |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Indirect Labor - Environmental Land |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Indirect Labor - Gas |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Mapping |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Paid Time Off |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Construction Supplies |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Fabricated Structures |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Material Burden |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Materials Not Otherwise Classified |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Borrowed |  | 001/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Borrowed |  | 002/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Borrowed |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Equity |  | 001/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Equity |  | 002/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | AFUDC-Equity |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Benefits OH |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Building Service Overhead |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Capitalized A&G |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Cost Adjustments |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Fleet OH - Elec |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Fleet OH - Gas |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | IT Device OH |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Minor Material OH |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212402 | FRRB - MONTICELLO 1101 LR 666 |  | Payroll Taxes OH |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Contracts |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Electric Activity Charge - Type A |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | GAS Activity Charge - Type A |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Indirect Labor - Electric |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Indirect Labor - Environmental Land |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Indirect Labor - Gas |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Mapping |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Paid Time Off |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Construction Supplies |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Fabricated Structures |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Material Burden |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Materials Not Otherwise Classified |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Borrowed |  | 001/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Borrowed |  | 002/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Borrowed |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Equity |  | 001/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Equity |  | 002/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | AFUDC-Equity |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Benefits OH |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Building Service Overhead |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Capitalized A&G |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Cost Adjustments |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Fleet OH - Elec |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Fleet OH - Gas |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | IT Device OH |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Minor Material OH |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212403 | FRRB - MONTICELLO 1101 LR 654 |  | Payroll Taxes OH |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Contracts |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Electric Activity Charge - Type A |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | GAS Activity Charge - Type A |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Indirect Labor - Electric |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Indirect Labor - Environmental Land |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Indirect Labor - Gas |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Mapping |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Paid Time Off |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Construction Supplies |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Fabricated Structures |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Material Burden |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Materials Not Otherwise Classified |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Borrowed |  | 001/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Borrowed |  | 002/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Borrowed |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Equity |  | 001/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Equity |  | 002/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | AFUDC-Equity |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Benefits OH |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Building Service Overhead |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Capitalized A&G |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Cost Adjustments |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Fleet OH - Elec |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Fleet OH - Gas |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | IT Device OH |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Minor Material OH |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212404 | FRRB - MONTICELLO 1101 LR 630 |  | Payroll Taxes OH |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Contracts |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Electric Activity Charge - Type A |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | GAS Activity Charge - Type A |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Indirect Labor - Electric |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Indirect Labor - Environmental Land |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Indirect Labor - Gas |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Mapping |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Paid Time Off |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Construction Supplies |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Fabricated Structures |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Material Burden |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Materials Not Otherwise Classified |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Borrowed |  | 001/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Borrowed |  | 002/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Borrowed |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Equity |  | 001/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Equity |  | 002/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | AFUDC-Equity |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Benefits OH |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Building Service Overhead |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Capitalized A&G |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Cost Adjustments |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Fleet OH - Elec |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Fleet OH - Gas |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | IT Device OH |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Minor Material OH |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212405 | FRRB - MONTICELLO 1101 LR 93384 |  | Payroll Taxes OH |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Contracts |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Electric Activity Charge - Type A |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | GAS Activity Charge - Type A |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Indirect Labor - Electric |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Indirect Labor - Environmental Land |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Indirect Labor - Gas |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Mapping |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Paid Time Off |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Construction Supplies |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Fabricated Structures |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Material Burden |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Materials Not Otherwise Classified |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Borrowed |  | 001/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Borrowed |  | 002/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Borrowed |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Equity |  | 001/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Equity |  | 002/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | AFUDC-Equity |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Benefits OH |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Building Service Overhead |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Capitalized A&G |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Cost Adjustments |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Fleet OH - Elec |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Fleet OH - Gas |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | IT Device OH |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Minor Material OH |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212406 | FRRB - MONTICELLO 1101 LR 37384 |  | Payroll Taxes OH |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Contracts |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Contractor Activity Charges |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Electric Activity Charge - Type A |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Indirect Labor - Electric |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Indirect Labor - Environmental Land |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Mapping |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Paid Time Off |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Borrowed |  | 001/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Borrowed |  | 002/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Borrowed |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Equity |  | 001/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Equity |  | 002/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | AFUDC-Equity |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Benefits OH |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Building Service Overhead |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Capitalized A&G |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Cost Adjustments |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Fleet OH - Elec |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | IT Device OH |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212407 | FRRB - SILVERADO 2102 LR 636 |  | Payroll Taxes OH |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Contracts |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Contractor Activity Charges |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Electric Activity Charge - Type A |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Indirect Labor - Electric |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Indirect Labor - Environmental Land |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Mapping |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Paid Time Off |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Borrowed |  | 001/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Borrowed |  | 002/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Borrowed |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Equity |  | 001/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Equity |  | 002/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | AFUDC-Equity |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Benefits OH |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Building Service Overhead |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Capitalized A&G |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Cost Adjustments |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Fleet OH - Elec |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | IT Device OH |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212408 | FRRB - SILVERADO 2102 LR 34959 |  | Payroll Taxes OH |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Contracts |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Contractor Activity Charges |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Electric Activity Charge - Type A |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Indirect Labor - Electric |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Indirect Labor - Environmental Land |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Mapping |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Paid Time Off |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | AFUDC-Borrowed |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | AFUDC-Equity |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Benefits OH |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Building Service Overhead |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Capitalized A&G |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Cost Adjustments |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Fleet OH - Elec |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | IT Device OH |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212409 | FRRB - SILVERADO 2104 LR 645 |  | Payroll Taxes OH |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Contracts |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Contractor Activity Charges |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Electric Activity Charge - Type A |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Indirect Labor - Electric |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Indirect Labor - Environmental Land |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Mapping |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Paid Time Off |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Borrowed |  | 001/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Borrowed |  | 002/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Borrowed |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Equity |  | 001/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Equity |  | 002/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | AFUDC-Equity |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Benefits OH |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Building Service Overhead |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Capitalized A&G |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Cost Adjustments |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Fleet OH - Elec |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | IT Device OH |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212410 | FRRB - SILVERADO 2104 LR 708 |  | Payroll Taxes OH |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Contracts |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Contractor Activity Charges |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Electric Activity Charge - Type A |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Indirect Labor - Electric |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Indirect Labor - Environmental Land |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Mapping |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Paid Time Off |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | AFUDC-Borrowed |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | AFUDC-Equity |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Benefits OH |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Building Service Overhead |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Capitalized A&G |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Cost Adjustments |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Fleet OH - Elec |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | IT Device OH |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212411 | FRRB - SILVERADO 2104 LR 722 |  | Payroll Taxes OH |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Contracts |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Contractor Activity Charges |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Electric Activity Charge - Type A |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Indirect Labor - Electric |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Indirect Labor - Environmental Land |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Mapping |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Paid Time Off |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Borrowed |  | 001/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Borrowed |  | 002/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Borrowed |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Equity |  | 001/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Equity |  | 002/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | AFUDC-Equity |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Benefits OH |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Building Service Overhead |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Capitalized A&G |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Cost Adjustments |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Fleet OH - Elec |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | IT Device OH |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212412 | FRRB - SILVERADO 2104 LR 37632 |  | Payroll Taxes OH |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Contracts |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Contractor Activity Charges |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Electric Activity Charge - Type A |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Indirect Labor - Electric |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Indirect Labor - Environmental Land |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Mapping |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Paid Time Off |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Borrowed |  | 001/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Borrowed |  | 002/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Borrowed |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Equity |  | 001/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Equity |  | 002/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | AFUDC-Equity |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Benefits OH |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Building Service Overhead |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Capitalized A&G |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Cost Adjustments |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Fleet OH - Elec |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | IT Device OH |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212413 | FRRB - SILVERADO 2105 LR 658898 |  | Payroll Taxes OH |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Contracts |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Contractor Activity Charges |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Electric Activity Charge - Type A |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Indirect Labor - Electric |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Indirect Labor - Environmental Land |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Mapping |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Paid Time Off |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Borrowed |  | 001/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Borrowed |  | 002/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Borrowed |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Equity |  | 001/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Equity |  | 002/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | AFUDC-Equity |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Benefits OH |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Building Service Overhead |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Capitalized A&G |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Cost Adjustments |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Fleet OH - Elec |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | IT Device OH |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212414 | FRRB - SILVERADO 2105 LR 131568 |  | Payroll Taxes OH |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Contracts |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Contractor Activity Charges |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Electric Activity Charge - Type A |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Indirect Labor - Electric |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Indirect Labor - Environmental Land |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Mapping |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Paid Time Off |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Borrowed |  | 001/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Borrowed |  | 002/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Borrowed |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Equity |  | 001/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Equity |  | 002/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | AFUDC-Equity |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Benefits OH |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Building Service Overhead |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Capitalized A&G |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Cost Adjustments |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Fleet OH - Elec |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | IT Device OH |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212415 | FRRB - SILVERADO 2105 LR 167360 |  | Payroll Taxes OH |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Contracts |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Contractor Activity Charges |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Electric Activity Charge - Type A |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Indirect Labor - Electric |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Indirect Labor - Environmental Land |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Mapping |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Paid Time Off |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Borrowed |  | 001/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Borrowed |  | 002/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Borrowed |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Equity |  | 001/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Equity |  | 002/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | AFUDC-Equity |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Benefits OH |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Building Service Overhead |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Capitalized A&G |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Cost Adjustments |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Fleet OH - Elec |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | IT Device OH |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212416 | FRRB - CALISTOGA 1102 LR 634 |  | Payroll Taxes OH |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Contracts |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Contractor Activity Charges |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Electric Activity Charge - Type A |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Indirect Labor - Electric |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Indirect Labor - Environmental Land |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Mapping |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Paid Time Off |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Borrowed |  | 001/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Borrowed |  | 002/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Borrowed |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Equity |  | 001/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Equity |  | 002/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | AFUDC-Equity |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Benefits OH |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Building Service Overhead |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Capitalized A&G |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Cost Adjustments |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Fleet OH - Elec |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | IT Device OH |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212417 | FRRB - CALISTOGA 1102 LR 769230 |  | Payroll Taxes OH |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Contracts |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Electric Activity Charge - Type A |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | GAS Activity Charge - Type A |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Electric |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Environmental Land |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Gas |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Mapping |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Paid Time Off |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Material Burden |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 001/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 002/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 001/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 002/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Benefits OH |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Building Service Overhead |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Capitalized A&G |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Cost Adjustments |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Fleet OH - Elec |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Fleet OH - Gas |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | IT Device OH |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Minor Material OH |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212418 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Payroll Taxes OH |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Contracts |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Contracts |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Contractor Activity Charges |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Electric Activity Charge - Type A |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Electric Activity Charge - Type A |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | GAS Activity Charge - Type A |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Electric |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Electric |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Environmental Land |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Environmental Land |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Gas |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Nuclear Gen |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Indirect Labor - Nuclear Gen |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Mapping |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Mapping |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Nuclear Activity Charge - Type A |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Nuclear Activity Charge - Type A |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Paid Time Off |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Paid Time Off |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Material Burden |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Borrowed |  | 001/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Borrowed |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Borrowed |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Equity |  | 001/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Equity |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | AFUDC-Equity |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Benefits OH |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Benefits OH |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Building Service Overhead |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Building Service Overhead |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Capitalized A&G |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Capitalized A&G |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Cost Adjustments |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Fleet OH - Elec |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Fleet OH - Elec |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Fleet OH - Gas |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | IT Device OH |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | IT Device OH |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Minor Material OH |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Payroll Taxes OH |  | 002/2021
35212419 | FRRB - DUNBAR 1101 - LR 416 |  | Payroll Taxes OH |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Contracts |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Contracts |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Contractor Activity Charges |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Electric Activity Charge - Type A |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Electric Activity Charge - Type A |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | GAS Activity Charge - Type A |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Electric |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Electric |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Environmental Land |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Environmental Land |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Gas |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Nuclear Gen |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Indirect Labor - Nuclear Gen |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Mapping |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Mapping |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Nuclear Activity Charge - Type A |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Nuclear Activity Charge - Type A |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Paid Time Off |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Paid Time Off |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Material Burden |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Borrowed |  | 001/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Borrowed |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Borrowed |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Equity |  | 001/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Equity |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | AFUDC-Equity |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Benefits OH |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Benefits OH |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Building Service Overhead |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Building Service Overhead |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Capitalized A&G |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Capitalized A&G |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Cost Adjustments |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Fleet OH - Elec |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Fleet OH - Elec |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Fleet OH - Gas |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | IT Device OH |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | IT Device OH |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Minor Material OH |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Payroll Taxes OH |  | 002/2021
35212460 | FRRB - RINCON 1101 LR 14605 |  | Payroll Taxes OH |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Contracts |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Contracts |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Contractor Activity Charges |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Electric Activity Charge - Type A |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Electric Activity Charge - Type A |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | GAS Activity Charge - Type A |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Electric |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Electric |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Environmental Land |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Environmental Land |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Gas |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Nuclear Gen |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Indirect Labor - Nuclear Gen |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Mapping |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Mapping |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Nuclear Activity Charge - Type A |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Nuclear Activity Charge - Type A |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Paid Time Off |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Paid Time Off |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Material Burden |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Borrowed |  | 001/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Borrowed |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Borrowed |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Equity |  | 001/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Equity |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | AFUDC-Equity |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Benefits OH |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Benefits OH |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Building Service Overhead |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Building Service Overhead |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Capitalized A&G |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Capitalized A&G |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Cost Adjustments |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Fleet OH - Elec |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Fleet OH - Elec |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Fleet OH - Gas |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | IT Device OH |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | IT Device OH |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Minor Material OH |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Payroll Taxes OH |  | 002/2021
35212461 | FRRB - RINCON 1101 LR 663641 |  | Payroll Taxes OH |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Contracts |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Contracts |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Contractor Activity Charges |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Electric Activity Charge - Type A |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Electric Activity Charge - Type A |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | GAS Activity Charge - Type A |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Electric |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Electric |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Environmental Land |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Environmental Land |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Gas |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Nuclear Gen |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Indirect Labor - Nuclear Gen |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Mapping |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Mapping |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Nuclear Activity Charge - Type A |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Nuclear Activity Charge - Type A |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Paid Time Off |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Paid Time Off |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Material Burden |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Borrowed |  | 001/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Borrowed |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Borrowed |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Equity |  | 001/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Equity |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | AFUDC-Equity |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Benefits OH |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Benefits OH |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Building Service Overhead |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Building Service Overhead |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Capitalized A&G |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Capitalized A&G |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Cost Adjustments |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Fleet OH - Elec |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Fleet OH - Elec |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Fleet OH - Gas |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | IT Device OH |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | IT Device OH |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Minor Material OH |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Payroll Taxes OH |  | 002/2021
35212462 | FRRB - RINCON 1103 LR 198 |  | Payroll Taxes OH |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Contracts |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Contracts |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Contractor Activity Charges |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Electric Activity Charge - Type A |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Electric Activity Charge - Type A |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | GAS Activity Charge - Type A |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Electric |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Electric |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Environmental Land |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Environmental Land |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Gas |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Nuclear Gen |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Indirect Labor - Nuclear Gen |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Mapping |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Mapping |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Nuclear Activity Charge - Type A |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Nuclear Activity Charge - Type A |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Paid Time Off |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Paid Time Off |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Material Burden |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Borrowed |  | 001/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Borrowed |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Borrowed |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Equity |  | 001/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Equity |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | AFUDC-Equity |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Benefits OH |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Benefits OH |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Building Service Overhead |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Building Service Overhead |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Capitalized A&G |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Capitalized A&G |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Cost Adjustments |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Fleet OH - Elec |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Fleet OH - Elec |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Fleet OH - Gas |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | IT Device OH |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | IT Device OH |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Minor Material OH |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Payroll Taxes OH |  | 002/2021
35212463 | FRRB - RINCON 1103 LR 474 |  | Payroll Taxes OH |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Contracts |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Electric Activity Charge - Type A |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Indirect Labor - Electric |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Indirect Labor - Environmental Land |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Indirect Labor - IT |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | IT Activity Charge - Type A |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Mapping |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Paid Time Off |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Construction Supplies |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Material Burden |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Tools, First Aid & Safety Supplies |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Borrowed |  | 001/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Borrowed |  | 002/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Borrowed |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Equity |  | 001/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Equity |  | 002/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | AFUDC-Equity |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Benefits OH |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Building Service Overhead |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Capitalized A&G |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Cost Adjustments |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Fleet OH - Elec |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | IT Device OH |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Minor Material OH |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Operation Mgmt & Support - IT |  | 003/2021
35212465 | FRRB - VACAVILLE 1108 LR 38316 |  | Payroll Taxes OH |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Contracts |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Electric Activity Charge - Type A |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Indirect Labor - Electric |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Indirect Labor - Environmental Land |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Indirect Labor - IT |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | IT Activity Charge - Type A |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Mapping |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Paid Time Off |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Construction Supplies |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Material Burden |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Tools, First Aid & Safety Supplies |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Borrowed |  | 001/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Borrowed |  | 002/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Borrowed |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Equity |  | 001/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Equity |  | 002/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | AFUDC-Equity |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Benefits OH |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Building Service Overhead |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Capitalized A&G |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Cost Adjustments |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Fleet OH - Elec |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | IT Device OH |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Minor Material OH |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Operation Mgmt & Support - IT |  | 003/2021
35212466 | FRRB - VACAVILLE 1108 LR 8762 |  | Payroll Taxes OH |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Contracts |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Indirect Labor - Electric |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Mapping |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Paid Time Off |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Borrowed |  | 001/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Borrowed |  | 002/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Borrowed |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Equity |  | 001/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Equity |  | 002/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | AFUDC-Equity |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Benefits OH |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Building Service Overhead |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Capitalized A&G |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Cost Adjustments |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Fleet OH - Elec |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | IT Device OH |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212467 | FRRB - LAURELES 1111 LR 2020 |  | Payroll Taxes OH |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Contracts |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Contractor Activity Charges |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Electric Activity Charge - Type A |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Indirect Labor - Electric |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Indirect Labor - Environmental Land |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Indirect Labor - IT |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | IT Activity Charge - Type A |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Mapping |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Paid Time Off |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Electrical Specialties |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Fabricated Structures |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Material Burden |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Borrowed |  | 001/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Borrowed |  | 002/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Borrowed |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Equity |  | 001/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Equity |  | 002/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | AFUDC-Equity |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Benefits OH |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Building Service Overhead |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Capitalized A&G |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Cost Adjustments |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Fleet OH - Elec |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | IT Device OH |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Minor Material OH |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Operation Mgmt & Support - IT |  | 003/2021
35212472 | FRRB - BIG BASIN 1102 LR5066 |  | Payroll Taxes OH |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Contracts |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Contractor Activity Charges |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Electric Activity Charge - Type A |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Indirect Labor - Electric |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Indirect Labor - Environmental Land |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Indirect Labor - IT |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | IT Activity Charge - Type A |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Mapping |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Paid Time Off |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Electrical Specialties |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Fabricated Structures |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Material Burden |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Borrowed |  | 001/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Borrowed |  | 002/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Borrowed |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Equity |  | 001/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Equity |  | 002/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | AFUDC-Equity |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Benefits OH |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Building Service Overhead |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Capitalized A&G |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Cost Adjustments |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Fleet OH - Elec |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | IT Device OH |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Minor Material OH |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Operation Mgmt & Support - IT |  | 003/2021
35212473 | FRRB - BIG BASIN 1102 LR10254 |  | Payroll Taxes OH |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Contracts |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Contractor Activity Charges |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Electric Activity Charge - Type A |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Indirect Labor - Electric |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Indirect Labor - Environmental Land |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Indirect Labor - IT |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | IT Activity Charge - Type A |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Mapping |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Paid Time Off |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Electrical Specialties |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Fabricated Structures |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Material Burden |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Borrowed |  | 001/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Borrowed |  | 002/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Borrowed |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Equity |  | 001/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Equity |  | 002/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | AFUDC-Equity |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Benefits OH |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Building Service Overhead |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Capitalized A&G |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Cost Adjustments |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Fleet OH - Elec |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | IT Device OH |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Minor Material OH |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Operation Mgmt & Support - IT |  | 003/2021
35212474 | FRRB - BIG BASIN 1102 LR12758 |  | Payroll Taxes OH |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Contracts |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Contractor Activity Charges |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Electric Activity Charge - Type A |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Env & Land Activity Charge - Type A |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Indirect Labor - Electric |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Indirect Labor - Environmental Land |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Indirect Labor - IT |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | IT Activity Charge - Type A |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Mapping |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Paid Time Off |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Electrical Specialties |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Fabricated Structures |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Material Burden |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Borrowed |  | 001/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Borrowed |  | 002/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Borrowed |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Equity |  | 001/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Equity |  | 002/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | AFUDC-Equity |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Benefits OH |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Building Service Overhead |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Capitalized A&G |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Cost Adjustments |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Fleet OH - Elec |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | IT Device OH |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Minor Material OH |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Operation Mgmt & Support - IT |  | 003/2021
35212475 | FRRB - BIG BASIN 1101 CB |  | Payroll Taxes OH |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Contracts |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Contractor Activity Charges |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Electric Activity Charge - Type A |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Indirect Labor - Electric |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Indirect Labor - Environmental Land |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Indirect Labor - IT |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | IT Activity Charge - Type A |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Mapping |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Paid Time Off |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Electrical Specialties |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Fabricated Structures |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Material Burden |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Borrowed |  | 001/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Borrowed |  | 002/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Borrowed |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Equity |  | 001/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Equity |  | 002/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | AFUDC-Equity |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Benefits OH |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Building Service Overhead |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Capitalized A&G |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Cost Adjustments |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Fleet OH - Elec |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | IT Device OH |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Minor Material OH |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Operation Mgmt & Support - IT |  | 003/2021
35212476 | FRRB - BIG BASIN 1101 LR5000 |  | Payroll Taxes OH |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Contracts |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Contractor Activity Charges |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Electric Activity Charge - Type A |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Indirect Labor - Electric |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Indirect Labor - Environmental Land |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Indirect Labor - IT |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | IT Activity Charge - Type A |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Mapping |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Paid Time Off |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Electrical Specialties |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Fabricated Structures |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Material Burden |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Borrowed |  | 001/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Borrowed |  | 002/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Borrowed |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Equity |  | 001/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Equity |  | 002/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | AFUDC-Equity |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Benefits OH |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Building Service Overhead |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Capitalized A&G |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Cost Adjustments |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Fleet OH - Elec |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | IT Device OH |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Minor Material OH |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Operation Mgmt & Support - IT |  | 003/2021
35212477 | FRRB - BIG BASIN 1101 LR10720 |  | Payroll Taxes OH |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Contracts |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Electric Activity Charge - Non-Type A |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Indirect Labor - Electric |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Indirect Labor - Environmental Land |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Mapping |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Paid Time Off |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Material Burden |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Purchasing Card |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Borrowed |  | 001/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Borrowed |  | 002/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Borrowed |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Equity |  | 001/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Equity |  | 002/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | AFUDC-Equity |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Benefits OH |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Building Service Overhead |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Capitalized A&G |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Cost Adjustments |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Fleet OH - Elec |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | IT Device OH |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Minor Material OH |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212478 | FRRB - SWIFT 2110 XR332 |  | Payroll Taxes OH |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Contracts |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Contracts |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Contractor Activity Charges |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Electric Activity Charge - Type A |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Env & Land Activity Charge - Type A |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Env & Land Activity Charge - Type A |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | GAS Activity Charge - Type A |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | GAS Activity Charge - Type A |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Electric |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Electric |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Environmental Land |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Environmental Land |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Gas |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Indirect Labor - Gas |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Mapping |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Mapping |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Paid Time Off |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Paid Time Off |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Construction Supplies |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Fabricated Structures |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Material Burden |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Materials Not Otherwise Classified |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Borrowed |  | 001/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Borrowed |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Borrowed |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Equity |  | 001/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Equity |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | AFUDC-Equity |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Benefits OH |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Benefits OH |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Building Service Overhead |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Building Service Overhead |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Capitalized A&G |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Capitalized A&G |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Cost Adjustments |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Fleet OH - Elec |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Fleet OH - Elec |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Fleet OH - Gas |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Fleet OH - Gas |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | IT Device OH |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | IT Device OH |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Minor Material OH |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Gas |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Operation Mgmt & Support - Gas |  | 003/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Payroll Taxes OH |  | 002/2021
35212479 | FRRB - BIG BEND 1102 CB |  | Payroll Taxes OH |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Contracts |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Contracts |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Contractor Activity Charges |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Electric Activity Charge - Type A |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | GAS Activity Charge - Type A |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | GAS Activity Charge - Type A |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Electric |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Electric |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Environmental Land |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Environmental Land |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Gas |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Indirect Labor - Gas |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Mapping |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Mapping |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Paid Time Off |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Paid Time Off |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Construction Supplies |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Fabricated Structures |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Material Burden |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Materials Not Otherwise Classified |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Borrowed |  | 001/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Borrowed |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Borrowed |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Equity |  | 001/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Equity |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | AFUDC-Equity |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Benefits OH |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Benefits OH |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Building Service Overhead |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Building Service Overhead |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Capitalized A&G |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Capitalized A&G |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Cost Adjustments |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Fleet OH - Elec |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Fleet OH - Elec |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Fleet OH - Gas |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Fleet OH - Gas |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | IT Device OH |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | IT Device OH |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Minor Material OH |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Gas |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Payroll Taxes OH |  | 002/2021
35212480 | FRRB - BIG BEND 1102 LR1972 |  | Payroll Taxes OH |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Contracts |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Contracts |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Contracts |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Contractor Activity Charges |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Electric Activity Charge - Type A |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | GAS Activity Charge - Type A |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | GAS Activity Charge - Type A |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Electric |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Electric |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Electric |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Environmental Land |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Environmental Land |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Gas |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Indirect Labor - Gas |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Mapping |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Mapping |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Mapping |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Paid Time Off |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Paid Time Off |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Paid Time Off |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Construction Supplies |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fabricated Structures |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Material Burden |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Materials Not Otherwise Classified |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Borrowed |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Borrowed |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Borrowed |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Equity |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Equity |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | AFUDC-Equity |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Benefits OH |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Benefits OH |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Benefits OH |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Building Service Overhead |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Building Service Overhead |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Building Service Overhead |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Capitalized A&G |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Capitalized A&G |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Capitalized A&G |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Cost Adjustments |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fleet OH - Elec |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fleet OH - Elec |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fleet OH - Elec |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fleet OH - Gas |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Fleet OH - Gas |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | IT Device OH |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | IT Device OH |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | IT Device OH |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Minor Material OH |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Electric |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Gas |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Payroll Taxes OH |  | 001/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Payroll Taxes OH |  | 002/2021
35212481 | FRRB - WYANDOTTE 1103 LR1508 |  | Payroll Taxes OH |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Contracts |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Contracts |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Contractor Activity Charges |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Electric Activity Charge - Type A |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | GAS Activity Charge - Type A |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | GAS Activity Charge - Type A |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Electric |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Electric |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Environmental Land |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Environmental Land |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Gas |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Indirect Labor - Gas |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Mapping |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Mapping |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Paid Time Off |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Paid Time Off |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Construction Supplies |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Fabricated Structures |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Material Burden |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Materials Not Otherwise Classified |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Borrowed |  | 001/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Borrowed |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Borrowed |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Equity |  | 001/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Equity |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | AFUDC-Equity |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Benefits OH |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Benefits OH |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Building Service Overhead |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Building Service Overhead |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Capitalized A&G |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Capitalized A&G |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Cost Adjustments |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Fleet OH - Elec |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Fleet OH - Elec |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Fleet OH - Gas |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Fleet OH - Gas |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | IT Device OH |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | IT Device OH |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Minor Material OH |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Gas |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Payroll Taxes OH |  | 002/2021
35212483 | FRRB - WYANDOTTE 1103 LR1974 |  | Payroll Taxes OH |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Contracts |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Contracts |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Contractor Activity Charges |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Electric Activity Charge - Type A |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Env & Land Activity Charge - Type A |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Env & Land Activity Charge - Type A |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | GAS Activity Charge - Type A |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | GAS Activity Charge - Type A |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Electric |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Electric |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Environmental Land |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Environmental Land |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Gas |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Indirect Labor - Gas |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Mapping |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Mapping |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Paid Time Off |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Paid Time Off |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Construction Supplies |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Fabricated Structures |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Material Burden |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Materials Not Otherwise Classified |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Borrowed |  | 001/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Borrowed |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Borrowed |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Equity |  | 001/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Equity |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | AFUDC-Equity |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Benefits OH |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Benefits OH |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Building Service Overhead |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Building Service Overhead |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Capitalized A&G |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Capitalized A&G |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Cost Adjustments |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Fleet OH - Elec |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Fleet OH - Elec |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Fleet OH - Gas |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Fleet OH - Gas |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | IT Device OH |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | IT Device OH |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Minor Material OH |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Gas |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Operation Mgmt & Support - Gas |  | 003/2021
35212486 | FRRB - KANAKA 1101 CB |  | Payroll Taxes OH |  | 002/2021
35212486 | FRRB - KANAKA 1101 CB |  | Payroll Taxes OH |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Contracts |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Contracts |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Contractor Activity Charges |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Electric Activity Charge - Type A |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | GAS Activity Charge - Type A |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | GAS Activity Charge - Type A |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Electric |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Electric |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Environmental Land |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Environmental Land |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Gas |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Indirect Labor - Gas |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Mapping |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Mapping |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Paid Time Off |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Paid Time Off |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Construction Supplies |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Fabricated Structures |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Material Burden |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Materials Not Otherwise Classified |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Borrowed |  | 001/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Borrowed |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Borrowed |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Equity |  | 001/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Equity |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | AFUDC-Equity |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Benefits OH |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Benefits OH |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Building Service Overhead |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Building Service Overhead |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Capitalized A&G |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Capitalized A&G |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Cost Adjustments |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Fleet OH - Elec |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Fleet OH - Elec |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Fleet OH - Gas |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Fleet OH - Gas |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | IT Device OH |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | IT Device OH |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Minor Material OH |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Gas |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Payroll Taxes OH |  | 002/2021
35212487 | FRRB - KANAKA 1101 LR1034 |  | Payroll Taxes OH |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Contracts |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Contracts |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Contractor Activity Charges |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Electric Activity Charge - Type A |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | GAS Activity Charge - Type A |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | GAS Activity Charge - Type A |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Electric |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Electric |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Environmental Land |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Environmental Land |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Gas |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Indirect Labor - Gas |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Mapping |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Mapping |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Paid Time Off |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Paid Time Off |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Construction Supplies |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Fabricated Structures |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Material Burden |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Materials Not Otherwise Classified |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Borrowed |  | 001/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Borrowed |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Borrowed |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Equity |  | 001/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Equity |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | AFUDC-Equity |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Benefits OH |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Benefits OH |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Building Service Overhead |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Building Service Overhead |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Capitalized A&G |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Capitalized A&G |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Cost Adjustments |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Fleet OH - Elec |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Fleet OH - Elec |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Fleet OH - Gas |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Fleet OH - Gas |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | IT Device OH |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | IT Device OH |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Minor Material OH |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Gas |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Operation Mgmt & Support - Gas |  | 003/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Payroll Taxes OH |  | 002/2021
35212488 | FRRB - KANAKA 1101 LR1406 |  | Payroll Taxes OH |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Contracts |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Contracts |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Electric Activity Charge - Type A |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Indirect Labor - Electric |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Indirect Labor - Electric |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Mapping |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Mapping |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Paid Time Off |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Paid Time Off |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Borrowed |  | 001/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Borrowed |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Borrowed |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Equity |  | 001/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Equity |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | AFUDC-Equity |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Benefits OH |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Benefits OH |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Building Service Overhead |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Building Service Overhead |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Capitalized A&G |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Capitalized A&G |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Cost Adjustments |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Cost Adjustments |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Fleet OH - Elec |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Fleet OH - Elec |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | IT Device OH |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | IT Device OH |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Payroll Taxes OH |  | 002/2021
35212489 | FRRB - GIRVAN 1101 LR1330 |  | Payroll Taxes OH |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Contracts |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Contracts |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Customer Care Activity Charge - Non-Type |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Electric Activity Charge - Type A |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Indirect Labor - Electric |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Indirect Labor - Electric |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Mapping |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Mapping |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Paid Time Off |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Paid Time Off |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Borrowed |  | 001/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Borrowed |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Borrowed |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Equity |  | 001/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Equity |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | AFUDC-Equity |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Benefits OH |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Benefits OH |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Building Service Overhead |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Building Service Overhead |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Capitalized A&G |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Capitalized A&G |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Cost Adjustments |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Cost Adjustments |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Fleet OH - Elec |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Fleet OH - Elec |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | IT Device OH |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | IT Device OH |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Payroll Taxes OH |  | 002/2021
35212490 | FRRB - GIRVAN 1101 LR323094 |  | Payroll Taxes OH |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Electric Activity Charge - Type A |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Env & Land Activity Charge - Type A |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Indirect Labor - Electric |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Indirect Labor - Environmental Land |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Paid Time Off |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Borrowed |  | 001/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Borrowed |  | 002/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Borrowed |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Equity |  | 001/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Equity |  | 002/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | AFUDC-Equity |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Benefits OH |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Building Service Overhead |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Capitalized A&G |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Cost Adjustments |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Fleet OH - Elec |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | IT Device OH |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Operation Mgmt & Support - Electric |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212491 | FRRB - SAN JOAQUIN #3 1103 LR5100 |  | Payroll Taxes OH |  | 003/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Contracts |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Indirect Labor - Electric |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Indirect Labor - Environmental Land |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Mapping |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Paid Time Off |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Borrowed |  | 001/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Borrowed |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Borrowed |  | 003/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Equity |  | 001/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Equity |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | AFUDC-Equity |  | 003/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Benefits OH |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Building Service Overhead |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Capitalized A&G |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Cost Adjustments |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Cost Adjustments |  | 003/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Fleet OH - Elec |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | IT Device OH |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212492 | FRRB - AUBERRY 1101 R2845 |  | Payroll Taxes OH |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Contracts |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Indirect Labor - Electric |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Indirect Labor - Environmental Land |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Mapping |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Paid Time Off |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Borrowed |  | 001/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Borrowed |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Borrowed |  | 003/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Equity |  | 001/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Equity |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | AFUDC-Equity |  | 003/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Benefits OH |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Building Service Overhead |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Capitalized A&G |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Cost Adjustments |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Cost Adjustments |  | 003/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Fleet OH - Elec |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | IT Device OH |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212493 | FRRB - AUBERRY 1101 R324 |  | Payroll Taxes OH |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Contracts |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Indirect Labor - Electric |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Indirect Labor - Environmental Land |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Mapping |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Paid Time Off |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Borrowed |  | 001/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Borrowed |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Borrowed |  | 003/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Equity |  | 001/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Equity |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | AFUDC-Equity |  | 003/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Benefits OH |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Building Service Overhead |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Capitalized A&G |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Cost Adjustments |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Cost Adjustments |  | 003/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Fleet OH - Elec |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | IT Device OH |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212494 | FRRB - AUBERRY 1101 LR37536 |  | Payroll Taxes OH |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Contracts |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Env & Land Activity Charge - Type A |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Indirect Labor - Electric |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Indirect Labor - Environmental Land |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Mapping |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Paid Time Off |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Borrowed |  | 001/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Borrowed |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Borrowed |  | 003/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Equity |  | 001/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Equity |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | AFUDC-Equity |  | 003/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Benefits OH |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Building Service Overhead |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Capitalized A&G |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Cost Adjustments |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Cost Adjustments |  | 003/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Fleet OH - Elec |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | IT Device OH |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Operation Mgmt & Support - Electric |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35212495 | FRRB - AUBERRY 1101 LR233716 |  | Payroll Taxes OH |  | 002/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Contracts |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Env & Land Activity Charge - Type A |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Indirect Labor - Electric |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Indirect Labor - Environmental Land |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Mapping |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Paid Time Off |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Material Burden |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Purchasing Card |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Borrowed |  | 001/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Borrowed |  | 002/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Borrowed |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Equity |  | 001/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Equity |  | 002/2021
35212496 | FRRB - HB TRINITY COUNTY |  | AFUDC-Equity |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Benefits OH |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Building Service Overhead |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Capitalized A&G |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Cost Adjustments |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Fleet OH - Elec |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | IT Device OH |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Minor Material OH |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Operation Mgmt & Support - Electric |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35212496 | FRRB - HB TRINITY COUNTY |  | Payroll Taxes OH |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Environmental Contract |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Environmental Contract |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Environmental Contract |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Consulting Services - Engineering |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Administration |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Administrative Services - OT |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Administrative Services - OT |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Design Services |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Electric Estimating |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Electric Estimating |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Electric Estimating Doubletime |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Electric Estimating Overtime |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Electric Estimating Overtime |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engineering/Mapping |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engineering/Mapping |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Engineering/Mapping |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Electric |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Electric |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Electric |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Environmental Land |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Environmental Land |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Indirect Labor - Environmental Land |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Land Rights - Misc |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Mapping |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Mapping |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Mapping |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Paid Time Off |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Paid Time Off |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Paid Time Off |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Borrowed |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Borrowed |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Borrowed |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Equity |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Equity |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | AFUDC-Equity |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Benefits OH |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Benefits OH |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Benefits OH |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Building Service Overhead |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Building Service Overhead |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Building Service Overhead |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Capitalized A&G |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Capitalized A&G |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Capitalized A&G |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Fleet OH - Elec |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Fleet OH - Elec |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Fleet OH - Elec |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | IT Device OH |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | IT Device OH |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | IT Device OH |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Lodging |  | 004/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Meals Expense |  | 004/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Electric |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Payroll Taxes OH |  | 001/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Payroll Taxes OH |  | 002/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Payroll Taxes OH |  | 003/2021
35217267 | TITLE: SH - MARIPOSA 2102 LR 241564 |  | Reimbursed Mileage Expense |  | 004/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Environmental Contract |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Environmental Contract |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Environmental Contract |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Consulting Services - Engineering |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Consulting Services - Engineering |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Administration |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Administration |  | 004/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Construction |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Electric Estimating |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engineering/Mapping |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Engineering/Mapping |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Electric |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Electric |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Electric |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Environmental Land |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Environmental Land |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Indirect Labor - Environmental Land |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Land Rights - Misc |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Mapping |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Mapping |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Mapping |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Paid Time Off |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Paid Time Off |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Paid Time Off |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Borrowed |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Borrowed |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Borrowed |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Equity |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Equity |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | AFUDC-Equity |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Benefits OH |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Benefits OH |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Benefits OH |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Building Service Overhead |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Building Service Overhead |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Building Service Overhead |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Capitalized A&G |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Capitalized A&G |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Capitalized A&G |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Fleet OH - Elec |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Fleet OH - Elec |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Fleet OH - Elec |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | IT Device OH |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | IT Device OH |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | IT Device OH |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Payroll Taxes OH |  | 001/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Payroll Taxes OH |  | 002/2021
35217268 | CWSP - BUCKS CREEK 1101 CB PH 1 |  | Payroll Taxes OH |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Environmental Contract |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Environmental Contract |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Electric Estimating |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Electric Estimating |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Electric Estimating Overtime |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Mapping |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Mapping |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Paid Time Off |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Paid Time Off |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Paid Time Off |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Benefits OH |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Benefits OH |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Benefits OH |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Building Service Overhead |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Building Service Overhead |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Building Service Overhead |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Capitalized A&G |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Capitalized A&G |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Capitalized A&G |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | IT Device OH |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | IT Device OH |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | IT Device OH |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35217269 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Environmental Contract |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Environmental Contract |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Consulting Services - Engineering |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Account Services |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Account Services |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Administrative Services - OT |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Administrative Services - OT |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Electric Estimating Overtime |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Electric Estimating Overtime |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engineering/Mapping |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Engineering/Mapping |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Cust Care |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Cust Care |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Electric |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Electric |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Electric |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Environmental Land |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Environmental Land |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Indirect Labor - Environmental Land |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Land Rights - Misc |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Mapping |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Mapping |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Paid Time Off |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Paid Time Off |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Paid Time Off |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Project Management Services |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Borrowed |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Borrowed |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Borrowed |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Equity |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Equity |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | AFUDC-Equity |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Benefits OH |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Benefits OH |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Benefits OH |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Building Service Overhead |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Building Service Overhead |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Building Service Overhead |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Capitalized A&G |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Capitalized A&G |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Capitalized A&G |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Fleet OH - Elec |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Fleet OH - Elec |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Fleet OH - Elec |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | IT Device OH |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | IT Device OH |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | IT Device OH |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Payroll Taxes OH |  | 001/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Payroll Taxes OH |  | 002/2021
35217270 | CWSP - KONOCTI 1102 LR 965078 PH1 |  | Payroll Taxes OH |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Environmental Contract |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Environmental Contract |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Account Services |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating |  | 004/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating Doubletime |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Electric Estimating Overtime |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Mapping |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Mapping |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Paid Time Off |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Paid Time Off |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Paid Time Off |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Benefits OH |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Benefits OH |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Benefits OH |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Building Service Overhead |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Building Service Overhead |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Building Service Overhead |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Capitalized A&G |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Capitalized A&G |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Capitalized A&G |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | IT Device OH |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | IT Device OH |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | IT Device OH |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35217271 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Environmental Contract |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Environmental Contract |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Acquisition - Misc |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Administrative Services - OT |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Electric Estimating |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Mapping |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Mapping |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Paid Time Off |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Paid Time Off |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Paid Time Off |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Benefits OH |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Benefits OH |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Benefits OH |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Building Service Overhead |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Building Service Overhead |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Building Service Overhead |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Capitalized A&G |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Capitalized A&G |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Capitalized A&G |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | IT Device OH |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | IT Device OH |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | IT Device OH |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Land Acquisition Services |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35217272 | CWSP - KESWICK 1101 LR 1586 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Environmental Contract |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Environmental Contract |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Consulting Services - Engineering |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Electric Estimating |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Electric Estimating Overtime |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engineering/Mapping |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engineering/Mapping |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Engineering/Mapping |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Environmental Planning & Permitting-Misc |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Indirect Labor - Electric |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Indirect Labor - Electric |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Indirect Labor - Electric |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Indirect Labor - Environmental Land |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Land Rights - Misc |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Mapping |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Mapping |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Paid Time Off |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Paid Time Off |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Paid Time Off |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Project Management Services |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Project Management Services |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Borrowed |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Borrowed |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Borrowed |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Equity |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Equity |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | AFUDC-Equity |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Benefits OH |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Benefits OH |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Benefits OH |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Building Service Overhead |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Building Service Overhead |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Building Service Overhead |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Capitalized A&G |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Capitalized A&G |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Capitalized A&G |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Fleet OH - Elec |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Fleet OH - Elec |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Fleet OH - Elec |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | IT Device OH |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | IT Device OH |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | IT Device OH |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Operation Mgmt & Support - Electric |  | 003/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Payroll Taxes OH |  | 001/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Payroll Taxes OH |  | 002/2021
35217273 | SH - UPPER LAKE 1101 CB |  | Payroll Taxes OH |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Contracts |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Environmental Contract |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Environmental Contract |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Consulting Services - Engineering |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Consulting Services - Engineering |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Account Services |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Account Services |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Acquisition - Misc |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Administrative Services - Double Time |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Administrative Services - Double Time |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Administrative Services - OT |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Administrative Services - OT |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Administrative Services - OT |  | 004/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Engineering/Mapping |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Engineering/Mapping |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Engineering/Mapping |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Environmental Planning & Permitting-Misc |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Environmental Planning & Permitting-Misc |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Cust Care |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Cust Care |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Electric |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Electric |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Electric |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Environmental Land |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Indirect Labor - Environmental Land |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Land Rights - Misc |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Land Rights - Misc |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Mapping |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Mapping |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Mapping |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Paid Time Off |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Paid Time Off |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Paid Time Off |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Borrowed |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Borrowed |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Borrowed |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Equity |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Equity |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | AFUDC-Equity |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Benefits OH |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Benefits OH |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Benefits OH |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Building Service Overhead |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Building Service Overhead |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Building Service Overhead |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Capitalized A&G |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Capitalized A&G |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Capitalized A&G |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Fleet OH - Elec |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Fleet OH - Elec |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Fleet OH - Elec |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | IT Device OH |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | IT Device OH |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | IT Device OH |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Operation Mgmt & Support - Electric |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Operation Mgmt & Support - Electric |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Operation Mgmt & Support - Electric |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Payroll Taxes OH |  | 001/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Payroll Taxes OH |  | 002/2021
35217274 | FRRB - HMB 1103 655644 PH1.1 SM COUNTY |  | Payroll Taxes OH |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Contracts |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Environmental Contract |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Environmental Contract |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Consulting Services - Engineering |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Consulting Services - Engineering |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Account Services |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Account Services |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Account Services |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Acquisition - Misc |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Administrative Services - Double Time |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Administrative Services - Double Time |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Administrative Services - OT |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Administrative Services - OT |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Administrative Services - OT |  | 004/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Engineering/Mapping |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Engineering/Mapping |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Engineering/Mapping |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Environmental Planning & Permitting-Misc |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Environmental Planning & Permitting-Misc |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Environmental Planning & Permitting-Misc |  | 004/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Cust Care |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Cust Care |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Cust Care |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Electric |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Electric |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Electric |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Environmental Land |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Indirect Labor - Environmental Land |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Land Rights - Misc |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Mapping |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Mapping |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Mapping |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Paid Time Off |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Paid Time Off |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Paid Time Off |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Borrowed |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Borrowed |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Borrowed |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Equity |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Equity |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | AFUDC-Equity |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Benefits OH |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Benefits OH |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Benefits OH |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Building Service Overhead |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Building Service Overhead |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Building Service Overhead |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Capitalized A&G |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Capitalized A&G |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Capitalized A&G |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Fleet OH - Elec |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Fleet OH - Elec |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Fleet OH - Elec |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | IT Device OH |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | IT Device OH |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | IT Device OH |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Operation Mgmt & Support - Electric |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Operation Mgmt & Support - Electric |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Operation Mgmt & Support - Electric |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Payroll Taxes OH |  | 001/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Payroll Taxes OH |  | 002/2021
35217275 | FRRB - HMB 1103 655644 PH2.1 SC COUNTY |  | Payroll Taxes OH |  | 003/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Engineering/Mapping |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Engineering/Mapping |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Indirect Labor - Electric |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Indirect Labor - Electric |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Paid Time Off |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Paid Time Off |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Borrowed |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Borrowed |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Borrowed |  | 003/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Equity |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Equity |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | AFUDC-Equity |  | 003/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Benefits OH |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Benefits OH |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Building Service Overhead |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Building Service Overhead |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Capitalized A&G |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Capitalized A&G |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Fleet OH - Elec |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Fleet OH - Elec |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | IT Device OH |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | IT Device OH |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Payroll Taxes OH |  | 001/2021
35219092 | CWSP - POSO MOUNTAIN 2104CB |  | Payroll Taxes OH |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Environmental Contract |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Traffic Control Contracts |  | 004/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Contractor Consultant |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Acquisition - Misc |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Acquisition - Misc |  | 004/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Administrative Services - OT |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Construction |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Construction Overtime Services |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Design Overtime Services |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Land Rights - Misc |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Land Rights - Misc |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Management Services |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Management Services |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Mapping |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Mapping |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Paid Time Off |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Paid Time Off |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Paid Time Off |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Benefits OH |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Benefits OH |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Benefits OH |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | IT Device OH |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | IT Device OH |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | IT Device OH |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219093 | CWSP - TIDEWATER 210614072 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Environmental Contract |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Acquisition - Misc |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Construction |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Construction Overtime Services |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Land Rights - Misc |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Manage L&EM |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Management Services |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Management Services |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Mapping |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Mapping |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Mapping |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Paid Time Off |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Paid Time Off |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Paid Time Off |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Benefits OH |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Benefits OH |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Benefits OH |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | IT Device OH |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | IT Device OH |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | IT Device OH |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219096 | CWSP - KIRKER 2104442850 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Environmental Contract |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Environmental Contract |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Acquisition - Misc |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Acquisition - Misc |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Administrative Services - OT |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Drafting Services |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Drafting Services |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Drafting Services |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Drafting Services - Overtime |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Drafting Services - Overtime |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Overtime Services |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Design Services |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating |  | 004/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating Doubletime |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating Doubletime |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating Overtime |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating Overtime |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Electric Estimating Overtime |  | 004/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Mapping |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Mapping |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Paid Time Off |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Paid Time Off |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Paid Time Off |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Benefits OH |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Benefits OH |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Benefits OH |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Building Service Overhead |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Building Service Overhead |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Building Service Overhead |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Capitalized A&G |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Capitalized A&G |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Capitalized A&G |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | IT Device OH |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | IT Device OH |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | IT Device OH |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Meals Expense |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219097 | CWSP - COARSEGOLD 2104CB PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Environmental Contract |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Environmental Contract |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Account Services |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Account Services |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Acquisition - Misc |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Administrative Services - OT |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Electric Estimating |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Electric Estimating |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Electric Estimating Doubletime |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Electric Estimating Doubletime |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Cust Care |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Mapping |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Mapping |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Mapping |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Paid Time Off |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Paid Time Off |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Paid Time Off |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Project Management Overtime |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Project Management Services |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Benefits OH |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Benefits OH |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Benefits OH |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | IT Device OH |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | IT Device OH |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | IT Device OH |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219098 | CWSP - MIDDLETOWN 1101118494 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Environmental Contract |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Construction Overtime Services |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Electric Estimating |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Electric Estimating Overtime |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Electric Estimating Overtime |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Mapping |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Mapping |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Mapping |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Paid Time Off |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Paid Time Off |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Paid Time Off |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Benefits OH |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Benefits OH |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Benefits OH |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | IT Device OH |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | IT Device OH |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | IT Device OH |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219099 | CWSP - HIGHLANDS 1102628 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Environmental Contract |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Acquisition - Misc |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Acquisition - Misc |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Acquisition - Misc |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Administrative Services - OT |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Engineering/Mapping Services Overtime |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Mapping |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Mapping |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Paid Time Off |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Paid Time Off |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Paid Time Off |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Benefits OH |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Benefits OH |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Benefits OH |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | IT Device OH |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | IT Device OH |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | IT Device OH |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219260 | CWSP - WYANDOTTE 110932586 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Engineering/Mapping |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Engineering/Mapping |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Indirect Labor - Electric |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Indirect Labor - Electric |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Paid Time Off |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Paid Time Off |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Borrowed |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Borrowed |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Borrowed |  | 003/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Equity |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Equity |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | AFUDC-Equity |  | 003/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Benefits OH |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Benefits OH |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Building Service Overhead |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Building Service Overhead |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Capitalized A&G |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Capitalized A&G |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Fleet OH - Elec |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Fleet OH - Elec |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | IT Device OH |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | IT Device OH |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Operation Mgmt & Support - Electric |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Operation Mgmt & Support - Electric |  | 002/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Payroll Taxes OH |  | 001/2021
35219264 | CWSP - POSO MOUNTAIN 2103CB |  | Payroll Taxes OH |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Environmental Contract |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Consulting Services - Engineering |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Acquisition - Misc |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Electric Estimating |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Indirect Labor - Electric |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Indirect Labor - Electric |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Indirect Labor - Environmental Land |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Land Rights - Misc |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Mapping |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Paid Time Off |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Paid Time Off |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Benefits OH |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Benefits OH |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Building Service Overhead |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Building Service Overhead |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Capitalized A&G |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Capitalized A&G |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Fleet OH - Elec |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Fleet OH - Elec |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | IT Device OH |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | IT Device OH |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219265 | CWSP - CRESTA 1101546650 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Payroll Taxes OH |  | 001/2021
35219265 | CWSP - CRESTA 1101546650 |  | Payroll Taxes OH |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Environmental Contract |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Environmental Contract |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Consulting Services - Engineering |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Consulting Services - Engineering |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Acquisition - Misc |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Acquisition - Misc |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Acquisition - Misc |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Administrative Services - OT |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Administrative Services - OT |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Construction Overtime Services |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Design Drafting Services |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Design Drafting Services |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Design Drafting Services - Overtime |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Design Drafting Services - Overtime |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Drafting Doubletime |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Drafting Doubletime |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating Doubletime |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating Doubletime |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating Overtime |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Electric Estimating Overtime |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Engineering/Mapping |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Engineering/Mapping |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Engineering/Mapping |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Electric |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Electric |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Electric |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Land Rights - Misc |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Land Rights - Misc |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Mapping |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Mapping |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Paid Time Off |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Paid Time Off |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Paid Time Off |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Borrowed |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Borrowed |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Borrowed |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Equity |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Equity |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | AFUDC-Equity |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Benefits OH |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Benefits OH |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Benefits OH |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Building Service Overhead |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Building Service Overhead |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Building Service Overhead |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Capitalized A&G |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Capitalized A&G |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Capitalized A&G |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Fleet OH - Elec |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Fleet OH - Elec |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Fleet OH - Elec |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | IT Device OH |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | IT Device OH |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | IT Device OH |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Payroll Taxes OH |  | 001/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Payroll Taxes OH |  | 002/2021
35219266 | CWSP - MARIPOSA 2102CB PH 1 |  | Payroll Taxes OH |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Environmental Contract |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Consulting Services - Engineering |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Consulting Services - Engineering |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Design Services |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Engineering/Mapping |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Engineering/Mapping |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Engineering/Mapping |  | 004/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Indirect Labor - Electric |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Indirect Labor - Electric |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Indirect Labor - Electric |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Mapping |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Mapping |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Paid Time Off |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Paid Time Off |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Paid Time Off |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Borrowed |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Borrowed |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Borrowed |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Equity |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Equity |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | AFUDC-Equity |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Benefits OH |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Benefits OH |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Benefits OH |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Building Service Overhead |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Building Service Overhead |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Building Service Overhead |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Capitalized A&G |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Capitalized A&G |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Capitalized A&G |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Fleet OH - Elec |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Fleet OH - Elec |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Fleet OH - Elec |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | IT Device OH |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | IT Device OH |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | IT Device OH |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Payroll Taxes OH |  | 001/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Payroll Taxes OH |  | 002/2021
35219267 | CWSP - MARIPOSA 2102440236 PH1 |  | Payroll Taxes OH |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Contracts |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Environmental Contract |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Environmental Contract |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Consulting Services - Engineering |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Consulting Services - Engineering |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Consulting Services - Engineering |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Consulting Services - Environmental Perm |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Acquisition - Misc |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Acquisition - Misc |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Acquisition - Misc |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Administration |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Administrative Services - OT |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Administrative Services - OT |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Construction Overtime Services |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Design Services |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Design Services |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Design Services |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating Doubletime |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating Doubletime |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating Overtime |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Electric Estimating Overtime |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Engineering/Mapping |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Engineering/Mapping |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Electric |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Electric |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Electric |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Land Rights - Misc |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Mapping |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Mapping |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Mapping |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Paid Time Off |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Paid Time Off |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Paid Time Off |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Borrowed |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Borrowed |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Borrowed |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Equity |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Equity |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | AFUDC-Equity |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Benefits OH |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Benefits OH |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Benefits OH |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Building Service Overhead |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Building Service Overhead |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Building Service Overhead |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Capitalized A&G |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Capitalized A&G |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Capitalized A&G |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Fleet OH - Elec |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Fleet OH - Elec |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Fleet OH - Elec |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | IT Device OH |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | IT Device OH |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | IT Device OH |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Payroll Taxes OH |  | 001/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Payroll Taxes OH |  | 002/2021
35219268 | CWSP - MARIPOSA 210197142 PH 1 |  | Payroll Taxes OH |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Environmental Contract |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Consulting Services - Engineering |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Consulting Services - Engineering |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Administration |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Design Drafting Services |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engineering/Mapping |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engineering/Mapping |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engineering/Mapping |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Engineering/Mapping Services Overtime |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Indirect Labor - Electric |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Indirect Labor - Electric |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Indirect Labor - Electric |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Indirect Labor - Environmental Land |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Indirect Labor - Environmental Land |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Mapping |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Mapping |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Paid Time Off |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Paid Time Off |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Paid Time Off |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Borrowed |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Borrowed |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Borrowed |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Equity |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Equity |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | AFUDC-Equity |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Benefits OH |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Benefits OH |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Benefits OH |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Building Service Overhead |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Building Service Overhead |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Building Service Overhead |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Capitalized A&G |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Capitalized A&G |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Capitalized A&G |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Fleet OH - Elec |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Fleet OH - Elec |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Fleet OH - Elec |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | IT Device OH |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | IT Device OH |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | IT Device OH |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Payroll Taxes OH |  | 001/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Payroll Taxes OH |  | 002/2021
35219269 | CWSP - VACA DIXON 110540092 |  | Payroll Taxes OH |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Environmental Contract |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Consulting Services - Engineering |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Consulting Services - Engineering |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Account Services |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Electric Estimating Overtime |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Engineering/Mapping |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Engineering/Mapping |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Engineering/Mapping |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Indirect Labor - Cust Care |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Indirect Labor - Electric |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Indirect Labor - Electric |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Indirect Labor - Electric |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Indirect Labor - Environmental Land |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Land Rights - Misc |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Mapping |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Mapping |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Paid Time Off |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Paid Time Off |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Paid Time Off |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Project Management Overtime |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Project Management Services |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Borrowed |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Borrowed |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Borrowed |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Equity |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Equity |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | AFUDC-Equity |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Benefits OH |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Benefits OH |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Benefits OH |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Building Service Overhead |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Building Service Overhead |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Building Service Overhead |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Capitalized A&G |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Capitalized A&G |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Capitalized A&G |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Fleet OH - Elec |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Fleet OH - Elec |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Fleet OH - Elec |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | IT Device OH |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | IT Device OH |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | IT Device OH |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Payroll Taxes OH |  | 001/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Payroll Taxes OH |  | 002/2021
35219272 | CWSP - MIDDLETOWN 1101481876 |  | Payroll Taxes OH |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Contracts |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Environmental Contract |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Consulting Services - Engineering |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Account Services |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Acquisition - Misc |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Acquisition - Misc |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Construction |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Construction |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Electric Estimating |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Engineering/Mapping |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Engineering/Mapping |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Cust Care |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Electric |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Electric |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Electric |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Environmental Land |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Environmental Land |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Indirect Labor - Environmental Land |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Land Rights - Misc |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Land Rights - Misc |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Mapping |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Mapping |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Paid Time Off |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Paid Time Off |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Paid Time Off |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Borrowed |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Borrowed |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Borrowed |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Equity |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Equity |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | AFUDC-Equity |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Benefits OH |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Benefits OH |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Benefits OH |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Building Service Overhead |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Building Service Overhead |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Building Service Overhead |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Capitalized A&G |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Capitalized A&G |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Capitalized A&G |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Fleet OH - Elec |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Fleet OH - Elec |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Fleet OH - Elec |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | IT Device OH |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | IT Device OH |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | IT Device OH |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219273 | CWSP - VOLTA 110149742 |  | Payroll Taxes OH |  | 001/2021
35219273 | CWSP - VOLTA 110149742 |  | Payroll Taxes OH |  | 002/2021
35219273 | CWSP - VOLTA 110149742 |  | Payroll Taxes OH |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Contracts |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Environmental Contract |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Consulting Services - Engineering |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Consulting Services - Engineering |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Account Services |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Administration |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Analyst Services |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Construction |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Engineering/Mapping |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Engineering/Mapping |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Engineering/Mapping |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Cust Care |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Electric |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Electric |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Electric |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Environmental Land |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Indirect Labor - Environmental Land |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Land Rights - Misc |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Mapping |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Mapping |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Mapping |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Paid Time Off |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Paid Time Off |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Paid Time Off |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Vegetation Management - Misc |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Benefits OH |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Benefits OH |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Benefits OH |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Building Service Overhead |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Building Service Overhead |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Building Service Overhead |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Capitalized A&G |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Capitalized A&G |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Capitalized A&G |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Fleet OH - Elec |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Fleet OH - Elec |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Fleet OH - Elec |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | IT Device OH |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | IT Device OH |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | IT Device OH |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Payroll Taxes OH |  | 001/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Payroll Taxes OH |  | 002/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Payroll Taxes OH |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Permits/Fees |  | 003/2021
35219275 | CWSP - PUTAH CREEK 110246012 |  | Reimbursed Mileage Expense |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Environmental Contract |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Consulting Services - Engineering |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Acquisition - Misc |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Construction Overtime Services |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engineering/Mapping |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Mapping |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Mapping |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Paid Time Off |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Paid Time Off |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Paid Time Off |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Benefits OH |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Benefits OH |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Benefits OH |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | IT Device OH |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | IT Device OH |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | IT Device OH |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219276 | CWSP - VACAVILLE 11046542 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Environmental Contract |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Consulting Services - Engineering |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Account Services |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Electric Estimating |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Engineering/Mapping |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Engineering/Mapping |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Land Rights - Misc |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Mapping |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Mapping |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Paid Time Off |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Paid Time Off |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Paid Time Off |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Project Management Services |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Equity |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Equity |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | AFUDC-Equity |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Benefits OH |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Benefits OH |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Benefits OH |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Building Service Overhead |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Building Service Overhead |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Building Service Overhead |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Capitalized A&G |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Capitalized A&G |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Capitalized A&G |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | IT Device OH |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | IT Device OH |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | IT Device OH |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35219280 | CWSP - POTTER VALLEY PH 110564118 PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Environmental Contract |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Consulting Services - Engineering |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Consulting Services - Engineering |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Design Overtime Services |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Design Services |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Design Services Double Time |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Electric Estimating |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Engineering Services - OT |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Electric |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Land Rights - Misc |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Mapping |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Mapping |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Paid Time Off |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Paid Time Off |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Paid Time Off |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Equity |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Equity |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | AFUDC-Equity |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Benefits OH |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Benefits OH |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Benefits OH |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Building Service Overhead |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Building Service Overhead |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Building Service Overhead |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Capitalized A&G |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Capitalized A&G |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Capitalized A&G |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Fleet OH - Elec |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Fleet OH - Elec |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | IT Device OH |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | IT Device OH |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | IT Device OH |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Payroll Taxes OH |  | 001/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35219281 | CWSP - MOUNTAIN QUARRIES 21016953 PH1.1 |  | Payroll Taxes OH |  | 003/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Environmental Contract |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Consulting Services - Engineering |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engineering/Mapping |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Electric |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Electric |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Environmental Land |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Land Rights - Misc |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Management Services |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Mapping |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Paid Time Off |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Paid Time Off |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Benefits OH |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Benefits OH |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Building Service Overhead |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Building Service Overhead |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Canceled Capital Order |  | 003/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Capitalized A&G |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Capitalized A&G |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Fleet OH - Elec |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Fleet OH - Elec |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | IT Device OH |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | IT Device OH |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Electric |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Electric |  | 002/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Payroll Taxes OH |  | 001/2021
35219282 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Payroll Taxes OH |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Environmental Contract |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Consulting Services - Engineering |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Administrative Services - OT |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engineering/Mapping |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Engineering/Mapping |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Electric |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Electric |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Indirect Labor - Environmental Land |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Land Rights - Misc |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Manage L&EM |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Management Services |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Mapping |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Paid Time Off |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Paid Time Off |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Benefits OH |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Benefits OH |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Building Service Overhead |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Building Service Overhead |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Canceled Capital Order |  | 003/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Capitalized A&G |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Capitalized A&G |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Fleet OH - Elec |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Fleet OH - Elec |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | IT Device OH |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | IT Device OH |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Electric |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Electric |  | 002/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Payroll Taxes OH |  | 001/2021
35219283 | *CANC*CWSP - NORTH DUBLIN 2101 CB *CANC |  | Payroll Taxes OH |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Environmental Contract |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Environmental Contract |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Account Services |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Construction |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Design Drafting Services |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Design Drafting Services - Overtime |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Drafting Doubletime |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Engineering/Mapping |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Cust Care |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Land Rights - Misc |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Land Rights - Misc |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Manage L&EM |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Management Services |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Mapping |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Mapping |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Paid Time Off |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Paid Time Off |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Paid Time Off |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Equity |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Equity |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | AFUDC-Equity |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Benefits OH |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Benefits OH |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Benefits OH |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Building Service Overhead |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Building Service Overhead |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Building Service Overhead |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Capitalized A&G |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Capitalized A&G |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Capitalized A&G |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Fleet OH - Elec |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | IT Device OH |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | IT Device OH |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | IT Device OH |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Payroll Taxes OH |  | 001/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35219286 | CWSP - DESCHUTES 11049718 PH1.1 |  | Payroll Taxes OH |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Environmental Contract |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Consulting Services - Engineering |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engineering/Mapping |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engineering/Mapping |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Engineering/Mapping Services Overtime |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Indirect Labor - Electric |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Indirect Labor - Electric |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Indirect Labor - Environmental Land |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Land Rights - Misc |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Management Services |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Mapping |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Mapping |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Paid Time Off |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Paid Time Off |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Borrowed |  | 001/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Borrowed |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Borrowed |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Equity |  | 001/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Equity |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | AFUDC-Equity |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Benefits OH |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Benefits OH |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Building Service Overhead |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Building Service Overhead |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Capitalized A&G |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Capitalized A&G |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Fleet OH - Elec |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Fleet OH - Elec |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | IT Device OH |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | IT Device OH |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Payroll Taxes OH |  | 002/2021
35219287 | CWSP - OREGON TRAIL 110335002 PHASE 6 |  | Payroll Taxes OH |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 001/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Environmental Contract |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Consulting Services - Engineering |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Construction Overtime Services |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engineering/Mapping |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Management Services |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Mapping |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Mapping |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Paid Time Off |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Paid Time Off |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Borrowed |  | 001/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Equity |  | 001/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Equity |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | AFUDC-Equity |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Benefits OH |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Benefits OH |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Building Service Overhead |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Building Service Overhead |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Capitalized A&G |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Capitalized A&G |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Fleet OH - Elec |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | IT Device OH |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | IT Device OH |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35219289 | CWSP - OREGON TRAIL 110335002 PH1.1 |  | Payroll Taxes OH |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Contract |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Contract |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Consulting Services - Engineering |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Consulting Services - Engineering |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Account Services |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Analyst Services |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Construction |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engineering/Mapping |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engineering/Mapping |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engineering/Mapping |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Engineering/Mapping Services Overtime |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Cust Care |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Electric |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Electric |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Electric |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Environmental Land |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Environmental Land |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Indirect Labor - Environmental Land |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Land Rights - Misc |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Land Rights - Misc |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Mapping |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Mapping |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Paid Time Off |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Paid Time Off |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Paid Time Off |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Benefits OH |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Benefits OH |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Benefits OH |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Building Service Overhead |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Building Service Overhead |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Building Service Overhead |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Capitalized A&G |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Capitalized A&G |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Capitalized A&G |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Fleet OH - Elec |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Fleet OH - Elec |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Fleet OH - Elec |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | IT Device OH |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | IT Device OH |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | IT Device OH |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Payroll Taxes OH |  | 001/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Payroll Taxes OH |  | 002/2021
35219291 | CWSP - VACA DIXON 1101126774 |  | Payroll Taxes OH |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Environmental Contract |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Consulting Services - Engineering |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Design Overtime Services |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Design Services |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Design Services Double Time |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Engineering/Mapping Services Overtime |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Indirect Labor - Electric |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Indirect Labor - Electric |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Indirect Labor - Environmental Land |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Indirect Labor - Environmental Land |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Land Rights - Misc |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Mapping |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Paid Time Off |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Paid Time Off |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Paid Time Off |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Benefits OH |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Benefits OH |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Benefits OH |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Building Service Overhead |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Building Service Overhead |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Building Service Overhead |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Capitalized A&G |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Capitalized A&G |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Capitalized A&G |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Fleet OH - Elec |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Fleet OH - Elec |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | IT Device OH |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | IT Device OH |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | IT Device OH |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Payroll Taxes OH |  | 001/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Payroll Taxes OH |  | 002/2021
35219542 | PSPS - ESKATON VILLAGE - PLACERVILLE 111 |  | Payroll Taxes OH |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Environmental Contract |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Consulting Services - Engineering |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Construction Overtime Services |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Design Overtime Services |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Electric Estimating Overtime |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Engineering/Mapping Services Overtime |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Environmental Planning & Permitting-Misc |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Indirect Labor - Electric |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Indirect Labor - Electric |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Indirect Labor - Electric |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Indirect Labor - Environmental Land |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Indirect Labor - Environmental Land |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Land Rights - Misc |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Mapping |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Mapping |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Paid Time Off |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Paid Time Off |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Paid Time Off |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Benefits OH |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Benefits OH |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Benefits OH |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Building Service Overhead |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Building Service Overhead |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Building Service Overhead |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Capitalized A&G |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Capitalized A&G |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Capitalized A&G |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Fleet OH - Elec |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Fleet OH - Elec |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Fleet OH - Elec |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | IT Device OH |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | IT Device OH |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | IT Device OH |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Operation Mgmt & Support - Electric |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Operation Mgmt & Support - Electric |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Operation Mgmt & Support - Electric |  | 003/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Payroll Taxes OH |  | 001/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Payroll Taxes OH |  | 002/2021
35219543 | PSPS - WEST MAIN ST / RESERVOIR ST - PLA |  | Payroll Taxes OH |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Environmental Contract |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Consulting Services - Engineering |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Engineering/Mapping |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Indirect Labor - Electric |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Indirect Labor - Electric |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Indirect Labor - Environmental Land |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Land Rights - Misc |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Mapping |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Mapping |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Paid Time Off |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Paid Time Off |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | AFUDC-Borrowed |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | AFUDC-Borrowed |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | AFUDC-Equity |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | AFUDC-Equity |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Benefits OH |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Benefits OH |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Building Service Overhead |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Building Service Overhead |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Capitalized A&G |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Capitalized A&G |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Fleet OH - Elec |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Fleet OH - Elec |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | IT Device OH |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | IT Device OH |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Payroll Taxes OH |  | 002/2021
35219587 | CWSP - MARIPOSA 2102440236 PH2 |  | Payroll Taxes OH |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Environmental Contract |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Consulting Services - Engineering |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Engineering/Mapping |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Indirect Labor - Electric |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Indirect Labor - Electric |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Indirect Labor - Environmental Land |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Mapping |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Mapping |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Paid Time Off |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Paid Time Off |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | AFUDC-Borrowed |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | AFUDC-Borrowed |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | AFUDC-Equity |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | AFUDC-Equity |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Benefits OH |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Benefits OH |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Building Service Overhead |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Building Service Overhead |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Capitalized A&G |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Capitalized A&G |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Fleet OH - Elec |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Fleet OH - Elec |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | IT Device OH |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | IT Device OH |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Payroll Taxes OH |  | 002/2021
35219588 | CWSP - MARIPOSA 2102440236 PH3 |  | Payroll Taxes OH |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Environmental Contract |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Consulting Services - Engineering |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Consulting Services - Engineering |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Consulting Services - Engineering |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Account Services |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Acquisition - Misc |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Administrative Services - OT |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engineering Services - OT |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engineering/Mapping |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engineering/Mapping |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Engineering/Mapping |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Cust Care |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Electric |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Electric |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Electric |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Environmental Land |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Indirect Labor - Environmental Land |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Land Rights - Misc |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Mapping |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Mapping |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Mapping |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Paid Time Off |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Paid Time Off |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Paid Time Off |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Borrowed |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Borrowed |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Borrowed |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Equity |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Equity |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | AFUDC-Equity |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Benefits OH |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Benefits OH |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Benefits OH |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Building Service Overhead |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Building Service Overhead |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Building Service Overhead |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Capitalized A&G |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Capitalized A&G |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Capitalized A&G |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Fleet OH - Elec |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Fleet OH - Elec |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Fleet OH - Elec |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | IT Device OH |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | IT Device OH |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | IT Device OH |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Operation Mgmt & Support - Electric |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Payroll Taxes OH |  | 001/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Payroll Taxes OH |  | 002/2021
35219589 | CWSP - WILDWOOD 11011454 |  | Payroll Taxes OH |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Environmental Contract |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Consulting Services - Engineering |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Consulting Services - Engineering |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Engineering/Mapping |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Indirect Labor - Electric |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Indirect Labor - Electric |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Indirect Labor - Environmental Land |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Land Rights - Misc |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Mapping |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Mapping |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Paid Time Off |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Paid Time Off |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | AFUDC-Borrowed |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | AFUDC-Borrowed |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | AFUDC-Equity |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | AFUDC-Equity |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Benefits OH |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Benefits OH |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Building Service Overhead |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Building Service Overhead |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Capitalized A&G |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Capitalized A&G |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Fleet OH - Elec |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Fleet OH - Elec |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | IT Device OH |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | IT Device OH |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Payroll Taxes OH |  | 002/2021
35219590 | CWSP - VACA DIXON 1105965390 |  | Payroll Taxes OH |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Environmental Contract |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Consulting Services - Engineering |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Consulting Services - Engineering |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Construction Overtime Services |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Design Drafting Services |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Design Drafting Services |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Design Drafting Services - Overtime |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Engineering/Mapping |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Indirect Labor - Electric |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Indirect Labor - Electric |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Indirect Labor - Gas |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Mapping |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Mapping |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Paid Time Off |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Paid Time Off |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | AFUDC-Borrowed |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | AFUDC-Borrowed |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | AFUDC-Equity |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | AFUDC-Equity |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Benefits OH |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Benefits OH |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Building Service Overhead |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Building Service Overhead |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Capitalized A&G |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Capitalized A&G |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Fleet OH - Elec |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Fleet OH - Elec |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Fleet OH - Gas |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | IT Device OH |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | IT Device OH |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Operation Mgmt & Support - Electric |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Operation Mgmt & Support - Electric |  | 003/2021
35219591 | CWSP - OLETA 1101754718 |  | Operation Mgmt & Support - Gas |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Payroll Taxes OH |  | 002/2021
35219591 | CWSP - OLETA 1101754718 |  | Payroll Taxes OH |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Environmental Contract |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Environmental Contract |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Consulting Services - Engineering |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Account Services |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Administrative Services - OT |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Design Drafting Services - Overtime |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Electric Estimating |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Electric Estimating Overtime |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Engineering/Mapping |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Engineering/Mapping |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Engineering/Mapping |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Cust Care |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Electric |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Electric |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Mapping |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Mapping |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Paid Time Off |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Paid Time Off |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Paid Time Off |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Borrowed |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Equity |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Equity |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | AFUDC-Equity |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Benefits OH |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Benefits OH |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Benefits OH |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Building Service Overhead |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Building Service Overhead |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Building Service Overhead |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Capitalized A&G |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Capitalized A&G |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Capitalized A&G |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Fleet OH - Elec |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Fleet OH - Elec |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Fleet OH - Elec |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | IT Device OH |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | IT Device OH |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | IT Device OH |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Payroll Taxes OH |  | 001/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Payroll Taxes OH |  | 002/2021
35220895 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 |  | Payroll Taxes OH |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Environmental Contract |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Consulting Services - Engineering |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Construction Overtime Services |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Electric Estimating |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Electric Estimating Overtime |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Engineering/Mapping |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Engineering/Mapping |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Indirect Labor - Electric |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Indirect Labor - Electric |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Indirect Labor - Electric |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Mapping |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Mapping |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Paid Time Off |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Paid Time Off |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Paid Time Off |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Borrowed |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Borrowed |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Borrowed |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Equity |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Equity |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | AFUDC-Equity |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Benefits OH |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Benefits OH |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Benefits OH |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Building Service Overhead |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Building Service Overhead |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Building Service Overhead |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Capitalized A&G |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Capitalized A&G |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Capitalized A&G |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Fleet OH - Elec |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Fleet OH - Elec |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Fleet OH - Elec |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | IT Device OH |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | IT Device OH |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | IT Device OH |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Payroll Taxes OH |  | 001/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Payroll Taxes OH |  | 002/2021
35220896 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 |  | Payroll Taxes OH |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Account Services |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Account Services |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Account Services |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Engineering/Mapping |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Engineering/Mapping |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Engineering/Mapping |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Cust Care |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Cust Care |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Cust Care |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Electric |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Electric |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Indirect Labor - Electric |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Paid Time Off |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Paid Time Off |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Paid Time Off |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Borrowed |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Borrowed |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Borrowed |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Equity |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Equity |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | AFUDC-Equity |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Benefits OH |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Benefits OH |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Benefits OH |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Building Service Overhead |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Building Service Overhead |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Building Service Overhead |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Capitalized A&G |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Capitalized A&G |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Capitalized A&G |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Fleet OH - Elec |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Fleet OH - Elec |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Fleet OH - Elec |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | IT Device OH |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | IT Device OH |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | IT Device OH |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Operation Mgmt & Support - Electric |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Operation Mgmt & Support - Electric |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Operation Mgmt & Support - Electric |  | 003/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Payroll Taxes OH |  | 001/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Payroll Taxes OH |  | 002/2021
35220936 | FRRB - HMB 1103 6012 - PH1 BUTANO |  | Payroll Taxes OH |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Environmental Contract |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Environmental Contract |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Consulting Services - Engineering |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Account Services |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Construction Overtime Services |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Electric Estimating |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Electric Estimating Overtime |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Engineering/Mapping |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Engineering/Mapping |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Cust Care |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Electric |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Electric |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Electric |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Environmental Land |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Indirect Labor - Environmental Land |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Mapping |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Mapping |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Paid Time Off |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Paid Time Off |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Paid Time Off |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Borrowed |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Borrowed |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Borrowed |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Equity |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Equity |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | AFUDC-Equity |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Benefits OH |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Benefits OH |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Benefits OH |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Building Service Overhead |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Building Service Overhead |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Building Service Overhead |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Capitalized A&G |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Capitalized A&G |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Capitalized A&G |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Fleet OH - Elec |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Fleet OH - Elec |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Fleet OH - Elec |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | IT Device OH |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | IT Device OH |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | IT Device OH |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Payroll Taxes OH |  | 001/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Payroll Taxes OH |  | 002/2021
35222045 | SH - MIDDLTOWN 1103 - LR 830 PH4 |  | Payroll Taxes OH |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Environmental Contract |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Consulting Services - Engineering |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Acquisition - Misc |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Design Services |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Engineering/Mapping |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Engineering/Mapping |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Engineering/Mapping |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Environmental Planning & Permitting-Misc |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Indirect Labor - Electric |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Indirect Labor - Electric |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Indirect Labor - Electric |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Indirect Labor - Environmental Land |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Management Services |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Management Services |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Management Services |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Mapping |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Paid Time Off |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Paid Time Off |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Paid Time Off |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Borrowed |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Borrowed |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Borrowed |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Equity |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Equity |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | AFUDC-Equity |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Benefits OH |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Benefits OH |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Benefits OH |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Building Service Overhead |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Building Service Overhead |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Building Service Overhead |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Capitalized A&G |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Capitalized A&G |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Capitalized A&G |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Fleet OH - Elec |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Fleet OH - Elec |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Fleet OH - Elec |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | IT Device OH |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | IT Device OH |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | IT Device OH |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Operation Mgmt & Support - Electric |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Operation Mgmt & Support - Electric |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Operation Mgmt & Support - Electric |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Payroll Taxes OH |  | 001/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Payroll Taxes OH |  | 002/2021
35222235 | REMG 631 - DUNLAP 1102, UC BERKELEY WHIT |  | Payroll Taxes OH |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Design Drafting Services |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Design Drafting Services |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Design Drafting Services - Overtime |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Design Drafting Services - Overtime |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Electric Estimating |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Electric Estimating |  | 004/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Electric Estimating Overtime |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Engineering/Mapping |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Engineering/Mapping |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Environmental Services |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Indirect Labor - Electric |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Indirect Labor - Electric |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Indirect Labor - Environmental Land |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Land Rights - Misc |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Paid Time Off |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Paid Time Off |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Project Management Services |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Project Management Services |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | AFUDC-Borrowed |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | AFUDC-Borrowed |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | AFUDC-Equity |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | AFUDC-Equity |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Benefits OH |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Benefits OH |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Building Service Overhead |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Building Service Overhead |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Capitalized A&G |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Capitalized A&G |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Fleet OH - Elec |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Fleet OH - Elec |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | IT Device OH |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | IT Device OH |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Payroll Taxes OH |  | 002/2021
35223027 | ECOP - SILVERADO 2104 - H05 - LR726 PH 4 |  | Payroll Taxes OH |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Consulting Services - Engineering |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Account Services |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Design Drafting Services |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Electric Estimating |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Electric Estimating |  | 004/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Electric Estimating Overtime |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Electric Estimating Overtime |  | 004/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Engineering/Mapping |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Indirect Labor - Cust Care |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Indirect Labor - Electric |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Indirect Labor - Electric |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Indirect Labor - Environmental Land |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Mapping |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Paid Time Off |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Paid Time Off |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Project Management Overtime |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Project Management Overtime |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | AFUDC-Borrowed |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | AFUDC-Borrowed |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | AFUDC-Equity |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | AFUDC-Equity |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Benefits OH |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Benefits OH |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Building Service Overhead |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Building Service Overhead |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Capitalized A&G |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Capitalized A&G |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Fleet OH - Elec |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Fleet OH - Elec |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | IT Device OH |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | IT Device OH |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Payroll Taxes OH |  | 002/2021
35223028 | ECOP - SILVERADO 2104 - H05 - LR726 PH 5 |  | Payroll Taxes OH |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Environmental Contract |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Environmental Contract |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Consulting Services - Engineering |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Administrative Services - OT |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Administrative Services - OT |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Engineering Services - OT |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Engineering/Mapping |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Engineering/Mapping |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Engineering/Mapping Services Overtime |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Environmental Planning & Permitting-Misc |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Indirect Labor - Electric |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Indirect Labor - Electric |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Indirect Labor - Electric |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Indirect Labor - Environmental Land |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Indirect Labor - Environmental Land |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Land Rights - Misc |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Mapping |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Mapping |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Paid Time Off |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Paid Time Off |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Paid Time Off |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Borrowed |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Borrowed |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Borrowed |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Equity |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Equity |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | AFUDC-Equity |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Benefits OH |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Benefits OH |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Benefits OH |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Building Service Overhead |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Building Service Overhead |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Building Service Overhead |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Capitalized A&G |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Capitalized A&G |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Capitalized A&G |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Fleet OH - Elec |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Fleet OH - Elec |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Fleet OH - Elec |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | IT Device OH |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | IT Device OH |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | IT Device OH |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Lodging |  | 004/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Meals Expense |  | 004/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Operation Mgmt & Support - Electric |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Operation Mgmt & Support - Electric |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Operation Mgmt & Support - Electric |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Payroll Taxes OH |  | 001/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Payroll Taxes OH |  | 002/2021
35223030 | PSPS - BANGOR 1101 CB - MICROGRID |  | Payroll Taxes OH |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Environmental Contract |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Consulting Services - Engineering |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Construction Overtime Services |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Design Overtime Services |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Design Services |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Electric Estimating |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Engineering/Mapping |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Engineering/Mapping |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Indirect Labor - Electric |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Indirect Labor - Electric |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Indirect Labor - Electric |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Indirect Labor - Environmental Land |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Indirect Labor - Environmental Land |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Land Rights - Misc |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Mapping |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Mapping |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Paid Time Off |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Paid Time Off |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Paid Time Off |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Borrowed |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Borrowed |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Borrowed |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Equity |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Equity |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | AFUDC-Equity |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Benefits OH |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Benefits OH |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Benefits OH |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Building Service Overhead |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Building Service Overhead |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Building Service Overhead |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Capitalized A&G |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Capitalized A&G |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Capitalized A&G |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Fleet OH - Elec |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Fleet OH - Elec |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Fleet OH - Elec |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | IT Device OH |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | IT Device OH |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | IT Device OH |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Operation Mgmt & Support - Electric |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Operation Mgmt & Support - Electric |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Operation Mgmt & Support - Electric |  | 003/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Payroll Taxes OH |  | 001/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Payroll Taxes OH |  | 002/2021
35223032 | PSPS - MOUNTAIN QUARRIES 2101 - COOL |  | Payroll Taxes OH |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Environmental Contract |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Consulting Services - Engineering |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Account Services |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Electric Estimating |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Engineering Services - OT |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Engineering/Mapping |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Engineering/Mapping Services Overtime |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Environmental Planning & Permitting-Misc |  | 004/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Cust Care |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Electric |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Electric |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Environmental Land |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Environmental Land |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Indirect Labor - Environmental Land |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Land Rights - Misc |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Land Rights - Misc |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Mapping |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Paid Time Off |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Paid Time Off |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Paid Time Off |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Borrowed |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Borrowed |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Borrowed |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Equity |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Equity |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | AFUDC-Equity |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Benefits OH |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Benefits OH |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Benefits OH |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Building Service Overhead |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Building Service Overhead |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Building Service Overhead |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Capitalized A&G |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Capitalized A&G |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Capitalized A&G |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Fleet OH - Elec |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Fleet OH - Elec |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | IT Device OH |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | IT Device OH |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | IT Device OH |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Operation Mgmt & Support - Electric |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Operation Mgmt & Support - Electric |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Payroll Taxes OH |  | 001/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Payroll Taxes OH |  | 002/2021
35223036 | PSPS - BRUNSWICK 1110 - MORGAN RANCH DR |  | Payroll Taxes OH |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Environmental Contract |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Environmental Contract |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Consulting Services - Engineering |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Acquisition - Misc |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Construction |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Design Services |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Design Services |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Design Services |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Electric Estimating |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Engineering/Mapping |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Engineering/Mapping |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Electric |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Electric |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Electric |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Environmental Land |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Environmental Land |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Indirect Labor - Environmental Land |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Land Rights - Misc |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Land Rights - Misc |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Mapping |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Mapping |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Paid Time Off |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Paid Time Off |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Paid Time Off |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Borrowed |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Borrowed |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Borrowed |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Equity |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Equity |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | AFUDC-Equity |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Benefits OH |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Benefits OH |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Benefits OH |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Building Service Overhead |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Building Service Overhead |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Building Service Overhead |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Capitalized A&G |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Capitalized A&G |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Capitalized A&G |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Fleet OH - Elec |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Fleet OH - Elec |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Fleet OH - Elec |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | IT Device OH |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | IT Device OH |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | IT Device OH |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Electric |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Electric |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Electric |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Payroll Taxes OH |  | 001/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Payroll Taxes OH |  | 002/2021
35223037 | PSPS - OAKHURST 1101 - OAKHURST |  | Payroll Taxes OH |  | 003/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Environmental Contract |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Consulting Services - Engineering |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Design Overtime Services |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Design Services |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Electric Estimating |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Indirect Labor - Electric |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Indirect Labor - Electric |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Indirect Labor - Environmental Land |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Indirect Labor - Environmental Land |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Land Rights - Misc |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Land Rights - Misc |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Mapping |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Paid Time Off |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Paid Time Off |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Borrowed |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Borrowed |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Borrowed |  | 003/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Equity |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Equity |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | AFUDC-Equity |  | 003/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Benefits OH |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Benefits OH |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Building Service Overhead |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Building Service Overhead |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Capitalized A&G |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Capitalized A&G |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Fleet OH - Elec |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Fleet OH - Elec |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | IT Device OH |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | IT Device OH |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Operation Mgmt & Support - Electric |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Operation Mgmt & Support - Electric |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Payroll Taxes OH |  | 001/2021
35223038 | PSPS- MARTELL1101/OLETA1101-SUTTER CREEK |  | Payroll Taxes OH |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Environmental Contract |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Environmental Contract |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Consulting Services - Engineering |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Administrative Services - OT |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Administrative Services - OT |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Engineering/Mapping |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Engineering/Mapping |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Environmental Planning & Permitting-Misc |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Electric |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Electric |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Electric |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Environmental Land |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Environmental Land |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Indirect Labor - Environmental Land |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Land Rights - Misc |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Mapping |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Mapping |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Paid Time Off |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Paid Time Off |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Paid Time Off |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Borrowed |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Borrowed |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Borrowed |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Equity |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Equity |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | AFUDC-Equity |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Benefits OH |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Benefits OH |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Benefits OH |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Building Service Overhead |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Building Service Overhead |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Building Service Overhead |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Capitalized A&G |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Capitalized A&G |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Capitalized A&G |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Fleet OH - Elec |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Fleet OH - Elec |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Fleet OH - Elec |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | IT Device OH |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | IT Device OH |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | IT Device OH |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Lodging |  | 004/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Meals Expense |  | 004/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Electric |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Electric |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Electric |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Other Expenses |  | 003/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Other Expenses |  | 004/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Payroll Taxes OH |  | 001/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Payroll Taxes OH |  | 002/2021
35223039 | PSPS - WYANDOTTE 1109 - MOORETOWN RANCHE |  | Payroll Taxes OH |  | 003/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Environmental Contract |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Administrative Services - OT |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Design Overtime Services |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Design Services |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Electric Estimating |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Indirect Labor - Electric |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Mapping |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Paid Time Off |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Paid Time Off |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Equity |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Equity |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | AFUDC-Equity |  | 003/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Benefits OH |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Benefits OH |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Building Service Overhead |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Building Service Overhead |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Capitalized A&G |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Capitalized A&G |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Fleet OH - Elec |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | IT Device OH |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | IT Device OH |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35223060 | PSPS-ALLEGHANY 1101-DOWNIEVILLE PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Environmental Contract |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Consulting Services - Engineering |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Administrative Services - OT |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Electric Estimating Overtime |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Engineering/Mapping |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Engineering/Mapping Services Overtime |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Indirect Labor - Electric |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Indirect Labor - Electric |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Indirect Labor - Environmental Land |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Indirect Labor - Environmental Land |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Mapping |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Paid Time Off |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Paid Time Off |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Borrowed |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Borrowed |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Borrowed |  | 003/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Equity |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Equity |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | AFUDC-Equity |  | 003/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Benefits OH |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Benefits OH |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Building Service Overhead |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Building Service Overhead |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Canceled Capital Order |  | 003/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Capitalized A&G |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Capitalized A&G |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Fleet OH - Elec |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Fleet OH - Elec |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | IT Device OH |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | IT Device OH |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Operation Mgmt & Support - Electric |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Operation Mgmt & Support - Electric |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Payroll Taxes OH |  | 001/2021
35223061 | *CANC*PSPS - CALISTOGA 1102 - DUNAWEAL W |  | Payroll Taxes OH |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Environmental Contract |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Consulting Services - Engineering |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Construction Overtime Services |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Electric Estimating Overtime |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Engineering/Mapping |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Engineering/Mapping |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Engineering/Mapping |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Indirect Labor - Electric |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Indirect Labor - Electric |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Indirect Labor - Electric |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Indirect Labor - Environmental Land |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Indirect Labor - Environmental Land |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Land Rights - Misc |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Mapping |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Mapping |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Paid Time Off |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Paid Time Off |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Paid Time Off |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Borrowed |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Borrowed |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Borrowed |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Equity |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Equity |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | AFUDC-Equity |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Benefits OH |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Benefits OH |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Benefits OH |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Building Service Overhead |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Building Service Overhead |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Building Service Overhead |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Capitalized A&G |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Capitalized A&G |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Capitalized A&G |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Fleet OH - Elec |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Fleet OH - Elec |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Fleet OH - Elec |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | IT Device OH |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | IT Device OH |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | IT Device OH |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Operation Mgmt & Support - Electric |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Operation Mgmt & Support - Electric |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Operation Mgmt & Support - Electric |  | 003/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Payroll Taxes OH |  | 001/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Payroll Taxes OH |  | 002/2021
35223062 | PSPS - CALISTOGA 1102 - W/O NAPA RIVER |  | Payroll Taxes OH |  | 003/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Environmental Contract |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Consulting Services - Engineering |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Design Drafting Services |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Design Drafting Services - Overtime |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Electric Estimating Overtime |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Environmental Planning & Permitting-Misc |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Indirect Labor - Electric |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Indirect Labor - Electric |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Indirect Labor - Environmental Land |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Land Rights - Misc |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Mapping |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Paid Time Off |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Paid Time Off |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Borrowed |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Borrowed |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Borrowed |  | 003/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Equity |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Equity |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | AFUDC-Equity |  | 003/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Benefits OH |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Benefits OH |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Building Service Overhead |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Building Service Overhead |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Capitalized A&G |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Capitalized A&G |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Fleet OH - Elec |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Fleet OH - Elec |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | IT Device OH |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | IT Device OH |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Operation Mgmt & Support - Electric |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Operation Mgmt & Support - Electric |  | 002/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Payroll Taxes OH |  | 001/2021
35223063 | PSPS - DUNBAR 1101 - OAKMONT |  | Payroll Taxes OH |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Contracts |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Gas Construction Contract |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Gas Construction Contract |  | 004/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Account Services |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Acquisition - Misc |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Administration |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Administration |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Administration |  | 004/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Design Drafting Services |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Design Drafting Services - Overtime |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Design Drafting Services - Overtime |  | 004/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Drafting Doubletime |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electric Activity Charge - Type A |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electric Estimating |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electric Estimating |  | 004/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electric Estimating Overtime |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Engineering/Mapping |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Engineering/Mapping |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Env & Land Activity Charge - Type A |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Cust Care |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Electric |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Electric |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Environmental Land |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Environmental Land |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Indirect Labor - Environmental Land |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Land Rights - Misc |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Management Services |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Management Services - OT |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Mapping |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Mapping |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Paid Time Off |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Paid Time Off |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Paid Time Off |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electl & Electronic Equipment Component |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Electrical Specialties |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Material Burden |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Borrowed |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Borrowed |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Borrowed |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Equity |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Equity |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | AFUDC-Equity |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Benefits OH |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Benefits OH |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Benefits OH |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Building Service Overhead |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Building Service Overhead |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Building Service Overhead |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Capitalized A&G |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Capitalized A&G |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Capitalized A&G |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Cost Adjustments |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Fleet OH - Elec |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Fleet OH - Elec |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Fleet OH - Gas |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | IT Device OH |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | IT Device OH |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | IT Device OH |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Minor Material OH |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Operation Mgmt & Support - Gas |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Payroll Taxes OH |  | 001/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Payroll Taxes OH |  | 002/2021
35223343 | FRRB - BIG BEND 1102-LAKE MADRONE ZONE 1 |  | Payroll Taxes OH |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Contracts |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 004/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Construction Contract |  | 004/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Gas Construction Contract |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Gas Construction Contract |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Gas Construction Contract |  | 004/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Administration |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Administration |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Administration |  | 004/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Administrative Services - OT |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction Overtime Services |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction Overtime Services |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction Overtime Services |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Design Drafting Services |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Design Drafting Services - Overtime |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Design Drafting Services - Overtime |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Drafting Doubletime |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Activity Charge - Type A |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Estimating |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electric Estimating Overtime |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Engineering/Mapping |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Engineering/Mapping |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Env & Land Activity Charge - Type A |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Environmental Services |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Electric |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Electric |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Electric |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Environmental Land |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Indirect Labor - Gas |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Maintain & Operate Services |  | 004/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Manage L&EM |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Manage L&EM |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Mapping |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Mapping |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Mapping |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Paid Time Off |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Paid Time Off |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Paid Time Off |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Warehouse Services |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Construction Supplies |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electl & Electronic Equipment Component |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electl & Electronic Equipment Component |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electrical Specialties |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electrical Specialties |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electrical Specialties |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Electrical Specialties |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Material Burden |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Material Burden |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Office Supplies Expense |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Printed Matls, Signs, Off Suppl & Furn |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Borrowed |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Borrowed |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Borrowed |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Equity |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Equity |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | AFUDC-Equity |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Benefits OH |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Benefits OH |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Benefits OH |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Building Service Overhead |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Building Service Overhead |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Building Service Overhead |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Capitalized A&G |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Capitalized A&G |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Capitalized A&G |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Cash Discount earned |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Cost Adjustments |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Fleet OH - Elec |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Fleet OH - Elec |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Fleet OH - Elec |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Fleet OH - Gas |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | IT Device OH |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | IT Device OH |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | IT Device OH |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Minor Material OH |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Minor Material OH |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Operation Mgmt & Support - Gas |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Payroll Taxes OH |  | 001/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Payroll Taxes OH |  | 002/2021
35223344 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 2 |  | Payroll Taxes OH |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Inspection |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Inspection |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Contracts |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Construction Contract |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Gas Construction Contract |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Gas Construction Contract |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | T&D Sewer Inspection |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | T&D Sewer Inspection |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Traffic Control Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Traffic Control Contracts |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Traffic Control Contracts |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Traffic Control Contracts |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Consulting Services - Engineering |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Consulting Services - Engineering |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Consulting Services - Engineering |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Consulting Services - Environmental Perm |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Account Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Acquisition - Misc |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Administration |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Administration |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Administration |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Administrative Services - OT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Analyst Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Analyst Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Doubletime Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Doubletime Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Doubletime Services |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Overtime Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Overtime Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Overtime Services |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Design Drafting Services |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Design Drafting Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Design Drafting Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Design Drafting Services - Overtime |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Design Drafting Services - Overtime |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Drafting Doubletime |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electric Activity Charge - Type A |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering Services - OT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering Services - OT |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering/Mapping |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Engineering/Mapping |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Env & Land Activity Charge - Type A |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Environmental Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Hours - Straight Time |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Cust Care |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Electric |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Electric |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Electric |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Environmental Land |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Environmental Land |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Gas |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - Gas |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Indirect Labor - IT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Inspection Services DT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Inspection Services OT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Land Rights - Misc |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Maintain & Operate Services |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Manage L&EM |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Manage L&EM |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Management Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Mapping |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Mapping |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Paid Time Off |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Paid Time Off |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Paid Time Off |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Automotive |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Construction Supplies |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electl & Electronic Equipment Component |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electl & Electronic Equipment Component |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electrical Specialties |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electrical Specialties |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Electrical Specialties |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Material Burden |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Material Burden |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Office Supplies Expense |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Purchasing Card |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Purchasing Card |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Purchasing Card |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Purchasing Card |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Borrowed |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Borrowed |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Borrowed |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Equity |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Equity |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | AFUDC-Equity |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Benefits OH |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Benefits OH |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Benefits OH |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Building Service Overhead |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Building Service Overhead |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Building Service Overhead |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Capitalized A&G |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Capitalized A&G |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Capitalized A&G |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cash Discount earned |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Cost Adjustments |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Fleet OH - Elec |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Fleet OH - Elec |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Fleet OH - Elec |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Fleet OH - Gas |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Fleet OH - Gas |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | IT Device OH |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | IT Device OH |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | IT Device OH |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Land Acquisition Services |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Land Acquisition Services |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Lodging |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Lodging |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Meals Expense |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Meals Expense |  | 004/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Minor Material OH |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Minor Material OH |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Gas |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - Gas |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Operation Mgmt & Support - IT |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Payroll Taxes OH |  | 001/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Payroll Taxes OH |  | 002/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Payroll Taxes OH |  | 003/2021
35223345 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 3 |  | Rents |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Acquisition - Misc |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Acquisition - Misc |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Acquisition - Misc |  | 004/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Administrative Services - OT |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Engineering/Mapping |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Indirect Labor - Electric |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Paid Time Off |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Paid Time Off |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | AFUDC-Borrowed |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | AFUDC-Borrowed |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | AFUDC-Equity |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | AFUDC-Equity |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Benefits OH |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Benefits OH |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Building Service Overhead |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Building Service Overhead |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Capitalized A&G |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Capitalized A&G |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Fleet OH - Elec |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | IT Device OH |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | IT Device OH |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Payroll Taxes OH |  | 002/2021
35223615 | ECOP - LAS GALLINAS A 1105 PH 2 |  | Payroll Taxes OH |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Engineering/Mapping |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Indirect Labor - Electric |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Paid Time Off |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | AFUDC-Borrowed |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | AFUDC-Equity |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Benefits OH |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Building Service Overhead |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Capitalized A&G |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Fleet OH - Elec |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | IT Device OH |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Operation Mgmt & Support - Electric |  | 003/2021
35224320 | TULUCAY 1101 RECOND WITH TREE WIRE |  | Payroll Taxes OH |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Environmental Contract |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Consulting Services - Engineering |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Consulting Services - Engineering |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Account Services |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engineering/Mapping |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Engineering/Mapping |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Environmental Planning & Permitting-Misc |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Indirect Labor - Cust Care |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Indirect Labor - Electric |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Indirect Labor - Electric |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Indirect Labor - Electric |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Indirect Labor - Environmental Land |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Mapping |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Mapping |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Paid Time Off |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Paid Time Off |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Paid Time Off |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Borrowed |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Borrowed |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Borrowed |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Equity |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Equity |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | AFUDC-Equity |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Benefits OH |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Benefits OH |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Benefits OH |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Building Service Overhead |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Building Service Overhead |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Building Service Overhead |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Capitalized A&G |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Capitalized A&G |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Capitalized A&G |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Fleet OH - Elec |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Fleet OH - Elec |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Fleet OH - Elec |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | IT Device OH |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | IT Device OH |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | IT Device OH |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Operation Mgmt & Support - Electric |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Operation Mgmt & Support - Electric |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Operation Mgmt & Support - Electric |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Payroll Taxes OH |  | 001/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Payroll Taxes OH |  | 002/2021
35224321 | CWSP - WILDWOOD 1101 LR 1454 TEHAMA CO |  | Payroll Taxes OH |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Environmental Contract |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Consulting Services - Engineering |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Construction Overtime Services |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Design Overtime Services |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Design Services |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Engineering/Mapping Services Overtime |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Indirect Labor - Electric |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Indirect Labor - Electric |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Land Rights - Misc |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Mapping |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Mapping |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Paid Time Off |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Paid Time Off |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Paid Time Off |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Borrowed |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Borrowed |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Borrowed |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Equity |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Equity |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | AFUDC-Equity |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Benefits OH |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Benefits OH |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Benefits OH |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Building Service Overhead |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Building Service Overhead |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Building Service Overhead |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Capitalized A&G |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Capitalized A&G |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Capitalized A&G |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Fleet OH - Elec |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Fleet OH - Elec |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | IT Device OH |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | IT Device OH |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | IT Device OH |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Payroll Taxes OH |  | 001/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Payroll Taxes OH |  | 002/2021
35224377 | PSPS - PLACERVILLE 2106 MICROGRID PH 1.1 |  | Payroll Taxes OH |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Environmental Contract |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Consulting Services - Engineering |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Construction Overtime Services |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Design Drafting Services |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Engineering/Mapping |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Engineering/Mapping |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Indirect Labor - Electric |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Indirect Labor - Electric |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Indirect Labor - Electric |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Indirect Labor - Environmental Land |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Land Rights - Misc |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Mapping |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Mapping |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Paid Time Off |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Paid Time Off |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Paid Time Off |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Borrowed |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Borrowed |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Borrowed |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Equity |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Equity |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | AFUDC-Equity |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Benefits OH |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Benefits OH |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Benefits OH |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Building Service Overhead |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Building Service Overhead |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Building Service Overhead |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Capitalized A&G |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Capitalized A&G |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Capitalized A&G |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Fleet OH - Elec |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Fleet OH - Elec |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Fleet OH - Elec |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | IT Device OH |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | IT Device OH |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | IT Device OH |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Payroll Taxes OH |  | 001/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Payroll Taxes OH |  | 002/2021
35224378 | CWSP - VACAVILLE 11046542 - PH 2.1 |  | Payroll Taxes OH |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Construction |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Indirect Labor - Electric |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Mapping |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Paid Time Off |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Paid Time Off |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | AFUDC-Borrowed |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | AFUDC-Borrowed |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | AFUDC-Equity |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | AFUDC-Equity |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Benefits OH |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Benefits OH |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Building Service Overhead |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Building Service Overhead |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Capitalized A&G |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Capitalized A&G |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Fleet OH - Elec |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | IT Device OH |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | IT Device OH |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Payroll Taxes OH |  | 002/2021
35224712 | CWSP - BUCKS CREEK 1101 CB PH 2 |  | Payroll Taxes OH |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Environmental Contract |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Construction |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Indirect Labor - Electric |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Indirect Labor - Electric |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Mapping |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Mapping |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Paid Time Off |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Paid Time Off |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | AFUDC-Borrowed |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | AFUDC-Borrowed |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | AFUDC-Equity |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | AFUDC-Equity |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Benefits OH |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Benefits OH |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Building Service Overhead |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Building Service Overhead |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Capitalized A&G |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Capitalized A&G |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Fleet OH - Elec |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Fleet OH - Elec |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | IT Device OH |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | IT Device OH |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Payroll Taxes OH |  | 002/2021
35224713 | CWSP - BUCKS CREEK 1101 CB PH 3 |  | Payroll Taxes OH |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Account Services |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Electric Estimating |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Engineering/Mapping |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Indirect Labor - Cust Care |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Indirect Labor - Electric |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Paid Time Off |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | AFUDC-Borrowed |  | 002/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | AFUDC-Borrowed |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | AFUDC-Equity |  | 002/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | AFUDC-Equity |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Benefits OH |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Building Service Overhead |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Capitalized A&G |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Fleet OH - Elec |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | IT Device OH |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225589 | CWSP - KONOCTI 1102 LR 965078 PH2 |  | Payroll Taxes OH |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 002/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Account Services |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Engineering/Mapping |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Indirect Labor - Cust Care |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Indirect Labor - Electric |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Indirect Labor - Environmental Land |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Paid Time Off |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | AFUDC-Borrowed |  | 002/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | AFUDC-Borrowed |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | AFUDC-Equity |  | 002/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | AFUDC-Equity |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Benefits OH |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Building Service Overhead |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Capitalized A&G |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Fleet OH - Elec |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | IT Device OH |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225591 | CWSP - KONOCTI 1102 LR 965078 PH3 |  | Payroll Taxes OH |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Contracts |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Consulting Services - Engineering |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Construction |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Construction |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Design Overtime Services |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Design Services |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Design Services Double Time |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating Doubletime |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating Doubletime |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating Overtime |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Electric Estimating Overtime |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Engineering/Mapping |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Engineering/Mapping |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Indirect Labor - Electric |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Indirect Labor - Electric |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Indirect Labor - Environmental Land |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Indirect Labor - Environmental Land |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Land Rights - Misc |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Mapping |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Mapping |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Paid Time Off |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Paid Time Off |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Benefits OH |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Benefits OH |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Building Service Overhead |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Building Service Overhead |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Capitalized A&G |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Capitalized A&G |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Fleet OH - Elec |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Fleet OH - Elec |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | IT Device OH |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | IT Device OH |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Payroll Taxes OH |  | 002/2021
35225593 | ECOP - CLAYTON 2212 - H01-LR2951 PH2 |  | Payroll Taxes OH |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Environmental Contract |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Consulting Services - Environmental Perm |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Construction Overtime Services |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Engineering/Mapping |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Engineering/Mapping |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Indirect Labor - Electric |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Mapping |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Paid Time Off |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Paid Time Off |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Paid Time Off |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Borrowed |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Equity |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Benefits OH |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Benefits OH |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Benefits OH |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Building Service Overhead |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Building Service Overhead |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Building Service Overhead |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Capitalized A&G |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Capitalized A&G |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Capitalized A&G |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Fleet OH - Elec |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | IT Device OH |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | IT Device OH |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | IT Device OH |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Payroll Taxes OH |  | 001/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35225594 | ECOP - FULTON 1107 - H02-LR604 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Environmental Contract |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Electric Estimating |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Electric Estimating Overtime |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Engineering/Mapping |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Engineering/Mapping |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Indirect Labor - Electric |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Mapping |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Paid Time Off |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Paid Time Off |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Paid Time Off |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Borrowed |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Equity |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Benefits OH |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Benefits OH |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Benefits OH |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Building Service Overhead |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Building Service Overhead |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Building Service Overhead |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Capitalized A&G |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Capitalized A&G |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Capitalized A&G |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Fleet OH - Elec |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | IT Device OH |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | IT Device OH |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | IT Device OH |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Payroll Taxes OH |  | 001/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35225595 | ECOP - FULTON 1107 - H02-LR604 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Environmental Contract |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Construction Overtime Services |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Design Drafting Services - Overtime |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Electric Estimating |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Electric Estimating Overtime |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Engineering/Mapping |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Engineering/Mapping |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Engineering/Mapping |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Indirect Labor - Electric |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Mapping |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Paid Time Off |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Paid Time Off |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Paid Time Off |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Borrowed |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Equity |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Benefits OH |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Benefits OH |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Benefits OH |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Building Service Overhead |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Building Service Overhead |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Building Service Overhead |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Capitalized A&G |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Capitalized A&G |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Capitalized A&G |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Fleet OH - Elec |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | IT Device OH |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | IT Device OH |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | IT Device OH |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Payroll Taxes OH |  | 001/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35225597 | ECOP - FULTON 1107 - H02-LR604 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Environmental Contract |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Account Services |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Electric Estimating |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Electric Estimating Overtime |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Engineering/Mapping |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Engineering/Mapping |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Engineering/Mapping |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Indirect Labor - Cust Care |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Indirect Labor - Electric |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Indirect Labor - Electric |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Mapping |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Paid Time Off |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Paid Time Off |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Paid Time Off |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Borrowed |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Borrowed |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Equity |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Equity |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Benefits OH |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Benefits OH |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Benefits OH |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Building Service Overhead |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Building Service Overhead |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Building Service Overhead |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Capitalized A&G |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Capitalized A&G |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Capitalized A&G |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Fleet OH - Elec |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Fleet OH - Elec |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | IT Device OH |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | IT Device OH |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | IT Device OH |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Payroll Taxes OH |  | 001/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Payroll Taxes OH |  | 002/2021
35225598 | ECOP - FULTON 1107 - H02-LR604 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Contracts |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Account Services |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Administration |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Administration |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Electric Activity Charge - Type A |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Engineering/Mapping |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Engineering/Mapping |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Env & Land Activity Charge - Type A |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Cust Care |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Electric |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Electric |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Environmental Land |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Manage L&EM |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Manage L&EM |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Manage L&EM |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Mapping |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Paid Time Off |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Paid Time Off |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Paid Time Off |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Electl & Electronic Equipment Component |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Electrical Specialties |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Material Burden |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Borrowed |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Borrowed |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Borrowed |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Equity |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Equity |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | AFUDC-Equity |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Benefits OH |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Benefits OH |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Benefits OH |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Building Service Overhead |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Building Service Overhead |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Building Service Overhead |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Capitalized A&G |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Capitalized A&G |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Capitalized A&G |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Cost Adjustments |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Fleet OH - Elec |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Fleet OH - Elec |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Fleet OH - Gas |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | IT Device OH |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | IT Device OH |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | IT Device OH |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Minor Material OH |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Operation Mgmt & Support - Gas |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Payroll Taxes OH |  | 001/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Payroll Taxes OH |  | 002/2021
35225821 | FRRB - BIG BEND - LAKE MADRONE ZONE 2 |  | Payroll Taxes OH |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Inspection |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Inspection |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Management Contracts |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Contracts |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Contracts |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electric Construction Contract |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Contract |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Contract |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Contract |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Contract |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Contract |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Traffic Control Contracts |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Traffic Control Contracts |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Consulting Services - Engineering |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Consulting Services - Environmental Perm |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Administration |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Administration |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Administration |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Analyst Services |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Analyst Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Doubletime Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Doubletime Services |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Overtime Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Construction Overtime Services |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Design Drafting Services |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Design Drafting Services - Overtime |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electric Activity Charge - Type A |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Engineering Doubletime |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Engineering Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Engineering Services - OT |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Engineering/Mapping |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Engineering/Mapping |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Env & Land Activity Charge - Type A |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Environmental Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Electric |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Electric |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Environmental Land |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Environmental Land |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Environmental Land |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Indirect Labor - Gas |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Inspection Services |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Inspection Services DT |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Inspection Services OT |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Manage L&EM |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Mapping |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Mapping |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Paid Time Off |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Paid Time Off |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Paid Time Off |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Chemicals,Cleaners,Compounds & Lab Suppl |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electl & Electronic Equipment Component |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electl & Electronic Equipment Component |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electrical Specialties |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electrical Specialties |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Electrical Specialties |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Material Burden |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Material Burden |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Borrowed |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Borrowed |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Borrowed |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Equity |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Equity |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | AFUDC-Equity |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Benefits OH |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Benefits OH |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Benefits OH |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Building Service Overhead |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Building Service Overhead |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Building Service Overhead |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Capitalized A&G |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Capitalized A&G |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Capitalized A&G |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Cash Discount earned |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Cash Discount earned |  | 004/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Cash Discount earned |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Cost Adjustments |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Fleet OH - Elec |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Fleet OH - Elec |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Fleet OH - Gas |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Fleet OH - Gas |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | IT Device OH |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | IT Device OH |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | IT Device OH |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Minor Material OH |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Minor Material OH |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Gas |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Operation Mgmt & Support - Gas |  | 003/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Payroll Taxes OH |  | 001/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Payroll Taxes OH |  | 002/2021
35225822 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 6 |  | Payroll Taxes OH |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Inspection |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Inspection |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Management Contracts |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Contracts |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Contract |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Contract |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Contract |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Contract |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Contract |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Consulting Services - Engineering |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Consulting Services - Environmental Perm |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Account Services |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Acquisition - Misc |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Administration |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Administration |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Administrative Services - OT |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Analyst Services |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Analyst Services |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Overtime Services |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Overtime Services |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Electric Activity Charge - Type A |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Engineering/Mapping |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Engineering/Mapping |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Env & Land Activity Charge - Type A |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Services |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Environmental Services |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Cust Care |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Electric |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Electric |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Environmental Land |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Environmental Land |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Gas |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Indirect Labor - Gas |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Land Rights - Misc |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Mapping |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Mapping |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Paid Time Off |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Paid Time Off |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Construction Supplies |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Electl & Electronic Equipment Component |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Electrical Specialties |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Electrical Specialties |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Material Burden |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Material Burden |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | AFUDC-Borrowed |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | AFUDC-Borrowed |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | AFUDC-Equity |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | AFUDC-Equity |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Benefits OH |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Benefits OH |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Building Service Overhead |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Building Service Overhead |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Capitalized A&G |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Capitalized A&G |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Cost Adjustments |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Fleet OH - Elec |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Fleet OH - Elec |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Fleet OH - Gas |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Fleet OH - Gas |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | IT Device OH |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | IT Device OH |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Lodging |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Lodging |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Lodging |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Minor Material OH |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Minor Material OH |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Gas |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Operation Mgmt & Support - Gas |  | 003/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Payroll Taxes OH |  | 002/2021
35225823 | FRRB - WYANDOTTE 1103 - BALD ROCK ZONE 7 |  | Payroll Taxes OH |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Contracts |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Acquisition - Misc |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Administration |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Administration |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Administrative Services - OT |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction Overtime Services |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction Overtime Services |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Construction Overtime Services |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Design Drafting Services |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Design Drafting Services - Overtime |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electric Activity Charge - Type A |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electric Estimating |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electric Estimating Overtime |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Engineering/Mapping |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Engineering/Mapping |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Env & Land Activity Charge - Type A |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | GAS Activity Charge - Non-Type A |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Hours - Straight Time |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Electric |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Electric |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Electric |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Environmental Land |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Environmental Land |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Environmental Land |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - Gas |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Indirect Labor - IT |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Land Rights - Misc |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Manage L&EM |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Mapping |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Mapping |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Mapping |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Paid Time Off |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Paid Time Off |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Paid Time Off |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electl & Electronic Equipment Component |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electrical Specialties |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Electrical Specialties |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Material Burden |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Material Burden |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Transformers, Regulators & Capacitors |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Borrowed |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Borrowed |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Borrowed |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Equity |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Equity |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | AFUDC-Equity |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Benefits OH |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Benefits OH |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Benefits OH |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Building Service Overhead |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Building Service Overhead |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Building Service Overhead |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Capitalized A&G |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Capitalized A&G |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Capitalized A&G |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Cost Adjustments |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Fleet OH - Elec |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Fleet OH - Elec |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Fleet OH - Elec |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Fleet OH - Gas |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Fleet OH - Gas |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | IT Device OH |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | IT Device OH |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | IT Device OH |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Minor Material OH |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Minor Material OH |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Electric |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Gas |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - Gas |  | 003/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Operation Mgmt & Support - IT |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Payroll Taxes OH |  | 001/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Payroll Taxes OH |  | 002/2021
35225824 | FRRB - WYANDOTTE 1103 - HWY 162 |  | Payroll Taxes OH |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Environmental Contract |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Environmental Contract |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Consulting Services - Engineering |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Construction |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Design Drafting Services |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Design Drafting Services - Overtime |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Drafting Doubletime |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Engineering Services - OT |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Engineering/Mapping |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Indirect Labor - Electric |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Land Rights - Misc |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Land Rights - Misc |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Management Services |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Mapping |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Mapping |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Paid Time Off |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Paid Time Off |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | AFUDC-Equity |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | AFUDC-Equity |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Benefits OH |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Benefits OH |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Building Service Overhead |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Building Service Overhead |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Capitalized A&G |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Capitalized A&G |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Fleet OH - Elec |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Fleet OH - Elec |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | IT Device OH |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | IT Device OH |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Payroll Taxes OH |  | 002/2021
35225825 | CWSP - DESCHUTES 11049718 PH2.1 |  | Payroll Taxes OH |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Construction Overtime Services |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Engineering/Mapping |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Engineering/Mapping Services Overtime |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Indirect Labor - Electric |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Mapping |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Paid Time Off |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Paid Time Off |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | AFUDC-Equity |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | AFUDC-Equity |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Benefits OH |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Benefits OH |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Building Service Overhead |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Building Service Overhead |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Capitalized A&G |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Capitalized A&G |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Fleet OH - Elec |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Fleet OH - Elec |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | IT Device OH |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | IT Device OH |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Payroll Taxes OH |  | 002/2021
35225826 | CWSP - OREGON TRAIL 110335002 PH2.1 |  | Payroll Taxes OH |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Construction Overtime Services |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Engineering/Mapping |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Engineering/Mapping |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Indirect Labor - Electric |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Indirect Labor - Electric |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Mapping |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Paid Time Off |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Paid Time Off |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | AFUDC-Borrowed |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | AFUDC-Borrowed |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | AFUDC-Equity |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | AFUDC-Equity |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Benefits OH |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Benefits OH |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Building Service Overhead |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Building Service Overhead |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Capitalized A&G |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Capitalized A&G |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Fleet OH - Elec |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Fleet OH - Elec |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | IT Device OH |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | IT Device OH |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Payroll Taxes OH |  | 002/2021
35225827 | CWSP - OREGON TRAIL 110335002 PH3.1 |  | Payroll Taxes OH |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Construction Overtime Services |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Engineering/Mapping |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Engineering/Mapping |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Indirect Labor - Electric |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Indirect Labor - Electric |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Mapping |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Paid Time Off |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Paid Time Off |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | AFUDC-Borrowed |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | AFUDC-Borrowed |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | AFUDC-Equity |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | AFUDC-Equity |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Benefits OH |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Benefits OH |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Building Service Overhead |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Building Service Overhead |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Capitalized A&G |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Capitalized A&G |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Fleet OH - Elec |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Fleet OH - Elec |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | IT Device OH |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | IT Device OH |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Payroll Taxes OH |  | 002/2021
35225828 | CWSP - OREGON TRAIL 110335002 PH4.1 |  | Payroll Taxes OH |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Construction Overtime Services |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Engineering/Mapping |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Engineering/Mapping |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Indirect Labor - Electric |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Indirect Labor - Electric |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Mapping |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Paid Time Off |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Paid Time Off |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | AFUDC-Borrowed |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | AFUDC-Borrowed |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | AFUDC-Equity |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | AFUDC-Equity |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Benefits OH |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Benefits OH |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Building Service Overhead |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Building Service Overhead |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Capitalized A&G |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Capitalized A&G |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Fleet OH - Elec |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Fleet OH - Elec |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | IT Device OH |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | IT Device OH |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Payroll Taxes OH |  | 002/2021
35225829 | CWSP - OREGON TRAIL 110335002 PH5.1 |  | Payroll Taxes OH |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Contracts |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Environmental Contract |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Consulting Services - Engineering |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Analyst Services |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Construction Overtime Services |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Design Drafting Services - Overtime |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Drafting Doubletime |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Electric Estimating |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Electric Estimating Doubletime |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Electric Estimating Overtime |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Engineering/Mapping |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Engineering/Mapping |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Indirect Labor - Electric |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Indirect Labor - Electric |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Indirect Labor - Environmental Land |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Mapping |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Mapping |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Paid Time Off |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Paid Time Off |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | AFUDC-Borrowed |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | AFUDC-Borrowed |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | AFUDC-Equity |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | AFUDC-Equity |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Benefits OH |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Benefits OH |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Building Service Overhead |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Building Service Overhead |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Capitalized A&G |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Capitalized A&G |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Fleet OH - Elec |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Fleet OH - Elec |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | IT Device OH |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | IT Device OH |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Payroll Taxes OH |  | 002/2021
35226240 | CWSP - MARIPOSA 210197142 PH 3 |  | Payroll Taxes OH |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Contracts |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Environmental Contract |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Consulting Services - Engineering |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Acquisition - Misc |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Acquisition - Misc |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Administration |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Administration |  | 004/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Administrative Services - OT |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Administrative Services - OT |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Design Drafting Services |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Design Drafting Services |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Design Drafting Services - Overtime |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Design Drafting Services - Overtime |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Design Services |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Electric Estimating |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Electric Estimating |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Electric Estimating Overtime |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Electric Estimating Overtime |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Engineering/Mapping |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Engineering/Mapping |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Indirect Labor - Electric |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Indirect Labor - Electric |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Mapping |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Paid Time Off |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Paid Time Off |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | AFUDC-Borrowed |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | AFUDC-Borrowed |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | AFUDC-Equity |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | AFUDC-Equity |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Benefits OH |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Benefits OH |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Building Service Overhead |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Building Service Overhead |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Capitalized A&G |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Capitalized A&G |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Fleet OH - Elec |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Fleet OH - Elec |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | IT Device OH |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | IT Device OH |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Payroll Taxes OH |  | 002/2021
35226241 | CWSP - MARIPOSA 210197142 PH 2 |  | Payroll Taxes OH |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Account Services |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Engineering/Mapping |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Indirect Labor - Cust Care |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Paid Time Off |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | AFUDC-Borrowed |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | AFUDC-Equity |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Benefits OH |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Building Service Overhead |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Capitalized A&G |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Fleet OH - Elec |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | IT Device OH |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226621 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.2 |  | Payroll Taxes OH |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Account Services |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Engineering/Mapping |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Indirect Labor - Cust Care |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Indirect Labor - Electric |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Paid Time Off |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | AFUDC-Borrowed |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | AFUDC-Equity |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Benefits OH |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Building Service Overhead |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Capitalized A&G |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Fleet OH - Elec |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | IT Device OH |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226622 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.3 |  | Payroll Taxes OH |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Engineering/Mapping |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Paid Time Off |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | AFUDC-Borrowed |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | AFUDC-Equity |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Benefits OH |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Building Service Overhead |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Capitalized A&G |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Fleet OH - Elec |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | IT Device OH |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226623 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.4 |  | Payroll Taxes OH |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Engineering/Mapping |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Indirect Labor - Electric |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Paid Time Off |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | AFUDC-Equity |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Benefits OH |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Building Service Overhead |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Capitalized A&G |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Fleet OH - Elec |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | IT Device OH |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226624 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH2.5 |  | Payroll Taxes OH |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Management Services |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Management Services |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | AFUDC-Borrowed |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | AFUDC-Borrowed |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | AFUDC-Equity |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | AFUDC-Equity |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Benefits OH |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Benefits OH |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Building Service Overhead |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Building Service Overhead |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Capitalized A&G |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Capitalized A&G |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | IT Device OH |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | IT Device OH |  | 003/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Payroll Taxes OH |  | 002/2021
35226625 | FRRB - ELK CREEK 1101 LR 2106 |  | Payroll Taxes OH |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Acquisition - Misc |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Acquisition - Misc |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Acquisition - Misc |  | 004/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Construction |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Electric |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Environmental Land |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Indirect Labor - Environmental Land |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Land Rights - Misc |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Land Rights - Misc |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Land Rights - Misc |  | 004/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Manage L&EM |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Management Services |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Management Services |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Mapping |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Paid Time Off |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Paid Time Off |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Paid Time Off |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Borrowed |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | AFUDC-Equity |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Benefits OH |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Benefits OH |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Benefits OH |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Building Service Overhead |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Building Service Overhead |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Building Service Overhead |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Capitalized A&G |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Capitalized A&G |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Capitalized A&G |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Fleet OH - Elec |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | IT Device OH |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | IT Device OH |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | IT Device OH |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Electric |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Payroll Taxes OH |  | 001/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Payroll Taxes OH |  | 002/2021
35226626 | FRRB - FITCH MOUNTAIN 1113 LR 6751 |  | Payroll Taxes OH |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Electric Estimating |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Paid Time Off |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Benefits OH |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Building Service Overhead |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Capitalized A&G |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | IT Device OH |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226627 | CWSP - KESWICK 1101 LR 1586 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Acquisition - Misc |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Acquisition - Misc |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Indirect Labor - Environmental Land |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Paid Time Off |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Paid Time Off |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Benefits OH |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Benefits OH |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Building Service Overhead |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Building Service Overhead |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Capitalized A&G |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Capitalized A&G |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | IT Device OH |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | IT Device OH |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35226628 | CWSP - KESWICK 1101 LR 1586 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Acquisition - Misc |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Acquisition - Misc |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Indirect Labor - Environmental Land |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Paid Time Off |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Paid Time Off |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | AFUDC-Equity |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Benefits OH |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Benefits OH |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Building Service Overhead |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Building Service Overhead |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Capitalized A&G |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Capitalized A&G |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | IT Device OH |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | IT Device OH |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35226629 | CWSP - KESWICK 1101 LR 1586 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Paid Time Off |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Benefits OH |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Building Service Overhead |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Capitalized A&G |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | IT Device OH |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226630 | CWSP - KESWICK 1101 LR 1586 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Acquisition - Misc |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Acquisition - Misc |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Electric Estimating Overtime |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Paid Time Off |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Paid Time Off |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | AFUDC-Borrowed |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | AFUDC-Equity |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | AFUDC-Equity |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Benefits OH |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Benefits OH |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Building Service Overhead |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Building Service Overhead |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Capitalized A&G |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Capitalized A&G |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | IT Device OH |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | IT Device OH |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Payroll Taxes OH |  | 002/2021
35226631 | CWSP - KESWICK 1101 LR 1586 PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Account Services |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Paid Time Off |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Paid Time Off |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Project Management Services |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Benefits OH |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Benefits OH |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Building Service Overhead |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Building Service Overhead |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Capitalized A&G |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Capitalized A&G |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | IT Device OH |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | IT Device OH |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35226632 | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Engineering/Mapping |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Indirect Labor - Electric |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Paid Time Off |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | AFUDC-Borrowed |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | AFUDC-Borrowed |  | 003/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | AFUDC-Equity |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | AFUDC-Equity |  | 003/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Benefits OH |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Building Service Overhead |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Capitalized A&G |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Fleet OH - Elec |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | IT Device OH |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226798 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH2 |  | Payroll Taxes OH |  | 002/2021
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | AFUDC-Borrowed |  | 003/2021
35226799 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH3 |  | AFUDC-Equity |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Paid Time Off |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Benefits OH |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Building Service Overhead |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Capitalized A&G |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | IT Device OH |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226819 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Contracts |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Design Drafting Services |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Design Drafting Services - Overtime |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Electric Estimating |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Electric Estimating |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Electric Estimating Overtime |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Electric Estimating Overtime |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Engineering/Mapping |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Engineering/Mapping |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Indirect Labor - Electric |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Indirect Labor - Electric |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Mapping |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Paid Time Off |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Paid Time Off |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | AFUDC-Borrowed |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | AFUDC-Borrowed |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | AFUDC-Equity |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | AFUDC-Equity |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Benefits OH |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Benefits OH |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Building Service Overhead |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Building Service Overhead |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Capitalized A&G |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Capitalized A&G |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Fleet OH - Elec |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Fleet OH - Elec |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | IT Device OH |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | IT Device OH |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Payroll Taxes OH |  | 002/2021
35226845 | ECOP-DIAMOND SPRINGS 1107-H02-LR1402-PH2 |  | Payroll Taxes OH |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Consulting Services - Engineering |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Construction |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Construction |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Design Services |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Engineering/Mapping |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Engineering/Mapping |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Indirect Labor - Electric |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Indirect Labor - Electric |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Mapping |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Mapping |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Paid Time Off |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Paid Time Off |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | AFUDC-Borrowed |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | AFUDC-Borrowed |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | AFUDC-Equity |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | AFUDC-Equity |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Benefits OH |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Benefits OH |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Building Service Overhead |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Building Service Overhead |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Capitalized A&G |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Capitalized A&G |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Fleet OH - Elec |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Fleet OH - Elec |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | IT Device OH |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | IT Device OH |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Payroll Taxes OH |  | 002/2021
35226846 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.2 |  | Payroll Taxes OH |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Consulting Services - Engineering |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Construction |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Construction |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Engineering/Mapping |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Engineering/Mapping |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Indirect Labor - Electric |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Indirect Labor - Electric |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Mapping |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Mapping |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Paid Time Off |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Paid Time Off |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | AFUDC-Borrowed |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | AFUDC-Borrowed |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | AFUDC-Equity |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | AFUDC-Equity |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Benefits OH |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Benefits OH |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Building Service Overhead |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Building Service Overhead |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Capitalized A&G |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Capitalized A&G |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Fleet OH - Elec |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Fleet OH - Elec |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | IT Device OH |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | IT Device OH |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Payroll Taxes OH |  | 002/2021
35226847 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.3 |  | Payroll Taxes OH |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Environmental Contract |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Account Services |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Construction Overtime Services |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Engineering/Mapping |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Engineering/Mapping |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Hours - Straight Time |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Indirect Labor - Cust Care |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Indirect Labor - Electric |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Indirect Labor - IT |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Mapping |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Paid Time Off |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Paid Time Off |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | AFUDC-Borrowed |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | AFUDC-Borrowed |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | AFUDC-Equity |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | AFUDC-Equity |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Benefits OH |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Benefits OH |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Building Service Overhead |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Building Service Overhead |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Capitalized A&G |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Capitalized A&G |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Fleet OH - Elec |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Fleet OH - Elec |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | IT Device OH |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | IT Device OH |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Operation Mgmt & Support - IT |  | 003/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Payroll Taxes OH |  | 002/2021
35226848 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.2 |  | Payroll Taxes OH |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Environmental Contract |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Consulting Services - Engineering |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Engineering/Mapping |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Engineering/Mapping |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Indirect Labor - Electric |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Indirect Labor - Electric |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Indirect Labor - Environmental Land |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Land Surveying & Engineering Supprt-Misc |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Mapping |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Paid Time Off |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Paid Time Off |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | AFUDC-Borrowed |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | AFUDC-Borrowed |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | AFUDC-Equity |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | AFUDC-Equity |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Benefits OH |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Benefits OH |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Building Service Overhead |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Building Service Overhead |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Capitalized A&G |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Capitalized A&G |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Fleet OH - Elec |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Fleet OH - Elec |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | IT Device OH |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | IT Device OH |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Payroll Taxes OH |  | 002/2021
35226849 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.3 |  | Payroll Taxes OH |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Environmental Contract |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Consulting Services - Engineering |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Account Services |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Administration |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Construction |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Engineering/Mapping |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Engineering/Mapping |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Indirect Labor - Cust Care |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Indirect Labor - Electric |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Mapping |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Paid Time Off |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Paid Time Off |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | AFUDC-Borrowed |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | AFUDC-Borrowed |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | AFUDC-Equity |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | AFUDC-Equity |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Benefits OH |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Benefits OH |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Building Service Overhead |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Building Service Overhead |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Capitalized A&G |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Capitalized A&G |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Fleet OH - Elec |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Fleet OH - Elec |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | IT Device OH |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | IT Device OH |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Payroll Taxes OH |  | 002/2021
35226850 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.4 |  | Payroll Taxes OH |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Environmental Contract |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Consulting Services - Engineering |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Account Services |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Administration |  | 004/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Engineering/Mapping |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Engineering/Mapping |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Indirect Labor - Cust Care |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Indirect Labor - Electric |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Indirect Labor - Electric |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Mapping |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Paid Time Off |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Paid Time Off |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | AFUDC-Borrowed |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | AFUDC-Equity |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | AFUDC-Equity |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Benefits OH |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Benefits OH |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Building Service Overhead |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Building Service Overhead |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Capitalized A&G |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Capitalized A&G |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Fleet OH - Elec |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Fleet OH - Elec |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | IT Device OH |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | IT Device OH |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Payroll Taxes OH |  | 002/2021
35226851 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.5 |  | Payroll Taxes OH |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Account Services |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Construction |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Construction |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Electric Estimating |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Electric Estimating |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Electric Estimating Overtime |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Electric Estimating Overtime |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Engineering/Mapping |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Indirect Labor - Cust Care |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Indirect Labor - Electric |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Indirect Labor - Electric |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Mapping |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Mapping |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Paid Time Off |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Paid Time Off |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | AFUDC-Borrowed |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | AFUDC-Borrowed |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | AFUDC-Equity |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | AFUDC-Equity |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Benefits OH |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Benefits OH |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Building Service Overhead |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Building Service Overhead |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Capitalized A&G |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Capitalized A&G |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Fleet OH - Elec |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Fleet OH - Elec |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | IT Device OH |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | IT Device OH |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Payroll Taxes OH |  | 002/2021
35226852 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.2 |  | Payroll Taxes OH |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Account Services |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Construction |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Construction |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Design Drafting Services |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Electric Estimating |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Electric Estimating |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Electric Estimating Overtime |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Engineering/Mapping |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Engineering/Mapping |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Indirect Labor - Cust Care |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Indirect Labor - Electric |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Indirect Labor - Electric |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Mapping |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Mapping |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Paid Time Off |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Paid Time Off |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | AFUDC-Borrowed |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | AFUDC-Borrowed |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | AFUDC-Equity |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | AFUDC-Equity |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Benefits OH |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Benefits OH |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Building Service Overhead |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Building Service Overhead |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Capitalized A&G |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Capitalized A&G |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Fleet OH - Elec |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Fleet OH - Elec |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | IT Device OH |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | IT Device OH |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Payroll Taxes OH |  | 002/2021
35226853 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.3 |  | Payroll Taxes OH |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Construction |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Construction |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating Doubletime |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating Doubletime |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating Overtime |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Electric Estimating Overtime |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Engineering/Mapping |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Indirect Labor - Electric |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Indirect Labor - Electric |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Mapping |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Mapping |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Paid Time Off |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Paid Time Off |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | AFUDC-Borrowed |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | AFUDC-Borrowed |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | AFUDC-Equity |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | AFUDC-Equity |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Benefits OH |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Benefits OH |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Building Service Overhead |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Building Service Overhead |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Capitalized A&G |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Capitalized A&G |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Fleet OH - Elec |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Fleet OH - Elec |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | IT Device OH |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | IT Device OH |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Payroll Taxes OH |  | 002/2021
35226854 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.4 |  | Payroll Taxes OH |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Construction |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Construction |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Electric Estimating |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Electric Estimating |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Electric Estimating Overtime |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Engineering/Mapping |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Indirect Labor - Electric |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Indirect Labor - Electric |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Mapping |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Mapping |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Paid Time Off |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Paid Time Off |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | AFUDC-Borrowed |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | AFUDC-Borrowed |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | AFUDC-Equity |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | AFUDC-Equity |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Benefits OH |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Benefits OH |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Building Service Overhead |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Building Service Overhead |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Capitalized A&G |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Capitalized A&G |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Fleet OH - Elec |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Fleet OH - Elec |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | IT Device OH |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | IT Device OH |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Payroll Taxes OH |  | 002/2021
35226856 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH3.5 |  | Payroll Taxes OH |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Administrative Services - OT |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Indirect Labor - Electric |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Indirect Labor - Electric |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Paid Time Off |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Paid Time Off |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Project Management Overtime |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Project Management Services |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | AFUDC-Borrowed |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | AFUDC-Borrowed |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | AFUDC-Equity |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | AFUDC-Equity |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Benefits OH |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Benefits OH |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Building Service Overhead |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Building Service Overhead |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Capitalized A&G |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Capitalized A&G |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Fleet OH - Elec |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Fleet OH - Elec |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | IT Device OH |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | IT Device OH |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Payroll Taxes OH |  | 002/2021
35226857 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.2 |  | Payroll Taxes OH |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Indirect Labor - Electric |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Indirect Labor - Electric |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Paid Time Off |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Paid Time Off |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Project Management Overtime |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Project Management Services |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | AFUDC-Borrowed |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | AFUDC-Borrowed |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | AFUDC-Equity |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | AFUDC-Equity |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Benefits OH |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Benefits OH |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Building Service Overhead |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Building Service Overhead |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Capitalized A&G |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Capitalized A&G |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Fleet OH - Elec |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Fleet OH - Elec |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | IT Device OH |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | IT Device OH |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Payroll Taxes OH |  | 002/2021
35226858 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.3 |  | Payroll Taxes OH |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Account Services |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Engineering/Mapping |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Indirect Labor - Cust Care |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Indirect Labor - Electric |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Indirect Labor - Electric |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Paid Time Off |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Paid Time Off |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Project Management Overtime |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Project Management Services |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | AFUDC-Borrowed |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | AFUDC-Borrowed |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | AFUDC-Equity |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | AFUDC-Equity |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Benefits OH |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Benefits OH |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Building Service Overhead |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Building Service Overhead |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Capitalized A&G |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Capitalized A&G |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Fleet OH - Elec |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Fleet OH - Elec |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | IT Device OH |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | IT Device OH |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Payroll Taxes OH |  | 002/2021
35226859 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.4 |  | Payroll Taxes OH |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Engineering/Mapping |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Indirect Labor - Electric |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Indirect Labor - Electric |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Paid Time Off |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Paid Time Off |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Project Management Overtime |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Project Management Services |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | AFUDC-Borrowed |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | AFUDC-Borrowed |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | AFUDC-Equity |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | AFUDC-Equity |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Benefits OH |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Benefits OH |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Building Service Overhead |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Building Service Overhead |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Capitalized A&G |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Capitalized A&G |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Fleet OH - Elec |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Fleet OH - Elec |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | IT Device OH |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | IT Device OH |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Payroll Taxes OH |  | 002/2021
35226861 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.5 |  | Payroll Taxes OH |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Engineering/Mapping |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Indirect Labor - Electric |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Indirect Labor - Electric |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Paid Time Off |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Paid Time Off |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Project Management Overtime |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Project Management Overtime |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Project Management Services |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | AFUDC-Borrowed |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | AFUDC-Borrowed |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | AFUDC-Equity |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | AFUDC-Equity |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Benefits OH |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Benefits OH |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Building Service Overhead |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Building Service Overhead |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Capitalized A&G |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Capitalized A&G |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Fleet OH - Elec |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Fleet OH - Elec |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | IT Device OH |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | IT Device OH |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Payroll Taxes OH |  | 002/2021
35226862 | ECOP-MIDDLETOWN 1101-H12-LR548-PH1.6 |  | Payroll Taxes OH |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Engineering/Mapping |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Paid Time Off |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Project Management Overtime |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Project Management Services |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | AFUDC-Borrowed |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | AFUDC-Equity |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Benefits OH |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Building Service Overhead |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Capitalized A&G |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Fleet OH - Elec |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | IT Device OH |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226863 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.2 |  | Payroll Taxes OH |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Engineering/Mapping |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Indirect Labor - Electric |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Paid Time Off |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Project Management Overtime |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Project Management Services |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | AFUDC-Borrowed |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | AFUDC-Equity |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Benefits OH |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Building Service Overhead |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Capitalized A&G |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Fleet OH - Elec |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | IT Device OH |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226864 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.3 |  | Payroll Taxes OH |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Engineering/Mapping |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Paid Time Off |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Project Management Overtime |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Project Management Services |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | AFUDC-Borrowed |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | AFUDC-Equity |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Benefits OH |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Building Service Overhead |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Capitalized A&G |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Fleet OH - Elec |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | IT Device OH |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226865 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.4 |  | Payroll Taxes OH |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Indirect Labor - Electric |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Paid Time Off |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Project Management Overtime |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Project Management Services |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | AFUDC-Equity |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Benefits OH |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Building Service Overhead |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Capitalized A&G |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Fleet OH - Elec |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | IT Device OH |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226866 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.5 |  | Payroll Taxes OH |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Engineering/Mapping |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Indirect Labor - Electric |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Paid Time Off |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Project Management Services |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | AFUDC-Borrowed |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | AFUDC-Equity |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Benefits OH |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Building Service Overhead |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Capitalized A&G |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Fleet OH - Elec |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | IT Device OH |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226870 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.6 |  | Payroll Taxes OH |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Indirect Labor - Electric |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Indirect Labor - Environmental Land |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Paid Time Off |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Project Management Overtime |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Project Management Services |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | AFUDC-Borrowed |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | AFUDC-Equity |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Benefits OH |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Building Service Overhead |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Capitalized A&G |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Fleet OH - Elec |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | IT Device OH |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226871 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.7 |  | Payroll Taxes OH |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Indirect Labor - Electric |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Indirect Labor - Environmental Land |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Paid Time Off |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Project Management Overtime |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Project Management Services |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | AFUDC-Borrowed |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | AFUDC-Equity |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Benefits OH |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Building Service Overhead |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Capitalized A&G |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Fleet OH - Elec |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | IT Device OH |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226872 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.8 |  | Payroll Taxes OH |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Engineering/Mapping |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Indirect Labor - Electric |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Indirect Labor - Environmental Land |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Paid Time Off |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Project Management Overtime |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Project Management Services |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | AFUDC-Borrowed |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | AFUDC-Equity |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Benefits OH |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Building Service Overhead |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Capitalized A&G |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Fleet OH - Elec |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | IT Device OH |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226873 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.9 |  | Payroll Taxes OH |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Indirect Labor - Electric |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Indirect Labor - Environmental Land |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Paid Time Off |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Project Management Overtime |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Project Management Services |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | AFUDC-Borrowed |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | AFUDC-Equity |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Benefits OH |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Building Service Overhead |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Capitalized A&G |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Fleet OH - Elec |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | IT Device OH |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Operation Mgmt & Support - Electric |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35226878 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.10 |  | Payroll Taxes OH |  | 003/2021
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 |  | AFUDC-Borrowed |  | 003/2021
35226900 | CWSP-WILDWOOD 1101-LR 1454-TEHAMA CO PH4 |  | AFUDC-Equity |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Engineering/Mapping |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Indirect Labor - Electric |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Indirect Labor - Environmental Land |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Paid Time Off |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Project Management Overtime |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Project Management Services |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | AFUDC-Borrowed |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | AFUDC-Equity |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Benefits OH |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Building Service Overhead |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Capitalized A&G |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Fleet OH - Elec |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | IT Device OH |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227001 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.11 |  | Payroll Taxes OH |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Engineering/Mapping |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Indirect Labor - Electric |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Indirect Labor - Environmental Land |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Paid Time Off |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Project Management Overtime |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Project Management Services |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | AFUDC-Borrowed |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | AFUDC-Equity |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Benefits OH |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Building Service Overhead |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Capitalized A&G |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Fleet OH - Elec |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | IT Device OH |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227002 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.12 |  | Payroll Taxes OH |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Administrative Services - OT |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Engineering/Mapping |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Indirect Labor - Electric |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Indirect Labor - Environmental Land |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Paid Time Off |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Project Management Overtime |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Project Management Services |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | AFUDC-Borrowed |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | AFUDC-Equity |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Benefits OH |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Building Service Overhead |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Capitalized A&G |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Fleet OH - Elec |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | IT Device OH |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227003 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.13 |  | Payroll Taxes OH |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Administrative Services - OT |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Engineering/Mapping |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Indirect Labor - Electric |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Indirect Labor - Environmental Land |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Paid Time Off |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Project Management Overtime |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Project Management Services |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | AFUDC-Borrowed |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | AFUDC-Equity |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Benefits OH |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Building Service Overhead |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Capitalized A&G |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Fleet OH - Elec |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | IT Device OH |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227004 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.14 |  | Payroll Taxes OH |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Administrative Services - OT |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Indirect Labor - Electric |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Paid Time Off |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Paid Time Off |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Project Management Overtime |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Project Management Services |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | AFUDC-Borrowed |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | AFUDC-Borrowed |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | AFUDC-Equity |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | AFUDC-Equity |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Benefits OH |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Benefits OH |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Building Service Overhead |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Building Service Overhead |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Capitalized A&G |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Capitalized A&G |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Fleet OH - Elec |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | IT Device OH |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | IT Device OH |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Payroll Taxes OH |  | 002/2021
35227007 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.2 |  | Payroll Taxes OH |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Administrative Services - OT |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Administrative Services - OT |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Engineering/Mapping |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Indirect Labor - Electric |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Indirect Labor - Environmental Land |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Paid Time Off |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Paid Time Off |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Project Management Overtime |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Project Management Services |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | AFUDC-Borrowed |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | AFUDC-Borrowed |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | AFUDC-Equity |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | AFUDC-Equity |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Benefits OH |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Benefits OH |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Building Service Overhead |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Building Service Overhead |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Capitalized A&G |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Capitalized A&G |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Fleet OH - Elec |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | IT Device OH |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | IT Device OH |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Payroll Taxes OH |  | 002/2021
35227010 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.3 |  | Payroll Taxes OH |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Indirect Labor - Electric |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Paid Time Off |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Project Management Overtime |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Project Management Services |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | AFUDC-Borrowed |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | AFUDC-Equity |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Benefits OH |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Building Service Overhead |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Capitalized A&G |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Fleet OH - Elec |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | IT Device OH |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227015 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.5 |  | Payroll Taxes OH |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Administrative Services - Double Time |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Administrative Services - OT |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Indirect Labor - Electric |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Paid Time Off |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Paid Time Off |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Project Management Overtime |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Project Management Services |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | AFUDC-Borrowed |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | AFUDC-Borrowed |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | AFUDC-Equity |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | AFUDC-Equity |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Benefits OH |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Benefits OH |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Building Service Overhead |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Building Service Overhead |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Capitalized A&G |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Capitalized A&G |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Fleet OH - Elec |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | IT Device OH |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | IT Device OH |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Payroll Taxes OH |  | 002/2021
35227018 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.6 |  | Payroll Taxes OH |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Administrative Services - OT |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Indirect Labor - Electric |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Indirect Labor - Environmental Land |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Paid Time Off |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Paid Time Off |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Project Management Overtime |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Project Management Services |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | AFUDC-Borrowed |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | AFUDC-Borrowed |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | AFUDC-Equity |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | AFUDC-Equity |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Benefits OH |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Benefits OH |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Building Service Overhead |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Building Service Overhead |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Capitalized A&G |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Capitalized A&G |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Fleet OH - Elec |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | IT Device OH |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | IT Device OH |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Payroll Taxes OH |  | 002/2021
35227021 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.7 |  | Payroll Taxes OH |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Administrative Services - OT |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Indirect Labor - Electric |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Indirect Labor - Environmental Land |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Paid Time Off |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Paid Time Off |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Project Management Overtime |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Project Management Services |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | AFUDC-Borrowed |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | AFUDC-Borrowed |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | AFUDC-Equity |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | AFUDC-Equity |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Benefits OH |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Benefits OH |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Building Service Overhead |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Building Service Overhead |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Capitalized A&G |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Capitalized A&G |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Fleet OH - Elec |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | IT Device OH |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | IT Device OH |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Payroll Taxes OH |  | 002/2021
35227025 | ECOP-MIDDLETOWN 1101-H12-LR548-PH3.8 |  | Payroll Taxes OH |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Account Services |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Engineering/Mapping |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Indirect Labor - Electric |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Paid Time Off |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | AFUDC-Borrowed |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | AFUDC-Equity |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Benefits OH |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Building Service Overhead |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Capitalized A&G |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Fleet OH - Elec |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | IT Device OH |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227027 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.2 |  | Payroll Taxes OH |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Account Services |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Engineering/Mapping |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Indirect Labor - Cust Care |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Indirect Labor - Electric |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Paid Time Off |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | AFUDC-Borrowed |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | AFUDC-Equity |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Benefits OH |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Building Service Overhead |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Capitalized A&G |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Fleet OH - Elec |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | IT Device OH |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227028 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.3 |  | Payroll Taxes OH |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Engineering/Mapping |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Indirect Labor - Electric |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Paid Time Off |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | AFUDC-Borrowed |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | AFUDC-Equity |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Benefits OH |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Building Service Overhead |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Capitalized A&G |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Fleet OH - Elec |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | IT Device OH |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227029 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.4 |  | Payroll Taxes OH |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Administrative Services - OT |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Engineering/Mapping |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Indirect Labor - Electric |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Paid Time Off |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | AFUDC-Borrowed |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | AFUDC-Equity |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Benefits OH |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Building Service Overhead |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Capitalized A&G |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Fleet OH - Elec |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | IT Device OH |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227030 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.5 |  | Payroll Taxes OH |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Acquisition - Misc |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Administrative Services - OT |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Engineering/Mapping |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Indirect Labor - Electric |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Paid Time Off |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | AFUDC-Borrowed |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | AFUDC-Equity |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Benefits OH |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Building Service Overhead |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Capitalized A&G |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Fleet OH - Elec |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | IT Device OH |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227031 | ECOP-MIDDLETOWN 1101-H16-LR48212 PH1.6 |  | Payroll Taxes OH |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Administration |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Paid Time Off |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Paid Time Off |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Project Management Overtime |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Project Management Overtime |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Benefits OH |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Benefits OH |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Building Service Overhead |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Building Service Overhead |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Capitalized A&G |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Capitalized A&G |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | IT Device OH |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | IT Device OH |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35227032 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Administration |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Paid Time Off |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Project Management Overtime |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Benefits OH |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Building Service Overhead |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Capitalized A&G |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | IT Device OH |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227033 | ECOP - PUEBLO 2102 - H01-LR792 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Inspection |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Contracts |  | 004/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Contracts |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Environmental Contract |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Helicopter Contract |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Traffic Control Contracts |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Traffic Control Contracts |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Administrative Services - OT |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Doubletime Services |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Doubletime Services |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Overtime Services |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Overtime Services |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Electric Estimating |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Electric Estimating Doubletime |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Engineering/Mapping |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Engineering/Mapping |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Engineering/Mapping |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Indirect Labor - Electric |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Indirect Labor - Electric |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Indirect Labor - Electric |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Indirect Labor - Environmental Land |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Indirect Labor - Environmental Land |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Maint & Operate Doubletime Services |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Manage L&EM |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Mapping |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Mapping |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Paid Time Off |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Paid Time Off |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Paid Time Off |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Construction Supplies |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Electl & Electronic Equipment Component |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Fabricated Structures |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Fabricated Structures |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Material Burden |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Material Burden |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Borrowed |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Borrowed |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Borrowed |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Equity |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Equity |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | AFUDC-Equity |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Benefits OH |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Benefits OH |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Benefits OH |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Building Service Overhead |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Building Service Overhead |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Building Service Overhead |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Capitalized A&G |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Capitalized A&G |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Capitalized A&G |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Cash Discount earned |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Cash Discount earned |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Cash Discount earned |  | 004/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Fleet OH - Elec |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Fleet OH - Elec |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Fleet OH - Elec |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | IT Device OH |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | IT Device OH |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | IT Device OH |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Minor Material OH |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Minor Material OH |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Operation Mgmt & Support - Electric |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Other Land Fees |  | 003/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Payroll Taxes OH |  | 001/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Payroll Taxes OH |  | 002/2021
35227096 | STRM - OAKHURST 1103 - LR 5120 PH 2 |  | Payroll Taxes OH |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Administrative Services - Double Time |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Engineering/Mapping |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Paid Time Off |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Benefits OH |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Building Service Overhead |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Capitalized A&G |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | IT Device OH |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227160 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Engineering/Mapping |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Paid Time Off |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Benefits OH |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Building Service Overhead |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Capitalized A&G |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | IT Device OH |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227161 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Administrative Services - Double Time |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Engineering/Mapping |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Paid Time Off |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Benefits OH |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Building Service Overhead |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Capitalized A&G |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | IT Device OH |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227162 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Engineering/Mapping |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Paid Time Off |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | AFUDC-Equity |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Benefits OH |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Building Service Overhead |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Capitalized A&G |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | IT Device OH |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227163 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Engineering/Mapping |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Paid Time Off |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | AFUDC-Equity |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Benefits OH |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Building Service Overhead |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Capitalized A&G |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | IT Device OH |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227164 | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Engineering/Mapping |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Indirect Labor - Electric |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Paid Time Off |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | AFUDC-Borrowed |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | AFUDC-Equity |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Benefits OH |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Building Service Overhead |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Capitalized A&G |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Fleet OH - Elec |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | IT Device OH |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227165 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 |  | Payroll Taxes OH |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Engineering/Mapping |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Indirect Labor - Electric |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Indirect Labor - Environmental Land |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Paid Time Off |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | AFUDC-Borrowed |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | AFUDC-Equity |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Benefits OH |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Building Service Overhead |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Capitalized A&G |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Fleet OH - Elec |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | IT Device OH |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227167 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 |  | Payroll Taxes OH |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Engineering/Mapping |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Indirect Labor - Electric |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Paid Time Off |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | AFUDC-Borrowed |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | AFUDC-Equity |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Benefits OH |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Building Service Overhead |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Capitalized A&G |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Fleet OH - Elec |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | IT Device OH |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227168 | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 |  | Payroll Taxes OH |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction Inspection |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Contracts |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Contracts |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Environmental Contract |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Helicopter Contract |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction Doubletime Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction Overtime Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electric Estimating |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electric Estimating Doubletime |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electric Estimating Overtime |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Engineering/Mapping |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Engineering/Mapping |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Environmental Planning & Permitting-Misc |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Environmental Planning & Permitting-Misc |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Hours - Overtime |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Hours - Overtime |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Hours - Straight Time |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Hours - Straight Time |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - Electric |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - Electric |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - Electric |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - Environmental Land |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - Environmental Land |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - IT |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Indirect Labor - IT |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Maint & Operate Doubletime Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Maintain & Operate Overtime Services |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Maintain & Operate Overtime Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Maintain & Operate Services |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Maintain & Operate Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Management Services |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Mapping |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Paid Time Off |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Paid Time Off |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Paid Time Off |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Communication & Signaling Equipment |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Communication & Signaling Equipment |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Conductors, Cable & Wire Connectors |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Conductors, Cable & Wire Connectors |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction Supplies |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Construction Supplies |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electl & Electronic Equipment Component |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electrical Specialties |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Electrical Specialties |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Fabricated Structures |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Material Burden |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Material Burden |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Materials Not Otherwise Classified |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Transformers, Regulators & Capacitors |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Benefits OH |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Benefits OH |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Benefits OH |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Building Service Overhead |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Building Service Overhead |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Building Service Overhead |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Capitalized A&G |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Capitalized A&G |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Capitalized A&G |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Cash Discount earned |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Cellular Phone Use |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Fleet OH - Elec |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Fleet OH - Elec |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Fleet OH - Elec |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | IT Device OH |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | IT Device OH |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | IT Device OH |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Minor Material OH |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Minor Material OH |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - Electric |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - IT |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Operation Mgmt & Support - IT |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Payroll Taxes OH |  | 001/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Payroll Taxes OH |  | 002/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Payroll Taxes OH |  | 003/2021
35227201 | STRM - OAKHURST 1103 - LR 5120 PH 3 |  | Reimbursed Mileage Expense |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Environmental Contract |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Design Overtime Services |  | 004/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Design Services |  | 004/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating |  | 004/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating Doubletime |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating Doubletime |  | 004/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating Overtime |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Electric Estimating Overtime |  | 004/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Engineering/Mapping |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Engineering/Mapping |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Mapping |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Paid Time Off |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Paid Time Off |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | AFUDC-Equity |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | AFUDC-Equity |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Benefits OH |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Benefits OH |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Building Service Overhead |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Building Service Overhead |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Capitalized A&G |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Capitalized A&G |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | IT Device OH |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | IT Device OH |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35227260 | CWSP - COARSEGOLD 2104CB PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Consulting Services - Engineering |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Design Drafting Services |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Design Drafting Services |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Design Drafting Services |  | 004/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Design Drafting Services - Overtime |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Design Drafting Services - Overtime |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Electric Estimating |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Electric Estimating |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Electric Estimating Doubletime |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Electric Estimating Overtime |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Electric Estimating Overtime |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Engineering/Mapping |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Engineering/Mapping |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Mapping |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Paid Time Off |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Paid Time Off |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | AFUDC-Equity |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | AFUDC-Equity |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Benefits OH |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Benefits OH |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Building Service Overhead |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Building Service Overhead |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Capitalized A&G |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Capitalized A&G |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | IT Device OH |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | IT Device OH |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35227261 | CWSP - COARSEGOLD 2104CB PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Consulting Services - Engineering |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Acquisition - Misc |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Administration |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Construction |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Construction Overtime Services |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating |  | 004/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating Doubletime |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating Overtime |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Electric Estimating Overtime |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Engineering/Mapping |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Engineering/Mapping |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Indirect Labor - Electric |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Land Rights - Misc |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Mapping |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Paid Time Off |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Paid Time Off |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | AFUDC-Borrowed |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | AFUDC-Equity |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | AFUDC-Equity |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Benefits OH |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Benefits OH |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Building Service Overhead |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Building Service Overhead |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Capitalized A&G |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Capitalized A&G |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Fleet OH - Elec |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | IT Device OH |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | IT Device OH |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Payroll Taxes OH |  | 002/2021
35227262 | CWSP - COARSEGOLD 2104CB PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Environmental Contract |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Design Drafting Services |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Design Drafting Services - Overtime |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Electric Estimating |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Electric Estimating |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Electric Estimating Overtime |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Electric Estimating Overtime |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Engineering/Mapping |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Engineering/Mapping |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Indirect Labor - Electric |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Indirect Labor - Electric |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Mapping |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Paid Time Off |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Paid Time Off |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | AFUDC-Borrowed |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | AFUDC-Borrowed |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | AFUDC-Equity |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | AFUDC-Equity |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Benefits OH |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Benefits OH |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Building Service Overhead |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Building Service Overhead |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Capitalized A&G |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Capitalized A&G |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Fleet OH - Elec |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Fleet OH - Elec |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | IT Device OH |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | IT Device OH |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Lodging |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Meals Expense |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Payroll Taxes OH |  | 002/2021
35227263 | CWSP - MARIPOSA 2102CB PH 2 |  | Payroll Taxes OH |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Construction |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Mapping |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Mapping |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Paid Time Off |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Paid Time Off |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Benefits OH |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Benefits OH |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Building Service Overhead |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Building Service Overhead |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Capitalized A&G |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Capitalized A&G |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | IT Device OH |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | IT Device OH |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35227655 | CWSP - KIRKER 2104442850 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Account Services |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Paid Time Off |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Benefits OH |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Building Service Overhead |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Capitalized A&G |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | IT Device OH |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227860 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Account Services |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Engineering/Mapping |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Indirect Labor - Cust Care |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Paid Time Off |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Benefits OH |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Building Service Overhead |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Capitalized A&G |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | IT Device OH |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227861 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Account Services |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Engineering/Mapping |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Indirect Labor - Cust Care |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Paid Time Off |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Benefits OH |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Building Service Overhead |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Capitalized A&G |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | IT Device OH |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227862 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Account Services |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Engineering/Mapping |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Indirect Labor - Cust Care |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Paid Time Off |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Benefits OH |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Building Service Overhead |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Capitalized A&G |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | IT Device OH |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227863 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Account Services |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Engineering/Mapping |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Indirect Labor - Cust Care |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Indirect Labor - Electric |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Paid Time Off |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | AFUDC-Borrowed |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | AFUDC-Equity |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Benefits OH |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Building Service Overhead |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Capitalized A&G |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Fleet OH - Elec |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | IT Device OH |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227864 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 |  | Payroll Taxes OH |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Account Services |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Engineering/Mapping |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Indirect Labor - Cust Care |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Paid Time Off |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | AFUDC-Equity |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Benefits OH |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Building Service Overhead |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Capitalized A&G |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | IT Device OH |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227866 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Construction Inspection |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Construction Inspection |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Account Services |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Engineering/Mapping |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Indirect Labor - Cust Care |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Indirect Labor - Electric |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Indirect Labor - Electric |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Mapping |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Mapping |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Paid Time Off |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Paid Time Off |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | AFUDC-Borrowed |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | AFUDC-Borrowed |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | AFUDC-Equity |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | AFUDC-Equity |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Benefits OH |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Benefits OH |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Building Service Overhead |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Building Service Overhead |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Capitalized A&G |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Capitalized A&G |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Fleet OH - Elec |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Fleet OH - Elec |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | IT Device OH |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | IT Device OH |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Operation Mgmt & Support - Electric |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Payroll Taxes OH |  | 002/2021
35227867 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 |  | Payroll Taxes OH |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Account Services |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Engineering/Mapping |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Indirect Labor - Cust Care |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Indirect Labor - Electric |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Indirect Labor - Environmental Land |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Paid Time Off |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | AFUDC-Borrowed |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | AFUDC-Equity |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Benefits OH |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Building Service Overhead |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Capitalized A&G |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Fleet OH - Elec |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | IT Device OH |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Operation Mgmt & Support - Electric |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35227868 | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 |  | Payroll Taxes OH |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Account Services |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Engineering/Mapping |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Indirect Labor - Cust Care |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Land Rights - Misc |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Paid Time Off |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | AFUDC-Borrowed |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | AFUDC-Equity |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Benefits OH |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Building Service Overhead |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Capitalized A&G |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Fleet OH - Elec |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | IT Device OH |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35228186 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 |  | Payroll Taxes OH |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Account Services |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Engineering/Mapping |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Indirect Labor - Cust Care |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Indirect Labor - Electric |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Paid Time Off |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | AFUDC-Borrowed |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | AFUDC-Equity |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Benefits OH |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Building Service Overhead |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Capitalized A&G |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Fleet OH - Elec |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | IT Device OH |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35228187 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 |  | Payroll Taxes OH |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Account Services |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Engineering/Mapping |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Indirect Labor - Cust Care |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Paid Time Off |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | AFUDC-Borrowed |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | AFUDC-Equity |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Benefits OH |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Building Service Overhead |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Capitalized A&G |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Fleet OH - Elec |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | IT Device OH |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35228188 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 |  | Payroll Taxes OH |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Contracts |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Contracts |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Contracts |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Construction Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Construction Contract |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Construction Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Construction Contract |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Contract |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Contract |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Helicopter Contract |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Helicopter Contract |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Administration |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Administration |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Administrative Services - OT |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Administrative Services - OT |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Apprentice |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Apprentice DT |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Apprentice OT |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Apprentice OT |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Construction |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Construction |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Construction Doubletime Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Construction Doubletime Services |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Construction Overtime Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Construction Overtime Services |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Design Drafting Services - Overtime |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Design Overtime Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Design Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Design Services Double Time |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Design Services Double Time |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Estimating |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Estimating Doubletime |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Estimating Overtime |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Electric Estimating Overtime |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Engineering Doubletime |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Engineering Services - OT |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Engineering/Mapping |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Engineering/Mapping |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Planning & Permitting-Misc |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Planning & Permitting-Misc |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Environmental Services |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Electric |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Electric |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Electric |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Environmental Land |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Environmental Land |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Gas |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Indirect Labor - Gas |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Land Rights - Misc |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Land Rights - Misc |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Mapping |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Mapping |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Paid Time Off |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Paid Time Off |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Paid Time Off |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Project Management Overtime |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Project Management Overtime |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Project Management Services |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Project Management Services |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Vegetation Management - Misc |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Conductors, Cable & Wire Connectors |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Construction Supplies |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Electl & Electronic Equipment Component |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Electrical Specialties |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Fabricated Structures |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Material Burden |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Material Burden |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Printed Matls, Signs, Off Suppl & Furn |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Borrowed |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Borrowed |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Borrowed |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Equity |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Equity |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | AFUDC-Equity |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Benefits OH |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Benefits OH |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Benefits OH |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Building Service Overhead |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Building Service Overhead |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Building Service Overhead |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Capitalized A&G |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Capitalized A&G |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Capitalized A&G |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Cash Discount earned |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Cash Discount earned |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Cash Discount earned |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Fleet OH - Elec |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Fleet OH - Elec |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Fleet OH - Elec |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Fleet OH - Gas |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Fleet OH - Gas |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | IT Device OH |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | IT Device OH |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | IT Device OH |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Land Acquisition Services |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Land Acquisition Services |  | 004/2021
35228449 | RIO DELL STORM REBUILD |  | Minor Material OH |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Minor Material OH |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Electric |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Electric |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Electric |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Gas |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Operation Mgmt & Support - Gas |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Other Expenses |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Other Expenses |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Other Expenses |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Other Expenses |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Other Land Fees |  | 003/2021
35228449 | RIO DELL STORM REBUILD |  | Payroll Taxes OH |  | 001/2021
35228449 | RIO DELL STORM REBUILD |  | Payroll Taxes OH |  | 002/2021
35228449 | RIO DELL STORM REBUILD |  | Payroll Taxes OH |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Environmental Contract |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Consulting Services - Engineering |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Acquisition - Misc |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Design Drafting Services - Overtime |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Indirect Labor - Electric |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Indirect Labor - Environmental Land |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Management Services |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Management Services |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Mapping |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Paid Time Off |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | AFUDC-Borrowed |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | AFUDC-Borrowed |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | AFUDC-Equity |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | AFUDC-Equity |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Benefits OH |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Benefits OH |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Building Service Overhead |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Building Service Overhead |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Capitalized A&G |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Capitalized A&G |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Fleet OH - Elec |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | IT Device OH |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | IT Device OH |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Operation Mgmt & Support - Electric |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Payroll Taxes OH |  | 002/2021
35229051 | REMG 299/300 - CORNING 1102, TURRI ELLIS |  | Payroll Taxes OH |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Account Services |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Administrative Services - OT |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Engineering/Mapping |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Indirect Labor - Cust Care |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Indirect Labor - Environmental Land |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Mapping |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Paid Time Off |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Paid Time Off |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Project Management Services |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Benefits OH |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Benefits OH |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Building Service Overhead |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Building Service Overhead |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Capitalized A&G |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Capitalized A&G |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | IT Device OH |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | IT Device OH |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35229119 | CWSP - MIDDLETOWN 1101118494 PH 1.2 |  | Permits/FeesLand Surveying Services |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Consulting Services - Engineering |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Acquisition - Misc |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Construction |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Construction Overtime Services |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Indirect Labor - Electric |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Indirect Labor - Environmental Land |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Land Surveying & Engineering Supprt-Misc |  | 004/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Management Services |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Mapping |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Mapping |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Paid Time Off |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Paid Time Off |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | AFUDC-Borrowed |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | AFUDC-Equity |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Benefits OH |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Benefits OH |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Building Service Overhead |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Building Service Overhead |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Capitalized A&G |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Capitalized A&G |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Fleet OH - Elec |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | IT Device OH |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | IT Device OH |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Payroll Taxes OH |  | 002/2021
35231543 | CWSP - TIDEWATER 210614072 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Consulting Services - Engineering |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Construction |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Construction Overtime Services |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Engineering/Mapping |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Indirect Labor - Electric |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Management Services |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Mapping |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Mapping |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Paid Time Off |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Paid Time Off |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | AFUDC-Borrowed |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | AFUDC-Equity |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Benefits OH |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Benefits OH |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Building Service Overhead |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Building Service Overhead |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Capitalized A&G |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Capitalized A&G |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Fleet OH - Elec |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | IT Device OH |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | IT Device OH |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Payroll Taxes OH |  | 002/2021
35231544 | CWSP - TIDEWATER 210614072 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Consulting Services - Engineering |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Account Services |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Construction |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Construction |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Engineering/Mapping |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Engineering/Mapping |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Indirect Labor - Cust Care |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Indirect Labor - Electric |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Indirect Labor - Electric |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Mapping |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Mapping |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Paid Time Off |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Paid Time Off |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | AFUDC-Borrowed |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | AFUDC-Borrowed |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | AFUDC-Equity |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | AFUDC-Equity |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Benefits OH |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Benefits OH |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Building Service Overhead |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Building Service Overhead |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Capitalized A&G |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Capitalized A&G |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Fleet OH - Elec |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Fleet OH - Elec |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | IT Device OH |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | IT Device OH |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Operation Mgmt & Support - Electric |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Payroll Taxes OH |  | 002/2021
35231607 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.4 |  | Payroll Taxes OH |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Construction |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Construction |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Electric Estimating |  | 004/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Engineering/Mapping |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Indirect Labor - Electric |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Indirect Labor - Electric |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Mapping |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Mapping |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Paid Time Off |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Paid Time Off |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | AFUDC-Borrowed |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | AFUDC-Borrowed |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | AFUDC-Equity |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | AFUDC-Equity |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Benefits OH |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Benefits OH |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Building Service Overhead |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Building Service Overhead |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Capitalized A&G |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Capitalized A&G |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Fleet OH - Elec |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Fleet OH - Elec |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | IT Device OH |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | IT Device OH |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Payroll Taxes OH |  | 002/2021
35231608 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.6 |  | Payroll Taxes OH |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Account Services |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Acquisition - Misc |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Construction |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Construction |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Engineering/Mapping |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Engineering/Mapping |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Hours - Overtime |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Indirect Labor - Cust Care |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Indirect Labor - Electric |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Indirect Labor - Electric |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Indirect Labor - Environmental Land |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Indirect Labor - IT |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Mapping |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Mapping |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Paid Time Off |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Paid Time Off |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | AFUDC-Borrowed |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | AFUDC-Borrowed |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | AFUDC-Equity |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | AFUDC-Equity |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Benefits OH |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Benefits OH |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Building Service Overhead |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Building Service Overhead |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Capitalized A&G |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Capitalized A&G |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Fleet OH - Elec |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Fleet OH - Elec |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | IT Device OH |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | IT Device OH |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Operation Mgmt & Support - Electric |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Operation Mgmt & Support - IT |  | 003/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Payroll Taxes OH |  | 002/2021
35231609 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH1.5 |  | Payroll Taxes OH |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Engr/Dsgn and Engr, Proc & Constr Contra |  | 004/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Environmental Contract |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Consulting Services - Engineering |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Account Services |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Administration |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Administration |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Administration |  | 004/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Electric Estimating |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Electric Estimating Overtime |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Engineering/Mapping |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Engineering/Mapping |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Indirect Labor - Cust Care |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Indirect Labor - Electric |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Indirect Labor - Electric |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Indirect Labor - Environmental Land |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Indirect Labor - Environmental Land |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Mapping |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Paid Time Off |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Paid Time Off |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | AFUDC-Borrowed |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | AFUDC-Borrowed |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | AFUDC-Equity |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | AFUDC-Equity |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Benefits OH |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Benefits OH |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Building Service Overhead |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Building Service Overhead |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Capitalized A&G |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Capitalized A&G |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Fleet OH - Elec |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Fleet OH - Elec |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | IT Device OH |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | IT Device OH |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Operation Mgmt & Support - Electric |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Payroll Taxes OH |  | 002/2021
35232280 | CWSP-SHINGLE SPRINGS 2109-LR 9372-PH2.6 |  | Payroll Taxes OH |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Consulting Services - Engineering |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Administration |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Administration |  | 004/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Construction Overtime Services |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Engineering/Mapping |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Engineering/Mapping Services Overtime |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Indirect Labor - Electric |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Indirect Labor - Electric |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Land Rights - Misc |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Land Rights - Misc |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Mapping |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Paid Time Off |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Paid Time Off |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | AFUDC-Borrowed |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | AFUDC-Borrowed |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | AFUDC-Equity |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | AFUDC-Equity |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Benefits OH |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Benefits OH |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Building Service Overhead |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Building Service Overhead |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Capitalized A&G |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Capitalized A&G |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Fleet OH - Elec |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Fleet OH - Elec |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | IT Device OH |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | IT Device OH |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Operation Mgmt & Support - Electric |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Payroll Taxes OH |  | 002/2021
35232298 | FRRB - WYANDOTTE 1103 - W1 PH1.1 |  | Payroll Taxes OH |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Construction |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Indirect Labor - Electric |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Mapping |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Paid Time Off |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | AFUDC-Borrowed |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | AFUDC-Equity |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Benefits OH |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Building Service Overhead |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Capitalized A&G |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Fleet OH - Elec |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | IT Device OH |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232442 | CWSP - DESCHUTES 11049718 PH 2.2 |  | Payroll Taxes OH |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Construction |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Indirect Labor - Electric |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Mapping |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Paid Time Off |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | AFUDC-Borrowed |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | AFUDC-Equity |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Benefits OH |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Building Service Overhead |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Capitalized A&G |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Fleet OH - Elec |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | IT Device OH |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232443 | CWSP - DESCHUTES 11049718 PH 2.3 |  | Payroll Taxes OH |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Construction Overtime Services |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Indirect Labor - Electric |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Mapping |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Paid Time Off |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | AFUDC-Borrowed |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | AFUDC-Equity |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Benefits OH |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Building Service Overhead |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Capitalized A&G |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Fleet OH - Elec |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | IT Device OH |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232444 | CWSP - DESCHUTES 11049718 PH 2.4 |  | Payroll Taxes OH |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Acquisition - Misc |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Administration |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Administrative Services - OT |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Construction Overtime Services |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Design Drafting Services |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Design Drafting Services |  | 004/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Design Drafting Services - Overtime |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Design Drafting Services - Overtime |  | 004/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Engineering/Mapping |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Indirect Labor - Electric |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Indirect Labor - Environmental Land |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Land Rights - Misc |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Land Rights - Misc |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Land Rights - Misc |  | 004/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Mapping |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Paid Time Off |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Paid Time Off |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | AFUDC-Borrowed |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | AFUDC-Borrowed |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | AFUDC-Equity |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | AFUDC-Equity |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Benefits OH |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Benefits OH |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Building Service Overhead |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Building Service Overhead |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Capitalized A&G |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Capitalized A&G |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Fleet OH - Elec |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | IT Device OH |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | IT Device OH |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Payroll Taxes OH |  | 002/2021
35232718 | FRRB - WYANDOTTE 1103 - W2 PH2.1 |  | Payroll Taxes OH |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Account Services |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Indirect Labor - Cust Care |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Paid Time Off |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | AFUDC-Borrowed |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | AFUDC-Equity |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Benefits OH |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Building Service Overhead |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Capitalized A&G |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | IT Device OH |  | 003/2021
35232960 | CWSP - DESCHUTES 11049718 PH1.2 |  | Payroll Taxes OH |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Construction Overtime Services |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Mapping |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Paid Time Off |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Benefits OH |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Building Service Overhead |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Capitalized A&G |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | IT Device OH |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233038 | FRRB - WYANDOTTE 1103 - W1 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Engineering/Mapping |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Paid Time Off |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Benefits OH |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Building Service Overhead |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Capitalized A&G |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | IT Device OH |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233039 | FRRB - WYANDOTTE 1103 - W1 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Engineering/Mapping |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Paid Time Off |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Benefits OH |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Building Service Overhead |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Capitalized A&G |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | IT Device OH |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233300 | FRRB - WYANDOTTE 1103 - W1 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Engineering/Mapping |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Paid Time Off |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Benefits OH |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Building Service Overhead |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Capitalized A&G |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | IT Device OH |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233301 | FRRB - WYANDOTTE 1103 - W1 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Engineering/Mapping |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Indirect Labor - Electric |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Paid Time Off |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | AFUDC-Borrowed |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | AFUDC-Equity |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Benefits OH |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Building Service Overhead |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Capitalized A&G |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Fleet OH - Elec |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | IT Device OH |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233303 | FRRB - WYANDOTTE 1103 - W1 PH 1.7 |  | Payroll Taxes OH |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Construction Overtime Services |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Engineering/Mapping |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Indirect Labor - Electric |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Mapping |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Paid Time Off |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | AFUDC-Borrowed |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | AFUDC-Equity |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Benefits OH |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Building Service Overhead |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Capitalized A&G |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Fleet OH - Elec |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | IT Device OH |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233305 | FRRB - WYANDOTTE 1103 - W1 PH 1.9 |  | Payroll Taxes OH |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Engineering/Mapping |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Indirect Labor - Electric |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Paid Time Off |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | AFUDC-Borrowed |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | AFUDC-Equity |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Benefits OH |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Building Service Overhead |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Capitalized A&G |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Fleet OH - Elec |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | IT Device OH |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233306 | FRRB - WYANDOTTE 1103 - W1 PH1.10 |  | Payroll Taxes OH |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Engineering/Mapping |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Indirect Labor - Electric |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Paid Time Off |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | AFUDC-Borrowed |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | AFUDC-Equity |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Benefits OH |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Building Service Overhead |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Capitalized A&G |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Fleet OH - Elec |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | IT Device OH |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233307 | FRRB - WYANDOTTE 1103 - W1 PH1.11 |  | Payroll Taxes OH |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Engineering/Mapping |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Indirect Labor - Electric |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Paid Time Off |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | AFUDC-Borrowed |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | AFUDC-Equity |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Benefits OH |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Building Service Overhead |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Capitalized A&G |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Fleet OH - Elec |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | IT Device OH |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233308 | FRRB - WYANDOTTE 1103 - W1 PH1.12 |  | Payroll Taxes OH |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Construction Overtime Services |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Indirect Labor - Electric |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Mapping |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Paid Time Off |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | AFUDC-Borrowed |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | AFUDC-Equity |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Benefits OH |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Building Service Overhead |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Capitalized A&G |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Fleet OH - Elec |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | IT Device OH |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233310 | FRRB - WYANDOTTE 1103 - W1 PH1.14 |  | Payroll Taxes OH |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Design Drafting Services |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Engineering/Mapping |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Indirect Labor - Electric |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Paid Time Off |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | AFUDC-Borrowed |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | AFUDC-Equity |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Benefits OH |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Building Service Overhead |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Capitalized A&G |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Fleet OH - Elec |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | IT Device OH |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233311 | FRRB - WYANDOTTE 1103 - W2 - PH2.2 |  | Payroll Taxes OH |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Design Drafting Services |  | 004/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Design Drafting Services - Overtime |  | 004/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Engineering/Mapping |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Indirect Labor - Electric |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Paid Time Off |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | AFUDC-Borrowed |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | AFUDC-Equity |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Benefits OH |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Building Service Overhead |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Capitalized A&G |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Fleet OH - Elec |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | IT Device OH |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233312 | FRRB - WYANDOTTE 1103 - W2 - PH2.3 |  | Payroll Taxes OH |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Construction Overtime Services |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Design Drafting Services |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Design Drafting Services - Overtime |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Drafting Doubletime |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Drafting Doubletime |  | 004/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Engineering/Mapping |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Indirect Labor - Electric |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Mapping |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Paid Time Off |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | AFUDC-Borrowed |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | AFUDC-Equity |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Benefits OH |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Building Service Overhead |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Capitalized A&G |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Fleet OH - Elec |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | IT Device OH |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233314 | FRRB - WYANDOTTE 1103 - W2 - PH2.4 |  | Payroll Taxes OH |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Construction Overtime Services |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Engineering/Mapping |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Indirect Labor - Electric |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Mapping |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Paid Time Off |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | AFUDC-Equity |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Benefits OH |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Building Service Overhead |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Capitalized A&G |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Fleet OH - Elec |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | IT Device OH |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35233315 | FRRB - WYANDOTTE 1103 - W2 - PH2.5 |  | Payroll Taxes OH |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Engineering/Mapping |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Indirect Labor - Electric |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Indirect Labor - Environmental Land |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Paid Time Off |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | AFUDC-Borrowed |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | AFUDC-Equity |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Benefits OH |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Building Service Overhead |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Capitalized A&G |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Fleet OH - Elec |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | IT Device OH |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35235139 | FRRB - BIG BEND 1102 - LAKE MADRONE PH3 |  | Payroll Taxes OH |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Administration |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Engineering/Mapping |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Indirect Labor - Electric |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Land Rights - Misc |  | 004/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Management Services |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Paid Time Off |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | AFUDC-Borrowed |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | AFUDC-Equity |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Benefits OH |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Building Service Overhead |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Capitalized A&G |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Fleet OH - Elec |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | IT Device OH |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35235320 | FRRB - WYANDOTTE 1103 - W3 PH3.1 |  | Payroll Taxes OH |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Administration |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Engineering/Mapping |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Environmental Planning & Permitting-Misc |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Environmental Planning & Permitting-Misc |  | 004/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Indirect Labor - Electric |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Indirect Labor - Environmental Land |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Paid Time Off |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | AFUDC-Borrowed |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | AFUDC-Equity |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Benefits OH |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Building Service Overhead |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Capitalized A&G |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Fleet OH - Elec |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | IT Device OH |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35235669 | FRRB - WYANDOTTE 1103 - W4 PH4.1 |  | Payroll Taxes OH |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Engineering/Mapping |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Indirect Labor - Electric |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Paid Time Off |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | AFUDC-Borrowed |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | AFUDC-Equity |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Benefits OH |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Building Service Overhead |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Capitalized A&G |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Fleet OH - Elec |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | IT Device OH |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235670 | FRRB - WYANDOTTE 1103 - W5 PH5 |  | Payroll Taxes OH |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Engineering/Mapping |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Indirect Labor - Electric |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Paid Time Off |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | AFUDC-Borrowed |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | AFUDC-Equity |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Benefits OH |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Building Service Overhead |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Capitalized A&G |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Fleet OH - Elec |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | IT Device OH |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235674 | FRRB - BIG BEND 1102 - B1 PH1 |  | Payroll Taxes OH |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Engineering/Mapping |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Indirect Labor - Electric |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Paid Time Off |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | AFUDC-Borrowed |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | AFUDC-Equity |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Benefits OH |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Building Service Overhead |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Capitalized A&G |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Fleet OH - Elec |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | IT Device OH |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235676 | FRRB - BIG BEND 1102 - LAKE MADRONE PH4 |  | Payroll Taxes OH |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Engineering/Mapping |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Indirect Labor - Electric |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Paid Time Off |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | AFUDC-Borrowed |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | AFUDC-Equity |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Benefits OH |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Building Service Overhead |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Capitalized A&G |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Fleet OH - Elec |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | IT Device OH |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235677 | FRRB - BIG BEND 1102 - B4 PH4 |  | Payroll Taxes OH |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Engineering/Mapping |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Indirect Labor - Electric |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Paid Time Off |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | AFUDC-Borrowed |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | AFUDC-Equity |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Benefits OH |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Building Service Overhead |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Capitalized A&G |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Fleet OH - Elec |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | IT Device OH |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235702 | FRRB - KANAKA 1101 - K3 PH3 |  | Payroll Taxes OH |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Engineering/Mapping |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Indirect Labor - Electric |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Paid Time Off |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | AFUDC-Borrowed |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | AFUDC-Equity |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Benefits OH |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Building Service Overhead |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Capitalized A&G |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Fleet OH - Elec |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | IT Device OH |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235703 | FRRB - KANAKA 1101 - K4 PH4.1 |  | Payroll Taxes OH |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Engineering/Mapping |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Indirect Labor - Electric |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Paid Time Off |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | AFUDC-Borrowed |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | AFUDC-Equity |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Benefits OH |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Building Service Overhead |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Capitalized A&G |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Fleet OH - Elec |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | IT Device OH |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235704 | FRRB - KANAKA 1101 - K5 PH5 |  | Payroll Taxes OH |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Design Drafting Services |  | 004/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Design Drafting Services - Overtime |  | 004/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Engineering/Mapping |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Indirect Labor - Electric |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Paid Time Off |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | AFUDC-Borrowed |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | AFUDC-Equity |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Benefits OH |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Building Service Overhead |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Capitalized A&G |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Fleet OH - Elec |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | IT Device OH |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235705 | FRRB - WYANDOTTE 1103 - W2 PH2.6 |  | Payroll Taxes OH |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Design Drafting Services - Overtime |  | 004/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Engineering/Mapping |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Indirect Labor - Electric |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Paid Time Off |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | AFUDC-Borrowed |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | AFUDC-Equity |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Benefits OH |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Building Service Overhead |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Capitalized A&G |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Fleet OH - Elec |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | IT Device OH |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235706 | FRRB - WYANDOTTE 1103 - W2 PH2.7 |  | Payroll Taxes OH |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Account Services |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Drafting Doubletime |  | 004/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Engineering/Mapping |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Indirect Labor - Cust Care |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Indirect Labor - Electric |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Management Services |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Paid Time Off |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | AFUDC-Borrowed |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | AFUDC-Equity |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Benefits OH |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Building Service Overhead |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Capitalized A&G |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Fleet OH - Elec |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | IT Device OH |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Operation Mgmt & Support - Electric |  | 003/2021
35235707 | FRRB - WYANDOTTE 1103 - W2 PH2.8 |  | Payroll Taxes OH |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Indirect Labor - Electric |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Paid Time Off |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Project Management Services |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | AFUDC-Borrowed |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | AFUDC-Equity |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Benefits OH |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Building Service Overhead |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Capitalized A&G |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Fleet OH - Elec |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | IT Device OH |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Operation Mgmt & Support - Electric |  | 003/2021
35236439 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.15 |  | Payroll Taxes OH |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Indirect Labor - Electric |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Paid Time Off |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Project Management Services |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | AFUDC-Borrowed |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | AFUDC-Equity |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Benefits OH |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Building Service Overhead |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Capitalized A&G |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Fleet OH - Elec |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | IT Device OH |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Operation Mgmt & Support - Electric |  | 003/2021
35236660 | ECOP-MIDDLETOWN 1101-H12-LR548-PH2.16 |  | Payroll Taxes OH |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Account Services |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Indirect Labor - Cust Care |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Paid Time Off |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | AFUDC-Borrowed |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | AFUDC-Equity |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Benefits OH |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Building Service Overhead |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Capitalized A&G |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | IT Device OH |  | 003/2021
35236661 | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 |  | Payroll Taxes OH |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Engineering/Mapping |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Indirect Labor - Electric |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Paid Time Off |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | AFUDC-Borrowed |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | AFUDC-Equity |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Benefits OH |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Building Service Overhead |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Capitalized A&G |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Fleet OH - Elec |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | IT Device OH |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Operation Mgmt & Support - Electric |  | 003/2021
35236982 | NCF - RG - K1101 - REMOVAL 33 |  | Payroll Taxes OH |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | Management Services |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | AFUDC-Borrowed |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | AFUDC-Equity |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | Benefits OH |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | Building Service Overhead |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | Capitalized A&G |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | IT Device OH |  | 003/2021
35236985 | NCF - RG - K1101- REMOVAL 28, 105,150 |  | Payroll Taxes OH |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | Management Services |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | AFUDC-Borrowed |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | AFUDC-Equity |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | Benefits OH |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | Building Service Overhead |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | Capitalized A&G |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | IT Device OH |  | 003/2021
35236989 | NCF - RG - K1101 - REMOVAL 1 |  | Payroll Taxes OH |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Management Services |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | AFUDC-Borrowed |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | AFUDC-Equity |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Benefits OH |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Building Service Overhead |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Capitalized A&G |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Fleet OH - Elec |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | IT Device OH |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Operation Mgmt & Support - Electric |  | 003/2021
35236990 | FRRB - WYANDOTTE 1103 - W3 PH3.9 |  | Payroll Taxes OH |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | Management Services |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | AFUDC-Borrowed |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | AFUDC-Equity |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | Benefits OH |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | Building Service Overhead |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | Capitalized A&G |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | IT Device OH |  | 003/2021
35236993 | FRRB - WYANDOTTE 1103 - W4 PH4.9 |  | Payroll Taxes OH |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Account Services |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Indirect Labor - Cust Care |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Management Services |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Paid Time Off |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | AFUDC-Borrowed |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | AFUDC-Equity |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Benefits OH |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Building Service Overhead |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Capitalized A&G |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | IT Device OH |  | 003/2021
35236995 | FRRB - WYANDOTTE 1103 - W4 PH4.10 |  | Payroll Taxes OH |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Account Services |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Indirect Labor - Cust Care |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Management Services |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Paid Time Off |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | AFUDC-Borrowed |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | AFUDC-Equity |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Benefits OH |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Building Service Overhead |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Capitalized A&G |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | IT Device OH |  | 003/2021
35236997 | NCF - RG - BB1102 - REMOVAL 134, 135 |  | Payroll Taxes OH |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Engineering/Mapping |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Indirect Labor - Electric |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Paid Time Off |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | AFUDC-Borrowed |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | AFUDC-Equity |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Benefits OH |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Building Service Overhead |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Capitalized A&G |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Fleet OH - Elec |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | IT Device OH |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237258 | CWSP - VACA DIXON 110540092 PH 1.2 |  | Payroll Taxes OH |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Engineering/Mapping |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Indirect Labor - Electric |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Paid Time Off |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | AFUDC-Borrowed |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | AFUDC-Equity |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Benefits OH |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Building Service Overhead |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Capitalized A&G |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Fleet OH - Elec |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | IT Device OH |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237259 | CWSP - VACA DIXON 110540092 PH 1.3 |  | Payroll Taxes OH |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Engineering/Mapping |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Paid Time Off |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Benefits OH |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Building Service Overhead |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Capitalized A&G |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | IT Device OH |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237360 | CWSP - VACA DIXON 110540092 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Engineering/Mapping |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Indirect Labor - Electric |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Paid Time Off |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | AFUDC-Borrowed |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | AFUDC-Equity |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Benefits OH |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Building Service Overhead |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Capitalized A&G |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Fleet OH - Elec |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | IT Device OH |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237361 | CWSP - VACA DIXON 110540092 PH 1.5 |  | Payroll Taxes OH |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Engineering/Mapping |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Indirect Labor - Electric |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Paid Time Off |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | AFUDC-Borrowed |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | AFUDC-Equity |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Benefits OH |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Building Service Overhead |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Capitalized A&G |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Fleet OH - Elec |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | IT Device OH |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237368 | CWSP - VACA DIXON 110540092 PH 1.9 |  | Payroll Taxes OH |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Engineering/Mapping |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Indirect Labor - Electric |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Paid Time Off |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | AFUDC-Borrowed |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | AFUDC-Equity |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Benefits OH |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Building Service Overhead |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Capitalized A&G |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Fleet OH - Elec |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | IT Device OH |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237369 | CWSP - VACA DIXON 110540092 PH 1.10 |  | Payroll Taxes OH |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Engineering/Mapping |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Indirect Labor - Electric |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Paid Time Off |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | AFUDC-Borrowed |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | AFUDC-Equity |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Benefits OH |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Building Service Overhead |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Capitalized A&G |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Fleet OH - Elec |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | IT Device OH |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237370 | CWSP - VACA DIXON 110540092 PH 1.11 |  | Payroll Taxes OH |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Engineering/Mapping |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Indirect Labor - Electric |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Paid Time Off |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | AFUDC-Borrowed |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | AFUDC-Equity |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Benefits OH |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Building Service Overhead |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Capitalized A&G |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Fleet OH - Elec |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | IT Device OH |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237371 | CWSP - VACA DIXON 110540092 PH 1.12 |  | Payroll Taxes OH |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Land Rights - Misc |  | 004/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Management Services |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | AFUDC-Borrowed |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | AFUDC-Equity |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Benefits OH |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Building Service Overhead |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Capitalized A&G |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Fleet OH - Elec |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | IT Device OH |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237889 | FRRB - WYANDOTTE 1103 - W3 PH3.2 |  | Payroll Taxes OH |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Land Rights - Misc |  | 004/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Management Services |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | AFUDC-Borrowed |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | AFUDC-Equity |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Benefits OH |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Building Service Overhead |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Capitalized A&G |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Fleet OH - Elec |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | IT Device OH |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Operation Mgmt & Support - Electric |  | 003/2021
35237890 | FRRB - WYANDOTTE 1103 - W3 PH3.3 |  | Payroll Taxes OH |  | 003/2021
35237891 | FRRB - WYANDOTTE 1103 - W3 PH3.4 |  | Land Rights - Misc |  | 004/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | Management Services |  | 003/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | Benefits OH |  | 003/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | Building Service Overhead |  | 003/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | Capitalized A&G |  | 003/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | IT Device OH |  | 003/2021
35238088 | REMG 531 - MARIPOSA 2101, SLAUGHTER HOUS |  | Payroll Taxes OH |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Electric Estimating |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Indirect Labor - Electric |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Indirect Labor - Environmental Land |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Land Surveying & Engineering Supprt-Misc |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Paid Time Off |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | AFUDC-Borrowed |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | AFUDC-Equity |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Benefits OH |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Building Service Overhead |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Capitalized A&G |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Fleet OH - Elec |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | IT Device OH |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Operation Mgmt & Support - Electric |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
35238567 | CWSP - MARIPOSA 210197142 PH 1.4 |  | Payroll Taxes OH |  | 003/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Borrowed |  | 001/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Borrowed |  | 002/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Borrowed |  | 003/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Equity |  | 001/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Equity |  | 002/2021
74011865 | PH.3 - RECON. ECHO SUMMIT 1101 11,600' |  | AFUDC-Equity |  | 003/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Borrowed |  | 001/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Borrowed |  | 002/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Borrowed |  | 003/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Equity |  | 001/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Equity |  | 002/2021
74014860 | R2 REPL OH COND/ ALTERNTE BACKTIE CE2104 |  | AFUDC-Equity |  | 003/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Construction Inspection |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Indirect Labor - Electric |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Indirect Labor - Electric |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Maint & Operate Doubletime Services |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Maint & Operate Doubletime Services |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Maintain & Operate Services |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Maintain & Operate Services |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Mapping |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Paid Time Off |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Paid Time Off |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Benefits OH |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Benefits OH |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Building Service Overhead |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Building Service Overhead |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Capitalized A&G |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Capitalized A&G |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Fleet OH - Elec |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Fleet OH - Elec |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | IT Device OH |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | IT Device OH |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Operation Mgmt & Support - Electric |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Operation Mgmt & Support - Electric |  | 002/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Payroll Taxes OH |  | 001/2021
74021903 | CWSP-BRUNSWICK 1105 LR-1030 ZONE |  | Payroll Taxes OH |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Construction Inspection |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Indirect Labor - Electric |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Mapping |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Paid Time Off |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Electl & Electronic Equipment Component |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Material Burden |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Benefits OH |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Benefits OH |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Building Service Overhead |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Building Service Overhead |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Capitalized A&G |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Fleet OH - Elec |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | IT Device OH |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | IT Device OH |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Minor Material OH |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Operation Mgmt & Support - Electric |  | 002/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Payroll Taxes OH |  | 001/2021
74021960 | CWSP-BRUNSWICK 1105 LR-32536 ZONE # PH 1 |  | Payroll Taxes OH |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Contracts |  | 004/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Contracts |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Account Services |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Account Services |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Engineering/Mapping |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Engineering/Mapping |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Engineering/Mapping |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Cust Care |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Cust Care |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Electric |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Electric |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Electric |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Indirect Labor - Environmental Land |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Land Rights - Misc |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Mapping |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Paid Time Off |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Paid Time Off |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Paid Time Off |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Benefits OH |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Benefits OH |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Benefits OH |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Billing Credit - CIAC Non Taxable |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Building Service Overhead |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Building Service Overhead |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Building Service Overhead |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Capitalized A&G |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Capitalized A&G |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Capitalized A&G |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Encroachment Permit Fees |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Fleet OH - Elec |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Fleet OH - Elec |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Fleet OH - Elec |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | IT Device OH |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | IT Device OH |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | IT Device OH |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Operation Mgmt & Support - Electric |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Operation Mgmt & Support - Electric |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Operation Mgmt & Support - Electric |  | 003/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Payroll Taxes OH |  | 001/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Payroll Taxes OH |  | 002/2021
74021961 | CWSP - MIRABEL 02/MONTE RIO 13 - LR 652 |  | Payroll Taxes OH |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Contracts |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Contracts |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Contracts |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Contracts |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Electric Construction Contract |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Electric Construction Contract |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Electric Construction Contract |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Electric Construction Contract |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Construction |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Construction Overtime Services |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Environmental Planning & Permitting-Misc |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Indirect Labor - Electric |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Indirect Labor - Electric |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Indirect Labor - Electric |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Indirect Labor - Environmental Land |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Mapping |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Mapping |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Mapping |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Paid Time Off |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Paid Time Off |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Paid Time Off |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Electrical Specialties |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Material Burden |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Benefits OH |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Benefits OH |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Benefits OH |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Building Service Overhead |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Building Service Overhead |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Building Service Overhead |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Capitalized A&G |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Capitalized A&G |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Capitalized A&G |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Cash Discount earned |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Fleet OH - Elec |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Fleet OH - Elec |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Fleet OH - Elec |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | IT Device OH |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | IT Device OH |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | IT Device OH |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Minor Material OH |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Operation Mgmt & Support - Electric |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Operation Mgmt & Support - Electric |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Operation Mgmt & Support - Electric |  | 003/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Operation Mgmt & Support - Environ Land |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Payroll Taxes OH |  | 001/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Payroll Taxes OH |  | 002/2021
74021963 | CWSP - OAKLAND K 1102 OCB ZONE |  | Payroll Taxes OH |  | 003/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Borrowed |  | 001/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Borrowed |  | 002/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Borrowed |  | 003/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Equity |  | 001/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Equity |  | 002/2021
74022383 | CWSP-EL DORADO PH 2102 LR19542 PH 1.0 |  | AFUDC-Equity |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Management Contracts |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Management Contracts |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Contracts |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Electric Construction Contract |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Electric Construction Contract |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Electric Construction Contract |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Environmental Contract |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Helicopter Contract |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Traffic Control Contracts |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Traffic Control Contracts |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Traffic Control Contracts |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Consulting Services - Engineering |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Consulting Services - Engineering |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Consulting Services - Engineering |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Consulting Services - Environmental Perm |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Consulting Services - Environmental Perm |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Account Services |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Account Services |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Account Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Acquisition - Misc |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Acquisition - Misc |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Acquisition - Misc |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Administration |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Administration |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Administration |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Administrative Services - OT |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Administrative Services - OT |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Doubletime Services |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Doubletime Services |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Doubletime Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Overtime Services |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Overtime Services |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Construction Overtime Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Engineering/Mapping |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Engineering/Mapping |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Engineering/Mapping |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Cust Care |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Cust Care |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Cust Care |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Electric |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Electric |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Electric |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Environmental Land |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Environmental Land |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Environmental Land |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Gas |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Gas |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Nuclear Gen |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Indirect Labor - Nuclear Gen |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Rights - Misc |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Rights - Misc |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Rights - Misc |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Maintain & Operate Overtime Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Maintain & Operate Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Manage L&EM |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Management Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Mapping |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Mapping |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Mapping |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Paid Time Off |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Paid Time Off |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Paid Time Off |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Technical Services |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Technical Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Electl & Electronic Equipment Component |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Material Burden |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Material Burden |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Material Burden |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Poles, Insulators & Hardware Bushing & B |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Poles, Insulators & Hardware Bushing & B |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Poles, Insulators & Hardware Bushing & B |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Purchasing Card |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Benefits OH |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Benefits OH |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Benefits OH |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Building Service Overhead |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Building Service Overhead |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Building Service Overhead |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Capitalized A&G |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Capitalized A&G |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Capitalized A&G |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Cash Discount earned |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Fleet OH - Elec |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Fleet OH - Elec |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Fleet OH - Elec |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Fleet OH - Gas |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Fleet OH - Gas |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | IT Device OH |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | IT Device OH |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | IT Device OH |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Acquisition Services |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Acquisition Services |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Acquisition Services |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Land Acquisition Services |  | 004/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Minor Material OH |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Minor Material OH |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Minor Material OH |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Electric |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Electric |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Electric |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Gas |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Gas |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Nuclear Gen |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Operation Mgmt & Support - Nuclear Gen |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Other Expenses |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Other Land Fees |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Payroll Taxes OH |  | 001/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Payroll Taxes OH |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Payroll Taxes OH |  | 003/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Reimbursed Mileage Expense |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Reimbursed Mileage Expense |  | 002/2021
74022384 | CWSP - FITCH MOUNTAIN 1113 LR 24918 |  | Reimbursed Mileage Expense |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Engineering/Mapping |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Environmental Planning & Permitting-Misc |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Environmental Planning & Permitting-Misc |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Environmental Planning & Permitting-Misc |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Indirect Labor - Electric |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Indirect Labor - Environmental Land |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Indirect Labor - Environmental Land |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Indirect Labor - Environmental Land |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Paid Time Off |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Paid Time Off |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Paid Time Off |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Borrowed |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Borrowed |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Borrowed |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Equity |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Equity |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | AFUDC-Equity |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Benefits OH |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Benefits OH |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Benefits OH |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Building Service Overhead |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Building Service Overhead |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Building Service Overhead |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Capitalized A&G |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Capitalized A&G |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Capitalized A&G |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Fleet OH - Elec |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | IT Device OH |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | IT Device OH |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | IT Device OH |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Operation Mgmt & Support - Electric |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Operation Mgmt & Support - Environ Land |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Operation Mgmt & Support - Environ Land |  | 003/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Payroll Taxes OH |  | 001/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Payroll Taxes OH |  | 002/2021
74022385 | ECEIVED SIZE CATCWSP-KONOCTI 1102-LR 532 |  | Payroll Taxes OH |  | 003/2021
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 |  | AFUDC-Borrowed |  | 001/2021
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 |  | AFUDC-Equity |  | 001/2021
74022386 | *CANC* CWSP - LOS GATOS 1106 - LB4 |  | Canceled Capital Order |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Environmental Contract |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Environmental Contract |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Engineering/Mapping |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Engineering/Mapping |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Indirect Labor - Electric |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Indirect Labor - Electric |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Indirect Labor - Electric |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Mapping |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Mapping |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Paid Time Off |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Paid Time Off |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Paid Time Off |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Benefits OH |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Benefits OH |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Benefits OH |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Building Service Overhead |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Building Service Overhead |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Building Service Overhead |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Capitalized A&G |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Capitalized A&G |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Capitalized A&G |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Cash Discount earned |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Encroachment Permit Fees |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Encroachment Permit Fees |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Fleet OH - Elec |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Fleet OH - Elec |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Fleet OH - Elec |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | IT Device OH |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | IT Device OH |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | IT Device OH |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Operation Mgmt & Support - Electric |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Operation Mgmt & Support - Electric |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Operation Mgmt & Support - Electric |  | 003/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Payroll Taxes OH |  | 001/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Payroll Taxes OH |  | 002/2021
74022388 | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Payroll Taxes OH |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Electric Construction Contract |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Electric Construction Contract |  | 004/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Electric Construction Contract |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Indirect Labor - Electric |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Indirect Labor - Electric |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Mapping |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Paid Time Off |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Paid Time Off |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Project Management Services |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Benefits OH |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Benefits OH |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Building Service Overhead |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Building Service Overhead |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Capitalized A&G |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Capitalized A&G |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Fleet OH - Elec |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Fleet OH - Elec |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | IT Device OH |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | IT Device OH |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Operation Mgmt & Support - Electric |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Operation Mgmt & Support - Electric |  | 003/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Payroll Taxes OH |  | 001/2021
74022390 | CWSP - SILVERADO 2104- LR722-PH 1A |  | Payroll Taxes OH |  | 003/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Borrowed |  | 001/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Borrowed |  | 002/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Borrowed |  | 003/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Equity |  | 001/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Equity |  | 002/2021
74022615 | CWSP - CAMP FIRE PADSE 1105 PENTZ RD |  | AFUDC-Equity |  | 003/2021
74022663 | CAMP FIRE RECOND LINE HONEY RN BUTTE 05 |  | AFUDC-Borrowed |  | 001/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Borrowed |  | 001/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Borrowed |  | 002/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Borrowed |  | 003/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Equity |  | 001/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Equity |  | 002/2021
74022664 | CAMP FIRE RECONDUCTOR LINE DEPOT RD |  | AFUDC-Equity |  | 003/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Borrowed |  | 001/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Borrowed |  | 002/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Borrowed |  | 003/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Equity |  | 001/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Equity |  | 002/2021
74022720 | CWSP-CAMP FIRE PADSE 1105 INST BIKE PATH |  | AFUDC-Equity |  | 003/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Borrowed |  | 001/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Borrowed |  | 002/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Borrowed |  | 003/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Equity |  | 001/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Equity |  | 002/2021
74022721 | CWSP - CAMP FIRE PADSE 1106 BILLIE RD |  | AFUDC-Equity |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Electric Estimating |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Indirect Labor - Electric |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Paid Time Off |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Borrowed |  | 001/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Borrowed |  | 002/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Borrowed |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Equity |  | 001/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Equity |  | 002/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | AFUDC-Equity |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Benefits OH |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Building Service Overhead |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Capitalized A&G |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Fleet OH - Elec |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | IT Device OH |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Operation Mgmt & Support - Electric |  | 003/2021
74022722 | CWSP-CAMP FIRE PDSE 1104 PEARSON RD |  | Payroll Taxes OH |  | 003/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Borrowed |  | 001/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Borrowed |  | 002/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Borrowed |  | 003/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Equity |  | 001/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Equity |  | 002/2021
74022723 | CWSP - CAMP FIRE PDSE 1106 PONDEROSA WAY |  | AFUDC-Equity |  | 003/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Contracts |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Indirect Labor - Electric |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Mapping |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Paid Time Off |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Benefits OH |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Building Service Overhead |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Capitalized A&G |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Cellular Phone Use |  | 002/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Cellular Phone Use |  | 003/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Cellular Phone Use |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Fleet OH - Elec |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | IT Device OH |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Operation Mgmt & Support - Electric |  | 001/2021
74024171 | CALISTOGA 1101 HIGH SPLICE COUNT |  | Payroll Taxes OH |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Contracts |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 004/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Environmental Contract |  | 004/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Consulting Services - Engineering |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Consulting Services - Engineering |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Consulting Services - Engineering |  | 004/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Outside Attorney Fees |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Account Services |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Administration |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Construction |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Construction |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Construction |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Construction Overtime Services |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Engineering/Mapping |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Engineering/Mapping |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Engineering/Mapping |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Indirect Labor - Cust Care |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Indirect Labor - Electric |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Indirect Labor - Electric |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Indirect Labor - Electric |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Indirect Labor - Environmental Land |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Mapping |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Mapping |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Mapping |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Paid Time Off |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Paid Time Off |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Paid Time Off |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Benefits OH |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Benefits OH |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Benefits OH |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Building Service Overhead |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Building Service Overhead |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Building Service Overhead |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Capitalized A&G |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Capitalized A&G |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Capitalized A&G |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Fleet OH - Elec |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Fleet OH - Elec |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Fleet OH - Elec |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | IT Device OH |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | IT Device OH |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | IT Device OH |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Operation Mgmt & Support - Electric |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Operation Mgmt & Support - Electric |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Operation Mgmt & Support - Electric |  | 003/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Operation Mgmt & Support - Environ Land |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Payroll Taxes OH |  | 001/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Payroll Taxes OH |  | 002/2021
74028021 | CWSP - MIRABEL 02/MONTE RIO 13-LR652 PH2 |  | Payroll Taxes OH |  | 003/2021

## 2021 pivot
Order Desc | (Multiple Items) |  |  |  | Order Desc | FRRB - MONTICELLO 1101 CB
Sum of $ | Column Labels |  |  |  | Sum of $ | Column Labels
Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total | Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total
Contract |  |  |  |  | Contract
Labor External |  |  |  |  | Labor Internal
Labor Internal |  |  |  |  | Materials
Materials |  |  |  |  | Other
Other |  |  |  |  | Grand Total
Grand Total | 7820816.14 | 12615264.75 | 24056542.27 | 44492623.16

## 2021 working pivot
Sum of $ | Column Labels
Row Labels | 001/2021 | 002/2021 | 003/2021 | Grand Total
Contract
Labor External
Labor Internal
Materials
Other
Grand Total | -55177296.44 | 52136697.78 | 18491182.6 | 15450583.94