## Master
25 | [36 empty] | 18.5445 | 14.1369 | 17.8 | 33705 | 17.8812 |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | 0 | 507.5 | 0 | 50 | 3746.8 | 9387.3 | 12996.6 | 3250 | 1153.3 | 0 | 0 | 0
Order | MAT | Order Description | Reg | Div | Job Owner Name | Project Managed? | Tree Wire? | User Status | Phase | Reason Missed 8/1 Date | Risk of not completing by 8/1 | Notes | Estimating Resource | Const. Resource | Contractor | EOD Date as of 6/6 | % of Estimate Complete | Current Out of PEND Date | % Const. Complete | In-Service Date (Forecasted) | Matts Cons Start | Matts Cons End | Click Start Date | Click End Date | P6 CSTRT Forecast (as of 5/8/18) | P6 FISD Forecast (as of 5/8/18) | FISD Week | Click Start Week | Click Finish Week | P6 Con Start Week | P6 Con End Week | Matts Cons Start Week | Matts Cons End Week | Matts Year | Matts Mo | Ckt Feet (Adjusted/Actual) | Ckt Miles (Adjusted/Actual) | Tier 3 Ckt Miles | 4/3/18 Planned Ckt Miles | Total Estimated Hours | Total Miles including partial completions. | # of Crews | Weeks of Const. Calc 5-10s 5 man crew | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
31234873 | 08J | X1104 (Oakland)- RELIAIBLITY 2017 - UWF X-1104 | BA - Bay Area | EB |  | Y | NO | #N/A | ?? | NA | 1 - Complete | Risk: NA NOTES: 5/31 - CN24 complete & units posted to SA Project Complete. Not tree wire. - 5/31 - CN24 complete & units posted to SA |  |  |  | Estimate Complete |  |  | 100% | 2018-03-28 | 2018-02-17 20:24 | 2018-02-28 | ? | ? | 2018-02-01 | 2018-03-13 | 13 | #VALUE! | #VALUE! | 5 | 11 | 7 | 9 | 2018 | 2 | 2100 | 0.39773 |  | 0.4 | 507.5 | 0.39773 | 1 | 2.03 | [32 empty] | 507.5
31095523 | 08W | OAKLAND K 1103 - MERRIEWOOD DR EB-RELIAIBLITY -K1103, REPL #4ACSR W | BA - Bay Area | EB |  | N | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk:NANOTES: Complete 5/30- 5/31 - completed per [REDACTED] |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-05-30 | 2018-05-22 | 2018-05-30 | 09/22/2017 | 05/30/2018 | ? | ? | 22 | 38 | 22 | #VALUE! | #VALUE! | 21 | 22 | 2018 | 5 | 1838 | 0.34811 | 0.34811 | 0.4 | 538.9 | 0.34811 | 1 | 2.1556 |  |  |  | C | C | [32 empty] | 538.9
31218981 | 08J | CEDAR CREEK 1101(Round Mountain)- UPGRADE 9 SPANS | NO - Northern | NV |  | N | NO | CLSD | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: 5/31 - CN24 complete & units posted to SAP Click Dates Start back up in June. AFW in for 5/16? - 5/31 - CN24 complete & units posted to SAP |  |  |  | Estimate Complete |  |  | 100% | 2018-06-04 | 2018-06-04 | 2018-06-04 | ? | ? | ? | ? | 23 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 23 | 23 | 2018 | 6 | 4200 | 0.79545 |  | 0.51 | 308.4 | 0.79545 | 1 | 1.2336 | [5 empty] | X | [28 empty] | 50
31206912 | 08W | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | CC - Central Coast | CC |  | N | YES | DOCC | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: - Permiting issue arose on 6/20, resolved now scheduled 7/12. - AFW in for 7/12 - Permit extended to 9/30. |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-16 | 2018-06-11 | 2018-07-12 | ? | ? | ? | ? | 29 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 24 | 28 | 2018 | 7 | 705 | 0.13352 | 0.13352 | 0.16 | 192 | 0.13352 | 1 | 0.768 | [6 empty] | C | C | C | C | C | [25 empty] | 191.5
31205198 | 08W | ALTO 1125 (Mill Valley)- REED ST, COUNTY | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: - 5/31 - expect construction to start on 6/25 & complete on 7/16 |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-16 | 2018-06-25 | 2018-07-16 | # | # | 2018-06-25 | 2018-07-16 | 29 | #VALUE! | #VALUE! | 26 | 29 | 26 | 29 | 2018 | 7 | 3900 | 0.73864 | 0.6178 | 0.73 | 1907.9 | 0.73864 | 2 | 3.8158 | [8 empty] | C | C | C | C | [24 empty] | 807.9 | 1100
31169729 | 08W | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | BA - Bay Area | EB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: - D1112 (Tier 3) complete and K1101 (Tier 1) is planned for July. - Added Scope: Planning may want to extend 3 spans to enhance the ckt. May cause some delays for estimating and dependencies. Redline? -GC click scheduled to complete on 8/1. Will do tree wire section first. - 5/31 - 1st clearance next week. Expect to complete mid July |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-17 | 2018-05-23 | 2018-07-17 | 05/23/2018 | 07/23/2018 | 2018-05-23 | 2018-07-17 | 29 | 21 | 30 | 21 | 29 | 21 | 29 | 2018 | 7 | 4171 | 0.78996 | 0.21136 | 0.94 | 1404.5 | 0.78996 | 1 | 5.618 |  |  |  | C | C | C |  |  |  | C | C | C | [23 empty] | 304.5 | 1100
31207126 | 08W | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: AFW 7/18 |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-18 | 2018-05-30 | 2018-07-18 | 05/30/2018 | 07/17/2018 | 2018-05-31 | 2018-07-18 | 29 | 22 | 29 | 22 | 29 | 22 | 29 | 2018 | 7 | 5300 | 1.0038 | 1.0038 | 1.05 | 1927.3 | 1.0038 | 2 | 3.8546 |  |  |  |  | C | C | C | C | C | C | C | C | [24 empty] | 827.3 | 1100
31264915 | 08W | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | NO - Northern | SO |  | N | YES | DOCC | 5 Post-Constr | NA | 1 - Complete | Risk: -JPA: Verbal approval requested. NOTES: AFW in for 7/26 |  |  |  | Estimate Complete | 100% | 2018-07-07 | 100% | 2018-07-25 | 2018-07-16 | 2018-07-25 | # | # | ? | ? | 30 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 29 | 30 | 2018 | 7 | 957 | 0.18125 | 0.18125 | 0.13 | 80.3 | 0.18125 | 1 | 0.3212 | [11 empty] | C | C | [23 empty] | 200
31255868 | 08W | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | CC - Central Coast | CC |  | Y | YES | PREC | 5 Post-Constr | NA | 1 - Complete | Risk: NOTES: AFW7/27 |  |  |  | Estimate Complete | 100% | 2018-07-11 | 100% | 2018-07-27 | 2018-07-16 | 2018-07-27 | 07/16/2018 | 07/31/2018 | 2018-07-17 | 2018-07-27 | 30 | 29 | 31 | 29 | 30 | 29 | 30 | 2018 | 7 | 1439 | 0.27254 | 0.27254 | 0.27 | 497 | 0.27254 | 1 | 1.988 | [10 empty] | C | C | C | [24 empty] | 350
31205343 | 08W | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk:ROW issue. Customer doesn’t want us to replace pole and damage landscaping. [REDACTED] working with land and others to resolve. 3 Spans. NOTES: Remove shoofly on 7/5. ROW issue pole. |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-28 | 2018-06-04 | 2018-07-28 | 06/04/2018 | 06/29/2018 | 2018-06-04 | 2018-07-28 | 30 | 23 | 26 | 23 | 30 | 23 | 30 | 2018 | 7 | 5006 | 0.94811 | 0.94811 | 0.94 | 2562.1 | 0.94811 | 2 | 5.1242 | [5 empty] | C | C | C | C | C | C | C | C | [22 empty] | 407.1 | 1050 | 1100
31205418 | 08W | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: - Update click dates - 5/31 - expected construction start on 6/26 & completion on 7/30 |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-30 | 2018-06-26 | 2018-07-30 | 06/25/2019 | 07/25/2019 | 2018-06-26 | 2018-07-27 | 31 | 26 | 30 | 26 | 30 | 26 | 31 | 2018 | 7 | 5480 | 1.0379 | 1.0379 | 1.04 | 2110.6 | 1.0379 | 2 | 4.2212 | [8 empty] | C | C | C | C | C | C | [22 empty] | 1010.6 | 1100
31204706 | 08W | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: NA NOTES: AFW/CWC submiting error. - 5/31 - expect to complete 7/2 |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-07-30 | 2018-06-18 | 2018-07-30 | 06/18/2018 | 07/30/2018 | 2018-06-18 | 2018-07-30 | 31 | 25 | 31 | 25 | 31 | 25 | 31 | 2018 | 7 | 1613 | 0.30549 | 0.30549 | 0.29 | 1348.6 | 0.30549 | 2 | 2.6972 | [7 empty] | C | C | C | C | C | C | C | [21 empty] | 500
31132867 | 08W | Half Moon Bay 1101 (Half Moon Bay)- SKYLINE BLVD | CC - Central Coast | PN |  | Y | YES | #N/A | ?? | Caltrans Permit: [REDACTED] (Land Agent) and [REDACTED] helping to expedite. Land:Lam Vu (Sr. Land Tech) and [REDACTED] helping to expedite. | 1 - Complete | Risk: Permit: Caltrans permit application submitted 5/10. Working with [REDACTED] to expedite. Didn't have JPA, which could cause an issue. Typically 2 month process. Revised TCON needed, amendment. Land/Easement: 3 locations are in SFPUC property, 1 year process for easement. Looking to redesign to stay in current easement or eliminate these locations from scope. NOTES:- JPA sent 4/28, June 12th. -Environmental Planned to finish 6/29. -Click dates are contract unassigned. -RFP issued to ILB 4/19.- 5/31 - no change to rick status. Not sure about status of Cal Trans permit submitted by contractor |  |  |  | Estimate Complete | 100% | TBD | 100% | 2018-07-31 | 2018-07-16 | 2018-07-31 | ? | ? | 2018-07-16 | 2018-07-31 | 31 | #VALUE! | #VALUE! | 29 | 31 | 29 | 31 | 2018 | 7 | 4638 | 0.87841 | 0.87841 | 0.41 | 1068.9 | 0.87841 | 1 | 4.2756 | [11 empty] | C | C | C | [25 empty] | 629.4
31286571 | 08W | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | NO - Northern | SI |  | Y | YES | FICL | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. |  |  |  | 2018-06-08 | 100% | 2018-07-11 | 100% | 2018-09-11 | 2018-07-11 | 2018-09-11 | 07/10/2018 | 2018-07-27 | 2018-07-10 | 2018-09-18 | 37 | 28 | 30 | 28 | 38 | 28 | 37 | 2018 | 9 | 1928 | 0.36515 | 0.36515 | 0.4 | 611.4 | 0.36515 | 1 | 2.4456 | [7 empty] | 0 |  |  | C | C | C | C | C | C | C | C | C | C | [17 empty] | 600
31246140 | 08W | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NO - Northern | NV |  | Y | YES | FICL | 5 Post-Constr | Outage Restrictions (Heat/Loading) | 1 - Complete | Reason for Missing Date: Crews Pulled to support north valley fire in late june. Work replanned for 7/18, but canceled by DO due to loading concerns being it was over 100 degrees. |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-09-13 | 2018-06-04 | 2018-09-13 | 06/04/2018 | 09/13/2018 | 2018-06-04 | 2018-09-13 | 37 | 23 | 37 | 23 | 37 | 23 | 37 | 2018 | 9 | 3309 | 0.6267 | 0.6267 | 0.57 | 617.9 | 0.6267 | 1 | 2.4716 | [5 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [17 empty] | 1000
31082394 | 08W | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | NO - Northern | SO |  | N | YES | MAPP | 5 Post-Constr | Permitting | 1 - Complete | Reason for missing date: 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. |  |  |  | Estimate Complete | 100% | 2018-06-28 | 100% | 2018-09-16 | 2018-08-27 | 2018-09-15 | 09/10/2018 | 09/13/2018 | ? | ? | 38 | 37 | 37 | #VALUE! | #VALUE! | 35 | 37 | 2018 | 9 | 1486 | 0.28144 | 0.28144 | 0.09 | 208.6 | 0.28144 | 1 | 0.8344 | [17 empty] | C | C | C | [15 empty] | 208
31207089 | 08J | GB 1103 (Mill Valley) - HAWTHORN | BA - Bay Area | NB |  | Y | YES | FICL | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-09-25 | 2018-07-10 | 2018-09-25 | 07/10/2018 | 07/31/2018 | 2018-07-10 | 2019-01-28 | 39 | 28 | 31 | 28 | 5 | 28 | 39 | 2018 | 9 | 4687 | 0.92614 | 0.92614 | 0.85 | 2834.1 | 0.92614 | 2 | 5.6682 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | [13 empty] | 563.5 | 1050 | 1100
31234871 | 08W | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | BA - Bay Area | EB |  | Y | YES | MAPP | 5 Post-Constr | NA | 1 - Complete | Risk: Tier 3 section on track to complete by 7/30. Tier 1 8/30 NOTES: - Half of the project is in Tier 1. - Work areas without dependencies first. - Need permit extensions for expired permits - Need to issue CWA & obtain work plan - Click dates are contract unassigned. - 5/31 - no change in risk status. Expects the Tier 3 portion to be completed by 8/1 |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-09-25 | 2018-06-18 | 2018-09-25 | 2018-07-09 | 09/25/2018 | 2018-06-26 | 2018-10-29 | 39 | 28 | 39 | 26 | 44 | 25 | 39 | 2018 | 9 | 7271 | 1.3771 | 0.57348 | 1.38 | 3201.1 | 1.3771 | 2 | 6.4022 | [6 empty] | C | C | C | C | C | C | C |  |  | C | C | C | C | C | C | C | [13 empty] | 1051.1 | 1050 | 1100
31330635 | 08W | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | NO - Northern | SI |  | Y | YES | FICL | 5 Post-Constr | Timing/Size of Project | 1 - Complete | Reason for missing date: Size of project. Project is over 2 miles and didn’t become construction ready till July. Every activity (Estimating/Dependancy/Construction) was put at its critical path, but too large to complete in time. |  |  |  | 2018-05-31 | 100% | 2018-07-13 | 100% | 2018-10-04 | 2018-07-16 | 2018-10-04 | 07/16/2018 | 10/05/2018 | 2018-07-13 | 2018-12-03 | 40 | 29 | 40 | 28 | 49 | 29 | 40 | 2018 | 10 | 11308 | 2.1417 | 2.1417 | 1.89 | 3200 | 2.1417 | 2.5 | 5.12 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | [14 empty] | 1050 | 1100 | 450
31275384 | 08W | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | NO - Northern | SO |  | N | YES | MAPP | 5 Post-Constr | Permitting | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. |  |  |  | Estimate Complete | 100% | 2018-06-28 | 100% | 2018-10-09 | 2018-08-27 | 2018-10-09 | 09/10/2018 | 10/09/2018 | ? | ? | 41 | 37 | 41 | #VALUE! | #VALUE! | 35 | 41 | 2018 | 10 | 1986 | 0.37614 | 0.37614 | 0.34 | 362.6 | 0.37614 | 1 | 1.4504 | [17 empty] | C | C | C | C | C | C | C | [11 empty] | 362.6
31338871 | 08W | El Cerrito G 1112 (Berkeley) Cal Berkeley | BA - Bay Area | EB |  | Y | YES | FICL | 5 Post-Constr | NA | 1 - Complete | Risk: Access/Permit: Short window to work with two adjacent city projects. City will not allow full road closure without exstensive review. • TCP/Encroachment permit - Meeting with city and contractor again on 6/28/18 to discuss TCP’s. The Following dependences are still needed before the City of Berkeley will issue the work permit.- Temporary Construction Easement (TCE) for resident parking during the full road closure at locations 71 -89. (The land team is currently working on Easement)- Stand by fire and emergency services has been agreed on and confirmed by Berkeley Fire. (Berkeley Fire has agreed to staff project for 1 one)- PG&E has notified residents affected by road closure and outage by the first week on July . - City of Oakland’s approval for the one day road closure on Panoramic way (the top portion is the City of Oakland’s jurisdiction) .• 7/26 locations 90 – 97, assuming (two) 4-man crews • 7/27 locations 90 – 97, assuming (two) 4-man crews• 7/30 locations 63 – 70, assuming (four) 4-man crews• 7/31 locations 71 – 89, assuming (nine) 4-man crewsPlease note: Project has started 7/26 and planned to complete 7/31, but has so many variables and pieces that need to fall in place it is still be considered high risk. NOTES:- Estimate complete 5/16.-Environmental Planned to finish 6/26. - Multiple crews?- Need to award to contractor. - Need to update click. - 5/31 - no change to risk staus. Traffic control plan sent to the city. EBMUD still working in area and likely there until end of June. [REDACTED] to help secure contractor |  |  |  | Estimate Complete | 100% | TBD | 100% | 2018-10-13 | 2018-07-26 | 2018-10-13 | 07/25/2018 | 10/13/2018 | 2018-09-04 | 2018-10-14 | 41 | 30 | 41 | 36 | 42 | 30 | 41 | 2018 | 10 | 3505 | 0.66383 | 0.66383 | 0.64 | 1540 | 0.66383 | 1 | 6.16 | [12 empty] | C | C |  |  |  | C | C | C | C | C | C | C | [14 empty] | 1000
31205937 | 08W | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | BA - Bay Area | NB |  | Y | YES | MAPP | 5 Post-Constr | Resources Pulled to Fire | 1 - Complete | Reason for Missing Date: Crews Pulled to support Fires. |  |  |  | Estimate Complete | 100% | NA | 100% | 2018-10-17 | 2018-07-09 | 2018-10-17 | 09/09/2018 | 10/05/2018 | 2018-07-09 | 2018-09-17 | 42 | 37 | 40 | 28 | 38 | 28 | 42 | 2018 | 10 | 5000 | 0.94697 | 0.94697 | 0.85 | 1999.5 | 0.94697 | 2 | 3.999 | [10 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [11 empty] | 1050 | 842.6
31206678 | 08W | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | BA - Bay Area | NB |  | Y | YES | UNSC | 3 Constr Ready | Resources Pulled to Fire | 4 - High Risk | Reason for Missing Date: Crews Pulled to support Fires. |  |  |  | Estimate Complete | 100% | 2018-06-15 | 90% | 2019-01-30 | 2018-07-19 | 2019-02-15 | 03/29/2019 | 03/29/2019 | 2018-07-25 | 2019-02-06 | 5 | 13 | 13 | 30 | 6 | 29 | 7 | 2019 | 2 | 2817 | 0.53352 | 0.53352 | 0.53 | 965.1 | 0.48017 | 2 | 1.9302 | [11 empty] | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [12 empty] | 915.1 | 50
31169728 | 08W | Oakland K 1102 GRIZZLY PEAK | BA - Bay Area | EB |  | Y | YES | CONS | 4 Construction | NA | 1 - Complete | Risk: - New Contractor: [REDACTED] just starting working on ED work. This will be their first complex project. Contractor concerned with working #6 copper hot, requesting clearance. This would take customers out 2-3 time for work in same month. Needed to Meet 8/1:Contractor to execute work without major issue. NOTES: [REDACTED] lead me to believe work will be complete 7/18?JPA cleared 6/7.-Vegetation: Concerns with contract resources to support this project in time. - Scope Reduction: 2876ft of project has shifted to pilot project to underground existing OH lines for wild fire resiliency. - Environmental planned to finish 6/11.-Update crew foreman sheet with Planned units. - Out to bid. - Click is contract unassigned. |  |  |  | Estimate Complete | 100% | TBD | 100% | 2018-11-15 | 2018-06-22 | 2018-11-15 | 06/22/2018 | 11/15/2018 | 2018-06-18 | 2018-09-28 | 46 | 25 | 46 | 25 | 39 | 25 | 46 | 2018 | 11 | 5016 | 0.95 | 0.54489 | 1.47 | 1183.4 | 0.95 | 1 | 4.7336 | [7 empty] | C | C | C | C | C |  |  |  | C | C | C | C | C | C | C | C | C | C | [13 empty] | 1100 | 73.9
31098626 | 08W | CLARKSVILLE 2104 (El Dorado Hills) - PH 3 Y2018 | NO - Northern | SI |  | Y | YES | UNSC | 3 Constr Ready | Resources Pulled to Fire | 1a - Complete (Tier 3 only) | Reason for Missing Date: Crews Pulled to support Fires. |  |  |  | 2018-06-30 | 100% | 2018-06-30 | 60% | 2019-03-31 | 2018-07-16 | 2019-02-28 | 2018-07-16 | 2018-09-28 | 2018-07-16 | 2019-01-30 | 14 | 29 | 39 | 29 | 5 | 29 | 9 | 2019 | 2 | 8052 | 1.525 | 0.21875 | 1.52 | 2527.3 | 0.915 | 1 | 10.1092 | [12 empty] | C | C | C | C | C | C | C | C |  | C | C | C | C | C | C | C | C | [6 empty] | 350 | 1050 | 1100

## Gantt
Order | Order Description | Tree Wire? | User Status | Phase | Ckt Miles | Risk of not completing by 8/1 | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November
Order | Order Description | Tree Wire? | User Status | Phase | Ckt Miles | Risk of not completing by 8/1 | Week - 18 | Week - 19 | Week - 20 | Week - 21 | Week - 22 | Week - 23 | Week - 24 | Week - 25 | Week - 26 | Week - 27 | Week - 28 | Week - 29 | Week - 30 | Week - 31 | Week - 32 | Week - 33 | Week - 34 | Week - 35 | Week - 36 | Week - 37 | Week - 38 | Week - 39 | Week - 40 | Week - 41 | Week - 42 | Week - 43 | Week - 44 | Week - 45 | Week - 46 | Week - 47 | Week - 48 | Reg | Matt End
31095523 | OAKLAND K 1103 - MERRIEWOOD DR EB-RELIAIBLITY -K1103, REPL #4ACSR W | YES | FICL | Post-Constr | 0.34811 | 1 - Complete | 0 | 0 | 0 | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-05-30
31206912 | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | YES | DOCC | Post-Constr | 0.13352 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-12
31205198 | ALTO 1125 (Mill Valley)- REED ST, COUNTY | YES | FICL | Post-Constr | 0.73864 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-16
31169729 | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | YES | FICL | Post-Constr | 0.78996 | 1 - Complete | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-17
31207126 | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | YES | FICL | Post-Constr | 1.0038 | 1 - Complete | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-18
31264915 | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | YES | DOCC | Post-Constr | 0.18125 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-07-25
31255868 | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | YES | PREC | Post-Constr | 0.27254 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-27
31205343 | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | YES | FICL | Post-Constr | 0.94811 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-28
31205418 | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | YES | FICL | Post-Constr | 1.0379 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-30
31204706 | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | YES | FICL | Post-Constr | 0.30549 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-07-30
31132867 | Half Moon Bay 1101 (Half Moon Bay)- SKYLINE BLVD | YES | #N/A | ?? | 0.87841 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | CC - Central Coast | 2018-07-31
31286571 | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | YES | DOCC | Post-Constr | 0.36515 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-11
31246140 | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | YES | DOCC | Post-Constr | 0.6267 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-13
31082394 | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | YES | DOCC | Post-Constr | 0.28144 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-09-15
31207089 | GB 1103 (Mill Valley) - HAWTHORN | YES | FICL | Post-Constr | 0.92614 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-09-25
31234871 | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | YES | MAPP | Post-Constr | 1.3771 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-09-25
31330635 | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | YES | CONS | Construction | 2.1417 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-10-04
31275384 | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | YES | MAPP | Post-Constr | 0.37614 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NO - Northern | 2018-10-09
31338871 | El Cerrito G 1112 (Berkeley) Cal Berkeley | YES | CONS | Construction | 0.66383 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | 0 | 0 | 0 | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-10-13
31169728 | Oakland K 1102 GRIZZLY PEAK | YES | CONS | Construction | 0.95 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-11-15
31205937 | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | YES | CONS | Construction | 0.94697 | 1 - Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2018-10-17
31206678 | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | YES | CONS | Construction | 0.53352 | 4 - High Risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | 0 | 0 | 0 | 0 | 0 | 0 | BA - Bay Area | 2019-02-15
31098626 | CLARKSVILLE 2104 (El Dorado Hills) - PH 3 Y2018 | YES | CONS | Construction | 1.525 | 1a - Complete (Tier 3 only) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | C | C | C | C | C | C | C | C | 0 | C | C | C | C | C | C | C | C | 0 | 0 | NO - Northern | 2019-02-28
|  |  |  | Cumulative Miles by Month |  |  | 0.348 |  |  |  |  | 0.35 |  |  |  | 6.56 |  |  |  |  | 6.56 |  |  |  | 10.14 |  |  |  | 15.65 |  |  |  |  | 17.17
| Region | [7 empty] | Phase | [5 empty] | Miles |  | # Proj
| Northern | [7 empty] | In Estimating | [5 empty] | 0 |  | 0
| Central Coast | [7 empty] | Pending
| Bay | [7 empty] | Construction Ready
[9 empty] | In Construction | [5 empty] | 4.89 |  | 6
[9 empty] | Complete | [5 empty] | 12.32 |  | 17
[9 empty] | Total | [5 empty] | 17.21 |  | 23
[5 empty] | 17.3513 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
[6 empty] | Low | 18: 10; 19: 11; Total 20: 12; Total 21: 13; Total 22: 13; Total 23: 13; Total 24: 14; Total 25: 13; 17.21 26: 16; 23 29: 11; 23 30: 10
[6 empty] | Medium | 18: 4; 19: 5; Total 20: 4; Total 21: 4; Total 22: 4; Total 23: 5; Total 24: 4; Total 25: 6; 17.21 26: 4; 23 29: 3; 23 30: 2
[6 empty] | High | 18: 9; 19: 7; Total 20: 7; Total 21: 6; Total 22: 5; Total 23: 4; Total 24: 4; Total 25: 3; 17.21 26: 2; 23 29: 4; 23 30: 5
[6 empty] | Complete | Total 22: 1; Total 23: 1; Total 24: 1; Total 25: 1; 17.21 26: 1; 23 29: 4; 23 30: 6

## Pivot
Projects by Phase
[6 empty] | Phase | # Projects | Ckt Miles | [13 empty] | Tree Wire? | YES
[6 empty] | Estimating | 0 | 0 | [13 empty] | Project Status - by Project
[6 empty] | Pending | 0 | 0 | [13 empty] | Sum of Total Miles including partial completions. | Column Labels
[6 empty] | Constr Ready | 0 | 0 | 10.97 | 12 | [11 empty] | Row Labels | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total
[6 empty] | Construction | 6 | 4.89 | 6.562 | 11 | [11 empty] | 1 - Complete | 0.34811 | 6.2568 | 3.5761 | 4.5606 |  |  | 14.7417
[6 empty] | Post-Constr | 17 | 12.32 | [13 empty] | 1a - Complete (Tier 3 only) |  |  |  |  | 0.9025 | 0.76693 | 1.6694
[6 empty] | Grand Total | 23 | 17.21 | [13 empty] | Grand Total | 0.34811 | 6.2568 | 3.5761 | 4.5606 | 0.9025 | 0.76693 | 16.4111
[6 empty] | Tree Wire? | YES
[6 empty] | Project Status - by Unit |  |  |  |  | Risk | May | June | July | Aug | Sep | Oct | Nov |  |  |  | Project Status - by Project
[6 empty] | Row Labels | Count of Order | Sum of Ckt Miles (Adjusted/Actual) |  |  | Complete | 1 |  | 10 |  | 5 | 1 | [5 empty] | Months
[6 empty] | 2 Pending | 3 | 4.0318 |  |  | Risk: Tier 3 Complete; Oct: 2; Nov: 1 |  |  |  | Status | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total
[6 empty] | 3 Constr Ready | 2 | 1.4635 | [13 empty] | 1 - Complete | 0.34811 | 6.2568 | 3.5761 | 4.5606 |  |  | 14.7417
[6 empty] | 4 Construction | 7 | 5.0964 |  |  | Risk: Missed Goal; Oct: 3 |  |  |  | 1a - Partial Completions |  |  |  |  | 0.9025 | 0.76693 | 1.6694
[6 empty] | 5 Post-Constr | 11 | 6.5621 | [13 empty] | Grand Total - Miles | 0.34811 | 6.2568 | 3.5761 | 4.5606 | 0.9025 | 0.76693 | 16.4111
[6 empty] | Grand Total | 23 | 17.1539
Contractor | (All) | [9 empty] | Risk: Tree Wire?; May: YES | Tree Wire? | YES
Hours per Month | [5 empty] | Project Status - by Project |  |  |  |  | Risk: Project Status - by Project | Project Status - by Project
Sum of Feb | Sum of Apr | Sum of May | Sum of Jun | Sum of Jul |  | Row Labels | Count of Order |  |  |  | Risk: Count of Order; May: Column Labels | Row Labels | Count of Order | Sum of Total Miles including partial completions.
507.5 | 50 | 3746.8 | 9387.3 | 12996.6 |  | 2 Pending | 3 |  |  |  | Row Labels | 5 | 7 | 9 | 10 | 11 | 12 | Grand Total | 1 - Complete | 21 | 14.7417
[6 empty] | 3 Constr Ready | 2 |  |  |  | 1 - Complete | 1 | 10 | 5 | 5 |  |  | 21 | 1a - Complete (Tier 3 only) | 2 | 1.6694
[6 empty] | 4 Construction | 7 |  |  |  | Risk: 1a - Complete (Tier 3 only); Sep: 1; Oct: 1; Nov: 2 | Grand Total | 23 | 16.4111
[6 empty] | 5 Post-Constr | 13 |  |  |  | Grand Total | 1 | 10 | 5 | 5 | 1 | 1 | 23
[6 empty] | Grand Total | 25
Estimate Crews Needed
| Feb | Apr | May | Jun | Jul
507.5 |  |  | 8.1629 | 12.3777 | 0
0 |  |  | 0 | 0 | 0
0 |  |  | 0 | 0 | 0
Avail - ST Man Hours |  | 1050 | 1150 | 1050 | 1100
Risk Summary - by Project
Row Labels | Count of Order | [9 empty] | Risk: Project Status - by Unit
1 - Complete | 13 | [9 empty] | Risk: Row Labels
4 - High Risk | 9 | [9 empty] | Risk: 3 Constr Ready
1a - Complete (Tier 3 only) | 3 | [9 empty] | Risk: 4 Construction
Grand Total | 25 | [9 empty] | Risk: 5 Post-Constr
??
Grand Total
Risk Summary - by Unit | [5 empty] | Project Status - by Project
Row Labels | [5 empty] | Row Labels | Count of Order
1 - Complete | [5 empty] | CC | 2
4 - High Risk | [5 empty] | EB | 6
1a - Complete (Tier 3 only) | [5 empty] | NB | 8
Grand Total | [5 empty] | NV | 2
[6 empty] | PN | 1
[6 empty] | SI | 3
[6 empty] | SO | 3
[6 empty] | Grand Total | 25

## High Risk Detail
Order | Order Description | Div | Project Manager | Const. Resource | User Status | Current Reason Off Track | % of Estimate Complete | Current Out of PEND Date | Risk of not completing by 8/1 | Notes | Who is Working on the Projects Major Hurdles
31338871 | El Cerrito G 1112 (Berkeley) Cal Berkeley | EB |  |  | FICL | Access/Permit | 100% | TBD | 1 - Complete | Risk: Access/Permit: Short window to work with two adjacent city projects. City will not allow full road closure without exstensive review. • TCP/Encroachment permit - Meeting with city and contractor again on 6/28/18 to discuss TCP’s. The Following dependences are still needed before the City of Berkeley will issue the work permit. - Temporary Construction Easement (TCE) for resident parking during the full road closure at locations 71 -89. (The land team is currently working on Easement) - Stand by fire and emergency services has been agreed on and confirmed by Berkeley Fire. (Berkeley Fire has agreed to staff project for 1 one) - PG&E has notified residents affected by road closure and outage by the first week on July . - City of Oakland’s approval for the one day road closure on Panoramic way (the top portion is the City of Oakland’s jurisdiction) . • 7/26 locations 90 – 97, assuming (two) 4-man crews • 7/27 locations 90 – 97, assuming (two) 4-man crews • 7/30 locations 63 – 70, assuming (four) 4-man crews • 7/31 locations 71 – 89, assuming (nine) 4-man crews Please note: Project has started 7/26 and planned to complete 7/31, but has so many variables and pieces that need to fall in place it is still be considered high risk. | Access/Permit: [REDACTED]
31082394 | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | SO |  |  | MAPP | Access/Permit | 100% | 2018-06-28 | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | NA
31275384 | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | SO |  |  | MAPP | Access/Permit | 100% | 2018-06-28 | 1 - Complete | Reason for missing date: - 2 months to obtain SO Count Permit, due to volume of rebuild work taking place. When received agency added special conditions to full road closure that would not allow crew to perform work. Permit revision couldn't be obtain in time to cmplete by 8/1. | NA
31246140 | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NV |  |  | FICL | Outage Restrictions (Heat) | 100% | NA | 1 - Complete | Reason for missing date: - 7/18 Clearance canceled due to heat restrictions. - 6/27 Clearance canceled as crew was send to support NV fires. | NA
31330635 | FORESTHILL 1102 (Foresthill) - SPRING GARDEN RD | SI |  |  | FICL | Timing/Size of Project | 100% | 2018-07-13 | 1 - Complete | Risk: Timing/Size of Project: Large project 2.14 miles, EOD 6/20. Challenging Terrain: Helicopter Sets and heavy TW (4/0) causing all poles to be replaced. Very remote. Needed to Meet 8/1: Addtional crews will be needed to complete by 8/1. GC evaluating if crews can be added and work safely. | Timing/Size of Project:[REDACTED]

## Tree Wire
3 | [10 empty] | 59993
Order | MAT | Order Description | Reg | Div | Job Owner Name | Project Managed? | User Status | Risk of not completing by 8/1 | Tree Wire MCODE | DESC | QTY | Planned Ckt Miles | Status | Notes | Construction Resource | Contractor | In-Service Date (Forecasted) | Click Start Date | Click End Date
31246140 | 08W | WYANDOTTE 1105 (Oroville)- RECONDUCTOR 3000 FT OF DET 4AR - WY1105 | NO - Northern | NV |  | Y | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 15000 | 3309 | Delivered |  |  |  | 2018-09-13 | 06/04/2018 | 09/13/2018
31082394 | 08W | Molino 1102 (Santa Rosa) - SIX SPANS FRATI LN | NO - Northern | SO |  | N | MAPP | 3 - Medium Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 2500 | 1486 | Delivered |  |  |  | 2018-09-16 | 09/10/2018 | 09/13/2018
31095523 | 08W | OAKLAND K 1103 (Oakland) - EB-RELIAIBLITY -K1103, REPL #4ACSR W | BA - Bay Area | EB |  | N | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 7500 | 1838 | Delivered |  |  |  | 2018-05-30 | 09/22/2017 | 05/30/2018
31206912 | 08W | CAMP EVERS 2103(Santa Cruz) - WDN 15-0073161 CE2103-OLD GRAHM HL R | CC - Central Coast | CC |  | N | #N/A | 2 - Low Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 2200 | 705 | Delivered |  |  |  | 2018-07-16 | ? | ?
31204706 | 08W | ALTO 1124 (Mill Valley)- THROCKMORTON LANE | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 4856 | 1613 | Delivered |  |  |  | 2018-07-30 | 06/18/2018 | 07/30/2018
31169729 | 08W | Oakland D 1112 (Oakland) - 2017 D1112/K1101 UWF | BA - Bay Area | EB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 3642 | 4171 | Delivered |  |  |  | 2018-07-17 | 05/23/2018 | 07/23/2018
31338871 | 08W | El Cerrito G 1112 (Richmond) - RICHMOND-REPL #6 CU-UWF_PH2 | BA - Bay Area | EB |  | Y | FICL | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12004 | 3505 | Delivered |  |  |  | 2018-10-13 | 07/25/2018 | 10/13/2018
31169728 | 08W | Oakland K 1102 (Oakland)- GRIZZLY PEAK REPL #6 CU-UWF | BA - Bay Area | EB |  | Y | CONS | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12000 | 5016 | Delivered |  |  |  | 2018-11-15 | 06/22/2018 | 11/15/2018
31234871 | 08W | Oakland K 1104 (Oakland) - UWF K1104/X1105/6 | BA - Bay Area | EB |  | Y | MAPP | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 11778 | 7271 | Delivered |  |  |  | 2018-09-25 | 06/26/2018 | 09/25/2018
31207089 | 08J | GREENBRAE 1103 (Mill Valley) - HAWTHORN, GB 1103 | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 3954 | 4687 | Delivered |  |  |  | 2018-09-25 | 07/10/2018 | 07/31/2018
31207126 | 08W | ALTO 1125 (Mill Valley) -PANORAMIC HWY, COUNTY, | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 16454 | 5300 | Delivered |  |  |  | 2018-07-18 | 05/30/2018 | 07/17/2018
31205343 | 08W | ALTO 1124 (Mill Valley) - SUMMIT AVE , CITY | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 11994 | 5006 | Delivered |  |  |  | 2018-07-28 | 06/04/2018 | 06/29/2018
31205198 | 08W | ALTO 1125 (Mill Valley)- REED ST, COUNTY | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 12002 | 3900 | Delivered |  |  |  | 2018-07-16 | # | #
31205418 | 08W | ALTO 1125 (Mill Valley)- BROOKLINE AVE, COUNTY, | BA - Bay Area | NB |  | Y | FICL | 2 - Low Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 16000 | 5480 | Delivered |  |  |  | 2018-07-30 | 06/25/2019 | 07/25/2019
31330635 | 08W | FORESTHILL 1101 (Foresthill) - SPRING GARDEN RD 08J | NO - Northern | SI |  | Y | FICL | 4 - High Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 28373 | 11308 | Ordered |  |  |  | 2018-10-04 | 07/16/2018 | 10/05/2018
31255868 | 08W | ROB ROY 2104 (Day Valley)- HIGH SPLICE CABLE REPLACE | CC - Central Coast | CC |  | Y | PREC | 4 - High Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 4350 | 1439 | Delivered |  |  |  | 2018-07-27 | 07/16/2018 | 07/31/2018
31275384 | 08W | MIRABEL 1101 (Santa Rosa)- R7 RECONDUCTOR MAYS CANYON | NO - Northern | SO |  | N | MAPP | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 6256 | 1986 | Not Ordered |  |  |  | 2018-10-09 | 09/10/2018 | 10/09/2018
31286571 | 08W | EL DORADO PH 2102 (Pollock Pines) - HIGH SPLICE AREA | NO - Northern | SI |  | Y | FICL | 3 - Medium Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 6300 | 1928 | Delivered |  |  |  | 2018-09-11 | 07/10/2018 | 09/11/2018
31264915 | 08W | RINCON 1103 (Santa Rosa) - R7 RECONDUCTOR WILSON RD- | NO - Northern | SO |  | N | FICL | 2 - Low Risk | M290398 | WIRE ELEC INSUL AL 2 AWG 22KV 7/1 ACSR | 2397 | 957 | Delivered |  |  |  | 2018-07-26 | # | #
31098626 | 08W | CLARKSVILLE 2104 (El Dorado Hills) - ECONDUCTOR -PH 3 Y2018 | NO - Northern | SI |  | Y | UNSC | 4 - High Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 25364 | 8052 | Ordered | 9355 ft remaining. Not need for a away Tier 1/2. |  |  | 2019-03-31 | 09/12/2018 | 10/01/2018
31206678 | 08W | ALTO 1125 (Mill Valley) -SEQUOIA VLY RD CTY/CNTY | BA - Bay Area | NB |  | Y | UNSC | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 8877 | 2817 | Delivered |  |  |  | 2019-01-30 | 03/29/2019 | 03/29/2019
31205937 | 08W | ALTO 1125 (Mill Valley) -HELENS LN,CITY/CNTY,ALTO | BA - Bay Area | NB |  | Y | MAPP | 3 - Medium Risk | M295046 | WIRE ELEC INSL AL 4/0 AWG 22KV 7 STRAND | 14387 | 5000 | Delivered |  |  |  | 2018-10-17 | 09/09/2018 | 10/05/2018
31132867 | 08W | Half Moon Bay 1101 (Half Moon Bay)- REPLACE OH LINE SKYLINE BLVD | CC - Central Coast | PN |  | Y | #N/A | 4 - High Risk | M295053 | WIRE ELEC INSL COP 2 AWG 165MIL HM-HDPE | 14624.7 | 4638 | Delivered |  |  |  | 2018-07-31 | ? | ?

## Drop Down
1 - Complete | JO | JO Name | PM? | Region | Abbr. | Division | Abbr. | Status | Phase | Status | Phase
2 - Low Risk |  |  | N | BA - Bay Area | BA | Central Coast | CC | ADER | 1 Estimating | ADER | Estimating
3 - Medium Risk |  |  | Y | CC - Central Coast | CC | De Anza | DA | APPR | 1 Estimating | APPR | Estimating
4 - High Risk |  |  | Y | CV - Central Valley | CV | Diablo | DI | CNCL | 6 Other | CNCL | Other
1a - Complete (Tier 3 only) |  |  | Y | NO - Northern | NO | East Bay | EB | CONS | 4 Construction | CONS | Construction
|  |  | N |  |  | Fresno | FR | DCNL | 1 Estimating | DCNL | Estimating
|  |  | Y |  |  | Humboldt | HB | DOCC | 5 Post-Constr | DOCC | Post-Constr
|  |  | Y |  |  | Kern | KE | ERDY | 1 Estimating | ERDY | Estimating
|  |  | N |  |  | Los Padres | LP | ESTS | 1 Estimating | ESTS | Estimating
|  |  | Y |  |  | Mission | MI | FICL | 5 Post-Constr | FICL | Post-Constr
|  |  | N |  |  | North Bay | NB | MAPP | 5 Post-Constr | MAPP | Post-Constr
|  |  | N |  |  | North Valley | NV | PEND | 2 Pending | PEND | Pending
|  |  | N |  |  | Peninsula | PN | PREC | 5 Post-Constr | PREC | Post-Constr
|  |  | Y |  |  | Sacramento | SA | PROD | 6 Other | PROD | Other
|  |  | N |  |  | San Francisco | SF | SRDY | 4 Construction | SRDY | Construction
|  |  | Y |  |  | San Jose | SJ | UNSC | 3 Constr Ready | UNSC | Constr Ready
|  |  | Y |  |  | Sierra | SI | UNSE | 1 Estimating | UNSE | Estimating
|  |  | Y |  |  | Sonoma | SO | UNSE HOLD | 1 Estimating | UNSE HOLD | Estimating
|  |  | Y |  |  | Stockton | ST | CLSD | 5 Post-Constr | CLSD | Post-Constr
|  |  | N |  |  | Yosemite | YO
N
Y
N
Y
N
N
N
Y
Y
N
N
N
Y
Y
N
N
N
Y
N
N
N
N
Y
N
N
N
Y (Sub)
N
N
N
N
Y
N
N
N
N
N
N
N
N
N
N
N
N
N
N
Y
Y
Y
N
N
Y
N
N
N
N
Y
N
N
N
N
N
N
Y
N
N
Y
N
N
N
Y
N
Y
N
Y
N
N
Y
Y
N
Y
Y
N
N
Y
N
N
N
N
N
N
N
N
N
N
N
Y
N
N
N
Y
N
N
N
Y
N
N
Y (TL)
N
Y
Y
Y
Y
N
Y
Y
N
Y
N
N
Y
N
N
Y
N
Y (Sub)
N
N
N
N
N
N
Y (Sub)
N
Y
N
N
N
N
Y
N
Y
N
N
Y
Y
N
N
Y
Y
Y
N
Y
N