## Construction
Q4 TARGET - 150 miles construction complete and QA
CONSTRUCTION
Order | Description | MAT | Contractor | Area | Status | Planned Miles | YTD Miles | % Complete | City | County | Notes
74022040 | CALISTOGA 1101 | 08W |  | North Coast | DOCC | 1.2646 | 1.2646 | 100% | CALISTOGA | Napa
31389447 | PUEBLO 1105 RECONDUCTOR PROJECT | 08W |  | North Coast | DOCC | 1.27 | 1.27 | 100% | NAPA | Napa
35040742 | DEMO - CWSP - 2018 MONTE RIO 1112 OH TO UG DEMO | 08W |  | North Coast | MAPP | 0.53 | 0.53 | 100% | OCCIDENTAL | Sonoma
35039002 | DEMO - 2018 CALISTOGA 1101 WILDFIRE DEMO Comp | 08W |  | North Coast | MAPP | 1.1377 | 1.1377 | 100% | CALISTOGA | Napa
31278200 | OCEANO 1102 S HALCYON & PINE RDGE | 08W |  | South Coast Valley | MAPP | 0.39 | 0.39 | 100% | ARROYO GRANDE | San Luis Obispo
35024926 | MARTELL 1101 RECONDCUTOR 3,700FT | 08W |  | Tri-Valley | DOCC | 0.13 | 0.13 | 100% | SUTTER CREEK | Amador
31425508 |  | 95 |  | Sacramento Valley | MAPP | 0.079924 | 0.079924 | 100% | PARADISE | Butte
31425506 |  | 95 |  | Sacramento Valley | FICL | 0.05 | 0.05 | 100% | PARADISE | Butte
31415330-a | FLEA MOUNTAIN (Big Bend 1101) | 95 |  | Sacramento Valley | DOCC | 3.49 | 3.49 | 100% |  | Butte
31415330-b | Big Bend RR Hardening (Bardee's Bar) | 95 |  | Sacramento Valley | DOCC | 1.1229 | 1.1229 | 100% |  | Butte
31401029-a | FRENCH GULCH 1101 Removal | 95 |  | Sacramento Valley | DOCC | 3.104 | 3.104 | 100% |  | Shasta
31286573 | Apple Hill 2102 | 08W |  | Sacramento Valley | FICL | 0.66136 | 0.66136 | 100% | SOMERSET | El Dorado
31215474 | Reconductor Rob Roy 2104 McDonald | 08W |  | South Coast Valley | FICL | 0.51 | 0.51 | 100% | APTOS | Santa Cruz
31360766 | FROGTOWN 1701 RECOND 1080FT TO 2AR | 08W |  | Tri-Valley | FICL | 0.22 | 0.22 | 100% | MURPHYS | Calaveras
35008479 | Auberry 1101 Reconductor | 08W |  | South Coast Valley | FICL | 0.31 | 0.31 | 100% | TOLLHOUSE | Fresno
74022387 | MIDDLETOWN 1101-TS 1079 | 08W |  | North Coast | DOCC | 3.9701 | 3.9701 | 100% | MIDDLETOWN | Lake
35101036 | Bucks Creek - BUCOCAMP POLE_BURN - BARDEES BAR RD OROV | 95 |  | Sacramento Valley | DOCC | 4.1068 | 4.1068 | 100% |  | Butte
35101860 | Bucks Creek - BUCOCAMP POLE_BURN HWY 70 OROVILLE | 95 |  | Sacramento Valley | FICL | 4.7458 | 4.7458 | 100% |  | Butte
35101861 | Bucks Creek - BUCOCAMP POLE BURN -CAMP CRK RD OROVILLE | 95 |  | Sacramento Valley | DOCC | 4.2203 | 4.2203 | 100% |  | Butte
Multiple | Paradise Rebuild - Q2 Small Jobs | 95 |  | Sacramento Valley | DOCC | 3.1265 | 3.1265 | 100% |  | Various | See separate tab for details
31269259 | ZACA 1101 FOXEN CYN RD, LOS OLIVOS | 08W |  | South Coast Valley | FICL | 1.2095 | 1.2095 | 100% | LOS OLIVOS | Santa Barbara
31232280 | ZACA 1102 LONG CYN RD, SANTA YNEZ | 08W |  | South Coast Valley | DOCC | 1.1081 | 1.1081 | 100% | SANTA YNEZ | Santa Barbara
74021960 | BRUNSWICK 1105 (LR 32536) | 08W |  | Sacramento Valley | DOCC | 5.8756 | 5.8756 | 100% | NEVADA CITY | Nevada
74021903 | BRUNSWICK 1105 LR-1030 ZONE | 08W |  | Sacramento Valley | DOCC | 4.771 | 4.771 | 100% | NEVADA CITY | Nevada
35052718 | Silverado 2104 (UG) | 08W |  | North Coast | FICL | 0.42898 | 0.42898 | 100% | ANGWIN | Napa
35089880 | PIH - SILVERADO 2104 - ANGWIN UG_PH 2 | 08W |  | North Coast | MAPP | 0.40095 | 0.40095 | 100% | ANGWIN | Napa
31289238 | Fruitland 1142-2 | 08W |  | North Coast | DOCC | 1.1877 | 1.1877 | 100% | MYERS FLAT | Humboldt
35060229 | Fruitland 1142 | 08W |  | North Coast | DOCC | 1.2366 | 1.2366 | 100% | MIRANDA | Humboldt
31082393 | Cherry Ridge Road | 08W |  | North Coast | DOCC | 0.25473 | 0.25473 | 100% | SEBASTOPOL | Sonoma
31290145 | San Rafael 1107 | 08W |  | North Coast | MAPP | 0.1517 | 0.1517 | 100% | KENTFIELD | Marin
35064793 | LP CABRILLO 1104 S006CC102 | 08W |  | South Coast Valley | FICL | 2.2996 | 2.2996 | 100% | LOMPOC | Santa Barbara
31290147 | Olema 1101 | 08W |  | North Coast | DOCC | 0.60114 | 0.60114 | 100% | INVERNESS | Marin
31209950 | Potter Valley 1105 | 08W |  | North Coast | DOCC | 0.5697 | 0.5697 | 100% | POTTER VALLEY | Mendocino
35060582 | SLO 1107 Recon 3,836 ft of 4ar to 2cu in corrosion zone | 08W |  | South Coast Valley | DOCC | 0.73561 | 0.73561 | 100% | OCEANO | San Luis Obispo
35018788 | Apple Hill 1104 | 08W |  | Sacramento Valley | DOCC | 1.1593 | 1.1593 | 100% | CAMINO | El Dorado
35032266 | Apple Hill 1104 - 2 | 08W |  | Sacramento Valley | DOCC | 0.1661 | 0.1661 | 100% | POLLOCK PINES | El Dorado
35043303 | Eel River 1102 - 2 | 08W |  | North Coast | DOCC | 1.5417 | 1.5417 | 100% | FERNDALE | Humboldt
35080227 | Calistoga 1101 - Legal Hold | 08W |  | North Coast | MAPP | 0.3553 | 0.3553 | 100% | CALISTOGA | Napa
31434881 | BUCOCAMP 3100 SKYWAY RD "MANCAMP" | 16H |  | Sacramento Valley | DOCC | 3.3589 | 3.3589 | 100% |  | Butte
35122641 | BUCOCAMP - CENTERVILLE CNYN TIE LINE RMV | 95 |  | Sacramento Valley | DOCC | 4.1657 | 4.1657 | 100% |  | Butte
99999999 | Q3 Idle Facilities | 2AF |  | Various | DOCC | 10.7888 | 10.7888 | 100% |  | Various | See separate tab for details
Multiple | Paradise Rebuild - Q3 Small Jobs | 95 |  | Sacramento Valley | DOCC | 1.9597 | 1.9597 | 100% |  | Various | See separate tab for details
35040225 | Higgins 1110 | 08W |  | Sacramento Valley | DOCC | 1.6258 | 1.6258 | 100% | GRASS VALLEY | Nevada
35085393 | CWSP Silverado 2104 1B | 08W |  | North Coast | DOCC | 0.35436 | 0.35436 | 100% | SAINT HELENA | Napa
35085681 | SILVERADO 2105 WIRE DOWN PH 4 | 08W |  | North Coast | DOCC | 0.55568 | 0.55568 | 100% | SAINT HELENA | Napa
35098579 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 3 | 08W |  | Sacramento Valley | DOCC | 1.4343 | 1.4343 | 100% | NORTH SAN JUAN | Nevada
35094388 | CWSP Konocti-1102-LR 532 PH 1 | 08W |  | North Coast | DOCC | 0.42443 | 0.42443 | 100% | KELSEYVILLE | Lake
99999998 | Q4 Idle Facilities | 2AF |  | Various | DOCC | 1.342 | 1.342 | 100% |  | Various | See separate tab for details
Multiple | Q4 Paradise Rebuild | 95 |  | Sacramento Valley | DOCC | 8.6195 | 8.6195 | 100% |  | Various | See separate tab for details
35120949 | BUCOCAMP - SKYWAY CHICO PARADISE TIE PH2 (UG) | 08W |  | Sacramento Valley | DOCC | 1.9223 | 1.9223 | 100% |  | Butte
35072720 | Gabilan 1101 17-0077248 | 08W |  | South Coast Valley | DOCC | 2.2244 | 2.2244 | 100% | SALINAS | Monterey
35098622 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 5 | 08W |  | Sacramento Valley | DOCC | 2.4813 | 2.4813 | 100% | NORTH SAN JUAN | Nevada
35085534 | CWSP Silverado 2104 1E:Harden OH InPlace | 08W |  | North Coast | CONS | 0.79375 | 0.069697 | 8.781% | SAINT HELENA | Napa
35072362 | Eel River 1102 | 08W |  | North Coast | DOCC | 2.7068 | 2.7068 | 100% | FERNDALE | Humboldt
35058905 | Volta 1102 LR 1648 Ph 4.1 | 08W |  | Sacramento Valley | CONS | 2.1108 | 1.3587 | 64.37% | SHINGLETOWN | Shasta
35110442 | CWSP - Volta 1102 - LR 1648 - Ph 3.2 | 08W |  | Sacramento Valley | DOCC | 1.3551 | 1.3244 | 97.74% | SHINGLETOWN | Shasta
35109543 | CWSP - El Dorado 2101 - 19752 - PHASE 1.5 | 08W |  | Sacramento Valley | DOCC | 1.6898 | 1.6898 | 100% |  | El Dorado
35085538 | SILVERADO 2105 WIRE DOWN PH 1 OH | 08W |  | North Coast | CONS | 1.9903 | 0.96326 | 48.4% | SAINT HELENA | Napa
35085537 | CWSP Silverado 2104 1H | 08W |  | North Coast | CONS | 0.71061 | 0.59167 | 83.26% | SAINT HELENA | Napa
35109550 | CWSP - El Dorado 2101 - 19752 - PHASE 3.3 | 08W |  | Sacramento Valley | CONS | 1.915 | 1.6239 | 84.8% |  | El Dorado
35110445 | CWSP - Volta 1102 - LR 1648 - Ph4.2 | 08W |  | Sacramento Valley | DOCC | 1.6417 | 1.4508 | 88.37% | SHINGLETOWN | Shasta
35043291 | CWSP- PINE GROVE 1102 LR9145 WFH LEVEL 1 | 08W |  | Tri-Valley | MAPP | 2.8733 | 2.8733 | 100% | PINE GROVE | Amador
35110444 | CWSP - Volta 1102 - LR 1648 - Ph 3.4 | 08W |  | Sacramento Valley | CONS | 1.4741 | 0.7858 | 53.31% | SHINGLETOWN | Shasta
35112076 | CWSP - FULTON 1107 - MARK WEST SPR RD. | 08W |  | North Coast | CONS | 2.2019 | 0.16856 | 7.655% | SANTA ROSA | Sonoma
35031139 | Shady Glen 1102 | 08W |  | Sacramento Valley | DOCC | 1.5182 | 1.5182 | 100% | COLFAX | Placer
35109549 | CWSP - El Dorado 2101 - 19752 - PHASE 3.2 | 08W |  | Sacramento Valley | CONS | 1.3375 | 0.68485 | 51.2% |  | El Dorado
35057017 | CWSP - EL DORADO 2101 - 19752 - PHASE 3.1 | 08W |  | Sacramento Valley | DOCC | 1.7057 | 1.7057 | 100% |  | El Dorado
35085532 | CWSP Silverado 2104 1C:Harden OH InPlace | 08W |  | North Coast | DOCC | 1.1265 | 1.1265 | 100% | SAINT HELENA | Napa
35106042 | CWSP - Volta 1102 - LR 1648 - Ph1.2 | 08W |  | Sacramento Valley | CONS | 1.8193 | 0.73466 | 40.38% | SHINGLETOWN | Shasta
35109542 | CWSP - El Dorado 2101 - 19752 - PHASE 1.4 | 08W |  | Sacramento Valley | DOCC | 1.832 | 1.832 | 100% |  | El Dorado
35019006 | Rob Roy 2104 CO11865 | 08W |  | South Coast Valley | DOCC | 1.804 | 1.804 | 100% | CORRALITOS | Santa Cruz
35098578 | CWSP-COLUMBIA HILL 1101-LR 2212 Ph 2 | 08W |  | Sacramento Valley | DOCC | 1.7955 | 1.7955 | 100% | NORTH SAN JUAN | Nevada
35109551 | CWSP - El Dorado 2101 - 19752 - PHASE 3.4 | 08W |  | Sacramento Valley | CONS | 1.4354 | 1.0926 | 76.12% |  | El Dorado
35109552 | CWSP - El Dorado 2101 - 19752 - PHASE 3.5 | 08W |  | Sacramento Valley | CONS | 2.1417 | 1.8341 | 85.64% |  | El Dorado
35081748 | Rob Roy 2105-SO28CC1119 | 08W |  | South Coast Valley | CONS | 0.30398 | 0.16098 | 52.96% | APTOS | Santa Cruz
35110443 | CWSP - Volta 1102 - LR 1648 - Ph 3.3 | 08W |  | Sacramento Valley | CONS | 1.2557 | 1.0956 | 87.25% | SHINGLETOWN | Shasta
35023687 | Ben Lomond 0401 | 08W |  | South Coast Valley | DOCC | 1.3341 | 1.3341 | 100% | BEN LOMOND | Santa Cruz
74021963 | Oakland K 1102 | 08W |  | Bay Area/Peninsula | CONS | 2.7609 | 2.4753 | 89.66% | OAKLAND | Alameda
35103065 | Moraga 1101 | 08W |  | Bay Area/Peninsula | CONS | 2.3862 | 2.3163 | 97.07% | ORINDA | Contra Costa
35042719 | CWSP DEMO: ANGWIN (Silverado) Steel | 08W |  | North Coast | DOCC | 0.24148 | 0.24148 | 100% | ANGWIN | Napa
35061709 | Silverado 2104 | 08W |  | North Coast | DOCC | 1.5157 | 1.5157 | 100% | ANGWIN | Napa
31275658 | Dunbar 1102 | 08W |  | North Coast | DOCC | 0.48864 | 0.48864 | 100% | SONOMA | Sonoma
31319444 | Rincon 1103 | 08W |  | North Coast | DOCC | 0.24223 | 0.24223 | 100% | SANTA ROSA | Sonoma
31334292 | Austin Creek Rd | 08W |  | North Coast | DOCC | 0.47216 | 0.47216 | 100% | CAZADERO | Sonoma
35030654 | TW ON WOODSIDE1101 N/O 7573 | 08W |  | Bay Area/Peninsula | DOCC | 0.9983 | 0.9983 | 100% | REDWOOD CITY | San Mateo
35018787 | Halsey 1101 | 08W |  | Sacramento Valley | DOCC | 0.54053 | 0.54053 | 100% | MEADOW VISTA | Placer
74024171 | Calistoga 1101 - Petrified Forest Rd. | 08W |  | North Coast | DOCC | 2.61 | 2.61 | 100% | CALISTOGA | Napa
35055474 | Redbud 1101 Reconductor (Clearlake) | 06H |  | North Coast | DOCC | 1.4309 | 1.4309 | 100% | ANGWIN | Napa
35043299 | Eel River 1102 - 3 | 08W |  | North Coast | DOCC | 1.2076 | 1.2076 | 100% | FERNDALE | Humboldt
35111500 | RECONDUCTOR UPPER LAKE 01 HUNTERS PT RD | 08W |  | North Coast | DOCC | 0.35038 | 0.35038 | 100% |  | Lake
35095165 | Volta 1102 LR 1648 Ph 3.1 | 08W |  | Sacramento Valley | DOCC | 0.69432 | 0.69432 | 100% | SHINGLETOWN | Shasta
35085533 | CWSP Silverado 2104 1D | 08W |  | North Coast | DOCC | 1.0161 | 1.0161 | 100% | SAINT HELENA | Napa
35066745 | Big Bend 1102 - Bloomer Hill | 08W |  | Sacramento Valley | DOCC | 1.6856 | 1.6856 | 100% | CORNING | Tehama
35072146 | Silverado 2105 WIRE DOWN OH | 08W |  | North Coast | DOCC | 0.69773 | 0.69773 | 100% | SAINT HELENA | Napa
35113871 | Silverado 2104 - 2 Phase 2 (UG) | 08W |  | North Coast | DOCC | 0.12311 | 0.12311 | 100% | SAINT HELENA | Napa
35094390 | CWSP Konocti-1102-LR 532 PH 3 | 08W |  | North Coast | DOCC | 0.54564 | 0.54564 | 100% | KELSEYVILLE | Lake
35085536 | CWSP Silverado 2104 1G | 08W |  | North Coast | DOCC | 1.3277 | 1.3277 | 100% | SAINT HELENA | Napa
31291071 | OCGC 14043533 WRO - HWY 175 MIDDLETOWN | 10J |  | North Coast | MAPP | 1.2468 | 1.2468 | 100% |  | Lake
31326119 | Weimar 1101 | 08W |  | Sacramento Valley | DOCC | 0.56629 | 0.56629 | 100% | COLFAX | Placer
35103324 | CWSP - Rossmoor 1102 OCB | 08W |  | Bay Area/Peninsula | CONS | 0.76629 | 0.45587 | 59.49% | ORINDA | Contra Costa
35113103 | CWSP - Los Gatos 1106 - LB44 - Phase 1.3 | 08W |  | Bay Area/Peninsula | DOCC | 0.21818 | 0.21818 | 100% | LOS GATOS | Santa Clara
35085539 | SILVERADO 2105 WIRE DOWN PH 2 OH | 08W |  | North Coast | CONS | 1.9432 | 1.1089 | 57.07% | SAINT HELENA | Napa
35113104 | CWSP - Los Gatos 1106 - LB44 - Phase 1.2 | 08W |  | Bay Area/Peninsula | DOCC | 0.25081 | 0.25081 | 100% | LOS GATOS | Santa Clara
35113109 | CWSP - Los Gatos 1106 - LB44 - Ph 3.2 Beardsley | 08W |  | Bay Area/Peninsula | MAPP | 0.12898 | 0.12898 | 100% | LOS GATOS | Santa Clara
35109737 | CWSP - Volta 1102 - LR 1648 - Ph 2.2 | 08W |  | Sacramento Valley | CONS | 2.1352 | 0.37273 | 17.46% | SHINGLETOWN | Shasta
35109553 | CWSP - El Dorado 2101 - 19752 - PHASE 3.6 | 08W |  | Sacramento Valley | CONS | 2.6667 | 1.4146 | 53.05% |  | El Dorado
35109555 | CWSP - El Dorado 2101 - 19752 - PHASE 4.3 | 08W |  | Sacramento Valley | CONS | 2.2436 | 0.75303 | 33.56% |  | El Dorado
35112426 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.3 | 08W |  | Sacramento Valley | DOCC | 1.8089 | 1.7117 | 94.63% |  | El Dorado
35112427 | CWSP - El Dorado 2101 - OCB Zone - Ph 1.4 | 08W |  | Sacramento Valley | CONS | 0.98883 | 0.071402 | 7.221% |  | El Dorado
35106265 | CWSP - Volta 1102 - LR 1648 - Ph1.3 | 08W |  | Sacramento Valley | CONS | 1.7972 | 0.086364 | 4.806% | SHINGLETOWN | Shasta
35109739 | CWSP - Volta 1102 - LR 1648 - Ph 2.4 | 08W |  | Sacramento Valley | CONS | 2.5083 | 1.2381 | 49.36% | SHINGLETOWN | Shasta
35094392 | CWSP Konocti-1102-LR 532 PH 5 | 08W |  | North Coast | MAPP | 0.37045 | 0.37045 | 100% | KELSEYVILLE | Lake
74022382 | Columbia Hill 1101 | 08W |  | Sacramento Valley | DOCC | 2.3464 | 2.3464 | 100% | NORTH SAN JUAN | Nevada
74021961 | MIRABEL 1102 /MONTE RIO 13 - LR 652 | 08W |  | North Coast | DOCC | 4.767 | 4.767 | 100% | FORESTVILLE | Sonoma
31475979 | Kincade Fire Rebuild | 95 |  | North Coast | DOCC | 0.99924 | 0.99924 | 100% |  | Sonoma
[5 empty] | TOTAL | 216.4837 | 171.1623
Complete in Q1-3
Complete in Q4
In Progress

## Q2Paradise
Order | Description | MAT | Estimating Category | 2019 Category | Physical Contractor | EOD | Planned Miles | Feet Hardened | Miles Hardened | SAP Status | Field Status | Bucket | City | County | Contract Status | Scoping | ProgressCurrent | ProgressPrevious | Change
31420416 |  | 95 | N/A | 2019 Baseline |  |  | 0.16723 | 883 | 0.16723 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31420810 | Billie Park Restrooms | 95 | N/A | 2019 Baseline |  |  | 0.15663 | 827 | 0.15663 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
UG 31422901 & OH 31422838 |  | 95 | N/A | 2019 Baseline |  |  | 0.031629 | 167 | 0.031629 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
OH 31422565 UG 31422566 |  | 95 | N/A | 2019 Baseline |  |  | 0.13485 | 712 | 0.13485 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31422902 |  | 95 | N/A | 2019 Baseline |  |  | 0.048295 | 255 | 0.048295 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31422909 |  | 95 | N/A | 2019 Baseline |  |  | 0.1714 | 905 | 0.1714 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31425894 | Chaparral Dr Paradise/95A Re-Build line | 95 | N/A | 2019 Baseline |  |  | 0.38201 | 2017 | 0.38201 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31423331 |  | 95 | N/A | 2019 Baseline |  |  | 0.079545 | 420 | 0.079545 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31427127 | Comcast-Forest Service Rd Paradise | 95 | N/A | 2019 Baseline |  |  | 0.15 | 792 | 0.15 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35073525 |  | 95 | N/A | 2019 Baseline |  |  | 0.3839 | 2027 | 0.3839 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35077480 |  | 95 | N/A | 2019 Baseline |  |  | 0.22064 | 1165 | 0.22064 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31426083 |  | 95 | N/A | 2019 Baseline |  |  | 0.032955 | 174 | 0.032955 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31426086 |  | 95 | N/A | 2019 Baseline |  |  | 0.0094697 | 50 | 0.0094697 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35078820 |  | 95 | N/A | 2019 Baseline |  |  | 0.0875 | 462 | 0.0875 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35077549 |  | 95 | N/A | 2019 Baseline |  |  | 0.051136 | 270 | 0.051136 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35077252 |  | 95 | N/A | 2019 Baseline |  |  | 0.10663 | 563 | 0.10663 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31426417 |  | 95 | N/A | 2019 Baseline |  |  | 0.14318 | 756 | 0.14318 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35081665 |  | 95 | N/A | 2019 Baseline |  |  | 0.025947 | 137 | 0.025947 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35082172 |  | 95 | N/A | 2019 Baseline |  |  | 0.16288 | 860 | 0.16288 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31433961 |  | 95 | N/A | 2019 Baseline |  |  | 0.049811 | 263 | 0.049811 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31426416 |  | 95 | N/A | 2019 Baseline |  |  | 0.10947 | 578 | 0.10947 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
31426519 |  | 95 | N/A | 2019 Baseline |  |  | 0.14053 | 742 | 0.14053 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35091861 |  | 95 | N/A | 2019 Baseline |  |  | 0.045076 | 238 | 0.045076 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35088308 |  | 95 | N/A | 2019 Baseline |  |  | 0.092045 | 486 | 0.092045 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35088309 |  | 95 | N/A | 2019 Baseline |  |  | 0.10038 | 530 | 0.10038 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
35076188 |  | 95 | N/A | 2019 Baseline |  |  | 0.043371 | 229 | 0.043371 | #N/A | DOCC | 5 QA/QC (DOCC+) | PARADISE | Butte |  | Scoped | 5 | #N/A | #N/A
3.1265

## Q3Paradise
Order | Description | MAT | Estimating Category | Construction Year | Physical Contractor | EOD | Planned Miles | Feet Hardened | Miles Hardened | SAP Status | Field Status | Bucket | City | County | Contract Status | Scoping | ProgressCurrent | ProgressPrevious | Change
35080391 |  | 95 | N/A | 2019 |  |  | 0.21951 | 1159 | 0.21951 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35087685 |  | 95 | N/A | 2019 |  |  | 0.051515 | 272 | 0.051515 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35099113 |  | 95 | N/A | 2019 |  |  | 0.053409 | 282 | 0.053409 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35102732 |  | 95 | N/A | 2019 |  |  | 0.97481 | 5147 | 0.97481 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35094363 |  | 95 | N/A | 2019 |  |  | 0.10511 | 555 | 0.10511 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35106277 |  | 95 | N/A | 2019 |  |  | 0.055114 | 291 | 0.055114 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35081676 |  | 95 | N/A | 2019 |  |  | 0.095455 | 504 | 0.095455 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35100245 |  | 95 | N/A | 2019 |  |  | 0.07803 | 412 | 0.07803 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35106027 |  | 95 | N/A | 2019 |  |  | 0.061553 | 325 | 0.061553 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35087693 |  | 95 | N/A | 2019 |  |  | 0.12614 | 666 | 0.12614 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
35106025 |  | 95 | N/A | 2019 |  |  | 0.13902 | 734 | 0.13902 |  | DOCC | 5 QA/QC (DOCC+) | Paradise | Butte |  | Scoped
[7 empty] | 1.9597 |  | 1.9597

## Q4ParadiseRebuild
Order | Project | Finish Date | Primary Length (FT) | Miles
35131804 |  | 2019-11-22 | 392 | 0.074242
35131034 |  | 2019-11-22 | 402 | 0.076136
35129370 |  | 2019-11-09 | 687 | 0.13011
35127511 |  | 2019-11-22 | 226 | 0.042803
35126986 |  | 2019-11-11 | 1121 | 0.21231
35126879 |  | 2019-11-15 | 292 | 0.055303
35126607 |  | 2019-11-22 | 887 | 0.16799
35126592 |  | 2019-11-16 | 229 | 0.043371
35126588 |  | 2019-11-02 | 860 | 0.16288
35126139 |  | 2019-11-18 | 1035 | 0.19602
35126138 |  | 2019-11-19 | 320 | 0.060606
35126057 |  | 2019-11-03 | 678 | 0.12841
35123825 |  | 2019-11-03 | 1379 | 0.26117
35123202 |  | 2019-11-13 | 884 | 0.16742
35123195 |  | 2019-11-16 | 50 | 0.0094697
35123182 |  | 2019-10-22 | 1137 | 0.21534
35121380 |  | 2019-11-02 | 256 | 0.048485
35121259 |  | 2019-11-03 | 532 | 0.10076
35120508 |  | 2019-10-17 | 290 | 0.054924
35120507 |  | 2019-10-18 | 960 | 0.18182
35120368 |  | 2019-11-03 | 362 | 0.068561
35120069 |  | 2019-11-01 | 1395 | 0.2642
35120063 |  | 2019-10-18 | 328 | 0.062121
35119726 |  | 2019-11-01 | 403 | 0.076326
35119487 |  | 2019-10-18 | 582 | 0.11023
35118171 |  | 2019-11-22 | 261 | 0.049432
35118170 |  | 2019-10-21 | 157 | 0.029735
35117411 |  | 2019-10-18 | 493 | 0.093371
35117406 |  | 2019-09-14 | 1095 | 0.20739
35117381 |  | 2019-09-26 | 525 | 0.099432
35117219 |  | 2019-11-19 | 463 | 0.087689
35117218 |  | 2019-01-03 | 700 | 0.13258
35117130 |  | 2019-11-03 | 682 | 0.12917
35117128 |  | 2019-10-16 | 536 | 0.10152
35117126 |  | 2019-09-16 | 980 | 0.18561
35117121 |  | 2019-09-13 | 1140 | 0.21591
35117031 |  | 2019-10-21 | 568 | 0.10758
35116866 |  | 2019-10-22 | 265 | 0.050189
35116863 |  | 2019-11-16 | 540 | 0.10227
35116861 |  | 2019-10-14 | 1089 | 0.20625
35114629 |  | 2019-09-11 | 511 | 0.09678
35113925 |  | 2019-09-21 | 167 | 0.031629
35113528 |  | 2019-09-19 | 200 | 0.037879
35113526 |  | 2019-09-16 | 387 | 0.073295
35113524 |  | 2019-10-19 | 185 | 0.035038
35113522 |  | 2019-10-15 | 784 | 0.14848
35113521 |  | 2019-10-14 | 1130 | 0.21402
35113520 |  | 2019-10-18 | 337 | 0.063826
35113075 |  | 2019-09-27 | 392 | 0.074242
35113072 |  | 2019-08-17 | 366 | 0.069318
35112838 |  | 2019-10-05 | 167 | 0.031629
35112837 |  | 2019-09-25 | 410 | 0.077652
35112822 |  | 2019-11-03 | 1264 | 0.23939
35112770 |  | 2019-07-26 | 369 | 0.069886
35112699 |  | 2019-08-20 | 299 | 0.056629
35112698 |  | 2019-09-17 | 1164 | 0.22045
35112504 |  | 2019-07-26 | 528 | 0.1
35111096 |  | 2019-09-16 | 136 | 0.025758
35110919 |  | 2019-09-12 | 480 | 0.090909
35110916 |  | 2019-10-07 | 503 | 0.095265
35110849 |  | 2019-08-31 | 341 | 0.064583
35110843 |  | 2019-09-26 | 377 | 0.071402
35110799 |  | 2019-10-16 | 222 | 0.042045
35110795 |  | 2019-09-30 | 936 | 0.17727
35110725 |  | 2019-10-13 | 281 | 0.05322
35110712 |  | 2019-09-07 | 2404 | 0.4553
35106022 |  | 2019-09-20 | 493 | 0.093371
35105132 |  | 2019-09-12 | 450 | 0.085227
35103767 |  | 2019-08-10 | 251 | 0.047538
35100982 |  | 2019-08-28 | 853 | 0.16155
35100980 |  | 2019-10-18 | 510 | 0.096591
35100244 |  | 2019-09-13 | 380 | 0.07197
35100240 |  | 2019-09-07 | 96 | 0.018182
35099740 |  | 2019-09-09 | 1929 | 0.36534
35096604 |  | 2019-09-27 | 218 | 0.041288
35081674 |  | 2019-11-04 | 254 | 0.048106
35081535 |  | 2019-09-23 | 556 | 0.1053
|  | Total | 45511 | 8.6195

## Q3IdleFacilities
Order | MAT | Footage | Planned Miles | Completed | SAP Status | Area | Main Work Center | Notification | HFTD | Circuit | City | Plat Map | Latitude | Longitude
31048050 | 2AF | 1185 | 0.22443 | 0.22443 | CLSD |  |  | 000107470323 | TIER 3 | 15308-2106, PLACERVILLE |  | T16 | 38.9288 | -120.77 | 2AF
31048480 | 2AF | 230 | 0.043561 | 0.043561 | CLSD |  |  | 000114814001 | TIER 2 | 15803-1101, ECHO SUMMIT |  | K2520 | 39.3233 | -120.3824 | 2AF
31081464 | 2AF | 819 | 0.15511 | 0.15511 | CLSD |  |  | 000109592241 | TIER 2 | 15256-1104, PENRYN |  | W0716 | 38.7925 | -121.1548 | 2AF
31088475 | 2AF | 3673 | 0.69564 | 0.69564 | CLSD |  |  | 000106943693 | TIER 2 | 04229-1101, OLEMA |  | QQ22 | 38.09 | -122.9268 | 2AF
31252335 | 2AF | 499 | 0.094508 | 0.094508 | CLSD |  |  | 000113154425 | TIER 2 | 15270-1108, BELL |  | T0803 | 38.9529 | -121.091 | 2AF
31254690 | 2AF | 300 | 0.056818 | 0.056818 | CLSD | North Coast | Napa | 113200975 | TIER 3 | 04271-1101, CALISTOGA | CALISTOGA | FF30 | 38.6071 | -122.6309 | 2AF
31297994 | 2AF | 895 | 0.16951 | 0.16951 | CLSD |  |  | 000111896609 | TIER 2 | 19240-1101, HOOPA |  | D23 | 41.3247 | -123.5142 | 2AF
31366453 | 2AF | 205 | 0.038826 | 0.038826 | CLSD |  |  | 000113826416 | TIER 2 | 19222-1102, GARBERVILLE |  | CC08 | 40.2264 | -124.1108 | 2AF
35018539 | 2AF | 252 | 0.047727 | 0.047727 | DOCC |  |  | 114255456 | TIER 2 | 04277-1114, UKIAH |  | T1709 | 39.1396 | -123.1476 | 2AF
35083751 | 2AF | 600 | 0.11364 | 0.11364 | DOCC | South Coast Valley | Bakersfield | 111480028 | TIER 2 | 25364-2101, POSO MOUNTAIN | BAKERSFIELD | 0000026285 | 35.6211 | -118.9583 | 2AF
31406815 | 2AF | 381 | 0.072159 | 0.072159 | DOCC | North Coast | Santa Rosa | 114979513 | TIER 3 | 04281-1111, MONTE RIO | CAZADERO | HH17 | 38.5104 | -123.14 | 2AF
31159701 | 2AF | 710 | 0.13447 | 0.13447 | FICL | South Coast Valley | Templeton | 109579626 | TIER 2 |  | PASO ROBLES | EE27 | 35.6253 | 120.6945 | 2AF
31326034 | 2AF | 134 | 0.025379 | 0.025379 | FICL |  |  | 112673705 | TIER 3 | 01409-1109, CASTRO VALLEY |  | J1101 | 37.6665 | -122.0274 | 2AF
31364361 | 2AF | 394 | 0.074621 | 0.074621 | FICL |  |  | 114736877 | TIER 2 | 15203-1103, GRASS VALLEY |  | N0819 | 39.1929 | -121.0788 | 2AF
35010118 | 2AF | 150 | 0.028409 | 0.028409 | FICL |  |  | 000107195639 | TIER 2 | 16376-1703, RACETRACK |  | U3303 | 37.9942 | -120.3876 | 2AF
35010356 | 2AF | 337 | 0.063826 | 0.063826 | FICL |  |  | 000114373036 | TIER 2 | 08369-2104, ROB ROY |  | P1906 | 36.9517 | -121.817 | 2AF
35011295 | 2AF | 1583 | 0.29981 | 0.29981 | FICL |  |  | 000114344419 | TIER 3 | 15226-1105, DIAMOND SPRINGS |  | I4017 | 38.7043 | -120.8626 | 2AF
35012324 | 2AF | 263 | 0.049811 | 0.049811 | FICL |  |  | 000110852522 | TIER 2 | 10352-1103, OREGON TRAIL |  | N3311 | 40.6316 | -122.2544 | 2AF
35012964 | 2AF | 1234 | 0.23371 | 0.23371 | FICL |  |  | 000114336757 | TIER 2 | 04319-1102, REDBUD |  | W29 | 39.008 | -122.6691 | 2AF
35014742 | 2AF | 803 | 0.15208 | 0.15208 | FICL |  |  | 000114580761 | TIER 2 |  |  | P06 | 39.1278 | -121.1697 | 2AF
35014889 | 2AF | 552 | 0.10455 | 0.10455 | FICL |  |  | 000114699362 | TIER 3 | 15247-1101, COLUMBIA HILL |  | J0816 | 39.3711 | -121.1025 | 2AF
35016357 | 2AF | 647 | 0.12254 | 0.12254 | FICL |  |  | 000111587138 | TIER 2 | 19217-1103, WILLOW CREEK |  | N2323 | 40.8705 | -123.5211 | 2AF
35016855 | 2AF | 214 | 0.04053 | 0.04053 | FICL |  |  | 112837105 | TIER 2 | 04338-1101, POINT ARENA |  | X04 | 38.9098 | -123.6856 | 2AF
35022707 | 2AF | 395 | 0.074811 | 0.074811 | FICL |  |  | 000113113068 | TIER 3 | 18294-1101, OTTER |  | M02 | 36.4215 | -121.9117 | 2AF
35025977 | 2AF | 712 | 0.13485 | 0.13485 | FICL |  |  | 000114133301 | TIER 3 | 04307-1101, DUNBAR |  | JJ3317 | 38.3949 | -122.5135 | 2AF
35026735 | 2AF | 420 | 0.079545 | 0.079545 | FICL |  |  | 000114257448 | TIER 3 | 08284-1102, BIG BASIN |  | K1001 | 37.1717 | -122.1761 | 2AF
35030877 | 2AF | 796 | 0.15076 | 0.15076 | FICL |  |  | 000113819801 | TIER 2 | 04285-1121, FORT ROSS |  | FF1203 | 38.6005 | -123.3488 | 2AF
35038141 | 2AF | 323 | 0.061174 | 0.061174 | FICL | Sacramento Valley | Redding | 109659442 | TIER 3 | 10254-1102, VOLTA | SHINGLETOWN | Q4212 | 40.4947 | 121.8665 | 2AF
35051827 | 2AF | 634 | 0.12008 | 0.12008 | FICL | Tri-Valley | Oakhurst | 114778924 | TIER 2 | 25442-1101, OAKHURST | AHWAHNEE | 06205D | 37.3614 | -119.7348 | 2AF
30962842 | 2AF | 7000 | 1.3258 | 1.3258 | MAPP | Sacramento Valley | Oroville | 106249553 | TIER 2 | 10322-1101, KANAKA | FEATHER FALLS | E31 | 39.3567 | -121.1428 | 2AF
31153500 | 2AF | 1365 | 0.25852 | 0.25852 | MAPP | Tri-Valley | Hayward | 111308209 | TIER 2 | 01409-1101, CASTRO VALLEY | HAYWARD | J1014 | 37.6479 | -122.0439 | 2AF
31298793 | 2AF | 285 | 0.053977 | 0.053977 | MAPP |  |  | 000112192561 | TIER 2 |  |  | S0811 | 38.9816 | -121.1133 | 2AF
35010358 | 2AF | 516 | 0.097727 | 0.097727 | MAPP |  |  | 000112172015 | TIER 3 | 08362-2105, CAMP EVERS |  | L1406 | 37.1219 | -122.1673 | 2AF
35018047 | 2AF | 839 | 0.1589 | 0.1589 | MAPP |  |  | 000113113542 | TIER 2 | 18256-2102, CHOLAME |  | Y41 | 35.9272 | -120.3825 | 2AF
35023234 | 2AF | 380 | 0.07197 | 0.07197 | MAPP | Sacramento Valley | Redding | 107854679 | TIER 2 | 10254-1102, VOLTA | SHINGLETOWN | Q44 | 40.5129 | -121.772 | 2AF
35023526 | 2AF | 410 | 0.077652 | 0.077652 | MAPP | North Coast | Lakeport | 113791547 | TIER 2 | 04214-1101, CLEAR LAKE | KELSEYVILLE | X24 | 38.9498 | -122.879 | 2AF
35026994 | 2AF | 390 | 0.073864 | 0.073864 | MAPP |  |  | 000114034547 | TIER 2 | 04331-1102, KONOCTI |  | X25 | 38.9517 | -122.8384 | 2AF
35037647 | 2AF | 527 | 0.099811 | 0.099811 | MAPP |  |  | 000117768322 | TIER 2 | 04308-1101, BIG RIVER |  | P02 | 39.3106 | -123.7828 | 2AF
35038190 | 2AF | 515 | 0.097538 | 0.097538 | MAPP | South Coast Valley | Salinas | 107962023 | TIER 2 |  | CHUALAR | I1517 | 36.603 | -121.429 | 2AF
35038502 | 2AF | 866 | 0.16402 | 0.16402 | MAPP | South Coast Valley | Templeton | 109234809 | TIER 2 |  | PARKFIELD | Z41 | 35.8493 | -120.3944 | 2AF
35042670 | 2AF | 467 | 0.088447 | 0.088447 | MAPP | Sacramento Valley | Placerville | 114601621 | TIER 2 | 15226-1106, DIAMOND SPRINGS | PLACERVILLE | I42 | 38.7026 | -120.7902 | 2AF
35054959 | 2AF | 406 | 0.076894 | 0.076894 | MAPP | Sacramento Valley | Placerville | 114804992 | TIER 3 | 15366-2102, APPLE HILL | FIDDLETOWN | M44 | 38.5424 | -120.693 | 2AF
35058267 | 2AF | 610 | 0.11553 | 0.11553 | MAPP | Tri-Valley | Jackson | 114944231 | TIER 3 | 16375-1102, PINE GROVE | PIONEER | K2724 | 38.4252 | -120.611 | 2AF
35066689 | 2AF | 103 | 0.019508 | 0.019508 | MAPP | Tri-Valley | Jackson | 114630849 | TIER 2 | 16216-1101, ELECTRA | JACKSON | M2410 | 38.3643 | -120.7245 | 2AF
35087462 | 2AF | 1538 | 0.29129 | 0.29129 | MAPP | Sacramento Valley | Auburn | 116590864 | TIER 2 | 15281-1105, WHEATLAND | LINCOLN | R03 | 39.0454 | -121.3034 | 2AF
35094321 | 2AF | 545 | 0.10322 | 0.10322 | MAPP | Peninsula South Bay | Edenvale | 116983310 | TIER 3 | 08324-2111, MORGAN HILL | MORGAN HILL | M20 | 37.0834 | -121.7524 | 2AF
35098264 | 2AF | 545 | 0.10322 | 0.10322 | MAPP | Tri-Valley | Angels Camp | 117157644 | TIER 3 | 16320-1102, WEST POINT | MOUNTAIN RANCH | N3022 | 38.2645 | -120.5095 | 2AF
31102666 | 2AF | 1245 | 0.2358 | 0.2358 | CONS | North Coast | Napa | 110096637 | TIER 2 | 04246-1106, BASALT | NAPA | MM36 | 38.2523 | -122.3786 | 2AF
35087207 | 2AF | 1065 | 0.2017 | 0.2017 | CONS | Bay Area | Concord | 117011694 | TIER 2 | 01202-2213, CLAYTON | CLAYTON | D14 | 37.9397 | -121.911 | 2AF
35100238 | 2AF | 665 | 0.12595 | 0.12595 | CONS | South Coast Valley | Templeton | 116153631 | TIER 3 | 18305-2110, TEMPLETON | TEMPLETON,CA | HH30 | 35.5212 | -120.7973 | 2AF
31257161 | 2AF | 490 | 0.092803 | 0.092803 | CONS | Tri-Valley | Stockton | 108565478 | TIER 2 |  | VALLEY SPRINGS | Q2021 | 38.1373 | -120.9225 | 2AF
35055289 | 2AF | 314 | 0.05947 | 0.05947 | CONS | Tri-Valley | Livermore | 114881462 | TIER 2 | 01440-2108, LAS POSITAS | LIVERMORE | K180 | 37.6057 | -121.7497 | 2AF
35037345 | 2AF | 250 | 0.047348 | 0.047348 | CONS | South Coast Valley | Buellton | 108883947 | TIER 2 | 18304-1101, BUELLTON | LOS OSOS | BB42 | 34.6385 | -120.2903 | 2AF
31254945 | 2AF | 270 | 0.051136 | 0.051136 | UNSC | North Coast | Petaluma | 113773964 | TIER 2 | 04263-1108, PETALUMA C | PETALUMA | N29 | 38.2097 | -122.6755 | 2AF
31254545 | 2AF | 857 | 0.16231 | 0.16231 | UNSC |  |  | 113192220 | TIER 2 | 10338-1102, FRENCH GULCH |  | N24 | 40.651 | -122.613 | 2AF
31254945 | 2AF | 270 | 0.051136 | 0.051136 | UNSC |  |  | 109973400 | TIER 2 | 04263-1108, PETALUMA C |  | N29 | 38.2092 | -122.6767 | 2AF
35009046 | 2AF | 891 | 0.16875 | 0.16875 | UNSC | North Coast | Napa | 107399395 | TIER 2 | 04343-2104, SILVERADO | SAINT HELENA | FF36 | 38.5783 | -122.3939 | 2AF
35038059 | 2AF | 115 | 0.02178 | 0.02178 | UNSC | Sacramento Valley | Oroville | 109198066 | TIER 3 | 10320-1101, CHALLENGE | CLIPPER MILLS | G33 | 39.5224 | -121.1819 | 2AF
35038312 | 2AF | 320 | 0.060606 | 0.060606 | UNSC | South Coast Valley | Santa Maria | 108879245 | TIER 2 | 18281-1102, SISQUOC | SISQUOC | XX44 | 34.8318 | -120.2326 | 2AF
35065058 | 2AF | 530 | 0.10038 | 0.10038 | UNSC | Sacramento Valley | Placerville | 111815691 | TIER 2 | 15226-1104, DIAMOND SPRINGS | EL DORADO | K41 | 38.6055 | -120.8122 | 2AF
35078728 | 2AF | 193 | 0.036553 | 0.036553 | UNSC | Sacramento Valley | Redding | 114944335 | TIER 2 | 10338-1101, FRENCH GULCH | FRENCH GULCH | J24 | 40.7906 | -122.6151 | 2AF
35078734 | 2AF | 337 | 0.063826 | 0.063826 | UNSC | Sacramento Valley | Redding | 114972983 | TIER 2 | 10338-1101, FRENCH GULCH | FRENCH GULCH | K24 | 40.7634 | -122.6102 | 2AF
35062127 | 2AF | 6011 | 1.1384 | 1.1384 | CONS | Sacramento Valley | Auburn | 114988505 | TIER 2 | 15228-2101, MOUNTAIN QUARRIES | PILOT HILL | V11 | 38.8359 | -120.98 | 2AF
35094082 | 2AF | 566 | 0.1072 | 0.1072 | CONS | Sacramento Valley | Chico | 116792166 | TIER 3 |  | PARADISE | T3310 | 39.7491 | -121.6026 | 2AF
35078144 | 2AF | 450 | 0.085227 | 0.085227 | CONS | South Coast Valley | Fresno | 114634235 | TIER 2 | 25415-1101, AUBERRY | Auberry | 0000010243 | 37.0566 | -119.3751 | 2AF
35022860 | 2AF | 368 | 0.069697 | 0.069697 | UNSC | Sacramento Valley | Placerville | 111772518 | TIER 3 | 15365-2105, SHINGLE SPRINGS | SHINGLE SPRINGS | J3811 | 38.6675 | -120.9541 | 2AF
35022861 | 2AF | 2168 | 0.41061 | 0.41061 | UNSC | Sacramento Valley | Placerville | 113747410 | TIER 2 | 15226-1104, DIAMOND SPRINGS | DIAMOND SPRINGS | J41 | 38.6523 | -120.8268 | 2AF
35038608 | 2AF | 1140 | 0.21591 | 0.21591 | UNSC | Sacramento Valley | Vacaville | 108878647 | TIER 2 | 06368-1102, PUTAH CREEK | VACAVILLE | O10 | 38.4603 | -122.0547 | 2AF
35011253 | 2AF | 800 | 0.15152 | 0.15152 | UNSC | Tri-Valley | Angels Camp | 111699237 | TIER 2 |  | SAN ANDREAS | Q26 | 38.1415 | -120.6643 | 2AF
35011254 | 2AF | 350 | 0.066288 | 0.066288 | UNSC | Tri-Valley | Angels Camp | 111712580 | TIER 2 | 16221-1101, CALAVERAS CEMENT | SAN ANDREAS | Q26 | 38.1675 | -120.6727 | 2AF
31159702 | 2AF | 380 | 0.07197 | 0.07197 | CLSD | South Coast Valley | Templeton | 109579629 | TIER 2 |  | PASO ROBLES | EE27 | 35.659 | -120.9226 | 2AF
35038571 | 2AF | 273 | 0.051705 | 0.051705 | FICL | North Coast | Ukiah | 109675711 | TIER 2 | 04228-1105, POTTER VALLEY P H | POTTER VALLEY | O17 | 39.2075 | -123.0845 | 2AF
|  |  | 10.7888 | 10.7888

## Q4IdleFacilities
Order | Notification | MAT | Primary Status | Bucket | Footage | Mileage | Construction Scheduled | Completed On | Location | HFTD | Functional Loc | Functional Loc Desc | Plat Map | Circuit | Latitude | Longitude | City | Comments
35038685 | 109197838 | 2AF | FICL | Post Construction | 624 | 0.11818 | complete | 2019-10-21 | NV | TIER 2 | ED.14-W090000000.STRU.POLE | GLENN W09 POLES | W09 | 10278-1101, ELK CREEK | 39.587 | -122.5887 | ELK CREEK | construction compete 10/21/19
35037594 | 109608767 | 2AF | MAPP | Post Construction | 497 | 0.094129 | complete | 2019-11-14 | HB | TIER 2 | ED.35-W120100000.STRU.POLE | FORTUNA W1201 POLES | W1201 | 19229-1121, CARLOTTA | 40.3012 | 123.5944 | CARLOTTA | construction complete 11/14/19
35011247 | 111690043 | 2AF | CONS | Construction | 1090 | 0.20644 | complete |  | ST | TIER 2 | ED.95-Q270000000.STRU.POLE | MOTHER LODE Q27 POLES | Q27 | 16221-1101, CALAVERAS CEMENT | 38.1713 | -120.6326 | SAN ANDREAS | Construction Complete. Verified with Inspector [REDACTED].
35111038 | 117146046 | 2AF | CONS | Construction | 4875 | 0.9233 | job owner checking completion status |  | LP | TIER 3 | ED.03-HH30000000.STRU.POLE | PASO ROBLES HH30 POLES | HH30 | 18254-1101, ATASCADERO | 35.4927 | -120.7772 | ATASCADERO | Appears to have been completed 11/13/19; no long text referancing completion. E-mail to Job Owner on 11/27/19 12/5: Job owner checking with [REDACTED] ([REDACTED])
|  |  |  | TOTAL |  | 1.342