## Q3-Q4 Restoration AI
PG&E Tower Assessment | [8 empty] | PRIVILEGED AND CONFIDENTIAL DRAFT FOR DISCUSSION
Action Items Tracker Template | [8 empty] | 2021-04-14 16:15
Actions from Restoration Q3-Q4 Workshop
# | Functional Group | Date Identified | Identified by | Objective | Item | Owner (s) | Due date / RAG Status | Status | Comments
1 | PMO | 2016-08-22 | Workshop | Tower Restoration | Name for "Pilot" |  | 2016-08-24 | Closed | Initial restoration, Phase 1; 2016 Restoration
2 | Operations | 2016-08-22 | Workshop | Tower Restoration | Determine additional customers need to reach 50/50 LBP/non-LBP |  | 2016-08-22 | Closed | Would this change our engagement strategy?
3 | Operations | 2016-08-22 | Workshop | Tower Restoration | List of Towers |  | 2016-08-24 | Closed
4 | Operations | 2016-08-22 | Workshop | Tower Restoration | Identify site walk participants |  | 2016-08-26 | Closed
5 | Operations | 2016-08-22 | Workshop | Tower Restoration | Hot procedure work pkg |  | 2016-09-27 | Closed | PGE approval needed by 9/27
6 | Operations | 2016-08-22 | Workshop | Tower Restoration | Clearance |  | 2016-09-01 | Closed | Waiting to hear back from [REDACTED]
7 | Operations | 2016-08-22 | Workshop | Tower Restoration | Detailed schedule |  | 2016-08-31 | Closed | Send with dependency dates
8 | Operations | 2016-08-22 | Workshop | Tower Restoration | Veg. review |  | 2016-08-31 | Closed
9 | Operations | 2016-08-22 | Workshop | Tower Restoration | Laydown yards and LZ |  | 2016-09-09 | Closed | Handoff to redacted; ensure that redacted has a chance to review in advance of mobilization
10 | Operations | 2016-08-22 | Workshop | Tower Restoration | Engineering approval soils |  | 2016-09-09 | Closed | Threshold
53 | PMO | 2016-09-26 | Workshop | Tower Restoration | Review non-responsive customer towers with Joe |  | 2016-09-28 | Closed | redacted to provide names
12 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer research |  | 2016-08-24 | Closed
13 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer letter, confirmation e-mail |  | 2016-08-29 | Closed | Letter, email approved. Talking points to be updated
14 | Customer | 2016-08-22 | Workshop | Tower Restoration | Gen Ref update - rapid response |  | 2016-09-02 | Closed
15 | Customer | 2016-08-22 | Workshop | Tower Restoration | 200, 500-ft radius list |  | 2016-11-01 | Closed | Revisit with potential customer sites south of Oroville
16 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer health related talking points |  | 2016-10-31 | Open | Draft send to redacted for initial review
17 | Land | 2016-08-22 | Workshop | Tower Restoration | Confirm P1 status |  | 2016-08-24 | Closed
45 | Land | 2016-09-09 | Working Team | Tower Restoration | FAI veg, confirm they are using same access protocol |  | 2016-10-07 | Closed | Create CAP, request messaging, if available
19 | Land | 2016-08-22 | Workshop | Tower Restoration | Determination Of Rights |  | 2016-09-02 | Closed | Stored on land site
20 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Determine allowed work hours in Butte County |  | 2016-08-23 | Closed | 7am - 6
21 | Environmental | 2016-08-22 | Workshop | Tower Restoration | AEA check |  | 2016-08-26 | Closed
22 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Soil sampling validation/assessment |  | 2016-08-31 | Closed
23 | Environmental | 2016-08-22 | Workshop | Tower Restoration | Confirm NEA update needed |  | 2016-08-31 | Closed
24 | Environmental | 2016-08-22 | Workshop | Tower Restoration | AUS/PSC oversight (waste management contract) |  | 2016-09-12 | Closed
25 | Public Affairs | 2016-08-22 | Workshop | Tower Restoration | Identify key stakeholders (ex. Butte) |  | 2016-08-26 | Closed | City manager, electeds, police, fire, county health
26 | Corporate comms | 2016-08-22 | Workshop | Tower Restoration | Draft content and conversations with digital strategies regarding website development |  | 2016-08-25 | Closed
27 | Corporate comms | 2016-08-22 | Workshop | Tower Restoration | Develop envelope messaging for letter |  | 2016-09-30 | Closed
28 | Corporate comms | 2016-08-24 | Working Team | Tower Restoration | Printing of letter, envelope, return label, mailing etc. |  | 2016-09-06 | Closed
29 | Land | 2016-08-26 | Working Team | Tower Restoration | Develop talking points regarding customer soil removal refusal |  | 2016-09-02 | Closed
30 | PMO | 2016-08-31 | Working Team | Tower Restoration | Soil removal depth standards per guidelines |  | 2016-08-31 | Closed | Status on Tuesday morning
31 | Environmental | 2016-08-31 | Working Team | Tower Restoration | Identify towers for use in soil sampling |  | 2016-09-07 | Closed
32 | LCE | 2016-09-02 | Working Team | Tower Restoration | Updates to customer phone script |  | 2016-09-07 | Closed
33 | Corporate comms | 2016-09-02 | Working Team | Tower Restoration | Gen Ref update - NV Letter |  | 2016-09-07 | Closed
34 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Final scope of work |  | 2016-09-09 | Closed
35 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Approved work plan |  | 2016-09-09 | Closed
36 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Price Sheet |  | 2016-09-09 | Closed
37 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract RFP - Land & Environmental RTC, access info, permits (if any), etc. |  | 2016-09-20 | Closed
38 | Operations | 2016-09-06 | Working Team | Tower Restoration | PAR Contract - Lead disposal provisions |  | 2016-09-09 | Closed | PSC is handling for 2016. 2017 under evaluation
39 | Operations | 2016-09-06 | Workshop | Tower Restoration | Confirm contractor qualification list |  | 2016-09-12 | Closed
40 | Operations | 2016-09-06 | Workshop | Tower Restoration | Determine if walk downs are needed |  | 2016-09-09 | Closed
41 | Operations | 2016-09-06 | Workshop | Tower Restoration | Full detailed schedule |  | 2016-09-09 | Closed | Project milestone report; redacted calendar placemat
42 | Operations | 2016-09-09 | Working Team | Tower Restoration | Determine schedule and processes for T-30/32 restoration |  | 2016-09-14 | Closed | MOVE
44 | Land | 2016-09-09 | Working Team | Tower Restoration | Update procedure, letter, door hangers for accessing property with a lock |  | 2016-10-21 | Open | KA to revise and re-circulate to team based on workshop discussion.
18 | Land | 2016-08-22 | Workshop | Tower Restoration | Workshop item: Review customer acknowledgement and soil restoration letters |  | 2016-10-17 | Closed | Under team review; acknowledgement letter, soil agreement, refusal agreement; Potential Workshop topic
43 | PMO | 2016-09-09 | Working Team | Governance | Identify PMO approval process |  | 2016-11-30 | Open | Exponent
51 | Operations | 2016-09-26 | Workshop | Tower Restoration | Update restoration schedule to highlight schedule changes, customer notification |  | 2016-09-26 | Closed | Sent 9/27
47 | Customer | 2016-09-09 | Working Team | Tower Restoration | Customer contact log / tracker |  | 2016-09-12 | Closed
48 | Land | 2016-09-09 | Working Team | Tower Restoration | Develop talking points regarding potential encroachments |  | 2016-09-23 | Closed | Review guidelines coming out of meeting with legal
49 | PMO | 2016-09-12 | Working Team | Tower Restoration | Confirm final dates needed for South Oroville lines to determine whether 2016 restoration is appropriate |  | 2016-09-16 | Closed
50 | PMO | 2016-09-12 | Working Team | Tower Restoration | Add agenda item for reviewing South Orville tower restoration feasibility |  | 2016-10-15 | Closed
51 | Operations | 2016-09-12 | Working Team | Tower Restoration | Prepare Q3 / Q4 tower restoration calendar placemat |  | 2016-09-16 | Closed
52 | PMO | 2016-09-26 | Workshop | Tower Restoration | Develop procedure for feedback loop regarding customer notification of schedule changes |  | 2016-11-30 | Closed | weekly update (redacted) and customer review (V. Bryan)
11 | Customer | 2016-08-22 | Workshop | Tower Restoration | Customer tool kit |  | TBD | Open

## Action Items
Community Wildfire Safety Program | [6 empty] | CONFIDENTIAL
Leadership Team Meeting Action Items Tracker | [6 empty] | 2021-04-14 16:15
Action Items
WORKSTREAM | DATE IDENTIFIED | DESCRIPTION | OWNER(S) | RESOURCE | DUE DATE/ RAG STATUS | STATUS | COMMENTS/NOTES
2021 Planning Questions | 2021-12-08 | Coordinate with Meteorology/[REDACTED] on PSPS decision making updates related to redacted order. |  |  | 2021-03-31 | Open | Discussing summary with the CPUC on 3/16. 3/30 Update: Coordination ongoing
Internal | 2021-02-09 | Coordinate regarding 2021 meeting structure/approach |  |  | 2021-02-16 | Closed | Meeting held on 2/19 to discuss; will include in discussions for 2/23 meeting
Customer | 2021-01-12 | Schedule working group to build out in-event communications strategy for communities de-scoped but not cancelled |  |  | 2021-02-19 | Closed | Now moving forward with a "hard cancel" approach for descoped customers within 2 hours of the decision. Testing messaging this week regarding messaging for descoped customers. Phase III decision includes 2 hour requirement "to the extent possible."
Vegetation Management | 2021-02-09 | Coordinate regarding redacted P1/P2 veg proposal and potential impacts to PSPS |  | Law | 2021-02-19 | Closed | Ongoing discussions regarding PSPS scope impacts. 3/30 Update: Close action item, ongoing coordination.
EVM | 2021-03-31 | [REDACTED] II/EVM team to include redacted and redacted on 4/1 customer refusal call |  |  | 2021-04-01 | Closed
External Engagement | 2021-02-02 | Coordinate regarding external messaging related to 2021 risk model for inclusion in external engagements i.e. Regional Working Groups, Wildfire Safety Working Sessions, etc. |  |  | 2021-03-05 | Closed | Messaging has been reviewed/approved, may revisit based on feedback received after it is used externally.
Wood Management | 2021-03-09 | Develop statement/talking points on wood management proposal |  |  | 2021-03-23 | Closed | Talking points being updated to reflect ongoing discussions with counties, MarComm team has a statement prepared to be used if necessary.
Full Scale Exercises | 2021-04-07 | [REDACTED] to coordinate with team to ensure full scale exercise one invitations are shared with the Federal Monitor and Filsinger. |  |  | 2021-04-09 | Open
Exercises | 2021-02-23 | Work to communicate as a part of the Phase 3 scoping process a potential to revise timeline requirement for exercises to 8/1 instead of 7/1 to align with current plans/approach |  | Law | 2021-03-31 | Closed | [REDACTED] /[REDACTED] to discuss potential path forward, if needed. 3/30 Update: Confirmed compliance with [REDACTED]
Customer Outreach and Preparedness | 2021-02-09 | Coordinate regarding list of “most likely” impacted customers (HFRA); targeting communication in March |  |  | 2021-04-12 | Closed | Data provided week of 3/29
Long Term Temp Gen Planning/Vision 2030 | 2021-04-07 | [REDACTED] to include[REDACTED] , [REDACTED] and [REDACTED] on the 4/9 temp gen long-term planning meeting. |  |  | 2021-04-09 | Closed
Vegetation Management | 2021-02-18 | Coordinate with EVM team regarding strategy for previously marked veg work that is no longer in scope. |  |  | 2021-04-12 | Open | Veg team working on reassessment plan, timeline TBD.
System Inspections | 2021-04-07 | [REDACTED] to coordinate with [REDACTED] regarding system inspections RAG status. |  |  | 2021-04-13 | Open
Data Quality | 2021-04-07 | [REDACTED] to coordinate with [REDACTED] for future meeting updates regarding data quality. |  |  | 2021-04-13 | Open
CCA/Temp Gen | 2021-04-07 | [REDACTED] to have [REDACTED] follow up with [REDACTED] regarding CCA/temporary power coordination |  |  | 2021-04-13 | Closed
EVM | 2021-03-31 | [REDACTED] to provide data outlining where fuel reduction projects are planned. |  |  | 2021-04-15 | Open
EVM | 2021-03-31 | [REDACTED] to coordinate with EVM team regarding communications approach for 2021. |  |  | 2021-04-15 | Open
REFCL | 2021-04-07 | [REDACTED] to schedule meeting regarding REFCL with [REDACTED] and [REDACTED] |  |  | 2021-04-16 | Closed
Sectionalizing | 2021-04-13 | [REDACTED] to follow up with [REDACTED] regarding if estimating is holding up distribution sectionalizing workflow |  |  | 2021-04-16 | Open
Substation Temp Gen | 2021-04-13 | [REDACTED] /[REDACTED] to discuss potential updates to Substation Temporary Generation talking points based on recent feedback |  |  | 2021-04-23 | Open
[REDACTED] / Frequency | 2021-04-13 | [REDACTED] /[REDACTED] to look into if 2020 redacted/Frequency data can be pulled by County and follow up with redacted |  |  | 2021-04-23 | Closed
Regional Working Groups | 2021-03-02 | Review Regional Working Group (RWG) regions based on new regionalization boundaries included in filing and coordinate with [REDACTED] to potentially update for Q2 RWG meetings. |  |  | 2021-05-01 | Open | 3/30 Update: Continue coordination based on ongoing changes as needed.
REFCL | 2021-04-07 | [REDACTED] to confirm if there were outages related to the REFCL issue in Calistoga and synch-up with redacted on any potential engagement needs. |  |  | 2021-05-01 | Open
EP&R | 2021-01-12 | Schedule meeting to identify gaps and next steps regarding procedures and messaging related to capacity outages. |  |  | 2021-06-01 | Open | 4/6 Update: Internal coordination meeting occurring on 4/7, additional stakeholders (to include [REDACTED] and [REDACTED] ) will be pulled in for coordination after this meeting.

## Sheet1
Identified By:
Working Team
OSC

## Sheet3
Category
Action
Decision
Completed
Incomplete
In-Progress