## Top 20
Order | Job Owner Name | Program | Workplan Status | Order Description | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Removal | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | 2023 Forecast Feet | 2023 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Ready to Break Ground | Pre-Eng. Mtg Date | Pre-Eng. Complete | SAP Est Out Date | Previous EOD Forecast | CMCS Approved | Walkdown Date | Walkdown Complete | 30% Drawing Complete (Walkdown) | 60% Drawing Complete (Land Rev Reqd) | 80% Drawing Complete (Dependency Set) | PEND IN Date | --1 | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Base Map Status | Expected Base Map Complete | Base Map Vendor | Surveyor | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | --2 | Expected Permit Date | Permits Complete | --3 | Veg Complete | Veg Completed | Veg Start | Veg Started | --4 | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | 2021 Feet Installed | 2021 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | OH QA Span | UG QA Span | Removal QA Span | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | --5 | Auth Amt without Contingency (Expected Case) | Total EAC | --6 | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Circuit Protection Zone | Functional Location | Risk Rank | Segmentation ID# | Project Type | Grid Design Priority | LTIP Condition 1 | LTIP Condition 2 | Last Edited By | Last Edited Date
35217268 |  | SH | Keep | CWSP - BUCKS CREEK 1101 CB PH 1 | Scoped | PEND |  | 0 | 1056 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 0.2 | 0 | 453 | 0.085795 | NV | 08W | 2021-08-23 13:10 | 2021-02-22 | Y | 2021-06-30 | 2021-06-30 | Yes |  | Yes | Yes | N/A | Yes | 2021-06-17 | [6 empty] | 2021-07-22 | 2021-04-22 | N/A |  | NA |  |  | 2021-07-22 | 2021-07-22 |  |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-06 17:00 |  | N/A | 2022-03-01 08:00 |  | 150000 | 581285 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Belden | Plumas | 0 | 0 | [10 empty] | ED.10221.1101 | 11 | 35217268 | CWSP |  | Meet | No |  | 2021-06-22 10:20
35217272 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.1 | Scoped | ESTS |  | 1584 | 0 | 0 | 1584 | 0.3 | 0 | 0 | 0 | 0 | 1584 | 0.3 | 0 | 0 | 0 |  |  | NV | 08W | 2022-04-07 17:00 | 2021-03-15 | Y | 2021-06-30 | 2021-06-30 | No | 2021-06-30 | No | No | [11 empty] | Completed | 2021-05-01 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-04-07 17:00 | No | N/A | 2022-05-02 08:00 |  | 150000 | 1055883.9 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | Meet |  | 2021-06-18 13:24
35219260 |  | SH | Keep | CWSP - WYANDOTTE 110932586 PH 1.1 | Scoped | PEND |  | 0 | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 0 | 6951 | 1.3165 | NV | 08W | 2021-07-05 | 2021-03-15 | Y | 2021-04-30 | 2021-04-30 | Yes |  | Yes | Yes |  | Yes | 2021-06-23 |  |  | Yes |  |  |  | 2021-05-27 | 2021-05-27 | Completed | 2021-04-16 |  |  | Full | 2021-05-27 | 2021-05-27 | Full |  |  | Yes |  | 2021-07-19 |  | 2021-07-05 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-06-30 17:00 | No | INPR | 2021-07-20 08:00 |  | 300000 | 723642.7 | [10 empty] | July Site Visit Potential | Feather Falls | Butte | 39.4631 | -121.5149 | [10 empty] | ED.10291.1109.RECL | 29 | 35219260 | CWSP |  | Meet | No |  | 2021-06-17 11:31
35224712 |  | SH | Keep | CWSP - BUCKS CREEK 1101 CB PH 2 | Scoped | ESTS |  | 9134.4 | 0 | 0 | 9134.4 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0 | 9134 | 1.7299 | 7.5758e-05 |  |  | NV | 08W | 2022-04-06 17:00 | 2021-02-22 | Y | 2021-07-31 |  | No |  | No | [12 empty] | Completed | 2021-05-07 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.73 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-04-06 17:00 |  | N/A | 2022-04-29 08:00 |  | 400000 | 15723451.9 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Belden | Plumas | 0 | 0 | [10 empty] | ED.10221.1101 | 11 | 35217268 | CWSP |  | Meet | Meet |  | 2021-06-21 20:38
35224713 |  | SH | Keep | CWSP - BUCKS CREEK 1101 CB PH 3 | Scoped | ESTS |  | 9662.4 | 0 | 0 | 9662.4 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 9662 | 1.8299 | 7.5758e-05 |  |  | NV | 08W | 2022-07-14 17:00 | 2021-02-22 | Y | 2021-07-31 |  | No |  | No | [12 empty] | Completed | 2021-05-07 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.83 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-07-14 17:00 |  | N/A | 2022-08-08 08:00 |  | 400000 | 6374571.1 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Belden | Plumas | 0 | 0 | [10 empty] | ED.10221.1101 | 11 | 35217268 | CWSP |  | Meet | Meet |  | 2021-06-21 20:38
35226627 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.2 | Scoped | PEND |  | 0 | 1677 | 0 | 1677 | 0.31761 | 0 | 0 | 1677 | 0.31761 | 0 | 0 | 0 | 0 | 0 | 1677 | 0.31761 | NV | 08W | 2021-08-23 13:10 | 2021-03-15 | Y | 2021-04-30 | 2021-04-30 | Yes |  |  | Yes |  | Yes | 2021-04-28 |  | 2021-05-06 | Yes |  |  |  | 2021-06-14 | 2021-06-14 |  |  |  |  | Full | 2021-07-07 | 2021-09-14 |  |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.31761 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-06-24 17:00 | No | INPR | 2021-07-26 08:00 |  | 150000 | 848066.8 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | No |  | 2021-06-22 10:08
35226628 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.3 | Scoped | ESTS |  | 4329.6 | 0 | 0 | 4329.6 | 0.82 | 0 | 0 | 0 | 0 | 4330 | 0.82008 | 0 | 0 | -7.5758e-05 |  |  | NV | 08W | 2021-09-01 17:00 | 2021-03-15 | Y | 2021-06-30 | 2021-06-30 | No | 2021-06-30 | No | No | [11 empty] | Completed | 2021-05-01 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.82 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-01 17:00 |  | N/A | 2021-10-14 08:00 |  | 150000 | 2860070.7 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | Meet |  | 2021-06-18 13:24
35226629 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.4 | Scoped | ESTS |  | 23760 | 0 | 0 | 23760 | 4.5 | 0 | 0 | 0 | 0 | 23760 | 4.5 | 0 | 0 | 0 |  |  | NV | 08W | 2021-09-01 17:00 | 2021-03-15 | Y | 2021-07-31 | 2021-07-31 | No | 2021-06-30 | No | No | [11 empty] | Completed | 2021-05-01 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-01 17:00 |  | N/A | 2021-10-14 08:00 |  | 200000 | 5995275.4 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | Meet |  | 2021-06-18 13:24
35226630 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.5 | Scoped | PEND |  | 0 | 7603.2 | 0 | 7603.2 | 1.44 | 0 | 0 | 7608 | 1.4409 | 0 | 0 | 0 | 0 | -0.00090909 | 7390 | 1.3996 | NV | 08W | 2021-08-23 13:10 | 2021-03-15 | Y | 2021-04-30 | 2021-04-30 | Yes |  |  | Yes |  | Yes | 2021-06-23 |  | 2021-07-16 | Yes |  |  |  | 2021-06-14 | 2021-06-14 |  |  |  |  | Full | 2021-06-14 | 2021-06-14 | Full |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.44 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-04 17:00 | No | N/A | 2021-08-10 08:00 |  | 150000 | 3103435.2 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | No |  | 2021-06-23 10:40
35226631 |  | SH | Keep | CWSP - KESWICK 1101 LR 1586 PH 1.6 | Scoped | PEND |  | 0 | 8131.2 | 0 | 8131.2 | 1.54 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 3.7879e-05 | 8132 | 1.5402 | NV | 08W | 2021-08-23 13:10 | 2021-03-15 | Y | 2021-04-30 | 2021-04-30 | Yes |  |  | Yes |  | Yes | 2021-06-23 |  | 2021-06-22 | Yes |  |  |  | 2021-06-14 | 2021-06-14 |  |  |  |  | Full | 2021-06-18 | 2021-06-18 | Full |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-15 17:00 | No | N/A | 2021-07-27 08:00 |  | 150000 | 3949070.4 | [10 empty] | July Site Visit Potential | Redding | Shasta | 40.6253 | -122.4633 | [10 empty] | ED.10345.1101.RECL | 7 | 35217272 | CWSP |  | Meet | No |  | 2021-06-23 10:40
35226700 |  | SH | Keep | CWSP - WYANDOTTE 110932586 PH 1.2 | Scoped | ESTS |  | 3010 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | 0 | 0 | 3010 | 0.57008 | 0 | 0 | 0 |  |  | NV | 08W | 2022-06-30 17:00 | 2021-03-31 | Y |  |  | No |  | No | [12 empty] | Completed | 2021-04-16 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.57008 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-06-30 17:00 |  | N/A | 2022-07-21 08:00 |  | 650000 | [11 empty] | July Site Visit Potential | [15 empty] | 29 | 35219260 | CWSP |  | Meet | Meet |  | 2021-06-21 20:33
35217269 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.1 | Scoped | UNSE |  | 0 | 2270 | 0 | 2270 | 0.42992 | 0 | 0 | 0 | 0 | 2270 | 0.42992 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-24 17:00 | 2021-04-28 | Y | [17 empty] | Completed | 2021-05-25 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.42992 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-24 17:00 |  | N/A | 2022-01-19 08:00 |  |  | 50096.5 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | No |  | 2021-06-16 09:53
35217270 |  | SH | Keep | CWSP - KONOCTI 1102 LR 965078 PH1 | Scoped | ESTS |  | 0 | 2904 | 0 | 2904 | 0.55 | 0 | 0 | 0 | 0 | 2904 | 0.55 | 0 | 0 | 0 | 2516 | 0.47652 | HB | 08W | 2021-09-07 17:00 | 2021-03-30 | Y | 2021-07-31 |  |  |  | No | [12 empty] | Completed | 2021-06-12 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.55 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-07 17:00 |  | N/A | 2021-12-10 08:00 |  | 316666 | 49709.5 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Kelseyville | Lake | 38.9301 | -122.7429 | [10 empty] | ED.04331.1102.RECL | 9 | 35217270 | CWSP |  | Meet | No |  | 2021-06-22 18:20
35217271 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.1 | Scoped | ESTS |  | 8131 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 | 0 | 8131 | 1.54 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-10 17:00 | 2021-03-30 | Y | [17 empty] | Completed | 2021-06-18 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.54 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-10 17:00 |  | N/A | 2022-01-05 08:00 |  | 200000 | 63138.3 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | Meet |  | 2021-03-31 08:55
35217273 |  | SH | Keep | SH - UPPER LAKE 1101 CB | Scoped | PEND |  | 0 | 5702.4 | 0 | 5702.4 | 1.08 | 0 | 0 | 5702.4 | 1.08 | 0 | 0 | 0 | 0 | 1.7225e-16 | 5690 | 1.0777 | HB | 08W | 2021-08-24 17:00 | 2021-05-11 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-08 | Yes | Yes | N/A | Yes | 2021-06-20 |  |  | No | [5 empty] | Completed | 2021-03-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.08 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-24 17:00 |  | N/A | 2021-11-25 08:00 |  | 500000 | 51042.9 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Upper Lake | Lake | 39.353 | -122.7722 | [10 empty] | ED.04287.1101 | 6 |  | CWSP |  | Meet | No |  | 2021-06-17 10:14
35220895 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH2.1 | Scoped | ESTS |  | 10190 | 0 | 0 | 10190 | 1.9299 | 0 | 0 | 0 | 0 | 10190 | 1.9299 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-17 17:00 | 2021-03-30 | Y | 2021-09-24 | 2021-09-24 | [15 empty] | Completed | 2021-06-10 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9299 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-17 17:00 |  | N/A | 2021-11-09 08:00 |  | 250000 | 28306.2 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | ED.04314.1103.RECL | 14 | 35220895 | CWSP |  | Meet | Meet |  | 2021-05-13 09:14
35220896 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH3.1 | Scoped | ESTS |  | 1478 | 0 | 0 | 1478 | 0.27992 | 0 | 0 | 0 | 0 | 1478 | 0.27992 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-24 17:00 | 2021-04-30 | Y | [17 empty] | Completed | 2021-06-18 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.27992 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-24 17:00 |  | N/A | 2022-01-19 08:00 |  |  | 11117.2 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7569 | -122.607 | [10 empty] | ED.04314.1103.RECL | 14 | 35220896 | CWSP |  | Meet | Meet |  | 2021-04-30 11:04
35225589 |  | SH | Keep | CWSP - KONOCTI 1102 LR 965078 PH2 | Scoped | ESTS |  | 0 | 4699.2 | 0 | 4699.2 | 0.89 | 0 | 0 | 0 | 0 | 4699 | 0.88996 | 0 | 0 | 3.7879e-05 |  |  | HB | 08W | 2021-09-10 17:00 | 2021-03-30 | Y | 2021-07-31 |  |  |  | No | [12 empty] | Completed | 2021-06-12 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.89 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-10 17:00 |  | N/A | 2021-12-15 08:00 |  | 316666 | 7959.8 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | ED.04331.1102.RECL | 9 | 35217270 | CWSP |  | Meet | No |  | 2021-06-22 18:20
35225591 |  | SH | Keep | CWSP - KONOCTI 1102 LR 965078 PH3 | Scoped | ESTS |  | 0 | 4224 | 0 | 4224 | 0.8 | 0 | 0 | 0 | 0 | 4224 | 0.8 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-20 17:00 | 2021-03-30 | Y | 2021-07-31 | [16 empty] | Completed | 2021-06-12 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-20 17:00 |  | N/A | 2021-11-10 08:00 |  | 316666 | 15491.6 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Kelseyville | Lake | 38.93 | -122.7428 | [10 empty] | ED.04331.1102.RECL | 9 | 35217270 | CWSP |  | Meet | No |  | 2021-05-26 17:29
35226819 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.2 | Scoped | ESTS |  | 0 | 10507 | 0 | 10507 | 1.99 | 0 | 0 | 0 | 0 | 10507 | 1.99 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-03 17:00 | 2021-04-28 | Y | [17 empty] | Completed | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.99 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-03 17:00 |  | N/A | 2021-12-29 08:00 |  |  | 29208.9 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | No |  | 2021-04-26 14:01
35227160 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.3 | Scoped | ESTS |  | 6970 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 | 0 | 6970 | 1.3201 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-03 17:00 | 2021-04-28 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3201 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-03 17:00 |  | N/A | 2021-12-29 08:00 |  |  | 27983.1 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | Meet |  | 2021-04-26 14:01
35227161 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.4 | Scoped | ESTS |  | 0 | 3907 | 0 | 3907 | 0.73996 | 0 | 0 | 0 | 0 | 3907 | 0.73996 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-10 17:00 | 2021-04-28 | Y | 2021-08-22 | 2021-07-23 | No |  | No | [12 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.73996 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-10 17:00 |  | N/A | 2021-12-14 08:00 |  |  | 17275.2 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | No |  | 2021-06-10 10:00
35227162 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.5 | Scoped | ESTS |  | 1690 | 0 | 0 | 1690 | 0.32008 | 0 | 0 | 0 | 0 | 1690 | 0.32008 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-24 17:00 | 2021-04-28 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32008 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-24 17:00 |  | N/A | 2021-12-29 08:00 |  |  | 2282.8 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | Meet |  | 2021-03-05 11:49
35227163 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.6 | Scoped | ESTS |  | 0 | 2429 | 0 | 2429 | 0.46004 | 0 | 0 | 0 | 0 | 2429 | 0.46004 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-17 17:00 | 2021-04-28 | Y | 2021-08-08 | 2021-07-09 | No |  | No | [12 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46004 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-17 17:00 |  | N/A | 2021-12-29 08:00 |  |  | 7411.5 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | No |  | 2021-06-10 11:10
35227164 |  | SH | Keep | CWSP - MIDDLETOWN 1102 -LR 302610 PH 1.7 | Scoped | ESTS |  | 0 | 4752 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-04-28 | Y | 2021-07-30 | 2021-06-30 | Yes |  | No | Yes | [11 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-11 17:00 |  | N/A | 2021-12-01 08:00 |  |  | 16852.2 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7573 | -122.606 | [10 empty] | ED.04314.1102.RECL | 8 | 35217269 | CWSP |  | Meet | No |  | 2021-06-24 10:22
35227165 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH3.2 | Scoped | ESTS |  | 5333 | 0 | 0 | 5333 | 1.01 | 0 | 0 | 0 | 0 | 5333 | 1.01 | 0 | 0 | 0 |  |  | HB | 08W | 2021-10-15 17:00 | 2021-04-30 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.01 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-15 17:00 |  | N/A | 2022-02-09 08:00 |  |  | 4444.9 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220896 | CWSP |  | Meet | Meet |  | 2021-03-05 11:50
35227167 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH3.3 | Scoped | ESTS |  | 9504 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 | 0 | 9504 | 1.8 | 0 | 0 | 0 |  |  | HB | 08W | 2021-10-15 17:00 | 2021-04-30 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-15 17:00 |  | N/A | 2022-02-09 08:00 |  |  | 3596.4 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220896 | CWSP |  | Meet | Meet |  | 2021-03-18 09:41
35227168 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH3.4 | Scoped | ESTS |  | 8290 | 0 | 0 | 8290 | 1.5701 | 0 | 0 | 0 | 0 | 8290 | 1.5701 | 0 | 0 | 0 |  |  | HB | 08W | 2021-10-15 17:00 | 2021-04-30 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5701 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-15 17:00 |  | N/A | 2022-02-09 08:00 |  |  | 3428.3 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220896 | CWSP |  | Meet | Meet |  | 2021-03-18 09:41
35227860 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.2 | Scoped | ESTS |  | 0 | 1056 | 0 | 1056 | 0.2 | 0 | 0 | 1056 | 0.2 | 0 | 0 | 0 | 0 | 0 | 1035 | 0.19602 | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-11 | 2021-06-11 | Yes | 2021-06-17 | Yes | Yes |  | Yes | 2021-06-10 |  |  | Yes | [5 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-16 17:00 |  | N/A | 2021-08-11 08:00 |  | 75000 | 21901.8 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-24 10:07
35227861 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.3 | Scoped | PEND |  | 0 | 8026 | 0 | 8026 | 1.5201 | 0 | 0 | 8026 | 1.5201 | 0 | 0 | 0 | 0 | 0 | 7992 | 1.5136 | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-03 | Yes | Yes |  |  | 2021-06-19 |  |  | No |  |  |  | 2021-07-30 |  | N/A |  |  |  |  | 2021-07-30 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5201 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-11 17:00 |  | N/A | 2021-10-01 08:00 |  | 80000 | 44052.1 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-17 10:32
35227862 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.4 | Scoped | PEND |  | 0 | 5755 | 0 | 5755 | 1.09 | 0 | 0 | 5755 | 1.09 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-24 | 2021-06-24 | Yes | 2021-06-03 | Yes | Yes |  |  | 2021-06-08 |  | 2021-06-21 | No |  |  |  | 2021-07-30 |  | N/A |  |  |  |  | 2021-07-30 |  |  |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-16 17:00 |  | N/A | 2021-08-25 08:00 |  | 80000 | 32504.9 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-22 09:02
35227863 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.5 | Scoped | APPR |  | 0 | 4171 | 0 | 4171 | 0.78996 | 0 | 0 | 4171 | 0.78996 | 0 | 0 | 0 | 0 | 0 | 4196 | 0.7947 | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-17 | Yes | Yes | [11 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.78996 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-09 17:00 |  | N/A | 2021-09-29 08:00 |  | 80000 | 13033.8 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-17 12:14
35227864 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.6 | Scoped | ESTS |  | 3274 | 0 | 0 | 3274 | 0.62008 | 0 | 0 | 0 | 0 | 3274 | 0.62008 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-10 17:00 | 2021-03-30 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62008 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-10 17:00 |  | N/A | 2022-01-05 08:00 |  | 200000 | 10038.7 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | Meet |  | 2021-04-13 20:38
35227866 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.7 | Scoped | ESTS |  | 0 | 2746 | 0 | 2746 | 0.52008 | 0 | 0 | 2746 | 0.52008 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-10 | Yes | Yes | [11 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.52008 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-11 17:00 |  | N/A | 2021-10-01 08:00 |  | 75000 | 44281.9 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-10 09:53
35227867 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.8 | Scoped | ADER |  | 0 | 5174 | 0 | 5174 | 0.97992 | 0 | 0 | 5174 | 0.97992 | 0 | 0 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-03 | Yes | Yes | [11 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.97992 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-11 17:00 |  | N/A | 2021-10-01 08:00 |  | 80000 | 25893.9 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-10 09:55
35227868 |  | SH | Keep | CWSP - MIDDLETOWN 1103 LR 830 PH 1.9 | Scoped | ESTS |  | 0 | 2112 | 0 | 2112 | 0.4 | 0 | 0 | 0 | 0 | 2112 | 0.4 | 0 | 0 | 0 |  |  | HB | 08W | 2021-09-03 17:00 | 2021-03-30 | Y | [17 empty] | Completed | 2021-06-15 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.4 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-03 17:00 |  | N/A | 2021-10-26 08:00 |  | 80000 | [11 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35217271 | CWSP |  | Meet | No |  | 2021-06-21 12:56
35228186 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH2.2 | Scoped | UNSE |  | 7867 | 0 | 0 | 7867 | 1.49 | 0 | 0 | 0 | 0 | 7867 | 1.49 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | [17 empty] | Completed | 2021-05-25 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.49 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-20 17:00 |  | N/A | 2021-12-08 08:00 |  | 250000 | 3804.6 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220895 | CWSP |  | Meet | Meet |  | 2021-05-26 17:26
35228187 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH2.3 | Scoped | PEND |  | 0 | 3326 | 0 | 3326 | 0.62992 | 0 | 0 | 3326 | 0.62992 | 0 | 0 | 0 | 0 | 0 | 3042 | 0.57614 | HB | 08W | 2021-08-23 13:10 | 2021-03-30 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-07 | Yes | Yes | N/A |  | 2021-06-17 |  |  | No |  |  |  | 2021-08-02 |  | N/A |  |  |  |  | 2021-08-02 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.62992 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-11 17:00 |  | N/A | 2021-10-01 08:00 |  | 100000 | 23298.2 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220895 | CWSP |  | Meet | No |  | 2021-06-22 10:33
35228188 |  | SH - Remote Grid | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH2.4 | Scoped | UNSE |  | 0 | 0 | 19694 | 19694 | 3.7299 | 0 | 0 | 0 | 0 | 19694 | 3.7299 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-30 17:00 |  | N | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7299 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-30 17:00 |  | N/A | 2021-10-20 08:00 |  | 250000 | [11 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220895 | CWSP |  | Meet | No |  | 2021-05-19 14:20
35236661 |  | SH | Keep | CWSP - MIDDLETOWN 1103 - LR 830 PH2.5 | Scoped | APPR |  | 0 | 1162 | 0 | 1162 | 0.22008 | 0 | 0 | 1162 | 0.22008 | 0 | 0 | 0 | 0 | 0 | 1067 | 0.20208 | HB | 08W | 2021-09-07 17:00 | 2021-03-31 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-17 | Yes | Yes | [11 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.22008 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-09-07 17:00 |  | N/A | 2021-10-28 08:00 |  | 100000 | 3854.5 | [10 empty] | July Site Visit Potential | Middletown | Lake | 38.7561 | -122.6052 | [10 empty] | ED.04314.1103.RECL | 14 | 35220895 | CWSP |  | Meet | No |  | 2021-06-17 10:32
35219098 |  | SH | Keep | CWSP - MIDDLETOWN 1101118494 PH 1.1 | Scoped | PEND |  | 0 | 3710 | 0 | 3710 | 0.70265 | 0 | 0 | 3710 | 0.70265 | 0 | 0 | 0 | 0 | 0 | 3710 | 0.70265 | HB | 08W | 2021-07-08 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-30 |  |  | Yes |  |  |  | 2021-06-04 |  | 2021-05-18 | Yes |  |  |  | 2021-05-24 | 2021-05-24 | N/A |  | NA |  | Full | 2021-05-24 | 2021-05-24 | Full |  | 2021-06-04 | Yes |  |  | Y |  | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70265 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-08 17:00 | No | INPR | 2021-08-16 08:00 |  | 475000 | 397993.6 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | ED.04314.1101.RECL | 23 | 35219098 | CWSP |  | Meet | No |  | 2021-06-08 08:50
35229119 |  | SH | Keep | CWSP - MIDDLETOWN 1101118494 PH 1.2 | Scoped | ESTS |  | 3093 | 0 | 0 | 3093 | 0.5858 | 0 | 0 | 0 | 0 | 3093 | 0.5858 | 0 | 0 | 0 | 3093 | 0.5858 | HB | 08W | 2021-10-12 17:00 | 2021-02-18 | Y | 2021-04-30 | 2021-04-30 | No |  | Yes |  |  |  | 2021-05-17 |  | 2021-07-16 | No |  |  |  | 2021-07-08 | 2021-07-08 | Completed | 2021-03-18 |  |  |  | 2021-07-08 | 2021-07-08 |  |  |  | Yes | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5858 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-12 17:00 | No | INPR | 2021-10-15 08:00 |  | 475000 | 422970.5 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Middletown | Lake | 38.7514 | -122.6117 | [10 empty] | ED.04314.1101.RECL | 23 | 35219098 | CWSP |  | Meet | Meet |  | 2021-06-22 14:53
35219097 |  | SH | Keep | CWSP - COARSEGOLD 2104CB PH 1.1 | Scoped | PEND |  | 0 | 13091 | 0 | 13091 | 2.4794 | 0 | 0 | 13091 | 2.4794 | 0 | 0 | 0 | 0 | 0 | 13091 | 2.4794 | YO | 08W | 2021-07-21 | 2021-02-26 | Y | 2021-04-30 | 2021-04-30 | [6 empty] | 2021-04-30 |  |  | Yes |  |  |  | 2021-07-21 | 2021-07-21 | N/A |  | NA |  |  | 2021-06-21 | 2021-07-21 | Full |  | 2021-08-07 | Yes |  | 2021-07-09 |  | 2021-06-22 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4794 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-06-17 17:00 | Yes | COMP | 2021-08-13 08:00 |  | 275000 | 3416024.7 | [10 empty] | July Site Visit Potential | Coarsegold | Madera | 37.2276 | -119.6896 |  | ML | OH | [7 empty] | ED.72-08213D0000.STRU.POLE | 22 | 35219097 | CWSP |  | Meet | No |  | 2021-06-22 10:54
35227260 |  | SH | Keep | CWSP - COARSEGOLD 2104CB PH 1.2 | Scoped | UNSC |  | 0 | 12501 | 0 | 12501 | 2.3676 | 0 | 0 | 12501 | 2.3676 | 0 | 0 | 0 | 0 | 0 | 12501 | 2.3676 | YO | 08W | 2021-06-16 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [6 empty] | 2021-05-27 |  |  | Yes |  |  |  | 2021-06-01 | 2021-06-01 |  |  |  |  | Full | 2021-06-01 | 2021-06-01 | Full |  | 2021-05-14 | Yes |  | 2021-06-18 |  | 2021-06-07 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3676 | 0 | 0 | 2.2212 | 11728 | 0 | 0 | 2.2212 | 0 | 0 |  |  | 2021-06-16 17:00 | Yes | COMP | 2021-07-14 08:00 |  | 275000 | 2543228.4 | [10 empty] | July Site Visit Potential | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | ED.72-08213D0000.STRU.POLE | 22 | 35219097 | CWSP |  | Meet | No |  | 2021-06-22 13:07
35227261 |  | SH | Keep | CWSP - COARSEGOLD 2104CB PH 1.3 | Scoped | UNSC |  | 0 | 9130 | 0 | 9130 | 1.7292 | 0 | 0 | 9130 | 1.7292 | 0 | 0 | 0 | 0 | 0 | 9130 | 1.7292 | YO | 08W | 2021-06-10 | 2021-02-26 | Y | 2021-04-16 | 2021-04-16 | [6 empty] | 2021-05-19 |  |  | Yes |  |  |  | 2021-05-17 | 2021-05-17 |  |  |  |  | Full | 2021-05-17 | 2021-05-17 | Full |  | 2021-05-10 | Yes |  | 2021-06-04 | Y | 2021-05-25 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7292 | 0 | 0 | 1.729 | 9129 | 0 | 0 | 1.729 | 0 | 0 |  |  | 2021-06-16 17:00 | Yes | COMP | 2021-07-27 08:00 |  | 250000 | 2081776.1 | [10 empty] | July Site Visit Potential | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | ED.72-08213D0000.STRU.POLE | 22 | 35219097 | CWSP |  | Meet | No |  | 2021-06-22 13:07
35227262 |  | SH | Keep | CWSP - COARSEGOLD 2104CB PH 1.4 | Scoped | UNSC |  | 0 | 9162 | 0 | 9162 | 1.7352 | 0 | 0 | 9162 | 1.7352 | 0 | 0 | 0 | 0 | 0 | 9162 | 1.7352 | YO | 08W | 2021-05-28 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-05-27 |  |  | Yes |  |  |  | 2021-05-10 | 2021-05-10 |  |  |  |  | Full | 2021-05-10 | 2021-05-10 | Full |  | 2021-05-15 | Yes |  | 2021-05-31 | Y | 2021-05-17 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7352 | 0 | 0 | 1.7341 | 9156 | 0 | 0 | 1.7341 | 0 | 0 |  |  | 2021-06-16 17:00 | Yes | COMP | 2021-07-20 08:00 |  | 150000 | 2417522 | [10 empty] | July Site Visit Potential | Coarsegold | Madera | 37.2275 | -119.6896 |  | TL | OH | [7 empty] | ED.72-08213D0000.STRU.POLE | 22 | 35219097 | CWSP |  | Meet | No |  | 2021-06-22 13:07
35219092 |  | SH | Remove | CWSP - POSO MOUNTAIN 2104CB |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 08W | 2021-08-23 13:10 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Bakersfield | Kern | 35.5492 | -118.9618 | [10 empty] | ED.66-2728600000.STRU.POLE | 15 |  | CWSP |  | Meet | No |  | 2021-03-15 16:10
35219264 |  | SH | Remove | CWSP - POSO MOUNTAIN 2103CB |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | KE | 08W | 2021-08-23 13:10 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Bakersfield | Kern | 35.559 | -118.9571 | [10 empty] | ED.66-2728400000.STRU.POLE | 30 |  | CWSP |  | Meet | No |  | 2021-03-15 16:10
35219265 |  | SH | Remove | CWSP - CRESTA 1101546650 |  | UNSE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | NV | 08W | 2021-08-23 13:10 | [42 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Feather Falls | Butte | 39.8308 | -121.4091 | [10 empty] | ED.10225.1101.RECL | 33 |  | CWSP |  | Meet | No |  | 2021-03-15 16:10
35217267 |  | SH | Keep | SH - MARIPOSA 2102 LR 241564 | Scoped | CONS |  | 0 | 4752 | 0 | 4752 | 0.9 | 0 | 0 | 4752 | 0.9 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | 2021-06-07 | 2021-02-18 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-06-03 |  | 2021-04-05 | Yes |  |  |  | 2021-05-03 | 2021-05-03 | N/A |  | NA |  | Full | 2021-05-03 | 2021-05-03 | Full |  | 2021-04-30 | Yes |  | 2021-05-21 | Y | 2021-05-04 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-06-07 17:00 | Yes | COMP | 2021-07-14 08:00 |  | 804541 | 770997.9 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Mariposa | Mariposa | 37.4871 | -119.9619 | [10 empty] | ED.25445.2102.RECL | 10 |  | CWSP |  | Meet | No |  | 2021-06-24 13:25
35219266 |  | SH | Keep | CWSP - MARIPOSA 2102CB PH 1 | Scoped | PEND |  | 0 | 13713 | 0 | 13713 | 2.5972 | 0 | 0 | 13713 | 2.5972 | 0 | 0 | 0 | 0 | 0 | 15653 | 2.9646 | YO | 08W | 2021-08-04 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-04-01 |  | 2021-04-09 | Yes |  |  |  | 2021-08-04 | 2021-08-04 | Completed | 2021-04-09 |  |  |  | 2021-08-04 | 2021-08-04 | Partial |  | 2021-04-30 | Yes |  | 2021-06-21 |  | 2021-06-08 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5972 | 0 | 0 | 2.9312 | 15477 | 0 | 0 | 2.9312 | 0 | 0 |  |  | 2021-07-08 17:00 | No | INPR | 2021-09-13 08:00 |  | 950000 | [11 empty] | July Site Visit Potential | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | ED.72-0518096000.STRU.POLE | 35 | 35219266 | CWSP |  | Meet | No |  | 2021-06-15 08:41
35219268 |  | SH | Keep | CWSP - MARIPOSA 210197142 PH 1 | Scoped | PEND |  | 0 | 8553.6 | 0 | 8553.6 | 1.62 | 0 | 0 | 8554 | 1.6201 | 0 | 0 | 0 | 0 | -7.5758e-05 | 10425 | 1.9744 | YO | 08W | 2021-08-19 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-03-25 |  |  | Yes |  |  |  | 2021-08-19 | 2021-08-19 | Completed | 2021-03-12 |  |  |  | 2021-08-19 | 2021-08-19 | Partial |  | 2021-04-30 | Yes |  | 2021-05-21 | Y | 2021-05-03 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.62 | 0 | 0 | 1.972 | 10412 | 0 | 0 | 1.972 | 0 | 0 |  |  | 2021-07-07 17:00 | No | INPR | 2021-09-14 08:00 |  | 950000 | [6 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | ED.25445.2101.RECL | 36 | 35219268 | CWSP |  | Meet | No |  | 2021-06-08 10:38
35226240 |  | SH | Keep | CWSP - MARIPOSA 210197142 PH 3 | Scoped | PEND |  | 0 | 7526.4 | 0 | 7526.4 | 1.4255 | 0 | 0 | 7526 | 1.4254 | 0 | 0 | 0 | 0 | 7.5758e-05 |  |  | YO | 08W | 2021-02-27 |  | Y | 2021-02-28 | 2021-02-28 | [6 empty] | 2021-03-03 |  |  | Yes |  |  |  | 2021-04-19 | 2021-04-19 |  |  |  |  | Full | 2021-04-19 | 2021-04-19 | Full |  | 2021-04-30 | Yes |  | 2021-05-07 | Y | 2021-04-27 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4255 | 0 | 0 | 1.1701 | 6178 | 0 | 0 | 1.1701 | 0 | 0 |  |  | 2021-05-26 17:00 | Yes | INPR | 2021-07-21 08:00 |  |  | 1296155.5 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | ED.25445.2101.RECL | 36 | 35219268 | CWSP |  | Meet | No |  | 2021-06-01 11:18
35226241 |  | SH | Keep | CWSP - MARIPOSA 210197142 PH 2 | Scoped | PEND |  | 0 | 7920 | 0 | 7920 | 1.5 | 0 | 0 | 7920 | 1.5 | 0 | 0 | 0 | 0 | 0 | 6651 | 1.2597 | YO | 08W | 2021-07-30 | 2021-02-08 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-03-26 |  |  | Yes |  |  |  | 2021-07-30 | 2021-06-30 | Completed | 2021-03-12 |  |  |  | 2021-07-30 | 2021-06-30 | Partial |  | 2021-04-30 | Yes |  | 2021-06-25 |  | 2021-06-14 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 1.2045 | 6360 | 0 | 0 | 1.2045 | 0 | 0 |  |  | 2021-06-01 17:00 | Yes | INPR | 2021-08-25 08:00 |  |  | 1201108.5 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Mariposa | Mariposa | 37.5066 | -120.0082 | [10 empty] | ED.25445.2101.RECL | 36 | 35219268 | CWSP |  | Meet | No |  | 2021-06-15 08:39
35227263 |  | SH | Keep | CWSP - MARIPOSA 2102CB PH 2 | Scoped | CONS |  | 0 | 1315.42 | 0 | 1315.42 | 0.24913 | 0 | 0 | 1315 | 0.24905 | 0 | 0 | 0 | 0 | 7.9545e-05 |  |  | YO | 08W | 2021-06-07 | 2021-02-22 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-05-14 |  | 2021-04-09 | Yes |  |  |  | 2021-05-13 | 2021-05-13 |  |  |  |  | Full | 2021-05-13 | 2021-05-13 | Full |  | 2021-05-15 | Yes |  | 2021-06-11 | Y | 2021-05-26 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.24913 | 0 | 0 | 3.457 | 18253 | 0 | 0 | 3.457 | 0 | 0 |  |  | 2021-06-07 17:00 | Yes | COMP | 2021-07-20 08:00 |  |  | 1154715.9 | [10 empty] | July Site Visit Potential | Mariposa | Mariposa | 37.5061 | -120.0049 | [10 empty] | ED.72-0518096000.STRU.POLE | 35 | 35219266 | CWSP |  | Meet | No |  | 2021-06-15 08:34
35238567 |  | SH | keep | CWSP - MARIPOSA 210197142 PH 1.4 | Scoped | PEND |  | 0 | 288 | 0 | 288 | 0.054545 | 0 | 0 | 0 | 0 | 288 | 0.054545 | 0 | 0 | 0 | 551 | 0.10436 | YO | 08W | 2021-08-23 13:10 |  |  |  |  | Yes | 2021-05-11 |  |  |  |  | 2021-06-12 | [6 empty] | 2021-07-29 |  | Completed | 2021-03-12 |  |  |  | 2021-07-29 |  |  |  | 2021-07-09 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.054545 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-16 17:00 |  | N/A | 2021-09-07 08:00 | [13 empty] | July Site Visit Potential | Mariposa | Mariposa | 37.5065 | -120.0082 | [10 empty] | ED.25445.2101.RECL | 36 | 35219268 | CWSP |  | Meet | No |  | 2021-06-22 10:37
35219093 |  | SH | Keep | CWSP - TIDEWATER 210614072 PH 1.1 | Scoped | UNSE |  | 6019 | 0 | 0 | 6019 | 1.14 | 0 | 0 | 0 | 0 | 6019 | 1.14 | 0 | 0 | 0 |  |  | DI | 08W | 2022-03-31 17:00 | 2021-03-03 | Y | [17 empty] | In Progress | 2021-06-24 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.14 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-03-31 17:00 |  | INPR | 2022-04-25 08:00 |  | 350000 | 4824512.6 | [10 empty] | July Site Visit Potential | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | ED.01465.2106.RECL | 18 | 35219093 | CWSP |  | Meet | Meet |  | 2021-06-01 19:24
35219096 |  | SH | Keep | CWSP - KIRKER 2104442850 PH 1.1 | Scoped | UNSE |  | 8817.6 | 0 | 0 | 8817.6 | 1.67 | 0 | 0 | 0 | 0 | 8818 | 1.6701 | 0 | 0 | -7.5758e-05 |  |  | DI | 08W | 2022-03-31 17:00 | 2021-03-03 | Y | [17 empty] | In Progress | 2021-06-24 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.67 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-03-31 17:00 |  | INPR | 2022-04-25 08:00 |  | 500000 | 5230409.8 | [10 empty] | July Site Visit Potential | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | ED.01445.2104.RECL | 21 | 35219096 | CWSP |  | Meet | Meet |  | 2021-03-16 08:22
35227655 |  | SH - Remote Grid | Keep | CWSP - KIRKER 2104442850 PH 1.2 | Scoped | UNSE |  | 0 | 0 | 19906 | 19906 | 3.7701 | 0 | 0 | 0 | 0 | 19906 | 3.7701 | 0 | 0 | 0 |  |  | DI | 08W | 2022-05-12 17:00 | [19 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7701 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-05-12 17:00 |  | INPR | 2022-06-06 08:00 |  | 450000 | 2008627.6 | [10 empty] | July Site Visit Potential | Pittsburg | Contra Costa | 37.9907 | -121.896 | [10 empty] | ED.01445.2104.RECL | 21 | 35219096 | CWSP |  | Meet | No |  | 2021-06-01 20:24
35231543 |  | SH | Keep | CWSP - TIDEWATER 210614072 PH 1.2 | Scoped | ESTS |  | 6864 | 0 | 0 | 6864 | 1.3 | 0 | 0 | 0 | 0 | 6864 | 1.3 | 0 | 0 | 0 |  |  | DI | 08W | 2022-03-31 17:00 | 2021-03-03 | Y | [17 empty] | In Progress | 2021-06-24 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-03-31 17:00 |  | INPR | 2022-04-25 08:00 |  | 350000 | 5441120.8 | [10 empty] | July Site Visit Potential | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | ED.01465.2106.RECL | 18 | 35219093 | CWSP |  | Meet | Meet |  | 2021-03-25 09:49
35231544 |  | SH | Keep | CWSP - TIDEWATER 210614072 PH 1.3 | Scoped | UNSC |  | 0 | 5813 | 0 | 5813 | 1.1009 | 0 | 0 | 5813 | 1.1009 | 0 | 0 | 0 | 0 | 0 | 5813 | 1.1009 | DI | 08W | 2021-06-21 | 2021-03-03 | Y | 2021-04-30 | 2021-04-30 | Yes |  | Yes |  |  |  | 2021-06-10 |  | 2021-06-22 | Yes |  |  |  | 2021-06-07 | 2021-06-07 |  |  |  |  | Full | 2021-06-07 | 2021-06-07 | Full |  | 2021-05-25 | Yes |  | 2021-06-14 | Y | 2021-06-14 | Y | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1009 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-08 17:00 | Yes | COMP | 2021-07-19 08:00 |  | 1703144 | 1485177.1 | [10 empty] | July Site Visit Potential | Concord | Contra Costa | 37.9632 | -121.9407 | [10 empty] | ED.01465.2106.RECL | 18 | 35219093 | CWSP |  | Meet | No |  | 2021-06-22 08:52
35219291 |  | SH | Keep | CWSP - VACA DIXON 1101126774 | Scoped | PEND |  | 0 | 2082 | 0 | 2082 | 0.39432 | 0 | 0 | 2082 | 0.39432 | 0 | 0 | 0 | 0 | 0 | 2082 | 0.39432 | SA | 08W | 2021-07-02 17:00 | 2021-02-22 | Y | 2021-03-15 | 2021-03-15 | Yes | [5 empty] | 2021-03-11 |  |  | Yes |  |  |  | 2021-04-26 | 2021-04-26 |  |  |  |  | Full | 2021-04-26 | 2021-04-26 | Full |  |  | Yes |  | 2021-07-02 |  | 2021-06-29 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39432 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-02 17:00 | No | INPR | 2021-08-03 08:00 |  | 950000 | 395211.8 | [5 empty] | Prioritized |  |  |  |  | July Site Visit Potential | Vacaville | Solano | 38.3973 | -121.9855 |  | TL | OH | [7 empty] | ED.06359.1101.RECL | 20 |  | CWSP |  | Meet | No |  | 2021-06-23 08:47
35219590 |  | SH | Keep | CWSP - VACA DIXON 1105965390 | Scoped | ADER |  | 0 | 8404 | 0 | 8404 | 1.5917 | 0 | 0 | 8404 | 1.5917 | 0 | 0 | 0 | 0 | 0 | 8536 | 1.6167 | SA | 08W | 2021-08-23 13:10 | 2021-05-10 | Y | 2021-06-30 | 2021-06-30 | Yes | 2021-06-30 | No | Yes |  | No | [9 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5917 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-28 17:00 |  | INPR | 2021-09-01 08:00 |  | 950000 | 2136721.4 | [10 empty] | July Site Visit Potential | Vacaville | Solano | 38.4341 | -121.9915 | [10 empty] | ED.06359.1105.RECL | 53 |  | CWSP |  | Meet | No |  | 2021-06-24 10:12
35237365 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.7 | Scoped | ESTS |  | 0 | 13569 | 0 | 13569 | 2.5699 | 0 | 0 | 0 | 0 | 13569 | 2.5699 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5699 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:57
35237366 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.8 | Scoped | ESTS |  | 0 | 11774 | 0 | 11774 | 2.2299 | 0 | 0 | 0 | 0 | 11774 | 2.2299 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2299 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:57
35237368 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.9 | Scoped | ESTS |  | 0 | 22123 | 0 | 22123 | 4.19 | 0 | 0 | 0 | 0 | 22123 | 4.19 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.19 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:57
35237369 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.10 | Scoped | ESTS |  | 0 | 16579 | 0 | 16579 | 3.14 | 0 | 0 | 0 | 0 | 16579 | 3.14 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.14 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:57
35237370 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.11 | Scoped | ESTS |  | 0 | 19958 | 0 | 19958 | 3.7799 | 0 | 0 | 0 | 0 | 19958 | 3.7799 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7799 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:57
35237371 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.12 | Scoped | ESTS |  | 0 | 1795 | 0 | 1795 | 0.33996 | 0 | 0 | 0 | 0 | 1795 | 0.33996 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.33996 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-24 07:58
35219099 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.1 | Scoped | UNSE |  | 0 | 14398 | 0 | 14398 | 2.7269 | 0 | 0 | 0 | 0 | 14398 | 2.7269 | 0 | 0 | 0 |  |  | HB | 08W | 2021-11-01 17:00 | 2021-04-15 | Y | [17 empty] | In Progress | 2021-09-03 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.7269 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-11-01 17:00 |  | N/A | 2021-11-24 08:00 |  | 73076 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-13 09:31
35231620 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.2 | Scoped | UNSE |  | 14141 | 0 | 0 | 14141 | 2.6782 | 0 | 0 | 0 | 0 | 14141 | 2.6782 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [17 empty] | In Progress | 2021-09-03 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6782 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | Meet |  | 2021-05-19 12:37
35231621 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.3 | Scoped | UNSE |  | 7210 | 0 | 0 | 7210 | 1.3655 | 0 | 0 | 0 | 0 | 7210 | 1.3655 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [17 empty] | In Progress | 2021-09-03 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3655 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | Meet |  | 2021-05-25 10:36
35231622 |  | SH - Remote Grid | Keep | CWSP - HIGHLANDS 1102628 PH 1.4 | Scoped | UNSE |  | 24499 | 0 | 24499 | 48998 | 9.2799 | 0 | 0 | 0 | 0 | 48998 | 9.2799 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2799 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | Meet |  | 2021-06-02 14:03
35231623 |  | SH - Remote Grid | Keep | CWSP - HIGHLANDS 1102628 PH 1.5 | Scoped | UNSE |  | 0 | 1078 | 14963 | 16041 | 3.0381 | 0 | 0 | 0 | 0 | 16041 | 3.0381 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0381 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-20 09:12
35231624 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.6 | Scoped | UNSE |  | 0 | 4096 | 0 | 4096 | 0.77576 | 0 | 0 | 0 | 0 | 4096 | 0.77576 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77576 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-25 10:36
35231625 |  | SH - Remote Grid | Keep | CWSP - HIGHLANDS 1102628 PH 1.7 | Scoped | UNSE |  | 0 | 0 | 1000 | 1000 | 0.18939 | 0 | 0 | 0 | 0 | 1000 | 0.18939 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18939 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-25 10:37
35231626 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.8 | Scoped | PEND |  | 0 | 3607 | 0 | 3607 | 0.68314 | 0 | 0 | 3607 | 0.68314 | 0 | 0 | 0 | 0 | 0 | 4041 | 0.76534 | HB | 08W | 2021-08-23 13:10 | 2021-04-15 | Y | 2021-05-31 | 2021-05-31 |  | 2021-06-09 |  | No |  |  | 2021-05-31 |  |  | Yes | [15 empty] | Yes |  |  |  | 2021-07-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68314 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-29 17:00 | No | N/A | 2021-08-25 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-06-22 10:31
35231627 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.9 | Scoped | ESTS |  | 0 | 2105 | 0 | 2105 | 0.39867 | 0 | 0 | 0 | 0 | 2105 | 0.39867 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.39867 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-06 11:41
35231628 |  | SH - Remote Grid | Keep | CWSP - HIGHLANDS 1102628 PH 1.10 | Scoped | UNSE |  | 0 | 0 | 7861 | 7861 | 1.4888 | 0 | 0 | 0 | 0 | 7861 | 1.4888 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4888 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-20 09:12
35231629 |  | SH - Remote Grid | Keep | CWSP - HIGHLANDS 1102628 PH 1.11 | Scoped | UNSE |  | 0 | 0 | 902 | 902 | 0.17083 | 0 | 0 | 0 | 0 | 902 | 0.17083 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.17083 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | INPR | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-20 09:12
35231630 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.12 | Scoped | PEND |  | 0 | 1918 | 0 | 1918 | 0.36326 | 0 | 0 | 1919 | 0.36345 | 0 | 0 | 0 | 0 | -0.00018939 | 1883 | 0.35663 | HB | 08W | 2021-08-26 17:00 | 2021-04-15 | Y | 2021-05-31 | 2021-05-31 |  | 2021-06-09 |  | No |  |  | 2021-06-02 |  | 2021-07-27 | No | [15 empty] | Yes |  |  |  | 2021-07-01 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36326 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-08-26 17:00 | No | N/A | 2021-09-20 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-06-22 10:32
35231631 |  | SH | Keep | CWSP - HIGHLANDS 1102628 PH 1.13 | Scoped | UNSE |  | 0 | 2465 | 0 | 2465 | 0.46686 | 0 | 0 | 0 | 0 | 2465 | 0.46686 | 0 | 0 | 0 |  |  | HB | 08W | 2021-12-27 17:00 | 2021-04-15 | Y | [40 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46686 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-12-27 17:00 |  | N/A | 2022-01-19 08:00 |  | 73077 | [11 empty] | July Site Visit Potential | Clearlake | Lake | 38.9822 | -122.6031 | [10 empty] | ED.04336.1102.RECL | 27 | 35219099 | CWSP |  | Meet | No |  | 2021-05-06 11:42
35219269 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.1 | Scoped | ESTS |  | 0 | 11299 | 0 | 11299 | 2.14 | 0 | 0 | 0 | 0 | 11299 | 2.14 | 0 | 0 | 0 |  |  | SA | 08W | 2021-10-01 17:00 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.14 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-01 17:00 |  | N/A | 2021-10-26 08:00 |  | 950000 | [11 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  | TL | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:44
35237258 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.2 | Scoped | ESTS |  | 0 | 11352 | 0 | 11352 | 2.15 | 0 | 0 | 0 | 0 | 11352 | 2.15 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  | MX | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:44
35237259 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.3 | Scoped | ESTS |  | 0 | 21359 | 772 | 22131 | 4.1915 | 0 | 0 | 0 | 0 | 21359 | 4.0453 | 0 | 0 | 0.14621 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.1915 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  | TL | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:44
35237360 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.4 | Scoped | ESTS |  | 0 | 15893 | 0 | 15893 | 3.01 | 0 | 0 | 0 | 0 | 15893 | 3.01 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.01 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:45
35237361 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.5 | Scoped | ESTS |  | 0 | 15154 | 0 | 15154 | 2.8701 | 0 | 0 | 0 | 0 | 15154 | 2.8701 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8701 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:45
35237364 |  | SH | Keep | CWSP - VACA DIXON 110540092 PH 1.6 | Scoped | ESTS |  | 0 | 15998 | 0 | 15998 | 3.0299 | 0 | 0 | 0 | 0 | 15998 | 3.0299 | 0 | 0 | 0 |  |  | SA | 08W | 2021-08-23 13:10 | 2021-06-08 | Y | [17 empty] | N/A | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.0299 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  |  |  | N/A | [14 empty] | July Site Visit Potential | Vacaville | Solano | 38.4159 | -121.9706 |  |  | OH | [7 empty] | ED.06359.1105.RECL | 37 | 35219269 | CWSP |  | Meet | No |  | 2021-06-08 16:45
Note on I1: [REDACTED] This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on J1: [REDACTED] :This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.

## Completed UG
Order | Job Owner Name | Program | Project Reporting Year | Workplan Status | Order Description | Job Owner | Scope Status | SAP Status | Circuit Feet from Planning | UG Feet | OH Feet | Removal | Planned Circuit Feet | Planned Circuit Miles | 2020 Forecast Feet | 2020 Forecast Miles | 2021 Forecast Feet | 2021 Forecast Miles | 2022 Forecast Feet | 2022 Forecast Miles | 2023 Forecast Feet | 2023 Forecast Miles | Unallocated Forecast Miles | SAP Plan Units | SAP Plan Miles | Div | MAT | Ready to Break Ground | Pre-Eng. Mtg Date | Pre-Eng. Complete | SAP Est Out Date | Previous EOD Forecast | CMCS Approved | Walkdown Date | Walkdown Complete | 30% Drawing Complete (Walkdown) | 60% Drawing Complete (Land Rev Reqd) | 80% Drawing Complete (Dependency Set) | PEND IN Date | Contract Estimating Comments | Additional Note/Variance Explanations | Estimating Resource | Estimating Assignment | Estimating Manager | ADE | Estimator | Priority | Status | T-Line Conflict | Composite Poles | Wood Poles | Comp Poles | --1 | Expected Joint Pole Date | Joint Pole Complete | Joint Pole Coordinator | Joint Pole Notes | LCE | Land Clear Date | Previous Land Clear Date | Base Map Status | Expected Base Map Complete | Base Map Vendor | Surveyor | Land Complete | ERTC Planned Date | Previous ERTC Date | ERTC Complete | Land Planner | Envrionmental Lead PGE Contact | Notes | L and ERTC Complete | --2 | Expected Permit Date | Permits Complete | Permit Expire Date | Permit Coordinator | Permitting Notes | --3 | Veg Complete | Veg Completed | Veg Start | Veg Started | ERTC Call Date | Veg Management | Veg Notes | --4 | MPP Resource | Contractor | Contract Ready Date | Contract Status | SAP Actual Units | SAP Actual Miles | 2019 Feet Installed | 2019 Miles Installed | 2020 Feet Installed | 2020 Miles Installed | 2021 Feet Installed | 2021 Miles Installed | Total Installed Miles | Remaining Planned Miles | QA Pass | QA Fix | Total QA Span Length | OH QA Span | UG QA Span | Removal QA Span | QA Remaining | QA Trailing Installed | IA Pass | Span Notes | Construction Notes | P6 Business Case Date | BC Complete | DS24 Status | P6 Construction Start | P6 Operative Date | P6 Operative Actualized | P6 Forecast In Service | UNSC In Date | UNSC Out Date | CLICK Construction Start | CLICK Construction End | CN24 Out Date | Materials Ready Date | Materials Ready | Readiness Notes | --5 | Auth Amt without Contingency (Expected Case) | Total EAC | --6 | Planned Num of Poles | Planning Engineer | General Comments | Scoping Status | Scoping Notes | DLT | Telecom | SCADA Specialist | SWPPP Status | FE Primary or Support | City | County | Latitude | Longitude | Schedule ID | Mainline or Tapline | Hardening Method | Rank Number | CompYR | QTR | Work Plan EOD Baseline | Construction Start Baseline | Construction Complete Baseline | Circuit Protection Zone | Functional Location | Risk Rank | Segmentation ID# | Project Type | Grid Design Priority | LTIP Condition 1 | LTIP Condition 2 | Last Edited By | Last Edited Date
35145522 |  | SH |  | Keep | PSPS - CLARKSVILLE 2104 - CB UG |  | Scoped | PEND | 20830 | 20830 | 0 | 0 | 20830 | 3.9451 | 0 | 0 | 0 | 0 | 20830 | 3.9451 | 0 | 0 | 0 |  |  | SI | 08W | 2022-03-17 17:00 |  | Y | 2020-10-31 | 2020-10-31 | [6 empty] | 2020-12-21 |  |  | DSGN_CENTR | AUBURN | [10 empty] | 2020-08-08 | Yes |  | PSPS |  | 2020-11-15 | 2020-11-15 |  |  |  |  | Full | 2020-08-17 | 2020-08-17 | Full |  |  | Redesign underway to avoid easement - Estimating delayed by fire rebuild | Full |  | 2020-11-30 | Yes | 2021-12-10 |  | Revised drawings submitted on 10/21/20 |  |  | Y |  |  |  |  | Drawings Provided 5/26/2020 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.9451 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-03-17 17:00 |  | INPR | 2022-04-11 08:00 | 2022-10-04 17:00 |  | 2022-12-05 17:00 | 2020-12-17 | 2020-12-21 | [7 empty] | 500000 | 228438.8 |  |  |  |  | Complete | need to verify ex. spare conduits to travel under Caltrans ROW. Most likely need 3rd party engineer for bridge hangers. |  |  |  | Remove |  | El Dorado Hills | El Dorado | 0 | 0 | E.5025635.01 | ML | UG | 2021-125 | 2021 |  |  |  | 2020-09-01 | CLARKSVILLE 2104CB | ED.15361.2109.SWIT | 134 |  | PSPS |  | Meet | Meet |  | 2021-06-16 12:12
35057018 |  | SH | 2021 | Keep | CWSP - EL DORADO 2101 - 19752 - PH 4.1 |  | Scoped | PEND | 10624 | 12966 | 0 | 0 | 12966 | 2.4557 | 0 | 0 | 12966 | 2.4557 | 0 | 0 | 0 | 0 | 0 |  |  | SI | 08W | 2021-08-23 13:10 |  | Y | [8 empty] | 2020-07-17 | 11/04: EST submitted10/28: RD EOD (11/29); retaining walls 2 wks out; met with county; conflict with land survey (distances from street - 2 sources)10/21: Meeting Monday with county and [REDACTED] in person for job walk07/17: APPROVED - INTO PEND07/17: ADER final corrections to CO; QUES submitted for final rvw07/15: Subcontractor - to conduct some fielding items; Contracts needing to be developed/issued for 3rd party surveying. To be added post approval (approx 1.5 month); RISK - Permitting 6wks out, El Dorado Review07/14: QUES submitted for 4th ADE rvw; ADE approved for routing07/13: ADE rtn [final pt] 3rd corrections to CO; through loc 229, sheet 11; complete07/09: [REDACTED] - rvw provided to CO; provided some insight on potential County rvw catch points.07/09: ADE rtn [partial] 3rd corrections to CO; through loc 117, sheet 707/08: ADE in rvw; QUES provided most up to date estimate file on sharepoint07/07: ADE rtn [partial] 3rd corrections to CO; through sheet 3 loc 2007/06: QUES submitted for 3rd ADE rvw07/01: EST Target sub (7/3) - in final rvw; structural usually works from their design 1st - EST trying to get sub-contractor to work from QUES design (structural small piece)06/24: EST On Track06/17: EST to submit (On Track) - w/ ref to civil design points, civil design to be added upon completion.06/16: EST reached out to 2 ENGR firms; waiting on response6/15: [REDACTED] advised - encourage EST to reach out to REY Engineering in Folsom, believe they are versed in working with El Dorado County regarding civil projects and should be able to assist in a job-package to avoid refusal via our future permit submission06/12: EST - this one needs civil engineering for large retaining walls. Rcv'd the locations from [REDACTED] and am contacting the firms today. DO NOT anticipate a quick turn around from civil.6/10: ADE status check - only have 2 pages of the construction map updated since CAD just started working on it today. Hoping the rest of the pages will be done by this Friday, but until then, only have the redlines ADE drew up for them. We’re using the LIDAR drawings as the base 06/10: EST Sub 6/26 - redlines and finalizing06/03 - 05/27: On Track - will confirm any changes05/20: EST Status - applying virtal job walk changes; new PM not needed, completing a ver.2; processing, review, stamping.05/13: Unable to create a new version to avoid a new PM, EST persuing new PM05/06: Waiting on new PM; Push 2 week 05/01: EES close to getting us into the new PM04/29: EST about ready to start - EES group close to providing PM04/15: [REDACTED] to create new order ([REDACTED] requested)04/08: Change order approved ( pulling new work order)04/01: Applying changes; QUES to submit Change Orders (per progress stage); will be submitting for ADE rvw (TBD; assign next Wen);03/xx: Completed virtual walk02/20 - 02/19: EST - Check in on base maps; [REDACTED] - just finished going through it, Coordination with EST to take a look and talk if you have any questions. EST flagged discussion points and scope completness of maps; information portions for PMS 35056733 & 3510954101/23: received the LiDAR data for the pole lines; will be out surveying some property corners to be able to accurately place the ROW boundary lines on our survey today through Monday or Tuesday; still waiting for the raw LiDAR data and aerial imagery to be able to plot the road and fog lines in their entirety (not a hold up); Planner assistance needed - about a mile section of the road that is on Forest Service property. Contact with the Forest Service will be required. 01/23: PMgr advised going into redesign, back into estimating01/15: Targeting 30% map by 3/14, for 'walk down'; contingent on base map provision by 2/1410/09: APPROVED 10/089/24 - 10/02: ADE complete rvw - approved - waiting for SCADA surveys, will route upon receipt9/23: QUES submitted for 2nd ADE rvw [PRELIM DWG ready]9/13: [REDACTED] Assigned - Review Rtn to contractor9/04 - 9/11: ADE to be assigned--> [RCC Issue]8/30: QUES submitted for 1st ADE Rvw8/21: Going into QUES internal review - may push to 8/27 8/14: UG Job - CAL Eng - push 1wk coordinate Tie ins with CAL7/24 - 8/07 On Track7/3 - 7/16: QUES to review to provide review on 1st ADE Submital |  | CNTRCT_EST | QUES |  |  |  | 2020 - RD- M11 [R2021_83] | Iss_RD1.2_Rdsn - ADE Redesign Rvw in Progress | No | Wood | 21 | 7 |  |  | Yes | [9 empty] | Full | 2020-05-03 | 2020-05-03 | Full |  |  | Received approval from USFS on package. Finalizing our 299 land rights. | Full |  | 2021-07-01 |  |  |  | Request to submit for permit on 3/30/21 - Full size Plans submitted on 6/1 | [7 empty] | [REDACTED] to request surveying on 6/15/21 - Then schedule pre inspection with [REDACTED]. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4557 | 0 | 0 | 2.4557 | 0 | 12966 | 0 | 2.4557 | 0 | 0 |  |  | 2021-07-15 17:00 | No | INPR | 2021-08-31 08:00 | 2022-01-11 17:00 |  | 2022-01-27 17:00 | 2020-07-17 | 2020-07-17 |  |  |  |  | Yes |  |  | 725000 | 7826446.3 |  | 54 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015414.01 | ML | UG | 2021-083 | 2021 |  | 2020-05-31 | 2020-09-01 |  | EL DORADO PH 210119752 | ED.15276.2101 | 1946 |  | PRE |  | No | Meet |  | 2021-06-16 13:28
35145001 |  | SH |  | Keep | PSPS - CLAYTON 2215 - CB |  | Scoped | PEND | 21042 | 9720 | 375 | 0 | 10095 | 1.9119 | 0 | 0 | 0 | 0 | 10095 | 1.9119 | 0 | 0 | 0 | 9720 | 1.8409 | DI | 08W | 2021-11-01 |  |  | 2020-11-30 | 2020-11-30 | Yes | [5 empty] | 2020-10-16 |  |  | DSGN_CENTR | CONCORD | [6 empty] | No |  |  |  | 2020-10-21 | Yes |  | PSPS |  | 2021-11-01 | 2021-01-20 | [5 empty] | 2021-11-01 | 2023-12-25 |  |  |  | CIF submitted 7/7/20 - Needs 2 more easements - already have 1; Potential for wetland constraints in some underground locations to be discussed with project manager in site walks. Need veg scope information for bio reports; to follow up in January; Revised final drawings sent. Land acquisiton working on easements as of 6/15 in negotiations. 2 easements needed |  |  | 2021-12-23 | Yes |  |  | Moved back to work plan on 6/7/21 | [7 empty] | Defering to 2022 for easements | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9119 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-07 17:00 |  | INPR | 2022-02-21 08:00 | 2022-09-06 17:00 |  | 2022-10-04 17:00 | [9 empty] | 500000 | 8133659.9 |  | 9 |  |  | Complete | UG 1.5 miles, OH 0.07 miles, 8 PSPS |  |  |  | Remove |  | Concord | Contra Costa | 0 | 0 | E.5025639.01 | ML | UG | 2021-127 | 2021 |  |  |  | 2020-09-01 | CLAYTON 2215CB | ED.01202.2215 | 0 |  | PSPS |  | Meet | Meet |  | 2021-06-22 10:27
35145524 |  | SH | 2021 | Keep | PSPS - RINCON 1101 1103 SYSTEM HARDENING |  | Scoped | UNSC | 3800 | 9175 | 0 | 0 | 9175 | 1.7377 | 0 | 0 | 9175 | 1.7377 | 0 | 0 | 0 | 0 | 0 | 9175 | 1.7377 | SO | 08W | 2021-06-22 |  | Y | 2020-12-10 | 2020-12-10 |  |  | Yes |  |  |  | 2021-06-21 |  |  | DSGN_CENTR | SANTAROSA | [6 empty] | wood |  |  |  | 2020-11-06 | Yes |  | PSPS |  | 2020-11-19 | 2020-11-19 |  |  |  |  | Full | 2020-11-19 | 2020-11-19 | Full |  |  | No enviro constraints identified | Full |  | 2021-04-07 | Yes | 2021-07-28 |  | As of 6/22/21 - Need to extend permit at least through August - County of Sonoma, City of Santa Rosa |  | 2021-03-03 | Y | 2021-02-22 | Y | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7377 | 0 | 0 | 0.775 | 0 | 4092 | 0 | 0.775 | 0 | 0 |  |  | 2021-03-08 17:00 | Yes | COMP | 2021-04-26 | 2021-08-30 17:00 |  | 2021-10-29 17:00 | 2021-06-22 |  | 2021-04-26 13:04 | 2021-07-30 12:37 |  |  | Yes |  |  | 6419958 | 3050625.3 |  |  |  |  | Complete | waiting for basemaps | [5 empty] | Santa Rosa | Sonoma | 38.4896 | -122.6662 | E.5025637.01 |  |  | 2021-126 | 2021 |  |  |  | 2020-09-01 | RINCON 1103CB | ED.04332.1101 | 1755 |  | PSPS |  | Meet | Meet |  | 2021-06-22 08:52
35145525 |  | SH | 2021 | Keep | PSPS - RINCON 1102 1104 SYSTEM HARDENING |  | Scoped | UNSC | 9398.4 | 7819 | 1056 | 0 | 8875 | 1.6809 | 0 | 0 | 8875 | 1.6809 | 0 | 0 | 0 | 0 | 0 |  |  | SO | 08W | 2021-06-22 |  | Y | 2020-10-31 | 2020-10-31 |  |  | Yes |  |  |  | 2021-06-21 |  |  | DSGN_CENTR | SANTAROSA | [6 empty] | wood |  |  |  | 2020-10-28 | Yes |  | PSPS |  | 2020-11-19 | 2020-11-19 |  |  |  |  | Full | 2020-11-19 | 2020-11-19 | Full |  |  | No enviro constraints identified | Full |  | 2021-03-02 | Yes | 2022-02-18 |  |  |  | 2021-03-03 | Y | 2021-02-22 | Y | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6809 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-03-02 | Yes | COMP | 2021-04-19 | 2021-08-18 17:00 |  | 2021-10-19 17:00 | 2021-06-22 |  | 2021-08-01 07:00 | 2021-10-31 16:00 |  |  | Yes |  |  | 5901787.4 | 2910396.9 |  |  |  |  | Complete | waiting for basemaps | [5 empty] | Santa Rosa | Sonoma | 38.489 | -122.666 | E.5025638.01 |  |  | 2021-130 | 2021 |  |  |  | 2020-09-01 | RINCON 1104CB | ED.04332.1102 | 3302 |  | PSPS |  | Meet | Meet |  | 2021-04-13 09:22
74022388 |  | SH | 2020 | Keep | OCGC CWSP: X-1104 OH RECOND SKYLINE |  | Scoped | CLSD | 3677 | 3810 | 0 | 0 | 3810 | 0.72159 | 3810 | 0.72159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | EB | 08W | 2021-08-23 13:10 | [10 empty] | 2019-10-08 |  |  | CNTRCT_EST | [5 empty] | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted 8/21 | Full |  |  | Yes |  |  | Submitted request on 8/20. No response from [REDACTED] |  | 1980-01-01 | Y | [12 empty] | 0 | 0 | 3810 | 0.72159 | 0 | 0 | 0.72159 | 0 | 0.72159 | 0 | 0.72159 | 0 | 3810 | 0 | 0 | 0 | 0.72159 |  |  | 2019-12-16 | Yes | N/A | 2020-02-14 | 2020-12-01 | Yes | 2020-12-01 | 2020-01-09 | 2020-03-02 | 2020-11-04 | 2020-11-04 | 2020-11-05 |  | Yes | Shovel Ready |  |  |  |  | 23 |  | MSO Hold | [7 empty] | Oakland | Alameda | 37.8317 | -122.1857 | E.5014312.01 |  | UG |  | 2020 | Q1 | 2019-09-27 | 2020-04-01 | 2020-09-30 | OAKLAND X 1104CR022 | ED.26-F070700000.STRU.POLE | 435 |  |  |  | Meet | Meet |  | 2021-03-12 13:54
35103325 |  | SH | 2020 | Keep | CWSP - MORAGA 1102 & 1104 - OCB |  | Scoped | CLSD | 6506 | 3755 | 3159 | 0 | 6914 | 1.3095 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7225e-16 |  |  | DI | 08W | 2021-08-23 13:10 | [10 empty] | 2019-09-04 | [8 empty] | COMPLETED | No | YES |  |  |  |  | Yes | [9 empty] | Full |  |  | Full |  |  | [REDACTED] to coordinate with [REDACTED] | Full |  |  | Yes |  |  | Submitted on 8/1 to [REDACTED]. Need SSSP |  | 1980-01-01 | Y | [12 empty] | 0 | 0 | 6914 | 1.3095 | 0 | 0 | 1.3095 | -1.7225e-16 | 1.3095 | 0 | 1.3095 | 2907 | 4007 | 0 | 0 | 1.7225e-16 | 1.3095 |  |  |  | Yes | COMP |  |  |  |  | 2019-10-15 | 2019-10-28 | 2020-03-14 | 2020-03-14 | 2020-04-14 |  | Yes | Shovel Ready |  | 5435558.5 |  |  | 20 | [9 empty] | Orinda | Contra Costa | 37.85 | -122.1594 | E.5014544.04 |  |  |  | 2020 | Q1 | 2019-09-04 | 2020-01-25 | 2020-03-20 | MORAGA 1102CB | ED.30-E072500000.STRU.POLE | 1024 |  |  |  | No | Meet
35112076 |  | SH | 2020 | Keep | OCGC FULTON 1107-OH TO UG MARK W SPG |  | Scoped | MAPP | 7980 | 3657 | 7969 | 0 | 11626 | 2.2019 | 10736 | 2.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4451e-16 |  |  | SO | 08W | 2021-08-23 13:10 | [10 empty] | 2019-11-19 | [8 empty] | 100 | Yes | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | CIF submitted Week of 8/12. Veg Scope Needed. CDFW requirements | Full |  |  | Yes |  |  | 10/1/2019 - working on permit revisions |  | 1980-01-01 | Y | [12 empty] | 890 | 0.16856 | 10736 | 2.0333 | 0 | 0 | 2.2019 | 3.4451e-16 | 2.2019 | 0 | 2.2019 | 8489 | 3137 | 0 | 0 | -3.4451e-16 | 2.2019 |  |  |  | Yes | N/A |  |  |  |  | 2019-12-12 | 2019-12-12 | 2020-03-10 | 2020-03-10 | 2020-04-06 |  | Yes | Shovel Ready |  |  |  |  | 46 |  | Underground | [7 empty] | Santa Rosa | Sonoma | 0 | 0 | E.5024097.01 |  |  |  | 2020 | Q1 | 2019-09-27 | 2019-11-24 | 2020-03-23 | FULTON 1107214 | ED.04256.1107 | 178 |  |  |  | Meet | Meet
35057010 |  | SH | 2022 | Keep | CWSP - EL DORADO 2101 - 19752 - PH 2.1 |  | Scoped | PEND | 6914 | 3135 | 3779 | 0 | 6914 | 1.3095 | 0 | 0 | 0 | 0 | 6914 | 1.3095 | 0 | 0 | 0 |  |  | SI | 08W | 2021-10-04 17:00 |  | Y | 2021-05-31 | 2021-05-31 | [6 empty] | 2021-05-06 | 05/06: ADE approved for final - APPROVED - INTO PEND05/05 - 04/28: EST routed for approval; ADE doesn't have docs, not in sap; docs on sharepoint - PAYAPP not submitted, no email notification.04/21: EST target sub (4/21); system slowing upload04/14: [EOD set 05/17]; Change Orders approved; EST target sub (4/16); On Track04/07: Multiple Change Orders; Change Order 1 approved; Change Order 2 in progress; Retaining wall impacts; design changes to possibly move path to reduce retaining wall impacts. Applying CALTRAN detail preferences.03/31: In final rvw to be approved - EOD Set 4/30; EST sent in Change Order.03/30: ADE APPR Status refamiliarizing with condition of est. EDO TBD03/25: Notified order brought back into plan; need new EOD; EOD tentatively set based on duration FC prior to HOLD.12/07: PC20 Joint Pole Task complete11/18: Risk rvw - Est put on Hold11/18: CAL resubmitted[Composite to Wood - Sept List]11/10: EST status TBD - mtg cancelled (Holiday)11/04: EST sub (11/05)10/28: EST sub (10/29); in final QC10/21: EST target sub (TBD); Estimator out of office till 10/22; Walkdown schedule for next Wed.10/16: Final rvw - rtn to CO; Con DWG and OCALC need some updating/QC rvw; not seeing how tied together with UG service. 10/14: ADE working with EST on pushing routing through. EST will route 10/1510/07 - 09/23: ADE target sub (10/02)09/08: CAL submitted for 4th ADE rvw/approval09/04: EST Conversion Complete08/12 - 07/29: EST working with county (details below)07/22: USER STATUS, should be back to ESTS - [REDACTED] looking into07/22 - 07/15: EST - working with County on more specifics of rejection; working on details with LIDAR to be applied; County request(s) will require another contractor to be brought on (Piggy back with QUES - 30-60 day. Geo Tech dependancies (avg 60-90 day impact); EOD ??07/10: County rejected the plans earlier this week. Needs to go back to Estimating to have the OH-UG scope revised.**********06/15: Per [REDACTED]; [REDACTED] approved; APPROVED - PEND06/08: Routed for approval; APPROVED - INTO PEND06/05: ADE in review06/04: CAL submitted for 3rd rvw06/03: EST Target sub (6/8);Changes were requested; applying changes05/27: On Track for (5/29); more changes than anticipated05/20: EST on track (5/22)05/13: EST status - Target sub (5/22)05/06 - 04/29: Est to proceed; foregoing V-Jobwalk; proceeding with current information with ADE [REDACTED]; reviewing to establish timeline03/23: Virtual walkdown to be rescheduled03/17: Cal Engineering build a kmz file with simple R/W and Center Line of road, that we could overlay into Google Earth for our ‘virtual’ walkdown? Information would be beneficial in placing sub-structures/pad-mount structures in the best possible location with R/W, existing ditches, trees, and slopes in mind.01/29: Confirm Target date EOD...03/31: Need EOD Set01/23: Per [REDACTED] - The balance of all five PM’s below should, per our bi-monthly meetings, reflect a revised EOD date of 5/31/2020; Can this date be met, w/remaining est required??01/22: Est out date 4-6 months01/08: EOD push pending resolutions - In talks with PGE Surveying (Unscheduled); Survey needs to sched/Complete; T+30 for Est/Refielding. RISK - additional push based on survey.12/18 <-- 10/30: EL Dorado "permitting"; Hold for review- potential scope change10/23 <-- 10/14: ADE approved for routing - waiting on routing Land/Enviro Cost (dependency) - Sent [REDACTED] cost request10/09: On track for 10/11; 2nd Submittal10/02: Second submittal targeted for 10/119/25: 1st ADE rvw rtn to contractor9/23: ADE assigned [REDACTED]9/19: CAL submitted for 1st ADE rvw9/18: Internal QC corrections - with Engr - push to Fri 9/209/11: on target--> [RCC Issue]9/04: Fielding conducted last week (ADE/Planner - resolving approach issues in design) - CAL to forward communications to [REDACTED]8/21: CAL UD- Fielding in progress until 8/30 - New submission date & Change Orders will be discussed by 8/30 - 1st submittal target to be provided next meeting.8/14: Information flow has started; still clearing up outliers; Focus will be on completing 2.5 and then move into 2.1 & 2.38/7: Contractor on hold for PGE information - Push 1wk ALL dates to allow time for resolution activities.7/31: [**] PGE to confirm scope to true-up date; impacting other phases [2.3 & 2.5]7/24: Sect moving to UG; Requested new scope, Re-Fielding required; CAL to provide an update7/16 <-- 7/3: On track for 8/5; 1st submittal |  | CNTRCT_EST | CALENG |  |  |  | 2021 - Q1- M1 [R2021_81] | COMPLETED | No | Wood | 55 | 0 |  | 2020-07-17 | Yes |  |  |  | 2021-06-05 | 2021-06-05 | [10 empty] | CIF submitted 9/19/19. OH to UG for permitting only. 6/1/21 [REDACTED] reviewing to confirm with [REDACTED] that scope hasn't changed. | [6 empty] | Need Estimating to complete |  | 2020-07-15 | Y | 2020-06-22 | Y |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3095 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-04 17:00 | No | INPR | 2021-11-24 08:00 | 2022-04-06 17:00 |  | 2022-06-07 17:00 | [6 empty] | Yes |  |  | 600000 | 343050.7 |  | 35 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015416.01 | ML | MX | 2021-081 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-11-30 | EL DORADO PH 210119752 | ED.15276.2101 | 1946 |  | PRE |  | No | Meet |  | 2021-06-15 16:11
35145004 |  | SH |  | Keep | PSPS CWSP - ROSSMOOR 1106 - CB |  | Scoped | PEND | 4171.2 | 3073 | 1965 | 0 | 5038 | 0.95417 | 0 | 0 | 5038 | 0.95417 | 0 | 0 | 0 | 0 | 0 | 1965 | 0.37216 | DI | 08W | 2021-08-23 13:10 |  |  | 2020-10-31 | 2020-10-31 | Yes | [5 empty] | 2020-07-13 |  |  | DSGN_CENTR | CONCORD |  |  |  |  | COMPLETED | No | YES | 21 | 1 |  |  | Yes |  | PSPS |  | 2021-07-26 | 2020-11-20 |  |  |  |  | Full | 2021-07-26 | 2023-12-25 |  |  |  | Easements obtained under Rossmoor 1109/PM# 74008802; Enviro reviews have been completed Land needs to clear land tasks | [6 empty] | Moved back to work plan on 6/7/21. 11 permits expired 1/7/21 need to reapply/extend | [7 empty] | Added back to work plan in early June 2021 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.95417 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-15 17:00 |  | INPR | 2021-11-09 08:00 | 2022-02-01 17:00 |  | 2022-03-01 17:00 | [9 empty] | 500000 | 2503856.8 |  | 2 |  |  | Complete | UG 0.4 miles, OH 0.25 miles 13 PSPS devices |  |  |  | Remove |  | Lafayette | Contra Costa | 37.8624 | -122.0862 | E.5025642.01 | ML |  | 2021-128 | 2021 |  |  |  | 2020-09-01 | ROSSMOOR 1106CB | ED.01416.1106 | 3259 |  | PSPS |  | Meet | Meet |  | 2021-06-22 10:22
35145540 |  | SH | 2022 | Keep | PSPS - FROGTOWN 1702 - CB |  | Scoped | PEND | 5780 | 2846 | 3872 | 0 | 6718 | 1.2723 | 0 | 0 | 0 | 0 | 6718 | 1.2723 | 0 | 0 | 0 |  |  | ST | 08W | 2021-09-01 |  | Y | 2020-10-31 | 2020-10-31 | [6 empty] | 2020-09-02 |  |  | DSGN_CENTR | STOCKTON | [6 empty] | wood |  |  |  | 2020-09-21 | Yes |  | PSPS |  | 2021-09-01 | 2021-07-15 | Completed | 2021-03-15 |  |  |  | 2021-09-01 | 2021-07-15 |  |  |  | ** Caltrans DSDD - ERTC date at risk dure to project needing a DSDD . Submitting DSDD permit on 6/30. |  |  | 2020-10-13 | Yes | 2021-10-13 |  | App submitted on 10/1/20 - [REDACTED] checking with City of Angels Camp. |  | 2021-02-12 | Y | 2020-12-01 | Y | 2020-11-30 |  | Finalized drawings provided 8/20/2020. Requeste Arborist quote. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2723 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-03-26 17:00 | No | INPR | 2021-10-28 08:00 | 2022-02-24 17:00 |  | 2022-04-27 17:00 | [6 empty] | Yes |  |  | 4122190 | 696662.7 |  |  |  |  | Complete | waiting for basemaps. Need 3rd party engineer to design bridge hangers within Caltrans ROW | [5 empty] | Angels Camp | Calaveras | 38.0453 | -120.5253 | E.5025634.01 | ML | MX | 2021-136 | 2021 |  |  |  | 2020-09-01 | FROGTOWN 1702CB | ED.16345.1702 | 1316 |  | PSPS |  | Meet | Meet |  | 2021-06-15 10:30
35225594 |  | SH | 2022 | Keep | CNCL ECOP FULTON 1107 - H02-LR604 PH 1.2 |  | Scoped | DOCC |  | 2481.6 | 0 | 0 | 2481.6 | 0.47 | 0 | 0 | 0 | 0 | 2482 | 0.47008 | 0 | 0 | -7.5758e-05 |  |  | SO | 08W | 2021-10-08 17:00 | 2021-02-11 | Y | 2021-05-31 | 2021-05-31 | [8 empty] | To be Canceled - [REDACTED] in the process of Canceling | DSGN_CENTR | SANTAROSA | [17 empty] | Completed | 2021-03-19 | [8 empty] | NEED SOME MAPPING FOR NEW POLE LINE | [22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-10-08 17:00 |  | INPR | 2022-01-18 08:00 | 2022-04-05 08:00 |  | 2022-05-18 17:00 | [9 empty] | 250000 | 25899.1 | [5 empty] | Prioritized | [5 empty] | Santa Rosa | Sonoma | 38.549 | -122.72 |  | ML | UG | [7 empty] | ED.44-GG28000000.STRU.POLE | 637 | 35192292 | ECOP |  | Meet | Meet |  | 2021-06-03 12:07
35056733 |  | SH | 2022 | Keep | CWSP - EL DORADO 2101 - 19752 - PH 1.1 |  | Scoped | PEND | 11252.4 | 1930 | 9322 | 0 | 11252 | 2.1311 | 0 | 0 | 0 | 0 | 11252 | 2.1311 | 0 | 0 | 0 | 8064 | 1.5273 | SI | 08W | 2022-04-11 17:00 |  | Y | 2020-10-31 | 2020-10-31 | [6 empty] | 2020-08-31 | 08/27: QUES rtn for final rvw; APPROVED - INTO PEND08/26: ADE - OK to concur this job; Final corrections communicated08/25: EST to route today08/22: ADE rtn 6th corrections to CO08/20: QUES submitted for 6th ADE rvw08/19: EST target sub (08/21)08/15: ADE rtn 5th corrections to CO08/13: EEI submitted for 5th ADE rvw08/12: On Track08/05: EST target sub (8/13)08/01: ADE rtn 4th corrections to CO; job scope change07/29: ADE in rvw - soft target 8/707/22: QUES submitted for 4th ADE rvw07/22: EST finishing stamping - sub by (7/24); ADE on vacation, rtn Monday 7/2707/15: EST target sub (7/21); finalizing stamping and changes07/08: On Track07/01: EST - ADE requesting change to reduce cost - Chng Ordr to be submitted; Removing PMI-9 from design.06/24: EST push (7/6) - UG design to be changes being applied06/17: EST target sub (6/29)06/12: ADE rtn corrections to CO; 3 locs. could not be opened in SAP for review. EST/ADE coordinated; locs. rvw completed06/03: ADE soft target (6/12)06/01: QUES submitted for ADE rvw05/27: Redesign- full review anticipated with scale of change - firm up ADE rvw duration05/20: EST status (6/1); UG portion going through rvw/stamping05/13: Pending stamps - target sub (5/15)05/06: On Track05/01: Very near ready to turn in for ADE review. But still need stamps04/29: EST close to submittal04/15: Rcv'd response from county; Change Order to be submitted. Going to proceed, should finish quick.04/08: Required survey (rcv'd Mon 4/6); submitting change order04/01: Applying changes;03/18: Rcving Maps - Going to Google earth/overlays - Meeting; more update coming next week03/04: xxx02/20 - 02/19: EST - Check in on base maps; [REDACTED] - just finished going through it, Coordination with EST to take a look and talk if you have any questions. 01/29: Confirm Target date EOD...01/23: Per [REDACTED] - The balance of all five PM's below should, per our bi-monthly meetings, reflect a revised EOD date of 5/31/2020; Can this date be met, w/remaining est required??01/09: EOD push pending resolutions - In talks with PGE Surveying (Unscheduled); Survey needs to sched/Complete; T+30 for Est/Refielding. RISK - additional push based on survey.12/18 <-- 12/11: UG Surveying (Internal actions item); Easement issue - Customer declined access/redesign required (Construction May? confirm - Q2/Q3)12/04: Will remain UG - can proceed; Fielding required - Q3 contruction target at RISK; dependant on weather and scope of work.11/13: On hold for Eldorado UG/Permitting10/29: Push/Est on Hold - El Dorado meeting; requiring more detail for work in there area. Scheduled job walk; design may go back to OH. (Construction in 2020): 1 month for next steps; EOD move to Jan (assessing impacts)10/23: Going back to redesign (scoping did not capture this approach) - Push 1wk10/21: ADE rtn 2nd corrections to contractor - Cannot install subsurface TX in snow area10/16: QUES submitted for 2nd ADE rvw - Scope changed from OH to UG on Sly Park Rd.Estimation Completed Documents uploaded to Sap10/16: Stamping - EOW9/25 - 10/09: On track for 10/169/11: 1) Meeting in field today - going in for scope change (line being redirected around property). 2) working redesign - requires additional easement(s)--> [RCC Issue]9/04: Awaiting ADE response8/28: scope is changed, planner suggested to change Overhead to Underground on Sly Park Rd. - QUES/ADE working on resolution8/23: REMOVED FROM AUG Priority - QUES communicated - advised early last week that it was going UG and not overhead. QUES turned in the full project as an overhead harden in place, and the JO shot us over the change. Fielding for UG. Target dates to be updated.8/20: ADE working through review8/16: 1st ADE corrections rtn to contractor8/12: ADE [REDACTED]: QUES Submitted for 1st ADE rvw7/16 - 8/7 : On track7/3: QUES to review to provide review on 1st ADE Submital |  | CNTRCT_EST | QUES |  |  |  | 2020 - Q3- M8 [R2021_79] | COMPLETED | No | Wood | 57 | 0 |  | 2020-09-18 | Yes |  |  |  | 2020-09-15 | 2020-09-15 |  |  |  |  | Full | 2020-05-01 | 2020-05-01 | Full |  |  | Waiting on Finalized Drawings | Full | [5 empty] | [REDACTED] submitted to Eldorado County on 3/30/21 - Will start reviewing after Phase 4.1 |  | 2020-07-03 | Y | 2020-06-15 | Y |  |  | Complete | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1311 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-04-11 17:00 | No | INPR | 2022-05-04 08:00 | 2022-10-05 17:00 |  | 2022-12-21 17:00 | [5 empty] | 2020-12-25 | Yes |  |  | 725000 | 744111.5 |  | 57 |  |  | Complete |  |  |  |  | Remove |  | Pollock Pines | El Dorado | 38.7821 | -120.6094 | E.5015417.01 | MX | MX | 2021-079 | 2021 | 2020 Reserve | 2020-05-31 | 2020-09-01 | 2020-10-31 | EL DORADO PH 210119752 | ED.15276.2101 | 1946 |  | PRE |  | No | Meet |  | 2021-06-22 09:18
35144944 |  | SH | 2022 | Keep | PSPS - SNEATH LANE 1107 - LR 48338 |  | Scoped | PEND | 739.2 | 1348 | 0 | 0 | 1348 | 0.2553 | 0 | 0 | 0 | 0 | 1348 | 0.2553 | 0 | 0 | 0 |  |  | PN | 08W | 2022-04-28 17:00 |  |  | 2020-10-31 | 2020-10-31 | Yes | [5 empty] | 2020-05-29 |  |  | DSGN_CENTR | FRESNO |  |  |  |  | COMPLETED | No | No | 3 | 0 |  |  | Yes |  | PSPS |  | 2021-10-05 | 2021-10-05 | [5 empty] | 2021-10-05 | 2021-10-05 |  |  |  | ** Caltrans DSDD application / permit submitted. Enviro reviews completed. |  |  |  | Yes | 2024-12-31 |  | Cal Trans permit only , rest of project on private property | [7 empty] | DSDD - Caltrans Delay | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2553 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2022-04-28 17:00 | No | INPR | 2022-06-15 08:00 | 2022-07-22 17:00 |  | 2022-08-19 17:00 | [6 empty] | Yes |  |  | 500000 | 1513389.3 |  | 3 |  |  | Complete | UG 0.14 miles, install PMI9, 5 PSPS devices |  |  |  | Remove |  | South San Francisco | San Mateo | 37.6433 | -122.4679 | 35144944 | ML |  | 2021-135 | 2021 |  |  |  | 2020-09-01 | SNEATH LANE 1107CB | ED.56-E031100000.STRU.POLE | 3550 |  | PSPS |  | Meet | Meet |  | 2021-06-08 10:51
35145003 |  | SH |  | Keep | PSPS CWSP - MORAGA 1103 - CB |  | Scoped | PEND | 1161.6 | 1268 | 420 | 0 | 1688 | 0.3197 | 0 | 0 | 1688 | 0.3197 | 0 | 0 | 0 | 0 | 0 | 1688 | 0.3197 | DI | 08W | 2021-08-23 13:10 |  |  | 2020-10-31 | 2020-10-31 | Yes | [5 empty] | 2021-06-15 |  |  | DSGN_CENTR | CONCORD |  |  |  |  | COMPLETED | No | YES | 10 | 4 |  |  | Yes |  | PSPS |  | 2020-07-15 | 2020-07-15 |  |  |  |  | Full | 2020-07-17 | 2020-07-17 | Full |  |  | CIF Submitted 6/1/20 | Full |  | 2021-07-01 |  |  |  | Moved back to work plan on 6/7/21. Have 2 of 3 permits (need 1 more for Town of Moraga) | [7 empty] | Added back to work plan in early June 2021 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3197 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-15 17:00 | No | INPR | 2021-08-24 08:00 | 2021-11-02 17:00 |  | 2021-11-30 17:00 | 2020-12-10 | 2021-06-15 |  |  |  |  | Yes | No click dates - ready to start work on 6/15/21 |  | 500000 | 1167895.2 |  | 5 |  |  | Complete | UG 0.22 miles, PM 3WSW, 4 PSPS devices |  |  |  | Remove |  | Orinda | Contra Costa | 0 | 0 | E.5025641.01 | ML |  | 2021-131 | 2021 |  |  |  | 2020-09-01 | MORAGA 1103CB | ED.01380.1103 | 2631 |  | PSPS |  | Meet | Meet |  | 2021-06-22 08:55
35116801 |  | SH | 2021 | Keep | CWSP-MIWUK 1702-LR 6018-PHASE 1.3 |  | Scoped | CONS | 7835 | 580 | 6197 | 0 | 6777 | 1.2835 | 1954 | 0.37008 | 4823 | 0.91345 | 0 | 0 | 0 | 0 | 0 |  |  | YO | 08W | 2020-07-22 |  | Y | 2020-04-15 | 2020-04-15 | [6 empty] | 2020-05-28 | 04/15: EST routed for approval; APPROVED - INTO PEND04/13: ADE rtn 4th corrections to CO - EST to cancel conflicting 07D PMS (x4)04/08: ADE status (4/8)??04/03: EEI sub for 4th ADE rvw04/01: Est to firm up sub date (4/3)??03/31: ADE rtn 3rd corrections to CO03/24: EEI submitted for 3rd ADE rvw03/18: Est confirmed sub (3/20) - 3/24 clearing up some conflicting information to apply corrections.03/17: ADE rtn 2nd corrections to CO03/11 - 03/03: Push ADE target 3/13; task with getting correct process in place for standards, Rule 20A picking back up - working with Estimators who took over work.02/25: ADE confirmed working 2nd rvw02/25: EEI submitted for 2nd ADE rvw - [PRELIM DWG ready]02/19 <-- 01/22: EST to follow up - [REDACTED] constructability rvw, confirm scope change or not (location shift between PMs); Computer issues - working to recover files (2wk per TSC)01/08: On Track12/18: EST Priority shifts; Ocalc end/rise drop need to be updated on each location12/06: ADE rtn corrections to contractor (EST access issues - req resubmit)11/27 <-- 11/20: ADE priorities may impact; Push 2wk (3-4 projs being balanced)11/13: Check w ADE - On track?11/06: Check in with ADE10/29: With ADE for rvw10/22: ADE assigned [REDACTED] - Push 2wk for 1st rvw duration10/16: ADE to be assigned (waiting for 2020 priority list)10/14: EEI submitted for 1st ADE rvw10/09: On Track for 10/1410/02 <-- 9/11: On Track09/04: On Track for 1st Submittal 11/12 |  | DSGN_CENTR | EEI |  |  |  | 2020 - Q2- M4 [R40] | COMPLETED |  | Comp/Wood | 40 | 48 |  |  | Yes | [9 empty] | Full |  |  | Full |  |  |  | Full |  |  | Yes | 2021-12-31 |  | Annual Permit |  | 2020-07-27 | Y | 2020-07-20 | Y | [10 empty] | 0 | 0 | 1954 | 0.37008 | 3843 | 0.72784 | 1.0979 | 0.18561 | 1.0839 | 0.19394 | 1.2778 | 6197 | 550 | 0 | 0 | 0.014015 | 0.3661 |  |  | 2020-07-06 | Yes | COMP | 2020-08-10 | 2021-05-21 17:00 | Yes | 2021-07-02 17:00 | 2020-07-22 | 2021-02-26 | 2020-08-25 | 2021-05-03 |  | 2020-07-13 | Yes | Work Complete - [REDACTED] to check with contractor on paper work. |  | 2333945.2 |  |  | 41 | [9 empty] | Twain Harte | Tuolumne | 38.0441 | -120.2479 | E.5014730.03 - JM |  |  | 2020-040 | 2020 | Q3 | 2020-04-30 | 2020-04-30 | 2020-06-05 | MIWUK 17026018 | ED.16366.1702 | 2411 |  | PRE |  | No | Meet |  | 2021-06-24 09:29
35226632 |  | SH | 2022 | Keep | CWSP - POTTER VALLEY PH 110564118 PH 1.2 |  | Scoped | PEND |  | 560 | 0 | 0 | 560 | 0.10606 | 0 | 0 | 0 | 0 | 560 | 0.10606 | 0 | 0 | 0 |  |  | HB | 08W | 2021-08-23 13:10 | 2021-03-31 | Y | 2021-05-31 | 2021-05-31 |  | 2021-06-15 | Yes |  |  |  | 2021-05-12 | [UG] Basemap & Pre-Engr Mtg 3/3105/07: APPROVED - INTO PEND05/05: Pending Approval05/04: ADE approved; in final rvw for approval05/03: EEI routed for approval05/01: ADE rtn rvw to CO04/28: EST to check on submittal, UNSE Status,04/21: EST Working on final revisions04/20: EEI reported submitted04/14: On Track04/05: Fielding complete; Still under review for base map requirement.03/31: Pre-Engr Mtg complete; Confirm base map need??03/31 - 03/24: Fielding scheduled03/17: Scoped03/10 - 2/24: [EOD PUSH] Awaiting Scope Clarification (preferred scope in SAP has OH & UG) – [REDACTED] to assist in separating PMs |  | CNTRCT_EST | EEI |  |  |  | 30d - Mar FT 210_430 | COMPLETED | [6 empty] | Yes |  |  |  | 2021-08-02 |  | In Progress | 2021-07-29 |  |  |  | 2021-08-02 |  |  |  |  | [REDACTED] to submit CIF |  |  | 2021-06-04 | Yes | 2024-12-31 |  | No permit needed - Private Property | [7 empty] | Preinspection to be started week of 6/15 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.10606 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-16 17:00 | No | INPR | 2021-11-17 08:00 | 2022-03-30 17:00 |  | 2022-05-31 17:00 | 2021-05-11 | 2021-05-12 | 2021-08-31 07:00 | 2021-08-31 16:00 |  |  | Yes |  |  | 475000 | 12757.6 | [5 empty] | Prioritized | [5 empty] | Potter Valley | Mendocino | 39.362 | -123.1283 | [10 empty] | ED.04228.1105.RECL | 43 | 35219280 | CWSP |  | Meet | Meet |  | 2021-06-22 10:30
35031662 |  | SH | 2020 | Keep | CWSP - LOS GATOS 1106 - LB44 - PHASE 2.1 |  | Scoped | FICL | 2978 | 511 | 2467 | 0 | 2978 | 0.56402 | 2978 | 0.56402 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1676e-16 |  |  | DA | 08W | 2021-08-23 13:10 | [10 empty] | 2019-10-07 | waiting on GC review |  | DSGN_CENTR | SANJOSE |  |  |  |  | 100 | No | [5 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | [REDACTED] to check on CIF - EOD 7/30/19; SJ Waterworks (notification only); Midpeninsula Open Space | Full |  |  | Yes |  |  | Santa Clara County |  | 1980-01-01 | Y | [12 empty] | 0 | 0 | 2978 | 0.56402 | 0 | 0 | 0.56402 | 5.1676e-16 | 0.56402 | 0 | 0.56402 | 2467 | 511 | 0 | 0 | -5.1676e-16 | 0.56402 |  |  | 2020-02-18 17:00 | Yes | N/A | 2020-02-12 | 2020-03-25 | Yes | 2020-03-25 17:00 | 2020-01-13 | 2020-02-03 | 2020-02-10 | 2020-03-27 | 2020-03-25 |  | Yes | Shovel Ready |  | 1109989 |  |  | 13 |  | 6/21 - next week will have additional PM numbers to add tohe list for new segments | [7 empty] | Los Gatos | Santa Clara | 37.1933 | -122.0204 | E.0000130.01 |  |  | 2020-079 | 2020 | Q1 | 2019-10-04 | 2020-02-02 | 2020-03-23 | LOS GATOS 1106LB44 | ED.08202.1106 | 841 |  |  |  | No | Meet
35114040 |  | SH | 2022 | Keep | CWSP - PINE GROVE 1102 - LR1222 - PH 1.2 |  | Scoped | CONS | 7188 | 477 | 7362 | 0 | 7839 | 1.4847 | 0 | 0 | 0 | 0 | 7839 | 1.4847 | 0 | 0 | 0 |  |  | ST | 08W | 2020-07-17 | 2019-08-22 | Y | 2020-04-24 | 2020-04-24 | Yes | [5 empty] | 2020-07-16 | 07/14: EOD (8/14); Apply [REDACTED] feedback, send for CALTRANS rvw; process for approval.07/09: submitted the Cal Trans poles that were in the CRZ zone; Plan and Profile project will be getting submitted for the 4 UG portions for the Cal Trans permit end of next week04/26: Redesign Caltrans CRZ. Needing to relocate poles.- Chg Order submitted**********04/24: APPROVED - INTO PEND04/23: Final approval corrections rtn to CO4/21: EST sub date (4/24) - target tomorrow04/19: ADE rtn 4th corrections to CO04/14: ADE status??04/09: EN submitted for 4th ADE rvw04/07: EST to firm up sub date (4/10)04/03: ADE rtn 3rd corrections to CO03/31: Target 4/1; PE Stamping; EN submitted for 3rd ADE rvw03/24: EST firm up sub (3/23)??03/20: ADE rtn 2nd corrections to CO03/17: ADE status/target (3/17)??03/12: EN submitted for 2nd ADE rvw03/10: Push to 03/20 - Addressing some construction concerns; equipment concerns3/05: EST/ADE working through markups3/03: EST Confirm ON TRACK2/25: EST confirm date (03/06)2/19: ADE Rtn 1st corrections to CO01/28 - 01/21: ADE Status??01/14: ADE Status (~2wk)??01/08: ADE priorities/holidays12/24: ADE assigned [REDACTED]01/07 <-- 12/03: ADE 1st rvw holding for resource availability & assignment11/19 <-- 10/01: ADE to be assigned - waiting on 2020 priority list; [11/19] 2nd push 1 9/24: EN submitted for 1st ADE rvw9/24: Submittig today 9/249/17 <-- 9/03: On Track for 9/238/13 Fielding planned for EOM (Aug) |  | CNTRCT_EST | ENENG |  |  |  | Redesign | RD0.0_Rdsn - Estimating Redesign |  | Obsolete (CONS+) | 0 | 0 |  |  | Yes |  |  |  | 2021-10-05 | 2021-10-05 |  |  |  |  | Partial | 2021-10-05 | 2021-10-05 | Partial |  |  | ** Caltrans DSDD - Pilot Project - district 10 permit expected 8/19/2020 - PERTC | Partial |  |  | Yes | 2024-12-31 |  | Permit Not Required |  | 2020-07-27 | Y | 2020-06-24 | Y |  |  | 95% complete as of 7/21/20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4847 | 0 | 0 | 1.4559 | 7193 | 494 | 0 | 1.4559 | 0 | 0 |  |  | 2020-07-06 | Yes | COMP | 2020-07-29 | 2021-08-02 17:00 |  | 2021-09-01 17:00 | 2020-07-17 | 2020-07-21 | 2021-08-09 07:00 | 2021-08-13 17:00 |  | 2020-07-16 | yes | Need to pull forward - 6/15/21 |  | 3107232.1 | 2681202.8 |  | 48 | [9 empty] | Kit Carson | Amador | 0 | 0 | E.5014745.02 |  |  | 2020-024 | 2020 | Q3 | 2020-04-30 | 2020-08-15 | 2020-09-29 | PINE GROVE 11021222 | ED.16375.1102 | 2271 |  | PRE |  | No | Meet |  | 2021-06-24 09:30
35094513 |  | SH | 2022 | Keep | CWSP-STANISLAUS 1702-LR1804&4905-PH 1.1 |  | Scoped | PEND | 10091 | 172 | 9383 | 0 | 9555 | 1.8097 | 0 | 0 | 0 | 0 | 9555 | 1.8097 | 0 | 0 | 0 |  |  | ST | 08W | 2021-10-18 | 2019-09-18 | Y | 2020-08-31 | 2020-08-31 | [6 empty] | 2020-06-29 | 06/23: EST target sub (6/26)06/16: ADE soft target (6/20) - ADE rtn 3rd correctionst to CO06/15: [REDACTED] submitted for 3rd ADE rvw06/09 - 05/26: EST target sub (6/05); (6/09); (6/12)05/24: ADE rtn 2nd corrections to CO5/18: ADE target (5/22); ok'd EST to sched constructability rvw05/15: BCF submitted for 2nd ADE rvw - [PRELIM DWG ready]05/12: On Track05/05 - 04/28: EST to firm up Sub date (5/15)04/07: ADE rtn 1st corrrections to CO04/03: BCF updated DO Field Notes in SAP for review 03/26: In ADE rvw - request CO provide detail field notes per the attached ADE/Contractor guidelines03/23: ADE assigned [REDACTED] - firm up rvw date (4/11)??03/17 <-- 10/29: ADE to be assigned10/22: PUSH 1 month - ADE resourcing10/15: Pending ADE assignment - waiting for 2020 Priority list10/11: BCF submitted for 1st ADE rvw10/08: On Track; (EES changes adding additional activities to processing)10/01: Push to 10/11 completing 9/24 task9/24: Push to 10/08 1st submittal - originally estimated to be 64 poles in 1.9 miles of conductor. Our fielding efforts revealed a large number of infractions (primarily tree attachments) that will increase the total number of poles to about 110- this is a 72% 9/17: On Target for 1st ADE submittal |  | CNTRCT_EST | BCANDF |  |  |  | 2020 - Q3- M7 [R153] | R3.3 - EST Implementing Corrections |  | Comp | 27 | 61 |  |  | Yes |  |  |  | 2021-10-05 | 2021-10-05 | Completed | 2021-02-18 |  |  |  | 2021-10-05 | 2021-10-05 |  |  |  | ** Caltrans DSDD | [6 empty] | DSDD Delay - County requires Caltans permit before County approval. Submitted to calaveras on 6/30/20 |  | 2021-11-30 |  | 2021-10-18 |  |  |  | DSDD - County won't allow partial | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.8097 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-03-19 17:00 | Yes | INPR | 2021-12-30 08:00 | 2022-03-09 08:00 |  | 2022-05-09 17:00 | [6 empty] | Yes |  |  | 250000 | 3621818.4 |  | 92 |  |  | Complete | [6 empty] | Arnold | Calaveras | 0 | 0 | E.5014540.01 | ML | MX | 2021-084 | 2021 |  | 2020-07-31 | 2021-02-26 |  | STANISLAUS 17021804 | ED.16282.1702 | 2712 |  | CWSP |  | No | Meet |  | 2021-06-15 10:34
35114431 |  | SH | 2020 | Keep | CWSP - MORAGA 1101 - LR108540 - PH5 |  | Scoped | CLSD | 7673 | 166 | 7421 | 0 | 7587 | 1.4369 | 7587 | 1.4369 | 0 | 0 | 0 | 0 | 0 | 0 | -1.8948e-15 |  |  | DI | 08W | 2021-08-23 13:10 | [10 empty] | 2019-12-17 | [15 empty] | Yes | [9 empty] | Full |  |  | Full |  |  | Waiting on land - estimating redesigning around land issue - EOD 12/5 | Full |  |  | Yes |  |  | PM submitted request on 9/5. Need Cons dates to submit road closure request |  | 1980-01-01 | Y | [12 empty] | 0 | 0 | 7587 | 1.4369 | 0 | 0 | 1.4369 | -1.8948e-15 | 1.4369 | 0 | 1.4369 | 7421 | 166 | 0 | 0 | 1.8948e-15 | 1.4369 |  |  |  | Yes | N/A |  |  |  |  | 2020-01-02 | 2020-01-06 | 2020-03-27 | 2020-03-27 | 2020-03-23 |  | Yes | Shovel Ready |  |  |  |  | 66 | [9 empty] | Concord | Contra Costa | 0 | 0 | E.5014544.05 |  |  |  | 2020 | Q1 | 2019-12-06 | 2020-01-02 | 2020-03-31 | MORAGA 1101108540 | ED.30-E060900000.STRU.POLE | 319 |  |  |  | Meet | Meet
35223037 |  | SH | 2021 | Keep | PSPS - OAKHURST 1101 - OAKHURST |  | Scoped | PEND |  | 105.6 | 0 | 0 | 105.6 | 0.02 | 0 | 0 | 106 | 0.020076 | 0 | 0 | 0 | 0 | -7.5758e-05 |  |  | YO | 08W | 2021-07-16 17:00 | 2021-02-26 | Y | 2021-03-31 | 2021-03-31 | [6 empty] | 2021-05-18 |  |  | DSGN_CENTR | FRESNO | [11 empty] | Yes |  |  |  | 2021-05-17 | 2021-05-17 | N/A |  | NA |  | Full | 2021-05-17 | 2021-05-17 | Full |  |  | 3/31/2021 approval recieved | Full |  |  | Yes | 2021-12-24 |  | No permit needed |  | 2021-06-21 | Y | 2021-06-18 | Y | 2021-05-17 |  | 1 day of work - Waiting on ERTC | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 2021-07-16 17:00 | No | INPR | 2021-08-11 08:00 | 2021-08-25 08:00 |  | 2021-11-01 17:00 | 2021-05-17 | 2021-05-18 | 2021-09-17 07:00 | 2021-09-23 16:00 |  |  | Yes |  |  | 500000 | 318263.3 | [11 empty] | Oakhurst | Madera | 37.3227 | -119.6344 |  | ML | UG | [7 empty] | ED.72-07214A0000.STRU.POLE | 847 |  | PSPS |  | Meet | Meet |  | 2021-06-22 15:34
Note on L1: [REDACTED] This data is required by the Fed. Monitor.This is the circuit footage of primary that was moved from OH to UG.This adds into your total planned mileage.
Note on M1: [REDACTED] This data is required by the Fed. Monitor.This is circuit footage of primary that was hardened in place and includes the relocated footage.This adds into your total planned mileage.