## Slide 1: Update Rx Script Count Audit Issue for DEA – Project Status
Onshore: | 0% | Offshore: | 100%
Overall Status Trend = Positive |  |  | 
Overall | G | Schedule | G
Scope | G | Cost | G
Resources | G |  | 
Key Messages
The overall status is neutral. The remains in Green status. The project is currently in Deploy Phase and is on track to be fully deployed by mid June.
Critical issues / Risks + Mitigation | Owner/ Due Date
I/R: No issues or risks identified at this time. M: | Owner Name/ MM/DD/YY
I/R: M: | Owner Name/ MM/DD/YY
I/R: M: | Owner Name/ MM/DD/YY
Key Milestones / Dependencies (Non-SDLC) | Baseline | Forecast | At Risk?
Project Closure | 7/10/15 | 7/10/15 | N
Accomplishments This Period:
System Testing Completed.
Documentation completed.
Move request initiated.
Week Ending 15 June 2015
Financial | Capital | Expense | Total
Plan Budget | 0 | 20,000 | 20,000
Actual Spend | 0 | 4,400 | 4,400
Forecast | 0 | 9,600 | 9,600
Total | 0 | 14,000 | 14,000
Budget Variance | 0 | 6,000 | 6,000
Contractor Resource Mix:
SDLC Start /End Dates | Initiation | Requirements | Design | Build | QA | Pilot | Deploy | Warranty
Final Release | 04/08/2015 – 05/07/2015 | 05/08/2015 – 05/25/2015 | 05/26/2015 – 05/26/2015 | 05/27/2015 –06/03/2015 | 06/04/2015 – 06/11/2015 | NA | 06/12/2015 – 06/18/2015 | 06/19/2015 – 07/10/2015
Project Manager: Kraig Keegan
Description: Check for the weekly Rx script count file to be current. If it is not current, force the job to end and get the current file
Activities Next Upcoming Period:
Deploy the changes to production.
Warranty support