## Slide 1: Update Rx Script Count Audit Issue for DEA – Project Status
Overall Status Trend = Positive |  |  | 
Overall | G | Schedule | G
Scope | G | Cost | G
Resources | G |  | 
Key Messages
The overall status is trending upward. The project is in Green status due to just being started. The project is currently in Requirements Phase and is on track to be fully deployed by early June.
Critical issues / Risks + Mitigation | Owner | Due
None |  | 
Key Milestones | Baseline | Forecast | At Risk?
Functional Requirements | 5/25/15 | 5/25/15 | N
Technical Design | 5/26/15 | 5/26/15 | N
Build Completed | 6/2/15 | 6/2/16 | N
Accomplishments This Period:
Project has been kicked off.
Project schedule has been set
Resources have been assigned
Business Requirements are complete
Week Ending 25 May 2015
Financial | Capital | Expense | Total
Plan Budget | 0K | 20K | 20K
Actual Spend | 0K | .2K | .2K
Forecast | 0K | 19.8K | 19.8K
Total | 0K | 20K | 20K
Budget Variance | 0 | 0K | 0K
Resource Mix:
Onshore: | 10% | Offshore: | 90%
Key Decisions/Change Requests | Owner | Due
None |  | 
Release | Initiation | Requirements | Design | Build | QA | Pilot | Deploy | Warranty
Final | 4/8/15 – 5/7/15 | 5/8/15 – 5/25/15 | 5/26/15 – 5/26/15 | 5/27/15 – 6/2/15 | 6/3/15 – 6/4/15 | NA | 6/5/15 – 6/5/15 | 6/8/15 – 6/25/15
Project Manager: Kraig Keegan
Description: The weekly job calculating ceiling limits for prescription does not verify that the latest sales data has been received. When this occurs, the job needs to be forced to fail and corrective actions to get the most current data need to be taken.

## Slide 2: Update Rx Script Count Audit Issue for DEA– Project Status
Key Dependencies |  |  |  |  | 
Area | Project | Description | Status | Owner | Due Date
Issues and Risk Detail |  |  |  |  | 
Type | Project | Description | Action Needed | Owner | Due Date
Week Ending 25 May 2015
Project Manager: Kraig Keegan